## Test Year
Schedule D (Historical Test Year)
Kentucky Power Company
Case No. 2025-00257
Construction Projects for the Historical Test Year
June 2024 - May 2025
Definitions:
| (E)* | Represents AFUDC Debt and AFUDC Equity (Cost Components 023 and 024, respectively)
| (F)* | Represents allocated construction overheads (Cost Component 020)
| n.m. | Not meaningful
| Property Acctg | Property Accounting perpetual administrative projects used to transfer plant in service or hold temporary charges later cleared to other work orders, e.g., construction overheads, suspense, labor accrual, etc.
Actual Accumulated Costs - June 2024 through May 2025
Line No. | Project No. | Description of Project | Most Recent Budget Estimate | Construction Amount | AFUDC Capitalized | Indirect Costs Other | Total Cost | Estimated Physical Percent Completed June 2024 Through May 2025 | GLBU-Project
(A) | (B) | (C) | (I) | (D) | (E)* | (F)* | (G=D+E+F) | (H) = (G)/(I)
1 | GLBU 110 (Distribution)
2 | 000001818 | KY/Svc Restoration NonMjr Evt | 5733590.512 | 4742443.01 | 15608.21 | 899232.47 | 5657283.69 | 98.67%
3 | 000002241 | KP-Damage Claims-Reimburse | 341653.849 | 325230.61 | 795.67 | 62275.71 | 388301.99 | 113.7%
4 | 000004737 | KPSectionalizing Program | 472362.16 | 941716.2 | 3504.51 | 166713.93 | 1111934.64 | 235.4%
5 | 000005234 | KyPCo-D Capital Software Dev | 0 | 3106479.94 |  |  | 3106479.94 | n.m.
6 | 000007558 | KP-PQ-QOS Mitigation | 26856.423 | 16103.32 | 21.95 | 2365.15 | 18490.42 | 68.85%
7 | 000007599 | KP-Failed Equip No Outage | 3560506.564 | 3462281.43 | 13685.89 | 600147.96 | 4076115.28 | 114.5%
8 | 000007615 | KP-Cust Req Relocate | 123109.092 | 49227.31 | 96.77 | 26836.58 | 76160.66 | 61.86%
9 | 000007818 | KP/Small Local Asset Improv | 3126035.608 | 3077713.86 | 28414.16 | 563917.28 | 3670045.3 | 117.4%
10 | 000008169 | KP Asset Imp Eng Support | 911308.399 | 145051.75 |  |  | 145051.75 | 15.92%
11 | 000008184 | KP Asset Programs Eng Support | 1138373.015 | 270712.95 |  |  | 270712.95 | 23.78%
12 | 000016528 | KYCutout-Arrester | 402561.255 | 261592.67 | 3685.48 | 44320.88 | 309599.03 | 76.91%
13 | 000025229 | 2018 Gen Plt Cap Blkt - KYPC-D | 557689.973 | 751750.77 | 28564.15 |  | 780314.92 | 139.9%
14 | 110KYLSBO | Dist KY Lease BO | 0 | 43332.16 |  |  | 43332.16 | n.m.
15 | A15710085 | Olive Hill Station TTMP | 26839.102 | 2973.37 | 2376.55 | 273.67 | 5623.59 | 20.95%
16 | A15710086 | Hayward Station TTMP | 0 | 1405.32 | 4152.89 | 267.64 | 5825.85 | n.m.
17 | A20045031 | South Pikeville Station NIP | 0 | 101.76 | 280.63 | 21.32 | 403.71 | n.m.
18 | A20045075 | Prestonsburg NIP Track 6 | 0 | 69.75 | 192.37 | 14.62 | 276.74 | n.m.
19 | A20045086 | Olive Hill Station NIP | 0 | 19.99 | 55.14 | 4.19 | 79.32 | n.m.
20 | A20045087 | Daisy Station NIP | 0 | 77.85 | 214.7 | 16.31 | 308.86 | n.m.
21 | A20077007 | Soft Shell Sta TTMP | 6760.012 | 49.67 | 136.96 | 10.41 | 197.04 | 2.915%
22 | A20077008 | Bulan Sta TTMP | 5497.736 | 36.61 | 100.96 | 7.68 | 145.25 | 2.642%
23 | A20077010 | Haddix Sta TTMP | 6045.979 | 46.52 | 128.27 | 9.75 | 184.54 | 3.052%
24 | A20077011 | Jackson Sta TTMP | 7974.449 | 31.65 | 87.29 | 6.63 | 125.57 | 1.575%
25 | A20077013 | Engle Sta TTMP | 6156.777 | 32.38 | 89.31 | 6.79 | 128.48 | 2.087%
26 | A20077017 | Whitesburg Sta TTMP | 7080.007 | 108.78 | 110.31 | 19.05 | 238.14 | 3.364%
27 | A20077018 | Mayking Sta TTMP | 7402.63 | 40.77 | 112.44 | 8.54 | 161.75 | 2.185%
28 | A20077019 | Collier Sta TTMP | 0 | 69.64 | 192.06 | 14.59 | 276.29 | n.m.
29 | A20077022 | South Pikeville Sta TTMP | 0 | 36.35 | 100.24 | 7.61 | 144.2 | n.m.
30 | A20705068 | Coleman Stn Needs Assessment | 0 | -8383.79 | -1259.46 | -1947.45 | -11590.7 | n.m.
31 | A20705085 | Tom Watkins Station Needs Asmt | 0 | 109.69 | 302.48 | 22.98 | 435.15 | n.m.
32 | A20934001 | Falcon Elim Cust DC System | 26785.15 | 606252.34 | 9604.12 | 87864.45 | 703720.91 | 2627%
33 | A21222009 | Tygart Station | 0 | 4271.81 | 18684.77 | 953.63 | 23910.21 | n.m.
34 | A21222015 | Jackson Sta TTMP | 0 | 1294.27 | 1535.56 | 349.86 | 3179.69 | n.m.
35 | A21505006 | Jackson Station NIP | 0 | 128.56 | 354.54 | 26.94 | 510.04 | n.m.
36 | A21505009 | Coalton NIP | 0 | 34.62 | 95.49 | 7.25 | 137.36 | n.m.
37 | A23067001 | Mobile KP-2 (4089) Rebuild | -97901.361 | 321676.45 | 9411.38 | 96051.67 | 427139.5 | -436.3%
38 | A23088001 | Barrenshe Mobile Pad Install | 0 | 17468.7 | 12017.54 | -69935.53 | -40449.29 | n.m.
39 | A23750004 | Keyser Station XFRMR Failure | 0 | 268291.18 | 3148.85 | 89907.32 | 361347.35 | n.m.
40 | A23928006 | Pikeville Cable Spare Purchase | 0 | 53981.64 | 478.47 | 8385.03 | 62845.14 | n.m.
41 | A24022009 | Argentum Sta TTMP | 0 | 3961.88 | 319.75 | 585.59 | 4867.22 | n.m.
42 | A24038004 | New Camp Sta TTMP | 2258.224 | 3427.85 | 347.55 | 506.66 | 4282.06 | 189.6%
43 | A24083001 | Catalpa TS TTMP | 0 | 855.51 | 0.89 | 126.45 | 982.85 | n.m.
44 | A24083003 | Beaver Creek TS TTMP | 0 | 406.8 | 1.09 | 60.12 | 468.01 | n.m.
45 | A24083004 | Busseyville 138kV Sta TTMP | 0 | 855.51 | 0.89 | 126.45 | 982.85 | n.m.
46 | A24083006 | Jenkins 69kV Sta TTMP | 0 | 244.09 | 0.66 | 36.07 | 280.82 | n.m.
47 | A24112002 | Argentum Sta TTMP | 3507.704 | -3910.49 | -309.16 |  | -4219.65 | -120.3%
48 | A24112010 | Lovely Sta TTMP | -2855.779 | 25.94 |  |  | 25.94 | -0.9083%
49 | A24112012 | New Camp Sta TTMP | -2855.779 | -3380.88 | -338.39 |  | -3719.27 | 130.2%
50 | A25101001 | 47th St Sta TTMP | 0 | 56.83 | 61.67 | 9.78 | 128.28 | n.m.
51 | A25101002 | Ashland (25th St) Sta TTMP | 0 | 115.5 | 33.38 | 17.82 | 166.7 | n.m.
52 | A25101003 | Argentum Sta TTMP | 0 | 12.84 | 35.41 | 2.69 | 50.94 | n.m.
53 | A25101005 | Tygart Sta TTMP | 0 | 4.3 | 11.86 | 0.9 | 17.06 | n.m.
54 | A25101006 | Second Fork Sta TTMP | 0 | 12.03 | 26.71 | 2.52 | 41.26 | n.m.
55 | A26112003 | Lovely Station | 0 | 34.5 | 0.09 | 5.1 | 39.69 | n.m.
56 | A26112006 | Jenkins Station | 0 | 34.5 | 0.09 | 5.1 | 39.69 | n.m.
57 | B110KYPAC | D/KY/P&C NSW | 0 | 71399.16 | 2147.65 | 9903.18 | 83449.99 | n.m.
58 | B110KYRMB | Reimbursable-DOP-110 Kentucky | 0 | 3242.46 | 6.1 | 479.26 | 3727.82 | n.m.
59 | B110KYSRR | D/KY/Non-Specific Work - Sta | 419334.144 | 1328150.41 | 21984.54 | 301181.86 | 1651316.81 | 393.8%
60 | B110KYTEL | Distr Telecom Sta/Fiber - KY | 7840.205 | 88517.71 | 2494.17 | 6638 | 97649.88 | 1246%
61 | C24097002 | Bonnyman Sta - Shamrock Ckt | 0 | 120.72 |  |  | 120.72 | n.m.
62 | C24097004 | Busseyville Sta - Mattie Ckt | 0 | 120.72 |  |  | 120.72 | n.m.
63 | C24097005 | Busseyville Sta-Torchlight Ckt | 0 | 120.72 |  |  | 120.72 | n.m.
64 | C24097006 | Busseyville Sta - Louisa Ckt | 0 | 120.72 |  |  | 120.72 | n.m.
65 | C24097007 | Busseyville Sta -Walbridge Ckt | 0 | 120.72 |  |  | 120.72 | n.m.
66 | C24097008 | Leslie Sta - Wooton Circuit | 0 | 120.72 |  |  | 120.72 | n.m.
67 | C24097009 | Vicco Sta - Jeff Circuit | 0 | 120.72 |  |  | 120.72 | n.m.
68 | DCTSUVLKY | KY CATS Monthly Unvouch Liab | 0 | 3316789.65 |  |  | 3316789.65 | n.m.
69 | DMS24KK04 | KY/ME/Thunderstorm 04.02.2024 | 0 | -216856.48 | 350.51 | 48374.93 | -168131.04 | n.m.
70 | DMS24KK05 | KY Pre/Valid Major Storm 05 | 0 | 1722.8 | 24.75 | 364.39 | 2111.94 | n.m.
71 | DMS24KK07 | KY Pre/Valid Major Storm 07 | 0 | -33890.11 |  | 17381.16 | -16508.95 | n.m.
72 | DMS24KK08 | KY/ME/Thunderstorm 05.26.2024 | 0 | -216711.1 |  | 122007.98 | -94703.12 | n.m.
73 | DMS24KK09 | Y Pre/Valid Major Storm 09 | 0 | 24132.1 | 0.12 | 8673.73 | 32805.95 | n.m.
74 | DMS24KK10 | KY Pre/Valid Major Storm 10 | 0 | 14148.92 | 8.04 | 2826.19 | 16983.15 | n.m.
75 | DMS24KK11 | KY Pre/Valid Major Storm 11 | 0 | 51687.25 | 2.19 | 11344.49 | 63033.93 | n.m.
76 | DMS24KK12 | KY ME Windstorm 09.27.2024 | 0 | 2828635.9 | 80430.61 | 358719.57 | 3267786.08 | n.m.
77 | DMS24KK13 | KY Pre\Valid Major Storm 13 | 0 | 120182.33 | 8.25 | 20199.6 | 140390.18 | n.m.
78 | DMS24KK14 | KY Pre\Valid Major Storm 14 | 0 | 40727.97 | 18.87 | 7324.61 | 48071.45 | n.m.
79 | DMS25KK01 | KY/ME/IceSnow Storm 01.05.2025 | 0 | 1746628.54 | 419.34 | 172505.18 | 1919553.06 | n.m.
80 | DMS25KK02 | KY Pre/Valid Major Storm 02 | 0 | 119497.52 | 69.61 | 12676.84 | 132243.97 | n.m.
81 | DMS25KK03 | KY/ME/Thunderstorm 02/15/25 | 0 | 2587628.83 | 369.31 | 210197.1 | 2798195.24 | n.m.
82 | DMS25KK05 | KY Pre/Valid Major Storm 05 | 0 | 298663.5 | 175.2 | 13035.25 | 311873.95 | n.m.
83 | DMS25KK06 | KY Pre/Valid Major Storm 06 | 0 | 228191.06 | 157.87 | 18945.52 | 247294.45 | n.m.
84 | DMS25KK07 | KY Pre/Valid Major Storm 07 | 0 | 63813.25 | 50.88 | 5884.67 | 69748.8 | n.m.
85 | DMS25KK08 | KY/ME/Thunderstorm 05.16.2025 | 0 | 1360210.15 | 508.91 | 61223.13 | 1421942.19 | n.m.
86 | DMS25KK09 | KY Pre/Valid Major Storm 09 | 0 | 76754.58 | 37.71 | 4397.93 | 81190.22 | n.m.
87 | DP16K03A0 | Tygart Sta - D line | 1713608.271 | 399361.75 | 31282.69 | 63712.28 | 494356.72 | 28.85%
88 | DP16K03B0 | Tygart Sta - Dist Station | 0 | 290437.18 | 32.27 | 54337.19 | 344806.64 | n.m.
89 | DR18K02A0 | Hazard 2018 DA Plan | 0 | 4590.42 | 9569.33 |  | 14159.75 | n.m.
90 | DR19K05A0 | Hazard DA 2019 - D line | 0 | 26889.72 | 25584.49 |  | 52474.21 | n.m.
91 | DR19K05B0 | Hazard DA 2019 - Shamrock | 0 | -76610.36 | 51881.8 | -23625.13 | -48353.69 | n.m.
92 | DR19K05B1 | Hazard DA 2019 - Engle | 0 | -40712.19 |  | -10850.4 | -51562.59 | n.m.
93 | DR19K05B2 | Hazard DA 2019 - Slemp | 0 | -166711.04 |  | -44430.94 | -211141.98 | n.m.
94 | DX21K0002 | Buckhorn DA Comm. Upgrade | 0 | 130.01 |  |  | 130.01 | n.m.
95 | DX21K0003 | Dewey DA Coms Upgrade | 0 | 23879.74 | -660.92 |  | 23218.82 | n.m.
96 | DX23K01A0 | Hyden DA Upgrade | 0 | 931.27 | 683.51 |  | 1614.78 | n.m.
97 | EDN011333 | Customer Meter/Kp | 565966.192 | 409302.78 |  | 39408.39 | 448711.17 | 79.28%
98 | EDN012370 | Ds/Kp/Public Relocation | 1206064.978 | 1014694.57 | 8776.79 | 166987.53 | 1190458.89 | 98.71%
99 | EDN014651 | Ds/Kp/Cs-New Customers | 3819253.481 | 3433708.15 | 3144.05 | 749687.53 | 4186539.73 | 109.6%
100 | EDN014658 | Ds/Kp/Cs-Upgrades | 284862.954 | 234319.84 | 57.98 | 43867.62 | 278245.44 | 97.68%
101 | EDN014680 | Ds-Kp-Ai Pole Replacement | 5148462.843 | 2410268.19 | 5177.53 | 412518.68 | 2827964.4 | 54.93%
102 | EDN014687 | Ds-Kp-Ai Aepc Make Ready | -40395.088 | 8255.06 | -17.81 | 1033.23 | 9270.48 | -22.95%
103 | EDN014694 | Ds-Kp-Ai Other Make Ready | 918660.897 | 477893.92 | -3705.5 | 81130.8 | 555319.22 | 60.45%
104 | EDN014701 | Ds Kp Ai Support Cs Res | 0 | 7903.13 | 9.45 | 1270.24 | 9182.82 | n.m.
105 | EDN014720 | Ds-Kp-Ai Recloser Replacement | 3820945.872 | 2864600.82 | 31346.73 | 492586.75 | 3388534.3 | 88.68%
106 | EDN015042 | Ds-Kp-Small Wire Repl Ovhd | 411905.334 | 37198.75 | 304.07 | 10500.02 | 48002.84 | 11.65%
107 | EDN100033 | Ds/Kp/C&I New | 1993108.924 | 1746412.84 | 7642 | 437834.66 | 2191889.5 | 110%
108 | EDN100044 | Ds/Kp/C&I Upgrades | 66216.378 | 86662.31 | 42.37 | 21266.15 | 107970.83 | 163.1%
109 | EDN100577 | Ds-Kp-Ai Ckt Inspections | 675582.675 | 169830.34 | 2305.76 | 29991.55 | 202127.65 | 29.92%
110 | EDN103175 | Ds Kp Anda | 0.025 | 9749369.89 |  | -9759348.63 | -9978.74 | -39914960%
111 | EON011326 | Line Transformer/Kp | 3413885.265 | 5818116.53 |  | 820696.29 | 6638812.82 | 194.5%
112 | ETN000110 | T Kp D Anda | 0 | 265127.51 |  | -265127.51 | 0 | n.m.
113 | IT1101723 | CIS-Smart Grid Gateway-KYP D | 0 | -650.1 |  |  | -650.1 | n.m.
114 | IT1101724 | CIS-Meter Enhancements-KYP D | 0 | -51353.01 | -5602.56 |  | -56955.57 | n.m.
115 | IT1101725 | CIS-Common Deployment-KYP D | 0 | 100175.28 | 65141.84 |  | 165317.12 | n.m.
116 | IT1102013 | Field Mobility iPAD CI - KYP D | 0 | 259082.06 | 287.42 |  | 259369.48 | n.m.
117 | IT1102049 | CIS-Agent Desktop Replat-KYP D | 0 | 990.51 | 341.02 |  | 1331.53 | n.m.
118 | IT110ADMS | ADMS Imp DSN DNEX-KYP D | 0 | 1065307.93 | 141593.33 |  | 1206901.26 | n.m.
119 | IT110CCIC | Cloud Comp Imp Cost - KyP D | 0 | 597108.21 |  |  | 597108.21 | n.m.
120 | ITCB11000 | KENTUCKY POWER - DIST | 0 | 194427.2 | 37446.7 | 6456.46 | 238330.36 | n.m.
121 | ITCF11000 | Tcom Field Ops Blanket-KYPCO D | 403986.429 | 352108.37 | 8839.13 |  | 360947.5 | 89.35%
122 | ITCT11004 | Ashland-Lynchburg MW Upgrade ( | -9448.098 | 662170.16 | 27278.3 |  | 689448.46 | -7297%
123 | ITCW11004 | KY Next Generation Radio Sys | 2327559.003 | 1428243.43 | 42172.84 |  | 1470416.27 | 63.17%
124 | ITPCLC110 | PC Lifecycle CI - 110 | 189923.307 | 74147.53 |  |  | 74147.53 | 39.04%
125 | KEPDS2201 | KPCo Storm - Distribution | -156479.756 |  | 510.99 |  | 510.99 | -0.3266%
126 | KEPDS2202 | KPCo Storm - Distribution | 0 |  | -4.17 | 150.84 | 146.67 | n.m.
127 | KEPDS2501 | KPCo Storm - Distribution | 0 | 58786.35 | 716.95 | 5589.82 | 65093.12 | n.m.
128 | KEPDS2502 | KPCo Storm - Distribution | 0 | 307984.71 | 117.2 | 45595.58 | 353697.49 | n.m.
129 | KY5YCYCLE | KY D 2017-00179 | 1840508.233 | 1353954.77 |  | 308894.43 | 1662849.2 | 90.35%
130 | KYCAPTOOL | KY Purch. Cap Tools | 13262.484 | 373705.21 | 65.98 |  | 373771.19 | 2818%
131 | P14030009 | Stinnett Station & Telecom | 23850.367 | 118086.42 | 17107.78 | 22080.72 | 157274.92 | 659.4%
132 | P17076002 | Kenwood Station | 0 | -169493.37 | -31923.92 | -39923.74 | -241341.03 | n.m.
133 | P17076003 | Prestonsburg Remote End Work | 0 | -71817.58 | -11734.8 | -18411.06 | -101963.44 | n.m.
134 | P17076011 | Distribution work at Kenwood | 0 | -5813.99 | -691.89 | -1100.34 | -7606.22 | n.m.
135 | P17083016 | McKinney Station Work | -245504.676 | 71144.11 | 47344.36 | 15055.69 | 133544.16 | -54.4%
136 | P17083025 | Soft Shell Station Work (KPCo) | 144661.037 | 244910.34 | 3265.21 | 127494.53 | 375670.08 | 259.7%
137 | P17083030 | Garrett Station (Distribution) | 1074899.769 | 965377.84 | 80663.04 | 155304.52 | 1201345.4 | 111.8%
138 | P17083033 | Garrett Land Purchase | 2393.466 |  | -2040.74 |  | -2040.74 | -85.26%
139 | P17083040 | Garrett Station | -837952.2 | 3463396.92 | 245806.93 | 574499.12 | 4283702.97 | -511.2%
140 | P17084005 | Myra Station | 183647.283 | 67132 |  | 9431.55 | 76563.55 | 41.69%
141 | P17084006 | Myra Land Purchase | 0 | 5850.96 |  |  | 5850.96 | n.m.
142 | P17084025 | Elwood Station Retirement | 0 |  |  | 7261.15 | 7261.15 | n.m.
143 | P17084055 | Myra Station | 0 | 50602.33 | 1384.39 | 7113.19 | 59099.91 | n.m.
144 | P18025001 | Kewanee Station - Baseline Wor | 519242.095 | 164896.64 |  | 29099.41 | 193996.05 | 37.36%
145 | P18025002 | Kewanee Station Land Purchase | 0 | 3252.79 | 3503.57 |  | 6756.36 | n.m.
146 | P18025018 | Kewanee Transco to KPCo | 0 | 108851.19 |  | 16275.11 | 125126.3 | n.m.
147 | P18221011 | Collier Remote End | 0 | 1575 | 126.97 | 405.62 | 2107.59 | n.m.
148 | P19036002 | Burton Station Retirement | 0 | 12596.08 |  | 4105.76 | 16701.84 | n.m.
149 | P19036005 | Osborne 69kV Station | 0 | 142774.76 | 122230.85 | 29370.92 | 294376.53 | n.m.
150 | P19036012 | Osborne Station T | 0 | 134727.36 | 12769.96 | 19078.52 | 166575.84 | n.m.
151 | P19037003 | Henry Clay Land Purchase | -268257.201 | 67552.42 |  |  | 67552.42 | -25.18%
152 | P19037008 | Henry Clay Station | -307393.269 | 133891.59 | 10124.25 | 27370.46 | 171386.3 | -55.75%
153 | P19037016 | Ratliff 69kV Station | -25556.083 | 76128.35 | 9979.43 | 12462.43 | 98570.21 | -385.7%
154 | P19037017 | New Ratliff Land Purchase | -24210.486 | 340261.26 |  |  | 340261.26 | -1405%
155 | P19037031 | Burdine Station | 0 | 22928.88 | 721.57 | 3827.13 | 27477.58 | n.m.
156 | P19037032 | Elwood Station Retirement | 0 | 1491.51 | 56.26 | 402.68 | 1950.45 | n.m.
157 | P19092002 | Allen Station (Dist) | 83.822 | 38121.03 | 426.11 | 169.17 | 38716.31 | 46189%
158 | P19092014 | Prestonsburg Remote End | 0 | 19413.66 |  | 3983.27 | 23396.93 | n.m.
159 | P19092016 | McKinney Remote End Work | 79075.102 | 25239.24 |  | 4921.6 | 30160.84 | 38.14%
160 | P19092022 | Allen Station Land Purchase | 3063.291 | 8805.96 | -4007.8 |  | 4798.16 | 156.6%
161 | P19092023 | Allen Station | 28005.544 | 174071.03 |  | 46966.1 | 221037.13 | 789.3%
162 | P19305013 | Orinoco KPCO D | -803654.76 | 1442476.99 | 138723.07 | 149607.36 | 1730807.42 | -215.4%
163 | P19305022 | New Camp Station | 22604.515 | 453402.53 | 52168.54 | 63277.02 | 568848.09 | 2517%
164 | P20035005 | Remote End at Prestonsburg | 0 | 1241.29 |  | 318.97 | 1560.26 | n.m.
165 | P20035008 | Middle Creek Station | -15881.831 | 2366.71 |  | 437.56 | 2804.27 | -17.66%
166 | P21043005 | Prestonsburg Remote End | -225399.304 | 249891.41 | 22577.98 | 33863.3 | 306332.69 | -135.9%
167 | P21043006 | Kenwood Station | 183670.804 | 506933.36 | 52469.91 | 97956.25 | 657359.52 | 357.9%
168 | P21720003 | Coalton Remote End | 29988.485 | 6789.7 | 2161.71 | 1271.44 | 10222.85 | 34.09%
169 | P21720007 | Raceland Remote End | 190984.327 | 4129.63 | 1826.91 | 426.64 | 6383.18 | 3.342%
170 | P21753003 | Stanville Remote End Work | -95531.386 | 12332.52 | 912.32 | 2566.3 | 15811.14 | -16.55%
171 | P22005001 | 47th Street Station | 182840.067 | 469596.71 | 11842.92 | 70043.36 | 551482.99 | 301.6%
172 | P22012001 | Coleman Station Work | 0 | 1319.94 | 543.42 | 74.51 | 1937.87 | n.m.
173 | P22012002 | Peter Creek Station Work | 0 | 410.05 | 1130.82 | 85.92 | 1626.79 | n.m.
174 | P22113002 | Gund Metering KY D - BPID | 4714.441 | 407505.42 | 7490.4 | 75899.46 | 490895.28 | 10413%
175 | P24083002 | Busseyville Station | 0 | 5113.62 | 122.69 | 902.23 | 6138.54 | n.m.
176 | P24125002 | Coleman Station D | 0 | 6908.3 | 35.3 | 1210.4 | 8154 | n.m.
177 | P24125003 | Coleman Station Cap Bank | 0 | 13398.79 | 117.8 | 1738.95 | 15255.54 | n.m.
178 | P24125004 | Tom Watkins Station | 0 | 1482.29 |  | 219.09 | 1701.38 | n.m.
179 | TP1403006 | T Funded D Work | 9224.677 | 578034.74 | 22871.6 | 88215.1 | 689121.44 | 7470%
180 | TP1708310 | T Funded D Garret Area Imp | 229872.882 | 11049.06 | 0 | 75.45 | 11124.51 | 4.839%
181 | TP1802510 | KEWANEE DLINE WORK | 395646.021 | 905306.07 | 3371.85 | 180990.73 | 1089668.65 | 275.4%
182 | TP1822105 | Fleming T-Funded D | 0 | 97551.45 |  | 12869.59 | 110421.04 | n.m.
183 | TP1903604 | T Funded D | 0 | 210192.9 | 1214.6 | 33489.58 | 244897.08 | n.m.
184 | TP1930505 | Orinoco T Funded D (Dist Line) | 0 | 967843.51 | 22022.54 | 246592.49 | 1236458.54 | n.m.
185 | TREEREL21 | ROW Capital Widening & Removal | 3.049 | 664.4 |  |  | 664.4 | 21791%
186 | TREEREL23 | ROW Capital Widening & Removal | 0 | -35421.61 |  |  | -35421.61 | n.m.
187 | TREEREL24 | ROW Capital Widening & Removal | 3051852.875 | 3529259.37 |  |  | 3529259.37 | 115.6%
188 | TREEREL25 | ROW Capital Widening & Removal | 2876334.506 | 3709344.5 |  |  | 3709344.5 | 129%
189 | XHWCAP110 | HW CAP CI - 110 | 0 | 329136.04 | 6107.12 | 0 | 335243.16 | n.m.
190 | Other Budgeted Projects |  | 34639948.035 | 0 | 0 | 0 | 0 | Other
191 | Total GLBU 110 (Distribution) |  | 86458621.917 | 88446984.17 | 1611722.36 | -196536.63 | 89862169.9
192 | GLBU 117 (Generation)
193 | 000005237 | KyPCo-G Capital Software Dev | 0 | 483424.81 |  |  | 483424.81 | n.m. | 117-000005237 | Budget Estimate is just for the referenced year-ending May
194 | 000025231 | 2018 Gen Plt Cap Blkt - KYPC-G | 0 | 7310.11 | 9.78 | 30.02 | 7349.91 | n.m. | 117-000025231
195 | BSPPB0002 | Boiler & Auxiliaries PPB<100k | 308158.934 | 61964.41 | 268.37 | -14657.89 | 47574.89 | 15.44% | 117-BSPPB0002
196 | BSPPB0007 | Condenser & Aux. PPB<100k | 0 | 152142.98 | 1484.51 | -15462.04 | 138165.45 | n.m. | 117-BSPPB0007
197 | BSPPB0008 | Clg Water Facilities PPB<100k | 0 | 29752.59 | 237.24 | 5038.52 | 35028.35 | n.m. | 117-BSPPB0008
198 | BSPPB0011 | Generator & Support PPB<100k | 0 | 63983.24 | 500.51 | 2803.64 | 67287.39 | n.m. | 117-BSPPB0011
199 | BSPPB0013 | Other Costs PPB<$100k | 832845.96 | 1128013.03 | 18709.19 | 11330.63 | 1158052.85 | 139% | 117-BSPPB0013
200 | BSPPBENEW | BSP PPB Envr. New | 0 | 219954.5 | 6057.81 | 21577.66 | 247589.97 | n.m. | 117-BSPPBENEW
201 | BSPPBOUT1 | Unit 1PPB Outage<100k | 956559.622 | 659100.25 | 6739.3 | -31150.36 | 634689.19 | 66.35% | 117-BSPPBOUT1
202 | BSPPBS347 | REP U1 BFPT Rotor with Spare | 183248.525 | 481560.43 | 1460.51 | -68062.99 | 414957.95 | 226.4% | 117-BSPPBS347
203 | BSPPBS368 | Big1 Boiler Exit Gas Duct Repl | 5810643.636 | 7932900.92 | 71369.89 | 131328.63 | 8135599.44 | 140% | 117-BSPPBS368
204 | BSPPBWGRN | Ovation Evergreen Upgrade | 1148697.852 | 1147.6 | 3.41 | 127.31 | 1278.32 | 0.1113% | 117-BSPPBWGRN
205 | IT117CCIC | Cloud Computing Imp Cost-KyP G | 0 | 106531.99 |  |  | 106531.99 | n.m. | 117-IT117CCIC
206 | ITCB11700 | KENTUCKY POWER - GEN | 5237.414 | 2388.83 | 2287.82 |  | 4676.65 | 89.29% | 117-ITCB11700
207 | ITCBLBRTY | KENTUCKY POWER LIBERTY | 0 | 639.56 | 601.9 |  | 1241.46 | n.m. | 117-ITCBLBRTY
208 | ITPCLC117 | PC Lifecycle CI - 117 | 12494.993 | 4542.91 |  |  | 4542.91 | 36.36% | 117-ITPCLC117
209 | ML1E25C02 | ML1 E COOLING TOWER REPLACMENT | 0 | 10023.78 |  | 823.58 | 10847.36 | n.m. | 117-ML1E25C02
210 | MLKP26265 | ML U2 Cooling Tower Reinforce | 1859019.84 | 2200971.59 | 78689.6 | 110682.68 | 2390343.87 | 128.6% | 117-MLKP26265
211 | MLKYELGFL | MLP KY ELG CPCN Filing 2025 | 0 | 90791.97 | 496.33 | 26557.92 | 117846.22 | n.m. | 117-MLKYELGFL
212 | MLL1CGRPL | ML U1 Clinker Grinder Rpl - KY | 202987.471 | 164436.49 | 7329.72 | 9102.57 | 180868.78 | 89.1% | 117-MLL1CGRPL
213 | MLL2CGRPL | ML U2 Clinker Grinder Rpl - KY | 0 | 69501.31 | 6871.37 | 3703.12 | 80075.8 | n.m. | 117-MLL2CGRPL
214 | MLLEC1VHL | ML E U1 VHP/HP&LPA Turbn Insp | 0 | 9.25 |  |  | 9.25 | n.m. | 117-MLLEC1VHL
215 | MLLEP2LA0 | ML2 LPA L0 Rtr Rpr at CMS KPCo | 0 | 263682.38 | 4554.39 | 7457.07 | 275693.84 | n.m. | 117-MLLEP2LA0
216 | MLLEP2LA1 | ML2 LPA L1 Rtr Rpr at CMS KPCo | 0 | 84362.76 | 2676.4 | 2385.83 | 89424.99 | n.m. | 117-MLLEP2LA1
217 | MLLEP2LB0 | ML2 LPB L0 Rtr Rpr at CMS KPCo | 0 | 263682.38 | 4554.39 | 7457.07 | 275693.84 | n.m. | 117-MLLEP2LB0
218 | MLLEP2LB1 | ML2 LPB L1 Rtr Rpr at CMS KPCo | 0 | 84362.76 | 2676.4 | 2385.83 | 89424.99 | n.m. | 117-MLLEP2LB1
219 | MLLHAULRD | Mitchell Haul Road Relocate | 645880.152 | 885555.52 | 3604.55 | 33245.68 | 922405.75 | 142.8% | 117-MLLHAULRD
220 | MLLPC0ELG | ML PCC U0 ELG/CCR Comply - 117 | 3414944.798 | 1790425.45 | 345800.63 | 159247.38 | 2295473.46 | 67.22% | 117-MLLPC0ELG
221 | MLLPC0LIM | ML PCC U0 Lime Conversion 117 | 0 | 147.06 |  | 6.56 | 153.62 | n.m. | 117-MLLPC0LIM
222 | MLLPC2ESP | ML PCC U2 ESP Upgrades 117 | 0 | -3164.66 |  | -335.79 | -3500.45 | n.m. | 117-MLLPC2ESP
223 | MLLPCT1BP | ML U1 Cooling Tower Canopy KYP | -69142.593 | -350190.29 | 1866.95 | 17481.62 | -330841.72 | 478.5% | 117-MLLPCT1BP
224 | MLLPCT1PC | ML1 Cool Twr Canopy PreCI KPCo | 0 | 162140.84 | -2970.36 | 7957.17 | 167127.65 | n.m. | 117-MLLPCT1PC
225 | MLLPPBSHD | ML Minor PPB Liberty Shadow | 2109996.758 | 2429069.11 | 41193.58 | 126401.14 | 2596663.83 | 123.1% | 117-MLLPPBSHD
226 | MLLSC1AHB | ML S U1 Air Htr Bskt Rplc Lbty | 0 | 0 | -44229.47 |  | -44229.47 | n.m. | 117-MLLSC1AHB
227 | MLLVC1CL1 | Mitchell U1 SCR Catalyst L1 | 273686.078 | 307591.21 | 7642.84 | 17080.61 | 332314.66 | 121.4% | 117-MLLVC1CL1
228 | XHWCAP117 | HW CAP CI - 117 | 0 | 116046.4 | 2306.77 | 0 | 118353.17 | n.m. | 117-XHWCAP117
229 | Other Budgeted Projects |  | 12244172.605 |  |  |  | 0 | 0% | Other
230 | Total GLBU 117 (Generation) |  | 29939432.045 | 19904803.47 | 572794.33 | 574543.17 | 21052140.97
231 | GLBU 180 (Transmission)
232 | 000005273 | KyPCo-T Capital Software Dev | 0 | 1034881.56 |  |  | 1034881.56 | n.m.
233 | 000025230 | 2018 Gen Plt Cap Blkt - KYPC-T | 0 | 18261.01 | 434.18 |  | 18695.19 | n.m.
234 | 180KYLSBO | Trans KY Lease Buyout | 0 | 37605.95 |  |  | 37605.95 | n.m.
235 | A14068001 | Baker 765kV Physical Security | 275.769 | 9558.75 | 1324.48 | 857.44 | 11740.67 | 4257%
236 | A14068006 | Baker Sta Ballistic/Wall Elect | 2486.71 | 12633.69 | 38486.49 | 1457.5 | 52577.68 | 2114%
237 | A15702006 | KYPCo BAT HCP | 0 | 5496.83 | 12437.77 |  | 17934.6 | n.m.
238 | A15702007 | Beaver Creek- Repl Cap Bk AACC | 0 |  | -15873.91 |  | -15873.91 | n.m.
239 | A15702029 | Leslie 161/69kV XF Replacement | -2219972.878 | 1686006.02 | 263455.92 | 111917.65 | 2061379.59 | -92.86%
240 | A15702030 | Morehead: Replace CB B | 0 | 55442.51 |  | 7787.69 | 63230.2 | n.m.
241 | A15702032 | Hazard-Bonnyman Str. Replace | 0 | 1966.81 |  | 259.35 | 2226.16 | n.m.
242 | A15702035 | Hazard - Fleming Str. Replace | 0 | 5290.62 |  | 697.66 | 5988.28 | n.m.
243 | A15702036 | Daisy-Clover Fork Str. Replace | 0 | 2340.72 |  | 308.66 | 2649.38 | n.m.
244 | A15702041 | Hazard CB/XF Replacements | 0 | -15973.69 |  | 37277.11 | 21303.42 | n.m.
245 | A15710071 | Morehead Station TTMP | 0 | 854.16 | 1778.82 | 86.05 | 2719.03 | n.m.
246 | A18730001 | Hazard-Bonnyman Str Replce ROW | 0 | 459.48 |  |  | 459.48 | n.m.
247 | A18730004 | Hazard-Fleming Str. Replc ROW | 0 | 496.05 |  |  | 496.05 | n.m.
248 | A18730005 | Daisy - Clover Fork ROW | 0 | 439.89 |  |  | 439.89 | n.m.
249 | A19063004 | Leon - Olive Hill Fiber Cable | 228382.981 | 4442.19 | 158.68 | 151.45 | 4752.32 | 2.081%
250 | A19063005 | Hayward Sta Fiber Cable Ext | 0 | 4006.76 | 144.21 | 138.36 | 4289.33 | n.m.
251 | A19063006 | Hayward - Morehead FCE | 0 | 139272.54 |  |  | 139272.54 | n.m.
252 | A19750118 | Prestonsburg-Middle Ck Slide F | 0 | -0.72 | 0.15 | -0.04 | -0.61 | n.m.
253 | A20020001 | Leon-Morehead69kVRehbLine | 0 | 321703.94 |  | 34192.78 | 355896.72 | n.m.
254 | A20020002 | Leon-Morehead69kVRehab ROW | 0 | 15053 |  |  | 15053 | n.m.
255 | A20045015 | Prestonsburg - Thelma 46kV NA | 0 | 165252.45 | 32632.41 | 6788.07 | 204672.93 | n.m.
256 | A20045023 | Betsy Layne - S Pikeville NIP | 0 | 248.26 | 460.78 | 32.74 | 741.78 | n.m.
257 | A20045046 | Allen - Prestonsburg NIP | 0 | 285.05 | 529.02 | 37.59 | 851.66 | n.m.
258 | A20045063 | 0Hatfield Station Work | 1826444.379 | 826480.58 | 65750.3 | 85549.34 | 977780.22 | 53.53%
259 | A20045085 | Leon (KP) NIP | 0 | 35.05 | 65.06 | 4.62 | 104.73 | n.m.
260 | A20077006 | Bonnyman Sta TTMP | 0 | 51.47 | 95.53 | 6.79 | 153.79 | n.m.
261 | A20077009 | Hays Branch Sta TTMP | 0 | 46.58 | 86.45 | 6.14 | 139.17 | n.m.
262 | A20077012 | Hazard Sta TTMP | 0 | 48.11 | 71.8 | 6.34 | 126.25 | n.m.
263 | A20077026 | Bonnyman-Jackson FC TelMod Fib | 1147165.257 | 24966.01 | 812.56 | 2032.06 | 27810.63 | 2.424%
264 | A20077027 | Haddix SS FCE TelMod Fib | 0 | 15204.03 | 468.01 | 1197.33 | 16869.37 | n.m.
265 | A20077028 | Engle SS FCE ModTel Fib | 142285.656 | 15192.08 | 507.55 | 1147.38 | 16847.01 | 11.84%
266 | A20077029 | Bonnyman-Hazard FC ModTel Fib | 429680.245 | 33907.51 | 1036.65 | 2700.59 | 37644.75 | 8.761%
267 | A20077030 | Bulan SS FCE TelMod Fib | 0 | 15878.13 | 453.02 | 1215.61 | 17546.76 | n.m.
268 | A20077031 | Whitesburg SS FCE TelMod Fib | 560072.757 | 7497.55 | 390.38 | 664.99 | 8552.92 | 1.527%
269 | A20077032 | Mayking SS FCE TelMod Fib | 135069.43 | 4634.4 | 184.75 | 393.2 | 5212.35 | 3.859%
270 | A20077033 | Collier SS FCE TelMod Fib | 0 | 45.64 | 100.6 | 6.01 | 152.25 | n.m.
271 | A20077034 | Jenkins-South Pikesville FC | 1114228.33 | 25272.7 | 1813.91 | 2073.16 | 29159.77 | 2.617%
272 | A20077035 | CANCEL-Jackhorn Sta TTMP | 0 | 75.98 |  |  | 75.98 | n.m.
273 | A20705028 | Sprigg-Barrenshe 69kV Pre Eng | 0 | 342.75 |  | 45.2 | 387.95 | n.m.
274 | A20705035 | Middle Creek-Falcon 46kV Remvl | 0 | 693.71 |  | 39.18 | 732.89 | n.m.
275 | A20705036 | Middle Creek-Prestonsburg Rebu | 0 | 77400.46 |  | 8333.91 | 85734.37 | n.m.
276 | A20705037 | Big Sandy - Thelma Pre Eng | 0 | -20541.79 | -2215.55 | -2160.77 | -24918.11 | n.m.
277 | A20705052 | Coleman - Stone 69kV Pre Eng | 0 | -24193.21 | -2488.69 | -2162.41 | -28844.31 | n.m.
278 | A20705057 | Big Sandy Station Pre Eng | 0 | 272.51 | 505.74 | 35.94 | 814.19 | n.m.
279 | A20705067 | McInness SW Needs Assessment | 0 | 124.23 | 230.57 | 16.38 | 371.18 | n.m.
280 | A20705077 | JohnsC - LeslieN1 69 Needs Asm | 0 | 162.77 | 302.09 | 21.46 | 486.32 | n.m.
281 | A20705078 | LeslieNo1-Hatfield69 NeedsAsm | 0 | 161.06 | 298.91 | 21.23 | 481.2 | n.m.
282 | A20705079 | McInnessMet69kV Needs Asm | 0 | 19.91 | 36.95 | 2.63 | 59.49 | n.m.
283 | A20705080 | Sidney 69kV Loop Needs Asm | 0 | 14.38 | 26.69 | 1.89 | 42.96 | n.m.
284 | A20705081 | Bevins 69kV Tap Needs Asm | 0 | 14.38 | 26.69 | 1.89 | 42.96 | n.m.
285 | A20705082 | Bellefonte Station supplmental | 360862.757 | 1512540.06 | 40850.64 | 86375.61 | 1639766.31 | 454.4%
286 | A20705083 | Bellefonte 34.5kV St Needs Asm | 0 | 347.84 | 645.56 | 45.87 | 1039.27 | n.m.
287 | A21071001 | BigSandy-Broadford KP 765 S&I | 32.06 | 1399.11 | 865.46 | 139.89 | 2404.46 | 7500%
288 | A21071002 | BigSandy-Brd KP 765 S&I ROW | 0 | 314.46 |  |  | 314.46 | n.m.
289 | A21071003 | Baker-DonMarq KP 765 S&I | 40.111 | 3640.65 | 2428.14 | 589.36 | 6658.15 | 16599%
290 | A21071004 | Baker-DonMarq KP 765 S&I ROW | 0 | 272.28 |  |  | 272.28 | n.m.
291 | A21222008 | South Portsmouth Sta Fiber | 0 | -4162.9 | -942.53 |  | -5105.43 | n.m.
292 | A21222017 | Greenup TS TTMP | 0 | 69 |  | 3.93 | 72.93 | n.m.
293 | A21222018 | Tygart FCE TTMP | 0 | 15273.63 | 50.69 | 781.71 | 16106.03 | n.m.
294 | A21505001 | Jackson - Helechawa 69kV NIP | 0 | 1637.09 | 3038.29 | 215.88 | 4891.26 | n.m.
295 | A21505003 | Hazard - Jackson 69kV Line NIP | 0 | 379.92 | 705.1 | 50.1 | 1135.12 | n.m.
296 | A21505004 | Morehead - Index 69kV Line NIP | 0 | 1789.32 | 3320.82 | 235.95 | 5346.09 | n.m.
297 | A21505005 | Baker 765kV/345kV Yard NIP | 0 | 129.08 | 239.56 | 17.02 | 385.66 | n.m.
298 | A21505007 | Jackson - Helechawa 69kV NIP | 0 | 329.29 | 611.11 | 43.43 | 983.83 | n.m.
299 | A21505008 | Index - Helechawa 69kV NIP | 0 | 906.98 | 1683.25 | 119.6 | 2709.83 | n.m.
300 | A21505011 | Leslie Station NIP | 0 | -19831.33 | -2151.88 | -2096.97 | -24080.18 | n.m.
301 | A21750002 | Bonnyman-Softshell Failure | 0 | 0.86 | 1.61 | 0.11 | 2.58 | n.m.
302 | A21750004 | Hazard-Pinevll 161kV Fire Fail | 0 | 36908.96 |  | 4690.24 | 41599.2 | n.m.
303 | A21750007 | Hays Branch-Morgan Fork Slide | 96588.343 | 30782.88 |  | 16074.93 | 46857.81 | 48.51%
304 | A21750008 | Sprigg-Beaver Crk Slide Fail | 463486.058 | 26394.36 | 7408.26 | 1887.71 | 35690.33 | 7.7%
305 | A21750009 | Sprigg-Bvr Crk Slide Fail ROW | 0 | 4600.9 |  |  | 4600.9 | n.m.
306 | A21750010 | HysBrnch-Morgan Frk Slide Fail | 166531.641 | 60720.91 | 9131.37 | 3026.57 | 72878.85 | 43.76%
307 | A21750015 | Hazard-Pineville 161kV Failure | 0 | 94601.29 |  | 3574.64 | 98175.93 | n.m.
308 | A23750005 | Bellefonte-S Point T-Line Fail | 0 | 93400.44 | 2013.86 | 5649.39 | 101063.69 | n.m.
309 | A23750007 | ASFI Switching Failure | 0 | 504587.72 | 9319.61 | 54280.69 | 568188.02 | n.m.
310 | A23750008 | BigSandy-Inez STR83 TLine Fail | 0 | 750177.45 | 4753.17 | 27846.68 | 782777.3 | n.m.
311 | A23750009 | BigSandy-Inez STR83 T-ROW Fail | 0 | 5430.58 | 39.47 | 399.4 | 5869.45 | n.m.
312 | A23928003 | Blaine Creek H-Frame K01 Spare | 0 | 51351.31 | 6.72 | 97.15 | 51455.18 | n.m.
313 | A23928005 | Blaine Creek H-Frame K02 Spare | 0 | 104.57 | 1.33 | 14.7 | 120.6 | n.m.
314 | A24005001 | Baker Station WIN10 Rplace '24 | 33818.004 | 22409.14 | 187.68 | 1801.16 | 24397.98 | 72.14%
315 | A24006001 | Big Sandy Station WIN10 2024 | 33818.004 | 36969.12 | 481.09 | 3139.75 | 40589.96 | 120%
316 | A24022001 | South Portsmouth-Tygart FC | 82424.831 | 6804.97 | 286.72 | 588.13 | 7679.82 | 9.317%
317 | A24022004 | Argentum - South Portsmouth FC | 289868.972 | 11617.96 | 1121.4 | 971.77 | 13711.13 | 4.73%
318 | A24022005 | Argentum Fiber Cable Extension | 114365.776 | 15073.99 | 944.01 | 1151.45 | 17169.45 | 15.01%
319 | A24025009 | Robert E. Matthews Service Cen | 938654.463 | 34121.26 | 1175.6 | 2408.79 | 37705.65 | 4.017%
320 | A24033001 | Sprigg-Beaver Creek 115 T-Line | 0 | 28738 | 13.58 | 2496.44 | 31248.02 | n.m.
321 | A24033002 | Sprigg-Beaver Creek 115 T-ROW | 0 | 149010.05 | 205.48 | 20071.23 | 169286.76 | n.m.
322 | A24033003 | Sprigg-Beaver Creek 116 T-Line | 0 | 752378.27 | 828.89 | 34193.91 | 787401.07 | n.m.
323 | A24033004 | Sprigg-Beaver Creek 116 T-ROW | 0 | 1058.73 | 11.51 | 47.32 | 1117.56 | n.m.
324 | A24038001 | Hatfield Sta FCE TTMP | 96504.398 | 4067.35 | 268.07 | 414.42 | 4749.84 | 4.922%
325 | A24038002 | New Camp Sta FCE TTMP | 34744.009 | 873.97 | 48.49 | 108.31 | 1030.77 | 2.967%
326 | A24038003 | Hatfield Sta TTMP | 10850.182 | 2386.49 | 133.17 | 162.98 | 2682.64 | 24.72%
327 | A24055001 | Cedar Creek Fence Replacement | 0 | 879520.78 | 774.97 | 23445.93 | 903741.68 | n.m.
328 | A24072002 | Beaver Creek Fence Replacement | -237135.997 | 1033573.98 | 913.27 | 32394.79 | 1066882.04 | -449.9%
329 | A24072003 | Big Sandy Fence Replacement | 0 | 1036376.71 | 2.47 | 22642.64 | 1059021.82 | n.m.
330 | A24072004 | Dewey Station Fence Rplacement | 0 | 508683.61 | 5.0626e-14 | 40245.68 | 548929.29 | n.m.
331 | A24072005 | Dorton Fence Replacement | 0 | 423389.44 | 328.47 | 12268.67 | 435986.58 | n.m.
332 | A24072006 | Inez Station Fence Replacement | 5975572.751 | 1193570.32 | 3339.6 | 42393.53 | 1239303.45 | 20.74%
333 | A24072007 | Lee City Fence Replacement | 0 | 256386.34 | 336.03 | 14593.19 | 271315.56 | n.m.
334 | A24072008 | Leon SW (KP) Fence Replacement | 0 | 233105.4 | 268.44 | 5042.73 | 238416.57 | n.m.
335 | A24072009 | Morgan County Fence Replace | 0 | 339115.32 | 698.75 | 16388.94 | 356203.01 | n.m.
336 | A24072010 | Morgan Fork Fence Replacement | 0 | 552647.9 | 1240.34 | 17109.16 | 570997.4 | n.m.
337 | A24072011 | S Porstmouth Fence Replacement | 0 | 184402.11 | 214.42 | 3902.76 | 188519.29 | n.m.
338 | A24072012 | Thelma Fence Replacement | 0 | 584954.72 | 1030.66 | 15729.75 | 601715.13 | n.m.
339 | A24072013 | Wooton Fence Replacement | 0 | 339532.27 | 752.19 | 10391.83 | 350676.29 | n.m.
340 | A24083007 | Stanville 138kV Sta TTMP | 0 | 193.27 |  | 13.26 | 206.53 | n.m.
341 | A24093002 | Leon - Morehead A2 Mitigation | 0 | 912977.33 | 4802.93 | 42966.16 | 960746.42 | n.m.
342 | A24093003 | Morehead - Index A2 Mitigation | 0 | 197586.77 | 890.9 | 13811.35 | 212289.02 | n.m.
343 | A24112005 | Dewey Sta TTMP | 18984.612 | 36.81 |  |  | 36.81 | 0.1939%
344 | A24112009 | Hatfield Sta TTMP | 18984.612 | -2276.49 | -126.39 |  | -2402.88 | -12.66%
345 | A25101004 | S Portsmouth Sta TTMP | 2358.625 | 51.82 | 96.15 | 6.84 | 154.81 | 6.564%
346 | A25101007 | John's Creek Sta TTMP | 0 | 15.8 | 29.34 | 2.08 | 47.22 | n.m.
347 | A25101008 | Bellefonte 138kV Sta TTMP | 0 | 30.33 | 56.3 | 4 | 90.63 | n.m.
348 | A26112002 | Inez Station | 0 | 34.5 | 0.09 | 2.37 | 36.96 | n.m.
349 | B180KYDEM | D/KY/DEM NSW | 0 | 11460.06 | 76.59 | 653.17 | 12189.82 | n.m.
350 | B180KYLRC | T/KY/Non-Specific Work - Line | 4870590.886 | 7660327.44 | 57342.88 | 617340.68 | 8335011 | 171.1%
351 | B180KYLRR | T/KY/Non-Specific Work - Line | 82364.334 | 8890433.35 | 60772.71 | 695634.78 | 9646840.84 | 11712%
352 | B180KYPAC | D/KY/P&C NSW | 18613.847 | 117901.2 | 4062.78 | 6928.95 | 128892.93 | 692.5%
353 | B180KYRMB | Reimbursable-DOP-180 Kentucky | 0 | 211959.73 | 2466.93 | 23497.5 | 237924.16 | n.m.
354 | B180KYSRR | T/KY/Non-Specific Work - Stati | 331396.221 | 290731.58 | 9141.94 | 18996.6 | 318870.12 | 96.22%
355 | B180KYTEC | Trans Telecom - KP-CO Reg | 65897.398 | 244629.7 | 884.72 | 11534.5 | 257048.92 | 390.1%
356 | DP16K03C0 | Tygart Sta - T line work | 0 | -777.84 | -17254.92 | -34829.02 | -52861.78 | n.m.
357 | DP16K03C1 | Tygart Sta - T line work | 0 | -2360.57 |  | -2219.68 | -4580.25 | n.m.
358 | DP16K03T0 | Tygart Sta - T line ROW | 0 | 254.93 | 199.66 | 1920.99 | 2375.58 | n.m.
359 | DR19K05C0 | Hazard DA 2019 Engle Tap | 0 | 1195.2 | 536.58 | 96.44 | 1828.22 | n.m.
360 | DR19K05D0 | Hazard DA 2019 - Hazard Sta | 0 | -57303.67 |  | -1044.25 | -58347.92 | n.m.
361 | DTLM18001 | DTLM - KPCO T | 0 | 349076.71 |  |  | 349076.71 | n.m.
362 | ETN000180 | T Kp T Anda | 0 | 6979714.052 | 0 | -7033413.91 | -53699.858 | n.m.
363 | ETN102802 | Tr/Leas/Transmission Row Lease | 0 | 277.26 |  |  | 277.26 | n.m.
364 | IT180BILL | Corp Prgrm Billing-KYPCO Trans | 0 | 166054.31 | 33581.12 |  | 199635.43 | n.m.
365 | IT180CCIC | Cloud Computing Imp Cost-KyP T | 0 | 161048.69 |  |  | 161048.69 | n.m.
366 | ITCB18000 | KENTUCKY POWER - TRANSM | 15241.214 | 3813.54 | 85.8 |  | 3899.34 | 25.58%
367 | KEPCS2202 | KPCo Storm - Transmission | -455250.681 | 1478806.09 | 4405.18 | 92890.86 | 1576102.13 | -346.2%
368 | KEPCS2401 | KPCo Storm - Transmission | 73413.52 | 33900 |  | 1538.24 | 35438.24 | 48.27%
369 | KEPCS2402 | KPCo Storm - Transmission | 346215.358 | 508369.11 | 6080.26 | 56118.86 | 570568.23 | 164.8%
370 | KEPCS2404 | KPCO Storm - Transmission | 0 | 249666.01 | 767.83 | 14832.77 | 265266.61 | n.m.
371 | KEPCS2503 | KPCO Storm - Transmission | 0 | 425433.51 | 335.66 | 28739.72 | 454508.89 | n.m.
372 | P11063002 | TKYHazard Station Improvemen | 0 | 825.55 |  | 101.36 | 926.91 | n.m.
373 | P13064002 | T/KP/Hazard Station / OPCO | 0 | 20781.12 |  | 1729.32 | 22510.44 | n.m.
374 | P13064003 | T/KP/Wooton Station - Station | 0 | 22869.61 |  | 2361.44 | 25231.05 | n.m.
375 | P13064021 | T/KP/Hazard - Jackson 69kV Lin | 0 | 44532.95 | 3415.05 | 5794.34 | 53742.34 | n.m.
376 | P13064025 | Hazard - Wooton ROW KPCo | 0 | 182.65 |  |  | 182.65 | n.m.
377 | P13064029 | Hazard-Wooton Change to KPCo | 0 | 1028.14 | -2918.7 | 131.3 | -1759.26 | n.m.
378 | P13064030 | Hazard Station Change to KPCo | 0 | -34756.91 | -1197.82 | 872.18 | -35082.55 | n.m.
379 | P13064031 | Hazard 161/138 Spare KPCo | 0 | -1260.55 |  | -163.63 | -1424.18 | n.m.
380 | P14030002 | Stinnett Loop Install OPGW | 298128.074 | 149112.45 | 9355.95 | 11710.2 | 170178.6 | 57.08%
381 | P14030008 | T/KP/Leslie Station Work | 957.318 | 1639374.08 | 39779.44 | 102241.4 | 1781394.92 | 186082%
382 | P14030010 | Leslie Loop ROW KPCo | 46677.945 | 9507.08 |  |  | 9507.08 | 20.37%
383 | P14030011 | Wooton-Leslie ROW KPCo | 266151.091 | 144486.87 |  |  | 144486.87 | 54.29%
384 | P14030013 | Wooton Relaying Work & Telecom | 42318.565 | 312234.4 | 32457.04 | 29475.14 | 374166.58 | 884.2%
385 | P14030015 | Lesile - Stinnett Removal | 0 | 3.23 | 8.72 | 0.42 | 12.37 | n.m.
386 | P14030016 | Leslie - Stinnett ROW (KPCo) | 679767.799 | 664495.35 | 52926.31 |  | 717421.66 | 105.5%
387 | P14030101 | Leslie - Clover Fork Line Work | 69020.139 | 39903.51 | 1177.21 | 5173.84 | 46254.56 | 67.02%
388 | P14030102 | Leslie - Wooton TL to KPCo | 1366105.256 | 11892904.86 | 302799.29 | 948739.88 | 13144444.03 | 962.2%
389 | P14030103 | Leslie - Stinnett TL to KPCo | 495876.459 | 9818382.78 | 319143.34 | 608251.4 | 10745777.52 | 2167%
390 | P14030104 | Leslie Ext Install to KPCo | 109701.853 | 1201.39 | 14739.05 | 33753.86 | 49694.3 | 45.3%
391 | P14030105 | Wooton Transition Fiber | 27940.968 | 142228.79 | 478.01 | 14345.9 | 157052.7 | 562.1%
392 | P14030106 | Leslie Transition Fiber | 26925.425 | 63711.54 | 179.94 | 4972.8 | 68864.28 | 255.8%
393 | P14030109 | Stinnett Station TFC | 0 | 1394.76 | 37.64 | 65.94 | 1498.34 | n.m.
394 | P14030110 | Seg IS Leslie Extension | 0 | 1944711.7 | 50225.66 | 88242.34 | 2083179.7 | n.m.
395 | P16116003 | Stinnett - Pineville ROW KPCo | 556250.343 | 664.83 |  |  | 664.83 | 0.1195%
396 | P16116005 | Stinnett -Pineville T-line | 0 | 14932.66 | 18697.55 | 1318.99 | 34949.2 | n.m.
397 | P17076001 | Kenwood Extension TLINE | 18.394 | -128088.7 | -23150.75 | -12918.11 | -164157.56 | -892452%
398 | P17076005 | Prestonsburg - Thelma 69kV | 0 | -19195.09 | -3088.1 | -1735.19 | -24018.38 | n.m.
399 | P17076006 | Kenwood Extension ROW | 0 | -199622.61 | -10128.28 | -18970.86 | -228721.75 | n.m.
400 | P17076008 | Kenwood Transition Fiber | 18.394 | -835.43 | -7.25 | -20.11 | -862.79 | -4691%
401 | P17076009 | Kenwood Station Fiber Ext | 23.193 | -1204.05 | -19.96 | -42.89 | -1266.9 | -5462%
402 | P17076010 | Van Lear - Kenwood Str Replace | 0 | -860.52 | -77.15 | -73.81 | -1011.48 | n.m.
403 | P17083001 | Garrett-Soft Shell 138kV TLINE | 7865150.127 | 3252895.68 | 610535.25 | 239718.86 | 4103149.79 | 52.17%
404 | P17083002 | Garrett - Soft Shell 138kV ROW | 909651.033 | 1090021.47 | 174037.91 |  | 1264059.38 | 139%
405 | P17083003 | Garrett Switch (Removal) | 1252.023 | -40109.96 | -7512.85 | -3816.73 | -51439.54 | -4109%
406 | P17083005 | Hays Branch S.S | 3254.215 | 443.47 | 14579.51 | 2100.47 | 17123.45 | 526.2%
407 | P17083006 | Garrett - Eastern 138 TLN | 4600653.1 | 697408.71 | 176587.98 | 56523.58 | 930520.27 | 20.23%
408 | P17083007 | Garrett - Eastern 138 ROW | -21870.206 | 842823.81 | 42047 |  | 884870.81 | -4046%
409 | P17083008 | Hays Br. - Morgan Frk. 138 TLN | 2304798.256 | 1796882.46 | 11896.33 | 20846.51 | 1829625.3 | 79.38%
410 | P17083009 | CANCEL Hays Br. Morgan FrkROW | 0 | -15873.54 |  |  | -15873.54 | n.m.
411 | P17083024 | Beaver Creek Station Work | 0 | -4666.48 | -579.62 | -470.07 | -5716.17 | n.m.
412 | P17083031 | Eastern-Hays Branch SS TLINE | 4623873.44 | 523743.22 | 186462.59 | 44185.3 | 754391.11 | 16.32%
413 | P17083032 | Eastern - Hays Branch SS ROW | 1722443.618 | 392597.85 |  |  | 392597.85 | 22.79%
414 | P17083034 | Morgan Fork Remote End | 589098.304 | 19113.53 | 17663.35 | 2041.74 | 38818.62 | 6.589%
415 | P17083037 | Eastern Station Land Purchase | 23793.069 |  | -19183.12 |  | -19183.12 | -80.62%
416 | P17083038 | Snag Fork SS | 123758.072 | 128053.9 | 63095.4 | 13903.93 | 205053.23 | 165.7%
417 | P17083041 | Eastern Station | 2504411.917 | 2998439.65 | 178786.03 | 196220.21 | 3373445.89 | 134.7%
418 | P17083042 | Garrett - Eastern TFC | 887799.049 | 28337.86 | 714.15 | 2155.91 | 31207.92 | 3.515%
419 | P17083043 | Eastern TFC | 68099.145 | 16769.1 | 532.51 | 1079.23 | 18380.84 | 26.99%
420 | P17083044 | Soft Shell-Garrett TFC | 0 | 15365.23 | 602.82 | 927.9 | 16895.95 | n.m.
421 | P17084007 | Myra 138kV Extension TLINE | 163515.095 | 175957.02 | 39161.87 | 59607.79 | 274726.68 | 168%
422 | P17084008 | Myra 138kV Extension ROW | 29251.904 | 33813.53 |  |  | 33813.53 | 115.6%
423 | P17084017 | Beaver Creek - Fremont Cut in | 0 | 3695.28 | 437.24 | 385.27 | 4517.79 | n.m.
424 | P17084018 | Beaver Creek - Elwood Retire | 0 | 2861.64 | 395.25 | 262.53 | 3519.42 | n.m.
425 | P17084019 | Elwood - Cedar Cr. Reconfig. | 0 | 4260.15 | 1077.91 | 437.49 | 5775.55 | n.m.
426 | P17084020 | Elwood - Henry Cl. Recon. @ EL | 0 | 40964.36 | 783.43 | 2995.48 | 44743.27 | n.m.
427 | P17084041 | Beaver Creek-Elwood Retire ROW | 0 | 2844.83 |  |  | 2844.83 | n.m.
428 | P17084042 | Elwood-Cedar Cr. Reconfig. ROW | 0 | 631.9 |  |  | 631.9 | n.m.
429 | P17084043 | Elwood - Henry Cl. Recon. ROW | 0 | 2470.92 |  |  | 2470.92 | n.m.
430 | P17084046 | Beaver Creek - Fremont ROW | 0 | 2304.12 |  |  | 2304.12 | n.m.
431 | P17084051 | Pike 29 SS | 0 | 9142.31 | 101.51 | 756.02 | 9999.84 | n.m.
432 | P17084053 | Beaver Creek Remote End | 0 | 17176.53 | 118.29 | 863.38 | 18158.2 | n.m.
433 | P17084056 | Myra Transition Fiber Cable | 0 | 15044.88 | 179.39 | 1079.02 | 16303.29 | n.m.
434 | P17084057 | Myra Station Fiber Cable Exten | 0 | 11127.09 | 94.34 | 803.51 | 12024.94 | n.m.
435 | P17225001 | Moore Hollow 138kV Station | 0 |  | -325.52 | -59257.57 | -59583.09 | n.m.
436 | P17225003 | Moore Hollow 138kV Extension | 0 | 0 |  | -3774.33 | -3774.33 | n.m.
437 | P17225015 | East Park - Princess 138kV TL | 0 |  |  | 986.93 | 986.93 | n.m.
438 | P18025005 | Kewanee 138 Ext TLINE | -2912326.911 | 2625615.2 |  | 220776 | 2846391.2 | -97.74%
439 | P18025006 | Kewanee 138 Ext ROW | 0 | 18988.31 |  | 1572.17 | 20560.48 | n.m.
440 | P18025007 | Cedar Creek Remote End | 416420.045 | 42645.73 | 6186.23 | 3102.18 | 51934.14 | 12.47%
441 | P18025008 | Beaver Creek Remote End Work | 2450953.676 | 47456.71 | 1715.89 | 3080.49 | 52253.09 | 2.132%
442 | P18025009 | Cedar Creek Fiber Extension | 0 | 1222.2 | -4127.94 | 50.96 | -2854.78 | n.m.
443 | P18025010 | Kewanee Fiber Termination | 0 | 83876.92 | 2773.76 | 3719.32 | 90370 | n.m.
444 | P18025012 | Cedar Creek - Elwood TLINE Wor | 0 | 51547.05 | 5053.89 | 5790.16 | 62391.1 | n.m.
445 | P18025013 | Sprigg - Beaver Cr. TLINE Work | 0 | -127.34 |  | -14.81 | -142.15 | n.m.
446 | P18025014 | S.Pike - Dorton Fiber Cable | 0 | 145514.93 | -32856.28 | 20572.39 | 133231.04 | n.m.
447 | P18221002 | Dorton - Fleming 138kV | 2450953.676 | 105141.98 |  | 13133.19 | 118275.17 | 4.826%
448 | P18221003 | Hazard - Fleming 69kV | 2450953.676 | 238739.16 | 1393.55 | 37817.35 | 277950.06 | 11.34%
449 | P18221004 | Fleming - Fremont 69kV | 4123.303 | 372308.05 | 1648.44 | 69267.27 | 443223.76 | 10749%
450 | P18221005 | Beaver Creek - Fleming 69kV | 3771.912 | 117740.69 |  | 20391.74 | 138132.43 | 3662%
451 | P18221007 | Hazard - Fleming 69kV ROW | 0 | 1561.65 | 60.63 | 266.89 | 1889.17 | n.m.
452 | P18221008 | Fleming - Fremont 69kV ROW | 0 | 4551.59 | 63.46 | 337.38 | 4952.43 | n.m.
453 | P18221010 | Dorton Remote End | 1633969.119 | 2588.95 |  | 260.73 | 2849.68 | 0.1744%
454 | P18221013 | Beaver Creek Remote End | 496.243 | 439.37 |  | 58.89 | 498.26 | 100.4%
455 | P18221014 | Fleming (Jackhorn) 138KV ADSS | 254.4 | 21370.59 | -1512.86 | 1836.36 | 21694.09 | 8528%
456 | P18221017 | Jackhorn Land Purchase | 0 |  | -48948.34 |  | -48948.34 | n.m.
457 | P18221019 | Jackhorn Station T Work | 0 | 60289.32 | 15844.69 | 5751.48 | 81885.49 | n.m.
458 | P18221020 | Jackhorn Station D Work | 6.417 | 26501.31 |  | 1288.28 | 27789.59 | 433062%
459 | P18221021 | Jackhorn 69kV Ring Bus | 8383.756 | 281941.39 |  | 15708.23 | 297649.62 | 3550%
460 | P19036003 | Osborne Extension TLINE | 3002733.306 | 1054296.55 | 117810.83 | 199733.78 | 1371841.16 | 45.69%
461 | P19036004 | Osborne Extension ROW | 0 | 4651 |  |  | 4651 | n.m.
462 | P19036006 | Beaver Creek - Fleming Cut in | 147741.802 | 427346.44 | 7487.67 | 93429.53 | 528263.64 | 357.6%
463 | P19036007 | Beaver Creek Remote End | 0 | 11570.82 | 714.34 | 696.28 | 12981.44 | n.m.
464 | P19036009 | Osborne Fiber Extension | 0 | 218444.62 | 3310.34 | 14585.45 | 236340.41 | n.m.
465 | P19037004 | Henry Clay - Dorton Reconfig. | 1302.149 | 344155.92 | 16976.52 | 28575.14 | 389707.58 | 29928%
466 | P19037005 | Henry Clay - Breaks Reconfi | 1349.966 | 207405.09 | 12375.42 | 18071.39 | 237851.9 | 17619%
467 | P19037006 | Poor Bottom Extension | 146.42 | 23411.32 | 2089.25 | 1832.95 | 27333.52 | 18668%
468 | P19037007 | Henry Clay Ext ROW | 0 | 40807.47 |  |  | 40807.47 | n.m.
469 | P19037011 | Henry Clay-Dorton Reconfig ROW | 235.802 | 204398.36 |  |  | 204398.36 | 86682%
470 | P19037012 | Henry Clay-Breaks Recon ROW | 3420.655 | 261004.3 |  |  | 261004.3 | 7630%
471 | P19037013 | Dorton Station Work | 577.912 | 77550.42 | 7674.44 | 4306.8 | 89531.66 | 15492%
472 | P19037014 | Breaks Station Work | 512.014 | 41720.78 | 5765.28 | 2608.78 | 50094.84 | 9784%
473 | P19037023 | Dorton Transition Fiber Cable | 1236.178 | 1015.2 | 27.79 | 133.87 | 1176.86 | 95.2%
474 | P19037025 | Ratliff Extension | 1236.178 | 7302.09 | 273.6 | 732.93 | 8308.62 | 672.1%
475 | P19037027 | Ratliff Extension ROW | -1898688.573 | 5448.55 |  |  | 5448.55 | -0.287%
476 | P19091011 | Middle Creek BESS | 0 | -0.12 |  | -8.32 | -8.44 | n.m.
477 | P19092007 | Allen -East Prestonsburg TLINE | 177.313 | 27274.4 |  | 2680.59 | 29954.99 | 16894%
478 | P19092008 | Allen -East Prestonsburg ROW | 0 | 616.36 |  |  | 616.36 | n.m.
479 | P19092011 | McKinney -Allen Reconfigure | 307.542 | 42637.68 |  | 4174.42 | 46812.1 | 15221%
480 | P19092012 | Betsy Layne - Allen Reconfigur | 2175.771 | 2122.86 |  | 194.39 | 2317.25 | 106.5%
481 | P19092013 | Allen - Prestonsburg TLINE | 2324.866 | 85315.91 |  |  | 85315.91 | 3670%
482 | P19092017 | McKinney - Allen ROW | 32.582 | 924.37 |  |  | 924.37 | 2837%
483 | P19092019 | Allen - Prestonsburg ROW | 142.356 | 17926.3 |  |  | 17926.3 | 12593%
484 | P19104010 | Bellefonte Ext (KY) Line work | 838817.418 | -10783.57 |  | 6502.72 | -4280.85 | -0.5103%
485 | P19294011 | Inez Station | 0 | 2933.19 |  | 387.11 | 3320.3 | n.m.
486 | P19294012 | Inez XF Replace Baseline | 0 | 3286.18 |  | 332.52 | 3618.7 | n.m.
487 | P19305001 | Orinoco - Stone TLINE | 5175046.551 | 2219612.3 | 149814.14 | 133479.02 | 2502905.46 | 48.36%
488 | P19305002 | Orinoco - Stone ROW | 23725.338 | 403523.73 | 39155.71 |  | 442679.44 | 1866%
489 | P19305009 | Hatfield Station Work | 78994.555 | 151246.32 | 22683.18 | 10048.54 | 183978.04 | 232.9%
490 | P19305010 | Stone Station Work | 11317.616 | 379656.82 | 39899.9 | 13906.96 | 433463.68 | 3830%
491 | P19305016 | New Camp - Orinoco TLINE | -1149161.805 | 3213491.52 | 115266.99 | 379434.04 | 3708192.55 | -322.7%
492 | P19305017 | New Camp - Orinoco ROW | 661572.797 | 695438.34 | 50254.69 |  | 745693.03 | 112.7%
493 | P19305018 | New Camp Tap TLINE | 55295.709 | 232838.51 | 11714.67 | 14376.47 | 258929.65 | 468.3%
494 | P19305019 | New Camp Tap ROW | 3629.254 | 6333.2 | 2758.83 |  | 9092.03 | 250.5%
495 | P19305021 | Belfry - Stone Trans Fiber | 10997.027 | 4660.99 | 165.2 | 318.65 | 5144.84 | 46.78%
496 | P19305023 | New Camp - Orinoco TFC | 13497.246 | 508.45 | 4.35 | 29.01 | 541.81 | 4.014%
497 | P20035004 | Middle Creek-Prestonsburg ROW | 0 | 24480.48 |  |  | 24480.48 | n.m.
498 | P20035007 | MiddleCreek-Preston Telecom | 0 | 47.32 |  | 0.97 | 48.29 | n.m.
499 | P21027001 | Inez 138kV Station Work | 0 | -48626.97 |  | 63618.46 | 14991.49 | n.m.
500 | P21027002 | Inez IPP T-Line Work | 3583.98 | -162053.28 |  | 5220.45 | -156832.83 | -4376%
501 | P21027003 | Inez IPP Metering | 0 | -9640.23 |  | 10859.35 | 1219.12 | n.m.
502 | P21043001 | Thelma-Kenwood 46kV Line | 9629.644 | 373848.07 | 29040.23 | 26146.45 | 429034.75 | 4455%
503 | P21043002 | Thelma-Kenwood 46kV ROW | 638291.874 | 366039.41 |  |  | 366039.41 | 57.35%
504 | P21043003 | Prestonsburg-Thelma TFC | 4948.463 | 3557.97 | 124.75 | 305.03 | 3987.75 | 80.59%
505 | P21043004 | Remote End Work at Thelma | 103428.12 | 34303.32 | 2081.51 | 1209.49 | 37594.32 | 36.35%
506 | P21043008 | Kenwood-Prestonsburg 46kV Line | 580953.064 | 255266.08 | 20740.14 | 4021.93 | 280028.15 | 48.2%
507 | P21043009 | Kenwood-Prestonsburg 46kV ROW | 89472.293 | 539515.22 | 10128.28 |  | 549643.5 | 614.3%
508 | P21043015 | Thelma Station | 447532.045 | 303039.88 | 12168.57 | 10391.25 | 325599.7 | 72.75%
509 | P21205003 | Leslie No.1-Hatfield 69kV | 28208.244 | 610935.72 | 11556.69 | 46258.48 | 668750.89 | 2371%
510 | P21720001 | Bellefonte Station Baseline | 4021.381 | 433439.74 | 22616.95 | 32818.56 | 488875.25 | 12157%
511 | P21720008 | Bellefonte - A.K. Steel 69kV | 1.578 | 17510.68 | 1268.14 | 776.13 | 19554.95 | 1239224%
512 | P21720011 | AshlAshland Relocate Str AB105 | 31851.508 | 38782.82 | 1161.47 | 3120.4 | 43064.69 | 135.2%
513 | P21720012 | Bellefonte 69kV/138kV Bus Tie | 125652.246 | 384118.37 | 2595.43 | 24603.03 | 411316.83 | 327.3%
514 | P21720013 | Bellefonte 69/138 Bus Tie ROW | 0 | 6427.61 | 80.85 | 626.33 | 7134.79 | n.m.
515 | P21753001 | Dewey Station | 237749.72 | 316836.96 | 16401.55 | 32550.13 | 365788.64 | 153.9%
516 | P21753002 | Dewey Station Supplemental | 2133532.079 | 483360.85 | 14946.94 | 45326.79 | 543634.58 | 25.48%
517 | P21753004 | Thelma Remote End Work | 20632.681 | 443804.52 | 14540.6 | 47055.26 | 505400.38 | 2450%
518 | P22005002 | 47th Street Line Work | 168111.477 | 51068.82 | 2908.39 | 5419.99 | 59397.2 | 35.33%
519 | P22012033 | Peter Creek Land Purchase | 0 | 73.76 |  |  | 73.76 | n.m.
520 | P22012039 | Wharncliffe-Coleman Fiber (KY) | 0 | 47.33 | 2.1 | 0.97 | 50.4 | n.m.
521 | P22012047 | Peter Creek-Wharncliffe KY ROW | 0 | 147.86 |  |  | 147.86 | n.m.
522 | P22012049 | Peter Creek-Wharncliffe (KY) | 15.806 | 254.17 | 768.16 | 28.25 | 1050.58 | 6647%
523 | P22012051 | Peter Creek-Coleman ROW | 101809.859 | 98.88 |  |  | 98.88 | 0.09712%
524 | P22012052 | Peter Creek-Coleman | 0 | 625.7 | 1946.49 | 77.24 | 2649.43 | n.m.
525 | P22043001 | AG1-066 Bonnyman Work | 0 | 894.71 |  | 61.39 | 956.1 | n.m.
526 | P22043002 | AG1-066 Bonnyman TLE | 0 | 81.42 |  | 5.59 | 87.01 | n.m.
527 | P22043005 | AG1-066 Bonnyman Metering | 0 | 681.24 |  | 46.75 | 727.99 | n.m.
528 | P22113001 | Gund Switch KY T - BPID | 0 | -14005.61 | -261.38 | 0 | -14266.99 | n.m.
529 | P22113005 | Leslie No.1-Hatfield Line Work | 0 | -696.32 | -27.47 | 7362.31 | 6638.52 | n.m.
530 | P22113006 | Bevins Metering KY-T | 0 | 574302.84 | 5232.93 | 34150.24 | 613686.01 | n.m.
531 | P22745001 | McCoy-Elkhorn Tap Station Work | 128121.739 | 383948.2 | 14647.85 | 27447.75 | 426043.8 | 332.5%
532 | P22745003 | McCoy-Elkhorn Hard Tap | 163350.627 | 123680.28 | 7860.98 | 8452.89 | 139994.15 | 85.7%
533 | P22745004 | McCoy-Elkhorn Tap ROW | 9478.073 | 118054.38 |  |  | 118054.38 | 1246%
534 | P22745005 | Johns Creek - Second Fork | 947352.772 | 186706.77 | 13782.1 | 11639.51 | 212128.38 | 22.39%
535 | P23042017 | Pigeon Creek-Sprigg KY | 0 | 69.34 | 60.86 | 3.97 | 134.17 | n.m.
536 | P23325001 | Leach Substation Work | 13595.923 | 222754.1 | 16328.34 | 17249.03 | 256331.47 | 1885%
537 | P24051001 | Kentucky Power Trans | 5830343.816 | 9726705.46 | 107546.76 | 47888.54 | 9882140.76 | 169.5%
538 | P24083001 | Big Sandy Station | 0 | 36626.38 | 3103.92 | 2277.51 | 42007.81 | n.m.
539 | P24083003 | Thelma Station | 0 | 5633.08 | 94.17 | 651.34 | 6378.59 | n.m.
540 | P24083004 | Big Sandy TFC | 0 | 101.72 | 2.8 | 4.76 | 109.28 | n.m.
541 | P24083005 | Busseyville TFC | 0 | 0 |  |  | 0 | n.m.
542 | P24083006 | Thelma TFC | 0 | 0 |  |  | 0 | n.m.
543 | P24083007 | Big Sandy-Thelma TLine KY | 0 | 42913.27 | 474.89 | 3566.46 | 46954.62 | n.m.
544 | P24083008 | Big Sandy-Thelma ROW | 0 | 37985.13 |  |  | 37985.13 | n.m.
545 | P24125001 | Coleman Station T | 0 | 12640.34 | 10.45 | 846.15 | 13496.94 | n.m.
546 | P24125005 | Stone Station | 0 | 3266.05 | 8.7 | 215.37 | 3490.12 | n.m.
547 | P24125006 | Coleman-Stone TLine | 0 | 50123.15 | 4930.2 | 3062.63 | 58115.98 | n.m.
548 | P24125007 | Coleman-Stone ROW | 0 | 913.73 |  |  | 913.73 | n.m.
549 | P24125009 | Pinson SW | 0 | 1142 |  | 78.37 | 1220.37 | n.m.
550 | TTKY180NN | Forestry KP T non-NERC | 2901965.48 | 5208637.79 | 6152.53 | 324725.75 | 5539516.07 | 190.9%
551 | TTKY180NR | Forestry KY T NERC | 702812.947 | 72090.1 | 65.47 | 10589.63 | 82745.2 | 11.77%
552 | XHWCAP180 | For Property Acctg Use Only - GLBU 110 | 0 | 479027.19 | 20529.51 | 0 | 499556.7 | n.m.
553 | Other Budgeted Projects |  | 47764800.078 | 0 | 0 | 0 | 0 | Other
554 | Total GLBU 180 (Transmission) |  | 124290671.096 | 120157737.442 | 3889649.17 | 9392.62 | 124056779.232
555 | Total Kentucky Power CWIP Additions |  | 240688725.058 | 228509525.082 | 6074165.86 | 387399.16 | 234971090.102
556
557 | X00000288 | For Property Acctg Use Only - GLBU 117 | Property Acctg | -38272432.36 | 0 | -69423.16 | -38341855.52 | Property Acctg
558 | X00000306 | For Property Acctg Use Only - GLBU 180 | Property Acctg | -113742832.65 | 0 | 0 | -113742832.65 | Property Acctg
559 | X00000317 | For Property Acctg Use Only - GLBU 110 | Property Acctg | -94767517.89 | 0 | 0 | -94767517.89 | Property Acctg
560 | Total Kentucky Power Transfers to 101/106 |  |  | -246782782.9 | 0 | -69423.16 | -246852206.06
561
562 | Total Kentucky Power CWIP Activity 12 Months Preceding the Historical Test Year April 2022 - March 2023 |  | 240688725.058 | -18273257.818 | 6074165.86 | 317976 | -11881115.958
563
564
565 | Reconciliation of AFUDC Capitalized to Section V, Schedule 8, Line 13 of the Company's Application
566 | 6074165.86 | AFUDC Capitalized per General Ledger Reported on Line 625
567 | 35116.8 | Reconciling Item: Other Manual Credits to AFUDC Recorded in General Ledger
568 | 6039049.06 | AFUDC Capitalized per Property Subledger Reported in Section V, Schedule 8, Line 13

## 12 Mos. Preceding Test Year
Schedule D (12 Months Preceding the Historical Test Year)
Kentucky Power Company
Case No. 2025-00257
Construction Projects for the 12 Months Preceding the Historical Test Year
June 2023 - May 2024
Definitions:
| (E)* | Represents AFUDC Debt and AFUDC Equity (Cost Components 023 and 024, respectively)
| (F)* | Represents allocated construction overheads (Cost Component 020)
| n.m. | Not meaningful
| Property Acctg | Property Accounting perpetual administrative projects used to transfer plant in service or hold temporary charges later cleared to other work orders, e.g., construction overheads, suspense, labor accrual, etc.
Actual Accumulated Costs - June 2023 through May 2024
Line No. | Project No. | Description of Project | Most Recent Budget Estimate | Construction Amount | AFUDC Capitalized | Indirect Costs Other | Total Cost | Estimated Physical Percent Completed June 2023 Through May 2024
(A) | (B) | (C) | (I) | (D) | (E)* | (F)* | (G=D+E+F) | (H) = (G)/(I) | GLBU-Project
1 | GLBU 110 (Distribution)
2 | 000001818 | KY/Svc Restoration NonMjr Evt | 5241246.798 | 4586041.14 | 12853.42 | 1082621.52 | 5681516.08 | 108.4%
3 | 000002241 | KP-Damage Claims-Reimburse | 234439.649 | 354020.85 | 479.52 | 86091.06 | 440591.43 | 187.9%
4 | 000004464 | KP/Offsystem Storm Assistance | 0 | 9.2015e-12 | 0 | 0 | 9.2015e-12 | n.m.
5 | 000004737 | KPSectionalizing Program | 2106742.521 | 1248301.56 | 2468.33 | 279460.9 | 1530230.79 | 72.63%
6 | 000005234 | KyPCo-D Capital Software Dev | 688765.009 | 2929871.45 |  |  | 2929871.45 | 425.4%
7 | 000007558 | KP-PQ-QOS Mitigation | 33901.26 | 542.52 | 0.73 | 140.86 | 684.11 | 2.018%
8 | 000007599 | KP-Failed Equip No Outage | 3631261.554 | 3380300.06 | 4270.59 | 808293.76 | 4192864.41 | 115.5%
9 | 000007615 | KP-Cust Req Relocate | 263637.9 | 184885.54 | 155.01 | 68429.41 | 253469.96 | 96.14%
10 | 000007818 | KP/Small Local Asset Improv | 6197138.549 | 5665344.9 | 33026.82 | 1323441.66 | 7021813.38 | 113.3%
11 | 000016528 | KYCutout-Arrester | 242604.657 | 420291.71 | 4664.86 | 101855.12 | 526811.69 | 217.1%
12 | 000025229 | 2018 Gen Plt Cap Blkt - KYPC-D | 201842.587 | 1466090.7 | 39419.95 |  | 1505510.65 | 745.9%
13 | 110KYLSBO | Dist KY Lease BO | 0 | 757447.04 |  |  | 757447.04 | n.m.
14 | A15710080 | Tenth Street Station TTMP | 0 | -6073 |  | -1145.17 | -7218.17 | n.m.
15 | A15710085 | Olive Hill Station TTMP | -126.855 | 712.83 | 2769.34 | 153.43 | 3635.6 | -2866%
16 | A15710086 | Hayward Station TTMP | -9026.079 | 19766.28 | 3240.91 | 4390.35 | 27397.54 | -303.5%
17 | A20045031 | South Pikeville Station NIP | 0 | 108.56 | 262.22 | 21.74 | 392.52 | n.m.
18 | A20045075 | Prestonsburg NIP Track 6 | 0 | 74.42 | 179.73 | 14.9 | 269.05 | n.m.
19 | A20045086 | Olive Hill Station NIP | 0 | 21.33 | 51.52 | 4.27 | 77.12 | n.m.
20 | A20045087 | Daisy Station NIP | 0 | 83.06 | 200.62 | 16.63 | 300.31 | n.m.
21 | A20077007 | Soft Shell Sta TTMP | 0 | 52.99 | 127.99 | 10.61 | 191.59 | n.m.
22 | A20077008 | Bulan Sta TTMP | 0 | 39.06 | 94.33 | 7.82 | 141.21 | n.m.
23 | A20077010 | Haddix Sta TTMP | 0 | 49.63 | 119.88 | 9.94 | 179.45 | n.m.
24 | A20077011 | Jackson Sta TTMP | 0 | 33.77 | 81.56 | 6.76 | 122.09 | n.m.
25 | A20077013 | Engle Sta TTMP | 0 | 34.55 | 83.46 | 6.92 | 124.93 | n.m.
26 | A20077017 | Whitesburg Sta TTMP | 0 | 42.44 | 102.51 | 8.5 | 153.45 | n.m.
27 | A20077018 | Mayking Sta TTMP | 0 | 43.5 | 105.06 | 8.71 | 157.27 | n.m.
28 | A20077019 | Collier Sta TTMP | 0 | 74.3 | 179.48 | 14.88 | 268.66 | n.m.
29 | A20077022 | South Pikeville Sta TTMP | 0 | 38.78 | 93.66 | 7.76 | 140.2 | n.m.
30 | A20077023 | CANCEL - Myra Sta TTMP | 0 | -2619.39 | -204.57 | -468.09 | -3292.05 | n.m.
31 | A20705033 | CANCEL: Barrenshe Station | 0 |  |  | 0.74 | 0.74 | n.m.
32 | A20705068 | Coleman Stn Needs Assessment | 0 | 470.88 | 629.86 | 126.13 | 1226.87 | n.m.
33 | A20705085 | Tom Watkins Station Needs Asmt | 0 | 117.02 | 282.66 | 23.43 | 423.11 | n.m.
34 | A20934001 | Falcon Elim Cust DC System | 0 | 12469.32 | 1703.16 | 3258.03 | 17430.51 | n.m.
35 | A21050054 | Tenth St GE/SEL Relay | 0 | 4495.43 |  | 2767.81 | 7263.24 | n.m.
36 | A21222009 | Tygart Station | 0 | 225041.69 | 9515.61 | 48097.5 | 282654.8 | n.m.
37 | A21222015 | Jackson Sta TTMP | -201.883 | 7618.3 | 1124.76 | 1682.76 | 10425.82 | -5164%
38 | A21505006 | Jackson Station NIP | 0 | 137.16 | 331.28 | 27.46 | 495.9 | n.m.
39 | A21505009 | Coalton NIP | 0 | 36.94 | 89.22 | 7.4 | 133.56 | n.m.
40 | A23088001 | Barrenshe Mobile Pad Install | 0 | 303113.57 | 23345.1 | 149496.25 | 475954.92 | n.m.
41 | A23750004 | Keyser Station XFRMR Failure | 0 | 1164002.84 | 5844.75 | 24486.93 | 1194334.52 | n.m.
42 | A24112002 | CANCEL-DO NOT USE | -3640.07 | 56.05 | 50.9 | 11.22 | 118.17 | -3.246%
43 | A24112010 | CANCEL-DO NOT USE | 1099.172 | 28.3 | 25.69 | 5.67 | 59.66 | 5.428%
44 | A24112012 | CANCEL-DO NOT USE | 1099.172 | 145.14 | 160.51 | 32.44 | 338.09 | 30.76%
45 | A25101001 | CANCEL-DO NOT USE | 0 | 23.82 | 57.54 | 4.77 | 86.13 | n.m.
46 | A25101002 | CANCEL-DO NOT USE | 0 | 12.8 | 30.93 | 2.57 | 46.3 | n.m.
47 | A25101003 | CANCEL-DO NOT USE | 0 | 13.7 | 33.07 | 2.74 | 49.51 | n.m.
48 | A25101005 | CANCEL-DO NOT USE | 0 | 4.59 | 11.07 | 0.92 | 16.58 | n.m.
49 | A25101006 | CANCEL-DO NOT USE | 0 | 12.84 | 31.01 | 2.57 | 46.42 | n.m.
50 | B110KYSRR | D/KY/Non-Specific Work - Sta | -358537.11 | 560789.11 | 23771.42 | 74268.55 | 658829.08 | -183.8%
51 | B110KYTEL | Distr Telecom Sta/Fiber - KY | 0 | 13135.96 | 97.53 |  | 13233.49 | n.m.
52 | DCTSUVLKY | KY CATS Monthly Unvouch Liab | 0 | -346679.58 |  |  | -346679.58 | n.m.
53 | DMS22KK14 | KY/ME/Flood 14 07/28/22 | 0 | -29556.98 | 373.25 | -2937.75 | -32121.48 | n.m.
54 | DMS23KK01 | KY Pre/Valid Major Storm 01 | 0 | 127882.32 |  | 27206.41 | 155088.73 | n.m.
55 | DMS23KK02 | KY/ME/Wind 02 03/03/2023 | 0 | -649739.3 |  | -21104.15 | -670843.45 | n.m.
56 | DMS23KK03 | KY/ME/Wind 03 03/25/2023 | 0 | 106270.18 | -1694.08 | 55492.88 | 160068.98 | n.m.
57 | DMS23KK04 | KY/ME/Wind 04 04/01/2023 | 0 | -610915.8 |  | 142496.85 | -468418.95 | n.m.
58 | DMS23KK05 | KY Pre/Valid Major Storm 05 | 0 | -109464.93 |  | -9108.47 | -118573.4 | n.m.
59 | DMS23KK06 | KY Pre/Valid Major Storm 06 | 0 | 37619.37 | 20.63 | 5414.44 | 43054.44 | n.m.
60 | DMS23KK07 | KY Pre/Valid Major Storm 07 | 0 | 65632.57 | 33.5 | 9836.92 | 75502.99 | n.m.
61 | DMS23KK08 | KY Pre/Valid Major Storm 08 | 0 | 68891.83 | 58.23 | 10814.21 | 79764.27 | n.m.
62 | DMS23KK09 | KY Pre/Valid Major Storm 09 | 0 | 71773.59 | 39.36 | 17834.83 | 89647.78 | n.m.
63 | DMS24KK01 | KY Pre/Valid Major Storm 01 | 0 | 64365.43 | 43.61 | 15640.84 | 80049.88 | n.m.
64 | DMS24KK02 | KY Pre/Valid Major Storm 02 | 0 | 208157.22 | 127.82 | 44011.35 | 252296.39 | n.m.
65 | DMS24KK03 | KY Pre/Valid Major Storm 03 | 0 | 115421.12 | 17.45 | 33835.14 | 149273.71 | n.m.
66 | DMS24KK04 | KY/ME/Thunderstorm 04.02.2024 | 0 | 996969.42 | 420.56 | 146631 | 1144020.98 | n.m.
67 | DMS24KK05 | KY Pre/Valid Major Storm 05 | 0 | 6871.43 | 9.75 | 2146.78 | 9027.96 | n.m.
68 | DMS24KK07 | KY Pre/Valid Major Storm 07 | 0 | 151449.19 | 63.02 | 16054.03 | 167566.24 | n.m.
69 | DMS24KK08 | KY/ME/Thunderstorm 05.26.2024 | 0 | 1415083.83 | 160.76 | 117877.76 | 1533122.35 | n.m.
70 | DP14K02A0 | Raccoon Sta - D line exits | -7.639 | -41649.9 | 9100.18 |  | -32549.72 | 426099%
71 | DP14K02B0 | KP/Raccoon Sta - 30 MVA 138-34 | 0 | 689.67 |  | 139.37 | 829.04 | n.m.
72 | DP16K03A0 | Tygart Sta - D line | 1468153.917 | 2164377.71 | 23040.89 | 486799.21 | 2674217.81 | 182.1%
73 | DP16K03B0 | Tygart Sta - Dist Station | 3112853.158 | 5372697.83 | 137164.68 | 1347530.84 | 6857393.35 | 220.3%
74 | DR18K02A0 | Hazard 2018 DA Plan | -2190.102 | 7922.76 | 8771.47 |  | 16694.23 | -762.3%
75 | DR19K05A0 | Hazard DA 2019 - D line | -29852.065 | 32145.77 | 25110.83 |  | 57256.6 | -191.8%
76 | DR19K05B0 | Hazard DA 2019 - Shamrock | 157680.065 | 78665.53 | 20899.65 | 19459.35 | 119024.53 | 75.48%
77 | DR19K05B2 | Hazard DA 2019 - Slemp | 0 |  | -46.82 |  | -46.82 | n.m.
78 | DR20K02B2 | Breaker Repl - Grayson | 0 | -11677.21 |  |  | -11677.21 | n.m.
79 | DX16K02A0 | Coalton Sta - US Rt 60 PPR | 0 | 92.25 |  |  | 92.25 | n.m.
80 | DX21K0002 | Buckhorn DA Comm. Upgrade | 0 | 379.22 |  |  | 379.22 | n.m.
81 | DX21K0003 | Dewey DA Coms Upgrade | 0 | 690217.61 | 8815.62 | 112080.99 | 811114.22 | n.m.
82 | DX23K01A0 | Hyden DA Upgrade | 0 | 10059.47 | 181.14 |  | 10240.61 | n.m.
83 | EDN011333 | Customer Meter/Kp | 892667.696 | 329033.84 |  | 30295.78 | 359329.62 | 40.25%
84 | EDN012370 | Ds/Kp/Public Relocation | 964271.601 | 873573.91 | 7161.71 | 279375.66 | 1160111.28 | 120.3%
85 | EDN014651 | Ds/Kp/Cs-New Customers | 3970840.235 | 3995708.51 | 2496.59 | 916923 | 4915128.1 | 123.8%
86 | EDN014658 | Ds/Kp/Cs-Upgrades | 298817.278 | 188613.75 | 90.05 | 48941.72 | 237645.52 | 79.53%
87 | EDN014680 | Ds-Kp-Ai Pole Replacement | 1476921.367 | 1188732.86 | 3187.24 | 288117.85 | 1480037.95 | 100.2%
88 | EDN014687 | Ds-Kp-Ai Aepc Make Ready | 2210254.226 | -31234.46 | -97.85 | -14056.26 | -45388.57 | -2.054%
89 | EDN014694 | Ds-Kp-Ai Other Make Ready | 689588.443 | 1191077.26 | 9010.48 | 329189.71 | 1529277.45 | 221.8%
90 | EDN014701 | Ds Kp Ai Support Cs Res | 0 | 6713.23 | 17.32 | 2014.79 | 8745.34 | n.m.
91 | EDN014720 | Ds-Kp-Ai Recloser Replacement | 1284646.482 | 1633935.59 | 17722.24 | 406096.21 | 2057754.04 | 160.2%
92 | EDN015042 | Ds-Kp-Small Wire Repl Ovhd | 736018.498 | 85877.39 | 304.31 | 14985.06 | 101166.76 | 13.75%
93 | EDN100033 | Ds/Kp/C&I New | 3956362.025 | 1595560.99 | 2498.7 | 471698.02 | 2069757.71 | 52.31%
94 | EDN100044 | Ds/Kp/C&I Upgrades | 115606.317 | 100568.23 | 65.82 | 29037.52 | 129671.57 | 112.2%
95 | EDN100577 | Ds-Kp-Ai Ckt Inspections | 633298.922 | 254802.42 | 2054.8 | 59753.27 | 316610.49 | 49.99%
96 | EDN103175 | Ds Kp Anda | 0.014 | 12731314.5 |  | -12741493.82 | -10179.32 | -72709429%
97 | EON011326 | Line Transformer/Kp | 4133307.758 | 4113437.8 |  | 729140.3 | 4842578.1 | 117.2%
98 | ETN000110 | T Kp D Anda | 0 | 315524.15 |  | -315524.15 | 0 | n.m.
99 | IT1101722 | CIS-Net Meter/Spc Bill-KYP D | 0 | 253066.84 | 16266.94 |  | 269333.78 | n.m.
100 | IT1101723 | CIS-Smart Grid Gateway-KYP D | 0 | 0 | -8.44 |  | -8.44 | n.m.
101 | IT1101724 | CIS-Meter Enhancements-KYP D | 0 | 5038.85 | 3370.92 |  | 8409.77 | n.m.
102 | IT1101725 | CIS-Common Deployment-KYP D | 0 | 566288.96 | 53217.32 |  | 619506.28 | n.m.
103 | IT1102013 | Field Mobility iPAD CI - KYP D | 0 | 60581.32 | 156.66 |  | 60737.98 | n.m.
104 | IT1102049 | CIS-Agent Desktop Replat-KYP D | 0 | 5329.04 | 175.81 |  | 5504.85 | n.m.
105 | IT110ADMS | ADMS Imp DSN DNEX-KYP D | 0 | 1666259.85 | 50585.72 |  | 1716845.57 | n.m.
106 | IT110CCIC | Cloud Comp Imp Cost - KyP D | 0 | 513160.34 |  |  | 513160.34 | n.m.
107 | ITCB11000 | KENTUCKY POWER - DIST | 448587.87 | 861027.84 | 67318.76 |  | 928346.6 | 206.9%
108 | ITCF11000 | Tcom Field Ops Blanket-KYPCO D | 0 | 147043.32 | 939.02 |  | 147982.34 | n.m.
109 | ITCT11004 | Ashland-Lynchburg MW Upgrade ( | 372644.145 | 426476.55 | 26585.48 |  | 453062.03 | 121.6%
110 | ITCW11004 | KY Next Generation Radio Sys | 152321.635 | 352616.59 | 7049.09 |  | 359665.68 | 236.1%
111 | ITCW11006 | NGUCS Weddington Leatherwood | 372644.145 | 145030.63 | 1600.54 |  | 146631.17 | 39.35%
112 | ITPCLC110 | PC Lifecycle CI - 110 | 257032.024 | 154626.13 |  |  | 154626.13 | 60.16%
113 | KEPDS2201 | KPCo Storm - Distribution | -49737.682 | -1221.97 | 8289.9 | 9990.43 | 17058.36 | -34.3%
114 | KEPDS2202 | KPCo Storm - Distribution | 0 | -807.15 | -12.81 | -268.81 | -1088.77 | n.m.
115 | KY5YCYCLE | KY D 2017-00179 | 3430698.448 | 1253557.69 |  | 346190.09 | 1599747.78 | 46.63%
116 | KYCAPTOOL | KY Purch. Cap Tools | 22364.013 | 179748.13 |  |  | 179748.13 | 803.7%
117 | P13064028 | D Line Work | 0 | 9665.68 | 7.13 | 1968.11 | 11640.92 | n.m.
118 | P14030009 | Stinnett Station & Telecom | 90485.868 | 58806.26 | 11055.63 | 10939.86 | 80801.75 | 89.3%
119 | P17076002 | Kenwood Station | 0 | 3391.86 |  | 538.93 | 3930.79 | n.m.
120 | P17076003 | Prestonsburg Remote End Work | 0 | 1140.59 |  | 228.35 | 1368.94 | n.m.
121 | P17076011 | Distribution work at Kenwood | -126.855 | 1011.41 |  | 86.27 | 1097.68 | -865.3%
122 | P17083016 | McKinney Station Work | -121130.632 | 373437.54 | 23896.98 | 91160.88 | 488495.4 | -403.3%
123 | P17083025 | Soft Shell Station Work (KPCo) | 606118.116 | 1049416.22 | 33397.22 | 167984.25 | 1250797.69 | 206.4%
124 | P17083030 | Garrett Station (Distribution) | 277887.777 | 325228.58 | 33806.62 | 58001.24 | 417036.44 | 150.1%
125 | P17083033 | Garrett Land Purchase | 1954.465 | 1022.44 | 2040.74 |  | 3063.18 | 156.7%
126 | P17083040 | Garrett Station | 367049.784 | 931836.99 | 89937.35 | 221811.85 | 1243586.19 | 338.8%
127 | P17084005 | Myra Station | 0 | 10186.86 | 11814.21 | 2453.98 | 24455.05 | n.m.
128 | P17084006 | Myra Land Purchase | 0 | 7389.23 |  |  | 7389.23 | n.m.
129 | P17084025 | Elwood Station Retirement | 0 | -24683.34 | -4548.92 | -11488.23 | -40720.49 | n.m.
130 | P17084055 | Myra Station | 0 | 84.23 | 0.64 | 826.62 | 911.49 | n.m.
131 | P17225006 | Ramey Station | 0 | 1496.69 | -2462.79 | -2785.59 | -3751.69 | n.m.
132 | P18025001 | Kewanee Station - Baseline Wor | -307262.775 | 253440.14 | 135080.61 | 56210.85 | 444731.6 | -144.7%
133 | P18025002 | Kewanee Station Land Purchase | 0 | 3537.28 | 3280.68 |  | 6817.96 | n.m.
134 | P18025018 | Kewanee Transco to KPCo | 0 | 171641.37 | 49679.79 | 35750.48 | 257071.64 | n.m.
135 | P18221011 | Collier Remote End | -70093.57 | 7576.49 | 2684.23 | 1622.48 | 11883.2 | -16.95%
136 | P19036002 | Burton Station Retirement | 0 | 4126.81 |  | 1112.05 | 5238.86 | n.m.
137 | P19036005 | Osborne 69kV Station | -193107.158 | 199594.81 | 260518.48 | 49417.05 | 509530.34 | -263.9%
138 | P19036011 | Osborne 69kV Land Purchase | 0 | 9243.69 |  |  | 9243.69 | n.m.
139 | P19036012 | Osborne Station T | 0 | 12716.04 | 11008.94 | 2972.03 | 26697.01 | n.m.
140 | P19037003 | Henry Clay Land Purchase | -127481.539 | 24160.37 |  |  | 24160.37 | -18.95%
141 | P19037008 | Henry Clay Station | -137422.41 | 51647.74 | 1455.53 | 12535.84 | 65639.11 | -47.76%
142 | P19037016 | Ratliff 69kV Station | -54968.966 | 44421.97 | 4740.02 | 13151.25 | 62313.24 | -113.4%
143 | P19037017 | New Ratliff Land Purchase | -102401.264 | 37327 |  |  | 37327 | -36.45%
144 | P19092002 | Allen Station (Dist) | -525234.356 | 134221.09 | 3709.74 | -54466 | 83464.83 | -15.89%
145 | P19092014 | Prestonsburg Remote End | -70630.535 | 64098.82 | 993.78 | 11407.63 | 76500.23 | -108.3%
146 | P19092016 | McKinney Remote End Work | -119070.457 | 97791.12 | 201.07 | 20853.99 | 118846.18 | -99.81%
147 | P19092022 | Allen Station Land Purchase | -100022.319 | 4216.67 | 4007.8 |  | 8224.47 | -8.223%
148 | P19092023 | Allen Station | 2522458.988 | 1222306.45 | 19121.8 | 257827.75 | 1499256 | 59.44%
149 | P19305013 | Orinoco KPCO D | -361758.17 | 614436.69 | 61574.83 | 161279.68 | 837291.2 | -231.5%
150 | P19305020 | Orinoco Station Land Purchase | 996.322 | 6449.06 |  |  | 6449.06 | 647.3%
151 | P19305022 | New Camp Station | 24180.948 | 175982.05 | 29141.74 | 39887.01 | 245010.8 | 1013%
152 | P20035005 | Remote End at Prestonsburg | -2610.544 | 599.97 | 62.25 | 30.03 | 692.25 | -26.52%
153 | P20035008 | Middle Creek Station | -33252.508 | 1201.27 | 73.68 | 300.07 | 1575.02 | -4.737%
154 | P21043005 | Prestonsburg Remote End | -130652.584 | 14070.99 | 2006.28 | 3901.63 | 19978.9 | -15.29%
155 | P21043006 | Kenwood Station | 0 | 5473.21 | 3455.81 | 1112.45 | 10041.47 | n.m.
156 | P21720003 | Coalton Remote End | -10399.428 | 7171.43 | 1369.67 | 1088.85 | 9629.95 | -92.6%
157 | P21720007 | Raceland Remote End | -17421.075 | 6856.07 | 1374.16 | 1320.87 | 9551.1 | -54.82%
158 | P21753003 | Stanville Remote End Work | -57974.412 | 3385.62 | 365.89 | 413.84 | 4165.35 | -7.185%
159 | P22005001 | 47th Street Station | 1008.193 | 29004.47 | 6178.17 | 7261.94 | 42444.58 | 4210%
160 | P22012001 | Coleman Station Work | 0 | 381.6 | 815.93 | 74.92 | 1272.45 | n.m.
161 | P22012002 | Peter Creek Station Work | 0 | 437.46 | 1419.08 | 87.58 | 1944.12 | n.m.
162 | P22113002 | Gund Metering KY D - BPID | 14896.04 | 137046.58 | 5233.75 | 8628.54 | 150908.87 | 1013%
163 | TP1403006 | T Funded D Work | -216943.146 | 1364381.23 | 42040 | 371977.46 | 1778398.69 | -819.8%
164 | TP1708310 | T Funded D Garret Area Imp | -192746.454 | 2366511.23 | 20954.31 | 633276.32 | 3020741.86 | -1567%
165 | TP1802510 | KEWANEE DLINE WORK | 320496.459 | 157989.59 | 2475.98 | 38077.38 | 198542.95 | 61.95%
166 | TP1822105 | Fleming T-Funded D | 0 | 69946.1 | 220.24 | 20457.43 | 90623.77 | n.m.
167 | TP1903604 | T Funded D | 5787.686 | 54449.86 | 596.66 | 14983.28 | 70029.8 | 1210%
168 | TP1930505 | Orinoco T Funded D (Dist Line) | 0 | 391724.06 | 713.46 | 53934.79 | 446372.31 | n.m.
169 | TREEREL21 | ROW Capital Widening & Removal | 5.082 | -24711.15 |  |  | -24711.15 | -486249%
170 | TREEREL23 | ROW Capital Widening & Removal | 4697274.052 | 3860779.31 |  |  | 3860779.31 | 82.19%
171 | TREEREL24 | ROW Capital Widening & Removal | 2198758.604 | 1114048.98 |  |  | 1114048.98 | 50.67%
172 | XHWCAP110 | HW CAP CI - 110 | 0 | 34291.72 | 364.53 |  | 34656.25 | n.m.
173 | Other Budgeted Projects |  | 25849947.449 |  |  |  | 0 | 0%
174 | Total GLBU 110 (Distribution) |  | 83574634.301 | 83935767.09 | 1560584.52 | -165514.67 | 85330836.94
175 | GLBU 117 (Generation)
176 | 000005237 | KyPCo-G Capital Software Dev | 53733.945 | 593628.23 |  |  | 593628.23 | 1105% | 117-000005237 | Budget Estimate is just for the referenced year-ending May
177 | 000025231 | 2018 Gen Plt Cap Blkt - KYPC-G | 0 | 5907.45 |  |  | 5907.45 | n.m. | 117-000025231
178 | BSPPB0002 | Boiler & Auxiliaries PPB<100k | 27286.031 | 5212.52 |  | 7053.31 | 12265.83 | 44.95% | 117-BSPPB0002
179 | BSPPB0007 | Condenser & Aux. PPB<100k | 0 | 23239.03 | 718.1 | 78.9 | 24036.03 | n.m. | 117-BSPPB0007
180 | BSPPB0008 | Clg Water Facilities PPB<100k | 276067.299 | 54853.07 | 1601.33 | 12729.99 | 69184.39 | 25.06% | 117-BSPPB0008
181 | BSPPB0009 | Effluent WW Treating PPB<100k | 0 | 19412.93 | 168.42 | -281292.19 | -261710.84 | n.m. | 117-BSPPB0009
182 | BSPPB0013 | Other Costs PPB<$100k | 28637.422 | 474661.94 | 18407.94 | -1795672.29 | -1302602.41 | -4549% | 117-BSPPB0013
183 | BSPPB0016 | Turb & Support Sys PPB<100k | 0 | -15930.78 |  | -8845.85 | -24776.63 | n.m. | 117-BSPPB0016
184 | BSPPBOUT1 | Unit 1PPB Outage<100k | 423526.055 | 35418 | 1249.75 | 3619.82 | 40287.57 | 9.512% | 117-BSPPBOUT1
185 | BSPPBS339 | REPLACE 15 BREAKERS "A" BUS | 0 | 356225.41 | 34002.11 | -19517.06 | 370710.46 | n.m. | 117-BSPPBS339
186 | BSPPBS340 | REPLACE 15 BREAKERS "B" BUS | 0 | 357236.5 | 36564.98 | -16899.93 | 376901.55 | n.m. | 117-BSPPBS340
187 | BSPPBS368 | Big1 Boiler Exit Gas Duct Repl | 1530189.504 | 861657.77 | 17936.71 | 150845.54 | 1030440.02 | 67.34% | 117-BSPPBS368
188 | IT117CCIC | Cloud Computing Imp Cost-KyP G | 0 | 146093.5 |  |  | 146093.5 | n.m. | 117-IT117CCIC
189 | ITCB11700 | KENTUCKY POWER - GEN | 0 | 34754.63 | 3418.4 |  | 38173.03 | n.m. | 117-ITCB11700
190 | ITCBLBRTY | KENTUCKY POWER LIBERTY | 0 | 10927.85 | 1049.35 |  | 11977.2 | n.m. | 117-ITCBLBRTY
191 | ITPCLC117 | PC Lifecycle CI - 117 | 11266.991 | 1531.77 |  |  | 1531.77 | 13.6% | 117-ITPCLC117
192 | ML1E25C02 | ML1 E COOLING TOWER REPLACMENT | 176022.417 | 1288353.56 | 14364.32 | 35349.87 | 1338067.75 | 760.2% | 117-ML1E25C02
193 | MLKP26265 | ML U2 Cooling Tower Reinforce | 1096610.033 | 164965.38 | 13549.35 | 6608.2 | 185122.93 | 16.88% | 117-MLKP26265
194 | MLL1CGRPL | ML U1 Clinker Grinder Rpl - KY | 43997.027 | 81123.25 | 1726.04 | 5677.27 | 88526.56 | 201.2% | 117-MLL1CGRPL
195 | MLL2CGRPL | ML U2 Clinker Grinder Rpl - KY | 133452.945 | 91508.98 | 2133.76 | 5665.3 | 99308.04 | 74.41% | 117-MLL2CGRPL
196 | MLLEC1VHL | ML E U1 VHP/HP&LPA Turbn Insp | 298295.199 | 568618.8 | 6703.55 | 14124.42 | 589446.77 | 197.6% | 117-MLLEC1VHL
197 | MLLEP2LBI | ML E U2 LPB Turb Insp Liberty | 0 | -683.25 |  |  | -683.25 | n.m. | 117-MLLEP2LBI
198 | MLLHAULRD | Mitchell Haul Road Relocate | 257240.84 | 34335.97 | 701.85 | 3092.45 | 38130.27 | 14.82% | 117-MLLHAULRD
199 | MLLPC0ELG | ML PCC U0 ELG/CCR Comply - 117 | 6526563.823 | 4173618.74 | 911605.48 | 231367.77 | 5316591.99 | 81.46% | 117-MLLPC0ELG
200 | MLLPC0LIM | ML PCC U0 Lime Conversion 117 | -33291.033 | 84804.42 | -3488.18 | 5420.36 | 86736.6 | -260.5% | 117-MLLPC0LIM
201 | MLLPC2CTC | ML PCC U2 Cooling Twr Cmp 117 | -174.942 | 7376.59 |  | 220.7 | 7597.29 | -4343% | 117-MLLPC2CTC
202 | MLLPC2ESP | ML PCC U2 ESP Upgrades 117 | -50470.045 | 45092.99 |  | 1413.44 | 46506.43 | -92.15% | 117-MLLPC2ESP
203 | MLLPCT1BP | ML U1 Cooling Tower Canopy KYP | 682955.453 | 935685.82 | 5410.19 | 19389.57 | 960485.58 | 140.6% | 117-MLLPCT1BP
204 | MLLPCT1PC | ML1 Cool Twr Canopy PreCI KPCo | 299894.262 | -161927.24 | 2970.36 | -7957.17 | -166914.05 | -55.66% | 117-MLLPCT1PC
205 | MLLPPBSHD | ML Minor PPB Liberty Shadow | 2030564.039 | 2710322.94 | 52396.18 | 147434.97 | 2910154.09 | 143.3% | 117-MLLPPBSHD
206 | MLLSC1AHB | ML S U1 Air Htr Bskt Rplc Lbty | 463303.058 | 460794.81 | 77697.56 | 11624.22 | 550116.59 | 118.7% | 117-MLLSC1AHB
207 | MLLSC2AHB | ML S U2 Air Htr Bskt Rplc Lbty | 524.83 | 1449.31 |  | 51.1 | 1500.41 | 285.9% | 117-MLLSC2AHB
208 | MLLVC2CL4 | ML V U2 Cat Layer 4 Rplc Lbty | 349.885 | 50.82 |  | -0.1 | 50.72 | 14.5% | 117-MLLVC2CL4
209 | XHWCAP117 | HW CAP CI - 117 | 0 | 18736.9 | 147.9 |  | 18884.8 | n.m. | 117-XHWCAP117
210 | Other Budgeted Projects |  | 464919.201 |  |  |  | 0 | 0% | Other
211 | Total GLBU 117 (Generation) |  | 14741464.239 | 13469058.61 | 1201035.45 | -1468417.39 | 13201676.67
212 | GLBU 180 (Transmission)
213 | 000005273 | KyPCo-T Capital Software Dev | 49825.313 | 1001538.9 |  |  | 1001538.9 | 2010%
214 | 000025230 | 2018 Gen Plt Cap Blkt - KYPC-T | 49167.172 | 85754.62 | 153.46 |  | 85908.08 | 174.7%
215 | 180KYLSBO | Trans KY Lease Buyout | 0 | 247580.34 |  |  | 247580.34 | n.m.
216 | A14068001 | Baker 765kV Physical Security | 0 | 44594.54 | 713.44 | 6405.02 | 51713 | n.m.
217 | A14068006 | Baker Sta Ballistic/Wall Elect | 0 | 11425.1 | 35818.07 | 966.45 | 48209.62 | n.m.
218 | A15702006 | KYPCo BAT HCP | 0 | 12867.57 | 11243.68 |  | 24111.25 | n.m.
219 | A15702007 | Beaver Creek- Repl Cap Bk AACC | 0 | -4441.93 | 6305.02 | -598.17 | 1264.92 | n.m.
220 | A15702029 | Leslie Station NIP | -3955886.484 | 3411139.67 | 314084.03 | 298714.71 | 4023938.41 | -101.7%
221 | A15702030 | Morehead: Replace CB B | 0 | -12750.44 |  | -1784.5 | -14534.94 | n.m.
222 | A15702032 | Hazard-Bonnyman Str. Replace | 0 | 1879.43 |  | 142.34 | 2021.77 | n.m.
223 | A15702035 | Hazard - Fleming Str. Replace | 0 | 5055.56 |  | 382.87 | 5438.43 | n.m.
224 | A15702036 | Daisy-Clover Fork Str. Replace | 0 | 2236.72 |  | 169.4 | 2406.12 | n.m.
225 | A15702041 | Hazard CB/XF Replacements | 266174.768 | 4338882.7 | 345349.96 | 423014.76 | 5107247.42 | 1919%
226 | A15702053 | Beaver Creek-Betsy Lane Remedi | 0 |  | -2509.43 |  | -2509.43 | n.m.
227 | A15702054 | Stone TF Failre Rplcment | 0 | -202143.99 |  | -17327.53 | -219471.52 | n.m.
228 | A15710034 | Coalton-Leon Fiber TelModFib | 0 | -3682.26 |  | -357.56 | -4039.82 | n.m.
229 | A15710071 | Morehead Station TTMP | 0 | 445.23 | 1372.56 | 36.16 | 1853.95 | n.m.
230 | A18730001 | Hazard-Bonnyman Str Replce ROW | 0 | 439.55 |  |  | 439.55 | n.m.
231 | A18730004 | Hazard-Fleming Str. Replc ROW | 0 | 474.54 |  |  | 474.54 | n.m.
232 | A18730005 | Daisy - Clover Fork ROW | 0 | 420.81 |  |  | 420.81 | n.m.
233 | A18730013 | Baker - Don Marquis STR 162-26 | 0 | 10119.25 |  |  | 10119.25 | n.m.
234 | A19750108 | Dewey - Inez Slide Failure | 0 | 283.2 |  | 28.57 | 311.77 | n.m.
235 | A19750113 | Henry Clay-Elkhorn C. Sl Fail | 0 | 1105.5 |  | 160.53 | 1266.03 | n.m.
236 | A19750114 | Breaks Rtg. Wall Fail - CXLD | 0 | -963.4 |  |  | -963.4 | n.m.
237 | A19750118 | Prestonsburg-Middle Ck Slide F | 0 | -105182.49 | 1.48 | 6957.93 | -98223.08 | n.m.
238 | A20020001 | Leon-Morehead69kVRehbLine | -389747.554 | 538299.33 | 11075.12 | 148763.49 | 698137.94 | -179.1%
239 | A20020002 | Leon-Morehead69kVRehab ROW | -25114.766 | 5847.07 | 1368.98 |  | 7216.05 | -28.73%
240 | A20045015 | Prestonsburg - Thelma 46kV NA | 0 | 1707.54 | 2085.79 | 171.77 | 3965.1 | n.m.
241 | A20045023 | Betsy Layne - S Pikeville NIP | 0 | 230.77 | 428.7 | 17.48 | 676.95 | n.m.
242 | A20045046 | Allen - Prestonsburg NIP | 0 | 264.97 | 492.22 | 20.06 | 777.25 | n.m.
243 | A20045063 | Hatfield Station Work | 459996.721 | 294249.95 | 28434.8 | 20162.75 | 342847.5 | 74.53%
244 | A20045085 | Leon (KP) NIP | 0 | 32.58 | 60.51 | 2.47 | 95.56 | n.m.
245 | A20077006 | Bonnyman Sta TTMP | -13030.697 | 47.85 | 88.89 | 3.62 | 140.36 | -1.077%
246 | A20077009 | Hays Branch Sta TTMP | -2103.632 | 43.3 | 80.45 | 3.28 | 127.03 | -6.039%
247 | A20077012 | Hazard Sta TTMP | -2103.632 | 44.72 | 83.07 | 3.38 | 131.17 | -6.235%
248 | A20077026 | Bonnyman-Jackson FC TelMod Fib | 0 | 3737.29 | 641.72 | 535.4 | 4914.41 | n.m.
249 | A20077027 | Haddix SS FCE TelMod Fib | 0 | 1393.11 | 141.23 | 399.8 | 1934.14 | n.m.
250 | A20077028 | Engle SS FCE ModTel Fib | 0 | 1358.41 | 171.88 | 1226.85 | 2757.14 | n.m.
251 | A20077029 | Bonnyman-Hazard FC ModTel Fib | 0 | 5594.73 | 872.66 | -2810.25 | 3657.14 | n.m.
252 | A20077030 | Bulan SS FCE TelMod Fib | 0 | 2282.06 | 305.06 | -1179.04 | 1408.08 | n.m.
253 | A20077031 | Whitesburg SS FCE TelMod Fib | 0 | 3776.64 | 519.75 | -901.24 | 3395.15 | n.m.
254 | A20077032 | Mayking SS FCE TelMod Fib | 0 | 160.53 | 6.33 | -1.22 | 165.64 | n.m.
255 | A20077033 | Collier SS FCE TelMod Fib | 0 | 2340.1 | 349.16 | 278.1 | 2967.36 | n.m.
256 | A20077034 | Jenkins-South Pikesville FC | 0 | 21723.09 | 2188.01 | -3791.59 | 20119.51 | n.m.
257 | A20077035 | CANCEL-Jackhorn Sta TTMP | 0 | 3918.46 | 520.19 | 555 | 4993.65 | n.m.
258 | A20705028 | Sprigg-Barrenshe 69kV Pre Eng | 0 | 327.52 |  | 24.81 | 352.33 | n.m.
259 | A20705029 | Barrenshe-Coleman Pre Eng | 0 |  |  | 838.42 | 838.42 | n.m.
260 | A20705035 | Middle Creek-Falcon 46kV Remvl | 0 | 366.62 |  | 47.61 | 414.23 | n.m.
261 | A20705036 | Middle Creek-Prestonsburg Rebu | 0 | 22159.64 | 1541.59 | 3075.61 | 26776.84 | n.m.
262 | A20705037 | Big Sandy - Thelma Pre Eng | 0 | 354.45 | 658.46 | 26.84 | 1039.75 | n.m.
263 | A20705052 | Coleman - Stone 69kV Pre Eng | 0 | 410.27 | 762.16 | 31.07 | 1203.5 | n.m.
264 | A20705057 | Big Sandy Station Pre Eng | 0 | 253.31 | 470.57 | 19.19 | 743.07 | n.m.
265 | A20705067 | McInness SW Needs Assessment | 0 | 209.2 | 299.16 | 22.18 | 530.54 | n.m.
266 | A20705077 | JohnsC - LeslieN1 69 Needs Asm | 0 | 151.3 | 281.08 | 11.46 | 443.84 | n.m.
267 | A20705078 | LeslieNo1-Hatfield69 NeedsAsm | 0 | 149.72 | 278.11 | 11.34 | 439.17 | n.m.
268 | A20705079 | McInnessMet69kV Needs Asm | 0 | 18.5 | 34.37 | 1.4 | 54.27 | n.m.
269 | A20705080 | Sidney 69kV Loop Needs Asm | 0 | 13.37 | 24.82 | 1.02 | 39.21 | n.m.
270 | A20705081 | Bevins 69kV Tap Needs Asm | 0 | 13.37 | 24.82 | 1.02 | 39.21 | n.m.
271 | A20705082 | Bellefonte Station supplmental | -34693.94 | 105148.95 | 8184.11 | 11720.6 | 125053.66 | -360.4%
272 | A20705083 | Bellefonte 34.5kV St Needs Asm | 260.536 | 323.34 | 600.68 | 24.48 | 948.5 | 364.1%
273 | A21071001 | BigSandy-Broadford KP 765 S&I | 0 | 2577 | 757.03 | 205.23 | 3539.26 | n.m.
274 | A21071002 | BigSandy-Brd KP 765 S&I ROW | 0 | 1344.45 |  |  | 1344.45 | n.m.
275 | A21071003 | Baker-DonMarq KP 765 S&I | 0 | 19452.28 | 1525.07 | 1906.04 | 22883.39 | n.m.
276 | A21071004 | Baker-DonMarq KP 765 S&I ROW | 0 | 2804.65 |  |  | 2804.65 | n.m.
277 | A21222008 | CANCEL-DO NOT USE | -1465.598 | 174.35 | 121.7 | 13.21 | 309.26 | -21.1%
278 | A21222017 | Greenup TS TTMP | 0 |  | 35.16 |  | 35.16 | n.m.
279 | A21505001 | Jackson - Helechawa 69kV NIP | 0 | 1521.77 | 2826.98 | 115.24 | 4463.99 | n.m.
280 | A21505003 | Hazard - Jackson 69kV Line NIP | 0 | 353.16 | 656.07 | 26.75 | 1035.98 | n.m.
281 | A21505004 | Morehead - Index 69kV Line NIP | 0 | -426.72 | 3089.87 | 125.97 | 2789.12 | n.m.
282 | A21505005 | Baker 765kV/345kV Yard NIP | 0 | 119.99 | 222.91 | 9.09 | 351.99 | n.m.
283 | A21505007 | Jackson - Helechawa 69kV NIP | 0 | 306.09 | 568.62 | 23.19 | 897.9 | n.m.
284 | A21505008 | Index - Helechawa 69kV NIP | 0 | 843.09 | 1566.2 | 63.85 | 2473.14 | n.m.
285 | A21505011 | CANCEL: Leslie Station NIP | 0 | 677.33 | 954.99 | 54.6 | 1686.92 | n.m.
286 | A21750001 | McKinney - Allen Str51 Failure | 0 | 166.32 |  | 15.14 | 181.46 | n.m.
287 | A21750002 | Bonnyman-Softshell Failure | 0 | 1086368.16 | 10704.74 | 146737.98 | 1243810.88 | n.m.
288 | A21750004 | Hazard-Pinevll 161kV Fire Fail | 0 | 3424.14 |  | 301.99 | 3726.13 | n.m.
289 | A21750006 | Big Sandy RE for Failure | 63323.332 | 29381.24 |  | 8229.13 | 37610.37 | 59.39%
290 | A21750007 | Hays Branch-Morgan Fork Slide | -119732.254 | 752471.51 | 17304.19 | 60186.92 | 829962.62 | -693.2%
291 | A21750008 | Sprigg-Beaver Crk Slide Fail | 139968.122 | 7581.57 | 6570.03 | 973.17 | 15124.77 | 10.81%
292 | A21750010 | HysBrnch-Morgan Frk Slide Fail | 116577.47 | 19262.67 | 6363.45 | 1677.9 | 27304.02 | 23.42%
293 | A21750012 | Hazard - Bonnyman 69kV Failure | 0 | 2426.45 |  | 288.28 | 2714.73 | n.m.
294 | A21750013 | Morehead - Index 69kV Failure | 0 | -730.49 |  | -70.93 | -801.42 | n.m.
295 | A21750015 | Hazard-Pineville 161kV Failure | 0 | 1395776.47 | 1366.67 | 94787.04 | 1491930.18 | n.m.
296 | A24033001 | Sprigg-Beaver Creek 115 T-Line | 0 | 5499.67 |  | 56.4 | 5556.07 | n.m.
297 | A24033002 | Sprigg-Beaver Creek 115 T-ROW | 0 | 647.98 |  | 73.14 | 721.12 | n.m.
298 | A24112005 | CANCEL-DO NOT USE | 13289.836 | 34.98 | 24.41 | 2.65 | 62.04 | 0.4668%
299 | A24112009 | CANCEL-DO NOT USE | 13289.836 | 38.96 | 27.2 | 2.95 | 69.11 | 0.52%
300 | A25101004 | CANCEL-DO NOT USE | 0 | 1991.5 | 124.34 | 281.33 | 2397.17 | n.m.
301 | A25101007 | CANCEL-DO NOT USE | 0 | 14.69 | 27.29 | 1.12 | 43.1 | n.m.
302 | A25101008 | CANCEL-DO NOT USE | 0 | 28.19 | 52.38 | 2.13 | 82.7 | n.m.
303 | B180KYLRC | T/KY/Non-Specific Work - Line | 2116084.388 | 2923005.41 | 44785.17 | 333511.81 | 3301302.39 | 156%
304 | B180KYLRR | T/KY/Non-Specific Work - Line | 0 | 2743372.71 | 34862.06 | 295317.11 | 3073551.88 | n.m.
305 | B180KYRMB | Reimbursable-DOP-180 Kentucky | 0 | 283854.54 | 169.99 | 27805.2 | 311829.73 | n.m.
306 | B180KYSRR | T/KY/Non-Specific Work - Stati | -193467.096 | 484331.04 | 7638.8 | 47836.72 | 539806.56 | -279%
307 | B180KYTEC | Trans Telecom - KP-CO Reg | 0 | 23427.48 | 1780.16 |  | 25207.64 | n.m.
308 | B180KYTRE | T/KP/Transmission Region Tools | 0 | 449893.27 |  |  | 449893.27 | n.m.
309 | DP16K03C0 | Tygart Sta - T line work | -78653.797 | 393380.15 | 18447.83 | 64808.76 | 476636.74 | -606%
310 | DP16K03C1 | Tygart Sta - T line work | -65229.434 | 479590.73 | 2195.89 | 39110.12 | 520896.74 | -798.6%
311 | DP16K03T0 | Tygart Sta - T line ROW | 0 | 77.58 | 472.01 |  | 549.59 | n.m.
312 | DR19K05C0 | Hazard DA 2019 Engle Tap | -5299.768 | 449.53 | 438.7 | 40.77 | 929 | -17.53%
313 | ETN000180 | T Kp T Anda | 0 | 4718272.59 |  | -4653957.15 | 64315.44 | n.m.
314 | ETN102802 | Tr/Leas/Transmission Row Lease | 0 | 1500 |  |  | 1500 | n.m.
315 | IT180BILL | Corp Prgrm Billing-KYPCO Trans | 0 | 261338.92 | 48153.92 |  | 309492.84 | n.m.
316 | IT180CCIC | Cloud Computing Imp Cost-KyP T | 0 | 136000.89 |  |  | 136000.89 | n.m.
317 | ITCB18000 | KENTUCKY POWER - TRANSM | -8034.713 | 32941.61 | -5662.13 |  | 27279.48 | -339.5%
318 | ITPCLC180 | PC Lifecycle CI - 180 | 1031.013 | 3503.66 |  |  | 3503.66 | 339.8%
319 | KEPCS2101 | KPCo Storm - Transmission | 872122.038 | 229190.15 |  | 32700.41 | 261890.56 | 30.03%
320 | KEPCS2201 | KPCo Storm - Transmission | 0 | -1013.4 |  | 177.84 | -835.56 | n.m.
321 | KEPCS2202 | KPCo Storm - Transmission | 0 | 113236.81 | 6817.86 | 16560.53 | 136615.2 | n.m.
322 | KEPCS2301 | KPCo Storm - Transmission | 0 | 7206.69 |  | 1838.69 | 9045.38 | n.m.
323 | KEPCS2302 | KPCo Storm - Transmission | 0 |  | -102.34 |  | -102.34 | n.m.
324 | KEPCS2401 | KPCo Storm - Transmission | 0 | 140999.19 | 16.87 | 8654.23 | 149670.29 | n.m.
325 | KEPCS2402 | KPCo Storm - Transmission | 0 | 672482.88 | 367.82 | 53410.33 | 726261.03 | n.m.
326 | P10115014 | Stone Change to KPCo | 0 | 0 |  | 46169.81 | 46169.81 | n.m.
327 | P10115015 | Inez Change to KPCo | 0 | -8877.45 |  | -1021.76 | -9899.21 | n.m.
328 | P11063002 | TKYHazard Station Improvemen | -818.874 | 275591.51 |  | 32472.65 | 308064.16 | -37620%
329 | P11161010 | B.Layne - Allen 46 kV KPCo | 0 | 0 | 0 | -13886.53 | -13886.53 | n.m.
330 | P11161023 | Stanville Ext TLINE KPCo | 0 |  | -3391.4 |  | -3391.4 | n.m.
331 | P13064002 | T/KP/Hazard Station / OPCO | 0 | 1105594.14 |  | 85111.96 | 1190706.1 | n.m.
332 | P13064003 | T/KP/Wooton Station - Station | 0 | 23212.61 |  | 2291.31 | 25503.92 | n.m.
333 | P13064021 | T/KP/Hazard - Jackson 69kV Lin | 0 | 243.71 | 452.76 | 18.45 | 714.92 | n.m.
334 | P13064025 | Hazard - Wooton ROW KPCo | 0 | 9936.68 |  |  | 9936.68 | n.m.
335 | P13064029 | Hazard-Wooton Change to KPCo | 0 | 53372.31 | 2902.35 | 6468.8 | 62743.46 | n.m.
336 | P13064030 | Hazard Station Change to KPCo | 0 | 336374.87 | 1197.82 | 23892.23 | 361464.92 | n.m.
337 | P13064031 | Hazard 161/138 Spare KPCo | 0 | -4912.22 | 7.46 | -281.04 | -5185.8 | n.m.
338 | P14030002 | Stinnett Loop Install OPGW | 71593.642 | 69857.04 | 3756.07 | 6974.7 | 80587.81 | 112.6%
339 | P14030008 | T/KP/Leslie Station Work | -97592.737 | 351744.46 | 35112.53 | 32175.09 | 419032.08 | -429.4%
340 | P14030010 | Leslie Loop ROW KPCo | 3505.614 | 117290.88 |  |  | 117290.88 | 3346%
341 | P14030011 | Wooton-Leslie ROW KPCo | -131791.02 | 621191.16 |  |  | 621191.16 | -471.3%
342 | P14030013 | Wooton Relaying Work & Telecom | 56627.763 | 593804.61 | 37747.08 | 48803.92 | 680355.61 | 1201%
343 | P14030015 | Lesile - Stinnett Removal | 0 | 2.96 | 8.16 | 0.22 | 11.34 | n.m.
344 | P14030016 | Leslie - Stinnett ROW (KPCo) | 1709.973 | 171473.59 | 22095.99 |  | 193569.58 | 11320%
345 | P14030101 | Leslie - Clover Fork Line Work | 57397.118 | 24053.09 | 1021.31 | 1916.49 | 26990.89 | 47.02%
346 | P14030102 | Leslie - Wooton TL to KPCo | 1125281.489 | 4084767.78 | 118593.81 | 303356.02 | 4506717.61 | 400.5%
347 | P14030103 | Leslie - Stinnett TL to KPCo | 668572.841 | 1221573.48 | 68706.66 | 102010.07 | 1392290.21 | 208.2%
348 | P14030104 | Leslie Ext Install to KPCo | -542477.836 | 763356.38 | 16557.95 | 57192.86 | 837107.19 | -154.3%
349 | P14030105 | Wooton Transition Fiber | 10987.398 | 3645.11 | 51.76 | 306.93 | 4003.8 | 36.44%
350 | P14030106 | Leslie Transition Fiber | 10333.654 | 1567.64 | 52.47 | 105.59 | 1725.7 | 16.7%
351 | P16116003 | Stinnett - Pineville ROW KPCo | -5720.536 | 635.99 |  |  | 635.99 | -11.12%
352 | P16116005 | Stinnett -Pineville T-line | 0 | 5005.09 | 9297.92 | 379.04 | 14682.05 | n.m.
353 | P17076001 | Kenwood Extension TLINE | 0 | 3041.27 |  | 180.02 | 3221.29 | n.m.
354 | P17076005 | Prestonsburg - Thelma 69kV | 0 | 463.57 |  | 36.86 | 500.43 | n.m.
355 | P17076006 | Kenwood Extension ROW | 0 | 16284.33 |  | 1848.13 | 18132.46 | n.m.
356 | P17076008 | Kenwood Transition Fiber | 0 | 835.43 | 7.25 | 20.11 | 862.79 | n.m.
357 | P17076009 | Kenwood Station Fiber Ext | 0 | 1013.55 |  | 20.51 | 1034.06 | n.m.
358 | P17076010 | Van Lear - Kenwood Str Replace | 0 | 14.71 |  | 1.12 | 15.83 | n.m.
359 | P17083001 | Garrett-Soft Shell 138kV TLINE | -2521188.675 | 6520504.46 | 233658.44 | 47104.35 | 6801267.25 | -269.8%
360 | P17083002 | Garrett - Soft Shell 138kV ROW | -510391.205 | 1413565.26 | 82818.15 |  | 1496383.41 | -293.2%
361 | P17083003 | Garrett Switch (Removal) | 0.069 | 1400.24 | 2820.98 | 131.87 | 4353.09 | 6308826%
362 | P17083005 | Hays Branch S.S | 86342.152 | 129899.34 | 8882.01 | 11659.23 | 150440.58 | 174.2%
363 | P17083006 | Garrett - Eastern 138 TLN | 285748.91 | 1993597.54 | 62533.81 | 178864.05 | 2234995.4 | 782.2%
364 | P17083007 | Garrett - Eastern 138 ROW | 221062.384 | 105164.62 | 14359.01 |  | 119523.63 | 54.07%
365 | P17083008 | Hays Br. - Morgan Frk. 138 TLN | 744303.212 | 60198.98 | 6809.29 | 5105.43 | 72113.7 | 9.689%
366 | P17083009 | Hays Br. Morgan FrkROW | 0 | 231.04 |  |  | 231.04 | n.m.
367 | P17083024 | Beaver Creek Station Work | 0 | 452.2 | 296.37 | 47.42 | 795.99 | n.m.
368 | P17083031 | Eastern-Hays Branch SS TLINE | 2265205.963 | 2362525.53 | 56040.56 | 153217.08 | 2571783.17 | 113.5%
369 | P17083032 | Eastern - Hays Branch SS ROW | 646322.839 | -3275.12 |  |  | -3275.12 | -0.5067%
370 | P17083034 | Morgan Fork Remote End | 814327.499 | 207775.98 | 8818.26 | 18731.26 | 235325.5 | 28.9%
371 | P17083037 | Eastern Station Land Purchase | 3639.04 | 12477.64 | 19183.12 |  | 31660.76 | 870%
372 | P17083038 | Snag Fork SS | 38944.494 | 380986.7 | 38916.68 | 44341.15 | 464244.53 | 1192%
373 | P17083041 | Eastern Station | 525322.884 | 1159143.56 | 83907.02 | 119979.57 | 1363030.15 | 259.5%
374 | P17083042 | Garrett - Eastern TFC | -12210.17 | 428.1 | 7.14 | 27.22 | 462.46 | -3.787%
375 | P17083043 | Eastern TFC | 47290.583 | 1872.16 | 25.07 | 77.38 | 1974.61 | 4.175%
376 | P17083044 | Soft Shell-Garrett TFC | 0 | 2006.4 | 27.08 | 85.05 | 2118.53 | n.m.
377 | P17084007 | Myra 138kV Extension TLINE | 0 | 66100 | 30425.62 | -27055.94 | 69469.68 | n.m.
378 | P17084008 | Myra 138kV Extension ROW | -17424.144 | 37391.85 |  |  | 37391.85 | -214.6%
379 | P17084017 | Beaver Creek - Fremont Cut in | 0 | 133.07 | 247.21 | 10.08 | 390.36 | n.m.
380 | P17084018 | Beaver Creek - Elwood Retire | 0 | 124.22 | 230.77 | 9.4 | 364.39 | n.m.
381 | P17084019 | Elwood - Cedar Cr. Reconfig. | 0 | 348.2 | 646.86 | 26.37 | 1021.43 | n.m.
382 | P17084020 | Elwood - Henry Cl. Recon. @ EL | 0 | 97.7 | 181.49 | 7.4 | 286.59 | n.m.
383 | P17225001 | Moore Hollow 138kV Station | 0 | -130787.26 | 325.52 | -12628.51 | -143090.25 | n.m.
384 | P17225003 | Moore Hollow 138kV Extension | 0 | 59846.9 | -53235.24 | -58465.68 | -51854.02 | n.m.
385 | P17225013 | Ramey 138 kV Extension TLINE | 0 | 2005.58 | -5020.01 | -2264.81 | -5279.24 | n.m.
386 | P17225014 | Ramey 138 kV Extension ROW | 0 | 1262.45 |  |  | 1262.45 | n.m.
387 | P17225015 | East Park - Princess 138kV TL | 0 | 2638.78 |  | -3704.03 | -1065.25 | n.m.
388 | P17225017 | Bellefonte - Coalton 138 kV TL | 0 | 1114.03 |  | -1185.13 | -71.1 | n.m.
389 | P17225025 | Moore Hollow Metering | 0 | -1920.54 |  | -278.31 | -2198.85 | n.m.
390 | P18025005 | Kewanee 138 Ext TLINE | -376130.377 | 2409764.45 | 204664.71 | 226910.89 | 2841340.05 | -755.4%
391 | P18025006 | Kewanee 138 Ext ROW | -83596.575 | 68879.69 | 32115.16 | 5649.75 | 106644.6 | -127.6%
392 | P18025007 | Cedar Creek Remote End | -375689.722 | 21976.31 | 6552.55 | 1990.42 | 30519.28 | -8.124%
393 | P18025008 | Beaver Creek Remote End Work | 1052594.201 | 11378.29 | 2768.78 | 1252.6 | 15399.67 | 1.463%
394 | P18025009 | Cedar Creek Fiber Extension | -3260.242 | 20915.85 | 4740.96 | 2169.85 | 27826.66 | -853.5%
395 | P18025010 | Kewanee Fiber Termination | -1313.719 | 20425.66 | 3191.05 | 2380.66 | 25997.37 | -1979%
396 | P18025012 | Cedar Creek - Elwood TLINE Wor | -3722.433 | 56702.36 | 4173.36 | 5948.78 | 66824.5 | -1795%
397 | P18025013 | Sprigg - Beaver Cr. TLINE Work | -62880.725 | 3071.8 |  | 394.49 | 3466.29 | -5.512%
398 | P18025014 | S.Pike - Dorton Fiber Cable | -12012.553 | 25246.61 | 27823.95 | 10317.07 | 63387.63 | -527.7%
399 | P18221002 | Dorton - Fleming 138kV | 1011432.259 | 565508.4 | 3882.6 | 58508.43 | 627899.43 | 62.08%
400 | P18221003 | Hazard - Fleming 69kV | 1180344.91 | 497387.11 | 4466.99 | 30293.63 | 532147.73 | 45.08%
401 | P18221004 | Fleming - Fremont 69kV | -132419.834 | 637719.73 | 3088.58 | 56739.61 | 697547.92 | -526.8%
402 | P18221005 | Beaver Creek - Fleming 69kV | -82637.909 | 722943.94 | 5068.07 | 74416.2 | 802428.21 | -971%
403 | P18221007 | Hazard - Fleming 69kV ROW | -1046.259 | 2921.89 | 1257.98 | 199.99 | 4379.86 | -418.6%
404 | P18221008 | Fleming - Fremont 69kV ROW | -1752.089 | 1625.92 | 1366.38 | 225.48 | 3217.78 | -183.7%
405 | P18221010 | Dorton Remote End | 696664.202 | 12409.35 | 396.6 | 1389.21 | 14195.16 | 2.038%
406 | P18221013 | Beaver Creek Remote End | -81066.392 | 5643.01 |  | 7611.58 | 13254.59 | -16.35%
407 | P18221014 | Fleming (Jackhorn) 138KV ADSS | -37678.749 | 115715.55 | 3556.59 | 11530.68 | 130802.82 | -347.2%
408 | P18221017 | Jackhorn Land Purchase | -30977.501 | 10011.1 | 7014.17 |  | 17025.27 | -54.96%
409 | P18221019 | Jackhorn Station T Work | -252163.977 | 298547.81 | 69593.94 | 26822.83 | 394964.58 | -156.6%
410 | P18221020 | Jackhorn Station D Work | -142745.576 | 107097.25 | 28740.91 | 6359.21 | 142197.37 | -99.62%
411 | P18221021 | Jackhorn 69kV Ring Bus | 489510.054 | 448527.41 | 62293.55 | 48720.09 | 559541.05 | 114.3%
412 | P19036003 | Osborne Extension TLINE | 1631403.531 | 3161831.76 | 72040.31 | 272760.11 | 3506632.18 | 214.9%
413 | P19036004 | Osborne Extension ROW | -22.586 | 3976.06 |  |  | 3976.06 | -17604%
414 | P19036006 | Beaver Creek - Fleming Cut in | 444764.637 | 568263.06 | 4956.43 | 967.65 | 574187.14 | 129.1%
415 | P19036007 | Beaver Creek Remote End | -952.194 | 4902.52 | 1009.13 | 295.07 | 6206.72 | -651.8%
416 | P19036009 | Osborne Fiber Extension | 0 | 46233.72 | 695.67 | 4298.45 | 51227.84 | n.m.
417 | P19037004 | Henry Clay - Dorton Reconfig. | 0 | 86585.5 | 4276.3 | 7642.73 | 98504.53 | n.m.
418 | P19037005 | Henry Clay - Breaks Reconfi | 1342.24 | 78159.4 | 3777.07 | 4608.93 | 86545.4 | 6448%
419 | P19037006 | Henry Clay Extension | 0 | 10242.22 | 909.23 | 606.12 | 11757.57 | n.m.
420 | P19037011 | Henry Clay-Dorton Reconfig ROW | -40329.961 | 8738.58 |  |  | 8738.58 | -21.67%
421 | P19037012 | Henry Clay-Breaks Recon ROW | -23580.751 | 13203.08 |  |  | 13203.08 | -55.99%
422 | P19037013 | Dorton Station Work | 0 | 41285.71 | 3038.2 | 3774.15 | 48098.06 | n.m.
423 | P19037014 | Breaks Station Work | 0 | 33774.83 | 2319.55 | 3979.45 | 40073.83 | n.m.
424 | P19091004 | Middle Creek- Prestonsburg ROW | 0 | 0 |  |  | 0 | n.m.
425 | P19091011 | Middle Creek BESS | -330840.264 | -535.93 |  | -61.69 | -597.62 | 0.1806%
426 | P19092007 | Allen -East Prestonsburg TLINE | -6968.329 | 37544.03 | 2572.55 | 3996.48 | 44113.06 | -633.1%
427 | P19092008 | Allen -East Prestonsburg ROW | -2714.377 | 589.62 | 187.85 |  | 777.47 | -28.64%
428 | P19092011 | McKinney -Allen Reconfigure | -98794.048 | 32755.57 | 3201.1 | 3253.36 | 39210.03 | -39.69%
429 | P19092012 | Betsy Layne - Allen Reconfigur | -12564.55 | 966.44 | 307.91 | 73.19 | 1347.54 | -10.72%
430 | P19092013 | Allen - Prestonsburg TLINE | 282490.728 | 100686.72 | 3038.94 |  | 103725.66 | 36.72%
431 | P19092017 | McKinney - Allen ROW | -6617.352 | 884.28 | 281.73 |  | 1166.01 | -17.62%
432 | P19092019 | Allen - Prestonsburg ROW | -5159.904 | 15525.08 | 509.56 |  | 16034.64 | -310.8%
433 | P19104010 | Bellefonte Ext (KY) Line work | 577803.953 | 150103.15 |  | 6097.94 | 156201.09 | 27.03%
434 | P19104012 | Bellefonte Ext (KY) ROW | 0 | 0 |  |  | 0 | n.m.
435 | P19104016 | Bellefonte TransFiber | -6887.214 | 4806.76 |  | 462.78 | 5269.54 | -76.51%
436 | P19215005 | Chadwick - Leach TLINE | 0 | 2795.25 | -11708.69 | 211.69 | -8701.75 | n.m.
437 | P19215014 | Leach Area Fiber | 0 |  | -5641.51 |  | -5641.51 | n.m.
438 | P19294011 | Inez Station | 0 | -8091.31 |  | -629.72 | -8721.03 | n.m.
439 | P19294012 | Inez XF Replace Baseline | 0 | 5913.46 |  | 720.06 | 6633.52 | n.m.
440 | P19305001 | Orinoco - Stone TLINE | 306660.864 | 436400.16 | 55448.75 | 31195.68 | 523044.59 | 170.6%
441 | P19305002 | Orinoco - Stone ROW | -80740.771 | 200362.39 | 18060.22 |  | 218422.61 | -270.5%
442 | P19305009 | Hatfield Station Work | -30995.424 | 117108.18 | 14420.21 | 7559.18 | 139087.57 | -448.7%
443 | P19305010 | Stone Station Work | -128924.266 | 118011.8 | 20509.48 | 9742.32 | 148263.6 | -115%
444 | P19305016 | New Camp - Orinoco TLINE | -368233.194 | 244979.63 | 32436.71 | 25577.09 | 302993.43 | -82.28%
445 | P19305017 | New Camp - Orinoco ROW | -32.022 | 215031.37 | 19912.3 |  | 234943.67 | -733695%
446 | P19305018 | New Camp Tap TLINE | 25571.871 | 42767.93 | 2100.75 | 4678.86 | 49547.54 | 193.8%
447 | P19305019 | New Camp Tap ROW | -122.649 | 18978.28 | 1839.11 |  | 20817.39 | -16973%
448 | P19305021 | Belfry - Stone Trans Fiber | -36188.612 | 4.37 | 8.12 | 0.33 | 12.82 | -0.03543%
449 | P20035004 | Middle Creek-Prestonsburg ROW | -5550.651 | 808.84 |  |  | 808.84 | -14.57%
450 | P21027001 | Inez 138kV Station Work | -74994.951 | 84373.7 | 388.56 | 68642.24 | 153404.5 | -204.6%
451 | P21027002 | Inez IPP T-Line Work | 0 | 136697.5 | 766.88 | 39283.14 | 176747.52 | n.m.
452 | P21027003 | Inez IPP Metering | 0 | -69754.51 | 1209.29 | 5984.29 | -62560.93 | n.m.
453 | P21043001 | Thelma-Kenwood 46kV Line | 85245.646 | 96680.78 | 16643.48 | 12573 | 125897.26 | 147.7%
454 | P21043002 | Thelma-Kenwood 46kV ROW | -57205.263 | 11604.43 |  |  | 11604.43 | -20.29%
455 | P21043004 | Remote End Work at Thelma | 0 | 11510.74 | 1943.53 | 1325.22 | 14779.49 | n.m.
456 | P21043008 | Kenwood-Prestonsburg 46kV Line | 265368.579 | 19798.3 | 11953.94 | 5176.7 | 36928.94 | 13.92%
457 | P21043009 | Kenwood-Prestonsburg 46kV ROW | -28602.614 | 9170.66 |  |  | 9170.66 | -32.06%
458 | P21043015 | Thelma Station | 0 | 28830.59 | 1150.24 | 3941.42 | 33922.25 | n.m.
459 | P21205003 | Leslie No.1-Hatfield 69kV | -247787.408 | 68816.74 | 38.75 | 766.61 | 69622.1 | -28.1%
460 | P21605001 | Big Sandy Station Work | 0 | 35936.61 |  | 276.06 | 36212.67 | n.m.
461 | P21605002 | Dragon Fly Extension Line Work | 0 | -25201.65 | -1009.04 | 29.43 | -26181.26 | n.m.
462 | P21605003 | Dragon Fly ROW | 0 | 0 |  |  | 0 | n.m.
463 | P21605004 | Dragon Fly Metering | 0 | -6679.8 | -232.39 | 7.76 | -6904.43 | n.m.
464 | P21720001 | Bellefonte Station Baseline | -36242.448 | 101852.64 | 10377.97 | 10029.42 | 122260.03 | -337.3%
465 | P21720008 | Bellefonte - A.K. Steel 69kV | 0 | 6153.59 | 388.53 | 538.46 | 7080.58 | n.m.
466 | P21720011 | AshlAshland Relocate Str AB105 | 0 | 5930.62 | 96.46 | 459.56 | 6486.64 | n.m.
467 | P21753001 | Dewey Station Baseline | -16073.078 | 46821.29 | 4644.3 | 4664.77 | 56130.36 | -349.2%
468 | P21753002 | Dewey Station Supplemental | 836067.762 | 43199.11 | 3136.95 | 4545.41 | 50881.47 | 6.086%
469 | P21753004 | Thelma Remote End Work | -8040.404 | 17036.79 | 1234.14 | 1339.54 | 19610.47 | -243.9%
470 | P22005002 | 47th Street Line Work | -42036.947 | 20442.18 | 1407.15 | 3147.08 | 24996.41 | -59.46%
471 | P22012033 | Peter Creek Land Purchase | 0 | 925.52 |  |  | 925.52 | n.m.
472 | P22012047 | Peter Creek-Wharncliffe KY ROW | 0 | 141.45 |  |  | 141.45 | n.m.
473 | P22012049 | Peter Creek-Wharncliffe (KY) | 0 | 1228.71 | 340.86 | 85.27 | 1654.84 | n.m.
474 | P22012051 | Peter Creek-Coleman ROW | 0 | 94.59 |  |  | 94.59 | n.m.
475 | P22012052 | Peter Creek-Coleman | 0 | 913.12 | 2209.47 | 78.93 | 3201.52 | n.m.
476 | P22113001 | CANCEL Gund Switch KY T - BPID | 1042898.718 | -28446 | -750.08 |  | -29196.08 | -2.8%
477 | P22113004 | CANCEL Gund Metering Tap ROW | -189516.594 | -20107.75 |  |  | -20107.75 | 10.61%
478 | P22113005 | CANCEL Leslie Hatfield Line | 0 | -16750.73 | -17.16 | -1913.58 | -18681.47 | n.m.
479 | P22113006 | Bevins Metering KY-T | 0 | 3107.52 | 11.85 | 372.53 | 3491.9 | n.m.
480 | P22745001 | McCoy-Elkhorn Tap Station Work | 0 | 87260.16 | 3955.14 | 8651.74 | 99867.04 | n.m.
481 | P22745003 | McCoy-Elkhorn Hard Tap | 0 | 81185.63 | 2930.98 | 7189.07 | 91305.68 | n.m.
482 | P22745004 | McCoy-Elkhorn Tap ROW | 0 | 26900 |  |  | 26900 | n.m.
483 | P22745005 | Johns Creek - Second Fork | 303496.61 | 100419.11 | 3622.64 | 10342.47 | 114384.22 | 37.69%
484 | P23042017 | Pigeon Creek-Sprigg KY | 0 | 1217.66 | 69.34 | 139.18 | 1426.18 | n.m.
485 | P23325001 | Leach Substation Work | 0 | 118050.82 | 3107.38 | 10249.17 | 131407.37 | n.m.
486 | TTKY180NN | Forestry KP T non-NERC | -99900.32 | 1208270.24 | 534.04 | 106524.55 | 1315328.83 | -1317%
487 | TTKY180NR | Forestry KY T NERC | -586.937 | 269534.47 | 242.91 | 18853.79 | 288631.17 | -49176%
488 | XHWCAP180 | HW CAP CI - 180 | 571812.21 | 155463.84 | 1342.08 |  | 156805.92 | 27.42%
489 | Other Budgeted Projects |  | 47494007.804 |  |  |  |  | Other
490 | Total GLBU 180 (Transmission) |  | 57742631.568 | 66017313.22 | 2696963.84 | -14516.63 | 68699760.43
491 | Total Kentucky Power CWIP Additions |  | 156058730.108 | 163422138.92 | 5458583.81 | -1648448.69 | 167232274.04
492
493 | X00000317 | For Property Acctg Use Only - GLBU 110 | Property Acctg | -79826328.91 | 0 |  | -79826328.91 | Property Acctg
494 | X00000288 | For Property Acctg Use Only - GLBU 117 | Property Acctg | -11438236.8 | 0 | 1947901.45 | -9490335.35 | Property Acctg
495 | X00000306 | For Property Acctg Use Only - GLBU 180 | Property Acctg | -54394338.75 | 0 |  | -54394338.75 | Property Acctg
496 | Total Kentucky Power Transfers to 101/106 |  |  | -145658904.46 | 0 | 1947901.45 | -143711003.01
497
498 | Total Kentucky Power CWIP Activity 12 Months Preceding the Historical Test Year June 2023 - May 2024 |  | 156058730.108 | 17763234.46 | 5458583.81 | 299452.76 | 23521271.03

## Lookups
|  |  | Year-ending May | Values
|  |  | 2024 | 2024 | 2025 | 2025
Prj | Project to Use for Budg | Est ISD, Prj to Use | Sum of Fore $ | Sum of Act $ | Sum of Fore $ | Sum of Act $ | Chk TY | Chk PY
000001585 | 000001585 O&M / Fuel Staff Project | (blank) | 1.4921e-13 | 0 | 0 | 0 | Other | Other
000001586 | 000001586 Capital Staff Project | (blank) | 0.005 | 0 | 0.012 | 0 | Other | Other
000005237 | 000005237 KyPCo-G Capital Software Dev | (blank) | 53733.945 | 593628.23 | 0 | 483424.81 | 117-000005237 | 117-000005237
000005706 | 000005706 Ds IM Mich-Anda | 1902-01-01 | 0 | 0 |  |  | Other | Other
000005707 | 000005707 Ds AP WVirg-Anda | 1902-01-01 | 0 | 0 | 0 | 0 | Other | Other
000005708 | 000005708 Ds SEP La-Anda | 1902-01-01 | 0 | 0 | 0 | 0 | Other | Other
000007652 | 000007652 OOC Capital Projects | 2028-12-31 | 8585.13 | 0 | 9958.401 | 0 | Other | Other
000012736 | 000012736 ISO Certification | (blank) | 0 | 0 | 0 | 0 | Other | Other
000014351 | 000014351 Budget Earnings Adjustments | (blank) | 0 | 0 | 0 | 0 | Other | Other
000018412 | 000018412 FEL IT Projects | (blank) | 5266.622 | 0 | 5675.422 | 0 | Other | Other
MLLPC0ELG | MLLPC0ELG ML PCC U0 ELG/CCR Comply - 117 | 2024-12-31 | 4744329.453 | 0 | 0 | 0 | 117-MLLPC0ELG | 117-MLLPC0ELG | Updated Project ID | 000020310 ML U0 ELG / CCR Compliance
000022309 | 000022309 ML U2 ESP Upgrades | 2022-05-27 | 0 | 0 |  |  | Other | Other
000022392 | 000022392 ML LANDFILL EXPANSION - PH 3 | 2019-12-31 |  |  | 0 | 0 | Other | Other
000025231 | 000025231 2018 Gen Plt Cap Blkt - KYPC-G | (blank) | 0 | 5907.45 | 0 | 7349.91 | 117-000025231 | 117-000025231
MLLHAULRD | MLLHAULRD Mitchell Haul Road Relocate | 2023-12-31 | -545872.715 | 0 | 513395.505 | 0 | 117-MLLHAULRD | 117-MLLHAULRD | Updated Project ID | 000025624 Mitchell Haul Road Relocate
000026753 | 000026753 189MW PSO Solar Pixley | 2025-04-30 | 0 | 0 | 0 | 0 | Other | Other
000026765 | 000026765 598MW SWEPCo Wagon Wheel | 2025-12-15 | 0 | 0 | 0 | 0 | Other | Other
000026956 | 000026956 135MW Wind Flat Ridge IV | 2025-05-30 | 0 | 0 | 0 | 0 | Other | Other
000026957 | 000026957 153MW Wind Flat Ridge V | 2025-07-30 | 0 | 0 | 0 | 0 | Other | Other
ACCTTAX | ACCTTAX Accounting and Tax BPO | (blank) | 0 | 0 | 0 | 0 | Other | Other
AEPLEADER | AEPLEADER AEP Leadership Devel Programs | (blank) |  |  | 0 | 0 | Other | Other
AESAVINGS | AESAVINGS AE Savings | (blank) | 0 | 0 |  |  | Other | Other
AP24IRCM1 | AP24IRCM1 WPCo Gen 24 IRC ML U2 CT Shell | 2025-12-31 |  |  | 0.005 | 0 | Other | Other
BDLABSPRD | BDLABSPRD Budget Labor Spread | (blank) | 0 | 0 |  |  | Other | Other
BLDCS | BLDCS Building Projects Cap Std | 2026-12-31 | 17769.939 | 0 | 19383.491 | 0 | Other | Other
BSPGENREW | BSPGENREW BS1 Gen Core Restack & Rewind | 2027-12-31 |  |  | 6952681.422 | 0 | Other | Other
BSPPB0002 | BSPPB0002 Boiler & Auxiliaries PPB<100k | (blank) | 27286.031 | 12265.83 | 308158.934 | 47574.89 | 117-BSPPB0002 | 117-BSPPB0002
BSPPB0003 | BSPPB0003 Boiler MU Water Supply PPB<100 | (blank) | 25580.642 | 0 | 304733.442 | 0 | Other | Other
BSPPB0007 | BSPPB0007 Condenser & Aux. PPB<100k | (blank) | 0 | 24036.03 | 0 | 138165.45 | 117-BSPPB0007 | 117-BSPPB0007
BSPPB0008 | BSPPB0008 Clg Water Facilities PPB<100k | (blank) | 276067.299 | 69184.39 | 0 | 35028.35 | 117-BSPPB0008 | 117-BSPPB0008
BSPPB0009 | BSPPB0009 Effluent WW Treating PPB<100k | (blank) | 0 | -261710.84 |  |  | Other | 117-BSPPB0009
BSPPB0011 | BSPPB0011 Generator & Support PPB<100k | (blank) |  |  | 0 | 67287.39 | 117-BSPPB0011 | Other
BSPPB0013 | BSPPB0013 Other Costs PPB<$100k | 2018-12-31 | 28637.422 | -1302602.41 | 832845.96 | 1158052.85 | 117-BSPPB0013 | 117-BSPPB0013
BSPPB0016 | BSPPB0016 Turb & Support Sys PPB<100k | (blank) | 0 | -24776.63 |  |  | Other | 117-BSPPB0016
BSPPBENEW | BSPPBENEW BSP PPB Envr. New | (blank) |  |  | 0 | 247589.97 | 117-BSPPBENEW | Other
BSPPBENVR | BSPPBENVR Other Environ Repl <100k | (blank) | 25243.096 | 0 | 37401.379 | 0 | Other | Other
BSPPBOUT1 | BSPPBOUT1 Unit 1PPB Outage<100k | (blank) | 423526.055 | 40287.57 | 956559.622 | 634689.19 | 117-BSPPBOUT1 | 117-BSPPBOUT1
BSPPBPOND | BSPPBPOND Install Reflective Balls | 2026-04-01 |  |  | 219464.851 | 0 | Other | Other
BSPPBRVSC | BSPPBRVSC River Screen - Upgrade | 2026-12-01 |  |  | 365422.777 | 0 | Other | Other
BSPPBS339 | BSPPBS339 REPLACE 15 BREAKERS "A" BUS | 2022-06-30 | 0 | 370710.46 |  |  | Other | 117-BSPPBS339
BSPPBS340 | BSPPBS340 REPLACE 15 BREAKERS "B" BUS | 2022-06-30 | 0 | 376901.55 |  |  | Other | 117-BSPPBS340
BSPPBS347 | BSPPBS347 REP U1 BFPT Rotor with Spare | 2018-12-21 |  |  | 183248.525 | 414957.95 | 117-BSPPBS347 | Other
BSPPBS358 | BSPPBS358 BS1 REPL BLR COMBUSTION COILS | 2029-12-31 | -7186.182 | 0 | 0 | 0 | Other | Other
BSPPBS359 | BSPPBS359 BS1 HEAT RATE INSTRUMENTATION | 2029-12-31 |  |  | 0 | 0 | Other | Other
BSPPBS365 | BSPPBS365 BSP UPGRADE U1 FREIGHT ELEVATO | 2024-12-31 | 0 | 0 | 146.278 | 0 | Other | Other
BSPPBS368 | BSPPBS368 Big1 Boiler Exit Gas Duct Repl | 2024-12-31 | 1530189.504 | 1030440.02 | 5810643.636 | 8135599.44 | 117-BSPPBS368 | 117-BSPPBS368
BSPPBS370 | BSPPBS370 Rep U1 BFPT Rotor with Spare | 2028-10-20 |  |  | 614835.375 | 0 | Other | Other
BSPPBS371 | BSPPBS371 REP BFP rotor with spare | 2024-10-25 |  |  | 245090.33 | 0 | Other | Other
BSPPBS372 | BSPPBS372 Rep Heater Bay Roof | 2026-12-18 |  |  | 77060.393 | 0 | Other | Other
BSPPBSKYC | BSPPBSKYC Stack Sky Climber Replacement | 2026-12-30 |  |  | 205494.38 | 0 | Other | Other
BSPPBWGRN | BSPPBWGRN Ovation Evergreen Upgrade | 2026-02-01 |  |  | 1148697.852 | 1278.32 | 117-BSPPBWGRN | Other
BUDOFFSET | BUDOFFSET Budget Reductions/Offsets | 2019-12-31 | 0 | 0 | 6602.85 | 0 | Other | Other
BUDTRKTBD | BUDTRKTBD Budget Adjustments | (blank) | 0 | 0 | 0 | 0 | Other | Other
CDNANDA | CDNANDA Corp Dev Anda | (blank) | 0 | 0 | 0 | 0 | Other | Other
CFOCAPPRJ | CFOCAPPRJ CFO CAPITAL PROJECTS | 2018-12-31 | 105620.148 | 0 | -149434.678 | 0 | Other | Other
CHNANDA | CHNANDA Chairman Anda | (blank) | 1.35e-13 | 0 | 0 | 0 | Other | Other
CORPR117G | CORPR117G Corporate Reserve - KYPCO Gen | 2018-12-31 | 0 | 0 | 0 | 0 | Other | Other
CRPTARGET | CRPTARGET CORP CALIBRATION PROJECT | (blank) | 0 | 0 | 0 | 0 | Other | Other
DIGITAHUB | DIGITAHUB Digital Hub Project | 2018-12-31 | -1102.846 | 0 |  |  | Other | Other
DISTARGET | DISTARGET Dist Budget Calibration | (blank) | 0 | 0 | 0 | 0 | Other | Other
ECNANDA | ECNANDA Telecommunications Anda | (blank) | 0 | 0 | 0 | 0 | Other | Other
EDN103172 | EDN103172 Ds Ap Virg-Anda | 1902-01-01 | 0 | 0 |  |  | Other | Other
EDN103175 | EDN103175 Ds Kp Anda | 1902-01-01 | 0 | 0 | 0 | 0 | Other | Other
EDN103177 | EDN103177 Ds Op Anda | 1902-01-01 | 0 | 0 |  |  | Other | Other
EDN103178 | EDN103178 Ds Pso Anda | 1902-01-01 | 0 | 0 | 0 | 0 | Other | Other
EDN103180 | EDN103180 Ds Im Ind-Anda | 1902-01-01 | 0 | 0 | 0 | 0 | Other | Other
EDNANDA | EDNANDA Distribution Anda Project | 1902-01-01 | -7.816e-14 | 0 | -3.6238e-13 | 0 | Other | Other
EON011324 | EON011324 Line Transformer/Op | 1902-01-01 | 647.696 | 0 | 58.101 | 0 | Other | Other
ETNANDA | ETNANDA Transmission Anda | 1902-01-01 | 0 | 0 | 0 | 0 | Other | Other
EVNCBA215 | EVNCBA215 Environmental Cap Blkt APCO | (blank) | 0 | 0 | 0 | 0 | Other | Other
EVNCBK117 | EVNCBK117 Environmental Cap Blkt KYPCO | (blank) | 0 | 0 | 0 | 0 | Other | Other
EVNCBW413 | EVNCBW413 Environmental Cap Blkt WPCO | (blank) | 0 | 0 | 0 | 0 | Other | Other
EVRCB | EVRCB Cap Blkt - Environmental Repl | (blank) | 0 | 0 | 0 | 0 | Other | Other
EVRCS | EVRCS Cap Stnd - Environmental Repl | (blank) |  |  | 0 | 0 | Other | Other
FANANDA | FANANDA Activity NOT assoc with a PROJ | (blank) | 0 | 0 | 0 | 0 | Other | Other
FHGCAPCUT | FHGCAPCUT FHG Capital Cuts | (blank) | -8067.154 | 0 | -29026.92 | 0 | Other | Other
FLTADJIRC | FLTADJIRC Fleet Adjustment IRC | (blank) | -0.002 | 0 | -0.002 | 0 | Other | Other
GLNANDA | GLNANDA General Ledger Expense | (blank) | -0.007 | 0 | -3.9311e-12 | 0 | Other | Other
GWSCB | GWSCB Cap Blkt - Prod Plant Blnkt | 2018-12-31 | 0 | 0 | 0 | 0 | Other | Other
GWSCBA215 | GWSCBA215 PPB for APCO - Budget Only | (blank) | 0 | 0 | 0 | 0 | Other | Other
GWSCBI132 | GWSCBI132 PPB I&M - Budget Only | (blank) |  |  | 0 | 0 | Other | Other
GWSCBK117 | GWSCBK117 PPB KPCO - Budget Only | (blank) | 0 | 0 | 0 | 0 | Other | Other
GWSCBU420 | GWSCBU420 PPB UNREG PPA 420 | (blank) |  |  | 0 | 0 | Other | Other
GWSCBW413 | GWSCBW413 PPB WPCO - Budget Only | (blank) | 0 | 0 | 0 | 0 | Other | Other
GWSCS | GWSCS Cap Stnd - Prod Plant Stnd | 2018-12-31 | 0 | 0 | 0 | 0 | Other | Other
INCCAPINV | INCCAPINV Incremental Capital Investment | 2024-12-31 | -1345871.205 | 0 | 1325056.392 | 0 | Other | Other
IT117CCIC | IT117CCIC Cloud Computing Imp Cost-KyP G | 2030-12-31 | 0 | 146093.5 | 0 | 106531.99 | 117-IT117CCIC | 117-IT117CCIC
ITCAPPROJ | ITCAPPROJ It Capital Projects | 2018-12-31 | -184418.621 | 0 | 87917.454 | 0 | Other | Other
ITCB10300 | ITCB10300 AEP Service Corp - Telecom | 2017-12-31 | -8568.124 | 0 |  |  | Other | Other
ITCB11700 | ITCB11700 KENTUCKY POWER - GEN | 2022-12-31 | 0 | 38173.03 | 5237.414 | 4676.65 | 117-ITCB11700 | 117-ITCB11700
ITCBLBRTY | ITCBLBRTY KENTUCKY POWER LIBERTY | 2022-12-31 | 0 | 11977.2 | 0 | 1241.46 | 117-ITCBLBRTY | 117-ITCBLBRTY
ITCHR0001 | ITCHR0001 IT Chairman Blanket | 2018-12-31 | 4352.293 | 0 | 4915.445 | 0 | Other | Other
ITCOP0001 | ITCOP0001 IT Commercial Ops Blanket | 2006-11-01 | 31686.538 | 0 | 34134.638 | 0 | Other | Other
ITCT10304 | ITCT10304 Fiber Asset Management Tool | 2025-05-15 | 3661.195 | 0 | 24019.696 | 0 | Other | Other
ITCUS1957 | ITCUS1957 Texas SET 5 | 2024-12-31 | 2263.864 | 0 | 1209.851 | 0 | Other | Other
ITDIS1952 | ITDIS1952 DIST Interconnect Standardize | 2026-02-27 | 1374.4 | 0 |  |  | Other | Other
ITDIS1987 | ITDIS1987 DIST Hosting Capacity Analysis | 2025-06-30 | 439.176 | 0 |  |  | Other | Other
ITDIS1988 | ITDIS1988 DER Data Repository | 2025-03-31 | 513.622 | 0 |  |  | Other | Other
ITDIS2004 | ITDIS2004 ESRI ELA Extension 2023-2024 | 2023-01-31 | 2.463 | 0 |  |  | Other | Other
ITGEN0004 | ITGEN0004 IT Generation Blanket | 2029-12-31 | 54606.514 | 0 | 59672.818 | 0 | Other | Other
ITGEN2000 | ITGEN2000 eSOMS Impl at Rest Fossil Hyd | 2024-12-31 | 32215.751 | 0 | 11867.46 | 0 | Other | Other
ITGEN2001 | ITGEN2001 Maximo WAM for Generation | 2024-04-30 | 6367.688 | 0 | 291.667 | 0 | Other | Other
ITPCLC103 | ITPCLC103 PC Lifecycle CI - 103 | 2025-12-31 | 1663.377 | 0 |  |  | Other | Other
ITPCLC117 | ITPCLC117 PC Lifecycle CI - 117 | 2025-12-31 | 11266.991 | 1531.77 | 12494.993 | 4542.91 | 117-ITPCLC117 | 117-ITPCLC117
ITPFP0002 | ITPFP0002 IT Pol Fin & Strat Pln Blanket | 2018-12-31 | 6093.203 | 0 | 11142.471 | 0 | Other | Other
ITPFP1742 | ITPFP1742 PeopleSoft Finance 9.2 Upgrade | 2022-05-01 | 215.813 | 0 |  |  | Other | Other
ITPFP1924 | ITPFP1924 ACCT PowerTax Utilization | 2023-05-31 | 1348.646 | 0 |  |  | Other | Other
ITPFP1978 | ITPFP1978 PowerPlan Module Upgrade | 2024-05-31 | 12070.402 | 0 | 6004.356 | 0 | Other | Other
ITPFP1986 | ITPFP1986 PeopleSoft 9.2 Rel 2 | 2023-12-31 | 0 | 0 |  |  | Other | Other
ITPFP2007 | ITPFP2007 UI Planner Mod Update | 2024-03-31 | 7833.456 | 0 | 4948.138 | 0 | Other | Other
ITPFP2089 | ITPFP2089 PeopleSoft Platform Update | 2025-10-10 |  |  | 62568.416 | 0 | Other | Other
ITSEC1436 | ITSEC1436 Security Blanket | 2018-12-31 | 56755.796 | 0 | -2918.179 | 0 | Other | Other
ITSEC1819 | ITSEC1819 Cyber-IronNet | 2025-12-31 | 2402.506 | 0 | 1719.712 | 0 | Other | Other
ITSEC1934 | ITSEC1934 Splunk | 2022-12-31 | 1022.313 | 0 |  |  | Other | Other
ITSEC1971 | ITSEC1971 Cyber - Hadoop | 2023-06-30 | 220.388 | 0 |  |  | Other | Other
ITSEC1972 | ITSEC1972 Cyber-Dashbrdng5newDomains | 2023-05-31 | 272.325 | 0 |  |  | Other | Other
ITSEC1974 | ITSEC1974 Cyber-DataPrivcyCompliance | 2023-01-31 | 249.395 | 0 | 131.172 | 0 | Other | Other
ITSEC2037 | ITSEC2037 Cyber-Tulsa IDS Upgrade | 2024-04-30 | 1957.083 | 0 | 74.209 | 0 | Other | Other
ITSEC2077 | ITSEC2077 Cybr-Trellix/McAfee SLA Ren 25 | 2028-10-31 |  |  | 9852.19 | 0 | Other | Other
ITSEC2079 | ITSEC2079 Content Management Upgrade | 2025-12-31 |  |  | 4195.891 | 0 | Other | Other
ITSEC2081 | ITSEC2081 MyAccess Solution Replacement | 2026-06-30 |  |  | 8226.931 | 0 | Other | Other
ITSEC2082 | ITSEC2082 Cyber-Full Packet Capture Soln | 2025-12-31 |  |  | 3888.315 | 0 | Other | Other
ITSEC2091 | ITSEC2091 Cyber Axonius Sec Asst Mgmt | 2025-10-31 |  |  | 6693.161 | 0 | Other | Other
ITSEC2106 | ITSEC2106 CyberArk Licensing | 2027-12-31 |  |  | 1648.033 | 0 | Other | Other
ITSEC2115 | ITSEC2115 CyberArk 2025 Expansion-Cpcty | 2025-12-31 |  |  | 1394.661 | 0 | Other | Other
ITSEC2125 | ITSEC2125 Cyber CIRC Logging Alerting | 2025-04-01 |  |  | 1290.147 | 0 | Other | Other
ITSSV0003 | ITSSV0003 IT Shared Services Blanket | (blank) | 468830.236 | 0 | 565170.884 | 0 | Other | Other
ITSSV1652 | ITSSV1652 IT SAS Centralized Server | 2022-12-30 | 297.391 | 0 |  |  | Other | Other
ITSSV1750 | ITSSV1750 IT INFR Windows 2012 | 2020-01-01 | 1100.752 | 0 |  |  | Other | Other
ITSSV1781 | ITSSV1781 IT Infrastructure Ent PKI Cert | 2023-12-31 | 1380.643 | 0 |  |  | Other | Other
ITSSV1830 | ITSSV1830 Enterprise Contract Admin | 2022-10-31 | 83.878 | 0 |  |  | Other | Other
ITSSV1834 | ITSSV1834 IT Microsoft Office 365 | 2023-10-31 | 27583.721 | 0 | 38041.658 | 0 | Other | Other
ITSSV1903 | ITSSV1903 GDC Network Upgrade | 2024-12-31 | 11409.919 | 0 | 4495.098 | 0 | Other | Other
ITSSV1912 | ITSSV1912 IT EggPlant Test App | 2023-04-01 | 388.048 | 0 |  |  | Other | Other
ITSSV1915 | ITSSV1915 SCPFO Fleet Virtul Svc Wtr | 2022-05-31 | 0 | 0 |  |  | Other | Other
ITSSV1916 | ITSSV1916 DERMS Event Hub | 2024-11-01 | 2603.403 | 0 | 1435.874 | 0 | Other | Other
ITSSV1963 | ITSSV1963 HR HCM Modernization | 2025-06-01 | 28851.882 | 0 | 37111.476 | 0 | Other | Other
ITSSV1970 | ITSSV1970 Synopsys Code Scanning | 2024-12-31 | 170.51 | 0 |  |  | Other | Other
ITSSV1980 | ITSSV1980 IDAA Appliance Lifecycle | 2022-12-31 | 13.358 | 0 |  |  | Other | Other
ITSSV1998 | ITSSV1998 1RP Comm Closet Upgrade | 2022-11-30 | 0 | 0 |  |  | Other | Other
ITSSV1999 | ITSSV1999 Cook Business LAN Lifecycle | 2023-12-31 | 2235.431 | 0 |  |  | Other | Other
ITSSV2013 | ITSSV2013 Field Mobility iPAD CI | 2023-12-31 | 39.033 | 0 |  |  | Other | Other
ITSSV2036 | ITSSV2036 Fortress VRM Renewal 2023 | 2023-06-30 | 13338.462 | 0 |  |  | Other | Other
ITSSV2039 | ITSSV2039 ServiceNow Renewal 2023 | 2023-08-31 | 14680.745 | 0 |  |  | Other | Other
ITSSV2043 | ITSSV2043 ARCOS Product Renewal 2024 | 2024-01-01 | 9128.818 | 0 | 9934.353 | 0 | Other | Other
ITSSV2063 | ITSSV2063 WAM RBS and Assessment | 2025-12-31 |  |  | 0 | 0 | Other | Other
ITSSV2069 | ITSSV2069 IBM Enterprise License Agrmt | 2024-12-31 |  |  | 12519.16 | 0 | Other | Other
ITSSV2076 | ITSSV2076 IOS Dell EMC TLA Renewal-2025 | 2025-01-31 |  |  | 20463.343 | 0 | Other | Other
ITSSV2078 | ITSSV2078 IOS Dynatrace Renewal - 2025 - | 2024-12-31 |  |  | 17813.772 | 0 | Other | Other
ITSSV2080 | ITSSV2080 IOS Splunk Renewal - 2025-2027 | 2024-12-31 |  |  | 13073.988 | 0 | Other | Other
ITSSV2086 | ITSSV2086 ESRI Platform Upgrade 11.3 | 2026-07-30 |  |  | 2242.533 | 0 | Other | Other
ITSSV2087 | ITSSV2087 Esri ELA 2025-2029 | 2025-01-31 |  |  | 42579.511 | 0 | Other | Other
ITSSV2092 | ITSSV2092 IOS OpenShift LC - Purch | 2025-01-31 |  |  | 18638.918 | 0 | Other | Other
ITSSV2093 | ITSSV2093 IBM Maximo App Suite Agreement | 2029-10-31 |  |  | 10205.496 | 0 | Other | Other
ITSSV2096 | ITSSV2096 ServiceNow Contract REN 2024 | 2024-12-31 |  |  | 10302.488 | 0 | Other | Other
ITSSV2098 | ITSSV2098 SYNOPSYS SOFTWARE 2025 | 2025-05-01 |  |  | 1220.366 | 0 | Other | Other
ITSSV2100 | ITSSV2100 Process Intelligence | 2025-12-31 |  |  | 13576.09 | 0 | Other | Other
ITSSV2122 | ITSSV2122 IOS OCPU Subscription | 2025-06-30 |  |  | 3320.797 | 0 | Other | Other
ITSSV2128 | ITSSV2128 VMWare ELA | 2025-07-31 |  |  | 10323.116 | 0 | Other | Other
ITTRN1272 | ITTRN1272 Transmission IT Projects Blank | (blank) | -37151.481 | 0 | -6807.676 | 0 | Other | Other
ITTRN1729 | ITTRN1729 T-Nexus RTO Integration | 2024-01-31 | 1390.606 | 0 |  |  | Other | Other
ITTRN1829 | ITTRN1829 Trans Outage Mgmt (T-Nexus) | 2023-08-30 | 2220.519 | 0 |  |  | Other | Other
ITTRN1844 | ITTRN1844 Trans Field Inspection | 2023-06-30 | 3211.183 | 0 |  |  | Other | Other
ITTRN1848 | ITTRN1848 T-Nexus Master Project | 2024-12-31 | 3539.852 | 0 | 3523.23 | 0 | Other | Other
ITTRN1909 | ITTRN1909 Short Circuit Modeling | 2024-12-31 | 9694.959 | 0 |  |  | Other | Other
ITTRN1921 | ITTRN1921 TPS Consolidated 2022 (T-Nexus | 2023-12-31 | 1086.775 | 0 |  |  | Other | Other
ITUOP1404 | ITUOP1404 WebEOC Implementation | 2016-12-31 | 453.759 | 0 | 520.566 | 0 | Other | Other
ITUOP2029 | ITUOP2029 TCOM and DIST Int Dsgn Constr | 2025-12-31 | 1480.463 | 0 | 458.438 | 0 | Other | Other
LGN100315 | LGN100315 Dgc Gen & Adm (Regulated) | (blank) |  |  | 0 | 0 | Other | Other
LGN101644 | LGN101644 Property Sales | (blank) |  |  | 0 | 0 | Other | Other
LGN101704 | LGN101704 Litigation - General | (blank) |  |  | 0 | 0 | Other | Other
LGN102539 | LGN102539 Ext, Media & Policy Comm | (blank) | 0 | 0 |  |  | Other | Other
LGN102653 | LGN102653 Video Web Design | (blank) |  |  | 0 | 0 | Other | Other
LGNANDA | LGNANDA Legal/Policy/Cc Anda | (blank) | 0 | 0 | 0 | 0 | Other | Other
ML020SP01 | ML020SP01 ML MITCHELL DSI PROJECT | 2023-04-30 | 0 | 0 |  |  | Other | Other
ML1E25C02 | ML1E25C02 ML1 E COOLING TOWER REPLACMENT | 2023-11-27 | 176022.417 | 1338067.75 | 0 | 10847.36 | 117-ML1E25C02 | 117-ML1E25C02
MLKP26265 | MLKP26265 ML U2 Cooling Tower Reinforce | 2026-12-31 | 1096610.033 | 185122.93 | 1859019.84 | 2390343.87 | 117-MLKP26265 | 117-MLKP26265
MLKYELGFL | MLKYELGFL MLP KY ELG CPCN Filing 2025 | 2025-06-30 |  |  | 0 | 117846.22 | 117-MLKYELGFL | Other
MLL1CGRPL | MLL1CGRPL ML U1 Clinker Grinder Rpl - KY | 2024-05-31 | 43997.027 | 88526.56 | 202987.471 | 180868.78 | 117-MLL1CGRPL | 117-MLL1CGRPL
MLL2CGRPL | MLL2CGRPL ML U2 Clinker Grinder Rpl - KY | 2024-05-31 | 133452.945 | 99308.04 | 0 | 80075.8 | 117-MLL2CGRPL | 117-MLL2CGRPL
MLLEC1VHL | MLLEC1VHL ML E U1 VHP/HP&LPA Turbn Insp | 2023-11-30 | 298295.199 | 589446.77 | 0 | 9.25 | 117-MLLEC1VHL | 117-MLLEC1VHL
MLLEP2LA0 | MLLEP2LA0 ML2 LPA L0 Rtr Rpr at CMS KPCo | 2026-06-01 |  |  | 0 | 275693.84 | 117-MLLEP2LA0 | Other
MLLEP2LA1 | MLLEP2LA1 ML2 LPA L1 Rtr Rpr at CMS KPCo | 2026-06-01 |  |  | 0 | 89424.99 | 117-MLLEP2LA1 | Other
MLLEP2LB0 | MLLEP2LB0 ML2 LPB L0 Rtr Rpr at CMS KPCo | 2026-06-01 |  |  | 0 | 275693.84 | 117-MLLEP2LB0 | Other
MLLEP2LB1 | MLLEP2LB1 ML2 LPB L1 Rtr Rpr at CMS KPCo | 2026-06-01 |  |  | 0 | 89424.99 | 117-MLLEP2LB1 | Other
MLLEP2LBI | MLLEP2LBI ML E U2 LPB Turb Insp Liberty | 2022-12-31 | 0 | -683.25 |  |  | Other | 117-MLLEP2LBI
MLLHAULRD | MLLHAULRD Mitchell Haul Road Relocate | 2024-11-30 | 803113.555 | 38130.27 | 132484.647 | 922405.75 | 117-MLLHAULRD | 117-MLLHAULRD
MLLPC0ELG | MLLPC0ELG ML PCC U0 ELG/CCR Comply - 117 | 2024-12-31 | 1782234.37 | 5316591.99 | 3414944.798 | 2295473.46 | 117-MLLPC0ELG | 117-MLLPC0ELG
MLLPC0LIM | MLLPC0LIM ML PCC U0 Lime Conversion 117 | 2023-12-31 | -33291.033 | 86736.6 | 0 | 153.62 | 117-MLLPC0LIM | 117-MLLPC0LIM
MLLPC2CTC | MLLPC2CTC ML PCC U2 Cooling Twr Cmp 117 | 2022-12-31 | -174.942 | 7597.29 |  |  | Other | 117-MLLPC2CTC
MLLPC2ESP | MLLPC2ESP ML PCC U2 ESP Upgrades 117 | 2022-12-31 | -50470.045 | 46506.43 | 0 | -3500.45 | 117-MLLPC2ESP | 117-MLLPC2ESP
MLLPCT1BP | MLLPCT1BP ML U1 Cooling Tower Canopy KYP | 2024-06-10 | 682955.453 | 960485.58 | -69142.593 | -330841.72 | 117-MLLPCT1BP | 117-MLLPCT1BP
MLLPCT1PC | MLLPCT1PC ML1 Cool Twr Canopy PreCI KPCo | 2025-11-30 | 299894.262 | -166914.05 | 0 | 167127.65 | 117-MLLPCT1PC | 117-MLLPCT1PC
MLLPPBSHD | MLLPPBSHD ML Minor PPB Liberty Shadow | (blank) | 2030564.039 | 2910154.09 | 2109996.758 | 2596663.83 | 117-MLLPPBSHD | 117-MLLPPBSHD
MLLSC1AHB | MLLSC1AHB ML S U1 Air Htr Bskt Rplc Lbty | 2023-12-31 | 463303.058 | 550116.59 | 0 | -44229.47 | 117-MLLSC1AHB | 117-MLLSC1AHB
MLLSC2AHB | MLLSC2AHB ML S U2 Air Htr Bskt Rplc Lbty | 2022-12-31 | 524.83 | 1500.41 | 0 | 0 | Other | 117-MLLSC2AHB
MLLVC1CL1 | MLLVC1CL1 Mitchell U1 SCR Catalyst L1 | 2025-05-31 |  |  | 273686.078 | 332314.66 | 117-MLLVC1CL1 | Other
MLLVC2CL4 | MLLVC2CL4 ML V U2 Cat Layer 4 Rplc Lbty | 2022-12-31 | 349.885 | 50.72 |  |  | Other | 117-MLLVC2CL4
MLWEC2HSI | MLWEC2HSI ML E U2 HP&2RH Trb & Rtr Insp | 2026-05-25 |  |  | 0 | 0 | Other | Other
MLWEP1LAR | MLWEP1LAR ML E U1 LPA Turbn Rotor Rep | 2023-11-30 | 210608.906 | 0 |  |  | Other | Other
MLWEP1RHR | MLWEP1RHR ML E U1 HP 1stRH Rem Rtr Rpr | (blank) | 38493.146 | 0 |  |  | Other | Other
MLWEP2LAR | MLWEP2LAR ML E U2 LPA Rotor Repr at CMS | 2026-06-01 | 183034.248 | 0 | 204069.984 | 0 | Other | Other
MLWEP2LBR | MLWEP2LBR ML E U2 LPB Rotor Repr at CMS | 2026-12-31 | 183034.248 | 0 | 204069.984 | 0 | Other | Other
MLWEPCPLC | MLWEPCPLC ML E Critical PLC Replacements | (blank) |  |  | 3024.912 | 0 | Other | Other
MLWEPCWPS | MLWEPCWPS ML E Circ Water Pump Cap Spare | (blank) |  |  | 10345.06 | 0 | Other | Other
MLWEPELVC | MLWEPELVC ML E Elevator Controls Upgrade | (blank) |  |  | 7906.805 | 0 | Other | Other
MLWEPNPCS | MLWEPNPCS ML E Nash Pump Cap Spare | (blank) |  |  | 17507.945 | 0 | Other | Other
MLWEPRVOS | MLWEPRVOS ML E Reverse Osmosis Rpl | (blank) |  |  | 0 | 0 | Other | Other
MLWEPSTRN | MLWEPSTRN ML E Strainer Replacements | (blank) |  |  | 15748.557 | 0 | Other | Other
MLWEPXPPT | MLWEPXPPT ML E Exciter PPT Xfrmr Repl | (blank) |  |  | 10584.059 | 0 | Other | Other
MLWES2BTI | MLWES2BTI ML2 E BFPT INSPECTION | (blank) |  |  | 0 | 0 | Other | Other
MLWMPGGBX | MLWMPGGBX ML M Gypsum GRBX Cap Spare | (blank) |  |  | 8471.586 | 0 | Other | Other
MLWMPGRBX | MLWMPGRBX ML M Gearbox Rebuild PPB | (blank) |  |  | 1694.313 | 0 | Other | Other
MLWMPHSGB | MLWMPHSGB ML M HS Coal GRBX Cap Spare | (blank) |  |  | 26185.934 | 0 | Other | Other
MLWMPLGBX | MLWMPLGBX ML M Limestone GRBX Cap Spare | (blank) |  |  | 8728.645 | 0 | Other | Other
MLWMPPOND | MLWMPPOND ML M N CY Pond Trtmnt Facility | (blank) |  |  | 20331.811 | 0 | Other | Other
MLWNPLABR | MLWNPLABR ML N Capital Labor Budgeting | (blank) | 59511.376 | 0 | 50323.844 | 0 | Other | Other
MLWSP1LSO | MLWSP1LSO ML S U1 Lower Sidewl Weld Ovly | 2023-11-30 | 309647.491 | 0 |  |  | Other | Other
MLWSPBECK | MLWSPBECK ML S Brnr Rgstr Sleeve Drv Rpl | (blank) |  |  | 10165.902 | 0 | Other | Other
MLWSPBLWR | MLWSPBLWR ML S Blowers & Fans Rplc | (blank) | 14285.993 | 0 | 8140.575 | 0 | Other | Other
MLWSPOILL | MLWSPOILL ML S Oil Lighter Replacements | (blank) |  |  | 13444.057 | 0 | Other | Other
MLWSPPDMP | MLWSPPDMP ML S PULV DAMPER REPL (OUT) | (blank) |  |  | 20166.087 | 0 | Other | Other
MLWSPPEXP | MLWSPPEXP ML S Pulv Exp Joint Repl | (blank) |  |  | 17960.855 | 0 | Other | Other
MLWSPPLVY | MLWSPPLVY ML S Pulverizer Yoke Rplc | (blank) | 9144.881 | 0 |  |  | Other | Other
MLWSPSJNT | MLWSPSJNT ML S Burner Line Slip Jnt Repl | (blank) |  |  | 12099.65 | 0 | Other | Other
MLWVC2CL1 | MLWVC2CL1 ML V U2 SCR Catalyst Layer 1 | 2033-08-10 | 0.151 | 0 | 0 | 0 | Other | Other
MLWVPBMIL | MLWVPBMIL ML V Ball Mill Inlt Liner Repl | (blank) |  |  | 8985.878 | 0 | Other | Other
MLWVPOXAB | MLWVPOXAB ML V Oxidation Air Blowers | (blank) |  |  | 1626.545 | 0 | Other | Other
P17CC1007 | P17CC1007 APCo - Virginia D Projects | 2022-12-31 | 0 | 0 |  |  | Other | Other
P17CC1031 | P17CC1031 OHPCo - D Projects | 2022-12-31 | 0 | 0 |  |  | Other | Other
SSGSNANDA | SSGSNANDA Shared Services-Accumulate Gen | (blank) | 0 | 0 | 0 | 0 | Other | Other
SSHRNANDA | SSHRNANDA Accumulate Gen & Admin HR Exp | (blank) | 0 | 0 | 0 | 0 | Other | Other
SSITNANDA | SSITNANDA Accumulate Gen _ Admin IT Exp | (blank) | 0 | 0 | 1.3856e-13 | 0 | Other | Other
SSNANDA | SSNANDA Shared Services Anda | (blank) | 0 | 0 |  |  | Other | Other
TDOANDA | TDOANDA T And D Other Anda | (blank) | 0 | 0 | 0 | 0 | Other | Other
TLSWEMERG | TLSWEMERG TRANS Project Labor | 1902-01-01 | -1.1369e-13 | 0 | 0 | 0 | Other | Other
TSCREDITC | TSCREDITC Tech Servics Cap Offset Credit | 2024-12-31 | -74637.504 | 0 | 4874.996 | 0 | Other | Other
WSNANDA | WSNANDA Generation ANDA | (blank) | 8.5265e-13 | 0 | 2.558e-13 | 0 | Other | Other
WSX114322 | WSX114322 Eng'r Svc. Capital Staff Budge | 2013-05-12 | 0 | 0 | 1.7408e-13 | 0 | Other | Other
WSXRENEWC | WSXRENEWC Renewable Capital Staff Budget | (blank) | 0 | 0 | 9.0949e-12 | 0 | Other | Other
X00000288 | X00000288 For Property Acctg Use Only | (blank) | 0 | -247320.04 | 0 | 37645.26 | Other | Other
X00000290 | X00000290 For Property Acctg Use Only | (blank) | 100646.056 | 0 | 172058.788 | 0 | Other | Other
X00116261 | X00116261 Pro Serv Capital All Reg Gener | (blank) | 0 | 0 |  |  | Other | Other
XHWCAP103 | XHWCAP103 HW CAP CI - 103 | 2025-12-31 | 0 | 0 |  |  | Other | Other
XHWCAP114 | XHWCAP114 HW CAP CI - 114 | 2025-12-31 | 0 | 0 |  |  | Other | Other
XHWCAP117 | XHWCAP117 HW CAP CI - 117 | 2025-12-31 | 0 | 18884.8 | 0 | 118353.17 | 117-XHWCAP117 | 117-XHWCAP117
XHWCAP120 | XHWCAP120 HW CAP CI - 120 | 2025-12-31 | 0 | 0 |  |  | Other | Other
XHWCAP150 | XHWCAP150 HW CAP CI - 150 | 2025-12-31 | 0 | 0 |  |  | Other | Other
XHWCAP160 | XHWCAP160 HW CAP CI - 160 | 2025-12-31 | 0 | 0 |  |  | Other | Other
XHWCAP169 | XHWCAP169 HW CAP CI - 169 | 2025-12-31 | 0 | 0 |  |  | Other | Other
XHWCAP180 | XHWCAP180 HW CAP CI - 180 | 2025-12-31 | 0 | 0 |  |  | Other | Other
XHWCAP190 | XHWCAP190 HW CAP CI - 190 | 2025-12-31 | 0 | 0 |  |  | Other | Other
XHWCAP192 | XHWCAP192 HW CAP CI - 192 | 2025-12-31 | 0 | 0 |  |  | Other | Other
XHWCAP194 | XHWCAP194 HW CAP CI - 194 | 2025-12-31 | 0 | 0 |  |  | Other | Other
XHWCAP200 | XHWCAP200 HW CAP CI - 200 | 2025-12-31 | 0 | 0 |  |  | Other | Other
XHWCAP250 | XHWCAP250 HW CAP CI - 250 | 2025-12-31 | 0 | 0 |  |  | Other | Other
XHWCAP380 | XHWCAP380 HW CAP CI - 380 | 2025-12-31 | 0 | 0 |  |  | Other | Other
XHWCAP385 | XHWCAP385 HW CAP CI - 385 | 2025-12-31 | 0 | 0 |  |  | Other | Other
Grand | Grand Total |  | 14741464.239 | 12954356.63 | 29939432.045 | 21089786.23