## ML2 Hydrated Lime PDS
Kentucky Power Company
Case No. 2025-00257
AEP Generation Project Data Sheet
REV 3.0
Plant |  |  |  | Mitchell | [12 empty] | Project Lead (PL) |  |  | Janine E White | [9 empty] | Proj ID |  | MLPDSI01
Unit |  |  |  | Mitchell 0 | [12 empty] | PLs Manager |  |  | Robert S Gellenbeck
Project Type |  |  |  | Capital Standard Project | [12 empty] | PLs Director* |  |  | Robert S Gellenbeck
Project Delivery Model |  |  |  | Intermediate
Cost Estimate Quality |  |  |  | Class 3
Project Title |  |  |  | Mitchell Unit 1&2 Dry Sorbent Injection Project
This project will reconfigure the existing dry sorbent injection (DSI) system to more efficiently handle hydrated lime and reduce issues related to corrosion as well as gain benefits such as heat rate improvement, improved Equivalent Unplanned Outage Rate (EUOR) and a lower minimum load.Mitchell Plant currently uses trona for SO3 mitigation and injects at the air heater (AH) outlet. Significant benefits can be realized by removing SO3 at the Selective Catalytic Reduction (SCR) inlet as compared to the AH outlet. Executing this project will allow the units to have lower minimum load, improved heat rate, sorbent dispersion and EUOR. It also helps with the long term protection of the SCR catalyst, air heaters and precipitators. By protecting the equipment from high concentrations of acid gas we are able to delay basket change out, catalyst changes, ducting and fan hubs.This Improvement Requisition is requesting $2.6M in funding for phase 1 of 2. The first phase includes the engineering and procurement for the project. Phase 2 will include the expenses associated with the actual construction and closeout. The total cost of all phases is projected to be $7.9M.
Outage |  | No | [24 empty] | Direct | [6 empty] | 1997024
Required? | [26 empty] | Costs
(Yes or No)
Project Start |  | 2021-07-01 | [16 empty] | Project End (In-Service) Date | [9 empty] | 2022-12-31
Date
Cash Flow
Capital / Lease |  | 2021 |  |  | 2022 | [5 empty] | 2023 |  |  |  |  | 2024 |  |  | 2025 |  |  | 2026 |  |  |  | 2027 |  |  |  |  | 2028 |  |  |  | Total
Internal Labor |  | 0 |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
Outside Services |  | 911300 |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 911300
Material |  | 0 |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
Other |  | 0 |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
Fleet |  | 0 |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
Fringes |  | 18000 |  |  | 125644 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 143644
FODA |  | 693854 |  |  | 279208 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 973062
Contingency |  | 64080 |  |  | 48582 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 112662
O&M Expense |  | 2021 |  |  | 2022 | [5 empty] | 2023 |  |  |  |  | 2024 |  |  | 2025 |  |  | 2026 |  |  |  | 2027 |  |  |  |  | 2028 |  |  |  | Total
Internal Labor |  | 0 |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
Outside Services |  | 0 |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
Material |  | 0 |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
Lease Payments |  | 0 |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
Other |  | 0 |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
Fleet |  | 0 |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
Fringes |  | 0 |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
Removal |  | 2021 |  |  | 2022 | [5 empty] | 2023 |  |  |  |  | 2024 |  |  | 2025 |  |  | 2026 |  |  |  | 2027 |  |  |  |  | 2028 |  |  |  | Total
Internal Labor |  | 0 |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
Outside Services |  | 0 |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
Material |  | 0 |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
Other |  | 0 |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
Fleet |  | 0 |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
Fringes |  | 0 |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
Removal Overheads |  | 0 |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
FODA |  | 0 |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
Contingency |  | 0 |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
Total Costs |  | 2021 |  |  | 2022 | [5 empty] | 2023 |  |  |  |  | 2024 |  |  | 2025 |  |  | 2026 |  |  |  | 2027 |  |  |  |  | 2028 |  |  |  | Total
Total Direct Capital |  | 1669234 |  |  | 327790 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 1997024
Total Direct Removal |  | 0 |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
Total Direct |  | 1669234 |  |  | 327790 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 1997024
Total Dir Cap+Fleet+Fringe |  | 1687234 |  |  | 453434 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 2140668
Cap Overheads - Standard |  | 264666 |  |  | 102926 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 367592
AFUDC Basis |  | 975950 |  |  | 2248660 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
AFUDC Debt - Standard |  | 8732 |  |  | 30256 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 38988
AFUDC Equity - Standard |  | 9848 |  |  | 34118 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 43966
Total Capital |  | 1970480 |  |  | 620734 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 2591214
Total Removal |  | 0 |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
Total Approved Project Cost |  | 1970480 |  |  | 620734 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 2591214
Total Expense |  | 0 |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
CIAC / Other Credits |  | 0 |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0
Total Project Cost |  | 1970480 |  |  | 620734 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 2591214
Accum Total Project Cost |  | 1970480 |  |  | 2591214 | [5 empty] | 2591214 |  |  |  |  | 2591214 |  |  | 2591214 |  |  | 2591214 |  |  |  | 2591214 |  |  |  |  | 2591214
Accum Total Cap Less CIAC |  | 1970480 |  |  | 2591214 | [5 empty] | 2591214 |  |  |  |  | 2591214 |  |  | 2591214 |  |  | 2591214 |  |  |  | 2591214 |  |  |  |  | 2591214
Will this project increase outage time? (Yes or No) | [12 empty] | No | [11 empty] | If Yes, How Many Days? | [10 empty] | 0
Classify Project | [6 empty] | Discretionary Projects
Section A | [11 empty] | Describe the root-cause of the problem to be solved
Mitchell Plant currently uses trona for SO3 mitigation and injects at the AH outlet. Significant benefits can be realized by removing SO3 at the SCR inlet as compared to the AH outlet. Executing this project will allow the units to have lower minimum load, improved heat rate and improved EUOR. It also helps with the long term protection of the SCR catalyst, air heaters, and precipitators. By protecting the equipment from high concentrations of acid gas and corrosion, we are able to delay basket change out, catalyst changes, ducting and fan hubs.The project will entail the following: The current DSI piping at the AH outlets will be re-routed to the SCR inlets which may require new splitters, distribution hoses, sorbent lances and injection ports at this location. Demolition and removal of existing discharge augers, pant leg splitters, bin vent filters and vent hopper components at the two existing DSI silos. Installation of upgraded silo discharge assemblies, weigh hoppers, vent hoppers, bin vent filters and dehumidification skids. A conversion of the existing Programmable Logic Controller (PLC) and addition of new integration to the existing plant Distributed Control System (DCS) is required to run these components. The inside of the DSI silos will be coated since original silo design is bolted and a known source of moisture infiltration.
Section B | [11 empty] | What alternatives have been considered, why must work be done in budgeted year.
The following options have been considered as part of the Risk Balanced Tech Options (RBTO) process:Option 1: Do nothing - rejected due to expensive sorbent costs and current performance limitations of trona injection at AH outlet.Option 2: Retrofit the DSI system for reliability and relocate trona injection to the SCR inlet - the limitations of performance at minimum load make this option untenable. The retrofit would replace certain components and eliminate certain safety hazards, but insufficient removal of SO3 remains. In addition, trona contract is set to expire in 2019 and converting to hydrated lime is more efficient. Option 3: Retrofit the DSI system to handle hydrated lime and relocate injection to the SCR inlet - this option provides all of the benefits associated with the transition to hydrated lime and is the recommeded option.Option 4: Utilize existing system with trona and reroute piping to SCR inlet - this is the lowest cost option but in addition to not receiving benefits associated with retrofitting the unit, there is still the limitations of trona associated with minimum load performance, which rule out this option.Option 5: Utilize existing system with lime, add dehumidification skid and reroute piping to SCR inlet - safety impacts associated with the material handling and not retrofitting the equipment rule out this option.
Section C | Describe how project will improve unit availability, capacity, heat rate, or reduce O&M / capital costs in the future vs DOING NOTHING /REASONABLE ALTERNATIVE (if doing nothing is not a reasonable alternative).
YEAR = |  |  | 0
[6 empty] | 0 |  |  |  | 1 |  |  |  | 2 |  |  |  | 3 |  |  | 4 |  | 5 |  |  |  |  | 6 |  |  |  |  | 7 & BEYOND
Annual Probability of Failure | [5 empty] | 0% |  |  |  | 0% |  |  |  | 0% |  |  |  | 0% |  |  | 0% |  | 0% |  |  |  |  | 0% |  |  |  |  | 0%
Statistically Adjusted Probability of Failure | [5 empty] | 0% |  |  |  | 0% |  |  |  | 0% |  |  |  | 0% |  |  | 0% |  | 0% |  |  |  |  | 0% |  |  |  |  | 0%
Apply Probability of Failure Calcs? | [5 empty] | No
[6 empty] | 0 |  |  |  | 1 |  |  |  | 2 |  |  |  | 3 |  |  | 4 |  |  | 5 |  |  |  | 6 |  |  |  |  | 7 & BEYOND
Availability Improvement | [5 empty] | 0% |  |  |  | 0% |  |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  |  |  | 0%
(% EUOR Improvement/yr)
100% Probability of Failure Availbility Improvement | [5 empty] | 0%
[6 empty] | 0 |  |  |  | 1 |  |  |  | 2 |  |  |  | 3 |  |  | 4 |  |  | 5 |  |  |  | 6 |  |  |  |  | 7 & BEYOND
O&M Cost Reduction/Avoidance | [5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
($000s)
100% Probability of Failure O&M Cost Reduction/Avoidance | [5 empty] | 0
[6 empty] | 0 |  |  |  | 1 |  |  |  | 2 |  |  |  | 3 |  |  | 4 |  |  | 5 |  |  |  | 6 |  |  |  |  | 7 & BEYOND
Capital Cost Reduction/Avoidance | [5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
($000s)
100% Probability of Failure Capital Cost Reduction/Avoidance | [5 empty] | 0
[8 empty] | 0 |  |  |  | 1 |  | 2 |  |  |  | 3 |  |  | 4 |  |  | 5 |  |  |  | 6 |  |  |  |  | 7 & BEYOND
Capacity Improvement in MW’s | [7 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  | 1 |  |  | 2 |  |  | 3 |  |  | 4 |  |  | 5 |  |  |  | 6 |  |  |  |  | 7 & BEYOND
Fuel Efficiency | [7 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
(Express in Btu/kwh improvement)
Section D | [8 empty] | What sensitivity analysis must be run to quantify the impact of potential variations in project costs, benefits, or schedules?

## ML2 Hydrated Lime Analysis
AEP Unit Valuation | ML2 Hydrated Lime Conversion Including Fuel Impact | [55 empty] | Ken Tamms
Capital Budgeting Unit Analysis | [56 empty] | Jeff Kersanty
| -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 |  | Project | [26 empty] | Rob Dool
Calendar Year | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 |  | Total | [26 empty] | 0
Month Operational In Year |  |  |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | [28 empty] | 0
0
Electric Revenues ($000)
Base Case - Using Unit Value Model Spread Option Only
Staus Quo Mitchell 2
Intrinsic Value |  |  |  | 704.3419 | 2265.725 | 5545.821 | 12916.3537 | 12896.1023 | 16295.8245 | 17708.2007 | 19458.3781 | 14855.1081 | 11320.8142 | 4993.9288 | 2805.5275 | 1041.6755 | 1439.0403 | 114.5305 | -329.5048 | 1094.8351 | 1559.7037 | 668.6305 | 679.6762 | 0 | 0 | 0 | 0 | 0
Extrinsic Value |  |  |  | 77.3947 | 420.4075 | 1827.9975 | 3163.8555 | 4878.9807 | 5692.5642 | 5526.5798 | 6918.8067 | 7438.6594 | 6970.441 | 5792.4597 | 5395.9561 | 5183.4142 | 6492.8439 | 7195.4593 | 7740.7088 | 8354.8734 | 10411.0851 | 11027.0689 | 13227.7872 | 0 | 0 | 0 | 0 | 0
Total |  |  |  | 781.7366 | 2686.1325 | 7373.8186 | 16080.2093 | 17775.083 | 21988.3887 | 23234.7805 | 26377.1849 | 22293.7675 | 18291.2551 | 10786.3885 | 8201.4836 | 6225.0897 | 7931.8842 | 7309.9898 | 7411.204 | 9449.7085 | 11970.7887 | 11695.6994 | 13907.4633 | 0 | 0 | 0 | 0 | 0
CAPEX Improved Mitchell 2
Unit Mitchell 2 Intrinsic Value |  |  |  | 704.3419 | 2265.725 | 10720.1789 | 18245.1082 | 18769.5364 | 22174.4247 | 23113.2036 | 25746.6584 | 21753.184 | 17791.6814 | 9817.0411 | 8198.1301 | 1312.571 | 1753.3088 | 442.8272 | 6.9374 | 1436.3951 | 658.1383 | 1075.9524 | 1148.1466 | 0 | 0 | 0 | 0 | 0
Unit Mitchell 2 Extrinsic Value |  |  |  | 77.3947 | 420.4075 | 2922.4233 | 4086.4639 | 6261.6308 | 7243.7188 | 7019.0838 | 8776.2701 | 9458.9276 | 9907.6297 | 10140.8888 | 8772.723 | 5183.4142 | 6492.8439 | 7195.4593 | 7740.7088 | 8354.8734 | 11738.7087 | 11027.0689 | 13227.7872 | 0 | 0 | 0 | 0 | 0
Total |  |  |  | 781.7366 | 2686.1325 | 13642.6022 | 22331.5722 | 25031.1672 | 29418.1436 | 30132.2874 | 34522.9285 | 31212.1117 | 27699.311 | 19957.9299 | 16970.8531 | 6495.9852 | 8246.1527 | 7638.2866 | 7747.6462 | 9791.2685 | 12396.847 | 12103.0213 | 14375.9338 | 0 | 0 | 0 | 0 | 0
Change in Capacity Value |  |  |  | 0 | 0 | -168.9668 | -216.3662 | -263.5572 | -310.6724 | -357.655 | -404.2966 | -421.4432 | -429.8998 | -438.4808 | -447.1197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Results Calibrated to Gentrader Simulation | 1: 0; 2: 0; 3: 6268.7836; 4: 6251.3629; 5: 7256.0842; 6: 7429.7549; 7: 6897.507
Staus Quo Mitchell 2
Intrinsic Value |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Extrinsic Value |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
CAPEX Improved Mitchell 2 | -2: 5-Year; -1: Gross; 0: Tax Effected
Unit Mitchell 2 Intrinsic Value | NPV9% | 13530.1843 | 8118.1106 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Unit Mitchell 2 Extrinsic Value | NPV15% | 12578.4461 | 7547.0677 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Use the Gentrader Calibration: | -2: FALSE
Incremental Revenues Due to Improvement Project |  | 1 | Base Case | 0 | 0 | 6099.8168 | 6034.9967 | 6992.5269 | 7119.0824 | 6539.852 | 7741.447 | 8496.901 | 8978.1561 | 8733.0606 | 8322.2498 | 270.8955 | 314.2686 | 328.2968 | 336.4423 | 341.56 | 426.0583 | 407.3219 | 468.4704 | 0 | 0 | 0 | 0 | 0 |  | 77951.4031
Fixed O&M Savings Due to Improvement Project
Maintenance/Start/Startup Fuel |  |  |  | 0 | 0 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outage Maintenance That will be avoided |  |  |  | 0 | 0 | -128.198 | -128.198 | -128.198 | -128.198 | -128.198 | -128.198 | -128.198 | -128.198 | -128.198 | -128.198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Type in Item 3 Savings |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Fixed O&M Savings |  |  |  | 0 | 0 | -64.198 | -64.198 | -64.198 | -64.198 | -64.198 | -64.198 | -64.198 | -64.198 | -64.198 | -64.198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Property Tax Impact of Improvement Project |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
EBITDA |  |  |  | 0 | 0 | 6164.0148 | 6099.1947 | 7056.7249 | 7183.2804 | 6604.05 | 7805.645 | 8561.099 | 9042.3541 | 8797.2586 | 8386.4478 | 270.8955 | 314.2686 | 328.2968 | 336.4423 | 341.56 | 426.0583 | 407.3219 | 468.4704 | 0 | 0 | 0 | 0 | 0
Tax Depreciation Associated With Improvement Project |  |  |  | 0 | 0 | 148.575 | 286.4569 | 265.8726 | 246.8322 | 229.2198 | 212.9283 | 197.8586 | 183.9193 | 182.0731 | 182.6085 | 182.6939 | 182.363 | 182.0971 | 181.8913 | 181.7411 | 181.6423 | 181.5911 | 181.5839 | 181.5839 | 181.5839 | 88.115 | 0 | 0
Expense Write-off of Capital Project | 1: 0
Removal Expense of Old Equipment (Tax Calculation Only) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EBT |  | 0 | 0 | 0 | 0 | 6015.4398 | 5812.7378 | 6790.8523 | 6936.4483 | 6374.8302 | 7592.7168 | 8363.2403 | 8858.4349 | 8615.1854 | 8203.8393 | 88.2016 | 131.9055 | 146.1996 | 154.5509 | 159.8189 | 244.416 | 225.7308 | 286.8866 | -181.5839 | -181.5839 | -88.115 | 0 | 0 |  | 74550.1522
Current Income Tax @ 26.1% |  |  | 0 | 0 | 0 | 1572.1352 | 1519.159 | 1774.7893 | 1812.8408 | 1666.0619 | 1984.3565 | 2185.7329 | 2315.152 | 2251.5787 | 2144.0734 | 23.0515 | 34.4735 | 38.2093 | 40.3919 | 41.7687 | 63.8781 | 58.9947 | 74.9778 | -47.4569 | -47.4569 | -23.0289 | 0 | 0 |  | 19483.6823
Project Net Income After Tax (Tax) |  |  | 0 | 0 | 0 | 4443.3046 | 4293.5788 | 5016.0631 | 5123.6075 | 4708.7683 | 5608.3602 | 6177.5075 | 6543.2829 | 6363.6067 | 6059.7659 | 65.1501 | 97.432 | 107.9904 | 114.159 | 118.0502 | 180.5379 | 166.736 | 211.9088 | -134.1269 | -134.1269 | -65.0862 | 0 | 0 |  | 55066.4699
After-Tax Cash Flow
Pre-Tax Project Cash Flow |  |  | 0 | 0 | 0 | 6164.0148 | 6099.1947 | 7056.7249 | 7183.2804 | 6604.05 | 7805.645 | 8561.099 | 9042.3541 | 8797.2586 | 8386.4478 | 270.8955 | 314.2686 | 328.2968 | 336.4423 | 341.56 | 426.0583 | 407.3219 | 468.4704 | 0 | 0 | 0 | 0 | 0
Less: Income Tax Paid (Saved) | 9.2565 |  | 0 | 0 | 0 | 1572.1352 | 1519.159 | 1774.7893 | 1812.8408 | 1666.0619 | 1984.3565 | 2185.7329 | 2315.152 | 2251.5787 | 2144.0734 | 23.0515 | 34.4735 | 38.2093 | 40.3919 | 41.7687 | 63.8781 | 58.9947 | 74.9778 | -47.4569 | -47.4569 | -23.0289 | 0 | 0
After-Tax Cash Out Flow |  |  | 0 | 0 | 0 | 4591.8796 | 4580.0357 | 5281.9357 | 5370.4397 | 4937.9881 | 5821.2885 | 6375.3661 | 6727.2022 | 6545.6799 | 6242.3744 | 247.844 | 279.7951 | 290.0875 | 296.0504 | 299.7913 | 362.1802 | 348.3271 | 393.4926 | 47.4569 | 47.4569 | 23.0289 | 0 | 0
Equity Investments |  |  | 0 | -1817 | -2133 | -12 | -12 | -12 | -12 | -12 | -12 | -12 | -12 | -12 | -12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
After Tax Cash Flow |  |  | -0.001 | -1817 | -2133 | 4579.8796 | 4568.0357 | 5269.9357 | 5358.4397 | 4925.9881 | 5809.2885 | 6363.3661 | 6715.2022 | 6533.6799 | 6230.3744 | 247.844 | 279.7951 | 290.0875 | 296.0504 | 299.7913 | 362.1802 | 348.3271 | 393.4926 | 47.4569 | 47.4569 | 23.0289 | 0 | 0
Date For Cash Flows =====> USER INPUT (Default to mid year) |  |  | 2020-06-30 | 2021-06-30 | 2022-06-30 | 2023-06-30 | 2024-06-30 | 2025-06-30 | 2026-06-30 | 2027-06-30 | 2028-06-30 | 2029-06-30 | 2030-06-30 | 2031-06-30 | 2032-06-30 | 2033-06-30 | 2034-06-30 | 2035-06-30 | 2036-06-30 | 2037-06-30 | 2038-06-30 | 2039-06-30 | 2040-06-30 | 2041-06-30 | 2042-06-30 | 2043-06-30 | 2044-06-30 | 2045-06-30
|  |  | -0.001 | -1817.001 | -3950.001 | 629.8786 | 5197.9143 | 10467.8499 | 15826.2896 | 20752.2777 | 26561.5662 | 32924.9323 | 39640.1345 | 46173.8144 | 52404.1888 | 52652.0328 | 52931.8279 | 53221.9154 | 53517.9658 | 53817.7571 | 54179.9373 | 54528.2644 | 54921.7571 | 54969.214 | 55016.6709 | 55039.6998 | 55039.6998 | 55039.6998
Return Summary |  |  | XNPV | -1702.9538 | -3576.5942 | 193.8901 | 3717.9487 | 7528.3144 | 11159.491 | 14288.0913 | 17745.4961 | 21294.9529 | 24805.5562 | 28006.8698 | 30867.4562 | 30974.1078 | 31086.9512 | 31196.6023 | 31301.4648 | 31400.9873 | 31513.6745 | 31615.2491 | 31722.773 | 31734.9269 | 31746.3179 | 31751.4986 | 31751.4986 | 31751.4986
IRR - 5 YR | 71.77% |  | XIRR | #NUM! | #NUM! | 10.57% | 53.5% | 71.77% | 79.53% | 82.82% | 84.72% | 85.77% | 86.33% | 86.62% | 86.76% | 86.76% | 86.77% | 86.77% | 86.77% | 86.77% | 86.77% | 86.77% | 86.77% | 86.77% | 86.77% | 86.77% | 86.77% | 86.77%
IRR - 10 YR | 86.33%
IRR - 15 YR | 86.77%
IRR - 20 YR | 86.77%
Simple Payback Years | 2.8625 |  |  | -1817.001 | -3950.001 | 629.8786 | 5197.9143 | 10467.8499 | 15826.2896 | 20752.2777 | 26561.5662 | 32924.9323 | 39640.1345 | 46173.8144 | 52404.1888 | 52652.0328 | 52931.8279 | 53221.9154 | 53517.9658 | 53817.7571 | 54179.9373 | 54528.2644 | 54921.7571 | 54969.214 | 55016.6709 | 55039.6998 | 55039.6998 | 55039.6998
|  |  |  | 1 | 1 | 0.86247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Analyst: | 2 | Discretionary? | 1 |  | Project ID: | Enter Project ID Here
Project NPV 6.7% - 5 Years | 7528.3144 |  | 2020-06-30: Brief comments for DB Summary:; 2022-06-30: (process will grab all 3 lines, flag length greater than 256 characters)
Project NPV 6.7% - 10 Years | 24805.5562 | bar: 2020-06-30 to 2027-06-30
Project NPV 6.7% - 15 Years | 31196.6023 | bar: 2020-06-30 to 2027-06-30
Project NPV 6.7% - 20 Years | 31722.773 | bar: 2020-06-30 to 2027-06-30
|  |  | 0 | Comment ok
ML2 Hydrated Lime Conversion Including Fuel Impact
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Book Income Analysis For Per Share Impacts |  |  |  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045
EBITDA |  |  |  | 0 | 0 | 6164.0148 | 6099.1947 | 7056.7249 | 7183.2804 | 6604.05 | 7805.645 | 8561.099 | 9042.3541 | 8797.2586 | 8386.4478 | 270.8955 | 314.2686 | 328.2968 | 336.4423 | 341.56 | 426.0583 | 407.3219 | 468.4704 | 0 | 0 | 0 | 0 | 0
Depreciation Book |  |  |  | -17.3595 | -17.3419 | 101.2026 | 101.4028 | 101.5693 | 101.6344 | 101.7231 | 101.7858 | 101.8572 | 101.98 | 102.1182 | 102.2458 | 102.3518 | 103.0357 | 105.4552 | 113.7917 | 113.9317 | 114.3192 | 114.6645 | 114.7828 | 115.2376 | 117.1742 | 117.9785 | 118.1759 | 0
Interest Expense on Leveraged Equity |  |  |  | 0 | 0 | 158.79 | 158.79 | 158.79 | 158.79 | 158.79 | 158.79 | 158.79 | 158.79 | 158.79 | 158.79 | 158.79 | 158.79 | 158.79 | 158.79 | 158.79 | 158.79 | 158.79 | 158.79 | 158.79 | 158.79 | 158.79 | 158.79 | 158.79
EBT |  |  |  | 17.3595 | 17.3419 | 5904.0222 | 5839.0019 | 6796.3656 | 6922.8561 | 6343.5368 | 7545.0692 | 8300.4518 | 8781.5841 | 8536.3503 | 8125.412 | 9.7537 | 52.4429 | 64.0516 | 63.8606 | 68.8382 | 152.9491 | 133.8674 | 194.8977 | -274.0276 | -275.9642 | -276.7685 | -276.9659 | -158.79
Book Income Tax @ 26.1% |  |  |  | 4.5369 | 4.5323 | 1543.0162 | 1526.0231 | 1776.2301 | 1809.2884 | 1657.8834 | 1971.9038 | 2169.3231 | 2295.067 | 2230.9752 | 2123.5764 | 2.5491 | 13.7059 | 16.7399 | 16.69 | 17.9909 | 39.9732 | 34.9863 | 50.9365 | -71.6171 | -72.1232 | -72.3334 | -72.385 | -41.4998
After tax Net Income |  |  |  | 12.8226 | 12.8096 | 4361.006 | 4312.9787 | 5020.1354 | 5113.5676 | 4685.6535 | 5573.1654 | 6131.1287 | 6486.5171 | 6305.3752 | 6001.8356 | 7.2046 | 38.7369 | 47.3117 | 47.1706 | 50.8474 | 112.9758 | 98.8812 | 143.9612 | -202.4105 | -203.841 | -204.435 | -204.5808 | -117.2902
AEP Per Share Analysis
Proportion of Capital Financed Internally with Debt | 60%
All-In Pre Tax Debt Interest Rate (Libor + 170 bps) | 6.7%
AEP Share Price | 41
|  |  |  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045
Current EPS Forecast - $/Sh |  |  |  | 4.1746 | 4.2998 | 4.4288 | 4.5617 | 4.6985 | 4.8395 | 4.9847 | 5.1342 | 5.2882 | 5.2882 | 5.2882 | 5.2882 | 5.2882 | 5.2882 | 5.2882 | 5.2882 | 5.2882 | 5.2882 | 5.2882 | 5.2882 | 5.2882 | 5.2882 | 5.2882 | 5.2882 | 5.2882
Current Shares Outstanding - 000 |  |  |  | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400
Current AEP Net Income Forecast - $000 |  |  |  | 2072266.476 | 2134434.4703 | 2198467.5044 | 2264421.5295 | 2332354.1754 | 2402324.8007 | 2474394.5447 | 2548626.381 | 2625085.1725 | 2625085.1725 | 2625085.1725 | 2625085.1725 | 2625085.1725 | 2625085.1725 | 2625085.1725 | 2625085.1725 | 2625085.1725 | 2625085.1725 | 2625085.1725 | 2625085.1725 | 2625085.1725 | 2625085.1725 | 2625085.1725 | 2625085.1725 | 2625085.1725
Incr. Net Income From Capital Project - $000 |  |  |  | 12.8226 | 12.8096 | 4361.006 | 4312.9787 | 5020.1354 | 5113.5676 | 4685.6535 | 5573.1654 | 6131.1287 | 6486.5171 | 6305.3752 | 6001.8356 | 7.2046 | 38.7369 | 47.3117 | 47.1706 | 50.8474 | 112.9758 | 98.8812 | 143.9612 | -202.4105 | -203.841 | -204.435 | -204.5808 | -117.2902
Pro Forma Net Income With Project |  |  |  | 2072279.2986 | 2134447.2798 | 2202828.5104 | 2268734.5083 | 2337374.3109 | 2407438.3683 | 2479080.1982 | 2554199.5464 | 2631216.3012 | 2631571.6896 | 2631390.5476 | 2631087.008 | 2625092.377 | 2625123.9094 | 2625132.4842 | 2625132.3431 | 2625136.0198 | 2625198.1483 | 2625184.0536 | 2625229.1336 | 2624882.762 | 2624881.3315 | 2624880.7374 | 2624880.5916 | 2624967.8822
Total Cost of Capital Project | 3950
Amount Financed with AEP Debt | 2370
Annual Interest Chg @ Libor + 170 bps | 158.79
AEP Equity Required to Fund Capital Project | 1580
Incremental Shares required (x1000) | 38.5366 |  |  | 0 | 0 | 38.5366 | 38.5366 | 38.5366 | 38.5366 | 38.5366 | 38.5366 | 38.5366 | 38.5366 | 38.5366 | 38.5366 | 38.5366 | 38.5366 | 38.5366 | 38.5366 | 38.5366 | 38.5366 | 38.5366 | 38.5366 | 38.5366 | 38.5366 | 38.5366 | 38.5366 | 38.5366
Existing AEP Shares (x1000) |  |  |  | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400 | 496400
Pro Forma AEP Shares (x1000) |  |  |  | 496400 | 496400 | 496438.5366 | 496438.5366 | 496438.5366 | 496438.5366 | 496438.5366 | 496438.5366 | 496438.5366 | 496438.5366 | 496438.5366 | 496438.5366 | 496438.5366 | 496438.5366 | 496438.5366 | 496438.5366 | 496438.5366 | 496438.5366 | 496438.5366 | 496438.5366 | 496438.5366 | 496438.5366 | 496438.5366 | 496438.5366 | 496438.5366
Pro Forma EPS |  |  |  | 4.1746 | 4.2999 | 4.4373 | 4.57 | 4.7083 | 4.8494 | 4.9937 | 5.145 | 5.3002 | 5.3009 | 5.3005 | 5.2999 | 5.2878 | 5.2879 | 5.2879 | 5.2879 | 5.2879 | 5.2881 | 5.288 | 5.2881 | 5.2874 | 5.2874 | 5.2874 | 5.2874 | 5.2876
Incremental Earnings on Incremental Shares |  |  |  | 0.33274 | 0.3324 | 113.1653 | 111.9191 | 130.2693 | 132.6938 | 121.5897 | 144.6201 | 159.0989 | 168.321 | 163.6205 | 155.7438 | 0.18695 | 1.0052 | 1.2277 | 1.224 | 1.3195 | 2.9317 | 2.5659 | 3.7357 | -5.2524 | -5.2895 | -5.305 | -5.3087 | -3.0436
EPS Accretion/(Dilution) $/Sh |  |  |  | 2.5831e-05 | 2.5805e-05 | 0.0084408 | 0.0083337 | 0.0097476 | 0.0099248 | 0.0090516 | 0.010828 | 0.01194 | 0.012656 | 0.012291 | 0.011679 | -0.00039599 | -0.00033248 | -0.0003152 | -0.00031549 | -0.00030808 | -0.00018293 | -0.00021132 | -0.00012052 | -0.00081823 | -0.00082111 | -0.00082231 | -0.0008226 | -0.00064677
NPV of EPS Impact at WACC=9% (10 Years) | 0.050084
0.059038
CashFlow to AEP - $000 |  |  |  | -1817 | -2133 | 4579.8796 | 4568.0357 | 5269.9357 | 5358.4397 | 4925.9881 | 5809.2885 | 6363.3661 | 6715.2022 | 6533.6799 | 6230.3744 | 247.844 | 279.7951 | 290.0875 | 296.0504 | 299.7913 | 362.1802 | 348.3271 | 393.4926 | 47.4569 | 47.4569 | 23.0289 | 0 | 0
Cash Flow Per Total AEP Shares- $/Sh | 0.046782 |  |  | -0.0036604 | -0.0042969 | 0.0092255 | 0.0092016 | 0.010615 | 0.010794 | 0.0099227 | 0.011702 | 0.012818 | 0.013527 | 0.013161 | 0.01255 | 0.00049924 | 0.0005636 | 0.00058434 | 0.00059635 | 0.00060388 | 0.00072956 | 0.00070165 | 0.00079263 | 9.5595e-05 | 9.5595e-05 | 4.6388e-05 | 0 | 0
Incremental Operating Adjustments Assoc. With CAPEX |  |  |  | 2021: The Changes Outlined Below Are Active In The Current Model Run
Avoided Capital |  |  |  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044
Avoided Capital (enter as a positive number if the capital will not be spent due to the incremental project) |  |  |  | 0 | 0 | -12 | -12 | -12 | -12 | -12 | -12 | -12 | -12 | -12 | -12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Depreciation on avoided capital (calculated by the model) |  |  |  | 0 | 0 | 0.45 | 1.3162 | 2.1175 | 2.8587 | 3.5443 | 4.1785 | 4.7651 | 5.3077 | 5.8431 | 6.3785 | 6.4639 | 6.133 | 5.8671 | 5.6613 | 5.5111 | 5.4123 | 5.3611 | 5.3538 | 5.3538 | 5.3538 | 0 | 0
FO + MO Impact |  |  |  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044
Status Quo Add-Factor (to Change Base Case Availability) |  |  |  | 0% | 0% | -0.657% | -0.657% | -0.657% | -0.657% | -0.657% | -0.657% | -0.657% | -0.657% | -0.657% | -0.657% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Status Quo FO + MO (%) |  |  |  | 28.65% | 27.93% | 27.79% | 27.89% | 29.55% | 29.55% | 29.55% | 29.55% | 29.55% | 29.55% | 29.55% | 29.55% | 30.21% | 30.21% | 30.21% | 30.21% | 30.21% | 30.21% | 30.21% | 30.21% | 30.21% | 0% | 0% | 0%
Incremental Change Due to CAPEX |  |  |  | 0% | 0% | 0.657% | 0.657% | 0.657% | 0.657% | 0.657% | 0.657% | 0.657% | 0.657% | 0.657% | 0.657% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CAPEX Improved FO + MO (%) |  |  |  | 28.65% | 27.93% | 28.45% | 28.55% | 30.21% | 30.21% | 30.21% | 30.21% | 30.21% | 30.21% | 30.21% | 30.21% | 30.21% | 30.21% | 30.21% | 30.21% | 30.21% | 30.21% | 30.21% | 30.21% | 30.21% | 0% | 0% | 0%
Output - Option Load |  |  |  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044
Status Quo Output (MW) |  |  |  | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380
Incremental Change Due to CAPEX |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CAPEX Improved Output |  |  |  | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380
Output - Base Load |  |  |  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044
Status Quo Output (MW) |  |  |  | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410
Incremental Change Due to CAPEX |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CAPEX Improved Output |  |  |  | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410
Heat Rate Average |  |  |  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044
Status Quo Incremental Heat Rate |  |  |  | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633
Direct Heat Rate Improvement Due To Change in Plant Efficiency |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indirect Heat Rate Improvement Due To Output Improvement | OPTION | ON |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Incremental Change Due to CAPEX |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CAPEX Improved Heat Rate |  |  |  | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633
Scheduled Outage Impact | time axis 2021-01-15 to 2041-12-15
Status Quo Scheduled Outage Days |  |  |  | 0 | 0 | 26 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 31 | 30 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 31 | 30 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 30 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 31 | 30 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 31 | 30 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 30 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Incremental Change Due to CAPEX |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CAPEX Improved Scheduled Outage (Min 0) |  |  |  | 0 | 0 | 26 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 31 | 30 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 31 | 30 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 30 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 31 | 30 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 31 | 30 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 30 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fixed O&M Impacts (Enter as a negative if the incremental project saves O&M) |  |  |  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044
Maintenance/Start/Startup Fuel |  |  |  | 0 | 0 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outage Maintenance That will be avoided |  |  |  | 0 | 0 | -128.198 | -128.198 | -128.198 | -128.198 | -128.198 | -128.198 | -128.198 | -128.198 | -128.198 | -128.198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Type in Item 3 Savings |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  | 0 | 0 | -64.198 | -64.198 | -64.198 | -64.198 | -64.198 | -64.198 | -64.198 | -64.198 | -64.198 | -64.198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044
Book Depreciation Impact
Book Depreciation Increase of New Equipment |  |  |  | 0 | 0 | 118.5 | 118.5 | 118.5 | 118.5 | 118.5 | 118.5 | 118.5 | 118.5 | 118.5 | 118.5 | 118.5 | 118.5 | 118.5 | 118.5 | 118.5 | 118.5 | 118.5 | 118.5 | 118.5 | 118.5 | 118.5 | 118.5
Book Depreciation Decrease of Old Equipment |  |  |  | -17.3595 | -17.3419 | -17.2974 | -17.0972 | -16.9307 | -16.8656 | -16.7769 | -16.7142 | -16.6428 | -16.52 | -16.3818 | -16.2542 | -16.1482 | -15.4643 | -13.0448 | -4.7083 | -4.5683 | -4.1808 | -3.8355 | -3.7172 | -3.2624 | -1.3258 | -0.52152 | -0.32412
Net Book depreciation Impact of Improvement Project |  |  |  | -17.3595 | -17.3419 | 101.2026 | 101.4028 | 101.5693 | 101.6344 | 101.7231 | 101.7858 | 101.8572 | 101.98 | 102.1182 | 102.2458 | 102.3518 | 103.0357 | 105.4552 | 113.7917 | 113.9317 | 114.3192 | 114.6645 | 114.7828 | 115.2376 | 117.1742 | 117.9785 | 118.1759
For Sensitivity Table Calculation Only
CAPEX Value
| 0 |  | 5 Year IRR | 2021: 10 Year IRR; 2022: 15 Year IRR
|  |  | 71.77% | 2021: 86.33%; 2022: 86.77%; 2024: MW
Mitchell 2 |  |  | 5047.2518 | 2021: 9287.8814; 2022: 12272.442; 2024: 790
GM
Improvement
EFOR | 1% | 1%
MW Addition (1 MW) | 0 | 1
HR improvement (0.1 HR) | 0 | -0.1
NOX (0.1) | 0 | 0.1
SO2 (0.1) | 0 | 0.1
FOM | 0 | -100
Minload reduction (1 MW) | 0 | 1
0
ON
OFF
Goal Seek 5 Yr
Goal Seek 10 Yr
Goal Seek 15 Yr
Note on A47: s141220: The Cash Flow Associated With this is included with equity cost of plant improvement
Note on A97: s141220: Rate per Jeff Chatas

## ML2 Hydrated Lime Summary
Project: ML2 Hydrated Lime Conversion Including Fuel Impact
Plant Profile
Capital Project Description: | [6 empty] | Unit Profile | [15 empty] | Project Economic Results | [7 empty] | Active Plant | Mitchell 1-2
This project will reconfigure the existing dry sorbent injection (DSI) system to more efficiently handle hydrated lime and reduce issues related to corrosion as well as gain benefits such as heat rate improvement, improved Equivalent Unplanned Outage Rate (EUOR) and a lower minimum load.Mitchell Plant currently uses trona for SO3 mitigation and injects at the air heater (AH) outlet. Significant benefits can be realized by removing SO3 at the Selective Catalytic Reduction (SCR) inlet as compared to the AH outlet. Executing this project will allow the units to have lower minimum load, improved heat rate, sorbent dispersion and EUOR. It also helps with the long term protection of the SCR catalyst, air heaters and precipitators. By protecting the equipment from high concentrations of acid gas we are able to delay basket change out, catalyst changes, ducting and fan hubs. The first phase includes the engineering and procurement for the project. Phase 2 will include the expenses associated with the actual construction and closeout. The total cost of all phases is projected to be $7.9M. | [6 empty] | Active Unit |  | Mitchell 2 | [21 empty] | Reg. / Dereg. | Deregulated
[7 empty] | Year In Service |  | 1971 | [21 empty] | Operating Company | KPC
[7 empty] | Annual Max Output Rating |  | 790 | [21 empty] | State | WV
[7 empty] | Minimum Unit Turndown (Non-SCR) |  | 410 | [21 empty] | NERC Region | ECAR
[7 empty] | Summer Capacity Derate (%) |  | 0% | [21 empty] | Primary Fuel | Coal
[7 empty] | Average Full-Load Unit Heat Rate |  | 9.8561 | [21 empty] | Size MW | 1600
[7 empty] | Heat Rate at Min Capacity Rating |  | 10.3129 | [21 empty] | Ownership % | 100%
[7 empty] | Heat Rate for Option Load |  | 9.3633 | [21 empty] | Power Curve | AEP
[7 empty] | NOX Control HR Derate |  | 0% | [21 empty] | Curve Date | 2020-01-01
Alternatives Considered: | [6 empty] | Beginning SO2 Rate - lbs/mmbtu |  | 3.9725 | [21 empty] | Fuel Basis Curve | COAL
Modify the existing Mitchell Unit 2 trona injection system to handle lime vs. do-nothing and continue to use the existing trona injection system. | [6 empty] | Coal Switch SO2 Rate |  | 3.9725 | [21 empty] | Major Pipeline | NONE
[7 empty] | Date of SO2 Control |  | 2007-01-01 | [21 empty] | LDC Chrg. | 0
[7 empty] | Full Load Nox Rate |  | 0.6 | [21 empty] | Vol Measure | 16xCIN
[7 empty] | Control Nox Rate Full Load |  | 0.045 | [21 empty] | Correlation | 25%
[7 empty] | First Month of Nox Control |  | 2007-01-01
Simulation Results:
Parameters Which Vary In Simulation:
Summary of Economic Analysis: | [6 empty] | Project Capital Costs($000) | [25 empty] | Input Variable | Distribution | Mean | S.D. | Min Value | Max Value
Modifying the existing Mitchell Unit 2 trona injection system to handle lime and switching to a 100% high-sulphur coal during off-peak hours results in a 10-year IRR of 86% and a 10-year NPV of $24.8 million versus doing nothing and continuing to use the existing trona injection system. The simple payback is 2.9 years from the first project spend in 2021. A sensitivity analysis of modifying the existing Mitchell Unit 2 trona injection system to handle lime and continuing to burn the 60% HS and 40% LS blend at all times results in a 10-year IRR of 54% and a 10-year NPV of $12.5 million versus doing nothing and continuing to use the existing trona injection system. The simple payback is 3.6 years from the first project spend in 2021. | [7 empty] | 2020 | 2021 | 2022 | 2023 | 2024 | Total | [19 empty] | Capital Cost
[7 empty] | Install Material | 0 | 1817 | 2133 | 0 | 0 | 3950 | [19 empty] | EFOR
[7 empty] | Install Labor | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | Heat Rate Impact
[7 empty] | Install FODA | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | Net Output Impact
[7 empty] | Contingency | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | Power Curve Adder
[7 empty] | Removal Material | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Removal Labor | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Removal FODA | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Other | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | AFUDC | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Total Direct Cost | 0 | 1817 | 2133 | 0 | 0 | 3950
[7 empty] | Overheads | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Stores | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Total BurdenedCost | 0 | 1817 | 2133 | 0 | 0 | 3950
Economic Results:
| NPV ($000s) | IRR
5 Year | 7528.3144 | 71.77%
10 Year | 24805.5562 | 86.33%
15 Year | 31196.6023 | 86.77%
20 Year | 31722.773 | 86.77%
Simple Payback (Years): |  | 2.8625
Discount Rate for NPV calculation: |  | 6.697%
Summary of Expected Benefits:
| EFOR (%) | O&M ($000s) | Heat Rate (MMBtu/MWh) | Output (MW) | Change in Gross Margin ($000s) | After-tax Cash Flows ($000s)
2021 | 0% | 0 | 0 | 0 | 0 | -1817
2022 | 0% | 0 | 0 | 0 | 0 | -2133
2023 | 0.657% | -64.198 | 0 | 0 | 6099.8168 | 4579.8796
2024 | 0.657% | -64.198 | 0 | 0 | 6034.9967 | 4568.0357
2025 | 0.657% | -64.198 | 0 | 0 | 6992.5269 | 5269.9357
2026 | 0.657% | -64.198 | 0 | 0 | 7119.0824 | 5358.4397
2027 | 0.657% | -64.198 | 0 | 0 | 6539.852 | 4925.9881
2028 | 0.657% | -64.198 | 0 | 0 | 7741.447 | 5809.2885
2029 | 0.657% | -64.198 | 0 | 0 | 8496.901 | 6363.3661
2030 | 0.657% | -64.198 | 0 | 0 | 8978.1561 | 6715.2022
Data Field For Graphs
Power Price Vs Dispatch
[11 empty] | 2021 | 2022 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041
[7 empty] | Around-The-Clock Power Price ($/Mwh) |  |  |  | 21.4063 | 22.2947 | 25.8935 | 27.0468 | 28.3198 | 29.7954 | 30.9802 | 31.256 | 31.505 | 30.9488 | 31.2852 | 32.3191 | 33.2476 | 34.0289 | 34.6474 | 36.046 | 37.48 | 38.0177 | 39.1082 | 0
[7 empty] | Annual Dispatchable Power Cost - Option Load ($/Mwh) |  |  |  | 25.6744 | 24.2898 | 23.0769 | 23.8254 | 24.1904 | 25.1861 | 26.0605 | 27.4219 | 28.7806 | 30.6491 | 32.1844 | 34.8266 | 35.1675 | 36.5111 | 37.3373 | 38.2711 | 39.1172 | 40.0201 | 40.5342 | 0
[7 empty] | Annual Dispatchable Power Cost - Base Load ($/Mwh) |  |  |  | 27.742 | 26.2063 | 21.6142 | 22.305 | 22.6501 | 23.5738 | 24.3854 | 25.6472 | 26.9087 | 28.6414 | 30.0663 | 37.4619 | 37.8194 | 39.2809 | 40.1723 | 41.1817 | 42.0942 | 43.069 | 43.615 | 0
[7 empty] | Nox Curve |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unit Gross Margins
[7 empty] | Annual option Load Gross Margin |  |  |  | -4.2681 | -1.9951 | 2.8166 | 3.2214 | 4.1295 | 4.6093 | 4.9198 | 3.8341 | 2.7244 | 0.29964 | -0.89927 | -2.5075 | -1.9199 | -2.4821 | -2.6899 | -2.2251 | -1.6372 | -2.0024 | -1.426 | 0
[7 empty] | Annual Base Load Gross Margin |  |  |  | -6.3357 | -3.9115 | 4.2793 | 4.7417 | 5.6697 | 6.2216 | 6.5948 | 5.6089 | 4.5963 | 2.3074 | 1.2188 | -5.1428 | -4.5718 | -5.252 | -5.5249 | -5.1357 | -4.6142 | -5.0512 | -4.5068 | 0
Forced & Maintenance Outage
[11 empty] | 2021 | 2022 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029
[7 empty] | Status Quo FO + MO (%) |  |  |  | 28.65% | 27.93% | 27.89% | 29.55% | 29.55% | 29.55% | 29.55% | 29.55%
[7 empty] | CAPEX Improved FO + MO (%) |  |  |  | 28.65% | 27.93% | 28.55% | 30.21% | 30.21% | 30.21% | 30.21% | 30.21%
[7 empty] | Net output Change |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Heat Rate Effects
[7 empty] | Status Quo Incremental Heat Rate |  |  |  | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633
[7 empty] | CAPEX Improved Heat Rate |  |  |  | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633 | 9.3633
Fixed O&M Impact
[11 empty] | 0 | 0 | -64.198 | -64.198 | -64.198 | -64.198 | -64.198 | -64.198
[7 empty] | Project IRR |  |  |  | 2021 | 2022 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041
[14 empty] | 71.77% | 79.53% | 82.82% | 84.72% | 85.77% | 86.33% | 86.62% | 86.76% | 86.76% | 86.77% | 86.77% | 86.77% | 86.77% | 86.77% | 86.77% | 86.77% | 86.77%
EPS Accretion/Dilution
[11 empty] | 2.5831e-05 | 2.5805e-05 | 0.0083337 | 0.0097476 | 0.0099248 | 0.0090516 | 0.010828 | 0.01194 | 0.012656 | 0.012291 | 0.011679 | -0.00039599 | -0.00033248 | -0.0003152 | -0.00031549 | -0.00030808 | -0.00018293 | -0.00021132 | -0.00012052 | -0.00081823
[9 empty] | Obs |  | 0 2021: Project NPV 9%; 0 2022: IRR - 10 YR; -64.198 2025: NPV; -64.198 2030: IRR - 10 Yr; -64.198 2035: Payback Years
[9 empty] | 1 |  |  |  |  | Min Increment | 100 | #DIV/0! | 0 |  | Min Increment | 2% | #DIV/0! | 0 |  | Min Increment | 1 | #REF! | #REF!
[9 empty] | 2 |  |  |  |  | Min | 0 | #DIV/0! | 0 |  | Min | 0% | #DIV/0! | 0 |  | Min | #REF! | #REF! | #REF!
[9 empty] | 3 |  |  |  |  | Max | 0 | #DIV/0! | #N/A |  | Max | 0% | #DIV/0! | #N/A |  | Max | #REF! | #REF! | #REF!
[9 empty] | 4 |  |  |  |  | Ticks | 20 | #DIV/0! | #N/A |  | Ticks | 20 | #DIV/0! | #N/A |  | Ticks | 50 | #REF! | #REF!
[9 empty] | 5 |  |  |  |  | Range | 0 | #DIV/0! | #N/A |  | Range | 0% | #DIV/0! | #N/A |  | Range | #REF! | #REF! | #REF!
[9 empty] | 6 |  |  |  |  | Average | 0 | #DIV/0! | #N/A |  | Average | 0% | #DIV/0! | #N/A |  | Average | #REF! | #REF! | #REF!
[9 empty] | 7 |  |  |  |  | Scaled Mid-point | #DIV/0! | #DIV/0! | #N/A |  | Scaled Mid-point | #DIV/0! | #DIV/0! | #N/A |  | Scaled Mid-point | #REF! | #REF! | #REF!
[9 empty] | 8 |  |  |  |  | Increment | 0 | #DIV/0! | #N/A |  | Increment | 0% | #DIV/0! | #N/A |  | Increment | #REF! | #REF! | #REF!
[9 empty] | 9 |  |  |  |  | Scaled Min | #DIV/0! | #DIV/0! | #N/A |  | Scaled Min | #DIV/0! | #DIV/0! | #N/A |  | Scaled Min | #REF! | #REF! | #REF!
[9 empty] | 10 |  |  |  |  | Scaled Max | #DIV/0! | #DIV/0! | #N/A |  | Scaled Max | #DIV/0! | #DIV/0! | #N/A |  | Scaled Max | #REF! | #REF! | #REF!
[9 empty] | 11 |  |  |  |  | Percentage >= 0 | #N/A | #DIV/0! | #N/A |  | Percentage >= 0 | #N/A | #DIV/0! | #N/A |  | Percentage >= 0 | #REF! | #REF! | #REF!
[9 empty] | 12 |  |  |  |  | Total Count | #N/A | #DIV/0! | #N/A |  | Total Count | #N/A | #DIV/0! | #N/A |  | Total Count | #REF! | #REF! | #REF!
[9 empty] | 13 |  | -64.198 2027: #DIV/0!; -64.198 2028: #N/A; -64.198 2032: #DIV/0!; -64.198 2033: #N/A; -64.198 2037: #REF!; -64.198 2038: #REF!
[9 empty] | 14 |  | -64.198 2027: #DIV/0!; -64.198 2028: #N/A; -64.198 2032: #DIV/0!; -64.198 2033: #N/A; -64.198 2037: #REF!; -64.198 2038: #REF!
[9 empty] | 15 |  | -64.198 2027: #DIV/0!; -64.198 2028: #N/A; -64.198 2032: #DIV/0!; -64.198 2033: #N/A; -64.198 2037: #REF!; -64.198 2038: #REF!
[9 empty] | 16 |  | -64.198 2027: #DIV/0!; -64.198 2028: #N/A; -64.198 2032: #DIV/0!; -64.198 2033: #N/A; -64.198 2037: #REF!; -64.198 2038: #REF!
[9 empty] | 17 |  | -64.198 2027: #DIV/0!; -64.198 2028: #N/A; -64.198 2032: #DIV/0!; -64.198 2033: #N/A; -64.198 2037: #REF!; -64.198 2038: #REF!
[9 empty] | 18 |  | -64.198 2027: #DIV/0!; -64.198 2028: #N/A; -64.198 2032: #DIV/0!; -64.198 2033: #N/A; -64.198 2037: #REF!; -64.198 2038: #REF!
[9 empty] | 19 |  | -64.198 2027: #DIV/0!; -64.198 2028: #N/A; -64.198 2032: #DIV/0!; -64.198 2033: #N/A; -64.198 2037: #REF!; -64.198 2038: #REF!
[9 empty] | 20 |  | -64.198 2027: #DIV/0!; -64.198 2028: #N/A; -64.198 2032: #DIV/0!; -64.198 2033: #N/A; -64.198 2037: #REF!; -64.198 2038: #REF!
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
Copy Summary Page to Blank Workbook
Print Summary

## ML2 Hydrated Lime Performance
AEP Unit Valuation
Performance
Performance by Unit
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
| 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
Unit Mitchell 2 - Base Case
Max Hourly MW | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790
Annual Unit Availability Factor | 63.98% | 57.65% | 69.1% | 58.08% | 67.42% | 67.32% | 59.28% | 67.32% | 67.32% | 67.04% | 63.18% | 56.38% | 66.79% | 56.18% | 66.79% | 66.69% | 58.72% | 66.69% | 66.69% | 66.42%
Annual Unit Capacity Factor - Scalars | 4.569% | 14.12% | 37.27% | 47.19% | 54.82% | 55.82% | 49.5% | 56.33% | 55.25% | 49.5% | 37.96% | 32% | 27.41% | 31.37% | 32% | 32.17% | 32.28% | 37.19% | 37.17% | 41.95%
Net Annual Unit Output (GWH)-Scalars | 316.1913 | 977.1038 | 2579.161 | 3265.4191 | 3793.9921 | 3862.8398 | 3425.3048 | 3898.0465 | 3823.5559 | 3425.5124 | 2626.7964 | 2214.3025 | 1896.7402 | 2170.9601 | 2214.2841 | 2226.0427 | 2233.8944 | 2574.0115 | 2571.9823 | 2903.14
Base Load | 217.641 | 659.5244 | 1719.4828 | 2093.1313 | 2419.3478 | 2419.3478 | 2128.1942 | 2426.2801 | 2419.3478 | 2197.5165 | 1712.2605 | 1448.8358 | 1249.8995 | 1421.589 | 1455.9269 | 1462.7945 | 1455.9269 | 1668.8219 | 1668.8219 | 1881.7169
Option Load | 98.5504 | 317.5793 | 859.6782 | 1172.2878 | 1374.6442 | 1443.492 | 1297.1106 | 1471.7665 | 1404.2081 | 1227.9959 | 914.5359 | 765.4667 | 646.8407 | 749.3711 | 758.3571 | 763.2482 | 777.9674 | 905.1896 | 903.1604 | 1021.4231
Nox Season Unit Output (GWH) | 316.1913 | 651.9305 | 1302.4438 | 1638.5311 | 1506.1516 | 1690.2607 | 1601.2211 | 1702.7597 | 1668.0624 | 1455.267 | 1284.0711 | 966.3781 | 948.8805 | 953.5603 | 950.712 | 950.43 | 958.0759 | 968.3935 | 965.1739 | 1276.1267
Base Load | 217.641 | 439.683 | 866.8467 | 1050.1133 | 949.7153 | 1060.631 | 998.2409 | 1060.631 | 1060.631 | 935.8509 | 845.7319 | 637.765 | 631.8174 | 631.8174 | 631.8174 | 631.8174 | 631.8174 | 631.8174 | 631.8174 | 837.8448
Option Load | 98.5504 | 212.2476 | 435.5971 | 588.4177 | 556.4363 | 629.6297 | 602.9801 | 642.1287 | 607.4314 | 519.4162 | 438.3392 | 328.6131 | 317.0631 | 321.7429 | 318.8947 | 318.6127 | 326.2586 | 336.5762 | 333.3566 | 438.2819
Non Nox Season Unit Output (GWH) | 0 | 325.1733 | 1276.7172 | 1626.888 | 2287.8405 | 2172.5791 | 1824.0837 | 2195.2868 | 2155.4936 | 1970.2454 | 1342.7253 | 1247.9244 | 947.8598 | 1217.3998 | 1263.572 | 1275.6127 | 1275.8185 | 1605.618 | 1606.8084 | 1627.0133
Base Load | 0 | 219.8415 | 852.6361 | 1043.018 | 1469.6325 | 1358.7168 | 1129.9533 | 1365.6491 | 1358.7168 | 1261.6656 | 866.5286 | 811.0708 | 618.0822 | 789.7717 | 824.1096 | 830.9772 | 824.1096 | 1037.0046 | 1037.0046 | 1043.8721
Option Load | 0 | 105.3318 | 424.0811 | 583.8701 | 818.208 | 813.8622 | 694.1304 | 829.6377 | 796.7767 | 708.5797 | 476.1967 | 436.8536 | 329.7776 | 427.6281 | 439.4625 | 444.6356 | 451.7089 | 568.6134 | 569.8038 | 583.1412
Annual Fuel Consumption (000mmbtu) | 3167.264 | 9775.194 | 25782.2625 | 32562.7142 | 37821.673 | 38466.314 | 34093.0659 | 38802.5476 | 38098.4877 | 34160.839 | 26221.4281 | 22108.9788 | 18946.64 | 21677.2774 | 22115.5398 | 22232.1612 | 22299.1568 | 25685.9381 | 25666.9382 | 28969.8297
Nox Season Fuel Consumption (000mmbtu) | 3167.264 | 9775.194 | 25782.2625 | 32562.7142 | 37821.673 | 38466.314 | 34093.0659 | 38802.5476 | 38098.4877 | 34160.839 | 26221.4281 | 22108.9788 | 18946.64 | 21677.2774 | 22115.5398 | 22232.1612 | 22299.1568 | 25685.9381 | 25666.9382 | 28969.8297
Base Load | 2244.5087 | 6801.6076 | 17732.8491 | 21586.2475 | 24950.4847 | 24950.4847 | 21947.8476 | 25021.9761 | 24950.4847 | 22662.7612 | 17658.366 | 14941.6943 | 12890.0852 | 14660.7013 | 15014.8245 | 15085.6491 | 15014.8245 | 17210.3884 | 17210.3884 | 19405.9524
Option Load | 922.7552 | 2973.5864 | 8049.4134 | 10976.4667 | 12871.1882 | 13515.8293 | 12145.2184 | 13780.5715 | 13148.003 | 11498.0778 | 8563.0621 | 7167.2846 | 6056.5548 | 7016.5762 | 7100.7154 | 7146.512 | 7284.3323 | 8475.5497 | 8456.5497 | 9563.8773
Annual Nox Emissions (Tons) | 71.2634 | 219.9419 | 580.1009 | 732.6611 | 850.9876 | 865.4921 | 767.094 | 873.0573 | 857.216 | 768.6189 | 589.9821 | 497.452 | 426.2994 | 487.7387 | 497.5996 | 500.2236 | 501.731 | 577.9336 | 577.5061 | 651.8212
Base Load | 50.5014 | 153.0362 | 398.9891 | 485.6906 | 561.3859 | 561.3859 | 493.8266 | 562.9945 | 561.3859 | 509.9121 | 397.3132 | 336.1881 | 290.0269 | 329.8658 | 337.8336 | 339.4271 | 337.8336 | 387.2337 | 387.2337 | 436.6339
Option Load | 20.762 | 66.9057 | 181.1118 | 246.9705 | 289.6017 | 304.1062 | 273.2674 | 310.0629 | 295.8301 | 258.7068 | 192.6689 | 161.2639 | 136.2725 | 157.873 | 159.7661 | 160.7965 | 163.8975 | 190.6999 | 190.2724 | 215.1872
Annual Nox Removal (Tons) | 1391.5124 | 4294.6543 | 11327.2335 | 14306.1714 | 16616.6534 | 16899.8714 | 14978.5194 | 17047.5929 | 16738.2698 | 15008.2949 | 11520.1774 | 9713.4053 | 8324.0567 | 9523.7407 | 9716.2878 | 9767.5245 | 9796.9585 | 11284.9141 | 11276.5667 | 12727.666
Annual SO2 Emissions (Tons) | 209.175 | 718.3057 | 1917.7626 | 2335.4962 | 2706.9208 | 2754.124 | 2440.062 | 2777.6602 | 2726.2048 | 2445.8591 | 1860.5545 | 1568.7536 | 1344.3683 | 1538.1221 | 1569.2192 | 1577.4941 | 1582.2478 | 1822.5586 | 1821.2104 | 2055.5688
Annual SO2 Removal (Tons) | 5767.2541 | 19804.7141 | 52875.4537 | 64392.9674 | 74633.6727 | 75935.1324 | 67275.9962 | 76584.0586 | 75165.3597 | 67435.8305 | 51298.1467 | 43252.7792 | 37066.155 | 42408.2225 | 43265.6147 | 43493.7662 | 43624.8328 | 50250.5438 | 50213.3733 | 56674.9671
Annual CO2 Emissions (Tons) | 325119.6448 | 1003423.6616 | 2646549.2478 | 3342562.6104 | 3882394.7297 | 3948567.1357 | 3499653.2188 | 3983081.5078 | 3910809.7639 | 3506610.1221 | 2691629.5967 | 2269486.6781 | 1944872.5961 | 2225172.5302 | 2270160.165 | 2282131.3433 | 2289008.4476 | 2636661.5476 | 2634711.2045 | 297375.3023
Annual CO2 Removal (Tons) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2676377.7207
Annual Hg Emissions (lbs) | 22.0442 | 68.0354 | 179.4445 | 226.6365 | 263.2388 | 267.7255 | 237.2877 | 270.0657 | 265.1655 | 237.7594 | 182.5011 | 153.8785 | 131.8686 | 150.8739 | 153.9242 | 154.7358 | 155.2021 | 178.7741 | 178.6419 | 201.63
Annual Hg Removal (lbs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Annual Dispatchable Power Cost - Option Load ($/Mwh) | 25.6744 | 24.2898 | 23.4102 | 23.3685 | 24.1247 | 24.4949 | 25.5001 | 26.383 | 27.7564 | 29.1269 | 31.0108 | 32.5592 | 34.8266 | 35.1675 | 36.5111 | 37.3373 | 38.2711 | 39.1172 | 40.0201 | 40.5342
Annual Dispatchable Power Cost - Base Load ($/Mwh) | 27.742 | 26.2063 | 25.2265 | 25.1694 | 25.9909 | 26.387 | 27.4823 | 28.4428 | 29.9431 | 31.4401 | 33.5021 | 35.1946 | 37.6786 | 38.0405 | 39.5064 | 40.4023 | 41.4163 | 42.3335 | 43.313 | 43.864
Annual Average Dispatchable Power Cost - ($/Mwh) | 27.0976 | 25.5834 | 24.6211 | 24.5229 | 25.3147 | 25.68 | 26.7317 | 27.6651 | 29.14 | 30.6109 | 32.6347 | 34.2836 | 36.706 | 37.0488 | 38.4805 | 39.3514 | 40.3209 | 41.2024 | 42.1567 | 42.6925
Summer Dispatchable Power Cost - Option Load ($/Mwh) | 25.6744 | 24.2898 | 23.4102 | 23.3685 | 24.1247 | 24.4949 | 25.5001 | 26.383 | 27.7564 | 29.1269 | 31.0108 | 32.5592 | 34.8266 | 35.1675 | 36.5111 | 37.3373 | 38.2711 | 39.1172 | 40.0201 | 40.5342
Summer Dispatchable Power Cost - Base Load ($/Mwh) | 27.742 | 26.2063 | 25.2265 | 25.1694 | 25.9909 | 26.387 | 27.4823 | 28.4428 | 29.9431 | 31.4401 | 33.5021 | 35.1946 | 37.6786 | 38.0405 | 39.5064 | 40.4023 | 41.4163 | 42.3335 | 43.313 | 43.864
Summer Average Dispatchable Power Cost - ($/Mwh) | 27.0976 | 25.5823 | 24.6191 | 24.5227 | 25.3014 | 25.6822 | 26.7359 | 27.666 | 29.1468 | 30.6145 | 32.6517 | 34.2985 | 36.7257 | 37.0711 | 38.5017 | 39.3748 | 40.3452 | 41.2156 | 42.1757 | 42.7204
Winter Dispatchable Power Cost ($/MWh) - Option Load | 25.6744 | 24.2898 | 23.4102 | 23.3685 | 24.1247 | 24.4949 | 25.5001 | 26.383 | 27.7564 | 29.1269 | 31.0108 | 32.5592 | 34.8266 | 35.1675 | 36.5111 | 37.3373 | 38.2711 | 39.1172 | 40.0201 | 40.5342
Winter Dispatchable Power Cost ($/MWh) - Base Load | 27.742 | 26.2063 | 25.2265 | 25.1694 | 25.9909 | 26.387 | 27.4823 | 28.4428 | 29.9431 | 31.4401 | 33.5021 | 35.1946 | 37.6786 | 38.0405 | 39.5064 | 40.4023 | 41.4163 | 42.3335 | 43.313 | 43.864
Winter Average Dispatchable Power Cost - ($/Mwh) | 27.742 | 25.5855 | 24.6232 | 24.5231 | 25.3235 | 25.6782 | 26.728 | 27.6644 | 29.1348 | 30.6082 | 32.6186 | 34.2721 | 36.6864 | 37.0313 | 38.4646 | 39.3339 | 40.3027 | 41.1945 | 42.1453 | 42.6706
Unit Mitchell 2 - Change Case
Max Hourly MW | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790 | 790
Annual Unit Availability Factor | 63.98% | 57.65% | 68.47% | 57.55% | 66.79% | 66.69% | 58.72% | 66.69% | 66.69% | 66.42% | 62.59% | 55.86% | 66.79% | 56.18% | 66.79% | 66.69% | 58.72% | 66.69% | 66.69% | 66.42%
Annual Unit Capacity Factor | 4.569% | 14.12% | 40.23% | 43.94% | 51.14% | 52.38% | 46.56% | 52.95% | 51.63% | 50.06% | 45.42% | 36.37% | 27.41% | 31.37% | 32% | 32.17% | 32.28% | 41.58% | 37.17% | 41.95%
Net Annual Unit Output (GWH) | 316.1913 | 977.1038 | 2784.1814 | 3040.6047 | 3539.1241 | 3625.0913 | 3222.0176 | 3664.1565 | 3573.0635 | 3464.4927 | 3143.3427 | 2517.1246 | 1896.7402 | 2170.9601 | 2214.2841 | 2226.0427 | 2233.8944 | 2877.2424 | 2571.9823 | 2903.14
Annual Fuel Consumption (000mmbtu) | 3167.264 | 9775.194 | 27325.8003 | 29743.9262 | 34608.3988 | 35408.176 | 31455.7372 | 35776.4331 | 34924.1468 | 33904.4365 | 30820.2447 | 24680.9218 | 18946.64 | 21677.2774 | 22115.5398 | 22232.1612 | 22299.1568 | 28720.8212 | 25666.9382 | 28969.8297
Nox Season Fuel Consumption (000mmbtu) | 3167.264 | 9775.194 | 27325.8003 | 29743.9262 | 34608.3988 | 35408.176 | 31455.7372 | 35776.4331 | 34924.1468 | 33904.4365 | 30820.2447 | 24680.9218 | 18946.64 | 21677.2774 | 22115.5398 | 22232.1612 | 22299.1568 | 28720.8212 | 25666.9382 | 28969.8297
Base Load | 2244.5087 | 6801.6076 | 15226.9436 | 15575.0218 | 17998.5084 | 17998.5084 | 15832.4988 | 18050.08 | 17998.5084 | 17895.365 | 16863.9319 | 13511.7742 | 12890.0852 | 14660.7013 | 15014.8245 | 15085.6491 | 15014.8245 | 19335.1278 | 17210.3884 | 19405.9524
Option Load | 922.7552 | 2973.5864 | 12098.8567 | 14168.9044 | 16609.8904 | 17409.6677 | 15623.2385 | 17726.3531 | 16925.6384 | 16009.0714 | 13956.3128 | 11169.1476 | 6056.5548 | 7016.5762 | 7100.7154 | 7146.512 | 7284.3323 | 9385.6935 | 8456.5497 | 9563.8773
Annual Nox Emissions (Tons) | 71.2634 | 219.9419 | 614.8305 | 669.2383 | 778.689 | 796.684 | 707.7541 | 804.9697 | 785.7933 | 762.8498 | 693.4555 | 555.3207 | 426.2994 | 487.7387 | 497.5996 | 500.2236 | 501.731 | 646.2185 | 577.5061 | 651.8212
Base Load | 50.5014 | 153.0362 | 342.6062 | 350.438 | 404.9664 | 404.9664 | 356.2312 | 406.1268 | 404.9664 | 402.6457 | 379.4385 | 304.0149 | 290.0269 | 329.8658 | 337.8336 | 339.4271 | 337.8336 | 435.0404 | 387.2337 | 436.6339
Option Load | 20.762 | 66.9057 | 272.2243 | 318.8003 | 373.7225 | 391.7175 | 351.5229 | 398.8429 | 380.8269 | 360.2041 | 314.017 | 251.3058 | 136.2725 | 157.873 | 159.7661 | 160.7965 | 163.8975 | 211.1781 | 190.2724 | 215.1872
Annual Nox Removal (Tons) | 1391.5124 | 4294.6543 | 12005.3746 | 13067.7592 | 15204.9268 | 15556.3026 | 13819.8298 | 15718.0934 | 15343.6482 | 14895.6465 | 13540.6312 | 10843.3681 | 8324.0567 | 9523.7407 | 9716.2878 | 9767.5245 | 9796.9585 | 12618.2661 | 11276.5667 | 12727.666
Annual SO2 Emissions (Tons) | 209.175 | 718.3057 | 3037.6665 | 3254.1363 | 3873.8261 | 3892.0089 | 3464.939 | 3932.9427 | 3841.4281 | 3802.6627 | 3368.8447 | 2680.6787 | 1344.3683 | 1538.1221 | 1569.2192 | 1577.4941 | 1582.2478 | 2037.9002 | 1821.2104 | 2055.5688
Annual SO2 Removal (Tons) | 5767.2541 | 19804.7141 | 83752.8036 | 89721.1877 | 106806.9199 | 107308.2467 | 95533.3184 | 108436.8492 | 105913.6599 | 104844.8444 | 92883.8605 | 73910.1411 | 37066.155 | 42408.2225 | 43265.6147 | 43493.7662 | 43624.8328 | 56187.8206 | 50213.3733 | 56674.9671
Annual CO2 Emissions (Tons) | 325119.6448 | 1003423.6616 | 2804993.3967 | 3053214.0274 | 3552552.1317 | 3634649.2683 | 3228931.425 | 3672450.8589 | 3584963.6668 | 3480290.4019 | 3163698.1216 | 2533496.619 | 1944872.5961 | 2225172.5302 | 2270160.165 | 2282131.3433 | 2289008.4476 | 2948192.2984 | 2634711.2045 | 297375.3023
Annual CO2 Removal (Tons) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2676377.7207
Annual Hg Emissions (lbs) | 22.0442 | 68.0354 | 190.1876 | 207.0177 | 240.8745 | 246.4409 | 218.9319 | 249.004 | 243.0721 | 235.9749 | 214.5089 | 171.7792 | 131.8686 | 150.8739 | 153.9242 | 154.7358 | 155.2021 | 199.8969 | 178.6419 | 201.63
Annual Hg Removal (lbs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Annual Dispatchable Power Cost - Option Load ($/Mwh) | 25.6744 | 24.2898 | 23.1212 | 23.0769 | 23.8254 | 24.1904 | 25.1861 | 26.0605 | 27.4219 | 28.7806 | 30.6491 | 32.1844 | 34.8266 | 35.1675 | 36.5111 | 37.3373 | 38.2711 | 39.1172 | 40.0201 | 40.5342
Annual Dispatchable Power Cost - Base Load ($/Mwh) | 27.742 | 26.2063 | 21.6516 | 21.6142 | 22.305 | 22.6501 | 23.5738 | 24.3854 | 25.6472 | 26.9087 | 28.6414 | 30.0663 | 37.4619 | 37.8194 | 39.2809 | 40.1723 | 41.1817 | 42.0942 | 43.069 | 43.615
Annual option Load Gross Margin | -4.2681 | -1.9951 | 0.31444 | 2.8166 | 3.2214 | 4.1295 | 4.6093 | 4.9198 | 3.8341 | 2.7244 | 0.29964 | -0.89927 | -2.5075 | -1.9199 | -2.4821 | -2.6899 | -2.2251 | -1.6372 | -2.0024 | -1.426
Annual Base Load Gross Margin | -6.3357 | -3.9115 | 1.784 | 4.2793 | 4.7417 | 5.6697 | 6.2216 | 6.5948 | 5.6089 | 4.5963 | 2.3074 | 1.2188 | -5.1428 | -4.5718 | -5.252 | -5.5249 | -5.1357 | -4.6142 | -5.0512 | -4.5068

## ML2 Hydrated Lime Assumptions
Hydrated Lime Conversion Project |  |  | 3% | assumed sorbent escalation rate
Economic Model Input Needs |  |  | Year
| ` |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
EPC Cash flow (annual) | $ |  | Year 1: 799355.1; Year 2: 3689140.8; Year 3: 559580.1; Year 4: 0; Year 5: 0; Year 6: 0; Year 7: 0; Year 8: 0; Year 9: 0; Year 10: 0
Delivered commodity cost - current | $/ton |  | 269 | 277.07 | 285.3821 | 293.9436 | 302.7619 | 311.8447 | 321.2001 | 330.8361 | 340.7612 | 350.984 | 361.5135 | 372.3589 | 383.5297 | 395.0356 | 406.8866 | 419.0932 | 431.666 | 444.616 | 457.9545 | 471.6931
Delivered commodity cost - new | $/ton | 0.62825 | 169 | 174.07 | 179.2921 | 184.6709 | 190.211 | 195.9173 | 201.7948 | 207.8487 | 214.0841 | 220.5067 | 227.1219 | 233.9355 | 240.9536 | 248.1822 | 255.6277 | 263.2965 | 271.1954 | 279.3312 | 287.7112 | 296.3425
Commodity Usage/Injection Rate |  | 0.62825
min load - current | #/mmbtu |  | 0.239 | 0.239 | 0.239 | 0.239 | 0.239 | 0.239 | 0.239 | 0.239 | 0.239 | 0.239 | 0.239 | 0.239 | 0.239 | 0.239 | 0.239 | 0.239 | 0.239 | 0.239 | 0.239 | 0.239
max load - current | #/mmbtu |  | 0.327 | 0.327 | 0.327 | 0.327 | 0.327 | 0.327 | 0.327 | 0.327 | 0.327 | 0.327 | 0.327 | 0.327 | 0.327 | 0.327 | 0.327 | 0.327 | 0.327 | 0.327 | 0.327 | 0.327
min load - new | #/mmbtu |  | 0.132 | 0.132 | 0.132 | 0.132 | 0.132 | 0.132 | 0.132 | 0.132 | 0.132 | 0.132 | 0.132 | 0.132 | 0.132 | 0.132 | 0.132 | 0.132 | 0.132 | 0.132 | 0.132 | 0.132
max load - new | #/mmbtu |  | 0.458 | 0.458 | 0.458 | 0.458 | 0.458 | 0.458 | 0.458 | 0.458 | 0.458 | 0.458 | 0.458 | 0.458 | 0.458 | 0.458 | 0.458 | 0.458 | 0.458 | 0.458 | 0.458 | 0.458
Heat rate/aux pwr impacts
Min Load - current | MW |  | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410 | 410
Min Load after modification | MW |  | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300
min load current | Btu/kWhr |  | 10127 | 10127 | 10127 | 10127 | 10127 | 10127 | 10127 | 10127 | 10127 | 10127 | 10127 | 10127 | 10127 | 10127 | 10127 | 10127 | 10127 | 10127 | 10127 | 10127
max load current | Btu/kWhr |  | 9696 | 9696 | 9696 | 9696 | 9696 | 9696 | 9696 | 9696 | 9696 | 9696 | 9696 | 9696 | 9696 | 9696 | 9696 | 9696 | 9696 | 9696 | 9696 | 9696
min load after modification | Btu/kWhr |  | 10079 | 10079 | 10079 | 10079 | 10079 | 10079 | 10079 | 10079 | 10079 | 10079 | 10079 | 10079 | 10079 | 10079 | 10079 | 10079 | 10079 | 10079 | 10079 | 10079
max load after modification | Btu/kWhr |  | 9668 | 9668 | 9668 | 9668 | 9668 | 9668 | 9668 | 9668 | 9668 | 9668 | 9668 | 9668 | 9668 | 9668 | 9668 | 9668 | 9668 | 9668 | 9668 | 9668
On going capital reqmts | $ |  | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000
On going annual maint savings | $ |  | 128198 | 128198 | 128198 | 128198 | 128198 | 128198 | 128198 | 128198 | 128198 | 128198 | 128198 | 128198 | 128198 | 128198 | 128198 | 128198 | 128198 | 128198 | 128198 | 128198
On going o&m annual incl CCR Impacts | $ |  | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000
Removal cost - min load | $/ton rem |  | Year 1: 194.2529; Year 2: 200.0805; Year 3: 206.0829; Year 4: 212.2654; Year 5: 218.6333; Year 6: 225.1923; Year 7: 231.9481; Year 8: 238.9065; Year 9: 246.0737; Year 10: 253.4559
Removal cost - full load | $/ton rem |  | Year 1: 454.3011; Year 2: 467.9301; Year 3: 481.968; Year 4: 496.4271; Year 5: 511.3199; Year 6: 526.6595; Year 7: 542.4592; Year 8: 558.733; Year 9: 575.495; Year 10: 592.7599
Incremental Outage Impact | days |  | Year 1: 0; Year 2: 0; Year 3: 0; Year 4: 0; Year 5: 0; Year 6: 0; Year 7: 0; Year 8: 0; Year 9: 0; Year 10: 0
Incremental EUOR Impact | % |  | 0.657 | 0.657 | 0.657 | 0.657 | 0.657 | 0.657 | 0.657 | 0.657 | 0.657 | 0.657 | 0.657 | 0.657 | 0.657 | 0.657 | 0.657 | 0.657 | 0.657 | 0.657 | 0.657 | 0.657
Questions (Answers from ko meeting 07/11/19)
1. Will there be equipment retirements from the old trona system? | bar: Year 2
2. What is the delivery method for hydrated lime? |  |  | Year 2: Same as Trona
3. Are there additional storage requirement parameters, (ie heat or humidity controls)? |  |  | Year 4: Yes
4. Can we switch back to trona if it makes sense? |  | Yes
5. Is this going before SCPB? | Yes
| Full Load $/mwh |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
| Current Incr HR (from SO Model) | 9.128 | 1: 9.219
| New Incr HR (from SO Model) | 9.121 | 1: 9.213
| max load - current | $/mwh | 0.40146 | 0.41351 | 0.42591 | 0.43869 | 0.45185 | 0.46541 | 0.47937 | 0.49375 | 0.50856 | 0.52382 | 0.53953 | 0.55572 | 0.57239 | 0.58956 | 0.60725 | 0.62547 | 0.64423 | 0.66356 | 0.68346 | 0.70397
| max load - new | $/mwh | 0.35299 | 0.36358 | 0.37449 | 0.38572 | 0.3973 | 0.40921 | 0.42149 | 0.43414 | 0.44716 | 0.46057 | 0.47439 | 0.48862 | 0.50328 | 0.51838 | 0.53393 | 0.54995 | 0.56645 | 0.58344 | 0.60094 | 0.61897
Min Load $/mwh
| Current HR | 9.977 | 1: 10.127
| New HR | 9.932 | 1: 10.079
| min load - current | $/mwh | 0.32072 | 0.33034 | 0.34025 | 0.35045 | 0.36097 | 0.3718 | 0.38295 | 0.39444 | 0.40627 | 0.41846 | 0.43102 | 0.44395 | 0.45726 | 0.47098 | 0.48511 | 0.49966 | 0.51465 | 0.53009 | 0.546 | 0.56238
| min load - new | $/mwh | 0.11078 | 0.1141 | 0.11753 | 0.12105 | 0.12469 | 0.12843 | 0.13228 | 0.13625 | 0.14033 | 0.14454 | 0.14888 | 0.15335 | 0.15795 | 0.16269 | 0.16757 | 0.17259 | 0.17777 | 0.1831 | 0.1886 | 0.19426