## Planned Outages 2025-2027
Kentucky Power Company Fuel Adjustment Clause Generating Planned Outages January 1,2025 -December 31, 2027
Unit Name | Estimated Start | Estimated End | Days | Executive Summary
Big Sandy 1 | 04/05/2025 00:00:00 | 04/13/2025 06:00:00 | 8 | Touchup Outage, Address Unit Liabilities, clean coolers and heat exchangers to get ready for Summer run.
Big Sandy 1 | 09/20/2025 00:00:00 | 11/02/2025 06:00:00 | 43 | Cooling Tower I/R, Upper Intercept RH Turbine Valves I/R, HP Turbine Governor Valves I/R, Furnace Wall I/R, BOP,
Mitchell 1 | 03/08/2025 00:00:00 | 06/06/2025 11:00:00 | 90 | Generator FO inspection (possible rotor replacement), SCR catalyst layer 1, MATS testing, BFPT rotor replacement, Clinker grinder/doghouse upgrade, 1RH/2RH SV/IV
Mitchell 2 | 09/06/2025 00:00:00 | 10/14/2025 00:00:00 | 38 | Boiler I/R, Generator FIP inspection, 1RH/2RH Combined Intercept/Stop Valve I/R, ID fan I/R, Plant Battery Replacement