## ReAnnounceVOH SEP 2024-Present
DAY | DATE | TIME (ET) | TYPE Phone/Voice Mail Email/US Mail In Person/Virtual Incoming/Outgoing | CONTACT VEHICLE or LOCATION | LO ID | MAP | TEAM MEMBER | NOTES Feedback Comments Questions | FOLLOW UP/ACTION ITEMS
FRI | 2024-09-06 |  | US Mail/Outgoing | Project Re-announcement Postcard |  |  |  | OH Invite postcard sent to all affected LO along the proposed route and new alternative route (183 landowners on mailing list)
MON | 2024-09-09 |  | US Mail/Outgoing | Project Re-announcement Packet |  |  |  | Mailing sent to all affected LO along the proposed route and the new alternative (183 landowners on the mailing list) - Cover letter - Project Overview Factsheet - Comment Card - Return address envelope
SUN | 2024-09-08 | 6:40pm | Email |  |  |  | Ryan Howell, ROW | [REDACTED] sent an email to RHowell requesting an update on both the Prestonsburg-Middle Creek and Prestonsburg-Thelma projects. | 09/10/2024: RHowell replied to [REDACTED]'s email to let him know all previous conversations and information have been entered into the record for both projects and to inform him that the Prestonsburg-Thelma project is being re-announced. [REDACTED] replied to indicate he had received the postcard in the mail and he was appreciative of the quick response. He stated he does not have any additional comments at this time, but will use the options on the postcard to submit them if he does.
THU | 2024-09-12 |  | Phone | [REDACTED] |  |  | Nancy Miller, ERM | [REDACTED] left a message on the project voicemail asking for a call back regarding the Pburg-Thelma project | 9/16/2024: Nancy called Mr. [REDACTED] back. Mr. [REDACTED] would like someone to talk to someone who can come out and show him where the line would cross his property. He would like to talk to someone within the next couple of days, if possible. Nancy forwarded Mr. [REDACTED] request to the project team. 9/20/2024: NRobertson @ POWER forwarded a screen shot of Mr. [REDACTED] property showing that the proposed line does not cross. 9/23/2024: Nancy called Mr. [REDACTED] to let him know and offer to send the screen shot. Mr. [REDACTED] does not have email or access to the website. He requested that someone send the screen shot via US Mail to his home. Nancy alerted the project team to the request and notified them that she is not in the office until next Wednesday 10/2. 10/01/2024: Natalie asked that we send the Aerial Map #9 to Mr. [REDACTED] instead of the screen shot. Nancy will get this out 10/02. 10/02/2024: ERM sent the map and a short cover memo to Mr. [REDACTED].
FRI | 2024-09-13 | 2:53pm | Phone | [REDACTED] |  |  | Nancy Miller, ERM | [REDACTED] left a message on the project voicemail asking for a call back regarding the Pburg-Thelma project; she mentioned that she owns the parcel at [REDACTED] | 9/16/2024: Nancy called [REDACTED] back and left a voicemail (2 VMs today, will try again tomorrow); historically, we've had trouble with [REDACTED] getting her messages on this number, so I also sent an email to: [REDACTED] asking her to call me back at her convenience [REDACTED] called Nancy back. Call notes below. Nancy forwarded [REDACTED]'s concerns to the project team and told her someone would get back to her. [REDACTED] called me back. She has some major concerns and is threatening legal action if we disturb what she is calling the “bottom land” on her property. She said she has 10 acres of flat land that has city water, sewer hook ups, electrical and natural gas that is being subdivided for housing. There is a home on the property that is currently rented out to traveling nurses. The rent from that property is her only income right now and she fears the nurses will not stay there if the line runs through her property. She mentioned that she has talked with the project team several times over the past couple of years, but it does not seem that any of her concerns were addressed. She mentioned that she is fine with the line crossing through the hillside around her property or finding some other way to cross the property that does not go directly through the planned development. She would like to talk with someone in the next couple of days who can discuss the route placement and any possible solutions to the issues. I told her I would share her concerns with the project team and either I or another member of the team would get back to her. 9/18/2024: At the request of the project team, Nancy emailed and phoned [REDACTED] to draw her attention to the alternative route and let her know we have not made a determination on the route we will pursue in that area. Nancy talked to [REDACTED] and downloaded Aerial Map #2 from the website and emailed to her. [REDACTED] replied that the alternative route is very much preferred and noted that there is also a natural gas well near the blue line on her property. [REDACTED] will submit formal remarks regarding her preference for the alternative route.
TUYE | 2024-09-17 | 10:21am | Email | [REDACTED] |  |  | Nancy Miller, ERM | From: [REDACTED] Email: [REDACTED] Address: [REDACTED] City: East Point State: KY Zip: 41216 Message: I am the property owner at [REDACTED], East Point, KY 41216. I have met with a land agent and discussed the alternate line that would negatively affect my property. I would prefer the proposed route that is shown on aerial map 3 opposing the alternate route that would disturb the property where I reside. | 9/17/2024: NMiller sent [REDACTED] the following email: Hello [REDACTED], I am writing to confirm we received your comment regarding the Prestonsburg-Thelma project. I have shared your information with the project team. Thank you for your feedback. 9/18/2024: Mr. [REDACTED] sent a second email to the Kentucky Power Outreach inbox and attached a letter describing his opposition to the alternative route. Nancy confirmed receipt of the letter and forwarded it to the project team for review.
TUE | 2024-09-24 |  | US Mail | Comment Card |  |  | Nancy Miller, ERM | Address: [REDACTED] City: East Point State: KY Zip: 41216 Email: None Phone: [REDACTED] Message: As can be seen on the new map of the alternate route, location will be determined by your employees, contractors, engineers, etc. with little or no regard for lifeline property owners in the area; however, for record purposes of any future damages, my concerns are as listed but not limited to the following: Wildlife: nearby habitat of bobcats that travel from the hill behind my house to the river - unknown location of eagles nest from which the baby eagle flys to catch prey in my yard and the grown eagle that perches in trees at river Damages: construction and equipment on adjoining property changing underground water seams on my side of the hill resulting is massive slides of rocks and uprooted 100 year old trees directly behind my house Debris: water from my hill property and adjacent ridges come together near the top of the hill on my property behind my home. All that water goes to the river beside my house through my underground tiles. If the tiles get blocked, all that water from all the hills behind my house will go straight through my house. Do I want you anywhere near the hills behind or beside my home? NO, I DO NOT! Can I stop you? No, you'll go wherever you want with no concern for the property owners that will be damaged by you. | 9/25/2024 @ 15:29: Natalie Robertson responded as follows: The Proposed Route does not cross the their property. 9/30/2024: Nancy left V/M to inform [REDACTED] that their property is not directly affected by the proposed line route and to explain that they received the notification mailings because their property is near the proposed route. Invited [REDACTED] to call back if they have any questions. SEE entry dated 10/01/2024 re: Additional comments by [REDACTED] and her niece
TUE | 2024-09-24 |  | US Mail | Comment Card (mailed in) |  |  | Nancy Miller, ERM | Address: [REDACTED] City: Paintsville State: KY Email: [REDACTED] Phone: [REDACTED] Message: The map provided is too simple/general for me to determine exactly what property of mine will be affected. I own 100 acres at the head of Preston Estates. I own cattle and have a farm with a pond. I do not want anymore transmission lines going over my property. I cannot allow any herbicide spraying on my property. you need to devise a new route and leave my property out of it. I will seek legal representation to prevent any part of this from being on my property. | 9/25/2024 @ 15:29: Natalie Robertson responded as follows: The Proposed Route crosses their property for approximately 0.3 miles and parallel to non-AEP transmission line. Refer to Aerial Map 11 of 12, AEP ID 14. 9/30/2024: Nancy: talked with [REDACTED]'s daughter and reviewed the map. Daughter commented that it appears the project team is "going out of its way to cross her mother's property and go directly over the pond". The route "dog-leggs" into her mother's property next to an existing line. The do not want any more lines crossing the property and feel the existing line has taken more than enough from them. I told her I would share her comments with the project team. She appreciated the call.
TUE | 2024-09-24 |  | US Mail | Comment Card |  |  | Nancy Miller, ERM | Address: [REDACTED] City: Van Lear State: KY Zip: 41265 Email: [REDACTED] Phone: [REDACTED] Message: We would like to know more about specific locations. We request a visit for more specifics. | SEE entry dated 09/12/2024 [REDACTED] has been notified that his property is not directly impacted by the proposed route. He received the materials because he is within the study corridor.
TUE | 2024-09-24 |  | US Mail | Comment Card |  |  | Nancy Miller, ERM | [REDACTED] Address: [REDACTED] City: Pikeville State: KY Zip: 41502 Email: [REDACTED] Phone: [REDACTED] Message: I have no concerns. My property is empty. As long as I get compensated. | 9/25/2024 @ 15:29: Natalie Robertson responded as follows: The Proposed Route does not cross their property; however I am confused because he says his property is empty but there is a residential structure on it. Refer to Aerial Map 5 of 12, AEP ID 58. 9/30/2024: Nancy tried to leave a message for [REDACTED], however his V/M has not been set up at this number. Will try again. 10/01/2024: Nancy talked with [REDACTED] and he requested a copy of the route map. Nancy informed him that the maps are available on the website and offered to send the link via email. Nancy sent the link to [REDACTED] 10/01/2024 at 11:55am Central.
TUE | 2024-09-24 |  | US Mail | Comment Card |  |  | Nancy Miller, ERM | Address: [REDACTED] City: Paintsville State: KY Zip: 41240 Email: [REDACTED] Phone: [REDACTED] Message: no comments on sheet | 9/25/2024 @ 15:29: Natalie Robertson responded as follows: The Proposed Route crosses their property to enter the Thelma Substation on the north end of the Project, refer to Aerial Map 12 of 12, AEP IDs 139, 140, and 141. 9/30/2024: Nancy emailed [REDACTED] to confirm receipt of the comment card. Since there were no substantive comments on the card, Nancy invited [REDACTED] to reach out at any time if he has any questions or comments in the future.
TUE | 2024-09-24 |  | US Mail | Comment Card |  |  | Nancy Miller, ERM | Address: [REDACTED] City: Thelma State: KY Zip: 41260 Phone: [REDACTED] Message: Just lived here 6yrs. Not familiar with said cemetery. (NOTE: this may be a reference to the "EXAMPLE" text regarding a cemetery that appears on the comment form - not an actual comment about an existing cemetery.) | 9/25/2024 @ 15:29: Natalie Robertson responded as follows: The Proposed Route does not cross their property. 9/30/2024: Nancy talked with [REDACTED] to confirm receipt of the comment card and let her know the proposed route does not cross the property. Nancy also invited [REDACTED] to reach out at any time with future questions or comments. [REDACTED] was appreciative of the call.
FRI | 2024-09-27 | 1:14pm | Email | [REDACTED] |  |  | Nancy Miller, ERM | Address: 3 [REDACTED] City: Meally State: KY Zip: 41234 Message: ADDITIONAL COMMENTS/CONCERNS 1) Depreciation of the Fair Market Value of Property. 2) Sterilization of marketable and merchantable coal on my property and adjoining properties. (My property has existing road and only feasible access to Kentucky Route 40E for coal transport or potential wheel-age income.) 3) Marketable and merchantable timber impacted. 4) Impact on any future entrepreneurship (Especially tourism as property is in close proximity to Paintsville City Limits, Golf Course, Dawkins Trail and Paintsville Lake.) 5) Access to partial of property under power lines. 6) Type of vegetation control on ROW (Impact to environment and wildlife) 7) Ingress and egress across property to access lines and structures (Who is responsible for access road maintenance?) | 10/01/2024: Email forwarded to Nancy for follow up; [REDACTED]'s comments were discussed on the P-T outreach/siting call; the team has asked Nancy to reach out to [REDACTED] to confirm receipt of his comments and let him know the message will be shared with the project team. 10/02/2024: Nancy emailed [REDACTED] to confirm receipt of his comments and to let him know the comments were forwarded to the project team for review.
MON | 2024-09-30 | 5:31p | Email | [REDACTED] |  |  | Nancy Miller, ERM | Address: [REDACTED] City: Paintsville State: KY Zip: 41240 Email: [REDACTED] Phone: [REDACTED] Message: Please advise that I write this letter on behalf of my dad/client and [REDACTED] They are owners of certain properties located in the Thelma Lake area. We are uncertain what area of properties you will be interested in acquiring or using? Can you please assist Thank you | 10/01/2024: Project team reviewed [REDACTED]'s message on the siting/outreach call and determined that the property is not crossed by the current, proposed route NOTE: [REDACTED] and [REDACTED] also left a voicemail on the project hotline on 9/30/2024. 10/02/2024: Nancy replied to [REDACTED]'s email to confirm receipt of his email, provide the map screen shot from Natalie regarding the [REDACTED] property and requesting the name of [REDACTED]'s dad so we could review his property as well. Nancy also informed [REDACTED] that the project maps are on the website and that they only show the proposed route and one route alternative. The team has not determined a final route nor the locations of access roads or other project related facilities. Nancy will seek input from Natalie once we have the name of [REDACTED]'s father. 10/03/2024: [REDACTED] confirmed that his father is [REDACTED]. Natalie provided a screen shot of the route crossing the [REDACTED] property and Nancy emailed it to [REDACTED].
TUE | 2024-10-01 | 7:59a | Email | [REDACTED] |  |  | Nancy Miller, ERM | CC: [REDACTED] ( [REDACTED]; [REDACTED] Message: Dear Ms. Mustard: I am reaching out to you on behalf of my mother [REDACTED]. She is the owner of [REDACTED] in Prestonsburg, Kentucky. This property includes [REDACTED] on the Area Map 2 CPDF. [REDACTED] has reached out to Ms. Nancy Miller by phone and discussed with her the objection to the first power line proposal as well as the new power line proposal. The second powerline proposal is acceptable. [REDACTED] informed Ms. Miller that the first proposal would destroy the only level land in city limits. It also met all the criteria identified in your correspondence of September 9, 2024. It was addressed to [REDACTED]. My daughter, [REDACTED] and I are the only other living heirs. [REDACTED] is copied on this email as is [REDACTED]. The land at [REDACTED] has historical significance. It was included in a land grant from the Governor of Virginia in 1813. The first proposal would disturb the family cemetery where our family has been buried for over 250 years and where we will be buried. The property has two gas wells, two water wells, creeks and artisan wells. It is home to undisturbed wildlife and virgin timber. We were unable to stop the gas drilling due to Kentucky's antiquated mineral rights laws. That continues to be a contentious relationship with the Kinzer Corporation that has little regard for the property owners. At present, my mother's childhood home that was built in the late 30's, early 40's serves as part of my mother's income. The home has been extensively renovated and is rented to a travel nurse. The current occupant is an Air Force retiree that works as a supervisor in the operating room at Prestonsburg ARH. Proposal one would destroy the only large tract of level land in the Prestonsburg city limits. Again, the second proposal for line placement is acceptable. it misses the cemetery, level land, homeplace, and the other houses in the community. We highly recommend the second route proposal. Feel free to contact me at [REDACTED] or [REDACTED] at [REDACTED] for more information. Sincerely, [REDACTED] | Cortney Mustard replied to [REDACTED] to confirm receipt of the email and inform her that the content would be shared with the project team.
WED | 2024-10-01 | 3:54p | Voicemail | [REDACTED] |  |  | Nancy Miller, ERM | Voicemail transcript: Hi, Nancy, this is [REDACTED] and [REDACTED]. We're calling on a conference call about a property situation related to your Thelma project. If you can give me a call back, my number is [REDACTED] and [REDACTED]'s number and I think you called her before is [REDACTED]. Thank you very much. Bye bye. | 10/02/2024: Nancy returned [REDACTED]' call. [REDACTED] conferenced in [REDACTED]. [REDACTED] and her niece ([REDACTED]) called to relay some additional concerns related to slides, drainage impacts, threatened and endangered species, and avenues for reparations should the project work cause damage to adjacent properties. Nancy let them know she would summarize the conversation for the project team and invited [REDACTED] and [REDACTED] to submit detailed comments to the project team. The have also requested a contact for potential legal issues that may result from the project (specifically reparations for any damage caused by the work). [REDACTED] indicates the area is "probably more trouble than its worth" due to the steepness of the terrain and related issues as well as the remoteness of the area. Note [REDACTED] works for the University of Tennessee and was previously General Counsel for a large insurance company. 10/03/2024: [REDACTED] provided additional comments and Nancy confirmed receipt and shared with the project team. To Whom It May Concern, I am writing to provide additional information following my conversation with Ms. Nancy Miller from Environmental Resource Management on October 2, 2024. Ms. Miller encouraged me to elaborate on concerns I shared verbally during our call, supplementing my earlier comment submission. While I understand the need for improvements to the electric transmission grid, I have significant concerns regarding the proposed routes and locations that may affect my property. The area’s unique structural and environmental challenges present considerable risks to your project and could have a negative, and potentially devastating, impact on my land. Ecological and Wildlife Impact My property is located near areas where baby bald eagles have been observed for several years. The presence of eaglets suggests that the nest is likely close to the proposed path. The Bald and Golden Eagle Protection Act prohibits disturbances to these birds, including potential habitat destruction caused by heavy equipment and the ongoing access needed for construction and management. Accordingly, I question why the project cannot be relocated to more developed areas to avoid such impacts. Additionally, the remote nature of the surrounding environment has served as a habitat for other threatened creatures, such as various bat species (including the statutorily protected Indiana bat) and bobcats. I am deeply concerned about the potential ecological consequences of the Thelma project. Risks to Property and Safety The construction of the proposed infrastructure poses significant risks to my home and the surrounding properties, particularly due to the hilly hard clay terrain and waterways. • Hillslides: Even minor shifts in topsoil in areas with hard clay soil can lead to severe hillslides. I have witnessed firsthand the consequences of minor disturbances on neighboring properties, which have severely impacted my own. • Flooding: My property and home are at the base of several hillsides, making it highly susceptible to flooding, especially if natural water flow is obstructed or impacted. Recent flooding in the area was exacerbated by a single branch blocking a visually small and inconsequential creek, demonstrating how quickly conditions can become life and property threatening. Any actions related to tree removal, digging, excavating or other construction could worsen flooding risk, despite the protective measures I have installed at significant personal cost. Liability and Mitigation Concerns As discussed with Ms. Miller, I am also deeply worried about financial responsibility for potential damages. Kentucky insurance often excludes hillslides caused by third-party actions. If the project proceeds, I request contact information for a local representative who can address issues promptly and ensure accountability for damages resulting from construction activities. I cannot afford delays while insurance matters are debated. In addition, I respectfully request that, in the event your project is approved on its proposed route, I be provided with a direct and immediate method of contact with a local onsite person at all times with accountability for the liabilities associated with the project. This person needs to be able to dispatch timely assistance to resolve issues caused by the project (things like immediately removing blocking branches, assisting to prevent flooding, etc.) as I am unable to address these matters myself or engage a contractor quick enough to mitigate any resulting damage. Impact on Property Values While I appreciate the need for electric infrastructure—having worked for 40 years with Big Sandy Rural Electric Cooperative—I am concerned about the negative effects this project will have on property values in this less developed area. The visual and environmental impacts will detrimentally affect neighboring properties in a manner that exceeds the economic impact to other areas that already are in the line of sight to various towers, equipment and access infrastructure. I understand from my conversation with Ms. Miller that the alternate route was proposed in response to public comments received. However, I am apprehensive that these decisions may prioritize certain individual economic interests over the health and safety of neighboring residents, many of whom may struggle to engage with this process. I will be filing a public records request to obtain documentation related to the decision-making for this alternate route and would appreciate your assistance in providing this information promptly. Thank you for your attention to these critical issues. I hope that you will implement my suggestions and create a new alternative plan that allows you to meet your project goals but does not introduce the significant risks described above. If you need any additional information, please contact me. Sincerely, [REDACTED] [REDACTED] East Point, KY 41216 [REDACTED]
WED | 2024-10-02 | 1:13pm | US Mail | Comment Card |  |  | Nancy Miller, ERM | Address: [REDACTED] City: Prestonsburg State: KY Zip: 41653 Email: [REDACTED] Phone: [REDACTED] Message: The line shows it will run approximately 300' from my property and will have a huge effect on our property value, also effect on electronics & on our health concerns. Would appreciate it if you found an alternative route. | Nancy sent an email to [REDACTED] to confirm receipt of the comment card and inform him that his comments will be shared with the project team. Nancy also forwarded [REDACTED] comments to the project team.
THU | 2024-10-03 | 1:47p | Email | [REDACTED] | 146 | 9 | Nancy Miller, ERM | Address: [REDACTED] City: Van Lear State: KY Zip: 41265 Phone: [REDACTED] Email: [REDACTED] Message: Our property is located on [REDACTED], property [REDACTED]. Our property has an access road off Rt. 302 on the east side of the property, parallel with the proposed route. The road was once used for a small surface mine - mine bench is still accessible. You can reach me by cell # [REDACTED]. | Nancy sent an email to Mr. [REDACTED] to confirm receipt of his comment and inform him that his message will be shared with the project team. Nancy also forwarded Mr. [REDACTED] comments to the project team.
FRI | 2024-10-04 | [6 empty] | END OF COMMENT PERIOD | END OF COMMENT PERIOD (Note: several additional comments were taken into consideration - through 10/15/2024 - since they were mailed before the close of the comment period)
SAT | 2024-10-05 | 11:00a | Email | [REDACTED] |  |  |  | Email: [REDACTED] Phone: [REDACTED] Address: [REDACTED] City: Prestonsburg State: KY Zip: 41653 [REDACTED] sent the following email to the project inbox: My name is [REDACTED], President of the [REDACTED] (formerly [REDACTED]). I have reviewed the proposed route and do not object to the project. The [REDACTED] looks forward to working with you on the project. The address listed above is [REDACTED]'s address. Future correspondence can be mailed to this address. My phone number is [REDACTED]. | 10/08/2024: AEP forwarded Mr. [REDACTED] comment to ERM, Nancy emailed Mr. [REDACTED] to confirm receipt of his comment and inform him that his message will be shared with the project team. Nancy forwarded Mr. [REDACTED] comments to the project team.
MON | 2024-10-07 | 7:29a | Email | [REDACTED] |  |  |  | [REDACTED] sent a follow up email after receiving screen shots of [REDACTED] and [REDACTED] parcels near the proposed route. (SEE LINE 15 for previous comments): Ms. Miller; Thank you for your time. Unfortunately, there are some issues with this map. My group has responded see below. “The property lines on almost every parcel are incorrect. PVA has on their maps. At the last meeting the electric company had with the property owners, I submitted mine and [REDACTED]'s deeds, and I drew out a map showing the correct property lines. Not sure what AEP done with the information. They still have [REDACTED] owning one of the parcels that I bought, and they have [REDACTED] owning most of [REDACTED]'s tract. [REDACTED]'s property lines are really off.” I suggest a meeting. [REDACTED] | Nancy send an email to [REDACTED] to confirm receipt of the additional comments and to inform him the message will be shared with the project team.
TUE | 2024-10-15 | 1:00p | US Mail | Comment Card | 184 185 | 2 | Nancy Miller, ERM | Address: [REDACTED] City: Tallahassee State: FL Zip: 32311 Email: [REDACTED] Phone: [REDACTED] Glenda is [REDACTED]'s daughter Message: Proposal two is acceptable, Against proposal one 1.) The property can be identified as [REDACTED] on Map 2. The land has historical significance. It was part of a land grant form the governor of Virginia in 1813. First proposal would go through family cemetery. 2.) Contains two gas wells, two water wells, creeks, & artisan wells. Marshlands. Home to undisturbed wildlife on virgin timber. 3.) House serves as income & provides housing for travel nurses. 4.) Only level land in Prestonsburg City limits. | SEE entry dated 09/13/2024 Nancy spoke to [REDACTED] after she left a message on the project voicemail on 9/13/2024. In that conversation, [REDACTED] outlined many of the same concerns as in this comment card. SEE entry dated 10/01/2024 Glenda Stanley emailed [REDACTED] on 10/01/2024 outlining many of the same concerns as this comment card. 10/18/2024: Nancy emailed [REDACTED] to confirm receipt of the comment card and inform her that the comments have been shared with the project team. SEE entry dated 02/17/2025 re: route selection
TUE | 2024-10-15 | 1:00p | US Mail | Comment Card |  |  | Nancy Miller, ERM | Address: [REDACTED] City: Paintsville State: KY Zip: 41240 Email: [REDACTED] Phone: [REDACTED] Message: The location of the existing and proposed lines should show approximately location of individual property owners and power lines crossing said properties. [SIC] Since the new bridge build that connected route 40 & 1107 has provide excellent access to very valuable property that can and probably be developed in the future. That is why we need to see in detail location of new route & impact of each property owners property. Kentucky Transportation has location of most of the properties that would be affected in my area. I also have survey of my property by Bocook Engineering if this is needed for location of lines across property. [SIC] | 10/18/2024: Nancy emailed project team to check on map requested by Nicole Hodges on Tues. 10/15/2024 10/23/2024: Natalie provided a map showing the Fitch parcel and Nancy forwarded to the landowner with an email confirming receipt of the comment card.
TUE | 2024-10-15 | 1:00p | US Mail | Comment Card |  |  | Nancy Miller, ERM | Address: [REDACTED] City: Prestonsburg State: KY Zip: 41653 Email: [REDACTED] Phone: [REDACTED] Message: The map doesn't show the streets affected so I can't determine how it affects my property. Is it possible to provide a more detailed map. | 10/18/2024: Nancy emailed project team to check on map requested by Nicole Hodges on Tues. 10/15/2024 10/23/2024: Natalie provided a map showing the [REDACTED] parcel and Nancy forwarded to the landowner with an email confirming receipt of the comment card.
TUE | 2024-10-15 | 1:00p | US Mail | Comment Card |  |  | Nancy Miller, ERM | Address: [REDACTED] City: Prestonsburg State: KY Email: [REDACTED] Phone: [REDACTED] Message: How many towers and distance between them | 10/18/2024: Nancy emailed [REDACTED] to confirm receipt of the comment card and inform her that the comment has been shared with the project team.
WED | 2024-11-13 | 10:39p | Email | [REDACTED] |  |  | Nancy Miller, ERM | Address: [REDACTED] City: Van Lear State: KY Zip: 41265 Email: [REDACTED] Message: Hello Nicole, My name is [REDACTED] and my property that I own [REDACTED] Van Lear, KY 41265 is going to be affected by this project. Can you please send me a map of my property and what would be installed on it? | 11/14/2024: Nancy requested a map from Natalie Robertson @ Power showing structure type and location. Natalie responded with a map from the open house showing preliminary structure locations. Nancy forwarded the map to [REDACTED] with the following note: Hello [REDACTED], I wanted to confirm that we received the comment you submitted regarding the Prestonsburg-Thelma Transmission Line Rebild Project. Per your request, I’ve attached a map showing PRELIMINARY structure locations. Please note that the structure locations are subject to change as we are still conducting surveys and other field work to determine a final route. On the attached map, your property is labeled with a #5 and the PRELIMINARY structure locations are indicated by the orange dots. Also, wanted to confirm we have the correct mailing address for you: [REDACTED] 11/15/2024: [REDACTED] responded asking for clarification on the mining rights designation on his parcel map; Nancy confirmed with Natalie that the designation came with data outlining mining rights from Kentucky Division of Mine Permits; the permit has been released and is currently inactive. [REDACTED] also asked if we have a date for the route selection and Nancy let him know it is anticipated in the next couple of months.
WED | 2024-11-27 |  | Phone | [REDACTED] |  |  | Nancy Miller, ERM | [REDACTED] left a voicemail on the project hotline 11/27 requesting information about the Prestonsburg-Thelma project. | 12/4/2024 @ 11:29a: Nancy returned [REDACTED]'s call. [REDACTED]'s phone rings "unavailable" so Nancy is unable to leave him a message after several attempts. Nancy sent [REDACTED] an email to let him know we are trying to reach him and to inquire what his questions are. [REDACTED] responded to the email and asked Nancy to attempt a call again. Nancy called [REDACTED] and got the same result...4 rings and cut off with an "unavailable" message. No voicemail. 12/5/2024 @ 5:46pm: Nancy made a third attempt to reach [REDACTED] w/ the same result as above. Also emailed [REDACTED] to ask for a specific time to try the call again or for him to reply to the email with any specific questions. 12/6/2024: [REDACTED] sent Nancy the following questions via email and Nancy forwarded to the project team for review and response. Nancy confirmed receipt of the questions w/ [REDACTED] and let him know she had forwarded to the project team. 1) I signed the "Survey & Appraisal Permission Form" a few weeks ago. I was told the survey crews would be starting within a week. Do you know if the surveys have been started yet? 2) The current proposed plan shows the lines going over my property along with a structure being placed on it. I believe someone said it was a 69 kv transmission pole. Is this correct? 3) Currently my property has no house on it. However, I plan to build a house. I question building on the property with high transmission lines and if it would take my location where I plan on building it. Do you think Kentucky Power would be interested in buying the property? 4:15p: ROW replied that they would follow up with [REDACTED] and report back to the project team 12/09/2024 @ 3:17pm: Derrick Wilson (Emerald) emailed to confirm Jim Childers had spoken with [REDACTED] and addressed all his questions.
MON | 2025-02-17 | 13:41 | Phone | [REDACTED] | 184 185 | 2 | Nancy Miller, ERM | Address: [REDACTED] City: Tallahassee State: FL Zip: 32311 Email: [REDACTED] Phone: [REDACTED] | SEE entry dated 09/13/2024 Nancy spoke to [REDACTED] after she left a message on the project voicemail on 9/13/2024. In that conversation, [REDACTED] outlined many of the same concerns as in this comment card. SEE entry dated 10/01/2024 [REDACTED] emailed [REDACTED] on 10/01/2024 outlining many of the same concerns as this comment card. SEE entry dated 10/18/2024 Nancy emailed [REDACTED] to confirm receipt of the comment card and inform her that the comments have been shared with the project team. 02/03/2025: On Route Selection planning meeting, project team requested that Outreach contact [REDACTED] to let her know the alternative route was selected prior to sending her the Route Selection letter. Nancy will contact [REDACTED] just before the letters are mailed. 02/17/2025 @ 13:50: Nancy talked with [REDACTED] to let her know the Western Alternative was selected as the preferred route that will be filed with regulators and to alert her that she should be receiving a mailing to that affect in the next few days. [REDACTED] was very appreciative of the call, reiterated that the land had been in her family sine 1813 and the house has recently been renovated to rent to traveling nurses at the local hospital. [REDACTED] noted that the alternative route will be "much better for the community".
| 2025-02-17 |  | US Mail/Outgoing | Route Selection Mailing |  |  |  | Mailing sent to all affected LO along both the proposed route and the new alternative (183 landowners on the mailing list) alerting everyone that the western route alternative was selected as the proposed route that will be file with regulators - Cover letter w/ updated concept map on the back
MON | 2025-02-27 | 12:32 | Voicemail | [REDACTED] | 14 | 10,11 | Nancy Miller, ERM | [REDACTED] left a voicemail stating that the numbers for Emerald ROW office are disconnected and that she would like someone to call her back re: the P-T project. | 03/03/2025 @ 15:10: Nancy reached out to [REDACTED] at the number provided. Nancy asked for [REDACTED] and the person who picked up said it was the wrong number. Nancy checked the number with the person on the line and confirmed that is the number that was dialed. After apologizing for the error and hanging up, Nancy double checked the voicemail and noted it was the number [REDACTED] left on the voicemail. Nancy called again and left a voicemail for [REDACTED]. Nancy reached out to Jason Crum of Emerald to confirm the phone numbers have been disconnected and request updated contact information. JCrum forwarded the inquiry to Derrick Wilson, lead ROW agent for the project. DWilson confirmed the old office numbers had been disconnected and provided a new number. DWilson also indicated that ROW would reach out to [REDACTED] regarding her concerns. 03/04/2025 - 03/10/2025: [REDACTED] left voicemails for Nancy indicating she will not allow another power line across her property and asking for a call back. Nancy forwarded all calls and voicemail transcriptions to ROW for follow up. 03/10/2025: DWilson confirmed that Doug Blevins spoke with [REDACTED] on Friday, March 7. [REDACTED] requested follow up from Siting or someone who can make a decision re: removing the line from her property. [REDACTED] left another voicemail for Nancy. Nancy forwarded to ROW, Siting and Outreach. Natalie Robertson replied to say she and Allen Hodges will meet to discuss next steps. DWilson replied that [REDACTED]'s daughter [REDACTED] would like all correspondence to go through her [REDACTED] as [REDACTED] is elderly and "sometimes gets details mixed up". 03/11/2025 @10:15am: [REDACTED], daughter to [REDACTED] left another message on Nancy's voicemail. Nicole Hodges requested that Nancy return [REDACTED]'s call and let her know we have received her messages and that the team is reviewing her comments. Hoping to have additional information for her next week. [REDACTED] mentioned her mother [REDACTED] is elderly. About every other year they are forced to give up property: RECC has taken a swath, local gas company taken a swath and created roads onto the property, trespassers/4-wheelers on the properties, cell phone tower within the last year; government came and condemned a piece of property for a flood wall. [REDACTED] feels they have given enough. They had a perfectly good transmission line already selected and now they have moved it and started all over. Can be easily remedied - her property can be completely avoided...just use the existing line instead of going in a whole different pathway. [REDACTED] is very into conservation: RECC line completely wiped out some endangered wildflowers on a hillside (a shade species) because they took out all the trees. If this line goes in she will have no trees. They have lots of animals. [REDACTED] has made a walking trail all around the property - willing to do a site visit and walk the property. It wouldn't take much to get completely off her property - [REDACTED] is happy to meet with someone out on the property to discuss. Very accessible paths. Nancy sent conversation summary to the project team. SEE 03/14/2025 ENTRY for additional information.
| 2025-03-11 |  | US Mail/Outgoing | Update Emerald Contact Information |  |  |  | Postcard mailing sent to all affected LO along both the proposed route and the new alternative (183 landowners on the mailing list) alerting everyone that the office phone number for Emerald (ROW Vendor) was incorrect on the Route Selection Mailing and providing the correct number
FRI | 2025-03-14 | 12:32 |  | [REDACTED] | 14 | 10,11 | Nancy Miller, ERM |  | Project team held a meeting on Friday, March 14 to discuss. Nicole Hodges will call LO to explain outcomes of the call and try to schedule a TEAMS meeting to show visuals of decision-making process. 03/25/2025: Project team held a prep call for scheduled team meeting with [REDACTED]. Nicole reiterated that she had spoken with [REDACTED] last week and shared the following talking points: - Explained that crossing existing KY Co-Op 69-kV line would create issues with reliability - Explained that we can leave trees in the valley and only cut those around the structures on the ridges - Confirmed we will use existing access roads where possible, but did not guarantee that we will not build additional if needed - Will not use aerial sprayers, but will use backpacks for any herbicide or insecticide use - Asked [REDACTED] to consider if there was anything AEP could do to make it a better situation: planting additional trees or other property improvements - [REDACTED] did not have anything immediate, but will consider the offer prior to the team meeting - [REDACTED] did come to the realization at the end of the conversation that the line will likely need to cross her property, agreed to meet w/ project team Project team met with [REDACTED] via TEAMS on Thursday, March 27 Project team met with [REDACTED]. She would still prefer that the line be moved off of her property and can not think of anything that would make the situation better. She has concerns about trees as well as wildflowers (Trillium, Jew, Jack in the Pulpit) along the southern border of her property. She feels the property lines on our map are incorrect and the line will actually be on her property at the top of the ridgeline along the southern border of her property (this is the area where the wildflowers bloom - also the area RECC decimated a large swath of said flowers during the last project). Doug Blevens/ROW will call [REDACTED] after the meeting to discuss survey permission. Nicole also offered a site visit to show the project team the areas of concern. [REDACTED] does not think there will be much that can be done: "the bottom line is that power lines are necessary, but if you have to live with them, they are not pretty" and "it is always an uncomfortable situation when your land is being taken away". [REDACTED] thanked the team for their time; Nicole thanks [REDACTED] for meeting with us and the call ended.
THU | 2025-04-10 | 14:45 | Voicemail | [REDACTED] | 89 | 10 | Nancy Miller, ERM | [REDACTED] left a voicemail on the project hotline regarding a mailing his mother received. He would like to update the address | 04/11/2025 @ 12:33: Nancy called [REDACTED] to ask which project he was referring to and ask for the address update. [REDACTED] confirmed he was calling about the Thelma Route Announcement letter dated February 2025. He says his Uncle's name is on it, but it went to his Mother's address. His aunt is the "secretary" of the property and wants ALL correspondence to go through them. [REDACTED] filed a change of address with Johnson County, but he thinks we may have pulled our mailing list before the change was made. [REDACTED] did not have the address at hand, but will email it to Nancy in the near future. He was very pleasant and appreciated the return call. Nancy will send the updated mailing address to ROW upon receipt.
THU | 2025-07-03 | 14:41 | Voicemail | [REDACTED] |  |  | Margot Bond-Downey, ERM | [REDACTED] left a voicemail regarding surveying of her land and would like more information about this. | 07/09/2025 @ 20:10: Nancy informed the project team that [REDACTED] had left a message about the requested survey. 07/11/2025 @ 7:06: Jim Childers, Emerald Energy, replied to confirm it is Landowner [REDACTED] on the Kenwood-Prestonsburg line and that Jim Childers with Emerald will reach out to her to discuss her concerns.
MON | 2025-10-20 | 13:46 | Voicemail | [REDACTED] |  |  | Nancy Miller, ERM | [REDACTED] left a voicemail on the AEP Corporate line. Zada Porter forwarded to Amanda DeHaven and Amanda forwarded to ERM for follow-up. | Nancy replied to Amanda to let her know [REDACTED] has contacted the project team several times over the years. Nancy will check in with ROW to see if they have talked to [REDACTED] recently and to see if they want to follow up with him or have Outreach follow up. Nancy will let Amanda know about any feedback received. 10/21/2025: Derrick Wilson (Emerald) replied to acknowledge Jim Childers spoke to [REDACTED] 10/20. ROW confirms [REDACTED] was inquiring about the project delay. Jim explained that there is some additional study underway re: culturally sensitive areas/cemeteries and that additional information would be coming out once that is resolved. [REDACTED] was satisfied with the response. NOTE: Jim Childers also sent a note 10/20/2025 confirming he had spoken to [REDACTED].
FRI | 2025-11-14 |  | US Mail/Outgoing | Route Update and Filing Notification |  |  |  | Mailing sent to all affected LO along the route to be filed (199 landowners on the mailing list) alerting everyone that the route has been modified to avoid cemeteries and that the project will be filed with state regulators later this month. - Cover letter noting route update and filing notification language - Project factsheet
FRI | 2025-11-14 |  | US Mail/Outgoing | Route Update and Filing Notification |  |  |  | Mailing to 15 LO affected by the cemetery route adjustment w/ notification that their property is affected by the re-route and containing LO packet - Cover letter noting route update - Project factsheet - Comment card - Parcel map - Return address envelope
MON | 2025-11-24 | 8:10 | Email | [REDACTED] | 136 | 8,9 | Margot Bond-Downey, ERM | Address: [REDACTED], Van Lear, KY 41265 Office: [REDACTED] Cell: [REDACTED] Message: We own property [REDACTED]on Aerial Map #9. There are three structures identified as 1494-9, -10 and -11 on or near Property [REDACTED]. Will there be a map with the proposed construction route and staging area for equipment provided to the property owners before construction begins? Can you provide a profile of the powerline crossing Property #136? Thanks. [REDACTED] Note: [REDACTED] is a [REDACTED] | Hello [REDACTED], I am reaching out in response to your email about the Prestonsburg-Thelma Line Rebuild Project. Please let me know if you did not receive a map in your informational packet. We also have an interactive map on the website at www.KentuckyPower.com/Thelma. The staging areas and access roads have not been finalized at this time. We do not currently have a line profile available. The draft route is on public notice and will not be finalized until the comment period is completed and all feedback has been reviewed. Once we have completed the public comment period and determined a final proposed route, a right-of-way agent will be in touch regarding next steps. If you would like to discuss in more detail or have any additional questions, please let me know. I’m happy to contact you via phone. If that is more convenient, please provide a phone number and your preferred time of day for a call. Thank you for your inquiry. 11/24/25 @ 16:23: [REDACTED] replied as follows: Thanks Ms. Miller. I don’t have any further questions.
MON | 2025-12-01 | 9:42 | Voicemail | [REDACTED] | 33 | 7,8,9 | Margot Bond-Downey, ERM | [REDACTED] called on behalf of [REDACTED], who owns the property. [REDACTED] would like to speak with someone about the property affected by the Prestonsburg-Thelma line. 12/01/2025 @ 14:19: [REDACTED] reached out to Amanda with the following email: hello Amanda contacting you for some info on line project phone [REDACTED] [REDACTED] thank you have a great day 12/01/2025 @ 13:08: [REDACTED] left a second voicemail requesting a call back. 12/02/2025 @ 07:57: [REDACTED] left a third voicemail requesting a call back. | 12/02/2025 @ 12:33: Nancy Miller returned [REDACTED]'s call. [REDACTED] was checking in and stated he spoke with Doug Blevins in August. [REDACTED] said the preliminary route that Doug shared at that time was very different and crossed over the middle of the property. The most recent route is MUCH BETTER in his opinion as it hugs the property line and avoids going over the top of the house. If this route is the final, they are very much in support of this option. Nancy explained that we plan to file the proposed route with the state in the near future. While there is always room for adjustments, we are planning to file the route as indicated on the maps he received. [REDACTED] was very appreciative of the call back and is in support of the project. Nancy thanked him for his time and invited him to call back if he should have any additional questions.
MON | 2025-12-01 | 10:33 | Email | [REDACTED] | 91 | 8,9 | Margot Bond-Downey, ERM | On Saturday, November 29, [REDACTED] submitted the below statement to the KY PSC docket for case number 2025-00346 Prestonsburg-Thelma Project. About an hour after this statement was filed with the PSC, [REDACTED] forwarded the email to the Kentucky Project Outreach inbox. This is a direct response to a letter received by [REDACTED] [REDACTED] Van Lear, KY 41265 regarding the new Prestonsburg-Thelma Transmission Line Rebuild. [REDACTED] was contacted via phone by an AEP representative regarding their desire for permission to move forward with examining and working on her property as one of the possible proposed routes for this project. At that time, months back, she verbally stated that she would NOT agree to allow a route for the project over her property. This is in response to extreme trauma from an electrical main line falling in her yard in the 1970’s, nearly causing the death of the entire family. Had they not been located upstairs at the time of the incident, all would have perished. Deep trenches in the dirt were dug out as the live line bounced and landed over and over and damages to the home and property WERE NOT covered by the power company. They did not help in any way. The event was extremely horrifying and she is almost 85 years old now. She is scared of additional lines being added across her property and she is terrified of negative health consequences from high voltage lines, stations, etc. She requested with the representative [REDACTED] that you choose an alternative route and not involve her property [REDACTED] Van Lear, KY 41265 in any way. After explaining this reasoning it was understood that there were other alternatives to bypass her property. She has been a cancer survivor as well and has always attributed the current power lines as a possible contributing factor in her diagnosis as nobody in her family on either side had ever suffered this particular type before. Now she has received a letter and a response is required and requested. This is to serve as her official response. She DOES NOT APPROVE and WILL NOT APPROVE her property as a possible route for this project and respectfully advises you to search and procure an alternative route that does not involve her property or air space above. Thank you for your opportunity to allow her written response. Respectfully signed, [REDACTED] [REDACTED] | 12/02/2025 @ 15:20: Nancy replied via email to let the [REDACTED]/ [REDACTED] know their comments have been received and shared with the project team. 12/8/2025: On the Prestonsburg-Thelma project team call, [REDACTED] asked Nancy to draft a second response to the [REDACTED] and [REDACTED]. Nancy sent DRAFT text to [REDACTED] noting that the project team wanted to inform her that they had discussed the issues Ms. [REDACTED] encountered with he distribution line and noting that the proposed transmission line is about 250 feet away from the home. Also noting the project has been filed with the KY PSC and is awaiting regulatory approvals. If approved, [REDACTED] would be contacted by ROW w/ additional information. 12/9/2025: Natalie Robertson emailed with some questions about the response and noted that she had spoken with [REDACTED]. She indicated they had discussed relocating the distribution line, but recommend sending a ROW agent to meet w/ her first. Nancy responded to ask if the plan is still to send a response or if Outreach should hold off until ROW/Distribution/Siting have that discussion. 12/10/2025: Natalie responded that she would take the following actions and Outreach should stand down until they are ready for us to respond. - Hold off on responding until we can confirm the distribution information and whether someone from ROW would be available to talk to her - Siting will confirm with David May (AEP Distribution) whether we can relocated the distribution line on her property - If the [REDACTED]/ [REDACTED] will agree to it, let's try and get a ROW agent out to talk with them about both the distribution line and this project 12/22/2025: Natalie asked on the project call if any additional action had been completed on this comment. Nancy reported Outreach was still on stand down awaiting notification of the above actions. The project team discussed the matter and determined that Outreach should send another message to [REDACTED] asking if they would be willing to meet with a ROW agent either via phone or onsite at [REDACTED]'s property. Nancy sent an email to the [REDACTED] asking if they would be interested in meeting and requesting a day/time that would work. for them. 01/05/2026: On the project team call, the group asked Nancy to reach out to the [REDACTED] again to see about setting up a site visit. Nancy emailed [REDACTED] and [REDACTED] a second time to propose a site visit and to get their availability. 01/14/2026: Nancy emailed [REDACTED] a third time to ask fi they would be interested in a meeting with the project team. [REDACTED] replied as follows: You can call and speak to mom at [REDACTED] SHE ABSOLUTELY DOES NOT WANT this project crossing her property. You can call her tomorrow January 15th between 2pm and 4pm. SHE IS ADIMANT due to her previous experiences. Thank you. Just find someone else’s property to cross. 01/15/2026: Nancy thanked [REDACTED] for her response and let her know Nancy was checking with the project team re: availability. Nancy also asked if a TEAMS call would be possible so the project team could pull up mapping. Nancy also asked if they would prefer a site visit. 01/16/2026: The project team met to discuss the [REDACTED]/ [REDACTED] concerns and determined that ROW would meet w/ Ms. [REDACTED] in person. Siting will provide mapping. ROW will explain the project in detail, note that no structures will be placed on her property and discuss the location of the distribution line. Jessee Reed and David May will go to property to collect photos of outbuildings on the adjacent property to the NW and review the distribution line placement. Siting will also work on potential routing adjustments.
WED | 2025-12-09 | 11:08 | Voicemail | [REDACTED] | 120 | 6,7 | Margot Bond-Downey, ERM | [REDACTED] called to speak with Amanda DeHaven. He lives at [REDACTED] and stated that the case number is [REDACTED]. called to get more information about property easements and to better understand how close the project will be to his property. 12/22/2025:Nancy forwarded a text to the project team from [REDACTED]. The text contained a letter he posted to the docket requesting intervenor status and outlining his concerns: RE: Case #2025-00346 Prestonsburg-Thelma Transmission Line Rebuild our property located: [REDACTED], Hager Hill, KY 41222 Dear PSC: I trust you have had good holidays, with more ahead this month. This request for intervention is in regards to the above noted case and property in Johnson County, Kentucky. We have received notice that the Prestonsburg-Thelma Transmission line rebuild may affect our property, and have the following concerns: 1. Will this new proposed route cross our property or be close enough to be within visual sight of our property. This is a request for an accurate and detailed map of the transmission route including the boundaries of our property estate at [REDACTED] Hager Hill, KY 41222. 2. Will the construction of towering electric poles, if close or in line of sight, destroy the pristine view from our property, a good parcel (50ac m.o.l in our hollow), that from its high points on our ridge has had a clean unobstructed view that is unchanged since the time of Daniel Boone, who traversed these ridgelines in eastern Kentucky. 3. Will these electric poles and line, if close to our estate, create potential dangers, hazards, and financial loss from Electromagnetic Radiation proximity, loss of practical use of land or future use of land and development, devaluations of adjacent land, sound disturbances from buzzing/humming electric lines, changes in wildlife abundance and biodiversity on our property, and increase risk for fires and other risks that may affect us, our property and our insurance. 4. Why is the line being moved from the current locations/easements, to create and entirely new path through properties previously unaffected. I understand this project is under review, so please contact me as soon as possible to discuss by phone at [REDACTED], and forward a detailed map at your earliest convenience to: [REDACTED], [REDACTED] Tallahassee, FL 32317. Thank you for your time and consideration. | 12/12/2025: Nancy attempted to return [REDACTED]'s call 2x. [REDACTED]'s mailbox is full and we cannot leave a message. Nancy also attempted a text to the same number, but has not received a response. 12/15 and 12/16: Nancy again attempted to connect with [REDACTED], but was unsuccessful in reaching him via phone. 12/23/2025: Natalie Robertson (Siting) noted that we can discuss [REDACTED]'s comments in more detail on the upcoming project team call (scheduled for Monday, January 5). 12/24/2025: Nancy texted [REDACTED] to acknowledge multiple attempts to reach him via phone and to let him know his comments were shared with the project team. 01/05/2026: During the project team call, the group asked Nancy to reach out via text once more and ask [REDACTED] if he would be available for a TEAMS call to discuss his comments. [REDACTED] responded that he is available Thursday, January 8, 2026 at 10am Eastern. Nancy set up the TEAMS call and invited Project Management, TLine, Construction Management, ROW, Siting and Outreach as requested. Nancy confirmed the call via text w/ [REDACTED] and let him know the meeting was scheduled through his email. 01/08/2026: Allen Hodges, Greg Ullom, Jacob Arwood, Natalie Robertson and Nancy Miller met w/ [REDACTED] to review his comments to the PSC docket. The current proposed line does not cross [REDACTED]'s property. However, [REDACTED] is concerned that at least 10 acres of his parcel is missing from the county records. He believes his property extends to the east and northeast of where the project team has his parcel lines drawn and it may clip the edge of the right-of-way to the northwest. [REDACTED] has a deed in storage and will share it with the project team when he can. We noted that the county records are used to notify landowners about the project and more detailed surveys and title work will be completed to determine exact easements as the project moves forward. [REDACTED] noted that the change to his viewshed will be "a big deal" and a "major change" from the pristine views he currently enjoys. The project team confirmed the tower nearest his home is about 815 feet away and will be between 70 and 80 feet tall. A second tower in the area will be about 100 feet tall. [REDACTED] also asked why the route is being changed and Natalie provided an overview of the siting rationale. [REDACTED] believes we need to fully delineate the property lines to be more exact and fully review the distances from residences to the line. Nancy will send [REDACTED] the link to the website and note which maps his property is visible on. After the meeting, Nancy sent [REDACTED] maps 6 and 7, shared the project website with [REDACTED], asked him to send a copy of his deed when he gets a chance, and invited [REDACTED] to reach out with any additional questions. 01/12/2026: NRobertson asked Nancy to reach out to [REDACTED] to find out if he would appreciate visual simulations of the route from his property. Nancy emailed [REDACTED] to determine his interest and he affirmed he would appreciate seeing the visual simulations. Siting will develop the VS and share them with Outreach to forward to [REDACTED].
FRI | 2025-12-19 | [6 empty] | END OF COMMENT PERIOD | END OF COMMENT PERIOD
MON | 2026-01-05 | 9:57 | US Mail/ Incoming | [REDACTED] | 106 | 8,9 | Margot Bond-Downey, ERM | Address (Property): [REDACTED], Van Lear, KY 41265 Address (Mailing): [REDACTED], [REDACTED], [REDACTED], Marietta, OH Found the content informative: checked Yes Additional Comments: Looking at the enclosed map it looks like this Project is going to take a large piece of my property. My concern is how close will this come to my home I live in. How safe is it to live close to those power lines. A big concern is when the trees are removed will cause a drainage problem pushing water down on my house. I would like to talk to someone who can give me more details about this project and what kind of impact its going to cause involving where I live. My contact information is listed above. | Nancy spoke with [REDACTED]. She has concerns about the safety of living near the power lines, would like to know how far the line will be away from her home and how much of a "path" would be cleared (how many trees will she lose?). She also has concerns about the drainage down to her property after the trees are removed (the home is in a lower spot and already experiences some drainage issues). She is also wondering if the route on the maps is final. [REDACTED] mentioned that someone had been to her property to conduct studies "looking for cemeteries in the area". Nancy noted that we have filed the route with state regulators and explained that, if the project is approved, the final ROW will be approximately 100 feet. Nancy also noted that [REDACTED]' comments have been shared with the project team for additional consideration. [REDACTED] was appreciative of the call and would like to talk with a ROW agent about next steps as well as an engineer regarding the drainage concerns. 01/05/2026: On the project team call, the group asked Nancy to let [REDACTED] know that the team is reviewing her comments and we will get back to her with additional information as it becomes available and to let her know the ROW team will be reaching out in the coming months regarding next steps in the process. ROW provided a couple of brochures on EMF and Amanda DeHaven is checking with Nicole Hodges to confirm they can still be used (somewhat outdated, but the only materials currently available). Nancy emailed [REDACTED] with the requested updates and will reach out again as additional information is available for [REDACTED]. 01/14/2026: Nancy forwarded [REDACTED] the approved KYPCO EMF brochures and let her know the team continues to work on the other aspects of her comments. Nancy reiterated that we will reach out as we move through the process.

## Landowners 2022-May 2024
DAY | DATE | TIME (ET) | TYPE Phone/Voice Mail Email/US Mail In Person/Virtual | CONTACT VEHICLE or LOCATION | LO ID | MAP | TEAM MEMBER | NOTES Feedback Comments Questions | FOLLOW UP/ACTION ITEMS
FRI | 2022-11-18 |  | US Mail/Outgoing | Project Announcement Postcard |  |  |  | OH Invite postcard sent to all affected LO in the project area (412 landowners on mailing list)
FRI | 2022-11-25 |  | US Mail/Outgoing | Project Announcement Packet |  |  |  | Mailing sent to all affected LO in the project area - Cover letter - Project Overview Factsheet - Comment Card - Return address envelope (AEP Roanoke)
MON | 2022-11-28 |  | Voicemail | phone | 13 | 5 | McKenzy Moreno | Hi, my name is [REDACTED]. I received one of these postcards in the mail that says that your transmission line from Thelma to Prestonsburg may have something to do with my property. I cannot read your study line maps and where it crosses from 23 back to 321. Now I did get some of the gentlemen at the parent company to try and pull some of this stuff up, but I still don't. I can't tell enough from the map to tell where the base Branch Rd is. If you don't care, could you give me a call back and tell me if this actually in the state lines are actually near on my property or if I will be getting a map that indicates where any of these roads actually are and where the river is and where the crossover is. My phone number is [REDACTED]. Thank you. | 12/1/2022: MM followed up via email. Hi [REDACTED] – I am contacting you today in regards to your questions left on November 28 and 30. Since your property is near a proposed route, we like to notify you to make sure you are made aware of any projects and provide updates. I ran your address through our interactive map on the project website and saw that one of the proposed routes will cross Bays Branch Rd, near CR-1514A. I’ll include a screen shot below for your reference. As this a proposed route out of multiple, our siting team is reviewing all routes at this time and processing all feedback received from landowners to ensure the route chosen works for the community. As a reminder, we are hosting an open house at the Big Sandy Community and Technical College on December 5. There will be multiple subject matter experts in attendance to answer any and all questions you may have. In addition, please feel free to submit a comment card via mail (provided in the landowner packet), the website or the open house. 11/30/2022: MM tried to leave VM. 11/28/2022: MM tried to leave VM.
MON | 2022-11-28 |  | Voicemail | email | 107 | 18 | McKenzy Moreno | Hi, My name is [REDACTED]. My husband and I saw the transmission line project on the website. We live at [REDACTED] Paintsville, Ky. We would like to know if this project is going to effect our home. The line goes over our garage. We didn’t know if this was something we should be following on the town hall meetings. Our concern is are the lines going to be replaced, widened or more high voltage. Please give me a call at [REDACTED] or you may contact me by email at [REDACTED] | 11/30/2022: See line 2 - 4 11/28/2022: MM tried to leave a VM.
TUE | 2022-11-29 |  | Voicemail | email | 107 | 18 | McKenzy Moreno | From: [REDACTED] Email: [REDACTED] Address: [REDACTED] City: Paintsville State: Ky Zip: 41240 Message: My husband and I saw our home on this mapping. We were concerned if we needed to following the town hall meetings. How this would affect our property? The powerline runs over our garage and we had concerns if the lines would be wider and the voltage. Thank You | 11/30/2022: MM called and spoke to her. She mentioned her and her husband were thinking about selling their home but needs more clarity on how/if the project will effect them. Confirmed her address on the interactive map on website. Confirmed her property is near the line that will be retired and a proposed study segment. Reminded her of the open house on 12/5 and told her SMEs will be there to answer all her questions. Also, I let her know she can submit a comment card from the one sent to her or at the open house. She and her husband are planning to attend.
WED | 2022-11-30 |  | Voicemail | email | 107 | 18 | McKenzy Moreno | [REDACTED] She and her husband are calling about the Middle Creek Prestonsburg Line as they notice it is over their home. They are asking for someone to call them back to see what kind of impact they will have. | 11/30/2022: MM called and spoke to her. She mentioned her and her husband were thinking about selling their home but needs more clarity on how/if the project will effect them. Confirmed her address on the interactive map on website. Confirmed her property is near the line that will be retired and a proposed study segment. Reminded her of the open house on 12/5 and told her SMEs will be there to answer all her questions. Also, I let her know she can submit a comment card from the one sent to her or at the open house. She and her husband are planning to attend.
THU | 2022-12-01 |  | Ecomment | email | 13 | 5 | McKenzy Moreno | From: [REDACTED] Email: [REDACTED] Address: [REDACTED] City: East Point State: KY Zip: 41216 Message: From what I can see on Aerial Map 5, the study line does not cross me. Why did I get the post card and what part of the study affects my property? | 12/1/2022: MM followed up via email. I am contacting you today in regards to your questions left on November 28 and 30. Since your property is near a proposed route, we like to notify you to make sure you are made aware of any projects and provide updates. I ran your address through our interactive map on the project website and saw that one of the proposed routes will cross Bays Branch Rd, near CR-1514A. I’ll include a screen shot below for your reference. As this a proposed route out of multiple, our siting team is reviewing all routes at this time and processing all feedback received from landowners to ensure the route chosen works for the community. As a reminder, we are hosting an open house at the Big Sandy Community and Technical College on December 5. There will be multiple subject matter experts in attendance to answer any and all questions you may have. In addition, please feel free to submit a comment card via mail (provided in the landowner packet), the website or the open house.
MON | 2022-12-05 | 9:11am | Voicemail | phone | 361 | 2,3 | McKenzy Moreno | My name is [REDACTED]. Telephone # is [REDACTED]. I'm calling regarding the Prestonsburg-Thelma Transmission Line Rebuild Project. I'm a property owner, please return my call. | 12/7/2022: MM called [REDACTED]. Her family has a land grant from Governor of Virginia from the 1800s. It is what is left from that land grant. Stephens branch Road, approximately a 1/2 mile, has about 37 houses and approx. 100 people. It would disrupt her property which has a cemetery on it with her ancestors going back till 1800s up to 1960s. Also, two gas wells on are on the property. The house on the property has been recently renovated. She depends on it for her income. She rents it out to traveling nurses. If you go through my front yard, you destroy my income. The map is prior to 11 years old. The area is served by Big Sandy RRC. Received the mailing on Monday, but couldn't come to OH because she doesn't live in the area. She's in favor of progress, but will seek legal action if AEP goes through her property. There is one well at top of mountain and one at the bottom. 12/7/2022: NM left her a voicemail and let her know the team is in transit back from Open Houses, but we will try again to reach out to her later today or tomorrow. 12/8/2022: NM left a message requesting a call back.
TUE | 2022-12-06 | 11:38am | Voicemail | phone | 361 | 2,3 | McKenzy Moreno | My name is [REDACTED]. Telephone # is [REDACTED]. I'm calling regarding the Prestonsburg-Thelma Transmission Line Rebuild Project. I received something in the mail saying you were going over my land and I'm very concerned. I want to know where you're going and details and looking at the map, from what I can tell you, it appears you're going right through my front yard and the hay field. Would you please call and this is the second time that I've called and I respectfully ask that you give me a call? Thank you. | See line 9
WED | 2022-12-07 | 10:03am | Voicemail | phone | 361 | 2,3 | McKenzy Moreno | My name is [REDACTED]. Telephone number [REDACTED]. I'm calling about the Prestonsburg Thelma Transmission Line Rebuild Project. I'm a property owner. This is the third time I've called. Please return my call. Thank you. | See line 9
MON | 2022-12-05 | 5:30pm | In-Person | Project Open House |  |  |  | Big Sandy Community and Technical College 31 attendees
MON | 2022-12-05 |  | In Person | OH Comment Card | 204 | 22,24 | Monica Zattera | Email: [REDACTED] Phone: [REDACTED] Address: [REDACTED] City: Paintsville State: KY Zip: 41240 Message: Thank you for the opportunity to discuss the proposed routes. [REDACTED] will be cooperative. | 12/13/2022: No additional follow up needed Logged 12/12/22 MZ
MON | 2022-12-05 |  | In Person | OH Comment Card | 343 | 17,19,20 | Monica Zattera | Email: [REDACTED] Phone: [REDACTED] Address: [REDACTED] City: Meally State: KY Zip 41234 Message: -How much compensated for timber and coal? -What are the landowners rights to the right away? -If use pre existing road- who is responsible for upkeep- -Will property taxes/ value go down. - Vegetation management- NO SPRAY! | 12/15/2022: MM followed up with him and will forward his questions to siting/ROW for assistance with answering his questions. Logged 12/12/22 MZ
MON | 2022-12-05 |  | In Person | OH Comment Card | 230 | 1,2 | Monica Zattera | Email: [REDACTED] Phone: [REDACTED] Address: [REDACTED] City: State: Zip: Message: Option 3 would cross the end of our driveway, and would require clearing some trees on or near our property. We would prefer option 2. | 12/15/2022: MM followed up via email I’m contacting you today in regards to your comment card that you submitted at the project open house on December 5. I have logged your comment and will notify siting of your route preferences. I appreciate your feedback! Logged 12/12/22 MZ
MON | 2022-12-05 |  | In Person | OH Comment Card | 107 | 18 | Monica Zattera | Email: [REDACTED] Phone: [REDACTED] Address: [REDACTED] City: Paintsville State: KY Zip: 41240 Message: We live at [REDACTED] the Power line runs across our garage. We are aware of being in the right away. We have looked at Projected routes. We would be willing to work with AEP to acquire our property to make it more cost efficient for AEP to follow the existing route. Sincerely, [REDACTED] | 12/15/2022: MM followed up via email. Thanks for attending our open house on December 5. I have logged your comment card. If you have additional questions or comments, please feel free to follow up. Logged 12/12/22 MZ
MON | 2022-12-05 |  | In Person | OH Comment Card | 108 | 18 | Monica Zattera | Email: [REDACTED] Phone: [REDACTED] Address: [REDACTED] City: Paintsville State: KY Zip: 41240 Message: the power line comes across our road; If the new lines require a broader path we would be willing to work with AEP on requiring our property. | 12/15/2022: MM followed up via email Thanks for attending our open house on December 5. I have logged your comment card. If you have additional questions or comments, please feel free to follow up. Logged 12/12/22 MZ
MON | 2022-12-05 |  | In Person | OH Comment Card |  |  | Monica Zattera | Email: [REDACTED] Phone: [REDACTED] Address: [REDACTED] Message: please copy of map 18 and 19 topo and aerial | 12/15/2022: MM followed up via email. Need to follow up with Siting for topographic map of parcel 18 and 19. Thank you for attending the open house on December 5. I have reviewed your comment card and have attached copies of aerial map 18 and 19. I am following up with our siting team for the requested topographic maps. I will send those over once received. Logged 12/12/22 MZ
MON | 2022-12-05 |  | In Person | OH Comment Card | 374 | 14 | Monica Zattera | Email: [REDACTED] Phone: [REDACTED] Address: [REDACTED] City: Russell State: KY Zip: 41169 NO substantive comments on card. | 12/13/2022: No follow up needed Logged 12/12/22 MZ
SUN | 2022-12-11 | 9:24p.m. | Ecomment | email | 8 | 17 | McKenzy Moreno | From: [REDACTED] Email: [REDACTED] Address: [REDACTED] City: Van Lear State: KY Zip: 41265 Message: Hello, I currently live at [REDACTED] Van Lear, Ky 41265 and own a piece of property above 415. The address of that property is [REDACTED] Van Lear, Ky 41265. I received a letter in the mail informing of the Prestonsburg-Thelma Transmission Line Rebuild Project. Can you please let me know if either of these properties will be affected? Also, can you please let me know what aerial map is for this specific area. | 1/4/2023: Property 1 Address: [REDACTED] Van Lear, Ky 41265 The H-Frame structures need to be moved away from homes. Shown below is an actual picture of the current path of the H-Frame structures. My property is highlighted shown below from Aerial map 17. I think moving the H-Frame structures to the study segment is a good location. However, the lattice towers should stay where there currently located on the right side. LO inserted a screenshot of aerial map 17 as well as a picture of transmission lines near the LOs property. Property 2 Address: [REDACTED] Van Lear, Ky 41265 My property is highlighted shown below (166) I think moving the H-Frame structures to the study segment is a good location. However, the lattice towers should stay where there currently located on the right side. LO inserted a screenshot of aerial map 18. 12/13/2022: MM followed up with a snapshot of the structures to be used and let him know that h-frame would be the majority. 12/12/2022: Mr. [REDACTED] followed up and inquired about structure type. 12/12/2022: MM emailed him and let him know that both properties were near one of the proposed routes. Clarified that we're early in the process and that no routes have been chosen at this time. Sent screen shots of his properties as they relate to the routes. Also, attached aerial map 17 -- the location of both properties.
WED | 2022-12-14 |  | US Mail | Comment Card | 198 | 16, 17 | McKenzy Moreno | From: [REDACTED] Email: [REDACTED] Address: [REDACTED] City: Van Lear State: KY Zip: 41265 Message: No substantive comments on card. | 12/14/2022: Logged. No follow up needed.
THU | 2022-12-14 |  | US Mail | Comment Card | 395 | 19, 20, 21 | McKenzy Moreno | From: [REDACTED] Email: Address: [REDACTED] City: Paintsville State: KY Zip: Message: I am located just off of KY Route 1145, I do not for see any concerns. | 12/14/2022: Logged. No follow up needed.
FRI | 2022-12-14 |  | US Mail | Comment Card | 364 | 10 | McKenzy Moreno | From: [REDACTED] Email: [REDACTED] Address: [REDACTED] City: Auxier State: KY Zip: 41602 Message: No substantive comment on card. . | 12/14/2022: Logged. No follow up needed.
SAT | 2022-12-14 |  | US Mail | Comment Card | 387 | 23, 25 | McKenzy Moreno | From: [REDACTED] Email: Address: [REDACTED] City: Thelma State: KY Zip: 41260 Phone: [REDACTED] Message: No substantive comment on card. . | 12/14/2022: Logged. No follow up needed.
TUE | 2022-12-20 |  | US Mail | Comment Card | 33 | 16 | Monica Zattera | From: [REDACTED] Email: [REDACTED] Phone: [REDACTED] Address: [REDACTED] City: Van Lear State: KY Zip: 41265 Message: Will the transmission lines and structures running across Richmond Hill, Van Lear to old Am. Standard Plant (Kenwood Substation) be completely removed? | 1/4/2023: MM called a left a VM. 12/21/22 Logged MZ
TUE | 2022-12-20 |  | US Mail | Comment Card | 13 | 5 | Monica Zattera | From: [REDACTED] Email: [REDACTED] Phone: [REDACTED] Address: [REDACTED] City: East Point State: KY Zip: 41216 Message: 2013- home directly at base of hill. Hill already has small break from past constructions, 100+ old trees uprooting, underground water from coal scams etc. Any type of further ground disturbances on my hill or any adjoining ground would result in catastrophic damage to the hill behind my home resulting in hillslide that would destroy my home. Brand beside my home has 250’ concrete drainage tiles starting at back of my house. Branch starts at top of hill behind and beside my home carrying the water run off from the surrounding hills on my property to adjoining property. Accumulating debris blocking my tiles would put my home in direct path of water run off. Property 232 Bayes/Marshall Cemetery-gravesites property 048 George Baldridge Cemetery top of hill from civil war. Top of hill. | 1/4/2022: MM followed up with her. She wanted to know when a proposed route would be chosen. I told her tentatively in February but that is subject to change. Also, let her know that we would communicate to LOs when a route is chosen and that after one is ROW will be in contact with those LOs. 12/21/22 Logged MZ
TUE | 2022-12-20 |  | US Mail | Comment Card | 346 | 1 | Monica Zattera | From: [REDACTED] Phone: [REDACTED] Address: [REDACTED] City: Hagerhill Message: I would like to meet on scene to determine exact placement | 2/28/2023: MM followed up for email. Sent siting response and map to [REDACTED]@gmail.com 1/31/2023: MM tried to call and get an email from him to send siting's response and detailed map. 1/4/2023: I own a lot of property in Johnson and Floyd counties. Wants to know if his property on [REDACTED] will be effected by the line that is being retired. It runs along the right side. How will the line be retired? Will the poles be removed? There is an out building seller on that land. They can be moved but he needs to let them know if they need to be moved. Asked for his personal email: [REDACTED]@gmail.com. He said he's more of a visual person, so if someone could send him a map of his property with an explanation of the impact or even go over it with him on Google Earth via phone. 12/21/22 Logged MZ
TUE | 2022-12-21 |  | Voicemail | phone/email | 326 | 22 | McKenzy Moreno | [REDACTED]. Area code [REDACTED]. The project is Prestonsburg-Thelma Transmission Line Rebuild Project. I was trying to get some information, perhaps [??] some information. I appreciate it. Thank you. | 12/28/2023: Followed up with email 12/21/2023: Attempted to leave VM but line kept ringing
TUE | 2022-12-21 |  | Voicemail | email | 326 | 22 | McKenzy Moreno | This is [REDACTED] again. I forgot to leave some information when I last spoke. My email address is [REDACTED]. My sister's is uh [REDACTED]. Thank you. | See line 28
TUE | 2023-01-03 |  | US Mail | Comment Card | 37 | 24 | McKenzy Moreno | From: [REDACTED] Phone: [REDACTED] Address: [REDACTED] City: Paintsville, KY 41240 Email: [REDACTED]@gmail.com Message: No substantive comments on card. | 1/4/2023: MM logged. No additional contact needed
TUE | 2023-01-03 |  | US Mail | Comment Card | 362 | 22, 24 | McKenzy Moreno | From: [REDACTED] Phone: [REDACTED] Address: [REDACTED] City: Paintsville, KY 41240 Message: No cemetery on my property. | 1/4/2023: MM logged. Will follow up.
TUE | 2023-01-03 |  | US Mail | Comment Card | 57 | 17 | McKenzy Moreno | From: [REDACTED] Phone: [REDACTED] Address: [REDACTED] City: Van Lear, KY 41265 Email: [REDACTED] Message: A lot of the electrical wires are now strung in our yard. Will this be routed to the hills in front or behind our houses on the hills? There is a lot of old mines shafts in the hill behind our houses from underground mining by Consolidated Coal Company. Many years ago. There is also an old cemetery on the hill behind our home on the top of the hill. This will be a great improvement for this area. When the power goes off in Meally, KY, our power goes of here. | 2/28/2023: MM called back to get updated email to send siting response. Got email and map and response sent. 1/31/23: Previous email is no longer working, so followed up to get another. 1/31/2023: Followed up w/ siting's response. Attached map and asked for LO to indicate cemeteries/gas line on property. 1/4/2023: MM logged. Reached out to the LO. MM to contact siting on routing question
WED | 2023-01-04 |  | Phone |  |  |  | Ryan Howell | RH spoke with the LO on the phone to discuss preferred route segments | 1/4/23: LO followed up with an email explaining his preferred route and provided a screenshot w/ markings of the preferred and not preferred route. "As mentioned on our call, I spoke with the landowner [REDACTED] who is effected by one study segment of our Prestonsburg – Kenwood line. [REDACTED] stated that he’d rather our line not effect the right side of his property, as he would like to potentially develop that area as a house seat. His preference is for the line to be located on the western side of the property. "
THU | 2023-01-05 | 8:37pm | Email | phone/email | 326 | 22 | McKenzy Moreno | Ryan Howell: One of the projected courses of the power line may cross my land from about [REDACTED] I cannot discern the exact path of the power line as it passes through this area I can't reconcile my memories about it with the small map which was provided by AEP. Would AEP have any map available which would give more definitive information on the proposed path ... especially as it might relate to the USGS locations as above. I would prefer that AEP would use the route directly south from the Thelma Substation, which does not cross my land. I have since located an aerial map found at: “https://www.aeptransmission.com/Kentucky/Thelma/” which shows clearly that the proposed new route passes nearly exactly through the center of the area I would most like it to avoid. The map ‘aerial map 22’, which is named ‘OpenHouse_Aerial_Mapbook_Combined_Prestonsburg_Thelma_22x34P_Part23.pdf’ shows this. The area which I would most like to avoid is shown on the map where the label “City of Paintsville” is present. This is the area which was used to put the excess dirt and rubble created by the completion of route 1107 (also on map). Judging from the aerial map, the proposed transmission line is considerably offset from the former transmission line. I wonder if this is truly the case or if the lines shown on the map are approximations. I had hoped to improve this area & the fill area once the rubble was sufficiently settled ... A high tension line at this spot would certainly impact that possibility. The property is listed with the city of Paintsville in the name of [REDACTED] 1. Description 18.77 acres. 2. The location [REDACTED] 3. Map number [REDACTED] 4. Deed book page [REDACTED] This property is now within the city limits of Paintsville. I would appreciate your comments. I receive email (which works best for me) @anytime. Sincerely, [REDACTED] [REDACTED] | 1/31/2023: Followed up via email with siting's response and detailed map. 1/5/2023: Logged by MM. Sent another email telling him his comment as been logged and shared with siting. Asked if he will be needing additional mapping materials.
| 2023-01-04 | [6 empty] | END OF COMMENT PERIOD | END OF COMMENT PERIOD
MON | 2022-01-09 | 9:37am | Phone | email/phone | 361 | 2,3 | McKenzy Moreno | From: [REDACTED] Email: [REDACTED] Address: [REDACTED] City: Tallahassee State: FL Zip: 32311 Message: I moved to FL. My family and I plan to develop the flat land at [REDACTED] 41653 into at least 20 high end building lots. KY Power going thru the center would make this impossible. City water, sewer already on property. Natural gas well on edge of bottom land, with cheap gas rates. Please change power line destination from going over my property. | 1/9/22: MM logged and called LO to let her know I had logged her comment and told her to follow up w/ additional questions. Will send siting consideration over to siting team
MON | 2023-01-09 | 12:07pm | Phone | email | 107 | 18 | McKenzy Moreno | From: [REDACTED] Email: [REDACTED] Address: [REDACTED] City: Paintsville State: KY Zip: 41240 Message: Hi we were wondering if a route has been determined between Prestonsburg and Thelma. We spoke with you at the Open House at Paintsville on December 5. Thank You | 1/9/23: RH followed up w/ LO via email " Hello [REDACTED], Thanks for you response. As of right now, those determinations are still under review and have not been made. The routes are set to be reviewed and completed in the month of February. Once a final route has been identified, if you're property is still affected, you'll receive additional follow up information from out team."
TUE | 2023-01-10 |  | US Mail | Comment Card | 361 | 2,3 | McKenzy Moreno | From: [REDACTED] Email: [REDACTED] Phone: [REDACTED] Address: [REDACTED] City: Tallahassee State: FL Zip: 32311 Do you find the content provided to be informative? Very vague. Had to do extensive research to know what proposal entail re:my property. Message: I moved to FL. Have concerns regarding proposed easement, which would go thru center of acreage of level land. This would limit any further development of this property. My family and I have current plan to divide flat land into approximately 20 high end house seats. Property in "city limits" with water & sewer. Gas well located base of level land with cheap gas rates, family cemetery from 1800's few feet from proposed rebuild section. Moving line to head of Stephens Branch [??] and Best Ln, or in the other direction toward Goodman property would love no interference from hilltop to hilltop. | 1/17/2023: Logged and followed up via email. I am following regarding the comment card you mailed in. I have logged your concerns and will share with our siting team to use in their routing process. Thanks so much for your feedback. Feel free to contact with additional questions or comments.
MON | 2023-01-31 |  | US Mail | Comment Card | 16 | 23, 25 | McKenzy Moreno | From: [REDACTED] Email: [REDACTED] Phone: [REDACTED] Address: [REDACTED] City: Hager Hill State: KY Zip: 41222 Message: My property is currently encumbered by two powerlines. The study segment area in Thelma would cross my property in a third location. I purchased property with the intent of building a cabin. The proposed powerline would eliminate any and all ability to build on this property. Also, the property boundaries on your maps are incorrect. I purchased a portion of the tract you have owned by [REDACTED]. I'm enclosing a copy of the deed for this additional tract. | 2/1/2023: MM called a tried to leave a VM. Followed up via email. "Hi Ms. [REDACTED] – I am contacting you today to let you know that we received your comment card. I have logged it and will forward over to our siting team to use for proposed route consideration. Please feel free to follow up with me via email or phone with additional questions or concerns.
MON | 2023-01-31 |  | US Mail | Comment Card | 141 | 23 | McKenzy Moreno | From: [REDACTED] Email: [REDACTED] Phone: [REDACTED] Address: [REDACTED] City: Paintsville State: KY Zip: 41240 Message: I protest the line crossing my property. | 2/1/23:MM called and talked to [REDACTED]. See line 38. They live together and I was able to communicate that we've received their comments card and I forwarded it over to siting. She asked when a route would be determined, and I told her to follow up mid-February.
MON | 2023-01-31 |  | US Mail | Comment Card | 112 | 6 | McKenzy Moreno | From: [REDACTED] Email: [REDACTED] Phone: [REDACTED] Address: [REDACTED] City: Auxier/East Point State: KY Zip: 41602/41216 Message: Our concern is that a powerline and ride of way will take or render our property nonusable. We have a house and barn on the upper bottom and my son lives in the house. We have prepared two house seats on the other end for our other son and family members. Therefore we would like to see this go in another direction. We could not replace our property of (??) structures or cover the cost of replacement. | 2/1/23: MM called and left a VM
THU | 2023-02-09 |  | Email | email | 339 | 13 | McKenzy Moreno | From: [REDACTED] Email: [REDACTED] Address: [REDACTED] City: Paintsville State: KY Zip: 41240 Message: Including comments for my immediate family location at [REDACTED] Van Lear, KY 41265, and my parents, [REDACTED], [REDACTED] Van Lear, Ky 41265. Property ownership of these properties dates back to the 1800's. There are two family cemeteries and an Indian mound located along the rebuild section 13, in Johnson and Floyd counties. We request other routes be pursued for this project rather than the two that impact our properties. Suggest the straight line route (shortest distance between two points) be pursued. | 2/14/23: MM followed up via email. Ryan CC Siting team to highlight concerns for proposed route consideration
TUE | 2023-02-14 |  | US Mail | Comment Card | 339 | 13 | McKenzy Moreno | From: [REDACTED] Email: [REDACTED] Address: [REDACTED]Van Lear, KY 41265 City: Paintsville State: KY Zip: 41240 Phone: [REDACTED] Message: Property family ownership dates to 1800's. 2 cemeteries on property -- one directly behind home, other on Floyd county side one 1800 burials, including [REDACTED](my great great grandfather). An Indian mound is also referenced on deed near the cemetery. Our impacted property is section 13 on map, we respectfully request other routes are pursued for this property. Prefer our home won't be located in close proximity to transmission line. | 2/14: MM followed up via email. Ryan CC Siting team to highlight concerns for proposed route consideration.
TUE | 2023-02-14 |  | US Mail | Comment Card | 339 | 13 | McKenzy Moreno | From: [REDACTED] Email: [REDACTED] Address: [REDACTED] Van Lear, KY 41265 City: Paintsville State: KY Zip: 41240 Phone: [REDACTED] Message: Property family ownership dates to 1800's. 2 cemeteries on property -- one directly behind home, other on Floyd county side one 1800 burials, including [REDACTED] (my great great grandfather). An Indian mound is also referenced on deed near the cemetery. Our impacted property is section 13 on map, we respectfully request other routes are pursued for this property. Prefer our home won't be located in close proximity to transmission line. | 2/14: MM followed up via email. Ryan CC Siting team to highlight concerns for proposed route consideration.
TUE | 2023-02-14 |  | US Mail | Comment Card | 10, 11 | 13,16 | McKenzy Moreno | From: [REDACTED] Address: [REDACTED] Van Lear, KY 41265 Phone: [REDACTED] Message: Family property ownership dates to 1800's. Two family cemeteries located on property -- one directly on hillside behind daughters home @ [REDACTED] & one on Floyd county side with 1800 burials, including [REDACTED] my great grandfather. An Indian mound is also referenced on deed near the cemetery. Our impacted property includes section 13 perhaps including other surrounding sections. Respectfully requesting that other routes are pursued for this project. Request our home and surrounding properties not be located in close proximity to transmission line. | 2/14: MM followed up via phone. She has no additional questions.
FRI | 2023-02-24 |  | Email | email |  |  | Nancy Miller | [REDACTED] reached out to Ryan Howell with the following email: Please take notice that I have not received any information via US Mail or any other means about the rebuilding of the Prestonsburg - Thelma Transmission Line. This potential project effects my property which is directly across the Levisa Fork of the Big Sandy River from the Prestonsburg Substation. Thanks, [REDACTED] | 02/27/2024: [REDACTED] reached out to the project team to note that he had not received any additional information. Ryan responded to let [REDACTED] know the project team was collecting some additional information and that we anticipate sending out additional information early summer 2024. 03/06/2023: Nicole responded: Thank you for sending. We will share this with the project team so they can look into the adjusted route. Have a great week, [REDACTED] thanked Nicole for the response. 03/03/2023: [REDACTED] responded as follows: Nicole, I have successfully accessed your attachments and viewed the project website without issue. Your proposed route shown in black would impact a spread of rhododendron maximum on the western face of an unnamed, pristine hollow, which is parallel with and between the Levisa Fork and US 23. The plant is indigenous to the Prestonsburg area, but is found sparingly throughout the region. Apparently, the soil conditions are perfect for its growth. I would appreciate AEP's cooperation in altering its proposed route shown in black to the blue route shown on the attached map. Thanks, [REDACTED] 02/27/2023: RHowell responded to Mr. [REDACTED] and forwarded his inquiry to Outeach. Nicole Hodges r3esponded to Mr. [REDACTED] as follows: Hi Mr. [REDACTED], I want to follow up on Ryan’s email below. Our apologies that you were not on our mailing list for the Prestonsburg-Thelma project. We would be happy to mail you any materials, but in the meantime I’ve attached a map showing where the new transmission line would cross your property before entering the Prestonsburg Substation. You will see that the black transmission line route would replace the existing line in red, which would later be removed. I’ve also attached the fact sheet for the project. You can view all of our project materials on the website at KentuckyPower.com/Thelma. Please let me know if you have any questions or comments for the project team, or if you’d like me to mail you any physical copies of the project materials. Thank you!
TUE | 2023-02-28 |  | Voicemail | phone | 13 | 5 | McKenzy Moreno | [REDACTED] called a left a VM inquiring about any project updates. | 2/28/2023: MM followed up and let her know a proposed route in scheduled to be chosen in March and that LO along the route would be notified
TUE | 2023-04-18 |  | Voicemail | phone | 361 | 2,3 | McKenzy Moreno | My name is [REDACTED]. Telephone number [REDACTED]. I'm calling regarding the Prestonsburg Thelma Transmission Rebuild Project. I'm a property owner in that area that apparently is being affected. Please call me as soon as possible. Thank you. | 4/20: MM called and tried to leave a VM for [REDACTED].
THU | 2023-05-11 |  | US Mail/Outgoing |  |  |  | Nicole Hodges | The proposed route letter was sent to 410 recipients
THU | 2023-05-25 |  | Voicemail | phone | 75 | 24, 25 | Nancy Miller, McKenzy Moreno | We got a call on the voice mail from: [REDACTED] He is asking what we need from him based on the letter he received. | 5/25/2023: [REDACTED] did not have the letter with him when I called him back, but he did recall that it was for the Prestonsburg-Thelma project. He said he is fine with the route going across his property as long as it is not going directly over his house (he said it appeared from the enclosed map it was not going over the house). I’m just checking to see what might have been sent and if there is anything specific we need from him. I can check in with Ryan @ ROW as well, if needed
WED | 2023-06-07 |  | Voicemail | phone | 361 | 2,3 | McKenzy Moreno | This is [REDACTED], [REDACTED], property owner regarding the Prestonsburg Thelma Transmission Line Rebuild project. I sent a letter and in response that I am against it is destroying my house and my property. Would you please call me? I'm going to keep calling and calling until someone talks to me. Thank you. | 6/7/2023: MM called and left a VM for her to call back and discuss concerns
THU | 2023-06-08 |  | Voicemail | phone | 361 | 2,3 | McKenzy Moreno | My name is [REDACTED]. Telephone number [REDACTED]. I'm calling regarding the Prestonsburg transmission line rebuild project. I'm a property owner. Would you please return my call? Thank you. | 6/15/23: [REDACTED] returned MM call after receiving the email MM sent on 6/8. She hasn't been receiving any of the VMs MM has left. She relayed that her house/land are currently being lived on my a radiologist as she and her husband moved to Florida. Also, the land has been in her family since 1813 and there is a family cemetery on it. She is willing to work with us and recommends moving any work further up Stephens Branch road, on the next ridge. She has talked to her family and will take legal action if we don't work with her. I relayed that we'd of course work with her and that I would forward her concerns over to ROW/Emerald. 6/12/2023: MM left another voicemail and reiterated that I have left multiple VMs and sent an email on 6/8. Also, asked what would be the best time to contact her. 6/8/2023: MM located her comment card w/ email and sent an email. "Hi [REDACTED] – I hope all is well with you! We have been receiving your voice messages on our project line and promptly returning your calls. I have left about three voicemail messages on the [REDACTED] line since yesterday, but I’m not sure if you’re receiving them. If not, please feel free to contact me personally at [REDACTED] or please let me know the preferred time of day you would like me to reach out to you. Thanks for your patience, and I look forward to speaking with you. 6/8/2023: MM called and left another VM at 12:56p.m. I told her I have left 3 VMs (including this one) since yesterday and told her to call me directly (provided by cell #) with her questions . Also, I asked that she provide a preferred time to contact her. 6/8/2023: MM called a left a VM again at 9:22 a.m.
WED | 2023-06-14 |  | Voicemail | phone |  |  | McKenzy Moreno | Yes, this is [REDACTED] and I'm calling for Ryan Howell, a right of way agent on the project that is called the Prestonsburg Thelma Transmission Line Rebuild Project. It's located in Eastern Kentucky. I'm calling on behalf of my mom, [REDACTED]. She's on the phone with me right now. Say hi mom. Hello. And we are just trying to find out how this project may or may not affect her Physical address. The address is [REDACTED]. My call back number is [REDACTED]. | RH called them on 6/14/23. [REDACTED], is the landowners property in question. Her property is not currently impacted by the proposed line route. She only received the notice due to her home be located within the notification area (roughly 2700 ft from the line). [REDACTED], was happy with the information I provided.
WED | 2023-07-19 |  | Email |  | 86 | 1,2 | McKenzy Moreno | Nicole Hodges-project outreach specialist Madam: Your notice of May 12, 2023, to property owners who may be affected by the proposed transmission line rebuild project implies substantial cost to be incurred if the project application is approved by Kentucky PSC. Included in the data to be filed with the application will be cost estimates by Kentucky Power executives and project engineers. The PSC and customers of KY Power will be interested in how KY Power intends to finance and pay for 14 miles of power line construction through newly acquired right of way. KY Power has currently pending before the KY PSC an application to raise rates on its consumers, the proceeds of which, if approved, are earmarked to pay for numerous budget categories, none being earmarked for 14 miles of a rebuild project. How does KY Power plan to pay for the Prestonsburg-Thelma Rebuild Project: by cash on hand; by borrowed funds, either banks of bonds; by selling the company to a foreign entity? Seeking authority from KY PSC to raise rates? I would appreciate a response. Sincerely [REDACTED] [REDACTED] [REDACTED] Prestonsburg, KY 41653 | 7/26/2023: Sarah Nusbaum to provide some talking points about rates to help us respond to the landowner’s concerns about project cost
MON | 2023-12-18 | 2:12p | Voicemail | phone | 361 | 2,3 | Nancy Miller | [REDACTED] left the following voicemail on the project hotline: This is [REDACTED]. The telephone number is [REDACTED]. I'm calling regarding the Prestonsburg-Thelma Transmission Line Rebuild project. Would you give me a call please? Thank you. | 01/04/2024: Nicole Hodges forwarded [REDACTED] comments to Ryan Howell. Ryan responded that he had talked with [REDACTED] previously and outlined her concerns. The project team reviewed [REDACTED] concerns and discussed possible mitigation measures. Ryan Howell spoke with [REDACTED] and shared her concerns with the project team. Project team will take under advisement as they work toward route selection.
FRI | 2024-05-17 | 2:29p | Voicemail | phone | 326 | 22 | Nancy Miller | [REDACTED] emailed Nicole Hodges as follows: I haven't heard from you in quite some time. I would like to know status on the "Prestonsburg - Thelma Transmission Line Rebuild Project". I am a property owner. All the links in my previous information from you have gone dead and get a "403 Forbidden" message. I will look for your reply. Thank you | [REDACTED] did not respond with any questions or additional content and the ticket was closed out. 07/05/2024: Nicole Hodges replied to [REDACTED] as follows: Hi [REDACTED], We received your voicemail and understand you have some questions about the Prestonsburg-Thelma project. I’d be happy to answer whatever ques􀆟ons you have if you’d like to email them to me. Look forward to hearing from you! Best, Nicole 07/01/2024: [REDACTED] left a voicemail on the project hotline: How do you do this is [REDACTED] and I'm calling from area code [REDACTED] about the Prestonsburg Thelma transmission line rebuild project. I'm trying to get some information on it. I'm easier to reach at my e-mail address which is [REDACTED]. That's [REDACTED]. Thank you.

## Stakeholders 2022-23
DAY | DATE | TIME (ET) | TYPE Phone/V Mail Email In Person/Virtual Incoming/Outgoing | CONTACT VEHICLE or LOCATION | FIRSTNAME | LASTNAME | TITLE | ORGANIZATION | TEAM MEMBER(S) | NOTES Feedback Comments Questions | FOLLOW UP/ACTION ITEMS
FRI | 2022-09-16 | 1:00pm | Virtual |  | [REDACTED] | [REDACTED] |  | Floyd and Johnson counties | Bob Shurtleff, AEP External Affairs Lance Blackburn, AEP Project Manager Shelley Campbell, AEP Siting Julia Sexton, Power Engineers Siting McKenzy Moreno, ERM Outreach Cortney Mustard, AEP Outreach Ryan Howell, AEP Right-of-way Scott Woody, AEP Transmission Line Engineer Greg Ullom, Transmission Line Engineer | Floyd/Johnson County Project Update Meeting -- One member of the county hopped on very late but had no questions.