## Sheet1
Bluegrass Water Utility Operating Company LLC
Exhibit PSC 6-24
Case No. 2025-00354
Site | County | CPCN | CPCN Approved | (1)Description | Original project description (CCN application) | (2)Annual actual cost | (3)Annual Original Budget | (4)Percent of Budget | (5)Total Actual Project Cost | (6)Total Budget Project Cost | Updated Total Budget Project Cost | Variance | Variance Percent (final/current cost as percentage of original budget) | Causes of Variance | (7)Original Budget Start Date | (8)Original Budget End Date | (9)Actual Start Date (use award date) | (10)Actual End Date
Persimmon Ridge | Shelby | 2022-00046 | 2022-11-03 | Two-stage sidestream MBBR treatment system Airlifts Blowers Diffusers Sieves Controls Lagoon penetrations for suction and discharge piping MBBR suction/discharge yard piping Air piping Miscellaneous electrical distribution | Two-stage sidestream MBBR treatment system Airlifts Blowers Diffusers Sieves Controls Lagoon penetrations for suction and discharge piping MBBR suction/discharge yard piping Air piping Miscellaneous electrical distribution | N/A | N/A | N/A | 496545 | 492696 | N/A | -3849 | 100.8% | Construction projects are initiated based on the best information available at the time design and bidding activities are completed. However, it is common for modifications to occur between the commencement of a project and its completion as additional information becomes available and conditions are encountered during construction. Changes may result from a variety of factors, including unforeseen site conditions, differing subsurface conditions, the actual status and condition of existing infrastructure and equipment revealed during construction, and conflicts with existing utilities or facilities that were not fully known during the design phase. Adjustments may also be necessary due to material availability, manufacturer lead times, supply chain constraints, discontinued equipment, contractor means and methods, and constructability considerations identified in the field. Additionally, project modifications may be driven by permitting requirements, regulatory agency comments, safety concerns, operational needs necessary to maintain service during construction, weather-related impacts, property access limitations, or coordination with third parties. In some cases, field conditions reveal opportunities to improve the efficiency, reliability, resiliency, or long-term operability of the completed facilities, resulting in revisions to the original construction approach. Accordingly, it is a normal and expected part of the construction process for project scopes, quantities, equipment selections, schedules, and construction methods to be adjusted as work progresses. These modifications are undertaken to address actual field conditions and ensure that the completed project safely, reliably, and effectively meets its intended purpose. While specific project components, construction methods, or equipment selections may evolve during construction, the underlying purpose and operational objectives of the project remain unchanged, with modifications made to best achieve those objectives under actual field conditions encountered during project execution. | 2023-10-04 | 2024-05-30 | 2023-05-03 | 2024-09-30
Woodland Acres | Bullit | 2022-00015 | 2022-09-01 | 1. MBBR Treatment System (KPDES Permit Compliance Upgrades) New MBBR assemblies Blowers and controls Blower pad Blower discharge piping, valves, and appurtenances Electrical distribution for the MBBR system 2. Chlorine tablet and Dechlorination Tablet Disinfection System Two tablet feeders New contact tanks and flow mesurement tank 3. Wet Weather Overflow Prevention System Wet weather storage tank and pad Valves and return piping Diffusers Blower and blower pad Air piping Grinder pump and control panel Electrical distribution Rehabiliatation of influent tank with new tank foundation following tank uplift and new pumps to route to EQ tank 4. Site Improvements All-weather gravel access road serving the new facilities 5. Digester New digester tank with decant lines | 1. MBBR Treatment System (KPDES Permit Compliance Upgrades) New MBBR assemblies Blowers and controls Blower pad Blower discharge piping, valves, and appurtenances Electrical distribution for the MBBR system 2. Peracetic Acid (PAA) Disinfection System PAA equipment and pad Electrical distribution for disinfection equipment 3. Wet Weather Overflow Prevention System Wet weather storage tank and pad Valves and return piping Diffusers Blower and blower pad Air piping Grinder pump and control panel Electrical distribution 4. Site Improvements All-weather gravel access road serving the new facilities | N/A | N/A | N/A | 757581 | 602752 | N/A | -154829 | 125.7% | Construction projects are initiated based on the best information available at the time design and bidding activities are completed. However, it is common for modifications to occur between the commencement of a project and its completion as additional information becomes available and conditions are encountered during construction. Changes may result from a variety of factors, including unforeseen site conditions, differing subsurface conditions, the actual status and condition of existing infrastructure and equipment revealed during construction, and conflicts with existing utilities or facilities that were not fully known during the design phase. Adjustments may also be necessary due to material availability, manufacturer lead times, supply chain constraints, discontinued equipment, contractor means and methods, and constructability considerations identified in the field. Additionally, project modifications may be driven by permitting requirements, regulatory agency comments, safety concerns, operational needs necessary to maintain service during construction, weather-related impacts, property access limitations, or coordination with third parties. In some cases, field conditions reveal opportunities to improve the efficiency, reliability, resiliency, or long-term operability of the completed facilities, resulting in revisions to the original construction approach. Accordingly, it is a normal and expected part of the construction process for project scopes, quantities, equipment selections, schedules, and construction methods to be adjusted as work progresses. These modifications are undertaken to address actual field conditions and ensure that the completed project safely, reliably, and effectively meets its intended purpose. While specific project components, construction methods, or equipment selections may evolve during construction, the underlying purpose and operational objectives of the project remain unchanged, with modifications made to best achieve those objectives under actual field conditions encountered during project execution. In this project several changes from the original project plan also occurred in the final project. First, the planned peracetic acid disinfection system was swapped for a conventional tablet chlorination and tablet dechlorination disinfection system in response to environmental regulatory permitting issues. Second, a polymer digester was added to the project plan when it became apparent the existing digester tank was in too poor condition to rehabilitate and to reduce operational costs related to solids hauling and improve plant function. Finally, during the course of the project the influent tank began to uplift due to groundwater pressure. Excavation was completed around the tank and a new foundation poured to address the tank uplift. | 2023-10-04 | 2024-05-30 | 2023-05-03 | 2025-05-30
Herrington Haven | Garrard | 2022-00102 | 2022-11-07 | 1. MBBR Treatment System (KPDES Permit Compliance Upgrades) New MBBR treatment units Blowers and controls Blower pad Blower discharge piping Electrical distribution 2. Peracetic Acid (PAA) Disinfection System PAA equipment and pad Electrical distribution 3. Solids Processing (Digester) System Digester tank and pad Digester piping and valves Diffusers Blower and blower pad WAS/RAS piping Grinder pump and controls Electrical distribution 4. Site Improvements All-weather gravel access road | 1. MBBR Treatment System (KPDES Permit Compliance Upgrades) New MBBR treatment units Blowers and controls Blower pad Blower discharge piping Electrical distribution 2. Peracetic Acid (PAA) Disinfection System PAA equipment and pad Electrical distribution 3. Solids Processing (Digester) System Digester tank and pad Digester piping and valves Diffusers Blower and blower pad WAS/RAS piping Grinder pump and controls Electrical distribution 4. Site Improvements All-weather gravel access road | N/A | N/A | N/A | 525420 | 525420 | N/A | 0 | 100% | Construction projects are initiated based on the best information available at the time design and bidding activities are completed. However, it is common for modifications to occur between the commencement of a project and its completion as additional information becomes available and conditions are encountered during construction. Changes may result from a variety of factors, including unforeseen site conditions, differing subsurface conditions, the actual status and condition of existing infrastructure and equipment revealed during construction, and conflicts with existing utilities or facilities that were not fully known during the design phase. Adjustments may also be necessary due to material availability, manufacturer lead times, supply chain constraints, discontinued equipment, contractor means and methods, and constructability considerations identified in the field. Additionally, project modifications may be driven by permitting requirements, regulatory agency comments, safety concerns, operational needs necessary to maintain service during construction, weather-related impacts, property access limitations, or coordination with third parties. In some cases, field conditions reveal opportunities to improve the efficiency, reliability, resiliency, or long-term operability of the completed facilities, resulting in revisions to the original construction approach. Accordingly, it is a normal and expected part of the construction process for project scopes, quantities, equipment selections, schedules, and construction methods to be adjusted as work progresses. These modifications are undertaken to address actual field conditions and ensure that the completed project safely, reliably, and effectively meets its intended purpose. While specific project components, construction methods, or equipment selections may evolve during construction, the underlying purpose and operational objectives of the project remain unchanged, with modifications made to best achieve those objectives under actual field conditions encountered during project execution. | 2023-11-14 | 2024-05-30 | 2023-05-03 | 2025-01-30
Delaplain | Scott | 2022-00104 | 2023-03-30 | MBBR, filtration prject (new building and equipment), new effluent pipe, chemical feed (alum), disinfection (PAA), tank rehabilitation, aeration overhaul, site improvements, | 1. MBBR Treatment System (KPDES Permit Compliance Upgrades) MBBR treatment units Blowers and controls Blower pad Piping, valves, and appurtenances Electrical distribution 2. Solids Handling Enhancements Polymer feed treatment system Filter building and foundation Filter equipment Filter backwash piping Filter building pump and sump Relocation of sodium bisulfite feed equipment Electrical distribution for filtration equipment 3. Site Improvements Security fencing All-weather gravel access road The subsequent PSC order summarized the approved scope as: Installation of an MBBR treatment system to address ammonia and BOD permit compliance issues. Installation of a polymer feed and tertiary filtration system to improve solids settling and effluent quality. | N/A | N/A | N/A | 2412387.13 | 2107220 | 2634000 | -305167.13 | 114.5% | Construction projects are initiated based on the best information available at the time design and bidding activities are completed. However, it is common for modifications to occur between the commencement of a project and its completion as additional information becomes available and conditions are encountered during construction. Changes may result from a variety of factors, including unforeseen site conditions, differing subsurface conditions, the actual status and condition of existing infrastructure and equipment revealed during construction, and conflicts with existing utilities or facilities that were not fully known during the design phase. Adjustments may also be necessary due to material availability, manufacturer lead times, supply chain constraints, discontinued equipment, contractor means and methods, and constructability considerations identified in the field. Additionally, project modifications may be driven by permitting requirements, regulatory agency comments, safety concerns, operational needs necessary to maintain service during construction, weather-related impacts, property access limitations, or coordination with third parties. In some cases, field conditions reveal opportunities to improve the efficiency, reliability, resiliency, or long-term operability of the completed facilities, resulting in revisions to the original construction approach. Accordingly, it is a normal and expected part of the construction process for project scopes, quantities, equipment selections, schedules, and construction methods to be adjusted as work progresses. These modifications are undertaken to address actual field conditions and ensure that the completed project safely, reliably, and effectively meets its intended purpose. While specific project components, construction methods, or equipment selections may evolve during construction, the underlying purpose and operational objectives of the project remain unchanged, with modifications made to best achieve those objectives under actual field conditions encountered during project execution. The complexity and delays that occurred with the Delaplain project resulted in several changes. First, as has been discussed in the CPCN filings related to this project, the initial bids expired prior to receiving regulatory approval to move forward on the project and the previous low bidder was no longer able to participate in the project, leading to resoliciting of bids resulting in higher bids and the need to seek new approval. These delays resulted in substantive increase in costs both due to the loss of the previous low bidder and in generally increasing costs related to construction as time passed. Next, the complexity of the project, plant, and site conditions led to a number of significant modifications required to construct the project. Subsurface conditions were often slightly different than anticipated, including a portion of the effluent pipe which was smaller diameter than anticipated causing issues with the installed filter and ultimately requiring replacement of the effluent line. Additionally, the planned polymer feed was swapped for an alum feed to address regulatory requirements and conditions required for the new filter to function. Additional regulatory issues also arose related to the potential for VOCs from the plant requiring modifications to the location and installation of the aeration equipment, and issues regarding the local electrical inspection and approvals. The Delaplain project remains in progress. | 2024-10-01 |  |  | in progress