## Sheet1
Case No. 2025-00354
Bluegrass Water Utility Operating Company, LLC
Facility Name | Permit No | Budgeted | Actual | Progress | Actual Start | Actual In-Service | Forecasted Start | Forecasted In-Service
Delaplain Disposal | KY0079049 | 2200000 | 2269786.16 | In Progress | 2024-07-30 |  | contingent on initial CPCN approval and appended per CPCN update | 2025-12-31
Herrington Haven | KY0053431 | 525420 | 525420 | Complete | 2023-11-14 | 2024-12-31 | 2024-01-01 | 2024-05-07
Persimmon Ridge | KY0090956 | 500000 | 496545.86 | Complete | 2023-10-04 | 2024-10-01 | 2024-01-01 | 2024-04-30
Woodland Acres | KY0091600 | 602000 | 757581 | Complete | 2023-10-04 | 2024-05-01 | 2024-01-01 | 2024-05-01
Yung Farm Estates | KY0092843 | 234000 |  | Planned |  |  | 2027-12-01 | 2028-06-01