## B - Features Timeline
PPL - One PowerPlan Project
Appendix B - Deliverable Features
Feature | ERP Project Team | Module | RICEFW Type | Target PI Completion
CR Master Data Integration | Acquire to Retire | Charge Repository | Integration | PI4-2025/2026
Work Order Master Data Integration* | Acquire to Retire | Project Module | Integration | PI4-2025/2026
Transactional Data SAP to PP* | Acquire to Retire | Charge Repository | Integration | PI4-2025/2026
Transactional Data PP to SAP* | Acquire to Retire | Charge Repository | Integration | PI4-2025/2026
Estimates / As-builts - Hexgon - PA | Acquire to Retire | Project Module | Integration | PI1-2026
Estimates / As-builts - Hexgon - RIE/KY | Acquire to Retire | Project Module | Integration | PI1-2026
Estimates / As-builts- OpenGrid RI | Acquire to Retire | Project Module | Integration | PI1-2026
Estimates / As-builts-KY | Acquire to Retire | Project Module | Integration | PI1-2026
Lease Fleet to PP | Acquire to Retire | Lease Module | Integration | PI1-2026
ASI PowePlan API | Acquire to Retire | ASI | Integration | PI1-2026
PowerPlan to Blackline API | Acquire to Retire | Blackline | Integration | PI1-2026
Asset Conversion - KY | Acquire to Retire | Asset Module | Conversion | PI1-2026
Asset Conversion - PA/RI | Acquire to Retire | Asset Module | Conversion | PI1-2026
Book Depreciation - KY | Acquire to Retire | Depreciation Module | Conversion | PI1-2026
Book Depreciation - PA / RI | Acquire to Retire | Depreciation Module | Conversion | PI1-2026
Project Master Conversion - KY | Acquire to Retire | Project Module | Conversion | PI1-2026
Project Master Conversion - PA / RI | Acquire to Retire | Project Module | Conversion | PI1-2026
Project Charges Conversion - KY | Acquire to Retire | Project Module | Conversion | PI1-2026
Project Charges Conversion - PA /RI | Acquire to Retire | Project Module | Conversion | PI1-2026
Unit estimate and as-built - KY | Acquire to Retire | Project Module | Conversion | PI1-2026
Unit estimate and as-built - PA/RI | Acquire to Retire | Project Module | Conversion | PI1-2026
Charge Repository Conversion* | Acquire to Retire | Charge Repository | Conversion | PI4-2025/2026
Lease Module Conversion - KY | Acquire to Retire | Lease Module | Conversion | PI4-2025/2026
Lease Module Conversion - PA / RI | Acquire to Retire | Lease Module | Conversion | PI4-2025/2026
Security Integration | Acquire to Retire | All | Integration | PI1-2026
PowerPlan to UI - Actual CWIP Spend | Acquire to Retire | UI | Integration | PI1-2026
LGE/KU Tax Repairs Conversion | Tax | Tax Repairs | Conversion | PI1-2026
PA/RIE Tax Repairs Conversion | Tax | Tax Repairs | Conversion | PI1-2026
Tax Repairs - Circuit Threshold Statistics Import | Tax | Tax Repairs | Integration/Report | PI1-2026
TBBS SAP ASI | Tax | Tax Provision | Workflow | PI2-2026
TBBS PowerPlan ASI | Tax | Tax Provision | Workflow | PI2-2026
TBBS OneSource ASI | Tax | Tax Provision | Workflow | PI2-2026
Provision Month End SAP ASI API | Tax | Tax Provision | Workflow | PI2-2026
RTP Process | Tax | Tax Provision | Enhancement | PI2-2026
Convert Provision Data | Tax | Tax Provision | Conversion | PI4-2026
Tax Journal Summary Report | Tax | Tax Provision | Report | PI1-2026
LGE/KU PowerTax Conversion | Tax | PowerTax | Conversion | PI1-2026
PA/RIE PowerTax Conversion | Tax | PowerTax | Conversion | PI1-2026
Property Tax Conversion - PA/RI | Tax | Property Tax | Conversion | PI1-2026
Property Tax Conversion - KY/VA | Tax | Property Tax | Conversion | PI1-2026
Property Tax - Payments Interface to SAP | Tax | Property Tax | Integration | PI1-2026
Property Tax - Update Payment Details from SAP | Tax | Property Tax | Integration | PI1-2026
Property Tax - Validate Vendors, Account String | Tax | Property Tax | Integration | PI1-2026
Property Tax - Placehold for Improvising Allocation Statistics | Tax | Property Tax | Integration | PI4 - 2025
Property Tax Reports | Tax | Property Tax | Report | PI4-2025
Property Tax PB, DB Minor Extensions | Tax | Property Tax | Enhancement | PI1-2026
AFUDC Calculation | Acquire to Retire | Project Module | Non-RICEFW | PI4-2025/2026
Asset Location Catalog | Acquire to Retire | Asset Module | Non-RICEFW | PI4-2025/2026
Asset Module Base Master Data | Acquire to Retire | Asset Module | Non-RICEFW | PI4-2025/2026
Build Queries - TBD - Plant | Acquire to Retire | Plant Reporting | Non-RICEFW | PI4-2025/2026
Charge Collection Heirarchy | Acquire to Retire | Project Module | Non-RICEFW | PI4-2025/2026
Configuration - RWIP Closeout | Acquire to Retire | Project Module | Non-RICEFW | PI4-2025/2026
Configuration - Work Order Type | Acquire to Retire | Project Module | Non-RICEFW | PI1-2026
CR Module Base Configuration | Acquire to Retire | Charge Repository | Non-RICEFW | PI4-2025/2026
Create ASI Controls - Plant | Acquire to Retire | ASI | Non-RICEFW | PI4-2025/2026
Depreciation Group Master Data | Acquire to Retire | Depreciation Module | Non-RICEFW | PI1-2026
Derivations | Acquire to Retire | Charge Repository | Non-RICEFW | PI4-2025/2026
Lease Module Config | Acquire to Retire | Lease Module | Non-RICEFW | PI4-2025/2026
ARO Module Configuration | Acquire to Retire | ARO Module | Non-RICEFW | PI4-2025/2026
Miscellaneous Project Module Configurations | Acquire to Retire | Project Module | Non-RICEFW | PI4-2025/2026
Property Unit Catalog | Acquire to Retire | Asset Module | Non-RICEFW | PI4-2025/2026
Regulatory Entries | Acquire to Retire | Depreciation Module | Non-RICEFW | PI4-2025/2026
SAP True-up | Acquire to Retire | Charge Repository | Non-RICEFW | PI1-2026
Security | Acquire to Retire | Security | Non-RICEFW | PI1-2026
System Controls | Acquire to Retire | All | Non-RICEFW | PI1-2026
ARO Functional Design Document | Acquire to Retire | ARO Module | Non-RICEFW | PI4-2025/2026
Charge Repository Design Document | Acquire to Retire | Charge Repository | Non-RICEFW | PI4-2025/2026
Provision M-Item Build | Tax | Provision | Non-RICEFW | PI4 - 2025
Provision Oper-Ind Build | Tax | Provision | Non-RICEFW | PI4 - 2025
Provision Allocation Build | Tax | Provision | Non-RICEFW | PI4 - 2025
Provision DIT Schema Builld | Tax | Provision | Non-RICEFW | PI4 - 2025
Provision JE Schema Build | Tax | Provision | Non-RICEFW | PI4 - 2025
Provision PowerTax Integration | Tax | Provision | Non-RICEFW | PI1 - 2026
Provision Spreadsheet Loader Integration | Tax | Provision | Non-RICEFW | PI1 - 2026
Provision Consolidation Integration | Tax | Provision | Non-RICEFW | PI1 - 2026
Provision Compliance Process Integration | Tax | Provision | Non-RICEFW | PI1 - 2026
Provision 12/31/2024 Balance Conversion | Tax | Provision | Non-RICEFW | PI1 - 2026
Provision 2025 Accrual Conversion | Tax | Provision | Non-RICEFW | PI1 - 2026
Provision 2025 RTP Conversion | Tax | Provision | Non-RICEFW | Go-live
Provision 2026 Accrual Conversion | Tax | Provision | Non-RICEFW | Go-live
Provision JE Translate Table | Tax | Provision | Non-RICEFW | PI1 - 2026
Tax Repairs Configuration | Tax | Tax Repairs | Non-RICEFW | PI4 - 2025
Tax Repairs 481(a) Gross Model | Tax | Tax Repairs | Non-RICEFW | PI1 - 2026
Prop Tax Configuration | Tax | Property Tax | Non-RICEFW | PI1 - 2026
PowerTax Configuration | Tax | PowerTax | Non-RICEFW | PI1 - 2026
PowerTax Depreciation Master Data Configuration | Tax | PowerTax | Non-RICEFW | PI4 - 2025
PowerTax Deferred Tax Master Data Configuration | Tax | PowerTax | Non-RICEFW | PI4 - 2025
PowerTax Benchmarking and Data Integrity Validations | Tax | PowerTax | Non-RICEFW | PI4 - 2025
PowerTax Book Cost Validations and Reconciliations | Tax | PowerTax | Non-RICEFW | PI4 - 2025
PowerTax Book Reserve Validations and Reconciliations | Tax | PowerTax | Non-RICEFW | PI1 - 2026
PowerTax Deferred Tax Validation and Regulatory Asset and Liability Sync | Tax | PowerTax | Non-RICEFW | PI1 - 2026
PowerTax Fixed Asset Interaces Configuration | Tax | PowerTax | Non-RICEFW | PI1 - 2026
PowerTax Forecasting Procedures | Tax | PowerTax | Non-RICEFW | PI1 - 2026
Tax Repairs 481(a) Net Calculation & System Load | Tax | Tax Repairs | Non-RICEFW | PI4 - 2026/2027