## DR 15 Att 1
PROJECT NO. | TITLE | COUNTY | VINTAGE | MATERIAL | DIAMETER (IN) | INSTALL LENGTH (LF) | REPLACE/ABANDON LENGTH (LF) | ADDITIONS $* | REMOVALS $* | STATUS | TO BE INCLUDED IN SIP (ANTICIPATED YEAR)? | CURRENT ESTIMATED PROJECT COST
1 | New Circle Rd ( Bore for Opportunity Way) | FAYETTE | 1961 | Cast Iron | 12 | 433 | 216 | 284121 | 30441 | Complete
2 | N. Broadway Park (Limestone to Broadway) | FAYETTE | 1922 | Cast Iron | 2 | 1211 | 2253 | 819871 | 89790 | Complete
3 | Warnock Street | FAYETTE | 1928 | Cast Iron | 1, 6 | 565 | 394 | 340534 | 37650 | Complete
4 | Kastle Road (Tremont to Sunset) | FAYETTE | 1923 | Cast Iron | 1, 4 | 645 | 639 | 327169 | 35843 | Complete
5 | Melrose Avenue | FAYETTE | 1923 | Cast Iron | 4, 6 | 1576 | 1535 | 654984 | 71606 | Complete
6 | Shawnee Place | FAYETTE | 1927 | Cast Iron | 2, 4, 6 | 890 | 890 | 619920 | 67506 | Complete
7 | Hagerman Court | FAYETTE | 1905-1906 | Cast Iron | 4, 6 | 704 | 700 | 293854 | 32351 | Complete
8 | Arcadia Park | FAYETTE | 1927 | Cast Iron | 4, 6 | 2972 | 2660 | 2031542 | 224977 | Complete
9 | Willard Street | FAYETTE | 1908 | Cast Iron | 6 |  |  | 14255 | 1551 | Suspended until future year due to City of Lexington paving road prior to waterline project | Yes (2029) | 447662
10 | South Upper Street (Cedar to Limestone) | FAYETTE | 1909 | Cast Iron | 8 | 1690 | 1630 | 1334193 | 146082 | Complete
11 | High Street (Rose to Mill) | FAYETTE | 1884 | Cast Iron | 6, 8 | 2702 | 2670 | 1336986 | 147820 | Complete
12 | Graham Avenue / Gladstone Avenue | FAYETTE | 1904-1919 | Cast Iron | 6 |  |  | 454 | 49 | Suspended until future year due to easement acquisition delays | Yes (2027) | 450875.64
13 | Lackawanna / Wabash (Replace) | FAYETTE | 1928-1936 | Cast Iron | 6 | 2180 | 2180 | 1005580 | 109089 | Final restoration | No
14 | Lackawanna / Wabash / Pensacola (Retire) | FAYETTE | 1936-1950 | Cast Iron | 2 | 2480 | 2480 | 1049768 | 114569 | Final restoration | No
15 | Euclid Avenue (High to S Ashland) | FAYETTE | 1914 | Cast Iron | 6 | 467 | 510 | 226470 | 24456 | Final restoration | No
16 | South Ashland (Euclid to Ashland Terrace) | FAYETTE | 1914 | Cast Iron | 6 | 406 | 480 | 394815 | 43626 | Complete
17 | Ashland Terrace | FAYETTE | 1914 | Cast Iron | 6 | 680 | 660 | 372106 | 40869 | Complete
18 | Sycamore Road (south of Richmond Rd) | FAYETTE | 1925 | Cast Iron | 6 | 2100 | 980 | 1011436 | 111318 | Complete
19 | Wilderness Road | FAYETTE | 1969 | Galvanized Iron | 2 | 2 | 3400 | 616 | 28271 | Complete
20 | Uttinger Lane | FAYETTE | 1955 | Galvanized Iron | 2 | 1560 | 1540 | 448694 | 49825 | Complete
21 | Columbus Lane | FAYETTE | 1955 | Galvanized Iron | 2 | 2347 | 2300 | 768347 | 83241 | Complete
22 | Williams Lane | FAYETTE | 1970 | Galvanized Iron | 0.5, 1.25 | 1185 | 1365 | 69796 | 7755 | Under construction. Project was delayed until 2026 due to easement acquisition delays. | No
23 | Adena Lane | FAYETTE | 1966 | Galvanized Iron | 3 |  |  |  |  | Delayed due to easement acquisitions delays | Yes (2028) | 287222.6522
24 | Georgetown Road (south of Berea Road) | FAYETTE | 1957 | Galvanized Iron | 2 |  | 1720 |  | 24662 | Complete
25 | Devine Avenue | FAYETTE | 1959 | Galvanized Iron | 2 | 260 | 282 | 153636 | 16988 | Complete
26 | Johnson Aly | SCOTT | 1964 | Galvanized Iron | 1.25 |  |  |  |  | Cancelled. Field investigations determined retirement was not necessary. | No
27 | Preston Avenue | FAYETTE | 1936 | Cast Iron | 2, 6 | 2441 | 2340 | 1608042 | 178210 | Complete
28 | Willowlawn Avenue | FAYETTE | 1937 | Cast Iron | 2 | 174 | 180 | 154731 | 17031 | Complete
29 | Whispering Wood Lane | FAYETTE | 1938 | Cast Iron | 2 | 559 | 551 | 293746 | 32543 | Complete
30 | McCubbing Drive | FAYETTE | 1947-1974 | Cast Iron | 2, 6 | 1150 | 1560 | 782024 | 85199 | Complete
31 | Longview Drive | FAYETTE | 1948-1974 | Cast Iron | 2, 6 | 1594 | 1548 | 1116880 | 123065 | Complete
32 | Walton Avenue (Main to Booneboro) | FAYETTE | 1900 | Cast Iron | 10 | 1460 | 1460 | 847919 | 93563 | Complete
33 | Lexington Avenue | FAYETTE | 1884 | Cast Iron | 8 | 960 | 970 | 504772 | 55743 | Final restoration | No
34 | Washington Avenue | FAYETTE | 1906 | Cast Iron | 8 |  |  |  |  | Delayed due to easement acquisition delays | Yes (2027) | 521001.5401
35 | Hawkins Avenue | FAYETTE | 1904 | Cast Iron | 6 | 425 | 425 | 237858 | 26174 | Complete
36 | Wilgus Avenue | FAYETTE | 1905 | Cast Iron | 6 | 356 | 356 | 198209 | 21507 | Complete
37 | Race Street (Third to Fifth) | FAYETTE | 1902 | Cast Iron | 8 | 1327 | 1327 | 477287 | 52398 | Complete
38 | College Street (Sadieville) | SCOTT | 1964 | Cast Iron | 2, 4, 6 | 1271 | 1221 | 620905 | 68058 | Complete
39 | Jones Hill St (Owenton) | OWEN | 1970 | Galvanized Iron | 2 | 1081 | 454 | 469770 | 51735 | Complete
40 | Sunset Drive (Owenton) | OWEN | 1969 | Cast Iron | 2, 4 | 1002 | 1060 | 527314 | 57893 | Complete
41 | N. Limestone (New Circle to W Sixth St) | FAYETTE | 1884-1937 | Cast Iron | 6, 12 | 6000 | 6000 | 5228369 | 573738 | Final restoration | No
42 | Fontaine Rd (High St to Chinoe) | FAYETTE | 1922-1928 | Cast Iron | 6 | 3900 | 3900 | 1768657 | 192361 | Final restoration | No
43 | E 5th St (Pemberton St to Race St) | FAYETTE | 1902 | Cast Iron | 8 | 430 | 435 | 159170 | 13933 | Complete
44 | Corral St (Race St to Midland Ave) | FAYETTE | 1927-1974 | Cast Iron | 6 | 430 | 429 | 179747 | 17437 | Complete
45 | Pine St - Lawrence St | FAYETTE | 1926 | Cast Iron | 6 | 1159 | 1020 | 693489 | 75655 | Complete
46 | Warwick Ct (Redding Rd to Dead End) | FAYETTE | 1972 | Cast Iron | 2, 6 | 893 | 910 | 497850 | 54014 | Complete
47 | Arrowhead Ct (Arrowhead Dr to Dead End) | FAYETTE | 1959 | Cast Iron | 2 | 396 | 390 | 353701 | 38745 | Complete
48 | Pike St (Sadieville) | SCOTT | 1964 | Cast Iron | 4 | 2013 | 2941 | 750672 | 81926 | Complete
49 | W. Fourth Street (Millersburg) | BOURBON | 1927 | Cast Iron | 2 | 402 | 405 | 201631 | 21785 | Complete
TOTAL | 49 |  |  |  |  | 56478 | 61366 | 31231890 | 3473048
[5 empty] | Miles | 10.6966 | 11.6223
*Costs through July 2026