## DR15 Att 2
NAME | WBS | EST. LENGTH (LF) | EST. PROJECT COSTS | ACTUAL LENGTH (LF) (7/31/26) | ACTUAL PROJECT COSTS (7/31/2026) | VARIENCE COMMENTS | STATUS | INCLUDED IN SIP (YEAR)? | CURRENT EST. COST
Todds Road @ Pricetown Ln | R12-02B2.23-P-0002 | 850 | 254571 | 946 | 188171.11 |  | Complete
Samuel Ln | R12-02B2.23-P-0003 | 575 | 168046 | 448 | 98426.48 |  | Complete
Uhlan Ct | R12-02B2.23-P-0004 | 390 | 134902 | 389 | 225104.43 |  | Complete
Old Leestown | R12-02B2.23-P-0021 | 1790 | 513665 | 1954 | 520884 |  | Complete
Adair/Madison/Gess (Owenton) | R12-30B2.23-P-0002 | 2215 | 666537 | 2333 | 1149835.77 | Additional 120' of pipe required for tie-in locations. The restoration requirements in KYTC right of way were full concrete road repair and caused increased restoration costs. | Complete
Strathmore Rd | R12-02B2.23-P-0006 | 970 | 306794 | 1010 | 488970 | Greater restoration limits required BY LFUCG than estimated. | Complete
Eastin Rd/Grandin Rd | R12-02B2.23-P-0007 | 1000 | 325313 | 730 | 440220 |  | Complete
Ranier Dr | R12-02B2.23-P-0008 | 715 | 242793 | 710 | 371460 |  | Complete
Pine St | R12-02B2.23-P-0041 | 2040 | 584742 | 2032 | 815818 | Greater restoration limits required by LFUCG than estimated and greater pipe installation costs than estimated. | Complete
Maxwell (Broadway to Cross) | R12-02B2.23-P-0046 | 2042 | 921643 | 2071 | 874323 |  | Complete
Sulphur Ln | R12-02B2.23-P-0009 | 730 | 219231 | 0 | 0 | Will be installed with Centerville/Boone Ln | Easement Negotiations | Yes (2027) | 264129
N Cleveland Rd | R12-02B2.23-P-0010 | 2620 | 210106 | 0 | 0 | Will be installed with Centerville/Boone Ln | Easement Negotiations | Yes (2027) | 260283
Centerville Ln/Boone Ln | R12-02B2.23-P-0011 | 1865 | 489097 | 0 | 0 | Currently under easement acquisition. Project area is privately owned. | Easement Negotiations | Yes (2027) | 584192
Cross St | R12-02B2.23-P-0040 | 400 | 131495 | 466 | 173048 |  | Complete
Merino St | R12-02B2.23-P-0042 | 753 | 254840 | 715 | 257682 |  | Complete
Patterson St | R12-02B2.23-P-0043 | 691 | 231523 | 671 | 324903 |  | Complete
Spring St | R12-02B2.23-P-0044 | 377 | 133860 | 425 | 175443 |  | Complete
Dunaway St | R12-02B2.23-P-0045 | 632 | 208313 | 656 | 224538 |  | Complete
Campsie Pl/Ct | R12-02B2.23-P-0014 | 775 | 290288 | 907 | 529080 | Increased pipeline installation costs due to many utility conflicts within the construction area. Curb to curb restoration required vs. one-lane estimated. | Complete
Ohio St | R12-02B2.23-P-0015 | 1575 | 445041 | 1558 | 966930 | Increased pipeline installation costs due to many utility conflicts within the construction area. Curb to curb restoration required vs. one-lane estimated. | Complete
Johnson Ave | R12-02B2.23-P-0016 | 780 | 312323 | 748 | 416481 | Increased pipeline installation costs due to many utility conflicts within the construction area. Curb to curb restoration required vs. one-lane estimated. | Complete
Silver Maple Way | R12-02B2.23-P-0017 | 795 | 306703 | 795 | 610823 | Increased pipeline installation costs due to many utility conflicts within the construction area. Curb to curb restoration required vs. one-lane estimated. | Complete
Forest Ave/Skain St/Indiana Ave | R12-02B2.23-P-0039 | 2658 | 927880 | 2981 | 1231962.42 | Additional length of pipe installation at a greater bid unit price than estimated. | Complete
Old Sweet Owen | R12-30B1.21-P-0002 | 3000 | 888783 | 3398 | 453772 |  | Complete
E Seventh St - N Lime to Maple | R12-02B2.23-P-0018 | 1190 | 440659 | 1174 | 896685 | Greater restoration limits required by LFUCG than estimated. | Complete
Delmar Ave/Boonesboro Ave/Bell Pl/Bell Ct | R12-02B2.23-P-0037 | 2281 | 810534 | 2475 | 1067866 |  | Complete
Russell Ave/E & W Bell Cts/Sayre Ave | R12-02B2.23-P-0038 | 3380 | 1067965 | 3220 | 1431374 | Greater restoration limits required by LFUCG than estimated. | Complete
Curley Ave | R12-02B2.23-P-0022 | 345 | 139167 | 360 | 142029 |  | Complete
Wilson St - Curley to Eastern | R12-02B2.23-P-0023 | 402 | 147984 | 400 | 185410 |  | Complete
Corral St - Elm Tree to Race | R12-02B2.23-P-0024 | 1033 | 364865 | 1085 | 357434 |  | Complete
Gunn St | R12-02B2.23-P-0027 | 488 | 172843 | 452 | 162463 |  | Complete
Niagara (to Trout) and Trent | R12-02B2.23-P-0032 | 4027 | 1320790 | 4171 | 1281740 |  | Complete
Maryland Ave | R12-02B2.23-P-0033 | 1144 | 427452 | 1137 | 682352 | Greater restoration limits required by LFUCG than estimated. Bid unit pricing for pipe installation greater than estimated. | Complete
Dove Run Rd | R12-02B2.23-P-0012 | 930 | 267488 | 970 | 328886 |  | Complete
Bermuda Ave | R12-02B2.23-P-0019 | 605 | 213025 | 630 | 204866 |  | Complete
E Second St - Elm Tree to Race | R12-02B2.23-P-0025 | 1120 | 400791 | 1020 | 423053 |  | Complete
Eastern Ave - E Third to before E Short | R12-02B2.23-P-0026 | 1100 | 384304 | 1080 | 540759 | Greater restoration limits required by LFUCG than estimated. | Complete
W Second St (Gtown to Jefferson) | R12-02B2.23-P-0034 | 916 | 339121 | 885 | 457788 |  | Complete
Jefferson St (W Short to W Third) | R12-02B2.23-P-0035 | 1775 | 630707 | 1696 | 1001753 | Greater restoration limits required by LFUCG than estimated. Bid unit pricing for pipe installation greater than estimated. | Complete
Tower Plz | R12-02B2.23-P-0036 | 412 | 161025 | 392 | 205391 |  | Complete
Rosemont Garden | R12-02B2.23-P-0047 | 1060 | 562844 | 1057 | 907345.56 | Significant restoration limits due to construction within small area of intersection, entire intersection was required to be restored. | Complete
Greentree Rd/Cir/Ct | R12-02B1.22-P-0004 | 5765 | 1533697 | 6013 | 2901873 | Greater restoration limits required by LFUCG than estimated. Bid unit pricing for pipe and service installation greater than estimated. | Complete
Locust Ave | R12-02B2.23-P-0020 | 1760 | 510570 | 1788 | 733670 | Greater restoration limits required by LFUCG than estimated. Bid unit pricing for service installation greater than estimated. | Complete
Caulder Rd | R12-02B2.23-P-0028 | 1235 | 376882 | 1265 | 450615.01 |  | Complete
Keeneland Ct | R12-02B2.23-P-0029 | 785 | 248196 | 797 | 229890.66 |  | Complete
Hot Springs Ct | R12-02B2.23-P-0030 | 710 | 229461 | 734 | 229399.48 |  | Complete
Hialeiah Ct | R12-02B2.23-P-0031 | 714 | 231940 | 735 | 222817.95 |  | Complete
| TOTAL FEET | 63415 | 20150799 | 59479 | 25583335.87
| TOTAL MILES | 12.0104 | total $ | 11.265 | total $