## Schedule G
KY PSC Case No. 2026-00099
Staff 1-25
Schedule G
Columbia Gas of Kentucky KY PSC Case No. 2026-00099 Construction Projects As of May 21st, 2026
Line No. (A) | Project No. (B) | Description of Project (C) | Construction Amount (D) | AFUDC Capitalized (E) | Indirect Costs Other (F)* | Total Cost (G = D + E + F) | Estimated Physical Percent Complete
1 | 18026779401 | ACQ 25X25 SITE FOR NEW R-1133 | 15053.61 | 1067.71 | 0 | 16121.32 | 100%
2 | 18026794401 | INSTALL 4400'-2"/4"PMMP MAIN | 911090.93 | 1850.82 | 337955.6 | 1250897.35 | 100%
3 | 18026795501 | INSTALL 14,600'-2,4,6,8" PMMP | 2550504.17 | 80451.23 | 795088.38 | 3426043.78 | 100%
4 | 19026867802 | INSTALL 376'-4" PMIP | 205355.06 | 3543.4 | 53752.93 | 262651.39 | 100%
5 | 20026983300 | INSTALL 6,600'-2"/4" PMMP | 1534319.1 | 11630.26 | 469280.69 | 2015230.05 | 100%
6 | 21026123000 | INVESTIGATE/AQUIRE EASEMENT | 10517.58 | 469.26 | 0 | 10986.84 | 100%
7 | 21026152101 | INSTALL 535' OF 8"CSHP MAIN | 365253.86 | 4902.8 | 110804.19 | 480960.85 | 100%
8 | 22026161800 | INSTALL 8" PCF | 27472.22 | 26.6 | 2046.08 | 29544.9 | 100%
9 | 22026165501 | INSTALL 3385' OF 2" PMMP | 269735.58 | 1645.51 | 76571.04 | 347952.13 | 100%
10 | 22026178300 | EMER-INSTALL 5'OF 2"PMMP MAIN | 2323.18 | 94.82 | 396.42 | 2814.42 | 100%
11 | 22026207100 | INSTALL 7870'-2", 4" PMMP | 1159198.32 | 14496.31 | 375429.09 | 1549123.72 | 100%
12 | 22026224201 | INSTALL 2300' OF 2"/4"PMMP | 453364.41 | 6363.9 | 129037.98 | 588766.29 | 100%
13 | 22026231301 | INSTALL 925' OF 2"PMMP MAIN | 297960.14 | 2049.43 | 88662.05 | 388671.62 | 100%
14 | 22026236501 | INSTALL 1325' OF 4"/8"CSHP MN | 984938.33 | 20338.34 | 401810.09 | 1407086.76 | 100%
15 | 22026236901 | INSTALL 11300'-2" PMMP | 2006758.56 | 34581.37 | 585250.99 | 2626590.92 | 100%
16 | 22026237301 | INSTALL 11,150'-8"6"4"2" PMMP | 2378997.6 | 59811.55 | 738466.4 | 3177275.55 | 100%
17 | 22026238401 | INSTALL 5765'-2" PMMP | 1085630.93 | 730.83 | 335798.81 | 1422160.57 | 100%
18 | 22026239702 | INSTALL 8650' - 2,4,6" PMMP | 1448355.47 | 46321.39 | 439987.19 | 1934664.05 | 100%
19 | 23026258300 | INSTALL VRG CONTROLLER | 33603.65 | 1508.41 | 6493.01 | 41605.07 | 100%
20 | 23026270600 | INSTALL 550' OF 2" PMMP | 32176.87 | 112.86 | 11055.97 | 43345.7 | 100%
21 | 23026283101 | INSTALL 780'-2" PMMP | 55147.55 | 264.86 | 16369.79 | 71782.2 | 100%
22 | 23026283600 | INSTALL LP FITTINGS | 7295.61 | 79.82 | 2283.27 | 9658.7 | 100%
23 | 23026286900 | HIGHLAND HEIGHTS BREAK METER | 28069.08 | 1202.35 | 10943.29 | 40214.72 | 100%
24 | 23026287300 | INSTALL 121'-4" CSMP | 142112.97 | 1571.06 | 44648.6 | 188332.63 | 100%
25 | 23026300300 | INSTALL 1810'-2" PMMP | 169099.2 | 0 | 48176.3 | 217275.5 | 100%
26 | 23026301200 | INSTALL 60' OF 6"PMMP MAIN | 29242.3 | 0 | 14636.92 | 43879.22 | 100%
27 | 23026306800 | INSTALL METER RUN | 34905.76 | 793.66 | 11351.04 | 47050.46 | 100%
28 | 23026308100 | INSTALL NEW METER | 5834.1 | 3.36 | 1562.62 | 7400.08 | 100%
29 | 24026312301 | INSTALL NEW GMB SETTING | 177429.22 | 2794.29 | 50321.18 | 230544.69 | 100%
30 | 24026312500 | ACQUIRE EASEMENT FOR RELOCATE | 500 | 15.95 | 0 | 515.95 | 100%
31 | 24026313000 | INSTALL 1570'-2" PMMP | 393446.75 | 826.08 | 108384.72 | 502657.55 | 100%
32 | 24026314400 | INSTALL 1,200'-4" PMMP | 314291.89 | 842.19 | 126658.96 | 441793.04 | 100%
33 | 24026316701 | INSTALL 11245' OF 2"PMMP MAIN | 810698.55 | 14886.26 | 259302.43 | 1084887.24 | 100%
34 | 24026324100 | INSTALL 670'-2' PMIP | 70340.21 | 65.98 | 20774.31 | 91180.5 | 100%
35 | 24026333201 | EMER - INSTALL 478'-4" PMLP | 141419.14 | 615.39 | 63412.76 | 205447.29 | 100%
36 | 24026333600 | INSTALL 75'-2" PMIP | 20999.52 | 63.22 | 7325.09 | 28387.83 | 100%
37 | 24026336600 | INSTALL GMB SETTING | 18363.65 | 82.87 | 4609.82 | 23056.34 | 100%
38 | 24026340200 | INSTALL 600' OF 8"PMMP MAIN | 252920.57 | 3.55 | 135661.1 | 388585.22 | 100%
39 | 24026340500 | ACQUIRE EASEMENT | 43765.62 | 2154.49 | 0 | 45920.11 | 100%
40 | 24026340800 | EMER - INSTALL 15'-2" PMMP | 11656.77 | 501.84 | 3552.15 | 15710.76 | 100%
41 | 24026341000 | INSTALL 300'OF 2" PMIP | 39782.89 | 957.46 | 15881.5 | 56621.85 | 100%
42 | 24026341800 | LAND PAYMENT FOR REG SITE EASE | 500 | 15.96 | 0 | 515.96 | 100%
43 | 24026341900 | INSTALL 4250' OF 2"/4"PMMP | 123201.12 | 1554.37 | 35397.86 | 160153.35 | 100%
44 | 24026345800 | INSTALL 1400'-2" PMIP | 189767.51 | 1240.7 | 72548.81 | 263557.02 | 100%
45 | 24026348200 | INSTALL ~30'-4" PMMP | 13263.85 | 30.19 | 3586.59 | 16880.63 | 100%
46 | 24026348900 | INSTALL 70'-8" PMMP | 87138.7 | 1694.2 | 21556.79 | 110389.69 | 100%
47 | 24026349200 | ACQUIRE EASEMENT | 1800 | 0.46 | 0 | 1800.46 | 100%
48 | 24026349300 | INSTALL 4"POLY VALVE KY-C1556 | 16870.94 | 42.51 | 5430.04 | 22343.49 | 100%
49 | 24026349500 | INSTALL 40'-12" CSMP | 157739.14 | 3131.06 | 77024.06 | 237894.26 | 100%
50 | 24026351200 | INSTALL 150' OF 2"PMIP MAIN | 10748.24 | 56.14 | 3694.82 | 14499.2 | 100%
51 | 24026352000 | INSTALL 700'-2" PMMP | 45137.93 | 191.85 | 30456.84 | 75786.62 | 100%
52 | 24026354300 | INSTALL 1750' OF 2"PMMP MAIN | 38943.9 | 397.42 | 10579.29 | 49920.61 | 100%
53 | 24026355200 | INSTALL 150'-4" PMLP | 47198.15 | 158.91 | 10012.57 | 57369.63 | 100%
54 | 24026355300 | INSTALL 250'-2" PMMP | 18029.99 | 58.25 | 6376.23 | 24464.47 | 100%
55 | 24026355900 | INSTALL 250' OF 2"PMMP MAIN | 45125.07 | 156.57 | 11024.65 | 56306.29 | 100%
56 | 24026356000 | INSTALL 475' OF 2"PMMP MAIN | 113053.66 | 757.69 | 24306.51 | 138117.86 | 100%
57 | 24026356200 | INSTALL NEW 4" CRITICAL VALVE | 4706.14 | 23.41 | 1508.37 | 6237.92 | 100%
58 | 24026356500 | EMER - INSTALL 2'-2" PMIP | 3685.18 | 12.32 | 1168.21 | 4865.71 | 100%
59 | 24026357000 | EMER-INSTALL 50' OF 4"PMLP | 14737.82 | 94.63 | 4738.17 | 19570.62 | 100%
60 | 24026357400 | INSTALL 275'-3" CSMP | 80097.7 | 301.74 | 24073.31 | 104472.75 | 100%
61 | 24026358600 | INSTALL 175' - 4" PMMP | 70812.59 | 109.77 | 19486.98 | 90409.34 | 100%
62 | 24026358700 | INSTALL 100' OF 2" PMMP MLE | 18509.29 | 115.35 | 5979.53 | 24604.17 | 100%
63 | 24026358801 | INSTALL 4200' OF 2"/4"PMMP | 583233.81 | 1821.46 | 197212.37 | 782267.64 | 100%
64 | 24026359401 | INSTALL 200' OF 4" PMIP | 38733.92 | 312.76 | 22939.46 | 61986.14 | 100%
65 | 24026360200 | EMER-INSTALL 3' OF 2"PMMP MAIN | 9660.3 | 26.42 | 3105.03 | 12791.75 | 100%
66 | 24026360500 | INSTALL 18'-2" PMMP | 8452.23 | 22.57 | 2153.05 | 10627.85 | 100%
67 | 24026360700 | INSTALL 230' OF 4"PMLP MAIN | 13636.19 | 311.04 | 5558.7 | 19505.93 | 100%
68 | 24026361300 | INSTALL 750'-2" PMMP | 139929.95 | 828.59 | 65356.1 | 206114.64 | 100%
69 | 24026361400 | INSTALL 100' OF 2" PMIP | 19693.71 | 79.07 | 8317.14 | 28089.92 | 100%
70 | 24026361500 | EMER - INSTALL 2'-3" PMLP | 3731.68 | 8.61 | 1143.88 | 4884.17 | 100%
71 | 24026362000 | EMER-INSTALL 3' OF 3"PMMP MAIN | 13448.14 | 58.57 | 4776.31 | 18283.02 | 100%
72 | 24026363600 | INSTALL 620' OF 4"PMMP MAIN | 218520.62 | 762.88 | 55910.1 | 275193.6 | 100%
73 | 24026363800 | INSTALL EC-350 UNIT | 4838.64 | 4.37 | 1049.19 | 5892.2 | 100%
74 | 24026364900 | INSTALL 2,300'-4" PMMP | 148950.54 | 1946.52 | 64302.96 | 215200.02 | 100%
75 | 24026365000 | EMER-INSTALL 10' - 2" PMMP | 2446.08 | 0.49 | 594 | 3040.57 | 100%
76 | 24026365300 | EMER INSTALL 5" OF 4" PMLP | 20766.8 | 44.62 | 5422.64 | 26234.06 | 100%
77 | 24026365700 | INSTALL 320' OF 2"PMIP MAIN | 23129.64 | 71.83 | 6553.26 | 29754.73 | 100%
78 | 24026366400 | INSTALL ~390'-2" PMIP | 29320.23 | 201.07 | 15381.14 | 44902.44 | 100%
79 | 24026367000 | EMER INSTALL 5'-2" PMMP | 6199.62 | 6.25 | 1703.54 | 7909.41 | 100%
80 | 24026367700 | INSTALL NEW EC-350 UNIT | 540.17 | 2.04 | 164.6 | 706.81 | 100%
81 | 24026368000 | EMER - INSTALL 5'-2" PMMP | 3479.67 | 13.09 | 1052.91 | 4545.67 | 100%
82 | 24026368600 | INSTALL 640' OF 2" PMMP | 39119.75 | 206.36 | 11058.82 | 50384.93 | 100%
83 | 24026368800 | INSTALL 5' OF 6" PMLP (PIF) | 36887.29 | 370.64 | 16666.57 | 53924.5 | 100%
84 | 24026369000 | INSTALL 65'-8" PMLP | 124747.47 | 517.71 | 19701.63 | 144966.81 | 100%
85 | 24026370500 | ACQUIRE LAND RIGHTS | 20000 | 657.58 | 0 | 20657.58 | 100%
86 | 24026370600 | INSTALL 32'-6" PMLP | 8445.36 | 122.98 | -250.5 | 8317.84 | 100%
87 | 24026371100 | EMER-INSTALL 6' OF 8"PMMP | 4659.38 | 18.01 | 1064.95 | 5742.34 | 100%
88 | 24026371600 | EMER - INSTALL 5' - 2" PMMP | 4843.72 | 3.32 | 1525.26 | 6372.3 | 100%
89 | 24026371800 | EMER - INSTALL 3'-2" PMMP | 15899.24 | 55.15 | 3305.14 | 19259.53 | 100%
90 | 24026372000 | INSTALLING 500'-2" PMMP | 27862.38 | 129.25 | 19897.92 | 47889.55 | 100%
91 | 24026373800 | EMER - INSTALL 3'-2" PMMP | 4719.22 | 10.75 | 1284.63 | 6014.6 | 100%
92 | 24026375200 | EMER-INSTALL 6' OF 2"PMMP MAIN | 5596.02 | 22.85 | 1231.66 | 6850.53 | 100%
93 | 24026376300 | EMER - INSTALL 5'-2" PMIP | 5035.7 | 10.75 | 1468.25 | 6514.7 | 100%
94 | 24026376700 | EMER - INSTALL 3'-2" PMMP | 2530.73 | 2.21 | 608.86 | 3141.8 | 100%
95 | 24026376901 | INSTALL 1218'-6" PMMP | 483743.85 | 5885.76 | 217464.91 | 707094.52 | 100%
96 | 25026377600 | EMER-INSTALL 4' OF 2"PMMP MAIN | 6438.29 | 26.83 | 2534.36 | 8999.48 | 100%
97 | 25026377900 | INSTALL LP FITTING-PAPER ONLY | 0 | 0 | 0 | 0 | 100%
98 | 25026378600 | INSTALL 42' OF 2"/4" PMMP MAIN | 21685.28 | 112.68 | 4213.06 | 26011.02 | 100%
99 | 25026378800 | EMER - INSTALL 25'-2" PMMP | 58495.62 | 112.31 | 22639.38 | 81247.31 | 100%
100 | 25026379000 | EMER - INSTALL 9'-2" PMMP | 859.88 | 2.86 | 321.52 | 1184.26 | 100%
101 | 25026381300 | EMER-INSTALL 180' OF 4"PMLP MN | 2117.88 | 84.11 | 719.67 | 2921.66 | 100%
102 | 25026381700 | INSTALL 230' OF 2" PMIP | 65381.23 | 156.74 | 24162.21 | 89700.18 | 100%
103 | 25026381800 | INSTALL 250'-2" PMMP | 35913.95 | 148.61 | 16293.19 | 52355.75 | 100%
104 | 25026385100 | EMER-INSTALL 4' OF 4"PMMP MAIN | 7238.82 | 333.19 | 2979.8 | 10551.81 | 100%
105 | 25026392000 | INSTALL 140'-2" PMMP | 17057.86 | 71.04 | 4386.57 | 21515.47 | 100%
106 | 25026393800 | INSTALL 2,100'-2" PMMP | 88029.82 | 341.85 | 22625.59 | 110997.26 | 100%
107 | 25026394000 | EMER INSERT 280'-1.2" PMIP | 1543.23 | 0 | 674.21 | 2217.44 | 100%
108 | 25026395600 | EMER-INSTALL 3' OF 3"PMMP MAIN | 250.66 | 0 | 79.57 | 330.23 | 100%
109 | 25026396000 | INSTALL CAT HEATER | 0 | 0 | 0 | 0 | 100%
110 | 25026397400 | EMER-INSTALL 3' OF 2"PMMP MAIN | 5686.06 | 130.41 | 2111.95 | 7928.42 | 100%
111 | 25026398400 | EMER - INSTALL FITTINGS | 4719.43 | 20.36 | 2120.46 | 6860.25 | 100%
112 | 25026398800 | INSTALL 3670' OF 2"/4"PMMP MN | 100303.49 | 556.94 | 29484.97 | 130345.4 | 100%
113 | 25026399300 | EMER - INSTALL 5'-2" PMMP | 1551.21 | 45.97 | 701.15 | 2298.33 | 100%
114 | 25026399900 | OBTAIN EASEMENTS | 7794.7 | 23.36 | 0 | 7818.06 | 100%
115 | 25026400200 | INSTALL 550'-2" PMMP | 36994.76 | 77.64 | 10435.6 | 47508 | 100%
116 | 25026400900 | EMER - INSTALL 2'-4" PMMP | 4316.75 | 18.92 | 1994.34 | 6330.01 | 100%
117 | 25026403000 | EMER - INSTALL 2'-3" PMMP | 230.88 | 0 | 0 | 230.88 | 100%
118 | 25026403300 | INSTALL MONITOR REGULATOR | 1488.58 | 5.71 | 415.31 | 1909.6 | 100%
119 | 25026405400 | EMER - INSTALL 2'-2" PMMP | 2824.62 | 10.14 | 744.56 | 3579.32 | 100%
120 | 25026406000 | EMER - INSTALL 2'-2" PMLP | 3188.3 | 59.66 | 871.06 | 4119.02 | 100%
121 | 25026406300 | INSTALL 15'-6" PMLP | 8321.58 | 108.24 | 2160.76 | 10590.58 | 100%
122 | 25026407800 | EMER - INSTALL 5'-2" PMMP | 1272.31 | 12.71 | 320.35 | 1605.37 | 100%
123 | 25026409300 | PAPER ONLY LP STOPPLE FITTINGS | 4975.29 | 0 | 1294.61 | 6269.9 | 100%
124 | 25026409900 | EMER - INSTALL 10'-2" PMMP | 7698.66 | 87.45 | 1962.06 | 9748.17 | 100%
125 | 25026410100 | EMER - INSTALL 200' - 2" | 503.2 | 0 | 0 | 503.2 | 100%
126 | 25026410400 | EMER - INSTALL 10'-2" PMMP | 1769.76 | 129.83 | 537.17 | 2436.76 | 100%
127 | 25026410600 | EMER-INSTALL 3'-2"PMMP MAIN | 59.2 | 0 | 0 | 59.2 | 100%
128 | 25026410800 | EMER - INSTALL 2'-2" PMMP | 1368.06 | 98.89 | 406.14 | 1873.09 | 100%
129 | ANC32.0000.00002 | SMRP-CHESTNUT DR 20-75304 | 0 | 0 | 0 | 0 | 100%
130 | ANC32.0000.00004 | SMRP-SUNSET DR 23-00569 | 867.4 | 0 | 451.94 | 1319.34 | 100%
131 | ANC32.0000.00005 | SMRP-CAMELOT DR 23-00572 | 417866.35 | 0 | 11295.19 | 429161.54 | 100%
132 | ANC32.0000.00006 | 2025 KENTUCKY FLOOD EMERGENCY 25-12421 | 4282.4 | 0 | 3014.87 | 7297.27 | 100%
133 | ANC32.0000.00007 | SMRP-ROWLAND AVE 20-75067 | 7118.22 | 0 | 0 | 7118.22 | 30%
134 | ANC32.0000.00010 | SMRP-BOB O LINK-LEXINGTON | 522169.75 | 0 | 33435.26 | 555605.01 | 25%
135 | ANC32.0000.00014 | SMRP-MACEY AVE 22-86868 | 0 | 0 | 0 | 0 | 0%
136 | ANC32.0000.00017 | SMRP-TRAFTON ST HP REPLACEMENT 22-93634 | 3284.99 | 0 | 704.72 | 3989.71 | 100%
137 | ANC32.0000.00018 | ANC-SMRP HIGH STREET-FRANKFORT | 0 | 0 | 0 | 0 | 0%
138 | ANC32.0000.00019 | ANC - Rand Ave SMRP - Lexington | 236484.6 | 0 | 17633.01 | 254117.61 | 25%
139 | ANC32.0000.00020 | SMRP-RICHMOND RD PHASE 2 22-93757 | 759337.58 | 0 | 28090.75 | 787428.33 | 100%
140 | ANC32.0000.00049 | SMRP-LEX SUNSET DRIVE 23-99784 | 1283963.37 | 0 | 43097.01 | 1327060.38 | 100%
141 | ANC32.0000.00050 | SMRP-BLUE RIDGE DR 23-99791 | 1078865.68 | 0 | 47346.44 | 1126212.12 | 100%
142 | ANC32.0000.00051 | EMER-2623-CHOCTAW TL | 0 | 0 | 0 | 0 | 100%
143 | ANC32.0000.00052 | SMRP-JEFFERSON ST 24-03101 | 0 | 0 | 0 | 0 | 100%
144 | ANC32.0000.00054 | SMRP-JESSELIN DRIVE 24-03459 | 1007374.35 | 0 | 222222.52 | 1229596.87 | 100%
145 | ANC32.0000.00056 | 2621-SMRP-ALGONQUIN AVE-Ashland | 1119365.58 | 0 | 22793.58 | 1142159.16 | 100%
146 | ANC32.0000.00057 | SMRP-GANO AVE2621-SMRP-ALGONQUI 24-03657 | 884899.8 | 0 | 20193.74 | 905093.54 | 50%
147 | ANC32.0000.00058 | SMRP-MOCKINGBIRD 24-03658 | 1032988.36 | 1.92 | 52706.48 | 1085696.76 | 100%
148 | ANC32.0000.00059 | SMRP-TURNER ST 24-03660 | 1682056.86 | 0 | 10100.56 | 1692157.42 | 80%
149 | ANC32.0000.00060 | EMER-2629-ORANGE AVE | 0 | 0 | 0 | 0 | 100%
150 | ANC32.0000.00061 | EMER-2629-SHALA-MAR RUE | 0 | 0 | 0 | 0 | 100%
151 | ANC32.0000.00062 | EMER-2623-209 WINDING CREEK | 0 | 0 | 0 | 0 | 100%
152 | ANC32.0000.00063 | EMER-2629-RUCKER ST | 0 | 0 | 0 | 0 | 100%
153 | ANC32.0000.00068 | EMER-2623-1017 COLONIAL TRACE | 0 | 0 | 0 | 0 | 100%
154 | ANC32.0000.00071 | EMER-2631-MCNIPP LEAK REPAIR | 0 | 0 | 0 | 0 | 100%
155 | ANC32.0000.00074 | EMER-2629-STRODE STATION LEAK REPAIR | 0 | 0 | 0 | 0 | 100%
156 | ANC32.0000.00075 | EMER-2632-203 E 2ND ST DAMAGE | 0 | 0 | 0 | 0 | 100%
157 | ANC32.0000.00076 | EMER-2629-GARDEN SPRINGS LEAK | 0 | 0 | 0 | 0 | 100%
158 | ANC32.0000.00077 | EMER-2623-CHESTNUT LEAK REPAIR | 0 | 0 | 0 | 0 | 100%
159 | ANC32.0000.00078 | SMRP-BASIN SPRINGS HP REPL 24-08395 | 238153.75 | 0 | 3225.52 | 241379.27 | 30%
160 | ANC32.0000.00080 | EMER-2629-MARKET ST DAMAGE | 0 | 0 | 0 | 0 | 100%
161 | ANC32.0000.00081 | 2621-SMRP GEORGETOWN RD BSHP-LEXINGTON | 255.51 | 0 | 75.11 | 330.62 | 0%
162 | ANC32.0000.00082 | SMRP-EASTIN RD MP REPL 24-09175 | 0 | 0 | 0 | 0 | 100%
163 | ANC32.0000.00083 | SMRP-N WOLF CREEK REPL 24-09225 | 12197.86 | 0 | 815.45 | 13013.31 | 100%
164 | ANC32.0000.00084 | SMRP-CASSIDY AVE 24-10079 | 1188.1 | 0 | 374.67 | 1562.77 | 0%
165 | ANC32.0000.00085 | SMRP-W 5TH & N LIMESTONE 24-10261 | 0 | 0 | 0 | 0 | 100%
166 | ANC32.0000.00086 | EMER-2621-2550 WINCHESTER RD LEAK REPAIR | 382.32 | 0 | 0 | 382.32 | 100%
167 | ANC32.0000.00087 | EMER-2631-HICKORY ST | 0 | 0 | 0 | 0 | 100%
168 | ANC32.0000.00088 | EMER-2621-1120 FONTAINE RD DAMAGE | 0 | 0 | 0 | 0 | 100%
169 | ANC32.0000.00089 | EMER-2629-ARLINGTON DAMAGE | 0 | 0 | 0 | 0 | 100%
170 | ANC32.0000.00090 | EMER-2629-VINE ST LEAK REP | 0 | 0 | 0 | 0 | 100%
171 | ANC32.0000.00092 | EMER-2629-CONSTITUTION DR LEAK | 0 | 0 | 0 | 0 | 100%
172 | ANC32.0000.00093 | SMRP-JONES CREEK EXPOSED MAIN | 1918.09 | 0 | 63.33 | 1981.42 | 0%
173 | ANC32.0000.00094 | EMER-2629-WINCHESTER PLAZA | 0 | 0 | 0 | 0 | 100%
174 | ANC32.0000.00095 | EMER-2623-BEVELED GLASS DIG IN | 0 | 0 | 0 | 0 | 100%
175 | ANC32.0000.00098 | EMER-2621-ELK LAKE REPL | 0 | 0 | 0 | 0 | 100%
176 | ANC32.0000.00099 | EMER-2621-FORT HARRODS | 0 | 0 | 0 | 0 | 100%
177 | ANC32.0000.00100 | EMER-2621-RIDGEPOINT DIG IN | 0 | 0 | 0 | 0 | 100%
178 | ANC32.0000.00110 | EMER-2623-879 KENTUCKY AVE | 0 | 0 | 0 | 0 | 100%
179 | ANC32.0000.00113 | EMER-2621-1735 SHARKEY WAY LEAK REPAIR | 0 | 0 | 0 | 0 | 100%
180 | ANC32.0000.00119 | LEVEE RD HP-MP REG & VALVE INSTALL | 1331.16 | 0 | 0 | 1331.16 | 0%
181 | ANC32.0000.00120 | R-1146 DURBIN LN VALVE REPL | 0 | 0 | 0 | 0 | 0%
182 | ANC32.0000.00121 | R-1439 LITTLE MUD CREEK REPL ODORIZER | 0 | 0 | 0 | 0 | 0%
183 | ANC32.0000.00122 | R-1308 GREENUP REPL METER RUN | 0 | 0 | 0 | 0 | 100%
184 | ANC32.0000.00124 | R-1282 SOUTHERN HILLS SUBDIVISION REPL M | 0 | 0 | 0 | 0 | 0%
185 | ANC32.0000.00126 | R-1469 HIGHLAND HEIGHTS BMF | 0 | 0 | 0 | 0 | 100%
186 | ANC32.0000.00127 | R-1349 FRIENDSHIP RD BMF | 0 | 0 | 0 | 0 | 100%
187 | ANC32.0000.00128 | R-1305 US23-UPPER RIGGS BMF | 0 | 0 | 0 | 0 | 0%
188 | ANC32.0000.00129 | R-1429 ALICE LLOYD COLLEGE | 0 | 0 | 0 | 0 | 0%
189 | ANC32.0000.00132 | R-1357 25TH ST PF REGULATOR INSTALL | 0 | 0 | 0 | 0 | 100%
190 | ANC32.0000.00133 | RETIRE PAPER GAUGES AT SEVERAL STATIONS | 0 | 0 | 0 | 0 | 100%
191 | ANC32.0000.00136 | 595I - INSTALL THREE SSD UNITS | 0 | 0 | 0 | 0 | 0%
192 | ANC32.0000.00137 | 595I - INSTALL SSD UNIT W | 0 | 0 | 0 | 0 | 0%
193 | ANC32.0000.00140 | 2633-Caney Circle-Pippa Passes | 6712.5 | 0 | 0 | 6712.5 | 0%
194 | ANC32.0000.00141 | SMRP-FAYETTE PARK 24-03646 | 61619.53 | 0 | 1996.73 | 63616.26 | 100%
195 | ANC32.0000.00143 | BET-WILSON LANE P-LP MAIN ABANDONMENT | 2292.84 | 0 | 249.85 | 2542.69 | 100%
196 | ANC32.0000.00144 | GRT-GOODWILL GEORGETOWN | 687.93 | 0 | 559.31 | 1247.24 | 100%
197 | ANC32.0000.00145 | SMRP-NICHOLASVILLD RD MP 24-10724 | 305155.33 | 0 | 14957.92 | 320113.25 | 100%
198 | ANC32.0000.00146 | GRT-BMC CONTRACTING 481 ADENA DR | 32007.28 | 0 | 5850.86 | 37858.14 | 100%
199 | ANC32.0000.00147 | SMRP-E MAIN ST MT STERLING 25-12744 | 110955.66 | 0 | 646.76 | 111602.42 | 100%
200 | ANC32.0000.00148 | BLUEGREASS PARKWAY RECTIFIER | 1808.74 | 0 | 264.31 | 2073.05 | 0%
201 | ANC32.0000.00149 | R-1537 COMPTON DR REPAIRS | 0 | 0 | 0 | 0 | 100%
202 | ANC32.0000.00150 | EMER-2621-NEW CIRCLE REPL | 0 | 0 | 0 | 0 | 100%
203 | ANC32.0000.00151 | EMER-2629-S MAIN ST DAMAGE | 0 | 0 | 0 | 0 | 100%
204 | ANC32.0000.00152 | SMRP-909 AURORA AVE 25-14136 | 0 | 0 | 0 | 0 | 100%
205 | ANC32.0000.00153 | 2621-COPPER RUN REPL JO | 0 | 0 | 0 | 0 | 100%
206 | ANC32.0000.00154 | SMRP-LONG ST 25-13851 | 114421.57 | 0 | 6916.3 | 121337.87 | 100%
207 | ANC32.0000.00157 | SMRP (AMRP)-SULLIVAN ST 18-55491 | 94927.76 | 0 | 0 | 94927.76 | 100%
208 | ANC32.0000.00158 | SMRP (AMRP)-MOY FOO 18-55582 | 535.09 | 0 | 546.12 | 1081.21 | 100%
209 | ANC32.0000.00163 | SMRP-ADDISON AVE HP REPL 20-75431 | 1487.13 | 0 | 966.37 | 2453.5 | 100%
210 | ANC32.0000.00165 | 2623-SMRP HIGHLAND PARKWAY-FRANKFORT | 0 | 0 | 0 | 0 | 0%
211 | ANC32.0000.00167 | SMRP-FARMERS MARKET 21-80320 | 0 | 0 | 0 | 0 | 100%
212 | ANC32.0000.00170 | SMRP-BURNS AVE 21-82509 | 2032589.11 | 0 | 50360.2 | 2082949.31 | 100%
213 | ANC32.0000.00171 | SMRP-E NEW CIRCLE 21-83195 | 0 | 0 | 0 | 0 | 100%
214 | ANC32.0000.00174 | SMRP-SCOTT AVE 22-86363 | 0 | 0 | 0 | 0 | 100%
215 | ANC32.0000.00176 | SMRP-CHEROKEE PARK 22-86440 | 0 | 0 | 0 | 0 | 100%
216 | ANC32.0000.00178 | SMRP-ASHLAND TERRACE 22-86912 | 0 | 0 | 0 | 0 | 100%
217 | ANC32.0000.00179 | SMRP-FERNLEAF DR 22-86927 | 592689.96 | 0 | 23880.82 | 616570.78 | 50%
218 | ANC32.0000.00180 | SMRP-MAPLE RD 22-86936 | 178351.44 | 0 | 13582.31 | 191933.75 | 100%
219 | ANC32.0000.00181 | SMRP-WESTWOOD PHASE II 22-86985 | 0 | 0 | 0 | 0 | 100%
220 | ANC32.0000.00184 | SMRP-VIRGINIA AVE 22-89651 | 13881.9 | 0 | 295.64 | 14177.54 | 100%
221 | ANC32.0000.00187 | SMRP-COLUMBIA AVE 22-91708 | 0 | 0 | 0 | 0 | 100%
222 | ANC32.0000.00191 | SMRP-E HIGH | 0 | 0 | 0 | 0 | 100%
223 | ANC32.0000.00192 | SMRP-OLD LEMONS MILL RD 22-93486 | 0 | 0 | 0 | 0 | 100%
224 | ANC32.0000.00193 | SMRP-CLAYTON AVE 22-93665 | 279.76 | 0 | 317.16 | 596.92 | 100%
225 | ANC32.0000.00194 | SMRP-LAFAYETTE HIGH SCHOOL 22-93681 | 358413.18 | 0 | 18277.5 | 376690.68 | 100%
226 | ANC32.0000.00195 | SMRP-MUTUAL AVE 22-93700 | 464.31 | 0 | 409.81 | 874.12 | 100%
227 | ANC32.0000.00196 | SMRP-BROADWAY AVE IP 22-93704 | 0 | 0 | 0 | 0 | 100%
228 | ANC32.0000.00197 | SMRP-NORTH MIDWAY 22-93724 | 0 | 0 | 0 | 0 | 100%
229 | ANC32.0000.00198 | SMRP-MONTCLAIR | 218540.75 | 0 | 10068.34 | 228609.09 | 100%
230 | ANC32.0000.00199 | SMRP-CASTLEWOOD DRIVE 22-93756 | 0 | 0 | 0 | 0 | 100%
231 | ANC32.0000.00200 | SMRP-RIVERSIDE DRIVE 23-00016 | 43611.23 | 0 | 2811.32 | 46422.55 | 100%
232 | ANC32.0000.00202 | SMRP-HARRISON AVE 23-00625 | 553021.67 | 0 | 33132.18 | 586153.85 | 100%
233 | ANC32.0000.00209 | EMER-2621-548 MERRIMAC | 0.02 | 0 | 0.34 | 0.36 | 100%
234 | ANC32.0000.00226 | CLEMENS DR VALVE REPAIR | 0 | 0 | 0 | 0 | 100%
235 | ANC32.0000.00230 | SMRP-RIVER CROSSING 23-97978 | 0 | 0 | 0 | 0 | 100%
236 | ANC32.0000.00234 | EMER-2629-GRINDSTONE | 0 | 0 | 0 | 0 | 100%
237 | ANC32.0000.00235 | EMER-2621-1054 REDWOOD DR | 0 | 0 | 0 | 0 | 100%
238 | ANC32.0000.00239 | EMER-2629-BROOKVIEW | 0 | 0 | 0 | 0 | 100%
239 | ANC32.0000.00248 | EMER-2621-3051 KIRKLEVINGTON LEAK REPAIR | 0 | 0 | 0 | 0 | 100%
240 | ANC32.0000.00249 | EMER-2621-WINTHROP DRIVE LEAK REPAIR | 0 | 0 | 0 | 0 | 100%
241 | ANC32.0000.00250 | SMRP-WILSON ST 24-03447 | 12394.74 | 0 | 2044.4 | 14439.14 | 100%
242 | ANC32.0000.00251 | SMRP-HORSESHOE DRIVE 24-03489 | 2475796.36 | 0 | 68624.82 | 2544421.18 | 90%
243 | ANC32.0000.00252 | SMRP-SAINT PHILLIP DRIVE 24-03558 | 0 | 0 | 0 | 0 | 100%
244 | ANC32.0000.00253 | EMER-2633-WALNUT ST LEAK REPAIR | 0 | 0 | 0 | 0 | 100%
245 | ANC32.0000.00256 | 2631 - SMRP FLOYD STREET - ASHLAND | 1856668.07 | 0 | 37568.45 | 1894236.52 | 100%
246 | ANC32.0000.00257 | SMRP-WOLF RUN DRIVE 24-03788 | 407173.62 | 0 | 41891.77 | 449065.39 | 100%
247 | ANC32.0000.00259 | EMER-2621-2104 WILTSHIRE PL | 0 | 0 | 0 | 0 | 100%
248 | ANC32.0000.00260 | SMRP-HENTON COURT REPL 24-04300 | 0 | 0 | 0 | 0 | 100%
249 | ANC32.0000.00262 | 2069 HEATHER WAY LEAK REPAIR | 0 | 0 | 0 | 0 | 100%
250 | ANC32.0000.00263 | EMER-2623-230 SUNDOWN DR | 0 | 0 | 0 | 0 | 100%
251 | ANC32.0000.00264 | EMER-2631-WILSHIRE BLVD | 0 | 0 | 0 | 0 | 100%
252 | ANC32.0000.00265 | MARCHMONT LEAK REPAIR | 0 | 0 | 0 | 0 | 100%
253 | ANC32.0000.00266 | SMRP-GETTYSBURG LEAK REPAIR | 0 | 0 | 0 | 0 | 0%
254 | ANC32.0000.00267 | BARBECUE HOLLOW HP MAIN REPL | 0 | 0 | 0 | 0 | 0%
255 | ANC32.0000.00269 | EMER-2621-1809 ALEXANDRIA DR | 0 | 0 | 0 | 0 | 100%
256 | ANC32.0000.00270 | EMER-2621-LOCUST AVE DAMAGE | 0 | 0 | 0 | 0 | 100%
257 | ANC32.0000.00272 | EMER-2621-C14-37 LEAK REPAIR | 0 | 0 | 0 | 0 | 100%
258 | ANC32.0000.00275 | EMER-2621-2233 EXECUTIVE DR | 0 | 0 | 0 | 0 | 100%
259 | ANC32.0000.00277 | ROGER AVE INST | 0 | 0 | 0 | 0 | 100%
260 | ANC32.0000.00280 | FAYETTE MALL LEAK REPAIR | 0 | 0 | 0 | 0 | 100%
261 | ANC32.0000.00281 | EMER-2621-1567 VAN BUREN DR LEAK REPAIR | 0 | 0 | 0 | 0 | 100%
262 | ANC32.0000.00282 | SMRP-WILGUS AVE 24-07694 | 24442.13 | 0 | 0 | 24442.13 | 100%
263 | ANC32.0000.00283 | HARTLAND 4" VLV REPLACEMENT | 0 | 0 | 0 | 0 | 100%
264 | ANC32.0000.00285 | EMER-2621-137 ST ANN LEAK REPAIR | 0 | 0 | 0 | 0 | 100%
265 | ANC32.0000.00286 | EMER-2623-211 CHESTNUT LN LEAK REPAIR | 0 | 0 | 0 | 0 | 100%
266 | ANC32.0000.00287 | EMER-2621-FOUNTAIN BLUE LN DAMAGE | 0 | 0 | 0 | 0 | 100%
267 | ANC32.0000.00288 | EMER-2631-GREENBRIAR RD | 0 | 0 | 0 | 0 | 100%
268 | ANC32.0000.00289 | SMRP-ELM TREE LN X-BORES 24-09466 | 138617.28 | 0 | 12433.79 | 151051.07 | 100%
269 | ANC32.0000.00290 | EMER-2631-CHESTNUT | 0 | 0 | 0 | 0 | 100%
270 | ANC32.0000.00292 | EMER-2621-188 HEDGEWOOD CT | 0 | 0 | 0 | 0 | 100%
271 | ANC32.0000.00293 | EMER-2629-LAMOND RUELLE | 0 | 0 | 0 | 0 | 100%
272 | ANC32.0000.00294 | EMER-2623-101 RANDOLPH RD | 0 | 0 | 0 | 0 | 100%
273 | ANC32.0000.00295 | EMER-2621-HARTLAND DR LEAK REPAIR | 0 | 0 | 0 | 0 | 100%
274 | ANC32.0000.00296 | EMER-2621-GIBSON AVE SL TAP REPAIR | 0 | 0 | 0 | 0 | 100%
275 | ANC32.0000.00297 | R-1463 MAYSVILLE VRG INSTALL | 0 | 0 | 0 | 0 | 50%
276 | ANC32.0000.00299 | REG STATION 1056 PF REG REPL | 0 | 0 | 0 | 0 | 50%
277 | ANC32.0000.00300 | RAVENNA OUTAGE | 0 | 0 | 0 | 0 | 100%
278 | ANC32.0000.00301 | US 60 RECTIFIER GROUND BED INSTALL | 0 | 0 | 0 | 0 | 100%
279 | ANC32.0000.00302 | EMER-2629-6845 LEVEE RD | 0 | 0 | 0 | 0 | 100%
280 | ANC32.0000.00305 | SMRP - CAPITOL AVE | 5036.78 | 133.6 | 2534.6 | 7704.98 | 0%
281 | ANC32.0000.00310 | SMRP - MAIN ST (JIM BEAM) | 2783.74 | 50.67 | 239.77 | 3074.18 | 0%
282 | ANC32.0000.00319 | ARMSTRONG MILL R RELO | 0 | 0 | 0 | 0 | 0%
283 | ANC32.0000.00320 | SMRP - NEW CIRCLE LEAK | 293245.77 | 2969.54 | 94323.17 | 390538.48 | 0%
284 | ANC32.0000.00322 | SMRP - PAUL SAWYLER DR | 490330.43 | 1738.08 | 187121.31 | 679189.82 | 0%
285 | ANC32.0000.00323 | SMRP - GOVERNORS MANSION - 2623 | 3750.54 | 63.86 | 1298.38 | 5112.78 | 0%
286 | ANC32.0000.00325 | SMRP - 2632 - Maysville BSHP | 49039.88 | 1069.05 | 14461.54 | 64570.47 | 0%
287 | ANC32.0000.00326 | 2629-Mutual Ave Land ABN-Winchester | 0 | 2.98 | 0 | 2.98 | 100%
288 | ANC32.0000.00327 | 2629-SMRP Broadway Ave-Cynthiana | 1323627.78 | 16456.46 | 394222.85 | 1734307.09 | 50%
289 | ANC32.0000.00328 | 2629-SMRP W Lexington Ave-Winchester | 27114.24 | 1301.57 | 11861.94 | 40277.75 | 0%
290 | ANC32.0000.00329 | 2629-SMRP Evergreen Dr-Irvine | 595777.18 | 2769.9 | 115093.22 | 713640.3 | 25%
291 | ANC32.0000.00330 | 2623 - SMRP Cleveland Ave - Versailles | 1641708.5 | 5726.74 | 329047.98 | 1976483.22 | 85%
292 | ANC32.0000.00333 | 2621 - SMRP St. Ann (Idle Hour III) - Le | 283102.16 | 1550.24 | 55659.01 | 340311.41 | 20%
293 | ANC32.0000.00334 | ANC-Catletts Creek-Ashland | 89394.9 | 859.07 | 20290.6 | 110544.57 | 0%
294 | ANC32.0000.00338 | 2629-SMRP Regan Dr-Winchester | 3831.94 | 16.5 | 641.85 | 4490.29 | 10%
295 | ANC32.0000.00340 | 2631-ROBERTS DR CASING-ASHLAND | 0 | 0 | 0 | 0 | 0%
296 | ANC32.0000.00342 | 2621-Hunters Rest Ct-Lexington | 252.48 | 10.9 | 303.61 | 566.99 | 100%
297 | ANC32.0000.00364 | 2633-Main St-Hindman | 104.53 | 0.48 | 52.16 | 157.17 | 0%
298 | ANC32.0000.00365 | ANC - E Main St Geo SMRP | 1687.34 | 6.39 | 417.86 | 2111.59 | 0%
299 | ANC32.0000.00366 | ANC- NE 4TH ST FRA SMRP | 7375.34 | 33.26 | 417.86 | 7826.46 | 0%
300 | ANC32.0000.00367 | ANC - SE 4TH ST FRA SMRP | 1896 | 0 | 0 | 1896 | 0%
301 | ANC32.0000.00368 | ANC - PINEHURST DR FRA SMRP | 0 | 0 | 0 | 0 | 0%
302 | ANC32.0000.00369 | ANC - WINDING WAY DR FRA SMRP | 0 | 0 | 0 | 0 | 0%
303 | ANC32.0000.00370 | ANC - CLIFTON RD FRA SMRP | 0 | 0 | 0 | 0 | 0%
304 | ANC32.0000.00371 | ANC - ELM ST VER SMRP | 0 | 0 | 0 | 0 | 0%
305 | ANC32.0000.00372 | ANC - PAYNES MILL RD VER SMRP | 0 | 0 | 0 | 0 | 0%
306 | ANC32.0000.00373 | ANC - E STEPHENS ST MID SMRP | 0 | 0 | 0 | 0 | 0%
307 | ANC32.0000.00374 | 2629-SMRP Lola Dr-Cynthiana | 0 | 0 | 0 | 0 | 0%
308 | ANC32.0000.00382 | 2623-NEWTOWN ANNER-VERSAILLES | 1289.51 | 11.75 | 0 | 1301.26 | 0%
309 | BET32.0000.00002 | 223 GOLD RUSH RD 24-04653 | 697.46 | 0 | 0 | 697.46 | 100%
310 | BET32.0000.00003 | SKYLINE DR VALVE REMOVAL 21-79598 | 3921 | 0 | 2374.5 | 6295.5 | 5%
311 | BET32.0000.00004 | LARKSPUR VALVE INSTALL 22-85729 | 819.48 | 0 | 215.62 | 1035.1 | 0%
312 | BET32.0000.00005 | TAMARACK VALVE INSTALL 22-86466 | 0 | 0 | 0 | 0 | 0%
313 | BET32.0000.00011 | EMER-2621-1333 CENTRE VALVE REPL | 0 | 0 | 0 | 0 | 100%
314 | BET32.0000.00013 | EMER-2623-POCAHONTAS CLAMP REPIAR | 0 | 0 | 0 | 0 | 100%
315 | BET32.0000.00016 | MANCHESTER ST LP RETIREMENT 24-06290 | 0 | 0 | 0 | 0 | 100%
316 | BET32.0000.00018 | CROSSBORE-106 E BROADWAY ST 24-07767 | 0 | 0 | 0 | 0 | 100%
317 | BET32.0000.00022 | RED LICK RD VALVE REPLACEMENT 22-85854 | 101350.69 | 0 | 24164.39 | 125515.08 | 100%
318 | BET32.0000.00023 | ECTON RD RELOCATION 25-13431 | 0 | 0 | 0 | 0 | 100%
319 | BET32.0000.00024 | EMER-2629-WACO LOOP LEAK | 0 | 0 | 0 | 0 | 100%
320 | BET32.0000.00025 | CASING UNDER 13TH 18-54111 | 132431.2 | 0 | 3151.42 | 135582.62 | 100%
321 | BET32.0000.00026 | HWY 27 MAIN LINE EXTENSION 25-12967 | 0 | 0 | 0 | 0 | 0%
322 | BET32.0000.00027 | INEZ EXPOSED MAIN @ BLACKLOG FORK 19-625 | 67.25 | 0 | 20.46 | 87.71 | 100%
323 | BET32.0000.00030 | CYPRESS DR VLV INSTALL 22-86564 | 0 | 0 | 0 | 0 | 0%
324 | BET32.0000.00040 | REPLACE CV C18-46 24-02788 | 0 | 0 | 0 | 0 | 100%
325 | BET32.0000.00042 | CRANCE COURT MLE 24-05531 | 0 | 0 | 0 | 0 | 100%
326 | BET32.0000.00043 | MAN O WAR CV REPLACEMENT 24-06051 | 0 | 0 | 0 | 0 | 100%
327 | BET32.0000.00044 | 32010185 PRESSURE RETEST 24-06339 | 0 | 0 | 0 | 0 | 100%
328 | BET32.0000.00045 | ROBERTS DRIVE SHORTED CASING 24-06656 | 757.41 | 0 | 283.93 | 1041.34 | 0%
329 | BET32.0000.00046 | SMRP-ZANDALE PIF 24-10260 | 0 | 0 | 0 | 0 | 100%
330 | BET32.0000.00048 | ENCROACHMENT-WOODMONT 24-02791 | 0 | 0 | 0 | 0 | 100%
331 | BET32.0000.00049 | EMER - Crossbore remediation | 0 | 0.09 | -2.4009e-15 | 0.09 | 100%
332 | BET32.0000.00059 | 2623-Industry Rd Station Upgrade-Geo | 97054.56 | 1126.61 | 23045.4 | 121226.57 | 10%
333 | BET32.0000.00060 | 2621-Duke Rd/Cooper Dr. Relocation | -7519.36 | 0 | -2304.02 | -9823.38 | 100%
334 | BET32.0000.00061 | 2629-Boone Village Topworks-Richmond | 0 | 0 | 0 | 0 | 0%
335 | BET32.0000.00063 | 2631-Hoods Creek-Ashland | 0 | 0 | 0 | 0 | 0%
336 | GRT32.0000.00002 | 524 SUNSET DR 25-11591 | 0 | 0 | 0 | 0 | 100%
337 | GRT32.0000.00004 | COPPERFIELD TOWNHOMES 22-87144 | 0 | 0 | 0 | 0 | 100%
338 | GRT32.0000.00019 | LOUISA TOWN HILL PLAZE 23-00812 | 0 | 0 | 0 | 0 | 100%
339 | GRT32.0000.00020 | LOCUST HILL ACRES 23-00964 | 82681.3 | 0 | 3630.75 | 86312.05 | 100%
340 | GRT32.0000.00021 | HARRISON CO. HIGH SCHOOL & ATC 23-01476 | 0 | 0 | 0 | 0 | 0%
341 | GRT32.0000.00022 | PHOENIX HILL SUBDIVISION P1 23-01540 | 1117.15 | 0 | 311.46 | 1428.61 | 100%
342 | GRT32.0000.00027 | 1929-1937 FOGG PIKE MLE 23-02559 | 0 | 0 | 0 | 0 | 0%
343 | GRT32.0000.00038 | SOLBERG LANE MLE 23-96687 | 0 | 0 | 0 | 0 | 100%
344 | GRT32.0000.00040 | GAS STATION E MAIN ST EXT 23-97832 | 19346.1 | 0 | 5203.85 | 24549.95 | 100%
345 | GRT32.0000.00044 | SUPER 8 191 FALLS CREEK DR 23-98575 | 0 | 0 | 0 | 0 | 100%
346 | GRT32.0000.00051 | TC ENERGY LINE UM10 24-03829 | 0 | 0 | 0 | 0 | 100%
347 | GRT32.0000.00052 | 111 CHERRY ST 24-04396 | 0 | 0 | 0 | 0 | 100%
348 | GRT32.0000.00055 | EXPRESS OIL CHANGE BULLION BV 24-07005 | 0 | 0 | 0 | 0 | 100%
349 | GRT32.0000.00056 | BALL HOMES-PENINSULA 4 24-07250 | 28325.74 | 0 | 3350.4 | 31676.14 | 100%
350 | GRT32.0000.00057 | 1037 LIME ST MLE 24-07391 | 0 | 0 | 0 | 0 | 100%
351 | GRT32.0000.00058 | BALL HOMES- SANDERS GARDEN P6 24-07470 | 0 | 0 | 0 | 0 | 100%
352 | GRT32.0000.00059 | BUSH BUILDING 403 WAPPING ST 24-07531 | 0 | 0 | 0 | 0 | 100%
353 | GRT32.0000.00060 | POPEYES 101 FINANCIAL WAY 24-07579 | 0 | 0 | 0 | 0 | 100%
354 | GRT32.0000.00061 | 3216 CARRIAGE LN MLE 24-07692 | 0 | 0 | 0 | 0 | 100%
355 | GRT32.0000.00062 | BALL HOMES-ROSE RIDGE P2 24-07751 | 11506.74 | 0 | 3465.08 | 14971.82 | 100%
356 | GRT32.0000.00063 | THE GROVE NICHOLASVILLE 24-08355 | 299286.06 | 0 | 24634.87 | 323920.93 | 100%
357 | GRT32.0000.00064 | 3426 MONTAVESTA RD 24-09328 | 0 | 0 | 0 | 0 | 100%
358 | GRT32.0000.00065 | FOUNTAINS AT PALOMAR PHASE 2 24-09557 | 0 | 0 | 0 | 0 | 100%
359 | GRT32.0000.00066 | LEGENDS VERSAILLES PHASE 6 24-10689 | 0 | 0 | 0 | 0 | 100%
360 | GRT32.0000.00067 | BALL HOMES-SUMMERFIELD P1 25-11893 | 105062.46 | 0 | 11364.33 | 116426.79 | 100%
361 | GRT32.0000.00068 | BET-ALICE LLOYD COLLEGE RELOCATION 19-63 | 0 | 0 | 0 | 0 | 0%
362 | GRT32.0000.00075 | EMER-2621-NORMAN REPL JO | 0 | 0 | 0 | 0 | 100%
363 | GRT32.0000.00077 | 309 WHITE PINE LN 25-11993 | 0 | 0 | 0 | 0 | 100%
364 | GRT32.0000.00078 | BALL HOMES-2509 DYER COVE 25-13134 | 49584.82 | 0 | 5432.68 | 55017.5 | 100%
365 | GRT32.0000.00096 | BOURBON OAKS PARIS PHASE 1 23-98765 | 267.59 | 0 | 260.03 | 527.62 | 0%
366 | GRT32.0000.00097 | UK LIMESTONE PLANT ADDITION 23-98970 | 444459.95 | 2076.33 | 300684.3 | 747220.58 | 100%
367 | GRT32.0000.00098 | SOUTHLAND CHRISTIAN RICHMOND 24-02680 | 0 | 0 | 0 | 0 | 100%
368 | GRT32.0000.00100 | LIMESTONE FARMS DISTILLERY 24-03695 | 0 | 0 | 0 | 0 | 0%
369 | GRT32.0000.00101 | NORMAN LN RESTAURANT 24-04261 | 0 | 0 | 0 | 0 | 100%
370 | GRT32.0000.00102 | BALL HOMES-BELHURST P1 24-05655 | 0 | 0 | 1.0614e-13 | 1.0614e-13 | 100%
371 | GRT32.0000.00103 | THE SILKS CLUB P4 24-07033 | 0 | 0 | 0 | 0 | 100%
372 | GRT32.0000.00104 | 1226 FAIRWAY DR MLE 24-08190 | 0 | 0 | 0 | 0 | 100%
373 | GRT32.0000.00105 | 150 DOYLE LN 24-08664 | 0 | 0 | 0 | 0 | 100%
374 | GRT32.0000.00106 | THE HAVEN PHASE 1 24-09391 | 0 | 0 | 0 | 0 | 100%
375 | GRT32.0000.00107 | PARIS CAR WASH 25-11455 | 0 | 0 | 8.8818e-16 | 8.8818e-16 | 100%
376 | GRT32.0000.00108 | NEWMARKET UNIT 11 25-13070 | 12198.48 | 0 | 0 | 12198.48 | 100%
377 | GRT32.0000.00109 | ANC-R-1301 BIGGS LANE HEATER 20-71985 | 0 | 0 | 0 | 0 | 0%
378 | GRT32.0000.00118 | Patsy Way MLE 2513434 | 8615.74 | 322.45 | 5239.45 | 14177.64 | 100%
379 | GRT32.0000.00120 | 2631 - 2804 PLEASANT AVE MLE - ASHLAND | 118431.53 | 1595.26 | 92311.48 | 212338.27 | 100%
380 | GRT32.0000.00121 | Paddocks of Frankfort | 365884.74 | 7133.4 | 181765.24 | 554783.38 | 100%
381 | GRT32.0000.00122 | BALL HOMES - MASTERSON HILLS MLE | 59345.65 | 481.57 | 27558.39 | 87385.61 | 100%
382 | GRT32.0000.00123 | BALL HOMES SUMMERFIELD PH1 MLE | 0 | 0 | 0 | 0 | 100%
383 | GRT32.0000.00124 | 2621 - PALOMAR FOUNTAINS MLE - LEXINGTON | 60689.44 | 749.73 | 16919.2 | 78358.37 | 100%
384 | GRT32.0000.00130 | 2621-Quintana Estates MLE-Lexington | 0 | 0 | 0 | 0 | 100%
385 | GRT32.0000.00131 | 2621-Carriage Ln MLE-Lexington | 172216.33 | 1435.48 | 81011.77 | 254663.58 | 100%
386 | GRT32.0000.00133 | Ball Homes South Crossing P3 Georgetown | 125238.18 | 7471.36 | 54890.32 | 187599.86 | 100%
387 | GRT32.0000.00134 | ACE HARDWARE MIDWAY | 135864.52 | 562.73 | 49495.88 | 185923.13 | 100%
388 | GRT32.0000.00139 | 2631 - 2029 FERN DRIVE MLE - LOUISA | 10772.98 | 114.56 | 8204.7 | 19092.24 | 90%
389 | GRT32.0000.00140 | 2631 - 124 AUDOBON CT MLE - RUSSELL | 38507.78 | 160.53 | 12591.16 | 51259.47 | 75%
390 | GRT32.0000.00141 | 2629-Boones Crossing MLE-Winchester | 42719.82 | 517.81 | 9634.82 | 52872.45 | 5%
391 | GRT32.0000.00142 | 2623-Village at Lemon Mill-Georgetown | 51348.94 | 531.8 | 27157.84 | 79038.58 | 5%
392 | GRT32.0000.00144 | 2623-Rumpke CNG-Georgetown | 52876.9 | 155.45 | 7279.02 | 60311.37 | 85%
393 | GRT32.0000.00149 | 2621-SPRINGS AT POLO CLUB-LEXINGTON | 15712.88 | 50.6 | 8258.1 | 24021.58 | 100%
394 | GRT32.0000.00159 | 130 LUCILLE DR MIXED USE | 48565.98 | 195.68 | 20839.89 | 69601.55 | 100%
395 | GRT32.0000.00160 | 2631 - SPRINGHAVEN ST MLE - CATLETTSBURG | 10648.11 | 40.61 | 2728.74 | 13417.46 | 50%
396 | GRT32.0000.00161 | 2621-BALL HOMES PATCHEN WILKES-LEXINGTON | 55551.93 | 200.43 | 12015.89 | 67768.25 | 25%
397 | GRT32.0000.00162 | 2629-Colby Rd Development MLE-Winchester | 1031.61 | 6.27 | 0 | 1037.88 | 5%
398 | PIG32.0000.00001 | KY 12-9013.00 DRIFT CULVERT 23-97807 | 484 | 0 | 0 | 484 | 100%
399 | PIG32.0000.00007 | CONNECTOR RD MP RELOCATION 23-00854 | 0 | 0 | 0 | 0 | 0%
400 | PIG32.0000.00011 | SAVANNAH-GUILFORD STORM 24-05283 | 59945.4 | 0 | 0 | 59945.4 | 100%
401 | PIG32.0000.00012 | CSX NEW TRACKS MAYSVILLE 24-07133 | 0 | 0 | 0 | 0 | 100%
402 | PIG32.0000.00013 | KU TRANSFORMER STATION RELOCATION 24-090 | 4680.98 | 0 | 3374.1 | 8055.08 | 100%
403 | PIG32.0000.00015 | STATE ST MP RELOCATION UK 25-11541 | 0 | 0 | 0 | 0 | 100%
404 | PIG32.0000.00016 | UK ELIZABETH ST HP/MP RELOCATION 25-1362 | -85440.98 | 0 | 0 | -85440.98 | 100%
405 | PIG32.0000.00017 | UK MP MAIN RETIREMENT 23-01315 | 0 | 0 | 0 | 0 | 100%
406 | PIG32.0000.00022 | RACE ST ABANDONMENT 24-05251 | 0 | 0 | 0 | 0 | 100%
407 | PIG32.0000.00024 | ANC-MARATHON BOND/ALEXNADRIA DR ANODE BE | 0 | 0 | 0 | 0 | 100%
408 | PIG32.0000.00027 | KYTC ITEM 7-113.02 LEESTOWN RD 19-68251 | 0 | 0 | 0 | 0 | 100%
409 | PIG32.0000.00028 | RICHMOND RD RCUT 20-75930 | 0 | 0 | 0 | 0 | 100%
410 | PIG32.0000.00030 | JOYLAND AREA STORM 21-84395 | 0 | 0 | 0 | 0 | 100%
411 | PIG32.0000.00037 | MEADOWTHORPE STORM SEWER 23-95080 | 0 | 0 | 0 | 0 | 100%
412 | PIG32.0000.00038 | UK HP RELOCATION CANCER CENTER 23-95330 | 0 | 0 | 0 | 0 | 100%
413 | PIG32.0000.00039 | COOPER DRIVE STORMWATER IMPROVEMENT 23-9 | 314.96 | 0 | 351.93 | 666.89 | 100%
414 | PIG32.0000.00041 | ASHLAND STREETSCAPE PROJECT 23-98273 | 0 | 0 | 0 | 0 | 100%
415 | PIG32.0000.00043 | KYTC ITEM 7-252.00 NEWTOWN PIKE 23-99054 | 254279.38 | 0 | 12623.34 | 266902.72 | 100%
416 | PIG32.0000.00047 | GREENUP AVE RELOCATION 24-06689 | 0 | 0 | 0 | 0 | 0%
417 | PIG32.0000.00049 | POLLARD MILLS PHASE 4 24-09943 | 68805.32 | 0 | 0 | 68805.32 | 100%
418 | PIG32.0000.00050 | MAIN ST SIDEWALK RELOCATION (WINCHESTER) | 0 | 0 | 0 | 0 | 100%
419 | PIG32.0000.00051 | 2629 - SANDE RIDGE RELO. - MT. STERLING | 16102.63 | 0 | 2143.62 | 18246.25 | 100%
420 | PIG32.0000.00052 | PIG-KY 292 Shallow Main-South Williamson | 125294.6 | 900.58 | 30644.96 | 156840.14 | 50%
421 | PIG32.0000.00053 | Finnely Relocation | 66806.98 | 243.91 | 15072.06 | 82122.95 | 100%
422 | PIG32.0000.00055 | 2629-S Highland St Relocation-Winchester | 0 | 0 | 0 | 0 | 0%
423 | PIG32.0000.00057 | 2631-S 5th Street-Greenup | 11769.83 | 231.75 | 2813.97 | 14815.55 | 90%
424 | PIG32.0000.00061 | Armstrong Mill Relocation | 12557.87 | 458.22 | 10091.76 | 23107.85 | 0%
425 | PIG32.0000.00064 | PIG-Liberty Road-Lexington | 56173.32 | 87.16 | 4701.45 | 60961.93 | 0%
426 | PIG32.0000.00065 | 2621-N Limestone-Lexington | 41335.49 | 748.95 | 15836.55 | 57920.99 | 0%
427 | PIG32.0000.00066 | 2623 - PIG - HOLMES ST RELO - FRA | 23614.33 | 322.3 | 6637.26 | 30573.89 | 5%
428 | PIG32.0000.00067 | 2621-Coleman ct-Lexington | 0 | 0 | 0 | 0 | 0%
429 | PIG32.0000.00068 | 2629-Stone Trace Dr Relo-Mt Sterling | 0 | 0 | 0 | 0 | 0%
430 | PIG32.0000.00069 | 2621-Redmile Rd Abandonment-Lexington | 13576.26 | 74.53 | 6955.28 | 20606.07 | 100%
431 | PIG32.0000.00070 | 2621-LAKEWOOD DRIVE RELO-LEXINGTON | -2.2098e-12 | 0 | -3.2685e-13 | -2.5366e-12 | 100%
432 | PIG32.0000.00071 | 2621-BRANNON RD RELOCATION-NICHOLASVILLE | 506 | 4.6 | 0 | 510.6 | 5%
433 | PIG32.0000.00072 | PIG - LIMA DR HP - LEXINGTON | 0 | 0 | 0 | 0 | 0%
434 | PIG32.0000.00073 | 2621-Buchanan St-Lexington | 1478.94 | 17.02 | 389.2 | 1885.16 | 0%
435 | PIG32.0000.00074 | 2621-Innovation Dr-Lexington | 2963.7 | 8.03 | 565.01 | 3536.74 | 0%
436 | PIG32.0000.00075 | 2621 - PIG - UK PATIENT TOWER 2 - LEX | 0 | 0 | 0 | 0 | 0%
437 | PIG32.0000.00076 | 2621-US25-Lexington | 0 | 0 | 0 | 0 | 0%
438 | PIG32.0000.00077 | Hagermans Ct Abdn | 0 | 0 | 0 | 0 | 100%
* The other inderect costs represent Supervision, Engineering, General, and Administrative Costs

## Sheet1 (hidden)
Project No. (B) | Project No. (B)
18026779401 | 18026779401
18026794401 | 18026794401
18026795501 | 18026795501
19026867802 | 19026867802
20026983300 | 20026983300
21026123000 | 21026123000
21026152101 | 21026152101
22026161800 | 22026161800
22026165501 | 22026165501
22026178300 | 22026178300
22026207100 | 22026207100
22026224201 | 22026224201
22026231301 | 22026231301
22026236501 | 22026236501
22026236901 | 22026236901
22026237301 | 22026237301
22026238401 | 22026238401
22026239702 | 22026239702
23026258300 | 23026258300
23026270600 | 23026270600
23026283101 | 23026283101
23026283600 | 23026283600
23026286900 | 23026286900
23026287300 | 23026287300
23026300300 | 23026300300
23026301200 | 23026301200
23026306800 | 23026306800
23026308100 | 23026308100
24026312301 | 24026312301
24026312500 | 24026312500
24026313000 | 24026313000
24026314400 | 24026314400
24026316701 | 24026316701
24026324100 | 24026324100
24026333201 | 24026333201
24026333600 | 24026333600
24026336600 | 24026336600
24026340200 | 24026340200
24026340500 | 24026340500
24026340800 | 24026340800
24026341000 | 24026341000
24026341800 | 24026341800
24026341900 | 24026341900
24026345800 | 24026345800
24026348200 | 24026348200
24026348900 | 24026348900
24026349200 | 24026349200
24026349300 | 24026349300
24026349500 | 24026349500
24026351200 | 24026351200
24026352000 | 24026352000
24026354300 | 24026354300
24026355200 | 24026355200
24026355300 | 24026355300
24026355900 | 24026355900
24026356000 | 24026356000
24026356200 | 24026356200
24026356500 | 24026356500
24026357000 | 24026357000
24026357400 | 24026357400
24026358600 | 24026358600
24026358700 | 24026358700
24026358801 | 24026358801
24026359401 | 24026359401
24026360200 | 24026360200
24026360500 | 24026360500
24026360700 | 24026360700
24026361300 | 24026361300
24026361400 | 24026361400
24026361500 | 24026361500
24026362000 | 24026362000
24026363600 | 24026363600
24026363800 | 24026363800
24026364900 | 24026364900
24026365000 | 24026365000
24026365300 | 24026365300
24026365700 | 24026365700
24026366400 | 24026366400
24026367000 | 24026367000
24026367700 | 24026367700
24026368000 | 24026368000
24026368600 | 24026368600
24026368800 | 24026368800
24026369000 | 24026369000
24026370500 | 24026370500
24026370600 | 24026370600
24026371100 | 24026371100
24026371600 | 24026371600
24026371800 | 24026371800
24026372000 | 24026372000
24026373800 | 24026373800
24026375200 | 24026375200
24026376300 | 24026376300
24026376700 | 24026376700
24026376901 | 24026376901
25026377600 | 25026377300
25026377900 | 25026377600
25026378600 | 25026377900
25026378800 | 25026378600
25026379000 | 25026378800
25026381300 | 25026379000
25026381700 | 25026381300
25026381800 | 25026381700
25026385100 | 25026381800
25026392000 | 25026385100
25026393800 | 25026392000
25026394000 | 25026393800
25026395600 | 25026394000
25026396000 | 25026395600
25026397400 | 25026396000
25026398400 | 25026397400
25026398800 | 25026398400
25026399300 | 25026398800
25026399900 | 25026399300
25026400200 | 25026399900
25026400900 | 25026400200
25026403000 | 25026400900
25026403300 | 25026403000
25026405400 | 25026403300
25026406000 | 25026405400
25026406300 | 25026406000
25026407800 | 25026406300
25026409300 | 25026407800
25026409900 | 25026409300
25026410100 | 25026409900
25026410400 | 25026410100
25026410600 | 25026410400
25026410800 | 25026410600
ANC32.0000.00002 | 25026410800
ANC32.0000.00004 | ANC32.0000.00002
ANC32.0000.00005 | ANC32.0000.00004
ANC32.0000.00006 | ANC32.0000.00005
ANC32.0000.00007 | ANC32.0000.00006
ANC32.0000.00010 | ANC32.0000.00007
ANC32.0000.00014 | ANC32.0000.00010
ANC32.0000.00017 | ANC32.0000.00014
ANC32.0000.00018 | ANC32.0000.00017
ANC32.0000.00019 | ANC32.0000.00018
ANC32.0000.00020 | ANC32.0000.00019
ANC32.0000.00049 | ANC32.0000.00020
ANC32.0000.00050 | ANC32.0000.00049
ANC32.0000.00051 | ANC32.0000.00050
ANC32.0000.00052 | ANC32.0000.00051
ANC32.0000.00054 | ANC32.0000.00052
ANC32.0000.00056 | ANC32.0000.00054
ANC32.0000.00057 | ANC32.0000.00056
ANC32.0000.00058 | ANC32.0000.00057
ANC32.0000.00059 | ANC32.0000.00058
ANC32.0000.00060 | ANC32.0000.00059
ANC32.0000.00061 | ANC32.0000.00060
ANC32.0000.00062 | ANC32.0000.00061
ANC32.0000.00063 | ANC32.0000.00062
ANC32.0000.00068 | ANC32.0000.00063
ANC32.0000.00071 | ANC32.0000.00068
ANC32.0000.00074 | ANC32.0000.00071
ANC32.0000.00075 | ANC32.0000.00074
ANC32.0000.00076 | ANC32.0000.00075
ANC32.0000.00077 | ANC32.0000.00076
ANC32.0000.00078 | ANC32.0000.00077
ANC32.0000.00080 | ANC32.0000.00078
ANC32.0000.00081 | ANC32.0000.00080
ANC32.0000.00082 | ANC32.0000.00081
ANC32.0000.00083 | ANC32.0000.00082
ANC32.0000.00084 | ANC32.0000.00083
ANC32.0000.00085 | ANC32.0000.00084
ANC32.0000.00086 | ANC32.0000.00085
ANC32.0000.00087 | ANC32.0000.00086
ANC32.0000.00088 | ANC32.0000.00087
ANC32.0000.00089 | ANC32.0000.00088
ANC32.0000.00090 | ANC32.0000.00089
ANC32.0000.00092 | ANC32.0000.00090
ANC32.0000.00093 | ANC32.0000.00092
ANC32.0000.00094 | ANC32.0000.00093
ANC32.0000.00095 | ANC32.0000.00094
ANC32.0000.00098 | ANC32.0000.00095
ANC32.0000.00099 | ANC32.0000.00098
ANC32.0000.00100 | ANC32.0000.00099
ANC32.0000.00110 | ANC32.0000.00100
ANC32.0000.00113 | ANC32.0000.00110
ANC32.0000.00119 | ANC32.0000.00113
ANC32.0000.00120 | ANC32.0000.00119
ANC32.0000.00121 | ANC32.0000.00120
ANC32.0000.00122 | ANC32.0000.00121
ANC32.0000.00124 | ANC32.0000.00122
ANC32.0000.00126 | ANC32.0000.00124
ANC32.0000.00127 | ANC32.0000.00126
ANC32.0000.00128 | ANC32.0000.00127
ANC32.0000.00129 | ANC32.0000.00128
ANC32.0000.00132 | ANC32.0000.00129
ANC32.0000.00133 | ANC32.0000.00132
ANC32.0000.00136 | ANC32.0000.00133
ANC32.0000.00137 | ANC32.0000.00136
ANC32.0000.00140 | ANC32.0000.00137
ANC32.0000.00141 | ANC32.0000.00140
ANC32.0000.00143 | ANC32.0000.00141
ANC32.0000.00144 | ANC32.0000.00143
ANC32.0000.00145 | ANC32.0000.00144
ANC32.0000.00146 | ANC32.0000.00145
ANC32.0000.00147 | ANC32.0000.00146
ANC32.0000.00148 | ANC32.0000.00147
ANC32.0000.00149 | ANC32.0000.00148
ANC32.0000.00150 | ANC32.0000.00149
ANC32.0000.00151 | ANC32.0000.00150
ANC32.0000.00152 | ANC32.0000.00151
ANC32.0000.00153 | ANC32.0000.00152
ANC32.0000.00154 | ANC32.0000.00153
ANC32.0000.00157 | ANC32.0000.00154
ANC32.0000.00158 | ANC32.0000.00157
ANC32.0000.00163 | ANC32.0000.00158
ANC32.0000.00165 | ANC32.0000.00163
ANC32.0000.00167 | ANC32.0000.00165
ANC32.0000.00170 | ANC32.0000.00167
ANC32.0000.00171 | ANC32.0000.00170
ANC32.0000.00174 | ANC32.0000.00171
ANC32.0000.00176 | ANC32.0000.00174
ANC32.0000.00178 | ANC32.0000.00176
ANC32.0000.00179 | ANC32.0000.00178
ANC32.0000.00180 | ANC32.0000.00179
ANC32.0000.00181 | ANC32.0000.00180
ANC32.0000.00184 | ANC32.0000.00181
ANC32.0000.00187 | ANC32.0000.00184
ANC32.0000.00191 | ANC32.0000.00187
ANC32.0000.00192 | ANC32.0000.00191
ANC32.0000.00193 | ANC32.0000.00192
ANC32.0000.00194 | ANC32.0000.00193
ANC32.0000.00195 | ANC32.0000.00194
ANC32.0000.00196 | ANC32.0000.00195
ANC32.0000.00197 | ANC32.0000.00196
ANC32.0000.00198 | ANC32.0000.00197
ANC32.0000.00199 | ANC32.0000.00198
ANC32.0000.00200 | ANC32.0000.00199
ANC32.0000.00202 | ANC32.0000.00200
ANC32.0000.00209 | ANC32.0000.00202
ANC32.0000.00226 | ANC32.0000.00209
ANC32.0000.00230 | ANC32.0000.00226
ANC32.0000.00234 | ANC32.0000.00230
ANC32.0000.00235 | ANC32.0000.00234
ANC32.0000.00239 | ANC32.0000.00235
ANC32.0000.00248 | ANC32.0000.00239
ANC32.0000.00249 | ANC32.0000.00248
ANC32.0000.00250 | ANC32.0000.00249
ANC32.0000.00251 | ANC32.0000.00250
ANC32.0000.00252 | ANC32.0000.00251
ANC32.0000.00253 | ANC32.0000.00252
ANC32.0000.00256 | ANC32.0000.00253
ANC32.0000.00257 | ANC32.0000.00256
ANC32.0000.00259 | ANC32.0000.00257
ANC32.0000.00260 | ANC32.0000.00259
ANC32.0000.00262 | ANC32.0000.00260
ANC32.0000.00263 | ANC32.0000.00262
ANC32.0000.00264 | ANC32.0000.00263
ANC32.0000.00265 | ANC32.0000.00264
ANC32.0000.00266 | ANC32.0000.00265
ANC32.0000.00267 | ANC32.0000.00266
ANC32.0000.00269 | ANC32.0000.00267
ANC32.0000.00270 | ANC32.0000.00269
ANC32.0000.00272 | ANC32.0000.00270
ANC32.0000.00275 | ANC32.0000.00272
ANC32.0000.00277 | ANC32.0000.00275
ANC32.0000.00280 | ANC32.0000.00277
ANC32.0000.00281 | ANC32.0000.00280
ANC32.0000.00282 | ANC32.0000.00281
ANC32.0000.00283 | ANC32.0000.00282
ANC32.0000.00285 | ANC32.0000.00283
ANC32.0000.00286 | ANC32.0000.00285
ANC32.0000.00287 | ANC32.0000.00286
ANC32.0000.00288 | ANC32.0000.00287
ANC32.0000.00289 | ANC32.0000.00288
ANC32.0000.00290 | ANC32.0000.00289
ANC32.0000.00292 | ANC32.0000.00290
ANC32.0000.00293 | ANC32.0000.00292
ANC32.0000.00294 | ANC32.0000.00293
ANC32.0000.00295 | ANC32.0000.00294
ANC32.0000.00296 | ANC32.0000.00295
ANC32.0000.00297 | ANC32.0000.00296
ANC32.0000.00299 | ANC32.0000.00297
ANC32.0000.00300 | ANC32.0000.00299
ANC32.0000.00301 | ANC32.0000.00300
ANC32.0000.00302 | ANC32.0000.00301
ANC32.0000.00305 | ANC32.0000.00302
ANC32.0000.00310 | ANC32.0000.00305
ANC32.0000.00319 | ANC32.0000.00310
ANC32.0000.00320 | ANC32.0000.00319
ANC32.0000.00322 | ANC32.0000.00320
ANC32.0000.00323 | ANC32.0000.00322
ANC32.0000.00325 | ANC32.0000.00323
ANC32.0000.00326 | ANC32.0000.00325
ANC32.0000.00327 | ANC32.0000.00326
ANC32.0000.00328 | ANC32.0000.00327
ANC32.0000.00329 | ANC32.0000.00328
ANC32.0000.00330 | ANC32.0000.00329
ANC32.0000.00333 | ANC32.0000.00330
ANC32.0000.00334 | ANC32.0000.00333
ANC32.0000.00338 | ANC32.0000.00334
ANC32.0000.00340 | ANC32.0000.00338
ANC32.0000.00342 | ANC32.0000.00340
ANC32.0000.00364 | ANC32.0000.00342
ANC32.0000.00365 | ANC32.0000.00364
ANC32.0000.00366 | ANC32.0000.00365
ANC32.0000.00367 | ANC32.0000.00366
ANC32.0000.00368 | ANC32.0000.00367
ANC32.0000.00369 | ANC32.0000.00368
ANC32.0000.00370 | ANC32.0000.00369
ANC32.0000.00371 | ANC32.0000.00370
ANC32.0000.00372 | ANC32.0000.00371
ANC32.0000.00373 | ANC32.0000.00372
ANC32.0000.00374 | ANC32.0000.00373
ANC32.0000.00382 | ANC32.0000.00374
BET32.0000.00002 | ANC32.0000.00382
BET32.0000.00003 | BET32.0000.00002
BET32.0000.00004 | BET32.0000.00003
BET32.0000.00005 | BET32.0000.00004
BET32.0000.00011 | BET32.0000.00005
BET32.0000.00013 | BET32.0000.00011
BET32.0000.00016 | BET32.0000.00013
BET32.0000.00018 | BET32.0000.00016
BET32.0000.00022 | BET32.0000.00018
BET32.0000.00023 | BET32.0000.00022
BET32.0000.00024 | BET32.0000.00023
BET32.0000.00025 | BET32.0000.00024
BET32.0000.00026 | BET32.0000.00025
BET32.0000.00027 | BET32.0000.00026
BET32.0000.00030 | BET32.0000.00027
BET32.0000.00040 | BET32.0000.00030
BET32.0000.00042 | BET32.0000.00040
BET32.0000.00043 | BET32.0000.00042
BET32.0000.00044 | BET32.0000.00043
BET32.0000.00045 | BET32.0000.00044
BET32.0000.00046 | BET32.0000.00045
BET32.0000.00048 | BET32.0000.00046
BET32.0000.00049 | BET32.0000.00048
BET32.0000.00059 | BET32.0000.00049
BET32.0000.00060 | BET32.0000.00059
BET32.0000.00061 | BET32.0000.00060
BET32.0000.00063 | BET32.0000.00061
GRT32.0000.00002 | BET32.0000.00063
GRT32.0000.00004 | GRT32.0000.00002
GRT32.0000.00019 | GRT32.0000.00004
GRT32.0000.00020 | GRT32.0000.00019
GRT32.0000.00021 | GRT32.0000.00020
GRT32.0000.00022 | GRT32.0000.00021
GRT32.0000.00027 | GRT32.0000.00022
GRT32.0000.00038 | GRT32.0000.00027
GRT32.0000.00040 | GRT32.0000.00038
GRT32.0000.00044 | GRT32.0000.00040
GRT32.0000.00051 | GRT32.0000.00044
GRT32.0000.00052 | GRT32.0000.00051
GRT32.0000.00055 | GRT32.0000.00052
GRT32.0000.00056 | GRT32.0000.00055
GRT32.0000.00057 | GRT32.0000.00056
GRT32.0000.00058 | GRT32.0000.00057
GRT32.0000.00059 | GRT32.0000.00058
GRT32.0000.00060 | GRT32.0000.00059
GRT32.0000.00061 | GRT32.0000.00060
GRT32.0000.00062 | GRT32.0000.00061
GRT32.0000.00063 | GRT32.0000.00062
GRT32.0000.00064 | GRT32.0000.00063
GRT32.0000.00065 | GRT32.0000.00064
GRT32.0000.00066 | GRT32.0000.00065
GRT32.0000.00067 | GRT32.0000.00066
GRT32.0000.00068 | GRT32.0000.00067
GRT32.0000.00075 | GRT32.0000.00068
GRT32.0000.00077 | GRT32.0000.00075
GRT32.0000.00078 | GRT32.0000.00077
GRT32.0000.00096 | GRT32.0000.00078
GRT32.0000.00097 | GRT32.0000.00096
GRT32.0000.00098 | GRT32.0000.00097
GRT32.0000.00100 | GRT32.0000.00098
GRT32.0000.00101 | GRT32.0000.00100
GRT32.0000.00102 | GRT32.0000.00101
GRT32.0000.00103 | GRT32.0000.00102
GRT32.0000.00104 | GRT32.0000.00103
GRT32.0000.00105 | GRT32.0000.00104
GRT32.0000.00106 | GRT32.0000.00105
GRT32.0000.00107 | GRT32.0000.00106
GRT32.0000.00108 | GRT32.0000.00107
GRT32.0000.00109 | GRT32.0000.00108
GRT32.0000.00118 | GRT32.0000.00109
GRT32.0000.00120 | GRT32.0000.00118
GRT32.0000.00121 | GRT32.0000.00120
GRT32.0000.00122 | GRT32.0000.00121
GRT32.0000.00123 | GRT32.0000.00122
GRT32.0000.00124 | GRT32.0000.00123
GRT32.0000.00130 | GRT32.0000.00124
GRT32.0000.00131 | GRT32.0000.00130
GRT32.0000.00133 | GRT32.0000.00131
GRT32.0000.00134 | GRT32.0000.00133
GRT32.0000.00139 | GRT32.0000.00134
GRT32.0000.00140 | GRT32.0000.00139
GRT32.0000.00141 | GRT32.0000.00140
GRT32.0000.00142 | GRT32.0000.00141
GRT32.0000.00144 | GRT32.0000.00142
GRT32.0000.00149 | GRT32.0000.00144
GRT32.0000.00159 | GRT32.0000.00149
GRT32.0000.00160 | GRT32.0000.00159
GRT32.0000.00161 | GRT32.0000.00160
GRT32.0000.00162 | GRT32.0000.00161
PIG32.0000.00001 | GRT32.0000.00162
PIG32.0000.00007 | PIG32.0000.00001
PIG32.0000.00011 | PIG32.0000.00007
PIG32.0000.00012 | PIG32.0000.00011
PIG32.0000.00013 | PIG32.0000.00012
PIG32.0000.00015 | PIG32.0000.00013
PIG32.0000.00016 | PIG32.0000.00015
PIG32.0000.00017 | PIG32.0000.00016
PIG32.0000.00022 | PIG32.0000.00017
PIG32.0000.00024 | PIG32.0000.00022
PIG32.0000.00027 | PIG32.0000.00024
PIG32.0000.00028 | PIG32.0000.00027
PIG32.0000.00030 | PIG32.0000.00028
PIG32.0000.00037 | PIG32.0000.00030
PIG32.0000.00038 | PIG32.0000.00037
PIG32.0000.00039 | PIG32.0000.00038
PIG32.0000.00041 | PIG32.0000.00039
PIG32.0000.00043 | PIG32.0000.00041
PIG32.0000.00047 | PIG32.0000.00043
PIG32.0000.00049 | PIG32.0000.00047
PIG32.0000.00050 | PIG32.0000.00049
PIG32.0000.00051 | PIG32.0000.00050
PIG32.0000.00052 | PIG32.0000.00051
PIG32.0000.00053 | PIG32.0000.00052
PIG32.0000.00055 | PIG32.0000.00053
PIG32.0000.00057 | PIG32.0000.00055
PIG32.0000.00061 | PIG32.0000.00057
PIG32.0000.00064 | PIG32.0000.00061
PIG32.0000.00065 | PIG32.0000.00064
PIG32.0000.00066 | PIG32.0000.00065
PIG32.0000.00067 | PIG32.0000.00066
PIG32.0000.00068 | PIG32.0000.00067
PIG32.0000.00069 | PIG32.0000.00068
PIG32.0000.00070 | PIG32.0000.00069
PIG32.0000.00071 | PIG32.0000.00070
PIG32.0000.00072 | PIG32.0000.00071
PIG32.0000.00073 | PIG32.0000.00072
PIG32.0000.00074 | PIG32.0000.00073
PIG32.0000.00075 | PIG32.0000.00074
PIG32.0000.00076 | PIG32.0000.00075
PIG32.0000.00077 | PIG32.0000.00076
PIG32.0000.00077

## Cognos Pivot (hidden)
Complete Dt | (All)
Job Type | Job Order | Job Summary | Construction Amount | AFUDC Cost | Sum of Actual SEGA Cost
555 | 23026270600 | INSTALL 550' OF 2" PMMP | 32176.87 | 112.86 | 11055.97
| 23026300300 | INSTALL 1810'-2" PMMP | 169099.2 | 0 | 48176.3
| 24026314400 | INSTALL 1,200'-4" PMMP | 314291.89 | 842.19 | 126658.96
| 24026324100 | INSTALL 670'-2' PMIP | 70340.21 | 65.98 | 20774.31
| 24026333600 | INSTALL 75'-2" PMIP | 20999.52 | 63.22 | 7325.09
| 24026340200 | INSTALL 600' OF 8"PMMP MAIN | 252920.57 | 3.55 | 135661.1
| 24026341900 | INSTALL 4250' OF 2"/4"PMMP | 123201.12 | 1554.37 | 35397.86
| 23026283101 | INSTALL 780'-2" PMMP | 55147.55 | 264.86 | 16369.79
| 24026351200 | INSTALL 150' OF 2"PMIP MAIN | 10748.24 | 56.14 | 3694.82
| 24026352000 | INSTALL 700'-2" PMMP | 45137.93 | 191.85 | 30456.84
| 24026354300 | INSTALL 1750' OF 2"PMMP MAIN | 38943.9 | 397.42 | 10579.29
| 24026355200 | INSTALL 150'-4" PMLP | 47198.15 | 158.91 | 10012.57
| 24026355300 | INSTALL 250'-2" PMMP | 18029.99 | 58.25 | 6376.23
| 24026355900 | INSTALL 250' OF 2"PMMP MAIN | 45125.07 | 156.57 | 11024.65
| 24026358700 | INSTALL 100' OF 2" PMMP MLE | 18509.29 | 115.35 | 5979.53
| 24026359401 | INSTALL 200' OF 4" PMIP | 38733.92 | 312.76 | 22939.46
| 24026361400 | INSTALL 100' OF 2" PMIP | 19693.71 | 79.07 | 8317.14
| 24026364900 | INSTALL 2,300'-4" PMMP | 148950.54 | 1946.52 | 64302.96
| 24026365700 | INSTALL 320' OF 2"PMIP MAIN | 23129.64 | 71.83 | 6553.26
| 24026366400 | INSTALL ~390'-2" PMIP | 29320.23 | 201.07 | 15381.14
| 24026368600 | INSTALL 640' OF 2" PMMP | 39119.75 | 206.36 | 11058.82
| 24026372000 | INSTALLING 500'-2" PMMP | 27862.38 | 129.25 | 19897.92
| 25026381700 | INSTALL 230' OF 2" PMIP | 65381.23 | 156.74 | 24162.21
| 25026381800 | INSTALL 250'-2" PMMP | 35913.95 | 148.61 | 16293.19
| 25026392000 | INSTALL 140'-2" PMMP | 17057.86 | 71.04 | 4386.57
| 25026393800 | INSTALL 2,100'-2" PMMP | 88029.82 | 341.85 | 22625.59
| 25026398800 | INSTALL 3670' OF 2"/4"PMMP MN | 100303.49 | 556.94 | 29484.97
557 | 22026161800 | INSTALL 8" PCF | 27472.22 | 26.6 | 2046.08
| 22026178300 | EMER-INSTALL 5'OF 2"PMMP MAIN | 2323.18 | 94.82 | 396.42
| 24026313000 | INSTALL 1570'-2" PMMP | 393446.75 | 826.08 | 108384.72
| 24026340800 | EMER - INSTALL 15'-2" PMMP | 11656.77 | 501.84 | 3552.15
| 18026794401 | INSTALL 4400'-2"/4"PMMP MAIN | 911090.93 | 1850.82 | 337955.6
| 18026795501 | INSTALL 14,600'-2,4,6,8" PMMP | 2550504.17 | 80451.23 | 795088.38
| 20026983300 | INSTALL 6,600'-2"/4" PMMP | 1534319.1 | 11630.26 | 469280.69
| 21026152101 | INSTALL 535' OF 8"CSHP MAIN | 365253.86 | 4902.8 | 110804.19
| 22026165501 | INSTALL 3385' OF 2" PMMP | 269735.58 | 1645.51 | 76571.04
| 22026207100 | INSTALL 7870'-2", 4" PMMP | 1159198.32 | 14496.31 | 375429.09
| 22026224201 | INSTALL 2300' OF 2"/4"PMMP | 453364.41 | 6363.9 | 129037.98
| 22026231301 | INSTALL 925' OF 2"PMMP MAIN | 297960.14 | 2049.43 | 88662.05
| 22026236501 | INSTALL 1325' OF 4"/8"CSHP MN | 984938.33 | 20338.34 | 401810.09
| 22026236901 | INSTALL 11300'-2" PMMP | 2006758.56 | 34581.37 | 585250.99
| 22026237301 | INSTALL 11,150'-8"6"4"2" PMMP | 2378997.6 | 59811.55 | 738466.4
| 22026238401 | INSTALL 5765'-2" PMMP | 1085630.93 | 730.83 | 335798.81
| 22026239702 | INSTALL 8650' - 2,4,6" PMMP | 1448355.47 | 46321.39 | 439987.19
| 23026283600 | INSTALL LP FITTINGS | 7295.61 | 79.82 | 2283.27
| 24026316701 | INSTALL 11245' OF 2"PMMP MAIN | 810698.55 | 14886.26 | 259302.43
| 24026333201 | EMER - INSTALL 478'-4" PMLP | 141419.14 | 615.39 | 63412.76
| 24026349500 | INSTALL 40'-12" CSMP | 157739.14 | 3131.06 | 77024.06
| 24026356000 | INSTALL 475' OF 2"PMMP MAIN | 113053.66 | 757.69 | 24306.51
| 24026356200 | INSTALL NEW 4" CRITICAL VALVE | 4706.14 | 23.41 | 1508.37
| 24026356500 | EMER - INSTALL 2'-2" PMIP | 3685.18 | 12.32 | 1168.21
| 24026357000 | EMER-INSTALL 50' OF 4"PMLP | 14737.82 | 94.63 | 4738.17
| 24026360200 | EMER-INSTALL 3' OF 2"PMMP MAIN | 9660.3 | 26.42 | 3105.03
| 24026361500 | EMER - INSTALL 2'-3" PMLP | 3731.68 | 8.61 | 1143.88
| 24026362000 | EMER-INSTALL 3' OF 3"PMMP MAIN | 13448.14 | 58.57 | 4776.31
| 24026363600 | INSTALL 620' OF 4"PMMP MAIN | 218520.62 | 762.88 | 55910.1
| 24026365000 | EMER-INSTALL 10' - 2" PMMP | 2446.08 | 0.49 | 594
| 24026365300 | EMER INSTALL 5" OF 4" PMLP | 20766.8 | 44.62 | 5422.64
| 24026367000 | EMER INSTALL 5'-2" PMMP | 6199.62 | 6.25 | 1703.54
| 24026368000 | EMER - INSTALL 5'-2" PMMP | 3479.67 | 13.09 | 1052.91
| 24026369000 | INSTALL 65'-8" PMLP | 124747.47 | 517.71 | 19701.63
| 24026371100 | EMER-INSTALL 6' OF 8"PMMP | 4659.38 | 18.01 | 1064.95
| 24026371600 | EMER - INSTALL 5' - 2" PMMP | 4843.72 | 3.32 | 1525.26
| 24026371800 | EMER - INSTALL 3'-2" PMMP | 15899.24 | 55.15 | 3305.14
| 24026373800 | EMER - INSTALL 3'-2" PMMP | 4719.22 | 10.75 | 1284.63
| 24026375200 | EMER-INSTALL 6' OF 2"PMMP MAIN | 5596.02 | 22.85 | 1231.66
| 24026376300 | EMER - INSTALL 5'-2" PMIP | 5035.7 | 10.75 | 1468.25
| 24026376700 | EMER - INSTALL 3'-2" PMMP | 2530.73 | 2.21 | 608.86
| 25026377300 | EMER - INSTALL 1'-2" PMLP | 0.64 | 0 | -824.31
| 25026378800 | EMER - INSTALL 25'-2" PMMP | 58495.62 | 112.31 | 22639.38
| 25026379000 | EMER - INSTALL 9'-2" PMMP | 859.88 | 2.86 | 321.52
| 25026381300 | EMER-INSTALL 180' OF 4"PMLP MN | 2117.88 | 84.11 | 719.67
| 25026385100 | EMER-INSTALL 4' OF 4"PMMP MAIN | 7238.82 | 333.19 | 2979.8
| 25026394000 | EMER INSERT 280'-1.2" PMIP | 1543.23 | 0 | 674.21
| 25026395600 | EMER-INSTALL 3' OF 3"PMMP MAIN | 250.66 | 0 | 79.57
| 25026397400 | EMER-INSTALL 3' OF 2"PMMP MAIN | 5686.06 | 130.41 | 2111.95
| 25026398400 | EMER - INSTALL FITTINGS | 4719.43 | 20.36 | 2120.46
| 25026399300 | EMER - INSTALL 5'-2" PMMP | 1551.21 | 45.97 | 701.15
| 25026400900 | EMER - INSTALL 2'-4" PMMP | 4316.75 | 18.92 | 1994.34
| 25026403000 | EMER - INSTALL 2'-3" PMMP | 230.88 | 0 | 0
| 25026405400 | EMER - INSTALL 2'-2" PMMP | 2824.62 | 10.14 | 744.56
| 25026406000 | EMER - INSTALL 2'-2" PMLP | 3188.3 | 59.66 | 871.06
| 25026406300 | INSTALL 15'-6" PMLP | 8321.58 | 108.24 | 2160.76
| 25026407800 | EMER - INSTALL 5'-2" PMMP | 1272.31 | 12.71 | 320.35
| 25026409900 | EMER - INSTALL 10'-2" PMMP | 7698.66 | 87.45 | 1962.06
| 25026410100 | EMER - INSTALL 200' - 2" | 503.2 | 0 | 0
| 25026410400 | EMER - INSTALL 10'-2" PMMP | 1769.76 | 129.83 | 537.17
| 25026410600 | EMER-INSTALL 3'-2"PMMP MAIN | 59.2 | 0 | 0
| 25026410800 | EMER - INSTALL 2'-2" PMMP | 1368.06 | 98.89 | 406.14
559 | 19026867802 | INSTALL 376'-4" PMIP | 205355.06 | 3543.4 | 53752.93
| 24026341000 | INSTALL 300'OF 2" PMIP | 39782.89 | 957.46 | 15881.5
| 24026348200 | INSTALL ~30'-4" PMMP | 13263.85 | 30.19 | 3586.59
| 24026349300 | INSTALL 4"POLY VALVE KY-C1556 | 16870.94 | 42.51 | 5430.04
| 24026368800 | INSTALL 5' OF 6" PMLP (PIF) | 36887.29 | 370.64 | 16666.57
| 25026377600 | EMER-INSTALL 4' OF 2"PMMP MAIN | 6438.29 | 26.83 | 2534.36
| 25026377900 | INSTALL LP FITTING-PAPER ONLY | 0 | 0 | 0
| 25026400200 | INSTALL 550'-2" PMMP | 36994.76 | 77.64 | 10435.6
| 25026409300 | PAPER ONLY LP STOPPLE FITTINGS | 4975.29 | 0 | 1294.61
| 25026411700 | INSTALL SHORTSTOP TEE | 0 | 0 | 0
561 | 23026287300 | INSTALL 121'-4" CSMP | 142112.97 | 1571.06 | 44648.6
| 23026301200 | INSTALL 60' OF 6"PMMP MAIN | 29242.3 | 0 | 14636.92
| 24026345800 | INSTALL 1400'-2" PMIP | 189767.51 | 1240.7 | 72548.81
| 24026348900 | INSTALL 70'-8" PMMP | 87138.7 | 1694.2 | 21556.79
| 24026357400 | INSTALL 275'-3" CSMP | 80097.7 | 301.74 | 24073.31
| 24026358600 | INSTALL 175' - 4" PMMP | 70812.59 | 109.77 | 19486.98
| 24026358801 | INSTALL 4200' OF 2"/4"PMMP | 583233.81 | 1821.46 | 197212.37
| 24026360500 | INSTALL 18'-2" PMMP | 8452.23 | 22.57 | 2153.05
| 24026360700 | INSTALL 230' OF 4"PMLP MAIN | 13636.19 | 311.04 | 5558.7
| 24026361300 | INSTALL 750'-2" PMMP | 139929.95 | 828.59 | 65356.1
| 24026370600 | INSTALL 32'-6" PMLP | 8445.36 | 122.98 | -250.5
| 24026376901 | INSTALL 1218'-6" PMMP | 483743.85 | 5885.76 | 217464.91
| 25026378600 | INSTALL 42' OF 2"/4" PMMP MAIN | 21685.28 | 112.68 | 4213.06
575 | 18026779401 | ACQ 25X25 SITE FOR NEW R-1133 | 15053.61 | 1067.71 | 0
| 21026123000 | INVESTIGATE/AQUIRE EASEMENT | 10517.58 | 469.26 | 0
| 24026312500 | ACQUIRE EASEMENT FOR RELOCATE | 500 | 15.95 | 0
| 24026340500 | ACQUIRE EASEMENT | 43765.62 | 2154.49 | 0
| 24026341800 | LAND PAYMENT FOR REG SITE EASE | 500 | 15.96 | 0
| 24026349200 | ACQUIRE EASEMENT | 1800 | 0.46 | 0
| 24026370500 | ACQUIRE LAND RIGHTS | 20000 | 657.58 | 0
| 25026399900 | OBTAIN EASEMENTS | 7794.7 | 23.36 | 0
583 | 23026286900 | HIGHLAND HEIGHTS BREAK METER | 28069.08 | 1202.35 | 10943.29
| 23026306800 | INSTALL METER RUN | 34905.76 | 793.66 | 11351.04
| 23026308100 | INSTALL NEW METER | 5834.1 | 3.36 | 1562.62
| 23026258300 | INSTALL VRG CONTROLLER | 33603.65 | 1508.41 | 6493.01
| 25026396000 | INSTALL CAT HEATER | 0 | 0 | 0
| 25026403300 | INSTALL MONITOR REGULATOR | 1488.58 | 5.71 | 415.31
587 | 24026336600 | INSTALL GMB SETTING | 18363.65 | 82.87 | 4609.82
| 24026312301 | INSTALL NEW GMB SETTING | 177429.22 | 2794.29 | 50321.18
| 24026363800 | INSTALL EC-350 UNIT | 4838.64 | 4.37 | 1049.19
| 24026367700 | INSTALL NEW EC-350 UNIT | 540.17 | 2.04 | 164.6
Grand Total |  |  | 22213879.89 | 347177 | 7186782.18

## Cognos Data (hidden)
Job Orders with Account Class and Actual Costs
cognos.nisource.net:// NGD>>Reports>>Job Orders | [27 empty] | Report Run: May 23, 2024 8:18:00 AM
Date Type: Jo Create Date | [27 empty] | **Nisource Confidential - For Internal Use Only
Date Range: Jan 1, 2018 Thru May 23, 2024 | [27 empty] | For questions, contact Business Intelligence at birepreq@nisource.com
Job Type: 555 - MAINS-NEW BUSINESS, 557 - MAINS-LEAKAGE ELIMINATION, 559 - MAINS-SERVICE IMPROVEMENT, 561 - MAINS-STREET IMPROVEMENT, 563 - SERVICE LINE - NEW, 565 - SERVICE LINE - REPLACE, 573 - PLANT REGULATORS - NEW, 575 - REGULATOR SITES, 577 - REGULATOR STRUCTURES - NEW, 583 - PLANT REGULATORS - REPL, 585 - REGULATOR STRUCTURES - REPL, 587 - L V EXCESS PRESSURE M&R, 595I - INSULATOR (CAPITAL), 595R - RECTIFIER/GROUND BED (CAPITAL)
Job Status: CO - COMPLETED, OP - OPEN, PE - PENDING, PL - PLANNED
Responsible Supervisor:
State, Ops Center, Work Loc, County: KY
Project Id:
Accounting Project Code:
PSID:
State | Ops Center | Work Loc | Job Order | Cap Flag | PSID | PSID Seq No | Map No | Project Id | Project Engineer | Current RT No | Job Type | Job Status | Job Summary | Resp Suprv | Located At | Address | Cnty Cd | Cty Cd | Stat Dt | Executed By | Entered By | Entered Dt | Priority Dt | Commit Dt | In Out Service Dt | Completed By | Complete Dt | Crew Start Dt | Actual Start Dt | Instl Cd | Bus Unit | Account | Home Dp | Chrg Dp | Affil | Activ | Project | Cst Elem Cd | Cost Obj Cd | Fclty cd | Proj Cd | Chrg Jo No | Chrg Pc | Nifit Work Order | Hours | Units | Total Actual Cost | Actual Labor Cost | Actual Mtl Cost | Actual Oth Cost | Actual Contr Cost | Actual Store Cost | Actual AFUDC Cost | Actual SEGA Cost | Footage
KY | KY - EAST | 2633 | 04578193200 |  | 500194875 | 14 | 7384168F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | TURKEY CREEK | TURKEY CREEK RD | 195 | S W | 2024-09-05 | U129900 | CESTEP | 2004-06-17 | 2022-07-01 | 2024-12-31 |  | U129900 | 2024-09-05 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.18333 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 05614429800 |  | 100468185 | 23 | 17344176 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PAINTSVILLE DP | PAINTSVILLE DP | 115 | VAN | 2024-09-05 | U129900 | BFMULLI | 2005-06-17 | 2024-12-31 | 2024-12-31 |  | U129900 | 2024-09-05 | 2022-11-17 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.18333 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 12989275500 |  | 100264697 |  | 7384168F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | TURKEY CREEK | TURKEY CREEK RD | 195 | S W | 2024-09-05 | U129900 | U908784 | 2012-09-24 | 2022-07-01 | 2024-12-31 |  | U129900 | 2024-09-05 | 2023-12-06 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 20.9833 | 5 | 5279.03 | 1839.86 | 0 | 240.89 | 3198.28 | 0 | 0 | 0
KY | KY - EAST | 2631 | 13122305300 |  | 100260025 |  | 7356256B |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | LEXINGTON | 2124 LEXINGTON AV | 019 | ASH | 2025-04-14 | U124604 | U124965 | 2013-03-05 | 2013-12-23 |  |  | MCOLLET | 2025-04-11 | 2024-08-14 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 57.8833 | 13 | 7808.79 | 3666.42 | 252.27 | 3752.46 | 137.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18026779401 |  |  |  | 6716216P | 1425507 | U461383 |  | 575 | CO | ACQ 25X25 SITE FOR NEW R-1133 | 2600E | NEW CIRCLE KDOT ESMT | 763 W NEW CIRCLE KDOT ESMT RD | 067 | LEX | 2025-06-17 |  | U461383 | 2024-01-08 | 2023-12-28 | 2023-12-31 | 2025-06-17 | LAND SERVICE | 2025-06-17 | 2020-12-17 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00575 | 3207513 |  |  | WP7794 |  |  | 100 | 751332180267794 |  | 1 | 16121.32 | 226.4 | 0 | 13.93 | 14813.28 | 0 | 1067.71 | 0
KY | KY - EAST | 2631 | 18026794401 |  |  |  | 7356216D | 1855491 | U132703 |  | 557 | CO | INSTALL 4400'-2"/4"PMMP MAIN | 2600B | SULLIVAN | SULLIVAN ST | 127 | LOU | 2025-05-27 |  | U132703 | 2025-03-04 | 2025-06-30 | 2025-12-31 | 2024-11-07 | MBLANKE/CJH C PACK | 2025-05-27 | 2024-10-17 | 2024-10-22 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP7944 | AMRCB |  | 100 | 055732180267944 | 1012.55 | 297472 | 1250897.35 | 79735.63 | 11429.49 | 110151.8 | 709774.01 | 0 | 1850.82 | 337955.6 | 2324
KY | KY - EAST | 2631 | 18026794500 |  |  |  | 7356216D | 1855491 | U132703 |  | 558 | CO | RETIRE 2450' - CS/BSMP | 2600B | SULLIVAN | SULLIVAN ST | 127 | LOU | 2025-05-27 |  | U127466 | 2018-09-12 | 2025-12-31 | 2025-12-31 | 2024-11-07 | MBLANKE/CJH C PACK | 2025-05-27 | 2025-04-29 | 2024-10-22 | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP7945 | AMRCB |  | 100 | 055832180267945 | 7.4167 | 0 | 589.7 | 505.47 | 0 | 84.23 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18026795501 |  |  |  | 6736248A | 1855582 | U128885 |  | 557 | EX | INSTALL 14,600'-2,4,6,8" PMMP | 2600B | MOY FOO | MOY FOO AL | 097 | CYN | 2025-03-07 | U128132 | U128885 | 2024-10-30 | 2022-11-28 | 2024-11-08 | 2024-10-15 | JPASLEY | 2024-11-15 | 2024-01-05 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP7955 | AMRCB |  | 100 | 055732180267955 | 1501.8167 | 2705912 | 3426043.78 | 106926.76 | 96759.65 | 32402.07 | 2314415.69 | 0 | 80451.23 | 795088.38 | 13948
KY | KY - CENTRAL | 2629 | 18026795600 |  |  |  | 6736248A | 1855582 | U128885 |  | 558 | EX | RETIRE 714' - 6" BSMP | 2600B | MOY FOO | MOY FOO AL | 097 | CYN | 2025-01-03 | U128132 | U128885 | 2018-09-14 | 2024-03-28 | 2024-11-08 | 2024-09-06 | JPASLEY | 2024-11-15 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP7956 | AMRCB |  | 100 | 055832180267956 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19026867802 |  |  |  | 7364188G | 1962537 | U122858 |  | 559 | CO | INSTALL 376'-4" PMIP | 2600E | SR 40 | SR 40 | 159 | INE | 2025-05-19 |  | U122858 | 2024-05-02 | 2025-09-11 | 2025-09-30 | 2025-05-06 | BRANDON ROBERTS | 2025-05-16 | 2025-04-07 | 2025-04-07 | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00559 | 3200559 |  |  | WP8678 |  |  | 100 | 055932190268678 | 233.9833 | 9800 | 262651.39 | 15540.81 | 6354.85 | 14531.31 | 168928.09 | 0 | 3543.4 | 53752.93 | 350
KY | KY - EAST | 2633 | 19026867900 |  |  |  | 7364188G | 1962537 | U122858 |  | 560 | EX | RETIRE 396'-3" P&CS | 2600B | SR 40 | SR 40 | 159 | INE | 2025-06-07 | U128132 | U122858 | 2019-03-23 | 2025-09-30 | 2025-09-30 | 2025-05-06 | BRANDON ROBERTS | 2025-05-16 |  | 2025-04-07 | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00560 | 3200560 |  |  | WP8679 |  |  | 100 | 056032190268679 | 0.31667 | 0 | 48.51 | 23.43 | 0 | 25.08 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 20026983300 |  |  |  | 7356256A | 2075304 | U132280 |  | 557 | EX | INSTALL 6,600'-2"/4" PMMP | 2600B | CHESTNUT | CHESTNUT DR | 019 | ASH | 2025-02-13 | U128132 | U461492 | 2020-10-20 | 2024-03-01 | 2024-12-31 | 2024-09-17 | ORA SLONE | 2024-12-19 | 2024-04-30 | 2024-04-29 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP9833 | AMRCB |  | 100 | 055732200269833 | 1272.4 | 1231560 | 2015230.05 | 88325.98 | 62953.6 | 28160.7 | 1354878.82 | 0 | 11630.26 | 469280.69 | 6220
KY | KY - EAST | 2631 | 20026983400 |  |  |  | 7356256A | 2075304 | U132280 |  | 558 | EX | RETIRE 5374'-4" BSLP/CSLP | 2600B | CHESTNUT | CHESTNUT | 019 | ASH | 2025-02-07 | U128132 | U461492 | 2020-10-20 | 2023-12-29 | 2024-12-31 | 2024-12-12 | ORA SLONE | 2024-12-19 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP9834 | AMRCB |  | 100 | 055832200269834 |  | 0 | 92.88 | 0 | 0 | 0 | 92.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21026123000 |  |  |  | 6688228C |  | U126783 |  | 575 | EX | INVESTIGATE/AQUIRE EASEMENT | 2600E | LAKEVIEW | LAKEVIEW PK | 073 | FRA | 2024-12-04 | U128132 | U130604 | 2021-05-12 | 2021-12-21 | 2021-12-21 | 2024-10-29 | LAND SERVICES | 2024-10-29 |  |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00575 | 3200575 |  |  | WP1230 |  |  | 100 | 057532210261230 |  | 1 | 10986.84 | 0 | 0 | 0 | 10517.58 | 0 | 469.26 | 0
KY | KY - WEST | 2621 | 21026152101 |  |  |  | 6716212N | 2075431 | U461383 |  | 557 | EX | INSTALL 535' OF 8"CSHP MAIN | 2600B | ADDISON | 629 ADDISON AV | 067 | LEX | 2024-12-05 | U132645 | U461383 | 2024-08-26 | 2025-12-02 | 2025-12-31 | 2024-10-29 | DDAVIS | 2024-10-31 | 2024-09-20 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP1521 | AMRCB |  | 100 | 055732210261521 | 356.9833 | 23268 | 480960.85 | 26006.06 | 62699.05 | 23775.4 | 252773.35 | 0 | 4902.8 | 110804.19 | 554
KY | KY - WEST | 2621 | 21026152200 |  |  |  | 6716212N | 2075431 | U461383 |  | 558 | EX | RETIRE 457' OF 6 5/8"BSHP MAIN | 2600B | ADDISON | 629 ADDISON AV | 067 | LEX | 2024-12-04 | U132645 | U461383 | 2021-11-23 | 2025-12-31 | 2025-12-31 | 2024-10-29 | DUSTIN DAVIS | 2024-10-31 | 2024-10-29 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP1522 | AMRCB |  | 100 | 055832210261522 | 13.9833 | 0 | 1859.99 | 943.68 | 0 | 696.31 | 220 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026161800 |  |  |  | 6736248A | 1855582 | U128885 |  | 557 | EX | INSTALL 8" PCF | 2600B | MOY FOO | MOY FOO AL | 097 | CYN | 2025-01-03 | U128132 | U128885 | 2022-01-20 | 2024-01-08 | 2024-12-31 | 2024-10-28 | JPASLEY | 2024-11-15 | 2024-07-30 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP1618 | AMRCB |  | 100 | 055732220261618 | 25.6333 | 0 | 29544.9 | 1592.53 | 4801.94 | 529.43 | 20548.32 | 0 | 26.6 | 2046.08
KY | KY - CENTRAL | 2629 | 22026161900 |  |  |  | 6736248A | 1855582 | U128885 |  | 558 | EX | RETIRE LP MAIN - LEAKAGE | 2600B | MOY FOO | MOY FOO AL | 097 | CYN | 2024-12-20 | U128132 | U128885 | 2022-01-20 | 2049-12-31 | 2024-12-31 | 2024-10-28 | JPASLEY | 2024-11-15 | 2024-10-28 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP1619 | AMRCB |  | 100 | 055832220261619 | 13 | 0 | 1465.95 | 821.85 | 0 | 644.1 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026165501 |  |  |  | 6716208G | 2286440 | U134275 |  | 557 | EX | INSTALL 3385' OF 2" PMMP | 2600B | CHEROKEE | CHEROKEE PK | 067 | LEX | 2024-10-17 | U128132 | U134275 | 2024-09-12 | 2024-01-22 | 2024-12-31 | 2024-06-19 | JPASLEY | 2024-09-13 | 2024-05-17 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP1655 | AMRCB |  | 100 | 055732220261655 | 119.6333 | 56712 | 347952.13 | 7525.87 | 8204.75 | 4302.81 | 249702.15 | 0 | 1645.51 | 76571.04 | 3336
KY | KY - WEST | 2621 | 22026165600 |  |  |  | 6716208G | 2286440 | U134275 |  | 558 | EX | RETIRE 2715'-BSLP & 425'-PLP | 2600B | CHEROKEE | CHEROKEE PK | 067 | LEX | 2024-10-16 | U128132 | U134275 | 2022-02-10 | 2024-12-31 | 2024-12-31 | 2024-08-12 | JPASLEY | 2024-09-13 | 2024-08-08 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP1656 | AMRCB |  | 100 | 055832220261656 | 13.0167 | 0 | 1766 | 946.34 | 0 | 819.66 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026178300 |  |  |  | 6712228L | 2287686 | U461383 |  | 557 | CO | EMER-INSTALL 5'OF 2"PMMP MAIN | 2621P | RUTH MILLER | RUTH MILLER | 209 | GEO | 2025-05-20 |  | U461383 | 2022-03-24 | 2022-11-30 |  |  | SLBARKER | 2025-05-20 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP1783 |  |  | 100 | 055732220261783 |  | 0 | 2814.42 | 1228.94 | 149.13 | 832.63 | 112.48 | 0 | 94.82 | 396.42
KY | KY - WEST | 2623 | 22026178400 |  |  |  | 6712228L | 2287686 | U461383 |  | 558 | CO | EMER-RETIRE 5' OF 2"PMMP MAIN | 2621P | RUTH MILLER | RUTH MILLER | 209 | GEO | 2025-05-20 |  | U461383 | 2022-03-24 | 2022-11-30 |  |  | SLBARKER | 2025-05-20 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP1784 |  |  | 100 | 055832220261784 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22026207100 |  |  |  | 7352256H | 2289651 | U938437 |  | 557 | EX | INSTALL 7870'-2", 4" PMMP | 2600B | VIRGINIA | VIRGINIA | 019 | ASH | 2025-05-02 | U128132 | U132280 | 2022-06-21 | 2024-01-02 | 2025-08-15 | 2024-06-27 | M BLANKENSHIP/CJH C PACK | 2024-10-28 | 2024-01-02 | 2024-01-02 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP2071 | AMRCB |  | 100 | 055732220262071 | 1292.3667 | 1447780 | 1549123.72 | 96735.66 | 44479.86 | 16152.09 | 1001830.71 | 0 | 14496.31 | 375429.09 | 7580
KY | KY - EAST | 2631 | 22026207200 |  |  |  | 7352256H | 2289651 | U938437 |  | 558 | EX | RETIRE 6009'-2",3", 4" LP | 2600B | VIRGINIA | VIRGINIA | 019 | ASH | 2024-12-10 | U128132 | U132280 | 2022-06-21 | 2024-12-31 | 2025-08-15 | 2024-10-15 | M BLANKENSHIP/CJH C PACK | 2024-10-28 | 2024-10-14 | 2024-01-02 | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP2072 | AMRCB |  | 100 | 055832220262072 | 11.7167 | 0 | 873.05 | 805.6 | 0 | 67.45 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026224201 |  |  |  | 6716212P | 2291708 | U461383 |  | 557 | EX | INSTALL 2300' OF 2"/4"PMMP | 2600B | COLUMBIA | 321 COLUMBIA AV | 067 | LEX | 2024-11-01 | U128132 | U461383 | 2024-09-03 | 2024-09-05 | 2024-12-31 | 2024-09-06 | DEREK PAYTON | 2024-09-16 | 2024-09-06 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2242 | AMRCB |  | 100 | 055732220262242 | 626.5 | 180357 | 588766.29 | 42413.78 | 17138.41 | 10968.54 | 382843.68 | 0 | 6363.9 | 129037.98 | 2283
KY | KY - WEST | 2621 | 22026224300 |  |  |  | 6716212P | 2291708 | U461383 |  | 558 | EX | RETIRE 4500' OF 6"/4"BSLP MAIN | 2600E | COLUMBIA | 321 COLUMBIA AV | 067 | LEX | 2024-10-30 | U128132 | U461383 | 2022-09-19 | 2024-12-31 | 2024-12-31 | 2024-09-06 | DEREK PAYTON | 2024-09-23 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2243 | AMRCB |  | 100 | 055832220262243 |  | 0 | 2115.84 | 0 | 0 | 0 | 2115.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026231301 |  |  |  | 6720212M | 2292814 | U461383 |  | 557 | EX | INSTALL 925' OF 2"PMMP MAIN | 2600B | HIGH | 626 E HIGH ST | 067 | LEX | 2024-12-11 | U128132 | U461383 | 2024-11-20 | 2024-11-11 | 2024-12-31 | 2024-09-10 | RANDALL HUMPHREYS | 2024-09-20 | 2024-06-11 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2313 | AMRCB |  | 100 | 055732220262313 | 246.8833 | 30168 | 388671.62 | 15375.78 | 7400.57 | 11263.48 | 263920.31 | 0 | 2049.43 | 88662.05 | 838
KY | KY - WEST | 2621 | 22026231400 |  |  |  | 6720212M | 2292814 | U461383 |  | 558 | EX | RETIRE 975' OF 8"BSLP MAIN | 2600B | HIGH | 626 E HIGH ST | 067 | LEX | 2024-12-10 | U128132 | U461383 | 2022-10-13 | 2024-12-31 | 2024-12-31 | 2024-09-10 | RANDALL HUMPHREYS | 2024-09-20 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2314 | AMRCB |  | 100 | 055832220262314 |  | 0 | 110 | 0 | 0 | 0 | 110 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026236501 |  |  |  | 6716212F | 2293634 | U461383 |  | 557 | CO | INSTALL 1325' OF 4"/8"CSHP MN | 2600B | TRAFTON | TRAFTON ST | 067 | LEX | 2025-05-29 |  | U461383 | 2025-05-19 | 2025-07-17 | 2025-12-31 | 2025-05-28 | DUSTIN DAVIS | 2025-05-29 | 2025-05-22 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2365 | AMRCB |  | 100 | 055732220262365 | 998.9167 | 182952 | 1407086.76 | 79007.59 | 305419.19 | 25651.51 | 574860.04 | 0 | 20338.34 | 401810.09 | 1386
KY | KY - WEST | 2621 | 22026236600 |  |  |  | 6716212F | 2293634 | U461383 |  | 558 | CO | RETIRE 1300'- 6 5/8"BSHP MAIN | 2600B | TRAFTON | TRAFTON ST | 067 | LEX | 2025-05-29 |  | U461383 | 2022-11-14 | 2025-12-31 | 2025-12-31 | 2025-05-28 | DUSTIN DAVIS | 2025-05-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2366 | AMRCB |  | 100 | 055832220262366 |  | 0 | 484.04 | 0 | 0 | 0 | 495 | 0 | 0 | -10.96
KY | KY - WEST | 2623 | 22026236901 |  |  |  | 6712228C | 2293665 | U132703 |  | 557 | EX | INSTALL 11300'-2" PMMP | 2600B | CLAYTON | CLAYTON | 209 | GEO | 2024-12-16 | U128132 | U132703 | 2024-09-10 | 2024-01-15 | 2024-12-31 | 2024-08-28 | WILLIAM GRAVES | 2024-10-21 | 2024-09-24 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP2369 | AMRCB |  | 100 | 055732220262369 | 1828.7833 | 2695585 | 2626590.92 | 120763.05 | 33133.93 | 33406.17 | 1819455.41 | 0 | 34581.37 | 585250.99 | 11185
KY | KY - WEST | 2623 | 22026237000 |  |  |  | 6712228C | 2293665 | U132703 |  | 558 | EX | ABDN~8924'-2",3",4" BS,CS,P LP | 2600B | CLAYTON | CLAYTON | 209 | GEO | 2024-12-12 | U128132 | U132703 | 2022-11-15 | 2024-12-31 | 2024-12-31 | 2024-10-16 | WILLIAM GRAVES | 2024-10-21 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP2370 | AMRCB |  | 100 | 055832220262370 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026237301 |  |  |  | 6748208I | 2293700 | U128885 |  | 557 | EX | INSTALL 11,150'-8"6"4"2" PMMP | 2600B | MUTUAL | MUTUAL AV | 049 | WIN | 2025-02-11 | U128132 | U128885 | 2024-11-01 | 2024-12-18 | 2026-10-21 | 2024-11-09 | WILLIAM FULKS | 2024-12-17 | 2024-11-08 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP2373 | AMRCB |  | 100 | 055732220262373 | 2217.45 | 3304272 | 3177275.55 | 151769.12 | 93208.58 | 36296.53 | 2097723.37 | 0 | 59811.55 | 738466.4 | 11972
KY | KY - CENTRAL | 2629 | 22026237400 |  |  |  | 6748208I | 2293700 | U128885 |  | 558 | EX | RETIRE LP MAIN | 2600B | MUTUAL | MUTUAL AV | 049 | WIN | 2025-02-06 | U128132 | U128885 | 2022-11-16 | 2025-12-31 | 2026-08-08 | 2024-12-12 | WILLIAM FULKS | 2024-12-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP2374 | AMRCB |  | 100 | 055832220262374 |  | 0 | 886.14 | 660.77 | 0 | 115.37 | 110 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026237500 |  |  |  | 6748208I | 2293700 | U128885 |  | 558 | EX | RETIRE MP MAIN | 2600B | MUTUAL | MUTUAL AV | 049 | WIN | 2025-02-06 | U128132 | U128885 | 2022-11-16 | 2024-01-31 | 2024-12-31 | 2024-12-12 | WILLIAM FULKS | 2024-12-17 | 2024-03-13 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP2375 | AMRCB |  | 100 | 055832220262375 | 5.5333 | 0 | 554.6 | 345.51 | 0 | 99.09 | 110 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026238401 |  |  |  | 6700224L | 2293724 | U122858 |  | 557 | EX | INSTALL 5765'-2" PMMP | 2600B | WINTER | WINTER | 239 | MID | 2025-03-06 | U136251 | U122858 | 2023-11-28 |  | 2049-12-31 | 2024-03-20 | OLIVER MAYNARD | 2024-12-03 | 2024-03-19 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP2384 | AMRCB |  | 100 | 055732220262384 | 1384.1833 | 1197228 | 1422160.57 | 92178.27 | 78302.72 | 15549.79 | 899600.15 | 0 | 730.83 | 335798.81 | 6764
KY | KY - WEST | 2623 | 22026238500 |  |  |  | 6700224L | 2293724 | U122858 |  | 558 | EX | RETIRE 7260'-2"-6" BS,CS & P | 2600B | WINTER | WINTER | 239 | MID | 2025-01-29 | U136251 | U122858 | 2022-11-16 |  | 2049-12-31 | 2024-11-12 | OLIVER MAYNARD | 2024-12-03 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP2385 | AMRCB |  | 100 | 055832220262385 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026238600 |  |  |  | 6700224L | 2293724 | U122858 |  | 558 | EX | RETIRE 116'-2"&3" CS&PMP | 2600E |  |  | 239 | MID | 2025-01-29 | U136251 | U122858 | 2022-11-16 | 2024-12-31 | 2024-12-31 | 2024-11-12 | OLIVER MAYNARD | 2024-12-03 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP2386 | AMRCB |  | 100 | 055832220262386 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026239702 |  |  |  | 6720212F | 2293756 | U134275 |  | 557 | CO | INSTALL 8650' - 2,4,6" PMMP | 2600B | CASTLEWOOD | 209 CASTLEWOOD DR | 067 | LEX | 2025-05-02 |  | U134275 | 2024-10-29 | 2024-06-20 | 2025-02-28 | 2025-03-18 | DAVID YOUNG | 2025-05-02 | 2025-02-03 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2397 | AMRCB |  | 100 | 055732220262397 | 2049.6667 | 2164932 | 1934664.05 | 147421.39 | 77147.36 | 13852.04 | 1209934.68 | 0 | 46321.39 | 439987.19 | 8591
KY | KY - WEST | 2621 | 22026239800 |  |  |  | 6720212F | 2293756 | U134275 |  | 558 | CO | RETIRE 6065' - 4/6" BS/CS/PLP | 2600B | CASTLEWOOD | CASTLEWOOD | 067 | LEX | 2025-05-02 |  | U134275 | 2022-11-17 | 2025-02-28 | 2025-02-28 | 2025-04-17 | DAVID YOUNG | 2025-05-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2398 | AMRCB |  | 100 | 055832220262398 |  | 0 | 149.74 | 0 | 0 | 0 | 110 | 0 | 0 | 39.74
KY | KY - EAST | 2631 | 22129068800 |  | 100263347 |  | 7352256H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CHIPPEWA | 810 CHIPPEWA RD | 019 | ASH | 2025-03-06 | U143504 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RECUMP | 2025-03-05 | 2024-04-26 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 23.0167 | 9 | 2198.22 | 1518.71 | 20.28 | 659.23 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129068900 |  | 100261336 |  | 7352256L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ELLIOTT | 1698 ELLIOTT AV | 019 | ASH | 2025-02-04 | MCOLLET | U130722 | 2022-09-05 | 2022-12-30 |  |  | MCOLLET | 2025-02-04 | 2024-05-14 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 10.6167 | 6 | 1637.19 | 892.59 | 20.28 | 724.32 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129070400 |  | 100265924 |  | 7348252D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | STATE RT 716 | 733 STATE RT 716 | 019 | ASH | 2024-11-22 | MCOLLET | U130722 | 2022-09-05 | 2022-12-30 |  |  | MCOLLET | 2024-11-22 | 2024-11-21 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 6.2 | 4 | 1415.35 | 483.52 | 45.57 | 426.26 | 460 | 0 | 0 | 0
KY | KY - EAST | 2682 | 22129076600 |  | 100426595 |  | 7324132F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2633S | GENERAL DELIVE | GENERAL DELIVE | 119 | LEB | 2024-09-04 | U130172 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JOHN HOWARD | 2024-09-03 |  |  | B | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 4.1833 | 2 | 299.94 | 283.76 | 0 | 16.18 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129076900 |  | 100261806 |  | 7332132T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PW4534 | PW4534 | 119 | PIP | 2024-10-15 | U129900 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ASHEPHERD | 2024-10-10 | 2024-08-26 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.2667 | 1 | 245.54 | 233.72 | 0 | 11.82 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22993214600 |  | 100288776 |  | 6720212D | 2285555 |  |  | 565 | EX | AOC FOLLOW UP REPAIRS NEEDED | 2621P | HI CREST | 521 HI CREST DR | 067 | LEX | 2024-10-09 | MCRAIG | AOC SYST | 2022-04-13 | 2024-12-31 |  |  | MCRAIG | 2024-10-09 | 2024-07-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 20.4167 | 5 | 1453.81 | 1267.68 | 278 | -91.87 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23026258300 |  |  |  | 7256276K | 2395599 | U461383 |  | 583 | EX | INSTALL VRG CONTROLLER | 2632M | MAPLE LEAF | MAPLE LEAF RD | 161 | MAY | 2025-06-20 | U133035 | U461383 | 2023-02-14 | 2024-12-23 | 2024-12-31 | 2024-11-18 | JUSTIN HOBBS | 2024-11-18 | 2023-11-02 |  | F | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00583 | 3200583 |  |  | WP2583 |  |  | 100 | 058332230262583 | 115.4833 | 0 | 41605.07 | 8021.92 | 22072.17 | 1531.56 | 1978 | 0 | 1508.41 | 6493.01
KY | KY - CENTRAL | 2632 | 23026258400 |  |  |  | 7256276K | 2395599 | U461383 |  | 584 | EX | RETIRE BRISTOL CONTROL UNIT | 2632M | MAPLE LEAF | MAPLE LEAF RD | 161 | MAY | 2024-12-05 | U133035 | U461383 | 2023-02-14 | 2024-12-31 | 2024-12-31 | 2024-11-18 | JUSTIN HOBBS | 2024-11-18 | 2024-11-15 |  | F | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00584 | 3200584 |  |  | WP2584 |  |  | 100 | 058432230262584 | 8 | 0 | 600.77 | 566.66 | 0 | 34.11 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026270600 |  | 501202041 |  | 6712208M | 2396687 | U134275 |  | 555 | EX | INSTALL 550' OF 2" PMMP | 2600B | MERRIDEW | 3833 MERRIDEW WY | 067 | LEX | 2024-10-04 | U128132 | U134275 | 2023-04-04 | 2024-10-02 | 2024-10-11 | 2024-09-26 | STEVE CANOY | 2024-09-26 | 2024-09-18 | 2024-09-20 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2706 |  |  | 100 | 055532230262706 | 79.6833 | 5300 | 43345.7 | 5273.65 | 821.42 | 5512.35 | 20569.45 | 0 | 112.86 | 11055.97 | 530
KY | KY - WEST | 2623 | 23026276700 |  |  |  | 6700224L | 2293724 | U122858 |  | 584 | EX | RETIRE STATION R-1581 | 2600E | WINTER | 313 N WINTER ST | 239 | MID | 2025-06-19 | U133035 | U122858 | 2023-05-30 | 2024-12-31 | 2024-12-31 | 2024-11-08 | BLONE | 2024-11-08 | 2024-11-08 |  | F | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00584 | 3200584 |  |  | WP2767 | AMRCB |  | 100 | 058432230262767 | 17.4833 | 0 | 1722.38 | 1380.2 | 0 | 342.18 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026276800 |  |  |  | 6700224L | 2293724 | U122858 |  | 586 | EX | RETIRE FENCE | 2600E | WINTER | 313 N WINTER ST | 239 | MID | 2025-06-19 | U133035 | U122858 | 2023-05-30 | 2024-12-31 | 2024-12-31 | 2024-11-08 | BLONE | 2024-11-08 |  |  | F | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00586 | 3200586 |  |  | WP2768 | AMRCB |  | 100 | 058632230262768 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026283101 |  | 501343072 |  | 7356220N | 2398575 | U122858 |  | 555 | CO | INSTALL 780'-2" PMMP | 2600B | FALLS CREEK | 191 FALLS CREEK DR | 127 | LOU | 2025-05-30 |  | U122858 | 2025-02-20 | 2025-05-21 | 2025-05-30 | 2025-05-28 | BRANDON ROBERTS | 2025-05-28 | 2025-05-20 | 2025-05-20 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP2831 |  |  | 100 | 055532230262831 | 41.75 | 3850 | 71782.2 | 2963.64 | 7114.83 | 1037.83 | 44031.25 | 0 | 264.86 | 16369.79 | 770
KY | KY - EAST | 2631 | 23026283600 |  |  |  | 7352256H | 2289651 | U938437 |  | 557 | EX | INSTALL LP FITTINGS | 2600B | VIRGINIA | VIRGINIA AV | 019 | ASH | 2024-12-10 | U128132 | U938437 | 2023-07-10 | 2024-12-31 | 2024-12-31 | 2024-10-15 | CJH C PACK/M BLANKENSHIP | 2024-10-28 | 2024-01-02 | 2024-08-22 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP2836 | AMRCB |  | 100 | 055732230262836 | 2.0167 | 0 | 9658.7 | 133.85 | 3117.52 | 11.46 | 4032.78 | 0 | 79.82 | 2283.27
KY | KY - CENTRAL | 2632 | 23026286900 |  |  |  | 7248280G | 2398644 | U122858 |  | 583 | EX | HIGHLAND HEIGHTS BREAK METER | 2600M | HIGHLAND | 3020 HIGHLAND DR | 161 | MAY | 2024-11-13 | U133035 | U122858 | 2023-08-04 | 2024-12-30 | 2024-12-31 | 2024-09-11 | JUSTIN HOBBS | 2024-09-11 | 2024-08-21 |  | F | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00583 | 3200583 |  |  | WP2869 |  |  | 100 | 058332230262869 | 29.2667 | 0 | 40214.72 | 3838.59 | 18092.9 | 1718.18 | 4419.41 | 0 | 1202.35 | 10943.29
KY | KY - CENTRAL | 2632 | 23026287000 |  |  |  | 7248280G | 2398644 | U122858 |  | 584 | VO | RETIRE BROKEN METER | 2600M | HIGHLAND | 3020 HIGHLAND DR | 161 | MAY | 2024-11-11 |  | U122858 | 2023-08-04 | 2024-12-31 | 2024-12-31 | 2024-09-11 | JUSTIN HOBBS | 2024-09-11 | 2024-09-11 |  | F | [11 empty] | 23026286900 | 100 |  | 11.6833 | 0 | -1075.17 | -795.82 | 0 | -279.35 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23026287300 |  |  |  | 7256276A | 2398923 | U122858 |  | 561 | EX | INSTALL 121'-4" CSMP | 2600B | ALGONQUIN | ALGONQUIN DR E | 161 | MAY | 2025-05-01 | U132645 | U122858 | 2023-08-07 | 2024-03-08 | 2024-12-30 | 2024-09-16 | EDWARD FOX | 2024-09-20 | 2024-08-23 |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00561 | 3200561 |  |  | WP2873 |  |  | 100 | 056132230262873 | 159.5333 | 3948 | 188332.63 | 11340.25 | 36132.73 | 2901.23 | 91738.76 | 0 | 1571.06 | 44648.6 | 188
KY | KY - CENTRAL | 2632 | 23026287400 |  |  |  | 7256276A | 2398923 | U122858 |  | 562 | EX | RETIRE 98'-4" CSMP | 2600B | ALGONQUIN | ALGONQUIN DR E | 161 | MAY | 2024-10-18 | U132645 | U122858 | 2023-08-07 | 2024-12-30 | 2024-12-30 | 2024-09-16 | EDWARD FOX | 2024-09-20 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00562 | 3200562 |  |  | WP2874 |  |  | 100 | 056232230262874 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026300300 |  | 501168502 |  | 7356216C | 2300812 | U122858 |  | 555 | EX | INSTALL 1810'-2" PMMP | 2600B | TOWN HILL | TOWN HILL RD | 127 | LOU | 2025-01-09 | U128132 | U122858 | 2023-10-13 | 2024-08-23 | 2024-09-20 | 2024-11-11 | M BLANKENSHIP/CJH CSAEY PACK | 2024-11-14 | 2024-10-17 | 2024-10-18 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP3003 |  |  | 100 | 055532230263003 | 50.2 | 18546 | 217275.5 | 3804.65 | 4535.42 | 793.92 | 159965.21 | 0 | 0 | 48176.3 | 1686
KY | KY - WEST | 2623 | 23026301200 |  |  |  | 6712232L | 2300854 | U461383 |  | 561 | EX | INSTALL 60' OF 6"PMMP MAIN | 2600B | CONNECTOR | CONNECTOR RD | 209 | GEO | 2025-03-12 | U128132 | U461383 | 2023-10-18 | 2025-03-26 | 2025-04-01 | 2025-03-05 | EDWARD FOX | 2025-03-06 | 2025-02-24 | 2025-02-24 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00561 | 3200561 |  |  | WP3012 |  |  | 100 | 056132230263012 | 42.9667 | 450 | 43879.22 | 3210.07 | 2275.48 | 581.97 | 23174.78 | 0 | 0 | 14636.92 | 75
KY | KY - WEST | 2623 | 23026301300 |  |  |  | 6712232L | 2300854 | U461383 |  | 562 | EX | RETIRE 54' OF 6"PMP MAIN | 2600B | CONNECTOR | CONNECTOR RD | 209 | GEO | 2025-03-11 | U128132 | U461383 | 2023-10-18 | 2025-04-01 | 2025-04-01 | 2025-03-03 | EDWARD FOX | 2025-03-06 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00562 | 3200562 |  |  | WP3013 |  |  | 100 | 056232230263013 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026306800 |  |  |  | 7340268J | 2301165 | U122858 |  | 583 | EX | INSTALL METER RUN | 2631M | ELM | 320 ELM ST | 089 | GRE | 2024-11-13 | U133035 | U122858 | 2023-12-01 | 2024-11-26 | 2024-12-01 | 2024-10-28 | SHANE GIORDANO | 2024-10-28 | 2024-10-28 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00583 | 3200583 |  |  | WP3068 |  |  | 100 | 058332230263068 | 30.6667 | 0 | 47050.46 | 3919.04 | 25219.2 | 1630.91 | 4136.61 | 0 | 793.66 | 11351.04
KY | KY - EAST | 2631 | 23026306900 |  |  |  | 7340268J | 2301165 | U122858 |  | 584 | VO | RETIRE METER RUN | 2631M | ELM | 320 ELM ST | 089 | GRE | 2024-11-11 |  | U122858 | 2023-12-01 | 2024-11-27 | 2024-12-01 | 2024-10-28 | SHANE GIORDANO | 2024-10-28 | 2024-10-28 |  | F | [11 empty] | 23026306800 | 100 |  | 4.9667 | 0 | -488.73 | -354.21 | 0 | -134.52 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026308100 |  |  |  | 7336272G | 2399822 | U134275 |  | 583 | EX | INSTALL NEW METER | 2631M | OLD US 23 | 2149 OLD US 23 | 089 | GRE | 2024-11-14 | U133035 | U134275 | 2023-12-13 | 2024-12-23 | 2024-12-31 | 2024-10-10 | SHNAE GIORDANO | 2024-10-10 | 2024-10-10 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00583 | 3200583 |  |  | WP3081 |  |  | 100 | 058332230263081 | 12.5333 | 8 | 7400.08 | 1723.1 | 3165.98 | 945.02 | 0 | 0 | 3.36 | 1562.62
KY | KY - EAST | 2631 | 23026308200 |  |  |  | 7336272G | 2399822 | U134275 |  | 584 | VO | RETIRE METER | 2631M | OLD US 23 | 2149 OLD US 23 | 089 | GRE | 2024-11-14 |  | U134275 | 2023-12-13 | 2024-12-31 | 2024-12-31 | 2024-10-10 | SHANE GIORDANO | 2024-10-10 | 2024-10-10 |  | F | [11 empty] | 23026308100 | 100 |  | 8.7333 | 0 | -867.54 | -527.83 | 0 | -339.71 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23169670700 |  | 100288735 |  | 6724212E | 2285555 |  |  | 565 | EX | AOC VALVE NOT ACCESSIBLE | 2621P | HI CREST | 675 HI CREST DR | 067 | LEX | 2024-10-10 | MCRAIG | AOC SYST | 2023-02-28 | 2023-03-28 |  |  | MCRAIG | 2024-10-10 | 2024-07-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.6667 | 4 | 1702.52 | 1352.73 | 482.31 | -132.52 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23192546300 |  | 100259015 |  | 7356256A | 1635077 |  |  | 565 | EX | RELOCATE SERVICE LINE | 2631D | MONTGOMERY | 1604 MONTGOMERY AV | 019 | ASH | 2024-09-06 | MCOLLET | AOC SYST | 2023-06-02 | 2023-12-01 | 2024-12-31 |  | MCOLLET | 2024-09-06 | 2024-09-06 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26310031 | 53.5 | 5 | 5786.06 | 3738.66 | 206.43 | 1840.97 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23205513400 |  | 100262282 |  | 7352256H | 2410099 |  |  | 565 | EX | REPLACE SERVICE LINE - D259646 | 2631D | 13TH | 2655 13TH ST | 019 | ASH | 2025-03-31 | ABHATFIE | AOC SYST | 2023-08-01 | 2025-01-16 | 2026-07-31 |  | ABHATFIE | 2025-03-31 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 | KYACA |  | 100 | 056532B26310021 | 20 | 2 | 4737.34 | 1525.61 | 254.42 | 89.4 | 2867.91 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23214030000 |  | 100264356 |  | 7356260M | 2410099 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2631D | 10TH | 516 10TH ST | 019 | ASH | 2025-05-08 | MCOLLET | AOC SYST | 2023-09-11 | 2021-03-11 | 2021-12-31 |  | MCOLLET | 2025-05-08 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26310031 | 23.4333 | 3 | 5094.49 | 1640.27 | 315.1 | 1849.47 | 1289.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23225568300 |  | 100464253 |  | 6720204P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D246498 | 2621P | OAKBROOK | 3408 OAKBROOK DR | 067 | LEX | 2025-04-09 | U123688 | U135005 | 2023-11-13 | 2024-01-31 |  |  | RJCRAWF | 2025-04-08 | 2025-02-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.25 | 4 | 1175.12 | 979.48 | 0 | 59.48 | 136.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23227567300 |  | 100298189 |  | 6716212H | 1855043 |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD/SOII | 2621P | BROADWAY | 144 N BROADWAY ST | 067 | LEX | 2024-11-11 | U141668 | U133234 | 2023-11-28 | 2023-12-12 | 2024-12-31 |  | TROE | 2024-11-08 | 2023-12-08 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 36.3667 | 13 | 6564.57 | 2435.44 | 0 | 146.25 | 3982.88 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23232551000 |  | 100260361 |  | 7352256H | 2289651 |  |  | 565 | EX | RPLC SL/22026207100 | 2600B | CUMBERLAND | 2501 CUMBERLAND AV | 019 | ASH | 2024-09-19 | JKEENER | U125763 | 2023-12-28 | 2024-12-31 |  |  | JKEENER | 2024-09-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 3.5333 | 1 | 2408.87 | 234.91 | 0 | 13.39 | 2160.57 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23232553300 |  | 100260381 |  | 7352256H | 2289651 |  |  | 565 | EX | RPLC SL/22026207100 | 2600B | CUMBERLAND | 2726 CUMBERLAND AV | 019 | ASH | 2024-09-04 | U123965 | U125763 | 2023-12-28 | 2024-12-31 |  |  | CJH JORDAN HIERONIMUS/MBLANKE | 2024-09-03 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2658.23 | 0 | 0 | 0 | 2658.23 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23232553400 |  | 100260390 |  | 7352256G | 2289651 |  |  | 565 | EX | RPLC SL/22026207100 | 2600B | CUMBERLAND | 2805 CUMBERLAND AV | 019 | ASH | 2024-09-06 | U123965 | U125763 | 2023-12-28 | 2024-12-31 |  |  | CJH JORDAN HIERONIMUS | 2024-09-06 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2083.25 | 0 | 0 | 0 | 2083.25 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23232553500 |  | 100260388 |  | 7352256G | 2289651 |  |  | 565 | EX | RPLC SL/22026207100 | 2600B | CUMBERLAND | 2809 CUMBERLAND AV | 019 | ASH | 2024-09-09 | JKEENER | U125763 | 2023-12-28 | 2024-09-09 |  |  | JKEENER | 2024-09-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.28333 | 1 | 3280.66 | 21.37 | 0 | 1.22 | 3258.07 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23232553600 |  | 100260389 |  | 7352256G | 2289651 |  |  | 565 | EX | RPLC SL/22026207100 | 2600B | CUMBERLAND | 2811 CUMBERLAND AV | 019 | ASH | 2024-09-06 | U123965 | U125763 | 2023-12-28 | 2024-12-31 |  |  | CJH MITCHELL DICKESS | 2024-09-06 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3346.82 | 0 | 0 | 0 | 3346.82 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23232553700 |  | 100260385 |  | 7352256G | 2289651 |  |  | 565 | EX | RPLC SL/22026207100 | 2600B | CUMBERLAND | 2816 CUMBERLAND AV | 019 | ASH | 2024-09-20 | JKEENER | U125763 | 2023-12-28 | 2024-12-31 |  |  | JKEENER | 2024-09-20 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 1.2167 | 1 | 4243.84 | 82.1 | 0 | 4.68 | 4157.06 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23232553900 |  | 100260386 |  | 7352256G | 2289651 |  |  | 565 | EX | RPLC SL/22026207100 | 2600B | CUMBERLAND | 2822 CUMBERLAND AV | 019 | ASH | 2024-09-11 | JKEENER | U125763 | 2023-12-28 | 2024-12-31 |  |  | JKEENER | 2024-09-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 8 | 1 | 3233.82 | 533.91 | 0 | 30.46 | 2669.45 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23232554600 |  | 100260332 |  | 7352256H | 2289651 |  |  | 565 | EX | RPLC SL/22026207100 | 2600B | KENTUCKY | 1311 KENTUCKY AV | 019 | ASH | 2024-09-13 | JKEENER | U125763 | 2023-12-28 | 2024-12-31 |  |  | JKEENER | 2024-09-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 1.3667 | 1 | 3013.69 | 93.45 | 0 | 5.33 | 2914.91 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23232557600 |  | 100260402 |  | 7352256H | 2289651 |  |  | 565 | EX | RPLC SL/22026207100 | 2600B | VIRGINIA | 2611 VIRGINIA AV | 019 | ASH | 2024-09-17 | JKEENER | U125763 | 2023-12-28 | 2024-12-31 |  |  | JKEENER | 2024-09-17 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.61667 | 1 | 3351.82 | 42.03 | 0 | 2.41 | 3307.38 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23232557700 |  | 100260401 |  | 7352256H | 2289651 |  |  | 565 | EX | RPLC SL/22026207100 | 2600B | VIRGINIA | 2612 VIRGINIA AV | 019 | ASH | 2024-09-13 | JKEENER | U125763 | 2023-12-28 | 2024-12-31 |  |  | JKEENER | 2024-09-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 1.3333 | 1 | 3061.7 | 88.1 | 0 | 5.03 | 2968.57 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23232557800 |  | 100260400 |  | 7352256H | 2289651 |  |  | 565 | EX | RPLC SL/22026207100 | 2600B | VIRGINIA | 2624 VIRGINIA AV | 019 | ASH | 2024-09-16 | JKEENER | U125763 | 2023-12-28 | 2024-12-31 |  |  | JKEENER | 2024-09-16 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 1.4167 | 1 | 2884.09 | 93.45 | 0 | 5.33 | 2785.31 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23232557900 |  | 100260398 |  | 7352256H | 2289651 |  |  | 565 | EX | RPLC SL/22026207100 | 2600B | VIRGINIA | 2630 VIRGINIA AV | 019 | ASH | 2024-09-17 | JKEENER | U125763 | 2023-12-28 | 2024-12-31 |  |  | JKEENER | 2024-09-17 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0 | 1 | 3591.59 | 0 | 0 | 0 | 3591.59 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23232558000 |  | 100260396 |  | 7352256H | 2289651 |  |  | 565 | EX | RPLC SL/22026207100 | 2600B | VIRGINIA | 2633 VIRGINIA AV | 019 | ASH | 2024-09-10 | JKEENER | U125763 | 2023-12-28 | 2024-12-31 |  |  | JKEENER | 2024-09-10 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 4.0667 | 1 | 2919.88 | 272.29 | 0 | 15.53 | 2632.06 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23232558100 |  | 100260397 |  | 7352256H | 2289651 |  |  | 565 | EX | RPLC SL/22026207100 | 2600B | VIRGINIA | 2634 VIRGINIA AV | 019 | ASH | 2024-09-18 | JKEENER | U125763 | 2023-12-28 | 2024-12-31 |  |  | JKEENER | 2024-09-18 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.31667 | 1 | 3488.46 | 21.37 | 0 | 1.23 | 3465.86 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23232558200 |  | 100260393 |  | 7352256H | 2289651 |  |  | 565 | EX | RPLC SL/22026207100 | 2600B | VIRGINIA | 2638 VIRGINIA AV | 019 | ASH | 2024-09-18 | JKEENER | U125763 | 2023-12-28 | 2024-12-31 |  |  | JKEENER | 2024-09-18 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.3 | 1 | 2768.18 | 21.37 | 0 | 1.23 | 2745.58 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23232558300 |  | 100260395 |  | 7352256H | 2289651 |  |  | 565 | EX | RPLC SL/22026207100 | 2600B | VIRGINIA | 2643 VIRGINIA AV | 019 | ASH | 2024-09-12 | JKEENER | U125763 | 2023-12-28 | 2024-12-31 |  |  | JKEENER | 2024-09-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 2.8833 | 1 | 3863.36 | 193.54 | 0 | 11.05 | 3658.77 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23232558400 |  | 100260392 |  | 7352256H | 2289651 |  |  | 565 | EX | RPLC SL/22026207100 | 2600B | VIRGINIA | 2650 VIRGINIA AV | 019 | ASH | 2024-09-19 | JKEENER | U125763 | 2023-12-28 | 2024-12-31 |  |  | JKEENER | 2024-09-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 4.4667 | 1 | 4475.25 | 298.97 | 0 | 17.04 | 4159.24 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23232558500 |  | 100260394 |  | 7352256H | 2289651 |  |  | 565 | EX | RPLC SL/22026207100 | 2600B | VIRGINIA | 2655 VIRGINIA AV | 019 | ASH | 2024-09-20 | JKEENER | U125763 | 2023-12-28 | 2024-12-31 |  |  | JKEENER | 2024-09-20 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 1.3833 | 1 | 3609.41 | 145.31 | 0 | 14.65 | 3449.45 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23232558600 |  | 100260391 |  | 7352256H | 2289651 |  |  | 565 | EX | RPLC SL/22026207100 | 2600B | VIRGINIA | 2658 VIRGINIA AV | 019 | ASH | 2024-09-05 | U123965 | U125763 | 2023-12-28 | 2024-12-31 |  |  | CJH MITCHELL DICKESS/MBLANKE | 2024-09-04 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2621.74 | 0 | 0 | 0 | 2621.74 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23232559800 |  | 100260380 |  | 7352256H | 2289651 |  |  | 565 | EX | RPLC SL/22026207100 | 2600B | CUMBERLAND | 2722 CUMBERLAND AV | 019 | ASH | 2024-09-04 | U123965 | U125763 | 2023-12-28 | 2024-12-31 |  |  | CJH MITCHELL DICKESS/MBLANKE | 2024-09-03 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2765.77 | 0 | 0 | 0 | 2765.77 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23232559900 |  | 100260382 |  | 7352256H | 2289651 |  |  | 565 | EX | RPLC SL/22026207100 | 2600B | CUMBERLAND | 2800 CUMBERLAND AV | 019 | ASH | 2024-09-05 | U123965 | U125763 | 2023-12-28 | 2024-12-31 |  |  | CJH JORDAN HIERONIMUS/MBLANKE | 2024-09-05 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2649.26 | 0 | 0 | 0 | 2649.26 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23232560000 |  | 100260383 |  | 7352256G | 2289651 |  |  | 565 | EX | RPLC SL/22026207100 | 2600B | CUMBERLAND | 2806 CUMBERLAND AV | 019 | ASH | 2024-09-05 | U123965 | U125763 | 2023-12-28 | 2024-12-31 |  |  | CJH MITCHELL DICKESS/MBLANKE | 2024-09-05 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2666.46 | 0 | 0 | 0 | 2666.46 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23232560600 |  | 100260399 |  | 7352256H | 2289651 |  |  | 565 | EX | RPLC SL/22026207100 | 2600B | VIRGINIA | 2622 VIRGINIA AV | 019 | ASH | 2024-09-16 | JKEENER | U125763 | 2023-12-28 | 2024-12-31 |  |  | JKEENER | 2024-09-16 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 1.65 | 1 | 3511.99 | 110.12 | 0 | 6.28 | 3395.59 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24026312301 |  |  |  | 6700224H | 2289685 | U126783 |  | 587 | EX | INSTALL NEW GMB SETTING | 2600M | LEESTOWN | 158 W LEESTOWN RD | 239 | MID | 2025-06-18 | U133035 | U126783 | 2024-08-12 | 2024-03-08 |  | 2024-07-31 | CHRIS COX | 2024-10-11 | 2024-05-22 |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00587 | 3200587 |  |  | WP3123 |  |  | 100 | 058732240263123 | 143.6 | 264 | 230544.69 | 10150.41 | 127167.63 | 4148.48 | 35962.7 | 0 | 2794.29 | 50321.18
KY | KY - CENTRAL | 2629 | 24026312500 |  |  |  | 6744208J | 2302060 | U128885 |  | 575 | EX | ACQUIRE EASEMENT FOR RELOCATE | 2629M | MARKET | MARKET ST | 049 | WIN | 2025-02-18 | U128132 | U128885 | 2024-01-18 | 2024-03-27 |  | 2025-01-29 | CHRIS DAVIS | 2025-01-29 |  |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00575 | 3200575 |  |  | WP3125 |  |  | 100 | 057532240263125 |  | 1 | 515.95 | 0 | 0 | 500 | 0 | 0 | 15.95 | 0
KY | KY - WEST | 2623 | 24026313000 |  |  |  | 6712232N | 2403101 | U132703 |  | 557 | EX | INSTALL 1570'-2" PMMP | 2600B | JEFFERSON | 124 JEFFERSON | 209 | GEO | 2025-01-29 | U136251 | U132703 | 2024-01-23 | 2025-08-19 | 2025-09-30 | 2024-11-22 | WILLIAM GRAVES | 2024-12-10 | 2024-10-26 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP3130 | AMRCB |  | 100 | 055732240263130 | 308.1167 | 56990 | 502657.55 | 22425.19 | 4319.95 | 5422.84 | 361278.77 | 0 | 826.08 | 108384.72 | 1390
KY | KY - WEST | 2623 | 24026313100 |  |  |  | 6712232N | 2403101 | U132703 |  | 558 | EX | RETIRE~1346 OF BSLP/PLP MAIN | 2600E | JEFFERSON | 124 W JEFFERSON ST | 209 | GEO | 2025-01-29 | U136251 | U132703 | 2024-01-23 |  | 2049-12-31 | 2024-12-09 | WILLIAM GRAVES | 2024-12-10 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP3131 | AMRCB |  | 100 | 055832240263131 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24026314400 |  | 501359277 |  | 6736180C | 2402680 | U128885 |  | 555 | EX | INSTALL 1,200'-4" PMMP | 2600B | ROBERT MARTIN | 1414 ROBERT MARTIN | 151 | RIC | 2025-04-23 | U128132 | U128885 | 2024-01-31 | 2025-03-31 | 2025-04-11 | 2025-04-15 | DEREK PAYTON | 2025-04-15 | 2025-03-17 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP3144 |  |  | 100 | 055532240263144 | 66.1667 | 8976 | 441793.04 | 4881.39 | 10416.67 | 10169.09 | 288824.74 | 0 | 842.19 | 126658.96 | 1122
KY | KY - WEST | 2621 | 24026316701 |  |  |  | 6720208G | 2403558 | U461383 |  | 557 | EX | INSTALL 11245' OF 2"PMMP MAIN | 2600B | SAINT PHILLIP | SAINT PHILLIP DR | 067 | LEX | 2025-06-11 | U132645 | U461383 | 2024-12-05 | 2024-05-28 | 2024-12-31 | 2024-12-12 | RTINCHER | 2024-12-12 | 2024-12-06 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3167 | AMRCB |  | 100 | 055732240263167 | 1444.2333 | 2505036 | 1084887.24 | 100471.58 | 41050.9 | 11958.06 | 657218.01 | 0 | 14886.26 | 259302.43 | 10987
KY | KY - WEST | 2621 | 24026316800 |  |  |  | 6720208G | 2403558 | U461383 |  | 558 | EX | RETIRE 9920' OF 4"/6"BSLP MAIN | 2600B | SAINT PHILLIP | SAINT PHILLIP DR | 067 | LEX | 2025-06-11 | U132645 | U461383 | 2024-02-08 | 2024-12-31 | 2024-12-31 | 2025-04-09 | RTINCHER | 2025-05-21 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP3168 | AMRCB |  | 100 | 055832240263168 |  | 0 | 717.72 | 161.16 | 0 | 116.56 | 440 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026318800 |  |  |  | 7340268E | 2403699 | U134275 |  | 909 | EX | ADD SOLAR BACKUP | 2631M | ELM | 320 ELM ST | 089 | GRE | 2024-09-17 | U133035 | U134275 | 2024-02-13 | 2024-12-31 | 2024-12-31 | 2024-09-16 | SHANE GIORDANO | 2024-09-16 |  |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP3188 |  |  | 100 | 090932240263188 | 9.9667 | 0 | 9847.7 | 713.04 | 0 | 671.15 | 8225 | 0 | 238.51 | 0
KY | KY - EAST | 2631 | 24026318900 |  |  |  | 7340268J | 2403699 | U134275 |  | 910 | EX | RETIRE COMPONENTS | 2631M | ELM | 320 ELM ST | 089 | GRE | 2024-09-17 | U133035 | U134275 | 2024-02-13 | 2024-12-31 | 2024-12-31 | 2024-09-16 | SHANE GIORDANO | 2024-09-16 |  |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00910 | 3200910 |  |  | WP3189 |  |  | 100 | 091032240263189 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026319200 |  |  |  | 7356216C | 2403699 | U134275 |  | 909 | EX | UPGRADE SCADA SYSTEM | 2631M | LACKEY | 515 LACKEY AV RR | 127 | LOU | 2024-09-24 | U133035 | U134275 | 2024-02-13 | 2024-12-31 | 2024-12-31 | 2024-09-17 | DANNY ASH | 2024-09-17 |  |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP3192 |  |  | 100 | 090932240263192 | 13.9833 | 0 | 9821.8 | 929.09 | 0 | 429.27 | 8225 | 0 | 238.44 | 0
KY | KY - EAST | 2631 | 24026319300 |  |  |  | 7356216C | 2403699 | U134275 |  | 910 | EX | RETIRE SCADA COMPONENTS | 2631M | LACKEY | 515 LACKEY AV RR | 127 | LOU | 2024-09-24 | U133035 | U134275 | 2024-02-13 | 2024-12-31 | 2024-12-31 | 2024-09-17 | DANNY ASH | 2024-09-17 |  |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00910 | 3200910 |  |  | WP3193 |  |  | 100 | 091032240263193 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026319400 |  |  |  | 7356252H | 2403699 | U134275 |  | 909 | EX | UPGRADE SCADA SYSTEM | 2631M | CENTER | 1418 CENTER ST RR | 019 | CAT | 2024-09-25 | U133035 | U134275 | 2024-02-13 | 2024-12-31 | 2024-12-31 | 2024-09-18 | DANNY ASH | 2024-09-18 |  |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP3194 |  |  | 100 | 090932240263194 | 15.9667 | 0 | 11260.82 | 1053.14 | 0 | 60.09 | 9905 | 0 | 242.59 | 0
KY | KY - EAST | 2631 | 24026319500 |  |  |  | 7356252H | 2403699 | U134275 |  | 910 | EX | RETIRE SCADA COMPONENTS | 2631M | CENTER | 1418 CENTER ST RR | 019 | CAT | 2024-09-25 | U133035 | U134275 | 2024-02-13 | 2024-12-31 | 2024-12-31 | 2024-09-18 | DANNY ASH | 2024-09-18 |  |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00910 | 3200910 |  |  | WP3195 |  |  | 100 | 091032240263195 |  | 0 | 23092 | 0 | 0 | 0 | 23092 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026319800 |  |  |  | 7356256P | 2403699 | U134275 |  | 909 | EX | UPGRADE SCADA SYSTEM | 2631M | CHESTNUT | 100 CHESTNUT ST | 019 | ASH | 2025-06-11 | U133035 | U134275 | 2024-02-13 | 2024-12-31 | 2024-12-31 | 2024-09-19 | DANNY ASH | 2024-09-19 |  |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP3198 |  |  | 100 | 090932240263198 | 16 | 0 | 7392.38 | 1055.76 | 0 | 60.22 | 6045 | 0 | 231.4 | 0
KY | KY - EAST | 2631 | 24026319900 |  |  |  | 7356256P | 2403699 | U134275 |  | 910 | EX | RETIRE SCADA COMPONENTS | 2631M | CHESTNUT | 100 CHESTNUT ST | 019 | ASH | 2025-06-11 | U133035 | U134275 | 2024-02-13 | 2024-12-31 | 2024-12-31 | 2024-09-19 | DANNY ASH | 2024-09-19 |  |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00910 | 3200910 |  |  | WP3199 |  |  | 100 | 091032240263199 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026320200 |  |  |  | 7356256O | 2403699 | U134275 |  | 909 | EX | UPGRADE SCADA SYSTEM | 2631M | HALBERT | 1108 HALBERT ST RR | 019 | ASH | 2025-04-07 | U133035 | U134275 | 2024-02-13 | 2024-12-31 | 2024-12-31 | 2024-09-23 | ANDREW MCCORMICK | 2024-09-23 | 2024-09-23 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP3202 |  |  | 100 | 090932240263202 | 5.2667 | 0 | 9127.38 | 341.14 | 274.53 | 57.39 | 8225 | 0 | 229.32 | 0
KY | KY - EAST | 2631 | 24026320300 |  |  |  | 7356256O | 2403699 | U134275 |  | 910 | EX | RETIRE SCADA COMPONENTS | 2631M | HALBERT | 1108 HALBERT ST RR | 019 | ASH | 2025-04-07 | U133035 | U134275 | 2024-02-13 | 2024-12-31 | 2024-12-31 | 2024-09-23 | ANDREW MCCORMICK | 2024-09-23 | 2024-09-23 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00910 | 3200910 |  |  | WP3203 |  |  | 100 | 091032240263203 | 11.9333 | 0 | 1185.97 | 765.99 | 0 | 419.98 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24026320400 |  |  |  | 6768172E | 2403699 | U461383 |  | 909 | EX | INSTALL MIWI W/FLOW SWITCH | 2629M | KIRKLAND | KIRKLAND AV | 065 | IRV | 2025-06-20 | U133035 | U461383 | 2024-02-13 | 2024-12-31 | 2024-12-31 | 2024-10-21 | JOSH MARTIN | 2024-10-21 | 2024-10-21 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00909 | 3200909 |  |  | WP3204 |  |  | 100 | 090932240263204 | 36.85 | 0 | 17939.6 | 2666.39 | 0 | 525.14 | 14700 | 0 | 48.07 | 0
KY | KY - EAST | 2631 | 24026322500 |  |  |  | 7348260B | 2403699 | U128885 |  | 909 | EX | INSTALL MIWI W/ SOLAR | 2631M | ENGLAND | 900 ENGLAND LN | 089 | FLA | 2024-11-08 | U133035 | U128885 | 2024-02-19 | 2024-12-31 | 2024-12-31 | 2024-10-17 | ANDREW MCCORMICK | 2024-10-17 | 2024-09-10 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP3225 |  |  | 100 | 090932240263225 | 49.05 | 0 | 18888.98 | 3173.04 | 128.73 | 430.97 | 14710 | 0 | 446.24 | 0
KY | KY - EAST | 2631 | 24026322600 |  |  |  | 7348260B | 2403699 | U128885 |  | 910 | EX | REITRE FACILITIES | 2631M | ENGLAND | 900 ENGLAND LN | 089 | FLA | 2024-11-04 | U133035 | U128885 | 2024-02-19 | 2024-12-31 | 2024-12-31 | 2024-10-17 | ANDREW MCCORMICK | 2024-10-17 |  |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00910 | 3200910 |  |  | WP3226 |  |  | 100 | 091032240263226 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026322700 |  |  |  | 6716208J | 2403699 | U128885 |  | 909 | EX | INSTALL MIWI W/ SOLAR | 2600E | STONE | 375 STONE RD | 067 | LEX | 2025-06-13 | U133035 | U128885 | 2024-02-19 | 2024-12-31 | 2024-12-31 | 2024-11-01 | CHRIS COX | 2024-11-01 | 2024-09-13 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP3227 |  |  | 100 | 090932240263227 | 25.9833 | 0 | 18428.99 | 2073.18 | 0 | 502.52 | 15330 | 0 | 523.29 | 0
KY | KY - WEST | 2621 | 24026322800 |  |  |  | 6716208J | 2403699 | U128885 |  | 910 | EX | RETIRE FACILITIES | 2600E | STONE | 375 STONE RD | 067 | LEX | 2025-04-15 | U133035 | U128885 | 2024-02-19 | 2024-12-31 | 2024-12-31 | 2024-11-01 | CHRIS COX | 2024-11-01 | 2024-11-01 |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00910 | 3200910 |  |  | WP3228 |  |  | 100 | 091032240263228 | 3.1667 | 0 | 339.76 | 233.02 | 0 | 106.74 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24026322900 |  |  |  | 6688228O | 2403699 | U128885 |  | 909 | EX | INSTALL MIWI W/ SOLAR | 2600E | MOCKINGBIRD | MOCKINGBIRD LN | 073 | FRA | 2025-06-20 | U133035 | U128885 | 2024-02-19 | 2024-12-31 | 2024-12-31 | 2024-11-13 | GREG HALE | 2024-11-13 | 2024-11-13 |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00909 | 3200909 |  |  | WP3229 |  |  | 100 | 090932240263229 | 29.8333 | 0 | 16866.28 | 2322.07 | 0 | 782.41 | 13486.26 | 0 | 275.54 | 0
KY | KY - WEST | 2623 | 24026323000 |  |  |  | 6688228O | 2403699 | U128885 |  | 910 | EX | RETIRE FACILITIES | 2600E | MOCKINGBIRD | MOCKINGBIRD LN | 073 | FRA | 2025-04-15 | U133035 | U128885 | 2024-02-19 | 2024-12-31 | 2024-12-31 | 2024-11-13 | GREG HALE | 2024-11-13 | 2024-11-11 |  | F | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00910 | 3200910 |  |  | WP3230 |  |  | 100 | 091032240263230 | 8 | 0 | 890.43 | 617.74 | 0 | 272.69 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026323100 |  |  |  | 7356256I | 2403699 | U128885 |  | 909 | CO | UPGRADE TO FULL TIME | 2631M | 29TH | 2254 29TH ST RR | 019 | ASH | 2024-10-01 |  | U128885 | 2024-02-19 | 2024-12-31 | 2024-12-31 | 2024-09-30 | ANDREW MCCORMICK | 2024-09-30 |  |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP3231 |  |  | 100 | 090932240263231 | 3.5333 | 0 | 7625.67 | 205.11 | 0 | 92.5 | 7135 | 0 | 193.06 | 0
KY | KY - EAST | 2631 | 24026323200 |  |  |  | 7356256I | 2403699 | U128885 |  | 910 | EX | RETIRE FACILITIES | 2631M | 29TH | 2254 29TH ST RR | 019 | ASH | 2025-04-15 | U133035 | U128885 | 2024-02-19 | 2024-12-31 | 2024-12-31 | 2024-09-30 | ANDREW MCCORMICK | 2024-09-30 | 2024-09-30 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00910 | 3200910 |  |  | WP3232 |  |  | 100 | 091032240263232 | 7 | 0 | 501.62 | 474.55 | 0 | 27.07 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026323300 |  |  |  | 7356256E | 2403699 | U128885 |  | 909 | CO | UPGRADE TO FULL TIME | 2631M | WOODLAND | 1820 WOODLAND AV | 019 | ASH | 2024-10-08 |  | U128885 | 2024-02-19 | 2024-12-31 | 2024-12-31 | 2024-10-07 | ANDREW MCCORMICK | 2024-10-07 | 2024-10-07 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP3233 |  |  | 100 | 090932240263233 | 4.1 | 0 | 7465.2 | 240.26 | 0 | 108.34 | 6885 | 0 | 231.6 | 0
KY | KY - EAST | 2631 | 24026323400 |  |  |  | 7356256E | 2403699 | U128885 |  | 910 | EX | RETIRE FACILITIES | 2631M | WOODLAND | 1820 WOODLAND AV | 019 | ASH | 2025-04-15 | U133035 | U128885 | 2024-02-19 | 2024-12-31 | 2024-12-31 | 2024-10-07 | ANDREW MCCORMICK | 2024-10-07 | 2024-10-07 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00910 | 3200910 |  |  | WP3234 |  |  | 100 | 091032240263234 | 8.5 | 0 | 722.69 | 498.09 | 0 | 224.6 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026323500 |  |  |  | 7356256A | 2403699 | U128885 |  | 909 | CO | UPGRADE TO FULL TIME | 2631M | PALMER | 1210 PALMER ST | 019 | ASH | 2024-10-09 |  | U128885 | 2024-02-19 | 2024-12-31 | 2024-12-31 | 2024-10-08 | ANDREW MCCORMICK | 2024-10-08 |  |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP3235 |  |  | 100 | 090932240263235 | 3.4333 | 0 | 7331.42 | 202.77 | 0 | 12.43 | 6885 | 0 | 231.22 | 0
KY | KY - EAST | 2631 | 24026323600 |  |  |  | 7356256A | 2403699 | U128885 |  | 910 | EX | RETIRE FACILITIES | 2631M | PALMER | 1210 PALMER ST | 019 | ASH | 2025-04-16 | U133035 | U128885 | 2024-02-19 | 2024-12-31 | 2024-12-31 | 2024-10-08 | ANDREW MCCORMICK | 2024-10-08 | 2024-10-08 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00910 | 3200910 |  |  | WP3236 |  |  | 100 | 091032240263236 | 8.4667 | 0 | 717.61 | 494.57 | 0 | 223.04 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026323700 |  |  |  | 7356256I | 2403699 | U128885 |  | 909 | CO | UPGRADE TO FULL TIME | 2631M | 29TH | 1900 29TH ST RR | 019 | ASH | 2024-10-02 |  | U128885 | 2024-02-19 | 2024-12-31 | 2024-12-31 | 2024-10-01 | ANDREW MCCORMICK | 2024-10-01 | 2024-10-01 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP3237 |  |  | 100 | 090932240263237 | 5.65 | 0 | 7820.77 | 340.04 | 0 | 113.09 | 7135 | 0 | 232.64 | 0
KY | KY - EAST | 2631 | 24026323800 |  |  |  | 7356256I | 2403699 | U128885 |  | 910 | EX | RETIRE FACILITIES | 2631M | 29TH | 1900 29TH ST RR | 019 | ASH | 2025-04-16 | U133035 | U128885 | 2024-02-19 | 2024-12-31 | 2024-12-31 | 2024-10-01 | ANDREW MCCORMICK | 2024-10-01 | 2024-10-01 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00910 | 3200910 |  |  | WP3238 |  |  | 100 | 091032240263238 | 8.8 | 0 | 748.22 | 515.67 | 0 | 232.55 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026324100 |  | 100253182 |  | 7352256G | 2403829 | U122858 |  | 555 | EX | INSTALL 670'-2' PMIP | 2621P | OLYMPIC | 137 OLYMPIC DR | 019 | ASH | 2025-03-07 | U128132 | U122858 | 2024-02-19 | 2024-08-15 | 2024-10-10 | 2024-08-01 | MCOLLET | 2024-11-14 | 2024-07-12 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP3241 |  |  | 100 | 055532240263241 | 175.7333 | 19712 | 91180.5 | 12191.3 | 385.18 | 10579.19 | 47184.54 | 0 | 65.98 | 20774.31 | 704
KY | KY - WEST | 2621 | 24026324600 |  |  |  | 6716212N | 2403699 | U132703 |  | 909 | EX | UPGRADE TO FULL TIME | 2621M | HARRODSBURG | 1590 HARRODSBURG RD | 067 | LEX | 2024-09-11 | U133035 | U132703 | 2024-02-19 | 2024-12-31 | 2024-12-31 | 2024-09-03 | ERIC BLANTON | 2024-09-03 | 2024-07-10 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP3246 |  |  | 100 | 090932240263246 | 4.1 | 0 | 8507.07 | 280.67 | 0 | 253.62 | 7725 | 0 | 247.78 | 0
KY | KY - WEST | 2621 | 24026324700 |  |  |  | 6716212N | 2403699 | U132703 |  | 910 | EX | UPGRADE TO FULL TIME | 2621M | HARRODSBURG | 1590 HARRODSBURG RD | 067 | LEX | 2024-09-11 | U133035 | U132703 | 2024-02-19 | 2024-12-31 | 2024-12-31 | 2024-09-03 | ERIC BLANTON | 2024-09-03 | 2024-07-31 |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00910 | 3200910 |  |  | WP3247 |  |  | 100 | 091032240263247 | 4.8667 | 0 | 568.65 | 286.1 | 0 | 282.55 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026324800 |  |  |  | 6716208K | 2403699 | U132703 |  | 909 | EX | MIWI WITH SOLAR | 2621M | NICHOLASVILLE | 2108 NICHOLASVILLE RD | 067 | LEX | 2024-11-01 | U133035 | U132703 | 2024-02-19 | 2024-12-31 | 2024-12-31 | 2024-10-22 | CHRIS COX | 2024-10-22 | 2024-10-22 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP3248 |  |  | 100 | 090932240263248 | 2.9667 | 0 | 10379.92 | 205.63 | 0 | 147.33 | 9760 | 0 | 266.96 | 0
KY | KY - WEST | 2621 | 24026324900 |  |  |  | 6716208K | 2403699 | U132703 |  | 910 | EX | RETIRE | 2621M | NICHOLASVILLE | 2108 NICHOLASVILLE RD | 067 | LEX | 2024-10-29 | U133035 | U132703 | 2024-02-19 | 2024-12-31 | 2024-12-31 | 2024-10-22 | CHRIS COX | 2024-10-22 | 2024-10-22 |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00910 | 3200910 |  |  | WP3249 |  |  | 100 | 091032240263249 | 4.4667 | 0 | 532.44 | 310.2 | 0 | 222.24 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24026325000 |  |  |  | 6744204G | 2403699 | U132703 |  | 909 | CO | MIWI WITH SOLAR | 2621M | BOONE | 620 BOONE AV | 049 | WIN | 2024-10-31 |  | U132703 | 2024-02-19 | 2024-12-31 | 2024-12-31 | 2024-10-30 | JAMES PASLEY | 2024-10-30 | 2024-09-16 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00909 | 3200909 |  |  | WP3250 |  |  | 100 | 090932240263250 | 31.15 | 0 | 17266.04 | 2241.44 | 0 | 497.46 | 14090 | 0 | 437.14 | 0
KY | KY - CENTRAL | 2629 | 24026325100 |  |  |  | 6744204G | 2403699 | U132703 |  | 910 | EX | MIWI WITH SOLAR | 2621M | BOONE | 620 BOONE AV | 049 | WIN | 2025-06-20 | U133035 | U132703 | 2024-02-19 | 2024-12-31 | 2024-12-31 | 2024-10-30 | JAMES PASLEY | 2024-10-30 |  |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00910 | 3200910 |  |  | WP3251 |  |  | 100 | 091032240263251 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026325300 |  |  |  | 7356256L | 2403699 | U126783 |  | 909 | EX | UPGRADE SCADA SYSTEM | 2631M | 39TH | 413 39TH ST | 019 | ASH | 2025-06-11 | U133035 | U126783 | 2024-02-20 | 2024-12-31 | 2024-12-31 | 2024-09-24 | DANNY ASH | 2024-09-24 |  |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP3253 |  |  | 100 | 090932240263253 | 8 | 0 | 9037.36 | 551.08 | 0 | 31.43 | 8225 | 0 | 229.85 | 0
KY | KY - EAST | 2631 | 24026325400 |  |  |  | 7356256L | 2403699 | U126783 |  | 910 | EX | UPGRADE SCADA SYSTEM | 2631M | 39TH | 413 39TH ST | 019 | ASH | 2025-06-11 | U133035 | U126783 | 2024-02-20 | 2024-12-31 | 2024-12-31 | 2024-09-24 | DANNY ASH | 2024-09-24 |  |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00910 | 3200910 |  |  | WP3254 |  |  | 100 | 091032240263254 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026325500 |  |  |  | 7352260O | 2403699 | U126783 |  | 909 | EX | UPGRADE SCADA SYSTEM | 2631M | BELLEFONTE | 608 BELLEFONTE RD RR | 019 | ASH | 2024-10-14 | U133035 | U126783 | 2024-02-20 | 2024-12-31 | 2024-12-31 | 2024-10-02 | ANDREW MCCORMICK | 2024-10-02 | 2024-10-02 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP3255 |  |  | 100 | 090932240263255 | 1.8167 | 0 | 7316.43 | 109.93 | 0 | 90.32 | 6885 | 0 | 231.18 | 0
KY | KY - EAST | 2631 | 24026325600 |  |  |  | 7352260O | 2403699 | U126783 |  | 910 | EX | UPGRADE SCADA SYSTEM | 2631M | BELLEFONTE | 608 BELLEFONTE RD RR | 019 | ASH | 2024-10-14 | U133035 | U126783 | 2024-02-20 | 2024-12-31 | 2024-12-31 | 2024-10-02 | ANDREW MCCORMICK | 2024-10-02 | 2024-10-02 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00910 | 3200910 |  |  | WP3256 |  |  | 100 | 091032240263256 | 5.15 | 0 | 563.53 | 309.37 | 0 | 254.16 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24026326000 |  |  |  | 6736252M | 2403699 | U126783 |  | 909 | EX | UPGRADE SCADA SYSTEM | 2600E | CARR | CARR AL | 097 | CYN | 2025-04-16 | U133035 | U126783 | 2024-02-20 | 2024-12-31 | 2024-12-31 | 2024-10-10 | JACOB BRADFORD | 2024-10-10 | 2024-10-01 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00909 | 3200909 |  |  | WP3260 |  |  | 100 | 090932240263260 | 7.1833 | 0 | 9009.11 | 442.95 | 0 | 355.08 | 7975 | 0 | 236.08 | 0
KY | KY - CENTRAL | 2629 | 24026326100 |  |  |  | 6736252M | 2403699 | U126783 |  | 910 | EX | UPGRADE SCADA SYSTEM | 2600E | CARR | CARR AL | 097 | CYN | 2025-04-16 | U133035 | U126783 | 2024-02-20 | 2024-12-31 | 2024-12-31 | 2024-10-10 | JACOB BRADFORD | 2024-10-10 |  |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00910 | 3200910 |  |  | WP3261 |  |  | 100 | 091032240263261 | 4.4333 | 0 | 494.05 | 275.32 | 0 | 218.73 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026326800 |  |  |  | 7352256L | 2403699 | U122858 |  | 909 | CO | INSTALL ELECTRINICS | 2631M | CAMPBELL | 2802 CAMPBELL ST | 019 | ASH | 2024-10-10 |  | U122858 | 2024-02-20 | 2024-12-31 | 2024-12-31 | 2024-10-09 | SHANE GIORDANO | 2024-10-09 | 2024-10-09 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP3268 | SCADA |  | 100 | 090932240263268 | 16 | 0 | 8703.66 | 949.89 | 0 | 423.57 | 7095 | 0 | 235.2 | 0
KY | KY - EAST | 2631 | 24026326900 |  |  |  | 7352256L | 2403699 | U122858 |  | 910 | EX | RETIRE ELECTRONICS | 2631M | CAMPBELL | 2802 CAMPBELL ST | 019 | ASH | 2025-06-20 | U133035 | U122858 | 2024-02-20 | 2024-12-31 | 2024-12-31 | 2024-10-09 | SHANE GIORDANO | 2024-10-09 |  |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00910 | 3200910 |  |  | WP3269 | SCADA |  | 100 | 091032240263269 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026327400 |  |  |  | 7356256G | 2403699 | U122858 |  | 909 | EX | INSTALL ELECTRONICS | 2631M | 33RD | 318 33RD ST | 019 | ASH | 2024-09-25 | U133035 | U122858 | 2024-02-20 | 2024-12-31 | 2024-12-31 | 2024-09-25 | SHANE GIORDANO | 2024-09-25 |  |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP3274 | SCADA |  | 100 | 090932240263274 | 6.0333 | 0 | 9042.76 | 431.25 | 0 | 405.92 | 7975 | 0 | 230.59 | 0
KY | KY - EAST | 2631 | 24026327500 |  |  |  | 7356256G | 2403699 | U122858 |  | 910 | EX | RETIRE ELECTRONICS | 2631M | 33RD | 318 33RD ST | 019 | ASH | 2024-09-25 | U133035 | U122858 | 2024-02-20 | 2024-12-31 | 2024-12-31 | 2024-09-25 | SHANE GIORDANO | 2024-09-25 |  |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00910 | 3200910 |  |  | WP3275 | SCADA |  | 100 | 091032240263275 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026327600 |  |  |  | 7352256K | 2403699 | U122858 |  | 909 | EX | INSTALL ELECTRONICS | 2631M | DOUGLAS | 3441 DOUGLAS ST | 019 | ASH | 2025-04-16 | U133035 | U122858 | 2024-02-20 | 2024-12-31 | 2024-12-31 | 2024-09-26 | ANREW MCCORMICK | 2024-09-26 | 2024-09-26 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP3276 | SCADA |  | 100 | 090932240263276 | 4.5 | 0 | 8257.47 | 287.06 | 0 | 16.37 | 7725 | 0 | 229.04 | 0
KY | KY - EAST | 2631 | 24026327700 |  |  |  | 7352256K | 2403699 | U122858 |  | 910 | EX | RETIRE ELECTRONICS | 2631M | DOUGLAS | 3441 DOUGLAS ST | 019 | ASH | 2025-04-16 | U133035 | U122858 | 2024-02-20 | 2024-12-31 | 2024-12-31 | 2024-09-26 | ANDREW MCCORMICK | 2024-09-26 | 2024-09-26 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00910 | 3200910 |  |  | WP3277 | SCADA |  | 100 | 091032240263277 | 10.3 | 0 | 1025.99 | 665.52 | 0 | 360.47 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026328000 |  |  |  | 7356256F | 2403699 | U122858 |  | 909 | EX | INSTALL ELECTRONICS | 2631M | NEWMAN | 2925 NEWMAN ST RR | 019 | ASH | 2024-10-15 | U133035 | U122858 | 2024-02-20 | 2024-12-31 | 2024-12-31 | 2024-10-03 | ANDREW MCCORMICK | 2024-10-03 | 2024-10-03 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP3280 | SCADA |  | 100 | 090932240263280 | 1.8167 | 0 | 7483.34 | 109.93 | 0 | 6.74 | 7135 | 0 | 231.67 | 0
KY | KY - EAST | 2631 | 24026328100 |  |  |  | 7356256F | 2403699 | U122858 |  | 910 | EX | RETIRE ELECTRONICS | 2631M | NEWMAN | 2925 NEWMAN ST RR | 019 | ASH | 2024-10-15 | U133035 | U122858 | 2024-02-20 | 2024-12-31 | 2024-12-31 | 2024-10-03 | ANDREW MCCORMICK | 2024-10-03 | 2024-10-02 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00910 | 3200910 |  |  | WP3281 | SCADA |  | 100 | 091032240263281 | 3.9667 | 0 | 431.14 | 236.69 | 0 | 194.45 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026333201 |  |  |  | 7356256E | 2404470 | U122858 |  | 557 | EX | EMER - INSTALL 478'-4" PMLP | 2600B | WILSHIRE | 2001 WILSHIRE BLVD | 019 | ASH | 2025-02-27 | U128132 | U122858 | 2025-01-16 | 2025-02-17 | 2025-02-28 | 2025-01-27 | BRANDON ROBERTS | 2025-02-06 | 2025-01-16 | 2025-01-14 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP3332 |  |  | 100 | 055732240263332 | 244.5167 | 17280 | 205447.29 | 16403.38 | 5000.19 | 9213.14 | 110802.43 | 0 | 615.39 | 63412.76 | 540
KY | KY - EAST | 2631 | 24026333301 |  |  |  | 7356256E | 2404470 | U122858 |  | 558 | EX | EMER - RETIRE 477'-4" CSLP | 2600B | WILSHIRE | 2001 WILSHIRE BLVD | 019 | ASH | 2025-02-24 | U128132 | U122858 | 2025-01-16 | 2025-02-28 | 2025-02-28 | 2025-02-05 | BRANDON ROBERTS | 2025-02-06 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP3333 |  |  | 100 | 055832240263333 |  | 0 | 226.51 | 119 | 0 | 107.51 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24026333600 |  | 501028114 |  | 7356152E | 2404396 | U122858 |  | 555 | EX | INSTALL 75'-2" PMIP | 2600B | CHERRY | 111 CHERRY ST | 071 | HAR | 2024-10-11 | U128132 | U122858 | 2024-03-14 | 2024-09-19 | 2024-09-20 | 2024-09-11 | MBLANKE/CJH J HIERONIMUS | 2024-09-12 | 2024-09-09 | 2024-09-09 | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00555 | 3200555 |  |  | WP3336 |  |  | 100 | 055532240263336 | 12.55 | 166 | 28387.83 | 869.61 | 1162.08 | 143.56 | 18824.27 | 0 | 63.22 | 7325.09 | 83
KY | KY - WEST | 2621 | 24026336400 |  | 100427637 |  | 6716208N | 2404653 | U122858 |  | 566 | EX | RETIRE ~71-4" PMMP S/L | 2621P | GOLD RUSH | 223 GOLD RUSH RD | 067 | LEX | 2025-02-04 | U123258 | U122858 | 2024-03-21 | 2024-12-31 | 2025-02-28 | 2024-10-03 | TROE | 2025-01-16 | 2024-09-30 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP3364 |  |  | 100 | 056632240263364 | 38.05 | 7 | 2817.23 | 2589.43 | 0 | 227.8 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026336500 |  | 100427637 |  | 6716208N | 2404653 | U122858 |  | 565 | EX | INSTALL ~75'-4" PMMP S/L | 2621P | GOLD RUSH | 223 GOLD RUSH RD | 067 | LEX | 2025-02-12 | U123258 | U122858 | 2024-03-21 | 2024-12-26 | 2025-02-28 | 2024-10-03 | TROE | 2025-01-16 | 2024-04-26 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP3365 |  |  | 100 | 056532240263365 | 81.1333 | 12 | 26538.42 | 5024.28 | 4735.36 | 429.68 | 10780.72 | 0 | 183.96 | 5384.42
KY | KY - WEST | 2621 | 24026336600 |  |  |  | 6716208N | 2404653 | U122858 |  | 587 | CO | INSTALL GMB SETTING | 2600M | GOLD RUSH | 223 GOLD RUSH RD | 067 | LEX | 2024-11-22 |  | U122858 | 2024-03-21 | 2024-12-30 | 2024-12-31 | 2024-10-16 | CHRIS COX | 2024-10-16 | 2024-10-01 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00587 | 3200587 |  |  | WP3366 |  |  | 100 | 058732240263366 | 68.65 | 0 | 23056.34 | 5033.04 | 11502.47 | 1828.14 | 0 | 0 | 82.87 | 4609.82
KY | KY - WEST | 2621 | 24026336700 |  |  |  | 6716208N | 2404653 | U122858 |  | 588 | EX | RETIRE GMB SETTING | 2600M | GOLD RUSH | 223 GOLD RUSH RD | 067 | LEX | 2025-06-20 | U133035 | U122858 | 2024-03-21 | 2024-12-31 | 2024-12-31 | 2024-10-16 | CHRIS COX | 2024-10-16 |  |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00588 | 3200588 |  |  | WP3367 |  |  | 100 | 058832240263367 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026339000 |  |  |  | 6720212P | 2403699 | U461383 |  | 909 | EX | INSTALL OT NETWORK HARDWARE | 2621M | FORTUNE | 2350 FORTUNE DR | 067 | LEX | 2025-04-30 | U133035 | U461383 | 2024-04-11 | 2024-10-01 | 2024-10-01 | 2024-09-20 | AL PARKS | 2024-09-20 | 2024-04-15 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP3390 |  |  | 100 | 090932240263390 | 48.05 | 0 | 5456.41 | 3142.06 | 0 | 2164.07 | 0 | 0 | 150.28 | 0
KY | KY - WEST | 2621 | 24026339100 |  |  |  | 6720212P | 2403699 | U461383 |  | 910 | EX | RETIRE MODEM WITH IT UPGRADES | 2621M | FORTUNE | 2350 FORTUNE DR | 067 | LEX | 2025-04-30 | U133035 | U461383 | 2024-04-11 | 2025-05-30 | 2025-06-01 | 2024-09-20 | ALPARKS | 2024-09-20 | 2024-04-15 |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00910 | 3200910 |  |  | WP3391 |  |  | 100 | 091032240263391 | 8 | 0 | 563.82 | 530.59 | 0 | 33.23 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026340200 |  | 100425964 |  | 6720212I | 2398970 | U461383 |  | 555 | EX | INSTALL 600' OF 8"PMMP MAIN | 2600B | LIMESTONE | 409 S LIMESTONE ST | 067 | LEX | 2025-03-10 | U132645 | U461383 | 2024-04-18 | 2025-01-08 | 2025-01-31 | 2025-02-25 | WILLIAM FULKS | 2025-02-25 | 2025-01-13 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3402 |  |  | 100 | 055532240263402 | 282.0333 | 22015 | 388585.22 | 20959.13 | 24903.57 | 6407.15 | 200650.72 | 0 | 3.55 | 135661.1 | 629
KY | KY - CENTRAL | 2629 | 24026340500 |  |  |  | 6736208M | 2180865 | U128885 |  | 575 | EX | ACQUIRE EASEMENT | 2629M | COMBS FERRY | COMBS FERRY RD | 049 | WIN | 2025-04-25 | U128132 | U128885 | 2024-04-23 | 2025-12-30 | 2025-12-31 | 2025-04-21 | CDAVIS | 2025-04-21 |  |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00575 | 3200575 |  |  | WP3405 |  |  | 100 | 057532240263405 |  | 1 | 45920.11 | 0 | 0 | 17825 | 25940.62 | 0 | 2154.49 | 0
KY | KY - WEST | 2623 | 24026340800 |  |  |  | 6712232O | 2405445 | U126783 |  | 557 | CO | EMER - INSTALL 15'-2" PMMP | 2621P | HAMILTON | 523 N HAMILTON ST | 209 | GEO | 2024-11-21 |  | U126783 | 2024-04-24 | 2024-04-29 | 2025-03-01 |  | D COLLINS | 2024-11-21 | 2024-11-20 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP3408 |  |  | 100 | 055732240263408 | 4.4833 | 0 | 15710.76 | 5891.24 | 0 | 1354.63 | 4410.9 | 0 | 501.84 | 3552.15
KY | KY - WEST | 2623 | 24026340900 |  |  |  | 6712232O | 2405445 | U126783 |  | 558 | CO | EMER - ABANDON 15'-2" PMP | 2621P | HAMILTON | 523 N HAMILTON ST | 209 | GEO | 2024-11-21 |  | U126783 | 2024-04-24 | 2024-05-01 | 2025-03-01 |  | DCOLLINS | 2024-11-21 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP3409 |  |  | 100 | 055832240263409 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026341000 |  |  |  | 7348260P | 2405531 | U141016 |  | 559 | CO | INSTALL 300'OF 2" PMIP | 2621P | CRANCE | CRANCE CT | 019 | ASH | 2025-06-06 |  | U141016 | 2024-04-29 | 2025-04-24 | 2025-04-30 |  | MCOLLET | 2025-06-06 | 2025-03-23 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00559 | 3200559 |  |  | WP3410 |  |  | 100 | 055932240263410 | 142.9667 | 0 | 56621.85 | 10835.91 | 1231.72 | 5386.14 | 22329.12 | 0 | 957.46 | 15881.5
KY | KY - CENTRAL | 2629 | 24026341800 |  |  |  | 6748208I | 2293700 | U141016 |  | 575 | CO | LAND PAYMENT FOR REG SITE EASE | 2600E | WINN | 37 WINN AV | 049 | WIN | 2025-06-02 |  | U141016 | 2024-05-02 | 2024-05-30 | 2024-05-31 |  | JOSH EMBRY | 2025-06-02 |  |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00575 | 3200575 |  |  | WP3418 |  |  | 100 | 057532240263418 |  | 1 | 515.96 | 0 | 0 | 500 | 0 | 0 | 15.96 | 0
KY | KY - WEST | 2621 | 24026341900 |  | 501365269 |  | 6728212M | 2405655 | U461383 |  | 555 | EX | INSTALL 4250' OF 2"/4"PMMP | 2600B | BLACKFORD | BLACKFORD PY LT1 | 067 | LEX | 2024-09-23 | U128132 | U461383 | 2024-05-02 | 2024-08-26 | 2024-09-30 | 2024-09-06 | DUSTIN DAVIS | 2024-09-06 | 2024-07-25 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3419 |  |  | 100 | 055532240263419 | 232.5 | 140340 | 160153.35 | 16289.63 | 14622.07 | 6430.9 | 85858.52 | 0 | 1554.37 | 35397.86 | 4678
KY | KY - WEST | 2621 | 24026343400 |  |  |  | 6724208G | 2406051 | U461383 |  | 560 | EX | RETIRE 4"POLY VALVE C19-270 | 2621P | PAVILION | 1916 PAVILION WY | 067 | LEX | 2024-12-20 | U136251 | U461383 | 2024-05-20 | 2024-11-01 | 2024-11-01 | 2024-06-06 | ATWILLI | 2024-10-31 | 2024-06-05 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00560 | 3200560 |  |  | WP3434 |  |  | 100 | 056032240263434 | 8.6 | 0 | 796.71 | 509.44 | 0 | 287.27 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24026345800 |  |  |  | 7344148I | 2397807 | U141016 |  | 561 | EX | INSTALL 1400'-2" PMIP | 2600B | COW HOLLOW | COW HOLLOW RD | 071 | DRI | 2025-05-15 | U128132 | U141016 | 2024-06-04 | 2025-03-26 | 2025-04-15 | 2025-03-21 | BRANDON ROBERTS | 2025-04-02 | 2025-01-17 | 2025-02-28 | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00561 | 3200561 |  |  | WP3458 | AMRCB |  | 100 | 056132240263458 | 212.75 | 31512 | 263557.02 | 13963.93 | 5148.73 | 13184.86 | 157469.99 | 0 | 1240.7 | 72548.81 | 1212
KY | KY - EAST | 2633 | 24026345900 |  |  |  | 7344148I | 2397807 | U141016 |  | 562 | EX | RETIRE 1200'-2"/4" PA/BS/CS IP | 2600B | COW HOLLOW | COW HOLLOW RD | 071 | DRI | 2025-04-10 | U128132 | U141016 | 2024-06-04 | 2025-04-15 | 2025-04-15 | 2025-04-01 | BRANDON ROBERTS | 2025-04-02 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00562 | 3200562 |  |  | WP3459 | AMRCB |  | 100 | 056232240263459 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026348200 |  |  |  | 6716208N | 2404653 | U122858 |  | 559 | EX | INSTALL ~30'-4" PMMP | 2621P | GOLD RUSH | 223 GOLD RUSH RD | 067 | LEX | 2025-02-12 | U123258 | U122858 | 2024-06-13 | 2024-12-27 | 2025-02-28 | 2024-10-03 | TROE | 2025-01-16 | 2024-10-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP3482 |  |  | 100 | 055932240263482 | 78.1333 | 470 | 16880.63 | 5035.55 | 1175.03 | 1005.86 | 6047.41 | 0 | 30.19 | 3586.59 | 47
KY | KY - WEST | 2621 | 24026348300 |  |  |  | 6716208N | 2404653 | U122858 |  | 560 | EX | RETIRE ~30'-4" PMMP | 2621P | GOLD RUSH | 223 GOLD RUSH RD | 067 | LEX | 2025-02-11 | U123258 | U122858 | 2024-06-13 | 2024-12-31 | 2025-02-28 | 2024-10-03 | TROE | 2025-01-16 | 2024-10-01 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00560 | 3200560 |  |  | WP3483 |  |  | 100 | 056032240263483 | 65.4833 | 0 | 3460.68 | 4180.75 | 0 | -720.07 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026348900 |  |  |  | 7356256C | 2406689 | U122858 |  | 561 | EX | INSTALL 70'-8" PMMP | 2600B | GREENUP | GREENUP AV | 019 | ASH | 2024-10-29 | U128132 | U122858 | 2024-06-20 | 2024-10-10 | 2024-10-30 | 2024-10-04 | CJH CASEY PACK/M BLANKENSHIP | 2024-10-07 | 2024-07-15 | 2024-07-15 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00561 | 3200561 |  |  | WP3489 |  |  | 100 | 056132240263489 | 110.1833 | 2261 | 110389.69 | 9610.57 | 23925.88 | 3094.99 | 50507.26 | 0 | 1694.2 | 21556.79 | 119
KY | KY - EAST | 2631 | 24026349000 |  |  |  | 7356256C | 2406689 | U122858 |  | 562 | EX | RETIRE 70' OF 10"CSMP MAIN | 2600B | GREENUP | GREENUP AV | 019 | ASH | 2024-10-26 | U128132 | U122858 | 2024-06-20 | 2024-10-30 | 2024-10-30 | 2024-10-04 | CJH C PACK/M BLANKENSHIP | 2024-10-07 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00562 | 3200562 |  |  | WP3490 |  |  | 100 | 056232240263490 |  | 0 | 110 | 0 | 0 | 0 | 110 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24026349200 |  |  |  | 6744204C | 2300572 | U128885 |  | 575 | EX | ACQUIRE EASEMENT | 2629M | COLBY | 616 COLBY RD | 049 | WIN | 2025-04-14 | U128132 | U128885 | 2024-06-24 | 2025-12-30 | 2025-12-31 | 2024-01-29 | CHRIS DAVIS - FISHEL | 2025-01-29 |  |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00575 | 3200575 |  |  | WP3492 | AMRCB |  | 100 | 057532240263492 |  | 1 | 1800.46 | 0 | 0 | 1800 | 0 | 0 | 0.46 | 0
KY | KY - WEST | 2621 | 24026349300 |  |  |  | 6724208J | 2406339 | U461383 |  | 559 | EX | INSTALL 4"POLY VALVE KY-C1556 | 2600B | OLD TODDS | 3005 OLD TODDS RD | 067 | LEX | 2024-10-11 | U128132 | U461383 | 2024-06-27 | 2025-05-28 | 2025-06-01 | 2024-09-26 | JOSHUA COX | 2024-10-02 | 2024-09-23 | 2024-09-23 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP3493 |  |  | 100 | 055932240263493 | 44.1667 | 28 | 22343.49 | 4426.84 | 2284.93 | 1005.99 | 9153.18 | 0 | 42.51 | 5430.04 | 4
KY | KY - WEST | 2621 | 24026349400 |  |  |  | 6724208J | 2406339 | U461383 |  | 560 | EX | RETIRE 10' OF 3"PMP MAIN | 2600B | OLD TODDS | 3005 OLD TODDS RD | 067 | LEX | 2024-10-11 | U128132 | U461383 | 2024-06-27 | 2025-05-30 | 2025-06-01 | 2024-09-26 | JOSHUA COX | 2024-10-02 |  | 2024-09-23 | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00560 | 3200560 |  |  | WP3494 |  |  | 100 | 056032240263494 | 0.31667 | 0 | 21.79 | 20.53 | 0 | 1.26 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026349500 |  |  |  | 7352260J | 2406826 | U122858 |  | 557 | EX | INSTALL 40'-12" CSMP | 2600B | BELLEF PRIN | 213 BELLEF PRIN RD | 019 | ASH | 2025-03-19 | U128132 | U122858 | 2024-06-27 | 2024-08-31 | 2025-04-20 | 2025-03-10 | ORA SLONE | 2025-03-14 | 2025-01-15 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP3495 |  |  | 100 | 055732240263495 | 235.1 | 986 | 237894.26 | 20855.41 | 19784.24 | 9279.19 | 107820.3 | 0 | 3131.06 | 77024.06 | 34
KY | KY - EAST | 2631 | 24026349600 |  |  |  | 7352260J | 2406826 | U122858 |  | 558 | EX | RETIRE ~40'-12" CSHP | 2600B | BELLEF PRIN | 213 BELLEF PRIN RD | 019 | ASH | 2025-03-19 | U128132 | U122858 | 2024-06-27 | 2024-08-31 | 2025-04-20 | 2025-03-10 | ORA SLONE | 2025-03-14 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP3496 |  |  | 100 | 055832240263496 |  | 0 | 220 | 0 | 0 | 0 | 220 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026351200 |  | 501312434 |  | 6712212I | 2407033 | U461383 |  | 555 | EX | INSTALL 150' OF 2"PMIP MAIN | 2600B | WINNERS | 1600 WINNERS CR LT40 | 067 | LEX | 2024-09-23 | U132645 | U461383 | 2024-07-09 | 2024-09-26 | 2024-09-27 | 2024-09-12 | JOSHUA COX | 2024-09-13 | 2024-09-10 | 2024-09-10 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3512 |  |  | 100 | 055532240263512 | 32 | 468 | 14499.2 | 2162.28 | 1054.57 | 123.36 | 7408.03 | 0 | 56.14 | 3694.82 | 117
KY | KY - CENTRAL | 2629 | 24026352000 |  | 501367045 |  | 6744208M | 2407005 | U128885 |  | 555 | EX | INSTALL 700'-2" PMMP | 2600B | BULLION | 550 BULLION BV | 049 | WIN | 2025-02-18 | U136930 | U128885 | 2024-07-12 | 2025-01-24 | 2025-01-30 | 2025-02-10 | JOSH PASLEY | 2025-02-10 | 2025-02-04 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP3520 |  |  | 100 | 055532240263520 | 40.85 | 3580 | 75786.62 | 3812.81 | 2609.35 | 2575.32 | 36140.45 | 0 | 191.85 | 30456.84 | 716
KY | KY - WEST | 2621 | 24026353900 |  |  |  | 6716204B | 2407257 | U461383 |  | 558 | EX | RETIRE 164' OF 4"CSMP MAIN | 2600B | NICHOLASVILLE | 3508 NICHOLASVILLE RD | 067 | LEX | 2024-09-11 | U128132 | U461383 | 2024-07-18 | 2024-10-01 | 2025-04-19 | 2024-08-29 | JOSHUA COX | 2024-09-04 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP3539 |  |  | 100 | 055832240263539 | 4.1333 | 0 | 419.02 | 337.8 | 0 | 81.22 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026354300 |  | 501369434 |  | 6716216F | 2407470 | U461383 |  | 555 | EX | INSTALL 1750' OF 2"PMMP MAIN | 2600B | CRAVAT PASS | CRAVAT PASS LT241 | 067 | LEX | 2024-12-20 | U132645 | U461383 | 2024-07-29 | 2024-11-14 | 2024-12-31 | 2024-11-05 | RANDALL HUMPHREYS | 2024-12-19 | 2024-10-22 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3543 |  |  | 100 | 055532240263543 | 83.1 | 21000 | 49920.61 | 5214.01 | 4245.92 | 3450.34 | 26033.63 | 0 | 397.42 | 10579.29 | 1750
KY | KY - WEST | 2623 | 24026354500 |  | 100425427 |  | 6712228C | 2293665 | U132703 |  | 566 | EX | RETIRE 4" BS-MP SERVICE LINE | 2600B | DUDLEY | 421 DUDLEY AV RR-GMB | 209 | GEO | 2025-03-04 | U136251 | U132703 | 2024-07-31 | 2024-12-31 | 2024-12-31 | 2024-10-02 | WILLIAM GRAVES | 2024-10-17 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP3545 | AMRSL |  | 100 | 056632240263545 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24026354600 |  | 100425427 |  | 6712228C | 2293665 | U132703 |  | 565 | EX | INSTALL 790'-4" PMMP S/L | 2600B | DUDLEY | 421 DUDLEY AV RR-GMB | 209 | GEO | 2025-01-28 | U136251 | U132703 | 2024-07-31 | 2024-12-16 | 2024-12-31 | 2024-10-02 | WILLIAM GRAVES | 2024-10-17 | 2024-09-13 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP3546 | AMRSL |  | 100 | 056532240263546 | 71.9833 | 10 | 73956.17 | 5229.62 | 7612.04 | 1614.97 | 41101.92 | 0 | 579.12 | 17818.5
KY | KY - WEST | 2623 | 24026355200 |  | 501358916 |  | 6684228J | 2407531 | U126783 |  | 555 | EX | INSTALL 150'-4" PMLP | 2600B | WAPPING | 403 WAPPING ST | 073 | FRA | 2025-01-28 | U136251 | U126783 | 2024-08-06 | 2024-12-16 | 2024-12-31 | 2024-12-13 | OLIVER MAYNARD | 2024-12-18 | 2024-12-09 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP3552 |  |  | 100 | 055532240263552 | 94.1833 | 2398 | 57369.63 | 7629.74 | 1097.14 | 616.93 | 37854.34 | 0 | 158.91 | 10012.57 | 218
KY | KY - WEST | 2623 | 24026355300 |  | 501368702 |  | 6712232L | 2407579 | U126783 |  | 555 | EX | INSTALL 250'-2" PMMP | 2600B | FINANCIAL | 101 FINANCIAL WY | 209 | GEO | 2025-01-15 | U136251 | U126783 | 2024-08-06 | 2024-09-23 | 2024-09-30 | 2024-09-18 | DUSTIN DAVIS | 2024-09-18 | 2024-09-10 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP3553 |  |  | 100 | 055532240263553 | 48 | 1074 | 24464.47 | 3234.18 | 1523.85 | 1196.28 | 12075.68 | 0 | 58.25 | 6376.23 | 179
KY | KY - WEST | 2621 | 24026355900 |  | 501369361 |  | 6720204C | 2407692 | U461383 |  | 555 | EX | INSTALL 250' OF 2"PMMP MAIN | 2600B | CARRIAGE | 3216 CARRIAGE LN | 067 | LEX | 2025-05-20 | U132645 | U461383 | 2024-08-07 | 2024-11-18 | 2024-11-21 | 2024-10-17 | RANDALL HUMPHREYS | 2024-10-31 | 2024-10-07 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3559 |  |  | 100 | 055532240263559 | 63 | 2780 | 56306.29 | 3722.72 | 1431.29 | 3106.81 | 36864.25 | 0 | 156.57 | 11024.65 | 278
KY | KY - WEST | 2621 | 24026356000 |  |  |  | 6720212I | 2407694 | U461383 |  | 557 | EX | INSTALL 475' OF 2"PMMP MAIN | 2600B | WILGUS | WILGUS AV | 067 | LEX | 2025-06-04 | U136251 | U461383 | 2024-08-07 | 2025-10-31 | 2025-12-01 | 2025-04-29 | STEVE CANOY | 2025-05-29 | 2024-09-24 | 2025-04-07 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3560 | AMRCB |  | 100 | 055732240263560 | 227.15 | 17784 | 138117.86 | 15062.17 | 3890.16 | 14353.27 | 79748.06 | 0 | 757.69 | 24306.51 | 468
KY | KY - WEST | 2621 | 24026356100 |  |  |  | 6720212I | 2407694 | U461383 |  | 558 | EX | RETIRE 420' OF 2"BSLP MAIN | 2600B | WILGUS | WILGUS AV | 067 | LEX | 2025-06-16 | U136251 | U461383 | 2024-08-07 | 2025-12-01 | 2025-12-01 | 2025-05-19 | EDWARD F GOINS | 2025-05-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP3561 | AMRCB |  | 100 | 055832240263561 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026356200 |  |  |  | 6720200A | 2407712 | U461383 |  | 557 | EX | INSTALL NEW 4" CRITICAL VALVE | 2621P | HARTLAND | 4999 HARTLAND PY | 067 | LEX | 2024-10-24 | U132645 | U461383 | 2024-08-08 | 2024-10-14 | 2026-04-16 | 2024-09-19 | MCRAIG | 2024-09-20 | 2024-09-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3562 |  |  | 100 | 055732240263562 | 10.3833 | 6 | 6237.92 | 1829.07 | 1396.83 | 383.4 | 1096.84 | 0 | 23.41 | 1508.37 | 2
KY | KY - WEST | 2621 | 24026356300 |  |  |  | 6720200A | 2407712 | U461383 |  | 558 | EX | RETIRE 4" POLY VALVE C16-184 | 2621P | HARTLAND | 4999 HARTLAND PY | 067 | LEX | 2024-10-02 | U132645 | U461383 | 2024-08-08 | 2025-08-29 | 2026-04-16 | 2024-09-19 | MCRAIG | 2024-09-20 | 2024-09-18 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP3563 |  |  | 100 | 055832240263563 | 102.85 | 0 | 6591.98 | 6119.2 | 0 | 472.78 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026356500 |  |  |  | 7344264B | 2407759 | U122858 |  | 557 | EX | EMER - INSTALL 2'-2" PMIP | 2621P | MONROE | 802 MONROE ST | 089 | WUR | 2024-09-21 | U128132 | U122858 | 2024-08-12 | 2024-08-29 | 2024-09-01 | 2024-08-07 | CWHEELE | 2024-09-04 | 2024-09-03 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP3565 |  |  | 100 | 055732240263565 | 3.1 | 6 | 4865.71 | 2508.8 | 101.58 | 987.48 | 87.32 | 0 | 12.32 | 1168.21 | 2
KY | KY - EAST | 2631 | 24026356600 |  |  |  | 7344264B | 2407759 | U122858 |  | 558 | EX | EMER - RETIRE 2'-2" PIP | 2621P | MONROE | 802 MONROE ST | 089 | WUR | 2024-09-21 | U128132 | U122858 | 2024-08-12 | 2024-08-30 | 2024-09-01 | 2024-08-07 | CWHEELE | 2024-09-04 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP3566 |  |  | 100 | 055832240263566 | 0.58333 | 0 | 49.73 | 42.67 | 0 | 7.06 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026357000 |  |  |  | 6720208G | 2407867 | U461383 |  | 557 | EX | EMER-INSTALL 50' OF 4"PMLP | 2621P | SAINT ANN | 137 SAINT ANN DR | 067 | LEX | 2024-10-22 | U136251 | U461383 | 2024-08-14 | 2025-11-24 | 2026-07-13 | 2024-09-10 | RJCRAWF | 2024-09-10 | 2024-09-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3570 | AMRCB |  | 100 | 055732240263570 | 46 | 300 | 19570.62 | 6114.31 | 5569 | 881.08 | 2173.43 | 0 | 94.63 | 4738.17 | 50
KY | KY - WEST | 2621 | 24026357100 |  |  |  | 6720208G | 2407867 | U461383 |  | 558 | EX | EMER-RETIRE 50' OF 4"BSLP MAIN | 2621P | SAINT ANN | 137 SAINT ANN DR | 067 | LEX | 2024-10-22 | U136251 | U461383 | 2024-08-14 | 2025-11-26 | 2026-07-13 | 2024-09-10 | RJCRAWF | 2024-09-10 | 2024-09-03 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP3571 | AMRCB |  | 100 | 055832240263571 | 134.75 | 0 | 8645.9 | 8179.41 | 0 | 466.49 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24026357400 |  |  |  | 7260280O | 2407133 | U122858 |  | 561 | EX | INSTALL 275'-3" CSMP | 2600B | RIVER | RIVER DR | 161 | MAY | 2025-01-24 | U128132 | U122858 | 2024-08-15 | 2024-10-17 | 2024-10-30 | 2024-10-21 | EDWARD FOX | 2024-10-24 | 2024-10-04 |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00561 | 3200561 |  |  | WP3574 |  |  | 100 | 056132240263574 | 150.9667 | 5548 | 104472.75 | 10177.67 | 15225.72 | 10919.53 | 43774.78 | 0 | 301.74 | 24073.31 | 292
KY | KY - CENTRAL | 2632 | 24026357500 |  |  |  | 7260280O | 2407133 | U122858 |  | 562 | EX | RETIRE 265'-3" CSMP | 2600B | RIVER | RIVER DR | 161 | MAY | 2024-12-19 | U128132 | U122858 | 2024-08-15 | 2024-10-30 | 2024-10-30 | 2024-10-21 | EDWARD FOX | 2024-10-24 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00562 | 3200562 |  |  | WP3575 |  |  | 100 | 056232240263575 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24026358600 |  |  |  | 6744208P | 2407925 | U128885 |  | 561 | EX | INSTALL 175' - 4" PMMP | 2600B | CHURCH | S CHURCH AL | 049 | WIN | 2025-01-09 | U128132 | U128885 | 2024-08-19 | 2024-10-24 | 2024-12-31 | 2024-11-26 | DUSTIN DAVIS | 2024-12-02 | 2024-11-20 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00561 | 3200561 |  |  | WP3586 |  |  | 100 | 056132240263586 | 94.5 | 2340 | 90409.34 | 7614.31 | 1596.11 | 1459.15 | 60143.02 | 0 | 109.77 | 19486.98 | 195
KY | KY - EAST | 2631 | 24026358700 |  | 501368538 |  | 7328264K | 2407391 | U141016 |  | 555 | CO | INSTALL 100' OF 2" PMMP MLE | 2621P | LIME | 1037 LIME ST | 089 | FLA | 2025-03-14 |  | U141016 | 2024-08-19 | 2024-10-29 | 2024-10-31 | 2024-10-03 | ABHATFIE | 2025-03-14 | 2024-09-20 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP3587 |  |  | 100 | 055532240263587 | 109.2833 | 0 | 24604.17 | 7407.34 | 1248.65 | 1697.88 | 8155.42 | 0 | 115.35 | 5979.53
KY | KY - WEST | 2621 | 24026358801 |  |  |  | 6720208E | 2396748 | U461383 |  | 561 | EX | INSTALL 4200' OF 2"/4"PMMP | 2600B | COOPER | COOPER DR | 067 | LEX | 2025-06-09 | U128132 | U461383 | 2025-03-27 | 2024-09-19 | 2025-06-01 | 2025-04-17 | JOSHUA COX | 2025-05-21 | 2025-04-17 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP3588 | AMRCB |  | 100 | 056132240263588 | 1456.4167 | 678078 | 782267.64 | 105673.31 | 24018.91 | 10651.64 | 442889.95 | 0 | 1821.46 | 197212.37 | 3897
KY | KY - WEST | 2621 | 24026358900 |  |  |  | 6720208E | 2396748 | U461383 |  | 562 | EX | RETIRE 914' OF 4"BSMP MAIN | 2600B | COOPER | COOPER DR | 067 | LEX | 2025-06-09 | U128132 | U461383 | 2024-08-22 | 2025-05-30 | 2025-06-01 | 2025-04-17 | JOSHUA COX | 2025-05-21 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP3589 | AMRCB |  | 100 | 056232240263589 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026359401 |  | 501019595 |  | 7344264L | 2408190 | U141016 |  | 555 | EX | INSTALL 200' OF 4" PMIP | 2600B | FAIRWAY | 1226 FAIRWAY DR LT67 | 089 | FLA | 2025-04-07 | U128132 | U141016 | 2025-02-17 | 2025-02-13 | 2025-02-19 | 2025-02-13 | BRANDON ROBERTS | 2025-02-27 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP3594 |  |  | 100 | 055532240263594 | 39.6333 | 770 | 61986.14 | 2877.18 | 3019.58 | 2459.88 | 30377.28 | 0 | 312.76 | 22939.46 | 154
KY | KY - WEST | 2623 | 24026360200 |  |  |  | 6696212H | 2408530 | U461383 |  | 557 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | 2621P | FRANKFORT | FRANKFORT ST | 239 | VER | 2024-12-23 | U136251 | U461383 | 2024-09-10 | 2024-08-21 | 2024-09-03 | 2024-09-04 | CDESPAIN | 2024-09-04 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP3602 |  |  | 100 | 055732240263602 |  | 3 | 12791.75 | 5941.59 | 62.21 | 706.5 | 2950 | 0 | 26.42 | 3105.03 | 3
KY | KY - WEST | 2623 | 24026360300 |  |  |  | 6696212H | 2408530 | U461383 |  | 558 | EX | EMER-RETIRE 3' OF 2"PAMP MAIN | 2621P | FRANKFORT | FRANKFORT ST | 239 | VER | 2024-12-23 | U136251 | U461383 | 2024-09-10 | 2024-09-03 | 2024-09-03 | 2024-09-04 | CDESPAIN | 2024-09-04 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP3603 |  |  | 100 | 055832240263603 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026360500 |  |  |  | 6716216M | 2395080 | U122858 |  | 561 | EX | INSTALL 18'-2" PMMP | 2621P | FORBES | N FORBES RD | 067 | LEX | 2025-02-04 | U132645 | U122858 | 2024-09-13 | 2024-11-22 | 2024-11-30 | 2024-10-29 | MCRAIG | 2024-10-29 | 2024-10-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP3605 |  |  | 100 | 056132240263605 | 86.8 | 280 | 10627.85 | 4913.98 | 0 | -129.9 | 3668.15 | 0 | 22.57 | 2153.05 | 20
KY | KY - WEST | 2621 | 24026360600 |  |  |  | 6716216M | 2395080 | U122858 |  | 562 | EX | RETIRE 10'-2" PMMP | 2621P | FORBES | N FORBES RD | 067 | LEX | 2025-02-03 | U132645 | U122858 | 2024-09-13 | 2024-11-27 | 2024-11-30 | 2024-10-29 | MCRAIG | 2024-10-29 | 2024-10-14 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP3606 |  |  | 100 | 056232240263606 | 61.4167 | 0 | 2874.37 | 3891.79 | 0 | -1017.42 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026360700 |  |  |  | 6720208E | 2396748 | U461383 |  | 561 | EX | INSTALL 230' OF 4"PMLP MAIN | 2600B | ROMANY | 310 ROMANY RD | 067 | LEX | 2025-06-10 | U128132 | U461383 | 2024-09-13 | 2025-05-30 | 2025-06-01 | 2025-04-29 | JOSHUA COX | 2025-05-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP3607 | AMRCB |  | 100 | 056132240263607 |  | 395 | 19505.93 | 0 | 13597.97 | 0 | 38.22 | 0 | 311.04 | 5558.7 | 395
KY | KY - WEST | 2621 | 24026360800 |  |  |  | 6720208E | 2396748 | U461383 |  | 562 | EX | RETIRE 620' OF 4"BSLP MAIN | 2600B | ROMANY | 310 ROMANY RD | 067 | LEX | 2025-06-10 | U128132 | U461383 | 2024-09-13 | 2025-05-30 | 2025-06-01 | 2025-04-29 | JOSHUA COX | 2025-05-21 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP3608 | AMRCB |  | 100 | 056232240263608 |  | 0 | 110 | 0 | 0 | 0 | 110 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026361300 |  |  |  | 6712208B | 2405283 | U122858 |  | 561 | EX | INSTALL 750'-2" PMMP | 2600B | SAVANNAH | SAVANNAH LN | 067 | LEX | 2025-03-27 | U132645 | U122858 | 2024-09-17 | 2025-03-04 | 2025-03-30 | 2025-03-11 | STEVE CANOY | 2025-03-19 | 2025-02-21 | 2025-02-25 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP3613 |  |  | 100 | 056132240263613 | 106.0333 | 12495 | 206114.64 | 7649.31 | 1991 | 6946.38 | 123343.26 | 0 | 828.59 | 65356.1 | 735
KY | KY - EAST | 2631 | 24026361400 |  | 501368206 |  | 7348264I | 2408664 | U141016 |  | 555 | EX | INSTALL 100' OF 2" PMIP | 2600E | DOYLE | 150 DOYLE LN | 089 | FLA | 2025-04-14 | U128132 | U141016 | 2024-09-17 | 2025-02-12 | 2025-03-26 | 2025-03-31 | ORA SLONE | 2025-03-31 | 2025-03-14 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP3614 |  |  | 100 | 055532240263614 | 29.1 | 680 | 28089.92 | 2028.07 | 1217.13 | 485.7 | 15962.81 | 0 | 79.07 | 8317.14 | 136
KY | KY - CENTRAL | 2629 | 24026361500 |  |  |  | 6744208I | 2408727 | U128885 |  | 557 | EX | EMER - INSTALL 2'-3" PMLP | 2621P | MARKET | MARKET | 049 | WIN | 2024-10-09 | U128132 | U128885 | 2024-09-18 | 2024-09-27 | 2024-09-30 | 2024-09-12 | NRICHIE | 2024-09-27 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3615 |  |  | 100 | 055732240263615 |  | 2 | 4884.17 | 1186.53 | 571.44 | 506.27 | 1467.44 | 0 | 8.61 | 1143.88 | 2
KY | KY - CENTRAL | 2629 | 24026361600 |  |  |  | 6744208J | 2408727 | U128885 |  | 558 | EX | EMER - RETIRE 2'-3" PALP | 2621P | MARKET | MARKET | 049 | WIN | 2024-10-09 | U128132 | U128885 | 2024-09-18 | 2024-09-30 | 2024-09-30 | 2024-09-12 | NRICHIE | 2024-09-27 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP3616 |  |  | 100 | 055832240263616 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24026362000 |  |  |  | 6696212D | 2408757 | U461383 |  | 557 | EX | EMER-INSTALL 3' OF 3"PMMP MAIN | 2621P | CHESTNUT | 211 CHESTNUT LN | 239 | VER | 2025-02-12 | U136251 | U461383 | 2024-09-19 | 2025-10-31 | 2026-06-27 | 2024-09-17 | CDESPAIN | 2024-09-17 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP3620 |  |  | 100 | 055732240263620 |  | 3 | 18283.02 | 6279.54 | 120.86 | 1748.84 | 5298.9 | 0 | 58.57 | 4776.31 | 3
KY | KY - WEST | 2623 | 24026362100 |  |  |  | 6696212D | 2408757 | U461383 |  | 558 | EX | EMER-RETIRE 2' OF 3"PMP/VALVE | 2621P | CHESTNUT | 211 CHESTNUT LN | 239 | VER | 2025-02-11 | U136251 | U461383 | 2024-09-19 | 2025-10-31 | 2026-06-27 | 2024-09-17 | CDESPAIN | 2024-09-17 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP3621 |  |  | 100 | 055832240263621 |  | 0 | 12763.63 | 5823.59 | 0 | 404.77 | 6535.27 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026362600 |  |  |  | 7332288M | 2395710 | U461383 |  | 577 | CO | DOCUMENT RTU BUILDING | 2631M | BIGGS | 624 BIGGS LN | 089 | S S | 2024-09-26 |  | U461383 | 2024-09-25 | 2024-11-27 | 2024-12-01 | 2024-09-26 | DANNY ASH | 2024-09-26 |  |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00577 | 3200577 |  |  | WP3626 |  |  | 100 | 057732240263626 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026363400 |  |  |  | 6716212O | 2291708 | U461383 |  | 560 | EX | PAPER ONLY MP RETIREMENT | 2600B | ROSE | ROSE ST | 067 | LEX | 2024-10-11 | U128132 | U461383 | 2024-09-30 | 2024-12-31 | 2024-12-31 | 2024-09-06 | DEREK PAYTON | 2024-09-23 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00560 | 3200560 |  |  | WP3634 | AMRCB |  | 100 | 056032240263634 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026363600 |  |  |  | 6720212D | 2409175 | U461383 |  | 557 | EX | INSTALL 620' OF 4"PMMP MAIN | 2600B | EASTIN | EASTIN RD | 067 | LEX | 2024-12-05 | U132645 | U461383 | 2024-10-07 | 2024-12-02 | 2024-12-31 | 2024-11-08 | DEREK PAYTON | 2024-11-19 | 2024-10-22 | 2024-10-22 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3636 | AMRCB |  | 100 | 055732240263636 | 329.3167 | 24552 | 275193.6 | 23804.19 | 6476.44 | 2510.56 | 185729.43 | 0 | 762.88 | 55910.1 | 682
KY | KY - WEST | 2621 | 24026363700 |  |  |  | 6720212D | 2409175 | U461383 |  | 558 | EX | RETIRE 580' OF 4"BSMP MAIN | 2600B | EASTIN | EASTIN RD | 067 | LEX | 2024-11-25 | U132645 | U461383 | 2024-10-07 | 2024-12-31 | 2024-12-31 | 2024-11-14 | DEREK PAYTON | 2024-11-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP3637 | AMRCB |  | 100 | 055832240263637 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24026363800 |  |  |  | 6684232O |  | U461383 |  | 587 | EX | INSTALL EC-350 UNIT | 2600M | US 127NORTH | 5701 US 127NORTH | 073 | FRA | 2025-05-20 | U128132 | U461383 | 2024-10-07 | 2024-11-26 | 2024-12-01 | 2024-10-04 | GREG HALE | 2024-10-04 |  |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00587 | 3200587 |  |  | WP3638 |  |  | 100 | 058732240263638 |  | 2 | 5892.2 | 817.1 | 3628.03 | 393.51 | 0 | 0 | 4.37 | 1049.19
KY | KY - WEST | 2623 | 24026363900 |  |  |  | 6684232L |  | U461383 |  | 588 | EX | RETIRE EFC UNIT | 2600M | US 127NORTH | 5701 US 127NORTH | 073 | FRA | 2025-05-13 | U133035 | U461383 | 2024-10-07 | 2024-11-27 | 2024-12-01 | 2024-10-04 | GREG HALE | 2024-10-04 |  |  | F | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00588 | 3200588 |  |  | WP3639 |  |  | 100 | 058832240263639 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24026364900 |  | 501351304 |  | 6736228K | 2398765 | U128885 |  | 555 | EX | INSTALL 2,300'-4" PMMP | 2600B | LINZI | LINZI WY LT45 | 017 | PAR | 2025-04-09 | U128132 | U128885 | 2024-10-09 | 2025-01-08 | 2025-01-31 | 2025-02-24 | RANDALL HUMPHREYS | 2025-03-24 | 2024-12-02 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP3649 |  |  | 100 | 055532240263649 | 291.8333 | 90250 | 215200.02 | 22289.22 | 12750.89 | 19641.15 | 94269.28 | 0 | 1946.52 | 64302.96 | 2375
KY | KY - WEST | 2621 | 24026365000 |  |  |  | 6712208N | 2409284 | U134275 |  | 557 | EX | EMER-INSTALL 10' - 2" PMMP | 2621P | FOUNTAINBLUE | FOUNTAINBLUE LN | 067 | LEX | 2025-03-03 | U136251 | U134275 | 2024-10-09 | 2024-12-30 | 2024-12-31 | 2024-09-03 | MCRAIG | 2024-10-30 | 2024-10-29 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3650 |  |  | 100 | 055732240263650 | 1.6 | 30 | 3040.57 | 1939.06 | 81.82 | 425.2 | 0 | 0 | 0.49 | 594 | 10
KY | KY - WEST | 2621 | 24026365100 |  |  |  | 6712208N | 2409284 | U134275 |  | 558 | EX | EMER-RETIRE 10' - 2" PMMP | 2621P | FOUNTAINBLUE | FOUNTAINBLUE LN | 067 | LEX | 2025-03-04 | U136251 | U134275 | 2024-10-09 | 2024-12-31 | 2024-12-31 | 2024-09-03 | MCRAIG | 2024-10-30 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP3651 |  |  | 100 | 055832240263651 | 0.18333 | 0 | 2.82 | 11.8 | 0 | -8.98 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026365300 |  |  |  | 7356256M | 2409326 | U141016 |  | 557 | EX | EMER INSTALL 5" OF 4" PMLP | 2600E | GREENBRIAR RD | GREENBRIAR RD | 019 | ASH | 2025-02-08 | U128132 | U141016 | 2024-10-11 | 2025-06-25 | 2025-06-30 | 2024-10-09 | MCOLLET | 2025-01-17 | 2024-12-18 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP3653 |  |  | 100 | 055732240263653 | 19.0833 | 16 | 26234.06 | 8160.15 | 444.65 | 2775.86 | 9386.14 | 0 | 44.62 | 5422.64 | 2
KY | KY - EAST | 2631 | 24026365400 |  |  |  | 7356256M | 2409326 | U141016 |  | 558 | EX | EMER RETIRE 5" OF 4" PALP | 2600E | GREENBRIAR RD | GREENBRIAR RD | 019 | ASH | 2025-02-08 | U128132 | U141016 | 2024-10-11 | 2025-06-30 | 2025-06-30 | 2024-10-09 | MCOLLET | 2025-01-17 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP3654 |  |  | 100 | 055832240263654 | 3.6667 | 0 | 612.15 | 267.22 | 0 | 344.93 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026365700 |  | 500514180 |  | 6720208M | 2409328 | U461383 |  | 555 | EX | INSTALL 320' OF 2"PMIP MAIN | 2600B | MONTAVESTA | 3426 MONTAVESTA RD | 067 | LEX | 2025-01-23 | U132645 | U461383 | 2024-10-14 | 2025-01-02 | 2025-01-10 | 2024-11-19 | RANDALL HUMPHREYS | 2024-12-18 | 2024-11-13 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3657 |  |  | 100 | 055532240263657 | 40 | 1825 | 29754.73 | 2768.05 | 1611.75 | 1344.15 | 17405.69 | 0 | 71.83 | 6553.26 | 365
KY | KY - CENTRAL | 2632 | 24026366400 |  | 501372394 |  | 7256276B | 2409391 | U122858 |  | 555 | EX | INSTALL ~390'-2" PMIP | 2621P | EVERGREEN | EVERGREEN LN LT1 | 161 | MAY | 2025-04-08 | U128132 | U122858 | 2024-10-22 | 2025-02-06 | 2025-02-14 | 2025-02-14 | TALLISON | 2025-03-31 | 2025-01-29 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00555 | 3200555 |  |  | WP3664 |  |  | 100 | 055532240263664 | 181.3 | 15428 | 44902.44 | 12792.64 | 4394.73 | 1004.11 | 11128.75 | 0 | 201.07 | 15381.14 | 532
KY | KY - EAST | 2631 | 24026367000 |  |  |  | 7356256A | 2409784 | U122858 |  | 557 | EX | EMER INSTALL 5'-2" PMMP | 2600E | CHESTNUT | 1511 CHESTNUT DR | 019 | ASH | 2025-03-24 | U132645 | U122858 | 2024-10-28 | 2024-10-09 | 2024-10-10 | 2024-10-11 | R CUMPSTON | 2024-10-11 | 2024-11-13 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP3670 |  |  | 100 | 055732240263670 | 36.5 | 45 | 7909.41 | 4847.43 | 379.1 | 950.89 | 22.2 | 0 | 6.25 | 1703.54 | 5
KY | KY - EAST | 2631 | 24026367100 |  |  |  | 7356256A | 2409784 | U122858 |  | 558 | EX | EMER RETIRE 5'-2" PMMP | 2600E | CHESTNUT | 1511 CHESTNUT DR | 019 | ASH | 2025-03-24 | U132645 | U122858 | 2024-10-28 | 2024-10-10 | 2024-10-10 | 2024-10-11 | R CUMPSTON | 2024-10-11 | 2024-12-05 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP3671 |  |  | 100 | 055832240263671 | 3.9167 | 0 | 451.33 | 271.3 | 0 | 180.03 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24026367700 |  |  |  | 7384168F | 1852534 | U461383 |  | 587 | EX | INSTALL NEW EC-350 UNIT | 2600M | CENTRAL | 2000 CENTRAL AV | 195 | S W | 2025-03-28 | U133035 | U461383 | 2024-11-06 | 2024-12-31 | 2024-12-31 | 2024-11-08 | MRYAN | 2024-11-08 | 2024-11-08 |  | F | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00587 | 3200587 |  |  | WP3677 |  |  | 100 | 058732240263677 | 4.6833 | 0 | 706.81 | 379 | 0 | 161.17 | 0 | 0 | 2.04 | 164.6
KY | KY - EAST | 2633 | 24026367800 |  |  |  | 7384168F | 1852534 | U461383 |  | 588 | EX | RETIRE EME UNIT | 2600M | CENTRAL | 2000 CENTRAL AV | 195 | S W | 2025-03-25 | U133035 | U461383 | 2024-11-06 | 2024-12-31 | 2024-12-31 | 2024-11-08 | MRYAN | 2024-11-08 | 2024-11-08 |  | F | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00588 | 3200588 |  |  | WP3678 |  |  | 100 | 058832240263678 | 3.3167 | 0 | 379.26 | 266.1 | 0 | 113.16 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24026368000 |  |  |  | 7240204J | 2410061 | U122858 |  | 557 | EX | EMER - INSTALL 5'-2" PMMP | 2621P | LEVEE | 6845 LEVEE RD | 173 | JEF | 2025-01-07 | U128132 | U122858 | 2024-11-07 | 2024-11-01 | 2024-11-01 | 2024-11-02 | WDENNING | 2024-12-09 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3680 |  |  | 100 | 055732240263680 |  | 6 | 4545.67 | 3257.63 | 0 | 198.36 | 23.68 | 0 | 13.09 | 1052.91 | 6
KY | KY - CENTRAL | 2629 | 24026368100 |  |  |  | 7240204J | 2410061 | U122858 |  | 558 | EX | EMER - RETIRE 5'-2" PMMP | 2621P | LEVEE | 6845 LEVEE RD | 173 | JEF | 2025-01-07 | U128132 | U122858 | 2024-11-07 | 2024-11-01 | 2024-11-01 | 2024-11-02 | DENNING | 2024-12-08 | 2024-11-08 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP3681 |  |  | 100 | 055832240263681 | 1.5333 | 0 | 295.06 | 184.15 | 0 | 110.91 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026368600 |  | 501372393 |  | 6712208N | 2409557 | U141016 |  | 555 | EX | INSTALL 640' OF 2" PMMP | 2600B | FOUNTAINBLUE | 3980 FOUNTAINBLUE LN LT4 | 067 | LEX | 2025-06-19 | U136251 | U141016 | 2024-11-11 | 2025-05-23 | 2025-06-01 | 2025-05-29 | EDWARD F GOINS | 2025-06-10 | 2025-05-20 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3686 |  |  | 100 | 055532240263686 | 55.0833 | 5456 | 50384.93 | 3760.94 | 2904.43 | 728.05 | 31726.33 | 0 | 206.36 | 11058.82 | 682
KY | KY - WEST | 2621 | 24026368800 |  |  |  | 6716208K | 2410260 | U134275 |  | 559 | EX | INSTALL 5' OF 6" PMLP (PIF) | 2600E | ZANDALE | 256 ZANDALE DR | 067 | LEX | 2025-02-07 | U132645 | U134275 | 2024-11-13 | 2025-06-26 | 2025-06-30 | 2025-02-03 | JOSH PASLEY | 2025-02-03 | 2025-01-17 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP3688 | AMRCB |  | 100 | 055932240263688 | 77.6167 | 72 | 53924.5 | 6309.92 | 16813.78 | 4085.08 | 9678.51 | 0 | 370.64 | 16666.57
KY | KY - WEST | 2621 | 24026368900 |  |  |  | 6716208K | 2410260 | U134275 |  | 560 | EX | RETIRE 5' OF 6" BSLP | 2600E | ZANDALE | 256 ZANDALE DR | 067 | LEX | 2025-02-06 | U132645 | U134275 | 2024-11-13 | 2025-06-30 | 2025-06-30 | 2025-02-03 | JOSH PASLEY | 2025-02-03 | 2025-01-31 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00560 | 3200560 |  |  | WP3689 | AMRCB |  | 100 | 056032240263689 | 8 | 0 | 806.6 | 546.52 | 0 | 35.96 | 224.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026369000 |  |  |  | 6720212E | 2410261 | U122858 |  | 557 | EX | INSTALL 65'-8" PMLP | 2621P | LIMESTONE | 501 N LIMESTONE | 067 | LEX | 2025-06-20 | U132645 | U122858 | 2024-11-13 | 2025-07-18 | 2025-07-31 | 2025-04-03 | BDARNELL | 2025-06-06 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3690 | AMRCB |  | 100 | 055732240263690 | 0.98333 | 178 | 144966.81 | 31637.83 | 9002.36 | 8115.7 | 75991.58 | 0 | 517.71 | 19701.63 | 178
KY | KY - WEST | 2621 | 24026369100 |  |  |  | 6720212E | 2410261 | U122858 |  | 558 | EX | RETIRE 70'-12'&6" BSLP | 2621P | LIMESTONE | LIMESTONE | 067 | LEX | 2025-06-20 | U132645 | U122858 | 2024-11-13 | 2025-07-31 | 2025-07-31 | 2025-04-03 | BDARNELL | 2025-06-06 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP3691 | AMRCB |  | 100 | 055832240263691 | 0.13333 | 0 | 6.18 | 5.83 | 0 | 0.35 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026370400 |  |  |  | 6728204M | 2403699 | U461383 |  | 577 | EX | INSTALL RTU BUILDING | 2621M | ATHENS BOONESBORO | 4940 ATHENS BOONESBORO RD | 067 | LEX | 2025-06-11 | U133035 | U461383 | 2024-11-26 | 2024-12-13 | 2024-12-15 | 2024-11-26 | DANNY ASH | 2024-11-26 |  |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00577 | 3200577 |  |  | WP3704 |  |  | 100 | 057732240263704 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24026370500 |  |  |  | 6736180C | 2402680 | U128885 |  | 575 | EX | ACQUIRE LAND RIGHTS | 2600E | MILLER | 231 MILLER DR | 151 | RIC | 2025-05-09 | U128132 | U128885 | 2024-12-02 | 2024-12-31 | 2024-12-31 | 2025-05-05 | DAVIS | 2025-05-05 |  |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00575 | 3200575 |  |  | WP3705 |  |  | 100 | 057532240263705 |  | 1 | 20657.58 | 0 | 0 | 20000 | 0 | 0 | 657.58 | 0
KY | KY - WEST | 2621 | 24026370600 |  |  |  | 6712212P | 2410683 | U122858 |  | 561 | CO | INSTALL 32'-6" PMLP | 2600E | FURLONG | 873 FURLONG DR | 067 | LEX | 2025-05-30 |  | U122858 | 2024-12-02 | 2025-05-23 |  | 2025-04-16 | KKINDER | 2025-05-30 | 2025-04-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP3706 | AMRCB |  | 100 | 056132240263706 | 82.6333 | 0 | 8317.84 | 4657.23 | 3313.8 | 474.33 | 0 | 0 | 122.98 | -250.5
KY | KY - WEST | 2621 | 24026370700 |  |  |  | 6712212P | 2410683 | U122858 |  | 562 | CO | RETIRE 20'-6" BSLP | 2600E | FURLONG | 873 FURLONG DR | 067 | LEX | 2025-05-30 |  | U122858 | 2024-12-02 | 2025-05-30 |  | 2025-04-16 | KKINDER | 2025-05-30 | 2025-04-14 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP3707 | AMRCB |  | 100 | 056232240263707 | 125.9333 | 0 | 8109.18 | 7113.59 | 0 | 995.59 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026371100 |  |  |  | 6724212K | 2410765 | U461383 |  | 557 | EX | EMER-INSTALL 6' OF 8"PMMP | 2621P | WINCHESTER | 2550 WINCHESTER RD | 067 | LEX | 2025-06-10 | U132645 | U461383 | 2024-12-05 | 2025-07-01 | 2025-07-01 | 2024-12-16 | BDARNELL | 2025-05-09 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3711 |  |  | 100 | 055732240263711 | 2.2333 | 6 | 5742.34 | 3438.75 | 864.86 | 355.77 | 0 | 0 | 18.01 | 1064.95 | 6
KY | KY - WEST | 2621 | 24026371200 |  |  |  | 6724212K | 2410765 | U461383 |  | 558 | EX | EMER-RETIRE 6' OF 8"PMP MAIN | 2621P | WINCHESTER | 2550 WINCHESTER RD | 067 | LEX | 2025-06-09 | U132645 | U461383 | 2024-12-05 | 2025-04-28 | 2025-07-01 | 2024-12-16 | BDARNELL | 2025-05-09 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP3712 |  |  | 100 | 055832240263712 | 0.31667 | 0 | 397.39 | 14.24 | 0 | 0.83 | 382.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026371600 |  |  |  | 6720208A | 2410818 | U134275 |  | 557 | EX | EMER - INSTALL 5' - 2" PMMP | 2621P | FONTAINE | 1120 FONTAINE RD | 067 | LEX | 2025-06-09 | U138344 | U134275 | 2024-12-06 | 2024-12-31 | 2025-07-01 | 2024-11-27 | RSTRONG | 2025-05-09 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3716 |  |  | 100 | 055732240263716 | 0.65 | 5 | 6372.3 | 1968.74 | 23.89 | 136.52 | 2714.57 | 0 | 3.32 | 1525.26 | 5
KY | KY - WEST | 2621 | 24026371700 |  |  |  | 6720208A | 2410818 | U134275 |  | 558 | EX | EMER - RETIRE 5' - 2" PMMP | 2621P | FONTAINE | 1120 FONTAINE RD | 067 | LEX | 2025-06-09 | U138344 | U134275 | 2024-12-06 | 2024-12-31 | 2025-07-01 | 2024-11-27 | RSTRONG | 2025-05-09 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP3717 |  |  | 100 | 055832240263717 | 0.43333 | 0 | 45.7 | 31.81 | 0 | 13.89 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24026371800 |  |  |  | 6736228C | 2410846 | U128885 |  | 557 | EX | EMER - INSTALL 3'-2" PMMP | 2621P | ARLINGTON | ARLINGTON | 017 | PAR | 2025-01-09 | U128132 | U128885 | 2024-12-09 | 2024-12-12 | 2024-12-31 | 2024-12-03 | NRICHIE | 2024-12-22 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3718 |  |  | 100 | 055732240263718 |  | 3 | 19259.53 | 7226.3 | 59.91 | 3696.58 | 4916.45 | 0 | 55.15 | 3305.14 | 3
KY | KY - CENTRAL | 2629 | 24026371900 |  |  |  | 6736228C | 2410846 | U128885 |  | 558 | EX | EMER - RETIRE 3'-2" PMP | 2621P | ALVERSON | ALVERSON | 017 | PAR | 2025-01-09 | U128132 | U128885 | 2024-12-09 | 2049-12-31 | 2049-12-31 | 2024-12-03 | NRICHIE | 2024-12-22 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP3719 |  |  | 100 | 055832240263719 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24026372000 |  | 501374098 |  | 6700212M | 2410689 | U126783 |  | 555 | EX | INSTALLING 500'-2" PMMP | 2600B | AZALEA | AZALEA LN LT87 | 239 | VER | 2025-03-05 | U128132 | U126783 | 2024-12-09 | 2025-02-28 | 2025-03-14 | 2025-02-18 | STEVE CANOY | 2025-02-21 | 2025-02-05 | 2025-02-12 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP3720 |  |  | 100 | 055532240263720 | 53.6833 | 4510 | 47889.55 | 4101.13 | 1631.68 | 3343.89 | 18785.68 | 0 | 129.25 | 19897.92 | 451
KY | KY - WEST | 2621 | 24026372500 |  |  |  | 6720212L | 2408542 | U132703 |  | 909 | CO | REPLACE VSAT WITH AT&T MODEM | 2621M | WINCHESTER | 1314 WINCHESTER RD | 067 | LEX | 2025-06-20 |  | U132703 | 2024-12-11 | 2025-12-31 | 2025-12-31 | 2025-05-20 | ROBERT HAYES | 2025-05-20 | 2025-05-08 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP3725 |  |  | 100 | 090932240263725 | 8 | 0 | 6289.92 | 572 | 0 | 33.12 | 5500 | 0 | 184.8 | 0
KY | KY - WEST | 2621 | 24026372600 |  |  |  | 6720212L | 2408542 | U132703 |  | 910 | CO | REPLACE VSAT | 2600E | WINCHESTER | 1314 WINCHESTER RD | 067 | LEX | 2025-06-20 |  | U132703 | 2024-12-11 | 2025-12-31 | 2025-12-31 | 2025-05-20 | ROBERT HAYES | 2025-05-20 |  |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00910 | 3200910 |  |  | WP3726 |  |  | 100 | 091032240263726 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026372700 |  |  |  | 6720212L | 2408542 | U132703 |  | 909 | CO | INSTALL SOLAR BACKUP | 2621M | WINCHESTER | 1314 WINCHESTER RD | 067 | LEX | 2025-06-20 |  | U132703 | 2024-12-11 | 2025-12-31 | 2025-12-31 | 2025-05-20 | ROBERT HAYES | 2025-05-20 |  |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP3727 |  |  | 100 | 090932240263727 |  | 0 | 7232.8 | 0 | 0 | 0 | 7000 | 0 | 232.8 | 0
KY | KY - EAST | 2631 | 24026372800 |  |  |  | 7352252K | 2408542 | U132703 |  | 909 | EX | INSTALL SOLAR BACKUP | 2631M | SKYLINE | SKYLINE DR | 019 | ASH | 2025-02-25 | U133035 | U132703 | 2024-12-11 | 2025-12-31 | 2025-12-31 | 2025-02-13 | AMCCORM | 2025-02-13 |  |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP3728 |  |  | 100 | 090932240263728 | 12.6 | 0 | 8466.91 | 944.72 | 0 | 413.86 | 7000 | 0 | 108.33 | 0
KY | KY - WEST | 2621 | 24026373100 |  |  |  | 6720212P | 2408542 | U132703 |  | 909 | EX | INSTALL SOLAR BACKUP | 2600E | FORTUNE | 2350 FORTUNE DR | 067 | LEX | 2025-02-25 | U133035 | U132703 | 2024-12-11 | 2025-12-31 | 2025-12-31 | 2025-02-12 | APARKS | 2025-02-12 | 2025-02-12 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP3731 |  |  | 100 | 090932240263731 | 5.9833 | 0 | 7699.73 | 463.44 | 0 | 130.26 | 7000 | 0 | 106.03 | 0
KY | KY - CENTRAL | 2629 | 24026373200 |  |  |  | 6736228H | 2408542 | U461383 |  | 909 | EX | INSTALL SOLAR BACKUP UNIT | 2600E | CLINTONVILLE | CLINTONVILLE RD | 017 | PAR | 2025-03-18 | U133035 | U461383 | 2024-12-11 | 2025-12-31 | 2025-12-31 | 2025-02-24 | JACOB BRADFORD | 2025-02-24 |  |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00909 | 3200909 |  |  | WP3732 |  |  | 100 | 090932240263732 |  | 0 | 7104.24 | 0 | 0 | 0 | 7000 | 0 | 104.24 | 0
KY | KY - EAST | 2631 | 24026373300 |  |  |  | 7356248P | 2408542 | U461383 |  | 909 | CO | INSTALL SOLAR BACKUP UNIT | 2631M | US23--ASHLAND OIL | US23--ASHLAND OIL | 019 | CAT | 2025-03-05 |  | U461383 | 2024-12-11 | 2025-12-31 | 2025-12-31 | 2025-02-27 | DAVID SKAGGS | 2025-02-27 | 2025-02-27 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP3733 |  |  | 100 | 090932240263733 | 4.5 | 0 | 7710.91 | 324.53 | 0 | 279.22 | 7000 | 0 | 107.16 | 0
KY | KY - EAST | 2631 | 24026373500 |  |  |  | 7360240T | 2408542 | U461383 |  | 909 | EX | INSTALL SOLAR BACKUP UNIT | 2631M | OLD US 23 | OLD US 23 | 019 | CAT | 2025-02-25 | U133035 | U461383 | 2024-12-11 | 2025-12-31 | 2025-12-31 | 2025-02-14 | AMCCORM | 2025-02-14 |  |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP3735 |  |  | 100 | 090932240263735 | 6.7667 | 0 | 7634.88 | 505.37 | 0 | 23.68 | 7000 | 0 | 105.83 | 0
KY | KY - CENTRAL | 2632 | 24026373600 |  |  |  | 7256276K | 2408542 | U461383 |  | 909 | EX | INSTALL SOLAR BACKUP UNIT | 2600E | MAPLE LEAF | MAPLE LEAF RD | 161 | MAY | 2025-02-25 | U133035 | U461383 | 2024-12-12 | 2025-12-31 | 2025-12-31 | 2025-02-17 | DSASH | 2025-02-17 |  |  | F | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00909 | 3200909 |  |  | WP3736 |  |  | 100 | 090932240263736 |  | 0 | 7104.24 | 0 | 0 | 0 | 7000 | 0 | 104.24 | 0
KY | KY - CENTRAL | 2629 | 24026373700 |  |  |  | 6748208E | 2408542 | U461383 |  | 909 | EX | INSTALL SOLAR BACKUP UNIT | 2600E | EARLY | EARLY DR | 049 | WIN | 2025-02-25 | U133035 | U461383 | 2024-12-12 | 2025-12-31 | 2025-12-31 | 2025-02-18 | JDHOBB | 2025-02-18 | 2025-02-18 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00909 | 3200909 |  |  | WP3737 |  |  | 100 | 090932240263737 | 8.8667 | 0 | 8114.69 | 768.99 | 0 | 238.44 | 7000 | 0 | 107.26 | 0
KY | KY - CENTRAL | 2629 | 24026373800 |  |  |  | 6740228A | 2410951 | U128885 |  | 557 | EX | EMER - INSTALL 3'-2" PMMP | 2621P | VINE | VINE | 017 | PAR | 2025-01-03 | U128132 | U128885 | 2024-12-12 | 2024-12-27 | 2024-12-31 | 2024-12-05 | NRICHIE | 2024-12-22 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3738 |  |  | 100 | 055732240263738 |  | 3 | 6014.6 | 1910.03 | 148.31 | 1097.12 | 1563.76 | 0 | 10.75 | 1284.63 | 3
KY | KY - CENTRAL | 2629 | 24026373900 |  |  |  | 6740228A | 2410951 | U128885 |  | 558 | EX | EMER - RETIRE 3'-2" PAMP | 2621P | VINE | VINE | 017 | PAR | 2024-12-28 | U128132 | U128885 | 2024-12-12 |  | 2049-12-31 | 2024-12-05 | NRICHIE | 2024-12-22 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP3739 |  |  | 100 | 055832240263739 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026374100 |  |  |  | 7344264A | 2408542 | U461383 |  | 909 | EX | INSTALL SOLAR BACKUP UNIT | 2631M | CAROLINE | 202 CAROLINE AV | 089 | WUR | 2025-03-18 | U133035 | U461383 | 2024-12-12 | 2025-12-31 | 2025-12-31 | 2025-02-24 | SHANE GIORDANO | 2025-02-24 | 2025-02-21 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP3741 |  |  | 100 | 090932240263741 | 5.9833 | 0 | 7964.76 | 486.08 | 0 | 371.86 | 7000 | 0 | 106.82 | 0
KY | KY - WEST | 2621 | 24026375200 |  |  |  | 6716216P | 2410970 | U461383 |  | 557 | EX | EMER-INSTALL 6' OF 2"PMMP MAIN | 2621P | ADCOLOR | ADCOLOR DR | 067 | LEX | 2025-06-10 | U132645 | U461383 | 2024-12-12 | 2025-08-29 |  | 2024-12-11 | L STANFIELD | 2024-12-11 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3752 |  |  | 100 | 055732240263752 |  | 6 | 6850.53 | 3673.83 | 285.03 | 1532.08 | 105.08 | 0 | 22.85 | 1231.66 | 6
KY | KY - WEST | 2621 | 24026375300 |  |  |  | 6716216P | 2410970 | U461383 |  | 558 | EX | EMER-RETIRE 6' OF 2"PMMP MAIN | 2621P | ADCOLOR | ADCOLOR DR | 067 | LEX | 2025-05-31 | U132645 | U461383 | 2024-12-12 | 2025-08-29 |  | 2024-12-11 | L STANFIELD | 2024-12-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP3753 |  |  | 100 | 055832240263753 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24026375700 |  |  |  | 7356152E | 2408542 | U126783 |  | 909 | EX | INSTALL FLOAT SWITCH | 2600E | US23 UPPER HAROLD 1419 | US23 UPPER HAROLD 1419 | 071 | HAR | 2025-03-18 | U133035 | U126783 | 2024-12-12 | 2025-12-31 | 2025-12-31 | 2025-02-26 | MATT RYAN | 2025-02-26 | 2025-02-25 |  | F | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00909 | 3200909 |  |  | WP3757 |  |  | 100 | 090932240263757 | 0.81667 | 0 | 1897.47 | 192.9 | 0 | 181.64 | 1500 | 0 | 22.93 | 0
KY | KY - EAST | 2633 | 24026375800 |  |  |  | 7384168L | 2408542 | U126783 |  | 909 | EX | INSTALL FLOAT SWITCH | 2600E | US 119 1433 | US 119 1433 | 195 | S W | 2025-06-11 | U133035 | U126783 | 2024-12-12 | 2025-12-31 | 2025-12-31 | 2025-02-25 | MATT RYAN | 2025-02-25 | 2025-02-25 |  | F | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00909 | 3200909 |  |  | WP3758 |  |  | 100 | 090932240263758 | 4.8 | 0 | 2733.24 | 652.03 | 0 | 556.49 | 1500 | 0 | 24.72 | 0
KY | KY - EAST | 2633 | 24026375900 |  |  |  | 7356152A | 2408542 | U126783 |  | 909 | EX | INSTALL FLOAT SWITCH | 2600E | LOWER HAROLD 1418 | LOWER HAROLD 1418 | 071 | HAR | 2025-03-18 | U133035 | U126783 | 2024-12-12 | 2025-12-31 | 2025-12-31 | 2025-02-26 | MATT RYAN | 2025-02-26 | 2025-02-25 |  | F | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00909 | 3200909 |  |  | WP3759 |  |  | 100 | 090932240263759 | 2.3833 | 0 | 2210.8 | 365.95 | 0 | 321.2 | 1500 | 0 | 23.65 | 0
KY | KY - CENTRAL | 2629 | 24026376300 |  |  |  | 6736212K | 2411100 | U128885 |  | 557 | EX | EMER - INSTALL 5'-2" PMIP | 2621P | CONSTITUTION | CONSTITUTION | 049 | WIN | 2025-02-19 | U128132 | U128885 | 2024-12-18 | 2024-12-23 | 2024-12-31 | 2024-12-13 | LSTANFI | 2025-01-24 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3763 |  |  | 100 | 055732240263763 |  | 5 | 6514.7 | 2596.97 | 596.56 | 151.69 | 1690.48 | 0 | 10.75 | 1468.25 | 5
KY | KY - CENTRAL | 2629 | 24026376400 |  |  |  | 6736212K | 2411100 | U128885 |  | 558 | EX | EMER - RETIRE 5'-2" PAIP | 2621P | CONSTITUTION | CONSTITUTION | 049 | WIN | 2025-02-08 | U128132 | U128885 | 2024-12-18 | 2024-12-30 | 2024-12-31 | 2024-12-13 | LSTANFI | 2025-01-24 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP3764 |  |  | 100 | 055832240263764 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026376700 |  |  |  | 6720208H | 2411195 | U122858 |  | 557 | EX | EMER - INSTALL 3'-2" PMMP | 2621P | HEDGEWOOD | 188 HEDGEWOOD CT | 067 | LEX | 2025-06-13 | U132645 | U122858 | 2024-12-20 | 2025-08-28 | 2025-08-31 | 2024-11-25 | HMCKUNE | 2025-01-10 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3767 |  |  | 100 | 055732240263767 | 6.95 | 9 | 3141.8 | 2101.44 | 24 | 297.25 | 108.04 | 0 | 2.21 | 608.86 | 3
KY | KY - WEST | 2621 | 24026376800 |  |  |  | 6720208H | 2411195 | U122858 |  | 558 | EX | EMER - RETIRE 3'-2" PMP | 2621P | HEDGEWOOD | 188 HEDGEWOOD CT | 067 | LEX | 2025-06-11 | U132645 | U122858 | 2024-12-20 | 2025-08-29 | 2025-08-31 | 2024-11-25 | HMCKUNE | 2025-01-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP3768 |  |  | 100 | 055832240263768 | 0.1 | 0 | 6.4 | 4.66 | 0 | 1.74 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026376901 |  |  |  | 6724208M | 2075930 | U122858 |  | 561 | EX | INSTALL 1218'-6" PMMP | 2600B | RICHMOND | RICHMOND RD | 067 | LEX | 2025-05-13 | U128132 | U122858 | 2025-05-01 | 2025-02-28 | 2025-04-30 | 2025-04-29 | WILLIAM FULKS | 2025-04-30 | 2025-03-04 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP3769 |  |  | 100 | 056132240263769 | 375.0667 | 66176 | 707094.52 | 24176.63 | 15262.68 | 7222.68 | 437081.86 | 0 | 5885.76 | 217464.91 | 1408
KY | KY - WEST | 2621 | 24026377000 |  |  |  | 6724208M | 2075930 | U122858 |  | 562 | EX | RETIRE 1140'-6" PMP | 2600B | RICHMOND | RICHMOND RD | 067 | LEX | 2025-05-13 | U128132 | U122858 | 2024-12-23 | 2025-09-30 | 2025-09-30 | 2025-04-30 | WILLIAM FULKS | 2025-04-30 | 2025-03-07 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP3770 |  |  | 100 | 056232240263770 | 8 | 0 | 571.78 | 540.12 | 0 | 31.66 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233582100 |  | 100259948 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | 16TH | 815 16TH ST | 019 | ASH | 2024-10-22 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-21 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2128.49 | 36.93 | 0 | -15.32 | 2106.88 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233582200 |  | 100259955 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | 16TH | 816 16TH ST | 019 | ASH | 2024-10-21 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-18 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3010.3 | 0 | 0 | 0 | 3010.3 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233582300 |  | 100259950 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | 16TH | 819 16TH ST | 019 | ASH | 2024-10-19 | U123965 | U125763 | 2024-01-02 | 2024-12-31 |  |  | CJH MITCHELL DICKESS/M BLANKEN | 2024-10-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 5224.37 | 0 | 0 | 0 | 5224.37 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233582400 |  | 100259976 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | 17TH | 812 17TH ST | 019 | ASH | 2024-10-09 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | MITCHELL DICKESS | 2024-10-03 | 2024-10-03 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 4.75 | 1 | 3846.92 | 268.67 | 0 | 232.03 | 3346.22 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233582600 |  | 100259968 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | 17TH | 817 17TH ST | 019 | ASH | 2024-10-02 | BROBERT | U125763 | 2024-01-02 | 2024-12-31 |  |  | BROBERT | 2024-10-02 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.86667 | 1 | 1977.08 | 50.09 | 0 | 43.26 | 1883.73 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233582700 |  | 100259973 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | 17TH | 818 17TH ST | 019 | ASH | 2024-10-09 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | JORDAN HIERONIMUS | 2024-10-03 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 1.0667 | 1 | 3162.26 | 59.77 | 0 | 51.62 | 3050.87 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233582800 |  | 100259969 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | 17TH | 819 17TH ST | 019 | ASH | 2024-09-25 | U123965 | U125763 | 2024-01-02 | 2024-12-31 |  |  | CJH JOSEPH HADLEY | 2024-09-24 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.26667 | 1 | 2359.57 | 15.36 | 0 | 13.28 | 2330.93 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233582900 |  | 100259971 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | 17TH | 821 17TH ST | 019 | ASH | 2024-10-01 | BROBERT | U125763 | 2024-01-02 | 2024-12-31 |  |  | BROBERT | 2024-10-01 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 2.15 | 1 | 2303.15 | 123.54 | 0 | 106.68 | 2072.93 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233583100 |  | 100260010 |  | 7356256B | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | 20TH | 822 20TH ST | 019 | ASH | 2024-10-11 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | ORA SLONE | 2024-10-10 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2909.2 | 0 | 0 | 0 | 2909.2 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233583200 |  | 100260003 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | ASHLAND | 816 ASHLAND AV | 019 | ASH | 2024-10-28 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-25 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1917.68 | 0 | 0 | 0 | 1917.68 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233583400 |  | 100260000 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | ASHLAND | 817 ASHLAND AV | 019 | ASH | 2024-09-30 | BROBERT | U125763 | 2024-01-02 | 2024-12-31 |  |  | BROBERT | 2024-09-30 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 2.9833 | 1 | 2890.96 | 198.31 | 0 | 202.29 | 2490.36 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233583500 |  | 100260002 |  | 7356256A |  |  |  | 565 | EX | GR 1 LK REPAIR | 2621P | ASHLAND | 818 ASHLAND AV | 019 | ASH | 2024-09-23 | DYOUNG | U125763 | 2024-01-02 | 2024-09-13 | 2024-09-13 |  | MCOLLET | 2024-09-13 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 23.6333 | 3 | 3068.84 | 1600.75 | 240.72 | 427.37 | 800 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233583600 |  | 100260001 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | ASHLAND | 819 ASHLAND AV | 019 | ASH | 2024-09-26 | U123965 | U125763 | 2024-01-02 | 2024-12-31 |  |  | CJH JOSEPH HADLEY/MBLANKE | 2024-09-24 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2470.7 | 0 | 0 | 0 | 2470.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233583700 |  | 100260129 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | ASHLAND | 907 ASHLAND AV | 019 | ASH | 2024-09-25 | U123965 | U125763 | 2024-01-02 | 2024-12-31 |  |  | MITCHELL DICKESS CJH | 2024-09-24 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2820.81 | 0 | 0 | 0 | 2820.81 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233583800 |  | 100260145 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | ASHLAND | 908 ASHLAND AV | 019 | ASH | 2024-09-25 | U123965 | U125763 | 2024-01-02 | 2024-12-31 |  |  | JORDAN HIERONIMUS | 2024-09-24 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2680.22 | 0 | 0 | 0 | 2680.22 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233583900 |  | 100260130 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | ASHLAND | 909 ASHLAND AV | 019 | ASH | 2024-09-25 | U123965 | U125763 | 2024-01-02 | 2024-12-31 |  |  | JORDAN HEIRONIMUS | 2024-09-24 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2888.19 | 0 | 0 | 0 | 2888.19 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233584000 |  | 100260140 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | ASHLAND | 914 ASHLAND AV 1 | 019 | ASH | 2024-09-25 | U123965 | U125763 | 2024-01-02 | 2024-12-31 |  |  | CJH JOSEPH HADLEY/MBLANKE | 2024-09-23 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 4490.57 | 0 | 0 | 0 | 4490.57 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233584100 |  | 100260139 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | ASHLAND | 924 ASHLAND AV | 019 | ASH | 2024-09-25 | U123965 | U125763 | 2024-01-02 | 2024-12-31 |  |  | CJH MITCHELL DICKESS/MBLANKE | 2024-09-23 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2544.14 | 0 | 0 | 0 | 2544.14 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233584200 |  | 100260133 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | ASHLAND | 925 ASHLAND AV 1F | 019 | ASH | 2024-09-25 | U123965 | U125763 | 2024-01-02 | 2024-12-31 |  |  | CJH JORDAN HIERONIMUS/MBLANKE | 2024-09-23 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2762.38 | 0 | 0 | 0 | 2762.38 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233584300 |  | 100260137 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | ASHLAND | 934 ASHLAND AV | 019 | ASH | 2024-09-20 | U123965 | U125763 | 2024-01-02 | 2024-12-31 |  |  | CJH JOSEPH HADLEY/MBLANKE | 2024-09-20 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2823.24 | 0 | 0 | 0 | 2823.24 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233584400 |  | 100260136 |  | 7356256E | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | ASHLAND | 946 ASHLAND AV | 019 | ASH | 2024-09-20 | U123965 | U125763 | 2024-01-02 | 2024-12-31 |  |  | CJH JOSEPH HADLEY | 2024-09-20 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2911.78 | 0 | 0 | 0 | 2911.78 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233584500 |  | 100260135 |  | 7356256E | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | ASHLAND | 952 ASHLAND AV | 019 | ASH | 2024-09-20 | U123965 | U125763 | 2024-01-02 | 2024-12-31 |  |  | CJH JOSEPH HADLEY/MBLANKE | 2024-09-18 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2553.09 | 0 | 0 | 0 | 2553.09 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233584600 |  | 100260134 |  | 7356256E | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | ASHLAND | 956 ASHLAND AV | 019 | ASH | 2024-09-20 | U123965 | U125763 | 2024-01-02 | 2024-12-31 |  |  | CJH JOSEPH HADLEY/MBLANKE | 2024-09-18 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1952.53 | 0 | 0 | 0 | 1952.53 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233584700 |  | 100259086 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | CHESTNUT | 909 CHESTNUT CT | 019 | ASH | 2024-11-05 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-11-04 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2644.21 | 1.07 | 0 | 0.76 | 2642.38 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233584800 |  | 100259089 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | CHESTNUT | 912 CHESTNUT CT | 019 | ASH | 2024-11-06 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-11-05 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3671.1 | 87.62 | 0 | 49.6 | 3533.88 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233584900 |  | 100259088 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | CHESTNUT | 918 CHESTNUT CT | 019 | ASH | 2024-10-25 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-24 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2000.69 | 0 | 0 | 0 | 2000.69 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233585000 |  | 100259083 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | CHESTNUT | 900 CHESTNUT DR | 019 | ASH | 2024-10-31 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-30 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2014.45 | 0 | 0 | 0 | 2014.45 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233585100 |  | 100259074 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | CHESTNUT | 903 CHESTNUT DR | 019 | ASH | 2024-10-30 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-29 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2091.95 | 22.14 | 0 | -9.1 | 2078.91 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233585200 |  | 100259075 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | CHESTNUT | 907 CHESTNUT DR | 019 | ASH | 2024-10-30 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-29 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2143.03 | 0 | 0 | 0 | 2143.03 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233585300 |  | 100259081 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | CHESTNUT | 923 CHESTNUT DR | 019 | ASH | 2024-10-26 | U124015 | U125763 | 2024-01-02 | 2024-12-31 |  |  | ORA SLONE | 2024-10-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2859.99 | 0 | 0 | 0 | 2859.99 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233585400 |  | 100259085 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | CHESTNUT | 1405 CHESTNUT DR | 019 | ASH | 2024-11-01 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-31 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2157.58 | 0 | 0 | 0 | 2157.58 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233585500 |  | 500073525 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | CHESTNUT | 1409 CHESTNUT DR | 019 | ASH | 2024-11-01 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-11-01 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2635.5 | 0 | 0 | 0 | 2635.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233585600 |  | 100259092 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | CHESTNUT | 1500 CHESTNUT DR | 019 | ASH | 2024-11-06 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-11-05 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2017.89 | 0 | 0 | 0 | 2017.89 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233585700 |  | 100259090 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | CHESTNUT | 1506 CHESTNUT DR | 019 | ASH | 2024-11-01 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-11-01 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2127.52 | 0 | 0 | 0 | 2127.52 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233585800 |  | 100259091 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | CHESTNUT | 1508 CHESTNUT DR | 019 | ASH | 2024-10-28 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-28 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2069.49 | 0 | 0 | 0 | 2069.49 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233585900 |  | 100259093 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | CHESTNUT | 1510 CHESTNUT DR | 019 | ASH | 2024-11-05 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-11-04 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2208.73 | 0 | 0 | 0 | 2208.73 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233586100 |  | 100259073 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | CHESTNUT | 1511 CHESTNUT DR | 019 | ASH | 2024-10-10 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.78333 | 1 | 2176.33 | 44.42 | 0 | 38.34 | 2093.57 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233586200 |  | 100259095 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | CHESTNUT | 1518 CHESTNUT DR | 019 | ASH | 2024-11-05 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-11-04 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2069.49 | 0 | 0 | 0 | 2069.49 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233586300 |  | 100259094 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | CHESTNUT | 1520 CHESTNUT DR | 019 | ASH | 2024-10-28 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-28 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3158 | 0 | 0 | 0 | 3158 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233586400 |  | 100259071 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | CHESTNUT | 1521 CHESTNUT DR | 019 | ASH | 2024-10-10 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 3.9 | 1 | 3432.74 | 220.31 | 0 | 190.24 | 3022.19 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233586600 |  | 100260099 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1508 HILTON AV | 019 | ASH | 2024-11-11 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-11-08 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2106.45 | 0 | 0 | 0 | 2106.45 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233586700 |  | 100260101 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1600 HILTON AV | 019 | ASH | 2024-11-14 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-11-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2089.25 | 0 | 0 | 0 | 2089.25 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233586800 |  | 100260102 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1604 HILTON AV | 019 | ASH | 2024-11-15 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-11-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 4628.43 | 0 | 0 | 0 | 4628.43 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233586900 |  | 100260094 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1605 HILTON AV | 019 | ASH | 2024-10-23 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-22 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2701.23 | 0 | 0 | 0 | 2701.23 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233587000 |  | 100260090 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1609 HILTON AV 1 | 019 | ASH | 2024-10-24 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-23 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3924.54 | 0 | 0 | 0 | 3924.54 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233587300 |  | 100260106 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1620 HILTON AV | 019 | ASH | 2024-11-20 | U124015 | U125763 | 2024-01-02 | 2024-12-31 |  |  | ORA SLONE | 2024-11-20 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 4088.5 | 0 | 0 | 0 | 4088.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233587400 |  | 100260110 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1628 HILTON AV | 019 | ASH | 2024-11-15 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-11-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2222.53 | 0 | 0 | 0 | 2222.53 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233587500 |  | 100260113 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1638 HILTON AV | 019 | ASH | 2024-11-14 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-11-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3036.83 | 72.82 | 0 | 34.43 | 2929.58 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233587600 |  | 100260115 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1704 HILTON AV | 019 | ASH | 2024-11-12 | U124015 | U125763 | 2024-01-02 | 2024-12-31 |  |  | ORA SLONE | 2024-11-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2361.35 | 0 | 0 | 0 | 2361.35 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233587800 |  | 100260117 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1712 HILTON AV | 019 | ASH | 2024-11-11 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-11-08 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2277.57 | 0 | 0 | 0 | 2277.57 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233587900 |  | 100260086 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1715 HILTON AV | 019 | ASH | 2024-11-11 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-11-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2011.01 | 0 | 0 | 0 | 2011.01 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233588000 |  | 100260085 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1717 HILTON AV | 019 | ASH | 2024-11-02 | U124015 | U125763 | 2024-01-02 | 2024-12-31 |  |  | ORA SLONE | 2024-11-02 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2673.31 | 21.7 | 0 | 12.2 | 2639.41 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233588200 |  | 100260082 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1805 HILTON AV | 019 | ASH | 2024-10-24 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-23 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3019.75 | 0 | 0 | 0 | 3019.75 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233588300 |  | 100260124 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1808 HILTON AV | 019 | ASH | 2024-10-18 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-17 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2744.65 | 70.43 | 0 | 4.32 | 2669.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233588400 |  | 100260125 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1812 HILTON AV | 019 | ASH | 2024-10-15 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2886.91 | 0 | 0 | 0 | 2886.91 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233588500 |  | 100260126 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1818 HILTON AV | 019 | ASH | 2024-10-15 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2656.73 | 0 | 0 | 0 | 2656.73 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233588800 |  | 100260127 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1824 HILTON AV | 019 | ASH | 2024-10-15 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3675.54 | 0 | 0 | 0 | 3675.54 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233588900 |  | 100260146 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1900 HILTON AV | 019 | ASH | 2024-10-14 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2635.5 | 0 | 0 | 0 | 2635.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233589000 |  | 100260147 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1904 HILTON AV | 019 | ASH | 2024-10-14 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2900.38 | 0 | 0 | 0 | 2900.38 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233589100 |  | 100260073 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1909 HILTON AV | 019 | ASH | 2024-10-12 | U123965 | U125763 | 2024-01-02 | 2024-12-31 |  |  | CJH BRENT RUNYON/M BLANKENSHIP | 2024-10-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2805.54 | 121.32 | 0 | 7.44 | 2676.78 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233589200 |  | 100260148 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1910 HILTON AV | 019 | ASH | 2024-10-14 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2673.34 | 0 | 0 | 0 | 2673.34 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233589300 |  | 100260149 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1914 HILTON AV | 019 | ASH | 2024-10-14 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | ORA SLONE | 2024-10-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3137.65 | 0 | 0 | 0 | 3137.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233589400 |  | 100260068 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1917 HILTON AV | 019 | ASH | 2024-10-12 | U123965 | U125763 | 2024-01-02 | 2024-12-31 |  |  | CJH J HIERONIMUS/M BLANKENSHIP | 2024-10-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2707.29 | 0 | 0 | 0 | 2707.29 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233589500 |  | 100260150 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1918 HILTON AV | 019 | ASH | 2024-10-14 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | ORA SLONE | 2024-10-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2662.15 | 0 | 0 | 0 | 2662.15 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233589600 |  | 100260067 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1921 HILTON AV | 019 | ASH | 2024-10-14 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | ORA SLONE | 2024-10-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2725.9 | 0 | 0 | 0 | 2725.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233589700 |  | 100260151 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1924 HILTON AV | 019 | ASH | 2024-10-12 | U123965 | U125763 | 2024-01-02 | 2024-12-31 |  |  | CJH JOSEPH HADLEY/ MBLANKENSHI | 2024-10-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2714.62 | 0 | 0 | 0 | 2714.62 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233589800 |  | 100260152 |  | 7356256B | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 2000 HILTON AV | 019 | ASH | 2024-10-12 | U123965 | U125763 | 2024-01-02 | 2024-12-31 |  |  | CJH MITCHELL DICKESS/M BLANKEN | 2024-10-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2669.9 | 0 | 0 | 0 | 2669.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233589900 |  | 100260066 |  | 7356256B | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 2005 HILTON AV | 019 | ASH | 2024-10-10 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-10 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3195.53 | 0 | 0 | 0 | 3195.53 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233590000 |  | 100260065 |  | 7356256B | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 2007 HILTON AV | 019 | ASH | 2024-10-10 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-10 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3414.49 | 0 | 0 | 0 | 3414.49 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233590100 |  | 500110200 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 2014 HILTON AV UNIT A | 019 | ASH | 2024-10-11 | U123965 | U125763 | 2024-01-02 | 2024-12-31 |  |  | CJH MITCHELL DICKESS/M BLANKEN | 2024-10-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3323.4 | 0 | 0 | 0 | 3323.4 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233590200 |  | 500110201 |  | 7356256B | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 2014 HILTON AV UNIT B | 019 | ASH | 2024-10-11 | U123965 | U125763 | 2024-01-02 | 2024-12-31 |  |  | CJH MITCHELL DICKESS/M BLANKEN | 2024-10-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1
KY | KY - EAST | 2631 | 24233590300 |  | 100260059 |  | 7356256B | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 2019 HILTON AV | 019 | ASH | 2024-10-10 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-10 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2808.79 | 64.9 | 0 | -26.99 | 2770.88 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233590400 |  | 100260057 |  | 7356256B | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 2101 HILTON AV | 019 | ASH | 2024-10-16 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-16 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2351.86 | 0 | 0 | 0 | 2351.86 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233590600 |  | 100260056 |  | 7356256B | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 2105 HILTON AV | 019 | ASH | 2024-10-16 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-16 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3341.97 | 0 | 0 | 0 | 3341.97 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233590700 |  | 100260055 |  | 7356256B | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 2107 HILTON AV | 019 | ASH | 2024-10-09 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-08 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 5.25 | 1 | 3163.25 | 320.79 | 0 | 249.11 | 2593.35 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233590800 |  | 100259128 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | PROSPECT | 806 PROSPECT AV | 019 | ASH | 2024-11-02 | U124015 | U125763 | 2024-01-02 | 2024-12-31 |  |  | ORA SLONE | 2024-11-02 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2037.38 | 0 | 0 | 0 | 2037.38 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233590900 |  | 100259127 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | PROSPECT | 808 PROSPECT AV | 019 | ASH | 2024-11-02 | U124015 | U125763 | 2024-01-02 | 2024-12-31 |  |  | ORA SLONE | 2024-11-02 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1932.57 | 0 | 0 | 0 | 1932.57 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233591100 |  | 100259061 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1317 HILTON CT | 019 | ASH | 2024-11-06 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-11-05 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3346.78 | 0 | 0 | 0 | 3346.78 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233591200 |  | 100259062 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1321 HILTON CT | 019 | ASH | 2024-09-20 | U123965 | U125763 | 2024-01-02 | 2024-12-31 |  |  | CJH JOSEPH HADLEY/MBLANKE | 2024-09-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1966.29 | 0 | 0 | 0 | 1966.29 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233591300 |  | 100259080 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1328 HILTON CT | 019 | ASH | 2024-10-25 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-24 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1939.92 | 31.21 | 0 | -12.86 | 1921.57 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233591400 |  | 100259078 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1330 HILTON CT | 019 | ASH | 2024-10-28 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-25 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3050.15 | 0 | 0 | 0 | 3050.15 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233592200 |  | 100259954 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | 16TH | 818 16TH ST | 019 | ASH | 2024-10-22 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-21 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2754.55 | 0 | 0 | 0 | 2754.55 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233592300 |  | 100259953 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | 16TH | 821 16TH ST | 019 | ASH | 2024-10-23 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-22 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1993.81 | 0 | 0 | 0 | 1993.81 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233592400 |  | 100259966 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | 17TH | 813 17TH ST | 019 | ASH | 2024-10-02 | BROBERT | U125763 | 2024-01-02 | 2024-12-31 |  |  | BROBERT | 2024-10-02 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 4.25 | 1 | 2580.58 | 241.93 | 0 | 208.92 | 2129.73 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233592500 |  | 500225506 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | 17TH | 815 17TH ST | 019 | ASH | 2024-10-02 | BROBERT | U125763 | 2024-01-02 | 2024-12-31 |  |  | BROBERT | 2024-10-02 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 1.4833 | 1 | 2228.89 | 83.7 | 0 | 72.26 | 2072.93 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233592600 |  | 100259076 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | CHESTNUT | 911 CHESTNUT DR | 019 | ASH | 2024-10-31 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-30 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3319.21 | 0 | 0 | 0 | 3319.21 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233592700 |  | 100259084 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | CHESTNUT | 1401 CHESTNUT DR | 019 | ASH | 2024-11-01 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-31 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2623.88 | 0 | 0 | 0 | 2623.88 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233592800 |  | 100259072 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | CHESTNUT | 1517 CHESTNUT DR | 019 | ASH | 2024-10-10 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 1 | 1 | 2151.51 | 56.94 | 0 | 49.16 | 2045.41 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233592900 |  | 100259125 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1500 HILTON AV | 019 | ASH | 2024-11-11 | U124015 | U125763 | 2024-01-02 | 2024-12-31 |  |  | ORA SLONE | 2024-11-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1993.81 | 0 | 0 | 0 | 1993.81 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233593100 |  | 100260104 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1612 HILTON AV | 019 | ASH | 2024-11-15 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-11-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 5007.63 | 0 | 0 | 0 | 5007.63 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233593200 |  | 100260105 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1616 HILTON AV | 019 | ASH | 2024-11-15 | U128523 | U125763 | 2024-01-02 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-11-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3461.63 | 0 | 0 | 0 | 3461.63 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233593300 |  | 100260153 |  | 7356256B | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 2004 HILTON AV | 019 | ASH | 2024-10-11 | U123965 | U125763 | 2024-01-02 | 2024-12-31 |  |  | CJH CASEY PACK/M BLANKENSHIP | 2024-10-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2814.26 | 0 | 0 | 0 | 2814.26 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24233593500 |  | 100259079 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 914 HILTON CT | 019 | ASH | 2024-09-20 | U123965 | U125763 | 2024-01-02 | 2024-12-31 |  |  | CJH JOSEPH HADLEY/MBLANKE | 2024-09-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2041.97 | 0 | 0 | 0 | 2041.97 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235197300 |  | 100348205 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | HILL | 304 HILL ST | 049 | WIN | 2024-10-31 | U126604 | U125763 | 2024-01-10 | 2024-12-31 |  |  | WILLIAM FULKS | 2024-10-31 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1953.6 | 0 | 0 | 0 | 1953.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235200100 |  | 100348178 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | MUTUAL | 104 MUTUAL AV | 049 | WIN | 2024-11-21 | U126604 | U125763 | 2024-01-10 | 2024-12-31 |  |  | WILLIAM FULKS | 2024-11-21 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1959.76 | 0 | 0 | 0 | 1959.76 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235200200 |  | 100348175 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | MUTUAL | 110 MUTUAL AV | 049 | WIN | 2024-10-22 | U126604 | U125763 | 2024-01-10 | 2024-12-31 |  |  | WILLIAM FULKS | 2024-10-22 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3310.82 | 0 | 0 | 0 | 3310.82 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235200500 |  | 500523460 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | MUTUAL | 226 MUTUAL AV | 049 | WIN | 2024-10-18 | U126602 | U125763 | 2024-01-10 | 2024-12-31 |  |  | DEREK PAYTON | 2024-10-15 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4617.33 | 0 | 454.96 | 0 | 4162.37 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235201100 |  | 100348284 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | PENDLETON | 21 PENDLETON ST | 049 | WIN | 2024-11-26 | U126530 | U125763 | 2024-01-10 | 2024-12-31 |  |  | JDUNN | 2024-11-26 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2956.71 | 0 | 0 | 0 | 2956.71 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235201200 |  | 100348283 |  | 6744208P | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | PENDLETON | 35 PENDLETON ST | 049 | WIN | 2024-11-26 | U126530 | U125763 | 2024-01-10 | 2024-12-31 |  |  | JDUNN | 2024-11-26 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 10 | 1 | 3821.29 | 748.76 | 0 | 45.07 | 3027.46 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235202400 |  | 100348321 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | GOLDIE | 15 GOLDIE AV | 049 | WIN | 2024-11-20 | U126604 | U125763 | 2024-01-10 | 2024-12-31 |  |  | WILLIAM FULKS | 2024-11-20 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2651.75 | 0 | 0 | 0 | 2651.75 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235202500 |  | 100348310 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | GOLDIE | 16 GOLDIE AV | 049 | WIN | 2024-10-29 | U127414 | U125763 | 2024-01-10 | 2024-12-31 |  |  | EDWRAD FOX | 2024-10-28 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2050.32 | 0 | 0 | 0 | 2050.32 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235202600 |  | 100348320 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | GOLDIE | 17 GOLDIE AV | 049 | WIN | 2024-11-20 | U126530 | U125763 | 2024-01-10 | 2024-12-31 |  |  | JDUNN | 2024-11-20 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3190.52 | 0 | 0 | 0 | 3190.52 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235202700 |  | 100348311 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | GOLDIE | 18 GOLDIE AV | 049 | WIN | 2024-11-20 | U126530 | U125763 | 2024-01-10 | 2024-12-31 |  |  | JDUNN | 2024-11-20 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 10 | 1 | 4002.51 | 748.78 | 0 | 45.07 | 3208.66 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235202800 |  | 100348318 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | GOLDIE | 19 GOLDIE AV | 049 | WIN | 2024-11-19 | U126530 | U125763 | 2024-01-10 | 2024-12-31 |  |  | JDUNN | 2024-11-19 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 9 | 1 | 3266.28 | 673.93 | 0 | 40.55 | 2551.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235202900 |  | 500554335 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | GOLDIE | 21 GOLDIE AV A-1FL | 049 | WIN | 2024-11-06 | U127414 | U125763 | 2024-01-10 | 2024-12-31 |  |  | EDWARD FOX | 2024-11-06 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3171.85 | 0 | 0 | 0 | 3171.85 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235203000 |  | 100348313 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | GOLDIE | 22 GOLDIE AV | 049 | WIN | 2024-11-07 | U127414 | U125763 | 2024-01-10 | 2024-12-31 |  |  | EDWARD FOX | 2024-11-07 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2156.57 | 0 | 0 | 0 | 2156.57 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235203100 |  | 100348569 |  | 6748208M | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | JACKSON | 304 JACKSON ST | 049 | WIN | 2024-10-30 | U127414 | U125763 | 2024-01-10 | 2024-12-31 |  |  | EDWARD FOX | 2024-10-30 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2221.36 | 0 | 0 | 0 | 2221.36 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235203300 |  | 100348570 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | JACKSON | 308 JACKSON ST | 049 | WIN | 2024-11-23 | U126604 | U125763 | 2024-01-10 | 2024-12-31 |  |  | WILLIAM FULKS | 2024-11-23 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3291.31 | 0 | 0 | 0 | 3291.31 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235203400 |  | 100348571 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | JACKSON | 310 JACKSON ST | 049 | WIN | 2024-11-25 | U126530 | U125763 | 2024-01-10 | 2024-12-31 |  |  | JDUNN | 2024-11-25 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 10 | 1 | 3866.62 | 748.76 | 0 | 45.07 | 3072.79 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235203500 |  | 100348572 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | JACKSON | 312 JACKSON ST | 049 | WIN | 2024-11-22 | U126530 | U125763 | 2024-01-10 | 2024-12-31 |  |  | JDUNN | 2024-11-22 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2372.26 | 0 | 0 | 0 | 2372.26 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235203600 |  | 100348560 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | JACKSON | 315 JACKSON ST | 049 | WIN | 2024-11-22 | U126530 | U125763 | 2024-01-10 | 2024-12-31 |  |  | JDUNN | 2024-11-22 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1899.43 | 0 | 0 | 0 | 1899.43 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235203700 |  | 100348574 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | JACKSON | 316 JACKSON ST | 049 | WIN | 2024-11-25 | U126530 | U125763 | 2024-01-10 | 2024-12-31 |  |  | JDUNN | 2024-11-25 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3369.97 | 0 | 0 | 0 | 3369.97 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235204000 |  | 100347748 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | MAIN | 216 N MAIN ST | 049 | WIN | 2024-12-10 | U126604 | U125763 | 2024-01-10 | 2024-12-31 |  |  | WILLIAM FULKS | 2024-12-10 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 9234.59 | 0 | 0 | 0 | 9234.59 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235204100 |  | 100348266 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | MAIN | 245 N MAIN ST | 049 | WIN | 2024-12-02 | U126604 | U125763 | 2024-01-10 | 2024-12-31 |  |  | WILLIAM FULKS | 2024-12-02 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3271.03 | 0 | 0 | 0 | 3271.03 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235204200 |  | 501302148 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | MAIN | 250 N MAIN ST 2 | 049 | WIN | 2024-12-02 | U126530 | U125763 | 2024-01-10 | 2024-12-31 |  |  | JDUNN | 2024-12-02 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1743 | 0 | 0 | 0 | 1743 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235204300 |  | 100348264 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | MAIN | 263 N MAIN ST | 049 | WIN | 2024-12-02 | U126530 | U125763 | 2024-01-10 | 2024-12-31 |  |  | JDUNN | 2024-12-02 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1996.55 | 0 | 0 | 0 | 1996.55 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235204400 |  | 500442150 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | WINN | 38 WINN AV B | 049 | WIN | 2024-11-25 | U126530 | U125763 | 2024-01-10 | 2024-12-31 |  |  | JDUNN | 2024-11-25 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4583.75 | 0 | 0 | 0 | 4583.75 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235204500 |  | 100348601 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | WINN | 42 WINN AV | 049 | WIN | 2024-11-22 | U126530 | U125763 | 2024-01-10 | 2024-12-31 |  |  | JDUNN | 2024-11-22 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 8.5 | 1 | 7511.21 | 636.45 | 0 | 38.31 | 6836.45 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235204600 |  | 100348596 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | WINN | 64 WINN AV | 049 | WIN | 2024-11-19 | U127414 | U125763 | 2024-01-10 | 2024-12-31 |  |  | EDWARD FOX | 2024-11-19 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4984.97 | 0 | 0 | 0 | 4984.97 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235204700 |  | 100348285 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | WINN | 105 WINN AV | 049 | WIN | 2024-11-27 | U126530 | U125763 | 2024-01-10 | 2024-12-31 |  |  | JDUNN | 2024-11-27 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 8.5 | 1 | 3263.91 | 636.44 | 0 | 38.3 | 2589.17 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235204800 |  | 100348289 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | WINN | 125 WINN AV 2 | 049 | WIN | 2024-11-13 | U126604 | U125763 | 2024-01-10 | 2024-12-31 |  |  | WILLIAM FULKS | 2024-11-13 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3327.61 | 0 | 0 | 0 | 3327.61 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235205000 |  | 100348290 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | WINN | 129 WINN AV 1 | 049 | WIN | 2024-11-16 | U126604 | U125763 | 2024-01-10 | 2024-12-31 |  |  | WILLIAM FULKS | 2024-11-16 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3642.99 | 0 | 0 | 0 | 3642.99 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235205100 |  | 100348291 |  | 6748208I | 2293700 |  |  | 566 | EX | ABANDN SL/22026237300 | 2600B | WINN | 135 WINN AV | 049 | WIN | 2024-11-16 | U126604 | U125763 | 2024-01-10 | 2024-12-31 |  |  | WILLIAM FULKS | 2024-11-15 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 567.27 | 0 | 0 | 0 | 567.27 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235205200 |  | 100348587 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | WINN | 148 WINN AV | 049 | WIN | 2024-10-29 | U127414 | U125763 | 2024-01-10 | 2024-12-31 |  |  | EDWARD FOX | 2024-10-29 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3950.82 | 0 | 0 | 0 | 3950.82 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235205300 |  | 100461364 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | WINN | 151 WINN AV 4 | 049 | WIN | 2024-11-20 | U127414 | U125763 | 2024-01-10 | 2024-12-31 |  |  | EDWARD FOX | 2024-11-20 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4614.04 | 0 | 0 | 0 | 4614.04 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235205400 |  | 100348297 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | WINN | 155 WINN AV | 049 | WIN | 2024-11-02 | U126602 | U125763 | 2024-01-10 | 2024-12-31 |  |  | DEREK PAYTON | 2024-11-02 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3789.93 | 0 | 0 | 0 | 3789.93 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235205500 |  | 100348585 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | WINN | 156 WINN AV | 049 | WIN | 2024-11-08 | U127414 | U125763 | 2024-01-10 | 2024-12-31 |  |  | EDWARD FOX | 2024-11-08 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3125.23 | 0 | 0 | 0 | 3125.23 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235205600 |  | 100348577 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | WINN | 170 WINN AV | 049 | WIN | 2024-11-05 | U127414 | U125763 | 2024-01-10 | 2024-12-31 |  |  | EDWARD FOX | 2024-11-05 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2781 | 0 | 0 | 0 | 2781 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235205700 |  | 100348300 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | WINN | 171 WINN AV | 049 | WIN | 2024-11-01 | U126604 | U125763 | 2024-01-10 | 2024-12-31 |  |  | WILLIAM FULKS | 2024-11-01 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3322.83 | 0 | 0 | 0 | 3322.83 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235205800 |  | 100348301 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | WINN | 175 WINN AV | 049 | WIN | 2024-11-09 | U123111 | U125763 | 2024-01-10 | 2024-12-31 |  |  | LYN STAFFORD | 2024-11-09 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 8 | 1 | 6275.93 | 596.69 | 0 | 35.92 | 5643.32 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235206000 |  | 100348575 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | WINN | 176 WINN AV | 049 | WIN | 2024-11-11 | U126604 | U125763 | 2024-01-10 | 2024-12-31 |  |  | WILLIAM FULKS | 2024-11-11 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3320.88 | 0 | 0 | 0 | 3320.88 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235206100 |  | 100348302 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | WINN | 179 WINN AV | 049 | WIN | 2024-11-18 | U126530 | U125763 | 2024-01-10 | 2024-12-31 |  |  | JDUNN | 2024-11-18 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2717.18 | 0 | 0 | 0 | 2717.18 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235206200 |  | 100348559 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | WINN | 205 WINN AV | 049 | WIN | 2024-11-11 | U126604 | U125763 | 2024-01-10 | 2024-12-31 |  |  | WILLIAM FULKS | 2024-11-11 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3742.54 | 0 | 0 | 0 | 3742.54 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235206300 |  | 100348308 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | WINN | 208 WINN AV | 049 | WIN | 2024-11-18 | U126530 | U125763 | 2024-01-10 | 2024-12-31 |  |  | JDUNN | 2024-11-18 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 10 | 1 | 2733.8 | 748.78 | 0 | 45.07 | 1939.95 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24235211100 |  | 100348176 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237300 | 2600B | MUTUAL | 108 MUTUAL AV | 049 | WIN | 2024-10-22 | U126604 | U125763 | 2024-01-10 | 2024-12-31 |  |  | WILLIAM FULKS | 2024-10-22 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1792.05 | 0 | 0 | 0 | 1792.05 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24236122800 |  | 100329296 |  | 6720208G |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | SAINT PHILLIP *HOLD* | 173 SAINT PHILLIP *HOLD* DR | 067 | LEX | 2024-11-06 | U461322 | U135005 | 2024-01-15 | 2024-01-16 | 2024-12-31 |  | STEVE CANOY | 2024-11-06 | 2024-01-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.3833 | 7 | 3351.24 | 376.21 | 0 | 47.17 | 2927.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24247870700 |  | 100282969 |  | 6712228B | 2293665 |  |  | 565 | EX | RPLC SL/22026236900 | 2600B | HAMILTON | 504 S HAMILTON ST | 209 | GEO | 2024-09-09 | U461443 | U125763 | 2024-02-27 | 2024-12-31 |  |  | WILLIAM GRAVES | 2024-09-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2743.35 | 0 | 0 | 0 | 2743.35 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24247870800 |  | 100282973 |  | 6712228B | 2293665 |  |  | 565 | EX | RPLC SL/22026236900 | 2600B | HAMILTON | 512 S HAMILTON ST | 209 | GEO | 2024-09-06 | U461443 | U125763 | 2024-02-27 | 2024-12-31 |  |  | WILLIAM GRAVES | 2024-09-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2023.36 | 0 | 0 | 0 | 2023.36 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24247870900 |  | 100282974 |  | 6712228B | 2293665 |  |  | 565 | EX | RPLC SL/22026236900 | 2600B | HAMILTON | 520 S HAMILTON ST | 209 | GEO | 2024-09-11 | U461443 | U125763 | 2024-02-27 | 2024-12-31 |  |  | WILLIAM GRAVES | 2024-09-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2120.23 | 0 | 0 | 0 | 2120.23 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24247871000 |  | 100282975 |  | 6712228B | 2293665 |  |  | 565 | EX | RPLC SL/22026236900 | 2600B | HAMILTON | 524 S HAMILTON ST | 209 | GEO | 2024-09-10 | U461443 | U125763 | 2024-02-27 | 2024-12-31 |  |  | WILLIAM GRAVES | 2024-09-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2110.23 | 0 | 0 | 0 | 2110.23 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24247871100 |  | 100282981 |  | 6712228B | 2293665 |  |  | 565 | EX | RPLC SL/22026236900 | 2600B | HAMILTON | 527 S HAMILTON ST | 209 | GEO | 2024-09-05 | U126309 | U125763 | 2024-02-27 | 2024-12-31 |  |  | JAMIE LYNN | 2024-09-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3075.16 | 0 | 0 | 0 | 3075.16 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24247871200 |  | 100282976 |  | 6712228B | 2293665 |  |  | 565 | EX | RPLC SL/22026236900 | 2600B | HAMILTON | 528 S HAMILTON ST | 209 | GEO | 2024-09-17 | U461443 | U125763 | 2024-02-27 | 2024-12-31 |  |  | WILLIAM GRAVES | 2024-09-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 4432.47 | 0 | 0 | 0 | 4432.47 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24247871300 |  | 100282977 |  | 6712228B | 2293665 |  |  | 565 | EX | RPLC SL/22026236900 | 2600B | HAMILTON | 530 S HAMILTON ST | 209 | GEO | 2024-09-25 | U126532 | U125763 | 2024-02-27 | 2024-12-31 |  |  | LESLIE SHARON | 2024-09-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2622.04 | 0 | 0 | 0 | 2622.04 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24247871600 |  | 100282799 |  | 6712228B | 2293665 |  |  | 565 | EX | RPLC SL/22026236900 | 2600B | JACKSON | 109 E JACKSON ST | 209 | GEO | 2024-09-16 | U461443 | U125763 | 2024-02-27 | 2024-12-31 |  |  | WILLIAM GRAVES | 2024-09-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3863.81 | 0 | 0 | 0 | 3863.81 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24247871700 |  | 100282800 |  | 6712228B | 2293665 |  |  | 565 | EX | RPLC SL/22026236900 | 2600B | JACKSON | 115 E JACKSON ST | 209 | GEO | 2024-09-05 | U461443 | U125763 | 2024-02-27 | 2024-12-31 |  |  | WILLIAM GRAVES | 2024-09-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2444.13 | 0 | 0 | 0 | 2444.13 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24247871800 |  | 100282801 |  | 6712228B | 2293665 |  |  | 565 | EX | RPLC SL/22026236900 | 2600B | JACKSON | 121 E JACKSON ST | 209 | GEO | 2024-09-05 | U461443 | U125763 | 2024-02-27 | 2024-12-31 |  |  | WILLIAM GRAVES | 2024-09-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2426.63 | 0 | 0 | 0 | 2426.63 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24247871900 |  | 100282802 |  | 6712228B | 2293665 |  |  | 565 | EX | RPLC SL/22026236900 | 2600B | JACKSON | 125 E JACKSON ST | 209 | GEO | 2024-09-19 | U461443 | U125763 | 2024-02-27 | 2024-12-31 |  |  | WILLIAM GRAVES | 2024-09-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3448.78 | 0 | 0 | 0 | 3448.78 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24247872000 |  | 100282803 |  | 6712228B | 2293665 |  |  | 565 | EX | RPLC SL/22026236900 | 2600B | JACKSON | 127 E JACKSON ST | 209 | GEO | 2024-09-26 | U126532 | U125763 | 2024-02-27 | 2024-12-31 |  |  | LESLIE SHARON | 2024-09-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3170.22 | 0 | 0 | 0 | 3170.22 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24247872100 |  | 100282966 |  | 6712228B | 2293665 |  |  | 565 | EX | RPLC SL/22026236900 | 2600B | JACKSON | 200 E JACKSON ST | 209 | GEO | 2024-09-03 | U126309 | U125763 | 2024-02-27 | 2024-12-31 |  |  | JAMIE LYNN | 2024-09-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.86667 | 1 | 2087.83 | 57.92 | 0 | 14.68 | 2015.23 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24248083300 |  | 100240028 |  | 7352264E | 2300016 |  |  | 565 | EX | RPLC SL/23026293500 | 2600B | BEECH | 400 BEECH ST | 089 | RUS | 2024-11-11 | U124015 | U125763 | 2024-02-28 | 2024-12-31 |  |  | ORA SLONE | 2024-11-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2775.64 | 0 | 0 | 0 | 2775.64 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24248083400 |  | 100240027 |  | 7352264E | 2300016 |  |  | 565 | EX | RPLC SL/23026293500 | 2600B | BEECH | 404 BEECH ST | 089 | RUS | 2024-11-11 | U124015 | U125763 | 2024-02-28 | 2024-12-31 |  |  | ORA SLONE | 2024-11-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 4294.5 | 0 | 0 | 0 | 4294.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24248083600 |  | 100240026 |  | 7352264E | 2300016 |  |  | 565 | EX | RPLC SL/23026293500 | 2600B | BEECH | 408 BEECH ST | 089 | RUS | 2024-10-30 | U124015 | U125763 | 2024-02-28 | 2024-12-31 |  |  | ORA SLONE | 2024-10-30 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2063.83 | 0 | 0 | 0 | 2063.83 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24248083700 |  | 100240023 |  | 7352264E | 2300016 |  |  | 565 | EX | RPLC SL/23026293500 | 2600B | BEECH | 418 BEECH ST | 089 | RUS | 2024-10-31 | U124015 | U125763 | 2024-02-28 | 2024-12-31 |  |  | ORA SLONE | 2024-10-31 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2749.85 | 0 | 0 | 0 | 2749.85 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24248084000 |  | 100239964 |  | 7352264E | 2300016 |  |  | 565 | EX | RPLC SL/23026293500 | 2600B | DIVISION | 619 DIVISION ST | 089 | RUS | 2024-10-23 | U124015 | U125763 | 2024-02-28 | 2024-12-31 |  |  | ORA SLONE | 2024-10-23 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1979.18 | 0 | 0 | 0 | 1979.18 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24248084100 |  | 100239961 |  | 7352264E | 2300016 |  |  | 565 | EX | RPLC SL/23026293500 | 2600B | DIVISION | 708 DIVISION ST | 089 | RUS | 2024-10-18 | U124015 | U125763 | 2024-02-28 | 2024-12-31 |  |  | ORA SLONE | 2024-10-18 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3512.95 | 0 | 0 | 0 | 3512.95 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24248084200 |  | 100239960 |  | 7352264E | 2300016 |  |  | 565 | EX | RPLC SL/23026293500 | 2600B | DIVISION | 711 DIVISION ST | 089 | RUS | 2024-10-19 | U124015 | U125763 | 2024-02-28 | 2024-12-31 |  |  | ORA SLONE | 2024-10-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1969.73 | 0 | 0 | 0 | 1969.73 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24248085000 |  | 100240016 |  | 7352264E | 2300016 |  |  | 565 | EX | RPLC SL/23026293500 | 2600B | FERRY | 404 FERRY ST | 089 | RUS | 2024-11-04 | U124015 | U125763 | 2024-02-28 | 2024-12-31 |  |  | ORA SLONE | 2024-11-04 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2306.47 | 0 | 0 | 0 | 2306.47 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24248085100 |  | 100239963 |  | 7352264E | 2300016 |  |  | 565 | EX | RPLC SL/23026293500 | 2600B | GROVE | 106 GROVE ST | 089 | RUS | 2024-10-21 | U124015 | U125763 | 2024-02-28 | 2024-12-31 |  |  | ORA SLONE | 2024-10-21 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2940.55 | 0 | 0 | 0 | 2940.55 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24248085200 |  | 100239966 |  | 7352264E | 2300016 |  |  | 565 | EX | RPLC SL/23026293500 | 2600B | GROVE | 115 GROVE ST | 089 | RUS | 2024-10-23 | U124015 | U125763 | 2024-02-28 | 2024-12-31 |  |  | ORA SLONE | 2024-10-23 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2929.41 | 0 | 0 | 0 | 2929.41 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24248085300 |  | 100239967 |  | 7352264E | 2300016 |  |  | 565 | EX | RPLC SL/23026293500 | 2600B | GROVE | 116 GROVE ST | 089 | RUS | 2024-10-24 | U124015 | U125763 | 2024-02-28 | 2024-12-31 |  |  | ORA SLONE | 2024-10-24 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2666.46 | 0 | 0 | 0 | 2666.46 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24248085400 |  | 100239970 |  | 7352264E | 2300016 |  |  | 565 | EX | RPLC SL/23026293500 | 2600B | GROVE | 119 GROVE ST FRONT | 089 | RUS | 2024-10-24 | U124015 | U125763 | 2024-02-28 | 2024-12-31 |  |  | ORA SLONE | 2024-10-24 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2370.25 | 0 | 0 | 0 | 2370.25 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24248085500 |  | 100239977 |  | 7352264E | 2300016 |  |  | 565 | EX | RPLC SL/23026293500 | 2600B | GROVE | 127 GROVE ST | 089 | RUS | 2024-10-28 | U124015 | U125763 | 2024-02-28 | 2024-12-31 |  |  | ORA SLONE | 2024-10-28 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2373.69 | 0 | 0 | 0 | 2373.69 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24248085600 |  | 100239979 |  | 7352264E | 2300016 |  |  | 565 | EX | RPLC SL/23026293500 | 2600B | GROVE | 133 GROVE ST | 089 | RUS | 2024-10-25 | U124015 | U125763 | 2024-02-28 | 2024-12-31 |  |  | ORA SLONE | 2024-10-25 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1920.7 | 0 | 0 | 0 | 1920.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24248085700 |  | 100239948 |  | 7352264E | 2300016 |  |  | 565 | EX | RPLC SL/23026293500 | 2600B | RIVERSIDE | 625 RIVERSIDE DR | 089 | RUS | 2024-10-22 | U124015 | U125763 | 2024-02-28 | 2024-12-31 |  |  | ORA SLONE | 2024-10-22 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2355.62 | 0 | 0 | 0 | 2355.62 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24248086000 |  | 100239951 |  | 7344268N | 2300016 |  |  | 565 | EX | RPLC SL/23026293500 | 2600B | RIVERSIDE | 709 RIVERSIDE DR | 089 | RUS | 2024-10-15 | U124015 | U125763 | 2024-02-28 | 2024-12-31 |  |  | ORA SLONE | 2024-10-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2038.53 | 0 | 0 | 0 | 2038.53 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24248086100 |  | 100239952 |  | 7352264E | 2300016 |  |  | 565 | EX | RPLC SL/23026293500 | 2600B | RIVERSIDE | 801 RIVERSIDE DR | 089 | RUS | 2024-10-17 | U124015 | U125763 | 2024-02-28 | 2024-12-31 |  |  | ORA SLONE | 2024-10-17 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2828.97 | 0 | 0 | 0 | 2828.97 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24248086200 |  | 100239953 |  | 7352264E | 2300016 |  |  | 565 | EX | RPLC SL/23026293500 | 2600B | RIVERSIDE | 807 RIVERSIDE DR | 089 | RUS | 2024-10-15 | U124015 | U125763 | 2024-02-28 | 2024-12-31 |  |  | ORA SLONE | 2024-10-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1973.25 | 0 | 0 | 0 | 1973.25 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24248086300 |  | 100239954 |  | 7352264E | 2300016 |  |  | 565 | EX | RPLC SL/23026293500 | 2600B | RIVERSIDE | 813 RIVERSIDE DR | 089 | RUS | 2024-10-16 | U124015 | U125763 | 2024-02-28 | 2024-12-31 |  |  | ORA SLONE | 2024-10-16 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2698.25 | 0 | 0 | 0 | 2698.25 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24248086400 |  | 100239955 |  | 7352264E | 2300016 |  |  | 565 | EX | RPLC SL/23026293500 | 2600B | RIVERSIDE | 815 RIVERSIDE DR | 089 | RUS | 2024-10-31 | U124015 | U125763 | 2024-02-28 | 2024-12-31 |  |  | ORA SLONE | 2024-10-16 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1924.14 | 0 | 0 | 0 | 1924.14 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24248086500 |  | 100239957 |  | 7352264E | 2300016 |  |  | 565 | EX | RPLC SL/23026293500 | 2600B | WOODLAWN | 107 WOODLAWN AV | 089 | RUS | 2024-10-18 | U124015 | U125763 | 2024-02-28 | 2024-12-31 |  |  | ORA SLONE | 2024-10-18 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3350.75 | 0 | 0 | 0 | 3350.75 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24248086600 |  | 100239958 |  | 7352264E | 2300016 |  |  | 565 | EX | RPLC SL/23026293500 | 2600B | WOODLAWN | 114 WOODLAWN ST | 089 | RUS | 2024-10-17 | U124015 | U125763 | 2024-02-28 | 2024-12-31 |  |  | ORA SLONE | 2024-10-17 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2677.61 | 0 | 0 | 0 | 2677.61 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24248087200 |  | 100239984 |  | 7352264E | 2300016 |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | DIVISION | 850 DIVISION ST | 089 | RUS | 2025-05-29 | U124604 | U125763 | 2024-02-28 | 2024-12-31 |  |  | MCOLLET | 2025-05-28 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 | 5.1667 | 2 | 1042.3 | 373.95 | 55.6 | 612.75 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24248098300 |  | 100240044 |  | 7352264E | 2300016 |  |  | 565 | EX | RPLC SL/23026293500 | 2600B | FERRY | 402 FERRY ST | 089 | RUS | 2024-11-26 | U128523 | U125763 | 2024-02-28 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-25 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3339.94 | 0 | 0 | 0 | 3339.94 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24248098800 |  | 100239962 |  | 7352264E | 2300016 |  |  | 565 | EX | RPLC SL/23026293500 | 2600B | GROVE | 110 GROVE ST | 089 | RUS | 2024-10-19 | U124015 | U125763 | 2024-02-28 | 2024-12-31 |  |  | ORA SLONE | 2024-10-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 30847.38 | 0 | 28931.09 | 0 | 1916.29 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249656700 |  | 100270575 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | ASHBROOK | 101 ASHBROOK CT | 097 | CYN | 2024-10-24 | U126532 | U125763 | 2024-02-29 | 2024-12-31 |  |  | LESLIE SHARON | 2024-10-24 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4569.83 | 0 | 0 | 0 | 4569.83 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249656800 |  | 100270576 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | ASHBROOK | 103 ASHBROOK CT | 097 | CYN | 2024-10-24 | U126532 | U125763 | 2024-02-29 | 2024-12-31 |  |  | LESLIE SHARON | 2024-10-24 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3605.82 | 0 | 0 | 0 | 3605.82 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249656900 |  | 100270578 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | ASHBROOK | 107 ASHBROOK CT | 097 | CYN | 2024-10-26 | U126285 | U125763 | 2024-02-29 | 2024-12-31 |  |  | DUSTIN DAVIS | 2024-10-26 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 8.75 | 1 | 5542.91 | 707.35 | 0 | 443.03 | 4392.53 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249657000 |  | 100270579 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | ASHBROOK | 109 ASHBROOK CT | 097 | CYN | 2024-10-28 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | JOSH PASLEY | 2024-10-28 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3528.14 | 0 | 0 | 0 | 3528.14 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249657100 |  | 100270586 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | ASHBROOK | 115 ASHBROOK CT | 097 | CYN | 2024-10-25 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-25 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 5.1 | 1 | 8817.93 | 322.42 | 0 | 252.67 | 8242.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249658000 |  | 100270668 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | BATTLE GROVE | 104 BATTLE GROVE AV | 097 | CYN | 2024-10-01 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-01 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3340.43 | 0 | 0 | 0 | 3340.43 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249658100 |  | 100270647 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | BATTLE GROVE | 105 BATTLE GROVE AV | 097 | CYN | 2024-10-01 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-01 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 5.1167 | 1 | 4105.36 | 322.42 | 0 | 252.67 | 3530.27 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249661900 |  | 100270560 |  | 6736252M | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | BRIDGE | 419 E BRIDGE ST | 097 | CYN | 2024-10-12 | U128336 | U125763 | 2024-02-29 | 2024-12-31 |  |  | JOSHUA COX | 2024-10-12 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 3.8833 | 1 | 2694.75 | 250.58 | 0 | 15.35 | 2428.82 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249670700 |  | 100270592 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | OLD LAIR | 109 OLD LAIR RD | 097 | CYN | 2024-10-17 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-17 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2089.68 | 0 | 0 | 0 | 2089.68 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249670800 |  | 100270593 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | OLD LAIR | 111 OLD LAIR RD | 097 | CYN | 2024-10-17 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-17 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3351.38 | 0 | 0 | 0 | 3351.38 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249670900 |  | 100270596 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | OLD LAIR | 115 OLD LAIR RD | 097 | CYN | 2024-10-17 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-17 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 2.8833 | 1 | 2608.87 | 183.33 | 0 | 143.68 | 2281.86 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249671000 |  | 100270597 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | OLD LAIR | 117 OLD LAIR RD | 097 | CYN | 2024-10-17 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-17 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2256.39 | 0 | 0 | 0 | 2256.39 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249671100 |  | 100270598 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | OLD LAIR | 119 OLD LAIR RD | 097 | CYN | 2024-10-16 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-16 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2625.8 | 124.84 | 0 | 94.43 | 2406.53 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249671200 |  | 100270600 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | OLD LAIR | 123 OLD LAIR RD | 097 | CYN | 2024-10-16 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-16 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 5.8 | 2 | 2700.88 | 374.75 | 0 | 155.41 | 2170.72 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249671300 |  | 100270574 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | OLD LAIR | 126 OLD LAIR RD | 097 | CYN | 2024-10-16 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-16 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3513.76 | 0 | 0 | 0 | 3513.76 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249671400 |  | 100270603 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | OLD LAIR | 129 OLD LAIR RD | 097 | CYN | 2024-10-15 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-15 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 3.4333 | 1 | 3274.35 | 218.08 | 0 | 170.93 | 2885.34 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249673300 |  | 100417460 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | SPRINGDALE | 112 SPRINGDALE AV | 097 | CYN | 2024-10-18 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-18 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2964.44 | 0 | 0 | 0 | 2964.44 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249673400 |  | 100410746 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | SPRINGDALE | 114 SPRINGDALE AV | 097 | CYN | 2024-10-18 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-18 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 2.8833 | 1 | 3454.39 | 183.33 | 0 | 143.68 | 3127.38 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249673500 |  | 100270617 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | SPRINGDALE | 116 SPRINGDALE AV | 097 | CYN | 2024-10-22 | U126532 | U125763 | 2024-02-29 | 2024-12-31 |  |  | LESLIE SHARON | 2024-10-21 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4423.13 | 39.61 | 0 | 30.34 | 4353.18 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249673600 |  | 100270616 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | SPRINGDALE | 118 SPRINGDALE AV | 097 | CYN | 2024-10-18 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-18 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2334.59 | 0 | 0 | 0 | 2334.59 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249673700 |  | 100270618 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | SPRINGDALE | 119 SPRINGDALE AV | 097 | CYN | 2024-10-22 | U126532 | U125763 | 2024-02-29 | 2024-12-31 |  |  | LESLIE SHARON | 2024-10-21 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2832.63 | 0 | 0 | 0 | 2832.63 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249673800 |  | 100270615 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | SPRINGDALE | 120 SPRINGDALE AV | 097 | CYN | 2024-10-22 | U126532 | U125763 | 2024-02-29 | 2024-12-31 |  |  | LESLIE SHARON | 2024-10-21 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2103.22 | 0 | 0 | 0 | 2103.22 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249673900 |  | 100270620 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | SPRINGDALE | 121 SPRINGDALE AV A | 097 | CYN | 2024-10-22 | U126532 | U125763 | 2024-02-29 | 2024-12-31 |  |  | LESLIE SHARON | 2024-10-21 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3194.65 | 0 | 0 | 0 | 3194.65 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249674100 |  | 100270614 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | SPRINGDALE | 122 SPRINGDALE AV | 097 | CYN | 2024-10-22 | U126532 | U125763 | 2024-02-29 | 2024-12-31 |  |  | LESLIE SHARON | 2024-10-22 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2434.42 | 0 | 0 | 0 | 2434.42 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249674200 |  | 100270621 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | SPRINGDALE | 123 SPRINGDALE AV | 097 | CYN | 2024-10-22 | U126532 | U125763 | 2024-02-29 | 2024-12-31 |  |  | LESLIE SHARON | 2024-10-22 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2611.42 | 0 | 0 | 0 | 2611.42 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249674600 |  | 100426027 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | SPRINGDALE | 210 SPRINGDALE AV | 097 | CYN | 2024-09-03 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-09-03 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2275.13 | 0 | 0 | 0 | 2275.13 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249674700 |  | 100270892 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | SPRINGDALE | 211 SPRINGDALE AV | 097 | CYN | 2024-09-09 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-09-09 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 5.1 | 1 | 3967.99 | 521.14 | 0 | 497.68 | 2949.17 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249674800 |  | 100270888 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | SPRINGDALE | 212 SPRINGDALE AV | 097 | CYN | 2024-09-09 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-09-05 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3003.17 | 0 | 0 | 0 | 3003.17 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249674900 |  | 100270893 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | SPRINGDALE | 213 SPRINGDALE AV | 097 | CYN | 2024-09-10 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-09-10 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3036.68 | 0 | 0 | 0 | 3036.68 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249675000 |  | 100270800 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | SPRINGDALE | 215 SPRINGDALE AV | 097 | CYN | 2024-09-10 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-09-10 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2291.12 | 0 | 0 | 0 | 2291.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249675100 |  | 100270795 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | SPRINGDALE | 216 SPRINGDALE AV | 097 | CYN | 2024-09-09 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-09-04 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2633.13 | 0 | 0 | 0 | 2633.13 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249675200 |  | 100270794 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | SPRINGDALE | 218 SPRINGDALE AV | 097 | CYN | 2024-09-09 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-09-04 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2604.6 | 0 | 0 | 0 | 2604.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249675300 |  | 100270802 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | SPRINGDALE | 219 SPRINGDALE AV | 097 | CYN | 2024-09-11 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-09-11 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 5.1167 | 1 | 3807.11 | 394.35 | 0 | 384.35 | 3028.41 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249675400 |  | 100270793 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | SPRINGDALE | 220 SPRINGDALE AV | 097 | CYN | 2024-09-13 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-09-13 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 5.0667 | 1 | 4179.11 | 344.9 | 0 | 339 | 3495.21 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249675500 |  | 100270792 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | SPRINGDALE | 222 SPRINGDALE AV | 097 | CYN | 2024-09-12 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-09-12 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4678.29 | 0 | 0 | 0 | 4678.29 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249675600 |  | 100270791 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | SPRINGDALE | 224 SPRINGDALE AV | 097 | CYN | 2024-09-12 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-09-12 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 5.1167 | 1 | 4173.92 | 348.31 | 0 | 342.39 | 3483.22 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249676700 |  | 100270786 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | TOLLIVER | 101 TOLLIVER LN | 097 | CYN | 2024-10-23 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-23 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 2.9 | 1 | 2952.28 | 218.82 | 0 | 173.83 | 2559.63 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249676800 |  | 500079559 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | TOLLIVER | 103 TOLLIVER LN | 097 | CYN | 2024-10-23 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-23 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3335.67 | 0 | 0 | 0 | 3335.67 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249676900 |  | 100270787 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | TOLLIVER | 104 TOLLIVER LN | 097 | CYN | 2024-10-23 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-23 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 5.1 | 1 | 3521.66 | 322.42 | 0 | 252.67 | 2946.57 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249677000 |  | 100270561 |  | 6736252M | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 101 WEBSTER AV | 097 | CYN | 2024-10-11 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-11 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2013.69 | 0 | 0 | 0 | 2013.69 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249677200 |  | 100270562 |  | 6736252M | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 103 WEBSTER AV | 097 | CYN | 2024-09-30 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-09-30 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 3.9167 | 1 | 3310.97 | 268.39 | 0 | 263.81 | 2778.77 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249677300 |  | 100270674 |  | 6736252M | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 104 WEBSTER AV | 097 | CYN | 2024-10-12 | U128336 | U125763 | 2024-02-29 | 2024-12-31 |  |  | JOSHUA COX | 2024-10-12 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 4.1167 | 2 | 3482.93 | 263.44 | 0 | 16.13 | 3203.36 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249677400 |  | 100270563 |  | 6736252M | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 105 WEBSTER AV | 097 | CYN | 2024-09-30 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-09-30 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2639.64 | 0 | 0 | 0 | 2639.64 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249677500 |  | 100270672 |  | 6736252M | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 106 WEBSTER AV | 097 | CYN | 2024-10-11 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-11 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2768.26 | 0 | 0 | 0 | 2768.26 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249677600 |  | 100270564 |  | 6736252M | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 107 WEBSTER AV | 097 | CYN | 2024-10-15 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-15 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4097.52 | 0 | 0 | 0 | 4097.52 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249677700 |  | 100270565 |  | 6736252M | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 109 WEBSTER AV | 097 | CYN | 2024-10-15 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-15 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2563.57 | 0 | 0 | 0 | 2563.57 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249677900 |  | 100270670 |  | 6736252M | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 110 WEBSTER AV | 097 | CYN | 2024-10-12 | U126285 | U125763 | 2024-02-29 | 2024-12-31 |  |  | DUSTIN DAVIS | 2024-10-12 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 8 | 1 | 4436.91 | 539.18 | 0 | 398.41 | 3499.32 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249678000 |  | 100270566 |  | 6736252M | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 111 WEBSTER AV | 097 | CYN | 2024-09-26 | U127414 | U125763 | 2024-02-29 | 2024-12-31 |  |  | EDWARD FOX | 2024-09-26 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3165.04 | 0 | 0 | 0 | 3165.04 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249678100 |  | 100270669 |  | 6736252M | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 112 WEBSTER AV | 097 | CYN | 2024-10-04 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-04 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 5.1 | 1 | 4542.99 | 322.42 | 0 | 252.67 | 3967.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249678200 |  | 100270567 |  | 6736252M | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 113 WEBSTER AV | 097 | CYN | 2024-09-26 | U127414 | U125763 | 2024-02-29 | 2024-12-31 |  |  | EDWARD FOX | 2024-09-26 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3136.74 | 0 | 0 | 0 | 3136.74 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249678300 |  | 100270568 |  | 6736252M | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 115 WEBSTER AV | 097 | CYN | 2024-09-25 | U127414 | U125763 | 2024-02-29 | 2024-12-31 |  |  | EDWRAD FOX | 2024-09-25 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2438.15 | 0 | 0 | 0 | 2438.15 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249678400 |  | 100270641 |  | 6736252M | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 118 WEBSTER AV | 097 | CYN | 2024-09-20 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-09-20 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 2.8833 | 1 | 4222.79 | 198.04 | 0 | 194.68 | 3830.07 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249678500 |  | 100270570 |  | 6736252M | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 119 WEBSTER AV | 097 | CYN | 2024-10-03 | U127414 | U125763 | 2024-02-29 | 2024-12-31 |  |  | EDWRAD FOX | 2024-10-03 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2509.67 | 0 | 0 | 0 | 2509.67 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249678600 |  | 100270640 |  | 6736252M | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 120 WEBSTER AV | 097 | CYN | 2024-09-25 | U127414 | U125763 | 2024-02-29 | 2024-12-31 |  |  | EDWARD FOX | 2024-09-25 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2617.99 | 18.33 | 0 | 19.12 | 2580.54 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249678700 |  | 100270639 |  | 6736252M | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 122 WEBSTER AV | 097 | CYN | 2024-09-25 | U127414 | U125763 | 2024-02-29 | 2024-12-31 |  |  | EDWARD FOX | 2024-09-23 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2280.64 | 0 | 0 | 0 | 2280.64 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249678800 |  | 100270572 |  | 6736252M | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 123 WEBSTER AV | 097 | CYN | 2024-09-19 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-09-19 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2469.87 | 0 | 0 | 0 | 2469.87 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249678900 |  | 100270637 |  | 6736252M | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 124 WEBSTER AV | 097 | CYN | 2024-10-03 | U127414 | U125763 | 2024-02-29 | 2024-12-31 |  |  | EDWARD FOX | 2024-10-03 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2317.05 | 0 | 0 | 0 | 2317.05 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249679000 |  | 100270573 |  | 6736252M | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 125 WEBSTER AV | 097 | CYN | 2024-09-19 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-09-18 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2726.9 | 0 | 0 | 0 | 2726.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249679100 |  | 100270636 |  | 6736252M | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 126 WEBSTER AV | 097 | CYN | 2024-09-19 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-09-19 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 5.1667 | 1 | 3192.1 | 410.95 | 0 | 407.96 | 2373.19 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249679200 |  | 100270635 |  | 6736252M | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 128 WEBSTER AV | 097 | CYN | 2024-09-19 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-09-18 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2995.62 | 0 | 0 | 0 | 2995.62 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249679300 |  | 100270633 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 202 WEBSTER AV | 097 | CYN | 2024-10-16 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-16 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 10.2 | 2 | 3679.19 | 659.03 | 0 | 273.29 | 2746.87 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249679400 |  | 500494735 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 204 WEBSTER AV | 097 | CYN | 2024-09-17 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-09-17 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3222.06 | 0 | 0 | 0 | 3222.06 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249679500 |  | 100270606 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 205 WEBSTER AV | 097 | CYN | 2024-10-02 | U127414 | U125763 | 2024-02-29 | 2024-12-31 |  |  | EDWARD FOX | 2024-10-02 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4923.43 | 0 | 0 | 0 | 4923.43 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249679600 |  | 100270632 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 208 WEBSTER AV | 097 | CYN | 2024-09-17 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-09-17 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 5.0833 | 1 | 4730.45 | 396.51 | 0 | 343.33 | 3990.61 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249679700 |  | 100270609 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 209 WEBSTER AV | 097 | CYN | 2024-10-08 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-08 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2652.26 | 0 | 0 | 0 | 2652.26 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249679800 |  | 100270610 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 211 WEBSTER AV | 097 | CYN | 2024-10-07 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-07 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2934.35 | 0 | 0 | 0 | 2934.35 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249679900 |  | 100270611 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 213 WEBSTER AV | 097 | CYN | 2024-10-07 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-07 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 4.9333 | 1 | 4389.42 | 312.94 | 0 | 245.25 | 3831.23 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249680000 |  | 100270622 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 301 WEBSTER AV | 097 | CYN | 2024-10-22 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-22 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 5.1 | 1 | 2972.72 | 322.42 | 0 | 252.67 | 2397.63 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249680100 |  | 100270797 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 302 WEBSTER AV | 097 | CYN | 2024-09-17 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-09-16 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2866.19 | 0 | 0 | 0 | 2866.19 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249680200 |  | 100270623 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 303 WEBSTER AV | 097 | CYN | 2024-10-09 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-09 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2421.3 | 0 | 0 | 0 | 2421.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249680300 |  | 100270625 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 305 WEBSTER AV | 097 | CYN | 2024-10-09 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-09 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 2.8833 | 1 | 4116.21 | 183.33 | 0 | 143.68 | 3789.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249687300 |  | 100270605 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | OLD LAIR | 131 OLD LAIR RD | 097 | CYN | 2024-10-15 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-15 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 3.9667 | 1 | 3105.54 | 249.76 | 0 | 195.71 | 2660.07 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249687500 |  | 100270613 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | SPRINGDALE | 124 SPRINGDALE AV | 097 | CYN | 2024-10-19 | U126532 | U125763 | 2024-02-29 | 2024-12-31 |  |  | LESLIE SHARON | 2024-10-19 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 8 | 2 | 4536.09 | 520.8 | 0 | 397.28 | 3618.01 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249687600 |  | 100270796 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | SPRINGDALE | 214 SPRINGDALE AV | 097 | CYN | 2024-09-09 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-09-06 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4124.15 | 0 | 0 | 0 | 4124.15 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249687700 |  | 100270569 |  | 6736252M | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 117 WEBSTER AV | 097 | CYN | 2024-09-25 | U127414 | U125763 | 2024-02-29 | 2024-12-31 |  |  | EDWARD FOX | 2024-09-23 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2629.43 | 0 | 0 | 0 | 2629.43 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249687800 |  | 100270612 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 215 WEBSTER AV | 097 | CYN | 2024-10-08 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-08 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 5.95 | 2 | 4315.4 | 376.18 | 0 | 294.79 | 3644.43 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24249687900 |  | 100270627 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | WEBSTER | 309 WEBSTER AV | 097 | CYN | 2024-10-10 | U126284 | U125763 | 2024-02-29 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-10 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 2.8833 | 1 | 3367.2 | 183.33 | 0 | 143.68 | 3040.19 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24249701600 |  | 500363818 |  | 6700224L | 2293724 |  |  | 565 | EX | RPLC SL/22026238401 | 2600B | 1ST | 321 1ST ST | 239 | MID | 2024-10-25 | U128816 | U125763 | 2024-02-29 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-10-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3351.66 | 0 | 0 | 0 | 3351.66 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24249701800 |  | 100344647 |  | 6700224L | 2293724 |  |  | 565 | EX | RPLC SL/22026238401 | 2600B | 1ST | 325 1ST ST | 239 | MID | 2024-10-23 | U461443 | U125763 | 2024-02-29 | 2024-12-31 |  |  | WILLIAM GRAVES | 2024-10-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2802.63 | 0 | 0 | 0 | 2802.63 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24249702000 |  | 100344650 |  | 6700224L | 2293724 |  |  | 565 | EX | RPLC SL/22026238401 | 2600B | 1ST | 337 1ST ST | 239 | MID | 2024-10-23 | U461443 | U125763 | 2024-02-29 | 2024-12-31 |  |  | WILLIAM GRAVES | 2024-10-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2836.17 | 0 | 0 | 0 | 2836.17 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24249702100 |  | 100344666 |  | 6700224L | 2293724 |  |  | 565 | EX | RPLC SL/22026238401 | 2600B | 1ST | 338 1ST ST | 239 | MID | 2024-10-26 | U128816 | U125763 | 2024-02-29 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-10-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 4600.05 | 0 | 0 | 0 | 4600.05 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24249702200 |  | 100344651 |  | 6700224L | 2293724 |  |  | 565 | EX | RPLC SL/22026238401 | 2600B | 1ST | 351 1ST ST | 239 | MID | 2024-10-24 | U461443 | U125763 | 2024-02-29 | 2024-12-31 |  |  | WILLIAM GRAVES | 2024-10-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 4013 | 0 | 0 | 0 | 4013 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24249702300 |  | 100344669 |  | 6700224L | 2293724 |  |  | 565 | EX | RPLC SL/22026238401 | 2600B | 1ST | 355 1ST ST | 239 | MID | 2024-11-07 | U128816 | U125763 | 2024-02-29 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-11-07 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3602.79 | 0 | 0 | 0 | 3602.79 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24249702400 |  | 100344645 |  | 6700224K | 2293724 |  |  | 565 | EX | RPLC SL/22026238401 | 2600B | 2ND | 308 2ND ST | 239 | MID | 2024-10-17 | U128816 | U125763 | 2024-02-29 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-10-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3461.36 | 0 | 0 | 0 | 3461.36 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24249702500 |  | 100344624 |  | 6700224K | 2293724 |  |  | 565 | EX | RPLC SL/22026238401 | 2600B | 2ND | 309 2ND ST | 239 | MID | 2024-10-17 | U128816 | U125763 | 2024-02-29 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-10-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 4115.37 | 0 | 0 | 0 | 4115.37 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24249702700 |  | 100344644 |  | 6700224K | 2293724 |  |  | 565 | EX | RPLC SL/22026238401 | 2600B | 2ND | 310 2ND ST | 239 | MID | 2024-10-21 | U128816 | U125763 | 2024-02-29 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-10-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 5618.07 | 0 | 0 | 0 | 5618.07 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24249702800 |  | 100344629 |  | 6700224K | 2293724 |  |  | 565 | EX | RPLC SL/22026238401 | 2600B | 2ND | 321 2ND ST | 239 | MID | 2024-10-18 | U128816 | U125763 | 2024-02-29 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-10-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3183.67 | 0 | 0 | 0 | 3183.67 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24249702900 |  | 100344639 |  | 6700224K | 2293724 |  |  | 565 | EX | RPLC SL/22026238401 | 2600B | 2ND | 330 2ND ST | 239 | MID | 2024-10-23 | U128816 | U125763 | 2024-02-29 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-10-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2485.89 | 0 | 0 | 0 | 2485.89 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24249703000 |  | 100344638 |  | 6700224K | 2293724 |  |  | 565 | EX | RPLC SL/22026238401 | 2600B | 2ND | 334 2ND ST | 239 | MID | 2024-10-22 | U128816 | U125763 | 2024-02-29 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-10-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2115.06 | 0 | 0 | 0 | 2115.06 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24249703100 |  | 100344632 |  | 6700224K | 2293724 |  |  | 565 | EX | RPLC SL/22026238401 | 2600B | 2ND | 335 2ND ST | 239 | MID | 2024-10-23 | U128816 | U125763 | 2024-02-29 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-10-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2382.66 | 0 | 0 | 0 | 2382.66 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24249703200 |  | 100344637 |  | 6700224K | 2293724 |  |  | 565 | EX | RPLC SL/22026238401 | 2600B | 2ND | 342 2ND ST | 239 | MID | 2024-10-22 | U128816 | U125763 | 2024-02-29 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-10-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3188.16 | 0 | 0 | 0 | 3188.16 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24249703300 |  | 100344636 |  | 6700224L | 2293724 |  |  | 565 | EX | RPLC SL/22026238401 | 2600B | 2ND | 404 2ND ST | 239 | MID | 2024-10-29 | U128816 | U125763 | 2024-02-29 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-10-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 6452.74 | 0 | 0 | 0 | 6452.74 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24249707300 |  | 100344686 |  | 6700224K | 2293724 |  |  | 565 | EX | RPLC SL/22026238401 | 2600B | WINTER | 226 N WINTER ST | 239 | MID | 2024-11-14 | U128816 | U125763 | 2024-02-29 | 2025-01-11 | 2026-07-31 |  | OLIVER MAYNARD | 2024-11-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3828.97 | 0 | 0 | 0 | 3828.97 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24249707400 |  | 100344684 |  | 6700224L | 2293724 |  |  | 565 | EX | RPLC SL/22026238401 | 2600B | WINTER | 246 N WINTER ST | 239 | MID | 2024-10-16 | U128816 | U125763 | 2024-02-29 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-10-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 4639.36 | 0 | 0 | 0 | 4639.36 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24249707500 |  | 100344683 |  | 6700224L | 2293724 |  |  | 565 | EX | RPLC SL/22026238401 | 2600B | WINTER | 250 N WINTER ST | 239 | MID | 2024-10-16 | U128816 | U125763 | 2024-02-29 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-10-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3137.23 | 0 | 0 | 0 | 3137.23 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24249707600 |  | 100344682 |  | 6700224L | 2293724 |  |  | 565 | EX | RPLC SL/22026238401 | 2600B | WINTER | 256 N WINTER ST | 239 | MID | 2024-10-15 | U128816 | U125763 | 2024-02-29 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-10-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1998.5 | 0 | 0 | 0 | 1998.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24249708700 |  | 100344672 |  | 6700224L | 2293724 |  |  | 566 | EX | ABANDN SL/22026238401 | 2600B | WINTER | 409 N WINTER ST | 239 | MID | 2024-12-03 | U128816 | U125763 | 2024-02-29 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-12-03 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 520.03 | 0 | 0 | 0 | 520.03 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24249711100 |  | 100344652 |  | 6700224L | 2293724 |  |  | 565 | EX | RPLC SL/22026238401 | 2600B | 1ST | 314 1ST ST | 239 | MID | 2024-10-24 | U128816 | U125763 | 2024-02-29 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-10-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3314.99 | 0 | 0 | 0 | 3314.99 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24249711300 |  | 100453793 |  | 6700224L | 2293724 |  |  | 565 | EX | RPLC SL/22026238401 | 2600B | 1ST | 318 1ST ST | 239 | MID | 2024-10-19 | U123111 | U125763 | 2024-02-29 | 2024-12-31 |  |  | LYN STAFFORD | 2024-10-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 1 | 4663.25 | 495.48 | 0 | 30.37 | 4137.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24249711400 |  | 100344648 |  | 6700224L | 2293724 |  |  | 565 | EX | RPLC SL/22026238401 | 2600B | 1ST | 329 1ST ST | 239 | MID | 2024-10-26 | U126532 | U125763 | 2024-02-29 | 2024-12-31 |  |  | LESLIE SHARON | 2024-10-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 5792.43 | 0 | 0 | 0 | 5792.43 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24252341300 |  | 100288346 |  | 6720212H | 1635077 |  |  | 565 | EX | AOC L1 Atmos Corr Remediate | 2621D | STONEHAVEN | 582 STONEHAVEN DR | 067 | LEX | 2025-06-18 | U130722 | AOC SYST | 2024-03-14 | 2025-12-31 | 2024-05-13 |  | SSHIMFE | 2025-06-17 | 2024-07-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 18.25 | 4 | 998.29 | 942.24 | 0 | 56.05 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253082800 |  | 100329328 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24-0263167-00 | 2600B | COBURN | 2201 COBURN BV | 067 | LEX | 2024-11-04 | U461322 | U141460 | 2024-03-19 | 2024-12-20 |  |  | STEVE CANOY | 2024-11-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.2833 | 1 | 5442.19 | 275.71 | 0 | 16.6 | 5149.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253084600 |  | 100329326 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24-0263167-00 | 2600B | COBURN | 2205 COBURN BV 1 | 067 | LEX | 2024-11-01 | U461322 | U141460 | 2024-03-19 | 2024-12-20 |  |  | STEVE CANOY | 2024-11-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 4964.43 | 678.7 | 0 | 276.35 | 4009.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253087400 |  | 100329319 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | COBURN | 2209 COBURN BV 1 | 067 | LEX | 2024-10-31 | U461322 | U141460 | 2024-03-19 | 2024-12-20 |  |  | STEVE CANOY | 2024-10-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.5667 | 1 | 4370.97 | 0 | 0 | 0 | 4370.97 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253087800 |  | 100329313 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | COBURN | 2213 COBURN BV | 067 | LEX | 2024-10-30 | U461322 | U141460 | 2024-03-19 | 2024-12-20 |  |  | STEVE CANOY | 2024-10-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.28333 | 1 | 3680.38 | 19.14 | 0 | 1.18 | 3660.06 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253088100 |  | 100457419 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | COBURN | 2222 COBURN BV | 067 | LEX | 2024-09-20 | U128762 | U141460 | 2024-03-19 | 2024-12-20 |  |  | RANDALL TINCHER | 2024-09-19 | 2024-09-19 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.1667 | 1 | 3116.57 | 317.22 | 0 | 18.08 | 2781.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253097000 |  | 100329586 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | SAINT MATHILDA | 2042 SAINT MATHILDA DR | 067 | LEX | 2024-11-05 | U126284 | U141460 | 2024-03-19 | 2024-12-20 |  |  | JOSH PASLEY | 2024-11-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 4382.49 | 638.72 | 0 | 137.46 | 3606.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253108200 |  | 100329454 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | SAINT MATHILDA | 2124 SAINT MATHILDA DR | 067 | LEX | 2024-09-06 | U128762 | U141460 | 2024-03-19 | 2024-12-20 |  |  | RANDALL TINCHER | 2024-09-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1856.25 | 0 | 0 | 0 | 1856.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253108700 |  | 100329455 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | SAINT MATHILDA | 2128 SAINT MATHILDA DR | 067 | LEX | 2024-09-12 | U128762 | U141460 | 2024-03-19 | 2024-12-20 |  |  | RANDALL TINCHER | 2024-09-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3038.22 | 0 | 0 | 0 | 3038.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253108900 |  | 100329443 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | SAINT MATHILDA | 2129 SAINT MATHILDA DR | 067 | LEX | 2024-09-05 | U128762 | U141460 | 2024-03-19 | 2024-12-20 |  |  | RANDALL TINCHER | 2024-09-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2391.64 | 0 | 0 | 0 | 2391.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253111500 |  | 100329435 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | SAINT MATHILDA | 2135 SAINT MATHILDA DR | 067 | LEX | 2024-09-05 | U128762 | U141460 | 2024-03-19 | 2024-12-20 |  |  | RANDALL TINCHER | 2024-09-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4166.43 | 0 | 0 | 0 | 4166.43 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253112000 |  | 100329434 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | SAINT MATHILDA | 2139 SAINT MATHILDA DR | 067 | LEX | 2024-09-12 | U128762 | U141460 | 2024-03-19 | 2024-12-20 |  |  | RANDALL TINCHER | 2024-09-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3466.52 | 0 | 0 | 0 | 3466.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253112400 |  | 100329432 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | SAINT MATHILDA | 2140 SAINT MATHILDA DR | 067 | LEX | 2024-09-16 | U128762 | U141460 | 2024-03-19 | 2024-12-20 |  |  | RANDALL TINCHER | 2024-09-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2742.75 | 0 | 0 | 0 | 2742.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253112700 |  | 100329433 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | SAINT MATHILDA | 2143 SAINT MATHILDA DR | 067 | LEX | 2024-09-12 | U128762 | U141460 | 2024-03-19 | 2024-12-20 |  |  | RANDALL TINCHER | 2024-09-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1941.1 | 0 | 0 | 0 | 1941.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253113400 |  | 100329281 |  | 6720208G | 2403558 |  |  | 566 | EX | ABANDN SL/24-0263167-00 | 2600B | SAINT PHILLIP | 118 SAINT PHILLIP DR | 067 | LEX | 2024-09-27 | U128762 | U141460 | 2024-03-19 | 2024-12-20 |  |  | RANDALL TINCHER | 2024-09-26 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1094.54 | 0 | 0 | 0 | 1094.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253114100 |  | 100329282 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | SAINT PHILLIP | 122 SAINT PHILLIP DR | 067 | LEX | 2024-09-24 | U128762 | U141460 | 2024-03-19 | 2024-12-20 |  |  | RANDALL TINCHER | 2024-09-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2970.53 | 0 | 0 | 0 | 2970.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253114700 |  | 100329309 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | SAINT PHILLIP | 125 SAINT PHILLIP DR | 067 | LEX | 2024-10-02 | U461322 | U141460 | 2024-03-19 | 2024-12-20 |  |  | STEVE CANOY | 2024-10-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.9333 | 1 | 6728.46 | 337.22 | 0 | 245.83 | 6145.41 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253115200 |  | 100329283 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | SAINT PHILLIP | 126 SAINT PHILLIP DR | 067 | LEX | 2024-09-18 | U128762 | U141460 | 2024-03-19 | 2024-12-20 |  |  | RANDALL TINCHER | 2024-09-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3237.58 | 0 | 0 | 0 | 3237.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253116600 |  | 100329284 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | SAINT PHILLIP | 130 SAINT PHILLIP DR | 067 | LEX | 2024-11-05 | U461322 | U141460 | 2024-03-19 | 2024-12-20 |  |  | STEVE CANOY | 2024-11-05 | 2024-11-02 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.1167 | 2 | 4785.43 | 1031.62 | 0 | 420.07 | 3333.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253117200 |  | 100329285 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | SAINT PHILLIP | 134 SAINT PHILLIP DR | 067 | LEX | 2024-10-03 | U461322 | U141460 | 2024-03-19 | 2024-12-20 |  |  | STEVE CANOY | 2024-10-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.95 | 1 | 1987.06 | 67.06 | 0 | 48.87 | 1871.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253118900 |  | 100329286 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | SAINT PHILLIP | 138 SAINT PHILLIP DR | 067 | LEX | 2024-10-01 | U461322 | U141460 | 2024-03-19 | 2024-12-20 |  |  | STEVE CANOY | 2024-10-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.5667 | 1 | 2977.47 | 381.67 | 0 | 278.22 | 2317.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253119200 |  | 100329304 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | SAINT PHILLIP | 141 SAINT PHILLIP DR | 067 | LEX | 2024-11-05 | U461322 | U141460 | 2024-03-19 | 2024-12-20 |  |  | STEVE CANOY | 2024-11-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.15 | 1 | 4092.39 | 349.54 | 0 | 142.35 | 3600.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253119600 |  | 100329287 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | SAINT PHILLIP | 142 SAINT PHILLIP DR | 067 | LEX | 2024-09-23 | U128762 | U141460 | 2024-03-19 | 2024-12-20 |  |  | RANDALL TINCHER | 2024-09-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2002.21 | 0 | 0 | 0 | 2002.21 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253120000 |  | 100329303 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | SAINT PHILLIP | 145 SAINT PHILLIP DR | 067 | LEX | 2024-11-06 | U461322 | U141460 | 2024-03-19 | 2024-12-20 |  |  | STEVE CANOY | 2024-11-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.7667 | 1 | 4604.98 | 828.01 | 0 | 337.16 | 3439.81 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253120400 |  | 100329288 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | SAINT PHILLIP | 146 SAINT PHILLIP DR | 067 | LEX | 2024-10-28 | U461322 | U141460 | 2024-03-19 | 2024-12-20 |  |  | STEVE CANOY | 2024-10-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.25 | 1 | 2310.69 | 155.97 | 0 | 113.69 | 2041.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253120700 |  | 100329302 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | SAINT PHILLIP | 149 SAINT PHILLIP DR | 067 | LEX | 2024-10-29 | U461322 | U141460 | 2024-03-19 | 2024-12-20 |  |  | STEVE CANOY | 2024-10-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.3 | 1 | 4610.47 | 499.3 | 0 | 363.99 | 3747.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253121200 |  | 100329301 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | SAINT PHILLIP | 153 SAINT PHILLIP DR | 067 | LEX | 2024-10-28 | U461322 | U141460 | 2024-03-19 | 2024-12-20 |  |  | STEVE CANOY | 2024-10-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.7167 | 1 | 3752.29 | 389.9 | 0 | 284.21 | 3078.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253122000 |  | 100329290 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | SAINT PHILLIP | 154 SAINT PHILLIP DR | 067 | LEX | 2024-10-12 | U461322 | U141460 | 2024-03-19 | 2024-10-11 |  |  | STEVE CANOY | 2024-10-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.3 | 2 | 3146.95 | 429.54 | 0 | 313.14 | 2404.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253122600 |  | 100329300 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | SAINT PHILLIP | 157 SAINT PHILLIP DR | 067 | LEX | 2024-10-30 | U461322 | U141460 | 2024-03-19 | 2024-12-20 |  |  | STEVE CANOY | 2024-10-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.2833 | 1 | 5064.44 | 292.76 | 0 | 17.93 | 4753.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253122800 |  | 100329291 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | SAINT PHILLIP | 158 SAINT PHILLIP DR | 067 | LEX | 2024-10-29 | U461322 | U141460 | 2024-03-19 | 2024-12-20 |  |  | STEVE CANOY | 2024-10-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.3167 | 1 | 2771.38 | 90.97 | 0 | 66.32 | 2614.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253123000 |  | 100329299 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | SAINT PHILLIP | 161 SAINT PHILLIP DR | 067 | LEX | 2024-10-30 | U461322 | U141460 | 2024-03-19 | 2024-12-20 |  |  | STEVE CANOY | 2024-10-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.3 | 1 | 2779.47 | 363.91 | 0 | 22.29 | 2393.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253123500 |  | 100329292 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | SAINT PHILLIP | 162 SAINT PHILLIP DR | 067 | LEX | 2024-10-31 | U461322 | U141460 | 2024-03-19 | 2024-12-20 |  |  | STEVE CANOY | 2024-10-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.9167 | 1 | 2165.45 | 0 | 0 | 0 | 2165.45 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253123600 |  | 100329298 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | SAINT PHILLIP | 165 SAINT PHILLIP DR | 067 | LEX | 2024-11-04 | U461322 | U141460 | 2024-03-19 | 2024-12-20 |  |  | STEVE CANOY | 2024-11-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.5 | 1 | 3213.61 | 464.92 | 0 | 28 | 2720.69 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253124200 |  | 100329293 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | SAINT PHILLIP | 166 SAINT PHILLIP DR | 067 | LEX | 2024-09-16 | U124604 | U141460 | 2024-03-19 | 2024-12-20 |  |  | JOCHOA | 2024-09-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.0667 | 3 | 1813.18 | 1348.13 | 331.92 | 76.89 | 56.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24253124500 |  | 100329297 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/ 24-0263167-00 | 2600B | SAINT PHILLIP | 169 SAINT PHILLIP DR | 067 | LEX | 2024-11-04 | U461322 | U141460 | 2024-03-19 | 2024-12-20 |  |  | STEVE CANOY | 2024-11-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.7167 | 1 | 2777.15 | 149.35 | 0 | 8.99 | 2618.81 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24256161000 |  | 100453717 |  | 6720212G | 1635077 |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2621D | NEW CIRCLE | 447 E NEW CIRCLE RD | 067 | LEX | 2025-06-17 | U124604 | AOC SYST | 2024-04-01 | 2025-12-31 | 2027-04-01 |  | SSHIMFE | 2025-06-16 | 2025-06-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 17.8167 | 3 | 4248.94 | 963.81 | 0 | 56.53 | 3228.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24256699400 |  | 100288954 |  | 6724212A | 1635077 |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2621D | NORTHSIDE | 601 NORTHSIDE DR | 067 | LEX | 2024-10-11 | MCRAIG | AOC SYST | 2024-04-04 | 2025-12-31 | 2025-12-31 |  | MCRAIG | 2024-10-11 | 2024-07-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 18.5833 | 4 | 1185.65 | 1163.96 | 165.79 | -144.1 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24257103900 |  | 100288870 |  | 6720212D | 1635077 |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2621D | WAYLAND | 1841 WAYLAND DR | 067 | LEX | 2025-03-17 | TROE | AOC SYST | 2024-04-08 | 2025-12-31 | 2025-12-31 |  | TROE | 2025-03-17 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 16 | 2 | 1824.94 | 1112.27 | 539.43 | 65.2 | 108.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24257248100 |  | 100291571 |  | 6720216G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | EDEN | 649 EDEN RD | 067 | LEX | 2025-03-24 | U124604 | U123688 | 2024-04-09 | 2024-12-31 |  |  | HSTANFI | 2025-03-21 | 2025-03-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 22.4667 | 5 | 1743.24 | 1345.97 | 195.51 | 78.92 | 122.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24258571000 |  | 100292878 |  | 6720216K | 1635077 |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2621D | RADCLIFFE | 633 RADCLIFFE RD | 067 | LEX | 2025-02-25 | U124604 | AOC SYST | 2024-04-16 | 2025-12-31 | 2025-12-31 |  | TROE | 2025-02-24 | 2024-07-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 17.35 | 5 | 1441.34 | 1142.21 | 245.1 | 54.03 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24259981500 |  | 100356254 |  | 7256280J |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | TERRE HAUTE | 840 TERRE HAUTE DR | 161 | MAY | 2024-09-19 | U124604 | U137009 | 2024-04-22 | 2024-12-23 | 2024-12-25 |  | SDADAMS | 2024-09-18 | 2024-08-09 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 | 30.5 | 8 | 2576.53 | 2032.33 | 429.75 | 114.45 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24260020900 |  | 100293216 |  | 6720216K | 1635077 |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2621D | RADCLIFFE | 521 RADCLIFFE RD | 067 | LEX | 2024-09-09 | TROE | AOC SYST | 2024-04-22 | 2024-10-22 | 2025-12-31 |  | TROE | 2024-09-09 | 2024-07-31 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 16.3167 | 3 | 1349.69 | 913.47 | 383.94 | 52.28 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24260028500 |  | 100409717 |  | 6720216G | 1635077 |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2621D | RUSSELL CAVE | 1836 RUSSELL CAVE RD | 067 | LEX | 2024-09-16 | TROE | AOC SYST | 2024-04-22 | 2025-12-31 | 2025-12-31 |  | TROE | 2024-09-16 | 2024-07-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 15.35 | 3 | 2067.98 | 1072.46 | 252.45 | 61.41 | 681.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24260606500 |  | 100448534 |  | 6716220A | 1635077 |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2621D | ADIOS | 2804 ADIOS CT | 067 | LEX | 2025-03-13 | U124604 | AOC SYST | 2024-04-24 | 2025-12-31 | 2025-12-31 |  | JGILES | 2025-03-12 | 2024-08-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 42.4333 | 7 | 4062.68 | 2395.66 | 122.31 | 1373.03 | 171.68 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24260739300 |  | 100246598 |  | 7356256M |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | KIMBERLY | 3616 KIMBERLY CT | 019 | ASH | 2024-12-20 | ABHATFIE | U137009 | 2024-04-25 | 2024-10-24 | 2026-04-30 |  | ABHATFIE | 2024-12-20 | 2024-07-24 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 31.3333 | 8 | 2599.36 | 2213.12 | 0 | 258.96 | 127.28 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24261489000 |  | 100273185 |  | 6680224D | 1635077 |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2623D | WOODHILL | 259 WOODHILL LN 1 | 073 | FRA | 2024-10-12 | U123688 | AOC SYST | 2024-04-29 | 2024-10-29 | 2026-04-30 |  | LSTANFI | 2024-10-10 | 2024-10-10 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 | KYACA |  | 100 | 056532B26230021 | 15.3833 | 2 | 1501.66 | 922.79 | 669.01 | -141.94 | 51.8 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24262444800 |  | 100246898 |  | 7356256M |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | ROBIN LYNN | 3414 ROBIN LYNN DR | 019 | ASH | 2024-09-17 | MCOLLET | U137009 | 2024-05-01 | 2024-12-31 |  |  | MCOLLET | 2024-09-17 | 2024-09-17 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 38.6833 | 4 | 8972.1 | 2719.72 | 379.61 | 1751.65 | 4121.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24262934500 |  | 100273287 |  | 6680224H |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HAWTHORNE | 230 HAWTHORNE DR | 073 | FRA | 2024-10-08 | ATWILLI | U123688 | 2024-05-03 | 2024-11-01 | 2026-05-31 |  | ATWILLI | 2024-10-08 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 16.5333 | 2 | 1657.66 | 1041.53 | 219.82 | 396.31 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24262935400 |  | 100273159 |  | 6680224H |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | GLENWOOD | 205 GLENWOOD PL | 073 | FRA | 2024-10-07 | ATWILLI | U123688 | 2024-05-03 | 2024-11-01 | 2026-05-31 |  | ATWILLI | 2024-10-07 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 16 | 2 | 1675.82 | 951.84 | 300.3 | 423.68 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24262963100 |  | 100278252 |  | 6688228B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D221463 | 2621P | PAIUTE | 504 PAIUTE TL | 073 | FRA | 2024-10-09 | DCOLLIN | U123688 | 2024-05-03 | 2024-11-01 | 2026-05-31 |  | DCOLLIN | 2024-10-09 | 2024-10-07 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 22.8 | 6 | 1618.06 | 1501.45 | 222.66 | -215.57 | 109.52 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24263174500 |  | 100273214 |  | 6680224D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333170 | 2621P | COLDSTREAM | 227 COLDSTREAM DR | 073 | FRA | 2024-10-24 | LSTANFI | U125208 | 2024-05-06 | 2024-11-01 | 2026-05-31 |  | LSTANFI | 2024-10-24 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 18.65 | 3 | 1007.68 | 968.58 | 110.59 | -71.49 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24264594300 |  | 100279534 |  | 6688228O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333174 | 2621P | PRADERO | 1104 PRADERO DR | 073 | FRA | 2024-10-16 | LSTANFI | U123688 | 2024-05-13 | 2024-11-08 | 2026-05-31 |  | LSTANFI | 2024-10-16 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 21.8 | 3 | 1287.69 | 1116.88 | 0 | 45.01 | 125.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24265271600 |  | 100272622 |  | 6684224A | 1635077 |  |  | 565 | EX | REPLACE SL/ LEAKAGE D333226 | 2623D | BELVOIR | 934 BELVOIR DR | 073 | FRA | 2024-10-22 | U124604 | AOC SYST | 2024-05-16 | 2024-11-15 | 2026-05-31 |  | LSTANFI | 2024-10-21 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 | KYACA |  | 100 | 056532B26230021 | 18.85 | 3 | 1053.4 | 981.08 | 181.07 | -108.75 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24265452900 |  | 100246742 |  | 7356256I |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MONROE | 2746 MONROE ST | 019 | ASH | 2024-09-19 | MCOLLET | U137009 | 2024-05-17 | 2024-11-15 | 2026-05-31 |  | MCOLLET | 2024-09-19 | 2024-08-19 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 30.3333 | 7 | 4897.91 | 2138.89 | 352.67 | 2406.35 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24265453700 |  | 100246640 |  | 7356256I |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | ADAMS | 2420 ADAMS ST | 019 | ASH | 2024-09-10 | MCOLLET | U137009 | 2024-05-17 | 2024-11-15 | 2026-05-31 |  | MCOLLET | 2024-09-10 | 2024-09-10 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 21.15 | 3 | 3386.14 | 1478.15 | 182.93 | 1725.06 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24265802300 |  | 100403744 |  | 6684224A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BELVOIR | 953 BELVOIR DR | 073 | FRA | 2024-10-22 | U124604 | U123688 | 2024-05-20 | 2024-11-15 | 2026-05-31 |  | LSTANFI | 2024-10-21 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.3 | 3 | 409.86 | 172.13 | 256.82 | -19.09 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24265835100 |  | 100272644 |  | 6684224A | 1635077 |  |  | 565 | EX | REPLACE SERVICE LINE -LEAKAGE | 2623D | BROOKHAVEN | 922 BROOKHAVEN DR | 073 | FRA | 2024-10-01 | DCOLLIN | AOC SYST | 2024-05-20 | 2024-11-20 | 2026-05-31 |  | DCOLLIN | 2024-10-01 | 2024-09-30 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 | KYACA |  | 100 | 056532B26230021 | 36.2833 | 5 | 3223.01 | 2309.77 | 222.22 | -157.48 | 848.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24265836200 |  | 100272906 |  | 6684224B | 1635077 |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2623D | REED | 506 REED DR | 073 | FRA | 2024-10-22 | U128410 | AOC SYST | 2024-05-20 | 2025-12-31 | 2025-12-31 |  | CDESPAIN | 2024-10-22 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 16 | 2 | 4139.44 | 1043.75 | 483.75 | 63.94 | 2548 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24265836900 |  | 100337934 |  | 6712220M | 1635077 |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2621D | LEESTOWN | 3895 LEESTOWN RD | 067 | LEX | 2025-01-28 | MCRAIG | AOC SYST | 2024-05-20 | 2025-12-31 | 2025-12-31 |  | MCRAIG | 2025-01-28 | 2024-08-29 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 26.5833 | 4 | 2926.62 | 1444.74 | 245.69 | 452.63 | 783.56 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24266301900 |  | 100272912 |  | 6684224B |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | REED | 421 REED DR | 073 | FRA | 2024-10-29 | U124604 | U123688 | 2024-05-22 | 2024-11-20 | 2026-05-31 |  | KKINDER | 2024-10-28 | 2024-10-18 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 20.4833 | 4 | 1671.68 | 1190.7 | 408.04 | 72.94 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24266304200 |  | 100272643 |  | 6684224A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BROOKHAVEN | 928 BROOKHAVEN DR | 073 | FRA | 2024-10-01 | DCOLLIN | U123688 | 2024-05-22 | 2024-11-20 | 2026-05-31 |  | DCOLLIN | 2024-10-01 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.1 | 3 | 291.44 | 76.09 | 221.44 | -6.09 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24266364400 |  | 100293614 |  | 6720212B | 1635077 |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2621D | BALLPARK | 313 BALLPARK DR 101 | 067 | LEX | 2024-11-04 | JOCHOA | AOC SYST | 2024-05-22 | 2025-12-31 | 2025-12-31 |  | JOCHOA | 2024-11-04 | 2024-08-12 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 26.4333 | 7 | 2399.34 | 1932.94 | 276.32 | 116.08 | 74 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24266515300 |  | 501146622 |  | 6748204H | 2406133 | U461383 |  | 563 | EX | M&R INSTALL NEW SERVICE LINE | 2621P | IRVINE | 2800 IRVINE RD HEATER | 049 | WIN | 2024-10-29 | WHIMES | U461383 | 2024-05-23 | 2024-12-31 | 2024-12-31 |  | WHIMES | 2024-10-29 | 2024-10-29 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 12.8333 | 2 | 2165.74 | 1416.32 | 24.62 | 724.8 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24266526400 |  | 501205336 |  | 7244216D | 2406133 | U461383 |  | 563 | EX | M&R INSTALL NEW SERVICE LINE | 2621P | STEPSTONE | 2580 STEPSTONE RD HEATER | 173 | MT | 2024-11-04 | U124604 | U461383 | 2024-05-23 | 2024-12-31 | 2024-12-31 |  | LCLARK | 2024-11-01 | 2024-10-31 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 12.6833 | 3 | 240.85 | 228.54 | 0 | 12.31 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24266529800 |  | 501210413 |  | 7244284I | 2406133 | U461383 |  | 563 | EX | M&R INSTALL NEW SERVICE LINE | 2621P | WALTON | 4241 WALTON PK HEATER | 161 | DOV | 2024-10-23 | U124604 | U461383 | 2024-05-23 | 2024-12-31 | 2024-12-31 |  | SDADAMS | 2024-10-22 | 2024-10-22 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26320011 | 6.6833 | 2 | 758.24 | 628.83 | 0 | 129.41 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24266533300 |  | 501205308 |  | 7256276K | 2406133 | U461383 |  | 563 | EX | M&R INSTALL NEW SERVICE LINE | 2621P | MAPLE LEAF | 198 E MAPLE LEAF RD HEATER | 161 | MAY | 2024-10-23 | U124604 | U461383 | 2024-05-23 | 2024-12-31 | 2024-12-31 |  | SDADAMS | 2024-10-22 | 2024-10-21 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26320011 | 11.0667 | 3 | 1320.62 | 959.48 | 0 | 361.14 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24266535700 |  | 501205337 |  | 6740208C | 2406133 | U461383 |  | 563 | EX | M&R INSTALL NEW SERVICE LINE | 2621P | ROCKWELL | 5855 ROCKWELL RD HEATER | 049 | WIN | 2024-10-28 | WHIMES | U461383 | 2024-05-23 | 2024-12-31 | 2024-12-31 |  | WHIMES | 2024-10-28 | 2024-10-28 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 8.2333 | 2 | 1887.54 | 1119.63 | 4.7 | 761.73 | 1.48 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24266542700 |  | 501205334 |  | 6748208E | 2406133 | U461383 |  | 563 | EX | M&R INSTALL NEW SERVICE LINE | 2621P | EARLY | 1049 EARLY DR HEATER | 049 | WIN | 2024-10-29 | JTOY | U461383 | 2024-05-23 | 2024-12-31 | 2024-12-31 |  | SDADAMS | 2024-10-25 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 8.2167 | 2 | 637.85 | 504.19 | 0 | 133.66 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24266544900 |  | 501205332 |  | 7240204B | 2406133 | U461383 |  | 563 | EX | M&R INSTALL NEW SERVICE LINE | 2621P | LEVEE | 4600 LEVEE RD HEATER | 173 | MT | 2024-11-04 | U124604 | U461383 | 2024-05-23 | 2024-12-31 | 2024-12-31 |  | LCLARK | 2024-11-01 | 2024-11-01 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 15.6 | 2 | 1567.99 | 1279.89 | 0 | 288.1 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24266549500 |  | 500521786 |  | 6760172J | 2406133 | U461383 |  | 563 | EX | M&R INSTALL NEW SERVICE LINE | 2621P | DUG HILL | 724 DUG HILL RD HEATER | 065 | IRV | 2024-11-07 | LCLARK | U461383 | 2024-05-23 | 2024-12-31 | 2024-12-31 |  | LCLARK | 2024-11-07 | 2024-11-07 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 16.2833 | 2 | 1461.13 | 1169.64 | 0 | 291.49 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24266551700 |  | 501239949 |  | 7256276A | 2406133 | U461383 |  | 563 | EX | M&R INSTALL NEW SERVICE LINE | 2621P | US 68 | 1755 US 68 HEATER | 161 | MAY | 2024-10-23 | U124604 | U461383 | 2024-05-23 | 2024-12-31 | 2024-12-31 |  | SDADAMS | 2024-10-22 | 2024-10-21 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26320011 | 12.9 | 4 | 2227.41 | 1627.99 | 0 | 599.42 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24266556300 |  | 500613641 |  | 6752176B | 2406133 | U461383 |  | 563 | EX | M&R INSTALL NEW SERVICE LINE | 2621P | BRASSFIELD | 3049 BRASSFIELD RD HEATER | 151 | WAC | 2024-11-13 | U141668 | U461383 | 2024-05-23 | 2024-12-31 | 2024-12-31 |  | NRICHIE | 2024-11-12 | 2024-11-08 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 17.55 | 4 | 2026.76 | 1413 | 276.66 | 337.1 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24266559900 |  | 500630909 |  | 6736228H | 2406133 | U461383 |  | 563 | EX | M&R INSTALL NEW SERVICE LINE | 2621P | CLINTONVILLE | 231 CLINTONVILLE RD HEATER | 017 | PAR | 2024-10-31 | U124604 | U461383 | 2024-05-23 | 2024-12-31 | 2024-12-31 |  | WHIMES | 2024-10-30 | 2024-10-30 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 11.7 | 2 | 1855.55 | 1221.73 | 24.62 | 609.2 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24266695100 |  | 100462309 |  | 6688228L |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | REGENTS PARK | 25 REGENTS PARK LN | 073 | FRA | 2024-10-31 | U124604 | U123688 | 2024-05-24 | 2024-11-22 | 2026-05-31 |  | KKINDER | 2024-10-30 | 2024-10-18 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 17.4167 | 4 | 1408.02 | 1011.35 | 228.15 | 61.96 | 106.56 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24266695500 |  | 100272685 |  | 6684224B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D506529 | 2621P | RAINTREE | 206 RAINTREE RD | 073 | FRA | 2024-10-23 | U124604 | U123688 | 2024-05-24 | 2024-11-22 | 2026-05-31 |  | LSTANFI | 2024-10-22 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 15.4333 | 3 | 810.35 | 822.06 | 86.86 | -98.57 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24267484800 |  | 100282663 |  | 6712228C |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | LANCASTER | 719 LANCASTER CT C | 209 | GEO | 2024-09-18 | DCOLLIN | U123688 | 2024-05-29 | 2024-12-31 |  |  | DCOLLIN | 2024-09-18 | 2024-09-06 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26230031 | 30.5167 | 5 | 3738.82 | 2108.47 | 363.76 | 480.18 | 786.41 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24267488200 |  | 100455792 |  | 6748208I | 2293700 |  |  | 566 | EX | RETIRE SERVICE LINE - LEAKAGE | 2621P | COOK | 240 COOK AV | 049 | WIN | 2024-10-23 | U126604 | U130871 | 2024-05-29 | 2024-12-31 |  |  | WILLIAM FULKS | 2024-10-23 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26290043 |  | 1 | 567.27 | 0 | 0 | 0 | 567.27 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24267949000 |  | 100345054 |  | 6696212G | 2405256 |  |  | 563 | EX | 2" P SHORT/STATE PRMT | 2600B | MCCRACKEN | 75 MCCRACKEN PK FG1 | 239 | VER | 2024-09-12 | U461322 | U128266 | 2024-05-31 | 2024-06-06 | 2024-09-30 |  | STEVE CANOY | 2024-09-12 | 2024-06-19 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 33.65 | 5 | 9578.9 | 2255.3 | 0 | 1739.28 | 5584.32 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24267965700 |  | 100272860 |  | 6684224B | 1635077 |  |  | 565 | EX | REPLACE SERVICE LINE-LEAKAGE | 2623D | TIMOTHY | 625 TIMOTHY DR | 073 | FRA | 2024-11-12 | U141668 | AOC SYST | 2024-05-31 | 2024-11-27 | 2026-05-31 |  | KKINDER | 2024-11-11 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 | KYACA |  | 100 | 056532B26230021 | 10.2333 | 2 | 718.6 | 626.15 | 0 | 37.69 | 54.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24267969800 |  | 100296722 |  | 6716212C | 1635077 |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2621D | GLEN ARVIN | 408 GLEN ARVIN AV | 067 | LEX | 2024-10-29 | U124604 | AOC SYST | 2024-05-31 | 2025-12-31 | 2025-12-31 |  | MCRAIG | 2024-10-28 | 2024-08-22 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 12.15 | 5 | 1129.69 | 765.62 | 323.57 | -71.98 | 112.48 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24267970100 |  | 100240595 |  | 7328284D | 2410099 |  |  | 565 | EX | REPLACE SERVICE LINE - D259711 | 2631D | CHRISTOPHER | 91 CHRISTOPHER DR | 089 | S S | 2025-03-11 | RECUMP | AOC SYST | 2024-05-31 | 2024-11-27 | 2026-05-31 |  | RECUMP | 2025-03-11 | 2025-02-12 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 | KYACA |  | 100 | 056532B26310021 | 19.45 | 5 | 2021.13 | 1373.63 | 0 | 548.34 | 99.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24268082400 |  | 100292342 |  | 6720216O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | NORTHRIDGE | 404 NORTHRIDGE DR | 067 | LEX | 2025-06-05 | TROE | U123688 | 2024-06-03 | 2024-11-27 | 2026-05-31 |  | TROE | 2025-06-05 | 2024-10-25 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 22.9 | 6 | 4343.77 | 1339.68 | 394.64 | 78.67 | 2530.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24268082900 |  | 100292567 |  | 6720216N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HAWTHORNE | 1601 HAWTHORNE LN | 067 | LEX | 2024-09-18 | TROE | U123688 | 2024-06-03 | 2024-11-27 | 2026-05-31 |  | TROE | 2024-09-18 | 2024-09-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16 | 2 | 1622.4 | 1051.95 | 510.45 | 60 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24268092900 |  | 100272740 |  | 6684224A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | TIMOTHY | 708 TIMOTHY DR | 073 | FRA | 2024-11-12 | U141668 | U123688 | 2024-06-03 | 2024-11-27 | 2026-05-31 |  | KKINDER | 2024-11-11 | 2024-11-01 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 9.4333 | 3 | 947.55 | 596.74 | 261.62 | 35.91 | 53.28 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24268219500 |  | 100272848 |  | 6684224B | 1635077 |  |  | 565 | EX | REPLACE SVC LINE-LEAKAGE | 2623D | TIMOTHY | 509 TIMOTHY DR | 073 | FRA | 2024-10-30 | DCOLLIN | AOC SYST | 2024-06-03 | 2024-12-03 | 2026-06-30 |  | DCOLLIN | 2024-10-30 | 2024-09-13 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 | KYACA |  | 100 | 056532B26230021 | 14.3 | 5 | 1450.07 | 841.59 | 234.96 | -86.48 | 460 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24268334600 |  | 100293906 |  | 6720212A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BROADWAY | 805 N BROADWAY ST | 067 | LEX | 2024-10-09 | MCRAIG | U124604 | 2024-06-04 | 2024-12-03 | 2026-06-30 |  | MCRAIG | 2024-10-09 | 2024-08-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 108.7333 | 16 | 11763.21 | 6557.09 | 489.18 | 1666.64 | 3050.3 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24269067100 |  | 100281228 |  | 6704216B |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | OLD FRANKFORT | 1489 OLD FRANKFORT PK FG22 | 239 | VER | 2024-09-19 | U124604 | U124604 | 2024-06-07 | 2024-12-06 | 2026-06-30 |  | LSTANFI | 2024-09-18 | 2024-09-17 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 73.1667 | 9 | 9661.73 | 4456.25 | 302.28 | 507.55 | 4395.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24269265800 |  | 100242055 |  | 7344168G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CARDINAL | 23 S CARDINAL DR | 071 | LNC | 2024-09-04 | JCKIRK | U124604 | 2024-06-10 | 2024-12-06 | 2026-06-30 |  | JCKIRK | 2024-09-04 | 2024-08-08 |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 26.15 | 4 | 1889.91 | 1788.87 | 0 | 101.04 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24269287700 |  | 100429607 |  | 7344168G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CARDINAL | 236 S CARDINAL DR | 071 | LNC | 2024-09-23 | JCKIRK | U124604 | 2024-06-10 | 2024-12-06 | 2026-06-30 |  | JCKIRK | 2024-09-23 | 2024-09-23 |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 24 | 3 | 2230.62 | 1631.65 | 0 | 598.97 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24269326400 |  | 100326060 |  | 6720208A |  |  |  | 565 | EX | REPLACE SL/ MOVE MTR OUT | 2621P | COCHRAN | 419 COCHRAN RD | 067 | LEX | 2024-11-07 | HMCKUNE | U134852 | 2024-06-10 | 2024-06-10 |  |  | HMCKUNE | 2024-11-07 | 2024-08-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 58.5 | 14 | 8014.64 | 5219.79 | 551.15 | 457.7 | 1786 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24270381900 |  | 100281651 |  | 6712232O | 1635077 |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2623D | GANO | 501 GANO AV | 209 | GEO | 2025-04-29 | DCOLLIN | AOC SYST | 2024-06-13 | 2025-12-31 | 2025-12-31 |  | DCOLLIN | 2025-04-29 | 2025-04-18 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 25.3333 | 5 | 3397.79 | 1777.83 | 28.56 | 390.88 | 1200.52 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24270500800 |  | 100272506 |  | 6684224B |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | RIDGE | 109 RIDGE RD | 073 | FRA | 2024-11-14 | U123688 | U124604 | 2024-06-14 | 2024-12-13 | 2026-06-30 |  | KKINDER | 2024-11-13 | 2024-11-13 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 23.95 | 3 | 2037.74 | 1547.41 | 305.44 | 93.13 | 91.76 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24270502300 |  | 100272503 |  | 6684224B |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LEAWOOD | 606 LEAWOOD DR | 073 | FRA | 2024-11-15 | U123688 | U124604 | 2024-06-14 | 2024-12-13 | 2026-06-30 |  | DCOLLIN | 2024-11-14 | 2024-10-11 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 30.75 | 6 | 4136.93 | 2321.9 | 283.6 | 477.47 | 1053.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24270781300 |  | 100295653 |  | 6716216K | 1635077 |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2621D | BOXWOOD | 1161 BOXWOOD DR | 067 | LEX | 2024-09-05 | U124604 | AOC SYST | 2024-06-17 | 2024-12-17 | 2025-12-31 |  | MCRAIG | 2024-09-04 | 2024-08-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 22.15 | 5 | 1803.59 | 1283.29 | 386.43 | 133.87 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24270782700 |  | 100295643 |  | 6716216K | 1635077 |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2621D | BOXWOOD | 1125 BOXWOOD DR | 067 | LEX | 2024-09-04 | U123688 | AOC SYST | 2024-06-17 | 2024-12-17 | 2025-12-31 |  | MCRAIG | 2024-09-03 | 2024-08-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 17.25 | 4 | 1643.81 | 1040.1 | 445.08 | 158.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24270946900 |  | 100302887 |  | 6712208C |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | WILLIAMSBURG | 2080 WILLIAMSBURG RD | 067 | LEX | 2025-01-28 | U124604 | U123688 | 2024-06-18 | 2024-12-13 | 2026-06-30 |  | JBURFOR | 2025-01-27 | 2024-07-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 36.2 | 13 | 3022.75 | 2169.35 | 428.23 | 294.93 | 130.24 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24271002600 |  | 100268582 |  | 7356256G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | WINCHESTER | 3341 WINCHESTER AV | 019 | ASH | 2025-03-12 | U124604 | U137009 | 2024-06-18 | 2024-12-18 | 2026-06-30 |  | JKEENER | 2025-03-11 | 2024-10-16 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 35.8667 | 7 | 3144 | 2579.88 | 0 | 538.96 | 25.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24271031600 |  | 100295543 |  | 6716216K | 1635077 |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2621D | REDWOOD | 1142 REDWOOD DR | 067 | LEX | 2025-01-28 | U124604 | AOC SYST | 2024-06-18 | 2025-12-31 | 2025-12-31 |  | MCRAIG | 2025-01-27 | 2024-09-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 26.65 | 7 | 3652.61 | 1459.93 | 532.72 | 258.45 | 1401.51 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24271531700 |  | 100247464 |  | 7352256H |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BLACKBURN | 2200 BLACKBURN AV | 019 | ASH | 2025-03-14 | ABHATFIE | U137009 | 2024-06-20 | 2024-12-19 | 2026-06-30 |  | ABHATFIE | 2025-03-14 | 2024-09-03 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 18.6 | 5 | 8346.67 | 1440.13 | 0 | 1395.58 | 5510.96 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24271624200 |  | 100242140 |  | 7356252D | 1635077 |  |  | 565 | EX | AOC L1 ATMOS CORR REPL RISER | 2631D | HONEYSUCKLE | 903 HONEYSUCKLE LN | 019 | CAT | 2025-02-04 | U124604 | AOC SYST | 2024-06-20 | 2024-07-19 | 2024-08-19 |  | RECUMP | 2025-02-03 | 2024-11-25 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26310031 | 34.1 | 13 | 3482.16 | 2710 | 245.08 | 527.08 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24272213800 |  | 100247623 |  | 7352256H |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | BLACKBURN | 1509 BLACKBURN AV REAR | 019 | ASH | 2025-01-16 | DYOUNG | U139701 | 2024-06-25 | 2024-06-25 |  |  | ABHATFIE | 2025-01-09 | 2024-07-10 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 28.4667 | 5 | 2191.31 | 1829.11 | 225.34 | 122.06 | 14.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24272545900 |  | 100278362 |  | 6688232O | 1635077 |  |  | 565 | EX | REPLACE SERVICE LINE- D506713 | 2623D | CHINOOK | 467 CHINOOK TL | 073 | FRA | 2024-09-24 | U124604 | AOC SYST | 2024-06-26 | 2024-12-26 | 2026-06-30 |  | ATWILLI | 2024-09-23 | 2024-09-13 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 | KYACA |  | 100 | 056532B26230021 | 27.5 | 7 | 2884.58 | 1794.05 | 458.26 | 632.27 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24272773200 |  | 100278360 |  | 6688232O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CHINOOK | 531 CHINOOK TL | 073 | FRA | 2024-09-27 | U123688 | U124604 | 2024-06-27 | 2024-12-26 | 2026-06-30 |  | ATWILLI | 2024-09-25 | 2024-09-13 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 23.65 | 5 | 2444.24 | 1346.98 | 505.03 | 592.23 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24273070100 |  | 100345494 |  | 6696212H |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | PRESTON | 115 PRESTON CT | 239 | VER | 2024-11-12 | U128410 | U124604 | 2024-06-28 | 2024-12-27 | 2026-06-30 |  | CDESPAIN | 2024-11-12 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 18 | 2 | 1539.44 | 1386.43 | 0 | 83.45 | 69.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24273071900 |  | 100352548 |  | 6744204J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HILLCREST | 20 HILLCREST DR | 049 | WIN | 2025-03-03 | DENNING | U137009 | 2024-06-28 | 2024-12-27 | 2026-06-30 |  | DENNING | 2025-03-03 | 2024-08-09 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 1.0833 | 5 | 543.5 | 86.11 | 367.12 | 4.43 | 85.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24273382600 |  | 100278314 |  | 6688228B | 1635077 |  |  | 565 | EX | REPLACE SERVICE LINE- D341939 | 2623D | MOJAVE | 1030 MOJAVE TL | 073 | FRA | 2024-11-13 | U141668 | AOC SYST | 2024-07-01 | 2025-05-05 | 2026-11-30 |  | KKINDER | 2024-11-13 | 2024-11-12 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 | KYACA |  | 100 | 056532B26230021 | 16 | 2 | 1870.53 | 1234.09 | 562.16 | 74.28 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24273489900 |  | 100278320 |  | 6688228B |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | PAWNEE | 504 PAWNEE TL | 073 | FRA | 2024-11-18 | U130722 | U124604 | 2024-07-02 | 2024-12-31 | 2026-07-31 |  | KKINDER | 2024-11-16 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 2 | 839.8 | 634.37 | 0 | 38.19 | 167.24 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24273490300 |  | 100278334 |  | 6688228B |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | PAWNEE | 501 PAWNEE TL | 073 | FRA | 2024-11-11 | U141668 | U124604 | 2024-07-02 | 2024-12-31 | 2026-07-31 |  | LSTANFI | 2024-11-09 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 13 | 4 | 1450.7 | 997.64 | 276.08 | 60.06 | 116.92 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24273490800 |  | 100278460 |  | 6688228B |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SHAWNEE | 1013 SHAWNEE TL | 073 | FRA | 2024-11-11 | U141668 | U124604 | 2024-07-02 | 2024-12-31 | 2026-07-31 |  | MCRAIG | 2024-11-09 | 2024-11-09 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 16 | 2 | 1503.13 | 1218.05 | 151.08 | 73.32 | 60.68 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24273491200 |  | 100278316 |  | 6688228B |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MOJAVE | 1040 MOJAVE TL | 073 | FRA | 2024-11-11 | U141668 | U124604 | 2024-07-02 | 2024-12-31 | 2026-07-31 |  | DCOLLIN | 2024-11-09 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 16 | 3 | 1705.36 | 1251.83 | 259.78 | 75.35 | 118.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24273727900 |  | 100278324 |  | 6688228B |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | PAWNEE | 520 PAWNEE TL | 073 | FRA | 2024-11-18 | CDESPAI | U124604 | 2024-07-03 | 2025-01-02 | 2026-07-31 |  | CDESPAI | 2024-11-18 | 2024-11-09 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 38.4833 | 6 | 3177.64 | 2706.62 | 0 | 327.46 | 143.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24273811600 |  | 100321851 |  | 6716212P | 2291708 |  |  | 565 | EX | RPLC SL/22026224200 | 2600B | COLUMBIA | 541 COLUMBIA AV | 067 | LEX | 2024-09-11 | U126602 | U125763 | 2024-07-03 | 2024-12-31 |  |  | DEREK PAYTON | 2024-09-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2297.08 | 0 | 384.55 | 0 | 1912.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24273811700 |  | 100321794 |  | 6716212P | 2291708 |  |  | 565 | EX | RPLC SL/22026224200 | 2600B | COLUMBIA | 542 COLUMBIA AV | 067 | LEX | 2024-09-11 | U126602 | U125763 | 2024-07-03 | 2024-12-31 |  |  | DEREK PAYTON | 2024-09-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3017.22 | 0 | 505.49 | 0 | 2511.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24273811800 |  | 100321850 |  | 6716212P | 2291708 |  |  | 565 | EX | RPLC SL/22026224200 | 2600B | COLUMBIA | 543 COLUMBIA AV | 067 | LEX | 2024-09-11 | U126602 | U125763 | 2024-07-03 | 2024-12-31 |  |  | DEREK PAYTON | 2024-09-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3647.11 | 0 | 384.55 | 0 | 3262.56 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24273813100 |  | 100344917 |  | 6700224O |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HIGGINS | 120 E HIGGINS ST | 239 | MID | 2025-04-08 | U123688 | U124604 | 2024-07-03 | 2024-12-31 |  |  | BWHITE | 2025-04-02 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 18.65 | 3 | 4241.3 | 1347.61 | 0 | 82.21 | 2811.48 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24273980300 |  | 100351783 |  | 6744208O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621P | BLOOMFIELD | 125 S BLOOMFIELD RD | 049 | WIN | 2024-10-07 | DENNING | U137009 | 2024-07-05 | 2025-01-03 | 2025-12-31 |  | DENNING | 2024-10-07 | 2024-07-26 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26290031 | 21.0833 | 4 | 1678.5 | 1377.67 | 216.01 | 84.82 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24274133600 |  | 100449841 |  | 7324132J |  |  |  | 566 | EX | ABANDON SL CUST RQSTD | 2621P | FROGTOWN | FROGTOWN RD | 119 | HIN | 2024-09-09 | JAHOWARD | U137009 | 2024-07-08 | 2024-07-22 | 2024-08-08 |  | JAHOWARD | 2024-09-09 | 2024-09-09 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.05 | 2 | 3.57 | 3.38 | 0 | 0.19 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24274134500 |  | 100240689 |  | 7324132J |  |  |  | 566 | EX | ABANDON SL CUST RQSTD | 2621P | FROGTOWN | 139 FROGTOWN RD | 119 | HIN | 2024-09-09 | JAHOWARD | U137009 | 2024-07-08 | 2024-07-22 | 2024-08-08 |  | JAHOWARD | 2024-09-09 | 2024-08-08 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 25.2333 | 4 | 1959.63 | 1719.05 | 143.1 | 97.48 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24274978000 |  | 100308338 |  | 6716212N |  |  |  | 565 | EX | REPLACE SL D311626 | 2621P | DUNCAN | 1056 DUNCAN AV | 067 | LEX | 2024-09-24 | RSTRONG | U124604 | 2024-07-12 | 2025-01-10 | 2026-07-31 |  | RSTRONG | 2024-09-24 | 2024-08-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 27.7833 | 6 | 2046.14 | 1749.88 | 188.96 | 107.3 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24275185500 |  | 100352557 |  | 6744204F |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HILLCREST | 48 HILLCREST DR | 049 | WIN | 2025-03-03 | DENNING | U124604 | 2024-07-15 | 2025-01-10 | 2026-07-31 |  | DENNING | 2025-03-03 | 2024-08-09 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 0.76667 | 2 | 282.93 | 60.62 | 121.55 | 3.08 | 97.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24275556700 |  | 500346355 |  | 6716216O | 9404606 |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LIMA | 250 LIMA DR | 067 | LEX | 2024-09-30 | RSTRONG | U124604 | 2024-07-16 | 2025-01-09 | 2026-07-31 |  | RSTRONG | 2024-09-30 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.83333 | 2 | 716.19 | 642.18 | 0 | 74.01 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24275557100 |  | 100467637 |  | 6684224E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LIMESTONE | 101 LIMESTONE DR | 073 | FRA | 2024-12-12 | U123688 | U124604 | 2024-07-16 | 2025-01-15 | 2026-07-31 |  | HMCKUNE | 2024-12-11 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 20.4 | 3 | 1705.58 | 1402.6 | 76.01 | 81.93 | 145.04 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24276305200 |  | 100345075 |  | 6696212H |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | FRANKFORT | 137 FRANKFORT ST | 239 | VER | 2024-10-30 | U128410 | U124604 | 2024-07-19 | 2024-12-31 |  |  | CDESPAIN | 2024-10-30 | 2024-10-02 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 13.8667 | 2 | 4622.24 | 906.69 | 0 | 55.54 | 3660.01 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24276655400 |  | 100348716 |  | 6748208M |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | WASHINGTON | 229 E WASHINGTON ST | 049 | WIN | 2024-09-10 | U124604 | U123688 | 2024-07-23 | 2024-12-31 |  |  | LCLARK | 2024-09-09 | 2024-08-30 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 16.6 | 3 | 2460.89 | 1171.96 | 227.36 | 691.57 | 370 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24276682400 |  | 100321468 |  | 6720212M | 2292814 |  |  | 565 | EX | RPLC SL/22026231300 | 2600B | HIGH | 608 E HIGH ST 1 | 067 | LEX | 2024-09-17 | U461309 | U125763 | 2024-07-23 | 2024-12-31 |  |  | RANDALL HUMPHREYS | 2024-09-04 | 2024-09-04 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 4171.76 | 522.76 | 388.07 | 133.2 | 3127.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24276683300 |  | 100321505 |  | 6720212M | 2292814 |  |  | 565 | EX | RPLC SL/22026231300 | 2600B | HIGH | 656 E HIGH ST 1F | 067 | LEX | 2024-09-03 | U461309 | U125763 | 2024-07-23 | 2024-12-31 |  |  | RANDALL HUMPHREYS | 2024-09-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 4032.63 | 522.76 | 520.88 | 133.2 | 2855.79 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24276706600 |  | 100265961 |  | 7348252D |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | STATE RT 716 | 1005 STATE RT 716 | 019 | ASH | 2024-11-22 | MCOLLET | U133234 | 2024-07-23 | 2024-08-12 | 2024-09-04 |  | MCOLLET | 2024-11-22 | 2024-11-21 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.7667 | 4 | 1329.73 | 441.94 | 10.01 | 417.78 | 460 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24277099400 |  | 100313024 |  | 6716208E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MITCHELL | 568 MITCHELL AV | 067 | LEX | 2025-02-26 | U124604 | U124604 | 2024-07-25 | 2025-01-24 | 2026-07-31 |  | JBURFOR | 2025-01-24 | 2024-09-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 45.0333 | 10 | 2635.44 | 2362.74 | 0 | 167.62 | 105.08 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24277242200 |  | 100249064 |  | 7328284B |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | JAMES HANNAH | 4940 JAMES HANNAH DR | 089 | S S | 2025-03-13 | U124604 | U123688 | 2024-07-26 | 2025-01-24 | 2026-07-31 |  | RECUMP | 2025-03-12 | 2025-03-12 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 14.0667 | 2 | 1664.26 | 964.86 | 284.03 | 403.53 | 11.84 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24277242400 |  | 100249078 |  | 7328284B |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MORTON | 83 MORTON ST | 089 | S S | 2024-10-04 | RECUMP | U123688 | 2024-07-26 | 2025-01-24 | 2026-07-31 |  | RECUMP | 2024-10-04 | 2024-09-16 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 26.9 | 7 | 1536.95 | 1678.34 | 0 | -145.83 | 4.44 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24277271400 |  | 100279728 |  | 6688228O |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | ROBIN | 535 ROBIN AV | 073 | FRA | 2025-02-25 | ATWILLI | U124604 | 2024-07-26 | 2024-12-31 |  |  | ATWILLI | 2025-02-25 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 16 | 2 | 2152.67 | 1169.42 | 373.27 | 524.14 | 85.84 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24277490800 |  | 100265985 |  | 7348252D |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | STATE RT 716 | 1113 STATE RT 716 RD | 019 | ASH | 2024-11-22 | MCOLLET | U123688 | 2024-07-29 | 2024-12-31 |  |  | MCOLLET | 2024-11-22 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.7167 | 2 | 1800.59 | 439.32 | 45.57 | 395.7 | 920 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24278200300 |  | 100433388 |  | 7328284B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D359626 | 2621P | STATE RT 784 | 649 STATE RT 784 | 089 | S S | 2024-09-23 | U124604 | U123688 | 2024-07-31 | 2025-01-30 | 2026-07-31 |  | RECUMP | 2024-09-20 | 2024-09-17 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 27 | 4 | 2339.05 | 1731.68 | 0 | 607.37 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24278474000 |  | 100239996 |  | 7352264E | 2300016 |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | DIVISION | 901 DIVISION ST | 089 | RUS | 2025-05-28 | MCOLLET | U461383 | 2024-08-01 | 2025-06-30 | 2025-06-30 |  | MCOLLET | 2025-05-28 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.4333 | 2 | 705.42 | 393.15 | 21.09 | 291.18 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24278475200 |  | 100239997 |  | 7352264E | 2300016 |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | ELWOOD | 913 ELWOOD ST | 089 | RUS | 2025-05-28 | MCOLLET | U461383 | 2024-08-01 | 2025-06-30 | 2025-06-30 |  | MCOLLET | 2025-05-28 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.7333 | 2 | 718.02 | 269.37 | 21.09 | 427.56 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24278949400 |  | 100405652 |  | 6712212G | 1635077 |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2621D | NICE | 1201 NICE DR | 067 | LEX | 2025-02-25 | U137585 | AOC SYST | 2024-08-05 | 2025-12-31 | 2025-12-31 |  | DJOHNSON | 2025-02-24 | 2024-11-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 26.6667 | 6 | 2050.17 | 1837.77 | 0 | 86.6 | 125.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24278950400 |  | 100302273 |  | 6712212G | 1635077 |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2621D | ROCKY POINT | 2305 ROCKY POINT CT B | 067 | LEX | 2025-02-18 | U124604 | AOC SYST | 2024-08-05 | 2025-12-31 | 2025-12-31 |  | JOCHOA | 2025-02-17 | 2024-09-25 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 23.0667 | 6 | 1706.58 | 1565 | 0 | 74.98 | 66.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24279114700 |  | 100344410 |  | 7240216P |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | SPENCER | 1005 SPENCER RD | 173 | MT | 2024-11-11 | DENNING | U123688 | 2024-08-06 | 2024-12-31 |  |  | DENNING | 2024-11-11 | 2024-08-15 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 34.9667 | 7 | 5515.38 | 2837.82 | 633.59 | 430.37 | 1613.6 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24279132000 |  | 100278278 |  | 6688228B |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | ARAPAHO | 1034 ARAPAHO TL | 073 | FRA | 2024-09-05 | ATWILLI | U131881 | 2024-08-06 | 2024-08-26 | 2024-09-18 |  | ATWILLI | 2024-09-05 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 16.35 | 3 | 1373.67 | 923.55 | 52.79 | 397.33 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279144700 |  | 501096936 |  | 6724208C | 1421490 |  |  | 563 | EX | 99-1"P-SHORT/PRMT READY 8/21 | 2600B | CORONEO | 2480 CORONEO LN | 067 | LEX | 2024-09-09 | U123111 | U128727 | 2024-08-06 | 2024-08-26 | 2024-09-09 |  | LYN STAFFORD | 2024-09-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 3612.41 | 262.58 | 325.57 | 14.96 | 3009.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24279346000 |  | 100441612 |  | 6752180E |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | WALTER | 111 WALTER LN | 151 | WAC | 2024-09-06 | DENNING | U123688 | 2024-08-07 | 2024-12-31 |  |  | DENNING | 2024-09-06 | 2024-08-16 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 15.6 | 5 | 1225.86 | 1143.55 | 20.27 | 62.04 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24279361800 |  | 501368702 |  | 6712232L | 2407579 |  |  | 563 | EX | TAP WITH MAIN 501368702 | 2600B | FINANCIAL | 101 FINANCIAL WY | 209 | GEO | 2024-09-18 | U126285 | U123852 | 2024-08-07 | 2024-09-16 | 2024-09-16 |  | DUSTIN DAVIS | 2024-09-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBTWM |  | 100 | 056332B26230011 |  | 1 | 4033.38 | 0 | 0 | 0 | 4033.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279405600 |  | 100338125 |  | 6720212F |  |  |  | 563 | EX | 1" P LONG/PRMT READY 8/21/24 | 2600B | 7TH | 442 E 7TH ST | 067 | LEX | 2024-09-11 | U461322 | U129294 | 2024-08-07 | 2024-08-26 | 2024-09-09 |  | STEVE CANOY | 2024-09-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 15.85 | 2 | 4246.24 | 1059.09 | 0 | 566.29 | 2620.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279421300 |  | 100302492 |  | 6712212G | 1635077 |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2621D | REIMS | 2416 REIMS RD | 067 | LEX | 2025-03-27 | U124604 | AOC SYST | 2024-08-07 | 2025-12-31 | 2025-12-31 |  | DMEDLEY | 2025-03-26 | 2024-09-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 19.05 | 6 | 1997.77 | 1090.84 | 326.25 | 509.64 | 71.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279421400 |  | 100300689 |  | 6716212E | 1635077 |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2621D | HALLS | 132 HALLS LN | 067 | LEX | 2025-02-04 | DMALONE | AOC SYST | 2024-08-07 | 2025-12-31 | 2025-12-31 |  | DMALONE | 2025-02-04 | 2024-08-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 27.8667 | 10 | 1882.78 | 1743.5 | 0 | 83.04 | 56.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279421600 |  | 100302472 |  | 6712212G | 1635077 |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2621D | BORDEAUX | 1250 BORDEAUX DR | 067 | LEX | 2025-01-15 | U124604 | AOC SYST | 2024-08-07 | 2025-12-31 | 2025-12-31 |  | MCRAIG | 2025-01-14 | 2024-08-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 18.7 | 5 | 2096.53 | 1135.54 | 410.07 | 422.16 | 128.76 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24279522900 |  | 100348384 |  | 6748208J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | IRONWORKS | 1074 IRONWORKS RD | 049 | WIN | 2024-09-06 | U124604 | U123688 | 2024-08-08 | 2025-02-07 | 2026-08-31 |  | DENNING | 2024-09-05 | 2024-08-27 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 26.2 | 6 | 4796.26 | 1876.49 | 632.79 | 130.48 | 2156.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279539600 |  | 100449479 |  | 6716208H |  |  |  | 565 | EX | REPAIR SERVICE LINE | 2621P | TATES CREEK | 1700 TATES CREEK RD | 067 | LEX | 2024-09-13 | U124604 | U124604 | 2024-08-08 | 2024-12-31 |  |  | RJCRAWF | 2024-09-12 | 2024-08-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 26.5167 | 5 | 3304.51 | 1809.76 | 170.75 | 102.99 | 1221.01 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24279540000 |  | 100260006 |  | 7356256A |  |  |  | 565 | EX | SL/METER RELOCATION | 2621P | LEXINGTON | 1908 LEXINGTON AV | 019 | ASH | 2024-11-20 | ABHATFIE | U123688 | 2024-08-08 | 2024-12-31 |  |  | ABHATFIE | 2024-11-20 | 2024-09-19 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 13.5167 | 2 | 5174.9 | 982.98 | 0 | 563.39 | 3628.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279564100 |  | 100339146 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 194 CASTLEWOOD DR | 067 | LEX | 2025-03-27 | U126532 | U125763 | 2024-08-08 | 2024-12-31 |  |  | LESLIE SHARON | 2025-03-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 5761.78 | 0 | 0 | 0 | 5761.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279564200 |  | 100286952 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 200 CASTLEWOOD DR | 067 | LEX | 2025-03-21 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2025-03-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2594.81 | 0 | 0 | 0 | 2594.81 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279564300 |  | 100286953 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 206 CASTLEWOOD DR | 067 | LEX | 2024-12-09 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-12-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2130.23 | 0 | 0 | 0 | 2130.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279564400 |  | 100456771 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 209 CASTLEWOOD DR BARN | 067 | LEX | 2025-04-15 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2025-04-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 7690.49 | 0 | 0 | 0 | 7690.49 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279564500 |  | 100286950 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 209 CASTLEWOOD DR GYM | 067 | LEX | 2025-04-08 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2025-04-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 9144.09 | 0 | 0 | 0 | 9144.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279564600 |  | 100286958 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 216 CASTLEWOOD DR | 067 | LEX | 2025-02-06 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2025-02-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2974.16 | 0 | 0 | 0 | 2974.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279564700 |  | 100286949 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 219 CASTLEWOOD DR | 067 | LEX | 2025-02-05 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2025-02-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4412.33 | 0 | 0 | 0 | 4412.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279564800 |  | 100286961 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 220 CASTLEWOOD DR | 067 | LEX | 2025-02-11 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2025-02-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2561.44 | 0 | 0 | 0 | 2561.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279564900 |  | 100286948 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 221 CASTLEWOOD DR | 067 | LEX | 2025-02-05 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2025-02-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3545.02 | 0 | 0 | 0 | 3545.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279565000 |  | 100286947 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 223 CASTLEWOOD DR | 067 | LEX | 2024-12-14 | U126604 | U125763 | 2024-08-08 | 2024-12-31 |  |  | WILLIAM FULKS | 2024-12-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2554.58 | 0 | 0 | 103.52 | 2451.06 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279565100 |  | 100286946 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 225 CASTLEWOOD DR | 067 | LEX | 2024-12-17 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-12-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3161.34 | 0 | 0 | 0 | 3161.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279565200 |  | 100286945 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 227 CASTLEWOOD DR | 067 | LEX | 2024-12-16 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-12-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2130.23 | 0 | 0 | 0 | 2130.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279565300 |  | 100286963 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 228 CASTLEWOOD DR | 067 | LEX | 2024-12-13 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-12-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3125.92 | 0 | 0 | 0 | 3125.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279565400 |  | 100286944 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 229 CASTLEWOOD DR | 067 | LEX | 2024-12-13 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-12-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3153.51 | 0 | 0 | 0 | 3153.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279565500 |  | 100286964 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 230 CASTLEWOOD DR 1F | 067 | LEX | 2024-12-13 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-12-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3489.82 | 0 | 0 | 0 | 3489.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279565600 |  | 100286943 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 231 CASTLEWOOD DR | 067 | LEX | 2025-02-11 | U127414 | U125763 | 2024-08-08 | 2024-12-31 |  |  | EDWARD FOX | 2025-02-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4019.46 | 0 | 0 | 0 | 4019.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279565700 |  | 100286966 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 232 CASTLEWOOD DR | 067 | LEX | 2025-01-02 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-12-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2722.59 | 0 | 0 | 0 | 2722.59 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279565800 |  | 100286942 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 233 CASTLEWOOD DR | 067 | LEX | 2024-12-13 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-12-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2775.09 | 0 | 0 | 0 | 2775.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279565900 |  | 100286967 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 234 CASTLEWOOD DR | 067 | LEX | 2025-02-04 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2025-02-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2192.3 | 0 | 0 | 0 | 2192.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279566000 |  | 100286941 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 235 CASTLEWOOD DR | 067 | LEX | 2025-02-11 | U127414 | U125763 | 2024-08-08 | 2024-12-31 |  |  | EDWARD FOX | 2025-02-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3650.21 | 0 | 0 | 0 | 3650.21 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279566100 |  | 100286968 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 236 CASTLEWOOD DR | 067 | LEX | 2024-12-13 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-12-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2107.73 | 0 | 0 | 0 | 2107.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279566200 |  | 100286940 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 237 CASTLEWOOD DR | 067 | LEX | 2025-05-08 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2025-04-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3469.48 | 0 | 0 | 0 | 3469.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279566300 |  | 100286971 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 238 CASTLEWOOD DR 1F | 067 | LEX | 2025-04-10 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2025-04-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2656.12 | 0 | 0 | 0 | 2656.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279566500 |  | 100286972 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 240 CASTLEWOOD DR | 067 | LEX | 2025-02-02 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2025-01-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2176.52 | 0 | 0 | 0 | 2176.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279566600 |  | 100286939 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 241 CASTLEWOOD DR | 067 | LEX | 2024-12-13 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-12-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2127.73 | 0 | 0 | 0 | 2127.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279566700 |  | 100287047 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 243 CASTLEWOOD DR | 067 | LEX | 2025-01-30 | U127414 | U125763 | 2024-08-08 | 2024-12-31 |  |  | EDWARD FOX | 2025-01-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4284.45 | 0 | 0 | 0 | 4284.45 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279566800 |  | 100286974 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 264 CASTLEWOOD DR | 067 | LEX | 2024-12-18 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-12-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2511.48 | 0 | 0 | 0 | 2511.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279566900 |  | 100287046 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 265 CASTLEWOOD DR | 067 | LEX | 2025-01-29 | U127414 | U125763 | 2024-08-08 | 2024-12-31 |  |  | EDWARD FOX | 2025-01-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3191.76 | 0 | 0 | 0 | 3191.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279567000 |  | 100287045 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 267 CASTLEWOOD DR | 067 | LEX | 2024-12-19 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-12-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2112.73 | 0 | 0 | 0 | 2112.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279567100 |  | 100286975 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 268 CASTLEWOOD DR | 067 | LEX | 2025-01-31 | U127414 | U125763 | 2024-08-08 | 2024-12-31 |  |  | EDWRAD FOX | 2025-01-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3916.78 | 0 | 0 | 0 | 3916.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279567200 |  | 100287044 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 269 CASTLEWOOD DR | 067 | LEX | 2024-12-13 | U127414 | U125763 | 2024-08-08 | 2024-12-31 |  |  | EDWARD FOX | 2024-12-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2855 | 0 | 0 | 0 | 2855 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279567300 |  | 100287043 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 271 CASTLEWOOD DR | 067 | LEX | 2024-12-12 | U127414 | U125763 | 2024-08-08 | 2024-12-31 |  |  | EDWARD FOX | 2024-12-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2458.56 | 0 | 0 | 0 | 2458.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279567400 |  | 100286976 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 276 CASTLEWOOD DR | 067 | LEX | 2025-02-27 | U126602 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DEREK PAYTON | 2025-02-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 6243.84 | 591.1 | 0 | 27.68 | 5625.06 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279567500 |  | 100286978 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 280 CASTLEWOOD DR | 067 | LEX | 2025-02-11 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2025-02-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2865.52 | 0 | 0 | 0 | 2865.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279567600 |  | 100287074 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CHURCHILL | 1010 CHURCHILL DR | 067 | LEX | 2024-09-18 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-09-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4248.34 | 0 | 0 | 0 | 4248.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279567700 |  | 100287075 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CHURCHILL | 1012 CHURCHILL DR | 067 | LEX | 2024-09-17 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-09-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3594.79 | 0 | 0 | 0 | 3594.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279567800 |  | 100287076 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CHURCHILL | 1014 CHURCHILL DR | 067 | LEX | 2024-09-17 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-09-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3027.26 | 0 | 0 | 0 | 3027.26 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279567900 |  | 100287048 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | HIGHLAND PARK | 914 HIGHLAND PARK DR | 067 | LEX | 2024-12-05 | U128816 | U125763 | 2024-08-08 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-12-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2910.06 | 0 | 0 | 0 | 2910.06 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279568000 |  | 100287049 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | HIGHLAND PARK | 916 HIGHLAND PARK DR | 067 | LEX | 2024-12-06 | U128816 | U125763 | 2024-08-08 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-12-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3443.99 | 0 | 0 | 0 | 3443.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279568100 |  | 100287051 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | HIGHLAND PARK | 922 HIGHLAND PARK DR | 067 | LEX | 2024-12-07 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-12-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 3695.12 | 706.94 | 0 | 698.33 | 2289.85 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279568200 |  | 100287054 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | HIGHLAND PARK | 930 HIGHLAND PARK DR | 067 | LEX | 2024-12-11 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-12-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2496.63 | 0 | 0 | 0 | 2496.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279568300 |  | 100287055 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | HIGHLAND PARK | 934 HIGHLAND PARK DR | 067 | LEX | 2024-12-12 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-12-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2444.13 | 0 | 0 | 0 | 2444.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279568400 |  | 100287057 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | HIGHLAND PARK | 940 HIGHLAND PARK DR | 067 | LEX | 2024-12-20 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-12-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2426.63 | 0 | 0 | 0 | 2426.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279568500 |  | 100287062 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | HIGHLAND PARK | 954 HIGHLAND PARK DR | 067 | LEX | 2024-12-12 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-12-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2501.63 | 0 | 0 | 0 | 2501.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279568600 |  | 100287071 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | HIGHLAND PARK | 957 HIGHLAND PARK DR | 067 | LEX | 2024-09-04 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-09-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3063.83 | 0 | 0 | 0 | 3063.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279568700 |  | 100287064 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | HIGHLAND PARK | 958 HIGHLAND PARK DR | 067 | LEX | 2024-12-14 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-12-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2419.13 | 0 | 0 | 0 | 2419.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279568800 |  | 100287070 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | HIGHLAND PARK | 959 HIGHLAND PARK DR | 067 | LEX | 2024-09-04 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-09-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2834.13 | 0 | 0 | 0 | 2834.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279568900 |  | 100287065 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | HIGHLAND PARK | 960 HIGHLAND PARK DR | 067 | LEX | 2024-12-12 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-12-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2752.59 | 0 | 0 | 0 | 2752.59 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279569000 |  | 100287069 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | HIGHLAND PARK | 961 HIGHLAND PARK DR | 067 | LEX | 2024-09-05 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-09-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2821.63 | 0 | 0 | 0 | 2821.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279569100 |  | 100286985 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | IDLEWILD | 910 IDLEWILD CT | 067 | LEX | 2024-10-25 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-10-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3310.49 | 0 | 0 | 0 | 3310.49 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279569200 |  | 100286986 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | IDLEWILD | 912 IDLEWILD CT | 067 | LEX | 2024-10-25 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-10-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2537.63 | 0 | 0 | 0 | 2537.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279569300 |  | 100287042 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | IDLEWILD | 913 IDLEWILD CT | 067 | LEX | 2024-12-12 | U127414 | U125763 | 2024-08-08 | 2024-12-31 |  |  | EDWARD FOX | 2024-12-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3099.57 | 0 | 0 | 0 | 3099.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279569400 |  | 100286987 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | IDLEWILD | 914 IDLEWILD CT | 067 | LEX | 2024-10-25 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-10-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4536.54 | 0 | 0 | 0 | 4536.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279569500 |  | 100287038 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | IDLEWILD | 915 IDLEWILD CT 1F | 067 | LEX | 2024-12-04 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-12-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2712.59 | 0 | 0 | 0 | 2712.59 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279569600 |  | 100286988 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | IDLEWILD | 918 IDLEWILD CT | 067 | LEX | 2024-10-24 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-10-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2788.47 | 0 | 0 | 0 | 2788.47 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279569700 |  | 100287037 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | IDLEWILD | 919 IDLEWILD CT | 067 | LEX | 2024-12-05 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-12-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2458.43 | 0 | 0 | 0 | 2458.43 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279569800 |  | 100286991 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | IDLEWILD | 922 IDLEWILD CT | 067 | LEX | 2024-10-24 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-10-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2468.56 | 0 | 0 | 0 | 2468.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279569900 |  | 100287036 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | IDLEWILD | 923 IDLEWILD CT | 067 | LEX | 2024-12-10 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-12-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2150.23 | 0 | 0 | 0 | 2150.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279570000 |  | 100286992 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | IDLEWILD | 924 IDLEWILD CT | 067 | LEX | 2024-10-23 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-10-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3454.73 | 0 | 0 | 0 | 3454.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279570100 |  | 100287035 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | IDLEWILD | 925 IDLEWILD CT | 067 | LEX | 2024-12-03 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-12-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2072.73 | 0 | 0 | 0 | 2072.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279570200 |  | 100287034 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | IDLEWILD | 927 IDLEWILD CT | 067 | LEX | 2024-12-04 | U128816 | U125763 | 2024-08-08 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-12-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3249.99 | 0 | 0 | 0 | 3249.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279570300 |  | 100286993 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | IDLEWILD | 928 IDLEWILD CT | 067 | LEX | 2024-10-23 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-10-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2869.22 | 0 | 0 | 0 | 2869.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279570400 |  | 100287033 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | IDLEWILD | 929 IDLEWILD CT | 067 | LEX | 2024-12-10 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-12-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2884.2 | 0 | 0 | 0 | 2884.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279570500 |  | 100287032 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | IDLEWILD | 931 IDLEWILD CT | 067 | LEX | 2024-12-19 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-12-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3142.82 | 0 | 0 | 0 | 3142.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279570600 |  | 100287030 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | IDLEWILD | 935 IDLEWILD CT | 067 | LEX | 2025-02-07 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2025-02-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2782.24 | 0 | 0 | 0 | 2782.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279570700 |  | 100287029 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | IDLEWILD | 937 IDLEWILD CT | 067 | LEX | 2024-12-11 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-12-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 9160.34 | 0 | 0 | 0 | 9160.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279570800 |  | 100287028 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | IDLEWILD | 939 IDLEWILD CT | 067 | LEX | 2024-12-09 | U128816 | U125763 | 2024-08-08 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-12-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3078.03 | 0 | 0 | 0 | 3078.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279570900 |  | 100286994 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | IDLEWILD | 940 IDLEWILD CT | 067 | LEX | 2024-10-28 | U123111 | U125763 | 2024-08-08 | 2024-12-31 |  |  | LYN STAFFORD | 2024-10-26 | 2024-10-26 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 5925.92 | 495.48 | 0 | 30.37 | 5400.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279571000 |  | 100287027 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | IDLEWILD | 941 IDLEWILD CT | 067 | LEX | 2025-02-14 | U127414 | U125763 | 2024-08-08 | 2024-12-31 |  |  | EDWARD FOX | 2025-02-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3254.5 | 0 | 0 | 0 | 3254.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279571100 |  | 100287019 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | OAK HILL | 826 OAK HILL DR | 067 | LEX | 2025-04-09 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2025-04-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2255.42 | 0 | 0 | 0 | 2255.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279571200 |  | 100287007 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | OAKHILL | 802 OAKHILL DR | 067 | LEX | 2024-12-11 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-12-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2125.23 | 0 | 0 | 0 | 2125.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279571300 |  | 100287004 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | OAKHILL | 803 OAKHILL DR 1 | 067 | LEX | 2024-10-29 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-10-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 8665.37 | 0 | 0 | 0 | 8665.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279571400 |  | 100287008 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | OAKHILL | 804 OAKHILL DR | 067 | LEX | 2024-11-27 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-11-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2516.06 | 0 | 0 | 0 | 2516.06 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279571500 |  | 100287009 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | OAKHILL | 806 OAKHILL DR | 067 | LEX | 2024-11-26 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-11-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3133.42 | 0 | 0 | 0 | 3133.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279571600 |  | 100287002 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | OAKHILL | 807 OAKHILL DR | 067 | LEX | 2024-10-15 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-10-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3291.34 | 0 | 0 | 0 | 3291.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279571700 |  | 100287010 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | OAKHILL | 808 OAKHILL DR | 067 | LEX | 2024-11-25 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-11-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3134.75 | 0 | 0 | 0 | 3134.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279571800 |  | 100287003 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | OAKHILL | 809 OAKHILL DR | 067 | LEX | 2024-10-15 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-10-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3030.08 | 0 | 0 | 0 | 3030.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279571900 |  | 100287001 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | OAKHILL | 811 OAKHILL DR | 067 | LEX | 2024-10-15 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-10-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.5 | 1 | 4846.17 | 843.79 | 0 | 622.62 | 3379.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279572000 |  | 100287012 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | OAKHILL | 812 OAKHILL DR | 067 | LEX | 2024-11-20 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-11-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3035.86 | 0 | 0 | 0 | 3035.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279572100 |  | 100287000 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | OAKHILL | 813 OAKHILL DR | 067 | LEX | 2024-10-21 | U126532 | U125763 | 2024-08-08 | 2024-12-31 |  |  | LESLIE SHARON | 2024-10-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3137.06 | 0 | 0 | 0 | 3137.06 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279572200 |  | 100287013 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | OAKHILL | 814 OAKHILL DR | 067 | LEX | 2024-11-23 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-11-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2808.73 | 0 | 0 | 0 | 2808.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279572300 |  | 100287014 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | OAKHILL | 816 OAKHILL DR | 067 | LEX | 2024-11-22 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-11-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3637.6 | 0 | 0 | 0 | 3637.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279572400 |  | 100286998 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | OAKHILL | 817 OAKHILL DR | 067 | LEX | 2024-10-16 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-10-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2917.56 | 0 | 0 | 0 | 2917.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279572500 |  | 100287015 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | OAKHILL | 818 OAKHILL DR | 067 | LEX | 2024-11-21 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-11-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2705.83 | 0 | 0 | 0 | 2705.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279572600 |  | 100286997 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | OAKHILL | 819 OAKHILL DR | 067 | LEX | 2024-10-16 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-10-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2922.56 | 0 | 0 | 0 | 2922.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279572700 |  | 100287016 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | OAKHILL | 820 OAKHILL DR | 067 | LEX | 2024-11-18 | U128816 | U125763 | 2024-08-08 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-11-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2531.73 | 0 | 0 | 0 | 2531.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279572800 |  | 100287018 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | OAKHILL | 824 OAKHILL DR | 067 | LEX | 2024-11-19 | U128816 | U125763 | 2024-08-08 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-11-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2085.23 | 0 | 0 | 0 | 2085.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279572900 |  | 100287020 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | OAKHILL | 914 OAKHILL DR | 067 | LEX | 2024-12-13 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-12-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2634.54 | 0 | 0 | 0 | 2634.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279573000 |  | 100287021 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | OAKHILL | 916 OAKHILL DR | 067 | LEX | 2024-11-16 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-11-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2760.09 | 0 | 0 | 0 | 2760.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279573100 |  | 100287022 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | OAKHILL | 918 OAKHILL DR | 067 | LEX | 2024-11-15 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-11-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2451.69 | 0 | 0 | 0 | 2451.69 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279573200 |  | 100287023 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | OAKHILL | 920 OAKHILL DR | 067 | LEX | 2024-11-15 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-11-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3145.53 | 0 | 0 | 0 | 3145.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279573300 |  | 100288032 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | PARKVIEW | 305 PARKVIEW AV | 067 | LEX | 2024-10-03 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-10-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2077.99 | 0 | 0 | 0 | 2077.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279573400 |  | 100288031 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | PARKVIEW | 307 PARKVIEW AV | 067 | LEX | 2024-10-03 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-10-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1222.5 | 0 | 0 | 0 | 1222.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279573500 |  | 100288030 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | PARKVIEW | 311 PARKVIEW AV | 067 | LEX | 2024-10-04 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-10-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2042.99 | 0 | 0 | 0 | 2042.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279573600 |  | 100288028 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | PARKVIEW | 317 PARKVIEW AV | 067 | LEX | 2024-10-04 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-10-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2060.49 | 0 | 0 | 0 | 2060.49 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279573700 |  | 100288027 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | PARKVIEW | 319 PARKVIEW AV | 067 | LEX | 2024-10-04 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-10-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2073.8 | 0 | 0 | 0 | 2073.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279573800 |  | 100288026 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | PARKVIEW | 321 PARKVIEW AV | 067 | LEX | 2024-10-04 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-10-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2110.49 | 0 | 0 | 0 | 2110.49 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279573900 |  | 100288024 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | PARKVIEW | 327 PARKVIEW AV | 067 | LEX | 2024-10-04 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-10-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2002.99 | 0 | 0 | 0 | 2002.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279574000 |  | 100288022 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | PARKVIEW | 405 PARKVIEW AV | 067 | LEX | 2024-10-29 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-10-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3273.04 | 0 | 0 | 0 | 3273.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279574100 |  | 100288020 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | PARKVIEW | 411 PARKVIEW AV | 067 | LEX | 2024-10-10 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-10-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 5067.79 | 0 | 0 | 0 | 5067.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279574200 |  | 100288019 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | PARKVIEW | 415 PARKVIEW AV | 067 | LEX | 2024-10-07 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-10-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2798.97 | 0 | 269.74 | 0 | 2529.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279574300 |  | 100288018 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | PARKVIEW | 417 PARKVIEW AV | 067 | LEX | 2024-10-07 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-10-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2534.23 | 0 | 0 | 0 | 2534.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279574400 |  | 100288015 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | PARKVIEW | 425 PARKVIEW AV | 067 | LEX | 2024-09-20 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-09-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3334.63 | 0 | 0 | 0 | 3334.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279574500 |  | 100288012 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | PARKVIEW | 503 PARKVIEW AV | 067 | LEX | 2024-10-01 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-10-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3451.87 | 0 | 0 | 0 | 3451.87 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279574600 |  | 100288011 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | PARKVIEW | 505 PARKVIEW AV | 067 | LEX | 2024-10-10 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-10-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4056.94 | 0 | 0 | 0 | 4056.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279579100 |  | 100287056 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | HIGHLAND PARK | 936 HIGHLAND PARK DR | 067 | LEX | 2024-12-05 | U128816 | U125763 | 2024-08-08 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-12-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3238.13 | 0 | 0 | 0 | 3238.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279579200 |  | 100287058 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | HIGHLAND PARK | 942 HIGHLAND PARK DR | 067 | LEX | 2024-12-19 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-12-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3829.29 | 0 | 0 | 0 | 3829.29 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279579300 |  | 100287061 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | HIGHLAND PARK | 952 HIGHLAND PARK DR | 067 | LEX | 2024-12-11 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-12-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2763.18 | 0 | 0 | 0 | 2763.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279579400 |  | 100287073 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | HIGHLAND PARK | 953 HIGHLAND PARK DR | 067 | LEX | 2024-09-12 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-09-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4293.51 | 0 | 0 | 0 | 4293.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279579500 |  | 100287072 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | HIGHLAND PARK | 955 HIGHLAND PARK DR | 067 | LEX | 2024-09-11 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | J ENSMINGER | 2024-09-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2998.03 | 0 | 0 | 0 | 2998.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279579600 |  | 100287066 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | HIGHLAND PARK | 962 HIGHLAND PARK DR | 067 | LEX | 2024-12-18 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-12-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3093.99 | 0 | 0 | 0 | 3093.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279579700 |  | 100287068 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | HIGHLAND PARK | 963 HIGHLAND PARK DR | 067 | LEX | 2024-10-04 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE NSMINGER | 2024-09-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2927.33 | 0 | 0 | 0 | 2927.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279579800 |  | 100287031 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | IDLEWILD | 933 IDLEWILD CT | 067 | LEX | 2024-12-17 | U127414 | U125763 | 2024-08-08 | 2024-12-31 |  |  | EDWARD FOX | 2024-12-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3088.81 | 0 | 0 | 0 | 3088.81 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279579900 |  | 100287011 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | OAKHILL | 810 OAKHILL DR | 067 | LEX | 2024-11-22 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-11-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2981.46 | 0 | 0 | 0 | 2981.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279580000 |  | 100287017 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | OAKHILL | 822 OAKHILL DR | 067 | LEX | 2024-11-23 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-11-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3230.03 | 0 | 0 | 0 | 3230.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279580100 |  | 100287025 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | OAKHILL | 928 OAKHILL DR | 067 | LEX | 2024-11-19 | U129722 | U125763 | 2024-08-08 | 2024-12-31 |  |  | DAVID YOUNG | 2024-11-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4181.22 | 0 | 0 | 0 | 4181.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279580200 |  | 100288021 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | PARKVIEW | 407 PARKVIEW AV | 067 | LEX | 2024-10-17 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-10-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4451.97 | 0 | 0 | 0 | 4451.97 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279580300 |  | 100288017 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | PARKVIEW | 419 PARKVIEW AV | 067 | LEX | 2024-10-09 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-10-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3182.96 | 0 | 0 | 0 | 3182.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279580400 |  | 100288014 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | PARKVIEW | 429 PARKVIEW AV | 067 | LEX | 2024-10-01 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-10-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3002.56 | 0 | 0 | 0 | 3002.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279580500 |  | 100288010 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | PARKVIEW | 507 PARKVIEW AV | 067 | LEX | 2024-09-30 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-09-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4769.81 | 0 | 0 | 0 | 4769.81 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279580600 |  | 100288009 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | PARKVIEW | 509 PARKVIEW AV | 067 | LEX | 2024-10-03 | U126308 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-10-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 40753.82 | 0 | 37339.44 | 0 | 3414.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279582000 |  | 100286954 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | CASTLEWOOD | 208 CASTLEWOOD DR | 067 | LEX | 2024-12-12 | U125201 | U125763 | 2024-08-08 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2024-12-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3108.99 | 0 | 0 | 0 | 3108.99 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24279657000 |  | 100404336 |  | 6688232O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | TONKAWA | 217 TONKAWA TL | 073 | FRA | 2024-11-18 | U130722 | U124604 | 2024-08-09 | 2025-02-07 | 2026-08-31 |  | MCRAIG | 2024-11-16 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 24 | 5 | 1767.48 | 1541.49 | 0 | 92.79 | 133.2 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24279657300 |  | 100278720 |  | 6688232O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | POWHATAN | 515 POWHATAN TL | 073 | FRA | 2024-12-05 | U124604 | U124604 | 2024-08-09 | 2025-02-07 | 2026-08-31 |  | DCOLLIN | 2024-12-04 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 20 | 2 | 2333.76 | 1547.21 | 193.81 | 511.34 | 81.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24279668400 |  | 100345698 |  | 6696212C |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | MOLLY | 123 MOLLY ST | 239 | VER | 2025-03-07 | U128410 | U124604 | 2024-08-09 | 2024-12-31 |  |  | CDESPAIN | 2025-03-07 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 33.9 | 5 | 5181.18 | 2666.88 | 0 | 511.16 | 2003.14 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279687500 |  | 100288164 |  | 6720212C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER | 2621P | WANSTEAD | 476 WANSTEAD WY | 067 | LEX | 2024-09-10 | STGOFF | U124604 | 2024-08-09 | 2024-09-09 | 2024-10-09 |  | STGOFF | 2024-09-10 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 10.9833 | 2 | 1120.96 | 712.24 | 368.08 | 40.64 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279875800 |  | 100302622 |  | 6712212K | 1635077 |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2621D | BORDEAUX | 1329 BORDEAUX DR | 067 | LEX | 2024-09-27 | U123688 | AOC SYST | 2024-08-12 | 2025-12-31 | 2025-12-31 |  | MCRAIG | 2024-09-25 | 2024-08-22 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 21.5333 | 6 | 2175.89 | 1395.75 | 566.98 | 213.16 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24279877400 |  | 100302609 |  | 6712212K | 1635077 |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2621D | LE HAVRE | 2383 LE HAVRE RD | 067 | LEX | 2025-03-07 | U143504 | AOC SYST | 2024-08-12 | 2025-12-31 | 2025-12-31 |  | JGILES | 2025-03-06 | 2024-08-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 27.05 | 7 | 2623.58 | 1551.74 | 393.57 | 540.63 | 137.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24280023300 |  | 100301297 |  | 6712212H |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | DUNKIRK | 2020 DUNKIRK DR | 067 | LEX | 2024-11-06 | U128711 | U124604 | 2024-08-13 | 2025-02-12 | 2026-08-31 |  | TROE | 2024-10-14 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.2333 | 3 | 1009.18 | 950.92 | 0 | 58.26 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24280094200 |  | 100331444 |  | 6720212N |  |  |  | 565 | EX | METER MOVE OUT / RELO | 2621P | VICTORY | 130 VICTORY AV | 067 | LEX | 2024-09-11 | HMCKUNE | U124604 | 2024-08-13 | 2024-09-30 |  |  | HMCKUNE | 2024-09-11 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 15.45 | 2 | 1267.65 | 1011.73 | 198.19 | 57.73 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24280132600 |  | 100359052 |  | 6740232M |  |  |  | 566 | EX | ABANDON SL/ DEMO CUST REQ | 2621P | HIGGINS | 634 HIGGINS ST | 017 | PAR | 2024-09-13 | NRICHIE | U139381 | 2024-08-13 | 2024-09-03 | 2024-09-25 |  | NRICHIE | 2024-09-13 | 2024-08-30 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10.3 | 5 | 1436.65 | 927.16 | 39.61 | 469.88 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24280162100 |  | 501339646 |  | 6688224D | 2294139 |  |  | 563 | EX | 99 2" P SHORT 2ND | 2600B | MILL | 55 MILL RD | 073 | FRA | 2024-09-09 | U461322 | U120250 | 2024-08-13 | 2024-08-15 | 2024-09-06 |  | STEVE CANOY | 2024-09-09 | 2024-08-28 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 24 | 3 | 6720.28 | 1617.22 | 0 | 927.82 | 4175.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24280443600 |  | 100295492 |  | 6716216K |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BRIARWOOD | 1130 BRIARWOOD DR | 067 | LEX | 2024-10-03 | U124604 | U124604 | 2024-08-14 | 2025-02-12 | 2026-08-31 |  | HMCKUNE | 2024-10-02 | 2024-09-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.0833 | 3 | 949.13 | 503.02 | 250.18 | 195.93 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24280445000 |  | 100278776 |  | 6688232O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | TECUMSEH | 109 TECUMSEH TL | 073 | FRA | 2024-11-09 | U128410 | U124604 | 2024-08-14 | 2025-02-13 | 2026-08-31 |  | CDESPAIN | 2024-11-09 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 16 | 3 | 1364.85 | 1231.52 | 0 | 74.13 | 59.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24280740900 |  | 100443385 |  | 6712212D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | WESTLAND | 764 WESTLAND DR | 067 | LEX | 2024-10-07 | U123688 | U124604 | 2024-08-15 | 2025-02-14 | 2026-08-31 |  | RSTRONG | 2024-10-03 | 2024-10-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.9167 | 5 | 952.27 | 1158.67 | 0 | -206.4 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24280741200 |  | 100299765 |  | 6716212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | FOX INDUSTRIAL | 735 FOX INDUSTRIAL RD | 067 | LEX | 2024-11-13 | U141668 | U124604 | 2024-08-15 | 2025-02-14 | 2026-08-31 |  | TROE | 2024-11-12 | 2024-09-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 31.5833 | 7 | 3796.45 | 2050.85 | 508.31 | 123.29 | 1114 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24280741400 |  | 100412808 |  | 6712212G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | YARMOUTH | 2298 YARMOUTH CT | 067 | LEX | 2024-10-23 | U124604 | U124604 | 2024-08-15 | 2025-02-14 | 2026-08-31 |  | HSTANFI | 2024-10-22 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.95 | 3 | 5130.23 | 674.74 | 4369.75 | 41.34 | 44.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24280742300 |  | 100302369 |  | 6712212G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | KELSEY | 1163 KELSEY DR | 067 | LEX | 2024-10-31 | U124604 | U124604 | 2024-08-15 | 2025-02-14 | 2026-08-31 |  | TROE | 2024-10-30 | 2024-10-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16 | 2 | 1300.67 | 1014.82 | 223.69 | 62.16 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24280986900 |  | 500490559 |  | 6732244H | 9509037 |  |  | 563 | EX | 99 1" P LONG | 2621P | US HIGHWAY 27 | 4503 US HIGHWAY 27 S | 097 | CYN | 2024-09-09 | U124604 | U134375 | 2024-08-16 | 2024-08-30 | 2024-09-16 |  | NRICHIE | 2024-09-06 | 2024-08-30 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 15.75 | 5 | 2580.09 | 1132.09 | 264.47 | 573.03 | 610.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24280995500 |  | 500038013 |  | 6724208M |  |  |  | 566 | EX | SERVICE LINE ABANDON | 2621P | RICHMOND | 3380 RICHMOND RD | 067 | LEX | 2024-09-06 | U124604 | U124604 | 2024-08-16 | 2024-12-31 |  |  | RSTRONG | 2024-09-05 | 2024-08-23 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 31.2167 | 10 | 5023.81 | 1913.47 | 0 | 247.27 | 2863.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24281227700 |  | 501149185 |  | 6712216H | 1423520 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | LUCILLE | 501 LUCILLE DR | 067 | LEX | 2024-09-05 | U123111 | U129531 | 2024-08-19 | 2024-08-22 | 2024-09-05 |  | LYN STAFFORD | 2024-09-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1922.75 | 0 | 338.34 | 0 | 1584.41 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24281232500 |  | 100326784 |  | 6720208I |  |  |  | 565 | EX | SERVICE LINE - REPAIR | 2621P | HAMPSHIRE | 1404 HAMPSHIRE PL | 067 | LEX | 2024-09-04 | U123688 | U123688 | 2024-08-19 | 2024-12-31 |  |  | KKINDER | 2024-09-03 | 2024-08-26 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 32.8 | 6 | 2470.93 | 1776.65 | 593.43 | 100.85 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24281256700 |  | 501358729 |  | 6700212O | 2398395 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | ABINGDON | 561 ABINGDON AV | 239 | VER | 2024-09-05 | U123111 | U126856 | 2024-08-19 | 2024-08-22 | 2024-09-05 |  | LYN STAFFORD | 2024-09-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4 | 1 | 3947.31 | 262.58 | 338.34 | 14.96 | 3331.43 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24281503400 |  | 100349130 |  | 6748208M |  |  |  | 566 | EX | ABANDON CUST RQST | 2621P | ASHLAND | 20 ASHLAND AV | 049 | WIN | 2025-04-01 | U930915 | U123688 | 2024-08-20 | 2024-12-31 |  |  | NRICHIE | 2025-04-01 | 2024-08-30 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9.9333 | 5 | 741.03 | 699.52 | 0 | 41.51 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24281506200 |  | 501346182 |  | 6728208I | 2396366 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | STOLEN HORSE | 3521 STOLEN HORSE TC LT77 | 067 | LEX | 2024-09-05 | U123111 | U130192 | 2024-08-20 | 2024-08-22 | 2024-09-05 |  | LYN STAFFORD | 2024-09-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 2134.21 | 262.58 | 317.6 | 14.96 | 1539.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24281509900 |  | 501320883 |  | 6728208I | 2182500 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | ANGUS | 1389 ANGUS TL LT52 | 067 | LEX | 2024-09-05 | U123111 | U130192 | 2024-08-20 | 2024-08-22 | 2024-09-05 |  | LYN STAFFORD | 2024-09-05 | 2024-09-03 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4013.51 | 525.13 | 338.34 | 29.96 | 3120.08 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24281538700 |  | 100275618 |  | 6684228F |  |  |  | 566 | EX | ABANDON SL/ DEMO CUST REQ | 2621P | BRAWNER | 816 BRAWNER ST | 073 | FRA | 2024-10-07 | U123688 | U139381 | 2024-08-20 | 2024-09-10 | 2024-10-02 |  | EFGOINS | 2024-10-03 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8.3333 | 2 | 515.97 | 486.18 | 0 | 29.79 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24281539300 |  | 100275619 |  | 6684228F |  |  |  | 566 | EX | ABANDON SL/ DEMO CUST REQ | 2621P | BRAWNER | 816< BRAWNER ST 2F | 073 | FRA | 2024-10-03 | EFGOINS | U139381 | 2024-08-20 | 2024-09-10 | 2024-10-02 |  | EFGOINS | 2024-10-03 | 2024-08-30 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 4.5667 | 4 | 323.05 | 306.42 | 0 | 16.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24281579900 |  | 100302697 |  | 6712212K | 1635077 |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2621D | CALUMET | 116 CALUMET TR | 067 | LEX | 2025-01-30 | U130722 | AOC SYST | 2024-08-20 | 2025-12-31 | 2025-12-31 |  | MCRAIG | 2025-01-24 | 2024-08-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 25.4667 | 6 | 1719.73 | 1377.59 | 0 | 288.86 | 53.28 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24281759800 |  | 100347936 |  | 6748208I |  |  |  | 563 | EX | 99 1"P LONG/NO PRMT REQ | 2600B | MAIN | 614 N MAIN ST | 049 | WIN | 2024-09-05 | U461516 | U132253 | 2024-08-21 | 2024-08-22 | 2024-09-05 |  | NEAL P JOHNSON | 2024-09-04 | 2024-09-04 | 2024-09-04 | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 3.2 | 1 | 3391.42 | 210.58 | 505.39 | 214.35 | 2461.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24281763100 |  | 501313793 |  | 6716232B | 2289995 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | OAK HILL | 104 OAK HILL LN | 209 | GEO | 2024-09-11 | U461516 | U126856 | 2024-08-21 | 2024-08-22 | 2024-09-05 |  | NEAL P JOHNSON | 2024-09-04 | 2024-09-04 | 2024-09-04 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 6.35 | 2 | 4466.41 | 415.89 | 304.84 | 143.86 | 3601.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24281767200 |  | 501320889 |  | 6728208I | 2182500 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | TWILIGHT SHADO | 1223 TWILIGHT SHADO DR | 067 | LEX | 2024-09-03 | U461516 | U126856 | 2024-08-21 | 2024-08-22 | 2024-09-05 |  | NEAL P JOHNSON | 2024-09-03 |  | 2024-09-03 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 2.5833 | 1 | 3620.63 | 171.09 | 311.23 | 9.77 | 3128.54 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24281803900 |  | 501052289 |  | 6744204A | 1854627 | U461383 |  | 563 | EX | INSTALL 1"PMMP SL W/700 EFV | 2600B | RUNNYMEADE | 287 RUNNYMEADE DR | 049 | WIN | 2024-09-24 | U126602 | U461383 | 2024-08-21 | 2024-09-13 | 2024-09-13 |  | DEREK PAYTON | 2024-09-16 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 8 | 1 | 4184.78 | 526.79 | 262.41 | 30.05 | 3365.53 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24281816700 |  | 501319187 |  | 6740204H | 2177603 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | BELLA SHAE | 116 BELLA SHAE WY | 049 | WIN | 2024-09-05 | U461516 | U126856 | 2024-08-21 | 2024-08-22 | 2024-09-05 |  | NEAL P JOHNSON | 2024-09-04 | 2024-09-04 | 2024-09-04 | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 7.45 | 2 | 2618.62 | 492.21 | 311.22 | 274.71 | 1540.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24281817000 |  | 501318802 |  | 6728208F | 2180892 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | BAY SPRING | 3596 BAY SPRING PK | 067 | LEX | 2024-09-03 | U461516 | U126856 | 2024-08-21 | 2024-08-22 | 2024-09-05 |  | NEAL P JOHNSON | 2024-09-03 |  | 2024-09-03 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4.4167 | 1 | 1699.1 | 289.54 | 311.23 | 16.51 | 1081.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24281841100 |  | 501312446 |  | 67122204J | 2179617 |  |  | 563 | EX | 1" P SHORT KERWIN HOMES | 2600B | LONGRIDGE | 114 LONGRIDGE DR | 113 | NIC | 2024-09-05 | U128336 | U134341 | 2024-08-21 | 2024-08-26 | 2024-09-09 |  | JOSHUA COX | 2024-09-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4068.55 | 540.57 | 281.43 | 30.84 | 3215.71 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24282013700 |  | 100301712 |  | 6712212H |  |  |  | 565 | EX | SERVICE LINE REPLACE | 2621P | NEWCASTLE | 133 NEWCASTLE ST | 067 | LEX | 2024-09-26 | MCRAIG | U124604 | 2024-08-22 | 2024-12-31 |  |  | MCRAIG | 2024-09-26 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.85 | 3 | 1824.87 | 1091.57 | 665.31 | 67.99 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24282019100 |  | 100257209 |  | 7348264F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RACELAND | 824< RACELAND AV | 089 | RAC | 2024-10-03 | MCOLLET | U123688 | 2024-08-22 | 2024-12-31 |  |  | MCOLLET | 2024-10-03 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 14.3333 | 2 | 2175.32 | 934.59 | 20.28 | -59.55 | 1280 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24282069300 |  | 501313791 |  | 6716232B | 2289995 |  |  | 563 | EX | 99-1"P- LONG ATKINS BUILDERS | 2600B | OAK HILL | 108 OAK HILL LN LT16 | 209 | GEO | 2024-09-10 | U461516 | U128727 | 2024-08-22 | 2024-08-26 | 2024-09-09 |  | NEAL P JOHNSON | 2024-09-09 | 2024-09-09 | 2024-09-09 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 3.6333 | 1 | 3963.45 | 241.51 | 311.22 | 245.86 | 3164.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24282079700 |  | 500518372 |  | 6712204H | 2404724 |  |  | 563 | EX | 1"P-LONG/NO PRMT REQ | 2600B | RETRAC | 479 RETRAC RD | 067 | LEX | 2024-09-09 | U123111 | U128727 | 2024-08-22 | 2024-08-26 | 2024-09-09 |  | LYN STAFFORD | 2024-09-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 4520.32 | 262.58 | 338.34 | 14.96 | 3904.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24282082100 |  | 500089303 |  | 16708204L |  |  |  | 563 | EX | 99 1"P LONG/NO PRMT REQ | 2600B | SUMMERTREE | 68 SUMMERTREE DR LT21B | 113 | NIC | 2024-09-06 | U123111 | U128266 | 2024-08-22 | 2024-08-26 | 2024-09-09 |  | LYN STAFFORD | 2024-09-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4470.35 | 525.13 | 338.34 | 29.96 | 3576.92 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24282247900 |  | 501309054 |  | 6712228I |  |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | COMPASS | 114 COMPASS TL | 209 | GEO | 2024-09-09 | U461516 | U126856 | 2024-08-23 | 2024-08-26 | 2024-09-09 |  | NEAL P JOHNSON | 2024-09-09 |  | 2024-09-09 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 2.2333 | 1 | 2146.5 | 146.08 | 311.22 | 148.72 | 1540.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24282255200 |  | 100311950 |  | 6716208I |  |  |  | 565 | EX | REPLACE/RELOCATE SERVICE LINE | 2621P | LAMONT | 487 LAMONT DR | 067 | LEX | 2024-10-25 | RSTRONG | U123688 | 2024-08-23 | 2024-12-31 |  |  | RSTRONG | 2024-10-25 | 2024-09-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 31.8833 | 8 | 3261.71 | 1742.53 | 0 | -37.65 | 1556.83 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24282255700 |  | 501121112 |  | 6696212-P |  |  |  | 566 | EX | ABANDON S/L - ALL ELETRIC | 2621P | STOURBRIDGE | 1150 STOURBRIDGE | 239 | VER | 2024-10-01 | U128410 | U123688 | 2024-08-23 | 2024-12-31 |  |  | CDESPAIN | 2024-10-01 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 14.4 | 2 | 2391.75 | 939.37 | 0 | 386.38 | 1066 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24282259100 |  | 501313790 |  | 6716232B |  |  |  | 563 | EX | 1"P LONG ATKINS HOMES | 2600B | OAK HILL | 110 OAK HILL LN LT15 | 209 | GEO | 2024-09-10 | U461516 | U128266 | 2024-08-23 | 2024-08-26 | 2024-09-09 |  | NEAL P JOHNSON | 2024-09-09 | 2024-09-09 | 2024-09-09 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 2.1333 | 1 | 3645.69 | 139.51 | 306.13 | 142.01 | 3058.04 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24282262200 |  | 100349773 |  | 6744208P | 2407495 |  |  | 563 | EX | 1" PL SHORT | 2600B | HIGHLAND | 225 S HIGHLAND ST | 049 | WIN | 2024-09-06 | U461516 | U125753 | 2024-08-23 | 2024-08-26 | 2024-09-09 |  | NEAL P JOHNSON | 2024-09-06 |  | 2024-09-06 | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 8 | 1 | 3418.34 | 526.43 | 272.32 | 535.92 | 2083.67 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24282273500 |  | 501314609 |  | 7336428B | 2180965 |  |  | 563 | EX | 1" P LONG | 2621P | BRIDGEVILLE | 623 BRIDGEVILLE RD | 023 | GER | 2024-09-11 | U124604 | U132256 | 2024-08-23 | 2024-09-20 | 2024-09-20 |  | SDADAMS | 2024-09-10 | 2024-08-30 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26320011 | 28.4667 | 5 | 8244 | 1917.81 | 435.74 | 212.88 | 5677.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24282298500 |  | 501291212 |  | 6712204J | 1967246 |  |  | 563 | EX | 20 1" P SHORT KERWIN HMS | 2600B | BLUE WING PASS | 101 BLUE WING PASS LT4 | 113 | NIC | 2024-09-06 | U128336 | U132805 | 2024-08-23 | 2024-08-26 | 2024-09-09 |  | JOSHUA COX | 2024-09-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4820.66 | 540.57 | 290.68 | 30.84 | 3958.57 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24282460000 |  | 100433807 |  | 7240280F |  |  |  | 563 | EX | 1" P LONG | 2621P | BROOKSVILLE GE | 6226 BROOKSVILLE GE | 023 | GER | 2024-09-16 | U124604 | U132256 | 2024-08-26 | 2024-09-24 | 2024-09-24 |  | SDADAMS | 2024-09-13 | 2024-09-09 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26320011 | 32.0833 | 7 | 9078.36 | 2120.21 | 348.18 | 120.94 | 6489.03 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24282461900 |  | 501317385 |  | 6716236J | 2178365 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | FLAMINGO | 101 FLAMINGO CR | 209 | GEO | 2024-09-11 | U126602 | U126856 | 2024-08-26 | 2024-08-29 | 2024-09-12 |  | DEREK PAYTON | 2024-09-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 1831.76 | 0 | 287.05 | 0 | 1544.71 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24282541800 |  | 100294684 |  | 6716212D |  |  |  | 566 | EX | ABANDON SL/ ELECTRIC CUST REQ | 2621P | JEFFERSON | 514 JEFFERSON ST | 067 | LEX | 2024-09-19 | TROE | U139381 | 2024-08-26 | 2024-09-16 | 2024-10-08 |  | TROE | 2024-09-19 | 2024-09-19 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 19.65 | 4 | 1382.75 | 1294.57 | 14.34 | 73.84 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24282548400 |  | 100295671 |  | 6716216K |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | BOXWOOD | 917 BOXWOOD CT | 067 | LEX | 2024-11-12 | U141668 | U123688 | 2024-08-26 | 2024-12-31 |  |  | MCRAIG | 2024-11-11 | 2024-11-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 26.3833 | 4 | 2650.06 | 1708.9 | 217.19 | 635.17 | 88.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24282551100 |  | 100295658 |  | 6716216K |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | BOXWOOD | 1164 BOXWOOD DR | 067 | LEX | 2024-09-24 | TROE | U123688 | 2024-08-26 | 2024-12-31 |  |  | TROE | 2024-09-24 | 2024-09-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 30.8667 | 6 | 2817.57 | 1799.94 | 914.97 | 102.66 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24282675700 |  | 501343713 |  | 6716220M | 2394864 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | MARLENA | 1216 MARLENA LN | 067 | LEX | 2024-09-10 | U123111 | U126856 | 2024-08-27 | 2024-08-29 | 2024-09-12 |  | LYN STAFFORD | 2024-09-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 3788.76 | 262.58 | 338.34 | 14.96 | 3172.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24282675900 |  | 501343674 |  | 6716220M | 2394864 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | MARLENA | 1217 MARLENA LN | 067 | LEX | 2024-09-10 | U123111 | U126856 | 2024-08-27 | 2024-08-29 | 2024-09-12 |  | LYN STAFFORD | 2024-09-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 1699.11 | 262.58 | 338.34 | 14.96 | 1083.23 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24282687100 |  | 100240633 |  | 7328284D | 2407078 |  |  | 563 | EX | 1"P LONG | 2621P | KEITH | 74 KEITH ST | 089 | S S | 2024-09-09 | U124604 | U132253 | 2024-08-27 | 2024-09-10 | 2024-09-24 |  | RECUMP | 2024-09-06 | 2024-09-05 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 20.0333 | 4 | 1726.62 | 1279.19 | 288.7 | 158.73 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24282718700 |  | 501348633 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | CLEMATIS | 2216 CLEMATIS WY | 067 | LEX | 2024-09-17 | U461309 | U126856 | 2024-08-27 | 2024-08-29 | 2024-09-12 |  | RANDALL HUMPHREYS | 2024-09-12 | 2024-09-12 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4570.39 | 522.76 | 287.05 | 639.09 | 3121.49 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24282719000 |  | 501334694 |  | 6716216E | 2290521 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | CALENDULA | 2312 CALENDULA RD | 067 | LEX | 2024-09-10 | U461516 | U126856 | 2024-08-27 | 2024-08-29 | 2024-09-12 |  | NEAL P JOHNSON | 2024-09-10 |  | 2024-09-10 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4780.51 | 526.43 | 300.05 | 535.92 | 3418.11 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24283090500 |  | 501338353 |  | 6716232B | 2179247 |  |  | 563 | EX | 99-1"P- LONG BALL HOMES | 2600B | DUNMORE | 152 DUNMORE LN LT221 | 209 | GEO | 2024-09-11 | U123111 | U128727 | 2024-08-28 | 2024-08-29 | 2024-09-12 |  | LYN STAFFORD | 2024-09-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 3986.64 | 525.13 | 325.57 | 29.96 | 3105.98 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24283092300 |  | 501327355 |  | 6716232B | 2179247 |  |  | 563 | EX | 99-1"P-SHORT BALL HOMES | 2600B | GALWAY | 118 GALWAY LN LT230 | 209 | GEO | 2024-09-25 | U126602 | U128727 | 2024-08-28 | 2024-08-29 | 2024-09-12 |  | DEREK PAYTON | 2024-09-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 1866.91 | 0 | 319.38 | 0 | 1547.53 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24283093000 |  | 501327356 |  | 6716232B | 2179247 |  |  | 563 | EX | 99-1"P-SHORT BALL HOMES | 2600B | GALWAY | 116 GALWAY LN LT231 | 209 | GEO | 2024-09-25 | U126602 | U128727 | 2024-08-28 | 2024-08-29 | 2024-09-12 |  | DEREK PAYTON | 2024-09-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 10 | 1 | 2636.58 | 658.48 | 384.55 | 37.56 | 1555.99 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24283102600 |  | 501347973 |  | 6696212P | 2292756 |  |  | 563 | EX | 1' P SHORT: YEARLING PROP | 2600B | SAFFRON | 521 SAFFRON LN LT23 | 239 | VER | 2024-09-12 | U461516 | U133050 | 2024-08-28 | 2024-08-29 | 2024-09-12 |  | NEAL P JOHNSON | 2024-09-12 |  | 2024-09-12 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 7.9 | 1 | 2432.28 | 519.87 | 311.23 | 529.23 | 1071.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24283114400 |  | 501356945 |  | 6712204E | 2397231 |  |  | 563 | EX | 1' P LONG/NO PRMT REQ | 2600B | BELLERIVE | 808 BELLERIVE BV LT27 | 113 | NIC | 2024-09-11 | U461516 | U133050 | 2024-08-28 | 2024-08-29 | 2024-09-12 |  | NEAL P JOHNSON | 2024-09-11 |  | 2024-09-11 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 3929.68 | 526.43 | 351.62 | 535.92 | 2515.71 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24283128000 |  | 500534609 |  | 6684228I |  |  |  | 566 | EX | ABANDON SL/ DEMO CUST REQ | 2621P | RIVER BEND | 1001 RIVER BEND RD 2 | 073 | FRA | 2024-09-17 | U930915 | U139381 | 2024-08-28 | 2024-09-18 | 2024-10-10 |  | EFGOINS | 2024-09-17 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 11.9 | 2 | 2076.57 | 786.38 | 0 | 44.86 | 1245.33 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24283128800 |  | 500553260 |  | 6684228I |  |  |  | 566 | EX | ABANDON SL/ DEMO CUST REQ | 2621P | RIVER BEND | 1001 RIVER BEND RD 1 | 073 | FRA | 2024-09-17 | EFGOINS | U139381 | 2024-08-28 | 2024-09-17 | 2024-10-10 |  | EFGOINS | 2024-09-17 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.066667 | 2 | 335.33 | 3.98 | 0 | 0.23 | 331.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24283135400 |  | 100300036 |  | 6716212B |  |  |  | 566 | EX | ABANDON SL/ DEMO CUST REQ | 2621P | HENTON | 104< HENTON RD | 067 | LEX | 2024-09-30 | MCRAIG | U139381 | 2024-08-28 | 2024-09-17 | 2024-10-10 |  | MCRAIG | 2024-09-30 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 18.9333 | 3 | 1492.21 | 1254.44 | 39.61 | 198.16 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24283141400 |  | 500376696 |  | 7244280E | 2408032 |  |  | 563 | EX | 1" P SHORT | 2621P | KY HIGHWAY 10 | 4197 KY HIGHWAY 10 | 161 | DOV | 2024-09-16 | U124604 | U132258 | 2024-08-28 | 2024-08-29 | 2024-09-11 |  | SDADAMS | 2024-09-13 | 2024-09-09 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26320011 | 32.8 | 6 | 2871.88 | 2193.72 | 342.44 | 335.72 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24283170300 |  | 501370851 |  | 6684228N | 0780931 |  |  | 563 | EX | 1"P SHORT MASTER | 2600B | BERRY HILL | 2004 BERRY HILL DR | 073 | FRA | 2024-09-13 | U461516 | U128266 | 2024-08-28 | 2024-08-30 | 2024-09-13 |  | NEAL P JOHNSON | 2024-09-13 | 2024-09-12 | 2024-09-13 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBMAN |  | 100 | 056332B26230012 | 4.4167 | 2 | 2458.58 | 289.56 | 311.22 | 294.76 | 1563.04 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24283174300 |  | 501370853 |  | 6684228N | 0780931 |  |  | 563 | EX | MANIFOLD W/501370851 | 2600B | BERRY HILL | 2006 BERRY HILL DR | 073 | FRA | 2024-09-13 | U461516 | U128266 | 2024-08-28 | 2024-08-30 | 2024-09-13 |  | NEAL P JOHNSON | 2024-09-13 |  | 2024-09-13 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBMAN |  | 100 | 056332B26230012 | 3.6833 | 1 | 936.91 | 243.46 | 145.58 | 247.85 | 300.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24283383200 |  | 100326238 |  | 6704212L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D506596 | 2621P | WESTMORLAND | 2587 WESTMORLAND DR | 067 | LEX | 2024-09-20 | U124604 | U123688 | 2024-08-29 | 2025-02-28 | 2026-08-31 |  | KKINDER | 2024-09-19 | 2024-09-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.8333 | 3 | 1482.55 | 1185.72 | 229.21 | 67.62 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24283397400 |  | 100317445 |  | 6716204J |  |  |  | 563 | EX | 1" P LONG | 2600B | KENLOCK | 252 KENLOCK DR | 067 | LEX | 2024-09-16 | U123111 | U130192 | 2024-08-29 | 2024-08-30 | 2024-09-13 |  | LYN STAFFORD | 2024-09-16 | 2024-09-13 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 12 | 2 | 5598.78 | 785.34 | 360.3 | 654.05 | 3799.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24283400300 |  | 501370866 |  | 6716220N | 0573035 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | KEARNEY CREEK | 2720 KEARNEY CREEK RD | 067 | LEX | 2024-09-12 | U123111 | U127708 | 2024-08-29 | 2024-08-30 | 2024-09-13 |  | LYN STAFFORD | 2024-09-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 2150.64 | 262.58 | 325.57 | 14.96 | 1547.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24283400400 |  | 501370867 |  | 6716220N | 0573035 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | KEARNEY CREEK | 2716 KEARNEY CREEK RD | 067 | LEX | 2024-09-12 | U123111 | U127708 | 2024-08-29 | 2024-08-30 | 2024-09-13 |  | LYN STAFFORD | 2024-09-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 2140.85 | 262.58 | 338.34 | 14.96 | 1524.97 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24283422400 |  | 501028114 |  | 7356152E | 2404396 |  |  | 563 | EX | TAP W MAIN 24-0263336-00 | 2600B | CHERRY | 111 CHERRY ST | 071 | HAR | 2024-09-11 | U123965 | U129294 | 2024-08-29 | 2024-09-16 | 2024-09-16 |  | CJH JORDAN HIERONIMUS | 2024-09-11 |  |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBTWM |  | 100 | 056332B26330012 | 4.25 | 2 | 1466.15 | 294.97 | 0 | 71.86 | 1099.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24283447400 |  | 100453295 |  | 6716212F |  |  |  | 566 | EX | ABANDON SL- DEMO | 2621P | VERSAILLES | 1318 VERSAILLES RD | 067 | LEX | 2024-09-19 | U124604 | U123688 | 2024-08-29 | 2024-09-13 | 2024-09-13 |  | RSTRONG | 2024-09-18 | 2024-09-16 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 17.75 | 5 | 1225.73 | 1090.42 | 39.61 | 95.7 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24283581100 |  | 100256809 |  | 7348264B |  |  |  | 565 | EX | REPLACE SL | 2621P | POND RUN | 402 POND RUN RD | 089 | RAC | 2025-05-01 | RECUMP | U132625 | 2024-08-30 | 2024-08-30 |  |  | RECUMP | 2025-05-01 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 11.2333 | 2 | 4179.4 | 753.25 | 35.4 | 199.72 | 3191.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24283593900 |  | 501346178 |  | 6728208I | 2396366 |  |  | 563 | EX | 1" P LONG MCCARTY | 2600B | STOLEN HORSE | 3512 STOLEN HORSE TC LT73 | 067 | LEX | 2024-09-16 | U461322 | U132258 | 2024-08-30 | 2024-09-06 | 2024-09-19 |  | STEVE CANOY | 2024-09-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 6.35 | 1 | 4031.76 | 430.37 | 0 | 426.1 | 3175.29 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24283746000 |  | 100417690 |  | 6720208H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D304035 | 2621P | HEDGEWOOD | 215 HEDGEWOOD CT | 067 | LEX | 2024-09-16 | U124604 | U123688 | 2024-09-03 | 2024-09-03 | 2024-09-20 |  | HMCKUNE | 2024-09-13 | 2024-09-12 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.1167 | 5 | 1687.59 | 1286.17 | 296.42 | 105 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24283746700 |  | 100417689 |  | 6720208H |  |  |  | 565 | VO | REPLACE SERVICE LINE - D304036 | 2621P | HEDGEWOOD | 213 HEDGEWOOD CT | 067 | LEX | 2024-09-25 | HMCKUNE | U123688 | 2024-09-03 | 2024-09-03 | 2024-09-20 |  | HMCKUNE | 2024-09-13 | 2024-09-09 |  | A | [11 empty] | 24287404200 | 100 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24283754100 |  | 501370889 |  | 6716208J |  |  |  | 563 | EX | PAPER MANIFOLD W/100458186 | 2600B | LOWRY | 171 W LOWRY LN 136 | 067 | LEX | 2024-09-04 | U123688 | U130192 | 2024-09-03 | 2024-09-17 | 2024-09-17 |  | OFFICE | 2024-09-04 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26210011 |  | 1
KY | KY - EAST | 2631 | 24283764600 |  | 501368577 |  | 7356248HA |  |  |  | 563 | EX | 99 1" P LONG | 2621P | EWING | 10570 EWING LN | 019 | CAT | 2024-10-01 | U129534 | U134375 | 2024-09-03 | 2024-09-17 | 2024-10-01 |  | MCOLLET | 2024-09-30 | 2024-09-18 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 32.7333 | 5 | 4173.46 | 2246.96 | 0 | 1926.5 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24283765600 |  | 100275032 |  | 6684228J |  |  |  | 566 | EX | ABANDON SL/ DEMO CUST REQ | 2621P | WILKINSON | 108 WILKINSON ST | 073 | FRA | 2024-10-02 | EFGOINS | U139381 | 2024-09-03 | 2024-09-23 | 2024-10-15 |  | EFGOINS | 2024-10-02 | 2024-09-20 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 19.6333 | 4 | 1250.91 | 1179.65 | 0 | 71.26 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24283771600 |  | 100254460 |  | 7348264J |  |  |  | 563 | EX | 99 1" P LONG | 2621P | MARTIN | 1612 MARTIN ST | 089 | FLA | 2024-10-25 | U123688 | U120250 | 2024-09-03 | 2024-09-17 | 2024-10-23 |  | MCOLLET | 2024-10-24 | 2024-09-18 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 28.7333 | 8 | 2458.07 | 1898.67 | 268.77 | 189.99 | 100.64 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24283777300 |  | 100342661 |  | 7240216N |  |  |  | 563 | EX | 1' P LONG | 2621P | ELM | 125 ELM ST | 173 | MT | 2024-09-12 | U124604 | U133050 | 2024-09-03 | 2024-09-04 | 2024-09-17 |  | LCLARK | 2024-09-11 | 2024-09-11 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 16.1833 | 2 | 3306.59 | 1134.25 | 306.28 | 186.06 | 1680 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24283834100 |  | 100296083 |  | 6716216O | 1635077 |  |  | 565 | EX | AOC L1 ATMOS CORR REPL RISER | 2621D | DEPORRES | 992 DEPORRES AV | 067 | LEX | 2024-10-12 | U123688 | AOC SYST | 2024-09-03 | 2024-11-02 | 2024-11-02 |  | TROE | 2024-10-10 | 2024-09-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 14.2 | 3 | 1457.72 | 902.35 | 420.3 | 55.15 | 79.92 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24283953100 |  | 100345857 |  | 6704212M |  |  |  | 565 | EX | REPLACE SERVICE LINE - D514403 | 2621P | GAYBOURNE | 146 GAYBOURNE WY | 239 | VER | 2025-03-11 | U128410 | U123688 | 2024-09-04 | 2025-03-03 | 2026-09-30 |  | CDESPAIN | 2025-03-10 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.65 | 3 | 2257.11 | 1811.06 | 0 | 184.09 | 261.96 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24283953400 |  | 100345868 |  | 6704212M |  |  |  | 565 | EX | REPLACE SERVICE LINE - D514405 | 2621P | HUNTERTOWN | 3851 HUNTERTOWN RD | 239 | VER | 2025-03-03 | U124604 | U123688 | 2024-09-04 | 2025-03-03 | 2026-09-30 |  | BWHITE | 2025-02-28 | 2025-02-26 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 19.2333 | 3 | 3010.74 | 1499.71 | 0 | 452.79 | 1058.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24283961100 |  | 501348102 |  | 6720208E | 2397505 |  |  | 563 | EX | PAPER W/ 100325995 | 2600B | ROMANY | 313 ROMANY RD LAUNDRY | 067 | LEX | 2024-09-04 | U123688 | U129176 | 2024-09-04 | 2024-09-04 | 2024-09-18 |  | OFFICE | 2024-09-04 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26210011 |  | 1
KY | KY - CENTRAL | 2629 | 24283964400 |  | 100405360 |  | 6744184J | 1530442 |  |  | 563 | EX | 1"P-SHORT | 2621P | UNION CITY | 2336 UNION CITY RD | 151 | RIC | 2024-09-18 | U124604 | U128727 | 2024-09-04 | 2024-09-05 | 2024-09-26 |  | LCLARK | 2024-09-17 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 20 | 2 | 7074.82 | 1404.46 | 1331.99 | 861.37 | 3477 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24283965600 |  | 100281755 |  | 6712232O |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HAMILTON | 521 N HAMILTON ST | 209 | GEO | 2024-09-13 | U123688 | U123688 | 2024-09-04 | 2024-12-31 |  |  | DCOLLIN | 2024-09-12 | 2024-09-11 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 22.3 | 4 | 4423.69 | 1452.27 | 321.76 | 165.86 | 2483.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24283966200 |  | 100275488 |  | 6684228F |  |  |  | 566 | EX | ABANDON SL/ DEMO CUST REQ | 2621P | WILSON | 711 WILSON ST | 073 | FRA | 2024-09-13 | U930915 | U139381 | 2024-09-04 | 2024-09-24 | 2024-10-16 |  | EFGOINS | 2024-09-09 | 2024-09-09 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 2.0667 | 5 | 166.12 | 157.14 | 0 | 8.98 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24283966400 |  | 100275487 |  | 6684228F |  |  |  | 566 | EX | ABANDON SL/ DEMO CUST REQ | 2621P | WILSON | 713 WILSON ST | 073 | FRA | 2024-09-13 | JMARSHA | U139381 | 2024-09-04 | 2024-09-24 | 2024-10-16 |  | JMARSHA | 2024-09-13 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 3.8333 | 1 | 258.98 | 245 | 0 | 13.98 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24284000600 |  | 100282980 |  | 6712228B |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HAMILTON | 529 S HAMILTON ST | 209 | GEO | 2024-09-05 | U126309 | U128613 | 2024-09-04 | 2024-09-04 |  |  | JAMIE LYNN | 2024-09-04 | 2024-09-04 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 9.5167 | 2 | 4189.75 | 625.41 | 839.65 | 158.44 | 2566.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24284029200 |  | 100321541 |  | 6720208A |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | ASHLAND | 316 S ASHLAND AV | 067 | LEX | 2024-09-11 | KOBRYAN | U123688 | 2024-09-04 | 2024-12-31 |  |  | KOBRYAN | 2024-09-11 | 2024-09-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 25.3 | 4 | 4641.16 | 3394.58 | 204.45 | 193.63 | 848.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24284186600 |  | 100345877 |  | 6704212M |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D514407 | 2621P | HUNTERTOWN | 3339 HUNTERTOWN RD | 239 | VER | 2025-02-05 | U128410 | U124604 | 2024-09-05 | 2025-05-30 |  |  | CDESPAIN | 2025-02-05 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 17.3667 | 2 | 2080.79 | 1356.6 | 0 | 63.59 | 660.6 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24284187000 |  | 100346056 |  | 6700212J |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D514408 | 2621P | ROAN | 109 ROAN RD | 239 | VER | 2024-12-09 | U124604 | U124604 | 2024-09-05 | 2025-05-30 |  |  | RJCRAWF | 2024-12-07 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 15.9 | 4 | 1630.44 | 1176.87 | 279.75 | 68.74 | 105.08 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24284195200 |  | 100273536 |  | 6680224F |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D514451 | 2621P | SHARON | 146 SHARON RD | 073 | FRA | 2024-11-23 | U128410 | U124604 | 2024-09-05 | 2025-03-04 | 2026-09-30 |  | CDESPAIN | 2024-11-23 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 14.6333 | 3 | 1142.63 | 938.07 | 0 | 52.12 | 152.44 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24284196600 |  | 100273538 |  | 6680224F |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D514453 | 2621P | SHARON | 120 SHARON RD | 073 | FRA | 2025-02-25 | U124604 | U124604 | 2024-09-05 | 2025-03-04 | 2026-09-30 |  | ATWILLI | 2025-02-24 | 2024-11-23 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 17.75 | 5 | 4261.46 | 1294.18 | 194.74 | 534.98 | 2237.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24284211000 |  | 501202041 |  | 6712208N | 2396687 |  |  | 563 | EX | TAP WITH MAIN 501202041 | 2600B | MERRIDEW | 3833 MERRIDEW WY | 067 | LEX | 2024-10-01 | U461309 | U123852 | 2024-09-05 | 2024-10-11 | 2024-10-11 |  | RANDALL HUMPHREYS | 2024-09-30 | 2024-09-20 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBTWM |  | 100 | 056332B26210012 | 6.8333 | 2 | 2824.12 | 450.54 | 287.05 | 456.99 | 1629.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24284237500 |  | 501343677 |  | 6716220M | 2394864 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | MARLENA | 1229 MARLENA LN | 067 | LEX | 2024-09-17 | U461309 | U126856 | 2024-09-05 | 2024-09-06 | 2024-09-19 |  | RANDALL HUMPHREYS | 2024-09-16 | 2024-09-13 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8.5 | 2 | 1958.67 | 556.65 | 287.05 | 31.74 | 1083.23 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24284238700 |  | 100457821 |  | 7352256E |  |  |  | 566 | EX | ABANDON SL/ DEMO CUST REQ | 2621P | NEW BUCKLEY | 1420 W NEW BUCKLEY RD | 019 | ASH | 2024-09-20 | MCOLLET | U139381 | 2024-09-05 | 2024-09-25 | 2024-10-17 |  | MCOLLET | 2024-09-20 | 2024-09-18 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 23.0667 | 5 | 4354.95 | 1622.97 | 20.27 | 1431.71 | 1280 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24284240900 |  | 100273514 |  | 6680224E |  |  |  | 565 | EX | REPLACE SERVICE LINE D304495 | 2621P | DONNA | 109 DONNA DR | 073 | FRA | 2024-09-06 | EFGOINS | U124604 | 2024-09-05 | 2024-09-05 | 2024-09-05 |  | EFGOINS | 2024-09-06 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 22.8667 | 3 | 2466.42 | 1545.78 | 114.46 | 88.18 | 718 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24284242200 |  | 100248028 |  | 7356256I |  |  |  | 563 | EX | 1" P LONG | 2621P | BLACKBURN | 2731 BLACKBURN AV | 019 | ASH | 2024-10-17 | DYOUNG | U132815 | 2024-09-05 | 2024-10-22 | 2024-10-22 |  | MCOLLET | 2024-10-16 | 2024-10-15 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 24.25 | 5 | 4831.88 | 1588.89 | 0 | -209.51 | 3452.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24284248800 |  | 100294145 |  | 6716212E |  |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | UPPER | 661 N UPPER ST | 067 | LEX | 2024-09-19 | U123111 | U130192 | 2024-09-05 | 2024-09-06 | 2024-09-19 |  | LYN STAFFORD | 2024-09-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4604.58 | 525.13 | 348.79 | 29.96 | 3700.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24284263700 |  | 501334612 |  | 6716216E | 2289300 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | GERANIUM | 2313 GERANIUM LN | 067 | LEX | 2024-09-17 | U461309 | U126856 | 2024-09-05 | 2024-09-11 | 2024-09-24 |  | RANDALL HUMPHREYS | 2024-09-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 3.5 | 1 | 1631.79 | 228.74 | 287.05 | 13.03 | 1102.97 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24284413500 |  | 100346086 |  | 6700212I |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D514410 | 2621P | MCDAVID | 233 MCDAVID DR | 239 | VER | 2024-12-09 | U124604 | U124604 | 2024-09-06 | 2025-03-05 | 2026-09-30 |  | MCRAIG | 2024-12-07 | 2024-12-07 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 23.3167 | 6 | 2228.7 | 1527.88 | 543.52 | 89.22 | 68.08 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24284414300 |  | 100346097 |  | 6700212I |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D51441 | 2621P | DALE | 105 DALE AV | 239 | VER | 2025-04-04 | BWHITE | U124604 | 2024-09-06 | 2025-03-05 | 2026-09-30 |  | BWHITE | 2025-04-04 | 2024-12-10 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 38.6333 | 6 | 5514.55 | 2851.96 | 0 | 696.99 | 1965.6 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24284415400 |  | 100273395 |  | 6680224G |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D514457 | 2621P | CEDAR | 107 CEDAR DR | 073 | FRA | 2025-02-04 | U124604 | U124604 | 2024-09-06 | 2025-03-05 | 2026-09-30 |  | DCOLLIN | 2025-02-03 | 2024-12-30 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 37.9333 | 5 | 3922.39 | 3051.23 | 0 | 777.92 | 93.24 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24284416800 |  | 100273526 |  | 6680224F |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D514458 | 2621P | CARLA | 96 CARLA CT | 073 | FRA | 2024-11-20 | U130722 | U124604 | 2024-09-06 | 2025-03-05 | 2026-09-30 |  | HMCKUNE | 2024-11-19 | 2024-11-18 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 21.65 | 5 | 1641.15 | 1345.8 | 0 | 234.67 | 60.68 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24284417100 |  | 100273515 |  | 6680224E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | DONNA | 119 DONNA DR | 073 | FRA | 2024-09-06 | U128410 | U134852 | 2024-09-06 | 2024-09-05 | 2024-09-05 |  | CDESPAIN | 2024-09-06 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 | 16 | 3 | 1148.63 | 1086.66 | 0 | 61.97 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24284420100 |  | 501242572 |  | 7336276J | 1748890 |  |  | 565 | EX | RELOCATE SERVICE LINE | 2621P | ALICE | 43 ALICE ST | 089 | GRE | 2025-05-23 | ABHATFIE | U123688 | 2024-09-06 | 2024-12-31 |  |  | ABHATFIE | 2025-05-23 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 9.3167 | 2 | 1629.44 | 660.49 | 0 | 38.26 | 930.69 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24284421200 |  | 100296153 |  | 6716216O |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | DOMINICAN | 461 DOMINICAN DR | 067 | LEX | 2024-11-06 | U461383 | U124604 | 2024-09-06 | 2025-12-31 |  |  | HSTANFI | 2024-10-25 | 2024-10-24 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.7667 | 5 | 1831.46 | 963.06 | 809.35 | 59.05 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24284427900 |  | 100290274 |  | 6720212B |  |  |  | 566 | EX | ABANDON SL/ DEMO CUST REQ | 2621P | HIGHLAWN | 1415 HIGHLAWN AV | 067 | LEX | 2024-10-04 | RSTRONG | U139381 | 2024-09-06 | 2024-09-26 | 2024-10-18 |  | RSTRONG | 2024-10-04 | 2024-09-30 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 18.55 | 4 | 1035.09 | 1090.22 | 0 | -55.13 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24284450100 |  | 100317380 |  | 6716204F |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | WALHAMPTON | 3821 WALHAMPTON DR | 067 | LEX | 2024-09-06 | RSTRONG | U134852 | 2024-09-06 | 2024-11-02 | 2026-05-31 |  | RSTRONG | 2024-09-06 | 2024-09-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 21.0833 | 4 | 1437.5 | 1119.11 | 229.99 | 88.4 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24284481000 |  | 501370895 |  | 7348248L |  |  |  | 563 | EX | 99 1" P SHORT | 2621P | SUNNY | 11540 SUNNY LN | 019 | ASH | 2024-10-03 | U124604 | U120250 | 2024-09-06 | 2024-09-20 | 2024-10-04 |  | MCOLLET | 2024-10-02 | 2024-09-23 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 22.2667 | 6 | 1824.75 | 1469.94 | 324.34 | 30.47 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24284609100 |  | 100463629 |  | 6688228F |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | VERSAILLES | 197 VERSAILLES RD | 073 | FRA | 2024-09-10 | U124604 | U937740 | 2024-09-09 | 2024-12-20 | 2026-06-30 |  | ATWILLI | 2024-09-09 | 2024-09-05 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 | 22.9167 | 6 | 4800.39 | 3385.96 | 230.42 | 1184.01 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24284611000 |  | 100262889 |  | 7352260O |  |  |  | 566 | EX | ABANDON SL/DEMO CUST REQ | 2621P | HOODS CREEK | 1720 HOODS CREEK PK | 019 | ASH | 2025-01-28 | RECUMP | U139381 | 2024-09-09 | 2024-09-27 | 2024-10-21 |  | RECUMP | 2025-01-28 | 2024-09-23 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 60.5667 | 13 | 7872.83 | 3992.76 | 20.28 | 954.79 | 2905 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24284632300 |  | 501326164 |  | 7356256B | 2286519 |  |  | 563 | EX | MANIFOLD W/100268171 | 2621P | WINCHESTER | 2325 WINCHESTER AV A | 019 | ASH | 2024-09-09 | U123688 | U132253 | 2024-09-09 | 2024-09-23 | 2024-09-23 |  | OFFICE | 2024-09-09 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26310011 |  | 1
KY | KY - EAST | 2631 | 24284633800 |  | 100241420 |  | 7356256G |  |  |  | 563 | EX | 1" P SHORT | 2621P | 31ST | 329 31ST ST | 019 | ASH | 2024-10-07 | U123688 | U129531 | 2024-09-09 | 2024-09-30 | 2024-09-30 |  | RECUMP | 2024-10-04 | 2024-10-01 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 36.95 | 9 | 2430.21 | 2269.71 | 412.04 | -255.98 | 4.44 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24284633900 |  | 100241237 |  | 7356256G |  |  |  | 563 | EX | 1" P SHORT | 2621P | 30TH | 453 30TH ST | 019 | ASH | 2024-09-27 | U123688 | U129531 | 2024-09-09 | 2024-09-30 | 2024-09-30 |  | RECUMP | 2024-09-26 | 2024-09-17 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 38.05 | 7 | 2821.44 | 2430.59 | 0 | 390.85 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24284634300 |  | 501346194 |  | 6728208I | 2396366 |  |  | 563 | EX | 1"P SHORT/NO PRMT REQ | 2600B | STOLEN HORSE | 3473 STOLEN HORSE TC LT89 | 067 | LEX | 2024-09-17 | U461322 | U128727 | 2024-09-09 | 2024-09-11 | 2024-09-24 |  | STEVE CANOY | 2024-09-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2636.41 | 542.2 | 0 | 536.81 | 1557.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24284635300 |  | 501370856 |  | 67162 |  |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | GREENWOOD | 446 GREENWOOD AV | 067 | LEX | 2024-09-23 | U461516 | U128272 | 2024-09-09 | 2024-09-13 | 2024-09-26 |  | NEAL P JOHNSON | 2024-09-23 |  | 2024-09-23 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 5007.47 | 526.43 | 530.41 | 535.92 | 3414.71 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24284638100 |  | 100241238 |  | 7356256G |  |  |  | 563 | EX | 1" P SHORT | 2621P | 30TH | 457 30TH ST | 019 | ASH | 2024-10-01 | U124604 | U129531 | 2024-09-09 | 2024-09-30 | 2024-09-30 |  | RECUMP | 2024-09-30 | 2024-09-26 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 11.8167 | 3 | 1237.37 | 765.73 | 328.76 | 91.08 | 51.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24284653200 |  | 501354375 |  | 6716212N | 2300730 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | LEGION | 340 LEGION DR | 067 | LEX | 2024-09-25 | U126602 | U126856 | 2024-09-09 | 2024-09-13 | 2024-09-26 |  | DEREK PAYTON | 2024-09-17 | 2024-09-17 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2146.03 | 526.79 | 303.66 | 30.05 | 1285.53 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24284661100 |  | 100248568 |  | 7356256I |  |  |  | 566 | EX | ABANDON SL/ DEMO CUST REQ | 2621P | CROOKS | 2231 CROOKS ST | 019 | ASH | 2024-10-22 | LAMAY | U139381 | 2024-09-09 | 2024-09-27 | 2024-10-21 |  | LAMAY | 2024-10-22 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 6.7 | 2 | 423.9 | 406.15 | 20.28 | -2.53 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24284672200 |  | 501347926 |  | 6724204A | 2291616 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | SHADY | 709 SHADY CV | 067 | LEX | 2024-09-19 | U126602 | U126856 | 2024-09-09 | 2024-09-11 | 2024-09-24 |  | DEREK PAYTON | 2024-09-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 5263.93 | 526.79 | 0 | 30.05 | 4707.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24284672500 |  | 501333763 |  | 6724204A | 2185117 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | NIGHT HERON | 3513 NIGHT HERON WY | 067 | LEX | 2024-09-18 | U461309 | U126856 | 2024-09-09 | 2024-09-11 | 2024-09-24 |  | RANDALL HUMPHREYS | 2024-09-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 3369.06 | 0 | 287.05 | 0 | 3082.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24284672900 |  | 501354163 |  | 6724204A | 2185117 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | BAY SHOALS | 3468 BAY SHOALS DR | 067 | LEX | 2024-09-18 | U123111 | U126856 | 2024-09-09 | 2024-09-11 | 2024-09-24 |  | LYN STAFFORD | 2024-09-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4361.46 | 525.13 | 338.95 | 29.96 | 3467.42 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24284679900 |  | 100258989 |  | 7356256A |  |  |  | 563 | EX | -1"P-SHORT | 2621P | MONTGOMERY | 1500 MONTGOMERY AV | 019 | ASH | 2024-10-07 | U123688 | U128727 | 2024-09-09 | 2024-09-10 | 2024-10-08 |  | CWHEELE | 2024-10-04 | 2024-09-23 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 18.6167 | 4 | 1854.96 | 1197.19 | 212.11 | 376.1 | 69.56 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24284831000 |  | 100273410 |  | 6680224G |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D514459 | 2621P | SPRUCE | 109 SPRUCE DR | 073 | FRA | 2024-11-09 | KOBRYAN | U124604 | 2024-09-10 | 2025-03-07 | 2026-09-30 |  | KOBRYAN | 2024-11-09 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 23.3667 | 5 | 1431.73 | 1244.37 | 0 | 74.88 | 112.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24284849700 |  | 501369222 |  | 6720216F |  |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | COSTIGAN | 1856 COSTIGAN DR | 067 | LEX | 2024-09-24 | U126602 | U120250 | 2024-09-10 | 2024-09-13 | 2024-09-26 |  | DEREK PAYTON | 2024-09-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 1974.09 | 526.79 | 274.28 | 30.05 | 1142.97 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24284859100 |  | 100407631 |  | 7348264K |  |  |  | 566 | EX | ABANDON SERV LINE-DEMO | 2621P | WALNUT | 2106 WALNUT ST | 019 | CAT | 2024-11-18 | JCYRUS | U123688 | 2024-09-10 | 2024-12-31 |  |  | JCYRUS | 2024-11-18 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.7 | 2 | 2551.35 | 446.89 | 35.49 | 26.9 | 2042.07 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24284875400 |  | 100273375 |  | 6680224G |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | TULIP | 105 TULIP DR | 073 | FRA | 2024-09-10 | EFGOINS | U139677 | 2024-09-10 | 2024-09-10 | 2024-09-10 |  | EFGOINS | 2024-09-10 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 16.2 | 2 | 2153.95 | 1071.85 | 621 | 61.1 | 400 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24284893900 |  | 100282078 |  | 6712232O | 2406782 |  |  | 563 | EX | 1" PL SHORT/NO PRMT REQ | 2600B | BOURBON | 719 BOURBON ST | 209 | GEO | 2024-09-19 | U126602 | U125753 | 2024-09-10 | 2024-09-13 | 2024-09-26 |  | DEREK PAYTON | 2024-09-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 9.6333 | 2 | 3659.13 | 636.59 | 466.08 | 138.76 | 2417.7 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24284896200 |  | 501370843 |  | 6688228K | 2408238 |  |  | 563 | EX | 2" P SHORT/NO PRMT REQ | 2600B | BRIGHTON PARK | 103 BRIGHTON PARK BV | 073 | FRA | 2024-09-26 | U123111 | U126856 | 2024-09-10 | 2024-09-13 | 2024-09-26 |  | LYN STAFFORD | 2024-09-25 | 2024-09-24 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 29 | 5 | 6799.11 | 2248.02 | 556.78 | 413.22 | 3581.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24284899600 |  | 100441873 |  | 6716212H | 2408081 |  |  | 563 | EX | 1" P LONG- HP ML/NO PRMT REQ | 2600B | HENRY | 321 HENRY ST | 067 | LEX | 2024-09-19 | U461322 | U131378 | 2024-09-10 | 2024-09-13 | 2024-09-26 |  | STEVE CANOY | 2024-09-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 19.2667 | 3 | 4514.46 | 1311.71 | 0 | 722.97 | 2479.78 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24284902600 |  | 500758945 |  | 6740204H | 0039068 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | TEAL | 111 TEAL LN | 049 | WIN | 2024-09-20 | U461322 | U138822 | 2024-09-10 | 2024-09-13 | 2024-09-26 |  | STEVE CANOY | 2024-09-20 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 5.9667 | 1 | 3918.4 | 405.29 | 0 | 401.27 | 3111.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24284903500 |  | 100273353 |  | 6680224G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | WILLOWCREST | 219 WILLOWCREST DR | 073 | FRA | 2024-09-12 | U124604 | U137585 | 2024-09-10 | 2024-09-10 | 2024-09-10 |  | CHERNDO | 2024-09-11 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 35.5333 | 3 | 9264.08 | 2560.37 | 718.05 | 146.06 | 5839.6 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24285054300 |  | 100273411 |  | 6680224G |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D514463 | 2621P | SPRUCE | 201 SPRUCE DR | 073 | FRA | 2024-11-11 | U141668 | U124604 | 2024-09-11 | 2025-03-10 | 2026-09-30 |  | KKINDER | 2024-11-09 | 2024-11-09 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 16 | 4 | 1750.61 | 1200.24 | 346.41 | 72.24 | 131.72 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24285055200 |  | 100273387 |  | 6680224G |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D514466 | 2621P | WILLOWCREST | 214 WILLOWCREST DR | 073 | FRA | 2024-12-09 | U124604 | U124604 | 2024-09-11 | 2025-03-10 | 2026-09-30 |  | KKINDER | 2024-12-07 | 2024-12-07 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 16 | 4 | 1629.21 | 1283.62 | 215.85 | 74.98 | 54.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24285071000 |  | 500187035 |  | 6708204J |  |  |  | 566 | EX | ABANDON SL/ DEMO CUST REQ | 2621P | DELANEY FERRY | 1075 DELANEY FERRY RD | 113 | NIC | 2024-10-09 | KOBRYAN | U139381 | 2024-09-11 | 2024-10-01 | 2024-10-23 |  | KOBRYAN | 2024-10-09 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 22.0833 | 3 | 1401.34 | 1320.46 | 0 | 80.88 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24285074500 |  | 501019595 |  | 7344264L | 2408190 |  |  | 563 | EX | 2" P SHORT | 2600B | FAIRWAY | 1226 FAIRWAY DR LT67 | 089 | FLA | 2025-02-25 | U128523 | U129176 | 2024-09-11 | 2024-12-11 | 2024-12-11 |  | BRANDON ROBERTS | 2025-02-25 | 2024-10-01 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26310012 | 45.65 | 8 | 14689.21 | 3277.83 | 0 | 2473.74 | 8937.64 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24285078700 |  | 100285597 |  | 6768172A |  |  |  | 563 | EX | 20 1" P SHORT | 2621P | BROADWAY | 709 BROADWAY ST | 065 | IRV | 2024-09-24 | U124604 | U132805 | 2024-09-11 | 2024-09-12 | 2024-09-25 |  | LCLARK | 2024-09-23 | 2024-09-19 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 14 | 4 | 2151.59 | 980.33 | 569.98 | 601.28 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24285083000 |  | 501370531 |  | 6764176P |  |  |  | 563 | EX | 99 1"P SHORT | 2621P | TURNER | 294 TURNER AV 7 | 065 | IRV | 2024-10-01 | U129534 | U132253 | 2024-09-11 | 2024-09-25 | 2024-10-09 |  | DENNING | 2024-09-30 | 2024-09-20 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 29.0667 | 4 | 5647.87 | 2021.73 | 440.57 | 234.82 | 2950.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24285084300 |  | 100296257 |  | 6716216O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | DEPORRES | 965 DEPORRES AV | 067 | LEX | 2024-09-12 | U124604 | U139677 | 2024-09-11 | 2025-01-09 | 2026-07-31 |  | TROE | 2024-09-11 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 4.7667 | 2 | 784.35 | 528.07 | 226.17 | 30.11 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24285089200 |  | 100410696 |  | 6716216K |  |  |  | 565 | EX | REPLACE SL | 2621P | REDWOOD | 1193 REDWOOD CR | 067 | LEX | 2024-10-09 | TROE | U124604 | 2024-09-11 | 2024-12-31 |  |  | TROE | 2024-10-09 | 2024-09-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.2167 | 3 | 1193.15 | 877.17 | 262.31 | 53.67 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24285119700 |  | 100259826 |  | 7356256F | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 2202 HILTON AV | 019 | ASH | 2024-09-12 | U123965 | U125763 | 2024-09-11 | 2024-12-31 |  |  | CJH JOSEPH HADLEY | 2024-09-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1552.53 | 0 | 0 | 0 | 1552.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24285133000 |  | 100458115 |  | 6728208C |  |  |  | 566 | EX | ABANDON SL | 2621P | WALNUT GROVE | 2581 WALNUT GROVE LN | 067 | LEX | 2024-11-20 | SSHIMFE | U124604 | 2024-09-11 | 2024-12-31 | 2024-12-31 |  | SSHIMFE | 2024-11-20 | 2024-10-10 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 24.1167 | 10 | 1630.22 | 1499.23 | 39.78 | 91.21 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24285359100 |  | 100345834 |  | 6704212M |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | GLENHAVEN | 10 GLENHAVEN DR | 239 | VER | 2025-03-27 | U128410 | U124604 | 2024-09-12 | 2025-03-11 | 2026-09-30 |  | CDESPAIN | 2025-03-27 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 21.1 | 3 | 1934.24 | 1747.44 | 0 | 102.44 | 84.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24285362300 |  | 501348653 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | CORSAGE | 2208 CORSAGE CT | 067 | LEX | 2024-09-17 | U123111 | U126856 | 2024-09-12 | 2024-09-13 | 2024-09-26 |  | LYN STAFFORD | 2024-09-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 1787.75 | 262.58 | 411.47 | 14.96 | 1098.74 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24285362800 |  | 501224881 |  | 6700228 | 1745078 |  |  | 563 | EX | 1' P SHORT/NO PRMT REQ | 2600B | ROCKY WATERS | 149 ROCKY WATERS WY LT25 | 209 | GEO | 2024-09-18 | U461322 | U133050 | 2024-09-12 | 2024-09-13 | 2024-09-26 |  | STEVE CANOY | 2024-09-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 6.3667 | 1 | 2470.08 | 432.39 | 0 | 428.12 | 1609.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24285369800 |  | 100459878 |  | 6720200D |  |  |  | 566 | EX | ABANDON SL/ DEMO CUST REQ | 2621P | DELONG | 2110 DELONG RD | 067 | LEX | 2024-10-02 | MSHARON | U139381 | 2024-09-12 | 2024-10-02 | 2024-10-24 |  | MSHARON | 2024-10-02 | 2024-09-20 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.8333 | 3 | 848.56 | 779.21 | 21.9 | 47.45 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24285396500 |  | 501055088 |  | 6728212M | 0889351 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | BOBWHITE | 3044 BOBWHITE TR | 067 | LEX | 2024-09-25 | U126602 | U126856 | 2024-09-12 | 2024-09-13 | 2024-09-26 |  | DEREK PAYTON | 2024-09-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 7.3833 | 1 | 4445.15 | 485.97 | 287.05 | 123.09 | 3549.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24285396800 |  | 501088552 |  | 6728208G | 2408636 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | REAL QUIET | 3900 REAL QUIET LN LT42 | 067 | LEX | 2024-09-23 | U123111 | U126856 | 2024-09-12 | 2024-09-13 | 2024-09-26 |  | LYN STAFFORD | 2024-09-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4473.31 | 525.13 | 172.02 | 29.96 | 3746.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24285401900 |  | 501334610 |  | 6716216E | 2289300 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | GERANIUM | 2309 GERANIUM LN | 067 | LEX | 2024-09-17 | U123111 | U126856 | 2024-09-12 | 2024-09-13 | 2024-09-26 |  | LYN STAFFORD | 2024-09-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 1671.25 | 262.58 | 304.84 | 14.96 | 1088.87 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24285426500 |  | 100322797 |  | 6716208D | 2408553 |  |  | 563 | EX | 99 1.25"PSHORT/PRMT RCVD | 2600B | KASTLE | 1257 KASTLE RD | 067 | LEX | 2024-10-09 | U461516 | U120250 | 2024-09-12 | 2024-09-30 | 2024-10-11 |  | NEAL P JOHNSON | 2024-10-09 |  | 2024-10-09 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 3108.63 | 480.26 | 687.45 | 394.8 | 1546.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24285433700 |  | 500089547 |  | 16708204L |  |  |  | 563 | EX | 1" P LONG /NO PERMIT NEEDED | 2600B | BAYWOOD | 219 BAYWOOD DR | 113 | NIC | 2024-10-02 | U461516 | U134341 | 2024-09-12 | 2024-09-19 | 2024-10-02 |  | NEAL P JOHNSON | 2024-10-02 |  | 2024-10-02 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4117.17 | 480.26 | 311.23 | 394.8 | 2930.88 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24285580000 |  | 100265004 |  | 7344264B |  |  |  | 566 | EX | ABANDON SL/ DEMO CUST REQ | 2621P | VIRGINIA | 502 VIRGINIA ST | 019 | ASH | 2024-10-28 | ABHATFIE | U139381 | 2024-09-13 | 2024-10-03 | 2024-10-25 |  | ABHATFIE | 2024-10-28 | 2024-10-28 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 18.5 | 2 | 1244.05 | 1172.26 | 0 | 71.79 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24285624000 |  | 100346399 |  | 6696212L |  |  |  | 565 | VO | REPLACE SERVICE LINE - LEAKAGE | 2621P | MORGAN | 130 MORGAN ST | 239 | VER | 2024-11-14 |  | U123688 | 2024-09-13 | 2024-11-30 |  |  | LSTANFI | 2024-09-06 |  |  | A | [11 empty] | 24295501900 | 100 |  |  | 1 | -71.34 | -63.47 | 0 | -7.87 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24285642700 |  | 100260864 |  | 7352256G |  |  |  | 565 | EX | REPLACE SERVICE LINE - D259733 | 2621P | LADOKA | 3402 LADOKA ST | 019 | ASH | 2024-09-24 | U124604 | U123688 | 2024-09-13 | 2024-09-16 | 2024-10-04 |  | ABHATFIE | 2024-09-24 | 2024-09-16 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 34.35 | 8 | 3857.47 | 2450.41 | 114.94 | 1292.12 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24285788700 |  | 501312440 |  | 67122204J | 2179617 |  |  | 563 | EX | 1" P SHORT/NO PERMIT NEEDED | 2600B | LONGRIDGE | 132 LONGRIDGE DR LT17 | 113 | NIC | 2024-09-26 | U126602 | U132256 | 2024-09-16 | 2024-09-19 | 2024-10-02 |  | DEREK PAYTON | 2024-09-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2397.11 | 526.79 | 289.92 | 30.05 | 1550.35 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24285822100 |  | 100314491 |  | 6716212L |  |  |  | 565 | EX | SERVICE LINE REPLACE | 2621P | MILL | 324 S MILL ST 1F | 067 | LEX | 2024-09-18 | U124604 | U141174 | 2024-09-16 | 2024-09-16 | 2024-09-16 |  | RSTRONG | 2024-09-17 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.6 | 2 | 1296.3 | 1047.84 | 119.59 | 128.87 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24286110100 |  | 100451473 |  | 6748204B |  |  |  | 566 | EX | ABANDON SL/ DEMO CUST REQ | 2621P | POCAHONTAS | 12 POCAHONTAS TL | 049 | WIN | 2024-09-20 | U124604 | U139381 | 2024-09-17 | 2024-10-07 | 2024-10-29 |  | LCLARK | 2024-09-19 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9.2667 | 2 | 1067.07 | 648.86 | 20.27 | 397.94 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24286112800 |  | 100258184 |  | 7352256C |  |  |  | 566 | EX | ABANDON SL/ DEMO CUST REQ | 2621P | 7TH | 312 7TH AV | 089 | WOR | 2024-10-11 | MCOLLET | U139381 | 2024-09-17 | 2024-10-07 | 2024-10-29 |  | MCOLLET | 2024-10-11 | 2024-10-08 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 16.3667 | 4 | 1264.96 | 1072.26 | 45.57 | 147.13 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24286124800 |  | 501317349 |  | 6716236J | 2178365 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | NUTHATCH | 128 NUTHATCH TR | 209 | GEO | 2024-09-25 | U461516 | U126856 | 2024-09-17 | 2024-10-01 | 2024-10-01 |  | NEAL P JOHNSON | 2024-09-25 |  | 2024-09-25 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 6.9333 | 1 | 4362.64 | 457.35 | 323.85 | 465.59 | 3115.85 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286132900 |  | 100306958 |  | 6716212F |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | VERSAILLES | 1322 VERSAILLES RD | 067 | LEX | 2024-09-18 | RSTRONG | U124604 | 2024-09-17 | 2024-10-30 |  |  | RSTRONG | 2024-09-18 | 2024-09-18 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10.2 | 3 | 725.81 | 649.19 | 39.61 | 37.01 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24286145200 |  | 100270358 |  | 6736248A |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | WALNUT | 312 S WALNUT ST | 097 | CYN | 2024-11-18 | NRICHIE | U123688 | 2024-09-17 | 2024-12-31 |  |  | NRICHIE | 2024-11-18 | 2024-11-11 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 11.2833 | 3 | 4279.81 | 882.62 | 32.23 | 229.17 | 3135.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286151300 |  | 501346192 |  | 6728208I | 2396366 |  |  | 563 | EX | 1" P LONG MULBERRY BLDRS | 2600B | STOLEN HORSE | 3516 STOLEN HORSE TC | 067 | LEX | 2024-09-23 | U123111 | U132256 | 2024-09-17 | 2024-09-18 | 2024-10-01 |  | LYN STAFFORD | 2024-09-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 5185.51 | 525.13 | 317.6 | 29.96 | 4312.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286172500 |  | 100336244 |  | 6720212I |  |  |  | 563 | EX | 1' P LONG/PRMT RCVD | 2600B | 3RD | 523 E 3RD ST | 067 | LEX | 2024-10-14 | U461516 | U133050 | 2024-09-17 | 2024-09-30 | 2024-10-11 |  | NEAL JOHNSON | 2024-10-11 |  | 2024-10-11 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 12 | 1 | 8033.01 | 720.4 | 424.79 | 44.14 | 6843.68 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24286175300 |  | 100356776 |  | 7260276C |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | ASH | 1708 ASH ST | 161 | MAY | 2024-09-18 | U124604 | U129939 | 2024-09-17 | 2025-01-29 | 2026-07-31 |  | SDADAMS | 2024-09-17 |  |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26320021 | 1.3 | 2 | 2594.91 | 2073.22 | 403.41 | 118.28 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286186700 |  | 100325053 |  | 6720204B |  |  |  | 565 | EX | REPLACE SERV LINE | 2621P | GAINESWAY | 1200 GAINESWAY DR | 067 | LEX | 2024-09-19 | U124604 | U129939 | 2024-09-17 | 2024-09-17 | 2024-09-17 |  | RJCRAWF | 2024-09-18 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 0.28333 | 1 | 284.41 | 19.57 | 263.71 | 1.13 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24286377500 |  | 100348739 |  | W1102-14 |  |  |  | 563 | EX | 20 1.25" P SHORT | 2600B | PARK | 130 PARK AV | 049 | WIN | 2024-09-26 | U461516 | U132805 | 2024-09-18 | 2024-09-19 | 2024-10-02 |  | NEAL P JOHNSON | 2024-09-25 |  | 2024-09-26 | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 12.5167 | 2 | 3865.25 | 822.55 | 701.17 | 837.36 | 1504.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286415300 |  | 100325530 |  | 6720208E | 2408133 |  |  | 565 | EX | UPGRADE SERVICE LINE | 2621P | INDIAN MOUND | 1182 INDIAN MOUND RD | 067 | LEX | 2024-10-07 | U123688 | U124604 | 2024-09-18 | 2024-10-16 | 2024-10-16 |  | RJCRAWF | 2024-10-03 | 2024-09-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 53.35 | 6 | 6075.65 | 3269.48 | 510.2 | 200.16 | 2095.81 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286420500 |  | 100329559 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | COBURN | 2029 COBURN BV 1 | 067 | LEX | 2025-03-12 | U129731 | U125763 | 2024-09-18 | 2024-12-31 |  |  | EDWARD F GOINS | 2025-03-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 3829.41 | 540.12 | 0 | 31.66 | 3257.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286420700 |  | 100329554 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | COBURN | 2035 COBURN BV 1 | 067 | LEX | 2024-12-19 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-12-19 | 2024-12-18 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.75 | 2 | 9870.52 | 1274.21 | 0 | 620.58 | 7975.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286420800 |  | 100329547 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | COBURN | 2041 COBURN BV 1 | 067 | LEX | 2024-12-17 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-12-17 | 2024-12-16 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.9667 | 2 | 8205.54 | 952.84 | 0 | 499.18 | 6753.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286420900 |  | 100329540 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | COBURN | 2047 COBURN BV WH | 067 | LEX | 2024-12-04 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-12-04 | 2024-12-02 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 27.8333 | 4 | 24819.02 | 2362.68 | 0 | 2345.62 | 20110.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286421000 |  | 100329541 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | COBURN | 2053 COBURN BV | 067 | LEX | 2024-10-11 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-10-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2459.08 | 0 | 191.6 | 0 | 2267.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286421100 |  | 100329485 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | COBURN | 2101 COBURN BV | 067 | LEX | 2024-11-20 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVEV CANOY | 2024-11-20 | 2024-11-19 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.1667 | 2 | 5264.97 | 778.84 | 0 | 74.26 | 4411.87 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286421200 |  | 100329483 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | COBURN | 2105 COBURN BV | 067 | LEX | 2024-11-19 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-11-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.1667 | 1 | 4622.45 | 524.35 | 0 | 213.48 | 3884.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286421300 |  | 100329481 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | COBURN | 2109 COBURN BV | 067 | LEX | 2024-11-18 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-11-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.45 | 1 | 5916 | 555.89 | 0 | 193.31 | 5166.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286421400 |  | 100329478 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | COBURN | 2117 COBURN BV | 067 | LEX | 2024-11-15 | U126530 | U125763 | 2024-09-18 | 2024-12-31 |  |  | JDUNN | 2024-11-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.5 | 1 | 5034.78 | 636.45 | 0 | 38.31 | 4360.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286421500 |  | 100329477 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | COBURN | 2119 COBURN BV | 067 | LEX | 2024-11-13 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-11-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3731.88 | 0 | 0 | 0 | 3731.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286421600 |  | 100329475 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | COBURN | 2123 COBURN BV | 067 | LEX | 2024-11-12 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-11-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.9333 | 1 | 5492.66 | 591.3 | 0 | 35.58 | 4865.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286421700 |  | 100329406 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | COBURN | 2127 COBURN BV | 067 | LEX | 2024-11-07 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-11-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.0167 | 1 | 5794.06 | 424.2 | 0 | 172.73 | 5197.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286421800 |  | 100329404 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | COBURN | 2131 COBURN BV 1 | 067 | LEX | 2024-11-08 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-11-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3372.75 | 0 | 0 | 0 | 3372.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286422000 |  | 100329392 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | COBURN | 2143 COBURN BV | 067 | LEX | 2024-11-07 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-11-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.5333 | 1 | 5066.53 | 133.22 | 0 | 54.25 | 4879.06 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286422100 |  | 100329267 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | RICHMOND | 2051 RICHMOND RD STE 105 | 067 | LEX | 2024-10-23 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-10-22 | 2024-10-21 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.2833 | 2 | 7217.73 | 1112.15 | 0 | 810.78 | 5294.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286422200 |  | 100329269 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | RICHMOND | 2051 RICHMOND RD STE 115 | 067 | LEX | 2024-10-18 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-10-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.1333 | 1 | 4943.53 | 487.68 | 0 | 29.87 | 4425.98 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286422300 |  | 100431691 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | RICHMOND | 2051 RICHMOND RD STE 125 | 067 | LEX | 2024-10-17 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-10-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.5 | 1 | 5894.18 | 718.17 | 0 | 523.55 | 4652.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286422400 |  | 100329273 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | RICHMOND | 2051 RICHMOND RD STE 140 | 067 | LEX | 2024-10-16 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-10-16 | 2024-10-14 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 31.25 | 3 | 16281.78 | 2137.51 | 0 | 1558.21 | 12586.06 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286422500 |  | 100329278 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | RICHMOND | 2121 RICHMOND RD STE 115 | 067 | LEX | 2024-10-11 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-10-11 | 2024-10-10 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.0167 | 2 | 5849.67 | 1026.01 | 0 | 747.94 | 4075.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286422600 |  | 500205421 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | RICHMOND | 2121 RICHMOND RD STE 150 | 067 | LEX | 2024-10-09 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-10-09 | 2024-10-08 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.9167 | 2 | 5776.21 | 747.63 | 0 | 545 | 4483.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286422700 |  | 100329473 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 125 SAINT JAMES DR | 067 | LEX | 2024-11-08 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-11-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.7 | 1 | 3925.6 | 229.95 | 0 | 93.63 | 3602.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286422800 |  | 100329411 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 126 SAINT JAMES DR | 067 | LEX | 2024-11-10 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-11-08 | 2024-11-08 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.9167 | 1 | 4298.47 | 670.21 | 0 | 40.34 | 3587.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286422900 |  | 100329472 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 129 SAINT JAMES DR | 067 | LEX | 2024-11-11 | U126530 | U125763 | 2024-09-18 | 2024-12-31 |  |  | JDUNN | 2024-11-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3584.05 | 0 | 0 | 0 | 3584.05 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286423000 |  | 100329412 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 130 SAINT JAMES DR | 067 | LEX | 2024-11-11 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-11-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2734.4 | 0 | 0 | 0 | 2734.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286423100 |  | 100329471 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 133 SAINT JAMES DR | 067 | LEX | 2024-11-12 | U126530 | U125763 | 2024-09-18 | 2024-12-31 |  |  | JDUNN | 2024-11-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3057.81 | 0 | 0 | 0 | 3057.81 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286423200 |  | 100329413 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 134 SAINT JAMES DR | 067 | LEX | 2024-11-11 | U126530 | U125763 | 2024-09-18 | 2024-12-31 |  |  | JDUNN | 2024-11-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.5 | 1 | 4293.97 | 711.37 | 0 | 42.8 | 3539.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286423300 |  | 100329470 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 137 SAINT JAMES DR | 067 | LEX | 2024-11-14 | U126530 | U125763 | 2024-09-18 | 2024-12-31 |  |  | JDUNN | 2024-11-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9 | 1 | 3996.98 | 673.93 | 0 | 40.55 | 3282.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286423400 |  | 100329414 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 138 SAINT JAMES DR | 067 | LEX | 2024-11-12 | U126530 | U125763 | 2024-09-18 | 2024-12-31 |  |  | JDUNN | 2024-11-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9 | 1 | 2753.48 | 673.93 | 0 | 40.55 | 2039 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286423500 |  | 100329469 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 141 SAINT JAMES DR | 067 | LEX | 2024-11-21 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-11-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.2167 | 1 | 4167.68 | 613.36 | 0 | 249.76 | 3304.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286423600 |  | 100329415 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 142 SAINT JAMES DR | 067 | LEX | 2024-12-20 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-12-20 | 2024-12-03 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.3167 | 2 | 2835.33 | 806.01 | 0 | 129.19 | 1900.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286423700 |  | 100329416 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 146 SAINT JAMES DR | 067 | LEX | 2024-11-14 | U126530 | U125763 | 2024-09-18 | 2024-12-31 |  |  | JDUNN | 2024-11-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2834.17 | 0 | 0 | 0 | 2834.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286423800 |  | 100329467 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 149 SAINT JAMES DR | 067 | LEX | 2024-11-20 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-11-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.016667 | 1 | 2878.4 | 1.67 | 0 | 0.11 | 2876.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286423900 |  | 100329417 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 150 SAINT JAMES DR | 067 | LEX | 2024-11-09 | U461322 | U125763 | 2024-09-18 | 2024-11-11 |  |  | STEVE CANOY | 2024-11-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.4 | 2 | 3558.31 | 542.97 | 0 | 32.67 | 2982.67 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286424000 |  | 100329466 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 153 SAINT JAMES DR | 067 | LEX | 2024-11-19 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-11-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.0333 | 1 | 2851.66 | 171.37 | 0 | 69.78 | 2610.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286424100 |  | 100329418 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 154 SAINT JAMES DR | 067 | LEX | 2024-11-21 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-11-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.2 | 1 | 4001.22 | 101.81 | 0 | 41.47 | 3857.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286424200 |  | 100329465 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 157 SAINT JAMES DR | 067 | LEX | 2024-11-26 | U126284 | U125763 | 2024-09-18 | 2024-12-31 |  |  | JOSH PASLEY | 2024-11-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.05 | 1 | 4802.44 | 403.18 | 0 | 24.26 | 4375 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286424400 |  | 100329464 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 161 SAINT JAMES DR | 067 | LEX | 2024-11-18 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-11-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.4 | 1 | 3089.07 | 285.91 | 0 | 116.43 | 2686.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286424600 |  | 100329463 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 165 SAINT JAMES DR | 067 | LEX | 2024-11-22 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-11-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.1167 | 1 | 3686.04 | 520.91 | 0 | 212.1 | 2953.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286424800 |  | 100329462 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 169 SAINT JAMES DR | 067 | LEX | 2024-12-14 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-12-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.5 | 1 | 4177.85 | 302.37 | 0 | 17.66 | 3857.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286425000 |  | 100329423 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 174 SAINT JAMES DR | 067 | LEX | 2024-11-11 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-11-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.3 | 1 | 4299.96 | 29.71 | 0 | 1.79 | 4268.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286425100 |  | 100329460 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 177 SAINT JAMES DR | 067 | LEX | 2024-11-11 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-11-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.6167 | 1 | 2945.46 | 305.43 | 0 | 18.39 | 2621.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286425200 |  | 100329424 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 178 SAINT JAMES DR | 067 | LEX | 2024-12-14 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-12-14 | 2024-12-02 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.2 | 3 | 3842.99 | 710.98 | 0 | 183.62 | 2948.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286425300 |  | 100329425 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 182 SAINT JAMES DR | 067 | LEX | 2024-11-12 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-11-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.4833 | 1 | 3491.85 | 208.68 | 0 | 12.57 | 3270.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286425400 |  | 100329458 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 185 SAINT JAMES DR | 067 | LEX | 2024-11-14 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-11-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.5167 | 1 | 3570.39 | 554.02 | 0 | 225.59 | 2790.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286425500 |  | 100329426 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 186 SAINT JAMES DR | 067 | LEX | 2024-11-13 | U126530 | U125763 | 2024-09-18 | 2024-12-31 |  |  | JDUNN | 2024-11-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3796.27 | 0 | 0 | 0 | 3796.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286425600 |  | 100329457 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 189 SAINT JAMES DR | 067 | LEX | 2024-11-14 | U126530 | U125763 | 2024-09-18 | 2024-12-31 |  |  | JDUNN | 2024-11-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10 | 1 | 4612.33 | 748.78 | 0 | 45.07 | 3818.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286425700 |  | 100329427 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 190 SAINT JAMES DR | 067 | LEX | 2024-11-08 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-11-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2488.43 | 0 | 0 | 0 | 2488.43 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286425800 |  | 100329456 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 193 SAINT JAMES DR | 067 | LEX | 2024-11-15 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-11-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.7 | 1 | 3872.76 | 738.07 | 0 | 300.52 | 2834.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286425900 |  | 100329428 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 194 SAINT JAMES DR | 067 | LEX | 2024-11-08 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-11-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.36667 | 1 | 2077.95 | 31.4 | 0 | 1.89 | 2044.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286426600 |  | 100329486 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 126 SAINT WILLIAM DR | 067 | LEX | 2024-10-14 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-10-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3779.49 | 0 | 0 | 0 | 3779.49 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286426700 |  | 100329545 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 129 SAINT WILLIAM DR | 067 | LEX | 2024-10-11 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-10-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4027.01 | 0 | 0 | 0 | 4027.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286426800 |  | 100329487 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 130 SAINT WILLIAM DR | 067 | LEX | 2024-10-14 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-10-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2676.26 | 0 | 0 | 0 | 2676.26 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286426900 |  | 100329544 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 133 SAINT WILLIAM DR | 067 | LEX | 2024-10-15 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-10-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2620.02 | 0 | 0 | 0 | 2620.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286427000 |  | 100329488 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 134 SAINT WILLIAM DR | 067 | LEX | 2024-10-18 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-10-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.85 | 1 | 2716.81 | 263.33 | 0 | 16.14 | 2437.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286427100 |  | 100329489 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 138 SAINT WILLIAM DR | 067 | LEX | 2024-10-16 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-10-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4232.29 | 0 | 0 | 0 | 4232.29 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286427200 |  | 100329523 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 141 SAINT WILLIAM DR | 067 | LEX | 2024-10-17 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-10-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3673.06 | 0 | 0 | 0 | 3673.06 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286427300 |  | 100329490 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 142 SAINT WILLIAM DR | 067 | LEX | 2024-10-15 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-10-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3151.5 | 0 | 0 | 0 | 3151.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286427400 |  | 100329491 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 146 SAINT WILLIAM DR | 067 | LEX | 2024-10-17 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-10-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4371.81 | 0 | 0 | 0 | 4371.81 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286427500 |  | 100329521 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 149 SAINT WILLIAM DR | 067 | LEX | 2024-10-21 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-10-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2936.26 | 0 | 0 | 0 | 2936.26 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286427600 |  | 100329492 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 150 SAINT WILLIAM DR | 067 | LEX | 2024-10-18 | U461322 | U125763 | 2024-09-18 | 2024-10-18 |  |  | STEVE CANOY | 2024-10-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.016667 | 1 | 3181.87 | 1.35 | 0 | 0.08 | 3180.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286427700 |  | 100329493 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 154 SAINT WILLIAM DR | 067 | LEX | 2024-10-25 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-10-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4025.88 | 0 | 0 | 0 | 4025.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286427800 |  | 100329494 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 158 SAINT WILLIAM DR | 067 | LEX | 2024-10-21 | U461322 | U125763 | 2024-09-18 | 2024-10-21 |  |  | STEVE CANOY | 2024-10-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.4167 | 1 | 4045.23 | 303.71 | 0 | 221.39 | 3520.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286427900 |  | 100329518 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 161 SAINT WILLIAM DR | 067 | LEX | 2024-10-21 | U126602 | U125763 | 2024-09-18 | 2024-10-21 |  |  | DEREK PAYTON | 2024-10-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.5 | 1 | 5428.3 | 562.04 | 0 | 122.84 | 4743.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286428000 |  | 100329495 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 162 SAINT WILLIAM DR | 067 | LEX | 2024-10-25 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-10-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3797.67 | 0 | 0 | 0 | 3797.67 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286428100 |  | 100329517 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 165 SAINT WILLIAM DR | 067 | LEX | 2024-10-26 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-10-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3273.83 | 0 | 0 | 0 | 3273.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286428300 |  | 100329516 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 169 SAINT WILLIAM DR | 067 | LEX | 2024-10-23 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-10-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2945.64 | 0 | 0 | 0 | 2945.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286428400 |  | 100329497 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 170 SAINT WILLIAM DR | 067 | LEX | 2024-10-26 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-10-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3192.77 | 0 | 0 | 0 | 3192.77 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286428500 |  | 100329498 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 172 SAINT WILLIAM DR | 067 | LEX | 2024-10-31 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-10-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3471.47 | 0 | 0 | 0 | 3471.47 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286428600 |  | 100329515 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 173 SAINT WILLIAM DR | 067 | LEX | 2024-10-29 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-10-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4131.18 | 0 | 0 | 0 | 4131.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286428700 |  | 100329501 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 174 SAINT WILLIAM DR | 067 | LEX | 2024-10-25 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-10-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.9833 | 1 | 5113.65 | 682.63 | 0 | 497.63 | 3933.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286428800 |  | 100329514 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 175 SAINT WILLIAM DR | 067 | LEX | 2024-10-29 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-10-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3330.2 | 0 | 0 | 0 | 3330.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286428900 |  | 100329502 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 176 SAINT WILLIAM DR | 067 | LEX | 2024-10-24 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-10-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.4333 | 1 | 3092.8 | 370.02 | 0 | 269.76 | 2453.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286429000 |  | 100329513 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 177 SAINT WILLIAM DR | 067 | LEX | 2024-10-24 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-10-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.5 | 1 | 4471.42 | 241.46 | 0 | 176 | 4053.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286429100 |  | 100329503 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 178 SAINT WILLIAM DR | 067 | LEX | 2024-10-26 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-10-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4016.07 | 0 | 0 | 0 | 4016.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286429200 |  | 100329512 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 179 SAINT WILLIAM DR | 067 | LEX | 2024-10-19 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-10-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9 | 2 | 5596.08 | 615.59 | 0 | 448.76 | 4531.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286429300 |  | 100329511 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 181 SAINT WILLIAM DR | 067 | LEX | 2024-10-31 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-10-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2542.8 | 0 | 0 | 0 | 2542.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286429400 |  | 100329505 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 182 SAINT WILLIAM DR | 067 | LEX | 2024-10-30 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-10-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3390.37 | 0 | 0 | 0 | 3390.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286429500 |  | 100329510 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 183 SAINT WILLIAM DR | 067 | LEX | 2024-11-02 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-11-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2583.14 | 0 | 0 | 0 | 2583.14 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286429600 |  | 100329509 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 185 SAINT WILLIAM DR | 067 | LEX | 2024-11-04 | U126284 | U125763 | 2024-09-18 | 2024-12-31 |  |  | JOSH PASLEY | 2024-11-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.5 | 1 | 5795.81 | 918.19 | 0 | 393.82 | 4483.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286429800 |  | 100329508 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 187 SAINT WILLIAM DR | 067 | LEX | 2024-11-01 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-10-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2205.96 | 0 | 0 | 0 | 2205.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286431100 |  | 100329280 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | RICHMOND | 2195 RICHMOND RD | 067 | LEX | 2024-10-07 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-10-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.8333 | 1 | 6582.9 | 536.95 | 0 | 391.42 | 5654.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286431200 |  | 100329468 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 145 SAINT JAMES DR | 067 | LEX | 2024-11-25 | U126284 | U125763 | 2024-09-18 | 2024-12-31 |  |  | JOSH PASLEY | 2024-11-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.5 | 1 | 6402.23 | 998.03 | 0 | 428.06 | 4976.14 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286431300 |  | 100329459 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT JAMES | 181 SAINT JAMES DR | 067 | LEX | 2024-11-12 | U461322 | U125763 | 2024-09-18 | 2024-12-31 |  |  | STEVE CANOY | 2024-11-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.0667 | 1 | 3109.24 | 89.09 | 0 | 5.36 | 3014.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286431500 |  | 100329546 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 125 SAINT WILLIAM DR | 067 | LEX | 2024-10-22 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-10-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3392.42 | 0 | 0 | 0 | 3392.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286431700 |  | 100329542 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 137 SAINT WILLIAM DR | 067 | LEX | 2024-10-16 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-10-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3311.8 | 0 | 0 | 0 | 3311.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286431800 |  | 100329520 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 153 SAINT WILLIAM DR | 067 | LEX | 2024-10-23 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-10-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3871.54 | 0 | 0 | 0 | 3871.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286431900 |  | 100329519 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT WILLIAM | 157 SAINT WILLIAM DR | 067 | LEX | 2024-11-05 | U128762 | U125763 | 2024-09-18 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-11-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2933.43 | 0 | 0 | 0 | 2933.43 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24286436200 |  | 501317350 |  | 6716236J | 2178365 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | NUTHATCH | 130 NUTHATCH TR | 209 | GEO | 2024-10-01 | U461516 | U126856 | 2024-09-18 | 2024-09-23 | 2024-10-04 |  | NEAL P JOHNSON | 2024-10-01 |  | 2024-10-01 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 4418.38 | 480.26 | 311.22 | 394.8 | 3232.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286436800 |  | 501371550 |  | 6716220M |  |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | KEARNEY CREEK | 2685 KEARNEY CREEK LN | 067 | LEX | 2024-10-03 | U126602 | U126856 | 2024-09-18 | 2024-09-23 | 2024-10-04 |  | DEREK PAYTON | 2024-10-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2395.97 | 528.99 | 287.04 | 32.41 | 1547.53 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24286502300 |  | 100281212 |  | 6700220J |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | OLD FRANKFORT | 3954 OLD FRANKFORT PK FG51 | 239 | VER | 2024-09-20 | LSTANFI | U129939 | 2024-09-19 | 2024-09-19 |  |  | LSTANFI | 2024-09-20 | 2024-09-19 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 20.0333 | 5 | 1227.95 | 1161.72 | 0 | 66.23 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24286503200 |  | 500025086 |  | 6700220J |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | OLD FRANKFORT | 3910 OLD FRANKFORT PK FG50 | 239 | VER | 2024-10-21 | U123688 | U129939 | 2024-09-19 | 2024-12-12 | 2026-06-30 |  | LSTANFI | 2024-09-20 | 2024-09-19 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 33.15 | 7 | 9985.18 | 2030.97 | 686.18 | 115.78 | 7152.25 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24286534100 |  | 100256388 |  | 7356256F |  |  |  | 563 | EX | 99 1" P SHORT | 2621P | BATH | 2524 BATH AV | 019 | ASH | 2024-10-08 | U123688 | U134375 | 2024-09-19 | 2024-10-03 | 2024-10-17 |  | MCOLLET | 2024-10-07 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 13.6 | 2 | 1064.79 | 894.4 | 244.42 | -233.87 | 159.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286542500 |  | 100302798 |  | 6712212N |  |  |  | 566 | EX | ABANDON SL/ DEMO CUST REQ | 2621P | PARKERS MILL | 1899 PARKERS MILL RD | 067 | LEX | 2024-10-02 | KKINDER | U139381 | 2024-09-19 | 2024-10-09 | 2024-10-31 |  | KKINDER | 2024-10-02 | 2024-09-20 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 19.4667 | 3 | 1397.45 | 1182 | 144.03 | 71.42 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286574700 |  | 100329308 |  | 6720208G | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT PHILLIP | 129 SAINT PHILLIP DR | 067 | LEX | 2024-09-23 | U128762 | U125763 | 2024-09-19 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-09-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2786.35 | 0 | 0 | 0 | 2786.35 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24286586700 |  | 100417058 |  | 6736212K | 2408531 |  |  | 563 | EX | 1" P SHORT | 2600B | CONSTITUTION | 502 CONSTITUTION DR | 049 | WIN | 2024-10-01 | U123111 | U129294 | 2024-09-19 | 2024-09-23 | 2024-10-04 |  | LYN STAFFORD | 2024-10-01 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 8 | 1 | 1879.56 | 495.48 | 305.73 | 30.37 | 1047.98 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286590700 |  | 100334480 |  | 6720208H |  |  |  | 565 | EX | GRADE 2+ REPLACE S/L | 2621P | PEACHTREE | 473 PEACHTREE RD | 067 | LEX | 2024-09-25 | HMCKUNE | U129939 | 2024-09-19 | 2024-09-22 | 2024-10-10 |  | HMCKUNE | 2024-09-25 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.6667 | 3 | 1437 | 1135.84 | 236.35 | 64.81 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286806100 |  | 501257681 |  | 6724212P | 2398241 |  |  | 563 | EX | 2" P SHORT/ PRMT REQ | 2600B | POLO CLUB | 2185 POLO CLUB BV | 067 | LEX | 2024-10-10 | U128336 | U126856 | 2024-09-20 | 2024-09-23 | 2024-10-11 |  | JOSHUA COX | 2024-10-10 | 2024-10-01 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26210011 | 48.1 | 7 | 22290.89 | 3094.16 | 1083.66 | 189.56 | 17923.51 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24286830200 |  | 501313752 |  | 6716232B | 2289995 |  |  | 563 | EX | 99 1" P SHORT/NO PRMT REQ | 2600B | OAK HILL | 103 OAK HILL LN LT1 | 209 | GEO | 2024-09-27 | U123111 | U131378 | 2024-09-20 | 2024-09-23 | 2024-10-04 |  | LYN STAFFORD | 2024-09-26 | 2024-09-26 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 1639.73 | 525.13 | 0 | 29.96 | 1084.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286840400 |  | 100330605 |  | 6732216P |  |  |  | 566 | EX | ABANDON SL/ DEMO CUST REQ | 2621P | BRIAR HILL | 5655 BRIAR HILL RD | 067 | LEX | 2024-10-25 | HMCKUNE | U139381 | 2024-09-20 | 2024-10-10 | 2024-11-01 |  | HMCKUNE | 2024-10-25 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 22.8667 | 3 | 1687.05 | 1202.43 | 45.57 | 439.05 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286852800 |  | 501171009 |  | 6728208E | 1528649 |  |  | 563 | EX | 1" P SHORT/PRMT RCVD | 2600B | SWEET CLOVER | 1572 SWEET CLOVER PK LT27 | 067 | LEX | 2024-10-18 | U126532 | U134375 | 2024-09-20 | 2024-10-09 | 2024-10-22 |  | LESLIE SHARON | 2024-10-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2439.66 | 520.8 | 287.04 | 31.9 | 1599.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286861200 |  | 100336260 |  | 6720212I | 2407694 |  |  | 565 | EX | RPLC SL/24026356000 | 2600B | WILGUS | 318 WILGUS AV | 067 | LEX | 2025-05-08 | U461322 | U125763 | 2024-09-20 | 2024-12-31 |  |  | STEVE CANOY | 2025-05-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.3333 | 1 | 3440.52 | 510.44 | 0 | 557.79 | 2372.29 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286861300 |  | 100336261 |  | 6720212I | 2407694 |  |  | 565 | EX | RPLC SL/24026356000 | 2600B | WILGUS | 322 WILGUS AV | 067 | LEX | 2025-05-13 | U461322 | U125763 | 2024-09-20 | 2024-12-31 |  |  | STEVE CANOY | 2025-05-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.55 | 1 | 1780.67 | 318.07 | 0 | 18.45 | 1444.15 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286861400 |  | 100336262 |  | 6720212I | 2407694 |  |  | 565 | EX | RPLC SL/24026356000 | 2600B | WILGUS | 326 WILGUS AV | 067 | LEX | 2025-05-06 | U461322 | U125763 | 2024-09-20 | 2024-12-31 |  |  | STEVE CANOY | 2025-05-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.1167 | 1 | 3071.48 | 494.49 | 0 | 540.32 | 2036.67 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286861500 |  | 100429418 |  | 6720212I | 2407694 |  |  | 565 | EX | RPLC SL/24026356000 | 2600B | WILGUS | 327 WILGUS AV | 067 | LEX | 2025-05-12 | U461322 | U125763 | 2024-09-20 | 2024-12-31 |  |  | STEVE CANOY | 2025-05-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.85 | 1 | 2473.14 | 545.18 | 0 | 595.72 | 1332.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286861600 |  | 100336271 |  | 6720212I | 2407694 |  |  | 565 | EX | RPLC SL/24026356000 | 2600B | WILGUS | 331 WILGUS AV | 067 | LEX | 2025-05-07 | U461322 | U125763 | 2024-09-20 | 2024-12-31 |  |  | STEVE CANOY | 2025-05-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.6167 | 1 | 2407.71 | 460.42 | 0 | 503.14 | 1444.15 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286861800 |  | 100336264 |  | 6720212I | 2407694 |  |  | 565 | EX | RPLC SL/24026356000 | 2600B | WILGUS | 334 WILGUS AV | 067 | LEX | 2025-05-05 | U461322 | U125763 | 2024-09-20 | 2024-12-31 |  |  | STEVE CANOY | 2025-05-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.1167 | 1 | 3178.17 | 425.71 | 0 | 465.18 | 2287.28 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24286862400 |  | 100336272 |  | 6720212I | 2407694 |  |  | 565 | EX | RPLC SL/24026356000 | 2600B | WILGUS | 329 WILGUS AV | 067 | LEX | 2025-05-09 | U461322 | U125763 | 2024-09-20 | 2024-12-31 |  |  | STEVE CANOY | 2025-05-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.5333 | 1 | 3466.7 | 522.97 | 0 | 571.44 | 2372.29 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24286864200 |  | 501260625 |  | 6700208A | 1856404 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | GREENTREE | 4064 GREENTREE RD | 239 | VER | 2024-10-14 | U126602 | U134341 | 2024-09-20 | 2024-09-23 | 2024-10-14 |  | DEREK PAYTON | 2024-10-09 | 2024-10-09 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26230011 | 9 | 1 | 4999.61 | 595.13 | 560.05 | 36.46 | 3807.97 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24287002300 |  | 100272184 |  | 6684228O | 2408121 |  |  | 563 | EX | 1" P LONG/PRMT RCVD | 2600B | LOGAN | 514 LOGAN ST | 073 | FRA | 2024-10-23 | U123119 | U132805 | 2024-09-23 | 2024-10-01 | 2024-10-14 |  | LYN STAFFORD | 2024-10-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4 | 1 | 3391.69 | 247.78 | 0 | 15.19 | 3128.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287005400 |  | 100301392 |  | 6712212H |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SUTTON | 219 SUTTON PL | 067 | LEX | 2024-09-24 | UIPBOT13 | U130871 | 2024-09-23 | 2024-06-04 | 2025-12-31 |  | MCRAIG | 2024-09-23 | 2024-09-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.6667 | 3 | 1427.62 | 747.24 | 549.91 | 130.47 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287005700 |  | 501371578 |  | 6716220N |  |  |  | 563 | EX | 1' P LONG/PRMT RCVD | 2600B | KEARNEY CREEK | 2633 KEARNEY CREEK LN | 067 | LEX | 2024-10-17 | U461516 | U133050 | 2024-09-23 | 2024-10-09 | 2024-10-22 |  | NEAL JOHNSON | 2024-10-17 |  | 2024-10-17 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 5938.84 | 480.26 | 311.23 | 394.8 | 4752.55 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24287011900 |  | 100285087 |  | 6764176K |  |  |  | 563 | EX | 99 1" P SHORT | 2621P | LAUREL | 508 LAUREL ST | 065 | IRV | 2024-10-09 | U123688 | U134375 | 2024-09-23 | 2024-10-07 | 2024-10-21 |  | DENNING | 2024-10-08 | 2024-09-26 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 28.7167 | 5 | 4009.76 | 1904.79 | 228.87 | 115.58 | 1760.52 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24287021200 |  | 100282970 |  | 6712228B | 2293665 |  |  | 565 | EX | RPLC SL/22026236900 | 2600B | HAMILTON | 508 S HAMILTON ST | 209 | GEO | 2024-09-23 | U126532 | U125763 | 2024-09-23 | 2024-12-31 |  |  | LESLIE SHARON | 2024-09-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2639.54 | 0 | 0 | 0 | 2639.54 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24287030900 |  | 500576249 |  | 6692224C | 9616085 |  |  | 563 | EX | 1" P SHORT/PRMT RCVD | 2600B | BUENA VISTA | 125 BUENA VISTA DR | 073 | FRA | 2024-10-16 | U126602 | U126856 | 2024-09-23 | 2024-10-01 | 2024-10-14 |  | DEREK PAYTON | 2024-10-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 10 | 1 | 3951.37 | 661.26 | 290.68 | 40.53 | 2958.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24287041500 |  | 100343309 |  | 7240212A |  |  |  | 565 | EX | GRADE 1 REPLACE SERVICE | 2621P | CHENAULT | 303 CHENAULT LN | 173 | MT | 2024-09-24 | NRICHIE | U129939 | 2024-09-23 | 2024-09-23 | 2024-09-23 |  | NRICHIE | 2024-09-24 | 2024-09-23 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 19.1 | 4 | 2342.02 | 1372.07 | 287.83 | 682.12 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24287042000 |  | 501370162 |  | 7344168K | 2408308 |  |  | 563 | EX | 1" P LONG | 2621P | EVERGREEN | 52 N EVERGREEN LN | 071 | LNC | 2024-10-12 | U123688 | U138822 | 2024-09-23 | 2024-09-23 | 2024-10-07 |  | BPREECE | 2024-10-10 | 2024-10-09 |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26330011 | 33.25 | 5 | 3074.61 | 2097.01 | 0 | 859.2 | 118.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287046100 |  | 100428569 |  | 6716212G |  |  |  | 566 | EX | ABANDON SL/ DEMO CUST REQ | 2621P | COX | 158 COX ST | 067 | LEX | 2024-10-18 | MCRAIG | U139381 | 2024-09-23 | 2024-10-11 | 2024-11-04 |  | MCRAIG | 2024-10-18 | 2024-10-14 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 20.6667 | 6 | 1000.51 | 1209.52 | 39.78 | -248.79 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287165500 |  | 501296515 |  | 0724204F | 1968324 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | WESTON | 397 WESTON PK | 067 | LEX | 2024-09-30 | U126602 | U126856 | 2024-09-24 | 2024-09-25 | 2024-10-08 |  | DEREK PAYTON | 2024-09-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2450.61 | 526.76 | 287.05 | 30.05 | 1606.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287166100 |  | 501092118 |  | 0724204F |  |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | WESTON | 400 WESTON PK | 067 | LEX | 2024-10-03 | U461516 | U126856 | 2024-09-24 | 2024-09-25 | 2024-10-08 |  | NEAL P JOHNSON | 2024-10-03 |  | 2024-10-03 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4599.09 | 480.26 | 317.61 | 394.8 | 3406.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287166600 |  | 501371597 |  | 6724204F |  |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | WESTON | 384 WESTON PK | 067 | LEX | 2024-10-07 | U126602 | U126856 | 2024-09-24 | 2024-09-25 | 2024-10-08 |  | DEREK PAYTON | 2024-10-03 | 2024-10-03 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4008.87 | 528.99 | 128.69 | 32.41 | 3318.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287171300 |  | 100311175 |  | 167122080 |  |  |  | 563 | EX | 1" P LONG/PRMT RCVD | 2600B | TUDOR | 3236 TUDOR DR | 067 | LEX | 2024-10-16 | U128336 | U132256 | 2024-09-24 | 2024-10-09 | 2024-10-22 |  | JOSHUA COX | 2024-10-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 6.9667 | 1 | 5294.58 | 448.43 | 1037.77 | 27.47 | 3780.91 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287172800 |  | 100295652 |  | 6716216K |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | BOXWOOD | 1157 BOXWOOD DR | 067 | LEX | 2024-09-24 | TROE | U129939 | 2024-09-24 | 2024-09-24 |  |  | TROE | 2024-09-24 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.3333 | 2 | 5776.51 | 73.92 | 5698.38 | 4.21 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24287174800 |  | 100246803 |  | 7352256L |  |  |  | 566 | EX | ABANDON SL/ DEMO CUST REQ | 2621P | 29TH | 3008 S 29TH ST | 019 | ASH | 2024-10-30 | MCOLLET | U139381 | 2024-09-24 | 2024-10-15 | 2024-11-06 |  | MCOLLET | 2024-10-30 | 2024-10-23 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 13.1 | 4 | 1469.14 | 853.71 | 20.28 | -204.85 | 800 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287177600 |  | 100409631 |  | 6720208G | 2403558 |  |  | 565 | EX | REPLACE SL/24026316700 | 2600B | RICHMOND | 2233 RICHMOND RD | 067 | LEX | 2024-09-27 | U128762 | U125763 | 2024-09-24 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-09-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4637.47 | 0 | 0 | 0 | 4637.47 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287183400 |  | 100297595 |  | 6716212H | 1855043 |  |  | 566 | EX | ABANDON SL - SOII/INSIDE | 2621P | 3RD | 510 W 3RD ST | 067 | LEX | 2024-10-17 | U930915 | U131897 | 2024-09-24 | 2024-12-31 | 2024-12-31 |  | HSTANFI | 2024-10-17 | 2024-10-17 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 25 | 4 | 1985.73 | 1368.02 | 21.9 | 83.81 | 512 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287193200 |  | 501334668 |  | 6716216E | 2289300 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | DAHLIA | 649 DAHLIA DR | 067 | LEX | 2024-10-07 | U126602 | U126856 | 2024-09-24 | 2024-09-25 | 2024-10-08 |  | DEREK PAYTON | 2024-10-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4189.65 | 528.99 | 322.16 | 32.41 | 3306.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287194000 |  | 501334622 |  | 6716216E | 2289300 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | GERANIUM | 2349 GERANIUM LN | 067 | LEX | 2024-09-30 | U123111 | U126856 | 2024-09-24 | 2024-09-25 | 2024-10-08 |  | LYN STAFFORD | 2024-09-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 1742.82 | 262.58 | 338.34 | 14.96 | 1126.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287195500 |  | 501334633 |  | 6716216E | 2289300 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | GERANIUM | 2381 GERANIUM LN | 067 | LEX | 2024-09-30 | U461516 | U126856 | 2024-09-24 | 2024-09-25 | 2024-10-08 |  | NEAL P JOHNSON | 2024-09-30 |  | 2024-09-30 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2531.53 | 526.43 | 311.22 | 535.92 | 1157.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287195800 |  | 501334638 |  | 6716216E | 2289300 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | GERANIUM | 2345 GERANIUM LN | 067 | LEX | 2024-09-30 | U123111 | U126856 | 2024-09-24 | 2024-09-25 | 2024-10-08 |  | LYN STAFFORD | 2024-09-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 2287.49 | 262.58 | 338.34 | 14.96 | 1671.61 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24287227500 |  | 501350437 |  | 6716232J | 2398315 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | OXFORD LANDING | 127 OXFORD LANDING DR LT83 | 209 | GEO | 2024-10-02 | U123111 | U130616 | 2024-09-24 | 2024-09-25 | 2024-10-08 |  | LYN STAFFORD | 2024-10-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 2353.06 | 495.48 | 312.11 | 30.37 | 1515.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24287227600 |  | 501332972 |  | 6716232I | 2180856 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | OXFORD LANDING | 106 OXFORD LANDING DR LT106 | 209 | GEO | 2024-10-04 | U461309 | U130616 | 2024-09-24 | 2024-09-25 | 2024-10-08 |  | RANDALL HUMPHREYS | 2024-10-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 4338.17 | 472.5 | 281.54 | 394.33 | 3189.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24287227800 |  | 501350518 |  | 6716232J | 2398315 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | OXFORD LANDING | 170 OXFORD LANDING DR LT53 | 209 | GEO | 2024-10-04 | U123111 | U130616 | 2024-09-24 | 2024-09-25 | 2024-10-08 |  | LYN STAFFORD | 2024-10-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 4224.55 | 495.48 | 277.77 | 30.37 | 3420.93 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24287229300 |  | 100449213 |  | 7344168G |  |  |  | 565 | EX | REPLACE SERVICE LINE - D325602 | 2621P | LAKE | 1368 S LAKE DR | 071 | LNC | 2024-09-26 | JCKIRK | U123688 | 2024-09-24 | 2024-09-27 | 2024-10-15 |  | JCKIRK | 2024-09-26 | 2024-09-25 |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26330021 | 61.1833 | 6 | 11761.15 | 4875.27 | 7.78 | 2036.1 | 4842 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287333000 |  | 501334671 |  | 6716216E | 2289300 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | DAHLIA | 632 DAHLIA DR | 067 | LEX | 2024-10-07 | U126602 | U126856 | 2024-09-25 | 2024-09-26 | 2024-10-09 |  | DEREK PAYTON | 2024-10-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 1913.34 | 528.99 | 287.04 | 32.41 | 1064.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287339200 |  | 100330401 |  | 6720212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | KINGSWOOD | 441 KINGSWOOD DR APT 1 | 067 | LEX | 2024-09-27 | U123688 | U129939 | 2024-09-25 | 2024-12-15 | 2026-06-30 |  | HMCKUNE | 2024-09-25 | 2024-07-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 25.9333 | 11 | 7319.26 | 3927.1 | 343.29 | 977.99 | 2070.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287351900 |  | 501346250 |  | 6728208I | 2396366 |  |  | 563 | EX | 1" P SHORT *PORTRAIT HMS* | 2600B | TWILIGHT SHADO | 1206 TWILIGHT SHADO DR LT145 | 067 | LEX | 2024-10-03 | U461309 | U138822 | 2024-09-25 | 2024-09-26 | 2024-10-09 |  | RANDALL HUMPHREYS | 2024-10-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 3.5 | 1 | 2213.81 | 206.72 | 287.04 | 172.52 | 1547.53 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24287365300 |  | 501371666 |  | 7240216F |  |  |  | 563 | EX | PAPER W/501360066 | 2621P | HANNAH | 21 HANNAH LN | 173 | MT | 2024-09-26 | U123688 | U127708 | 2024-09-25 | 2024-10-09 | 2024-10-09 |  | OFFICE | 2024-09-26 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26290011 |  | 1 | 179.08 | 0 | 0 | 0 | 179.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287371900 |  | 501348630 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | CLEMATIS | 2221 CLEMATIS WY | 067 | LEX | 2024-10-03 | U461309 | U126856 | 2024-09-25 | 2024-09-26 | 2024-10-09 |  | RANDALL HUMPHREYS | 2024-10-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4.5 | 1 | 1870.56 | 265.79 | 287.04 | 221.81 | 1095.92 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24287372400 |  | 100248883 |  | 7356256I |  |  |  | 563 | EX | 1" P LONG | 2621P | SMITH | 2213 SMITH ST | 019 | ASH | 2024-10-18 | U141668 | U132256 | 2024-09-25 | 2024-10-16 | 2024-10-16 |  | RECUMP | 2024-10-17 | 2024-10-11 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 28.75 | 6 | 1754.71 | 1746.63 | 283.76 | -331.92 | 56.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287374900 |  | 100340643 |  | 6724212E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | SARASOTA | 1712 SARASOTA CT | 067 | LEX | 2024-10-23 | U124604 | U124604 | 2024-09-25 | 2024-12-31 |  |  | HMCKUNE | 2024-10-22 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.9833 | 2 | 1439.62 | 985.83 | 393.4 | 60.39 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287376200 |  | 501239143 |  | 6720200I | 2408906 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | SERENITY | 1046 SERENITY CR | 113 | NIC | 2024-10-14 | U126602 | U126856 | 2024-09-25 | 2024-09-26 | 2024-10-09 |  | DEREK PAYTON | 2024-10-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 5552.7 | 528.99 | 566.14 | 32.41 | 4425.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287410900 |  | 501346172 |  | 6728208I | 2396366 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | STOLEN HORSE | 3488 STOLEN HORSE TC LT67 | 067 | LEX | 2024-10-08 | U461516 | U130616 | 2024-09-25 | 2024-09-30 | 2024-10-11 |  | NEAL P JOHNSON | 2024-10-08 |  | 2024-10-08 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4.1667 | 1 | 3889.96 | 250.96 | 311.23 | 206.28 | 3121.49 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24287411200 |  | 100257123 |  | 7348264I |  |  |  | 565 | EX | SL/METER RELOCATE | 2621P | CAROLINE | 2014 CAROLINE RD | 089 | FLA | 2024-11-06 | MCOLLET | U123688 | 2024-09-25 | 2024-11-25 | 2024-11-25 |  | MCOLLET | 2024-11-06 | 2024-10-08 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 17.8 | 4 | 3519.29 | 1363.89 | 231.43 | 796.73 | 1127.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287414400 |  | 100292778 |  | 6720216K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D341667 | 2621P | RADCLIFFE | 570 RADCLIFFE RD | 067 | LEX | 2024-09-27 | U123688 | U131366 | 2024-09-25 | 2024-09-27 | 2024-10-16 |  | RJCRAWF | 2024-09-26 | 2024-09-26 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 24 | 3 | 1878.37 | 1415.74 | 381.88 | 80.75 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24287538200 |  | 501309817 |  | 6716232E | 2076283 |  |  | 563 | EX | 1" P SHORT/PRMT READY 10/4/24 | 2600B | AMICK | 128 AMICK WY | 209 | GEO | 2024-10-21 | U123111 | U126856 | 2024-09-26 | 2024-10-09 | 2024-10-22 |  | LYN STAFFORD | 2024-10-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 2390.99 | 495.48 | 317.61 | 30.37 | 1547.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287641100 |  | 100318135 |  | 6716204G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | KING ARTHUR | 3653 KING ARTHUR DR | 067 | LEX | 2024-09-30 | U124604 | U141176 | 2024-09-26 | 2024-09-26 | 2024-09-26 |  | TROE | 2024-09-27 | 2024-09-27 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 59.1 | 11 | 3662.94 | 3311.98 | 139.01 | 211.95 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287790000 |  | 501334651 |  | 6716216E | 2289300 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | GERANIUM | 2341 GERANIUM LN | 067 | LEX | 2024-10-03 | U123111 | U126856 | 2024-09-27 | 2024-09-30 | 2024-10-11 |  | LYN STAFFORD | 2024-10-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 1940.79 | 495.48 | 317.61 | 30.37 | 1097.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287790400 |  | 501334652 |  | 6716216E | 2289300 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | GERANIUM | 2333 GERANIUM LN | 067 | LEX | 2024-10-03 | U123111 | U126856 | 2024-09-27 | 2024-09-30 | 2024-10-11 |  | LYN STAFFORD | 2024-10-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1865.14 | 0 | 317.61 | 0 | 1547.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287790600 |  | 501334639 |  | 6716216E | 2289300 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | DAHLIA | 636 DAHLIA LN | 067 | LEX | 2024-10-07 | U126602 | U126856 | 2024-09-27 | 2024-09-30 | 2024-10-11 |  | DEREK PAYTON | 2024-10-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 1991.41 | 528.99 | 287.04 | 32.41 | 1142.97 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24287790700 |  | 501358742 |  | 6700212O | 2398395 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | ABINGDON | 501 ABINGDON AV | 239 | VER | 2024-10-11 | U126602 | U126856 | 2024-09-27 | 2024-10-01 | 2024-10-14 |  | DEREK PAYTON | 2024-10-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 9.6667 | 1 | 4445.68 | 638.74 | 0 | 39.13 | 3767.81 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287791400 |  | 501334667 |  | 6716216E | 2289300 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | DAHLIA | 656 DAHLIA DR | 067 | LEX | 2024-10-07 | U126602 | U126856 | 2024-09-27 | 2024-09-30 | 2024-10-11 |  | DEREK PAYTON | 2024-10-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1308.21 | 0 | 236.26 | 0 | 1071.95 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24287793000 |  | 501304849 |  | 6712228I | 2177127 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | MAGELLAN | 111 MAGELLAN LN | 209 | GEO | 2024-10-16 | U461309 | U126856 | 2024-09-27 | 2024-10-01 | 2024-10-14 |  | RANDALL HUMPHREYS | 2024-10-14 | 2024-10-14 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 5.5 | 1 | 4421.44 | 324.84 | 356.67 | 271.1 | 3468.83 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24287793300 |  | 501309008 |  | 6712228I | 2177127 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | PINWHEEL | 101 PINWHEEL CT | 209 | GEO | 2024-10-24 | U125559 | U126856 | 2024-09-27 | 2024-10-01 | 2024-10-14 |  | LYN STAFFORD | 2024-10-16 | 2024-10-11 | 2024-10-14 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 21.55 | 3 | 5735.71 | 1326.96 | 554.93 | 81.3 | 3772.52 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24287793800 |  | 501309010 |  | 6712228I | 2177127 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | PINWHEEL | 105 PINWHEEL CT | 209 | GEO | 2024-10-14 | U128336 | U126856 | 2024-09-27 | 2024-10-01 | 2024-10-14 |  | JOSHUA COX | 2024-10-14 | 2024-10-11 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 13.95 | 2 | 5319.85 | 896.25 | 418.79 | 54.89 | 3949.92 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24287794600 |  | 501309025 |  | 6712228I | 2398438 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | HOURGLASS | 131 HOURGLASS LN | 209 | GEO | 2024-10-16 | U126532 | U126856 | 2024-09-27 | 2024-10-01 | 2024-10-17 |  | LESLIE SHARON | 2024-10-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 5458.41 | 520.8 | 145.1 | 397.28 | 4395.23 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24287794800 |  | 501309046 |  | 6712228I |  |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | HOURGLASS | 113 HOURGLASS LN | 209 | GEO | 2024-10-15 | U123111 | U126856 | 2024-09-27 | 2024-10-01 | 2024-10-14 |  | LYN STAFFORD | 2024-10-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4 | 1 | 3793.07 | 247.78 | 306.44 | 15.19 | 3223.66 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24287794900 |  | 501309045 |  | 6712228I |  |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | HOURGLASS | 107 HOURGLASS LN | 209 | GEO | 2024-10-29 | U126602 | U126856 | 2024-09-27 | 2024-10-01 | 2024-10-14 |  | DEREK PAYTON | 2024-10-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 3331.47 | 0 | 0 | 0 | 3331.47 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24287795000 |  | 501309044 |  | 6712228I |  |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | HOURGLASS | 105 HOURGLASS LN | 209 | GEO | 2024-10-09 | U123111 | U126856 | 2024-09-27 | 2024-10-01 | 2024-10-14 |  | LYN STAFFORD | 2024-10-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 4045.07 | 495.48 | 284.3 | 30.37 | 3234.92 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24287795100 |  | 501309035 |  | 6712228I |  |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | HOURGLASS | 108 HOURGLASS LN | 209 | GEO | 2024-10-29 | U126602 | U126856 | 2024-09-27 | 2024-10-01 | 2024-10-14 |  | DEREK PAYTON | 2024-10-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 1540.48 | 0 | 0 | 0 | 1540.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287799100 |  | 100308601 |  | 6716212N | 2408969 |  |  | 563 | EX | 2" P LONG/NEED STATE PRMT | 2600B | BROADWAY | 1207 S BROADWAY ST | 067 | LEX | 2024-11-14 | U461516 | U126856 | 2024-09-27 | 2024-10-21 | 2024-11-15 |  | NEAL JOHNSON | 2024-11-12 | 2024-10-28 | 2024-10-29 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 64.5333 | 9 | 20192.33 | 4462.7 | 1536.06 | 2169.4 | 12024.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287804200 |  | 501320325 |  | 6708204K | 2182537 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | BACKSTRETCH | 308 BACKSTRETCH LT42 | 113 | NIC | 2024-10-07 | U461516 | U129176 | 2024-09-27 | 2024-10-01 | 2024-10-14 |  | NEAL P JOHNSON | 2024-10-07 |  | 2024-10-07 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4338.8 | 480.26 | 311.23 | 394.8 | 3152.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287825900 |  | 501369361 |  | 6720204C | 2407692 |  |  | 563 | EX | TAP W/MAIN 24026355900 | 2600B | CARRIAGE | 3216 CARRIAGE LN | 067 | LEX | 2024-10-21 | U461309 | U128272 | 2024-09-27 | 2024-11-21 | 2024-11-21 |  | RANDALL HUMPHREYS | 2024-10-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBTWM |  | 100 | 056332B26210012 | 8 | 1 | 4091.77 | 472.5 | 287.92 | 394.33 | 2937.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287826500 |  | 501369362 |  | 6720204C | 2407692 |  |  | 563 | EX | TAP W/MAIN 24026355900 | 2600B | CARRIAGE | 3212 CARRIAGE LN | 067 | LEX | 2024-10-21 | U461309 | U128272 | 2024-09-27 | 2024-11-21 | 2024-11-21 |  | RANDALL HUMPHREYS | 2024-10-21 | 2024-10-18 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBTWM |  | 100 | 056332B26210012 | 8 | 1 | 3498.31 | 472.5 | 327.56 | 394.33 | 2303.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287829400 |  | 100340025 |  | 6724212E |  |  |  | 566 | VO | ABANDON SL/ CONVRT TO ELECTRIC | 2621P | AUGUSTA | 1822 AUGUSTA DR 1FL | 067 | LEX | 2024-10-21 |  | U139381 | 2024-09-27 | 2024-10-17 | 2024-11-08 |  | HMCKUNE | 2024-10-14 |  |  | A | [11 empty] | 24287992900 | 100 |  | 14.6833 | 3 | 1044.61 | 790.64 | 0 | 253.97 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287830500 |  | 100340024 |  | 6724212E |  |  |  | 566 | EX | ABANDON SL/ DEMO CUST REQ | 2621P | AUGUSTA | 1822 AUGUSTA DR 1FR | 067 | LEX | 2024-10-14 | HMCKUNE | U139381 | 2024-09-27 | 2024-10-17 | 2024-11-08 |  | HMCKUNE | 2024-10-14 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.1833 | 1 | 170.24 | 143.56 | 17.88 | 8.8 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287984300 |  | 100328785 |  | 6720208F |  |  |  | 565 | EX | UPGRADE SERVICE LINE | 2621P | HART | 2133 HART CT | 067 | LEX | 2024-11-06 | U461383 | U124604 | 2024-09-30 | 2024-10-25 | 2024-10-25 |  | RJCRAWF | 2024-10-23 | 2024-10-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 52.15 | 8 | 12414.27 | 2857.95 | 790.73 | 175.11 | 8590.48 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24287989600 |  | 100260002 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2621P | ASHLAND | 818 ASHLAND AV | 019 | ASH | 2024-10-01 | U124604 | U124960 | 2024-09-30 | 2049-12-31 |  |  | BROBERT | 2024-09-30 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 4.4167 | 1 | 3728.32 | 287.62 | 0 | 293.38 | 3147.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287990900 |  | 100414735 |  | 6720216I |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D311032 | 2621P | GRANT | 1506 GRANT DR | 067 | LEX | 2024-10-12 | U123688 | U124604 | 2024-09-30 | 2024-10-01 | 2024-10-19 |  | HMCKUNE | 2024-10-10 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.0333 | 2 | 929.07 | 666.47 | 221.77 | 40.83 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287992900 |  | 100340025 | 35 | 6724212E |  |  |  | 566 | EX | D - ABANDON COMPANY SERVICE | 2621P | AUGUSTA | 1822 AUGUSTA DR 1FL | 067 | LEX | 2024-10-15 | HMCKUNE | BLINDSA | 2024-09-30 | 2024-12-31 |  |  | HMCKUNE | 2024-10-15 | 2024-10-14 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.05 | 3 | 518.66 | 338.09 | 0 | 180.57 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287994300 |  | 100296310 |  | 6716216O |  |  |  | 563 | EX | 1"P SHORT/PRMT RCVD | 2600B | TIBBS | 416 TIBBS LN | 067 | LEX | 2024-10-17 | U128336 | U130192 | 2024-09-30 | 2024-10-09 | 2024-10-22 |  | JOSHUA COX | 2024-10-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 3699.3 | 513.96 | 531.49 | 31.48 | 2622.37 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24287994700 |  | 100353014 |  | 6744208P |  |  |  | 563 | EX | 99 1" P LONG | 2600B | BROADWAY | 235 W BROADWAY ST | 049 | WIN | 2024-10-16 | U461516 | U134375 | 2024-09-30 | 2024-10-02 | 2024-10-16 |  | NEAL JOHNSON | 2024-10-16 |  | 2024-10-16 | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 8 | 1 | 5554.46 | 480.26 | 462.3 | 394.8 | 4217.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24287995800 |  | 500510640 |  | 16712208M | 2396687 |  |  | 563 | EX | 1"P LONG/TAP W/MAIN | 2600B | SOLBERG | 4097 SOLBERG LN | 067 | LEX | 2024-10-03 | U461309 | U123852 | 2024-09-30 | 2024-12-31 |  |  | RANDALL HUMPHREYS | 2024-10-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBTWM |  | 100 | 056332B26210012 | 5 | 1 | 2446.31 | 295.32 | 287.04 | 18.09 | 1845.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24287997500 |  | 100283099 |  | 6712228C | 2293665 |  |  | 565 | EX | RPLC SL/22026236900 | 2600B | CLAYTON | 424 CLAYTON AV | 209 | GEO | 2024-09-30 | U126532 | U123235 | 2024-09-30 | 2024-12-31 |  |  | LESLIE SHARON | 2024-09-30 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2627 | 0 | 0 | 0 | 2627 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24288006700 |  | 100302804 |  | 6712212N | 2408326 |  |  | 563 | EX | 1" P SHORT REMOTE PRIVATE EASM | 2600B | PARKERS MILL | 2101 PARKERS MILL RD | 067 | LEX | 2024-10-09 | U123111 | U132256 | 2024-09-30 | 2024-10-01 | 2024-10-14 |  | LYN STAFFORD | 2024-09-08 | 2024-10-07 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 12.5 | 2 | 4022.92 | 774.21 | 328.29 | 47.45 | 2872.97 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24288023800 |  | 100260054 |  | 7356256B | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 2113 HILTON AV | 019 | ASH | 2024-10-09 | U128523 | U125763 | 2024-09-30 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-08 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.25 | 1 | 2524.05 | 14.23 | 0 | 12.29 | 2497.53 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24288023900 |  | 100260053 |  | 7356256B | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 2117 HILTON AV | 019 | ASH | 2024-10-09 | U128523 | U125763 | 2024-09-30 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-08 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 2.3 | 1 | 2955.21 | 130.95 | 0 | 113.08 | 2711.18 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24288024000 |  | 100260052 |  | 7356256B | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 2121 HILTON AV | 019 | ASH | 2024-10-09 | U128523 | U125763 | 2024-09-30 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-07 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2606.73 | 0 | 0 | 0 | 2606.73 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24288024100 |  | 100260051 |  | 7356256B | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 2125 HILTON AV | 019 | ASH | 2024-10-09 | U128523 | U125763 | 2024-09-30 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-07 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2814.38 | 0 | 0 | 0 | 2814.38 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24288024200 |  | 100260050 |  | 7356256B | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 2129 HILTON AV | 019 | ASH | 2024-10-09 | U128523 | U125763 | 2024-09-30 | 2024-12-31 |  |  | JORDAN HIERONIMUS | 2024-10-04 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2755.9 | 0 | 0 | 0 | 2755.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24288024400 |  | 100260049 |  | 7356256B | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 2131 HILTON AV | 019 | ASH | 2024-10-09 | U128523 | U125763 | 2024-09-30 | 2024-12-31 |  |  | MITCHELL DICKESS CJH | 2024-10-04 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2848.78 | 0 | 0 | 0 | 2848.78 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24288024500 |  | 100260047 |  | 7356256B | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 2133 HILTON AV | 019 | ASH | 2024-10-03 | U123965 | U125763 | 2024-09-30 | 2024-12-31 |  |  | CJH JOSEPH HADLEY | 2024-10-03 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2924.26 | 0 | 0 | 0 | 2924.26 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24288024600 |  | 100260046 |  | 7356256B | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 2135 HILTON AV | 019 | ASH | 2024-10-03 | U123965 | U125763 | 2024-09-30 | 2024-12-31 |  |  | CJH JOSEPH HADLEY/MBLANKE | 2024-10-02 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2751.56 | 0 | 0 | 0 | 2751.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24288024700 |  | 100260045 |  | 7356256B | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 2137 HILTON AV | 019 | ASH | 2024-10-03 | U123965 | U125763 | 2024-09-30 | 2024-12-31 |  |  | CJH JOSEPH HADLEY/MBLANKE | 2024-10-01 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3297.33 | 0 | 0 | 0 | 3297.33 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24288024800 |  | 100260044 |  | 7356256B | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 2139 HILTON AV | 019 | ASH | 2024-10-01 | U123965 | U125763 | 2024-09-30 | 2024-12-31 |  |  | CJH JOSEPH HADLEY/MBLANKE | 2024-09-30 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2874.43 | 0 | 0 | 0 | 2874.43 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24288041300 |  | 501333762 |  | 6724204A | 2185117 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | NIGHT HERON | 3509 NIGHT HERON WY | 067 | LEX | 2024-10-10 | U461516 | U126856 | 2024-09-30 | 2024-10-01 | 2024-10-14 |  | NEAL JOHNSON | 2024-10-10 |  | 2024-10-10 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4534.64 | 480.26 | 311.23 | 394.8 | 3348.35 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24288042500 |  | 501327318 |  | 6716232B | 2179247 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | WELLESLY | 156 WELLESLY AV LT277 | 209 | GEO | 2024-10-16 | U123111 | U130616 | 2024-09-30 | 2024-10-02 | 2024-10-15 |  | LYN STAFFORD | 2024-10-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 1.15 | 1 | 4390.25 | 73.09 | 317.61 | 4.46 | 3995.09 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24288042600 |  | 501327319 |  | 6716232B | 2179247 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | WELLESLY | 154 WELLESLY AV LT278 | 209 | GEO | 2024-10-16 | U123111 | U130616 | 2024-09-30 | 2024-10-02 | 2024-10-15 |  | LYN STAFFORD | 2024-10-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4.5667 | 1 | 4202.19 | 281.83 | 317.61 | 17.27 | 3585.48 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24288042700 |  | 501327354 |  | 6716232B | 2179247 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | GALWAY | 120 GALWAY LN LT229 | 209 | GEO | 2024-10-15 | U128336 | U130616 | 2024-09-30 | 2024-10-02 | 2024-10-15 |  | JOSHUA COX | 2024-10-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4.45 | 1 | 1739.95 | 285.95 | 360.31 | 17.51 | 1076.18 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24288044400 |  | 500016332 |  | 6748204A |  |  |  | 566 | EX | ABANDON SL/ DEMO CUST REQ | 2621P | HAMILTON | 335 HAMILTON ST | 049 | WIN | 2024-10-26 | WHIMES | U139381 | 2024-09-30 | 2024-10-18 | 2024-11-11 |  | WHIMES | 2024-10-26 | 2024-10-25 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 6.8333 | 5 | 2533.28 | 435.48 | 20.28 | 33.52 | 2044 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24288044900 |  | 501327321 |  | 6716232B | 2179247 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | KIRKSTALL | 106 KIRKSTALL WY LT280C | 209 | GEO | 2024-10-15 | U461516 | U130616 | 2024-09-30 | 2024-10-02 | 2024-10-15 |  | NEAL JOHNSON | 2024-10-15 |  | 2024-10-15 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 1.95 | 1 | 1595.07 | 117.08 | 311.23 | 96.22 | 1070.54 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24288045000 |  | 501327345 |  | 6716232B | 2179247 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | KIRKSTALL | 109 KIRKSTALL WY LT263 | 209 | GEO | 2024-10-15 | U461516 | U130616 | 2024-09-30 | 2024-10-02 | 2024-10-15 |  | NEAL JOHNSON | 2024-10-15 |  | 2024-10-15 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 3.8167 | 1 | 4148.24 | 229.92 | 311.23 | 189.02 | 3418.07 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24288045100 |  | 501327346 |  | 6716232B | 2179247 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | KIRKSTALL | 107 KIRKSTALL WY LT264 | 209 | GEO | 2024-10-15 | U128336 | U130616 | 2024-09-30 | 2024-10-02 | 2024-10-15 |  | JOSHUA COX | 2024-10-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 5.55 | 1 | 3148.91 | 356.59 | 311.24 | 21.84 | 2459.24 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24288045400 |  | 100428451 |  | 6740232M |  |  |  | 566 | EX | ABANDON SL- PER J. TOY | 2621P | MAIN | 708 MAIN ST | 017 | PAR | 2024-10-03 | NRICHIE | U129534 | 2024-09-30 | 2024-11-08 | 2024-12-25 |  | NRICHIE | 2024-10-03 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9.0333 | 2 | 952.98 | 571.65 | 0 | 35.01 | 346.32 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24288045600 |  | 501338339 |  | 6716232B | 2179247 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | DUNMORE | 147 DUNMORE LN LT181 | 209 | GEO | 2024-10-15 | U126532 | U130616 | 2024-09-30 | 2024-10-02 | 2024-10-15 |  | LESLIE SHARON | 2024-10-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 1.7 | 1 | 2338.17 | 113.25 | 574.07 | 86.4 | 1564.45 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24288045900 |  | 501327307 |  | 6716232B | 2179247 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | DUNMORE | 134 DUNMORE LN LT212 | 209 | GEO | 2024-10-15 | U126532 | U130616 | 2024-09-30 | 2024-10-02 | 2024-10-15 |  | LESLIE SHARON | 2024-10-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 5.5667 | 1 | 3826.75 | 361.32 | 0 | 275.63 | 3189.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24288046400 |  | 100360051 |  | 6740232M |  |  |  | 566 | EX | ABANDON SL - PER J. TOY | 2621P | MAIN | 714 MAIN ST | 017 | PAR | 2024-10-03 | NRICHIE | U129534 | 2024-09-30 | 2024-11-08 | 2024-12-25 |  | NRICHIE | 2024-10-03 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.3667 | 2 | 984.93 | 212.17 | 39.78 | 12.98 | 720 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24288046900 |  | 100360050 |  | 6740232M |  |  |  | 566 | EX | ABANDON SL - PER J. TOY | 2621P | MAIN | 712 MAIN ST | 017 | PAR | 2024-10-03 | NRICHIE | U129534 | 2024-09-30 | 2024-11-08 | 2024-12-25 |  | NRICHIE | 2024-10-03 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.5667 | 0 | 1671.98 | 105.5 | 0 | 6.48 | 1560 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24288047200 |  | 100360049 |  | 6740232M |  |  |  | 566 | EX | ABANDON SL - PER J. TOY | 2621P | MAIN | 710 MAIN ST | 017 | PAR | 2024-10-03 | NRICHIE | U129534 | 2024-09-30 | 2024-11-08 | 2024-12-25 |  | NRICHIE | 2024-10-03 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.0333 | 0 | 960.86 | 127.05 | 0 | 7.81 | 826 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24288047900 |  | 501314731 |  | 6720208O |  |  |  | 563 | EX | 1" P SHORT/PRMT RCVD | 2600B | LAKE CLAIR | 601 LAKE CLAIR CT | 067 | LEX | 2024-10-25 | U126532 | U134375 | 2024-09-30 | 2024-10-16 | 2024-10-29 |  | LESLIE SHARON | 2024-10-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2770.53 | 520.8 | 293.42 | 397.28 | 1559.03 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24288132800 |  | 501370045 |  | 7360216E | 2407961 |  |  | 563 | EX | 1" P SHORT STATE PERMIT | 2621P | HWY 3 | 828 S HWY 3 | 127 | LOU | 2024-11-04 | U124604 | U132256 | 2024-10-01 | 2024-10-22 | 2024-10-22 |  | RECUMP | 2024-11-01 | 2024-10-30 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 28.9333 | 5 | 1854.29 | 1248.65 | 802.21 | -258.73 | 62.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24288133600 |  | 100313623 |  | 6716208B |  |  |  | 566 | EX | ABANDON SL/ CONVRT TO ELECTRIC | 2621P | JACANA | 1575 JACANA DR | 067 | LEX | 2024-11-06 | JGILES | U139381 | 2024-10-01 | 2024-10-21 | 2024-11-12 |  | JGILES | 2024-11-06 | 2024-11-04 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 14.3167 | 3 | 1542.05 | 1050.42 | 17.88 | 473.75 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24288162200 |  | 100252989 |  | 7356256F |  |  |  | 563 | EX | 1" P LONG | 2621P | SHORT | 3251 SHORT ST | 019 | ASH | 2024-10-16 | U141668 | U129294 | 2024-10-01 | 2024-10-15 | 2024-10-15 |  | ABHATFIE | 2024-10-15 | 2024-10-11 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 45.1833 | 6 | 2978.51 | 2823.42 | 89.47 | -12.82 | 78.44 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24288164000 |  | 100253189 |  | 7352256T |  |  |  | 566 | EX | ABANDON SL/ DEMO CUST REQ | 2621P | ROBERTS | 3742 ROBERTS DR | 019 | ASH | 2024-10-25 | DYOUNG | U139381 | 2024-10-01 | 2024-10-21 | 2024-11-12 |  | LAMAY | 2024-10-22 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 6 | 2 | 361.33 | 363.62 | 0 | -2.29 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24288185900 |  | 500065290 |  | 6684224M |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | US 127 | 2576 US 127 SO OFFICE | 073 | FRA | 2024-10-23 | U126332 | U124604 | 2024-10-01 | 2024-12-31 |  |  | DCOLLIN | 2024-10-22 | 2024-10-18 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 26.8833 | 5 | 3159.5 | 1693.66 | 0 | -160.16 | 1626 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24288197700 |  | 100239951 |  | 7344268N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | RIVERSIDE | 709 RIVERSIDE DR | 089 | RUS | 2024-10-01 | ABHATFIE | U129939 | 2024-10-01 | 2024-09-19 | 2024-10-07 |  | ABHATFIE | 2024-10-01 | 2024-09-30 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 24.6333 | 5 | 3513.8 | 3016.49 | 0 | 432.19 | 65.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24288201800 |  | 100351781 |  | 6744208O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BLOOMFIELD | 119 S BLOOMFIELD RD | 049 | WIN | 2024-10-02 | DENNING | U137585 | 2024-10-01 | 2024-10-01 | 2024-10-01 |  | DENNING | 2024-10-02 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 15.1 | 2 | 1464.51 | 1003.16 | 399.9 | 61.45 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24288271300 |  | 100263176 |  | 7384168K |  |  |  | 563 | EX | MANIFOLD W. 100263178 | 2621P | 5TH | 403 5TH ST APT 2 | 195 | S W | 2024-10-24 | U130172 | U131378 | 2024-10-02 | 2024-10-09 | 2024-10-09 |  | CHAMMOND | 2024-10-22 |  |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBMAN |  | 100 | 056332B26330011 | 0.016667 | 1 | 1.35 | 1.27 | 0 | 0.08 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24288305800 |  | 100244475 |  | 7356256L |  |  |  | 566 | EX | ABANDON SL/DEMO CUST REQ | 2621P | BELFORD | 3870 BELFORD ST | 019 | ASH | 2024-11-04 | MCOLLET | U139381 | 2024-10-02 | 2024-10-22 | 2024-11-13 |  | MCOLLET | 2024-11-04 | 2024-10-23 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 16.6 | 4 | 2482.41 | 1351.69 | 20.28 | 1110.44 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24288316100 |  | 100239554 |  | T-1727-9- | 2408621 |  |  | 563 | EX | 1.25" P LONG | 2621P | BOYD | 504 BOYD ST | 089 | RUS | 2024-10-22 | U124604 | U134341 | 2024-10-02 | 2024-10-16 | 2024-10-16 |  | MCOLLET | 2024-10-21 | 2024-10-08 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 30.15 | 6 | 6042.21 | 1976.82 | 218.44 | -172.49 | 4019.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24288325600 |  | 100329305 |  | 6720208G | 2403558 |  |  | 565 | EX | PER SCANOY/24026316700 | 2600B | SAINT PHILLIP | 137 SAINT PHILLIP DR | 067 | LEX | 2024-10-04 | U461322 | U125763 | 2024-10-02 | 2024-12-31 |  |  | STEVE CANOY | 2024-10-04 | 2024-10-03 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.7833 | 2 | 4188.32 | 736.67 | 0 | 537.03 | 2914.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24288424900 |  | 501345529 |  | 6716212D | 2396147 |  |  | 563 | EX | PAPER W/500275657 | 2600B | NEWTOWN | 690 NEWTOWN PK NORTH | 067 | LEX | 2024-10-07 | U125763 | U127708 | 2024-10-03 | 2024-10-17 | 2024-10-17 |  | OFFICE PER MANAGEMENT | 2024-10-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBPEX |  | 100 | 056332B26210012 |  | 1
KY | KY - EAST | 2631 | 24288438300 |  | 100244756 |  | 7356256G |  |  |  | 563 | EX | 1" P LONG | 2621P | BATH | 3143 BATH AV | 019 | ASH | 2024-10-15 | U123688 | U129531 | 2024-10-03 | 2024-10-18 | 2024-10-18 |  | MCOLLET | 2024-10-14 | 2024-10-08 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 25.8667 | 5 | 1905.57 | 1658.62 | 341.6 | -186.41 | 91.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24288440800 |  | 100418240 |  | 6720208J |  |  |  | 565 | EX | REPAIR/REPLACE SERVICE LINE | 2621P | BRIDGEPORT | 2059 BRIDGEPORT DR | 067 | LEX | 2024-10-03 | HMCKUNE | U139677 | 2024-10-03 | 2024-10-03 | 2024-10-03 |  | HMCKUNE | 2024-10-03 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.4833 | 4 | 1221.78 | 687.75 | 227.37 | 182.34 | 124.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24288453200 |  | 100418241 |  | 6720208J |  |  |  | 565 | EX | REPAIR/REPLACE SERVICE LINE | 2621P | BRIDGEPORT | 2063 BRIDGEPORT DR | 067 | LEX | 2024-10-03 | HMCKUNE | U139677 | 2024-10-03 | 2024-10-03 |  |  | HMCKUNE | 2024-10-03 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 9.2333 | 4 | 1059.52 | 548.49 | 227.37 | 132.7 | 150.96 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24288477900 |  | 100278653 |  | 6688232O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | NOOTKA | 428 NOOTKA TL | 073 | FRA | 2024-10-07 | U123688 | U139677 | 2024-10-03 | 2025-02-13 | 2026-08-31 |  | LSTANFI | 2024-10-03 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 | 0.36667 | 2 | 1199.5 | 786.35 | 235.15 | 43.32 | 134.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24288479000 |  | 100299735 |  | 6712212D |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | WESTLAND | 773 WESTLAND DR A | 067 | LEX | 2024-12-13 | U124604 | U124604 | 2024-10-03 | 2024-12-31 |  |  | RSTRONG | 2024-12-12 | 2024-12-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 42.1 | 11 | 5040.8 | 2654.81 | 169.69 | 586.16 | 1630.14 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24288480300 |  | 100345622 |  | 6700212I |  |  |  | 566 | EX | ABANDON SL/ DEMO CUST REQ | 2621P | LEXINGTON | 1140 LEXINGTON RD | 239 | VER | 2024-10-16 | U128410 | U139381 | 2024-10-03 | 2024-10-23 | 2024-11-14 |  | CDESPAIN | 2024-10-16 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 9.0333 | 2 | 1321 | 571.04 | 0 | 34.96 | 715 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24288517500 |  | 100301037 |  | 6716212E | 1635077 |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2621D | GARRETT | 221 GARRETT AV | 067 | LEX | 2025-02-19 | U124604 | AOC SYST | 2024-10-03 | 2025-12-31 | 2025-12-31 |  | CHEMMER | 2025-02-18 | 2024-11-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 23.9 | 6 | 2106.79 | 1631.19 | 281.66 | 77.02 | 116.92 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24288655400 |  | 100278353 |  | 6688232N |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | CHINOOK | 583 CHINOOK TL | 073 | FRA | 2024-11-05 | U124604 | U123688 | 2024-10-04 | 2024-12-26 |  |  | DCOLLIN | 2024-11-04 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 23.75 | 3 | 2875.83 | 1765.86 | 193.11 | 368.78 | 548.08 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24288680800 |  | 500532677 |  | 6692228E |  |  |  | 563 | EX | 99 1"P LONG/NO PRMT REQ | 2600B | ELMENDORF | 30 ELMENDORF LT199 | 073 | FRA | 2024-10-22 | U128336 | U134375 | 2024-10-04 | 2024-10-09 | 2024-10-22 |  | JOSHUA COX | 2024-10-22 | 2024-10-21 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 19.5 | 2 | 7618.31 | 1252.8 | 293.62 | 76.74 | 5995.15 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24288706300 |  | 100291347 |  | 6720216H |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | ELMWOOD | 241 ELMWOOD DR | 067 | LEX | 2024-10-04 | KKINDER | U139701 | 2024-10-04 | 2024-10-03 | 2024-10-21 |  | KKINDER | 2024-10-04 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 19.2167 | 4 | 1780.75 | 1588.68 | 0 | 97.35 | 94.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24288863700 |  | 501348004 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | CRAVAT PASS | 2141 CRAVAT PASS | 067 | LEX | 2024-10-18 | U461516 | U126856 | 2024-10-07 | 2024-10-08 | 2024-10-21 |  | NEAL JOHNSON | 2024-10-18 |  | 2024-10-18 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2887.31 | 480.26 | 304.84 | 394.8 | 1707.41 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24288866500 |  | 501333772 |  | 6724204A | 2185117 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | BAY SHOALS | 3480 BAY SHOALS DR | 067 | LEX | 2024-10-17 | U123111 | U126856 | 2024-10-07 | 2024-10-08 | 2024-10-21 |  | LYN STAFFORD | 2024-10-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4.5 | 1 | 3733.46 | 278.7 | 317.61 | 17.07 | 3120.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24288867500 |  | 501354164 |  | 6724204A | 2185117 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | BAY SHOALS | 3464 BAY SHOALS DR | 067 | LEX | 2024-10-17 | U123111 | U126856 | 2024-10-07 | 2024-10-08 | 2024-10-21 |  | LYN STAFFORD | 2024-10-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 3693.58 | 247.75 | 317.61 | 15.19 | 3113.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24288868200 |  | 501333756 |  | 6724204A | 2185117 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | NIGHT HERON | 3512 NIGHT HERON WY | 067 | LEX | 2024-10-17 | U126532 | U126856 | 2024-10-07 | 2024-10-08 | 2024-10-21 |  | LESLIE SHARON | 2024-10-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8.5 | 1 | 2802.26 | 553.36 | 280.66 | 422.12 | 1546.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24288893300 |  | 500637289 |  | 16736192I | 9720379 |  |  | 563 | EX | 1" P LONG | 2621P | WARRIORS | 1018 WARRIORS TR | 151 | RIC | 2024-10-25 | U123688 | U126856 | 2024-10-07 | 2024-10-21 | 2024-10-21 |  | DENNING | 2024-10-17 | 2024-10-14 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 16.0333 | 4 | 1826.36 | 1062.7 | 469.33 | 64.93 | 229.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24288916900 |  | 100424187 |  | 6712212O |  |  |  | 565 | EX | GRADE 1 REPLACE S/L | 2621P | CLARIDGE | 1094 CLARIDGE CT | 067 | LEX | 2024-10-08 | HMCKUNE | U129939 | 2024-10-07 | 2024-10-07 | 2024-10-07 |  | HMCKUNE | 2024-10-08 | 2024-10-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.6667 | 4 | 1468.36 | 868.32 | 375.53 | 224.51 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24288929000 |  | 100439140 |  | 6716216L | 0886373 |  |  | 563 | EX | 1' P SHORT/PRMT RCVD | 2600B | NANDINO | 960 NANDINO BV | 067 | LEX | 2024-10-31 | U123111 | U132805 | 2024-10-07 | 2024-10-22 | 2024-11-04 |  | LYN STAFFORD | 2024-10-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 3001.72 | 0 | 304.85 | 0 | 2696.87 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24288929200 |  | 501313759 |  | 6708204J | 2178312 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | LAFONTAINE | 113 LAFONTAINE CT LTLOT 2 | 113 | NIC | 2024-10-22 | U461516 | U129531 | 2024-10-07 | 2024-10-09 | 2024-10-22 |  | NEAL P JOHNSON | 2024-10-21 | 2024-10-21 | 2024-10-21 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 2759.91 | 240.14 | 497.83 | 197.41 | 1824.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24288929300 |  | 100305183 |  | 6712212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D310368 | 2621P | DARIEN | 1821 DARIEN DR | 067 | LEX | 2024-10-09 | U123688 | U123688 | 2024-10-07 | 2024-10-07 | 2024-10-07 |  | KKINDER | 2024-10-08 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.95 | 2 | 1409.04 | 929.67 | 422.42 | 56.95 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24288936200 |  | 100413120 |  | 7352252B |  |  |  | 566 | EX | ABANDON SL/DEMO CUST REQ | 2621P | LITTLE GARNER | 108 W LITTLE GARNER RD | 019 | ASH | 2025-02-17 | U124604 | U123688 | 2024-10-07 | 2024-11-01 | 2024-11-03 |  | RECUMP | 2025-02-14 | 2024-10-28 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 21.4167 | 5 | 4030.52 | 1623.13 | 20.28 | 394.71 | 1992.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24289212700 |  | 500887787 |  | 6712232P |  |  |  | 563 | EX | PAPER W/501245529 | 2621P | OUTLET CENTER | 401 OUTLET CENTER DR 105 | 209 | GEO | 2024-10-15 | U125763 | U127708 | 2024-10-08 | 2024-10-22 | 2024-10-22 |  | OFFICE PER MANAGEMNT | 2024-10-15 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26230011 |  | 1 | 56.24 | 0 | 0 | 0 | 56.24 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289228700 |  | 100463790 |  | 7348260D |  |  |  | 565 | EX | GRADE 1 SERV LINE REPLACEMENT | 2621P | SPARROW | 204 SPARROW CT | 089 | RUS | 2024-10-08 | RECUMP | U129939 | 2024-10-08 | 2024-10-08 | 2024-10-08 |  | RECUMP | 2024-10-08 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 10.2833 | 2 | 700.82 | 628.38 | 219.55 | -238.87 | 91.76 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289242600 |  | 500464827 |  | 7356216D | 1855491 |  |  | 566 | EX | ABANDON SL/18-0267944-00 | 2600B | BERRY | 207 BERRY ST | 127 | LOU | 2025-04-14 | U123965 | U139198 | 2024-10-08 | 2024-12-23 |  |  | MARCUS BLANKENSHIP | 2025-03-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 |  | 1
KY | KY - EAST | 2631 | 24289242700 |  | 100243594 |  | 7356216D | 1855491 |  |  | 565 | EX | REPLACE SL/18-0267944-00 | 2600B | BERRY | 304 BERRY ST | 127 | LOU | 2024-11-13 | U123965 | U139198 | 2024-10-08 | 2024-12-23 |  |  | CJH BRIAN MURDOCK | 2024-11-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2753.29 | 0 | 0 | 0 | 2753.29 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289242800 |  | 100243607 |  | 7356216D | 1855491 |  |  | 565 | EX | REPLACE SL/18-0267944-00 | 2600B | BURNS | 401 BURNS ST | 127 | LOU | 2025-01-27 | U123965 | U139198 | 2024-10-08 | 2024-12-23 |  |  | CJH MITCHELL DICKESS | 2025-01-27 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3311.55 | 0 | 0 | 0 | 3311.55 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289243000 |  | 100243611 |  | 7356216D | 1855491 |  |  | 565 | EX | REPLACE SL/18-0267944-00 | 2600B | MAIN CROSS | 309 N MAIN CROSS ST | 127 | LOU | 2025-01-27 | U123965 | U140376 | 2024-10-08 | 2024-12-23 |  |  | CJ HUGHES MICHELL DICKESS | 2025-01-27 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 | AMRCB |  | 100 | 056532B26310032 |  | 1 | 3455.87 | 63.29 | 0 | 23.59 | 3368.99 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289243100 |  | 100243571 |  | 7352256C | 1855491 |  |  | 565 | EX | REPLACE SL/18-0267944-00 | 2600B | SULLIVAN | 410 SULLIVAN ST | 127 | LOU | 2024-11-12 | U123965 | U133183 | 2024-10-08 | 2024-12-23 |  |  | CJH BRIAN MURDOCK | 2024-11-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1966.29 | 0 | 0 | 0 | 1966.29 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289243200 |  | 100243606 |  | 7356216D | 1855491 |  |  | 565 | EX | REPLACE SL/18-0267944-00 | 2600B | BURNS | 403 BURNS ST | 127 | LOU | 2024-12-12 | U123965 | U139198 | 2024-10-08 | 2024-12-23 |  |  | CJH BRENT RUNYON | 2024-12-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3348.59 | 0 | 0 | 0 | 3348.59 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289243400 |  | 100243572 |  | 7356216D | 1855491 |  |  | 565 | EX | REPLACE SL/18-0267944-00 | 2600B | BURNS | 406 BURNS ST | 127 | LOU | 2025-01-27 | U123965 | U139198 | 2024-10-08 | 2024-12-23 |  |  | CJ HUGHES JORDAN HIERONIMUS | 2025-01-27 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 4006.04 | 0 | 0 | 0 | 4006.04 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289243500 |  | 100243601 |  | 7356216D | 1855491 |  |  | 565 | EX | REPLACE SL/18-0267944-00 | 2600B | BURNS | 502 BURNS ST | 127 | LOU | 2024-11-09 | U123965 | U139198 | 2024-10-08 | 2024-12-23 |  |  | CJH GENE STEVENS/MBLANKE | 2024-11-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1891.13 | 0 | 0 | 0 | 1891.13 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289243700 |  | 100243587 |  | 7356216D | 1855491 |  |  | 565 | EX | REPLACE SL/18-0267944-00 | 2600B | MOORE | 407 MOORE ST | 127 | LOU | 2024-11-09 | U123965 | U140425 | 2024-10-08 | 2024-12-31 |  |  | CJH GENE STEVENS/MBLANKE | 2024-11-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 2689.64 | 0 | 0 | 0 | 2689.64 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289243900 |  | 100243610 |  | 7356216D | 1855491 |  |  | 565 | EX | REPLACE SL/18-0267944-00 | 2600B | MAIN CROSS | 311 N MAIN CROSS ST | 127 | LOU | 2025-01-03 | U123965 | U140376 | 2024-10-08 | 2024-12-23 |  |  | CJH CASEY PACK | 2025-01-02 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 | AMRCB |  | 100 | 056532B26310032 |  | 1 | 2912.48 | 0 | 0 | 0 | 2912.48 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289244000 |  | 100243586 |  | 7356216D | 1855491 |  |  | 565 | EX | REPLACE SL/18-0267944-00 | 2600B | MOORE | 409 MOORE ST | 127 | LOU | 2024-11-12 | U123965 | U140425 | 2024-10-08 | 2024-12-31 |  |  | CJH BRENT RUNYON | 2024-11-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 2006.67 | 0 | 0 | 0 | 2006.67 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289244700 |  | 100243602 |  | 7356216D | 1855491 |  |  | 565 | EX | REPLACE SL/18-0267944-00 | 2600B | MAIN CROSS | 508 N MAIN CROSS ST | 127 | LOU | 2024-11-14 | U123965 | U140376 | 2024-10-08 | 2024-12-23 |  |  | CJH BRENT RUNYON | 2024-11-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 | AMRCB |  | 100 | 056532B26310032 |  | 1 | 2431.67 | 0 | 0 | 0 | 2431.67 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289244900 |  | 500425871 |  | 7356220P | 1855491 |  |  | 565 | EX | REPLACE SL/18-0267944-00 | 2600B | MOORE | 310 MOORE ST C | 127 | LOU | 2024-11-13 | U123965 | U140376 | 2024-10-08 | 2024-12-23 |  |  | CJH BRENT RUNYON | 2024-11-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 | AMRCB |  | 100 | 056532B26310032 |  | 1 | 2368.7 | 0 | 0 | 0 | 2368.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289245100 |  | 500326884 |  | 7356220P | 1855491 |  |  | 565 | EX | REPLACE SL/18-0267944-00 | 2600B | MOORE | 403 MOORE ST | 127 | LOU | 2024-11-12 | U123965 | U140376 | 2024-10-08 | 2024-12-23 |  |  | CJH BRENT RUNYON | 2024-11-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 | AMRCB |  | 100 | 056532B26310032 |  | 1 | 2014.45 | 0 | 0 | 0 | 2014.45 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289246800 |  | 100243558 |  | 7352256C | 1855491 |  |  | 565 | EX | REPLACE SL/18-0267944-00 | 2600B | SULLIVAN | 308 SULLIVAN ST | 127 | LOU | 2024-11-14 | U123965 | U140425 | 2024-10-08 | 2024-12-31 |  |  | CJH CASEY PACK | 2024-11-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 2679.37 | 0 | 0 | 0 | 2679.37 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289252400 |  | 100243582 |  | 7356216D | 1855491 |  |  | 565 | EX | REPLACE SL/18-0267944-00 | 2600B | WATER | 409 N WATER ST | 127 | LOU | 2024-12-09 | U123965 | U133183 | 2024-10-08 | 2024-12-23 |  |  | CJH BRENT RUNYON | 2024-12-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2805.7 | 0 | 0 | 0 | 2805.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289252700 |  | 100243583 |  | 7356216D | 1855491 |  |  | 565 | EX | REPLACE SL/18-0267944-00 | 2600B | WATER | 411 N WATER ST | 127 | LOU | 2025-01-29 | U123965 | U133183 | 2024-10-08 | 2024-12-23 |  |  | CJH MITCHELL DICKESS | 2025-01-29 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3713.1 | 0 | 0 | 0 | 3713.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289253000 |  | 100243581 |  | 7356216D | 1855491 |  |  | 565 | EX | REPLACE SL/18-0267944-00 | 2600B | WATER | 415 N WATER ST | 127 | LOU | 2025-01-30 | U123965 | U133183 | 2024-10-08 | 2024-12-23 |  |  | CJH MITCHELL DICKESS | 2025-01-30 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2106.9 | 0 | 0 | 0 | 2106.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24289259900 |  | 100303572 |  | 6712208C |  |  |  | 565 | EX | GRADE 1 REPLACE SERVICE LINE | 2621P | OLEANDER | 2218 OLEANDER CT | 067 | LEX | 2024-10-09 | U123688 | U129939 | 2024-10-08 | 2024-10-08 | 2024-10-08 |  | LSTANFI | 2024-10-08 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.6333 | 2 | 611.69 | 403.43 | 215.84 | -7.58 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24289263800 |  | 500684348 |  | 7256276A | 9937177 |  |  | 565 | EX | REPLACE SERVCIE LINE | 2621P | US 68 | 1684 US 68 | 161 | MAY | 2024-10-31 | U124604 | U123688 | 2024-10-08 | 2024-12-31 |  |  | SDADAMS | 2024-10-30 | 2024-10-25 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26320031 | 21.8667 | 5 | 1986.34 | 1322.54 | 261.63 | 81.01 | 321.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24289264300 |  | 100323121 |  | 6716208L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D096637 | 2621P | SHIRLEE | 3033 SHIRLEE DR | 067 | LEX | 2024-12-03 | U137585 | U123688 | 2024-10-08 | 2025-04-08 | 2026-10-31 |  | LSTANFI | 2024-12-02 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24 | 3 | 2167.19 | 1613.34 | 0 | 431.01 | 122.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24289266300 |  | 100353514 |  | 7256280K |  |  |  | 563 | EX | 1" P SHORT | 2621P | 3RD | 233 W 3RD ST | 161 | MAY | 2024-10-24 | U124604 | U129531 | 2024-10-08 | 2024-10-29 | 2024-10-29 |  | RALLISO | 2024-10-23 | 2024-10-18 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26320011 | 30.1 | 9 | 1996.63 | 1756.49 | 0 | 214.98 | 25.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24289282300 |  | 100339055 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL/ DEMO CUST REQ | 2621P | WITTLAND | 122 WITTLAND LN | 067 | LEX | 2024-10-21 | MCRAIG | U139381 | 2024-10-08 | 2024-10-28 | 2024-11-19 |  | MCRAIG | 2024-10-21 | 2024-10-21 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.8833 | 3 | 508.84 | 660.21 | 39.78 | -191.15 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289287100 |  | 501371236 |  | 7348268N |  |  |  | 563 | EX | 1.25" P SHORT | 2621P | WORTHINGTON | 201 WORTHINGTON AV | 089 | WOR | 2024-10-23 | ABHATFIE | U129294 | 2024-10-08 | 2024-10-22 | 2024-10-22 |  | ABHATFIE | 2024-10-23 | 2024-10-14 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 29.2667 | 4 | 2042.79 | 1877.59 | 0 | 80.84 | 84.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24289524000 |  | 100293909 |  | 6720212A |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | BROADWAY | 801 N BROADWAY ST | 067 | LEX | 2024-10-10 | U930915 | U129939 | 2024-10-09 | 2024-10-09 |  |  | MCRAIG | 2024-10-09 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.48333 | 1 | 180.93 | 31.46 | 160.45 | -10.98 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24289524900 |  | 100423198 |  | 6720212A |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | BROADWAY | 801 N BROADWAY ST | 067 | LEX | 2024-10-09 | MCRAIG | U129939 | 2024-10-09 | 2024-10-09 |  |  | MCRAIG | 2024-10-09 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.033333 | 1 | 1.28 | 1.97 | 0 | -0.69 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24289525100 |  | 100293908 |  | 6720212A |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | BROADWAY | 801 N BROADWAY ST | 067 | LEX | 2024-10-09 | MCRAIG | U129939 | 2024-10-09 | 2024-10-09 |  |  | MCRAIG | 2024-10-09 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.55 | 1 | 23.48 | 36.07 | 0 | -12.59 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24289540700 |  | 100351892 |  | 6744208O |  |  |  | 563 | EX | 1" P LONG | 2600B | FULTON | 220 FULTON AV | 049 | WIN | 2024-10-24 | U461516 | U128272 | 2024-10-09 | 2024-10-11 | 2024-10-24 |  | NEAL JOHNSON | 2024-10-23 |  | 2024-10-23 | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 7.3833 | 1 | 3397.69 | 443.06 | 446.24 | 27.14 | 2481.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24289550800 |  | 501346246 |  | 6728208I | 2396366 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | TWILIGHT SHADO | 1190 TWILIGHT SHADO DR | 067 | LEX | 2024-10-18 | U123111 | U126856 | 2024-10-09 | 2024-10-11 | 2024-10-24 |  | LYN STAFFORD | 2024-10-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2390.99 | 495.48 | 317.61 | 30.37 | 1547.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24289556300 |  | 100303411 |  | 6712208C |  |  |  | 565 | EX | GRADE 1 REPLACE SL | 2621P | WINTERBERRY | 2212 WINTERBERRY DR A | 067 | LEX | 2024-10-10 | HMCKUNE | U141867 | 2024-10-09 | 2024-10-09 | 2024-10-09 |  | HMCKUNE | 2024-10-10 | 2024-10-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.6 | 3 | 1530.34 | 1037.9 | 428.87 | 63.57 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24289583100 |  | 501358730 |  | 6700212O | 2398395 |  |  | 563 | EX | 1" P LONG BALL HOMES | 2600B | ABINGDON | 557 ABINGDON AV | 239 | VER | 2024-10-25 | U461516 | U126856 | 2024-10-09 | 2024-10-11 | 2024-10-24 |  | NEAL JOHNSON | 2024-10-24 |  | 2024-10-24 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 9 | 1 | 4755.97 | 540.31 | 311.23 | 444.15 | 3460.28 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24289583600 |  | 500899055 |  | 6676224K | 0356194 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | OLD STATION | 505 OLD STATION RD | 073 | FRA | 2024-10-29 | U123111 | U126856 | 2024-10-09 | 2024-10-16 | 2024-10-29 |  | LYN STAFFORD | 2024-10-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 2537.69 | 495.53 | 311.24 | 30.37 | 1700.55 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289606700 |  | 100250808 |  | 7336268-D |  |  |  | 563 | EX | 99 1"P SHORT | 2621P | PERRY | 214 PERRY ST 1 | 089 | GRE | 2024-10-29 | DYOUNG | U132253 | 2024-10-09 | 2024-10-23 | 2024-11-06 |  | MCOLLET | 2024-10-28 | 2024-10-23 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 21.1833 | 4 | 2059.55 | 1385.13 | 0 | 637.42 | 37 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289606800 |  | 100250809 |  | 7336268-D |  |  |  | 563 | EX | MANIFOLD W/100250808 | 2621P | PERRY | 214 PERRY ST 2 | 089 | GRE | 2024-10-29 | DYOUNG | U132253 | 2024-10-09 | 2024-10-23 | 2024-11-06 |  | MCOLLET | 2024-10-28 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBMAN |  | 100 | 056332B26310011 | 0.1 | 0 | 11.63 | 6.65 | 0 | 4.98 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289606900 |  | 100428591 |  | T-1624-10 |  |  |  | 563 | EX | MANIFOLD W/100250808 | 2621P | PERRY | 214 PERRY ST 3 | 089 | GRE | 2024-10-29 | U124604 | U132253 | 2024-10-09 | 2024-10-23 | 2024-11-06 |  | MCOLLET | 2024-10-28 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBMAN |  | 100 | 056332B26310011 | 0.13333 | 1 | 109.22 | 8.67 | 94.06 | 6.49 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289635000 |  | 100267128 |  | 7352260N | 1635077 |  |  | 565 | EX | REPLACE SERVICE LINE- D359725 | 2631D | JANE HILL | 212 JANE HILL RD | 019 | ASH | 2025-05-09 | ABHATFIE | AOC SYST | 2024-10-09 | 2025-04-09 | 2026-10-31 |  | ABHATFIE | 2025-05-09 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 | KYACA |  | 100 | 056532B26310021 | 19.1667 | 2 | 1451.61 | 1372.17 | 0 | 79.44 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24289733900 |  | 501348647 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | CALISTA FLAT | 796 CALISTA FLAT | 067 | LEX | 2024-10-18 | U128336 | U126856 | 2024-10-10 | 2024-10-11 | 2024-10-24 |  | JOSHUA COX | 2024-10-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4802.41 | 513.96 | 311.23 | 31.48 | 3945.74 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289753300 |  | 500026653 |  | 7356216D |  |  |  | 563 | EX | 1"P SHORT | 2621P | ROBINSON | 305 ROBINSON ST | 127 | LOU | 2024-10-28 | U124604 | U128266 | 2024-10-10 | 2024-10-11 | 2024-10-24 |  | RECUMP | 2024-10-25 | 2024-10-24 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 25.9167 | 4 | 1500.33 | 1583.04 | 358.51 | -475.26 | 34.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24289756600 |  | 100328491 |  | 6720208F |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | CLINTON | 404 CLINTON RD | 067 | LEX | 2024-11-08 | JGILES | U123688 | 2024-10-10 | 2024-12-31 |  |  | JGILES | 2024-11-08 | 2024-10-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 42.6 | 9 | 7370.4 | 2691.93 | 1000.53 | 854.42 | 2823.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24289757800 |  | 100296167 |  | 6716216O |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | ERIE | 470 ERIE RD | 067 | LEX | 2024-11-21 | U124604 | U123688 | 2024-10-10 | 2024-12-31 |  |  | TROE | 2024-11-20 | 2024-11-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24 | 3 | 1888.24 | 1466.25 | 333.74 | 88.25 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24289764600 |  | 100295231 |  | 6716216P |  |  |  | 565 | EX | RELOC SERVICE LINE | 2621P | HASKINS | 543 HASKINS DR | 067 | LEX | 2024-10-21 | HSTANFI | U123688 | 2024-10-10 | 2024-12-31 |  |  | HSTANFI | 2024-10-21 | 2024-10-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 33.1833 | 5 | 2439.03 | 1861.79 | 463.18 | 114.06 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289772700 |  | 500024386 |  | 7352256C | 1855491 |  |  | 565 | EX | REPLACE SL/18-0267944-00 | 2600B | SULLIVAN | 312 SULLIVAN ST | 127 | LOU | 2025-01-30 | U123965 | U125201 | 2024-10-10 | 2024-12-23 |  |  | CJH MICHELL DICKESS | 2025-01-29 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2664.55 | 0 | 0 | 0 | 2664.55 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289772800 |  | 500023018 |  | 7352256C | 1855491 |  |  | 565 | EX | REPLACE SL/18-0267944-00 | 2600B | SULLIVAN | 314 SULLIVAN ST | 127 | LOU | 2024-12-13 | U123965 | U125201 | 2024-10-10 | 2024-12-23 |  |  | CJH BRENT RUNYON | 2024-12-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3384.66 | 0 | 0 | 0 | 3384.66 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289773000 |  | 100243564 |  | 7352256C | 1855491 |  |  | 565 | EX | REPLACE SL/18-0267944-00 | 2600B | SULLIVAN | 318 SULLIVAN ST | 127 | LOU | 2024-11-15 | U123965 | U125201 | 2024-10-10 | 2024-12-23 |  |  | CJH BRIAN MURDOCK | 2024-11-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2614.86 | 0 | 0 | 0 | 2614.86 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289773100 |  | 100243565 |  | 7356216D | 1855491 |  |  | 565 | EX | REPLACE SL/18-0267944-00 | 2600B | SULLIVAN | 320 SULLIVAN ST | 127 | LOU | 2024-11-15 | U123965 | U125201 | 2024-10-10 | 2024-12-23 |  |  | CJH BRENT RUNYON | 2024-11-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2566.7 | 0 | 0 | 0 | 2566.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289773400 |  | 100243567 |  | 7352256C | 1855491 |  |  | 565 | EX | REPLACE SL/18-0267944-00 | 2600B | SULLIVAN | 323 SULLIVAN ST | 127 | LOU | 2024-12-17 | U123965 | U125201 | 2024-10-10 | 2024-12-23 |  |  | CJH BRENT RUNYON | 2024-12-17 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 20232.78 | 0 | 17301.15 | 0 | 2931.63 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289773700 |  | 100243566 |  | 7352256C | 1855491 |  |  | 565 | EX | REPLACE SL/18-0267944-00 | 2600B | SULLIVAN | 324 SULLIVAN ST | 127 | LOU | 2024-12-19 | U123965 | U125201 | 2024-10-10 | 2024-12-23 |  |  | CJH BRENT RUNYON | 2024-12-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3879.9 | 0 | 0 | 0 | 3879.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289786800 |  | 100267127 |  | 7352260N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D359726 | 2621P | JANE HILL | 210 JANE HILL RD | 019 | ASH | 2025-05-09 | ABHATFIE | U123688 | 2024-10-10 | 2025-04-09 | 2026-10-31 |  | ABHATFIE | 2025-05-09 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.83333 | 2 | 2600.37 | 64.65 | 0 | 3.73 | 2531.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24289787200 |  | 100303577 |  | 6712208C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D506732 | 2621P | OLEANDER | 2112 OLEANDER DR | 067 | LEX | 2024-11-06 | U124604 | U123688 | 2024-10-10 | 2025-04-09 | 2026-10-31 |  | MCRAIG | 2024-11-05 | 2024-11-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.6 | 5 | 2651.77 | 1389.38 | 482.01 | 780.38 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24289790400 |  | 100305158 |  | 6712212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D514421 | 2621P | MERIDIAN | 1086 MERIDIAN CT | 067 | LEX | 2025-01-31 | U124604 | U123688 | 2024-10-10 | 2025-04-09 | 2026-10-31 |  | JOCHOA | 2025-01-30 | 2025-01-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.25 | 4 | 2093.67 | 1355.47 | 564.65 | 89.19 | 84.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24289791000 |  | 100305013 |  | 6712212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D514423 | 2621P | ALEXANDRIA | 1785 ALEXANDRIA DR | 067 | LEX | 2025-01-31 | U124604 | U123688 | 2024-10-10 | 2025-04-09 | 2026-10-31 |  | KOBRYAN | 2025-01-30 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 28.2667 | 4 | 1892.81 | 1382.86 | 340.52 | 90.99 | 78.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24289791600 |  | 100305378 |  | 6712212K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D514424 | 2621P | TRAVELLER | 1671 TRAVELLER RD | 067 | LEX | 2025-02-14 | U124604 | U123688 | 2024-10-10 | 2025-04-09 | 2026-10-31 |  | RSTRONG | 2025-02-13 | 2025-02-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25.6 | 4 | 2698.55 | 1925.62 | 463.4 | 309.53 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24289796800 |  | 501322262 |  | 6708232O | 2184915 |  |  | 563 | EX | 2" P SHORT/PRMT RCVD | 2600B | BETSY | 105 BETSY WY GENERAT | 209 | GEO | 2024-11-07 | U126530 | U127708 | 2024-10-10 | 2024-10-25 | 2024-11-07 |  | JDUNN | 2024-11-07 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 20 | 2 | 8668.11 | 1497.58 | 0 | 90.13 | 7080.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24289803200 |  | 100303361 |  | 6712208C |  |  |  | 565 | EX | REPLACE SERVCIE LINE D506734 | 2621P | JUNIPER | 1033 JUNIPER DR | 067 | LEX | 2024-10-23 | U124604 | U123688 | 2024-10-10 | 2024-10-11 | 2024-10-31 |  | RSTRONG | 2024-10-22 | 2024-10-21 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.5333 | 4 | 1265.64 | 1239.05 | 196.31 | -169.72 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24289805100 |  | 100309219 |  | 6712208D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | WEYBRIDGE | 2005 WEYBRIDGE CT | 067 | LEX | 2024-10-12 | U123688 | U123688 | 2024-10-10 | 2024-10-10 | 2024-10-10 |  | LSTANFI | 2024-10-10 | 2024-10-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.8667 | 3 | 1090.12 | 949.18 | 207.46 | -66.52 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24289814600 |  | 100303347 |  | 6712208D |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | ALEXANDRIA | 2025 ALEXANDRIA DR | 067 | LEX | 2025-03-18 | U124604 | U123688 | 2024-10-10 | 2024-12-31 |  |  | JOCHOA | 2025-03-17 | 2025-01-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 24.8167 | 8 | 2090.45 | 1535.66 | 326.33 | 90.82 | 137.64 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24289852500 |  | 100267196 |  | 7352260M |  |  |  | 565 | EX | GR 2+ LEAK ON SL D359727 | 2631D | LAVERNE | 108 LAVERNE CT | 019 | ASH | 2024-10-28 | LAMAY | AOC SYST | 2024-10-10 | 2024-10-11 | 2024-10-31 |  | LAMAY | 2024-10-28 | 2024-10-25 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 15.35 | 3 | 650.67 | 937.08 | 0 | -341.17 | 54.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24289992200 |  | 100310487 |  | 6712208L |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | CECIL | 623 CECIL WY | 067 | LEX | 2025-02-10 | JOCHOA | U123688 | 2024-10-11 | 2024-12-31 |  |  | JOCHOA | 2025-02-10 | 2024-11-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 37.75 | 8 | 3381.19 | 2605.27 | 457.53 | 149.67 | 168.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24289993100 |  | 501334669 |  | 6716216E | 2289300 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | DAHLIA | 645 DAHLIA DR | 067 | LEX | 2024-10-22 | U123111 | U126856 | 2024-10-11 | 2024-10-14 | 2024-10-25 |  | LYN STAFFORD | 2024-10-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4358.09 | 495.48 | 317.62 | 30.37 | 3514.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24289999900 |  | 100303319 |  | 6712208C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D506735 | 2621P | CAMELLIA | 1025 CAMELLIA DR | 067 | LEX | 2024-11-19 | U137585 | U123688 | 2024-10-11 | 2025-04-10 | 2026-10-31 |  | RSTRONG | 2024-11-18 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16 | 2 | 1224.13 | 946.42 | 0 | 206.67 | 71.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290000100 |  | 100305362 |  | 6712212K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D513553 | 2621P | CROSS KEYS | 1283 CROSS KEYS RD | 067 | LEX | 2025-01-29 | U124604 | U123688 | 2024-10-11 | 2025-04-10 | 2026-10-31 |  | TROE | 2025-01-28 | 2025-01-22 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 31.1 | 7 | 2436.99 | 1808.65 | 393.9 | 119 | 115.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290001600 |  | 100305333 |  | 6712212N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D513554 | 2621P | LANE ALLEN | 1169 LANE ALLEN RD | 067 | LEX | 2025-03-27 | U124604 | U123688 | 2024-10-11 | 2025-04-10 | 2026-10-31 |  | ABLAKE | 2025-03-26 | 2025-01-22 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.3 | 5 | 2120.9 | 1546.05 | 485.16 | 89.69 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290001900 |  | 100305285 |  | 6712212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D513555 | 2621P | LINSTEAD | 1632 LINSTEAD DR | 067 | LEX | 2025-02-06 | U124604 | U123688 | 2024-10-11 | 2025-04-10 | 2026-10-31 |  | CHEMMER | 2025-02-05 | 2025-01-22 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.2 | 3 | 1775.57 | 1208.54 | 398.84 | 57.19 | 111 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290002000 |  | 100305063 |  | 6712212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D513557 | 2621P | MANASSAS | 1883 MANASSAS DR | 067 | LEX | 2025-03-28 | U124604 | U123688 | 2024-10-11 | 2025-04-10 | 2026-10-31 |  | CHEMMER | 2025-03-27 | 2025-03-27 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.5 | 3 | 1490.28 | 974.65 | 382.98 | 57.17 | 75.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290002200 |  | 100305296 |  | 6712212K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D513558 | 2621P | WILLIAMSBURG | 1695 WILLIAMSBURG RD | 067 | LEX | 2024-12-20 | U137585 | U123688 | 2024-10-11 | 2025-04-10 | 2026-10-31 |  | JGILES | 2024-12-19 | 2024-12-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 26.7 | 6 | 2679.59 | 1725.84 | 0 | 844.23 | 109.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290002400 |  | 100305321 |  | 6712212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - S513559 | 2621P | WILLIAMSBURG | 1805 WILLIAMSBURG RD | 067 | LEX | 2024-12-18 | U137585 | U123688 | 2024-10-11 | 2025-04-10 | 2026-10-31 |  | MCRAIG | 2024-12-17 | 2024-12-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 33.1667 | 7 | 2572.79 | 1987.69 | 0 | 435.62 | 149.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290021300 |  | 100312353 |  | 6716208J |  |  |  | 563 | EX | 1"P SHORT/PRMT RCVD | 2600B | HOLLYHILL | 308 HOLLYHILL DR | 067 | LEX | 2024-11-07 | U461516 | U123852 | 2024-10-11 | 2024-10-25 | 2024-11-07 |  | NEAL JOHNSON | 2024-11-07 |  | 2024-11-07 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2447.55 | 570.61 | 455.66 | 269.85 | 1151.43 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24290024100 |  | 100345916 |  | 6704208A |  |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | LILAC | 309 LILAC CT | 239 | VER | 2024-10-29 | U126532 | U129294 | 2024-10-11 | 2024-10-16 | 2024-10-29 |  | LESLIE SHARON | 2024-10-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 2729.86 | 520.8 | 249.93 | 397.28 | 1561.85 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24290026000 |  | 100276332 |  | 6 |  |  |  | 563 | EX | 1" P LONG/PRMT RCVD | 2600B | WRIGHT | 241 WRIGHT ST | 073 | FRA | 2024-11-06 | U461516 | U130192 | 2024-10-11 | 2024-10-22 | 2024-11-04 |  | NEAL P JOHNSON | 2024-11-04 |  | 2024-11-04 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 3.8833 | 1 | 3839.78 | 276.06 | 391.86 | 130.54 | 3041.32 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24290050000 |  | 501358737 |  | 6700212O | 2398395 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | ABINGDON | 525 ABINGDON AV | 239 | VER | 2024-10-25 | U461516 | U126856 | 2024-10-11 | 2024-10-16 | 2024-10-29 |  | NEAL JOHNSON | 2024-10-25 |  | 2024-10-25 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 4279.58 | 480.26 | 311.23 | 394.8 | 3093.29 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290174400 |  | 501348636 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | CLEMATIS | 2204 CLEMATIS WY | 067 | LEX | 2024-10-24 | U123111 | U126856 | 2024-10-14 | 2024-10-16 | 2024-10-29 |  | LYN STAFFORD | 2024-10-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4274.27 | 495.48 | 317.62 | 30.37 | 3430.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290175200 |  | 100303548 |  | 6712208C |  |  |  | 565 | EX | REPLACE SL-LEAKAGE- D506736 | 2621P | PALMS | 2143 PALMS DR | 067 | LEX | 2024-11-14 | U123688 | U124604 | 2024-10-14 | 2025-04-11 | 2026-10-31 |  | RSTRONG | 2024-11-13 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16 | 2 | 1672.08 | 1134.93 | 202.69 | 334.46 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24290188500 |  | 100419840 |  | 7336268H | 2408495 |  |  | 563 | EX | 20 1" P SHORT ***RUSH*** | 2621P | ELM | 404 ELM ST | 089 | GRE | 2024-10-28 | U124604 | U126919 | 2024-10-14 | 2024-10-15 | 2024-10-28 |  | MCOLLET | 2024-10-25 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 11.9667 | 2 | 1051.24 | 786.47 | 263.05 | -50.08 | 51.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290219400 |  | 501346232 |  | 6728208I | 2396366 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | TWILIGHT SHADO | 1179 TWILIGHT SHADO DR LT127 | 067 | LEX | 2024-10-22 | U461516 | U130192 | 2024-10-14 | 2024-10-16 | 2024-10-29 |  | NEAL JOHNSON | 2024-10-22 |  | 2024-10-22 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4751.15 | 480.26 | 304.85 | 394.8 | 3571.24 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24290220000 |  | 500480421 |  | 6676224L |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BRIDGEPORT | 550 BRIDGEPORT RD | 073 | FRA | 2024-10-16 | U126332 | U129939 | 2024-10-14 | 2025-03-11 | 2026-09-30 |  | KKINDER | 2024-10-14 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 | 9.7333 | 2 | 1085.44 | 907.02 | 0 | 55.58 | 122.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24290227600 |  | 100349075 |  | 6748208M |  |  |  | 566 | EX | ABANDON SL/DEMO CUST REQ | 2621P | PARK | 37 PARK AV | 049 | WIN | 2024-11-06 | U123688 | U139381 | 2024-10-14 | 2024-11-01 | 2024-11-25 |  | DENNING | 2024-11-05 | 2024-10-25 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 7.4 | 6 | 868.59 | 585.42 | 62.81 | 220.36 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24290228200 |  | 100253662 |  | 7364188H |  |  |  | 565 | EX | GRADE 1 REPLACE SERVIE LINE | 2621P | BLACKLOG | 1489 BLACKLOG RD | 159 | INE | 2024-10-16 | U141668 | U129939 | 2024-10-14 | 2024-10-14 | 2024-10-14 |  | JAHOWARD | 2024-10-15 | 2024-10-14 |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 46.2167 | 5 | 5943.6 | 2665.77 | 19.07 | 163.32 | 3095.44 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24290229100 |  | 100349710 |  | 6748204A |  |  |  | 566 | EX | ABANDON SL/DEMO CUST REQ | 2621P | CENTRAL | 138 CENTRAL AV | 049 | WIN | 2024-11-22 | DENNING | U139381 | 2024-10-14 | 2024-11-01 | 2024-11-25 |  | DENNING | 2024-11-22 | 2024-10-25 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9.5 | 4 | 1593.74 | 795.52 | 341.01 | 457.21 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24290239500 |  | 100273974 |  | 6684224A |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D311034 | 2621P | PARKSIDE | 130 PARKSIDE DR | 073 | FRA | 2024-10-16 | U141668 | U124604 | 2024-10-14 | 2024-10-14 | 2024-10-14 |  | EFGOINS | 2024-10-15 | 2024-10-15 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 14.55 | 2 | 2228.19 | 871.54 | 70.26 | 53.39 | 1233 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24290242500 |  | 501344280 |  | 6700224H | 2395869 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | LACEFIELD | 100 LACEFIELD ST A | 239 | MID | 2024-10-28 | U126532 | U127708 | 2024-10-14 | 2024-10-16 | 2024-10-29 |  | LESLIE SHARON | 2024-10-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 13 | 1 | 5302.39 | 846.27 | 1045.84 | 51.84 | 3358.44 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24290242600 |  | 501372477 |  | 6700224H | 2395869 |  |  | 563 | EX | MANIFOLD W/501344280 | 2600B | LACEFIELD | 100 LACEFIELD ST B | 239 | MID | 2024-10-28 | U126532 | U127708 | 2024-10-14 | 2024-10-16 | 2024-10-29 |  | LESLIE SHARON | 2024-10-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBMAN |  | 100 | 056332B26230012 |  | 1 | 375.72 | 0 | 0 | 0 | 375.72 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24290242700 |  | 501372478 |  | 6700224H | 2395869 |  |  | 563 | EX | MANIFOLD W/501344280 | 2600B | LACEFIELD | 100 LACEFIELD ST C | 239 | MID | 2024-10-28 | U126532 | U127708 | 2024-10-14 | 2024-10-16 | 2024-10-29 |  | LESLIE SHARON | 2024-10-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBMAN |  | 100 | 056332B26230012 |  | 1 | 375.72 | 0 | 0 | 0 | 375.72 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24290242800 |  | 501372479 |  | 6700224H | 2395869 |  |  | 563 | EX | MANIFOLD W/501344280 | 2600B | LACEFIELD | 100 LACEFIELD ST D | 239 | MID | 2024-10-28 | U126532 | U127708 | 2024-10-14 | 2024-10-16 | 2024-10-29 |  | LESLIE SHARON | 2024-10-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBMAN |  | 100 | 056332B26230012 |  | 1 | 375.72 | 0 | 0 | 0 | 375.72 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24290242900 |  | 501372480 |  | 6700224H | 2395869 |  |  | 563 | EX | MANIFOLD W/501344280 | 2600B | LACEFIELD | 100 LACEFIELD ST E | 239 | MID | 2024-10-28 | U126532 | U127708 | 2024-10-14 | 2024-10-16 | 2024-10-29 |  | LESLIE SHARON | 2024-10-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBMAN |  | 100 | 056332B26230012 |  | 1 | 375.72 | 0 | 0 | 0 | 375.72 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24290243000 |  | 501372481 |  | 6700224H | 2395869 |  |  | 563 | EX | MANIFOLD W/501344280 | 2600B | LACEFIELD | 100 LACEFIELD ST F | 239 | MID | 2024-10-28 | U126532 | U127708 | 2024-10-14 | 2024-10-16 | 2024-10-29 |  | LESLIE SHARON | 2024-10-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBMAN |  | 100 | 056332B26230012 |  | 1 | 375.72 | 0 | 0 | 0 | 375.72 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24290244500 |  | 100278449 |  | 6688228B |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HIAWATHA | 499 HIAWATHA TL | 073 | FRA | 2024-11-08 | DCOLLIN | U124604 | 2024-10-14 | 2024-12-31 |  |  | DCOLLIN | 2024-11-08 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 15.9 | 2 | 2545.55 | 1158.67 | 644.85 | 333.23 | 408.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290246600 |  | 501346021 |  | 6728208I | 2396366 |  |  | 563 | EX | 1" P LONG MULBERRY | 2600B | STOLEN HORSE | 3476 STOLEN HORSE TC LT64 | 067 | LEX | 2024-10-21 | U126602 | U134375 | 2024-10-14 | 2024-10-16 | 2024-10-29 |  | DEREK PAYTON | 2024-10-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 10 | 1 | 4395.26 | 661.26 | 287.04 | 40.53 | 3406.43 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290262800 |  | 100301282 |  | 6712212H | 1635077 |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2621D | DUNKIRK | 1921 DUNKIRK DR | 067 | LEX | 2025-02-13 | U137585 | AOC SYST | 2024-10-14 | 2025-12-31 | 2025-12-31 |  | JOCHOA | 2025-02-12 | 2024-11-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 23 | 6 | 1631.76 | 1556.94 | 0 | 74.82 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290527400 |  | 501334666 |  | 6716216E | 2289300 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | DAHLIA | 641 DAHLIA DR | 067 | LEX | 2024-10-24 | U123111 | U126856 | 2024-10-15 | 2024-10-16 | 2024-10-29 |  | LYN STAFFORD | 2024-10-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2646.1 | 495.48 | 317.62 | 30.37 | 1802.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290538800 |  | 501359273 |  | 6712212D | 2403294 |  |  | 563 | EX | PAPER W/100443385 | 2621P | WESTLAND | 764 WESTLAND DR SUITE B | 067 | LEX | 2024-10-18 | U125763 | U127708 | 2024-10-15 | 2024-10-29 | 2024-10-29 |  | OFFICE PER MGMNT | 2024-10-18 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26210011 |  | 1 | 23.68 | 0 | 0 | 0 | 23.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290541000 |  | 100319633 |  | 6716208K |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D096643 | 2621P | ZANDALE | 221 ZANDALE DR | 067 | LEX | 2024-12-13 | U124604 | U124604 | 2024-10-15 | 2025-04-14 | 2026-10-31 |  | RJCRAWF | 2024-12-12 | 2024-12-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 27.75 | 6 | 4590.32 | 1774.83 | 520.3 | 103.64 | 2191.55 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290542300 |  | 100319635 |  | 6716208K |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D096644 | 2621P | ZANDALE | 213 ZANDALE DR | 067 | LEX | 2024-12-16 | U124604 | U124604 | 2024-10-15 | 2025-04-14 | 2026-10-31 |  | RJCRAWF | 2024-12-13 | 2024-12-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.5667 | 5 | 1301.21 | 773.54 | 322.65 | 45.18 | 159.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290544000 |  | 100323176 |  | 6716208P |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D096646 | 2621P | SHERWOOD | 762 SHERWOOD DR | 067 | LEX | 2025-05-27 | U124604 | U124604 | 2024-10-15 | 2025-04-14 | 2026-10-31 |  | WCRIM | 2025-05-23 | 2025-01-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 41.0833 | 14 | 2555.42 | 2139.56 | 246.67 | 124.79 | 44.4 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24290545500 |  | 100269350 |  | 6736252I |  |  |  | 563 | EX | 1" P SHORT | 2621P | ST EDWARDS | 18 ST EDWARDS LN | 097 | CYN | 2024-11-01 | U124604 | U132258 | 2024-10-15 | 2024-10-29 | 2024-11-12 |  | NRICHIE | 2024-10-31 | 2024-10-25 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 16.6 | 4 | 1218.44 | 548.03 | 223.69 | 412.68 | 34.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290546900 |  | 100301351 |  | 6712212H |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D513530 | 2621P | RUGBY | 222 RUGBY RD | 067 | LEX | 2024-12-10 | U137585 | U124604 | 2024-10-15 | 2025-04-14 | 2026-10-31 |  | MCRAIG | 2024-12-09 | 2024-12-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24 | 3 | 2433.39 | 1552.27 | 0 | 764.2 | 116.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290548400 |  | 100302783 |  | 6712212K |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | VERSAILLES | 2492 VERSAILLES RD | 067 | LEX | 2024-10-16 | U141668 | U132424 | 2024-10-15 | 2024-10-15 | 2024-10-15 |  | ATWILLI | 2024-10-15 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.5 | 3 | 2000.11 | 851.16 | 318.12 | 280.5 | 550.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290557800 |  | 100318832 |  | 6716204F |  |  |  | 565 | EX | METER MOVEOUT/RELO CUST REQ | 2621P | ABERDEEN | 232 ABERDEEN DR | 067 | LEX | 2024-11-11 | LSTANFI | U124604 | 2024-10-15 | 2024-12-31 |  |  | LSTANFI | 2024-11-11 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 15.6667 | 4 | 1357.17 | 1067.6 | 225.3 | 64.27 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290566000 |  | 501365730 |  | 6716216M | 0462053 |  |  | 563 | EX | 2" P SHORT/PRMT RCVD | 2600B | SHARKEY | 1781 SHARKEY WY 115 | 067 | LEX | 2024-11-11 | U126284 | U126856 | 2024-10-15 | 2024-10-29 | 2024-11-11 |  | JOSH PASLEY | 2024-11-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 13 | 1 | 6085.07 | 1037.93 | 0 | 62.48 | 4984.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290566500 |  | 100305102 |  | 6712212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D513550 | 2621P | TRAVELLER | 1740 TRAVELLER RD | 067 | LEX | 2025-04-01 | U124604 | U123688 | 2024-10-15 | 2025-06-30 |  |  | KKINDER | 2025-03-31 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 15.5 | 2 | 1459.37 | 1022.13 | 377.32 | 59.92 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24290578000 |  | 100273890 |  | 6680228H |  |  |  | 565 | EX | REPLACE SERVICE LINE D513655 | 2621P | MOSS | 801 MOSS LN | 073 | FRA | 2024-10-21 | DCOLLIN | U124604 | 2024-10-15 | 2024-10-18 | 2024-11-05 |  | DCOLLIN | 2024-10-21 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 16 | 2 | 2067.45 | 1051.73 | 229.28 | -151.02 | 937.46 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24290586400 |  | 100460606 |  | 6680224G |  |  |  | 566 | EX | ABANDON SL - SOII/OUTSIDE | 2621P | HIGHVIEW | 1648 HIGHVIEW CR | 073 | FRA | 2024-12-27 | BWHITE | U127297 | 2024-10-15 | 2024-12-31 | 2024-12-31 |  | BWHITE | 2024-12-27 | 2024-11-14 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 49.5333 | 13 | 6448.49 | 3769.83 | 0 | 562.91 | 2115.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290603100 |  | 501312438 |  | 67122204J | 2179617 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | LONGRIDGE | 117 LONGRIDGE DR | 113 | NIC | 2024-10-28 | U461516 | U126856 | 2024-10-15 | 2024-10-17 | 2024-10-30 |  | NEAL JOHNSON | 2024-10-28 |  | 2024-10-28 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 3.5833 | 1 | 2418.9 | 216.13 | 304.84 | 13.26 | 1884.67 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290608100 |  | 500521133 |  | 6728204K |  |  |  | 563 | EX | 1' P LONG/PRMT RCVD | 2600B | CUTTERS HILL | 350 CUTTERS HILL CT | 067 | LEX | 2024-11-09 | U128336 | U133050 | 2024-10-15 | 2024-10-29 | 2024-11-11 |  | JOSHUA COX | 2024-11-08 | 2024-11-08 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 5.1 | 1 | 5203.84 | 419.14 | 311.23 | 25.22 | 4448.25 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24290823900 |  | 100273882 |  | 6680228H |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D513657 | 2621P | MOSS | 713 MOSS LN | 073 | FRA | 2024-12-12 | U137585 | U124604 | 2024-10-16 | 2025-04-15 | 2026-10-31 |  | KKINDER | 2024-12-11 | 2024-12-11 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 22.4667 | 3 | 1641.81 | 1498.06 | 0 | 87.51 | 56.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290826700 |  | 100326784 |  | 6720208I |  |  |  | 565 | EX | *RUSH* INSTALL 2"PMLP S/L | 2621P | HAMPSHIRE | 1404 HAMPSHIRE PL | 067 | LEX | 2024-10-22 | KKINDER | U461383 | 2024-10-16 | 2024-10-25 | 2024-10-25 |  | KKINDER | 2024-10-22 | 2024-10-21 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 29.2833 | 4 | 2666.48 | 1548.22 | 866.51 | 94.87 | 156.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290861800 |  | 100323264 |  | 6716208P |  |  |  | 565 | EX | SERVICE LINE UPGRADE -CUST REQ | 2621P | ROBIN | 856 ROBIN RD | 067 | LEX | 2024-10-31 | RSTRONG | U124604 | 2024-10-16 | 2024-11-27 |  |  | RSTRONG | 2024-10-31 | 2024-10-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 42.8 | 9 | 1093.84 | 91.05 | 997.21 | 5.58 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24290895200 |  | 500761249 |  | 6712232K | 0144367 |  |  | 563 | EX | 20 1" P SHORT/NO PRMT REQ | 2600B | CARRIAGE | 163 CARRIAGE LN | 209 | GEO | 2024-11-06 | U126532 | U132805 | 2024-10-16 | 2024-10-17 | 2024-11-06 |  | LESLIE SHARON | 2024-11-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 10 | 1 | 4287.51 | 728.39 | 400.99 | 338.23 | 2819.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290908800 |  | 500935514 |  | 6724208G | 0567341 |  |  | 565 | EX | SERVICE LINE RELO /CUST REQ | 2621P | PLAUDIT | 1872 PLAUDIT PL | 067 | LEX | 2024-10-29 | HMCKUNE | U124604 | 2024-10-16 | 2024-11-15 |  |  | HMCKUNE | 2024-10-29 | 2024-10-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 99.6 | 11 | 16068.51 | 6082.28 | 200.83 | 1110.52 | 8674.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24290914400 |  | 100457817 |  | 6712228J | 2407982 |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | LEXINGTON | 1131 LEXINGTON RD | 209 | GEO | 2024-10-24 | DCOLLIN | U124604 | 2024-10-16 | 2024-10-23 |  |  | DCOLLIN | 2024-10-24 | 2024-10-23 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26230031 | 30.4833 | 5 | 5034.29 | 1937.3 | 108.85 | -164.62 | 3152.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290953000 |  | 501055085 |  | 6728212M | 2407268 |  |  | 563 | EX | 1"P LONG/PRMT RCVD | 2600B | BOBWHITE | 3016 BOBWHITE TR LT12 | 067 | LEX | 2024-11-19 | U123111 | U128266 | 2024-10-16 | 2024-10-29 | 2024-11-11 |  | LYN STAFFORD | 2024-11-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8.5 | 1 | 2897.37 | 633.97 | 317.61 | 38.17 | 1907.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24290964600 |  | 100301307 |  | 6712212H | 1635077 |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2621D | DUNKIRK | 1946 DUNKIRK CT | 067 | LEX | 2025-02-14 | U137585 | AOC SYST | 2024-10-16 | 2025-12-31 | 2025-12-31 |  | JOCHOA | 2025-02-13 | 2024-11-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 26.3333 | 6 | 1875.88 | 1790 | 0 | 85.88 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291112300 |  | 100301113 |  | 6716212E |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D513531 | 2621P | SAVOY | 217 SAVOY RD | 067 | LEX | 2024-12-06 | U137585 | U124604 | 2024-10-17 | 2025-04-16 | 2026-10-31 |  | MCRAIG | 2024-12-05 | 2024-12-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.1 | 2 | 1777.41 | 1114.54 | 0 | 662.87 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291126200 |  | 501332946 |  | 6716232I | 2180856 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | LIMESTONE | 140 LIMESTONE LN | 209 | GEO | 2024-10-30 | U126532 | U130192 | 2024-10-17 | 2024-10-22 | 2024-11-04 |  | LESLIE SHARON | 2024-10-30 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 6.2667 | 1 | 3959.44 | 408.79 | 290.68 | 25.05 | 3234.92 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291126600 |  | 501332973 |  | 6716232I | 2180856 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | OXFORD LANDING | 107 OXFORD LANDING DR | 209 | GEO | 2024-10-30 | U126532 | U130192 | 2024-10-17 | 2024-10-22 | 2024-11-04 |  | LESLIE SHARON | 2024-10-30 | 2024-10-30 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 3.7333 | 1 | 1624.48 | 242.19 | 287.04 | 14.84 | 1080.41 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291142900 |  | 100303961 |  | 6712208C |  |  |  | 565 | EX | REPAIR/REPLACE SERVICE LINE | 2621P | WINTERBERRY | 2104 WINTERBERRY DR | 067 | LEX | 2024-10-18 | U141668 | U139677 | 2024-10-17 | 2024-10-17 | 2024-10-17 |  | MCRAIG | 2024-10-17 | 2024-10-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.8167 | 2 | 902.77 | 623.59 | 379.66 | -100.48 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24291150800 |  | 100260083 |  | 7356256A | 2075304 |  |  | 565 | EX | RPLC SL/20026983300 | 2600B | HILTON | 1801 HILTON AV | 019 | ASH | 2024-10-18 | U128523 | U125763 | 2024-10-17 | 2024-12-31 |  |  | BRANDON ROBERTS | 2024-10-17 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 2.6167 | 1 | 3589.15 | 148.02 | 0 | 127.82 | 3313.31 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24291158700 |  | 100421639 |  | 6736248A | 1855582 |  |  | 565 | EX | RPLC SL/18026795500 | 2600B | OLD LAIR | 107 OLD LAIR RD | 097 | CYN | 2024-10-17 | U126284 | U125763 | 2024-10-17 | 2024-12-31 |  |  | MILLER PIPELINE | 2024-10-17 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2762.37 | 0 | 0 | 0 | 2762.37 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24291176700 |  | 100265370 |  | 7348260P | 2405531 |  |  | 565 | EX | REPLACE SL/24026341000 | 2621P | CRANCE | 3119 CRANCE CT | 019 | ASH | 2025-06-19 | ABHATFIE | U123688 | 2024-10-17 | 2024-12-31 |  |  | ABHATFIE | 2025-06-19 | 2025-03-28 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 26.4167 | 3 | 3662.99 | 2008.29 | 0 | 117.69 | 1537.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291183000 |  | 100307675 |  | 6716212K |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | MERINO | 341 MERINO ST 1F | 067 | LEX | 2024-10-18 | U141668 | U134115 | 2024-10-17 | 2024-10-17 |  |  | ATWILLI | 2024-10-17 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.25 | 3 | 7098.63 | 1803.16 | 385.01 | 542.17 | 4368.29 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24291186700 |  | 100269197 |  | 6736252M |  |  |  | 563 | EX | 1" P SHORT | 2621P | CHURCH | 240 N CHURCH ST | 097 | CYN | 2024-10-28 | U124604 | U128272 | 2024-10-17 | 2024-10-31 | 2024-10-31 |  | NRICHIE | 2024-10-25 | 2024-10-24 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 15 | 4 | 2741.08 | 949.01 | 509.95 | 399.3 | 882.82 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24291188400 |  | 100267259 |  | 7352260E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D359731 | 2621P | AMHERST | 1150 AMHERST DR | 089 | ASH | 2025-06-18 | ABHATFIE | U123688 | 2024-10-17 | 2025-04-16 | 2026-10-31 |  | ABHATFIE | 2025-06-18 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 13.2333 | 2 | 1034.66 | 954.96 | 0 | 56.02 | 23.68 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291406800 |  | 100458158 |  | 6700212E |  |  |  | 563 | EX | 1" P LONG/PRMT RCVD | 2600B | FIELDING | 304 FIELDING RD | 239 | VER | 2024-11-07 | U123111 | U128272 | 2024-10-18 | 2024-10-25 | 2024-11-07 |  | LYN STAFFORD | 2024-11-07 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8.5 | 1 | 2798.65 | 633.97 | 433.76 | 38.17 | 1692.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291409600 |  | 100293559 |  | 6720216N |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HOLLOW CREEK | 440 HOLLOW CREEK RD | 067 | LEX | 2025-01-28 | TROE | U124604 | 2024-10-18 | 2024-12-31 |  |  | TROE | 2025-01-28 | 2024-11-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 162.45 | 23 | 27906.8 | 9748.13 | 827.32 | 809.07 | 16522.28 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291416800 |  | 100290261 |  | 6720212C |  |  |  | 566 | EX | ABANDON SL CUST REQ | 2621P | HIGHLAWN | 1451 HIGHLAWN AV | 067 | LEX | 2024-11-15 | MCRAIG | U140273 | 2024-10-18 | 2024-11-07 | 2024-12-02 |  | MCRAIG | 2024-11-15 | 2024-11-12 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 27.0333 | 7 | 2334.49 | 1756.48 | 39.78 | 538.23 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291430500 |  | 100303981 |  | 6712208C |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D513562 | 2621P | JASMINE | 2176 JASMINE DR | 067 | LEX | 2024-10-24 | U124604 | U124604 | 2024-10-18 | 2024-10-18 | 2024-11-07 |  | ATWILLI | 2024-10-23 | 2024-10-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.8 | 3 | 1744.36 | 1275.71 | 25.13 | 443.52 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291431300 |  | 100304008 |  | 6712208D |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D513563 | 2621P | JASMINE | 2139 JASMINE DR | 067 | LEX | 2025-01-15 | U124604 | U124604 | 2024-10-18 | 2025-04-17 | 2026-10-31 |  | CHEMMER | 2025-01-14 | 2025-01-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.3833 | 4 | 1899.4 | 1288.97 | 410.19 | 84.8 | 115.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291431600 |  | 100303950 |  | 6712208C |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D513564 | 2621P | WINTERBERRY | 2144 WINTERBERRY DR | 067 | LEX | 2025-02-14 | U124604 | U124604 | 2024-10-18 | 2025-04-17 | 2026-10-31 |  | DJOHNSON | 2025-02-13 | 2025-01-24 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.7 | 5 | 2302.32 | 1601.52 | 415.56 | 285.24 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291431800 |  | 100304032 |  | 6712208C |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D513566 | 2621P | JASMINE | 2205 JASMINE DR | 067 | LEX | 2025-01-14 | U124604 | U124604 | 2024-10-18 | 2025-04-17 | 2026-10-31 |  | JOCHOA | 2025-01-13 | 2025-01-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 26.5 | 5 | 1981.59 | 1449.94 | 382.98 | 95.39 | 53.28 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291441400 |  | 100337154 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL CUST REQ | 2621P | 5TH | 209 E 5TH ST | 067 | LEX | 2024-11-18 | LSTANFI | U140273 | 2024-10-18 | 2024-11-07 | 2024-12-02 |  | LSTANFI | 2024-11-18 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 22.95 | 3 | 2332.74 | 1435.13 | 0 | 317.61 | 580 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291447100 |  | 100279440 |  | 6692224E |  |  |  | 566 | EX | ABANDON SL/DEMO CUST REQ | 2621P | OLD VERSAILLES | 25 OLD VERSAILLES RD | 073 | FRA | 2024-11-13 | EFGOINS | U140273 | 2024-10-18 | 2024-11-07 | 2024-12-02 |  | EFGOINS | 2024-11-13 | 2024-11-13 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 12.4833 | 2 | 1151.63 | 911.48 | 28.69 | 211.46 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291469600 |  | 100279439 |  | 6692224E |  |  |  | 566 | EX | ABANDON SL/DEMO CUST REQ | 2621P | OLD VERSAILLES | 35 OLD VERSAILLES RD | 073 | FRA | 2024-11-13 | ATWILLI | U140273 | 2024-10-18 | 2024-11-07 | 2024-12-02 |  | ATWILLI | 2024-11-13 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 2.6833 | 1 | 331.72 | 200.94 | 39.78 | 91 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291469700 |  | 100281365 |  | 6712228B | 2403101 |  |  | 565 | EX | RPLC SL/24026313000 | 2600B | BROADWAY | 221 N BROADWAY ST | 209 | GEO | 2024-12-05 | U461443 | U125763 | 2024-10-18 | 2024-12-31 |  |  | WILLIAM GRAVES | 2024-12-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3407.25 | 0 | 0 | 0 | 3407.25 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291469800 |  | 100281402 |  | 6712232N | 2403101 |  |  | 565 | EX | RPLC SL/24026313000 | 2600B | BROADWAY | 301 N BROADWAY ST | 209 | GEO | 2024-11-26 | U128816 | U125763 | 2024-10-18 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-11-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2418.43 | 0 | 0 | 0 | 2418.43 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291469900 |  | 100281373 |  | 6712228B | 2403101 |  |  | 565 | EX | RPLC SL/24026313000 | 2600B | CHURCH | 116 CHURCH ST | 209 | GEO | 2024-11-25 | U128816 | U125763 | 2024-10-18 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-11-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2327.63 | 0 | 0 | 0 | 2327.63 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291470000 |  | 100281372 |  | 6712228B | 2403101 |  |  | 565 | EX | RPLC SL/24026313000 | 2600B | CHURCH | 118 CHURCH ST | 209 | GEO | 2024-11-25 | U128816 | U125763 | 2024-10-18 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-11-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2193.26 | 0 | 0 | 0 | 2193.26 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291470100 |  | 100281371 |  | 6712228B | 2403101 |  |  | 565 | EX | RPLC SL/24026313000 | 2600B | CHURCH | 120 CHURCH ST | 209 | GEO | 2024-11-25 | U128816 | U125763 | 2024-10-18 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-11-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2119.96 | 0 | 0 | 0 | 2119.96 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291470300 |  | 100281400 |  | 6712232N | 2403101 |  |  | 565 | EX | RPLC SL/24026313000 | 2600B | JEFFERSON | 117 W JEFFERSON ST | 209 | GEO | 2024-11-22 | U461443 | U125763 | 2024-10-18 | 2024-12-31 |  |  | WILLIAM GRAVES | 2024-11-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2117.73 | 0 | 0 | 0 | 2117.73 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291470400 |  | 100281397 |  | 6712232N | 2403101 |  |  | 565 | EX | RPLC SL/24026313000 | 2600B | JEFFERSON | 123 W JEFFERSON ST | 209 | GEO | 2024-11-26 | U128816 | U125763 | 2024-10-18 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-11-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2381.56 | 0 | 0 | 0 | 2381.56 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291470500 |  | 100281369 |  | 6712232N | 2403101 |  |  | 565 | EX | RPLC SL/24026313000 | 2600B | JEFFERSON | 124 W JEFFERSON ST | 209 | GEO | 2024-12-05 | U461443 | U125763 | 2024-10-18 | 2024-12-31 |  |  | WILLIAM GRAVES | 2024-12-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3313.61 | 0 | 0 | 0 | 3313.61 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291470600 |  | 100281370 |  | 6712232N | 2403101 |  |  | 565 | EX | RPLC SL/24026313000 | 2600B | JEFFERSON | 209 W JEFFERSON ST | 209 | GEO | 2024-12-09 | U123111 | U125763 | 2024-10-18 | 2024-12-31 |  |  | LYN STAFFORD | 2024-12-07 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7 | 1 | 6575.97 | 562.65 | 0 | 32.86 | 5980.46 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291470800 |  | 100281392 |  | 6712232N | 2403101 |  |  | 565 | EX | RPLC SL/24026313000 | 2600B | WATER | 310 N WATER ST | 209 | GEO | 2024-12-03 | U461443 | U125763 | 2024-10-18 | 2024-12-31 |  |  | WILLIAM GRAVES | 2024-12-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3073.29 | 0 | 0 | 0 | 3073.29 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291470900 |  | 100281381 |  | 6712232N | 2403101 |  |  | 565 | EX | RPLC SL/24026313000 | 2600B | WATER | 311 N WATER ST | 209 | GEO | 2024-12-04 | U461443 | U125763 | 2024-10-18 | 2024-12-31 |  |  | WILLIAM GRAVES | 2024-12-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2971.42 | 0 | 0 | 0 | 2971.42 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291471000 |  | 100281383 |  | 6712232N | 2403101 |  |  | 565 | EX | RPLC SL/24026313000 | 2600B | WATER | 313 N WATER ST | 209 | GEO | 2024-11-27 | U128816 | U125763 | 2024-10-18 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-11-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3083.29 | 0 | 0 | 0 | 3083.29 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291471100 |  | 100281384 |  | 6712232N | 2403101 |  |  | 565 | EX | RPLC SL/24026313000 | 2600B | WATER | 315 N WATER ST | 209 | GEO | 2024-11-27 | U128816 | U125763 | 2024-10-18 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-11-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2415.93 | 0 | 0 | 0 | 2415.93 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291471200 |  | 100281389 |  | 6712232N | 2403101 |  |  | 565 | EX | RPLC SL/24026313000 | 2600B | WATER | 316 N WATER ST | 209 | GEO | 2024-12-03 | U461443 | U125763 | 2024-10-18 | 2024-12-31 |  |  | WILLIAM GRAVES | 2024-12-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3068.29 | 0 | 0 | 0 | 3068.29 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291471300 |  | 100281385 |  | 6712232N | 2403101 |  |  | 565 | EX | RPLC SL/24026313000 | 2600B | WATER | 317 N WATER ST | 209 | GEO | 2024-12-02 | U461443 | U125763 | 2024-10-18 | 2024-12-31 |  |  | WILLIAM GRAVES | 2024-12-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3093.29 | 0 | 0 | 0 | 3093.29 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291471400 |  | 100281386 |  | 6712232N | 2403101 |  |  | 565 | EX | RPLC SL/24026313000 | 2600B | WATER | 319 N WATER ST | 209 | GEO | 2024-12-02 | U461443 | U125763 | 2024-10-18 | 2024-12-31 |  |  | WILLIAM GRAVESQ | 2024-12-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3065.79 | 0 | 0 | 0 | 3065.79 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291471500 |  | 500493602 |  | 6712232N | 2403101 |  |  | 565 | EX | RPLC SL/24026313000 | 2600B | WHITE PINE | 305 WHITE PINE LN | 209 | GEO | 2024-12-04 | U461443 | U125763 | 2024-10-18 | 2024-12-31 |  |  | WILLIAM GRAVES | 2024-12-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2733.05 | 0 | 0 | 0 | 2733.05 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291475100 |  | 100279441 |  | 6688224D |  |  |  | 566 | EX | ABANDON SL/DEMO CUST REQ | 2621P | VERSAILLES | 1625 VERSAILLES RD | 073 | FRA | 2024-11-22 | EFGOINS | U140273 | 2024-10-18 | 2024-11-07 | 2024-12-02 |  | EFGOINS | 2024-11-22 | 2024-11-14 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 16.2 | 3 | 5705.57 | 1194.39 | 0 | 166.68 | 4344.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291477800 |  | 501356947 |  | 6712204E | 2397231 |  |  | 563 | EX | 1" P LONG HMS ANDERSON TATE | 2600B | BELLERIVE | 804 BELLERIVE BV LT29 | 113 | NIC | 2024-11-07 | U123111 | U134341 | 2024-10-18 | 2024-10-23 | 2024-11-12 |  | LYN STAFFORD | 2024-11-06 | 2024-11-05 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 16 | 2 | 6284.72 | 1193.38 | 312.11 | 71.84 | 4707.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291477900 |  | 100289886 |  | 6720212D | 2409175 |  |  | 565 | EX | RPLC SL/24026363600 | 2600B | EASTIN | 306 EASTIN RD | 067 | LEX | 2024-11-14 | U126602 | U125763 | 2024-10-18 | 2024-12-31 |  |  | DEREK PAYTON | 2024-11-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3791.83 | 0 | 239.9 | 0 | 3551.93 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291478000 |  | 500928526 |  | 6720212D | 2409175 |  |  | 565 | EX | RPLC SL/24026363600 | 2600B | EASTIN | 312 EASTIN RD | 067 | LEX | 2024-11-12 | U128336 | U125763 | 2024-10-18 | 2024-12-31 |  |  | JOSHUA COX | 2024-11-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2783.04 | 0 | 0 | 0 | 2783.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291478200 |  | 100289839 |  | 6720212D | 2409175 |  |  | 565 | EX | RPLC SL/24026363600 | 2600B | EASTIN | 319 EASTIN RD | 067 | LEX | 2024-11-14 | U126602 | U125763 | 2024-10-18 | 2024-12-31 |  |  | DEREK PAYTON | 2024-11-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 3987.01 | 660.68 | 0 | 138.77 | 3187.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291478300 |  | 100289838 |  | 6720212D | 2409175 |  |  | 565 | EX | RPLC SL/24026363600 | 2600B | EASTIN | 323 EASTIN RD | 067 | LEX | 2024-11-13 | U128336 | U125763 | 2024-10-18 | 2024-12-31 |  |  | JOSHUA COX | 2024-11-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2196.29 | 0 | 398.25 | 0 | 1798.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291478400 |  | 100289888 |  | 6720212D | 2409175 |  |  | 565 | EX | RPLC SL/24026363600 | 2600B | EASTIN | 324 EASTIN RD | 067 | LEX | 2024-11-12 | U128336 | U125763 | 2024-10-18 | 2024-12-31 |  |  | JOSHUA COX | 2024-11-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2714.72 | 0 | 0 | 0 | 2714.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291478500 |  | 100289889 |  | 6720212D | 2409175 |  |  | 565 | EX | RPLC SL/24026363600 | 2600B | EASTIN | 330 EASTIN RD | 067 | LEX | 2024-11-14 | U128336 | U125763 | 2024-10-18 | 2024-12-31 |  |  | JOSHUA COX | 2024-11-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3097.35 | 0 | 392.75 | 0 | 2704.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291478600 |  | 100289836 |  | 6720212D | 2409175 |  |  | 565 | EX | RPLC SL/24026363600 | 2600B | EASTIN | 331 EASTIN RD | 067 | LEX | 2024-11-11 | U128336 | U125763 | 2024-10-18 | 2024-12-31 |  |  | JOSHUA COX | 2024-11-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2391.69 | 0 | 0 | 0 | 2391.69 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291479100 |  | 100289837 |  | 6720212D | 2409175 |  |  | 565 | EX | RPLC SL/24026363600 | 2600B | EASTIN | 327 EASTIN RD | 067 | LEX | 2024-11-13 | U128336 | U125763 | 2024-10-18 | 2024-12-31 |  |  | JOSHUA COX | 2024-11-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2875.56 | 0 | 398.25 | 0 | 2477.31 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24291491100 |  | 100286454 |  | 6768172B | 2409128 |  |  | 563 | EX | 2" P SHORT | 2621P | DANIELS ADDITI | 409 DANIELS ADDITI | 065 | RAV | 2024-10-31 | U124604 | U132805 | 2024-10-18 | 2024-10-21 | 2024-11-01 |  | DENNING | 2024-10-30 | 2024-10-25 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 17.9667 | 4 | 2430.38 | 1190.73 | 1127.03 | 62.3 | 50.32 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291663400 |  | 501317389 |  | 6716236J | 2178365 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | FLAMINGO | 109 FLAMINGO CR | 209 | GEO | 2024-10-30 | U123111 | U126856 | 2024-10-21 | 2024-10-22 | 2024-11-04 |  | LYN STAFFORD | 2024-10-30 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 2393.08 | 495.48 | 311.24 | 30.37 | 1555.99 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291670100 |  | 500510156 |  | 6716232N | 9616288 |  |  | 566 | EX | ABANDON SL CUST REQ | 2621P | WILDERNESS COV | 112 WILDERNESS COV LN | 209 | GEO | 2024-11-25 | DCOLLIN | U140273 | 2024-10-21 | 2024-11-08 | 2024-12-03 |  | DCOLLIN | 2024-11-25 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 16 | 2 | 3371.9 | 1247.74 | 0 | 218.16 | 1906 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291671400 |  | 100337462 |  | 6720212J | 2409413 |  |  | 563 | EX | 1" P SHORT/PRMT RCVD | 2600B | PEMBERTON | 548 PEMBERTON ST | 067 | LEX | 2024-11-19 | U461516 | U129531 | 2024-10-21 | 2024-11-05 | 2024-11-18 |  | NEAL JOHNSON | 2024-11-19 | 2024-11-18 | 2024-11-18 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 20.2167 | 3 | 7422.02 | 1454.51 | 651.1 | 558.54 | 4757.87 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291678500 |  | 500050835 |  | 6684224M |  |  |  | 565 | EX | REPLACE SERVIC LINE | 2621P | US 127 | 2311 US 127 SO | 073 | FRA | 2024-10-28 | EFGOINS | U124604 | 2024-10-21 | 2024-11-15 |  |  | EFGOINS | 2024-10-28 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 16 | 2 | 1786.41 | 941.75 | 291.16 | 57.7 | 495.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291691200 |  | 500744653 |  | 6724208B |  |  |  | 563 | EX | 1" P SHORT/PERMIT RCVD | 2600B | FLYING EBONY | 2418 FLYING EBONY DR | 067 | LEX | 2024-10-29 | U461516 | U127708 | 2024-10-21 | 2024-10-24 | 2024-11-06 |  | NEAL JOHNSON | 2024-10-29 |  | 2024-10-29 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4.3167 | 1 | 2630.55 | 258.12 | 300.06 | 212.21 | 1860.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291691500 |  | 500919791 |  | 6724208B | 0465046 |  |  | 563 | EX | MANIFOLD W/500744653 | 2600B | FLYING EBONY | 2420 FLYING EBONY DR | 067 | LEX | 2024-10-29 | U461516 | U127708 | 2024-10-21 | 2024-10-24 | 2024-11-06 |  | NEAL JOHNSON | 2024-10-29 |  | 2024-10-29 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBMAN |  | 100 | 056332B26210012 | 3.6833 | 1 | 866.51 | 222.13 | 145.58 | 182.6 | 316.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291693300 |  | 501372866 |  | 6712208M |  |  |  | 563 | EX | 2"P LONG(TAP ON COCOS WAY)RCVD | 2600B | HARRODSBURG | 4257 HARRODSBURG RD 110 | 067 | LEX | 2024-11-19 | U128336 | U126856 | 2024-10-21 | 2024-11-05 | 2024-11-18 |  | JOSHUA COX | 2024-11-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 3794.52 | 0 | 871.65 | 0 | 2922.87 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24291701800 |  | 100254824 |  | 7348260G |  |  |  | 565 | EX | GRADE 1 REPLACE S/L | 2621P | RADFORD | 1075 RADFORD DR | 089 | RUS | 2024-10-23 | U124604 | U129939 | 2024-10-21 | 2024-10-21 | 2024-10-21 |  | LAMAY | 2024-10-22 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 15.3833 | 4 | 1074.59 | 932.37 | 0 | 41.58 | 100.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291712500 |  | 100304830 |  | 6716212M |  |  |  | 565 | EX | GRADE 1 | 2621P | CELIA | 913 CELIA LN | 067 | LEX | 2024-11-14 | U123688 | U137585 | 2024-10-21 | 2024-10-21 | 2024-10-21 |  | RJCRAWF | 2024-10-21 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.8 | 2 | 1532.63 | 1052.57 | 415.59 | 64.47 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291714800 |  | 100329599 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2000 SAINT CHRISTOP DR | 067 | LEX | 2024-12-20 | U461322 | U125763 | 2024-10-21 | 2024-12-31 |  |  | STEVE CANOY | 2024-12-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2964.12 | 0 | 0 | 0 | 2964.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291714900 |  | 100329658 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2001 SAINT CHRISTOP DR | 067 | LEX | 2025-01-29 | U461322 | U125763 | 2024-10-21 | 2024-12-31 |  |  | STEVE CANOY | 2025-01-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.05 | 1 | 5823.39 | 1553.71 | 0 | 250.51 | 4019.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291715100 |  | 100329656 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2009 SAINT CHRISTOP DR | 067 | LEX | 2025-01-17 | U461322 | U125763 | 2024-10-21 | 2024-12-31 |  |  | STEVE CANOY | 2025-01-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.7333 | 1 | 3994.42 | 241.39 | 0 | 15.9 | 3737.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291715200 |  | 100329602 |  | 6720208C | 2403558 |  |  | 565 | EX | REPLACE SL/24026316700 | 2600B | SAINT CHRISTOP | 2012 SAINT CHRISTOP DR | 067 | LEX | 2024-12-17 | U461322 | U125763 | 2024-10-21 | 2024-12-31 |  |  | STEVE CANOY | 2024-12-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.0833 | 1 | 2744.56 | 178.85 | 0 | 180.48 | 2385.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291715300 |  | 100329655 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2013 SAINT CHRISTOP DR | 067 | LEX | 2025-01-28 | U128762 | U125763 | 2024-10-21 | 2024-01-19 |  |  | RANDALL TINCHER | 2025-01-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 6078.3 | 2263.31 | 0 | 468.87 | 3346.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291715400 |  | 100329603 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2016 SAINT CHRISTOP DR | 067 | LEX | 2024-12-09 | U461322 | U125763 | 2024-10-21 | 2024-12-31 |  |  | STEVE CANOY | 2024-12-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.1833 | 1 | 3657.17 | 358.51 | 0 | 361.76 | 2936.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291715600 |  | 100329654 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2017 SAINT CHRISTOP DR | 067 | LEX | 2024-12-19 | U461322 | U125763 | 2024-10-21 | 2024-12-31 |  |  | STEVE CANOY | 2024-12-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.35 | 1 | 3515.52 | 375.76 | 0 | 379.22 | 2760.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291715700 |  | 100329604 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2020 SAINT CHRISTOP DR | 067 | LEX | 2025-01-29 | U461322 | U125763 | 2024-10-21 | 2024-12-31 |  |  | STEVE CANOY | 2025-01-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.2 | 1 | 3423.93 | 334.71 | 0 | 22.02 | 3067.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291715900 |  | 100329652 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2025 SAINT CHRISTOP DR | 067 | LEX | 2024-12-12 | U461322 | U125763 | 2024-10-21 | 2024-12-31 |  |  | STEVE CANOY | 2024-12-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.7333 | 1 | 3045.89 | 496.72 | 0 | 29.01 | 2520.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291716000 |  | 100329606 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2028 SAINT CHRISTOP DR | 067 | LEX | 2024-12-11 | U461322 | U125763 | 2024-10-21 | 2024-12-31 |  |  | STEVE CANOY | 2024-12-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2183.82 | 0 | 0 | 0 | 2183.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291716100 |  | 100329651 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2029 SAINT CHRISTOP DR | 067 | LEX | 2025-01-31 | U461322 | U125763 | 2024-10-21 | 2024-12-31 |  |  | STEVE CANOY | 2025-01-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.2333 | 1 | 2915.78 | 79.19 | 0 | 5.21 | 2831.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291716200 |  | 100329607 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2032 SAINT CHRISTOP DR | 067 | LEX | 2025-01-28 | U461322 | U125763 | 2024-10-21 | 2024-12-31 |  |  | STEVE CANOY | 2025-01-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.2167 | 1 | 3066.07 | 77.25 | 0 | 5.09 | 2983.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291716300 |  | 100329650 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2033 SAINT CHRISTOP DR | 067 | LEX | 2025-01-27 | U128762 | U125763 | 2024-10-21 | 2024-12-31 |  |  | RANDALL TINCHER | 2025-01-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2473.85 | 0 | 0 | 0 | 2473.85 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291716400 |  | 100329608 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2036 SAINT CHRISTOP DR | 067 | LEX | 2024-12-10 | U461322 | U125763 | 2024-10-21 | 2024-12-31 |  |  | STEVE CANOY | 2024-12-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.6167 | 1 | 3049.07 | 397.37 | 0 | 23.22 | 2628.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291716500 |  | 100329649 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2037 SAINT CHRISTOP DR | 067 | LEX | 2025-01-27 | U461322 | U125763 | 2024-10-21 | 2024-12-31 |  |  | STEVE CANOY | 2025-01-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.8 | 1 | 3610.74 | 246.57 | 0 | 16.21 | 3347.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291716600 |  | 100329609 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2040 SAINT CHRISTOP DR | 067 | LEX | 2024-12-10 | U461322 | U125763 | 2024-10-21 | 2024-12-31 |  |  | STEVE CANOY | 2024-12-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.8167 | 1 | 2439.84 | 241.9 | 0 | 14.12 | 2183.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291716700 |  | 100329648 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2041 SAINT CHRISTOP DR | 067 | LEX | 2025-02-04 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-02-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2176.01 | 0 | 0 | 0 | 2176.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291716900 |  | 100329610 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2044 SAINT CHRISTOP DR | 067 | LEX | 2024-12-11 | U126284 | U125763 | 2024-10-21 | 2024-12-31 |  |  | JOSH PASLEY | 2024-12-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.95 | 1 | 2715.69 | 521.25 | 0 | 30.43 | 2164.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291717000 |  | 100329647 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2045 SAINT CHRISTOP DR | 067 | LEX | 2024-12-11 | U461322 | U125763 | 2024-10-21 | 2024-12-31 |  |  | STEVE CANOY | 2024-12-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.8833 | 1 | 3123.54 | 679.01 | 0 | 39.67 | 2404.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291717100 |  | 100329611 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2048 SAINT CHRISTOP DR | 067 | LEX | 2024-12-11 | U128762 | U125763 | 2024-10-21 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-12-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2405.05 | 0 | 0 | 0 | 2405.05 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291717200 |  | 100329646 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2049 SAINT CHRISTOP DR | 067 | LEX | 2024-12-16 | U128762 | U125763 | 2024-10-21 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-12-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2859.5 | 0 | 0 | 0 | 2859.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291717300 |  | 100329612 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2052 SAINT CHRISTOP DR | 067 | LEX | 2024-12-10 | U126284 | U125763 | 2024-10-21 | 2024-12-31 |  |  | JOSH PASLEY | 2024-12-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.05 | 1 | 2654.94 | 442.43 | 0 | 25.86 | 2186.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291717400 |  | 100329645 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2053 SAINT CHRISTOP DR | 067 | LEX | 2024-12-11 | U126284 | U125763 | 2024-10-21 | 2024-12-31 |  |  | JOSH PASLEY | 2024-12-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.05 | 1 | 3987.14 | 442.4 | 0 | 25.83 | 3518.91 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291717500 |  | 100329613 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2056 SAINT CHRISTOP DR | 067 | LEX | 2024-12-05 | U128762 | U125763 | 2024-10-21 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-12-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2252.97 | 0 | 0 | 0 | 2252.97 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291717700 |  | 100329614 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2060 SAINT CHRISTOP DR | 067 | LEX | 2024-12-03 | U461322 | U125763 | 2024-10-21 | 2024-12-31 |  |  | STEVE CANOY | 2024-12-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.93333 | 1 | 2353.28 | 82.95 | 0 | 83.68 | 2186.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291717800 |  | 100329643 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2061 SAINT CHRISTOP DR | 067 | LEX | 2024-12-10 | U126284 | U125763 | 2024-10-21 | 2024-12-31 |  |  | JOSH PASLEY | 2024-12-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.45 | 1 | 2996.08 | 477.48 | 0 | 27.9 | 2490.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291718000 |  | 100329642 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2065 SAINT CHRISTOP DR | 067 | LEX | 2024-12-09 | U128762 | U125763 | 2024-10-21 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-12-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4111.54 | 0 | 0 | 0 | 4111.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291718100 |  | 100329616 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2068 SAINT CHRISTOP DR | 067 | LEX | 2024-12-02 | U461322 | U125763 | 2024-10-21 | 2024-12-31 |  |  | STEVE CANOY | 2024-12-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.71667 | 1 | 2635.43 | 61.35 | 0 | 61.89 | 2512.19 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291718200 |  | 100329641 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2069 SAINT CHRISTOP DR | 067 | LEX | 2024-12-13 | U128762 | U125763 | 2024-10-21 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-12-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2334.97 | 0 | 0 | 0 | 2334.97 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291718300 |  | 100329617 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2072 SAINT CHRISTOP DR | 067 | LEX | 2024-12-04 | U128762 | U125763 | 2024-10-21 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-12-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2281.7 | 0 | 0 | 0 | 2281.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291718400 |  | 100329640 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2073 SAINT CHRISTOP DR | 067 | LEX | 2024-12-19 | U128762 | U125763 | 2024-10-21 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-12-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3372.29 | 0 | 0 | 0 | 3372.29 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291718500 |  | 100329618 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2076 SAINT CHRISTOP DR | 067 | LEX | 2025-01-17 | U126308 | U125763 | 2024-10-21 | 2024-12-31 |  |  | JAMIE ENSMINGER | 2025-01-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2419.85 | 509.39 | 0 | 33.51 | 1876.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291718600 |  | 100329639 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2077 SAINT CHRISTOP DR | 067 | LEX | 2024-12-17 | U126284 | U125763 | 2024-10-21 | 2024-12-31 |  |  | JOSH PASLEY | 2024-12-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.6 | 1 | 6829.59 | 841.01 | 0 | 49.12 | 5939.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291718700 |  | 100329638 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2081 SAINT CHRISTOP DR | 067 | LEX | 2025-02-07 | U126604 | U125763 | 2024-10-21 | 2024-12-31 |  |  | WILLIAM FULKS | 2025-02-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4050.94 | 0 | 0 | 0 | 4050.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291718800 |  | 100329637 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2085 SAINT CHRISTOP DR | 067 | LEX | 2025-01-29 | U461322 | U125763 | 2024-10-21 | 2024-12-31 |  |  | STEVE CANOY | 2025-01-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.43333 | 1 | 3030.3 | 28.93 | 0 | 1.89 | 2999.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291718900 |  | 100329621 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2088 SAINT CHRISTOP DR | 067 | LEX | 2024-12-13 | U128762 | U125763 | 2024-10-21 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-12-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2175.33 | 0 | 0 | 0 | 2175.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291719000 |  | 100329636 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2089 SAINT CHRISTOP DR | 067 | LEX | 2025-01-28 | U461322 | U125763 | 2024-10-21 | 2024-12-31 |  |  | STEVE CANOY | 2025-01-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.7167 | 1 | 4861.84 | 370.13 | 0 | 24.35 | 4467.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291719200 |  | 100329635 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2093 SAINT CHRISTOP DR | 067 | LEX | 2025-01-30 | U461322 | U125763 | 2024-10-21 | 2024-12-31 |  |  | STEVE CANOY | 2025-01-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.73333 | 1 | 3366.91 | 49.57 | 0 | 39.87 | 3277.47 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291719500 |  | 100329633 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2101 SAINT CHRISTOP DR | 067 | LEX | 2025-01-27 | U461322 | U125763 | 2024-10-21 | 2024-12-31 |  |  | STEVE CANOY | 2025-01-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.6833 | 1 | 3928.97 | 363.66 | 0 | 23.93 | 3541.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291719600 |  | 100329625 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2104 SAINT CHRISTOP DR | 067 | LEX | 2025-01-17 | U461322 | U125763 | 2024-10-21 | 2024-12-31 |  |  | STEVE CANOY | 2025-01-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6 | 1 | 2950.8 | 384.95 | 0 | 25.32 | 2540.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291719700 |  | 100329632 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2105 SAINT CHRISTOP DR | 067 | LEX | 2024-12-20 | U128762 | U125763 | 2024-10-21 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-12-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3041.65 | 0 | 0 | 0 | 3041.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291719900 |  | 100329631 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2109 SAINT CHRISTOP DR | 067 | LEX | 2024-12-17 | U128762 | U125763 | 2024-10-21 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-12-17 | 2024-12-07 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.5333 | 1 | 2983.89 | 131.31 | 0 | 132.51 | 2720.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291720000 |  | 100329630 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2113 SAINT CHRISTOP DR | 067 | LEX | 2025-01-16 | U128762 | U125763 | 2024-10-21 | 2024-12-31 |  |  | RANDALL TINCHER | 2025-01-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3390.09 | 0 | 0 | 0 | 3390.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291720200 |  | 100329629 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2117 SAINT CHRISTOP DR | 067 | LEX | 2024-12-19 | U128762 | U125763 | 2024-10-21 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-12-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3963.17 | 0 | 0 | 0 | 3963.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291720300 |  | 100329659 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2000 SAINT TERESA DR | 067 | LEX | 2025-02-03 | U461322 | U125763 | 2024-10-21 | 2024-12-31 |  |  | STEVE CANOY | 2025-02-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.8167 | 1 | 3975.54 | 670.37 | 0 | 31.39 | 3273.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291720400 |  | 100329721 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2001 SAINT TERESA DR | 067 | LEX | 2025-02-03 | U461322 | U125763 | 2024-10-21 | 2024-12-31 |  |  | STEVE CANOY | 2025-02-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.13333 | 1 | 2739.12 | 11.43 | 0 | 0.53 | 2727.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291720500 |  | 100329661 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2008 SAINT TERESA DR | 067 | LEX | 2025-02-05 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-02-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3743.4 | 0 | 0 | 0 | 3743.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291720600 |  | 100329719 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2009 SAINT TERESA DR | 067 | LEX | 2025-02-04 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-02-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2294.65 | 0 | 0 | 0 | 2294.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291720700 |  | 100329718 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2013 SAINT TERESA DR | 067 | LEX | 2025-01-31 | U461322 | U125763 | 2024-10-21 | 2024-12-31 |  |  | STEVE CANOY | 2025-01-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.75 | 1 | 3898.28 | 434.49 | 0 | 28.59 | 3435.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291720800 |  | 100329663 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2016 SAINT TERESA DR | 067 | LEX | 2025-02-06 | U129722 | U125763 | 2024-10-21 | 2024-12-31 |  |  | DAVID YOUNG | 2025-02-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3869.87 | 0 | 0 | 0 | 3869.87 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291720900 |  | 100329717 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2017 SAINT TERESA DR | 067 | LEX | 2025-02-06 | U129722 | U125763 | 2024-10-21 | 2024-12-31 |  |  | DAVID YOUNG | 2025-02-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3075.81 | 0 | 0 | 0 | 3075.81 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291721200 |  | 100329716 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2021 SAINT TERESA DR | 067 | LEX | 2025-02-07 | U126604 | U125763 | 2024-10-21 | 2024-12-31 |  |  | WILLIAM FULKS | 2025-02-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2580.34 | 0 | 0 | 0 | 2580.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291721300 |  | 100329665 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2024 SAINT TERESA DR | 067 | LEX | 2025-02-13 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-02-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3496.1 | 0 | 0 | 0 | 3496.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291721400 |  | 100329715 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2025 SAINT TERESA DR | 067 | LEX | 2025-02-12 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-02-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2256.57 | 0 | 0 | 0 | 2256.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291721500 |  | 100329666 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2028 SAINT TERESA DR | 067 | LEX | 2025-02-26 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-02-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3561.19 | 0 | 0 | 0 | 3561.19 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291721600 |  | 100329714 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2029 SAINT TERESA DR | 067 | LEX | 2025-02-14 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-02-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2296.35 | 0 | 0 | 0 | 2296.35 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291721700 |  | 100329667 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2032 SAINT TERESA DR | 067 | LEX | 2025-02-25 | U126530 | U125763 | 2024-10-21 | 2024-12-31 |  |  | JDUNN | 2025-02-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 3112.48 | 600.46 | 0 | 28.13 | 2483.89 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291721800 |  | 100329713 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2033 SAINT TERESA DR | 067 | LEX | 2025-03-11 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-03-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1829.7 | 0 | 0 | 0 | 1829.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291721900 |  | 100329668 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2036 SAINT TERESA DR | 067 | LEX | 2025-02-25 | U126530 | U125763 | 2024-10-21 | 2024-12-31 |  |  | JDUNN | 2025-02-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2287.17 | 0 | 0 | 0 | 2287.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291722000 |  | 100329669 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2040 SAINT TERESA DR | 067 | LEX | 2025-02-27 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-02-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3297.46 | 0 | 0 | 0 | 3297.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291722100 |  | 100329711 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2041 SAINT TERESA DR | 067 | LEX | 2025-03-03 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-02-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3246.09 | 0 | 0 | 0 | 3246.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291722200 |  | 100329671 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2044 SAINT TERESA DR | 067 | LEX | 2025-03-03 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-03-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2805.14 | 0 | 0 | 0 | 2805.14 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291722300 |  | 100329710 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2045 SAINT TERESA DR | 067 | LEX | 2025-03-04 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-03-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2193.61 | 0 | 0 | 0 | 2193.61 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291722400 |  | 100329672 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2048 SAINT TERESA DR | 067 | LEX | 2025-03-05 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-03-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2653.27 | 0 | 0 | 0 | 2653.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291722500 |  | 100329709 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2049 SAINT TERESA DR | 067 | LEX | 2025-03-04 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-03-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2615.7 | 0 | 0 | 0 | 2615.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291722600 |  | 100329708 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2053 SAINT TERESA DR | 067 | LEX | 2025-03-05 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-03-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2609.92 | 0 | 0 | 0 | 2609.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291722700 |  | 100329674 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2056 SAINT TERESA DR | 067 | LEX | 2025-03-07 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-03-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 9918.46 | 0 | 5841.89 | 0 | 4076.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291722800 |  | 100329707 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2057 SAINT TERESA DR | 067 | LEX | 2025-03-06 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-03-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3806.81 | 0 | 0 | 0 | 3806.81 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291722900 |  | 100329675 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2060 SAINT TERESA DR | 067 | LEX | 2025-03-07 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-03-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 10881.28 | 0 | 5855.57 | 0 | 5025.71 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291723000 |  | 100329706 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2061 SAINT TERESA DR | 067 | LEX | 2025-03-14 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-03-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2569.46 | 0 | 0 | 0 | 2569.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291723100 |  | 100329676 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2064 SAINT TERESA DR | 067 | LEX | 2025-03-10 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-03-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2839.71 | 0 | 0 | 0 | 2839.71 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291723200 |  | 100329705 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2065 SAINT TERESA DR | 067 | LEX | 2025-03-10 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-03-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2972.07 | 0 | 0 | 0 | 2972.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291723300 |  | 100329704 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2069 SAINT TERESA DR | 067 | LEX | 2025-03-05 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-03-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3015.74 | 0 | 0 | 0 | 3015.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291723400 |  | 100329678 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2072 SAINT TERESA DR | 067 | LEX | 2025-03-18 | U129731 | U125763 | 2024-10-21 | 2024-12-31 |  |  | EDWARD F GOINS | 2025-03-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10 | 1 | 4029.36 | 675.15 | 0 | 39.58 | 3314.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291723500 |  | 100329703 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2073 SAINT TERESA DR | 067 | LEX | 2025-03-04 | U129731 | U125763 | 2024-10-21 | 2024-12-31 |  |  | EDWARD F GOINS | 2025-03-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.2667 | 1 | 2972.2 | 220.75 | 0 | 12.95 | 2738.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291723600 |  | 100329679 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2076 SAINT TERESA DR | 067 | LEX | 2025-03-03 | U129731 | U125763 | 2024-10-21 | 2024-12-31 |  |  | F.GOINS | 2025-03-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 4180.56 | 540.12 | 0 | 31.66 | 3608.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291723700 |  | 100329702 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2077 SAINT TERESA DR | 067 | LEX | 2025-03-04 | U129731 | U125763 | 2024-10-21 | 2024-12-31 |  |  | EDWARD F GOINS | 2025-03-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.7333 | 1 | 3243.94 | 319.34 | 0 | 18.71 | 2905.89 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291723800 |  | 100329680 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 D341671 | 2600B | SAINT TERESA | 2080 SAINT TERESA DR | 067 | LEX | 2024-12-05 | U128762 | U125763 | 2024-10-21 | 2024-12-06 | 2024-12-25 |  | RANDALL TINCHER | 2024-12-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3027.02 | 0 | 0 | 0 | 3027.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291723900 |  | 100329701 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2081 SAINT TERESA DR | 067 | LEX | 2025-03-05 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-03-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3509.4 | 0 | 0 | 0 | 3509.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291724000 |  | 100329700 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2085 SAINT TERESA DR | 067 | LEX | 2025-02-28 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-02-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2028.88 | 0 | 0 | 0 | 2028.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291724100 |  | 100329699 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2089 SAINT TERESA DR | 067 | LEX | 2025-02-25 | U129731 | U125763 | 2024-10-21 | 2024-12-31 |  |  | F.GOINS | 2025-02-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2194.59 | 0 | 0 | 0 | 2194.59 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291724200 |  | 100329683 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2092 SAINT TERESA DR | 067 | LEX | 2025-02-26 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-02-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4033.22 | 0 | 0 | 0 | 4033.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291724300 |  | 100329698 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2093 SAINT TERESA DR | 067 | LEX | 2025-02-25 | U129731 | U125763 | 2024-10-21 | 2024-12-31 |  |  | F.GOINS | 2025-02-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2508.32 | 0 | 0 | 0 | 2508.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291724400 |  | 100329684 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2096 SAINT TERESA DR | 067 | LEX | 2025-02-14 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-02-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4572.82 | 0 | 0 | 0 | 4572.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291724500 |  | 100329697 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2097 SAINT TERESA DR | 067 | LEX | 2025-02-13 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-02-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2388.63 | 0 | 0 | 0 | 2388.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291724600 |  | 100329685 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2100 SAINT TERESA DR | 067 | LEX | 2025-02-11 | U127414 | U125763 | 2024-10-21 | 2024-12-31 |  |  | EDWARD FOX | 2025-02-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3629.17 | 0 | 0 | 0 | 3629.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291724700 |  | 100329696 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2101 SAINT TERESA DR | 067 | LEX | 2025-02-11 | U127414 | U125763 | 2024-10-21 | 2024-12-31 |  |  | EDWARD FOX | 2025-02-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 5371.91 | 0 | 0 | 0 | 5371.91 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291724800 |  | 100329686 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2104 SAINT TERESA DR | 067 | LEX | 2025-03-11 | U129731 | U125763 | 2024-10-21 | 2024-12-31 |  |  | EDWARD F GOINS | 2025-03-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 4441.12 | 540.12 | 0 | 31.66 | 3869.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291724900 |  | 100329695 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2105 SAINT TERESA DR | 067 | LEX | 2025-02-05 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-02-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2257.19 | 0 | 0 | 0 | 2257.19 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291725000 |  | 100329687 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2108 SAINT TERESA DR | 067 | LEX | 2025-02-03 | U126604 | U125763 | 2024-10-21 | 2024-12-31 |  |  | WILLIAM FULKS | 2025-02-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3576.79 | 0 | 0 | 0 | 3576.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291725100 |  | 100329694 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2109 SAINT TERESA DR | 067 | LEX | 2025-02-06 | U129722 | U125763 | 2024-10-21 | 2024-12-31 |  |  | DAVID YOUNG | 2025-02-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2377.07 | 0 | 0 | 0 | 2377.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291725200 |  | 100329693 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2113 SAINT TERESA DR | 067 | LEX | 2025-02-27 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-02-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2788.41 | 0 | 0 | 0 | 2788.41 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291725300 |  | 100329689 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2116 SAINT TERESA DR | 067 | LEX | 2025-02-12 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-02-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2955.06 | 0 | 0 | 0 | 2955.06 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291725400 |  | 100329692 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2117 SAINT TERESA DR | 067 | LEX | 2025-02-27 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-02-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3017.82 | 0 | 0 | 0 | 3017.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291725500 |  | 100329690 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2120 SAINT TERESA DR | 067 | LEX | 2025-02-05 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-02-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3373.64 | 0 | 0 | 0 | 3373.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291725700 |  | 100329691 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2124 SAINT TERESA DR | 067 | LEX | 2025-03-13 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-03-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 5053.97 | 0 | 0 | 0 | 5053.97 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291726500 |  | 501367899 |  | 6724212J |  |  |  | 563 | EX | 1"P LONG/NO PRMT REQ | 2600B | WAR ADMIRAL | 2212 WAR ADMIRAL WY | 067 | LEX | 2024-11-05 | U128336 | U132253 | 2024-10-21 | 2024-10-23 | 2024-11-05 |  | JOSHUA COX | 2024-11-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26210011 | 10 | 1 | 3657.37 | 821.81 | 212.69 | 49.47 | 2573.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291727600 |  | 100329653 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2021 SAINT CHRISTOP DR | 067 | LEX | 2024-12-13 | U461322 | U125763 | 2024-10-21 | 2024-12-31 |  |  | STEVE CANOY | 2024-12-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.9833 | 1 | 4063.15 | 777.48 | 0 | 45.43 | 3240.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291727700 |  | 100329634 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2097 SAINT CHRISTOP DR | 067 | LEX | 2024-12-13 | U128762 | U125763 | 2024-10-21 | 2024-12-31 |  |  | RANDALL TINCHER | 2024-12-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2995.86 | 0 | 0 | 0 | 2995.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291727800 |  | 100329628 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT CHRISTOP | 2121 SAINT CHRISTOP DR | 067 | LEX | 2025-01-16 | U461322 | U125763 | 2024-10-21 | 2024-12-31 |  |  | STEVE CANOY | 2025-01-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.0833 | 1 | 3205.8 | 392.67 | 0 | 315.65 | 2497.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291727900 |  | 100329660 |  | 6720208C | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2004 SAINT TERESA DR | 067 | LEX | 2025-02-04 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-02-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3473.09 | 0 | 0 | 0 | 3473.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291728000 |  | 100329664 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2020 SAINT TERESA DR | 067 | LEX | 2025-02-11 | U127414 | U125763 | 2024-10-21 | 2024-12-31 |  |  | EDWARD FOX | 2025-02-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 19675.53 | 0 | 16071.24 | 0 | 3604.29 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291728100 |  | 100329712 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2037 SAINT TERESA DR | 067 | LEX | 2025-02-24 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-02-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2296.35 | 0 | 0 | 0 | 2296.35 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291728300 |  | 100329677 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2068 SAINT TERESA DR | 067 | LEX | 2025-03-06 | U129731 | U125763 | 2024-10-21 | 2024-12-31 |  |  | EDWARD F GOINS | 2025-03-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 3595.09 | 540.12 | 0 | 31.66 | 3023.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291728400 |  | 100329682 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2088 SAINT TERESA DR | 067 | LEX | 2025-02-24 | U128816 | U125763 | 2024-10-21 | 2024-12-31 |  |  | OLIVER MAYNARD | 2025-02-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3074.32 | 0 | 0 | 0 | 3074.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291728500 |  | 100329688 |  | 6720208D | 2403558 |  |  | 565 | EX | RPLC SL/24026316700 | 2600B | SAINT TERESA | 2112 SAINT TERESA DR | 067 | LEX | 2025-02-06 | U129722 | U125763 | 2024-10-21 | 2024-12-31 |  |  | DAVID YOUNG | 2025-02-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4131.62 | 0 | 0 | 0 | 4131.62 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24291735300 |  | 501360545 |  | 7328294B | 2404483 |  |  | 563 | EX | 1" P SHORT | 2621P | RIDGE | 125 RIDGE ST | 089 | S S | 2024-11-04 | U124604 | U127708 | 2024-10-21 | 2024-11-11 | 2024-11-11 |  | MCOLLET | 2024-11-02 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 10.25 | 2 | 1522.92 | 847.65 | 254.43 | 352.76 | 68.08 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291741900 |  | 501365563 |  | 6696212P | 2292756 |  |  | 563 | EX | 1" P-LONG/NO PRMT REQ | 2600B | SAFFRON | 558 SAFFRON LN LT33 | 239 | VER | 2024-11-19 | U126532 | U128727 | 2024-10-21 | 2024-10-23 | 2024-11-19 |  | LESLIE SHARON | 2024-11-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 9 | 1 | 4404.88 | 655.57 | 302.68 | 39.47 | 3407.16 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291742000 |  | 501361908 |  | 6712228L | 2292762 |  |  | 563 | EX | 99 1" P SHORT ATKINS HOMES | 2600B | RUTH MILLER | 173 RUTH MILLER DR LT111 | 209 | GEO | 2024-11-01 | U126532 | U142144 | 2024-10-21 | 2024-10-23 | 2024-11-05 |  | LESLIE SHARON | 2024-10-31 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4 | 1 | 1850.9 | 0 | 290.68 | 0 | 1560.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291742100 |  | 501355426 |  | 6716216G | 2301170 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | REMINGTON | 2317 REMINGTON DR LT2 | 067 | LEX | 2024-11-05 | U126285 | U126856 | 2024-10-21 | 2024-10-23 | 2024-11-05 |  | DUSTIN DAVIS | 2024-11-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 9.25 | 1 | 4106.79 | 679 | 0 | 313.17 | 3114.62 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291742400 |  | 501365564 |  | 6696212P | 2292756 |  |  | 563 | EX | 1"P-LONG/NO PRMT REQ | 2600B | SAFFRON | 562 SAFFRON LN LT34 | 239 | VER | 2024-11-05 | U126532 | U128727 | 2024-10-21 | 2024-10-23 | 2024-11-05 |  | LESLIE SHARON | 2024-11-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 5 | 1 | 4123.81 | 364.24 | 287.04 | 169.14 | 3303.39 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291742900 |  | 501365565 |  | 6696212P | 2292756 |  |  | 563 | EX | 1"P-LONG/NO PRMT REQ | 2600B | SAFFRON | 566 SAFFRON LN LT35 | 239 | VER | 2024-11-05 | U126532 | U128727 | 2024-10-21 | 2024-10-23 | 2024-11-05 |  | LESLIE SHARON | 2024-11-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 5 | 1 | 4328.11 | 364.24 | 287.04 | 169.14 | 3507.69 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291745200 |  | 501361909 |  | 6712228L | 2292762 |  |  | 563 | EX | 99 1 " P ATKINS HOMES | 2600B | RUTH MILLER | 171 RUTH MILLER DR LT112 | 209 | GEO | 2024-10-30 | U126532 | U142144 | 2024-10-21 | 2024-10-23 | 2024-11-05 |  | LESLIE SHARON | 2024-10-30 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 1839.62 | 0 | 290.68 | 0 | 1548.94 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291748000 |  | 501361911 |  | 6712228L | 2292762 |  |  | 563 | EX | 99 1 " P ATKINS HOMES | 2600B | RUTH MILLER | 167 RUTH MILLER DR LT114 | 209 | GEO | 2024-10-30 | U126532 | U142144 | 2024-10-21 | 2024-10-23 | 2024-11-05 |  | LESLIE SHARON | 2024-10-30 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 1848.08 | 0 | 290.68 | 0 | 1557.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291748100 |  | 501361915 |  | 6712228L | 2292762 |  |  | 563 | EX | 99 1 " P ATKINS HOMES | 2600B | RUTH MILLER | 155 RUTH MILLER DR LT86 | 209 | GEO | 2024-11-01 | U126532 | U142144 | 2024-10-21 | 2024-10-23 | 2024-11-05 |  | LESLIE SHARON | 2024-10-31 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 1826.93 | 0 | 290.68 | 0 | 1536.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291782600 |  | 100304114 |  | 6712208D | 1635077 |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2621D | VIOLET | 2120 VIOLET RD | 067 | LEX | 2025-02-28 | U124604 | AOC SYST | 2024-10-21 | 2025-04-21 | 2026-10-31 |  | KKINDER | 2025-02-27 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 | KYACA |  | 100 | 056532B26210021 | 18.35 | 2 | 2035.13 | 1404 | 0 | 65.75 | 565.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291890500 |  | 100304112 |  | 6712208D |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D513567 | 2621P | VIOLET | 2128 VIOLET RD | 067 | LEX | 2025-02-28 | U124604 | U124604 | 2024-10-22 | 2025-04-21 | 2026-10-31 |  | RSTRONG | 2025-02-27 | 2025-01-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.5667 | 3 | 7991.51 | 1735.8 | 509.6 | 93.24 | 5652.87 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291891000 |  | 100303674 |  | 6712208D |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D513568 | 2621P | DOGWOOD | 2013 DOGWOOD DR | 067 | LEX | 2025-03-13 | U130761 | U124604 | 2024-10-22 | 2025-04-21 | 2026-10-31 |  | KKINDER | 2025-03-10 | 2025-01-24 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.15 | 5 | 1837.99 | 1173.46 | 355.97 | 308.56 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291892500 |  | 501372898 |  | 6700212E |  |  |  | 563 | EX | PAPER MANIFOLD W/ 500380397 | 2621P | CROSSFIELD | 107 CROSSFIELD DR A | 239 | VER | 2024-10-23 | U125763 | U129176 | 2024-10-22 | 2024-11-05 | 2024-11-05 |  | OFFICE PER MGMNT | 2024-10-23 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26230011 |  | 1 | 162.8 | 0 | 0 | 0 | 162.8 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24291903900 |  | 100239943 |  | 7352264E | 2300016 |  |  | 565 | EX | RPLC SL/23026293500 | 2600B | FERRY | 120 FERRY ST | 089 | RUS | 2024-10-22 | U124015 | U125763 | 2024-10-22 | 2024-12-31 |  |  | ORA SLONE | 2024-10-22 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2181.21 | 0 | 0 | 0 | 2181.21 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291910200 |  | 501327353 |  | 6716232B | 2179247 |  |  | 563 | EX | 1" PL SHORT/NO PRMT REQ | 2600B | GALWAY | 122 GALWAY LN LT228 | 209 | GEO | 2024-11-01 | U126532 | U125753 | 2024-10-22 | 2024-10-23 | 2024-11-05 |  | LESLIE SHARON | 2024-11-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4.9667 | 1 | 2859.79 | 360.57 | 290.68 | 167.41 | 2041.13 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291910300 |  | 501327352 |  | 6716232B | 2179247 |  |  | 563 | EX | 1" PL SHORT/NO PRMT REQ | 2600B | GALWAY | 124 GALWAY LN LT227 | 209 | GEO | 2024-11-01 | U126532 | U125753 | 2024-10-22 | 2024-10-23 | 2024-11-05 |  | LESLIE SHARON | 2024-11-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 3.0333 | 1 | 2338.77 | 222.21 | 449.26 | 103.16 | 1564.14 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291910500 |  | 501327315 |  | 6716232B | 2179247 |  |  | 563 | EX | 1" PL SHORT/NO PRMT REQ | 2600B | WELLESLY | 157 WELLESLY AV LT274 | 209 | GEO | 2024-11-04 | U123111 | U125753 | 2024-10-22 | 2024-10-23 | 2024-11-05 |  | LYN STAFFORD | 2024-11-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 2.5 | 1 | 1597.13 | 186.48 | 317.61 | 11.22 | 1081.82 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291910700 |  | 501327349 |  | 6716232B | 2179247 |  |  | 563 | EX | 1" PL LONG/NO PRMT REQ | 2600B | KIRKSTALL | 101 KIRKSTALL WY LT267 | 209 | GEO | 2024-11-04 | U123111 | U125753 | 2024-10-22 | 2024-10-23 | 2024-11-05 |  | LYN STAFFORD | 2024-11-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 3 | 1 | 4440.74 | 223.77 | 317.61 | 13.47 | 3885.89 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291911100 |  | 501327348 |  | 6716232B | 2179247 |  |  | 563 | EX | 1" PL LONG/NO PRMT REQ | 2600B | KIRKSTALL | 103 KIRKSTALL WY LT266 | 209 | GEO | 2024-11-09 | U128336 | U125753 | 2024-10-22 | 2024-10-23 | 2024-11-08 |  | JOSHUA COX | 2024-11-08 | 2024-11-08 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4.9 | 1 | 4281 | 402.72 | 311.23 | 24.23 | 3542.82 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291911800 |  | 501338344 |  | 6716232B | 2179247 |  |  | 563 | EX | 1" PL SHORT/NO PRMT REQ | 2600B | DUNMORE | 137 DUNMORE LN LT186 | 209 | GEO | 2024-11-04 | U123111 | U125753 | 2024-10-22 | 2024-10-23 | 2024-11-05 |  | LYN STAFFORD | 2024-11-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 3.5 | 1 | 2129.26 | 261.11 | 317.61 | 15.7 | 1534.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291912000 |  | 501338352 |  | 6716232B | 2179247 |  |  | 563 | EX | 1" PL LONG/NO PRMT REQ | 2600B | DUNMORE | 150 DUNMORE LN LT220 | 209 | GEO | 2024-11-07 | U126532 | U125753 | 2024-10-22 | 2024-10-23 | 2024-11-08 |  | LESLIE SHARON | 2024-11-07 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 4276.16 | 582.73 | 287.04 | 270.58 | 3135.81 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24291945700 |  | 500066463 |  | 6684224M |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | US 127 | 2576 US 127 SO SHOP | 073 | FRA | 2024-10-22 | DCOLLIN | U129939 | 2024-10-22 | 2024-10-22 |  |  | DCOLLIN | 2024-10-22 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.15 | 3 | 8.71 | 9.48 | 0 | -0.77 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291946900 |  | 500266039 |  | 16712204B |  |  |  | 563 | EX | 1" P LONG *RUSH*/PRMT READY | 2600B | WITTHUHN | 933 WITTHUHN WY | 067 | LEX | 2024-10-28 | U123111 | U129531 | 2024-10-22 | 2024-10-23 | 2024-11-05 |  | LYN STAFFORD | 2024-10-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 5624.42 | 495.54 | 317.61 | 30.35 | 4780.92 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24291956300 |  | 100243759 |  | 7356256F |  |  |  | 563 | EX | 99 1 " P SHORT | 2621P | SIMPSON | 3218 SIMPSON RD | 019 | ASH | 2024-11-05 | U124604 | U142144 | 2024-10-22 | 2024-10-23 | 2024-11-05 |  | RECUMP | 2024-11-04 | 2024-10-29 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 20.4 | 4 | 2146.78 | 1445.71 | 164.1 | 519.21 | 17.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291968800 |  | 501368848 |  | 6728212M | 2405655 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | BLACKFORD | 2865 BLACKFORD PY | 067 | LEX | 2024-11-01 | U123111 | U126856 | 2024-10-22 | 2024-10-24 | 2024-11-06 |  | LYN STAFFORD | 2024-11-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 2202.61 | 298.36 | 317.61 | 17.96 | 1568.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24291969000 |  | 501368849 |  | 6728212M | 2405655 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | BLACKFORD | 2861 BLACKFORD PY | 067 | LEX | 2024-11-01 | U123111 | U126856 | 2024-10-22 | 2024-10-24 | 2024-11-06 |  | LYN STAFFORD | 2024-11-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 2185.69 | 298.36 | 317.61 | 17.96 | 1551.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24292190200 |  | 100304239 |  | 6712208H |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D513572 | 2621P | CYPRESS | 2152 CYPRESS DR | 067 | LEX | 2025-01-17 | U124604 | U124604 | 2024-10-23 | 2025-04-22 | 2026-10-31 |  | KKINDER | 2025-01-16 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 28.5833 | 5 | 2171.03 | 1570.75 | 392.44 | 147.16 | 60.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24292191800 |  | 100304251 |  | 6712208D |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D513574 | 2621P | CYPRESS | 2112 CYPRESS DR | 067 | LEX | 2025-01-17 | U124604 | U124604 | 2024-10-23 | 2025-04-22 | 2026-10-31 |  | JOCHOA | 2025-01-16 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.5 | 3 | 1889 | 1294.05 | 398.84 | 85.11 | 111 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24292209100 |  | 100304143 |  | 6712208H |  |  |  | 565 | EX | GRADE 1 REPLACE SERVICE LINE | 2621P | ASTER | 874 ASTER RD | 067 | LEX | 2024-10-24 | U124604 | U129939 | 2024-10-23 | 2024-10-23 |  |  | RSTRONG | 2024-10-23 | 2024-10-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.2667 | 3 | 1196.72 | 727.82 | 546.85 | -77.95 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24292212500 |  | 501055132 |  | 6728212M | 0889351 |  |  | 563 | EX | 1"P- LONG/PRMT RCVD | 2600B | BROWNING | 1833 BROWNING TR LT59 | 067 | LEX | 2024-11-15 | U123111 | U128727 | 2024-10-23 | 2024-11-05 | 2024-11-18 |  | LYN STAFFORD | 2024-11-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 3703.25 | 298.36 | 317.61 | 17.96 | 3069.32 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24292227300 |  | 100358435 |  | 6740232M |  |  |  | 563 | EX | 1" P SHORT | 2621P | MAIN | 115 MAIN ST | 017 | PAR | 2024-11-06 | U124604 | U132805 | 2024-10-23 | 2024-10-24 | 2024-11-06 |  | NRICHIE | 2024-11-05 | 2024-10-25 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 29.9333 | 6 | 7779.77 | 2399.83 | 345.96 | 1063.36 | 3970.62 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24292227900 |  | 100435023 |  | 6684228I |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LEE | 102 LEE DR | 073 | FRA | 2024-10-24 | U124604 | U129939 | 2024-10-23 | 2024-10-20 | 2024-11-07 |  | LSTANFI | 2024-10-23 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 | 11.95 | 3 | 1432.47 | 1251.76 | 211.71 | -31 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24292229400 |  | 100304977 |  | 6712212P |  |  |  | 566 | EX | ABANDON SERVICE | 2621P | APPOMATTOX | 1745 APPOMATTOX RD | 067 | LEX | 2024-11-20 | RSTRONG | U124604 | 2024-10-23 | 2024-11-22 | 2024-12-31 |  | RSTRONG | 2024-11-20 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.4167 | 2 | 805.04 | 595.62 | 35.49 | 173.93 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24292257700 |  | 100239969 |  | 7352264E | 2300016 |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | GROVE | 120 GROVE ST | 089 | RUS | 2024-10-24 | U124015 | U129939 | 2024-10-23 | 2024-10-23 |  |  | ORA SLONE | 2024-10-24 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2733.72 | 0 | 0 | 0 | 2733.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24292428800 |  | 100304259 |  | 6712208D |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D514375 | 2621P | TAMARACK | 2107 TAMARACK DR | 067 | LEX | 2025-02-05 | U124604 | U124604 | 2024-10-24 | 2025-04-23 | 2026-10-31 |  | MSHARON | 2025-02-04 | 2025-01-29 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.55 | 6 | 1876.44 | 1407.3 | 401.23 | 67.91 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24292430500 |  | 100303728 |  | 6712208D |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D514377 | 2621P | TAMARACK | 2043 TAMARACK DR | 067 | LEX | 2025-02-28 | U124604 | U124604 | 2024-10-24 | 2025-04-23 | 2026-10-31 |  | RJCRAWF | 2025-02-27 | 2024-12-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.4 | 8 | 1773.7 | 1326.34 | 382.98 | 64.38 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24292444300 |  | 501372439 |  | 6720200F |  |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | CRESTFIELD | 996 CRESTFIELD LN | 067 | LEX | 2024-11-08 | U461516 | U131378 | 2024-10-24 | 2024-10-29 | 2024-11-11 |  | NEAL P JOHNSON | 2024-11-08 |  | 2024-11-08 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2732.55 | 570.61 | 357.25 | 269.85 | 1534.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24292444700 |  | 100304309 |  | 6712208D |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D341622 | 2621P | LARKSPUR | 2117 LARKSPUR DR | 067 | LEX | 2024-11-06 | U124604 | U124604 | 2024-10-24 | 2024-10-25 | 2024-11-14 |  | DMALONE | 2024-11-05 | 2024-11-04 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 37.7 | 6 | 3232.38 | 2629.77 | 195.11 | 407.5 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24292446300 |  | 100270603 |  | 6736248A |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2600B | OLD LAIR | 129 OLD LAIR RD | 097 | CYN | 2024-10-31 | U126284 | U140273 | 2024-10-24 | 2024-11-13 | 2024-12-06 |  | JPASLEY | 2024-10-29 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1492.79 | 0 | 0 | 0 | 1492.79 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24292465200 |  | 501368538 |  | 7328264K | 2407391 |  |  | 563 | EX | 20 1" P SHORT | 2621P | LIME | 1037 LIME ST | 089 | FLA | 2024-11-08 | ABHATFIE | U132805 | 2024-10-24 | 2024-10-25 | 2024-11-07 |  | ABHATFIE | 2024-11-08 | 2024-11-05 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 27.7167 | 5 | 3642.65 | 2196.63 | 0 | 1114.5 | 331.52 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24292483000 |  | 501368294 |  | 7348260B |  |  |  | 563 | EX | 1" P SHORT NO HEAT | 2621P | INDIAN RUN | 2715 INDIAN RUN RD | 089 | FLA | 2024-11-11 | U141668 | U132256 | 2024-10-24 | 2024-11-07 | 2024-11-07 |  | MCOLLET | 2024-11-08 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 15.05 | 2 | 3795.72 | 1243.66 | 389.98 | 1108.84 | 1053.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24292751500 |  | 100306211 |  | 6712212L |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D513533 | 2621P | PORT ROYAL | 1902 PORT ROYAL CT | 067 | LEX | 2025-03-31 | U124604 | U124604 | 2024-10-25 | 2025-04-24 | 2026-10-31 |  | KOBRYAN | 2025-03-28 | 2025-01-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25.5333 | 11 | 1891.79 | 1471.19 | 142.95 | 148.89 | 128.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24292751800 |  | 100461236 |  | 6716212J |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D513535 | 2621P | RED MILE | 651 RED MILE RD | 067 | LEX | 2025-02-25 | U124604 | U124604 | 2024-10-25 | 2025-04-24 | 2026-10-31 |  | KKINDER | 2025-02-24 | 2025-01-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.95 | 3 | 1448.33 | 1226.53 | 20.12 | 58.12 | 143.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24292760900 |  | 501320906 |  | 7352256B |  |  |  | 563 | EX | 99 1" P LONG | 2621P | PRICHARD | 420 PRICHARD ST | 019 | ASH | 2024-11-11 | U141668 | U120250 | 2024-10-25 | 2024-11-08 | 2024-11-22 |  | MCOLLET | 2024-11-09 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 23.2667 | 2 | 3030.88 | 1927.48 | 560.64 | 399.2 | 143.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24292765700 |  | 100302703 |  | 6712212M |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | WELLESLEY HTS | 1525 WELLESLEY HTS WY | 067 | LEX | 2024-11-27 | U141668 | U124604 | 2024-10-25 | 2024-11-22 |  |  | RSTRONG | 2024-11-26 | 2024-11-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.8333 | 8 | 2377.87 | 1542.33 | 363.27 | 328.71 | 143.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24292767500 |  | 100239983 |  | 7352264E | 2300016 |  |  | 565 | EX | REPLACE SL/ 23026293500 | 2600B | GROVE | 141 GROVE ST | 089 | RUS | 2024-10-25 | U124015 | U129589 | 2024-10-25 | 2024-12-31 |  |  | ORA SLONE | 2024-10-25 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 1957.66 | 0 | 0 | 0 | 1957.66 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24292775900 |  | 100264474 |  | 7356260M |  |  |  | 566 | EX | ABANDON SL/DEMO CUST REQ | 2621P | MONTGOMERY | 829 MONTGOMERY AV | 019 | ASH | 2025-01-16 | MCOLLET | U140273 | 2024-10-25 | 2024-11-14 | 2024-12-09 |  | MCOLLET | 2025-01-16 | 2024-12-30 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 15.2667 | 4 | 2055.02 | 1120.16 | 0 | 294.86 | 640 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24292779500 |  | 100241633 |  | 7356256P |  |  |  | 566 | EX | ABANDON SL/DEMO CUST REQ | 2621P | BOYD | 4748 BOYD ST | 019 | ASH | 2024-11-18 | JCYRUS | U140273 | 2024-10-25 | 2024-11-14 | 2024-12-09 |  | JCYRUS | 2024-11-18 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 7.2667 | 2 | 2165.93 | 572.39 | 20.28 | 34.44 | 1538.82 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24292780700 |  | 100242763 |  | 7356256O |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | GALLAHER | 1213 GALLAHER DR | 019 | ASH | 2024-11-18 | JCYRUS | U140273 | 2024-10-25 | 2024-11-14 | 2024-12-09 |  | JCYRUS | 2024-11-18 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.5333 | 2 | 1213.21 | 274.36 | 20.28 | 16.5 | 902.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24292789300 |  | 500029256 |  | 6712208O |  |  |  | 565 | EX | REPAIR SERVICE LINE | 2621P | BLENHEIM | 3273 BLENHEIM WY | 067 | LEX | 2024-10-29 | U124604 | U139701 | 2024-10-25 | 2024-10-24 | 2024-10-24 |  | BYOUNG2 | 2024-10-28 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.36667 | 1 | 595.84 | 731.21 | 0 | -135.37 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24292812300 |  | 501373127 |  | 6684228N |  |  |  | 563 | EX | 1"P SHORT/PRMT RCVD | 2600B | LEAWOOD | 1105 LEAWOOD DR | 073 | FRA | 2024-11-14 | U126532 | U128266 | 2024-10-25 | 2024-11-05 | 2024-11-18 |  | LESLIE SHARON | 2024-11-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBMAN |  | 100 | 056332B26230012 | 4.9667 | 1 | 2926.63 | 360.57 | 488.09 | 167.41 | 1910.56 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24292812800 |  | 501373128 |  | 6684228N |  |  |  | 563 | EX | MANIFOLD W/ 501373127 | 2600B | LEAWOOD | 1107 LEAWOOD DR | 073 | FRA | 2024-11-14 | U126532 | U128266 | 2024-10-25 | 2024-11-05 | 2024-11-18 |  | LESLIE SHARON | 2024-11-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBMAN |  | 100 | 056332B26230012 | 3.0333 | 1 | 325.37 | 222.21 | 0 | 103.16 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24292946800 |  | 100435615 |  | 6716208N |  |  |  | 563 | EX | PAPER TAP W/MASTER 100435979 | 2600B | REGENCY | 2520 REGENCY RD 106 | 067 | LEX | 2024-10-29 | U124604 | U133050 | 2024-10-28 | 2024-10-31 | 2024-10-31 |  | OFFICE | 2024-10-29 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBMAN |  | 100 | 056332B26210011 |  | 1
KY | KY - WEST | 2621 | 24292947200 |  | 501308771 |  | 6724208B | 2177929 |  |  | 563 | EX | 1" P LONG/PRMT RCVD | 2600B | LORENZO | 2417 LORENZO WY | 067 | LEX | 2024-11-15 | U126532 | U126856 | 2024-10-28 | 2024-11-05 | 2024-11-18 |  | LESLIE SHARON | 2024-11-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4300.07 | 582.73 | 302.68 | 35.07 | 3379.59 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24292956100 |  | 100285141 |  | X |  |  |  | 566 | EX | ABANDON SL/DEMO CUST REQ | 2621P | BAUMSTARK | 122 BAUMSTARK RD | 151 | WAC | 2024-12-04 | U930915 | JTOY | 2024-10-28 | 2024-11-27 |  |  | DENNING | 2024-12-03 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10.55 | 3 | 1486.29 | 858.17 | 0 | 628.12 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24292967900 |  | 501348639 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | CALISTA FLAT | 793 CALISTA FLAT | 067 | LEX | 2024-11-07 | U128336 | U126856 | 2024-10-28 | 2024-10-29 | 2024-11-11 |  | JOSHUA COX | 2024-11-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 2.2833 | 1 | 2099.03 | 186.57 | 305.73 | 11.21 | 1595.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24292972500 |  | 100313327 |  | 6716208B |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | SPRINGHILL | 501 SPRINGHILL DR | 067 | LEX | 2024-11-25 | TROE | U140273 | 2024-10-28 | 2024-11-15 | 2024-12-10 |  | TROE | 2024-11-25 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.4333 | 2 | 645.38 | 595.22 | 14.35 | 35.81 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24292977700 |  | 500354711 |  | 7332132J |  |  |  | 563 | EX | 1' P SHORT | 2621P | HIGHWAY 899 | 6260 HIGHWAY 899 A | 119 | PIP | 2024-11-19 | BPREECE | U133050 | 2024-10-28 | 2024-10-29 | 2024-11-11 |  | BPREECE | 2024-11-19 | 2024-11-18 |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26330011 | 29.3 | 3 | 2761.1 | 2137.3 | 0 | 511.32 | 112.48 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24292980400 |  | 500462027 |  | 6700224L | 2293724 |  |  | 565 | EX | RPLC SL/22026238401 | 2600B | MIDWAY | 6642 MIDWAY RD | 239 | MID | 2024-10-28 | U128816 | U125763 | 2024-10-28 | 2024-12-31 |  |  | OLIVER MAYNARD | 2024-10-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3843.46 | 0 | 0 | 0 | 3843.46 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24292980600 |  | 100239972 |  | 7352264E | 2300016 |  |  | 565 | EX | REPLACE SL/23026293500 | 2621P | GROVE | 125 GROVE ST | 089 | RUS | 2024-10-28 | U124015 | U129589 | 2024-10-28 | 2024-12-31 |  |  | ORA SLONE | 2024-10-28 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 1962.85 | 0 | 0 | 0 | 1962.85 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24292980800 |  | 100239981 |  | 7352264E | 2300016 |  |  | 565 | EX | REPLACE SL/ 24-2929806-00 | 2621P | GROVE | 137 GROVE ST | 089 | RUS | 2024-10-28 | U124015 | U129589 | 2024-10-28 | 2024-12-31 |  |  | ORA SLONE | 2024-10-28 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 2142.95 | 0 | 0 | 0 | 2142.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24293000300 |  | 100319924 |  | 6716208K |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D311713 | 2621P | JESSELIN | 214 JESSELIN DR | 067 | LEX | 2024-10-30 | U124604 | U124604 | 2024-10-28 | 2024-10-28 | 2024-10-28 |  | HSTANFI | 2024-10-29 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.9333 | 3 | 1726.77 | 1458.54 | 100.44 | 89.35 | 78.44 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24293002300 |  | 100356210 |  | 7256280F |  |  |  | 565 | EX | REPLACE SERVICELINE | 2621P | JERSEY RIDGE | 845 JERSEY RIDGE RD | 161 | MAY | 2025-01-27 | SDADAMS | U123688 | 2024-10-28 | 2024-12-31 |  |  | SDADAMS | 2025-01-27 | 2025-01-27 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26320031 | 22.4667 | 3 | 2197.3 | 1407.15 | 209.17 | 92.58 | 488.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24293019200 |  | 100323249 |  | 6716208P |  |  |  | 565 | EX | MTR MOVE OUT/ UPGRADE | 2621P | STARLING | 3140 STARLING DR | 067 | LEX | 2024-11-04 | U124604 | U124604 | 2024-10-28 | 2024-11-27 |  |  | ATWILLI | 2024-11-01 | 2024-11-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 43.55 | 5 | 4611.94 | 3197.66 | 664.89 | 749.39 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24293031700 |  | 100313559 |  | 6716208B |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HERON | 1547 HERON LN | 067 | LEX | 2024-10-31 | MCRAIG | U139701 | 2024-10-28 | 2024-10-28 | 2024-10-28 |  | MCRAIG | 2024-10-31 | 2024-10-31 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.1833 | 2 | 1146.15 | 535.53 | 679.43 | -187.21 | 118.4 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24293036500 |  | 100462027 |  | 7240216I |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | INDIAN MOUND | 1107 INDIAN MOUND DR D | 173 | MT | 2024-10-29 | U124604 | U137585 | 2024-10-28 | 2025-04-01 | 2026-10-31 |  | DENNING | 2024-10-29 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26290021 | 48.6 | 7 | 9547.23 | 4744.61 | 49.14 | 290.76 | 4462.72 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24293168600 |  | 100355911 |  | 7260276B |  |  |  | 563 | EX | 1" P SHORT | 2621P | WOOD | 609 WOOD ST | 161 | MAY | 2024-11-13 | U141668 | U129176 | 2024-10-29 | 2024-10-29 | 2024-11-12 |  | SDADAMS | 2024-11-12 | 2024-11-04 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26320011 | 29.0667 | 6 | 3045.32 | 2089.43 | 663.01 | 248.48 | 44.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24293173000 |  | 100319538 |  | 6716208L | 2409540 |  |  | 565 | EX | UPGRADE SERVICE LINE | 2621P | GREENBRIAR | 401 GREENBRIAR RD | 067 | LEX | 2024-11-21 | U124604 | U124604 | 2024-10-29 | 2024-11-26 | 2024-11-26 |  | RJCRAWF | 2024-11-20 | 2024-11-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 18.05 | 3 | 4818.27 | 1287.61 | 748.23 | 77.51 | 2704.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24293173100 |  | 500514180 |  | 6720208M | 2409328 |  |  | 563 | EX | TAP WITH MAIN 24-0263657-00 | 2600B | MONTAVESTA | 3426 MONTAVESTA RD | 067 | LEX | 2024-11-20 | U461309 | U129531 | 2024-10-29 | 2025-01-29 | 2025-01-29 |  | RANDALL HUMPHREYS | 2024-11-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBTWM |  | 100 | 056332B26210012 | 8 | 1 | 2617.21 | 553.61 | 266.31 | 268.83 | 1528.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24293175100 |  | 100288620 |  | 6720212H |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | BELLCASTLE | 624 BELLCASTLE RD | 067 | LEX | 2024-10-31 | DMALONE | U129939 | 2024-10-29 | 2024-09-30 | 2024-09-30 |  | DMALONE | 2024-10-31 | 2024-10-29 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.25 | 2 | 127.5 | 120.15 | 0 | 7.35 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24293180800 |  | 100302270 |  | 6712212G |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | ROCKY POINT | 2301 ROCKY POINT CT B | 067 | LEX | 2024-11-22 | U130722 | U124604 | 2024-10-29 | 2024-12-31 |  |  | BDARNELL | 2024-11-21 | 2024-11-21 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 11.0167 | 2 | 659.31 | 621.88 | 0 | 37.43 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24293187800 |  | 100351521 |  | 6744208P |  |  |  | 563 | EX | 1.25" P SHORT | 2600B | HICKMAN | 305 W HICKMAN ST | 049 | WIN | 2024-11-15 | U461309 | U129531 | 2024-10-29 | 2024-10-30 | 2024-11-12 |  | RANDALL HUMPHREYS | 2024-11-12 | 2024-11-12 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 8 | 1 | 2427.88 | 553.61 | 474.24 | 268.83 | 1131.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24293192300 |  | 500027563 |  | 6752180F |  |  |  | 563 | EX | 1" P SHORT | 2621P | FLINT | 318 FLINT RD | 151 | WAC | 2024-11-04 | DENNING | U129294 | 2024-10-29 | 2024-11-12 | 2024-11-12 |  | DENNING | 2024-11-04 | 2024-11-01 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 23.4 | 5 | 2593.46 | 1980.4 | 233.38 | 119.2 | 260.48 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24293198700 |  | 100456475 |  | 6696212G |  |  |  | 566 | EX | ABANDON SERVICE LN -CUST REQ | 2621P | SPRING RUN | 187 SPRING RUN ST | 239 | VER | 2024-11-27 | U128410 | U124604 | 2024-10-29 | 2024-11-27 | 2024-12-31 |  | CDESPAIN | 2024-11-26 | 2024-11-26 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 16 | 2 | 1265.09 | 1193.28 | 0 | 71.81 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24293204500 |  | 501372739 |  | 7352256B |  |  |  | 563 | EX | 99 1"P LONG | 2621P | OLD BUCKLEY | 415 OLD BUCKLEY RD | 019 | ASH | 2024-11-18 | U124604 | U132253 | 2024-10-29 | 2024-11-12 | 2024-11-26 |  | MCOLLET | 2024-11-16 | 2024-11-11 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 23.9333 | 5 | 5633.53 | 1938.03 | 251.68 | 590.58 | 2853.24 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24293207200 |  | 501371531 |  | 7364188H | 2408866 |  |  | 563 | EX | 1" P LONG | 2621P | BLACKLOG | 2291 BLACKLOG RD | 159 | INE | 2024-10-31 | U130172 | U132258 | 2024-10-29 | 2024-10-30 | 2024-11-12 |  | C HAMMOND | 2024-10-31 |  |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26330011 | 0.88333 | 1 | 62.33 | 58.74 | 0 | 3.59 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24293233000 |  | 501183462 |  | 6736216L | 2292620 |  |  | 563 | EX | 1" P SHORT | 2621P | SQUIRES POINTE | 209 SQUIRES POINTE RD | 017 | PAR | 2024-11-08 | U124604 | U138822 | 2024-10-29 | 2024-10-29 | 2024-11-12 |  | NRICHIE | 2024-11-07 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 12.5667 | 2 | 2275.04 | 1053.9 | 254.43 | 849.79 | 116.92 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24293245200 |  | 501317398 |  | 6716236J | 2178365 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | FLAMINGO | 102 FLAMINGO CR | 209 | GEO | 2024-11-12 | U126532 | U126856 | 2024-10-29 | 2024-10-30 | 2024-11-12 |  | LESLIE SHARON | 2024-11-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 5.0167 | 1 | 4577.29 | 364.2 | 287.04 | 169.1 | 3756.95 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24293256900 |  | 100429642 |  | 7356152E |  |  |  | 566 | EX | ABANDON SERVCIE LINE-DEMO | 2621P | 1ST | 1ST ST | 071 | HAR | 2024-11-25 | BPREECE | U123688 | 2024-10-29 | 2024-11-22 |  |  | BPREECE | 2024-11-25 | 2024-11-04 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 23.8 | 4 | 1831.83 | 1727.85 | 0 | 103.98 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24293262900 |  | 501348642 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | CALISTA FLAT | 805 CALISTA FLAT | 067 | LEX | 2024-11-07 | U128336 | U126856 | 2024-10-29 | 2024-10-30 | 2024-11-12 |  | JOSHUA COX | 2024-11-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 1.7833 | 1 | 1550.43 | 147.12 | 311.23 | 8.85 | 1083.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24293263100 |  | 501348604 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | CALISTA FLAT | 769 CALISTA FLAT | 067 | LEX | 2024-11-07 | U128336 | U126856 | 2024-10-29 | 2024-10-30 | 2024-11-12 |  | JOSHUA COX | 2024-11-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 2.85 | 1 | 2099.1 | 235.86 | 305.73 | 14.21 | 1543.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24293269200 |  | 501266493 |  | 6720204O | 1963066 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | HARPER WOODS | 3517 HARPER WOODS LN LT29 | 067 | LEX | 2024-11-11 | U126532 | U129531 | 2024-10-29 | 2024-10-31 | 2024-11-13 |  | LESLIE SHARON | 2024-11-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4.5 | 1 | 3998.73 | 327.8 | 287.04 | 152.21 | 3231.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24293271000 |  | 501266490 |  | 6720204O | 1963066 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | HARPER WOODS | 3521 HARPER WOODS LN LT26 | 067 | LEX | 2024-11-11 | U126532 | U129531 | 2024-10-29 | 2024-10-31 | 2024-11-13 |  | LESLIE SHARON | 2024-11-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 5 | 1 | 4109.9 | 364.24 | 287.04 | 169.1 | 3289.52 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24293275800 |  | 501372456 |  | 7348248L |  |  |  | 563 | EX | 99 1" P LONG | 2621P | JOHNSON | 11910 E JOHNSON RD | 019 | CAN | 2024-11-18 | U124604 | U120250 | 2024-10-29 | 2024-11-12 | 2024-11-26 |  | MCOLLET | 2024-11-15 | 2024-11-11 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 27.3167 | 5 | 4013.82 | 2125.85 | 713.63 | 1035.22 | 139.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24293276200 |  | 501313783 |  | 6716232B | 2289995 |  |  | 563 | EX | 99 1" P SHORT ATKINS 2ND TRY | 2600B | OAK HILL | 117 OAK HILL LN LT8 | 209 | GEO | 2024-11-13 | U123111 | U120250 | 2024-10-29 | 2024-10-31 | 2024-11-13 |  | LYN STAFFORD | 2024-11-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 1867.97 | 0 | 317.62 | 0 | 1550.35 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24293286000 |  | 100254790 |  | 7348260D |  |  |  | 565 | EX | GRADE 2+ SERVICE LINE REPLACE | 2621P | VERNA | 57 VERNA DR | 089 | RUS | 2024-11-13 | U141668 | U137585 | 2024-10-29 | 2024-11-01 | 2024-11-19 |  | MCOLLET | 2024-11-12 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 13.3833 | 2 | 2559.4 | 1026.54 | 330.18 | 1106.48 | 96.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24293514300 |  | 100295191 |  | 6716212H |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | JEFFERSON | 430 JEFFERSON ST | 067 | LEX | 2024-11-26 | HSTANFI | U140273 | 2024-10-30 | 2024-11-19 | 2024-12-12 |  | HSTANFI | 2024-11-26 | 2024-11-26 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 23.9833 | 3 | 1574.85 | 1464.78 | 21.9 | 88.17 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24293530700 |  | 501373160 |  | 6716212D | 2408860 |  |  | 563 | EX | PAPER W/500195440 | 2600B | LOUDON | 360 W LOUDON AV BLG ADD | 067 | LEX | 2024-11-01 | U125763 | U127708 | 2024-10-30 | 2024-11-13 | 2024-11-13 |  | OFFICE PER MNGMNT | 2024-11-01 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26210011 |  | 1
KY | KY - WEST | 2621 | 24293534200 |  | 501333757 |  | 6724204A | 2185117 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | NIGHT HERON | 3508 NIGHT HERON WY | 067 | LEX | 2024-11-12 | U126284 | U126856 | 2024-10-30 | 2024-10-31 | 2024-11-13 |  | JOSH PASLEY | 2024-11-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 5.0333 | 1 | 1559.44 | 400.8 | 0 | 24.13 | 1134.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24293534500 |  | 501303276 |  | 6724208M |  |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | SQUIRES | 281 SQUIRES CR | 067 | LEX | 2024-11-12 | U126284 | U126856 | 2024-10-30 | 2024-10-31 | 2024-11-13 |  | JOSH PASLEY | 2024-11-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 7.4667 | 1 | 4309.33 | 597.19 | 0 | 35.93 | 3676.21 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24293534700 |  | 501333745 |  | 6724204A | 2185117 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | SQUIRES | 231 SQUIRES CR | 067 | LEX | 2024-11-13 | U123111 | U126856 | 2024-10-30 | 2024-10-31 | 2024-11-13 |  | LYN STAFFORD | 2024-11-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4067.49 | 596.69 | 317.62 | 35.92 | 3117.26 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24293535700 |  | 501317407 |  | 6716236J | 2178365 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | CHICKADEE | 132 CHICKADEE TR | 209 | GEO | 2024-11-12 | U126532 | U126856 | 2024-10-30 | 2024-10-31 | 2024-11-13 |  | LESLIE SHARON | 2024-11-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 3848.15 | 0 | 287.04 | 0 | 3561.11 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24293535900 |  | 501317408 |  | 6716236J | 2178365 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | CHICKADEE | 130 CHICKADEE TR | 209 | GEO | 2024-11-12 | U126532 | U126856 | 2024-10-30 | 2024-10-31 | 2024-11-13 |  | LESLIE SHARON | 2024-11-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 3.4833 | 1 | 3790.32 | 254.95 | 287.04 | 118.38 | 3129.95 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24293536100 |  | 501317306 |  | 6716236J | 2178365 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | DOVE RUN | 138 DOVE RUN CR | 209 | GEO | 2024-11-20 | U123111 | U126856 | 2024-10-30 | 2024-10-31 | 2024-11-20 |  | LYN STAFFORD | 2024-11-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 4716.31 | 596.69 | 311.24 | 35.92 | 3772.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24293555100 |  | 501373254 |  | 6716216C | 2301170 |  |  | 563 | EX | PAPER W/501369334 | 2600B | STOCKTON | 1976 STOCKTON WY | 067 | LEX | 2024-11-01 | U125763 | U127708 | 2024-10-30 | 2024-11-13 | 2024-11-13 |  | OFFICE PER MNGMNT | 2024-11-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBPEX |  | 100 | 056332B26210012 |  | 1
KY | KY - WEST | 2621 | 24293556700 |  | 501343671 |  | 6716220M | 2394864 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | MARLENA | 1205 MARLENA LN | 067 | LEX | 2024-11-13 | U123111 | U126856 | 2024-10-30 | 2024-10-31 | 2024-11-13 |  | LYN STAFFORD | 2024-11-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1404.98 | 0 | 318.93 | 0 | 1086.05 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24293556900 |  | 501343672 |  | 6716220M | 2394864 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | MARLENA | 1209 MARLENA LN | 067 | LEX | 2024-11-12 | U461309 | U126856 | 2024-10-30 | 2024-10-31 | 2024-11-13 |  | RANDALL HUMPHREYS | 2024-11-11 | 2024-11-11 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 3.5 | 1 | 1666.04 | 242.24 | 217.31 | 117.62 | 1088.87 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24293557000 |  | 501343673 |  | 6716220M | 2394864 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | MARLENA | 1213 MARLENA LN | 067 | LEX | 2024-11-12 | U461309 | U126856 | 2024-10-30 | 2024-10-31 | 2024-11-13 |  | RANDALL HUMPHREYS | 2024-11-11 | 2024-11-11 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4.5 | 1 | 1754.58 | 311.43 | 222.81 | 151.21 | 1069.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24293557100 |  | 501343708 |  | 6716220M | 2394864 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | MARLENA | 1236 MARLENA LN | 067 | LEX | 2024-11-13 | U461516 | U126856 | 2024-10-30 | 2024-10-31 | 2024-11-13 |  | NEAL JOHNSON | 2024-11-13 |  | 2024-11-13 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 9 | 1 | 3557.11 | 641.96 | 304.85 | 163.75 | 2446.55 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24293558800 |  | 501371219 |  | 7344268 |  |  |  | 563 | EX | 1" P LONG | 2621P | JACOBS | 156 JACOBS LN | 089 | WUR | 2024-11-08 | U124604 | U129176 | 2024-10-30 | 2024-10-30 | 2024-11-13 |  | MCOLLET | 2024-11-07 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 21.5 | 2 | 3945.91 | 1780.4 | 483.93 | 1496.58 | 185 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24293576800 |  | 100267137 |  | 7352260N |  |  |  | 563 | EX | 99 1" P SHORT | 2621P | SARAH | 2308 SARAH RD | 019 | ASH | 2024-11-13 | U141668 | U129294 | 2024-10-30 | 2024-11-13 | 2024-11-13 |  | RECUMP | 2024-11-12 | 2024-11-07 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 30.1333 | 6 | 4099.66 | 2141.19 | 990.5 | 914.69 | 53.28 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24293581300 |  | 100240802 |  | 7324132I | 2409813 |  |  | 563 | EX | 99 1" P SHORT | 2621P | MAIN | 88 W MAIN ST 2ND FL | 119 | HIN | 2024-11-22 | U130172 | U120250 | 2024-10-30 | 2024-11-13 | 2024-11-27 |  | JAHOWARD | 2024-11-22 | 2024-11-04 |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26330011 | 11.45 | 3 | 1348.76 | 836.5 | 300 | 212.26 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24293581500 |  | 500449352 |  | 7356256G | 1963163 |  |  | 563 | EX | 1" P LONG | 2621P | CENTRAL | 2825 CENTRAL AV | 019 | ASH | 2024-11-22 | U124604 | U132627 | 2024-10-30 | 2024-10-31 | 2024-11-13 |  | ABHATFIE | 2024-11-21 | 2024-11-12 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 11.0667 | 3 | 5038.14 | 896.2 | 191.8 | 105.5 | 3844.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24293582800 |  | 100303217 |  | 6712208C |  |  |  | 565 | EX | GRADE 1 REPLACE SL | 2621P | LILY | 993 LILY CT | 067 | LEX | 2024-11-01 | U124604 | U129939 | 2024-10-30 | 2024-10-30 | 2024-10-30 |  | RJCRAWF | 2024-10-31 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.1667 | 2 | 1252.44 | 875.72 | 323.06 | 53.66 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24293586600 |  | 100326810 |  | 6720208E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | CHINOE | 602 CHINOE RD | 067 | LEX | 2024-11-01 | U124604 | U138682 | 2024-10-30 | 2024-10-30 | 2024-10-30 |  | LSTANFI | 2024-10-31 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 27.7667 | 4 | 1894.18 | 473.55 | 587.48 | 29.47 | 803.68 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24293672100 |  | 100281216 |  | 6700220K |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D513677 | 2621P | OLD FRANKFORT | 3504 OLD FRANKFORT PK FG39 | 239 | VER | 2025-06-13 | U128410 | U124604 | 2024-10-31 | 2025-04-30 | 2026-10-31 |  | CDESPAIN | 2025-06-12 | 2025-04-15 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 116.15 | 12 | 22156.79 | 9428.11 | 657.4 | 2885.83 | 9185.45 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24293682400 |  | 100240005 |  | 7352264E | 2300016 |  |  | 565 | EX | REPLACE SL/23026293500 | 2600B | FERRY | 306< FERRY ST | 089 | RUS | 2024-10-31 | U124015 | U129589 | 2024-10-31 | 2024-12-31 |  |  | ORA SLONE | 2024-10-31 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 1897.49 | 0 | 0 | 0 | 1897.49 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24293683500 |  | 501373034 |  | 6716220C |  |  |  | 563 | EX | 99 1"P LONG/NO PRMT REQ | 2600B | SPINDLETOP | 2791 SPINDLETOP WY | 067 | LEX | 2024-11-18 | U126284 | U132253 | 2024-10-31 | 2024-11-05 | 2024-11-18 |  | JOSH PASLEY | 2024-11-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 19.5 | 2 | 4935.14 | 1505.45 | 0 | 90.61 | 3339.08 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24293706000 |  | 500184017 |  | V-804/46 |  |  |  | 563 | EX | 99 1" P LONG/PRMT RCVD | 2600B | QUACHITA | 103 QUACHITA TL | 073 | FRA | 2024-11-27 | U128816 | U134341 | 2024-10-31 | 2024-11-19 | 2024-12-03 |  | OLIVER MAYNARD | 2024-11-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 1601.33 | 0 | 0 | 0 | 1601.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24293706900 |  | 100331579 |  | 6720212N |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | HAZEL | 103 HAZEL AV | 067 | LEX | 2024-11-21 | U123688 | U140273 | 2024-10-31 | 2024-11-20 | 2024-12-13 |  | SSHIMFE | 2024-11-20 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10.9833 | 3 | 738.06 | 658.62 | 39.78 | 39.66 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24293709800 |  | 100447201 |  | 7348260G |  |  |  | 565 | EX | GRADE 1 REPLACE SERVICE | 2621P | HARRIS | 2001 HARRIS WAY | 089 | RUS | 2024-11-01 | U124604 | U129939 | 2024-10-31 | 2024-10-31 | 2024-10-31 |  | ABHATFIE | 2024-10-31 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 7 | 2 | 100.64 | 0 | 0 | 0 | 100.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24293849800 |  | 100323040 |  | 6716208L | 2409486 |  |  | 565 | EX | SERVICE LINE UPGRADE | 2621P | OLD DOBBIN | 800 OLD DOBBIN RD | 067 | LEX | 2024-11-25 | U141668 | U124604 | 2024-11-01 | 2024-11-27 | 2024-11-29 |  | MCRAIG | 2024-11-22 | 2024-11-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 33.95 | 7 | 8871.56 | 2533.97 | 812.23 | 858.47 | 4666.89 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24293850100 |  | 100352651 |  | 6744204F |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | VALLEY | 12 VALLEY DR | 049 | WIN | 2024-11-01 | DENNING | U139701 | 2024-11-01 | 2024-11-01 |  |  | DENNING | 2024-11-01 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26290031 | 6.7333 | 2 | 674.26 | 578.72 | 0 | 34.86 | 60.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24293850400 |  | 501348612 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | CALISTA FLAT | 721 CALISTA FLAT | 067 | LEX | 2024-11-12 | U461309 | U126856 | 2024-11-01 | 2024-11-04 | 2024-11-15 |  | RANDALL HUMPHREYS | 2024-11-08 | 2024-11-08 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4.5 | 1 | 1760.22 | 311.43 | 222.81 | 151.21 | 1074.77 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24293850600 |  | 501348613 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | CALISTA FLAT | 717 CALISTA FLAT | 067 | LEX | 2024-11-12 | U461309 | U126856 | 2024-11-01 | 2024-11-04 | 2024-11-15 |  | RANDALL HUMPHREYS | 2024-11-08 | 2024-11-08 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 3.5 | 1 | 1642.59 | 242.24 | 216.42 | 117.62 | 1066.31 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24293854000 |  | 501373038 |  | 6712228F |  |  |  | 563 | EX | PAPER W/ 100404313 | 2600B | BROADWAY | 705 S BROADWAY A | 209 | GEO | 2024-11-08 | U125763 | U132627 | 2024-11-01 | 2024-11-15 | 2024-11-15 |  | OFFICE PER MGMNT | 2024-11-08 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBMAN |  | 100 | 056332B26230012 |  | 1 | 257.52 | 0 | 0 | 0 | 257.52 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24293886400 |  | 501372476 |  | 7364188H | 2409740 |  |  | 563 | EX | 99 1" P SHORT | 2621P | MAIN ST | 1298 E MAIN ST | 159 | INE | 2024-11-22 | JCKIRK | U120250 | 2024-11-01 | 2024-11-15 | 2024-11-29 |  | JCKIRK | 2024-11-22 | 2024-11-06 |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26330011 | 36.5333 | 7 | 9002.69 | 2679.45 | 182.32 | 234.84 | 5906.08 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24293888400 |  | 501372765 |  | 7240216 |  |  |  | 563 | EX | 1"P-SHORT | 2621P | MIDLAND TRAIL | 228 MIDLAND TRAIL DR | 173 | MT | 2024-11-13 | DENNING | U128727 | 2024-11-01 | 2024-11-04 | 2024-11-15 |  | DENNING | 2024-11-13 | 2024-11-08 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 27.3333 | 5 | 6907.46 | 2227.37 | 633.87 | 1001.57 | 3044.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24293961500 |  | 100244293 |  | 356256O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D359583 | 2621P | GARTRELL | 620 GARTRELL ST | 019 | ASH | 2025-05-30 | U124604 | U123688 | 2024-11-04 | 2025-05-01 | 2026-11-30 |  | MCOLLET | 2025-05-29 | 2025-03-20 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 30.0333 | 6 | 7354.24 | 2135.64 | 334.63 | 2891.57 | 1992.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24293989500 |  | 100336676 |  | 6720212I |  |  |  | 563 | EX | 1" P SHORT *RUSH* | 2600B | HAWKINS | 454 HAWKINS AV | 067 | LEX | 2024-11-18 | U126532 | U128272 | 2024-11-04 | 2024-11-05 | 2024-11-18 |  | LESLIE SHARON | 2024-11-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26210011 | 9 | 1 | 2110.71 | 655.57 | 279.75 | 39.47 | 1135.92 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24294020200 |  | 100281423 |  | 6712232N |  |  |  | 565 | EX | REPLACE SERVICE LINE D333416 | 2621P | BROADWAY | 511 N BROADWAY ST | 209 | GEO | 2024-11-14 | U123688 | U124604 | 2024-11-04 | 2024-11-07 | 2024-11-25 |  | DCOLLIN | 2024-11-13 | 2024-11-13 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 26 | 3 | 4516.96 | 1977.36 | 114.39 | 418.44 | 2006.77 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294027100 |  | 100328763 |  | 6720208F | 2409869 | U124604 |  | 565 | EX | SERVICE LINE UPGRADE-NBT | 2621P | HART | 1965 HART RD | 067 | LEX | 2024-11-25 | U141668 | U124604 | 2024-11-04 | 2024-12-23 | 2024-12-25 |  | RSTRONG | 2024-11-22 | 2024-11-21 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 32.95 | 5 | 3590.87 | 2044.26 | 931.07 | 508.98 | 106.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24294032900 |  | 501373141 |  | 7356216D |  |  |  | 563 | EX | 1.25" P LONG | 2621P | RICE | 110 S RICE AV B | 127 | LOU | 2024-11-25 | U141668 | U129531 | 2024-11-04 | 2024-11-25 | 2024-11-25 |  | LAMAY | 2024-11-22 | 2024-11-11 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 13.4667 | 6 | 5840.51 | 1054.64 | 196.95 | 543.32 | 4045.6 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24294036100 |  | 100344639 |  | 6700224K |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | 2ND | 330 2ND ST | 239 | MID | 2024-11-22 | U128410 | U140273 | 2024-11-04 | 2024-11-22 | 2024-12-17 |  | CDESPAIN | 2024-11-22 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 4.3833 | 2 | 361.26 | 340.76 | 0 | 20.5 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294040900 |  | 501373163 |  | 6708200-C |  |  |  | 563 | EX | 1"P LONG/NO PRMT REQ | 2600B | KEENE MANOR | 435 KEENE MANOR CR LT 28 | 113 | NIC | 2024-11-22 | U126284 | U128266 | 2024-11-04 | 2024-11-12 | 2024-11-25 |  | JOSH PASLEY | 2024-11-22 | 2024-11-21 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 15.55 | 2 | 5933.45 | 1241.51 | 0 | 383.84 | 4308.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24294152900 |  | 500251698 |  | 7352256L | 2409878 |  |  | 563 | EX | 99 1.25" P LONG | 2621P | BLACKBURN | 2610 BLACKBURN AV | 019 | ASH | 2024-12-27 | U141668 | U120250 | 2024-11-05 | 2024-11-19 | 2024-12-17 |  | ABHATFIE | 2024-12-26 | 2024-12-20 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 51.5167 | 7 | 17525.19 | 3888.89 | 119.56 | 3545.34 | 9971.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24294156400 |  | 501358727 |  | 6700212O | 2398395 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | WROUGHTON | 622 WROUGHTON DR | 239 | VER | 2024-11-15 | U126284 | U126856 | 2024-11-05 | 2024-11-08 | 2024-11-21 |  | JOSH PASLEY | 2024-11-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 10.5 | 1 | 2020.47 | 838.33 | 0 | 50.45 | 1131.69 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24294197200 |  | 500320051 |  | 6712228J |  |  |  | 563 | EX | 1" P SHORT/PRMT RCVD | 2600B | MARSHALL PARK | 1010 MARSHALL PARK DR | 209 | GEO | 2024-11-20 | U461516 | U134341 | 2024-11-05 | 2024-11-08 | 2024-11-21 |  | NEAL JOHNSON | 2024-11-20 |  | 2024-11-20 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4.3167 | 1 | 2587.41 | 306.75 | 312.11 | 145.05 | 1823.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24294228700 |  | 500627592 |  | 6680224K | 9722970 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | WATERFORD | 140 WATERFORD CR LT46 | 073 | FRA | 2024-11-22 | U461516 | U138822 | 2024-11-05 | 2024-11-12 | 2024-11-25 |  | NEALJOHNSON | 2024-11-22 |  | 2024-11-22 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 2234.93 | 570.61 | 311.24 | 269.85 | 1083.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294374800 |  | 501373372 |  | 6720208K | 2410013 |  |  | 563 | EX | 2" P LONG/NO PRMT REQ | 2600B | LAKETOWER | 519 LAKETOWER DR | 067 | LEX | 2024-11-15 | U461516 | U126856 | 2024-11-06 | 2024-11-08 | 2024-11-21 |  | NEAL JOHNSON | 2024-11-15 | 2024-11-14 | 2024-11-14 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 16 | 2 | 6195.32 | 1141.22 | 2017.14 | 304.19 | 2732.77 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24294376100 |  | 501285868 |  | 7236212L | 2069582 |  |  | 563 | EX | 1" P SHORT | 2621P | SANDE RIDGE LN | 310 SANDE RIDGE LN LT12 | 173 | MT | 2024-11-21 | DENNING | U128272 | 2024-11-06 | 2024-12-02 | 2024-12-02 |  | DENNING | 2024-11-21 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 2.7667 | 3 | 1282.77 | 237.63 | 772.58 | 146.76 | 125.8 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24294423100 |  | 100462062 |  | 7332288M |  |  |  | 563 | EX | 1" P SHORT | 2621P | BIGGS | 170 BIGGS LN | 089 | S S | 2024-11-21 | U124604 | U128272 | 2024-11-06 | 2024-11-20 | 2024-11-20 |  | LAMAY | 2024-11-20 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 8.25 | 1 | 5243.47 | 642.77 | 345.08 | 313.16 | 3942.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294431100 |  | 501348635 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | CLEMATIS | 2208 CLEMATIS WY | 067 | LEX | 2024-12-30 | U123111 | U126856 | 2024-11-06 | 2024-11-08 | 2024-11-21 |  | LYN STAFFORD | 2024-11-19 | 2024-11-19 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4053.01 | 596.69 | 229.19 | 35.92 | 3191.21 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294431400 |  | 501334692 |  | 6716216E | 2290521 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | CALENDULA | 2320 CALENDULA RD | 067 | LEX | 2024-11-19 | U126284 | U126856 | 2024-11-06 | 2024-11-08 | 2024-11-21 |  | JOSH PASLEY | 2024-11-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4922.17 | 638.72 | 0 | 273.96 | 4009.49 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24294432700 |  | 500630052 |  | 6748208I | 2293700 |  |  | 566 | EX | ABANDON SL/ 22-0262373-00 | 2600B | GOLDIE | 21 GOLDIE AV B-1FR | 049 | WIN | 2024-11-06 | U127414 | U129589 | 2024-11-06 | 2024-12-31 |  |  | EDWARD FOX | 2024-11-06 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - CENTRAL | 2632 | 24294548200 |  | 500114717 |  | 7252280P |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | MARTIN LUTHER | 1050 MARTIN LUTHER HY | 161 | MAY | 2024-11-20 | U124604 | U140273 | 2024-11-07 | 2024-11-27 | 2024-12-27 |  | SDADAMS | 2024-11-19 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 7.1333 | 2 | 584.51 | 513.8 | 39.78 | 30.93 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24294562300 |  | 100342696 |  | 7240216N |  |  |  | 563 | EX | 1" P SHORT | 2621P | CLAY | 110 CLAY ST | 173 | MT | 2024-11-22 | JTOY | U130192 | 2024-11-07 | 2024-11-21 | 2024-11-21 |  | DENNING | 2024-11-21 | 2024-11-19 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 30.3833 | 8 | 4996.44 | 2512.75 | 589.27 | 1198.98 | 695.44 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24294575100 |  | 100244656 |  | 7356256G |  |  |  | 563 | EX | 1" P LONG | 2621P | CENTRAL | 3436 CENTRAL AV | 019 | ASH | 2024-11-21 | U124604 | U138822 | 2024-11-07 | 2024-11-07 | 2024-11-21 |  | ABHATFIE | 2024-11-20 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 2.4833 | 1 | 4451.27 | 205.67 | 158.35 | 12.38 | 4074.87 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24294607900 |  | 500833045 |  | 7324132F |  |  |  | 563 | EX | 1" P LONG | 2621P | MAIN | 1014 E MAIN ST GARAGE | 119 | HIN | 2025-01-06 | U123688 | U132256 | 2024-11-07 | 2024-12-19 | 2024-12-19 |  | JAHOWARD | 2024-12-23 | 2024-12-23 |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26330011 | 40.5 | 3 | 7404.86 | 3744.38 | 0 | 218.72 | 3441.76 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24294620600 |  | 100261117 |  | 7352256D |  |  |  | 563 | EX | 1" P SHORT | 2621P | HICKMAN | 1917 HICKMAN ST | 019 | ASH | 2024-11-22 | ABHATFIE | U134341 | 2024-11-07 | 2024-11-21 | 2024-11-21 |  | ABHATFIE | 2024-11-22 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 8 | 1 | 2797.56 | 663.34 | 0 | 39.92 | 2094.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24294621300 |  | 500465375 |  | 7240280F |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | BRIDGEVILLE | 372 BRIDGEVILLE RD | 023 | GER | 2024-11-25 | SDADAMS | U140273 | 2024-11-07 | 2024-11-27 | 2024-12-20 |  | SDADAMS | 2024-11-25 | 2024-11-19 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 19.2667 | 5 | 1515.93 | 1384.1 | 48.51 | 83.32 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294724400 |  | 501343696 |  | 6716220M | 2394864 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | MARLENA | 1280 MARLENA LN | 067 | LEX | 2024-11-22 | U123111 | U126856 | 2024-11-08 | 2024-11-12 | 2024-11-25 |  | LYN STAFFORD | 2024-11-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 2165.88 | 298.36 | 304.85 | 17.96 | 1544.71 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294725800 |  | 501343707 |  | 6716220M | 2394864 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | MARLENA | 1240 MARLENA LN | 067 | LEX | 2024-11-21 | U126284 | U126856 | 2024-11-08 | 2024-11-12 | 2024-11-25 |  | JOSH PASLEY | 2024-11-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 6.45 | 1 | 5054.89 | 514.97 | 0 | 31 | 4508.92 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24294738900 |  | 100348565 |  | 6748208I | 2293700 | U461383 |  | 565 | EX | INSTALL 100' OF 2"PMMP S/L | 2600B | WINN | 215 WINN AV BLDG117 | 049 | WIN | 2024-12-09 | U126604 | U461383 | 2024-11-08 | 2024-12-12 | 2024-12-15 |  | WILLIAM FULKS | 2024-12-09 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0032 | AMRCB |  | 100 | 056532B26290032 | 13.0333 | 2 | 25179.95 | 1097.35 | 19492.15 | 393.42 | 4197.03 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24294739400 |  | 501350547 |  | 6716232J | 2398315 |  |  | 563 | EX | 1" P SHORT BALL/NO PRMT REQ | 2600B | OXFORD LANDING | 131 OXFORD LANDING DR LT82 | 209 | GEO | 2024-11-21 | U123111 | U129294 | 2024-11-08 | 2024-11-12 | 2024-11-25 |  | LYN STAFFORD | 2024-11-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4 | 1 | 2164.55 | 298.36 | 317.62 | 17.96 | 1530.61 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24294740800 |  | 501332974 |  | 6716232I | 2180856 |  |  | 563 | EX | 1" P LONG BALL/NO PRMT REQ | 2600B | OXFORD LANDING | 108 OXFORD LANDING DR | 209 | GEO | 2024-11-21 | U461516 | U129294 | 2024-11-08 | 2024-11-12 | 2024-11-25 |  | NEAL JOHNSON | 2024-11-21 |  | 2024-11-21 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 4221.68 | 570.61 | 304.85 | 269.85 | 3076.37 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24294743500 |  | 501350538 |  | 6716232J | 2398315 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | OXFORD LANDING | 151 OXFORD LANDING DR LT73 | 209 | GEO | 2024-11-21 | U123111 | U130192 | 2024-11-08 | 2024-11-12 | 2024-11-25 |  | LYN STAFFORD | 2024-11-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4 | 1 | 2153.27 | 298.36 | 317.62 | 17.96 | 1519.33 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24294743600 |  | 501350541 |  | 6716232J | 2398315 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | OXFORD LANDING | 143 OXFORD LANDING DR LT76 | 209 | GEO | 2024-11-20 | U461516 | U130192 | 2024-11-08 | 2024-11-12 | 2024-11-25 |  | NEAL JOHNSON | 2024-11-20 |  | 2024-11-20 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 3.6833 | 1 | 1771.92 | 263.92 | 311.24 | 124.81 | 1071.95 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24294763900 |  | 100433954 |  | 7324132I |  |  |  | 563 | EX | 20 1" P LONG | 2621P | MAIN | 440 W MAIN ST | 119 | HIN | 2024-12-13 | JAHOWARD | U142144 | 2024-11-08 | 2024-11-11 | 2024-12-30 |  | JAHOWARD | 2024-12-13 | 2024-12-12 |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26330011 | 54.3333 | 5 | 20126.24 | 4880.37 | 29.46 | 285.05 | 14931.36 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24294764600 |  | 100246495 |  | 7356256I |  |  |  | 563 | EX | 1.25" P LONG | 2621P | RIDGEWAY | 3204 RIDGEWAY DR | 019 | ASH | 2024-11-25 | U141668 | U129294 | 2024-11-08 | 2024-11-22 | 2024-11-22 |  | LAMAY | 2024-11-22 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 8.7667 | 2 | 5145.67 | 682.51 | 185.31 | 58.05 | 4219.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24294767200 |  | 501371461 |  | 6736228C | 2408620 |  |  | 563 | EX | 1" CS HP | 2621P | THORNBERRY | 300 THORNBERRY WY | 017 | PAR | 2024-11-20 | U124604 | U126856 | 2024-11-08 | 2024-11-22 | 2024-11-22 |  | NRICHIE | 2024-11-19 | 2024-11-15 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 38.2833 | 5 | 3753.3 | 3006.04 | 263.74 | 483.52 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294776400 |  | 500514191 |  | 6720208M |  |  |  | 563 | EX | 1" P SHORT/PRMT RCVD | 2600B | PEPPERHILL | 3209 PEPPERHILL RD | 067 | LEX | 2024-11-27 | U129722 | U128272 | 2024-11-08 | 2024-11-22 | 2024-12-09 |  | DAVID YOUNG | 2024-11-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1886.96 | 0 | 287.04 | 0 | 1599.92 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24294928500 |  | 100270599 |  | 6736248A |  |  |  | 563 | EX | 1"P LONG ***RUSH*** | 2621P | OLD LAIR | 121 OLD LAIR RD | 097 | CYN | 2024-11-22 | JTOY | U132253 | 2024-11-11 | 2024-11-25 | 2024-12-09 |  | NRICHIE | 2024-11-21 | 2024-11-15 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 13.8667 | 5 | 5190.17 | 1114.9 | 0 | 280.25 | 3795.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294942800 |  | 100445829 |  | 6716212O |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | LIMESTONE | 800 S LIMESTONE ST | 067 | LEX | 2025-01-06 | U123688 | U124604 | 2024-11-11 | 2024-12-31 | 2024-12-31 |  | RJCRAWF | 2024-12-04 | 2024-11-25 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 14.5167 | 4 | 1593.7 | 974.82 | 21.82 | 57.06 | 540 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294955800 |  | 100325853 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | COLONY | 377 COLONY BV | 067 | LEX | 2025-04-18 | U128336 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSHUA COX | 2025-04-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1505.89 | 0 | 0 | 0 | 1505.89 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294956200 |  | 100325489 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | COOPER | 1202 COOPER DR 1 | 067 | LEX | 2025-03-24 | U128336 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSHUA COX | 2025-03-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 5706.98 | 0 | 0 | 0 | 5706.98 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294957100 |  | 100325736 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | COOPER | 1207 COOPER DR | 067 | LEX | 2025-03-06 | U128336 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSHUA COX | 2025-03-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1513.24 | 0 | 0 | 0 | 1513.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294957500 |  | 100325493 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | COOPER | 1208 COOPER DR | 067 | LEX | 2025-01-17 | U128336 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSHUA COX | 2025-01-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2249.12 | 0 | 0 | 0 | 2249.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294958700 |  | 100325494 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | COOPER | 1210 COOPER DR | 067 | LEX | 2025-02-05 | U128336 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSHUA COX | 2025-02-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3728.45 | 0 | 0 | 0 | 3728.45 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294958900 |  | 100325735 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | COOPER | 1211 COOPER DR | 067 | LEX | 2025-03-11 | U128336 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSHUA COX | 2025-03-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2401.09 | 0 | 0 | 0 | 2401.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294960200 |  | 100325495 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | COOPER | 1214 COOPER DR | 067 | LEX | 2025-01-28 | U128336 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSHUA COX | 2025-01-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2341.18 | 0 | 0 | 0 | 2341.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294960300 |  | 100325734 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | COOPER | 1215 COOPER DR | 067 | LEX | 2025-03-13 | U128336 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSHUA COX | 2025-03-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1527.94 | 0 | 0 | 0 | 1527.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294960400 |  | 100325496 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | COOPER | 1218 COOPER DR | 067 | LEX | 2025-01-17 | U129722 | U125201 | 2024-11-11 | 2024-12-20 |  |  | DAVID YOUNG | 2025-01-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2337.73 | 486.27 | 0 | 31.99 | 1819.47 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294960500 |  | 100325733 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | COOPER | 1219 COOPER DR | 067 | LEX | 2025-03-11 | U128336 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSHUA COX | 2025-03-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2948.02 | 0 | 0 | 0 | 2948.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294960600 |  | 100325698 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | COOPER | 1225 COOPER DR | 067 | LEX | 2025-03-12 | U128336 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSHUA COX | 2025-03-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1739.6 | 0 | 0 | 0 | 1739.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294960700 |  | 100325498 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | COOPER | 1226 COOPER DR | 067 | LEX | 2025-01-31 | U128336 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSHUA COX | 2025-01-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2438.5 | 0 | 0 | 0 | 2438.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294960800 |  | 100325697 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | COOPER | 1229 COOPER DR | 067 | LEX | 2025-03-17 | U128336 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSHUA COX | 2025-03-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2237.36 | 0 | 0 | 0 | 2237.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294960900 |  | 100325499 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | COOPER | 1230 COOPER DR | 067 | LEX | 2025-05-02 | U126602 | U125201 | 2024-11-11 | 2024-12-20 |  |  | DEREK PAYTON | 2025-02-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2602.46 | 0 | 0 | 0 | 2602.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294961000 |  | 100325696 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | COOPER | 1233 COOPER DR | 067 | LEX | 2025-03-10 | U129731 | U125201 | 2024-11-11 | 2024-12-20 |  |  | EDWARD GOINS | 2025-03-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 3544.03 | 540.12 | 0 | 31.66 | 2972.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294961100 |  | 100325500 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | COOPER | 1234 COOPER DR | 067 | LEX | 2025-02-03 | U128336 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSHUA COX | 2025-02-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2437.03 | 0 | 0 | 0 | 2437.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294961200 |  | 100325695 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | COOPER | 1237 COOPER DR | 067 | LEX | 2025-03-19 | U128336 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSHUA COX | 2025-03-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3117.86 | 0 | 0 | 0 | 3117.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294961400 |  | 100325502 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | COOPER | 1242 COOPER DR | 067 | LEX | 2024-12-13 | U128336 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSHUA COX | 2024-12-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2766.68 | 0 | 0 | 0 | 2766.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294961500 |  | 100325677 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | COOPER | 1244 COOPER DR | 067 | LEX | 2025-04-01 | U128336 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSHUA COX | 2025-04-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2507.82 | 0 | 0 | 0 | 2507.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294961600 |  | 100325678 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | COOPER | 1245 COOPER DR | 067 | LEX | 2025-03-13 | U128336 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSHUA COX | 2025-03-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1986.56 | 0 | 0 | 0 | 1986.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294962200 |  | 100325521 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | INDIAN MOUND | 1165 INDIAN MOUND RD | 067 | LEX | 2024-12-10 | U128336 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSHUA COX | 2024-12-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2281.43 | 0 | 287.04 | 0 | 1994.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294962300 |  | 100325526 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | INDIAN MOUND | 1166 INDIAN MOUND RD | 067 | LEX | 2025-02-28 | U128336 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSHUA COX | 2025-02-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2778.67 | 0 | 0 | 0 | 2778.67 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294962400 |  | 100325520 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | INDIAN MOUND | 1169 INDIAN MOUND RD | 067 | LEX | 2024-12-06 | U128336 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSHUA COX | 2024-12-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2219.15 | 0 | 311.23 | 0 | 1907.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294962500 |  | 100325527 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | INDIAN MOUND | 1170 INDIAN MOUND RD | 067 | LEX | 2025-01-31 | U128336 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSHUA COX | 2025-01-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3094.23 | 0 | 0 | 0 | 3094.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294962600 |  | 100325529 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | INDIAN MOUND | 1178 INDIAN MOUND RD | 067 | LEX | 2025-02-28 | U128336 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSHUA COX | 2025-02-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3100.22 | 0 | 0 | 0 | 3100.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294962800 |  | 100325516 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | INDIAN MOUND | 1181 INDIAN MOUND RD | 067 | LEX | 2025-05-01 | U126602 | U125201 | 2024-11-11 | 2024-12-20 |  |  | DEREK PAYTON | 2024-12-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2978.07 | 0 | 0 | 0 | 2978.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294962900 |  | 100325530 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | INDIAN MOUND | 1182 INDIAN MOUND RD | 067 | LEX | 2025-02-13 | U128336 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSHUA COX | 2025-02-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2134.02 | 0 | 0 | 0 | 2134.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294963100 |  | 100325517 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | INDIAN MOUND | 1185 INDIAN MOUND RD | 067 | LEX | 2024-12-13 | U128336 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSHUA COX | 2024-12-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2200.14 | 0 | 0 | 0 | 2200.14 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294963300 |  | 100325514 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | INDIAN MOUND | 1193 INDIAN MOUND RD | 067 | LEX | 2024-12-05 | U128336 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSHUA COX | 2024-12-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1666.78 | 0 | 217.31 | 0 | 1449.47 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294963400 |  | 100325532 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | INDIAN MOUND | 1194 INDIAN MOUND RD | 067 | LEX | 2025-05-01 | U126602 | U125201 | 2024-11-11 | 2024-12-20 |  |  | DEREK PAYTON | 2024-12-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2380.51 | 0 | 0 | 0 | 2380.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294966500 |  | 100325519 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | INDIAN MOUND | 1173 INDIAN MOUND RD | 067 | LEX | 2024-12-07 | U128336 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSHUA COX | 2024-12-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2452.02 | 0 | 389.11 | 0 | 2062.91 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294966600 |  | 100325518 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | INDIAN MOUND | 1177 INDIAN MOUND RD | 067 | LEX | 2024-12-12 | U128336 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSHUA COX | 2024-12-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2453.56 | 0 | 311.23 | 0 | 2142.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294966700 |  | 100325531 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | INDIAN MOUND | 1186 INDIAN MOUND RD | 067 | LEX | 2024-12-20 | U126284 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSH PASLEY | 2024-12-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 3954.92 | 700.83 | 0 | 697.96 | 2556.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294966900 |  | 100325515 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2600B | INDIAN MOUND | 1189 INDIAN MOUND RD | 067 | LEX | 2024-12-11 | U128336 | U125201 | 2024-11-11 | 2024-12-20 |  |  | JOSHUA COX | 2024-12-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2575.2 | 0 | 281.53 | 0 | 2293.67 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294976500 |  | 500654132 |  | 6712208B | 9829045 |  |  | 563 | EX | 1' P LONG/PRMT RCVD | 2600B | SOVEREIGN | 2133 SOVEREIGN LN | 067 | LEX | 2024-12-12 | U461516 | U133050 | 2024-11-11 | 2024-12-02 | 2024-12-13 |  | NEAL JOHNSON | 2024-12-12 |  | 2024-12-12 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 5764.72 | 587.16 | 311.23 | 691.33 | 4175 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24294990000 |  | 501239158 |  | 6720200I | 2408944 |  |  | 563 | EX | 1" P SHORT *ARTISAN HOMES* | 2600B | SERENITY | 1027 SERENITY CR LT17 | 113 | NIC | 2024-11-26 | U129722 | U138822 | 2024-11-11 | 2024-11-15 | 2024-12-03 |  | DAVID YOUNG | 2024-11-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 3190.35 | 0 | 294.34 | 0 | 2896.01 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24295056100 |  | 500518783 |  | 7356220P | 1855491 |  |  | 566 | EX | ABANDON SL/18-0267944-00 | 2600B | MOORE | 310 MOORE ST A | 127 | LOU | 2024-11-12 | U123965 | U141460 | 2024-11-12 | 2024-12-31 |  |  | CJH BRENT RUNYON | 2024-11-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1
KY | KY - WEST | 2621 | 24295071600 |  | 500626798 |  | 6728204K | 9830707 |  |  | 563 | EX | 1"P LONG/PRMT RCVD | 2600B | CUTTERS HILL | 360 CUTTERS HILL CT | 067 | LEX | 2024-12-12 | U123111 | U132253 | 2024-11-12 | 2024-12-02 | 2024-12-13 |  | LYN STAFFORD | 2024-12-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 5 | 1 | 4518.94 | 401.91 | 311.23 | 23.48 | 3782.32 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295081500 |  | 100354585 |  | 7260280M |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | 2ND | 609 E 2ND ST | 161 | MAY | 2025-01-16 | RALLISO | U141668 | 2024-11-12 | 2024-12-31 |  |  | RALLISO | 2025-01-16 |  |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26320031 | 17.2833 | 4 | 1207.7 | 1067.9 | 0 | 70.24 | 69.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24295091800 |  | 100260097 |  | 7356256A | 2075304 |  |  | 565 | EX | REPLACE SL/ 20026983300 | 2621P | HILTON | 1504 HILTON AV | 019 | ASH | 2024-11-12 | U124015 | U129589 | 2024-11-12 | 2024-12-31 |  |  | ORA SLONE | 2024-11-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 5759.81 | 0 | 0 | 0 | 5759.81 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295100700 |  | 500020546 |  | 16708204L |  |  |  | 563 | EX | 20 1" P SHORT/NO PRMT REQ | 2600B | SUMMERTREE | 91 SUMMERTREE DR LT6C | 113 | NIC | 2024-11-25 | U129722 | U142144 | 2024-11-12 | 2024-11-15 | 2024-12-03 |  | DAVID YOUNG | 2024-11-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 2206.98 | 0 | 293.42 | 0 | 1913.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295106600 |  | 100325036 |  | 6720204A |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | GREENTREE | 3470 GREENTREE RD | 067 | LEX | 2024-11-13 | U141668 | U129939 | 2024-11-12 | 2024-11-12 |  |  | LSTANFI | 2024-11-12 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.2833 | 1 | 1744.77 | 1198.25 | 401.87 | 72.13 | 72.52 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295110500 |  | 501363944 |  | 6696212N | 2404754 |  |  | 563 | EX | 1" P LONG HP MAIN | 2600B | TYRONE | 1031 TYRONE PK 100 | 239 | VER | 2024-12-04 | U126532 | U127708 | 2024-11-12 | 2024-11-22 | 2024-12-09 |  | LESLIE SHARON | 2024-12-03 | 2024-12-02 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 27.5 | 3 | 18258.99 | 2128.28 | 1345.34 | 781.33 | 14004.04 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295110800 |  | 501363953 |  | 6696212N | 2404754 |  |  | 563 | EX | MANIFOLD W/501363944 | 2600B | TYRONE | 1031 TYRONE PK 200 | 239 | VER | 2024-12-04 | U126532 | U127708 | 2024-11-12 | 2024-11-22 | 2024-12-09 |  | LESLIE SHARON | 2024-12-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1
KY | KY - WEST | 2623 | 24295110900 |  | 501363954 |  | 6696212N | 2404754 |  |  | 563 | EX | MANIFOLD W/501363944 | 2600B | TYRONE | 1031 TYRONE PK 300 | 239 | VER | 2024-12-04 | U126532 | U127708 | 2024-11-12 | 2024-11-22 | 2024-12-09 |  | LESLIE SHARON | 2024-12-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1
KY | KY - WEST | 2621 | 24295111800 |  | 501343693 |  | 6716220M | 2394864 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | MARLENA | 1292 MARLENA LN | 067 | LEX | 2024-11-22 | U123111 | U126856 | 2024-11-12 | 2024-11-15 | 2024-11-29 |  | LYN STAFFORD | 2024-11-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 2262.16 | 298.36 | 412.41 | 17.96 | 1533.43 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295117700 |  | 501373422 |  | 7240216E |  |  |  | 563 | EX | 1" P SHORT | 2621P | CLUBHOUSE | 1367 CLUBHOUSE LN | 173 | MT | 2024-11-18 | DENNING | U129294 | 2024-11-12 | 2024-11-26 | 2024-11-26 |  | DENNING | 2024-11-18 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 24 | 3 | 3440.34 | 1966.27 | 587.92 | 886.15 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295129300 |  | 501372371 |  | 6728204O | 2409791 |  |  | 563 | EX | 1" P LONG/PRMT RCVD | 2600B | CUTTERS HILL | 270 CUTTERS HILL CT | 067 | LEX | 2024-12-19 | U123111 | U128266 | 2024-11-12 | 2024-12-02 | 2024-12-13 |  | LYN STAFFORD | 2024-12-18 | 2024-12-17 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 10.5 | 2 | 11090.73 | 843.96 | 262.4 | 49.31 | 9935.06 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24295154800 |  | 500568603 |  | 7340264B | 1635077 |  |  | 565 | EX | AOC L1 ATMOS CORR REPL RISER | 2631D | STATE RT 1 | 1627 STATE RT 1 | 089 | GRE | 2025-01-02 | CWHEELE | AOC SYST | 2024-11-12 | 2024-12-12 | 2025-01-11 |  | CWHEELE | 2025-01-02 | 2024-12-30 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26310031 | 2.9833 | 3 | 336.59 | 223.38 | 0 | 71.77 | 41.44 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295273400 |  | 100270949 |  | 6736248A | 1313371 |  |  | 565 | EX | SERVICE LINE REPAIR | 2621P | MILEY | 102 MILEY AV | 097 | CYN | 2024-11-13 | NRICHIE | U134902 | 2024-11-13 | 2024-11-13 |  |  | NRICHIE | 2024-11-13 | 2024-11-13 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 13.45 | 4 | 2610.1 | 1091.22 | 426.18 | 453.34 | 639.36 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295282100 |  | 100446240 |  | 6768172B |  |  |  | 563 | EX | 1" P LONG | 2621P | DANIELS ADDITI | 407 DANIELS ADDITI | 065 | RAV | 2024-11-20 | DENNING | U132627 | 2024-11-13 | 2024-11-14 | 2024-11-27 |  | DENNING | 2024-11-20 | 2024-11-15 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 27.55 | 6 | 3905.75 | 2253.84 | 575.47 | 1015.76 | 60.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295282600 |  | 100290115 |  | 6720212B |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | LOCUST | 311 LOCUST AV | 067 | LEX | 2024-12-17 | U930915 | U140273 | 2024-11-13 | 2024-12-04 | 2024-12-27 |  | HSTANFI | 2024-12-17 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 14.5167 | 2 | 941.56 | 868.92 | 21.9 | 50.74 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295282700 |  | 100290114 |  | 6720212B |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | LOCUST | 311< LOCUST AV 102 | 067 | LEX | 2024-12-17 | HSTANFI | U140273 | 2024-11-13 | 2024-12-04 | 2024-12-27 |  | HSTANFI | 2024-12-17 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.4833 | 1 | 114.98 | 108.63 | 0 | 6.35 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295296000 |  | 501361907 |  | 6712228L | 2292762 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | RUTH MILLER | 175 RUTH MILLER DR LT110 | 209 | GEO | 2024-12-03 | U126284 | U129531 | 2024-11-13 | 2024-11-22 | 2024-12-09 |  | JOSH PASLEY | 2024-12-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 2.8 | 1 | 1870.8 | 247.92 | 0 | 14.5 | 1608.38 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24295325400 |  | 500026653 |  | 7356216D | 1855491 |  |  | 565 | EX | RPLC SL/18026794400 | 2600B | ROBINSON | 305 ROBINSON ST | 127 | LOU | 2024-12-09 | U123965 | U125763 | 2024-11-13 | 2024-12-31 |  |  | CJH BRENT RUNYON | 2024-12-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2313.53 | 0 | 0 | 0 | 2313.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295328600 |  | 100305086 |  | 6712212O |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | ANTIETAM | 1982 ANTIETAM RD | 067 | LEX | 2024-11-15 | U123688 | U124604 | 2024-11-13 | 2024-12-31 |  |  | LSTANFI | 2024-11-14 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16 | 2 | 1837.04 | 1180.87 | 318.94 | 337.23 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24295330900 |  | 501373145 |  | 7356256C |  |  |  | 563 | EX | 99 1" P SHORT | 2621P | GREENUP | 3412 GREENUP AV | 019 | ASH | 2024-11-25 | U141668 | U142144 | 2024-11-13 | 2024-11-14 | 2024-11-27 |  | MCOLLET | 2024-11-23 | 2024-11-23 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 23 | 4 | 2221.15 | 1868.29 | 233.04 | 112.42 | 7.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295331200 |  | 100281993 |  | 6712232O |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTRQD | 2621P | CHAMBERS | 330 CHAMBERS AV | 209 | GEO | 2024-12-09 | DCOLLIN | U140273 | 2024-11-13 | 2024-12-04 | 2024-12-27 |  | DCOLLIN | 2024-12-09 | 2024-12-09 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 16 | 2 | 1522.69 | 1180.44 | 94.39 | 247.86 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24295371500 |  | 500346716 |  | 7336276N | 2410016 |  |  | 563 | EX | PAPER W/ MASTER 500527505 | 2621P | OHIO RIVER | 1022 OHIO RIVER RD APT 1 | 089 | GRE | 2024-11-14 | U123688 | U129531 | 2024-11-13 | 2024-11-27 | 2024-11-27 |  | OFFICE | 2024-11-14 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26310011 |  | 1
KY | KY - WEST | 2621 | 24295381000 |  | 100417796 |  | 6716204J |  |  |  | 565 | EX | RELIACE SERVICE LINE | 2621P | WEM | 3860 WEM DR | 067 | LEX | 2024-11-15 | UIPBOT10 | U141174 | 2024-11-13 | 2024-11-13 | 2024-11-13 |  | MCRAIG | 2024-11-14 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.2333 | 3 | 1598.41 | 1122.3 | 66.11 | 287.16 | 122.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295472600 |  | 100355784 |  | 7260276B |  |  |  | 563 | EX | 1" P LONG | 2621P | CENTRAL | 613 CENTRAL AV | 161 | MAY | 2024-11-27 | U141668 | U132627 | 2024-11-14 | 2024-11-15 | 2024-11-28 |  | SDADAMS | 2024-11-26 |  |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26320011 | 16 | 2 | 1591.3 | 1148.12 | 331.16 | 69.1 | 42.92 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295478400 |  | 100360796 |  | 6736228G |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | HUME BEDFORD | 86 HUME BEDFORD RD | 017 | PAR | 2024-11-22 | U124604 | U123688 | 2024-11-14 | 2024-12-31 |  |  | NRICHIE | 2024-11-21 | 2024-11-15 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 13.4167 | 6 | 1796.19 | 1117.04 | 129.88 | 549.27 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295501700 |  | 501364128 |  | 6724212 |  |  |  | 563 | EX | PAPER W/ 501267634 | 2600B | ELKHORN | 2344 ELKHORN RD 100 | 067 | LEX | 2024-11-14 | U125763 | U128727 | 2024-11-14 | 2024-11-27 | 2024-11-28 |  | OFFICE PER MGMNT | 2024-11-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBPEX |  | 100 | 056332B26210012 |  | 1
KY | KY - WEST | 2621 | 24295525500 |  | 501303230 |  | 16720208O |  |  |  | 563 | EX | 1" P SHORT/PRIVATE RD | 2600B | LAKE CLAIR | 609 LAKE CLAIR CT | 067 | LEX | 2024-12-06 | U123111 | U129531 | 2024-11-14 | 2024-11-15 | 2024-12-06 |  | LYN STAFFORD | 2024-12-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 5 | 1 | 4854.63 | 401.93 | 317.61 | 23.49 | 4111.6 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295533600 |  | 501292378 |  | 6684224E | 2408452 |  |  | 563 | EX | 1" P SHORT/PRMT RCVD | 2600B | LIMESTONE | 200 LIMESTONE DR | 073 | FRA | 2024-12-03 | U123111 | U129176 | 2024-11-14 | 2024-11-22 | 2024-12-09 |  | LYN STAFFORD | 2024-12-02 | 2024-12-02 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 16.5 | 2 | 4966.51 | 1326.19 | 216.18 | 77.48 | 3346.66 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24295545100 |  | 100240865 |  | 7324132E |  |  |  | 566 | EX | ABANDON SL - DEMO | 2621P | KENTUCKY | 23 KENTUCKY DR | 119 | HIN | 2025-06-12 | JCKIRK | U124420 | 2024-11-14 | 2025-05-19 | 2025-06-05 |  | JCKIRK | 2025-06-12 | 2025-05-21 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 20.2333 | 4 | 6343.99 | 1592.58 | 0 | 154.41 | 4597 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24295545200 |  | 100240867 |  | 7324132F |  |  |  | 566 | EX | ABANDON SL - DEMO | 2621P | OLD GARNER | 15 OLD GARNER RD | 119 | HIN | 2025-06-03 | JCKIRK | U124420 | 2024-11-14 | 2025-05-19 | 2025-06-05 |  | JCKIRK | 2025-06-03 | 2025-05-21 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 25.4667 | 4 | 2215.2 | 2024.7 | 0 | 190.5 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24295545500 |  | 100240963 |  | 7324132F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 880 E MAIN ST | 119 | HIN | 2025-01-31 | U130172 | U124420 | 2024-11-14 | 2027-07-27 | 2027-07-27 |  | JOHN HOWARD | 2025-01-31 | 2025-01-29 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 17.0833 | 3 | 1309.03 | 1228.2 | 0 | 80.83 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24295545900 |  | 100241218 |  | 7356256G |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | 29TH | 452 29TH ST | 019 | ASH | 2025-06-12 | U124604 | U124420 | 2024-11-14 | 2025-06-17 | 2025-07-08 |  | ABHATFIE | 2025-06-11 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 14.85 | 2 | 1139.03 | 1075.94 | 0 | 63.09 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24295546700 |  | 100241686 |  | 7352256P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CLAY | 4818 CLAY ST | 019 | ASH | 2025-02-13 | MCOLLET | U124420 | 2024-11-14 | 2025-11-06 | 2025-11-06 |  | MCOLLET | 2025-02-13 | 2025-02-07 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 15.35 | 5 | 2591.48 | 1340.05 | 45.19 | 1206.24 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24295547200 |  | 100242296 |  | 7356252H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MITCHELL | 1136 MITCHELL ST | 019 | CAT | 2025-03-31 | U124604 | U124420 | 2024-11-14 | 2025-12-31 | 2025-12-31 |  | JROGER1 | 2025-03-28 | 2025-02-28 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 16.3 | 3 | 1287.41 | 1145.24 | 45.19 | 96.98 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24295550900 |  | 100245287 |  | 7356256M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | TERRACE | 2623 TERRACE BV | 019 | ASH | 2025-04-22 | JKEENER | U124420 | 2024-11-14 | 2026-01-28 | 2026-01-28 |  | JKEENER | 2025-04-22 | 2025-04-22 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 15.9167 | 2 | 2587.73 | 1010.65 | 21.09 | 61.69 | 1494.3 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24295552900 |  | 100247281 |  | 7352256L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BEECH | 2315 BEECH ST 2 | 019 | ASH | 2025-05-19 | U123688 | U124420 | 2024-11-14 | 2025-10-09 | 2025-10-09 |  | ABHATFIE | 2025-05-16 | 2025-03-25 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 29.75 | 7 | 3805.48 | 2020.45 | 0 | 788.83 | 996.2 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24295553000 |  | 100247302 |  | 7352256L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BEECH | 2315 BEECH ST 13 | 019 | ASH | 2025-03-17 | U124604 | U124420 | 2024-11-14 | 2025-02-25 | 2025-02-25 |  | RECUMP | 2025-03-14 | 2025-02-11 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 19.35 | 5 | 1919.25 | 1361.92 | 31.41 | 525.92 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24295554300 |  | 100249504 |  | 7344264D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HIGHWAY 2565 | 2936 HIGHWAY 2565 | 127 | LOU | 2025-02-21 | MCOLLET | U124420 | 2024-11-14 | 2026-03-16 | 2026-03-16 |  | MCOLLET | 2025-02-21 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 17.85 | 2 | 2242.99 | 1595.7 | 10.01 | 637.28 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295555300 |  | 501317065 |  | 6708204F | 2074205 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | MEADOW RIDGE | 148 MEADOW RIDGE DR LT5 | 113 | NIC | 2024-11-25 | U129722 | U129531 | 2024-11-14 | 2024-11-15 | 2024-12-03 |  | DAVID YOUNG | 2024-11-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 3652.85 | 0 | 570.07 | 0 | 3082.78 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24295556300 |  | 100250614 |  | 7376184A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HALE | 165 HALE AV | 159 | LOV | 2025-03-21 | JCKIRK | U124420 | 2024-11-14 | 2026-03-13 | 2026-03-15 |  | JCKIRK | 2025-03-21 | 2025-03-21 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 16 | 2 | 1271.05 | 1200.68 | 0 | 70.37 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24295558000 |  | 100252201 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | COLDWATER | 760 COLDWATER RD | 159 | INE | 2024-12-30 | U130172 | U124420 | 2024-11-14 | 2025-09-25 | 2025-09-25 |  | J KIRK | 2024-12-24 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 6.2167 | 2 | 589.65 | 556.88 | 0 | 32.77 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24295558600 |  | 100253693 |  | 7356216D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | JEFFERSON | 316 S JEFFERSON ST | 127 | LOU | 2025-05-23 | CWHEELE | U124420 | 2024-11-14 | 2025-12-26 | 2025-12-28 |  | CWHEELE | 2025-05-23 | 2025-05-23 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 16 | 2 | 2069.36 | 1181.16 | 21.09 | 867.11 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24295561400 |  | 100257860 |  | 7348168T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CORN FORK | 2422 CORN FORK RD | 071 | LNC | 2025-03-11 | U130172 | U124420 | 2024-11-14 | 2026-11-10 | 2026-11-10 |  | B PREECE | 2025-03-11 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 8.4 | 2 | 664.44 | 627.67 | 0 | 36.77 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24295563400 |  | 100259158 |  | 7344156T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KY ROUTE 3188 | 1174 KY ROUTE 3188 | 071 | LAN | 2025-01-28 | U130172 | U124420 | 2024-11-14 | 2026-01-12 | 2026-01-12 |  | JOHN HOWARD | 2025-01-28 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.56667 | 1 | 43.44 | 40.75 | 0 | 2.69 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24295563900 |  | 100260100 |  | 7356256A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HILTON | 1512 HILTON AV | 019 | ASH | 2025-01-07 | U128523 | U124420 | 2024-11-14 | 2026-01-16 | 2026-01-18 |  | BRANDON ROBERTS | 2025-01-07 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1
KY | KY - EAST | 2633 | 24295564300 |  | 100260490 |  | 7344148T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | STUMBO HOLLOW | 1332 STUMBO HOLLOW | 071 | DRI | 2025-03-19 | U130172 | U124420 | 2024-11-14 | 2026-03-05 | 2026-03-05 |  | B PREECE | 2025-03-19 | 2025-03-19 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 8.9333 | 2 | 693.53 | 655.13 | 0 | 38.4 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24295564400 |  | 100260514 |  | 7348160T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HAUS | 352 HAUS BR | 071 | BAN | 2025-05-02 | U130172 | U124420 | 2024-11-14 | 2026-03-03 | 2026-03-03 |  | JOHN HOWARD | 2025-05-02 | 2025-05-02 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.5833 | 1 | 457.34 | 432.3 | 0 | 25.04 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24295566000 |  | 100262026 |  | 7352256H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 13TH | 1813 13TH ST | 019 | ASH | 2025-04-25 | MCOLLET | U124420 | 2024-11-14 | 2025-10-31 | 2025-11-02 |  | MCOLLET | 2025-04-25 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 9.75 | 2 | 2595.37 | 656.51 | 21.09 | 1176.13 | 741.64 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24295566400 |  | 100262374 |  | 7352256H |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | CLINTON | 2449 CLINTON ST | 019 | ASH | 2025-05-23 | ABHATFIE | U124420 | 2024-11-14 | 2025-05-07 | 2025-05-28 |  | ABHATFIE | 2025-05-23 | 2025-05-06 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 21.3167 | 5 | 1668.76 | 1577.4 | 0 | 91.36 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24295567100 |  | 100263177 |  | 7384168K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 4TH | 309 4TH ST | 195 | S W | 2025-03-03 | JCKIRK | U124420 | 2024-11-14 | 2025-10-30 | 2025-10-30 |  | JCKIRK | 2025-03-03 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 6.2667 | 2 | 489.91 | 462.77 | 0 | 27.14 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24295567200 |  | 100263185 |  | 7384168K | 2512421 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 4TH | 357 4TH ST | 195 | S W | 2025-03-27 | JCKIRK | U124420 | 2024-11-14 | 2026-05-08 | 2026-05-10 |  | JCKIRK | 2025-03-27 | 2025-03-27 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 23.1833 | 3 | 1816.11 | 1715.56 | 0 | 100.55 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24295567300 |  | 100263195 |  | 7384168K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 4TH | 316 4TH ST | 195 | S W | 2025-03-03 | JCKIRK | U124420 | 2024-11-14 | 2025-10-24 | 2025-10-26 |  | JCKIRK | 2025-03-03 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 18.45 | 3 | 1577.75 | 1372.23 | 125.06 | 80.46 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24295568400 |  | 100263686 |  | 7352260O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CENTRAL | 425 W CENTRAL AV | 019 | ASH | 2025-04-28 | U123688 | U124420 | 2024-11-14 | 2026-02-24 | 2026-02-24 |  | RECUMP | 2025-04-25 | 2025-02-10 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 26.4667 | 6 | 2332.5 | 1776.87 | 21.09 | 534.54 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24295568500 |  | 100263861 |  | 7352260O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HOODS CREEK | 1605 HOODS CREEK PK | 019 | ASH | 2025-02-14 | MCOLLET | U124420 | 2024-11-14 | 2025-11-10 | 2025-11-10 |  | MCOLLET | 2025-02-14 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 10.7667 | 2 | 3196.03 | 954.75 | 35.11 | 711.87 | 1494.3 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24295570500 |  | 100266161 |  | 7380144T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GRAPEVINE | 16722 GRAPEVINE RD | 195 | PHY | 2025-05-05 | U130172 | U124420 | 2024-11-14 | 2026-02-05 | 2026-02-05 |  | JOHN HOWARD | 2025-05-05 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.0833 | 1 | 420.27 | 397.26 | 0 | 23.01 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24295570800 |  | 100266361 |  | 7380144T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GRAPEVINE | 16484 GRAPEVINE RD | 195 | PHY | 2025-01-20 | U130172 | U124420 | 2024-11-14 | 2025-11-11 | 2025-11-11 |  | J HOWARD | 2025-01-20 | 2025-01-17 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 8 | 1 | 609.57 | 571.94 | 0 | 37.63 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24295572100 |  | 100268664 |  | 7352156L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LOWER HOLLOW | 213 LOWER HOLLOW RD | 071 | BET | 2025-03-14 | JCKIRK | U124420 | 2024-11-14 | 2026-03-18 | 2026-03-18 |  | JCKIRK | 2025-03-14 | 2025-02-27 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 14 | 3 | 925.31 | 874.07 | 0 | 51.24 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24295572200 |  | 100268792 |  | 7352156L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FOUNTAIN | 26 FOUNTAIN LN | 071 | BET | 2025-04-23 | U124604 | U124420 | 2024-11-14 | 2026-12-15 | 2026-12-15 |  | BPREECE | 2025-04-21 | 2025-02-27 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 23.9667 | 4 | 5891.68 | 3217.31 | 0 | 192.12 | 2482.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295572300 |  | 100268880 |  | 6736252N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ELMARCH | 137 N ELMARCH AV | 097 | CYN | 2025-01-30 | U124604 | U124420 | 2024-11-14 | 2026-11-09 | 2026-11-09 |  | NRICHIE | 2025-01-29 | 2025-01-20 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.6 | 4 | 1628.66 | 420.57 | 17.88 | 40.55 | 1149.66 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295572700 |  | 100268924 |  | 6736252M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WILSON | 236 WILSON AV | 097 | CYN | 2025-01-24 | NRICHIE | U124420 | 2024-11-14 | 2025-12-03 | 2025-12-03 |  | NRICHIE | 2025-01-24 | 2025-01-14 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.0667 | 5 | 2198.23 | 607.7 | 39.7 | 50.95 | 1499.88 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295573400 |  | 100269470 |  | 6732252P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LOCUST | 419 N LOCUST ST | 097 | CYN | 2025-01-30 | U124604 | U124420 | 2024-11-14 | 2025-12-29 | 2025-12-29 |  | NRICHIE | 2025-01-29 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 6 | 2 | 1930.96 | 455.57 | 17.88 | 29.99 | 1427.52 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295573700 |  | 100269919 |  | 6732252P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BROADWAY | 303 BROADWAY AV | 097 | CYN | 2025-04-15 | U930915 | U124420 | 2024-11-14 | 2026-03-16 | 2026-03-16 |  | NRICHIE | 2025-04-15 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.2 | 2 | 1948.52 | 347.21 | 47.24 | 21.19 | 1532.88 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295574300 |  | 100271101 |  | NEW |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PEA RIDGE | 295 PEA RIDGE | 023 | AUG | 2025-05-06 | U930915 | U124420 | 2024-11-14 | 2026-05-22 | 2026-05-24 |  | SDADAMS | 2025-05-05 | 2025-04-29 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 2.15 | 3 | 160.1 | 151.31 | 0 | 8.79 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295574600 |  | 100271570 |  | 6736252N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ELMARCH | 144 N ELMARCH AV | 097 | CYN | 2025-01-30 | U930915 | U124420 | 2024-11-14 | 2026-02-05 | 2026-02-05 |  | NRICHIE | 2025-01-29 | 2025-01-20 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9.8667 | 4 | 1627.86 | 748.67 | 39.7 | 73.05 | 766.44 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295574700 |  | 100271623 |  | 6684228K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 2ND | 124 E 2ND ST | 073 | FRA | 2025-03-05 | U930915 | U124420 | 2024-11-14 | 2026-05-08 | 2026-05-10 |  | ATWILLI | 2025-03-04 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 12.6 | 4 | 1416.6 | 923.8 | 38.16 | 454.64 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295574800 |  | 100271993 |  | 6684228K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 4TH | 314 E 4TH ST | 073 | FRA | 2025-03-14 | ATWILLI | U124420 | 2024-11-14 | 2026-09-17 | 2026-09-17 |  | ATWILLI | 2025-03-14 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 12 | 2 | 2766.95 | 861.53 | 160.06 | 50.48 | 1694.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295575400 |  | 100274001 |  | 6684224A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LOUISVILLE | 954 LOUISVILLE RD | 073 | FRA | 2025-04-24 | U123688 | U124420 | 2024-11-14 | 2026-07-10 | 2026-07-12 |  | BSEXTON | 2025-04-08 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 10.4167 | 3 | 1292.11 | 645.2 | 0 | 39.41 | 607.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295575800 |  | 100274803 |  | 6684228J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 2ND | 215 W 2ND ST | 073 | FRA | 2025-02-06 | U124604 | U124420 | 2024-11-14 | 2026-10-12 | 2026-10-12 |  | EFGOINS | 2025-02-05 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 4.1 | 3 | 1623.38 | 316.65 | 0 | 94.07 | 1212.66 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295576000 |  | 100274935 |  | 6684228K | 2074677 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 2ND | 106 W 2ND ST | 073 | FRA | 2025-03-10 | ATWILLI | U124420 | 2024-11-14 | 2026-11-02 | 2026-11-02 |  | ATWILLI | 2025-03-10 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 10.3667 | 2 | 1943.61 | 1322.8 | 38.16 | 582.65 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295576100 |  | 100275389 |  | 6684228F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BENSON | 778 BENSON AV | 073 | FRA | 2025-02-27 | ATWILLI | U124420 | 2024-11-14 | 2027-07-22 | 2027-07-22 |  | ATWILLI | 2025-02-27 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 1.3 | 2 | 789.77 | 97.93 | 0 | 43.9 | 647.94 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295576200 |  | 100275423 |  | 6684228F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BENSON | 716 BENSON AV | 073 | FRA | 2025-02-27 | ATWILLI | U124420 | 2024-11-14 | 2027-04-02 | 2027-04-04 |  | ATWILLI | 2025-02-27 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.066667 | 2 | 761.82 | 7.28 | 17.88 | 3.22 | 733.44 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295576300 |  | 100275427 |  | 6684228F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BENSON | 712 BENSON AV | 073 | FRA | 2025-02-27 | U930915 | U124420 | 2024-11-14 | 2026-07-31 | 2026-08-02 |  | ATWILLI | 2025-02-27 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 21.25 | 3 | 3624.68 | 1530.13 | 39.7 | 496.41 | 1558.44 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295576400 |  | 100275484 |  | 6684228F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WILSON | 719 WILSON ST | 073 | FRA | 2025-02-07 | DCOLLIN | U124420 | 2024-11-14 | 2026-01-15 | 2026-01-15 |  | DCOLLIN | 2025-02-07 | 2025-02-07 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 16.5 | 3 | 2316.88 | 1323.74 | 43.63 | 229.51 | 720 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295576500 |  | 100275520 |  | 6684228F |  |  |  | 566 | CO | ABANDON SL/IDLE-INACTIVE | 2621P | BRAWNER | 722 BRAWNER ST | 073 | FRA | 2025-06-18 |  | U124420 | 2024-11-14 | 2027-06-21 | 2027-06-21 |  | RJCRAWF | 2025-06-18 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 12.5667 | 2 | 1451.59 | 913.94 | 0 | 537.65 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295576600 |  | 100275524 |  | 6684228F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CLINE | 731 CLINE ST | 073 | FRA | 2025-02-07 | U930915 | U124420 | 2024-11-14 | 2025-11-26 | 2025-11-30 |  | EFGOINS | 2025-02-07 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 15.3 | 2 | 1406.31 | 1147.21 | 0 | 259.1 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295576700 |  | 100275614 |  | 6684228F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BRAWNER | 828 BRAWNER ST | 073 | FRA | 2025-06-19 | U124604 | U124420 | 2024-11-14 | 2026-11-10 | 2026-11-10 |  | RJCRAWF | 2025-06-18 | 2025-06-06 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 2.9 | 4 | 2522.31 | 218.67 | 39.82 | 82.32 | 2181.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295577700 |  | 100276799 |  | 6684228D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HENRY | 314 HENRY ST | 073 | FRA | 2025-03-04 | U124604 | U124420 | 2024-11-14 | 2025-10-30 | 2025-10-30 |  | ATWILLI | 2025-02-28 | 2024-12-09 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 17 | 6 | 4214.91 | 1174.95 | 38.16 | 257.76 | 2744.04 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295578200 |  | 100277146 |  | 6684228H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE/POS | 2621P | HOLMES | 751 HOLMES ST | 073 | FRA | 2025-03-11 | ATWILLI | U124420 | 2024-11-14 | 2026-09-04 | 2026-09-07 |  | ATWILLI | 2025-03-11 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 9.8 | 2 | 1346.86 | 716.21 | 38.16 | 352.49 | 240 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295578300 |  | 100277287 |  | 6684228G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HOLMES | 221 HOLMES ST | 073 | FRA | 2025-03-11 | ATWILLI | U124420 | 2024-11-14 | 2027-03-05 | 2027-03-07 |  | ATWILLI | 2025-03-11 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 6.2 | 2 | 939.15 | 453.13 | 27.89 | 218.13 | 240 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295578400 |  | 100277470 |  | 6684228K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 258 E MAIN ST | 073 | FRA | 2025-02-24 | DCOLLIN | U124420 | 2024-11-14 | 2026-07-27 | 2026-07-27 |  | DCOLLIN | 2025-02-24 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 10.4 | 3 | 1349.45 | 811.56 | 0 | 110.39 | 427.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295579600 |  | 100279023 |  | 6688228F |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTRQD | 2621P | ELIZABETH | 131 ELIZABETH ST | 073 | FRA | 2025-01-14 | U124604 | U124420 | 2024-11-14 | 2025-01-21 | 2025-02-11 |  | EFGOINS | 2025-01-13 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 7.5 | 2 | 518.28 | 486.27 | 0 | 32.01 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295580400 |  | 100281071 |  | 6684228K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 139 E MAIN ST | 073 | FRA | 2025-02-24 | DCOLLIN | U124420 | 2024-11-14 | 2026-07-13 | 2026-07-13 |  | DCOLLIN | 2025-02-24 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 23.95 | 3 | 2137.8 | 1881.72 | 0 | 256.08 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295580900 |  | 100281834 |  | 6712232N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HARMON | 328 HARMON CT | 209 | GEO | 2025-02-24 | U124604 | U124420 | 2024-11-14 | 2026-03-09 | 2026-03-09 |  | DCOLLIN | 2025-02-21 | 2025-01-20 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 26.6667 | 6 | 4015.99 | 1955.47 | 0 | 380.52 | 1680 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295581300 |  | 100282319 |  | 6712232N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PRATHER | 120 PRATHER BV | 209 | GEO | 2025-01-23 | DCOLLIN | U124420 | 2024-11-14 | 2026-02-20 | 2026-02-22 |  | DCOLLIN | 2025-01-23 | 2025-01-10 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 31.1667 | 4 | 2724.61 | 2076.72 | 0 | 327.89 | 320 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295581500 |  | 100282632 |  | 6712228B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | COLLEGE | 111 E COLLEGE ST | 209 | GEO | 2025-05-15 | DCOLLIN | U124420 | 2024-11-14 | 2026-05-05 | 2026-05-05 |  | DCOLLIN | 2025-05-15 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 14.4333 | 4 | 1673.87 | 1204.11 | 15.08 | 454.68 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295581800 |  | 100283026 |  | 6712228G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MILITARY | 610 MILITARY ST | 209 | GEO | 2025-01-23 | DCOLLIN | U124420 | 2024-11-14 | 2025-11-10 | 2025-11-10 |  | DCOLLIN | 2025-01-23 | 2024-12-06 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 10.5167 | 5 | 1312.65 | 792.15 | 0 | 240.5 | 280 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295581900 |  | 100283092 |  | 6712228G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OLD LEMONS MIL | 515 OLD LEMONS MIL RD | 209 | GEO | 2025-01-30 | DCOLLIN | U124420 | 2024-11-14 | 2026-03-09 | 2026-03-09 |  | DCOLLIN | 2025-01-30 | 2025-01-29 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 18.8 | 4 | 1517.43 | 1270.02 | 0 | 247.41 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295582100 |  | 100283651 |  | V90907 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BROADWAY | 501 S BROADWAY ST | 209 | GEO | 2025-02-25 | DCOLLIN | U124420 | 2024-11-14 | 2025-12-17 | 2025-12-17 |  | DCOLLIN | 2025-02-25 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 15.55 | 3 | 3018.75 | 1242.23 | 95.31 | 166.71 | 1514.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295582300 |  | 100283954 |  | 6712228B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | COLLEGE | 109 W COLLEGE ST | 209 | GEO | 2025-05-15 | DCOLLIN | U124420 | 2024-11-14 | 2026-05-01 | 2026-05-03 |  | DCOLLIN | 2025-05-15 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 16.8333 | 5 | 1712.37 | 1408.6 | 15.08 | 288.69 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295582500 |  | 100284018 |  | 6712228J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LEXINGTON | 1171 LEXINGTON RD | 209 | GEO | 2025-02-27 | DCOLLIN | U124420 | 2024-11-14 | 2027-09-03 | 2027-09-06 |  | DCOLLIN | 2025-02-27 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 7.4667 | 2 | 1155.86 | 981.81 | 0 | 174.05 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295582700 |  | 100284457 |  | 6764176N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RIVERVIEW | 90 RIVERVIEW RD | 065 | IRV | 2025-02-11 | U930915 | U124420 | 2024-11-14 | 2025-12-29 | 2025-12-29 |  | DENNING | 2025-02-10 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 23.2333 | 3 | 2288.4 | 2128.61 | 60.08 | 99.71 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295585800 |  | 100285880 |  | 6764176P | 1855043 |  |  | 566 | EX | ABANDON SL - SOII/LEGACY | 2621P | TURNER | 318 TURNER AV | 065 | IRV | 2025-05-08 | U124604 | U124420 | 2024-11-14 | 2025-06-10 | 2025-06-10 |  | LCLARK | 2025-05-07 | 2025-05-06 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10.3667 | 4 | 4751.24 | 828.06 | 17.9 | 47.98 | 3857.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295585900 |  | 100285921 |  | 6764176P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HOOD | 215 HOOD AV 12 | 065 | IRV | 2025-01-16 | DENNING | U124420 | 2024-11-14 | 2025-12-15 | 2025-12-15 |  | DENNING | 2025-01-16 | 2025-01-10 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 21.3333 | 6 | 5743.91 | 1595.19 | 142.02 | 104.95 | 3901.75 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295586100 |  | 100285942 |  | 6764176P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MADISON | 142 S MADISON AV | 065 | IRV | 2025-03-21 | DENNING | U124420 | 2024-11-14 | 2025-12-11 | 2025-12-11 |  | DENNING | 2025-03-21 | 2025-01-10 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 22.9333 | 4 | 2796.81 | 1816.18 | 35.11 | 945.52 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295586900 |  | 100286241 |  | 6764172G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FRONT | 115 FRONT ST | 065 | IRV | 2025-03-10 | U930915 | U124420 | 2024-11-14 | 2026-02-20 | 2026-02-22 |  | DENNING | 2025-03-07 | 2025-02-19 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 12.9167 | 3 | 1233.08 | 1041.22 | 131.22 | 60.64 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295587400 |  | 100286820 |  | 6720212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DEVONIA | 118 DEVONIA AV | 067 | LEX | 2025-02-05 | U124604 | U124420 | 2024-11-14 | 2027-06-15 | 2027-06-15 |  | TROE | 2025-02-04 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.7 | 3 | 1084.94 | 1036.35 | 0 | 48.59 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295587500 |  | 100286846 |  | 6720212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DEVONIA | 226 DEVONIA AV | 067 | LEX | 2025-02-07 | TROE | U124420 | 2024-11-14 | 2027-06-17 | 2027-06-17 |  | TROE | 2025-02-07 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.8 | 2 | 181.58 | 173.43 | 0 | 8.15 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295587700 |  | 100287505 |  | 6720212G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DARLEY | 1044 DARLEY DR | 067 | LEX | 2025-01-17 | U123688 | U124420 | 2024-11-14 | 2025-11-07 | 2025-11-09 |  | LSTANFI | 2025-01-13 | 2025-01-03 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 21.7 | 5 | 1542.4 | 1248.88 | 82.78 | 210.74 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295587900 |  | 100287614 |  | 6720212G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MARCELLUS | 1011 MARCELLUS DR | 067 | LEX | 2025-04-18 | U930915 | U124420 | 2024-11-14 | 2026-07-08 | 2026-07-08 |  | BDARNELL | 2025-04-17 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 21.75 | 3 | 2277.09 | 1209.67 | 15.08 | 272.34 | 780 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295588100 |  | 100287726 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HIGHLAND PARK | 1031 HIGHLAND PARK DR | 067 | LEX | 2025-02-17 | LSTANFI | U124420 | 2024-11-14 | 2026-07-06 | 2026-07-06 |  | LSTANFI | 2025-02-17 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.6333 | 2 | 365.04 | 313.12 | 19.42 | 32.5 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295588200 |  | 100287830 |  | 6720212G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SHAWNEE | 441 SHAWNEE AV | 067 | LEX | 2025-01-29 | LSTANFI | U124420 | 2024-11-14 | 2027-03-16 | 2027-03-16 |  | LSTANFI | 2025-01-29 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.0167 | 3 | 764.15 | 340.11 | 38.16 | 25.88 | 360 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295588300 |  | 100287844 |  | 6720212G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SHAWNEE | 404 SHAWNEE AV | 067 | LEX | 2025-01-30 | U124604 | U124420 | 2024-11-14 | 2027-03-10 | 2027-03-10 |  | LSTANFI | 2025-01-29 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.5 | 3 | 1585.39 | 367.4 | 17.88 | 55.29 | 1144.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295588500 |  | 100287853 |  | 6720212G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SHAWNEE | 426 SHAWNEE AV | 067 | LEX | 2025-01-29 | LSTANFI | U124420 | 2024-11-14 | 2027-03-08 | 2027-03-08 |  | LSTANFI | 2025-01-29 | 2025-01-29 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.8833 | 3 | 586.65 | 297.89 | 38.16 | 30.6 | 220 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295588700 |  | 100287945 |  | 6720212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LOCUST | 404 LOCUST AV | 067 | LEX | 2025-03-06 | U930915 | U124420 | 2024-11-14 | 2026-03-17 | 2026-03-17 |  | SSHIMFE | 2025-03-06 | 2025-03-04 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 14.3333 | 5 | 874.52 | 826.09 | 0 | 48.43 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295588800 |  | 100288046 |  | 6720212C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BRYAN | 1404 BRYAN AV | 067 | LEX | 2024-12-24 | U141668 | U124420 | 2024-11-14 | 2027-07-28 | 2027-07-28 |  | LSTANFI | 2024-12-23 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.7667 | 2 | 284.61 | 213.02 | 1.47 | 70.12 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295588900 |  | 100288048 |  | 6720212C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BRYAN | 1408 BRYAN AV | 067 | LEX | 2024-12-24 | U141668 | U124420 | 2024-11-14 | 2027-03-16 | 2027-03-16 |  | LSTANFI | 2024-12-23 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.1667 | 2 | 222.61 | 166.37 | 1.47 | 54.77 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295589200 |  | 100288823 |  | 6724212A | 1855043 |  |  | 566 | EX | ABANDON SL - SOII/LEGACY | 2621P | SAINT ANTHONY | 649 SAINT ANTHONY DR | 067 | LEX | 2025-04-02 | LSTANFI | U124420 | 2024-11-14 | 2025-05-23 | 2025-05-25 |  | LSTANFI | 2025-04-02 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.5333 | 2 | 638.05 | 529.31 | 0 | 108.74 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295589300 |  | 100289048 |  | 6720212D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MOSS | 477 MOSS DR | 067 | LEX | 2025-04-14 | LSTANFI | U124420 | 2024-11-14 | 2026-04-02 | 2026-04-02 |  | LSTANFI | 2025-04-14 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10.3 | 3 | 939.25 | 554.04 | 34.81 | 118.68 | 231.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295589600 |  | 100290050 |  | 6720212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CARLISLE | 235 CARLISLE AV | 067 | LEX | 2025-02-07 | TROE | U124420 | 2024-11-14 | 2027-01-12 | 2027-01-12 |  | TROE | 2025-02-07 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.1667 | 2 | 236.7 | 226.09 | 0 | 10.61 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295589700 |  | 100290149 |  | 6720212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BLUE GRASS | 106 BLUE GRASS AV | 067 | LEX | 2025-03-06 | TROE | U124420 | 2024-11-14 | 2027-06-10 | 2027-06-10 |  | TROE | 2025-03-06 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11 | 3 | 725.24 | 653.95 | 32.95 | 38.34 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295589800 |  | 100290152 |  | 6720212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BLUE GRASS | 110 BLUE GRASS AV | 067 | LEX | 2025-03-04 | TROE | U124420 | 2024-11-14 | 2027-09-09 | 2027-09-09 |  | TROE | 2025-03-04 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.1833 | 3 | 552.39 | 498.57 | 24.58 | 29.24 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295589900 |  | 100290185 |  | 6720212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | EDGELAWN | 1402 EDGELAWN AV | 067 | LEX | 2024-12-05 | U930915 | U124420 | 2024-11-14 | 2025-12-10 | 2025-12-10 |  | HSTANFI | 2024-12-05 | 2024-12-04 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.2333 | 3 | 885.83 | 816.23 | 21.9 | 47.7 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295590000 |  | 100290257 |  | 6720212C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HIGHLAWN | 1442 HIGHLAWN AV | 067 | LEX | 2025-03-06 | TROE | U124420 | 2024-11-14 | 2026-12-01 | 2026-12-01 |  | TROE | 2025-03-06 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.75 | 3 | 892.08 | 828.89 | 15.07 | 48.12 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295590100 |  | 100290296 |  | 6720212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BLUE GRASS | 207 BLUE GRASS AV | 067 | LEX | 2025-03-04 | TROE | U124420 | 2024-11-14 | 2027-02-25 | 2027-02-25 |  | TROE | 2025-03-04 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.45 | 3 | 720.4 | 657.31 | 24.58 | 38.51 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295590200 |  | 100290393 |  | 6720212C | 9936141 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NEW CIRCLE | 235 E NEW CIRCLE RD | 067 | LEX | 2025-02-18 | HSTANFI | U124420 | 2024-11-14 | 2026-05-15 | 2026-05-17 |  | HSTANFI | 2025-02-18 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.3667 | 3 | 2483.62 | 740.64 | 6.62 | 34.7 | 1701.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295590300 |  | 100290542 |  | 6720216L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OLD PARIS | 2080 OLD PARIS RD | 067 | LEX | 2024-12-26 | LSTANFI | U124420 | 2024-11-14 | 2027-02-19 | 2027-02-21 |  | LSTANFI | 2024-12-26 | 2024-12-26 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 21.6833 | 4 | 3146.51 | 1650.92 | 0 | 835.59 | 660 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295590400 |  | 100290581 |  | 6720216P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OLD PARIS | 2005 OLD PARIS RD | 067 | LEX | 2025-02-18 | TROE | U124420 | 2024-11-14 | 2027-05-17 | 2027-05-17 |  | TROE | 2025-02-18 | 2024-12-26 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 27.4833 | 9 | 3132.36 | 1843.03 | 15.07 | 94.6 | 1179.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295590500 |  | 100290583 |  | 6720216P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OLD PARIS | 1975 OLD PARIS RD | 067 | LEX | 2025-02-12 | U930915 | U124420 | 2024-11-14 | 2027-05-18 | 2027-05-18 |  | HSTANFI | 2025-02-12 | 2025-01-03 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.4 | 5 | 2142.96 | 722.78 | 21.82 | 38.36 | 1360 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295590700 |  | 100290661 |  | 6720212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BROADVIEW | 241 BROADVIEW DR | 067 | LEX | 2025-03-27 | U930915 | U124420 | 2024-11-14 | 2025-12-11 | 2025-12-11 |  | HSTANFI | 2025-03-27 | 2025-01-03 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.9 | 4 | 509.21 | 474.52 | 6.62 | 28.07 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295590900 |  | 100290812 |  | 6720212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FAIRLAWN | 144 FAIRLAWN AV | 067 | LEX | 2025-02-06 | U124604 | U124420 | 2024-11-14 | 2027-10-21 | 2027-10-21 |  | TROE | 2025-02-05 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 23.4 | 3 | 1621.04 | 1548.51 | 0 | 72.53 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295591000 |  | 100291032 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DAKOTA | 714 DAKOTA ST | 067 | LEX | 2025-06-18 | HSTANFI | U124420 | 2024-11-14 | 2027-03-29 | 2027-03-29 |  | HSTANFI | 2025-06-18 | 2025-06-18 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.5 | 2 | 2173.35 | 536.11 | 21.92 | 31.44 | 1583.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295591100 |  | 100291265 |  | 6720216H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KINGSTON | 609 KINGSTON RD | 067 | LEX | 2025-01-30 | U124604 | U124420 | 2024-11-14 | 2026-04-24 | 2026-04-26 |  | HSTANFI | 2025-01-29 | 2025-01-03 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 14.15 | 4 | 1187.73 | 831.19 | 21.82 | 54.72 | 280 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295591200 |  | 100291786 |  | 6720216K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BURGOYNE | 729 BURGOYNE CT | 067 | LEX | 2025-05-23 | STGOFF | U124420 | 2024-11-14 | 2027-04-19 | 2027-04-19 |  | STGOFF | 2025-05-23 | 2025-01-31 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.6333 | 8 | 2205.62 | 915.63 | 18.63 | 55.7 | 1215.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295591400 |  | 100292233 |  | 6720216K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | JUDY | 574 JUDY LN | 067 | LEX | 2025-02-24 | U124604 | U124420 | 2024-11-14 | 2026-04-24 | 2026-04-26 |  | HSTANFI | 2025-02-21 | 2025-01-22 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 31.6167 | 10 | 2934.65 | 2067.81 | 0 | 101.9 | 764.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295591500 |  | 100292341 |  | 6720216O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NORTHRIDGE | 408 NORTHRIDGE DR | 067 | LEX | 2025-06-13 | TROE | U124420 | 2024-11-14 | 2027-06-09 | 2027-06-09 |  | TROE | 2025-06-13 | 2025-05-30 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.9333 | 5 | 1337.93 | 1049.52 | 0 | 288.41 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295591800 |  | 100292893 |  | 6720212J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RUSSELL CAVE | 1782 RUSSELL CAVE RD | 067 | LEX | 2025-04-09 | U930915 | U124420 | 2024-11-14 | 2026-08-05 | 2026-08-05 |  | TROE | 2025-04-09 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 17.1167 | 3 | 1724.18 | 911.03 | 15.08 | 55.57 | 742.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295591900 |  | 100293092 |  | 6720216K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WELLS | 623 WELLS CT | 067 | LEX | 2025-01-15 | U930915 | U124420 | 2024-11-14 | 2026-06-08 | 2026-06-08 |  | TROE | 2025-01-14 | 2025-01-14 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.9 | 3 | 1043.82 | 979.38 | 0 | 64.44 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295592200 |  | 100293409 |  | 6720216J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ASBURY | 501 ASBURY LN | 067 | LEX | 2025-03-28 | U124604 | U124420 | 2024-11-14 | 2026-07-01 | 2026-07-01 |  | HSTANFI | 2025-03-27 | 2025-03-14 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.3 | 3 | 487.04 | 433.42 | 28.21 | 25.41 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295592300 |  | 100293983 |  | 6720212A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PRICE | 712 PRICE AV | 067 | LEX | 2025-06-19 | U930915 | U124420 | 2024-11-14 | 2027-04-23 | 2027-04-25 |  | JGILES | 2025-06-19 | 2025-06-19 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 21.6167 | 3 | 1294.84 | 1223.12 | 0 | 71.72 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295592400 |  | 100294012 |  | 6720212A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BELLAIRE | 704 BELLAIRE AV | 067 | LEX | 2025-03-07 | U930915 | U124420 | 2024-11-14 | 2025-12-30 | 2025-12-30 |  | TROE | 2025-03-07 | 2024-12-09 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 23.9333 | 6 | 1647.13 | 1541.6 | 15.07 | 90.46 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295592500 |  | 100294489 |  | 6716212E |  |  |  | 566 | EX | ABANDON SL- CONVRT/CUSTRQD | 2621P | UPPER | 566 N UPPER ST | 067 | LEX | 2025-05-16 | TROE | U124420 | 2024-11-14 | 2025-05-06 | 2025-05-27 |  | TROE | 2025-05-16 | 2025-05-02 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 25.75 | 6 | 1812.18 | 1372.69 | 0 | 79.49 | 360 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295592700 |  | 100294606 |  | 6716212H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WILLY | 478 WILLY ST | 067 | LEX | 2025-02-18 | MCRAIG | U124420 | 2024-11-14 | 2026-01-15 | 2026-01-15 |  | MCRAIG | 2025-02-18 | 2025-01-31 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 14.8833 | 3 | 1248.72 | 894.79 | 39.7 | 314.23 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295592900 |  | 100294994 |  | 6716212H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BROADWAY | 426 N BROADWAY ST 1-1FFT | 067 | LEX | 2025-04-14 | U930915 | U124420 | 2024-11-14 | 2026-06-15 | 2026-06-15 |  | HSTANFI | 2025-04-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.6 | 3 | 690.34 | 613.11 | 39.82 | 37.41 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295593000 |  | 100295224 |  | 6716216P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HASKINS | 557 HASKINS DR | 067 | LEX | 2025-04-24 | DMEDLEY | U124420 | 2024-11-14 | 2026-12-01 | 2026-12-01 |  | DMEDLEY | 2025-04-24 | 2025-04-21 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.8833 | 6 | 1077.18 | 770.11 | 0 | 307.07 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295593100 |  | 100295442 |  | 6716212D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ASH | 518 ASH ST | 067 | LEX | 2024-12-26 | U930915 | U124420 | 2024-11-14 | 2027-07-02 | 2027-07-05 |  | MCRAIG | 2024-12-26 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.3 | 2 | 580.69 | 383.78 | 39.78 | 157.13 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295593200 |  | 100295459 |  | 6716212D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ASH | 566 ASH ST | 067 | LEX | 2024-12-26 | U930915 | U124420 | 2024-11-14 | 2026-03-05 | 2026-03-05 |  | MCRAIG | 2024-12-26 | 2024-12-26 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10.1167 | 2 | 1326.33 | 754.18 | 39.78 | 532.37 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295593300 |  | 100295674 |  | 6716216K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BOXWOOD | 930 BOXWOOD CT | 067 | LEX | 2025-01-03 | MCRAIG | U124420 | 2024-11-14 | 2027-06-08 | 2027-06-08 |  | MCRAIG | 2025-01-03 | 2025-01-02 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 26.5 | 5 | 1623.89 | 1324.68 | 17.88 | 281.33 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295593400 |  | 100295678 |  | 6716216K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BOXWOOD | 914 BOXWOOD CT | 067 | LEX | 2025-01-03 | U124604 | U124420 | 2024-11-14 | 2026-03-10 | 2026-03-10 |  | JBURFOR | 2025-01-02 | 2024-12-31 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.7667 | 4 | 1054.43 | 972.92 | 17.88 | 63.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295593500 |  | 100295734 |  | 6716216G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BIRCH | 1074 BIRCH DR | 067 | LEX | 2024-12-30 | MCRAIG | U124420 | 2024-11-14 | 2026-02-25 | 2026-02-25 |  | MCRAIG | 2024-12-30 | 2024-12-30 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.9333 | 5 | 1828.8 | 1070.36 | 182.35 | 576.09 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295593700 |  | 100296268 |  | 6716216O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | EFFIE | 934 EFFIE RD | 067 | LEX | 2025-05-05 | U930915 | U124420 | 2024-11-14 | 2026-07-15 | 2026-07-15 |  | MCRAIG | 2025-05-02 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.2 | 3 | 1654.31 | 875.68 | 39.82 | 738.81 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295594200 |  | 100296826 |  | 6716212C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ASH | 438 ASH ST | 067 | LEX | 2024-12-27 | U930915 | U124420 | 2024-11-14 | 2026-05-08 | 2026-05-10 |  | MCRAIG | 2024-12-27 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11 | 2 | 1326.93 | 808.05 | 39.78 | 479.1 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295594400 |  | 100297012 |  | 6716212C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CHARLES | 944 CHARLES AV | 067 | LEX | 2025-02-13 | DJOHNSON | U124420 | 2024-11-14 | 2027-08-03 | 2027-08-03 |  | DJOHNSON | 2025-02-13 | 2025-02-12 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.7833 | 4 | 702.56 | 548.99 | 39.7 | 113.87 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295594500 |  | 100297014 |  | 6716212C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CHARLES | 932 CHARLES AV | 067 | LEX | 2025-02-13 | JGILES | U124420 | 2024-11-14 | 2027-03-30 | 2027-03-30 |  | JGILES | 2025-02-13 | 2025-02-12 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.4167 | 4 | 1017.85 | 753.1 | 39.7 | 225.05 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295595100 |  | 100297453 |  | 6716212H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | JEFFERSON | 318 JEFFERSON ST | 067 | LEX | 2025-05-28 | U124604 | U124420 | 2024-11-14 | 2026-11-09 | 2026-11-09 |  | JOCHOA | 2025-05-27 | 2025-05-15 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 21.75 | 4 | 2049.52 | 1332.5 | 39.82 | 77.2 | 600 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295595200 |  | 100297567 |  | 6716212H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 3RD | 604 W 3RD ST | 067 | LEX | 2025-05-20 | U930915 | U124420 | 2024-11-14 | 2025-05-20 | 2026-09-14 |  | DMEDLEY | 2025-05-20 | 2025-05-09 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 17.65 | 6 | 1365.26 | 1083.92 | 21.92 | 259.42 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295595300 |  | 100297931 |  | 6716212H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OLD GEORGETOWN | 219 OLD GEORGETOWN ST | 067 | LEX | 2025-06-04 | U930915 | U124420 | 2024-11-14 | 2026-06-03 | 2026-06-03 |  | KOBRYAN | 2025-06-04 | 2025-04-01 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.9333 | 5 | 411.99 | 388.91 | 0 | 23.08 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295595500 |  | 100298325 |  | 6716212H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SHORT | 641 W SHORT ST | 067 | LEX | 2025-06-05 | DMEDLEY | U124420 | 2024-11-14 | 2026-06-30 | 2026-06-30 |  | DMEDLEY | 2025-06-05 | 2025-05-23 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.4 | 3 | 1353.08 | 1032.69 | 21.92 | 298.47 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295595600 |  | 100298343 |  | 6716212H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OLD GEORGETOWN | 195 OLD GEORGETOWN ST | 067 | LEX | 2025-04-25 | U930915 | U124420 | 2024-11-14 | 2026-06-09 | 2026-06-09 |  | KOBRYAN | 2025-04-24 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.5333 | 2 | 443.31 | 417.81 | 0 | 25.5 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295595700 |  | 100298774 |  | 6716216O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CRANBERRY | 309 CRANBERRY ST | 067 | LEX | 2025-05-26 | U930915 | U124420 | 2024-11-14 | 2026-09-23 | 2026-09-23 |  | JOCHOA | 2025-05-23 | 2025-05-23 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.85 | 3 | 1139.63 | 1054.54 | 24.01 | 61.08 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295595800 |  | 100298858 |  | 6716216O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | EMBASSY | 224 EMBASSY DR | 067 | LEX | 2025-06-09 | U930915 | U124420 | 2024-11-14 | 2027-04-14 | 2027-04-14 |  | JGILES | 2025-06-09 | 2025-06-09 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.7167 | 3 | 1068.59 | 751.39 | 17.9 | 299.3 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295596000 |  | 100299274 |  | 6716216N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BOILING SPRING | 224 BOILING SPRING DR | 067 | LEX | 2025-01-31 | MCRAIG | U124420 | 2024-11-14 | 2026-03-11 | 2026-03-11 |  | MCRAIG | 2025-01-31 | 2025-01-29 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 20.4 | 4 | 1481.69 | 1083.98 | 39.7 | 358.01 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295596100 |  | 100299699 |  | 6716212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LISLE INDUSTRI | 395 LISLE INDUSTRI AV | 067 | LEX | 2025-03-28 | U124604 | U124420 | 2024-11-14 | 2026-04-22 | 2026-04-22 |  | DMEDLEY | 2025-03-27 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 25.1333 | 4 | 1955.71 | 1379.37 | 21.82 | 554.52 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295596400 |  | 100299991 |  | 6716212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | THOMPSON | 123 THOMPSON RD | 067 | LEX | 2025-02-17 | U124604 | U124420 | 2024-11-14 | 2027-08-24 | 2027-08-24 |  | WBURGESS | 2025-02-14 | 2025-02-14 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 24 | 3 | 1598.71 | 1527.18 | 0 | 71.53 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295596600 |  | 100300505 |  | 6716212G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ROBERTSON | 520 ROBERTSON ST | 067 | LEX | 2025-02-05 | JBURFOR | U124420 | 2024-11-14 | 2027-07-02 | 2027-07-05 |  | JBURFOR | 2025-02-05 | 2025-01-24 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 19.6833 | 5 | 1223.77 | 1167.66 | 0 | 56.11 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295596700 |  | 100300506 |  | 6716212G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ROBERTSON | 516 ROBERTSON ST | 067 | LEX | 2025-02-04 | JBURFOR | U124420 | 2024-11-14 | 2027-07-26 | 2027-07-26 |  | JBURFOR | 2025-02-04 | 2025-01-24 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 23.0667 | 5 | 1508.45 | 1440.1 | 0 | 68.35 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295596900 |  | 100300551 |  | 6716212G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SPEIGLE | 459 SPEIGLE ST | 067 | LEX | 2025-06-09 | U124604 | U124420 | 2024-11-14 | 2026-08-03 | 2026-08-03 |  | HSTANFI | 2025-06-06 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.5833 | 4 | 2304.1 | 1009.83 | 17.9 | 59.21 | 1217.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295597000 |  | 100300585 |  | 6716212F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ROBERTSON | 409 ROBERTSON ST | 067 | LEX | 2025-02-04 | U124604 | U124420 | 2024-11-14 | 2026-06-09 | 2026-06-09 |  | JBURFOR | 2025-02-03 | 2025-01-24 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 24.2833 | 4 | 1609.78 | 1537.57 | 0 | 72.21 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295597100 |  | 100300727 |  | 6716212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DELMONT | 128 DELMONT DR | 067 | LEX | 2025-01-30 | MCRAIG | U124420 | 2024-11-14 | 2026-04-03 | 2026-04-05 |  | MCRAIG | 2025-01-30 | 2025-01-30 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10.25 | 3 | 855.66 | 540.44 | 160.06 | 155.16 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295597200 |  | 100300820 |  | 6716212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GARRETT | 122 GARRETT AV | 067 | LEX | 2025-06-13 | U124604 | U124420 | 2024-11-14 | 2027-03-09 | 2027-03-09 |  | DMEDLEY | 2025-06-12 | 2025-06-12 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.1 | 3 | 1561.65 | 1034.96 | 0 | 526.69 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295597400 |  | 100301235 |  | 6716212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DUNKIRK | 1841 DUNKIRK DR | 067 | LEX | 2025-02-18 | U124604 | U124420 | 2024-11-14 | 2026-03-23 | 2026-03-23 |  | DJOHNSON | 2025-02-17 | 2025-02-17 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 18.0667 | 3 | 1509.13 | 1213.17 | 17.88 | 278.08 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295597600 |  | 100301801 |  | 6712212H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DEAUVILLE | 1908 DEAUVILLE DR | 067 | LEX | 2025-06-10 | U930915 | U124420 | 2024-11-14 | 2027-06-09 | 2027-06-09 |  | JGILES | 2025-06-10 | 2025-06-10 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.2 | 3 | 746.17 | 522.63 | 17.9 | 205.64 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295597800 |  | 100302186 |  | 6712212L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | VERSAILLES | 2089 VERSAILLES RD | 067 | LEX | 2025-01-14 | WBURGESS | U124420 | 2024-11-14 | 2026-01-19 | 2026-01-19 |  | WBURGESS | 2025-01-14 | 2025-01-14 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 23.8833 | 3 | 1317.79 | 1236.44 | 0 | 81.35 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295598000 |  | 100302974 |  | 6712208C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GEORGIAN | 2067 GEORGIAN WY 1FL | 067 | LEX | 2025-02-18 | U123688 | U124420 | 2024-11-14 | 2027-04-06 | 2027-04-06 |  | RSTRONG | 2025-02-14 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 14.1167 | 3 | 2834.92 | 1046.62 | 161.52 | 96.9 | 1529.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295598100 |  | 100304170 |  | 6712208D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CYPRESS | 2137 CYPRESS DR | 067 | LEX | 2025-01-31 | U124604 | U124420 | 2024-11-14 | 2027-04-01 | 2027-04-01 |  | RSTRONG | 2025-01-30 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 14.6 | 2 | 1000.68 | 797.73 | 52.99 | 149.96 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295598300 |  | 100305000 |  | 6712212O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ALEXANDRIA | 1718 ALEXANDRIA DR | 067 | LEX | 2025-03-25 | KKINDER | U124420 | 2024-11-14 | 2026-12-14 | 2026-12-14 |  | KKINDER | 2025-03-25 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 24 | 3 | 1995.33 | 1607.88 | 67.52 | 319.93 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295598400 |  | 100305304 |  | 6712212O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LINSTEAD | 1653 LINSTEAD DR | 067 | LEX | 2025-01-30 | U130722 | U124420 | 2024-11-14 | 2027-02-11 | 2027-02-11 |  | RSTRONG | 2025-01-24 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.9333 | 3 | 739.38 | 607.61 | 0 | 131.77 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295598700 |  | 100307264 |  | 6716212J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BENNETT | 780 BENNETT AV | 067 | LEX | 2025-01-30 | MCRAIG | U124420 | 2024-11-14 | 2027-04-08 | 2027-04-08 |  | MCRAIG | 2025-01-30 | 2025-01-30 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.4167 | 2 | 748.54 | 515.21 | 39.7 | 193.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295598800 |  | 100307356 |  | 6716212J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ANGLIANA | 850 ANGLIANA AV | 067 | LEX | 2024-12-16 | U124604 | U124420 | 2024-11-14 | 2026-06-04 | 2026-06-04 |  | RSTRONG | 2024-12-13 | 2024-12-09 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 25.4833 | 4 | 2201.65 | 1687.42 | 17.88 | 496.35 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295598900 |  | 100308494 |  | 6716212N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GOLFVIEW | 645 GOLFVIEW DR | 067 | LEX | 2025-06-13 | U930915 | U124420 | 2024-11-14 | 2027-03-10 | 2027-03-10 |  | DMEDLEY | 2025-06-13 | 2025-01-09 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 19.5667 | 4 | 1590.27 | 1256.28 | 0 | 333.99 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295599000 |  | 100308811 |  | 6716208A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FURLONG | 829 FURLONG DR | 067 | LEX | 2025-06-03 | U124604 | U124420 | 2024-11-14 | 2027-08-09 | 2027-08-09 |  | JBURFOR | 2025-06-02 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.15 | 2 | 1071.16 | 836.69 | 185.4 | 49.07 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295599200 |  | 100309113 |  | 6716208A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HARRODSBURG | 1907 HARRODSBURG RD | 067 | LEX | 2025-02-21 | U124604 | U124420 | 2024-11-14 | 2026-01-02 | 2026-01-04 |  | RSTRONG | 2025-02-20 | 2025-01-29 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 20.7833 | 6 | 1493.63 | 1368.45 | 17.88 | 107.3 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295599400 |  | 100310020 |  | 6712008H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SHERIDAN | 703 SHERIDAN DR | 067 | LEX | 2025-02-05 | RSTRONG | U124420 | 2024-11-14 | 2027-09-22 | 2027-09-22 |  | RSTRONG | 2025-02-05 | 2025-01-24 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.5667 | 4 | 1488.73 | 458.75 | 40.1 | 160.44 | 829.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295599500 |  | 100310157 |  | 6716208A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SPRINGRIDGE | 694 SPRINGRIDGE DR | 067 | LEX | 2025-03-11 | U930915 | U124420 | 2024-11-14 | 2027-05-21 | 2027-05-23 |  | JGILES | 2025-03-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.0833 | 3 | 916.27 | 740.73 | 17.88 | 157.66 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295599600 |  | 100310199 |  | 6716208A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SPRINGRIDGE | 671 SPRINGRIDGE DR | 067 | LEX | 2025-01-03 | U124604 | U124420 | 2024-11-14 | 2025-12-19 | 2025-12-21 |  | RSTRONG | 2025-01-02 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 23.4 | 3 | 1632.96 | 1247.7 | 152.24 | 233.02 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295599700 |  | 100310347 |  | 6716208A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CLAYS MILL | 1939 CLAYS MILL RD | 067 | LEX | 2025-02-25 | U124604 | U124420 | 2024-11-14 | 2026-11-30 | 2026-11-30 |  | KOBRYAN | 2025-02-24 | 2025-02-07 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 14.6 | 3 | 3152.16 | 1043.88 | 0 | 48.9 | 2059.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295599800 |  | 100311681 |  | 6712204D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | POST | 3374 POST RD | 067 | LEX | 2025-01-15 | JBURFOR | U124420 | 2024-11-14 | 2026-05-04 | 2026-05-04 |  | JBURFOR | 2025-01-15 | 2025-01-15 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 20.8667 | 3 | 1186.45 | 1113.22 | 0 | 73.23 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295599900 |  | 100312026 |  | 6716208J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MILLBROOK | 2572 MILLBROOK DR | 067 | LEX | 2025-01-13 | JBURFOR | U124420 | 2024-11-14 | 2026-07-31 | 2026-08-02 |  | JBURFOR | 2025-01-13 | 2025-01-13 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.2833 | 3 | 1000.43 | 938.65 | 0 | 61.78 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295600000 |  | 100312782 |  | 6716208E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | STRATFORD | 561 STRATFORD DR | 067 | LEX | 2025-03-17 | U124604 | U124420 | 2024-11-14 | 2027-07-20 | 2027-07-20 |  | KKINDER | 2025-03-14 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 21.6667 | 3 | 1864.76 | 1446.39 | 132.42 | 285.95 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295600200 |  | 100315592 |  | 6716208C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ELIZABETH | 1549 ELIZABETH ST | 067 | LEX | 2025-02-26 | KOBRYAN | U124420 | 2024-11-14 | 2027-02-19 | 2027-02-21 |  | KOBRYAN | 2025-02-26 | 2025-02-14 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.3167 | 5 | 1602.65 | 880.59 | 0 | 66.86 | 655.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295600300 |  | 100315876 |  | 6716208F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ARCADIA | 542 ARCADIA PR | 067 | LEX | 2025-02-11 | U930915 | U124420 | 2024-11-14 | 2026-11-16 | 2026-11-16 |  | KKINDER | 2025-02-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.95 | 2 | 660.2 | 541.39 | 17.88 | 100.93 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295600500 |  | 100316555 |  | 6716208F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PENMOKEN | 153 PENMOKEN PA | 067 | LEX | 2025-02-18 | WBURGESS | U124420 | 2024-11-14 | 2027-01-25 | 2027-01-25 |  | WBURGESS | 2025-02-18 | 2025-01-15 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 19.05 | 4 | 1690.05 | 1095.97 | 0 | 54.08 | 540 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295600600 |  | 100316593 |  | 6716208F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PENMOKEN | 124 PENMOKEN PA FT | 067 | LEX | 2025-02-14 | U123688 | U124420 | 2024-11-14 | 2027-02-09 | 2027-02-09 |  | JBURFOR | 2025-02-12 | 2025-01-10 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 19.6333 | 6 | 1364.32 | 1169.56 | 132.42 | 62.34 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295600700 |  | 100316827 |  | 6716208F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GOODRICH | 116 GOODRICH AV | 067 | LEX | 2025-02-06 | U124604 | U124420 | 2024-11-14 | 2027-04-12 | 2027-04-12 |  | RSTRONG | 2025-02-05 | 2025-01-24 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.4667 | 4 | 2045.33 | 970.46 | 39.7 | 222.23 | 812.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295600800 |  | 100316929 |  | 6716208F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SOUTHLAND | 246 SOUTHLAND DR | 067 | LEX | 2025-01-27 | U930915 | U124420 | 2024-11-14 | 2027-01-25 | 2027-01-25 |  | ABLAKE | 2025-01-24 | 2025-01-10 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 21.7333 | 7 | 4320.42 | 1197.57 | 0 | 78.81 | 3044.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295600900 |  | 100316986 |  | 6716208J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SOUTHLAND | 204 SOUTHLAND DR | 067 | LEX | 2025-01-28 | U930915 | U124420 | 2024-11-14 | 2027-06-07 | 2027-06-07 |  | JOCHOA | 2025-01-24 | 2025-01-10 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.65 | 8 | 905.14 | 849.21 | 0 | 55.93 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295601100 |  | 100318477 |  | 6716204C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HIGHTOWER | 297 HIGHTOWER RD | 067 | LEX | 2025-02-03 | U123688 | U124420 | 2024-11-14 | 2026-05-29 | 2026-05-29 |  | DMALONE | 2025-01-31 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 498.62 | 467.86 | 0 | 30.76 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295601300 |  | 100321183 |  | 6716212P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | AYLESFORD | 329 AYLESFORD PL | 067 | LEX | 2025-05-23 | MSHARON | U124420 | 2024-11-14 | 2027-07-08 | 2027-07-08 |  | MSHARON | 2025-05-23 | 2025-02-13 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 34.2333 | 9 | 2045.69 | 1920.67 | 21.92 | 103.1 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295601400 |  | 100321189 |  | 6716212P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | AYLESFORD | 343 AYLESFORD PL 1F | 067 | LEX | 2025-02-24 | U123688 | U124420 | 2024-11-14 | 2027-09-09 | 2027-09-09 |  | RJCRAWF | 2025-02-21 | 2025-02-13 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 17.9667 | 6 | 1436.17 | 1365.47 | 6.71 | 63.99 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295601700 |  | 100321815 |  | 6716208D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PARK | 513 PARK AV | 067 | LEX | 2025-01-14 | U930915 | U124420 | 2024-11-14 | 2027-04-19 | 2027-04-19 |  | RJCRAWF | 2025-01-13 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.3167 | 3 | 563.96 | 508.63 | 21.82 | 33.51 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295601800 |  | 100321968 |  | 6716212P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ROSE | 463 ROSE LN | 067 | LEX | 2025-03-21 | JOCHOA | U124420 | 2024-11-14 | 2026-06-19 | 2026-06-21 |  | JOCHOA | 2025-03-21 | 2025-02-18 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 17.1667 | 5 | 1224.97 | 1120.61 | 39.7 | 64.66 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295602100 |  | 100324469 |  | 6720204E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OLYMPIA | 3547 OLYMPIA RD | 067 | LEX | 2024-12-09 | U930915 | U124420 | 2024-11-14 | 2025-10-09 | 2025-10-09 |  | RJCRAWF | 2024-12-06 | 2024-11-25 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.95 | 4 | 879.77 | 831.16 | 0 | 48.61 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295602200 |  | 100324723 |  | 6720204B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SUTHERLAND | 3271 SUTHERLAND DR | 067 | LEX | 2025-04-02 | U124604 | U124420 | 2024-11-14 | 2026-03-03 | 2026-03-03 |  | KOBRYAN | 2025-04-01 | 2025-02-17 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.5 | 4 | 809.15 | 763.32 | 0 | 45.83 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295602300 |  | 100325413 |  | 6720208E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | THE CURTILAGE | 912 THE CURTILAGE | 067 | LEX | 2025-05-06 | U930915 | U124420 | 2024-11-14 | 2027-06-30 | 2027-06-30 |  | RJCRAWF | 2025-05-05 | 2025-01-31 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.8333 | 6 | 1838.15 | 331.9 | 39.82 | 19.41 | 1447.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295602400 |  | 100326160 |  | 6712216I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OLD FRANKFORT | 3225 OLD FRANKFORT PK | 067 | LEX | 2025-04-02 | DMEDLEY | U124420 | 2024-11-14 | 2026-01-08 | 2026-01-08 |  | DMEDLEY | 2025-04-02 | 2025-01-10 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 42.6667 | 11 | 3665.25 | 2705.08 | 0 | 960.17 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295602500 |  | 100326854 |  | 6720208B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FONTAINE | 1509 FONTAINE RD | 067 | LEX | 2025-03-11 | U930915 | U124420 | 2024-11-14 | 2027-10-13 | 2027-10-13 |  | JOCHOA | 2025-03-07 | 2025-01-31 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 23.0167 | 6 | 1503.08 | 1382.32 | 39.7 | 81.06 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295602600 |  | 100327096 |  | 6720212M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WOODLAND | 144 WOODLAND AV | 067 | LEX | 2024-12-04 | U123688 | U124420 | 2024-11-14 | 2025-11-24 | 2025-11-24 |  | RJCRAWF | 2024-12-03 | 2024-11-25 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.7 | 4 | 1485.01 | 874.05 | 39.78 | 51.18 | 520 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295602700 |  | 100327669 |  | 6720212M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HANOVER | 122 S HANOVER AV FURN | 067 | LEX | 2025-03-19 | KOBRYAN | U124420 | 2024-11-14 | 2026-10-26 | 2026-10-26 |  | KOBRYAN | 2025-03-19 | 2024-12-27 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 21.7833 | 4 | 3193.97 | 1242.54 | 0 | 72.83 | 1878.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295602800 |  | 100328226 |  | 6720208F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CULPEPPER | 401 CULPEPPER RD | 067 | LEX | 2024-12-20 | U124604 | U124420 | 2024-11-14 | 2026-04-10 | 2026-04-12 |  | MSHARON | 2024-12-19 | 2024-12-09 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 14.9333 | 11 | 1022.54 | 966.09 | 0 | 56.45 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295603000 |  | 100328761 |  | 6720208F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HART | 1973 HART RD | 067 | LEX | 2025-02-18 | U930915 | U124420 | 2024-11-14 | 2027-06-25 | 2027-06-25 |  | RJCRAWF | 2025-02-18 | 2024-12-27 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.5667 | 5 | 859.09 | 794.41 | 27.31 | 37.37 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295603300 |  | 100330471 |  | 6728212M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WINCHESTER | 2950 WINCHESTER RD FG13 | 067 | LEX | 2025-06-04 | U930915 | U124420 | 2024-11-14 | 2026-06-17 | 2026-06-17 |  | SSHIMFE | 2025-05-30 | 2025-05-16 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.8833 | 3 | 817.68 | 746.16 | 28.31 | 43.21 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295603400 |  | 100330581 |  | 6732212M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WINCHESTER | 4300 WINCHESTER RD | 067 | LEX | 2025-01-31 | U124604 | U124420 | 2024-11-14 | 2027-07-06 | 2027-07-06 |  | LSTANFI | 2025-01-30 | 2025-01-30 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.2833 | 2 | 1451.04 | 292.17 | 17.88 | 61.83 | 1079.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295603500 |  | 100330705 |  | 6720212N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SHERMAN | 204 SHERMAN AV | 067 | LEX | 2025-05-23 | BDARNELL | U124420 | 2024-11-14 | 2027-06-15 | 2027-06-15 |  | BDARNELL | 2025-05-23 | 2025-05-23 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.9333 | 3 | 2288.04 | 707.71 | 39.82 | 40.99 | 1499.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295603600 |  | 100330925 |  | 6720212O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BASSETT | 357 BASSETT AV | 067 | LEX | 2025-03-07 | U930915 | U124420 | 2024-11-14 | 2026-04-20 | 2026-04-20 |  | HMCKUNE | 2025-03-06 | 2025-03-06 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 24 | 3 | 3649.57 | 1380.01 | 0 | 587.82 | 1681.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295603700 |  | 100331180 |  | 6720212N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MENIFEE | 1305 MENIFEE AV | 067 | LEX | 2025-02-27 | U124604 | U124420 | 2024-11-14 | 2026-10-06 | 2026-10-06 |  | JOCHOA | 2025-02-26 | 2025-02-07 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 24.7167 | 6 | 2059.91 | 1858.95 | 113.88 | 87.08 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295603900 |  | 100331310 |  | 6720212N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MONROE | 1201 MONROE AV 1 | 067 | LEX | 2025-03-20 | U123688 | U124420 | 2024-11-14 | 2026-04-07 | 2026-04-07 |  | HMCKUNE | 2025-03-13 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.9333 | 4 | 1219.94 | 763.31 | 0 | 456.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295604000 |  | 100331345 |  | 6720212N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OWSLEY | 328 OWSLEY AV | 067 | LEX | 2025-03-10 | U930915 | U124420 | 2024-11-14 | 2027-02-10 | 2027-02-10 |  | HMCKUNE | 2025-03-10 | 2025-01-23 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 28.7333 | 5 | 3332.14 | 1559.19 | 0 | 457.93 | 1315.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295604100 |  | 100331596 |  | 6720212N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MARNE | 113 MARNE AV | 067 | LEX | 2025-04-28 | U930915 | U124420 | 2024-11-14 | 2026-10-02 | 2026-10-04 |  | CHEMMER | 2025-04-28 | 2025-01-28 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 29.1667 | 7 | 2308.76 | 1641.52 | 45.93 | 101.31 | 520 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295604200 |  | 100331970 |  | 6720212M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WALTON | 148 WALTON AV | 067 | LEX | 2024-12-13 | U930915 | U124420 | 2024-11-14 | 2025-12-03 | 2025-12-03 |  | JOCHOA | 2024-12-13 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.2667 | 2 | 601.52 | 568.35 | 0 | 33.17 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295604300 |  | 100332063 |  | 6720212J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WALTON | 222 WALTON AV 1FL | 067 | LEX | 2025-03-25 | U930915 | U124420 | 2024-11-14 | 2026-07-09 | 2026-07-09 |  | JOCHOA | 2025-03-25 | 2025-03-21 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.9833 | 6 | 812.61 | 767.6 | 0 | 45.01 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295604400 |  | 100332421 |  | 6720212M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 647 E MAIN ST | 067 | LEX | 2025-01-17 | U930915 | U124420 | 2024-11-14 | 2025-10-22 | 2025-10-22 |  | BDARNELL | 2025-01-16 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.4833 | 2 | 2034.92 | 937.94 | 21.82 | 235.16 | 840 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295604800 |  | 100333401 |  | 6720212I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RACE | 253 RACE ST | 067 | LEX | 2025-04-30 | U930915 | U124420 | 2024-11-14 | 2026-07-10 | 2026-07-12 |  | BDARNELL | 2025-04-29 | 2025-04-29 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 17.3333 | 3 | 1208.28 | 919.54 | 79.54 | 209.2 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295604900 |  | 100333432 |  | 6720212I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | EASTERN | 208 EASTERN AV A | 067 | LEX | 2025-03-11 | U124604 | U124420 | 2024-11-14 | 2025-03-10 | 2026-11-09 |  | LSTANFI | 2025-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.85 | 3 | 82.23 | 51.33 | 0 | 10.9 | 20 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295605000 |  | 100333955 |  | 6720212O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DALLAS | 400 DALLAS AV | 067 | LEX | 2025-06-05 | U930915 | U124420 | 2024-11-14 | 2027-01-12 | 2027-01-12 |  | SSHIMFE | 2025-06-05 | 2025-05-29 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.3667 | 3 | 2473.13 | 501.71 | 0 | 29.4 | 1942.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295605100 |  | 100333977 |  | 6720212K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LIBERTY | 1004 LIBERTY RD | 067 | LEX | 2025-06-19 | U930915 | U124420 | 2024-11-14 | 2027-03-25 | 2027-03-25 |  | SSHIMFE | 2025-06-19 | 2025-06-19 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.95 | 2 | 1379.51 | 849.67 | 0 | 49.84 | 480 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295605300 |  | 100334423 |  | 6720208H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PLUMTREE | 2454 PLUMTREE CT | 067 | LEX | 2025-06-06 | HMCKUNE | U124420 | 2024-11-14 | 2027-10-22 | 2027-10-24 |  | HMCKUNE | 2025-06-06 | 2025-06-06 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 24 | 3 | 1500.99 | 1403.6 | 15.08 | 82.31 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295605400 |  | 100334640 |  | 6720208D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WILDERNESS | 649 WILDERNESS RD | 067 | LEX | 2024-12-10 | U137585 | U124420 | 2024-11-14 | 2025-11-07 | 2025-11-07 |  | HMCKUNE | 2024-12-09 | 2024-12-09 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 23.1167 | 3 | 1713.27 | 1618.73 | 0 | 94.54 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295605500 |  | 100334760 |  | 6724208F | 0779343 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LIBERTY | 2838 LIBERTY RD | 067 | LEX | 2025-05-29 | JBURFOR | U124420 | 2024-11-14 | 2026-04-27 | 2026-04-27 |  | JBURFOR | 2025-05-29 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.35 | 2 | 406.14 | 346.28 | 39.82 | 20.04 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295605600 |  | 100335142 |  | 6720212K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LIBERTY | 1051 LIBERTY RD | 067 | LEX | 2025-05-29 | U930915 | U124420 | 2024-11-14 | 2026-05-11 | 2026-05-11 |  | KOBRYAN | 2025-05-29 | 2025-05-28 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.85 | 3 | 1427.61 | 895.73 | 0 | 51.88 | 480 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295605700 |  | 100335194 |  | 6720212K |  |  |  | 566 | EX | ABANDON SL/IDLE/ INACTIVE | 2621P | BROWN | 108 BROWN AV | 067 | LEX | 2025-02-14 | LSTANFI | U124420 | 2024-11-14 | 2026-12-29 | 2026-12-29 |  | LSTANFI | 2025-02-14 | 2025-02-13 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.0833 | 5 | 1031.29 | 927.26 | 10.01 | 94.02 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295606000 |  | 100335806 |  | 6720212L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | COMMERCIAL | 1137 COMMERCIAL DR RRR | 067 | LEX | 2025-02-10 | BDARNELL | U124420 | 2024-11-14 | 2025-11-26 | 2025-11-30 |  | BDARNELL | 2025-02-10 | 2025-01-03 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.2167 | 4 | 548.75 | 518.2 | 0 | 30.55 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295606100 |  | 100335882 |  | 6720212G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FLOYD | 885 FLOYD DR | 067 | LEX | 2025-04-11 | BDARNELL | U124420 | 2024-11-14 | 2026-04-30 | 2026-04-30 |  | BDARNELL | 2025-04-11 | 2025-04-09 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10.3 | 3 | 575.3 | 528.03 | 15.08 | 32.19 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295606200 |  | 100335949 |  | 6720212K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HILLCREST | 328 HILLCREST AV | 067 | LEX | 2025-03-21 | U124604 | U124420 | 2024-11-14 | 2026-05-11 | 2026-05-11 |  | LSTANFI | 2025-03-20 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.8 | 3 | 148.55 | 110.07 | 15.07 | 23.41 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295606300 |  | 100335958 |  | 6720212K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HILLCREST | 303 HILLCREST AV | 067 | LEX | 2025-03-21 | U930915 | U124420 | 2024-11-14 | 2026-07-10 | 2026-07-12 |  | LSTANFI | 2025-03-20 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 19.1 | 3 | 1427.05 | 1164.57 | 15.07 | 247.41 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295606600 |  | 100336028 |  | 6720212K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BYARS | 904 BYARS AV | 067 | LEX | 2025-02-17 | U930915 | U124420 | 2024-11-14 | 2026-09-25 | 2026-09-27 |  | LSTANFI | 2025-02-14 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 22.9833 | 5 | 1594.12 | 1522.41 | 0 | 71.71 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295606700 |  | 100336097 |  | 6720212J | 9610649 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 7TH | 628 E 7TH ST | 067 | LEX | 2025-01-23 | LSTANFI | U124420 | 2024-11-14 | 2026-01-15 | 2026-01-15 |  | LSTANFI | 2025-01-23 | 2025-01-23 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.4167 | 3 | 2948.59 | 763.8 | 15.07 | 60.06 | 2109.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295606800 |  | 100336165 |  | 6720212J | 0252689 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WINCHESTER | 919 WINCHESTER RD | 067 | LEX | 2025-01-31 | U930915 | U124420 | 2024-11-14 | 2027-07-27 | 2027-07-27 |  | LSTANFI | 2025-01-30 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.8667 | 2 | 1718.21 | 252.11 | 25.39 | 40.55 | 1400.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295606900 |  | 100336252 |  | 6720212I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 3RD | 503 E 3RD ST | 067 | LEX | 2025-01-24 | U124604 | U124420 | 2024-11-14 | 2025-11-13 | 2025-11-13 |  | LSTANFI | 2025-01-23 | 2025-01-23 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.5333 | 4 | 994.58 | 769.01 | 82.78 | 142.79 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295607000 |  | 100336267 |  | 6720212I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WILGUS | 341 WILGUS AV | 067 | LEX | 2025-01-03 | U124604 | U124420 | 2024-11-14 | 2025-12-19 | 2025-12-21 |  | JOCHOA | 2025-01-02 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 20.3 | 4 | 1292.98 | 1175.92 | 39.7 | 77.36 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295607200 |  | 100336448 |  | 6720212I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CAMPSIE | 248 CAMPSIE PL | 067 | LEX | 2025-02-10 | LSTANFI | U124420 | 2024-11-14 | 2026-01-05 | 2026-01-05 |  | LSTANFI | 2025-02-10 | 2024-12-19 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 18.1333 | 6 | 1417.93 | 1239.98 | 0 | 177.95 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295607300 |  | 100336505 |  | 6720212I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OHIO | 347 OHIO ST | 067 | LEX | 2025-01-31 | LSTANFI | U124420 | 2024-11-14 | 2026-05-11 | 2026-05-11 |  | LSTANFI | 2025-01-31 | 2025-01-31 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.5667 | 3 | 712.84 | 403.74 | 82.78 | 60.76 | 165.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295607400 |  | 100336517 |  | 6720212I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OHIO | 316 OHIO ST | 067 | LEX | 2025-01-29 | U124604 | U124420 | 2024-11-14 | 2026-10-30 | 2026-11-01 |  | LSTANFI | 2025-01-28 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.0667 | 3 | 460.19 | 341.04 | 82.78 | 36.37 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295607600 |  | 100337274 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 6TH | 178 E 6TH ST | 067 | LEX | 2025-01-30 | U930915 | U124420 | 2024-11-14 | 2026-03-16 | 2026-03-16 |  | LSTANFI | 2025-01-30 | 2025-01-30 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.75 | 2 | 1552.75 | 523.09 | 0 | 129.66 | 900 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295607700 |  | 100337342 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OHIO | 553 OHIO ST | 067 | LEX | 2025-01-29 | U124604 | U124420 | 2024-11-14 | 2026-03-10 | 2026-03-10 |  | LSTANFI | 2025-01-28 | 2025-01-28 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.8667 | 3 | 1391.36 | 832 | 24.58 | 54.78 | 480 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295608100 |  | 100337757 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ELM TREE | 660 ELM TREE LN | 067 | LEX | 2025-03-11 | U124604 | U124420 | 2024-11-14 | 2026-08-06 | 2026-08-06 |  | LSTANFI | 2025-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 18.8 | 3 | 1772.5 | 1146.21 | 82.78 | 243.51 | 300 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295608300 |  | 100337920 |  | 6712216F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BRACKTOWN | 3240 BRACKTOWN RD | 067 | LEX | 2025-02-07 | DMALONE | U124420 | 2024-11-14 | 2026-12-14 | 2026-12-14 |  | DMALONE | 2025-02-07 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10.0667 | 2 | 626.15 | 598.12 | 0 | 28.03 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295608400 |  | 100338110 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 7TH | 406 E 7TH ST | 067 | LEX | 2025-02-03 | U930915 | U124420 | 2024-11-14 | 2027-02-18 | 2027-02-18 |  | LSTANFI | 2025-01-31 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.25 | 3 | 985.76 | 806.73 | 0 | 179.03 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295608600 |  | 100338175 |  | 6720212J | 2185057 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BRECKENRIDGE | 545 BRECKENRIDGE ST | 067 | LEX | 2025-02-13 | BDARNELL | U124420 | 2024-11-14 | 2027-03-22 | 2027-03-22 |  | BDARNELL | 2025-02-13 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.4167 | 3 | 1549.47 | 470.4 | 82.78 | 36.29 | 960 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295608900 |  | 100338385 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SHELBY | 605 SHELBY ST | 067 | LEX | 2025-06-13 | U930915 | U124420 | 2024-11-14 | 2027-05-24 | 2027-05-24 |  | KOBRYAN | 2025-06-13 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10.0333 | 2 | 504.41 | 476.47 | 0 | 27.94 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295609000 |  | 100338619 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | YORK | 149 YORK ST | 067 | LEX | 2025-04-29 | BDARNELL | U124420 | 2024-11-14 | 2026-08-14 | 2026-08-16 |  | BDARNELL | 2025-04-29 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.6333 | 3 | 1238.23 | 374.87 | 15.08 | 68.28 | 780 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295609200 |  | 100340041 |  | 6724212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | AUGUSTA | 1839 AUGUSTA DR 1 | 067 | LEX | 2024-12-30 | U930915 | U124420 | 2024-11-14 | 2027-10-21 | 2027-10-21 |  | LSTANFI | 2024-12-27 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 14.4 | 2 | 1441.3 | 1108.4 | 0 | 332.9 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295609600 |  | 100340850 |  | 6744184D |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTRQD | 2621P | DOYLESVILLE | 2567 DOYLESVILLE RD | 151 | RIC | 2025-05-07 | U930915 | U124420 | 2024-11-14 | 2025-05-06 | 2025-05-27 |  | DENNING | 2025-05-06 | 2025-05-06 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 15.6 | 3 | 4609.52 | 1231.95 | 0 | 71.32 | 3306.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295609900 |  | 100341111 |  | 7244216E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OWINGSVILLE | 1520 OWINGSVILLE RD | 173 | MT | 2025-03-04 | DENNING | U124420 | 2024-11-14 | 2026-03-16 | 2026-03-16 |  | DENNING | 2025-03-04 | 2025-03-04 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 26.55 | 4 | 4990.97 | 2108.77 | 0 | 123.63 | 2758.57 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295610000 |  | 100341240 |  | 7244216I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KENTUCKY | 550 KENTUCKY DR | 173 | MT | 2025-03-05 | U930915 | U124420 | 2024-11-14 | 2026-03-16 | 2026-03-16 |  | LCLARK | 2025-03-05 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 12.1333 | 2 | 1020.03 | 954.1 | 10.01 | 55.92 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295610900 |  | 100342318 |  | 7240216J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BOB O LINK | 518 BOB O LINK CT 7B | 173 | MT | 2025-01-21 | U123688 | U124420 | 2024-11-14 | 2025-11-07 | 2025-11-09 |  | DENNING | 2025-01-20 | 2025-01-17 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 21.65 | 4 | 2422.57 | 1608.97 | 0 | 813.6 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295611100 |  | 100342772 |  | 7240216M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GREENLAND | 305 GREENLAND CT | 173 | MT | 2025-02-27 | U930915 | U124420 | 2024-11-14 | 2026-01-16 | 2026-01-18 |  | DENNING | 2025-02-26 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 17.7333 | 2 | 4244.51 | 1638 | 47.03 | 967.48 | 1592 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295612000 |  | 100343748 |  | 7240212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LEVEE | 360 LEVEE RD | 173 | MT | 2025-02-05 | U930915 | U124420 | 2024-11-14 | 2026-02-20 | 2026-02-22 |  | DENNING | 2025-02-04 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 13.4 | 2 | 3660.11 | 1234.52 | 0 | 729.21 | 1696.38 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295612400 |  | 100344165 |  | NEW |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HOLLEY | 338 HOLLEY RD | 135 | VAN | 2025-05-20 | U124604 | U124420 | 2024-11-14 | 2026-08-05 | 2026-08-05 |  | RALLISO | 2025-05-19 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 9.3 | 2 | 833.79 | 796.79 | 0 | 37 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295612900 |  | 100345393 |  | 6696212H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DEPOT | 128 DEPOT ST | 239 | VER | 2025-03-26 | U128410 | U124420 | 2024-11-14 | 2026-04-29 | 2026-04-29 |  | CDESPAIN | 2025-03-26 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 10.55 | 2 | 914.31 | 863.7 | 0 | 50.61 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295613000 |  | 100345455 |  | 6696212H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DOUGLAS | 236 DOUGLAS AV 1F | 239 | VER | 2025-03-26 | U128410 | U124420 | 2024-11-14 | 2026-03-06 | 2026-03-08 |  | CDESPAIN | 2025-03-26 | 2024-12-10 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 6.9 | 3 | 1846.43 | 532.1 | 0 | 31.08 | 1283.25 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295613100 |  | 100345743 |  | 6696212D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MARCELLA | 781 MARCELLA ST | 239 | VER | 2025-03-19 | U128410 | U124420 | 2024-11-14 | 2026-05-06 | 2026-05-06 |  | CDESPAIN | 2025-03-19 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 3.3 | 2 | 387.91 | 267.66 | 0 | 120.25 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295613200 |  | 100346318 |  | 6696212L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CHURCH | 280 CHURCH ST | 239 | VER | 2025-02-03 | U128410 | U124420 | 2024-11-14 | 2026-12-18 | 2026-12-20 |  | CDESPAIN | 2025-02-03 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 14.85 | 3 | 1204.94 | 1151.02 | 0 | 53.92 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295613300 |  | 100346376 |  | 6696212L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CHURCH | 225 CHURCH ST | 239 | VER | 2025-02-03 | U128410 | U124420 | 2024-11-14 | 2026-06-23 | 2026-06-23 |  | CDESPAIN | 2025-02-03 | 2025-01-17 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 24.7 | 6 | 3947.35 | 1752.95 | 0 | 874.4 | 1320 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295613600 |  | 100346991 |  | 6696212K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HIGH | 230 HIGH ST | 239 | VER | 2025-02-04 | U128410 | U124420 | 2024-11-14 | 2027-06-16 | 2027-06-16 |  | CDESPAIN | 2025-02-04 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 9.4833 | 2 | 773.34 | 738.71 | 0 | 34.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295613700 |  | 100347007 |  | 6696212K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HIGH | 275 HIGH ST | 239 | VER | 2025-02-04 | U128410 | U124420 | 2024-11-14 | 2027-02-23 | 2027-02-23 |  | CDESPAIN | 2025-02-04 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 6.9167 | 2 | 1345.17 | 539.87 | 0 | 25.3 | 780 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295613800 |  | 100347124 |  | 6696212K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | TYRONE | 798 TYRONE PK | 239 | VER | 2025-02-10 | U128410 | U124420 | 2024-11-14 | 2026-09-22 | 2026-09-22 |  | CDESPAIN | 2025-02-10 | 2025-01-08 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 9.0833 | 3 | 809.42 | 677.2 | 0 | 132.22 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295614800 |  | 100348605 |  | W-1102-5 | 2293700 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | MAIN | 151 N MAIN ST | 049 | WIN | 2024-12-11 | U126604 | U124420 | 2024-11-14 | 2026-06-16 | 2026-06-16 |  | WILLIAM FULKS | 2024-12-11 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26290043 |  | 1 | 1094.54 | 0 | 0 | 0 | 1094.54 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295615200 |  | 100349083 |  | 6748208M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PARK | 7 PARK AV | 049 | WIN | 2025-03-10 | NRICHIE | U124420 | 2024-11-14 | 2026-01-16 | 2026-01-18 |  | NRICHIE | 2025-03-10 | 2025-02-17 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 11.3833 | 3 | 1896.22 | 858.54 | 0 | 49.68 | 988 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295615300 |  | 100349127 |  | 6748208M | 1855043 |  |  | 566 | EX | ABANDON SL - SOII/LEGACY | 2621P | ASHLAND | 16 ASHLAND AV | 049 | WIN | 2025-03-24 | U124604 | U124420 | 2024-11-14 | 2025-04-17 | 2025-04-19 |  | NRICHIE | 2025-03-21 | 2025-03-05 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 12.65 | 6 | 1003.03 | 947.5 | 0 | 55.53 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295615900 |  | 100349319 |  | 6748208M | 1855043 |  |  | 566 | EX | ABANDON SL - SOII/LEGACY | 2621P | BUCKNER | 21 BUCKNER ST | 049 | WIN | 2025-03-21 | U124604 | U124420 | 2024-11-14 | 2025-05-28 | 2025-05-28 |  | DENNING | 2025-03-20 | 2025-03-05 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 19.5667 | 5 | 4474.82 | 1554.3 | 79.17 | 91.1 | 2750.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295616600 |  | 100349650 |  | 6748208M |  |  |  | 566 | EX | ABANDON SL - DEMO/CUST RQST | 2621P | GEORGIA | 109 GEORGIA ST | 049 | WIN | 2025-05-09 | DENNING | U124420 | 2024-11-14 | 2025-05-16 | 2025-05-18 |  | DENNING | 2025-05-09 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 19.8333 | 3 | 1716.51 | 1562.74 | 63.27 | 90.5 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295617000 |  | 100349763 |  | 6744208P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HICKMAN | 114 E HICKMAN ST | 049 | WIN | 2025-04-02 | NRICHIE | U124420 | 2024-11-14 | 2026-03-02 | 2026-03-02 |  | NRICHIE | 2025-04-02 | 2025-03-21 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 11.1167 | 3 | 1318.17 | 759.19 | 181.93 | 45.93 | 331.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295617300 |  | 100349890 |  | 6748204A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ELIZABETH | 17 ELIZABETH ST | 049 | WIN | 2025-03-10 | NRICHIE | U124420 | 2024-11-14 | 2026-02-25 | 2026-02-25 |  | NRICHIE | 2025-03-10 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 7.2333 | 2 | 2062.23 | 543.22 | 142.19 | 31.82 | 1345 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295617900 |  | 100350747 |  | 6744208P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BOONE | 219 BOONE AV | 049 | WIN | 2025-05-29 | U124604 | U124420 | 2024-11-14 | 2025-12-30 | 2025-12-30 |  | NRICHIE | 2025-05-28 | 2025-02-19 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 16.4 | 5 | 2018.83 | 1269.11 | 126.56 | 73.26 | 549.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295618400 |  | 100351129 |  | 6744208P | 1855043 |  |  | 566 | EX | ABANDON SL - SOII/LEGACY | 2621P | COLLEGE | 239 COLLEGE ST | 049 | WIN | 2025-03-21 | U124604 | U124420 | 2024-11-14 | 2025-05-23 | 2025-05-23 |  | NRICHIE | 2025-03-20 | 2025-03-05 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 7.3667 | 4 | 584.54 | 552.18 | 0 | 32.36 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295619700 |  | 100352998 |  | 6744208P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BROADWAY | 154 W BROADWAY ST | 049 | WIN | 2025-04-07 | U930915 | U124420 | 2024-11-14 | 2026-03-09 | 2026-03-09 |  | NRICHIE | 2025-04-04 | 2025-03-21 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 16.15 | 3 | 3145.5 | 1124.98 | 21.09 | 68.33 | 1931.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295619800 |  | 100353040 |  | 6744208P | 1855043 |  |  | 566 | EX | ABANDON SL - SOII/LEGACY | 2621P | BURNS | 43 N BURNS AV | 049 | WIN | 2025-03-18 | NRICHIE | U124420 | 2024-11-14 | 2025-05-08 | 2025-05-08 |  | NRICHIE | 2025-03-18 | 2025-03-05 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9.5 | 4 | 2438.94 | 709.3 | 39.7 | 41.56 | 1648.38 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295620000 |  | 100353211 |  | 7256280K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 2ND | 331< W 2ND ST | 161 | MAY | 2025-03-21 | SDADAMS | U124420 | 2024-11-14 | 2027-08-04 | 2027-08-04 |  | SDADAMS | 2025-03-21 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 8.7667 | 2 | 1813.16 | 638.05 | 39.7 | 37.41 | 1098 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295620100 |  | 100353445 |  | 7256280K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 2ND | 225 W 2ND ST | 161 | MAY | 2025-02-26 | SDADAMS | U124420 | 2024-11-14 | 2026-03-16 | 2026-03-16 |  | SDADAMS | 2025-02-26 | 2025-02-21 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 10.0333 | 4 | 4012.58 | 762.94 | 39.7 | 35.76 | 3174.18 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295620200 |  | 100353457 |  | 7256280K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 2ND | 310 W 2ND ST | 161 | MAY | 2025-02-28 | RALLISO | U124420 | 2024-11-14 | 2026-11-30 | 2026-11-30 |  | RALLISO | 2025-02-28 | 2025-02-21 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 10.2333 | 4 | 2722.71 | 771.52 | 0 | 37.44 | 1913.75 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295620300 |  | 100353461 |  | 7256280K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 2ND | 304 W 2ND ST | 161 | MAY | 2025-03-20 | SDADAMS | U124420 | 2024-11-14 | 2027-06-18 | 2027-06-20 |  | SDADAMS | 2025-03-20 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 10.15 | 2 | 2422.64 | 734.39 | 39.7 | 43.05 | 1605.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295620400 |  | 100353694 |  | 7256280L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 2ND | 47 W 2ND ST | 161 | MAY | 2025-02-27 | U124604 | U124420 | 2024-11-14 | 2025-11-05 | 2025-11-05 |  | SDADAMS | 2025-02-26 | 2025-02-07 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 12.3667 | 5 | 3804.59 | 937.98 | 39.7 | 43.91 | 2783 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295620500 |  | 100353855 |  | 7256280L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MARKET | 204 MARKET ST | 161 | MAY | 2025-03-28 | SDADAMS | U124420 | 2024-11-14 | 2026-03-09 | 2026-03-09 |  | SDADAMS | 2025-03-28 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 15.0667 | 2 | 2518.43 | 1091.91 | 79.27 | 64 | 1283.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295620700 |  | 100354168 |  | 7256280P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 4TH | 366 E 4TH ST | 161 | MAY | 2025-06-05 | U124604 | U124420 | 2024-11-14 | 2027-11-01 | 2027-11-01 |  | RALLISO | 2025-06-04 | 2025-05-20 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 10.6833 | 4 | 1125.24 | 686.74 | 0 | 438.5 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295621200 |  | 100354580 |  | 7260280M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 2ND | 603 E 2ND ST | 161 | MAY | 2025-03-26 | RALLISO | U124420 | 2024-11-14 | 2026-02-23 | 2026-02-23 |  | RALLISO | 2025-03-26 | 2025-03-26 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 6.5167 | 3 | 4248.97 | 474.79 | 0 | 27.83 | 3746.35 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295621300 |  | 100354627 |  | 7260280N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 2ND | 907 E 2ND ST | 161 | MAY | 2025-04-16 | SDADAMS | U124420 | 2024-11-14 | 2027-09-22 | 2027-09-22 |  | SDADAMS | 2025-04-16 | 2025-04-14 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 15.9333 | 6 | 4901.57 | 950.97 | 39.82 | 120.36 | 3790.42 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295621700 |  | 100354938 |  | 7260280M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 2ND | 834 E 2ND ST | 161 | MAY | 2025-03-25 | U930915 | U124420 | 2024-11-14 | 2027-02-23 | 2027-02-23 |  | RALLISO | 2025-03-25 | 2025-03-07 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 23.6 | 6 | 5703.31 | 1711.44 | 0 | 100.31 | 3891.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295621800 |  | 100354967 |  | 7260280M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 2ND | 704 E 2ND ST | 161 | MAY | 2025-02-26 | RALLISO | U124420 | 2024-11-14 | 2026-01-19 | 2026-01-19 |  | RALLISO | 2025-02-26 | 2025-02-07 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 13.9167 | 5 | 6222.02 | 1048.9 | 0 | 49.13 | 5123.99 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295621900 |  | 100355032 |  | 7260280M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 2ND | 410 E 2ND ST | 161 | MAY | 2025-02-26 | RALLISO | U124420 | 2024-11-14 | 2026-01-15 | 2026-01-15 |  | RALLISO | 2025-02-26 | 2025-02-21 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 17.1333 | 5 | 1657.44 | 1300.44 | 25 | 332 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295622000 |  | 100355076 |  | 7260280M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | COMMERCE | 305 COMMERCE ST | 161 | MAY | 2025-04-17 | U930915 | U124420 | 2024-11-14 | 2026-03-24 | 2026-03-24 |  | SDADAMS | 2025-04-17 | 2025-02-12 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 7.0667 | 5 | 1892.87 | 465.25 | 39.82 | 59.52 | 1328.28 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295622500 |  | 100355225 |  | 7260280N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FOREST | 1001 FOREST AV | 161 | MAY | 2025-04-16 | U930915 | U124420 | 2024-11-14 | 2027-03-30 | 2027-03-30 |  | SDADAMS | 2025-04-16 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 0.76667 | 1 | 48.66 | 45.86 | 0 | 2.8 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295622700 |  | 100355338 |  | 7260280N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 306 MAIN ST | 161 | MAY | 2025-03-12 | U930915 | U124420 | 2024-11-14 | 2026-03-13 | 2026-03-15 |  | SDADAMS | 2025-03-12 | 2025-02-10 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 19.8167 | 7 | 1574.53 | 1457.61 | 39.7 | 77.22 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295622800 |  | 100355346 |  | 7260280N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FOREST | 1403 FOREST AV | 161 | MAY | 2025-04-24 | SDADAMS | U124420 | 2024-11-14 | 2027-07-30 | 2027-07-31 |  | SDADAMS | 2025-04-24 | 2025-04-22 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 14.65 | 5 | 5353.06 | 874.03 | 39.82 | 53.34 | 4385.87 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295622900 |  | 100355430 |  | 7260280N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FOREST | 1300 FOREST AV | 161 | MAY | 2025-03-26 | U930915 | U124420 | 2024-11-14 | 2026-11-03 | 2026-11-03 |  | RALLISO | 2025-03-26 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 8.5 | 2 | 5469.12 | 614.81 | 0 | 36.04 | 4818.27 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295623600 |  | 100355678 |  | 7260280N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BUCKNER | 504 BUCKNER ST | 161 | MAY | 2025-04-23 | RALLISO | U124420 | 2024-11-14 | 2026-06-23 | 2026-06-23 |  | RALLISO | 2025-04-23 | 2025-04-23 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 8.75 | 3 | 782.99 | 522.45 | 21.92 | 238.62 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295623700 |  | 100355760 |  | 7260280N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CENTRAL | 434 CENTRAL AV | 161 | MAY | 2025-04-29 | U123688 | U124420 | 2024-11-14 | 2025-12-01 | 2025-12-01 |  | RALLISO | 2025-04-28 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 8.0167 | 2 | 1701.92 | 477.6 | 21.92 | 29.15 | 1173.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295623800 |  | 100355795 |  | 7260276B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CENTRAL | 509 CENTRAL AV | 161 | MAY | 2025-05-12 | RALLISO | U124420 | 2024-11-14 | 2026-06-23 | 2026-06-23 |  | RALLISO | 2025-05-12 | 2025-04-29 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 15.0167 | 3 | 2767.34 | 1038.16 | 77.95 | 59.23 | 1592 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295623900 |  | 100355838 |  | 7260280N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FOREST | 1000 FOREST AV | 161 | MAY | 2025-04-24 | U930915 | U124420 | 2024-11-14 | 2027-07-13 | 2027-07-13 |  | RALLISO | 2025-04-23 | 2025-03-12 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 10.6 | 5 | 2790.36 | 654.85 | 0 | 236.51 | 1899 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295624000 |  | 100355877 |  | 7260276B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WOOD | 512 WOOD ST | 161 | MAY | 2025-05-15 | SDADAMS | U124420 | 2024-11-14 | 2026-08-18 | 2026-08-18 |  | SDADAMS | 2025-05-15 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 18.9167 | 3 | 2884.04 | 1300.41 | 39.82 | 75.31 | 1468.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295624200 |  | 100356065 |  | 7260280N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FOREST | 908 FOREST AV | 161 | MAY | 2025-04-22 | SDADAMS | U124420 | 2024-11-14 | 2027-03-30 | 2027-03-30 |  | SDADAMS | 2025-04-22 | 2025-04-08 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 13.15 | 4 | 3609.51 | 788.02 | 39.82 | 48.08 | 2733.59 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295624300 |  | 100356116 |  | 7260280M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FOREST | 600 FOREST AV | 161 | MAY | 2025-03-05 | U930915 | U124420 | 2024-11-14 | 2026-04-17 | 2026-04-19 |  | SDADAMS | 2025-03-05 | 2025-03-04 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 19.85 | 3 | 2563.47 | 1438.17 | 52.99 | 84.31 | 988 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295624400 |  | 100356165 |  | 7256280G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GERMANTOWN | 644 GERMANTOWN RD | 161 | MAY | 2025-05-02 | U123688 | U124420 | 2024-11-14 | 2026-01-21 | 2026-01-21 |  | RALLISO | 2025-05-01 | 2025-05-01 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 15.0333 | 3 | 1115.41 | 1033.64 | 21.92 | 59.85 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295624500 |  | 100356562 |  | 7260276A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FLEMING | 740 FLEMING RD | 161 | MAY | 2025-02-19 | U930915 | U124420 | 2024-11-14 | 2026-05-05 | 2026-05-05 |  | SDADAMS | 2025-02-19 | 2025-02-12 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 16.1333 | 6 | 3317.14 | 1212.21 | 50.98 | 324.95 | 1729 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295624600 |  | 100356567 |  | 7260276A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FLEMING | 748 FLEMING RD | 161 | MAY | 2025-02-19 | SDADAMS | U124420 | 2024-11-14 | 2026-05-26 | 2026-05-26 |  | SDADAMS | 2025-02-19 | 2025-02-18 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 5.95 | 3 | 2767.29 | 437.97 | 39.7 | 171.87 | 2117.75 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295625000 |  | 100356973 |  | 7256276I |  |  |  | 566 | EX | ABANDON SL/IDLE PEND CN 2/19 | 2621P | DUKE OF YORK | 225 DUKE OF YORK ST | 161 | MAY | 2025-02-19 | SDADAMS | U124420 | 2024-11-14 | 2026-05-27 | 2026-05-27 |  | SDADAMS | 2025-02-19 | 2025-02-12 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 9.7333 | 5 | 863.41 | 734.05 | 50.98 | 78.38 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295625200 |  | 100357205 |  | 7240280G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KY 10 | 4384 KY 10 | 161 | GER | 2025-05-12 | U930915 | U124420 | 2024-11-14 | 2026-05-05 | 2026-05-05 |  | RALLISO | 2025-05-05 | 2025-04-29 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 13.9333 | 3 | 2829.2 | 949.57 | 47.24 | 55.14 | 1777.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295625500 |  | 100357845 |  | 6740232M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | VINE | 639 VINE ST | 017 | PAR | 2025-02-27 | U124604 | U124420 | 2024-11-14 | 2025-12-09 | 2025-12-09 |  | NRICHIE | 2025-02-26 | 2024-12-02 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.3 | 4 | 2042.87 | 464.58 | 39.7 | 22.21 | 1516.38 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295625600 |  | 100357852 |  | 6740232M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | VINE | 539 VINE ST | 017 | PAR | 2025-02-27 | U124604 | U124420 | 2024-11-14 | 2025-09-30 | 2025-09-30 |  | NRICHIE | 2025-02-26 | 2024-12-02 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9.6167 | 6 | 3243.64 | 810.7 | 39.7 | 126.42 | 2266.82 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295627900 |  | 100359344 |  | 6736232P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | VIRGINIA | 135 VIRGINIA AV | 017 | PAR | 2025-04-16 | NRICHIE | U124420 | 2024-11-14 | 2026-04-02 | 2026-04-02 |  | NRICHIE | 2025-04-16 | 2025-03-14 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 11.65 | 5 | 2253.6 | 786.13 | 39.82 | 142.99 | 1284.66 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295628000 |  | 100359345 |  | 6736232P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | VIRGINIA | 139 VIRGINIA AV | 017 | PAR | 2025-04-17 | U930915 | U124420 | 2024-11-14 | 2026-03-31 | 2026-03-31 |  | NRICHIE | 2025-04-16 | 2025-03-14 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.4167 | 3 | 1924.68 | 565.8 | 39.82 | 34.4 | 1284.66 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295628600 |  | 100359921 |  | 6740228A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HIGH | 1431 HIGH ST | 017 | PAR | 2025-02-10 | U930915 | U124420 | 2024-11-14 | 2025-11-19 | 2025-11-19 |  | NRICHIE | 2025-02-10 | 2025-01-14 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.6667 | 3 | 2459.01 | 768.93 | 39.7 | 36.5 | 1613.88 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295629500 |  | 100360435 |  | 6736228H | 2300569 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | SUNSET | 2008 SUNSET DR | 017 | PAR | 2025-04-29 | U126530 | U124420 | 2024-11-14 | 2026-02-20 | 2026-02-22 |  | JDUNN | 2025-04-29 | 2025-02-14 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.46667 | 1 | 1610.87 | 41.64 | 0 | 1.95 | 1567.28 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295630100 |  | 100361066 |  | 6732240H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CYNTHIANA | 1847 CYNTHIANA RD | 017 | PAR | 2025-02-13 | U930915 | U124420 | 2024-11-14 | 2025-12-08 | 2025-12-08 |  | NRICHIE | 2025-02-12 | 2025-01-14 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.95 | 3 | 360.64 | 342.97 | 0 | 17.67 | 0 | 0 | 0 | 0
KY | KY - EAST | 2682 | 24295630700 |  | 501322828 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2633S | ROCKCASTLE | 4836 ROCKCASTLE RD | 159 | INE | 2025-04-17 | U130172 | U124420 | 2024-11-14 | 2027-02-26 | 2027-02-28 |  | JAHOWARD | 2025-04-17 | 2025-03-31 |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 3.15 | 2 | 202.98 | 191.31 | 0 | 11.67 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295630900 |  | 501322537 |  | 6724212M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HAYMAKER | 1730 HAYMAKER PY | 067 | LEX | 2025-02-18 | U930915 | U124420 | 2024-11-14 | 2026-12-17 | 2026-12-17 |  | LSTANFI | 2025-02-17 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 18.3167 | 3 | 1554.11 | 1342.22 | 0 | 211.89 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295631100 |  | 501321819 |  | 6684228 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BERRY HILL | 2015 BERRY HILL DR | 073 | FRA | 2025-01-24 | DCOLLIN | U124420 | 2024-11-14 | 2026-12-09 | 2026-12-09 |  | DCOLLIN | 2025-01-24 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 13.8667 | 2 | 1785.89 | 1078.57 | 0 | 234.82 | 472.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295631200 |  | 501321349 |  | 7260276B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WOOD | 522 WOOD ST APT 2 | 161 | MAY | 2025-05-16 | U124604 | U124420 | 2024-11-14 | 2026-12-11 | 2026-12-13 |  | SDADAMS | 2025-05-15 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 1.45 | 1 | 123.29 | 99.63 | 17.9 | 5.76 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24295631300 |  | 501321306 |  | 7344148T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | STUMBO HOLLOW | 1500 STUMBO HOLLOW RD | 071 | DRI | 2025-03-19 | U130172 | U124420 | 2024-11-14 | 2025-04-01 | 2025-04-01 |  | B PREECE | 2025-03-19 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 4.0833 | 2 | 316.98 | 299.43 | 0 | 17.55 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295631700 |  | 100404509 |  | 6712220M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LEESTOWN | 3805 LEESTOWN RD | 067 | LEX | 2024-12-17 | U930915 | U124420 | 2024-11-14 | 2025-09-16 | 2025-09-16 |  | MCRAIG | 2024-12-16 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.2333 | 3 | 756.25 | 367.25 | 182.35 | 206.65 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295632000 |  | 100405934 |  | 6720216F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RITTENHOUSE | 1880 RITTENHOUSE CT | 067 | LEX | 2024-12-05 | HSTANFI | U124420 | 2024-11-14 | 2025-11-07 | 2025-11-09 |  | HSTANFI | 2024-12-05 | 2024-12-04 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.15 | 4 | 1918.09 | 623.7 | 21.9 | 36.44 | 1236.05 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295632100 |  | 100406088 |  | 7240212J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FULLER | 131 FULLER WY | 173 | MT | 2025-02-13 | U930915 | U124420 | 2024-11-14 | 2025-11-21 | 2025-11-23 |  | DENNING | 2025-02-13 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 21.2 | 3 | 2797.25 | 1939.06 | 62.81 | 795.38 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295632300 |  | 100406518 |  | 6736212K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | POTOMAC | 301 POTOMAC DR | 049 | WIN | 2025-03-14 | U124604 | U124420 | 2024-11-14 | 2026-01-23 | 2026-01-25 |  | NRICHIE | 2025-03-13 | 2025-02-17 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9.8167 | 5 | 2212.46 | 594.97 | 53.33 | 34.28 | 1529.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295632600 |  | 100407490 |  | 6712224L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LISLE | 1169 LISLE RD | 209 | GEO | 2025-02-25 | DCOLLIN | U124420 | 2024-11-14 | 2025-12-11 | 2025-12-11 |  | DCOLLIN | 2025-02-25 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 13.7 | 3 | 3666.15 | 1093.28 | 43.63 | 146.74 | 2382.5 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24295633000 |  | 100408877 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KY FIELD | KY FIELD | 159 | INE | 2025-02-03 | U123688 | U124420 | 2024-11-14 | 2026-03-26 | 2026-03-26 |  | JKIRK | 2025-01-28 | 2025-01-28 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.9833 | 1 | 234.97 | 220.45 | 0 | 14.52 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295633100 |  | 100408943 |  | 6720216F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PENNEBAKER | 1005 PENNEBAKER DR A | 067 | LEX | 2024-12-10 | U930915 | U124420 | 2024-11-14 | 2025-12-09 | 2025-12-09 |  | JOCHOA | 2024-12-09 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 14.1167 | 4 | 1319.19 | 1065.24 | 191.73 | 62.22 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295633500 |  | 100411070 |  | 7240204G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LEVEE | 7315 LEVEE RD | 173 | MT | 2025-01-27 | U930915 | U124420 | 2024-11-14 | 2025-10-27 | 2025-10-27 |  | DENNING | 2025-01-24 | 2025-01-17 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10.8333 | 6 | 3330.71 | 798.11 | 283.57 | 244.47 | 2004.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295634200 |  | 100412060 |  | 7244216F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OLD OWINGSVILL | 3113 OLD OWINGSVILL RD | 173 | MT | 2025-04-03 | DENNING | U124420 | 2024-11-14 | 2026-03-16 | 2026-03-16 |  | DENNING | 2025-04-03 | 2025-04-03 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 21.6333 | 3 | 3373.31 | 1600.89 | 21.09 | 97.58 | 1653.75 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295634400 |  | 100412682 |  | 6700212I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BRYANWOOD | 320 BRYANWOOD ST | 239 | VER | 2025-04-01 | BWHITE | U124420 | 2024-11-14 | 2026-07-06 | 2026-07-06 |  | BWHITE | 2025-04-01 | 2025-01-31 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 23.0333 | 5 | 1877.52 | 1650.49 | 0 | 227.03 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295634500 |  | 100412716 |  | 6716216P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | EARL | 2 EARL CT | 067 | LEX | 2025-04-30 | U930915 | U124420 | 2024-11-14 | 2026-04-06 | 2026-04-06 |  | JBURFOR | 2025-04-30 | 2025-04-30 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.5833 | 3 | 2554.68 | 827.8 | 65.13 | 50.51 | 1611.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295634600 |  | 100412952 |  | 6712212G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | YARMOUTH | 2294 YARMOUTH CT | 067 | LEX | 2025-03-14 | MCRAIG | U124420 | 2024-11-14 | 2026-05-27 | 2026-05-27 |  | MCRAIG | 2025-03-14 | 2025-02-25 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 20.2833 | 5 | 1719.73 | 1198.39 | 70.21 | 451.13 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295634800 |  | 100413961 |  | 6720208H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WOODHILL | 2456 WOODHILL DR | 067 | LEX | 2025-03-11 | U124604 | U124420 | 2024-11-14 | 2026-04-27 | 2026-04-27 |  | HMCKUNE | 2025-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.6 | 3 | 546.11 | 382.97 | 0 | 163.14 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295634900 |  | 100414222 |  | 6720208H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HEDGEWOOD | 261 HEDGEWOOD CT | 067 | LEX | 2025-03-25 | U930915 | U124420 | 2024-11-14 | 2026-10-05 | 2026-10-05 |  | JOCHOA | 2025-03-25 | 2025-03-21 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15 | 6 | 1041.45 | 940.24 | 46.09 | 55.12 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295635100 |  | 100415372 |  | 7256280P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 5TH | 334 E 5TH ST | 161 | MAY | 2025-05-13 | U930915 | U124420 | 2024-11-14 | 2026-12-29 | 2026-12-29 |  | RALLISO | 2025-05-13 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 10.25 | 2 | 745.39 | 704.58 | 0 | 40.81 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295635400 |  | 100421203 |  | 7256280N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | US 68 | 1110 US 68 | 161 | MAY | 2025-04-29 | U123688 | U124420 | 2024-11-14 | 2026-01-20 | 2026-01-20 |  | RALLISO | 2025-04-28 | 2025-03-21 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 12.4833 | 5 | 2178.73 | 786.31 | 0 | 47.42 | 1345 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295635800 |  | 100422272 |  | 6720208M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MOUNDVIEW | 3387 MOUNDVIEW CT 1FR | 067 | LEX | 2025-01-10 | U930915 | U124420 | 2024-11-14 | 2027-06-17 | 2027-06-17 |  | RJCRAWF | 2025-01-08 | 2024-12-27 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 14.95 | 4 | 918.18 | 835.11 | 28.21 | 54.86 | 0 | 0 | 0 | 0
KY | KY - EAST | 2682 | 24295637900 |  | 100427174 |  | 7388156T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2633S | COLLINS BRANCH | 670 COLLINS BRANCH RD | 119 | PIN | 2025-06-20 | U130172 | U124420 | 2024-11-14 | 2026-03-10 | 2026-03-10 |  | J HOWARD | 2025-06-20 | 2025-04-30 |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 15.0167 | 3 | 1015.29 | 958.08 | 0 | 57.21 | 0 | 0 | 0 | 0
KY | KY - EAST | 2682 | 24295638200 |  | 100428111 |  | 111111111 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2633S | RACCOON | 2611 RACCOON RD | 071 | HUE | 2025-02-03 | U130172 | U124420 | 2024-11-14 | 2025-11-17 | 2025-11-17 |  | JOHN HOWARD | 2025-02-03 |  |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 11.6667 | 2 | 968.95 | 925.56 | 0 | 43.39 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295638300 |  | 100428536 |  | 7240204G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LEVEE | 7145 LEVEE RD | 173 | MT | 2025-01-27 | U930915 | U124420 | 2024-11-14 | 2025-11-26 | 2025-11-30 |  | DENNING | 2025-01-24 | 2025-01-17 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 18.3833 | 6 | 3426.26 | 1366.34 | 166.62 | 470.37 | 1422.93 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295639100 |  | 100430590 |  | 6684228J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 2ND | 301 W 2ND ST | 073 | FRA | 2025-02-06 | U124604 | U124420 | 2024-11-14 | 2026-09-17 | 2026-09-17 |  | EFGOINS | 2025-02-05 | 2025-01-31 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 20.6 | 4 | 2138.65 | 1570.11 | 0 | 568.54 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295639600 |  | 100434575 |  | 7256280G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 2ND | 702 W 2ND ST | 161 | MAY | 2025-02-28 | SDADAMS | U124420 | 2024-11-14 | 2026-04-17 | 2026-04-19 |  | SDADAMS | 2025-02-28 | 2025-02-07 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 4.25 | 3 | 4136.41 | 326.19 | 39.7 | 15.27 | 3755.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295639700 |  | 100435587 |  | 7236212L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FOGG | 1475 FOGG PK | 173 | MT | 2025-04-03 | U124604 | U124420 | 2024-11-14 | 2026-02-25 | 2026-02-25 |  | DENNING | 2025-04-02 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.6667 | 3 | 1669.33 | 330.03 | 0 | 104.3 | 1235 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24295640100 |  | 100436765 |  | 7372180T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KY FIELD | KY FIELD | 159 | PIL | 2025-02-10 | U130172 | U124420 | 2024-11-14 | 2025-12-12 | 2025-12-14 |  | J KIRK | 2025-02-10 | 2025-02-07 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 9.6333 | 2 | 881.65 | 842.22 | 0 | 39.43 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295640400 |  | 100438594 |  | 6700220N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MIDWAY | 3566 MIDWAY RD FG17 | 239 | VER | 2025-04-25 | U128410 | U124420 | 2024-11-14 | 2025-10-08 | 2025-10-08 |  | CDESPAIN | 2025-04-25 | 2024-12-03 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 60.9 | 11 | 5862.13 | 4530.3 | 0 | 893.08 | 438.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295640700 |  | 100439917 |  | 6720212G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NEW CIRCLE | 475 E NEW CIRCLE RD | 067 | LEX | 2024-12-24 | U141668 | U124420 | 2024-11-14 | 2025-11-21 | 2025-11-23 |  | LSTANFI | 2024-12-23 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 17.7 | 3 | 2271.54 | 1129.09 | 94.39 | 69.31 | 978.75 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24295640800 |  | 100440107 |  | 7348152T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KY ROUTE 2030 | 5222 KY ROUTE 2030 | 071 | HON | 2025-03-28 | U130172 | U124420 | 2024-11-14 | 2026-12-21 | 2026-12-21 |  | J HOWARD | 2025-03-28 | 2025-02-27 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 16.3 | 3 | 1264.83 | 1194.8 | 0 | 70.03 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295641100 |  | 100441291 |  | 6720208P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ELK LAKE | 3209 ELK LAKE CT | 067 | LEX | 2025-04-10 | HMCKUNE | U124420 | 2024-11-14 | 2026-09-02 | 2026-09-02 |  | HMCKUNE | 2025-04-10 | 2025-04-09 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.1667 | 4 | 487.2 | 432.43 | 6.71 | 48.06 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295643500 |  | 100451998 |  | 6764176K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WINCHESTER | 1041 WINCHESTER RD | 065 | IRV | 2025-03-17 | DENNING | U124420 | 2024-11-14 | 2026-03-16 | 2026-03-16 |  | DENNING | 2025-03-17 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 14.85 | 3 | 2494.4 | 1174.75 | 40.58 | 658.22 | 620.85 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295643800 |  | 100453510 |  | 6712208K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NEVIUS | 3362 NEVIUS DR | 067 | LEX | 2025-01-08 | KKINDER | U124420 | 2024-11-14 | 2026-09-04 | 2026-09-07 |  | KKINDER | 2025-01-08 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 19.9333 | 3 | 1168.05 | 1058.7 | 39.7 | 69.65 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295644100 |  | 100454958 |  | 6748208M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | JACKSON | 224 JACKSON ST 2F | 049 | WIN | 2025-02-28 | U930915 | U124420 | 2024-11-14 | 2026-02-13 | 2026-02-15 |  | NRICHIE | 2025-02-27 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.9333 | 2 | 465.06 | 444.26 | 0 | 20.8 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295644500 |  | 100456883 |  | 6700216N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BIG SINK | 1857 BIG SINK RD FG30 | 239 | VER | 2025-03-19 | U128410 | U124420 | 2024-11-14 | 2027-06-07 | 2027-06-07 |  | CDESPAIN | 2025-03-19 | 2025-01-10 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 60.8833 | 10 | 6117.87 | 4586.76 | 0 | 1531.11 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295644900 |  | 100459672 |  | 6696212G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SPRING RUN | 149 SPRING RUN ST | 239 | VER | 2025-02-07 | U128410 | U124420 | 2024-11-14 | 2027-06-01 | 2027-06-01 |  | CDESPAIN | 2025-02-07 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 9.7333 | 2 | 797.38 | 761.69 | 0 | 35.69 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295645800 |  | 100461380 |  | V92158 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SCARBOROUGH | 499 SCARBOROUGH DR | 239 | VER | 2024-12-30 | U128410 | U124420 | 2024-11-14 | 2027-07-19 | 2027-07-19 |  | CDESPAIN | 2024-12-30 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 14.35 | 2 | 3039.7 | 1127.82 | 0 | 65.88 | 1846 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295646000 |  | 100462105 |  | 6764180P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DRY BRANCH | 346 DRY BRANCH RD | 065 | IRV | 2025-02-13 | U124604 | U124420 | 2024-11-14 | 2025-11-20 | 2025-11-20 |  | DENNING | 2025-02-12 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.4833 | 2 | 234.31 | 138.07 | 0 | 96.24 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295646200 |  | 100462753 |  | 6744208J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DALE | 1335 DALE DR | 049 | WIN | 2024-12-20 | U930915 | U124420 | 2024-11-14 | 2025-11-21 | 2025-11-23 |  | DENNING | 2024-12-19 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 14.7 | 3 | 1946.72 | 1191.83 | 0 | 754.89 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295647400 |  | 100467400 |  | 6720208O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | EDGEWATER | 883 EDGEWATER DR | 067 | LEX | 2024-12-17 | U124604 | U124420 | 2024-11-14 | 2027-05-07 | 2027-05-09 |  | MSHARON | 2024-12-16 | 2024-12-16 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.2333 | 2 | 1175.45 | 365.57 | 21.9 | 21.36 | 766.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295647700 |  | 100468109 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BRECKENRIDGE | 427 BRECKENRIDGE ST | 067 | LEX | 2025-02-13 | BDARNELL | U124420 | 2024-11-14 | 2027-07-07 | 2027-07-07 |  | BDARNELL | 2025-02-13 | 2025-02-13 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.2333 | 3 | 1301.13 | 1083.3 | 21.82 | 196.01 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295647800 |  | 100468404 |  | 6724208I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LOCUST HILL | 115 N LOCUST HILL DR 116 | 067 | LEX | 2024-12-13 | HMCKUNE | U124420 | 2024-11-14 | 2025-12-04 | 2025-12-04 |  | HMCKUNE | 2024-12-13 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 22.95 | 3 | 1704.93 | 1604.81 | 6.38 | 93.74 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295648700 |  | 501294049 |  | 6716228E | 1851303 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BILL PERKINS | 101 BILL PERKINS LN | 209 | GEO | 2025-02-25 | DCOLLIN | U124420 | 2024-11-14 | 2025-12-08 | 2025-12-08 |  | DCOLLIN | 2025-02-25 | 2024-12-18 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 5.5667 | 7 | 661.01 | 432.24 | 118.47 | 110.3 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295648800 |  | 501286773 |  | 6712232O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | M L KING JR | 341 M L KING JR DR | 209 | GEO | 2025-01-16 | U124604 | U124420 | 2024-11-14 | 2025-10-24 | 2025-10-26 |  | DCOLLIN | 2025-01-15 | 2025-01-09 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 20.4667 | 4 | 3103.91 | 1361.74 | 121.43 | 180.74 | 1440 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295648900 |  | 501285810 |  | 6756176O | 2069750 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WINSTON | 310 WINSTON RD | 065 | IRV | 2025-01-14 | U124604 | U124420 | 2024-11-14 | 2025-01-13 | 2027-05-02 |  | DENNING | 2025-01-13 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.15 | 3 | 19.44 | 13.32 | 0 | 6.12 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295649200 |  | 501279361 |  | 6724212M | 1966837 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAYBANK | 1404 MAYBANK PK | 067 | LEX | 2025-05-06 | U930915 | U124420 | 2024-11-14 | 2026-11-02 | 2026-11-02 |  | ABLAKE | 2025-05-06 | 2025-05-01 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 21.5333 | 7 | 1415.69 | 1294.78 | 45.93 | 74.98 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295650300 |  | 501258649 |  | 6712204D | 1850689 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SAYBROOK | 605 SAYBROOK PT | 067 | LEX | 2025-01-03 | U930915 | U124420 | 2024-11-14 | 2025-10-13 | 2025-10-13 |  | KKINDER | 2025-01-02 | 2025-01-02 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16 | 2 | 925.75 | 831.35 | 39.7 | 54.7 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295650700 |  | 501251472 |  | 6728208F | 1748529 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BAY SPRINGS | 3680 BAY SPRINGS PR | 067 | LEX | 2025-03-12 | U124604 | U124420 | 2024-11-14 | 2026-11-23 | 2026-11-23 |  | HMCKUNE | 2025-03-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10.7667 | 3 | 907.77 | 589.93 | 0 | 317.84 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295650800 |  | 501251400 |  | 6728208F | 1748529 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HEMP HILL | 1728 HEMP HILL DR | 067 | LEX | 2025-04-18 | U930915 | U124420 | 2024-11-14 | 2026-07-20 | 2026-07-20 |  | STGOFF | 2025-04-18 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 22.9 | 3 | 1109.12 | 1031.12 | 15.08 | 62.92 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295650900 |  | 501246696 |  | 6716208K | 1859152 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HEATHER | 1928 HEATHER WY | 067 | LEX | 2024-12-31 | U930915 | U124420 | 2024-11-14 | 2025-10-22 | 2025-10-22 |  | RJCRAWF | 2024-12-31 | 2024-12-06 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.4833 | 3 | 461.79 | 436.3 | 0 | 25.49 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295651100 |  | 501245160 |  | 6716216A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LUCILLE | 616 LUCILLE DR | 067 | LEX | 2025-05-30 | TROE | U124420 | 2024-11-14 | 2026-11-30 | 2026-11-30 |  | TROE | 2025-05-30 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.5167 | 3 | 1650.25 | 438.64 | 21.92 | 25.39 | 1164.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295651300 |  | 501240371 |  | 6716216A | 1852616 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OUR TIBBS | 2796 OUR TIBBS TL | 067 | LEX | 2024-12-18 | U930915 | U124420 | 2024-11-14 | 2025-10-23 | 2025-10-23 |  | MCRAIG | 2024-12-18 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.7333 | 3 | 1282.29 | 952.4 | 39.78 | 290.11 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295652200 |  | 501220367 |  | 6724208N | 1746946 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SAWGRASS | 1053 SAWGRASS CV | 067 | LEX | 2025-01-14 | HMCKUNE | U124420 | 2024-11-14 | 2027-05-10 | 2027-05-10 |  | HMCKUNE | 2025-01-14 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.9667 | 2 | 506.03 | 468.48 | 6.71 | 30.84 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295652300 |  | 501220365 |  | 6724208N | 1746946 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SAWGRASS | 1061 SAWGRASS CV | 067 | LEX | 2025-01-17 | U124604 | U124420 | 2024-11-14 | 2027-06-25 | 2027-06-25 |  | HMCKUNE | 2025-01-16 | 2025-01-15 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.9333 | 4 | 469.8 | 440.81 | 0 | 28.99 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295652400 |  | 501217651 |  | 6724212M | 1641397 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | COVINGTON | 1913 COVINGTON DR | 067 | LEX | 2025-06-06 | U930915 | U124420 | 2024-11-14 | 2026-08-05 | 2026-08-05 |  | SSHIMFE | 2025-06-05 | 2025-05-29 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.3667 | 3 | 2359.11 | 400.38 | 39.82 | 23.45 | 1895.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295652500 |  | 501217229 |  | 6708204K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BRANNON | 421 W BRANNON | 113 | NIC | 2025-01-09 | U930915 | U124420 | 2024-11-14 | 2027-02-01 | 2027-02-01 |  | RSTRONG | 2025-01-09 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.7333 | 3 | 444.16 | 349.49 | 0 | 94.67 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295652800 |  | 501201386 |  | 6716220N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SULLIVANS | 2793 SULLIVANS TC | 067 | LEX | 2025-03-28 | U930915 | U124420 | 2024-11-14 | 2026-05-22 | 2026-05-24 |  | JOCHOA | 2025-03-28 | 2025-01-22 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.6667 | 4 | 1180.89 | 1077.87 | 39.7 | 63.32 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295653100 |  | 501199395 |  | 6712216G | 1640823 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MEADOW VALLEY | 204 MEADOW VALLEY RD | 067 | LEX | 2025-02-06 | U930915 | U124420 | 2024-11-14 | 2026-03-09 | 2026-03-09 |  | ABLAKE | 2025-02-06 | 2025-01-02 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.45 | 4 | 1099.01 | 1005.83 | 45.45 | 47.73 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295653400 |  | 501190509 |  | 6680224G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BAMBOO | 127 BAMBOO DR | 073 | FRA | 2025-06-04 | U930915 | U124420 | 2024-11-14 | 2026-08-11 | 2026-08-11 |  | RJCRAWF | 2025-06-03 | 2025-04-04 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 9.6167 | 3 | 3589.53 | 690.41 | 21.09 | 351.85 | 2526.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295653500 |  | 501189841 |  | 6716216A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ESTRELLA | 616 ESTRELLA DR | 067 | LEX | 2025-04-24 | U930915 | U124420 | 2024-11-14 | 2026-10-21 | 2026-10-21 |  | DMEDLEY | 2025-04-24 | 2025-04-21 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 19.3 | 7 | 1402.75 | 1044.41 | 21.92 | 336.42 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295653600 |  | 501189825 |  | 6716216E | 1636328 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ESTRELLA | 584 ESTRELLA DR | 067 | LEX | 2025-02-03 | U930915 | U124420 | 2024-11-14 | 2026-03-19 | 2026-03-19 |  | ABLAKE | 2025-01-31 | 2025-01-22 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.6833 | 3 | 590.66 | 516.97 | 39.7 | 33.99 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24295654400 |  | 501178083 |  | 7328284F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OLD SUNSHINE | 188 OLD SUNSHINE RD | 089 | S S | 2025-02-05 | RECUMP | U124420 | 2024-11-14 | 2025-11-21 | 2025-11-23 |  | RECUMP | 2025-02-05 | 2025-01-31 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 28.1167 | 6 | 2801.34 | 2157.62 | 0 | 643.72 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295654700 |  | 501170998 |  | 6728208E | 1528649 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MILLSTONE | 2188 MILLSTONE WY | 067 | LEX | 2025-04-16 | U124604 | U124420 | 2024-11-14 | 2026-06-10 | 2026-06-10 |  | STGOFF | 2025-04-15 | 2025-04-14 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 18.9167 | 6 | 1121.71 | 974.9 | 15.08 | 131.73 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295654800 |  | 501170984 |  | 6728208E | 1528649 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SWEET CLOVER | 3132 SWEET CLOVER LN | 067 | LEX | 2025-01-30 | U124604 | U124420 | 2024-11-14 | 2026-03-31 | 2026-03-31 |  | HMCKUNE | 2025-01-29 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 19.5667 | 3 | 1224.72 | 1149.14 | 0 | 75.58 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24295655200 |  | 501164132 |  | 7252280O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MCHUGH | 1586 MCHUGH CT | 161 | MAY | 2025-06-09 | U930915 | U124420 | 2024-11-14 | 2025-12-02 | 2025-12-02 |  | RALLISO | 2025-06-09 | 2025-05-01 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 16.35 | 3 | 2098.07 | 1048.62 | 0 | 61.45 | 988 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295655300 |  | 501160796 |  | 6716212K | 1528227 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | EMMALINE | 601 EMMALINE LN | 067 | LEX | 2025-02-17 | U930915 | U124420 | 2024-11-14 | 2025-12-23 | 2025-12-23 |  | JOCHOA | 2025-02-14 | 2024-12-05 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 33.95 | 12 | 3659.98 | 1895.13 | 24.58 | 111.39 | 1628.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295655400 |  | 501152673 |  | 6724208L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | AUTUMN RIDGE | 1192 AUTUMN RIDGE DR | 067 | LEX | 2025-01-16 | U124604 | U124420 | 2024-11-14 | 2025-12-30 | 2025-12-30 |  | LSTANFI | 2025-01-15 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 20.55 | 3 | 1464.52 | 1207.43 | 38.16 | 218.93 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295656000 |  | 501139029 |  | 6724208L | 1316464 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LAWSON | 3333 LAWSON LN | 067 | LEX | 2025-02-20 | U930915 | U124420 | 2024-11-14 | 2025-12-02 | 2025-12-02 |  | LSTANFI | 2025-02-20 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.2167 | 3 | 2600.76 | 1015.7 | 0 | 52.18 | 1532.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295656100 |  | 501139027 |  | 6724208L | 1316464 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LAWSON | 3326 LAWSON LN | 067 | LEX | 2025-03-05 | U930915 | U124420 | 2024-11-14 | 2026-01-23 | 2026-01-25 |  | HMCKUNE | 2025-03-04 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.8833 | 3 | 499.7 | 370.26 | 0 | 129.44 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295656200 |  | 501139002 |  | 6724208L | 1316464 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KAVENAUGH | 1116 KAVENAUGH LN | 067 | LEX | 2025-03-14 | U124604 | U124420 | 2024-11-14 | 2026-06-10 | 2026-06-10 |  | HMCKUNE | 2025-03-13 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10.4667 | 4 | 976.01 | 610.67 | 0 | 365.34 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295656600 |  | 501097934 |  | 6724208E | 1102270 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SUNFLOWER | 3771 SUNFLOWER ST | 067 | LEX | 2025-01-17 | U123688 | U124420 | 2024-11-14 | 2026-01-16 | 2026-01-18 |  | HMCKUNE | 2025-01-16 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10.7333 | 2 | 566.89 | 531.88 | 0 | 35.01 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295656700 |  | 501097919 |  | 6724208E | 1102270 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SUNFLOWER | 3712 SUNFLOWER CT | 067 | LEX | 2025-01-09 | HMCKUNE | U124420 | 2024-11-14 | 2026-03-25 | 2026-03-25 |  | HMCKUNE | 2025-01-09 | 2025-01-08 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 24.85 | 8 | 1644.87 | 1269.18 | 20.28 | 355.41 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295656900 |  | 501097842 |  | 6728208E | 1102270 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FALLING LEAVES | 2001 FALLING LEAVES LN | 067 | LEX | 2025-01-10 | HMCKUNE | U124420 | 2024-11-14 | 2027-04-14 | 2027-04-14 |  | HMCKUNE | 2025-01-10 | 2025-01-08 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 32.75 | 10 | 2228.49 | 1674.46 | 21.82 | 532.21 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295657000 |  | 501097815 |  | 6724208E | 1102270 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FALLING LEAVES | 3009 FALLING LEAVES LN | 067 | LEX | 2025-01-20 | U124604 | U124420 | 2024-11-14 | 2026-04-02 | 2026-04-02 |  | HMCKUNE | 2025-01-17 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 14.3 | 2 | 754.77 | 708.17 | 0 | 46.6 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295657200 |  | 501094581 |  | 6724212I | 0991247 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BATTERY | 1839 BATTERY ST | 067 | LEX | 2025-03-24 | U930915 | U124420 | 2024-11-14 | 2026-01-13 | 2026-01-13 |  | LSTANFI | 2025-03-21 | 2025-01-03 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 26.4667 | 7 | 3212.81 | 1697.72 | 15.07 | 288.86 | 1211.16 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24295657700 |  | 501088360 |  | 7360248A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PARK | 3732 PARK ST | 019 | CAT | 2025-04-22 | MCOLLET | U124420 | 2024-11-14 | 2025-12-16 | 2025-12-16 |  | MCOLLET | 2025-04-22 | 2025-02-13 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 9.7833 | 3 | 1777.33 | 711.72 | 21.09 | 1044.52 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295657900 |  | 501057386 |  | 6728208A | 0677737 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BLACKFORD | 3056 BLACKFORD PY | 067 | LEX | 2025-03-10 | U124604 | U124420 | 2024-11-14 | 2026-04-16 | 2026-04-16 |  | HMCKUNE | 2025-03-07 | 2025-03-07 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10.6333 | 3 | 873.73 | 615.86 | 0 | 257.87 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295658100 |  | 501025887 |  | 6696216J | 1207420 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FRANKFORT | 3450 FRANKFORT RD UK 3740 | 239 | VER | 2025-03-06 | BWHITE | U124420 | 2024-11-14 | 2026-06-08 | 2026-06-08 |  | BWHITE | 2025-03-06 | 2025-01-08 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 7.8167 | 3 | 722.47 | 590.73 | 0 | 131.74 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295658200 |  | 501015979 |  | 6688228K | 0779465 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BRIGHTON PARK | 108 BRIGHTON PARK BV | 073 | FRA | 2025-03-05 | DCOLLIN | U124420 | 2024-11-14 | 2026-07-15 | 2026-07-15 |  | DCOLLIN | 2025-03-05 | 2025-02-19 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 4.8667 | 4 | 533.79 | 401.86 | 0 | 131.93 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295658700 |  | 500972418 |  | 6724204H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | STUART HALL | 4372 STUART HALL BV | 067 | LEX | 2025-04-28 | U930915 | U124420 | 2024-11-14 | 2026-08-20 | 2026-08-20 |  | STGOFF | 2025-04-28 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.0333 | 3 | 620.01 | 584.33 | 0 | 35.68 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295658800 |  | 500949525 |  | 6716204P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FIDDLER CREEK | 936 FIDDLER CREEK WY | 067 | LEX | 2025-06-06 | JGILES | U124420 | 2024-11-14 | 2026-10-09 | 2026-10-11 |  | JGILES | 2025-06-06 | 2025-05-14 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 14.5833 | 7 | 2573.05 | 912.1 | 0 | 82.71 | 1578.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295658900 |  | 500939514 |  | 6712208G | 0567538 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BEAUMONT CENTR | 3331 BEAUMONT CENTR CI | 067 | LEX | 2024-12-31 | U124604 | U124420 | 2024-11-14 | 2027-07-19 | 2027-07-19 |  | KOBRYAN | 2024-12-30 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.5 | 3 | 789.53 | 745.96 | 0 | 43.57 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295659000 |  | 500939511 |  | 6712208G | 0567538 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BEAUMONT CENTR | 3325 BEAUMONT CENTR CI | 067 | LEX | 2024-12-31 | U124604 | U124420 | 2024-11-14 | 2027-02-26 | 2027-02-28 |  | KOBRYAN | 2024-12-30 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.75 | 3 | 832.37 | 786.43 | 0 | 45.94 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295659100 |  | 500939498 |  | 6712208G | 0567538 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | VERANDAH | 3271 VERANDAH PL | 067 | LEX | 2025-02-26 | U124604 | U124420 | 2024-11-14 | 2026-03-25 | 2026-03-25 |  | KKINDER | 2025-02-25 | 2025-02-07 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 20.7667 | 6 | 1685.08 | 1552.71 | 39.7 | 92.67 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295659400 |  | 500009762 |  | 6716204K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FOX HARBOUR | 421 FOX HARBOUR DR | 067 | LEX | 2025-04-22 | U124604 | U124420 | 2024-11-14 | 2026-09-23 | 2026-09-23 |  | JOCHOA | 2025-04-21 | 2025-04-16 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 20.25 | 6 | 1285.34 | 1173.84 | 39.82 | 71.68 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295659700 |  | 500017361 |  | 6728200D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ATHENS BOONESB | 6434 ATHENS BOONESB RD | 067 | LEX | 2025-01-13 | U930915 | U124420 | 2024-11-14 | 2026-06-26 | 2026-06-28 |  | STGOFF | 2025-01-13 | 2025-01-13 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 19.8 | 3 | 1351.76 | 1238.83 | 31.41 | 81.52 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295659800 |  | 500020605 |  | 6720208D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DOWNS | 707 DOWNS AV | 067 | LEX | 2025-02-24 | U930915 | U124420 | 2024-11-14 | 2026-10-02 | 2026-10-04 |  | LSTANFI | 2025-02-21 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 23.8333 | 3 | 1886.54 | 1643.73 | 0 | 242.81 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295659900 |  | 500020659 |  | 7244216E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FLINT | 306 FLINT DR | 173 | MT | 2025-03-06 | DENNING | U124420 | 2024-11-14 | 2026-02-20 | 2026-02-22 |  | DENNING | 2025-03-06 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 11.1667 | 2 | 1621.38 | 897.92 | 0 | 723.46 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295660500 |  | 500026883 |  | 6684228F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KENTUCKY | 613 KENTUCKY AV | 073 | FRA | 2024-12-09 | KKINDER | U124420 | 2024-11-14 | 2026-01-14 | 2026-01-14 |  | KKINDER | 2024-12-09 | 2024-12-09 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 18.1833 | 3 | 1393.53 | 1293.7 | 24.26 | 75.57 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295660800 |  | 500047988 |  | 6712212K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DEVONPORT | 1364 DEVONPORT DR | 067 | LEX | 2025-01-30 | U124604 | U124420 | 2024-11-14 | 2026-03-16 | 2026-03-16 |  | CHEMMER | 2025-01-29 | 2025-01-29 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.45 | 3 | 764.58 | 680.11 | 39.7 | 44.77 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24295660900 |  | 500049334 |  | 7352260P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WINCHESTER | 500 WINCHESTER AV SP 434 | 019 | ASH | 2025-05-15 | U124604 | U124420 | 2024-11-14 | 2025-10-10 | 2025-10-12 |  | ABHATFIE | 2025-05-14 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 8.1333 | 2 | 615.87 | 582.14 | 0 | 33.73 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295661100 |  | 500910064 |  | 6728208A | 0462539 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CHERRY MEADOW | 3172 CHERRY MEADOW PA | 067 | LEX | 2025-03-24 | U930915 | U124420 | 2024-11-14 | 2027-04-01 | 2027-04-01 |  | HMCKUNE | 2025-03-21 | 2025-03-17 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 29.2 | 6 | 1883.98 | 1676.7 | 0 | 207.28 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295663200 |  | 500141448 |  | 6720204M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | JAIRUS | 983 JAIRUS DR | 067 | LEX | 2025-04-29 | U930915 | U124420 | 2024-11-14 | 2026-09-02 | 2026-09-02 |  | RJCRAWF | 2025-04-29 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.3167 | 3 | 905.84 | 816.22 | 39.82 | 49.8 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295663600 |  | 500165371 |  | 6720204J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | THAMES | 1633 THAMES DR | 067 | LEX | 2025-04-02 | RJCRAWF | U124420 | 2024-11-14 | 2026-05-12 | 2026-05-12 |  | RJCRAWF | 2025-04-02 | 2025-04-02 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.4167 | 2 | 419.45 | 395.32 | 0 | 24.13 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24295664400 |  | 500188425 |  | 7356216B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | US 23 | 505 US 23 | 089 | GRE | 2025-04-01 | RECUMP | U124420 | 2024-11-14 | 2027-04-09 | 2027-04-11 |  | RECUMP | 2025-04-01 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 14.3167 | 2 | 1218.57 | 948.11 | 20.28 | 250.18 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295664700 |  | 500203940 |  | 6720204J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | STEPHEN FOSTER | 1457 STEPHEN FOSTER DR | 067 | LEX | 2024-12-23 | U930915 | U124420 | 2024-11-14 | 2026-01-21 | 2026-01-21 |  | RJCRAWF | 2024-12-23 | 2024-12-23 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.7 | 3 | 806.12 | 724.05 | 39.78 | 42.29 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295665100 |  | 500219312 |  | 6716212D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CHARLES | 724 CHARLES AV | 067 | LEX | 2025-02-10 | DJOHNSON | U124420 | 2024-11-14 | 2026-09-23 | 2026-09-23 |  | DJOHNSON | 2025-02-10 | 2025-02-10 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 14.0667 | 3 | 988.21 | 840.89 | 39.7 | 107.62 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24295665300 |  | 500222192 |  | 7352256L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BEECH | 2315 BEECH ST 19 | 019 | ASH | 2025-05-01 | U123688 | U124420 | 2024-11-14 | 2026-07-06 | 2026-07-06 |  | RECUMP | 2025-04-30 | 2025-03-24 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 11.9 | 3 | 991.02 | 743.5 | 21.09 | 226.43 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295665600 |  | 500873755 |  | 6716204L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WAXWING | 610 WAXWING WY | 067 | LEX | 2025-02-18 | U124604 | U124420 | 2024-11-14 | 2026-02-23 | 2026-02-23 |  | MSHARON | 2025-02-17 | 2025-02-10 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.8 | 5 | 1227.23 | 1172.27 | 0 | 54.96 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295665800 |  | 500248735 |  | 6712208J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PALOMAR TRACE | 2177 PALOMAR TRACE DR | 067 | LEX | 2025-03-10 | U124604 | U124420 | 2024-11-14 | 2026-11-06 | 2026-11-08 |  | KKINDER | 2025-03-07 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.4333 | 2 | 1096.28 | 1018.69 | 17.88 | 59.71 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295666600 |  | 500300723 |  | 6712204D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FRASERDALE | 3421 FRASERDALE DR | 067 | LEX | 2025-02-11 | U930915 | U124420 | 2024-11-14 | 2027-03-25 | 2027-03-25 |  | KOBRYAN | 2025-02-10 | 2025-01-10 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.85 | 4 | 802.79 | 769.55 | 0 | 33.24 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295666800 |  | 500309341 |  | 6728208M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DEER CROSSING | 933 DEER CROSSING WY | 067 | LEX | 2025-02-28 | U124604 | U124420 | 2024-11-14 | 2027-10-04 | 2027-10-04 |  | HMCKUNE | 2025-02-27 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.2333 | 2 | 207.02 | 197.74 | 0 | 9.28 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24295667200 |  | 500335680 |  | 7348248E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | VIRGINIA | 12165 VIRGINIA BV BLDG 2 | 019 | ASH | 2025-04-15 | ABHATFIE | U124420 | 2024-11-14 | 2027-02-09 | 2027-02-09 |  | ABHATFIE | 2025-04-15 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 18 | 2 | 1294.73 | 1220.27 | 0 | 74.46 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295667500 |  | 500345693 |  | 6680224G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LOUISVILLE | 1520 LOUISVILLE RD J | 073 | FRA | 2025-04-09 | BSEXTON | U124420 | 2024-11-14 | 2026-10-28 | 2026-10-28 |  | BSEXTON | 2025-04-09 | 2025-04-09 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 7.6667 | 2 | 2760.08 | 473.65 | 0 | 28.93 | 2257.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295667900 |  | 500351028 |  | 6724208K | 9402231 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FOREST HILL | 264 FOREST HILL DR | 067 | LEX | 2025-05-01 | U123688 | U124420 | 2024-11-14 | 2026-10-02 | 2026-10-02 |  | STGOFF | 2025-04-30 | 2025-04-30 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.2167 | 3 | 660.22 | 605.36 | 17.9 | 36.96 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295668100 |  | 500357924 |  | 6716212M | 9403253 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CHANDLER | 1765 CHANDLER LN | 067 | LEX | 2024-12-20 | U930915 | U124420 | 2024-11-14 | 2026-10-08 | 2026-10-08 |  | BYOUNG2 | 2024-12-19 | 2024-12-05 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.9167 | 3 | 873.83 | 825.61 | 0 | 48.22 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295668300 |  | 500372629 |  | 6696212K | 9403239 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | POCAHONTAS | 621 POCAHONTAS TL | 239 | VER | 2024-12-27 | BWHITE | U124420 | 2024-11-14 | 2026-09-08 | 2026-09-08 |  | BWHITE | 2024-12-27 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 7.9667 | 3 | 1959.25 | 617.2 | 0 | 36.05 | 1306 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295668400 |  | 500372630 |  | 6696212K | 9403239 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | POCAHONTAS | 619 POCAHONTAS TL | 239 | VER | 2024-12-27 | BWHITE | U124420 | 2024-11-14 | 2026-09-08 | 2026-09-08 |  | BWHITE | 2024-12-27 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 1.9833 | 3 | 162.64 | 153.65 | 0 | 8.99 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295668600 |  | 500376111 |  | 6720208M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MONTAVESTA | 3390 MONTAVESTA RD | 067 | LEX | 2024-12-04 | U123688 | U124420 | 2024-11-14 | 2025-12-12 | 2025-12-14 |  | RJCRAWF | 2024-12-03 | 2024-11-25 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.5833 | 4 | 930.09 | 841.12 | 39.78 | 49.19 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295669400 |  | 500414716 |  | 6712204D | 2288473 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FRASERDALE | 3405 FRASERDALE DR | 067 | LEX | 2025-02-10 | WBURGESS | U124420 | 2024-11-14 | 2027-10-11 | 2027-10-11 |  | WBURGESS | 2025-02-10 | 2025-01-10 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.6333 | 3 | 310.65 | 295.59 | 0 | 15.06 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295670300 |  | 500454750 |  | 6764172D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RIVER | 701 RIVER DR | 065 | IRV | 2024-12-18 | DENNING | U124420 | 2024-11-14 | 2025-11-19 | 2025-11-19 |  | DENNING | 2024-12-18 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 24 | 3 | 3968.86 | 1961.5 | 259.29 | 114.57 | 1633.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24295670900 |  | 500461835 |  | 7356256M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RANDY | 3458 RANDY DR | 019 | ASH | 2025-02-13 | U124604 | U124420 | 2024-11-14 | 2025-10-07 | 2025-10-07 |  | JKEENER | 2025-02-12 | 2025-02-07 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 9.7 | 4 | 844.91 | 807.09 | 0 | 37.82 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295671000 |  | 500467899 |  | 6708232H | 9506169 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MONTICELLO | 105 MONTICELLO DR | 209 | GEO | 2025-02-27 | U124604 | U124420 | 2024-11-14 | 2026-02-27 | 2026-03-01 |  | DCOLLIN | 2025-02-26 | 2025-01-31 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 13.1 | 4 | 1292.42 | 979.97 | 110.3 | 202.15 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295671200 |  | 500472481 |  | 6720212K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | INDUSTRY | 1039 INDUSTRY RD | 067 | LEX | 2025-03-14 | U124604 | U124420 | 2024-11-14 | 2026-11-02 | 2026-11-02 |  | LSTANFI | 2025-03-13 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 14.15 | 5 | 2543.56 | 847.24 | 0 | 133.44 | 1562.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295671400 |  | 500492322 |  | 6712216G | 9613267 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | TRAILSIDE | 3008 TRAILSIDE DR | 067 | LEX | 2025-02-07 | JBURFOR | U124420 | 2024-11-14 | 2026-09-17 | 2026-09-17 |  | JBURFOR | 2025-02-07 | 2025-01-24 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 22.1167 | 4 | 1446.84 | 1381.94 | 0 | 64.9 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295671900 |  | 500819798 |  | 6716208B | 0253080 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WALLER | 386 WALLER AV CABLE | 067 | LEX | 2025-02-13 | HSTANFI | U124420 | 2024-11-14 | 2027-03-12 | 2027-03-14 |  | HSTANFI | 2025-02-13 | 2025-02-13 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 31.4333 | 4 | 2390.15 | 1888.69 | 52.99 | 88.47 | 360 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24295672200 |  | 500516417 |  | 7356256M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | TERRACE | 2838 TERRACE BV | 019 | ASH | 2025-05-30 | U124604 | U124420 | 2024-11-14 | 2026-03-16 | 2026-03-16 |  | ABHATFIE | 2025-05-29 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 8 | 2 | 608.01 | 574.72 | 0 | 33.29 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295672300 |  | 500516428 |  | 6712204K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SPRING RUN | 988 SPRING RUN RD | 067 | LEX | 2025-01-17 | U930915 | U124420 | 2024-11-14 | 2026-04-14 | 2026-04-14 |  | JBURFOR | 2025-01-16 | 2025-01-16 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10.25 | 3 | 543.6 | 510.02 | 0 | 33.58 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295672500 |  | 500526277 |  | 6724208A | 9614073 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CHIMNEY POINT | 2420 CHIMNEY POINT LN | 067 | LEX | 2025-03-14 | U124604 | U124420 | 2024-11-14 | 2026-08-17 | 2026-08-17 |  | HMCKUNE | 2025-03-13 | 2025-03-12 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.7833 | 7 | 808.21 | 514.37 | 0 | 293.84 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295672700 |  | 500536758 |  | 6748212M | 9613807 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WINTERBERRY | 114 WINTERBERRY CR | 049 | WIN | 2025-04-11 | U930915 | U124420 | 2024-11-14 | 2026-01-15 | 2026-01-15 |  | LCLARK | 2025-04-10 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9.0333 | 2 | 1203.38 | 645.33 | 0 | 558.05 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295673500 |  | 500573923 |  | 6724208E | 9721496 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HUGGING BEAR | 661 HUGGING BEAR DR | 067 | LEX | 2025-03-05 | U930915 | U124420 | 2024-11-14 | 2026-02-23 | 2026-02-23 |  | HMCKUNE | 2025-03-04 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.05 | 3 | 956.41 | 678.98 | 0 | 277.43 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295673600 |  | 500573969 |  | 6724208E | 9721496 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SMUGGLERS NOTC | 673 SMUGGLERS NOTC DR | 067 | LEX | 2025-06-04 | STGOFF | U124420 | 2024-11-14 | 2026-12-02 | 2026-12-02 |  | STGOFF | 2025-06-04 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.2167 | 3 | 763.23 | 706.68 | 15.08 | 41.47 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295673700 |  | 500574325 |  | 6724208E | 9721496 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | TINMOUTH VALE | 2525 TINMOUTH VALE LN | 067 | LEX | 2025-01-28 | U124604 | U124420 | 2024-11-14 | 2026-03-30 | 2026-03-30 |  | HMCKUNE | 2025-01-27 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10.7333 | 2 | 929.63 | 633.75 | 0 | 295.88 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295673800 |  | 500575058 |  | 6708232L | 9720403 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | COLONIAL HEIGH | 123 S COLONIAL HEIGH DR | 209 | GEO | 2025-01-15 | DCOLLIN | U124420 | 2024-11-14 | 2026-04-21 | 2026-04-21 |  | DCOLLIN | 2025-01-15 | 2025-01-14 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 12.3333 | 5 | 2631.39 | 835.29 | 0 | 80.6 | 1715.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295674000 |  | 500575079 |  | 6708232L | 9720403 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | COLONIAL HEIGH | 102 S COLONIAL HEIGH DR | 209 | GEO | 2025-01-15 | U124604 | U124420 | 2024-11-14 | 2026-05-04 | 2026-05-04 |  | DCOLLIN | 2025-01-14 | 2024-12-20 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 23.2333 | 5 | 4186.01 | 1590.91 | 18.89 | 355.71 | 2220.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295674300 |  | 500588934 |  | 6712216H | 9723002 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DEERFIELD | 284 DEERFIELD LN | 067 | LEX | 2025-02-17 | WBURGESS | U124420 | 2024-11-14 | 2026-02-20 | 2026-02-22 |  | WBURGESS | 2025-02-17 | 2025-01-14 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.8167 | 4 | 1056.24 | 1008.9 | 0 | 47.34 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24295674400 |  | 500589119 |  | 6712228J | 9723374 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DICKINSON | 106 DICKINSON DR | 209 | GEO | 2025-03-17 | U124604 | U124420 | 2024-11-14 | 2026-04-20 | 2026-04-20 |  | DCOLLIN | 2025-03-14 | 2025-03-11 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 16.4333 | 5 | 1622.96 | 1319.08 | 0 | 303.88 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295674800 |  | 500795819 |  | 6712216D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HAVANA | 604 HAVANA CT LT104 | 067 | LEX | 2025-05-27 | DMEDLEY | U124420 | 2024-11-14 | 2026-11-20 | 2026-11-22 |  | DMEDLEY | 2025-05-27 | 2025-05-16 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.7167 | 6 | 1437.9 | 997.73 | 0 | 440.17 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295676000 |  | 500654154 |  | 6712208B | 9829045 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ALLEGHENY | 2132 ALLEGHENY WY | 067 | LEX | 2025-01-15 | U930915 | U124420 | 2024-11-14 | 2026-02-20 | 2026-02-22 |  | KKINDER | 2025-01-15 | 2024-12-24 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 19.3833 | 5 | 3053.79 | 1321.21 | 0 | 222.2 | 1510.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295676100 |  | 500654171 |  | 6712208C | 9829045 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ALLEGHENY | 2080 ALLEGHENY WY | 067 | LEX | 2024-12-30 | U124604 | U124420 | 2024-11-14 | 2026-03-25 | 2026-03-25 |  | KOBRYAN | 2024-12-27 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 19.1 | 3 | 1546.26 | 1460.94 | 0 | 85.32 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24295676300 |  | 500656118 |  | 7240216E | 9831114 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GREENFIELD | 817 GREENFIELD TL | 173 | MT | 2025-04-14 | U930915 | U124420 | 2024-11-14 | 2025-10-30 | 2025-10-30 |  | LCLARK | 2025-04-11 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9 | 2 | 1203.38 | 645.33 | 0 | 558.05 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295676400 |  | 500679201 |  | 6716208M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SEVERN | 433 SEVERN WY | 067 | LEX | 2025-02-10 | U930915 | U124420 | 2024-11-14 | 2027-04-08 | 2027-04-08 |  | KKINDER | 2025-02-07 | 2025-01-24 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.7833 | 5 | 1317.91 | 1153.63 | 0 | 164.28 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295676600 |  | 500690085 |  | 6724208F | 9934174 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RED LEAF | 2812 RED LEAF DR | 067 | LEX | 2025-03-07 | U930915 | U124420 | 2024-11-14 | 2026-04-08 | 2026-04-08 |  | HMCKUNE | 2025-03-07 | 2025-01-20 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 21.6833 | 7 | 1476.43 | 1122.65 | 0 | 353.78 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295676900 |  | 500696882 |  | 6720208I | 9827364 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CLAIR | 3063 CLAIR RD | 067 | LEX | 2025-03-04 | U124604 | U124420 | 2024-11-14 | 2027-06-30 | 2027-06-30 |  | JOCHOA | 2025-03-03 | 2025-01-29 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 23.9833 | 8 | 1554.19 | 1430.21 | 39.7 | 84.28 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295677000 |  | 500704082 |  | 6712208J | 9616897 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ROBINHILL | 3573 ROBINHILL WY | 067 | LEX | 2025-02-10 | U930915 | U124420 | 2024-11-14 | 2026-07-10 | 2026-07-12 |  | KKINDER | 2025-02-10 | 2025-01-10 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 18.7833 | 6 | 1558.9 | 1356.6 | 39.7 | 162.6 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295677100 |  | 500704097 |  | 6724208H | 9935860 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ROYAL TROON | 3317 ROYAL TROON RD | 067 | LEX | 2025-04-28 | STGOFF | U124420 | 2024-11-14 | 2026-08-17 | 2026-08-17 |  | STGOFF | 2025-04-28 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.8333 | 3 | 746.39 | 672.37 | 32.98 | 41.04 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295677500 |  | 500712316 |  | 6716204P | 9933613 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MARBELLA | 917 MARBELLA LN | 067 | LEX | 2025-02-11 | U124604 | U124420 | 2024-11-14 | 2026-04-29 | 2026-04-29 |  | MSHARON | 2025-02-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.85 | 2 | 565.95 | 540.59 | 0 | 25.36 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295678000 |  | 500749506 |  | 6708204K | 0144034 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BRANNON | 411 W BRANNON RD | 113 | NIC | 2025-01-06 | U930915 | U124420 | 2024-11-14 | 2025-12-22 | 2025-12-22 |  | RSTRONG | 2025-01-03 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 22.5667 | 3 | 1408.08 | 1195.3 | 0 | 212.78 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24295678700 |  | 500777591 |  | 6712216H | 2177177 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MABLE | 2708 MABLE LN | 067 | LEX | 2025-06-19 | U930915 | U124420 | 2024-11-14 | 2027-04-05 | 2027-04-05 |  | KOBRYAN | 2025-06-19 | 2025-06-06 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.4833 | 4 | 798.5 | 754.25 | 0 | 44.25 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24296122200 |  | 100270602 |  | 6736248A |  |  |  | 563 | EX | 1" P LONG | 2621P | OLD LAIR | 127 OLD LAIR RD | 097 | CYN | 2024-11-26 | U141668 | U132627 | 2024-11-15 | 2024-11-18 | 2024-12-03 |  | NRICHIE | 2024-11-25 | 2024-11-15 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 20.8167 | 4 | 2688.02 | 1655.5 | 349.04 | 337.16 | 346.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24296132200 |  | 500035589 |  | 6720208I | 2410325 |  |  | 563 | EX | 1" P SHORT/PRMT RCVD | 2600B | TALLY | 624 TALLY RD | 067 | LEX | 2024-12-13 | U126602 | U126856 | 2024-11-15 | 2024-12-02 | 2024-12-13 |  | DEREK PAYTON | 2024-12-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1821.72 | 0 | 674.52 | 0 | 1147.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24296141000 |  | 501094565 |  | 6724212I | 0991247 |  |  | 563 | EX | 99 1" P SHORT/PRMT RCVD | 2600B | BATTERY | 1748 BATTERY ST LT24 | 067 | LEX | 2024-12-11 | U461516 | U120250 | 2024-11-15 | 2024-12-02 | 2024-12-13 |  | NEAL JOHNSON | 2024-12-11 |  | 2024-12-11 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 1.9167 | 1 | 2235.52 | 141.67 | 311.23 | 166.78 | 1615.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24296175600 |  | 500774121 |  | 6688232N | 0147140 |  |  | 563 | EX | 1" P LONG/PRMT RCVD | 2600B | TETON | 801 TETON TL | 073 | FRA | 2024-12-09 | U123111 | U128272 | 2024-11-15 | 2024-11-22 | 2024-12-09 |  | LYN STAFFORD | 2024-12-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 5416.21 | 643 | 306.44 | 37.56 | 4429.21 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24296191800 |  | 100334918 |  | 6720212P |  |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | NEW CIRCLE | 1087 E NEW CIRCLE RD STE 2 | 067 | LEX | 2024-11-25 | U126285 | U132815 | 2024-11-15 | 2024-11-19 | 2024-12-03 |  | DUSTIN DAVIS | 2024-11-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1393.21 | 0 | 0 | 0 | 1393.21 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24296262500 |  | 501150515 |  | 6708228C | 1421257 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | QUAIL HOLLOW | 199 QUAIL HOLLOW DR LT127 | 209 | GEO | 2024-12-03 | U126284 | U130192 | 2024-11-18 | 2024-11-22 | 2024-12-09 |  | JOSH PASLEY | 2024-12-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 3.9833 | 1 | 2471.5 | 347.79 | 0 | 20.32 | 2103.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24296279800 |  | 500626770 |  | 6728204K | 9830478 |  |  | 563 | EX | 1"P SHORT/PRMT RCVD | 2600B | CUTTERS HILL | 370 CUTTERS HILL CT | 067 | LEX | 2024-12-12 | U123111 | U132253 | 2024-11-18 | 2024-12-02 | 2024-12-13 |  | LYN STAFFORD | 2024-12-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 4052.58 | 0 | 311.23 | 0 | 3741.35 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24296280100 |  | 500633332 |  | 6728204K | 9830479 |  |  | 563 | EX | 1"P SHORT/PRMT RCVD | 2600B | CUTTERS HILL | 380 CUTTERS HILL CT | 067 | LEX | 2024-12-12 | U123111 | U132253 | 2024-11-18 | 2024-12-02 | 2024-12-13 |  | LYN STAFFORD | 2024-12-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1388.47 | 0 | 222.39 | 0 | 1166.08 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24296287200 |  | 100281462 |  | 6712232N |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTRQD | 2621P | GANO | 123 GANO AV | 209 | GEO | 2025-01-02 | DCOLLIN | U140273 | 2024-11-18 | 2024-12-16 | 2025-01-09 |  | DCOLLIN | 2025-01-02 | 2024-12-16 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 26.9333 | 7 | 3457.09 | 1894.94 | 0 | 542.15 | 1020 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24296308400 |  | 501329621 |  | 6712208N |  |  |  | 563 | EX | 1"P- LONG/PRMT RCVD | 2600B | BRAVINGTON | 917 BRAVINGTON WY | 067 | LEX | 2024-12-13 | U461516 | U128727 | 2024-11-18 | 2024-12-02 | 2024-12-13 |  | NEAL JOHNSON | 2024-12-13 |  | 2024-12-13 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 6272.81 | 587.16 | 300.06 | 691.33 | 4694.26 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24296312200 |  | 100343665 |  | V122241 |  |  |  | 563 | EX | 1" P LONG | 2621P | LOCUST | 246 W LOCUST ST | 173 | MT | 2024-11-26 | DENNING | U134341 | 2024-11-18 | 2024-12-02 | 2024-12-02 |  | DENNING | 2024-11-26 | 2024-11-20 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 51.8 | 6 | 5972.2 | 4269.63 | 394.34 | 346.23 | 962 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24296313100 |  | 100343138 |  | 7236212D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SHELIA | 981 SHELIA LN | 173 | MT | 2024-11-19 | U123688 | U139701 | 2024-11-18 | 2024-11-17 | 2024-11-17 |  | KKINDER | 2024-11-18 | 2024-11-17 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26290021 | 15.7833 | 6 | 2064.43 | 1832.76 | 0 | 110.31 | 121.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24296313300 |  | 500305172 |  | 6720212N |  |  |  | 566 | EX | ABANDON SL - DEMO/FIRE | 2621P | OWSLEY | 305 OWSLEY AV | 067 | LEX | 2024-11-27 | LSTANFI | U140273 | 2024-11-18 | 2024-12-09 | 2025-01-02 |  | LSTANFI | 2024-11-27 | 2024-11-27 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.25 | 6 | 342.15 | 317.51 | 2.21 | 22.43 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24296316100 |  | 100267766 |  | 7356216D |  |  |  | 563 | EX | 1.25" P SHORT | 2621P | BOONE | 105 S BOONE ST | 127 | LOU | 2024-12-10 | U124604 | U129531 | 2024-11-18 | 2024-12-11 | 2024-12-11 |  | MCOLLET | 2024-12-09 | 2024-12-05 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 16.95 | 3 | 3522.55 | 1265.5 | 279.35 | 1899.26 | 78.44 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24296322500 |  | 500532674 |  | 6688228K |  |  |  | 563 | EX | 99 1" P LONG/NO PRMT REQ | 2600B | SARATOGA | 102 SARATOGA LT2 | 073 | FRA | 2024-12-09 | U126284 | U120250 | 2024-11-18 | 2024-11-22 | 2024-12-09 |  | JOSH PASLEY | 2024-12-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 10 | 1 | 5685.42 | 876.03 | 0 | 872.44 | 3936.95 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24296322900 |  | 501373138 |  | 7340268A |  |  |  | 563 | EX | 1"P LONG | 2621P | PERRY | 618 PERRY ST | 089 | GRE | 2024-12-04 | U123688 | U126919 | 2024-11-18 | 2024-11-19 | 2024-12-02 |  | MCOLLET | 2024-12-03 | 2024-12-02 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 15.4833 | 3 | 3339.91 | 1220.59 | 364.89 | 1710.03 | 44.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24296733700 |  | 501241459 |  | 6728208I |  |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | MORNING GLORY | 3941 MORNING GLORY LN | 067 | LEX | 2024-12-05 | U126532 | U130192 | 2024-11-19 | 2024-11-25 | 2024-12-10 |  | LESLIE SHARON | 2024-12-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4.3333 | 1 | 2213.25 | 336.68 | 249.93 | 19.67 | 1606.97 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24296748300 |  | 501172635 |  | 7356216L | 1528382 |  |  | 563 | EX | 1" P LONG | 2621P | RIVER OAKS | 33 RIVER OAKS LN LT2 | 127 | LOU | 2024-12-05 | U124604 | U134341 | 2024-11-19 | 2024-12-03 | 2024-12-03 |  | RECUMP | 2024-12-04 | 2024-12-02 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 38.0667 | 6 | 4578.04 | 2759.06 | 233.82 | 1428.28 | 156.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24296760000 |  | 501315661 |  | 6712208N | 2073901 |  |  | 563 | EX | 2" P LONG/NO PRMT REQ | 2600B | FOUNTAINBLUE | 3855 FOUNTAINBLUE LN | 067 | LEX | 2024-12-09 | U126284 | U126856 | 2024-11-19 | 2024-11-22 | 2024-12-09 |  | JOSH PASLEY | 2024-12-06 | 2024-12-05 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 9.5 | 2 | 12295.34 | 763.61 | 0 | 44.59 | 11487.14 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24296763800 |  | 500372538 |  | 6700208A | 9403247 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | RIVA RIDGE | 6036 RIVA RIDGE RD LT109 | 239 | VER | 2024-12-05 | U123111 | U126856 | 2024-11-19 | 2024-11-22 | 2024-12-09 |  | LYN STAFFORD | 2024-12-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 10 | 1 | 5502.95 | 803.77 | 229.19 | 46.95 | 4423.04 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24296776100 |  | 501309804 |  | 6716232E | 2076283 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | AMICK | 113 AMICK WY | 209 | GEO | 2024-12-05 | U126532 | U126856 | 2024-11-19 | 2024-11-22 | 2024-12-09 |  | LESLIE SHARON | 2024-12-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 3.1833 | 1 | 3632.51 | 245.31 | 287.04 | 14.33 | 3085.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24296776900 |  | 501348645 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | CALISTA FLAT | 788 CALISTA FLAT | 067 | LEX | 2024-11-26 | U129722 | U126856 | 2024-11-19 | 2024-11-21 | 2024-12-06 |  | DAVID YOUNG | 2024-11-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 4224.83 | 0 | 293.42 | 0 | 3931.41 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24296777200 |  | 501348622 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | CALISTA FLAT | 744 CALISTA FLAT | 067 | LEX | 2024-11-27 | U129722 | U126856 | 2024-11-19 | 2024-11-21 | 2024-12-06 |  | DAVID YOUNG | 2024-11-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 2814.51 | 0 | 274.27 | 0 | 2540.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24296777300 |  | 501348620 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | CALISTA FLAT | 789 CALISTA FLAT | 067 | LEX | 2024-11-26 | U129722 | U126856 | 2024-11-19 | 2024-11-21 | 2024-12-06 |  | DAVID YOUNG | 2024-11-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1357.58 | 0 | 287.04 | 0 | 1070.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24296777500 |  | 501348634 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | CLEMATIS | 2212 CLEMATIS WY | 067 | LEX | 2024-11-26 | U129722 | U126856 | 2024-11-19 | 2024-11-21 | 2024-12-06 |  | DAVID YOUNG | 2024-11-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 2859.68 | 0 | 274.27 | 0 | 2585.41 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24296797500 |  | 100423807 |  | 6732212C | 2405195 |  |  | 563 | EX | 1"P SHORT/NO PRMT REQ | 2600B | HALEY | 4550 HALEY RD | 067 | LEX | 2024-12-10 | U123111 | U128266 | 2024-11-19 | 2024-11-22 | 2024-12-10 |  | LYN STAFFORD | 2024-12-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1641.16 | 0 | 0 | 0 | 1641.16 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24296927000 |  | 501373554 |  | 6764176B |  |  |  | 563 | EX | 20 1" P LONG | 2621P | INDUSTRIAL | 21 INDUSTRIAL DR | 065 | IRV | 2024-12-05 | DENNING | U132805 | 2024-11-20 | 2024-12-04 | 2024-12-04 |  | DENNING | 2024-12-05 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 13.9 | 2 | 1537.77 | 1150.29 | 203.37 | 67.19 | 116.92 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24296935700 |  | 100351380 |  | 6736212P |  |  |  | 563 | EX | 1"P LONG*RUSH* | 2600B | WAYLAND | 756 WAYLAND DR | 049 | WIN | 2024-11-27 | U127414 | U132253 | 2024-11-20 | 2024-11-21 | 2024-12-06 |  | EDWARD FOX | 2024-11-27 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 9 | 1 | 2952.7 | 637.71 | 0 | 149.78 | 2165.21 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24296959000 |  | 100424093 |  | 6720204B |  |  |  | 565 | EX | REPLACE SERVICE LINE D512075 | 2621P | SUTHERLAND | 3442 SUTHERLAND DR | 067 | LEX | 2024-11-25 | U141668 | U124604 | 2024-11-20 | 2024-11-23 | 2024-12-11 |  | JOCHOA | 2024-11-22 | 2024-11-21 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 55.4167 | 7 | 4245.42 | 3778.22 | 239.82 | 227.38 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24296963500 |  | 100287024 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2600B | OAKHILL | 924 OAKHILL DR | 067 | LEX | 2024-12-12 | U125201 | U125763 | 2024-11-20 | 2024-12-31 |  |  | DAVID YOUNG | 2024-11-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4166.22 | 0 | 0 | 0 | 4166.22 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24297030900 |  | 100247733 |  | 7364188A |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | NICHOLS | 66 NICHOLS ST | 159 | INE | 2024-11-22 | U124604 | U131366 | 2024-11-20 | 2024-11-20 | 2024-11-20 |  | JCKIRK | 2024-11-21 |  |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 24.4 | 3 | 2165.88 | 1766.86 | 273.48 | 106.3 | 19.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24297063100 |  | 501347384 |  | 6708204K | 2397152 |  |  | 563 | EX | 99 1"P SHORT/NO PRMT REQ | 2600B | HOMESTRETCH | 104 HOMESTRETCH CR LT29 | 113 | NIC | 2024-11-27 | U129722 | U132253 | 2024-11-21 | 2024-11-22 | 2024-12-09 |  | DAVID YOUNG | 2024-11-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1892.38 | 0 | 287.04 | 0 | 1605.34 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24297073700 |  | 100408535 |  | 7320280B |  |  |  | 563 | EX | 1" P LONG | 2621P | BENNETT | 81 BENNETT ST | 135 | FIR | 2024-12-13 | U124604 | U132256 | 2024-11-21 | 2024-12-19 | 2024-12-19 |  | MCOLLET | 2024-12-12 | 2024-12-05 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 46.3833 | 7 | 9038.85 | 3661.93 | 19.12 | 5269 | 88.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24297075500 |  | 501370076 |  | 6720212I |  |  |  | 563 | EX | MANIFOLD W/100336279 | 2600B | 3RD | 379 E 3RD ST UNIT B | 067 | LEX | 2024-11-25 | U125763 | U120250 | 2024-11-21 | 2024-12-05 | 2024-12-19 |  | OFFICE PER MGMNT | 2024-11-25 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26210011 |  | 1
KY | KY - WEST | 2621 | 24297081100 |  | 501346175 |  | 6728208I | 2396366 |  |  | 563 | EX | 99 1" P LONG | 2600B | STOLEN HORSE | 3500 STOLEN HORSE TC LT70 | 067 | LEX | 2024-12-02 | U126284 | U120250 | 2024-11-21 | 2024-11-22 | 2024-12-09 |  | JOSH PASLEY | 2024-12-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 10 | 1 | 5139.38 | 876.03 | 0 | 872.44 | 3390.91 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24297087500 |  | 501317303 |  | 6716236J | 2178365 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | DOVE RUN | 132 DOVE RUN CR | 209 | GEO | 2024-12-06 | U126532 | U126856 | 2024-11-21 | 2024-11-22 | 2024-12-09 |  | LESLIE SHARON | 2024-12-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 13 | 1 | 5738.63 | 1006.1 | 287.04 | 58.76 | 4386.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24297088700 |  | 500097555 |  | 6720208F |  |  |  | 565 | EX | UPGRADE SERVICE LINE | 2621P | HART | 2026 HART RD | 067 | LEX | 2024-12-11 | LSTANFI | U124604 | 2024-11-21 | 2024-12-23 | 2024-12-23 |  | LSTANFI | 2024-12-11 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 0.11667 | 1 | 6478.98 | 5.6 | 585.15 | 5.64 | 5882.59 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24297100900 |  | 100295553 |  | 6716216K |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | REDWOOD | 1098 REDWOOD DR | 067 | LEX | 2024-12-23 | U930915 | U124604 | 2024-11-21 | 2025-01-20 | 2025-01-20 |  | MCRAIG | 2024-12-23 | 2024-12-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 24 | 3 | 2649.27 | 1552.27 | 220.32 | 764.2 | 112.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24297118000 |  | 100294011 |  | 6720212A |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTRQD | 2621P | BELLAIRE | 702 BELLAIRE AV | 067 | LEX | 2025-01-03 | U930915 | U140273 | 2024-11-21 | 2024-12-12 | 2025-01-07 |  | HSTANFI | 2025-01-03 | 2024-12-19 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 21.9667 | 4 | 1353.04 | 1249.3 | 21.82 | 81.92 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24297119900 |  | 500486521 |  | 6712208M | 9507827 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | NUTMEG | 4245 NUTMEG DR | 067 | LEX | 2024-12-10 | U461516 | U131378 | 2024-11-21 | 2024-11-25 | 2024-12-10 |  | NEAL P JOHNSON | 2024-12-10 |  | 2024-12-10 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4.5667 | 1 | 3390.23 | 333.95 | 357.25 | 393.2 | 2305.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24297121700 |  | 501373931 |  | 6716216N |  |  |  | 563 | EX | PAPER W/501329800 | 2600B | TURNER COMMONS | 144 TURNER COMMONS WY LOT 130 | 067 | LEX | 2024-11-25 | U125763 | U127708 | 2024-11-21 | 2024-12-12 | 2024-12-12 |  | OFFICE PER MGMNT | 2024-11-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBPEX |  | 100 | 056332B26210012 |  | 1
KY | KY - WEST | 2621 | 24297205900 |  | 501374038 |  | 6712208M |  |  |  | 563 | EX | PAPER W/501372866 | 2600B | HARRODSBURG | 4257 HARRODSBURG RD STE 120 | 067 | LEX | 2024-11-25 | U125763 | U127708 | 2024-11-22 | 2024-12-06 | 2024-12-06 |  | OFFICE PER MGMNT | 2024-11-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBPEX |  | 100 | 056332B26210012 |  | 1
KY | KY - WEST | 2621 | 24297206000 |  | 501374039 |  | 6712208M |  |  |  | 563 | EX | PAPER W/501372866 | 2600B | HARRODSBURG | 4257 HARRODSBURG RD STE 130 | 067 | LEX | 2024-11-25 | U125763 | U127708 | 2024-11-22 | 2024-12-06 | 2024-12-06 |  | OFFICE PER MGMNT | 2024-11-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBPEX |  | 100 | 056332B26210012 |  | 1
KY | KY - WEST | 2621 | 24297206100 |  | 501374040 |  | 6712208M |  |  |  | 563 | EX | PAPER W/501372866 | 2600B | HARRODSBURG | 4257 HARRODSBURG RD STE 140 | 067 | LEX | 2024-11-25 | U125763 | U127708 | 2024-11-22 | 2024-12-06 | 2024-12-06 |  | OFFICE PER MGMNT | 2024-11-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBPEX |  | 100 | 056332B26210012 |  | 1
KY | KY - WEST | 2621 | 24297206200 |  | 501374041 |  | 6712208M |  |  |  | 563 | EX | PAPER W/501372866 | 2600B | HARRODSBURG | 4257 HARRODSBURG RD STE 150 | 067 | LEX | 2024-11-25 | U125763 | U127708 | 2024-11-22 | 2024-12-06 | 2024-12-06 |  | OFFICE PER MGMNT | 2024-11-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBPEX |  | 100 | 056332B26210012 |  | 1
KY | KY - EAST | 2631 | 24297206700 |  | 501373324 |  | 7352260O |  |  |  | 563 | EX | 1"P LONG RUSH | 2621P | BREWER | 405 BREWER RD | 019 | ASH | 2024-12-05 | U124604 | U128266 | 2024-11-22 | 2024-11-25 | 2024-12-06 |  | MCOLLET | 2024-12-04 | 2024-12-04 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 18.5 | 2 | 5026.5 | 1463.44 | 354.37 | 3183.53 | 25.16 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24297213200 |  | 100348564 |  | 6748208I | 2293700 |  |  | 565 | EX | REPLACE SL/ 22026237301 | 2600B | STEVENSON | 114 STEVENSON ST | 049 | WIN | 2024-11-26 | U126530 | U128445 | 2024-11-22 | 2024-12-23 |  |  | JDUNN | 2024-11-26 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2446.27 | 0 | 0 | 0 | 2446.27 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24297222200 |  | 501371542 |  | 6740212O |  |  |  | 563 | EX | PAPER W/100437255 | 2621P | ROCKWELL | 5855 ROCKWELL RD 1B | 049 | WIN | 2024-12-09 | U123688 | U128727 | 2024-11-22 | 2024-12-06 | 2024-12-06 |  | OFFICE | 2024-12-09 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26290011 |  | 1
KY | KY - CENTRAL | 2629 | 24297228600 |  | 100349049 |  | 6748208M |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTRQD | 2621P | JACKSON | 48 JACKSON ST | 049 | WIN | 2024-12-13 | U124604 | U140273 | 2024-11-22 | 2024-12-13 | 2025-01-08 |  | DENNING | 2024-12-12 | 2024-12-06 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.3667 | 4 | 1775.91 | 694.91 | 94.39 | 40.61 | 946 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24297231400 |  | 100285503 |  | 6768172A |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | GEORGE | 501 GEORGE ST | 065 | IRV | 2024-12-04 | DENNING | U123688 | 2024-11-22 | 2027-12-30 |  |  | DENNING | 2024-12-04 | 2024-12-04 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 13.2333 | 3 | 2159.07 | 1094.87 | 319.54 | 63.94 | 680.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24297254300 |  | 100424094 |  | 6720204B | 1313369 |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | SUTHERLAND | 3444 SUTHERLAND DR | 067 | LEX | 2024-11-25 | U141668 | U134902 | 2024-11-22 | 2024-11-22 |  |  | JOCHOA | 2024-11-22 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.51667 | 1 | 385.9 | 42.43 | 340.91 | 2.56 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24297266800 |  | 501374065 |  | 6684228N |  |  |  | 563 | EX | 1" P LONG | 2600B | BERRY HILL | 2025 BERRY HILL DR | 073 | FRA | 2025-01-03 | U126532 | U131378 | 2024-11-22 | 2024-11-25 | 2025-01-03 |  | LESLIE SHARON | 2025-01-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 9.5 | 1 | 5181.15 | 621.04 | 471.2 | 492.21 | 3596.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24297267800 |  | 501340654 |  | 6720212K |  |  |  | 563 | EX | 1" P LONG/PRMT RCVD | 2600B | LOUDON | 713 E LOUDON AV | 067 | LEX | 2024-12-23 | U123111 | U131378 | 2024-11-22 | 2024-12-09 | 2024-12-20 |  | LYN STAFFORD | 2024-12-20 | 2024-12-19 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 16 | 2 | 9356.72 | 1286 | 353.92 | 75.12 | 7641.68 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24297460600 |  | 100341242 |  | 7244216I | 1635077 |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | OSBORNE | 1256 OSBORNE RD | 173 | MT | 2024-11-25 | DENNING | U141174 | 2024-11-24 | 2024-11-24 | 2024-11-24 |  | DENNING | 2024-11-25 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 19.85 | 3 | 3420.51 | 1598.1 | 790.31 | 286.93 | 745.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24297467900 |  | 501333771 |  | 6724204A | 2185117 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | BAY SHOALS | 3484 BAY SHOALS DR | 067 | LEX | 2024-12-11 | U123111 | U126856 | 2024-11-25 | 2024-11-26 | 2024-12-11 |  | LYN STAFFORD | 2024-12-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 3876.57 | 0 | 311.23 | 0 | 3565.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24297468000 |  | 501347913 |  | 6724204A | 2291616 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | NIGHT HERON | 3429 NIGHT HERON WY | 067 | LEX | 2024-12-11 | U461516 | U126856 | 2024-11-25 | 2024-11-26 | 2024-12-11 |  | NEAL JOHNSON | 2024-12-10 |  | 2024-12-10 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 3.4333 | 1 | 2415.76 | 253.22 | 311.23 | 298.14 | 1553.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24297468300 |  | 501347929 |  | 6724204A | 2291616 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | BAY SHOALS | 3440 BAY SHOALS DR | 067 | LEX | 2024-12-11 | U123111 | U126856 | 2024-11-25 | 2024-11-26 | 2024-12-11 |  | LYN STAFFORD | 2024-12-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 2031.33 | 0 | 311.23 | 0 | 1720.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24297468500 |  | 501347945 |  | 6724204A | 2291616 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | BAY SHOALS | 3433 BAY SHOALS DR | 067 | LEX | 2024-12-10 | U123111 | U126856 | 2024-11-25 | 2024-11-26 | 2024-12-11 |  | LYN STAFFORD | 2024-12-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 9.5 | 1 | 2185.7 | 763.56 | 311.23 | 44.6 | 1066.31 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24297480500 |  | 501309027 |  | 6712228I |  |  |  | 563 | EX | 99 1" P LONG/NO PRMT REQ | 2600B | HOURGLASS | 135 HOURGLASS LN LT15 | 209 | GEO | 2024-12-11 | U123111 | U123852 | 2024-11-25 | 2024-11-26 | 2024-12-11 |  | LYN STAFFORD | 2024-12-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26230011 | 4.5 | 1 | 4069.42 | 361.71 | 412.41 | 21.12 | 3274.18 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24297480800 |  | 501309028 |  | 6712228I |  |  |  | 563 | EX | 99 1" P LONG/NO PRMT REQ | 2600B | HOURGLASS | 137 HOURGLASS LN LT16 | 209 | GEO | 2024-12-11 | U123111 | U123852 | 2024-11-25 | 2024-11-26 | 2024-12-11 |  | LYN STAFFORD | 2024-12-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 5 | 1 | 3863.51 | 401.88 | 311.23 | 23.49 | 3126.91 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24297482900 |  | 501327320 |  | 6716232B | 2179247 |  |  | 563 | EX | 1 "P SHORT/NO PRMT REQ | 2600B | KIRKSTALL | 104 KIRKSTALL WY LT279C | 209 | GEO | 2024-12-06 | U123111 | U123852 | 2024-11-25 | 2024-11-26 | 2024-12-11 |  | LYN STAFFORD | 2024-12-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 3 | 1 | 1663.79 | 241.14 | 311.23 | 14.09 | 1097.33 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24297483200 |  | 501327309 |  | 6716232B | 2179247 |  |  | 563 | EX | 1 "P SHORT/NO PRMT REQ | 2600B | WELLESLY | 145 WELLESLY AV LT268 | 209 | GEO | 2024-12-06 | U123111 | U123852 | 2024-11-25 | 2024-11-26 | 2024-12-11 |  | LYN STAFFORD | 2024-12-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 3 | 1 | 1638.41 | 241.14 | 311.23 | 14.09 | 1071.95 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24297483700 |  | 501327364 |  | 6716232B | 2179247 |  |  | 563 | EX | 1 "P SHORT/NO PRMT REQ | 2600B | GALWAY | 100 GALWAY LN LT239 | 209 | GEO | 2024-12-11 | U461516 | U123852 | 2024-11-25 | 2024-11-26 | 2024-12-11 |  | NEAL P JOHNSON | 2024-12-11 |  | 2024-12-11 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 6.0833 | 1 | 2816.98 | 445.51 | 306.44 | 524.55 | 1540.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24297503500 |  | 501346197 |  | 6728208I | 2396366 |  |  | 563 | EX | 1" P LONG 2ND ATP | 2600B | SQUIRREL NEST | 1109 SQUIRREL NEST LN LT90 | 067 | LEX | 2024-12-11 | U126532 | U132258 | 2024-11-25 | 2024-11-26 | 2024-12-11 |  | LESLIE SHARON | 2024-12-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 9 | 1 | 3841.09 | 696.52 | 287.04 | 779.84 | 2077.69 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24297738600 |  | 100245843 |  | 7360252M |  |  |  | 565 | EX | REPLACE SERVICE LINE EMER | 2621P | 28TH | 641 28TH ST | 019 | CAT | 2024-11-27 | RECUMP | U137009 | 2024-11-26 | 2024-11-26 |  |  | RECUMP | 2024-11-27 | 2024-11-26 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 26.5 | 3 | 2685.37 | 1920.69 | 231.97 | 381.75 | 150.96 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24297745400 |  | 501358916 |  | 6684228J | 2407531 |  |  | 563 | EX | TAP W/ MAIN JO # 24-0263552-00 | 2600B | WAPPING | 403 WAPPING ST | 073 | FRA | 2024-12-17 | U128816 | U129819 | 2024-11-26 | 2024-12-23 | 2024-12-25 |  | OLIVER MAYNARD | 2024-12-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBTWM |  | 100 | 056332B26230012 |  | 1 | 3842.45 | 0 | 2836.18 | 0 | 1006.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24297763000 |  | 100331258 |  | 6720212N |  |  |  | 565 | EX | RELOCATE CUSTOMER SL | 2621P | LINCOLN | 169 LINCOLN AV | 067 | LEX | 2025-01-14 | U124604 | U141668 | 2024-11-26 | 2025-01-17 | 2025-01-17 |  | HSTANFI | 2025-01-13 | 2025-01-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.3667 | 4 | 1652.64 | 1057.13 | 324.64 | 69.59 | 201.28 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24297806300 |  | 500072380 |  | 16712208M |  |  |  | 563 | EX | 1" P LONG/PRMT RCVD | 2600B | STEDMAN | 2108 STEDMAN DR | 067 | LEX | 2024-12-19 | U461516 | U129531 | 2024-11-26 | 2024-12-09 | 2024-12-20 |  | NEAL JOHNSON | 2024-12-19 |  | 2024-12-19 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4.3667 | 1 | 4642.73 | 319.29 | 280.66 | 375.9 | 3666.88 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24297817400 |  | 100269876 |  | 6732252O |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | 5TH | 203 5TH ST | 097 | CYN | 2024-11-27 | DENNING | U139715 | 2024-11-26 | 2024-11-26 |  |  | DENNING | 2024-11-27 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 0.35 | 4 | 576.65 | 44.49 | 428.78 | 2.74 | 100.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24297817600 |  | 501254559 |  | 6716216L |  |  |  | 563 | EX | 20 1" P SHORT/PRMT RCVD | 2600B | NANDINO | 968 NANDINO BV | 067 | LEX | 2024-12-20 | U126532 | U132805 | 2024-11-26 | 2024-12-09 | 2024-12-20 |  | LESLIE SHARON | 2024-12-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 12.5 | 1 | 7445.65 | 967.42 | 511.34 | 56.5 | 5910.39 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24297848000 |  | 100262919 |  | 7352260N |  |  |  | 563 | EX | 99 1" P LONG | 2621P | HOODS CREEK | 2200 HOODS CREEK PK | 019 | ASH | 2024-12-20 | U124604 | U120250 | 2024-11-26 | 2024-12-10 | 2024-12-24 |  | MCOLLET | 2024-12-19 | 2024-12-19 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 17.5 | 2 | 6088.86 | 1384.32 | 264.64 | 1894.54 | 2545.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24297911500 |  | 501374036 |  | 6720212K | 2410539 |  |  | 563 | EX | 2" P LONG/PRMT READY 12/16/24 | 2600B | INDUSTRY | 1064 INDUSTRY RD 110 | 067 | LEX | 2025-01-08 | U461516 | U126919 | 2024-11-27 | 2024-12-17 | 2025-01-02 |  | NEAL JOHNSON | 2025-01-03 |  | 2025-01-02 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 10060.66 | 487.03 | 1708.79 | 412.11 | 7452.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24297911600 |  | 501374043 |  | 6720212K | 2410539 |  |  | 563 | EX | MANIFOLD W/ 501374036 | 2600B | INDUSTRY | 1064 INDUSTRY RD 120 | 067 | LEX | 2025-01-08 | U461516 | U126919 | 2024-11-27 | 2024-12-17 | 2025-01-02 |  | NEAL JOHNSON | 2025-01-03 |  | 2025-01-02 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBMAN |  | 100 | 056332B26210012 |  | 1 | 491.59 | 0 | 99.71 | 0 | 391.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24297911700 |  | 501374044 |  | 6720212K | 2410539 |  |  | 563 | EX | MANIFOLD W/ 501374036 | 2600B | INDUSTRY | 1064 INDUSTRY RD 130 | 067 | LEX | 2025-01-08 | U461516 | U126919 | 2024-11-27 | 2024-12-17 | 2025-01-02 |  | NEAL JOHNSON | 2025-01-03 |  | 2024-01-02 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBMAN |  | 100 | 056332B26210012 |  | 1 | 491.59 | 0 | 99.71 | 0 | 391.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24297911800 |  | 501374045 |  | 6720212K | 2410539 |  |  | 563 | EX | MANIFOLD W/ 501374036 | 2600B | INDUSTRY | 1064 INDUSTRY RD 140 | 067 | LEX | 2025-01-08 | U461516 | U126919 | 2024-11-27 | 2024-12-17 | 2025-01-02 |  | NEAL JOHNSON | 2025-01-03 |  | 2025-01-02 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBMAN |  | 100 | 056332B26210012 |  | 1 | 491.59 | 0 | 99.71 | 0 | 391.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24297911900 |  | 501374046 |  | 6720212K | 2410539 |  |  | 563 | EX | MANIFOLD W/ 501374036 | 2600B | INDUSTRY | 1064 INDUSTRY RD 150 | 067 | LEX | 2025-01-08 | U461516 | U126919 | 2024-11-27 | 2024-12-17 | 2025-01-02 |  | NEAL JOHNSON | 2025-01-03 |  | 2025-01-02 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBMAN |  | 100 | 056332B26210012 |  | 1 | 491.59 | 0 | 99.71 | 0 | 391.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24297912200 |  | 501374047 |  | 6720212K | 2410539 |  |  | 563 | EX | MANIFOLD W/ 501374036 | 2600B | INDUSTRY | 1064 INDUSTRY RD 160 | 067 | LEX | 2025-01-08 | U461516 | U126919 | 2024-11-27 | 2024-12-17 | 2025-01-02 |  | NEAL JOHNSON | 2025-01-03 |  | 2025-01-02 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBMAN |  | 100 | 056332B26210012 |  | 1 | 491.59 | 0 | 99.71 | 0 | 391.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24297912600 |  | 501374048 |  | 6720212K | 2410539 |  |  | 563 | EX | 2" P SHORT/PRMT READY 12/16/24 | 2600B | INDUSTRY | 1052 INDUSTRY RD 110 | 067 | LEX | 2025-01-07 | U461309 | U126919 | 2024-11-27 | 2024-12-17 | 2025-01-02 |  | RANDALL HUMPHREYS | 2025-01-02 | 2025-01-02 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 5537.26 | 484.89 | 626.13 | 411.98 | 4014.26 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24297912900 |  | 501374049 |  | 6720212K | 2410539 |  |  | 563 | EX | MANIFOLD W/ 501374048 | 2600B | INDUSTRY | 1052 INDUSTRY RD 120 | 067 | LEX | 2025-01-07 | U461309 | U126919 | 2024-11-27 | 2024-12-17 | 2025-01-02 |  | RANDALL HUMPHREYS | 2025-01-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBMAN |  | 100 | 056332B26210012 |  | 0 | 412.63 | 0 | 99.71 | 0 | 312.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24297913000 |  | 501374050 |  | 6720212K | 2410539 |  |  | 563 | EX | MANIFOLD W/ 501374048 | 2600B | INDUSTRY | 1052 INDUSTRY RD 130 | 067 | LEX | 2025-01-07 | U461309 | U126919 | 2024-11-27 | 2024-12-17 | 2025-01-02 |  | RANDALL HUMPHREYS | 2025-01-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBMAN |  | 100 | 056332B26210012 |  | 1 | 412.63 | 0 | 99.71 | 0 | 312.92 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24297921100 |  | 100340894 |  | 6736192N | 1635077 |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | DANIEL | 501 DANIEL DR | 151 | RIC | 2024-12-02 | U124604 | U141174 | 2024-11-27 | 2024-11-27 | 2024-11-27 |  | LSTANFI | 2024-11-27 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 3.6 | 3 | 653.97 | 228.24 | 289.2 | 53.65 | 82.88 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24297936400 |  | 100253760 |  | 7356220P | 1855491 |  |  | 565 | EX | REPLACE SL/ 18026794400 | 2600B | FYFFE | 304 FYFFE ST | 127 | LOU | 2025-03-17 | U123965 | U128445 | 2024-11-27 | 2024-12-23 |  |  | CJH CASEY PACK | 2025-03-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2242.79 | 0 | 0 | 0 | 2242.79 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24297936900 |  | 500537231 |  | 7356216D | 1855491 |  |  | 565 | EX | REPLACE SL/ 18026794400 | 2600B | FYFFE | 117 FYFFE ST 119 | 127 | LOU | 2025-03-18 | U123965 | U128445 | 2024-11-27 | 2024-12-23 |  |  | CJ HUGHES MITCHELL DICKESS | 2025-03-17 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2796.49 | 0 | 0 | 0 | 2796.49 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24297937200 |  | 500083272 |  | 7356216D | 1855491 |  |  | 565 | EX | REPLACE SL/ 18026794400 | 2600B | FYFFE | 309 FYFFE ST | 127 | LOU | 2025-03-18 | U123965 | U128445 | 2024-11-27 | 2024-12-23 |  |  | CJH MITCHELL DICKESS | 2025-03-17 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2151.41 | 0 | 0 | 0 | 2151.41 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24297937400 |  | 100344353 |  | 7240212C |  |  |  | 563 | EX | 99 1" P SHORT | 2621P | JACKSON | 412 JACKSON ST | 173 | MT | 2024-12-10 | DENNING | U142144 | 2024-11-27 | 2024-12-02 | 2024-12-11 |  | DENNING | 2024-12-10 | 2024-12-06 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 26.6833 | 5 | 3373.9 | 2204.88 | 385.46 | 128.8 | 654.76 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24297937600 |  | 500537241 |  | 7356216D | 1855491 |  |  | 565 | EX | REPLACE SL/ 18026794400 | 2600B | FYFFE | 117 FYFFE ST 129 | 127 | LOU | 2025-03-14 | U123965 | U128445 | 2024-11-27 | 2024-12-23 |  |  | CJH CASEY PACK | 2025-03-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2849.85 | 0 | 0 | 0 | 2849.85 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24297937700 |  | 100253764 |  | 7356216D | 1855491 |  |  | 565 | EX | REPLACE SL/ 18026794400 | 2600B | FYFFE | 355 FYFFE ST | 127 | LOU | 2025-03-07 | U123965 | U128445 | 2024-11-27 | 2024-12-23 |  |  | CJH CASEY PACK | 2025-03-07 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2769.88 | 0 | 0 | 0 | 2769.88 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24297937900 |  | 500537250 |  | 7356216D | 1855491 |  |  | 565 | EX | REPLACE SL/ 18026794400 | 2600B | FYFFE | 117 FYFFE ST 138 | 127 | LOU | 2025-03-12 | U123965 | U128445 | 2024-11-27 | 2024-12-23 |  |  | CJH CASEY PACK | 2025-03-10 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1994.31 | 0 | 0 | 0 | 1994.31 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24297938100 |  | 100253766 |  | 7356220P | 1855491 |  |  | 565 | EX | REPLACE SL/ 18026794400 | 2600B | WALNUT | 361 N WALNUT ST | 127 | LOU | 2025-03-12 | U123965 | U128445 | 2024-11-27 | 2024-12-23 |  |  | CJH CASEY PACK | 2025-03-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2264.33 | 0 | 0 | 0 | 2264.33 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24297938200 |  | 100253777 |  | 7356220P | 1855491 |  |  | 565 | EX | REPLACE SL/ 18026794400 | 2600B | SYCAMORE | 416 E SYCAMORE ST | 127 | LOU | 2025-03-07 | U123965 | U128445 | 2024-11-27 | 2024-12-23 |  |  | CJH CASEY PACK | 2025-03-07 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2154.51 | 0 | 0 | 0 | 2154.51 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24297938300 |  | 100253776 |  | 7336268H | 1855491 |  |  | 565 | EX | REPLACE SL/ 18026794400 | 2600B | SYCAMORE | 414 SYCAMORE ST | 127 | LOU | 2025-03-07 | U123965 | U128445 | 2024-11-27 | 2024-12-23 |  |  | CJH CASEY PACK | 2025-03-07 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2114.53 | 0 | 0 | 0 | 2114.53 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24297938700 |  | 100253779 |  | 7356220P | 1855491 |  |  | 565 | EX | REPLACE SL/ 18026794400 | 2600B | SYCAMORE | 413 E SYCAMORE ST | 127 | LOU | 2025-03-04 | U123965 | U128445 | 2024-11-27 | 2024-12-23 |  |  | CJH MITCHELL DICKESS | 2025-03-03 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2111.03 | 0 | 0 | 0 | 2111.03 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24297938900 |  | 100253780 |  | 7356220P | 1855491 |  |  | 565 | EX | REPLACE SL/ 18026794400 | 2600B | SYCAMORE | 411 E SYCAMORE ST | 127 | LOU | 2025-03-03 | U123965 | U128445 | 2024-11-27 | 2024-12-23 |  |  | CJH MITCHELL DICKESS | 2025-03-03 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2795.64 | 0 | 0 | 0 | 2795.64 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24297939000 |  | 100253775 |  | 7356220P | 1855491 |  |  | 565 | EX | REPLACE SL/ 18026794400 | 2600B | SYCAMORE | 412 E SYCAMORE ST | 127 | LOU | 2025-03-05 | U123965 | U128445 | 2024-11-27 | 2024-12-23 |  |  | CJH MITCHELL DICKESS | 2025-03-04 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1840.29 | 0 | 0 | 0 | 1840.29 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24297939200 |  | 100253774 |  | 7356220P | 1855491 |  |  | 565 | EX | REPLACE SL/ 18026794400 | 2600B | SYCAMORE | 410 E SYCAMORE ST | 127 | LOU | 2025-03-07 | U123965 | U128445 | 2024-11-27 | 2024-12-23 |  |  | CJH CASEY PACK | 2025-03-07 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3063.58 | 0 | 0 | 0 | 3063.58 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24297939500 |  | 100253773 |  | 7356220P | 1855491 |  |  | 565 | EX | REPLACE SL/ 18026794400 | 2600B | SYCAMORE | 408 N SYCAMORE ST | 127 | LOU | 2025-02-24 | U123965 | U128445 | 2024-11-27 | 2024-12-23 |  |  | CJH MITCHELL DICKESS | 2025-02-24 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2727.43 | 0 | 0 | 0 | 2727.43 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24297939700 |  | 100253772 |  | 7356220P | 1855491 |  |  | 565 | EX | REPLACE SL/ 18026794400 | 2600B | SYCAMORE | 406 E SYCAMORE ST | 127 | LOU | 2025-02-26 | U123965 | U128445 | 2024-11-27 | 2024-12-23 |  |  | CJH MITCHELL DICKESS | 2025-02-25 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2727.43 | 0 | 0 | 0 | 2727.43 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24297939800 |  | 100253771 |  | 7356220P | 1855491 |  |  | 565 | EX | REPLACE SL/ 18026794400 | 2600B | SYCAMORE | 404 E SYCAMORE ST | 127 | LOU | 2025-02-14 | U123965 | U128445 | 2024-11-27 | 2024-12-23 |  |  | CJH MITCHELL DICKESS | 2025-02-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2819.79 | 0 | 0 | 0 | 2819.79 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24297940000 |  | 100253770 |  | 7356220P | 1855491 |  |  | 565 | EX | REPLACE SL/ 18026794400 | 2600B | SYCAMORE | 402 SYCAMORE ST | 127 | LOU | 2025-03-05 | U123965 | U128445 | 2024-11-27 | 2024-12-23 |  |  | CJH CASEY PACK | 2025-03-04 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3530.37 | 0 | 0 | 0 | 3530.37 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24297940100 |  | 100253783 |  | 7356220P | 1855491 |  |  | 565 | EX | REPLACE SL/ 18026794400 | 2600B | SYCAMORE | 403 E SYCAMORE ST | 127 | LOU | 2025-02-24 | U123965 | U128445 | 2024-11-27 | 2024-12-23 |  |  | CJH MITCHELL DICKESS | 2025-02-24 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2161.69 | 0 | 0 | 0 | 2161.69 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24297940200 |  | 100270758 |  | 6736248A |  |  |  | 563 | EX | 1" P SHORT | 2621P | OLD LAIR | 204 OLD LAIR RD | 097 | CYN | 2024-12-09 | U124604 | U130192 | 2024-11-27 | 2024-12-11 | 2024-12-11 |  | NRICHIE | 2024-12-06 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 18 | 2 | 2680.6 | 1432.53 | 352.77 | 83.65 | 811.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24297940300 |  | 100253784 |  | 7356220P | 1855491 |  |  | 565 | EX | REPLACE SL/ 18026794400 | 2600B | SYCAMORE | 401 E SYCAMORE ST | 127 | LOU | 2025-03-21 | U123965 | U128445 | 2024-11-27 | 2024-12-23 |  |  | CJ HUGHES MITCHELL DICKESS | 2025-03-20 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 4276.93 | 0 | 0 | 0 | 4276.93 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24297940600 |  | 100253768 |  | 7356220P | 1855491 |  |  | 565 | EX | REPLACE SL/ 18026794400 | 2600B | SYCAMORE | 398 E SYCAMORE ST | 127 | LOU | 2025-03-05 | U123965 | U128445 | 2024-11-27 | 2024-12-23 |  |  | CJH CASEY PACK | 2025-03-05 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2070.48 | 0 | 0 | 0 | 2070.48 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24297940800 |  | 100253785 |  | 7356220P | 1855491 |  |  | 565 | EX | REPLACE SL/ 18026794400 | 2600B | SYCAMORE | 305 E SYCAMORE ST | 127 | LOU | 2025-02-18 | U123965 | U128445 | 2024-11-27 | 2024-12-23 |  |  | CJH CASEY PACK | 2025-02-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2632.13 | 0 | 0 | 0 | 2632.13 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24297940900 |  | 100253787 |  | 7356620P | 1855491 |  |  | 565 | EX | REPLACE SL/ 18026794400 | 2600B | LOCK | 608 N LOCK AV | 127 | LOU | 2025-03-19 | U123965 | U128445 | 2024-11-27 | 2024-12-23 |  |  | CJ HUGHES MITCHELL DICKESS | 2025-03-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3067.01 | 0 | 0 | 0 | 3067.01 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24297941000 |  | 100253767 |  | 7356216D | 1855491 |  |  | 565 | EX | REPLACE SL/ 18026794400 | 2600B | LOCK | 602 N LOCK AV | 127 | LOU | 2025-03-05 | U123965 | U128445 | 2024-11-27 | 2024-12-23 |  |  | CJH CASEY PACK | 2025-03-05 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3251.78 | 0 | 0 | 0 | 3251.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24297954100 |  | 100409368 |  | 6720204I | 1635077 |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | CROSBY | 3644 CROSBY DR | 067 | LEX | 2024-12-03 | UIPBOT17 | U141174 | 2024-11-27 | 2024-11-27 | 2024-11-27 |  | JGILES | 2024-12-02 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.15 | 5 | 1441.1 | 1198.03 | 41.15 | 71.68 | 130.24 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24298000700 |  | 100349478 |  | 6744208P | 2407925 |  |  | 565 | EX | D | 2621P | MAIN | 55 S MAIN ST | 049 | WIN | 2024-12-09 | U126285 | U134844 | 2024-11-29 | 2024-11-27 |  |  | LYN STAFFORD | 2024-11-29 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 24 | 2 | 11615.79 | 1776 | 0 | 106.86 | 9732.93 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24298019100 |  | 100349451 |  | 6744208P | 2407925 |  |  | 565 | EX | REPLACE SL/24026358600 | 2621P | MAIN | 5 S MAIN ST | 049 | WIN | 2025-01-30 | U126285 | U125765 | 2024-12-01 | 2025-12-23 |  |  | DUSTIN DAVIS | 2025-01-29 | 2025-01-02 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26290032 | 36 | 4 | 16859.74 | 2529.84 | 0 | 689.13 | 13640.77 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24298019300 |  | 100349461 |  | 6744208P | 2407925 |  |  | 565 | EX | REPLACE SL/24026358600 | 2621P | MAIN | 23 S MAIN ST 1F | 049 | WIN | 2024-12-05 | U126604 | U125765 | 2024-12-01 | 2025-12-23 |  |  | WILLIAM FULKS | 2024-12-05 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26290032 |  | 1 | 10633.72 | 69.09 | 0 | 4.05 | 10560.58 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24298019400 |  | 100349468 |  | 6744208P | 2407925 |  |  | 565 | EX | REPLACE SL/24026358600 | 2621P | MAIN | 33 S MAIN ST 1F | 049 | WIN | 2024-12-14 | U126285 | U125765 | 2024-12-01 | 2025-12-23 |  |  | DUSTIN DAVIS | 2024-12-07 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26290032 | 33 | 3 | 15973.51 | 2778.5 | 0 | 1825.4 | 11369.61 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24298019700 |  | 100349475 |  | 6744208P | 2407925 |  |  | 565 | EX | REPLACE SL/24026358600 | 2621P | MAIN | 47 S MAIN ST | 049 | WIN | 2024-12-17 | U126285 | U125765 | 2024-12-01 | 2025-12-23 |  |  | DUSTIN DAVIS | 2024-12-17 | 2024-12-14 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26290032 | 13 | 2 | 7520.43 | 1094.57 | 0 | 556.69 | 5869.17 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24298019800 |  | 100458297 |  | 6744208P | 2407925 |  |  | 565 | EX | REPLACE SL/24026358600 | 2621P | MAIN | 51 S MAIN ST | 049 | WIN | 2024-12-09 | U126285 | U125765 | 2024-12-01 | 2025-12-23 |  |  | DUSTIN DAVIS | 2024-11-30 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26290032 |  | 1 | 2200 | 0 | 0 | 0 | 2200 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24298019900 |  | 100349485 |  | 6744208P | 2407925 |  |  | 565 | EX | REPLACE SL/24026358600 | 2621P | MAIN | 57 S MAIN ST | 049 | WIN | 2024-12-13 | U126285 | U125765 | 2024-12-01 | 2025-12-23 |  |  | DUSTIN DAVIS | 2024-12-11 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26290032 |  | 1 | 11721.29 | 0 | 0 | 0 | 11721.29 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24298020000 |  | 100464805 |  | 6744208P | 2407925 |  |  | 565 | EX | REPLACE SL/24026358600 | 2621P | MAIN | 61 S MAIN ST | 049 | WIN | 2024-12-09 | U126285 | U125765 | 2024-12-01 | 2025-12-23 |  |  | DUSTIN DAVIS | 2024-12-03 | 2024-12-02 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26290032 | 19 | 2 | 10059.32 | 1599.78 | 0 | 1653.89 | 6805.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24298036700 |  | 501348626 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | CLEMATIS | 2205 CLEMATIS WY | 067 | LEX | 2024-12-17 | U123111 | U126856 | 2024-12-02 | 2024-12-04 | 2024-12-17 |  | LYN STAFFORD | 2024-12-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2037.4 | 643 | 280.66 | 37.56 | 1076.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24298055200 |  | 501347382 |  | 6708204K | 2397152 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | HOMESTRETCH | 112 HOMESTRETCH CR | 113 | NIC | 2024-12-17 | U461516 | U126856 | 2024-12-02 | 2024-12-04 | 2024-12-17 |  | NEAL JOHNSON | 2024-12-16 |  | 2024-12-16 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 6.4167 | 1 | 3235.58 | 471.96 | 266.31 | 555.65 | 1941.66 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24298069200 |  | 100270475 |  | 6736248A |  |  |  | 563 | EX | PAPER W/100452647 | 2621P | CHURCH | 306 S CHURCH ST | 097 | CYN | 2024-12-10 | U123688 | U132253 | 2024-12-02 | 2024-12-16 | 2024-12-16 |  | OFFICE | 2024-12-10 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26290011 |  | 1
KY | KY - EAST | 2631 | 24298074000 |  | 100267375 |  | 7352260I | 2410274 |  |  | 563 | EX | 1.25"P SHORT | 2621P | PRINCESS | 203 PRINCESS DR | 089 | ASH | 2024-12-12 | U124604 | U128266 | 2024-12-02 | 2024-12-03 | 2024-12-16 |  | MCOLLET | 2024-12-11 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 20 | 2 | 5332.65 | 1583.13 | 234.37 | 3418.95 | 96.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24298094200 |  | 100316115 |  | 6716208F |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | PIN OAK | 206 PIN OAK DR | 067 | LEX | 2024-12-03 | U124604 | U139701 | 2024-12-02 | 2025-01-21 | 2026-07-31 |  | HSTANFI | 2024-12-02 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 25.5333 | 8 | 4767.03 | 2146.04 | 191.13 | 72.8 | 2357.06 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24298174600 |  | 100261162 |  | 7352256C |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | 6TH | 2300 6TH ST | 019 | ASH | 2025-01-29 | MCOLLET | U140273 | 2024-12-03 | 2024-12-23 | 2025-01-16 |  | MCOLLET | 2025-01-29 | 2025-01-17 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 23.8333 | 6 | 3459.05 | 1724.7 | 20.28 | 1714.07 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24298193000 |  | 100347749 |  | 6748208I | 2293700 |  |  | 565 | EX | REPLACE SL/ 22026237301 | 2621P | MAIN | 250 N MAIN ST | 049 | WIN | 2024-12-04 | U126604 | U128445 | 2024-12-03 | 2024-12-23 |  |  | WILLIAM FULKS | 2024-12-04 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 7972.66 | 274.7 | 0 | 315.05 | 7382.91 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24298197800 |  | 100285142 |  | 6748180P |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | IRVINE | IRVINE RD | 151 | WAC | 2024-12-05 | U930915 | U129939 | 2024-12-03 | 2024-12-03 |  |  | DENNING | 2024-12-05 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24298198900 |  | 100331197 |  | 6720212N |  |  |  | 563 | EX | 1" P SHORT/PRMT READY 12/16/24 | 2600B | LINCOLN | 352 LINCOLN AV | 067 | LEX | 2024-12-27 | U129722 | U130192 | 2024-12-03 | 2024-12-17 | 2025-01-02 |  | DAVID YOUNG | 2024-12-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2135.34 | 615.08 | 361.11 | 35.92 | 1123.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24298203900 |  | 501365934 |  | 6712204D | 2406638 |  |  | 563 | EX | PAPER W/ 100439969 | 2600B | PARTNER | 3330 PARTNER PL STE 140 | 067 | LEX | 2024-12-17 | U125201 | U134341 | 2024-12-03 | 2024-12-04 | 2024-12-17 |  | OFFICE | 2024-12-17 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26210011 |  | 0
KY | KY - CENTRAL | 2629 | 24298240500 |  | 100360800 |  | 6736228G |  |  |  | 563 | EX | 1" P SHORT | 2621P | HORSESHOE | 44 HORSESHOE DR | 017 | PAR | 2024-12-17 | U124604 | U129294 | 2024-12-03 | 2024-12-17 | 2024-12-17 |  | NRICHIE | 2024-12-16 | 2024-12-11 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 16.4167 | 3 | 4781.77 | 1307.72 | 601.64 | 813.9 | 2058.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24298262800 |  | 100296007 |  | 6716216O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LIMA | 522 LIMA DR 1 | 067 | LEX | 2024-12-04 | U123688 | U138682 | 2024-12-03 | 2025-03-25 | 2026-09-30 |  | MCRAIG | 2024-12-03 | 2024-10-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 13.3167 | 4 | 5832.59 | 4610.82 | 727.67 | 329.82 | 164.28 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24298397800 |  | 100337927 |  | 6712216B | 2410596 |  |  | 563 | EX | 1" P LONG/PRMT READY 12/19/24 | 2600B | BRADLEY | 150 BRADLEY LN | 067 | LEX | 2025-01-03 | U129722 | U130616 | 2024-12-04 | 2024-12-17 | 2025-01-02 |  | DAVID YOUNG | 2025-01-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1698.26 | 0 | 356.09 | 0 | 1342.17 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24298411100 |  | 100267320 |  | 7352260-E | 2410564 |  |  | 563 | EX | 1.25" P SHORT | 2621P | FRANKLIN | 512 FRANKLIN CT | 089 | ASH | 2024-12-16 | U124604 | U127708 | 2024-12-04 | 2024-12-26 | 2024-12-26 |  | MCOLLET | 2024-12-13 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 16 | 2 | 4691.82 | 1266.45 | 588.11 | 2735.14 | 102.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24298418800 |  | 100413888 |  | 6712212K |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | DEVONPORT | 1308 DEVONPORT DR | 067 | LEX | 2025-01-10 | U930915 | U124604 | 2024-12-04 | 2025-12-31 |  |  | MCRAIG | 2025-01-09 | 2025-01-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.6833 | 3 | 1914.7 | 1190.97 | 227.26 | 426.91 | 69.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24298428400 |  | 100250231 |  | 7360248A |  |  |  | 563 | EX | 99 1"P LONG | 2621P | CEMETERY | 8488 CEMETERY RD | 019 | CAT | 2025-01-07 | U123688 | U132253 | 2024-12-04 | 2024-12-18 | 2025-01-03 |  | MCOLLET | 2025-01-03 | 2024-12-23 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 31.8167 | 6 | 7149.89 | 2325.65 | 236.2 | 1982.05 | 2605.99 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24298465600 |  | 500180328 |  | 6744204B |  |  |  | 563 | EX | 99 1" P LONG | 2600B | WESTMEADE | 620 WESTMEADE DR | 049 | WIN | 2024-12-17 | U461516 | U132253 | 2024-12-04 | 2024-12-09 | 2024-12-20 |  | NEAL JOHNSON | 2024-12-17 |  | 2024-12-17 | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 8 | 1 | 5234.13 | 587.16 | 306.44 | 691.33 | 3649.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24298553900 |  | 100348262 |  | 6748208I | 2293700 |  |  | 566 | EX | ABANDON SL/ 22026237301 | 2600B | BAIT | 1 BAIT ST 2F | 049 | WIN | 2024-12-05 | U126604 | U128445 | 2024-12-05 | 2024-12-23 |  |  | WILLIAM FULKS | 2024-12-05 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26290043 |  | 1 | 567.27 | 0 | 0 | 0 | 567.27 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24298555700 |  | 500064951 |  | 6748208I | 2293700 |  |  | 565 | EX | RPLC SL/22026237301 | 2600B | BAIT | 3 BAIT ST | 049 | WIN | 2024-12-05 | U126604 | U132386 | 2024-12-05 | 2024-12-23 |  |  | WILLIAM FULKS | 2024-12-05 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 57183.45 | 0 | 53788.48 | 0 | 3394.97 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24298557000 |  | 100348263 |  | 6748208I | 2293700 |  |  | 566 | EX | ABN SL/22026237301 | 2600B | BAIT | 1 BAIT ST | 049 | WIN | 2024-12-05 | U126604 | U132386 | 2024-12-05 | 2024-12-23 |  |  | WILLIAM FULKS | 2024-12-05 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26290043 |  | 1 | 567.27 | 0 | 0 | 0 | 567.27 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24298558800 |  | 501374397 |  | 7256280M |  |  |  | 563 | EX | PAPER W/500084769 | 2621P | PARKER | 697 PARKER RD BLD 19 | 161 | MAY | 2024-12-11 | U123688 | U127708 | 2024-12-05 | 2024-12-19 | 2024-12-19 |  | SDADAMS | 2024-12-10 |  |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26320011 | 9.4 | 3 | 1010.49 | 712.63 | 0 | 297.86 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24298574200 |  | 501335647 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTRQD | 2621P | TUG RIVER | 1169 TUG RIVER RD | 159 | INE | 2024-12-13 | U130172 | U140273 | 2024-12-05 | 2024-12-26 | 2025-01-16 |  | JKIRK | 2024-12-13 | 2024-12-13 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 6.3167 | 1 | 612.04 | 578.27 | 0 | 33.77 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24298578400 |  | 100285586 |  | 6768172A |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | BROADWAY | 533 BROADWAY ST | 065 | IRV | 2024-12-05 | DENNING | U129939 | 2024-12-05 | 2024-12-05 |  |  | DENNING | 2024-12-05 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26290031 | 10.1 | 2 | 1976.93 | 844.37 | 1044.79 | 49.29 | 38.48 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24298599900 |  | 100468547 |  | 6744208P | 2407925 |  |  | 566 | EX | ABANDON SL/ 24026358600 | 2600B | MAIN | 25 S MAIN ST 2F | 049 | WIN | 2024-12-06 | U126604 | U128445 | 2024-12-05 | 2024-12-23 |  |  | WILLIAM FULKS | 2024-12-05 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - WEST | 2621 | 24298620300 |  | 100299742 |  | 6712212D |  |  |  | 563 | EX | 20 1" P LONG/PRMT READY 12/19 | 2600B | WESTLAND | 741 WESTLAND DR | 067 | LEX | 2024-12-26 | U126532 | U132627 | 2024-12-05 | 2024-12-17 | 2025-01-02 |  | LESLIE SHARON | 2024-12-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 16 | 2 | 6841.25 | 1221.14 | 435.78 | 900.53 | 4283.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24298913600 |  | 501358758 |  | 6700212O | 2398395 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | GRANGER | 230 GRANGER LN | 239 | VER | 2024-12-20 | U128816 | U126856 | 2024-12-06 | 2024-12-09 | 2024-12-20 |  | OLIVER MAYNARD | 2024-12-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 4427.21 | 662.59 | 306.44 | 38.7 | 3419.48 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24298913800 |  | 501358757 |  | 6700212O | 2398395 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | GRANGER | 234 GRANGER LN | 239 | VER | 2024-12-20 | U461516 | U126856 | 2024-12-06 | 2024-12-09 | 2024-12-20 |  | NEAL JOHNSON | 2024-12-20 |  | 2024-12-20 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 5145.62 | 587.16 | 327.17 | 691.33 | 3539.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24298915700 |  | 100317029 |  | 6716208J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | REBEL | 2025 REBEL RD | 067 | LEX | 2024-12-09 | U124604 | U139701 | 2024-12-06 | 2024-12-05 | 2024-12-23 |  | MCRAIG | 2024-12-06 | 2024-08-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 34.9667 | 12 | 4471.42 | 2987.77 | 495.87 | 987.78 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24298924800 |  | 100355126 |  | 7260280M |  |  |  | 563 | EX | 1"P-LONG | 2621P | POPLAR | 306 POPLAR ST | 161 | MAY | 2024-12-19 | U124604 | U128727 | 2024-12-06 | 2024-12-09 | 2024-12-20 |  | SDADAMS | 2024-12-18 | 2024-12-17 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26320011 | 37.9333 | 6 | 3426.02 | 2886.96 | 303.88 | 168.58 | 66.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24298928300 |  | 100324443 |  | 6720204E |  |  |  | 565 | EX | REPAIR SERVICE LINE | 2621P | OLYMPIA | 3548 OLYMPIA RD | 067 | LEX | 2024-12-09 | U124604 | U139701 | 2024-12-06 | 2024-12-06 |  |  | RJCRAWF | 2024-12-06 | 2024-12-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.7333 | 3 | 1079.48 | 620.96 | 302.34 | 36.3 | 119.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24298933100 |  | 500704103 |  | 6724208H |  |  |  | 563 | EX | 99 1" P SHORT/PRMT READY 12/24 | 2600B | ROYAL TROON | 3293 ROYAL TROON RD | 067 | LEX | 2025-01-13 | U461516 | U134375 | 2024-12-06 | 2024-12-31 | 2025-01-14 |  | NEAL JOHNSON | 2025-01-13 |  | 2025-01-13 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 3646.03 | 487.03 | 315.49 | 412.11 | 2431.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24298933400 |  | 501358741 |  | 6700212O | 2398395 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | ABINGDON | 505 ABINGDON AV | 239 | VER | 2024-12-18 | U125201 | U126856 | 2024-12-06 | 2024-12-09 | 2024-12-20 |  | LYN STAFFORD | 2024-12-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4 | 1 | 3956.59 | 321.49 | 280.66 | 18.78 | 3335.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24298972700 |  | 100289188 |  | 6724212A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | ANNISTON | 562 ANNISTON DR | 067 | LEX | 2024-12-09 | U124604 | U141176 | 2024-12-06 | 2024-12-06 | 2024-12-06 |  | JOCHOA | 2024-12-06 | 2024-12-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 5.6 | 2 | 1889.7 | 1271.39 | 406.4 | 74.27 | 137.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24298973200 |  | 100319985 |  | 6716208L | 2410597 |  |  | 565 | EX | MTR MOVE OUT/REPL-2"PMLP S/L | 2621P | BELLEFONTE | 1953 BELLEFONTE DR | 067 | LEX | 2025-06-05 | WCRIM | U124604 | 2024-12-06 | 2025-12-31 |  |  | WCRIM | 2025-06-05 | 2024-12-27 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 39.75 | 11 | 5882.01 | 2186.2 | 666.26 | 128.73 | 2900.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24299035000 |  | 100329623 |  | 6720208D |  |  |  | 565 | EX | REPAIR SERVICE LINE | 2621P | SAINT CHRISTOP | 2096 SAINT CHRISTOP DR | 067 | LEX | 2024-12-07 | U461322 | U139701 | 2024-12-07 | 2024-12-06 |  |  | STEVE CANOY | 2024-12-07 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.7167 | 2 | 2850.4 | 319.63 | 0 | 322.55 | 2208.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24299064100 |  | 501355441 |  | 6712204J | 2398051 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | MERGANSER | 120 MERGANSER CT LT36 | 113 | NIC | 2024-12-19 | U461516 | U133050 | 2024-12-09 | 2024-12-10 | 2024-12-23 |  | NEAL JOHNSON | 2024-12-19 | 2024-12-18 | 2024-12-19 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 11.6333 | 2 | 5947.17 | 855.05 | 274.27 | 1006.75 | 3811.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24299072000 |  | 100287052 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2621P | HIGHLAND PARK | 926 HIGHLAND PARK DR | 067 | LEX | 2024-12-10 | U129722 | U132386 | 2024-12-09 | 2024-12-23 |  |  | DAVID YOUNG | 2024-12-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2424.13 | 0 | 0 | 0 | 2424.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24299082900 |  | 100311061 |  | 6712208N |  |  |  | 565 | EX | GRADE 1 REPLACE SERV LINE | 2621P | CINDY BLAIR | 779 CINDY BLAIR WY | 067 | LEX | 2024-12-11 | U124604 | U129939 | 2024-12-09 | 2024-12-09 | 2024-12-09 |  | RSTRONG | 2024-12-10 | 2024-12-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.1333 | 3 | 1305.22 | 614.33 | 382.39 | 212.3 | 96.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24299115000 |  | 501371660 |  | 7260280M |  |  |  | 563 | EX | 1 " P LONG | 2621P | LEXINGTON | 660 LEXINGTON ST 1 | 161 | MAY | 2024-12-20 | U124604 | U130192 | 2024-12-09 | 2024-12-23 | 2024-12-23 |  | SDADAMS | 2024-12-19 | 2024-12-19 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26320011 | 24.5667 | 3 | 18404.67 | 1867.96 | 401.62 | 109.08 | 16026.01 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24299115100 |  | 501371661 |  | 7260280M |  |  |  | 563 | EX | MANIFOLD W/ 501371660 | 2621P | LEXINGTON | 660 LEXINGTON ST 2 | 161 | MAY | 2024-12-23 | U461383 | U130192 | 2024-12-09 | 2024-12-23 | 2024-12-23 |  | SDADAMS | 2024-12-19 |  |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26320011 | 0.68333 | 1 | 58.48 | 55.25 | 0 | 3.23 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24299116900 |  | 100408944 |  | 6720216F |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | PENNEBAKER | 1005 PENNEBAKER DR B | 067 | LEX | 2024-12-10 | U930915 | U129939 | 2024-12-09 | 2024-12-09 |  |  | HSTANFI | 2024-12-09 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.65 | 1 | 51.37 | 48.53 | 0 | 2.84 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24299178400 |  | 100277638 |  | 6688228E |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTRQD | 2621P | ALLNUTT | 121 ALLNUTT DR | 073 | FRA | 2025-01-17 | EFGOINS | U140273 | 2024-12-10 | 2024-12-31 | 2025-01-23 |  | EFGOINS | 2025-01-17 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 7.7 | 2 | 1819.48 | 503.1 | 0 | 33.13 | 1283.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24299186000 |  | 100286956 |  | 6720212F | 2285555 |  |  | 566 | EX | ABANDON SL | 2600B | CASTLEWOOD | 212 CASTLEWOOD DR | 067 | LEX | 2024-12-11 | U126308 | U132386 | 2024-12-10 | 2049-12-31 |  |  | JAMIE ENSMINGER | 2024-12-11 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 553.08 | 0 | 0 | 0 | 553.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24299192800 |  | 100287053 |  | 6720212F | 2293756 |  |  | 565 | EX | RPLC SL/22026239700 | 2621P | HIGHLAND PARK | 928 HIGHLAND PARK DR | 067 | LEX | 2024-12-11 | U129722 | U132386 | 2024-12-10 | 2024-12-23 |  |  | DAVID YOUNG | 2024-12-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2577.96 | 0 | 133.83 | 0 | 2444.13 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24299199100 |  | 501373722 |  | 7364188A | 2410581 |  |  | 563 | EX | 99 2" P SHORT | 2621P | MAIN | 221 E MAIN ST | 159 | INE | 2025-01-02 | JCKIRK | U134375 | 2024-12-10 | 2024-12-26 | 2025-01-10 |  | JCKIRK | 2025-01-02 | 2024-12-17 |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26330011 | 44.9833 | 4 | 11643.74 | 3484.19 | 0 | 224.95 | 7934.6 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24299213800 |  | 100239923 |  | 7352264I |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTRQD | 2621P | RIVERSIDE | 513 RIVERSIDE DR | 089 | RUS | 2025-02-24 | RECUMP | U140273 | 2024-12-10 | 2024-12-31 | 2025-01-23 |  | RECUMP | 2025-02-24 | 2024-12-26 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 26.5333 | 7 | 2532.12 | 1963.17 | 101.44 | 467.51 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24299231500 |  | 501368206 |  | 7348264L | 2408664 |  |  | 563 | EX | TAP W/ MAIN JO # 24-0263614-00 | 2600B | DOYLE | 150 DOYLE LN | 089 | FLA | 2025-04-01 | U124015 | U132253 | 2024-12-10 | 2025-12-23 | 2025-12-25 |  | ORA SLONE | 2025-04-01 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBTWM |  | 100 | 056332B26310012 | 6.2833 | 1 | 1973.1 | 398.25 | 0 | 99.1 | 1475.75 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24299235600 |  | 100260692 |  | 7352256K |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | GALLOWAY | 2138 GALLOWAY ST | 019 | ASH | 2025-02-03 | U124604 | U140273 | 2024-12-10 | 2024-12-31 | 2025-01-23 |  | ABHATFIE | 2025-01-31 | 2025-01-23 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 20.6667 | 3 | 1655.15 | 1553.3 | 0 | 101.85 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24299248200 |  | 501374447 |  | 6716216C | 2301170 |  |  | 563 | EX | PAPER W/ 501369334 | 2600B | STOCKTON | 1988 STOCKTON WY STE 100 | 067 | LEX | 2024-12-17 | U124604 | U127708 | 2024-12-10 | 2024-12-11 | 2024-12-26 |  | OFFICE | 2024-12-17 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26210011 |  | 1
KY | KY - WEST | 2621 | 24299248500 |  | 501374448 |  | 6716216C | 2301170 |  |  | 563 | EX | PAPER W/ 501369334 | 2600B | STOCKTON | 1988 STOCKTON WY STE 130 | 067 | LEX | 2024-12-17 | U124604 | U127708 | 2024-12-10 | 2024-12-17 | 2024-12-26 |  | OFFICE | 2024-12-17 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26210011 |  | 1
KY | KY - WEST | 2621 | 24299248600 |  | 501374449 |  | 6716216C | 2301170 |  |  | 563 | EX | PAPER W/ 501369334 | 2600B | STOCKTON | 1988 STOCKTON WY STE 140 | 067 | LEX | 2024-12-17 | U124604 | U127708 | 2024-12-10 | 2024-12-11 | 2024-12-26 |  | OFFICE | 2024-12-17 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26210011 |  | 1
KY | KY - WEST | 2621 | 24299248700 |  | 501374450 |  | 6716216C | 2301170 |  |  | 563 | EX | PAPER W/ 501369334 | 2600B | STOCKTON | 1988 STOCKTON WY STE 160 | 067 | LEX | 2024-12-17 | U124604 | U127708 | 2024-12-10 | 2024-12-11 | 2024-12-26 |  | OFFICE | 2024-12-17 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26210011 |  | 1
KY | KY - WEST | 2621 | 24299248800 |  | 501374451 |  | 6716216C | 2301170 |  |  | 563 | EX | PAPER W/ 501369334 | 2600B | STOCKTON | 1988 STOCKTON WY STE 195 | 067 | LEX | 2024-12-17 | U124604 | U127708 | 2024-12-10 | 2024-12-11 | 2024-12-26 |  | OFFICE | 2024-12-17 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26210011 |  | 1
KY | KY - WEST | 2621 | 24299251000 |  | 500218734 |  | 6712208N | 2181236 |  |  | 563 | EX | 1" P SHORT/PRMT READY 12/24 | 2600B | GRASMERE | 3328 GRASMERE DR | 067 | LEX | 2025-01-13 | U126284 | U133050 | 2024-12-10 | 2024-12-31 | 2025-01-14 |  | JOSH PASLEY | 2025-01-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 10 | 1 | 4939.6 | 634.53 | 0 | 516.81 | 3788.26 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24299256000 |  | 100425885 |  | 6740232M |  |  |  | 563 | EX | 99 1" P LONG | 2621P | 8TH | 220 W 8TH ST | 017 | PAR | 2025-01-17 | U124604 | U120250 | 2024-12-10 | 2025-01-30 | 2025-01-30 |  | NRICHIE | 2025-01-16 | 2024-12-13 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 18.55 | 4 | 6533.13 | 1412.92 | 428.02 | 182.68 | 4509.51 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24299475800 |  | 100265190 |  | 7352260O | 2410870 |  |  | 563 | EX | 99 1" P LONG | 2621P | MARCUM | 336 MARCUM RD | 019 | ASH | 2024-12-30 | ABHATFIE | U132253 | 2024-12-11 | 2024-12-26 | 2025-01-09 |  | ABHATFIE | 2024-12-30 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 16 | 2 | 1348.55 | 1240.56 | 0 | 72.47 | 35.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24299515600 |  | 501303245 |  | 6724208M |  |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | SUNNY LANDING | 644 SUNNY LANDING TR | 067 | LEX | 2024-12-27 | U126532 | U126856 | 2024-12-11 | 2024-12-17 | 2025-01-02 |  | LESLIE SHARON | 2024-12-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26210011 | 16 | 2 | 3947.78 | 1221.14 | 287.04 | 900.53 | 1539.07 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24299581600 |  | 501032452 |  | 6712232M | 0783585 |  |  | 563 | EX | 20 1" P LONG/PRMT RCVD | 2600B | INVERNESS | 150 INVERNESS DR 61 | 209 | GEO | 2025-01-29 | U128816 | U132805 | 2024-12-11 | 2025-01-13 | 2025-01-24 |  | OLIVER MAYNARD | 2025-01-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4.75 | 1 | 5928.84 | 307.7 | 0 | 20.25 | 5600.89 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24299582500 |  | 100287050 |  | 6720212F | 2293756 |  |  | 565 | EX | REPLACE SL/22026239700 | 2600B | HIGHLAND PARK | 920 HIGHLAND PARK DR | 067 | LEX | 2024-12-12 | U129722 | U123268 | 2024-12-11 | 2024-12-20 |  |  | DAVID YOUNG | 2024-12-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2429.13 | 0 | 0 | 0 | 2429.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24299639000 |  | 501343714 |  | 6716220M | 2394864 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | MARLENA | 1212 MARLENA LN | 067 | LEX | 2024-12-26 | U461516 | U126856 | 2024-12-11 | 2024-12-17 | 2025-01-02 |  | NEAL JOHNSON | 2024-12-26 |  | 2024-12-26 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4.3167 | 1 | 4373 | 315.61 | 266.31 | 371.6 | 3419.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24299646500 |  | 501334653 |  | 6716216E | 2289300 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | GERANIUM | 2425 GERANIUM LN | 067 | LEX | 2024-12-26 | U128336 | U126856 | 2024-12-11 | 2024-12-17 | 2025-01-02 |  | JOSHUA COX | 2024-12-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1350.53 | 0 | 287.04 | 0 | 1063.49 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24299716600 |  | 500017198 |  | 6760176J |  |  |  | 563 | EX | 1" P SHORT | 2621P | BLACKBURN | 421 BLACKBURN RD | 065 | IRV | 2024-12-17 | DENNING | U134341 | 2024-12-11 | 2024-12-23 | 2024-12-25 |  | DENNING | 2024-12-17 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 8.6167 | 3 | 3535.62 | 709.12 | 497.42 | 227.72 | 2101.36 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24299997700 |  | 100256592 |  | 7356152E |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | 1ST | 192 1ST ST | 071 | HAR | 2025-01-14 | JAHOWARD | U140273 | 2024-12-11 | 2025-01-02 | 2025-01-24 |  | JAHOWARD | 2025-01-14 | 2024-12-26 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 24.25 | 4 | 2005.95 | 1799.02 | 90.08 | 116.85 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24300002900 |  | 100443130 |  | 6716216L |  |  |  | 563 | EX | PAPER W/ 100443170 | 2600B | NANDINO | 1034 NANDINO BV | 067 | LEX | 2024-12-17 | U125201 | U128266 | 2024-12-11 | 2024-12-12 | 2024-12-26 |  | OFFICE | 2024-12-17 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26210011 |  | 1
KY | KY - WEST | 2623 | 24300008000 |  | 100279308 |  | 6688228K |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | RANDOLPH | 114 RANDOLPH RD | 073 | FRA | 2024-12-11 | HMCKUNE | U129939 | 2024-12-11 | 2024-12-11 |  |  | HMCKUNE | 2024-12-11 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.6 | 1 | 801.3 | 133.57 | 333.53 | 7.8 | 326.4 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24300074400 |  | 100262129 |  | 7352256D | 1635077 |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | POLLARD | 612 POLLARD RD | 019 | ASH | 2024-12-13 | ABHATFIE | U143023 | 2024-12-12 | 2025-06-12 | 2026-12-31 |  | ABHATFIE | 2024-12-13 | 2024-12-12 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 54.2667 | 8 | 8539.07 | 4022.8 | 103.82 | 341.67 | 4070.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24300086700 |  | 501355450 |  | 6712204J | 2398051 |  |  | 563 | EX | 1" P SHORT | 2600B | PINTAIL | 113 PINTAIL CT | 113 | NIC | 2024-12-27 | U461516 | U126856 | 2024-12-12 | 2024-12-17 | 2025-01-02 |  | NEAL JOHNSON | 2024-12-27 |  | 2024-12-27 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 3155.27 | 587.16 | 312.33 | 691.33 | 1564.45 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24300087400 |  | 100353278 |  | 7256280G |  |  |  | 563 | EX | 1" P SHORT | 2621P | 2ND | 520 W 2ND ST | 161 | MAY | 2025-01-08 | JTOY | U132258 | 2024-12-12 | 2024-12-26 | 2025-01-09 |  | SDADAMS | 2025-01-08 | 2024-12-20 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26320011 | 55.3 | 9 | 4420.77 | 3818.55 | 132.25 | 237.61 | 232.36 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24300092000 |  | 501152057 |  | 6744208P | 2407767 |  |  | 566 | EX | ABANDON SL/ 24026356800 | 2600B | MAIN | 57 S MAIN ST ST 3 | 049 | WIN | 2024-12-13 | U126285 | U128445 | 2024-12-12 | 2024-12-23 |  |  | DUSTIN DAVIS | 2024-12-13 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - CENTRAL | 2629 | 24300092100 |  | 100349484 |  | 6744208P | 2407767 |  |  | 566 | EX | ABANDON SL/ 24026356800 | 2600B | MAIN | 57< S MAIN ST | 049 | WIN | 2024-12-13 | U126285 | U128445 | 2024-12-12 | 2024-12-23 |  |  | DUSTIN DAVIS | 2024-12-13 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - CENTRAL | 2629 | 24300092300 |  | 100450669 |  | 6744208P | 2407767 |  |  | 566 | EX | ABANDON SL/ 24026356800 | 2600B | MAIN | 59 S MAIN ST | 049 | WIN | 2024-12-13 | U126285 | U128445 | 2024-12-12 | 2024-12-23 |  |  | DUSTIN DAVIS | 2024-12-13 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - CENTRAL | 2629 | 24300100600 |  | 501374521 |  | 6740232M | 2410928 |  |  | 563 | EX | 1" P LONG | 2621P | PLEASANT | 403 PLEASANT ST GEN | 017 | PAR | 2024-12-31 | U124604 | U126856 | 2024-12-12 | 2024-12-27 | 2024-12-27 |  | NRICHIE | 2024-12-30 | 2024-12-19 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 35 | 5 | 8642.09 | 2823.01 | 616.06 | 2055.02 | 3148 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24300101100 |  | 501343709 |  | 6716220M | 2394864 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | MARLENA | 1232 MARLENA LN | 067 | LEX | 2024-12-26 | U128336 | U126856 | 2024-12-12 | 2024-12-17 | 2025-01-02 |  | JOSHUA COX | 2024-12-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 2725.13 | 0 | 287.04 | 0 | 2438.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24300101200 |  | 501343710 |  | 6716220M | 2394864 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | MARLENA | 1228 MARLENA LN | 067 | LEX | 2024-12-26 | U461516 | U126856 | 2024-12-12 | 2024-12-17 | 2025-01-02 |  | NEAL JOHNSON | 2024-12-26 |  | 2024-12-26 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 3.6833 | 1 | 5060.32 | 271.56 | 295 | 319.75 | 4174.01 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24300101400 |  | 501358744 |  | 6700212O | 2398395 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | ABINGDON | 552 ABINGDON AV | 239 | VER | 2025-01-15 | U126602 | U126856 | 2024-12-12 | 2024-12-31 | 2025-01-14 |  | DEREK PAYTON | 2025-01-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 1497.61 | 0 | 261.82 | 0 | 1235.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24300123200 |  | 501320319 |  | 6708204K | 2182537 |  |  | 563 | EX | 1" P SHORT | 2600B | BACKSTRETCH | 301 BACKSTRETCH LT36 | 113 | NIC | 2024-12-27 | U128336 | U123852 | 2024-12-12 | 2024-12-17 | 2025-01-02 |  | JOSHUA COX | 2024-12-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1868.41 | 0 | 287.04 | 0 | 1581.37 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24300124100 |  | 100239941 |  | 7352264E |  |  |  | 563 | EX | 99 1" P LONG | 2621P | FERRY | 202 FERRY ST DWNST | 089 | RUS | 2024-12-31 | U124604 | U142144 | 2024-12-12 | 2024-12-13 | 2024-12-26 |  | RECUMP | 2024-12-30 | 2024-12-23 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 15.95 | 5 | 1941.91 | 1119.2 | 94.06 | 678.33 | 50.32 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24300271700 |  | 100273845 |  | 6680228K |  |  |  | 563 | EX | 1" P SHORT | 2600B | DEVILS HOLLOW | 983 DEVILS HOLLOW RD | 073 | FRA | 2025-01-13 | U123111 | U128272 | 2024-12-13 | 2024-12-31 | 2025-01-14 |  | LYN STAFFORD | 2025-01-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4 | 1 | 3334.89 | 258.39 | 518.49 | 17 | 2541.01 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24300275100 |  | 100349676 |  | 6748208M | 2410886 |  |  | 563 | EX | 20 1" P SHORT | 2600B | GEORGIA | 2 GEORGIA ST | 049 | WIN | 2025-01-16 | U123111 | U138822 | 2024-12-13 | 2025-01-03 | 2025-01-16 |  | LYN STAFFORD | 2025-01-16 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 4 | 1 | 1669.89 | 261.48 | 256.44 | 17.21 | 1134.76 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24300275300 |  | 501372905 |  | 6732252G |  |  |  | 563 | EX | 1" P LONG | 2621P | LAKESIDE | 20 LAKESIDE DR | 097 | CYN | 2025-01-03 | U124604 | U133050 | 2024-12-13 | 2024-12-31 | 2024-12-31 |  | NRICHIE | 2025-01-02 | 2024-12-20 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 34.15 | 5 | 10624.79 | 2587.92 | 283.61 | 255.86 | 7497.4 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24300278500 |  | 100357327 |  | 7240280K |  |  |  | 563 | EX | 1" P SHORT | 2621P | KY 596 | 41041 KY 596 | 161 | GER | 2025-01-15 | U124604 | U128727 | 2024-12-13 | 2024-12-16 | 2025-01-15 |  | SDADAMS | 2025-01-14 | 2024-12-26 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26320011 | 26.7333 | 5 | 2326.01 | 1728.85 | 408.98 | 112.7 | 75.48 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24300278900 |  | 500664749 |  | 6764176P |  |  |  | 563 | EX | 1" P SHORT | 2621P | STAR MOUNTAIN | 106 STAR MOUNTAIN DR | 065 | IRV | 2025-01-02 | DENNING | U128272 | 2024-12-13 | 2024-12-31 | 2024-12-31 |  | DENNING | 2025-01-02 | 2024-12-20 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 23.3 | 6 | 3548.11 | 1780.92 | 567.87 | 1126.8 | 72.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24300299400 |  | 100287059 |  | 6720212F | 2293756 |  |  | 565 | EX | REPLACE SL/ 22026239700 | 2600B | HIGHLAND PARK | 944 HIGHLAND PARK DR | 067 | LEX | 2024-12-14 | U129722 | U128445 | 2024-12-13 | 2024-12-23 |  |  | DAVID YOUNG | 2024-12-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2396.63 | 0 | 0 | 0 | 2396.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24300299800 |  | 100286962 |  | 6720212F | 2293756 |  |  | 565 | EX | REPLACE SL/ 22026239700 | 2621P | CASTLEWOOD | 226 CASTLEWOOD DR | 067 | LEX | 2024-12-13 | U126308 | U128445 | 2024-12-13 | 2025-12-23 |  |  | JAMIE ENSMINGER | 2024-12-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.016667 | 1 | 2167.1 | 1.76 | 0 | 0.11 | 2165.23 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24300300600 |  | 100282069 |  | 6712232O |  |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | M L KING JR | 334 M L KING JR DR | 209 | GEO | 2025-01-25 | U126602 | U128272 | 2024-12-13 | 2025-01-10 | 2025-01-23 |  | DEREK PAYTON | 2025-01-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 9 | 1 | 6755.11 | 597 | 536.12 | 39.28 | 5582.71 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24300306700 |  | 501327310 |  | 6716232B | 2179247 |  |  | 563 | EX | 1" P SHORT BALL | 2600B | WELLESLY | 147 WELLESLY AV LT269 | 209 | GEO | 2025-01-15 | U461309 | U132258 | 2024-12-13 | 2024-12-31 | 2025-01-14 |  | RANDALL HUMPHREYS | 2025-01-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 1403.36 | 0 | 261.82 | 0 | 1141.54 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24300306800 |  | 501327323 |  | 6716232B | 2179247 |  |  | 563 | EX | 1" P SHORT BALL | 2600B | KIRKSTALL | 124 KIRKSTALL WY LT241 | 209 | GEO | 2025-01-03 | U129722 | U132258 | 2024-12-13 | 2024-12-31 | 2025-01-14 |  | DAVID YOUNG | 2025-01-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4.5 | 1 | 2179.2 | 288.77 | 261.82 | 18.99 | 1609.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24300314500 |  | 100335540 |  | 6712224L |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | GEORGETOWN | GEORGETOWN RD | 067 | LEX | 2024-12-13 | LSTONE | U143023 | 2024-12-13 | 2024-12-13 |  |  | LSTONE | 2024-12-13 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.05 | 1 | 3.77 | 3.57 | 0 | 0.2 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24300320500 |  | 100349458 |  | 6744208P | 2407925 |  |  | 565 | EX | REPLACE SL/ 24026358600 | 2621P | MAIN | 17 S MAIN ST | 049 | WIN | 2025-01-28 | U126285 | U128445 | 2024-12-13 | 2025-12-23 |  |  | DUSTIN DAVIS | 2025-01-28 | 2024-12-17 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26290032 | 46 | 6 | 9298.23 | 3525.05 | 0 | 1675.8 | 4097.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24300343100 |  | 100326786 |  | 6720208I |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HAMPSHIRE | 1412 HAMPSHIRE PL | 067 | LEX | 2024-12-23 | U141668 | U123688 | 2024-12-13 | 2025-12-31 |  |  | BYOUNG2 | 2024-12-20 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 0.28333 | 1 | 687.88 | 21.09 | 473.14 | 1.25 | 192.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24300349800 |  | 501372463 |  | 6712228G |  |  |  | 563 | EX | PAPER W/ 100283028 | 2621P | MILITARY | 616 MILITARY ST B | 209 | GEO | 2024-12-17 | U124604 | U120250 | 2024-12-13 | 2024-12-16 | 2024-12-31 |  | OFFICE | 2024-12-17 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26230011 |  | 1
KY | KY - WEST | 2621 | 24300447100 |  | 501348609 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | CALISTA FLAT | 733 CALISTA FLAT | 067 | LEX | 2024-12-27 | U129722 | U126856 | 2024-12-16 | 2024-12-17 | 2025-01-02 |  | DAVID YOUNG | 2024-12-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2038.19 | 615.08 | 287.04 | 35.92 | 1100.15 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24300455900 |  | 501003140 |  | T-1602-38 | 2410875 |  |  | 563 | EX | 1" P LONG | 2621P | US ROUTE 23 | 28474 US ROUTE 23 | 089 | S S | 2025-01-28 | U124604 | U129176 | 2024-12-16 | 2024-12-16 | 2025-01-03 |  | MCOLLET | 2025-01-27 | 2025-01-02 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 39.8667 | 8 | 4085.15 | 2205.32 | 492.63 | 1288.04 | 99.16 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24300458500 |  | 501317393 |  | 6716236J | 2178365 |  |  | 563 | EX | 1" P SHORT | 2600B | FLAMINGO | 112 FLAMINGO CR | 209 | GEO | 2025-01-14 | U461309 | U126856 | 2024-12-16 | 2024-12-31 | 2025-01-14 |  | RANDALL HUMPHREYS | 2025-01-13 | 2025-01-13 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 16 | 2 | 3770.62 | 1023.86 | 300.8 | 827.52 | 1618.44 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24300463500 |  | 500182120 |  | 6688228K |  |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | SHEFFIELD | 15 SHEFFIELD LN | 073 | FRA | 2025-01-22 | U461309 | U128727 | 2024-12-16 | 2025-01-06 | 2025-01-17 |  | RANDALL HUMPHREYS | 2025-01-17 | 2025-01-17 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 5837.94 | 511.93 | 261.82 | 413.76 | 4650.43 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24300466600 |  | 501347979 |  | 6696212P | 2292756 |  |  | 563 | EX | 20 1" P SHORT YEARLING | 2600B | SAFFRON | 510 SAFFRON LN LT97 | 239 | VER | 2025-01-14 | U128336 | U132805 | 2024-12-16 | 2024-12-31 | 2025-01-14 |  | JOSHUA COX | 2025-01-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 1951.02 | 0 | 294.1 | 0 | 1656.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24300468900 |  | 501320870 |  | 6728208I | 2182500 |  |  | 563 | EX | 99 1" P SHORT/NO PRMT REQ | 2600B | ANGUS | 1344 ANGUS TL LT38 | 067 | LEX | 2025-01-13 | U126532 | U120250 | 2024-12-16 | 2025-01-06 | 2025-01-17 |  | LESLIE SHARON | 2025-01-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26210011 | 3.3667 | 1 | 2263.89 | 209.28 | 261.82 | 174.35 | 1618.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24300484600 |  | 100301293 |  | 6712212H |  |  |  | 563 | EX | 1" P LONG | 2600B | DUNKIRK | 2036 DUNKIRK DR | 067 | LEX | 2025-01-23 | U126285 | U128266 | 2024-12-16 | 2025-01-07 | 2025-01-20 |  | DUSTIN DAVIS | 2025-01-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 9 | 1 | 5719.18 | 586.66 | 628.08 | 466.21 | 4038.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24300485700 |  | 501373246 |  | 6712204G |  |  |  | 563 | EX | 20 1" P LONG/PRMT RCVD | 2600B | MCGARRY | 3865 MCGARRY DR | 067 | LEX | 2025-01-24 | U129722 | U132805 | 2024-12-16 | 2025-01-13 | 2025-01-24 |  | DAVID YOUNG | 2025-01-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 9 | 1 | 4749.58 | 547.06 | 365.62 | 36.01 | 3800.89 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24300488300 |  | 500727330 |  | 16720212P | 0041732 |  |  | 563 | EX | PAPER MANIFOLD W/500725873 | 2600B | FORTUNE | 2473 FORTUNE DR 140 | 067 | LEX | 2024-12-19 | U124604 | U129176 | 2024-12-16 | 2024-12-16 | 2024-12-30 |  | OFFICE | 2024-12-19 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26210011 |  | 1
KY | KY - WEST | 2621 | 24300488400 |  | 501373408 |  | 6724212M |  |  |  | 563 | EX | PAPER MANIFOLD W/500725873 | 2600B | FORTUNE | 2473 FORTUNE DR 106 | 067 | LEX | 2024-12-19 | U124604 | U129176 | 2024-12-16 | 2024-12-16 | 2024-12-30 |  | OFFICE | 2024-12-19 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26210011 |  | 1
KY | KY - WEST | 2621 | 24300490300 |  | 100287500 |  | 6720212G |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTRQD | 2621P | DARLEY | 1024 DARLEY DR | 067 | LEX | 2025-01-27 | LSTANFI | U140273 | 2024-12-16 | 2025-01-08 | 2025-01-30 |  | LSTANFI | 2025-01-27 | 2025-01-03 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.1333 | 7 | 2091.66 | 795.67 | 0 | 66.83 | 1229.16 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24300576800 |  | 501361936 |  | 6712228L | 2292762 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | RUTH MILLER | 144 RUTH MILLER DR LT95 | 209 | GEO | 2025-01-16 | U126285 | U129531 | 2024-12-17 | 2025-01-06 | 2025-01-17 |  | DUSTIN DAVIS | 2025-01-16 | 2025-01-15 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 6487.84 | 550.54 | 0 | 36.23 | 5901.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24300585400 |  | 501373308 |  | 6720212J | 2410511 |  |  | 563 | EX | 320'-1"PMMP SHORT/PRMT RCVD | 2600B | OWENS | 223 OWENS AV | 067 | LEX | 2025-03-05 | U123111 | U132805 | 2024-12-17 | 2025-01-13 | 2025-02-21 |  | LYN STAFFORD | 2025-03-05 | 2025-02-13 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 38.1833 | 5 | 10424.14 | 2710.81 | 413.97 | 655.72 | 6643.64 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24300591800 |  | 501347981 |  | 6696212P | 2292756 |  |  | 563 | EX | 1" P SHORT | 2600B | SAFFRON | 502 SAFFRON LN | 239 | VER | 2025-01-31 | U126602 | U126856 | 2024-12-17 | 2024-12-31 | 2025-01-14 |  | DEREK PAYTON | 2025-01-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 1430.91 | 0 | 223.81 | 0 | 1207.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24300595000 |  | 501374535 |  | 6744208M |  |  |  | 563 | EX | PAPER W/500551728 | 2621P | BY PASS | 1600 BY PASS RD 1 | 049 | WIN | 2024-12-17 | U123688 | U134375 | 2024-12-17 | 2024-12-31 | 2024-12-31 |  | OFFICE | 2024-12-17 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26290011 |  | 1
KY | KY - WEST | 2621 | 24300603500 |  | 100323304 |  | 6716208P |  |  |  | 565 | EX | SERVICE LINE/METER UPGRADE | 2621P | ALBANY | 840 ALBANY RD | 067 | LEX | 2024-12-30 | U124604 | U124604 | 2024-12-17 | 2025-01-02 | 2025-01-02 |  | MSHARON | 2024-12-27 | 2024-12-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 38.6667 | 7 | 3605.27 | 2867.18 | 478.84 | 167.49 | 91.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24300632500 |  | 501374053 |  | 6720200B |  |  |  | 563 | EX | 99 1" P LONG/PRMT RCVD | 2600B | HARTLAND | 4954 HARTLAND PY | 067 | LEX | 2025-01-27 | U123111 | U120250 | 2024-12-17 | 2025-01-13 | 2025-01-24 |  | LYN STAFFORD | 2025-01-27 | 2025-01-24 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 16 | 2 | 5845.69 | 978.92 | 317.09 | 64.4 | 4485.28 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24300639800 |  | 100346421 |  | 6696212L |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | MONTGOMERY | 115 MONTGOMERY AV | 239 | VER | 2025-01-28 | U128410 | U140273 | 2024-12-17 | 2025-01-08 | 2025-01-30 |  | CDESPAIN | 2025-01-28 | 2025-01-20 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 24.25 | 8 | 2342.21 | 1746 | 0 | 596.21 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24300667800 |  | 500550470 |  | 6688228L | 9718931 |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SARATOGA | 106 SARATOGA | 073 | FRA | 2024-12-17 | DCOLLIN | U129939 | 2024-12-17 | 2024-11-21 | 2026-05-31 |  | DCOLLIN | 2024-12-17 | 2024-12-17 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 | 32.6 | 11 | 11543.79 | 3944.27 | 385.9 | 1145.02 | 6068.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24300672500 |  | 501374737 |  | 6720216A |  |  |  | 563 | EX | PAPER W/ 501352417 | 2600B | PROVIDENCE | 1041 PROVIDENCE PL STE 120 | 067 | LEX | 2024-12-19 | U125201 | U127708 | 2024-12-17 | 2024-12-18 | 2025-01-03 |  | OFFICE | 2024-12-19 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26210011 |  | 0
KY | KY - CENTRAL | 2629 | 24300807600 |  | 100270296 |  | 6736252M | 1635077 |  |  | 565 | EX | AOC L1 ATMOS CORR REPL RISER | 2629D | MAIN | 130 S MAIN ST | 097 | CYN | 2025-02-04 | U123688 | AOC SYST | 2024-12-17 | 2025-01-16 | 2025-02-15 |  | NRICHIE | 2025-02-03 | 2024-12-27 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26290031 | 16.8667 | 3 | 4114.83 | 1502.59 | 243.37 | 142.63 | 2226.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24300936500 |  | 500517670 |  | 6712204A |  |  |  | 563 | EX | 1" P LONG/PRMT RCVD | 2600B | CLEMENS | 4221 CLEMENS DR | 067 | LEX | 2025-01-15 | U123111 | U138822 | 2024-12-18 | 2025-01-10 | 2025-01-23 |  | LYN STAFFORD | 2025-01-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2479.28 | 489.46 | 255.11 | 32.2 | 1702.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24300938200 |  | 500243630 |  | 6720208J |  |  |  | 565 | EX | SERVICE LINE REPLACE | 2621P | MANOR | 2084 MANOR DR | 067 | LEX | 2025-01-13 | U124604 | U124604 | 2024-12-18 | 2025-01-31 |  |  | RJCRAWF | 2025-01-10 | 2025-01-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 37.5667 | 6 | 3219.32 | 2243.82 | 553.35 | 275.63 | 146.52 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24300938600 |  | 100253892 |  | 7356216D |  |  |  | 563 | EX | 1" P SHORT | 2621P | LOCK | 509 N LOCK AV | 127 | LOU | 2025-01-28 | U124604 | U131378 | 2024-12-18 | 2024-12-26 | 2025-01-10 |  | RECUMP | 2025-01-27 | 2025-01-07 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 21.6667 | 4 | 2356.49 | 1451.65 | 166.96 | 680.16 | 57.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24300940000 |  | 500852718 |  | 16716204P | 0252727 |  |  | 563 | EX | 1" P LONG/PRMT RCVD | 2600B | HAMMOCK OAK | 944 HAMMOCK OAK LN LT9 | 067 | LEX | 2025-01-24 | U128336 | U129531 | 2024-12-18 | 2025-01-13 | 2025-01-24 |  | JOSHUA COX | 2025-01-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 4207.3 | 0 | 303.42 | 0 | 3903.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24300960600 |  | 100299727 |  | 6712212D | 2411097 |  |  | 563 | EX | 99 1" P SHORT/PRMT RCVD | 2600B | DUNCAN MACHINE | 2020 DUNCAN MACHINE DR | 067 | LEX | 2025-02-11 | U461516 | U126919 | 2024-12-18 | 2025-01-13 | 2025-01-24 |  | NEAL JOHNSON | 2025-01-24 | 2025-01-17 | 2025-01-17 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 16 | 2 | 6323.35 | 974.06 | 1072.25 | 824.22 | 3452.82 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24300974000 |  | 500899068 |  | 6676224K | 0356194 |  |  | 563 | EX | 1" P SHORT | 2600B | OLD STATION | 305 OLD STATION RD | 073 | FRA | 2025-01-13 | U123111 | U126856 | 2024-12-18 | 2024-12-31 | 2025-01-14 |  | LYN STAFFORD | 2025-01-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 3 | 1 | 1320.14 | 193.78 | 0 | 12.75 | 1113.61 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24300974300 |  | 500899065 |  | 6676224K | 0356194 |  |  | 563 | EX | 1" P SHORT | 2600B | OLD STATION | 317 OLD STATION RD | 073 | FRA | 2025-01-13 | U123111 | U126856 | 2024-12-18 | 2024-12-31 | 2025-01-14 |  | LYN STAFFORD | 2025-01-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 3 | 1 | 1318.67 | 193.78 | 0 | 12.75 | 1112.14 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24301101400 |  | 500353512 |  | 7236212K | 9403488 |  |  | 563 | EX | 20 1" P SHORT | 2621P | FOGG | 1947 FOGG PK LT3 | 173 | MT | 2025-01-03 | DENNING | U132805 | 2024-12-19 | 2024-12-20 | 2025-01-07 |  | DENNING | 2025-01-03 | 2025-01-02 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 14.1 | 7 | 4086.66 | 1051.96 | 1127.48 | 166.61 | 1740.61 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24301118100 |  | 501327324 |  | 6716232B | 2179247 |  |  | 563 | EX | 1" P SHORT: BALL HOMES | 2600B | KIRKSTALL | 126 KIRKSTALL WY LT242 | 209 | GEO | 2025-01-03 | U129722 | U134341 | 2024-12-19 | 2024-12-31 | 2025-01-14 |  | DAVID YOUNG | 2025-01-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26230011 | 3.5 | 1 | 2110.86 | 224.63 | 261.82 | 14.79 | 1609.62 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24301119700 |  | 100252974 |  | 7356256F |  |  |  | 563 | EX | 1" P LONG | 2621P | PARK | 3230 PARK ST | 019 | ASH | 2025-01-02 | ABHATFIE | U123852 | 2024-12-19 | 2025-01-07 | 2025-01-07 |  | ABHATFIE | 2025-01-02 | 2025-01-02 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 31.1 | 4 | 2719.78 | 2300.26 | 0 | 357.36 | 62.16 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24301123000 |  | 501338366 |  | 6716232B | 2179247 |  |  | 563 | EX | 1" P SHORT: BALL HOMES | 2600B | DUNMORE | 105 DUNMORE LN LT198 | 209 | GEO | 2025-01-15 | U461516 | U133050 | 2024-12-19 | 2024-12-31 | 2025-01-15 |  | NEAL JOHNSON | 2025-01-15 |  | 2025-01-15 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 5383.13 | 514.18 | 268.54 | 413.9 | 4186.51 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24301123100 |  | 501338370 |  | 6716232B | 2179247 |  |  | 563 | EX | 1" P SHORT: BALL HOMES | 2600B | DUNMORE | 102 DUNMORE LN LT202 | 209 | GEO | 2025-01-24 | U461309 | U133050 | 2024-12-19 | 2024-12-31 | 2025-01-28 |  | RANDALL HUMPHREYS | 2025-01-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 2787.23 | 511.93 | 256.33 | 413.76 | 1605.21 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24301123300 |  | 501338371 |  | 6716232B | 2179247 |  |  | 563 | EX | 1" P SHORT: BALL HOMES | 2600B | DUNMORE | 104 DUNMORE LN LT203 | 209 | GEO | 2025-01-28 | U461516 | U133050 | 2024-12-19 | 2024-12-31 | 2025-01-28 |  | NEAL JOHNSON | 2025-01-28 |  | 2025-01-28 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 3.6833 | 1 | 1828.18 | 237.8 | 261.82 | 191.43 | 1137.13 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24301123500 |  | 501332949 |  | 6716232I | 2180856 |  |  | 563 | EX | 1" P SHORT: BALL HOMES | 2600B | LIMESTONE | 143 LIMESTONE LN | 209 | GEO | 2025-01-03 | U126532 | U133050 | 2024-12-19 | 2024-12-31 | 2025-01-14 |  | LESLIE SHARON | 2025-01-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4.5 | 1 | 1918.92 | 294.18 | 261.82 | 233.14 | 1129.78 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24301123600 |  | 501332951 |  | 6716232I | 2180856 |  |  | 563 | EX | 1" P SHORT: BALL HOMES | 2600B | LIMESTONE | 145 LIMESTONE LN | 209 | GEO | 2025-01-03 | U126532 | U133050 | 2024-12-19 | 2024-12-31 | 2025-01-14 |  | LESLIE SHARON | 2025-01-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 3.5 | 1 | 1798.79 | 228.79 | 261.82 | 181.34 | 1126.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24301123900 |  | 501332965 |  | 6716232I | 2180856 |  |  | 563 | EX | 1" P LONG: BALL HOMES | 2600B | LIMESTONE | 136 LIMESTONE LN | 209 | GEO | 2025-01-16 | U461309 | U133050 | 2024-12-19 | 2024-12-31 | 2025-01-15 |  | RANDALL HUMPHREYS | 2025-01-15 | 2025-01-15 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 5036.74 | 511.93 | 261.82 | 413.76 | 3849.23 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24301124100 |  | 501332969 |  | 6716232I | 2180856 |  |  | 563 | EX | 1" P SHORT: BALL HOMES | 2600B | OXFORD LANDING | 103 OXFORD LANDING DR | 209 | GEO | 2025-01-07 | U461309 | U133050 | 2024-12-19 | 2024-12-31 | 2025-01-14 |  | RANDALL HUMPHREYS | 2025-01-03 | 2025-01-03 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 2450.16 | 511.93 | 300.8 | 33.69 | 1603.74 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24301127100 |  | 100243561 |  | 7352256C | 1855491 |  |  | 565 | EX | RPLC SL/18026794400 | 2621P | SULLIVAN | 310< SULLIVAN ST | 127 | LOU | 2025-01-29 | U123965 | U132386 | 2024-12-19 | 2025-12-19 |  |  | CJH MITCHELL DICKESS | 2025-01-28 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 4128.49 | 0 | 0 | 0 | 4128.49 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24301130800 |  | 100330748 |  | 6720212O |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D512077 | 2621P | SHERMAN | 378 SHERMAN AV | 067 | LEX | 2025-01-06 | U137585 | U124604 | 2024-12-19 | 2024-12-20 | 2025-01-09 |  | RJCRAWF | 2025-01-03 | 2024-12-27 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 45.75 | 7 | 5199.66 | 2366.16 | 0 | 154.66 | 2678.84 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24301144800 |  | 100254162 |  | 7348264N |  |  |  | 563 | EX | 1" P LONG | 2621P | COLLINS | 1413 W COLLINS ST | 089 | FLA | 2025-01-29 | U124604 | U131378 | 2024-12-19 | 2024-12-27 | 2025-01-13 |  | MCOLLET | 2025-01-28 | 2025-01-08 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 38.9333 | 7 | 5915.82 | 2809.94 | 329.54 | 2705.3 | 71.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24301185100 |  | 500360161 |  | 6708212I | 2293210 |  |  | 563 | EX | 1" P SHORT/PRMT RCVD | 2600B | GLOUCESTER | 3641 GLOUCESTER DR | 067 | LEX | 2025-01-24 | U126284 | U134341 | 2024-12-19 | 2025-01-13 | 2025-01-24 |  | JOSH PASLEY | 2025-01-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 3351 | 507.62 | 0 | 413.45 | 2429.93 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24301185200 |  | 100321544 |  | 6720208A |  |  |  | 563 | EX | PAPER W/ 500078684 | 2600B | ASHLAND | 312< S ASHLAND AV | 067 | LEX | 2024-12-19 | U125201 | U128272 | 2024-12-19 | 2024-12-20 | 2025-01-07 |  | OFFICE | 2024-12-19 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26210011 |  | 1
KY | KY - WEST | 2621 | 24301190600 |  | 100329062 |  | 6720208O |  |  |  | 565 | EX | GR1 LK RP ON S/L | 2621P | COMPTON | 565 COMPTON DR | 067 | LEX | 2024-12-23 | U141668 | U131366 | 2024-12-19 | 2024-12-19 | 2024-12-19 |  | LSTANFI | 2024-12-20 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.7167 | 7 | 880.8 | 543.37 | 219.74 | 51.09 | 66.6 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24301235300 |  | 501371241 |  | 7352256O | 2408720 |  |  | 563 | EX | 99 1" P LONG | 2621P | WOODHAVEN | 2816 WOODHAVEN DR | 019 | ASH | 2025-01-31 | ABHATFIE | U134341 | 2024-12-20 | 2025-01-08 | 2025-01-08 |  | ABHATFIE | 2025-01-31 | 2025-01-28 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 32.8 | 5 | 2693.6 | 2325.74 | 0 | 154.74 | 213.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24301255200 |  | 500619105 |  | 6744204E | 9828814 |  |  | 563 | EX | 1" P LONG | 2600B | WOODDUCK | 209 WOODDUCK CT | 049 | WIN | 2025-01-16 | U461516 | U128727 | 2024-12-20 | 2025-01-03 | 2025-01-16 |  | NEAL JOHNSON | 2025-01-16 |  | 2025-01-16 | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 8 | 1 | 5626.88 | 520.36 | 419.86 | 414.3 | 4272.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24301263300 |  | 100288131 |  | 6720212G |  |  |  | 565 | EX | SERVICE LINE REPLACE | 2621P | SHAFTSBURY | 508 SHAFTSBURY DR | 067 | LEX | 2024-12-20 | LSTANFI | U137585 | 2024-12-20 | 2024-12-20 |  |  | LSTANFI | 2024-12-20 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 5.7 | 2 | 2380.39 | 441.56 | 32.56 | 145.35 | 1760.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24301263800 |  | 500258888 |  | 16712208I |  |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | PEPPERTREE | 4037 PEPPERTREE DR LT10D | 067 | LEX | 2025-01-14 | U126308 | U130192 | 2024-12-20 | 2025-01-06 | 2025-01-17 |  | JAMIE ENSMINGER | 2025-01-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 3297.25 | 509.39 | 336.18 | 33.51 | 2418.17 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24301285700 |  | 100268036 |  | 7356256B | 2411044 |  |  | 565 | EX | NBT UPGRADE INSTALL 2"PMLP S/L | 2621P | 19TH | 219 19TH ST | 019 | ASH | 2025-01-29 | ABHATFIE | U123688 | 2024-12-20 | 2025-01-31 | 2025-01-31 |  | ABHATFIE | 2025-01-29 | 2025-01-29 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 30 | 3 | 11088.01 | 2186.86 | 8742.48 | 143.87 | 14.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24301289300 |  | 501348641 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | CALISTA FLAT | 801 CALISTA FLAT | 067 | LEX | 2025-01-14 | U126285 | U126856 | 2024-12-20 | 2025-01-06 | 2025-01-17 |  | DUSTIN DAVIS | 2025-01-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 1848.76 | 521.46 | 0 | 34.32 | 1292.98 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24301307700 |  | 501172641 |  | 7356216L | 1528382 |  |  | 563 | EX | 1" P LONG | 2621P | RIVER OAKS | 129 RIVER OAKS LN LT8 | 127 | LOU | 2025-01-08 | U124604 | U134341 | 2024-12-20 | 2025-01-08 | 2025-01-08 |  | LAMAY | 2025-01-07 | 2025-01-03 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 26.35 | 5 | 2669.39 | 1792.67 | 329.92 | 407.68 | 139.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24301319500 |  | 100299217 |  | 6716216N |  |  |  | 563 | EX | 20 1" P SHORT/2ND ATTEMPT | 2600B | LARCH | 264 LARCH LN | 067 | LEX | 2025-01-23 | U128816 | U142144 | 2024-12-20 | 2025-01-10 | 2025-01-23 |  | OLIVER MAYNARD | 2025-01-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 1695.39 | 488.78 | 0 | 32.16 | 1174.45 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24301320500 |  | 100409982 |  | 6720216L |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | STRAWBERRY FIE | 153 STRAWBERRY FIE RD | 067 | LEX | 2024-12-23 | U137585 | U131366 | 2024-12-20 | 2024-12-20 | 2025-01-09 |  | MCRAIG | 2024-12-20 | 2024-12-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 17.5667 | 4 | 3386.23 | 3063.72 | 0 | 178.95 | 143.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24301321100 |  | 100333003 |  | 6728200C | 2410979 |  |  | 563 | EX | 99 1" P LONG HP MAIN | 2600B | ATHENS WALNUT | 5867 ATHENS WALNUT PK | 067 | LEX | 2025-02-11 | U461516 | U120250 | 2024-12-20 | 2025-01-16 | 2025-01-29 |  | NEAL JOHNSON | 2025-01-30 | 2025-01-29 | 2025-01-29 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 13.4 | 3 | 6229.72 | 881.58 | 1344.52 | 473.64 | 3529.98 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24301391100 |  | 100334640 |  | 6720208D |  |  |  | 563 | EX | 1" P SHORT/PRIVATE RD | 2600B | WILDERNESS | 649 WILDERNESS RD | 067 | LEX | 2025-01-14 | U461516 | U131378 | 2024-12-23 | 2025-01-10 | 2025-01-23 |  | NEAL JOHNSON | 2025-01-14 |  | 2025-01-14 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 3777.47 | 487.03 | 608.31 | 412.11 | 2270.02 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24301447600 |  | 501374060 |  | 7348268N |  |  |  | 563 | EX | 1" P SHORT | 2621P | STEWART | 100 STEWART AV | 089 | WOR | 2025-01-07 | U123688 | U129294 | 2024-12-23 | 2025-01-08 | 2025-01-08 |  | RECUMP | 2025-01-03 | 2025-01-02 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 14.7833 | 3 | 1588.2 | 989.5 | 356.27 | 203.95 | 38.48 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24301458500 |  | 100349626 |  | 6748204A | 2411074 |  |  | 563 | EX | 1.25" P SHORT | 2600B | KENTUCKY | 118 KENTUCKY ST | 049 | WIN | 2025-01-16 | U123111 | U138822 | 2024-12-23 | 2025-01-03 | 2025-01-16 |  | LYN STAFFORD | 2025-01-16 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 4 | 1 | 2984.2 | 261.48 | 179.16 | 17.21 | 2526.35 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24303088000 |  | 501374066 |  | 6684228N |  |  |  | 563 | EX | MANIFOLD W/ 501374065 | 2600B | BERRY HILL | 2027 BERRY HILL DR | 073 | FRA | 2025-01-03 | U126532 | U128727 | 2024-12-26 | 2024-12-30 | 2025-01-03 |  | LESLIE SHARON | 2025-01-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBMAN |  | 100 | 056332B26230012 |  | 1
KY | KY - CENTRAL | 2632 | 24303108200 |  | 100354087 |  | 7256280P |  |  |  | 563 | EX | 1" P LONG | 2621P | LIMESTONE | 325 LIMESTONE ST | 161 | MAY | 2025-02-20 | U124604 | U129531 | 2024-12-26 | 2024-12-26 | 2025-01-17 |  | SDADAMS | 2025-02-19 | 2025-02-17 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26320011 | 26.3 | 5 | 2207.66 | 1939.55 | 177.28 | 90.83 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24303182600 |  | 100285158 |  | 6756176O |  |  |  | 565 | EX | 2+ LK ON SERVICE LINE | 2621P | WINSTON | 270 WINSTON RD | 065 | IRV | 2025-01-14 | U124604 | U139715 | 2024-12-27 | 2024-12-27 | 2025-01-16 |  | DENNING | 2025-01-13 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 17.15 | 3 | 6085.23 | 1530.42 | 3202.85 | 835.89 | 516.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24303186000 |  | 100291423 |  | 6720216H |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | KINGSTON | 604 KINGSTON RD | 067 | LEX | 2025-02-12 | U124604 | U141668 | 2024-12-27 | 2025-06-27 | 2025-06-27 |  | TROE | 2025-02-11 | 2025-01-31 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 33.8833 | 8 | 11850.19 | 2238.3 | 9504.44 | 107.45 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24303213300 |  | 501097953 |  | 6728208E | 1102270 |  |  | 563 | EX | 1" P SHORT/PRMT RCVD | 2600B | HARDWOOD | 3745 HARDWOOD RD | 067 | LEX | 2025-01-16 | U461309 | U126919 | 2024-12-27 | 2025-01-13 | 2025-01-24 |  | RANDALL HUMPHREYS | 2025-01-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 3076.56 | 484.89 | 248.4 | 411.98 | 1931.29 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24303316500 |  | 100340044 |  | 6724212E |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | AUGUSTA | 1839 AUGUSTA DR 7 | 067 | LEX | 2024-12-30 | HSTANFI | U129939 | 2024-12-30 | 2024-12-30 |  |  | HSTANFI | 2024-12-30 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.23333 | 2 | 18.33 | 17.33 | 0 | 1 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24303316600 |  | 100340042 |  | 6724212E |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | AUGUSTA | 1839 AUGUSTA DR 5 | 067 | LEX | 2024-12-30 | HSTANFI | U129939 | 2024-12-30 | 2024-12-30 |  |  | HSTANFI | 2024-12-30 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.1 | 2 | 7.59 | 7.19 | 0 | 0.4 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24303316700 |  | 100340043 |  | 6724212E |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | AUGUSTA | 1839 AUGUSTA DR 3 | 067 | LEX | 2024-12-30 | HSTANFI | U129939 | 2024-12-30 | 2024-12-30 |  |  | HSTANFI | 2024-12-30 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.13333 | 2 | 10.76 | 10.14 | 0 | 0.62 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24303316900 |  | 100340038 |  | 6724212E |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | AUGUSTA | 1839 AUGUSTA DR LDRY | 067 | LEX | 2024-12-30 | HSTANFI | U129939 | 2024-12-30 | 2024-12-30 |  |  | HSTANFI | 2024-12-30 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.13333 | 2 | 10.76 | 10.14 | 0 | 0.62 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24303318100 |  | 501374739 |  | 6708228H | 2411213 |  |  | 563 | EX | 1" P LONG/PRMT RCVD | 2600B | WOODLAWN | 107 WOODLAWN AV | 209 | GEO | 2025-01-28 | U461516 | U134341 | 2024-12-30 | 2025-01-13 | 2025-01-24 |  | NEAL JOHNSON | 2025-01-28 |  | 2025-01-28 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4.3167 | 1 | 5823.02 | 276.4 | 261.82 | 222.47 | 5062.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24303324000 |  | 501347012 |  | 6708204K | 2397152 |  |  | 563 | EX | 1" P SHORT PADGETT CONSTRUCTN | 2600B | HOMESTRETCH | 116 HOMESTRETCH CR LT26 | 113 | NIC | 2025-01-14 | U123111 | U128266 | 2024-12-30 | 2025-01-06 | 2025-01-17 |  | LYN STAFFORD | 2025-01-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2681.27 | 489.46 | 300.81 | 32.2 | 1858.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24303325200 |  | 100335810 |  | 6720212L |  |  |  | 563 | EX | 1.25" P SHORT/PRMT RCVD | 2600B | COMMERCIAL | 1127 COMMERCIAL DR | 067 | LEX | 2025-01-25 | U126602 | U129294 | 2024-12-30 | 2025-01-13 | 2025-01-24 |  | DEREK PAYTON | 2025-01-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 5967.45 | 502.65 | 961.8 | 33.06 | 4469.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24303338600 |  | 100303132 |  | 6712208C |  |  |  | 563 | EX | PAPER W/ 100303131 | 2600B | ALEXANDRIA | 2233 ALEXANDRIA DR | 067 | LEX | 2024-12-31 | U125201 | U129531 | 2024-12-30 | 2024-12-31 | 2025-01-14 |  | OFFICE | 2024-12-31 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26210011 |  | 1 | 155.4 | 0 | 0 | 0 | 155.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24303358700 |  | 501057339 |  | 67242080 | 0888645 |  |  | 563 | EX | 99 1" PL LONG/PRMT RCVD | 2600B | CORINTHIAN | 1013 CORINTHIAN CT LT3 | 067 | LEX | 2025-01-23 | U128336 | U125753 | 2024-12-30 | 2025-01-13 | 2025-01-24 |  | JOSHUA COX | 2025-01-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 3188.4 | 0 | 296.7 | 0 | 2891.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24303468200 |  | 500182380 | 36 | 6768172A |  |  |  | 566 | EX | ABANDON-SL/CONVRT/CUSTREQ | 2621P | ELM | 812 ELM ST | 065 | RAV | 2025-01-21 | DENNING | TJROSEN | 2024-12-31 | 2025-01-16 | 2025-02-02 |  | DENNING | 2025-01-21 | 2025-01-10 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 6.6833 | 4 | 758.6 | 495.86 | 58.46 | 204.28 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24303519700 |  | 100463546 |  | 6720204O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | WOODFIELD | 2416 WOODFIELD CR | 067 | LEX | 2025-01-02 | U124604 | U139715 | 2024-12-31 | 2025-06-28 | 2026-12-31 |  | HSTANFI | 2024-12-31 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.8167 | 4 | 2824.42 | 1036.73 | 14.76 | 64.77 | 1708.16 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25026377300 |  |  |  | 7352256D | 2511329 | U122858 |  | 557 | VO | EMER - INSTALL 1'-2" PMLP | 2621P | BECKETT | 404 BECKETT ST | 019 | ASH | 2025-02-14 |  | U122858 | 2025-01-03 | 2025-01-30 | 2025-01-31 | 2024-12-30 | R CUMPSTON | 2024-12-30 | 2025-01-09 |  | A | 00032 | 88000000 | 0326310 | 0326310 | 00032 | 05007 | [6 empty] | 100 |  | 21.9833 | 0 | -823.67 | 0 | 0.64 | 0 | 0 | 0 | 0 | -824.31
KY | KY - EAST | 2631 | 25026377400 |  |  |  | 7352256D | 2511329 | U122858 |  | 558 | VO | EMER - RETIRE 1'-2" PLP | 2621P | BECKETT | 404 BECKETT ST | 019 | ASH | 2025-02-14 |  | U122858 | 2025-01-03 | 2025-01-30 | 2025-01-31 | 2024-12-30 | R CUMPSTON | 2024-12-20 | 2025-01-08 |  | A | 00032 | 88000000 | 0326310 | 0326310 | 00032 | 05007 | [6 empty] | 100 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25026377600 |  |  |  | 6696212K | 2511446 | U461383 |  | 559 | EX | EMER-INSTALL 4' OF 2"PMMP MAIN | 2621P | POCAHONTAS | 621 POCAHONTAS TL | 239 | VER | 2025-02-28 | U136251 | U461383 | 2025-01-08 | 2025-05-29 | 2025-06-01 | 2025-01-02 | CDESPAIN | 2025-01-02 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00559 | 3200559 |  |  | WP3776 |  |  | 100 | 055932250263776 |  | 4 | 8999.48 | 4760.11 | 168.32 | 1487.66 | 22.2 | 0 | 26.83 | 2534.36 | 4
KY | KY - WEST | 2623 | 25026377700 |  |  |  | 6696212K | 2511446 | U461383 |  | 560 | EX | EMER-RETIRE 4' OF 2"PMP MAIN | 2621P | POCAHONTAS | 621 POCAHONTAS TL | 239 | VER | 2025-02-28 | U136251 | U461383 | 2025-01-08 | 2025-05-30 | 2025-06-01 | 2025-01-02 | CDESPAIN | 2025-01-02 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00560 | 3200560 |  |  | WP3777 |  |  | 100 | 056032250263777 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25026377900 |  |  |  | 6748208I | 2293700 | U128885 |  | 559 | EX | INSTALL LP FITTING-PAPER ONLY | 2600B | MAIN | MAIN ST | 049 | WIN | 2025-02-06 | U128132 | U128885 | 2025-01-10 | 2025-01-31 | 2025-01-31 | 2024-12-12 | WILLIAM FULKS | 2024-12-17 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00559 | 3200559 |  |  | WP3779 | AMRCB |  | 100 | 055932250263779 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25026378600 |  |  |  | 6716208C | 2511541 | U461383 |  | 561 | EX | INSTALL 42' OF 2"/4" PMMP MAIN | 2600B | STATE | 201 STATE ST | 067 | LEX | 2025-03-07 | U132645 | U461383 | 2025-01-13 | 2025-02-26 | 2025-03-01 | 2025-02-24 | JOSH PASLEY | 2025-02-26 | 2025-02-12 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP3786 |  |  | 100 | 056132250263786 | 80.9167 | 451 | 26011.02 | 6695.98 | 710.33 | 4651.5 | 9627.47 | 0 | 112.68 | 4213.06 | 41
KY | KY - WEST | 2621 | 25026378700 |  |  |  | 6716208C | 2511541 | U461383 |  | 562 | EX | RETIRE 30' OF 2"/4"PMMP MAIN | 2600B | STATE | 201 STATE ST | 067 | LEX | 2025-03-07 | U132645 | U461383 | 2025-01-13 | 2025-02-28 | 2025-03-01 | 2025-02-24 | JOSH PASLEY | 2025-02-26 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP3787 |  |  | 100 | 056232250263787 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25026378800 |  |  |  | 6744208F | 2511563 | U128885 |  | 557 | EX | EMER - INSTALL 25'-2" PMMP | 2621P | WINCHESTER | 6 WINCHESTER PZ E | 049 | WIN | 2025-02-21 | U128132 | U128885 | 2025-01-14 | 2024-11-13 | 2025-01-07 | 2025-01-09 | TROE | 2025-01-24 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3788 |  |  | 100 | 055732250263788 |  | 25 | 81247.31 | 17392.42 | 2537.39 | 3118.61 | 35447.2 | 0 | 112.31 | 22639.38 | 25
KY | KY - CENTRAL | 2629 | 25026378900 |  |  |  | 6744208E | 2511563 | U128885 |  | 558 | EX | EMER - RETIRE 25'-3" PAMP | 2621P | WINCHESTER | 6 WINCHESTER PZ E | 049 | WIN | 2025-02-18 | U128132 | U128885 | 2025-01-14 | 2025-01-07 | 2025-01-07 | 2025-01-09 | TROE | 2025-01-24 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP3789 |  |  | 100 | 055832250263789 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25026379000 |  |  |  | 6740208H | 2511570 | U128885 |  | 557 | EX | EMER - INSTALL 9'-2" PMMP | 2621P | LAMOND RUELLE | 213 LAMOND RUELLE | 049 | WIN | 2025-02-21 | U128132 | U128885 | 2025-01-14 | 2025-01-02 | 2025-01-13 | 2025-01-14 | WDENNING | 2025-01-28 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3790 |  |  | 100 | 055732250263790 |  | 9 | 1184.26 | 0 | 784.4 | 0 | 75.48 | 0 | 2.86 | 321.52 | 9
KY | KY - CENTRAL | 2629 | 25026379101 |  |  |  | 6740208H | 2511570 | U128885 |  | 558 | EX | EMER - RETIRE 9'-2" PMP | 2621P | LAMOND RUELLE | 213 LAMOND RUELLE | 049 | WIN | 2025-02-12 | U128132 | U128885 | 2025-01-16 | 2025-01-02 | 2025-01-13 | 2025-01-14 | WDENNING | 2025-01-28 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP3791 |  |  | 100 | 055832250263791 |  | 0 | 9245.89 | 3876.76 | 0 | 1741.32 | 3627.81 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25026379500 |  |  |  | 7240212F | 2408542 | U128885 |  | 909 | CO | INSTALL SCADA VISIBILITY | 2626M | FOGG | FOGG PK | 173 | MT | 2025-06-12 |  | U128885 | 2025-01-14 | 2025-12-30 | 2025-12-31 | 2025-05-22 | DANNY ASH | 2025-06-12 | 2025-04-07 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00909 | 3200909 |  |  | WP3795 |  |  | 100 | 090932250263795 | 21.8 | 0 | 13338.87 | 3227.7 | 5624.1 | 1594.6 | 2826.04 | 0 | 66.43 | 0
KY | KY - CENTRAL | 2629 | 25026379700 |  |  |  | 6736228C | 2408542 | U128885 |  | 909 | CO | INSTALL SCADA VISIBILITY | 2600E | FORDS MILL | FORDS MILL RD | 017 | PAR | 2025-06-12 |  | U128885 | 2025-01-14 | 2025-12-30 | 2025-12-31 | 2025-06-05 | DANNY ASH | 2025-06-12 | 2025-03-05 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00909 | 3200909 |  |  | WP3797 |  |  | 100 | 090932250263797 | 30.8667 | 0 | 11378.96 | 3411.87 | 5553.82 | 2280.82 | 0 | 0 | 132.45 | 0
KY | KY - WEST | 2621 | 25026380600 |  |  |  | 6716216K | 2408542 | U134275 |  | 909 | CO | INSTALL SCADA VISIBILITY | 2621M | OAKWOOD | 1198 OAKWOOD DR | 067 | LEX | 2025-06-11 |  | U134275 | 2025-01-14 | 2025-12-30 | 2025-12-31 | 2025-05-28 | DSASH | 2025-06-11 | 2025-04-03 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP3806 |  |  | 100 | 090932250263806 | 32.3833 | 0 | 10718.92 | 3274.09 | 5553.82 | 1816.56 | 0 | 0 | 74.45 | 0
KY | KY - WEST | 2621 | 25026380700 |  |  |  | 6708212I | 2408542 | U134275 |  | 909 | CO | INSTALL SCADA VISIBILITY | 2621M | ROSALIE | 3781 ROSALIE DR | 067 | LEX | 2025-03-17 |  | U134275 | 2025-01-14 | 2025-12-30 | 2025-12-31 |  | BJLONE | 2025-03-17 |  |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP3807 |  |  | 100 | 090932250263807 | 12.8667 | 0 | 8310 | 1816.8 | 5553.82 | 826.02 | 0 | 0 | 113.36 | 0
KY | KY - WEST | 2621 | 25026380800 |  |  |  | 6712212M | 2408542 | U134275 |  | 909 | CO | INSTALL SCADA VISIBILITY | 2621M | KENSINGTON | 1621 KENSINGTON WY | 067 | LEX | 2025-06-16 |  | U134275 | 2025-01-14 | 2025-12-30 | 2025-12-31 | 2025-06-13 | DANY ASH | 2025-06-16 | 2025-03-17 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP3808 |  |  | 100 | 090932250263808 | 19.1333 | 0 | 9824.48 | 2285.79 | 5553.82 | 1880.01 | 0 | 0 | 104.86 | 0
KY | KY - WEST | 2623 | 25026380900 |  |  |  | 6688228P | 2408542 | U134275 |  | 909 | CO | INSTALL SCADA VISIBILITY | 2623M | US 421 | US 421 | 073 | FRA | 2025-03-31 |  | U134275 | 2025-01-14 | 2025-12-30 | 2025-12-31 |  | WSHIMFE | 2025-03-31 |  |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00909 | 3200909 |  |  | WP3809 |  |  | 100 | 090932250263809 | 2.7833 | 0 | 6732.49 | 965.36 | 5553.82 | 124.32 | 0 | 0 | 88.99 | 0
KY | KY - WEST | 2623 | 25026381100 |  |  |  | 6684228P | 2408542 | U134275 |  | 909 | CO | INSTALL SCADA VISIBILITY | 2623M | GLENNS CREEK | GLENNS CREEK PK | 073 | FRA | 2025-06-12 |  | U134275 | 2025-01-14 | 2025-12-30 | 2025-12-31 | 2025-06-10 | DANNY ASH | 2025-06-12 | 2025-04-01 |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00909 | 3200909 |  |  | WP3811 |  |  | 100 | 090932250263811 | 18.9667 | 0 | 8624.74 | 2080.6 | 5553.82 | 894.45 | 0 | 0 | 95.87 | 0
KY | KY - WEST | 2623 | 25026381300 |  |  |  | 6688228K | 2511609 | U126783 |  | 557 | CO | EMER-INSTALL 180' OF 4"PMLP MN | 2621P | RANDOLPH | 101 RANDOLPH RD | 073 | FRA | 2025-02-07 |  | U126783 | 2025-01-15 | 2025-01-28 | 2026-11-15 |  | KKINDER | 2025-02-07 | 2025-01-28 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP3813 | AMRCB |  | 100 | 055732250263813 | 0.93333 | 0 | 2921.66 | 68.93 | 1732.48 | 4.19 | 312.28 | 0 | 84.11 | 719.67
KY | KY - WEST | 2623 | 25026381400 |  |  |  | 6688228K | 2511609 | U126783 |  | 558 | CO | EMER-RETIRE 180' OF 6"BSLP MN | 2621P | RANDOLPH | 101 RANDOLPH RD | 073 | FRA | 2025-02-07 |  | U126783 | 2025-01-15 | 2025-01-28 | 2026-11-15 |  | KKINDER | 2025-02-07 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP3814 | AMRCB |  | 100 | 055832250263814 | 0.38333 | 0 | 34.56 | 33 | 0 | 1.56 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25026381500 |  |  |  | 7356256M | 2511614 | U122858 |  | 558 | CO | EMER - RETIRE ~870'-3" PIP | 2621P | WILDWOOD | WILDWOOD DR | 019 | ASH | 2025-03-14 |  | U122858 | 2025-01-15 | 2025-01-27 | 2049-12-31 | 2025-01-14 | ABHATFIE | 2025-03-14 | 2025-03-06 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP3815 |  |  | 100 | 055832250263815 | 23.9 | 0 | 8256.1 | 3950.75 | 196.51 | 373.17 | 3735.67 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25026381700 |  | 501375187 |  | 7348260H | 2511591 | U141016 |  | 555 | EX | INSTALL 230' OF 2" PMIP | 2600E | SUNSET | 524 SUNSET DR | 089 | ASH | 2025-04-04 | U128132 | U141016 | 2025-01-18 | 2025-02-04 | 2025-04-14 | 2025-03-24 | ORA SLONE | 2025-03-24 | 2025-03-17 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP3817 |  |  | 100 | 055532250263817 | 53.7167 | 2784 | 89700.18 | 3765.58 | 1743.92 | 844.36 | 59027.37 | 0 | 156.74 | 24162.21 | 348
KY | KY - CENTRAL | 2629 | 25026381800 |  | 501375602 |  | 6736228C | 2511455 | U128885 |  | 555 | EX | INSTALL 250'-2" PMMP | 2600B | DOGWOOD | 1200 DOGWOOD DR | 017 | PAR | 2025-04-04 | U128132 | U128885 | 2025-01-20 | 2025-04-09 | 2025-04-11 | 2025-03-25 | STEVE CANOY | 2025-03-28 | 2025-03-18 | 2025-03-20 | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP3818 |  |  | 100 | 055532250263818 | 49.6667 | 1864 | 52355.75 | 3626.25 | 1842.97 | 3098.94 | 27345.79 | 0 | 148.61 | 16293.19 | 233
KY | KY - EAST | 2631 | 25026382400 |  |  |  | 7360232B | 2408542 | U141016 |  | 909 | CO | INSTALL SCADA EQUIPMENT | 2631M | US 23 | 7124 US 23 | 019 | CAT | 2025-06-12 |  | U141016 | 2025-01-21 | 2025-12-30 | 2025-12-31 | 2025-05-29 | DANNY ASH | 2025-06-12 | 2025-04-23 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP3824 |  |  | 100 | 090932250263824 | 39.4833 | 0 | 11519.85 | 3497.25 | 5840.92 | 2103.58 | 0 | 0 | 78.1 | 0
KY | KY - WEST | 2621 | 25026385100 |  |  |  | 6720204M | 2511942 | U461383 |  | 557 | CO | EMER-INSTALL 4' OF 4"PMMP MAIN | 2621P | HARTLAND | 4541 HARTLAND PR | 067 | LEX | 2025-05-09 |  | U461383 | 2025-01-30 | 2025-06-30 | 2025-07-01 |  | HMCKUNE | 2025-05-09 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3851 |  |  | 100 | 055732250263851 | 1.3667 | 0 | 10551.81 | 6006.97 | 428.33 | 803.52 | 0 | 0 | 333.19 | 2979.8
KY | KY - WEST | 2621 | 25026385200 |  |  |  | 6720204M | 2511942 | U461383 |  | 558 | CO | EMER-RETIRE 4' OF 4"PMP MAIN | 2621P | HARTLAND | 4541 HARTLAND PR | 067 | LEX | 2025-05-09 |  | U461383 | 2025-01-30 | 2025-01-29 | 2025-07-01 |  | HMCKUNE | 2025-05-09 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP3852 |  |  | 100 | 055832250263852 | 5.9667 | 0 | 1550.11 | 1259.07 | 0 | 291.04 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25026392000 |  | 501376468 |  | 6712232N | 2511993 | U126783 |  | 555 | EX | INSTALL 140'-2" PMMP | 2600E | WHITE PINE | 309 WHITE PINE LN | 209 | GEO | 2025-05-23 | U136251 | U126783 | 2025-02-07 | 2025-02-27 | 2025-05-28 | 2025-05-09 | EDWARD F GOINS | 2025-05-12 | 2025-05-05 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP3920 |  |  | 100 | 055532250263920 | 40 | 690 | 21515.47 | 2899.8 | 1652.44 | 167.95 | 12337.67 | 0 | 71.04 | 4386.57 | 138
KY | KY - EAST | 2631 | 25026392800 |  |  |  | 7356216D | 1855491 | U132703 |  | 560 | CO | RETIRE MP - PAPER ONLY | 2600B | PIKE | E PIKE ST | 127 | LOU | 2025-05-27 |  | U132703 | 2025-02-12 | 2026-12-31 | 2026-12-31 | 2025-04-16 | MBLANKE/CJH C PACK | 2025-05-27 |  | 2025-02-25 | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00560 | 3200560 |  |  | WP3928 | AMRCB |  | 100 | 056032250263928 | 2.85 | 0 | 251.75 | 200.04 | 0 | 51.71 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25026393800 |  | 501357014 |  | 7240216O | 2301540 | U128885 |  | 555 | EX | INSTALL 2,100'-2" PMMP | 2600E | HAWK | HAWK LN LT1 | 173 | MT | 2025-05-28 | U128132 | U128885 | 2025-02-18 | 2025-05-13 | 2025-05-30 | 2025-05-19 | ALEX WILLIAMSON | 2025-05-20 | 2025-05-05 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP3938 |  |  | 100 | 055532250263938 | 108.6833 | 28518 | 110997.26 | 9385.78 | 6615.74 | 2288.92 | 69739.38 | 0 | 341.85 | 22625.59 | 2037
KY | KY - EAST | 2633 | 25026394000 |  |  |  | 7352156L | 2512421 | U122858 |  | 557 | EX | EMER INSERT 280'-1.2" PMIP | 2621P | DOW HUNTER | DOW HUNTER | 071 | BET | 2025-03-31 | U128132 | U122858 | 2025-02-19 | 2025-10-28 | 2025-10-31 | 2025-02-19 | JAHOWARD | 2025-03-10 |  |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00557 | 3200557 |  |  | WP3940 | AMRCB |  | 100 | 055732250263940 | 0.5 | 284 | 2217.44 | 264.48 | 1263.6 | 15.15 | 0 | 0 | 0 | 674.21 | 284
KY | KY - EAST | 2633 | 25026394100 |  |  |  | 7352156L | 2512421 | U122858 |  | 558 | EX | EMER - RETIRE 284'-2"BSIP | 2621P | DOW HUNTER | DOW HUNTER | 071 | BET | 2025-03-14 | U128132 | U122858 | 2025-02-19 | 2025-10-31 | 2025-10-31 | 2025-02-19 | JAHOWARD | 2025-03-10 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00558 | 3200558 |  |  | WP3941 | AMRCB |  | 100 | 055832250263941 | 0.23333 | 0 | 19.19 | 18.11 | 0 | 1.08 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25026395600 |  |  |  | 6716212N | 2512799 | U461383 |  | 557 | EX | EMER-INSTALL 3' OF 3"PMMP MAIN | 2600B | GIBSON | 511 GIBSON AV | 067 | LEX | 2025-03-27 | U136251 | U461383 | 2025-02-28 | 2026-06-30 | 2027-02-18 | 2025-02-26 | JOSH PASLEY | 2025-03-13 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3956 |  |  | 100 | 055732250263956 |  | 3 | 330.23 | 0 | 172.22 | 0 | 78.44 | 0 | 0 | 79.57 | 3
KY | KY - WEST | 2621 | 25026395700 |  |  |  | 6716212N | 2512799 | U461383 |  | 558 | EX | EMER-RETIRE 3' OF 3"PMP MAIN | 2600B | GIBSON | 511 GIBSON AV | 067 | LEX | 2025-04-24 | U136251 | U461383 | 2025-02-28 | 2026-06-30 | 2027-02-18 | 2025-02-26 | JOSH PASLEY | 2025-03-13 | 2025-03-07 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP3957 |  |  | 100 | 055832250263957 | 6.5833 | 0 | 435.29 | 410.42 | 0 | 24.87 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 25026396000 |  |  |  | 7356152A | 2512421 | U461383 |  | 583 | EX | INSTALL CAT HEATER | 2633M | LOWER HAROLD 1418 | LOWER HAROLD 1418 | 071 | HAR | 2025-06-04 | U133035 | U461383 | 2025-03-03 | 2025-10-01 | 2025-10-01 | 2025-02-17 | JAMES PASLEY | 2025-02-17 |  |  | F | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00583 | 3200583 |  |  | WP3960 |  |  | 100 | 058332250263960 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 25026396100 |  |  |  | 7356152A | 2512421 | U461383 |  | 584 | EX | RETIRE CAT HEATER | 2633M | LOWER HAROLD 1418 | LOWER HAROLD 1418 | 071 | HAR | 2025-06-04 | U133035 | U461383 | 2025-03-03 | 2025-10-01 | 2025-10-01 | 2025-02-17 | JAMES PASLEY | 2025-02-17 |  |  | F | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00584 | 3200584 |  |  | WP3961 |  |  | 100 | 058432250263961 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25026397400 |  |  |  | 6712232K | 2512986 | U461383 |  | 557 | CO | EMER-INSTALL 3' OF 2"PMMP MAIN | 2621P | BEVELED GLASS | 108 BEVELED GLASS LN | 209 | GEO | 2025-05-20 |  | U461383 | 2025-03-07 | 2025-07-01 | 2025-07-01 |  | M. COLLINS | 2025-05-20 | 2025-05-15 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP3974 |  |  | 100 | 055732250263974 | 20.3167 | 0 | 7928.42 | 4332.7 | 168.32 | 1115.48 | 69.56 | 0 | 130.41 | 2111.95
KY | KY - WEST | 2623 | 25026397500 |  |  |  | 6712232K | 2512986 | U461383 |  | 558 | CO | EMER-RETIRE 3' OF 2"PMP MAIN | 2621P | BEVELED GLASS | 108 BEVELED GLASS LN | 209 | GEO | 2025-05-20 |  | U461383 | 2025-03-07 | 2025-03-03 | 2025-07-01 |  | M.COLLINS | 2025-05-20 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP3975 |  |  | 100 | 055832250263975 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 25026398400 |  |  |  | 7352156L | 2513045 | U122858 |  | 557 | EX | EMER - INSTALL FITTINGS | 2621P | BOOOMERANG | BOOOMERANG | 071 | BET | 2025-04-04 | U128132 | U122858 | 2025-03-11 | 2025-11-25 |  | 2025-03-05 | JHOWARD | 2025-03-24 |  |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00557 | 3200557 |  |  | WP3984 | AMRCB |  | 100 | 055732250263984 |  | 0 | 6860.25 | 4256.46 | 0 | 334.21 | 128.76 | 0 | 20.36 | 2120.46
KY | KY - EAST | 2633 | 25026398500 |  |  |  | 7352156L | 2513045 | U122858 |  | 558 | EX | EMER - RETIRE 50'-4" CSIP | 2621P | BOOOMERANG | BOOOMERANG | 071 | BET | 2025-04-04 | U128132 | U122858 | 2025-03-11 | 2025-11-26 |  | 2025-03-05 | JHOWARD | 2025-03-24 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00558 | 3200558 |  |  | WP3985 | AMRCB |  | 100 | 055832250263985 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25026398800 |  | 501378936 |  | 6728208J | 2513070 | U461383 |  | 555 | EX | INSTALL 3670' OF 2"/4"PMMP MN | 2600B | BUTTERMILK | BUTTERMILK RD LT1 | 067 | LEX | 2025-05-13 | U132645 | U461383 | 2025-03-12 | 2025-05-02 | 2025-05-30 | 2025-04-15 | OLIVER MAYNARD | 2025-05-05 | 2025-03-21 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3988 |  |  | 100 | 055532250263988 | 217.9667 | 99428 | 130345.4 | 14026.44 | 19385.68 | 841.97 | 66049.4 | 0 | 556.94 | 29484.97 | 3551
KY | KY - WEST | 2621 | 25026399300 |  |  |  |  | 2513258 | U132703 |  | 557 | CO | EMER - INSTALL 5'-2" PMMP | 2600B | 6870 ATHENS BOONESBORO | 6870 ATHENS BOONESBORO | 067 | LEX | 2025-06-06 |  | U132703 | 2025-03-19 | 2025-11-26 |  |  | BDARNELL | 2025-06-06 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3993 | AMRCB |  | 100 | 055732250263993 | 1.4333 | 0 | 2298.33 | 1275.32 | 33.81 | 242.08 | 0 | 0 | 45.97 | 701.15
KY | KY - WEST | 2621 | 25026399900 |  |  |  | 6712212L | 2405929 | U122858 |  | 575 | EX | OBTAIN EASEMENTS | 2621M | MASON HEADLEY | MASON HEADLEY RD | 067 | LEX | 2025-05-21 | U136251 | U122858 | 2025-03-20 | 2025-04-29 | 2025-04-30 | 2025-04-16 | LAND | 2025-04-16 |  |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00575 | 3200575 |  |  | WP3999 |  |  | 100 | 057532250263999 |  | 1 | 7818.06 | 0 | 0 | 7794.7 | 0 | 0 | 23.36 | 0
KY | KY - CENTRAL | 2629 | 25026400200 |  |  |  | 6732248G | 2512967 | U128885 |  | 559 | EX | INSTALL 550'-2" PMMP | 2600B | US HIGHWAY 27 S | 1282 US HIGHWAY 27 S | 097 | CYN | 2025-05-23 | U136251 | U128885 | 2025-03-24 | 2025-04-28 | 2025-05-01 | 2025-04-23 | EDWARD F GOINS | 2025-04-25 | 2025-04-21 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00559 | 3200559 |  |  | WP4002 |  |  | 100 | 055932250264002 | 43.5 | 2615 | 47508 | 2933.96 | 1210.74 | 179.01 | 32671.05 | 0 | 77.64 | 10435.6 | 523
KY | KY - CENTRAL | 2629 | 25026400700 |  |  |  | 6748208K | 2513431 | U128885 |  | 562 | EX | RETIRE 100'-4" PMMP | 2600E | ECTON | 740 ECTON RD | 049 | WIN | 2025-06-10 | U128132 | U128885 | 2025-03-25 | 2025-05-14 | 2025-05-15 | 2025-05-06 | WDENNINGHOFF | 2025-05-06 | 2025-05-06 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00562 | 3200562 |  |  | WP4007 |  |  | 100 | 056232250264007 | 20.6333 | 0 | 2247.29 | 1624.46 | 0 | 94.08 | 528.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25026400900 |  |  |  | 6716204H | 2513468 | U122858 |  | 557 | EX | EMER - INSTALL 2'-4" PMMP | 2621P | RIDGEPOINT | RIDGEPOINT | 067 | LEX | 2025-04-14 | U132645 | U122858 | 2025-03-26 | 2025-11-25 | 2025-11-30 | 2025-03-23 | T ROE | 2025-03-24 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP4009 |  |  | 100 | 055732250264009 |  | 2 | 6330.01 | 3926.41 | 160.22 | 230.12 | 0 | 0 | 18.92 | 1994.34 | 2
KY | KY - WEST | 2621 | 25026401000 |  |  |  | 6716204H | 2513468 | U122858 |  | 558 | EX | EMER - RETIRE 2'-4" PMP | 2621P | RIDGEPOINT | RIDGEPOINT | 067 | LEX | 2025-04-04 | U132645 | U122858 | 2025-03-26 | 2025-11-26 | 2025-11-30 | 2025-03-23 | T ROE | 2025-03-24 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP4010 |  |  | 100 | 055832250264010 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25026403000 |  |  |  | 6748180P | 2513719 | U128885 |  | 557 | CO | EMER - INSTALL 2'-3" PMMP | 2621P | WACO LOOP | 191 WACO LOOP | 151 | WAC | 2025-05-23 |  | U128885 | 2025-04-07 | 2025-03-26 | 2025-04-09 | 2025-03-27 | U125572 | 2025-03-27 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP4030 |  |  | 100 | 055732250264030 |  | 0 | 230.88 | 0 | 0 | 0 | 230.88 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25026403100 |  |  |  | 6748180P | 2513719 | U128885 |  | 558 | CO | EMER - RETIRE 2'-3" PAMP | 2621P | WACO LOOP | 191 WACO LOOP | 151 | WAC | 2025-05-20 |  | U128885 | 2025-04-07 | 2025-04-07 | 2025-04-09 | 2025-03-27 | U125572 | 2025-03-27 | 2025-04-25 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP4031 |  |  | 100 | 055832250264031 | 0.66667 | 0 | 15086.34 | 5609 | 0 | 3143.97 | 5967.09 | 0 | 0 | 366.28
KY | KY - WEST | 2623 | 25026403300 |  |  |  | 6684228C | 2513772 | U141016 |  | 583 | EX | INSTALL MONITOR REGULATOR | 2623M | COMPTON | COMPTON DR | 073 | FRA | 2025-06-04 | U133035 | U141016 | 2025-04-09 | 2025-05-29 | 2025-06-01 | 2025-04-10 | WADE SHIMFESSEL | 2025-04-10 | 2025-04-10 |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00583 | 3200583 |  |  | WP4033 |  |  | 100 | 058332250264033 | 2.3667 | 0 | 1909.6 | 1155.51 | 0 | 333.07 | 0 | 0 | 5.71 | 415.31
KY | KY - WEST | 2623 | 25026403400 |  |  |  | 6684228C | 2513772 | U141016 |  | 584 | EX | RETIRE MONITORING REG | 2623M | COMPTON | COMPTON DR | 073 | FRA | 2025-06-04 | U133035 | U141016 | 2025-04-09 | 2025-05-30 | 2025-06-01 | 2025-04-10 | WADE SHIMFESSEL | 2025-04-10 |  |  | F | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00584 | 3200584 |  |  | WP4034 |  |  | 100 | 058432250264034 |  | 0 | 1316.2 | 993.04 | 0 | 323.16 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25026405400 |  |  |  | 6720216M | 2514040 | U122858 |  | 557 | EX | EMER - INSTALL 2'-2" PMMP | 2621P | NEW CIRCLE | 547 W NEW CIRCLE RD | 067 | LEX | 2025-06-04 | U136251 | U122858 | 2025-04-21 | 2025-06-30 | 2025-07-01 | 2025-04-17 | KKINDER | 2025-05-30 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP4054 |  |  | 100 | 055732250264054 | 0.033333 | 2 | 3579.32 | 2374.73 | 23.97 | 272 | 153.92 | 0 | 10.14 | 744.56 | 2
KY | KY - WEST | 2621 | 25026405500 |  |  |  | 6720216M | 2514040 | U122858 |  | 558 | EX | EMER - RETIRE 2'-2" PMP | 2621P | NEW CIRCLE | 547 W NEW CIRCLE RD | 067 | LEX | 2025-06-16 | U136251 | U122858 | 2025-04-21 | 2025-07-01 | 2025-07-01 | 2025-04-17 | KKINDER | 2025-05-30 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP4055 |  |  | 100 | 055832250264055 | 1.4833 | 0 | 108.37 | 102.43 | 0 | 5.94 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25026406000 |  |  |  | 6744208P | 2514108 | U128885 |  | 557 | CO | EMER - INSTALL 2'-2" PMLP | 2621P | MAIN | 17 S MAIN ST | 049 | WIN | 2025-05-23 |  | U128885 | 2025-04-23 | 2025-04-11 | 2025-04-18 |  | U125572 | 2025-04-18 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP4060 |  |  | 100 | 055732250264060 |  | 0 | 4119.02 | 2419.63 | 566.27 | 147.64 | 54.76 | 0 | 59.66 | 871.06
KY | KY - CENTRAL | 2629 | 25026406100 |  |  |  | 6744208P | 2514108 | U128885 |  | 558 | CO | EMER - RETIRE 2'-2" PMLP | 2621P | MAIN | 17 S MAIN ST | 049 | WIN | 2025-05-20 |  | U128885 | 2025-04-23 | 2025-04-17 | 2025-04-18 |  | U125572 | 2025-04-18 | 2025-04-25 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP4061 |  |  | 100 | 055832250264061 | 0.4 | 0 | 30.82 | 29.07 | 0 | 1.75 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25026406300 |  |  |  | 6720212N | 2514136 | U126783 |  | 557 | CO | INSTALL 15'-6" PMLP | 2621P | AURORA | 908 AURORA AV | 067 | LEX | 2025-06-06 |  | U126783 | 2025-04-24 | 2025-05-01 | 2025-07-31 |  | TROE | 2025-06-06 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP4063 | AMRCB |  | 100 | 055732250264063 | 0.1 | 0 | 10590.58 | 5611.78 | 0 | 582.16 | 2127.64 | 0 | 108.24 | 2160.76
KY | KY - WEST | 2621 | 25026406400 |  |  |  | 6720212N | 2514136 | U126783 |  | 558 | CO | RETIRE ~15'-6" BSLP | 2621P | AURORA | 908 AURORA AV | 067 | LEX | 2025-06-06 |  | U126783 | 2025-04-24 | 2025-05-02 | 2025-07-31 |  | TROE | 2025-06-06 | 2025-05-09 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP4064 | AMRCB |  | 100 | 055832250264064 | 5.1 | 0 | 436.95 | 412.96 | 0 | 23.99 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25026407800 |  |  |  | 6716208J | 2514497 | U122858 |  | 557 | CO | EMER - INSTALL 5'-2" PMMP | 2621P | NORMAN | 2350 NORMAN LN | 067 | LEX | 2025-06-10 |  | U122858 | 2025-05-14 | 2025-05-13 | 2025-05-13 |  | RSTRONG | 2025-06-10 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP4078 |  |  | 100 | 055732250264078 | 1.2833 | 0 | 1605.37 | 1062.64 | 23.97 | 120.58 | 65.12 | 0 | 12.71 | 320.35
KY | KY - WEST | 2621 | 25026407900 |  |  |  | 6716208J | 2514497 | U122858 |  | 558 | CO | EMER - RETIRE 5'-2" PMP | 2621P | NORMAN | 2350 NORMAN LN | 067 | LEX | 2025-06-10 |  | U122858 | 2025-05-14 | 2025-05-13 | 2025-05-13 |  | RSTRONG | 2025-06-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP4079 |  |  | 100 | 055832250264079 | 0.76667 | 0 | 75.49 | 50.69 | 0 | 24.8 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25026408300 |  | 500543786 |  | 6716204I | 2514584 | U122858 |  | 566 | CO | RETIRE CRITICAL VALVE | 2621P | MARKETPLACE | 101 MARKETPLACE DR | 067 | LEX | 2025-05-27 |  | U122858 | 2025-05-20 | 2025-06-30 | 2025-06-30 |  | KOBRYAN | 2025-05-27 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP4083 |  |  | 100 | 056632250264083 | 0.68333 | 1 | 46.56 | 44.02 | 0 | 2.54 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25026408400 |  | 500543786 |  | 6716204E | 2514584 | U122858 |  | 565 | CO | INSTALL CRITICAL VALVE | 2621P | MARKETPLACE | 101 MARKETPLACE DR | 067 | LEX | 2025-05-27 |  | U122858 | 2025-05-20 | 2025-06-27 | 2025-06-30 |  | KOBRYAN | 2025-05-27 | 2025-05-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP4084 |  |  | 100 | 056532250264084 | 9.8333 | 2 | 6907.14 | 2652.66 | 0 | 153.65 | 2134.36 | 0 | 362.35 | 1604.12
KY | KY - WEST | 2621 | 25026409300 |  |  |  | 6720208G | 2403558 | U461383 |  | 559 | EX | PAPER ONLY LP STOPPLE FITTINGS | 2600B | SAINT PHILLIPS | SAINT PHILLIPS | 067 | LEX | 2025-06-10 | U132645 | U461383 | 2025-05-23 | 2025-05-30 | 2025-06-15 | 2024-12-12 | RTINCHER | 2024-12-12 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP4093 | AMRCB |  | 100 | 055932250264093 |  | 0 | 6269.9 | 0 | 4975.29 | 0 | 0 | 0 | 0 | 1294.61
KY | KY - CENTRAL | 2629 | 25026409900 |  |  |  | 7240202G | 2514761 | U128885 |  | 557 | CO | EMER - INSTALL 10'-2" PMMP | 2621P | LEVEE | 6590 LEVEE RD | 173 | MT | 2025-06-17 |  | U128885 | 2025-05-29 | 2025-05-08 | 2025-05-19 |  | DENNING | 2025-05-19 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP4099 |  |  | 100 | 055732250264099 |  | 0 | 9748.17 | 5423.18 | 0 | 2226.64 | 48.84 | 0 | 87.45 | 1962.06
KY | KY - CENTRAL | 2629 | 25026410000 |  |  |  | 7240202G | 2514761 | U128885 |  | 558 | CO | EMER - RETIRE 10'-2" PMMP | 2621P | LEVEE | 6590 LEVEE RD | 173 | MT | 2025-06-17 |  | U128885 | 2025-05-29 | 2025-05-19 | 2025-05-19 |  | DENNING | 2025-05-19 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP4100 |  |  | 100 | 055832250264100 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25026410100 |  |  |  | 6684228B | 2514791 | U132703 |  | 557 | CO | EMER - INSTALL 200' - 2" | 2600E | KENTUCKY | 874 KENTUCKY AV | 073 | FRA | 2025-06-19 |  | U132703 | 2025-05-30 | 2026-08-27 | 2027-04-12 |  | D. COLLINS | 2025-06-19 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP4101 | AMRCB |  | 100 | 055732250264101 |  | 0 | 503.2 | 0 | 0 | 0 | 503.2 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25026410200 |  |  |  | 6684228B | 2514791 | U132703 |  | 558 | CO | EMER - RETIRE `200' - 2" | 2600E | KENTUCKY | 874 KENTUCKY AV | 073 | FRA | 2025-06-19 |  | U132703 | 2025-05-30 | 2026-08-31 | 2027-04-12 |  | D. COLLINS | 2025-06-19 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP4102 | AMRCB |  | 100 | 055832250264102 | 4.2333 | 0 | 448.33 | 310.98 | 0 | 137.35 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25026410400 |  |  |  | 6720216O | 2514859 | U122858 |  | 557 | CO | EMER - INSTALL 10'-2" PMMP | 2621P | WHISPERING WOOD | 115 WHISPERING WOOD | 067 | LEX | 2025-06-16 |  | U122858 | 2025-06-04 | 2026-02-27 | 2025-07-31 |  | KKINDER | 2025-06-16 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP4104 |  |  | 100 | 055732250264104 | 0.85 | 0 | 2436.76 | 1561.32 | 0 | 91.52 | 116.92 | 0 | 129.83 | 537.17
KY | KY - WEST | 2621 | 25026410500 |  |  |  | 6720216O | 2514859 | U122858 |  | 558 | CO | EMER - REITIE 10'-2" CSMP | 2621P | WHISPERING WOOD | 115 WHISPERING WOOD | 067 | LEX | 2025-06-16 |  | U122858 | 2025-06-04 | 2025-07-31 | 2025-07-31 |  | KKINDER | 2025-06-16 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP4105 |  |  | 100 | 055832250264105 | 0.083333 | 0 | 5.9 | 5.56 | 0 | 0.34 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25026410600 |  |  |  | 6720208D | 2403558 | U461383 |  | 557 | CO | EMER-INSTALL 3'-2"PMMP MAIN | 2600B | SAINT TERESA | 2021 SAINT TERESA | 067 | LEX | 2025-06-09 |  | U461383 | 2025-06-05 | 2026-06-30 | 2027-02-10 | 2025-02-10 | JAMIE ENSMINGER | 2025-02-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP4106 |  |  | 100 | 055732250264106 |  | 0 | 59.2 | 0 | 0 | 0 | 59.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25026410700 |  |  |  | 6720208D | 2403558 | U461383 |  | 558 | CO | EMER-RETIRE 3' OF 2"PMMP MAIN | 2600B | SAINT TERESA | 2021 SAINT TERESA | 067 | LEX | 2025-06-09 |  | U461383 | 2025-06-05 | 2026-06-30 | 2027-02-10 | 2025-02-10 | JAMIE ENSMINGER | 2025-02-10 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP4107 |  |  | 100 | 055832250264107 | 0.73333 | 0 | 59.14 | 55.87 | 0 | 3.27 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25026410800 |  |  |  | 7240216I | 2514918 | U128885 |  | 557 | CO | EMER - INSTALL 2'-2" PMMP | 2621P | INDIAN MOUND | 490 INDIAN MOUND DR | 173 | MT | 2025-06-17 |  | U128885 | 2025-06-06 | 2025-06-03 | 2025-06-04 |  | DENNING | 2025-06-04 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP4108 |  |  | 100 | 055732250264108 |  | 0 | 1873.09 | 789.55 | 0 | 460.11 | 118.4 | 0 | 98.89 | 406.14
KY | KY - CENTRAL | 2629 | 25026410900 |  |  |  | 7240216I | 2514918 | U128885 |  | 558 | CO | EMER - RETIRE 2'-2" PMMP | 2621P | INDIAN MOUND | 490 INDIAN MOUND DR | 173 | MT | 2025-06-17 |  | U128885 | 2025-06-06 | 2025-06-04 | 2025-06-04 |  | DENNING | 2025-06-04 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP4109 |  |  | 100 | 055832250264109 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25026411700 |  |  |  | 7356216D | 1855491 | U132703 |  | 559 | CO | INSTALL SHORTSTOP TEE | 2600B | PIKE | PIKE ST | 127 | LOU | 2025-06-19 |  | U132703 | 2025-06-17 | 2025-12-31 | 2025-12-31 | 2025-04-16 | MBLANKE/CJH CASEY PACK | 2025-05-27 |  | 2025-03-21 | C | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00559 | 3200559 |  |  | WP4117 | AMRCB |  | 100 | 055932250264117 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25303803400 |  | 100261539 |  | 7356256E |  |  |  | 566 | EX | ABANDON SL-IDLE/INACTIVE | 2621P | WILSHIRE | 2015 WILSHIRE BV | 019 | ASH | 2025-01-13 | CWHEELE | U137009 | 2025-01-02 | 2025-01-16 | 2025-02-02 |  | CWHEELE | 2025-01-13 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.3333 | 2 | 260.34 | 168.34 | 0 | 92 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25303809500 |  | 501355436 |  | 6712204J | 2398051 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | MERGANSER | 100 MERGANSER CT LT31 | 113 | NIC | 2025-01-16 | U128336 | U130192 | 2025-01-02 | 2025-01-06 | 2025-01-17 |  | JOSHUA COX | 2025-01-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 3139.89 | 170.76 | 296.7 | 8 | 2664.43 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25303812400 |  | 501096221 |  | 6724208C | 1421490 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | CARDUCCI | 2528 CARDUCCI ST | 067 | LEX | 2025-01-15 | U126532 | U129176 | 2025-01-02 | 2025-01-06 | 2025-01-17 |  | LESLIE SHARON | 2025-01-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 6.45 | 1 | 2900.26 | 399.34 | 277.92 | 26.26 | 2196.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25303841700 |  | 100296208 |  | 6716216O |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTRQD | 2621P | WAVERLY | 966 WAVERLY DR | 067 | LEX | 2025-02-17 | U130722 | U140273 | 2025-01-02 | 2025-01-23 | 2025-02-13 |  | HMCKUNE | 2025-02-14 | 2025-02-14 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 24 | 3 | 1581.15 | 1510.38 | 0 | 70.77 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25304095800 |  | 501347150 |  | 6748204C | 2293331 |  |  | 563 | EX | 20 1" P LONG JOHN WILSON PROP | 2600B | DUCLAIR | 240 DUCLAIR DR LT16 | 049 | WIN | 2025-01-16 | U129722 | U142144 | 2025-01-03 | 2025-01-07 | 2025-01-20 |  | DAVID YOUNG | 2025-01-16 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 8 | 1 | 2721.47 | 519.54 | 261.82 | 34.17 | 1905.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304121000 |  | 100322787 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | KASTLE | 1211 KASTLE RD | 067 | LEX | 2025-05-14 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-05-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 3046.96 | 544.64 | 0 | 31.54 | 2470.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304121100 |  | 100322788 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | KASTLE | 1215 KASTLE RD | 067 | LEX | 2025-05-14 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-05-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1592.08 | 0 | 0 | 0 | 1592.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304121200 |  | 100322812 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | KASTLE | 1216 KASTLE RD | 067 | LEX | 2025-06-10 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-06-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1393.74 | 0 | 0 | 0 | 1393.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304121300 |  | 100322789 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | KASTLE | 1219 KASTLE RD | 067 | LEX | 2025-06-10 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-06-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3008.91 | 0 | 0 | 0 | 3008.91 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304121500 |  | 100322790 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | KASTLE | 1223 KASTLE RD | 067 | LEX | 2025-06-10 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-06-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2767.88 | 0 | 0 | 0 | 2767.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304121600 |  | 100322791 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | KASTLE | 1227 KASTLE RD | 067 | LEX | 2025-05-23 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-05-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2169.82 | 0 | 0 | 0 | 2169.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304121700 |  | 100322810 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | KASTLE | 1230 KASTLE RD | 067 | LEX | 2025-06-05 | U129673 | U132386 | 2025-01-03 | 2025-12-19 |  |  | A WILLIAMSON | 2025-06-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2950.95 | 0 | 0 | 0 | 2950.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304121800 |  | 100322792 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | KASTLE | 1231 KASTLE RD | 067 | LEX | 2025-06-17 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-06-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1
KY | KY - WEST | 2621 | 25304121900 |  | 100322809 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | KASTLE | 1234 KASTLE RD | 067 | LEX | 2025-06-09 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-06-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2022.72 | 522.4 | 0 | 30.63 | 1469.69 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304122100 |  | 100322793 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | KASTLE | 1235 KASTLE RD | 067 | LEX | 2025-06-10 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-06-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.7333 | 1 | 3215.29 | 310.19 | 0 | 18.18 | 2886.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304122200 |  | 100322794 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | KASTLE | 1243 KASTLE RD | 067 | LEX | 2025-05-27 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-05-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3564.43 | 0 | 0 | 0 | 3564.43 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304122300 |  | 100322807 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | KASTLE | 1246 KASTLE RD | 067 | LEX | 2025-06-10 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-06-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3330.99 | 0 | 0 | 0 | 3330.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304122400 |  | 100322806 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | KASTLE | 1248 KASTLE RD | 067 | LEX | 2025-06-10 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-06-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1592.08 | 0 | 0 | 0 | 1592.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304122500 |  | 100322795 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | KASTLE | 1249 KASTLE RD | 067 | LEX | 2025-06-10 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-06-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1729.33 | 0 | 0 | 0 | 1729.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304122600 |  | 100322796 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | KASTLE | 1253 KASTLE RD | 067 | LEX | 2025-06-12 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RTINCHE | 2025-06-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2624.17 | 0 | 0 | 0 | 2624.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304122700 |  | 100322805 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | KASTLE | 1254 KASTLE RD | 067 | LEX | 2025-06-12 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-06-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2092.09 | 0 | 0 | 0 | 2092.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304122900 |  | 100322798 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | KASTLE | 1261 KASTLE RD | 067 | LEX | 2025-06-06 | U129673 | U132386 | 2025-01-03 | 2025-12-19 |  |  | A WILLIAMSON | 2025-06-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2305.25 | 0 | 0 | 0 | 2305.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304123000 |  | 100322803 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | KASTLE | 1262 KASTLE RD | 067 | LEX | 2025-05-28 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-05-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3466.79 | 0 | 0 | 0 | 3466.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304123200 |  | 100322801 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | KASTLE | 1276 KASTLE RD | 067 | LEX | 2025-06-16 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-06-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1
KY | KY - WEST | 2621 | 25304123300 |  | 100322800 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | KASTLE | 1280 KASTLE RD | 067 | LEX | 2025-04-02 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-04-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1500.67 | 0 | 0 | 0 | 1500.67 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304123600 |  | 100322869 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | MONTCLAIR | 616 MONTCLAIR DR | 067 | LEX | 2025-04-17 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-04-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2470.68 | 0 | 0 | 0 | 2470.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304123700 |  | 100322870 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | MONTCLAIR | 620 MONTCLAIR DR | 067 | LEX | 2025-03-24 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-03-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3254.9 | 0 | 0 | 0 | 3254.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304123800 |  | 100322871 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | MONTCLAIR | 624 MONTCLAIR DR | 067 | LEX | 2025-03-24 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-03-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 3377.91 | 540.12 | 0 | 31.66 | 2806.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304123900 |  | 100322872 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | MONTCLAIR | 628 MONTCLAIR DR | 067 | LEX | 2025-03-21 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-03-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 4357.06 | 540.12 | 0 | 31.66 | 3785.28 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304124000 |  | 100322873 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | MONTCLAIR | 636 MONTCLAIR DR | 067 | LEX | 2025-05-03 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-05-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2292.25 | 0 | 0 | 0 | 2292.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304124100 |  | 100322874 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | MONTCLAIR | 640 MONTCLAIR DR | 067 | LEX | 2025-03-25 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-03-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2555.76 | 0 | 0 | 0 | 2555.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304124200 |  | 100322864 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | MONTCLAIR | 641 MONTCLAIR DR | 067 | LEX | 2025-03-25 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-03-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2422.49 | 540.12 | 0 | 31.66 | 1850.71 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304124300 |  | 100322875 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | MONTCLAIR | 644 MONTCLAIR DR | 067 | LEX | 2025-03-31 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-03-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.2 | 1 | 2114.21 | 149.87 | 0 | 8.78 | 1955.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304124500 |  | 100322862 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | MONTCLAIR | 649 MONTCLAIR DR | 067 | LEX | 2025-03-26 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-03-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2075.67 | 0 | 0 | 0 | 2075.67 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304124600 |  | 100322876 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | MONTCLAIR | 650 MONTCLAIR DR | 067 | LEX | 2025-03-27 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-03-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4461.48 | 0 | 0 | 0 | 4461.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304124700 |  | 100322858 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | MONTCLAIR | 653 MONTCLAIR DR | 067 | LEX | 2025-03-28 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-03-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1853.6 | 0 | 0 | 0 | 1853.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304124800 |  | 100322859 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | MONTCLAIR | 657 MONTCLAIR DR | 067 | LEX | 2025-03-31 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-03-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1944 | 0 | 0 | 0 | 1944 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304124900 |  | 100322878 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | MONTCLAIR | 658 MONTCLAIR DR | 067 | LEX | 2025-04-01 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-04-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10 | 1 | 3284.47 | 630.46 | 0 | 38.48 | 2615.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304125200 |  | 100322881 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | MONTCLAIR | 700 MONTCLAIR DR | 067 | LEX | 2025-03-28 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-03-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2974.95 | 540.12 | 0 | 31.66 | 2403.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304125300 |  | 100322861 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | MONTCLAIR | 705 MONTCLAIR DR | 067 | LEX | 2025-04-14 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-04-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2041.42 | 0 | 0 | 0 | 2041.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304125400 |  | 100322882 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | MONTCLAIR | 708 MONTCLAIR DR | 067 | LEX | 2025-03-25 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-03-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2420.51 | 0 | 0 | 0 | 2420.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304125500 |  | 100322883 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | MONTCLAIR | 716 MONTCLAIR DR | 067 | LEX | 2025-03-25 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-03-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2080.84 | 0 | 0 | 0 | 2080.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304125700 |  | 100322885 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | MONTCLAIR | 742 MONTCLAIR DR | 067 | LEX | 2025-03-27 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-03-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2511.5 | 0 | 0 | 0 | 2511.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304125800 |  | 100322886 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | MONTCLAIR | 748 MONTCLAIR DR | 067 | LEX | 2025-03-27 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-03-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.25 | 1 | 2891.53 | 557 | 0 | 32.66 | 2301.87 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304125900 |  | 100322887 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | MONTCLAIR | 760 MONTCLAIR DR | 067 | LEX | 2025-04-17 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-04-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2520.56 | 0 | 0 | 0 | 2520.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304126000 |  | 100322888 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | MONTCLAIR | 814 MONTCLAIR DR | 067 | LEX | 2025-03-26 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-03-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2561.54 | 0 | 0 | 0 | 2561.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304126100 |  | 100322889 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | MONTCLAIR | 818 MONTCLAIR DR | 067 | LEX | 2025-05-23 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-05-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2115.35 | 0 | 0 | 0 | 2115.35 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304126200 |  | 100322752 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | SCOVILLE | 1217 SCOVILLE RD | 067 | LEX | 2025-05-23 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-05-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2843.38 | 0 | 0 | 0 | 2843.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304126300 |  | 100322753 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | SCOVILLE | 1221 SCOVILLE RD | 067 | LEX | 2025-04-18 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-04-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2607.32 | 504.37 | 0 | 30.78 | 2072.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304126400 |  | 100322754 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | SCOVILLE | 1223 SCOVILLE RD | 067 | LEX | 2025-04-25 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-04-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2214.39 | 0 | 0 | 0 | 2214.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304126500 |  | 100322755 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | SCOVILLE | 1225 SCOVILLE RD | 067 | LEX | 2025-04-25 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-04-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2662.25 | 0 | 0 | 0 | 2662.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304126600 |  | 100322780 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | SCOVILLE | 1226 SCOVILLE RD | 067 | LEX | 2025-05-23 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-05-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1968.47 | 0 | 0 | 0 | 1968.47 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304126700 |  | 100322756 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | SCOVILLE | 1227 SCOVILLE RD | 067 | LEX | 2025-05-14 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-05-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2411.26 | 0 | 0 | 0 | 2411.26 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304126800 |  | 100322757 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | SCOVILLE | 1229 SCOVILLE RD | 067 | LEX | 2025-05-23 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-05-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3371.79 | 0 | 0 | 0 | 3371.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304126900 |  | 100322779 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | SCOVILLE | 1230 SCOVILLE RD | 067 | LEX | 2025-04-18 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-04-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1619.97 | 0 | 0 | 0 | 1619.97 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304127300 |  | 100322759 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | SCOVILLE | 1249 SCOVILLE RD | 067 | LEX | 2025-04-28 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-04-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2751.51 | 0 | 0 | 0 | 2751.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304127400 |  | 100322775 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | SCOVILLE | 1250 SCOVILLE RD | 067 | LEX | 2025-05-14 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-05-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2819.56 | 0 | 0 | 0 | 2819.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304127500 |  | 100322760 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | SCOVILLE | 1253 SCOVILLE RD | 067 | LEX | 2025-06-19 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-06-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1
KY | KY - WEST | 2621 | 25304127600 |  | 100322773 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | SCOVILLE | 1258 SCOVILLE RD | 067 | LEX | 2025-04-23 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-04-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2236.11 | 0 | 0 | 0 | 2236.11 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304127700 |  | 100322761 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | SCOVILLE | 1259 SCOVILLE RD | 067 | LEX | 2025-04-17 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-04-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1722.13 | 0 | 0 | 0 | 1722.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304127800 |  | 100322772 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | SCOVILLE | 1262 SCOVILLE RD | 067 | LEX | 2025-04-17 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-04-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2633.75 | 0 | 0 | 0 | 2633.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304127900 |  | 100322762 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | SCOVILLE | 1263 SCOVILLE RD | 067 | LEX | 2025-06-13 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-06-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2767.88 | 0 | 0 | 0 | 2767.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304128100 |  | 100322771 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | SCOVILLE | 1266 SCOVILLE RD | 067 | LEX | 2025-04-17 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-04-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2297.74 | 504.37 | 0 | 30.78 | 1762.59 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304128200 |  | 100322770 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | SCOVILLE | 1270 SCOVILLE RD | 067 | LEX | 2025-05-23 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-05-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2771.33 | 0 | 0 | 0 | 2771.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304128300 |  | 100322763 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | SCOVILLE | 1271 SCOVILLE RD | 067 | LEX | 2025-05-23 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-05-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3564.93 | 0 | 0 | 0 | 3564.93 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304128400 |  | 100322764 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | SCOVILLE | 1275 SCOVILLE RD | 067 | LEX | 2025-04-24 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-04-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3963.17 | 0 | 0 | 0 | 3963.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304128500 |  | 100322765 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | SCOVILLE | 1279 SCOVILLE RD | 067 | LEX | 2025-04-24 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-04-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2426.29 | 0 | 0 | 0 | 2426.29 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304128600 |  | 501341965 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | SCOVILLE | 1282 SCOVILLE RD | 067 | LEX | 2025-04-15 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-04-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1532.46 | 0 | 0 | 0 | 1532.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304128700 |  | 100322766 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | SCOVILLE | 1283 SCOVILLE RD | 067 | LEX | 2025-04-14 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-04-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 15134.18 | 504.37 | 0 | 30.78 | 14599.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304129100 |  | 100322830 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | SUMMIT | 1218 SUMMIT DR | 067 | LEX | 2025-06-18 | U128762 | U132386 | 2025-01-03 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-06-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1
KY | KY - WEST | 2621 | 25304130200 |  | 100322824 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE W/22026238800 | 2600B | SUMMIT | 1252 SUMMIT DR | 067 | LEX | 2025-03-19 | U128816 | U132386 | 2025-01-03 | 2025-12-19 |  |  | OLIVER MAYNARD | 2025-03-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1696.12 | 0 | 0 | 0 | 1696.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304138900 |  | 100322877 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE SL/22026238800 | 2600B | MONTCLAIR | 654 MONTCLAIR DR | 067 | LEX | 2025-04-01 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-04-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2411.84 | 0 | 0 | 0 | 2411.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304139400 |  | 100322879 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE SL/22026238800 | 2600B | MONTCLAIR | 660 MONTCLAIR DR | 067 | LEX | 2025-04-02 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-04-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 4395.57 | 504.37 | 0 | 30.78 | 3860.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304140000 |  | 100322857 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE SL/22026238800 | 2600B | MONTCLAIR | 817 MONTCLAIR DR | 067 | LEX | 2025-03-26 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-03-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1636.5 | 0 | 0 | 0 | 1636.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304140300 |  | 100322751 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE SL/22026238800 | 2600B | SCOVILLE | 1213 SCOVILLE RD | 067 | LEX | 2025-05-15 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-05-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 3537.13 | 544.64 | 0 | 31.54 | 2960.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304141200 |  | 100322768 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE SL/22026238800 | 2600B | SCOVILLE | 1276 SCOVILLE RD | 067 | LEX | 2025-04-16 | U129731 | U132386 | 2025-01-03 | 2025-12-19 |  |  | EDWARD F GOINS | 2025-04-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 3707.38 | 504.37 | 0 | 30.78 | 3172.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304141600 |  | 100292153 |  | 6720216L | 2184395 |  |  | 565 | EX | REPLACE SL 24026370200 | 2600B | FREEMAN | 552 FREEMAN DR | 067 | LEX | 2025-05-01 | U461309 | U123268 | 2025-01-03 | 2025-12-19 |  |  | RANDALL HUMPHREYS | 2025-05-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 2137.82 | 0 | 297.86 | 0 | 1839.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304141700 |  | 100292099 |  | 6720216L | 2184395 |  |  | 565 | EX | REPLACE SL 24026370200 | 2600B | FREEMAN | 553 FREEMAN DR | 067 | LEX | 2025-04-29 | U461309 | U123268 | 2025-01-03 | 2025-12-19 |  |  | RANDALL HUMPHREYS | 2025-04-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 3 | 1 | 2085.94 | 183.81 | 350.74 | 208.13 | 1343.26 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304141800 |  | 100292152 |  | 6720216L | 2184395 |  |  | 565 | EX | REPLACE SL 24026370200 | 2600B | FREEMAN | 554 FREEMAN DR | 067 | LEX | 2025-04-30 | U461309 | U123268 | 2025-01-03 | 2025-12-19 |  |  | RANDALL HUMPHREYS | 2025-04-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 3.5 | 1 | 2677.42 | 214.47 | 297.86 | 242.81 | 1922.28 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304141900 |  | 100292100 |  | 6720216L | 2184395 |  |  | 565 | EX | REPLACE SL 24026370200 | 2600B | FREEMAN | 555 FREEMAN DR | 067 | LEX | 2025-04-25 | U129722 | U123268 | 2025-01-03 | 2025-12-19 |  |  | DAVID YOUNG | 2025-04-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 2268.23 | 0 | 0 | 0 | 2268.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304142000 |  | 100292151 |  | 6720216L | 2184395 |  |  | 565 | EX | REPLACE SL 24026370200 | 2600B | FREEMAN | 556 FREEMAN DR | 067 | LEX | 2025-04-30 | U461309 | U123268 | 2025-01-03 | 2025-12-19 |  |  | RANDALL HUMPHREYS | 2025-04-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 4.5 | 1 | 2857.42 | 275.72 | 297.86 | 312.19 | 1971.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304142100 |  | 100292101 |  | 6720216L | 2184395 |  |  | 565 | EX | REPLACE SL 24026370200 | 2600B | FREEMAN | 557 FREEMAN DR | 067 | LEX | 2025-04-29 | U461309 | U123268 | 2025-01-03 | 2025-12-19 |  |  | RANDALL HUMPHREYS | 2025-04-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 5 | 1 | 3109.74 | 306.35 | 408.24 | 346.88 | 2048.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304142200 |  | 100292102 |  | 6720216L | 2184395 |  |  | 565 | EX | REPLACE SL 24026370200 | 2600B | FREEMAN | 559 FREEMAN DR | 067 | LEX | 2025-04-24 | U129722 | U123268 | 2025-01-03 | 2025-12-19 |  |  | DAVID YOUNG | 2025-04-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 1967.85 | 0 | 0 | 0 | 1967.85 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304142300 |  | 100292149 |  | 6720216L | 2184395 |  |  | 565 | EX | REPLACE SL 24026370200 | 2600B | FREEMAN | 560 FREEMAN DR | 067 | LEX | 2025-05-01 | U461309 | U123268 | 2025-01-03 | 2025-12-19 |  |  | RANDALL HUMPHREYS | 2025-05-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 8 | 1 | 3284.35 | 540.3 | 297.86 | 606.23 | 1839.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304142400 |  | 100292103 |  | 6720216L | 2184395 |  |  | 565 | EX | REPLACE SL 24026370200 | 2600B | FREEMAN | 561 FREEMAN DR | 067 | LEX | 2025-04-15 | U461309 | U123268 | 2025-01-03 | 2025-12-19 |  |  | RANDALL HUMPHREYS | 2025-04-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 8 | 1 | 3705.46 | 490.16 | 408.24 | 555 | 2252.06 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304142500 |  | 100292148 |  | 6720216L | 2184395 |  |  | 565 | EX | REPLACE SL 24026370200 | 2600B | FREEMAN | 562 FREEMAN DR | 067 | LEX | 2025-05-02 | U461309 | U123268 | 2025-01-03 | 2025-12-19 |  |  | RANDALL HUMPHREYS | 2025-05-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 4.5 | 1 | 2782.76 | 303.93 | 297.86 | 341.01 | 1839.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304142600 |  | 100292104 |  | 6720216L | 2184395 |  |  | 565 | EX | REPLACE SL 24026370200 | 2600B | FREEMAN | 563 FREEMAN DR | 067 | LEX | 2025-04-28 | U461309 | U123268 | 2025-01-03 | 2025-12-19 |  |  | RANDALL HUMPHREYS | 2025-04-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 8 | 1 | 3415.61 | 490.16 | 368.79 | 555 | 2001.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304142700 |  | 100292147 |  | 6720216L | 2184395 |  |  | 565 | EX | REPLACE SL 24026370200 | 2600B | FREEMAN | 564 FREEMAN DR | 067 | LEX | 2025-05-05 | U129722 | U123268 | 2025-01-03 | 2025-12-19 |  |  | DAVID YOUNG | 2025-05-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 2001.72 | 0 | 0 | 0 | 2001.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304142800 |  | 100292105 |  | 6720216L | 2184395 |  |  | 565 | EX | REPLACE SL 24026370200 | 2600B | FREEMAN | 565 FREEMAN DR | 067 | LEX | 2025-04-21 | U129673 | U123268 | 2025-01-03 | 2025-12-19 |  |  | A WILLIAMSON | 2025-04-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 8 | 1 | 2687.06 | 514.41 | 0 | 126.37 | 2046.28 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304142900 |  | 100292146 |  | 6720216L | 2184395 |  |  | 565 | EX | REPLACE SL 24026370200 | 2600B | FREEMAN | 566 FREEMAN DR | 067 | LEX | 2025-04-17 | U461309 | U123268 | 2025-01-03 | 2025-12-19 |  |  | RANDALL HUMPHREYS | 2025-04-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 8 | 1 | 3101.51 | 490.16 | 304.57 | 555 | 1751.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304143000 |  | 100292106 |  | 6720216L | 2184395 |  |  | 565 | EX | REPLACE SL 24026370200 | 2600B | FREEMAN | 567 FREEMAN DR | 067 | LEX | 2025-04-11 | U461309 | U123268 | 2025-01-03 | 2025-12-19 |  |  | RANDALL HUMPHREYS | 2025-04-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 8 | 1 | 3772.79 | 490.16 | 460.87 | 555 | 2266.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304143100 |  | 100292107 |  | 6720216L | 2184395 |  |  | 565 | EX | REPLACE SL 24026370200 | 2600B | FREEMAN | 569 FREEMAN DR | 067 | LEX | 2025-04-22 | U129673 | U123268 | 2025-01-03 | 2025-12-19 |  |  | A WILLIAMSON | 2025-04-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 8 | 1 | 3409.14 | 514.41 | 0 | 126.37 | 2768.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304143200 |  | 100292144 |  | 6720216L | 2184395 |  |  | 565 | EX | REPLACE SL 24026370200 | 2600B | FREEMAN | 570 FREEMAN DR | 067 | LEX | 2025-04-14 | U461309 | U123268 | 2025-01-03 | 2025-12-19 |  |  | RANDALL HUMPHREYS | 2025-04-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 8 | 1 | 3614.19 | 490.16 | 297.86 | 555 | 2271.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304143300 |  | 100292154 |  | 6720216L | 2184395 |  |  | 565 | EX | REPLACE SL 24026370200 | 2600B | FREEMAN | 550 FREEMAN DR | 067 | LEX | 2025-05-02 | U461309 | U123268 | 2025-01-03 | 2025-12-19 |  |  | RANDALL HUMPHREYS | 2025-05-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 3.5 | 1 | 2639.45 | 236.41 | 297.86 | 265.22 | 1839.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304143900 |  | 100292145 |  | 6720216L | 2184395 |  |  | 565 | EX | REPLACE SL 24026370200 | 2600B | FREEMAN | 568 FREEMAN DR | 067 | LEX | 2025-04-16 | U461309 | U123268 | 2025-01-03 | 2025-12-19 |  |  | RANDALL HUMPHREYS | 2025-04-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 8 | 1 | 4351.92 | 490.16 | 297.86 | 555 | 3008.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304153900 |  | 100306731 |  | 6712212L |  |  |  | 565 | EX | GRADE 1 REPLACE S-L 2402632200 | 2621P | WOLF RUN | 957 WOLF RUN DR | 067 | LEX | 2025-04-01 | MCRAIG | U123268 | 2025-01-03 | 2025-04-01 | 2025-04-01 |  | MCRAIG | 2025-04-01 | 2025-04-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 22.6333 | 4 | 2268.73 | 1251.96 | 418.23 | 598.54 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304154700 |  | 100306722 |  | 6712212L | 2403788 |  |  | 565 | EX | REPLACE SL 24026322000 | 2621P | DUNTREATH | 1634 DUNTREATH DR | 067 | LEX | 2025-04-03 | BYOUNG2 | U123268 | 2025-01-03 | 2025-04-02 | 2025-04-02 |  | BYOUNG2 | 2025-04-03 | 2025-04-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.1833 | 5 | 1508.19 | 772.9 | 401.62 | 228.59 | 105.08 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25304156400 |  | 501079547 |  | 7356216-H | 0991319 |  |  | 563 | EX | 1" P LONG | 2621P | LEVISA | 458 LEVISA DR | 127 | LOU | 2025-02-05 | U124604 | U129176 | 2025-01-03 | 2025-01-03 | 2025-01-17 |  | RECUMP | 2025-02-04 | 2025-01-23 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 38.9833 | 8 | 3608.44 | 2620.98 | 180.12 | 680.06 | 127.28 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25304158200 |  | 100262453 |  | 7352256G |  |  |  | 563 | EX | 1" P SHORT | 2621P | CHINN | 2723 CHINN ST | 019 | ASH | 2025-02-03 | U124604 | U128272 | 2025-01-03 | 2025-01-17 | 2025-01-17 |  | ABHATFIE | 2025-01-31 | 2025-01-27 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 25.45 | 4 | 2298.53 | 1855.14 | 220.7 | 122.05 | 100.64 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25304645700 |  | 100242173 |  | 7356260M | 1635077 |  |  | 565 | EX | SERVICE LINE REPAIR | 2621P | 10TH | 616 10TH ST | 019 | CAT | 2025-01-04 | MCOLLET | U134902 | 2025-01-04 | 2025-01-04 | 2025-01-04 |  | MCOLLET | 2025-01-04 | 2025-01-04 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 | KYACN |  | 100 | 056532B26310021 | 20.35 | 4 | 7657.39 | 5581.17 | 428.37 | 1590.13 | 57.72 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25304673700 |  | 501356514 |  | 6736248E | 2301356 | U128885 |  | 563 | EX | INSTALL 700'-2" CSHP | 2600B | NEW LAIR | 1205 NEW LAIR RD LTNEWBD | 097 | CYN | 2025-05-27 | U126284 | U128885 | 2025-01-06 | 2025-04-16 | 2025-04-30 |  | JOSH PASLEY | 2025-05-23 | 2025-04-21 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 60.8167 | 7 | 48546.03 | 4382.42 | 28488.92 | 258.79 | 15415.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25304674400 |  | 500941998 |  | 6716232M | 0567438 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | ROCKY CREEK | 111 ROCKY CREEK RD | 209 | GEO | 2025-01-28 | U461516 | U126856 | 2025-01-06 | 2025-01-07 | 2025-01-20 |  | NEAL JOHNSON | 2025-01-23 |  | 2025-01-23 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 4780.6 | 514.18 | 240.47 | 33.83 | 3992.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304674900 |  | 501347910 |  | 6724204A | 2291616 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | NIGHT HERON | 3417 NIGHT HERON WY | 067 | LEX | 2025-01-25 | U126285 | U126856 | 2025-01-06 | 2025-01-07 | 2025-01-27 |  | DUSTIN DAVIS | 2025-01-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 3061.52 | 521.46 | 363.51 | 414.39 | 1762.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304675100 |  | 501347911 |  | 6724204A | 2291616 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | NIGHT HERON | 3421 NIGHT HERON WY | 067 | LEX | 2025-01-14 | U126532 | U126856 | 2025-01-06 | 2025-01-07 | 2025-01-20 |  | LESLIE SHARON | 2025-01-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 10.5 | 1 | 2642.85 | 650.12 | 316.91 | 541.63 | 1134.19 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25304778700 |  | 501372769 |  | 6700224O | 2409529 |  |  | 563 | EX | 2" P SHORT/2ND ATTEMPT | 2600B | GAYLAND | 223 GAYLAND DR | 239 | MID | 2025-01-16 | U128336 | U130616 | 2025-01-07 | 2025-01-10 | 2025-01-23 |  | JOSHUA COX | 2025-01-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 6530.53 | 0 | 2443.33 | 0 | 4087.2 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25304791600 |  | 100260119 |  | 7356256A |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | HILTON | 1720 HILTON AV | 019 | ASH | 2025-01-07 | U128523 | U129939 | 2025-01-07 | 2025-01-07 |  |  | BRANDON ROBERTS | 2025-01-07 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1
KY | KY - EAST | 2631 | 25304803400 |  | 100247125 |  | 7352256L | 2403760 |  |  | 565 | EX | REPLACE SL 24026321400 | 2600B | CHARLES | 3441 CHARLES ST | 019 | ASH | 2025-06-05 | U128523 | U123268 | 2025-01-07 | 2025-12-19 |  |  | BRANDON ROBERTS | 2025-06-05 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1964.73 | 0 | 0 | 0 | 1964.73 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25304808200 |  | 100247044 |  | 7352256L | 2403760 |  |  | 565 | EX | REPLACE SL 24026321400 | 2600B | NOLTE | 2800 NOLTE ST | 019 | ASH | 2025-06-13 | U123965 | U123268 | 2025-01-07 | 2025-12-19 |  |  | MBLANKE/CJH MITCHELL DICKESS | 2025-06-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2505.15 | 0 | 0 | 0 | 2505.15 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304847200 |  | 100458320 |  | 6724208M |  |  |  | 565 | EX | SERVICE LINE UPGRADE | 2621P | RICHMOND | 3360 RICHMOND RD | 067 | LEX | 2025-02-19 | U124604 | U124604 | 2025-01-07 | 2025-12-23 | 2025-12-25 |  | LSTANFI | 2025-02-18 | 2025-01-27 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 58.7667 | 10 | 10576.65 | 3733.54 | 697.56 | 331.96 | 5813.59 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304927800 |  | 500673720 |  | 6720216E | 2407535 |  |  | 563 | EX | 2"PMMP LONG S/L (2ND ATTEMPT) | 2600B | NEWTOWN SPRING | 760 NEWTOWN SPRING DR | 067 | LEX | 2025-02-25 | U126602 | U126856 | 2025-01-08 | 2025-01-10 | 2025-01-23 |  | DEREK PAYTON | 2025-01-17 | 2025-01-14 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 37.4 | 5 | 14765.55 | 2340.22 | 0 | 153.92 | 12271.41 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304928600 |  | 500072157 |  | 16712204A |  |  |  | 563 | EX | 1" P LONG/PRMT RCVD | 2600B | GLADMAN | 3917 GLADMAN WY | 067 | LEX | 2025-01-28 | U461516 | U129531 | 2025-01-08 | 2025-01-13 | 2025-01-24 |  | NEAL JOHNSON | 2025-01-27 |  | 2025-01-27 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 6522.26 | 487.03 | 261.82 | 412.11 | 5361.3 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25304932800 |  | 100407055 |  | 6712228C |  |  |  | 563 | EX | 1.25" P SHORT LP MAIN/PRMT RCV | 2600B | WASHINGTON | 341< E WASHINGTON ST | 209 | GEO | 2025-01-27 | U128816 | U132256 | 2025-01-08 | 2025-01-13 | 2025-01-24 |  | OLIVER MAYNARD | 2025-01-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 9.5 | 1 | 4573.23 | 612.8 | 0 | 40.32 | 3920.11 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25304936300 |  | 500536332 |  | 6744204C | 2300572 |  |  | 565 | EX | REPLACE SL/23026298000 | 2600B | CAMELOT | 100 CAMELOT DR | 049 | WIN | 2025-06-16 | U126602 | U132386 | 2025-01-08 | 2025-12-19 |  |  | DEREK PAYTON | 2025-05-16 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 7382.35 | 0 | 0 | 0 | 7382.35 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25304937000 |  | 100452137 |  | 6744204C | 2300572 |  |  | 565 | EX | REPLACE SL/23026298000 | 2600B | CAMELOT | 101 CAMELOT DR | 049 | WIN | 2025-06-16 | U126602 | U132386 | 2025-01-08 | 2025-12-19 |  |  | DEREK PAYTON | 2025-05-16 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3346.84 | 0 | 0 | 0 | 3346.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25304937300 |  | 100466428 |  | 6744204C | 2300572 |  |  | 565 | EX | REPLACE SL/23026298000 | 2600B | CAMELOT | 102 CAMELOT DR | 049 | WIN | 2025-06-19 | U126602 | U132386 | 2025-01-08 | 2025-12-19 |  |  | DEREK PAYTON | 2025-05-16 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2771.96 | 0 | 0 | 0 | 2771.96 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25304937500 |  | 500782409 |  | 6744204C | 2300572 |  |  | 565 | EX | REPLACE SL/23026298000 | 2600B | CAMELOT | 103 CAMELOT DR | 049 | WIN | 2025-06-18 | U126602 | U132386 | 2025-01-08 | 2025-12-19 |  |  | DEREK PAYTON | 2025-06-02 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3729.44 | 0 | 0 | 0 | 3729.44 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25304938000 |  | 100460050 |  | 6744204C | 2300572 |  |  | 565 | EX | REPLACE SL/23026298000 | 2600B | CAMELOT | 104 CAMELOT DR | 049 | WIN | 2025-05-07 | U126602 | U132386 | 2025-01-08 | 2025-12-19 |  |  | DEREK PAYTON | 2025-05-07 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2489.61 | 0 | 0 | 0 | 2489.61 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25304938100 |  | 500810287 |  | 6744204C | 2300572 |  |  | 565 | EX | REPLACE SL/23026298000 | 2600B | CAMELOT | 105 CAMELOT DR | 049 | WIN | 2025-06-18 | U126602 | U132386 | 2025-01-08 | 2025-12-19 |  |  | CAMELOT | 2025-05-16 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3346.84 | 0 | 0 | 0 | 3346.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25304938500 |  | 500012421 |  | 6744204C | 2300572 |  |  | 565 | EX | REPLACE SL/23026298000 | 2600B | CAMELOT | 106 CAMELOT DR | 049 | WIN | 2025-05-02 | U126602 | U132386 | 2025-01-08 | 2025-12-19 |  |  | DEREK PAYTON | 2025-05-02 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3059.4 | 0 | 0 | 0 | 3059.4 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25304938600 |  | 500642194 |  | 6744204C | 2300572 |  |  | 565 | EX | REPLACE SL/23026298000 | 2600B | CAMELOT | 107 CAMELOT DR | 049 | WIN | 2025-05-07 | U126602 | U132386 | 2025-01-08 | 2025-12-19 |  |  | DEREK PAYTON | 2025-05-07 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3423.36 | 0 | 0 | 0 | 3423.36 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25304938800 |  | 500536328 |  | 6744204C | 2300572 |  |  | 565 | EX | REPLACE SL/23026298000 | 2600B | CAMELOT | 108 CAMELOT DR | 049 | WIN | 2025-06-16 | U126602 | U132386 | 2025-01-08 | 2025-12-19 |  |  | DEREK PAYTON | 2025-05-16 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3427.16 | 0 | 0 | 0 | 3427.16 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25304938900 |  | 500615841 |  | 6744204C | 2300572 |  |  | 565 | EX | REPLACE SL/23026298000 | 2600B | CAMELOT | 110 CAMELOT DR | 049 | WIN | 2025-05-07 | U126602 | U132386 | 2025-01-08 | 2025-12-19 |  |  | DEREK PAYTON | 2025-05-07 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3346.84 | 0 | 0 | 0 | 3346.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25304939800 |  | 100443087 |  | 6744204C | 2300572 |  |  | 565 | EX | REPLACE SL/23026298000 | 2600B | EDGEWOOD | 11 EDGEWOOD DR | 049 | WIN | 2025-04-30 | U126602 | U132386 | 2025-01-08 | 2025-12-19 |  |  | DEREK PAYTON | 2025-04-30 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3198.62 | 0 | 0 | 0 | 3198.62 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25304940500 |  | 500179061 |  | 6744204C | 2300572 |  |  | 565 | EX | REPLACE SL/23026298000 | 2600B | EDGEWOOD | 16 EDGEWOOD DR | 049 | WIN | 2025-06-05 | U126602 | U132386 | 2025-01-08 | 2025-12-19 |  |  | DEREK PAYTON | 2025-06-05 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3346.84 | 0 | 0 | 0 | 3346.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25304941000 |  | 100350380 |  | 6744204C | 2300572 |  |  | 565 | EX | REPLACE SL/23026298000 | 2600B | EDGEWOOD | 21 EDGEWOOD DR | 049 | WIN | 2025-05-01 | U126602 | U132386 | 2025-01-08 | 2025-12-19 |  |  | DEREK PAYTON | 2025-05-01 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3059.4 | 0 | 0 | 0 | 3059.4 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25304942000 |  | 100350379 |  | 6744204C | 2300572 |  |  | 565 | EX | REPLACE SL/23026298000 | 2600B | EDGEWOOD | 24 EDGEWOOD DR | 049 | WIN | 2025-06-04 | U126602 | U132386 | 2025-01-08 | 2025-12-19 |  |  | DEREK PAYTON | 2025-06-04 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4057.9 | 0 | 0 | 0 | 4057.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25304942200 |  | 100455229 |  | 6744204C | 2300572 |  |  | 565 | EX | REPLACE SL/23026298000 | 2600B | EDGEWOOD | 28 EDGEWOOD DR | 049 | WIN | 2025-06-04 | U126602 | U132386 | 2025-01-08 | 2025-12-19 |  |  | DEREK PAYTON | 2025-06-04 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3516.99 | 84.78 | 0 | 85.37 | 3346.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25304942500 |  | 100451520 |  | 6744204C | 2300572 |  |  | 565 | EX | REPLACE SL/23026298000 | 2600B | EDGEWOOD | 35 EDGEWOOD DR | 049 | WIN | 2025-06-18 | U126602 | U132386 | 2025-01-08 | 2025-12-19 |  |  | DEREK PAYTON | 2025-06-02 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 5112.27 | 0 | 0 | 0 | 5112.27 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25304949800 |  | 100350376 |  | 6744204C | 2300572 |  |  | 565 | EX | REPLACE SL/23026298000 | 2600B | MOCKINGBIRD VA | 72 MOCKINGBIRD VA RD | 049 | WIN | 2025-06-16 | U126602 | U132386 | 2025-01-08 | 2025-12-19 |  |  | DEREK PAYTON | 2025-06-02 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3346.84 | 0 | 0 | 0 | 3346.84 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25304973100 |  | 500390717 |  | 7336276I | 2410099 |  |  | 565 | EX | SERVICE LINE/METER UPGRADE | 2621P | LEWIS | 261 LEWIS LN | 089 | GRE | 2025-02-26 | RECUMP | U123688 | 2025-01-08 | 2025-02-21 | 2025-02-21 |  | RECUMP | 2025-02-26 | 2025-02-06 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26310031 | 15.85 | 3 | 2171.02 | 1275.2 | 547.48 | 348.34 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304974500 |  | 100316215 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | KOSTER | 202 KOSTER ST | 067 | LEX | 2025-06-05 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-06-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2424.79 | 0 | 0 | 0 | 2424.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304974600 |  | 100316174 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | KOSTER | 203 KOSTER ST | 067 | LEX | 2025-06-13 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-06-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 5153.77 | 0 | 0 | 0 | 5153.77 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304974800 |  | 100316213 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | KOSTER | 206 KOSTER ST | 067 | LEX | 2025-06-03 | U128762 | U132386 | 2025-01-08 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-06-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2092.36 | 0 | 0 | 0 | 2092.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304975200 |  | 100316205 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | KOSTER | 214 KOSTER ST | 067 | LEX | 2025-06-10 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-06-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4787.22 | 0 | 0 | 0 | 4787.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304975300 |  | 100316179 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | KOSTER | 217 KOSTER ST | 067 | LEX | 2025-05-22 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-05-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2645.62 | 0 | 0 | 0 | 2645.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304975500 |  | 100316203 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | KOSTER | 220 KOSTER ST | 067 | LEX | 2025-06-06 | U128762 | U132386 | 2025-01-08 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-06-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3501.76 | 0 | 0 | 0 | 3501.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304975600 |  | 100316200 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | KOSTER | 226 KOSTER ST | 067 | LEX | 2025-05-28 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-05-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2529.94 | 0 | 0 | 0 | 2529.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304975700 |  | 100316182 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | KOSTER | 227 KOSTER ST | 067 | LEX | 2025-05-21 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-05-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2092.36 | 0 | 0 | 0 | 2092.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304975800 |  | 100316198 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | KOSTER | 228 KOSTER ST | 067 | LEX | 2025-06-06 | U128762 | U132386 | 2025-01-08 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-06-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1601.21 | 0 | 0 | 0 | 1601.21 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304975900 |  | 100316183 |  | 6716208B | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | KOSTER | 231 KOSTER ST | 067 | LEX | 2025-05-20 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-05-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2772.08 | 0 | 0 | 0 | 2772.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304976200 |  | 100316193 |  | 6716208B | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | KOSTER | 238 KOSTER ST | 067 | LEX | 2025-05-28 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-05-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2092.36 | 0 | 0 | 0 | 2092.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304976300 |  | 100316185 |  | 6716208B | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | KOSTER | 239 KOSTER ST | 067 | LEX | 2025-05-21 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-05-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2772.08 | 0 | 0 | 0 | 2772.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304976400 |  | 100316192 |  | 6716208B | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | KOSTER | 242 KOSTER ST | 067 | LEX | 2025-06-09 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-06-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3808.75 | 0 | 0 | 0 | 3808.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304976500 |  | 100316186 |  | 6716208B | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | KOSTER | 243 KOSTER ST | 067 | LEX | 2025-05-29 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-05-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3544.77 | 0 | 0 | 0 | 3544.77 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304976600 |  | 100316191 |  | 6716208B | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | KOSTER | 246 KOSTER ST | 067 | LEX | 2025-06-09 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-06-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3742.13 | 0 | 0 | 0 | 3742.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304976700 |  | 100316187 |  | 6716208B | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | KOSTER | 247 KOSTER ST | 067 | LEX | 2025-06-11 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-06-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3423.98 | 0 | 0 | 0 | 3423.98 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304979000 |  | 100316250 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | PICADOME | 297 PICADOME PR | 067 | LEX | 2025-03-31 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-03-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2586.92 | 0 | 0 | 0 | 2586.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304979100 |  | 100316248 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | PICADOME | 298 PICADOME PR | 067 | LEX | 2025-04-02 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-04-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.7 | 1 | 5662.74 | 109.34 | 0 | 6.7 | 5546.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304979200 |  | 100316252 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | PICADOME | 301 PICADOME PR | 067 | LEX | 2025-03-24 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-03-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2163.37 | 0 | 0 | 0 | 2163.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304979300 |  | 100316253 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | PICADOME | 303 PICADOME PR | 067 | LEX | 2025-04-07 | U129673 | U132386 | 2025-01-08 | 2025-12-19 |  |  | A WILLIAMSON | 2025-04-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.8 | 1 | 8471.34 | 437.28 | 0 | 26.68 | 8007.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304979400 |  | 100316246 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | PICADOME | 304 PICADOME PR | 067 | LEX | 2025-03-28 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-03-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3509.02 | 0 | 0 | 0 | 3509.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304979500 |  | 100316254 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | PICADOME | 305 PICADOME PR | 067 | LEX | 2025-03-20 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-03-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2955.53 | 0 | 0 | 0 | 2955.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304979600 |  | 100316303 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | PICADOME | 401 PICADOME PR | 067 | LEX | 2025-03-21 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-03-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3347.52 | 0 | 0 | 0 | 3347.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304979700 |  | 100316304 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | PICADOME | 403 PICADOME PR | 067 | LEX | 2025-03-17 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-03-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2538.41 | 0 | 0 | 0 | 2538.41 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304979800 |  | 100316305 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | PICADOME | 405 PICADOME PR | 067 | LEX | 2025-03-17 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-03-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2591.01 | 0 | 0 | 0 | 2591.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304979900 |  | 100316306 |  | 6716208B | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | PICADOME | 407 PICADOME PR | 067 | LEX | 2025-03-17 | U127414 | U132386 | 2025-01-08 | 2025-12-19 |  |  | EDWARD FOX | 2025-03-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3236.54 | 0 | 0 | 0 | 3236.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304980000 |  | 100316307 |  | 6716208B | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | PICADOME | 409 PICADOME PR | 067 | LEX | 2025-03-17 | U127414 | U132386 | 2025-01-08 | 2025-12-19 |  |  | EDWARD FOX | 2025-03-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2546.3 | 0 | 0 | 0 | 2546.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304980100 |  | 100316308 |  | 6716208B | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | PICADOME | 411 PICADOME PR | 067 | LEX | 2025-03-21 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-03-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3016.02 | 0 | 0 | 0 | 3016.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304980200 |  | 100316333 |  | 6716208B | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | PICADOME | 415 PICADOME PR | 067 | LEX | 2025-03-10 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-03-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4215.09 | 0 | 0 | 0 | 4215.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304980400 |  | 100316335 |  | 6716208B | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | PICADOME | 419 PICADOME PR | 067 | LEX | 2025-03-13 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-03-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4973.57 | 0 | 0 | 0 | 4973.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304980500 |  | 100316336 |  | 6716208B | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | PICADOME | 421 PICADOME PR | 067 | LEX | 2025-03-14 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-03-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2208.08 | 0 | 0 | 0 | 2208.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304983100 |  | 100316140 |  | 6716208B | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | REED | 206 REED LN | 067 | LEX | 2025-06-19 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-06-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1
KY | KY - WEST | 2621 | 25304983200 |  | 100316139 |  | 6716208B | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | REED | 210 REED LN | 067 | LEX | 2025-06-18 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-06-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1
KY | KY - WEST | 2621 | 25304983300 |  | 100316137 |  | 6716208B | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | REED | 212 REED LN | 067 | LEX | 2025-06-17 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-06-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1
KY | KY - WEST | 2621 | 25304983400 |  | 100316134 |  | 6716208B | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | REED | 222 REED LN | 067 | LEX | 2025-06-19 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-06-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1
KY | KY - WEST | 2621 | 25304983700 |  | 100316130 |  | 6716208B | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | REED | 238 REED LN | 067 | LEX | 2025-06-18 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-06-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1
KY | KY - WEST | 2621 | 25304990400 |  | 100316287 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | SOUTHPORT | 101 SOUTHPORT DR | 067 | LEX | 2025-03-20 | U127414 | U132386 | 2025-01-08 | 2025-12-19 |  |  | EDWARD FOX | 2025-03-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3447.46 | 0 | 0 | 0 | 3447.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304990500 |  | 100316241 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | SOUTHPORT | 102 SOUTHPORT DR | 067 | LEX | 2025-03-19 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-03-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3225.75 | 0 | 0 | 0 | 3225.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304990600 |  | 100316286 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | SOUTHPORT | 103 SOUTHPORT DR | 067 | LEX | 2025-03-26 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-03-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3729.04 | 0 | 0 | 0 | 3729.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304990700 |  | 100316242 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | SOUTHPORT | 104 SOUTHPORT DR | 067 | LEX | 2025-03-19 | U127414 | U132386 | 2025-01-08 | 2025-12-19 |  |  | EDWARD FOX | 2025-03-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3334.37 | 0 | 0 | 0 | 3334.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304990800 |  | 100316243 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | SOUTHPORT | 106 SOUTHPORT DR | 067 | LEX | 2025-03-19 | U127414 | U132386 | 2025-01-08 | 2025-12-19 |  |  | EDWARD FOX | 2025-03-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4030.14 | 0 | 0 | 0 | 4030.14 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304990900 |  | 100316245 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | SOUTHPORT | 107 SOUTHPORT DR | 067 | LEX | 2025-03-19 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-03-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2614.68 | 0 | 0 | 0 | 2614.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304991000 |  | 100316244 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | SOUTHPORT | 108 SOUTHPORT DR | 067 | LEX | 2025-03-27 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-03-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4013.58 | 0 | 0 | 0 | 4013.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304991100 |  | 100316257 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | SOUTHPORT | 202 SOUTHPORT DR | 067 | LEX | 2025-06-12 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-06-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3606.71 | 0 | 0 | 0 | 3606.71 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304991200 |  | 100316284 |  | 6716208B | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | SOUTHPORT | 203 SOUTHPORT DR | 067 | LEX | 2025-06-05 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-06-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2320.34 | 0 | 0 | 0 | 2320.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304991400 |  | 100316282 |  | 6716208B | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | SOUTHPORT | 211 SOUTHPORT DR | 067 | LEX | 2025-06-06 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-06-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2374.71 | 0 | 0 | 0 | 2374.71 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304991500 |  | 100316281 |  | 6716208B | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | SOUTHPORT | 215 SOUTHPORT DR | 067 | LEX | 2025-06-05 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-06-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2772.08 | 0 | 0 | 0 | 2772.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304993500 |  | 100316297 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | VISTA | 110 VISTA ST | 067 | LEX | 2025-03-14 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-03-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2975.42 | 0 | 0 | 0 | 2975.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304993800 |  | 100316300 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | VISTA | 114 VISTA ST | 067 | LEX | 2025-03-13 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-03-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3769.83 | 0 | 0 | 0 | 3769.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304993900 |  | 100316301 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | VISTA | 116 VISTA ST | 067 | LEX | 2025-03-10 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-03-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4024.61 | 0 | 0 | 0 | 4024.61 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304994000 |  | 100316337 |  | 6716208B | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | VISTA | 117 VISTA ST | 067 | LEX | 2025-03-11 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-03-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4189.92 | 0 | 0 | 0 | 4189.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25304994100 |  | 100316302 |  | 6716208B | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | VISTA | 118 VISTA ST | 067 | LEX | 2025-03-13 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-03-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4963.79 | 0 | 0 | 0 | 4963.79 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25305001300 |  | 501361898 |  | 6712228L | 2292762 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | BILL PERKINS | 144 BILL PERKINS LN LT116C | 209 | GEO | 2025-01-23 | U126284 | U129294 | 2025-01-08 | 2025-01-10 | 2025-01-23 |  | JOSH PASLEY | 2025-01-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 10 | 1 | 3299.18 | 669.92 | 0 | 519.17 | 2110.09 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25305002100 |  | 501361897 |  | 6712228L | 2292762 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | BILL PERKINS | 142 BILL PERKINS LN LT117 | 209 | GEO | 2025-01-23 | U123111 | U129294 | 2025-01-08 | 2025-01-10 | 2025-01-23 |  | LYN STAFFORD | 2025-01-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 3249.07 | 516.74 | 255.11 | 33.99 | 2443.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25305004000 |  | 100316247 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | PICADOME | 300 PICADOME PR | 067 | LEX | 2025-03-25 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-03-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4691.51 | 0 | 0 | 0 | 4691.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25305004600 |  | 100316255 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | PICADOME | 307 PICADOME PR | 067 | LEX | 2025-04-08 | U129673 | U132386 | 2025-01-08 | 2025-12-19 |  |  | A WILLIAMSON | 2025-04-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 4873.56 | 514.41 | 0 | 556.48 | 3802.67 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25305005500 |  | 100316334 |  | 6716208B | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | PICADOME | 417 PICADOME PR | 067 | LEX | 2025-03-07 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-03-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3662.58 | 0 | 0 | 0 | 3662.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25305012200 |  | 100316135 |  | 6716208B | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | REED | 218 REED LN | 067 | LEX | 2025-06-17 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-06-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1
KY | KY - WEST | 2621 | 25305013200 |  | 100316131 |  | 6716208B | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | REED | 234 REED LN | 067 | LEX | 2025-06-16 | U126532 | U132386 | 2025-01-08 | 2025-12-19 |  |  | LESLIE SHARON | 2025-06-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 13282.87 | 0 | 0 | 0 | 13282.87 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25305015500 |  | 501371446 |  | 6716212O | 2410916 |  |  | 563 | EX | 1"PMMP SERVICE LINE/NO PRMT RE | 2600B | TRANSCRIPT | 110 TRANSCRIPT AV PARK 8 | 067 | LEX | 2025-01-25 | U126602 | U134341 | 2025-01-08 | 2025-01-10 | 2025-01-23 |  | DEREK PAYTON | 2025-01-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2672.98 | 502.65 | 654.57 | 33.06 | 1482.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305161100 |  | 100352028 |  | 6744208F | 1211049 |  |  | 565 | EX | REPLACE SL | 2621P | WINCHESTER | 6 WINCHESTER PZ E | 049 | WIN | 2025-01-14 | U124604 | U143023 | 2025-01-09 | 2025-01-09 |  |  | HSTANFI | 2025-01-13 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26290031 | 5.1 | 2 | 930.98 | 288.05 | 575.12 | 18.97 | 48.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25305175300 |  | 100316288 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | ROSEMONT | 401 ROSEMONT GN | 067 | LEX | 2025-04-01 | U126532 | U132386 | 2025-01-09 | 2025-12-19 |  |  | LESLIE SHARON | 2025-04-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3297.66 | 0 | 0 | 0 | 3297.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25305175900 |  | 100316285 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | SOUTHPORT | 105 SOUTHPORT DR | 067 | LEX | 2025-03-19 | U126532 | U132386 | 2025-01-09 | 2025-12-19 |  |  | LESLIE SHARON | 2025-03-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3721.01 | 0 | 0 | 0 | 3721.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25305177200 |  | 100316339 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | VISTA | 113 VISTA ST | 067 | LEX | 2025-03-12 | U126532 | U132386 | 2025-01-09 | 2025-12-19 |  |  | LESLIE SHARON | 2025-03-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3334.37 | 0 | 0 | 0 | 3334.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25305177500 |  | 100316338 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/22026237100 | 2600B | VISTA | 115 VISTA ST | 067 | LEX | 2025-03-12 | U126532 | U132386 | 2025-01-09 | 2025-12-19 |  |  | LESLIE SHARON | 2025-03-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3803.18 | 0 | 0 | 0 | 3803.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25305183500 |  | 100312037 |  | 6716208I |  |  |  | 565 | EX | MTR MOVE OUT / RELO | 2621P | CLEARVIEW | 243 CLEARVIEW DR | 067 | LEX | 2025-01-24 | U124604 | U124604 | 2025-01-09 | 2025-01-31 |  |  | JOCHOA | 2025-01-23 | 2025-01-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 27.4667 | 5 | 1985.18 | 1506.62 | 326.19 | 99.09 | 53.28 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25305189900 |  | 100254516 |  | 7348264O |  |  |  | 565 | EX | REPL/REPAIR SERVICE LINE | 2621P | WASHINGTON | 918 WASHINGTON ST | 089 | FLA | 2025-01-10 | ABHATFIE | U123688 | 2025-01-09 | 2022-12-30 |  |  | ABHATFIE | 2025-01-10 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 1.6833 | 2 | 299.8 | 170.14 | 0 | 11.26 | 118.4 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305225100 |  | 501375135 |  | 7244216B |  |  |  | 563 | EX | 1" P SHORT | 2621P | OWINGSVILLE | 1840 OWINGSVILLE RD | 173 | MT | 2025-01-29 | DENNING | U133050 | 2025-01-09 | 2025-01-23 | 2025-01-23 |  | DENNING | 2025-01-29 | 2025-01-17 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 28.8667 | 11 | 5238.22 | 2135.3 | 1252.21 | 772.99 | 1077.72 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305235000 |  | 100350513 |  | 6744204D |  |  |  | 565 | EX | REPAIR SL | 2621P | BOONE | 323 BOONE AV R | 049 | WIN | 2025-01-10 | NRICHIE | U143023 | 2025-01-09 | 2025-01-09 |  |  | NRICHIE | 2025-01-10 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 77.3 | 9 | 5095.03 | 2979.58 | 514.88 | 196.07 | 1404.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25305244500 |  | 500871749 |  | 6716232E | 0251093 |  |  | 563 | EX | 1" P SHORT/PRMT RCVD | 2600B | LOCH LOMOND | 105 LOCH LOMOND DR | 209 | GEO | 2025-02-03 | U126602 | U134341 | 2025-01-09 | 2025-01-20 | 2025-01-31 |  | DEREK PAYTON | 2025-01-31 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 2394.53 | 0 | 261.82 | 0 | 2132.71 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305357700 |  | 100352031 |  | 6744208L | 1313371 |  |  | 565 | EX | SERVICE LINE REPLACEMENT | 2621P | LEXINGTON | 1515 W LEXINGTON AV C | 049 | WIN | 2025-01-10 | DENNING | U134902 | 2025-01-10 | 2025-01-10 |  |  | DENNING | 2025-01-10 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 63.67 | 29.2 | 0 | 1.91 | 32.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25305369700 |  | 501334685 |  | 6716216E | 2290521 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | CALENDULA | 2313 CALENDULA RD | 067 | LEX | 2025-01-17 | U126285 | U126856 | 2025-01-10 | 2025-01-13 | 2025-01-24 |  | DUSTIN DAVIS | 2025-01-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2492.86 | 521.46 | 0 | 414.39 | 1557.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25305370600 |  | 501348621 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | CALISTA FLAT | 748 CALISTA FLAT | 067 | LEX | 2025-01-24 | U126285 | U126856 | 2025-01-10 | 2025-01-13 | 2025-01-24 |  | DUSTIN DAVIS | 2025-01-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 14 | 1 | 5154.42 | 912.53 | 249.43 | 60.05 | 3932.41 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25305381400 |  | 100287442 |  | 6720212G |  |  |  | 565 | EX | REPAIR SERVICE LINE | 2621P | MEADOW | 1017 MEADOW LN | 067 | LEX | 2025-01-13 | U124604 | U139701 | 2025-01-10 | 2025-01-10 |  |  | LSTANFI | 2025-01-10 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 42.35 | 7 | 3180.78 | 2395.96 | 195.16 | 530.46 | 59.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305400400 |  | 501351304 |  | 6736228K | 2398765 |  |  | 563 | EX | TAP W/ MAIN JO # 24-0263649-00 | 2600B | LINZI | 100 LINZI WY | 017 | PAR | 2025-02-27 | U461309 | U127708 | 2025-01-10 | 2025-04-10 | 2025-04-10 |  | RANDALL HUMPHREYS | 2025-02-27 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBTWM |  | 100 | 056332B26290012 | 8 | 1 | 5550.69 | 665.5 | 261.82 | 500.52 | 4122.85 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25305404200 |  | 501334654 |  | 6716216E | 2289300 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | GERANIUM | 2305 GERANIUM LN | 067 | LEX | 2025-01-17 | U123111 | U126856 | 2025-01-10 | 2025-01-13 | 2025-01-24 |  | LYN STAFFORD | 2025-01-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 1921.01 | 489.46 | 254.87 | 32.2 | 1144.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25305405800 |  | 100337684 |  | 6720212E |  |  |  | 565 | EX | REPAIR SERVICE LINE | 2621P | MAPLE | 627 MAPLE AV | 067 | LEX | 2025-01-27 | U123688 | U139701 | 2025-01-10 | 2025-07-09 | 2027-01-31 |  | ABLAKE | 2025-01-15 | 2025-01-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 53.1667 | 6 | 7819.95 | 2837.02 | 518.11 | 186.62 | 4278.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25305412600 |  | 100422273 |  | 6720208M |  |  |  | 566 | EX | PAPER ABANDON | 2621P | MOUNDVIEW | 3387 MOUNDVIEW CT 1FL | 067 | LEX | 2025-01-10 | U930915 | U124604 | 2025-01-10 | 2025-12-31 |  |  | OFFICE | 2025-01-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2623 | 25305432800 |  | 501258097 |  | 6700208A | 1856404 |  |  | 563 | EX | 1"P LONG BALL HOMES | 2600B | PRAIRIE ROSE | 5004 PRAIRIE ROSE WY | 239 | VER | 2025-01-28 | U128816 | U128272 | 2025-01-10 | 2025-01-13 | 2025-01-24 |  | OLIVER MAYNARD | 2025-01-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 4847.23 | 516.02 | 0 | 33.95 | 4297.26 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25305471200 |  | 100258717 |  | 7356256 |  |  |  | 563 | EX | PAPER W/100258718 | 2621P | MONTGOMERY | 2517< MONTGOMERY AV | 019 | ASH | 2025-01-13 | U123688 | U128727 | 2025-01-10 | 2025-01-13 | 2025-01-13 |  | OFFICE | 2025-01-13 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26310011 |  | 1
KY | KY - EAST | 2631 | 25305642900 |  | 100257357 |  | 7356256F | 2410099 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621P | 29TH | 1123 29TH ST | 019 | ASH | 2025-03-19 | MCOLLET | U123688 | 2025-01-13 | 2020-12-04 | 2021-12-31 |  | MCOLLET | 2025-03-19 | 2025-03-17 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26310031 | 20.4833 | 6 | 6085.79 | 1577.44 | 190.28 | 2325.67 | 1992.4 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305652400 |  | 100352030 |  | 6744208E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | WINCHESTER | 8 WINCHESTER PZ F | 049 | WIN | 2025-01-13 | HSTANFI | U137167 | 2025-01-13 | 2025-01-13 |  |  | HSTANFI | 2025-01-13 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26290031 | 0.46667 | 2 | 54.34 | 25.99 | 0 | 1.71 | 26.64 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25305681800 |  | 100266965 |  | 7356260M | 2410099 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621P | 9TH | 224 9TH ST | 019 | ASH | 2025-04-28 | MCOLLET | U123688 | 2025-01-13 | 2021-01-08 | 2021-12-31 |  | MCOLLET | 2025-04-28 | 2025-03-20 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26310031 | 22.1167 | 5 | 7213.74 | 1491.19 | 389.11 | 2288.31 | 3045.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25305691400 |  | 100337177 |  | 6720212E |  |  |  | 563 | EX | 1.25" P SHORT/PRMT RCVD | 2600B | 6TH | 158 E 6TH ST | 067 | LEX | 2025-02-11 | U461516 | U138822 | 2025-01-13 | 2025-01-30 | 2025-02-12 |  | NEAL JOHNSON | 2025-02-10 |  | 2025-02-10 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 5.45 | 1 | 4120.99 | 400.81 | 762.02 | 18.79 | 2939.37 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25305695600 |  | 100268266 |  | 7356260M | 1534686 |  |  | 563 | EX | 2" P LONG | 2621P | WINCHESTER | 1001 WINCHESTER AV | 019 | ASH | 2025-02-03 | U124604 | U132627 | 2025-01-13 | 2025-01-14 | 2025-01-28 |  | ABHATFIE | 2025-01-31 | 2025-01-30 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 68.25 | 7 | 6927.4 | 5729.43 | 266.72 | 882.41 | 48.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25305859400 |  | 501372962 |  | 6716204G |  |  |  | 563 | EX | 1"P SHORT/PRMT RCVD | 2600B | CAMELOT | 3425 CAMELOT DR | 067 | LEX | 2025-02-07 | U123111 | U128272 | 2025-01-14 | 2025-01-30 | 2025-02-12 |  | LYN STAFFORD | 2025-02-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2503.71 | 606.42 | 256.33 | 28.4 | 1612.56 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25305969200 |  | 501365566 |  | 6696212P | 2292756 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | SAFFRON | 570 SAFFRON LN LT36 | 239 | VER | 2025-02-11 | U461516 | U129294 | 2025-01-15 | 2025-01-20 | 2025-01-31 |  | NEAL JOHNSON | 2025-01-30 |  | 2025-01-30 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 11.4833 | 2 | 4704.69 | 772.18 | 241.69 | 45.9 | 3644.92 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25305969400 |  | 501365567 |  | 6696212P | 2292756 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | SAFFRON | 574 SAFFRON LN LT37 | 239 | VER | 2025-02-11 | U461516 | U129294 | 2025-01-15 | 2025-01-20 | 2025-01-31 |  | NEAL JOHNSON | 2025-01-30 |  | 2025-01-30 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 3068.35 | 0 | 268.54 | 0 | 2799.81 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25305969700 |  | 501365562 |  | 6696212P | 2292756 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | SAFFRON | 554 SAFFRON LN LT32 | 239 | VER | 2025-02-11 | U461516 | U129294 | 2025-01-15 | 2025-01-20 | 2025-01-31 |  | NEAL JOHNSON | 2025-01-30 |  | 2025-01-30 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 3858.66 | 0 | 255.11 | 0 | 3603.55 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305973100 |  | 100420277 |  | 6736228D | 2300569 |  |  | 566 | EX | ABANDONSL/DOWNSTREAM | 2621P | MAIN | 2009 MAIN ST UP | 017 | PAR | 2025-05-22 | U126530 | U132386 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-05-21 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26290043 |  | 1
KY | KY - WEST | 2621 | 25305973800 |  | 100318531 |  | 6716204C |  |  |  | 565 | EX | SL REPAIR | 2621P | FLINTRIDGE | 3405 FLINTRIDGE CR | 067 | LEX | 2025-01-16 | U930915 | U143023 | 2025-01-15 | 2025-01-15 | 2025-01-15 |  | RJCRAWF | 2025-01-15 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 32.8833 | 5 | 2484 | 1810.42 | 436.06 | 119.12 | 118.4 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305976500 |  | 100360465 |  | 6736228D | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | MAIN | 2000 MAIN ST | 017 | PAR | 2025-06-09 | U126530 | U128445 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-06-09 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 8393.07 | 0 | 1642.15 | 0 | 6750.92 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305976600 |  | 500669608 |  | 6736228D | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | MAIN | 2000< MAIN ST | 017 | PAR | 2025-06-05 | U126530 | U128445 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-06-05 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3773.61 | 0 | 0 | 0 | 3773.61 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305976700 |  | 100360482 |  | 6736228D | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | MAIN | 2001 MAIN ST | 017 | PAR | 2025-05-28 | U126530 | U128445 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-05-28 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2149.95 | 0 | 0 | 0 | 2149.95 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305976800 |  | 100360478 |  | 6736228D | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | MAIN | 2009 MAIN ST DN | 017 | PAR | 2025-05-22 | U126530 | U128445 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-05-21 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1592.08 | 0 | 0 | 0 | 1592.08 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305976900 |  | 100360477 |  | 6736228D | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | MAIN | 2011 MAIN ST | 017 | PAR | 2025-05-19 | U126530 | U128445 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-05-19 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2525.48 | 0 | 0 | 0 | 2525.48 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305977000 |  | 100360476 |  | 6736228D | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | MAIN | 2013 MAIN ST | 017 | PAR | 2025-05-22 | U126530 | U128445 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-05-22 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 5227.98 | 0 | 0 | 0 | 5227.98 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305977100 |  | 100360475 |  | 6736228D | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | MAIN | 2015< MAIN ST | 017 | PAR | 2025-05-28 | U126530 | U128445 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-05-22 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3635.9 | 0 | 0 | 0 | 3635.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305977200 |  | 100360473 |  | 6736228D | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | MAIN | 2017 MAIN ST | 017 | PAR | 2025-06-03 | U129673 | U128445 | 2025-01-15 | 2025-12-19 |  |  | A WILLIAMSON | 2025-06-03 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1805.28 | 0 | 0 | 0 | 1805.28 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305977300 |  | 100360472 |  | 6736228D | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | MAIN | 2021 MAIN ST | 017 | PAR | 2025-06-06 | U126530 | U128445 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-06-06 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4791.7 | 0 | 0 | 0 | 4791.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305977400 |  | 100360445 |  | 6736228G | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | RIDGEWAY | 6 RIDGEWAY DR | 017 | PAR | 2025-04-14 | U126530 | U128445 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-04-14 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2440.46 | 0 | 0 | 0 | 2440.46 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305977500 |  | 100360447 |  | 6736228G | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | RIDGEWAY | 7 RIDGEWAY DR | 017 | PAR | 2025-04-18 | U126530 | U128445 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-04-18 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4969.58 | 0 | 0 | 0 | 4969.58 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305977600 |  | 100409183 |  | 6736228G | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | RIDGEWAY | 9 RIDGEWAY DR | 017 | PAR | 2025-03-27 | U126530 | U128445 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-03-27 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1969.17 | 0 | 0 | 0 | 1969.17 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305977700 |  | 500229043 |  | 6736228G | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | RIDGEWAY | 10 RIDGEWAY DR | 017 | PAR | 2025-03-28 | U126530 | U128445 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-03-28 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1924.77 | 0 | 0 | 0 | 1924.77 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305977800 |  | 100360448 |  | 6736228G | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | RIDGEWAY | 11 RIDGEWAY DR | 017 | PAR | 2025-04-02 | U126530 | U128445 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-04-02 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2365.45 | 0 | 0 | 0 | 2365.45 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305977900 |  | 100360444 |  | 6736228G | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | RIDGEWAY | 14 RIDGEWAY DR | 017 | PAR | 2025-03-31 | U126530 | U128445 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-03-31 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2923.52 | 0 | 0 | 0 | 2923.52 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305978000 |  | 100360449 |  | 6736228G | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | RIDGEWAY | 15 RIDGEWAY DR | 017 | PAR | 2025-04-01 | U126530 | U128445 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-04-01 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3455.58 | 0 | 0 | 0 | 3455.58 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305978100 |  | 100360433 |  | 6736228H | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | SUNSET | 2000 SUNSET DR | 017 | PAR | 2025-04-30 | U126530 | U128445 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-04-30 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2595.41 | 0 | 0 | 0 | 2595.41 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305978200 |  | 100360464 |  | 6736228H | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | SUNSET | 2003 SUNSET DR | 017 | PAR | 2025-04-30 | U126530 | U128445 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-04-30 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3386.33 | 0 | 0 | 0 | 3386.33 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305978300 |  | 100360463 |  | 6736228H | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | SUNSET | 2005 SUNSET DR | 017 | PAR | 2025-05-01 | U126530 | U128445 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-05-01 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3339.28 | 0 | 0 | 0 | 3339.28 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305978400 |  | 100360434 |  | 6736228H | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | SUNSET | 2006 SUNSET DR | 017 | PAR | 2025-04-30 | U126530 | U128445 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-04-30 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3609.95 | 0 | 0 | 0 | 3609.95 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305978500 |  | 100360436 |  | 6736228H | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | SUNSET | 2010 SUNSET DR | 017 | PAR | 2025-04-28 | U126530 | U128445 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-04-28 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3308.3 | 0 | 0 | 0 | 3308.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305978600 |  | 100360461 |  | 6736228H | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | SUNSET | 2011 SUNSET DR | 017 | PAR | 2025-04-23 | U126530 | U128445 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-04-23 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2601.08 | 0 | 0 | 0 | 2601.08 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305978700 |  | 100360437 |  | 6736228H | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | SUNSET | 2014 SUNSET DR | 017 | PAR | 2025-05-06 | U126530 | U128445 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-05-06 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4290.71 | 0 | 0 | 0 | 4290.71 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305978800 |  | 100360438 |  | 6736228H | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | SUNSET | 2018 SUNSET DR | 017 | PAR | 2025-04-29 | U126530 | U128445 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-04-29 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2615.53 | 0 | 0 | 0 | 2615.53 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305978900 |  | 100360451 |  | 6736228H | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | SUNSET | 2103 SUNSET DR | 017 | PAR | 2025-04-11 | U126530 | U128445 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-04-11 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4274.36 | 0 | 0 | 0 | 4274.36 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305979000 |  | 100360440 |  | 6736228H | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | SUNSET | 2108 SUNSET DR | 017 | PAR | 2025-04-22 | U126530 | U128445 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-04-22 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3871.98 | 0 | 0 | 0 | 3871.98 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305979100 |  | 100360450 |  | 6736228H | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | SUNSET | 2109 SUNSET DR | 017 | PAR | 2025-04-07 | U126530 | U128445 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-04-07 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2441.42 | 0 | 0 | 0 | 2441.42 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305979200 |  | 100360441 |  | 6736228H | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | SUNSET | 2112 SUNSET DR | 017 | PAR | 2025-04-09 | U126530 | U128445 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-04-09 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2690.16 | 0 | 0 | 0 | 2690.16 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305985900 |  | 100465782 |  | 6736228G | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | MAIN | 2050 MAIN ST | 017 | PAR | 2025-03-26 | U461322 | U132386 | 2025-01-15 | 2025-12-19 |  |  | STEVE CANOY | 2025-03-26 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 0.38333 | 1 | 1870.37 | 27.76 | 0 | 1.65 | 1840.96 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25305986200 |  | 100360462 |  | 6736228H | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | SUNSET | 2009 SUNSET DR | 017 | PAR | 2025-05-01 | U126530 | U132386 | 2025-01-15 | 2025-12-19 |  |  | JDUNN | 2025-05-01 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2092.09 | 0 | 0 | 0 | 2092.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25305989900 |  | 500855007 |  | 6716212L | 2405526 |  |  | 563 | EX | 99 2" P SHORT/PRMT RCVD | 2600B | MILL | 112 N MILL ST | 067 | LEX | 2025-02-25 | U123688 | U134375 | 2025-01-15 | 2025-01-30 | 2025-02-12 |  | LSTAFFO | 2025-02-21 | 2025-02-21 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 20 | 2 | 7661.49 | 1498.01 | 0 | 539.53 | 5623.95 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25305991800 |  | 501338364 |  | 6716232B | 2179247 |  |  | 563 | EX | 1"P LONG (BALL HOMES)2ND TRY | 2600B | DUNMORE | 109 DUNMORE LN LT196 | 209 | GEO | 2025-01-25 | U461322 | U126856 | 2025-01-15 | 2025-01-16 | 2025-01-29 |  | STEVE CANOY | 2025-01-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 7.9667 | 1 | 4802.33 | 540.27 | 0 | 35.54 | 4226.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25306007200 |  | 100460607 |  | 6720200A |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D341553 | 2621P | SARON | 4652 SARON DR | 067 | LEX | 2025-01-20 | U124604 | U124604 | 2025-01-15 | 2025-01-17 | 2025-02-05 |  | JOCHOA | 2025-01-17 | 2025-01-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 27.4667 | 4 | 1946.32 | 1502.35 | 269.68 | 98.81 | 75.48 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 25306008200 |  | 100353308 |  | 7256280K |  |  |  | 563 | EX | 1"P-SHORT | 2621P | 2ND | 346 W 2ND ST | 161 | MAY | 2025-01-29 | U124604 | U128727 | 2025-01-15 | 2025-01-16 | 2025-01-29 |  | SDADAMS | 2025-01-28 | 2025-01-28 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26320011 | 29.45 | 4 | 5410.41 | 1878.3 | 295.5 | 123.58 | 3113.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25306027600 |  | 100466961 |  | 6720216E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | SILVER PHEASAN | 1635 SILVER PHEASAN CR | 067 | LEX | 2025-01-20 | UIPBOT21 | U129939 | 2025-01-15 | 2025-01-18 | 2025-02-05 |  | MCRAIG | 2025-01-17 | 2025-01-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 27.6167 | 5 | 2211.79 | 1532.06 | 193.53 | 428.48 | 57.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25306132100 |  | 100329627 |  | 6720208D | 2403558 |  |  | 565 | EX | REPLACE SL/24026316701 | 2621P | SAINT ANN | 217 SAINT ANN DR | 067 | LEX | 2025-01-16 | U461322 | U132386 | 2025-01-16 | 2025-12-19 |  |  | STEVE CANOY | 2025-01-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.4167 | 1 | 2946.51 | 218.88 | 0 | 175.93 | 2551.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25306141100 |  | 100302612 |  | 6712212K | 1635077 |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2621P | BORDEAUX | 1376 BORDEAUX DR | 067 | LEX | 2025-01-16 | MCRAIG | U129939 | 2025-01-16 | 2025-01-16 |  |  | MCRAIG | 2025-01-16 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 3.0833 | 1 | 498.8 | 202.72 | 17.88 | 139.08 | 139.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25306145300 |  | 501373772 |  | 6692224A |  |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | CHENAULT | 955 CHENAULT RD C | 073 | FRA | 2025-01-31 | U126602 | U134341 | 2025-01-16 | 2025-01-20 | 2025-01-31 |  | DEREK PAYTON | 2025-01-31 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 7.6833 | 1 | 3877.54 | 510.78 | 551.2 | 33.59 | 2781.97 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25306178400 |  | 100286576 |  | 6768172F |  |  |  | 565 | EX | REPLACE SL | 2621P | POPLAR | 311 POPLAR ST | 065 | RAV | 2025-01-16 | DENNING | U143023 | 2025-01-16 | 2025-01-16 |  |  | DENNING | 2025-01-16 | 2025-01-16 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 5.4333 | 1 | 2581.31 | 1539.83 | 748.84 | 134.28 | 158.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25306199300 |  | 100440641 |  | 6720208I |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | CHINOE | 833 CHINOE RD | 067 | LEX | 2025-02-26 | RJCRAWF | U124604 | 2025-01-16 | 2025-12-31 |  |  | RJCRAWF | 2025-02-26 | 2025-02-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 45.85 | 7 | 11978.45 | 3102.84 | 0 | 145.32 | 8730.29 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25306305100 |  | 501375641 |  | 6676224K |  |  |  | 563 | EX | 1' P LONG/NO PRMT REQ | 2600B | BRIDGEPORT | 1289 BRIDGEPORT RD | 073 | FRA | 2025-02-03 | U126602 | U133050 | 2025-01-17 | 2025-01-20 | 2025-01-31 |  | DEREK PAYTON | 2025-01-31 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 5250.7 | 0 | 261.82 | 0 | 4988.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25306307600 |  | 501317397 |  | 6716236J | 2178365 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | FLAMINGO | 104 FLAMINGO CR | 209 | GEO | 2025-01-29 | U128816 | U126856 | 2025-01-17 | 2025-01-20 | 2025-01-31 |  | OLIVER MAYNARD | 2025-01-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 3.25 | 1 | 4076.8 | 208.35 | 0 | 13.69 | 3854.76 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25306313200 |  | 500187781 |  | 6684228M |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | KIMBERLY | 117 KIMBERLY DR | 073 | FRA | 2025-01-20 | U124604 | U141174 | 2025-01-17 | 2025-04-14 | 2026-10-31 |  | DCOLLIN | 2025-01-17 | 2024-12-05 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 | 56.95 | 7 | 10422.75 | 3847.39 | 230.52 | 335.89 | 6008.95 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25306380500 |  | 501371996 |  | 7352260A |  |  |  | 563 | EX | 99 1" P LONG | 2621P | CARDINAL | 412 CARDINAL RD | 089 | RUS | 2025-02-26 | U124604 | U120250 | 2025-01-17 | 2025-01-31 | 2025-02-14 |  | MCOLLET | 2025-02-25 | 2025-02-07 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 33.3667 | 6 | 5026.02 | 2965.95 | 217.47 | 1749.36 | 93.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25306524200 |  | 501346193 |  | 6728208I | 2396366 |  |  | 563 | EX | 1"P-SHORT/NO PRMT REQ | 2600B | STOLEN HORSE | STOLEN HORSE TC LT87 | 067 | LEX | 2025-02-04 | U461322 | U128727 | 2025-01-20 | 2025-01-22 | 2025-02-04 |  | STEVE CANOY | 2025-02-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 6.1667 | 1 | 2076.56 | 468.5 | 0 | 21.96 | 1586.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25306559900 |  | 501375774 |  | 6684224 |  |  |  | 563 | EX | 99-1"P-SHORT | 2600B | US 127 | 1303 US 127 SO STE 301 | 073 | FRA | 2025-02-04 | U123111 | U128727 | 2025-01-20 | 2025-02-04 | 2025-02-04 |  | LYN STAFFORD | 2025-02-04 | 2025-01-24 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 27.05 | 4 | 4163.78 | 1906.9 | 513.84 | 113.95 | 1629.09 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25306560100 |  | 501375920 |  | 6684224 |  |  |  | 563 | EX | MANIFOLD W/501375774 | 2600B | US 127 | 1303 US 127 SO RISER | 073 | FRA | 2025-02-05 | U125763 | U128727 | 2025-01-20 | 2025-02-04 | 2025-02-04 |  | OFFICE PER MANAGEMENT | 2025-02-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBPEX |  | 100 | 056332B26230012 |  | 1
KY | KY - CENTRAL | 2629 | 25306610400 |  | 500293611 |  | 7244216J |  |  |  | 563 | EX | 1" P SHORT | 2621P | OSBORNE | 2010 OSBORNE RD | 173 | MT | 2025-01-31 | DENNING | U138822 | 2025-01-20 | 2025-01-20 | 2025-02-03 |  | DENNING | 2025-01-31 | 2025-01-28 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 19.4667 | 7 | 2077.75 | 1465.34 | 125.25 | 399.84 | 87.32 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25306618700 |  | 100350538 |  | 6744204C |  |  |  | 563 | EX | 1"P LONG | 2600B | SOUTHERN | 103 SOUTHERN CT | 049 | WIN | 2025-02-03 | U126285 | U132253 | 2025-01-21 | 2025-01-22 | 2025-02-04 |  | DUSTIN DAVIS | 2025-02-03 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 8.5 | 1 | 6237.39 | 744.22 | 756.06 | 533.56 | 4203.55 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25306625200 |  | 500633864 |  | 7352256E | 2404470 |  |  | 565 | EX | RPLC SL/24026333201 | 2600B | WILSHIRE | 1915 WILSHIRE BV | 019 | ASH | 2025-01-28 | U124015 | U125763 | 2025-01-21 | 2025-12-31 |  |  | ORA SLONE | 2025-01-28 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 3489.53 | 537.67 | 0 | 192.12 | 2759.74 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25306625300 |  | 100261536 |  | 7356256E | 2404470 |  |  | 565 | EX | RPLC SL/24026333201 | 2600B | WILSHIRE | 1927 WILSHIRE BV | 019 | ASH | 2025-01-30 | U124015 | U125763 | 2025-01-21 | 2025-12-31 |  |  | ORA SLONE | 2025-01-30 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 3817.04 | 748.31 | 0 | 244.37 | 2824.36 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25306625400 |  | 100261534 |  | 7356256E | 2404470 |  |  | 565 | EX | RPLC SL/24026333201 | 2600B | WILSHIRE | 2000 WILSHIRE BV | 019 | ASH | 2025-01-29 | U128523 | U125763 | 2025-01-21 | 2025-12-31 |  |  | BRANDON ROBERTS | 2025-01-28 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 2383.78 | 522.44 | 0 | 212.51 | 1648.83 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25306625500 |  | 100261533 |  | 7356256E | 2404470 |  |  | 565 | EX | RPLC SL/24026333201 | 2600B | WILSHIRE | 2006 WILSHIRE BV | 019 | ASH | 2025-01-30 | U128523 | U125763 | 2025-01-21 | 2025-12-31 |  |  | BRANDON ROBERTS | 2025-01-30 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 2033.18 | 0 | 0 | 0 | 2033.18 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25306625600 |  | 100261538 |  | 7356256E | 2404470 |  |  | 565 | EX | RPLC SL/24026333201 | 2600B | WILSHIRE | 2007 WILSHIRE BV | 019 | ASH | 2025-01-29 | U128523 | U125763 | 2025-01-21 | 2025-12-31 |  |  | BRANDON ROBERTS | 2025-01-28 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 1926.88 | 0 | 0 | 0 | 1926.88 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25306625700 |  | 100261532 |  | 7356256E | 2404470 |  |  | 565 | EX | RPLC SL/24026333201 | 2600B | WILSHIRE | 2018 WILSHIRE BV | 019 | ASH | 2025-02-04 | U128523 | U125763 | 2025-01-21 | 2025-12-31 |  |  | BRANDON ROBERTS | 2025-02-04 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 1555.49 | 0 | 0 | 0 | 1555.49 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25306625800 |  | 100261531 |  | 7356256E | 2404470 |  |  | 565 | EX | RPLC SL/24026333201 | 2600B | WILSHIRE | 2024 WILSHIRE BV | 019 | ASH | 2025-02-03 | U124015 | U125763 | 2025-01-21 | 2025-12-31 |  |  | ORA SLONE | 2025-02-03 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 2774.1 | 0 | 0 | 0 | 2774.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25306626000 |  | 100261530 |  | 7356256E | 2404470 |  |  | 565 | EX | RPLC SL/24026333201 | 2600B | WILSHIRE | 2036 WILSHIRE BV | 019 | ASH | 2025-02-04 | U128523 | U125763 | 2025-01-21 | 2025-12-31 |  |  | BRANDON ROBERTS | 2025-02-04 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 2041.76 | 0 | 0 | 0 | 2041.76 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25306626100 |  | 100261535 |  | 7352256E | 2404470 |  |  | 565 | EX | RPLC SL/24026333201 | 2600B | WILSHIRE | 1923 WILSHIRE BV | 019 | ASH | 2025-01-29 | U124015 | U125763 | 2025-01-21 | 2025-12-31 |  |  | ORA SLONE | 2025-01-29 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 3331.54 | 456.97 | 0 | 32.26 | 2842.31 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25306626200 |  | 100261537 |  | 7356256E | 2404470 |  |  | 565 | EX | RPLC SL/24026333201 | 2600B | WILSHIRE | 2001 WILSHIRE BV | 019 | ASH | 2025-01-30 | U128523 | U125763 | 2025-01-21 | 2025-12-31 |  |  | BRANDON ROBERTS | 2025-01-30 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 2629.05 | 26.81 | 0 | 23.59 | 2578.65 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25306647200 |  | 100275640 |  | 6684228F |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | KENTUCKY | 802 KENTUCKY AV | 073 | FRA | 2025-01-21 | CELKINS | U129939 | 2025-01-21 | 2025-01-21 |  |  | CELKINS | 2025-01-21 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 4.1 | 2 | 309.94 | 290.81 | 0 | 19.13 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25306656400 |  | 501359895 |  | 7348260C | 2403535 |  |  | 563 | EX | 1" P SHORT | 2621P | MCCOWAN | 804 MCCOWAN ST | 089 | FLA | 2025-02-12 | U124604 | U131378 | 2025-01-21 | 2025-01-28 | 2025-02-11 |  | RECUMP | 2025-02-11 | 2025-01-31 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 26.75 | 6 | 2849.71 | 2088.45 | 228.27 | 408.67 | 124.32 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25306815800 |  | 501338330 |  | 6716232B | 2179247 |  |  | 563 | EX | 1" P SHORT BALL HOMES | 2600B | DUNMORE | 165 DUNMORE LN LT172 | 209 | GEO | 2025-02-05 | U461322 | U132256 | 2025-01-22 | 2025-01-23 | 2025-02-05 |  | STEVE CANOY | 2025-02-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4.1 | 1 | 1693.59 | 313.01 | 0 | 255.21 | 1125.37 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25306848000 |  | 100284612 |  | 6748180H |  |  |  | 566 | EX | ABANDON SL IDLE/INACTIVE | 2621P | COLLEGE HILL | 337 COLLEGE HILL RD | 151 | WAC | 2025-02-06 | U124604 | U137009 | 2025-01-22 | 2025-02-07 | 2025-02-22 |  | DENNING | 2025-02-05 | 2025-02-05 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 13.6833 | 3 | 2965.57 | 1260.12 | 94.22 | 59.06 | 1552.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25306889300 |  | 100329349 |  | 6720208G | 2403558 |  |  | 565 | EX | REPLACE SL/24026316701 | 2621P | SAINT PHILLIP | 194 SAINT PHILLIP DR | 067 | LEX | 2025-01-30 | U461322 | U132386 | 2025-01-22 | 2025-12-19 |  |  | STEVE CANOY | 2025-01-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.2667 | 1 | 4045.66 | 594.16 | 0 | 477.59 | 2973.91 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25306904700 |  | 100351185 |  | 6744208P |  |  |  | 565 | EX | GR1 LEAK S/L | 2621P | BOONE | 23 BOONE AV 2F | 049 | WIN | 2025-01-24 | NRICHIE | U131366 | 2025-01-22 | 2025-01-22 | 2025-01-22 |  | NRICHIE | 2025-01-24 | 2025-01-22 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26290021 | 34.9333 | 6 | 3070.78 | 2224.41 | 619.32 | 145.65 | 81.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25307017300 |  | 500673682 |  | 6716208N | 9935847 |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | NICHOLASVILLE | 2601< NICHOLASVILLE RD SUITE 1 | 067 | LEX | 2025-02-06 | U123688 | U140273 | 2025-01-23 | 2025-02-13 | 2025-03-06 |  | RSTRONG | 2025-02-04 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.4333 | 0 | 660.49 | 598.94 | 23.63 | 37.92 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25307027400 |  | 100317192 |  | 6716208N |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | NICHOLASVILLE | 2601 NICHOLASVILLE RD SUITE 2 | 067 | LEX | 2025-02-05 | U930915 | U140273 | 2025-01-23 | 2025-02-13 | 2025-03-06 |  | RSTRONG | 2025-02-04 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.5167 | 1 | 680.3 | 497.36 | 23.63 | 159.31 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25307069600 |  | 501376023 |  | 6728081I |  |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | STOLEN HORSE | 3477 STOLEN HORSE TC LT 88 | 067 | LEX | 2025-02-04 | U461322 | U129294 | 2025-01-23 | 2025-01-27 | 2025-02-07 |  | STEVE CANOY | 2025-02-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 1.8333 | 1 | 1748.35 | 140.96 | 0 | 6.59 | 1600.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25307079500 |  | 501346176 |  | 6728208I | 2396366 |  |  | 563 | EX | 99 1" P LONG ARTISAN | 2600B | STOLEN HORSE | 3504 STOLEN HORSE TC LT71 | 067 | LEX | 2025-02-03 | U128816 | U134375 | 2025-01-23 | 2025-01-27 | 2025-02-07 |  | OLIVER MAYNARD | 2025-02-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4432.63 | 596.19 | 0 | 27.92 | 3808.52 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25307080400 |  | 100250993 |  | 7348264H |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | PERRY | 424 PERRY ST | 089 | GRE | 2025-02-14 | RECUMP | U140273 | 2025-01-23 | 2025-02-13 | 2025-03-06 |  | RECUMP | 2025-02-14 | 2025-01-31 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 20.9833 | 6 | 4003.57 | 1603.01 | 20.28 | 387.88 | 1992.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25307081900 |  | 501347909 |  | 6724204A | 2291616 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | NIGHT HERON | 3413 NIGHT HERON WY | 067 | LEX | 2025-02-03 | U123111 | U126856 | 2025-01-23 | 2025-01-27 | 2025-02-07 |  | LYN STAFFORD | 2025-02-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 2178.58 | 303.21 | 261.82 | 14.22 | 1599.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25307082300 |  | 501333744 |  | 6724204A | 2185117 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | SQUIRES | 227 SQUIRES CR | 067 | LEX | 2025-02-05 | U461322 | U126856 | 2025-01-23 | 2025-01-27 | 2025-02-07 |  | STEVE CANOY | 2025-02-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 3.1333 | 1 | 2401.42 | 237.67 | 0 | 194.18 | 1969.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25307082600 |  | 501347944 |  | 6724204A | 2291616 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | BAY SHOALS | 3425 BAY SHOALS DR | 067 | LEX | 2025-02-03 | U123111 | U126856 | 2025-01-23 | 2025-01-27 | 2025-02-07 |  | LYN STAFFORD | 2025-02-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 2180.05 | 303.21 | 261.82 | 14.22 | 1600.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25307082800 |  | 501358749 |  | 6700212O | 2398395 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | GLASBURY | 309 GLASBURY LN | 239 | VER | 2025-02-05 | U123111 | U126856 | 2025-01-23 | 2025-01-27 | 2025-02-07 |  | LYN STAFFORD | 2025-02-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 3373.67 | 607.71 | 248.4 | 28.46 | 2489.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25307083200 |  | 501358748 |  | 6700212O | 2398395 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | GLASBURY | 313 GLASBURY LN | 239 | VER | 2025-02-05 | U123111 | U126856 | 2025-01-23 | 2025-01-27 | 2025-02-07 |  | LYN STAFFORD | 2025-02-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 2845.42 | 0 | 261.82 | 0 | 2583.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25307090200 |  | 100351709 |  | 6744208O |  |  |  | 563 | EX | 1.25" LONG | 2600B | LEXINGTON | 636 W LEXINGTON AV | 049 | WIN | 2025-02-04 | U126285 | U128266 | 2025-01-23 | 2025-01-27 | 2025-02-07 |  | DUSTIN DAVIS | 2025-02-04 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 9 | 1 | 2788.08 | 788.01 | 161.28 | 564.95 | 1273.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25309490000 |  | 100313025 |  | 6716208E |  |  |  | 565 | EX | REPAIR SERVICE LINE | 2621P | MITCHELL | 566 MITCHELL AV | 067 | LEX | 2025-01-24 | JBURFOR | U139701 | 2025-01-24 | 2025-01-24 |  |  | JBURFOR | 2025-01-24 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.1833 | 1 | 307.4 | 127.35 | 0 | 8.37 | 171.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25309490900 |  | 100317189 |  | 6716208N |  |  |  | 565 | EX | REPAIR SERVICE LINE | 2621P | NICHOLASVILLE | 2467 NICHOLASVILLE RD STE 160 | 067 | LEX | 2025-02-03 | U123688 | U139701 | 2025-01-24 | 2025-01-24 |  |  | KKINDER | 2025-01-24 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0 | 1 | 10833.25 | 9583.99 | 0 | 1086.46 | 162.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25309500000 |  | 100292307 |  | 6720216O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LIN WAL | 436 LIN WAL RD | 067 | LEX | 2025-01-30 | U124604 | U124604 | 2025-01-24 | 2025-01-27 | 2025-02-14 |  | MCRAIG | 2025-01-29 | 2025-01-29 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16 | 2 | 2487.3 | 1448.99 | 469.59 | 468.08 | 100.64 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25312127000 |  | 100340858 |  | 6736192N |  |  |  | 565 | EX | REPLACE SL- LEAKAGE D304086 | 2621P | DANIEL | 514 DANIEL DR | 151 | RIC | 2025-02-04 | DENNING | U137009 | 2025-01-27 | 2025-01-27 | 2025-02-14 |  | DENNING | 2025-02-04 | 2025-02-04 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 12.2 | 3 | 2566.97 | 1136.75 | 665.93 | 637.01 | 127.28 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25312135000 |  | 100259835 |  | 7356256-B |  |  |  | 563 | EX | 1"P-LONG | 2621P | CENTRAL | 2123 CENTRAL AV | 019 | ASH | 2025-02-25 | U124604 | U128727 | 2025-01-27 | 2025-01-28 | 2025-02-10 |  | ABHATFIE | 2025-02-24 | 2025-01-31 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 31.1833 | 6 | 10625.1 | 2740.36 | 154.57 | 2398.25 | 5331.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25312138300 |  | 501375750 |  | 6716208M | 2511691 |  |  | 563 | EX | 1" P LONG/PRMT RCVD | 2600B | WESTERFIELD | 403 WESTERFIELD WY | 067 | LEX | 2025-02-24 | U461516 | U129531 | 2025-01-27 | 2025-02-11 | 2025-02-24 |  | NEAL JOHNSON | 2025-02-24 |  | 2025-02-24 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26210011 | 8 | 1 | 4628.45 | 588.38 | 227.05 | 496.91 | 3316.11 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25312176900 |  | 501362560 |  | 6712236C | 2410750 |  |  | 563 | EX | 2" P SHORT/NO PRMT REQ | 2600B | YUSEN | 331 E YUSEN DR | 209 | GEO | 2025-02-10 | U123111 | U126856 | 2025-01-27 | 2025-01-30 | 2025-02-12 |  | LYN STAFFORD | 2025-02-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 9 | 1 | 5384.43 | 683.7 | 258 | 32.01 | 4410.72 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25312177100 |  | 501020543 |  | 6700212I | 0780551 |  |  | 563 | EX | PAPER TAP W/500252463 | 2621P | MARSAILLES | 543 MARSAILLES RD | 239 | VER | 2025-01-30 | U124604 | U133050 | 2025-01-27 | 2025-02-10 | 2025-02-10 |  | OFFICE | 2025-01-30 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBMAN |  | 100 | 056332B26230011 |  | 1
KY | KY - WEST | 2621 | 25312298800 |  | 100308394 |  | 6716212N | 2511512 |  |  | 563 | EX | 50'-1 1/4"PMLP S/L-PRMT RCVD | 2600B | GIBSON | 511 GIBSON AV | 067 | LEX | 2025-02-26 | U126284 | U132253 | 2025-01-28 | 2025-02-11 | 2025-02-24 |  | JOSH PASLEY | 2025-02-26 | 2025-02-18 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 16.5167 | 2 | 7354.81 | 1333.57 | 0 | 766.56 | 5254.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25312300700 |  | 100456907 |  | 6716204H |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D512751 | 2621P | WATERWOOD | 3925 WATERWOOD TE | 067 | LEX | 2025-03-07 | U143504 | U124604 | 2025-01-28 | 2025-07-25 | 2027-01-31 |  | KKINDER | 2025-03-06 | 2025-02-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.7 | 3 | 1410.14 | 1112.3 | 218.58 | 79.26 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25312300900 |  | 100317494 |  | 6716204F |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D512752 | 2621P | WALHAMPTON | 3816 WALHAMPTON DR | 067 | LEX | 2025-04-17 | U124604 | U124604 | 2025-01-28 | 2025-07-25 | 2027-01-31 |  | MSHARON | 2025-04-16 | 2025-04-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.3833 | 5 | 1404.21 | 989.85 | 234.09 | 60.39 | 119.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25312317000 |  | 501159534 |  | 6720216P |  |  |  | 563 | EX | 1" P SHORT/PRMT RCVD | 2600B | TANGLEWOOD | 9 TANGLEWOOD DR | 067 | LEX | 2025-02-24 | U128336 | U129531 | 2025-01-28 | 2025-02-11 | 2025-02-24 |  | JOSHUA COX | 2025-02-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1773.93 | 0 | 602.42 | 0 | 1171.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25312324900 |  | 100304113 |  | 6712208D |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | VIOLET | 2124 VIOLET RD | 067 | LEX | 2025-02-28 | U124604 | U124604 | 2025-01-28 | 2025-02-28 |  |  | JOCHOA | 2025-02-27 | 2025-02-27 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 27.3833 | 2 | 6846.09 | 2216.56 | 390.73 | 103.87 | 4134.93 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25312329300 |  | 100286977 |  | 6720212F | 2293756 |  |  | 565 | EX | REPLACE SL/22026239700 | 2621P | CASTLEWOOD | 278 CASTLEWOOD DR | 067 | LEX | 2025-01-29 | U129722 | U132386 | 2025-01-28 | 2025-12-19 |  |  | DAVID YOUNG | 2025-01-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2844.91 | 0 | 0 | 0 | 2844.91 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25312340000 |  | 100269964 |  | 6732252P |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTRQD | 2621P | 3RD | 203 3RD ST | 097 | CYN | 2025-03-06 | NRICHIE | U140273 | 2025-01-28 | 2025-02-28 | 2025-03-02 |  | NRICHIE | 2025-03-06 | 2025-02-21 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 6.6667 | 4 | 890.48 | 512.26 | 100.65 | 29.23 | 248.34 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25312347200 |  | 501363516 |  | 7348252A | 2404834 |  |  | 563 | EX | 1"P LONG | 2621P | STATE RT 5 | 7138 STATE RT 5 | 019 | ASH | 2025-02-27 | U124604 | U132253 | 2025-01-28 | 2025-02-11 | 2025-02-25 |  | ABHATFIE | 2025-02-26 | 2025-02-26 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 33.75 | 3 | 10127.41 | 3017.07 | 202.46 | 2120.63 | 4787.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25312354400 |  | 100360007 |  | 6740232M | 1855043 |  |  | 566 | EX | ABANDON SL - SOII/MANIFOLD | 2621P | MAIN | 420 MAIN ST | 017 | PAR | 2025-03-07 | NRICHIE | U132554 | 2025-01-28 | 2025-04-10 | 2025-04-10 |  | NRICHIE | 2025-03-07 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.1667 | 2 | 261.36 | 246.9 | 0 | 14.46 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25312379200 |  | 100465671 |  | 6720208I | 2511842 |  |  | 563 | EX | 1"P-SHORT/PRMT RCVD | 2600B | STRAWBERRY | 1379 STRAWBERRY LN | 067 | LEX | 2025-02-24 | U123111 | U128727 | 2025-01-28 | 2025-02-11 | 2025-02-24 |  | LYN STAFFORD | 2025-02-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2041.96 | 606.42 | 209.17 | 28.4 | 1197.97 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25312481700 |  | 100326297 |  | 6720208A |  |  |  | 563 | EX | 1" P SHORT/PRMT RCVD | 2600B | HART | 407 HART RD | 067 | LEX | 2025-02-25 | U461516 | U132256 | 2025-01-29 | 2025-02-11 | 2025-02-24 |  | NEAL JOHNSON | 2025-02-25 |  | 2025-02-25 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4985.31 | 588.38 | 416.29 | 496.91 | 3483.73 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25312485200 |  | 100348133 |  | 6748208I |  |  |  | 563 | EX | 1" P SHORT | 2600B | MUTUAL | 215 MUTUAL AV | 049 | WIN | 2025-02-11 | U461516 | U132256 | 2025-01-29 | 2025-01-30 | 2025-02-12 |  | NEAL JOHNSON | 2025-01-07 |  | 2025-02-07 | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 |  | 1 | 1355.49 | 0 | 255.11 | 0 | 1100.38 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25312489600 |  | 100408536 |  | 7320280B |  |  |  | 565 | EX | GRADE 1 REPLACE SERVICE LINE | 2621P | BENNETT | 95 BENNETT ST | 135 | FIR | 2025-01-29 | RECUMP | U129939 | 2025-01-29 | 2025-01-29 | 2025-01-29 |  | RECUMP | 2025-01-29 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 15.15 | 3 | 1557.31 | 979.98 | 252.65 | 274.36 | 50.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25312592600 |  | 100309905 |  | 6712208H | 1318098 |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HARRODSBURG | 2356 HARRODSBURG RD | 067 | LEX | 2025-01-30 | U124604 | U131366 | 2025-01-29 | 2025-01-28 | 2025-01-28 |  | KKINDER | 2025-01-29 | 2025-01-29 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 77.5 | 11 | 14175.42 | 4962.07 | 678.01 | 381.18 | 8154.16 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25312627800 |  | 501224865 |  | 6700228K | 2511804 |  |  | 563 | EX | 20 1" P LONG HP/NO PRMT REQ | 2600B | ROCKY WATERS | 112 ROCKY WATERS WY LT9 | 209 | GEO | 2025-02-14 | U123111 | U120250 | 2025-01-30 | 2025-02-06 | 2025-02-19 |  | LYN STAFFORD | 2025-02-14 | 2025-02-13 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 12.5667 | 2 | 5605.42 | 943.03 | 261.82 | 44.19 | 4356.38 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25312629200 |  | 100407394 |  | 6748208K |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | ECTON | 740 ECTON RD | 049 | WIN | 2025-03-04 | NRICHIE | U140273 | 2025-01-30 | 2025-02-17 | 2025-03-10 |  | NRICHIE | 2025-03-04 | 2025-02-19 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 12 | 3 | 3180.55 | 903.05 | 39.7 | 52.42 | 2185.38 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25312632800 |  | 501317405 |  | 6716236J | 2178365 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | CHICKADEE | 139 CHICKADEE TR | 209 | GEO | 2025-02-06 | U461322 | U126856 | 2025-01-30 | 2025-01-31 | 2025-02-13 |  | STEVE CANOY | 2025-02-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26230011 | 8 | 1 | 2705.1 | 610.74 | 0 | 497.97 | 1596.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25312633700 |  | 100302886 |  | 6712208C |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D341330 | 2621P | WILLIAMSBURG | 2084 WILLIAMSBURG RD | 067 | LEX | 2025-02-28 | U124604 | U124604 | 2025-01-30 | 2025-07-29 | 2027-01-31 |  | JGILES | 2025-02-27 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24 | 3 | 2188.99 | 1554.07 | 394.21 | 240.71 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 25312639700 |  | 100259371 |  | 7344148I | 2397807 |  |  | 565 | EX | REPLACE SL/24026345800 | 2600B | KY RT 122 | 6940 KY RT 122 | 071 | DRI | 2025-03-31 | U128523 | U132386 | 2025-01-30 | 2025-12-19 |  |  | BRANDON ROBERTS | 2025-03-28 |  |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 |  | 1 | 1964.73 | 0 | 0 | 0 | 1964.73 | 0 | 0 | 0
KY | KY - EAST | 2633 | 25312639800 |  | 500085907 |  | 7344148I | 2397807 |  |  | 565 | EX | REPLACE SL/24026345800 | 2600B | REED | 36 REED ST | 071 | DRI | 2025-03-24 | U128523 | U132386 | 2025-01-30 | 2025-12-19 |  |  | BRANDON ROBERTS | 2025-03-24 |  |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 |  | 1 | 1440.61 | 0 | 0 | 0 | 1440.61 | 0 | 0 | 0
KY | KY - EAST | 2633 | 25312639900 |  | 100259369 |  | 7344148I | 2397807 |  |  | 565 | EX | REPLACE SL/24026345800 | 2600B | REED | 8 REED LN | 071 | DRI | 2025-04-02 | U128523 | U132386 | 2025-01-30 | 2025-12-19 |  |  | BRANDON ROBERTS | 2025-03-31 |  |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 |  | 1 | 4972.66 | 0 | 0 | 0 | 4972.66 | 0 | 0 | 0
KY | KY - EAST | 2633 | 25312655100 |  | 501375770 |  | 7364188H | 2511794 |  |  | 563 | EX | 1" P LONG | 2621P | BLACKLOG | 2347 BLACKLOG RD | 159 | INE | 2025-03-10 | JCKIRK | U128272 | 2025-01-30 | 2025-03-05 | 2025-03-05 |  | JCKIRK | 2025-03-10 | 2025-02-07 |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26330011 | 41.3167 | 6 | 7667.69 | 3101.43 | 182.32 | 177.78 | 4206.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25312658500 |  | 501348615 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | CALISTA FLAT | 709 CALISTA FLAT | 067 | LEX | 2025-02-06 | U461516 | U126856 | 2025-01-30 | 2025-01-31 | 2025-02-13 |  | NEAL JOHNSON | 2025-02-06 |  | 2025-02-06 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2592.64 | 588.38 | 365.62 | 27.55 | 1611.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25312658600 |  | 501348616 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | CALISTA FLAT | 705 CALISTA FLAT | 067 | LEX | 2025-02-06 | U123111 | U126856 | 2025-01-30 | 2025-01-31 | 2025-02-13 |  | LYN STAFFORD | 2025-02-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2591.58 | 606.42 | 358.9 | 28.4 | 1597.86 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25312710000 |  | 100244320 |  | 7356256P |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | GARTRELL | 529 GARTRELL ST | 019 | ASH | 2025-02-06 | U123688 | U129939 | 2025-01-30 | 2025-05-09 | 2026-11-30 |  | MCOLLET | 2025-01-30 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 2.9333 | 2 | 2617.73 | 1415.52 | 0 | 1160.77 | 41.44 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25312767500 |  | 501372636 |  | 6736228K | 2398765 |  |  | 563 | EX | TAP W/MAIN 24-0263649-00 | 2600B | LINZI | 118 LINZI WY | 017 | PAR | 2025-02-27 | U461309 | U127708 | 2025-01-31 | 2025-04-30 | 2025-04-30 |  | RANDALL HUMPHREYS | 2025-02-25 | 2025-02-25 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBTWM |  | 100 | 056332B26290012 | 4.5 | 1 | 3952.72 | 374.37 | 261.82 | 281.57 | 3034.96 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25312767800 |  | 501372638 |  | 6736228K | 2398765 |  |  | 563 | EX | TAP W/MAIN 24-0263649-00 | 2600B | LINZI | 120 LINZI WY | 017 | PAR | 2025-02-27 | U461309 | U127708 | 2025-01-31 | 2025-04-30 | 2025-04-30 |  | RANDALL HUMPHREYS | 2025-02-25 | 2025-02-25 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBTWM |  | 100 | 056332B26290012 | 3.5 | 1 | 3895.57 | 291.19 | 261.82 | 218.98 | 3123.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25312772400 |  | 100291163 |  | 6720216N |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D333398 | 2621P | NEW CIRCLE | 177 W NEW CIRCLE RD | 067 | LEX | 2025-05-09 | U124604 | U124604 | 2025-01-31 | 2025-07-30 | 2027-01-31 |  | TROE | 2025-05-08 | 2025-05-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 37.5333 | 8 | 3537.22 | 2313.52 | 389.72 | 133.98 | 700 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25312775500 |  | 100338107 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL IDLE/INACTIVE | 2621P | 7TH | 402 E 7TH ST | 067 | LEX | 2025-01-31 | LSTANFI | U139701 | 2025-01-31 | 2025-01-31 |  |  | LSTANFI | 2025-01-31 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 0.083333 | 1 | 7.61 | 5.61 | 0 | 2 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25312775900 |  | 100338109 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL IDLE/INACTIVE | 2621P | 7TH | 404 E 7TH ST | 067 | LEX | 2025-01-31 | LSTANFI | U139701 | 2025-01-31 | 2025-01-31 |  |  | LSTANFI | 2025-01-31 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 0.033333 | 1 | 2.85 | 2.1 | 0 | 0.75 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25312795600 |  | 100336023 |  | 6720212K |  |  |  | 566 | EX | SERVICE LINE ABANDON | 2621P | HIGHLAND | 903 HIGHLAND DR | 067 | LEX | 2025-02-28 | LSTANFI | U124604 | 2025-01-31 | 2025-02-28 |  |  | LSTANFI | 2025-02-28 | 2025-02-27 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 35.05 | 10 | 2674.14 | 2394.12 | 0 | 280.02 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25312819400 |  | 501375089 |  | 6764172B | 2511530 |  |  | 563 | EX | PAPER TAP | 2621P | WISEMANTOWN | 1517 WISEMANTOWN RD | 065 | IRV | 2025-02-03 | U137009 | U129176 | 2025-01-31 | 2025-01-31 | 2025-02-14 |  | OFFICE | 2025-02-03 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26290011 |  | 1
KY | KY - WEST | 2621 | 25312821000 |  | 501348623 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | CALISTA FLAT | 740 CALISTA FLAT | 067 | LEX | 2025-02-13 | U123111 | U126856 | 2025-01-31 | 2025-02-04 | 2025-02-17 |  | LYN STAFFORD | 2025-02-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4490.11 | 606.42 | 261.82 | 28.4 | 3593.47 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25312832900 |  | 100468096 |  | 6720208I | 1313369 |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | OLD MOUNT TABO | 260 OLD MOUNT TABO RD 13 | 067 | LEX | 2025-02-03 | HSTANFI | U141174 | 2025-01-31 | 2025-01-31 | 2025-01-31 |  | HSTANFI | 2025-02-03 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.9667 | 3 | 1964.75 | 1585.65 | 300.38 | 74.28 | 4.44 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25312918900 |  | 100350069 |  | 6744204D |  |  |  | 565 | EX | REPAIR/REPLACE SL | 2621P | MOUNDALE | 2 MOUNDALE AV | 049 | WIN | 2025-02-01 | DENNING | U139677 | 2025-02-01 | 2025-02-03 |  |  | DENNING | 2025-02-01 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26290031 |  | 1 | 544.62 | 0 | 230.86 | 0 | 313.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25312922200 |  | 500689347 |  | 6716212L | 9937556 |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LIMESTONE | 150 N LIMESTONE ST | 067 | LEX | 2025-02-03 | U123688 | U141174 | 2025-02-01 | 2025-01-23 | 2025-02-10 |  | RJCRAWF | 2025-02-01 | 2025-02-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 1.9667 | 5 | 5799.13 | 2013.55 | 391.31 | 168.21 | 3226.06 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25312934200 |  | 100292748 |  | 6720216K |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | LIN WAL | 561 LIN WAL RD | 067 | LEX | 2025-02-03 | U930915 | U132424 | 2025-02-02 | 2025-02-05 | 2025-02-23 |  | RSTRONG | 2025-02-03 | 2025-02-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 | KYACN |  | 100 | 056532B26210021 | 23.5667 | 3 | 1945.93 | 1588.31 | 115.29 | 242.33 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25312959400 |  | 100458840 |  | 6724208M |  |  |  | 563 | EX | 99 1" P SHORT/PRMT RCVD | 2600B | EAGLE CREEK | 195 S EAGLE CREEK DR | 067 | LEX | 2025-03-04 | U126284 | U134375 | 2025-02-03 | 2025-02-20 | 2025-03-05 |  | JOSH PASLEY | 2025-03-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 5.45 | 1 | 1977.93 | 403.57 | 0 | 369.04 | 1205.32 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25312986800 |  | 501375134 |  | 7352260O | 2511475 |  |  | 563 | EX | 1" P LONG | 2621P | MARCUM | 115 MARCUM ST | 019 | ASH | 2025-02-26 | U124604 | U134341 | 2025-02-03 | 2025-02-17 | 2025-02-17 |  | RECUMP | 2025-02-25 | 2025-02-25 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 16 | 2 | 1976.8 | 1258.03 | 348.13 | 370.64 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25312991200 |  | 100318478 |  | 6716204C |  |  |  | 566 | EX | PAPER ABANDON | 2621P | HIGHTOWER | 299 HIGHTOWER RD | 067 | LEX | 2025-02-03 | U123688 | U123688 | 2025-02-03 | 2025-12-31 |  |  | OFFICE | 2025-02-03 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - EAST | 2631 | 25312991800 |  | 501371782 |  | 7352256B | 2511673 |  |  | 563 | EX | 1" P LONG | 2621P | OHIO | 2820 OHIO ST | 019 | ASH | 2025-02-14 | U124604 | U130192 | 2025-02-03 | 2025-02-17 | 2025-02-17 |  | ABHATFIE | 2025-02-13 | 2025-02-07 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 37.45 | 6 | 4351.37 | 3180.3 | 323.06 | 848.01 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25313012500 |  | 501347917 |  | 6724204A | 2291616 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | NIGHT HERON | 3445 NIGHT HERON WY | 067 | LEX | 2025-02-12 | U461309 | U126856 | 2025-02-03 | 2025-02-06 | 2025-02-19 |  | RANDALL HUMPHREYS | 2025-02-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 5.6167 | 1 | 2146.57 | 414.08 | 261.82 | 349.71 | 1120.96 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25313013200 |  | 501319186 |  | 6740204H | 2177603 |  |  | 563 | EX | 1" P SHORT | 2600B | BELLA SHAE | 118 BELLA SHAE WY | 049 | WIN | 2025-02-12 | U123111 | U126856 | 2025-02-03 | 2025-02-06 | 2025-02-19 |  | LYN STAFFORD | 2025-02-12 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 8 | 1 | 2677.92 | 685.89 | 261.82 | 32.13 | 1698.08 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25313013300 |  | 501319193 |  | 6740204H | 2177603 |  |  | 563 | EX | 1" P SHORT | 2600B | BELLA SHAE | 102 BELLA SHAE WY | 049 | WIN | 2025-02-12 | U461516 | U126856 | 2025-02-03 | 2025-02-06 | 2025-02-19 |  | NEAL JOHNSON | 2025-02-12 |  | 2025-02-12 | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 8 | 1 | 3116.09 | 665.5 | 311.05 | 500.52 | 1639.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25313117800 |  | 500689006 |  | 6724208H | 9403236 |  |  | 566 | EX | SERVICE LINE ABANDON | 2621P | BRIGHTON PLACE | 3256 BRIGHTON PLACE DR | 067 | LEX | 2025-02-06 | U930915 | U124604 | 2025-02-04 | 2025-02-14 |  |  | ABLAKE | 2025-02-06 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.5333 | 2 | 505.31 | 482.69 | 0 | 22.62 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25313118700 |  | 100261410 |  | 7352256L |  |  |  | 563 | EX | 1.25" P LONG | 2621P | WOODLAWN | 3116 WOODLAWN AV | 019 | ASH | 2025-02-20 | U124604 | U138822 | 2025-02-04 | 2025-02-04 | 2025-02-20 |  | RECUMP | 2025-02-19 | 2025-02-18 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 22.1833 | 4 | 2491.98 | 1988.16 | 235.88 | 267.94 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25313120700 |  | 100313461 |  | 6716208B |  |  |  | 565 | EX | METER MOVE OUT/SL REPLACE | 2621P | BOB O LINK | 477 BOB O LINK DR | 067 | LEX | 2025-02-28 | KKINDER | U124604 | 2025-02-04 | 2025-03-28 |  |  | KKINDER | 2025-02-28 | 2025-02-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 49.3667 | 8 | 5796.68 | 3438.83 | 283.72 | 354.17 | 1719.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25313123800 |  | 501376770 |  | 6724204A | 2185117 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | NIGHT HERON | 3476 NIGHT HERON WY | 067 | LEX | 2025-02-13 | U461309 | U127708 | 2025-02-04 | 2025-02-06 | 2025-02-19 |  | RANDALL HUMPHREYS | 2025-02-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2473.95 | 588.38 | 261.82 | 496.91 | 1126.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25313124600 |  | 501359277 |  | 6736180C | 2402680 |  |  | 563 | EX | TAP W/MAIN 24-0263144-00 | 2600B | ROBERT MARTIN | 1414 ROBERT MARTIN | 151 | RIC | 2025-04-15 | U126284 | U127708 | 2025-02-04 | 2025-05-05 | 2025-05-05 |  | JOSH PASLEY | 2025-04-15 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBTWM |  | 100 | 056332B26290012 |  | 1 | 6532.37 | 0 | 0 | 0 | 6532.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25313136100 |  | 100465745 |  | 6712208J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LYON | 3430 LYON DR | 067 | LEX | 2025-03-05 | U123688 | U124604 | 2025-02-04 | 2025-08-01 | 2027-02-28 |  | JGILES | 2025-03-04 | 2025-02-21 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 31.7667 | 6 | 2466.84 | 1883.89 | 0 | 556.31 | 26.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25313145000 |  | 100286821 |  | 6720212B |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | DEVONIA | 120 DEVONIA AV | 067 | LEX | 2025-02-04 | TROE | U134822 | 2025-02-04 | 2025-02-04 |  |  | TROE | 2025-02-04 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 10.75 | 3 | 741.99 | 708.77 | 0 | 33.22 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25313160900 |  | 501356927 |  | 6712204E | 2397231 |  |  | 563 | EX | 20 1" P SHORT/NO PRMT REQ | 2600B | BELLERIVE | 803 BELLERIVE BV LT8 | 113 | NIC | 2025-02-17 | U123111 | U142144 | 2025-02-04 | 2025-02-06 | 2025-02-19 |  | LYN STAFFORD | 2025-02-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2096.08 | 606.42 | 261.82 | 28.4 | 1199.44 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25313184300 |  | 501278631 |  | 6716232J |  |  |  | 563 | EX | 1"P-LONG BALL HOMES | 2600B | SILVER SPRING | 126 SILVER SPRING WY LT349 | 209 | GEO | 2025-02-17 | U461516 | U128727 | 2025-02-04 | 2025-02-06 | 2025-02-19 |  | NEAL JOHNSON | 2025-02-17 |  | 2025-02-17 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 5944.24 | 589.62 | 249.05 | 496.96 | 4608.61 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25313184600 |  | 100330683 |  | 6720208B |  |  |  | 565 | EX | REPLACE SERVICE LINE - MMO | 2621P | SHERMAN | 124 SHERMAN AV | 067 | LEX | 2025-02-05 | U124604 | U134822 | 2025-02-04 | 2025-02-04 | 2025-02-04 |  | MCRAIG | 2025-02-04 | 2025-02-04 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.7333 | 5 | 2053.46 | 1456.22 | 335.96 | 261.28 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25313298900 |  | 100329662 |  | 6720208C | 2403558 |  |  | 565 | EX | REPLACE SL/24026316701 | 2600B | SAINT TERESA | 2012 SAINT TERESA DR | 067 | LEX | 2025-02-05 | U128816 | U132386 | 2025-02-05 | 2025-12-19 |  |  | OLIVER MAYNARD | 2025-02-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2282.83 | 0 | 0 | 0 | 2282.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25313304700 |  | 100289986 |  | 6720212C |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | NORTHWOOD | 328 NORTHWOOD DR | 067 | LEX | 2025-03-11 | HSTANFI | U124604 | 2025-02-05 | 2025-12-31 |  |  | HSTANFI | 2025-03-11 | 2025-03-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 29.5667 | 7 | 10603.66 | 1758.4 | 7196.69 | 136.69 | 1511.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25313320500 |  | 100468216 |  | 6720212G |  |  |  | 563 | EX | PAPER W/100464645 | 2600B | CONTRACT | 843 CONTRACT ST | 067 | LEX | 2025-02-17 | U939005 | U128727 | 2025-02-05 | 2025-02-17 | 2025-02-17 |  | OFFICE | 2025-02-17 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26210011 |  | 0
KY | KY - EAST | 2631 | 25313336300 |  | 501010006 |  | 7344248D | 0678301 |  |  | 566 | EX | ABANDON SL | 2621P | VIRGINIA | 12005< VIRGINIA BV B | 019 | ASH | 2025-02-07 | U124604 | U141867 | 2025-02-05 | 2025-02-05 |  |  | JCYRUS | 2025-02-06 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.9167 | 1 | 182.45 | 174.29 | 0 | 8.16 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25313336900 |  | 500834756 |  | 7344248D |  |  |  | 566 | EX | ABANDON SL | 2621P | VIRGINIA | 12005 VIRGINIA BV B | 019 | ASH | 2025-02-07 | U124604 | U141867 | 2025-02-05 | 2025-02-05 |  |  | JCYRUS | 2025-02-06 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.083333 | 1 | 7.7 | 7.34 | 0 | 0.36 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25313340900 |  | 100344921 |  | 6700224O |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | GRATZ | 129 S GRATZ ST | 239 | MID | 2025-02-06 | U124604 | U141867 | 2025-02-05 | 2025-02-05 |  |  | LSTANFI | 2025-02-05 | 2025-02-05 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 12.2 | 4 | 1332.8 | 860.85 | 431.63 | 40.32 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25313348700 |  | 100253713 |  | 7356216D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MADISON | 207 E MADISON ST 1F | 127 | LOU | 2025-02-06 | U124604 | U132424 | 2025-02-05 | 2025-02-05 | 2025-02-05 |  | MCOLLET | 2025-02-05 | 2025-02-05 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 17.8 | 3 | 6403.94 | 2866.53 | 195.02 | 608.42 | 2733.97 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25313471700 |  | 100342450 |  | 7240216N |  |  |  | 563 | EX | 1"P-LONG | 2621P | CLAY | 111 CLAY ST | 173 | MT | 2025-02-28 | DENNING | U128727 | 2025-02-06 | 2025-02-07 | 2025-02-27 |  | DENNING | 2025-02-28 | 2025-02-18 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 34.7333 | 7 | 5830.15 | 3201.27 | 510.39 | 1497.64 | 620.85 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25313504700 |  | 100280666 |  | 6688228E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BEAUMONT | 141 BEAUMONT AV | 073 | FRA | 2025-02-06 | BWHITE | U130871 | 2025-02-06 | 2025-04-29 | 2026-10-31 |  | BWHITE | 2025-02-06 | 2025-02-05 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 | 16.7333 | 6 | 3008.93 | 1285.94 | 0 | 591.19 | 1131.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25313514500 |  | 500828050 |  | W-1101/37 |  |  |  | 563 | EX | 1" P SHORT | 2600B | PRIMROSE | 318 PRIMROSE LN LT121 | 049 | WIN | 2025-02-20 | U461516 | U130192 | 2025-02-06 | 2025-02-11 | 2025-02-24 |  | NEAL JOHNSON | 2025-02-18 |  | 2025-02-18 | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 12.0167 | 2 | 4174.95 | 1000.78 | 261.82 | 516.23 | 2396.12 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25313519200 |  | 100267614 |  | 7352264N |  |  |  | 565 | EX | REPLACE SL | 2621P | RIVERVIEW | 1316 RIVERVIEW RD | 089 | RUS | 2025-03-03 | JROGER1 | U137009 | 2025-02-06 | 2025-04-04 | 2025-04-06 |  | JROGER1 | 2025-03-03 | 2025-03-03 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 20.5167 | 3 | 1831.76 | 1456.4 | 290.01 | 85.35 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25313519800 |  | 501377070 |  | 6716216A | 1748606 |  |  | 563 | EX | 1" P SHORT/PRMT RCVD | 2600B | LUCILLE | 603 LUCILLE DR | 067 | LEX | 2025-03-04 | U126284 | U127708 | 2025-02-06 | 2025-02-20 | 2025-03-05 |  | JOSH PASLEY | 2025-03-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 5.05 | 1 | 1885.96 | 373.98 | 0 | 341.94 | 1170.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25313519900 |  | 501377071 |  | 6716216A | 1748606 |  |  | 563 | EX | 1" P SHORT/PRMT RCVD | 2600B | LUCILLE | 597 LUCILLE DR | 067 | LEX | 2025-03-03 | U126602 | U127708 | 2025-02-06 | 2025-02-20 | 2025-03-05 |  | DEREK PAYTON | 2025-03-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 1994.85 | 549.02 | 261.82 | 32.18 | 1151.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25313520000 |  | 501377072 |  | 6716216A | 1748606 |  |  | 563 | EX | 1" P SHORT/PRMT RCVD | 2600B | LUCILLE | 589 LUCILLE DR | 067 | LEX | 2025-03-03 | U126602 | U127708 | 2025-02-06 | 2025-02-20 | 2025-03-05 |  | DEREK PAYTON | 2025-03-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1419.53 | 0 | 261.82 | 0 | 1157.71 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25313625400 |  | 100256118 |  | 7356256F |  |  |  | 565 | EX | REPAIR SERVICE LINE | 2621P | LYNNWOOD | 2614 LYNNWOOD AV | 019 | ASH | 2025-02-07 | MCOLLET | U139701 | 2025-02-07 | 2025-02-07 | 2025-02-07 |  | MCOLLET | 2025-02-07 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 12.2333 | 5 | 2769.98 | 1069.51 | 181.97 | 522.3 | 996.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25313657600 |  | 500453104 |  | 6720208N |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTREQ | 2621P | CHINOE | 1088 CHINOE RD | 067 | LEX | 2025-03-14 | JBURFOR | U140273 | 2025-02-07 | 2025-02-28 | 2025-03-21 |  | JBURFOR | 2025-03-14 | 2025-03-13 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 33.6167 | 5 | 3859.16 | 1882.69 | 39.7 | 110.39 | 1826.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25313675300 |  | 501373033 |  | 6712204G |  |  |  | 563 | EX | 1"P SHORT/PRMT RCVD | 2600B | HIGBEE MILL | 1072 HIGBEE MILL RD | 067 | LEX | 2025-02-28 | U129731 | U128266 | 2025-02-07 | 2025-02-20 | 2025-03-05 |  | EDWARD GOINS | 2025-02-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 2228.19 | 0 | 305.72 | 0 | 1922.47 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25313912500 |  | 100413838 |  | 6716204C |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D341950 | 2621P | ARGONNE | 267 ARGONNE CR A | 067 | LEX | 2025-02-26 | U124604 | U124604 | 2025-02-10 | 2025-02-11 | 2025-03-01 |  | RJCRAWF | 2025-02-25 | 2025-02-21 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19 | 6 | 1698.49 | 1242.14 | 398.17 | 58.18 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25313937400 |  | 100357835 |  | 6740228A |  |  |  | 563 | EX | 1" P SHORT | 2621P | VINE | 1013 VINE ST | 017 | PAR | 2025-02-27 | U124604 | U129531 | 2025-02-10 | 2025-02-10 | 2025-03-03 |  | NRICHIE | 2025-02-26 | 2025-02-19 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 15.3333 | 3 | 5430.77 | 1369.4 | 987.74 | 64.16 | 3009.47 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25313980700 |  | 501365165 |  | 6720208H |  |  |  | 563 | EX | PAPER MANIFOLD W/ 100453775 | 2600B | NEW CIRCLE | 1555 E NEW CIRCLE RD 158 | 067 | LEX | 2025-02-13 | U124604 | U129176 | 2025-02-10 | 2025-02-10 | 2025-02-24 |  | OFFICE | 2025-02-13 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26210011 |  | 1
KY | KY - WEST | 2621 | 25313988900 |  | 100291422 |  | 6720216H |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | KINGSTON | 608 KINGSTON RD | 067 | LEX | 2025-02-12 | U123688 | U137607 | 2025-02-10 | 2025-02-10 |  |  | TROE | 2025-02-11 | 2025-02-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 1.25 | 6 | 619.91 | 89.36 | 526.39 | 4.16 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25314090200 |  | 100279349 |  | 6688228K |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | RANDOLPH | 101 RANDOLPH RD | 073 | FRA | 2025-02-11 | KKINDER | U129939 | 2025-02-11 | 2025-02-11 |  |  | KKINDER | 2025-02-11 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.2167 | 1 | 254.77 | 94.31 | 156.03 | 4.43 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25314098500 |  | 100303184 |  | 6712208G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | AZALEA | 2224 AZALEA DR | 067 | LEX | 2025-02-27 | U124604 | U124604 | 2025-02-11 | 2025-04-30 | 2026-10-31 |  | MMALONE | 2025-02-06 | 2024-12-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 29 | 7 | 1836.99 | 1748.33 | 0 | 88.66 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25314100500 |  | 100279723 |  | 6688228O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | FLAMINGO | 554 FLAMINGO AV | 073 | FRA | 2025-02-12 | U124604 | U129939 | 2025-02-11 | 2025-05-06 | 2026-11-30 |  | DCOLLIN | 2025-02-11 | 2025-02-10 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 | 10.9167 | 4 | 3004.47 | 2439.18 | 233.42 | 331.87 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25314101200 |  | 501377197 |  | 6724208G |  |  |  | 563 | EX | PAPER W/500876364 | 2600B | SIR BARTON | 2321 SIR BARTON WY STE 115 | 067 | LEX | 2025-02-20 | U132386 | U127708 | 2025-02-11 | 2025-02-21 | 2025-03-06 |  | OFFICE | 2025-02-20 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26210011 |  | 0
KY | KY - WEST | 2621 | 25314117200 |  | 100315875 |  | 6716208F |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | ARCADIA | 538 ARCADIA PR | 067 | LEX | 2025-02-11 | KKINDER | U124604 | 2025-02-11 | 2025-02-28 |  |  | KKINDER | 2025-02-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.066667 | 1 | 5.74 | 5.49 | 0 | 0.25 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25314145400 |  | 501358724 |  | 6700212O | 2398395 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | WROUGHTON | 617 WROUGHTON DR | 239 | VER | 2025-02-27 | U123111 | U126856 | 2025-02-11 | 2025-02-14 | 2025-02-27 |  | LYN STAFFORD | 2025-02-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 2.5 | 1 | 4000.37 | 189.94 | 296.7 | 8.88 | 3504.85 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25314145700 |  | 501358721 |  | 6700212O | 2398395 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | WROUGHTON | 629 WROUGHTON DR | 239 | VER | 2025-02-27 | U123111 | U126856 | 2025-02-11 | 2025-02-14 | 2025-02-27 |  | LYN STAFFORD | 2025-02-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 3 | 1 | 3929.49 | 227.93 | 296.7 | 10.68 | 3394.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25314163600 |  | 100296459 |  | 6716216O |  |  |  | 563 | EX | 1" P LONG/PRMT RCVD | 2600B | GREENWOOD | 424 GREENWOOD AV | 067 | LEX | 2025-03-24 | U461516 | U132258 | 2025-02-11 | 2025-02-20 | 2025-03-05 |  | NEAL JOHNSON | 2025-03-12 | 2025-03-05 | 2025-03-05 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26210011 | 20.3167 | 3 | 9777.14 | 1361.23 | 310.58 | 1366.14 | 6739.19 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25314169000 |  | 100262014 |  | 7352256H | 2511883 |  |  | 563 | EX | 1.25" P SHORT | 2621P | LONG | 1220 LONG ST | 019 | ASH | 2025-03-03 | U124604 | U128266 | 2025-02-11 | 2025-02-12 | 2025-02-26 |  | JROGER1 | 2025-02-28 | 2025-02-25 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 42.1167 | 6 | 7691.35 | 3409.74 | 358.23 | 159.76 | 3763.62 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25314236600 |  | 100456476 |  | 6696212P |  |  |  | 565 | VO | REPLACE SL-LEAKAGE D341975 | 2621P | STOURBRIDGE | 222 S STOURBRIDGE RD | 239 | VER | 2025-03-19 |  | U124604 | 2025-02-12 | 2025-08-11 | 2027-02-28 |  | CDESPAIN | 2025-03-17 |  |  | A | [11 empty] | 25321165600 | 100 |  | 1.5333 | 2 | 181.03 | 124.93 | 0 | 56.1 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25314241000 |  | 501317396 |  | 6716236J | 2178365 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | FLAMINGO | 106 FLAMINGO CR | 209 | GEO | 2025-02-27 | U123111 | U126856 | 2025-02-12 | 2025-02-14 | 2025-02-27 |  | LYN STAFFORD | 2025-02-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4 | 1 | 2983.35 | 303.87 | 261.82 | 14.24 | 2403.42 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25314241600 |  | 501338362 |  | 6716232B | 2179247 |  |  | 563 | EX | 1" P LONG BALL HOMES | 2600B | DUNMORE | 113 DUNMORE LN LT194 | 209 | GEO | 2025-03-06 | U126284 | U129531 | 2025-02-12 | 2025-02-14 | 2025-03-12 |  | JOSH PASLEY | 2025-03-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 9 | 1 | 5246.95 | 703.01 | 0 | 611.52 | 3932.42 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25314242300 |  | 501327305 |  | 6716232B | 2179247 |  |  | 563 | EX | 1" P SHORT BALL HOMES | 2600B | DUNMORE | 125 DUNMORE LN LT188 | 209 | GEO | 2025-02-27 | U126284 | U129531 | 2025-02-12 | 2025-02-14 | 2025-02-27 |  | JOSH PASLEY | 2025-02-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 10 | 1 | 3378.47 | 826.95 | 0 | 625.45 | 1926.07 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 25314249800 |  | 100356214 |  | 7256280F |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTREQ | 2621P | JERSEY RIDGE | 836 JERSEY RIDGE RD | 161 | MAY | 2025-03-05 | U930915 | U140273 | 2025-02-12 | 2025-03-05 | 2025-03-26 |  | SDADAMS | 2025-03-05 | 2025-03-04 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 3.6833 | 2 | 2731.39 | 303.46 | 0 | 48.43 | 2379.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25314269500 |  | 100300617 |  | 6716212F |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | ANDERSON | 1137 ANDERSON AV | 067 | LEX | 2025-03-14 | MCRAIG | U140273 | 2025-02-12 | 2025-03-05 | 2025-03-26 |  | MCRAIG | 2025-03-14 | 2025-03-14 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.8 | 3 | 564.18 | 431.47 | 39.7 | 93.01 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25314270300 |  | 100328529 |  | 6720208F | 2511899 |  |  | 565 | CO | 2"PMLP S/L - METER UPGRADE | 2621P | BRISTOL | 428 BRISTOL RD | 067 | LEX | 2025-06-20 |  | U124604 | 2025-02-12 | 2025-12-23 | 2025-12-25 |  | HMCKUNE | 2025-06-20 | 2025-02-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 37.2167 | 8 | 7338.53 | 2158.67 | 0 | 841.8 | 4338.06 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25314282500 |  | 500918944 |  | 6716232E | 0462761 |  |  | 566 | EX | ABANDON SL - DEMO/FIRE | 2621P | KINGSTON | 127 KINGSTON DR | 209 | GEO | 2025-03-10 | DCOLLIN | U140273 | 2025-02-12 | 2025-03-05 | 2025-03-26 |  | DCOLLIN | 2025-03-10 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 15.95 | 2 | 1581.33 | 1280.58 | 0 | 300.75 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25314297300 |  | 501285104 |  | 6744208I | 1968301 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | GIBSON | 140 GIBSON WY | 049 | WIN | 2025-02-26 | U123111 | U126856 | 2025-02-12 | 2025-02-14 | 2025-02-27 |  | LYN STAFFORD | 2025-02-26 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 2 | 1 | 1565.26 | 171.49 | 261.82 | 8.05 | 1123.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25314297500 |  | 501285121 |  | 6744208I | 1968301 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | GIBSON | 138 GIBSON WY | 049 | WIN | 2025-02-26 | U123111 | U126856 | 2025-02-12 | 2025-02-14 | 2025-02-27 |  | LYN STAFFORD | 2025-02-26 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 2 | 1 | 1577.02 | 171.49 | 261.82 | 8.05 | 1135.66 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25314297700 |  | 501285120 |  | 6744208I | 1968301 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | GIBSON | 136 GIBSON WY | 049 | WIN | 2025-02-26 | U123111 | U126856 | 2025-02-12 | 2025-02-14 | 2025-02-27 |  | LYN STAFFORD | 2025-02-26 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 2 | 1 | 2043.63 | 171.49 | 261.82 | 8.05 | 1602.27 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25314404400 |  | 100269083 |  | 6736252M |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | SAINT CLAIR | 111 SAINT CLAIR ST | 097 | CYN | 2025-03-07 | U930915 | U140273 | 2025-02-13 | 2025-03-06 | 2025-03-27 |  | NRICHIE | 2025-03-06 | 2025-02-21 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 11.8333 | 4 | 1433.82 | 909.45 | 100.65 | 51.21 | 372.51 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25314417100 |  | 501346459 |  | 6740204H | 2288186 |  |  | 563 | EX | 99 1" P LONG | 2600B | CRAIG CROSSING | 1110 CRAIG CROSSING | 049 | WIN | 2025-02-26 | U123111 | U134375 | 2025-02-13 | 2025-02-14 | 2025-02-27 |  | LYN STAFFORD | 2025-02-26 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 4 | 1 | 3588.26 | 342.97 | 261.82 | 16.05 | 2967.42 | 0 | 0 | 0
KY | KY - EAST | 2633 | 25314417200 |  | 501376368 |  | 7356152E |  |  |  | 563 | EX | 1" P SHORT | 2621P | MAYO | 5229 N MAYO TL | 195 | PIK | 2025-03-06 | BPREECE | U134341 | 2025-02-13 | 2025-02-27 | 2025-02-27 |  | BPREECE | 2025-03-06 | 2025-02-26 |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26330011 | 36.1833 | 5 | 3756.08 | 2961.82 | 218.55 | 575.71 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25314417800 |  | 500123280 |  | 6720208M |  |  |  | 563 | EX | 1" P SHORT/PRMT RCVD | 2600B | PEPPERHILL | 3193 PEPPERHILL RD | 067 | LEX | 2025-03-12 | U123111 | U127708 | 2025-02-13 | 2025-02-20 | 2025-03-07 |  | LYN STAFFORD | 2025-03-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 4217.64 | 280.37 | 261.82 | 16.43 | 3659.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25314423900 |  | 500040395 |  | 6724208M |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | RICHMOND | 3029 RICHMOND RD | 067 | LEX | 2025-03-20 | U123688 | U124604 | 2025-02-13 | 2025-03-28 |  |  | LSTANFI | 2025-03-12 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.5 | 3 | 1309.28 | 1038.56 | 15.07 | 255.65 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25314434900 |  | 501249836 |  | 7356252B |  |  |  | 563 | EX | 2" P SHORT LP | 2621P | CANTERBURY | 4678 CANTERBURY CT | 019 | ASH | 2025-03-07 | ABHATFIE | U132256 | 2025-02-13 | 2025-03-06 | 2025-03-06 |  | ABHATFIE | 2025-03-07 | 2025-03-07 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 34.6167 | 4 | 3541.7 | 2518 | 0 | 926.02 | 97.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25314447900 |  | 100309077 |  | 6716212M |  |  |  | 565 | EX | METER MOVE OUT / RELO | 2621P | DELLA | 804 DELLA DR | 067 | LEX | 2025-03-13 | KKINDER | U124604 | 2025-02-13 | 2025-03-28 |  |  | KKINDER | 2025-03-13 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 20.65 | 3 | 1772.57 | 1376.1 | 188.86 | 207.61 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25314449000 |  | 100443362 |  | 6720212E |  |  |  | 563 | EX | 1" P LONG/PRMT RCVD | 2600B | LIMESTONE | 810 N LIMESTONE ST 1FR | 067 | LEX | 2025-03-18 | U123111 | U134341 | 2025-02-13 | 2025-02-28 | 2025-03-13 |  | LYN STAFFORD | 2025-03-12 | 2025-03-12 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 13.5 | 2 | 11740.21 | 946.22 | 402.18 | 55.45 | 10336.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25314456100 |  | 100287506 |  | 6720212G |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | DARLEY | 1048 DARLEY DR | 067 | LEX | 2025-02-13 | U123688 | U123688 | 2025-02-13 | 2025-01-14 |  |  | LSTANFI | 2025-01-14 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 9.3 | 3 | 2565.04 | 1848.24 | 438.92 | 277.88 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25314590900 |  | 100302506 |  | 6712212G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BORDEAUX | 1283 BORDEAUX DR | 067 | LEX | 2025-02-17 | U124604 | U137585 | 2025-02-14 | 2025-02-16 | 2025-03-06 |  | JGILES | 2025-02-14 | 2025-02-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 15.1 | 2 | 1694.15 | 1105.28 | 388.71 | 200.16 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25314599800 |  | 100345844 |  | 6704212M |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | GAYBOURNE | 110 GAYBOURNE WY | 239 | VER | 2025-03-14 | U128410 | U124604 | 2025-02-14 | 2025-03-28 |  |  | CDESPAIN | 2025-03-12 | 2025-03-11 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 7.35 | 3 | 1311.63 | 1097.85 | 0 | 213.78 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 25314607300 |  | 501247552 |  | 7260280N |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | WILLIAMS | 1026 WILLIAMS ST | 161 | MAY | 2025-03-11 | SDADAMS | U140273 | 2025-02-14 | 2025-03-07 | 2025-03-28 |  | SDADAMS | 2025-03-11 | 2025-03-11 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 6.45 | 3 | 3968.83 | 470.54 | 39.7 | 27.59 | 3431 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25314615800 |  | 100430846 |  | 6716208F |  |  |  | 566 | EX | PAPER ABANDON SL W/100316593 | 2621P | PENMOKEN | 124 PENMOKEN PA RR | 067 | LEX | 2025-02-14 | U123688 | U124604 | 2025-02-14 | 2025-02-14 |  |  | OFFICE | 2025-02-14 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - CENTRAL | 2632 | 25314616600 |  | 100354973 |  | 7260280M |  |  |  | 563 | EX | 1 "P LONG | 2621P | HALL | 709 HALL ST | 161 | MAY | 2025-03-04 | U124604 | U132253 | 2025-02-14 | 2025-02-28 | 2025-03-14 |  | SDADAMS | 2025-03-03 |  |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26320011 | 16 | 2 | 1507.27 | 1160.14 | 279.12 | 68.01 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25314616700 |  | 100430847 |  | 6716208F |  |  |  | 566 | EX | PAPER ABANDON SL W/100316593 | 2621P | PENMOKEN | 124 PENMOKEN PA 2FL | 067 | LEX | 2025-02-14 | U123688 | U124604 | 2025-02-14 | 2025-02-14 |  |  | OFFICE | 2025-02-14 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 25314647000 |  | 501231582 |  | 6712216H | 1852431 |  |  | 563 | EX | 1" P SHORT/PRMT RCVD | 2600B | MAJESTIC VIEW | 3098 MAJESTIC VIEW WK | 067 | LEX | 2025-03-11 | U461516 | U126856 | 2025-02-14 | 2025-02-28 | 2025-03-13 |  | NEAJOHNSON | 2025-03-06 | 2025-03-06 | 2025-03-06 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 3.6833 | 1 | 2723.03 | 248.13 | 271.96 | 249 | 1953.94 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25314647700 |  | 500071375 |  | 6700212A |  |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | ASHBY | 301 ASHBY CT | 239 | VER | 2025-03-05 | U123111 | U129531 | 2025-02-14 | 2025-02-20 | 2025-03-05 |  | LYN STAFFORD | 2025-03-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 5 | 1 | 1886.01 | 369.67 | 296.7 | 21.67 | 1197.97 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25314813100 |  | 100243032 |  | 7356256P |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BLACKBURN | 5523 BLACKBURN AV | 019 | ASH | 2025-02-17 | U124604 | U141174 | 2025-02-16 | 2025-02-16 | 2025-02-16 |  | ABHATFIE | 2025-02-16 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 23.7167 | 4 | 9824.83 | 4174.53 | 0 | 1571.39 | 4078.91 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25314847800 |  | 501374313 |  | 7356256B |  |  |  | 563 | EX | 199 1" PL LONG | 2621P | LINDA | 815 LINDA LN | 019 | ASH | 2025-03-04 | ABHATFIE | U125753 | 2025-02-17 | 2025-02-18 | 2025-03-03 |  | ABHATFIE | 2025-03-04 | 2025-02-28 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 23.3167 | 6 | 2881.92 | 1833.11 | 0 | 1048.81 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25314854300 |  | 100300506 |  | 6716212G |  |  |  | 563 | EX | 1" P LONG/PRMT RCVD | 2600B | ROBERTSON | 516 ROBERTSON ST | 067 | LEX | 2025-03-18 | U461516 | U134375 | 2025-02-17 | 2025-02-28 | 2025-03-13 |  | NEAL JOHNSON | 2025-03-13 |  | 2025-03-13 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4.75 | 1 | 6157.59 | 318.51 | 354.08 | 18.67 | 5466.33 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25314857800 |  | 501377850 |  | 7240216F | 2512493 |  |  | 563 | EX | 2" PMMP S/L TEMP HEAT/BOILER | 2600B | FALCON | 225 FALCON DR TEMP HT | 173 | MT | 2025-02-18 | U126604 | U127708 | 2025-02-17 | 2025-03-03 | 2025-03-03 |  | WILLIAM FULKS | 2025-02-18 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 4.4833 | 1 | 5416.37 | 381.47 | 0 | 96.7 | 4938.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25315113000 |  | 100303818 |  | 6712208D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | OLEANDER | 2008 OLEANDER DR | 067 | LEX | 2025-03-18 | U124604 | U124604 | 2025-02-18 | 2025-08-15 | 2027-02-28 |  | JGILES | 2025-03-17 | 2025-03-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25.0667 | 5 | 2229.01 | 1288.4 | 389.69 | 490.24 | 60.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25315119800 |  | 100302975 |  | 6712208C |  |  |  | 566 | EX | PAPER ABANDON | 2621P | GEORGIAN | 2067 GEORGIAN WY 1FR | 067 | LEX | 2025-02-18 | U123688 | U123688 | 2025-02-18 | 2025-02-18 |  |  | OFFICE | 2025-02-18 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2623 | 25315138500 |  | 500566852 |  | 6700212M | 9721521 |  |  | 563 | EX | 20 1" P LONG/NO PRMT REQ | 2600B | MARTIN | 492 MARTIN DR | 239 | VER | 2025-03-05 | U123111 | U142144 | 2025-02-18 | 2025-02-20 | 2025-03-05 |  | LYN STAFFORD | 2025-03-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 5 | 1 | 4637 | 369.67 | 296.7 | 21.67 | 3948.96 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25315146400 |  | 500346055 |  | 7240212B | 2511978 |  |  | 565 | EX | NBT UPGRADE SERVICE LINE | 2621P | REID | 19 REID AV | 173 | MT | 2025-03-14 | U123688 | U137009 | 2025-02-18 | 2025-03-18 | 2025-03-18 |  | DENNING | 2025-03-11 | 2025-03-06 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26290031 | 36.9333 | 6 | 15287.28 | 2998.26 | 10729.66 | 1559.36 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25315149700 |  | 501343691 |  | 6716220M | 2394864 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | MARLENA | 1285 MARLENA LN | 067 | LEX | 2025-02-28 | U129731 | U126856 | 2025-02-18 | 2025-02-20 | 2025-03-05 |  | EDWARD GOINS | 2025-02-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 5.85 | 1 | 2429.43 | 430.15 | 247.19 | 123.1 | 1628.99 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25315151300 |  | 100244698 |  | 7356256G |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | CENTRAL | 3128 CENTRAL AV | 019 | ASH | 2025-03-07 | JKEENER | U140273 | 2025-02-18 | 2025-03-04 | 2025-03-04 |  | JKEENER | 2025-03-07 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 13.5333 | 2 | 1001.11 | 945.67 | 0 | 55.44 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25315177000 |  | 100298221 |  | 6716212H | 2512413 |  |  | 563 | EX | 1" PL SHORT/PRMT RCVD | 2600B | SAUNIER | 150 SAUNIER AV | 067 | LEX | 2025-03-07 | U126284 | U125753 | 2025-02-18 | 2025-02-28 | 2025-03-13 |  | JOSH PASLEY | 2025-03-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 10 | 1 | 3264.25 | 740.55 | 0 | 677.08 | 1846.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25315192200 |  | 100436672 |  | 6716208N |  |  |  | 563 | EX | PAPER MANIFOLD W/ 100435979 | 2600B | REGENCY | 2520 REGENCY RD 102 | 067 | LEX | 2025-02-20 | U132386 | U129176 | 2025-02-18 | 2025-02-18 | 2025-03-04 |  | OFFICE | 2025-02-20 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26210011 |  | 0
KY | KY - WEST | 2621 | 25315196600 |  | 501028359 |  | 6712208G |  |  |  | 563 | EX | 1" P SHORT/PRMT RCVD | 2600B | BEAUMONT CENTR | 3254 BEAUMONT CENTR CR | 067 | LEX | 2025-03-13 | U126284 | U128272 | 2025-02-18 | 2025-02-28 | 2025-03-13 |  | JOSH PASLEY | 2025-03-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2966.68 | 592.43 | 0 | 541.66 | 1832.59 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25315290800 |  | 100252472 |  | 7348264O |  |  |  | 563 | EX | 1"P LONG | 2621P | JONES | 1707 JONES ST | 089 | FLA | 2025-03-06 | U143504 | U132253 | 2025-02-19 | 2025-03-05 | 2025-03-19 |  | ABHATFIE | 2025-03-05 | 2025-02-28 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 23.5167 | 5 | 2705.06 | 1856.95 | 400.68 | 447.43 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25315322100 |  | 501208666 |  | 6712228B |  |  |  | 563 | EX | 20 1" P LONG/NO PRMT REQ | 2600B | MALLORY | 124 MALLORY LN | 209 | GEO | 2025-03-10 | U123111 | U142144 | 2025-02-19 | 2025-02-20 | 2025-03-12 |  | LYN STAFFORD | 2025-03-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 4878.35 | 591.45 | 277.03 | 34.66 | 3975.21 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25315323700 |  | 100330317 |  | 6720208B | 2409850 |  |  | 565 | EX | SERVICE LINE/METER UPGRADE | 2621P | BON AIR | 1701 BON AIR DR | 067 | LEX | 2025-04-16 | U124604 | U124604 | 2025-02-19 | 2025-12-23 | 2025-12-25 |  | BDARNELL | 2025-04-15 | 2025-03-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 37.3833 | 7 | 8667.53 | 1887.36 | 705.77 | 176.91 | 5897.49 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25315347700 |  | 501348614 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | CALISTA FLAT | 713 CALISTA FLAT | 067 | LEX | 2025-03-06 | U126285 | U126856 | 2025-02-19 | 2025-02-21 | 2025-03-06 |  | DUSTIN DAVIS | 2025-03-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1296.84 | 0 | 268.11 | 0 | 1028.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25315427800 |  | 100286906 |  | 6720212B |  |  |  | 565 | EX | REPAIR/REPLACE SERVICE LINE | 2621P | CARLISLE | 170 CARLISLE AV | 067 | LEX | 2025-02-20 | KKINDER | U139677 | 2025-02-20 | 2025-02-20 |  |  | KKINDER | 2025-02-20 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.71667 | 1 | 230.59 | 64.3 | 163.26 | 3.03 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25315440600 |  | 100281828 |  | 6712232N |  |  |  | 566 | EX | ABANDON SERVICE/CUST REQ | 2621P | HAMILTON | 328 N HAMILTON ST | 209 | GEO | 2025-03-07 | U930915 | U124604 | 2025-02-20 | 2025-03-28 |  |  | CHERNDO | 2025-03-06 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 30.1833 | 4 | 3429.36 | 2389.31 | 0 | 140.05 | 900 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25315443200 |  | 100353044 |  | 6744208P |  |  |  | 563 | EX | 1' P LONG | 2600B | BURNS | 35 N BURNS AV | 049 | WIN | 2025-03-11 | U461516 | U133050 | 2025-02-20 | 2025-02-21 | 2025-03-06 |  | NEAL JOHNSON | 2025-03-07 |  | 2025-03-07 | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 9 | 1 | 5062.24 | 631.83 | 284.18 | 607.34 | 3538.89 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25315560600 |  | 501086423 |  | 7348260D | 1098657 |  |  | 566 | EX | ABANDON SL/ DEMO/FIRE | 2621P | DIEDERICH | 1420 DIEDERICH BV 101 | 089 | RUS | 2025-05-16 | RECUMP | U123688 | 2025-02-21 | 2026-12-31 |  |  | RECUMP | 2025-05-16 | 2025-04-11 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 16.7833 | 4 | 1748.73 | 1119.19 | 21.09 | 608.45 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25315577900 |  | 501034092 |  | 6720208D | 1100502 |  |  | 566 | EX | ABANDON SL IDLE/INACTIVE | 2621P | DOWNS | 707 DOWNS AV B | 067 | LEX | 2025-02-21 | LSTANFI | U139701 | 2025-02-21 | 2025-02-21 |  |  | LSTANFI | 2025-02-21 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.16667 | 2 | 18.53 | 15.69 | 0 | 2.84 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25317226200 |  | 100328380 |  | 6720208F | 1313369 |  |  | 565 | EX | SERVICE LINE REPAIR | 2621P | CULPEPPER | 504 CULPEPPER RD | 067 | LEX | 2025-02-24 | LSTANFI | U134902 | 2025-02-24 | 2025-02-23 | 2025-02-23 |  | LSTANFI | 2025-02-24 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.6667 | 3 | 2203.5 | 1631.18 | 331.77 | 240.55 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25317238700 |  | 100414306 |  | 6712204C |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D341737 | 2621P | BATHURST | 3481 BATHURST CT | 067 | LEX | 2025-03-27 | U124604 | U124604 | 2025-02-24 | 2025-08-22 | 2027-02-28 |  | RSTRONG | 2025-03-26 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 24 | 3 | 2281.87 | 1607.88 | 275.62 | 319.93 | 78.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25317239200 |  | 100458155 |  | 6712208J |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D341738 | 2621P | LYON | 3475 LYON DR 73 | 067 | LEX | 2025-04-01 | U123688 | U124604 | 2025-02-24 | 2025-08-22 | 2027-02-28 |  | RSTRONG | 2025-03-27 | 2025-03-27 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 24 | 3 | 2234.58 | 1607.88 | 204.65 | 319.93 | 102.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25317239700 |  | 100281072 |  | 6684228K |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | MAIN | 137 E MAIN ST | 073 | FRA | 2025-02-24 | DCOLLIN | U129939 | 2025-02-24 | 2025-02-24 |  |  | DCOLLIN | 2025-02-24 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.15 | 3 | 13.34 | 11.74 | 0 | 1.6 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25317240600 |  | 100463060 |  | 6720208L |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D512756 | 2621P | PATCHEN | 379 PATCHEN DR | 067 | LEX | 2025-03-20 | U124604 | U124604 | 2025-02-24 | 2025-08-22 | 2027-02-28 |  | HMCKUNE | 2025-03-18 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 23.3333 | 3 | 2284.05 | 1332.85 | 269.95 | 585.05 | 96.2 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25317246700 |  | 500337040 |  | 6692228N | 2512271 |  |  | 565 | EX | SERVICE LINE/METER UPGRADE | 2621P | VILLAGE | 342 VILLAGE DR | 073 | FRA | 2025-03-24 | U124604 | U124604 | 2025-02-24 | 2025-03-24 | 2025-03-24 |  | DCOLLIN | 2025-03-21 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26230031 | 26.0667 | 3 | 5319.84 | 2157.05 | 505.26 | 422.65 | 2234.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25317254600 |  | 100321188 |  | 6716212P |  |  |  | 566 | EX | ABANDON SERVICE W/100321189 | 2621P | AYLESFORD | 343 AYLESFORD PL 2F | 067 | LEX | 2025-02-24 | U123688 | U124604 | 2025-02-24 | 2025-02-24 |  |  | OFFICE | 2025-02-24 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 25317405000 |  | 100330703 |  | 6720212N |  |  |  | 566 | EX | PAPER ABANDON | 2621P | SHERMAN | 198 SHERMAN AV 2F | 067 | LEX | 2025-02-25 | U124604 | U124604 | 2025-02-25 | 2025-02-25 |  |  | OFFICE | 2025-02-25 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 25317406400 |  | 100462721 |  | 6720212N |  |  |  | 566 | EX | PAPER ABANDON | 2621P | SHERMAN | 198 SHERMAN AV W-HEAT | 067 | LEX | 2025-02-25 | U123688 | U123688 | 2025-02-25 | 2025-12-31 |  |  | OFFICE | 2025-02-25 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2623 | 25317413900 |  | 501373391 |  | 6684228N |  |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | BERRY HILL | 2052 BERRY HILL DR | 073 | FRA | 2025-03-06 | U123111 | U129531 | 2025-02-25 | 2025-02-26 | 2025-03-11 |  | LYN STAFFORD | 2025-03-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 2568.67 | 591.45 | 275.35 | 34.66 | 1667.21 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25317414700 |  | 501044034 |  | 6684228N | 0780931 |  |  | 563 | EX | PAPER W/501044033 | 2621P | BERRY HILL | 2038 BERRY HILL DR | 073 | FRA | 2025-02-27 | U132386 | U128727 | 2025-02-25 | 2025-02-28 | 2025-03-13 |  | OFFICE | 2025-02-27 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26230011 |  | 0
KY | KY - CENTRAL | 2629 | 25317419500 |  | 501372642 |  | 6736228K | 2398765 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | LINZI | 124 LINZI WY | 017 | PAR | 2025-03-03 | U461309 | U126856 | 2025-02-25 | 2025-03-11 | 2025-03-11 |  | RANDALL HUMPHREYS | 2025-02-28 | 2025-02-28 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBTWM |  | 100 | 056332B26290012 | 4.5 | 1 | 3926.26 | 374.37 | 261.82 | 281.57 | 3008.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25317419900 |  | 501372640 |  | 6736228K | 2398765 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | LINZI | 122 LINZI WY | 017 | PAR | 2025-03-03 | U461309 | U126856 | 2025-02-25 | 2025-03-11 | 2025-03-11 |  | RANDALL HUMPHREYS | 2025-02-28 | 2025-02-28 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBTWM |  | 100 | 056332B26290012 | 3.5 | 1 | 3801.07 | 291.19 | 261.82 | 218.98 | 3029.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25317421500 |  | 501334670 |  | 6716216E | 2289300 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | DAHLIA | 660 DAHLIA DR | 067 | LEX | 2025-03-07 | U123111 | U126856 | 2025-02-25 | 2025-02-26 | 2025-03-11 |  | LYN STAFFORD | 2025-03-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2000.95 | 560.72 | 296.7 | 32.86 | 1110.67 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25317463800 |  | 500128085 |  | 6704204L |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D341562 | 2621P | AVENUE OF CHAM | 26 AVENUE OF CHAM | 113 | NIC | 2025-02-27 | U124604 | U124604 | 2025-02-25 | 2025-02-25 | 2025-02-25 |  | HMCKUNE | 2025-02-27 | 2025-02-26 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 25.4333 | 5 | 2030.89 | 1589.18 | 367.26 | 74.45 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25317603300 |  | 501361983 |  | 6716216E | 2403608 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | DITTANY | 2474 DITTANY LN | 067 | LEX | 2025-03-11 | U461516 | U126856 | 2025-02-26 | 2025-02-27 | 2025-03-12 |  | NEAL JOHNSON | 2025-03-10 |  | 2025-03-10 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4.5 | 1 | 4080.08 | 301.74 | 263.15 | 17.69 | 3497.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25317603400 |  | 501361984 |  | 6716216E | 2403608 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | DITTANY | 2478 DITTANY LN | 067 | LEX | 2025-03-11 | U461516 | U126856 | 2025-02-26 | 2025-02-27 | 2025-03-12 |  | NEAL JOHNSON | 2025-03-10 |  | 2025-03-10 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 3.5 | 1 | 3826.36 | 234.69 | 290 | 13.75 | 3287.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25317607400 |  | 100415463 |  | 6720208M |  |  |  | 565 | EX | REPLACE SERVICE | 2621P | MONTAVESTA | 2925 MONTAVESTA RD | 067 | LEX | 2025-02-26 | KOBRYAN | U130871 | 2025-02-26 | 2025-02-26 | 2025-02-26 |  | KOBRYAN | 2025-02-26 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 6.85 | 2 | 2727.64 | 1032.12 | 231.71 | 269.15 | 1194.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25317608100 |  | 100415462 |  | 6720208M |  |  |  | 565 | EX | REPLACE SERVICE | 2621P | MONTAVESTA | 2921 MONTAVESTA RD | 067 | LEX | 2025-02-26 | LSTANFI | U130871 | 2025-02-26 | 2025-02-26 | 2025-02-26 |  | LSTANFI | 2025-02-26 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 12.4167 | 3 | 1919.21 | 796.27 | 226.21 | 100.29 | 796.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25317811900 |  | 100325865 |  | 6720208E |  |  |  | 565 | EX | SERVICE LINE UPGRADE | 2621P | COLONY | 329 COLONY BV | 067 | LEX | 2025-03-21 | U124604 | U124604 | 2025-02-27 | 2025-03-19 | 2025-03-19 |  | HMCKUNE | 2025-03-20 | 2025-03-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 38.55 | 12 | 5698.22 | 2278.07 | 1151.2 | 232.45 | 2036.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25317816800 |  | 501313792 |  | 6716232B | 2289995 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | OAK HILL | 106 OAK HILL LN | 209 | GEO | 2025-03-14 | U126284 | U126856 | 2025-02-27 | 2025-02-28 | 2025-03-13 |  | JOSH PASLEY | 2025-03-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 4881.01 | 624.9 | 0 | 543.56 | 3712.55 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25317846200 |  | 100410587 |  | 6716208D |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | COOPER | 560 COOPER DR | 067 | LEX | 2025-03-17 | U930915 | U140273 | 2025-02-27 | 2025-03-20 | 2025-04-10 |  | JBURFOR | 2025-03-17 | 2025-03-17 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.5833 | 3 | 941.42 | 889.3 | 0 | 52.12 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25317875200 |  | 100275426 |  | 6684228F |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | BENSON | 714 BENSON AV | 073 | FRA | 2025-02-27 | ATWILLI | U139417 | 2025-02-27 | 2025-02-27 |  |  | ATWILLI | 2025-02-27 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26230043 | 0.1 | 2 | 28.47 | 7.3 | 17.88 | 3.29 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25318085300 |  | 501332977 |  | 6716232I | 2180856 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | OXFORD LANDING | 113 OXFORD LANDING DR | 209 | GEO | 2025-03-11 | U123111 | U126856 | 2025-02-28 | 2025-03-03 | 2025-03-14 |  | LYN STAFFORD | 2025-03-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 3 | 1 | 1646.59 | 221.82 | 296.7 | 12.99 | 1115.08 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25318085500 |  | 501332986 |  | 6716232I | 2180856 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | OXFORD LANDING | 122 OXFORD LANDING DR | 209 | GEO | 2025-03-11 | U126284 | U126856 | 2025-02-28 | 2025-03-03 | 2025-03-14 |  | JOSH PASLEY | 2025-03-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 5.05 | 1 | 4971.79 | 394.47 | 0 | 343.15 | 4234.17 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25318085800 |  | 501332988 |  | 6716232I | 2180856 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | OXFORD LANDING | 124 OXFORD LANDING DR | 209 | GEO | 2025-03-11 | U126284 | U126856 | 2025-02-28 | 2025-03-03 | 2025-03-14 |  | JOSH PASLEY | 2025-03-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 5.45 | 1 | 4997.86 | 425.69 | 0 | 370.34 | 4201.83 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25318086000 |  | 501350501 |  | 6716232J | 2398315 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | OXFORD LANDING | 134 OXFORD LANDING DR | 209 | GEO | 2025-03-17 | U123111 | U126856 | 2025-02-28 | 2025-03-03 | 2025-03-14 |  | LYN STAFFORD | 2025-03-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 4621.68 | 591.45 | 296.7 | 34.66 | 3698.87 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25318086200 |  | 501350539 |  | 6716232J | 2398315 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | OXFORD LANDING | 149 OXFORD LANDING DR | 209 | GEO | 2025-03-11 | U123111 | U126856 | 2025-02-28 | 2025-03-03 | 2025-03-14 |  | LYN STAFFORD | 2025-03-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 3 | 1 | 1648.06 | 221.82 | 296.7 | 12.99 | 1116.55 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25318086500 |  | 501350537 |  | 6716232J | 2398315 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | OXFORD LANDING | 153 OXFORD LANDING DR | 209 | GEO | 2025-03-11 | U123111 | U126856 | 2025-02-28 | 2025-03-03 | 2025-03-14 |  | LYN STAFFORD | 2025-03-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 3 | 1 | 1648.06 | 221.82 | 296.7 | 12.99 | 1116.55 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25318086700 |  | 501350528 |  | 6716232J | 2398315 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | OXFORD LANDING | 173 OXFORD LANDING DR | 209 | GEO | 2025-03-10 | U127414 | U126856 | 2025-02-28 | 2025-03-03 | 2025-03-14 |  | EDWRAD FOX | 2025-03-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 1865.52 | 589.31 | 0 | 162.6 | 1113.61 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25318097200 |  | 100325743 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/ 24026358800 | 2621P | COOPER | 1157 COOPER DR | 067 | LEX | 2025-02-28 | U128336 | U128445 | 2025-02-28 | 2025-12-19 |  |  | JOSHUA COX | 2025-02-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1523.93 | 0 | 0 | 0 | 1523.93 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25318124200 |  | 501366338 |  | 7360216E | 2512539 |  |  | 563 | EX | 1" P SHORT | 2621P | HWY 3 | 1010 S HWY 3 | 127 | LOU | 2025-05-22 | U124604 | U138822 | 2025-02-28 | 2025-02-28 | 2025-05-21 |  | MCOLLET | 2025-05-21 | 2025-05-20 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 24.3167 | 4 | 9444.71 | 1765.63 | 443.91 | 3250.33 | 3984.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25318257000 |  | 501376468 |  | 6712232N | 2511993 |  |  | 563 | EX | TAP W/25-0263920-00 | 2600B | WHITE PINE | 309 WHITE PINE LN | 209 | GEO | 2025-05-09 | U129731 | U120250 | 2025-03-03 | 2025-05-30 | 2025-05-31 |  | EDWARD F GOINS | 2025-05-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBTWM |  | 100 | 056332B26230012 |  | 1 | 1952.93 | 0 | 0 | 0 | 1952.93 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25318274400 |  | 100346798 |  | 6696212O |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HILLCREST | 323 HILLCREST DR | 239 | VER | 2025-03-03 | U128410 | U139701 | 2025-03-03 | 2025-02-28 | 2025-02-28 |  | CDESPAIN | 2025-02-28 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0 | 2 | 420 | 0 | 0 | 0 | 420 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25318281700 |  | 100253778 |  | 7356220P | 1855491 |  |  | 565 | EX | RPLC SL/18026794400 | 2621P | SYCAMORE | 415 E SYCAMORE ST | 127 | LOU | 2025-03-05 | U123965 | U132386 | 2025-03-03 | 2025-12-19 |  |  | CJH CASEY PACK | 2025-03-05 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2903.5 | 0 | 0 | 0 | 2903.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25318291300 |  | 100328517 |  | 6720208F | 2512769 |  |  | 565 | EX | SERVICE LINE/METER UPGRADE | 2621P | BRISTOL | 425 BRISTOL RD | 067 | LEX | 2025-03-20 | KKINDER | U124604 | 2025-03-03 | 2025-03-28 | 2025-03-28 |  | KKINDER | 2025-03-20 | 2025-03-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 47.15 | 6 | 4976.6 | 3209.24 | 781.37 | 985.99 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25318297900 |  | 100289038 |  | 6724212A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SANDALWOOD | 561 SANDALWOOD DR | 067 | LEX | 2025-03-04 | U124604 | U139701 | 2025-03-03 | 2025-07-25 | 2027-01-31 |  | LSTANFI | 2025-03-03 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 10.4 | 3 | 1637.79 | 1082.02 | 393.61 | 162.16 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25318305900 |  | 100444657 |  | 6768172A |  |  |  | 563 | EX | 1"P-LONG | 2621P | MAIN | 704 MAIN ST | 065 | RAV | 2025-03-24 | DENNING | U128727 | 2025-03-03 | 2025-03-04 | 2025-03-31 |  | DENNING | 2025-03-24 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 20 | 2 | 4594.69 | 1603.45 | 542.23 | 94.01 | 2355 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25318318100 |  | 500008273 |  | 6716212H |  |  |  | 565 | EX | AOC L3 ATMOS CORR REMEDIATE | 2621P | SHORT | 541 W SHORT ST 35 | 067 | LEX | 2025-03-03 | HSTANFI | U139701 | 2025-03-03 | 2025-03-03 |  |  | HSTANFI | 2025-03-03 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.7 | 4 | 757.71 | 489.85 | 211.01 | 28.73 | 28.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25318318400 |  | 100318063 |  | 6716204G |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D341563 | 2621P | KING ARTHUR | 3548 KING ARTHUR DR | 067 | LEX | 2025-03-05 | U124604 | U124604 | 2025-03-03 | 2025-03-03 | 2025-03-03 |  | KKINDER | 2025-03-04 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.5 | 3 | 2371.66 | 1573.55 | 365.54 | 303.81 | 128.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25318343500 |  | 100461096 |  | 6716212H |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | SHORT | 541 W SHORT ST 32 | 067 | LEX | 2025-03-03 | HSTANFI | U139701 | 2025-03-03 | 2025-03-03 | 2025-03-03 |  | HSTANFI | 2025-03-03 | 2025-03-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.95 | 4 | 3254.59 | 772.45 | 224.43 | 45.29 | 2212.42 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25318501200 |  | 501307383 |  | 7356256N | 2511687 |  |  | 563 | EX | 99 2"P SHORT | 2621P | DIVISION | 2421 DIVISION ST | 019 | ASH | 2025-04-03 | U124604 | U134375 | 2025-03-04 | 2025-03-18 | 2025-04-01 |  | ABHATFIE | 2025-04-02 | 2025-04-01 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 49.2333 | 6 | 9199.61 | 3316.31 | 1047.66 | 673.63 | 4162.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25318504300 |  | 501303244 |  | 6724208M |  |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | SUNNY LANDING | 640 SUNNY LANDING TR | 067 | LEX | 2025-03-14 | U129731 | U126856 | 2025-03-04 | 2025-03-07 | 2025-03-20 |  | EDWARD F GOINS | 2025-03-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4.6167 | 1 | 2276.09 | 312.58 | 261.82 | 18.31 | 1683.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25318532900 |  | 100289348 |  | 6724212A |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | IVY | 606 IVY CT | 067 | LEX | 2025-03-05 | U124604 | U130871 | 2025-03-04 | 2025-03-04 |  |  | LSTANFI | 2025-03-04 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 1.9167 | 1 | 1445.2 | 802.73 | 386.44 | 256.03 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25318533400 |  | 100278376 |  | 6688232N |  |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | KIOWA | 1142 KIOWA TL | 073 | FRA | 2025-03-20 | U123111 | U130192 | 2025-03-04 | 2025-03-07 | 2025-03-20 |  | LYN STAFFORD | 2025-03-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 4965.1 | 591.45 | 426.9 | 34.66 | 3912.09 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25318540700 |  | 501370237 |  | 6744208N |  |  |  | 563 | EX | 1" P SHORT | 2600B | BULLION | 550 BULLION BV | 049 | WIN | 2025-03-18 | U461516 | U126856 | 2025-03-04 | 2025-03-07 | 2025-03-20 |  | NEAL JOHNSON | 2025-03-18 | 2025-03-17 | 2025-03-18 | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 9.45 | 2 | 3683.2 | 664.13 | 382.09 | 38.92 | 2598.06 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25318541800 |  | 100241482 |  | 7356256G |  |  |  | 565 | EX | AOC ENCROACHMENT REMEDIA | 2621P | CARTER | 2821 CARTER AV | 019 | ASH | 2025-05-19 | MCOLLET | U137009 | 2025-03-04 | 2025-12-31 |  |  | MCOLLET | 2025-05-19 | 2025-03-20 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 31.7167 | 8 | 5812.64 | 2521.13 | 221.85 | 3069.66 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25318700000 |  | 100303103 |  | 6712208C |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D341702 | 2621P | PINEBLOOM | 1039 PINEBLOOM DR | 067 | LEX | 2025-04-02 | U124604 | U124604 | 2025-03-05 | 2025-09-04 | 2027-03-31 |  | TROE | 2025-04-01 | 2025-03-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.65 | 5 | 1562.71 | 996.71 | 505.28 | 60.72 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25318700600 |  | 100309405 |  | 6712208P |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D513578 | 2621P | TRINITY | 3161 TRINITY RD | 067 | LEX | 2025-04-25 | U124604 | U124604 | 2025-03-05 | 2025-09-04 | 2027-03-31 |  | MCRAIG | 2025-04-24 | 2025-04-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.05 | 5 | 2277.37 | 1238.33 | 428.29 | 470.15 | 140.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25318711300 |  | 501346245 |  | 6728208I | 2396366 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | TWILIGHT SHADO | 1186 TWILIGHT SHADO DR | 067 | LEX | 2025-03-14 | U129731 | U126856 | 2025-03-05 | 2025-03-07 | 2025-03-20 |  | EDWARD F GOINS | 2025-03-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 3.3833 | 1 | 2169.7 | 227.53 | 248.4 | 13.33 | 1680.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25318711600 |  | 501378492 |  | 6720212B |  |  |  | 563 | EX | 1" P SHORT/PRMT RCVD | 2600B | LIMESTONE | 1406 N LIMESTONE ST NEW | 067 | LEX | 2025-04-01 | U461322 | U126856 | 2025-03-05 | 2025-03-19 | 2025-04-01 |  | STEVE CANOY | 2025-04-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 5.4 | 1 | 2414.35 | 347.27 | 0 | 375.65 | 1691.43 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25318714200 |  | 500302942 |  | 6712208N | 2512469 |  |  | 565 | EX | NBT:INSTALL EFV 1" 700 SERIES | 2621P | BLACKHORSE | 2053 BLACKHORSE LN | 067 | LEX | 2025-04-17 | U124604 | U124604 | 2025-03-05 | 2025-03-25 |  |  | HMCKUNE | 2025-04-16 | 2025-03-24 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 33.1 | 10 | 2625.81 | 1801.93 | 21.58 | 802.3 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 25318734800 |  | 501378368 |  | 7372188L |  |  |  | 563 | EX | 99 1" P SHORT | 2621P | FIREHOUSE | 45 FIREHOUSE LN | 159 | WAR | 2025-03-12 | JAHOWARD | U142144 | 2025-03-05 | 2025-03-06 | 2025-03-19 |  | JAHOWARD | 2025-03-12 | 2025-03-11 |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26330011 | 30.3 | 4 | 2372.54 | 2241.16 | 0 | 131.38 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25318736000 |  | 100342095 |  | 7240216N |  |  |  | 566 | EX | ABANDON SLIDLE/INACTIVE | 2621P | MAYSVILLE | 25 MAYSVILLE AV | 173 | MT | 2025-03-19 | U930915 | U137009 | 2025-03-05 | 2025-03-19 | 2025-04-05 |  | LCLARK | 2025-03-18 | 2025-03-07 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 16.8333 | 4 | 4392.11 | 1333.15 | 0 | 1036.46 | 2022.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25318754100 |  | 500008718 |  | 6712208J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SALLEE | 2148 SALLEE DR | 067 | LEX | 2025-03-06 | U143504 | U139677 | 2025-03-05 | 2025-07-29 | 2027-01-30 |  | JGILES | 2025-03-05 | 2025-03-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 13.6833 | 6 | 2658.57 | 1798.77 | 204.65 | 520.47 | 134.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25318776400 |  | 500815441 |  | 728208F | 0145363 |  |  | 563 | EX | 1"P LONG *DAILEY HMS*NO PRMT | 2600B | SILVER CHARM | 3852 SILVER CHARM LN LT26 | 067 | LEX | 2025-03-18 | U123111 | U138822 | 2025-03-05 | 2025-03-07 | 2025-03-20 |  | LYN STAFFORD | 2025-03-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4165.74 | 560.72 | 346.14 | 32.86 | 3226.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25318848200 |  | 501369867 |  | 6724208M | 2408136 |  |  | 563 | EX | PAPER W/500114822 | 2600B | RICHMOND | 3080 RICHMOND RD STE 115 | 067 | LEX | 2025-03-13 | U123688 | U127708 | 2025-03-06 | 2025-03-06 | 2025-03-20 |  | OFFICE | 2025-03-06 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26210011 |  | 1
KY | KY - CENTRAL | 2629 | 25318855100 |  | 501375602 |  | 6736228G | 2511455 |  |  | 563 | EX | TAP W/MAIN 25-0263818-00 | 2600B | DOGWOOD | 1200 DOGWOOD DR | 017 | PAR | 2025-03-27 | U461322 | U127708 | 2025-03-06 | 2025-06-06 | 2025-06-06 |  | STEVE CANOY | 2025-03-27 | 2025-03-26 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBTWM |  | 100 | 056332B26290012 | 10 | 2 | 3271.72 | 730.2 | 0 | 327.95 | 2213.57 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25318882400 |  | 501378296 |  | 6744208P | 2512779 |  |  | 563 | EX | 2" P LONG | 2600B | LEXINGTON | 5 E LEXINGTON AV | 049 | WIN | 2025-03-21 | U461516 | U129531 | 2025-03-06 | 2025-03-07 | 2025-03-20 |  | NEAL JOHNSON | 2025-03-20 |  | 2025-03-20 | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 | 8 | 1 | 7647.95 | 561.63 | 1338.78 | 539.85 | 5207.69 | 0 | 0 | 0
KY | KY - EAST | 2633 | 25318904600 |  | 501337629 |  | 7344148I | 2397807 |  |  | 563 | EX | TAP WITH MAIN - 24026345800 | 2600B | REED | 6981 REED LN | 071 | DRI | 2025-03-28 | U128523 | U134341 | 2025-03-06 | 2025-04-15 | 2025-04-15 |  | BRANDON ROBERTS | 2025-03-27 |  |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26330012 |  | 1 | 2502.27 | 0 | 0 | 0 | 2502.27 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25318931400 |  | 501378650 |  | 6684224 |  |  |  | 563 | EX | 1"P-SHORT/NO PRMT REQ | 2600B | US 127 | 1301 US 127 SO B | 073 | FRA | 2025-04-15 | U123111 | U128727 | 2025-03-06 | 2025-03-12 | 2025-04-04 |  | LYN STAFFORD | 2025-04-14 | 2025-04-14 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4 | 1 | 3130.86 | 261.48 | 297.73 | 15.96 | 2555.69 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25318941300 |  | 100276827 |  | 6684228D |  |  |  | 566 | EX | ABANDON SL-CONVRT/CUSTRQD | 2621P | 1ST | 822 1ST AV | 073 | FRA | 2025-04-09 | BSEXTON | U143435 | 2025-03-06 | 2025-03-26 | 2025-04-16 |  | BSEXTON | 2025-04-09 | 2025-04-08 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 16.6167 | 3 | 2083.19 | 1020.9 | 0 | 62.29 | 1000 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25318943700 |  | 501361900 |  | 6712228L | 2292762 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | BILL PERKINS | 150 BILL PERKINS LN LT82 | 209 | GEO | 2025-03-17 | U129731 | U129531 | 2025-03-06 | 2025-03-12 | 2025-03-25 |  | EDWARD F GOINS | 2025-03-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 6.55 | 1 | 2418.44 | 466.46 | 261.82 | 27.36 | 1662.8 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25318946600 |  | 100259101 |  | 7356256A |  |  |  | 563 | EX | 99 1" P SHORT | 2621P | PROSPECT | 921 PROSPECT AV | 019 | ASH | 2025-04-01 | U124604 | U134375 | 2025-03-06 | 2025-03-20 | 2025-04-03 |  | CWHEELE | 2025-03-31 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 16 | 2 | 4192.98 | 1138.12 | 263.12 | 799.34 | 1992.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25319033400 |  | 100329673 |  | 6720208D | 2403558 |  |  | 566 | EX | RETIRE S/L WITH SMRP | 2600B | SAINT TERESA | 2052 SAINT TERESA DR | 067 | LEX | 2025-03-11 | U128816 | U461383 | 2025-03-07 | 2025-05-01 | 2025-05-01 |  | OLIVER MAYNARD | 2025-03-11 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1118.62 | 0 | 0 | 0 | 1118.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25319056000 |  | 501356938 |  | 6712204E | 2397231 |  |  | 563 | EX | 20 1" P SHORT MOORE BLDRS | 2600B | BELLERIVE | 909 BELLERIVE BV LT19 | 113 | NIC | 2025-03-19 | U461516 | U132805 | 2025-03-07 | 2025-03-12 | 2025-03-25 |  | NEAL JOHNSON | 2025-03-19 |  | 2025-03-19 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4.3167 | 1 | 2519.45 | 288.33 | 276.8 | 289.38 | 1664.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25319071100 |  | 500117902 |  | 6720208H |  |  |  | 563 | EX | 1" P SHORT/PRMT RCVD | 2600B | CODELL | 371 CODELL DR 4 | 067 | LEX | 2025-04-01 | U123111 | U130192 | 2025-03-07 | 2025-03-19 | 2025-04-01 |  | LYN STAFFORD | 2025-04-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2782.28 | 506.76 | 381.28 | 30.92 | 1863.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25319296600 |  | 100303019 |  | 6712208C |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D512760 | 2621P | PINEBLOOM | 1040 PINEBLOOM DR | 067 | LEX | 2025-04-04 | U124604 | U124604 | 2025-03-10 | 2025-09-05 | 2027-03-31 |  | HSTANFI | 2025-04-03 | 2025-03-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.2 | 7 | 789.91 | 538.42 | 218.73 | 32.76 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 25319297300 |  | 501374457 |  | 7256276B | 2409391 |  |  | 563 | EX | 1" P LONG | 2621P | EVERGREEN | 105 EVERGREEN LN | 161 | MAY | 2025-03-20 | U124604 | U126856 | 2025-03-10 | 2025-03-24 | 2025-03-24 |  | SDADAMS | 2025-03-19 | 2025-03-18 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26320011 | 17.5667 | 4 | 2230.11 | 1276.34 | 213.63 | 581.78 | 158.36 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 25319297500 |  | 501374456 |  | 7256276B | 2409391 |  |  | 563 | EX | 1" P LONG | 2621P | EVERGREEN | 106 EVERGREEN LN | 161 | MAY | 2025-03-20 | U124604 | U126856 | 2025-03-10 | 2025-03-24 | 2025-03-24 |  | SDADAMS | 2025-03-19 | 2025-03-19 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26320011 | 13.4833 | 2 | 1382.74 | 974.46 | 195.75 | 57.13 | 155.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25319310200 |  | 501356936 |  | 6712204E | 2397231 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | BELLERIVE | 905 BELLERIVE BV | 113 | NIC | 2025-03-19 | U461516 | U126856 | 2025-03-10 | 2025-03-12 | 2025-03-25 |  | NEAL JOHNSON | 2025-03-19 |  | 2025-03-19 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 3.6833 | 1 | 2385.02 | 248.13 | 276.8 | 249 | 1611.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25319312400 |  | 500985976 |  | 6708204J | 2511832 |  |  | 563 | EX | 1 " P LONG/NO PRMT REQ | 2600B | PEARL | 141 PEARL LN LT4 | 113 | NIC | 2025-03-24 | U461516 | U134341 | 2025-03-10 | 2025-03-12 | 2025-03-25 |  | NEAL JOHNSON | 2025-03-21 |  | 2025-03-21 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 6711.22 | 536.45 | 354.89 | 31.44 | 5788.44 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25319322500 |  | 100276826 |  | 6684228D |  |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | 1ST | 818 1ST AV | 073 | FRA | 2025-03-21 | U123111 | U130192 | 2025-03-10 | 2025-03-12 | 2025-03-25 |  | LYN STAFFORD | 2025-03-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 3488.75 | 591.45 | 339.18 | 34.66 | 2523.46 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25319333700 |  | 100285797 |  | 6764172D |  |  |  | 563 | EX | 1" P SHORT | 2621P | BROADWAY | 406 BROADWAY ST | 065 | IRV | 2025-03-21 | U124604 | U134341 | 2025-03-10 | 2025-03-24 | 2025-03-24 |  | DENNING | 2025-03-20 | 2025-03-20 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 15.7333 | 3 | 1885.23 | 1252.75 | 493.9 | 73.46 | 65.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25319354000 |  | 100309395 |  | 6712208P |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | TRINITY | 3172 TRINITY RD | 067 | LEX | 2025-03-10 | U930915 | U129939 | 2025-03-10 | 2025-03-07 | 2025-03-25 |  | JGILES | 2025-03-10 | 2025-03-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.1 | 5 | 2340.14 | 1498.3 | 302.64 | 539.2 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25319364400 |  | 501345752 |  | 7352256D | 2512177 |  |  | 563 | EX | 1" P SHORT | 2621P | NEVADA | 2231 NEVADA ST | 019 | ASH | 2025-03-21 | U124604 | U134341 | 2025-03-10 | 2025-03-24 | 2025-03-24 |  | ABHATFIE | 2025-03-20 | 2025-03-20 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 26.35 | 3 | 2177.78 | 1928.73 | 136 | 113.05 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25319364700 |  | 100333434 |  | 6720212I |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | EASTERN | 210 EASTERN AV A | 067 | LEX | 2025-03-10 | LSTANFI | U129939 | 2025-03-10 | 2025-03-10 |  |  | LSTANFI | 2025-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.35 | 3 | 26.75 | 22.03 | 0 | 4.72 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25319364900 |  | 100333436 |  | 6720212I |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | EASTERN | 210 EASTERN AV B | 067 | LEX | 2025-03-10 | LSTANFI | U129939 | 2025-03-10 | 2025-03-10 |  |  | LSTANFI | 2025-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.4 | 3 | 28.96 | 23.87 | 0 | 5.09 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25319371800 |  | 500174290 |  | 7240216O |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | MAIN | 200 E MAIN ST | 173 | MT | 2025-03-12 | U124604 | U129939 | 2025-03-10 | 2025-03-10 |  |  | DENNING | 2025-03-11 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 84.74 | 80.05 | 0 | 4.69 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25319611900 |  | 500048041 |  | 6720204N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | KENESAW VILLAG | 1217 KENESAW VILLAG DR | 067 | LEX | 2025-03-14 | U124604 | U137248 | 2025-03-10 | 2025-03-13 | 2025-03-31 |  | TROE | 2025-03-13 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.65 | 5 | 1564.67 | 1278.14 | 211.6 | 74.93 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25319612000 |  | 100402776 |  | 7352256G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | NEW BUCKLEY | 236 W NEW BUCKLEY RD | 019 | ASH | 2025-03-11 | U124604 | U137248 | 2025-03-10 | 2025-03-10 | 2025-03-10 |  | ABHATFIE | 2025-03-10 | 2025-03-10 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 31.5 | 3 | 6409.41 | 3029.15 | 0 | 1478.01 | 1902.25 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25319615000 |  | 500537242 |  | 7356216D | 1855491 |  |  | 565 | EX | REPLACE W/ 18-0267944-00 | 2600B | FYFFE | 117 FYFFE ST 130 | 127 | LOU | 2025-03-14 | U123965 | U125768 | 2025-03-11 | 2049-12-31 |  |  | CJH CASEY PACK | 2025-03-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3715.94 | 0 | 0 | 0 | 3715.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25319624800 |  | 100289244 |  | 6724212A |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D512083 | 2621P | LOMBARDY | 612 LOMBARDY DR | 067 | LEX | 2025-03-20 | U124604 | U124604 | 2025-03-11 | 2025-03-12 | 2025-03-30 |  | JGILES | 2025-03-19 | 2025-03-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.5 | 3 | 2840.17 | 1395.72 | 427.65 | 321.64 | 695.16 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25319627500 |  | 501378780 |  | 6716236I |  |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | CORPORATE | 235 CORPORATE BV | 209 | GEO | 2025-03-26 | U129673 | U126856 | 2025-03-11 | 2025-03-26 | 2025-03-26 |  | A WILLIAMSON | 2025-03-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 4846.9 | 615.66 | 297.74 | 164.14 | 3769.36 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25319627800 |  | 501378782 |  | 6716236I |  |  |  | 563 | EX | 2" P LONG/NO PRMT REQ | 2600B | ENTERPRISE | 201 ENTERPRISE WY | 209 | GEO | 2025-03-25 | U123111 | U126856 | 2025-03-11 | 2025-03-26 | 2025-03-26 |  | LYN STAFFORD | 2025-03-24 | 2025-03-24 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 11.75 | 2 | 4754.34 | 895.15 | 190.75 | 52.47 | 3615.97 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25319628200 |  | 501378783 |  | 6716236I |  |  |  | 563 | EX | 2"P LONG MANIFOLD W/501378782 | 2600B | ENTERPRISE | 205 ENTERPRISE WY | 209 | GEO | 2025-03-25 | U123111 | U126856 | 2025-03-11 | 2025-03-26 | 2025-03-26 |  | LYN STAFFORD | 2025-03-24 | 2025-03-24 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 3.5 | 1 | 1663.29 | 258.76 | 0 | 15.17 | 1389.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25319628700 |  | 100309581 |  | 6712208K |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D513583 | 2621P | ARROWHEAD | 3004 ARROWHEAD DR | 067 | LEX | 2025-04-15 | U124604 | U124604 | 2025-03-11 | 2025-09-10 | 2027-03-31 |  | WCRIM | 2025-04-14 | 2025-04-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 34.6167 | 7 | 4009.59 | 1856.08 | 247.52 | 113.25 | 1792.74 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25319630200 |  | 501375187 |  | 7348260H | 2511591 |  |  | 563 | EX | TAP W/ MAIN 25026381700 | 2600B | SUNSET | 524 SUNSET DR | 089 | ASH | 2025-03-26 | U124015 | U132627 | 2025-03-11 | 2025-04-14 | 2025-04-14 |  | ORA SLONE | 2025-03-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBTWM |  | 100 | 056332B26310012 | 3.4667 | 1 | 1739.4 | 243.9 | 0 | 70.01 | 1425.49 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25319650700 |  | 501150044 |  | 6720208E | 2511696 |  |  | 563 | EX | 2" P LONG/PRMT RCVD | 2600B | WOODLAKE | 458 WOODLAKE WY | 067 | LEX | 2025-04-08 | U123111 | U129531 | 2025-03-11 | 2025-03-25 | 2025-04-07 |  | LYN STAFFORD | 2025-04-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 4695.53 | 253.38 | 503.7 | 15.46 | 3922.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25319683800 |  | 100326852 |  | 6720208B |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | FONTAINE | 1513 FONTAINE RD FURN | 067 | LEX | 2025-03-11 | JOCHOA | U129939 | 2025-03-11 | 2025-03-11 |  |  | JOCHOA | 2025-03-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.16667 | 1 | 24.33 | 12.8 | 0 | 11.53 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25319683900 |  | 100326853 |  | 6720208B |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | FONTAINE | 1511 FONTAINE RD | 067 | LEX | 2025-03-11 | JOCHOA | U129939 | 2025-03-11 | 2025-03-11 |  |  | JOCHOA | 2025-03-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.21667 | 1 | 31.49 | 16.56 | 0 | 14.93 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25319684100 |  | 500935165 |  | 6720208B |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | FONTAINE | 1513 FONTAINE RD | 067 | LEX | 2025-03-11 | JOCHOA | U129939 | 2025-03-11 | 2025-03-11 |  |  | JOCHOA | 2025-03-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.25 | 1 | 40.05 | 21.06 | 0 | 18.99 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25319689600 |  | 100286968 |  | 6720212F |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2600B | CASTLEWOOD | 236 CASTLEWOOD DR | 067 | LEX | 2025-03-11 | U129722 | U125768 | 2025-03-11 | 2025-03-11 | 2025-03-11 |  | DAVID YOUNG | 2025-03-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26210022 | 2.8167 | 1 | 205.43 | 194.06 | 0 | 11.37 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25319702100 |  | 501378059 |  | 7344264D | 2512648 |  |  | 563 | EX | 99 2" P SHORT | 2621P | GREENUP | 440 GREENUP RD | 089 | RAC | 2025-04-09 | DYOUNG | U134375 | 2025-03-11 | 2025-03-25 | 2025-04-08 |  | LAMAY | 2025-04-09 | 2025-04-03 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 73.7833 | 14 | 7788.28 | 4829.91 | 0 | 2848.85 | 109.52 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25319703100 |  | 500009749 |  | 7348264N |  |  |  | 565 | EX | REPLACE SL- LEAKAGE D359587 | 2621P | BRENT ANN | 2215 BRENT ANN DR | 089 | FLA | 2025-03-21 | U124604 | U137009 | 2025-03-11 | 2025-03-14 | 2025-04-01 |  | RECUMP | 2025-03-20 | 2025-03-19 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 14.5667 | 3 | 1424.89 | 997.78 | 98.65 | 244.1 | 84.36 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25319708200 |  | 100245121 |  | 7356256N |  |  |  | 565 | EX | GRADE 1 REPLACE SERVICE LINE | 2621P | COURT | 2856 COURT ST | 019 | ASH | 2025-03-12 | U124604 | U129939 | 2025-03-11 | 2025-03-11 | 2025-03-11 |  | JKEENER | 2025-03-11 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 11.2 | 3 | 1184.14 | 824.39 | 0 | 287.23 | 72.52 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25319713000 |  | 501361926 |  | 6712228L | 2292762 |  |  | 563 | EX | 1" P LONG DALAMAR | 2600B | RUTH MILLER | 166 RUTH MILLER DR LT105 | 209 | GEO | 2025-03-27 | U129673 | U132256 | 2025-03-11 | 2025-03-26 | 2025-03-26 |  | A WILLIAMSON | 2025-03-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 2.5 | 1 | 3723.18 | 192.4 | 311.05 | 169.71 | 3050.02 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25319715200 |  | 501361939 |  | 6712228L | 2292762 |  |  | 563 | EX | 1" P LONG DALAMAR | 2600B | RUTH MILLER | 164 RUTH MILLER DR | 209 | GEO | 2025-03-26 | U123111 | U132256 | 2025-03-11 | 2025-03-26 | 2025-03-26 |  | LYN STAFFORD | 2025-03-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 5 | 1 | 4481.79 | 369.67 | 298.38 | 21.68 | 3792.06 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25319715900 |  | 501361928 |  | 6712228L | 2292762 |  |  | 563 | EX | 1" P LONG DALAMAR | 2600B | RUTH MILLER | 160 RUTH MILLER DR LT103 | 209 | GEO | 2025-03-26 | U123111 | U132256 | 2025-03-11 | 2025-03-26 | 2025-03-26 |  | LYN STAFFORD | 2025-03-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4 | 1 | 4293.77 | 295.74 | 402.18 | 17.33 | 3578.52 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25319717700 |  | 501361929 |  | 6712228L | 2292762 |  |  | 563 | EX | 1" P LONG DALAMAR | 2600B | RUTH MILLER | 158 RUTH MILLER DR LT102 | 209 | GEO | 2025-03-24 | U123111 | U132256 | 2025-03-11 | 2025-03-26 | 2025-03-26 |  | LYN STAFFORD | 2025-03-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4 | 1 | 4129.77 | 295.73 | 395.46 | 17.33 | 3421.25 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25319734400 |  | 501361930 |  | 6712228L | 2292762 |  |  | 563 | EX | 1" P LONG DALAMAR | 2600B | RUTH MILLER | 156 RUTH MILLER DR LT101 | 209 | GEO | 2025-03-25 | U129673 | U132256 | 2025-03-11 | 2025-03-26 | 2025-03-26 |  | A WILLIAMSON | 2025-03-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 4645.26 | 615.66 | 312.61 | 543.02 | 3173.97 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25319737300 |  | 501361932 |  | 6712228L | 2292762 |  |  | 563 | EX | 1" P LONG DALAMAR | 2600B | RUTH MILLER | 152 RUTH MILLER DR LT99 | 209 | GEO | 2025-03-25 | U123111 | U132256 | 2025-03-11 | 2025-03-26 | 2025-03-26 |  | LYN STAFFORD | 2025-03-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8.5 | 1 | 5824.66 | 628.42 | 298.38 | 36.84 | 4861.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25319738500 |  | 100296458 |  | 6716216O |  |  |  | 565 | EX | REPLACE SL PER NJOHNSON | 2621P | GREENWOOD | 420 GREENWOOD AV | 067 | LEX | 2025-03-20 | U461516 | U132386 | 2025-03-11 | 2025-12-19 |  |  | NEAL JOHNSON | 2025-03-13 |  | 2025-03-13 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 8 | 1 | 5804.13 | 639.35 | 154.31 | 37.48 | 4972.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25319869000 |  | 100309398 |  | 6712208P |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D513585 | 2621P | TRINITY | 3136 TRINITY RD | 067 | LEX | 2025-04-25 | U124604 | U124604 | 2025-03-12 | 2025-09-11 | 2027-03-31 |  | DMEDLEY | 2025-04-24 | 2025-04-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.8833 | 5 | 2390.03 | 1409.53 | 553.99 | 426.51 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25319876700 |  | 501348617 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | CALISTA FLAT | 701 CALISTA FLAT | 067 | LEX | 2025-03-17 | U129731 | U126856 | 2025-03-12 | 2025-03-13 | 2025-03-26 |  | EDWARD F GOINS | 2025-03-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1901.8 | 0 | 240.47 | 0 | 1661.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25319877000 |  | 501348618 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | CALISTA FLAT | 700 CALISTA FLAT | 067 | LEX | 2025-03-19 | U129731 | U126856 | 2025-03-12 | 2025-03-13 | 2025-03-26 |  | EDWARD F GOINS | 2025-03-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2444.69 | 540.12 | 261.82 | 31.66 | 1611.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25319877300 |  | 501348628 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | CLEMATIS | 2213 CLEMATIS WY | 067 | LEX | 2025-03-19 | U129731 | U126856 | 2025-03-12 | 2025-03-13 | 2025-03-26 |  | EDWARD GOINS | 2025-03-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1384.35 | 0 | 206.96 | 0 | 1177.39 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25319924600 |  | 100245101 |  | 7356256N |  |  |  | 565 | EX | GRD 1 ON SERVICE | 2621P | GRANDVIEW | 4322 GRANDVIEW DR | 019 | ASH | 2025-03-12 | ABHATFIE | U130871 | 2025-03-12 | 2025-03-12 | 2025-03-12 |  | ABHATFIE | 2025-03-12 | 2025-03-12 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 26.1667 | 3 | 4511.94 | 1937.46 | 292.02 | 563.47 | 1718.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25319934000 |  | 501296504 |  | 0724204F | 1968324 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | BRANHAM | 3786 BRANHAM PK | 067 | LEX | 2025-04-01 | U461322 | U126856 | 2025-03-12 | 2025-03-17 | 2025-03-28 |  | STEVE CANOY | 2025-04-01 | 2025-03-28 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 9.9333 | 2 | 5707.16 | 666.65 | 297.73 | 539.37 | 4203.41 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25319960100 |  | 100345008 |  | 6696212G |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | SHAW | 100 SHAW AV | 239 | VER | 2025-03-12 | U128410 | U129939 | 2025-03-12 | 2025-03-12 |  |  | CDESPAIN | 2025-03-12 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26230031 |  | 1 | 3250.32 | 2300.54 | 0 | 529.78 | 420 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320021800 |  | 100292915 |  | 6720216K |  |  |  | 563 | EX | 99 1" P LONG/PRMT RCVD | 2600B | BISHOP | 702 BISHOP DR | 067 | LEX | 2025-04-21 | U123111 | U120250 | 2025-03-12 | 2025-03-25 | 2025-04-07 |  | LYN STAFFORD | 2025-04-08 | 2025-04-08 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 4422.83 | 253.38 | 287.47 | 15.46 | 3866.52 | 0 | 0 | 0
KY | KY - EAST | 2633 | 25320094100 |  | 100240707 |  | 7324132J | 2512421 |  |  | 566 | EX | ABANDON SL DEMO/CUSTRQD | 2621P | SUNSET | 65 SUNSET ST | 119 | HIN | 2025-03-18 | JCKIRK | U137009 | 2025-03-13 | 2025-03-21 |  |  | JCKIRK | 2025-03-18 | 2025-03-18 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 19.7833 | 3 | 1659.37 | 1567.49 | 0 | 91.88 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320096300 |  | 100456777 |  | 6720204O |  |  |  | 565 | VO | REPLACE SL-LEAKAGE D514331 | 2621P | WOODFIELD | 2308 WOODFIELD CR | 067 | LEX | 2025-04-23 | U124604 | U124604 | 2025-03-13 | 2025-09-12 | 2027-03-31 |  | HMCKUNE | 2025-04-08 |  |  | A | [11 empty] | 25328409400 | 100 |  |  | 1 | 1601.17 | 951.59 | 6.71 | 642.87 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320123100 |  | 100309507 |  | 6712208K |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | APACHE | 809 APACHE TL | 067 | LEX | 2025-03-14 | U124604 | U129939 | 2025-03-13 | 2025-03-06 | 2025-03-24 |  | KKINDER | 2025-03-13 | 2025-03-12 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.2833 | 4 | 1978.33 | 1368.99 | 350.48 | 258.86 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25320125300 |  | 100253914 |  | 7356220O | 1855491 |  |  | 565 | EX | REPLACE SL/18026794400 | 2600B | LOCK | 300 N LOCK AV | 127 | LOU | 2025-03-14 | U123965 | U132386 | 2025-03-13 | 2025-12-19 |  |  | CJH CASEY PACK | 2025-03-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 6301.91 | 0 | 0 | 0 | 6301.91 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25320129400 |  | 501361884 |  | 6712228L | 2292762 |  |  | 563 | EX | 1" P LONG DALAMAR | 2600B | RUTH MILLER | 145 RUTH MILLER DR LT67C | 209 | GEO | 2025-03-27 | U129673 | U132256 | 2025-03-13 | 2025-03-17 | 2025-03-28 |  | A WILLIAMSON | 2025-03-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 2 | 1 | 1646.23 | 153.91 | 298.38 | 135.77 | 1058.17 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25320130200 |  | 501361919 |  | 6712228L | 2292762 |  |  | 563 | EX | 1" P SHORT DALAMAR | 2600B | RUTH MILLER | 147 RUTH MILLER DR LT90 | 209 | GEO | 2025-03-27 | U129673 | U132256 | 2025-03-13 | 2025-03-17 | 2025-03-28 |  | A WILLIAMSON | 2025-03-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 2 | 1 | 2129.01 | 153.91 | 298.38 | 135.77 | 1540.95 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25320132100 |  | 501361888 |  | 6712228L | 2292762 |  |  | 563 | EX | 1" P LONG DALAMAR | 2600B | BILL PERKINS | 155 BILL PERKINS LN LT71 | 209 | GEO | 2025-03-28 | U129673 | U132256 | 2025-03-13 | 2025-03-17 | 2025-03-28 |  | A WILLIAMSON | 2025-03-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4.5167 | 1 | 3839.51 | 346.29 | 296.7 | 92.35 | 3104.17 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25320136600 |  | 501361899 |  | 6712228L | 2292762 |  |  | 563 | EX | 1" P SHORT DALAMAR | 2600B | BILL PERKINS | 148 BILL PERKINS LN LT83C | 209 | GEO | 2025-03-27 | U129673 | U132256 | 2025-03-13 | 2025-03-17 | 2025-03-28 |  | A WILLIAMSON | 2025-03-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 1.5 | 1 | 2121.08 | 115.45 | 296.7 | 101.83 | 1607.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25320147100 |  | 501361896 |  | 6712228L | 2292762 |  |  | 563 | EX | 1" P LONG DALAMAR | 2600B | BILL PERKINS | 140 BILL PERKINS LN LT118 | 209 | GEO | 2025-03-27 | U129673 | U132256 | 2025-03-13 | 2025-03-17 | 2025-03-28 |  | A WILLIAMSON | 2025-03-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 2 | 1 | 2093.43 | 153.91 | 255.45 | 135.77 | 1548.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320179300 |  | 501378950 |  | 6724204F | 1968324 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | WESTON | 393 WESTON PK | 067 | LEX | 2025-03-28 | U129673 | U127708 | 2025-03-13 | 2025-03-17 | 2025-03-28 |  | A WILLIAMSON | 2025-03-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 2.4 | 1 | 2127.17 | 175.1 | 296.7 | 48.69 | 1606.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320189100 |  | 100300585 |  | 6716212F |  |  |  | 563 | EX | 1" P LONG/PRMT RCVD | 2600B | ROBERTSON | 409 ROBERTSON ST | 067 | LEX | 2025-04-11 | U123111 | U134341 | 2025-03-13 | 2025-03-25 | 2025-04-07 |  | LYN STAFFORD | 2025-04-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 5261.77 | 253.38 | 401.41 | 15.46 | 4591.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320203000 |  | 100437366 |  | 6712208P |  |  |  | 565 | EX | REPLACE SERVICE LINE D513590 | 2621P | CLAYS MILL | 3101 CLAYS MILL RD STE 113 | 067 | LEX | 2025-03-20 | U124604 | U124604 | 2025-03-13 | 2025-03-16 | 2025-04-03 |  | MCRAIG | 2025-03-18 | 2025-03-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 35.0833 | 4 | 3218.77 | 1967.6 | 192.43 | 1058.74 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320214900 |  | 501088823 |  | 6728208C | 1098336 |  |  | 563 | EX | 1" P SHORT/PRMT RCVD | 2600B | CAYMAN HEIGHTS | 2616 CAYMAN HEIGHTS | 067 | LEX | 2025-04-07 | U123111 | U126856 | 2025-03-13 | 2025-03-25 | 2025-04-07 |  | LYN STAFFORD | 2025-04-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 5 | 1 | 4086.41 | 316.73 | 297.73 | 19.32 | 3452.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320215000 |  | 501088822 |  | 6728208C | 1098336 |  |  | 563 | EX | 1" P SHORT/PRMT RCVD | 2600B | CAYMAN HEIGHTS | 2632 CAYMAN HEIGHTS | 067 | LEX | 2025-04-07 | U123111 | U126856 | 2025-03-13 | 2025-03-25 | 2025-04-07 |  | LYN STAFFORD | 2025-04-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 2976.58 | 0 | 297.73 | 0 | 2678.85 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25320216500 |  | 100422410 |  | 6696212H |  |  |  | 566 | EX | SERVICE LINE LK D304844 | 2621P | RUSSELL | 303 S RUSSELL AV | 239 | VER | 2025-03-14 | U128410 | U124604 | 2025-03-13 | 2025-03-16 | 2025-04-03 |  | CDESPAIN | 2025-03-14 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 11.1833 | 2 | 987.44 | 932.74 | 0 | 54.7 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320218000 |  | 100443172 |  | 6716216L |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | NANDINO | 1044 NANDINO BV | 067 | LEX | 2025-03-14 | U124604 | U129939 | 2025-03-13 | 2025-03-13 |  |  | JGILES | 2025-03-13 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.9 | 2 | 233.72 | 130.59 | 35.11 | 68.02 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320218700 |  | 100447604 |  | 6716216L |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | NANDINO | 1048 NANDINO BV | 067 | LEX | 2025-03-14 | U124604 | U129939 | 2025-03-13 | 2025-03-13 |  |  | JGILES | 2025-03-13 | 2025-03-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 2.9333 | 3 | 825.81 | 145.06 | 667.71 | 13.04 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320232400 |  | 100322403 |  | 6716208D |  |  |  | 565 | EX | METER MOVE OUT/RELO CUST REQ | 2621P | SUNSET | 712 SUNSET DR | 067 | LEX | 2025-03-31 | HMCKUNE | U124604 | 2025-03-13 | 2025-03-31 |  |  | HMCKUNE | 2025-03-31 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.9 | 5 | 1772.94 | 1160.33 | 544.59 | 68.02 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320346100 |  | 501378984 |  | 6716220N |  |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | KEARNEY CREEK | 2724 KEARNEY CREEK LN | 067 | LEX | 2025-03-31 | U461322 | U127708 | 2025-03-14 | 2025-03-18 | 2025-03-31 |  | STEVE CANOY | 2025-03-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 3.7833 | 1 | 1875.5 | 265.04 | 0 | 15.54 | 1594.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320354400 |  | 501368857 |  | 6728212M | 2405655 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | BLACKFORD | 2829 BLACKFORD PY | 067 | LEX | 2025-03-31 | U129673 | U126856 | 2025-03-14 | 2025-03-18 | 2025-03-31 |  | A WILLIAMSON | 2025-03-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 3.5 | 1 | 2385.42 | 255.35 | 298.38 | 236.77 | 1594.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320354500 |  | 501368855 |  | 6728212M | 2405655 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | BLACKFORD | 2837 BLACKFORD PY | 067 | LEX | 2025-03-31 | U129673 | U126856 | 2025-03-14 | 2025-03-18 | 2025-03-31 |  | A WILLIAMSON | 2025-03-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4.5 | 1 | 2534.82 | 328.31 | 298.38 | 304.39 | 1603.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320355400 |  | 501347924 |  | 6724204A | 2291616 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | SHADY | 717 SHADY CV | 067 | LEX | 2025-03-31 | U123111 | U126856 | 2025-03-14 | 2025-03-18 | 2025-03-31 |  | LYN STAFFORD | 2025-03-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4.5 | 1 | 3920 | 315.42 | 296.7 | 18.49 | 3289.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320355900 |  | 501347928 |  | 6724204A | 2291616 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | BAY SHOALS | 3448 BAY SHOALS DR | 067 | LEX | 2025-03-31 | U123111 | U126856 | 2025-03-14 | 2025-03-18 | 2025-03-31 |  | LYN STAFFORD | 2025-03-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 5 | 1 | 3924.53 | 350.42 | 283.29 | 20.54 | 3270.28 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320379900 |  | 501348625 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | CLEMATIS | 2201 CLEMATIS WY | 067 | LEX | 2025-03-31 | U461322 | U126856 | 2025-03-14 | 2025-03-18 | 2025-03-31 |  | STEVE CANOY | 2025-03-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4.2167 | 1 | 1460.46 | 292.93 | 0 | 17.17 | 1150.36 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25320382600 |  | 501346460 |  | 6740204H | 2288186 |  |  | 563 | EX | 99 1" P LONG | 2600B | CRAIG CROSSING | 1150 CRAIG CROSSING LT17 | 049 | WIN | 2025-04-01 | U129673 | U128272 | 2025-03-14 | 2025-03-17 | 2025-03-28 |  | A WILLIAMSON | 2025-04-01 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 8 | 1 | 4810.23 | 550.32 | 297.73 | 128.56 | 3833.62 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25320396200 |  | 100346980 |  | 6696212K |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HIGH | 162 HIGH ST | 239 | VER | 2025-03-14 | U128410 | U139701 | 2025-03-14 | 2025-03-14 |  |  | CDESPAIN | 2025-03-12 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26230031 | 0.68333 | 2 | 486.27 | 57.86 | 0 | 3.41 | 425 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320416800 |  | 100337274 |  | 6720212E |  |  |  | 563 | EX | 1" P SHORT/PRMT RCVD | 2600B | 6TH | 178 E 6TH ST | 067 | LEX | 2025-04-15 | U123111 | U130192 | 2025-03-14 | 2025-04-01 | 2025-04-14 |  | LYN STAFFORD | 2025-04-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 5 | 1 | 1855.49 | 316.73 | 0 | 19.32 | 1519.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320622500 |  | 501256154 |  | 6712204A |  |  |  | 563 | EX | 20 1"P LONG/PRMT RCVD | 2600B | TWAIN RIDGE | 1992 TWAIN RIDGE DR | 067 | LEX | 2025-04-10 | U123111 | U132805 | 2025-03-17 | 2025-04-01 | 2025-04-14 |  | LYN STFFORD | 2025-04-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 4138.13 | 253.38 | 297.73 | 15.46 | 3571.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320624300 |  | 501379077 |  | 6728208J | 2513070 |  |  | 563 | EX | TAP W/MAIN 25-0263988-00 | 2600B | MEADOWLARK | 4165 MEADOWLARK RD LT87 | 067 | LEX | 2025-04-16 | U128816 | U127708 | 2025-03-17 | 2025-06-17 | 2025-06-17 |  | OLIVER MAYNARD | 2025-04-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBTWM |  | 100 | 056332B26210012 |  | 1 | 1543.33 | 0 | 0 | 0 | 1543.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320624600 |  | 501379078 |  | 6728208J | 2513070 |  |  | 563 | EX | TAP W/MAIN 25-0263988-00 | 2600B | MEADOWLARK | 4169 MEADOWLARK RD LT88 | 067 | LEX | 2025-04-16 | U128816 | U127708 | 2025-03-17 | 2025-06-17 | 2025-06-17 |  | OLIVER MAYNARD | 2025-04-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBTWM |  | 100 | 056332B26210011 |  | 1 | 1224.98 | 0 | 0 | 0 | 1224.98 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320632100 |  | 100311820 |  | 6716208I |  |  |  | 565 | EX | REPAIR SERVICE LINE | 2621P | WESTERFIELD | 498 WESTERFIELD WY | 067 | LEX | 2025-03-17 | HMCKUNE | U134844 | 2025-03-17 | 2025-03-17 | 2025-03-17 |  | HMCKUNE | 2025-03-17 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.15 | 3 | 1422.28 | 750.36 | 352.3 | 319.62 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 25320690000 |  | 501378294 |  | 7260276B |  |  |  | 563 | EX | 1" P SHORT | 2621P | CLARK | 500 CLARK ST | 161 | MAY | 2025-04-04 | U124604 | U129531 | 2025-03-17 | 2025-03-17 | 2025-04-07 |  | SDADAMS | 2025-04-03 | 2025-03-27 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26320011 | 23.8333 | 7 | 1842.69 | 1429.29 | 326.28 | 87.12 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25320696500 |  | 501361938 |  | 6712228L | 2292762 |  |  | 563 | EX | 1" P LONG DALAMAR/NO PRMT REQ | 2600B | RUTH MILLER | 140 RUTH MILLER DR LT93 | 209 | GEO | 2025-05-01 | U123111 | U132256 | 2025-03-17 | 2025-03-18 | 2025-03-31 |  | LYN STAFFORD | 2025-04-02 | 2025-04-02 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 5321.45 | 522.97 | 299.38 | 31.91 | 4467.19 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25320708100 |  | 100253761 |  | 7356220P | 1855491 |  |  | 565 | EX | REPLACE SL W/ 18026794400 | 2600B | FYFFE | 305 FYFFE ST | 127 | LOU | 2025-03-18 | U123965 | U125768 | 2025-03-17 | 2025-12-23 |  |  | CJ HUGHES MITCHELL DICKESS | 2025-03-18 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2723.84 | 0 | 0 | 0 | 2723.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320719600 |  | 100303348 |  | 6712208D |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | ALEXANDRIA | 2029 ALEXANDRIA DR | 067 | LEX | 2025-03-18 | U124604 | U137248 | 2025-03-17 | 2025-03-17 |  |  | JOCHOA | 2025-03-17 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.65 | 3 | 1445.18 | 1109.61 | 270.53 | 65.04 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25320921200 |  | 100253757 |  | 7356216D | 1855491 |  |  | 565 | EX | REPLACE SL W/18026794400 | 2600B | LOCK | 520 N LOCK AV | 127 | LOU | 2025-03-18 | U123965 | U125768 | 2025-03-18 | 2025-12-23 |  |  | CJ HUGHES MITCHELL DICKESS | 2025-03-18 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3452.95 | 0 | 0 | 0 | 3452.95 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25320924600 |  | 501371244 |  | 6712228C |  |  |  | 563 | EX | PAPER TAP /100282421 EXE ONLY | 2621P | WASHINGTON | 533 E WASHINGTON AV | 209 | GEO | 2025-03-19 | U125768 | U132805 | 2025-03-18 | 2025-03-20 | 2025-04-02 |  | OFFICE | 2025-03-19 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26230011 |  | 0
KY | KY - EAST | 2631 | 25320934200 |  | 100245103 |  | 7356256N |  |  |  | 565 | EX | AOC ENCROACHMENT REMEDIA | 2621P | DIVISION | 2700 DIVISION ST | 019 | ASH | 2025-04-23 | MCOLLET | U137009 | 2025-03-18 | 2025-05-16 | 2025-05-18 |  | MCOLLET | 2025-04-23 | 2025-03-25 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 19.2667 | 6 | 6475.21 | 1321.24 | 383.88 | 1371.91 | 3398.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320935200 |  | 100295803 |  | 6716216G |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | KNIGHT | 1982 KNIGHT LN | 067 | LEX | 2025-03-27 | U124604 | U140273 | 2025-03-18 | 2025-04-08 | 2025-04-29 |  | TROE | 2025-03-26 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.3333 | 2 | 405.73 | 383.24 | 0 | 22.49 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320936200 |  | 100309510 |  | 6712208K |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | APACHE | 821 APACHE TL | 067 | LEX | 2025-03-20 | U124604 | U130871 | 2025-03-18 | 2025-03-06 | 2025-03-24 |  | KKINDER | 2025-03-18 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 18.6 | 5 | 1638.91 | 1240.05 | 177.34 | 97.2 | 124.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320951800 |  | 100310919 |  | 6712204C |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | KEITHSHIRE | 3469 KEITHSHIRE WY | 067 | LEX | 2025-03-20 | U124604 | U130871 | 2025-03-18 | 2025-03-12 | 2025-03-30 |  | RSTRONG | 2025-03-18 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 17.0667 | 3 | 2024.16 | 1435.94 | 278.35 | 309.87 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320954500 |  | 100310246 |  | 6716208A |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | HARRODSBURG | 2090 HARRODSBURG RD | 067 | LEX | 2025-06-10 | TROE | U140273 | 2025-03-18 | 2025-04-08 | 2025-06-16 |  | TROE | 2025-06-10 | 2025-06-09 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.9333 | 6 | 1469.74 | 719.54 | 32.98 | 42.22 | 675 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25320961200 |  | 100352170 |  | 6744208K |  |  |  | 565 | EX | GRD 1 ON SERVICE | 2621P | MARYLAND | 16< MARYLAND AV | 049 | WIN | 2025-03-18 | NRICHIE | U130871 | 2025-03-18 | 2025-03-18 | 2025-03-18 |  | NRICHIE | 2025-03-18 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26290021 | 19.6 | 3 | 4415.2 | 1449.12 | 329.49 | 84.96 | 2551.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320967500 |  | 100419996 |  | 6716204J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | WEM | 3824 WEM DR | 067 | LEX | 2025-03-20 | U124604 | U134822 | 2025-03-18 | 2025-07-25 | 2027-01-31 |  | CHEMMER | 2025-03-18 | 2025-02-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 18.9667 | 5 | 1911.84 | 1595.69 | 226.19 | 89.96 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25320969100 |  | 100328875 |  | 6720208G |  |  |  | 566 | EX | ABD SERVICE LINE | 2621P | DINSMORE | 2256 DINSMORE DR | 067 | LEX | 2025-04-23 | STGOFF | U130871 | 2025-03-18 | 2025-03-18 |  |  | STGOFF | 2025-04-23 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.1333 | 2 | 477.94 | 444.12 | 6.71 | 27.11 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25321002200 |  | 100309479 |  | 6712208O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | WELLINGTON | 737 WELLINGTON WY | 067 | LEX | 2025-03-20 | U124604 | U137248 | 2025-03-18 | 2025-03-18 | 2025-03-18 |  | ABLAKE | 2025-03-19 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.8833 | 3 | 1586.53 | 947.72 | 346.98 | 55.58 | 236.25 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25321155900 |  | 100278704 |  | 6688232O |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D341977 | 2621P | POWHATAN | 432 POWHATAN TL | 073 | FRA | 2025-06-10 | U124604 | U124604 | 2025-03-19 | 2025-09-18 | 2027-03-31 |  | RJCRAWF | 2025-06-09 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 16 | 2 | 4352.03 | 1166.06 | 334.08 | 685.97 | 2165.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25321156500 |  | 100309410 |  | 6712208P |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D513598 | 2621P | WELLINGTON | 661 WELLINGTON WY | 067 | LEX | 2025-04-17 | U124604 | U124604 | 2025-03-19 | 2025-09-18 | 2027-03-31 |  | HSTANFI | 2025-04-16 | 2025-04-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.7667 | 5 | 2351.39 | 1272.65 | 281.09 | 77.65 | 720 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25321163300 |  | 100247293 |  | 7352256L |  |  |  | 566 | EX | SERVICE LINE ABANDON | 2621P | BEECH | 2315 BEECH ST 32 | 019 | ASH | 2025-03-20 | RECUMP | U141174 | 2025-03-19 | 2025-03-19 |  |  | RECUMP | 2025-03-20 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 21.4167 | 3 | 1959.51 | 1510.89 | 31.41 | 417.21 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25321174400 |  | 100253789 |  | 7356216D | 1855491 |  |  | 565 | EX | REPLACE SL/18026794400 | 2621P | LOCK | 618 N LOCK AV | 127 | LOU | 2025-03-21 | U123965 | U132386 | 2025-03-19 | 2025-12-19 |  |  | CJ HUGHES MITCHELL DICKESS | 2025-03-20 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3236.16 | 0 | 0 | 0 | 3236.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25321203100 |  | 100325737 |  | 6720208E | 2396748 |  |  | 566 | EX | ABND SL W/ 24026358800 | 2600B | COOPER | 1201 COOPER DR WH | 067 | LEX | 2025-03-19 | U128336 | U125768 | 2025-03-19 | 2025-12-23 |  |  | JOSHUA COX | 2025-03-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 25321203300 |  | 100325738 |  | 6720208E | 2396748 |  |  | 566 | EX | ABND SL W/24026358800 | 2600B | COOPER | 1201 COOPER DR 5 | 067 | LEX | 2025-03-19 | U128336 | U125768 | 2025-03-19 | 2025-12-23 |  |  | JOSHUA COX | 2025-03-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 25321206000 |  | 100317458 |  | 6716204J |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | HABERSHAM | 214 HABERSHAM CT | 067 | LEX | 2025-04-09 | HMCKUNE | U124604 | 2025-03-19 | 2025-04-17 |  |  | HMCKUNE | 2025-04-09 | 2025-04-08 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.0833 | 4 | 2566 | 973.42 | 6.71 | 588.43 | 997.44 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25321218900 |  | 501373627 |  | 7348264K |  |  |  | 563 | EX | 1" P LONG | 2621P | DIEDRICH | 935 DIEDRICH DR | 089 | FLA | 2025-04-03 | RECUMP | U128272 | 2025-03-19 | 2025-04-02 | 2025-04-02 |  | RECUMP | 2025-04-03 | 2025-04-02 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 14.8333 | 3 | 1463.27 | 932.88 | 0 | 410.51 | 119.88 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25321254600 |  | 100440695 |  | 7352260F |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | DIEDERICH | 500 DIEDERICH BV | 089 | RUS | 2025-03-29 | U123688 | U137248 | 2025-03-19 | 2025-02-20 | 2026-08-31 |  | ABHATFIE | 2025-03-19 | 2025-03-18 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 36.95 | 6 | 3404.34 | 2795.8 | 0 | 608.54 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25321344800 |  | 100325328 |  | 6720208M |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LAMAR | 3114 LAMAR DR | 067 | LEX | 2025-03-24 | U124604 | U137248 | 2025-03-19 | 2025-03-19 | 2025-03-19 |  | RJCRAWF | 2025-03-21 | 2025-03-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 57.6167 | 9 | 6023.13 | 3450.78 | 222.14 | 202.29 | 2147.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25321375700 |  | 501338080 |  | 6712208M | 2288773 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | COCOS | 4185 COCOS WY LT8 | 067 | LEX | 2025-04-02 | U461322 | U126856 | 2025-03-20 | 2025-04-03 | 2025-04-03 |  | STEVE CANOY | 2025-04-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 2.2 | 1 | 2125.05 | 144.68 | 0 | 156.52 | 1823.85 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25321375900 |  | 501338082 |  | 6712208M | 2288773 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | COCOS | 4181 COCOS WY LT10 | 067 | LEX | 2025-04-02 | U461322 | U126856 | 2025-03-20 | 2025-04-03 | 2025-04-03 |  | STEVE CANOY | 2025-04-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 6.6333 | 0 | 883.55 | 424.44 | 0 | 459.11 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25321376000 |  | 501338081 |  | 6712208M | 2288773 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | COCOS | 4183 COCOS WY LT9 | 067 | LEX | 2025-04-02 | U461322 | U126856 | 2025-03-20 | 2025-04-03 | 2025-04-03 |  | STEVE CANOY | 2025-04-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 0.016667 | 0 | 2.69 | 1.3 | 0 | 1.39 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25321376900 |  | 501338084 |  | 6712208M | 2288773 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | COCOS | 4177 COCOS WY LT12 | 067 | LEX | 2025-04-02 | U461322 | U126856 | 2025-03-20 | 2025-04-03 | 2025-04-03 |  | STEVE CANOY | 2025-04-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 0.016667 | 0 | 46.79 | 1.3 | 0 | 1.39 | 44.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25321377100 |  | 501338083 |  | 6712208M | 2288773 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | COCOS | 4179 COCOS WY LT11 | 067 | LEX | 2025-04-02 | U461322 | U126856 | 2025-03-20 | 2025-04-03 | 2025-04-03 |  | STEVE CANOY | 2025-04-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 0.066667 | 1 | 2047.49 | 4.53 | 0 | 4.85 | 2038.11 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25321386500 |  | 100331305 |  | 6720212N |  |  |  | 566 | EX | PAPER ABANDON | 2621P | MONROE | 1201 MONROE AV 4 | 067 | LEX | 2025-03-20 | U123688 | U123688 | 2025-03-20 | 2025-12-31 |  |  | OFFICE | 2025-03-13 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 0
KY | KY - WEST | 2621 | 25321386900 |  | 100331308 |  | 6720212N |  |  |  | 566 | EX | PAPER ABANDON | 2621P | MONROE | 1201 MONROE AV 3 | 067 | LEX | 2025-03-20 | U123688 | U123688 | 2025-03-20 | 2025-12-31 |  |  | OFFICE | 2025-03-13 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 25321387500 |  | 100331311 |  | 6720212N |  |  |  | 566 | EX | PAPER ABANDON | 2621P | MONROE | 1201 MONROE AV 2 | 067 | LEX | 2025-03-20 | U123688 | U123688 | 2025-03-20 | 2025-12-31 |  |  | OFFICE | 2025-03-13 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2623 | 25321406700 |  | 501317403 |  | 6716236J | 2178365 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | CHICKADEE | 135 CHICKADEE TR | 209 | GEO | 2025-04-11 | U123111 | U126856 | 2025-03-20 | 2025-04-03 | 2025-04-03 |  | LYN STAFFORD | 2025-04-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4 | 1 | 1843.91 | 261.48 | 401.41 | 15.96 | 1165.06 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25321407000 |  | 501317387 |  | 6716236J | 2178365 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | FLAMINGO | 105 FLAMINGO CR | 209 | GEO | 2025-04-02 | U129673 | U126856 | 2025-03-20 | 2025-04-03 | 2025-04-03 |  | A WILLIAMSON | 2025-04-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4.5 | 1 | 2267.5 | 298.6 | 292.04 | 71.65 | 1605.21 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25321407600 |  | 501317315 |  | 6716236J | 2178365 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | MEADOW LARK | 137 MEADOW LARK TR | 209 | GEO | 2025-04-02 | U129673 | U126856 | 2025-03-20 | 2025-04-03 | 2025-04-03 |  | A WILLIAMSON | 2025-04-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 3.5 | 1 | 4341.3 | 232.24 | 297.73 | 55.74 | 3755.59 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25321922200 |  | 100284605 |  | 6748180L |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D513718 | 2621P | COLLEGE HILL | 591 COLLEGE HILL RD | 151 | WAC | 2025-05-14 | U124604 | U137009 | 2025-03-21 | 2025-09-19 | 2027-03-31 |  | LCLARK | 2025-05-13 | 2025-05-12 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 11.0333 | 4 | 3832.26 | 885.68 | 252.59 | 51.29 | 2642.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25321928600 |  | 100247113 |  | 7352256L | 2403760 |  |  | 565 | EX | REPLACE W/ 24026321400 | 2600B | WILLIS | 3404 WILLIS AV | 019 | ASH | 2025-06-10 | U123965 | U125768 | 2025-03-21 | 2025-12-19 |  |  | MBLANKE/CJH MITCHELL DICKESS | 2025-06-10 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1964.73 | 0 | 0 | 0 | 1964.73 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25321928700 |  | 100247114 |  | 7352256L | 2403760 |  |  | 565 | EX | REPLACE W/ 24026321400 | 2600B | WILLIS | 3412 WILLIS AV | 019 | ASH | 2025-06-09 | U123965 | U125768 | 2025-03-21 | 2025-12-19 |  |  | MBLANKE/CJH MITCHELL DICKESS | 2025-06-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1826.36 | 0 | 0 | 0 | 1826.36 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25321928800 |  | 100247115 |  | 7352256L | 2403760 |  |  | 565 | EX | REPLACE W/ 24026321400 | 2600B | WILLIS | 3416 WILLIS AV | 019 | ASH | 2025-06-09 | U123965 | U125768 | 2025-03-21 | 2025-12-19 |  |  | MBLANKE/CJH MITCHELL DICKESS | 2025-06-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2407.49 | 0 | 0 | 0 | 2407.49 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25321928900 |  | 100247116 |  | 7352256L | 2403760 |  |  | 565 | EX | REPLACE W/ 24026321400 | 2600B | WILLIS | 3420 WILLIS AV | 019 | ASH | 2025-06-06 | U123965 | U125768 | 2025-03-21 | 2025-12-19 |  |  | MBLANKE/CJH KYLE BLANKENSHIP | 2025-06-06 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1964.73 | 0 | 0 | 0 | 1964.73 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25321929000 |  | 100247117 |  | 7352256L | 2403760 |  |  | 565 | EX | REPLACE W/ 24026321400 | 2600B | WILLIS | 3424 WILLIS AV | 019 | ASH | 2025-06-05 | U123965 | U125768 | 2025-03-21 | 2025-12-19 |  |  | MBLANKE/CJH KYLE BLANKENSHIP | 2025-06-05 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1300.6 | 0 | 0 | 0 | 1300.6 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25321929100 |  | 100247118 |  | 7352256L | 2403760 |  |  | 565 | EX | REPLACE W/ 24026321400 | 2600B | WILLIS | 3428 WILLIS AV | 019 | ASH | 2025-06-04 | U128523 | U125768 | 2025-03-21 | 2025-12-19 |  |  | BRANDON ROBERTS | 2025-06-04 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1964.73 | 0 | 0 | 0 | 1964.73 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25321929200 |  | 100247120 |  | 7352256L | 2403760 |  |  | 565 | EX | REPLACE W/ 24026321400 | 2600B | WILLIS | 3436 WILLIS AV | 019 | ASH | 2025-06-03 | U123965 | U125768 | 2025-03-21 | 2025-12-19 |  |  | MBLANKE/CJH MITCHELL DICKESS | 2025-06-03 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1826.36 | 0 | 0 | 0 | 1826.36 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25321929300 |  | 100247121 |  | 7352256L | 2403760 |  |  | 565 | EX | REPLACE W/ 24026321400 | 2600B | WILLIS | 3438 WILLIS AV | 019 | ASH | 2025-06-04 | U123965 | U125768 | 2025-03-21 | 2025-12-19 |  |  | MBLANKE/CJH MITCHELL DICKESS | 2025-06-04 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2553.53 | 0 | 0 | 0 | 2553.53 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25321929400 |  | 100247122 |  | 7352256L | 2403760 |  |  | 565 | EX | REPLACE W/ 24026321400 | 2600B | WILLIS | 3444 WILLIS AV | 019 | ASH | 2025-06-02 | U128523 | U125768 | 2025-03-21 | 2025-12-19 |  |  | BRANDON ROBERTS | 2025-06-02 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1964.73 | 0 | 0 | 0 | 1964.73 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25321929500 |  | 100247123 |  | 7352256L | 2403760 |  |  | 565 | EX | REPLACE W/ 24026321400 | 2600B | WILLIS | 3450 WILLIS AV | 019 | ASH | 2025-06-02 | U123965 | U125768 | 2025-03-21 | 2025-12-19 |  |  | MBLANKE/CJH MITCHELL DICKESS | 2025-06-02 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2490.49 | 0 | 0 | 0 | 2490.49 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25321929600 |  | 100247124 |  | 7352256L | 2403760 |  |  | 565 | EX | REPLACE W/ 24026321400 | 2600B | WILLIS | 3454 WILLIS AV | 019 | ASH | 2025-05-30 | U123965 | U125768 | 2025-03-21 | 2025-12-19 |  |  | MBLANKE/CJH MITCHELL DICKESS | 2025-05-29 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2754.04 | 0 | 0 | 0 | 2754.04 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25321929700 |  | 500207314 |  | 7352256L | 2403760 |  |  | 565 | EX | REPLACE W/ 24026321400 | 2600B | WILLIS | 3455 WILLIS AV | 019 | ASH | 2025-06-03 | U128523 | U125768 | 2025-03-21 | 2025-12-19 |  |  | BRANDON ROBERTS | 2025-06-03 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2462.73 | 0 | 0 | 0 | 2462.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25321940500 |  | 100333056 |  | 6720212I | 2403447 |  |  | 565 | EX | REPLACE W/ 24-0263150-00 | 2600B | WILSON | 357 WILSON ST | 067 | LEX | 2025-06-19 | U129731 | U125768 | 2025-03-21 | 2025-12-23 |  |  | EDWARD F GOINS | 2025-06-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 553.03 | 522.4 | 0 | 30.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25321940600 |  | 100333064 |  | 6720212I | 2403447 |  |  | 565 | EX | REPLACE W/ 24-0263150-00 | 2600B | WILSON | 361 WILSON ST | 067 | LEX | 2025-06-18 | U129731 | U125768 | 2025-03-21 | 2025-12-23 |  |  | EDWARD F GOINS | 2025-06-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 553.03 | 522.4 | 0 | 30.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25321940700 |  | 100333062 |  | 6720212I | 2403447 |  |  | 565 | EX | REPLACE W/ 24-0263150-00 | 2600B | WILSON | 365 WILSON ST | 067 | LEX | 2025-06-17 | U129731 | U125768 | 2025-03-21 | 2025-12-23 |  |  | EDWARD F GOINS | 2025-06-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 553.03 | 522.4 | 0 | 30.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25321940800 |  | 100333053 |  | 6720212I | 2403447 |  |  | 565 | EX | REPLACE W/ 24-0263150-00 | 2600B | WILSON | 369 WILSON ST | 067 | LEX | 2025-06-18 | U129731 | U125768 | 2025-03-21 | 2025-12-23 |  |  | EDWARD F GOINS | 2025-06-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1
KY | KY - WEST | 2621 | 25321940900 |  | 500241573 |  | 6720212I | 2403447 |  |  | 565 | EX | REPLACE W/ 24-0263150-00 | 2600B | WILSON | 371 WILSON ST | 067 | LEX | 2025-06-16 | U129731 | U125768 | 2025-03-21 | 2025-12-23 |  |  | EDWARD F GOINS | 2025-06-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 36398.8 | 0 | 0 | 0 | 36398.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25321941000 |  | 100333057 |  | 6720212I | 2403447 |  |  | 565 | EX | REPLACE W/ 24-0263150-00 | 2600B | WILSON | 375 WILSON ST | 067 | LEX | 2025-06-16 | U129731 | U125768 | 2025-03-21 | 2025-12-23 |  |  | EDWARD F GOINS | 2025-06-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 553.03 | 522.4 | 0 | 30.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25321953900 |  | 501374431 |  | 16708204D |  |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | KEENE | 4701 KEENE RD | 067 | LEX | 2025-04-07 | U123111 | U129531 | 2025-03-21 | 2025-03-25 | 2025-04-07 |  | LYN STAFFORD | 2025-04-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1515.9 | 0 | 348.8 | 0 | 1167.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25321954800 |  | 100282771 |  | 6712228B |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HAMILTON | 300 S HAMILTON ST | 209 | GEO | 2025-03-24 | U128410 | U139701 | 2025-03-21 | 2025-03-21 | 2025-03-21 |  | CDESPAIN | 2025-03-21 | 2025-03-21 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 35.3 | 5 | 4670.9 | 2805.4 | 0 | 1067.5 | 798 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25321957500 |  | 100306601 |  | 6716212I |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | PINKNEY | 888 PINKNEY DR | 067 | LEX | 2025-03-24 | U124604 | U139701 | 2025-03-21 | 2025-08-07 | 2027-02-28 |  | KKINDER | 2025-03-21 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 9.75 | 2 | 2064.31 | 1403.63 | 352.72 | 307.96 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25321989100 |  | 501358751 |  | 6700212O | 2398395 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | GLASBURY | 301 GLASBURY LN | 239 | VER | 2025-04-07 | U123111 | U126856 | 2025-03-21 | 2025-03-25 | 2025-04-07 |  | LYN STAFFORD | 2025-04-07 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 5 | 1 | 2252.69 | 326.86 | 297.73 | 19.95 | 1608.15 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25321993000 |  | 100326363 |  | 6720208A |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | OLD CASSIDY | 105 OLD CASSIDY AV | 067 | LEX | 2025-04-10 | JBURFOR | U124604 | 2025-03-21 | 2025-04-07 |  |  | JBURFOR | 2025-04-10 | 2025-04-07 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 19 | 5 | 1318.01 | 1043.94 | 210.34 | 63.73 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 25322151700 |  | 100356920 |  | 7252276H |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | OLD MAIN | 1890 OLD MAIN ST | 161 | MAY | 2025-04-17 | RALLISO | U140273 | 2025-03-24 | 2025-04-14 | 2025-05-05 |  | RALLISO | 2025-04-17 | 2025-04-03 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 5.3 | 5 | 1662.7 | 315.16 | 0 | 19.26 | 1328.28 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25322167500 |  | 100339007 |  | 6720212F | 2293756 |  |  | 565 | EX | REPLACE SL/22026239702 | 2600B | MAPLE | 810 MAPLE AV | 067 | LEX | 2025-03-25 | U129722 | U132386 | 2025-03-24 | 2025-12-19 |  |  | DAVID YOUNG | 2025-03-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2585.11 | 0 | 0 | 0 | 2585.11 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25322190500 |  | 100285459 |  | 6764176P |  |  |  | 566 | EX | ABANDON SL - DEMO/FIRE | 2621P | CHERRY | 104 CHERRY ST | 065 | IRV | 2025-04-09 | U930915 | U140273 | 2025-03-24 | 2025-04-14 | 2025-05-05 |  | LCLARK | 2025-04-08 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9.7 | 2 | 1004.5 | 696.02 | 0 | 308.48 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25322254400 |  | 500711438 |  | 7348260H | 2511591 |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | SUNSET | 529 SUNSET DR | 089 | ASH | 2025-03-26 | U124015 | U137248 | 2025-03-24 | 2025-03-24 |  |  | ORA SLONE | 2025-03-24 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 |  | 1 | 2160.23 | 0 | 0 | 0 | 2160.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25322256200 |  | 100453205 |  | 6712208J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | FORT HARRODS | 2108 FORT HARRODS DR | 067 | LEX | 2025-03-25 | U124604 | U137248 | 2025-03-24 | 2025-08-24 | 2027-02-28 |  | JOCHOA | 2025-03-24 | 2025-03-24 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 6.35 | 3 | 678.47 | 396.68 | 258.52 | 23.27 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25322398400 |  | 100455228 |  | 6748204B |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D513707 | 2621P | POCAHONTAS | 11 POCAHONTAS TL | 049 | WIN | 2025-05-30 | U124604 | U137009 | 2025-03-25 | 2025-09-12 | 2027-03-31 |  | NRICHIE | 2025-05-29 | 2025-05-16 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 18.4333 | 6 | 2476.47 | 1426.6 | 272.12 | 82.59 | 695.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25322426000 |  | 100337926 |  | 6712216B |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | BRADLEY | 158 BRADLEY LN | 067 | LEX | 2025-05-06 | JGILES | U140273 | 2025-03-25 | 2025-04-15 | 2025-05-06 |  | JGILES | 2025-05-06 | 2025-04-03 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 20.85 | 6 | 1622.44 | 1170.86 | 17.9 | 433.68 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25322456300 |  | 500191389 |  | 6744208I |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTRQD | 2621P | ARBOR | 203 ARBOR CT | 049 | WIN | 2025-04-10 | U930915 | U140273 | 2025-03-25 | 2025-04-15 | 2025-05-06 |  | LCLARK | 2025-04-09 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.7333 | 2 | 3856.92 | 408.72 | 0 | 353.45 | 3094.75 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25322482900 |  | 100268653 |  | 7356256G |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | WINCHESTER | 2925< WINCHESTER AV | 019 | ASH | 2025-04-18 | ABHATFIE | U140273 | 2025-03-25 | 2025-04-15 | 2025-05-06 |  | ABHATFIE | 2025-04-18 | 2025-04-16 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.8833 | 2 | 266.1 | 250.79 | 0 | 15.31 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25322484000 |  | 100268654 |  | 7356256G |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | WINCHESTER | 2925 WINCHESTER AV | 019 | ASH | 2025-04-22 | U123688 | U140273 | 2025-03-25 | 2025-04-15 | 2025-05-06 |  | ABHATFIE | 2025-04-16 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 9.6167 | 2 | 2093.84 | 643.31 | 0 | 39.24 | 1411.29 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25322484400 |  | 501365559 |  | 6696212P | 2292756 |  |  | 563 | EX | 1" P LONG GSL CONSTRUCTION | 2600B | SAFFRON | 542 SAFFRON LN LT29 | 239 | VER | 2025-04-09 | U123111 | U132627 | 2025-03-25 | 2025-03-27 | 2025-04-09 |  | LYN STAFFORD | 2025-04-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 5 | 1 | 3957.45 | 326.86 | 297.73 | 19.95 | 3312.91 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25322484600 |  | 501365560 |  | 6696212P | 2292756 |  |  | 563 | EX | 1" P LONG GSL CONSTRUCTION | 2600B | SAFFRON | 546 SAFFRON LN LT30 | 239 | VER | 2025-04-09 | U123111 | U132627 | 2025-03-25 | 2025-03-27 | 2025-04-09 |  | LYN STAFFORD | 2025-04-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 3519.08 | 0 | 297.73 | 0 | 3221.35 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25322484700 |  | 501365561 |  | 6696212P | 2292756 |  |  | 563 | EX | 1" P LONG GSL CONSTRUCTION | 2600B | SAFFRON | 550 SAFFRON LN LT31 | 239 | VER | 2025-04-09 | U123111 | U132627 | 2025-03-25 | 2025-03-27 | 2025-04-09 |  | LYN STAFFORD | 2025-04-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 3513.2 | 0 | 297.73 | 0 | 3215.47 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25322485200 |  | 100268657 |  | 7356256G |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | WINCHESTER | 2901 WINCHESTER AV | 019 | ASH | 2025-04-28 | U123688 | U140273 | 2025-03-25 | 2025-04-15 | 2025-05-06 |  | ABHATFIE | 2025-04-17 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 16 | 2 | 2111.47 | 1051.12 | 0 | 64.15 | 996.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25323659400 |  | 100306422 |  | 6716212M |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D513730 | 2621P | LAUREL HILL | 836 LAUREL HILL RD | 067 | LEX | 2025-05-01 | U123688 | U124604 | 2025-03-26 | 2025-09-25 | 2027-03-31 |  | JOCHOA | 2025-04-30 | 2025-04-25 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 26.1667 | 5 | 1903.72 | 1475.02 | 338.69 | 90.01 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25323663300 |  | 501347902 |  | 6724204A | 2291616 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | NIGHT HERON | 3412 NIGHT HERON WY | 067 | LEX | 2025-04-10 | U123111 | U126856 | 2025-03-26 | 2025-04-09 | 2025-04-09 |  | LYN STAFFORD | 2025-04-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 3919.17 | 253.38 | 297.73 | 15.46 | 3352.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25323663500 |  | 501347942 |  | 6724204A | 2291616 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | BAY SHOALS | 3421 BAY SHOALS DR | 067 | LEX | 2025-04-10 | U461309 | U126856 | 2025-03-26 | 2025-04-09 | 2025-04-09 |  | RANDALL HUMPHREYS | 2025-04-09 | 2025-04-09 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4.5 | 1 | 2460.15 | 275.72 | 249.39 | 312.19 | 1622.85 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25323664200 |  | 501347940 |  | 6724204A | 2291616 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | BAY SHOALS | 3409 BAY SHOALS DR | 067 | LEX | 2025-04-10 | U461309 | U126856 | 2025-03-26 | 2025-04-09 | 2025-04-09 |  | RANDALL HUMPHREYS | 2025-04-09 | 2025-04-09 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 3.5 | 1 | 1888.22 | 214.47 | 308.51 | 242.81 | 1122.43 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25323673500 |  | 501320332 |  | 6708204K | 2182537 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | BACKSTRETCH | 202 BACKSTRETCH LT61 | 113 | NIC | 2025-04-09 | U123111 | U129531 | 2025-03-26 | 2025-03-27 | 2025-04-09 |  | LYN STAFFORD | 2025-04-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 5 | 1 | 3485.53 | 316.73 | 297.73 | 19.32 | 2851.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25323680400 |  | 100287290 |  | 6720212G |  |  |  | 565 | EX | GRD 1 ON SERVICE | 2621P | MEADOW | 1074 MEADOW LN | 067 | LEX | 2025-03-26 | HSTANFI | U130871 | 2025-03-26 | 2025-03-26 | 2025-03-26 |  | HSTANFI | 2025-03-26 | 2025-03-26 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 29.9667 | 6 | 2675.47 | 1741.26 | 527.99 | 406.22 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25323683700 |  | 501313794 |  | 6716212B |  |  |  | 563 | EX | PAPER W/100298885 | 2600B | TURNER COMMONS | 113 TURNER COMMONS WY 110 | 067 | LEX | 2025-03-26 | U125768 | U127708 | 2025-03-26 | 2025-03-27 | 2025-04-09 |  | OFFICE | 2025-03-26 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26210011 |  | 0
KY | KY - EAST | 2631 | 25323695200 |  | 100245256 |  | 7356256M | 1635077 |  |  | 565 | EX | GRD 1 ON SERVICE | 2621P | TERRACE | 2965 TERRACE BV | 019 | ASH | 2025-03-28 | U124604 | U130871 | 2025-03-26 | 2025-03-26 | 2025-03-26 |  | RECUMP | 2025-03-27 | 2025-03-26 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 10.95 | 3 | 1182.32 | 753.6 | 253.38 | 175.34 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25323704600 |  | 100265302 |  | 7352256J |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D259746 | 2621P | WINSLOW | 1001 WINSLOW RD | 019 | ASH | 2025-03-28 | U124604 | U137009 | 2025-03-26 | 2025-03-28 | 2025-04-16 |  | RECUMP | 2025-03-27 | 2025-03-27 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 23.8 | 3 | 5087.58 | 1709.96 | 163.47 | 556.11 | 2658.04 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25323713600 |  | 100349317 |  | 6748208M |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | BUCKNER | 19 BUCKNER ST 1F | 049 | WIN | 2025-04-18 | U124604 | U137009 | 2025-03-26 | 2025-04-25 |  |  | DENNING | 2025-04-17 | 2025-04-16 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 35.3 | 5 | 6820.04 | 2553.04 | 301.33 | 389.77 | 3575.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25323916100 |  | 100305776 |  | 6712212K |  |  |  | 565 | VO | REPLACE SL-LEAKAGE D512722 | 2621P | MAYWICK VIEW | 1649 MAYWICK VIEW LN | 067 | LEX | 2025-04-22 |  | U124604 | 2025-03-27 | 2025-09-26 | 2027-03-31 |  | MCRAIG | 2025-04-22 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.7167 | 1 | 899.01 | 487.16 | 0 | 411.85 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25323916400 |  | 100305664 |  | 6712212O |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D513720 | 2621P | ALEXANDRIA | 1674 ALEXANDRIA DR 3 | 067 | LEX | 2025-04-22 | U124604 | U124604 | 2025-03-27 | 2025-09-26 | 2027-03-31 |  | SSHIMFE | 2025-04-21 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.3667 | 2 | 3042.02 | 651.51 | 286.86 | 39.77 | 2063.88 | 0 | 0 | 0
KY | KY - EAST | 2633 | 25323933800 |  | 100259370 |  | 7344148I | 2397807 |  |  | 565 | EX | REPLACE W/ 24026345800 | 2600B | REED | 74 REED ST | 071 | DRI | 2025-03-28 | U128523 | U125768 | 2025-03-27 | 2025-12-23 |  |  | BRANDON ROBERTS | 2025-03-27 |  |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 |  | 1 | 1717.2 | 0 | 0 | 0 | 1717.2 | 0 | 0 | 0
KY | KY - EAST | 2633 | 25323934000 |  | 100259367 |  | 7344148I | 2397807 |  |  | 565 | EX | REPLACE W/ 24026345800 | 2600B | REED | 83 REED LN | 071 | DRI | 2025-04-02 | U128523 | U125768 | 2025-03-27 | 2049-12-31 |  |  | BRANDON ROBERTS | 2025-03-27 |  |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 |  | 1 | 2490.49 | 0 | 0 | 0 | 2490.49 | 0 | 0 | 0
KY | KY - EAST | 2633 | 25323934200 |  | 100259372 |  | 7344148I | 2397807 |  |  | 565 | EX | REPLACE W/ 24026345800 | 2600B | KY ROUTE 122 | 7043 KY ROUTE 122 | 071 | DRI | 2025-03-31 | U128523 | U125768 | 2025-03-27 | 2025-12-23 |  |  | BRANDON ROBERTS | 2025-03-28 |  |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 |  | 1 | 2050.89 | 0 | 0 | 0 | 2050.89 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25323972200 |  | 100305945 |  | 6712212P |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CROSS KEYS | 1049 CROSS KEYS RD 1 | 067 | LEX | 2025-03-28 | U124604 | U141869 | 2025-03-27 | 2025-03-27 | 2025-03-27 |  | JOCHOA | 2025-03-27 | 2025-03-27 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 20.5 | 3 | 2301.24 | 1251.6 | 976.23 | 73.41 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25323987700 |  | 100306631 |  | 6716212I |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D303949 | 2621P | PINE MEADOWS | 1440 PINE MEADOWS RD | 067 | LEX | 2025-03-31 | U124604 | U124604 | 2025-03-27 | 2025-03-27 | 2025-03-27 |  | TROE | 2025-03-28 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 39.9667 | 5 | 2701.96 | 2298.73 | 163.45 | 134.7 | 105.08 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25323993600 |  | 100342242 |  | 7240216N |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D341565 | 2621P | WYANDOT | 409 WYANDOT WY | 173 | MT | 2025-05-19 | DENNING | U137009 | 2025-03-27 | 2025-09-26 | 2027-03-31 |  | DENNING | 2025-05-19 | 2025-04-23 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 24.2167 | 7 | 4394.54 | 1938.8 | 1114.56 | 1290.86 | 50.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25323996800 |  | 500679193 |  | 6716208I | 2513335 |  |  | 563 | EX | 20 1" P LONG/PRMT RCVD | 2600B | SEVERN | 501 SEVERN WY | 067 | LEX | 2025-04-29 | U123111 | U132805 | 2025-03-27 | 2025-04-29 | 2025-04-29 |  | LYN STAFFORD | 2025-04-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4.5 | 1 | 3386.72 | 285.03 | 262.73 | 17.4 | 2821.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25323999300 |  | 100245173 |  | 7356256N |  |  |  | 565 | EX | REPAIR SL LINE | 2621P | GROVE | 2629 W GROVE ST | 019 | ASH | 2025-03-28 | ABHATFIE | U141869 | 2025-03-27 | 2025-03-27 | 2025-03-27 |  | ABHATFIE | 2025-03-28 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 23.2333 | 4 | 1864.42 | 1761.21 | 0 | 103.21 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25324002200 |  | 501380128 |  | 6720208E | 2513472 |  |  | 563 | EX | 1 1/4" P SHORT/PRMT RCVD | 2600B | TURKEYFOOT | 989 TURKEYFOOT RD | 067 | LEX | 2025-05-02 | U123111 | U126856 | 2025-03-27 | 2025-05-07 | 2025-05-07 |  | LYN STAFFORD | 2025-05-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 3698.36 | 553.92 | 447.79 | 32.08 | 2664.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25324141300 |  | 100306638 |  | 6716212I |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D524344 | 2621P | PINE MEADOWS | 1412 PINE MEADOWS RD | 067 | LEX | 2025-04-25 | U124604 | U124604 | 2025-03-28 | 2025-09-26 | 2027-03-31 |  | TROE | 2025-04-24 | 2025-04-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.2833 | 5 | 1033.45 | 761.05 | 225.94 | 46.46 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25324148500 |  | 100312528 |  | 6716208F |  |  |  | 565 | EX | AOC METER MOVE OUT/RELOCATE | 2621P | SHERIDAN | 359 SHERIDAN DR | 067 | LEX | 2025-04-23 | U930915 | U124604 | 2025-03-28 | 2025-12-31 |  |  | CHEMMER | 2025-04-22 | 2025-04-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 22.2167 | 6 | 1795.66 | 1353.24 | 359.84 | 82.58 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25324158900 |  | 501346251 |  | 6728208I | 2396366 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | TWILIGHT SHADO | 1210 TWILIGHT SHADO DR LT146 | 067 | LEX | 2025-04-14 | U123111 | U128272 | 2025-03-28 | 2025-04-01 | 2025-04-14 |  | LYN STAFFORD | 2025-04-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 2189.42 | 253.38 | 297.73 | 15.46 | 1622.85 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25324159200 |  | 100455163 |  | 16684228D |  |  |  | 563 | EX | 1"P SHORT/NO PRMT REQ | 2600B | FIELDS | 818 FIELDS AV | 073 | FRA | 2025-04-15 | U123111 | U128266 | 2025-03-28 | 2025-04-01 | 2025-04-14 |  | LYN STAFFORD | 2025-04-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 5 | 1 | 2208.94 | 326.86 | 401.41 | 19.95 | 1460.72 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25324186700 |  | 100242294 |  | 7356252H | 2513011 |  |  | 563 | EX | 1" P SHORT | 2621P | MITCHELL | 1128 MITCHELL ST | 019 | CAT | 2025-04-18 | DYOUNG | U129531 | 2025-03-28 | 2025-03-28 | 2025-04-18 |  | MCOLLET | 2025-04-17 | 2025-04-16 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 17.9 | 4 | 3333.56 | 1203.11 | 18.95 | 2111.5 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25324202700 |  | 100302172 |  | 6712212L |  |  |  | 563 | EX | 1" PMMP /NO PRMT REQ | 2600B | VERSAILLES | 2089 VERSAILLES RD FT | 067 | LEX | 2025-05-01 | U126284 | U128272 | 2025-03-28 | 2025-04-01 | 2025-04-28 |  | JOSH PASLEY | 2025-05-01 | 2025-04-30 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 10.8833 | 2 | 7054.53 | 771.61 | 0 | 45.28 | 6237.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25324388800 |  | 100459766 |  | 6704212L |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D514601 | 2621P | WYSE | 3864 WYSE SQ | 067 | LEX | 2025-04-30 | U123688 | U124604 | 2025-03-31 | 2025-09-26 | 2027-03-31 |  | DJOHNSON | 2025-04-29 | 2025-04-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.6167 | 5 | 1852.68 | 1359.08 | 0 | 493.6 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25324408200 |  | 100458788 |  | 6712212L |  |  |  | 566 | EX | RETIRE SERVICE LINE - LEAKAGE | 2621P | OXFORD | 1816 OXFORD CR | 067 | LEX | 2025-04-03 | U123688 | U129939 | 2025-03-31 | 2025-03-31 | 2025-04-18 |  | DMEDLEY | 2025-03-31 | 2025-03-31 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9 | 4 | 1378.41 | 1001.72 | 0 | 376.69 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25324443500 |  | 100312242 |  | 6716208I |  |  |  | 565 | EX | REPLACE SERVICE /MMO | 2621P | SOUTHVIEW | 2542 SOUTHVIEW DR | 067 | LEX | 2025-04-28 | U123688 | U124604 | 2025-03-31 | 2025-06-30 |  |  | RJCRAWF | 2025-04-24 | 2025-04-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 27.7 | 7 | 1792.72 | 1530.11 | 169.26 | 93.35 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25324462400 |  | 100281892 |  | 6712232O | 1855043 |  |  | 566 | EX | ABANDON SL - SOII/INSIDE | 2621P | MAIN | 434 MAIN AV | 209 | GEO | 2025-05-05 | DCOLLIN | U132554 | 2025-03-31 | 2025-06-13 | 2025-06-15 |  | DCOLLIN | 2025-05-05 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 24 | 3 | 2972.37 | 1917.56 | 0 | 334.81 | 720 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25324585000 |  | 100415442 |  | 7336268H |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | US ROUTE 23 | 505 US ROUTE 23 | 089 | GRE | 2025-04-02 | U124604 | DYOUNG | 2025-04-01 | 2025-03-26 | 2025-04-13 |  | RECUMP | 2025-04-01 | 2025-03-31 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 12.8167 | 3 | 196.21 | 14.7 | 174.4 | 7.11 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25324613800 |  | 501279257 |  | 6700208A | 1856404 |  |  | 563 | EX | 1" PL LONG/NO PRMT REQ | 2600B | HARKNESS | 6014 HARKNESS LN | 239 | VER | 2025-04-23 | U129722 | U125753 | 2025-04-01 | 2025-04-04 | 2025-04-18 |  | DAVID YOUNG | 2025-04-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 4863.23 | 510.09 | 304.57 | 31.13 | 4017.44 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25324617300 |  | 100275640 |  | 6684228F |  |  |  | 563 | EX | 20 1"P SHORT/NO PRMT REQ | 2600B | KENTUCKY | 802 KENTUCKY AV | 073 | FRA | 2025-04-24 | U123111 | U142144 | 2025-04-01 | 2025-04-04 | 2025-04-25 |  | LYN STAFFORD | 2025-04-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4 | 1 | 3532.05 | 261.48 | 401.41 | 15.96 | 2853.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25324655100 |  | 100343260 |  | 7236212G |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D303590 | 2621P | PREWITT | 486 PREWITT PK | 173 | MT | 2025-04-02 | DENNING | U137009 | 2025-04-01 | 2025-04-01 | 2025-04-01 |  | DENNING | 2025-04-02 | 2025-04-02 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 15.4667 | 3 | 3064.46 | 1110.12 | 426.04 | 679.8 | 848.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25324657800 |  | 100302555 |  | 6712212G |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | NICE | 1272 NICE DR | 067 | LEX | 2025-04-16 | U124604 | U124604 | 2025-04-01 | 2025-12-31 |  |  | HSTANFI | 2025-04-15 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.6667 | 3 | 1700.23 | 1387.8 | 227.88 | 84.55 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25324658400 |  | 100352030 |  | 6744208E |  |  |  | 565 | EX | REPLACE SERVICE | 2621P | WINCHESTER | 8 WINCHESTER PZ F | 049 | WIN | 2025-04-03 | U123688 | U123688 | 2025-04-01 | 2025-01-09 |  |  | HSTANFI | 2025-01-13 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26290031 |  | 1 | 92.72 | 86.99 | 0 | 5.73 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25324788000 |  | 100306575 |  | 6716212I |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D514348 | 2621P | SUMMERVILLE | 841 SUMMERVILLE DR | 067 | LEX | 2025-05-01 | U123688 | U124604 | 2025-04-02 | 2025-10-01 | 2027-04-30 |  | DUSTIN JOHNSON | 2025-05-01 | 2025-04-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 37.1 | 9 | 3230.15 | 2054.39 | 435.82 | 739.94 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25324791100 |  | 100343259 |  | 7236212C |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D333421 | 2621P | PREWITT | 478 PREWITT PK | 173 | MT | 2025-06-10 | DENNING | U137009 | 2025-04-02 | 2025-10-01 | 2027-04-30 |  | DENNING | 2025-06-10 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 18.6 | 3 | 6274.12 | 1389.77 | 346.66 | 931.94 | 3605.75 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25324795300 |  | 100435586 |  | 7236212L |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | FOGG | 1477 FOGG PK | 173 | MT | 2025-04-02 | DENNING | U129939 | 2025-04-02 | 2025-04-02 |  |  | DENNING | 2025-04-02 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.1333 | 2 | 297.17 | 160.57 | 0 | 136.6 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25324806300 |  | 501169535 |  | 7356256A |  |  |  | 563 | EX | 1" P LONG | 2621P | ASHLAND | 920 ASHLAND AV | 019 | ASH | 2025-04-17 | U124604 | U130192 | 2025-04-02 | 2025-04-16 | 2025-04-16 |  | ABHATFIE | 2025-04-16 | 2025-04-14 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 30.2 | 5 | 5044.81 | 1988.43 | 298.33 | 226.06 | 2531.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25324808800 |  | 501312434 |  | 6712212I | 2407033 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | WINNERS | 1600 WINNERS CR LT40 | 067 | LEX | 2025-04-16 | U129673 | U126856 | 2025-04-02 | 2025-04-04 | 2025-04-17 |  | A WILLIAMSON | 2025-04-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 3.75 | 1 | 2544.67 | 241.15 | 502.29 | 59.24 | 1741.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25324808900 |  | 501312435 |  | 6712212I | 2179179 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | WINNERS | 1602 WINNERS CR LT41 | 067 | LEX | 2025-04-16 | U129673 | U126856 | 2025-04-02 | 2025-04-04 | 2025-04-17 |  | A WILLIAMSON | 2025-04-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 1.5 | 1 | 2346.82 | 96.47 | 502.29 | 23.71 | 1724.35 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25324809000 |  | 501312436 |  | 6712212I | 2398229 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | WINNERS | 1604 WINNERS CR LT42 | 067 | LEX | 2025-04-16 | U129673 | U126856 | 2025-04-02 | 2025-04-04 | 2025-04-17 |  | A WILLIAMSON | 2025-04-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 1.45 | 1 | 2342.82 | 93.27 | 502.29 | 22.91 | 1724.35 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25324812100 |  | 501364874 |  | 6724212I |  |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | PATCHEN LAKE | 2235 PATCHEN LAKE LN | 067 | LEX | 2025-04-16 | U129673 | U126856 | 2025-04-02 | 2025-04-04 | 2025-04-17 |  | A WILLIAMSON | 2025-04-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4.3 | 1 | 5580.79 | 276.54 | 150.74 | 67.91 | 5085.6 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25324812600 |  | 501317386 |  | 6716236J | 2178365 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | FLAMINGO | 103 FLAMINGO CR | 209 | GEO | 2025-04-18 | U126284 | U126856 | 2025-04-02 | 2025-04-07 | 2025-04-18 |  | JOSH PASLEY | 2025-04-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 5.1333 | 1 | 2043.34 | 346.19 | 0 | 21.12 | 1676.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325005200 |  | 100323418 |  | 6716208O |  |  |  | 565 | EX | SERVICE LINE/METER UPGRADE | 2621P | BRAEMER | 3345 BRAEMER DR | 067 | LEX | 2025-04-23 | U124604 | U124604 | 2025-04-03 | 2025-04-24 | 2025-04-24 |  | MSHARON | 2025-04-22 | 2025-04-22 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 17.9333 | 3 | 1107.62 | 994.94 | 51.97 | 60.71 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325007800 |  | 100327565 |  | 6720212M |  |  |  | 566 | EX | ABONDON SL/IDLE INACTIVE | 2621P | CENTRAL | 707 CENTRAL AV 1-1FR | 067 | LEX | 2025-04-28 | U123688 | U131178 | 2025-04-03 | 2025-05-02 |  |  | RJCRAWF | 2025-04-25 | 2025-04-10 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 24.3667 | 6 | 2194.86 | 1474.86 | 0 | 90 | 630 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25325008700 |  | 100345380 |  | 6696212H |  |  |  | 566 | EX | ABANDON SL IDLE/INACTIVE | 2621P | DOUGLAS | 221 DOUGLAS AV 2F | 239 | VER | 2025-04-28 | U123688 | U131178 | 2025-04-03 | 2025-05-02 |  |  | SLBARKER | 2025-04-23 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2621 | 25325032200 |  | 501361949 |  | 6716216E | 2403608 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | DAHLIA | 705 DAHLIA DR | 067 | LEX | 2025-04-17 | U129673 | U126856 | 2025-04-03 | 2025-04-07 | 2025-04-18 |  | A WILLIAMSON | 2025-04-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 2.8667 | 1 | 3706.82 | 183.25 | 291.02 | 45.01 | 3187.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325032300 |  | 501361950 |  | 6716216E | 2403608 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | DAHLIA | 709 DAHLIA DR | 067 | LEX | 2025-04-17 | U129673 | U126856 | 2025-04-03 | 2025-04-07 | 2025-04-18 |  | A WILLIAMSON | 2025-04-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 2.5167 | 1 | 3661.18 | 160.75 | 291.02 | 39.51 | 3169.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325032500 |  | 501361951 |  | 6716216E | 2403608 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | DAHLIA | 713 DAHLIA DR | 067 | LEX | 2025-04-18 | U129673 | U126856 | 2025-04-03 | 2025-04-07 | 2025-04-18 |  | A WILLIAMSON | 2025-04-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4.4667 | 1 | 3961.83 | 286.14 | 291.02 | 70.29 | 3314.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325046600 |  | 100328347 |  | 6720208F |  |  |  | 565 | EX | REPLACE SERVICE | 2621P | COOPER | 1340 COOPER DR | 067 | LEX | 2025-04-29 | U123688 | U124604 | 2025-04-03 | 2025-04-30 |  |  | RJCRAWF | 2025-04-28 | 2025-04-21 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 26.7833 | 4 | 9750.08 | 1472.55 | 861.43 | 89.86 | 7326.24 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25325073400 |  | 500186838 |  | 6736252O |  |  |  | 563 | EX | 1" P SHORT | 2621P | CULPEPPER | 268 CULPEPPER DR | 097 | CYN | 2025-04-16 | U124604 | U134341 | 2025-04-03 | 2025-04-17 | 2025-04-17 |  | NRICHIE | 2025-04-15 | 2025-04-14 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 10.5167 | 3 | 2361.97 | 700.58 | 272.12 | 42.75 | 1346.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325078300 |  | 501380363 |  | 6724204F |  |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | WESTON | 380 WESTON PK | 067 | LEX | 2025-04-22 | U123111 | U127708 | 2025-04-03 | 2025-04-09 | 2025-04-22 |  | LYN STAFFORD | 2025-04-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 2 | 1 | 3649.11 | 126.69 | 297.73 | 7.75 | 3216.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325080200 |  | 501380364 |  | 6724204F |  |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | WESTON | 3709 WESTON CT | 067 | LEX | 2025-04-22 | U123111 | U127708 | 2025-04-03 | 2025-04-09 | 2025-04-22 |  | LYN STAFFORD | 2025-04-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 3 | 1 | 2165.12 | 190.05 | 297.73 | 11.6 | 1665.74 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25325200400 |  | 500010884 |  | 7356256M |  |  |  | 565 | EX | AOC ENCROACHMENT REMEDIA | 2621P | BELMONT | 2930 S BELMONT ST | 019 | ASH | 2025-05-07 | U141668 | U123688 | 2025-04-04 | 2025-06-02 | 2025-06-02 |  | RECUMP | 2025-05-06 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 16.5 | 3 | 1783.37 | 1120.49 | 190.14 | 472.74 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325300300 |  | 100295210 |  | 6716212H | 2513548 |  |  | 563 | EX | 1.25" P LONG/PRMT RCVD | 2600B | 4TH | 505 W 4TH ST | 067 | LEX | 2025-05-08 | U128336 | U129294 | 2025-04-04 | 2025-05-07 | 2025-05-07 |  | JOSHUA COX | 2025-05-07 | 2025-05-06 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 8551.7 | 548.16 | 825.32 | 31.74 | 7146.48 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25325308600 |  | 501258081 |  | 6700208A | 1856404 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | ROSE RIDGE | 1013 ROSE RIDGE RD | 239 | VER | 2025-04-17 | U129673 | U128266 | 2025-04-04 | 2025-04-07 | 2025-04-18 |  | A WILLIAMSON | 2025-04-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 2.6167 | 1 | 4748.77 | 175.84 | 346.52 | 42.2 | 4184.21 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325457300 |  | 100297582 |  | 6716212H | 2512340 |  |  | 565 | EX | NBT SERVICE LINE/METER UPGRADE | 2621P | 3RD | 536 W 3RD ST | 067 | LEX | 2025-04-30 | U123688 | U124604 | 2025-04-07 | 2025-05-30 |  |  | HSTANFI | 2025-04-29 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 30.2667 | 6 | 10344.73 | 1617.37 | 230.06 | 98.69 | 8398.61 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325489000 |  | 501355464 |  | 6712204J | 2398051 |  |  | 563 | EX | 1' P LONG/NO PRMT REQ | 2600B | CANVASBACK | 117 CANVASBACK DR LT56 | 113 | NIC | 2025-05-01 | U123111 | U133050 | 2025-04-07 | 2025-04-09 | 2025-04-22 |  | LYN STAFFORD | 2025-04-30 | 2025-04-30 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 3451.11 | 253.37 | 300 | 15.45 | 2882.29 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25325496400 |  | 501350519 |  | 6716232J | 2398315 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | OXFORD LANDING | 172 OXFORD LANDING DR | 209 | GEO | 2025-04-21 | U123111 | U126856 | 2025-04-07 | 2025-04-22 | 2025-04-22 |  | LYN STAFFORD | 2025-04-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4 | 1 | 4187.91 | 261.48 | 401.41 | 15.95 | 3509.07 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25325496700 |  | 501350533 |  | 6716232J | 2398315 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | OXFORD LANDING | 161 OXFORD LANDING DR | 209 | GEO | 2025-04-21 | U123111 | U126856 | 2025-04-07 | 2025-04-22 | 2025-04-22 |  | LYN STAFFORD | 2025-04-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 1420.16 | 0 | 297.73 | 0 | 1122.43 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25325496900 |  | 501350534 |  | 6716232J | 2398315 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | OXFORD LANDING | 159 OXFORD LANDING DR | 209 | GEO | 2025-04-22 | U123111 | U126856 | 2025-04-07 | 2025-04-22 | 2025-04-22 |  | LYN STAFFORD | 2025-04-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 2 | 1 | 1573.6 | 130.75 | 297.73 | 7.99 | 1137.13 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25325497100 |  | 501350535 |  | 6716232J | 2398315 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | OXFORD LANDING | 157 OXFORD LANDING DR | 209 | GEO | 2025-04-22 | U123111 | U126856 | 2025-04-07 | 2025-04-22 | 2025-04-22 |  | LYN STAFFORD | 2025-04-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 3 | 1 | 1650.31 | 196.12 | 297.73 | 11.98 | 1144.48 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25325497300 |  | 501350536 |  | 6716232J | 2398315 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | OXFORD LANDING | 155 OXFORD LANDING DR | 209 | GEO | 2025-04-18 | U126284 | U126856 | 2025-04-07 | 2025-04-22 | 2025-04-22 |  | JOSH PASLEY | 2025-04-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 2.8667 | 1 | 1869.44 | 194.76 | 0 | 11.88 | 1662.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25325498400 |  | 501278633 |  | 6716232J |  |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | SILVER SPRING | 122 SILVER SPRING WY | 209 | GEO | 2025-04-21 | U123111 | U126856 | 2025-04-07 | 2025-04-22 | 2025-04-22 |  | LYN STAFFORD | 2025-04-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4.5 | 1 | 3810.62 | 294.16 | 297.73 | 17.96 | 3200.77 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25325501600 |  | 100267377 |  | 7352260I |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | PRINCESS | 200 PRINCESS DR | 089 | ASH | 2025-04-15 | MCOLLET | U129939 | 2025-04-07 | 2025-04-02 |  |  | MCOLLET | 2025-04-15 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 30.2667 | 4 | 12875.02 | 1978.63 | 237.88 | 2529.41 | 8129.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325504500 |  | 500022432 |  | 6708204L |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | WOODSIDE | 103 WOODSIDE WY | 113 | NIC | 2025-04-17 | DMEDLEY | U140273 | 2025-04-07 | 2025-04-28 | 2025-05-19 |  | DMEDLEY | 2025-04-17 | 2025-04-14 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.8667 | 4 | 1209.97 | 794.95 | 0 | 415.02 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25325515400 |  | 501371484 |  | 7356252F | 2408804 |  |  | 563 | EX | 99 1" P LONG HP MAIN | 2621P | CATLETTS CRK | 4510 CATLETTS CRK | 019 | CAT | 2025-04-25 | U124604 | U134375 | 2025-04-07 | 2025-04-21 | 2025-05-05 |  | MCOLLET | 2025-04-24 | 2025-04-24 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 43.75 | 4 | 6997.63 | 3035.39 | 399.92 | 3239.68 | 322.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325541800 |  | 501334655 |  | 6716216E | 2289300 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | DAHLIA | 653 DAHLIA DR | 067 | LEX | 2025-04-24 | U123111 | U126856 | 2025-04-07 | 2025-04-09 | 2025-04-22 |  | LYN STAFFORD | 2025-04-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 4102.04 | 253.38 | 297.73 | 15.46 | 3535.47 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325542000 |  | 501334656 |  | 6716216E | 2289300 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | DAHLIA | 659 DAHLIA DR | 067 | LEX | 2025-04-18 | U129673 | U126856 | 2025-04-07 | 2025-04-09 | 2025-04-22 |  | A WILLIAMSON | 2025-04-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 3.5333 | 1 | 3848.6 | 228.28 | 291.02 | 56.08 | 3273.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325645000 |  | 501347263 |  | 6712204E | 2397231 |  |  | 563 | EX | 1" P LONG (JIMMY NASH HOMES) | 2600B | POLLY | 100 POLLY CT | 113 | NIC | 2025-04-24 | U123111 | U126856 | 2025-04-08 | 2025-04-10 | 2025-04-23 |  | LYN STAFFORD | 2025-04-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 3889.78 | 253.39 | 297.73 | 15.46 | 3323.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325656700 |  | 100465180 |  | 6716200D |  |  |  | 565 | EX | REPAIR/REPLACE SERVICE LINE | 2621P | CHARWOOD | 4608 CHARWOOD CT | 067 | LEX | 2025-04-08 | TROE | U139677 | 2025-04-08 | 2025-04-08 | 2025-04-08 |  | TROE | 2025-04-08 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.65 | 3 | 660.03 | 622.06 | 0 | 37.97 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25325658900 |  | 100360439 |  | 6736228H | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | SUNSET | 2100 SUNSET DR | 017 | PAR | 2025-04-11 | U126530 | U125768 | 2025-04-08 | 2025-12-23 |  |  | JDUNN | 2025-04-08 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4003.54 | 0 | 0 | 0 | 4003.54 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25325678100 |  | 100257519 |  | 7356256A | 1855043 |  |  | 566 | EX | ABANDON SL - | 2621P | DYSARD HILL | 928 DYSARD HILL DR | 019 | ASH | 2025-04-23 | U124604 | U132554 | 2025-04-08 | 2025-07-25 | 2025-07-26 |  | MCOLLET | 2025-04-21 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 8 | 2 | 876.23 | 558.5 | 21.09 | 296.64 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25325678600 |  | 100349649 |  | 6748208M | 1855043 |  |  | 566 | EX | ABANDON SL - SOII/INSIDE | 2621P | GEORGIA | 107 GEORGIA ST | 049 | WIN | 2025-04-22 | DENNING | U132554 | 2025-04-08 | 2025-05-30 | 2025-06-01 |  | DENNING | 2025-04-22 | 2025-04-22 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 16.0667 | 3 | 1943.27 | 1288.33 | 0 | 654.94 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 25325691500 |  | 100240944 |  | 7324132H |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | HIGHWAY 550 E | 2028 HIGHWAY 550 E DOWNSTA | 119 | LEB | 2025-06-02 | JAHOWARD | U123688 | 2025-04-08 | 2025-05-08 | 2025-05-08 |  | JAHOWARD | 2025-06-02 | 2025-06-02 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 16.1833 | 2 | 3984.23 | 1296 | 0 | 75.99 | 2612.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325805500 |  | 100462125 |  | 6720200A |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D514349 | 2621P | CHARWOOD | 950 CHARWOOD DR | 067 | LEX | 2025-06-06 | U124604 | U124604 | 2025-04-09 | 2025-10-08 | 2027-04-30 |  | JBURFOR | 2025-06-05 | 2025-05-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.95 | 3 | 981.97 | 927.61 | 0 | 54.36 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325806200 |  | 100461241 |  | 6716200D |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D514553 | 2621P | CHARWOOD | 915 CHARWOOD DR | 067 | LEX | 2025-06-05 | U124604 | U124604 | 2025-04-09 | 2025-10-08 | 2027-04-30 |  | JBURFOR | 2025-06-04 | 2025-06-04 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.2333 | 2 | 1232.13 | 721.51 | 309.97 | 42.29 | 158.36 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25325809900 |  | 100423148 |  | 6744208P |  |  |  | 565 | EX | GRADE 1 REPLACE | 2621P | DIXIE | 9 DIXIE ST | 049 | WIN | 2025-04-10 | U124604 | U129939 | 2025-04-09 | 2025-04-09 | 2025-04-09 |  | LCLARK | 2025-04-09 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 14.2333 | 2 | 2496.18 | 1022.47 | 413.39 | 884.2 | 176.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25325827900 |  | 501338357 |  | 6716232B | 2179247 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | DUNMORE | 123 DUNMORE LN LT189 | 209 | GEO | 2025-04-28 | U123111 | U129294 | 2025-04-09 | 2025-04-23 | 2025-04-23 |  | LYN STAFFORD | 2025-04-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 2 | 1 | 2945.28 | 130.74 | 297.73 | 7.99 | 2508.82 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25325828200 |  | 501338361 |  | 6716232B | 2179247 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | DUNMORE | 115 DUNMORE LN LT193 | 209 | GEO | 2025-05-01 | U129673 | U129294 | 2025-04-09 | 2025-04-23 | 2025-04-23 |  | A WILLIAMSON | 2025-05-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 3591.35 | 586.66 | 304.45 | 146.64 | 2553.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325836300 |  | 100320733 |  | 6716212L |  |  |  | 566 | EX | MAS ABDN- DEMO/CUSTRQD | 2621P | STONE | 251 STONE AV 1F | 067 | LEX | 2025-05-30 | U930915 | U140273 | 2025-04-09 | 2025-04-30 | 2025-05-31 |  | HMCKUNE | 2025-05-27 | 2025-04-16 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.0333 | 6 | 1284.28 | 167.26 | 15.08 | 15.94 | 1086 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325836600 |  | 100320736 |  | 6716212L |  |  |  | 566 | EX | PAP ABDN- DEMO/CUSTRQD | 2621P | STONE | 251 STONE AV 2F | 067 | LEX | 2025-05-30 | U930915 | U140273 | 2025-04-09 | 2025-04-30 | 2025-05-31 |  | HMCKUNE | 2025-05-30 | 2025-04-16 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.3167 | 3 | 562.56 | 78.58 | 15.08 | 4.68 | 464.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325838900 |  | 500284098 |  | 6716212L |  |  |  | 566 | EX | PAP ABDN- DEMO/CUSTRQD | 2621P | MAXWELL | 231 E MAXWELL ST 3-2F | 067 | LEX | 2025-05-22 | SSHIMFE | U140273 | 2025-04-09 | 2025-04-30 | 2025-05-31 |  | SSHIMFE | 2025-05-22 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.1 | 2 | 5.84 | 5.54 | 0 | 0.3 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325839400 |  | 500284099 |  | 6716212L |  |  |  | 566 | EX | PAP ABDN- DEMO/CUSTRQD | 2621P | MAXWELL | 231 E MAXWELL ST 4-3F | 067 | LEX | 2025-05-23 | U124604 | U140273 | 2025-04-09 | 2025-04-30 | 2025-05-31 |  | SSHIMFE | 2025-05-22 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.26667 | 2 | 33.24 | 14.51 | 17.9 | 0.83 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325839500 |  | 500283519 |  | 6716212L |  |  |  | 566 | EX | PAP ABDN- DEMO/CUSTRQD | 2621P | MAXWELL | 231 E MAXWELL ST 2-1F | 067 | LEX | 2025-05-22 | SSHIMFE | U140273 | 2025-04-09 | 2025-04-30 | 2025-05-31 |  | SSHIMFE | 2025-05-22 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.1 | 2 | 5.84 | 5.54 | 0 | 0.3 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325840400 |  | 100321036 |  | 6716212L |  |  |  | 566 | EX | MAS ABDN- DEMO/CUSTRQD | 2621P | MAXWELL | 231 E MAXWELL ST BSMT | 067 | LEX | 2025-05-23 | U124604 | U140273 | 2025-04-09 | 2025-04-30 | 2025-05-31 |  | SSHIMFE | 2025-05-22 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.16667 | 2 | 530.35 | 10.06 | 38.99 | 0.58 | 480.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325842500 |  | 100321047 |  | 6716212L |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | MAXWELL | 211 E MAXWELL ST | 067 | LEX | 2025-05-23 | U124604 | U140273 | 2025-04-09 | 2025-04-30 | 2025-05-31 |  | SSHIMFE | 2025-05-22 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.46667 | 2 | 1574.41 | 25.69 | 38.99 | 1.51 | 1508.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325844200 |  | 100321048 |  | 6716212L |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | MAXWELL | 209 E MAXWELL ST | 067 | LEX | 2025-05-23 | U124604 | U140273 | 2025-04-09 | 2025-04-30 | 2025-05-31 |  | SSHIMFE | 2025-05-22 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.3 | 2 | 750.81 | 16.75 | 20.38 | 0.96 | 712.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325844700 |  | 100321046 |  | 6716212L |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | MAXWELL | 215 E MAXWELL ST 1 | 067 | LEX | 2025-05-23 | U124604 | U140273 | 2025-04-09 | 2025-04-30 | 2025-05-31 |  | SSHIMFE | 2025-05-22 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.33333 | 2 | 505.57 | 17.83 | 38.99 | 1.03 | 447.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325847500 |  | 100462581 |  | 6716212L |  |  |  | 566 | EX | PAP ABDN- DEMO/CUSTRQD | 2621P | MAXWELL | 207 E MAXWELL ST 2 | 067 | LEX | 2025-05-23 | U124604 | U140273 | 2025-04-09 | 2025-04-30 | 2025-05-31 |  | SSHIMFE | 2025-05-22 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.2 | 2 | 510.42 | 11.17 | 17.9 | 0.63 | 480.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325848000 |  | 100321049 |  | 6716212L |  |  |  | 566 | EX | MAS ABDN- DEMO/CUSTRQD | 2621P | MAXWELL | 207 E MAXWELL ST 1 | 067 | LEX | 2025-05-23 | U124604 | U140273 | 2025-04-09 | 2025-04-30 | 2025-05-31 |  | SSHIMFE | 2025-05-22 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.36667 | 2 | 60.26 | 20.1 | 38.99 | 1.17 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325848300 |  | 100321050 |  | 6716212L |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | MAXWELL | 201 E MAXWELL ST | 067 | LEX | 2025-05-23 | U124604 | U140273 | 2025-04-09 | 2025-04-30 | 2025-05-31 |  | SSHIMFE | 2025-05-22 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 17.7 | 2 | 1898.82 | 988.17 | 38.99 | 57.22 | 814.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325849400 |  | 100321041 |  | 6716212L |  |  |  | 566 | EX | MAS ABDN- DEMO/CUSTRQD | 2621P | MAXWELL | 221 E MAXWELL ST 2F | 067 | LEX | 2025-05-23 | U124604 | U140273 | 2025-04-09 | 2025-04-30 | 2025-05-31 |  | SSHIMFE | 2025-05-22 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.16667 | 2 | 28.54 | 10.06 | 17.9 | 0.58 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325849800 |  | 500284568 |  | 6716212L |  |  |  | 566 | EX | PAP ABDN- DEMO/CUSTRQD | 2621P | MAXWELL | 221 E MAXWELL ST 1F | 067 | LEX | 2025-05-23 | U124604 | U140273 | 2025-04-09 | 2025-04-30 | 2025-05-31 |  | SSHIMFE | 2025-05-22 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.16667 | 2 | 49.63 | 10.06 | 38.99 | 0.58 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325851300 |  | 100321040 |  | 6716212L |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | MAXWELL | 225 E MAXWELL ST | 067 | LEX | 2025-05-23 | U124604 | U140273 | 2025-04-09 | 2025-04-30 | 2025-05-31 |  | SSHIMFE | 2025-05-22 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.5 | 2 | 68.58 | 27.94 | 38.99 | 1.65 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325852000 |  | 100321039 |  | 6716212L |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | MAXWELL | 227 E MAXWELL ST 1F | 067 | LEX | 2025-05-23 | U124604 | U140273 | 2025-04-09 | 2025-04-30 | 2025-05-31 |  | SSHIMFE | 2025-05-22 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.16667 | 2 | 49.63 | 10.06 | 38.99 | 0.58 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25325852300 |  | 500432369 |  | 7352260N | 2409717 |  |  | 563 | EX | 1" P SHORT 2ND ATP | 2621P | SARAH | 777 SARAH RD | 019 | ASH | 2025-06-04 | U124604 | U132258 | 2025-04-09 | 2025-04-10 | 2025-12-25 |  | MCOLLET | 2025-06-03 | 2025-06-03 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 34.5 | 4 | 3090.74 | 2510.72 | 432.83 | 147.19 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25325853800 |  | 501358756 |  | 6700212O | 2398395 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | GLASBURY | 318 GLASBURY LN | 239 | VER | 2025-05-01 | U123111 | U126856 | 2025-04-09 | 2025-04-23 | 2025-04-23 |  | LYN STAFFORD | 2025-05-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 3310.01 | 589.84 | 297.73 | 34.16 | 2388.28 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25325854000 |  | 501358747 |  | 6700212O | 2398395 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | GLASBURY | 317 GLASBURY LN | 239 | VER | 2025-04-24 | U123111 | U126856 | 2025-04-09 | 2025-04-23 | 2025-04-23 |  | LYN STAFFORD | 2025-04-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 2.5 | 1 | 2089.61 | 163.45 | 297.73 | 9.99 | 1618.44 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25325854200 |  | 501358750 |  | 6700212O | 2398395 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | GLASBURY | 305 GLASBURY LN | 239 | VER | 2025-04-24 | U123111 | U126856 | 2025-04-09 | 2025-04-23 | 2025-04-23 |  | LYN STAFFORD | 2025-04-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 3 | 1 | 1642.99 | 196.14 | 297.73 | 11.99 | 1137.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325856600 |  | 100320732 |  | 6716212L |  |  |  | 566 | EX | MAS ABDN- DEMO/CUSTRQD | 2621P | STONE | 249 STONE AV 2F | 067 | LEX | 2025-05-28 | U930915 | U140273 | 2025-04-09 | 2025-04-30 | 2025-05-31 |  | HMCKUNE | 2025-05-27 | 2025-05-22 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.1167 | 5 | 964.35 | 893.91 | 15.08 | 55.36 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325857600 |  | 100320731 |  | 6716212L |  |  |  | 566 | EX | PAP ABDN- DEMO/CUSTRQD | 2621P | STONE | 247 STONE AV 1F | 067 | LEX | 2025-05-28 | U124604 | U140273 | 2025-04-09 | 2025-04-30 | 2025-05-31 |  | HMCKUNE | 2025-05-27 | 2025-04-30 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.5 | 5 | 760.1 | 468.68 | 15.08 | 36.34 | 240 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25325858000 |  | 500008795 |  | 6720200A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | WOODGLEN | 961 WOODGLEN CT | 067 | LEX | 2025-04-09 | U930915 | U139701 | 2025-04-09 | 2025-04-09 | 2025-04-09 |  | RJCRAWF | 2025-04-09 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 7.9833 | 2 | 935.63 | 633.26 | 263.74 | 38.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25326046100 |  | 100462121 |  | 6720200A |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D514554KAGE | 2621P | WOODGLEN | 948 WOODGLEN CT | 067 | LEX | 2025-05-08 | U124604 | U124604 | 2025-04-10 | 2025-10-09 | 2027-04-30 |  | JOCHOA | 2025-05-07 | 2025-05-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.5 | 6 | 1581.6 | 1276.05 | 231.63 | 73.92 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25326068400 |  | 100342532 |  | 7240216M |  |  |  | 563 | EX | 1" P LONG | 2621P | HOLT | 209 HOLT AV | 173 | MT | 2025-04-22 | U124604 | U130192 | 2025-04-10 | 2025-04-24 | 2025-04-24 |  | DENNING | 2025-04-21 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 19.9667 | 3 | 2744.35 | 1429.98 | 539 | 775.37 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25326068900 |  | 500291607 |  | 6720208N |  |  |  | 563 | EX | 1" P LONG/PRMT RCVD | 2600B | COLT NECK | 3504 COLT NECK LN | 067 | LEX | 2025-05-12 | U128816 | U134341 | 2025-04-10 | 2025-05-12 | 2025-05-12 |  | OLIVER MAYNARD | 2025-05-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 6.5167 | 1 | 3843.69 | 446.73 | 0 | 25.88 | 3371.08 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25326073300 |  | 500362802 |  | 7348260H | 2513174 |  |  | 563 | EX | 1" P SHORT | 2621P | SHENANDOAH | 109 SHENANDOAH LN | 089 | RUS | 2025-04-25 | JKEENER | U138822 | 2025-04-10 | 2025-04-10 | 2025-04-24 |  | JKEENER | 2025-04-25 | 2025-04-24 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 34.45 | 8 | 2496.62 | 2221.35 | 0 | 275.27 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25326077300 |  | 501374042 |  | 7332284A | 2513714 |  |  | 563 | EX | 1" P LONG | 2621P | HITCHCOCK | 63 HITCHCOCK DR | 089 | S S | 2025-04-25 | U124604 | U138822 | 2025-04-10 | 2025-04-10 | 2025-04-24 |  | RECUMP | 2025-04-24 | 2025-04-21 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 48.3833 | 10 | 3994.12 | 3052.84 | 229.01 | 712.27 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25326084700 |  | 100462316 |  | 6720208I |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D341568 | 2621P | TURKEYFOOT | 1129 TURKEYFOOT RD 10 | 067 | LEX | 2025-04-18 | U124604 | U124604 | 2025-04-10 | 2025-04-11 | 2025-05-01 |  | JOCHOA | 2025-04-17 | 2025-04-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 26.75 | 9 | 4039.54 | 1577.08 | 284.42 | 188.78 | 1989.26 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25326117300 |  | 501355463 |  | 6712204J | 2398051 |  |  | 563 | EX | 20 1"P LONG/NO PRMT REQ | 2600B | CANVASBACK | 113 CANVASBACK DR LT55 | 113 | NIC | 2025-04-28 | U123111 | U142144 | 2025-04-10 | 2025-04-25 | 2025-04-25 |  | LYN STAFFORD | 2025-04-28 | 2025-04-25 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 6 | 2 | 3359.5 | 380.06 | 300.01 | 23.19 | 2656.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25326118300 |  | 100329587 |  | 6720208C | 2403558 |  |  | 565 | EX | REPLACE SL / 24026316701 | 2600B | SAINT MATHILDA | 2035 SAINT MATHILDA DR | 067 | LEX | 2025-04-24 | U128762 | U129939 | 2025-04-10 | 2025-12-23 |  |  | RANDALL TINCHER | 2025-04-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 3202.94 | 0 | 0 | 0 | 3202.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25326331400 |  | 500491211 |  | 6716212H |  |  |  | 566 | EX | ABANDON DL - IDLE/INACTIVE | 2621P | BROADWAY | 426 N BROADWAY ST 4-2F | 067 | LEX | 2025-04-14 | U124604 | U139701 | 2025-04-11 | 2025-04-11 |  |  | HSTANFI | 2025-04-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 1.65 | 3 | 79.2 | 74.64 | 0 | 4.56 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25326332100 |  | 500471503 |  | 6716212H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BROADWAY | 426 N BROADWAY ST 3-2FF | 067 | LEX | 2025-04-14 | U124604 | U139701 | 2025-04-11 | 2025-04-11 |  |  | HSTANFI | 2025-04-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 8.75 | 3 | 421.67 | 397.41 | 0 | 24.26 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25326354900 |  | 501348638 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | CALISTA FLAT | 752 CALISTA FLAT | 067 | LEX | 2025-04-28 | U123111 | U126856 | 2025-04-11 | 2025-04-25 | 2025-04-25 |  | LYN STAFFORD | 2025-04-28 | 2025-04-25 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 6 | 2 | 4288.99 | 380.06 | 297.73 | 23.19 | 3588.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25326384300 |  | 501206379 |  | 6712212M |  |  |  | 563 | EX | 99 1"P SHORT/PRMT RCVD | 2600B | WELLESLEY | 1569 WELLESLEY DR | 067 | LEX | 2025-05-13 | U128816 | U129176 | 2025-04-11 | 2025-05-12 | 2025-05-12 |  | OLIVER MAYNARD | 2025-05-13 | 2025-05-12 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 3.6 | 2 | 2866.19 | 245.31 | 0 | 14.2 | 2606.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25326393300 |  | 100333991 |  | 6720212O |  |  |  | 565 | EX | REPAIR SERVICE LINE | 2621P | LIBERTY | 1122 LIBERTY RD | 067 | LEX | 2025-04-14 | TROE | U139701 | 2025-04-11 | 2025-04-11 | 2025-04-11 |  | TROE | 2025-04-14 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 26.9833 | 5 | 1964.21 | 1436.19 | 26.48 | 87.64 | 413.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25326544000 |  | 500673136 |  | 7344268P | 2513333 |  |  | 563 | EX | 1' P LONG | 2621P | CALUMET | 1436 N CALUMET DR LT73 | 089 | WOR | 2025-05-01 | U123688 | U133050 | 2025-04-14 | 2025-04-28 | 2025-04-28 |  | RECUMP | 2025-04-30 | 2025-04-28 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 30.5 | 6 | 2714.8 | 1913.66 | 295.67 | 398.91 | 106.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25326548200 |  | 501347906 |  | 6724204A | 2291616 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | NIGHT HERON | 3401 NIGHT HERON WY | 067 | LEX | 2025-04-28 | U123111 | U126856 | 2025-04-14 | 2025-04-29 | 2025-04-29 |  | LYN STAFFORD | 2025-04-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 2.25 | 1 | 1552.28 | 142.53 | 297.73 | 8.7 | 1103.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25326600200 |  | 100332142 |  | 720212N |  |  |  | 565 | EX | GRADE 1 REPLACE S-L | 2621P | AURORA | 909 AURORA AV | 067 | LEX | 2025-04-14 | JOCHOA | U129939 | 2025-04-14 | 2025-04-14 | 2025-04-14 |  | JOCHOA | 2025-04-14 | 2025-04-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 35.4833 | 5 | 2564.77 | 1952.58 | 493.04 | 119.15 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25326602400 |  | 100358333 |  | 6740232I |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | FITHIAN | 418 FITHIAN AV | 017 | PAR | 2025-05-13 | U930915 | U137009 | 2025-04-14 | 2025-05-23 | 2025-05-23 |  | NRICHIE | 2025-05-12 | 2025-05-09 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.5333 | 4 | 1983.73 | 659.03 | 38.99 | 38.19 | 1247.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25326613300 |  | 100333037 |  | 6728200D |  |  |  | 563 | EX | 1" P SHORT/NO PRMT NEEDED | 2600B | ATHENS BOONESB | 6329 ATHENS BOONESB RD | 067 | LEX | 2025-04-30 | U123111 | U130192 | 2025-04-14 | 2025-05-01 | 2025-05-01 |  | LYN STAFFORD | 2025-04-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 1697.8 | 253.37 | 297.73 | 15.45 | 1131.25 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25326617100 |  | 100345744 |  | 6696212D |  |  |  | 565 | EX | REPLACE SERVICE LINE D513744 | 2621P | MARCELLA | 783 MARCELLA ST | 239 | VER | 2025-04-22 | U128410 | U124604 | 2025-04-14 | 2025-04-17 | 2025-05-05 |  | CDESPAIN | 2025-04-22 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 22.3 | 2 | 1737.7 | 1637.77 | 0 | 99.93 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 25326621000 |  | 100438777 |  | 7356152E |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | US RT 23 | 12360 US RT 23 S | 071 | HAR | 2025-04-15 | U124604 | U129939 | 2025-04-14 | 2025-04-14 |  |  | JAHOWARD | 2025-04-14 | 2025-04-14 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.71667 | 1 | 1079.63 | 1017.55 | 0 | 62.08 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25326623800 |  | 100279546 |  | 6688228O |  |  |  | 565 | EX | GRADE 1 REPLACE SERVICE LINE | 2621P | REGIO | 100 REGIO CT | 073 | FRA | 2025-04-15 | MCRAIG | U129939 | 2025-04-14 | 2025-04-14 | 2025-04-14 |  | MCRAIG | 2025-04-15 | 2025-04-15 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 29.9167 | 4 | 3329.1 | 1688.34 | 466.34 | 512.18 | 662.24 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25326796200 |  | 100345751 |  | 6696212D |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D341981 | 2621P | MARCELLA | 797 MARCELLA ST | 239 | VER | 2025-04-22 | U128410 | U124604 | 2025-04-15 | 2025-04-17 | 2025-05-05 |  | CDESPAIN | 2025-04-22 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.23333 | 2 | 61.78 | 20.54 | 0 | 1.28 | 39.96 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25326797100 |  | 100345745 |  | 6696212D |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D341982 | 2621P | MARCELLA | 785 MARCELLA ST | 239 | VER | 2025-04-22 | U128410 | U124604 | 2025-04-15 | 2025-04-17 | 2025-05-05 |  | CDESPAIN | 2025-04-22 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.53333 | 2 | 104.43 | 42.65 | 0 | 2.58 | 59.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25326802800 |  | 100463522 |  | 6716200D |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D514567 | 2621P | JAIRUS | 799 JAIRUS DR | 067 | LEX | 2025-05-13 | U124604 | U124604 | 2025-04-15 | 2025-10-14 | 2027-04-30 |  | TROE | 2025-05-12 | 2025-05-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.35 | 6 | 1244.93 | 1043.59 | 80.26 | 60.4 | 60.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25326818900 |  | 501320841 |  | 6728208I | 2182500 |  |  | 563 | EX | 1" P SHORT/PRMT RCVD | 2600B | BUTTERMILK | 4041 BUTTERMILK RD LT9 | 067 | LEX | 2025-05-08 | U123111 | U131378 | 2025-04-15 | 2025-04-29 | 2025-05-14 |  | LYN STAFFORD | 2025-05-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 1650.14 | 276.97 | 299.38 | 16.04 | 1057.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25326849400 |  | 100322767 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE SL W/ 22026238800 | 2600B | SCOVILLE | 1278 SCOVILLE RD | 067 | LEX | 2025-04-15 | U129731 | U125768 | 2025-04-15 | 2025-12-23 |  |  | EDWARD F GOINS | 2025-04-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10 | 1 | 2971.42 | 630.46 | 0 | 38.48 | 2302.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25326866400 |  | 501333760 |  | 6724204A | 2185117 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | NIGHT HERON | 3501 NIGHT HERON WY | 067 | LEX | 2025-04-29 | U123111 | U126856 | 2025-04-15 | 2025-04-29 | 2025-04-29 |  | LYN STAFFORD | 2025-04-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 4074.05 | 253.37 | 297.73 | 15.46 | 3507.49 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25326871600 |  | 501346224 |  | 6728208I | 2396366 |  |  | 563 | EX | 1"P LONG/NO PRMT REQ | 2600B | TWILIGHT SHADO | 1215 TWILIGHT SHADO DR LT119 | 067 | LEX | 2025-04-30 | U126284 | U128266 | 2025-04-15 | 2025-04-16 | 2025-04-30 |  | JOSH PASLEY | 2025-04-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 5.1167 | 1 | 3405.39 | 334.14 | 0 | 20.39 | 3050.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25326872600 |  | 500010690 |  | 6716200D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | FAIRHAVEN | 899 FAIRHAVEN DR | 067 | LEX | 2025-04-16 | U124604 | U129939 | 2025-04-15 | 2025-04-11 | 2025-05-01 |  | JOCHOA | 2025-04-15 | 2025-04-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 5.6667 | 6 | 2072.4 | 1296.89 | 231.63 | 543.88 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25327106500 |  | 100345704 |  | 6696212D |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D341983 | 2621P | JANET | 808 JANET ST | 239 | VER | 2025-04-23 | U128410 | U124604 | 2025-04-16 | 2025-04-17 | 2025-05-06 |  | CDESPAIN | 2025-04-23 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.033333 | 2 | 3.1 | 2.92 | 0 | 0.18 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25327113100 |  | 100345708 |  | 6696212D |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D513745 | 2621P | JANET | 800 JANET ST | 239 | VER | 2025-06-06 | U124604 | U124604 | 2025-04-16 | 2025-10-15 | 2027-04-30 |  | RJCRAWF | 2025-06-05 | 2025-05-20 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 11.0667 | 4 | 1546.25 | 808.89 | 224.2 | 412.52 | 100.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25327115300 |  | 100462117 |  | 6720200A |  |  |  | 565 | EX | REPLACE SL-LEAKAGE | 2621P | JAIRUS | 871 JAIRUS DR | 067 | LEX | 2025-05-15 | U137585 | U124604 | 2025-04-16 | 2025-10-15 | 2027-04-30 |  | HSTANFI | 2025-05-14 | 2025-05-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 22.2167 | 6 | 1486.73 | 1357.76 | 0 | 78.65 | 50.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25327117000 |  | 501378948 |  | 6716212G | 2513119 |  |  | 563 | EX | PAPER W/501303150 | 2600B | MANCHESTER | 903 MANCHESTER ST STE 160 | 067 | LEX | 2025-04-16 | U125768 | U127708 | 2025-04-16 | 2025-04-17 | 2025-04-30 |  | OFFICE | 2025-04-16 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26210011 |  | 0
KY | KY - WEST | 2621 | 25327139800 |  | 501379089 |  | 6728208J | 2513070 |  |  | 563 | EX | TAP W/MAIN JO# 25026398800 | 2600B | RABBIT WARREN | 1304 RABBIT WARREN FL LT54 | 067 | LEX | 2025-04-30 | U128816 | U133050 | 2025-04-16 | 2025-04-30 | 2025-04-30 |  | EDWARD F GOINS | 2025-04-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBTWM |  | 100 | 056332B26210012 | 8 | 1 | 3023.75 | 504.37 | 0 | 30.78 | 2488.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25327143100 |  | 501379067 |  | 6728208J | 2513070 |  |  | 563 | EX | 1" P SHORT MULBERRY BLDRS | 2600B | MEADOWLARK | 4125 MEADOWLARK RD LT77 | 067 | LEX | 2025-04-30 | U129673 | U134341 | 2025-04-16 | 2025-05-01 | 2025-05-01 |  | A WILLIAMSON | 2025-04-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 2202.28 | 257.19 | 297.73 | 15.69 | 1631.67 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 25327144500 |  | 500015567 |  | 7260280N |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | FOREST | 1001< FOREST AV | 161 | MAY | 2025-04-16 | U930915 | U129939 | 2025-04-16 | 2025-04-16 |  |  | SDADAMS | 2025-04-16 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 1.3 | 1 | 82.19 | 77.46 | 0 | 4.73 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25327151800 |  | 100319999 |  | 6716208K |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | BLUEBERRY | 317 BLUEBERRY RD | 067 | LEX | 2025-05-08 | U124604 | U140273 | 2025-04-16 | 2025-05-07 | 2025-05-27 |  | RJCRAWF | 2025-05-07 | 2025-04-29 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.95 | 5 | 973.85 | 903.51 | 17.9 | 52.44 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25327155200 |  | 100345820 |  | 6696212C |  |  |  | 565 | EX | REPLACE SERVICE LINE D513749 | 2621P | MILDRED | 799 MILDRED ST | 239 | VER | 2025-04-23 | U128410 | U124604 | 2025-04-16 | 2025-04-19 | 2025-05-07 |  | CDESPAIN | 2025-04-23 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 18.6667 | 2 | 1452.54 | 1369.02 | 0 | 83.52 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25327170000 |  | 100326756 |  | 6720208I |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D512086 | 2621P | CHINOE | 821 CHINOE RD | 067 | LEX | 2025-04-21 | U124604 | U124604 | 2025-04-16 | 2025-04-16 | 2025-04-16 |  | STGOFF | 2025-04-18 | 2025-04-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 29.2167 | 5 | 2863.87 | 1496.86 | 173.36 | 616.45 | 577.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25327170500 |  | 500141495 |  | 6716200D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SARON | 4533 SARON DR | 067 | LEX | 2025-04-17 | U124604 | U129939 | 2025-04-16 | 2025-04-16 | 2025-04-16 |  | BDARNELL | 2025-04-16 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 11.2833 | 2 | 962.95 | 576.79 | 82.51 | 170.45 | 133.2 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25327185200 |  | 501380643 |  | 7348264J |  |  |  | 563 | EX | 1" P LONG | 2621P | MAN O WAR | 2006 MAN O WAR DR | 089 | RAC | 2025-05-12 | U124604 | U132258 | 2025-04-16 | 2025-04-30 | 2025-05-14 |  | RECUMP | 2025-05-09 | 2025-05-02 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 19.0167 | 7 | 2194.73 | 1289.95 | 258.92 | 576.3 | 69.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25327197300 |  | 100338387 |  | 6720212F |  |  |  | 563 | EX | 1" P SHORT/PRMT RCVD | 2600B | SHELBY | 601 SHELBY ST | 067 | LEX | 2025-05-14 | U128816 | U128266 | 2025-04-16 | 2025-04-17 | 2025-05-14 |  | OLIVER MAYNARD | 2025-05-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 1.3833 | 1 | 3567.1 | 93.18 | 0 | 5.41 | 3468.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25327409200 |  | 100328471 |  | 6720208F |  |  |  | 565 | EX | AOC ATMOS CORR REMED/MMO | 2621P | PRATHER | 1335 PRATHER RD | 067 | LEX | 2025-05-14 | U124604 | U124604 | 2025-04-17 | 2025-12-31 |  |  | HMCKUNE | 2025-05-13 | 2025-05-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 29.15 | 6 | 2091.99 | 1705.05 | 288.14 | 98.8 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25327420400 |  | 501380349 |  | 7348264J |  |  |  | 563 | EX | PAPER TAP W/ 100257070 | 2621P | BELLEFONTE | 2201 BELLEFONTE RD SUITE B | 089 | FLA | 2025-04-24 | U124604 | U128266 | 2025-04-17 | 2025-04-21 | 2025-05-01 |  | JCYRUS | 2025-04-23 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26310011 | 1.1667 | 1 | 231.1 | 72.35 | 154.33 | 4.42 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25327421400 |  | 100325466 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE SL/24026358800 | 2621P | COOPER | 1118 COOPER DR 1 | 067 | LEX | 2025-04-18 | U128336 | U132386 | 2025-04-17 | 2025-12-19 |  |  | JOSHUA COX | 2025-04-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2691.76 | 0 | 0 | 0 | 2691.76 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 25327424800 |  | 100355075 |  | 7260280M |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | COMMERCE | 305< COMMERCE ST | 161 | MAY | 2025-04-17 | SDADAMS | U129939 | 2025-04-17 | 2025-04-17 |  |  | SDADAMS | 2025-04-17 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 2.0667 | 2 | 129.28 | 121.85 | 0 | 7.43 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25327434200 |  | 100331095 |  | 6720212N |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | PRESTON | 243 PRESTON AV | 067 | LEX | 2025-05-15 | U124604 | U140273 | 2025-04-17 | 2025-05-08 | 2025-05-29 |  | BDARNELL | 2025-05-14 | 2025-05-02 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.8167 | 4 | 1733.82 | 733.75 | 134.69 | 205.38 | 660 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25327446000 |  | 100296248 |  | 6716216O |  |  |  | 565 | EX | GRADE 1 REPLACE SERVICE LINE | 2621P | EFFIE | 960 EFFIE RD | 067 | LEX | 2025-05-16 | U123688 | U129939 | 2025-04-17 | 2025-04-17 | 2025-04-17 |  | RJCRAWF | 2025-04-17 | 2025-04-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.95 | 5 | 1116.14 | 521.2 | 483.2 | 31.82 | 79.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25327454700 |  | 100322774 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/ 22026238800 | 2600B | SCOVILLE | 1254 SCOVILLE RD | 067 | LEX | 2025-04-17 | U129731 | U125768 | 2025-04-17 | 2025-12-23 |  |  | EDWARD F GOINS | 2025-04-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1454.42 | 0 | 0 | 0 | 1454.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25327465800 |  | 100330694 |  | 6720208B |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D304045 | 2621P | SHERMAN | 160 SHERMAN AV | 067 | LEX | 2025-06-13 | U124604 | U124604 | 2025-04-17 | 2025-10-17 | 2027-04-30 |  | HMCKUNE | 2025-06-12 | 2025-06-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.5833 | 4 | 1781 | 1375.13 | 325.23 | 80.64 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25327471900 |  | 100308386 |  | 6716212N |  |  |  | 565 | EX | GRADE 1 REPLACE SERVICE | 2621P | GIBSON | 419 GIBSON AV | 067 | LEX | 2025-04-18 | HSTANFI | U129939 | 2025-04-17 | 2025-04-17 | 2025-04-17 |  | HSTANFI | 2025-04-18 | 2025-04-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 32 | 5 | 2515.5 | 1858.62 | 543.43 | 113.45 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25327666100 |  | 100360455 |  | 6736228H | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | HILLCREST | 11 HILLCREST DR | 017 | PAR | 2025-05-15 | U126530 | U132386 | 2025-04-18 | 2025-12-19 |  |  | JDUNN | 2025-05-15 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3245.16 | 0 | 0 | 0 | 3245.16 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25327666200 |  | 100360456 |  | 6736228H | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | HILLCREST | 15 HILLCREST DR | 017 | PAR | 2025-05-02 | U126530 | U132386 | 2025-04-18 | 2025-12-19 |  |  | JDUNN | 2025-05-02 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2687.5 | 0 | 0 | 0 | 2687.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25327666400 |  | 100465607 |  | 6736228H | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | HILLCREST | 16 HILLCREST DR | 017 | PAR | 2025-05-08 | U126530 | U132386 | 2025-04-18 | 2025-12-19 |  |  | JDUNN | 2025-05-08 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2264.45 | 0 | 0 | 0 | 2264.45 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25327666800 |  | 100360457 |  | 6736228H | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | HILLCREST | 17 HILLCREST DR | 017 | PAR | 2025-05-14 | U126530 | U132386 | 2025-04-18 | 2025-12-19 |  |  | JDUNN | 2025-05-14 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3069.99 | 0 | 0 | 0 | 3069.99 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25327667300 |  | 100360454 |  | 6736228H | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | HILLCREST | 18 HILLCREST DR | 017 | PAR | 2025-05-07 | U126530 | U132386 | 2025-04-18 | 2025-12-19 |  |  | JDUNN | 2025-05-07 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3082.88 | 0 | 0 | 0 | 3082.88 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25327667600 |  | 100360458 |  | 6736228H | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | HILLCREST | 19 HILLCREST DR | 017 | PAR | 2025-05-12 | U126530 | U132386 | 2025-04-18 | 2025-12-19 |  |  | JDUNN | 2025-05-12 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 8485.12 | 0 | 0 | 0 | 8485.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25327667800 |  | 100360453 |  | 6736228H | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2621P | HILLCREST | 20 HILLCREST DR | 017 | PAR | 2025-05-05 | U126530 | U132386 | 2025-04-18 | 2025-12-19 |  |  | JDUNN | 2025-05-05 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2092.09 | 0 | 0 | 0 | 2092.09 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25327668100 |  | 100360452 |  | 6736228H | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | HILLCREST | 22 HILLCREST DR | 017 | PAR | 2025-04-21 | U126530 | U132386 | 2025-04-18 | 2025-12-19 |  |  | JDUNN | 2025-04-21 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3135.82 | 0 | 0 | 0 | 3135.82 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25327668200 |  | 100360459 |  | 6736228H | 2300569 |  |  | 565 | EX | REPLACE SL/23026297700 | 2600B | HILLCREST | 23 HILLCREST DR | 017 | PAR | 2025-04-18 | U126530 | U132386 | 2025-04-18 | 2025-12-19 |  |  | JDUNN | 2025-04-17 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2246.96 | 0 | 0 | 0 | 2246.96 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25327683700 |  | 501378524 |  | 7240212I |  |  |  | 563 | EX | 1' P SHORT | 2621P | SHADELAWN | 1324 SHADELAWN DR | 173 | MT | 2025-04-28 | DENNING | U133050 | 2025-04-18 | 2025-05-02 | 2025-05-02 |  | DENNING | 2025-04-28 | 2025-04-28 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 25 | 3 | 4777.74 | 1799.24 | 331.03 | 109.78 | 2537.69 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25327704000 |  | 100273367 |  | 6680224G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | REDWOOD | 110 REDWOOD DR | 073 | FRA | 2025-04-21 | U124604 | U139701 | 2025-04-18 | 2025-04-18 | 2025-04-18 |  | JGILES | 2025-04-18 | 2025-04-18 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 | 15.2667 | 3 | 2352.08 | 1573.93 | 324.78 | 453.37 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25327848000 |  | 501381342 |  | 6684228N |  |  |  | 563 | EX | 1" P LONG VANHOUTEN BLDRS | 2600B | BERRY HILL | 2031 BERRY HILL DR | 073 | FRA | 2025-05-08 | U128336 | U134341 | 2025-04-21 | 2025-05-07 | 2025-05-07 |  | JOSHUA COX | 2025-05-07 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 655.2 | 0 | 0 | 0 | 655.2 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25327848100 |  | 501381343 |  | 6684228N |  |  |  | 563 | EX | MANIFOLD W/ MASTER 501381342 | 2600B | BERRY HILL | 2033 BERRY HILL DR | 073 | FRA | 2025-05-08 | U128336 | U134341 | 2025-04-21 | 2025-05-07 | 2025-05-07 |  | JOSHUA COX | 2025-05-07 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 | NBMAN |  | 100 | 056332B26230012 |  | 1 | 3232.83 | 0 | 452.67 | 0 | 2780.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25327848600 |  | 501362650 |  | 6716208J | 2404261 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | NORMAN | 2350 NORMAN LN | 067 | LEX | 2025-05-06 | U123111 | U126856 | 2025-04-21 | 2025-05-09 | 2025-05-09 |  | LYN STAFFORD | 2025-05-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4007.53 | 553.92 | 253.42 | 32.08 | 3168.11 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25327866300 |  | 501361948 |  | 6716216E | 2403608 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | DAHLIA | 701 DAHLIA DR | 067 | LEX | 2025-05-05 | U123111 | U126856 | 2025-04-21 | 2025-05-07 | 2025-05-07 |  | LYN STAFFORD | 2025-05-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 2979.02 | 276.97 | 297.73 | 16.04 | 2388.28 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25327866400 |  | 501361953 |  | 6716216E | 2403608 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | DAHLIA | 721 DAHLIA DR | 067 | LEX | 2025-05-01 | U129731 | U126856 | 2025-04-21 | 2025-05-07 | 2025-05-07 |  | EDWARD F GOINS | 2025-05-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 2652.48 | 544.64 | 194.78 | 31.54 | 1881.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25327866500 |  | 501361954 |  | 6716216E | 2403608 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | DAHLIA | 725 DAHLIA DR | 067 | LEX | 2025-05-01 | U129731 | U126856 | 2025-04-21 | 2025-05-07 | 2025-05-07 |  | EDWARD F GOINS | 2025-05-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 2144.32 | 0 | 262.8 | 0 | 1881.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25327896200 |  | 100326246 |  | 6708212M |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D512003 | 2621P | NEW VINE | 4339 NEW VINE LN ANNEX | 067 | LEX | 2025-04-23 | U124604 | U124604 | 2025-04-21 | 2025-04-21 | 2025-04-21 |  | BDARNELL | 2025-04-22 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.9833 | 3 | 1771.74 | 1293.99 | 201.01 | 276.74 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25328100400 |  | 100463712 |  | 7356256A |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D359300 | 2621P | CENTRAL | 1500 CENTRAL AV | 019 | ASH | 2025-05-08 | U124604 | U137009 | 2025-04-22 | 2025-10-21 | 2027-04-30 |  | MCOLLET | 2025-05-07 | 2025-05-07 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 28.5 | 3 | 5954.81 | 2130.39 | 697.98 | 3126.44 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25328101000 |  | 100462924 |  | 6716200D |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D514679 | 2621P | WATERMILL | 1024 WATERMILL LN | 067 | LEX | 2025-06-13 | U124604 | U124604 | 2025-04-22 | 2025-10-16 | 2027-04-30 |  | JOCHOA | 2025-06-12 | 2025-05-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 17.55 | 4 | 1421.04 | 1062.1 | 231.63 | 62.19 | 65.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25328133300 |  | 501365524 |  | 6696212P |  |  |  | 563 | EX | 1" P LONG GSL CONSTRUCTION | 2600B | SAFFRON | 538 SAFFRON LN LT28 | 239 | VER | 2025-05-02 | U126284 | U132627 | 2025-04-22 | 2025-04-23 | 2025-05-07 |  | JOSH PASLEY | 2025-05-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 1772.29 | 619.3 | 0 | 35.87 | 1117.12 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25328140800 |  | 100259661 |  | 7348268N |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | COURT | 1108 COURT ST | 089 | WOR | 2025-06-02 | RECUMP | U140273 | 2025-04-22 | 2025-05-13 | 2025-06-03 |  | RECUMP | 2025-06-02 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 8.5167 | 2 | 787.15 | 551.61 | 21.09 | 214.45 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25328168500 |  | 501361913 |  | 6712228L | 2292762 |  |  | 563 | EX | 99 1" P SHORT ATKINS | 2600B | RUTH MILLER | 159 RUTH MILLER DR LT84C | 209 | GEO | 2025-05-02 | U129731 | U132627 | 2025-04-22 | 2025-04-23 | 2025-05-07 |  | EDWARD F GOINS | 2025-05-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 2317.85 | 579.96 | 308.98 | 33.59 | 1395.32 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25328169800 |  | 501361912 |  | 6712228L | 2292762 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | RUTH MILLER | 165 RUTH MILLER DR LT115C | 209 | GEO | 2025-04-30 | U129731 | U130192 | 2025-04-22 | 2025-05-07 | 2025-05-07 |  | EDWARD F GOINS | 2025-04-30 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 2577.54 | 520.5 | 227.81 | 31.77 | 1797.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25328170600 |  | 100306633 |  | 6716212I |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | PINE MEADOWS | 1432 PINE MEADOWS RD | 067 | LEX | 2025-04-23 | U124604 | U937740 | 2025-04-22 | 2025-09-26 | 2027-03-31 |  | HSTANFI | 2025-04-22 | 2025-04-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 26.3 | 5 | 2689.06 | 1900.25 | 227.88 | 427.73 | 133.2 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25328175500 |  | 501361914 |  | 6712228L | 2292762 |  |  | 563 | EX | 99-1"P-SHORT/NO PRMT REQ | 2600B | RUTH MILLER | 157 RUTH MILLER DR LT85 | 209 | GEO | 2025-05-05 | U123111 | U128727 | 2025-04-22 | 2025-04-23 | 2025-05-07 |  | LYN STAFFORD | 2025-05-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4 | 1 | 2503.38 | 294.94 | 297.73 | 17.08 | 1893.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25328189800 |  | 100457218 |  | 6720204O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BIRCHAM | 3600 BIRCHAM WY | 067 | LEX | 2025-04-24 | U124604 | U137248 | 2025-04-22 | 2025-09-19 | 2027-03-31 |  | RJCRAWF | 2025-04-23 | 2025-04-22 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 10.9667 | 9 | 4096.79 | 1288.56 | 207.99 | 199.27 | 2400.97 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25328384600 |  | 100461076 |  | 6720200A |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D514681 | 2621P | TURNBRIDGE | 1033 TURNBRIDGE RD | 067 | LEX | 2025-05-30 | U124604 | U124604 | 2025-04-23 | 2025-10-22 | 2027-04-30 |  | ABLAKE | 2025-05-29 | 2025-05-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.0333 | 4 | 1385 | 958.19 | 272.12 | 55.53 | 99.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25328403800 |  | 100311999 |  | 6716208I |  |  |  | 565 | EX | REPAIR OR REPLACE SL | 2621P | HILL N DALE | 294 HILL N DALE RD | 067 | LEX | 2025-04-23 | JOCHOA | U141869 | 2025-04-23 | 2025-04-23 | 2025-04-23 |  | JOCHOA | 2025-04-23 | 2025-04-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.05 | 3 | 1818.16 | 1293.19 | 446.06 | 78.91 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25328406800 |  | 100305776 |  | 6712212K |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MAYWICK VIEW | 1649 MAYWICK VIEW LN | 067 | LEX | 2025-04-29 | U123688 | U124604 | 2025-04-23 | 2025-09-26 | 2027-03-31 |  | MCRAIG | 2025-04-22 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 1.5667 | 1 | 162.65 | 117.03 | 0 | 45.62 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25328427800 |  | 100262182 |  | 7352256D | 2409943 |  |  | 565 | EX | REPLACE SL/24026367500 | 2600B | DIXON | 1905 DIXON ST | 019 | ASH | 2025-06-11 | U124015 | U132386 | 2025-04-23 | 2025-12-19 |  |  | ORA SLONE | 2025-06-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 3204.08 | 0 | 0 | 0 | 3204.08 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25328427900 |  | 100262175 |  | 7352256D | 2409943 |  |  | 565 | EX | REPLACE SL/24026367500 | 2600B | DIXON | 1915 DIXON ST | 019 | ASH | 2025-06-09 | U124015 | U132386 | 2025-04-23 | 2025-12-19 |  |  | ORA SLONE | 2025-06-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 1931.53 | 0 | 0 | 0 | 1931.53 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25328428000 |  | 100262133 |  | 7352256D | 2409943 |  |  | 565 | EX | REPLACE SL/24026367500 | 2600B | DIXON | 1924 DIXON ST | 019 | ASH | 2025-06-02 | U128523 | U132386 | 2025-04-23 | 2025-12-19 |  |  | BRANDON ROBERTS | 2025-06-02 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 1964.73 | 0 | 0 | 0 | 1964.73 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25328428100 |  | 100262171 |  | 7352256D | 2409943 |  |  | 565 | EX | REPLACE SL/24026367500 | 2600B | DIXON | 2003 DIXON ST | 019 | ASH | 2025-06-06 | U128523 | U132386 | 2025-04-23 | 2025-12-19 |  |  | BRANDON ROBERTS | 2025-06-06 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 1964.73 | 0 | 0 | 0 | 1964.73 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25328428200 |  | 100262136 |  | 7352256D | 2409943 |  |  | 565 | EX | REPLACE SL/24026367500 | 2600B | DIXON | 2022 DIXON ST | 019 | ASH | 2025-05-29 | U124015 | U132386 | 2025-04-23 | 2025-12-19 |  |  | ORA SLONE | 2025-05-29 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 1981.24 | 0 | 0 | 0 | 1981.24 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25328428300 |  | 100262139 |  | 7352256D | 2409943 |  |  | 565 | EX | REPLACE SL/24026367500 | 2600B | DIXON | 2102 DIXON ST | 019 | ASH | 2025-05-28 | U124015 | U132386 | 2025-04-23 | 2025-12-19 |  |  | ORA SLONE | 2025-05-28 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 996.21 | 0 | 0 | 0 | 996.21 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25328428400 |  | 100262140 |  | 7352256D | 2409943 |  |  | 565 | EX | REPLACE SL/24026367500 | 2600B | DIXON | 2110 DIXON ST | 019 | ASH | 2025-05-28 | U124015 | U132386 | 2025-04-23 | 2025-12-19 |  |  | ORA SLONE | 2025-05-28 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 996.21 | 0 | 0 | 0 | 996.21 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25328428500 |  | 100262141 |  | 7352256D | 2409943 |  |  | 565 | EX | REPLACE SL/24026367500 | 2600B | DIXON | 2116 DIXON ST | 019 | ASH | 2025-05-22 | U124015 | U132386 | 2025-04-23 | 2025-12-19 |  |  | ORA SLONE | 2025-05-22 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 1627.14 | 0 | 0 | 0 | 1627.14 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25328428600 |  | 100262167 |  | 7352256D | 2409943 |  |  | 565 | EX | REPLACE SL/24026367500 | 2600B | DIXON | 2119 DIXON ST | 019 | ASH | 2025-05-22 | U124015 | U132386 | 2025-04-23 | 2025-12-19 |  |  | ORA SLONE | 2025-05-22 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 996.21 | 0 | 0 | 0 | 996.21 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25328428700 |  | 100262166 |  | 7352256D | 2409943 |  |  | 565 | EX | REPLACE SL/24026367500 | 2600B | DIXON | 2125 DIXON ST | 019 | ASH | 2025-05-22 | U124015 | U132386 | 2025-04-23 | 2025-12-19 |  |  | ORA SLONE | 2025-05-22 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 996.21 | 0 | 0 | 0 | 996.21 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25328428800 |  | 100262165 |  | 7352256D | 2409943 |  |  | 565 | EX | REPLACE SL/24026367500 | 2600B | DIXON | 2127 DIXON ST | 019 | ASH | 2025-05-21 | U124015 | U132386 | 2025-04-23 | 2025-12-19 |  |  | ORA SLONE | 2025-05-21 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 996.21 | 0 | 0 | 0 | 996.21 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25328428900 |  | 100262143 |  | 7352256D | 2409943 |  |  | 565 | EX | REPLACE SL/24026367500 | 2600B | DIXON | 2132 DIXON ST | 019 | ASH | 2025-05-21 | U124015 | U132386 | 2025-04-23 | 2025-12-19 |  |  | ORA SLONE | 2025-05-21 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 996.21 | 0 | 0 | 0 | 996.21 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25328429000 |  | 100262145 |  | 7352256D | 2409943 |  |  | 565 | EX | REPLACE SL/24026367500 | 2600B | DIXON | 2136 DIXON ST | 019 | ASH | 2025-05-21 | U124015 | U132386 | 2025-04-23 | 2025-12-19 |  |  | ORA SLONE | 2025-05-21 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 996.21 | 0 | 0 | 0 | 996.21 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25328429100 |  | 100262180 |  | 7352256D | 2409943 |  |  | 565 | EX | REPLACE SL/24026367500 | 2600B | OLD STAGE | 506 OLD STAGE RD | 019 | ASH | 2025-06-03 | U128523 | U132386 | 2025-04-23 | 2025-12-19 |  |  | BRANDON ROBERTS | 2025-06-03 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 1964.73 | 0 | 0 | 0 | 1964.73 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25328429200 |  | 100262179 |  | 7352256D | 2409943 |  |  | 565 | EX | REPLACE SL/24026367500 | 2600B | POLLARD | 512 POLLARD RD | 019 | ASH | 2025-06-12 | U123688 | U132386 | 2025-04-23 | 2025-12-19 |  |  | BRANDON ROBERTS | 2025-06-04 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 2490.49 | 0 | 0 | 0 | 2490.49 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25328432700 |  | 100262181 |  | 7352256D | 2409943 |  |  | 565 | EX | REPLACE SL/24026367500 | 2600B | POLLARD | 520 POLLARD RD RR | 019 | ASH | 2025-06-05 | U128523 | U132386 | 2025-04-23 | 2025-12-19 |  |  | BRANDON ROBERTS | 2025-06-05 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1964.73 | 0 | 0 | 0 | 1964.73 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25328434000 |  | 501248089 |  | 6700212I | 1854946 |  |  | 563 | EX | MANIFOLD W/ 501248090 | 2621P | KROGER | 466 KROGER WY | 239 | VER | 2025-04-30 | U132386 | U125753 | 2025-04-23 | 2025-05-01 | 2025-05-15 |  | OFFICE | 2025-04-30 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBMAN |  | 100 | 056332B26230011 |  | 0
KY | KY - WEST | 2621 | 25328439000 |  | 100322777 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE W/ 22026238800 | 2600B | SCOVILLE | 1238 SCOVILLE RD | 067 | LEX | 2025-04-23 | U128762 | U125768 | 2025-04-23 | 2025-12-23 |  |  | RANDALL TINCHER | 2025-04-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2971.52 | 0 | 0 | 0 | 2971.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25328445700 |  | 501355438 |  | 6712204J | 2398051 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | MERGANSER | 108 MERGANSER CT LT33 | 113 | NIC | 2025-05-02 | U129673 | U132258 | 2025-04-23 | 2025-04-24 | 2025-05-07 |  | A WILLIAMSON | 2025-05-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26210011 | 8 | 1 | 3582.06 | 550.93 | 297.73 | 144.57 | 2588.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25328453800 |  | 100325939 |  | 6720208E | 2396748 |  |  | 565 | EX | REPLACE W/ 24-0263588-00 | 2600B | DUKE | 319 DUKE RD | 067 | LEX | 2025-04-29 | U129731 | U125768 | 2025-04-23 | 2025-12-23 |  |  | EDWARD F GOINS | 2025-04-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.4833 | 1 | 2050.01 | 220.67 | 0 | 13.46 | 1815.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25328454100 |  | 100325930 |  | 720208E | 2396748 |  |  | 565 | EX | REPLACE W/ 24026358800 | 2600B | DUKE | 331 DUKE RD 1 | 067 | LEX | 2025-04-28 | U129673 | U125768 | 2025-04-23 | 2025-12-23 |  |  | A WILLIAMSON | 2025-04-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 6506.7 | 0 | 0 | 0 | 6506.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25328455800 |  | 501347943 |  | 6724204A | 2291616 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | BAY SHOALS | 3413 BAY SHOALS DR | 067 | LEX | 2025-05-07 | U126604 | U126856 | 2025-04-23 | 2025-05-12 | 2025-05-12 |  | WILLIAM FULKS | 2025-05-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1057.75 | 0 | 0 | 0 | 1057.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25328456200 |  | 501347941 |  | 6724204A | 2291616 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | BAY SHOALS | 3417 BAY SHOALS DR | 067 | LEX | 2025-05-07 | U126604 | U126856 | 2025-04-23 | 2025-05-12 | 2025-05-12 |  | WILLIAM FULKS | 2025-05-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1511.13 | 0 | 0 | 0 | 1511.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25328458400 |  | 500008782 |  | 6720204I |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D512784 | 2621P | TANBARK | 1177 TANBARK RD | 067 | LEX | 2025-06-06 | U124604 | U124604 | 2025-04-23 | 2025-10-23 | 2027-04-30 |  | HMCKUNE | 2025-06-05 | 2025-06-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.8 | 3 | 2344.99 | 1391.29 | 259.92 | 693.78 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25328466700 |  | 100467196 |  | 6716200D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | JAIRUS | 787 JAIRUS DR | 067 | LEX | 2025-04-28 | U123688 | U129939 | 2025-04-23 | 2025-04-17 | 2025-05-05 |  | BDARNELL | 2025-04-23 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 6.0833 | 3 | 1153.22 | 795.68 | 254.23 | 48.55 | 54.76 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25328479600 |  | 100342354 |  | 240216J |  |  |  | 565 | EX | GRADE 1 REPLACE SL | 2621P | VIRGINIA | 603 VIRGINIA AV | 173 | MT | 2025-04-24 | DENNING | U129939 | 2025-04-23 | 2025-04-23 | 2025-04-23 |  | DENNING | 2025-04-24 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 15.8667 | 2 | 2727.2 | 1152.99 | 593.28 | 980.93 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25328847700 |  | 500408989 |  | 6736252I | 2512967 |  |  | 565 | EX | RELOCATE SL W/25-0264002-00 | 2600B | US HIGHWAY 27 | 1340 US HIGHWAY 27 S | 097 | CYN | 2025-04-25 | U129731 | U125768 | 2025-04-24 | 2025-12-23 |  |  | EDWARD F GOINS | 2025-04-24 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26290032 |  | 1 | 4007.56 | 0 | 0 | 0 | 4007.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25328865800 |  | 100335936 |  | 6720212K |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | HILLCREST | 202 HILLCREST AV | 067 | LEX | 2025-05-09 | U930915 | U124604 | 2025-04-24 | 2025-06-24 |  |  | SSHIMFE | 2025-05-08 | 2025-05-08 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10.0167 | 2 | 2031.69 | 558.28 | 0 | 32.33 | 1441.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25328892700 |  | 100333775 |  | 6720212J |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | DELAWARE | 918 DELAWARE AV | 067 | LEX | 2025-05-08 | U930915 | U140273 | 2025-04-24 | 2025-05-15 | 2025-06-05 |  | BDARNELL | 2025-05-05 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.05 | 3 | 1667.64 | 440.61 | 21.92 | 22.45 | 1182.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25328904200 |  | 500219312 |  | 6716212D |  |  |  | 563 | CO | 1" P SHORT/PRMT READY 5/9/2025 | 2600B | CHARLES | 724 CHARLES AV | 067 | LEX | 2025-05-22 |  | U132258 | 2025-04-24 | 2025-05-08 | 2025-05-21 |  | DAVID YOUNG | 2025-06-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 3141.88 | 0 | 0 | 0 | 3141.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25328919900 |  | 100306368 |  | 6716212M |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MASON HEADLEY | 898 MASON HEADLEY RD | 067 | LEX | 2025-04-25 | U124604 | U137248 | 2025-04-24 | 2025-09-26 | 2027-03-31 |  | BDARNELL | 2025-04-24 | 2025-04-24 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 19.5833 | 3 | 2849.86 | 1174.72 | 517.44 | 71.7 | 1086 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25328920100 |  | 501372631 |  | 6736228K | 2398765 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2621P | LINZI | 113 LINZI WY | 017 | PAR | 2025-05-07 | U141668 | U126856 | 2025-04-24 | 2025-05-08 | 2025-05-08 |  | NRICHIE | 2025-05-06 | 2025-05-02 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 18.1333 | 4 | 2338.93 | 1403.35 | 310.04 | 81.22 | 544.32 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25328920200 |  | 501372629 |  | 6736228K | 2398765 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2621P | LINZI | 111 LINZI WY | 017 | PAR | 2025-05-07 | U141668 | U126856 | 2025-04-24 | 2025-05-08 | 2025-05-08 |  | NRICHIE | 2025-05-05 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 16 | 2 | 2802.99 | 1240.49 | 315.73 | 71.81 | 1174.96 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25328920300 |  | 501372647 |  | 6736228K | 2398765 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2621P | LINZI | 129 LINZI WY | 017 | PAR | 2025-05-08 | U124604 | U126856 | 2025-04-24 | 2025-05-08 | 2025-05-08 |  | NRICHIE | 2025-05-07 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 2.8667 | 2 | 873.57 | 227.95 | 333.62 | 13.2 | 298.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25328920500 |  | 100456611 |  | 6720204M |  |  |  | 565 | EX | REPLACE SERVICE LINED514683 | 2621P | DARDA | 953 DARDA CT | 067 | LEX | 2025-05-06 | U930915 | U124604 | 2025-04-24 | 2025-04-27 | 2025-05-15 |  | RJCRAWF | 2025-05-06 | 2025-05-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.7833 | 5 | 1331.28 | 1200.98 | 60.72 | 69.58 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25328921500 |  | 501376768 |  | 6720212M |  |  |  | 563 | EX | 1" P SHORT/PRMT READY 5/9/2025 | 2600B | KENTUCKY | 137 KENTUCKY AV | 067 | LEX | 2025-05-23 | U123111 | U129531 | 2025-04-24 | 2025-04-24 | 2025-05-23 |  | LYN STAFFORD | 2025-05-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 6119.23 | 553.92 | 401.41 | 32.08 | 5131.82 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25329499100 |  | 100431901 |  | 7352260F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D359283 | 2621P | RUSSELL | RUSSELL RD | 089 | RUS | 2025-05-16 | DYOUNG | U123688 | 2025-04-25 | 2025-05-02 | 2025-05-13 |  | MCOLLET | 2025-05-05 | 2025-05-02 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 24.1667 | 7 | 3570.73 | 1752.77 | 236.65 | 1581.31 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25329537700 |  | 501285876 |  | 7236212L | 2069582 |  |  | 563 | EX | 99 1" P LONG | 2621P | SANDE RIDGE LN | 138 SANDE RIDGE LN LT20 | 173 | MT | 2025-05-05 | DENNING | U129176 | 2025-04-25 | 2025-04-25 | 2025-05-12 |  | DENNING | 2025-05-05 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 24 | 3 | 2319.27 | 1894.32 | 315.28 | 109.67 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 25329561100 |  | 100356562 |  | 7260276A |  |  |  | 563 | EX | 1" P SHORT | 2621P | FLEMING | 740 FLEMING RD | 161 | MAY | 2025-05-09 | U124604 | U132258 | 2025-04-25 | 2025-05-09 | 2025-05-23 |  | RALLISO | 2025-05-08 | 2025-05-06 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26320011 | 34.6 | 8 | 20315.41 | 2384.72 | 17745.88 | 184.81 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25329565800 |  | 100295223 |  | 6716216P |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HASKINS | 559 HASKINS DR | 067 | LEX | 2025-04-28 | BDARNELL | U137248 | 2025-04-25 | 2025-04-28 |  |  | BDARNELL | 2025-04-28 | 2025-04-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 35.1333 | 6 | 2792.21 | 1894.36 | 584.45 | 313.4 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25329686300 |  | 100328981 |  | 6720208P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D512765 | 2621P | PADDOCK | 2692 PADDOCK CT | 067 | LEX | 2025-05-30 | U124604 | U123688 | 2025-04-28 | 2025-10-24 | 2027-04-30 |  | SSHIMFE | 2025-05-29 | 2025-05-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.5333 | 3 | 1208.62 | 928.9 | 225.94 | 53.78 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25329688600 |  | 100313506 |  | 6716208B |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | MOCKINGBIRD | 272 MOCKINGBIRD LN | 067 | LEX | 2025-05-19 | ABLAKE | U140273 | 2025-04-28 | 2025-05-19 | 2025-06-09 |  | ABLAKE | 2025-05-19 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10.1667 | 2 | 678.65 | 559.64 | 86.58 | 32.43 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25329696800 |  | 501361924 |  | 6712228L | 2292762 |  |  | 563 | EX | 99-1"P- LONG/NO PRMT REQ | 2600B | RUTH MILLER | 170 RUTH MILLER DR LT107 | 209 | GEO | 2025-05-12 | U128816 | U128727 | 2025-04-28 | 2025-04-29 | 2025-05-12 |  | OLIVER MAYNARD | 2025-05-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 0.6 | 1 | 3089.8 | 43.78 | 0 | 2.54 | 3043.48 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25329721500 |  | 100410599 |  | 6704208E |  |  |  | 565 | EX | GRADE 1 REPLACE SERVICE LINE | 2621P | JUNIPER | 188 JUNIPER DR | 239 | VER | 2025-04-29 | U128410 | U129939 | 2025-04-28 | 2025-04-28 | 2025-04-28 |  | CDESPAIN | 2025-04-28 | 2025-04-28 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.4333 | 2 | 501.9 | 473.05 | 0 | 28.85 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25329749200 |  | 501347908 |  | 6724204A | 2291616 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | NIGHT HERON | 3409 NIGHT HERON WY | 067 | LEX | 2025-05-08 | U128336 | U126856 | 2025-04-28 | 2025-05-12 | 2025-05-12 |  | JOSHUA COX | 2025-05-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1808.86 | 0 | 297.73 | 0 | 1511.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25329749400 |  | 501347915 |  | 6724204A | 2291616 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | NIGHT HERON | 3437 NIGHT HERON WY | 067 | LEX | 2025-05-08 | U128336 | U126856 | 2025-04-28 | 2025-05-12 | 2025-05-12 |  | JOSHUA COX | 2025-05-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1355.48 | 0 | 297.73 | 0 | 1057.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25329752200 |  | 100409650 |  | 724208E |  |  |  | 565 | EX | GRADE 1 REPLACE SERVICE LINE | 2621P | LARKWOOD | 344 LARKWOOD DR | 067 | LEX | 2025-04-30 | U123688 | U129939 | 2025-04-28 | 2025-04-28 | 2025-04-28 |  | TROE | 2025-04-29 | 2025-04-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.25 | 7 | 1323.64 | 1016.46 | 245.79 | 61.39 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25329763100 |  | 500691625 |  | 7348264-K |  |  |  | 563 | EX | 1"P-LONG | 2621P | ACKISON | 1146 ACKISON ST | 089 | RAC | 2025-05-12 | U124604 | U128727 | 2025-04-28 | 2025-04-29 | 2025-05-19 |  | RECUMP | 2025-05-09 | 2025-05-02 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 25.1167 | 7 | 2426.86 | 1689.53 | 396.43 | 340.9 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25329924400 |  | 501350532 |  | 6716232J | 2398315 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | OXFORD LANDING | 163 OXFORD LANDING DR | 209 | GEO | 2025-05-08 | U123111 | U126856 | 2025-04-29 | 2025-04-30 | 2025-05-13 |  | LYN STAFFORD | 2025-05-08 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4 | 1 | 2041.92 | 294.94 | 297.73 | 17.08 | 1432.17 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25329924700 |  | 501332944 |  | 6716232I | 2180856 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | LIMESTONE | 138 LIMESTONE LN | 209 | GEO | 2025-05-08 | U123111 | U126856 | 2025-04-29 | 2025-04-30 | 2025-05-13 |  | LYN STAFFORD | 2025-05-08 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 3015.26 | 0 | 299.38 | 0 | 2715.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25329925100 |  | 501278632 |  | 6716232J |  |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | SILVER SPRING | 124 SILVER SPRING WY | 209 | GEO | 2025-05-09 | U123111 | U126856 | 2025-04-29 | 2025-04-30 | 2025-05-13 |  | LYN STAFFORD | 2025-05-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4 | 1 | 2342.83 | 294.94 | 297.73 | 17.08 | 1733.08 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 25329926000 |  | 100413492 |  | 7256280N |  |  |  | 566 | EX | PAPER ABANDON | 2621P | US 68 | 1116 US 68 | 161 | MAY | 2025-04-29 | U123688 | U123688 | 2025-04-29 | 2025-12-31 |  |  | OFFICE | 2025-04-28 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1
KY | KY - CENTRAL | 2632 | 25329926100 |  | 100421202 |  | 7256280N |  |  |  | 566 | EX | PAPER ABANDON | 2621P | US 68 | 1110< US 68 | 161 | MAY | 2025-04-29 | U123688 | U123688 | 2025-04-29 | 2025-12-31 |  |  | OFFICE | 2025-04-28 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1
KY | KY - CENTRAL | 2632 | 25329926400 |  | 100421440 |  | 7256280N |  |  |  | 566 | EX | PAPER ABANDON | 2621P | US 68 | 1110< US 68 | 161 | MAY | 2025-04-29 | U123688 | U123688 | 2025-04-29 | 2025-12-31 |  |  | OFFICE | 2025-04-28 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1
KY | KY - WEST | 2621 | 25329938700 |  | 500301583 |  | 6720204O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | STOCKLEA | 3608 STOCKLEA WY | 067 | LEX | 2025-04-30 | U123688 | U129939 | 2025-04-29 | 2025-09-10 | 2027-03-31 |  | STGOFF | 2025-04-29 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 16.4 | 2 | 1042.21 | 796.48 | 197.16 | 48.57 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25329951200 |  | 100345948 |  | 6704208A |  |  |  | 565 | EX | GRADE 1 REPLACE S-L | 2621P | BAYBERRY | 101 BAYBERRY RD | 239 | VER | 2025-05-02 | U123688 | U129939 | 2025-04-29 | 2025-04-29 | 2025-04-29 |  | BWHITE | 2025-05-01 | 2025-04-29 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 | 17.35 | 3 | 1222.09 | 1151.84 | 0 | 70.25 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25329969200 |  | 100404706 |  | 6748208L |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | GREENWAY | 464 GREENWAY DR | 049 | WIN | 2025-05-05 | U930915 | U137009 | 2025-04-29 | 2025-05-05 | 2025-05-05 |  | NRICHIE | 2025-05-02 | 2025-04-30 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 17.1 | 6 | 2921.39 | 1287.96 | 179.66 | 75.39 | 1378.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25329970100 |  | 500123544 |  | 16720204F |  |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | SWOONALONG | 1309 SWOONALONG CT | 067 | LEX | 2025-05-13 | U128816 | U129531 | 2025-04-29 | 2025-04-29 | 2025-05-13 |  | OLIVER MAYNARD | 2025-05-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 5.2833 | 1 | 3646.08 | 363.17 | 0 | 21.03 | 3261.88 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25329989800 |  | 100358646 |  | 6740232A |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D303725 | 2621P | MILL RUN | 137 MILL RUN RD | 017 | PAR | 2025-05-13 | U124604 | U137009 | 2025-04-29 | 2025-05-02 | 2025-05-20 |  | NRICHIE | 2025-05-12 | 2025-05-09 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 9.7333 | 4 | 2329.14 | 752.06 | 354.21 | 43.57 | 1179.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25329997700 |  | 501355400 |  | 6716216G | 2301170 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | STOCKTON | 1996 STOCKTON WY LT1 | 067 | LEX | 2025-05-15 | U128816 | U126856 | 2025-04-29 | 2025-05-14 | 2025-05-14 |  | OLIVER MAYNARD | 2025-05-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4.9333 | 1 | 2278.45 | 337.14 | 0 | 19.52 | 1921.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25329998100 |  | 501348605 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | CALISTA FLAT | 765 CALISTA FLAT | 067 | LEX | 2025-05-09 | U123111 | U126856 | 2025-04-29 | 2025-05-14 | 2025-05-14 |  | LYN STAFFORD | 2025-05-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 2101.87 | 276.97 | 297.73 | 16.04 | 1511.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25329998200 |  | 501348631 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | CLEMATIS | 2224 CLEMATIS WY | 067 | LEX | 2025-05-19 | U123111 | U126856 | 2025-04-29 | 2025-05-19 | 2025-05-19 |  | LYN STAFFORD | 2025-05-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 3088.23 | 276.98 | 297.73 | 16.04 | 2497.48 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25330132000 |  | 100345995 |  | 6704208A |  |  |  | 565 | EX | REPLACE SERVICE LINE - D514585 | 2621P | WOODLARK | 169 WOODLARK RD | 239 | VER | 2025-05-06 | U128410 | U137248 | 2025-04-29 | 2025-05-02 | 2025-05-20 |  | CDESPAIN | 2025-05-06 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 24 | 3 | 2030.55 | 1919.42 | 0 | 111.13 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25330132100 |  | 100345996 |  | 6704208A |  |  |  | 565 | EX | REPLACE SERVICE LINE - D514586 | 2621P | WOODLARK | 173 WOODLARK RD | 239 | VER | 2025-05-06 | U128410 | U137248 | 2025-04-29 | 2025-05-02 | 2025-05-20 |  | CDESPAIN | 2025-05-06 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 |  | 1 | 124.32 | 0 | 0 | 0 | 124.32 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25330139600 |  | 100272008 |  | 6684228K |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HERMITAGE | 300 HERMITAGE DR | 073 | FRA | 2025-05-01 | BWHITE | U123688 | 2025-04-30 | 2025-12-31 |  |  | BWHITE | 2025-05-01 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 12 | 2 | 1212.79 | 800.33 | 0 | 48.82 | 363.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25330155300 |  | 100309694 |  | 6712208H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333433 | 2621P | PASADENA | 627 PASADENA DR | 067 | LEX | 2025-06-19 | U124604 | U123688 | 2025-04-30 | 2025-10-29 | 2027-04-30 |  | KKINDER | 2025-06-18 | 2025-06-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 22.8667 | 3 | 2539.47 | 1345.84 | 570.45 | 623.18 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25330194600 |  | 501378786 |  | 7348264K |  |  |  | 563 | EX | 1' P LONG | 2621P | BLUEGRASS | 1312 BLUEGRASS ST | 089 | FLA | 2025-05-07 | U141668 | U133050 | 2025-04-30 | 2025-05-14 | 2025-05-14 |  | MCOLLET | 2025-05-06 | 2025-05-02 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 24.5 | 6 | 3521.7 | 1717.03 | 202.25 | 1602.42 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25330196900 |  | 501355433 |  | 6716216G | 2301170 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | REMINGTON | 2365 REMINGTON DR | 067 | LEX | 2025-05-14 | U128816 | U126856 | 2025-04-30 | 2025-05-14 | 2025-05-14 |  | OLIVER MAYNARD | 2025-05-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 9.1167 | 1 | 2788.8 | 626.32 | 0 | 36.26 | 2126.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25330200800 |  | 100322856 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE W/ 22026238800 | 2600B | TATES CREEK | 1566 TATES CREEK RD | 067 | LEX | 2025-05-02 | U128762 | U125768 | 2025-04-30 | 2025-04-30 |  |  | RANDALL TINCHER | 2025-04-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3494.08 | 0 | 0 | 0 | 3494.08 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25330202300 |  | 501350442 |  | 6700212O | 2398395 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | ABINGDON | 513 ABINGDON AV | 239 | VER | 2025-05-19 | U128816 | U126856 | 2025-04-30 | 2025-05-19 | 2025-05-19 |  | OLIVER MAYNARD | 2025-05-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 1.6 | 1 | 1856.58 | 116.75 | 0 | 6.75 | 1733.08 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25330202700 |  | 501358725 |  | 6700212O | 2398395 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | WROUGHTON | 630 WROUGHTON DR | 239 | VER | 2025-05-19 | U128816 | U126856 | 2025-04-30 | 2025-05-19 | 2025-05-19 |  | OLIVER MAYNARD | 2025-05-19 | 2025-05-16 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 7.9 | 2 | 1667.57 | 576.43 | 0 | 33.39 | 1057.75 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25330206100 |  | 501317425 |  | 6716236J | 2178365 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | CHICKADEE | 115 CHICKADEE TR | 209 | GEO | 2025-05-15 | U128816 | U126856 | 2025-04-30 | 2025-05-15 | 2025-05-15 |  | OLIVER MAYNARD | 2025-05-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 1.7167 | 1 | 1644.66 | 126.23 | 0 | 7.3 | 1511.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25330208000 |  | 100301131 |  | 6716212E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | LONDONDERRY | 226 LONDONDERRY DR | 067 | LEX | 2025-04-30 | TROE | U129939 | 2025-04-30 | 2025-04-30 |  |  | TROE | 2025-04-30 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24 | 3 | 3419.7 | 2308.06 | 237.29 | 109.95 | 764.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25330229800 |  | 100463968 |  | 6720208N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | DUNBARTON | 1108 DUNBARTON LN | 067 | LEX | 2025-05-02 | U123688 | U123688 | 2025-04-30 | 2025-05-02 | 2025-05-21 |  | RJCRAWF | 2025-05-01 | 2025-05-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24 | 3 | 1776.07 | 1440.19 | 252.48 | 83.4 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25330396400 |  | 100346674 |  | 6696212P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D341988 | 2621P | MEADOW | 542 MEADOW LN | 239 | VER | 2025-05-16 | U128410 | U123688 | 2025-05-01 | 2025-05-02 | 2025-05-21 |  | CDESPAIN | 2025-05-14 | 2025-05-14 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 24.4333 | 4 | 2143.63 | 2026.29 | 0 | 117.34 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25330398600 |  | 100335554 |  | 6716220B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D359682 | 2621P | TILLYBROOK | 2807 TILLYBROOK CT | 067 | LEX | 2025-06-17 | U124604 | U123688 | 2025-05-01 | 2025-10-30 | 2027-04-30 |  | JGILES | 2025-06-16 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16 | 2 | 1623.47 | 1008.9 | 408.9 | 59.15 | 146.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25330413700 |  | 501055109 |  | 6728212M | 0889351 |  |  | 563 | EX | 20 1" P SHORT JUSTICE | 2600B | BOBWHITE | 3073 BOBWHITE TR LT36 | 067 | LEX | 2025-05-15 | U128816 | U132805 | 2025-05-01 | 2025-05-02 | 2025-05-15 |  | OLIVER MAYNARD | 2025-05-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 5.35 | 2 | 1902.02 | 369.49 | 0 | 21.4 | 1511.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25330437000 |  | 100309311 |  | 6712208K |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | APACHE | 804 APACHE TL | 067 | LEX | 2025-05-15 | U124604 | U140273 | 2025-05-01 | 2025-05-22 | 2025-06-12 |  | MSHARON | 2025-05-15 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.7 | 3 | 387.95 | 366.71 | 0 | 21.24 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25330443200 |  | 500443371 |  | 6684224M |  |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | TAMWORTH | 1038 TAMWORTH LN LT1 | 073 | FRA | 2025-05-23 | U129673 | U131378 | 2025-05-01 | 2025-05-08 | 2025-05-22 |  | A WILLIAMSON | 2025-05-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 3715.43 | 586.66 | 287.48 | 146.64 | 2694.65 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25330444300 |  | 501317433 |  | 6716236J | 2178365 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | IBIS | 104 IBIS CR | 209 | GEO | 2025-05-20 | U123111 | U126856 | 2025-05-01 | 2025-05-20 | 2025-05-20 |  | LYN STAFFORD | 2025-05-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 2432.86 | 589.84 | 297.73 | 34.16 | 1511.13 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25330471500 |  | 100345893 |  | 6700208D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D514596 | 2621P | HAWTHORNE | 108 HAWTHORNE CT | 239 | VER | 2025-05-07 | U128410 | U123688 | 2025-05-01 | 2025-05-02 | 2025-05-22 |  | CDESPAIN | 2025-05-07 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 1 | 683.81 | 646.38 | 0 | 37.43 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25330478300 |  | 100313024 |  | 6716208E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MITCHELL | 566 MITCHELL AV | 067 | LEX | 2025-05-02 | U123688 | U137248 | 2025-05-01 | 2025-09-26 | 2027-03-31 |  | MCRAIG | 2025-05-01 | 2025-05-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 48.55 | 8 | 4039.86 | 2978.9 | 179.4 | 342.84 | 538.72 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25330648000 |  | 100342269 |  | 7240216J |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D333060 | 2621P | DARE | 521 DARE DR | 173 | MT | 2025-06-09 | DENNING | U137009 | 2025-05-02 | 2025-10-31 | 2027-05-31 |  | DENNING | 2025-06-09 | 2025-06-09 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 14.8167 | 3 | 3769.57 | 1113.13 | 439.2 | 506.84 | 1710.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25330659200 |  | 100277906 |  | 6688228F |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | PINEWOOD | 202 PINEWOOD AV | 073 | FRA | 2025-06-05 | U128410 | U123688 | 2025-05-02 | 2025-12-31 |  |  | CDESPAIN | 2025-06-05 | 2025-05-09 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26230031 | 30.75 | 4 | 2584.14 | 2390.05 | 0 | 139.33 | 54.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25330664600 |  | 501355427 |  | 6716216G | 2301170 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | REMINGTON | 2325 REMINGTON DR | 067 | LEX | 2025-05-22 | U123111 | U126856 | 2025-05-02 | 2025-05-21 | 2025-05-21 |  | LYN STAFFORD | 2025-05-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 2351.09 | 0 | 403.7 | 0 | 1947.39 | 0 | 0 | 0
KY | KY - EAST | 2633 | 25330671000 |  | 100253619 |  | 7364188G | 1962537 |  |  | 565 | EX | REPLACE SL/19-0268678-02 | 2600B | HIGHWAY 645 | 7900 HIGHWAY 645 | 159 | INE | 2025-05-09 | U128523 | U125765 | 2025-05-02 | 2025-12-23 |  |  | BRANDON ROBERTS | 2025-05-09 |  |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26330032 |  | 1 | 2346.61 | 0 | 0 | 0 | 2346.61 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25330703800 |  | 501381431 |  | 6716212K |  |  |  | 563 | EX | 1" P SHORT/PRMT READY 5/9/2025 | 2600B | CHAIR | 419 CHAIR AV | 067 | LEX | 2025-05-22 | U123111 | U130192 | 2025-05-02 | 2025-05-21 | 2025-05-21 |  | LYN STAFFORD | 2025-05-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 3100.7 | 276.97 | 297.73 | 16.04 | 2509.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25330717000 |  | 501348650 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | CALISTA FLAT | 812 CALISTA FLAT | 067 | LEX | 2025-05-22 | U123111 | U126856 | 2025-05-02 | 2025-05-20 | 2025-05-20 |  | LYN STAFFORD | 2025-05-22 | 2025-05-20 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 6.45 | 2 | 3375.02 | 444.85 | 297.73 | 25.76 | 2606.68 | 0 | 0 | 0
KY | KY - EAST | 2633 | 25330730300 |  | 100266568 |  | 7356156P |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | A | A ST | 195 | BLA | 2025-05-05 | DYOUNG | U137248 | 2025-05-02 | 2025-05-02 | 2025-05-02 |  | JAHOWARD | 2025-05-02 |  |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26330021 | 13.1667 | 2 | 1616.71 | 1528.2 | 0 | 88.51 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 25331108800 |  | 100268773 |  | 7356156I |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D325543 | 2621P | GEORGE | 253 GEORGE RD | 071 | BET | 2025-05-14 | JCKIRK | U137009 | 2025-05-06 | 2025-05-08 | 2025-05-26 |  | JCKIRK | 2025-05-14 |  |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 16 | 2 | 1225.84 | 1158.74 | 0 | 67.1 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25331124400 |  | 501361967 |  | 6716216E | 2403608 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | DAHLIA | 668 DAHLIA DR | 067 | LEX | 2025-05-20 | U128816 | U126856 | 2025-05-06 | 2025-05-20 | 2025-05-20 |  | OLIVER MAYNARD | 2025-05-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 0.98333 | 1 | 1128.78 | 67.14 | 0 | 3.89 | 1057.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25331124900 |  | 501361968 |  | 6716216E | 2403608 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | DAHLIA | 664 DAHLIA DR | 067 | LEX | 2025-05-20 | U128816 | U126856 | 2025-05-06 | 2025-05-20 | 2025-05-20 |  | OLIVER MAYNARD | 2025-05-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4.3167 | 1 | 1370.91 | 296.01 | 0 | 17.15 | 1057.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25331143200 |  | 501097035 |  | 6724208C | 1421490 |  |  | 563 | EX | 20 1" P LONG/PRMT READY 5/9/25 | 2600B | GEPPA | 2420 GEPPA CT | 067 | LEX | 2025-05-29 | U123111 | U138822 | 2025-05-06 | 2025-05-06 | 2025-05-27 |  | LYN STAFFORD | 2025-05-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 3567.95 | 553.92 | 401.41 | 32.08 | 2580.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25331165800 |  | 100316370 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/2202623710000 | 2600B | CHERRYBARK | 121 CHERRYBARK DR | 067 | LEX | 2025-05-07 | U126532 | U132386 | 2025-05-06 | 2025-12-19 |  |  | LESLIE SHARON | 2025-05-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4109.9 | 0 | 0 | 0 | 4109.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25331166000 |  | 100316372 |  | 6716208F | 2293681 |  |  | 565 | EX | REPLACE SL/2202623710000 | 2600B | CHERRYBARK | 125 CHERRYBARK DR 1 | 067 | LEX | 2025-05-08 | U126532 | U132386 | 2025-05-06 | 2025-12-19 |  |  | LESLIE SHARON | 2025-05-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 5533.7 | 0 | 0 | 0 | 5533.7 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25331326200 |  | 100272027 |  | 6684228O |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | ADMIRALS LNDG | 107 ADMIRALS LNDG | 073 | FRA | 2025-05-08 | U930915 | U141668 | 2025-05-07 | 2025-05-30 | 2025-05-31 |  | DCOLLIN | 2025-05-08 | 2025-05-07 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26230031 | 41.05 | 7 | 4411.42 | 3392.8 | 297.71 | 272.35 | 448.56 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25331335900 |  | 100272025 |  | 6684228J |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTRQD | 2621P | 4TH | 403 E 4TH ST | 073 | FRA | 2025-06-20 | U123688 | U140273 | 2025-05-07 | 2025-05-28 | 2025-06-18 |  | D.COLLINS | 2025-06-04 | 2025-06-04 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 6.0167 | 5 | 818.03 | 458.66 | 0 | 119.37 | 240 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25331337500 |  | 100256402 |  | 7356256B |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | 25TH | 609 25TH ST | 019 | ASH | 2025-06-11 | U124604 | U140273 | 2025-05-07 | 2025-05-23 | 2025-06-18 |  | ABHATFIE | 2025-06-10 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 13.4667 | 2 | 1035.94 | 978.56 | 0 | 57.38 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25331349200 |  | 501317317 |  | 6716236J | 2178365 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | MEADOW LARK | 133 MEADOW LARK TR | 209 | GEO | 2025-05-23 | U126604 | U126856 | 2025-05-07 | 2025-05-23 | 2025-05-23 |  | WILLIAM FULKS | 2025-05-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 2884.75 | 0 | 0 | 0 | 2884.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25331356000 |  | 100456267 |  | 6720200B |  |  |  | 565 | EX | REPLACE SL | 2621P | THORNDALE | 2116 THORNDALE WY | 067 | LEX | 2025-05-08 | U124604 | U137248 | 2025-05-07 | 2025-05-07 | 2025-05-07 |  | RJCRAWF | 2025-05-07 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.7667 | 3 | 769.12 | 532 | 206.3 | 30.82 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25331361000 |  | 100248136 |  | 7356256I |  |  |  | 565 | EX | REPLACE SERVICE LINE/PRMT SNT | 2621P | OAKVIEW | 2610 OAKVIEW RD | 019 | ASH | 2025-05-21 | LAMAY | U137009 | 2025-05-07 | 2025-07-07 | 2025-07-07 |  | LAMAY | 2025-05-21 | 2025-05-21 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 19.5667 | 5 | 1749.88 | 1367.86 | 192.3 | 189.72 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25331530600 |  | 100274183 |  | 6684228O |  |  |  | 565 | EX | REPLACE SERVICE | 2621P | STATE | 130 W STATE ST 1 | 073 | FRA | 2025-05-16 | U128410 | U124604 | 2025-05-08 | 2025-05-07 | 2025-05-07 |  | CDESPAIN | 2025-05-08 | 2025-05-08 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 | 111.1333 | 9 | 9678.67 | 7364.96 | 0 | 426.47 | 1887.24 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25331536300 |  | 100249342 |  | 7356216H |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | GARDEN | 40 GARDEN ST | 127 | LOU | 2025-05-30 | MCOLLET | U140273 | 2025-05-08 | 2025-05-29 | 2025-06-19 |  | MCOLLET | 2025-05-30 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 17.6667 | 4 | 2870.83 | 1236.61 | 10.41 | 627.61 | 996.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25331547200 |  | 501333758 |  | 6724204A | 2185117 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | NIGHT HERON | 3504 NIGHT HERON WY | 067 | LEX | 2025-05-23 | U126530 | U126856 | 2025-05-08 | 2025-05-27 | 2025-05-27 |  | JDUNN | 2025-05-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1057.75 | 0 | 0 | 0 | 1057.75 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25331862300 |  | 500701898 |  | 7336276E |  |  |  | 565 | EX | RELOCATE METER | 2621P | FIELDSTONE | 59 FIELDSTONE CT | 089 | GRE | 2025-05-09 | MCOLLET | U132990 | 2025-05-09 | 2025-05-09 |  |  | MCOLLET | 2025-05-09 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 0.083333 | 1 | 2274.43 | 748.58 | 93.45 | 1293.28 | 139.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25331868500 |  | 100320075 |  | 6716208K |  |  |  | 563 | EX | 1"P LONG/PRMT RCVD | 2600B | NICHOLASVILLE | 1950 NICHOLASVILLE RD | 067 | LEX | 2025-06-05 | U123111 | U128266 | 2025-05-09 | 2025-05-12 | 2025-06-10 |  | LYN STAFFORD | 2025-06-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 3764.77 | 539.92 | 322.32 | 31.66 | 2870.87 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25331900000 |  | 500337405 |  | 16712204G |  |  |  | 563 | EX | 20 1" P LONG/PRMT RCVD | 2600B | MELLINOCKET | 3510 MELLINOCKET CT | 067 | LEX | 2025-06-18 | U123111 | U132805 | 2025-05-09 | 2025-06-10 | 2025-06-10 |  | LYN STAFFORD | 2025-06-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 5 | 1 | 1230.85 | 337.45 | 0 | 19.8 | 873.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332024400 |  | 501348637 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | CALISTA FLAT | 785 CALISTA FLAT | 067 | LEX | 2025-05-23 | U129673 | U126856 | 2025-05-12 | 2025-05-27 | 2025-05-27 |  | A WILLIAMSON | 2025-05-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 2.6667 | 1 | 1548.52 | 182.48 | 297.73 | 10.56 | 1057.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332026200 |  | 501382739 |  | 6716216E |  |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | CALENDULA | 2325 CALENDULA RD | 067 | LEX | 2025-05-23 | U129673 | U126856 | 2025-05-12 | 2025-05-27 | 2025-05-27 |  | A WILLIAMSON | 2025-05-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 1.3333 | 1 | 1455.51 | 93 | 299.38 | 5.38 | 1057.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332028500 |  | 100299735 |  | 6712212D |  |  |  | 566 | EX | ABN SL MAS- CONVERT/CUSTRQD | 2621P | WESTLAND | 773 WESTLAND DR A | 067 | LEX | 2025-06-02 | TROE | U140273 | 2025-05-12 | 2025-06-02 | 2025-06-23 |  | TROE | 2025-06-02 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.8333 | 2 | 124.76 | 117.86 | 0 | 6.9 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332029300 |  | 100448198 |  | 6712212D |  |  |  | 566 | EX | PAP ABDN- CONVERT/CUSTREQ | 2621P | WESTLAND | 773 WESTLAND DR B | 067 | LEX | 2025-06-02 | TROE | U140273 | 2025-05-12 | 2025-06-02 | 2025-06-23 |  | TROE | 2025-06-02 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.16667 | 2 | 10.81 | 10.22 | 0 | 0.59 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332030600 |  | 100299741 |  | 6712212D |  |  |  | 566 | EX | PAP ABDN- CONVERT/CUSTREQ | 2621P | WESTLAND | 773 WESTLAND DR C | 067 | LEX | 2025-06-02 | TROE | U140273 | 2025-05-12 | 2025-06-02 | 2025-06-23 |  | TROE | 2025-06-02 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.9333 | 2 | 332.15 | 313.76 | 0 | 18.39 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332030800 |  | 100299743 |  | 6712212D |  |  |  | 566 | EX | PAP ABDN- CONVERT/CUSTREQ | 2621P | WESTLAND | 773 WESTLAND DR D | 067 | LEX | 2025-06-02 | TROE | U140273 | 2025-05-12 | 2025-06-02 | 2025-06-23 |  | TROE | 2025-06-02 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.7333 | 2 | 117.97 | 111.42 | 0 | 6.55 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332031300 |  | 100299744 |  | 6712212D |  |  |  | 566 | EX | PAP ABDN- CONVERT/CUSTREQ | 2621P | WESTLAND | 773 WESTLAND DR E | 067 | LEX | 2025-06-02 | TROE | U140273 | 2025-05-12 | 2025-06-02 | 2025-06-23 |  | TROE | 2025-06-02 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.3667 | 2 | 361.96 | 341.91 | 0 | 20.05 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332032200 |  | 100293127 |  | 6720216G |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D333447 | 2621P | RADCLIFFE | 249 RADCLIFFE RD | 067 | LEX | 2025-06-10 | U124604 | U124604 | 2025-05-12 | 2025-11-07 | 2027-05-31 |  | TROE | 2025-06-09 | 2025-05-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.4167 | 6 | 1139.6 | 901.72 | 185.05 | 52.83 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25332047100 |  | 500817621 |  | W-1122-57 |  |  |  | 563 | EX | 1"P LONG | 2621P | CHARLIE NORRIS | 979 CHARLIE NORRIS RD | 151 | RIC | 2025-05-22 | DENNING | U128266 | 2025-05-12 | 2025-05-13 | 2025-05-26 |  | DENNING | 2025-05-22 | 2025-05-21 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 22.35 | 5 | 6546.3 | 1748.41 | 331.03 | 241.86 | 4225 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 25332085000 |  | 100438216 |  | 7240280G |  |  |  | 566 | EX | ABANDONMENT | 2621P | KY 10 | 4386 KY 10 | 161 | GER | 2025-05-12 | SDADAMS | U137607 | 2025-05-12 | 2025-05-12 |  |  | SDADAMS | 2025-05-12 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 0.43333 | 1 | 34.16 | 32.29 | 0 | 1.87 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332225400 |  | 100463607 |  | 6716200D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | JAIRUS | 818 JAIRUS DR | 067 | LEX | 2025-05-14 | U124604 | U137248 | 2025-05-13 | 2025-10-10 | 2027-04-30 |  | TROE | 2025-05-13 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.8333 | 7 | 1206.36 | 1060.6 | 0 | 61.4 | 84.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332227500 |  | 100333642 |  | 6720212I |  |  |  | 563 | EX | 1 1/4"PMLP SHORT/PRMT RCVD | 2600B | 3RD | 326 E 3RD ST | 067 | LEX | 2025-06-05 | U129731 | U134375 | 2025-05-13 | 2025-05-28 | 2025-06-10 |  | EDWARD F GOINS | 2025-06-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 8 | 1 | 4933.29 | 522.4 | 372.17 | 30.63 | 4008.09 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 25332230800 |  | 100354165 |  | 7256280P |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTREQ | 2621P | 4TH | 360 E 4TH ST | 161 | MAY | 2025-06-03 | RALLISO | U140273 | 2025-05-13 | 2025-06-03 | 2025-06-24 |  | RALLISO | 2025-06-03 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 10.1667 | 2 | 2999.74 | 647.97 | 0 | 389.27 | 1962.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 25332231200 |  | 100457984 |  | 7256280P |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTRQD | 2621P | 4TH | 352 E 4TH ST | 161 | MAY | 2025-06-04 | U930915 | U140273 | 2025-05-13 | 2025-06-03 | 2025-06-24 |  | RALLISO | 2025-06-03 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 4.7833 | 2 | 1934.8 | 305.53 | 0 | 284.27 | 1345 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332242800 |  | 100315157 |  | 6716212O | 2513622 |  |  | 566 | EX | RETIRE W/25-0264025-00 | 2600B | TRANSCRIPT | 208 TRANSCRIPT AV | 067 | LEX | 2025-05-19 | U126284 | U461383 | 2025-05-13 | 2025-05-30 | 2025-06-01 |  | JOSH PASLEY | 2025-05-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.3833 | 1 | 1300.89 | 172.3 | 0 | 9.97 | 1118.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332243000 |  | 100315158 |  | 6716212O | 2513622 |  |  | 566 | EX | RETIRE W/25-0264025-00 | 2600B | TRANSCRIPT | 204 TRANSCRIPT AV | 067 | LEX | 2025-05-19 | U126284 | U461383 | 2025-05-13 | 2025-05-30 | 2025-06-01 |  | JOSH PASLEY | 2025-05-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.4667 | 1 | 1305.53 | 176.69 | 0 | 10.22 | 1118.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332243200 |  | 100315156 |  | 6716212O | 2513622 |  |  | 566 | EX | RETIRE W/25-0264025-00 | 2600B | TRANSCRIPT | 210 TRANSCRIPT AV | 067 | LEX | 2025-05-19 | U126284 | U461383 | 2025-05-13 | 2025-05-30 | 2025-06-01 |  | JOSH PASLEY | 2025-05-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1118.62 | 0 | 0 | 0 | 1118.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332262600 |  | 100330081 |  | 6720212O |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | HOLIDAY | 414 HOLIDAY RD | 067 | LEX | 2025-05-30 | HMCKUNE | U140273 | 2025-05-13 | 2025-06-03 | 2025-06-24 |  | HMCKUNE | 2025-05-30 | 2025-05-27 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.7333 | 4 | 2448.03 | 807.95 | 15.08 | 194.12 | 1430.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25332264000 |  | 100279085 |  | 6688228F |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTRQD | 2621P | LAFFOON | 214 LAFFOON DR | 073 | FRA | 2025-06-06 | DCOLLIN | U140273 | 2025-05-13 | 2025-06-03 | 2025-06-24 |  | DCOLLIN | 2025-06-06 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 12.4833 | 2 | 1085.04 | 933.05 | 52.48 | 99.51 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332271600 |  | 100460111 |  | 6720200A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | JAIRUS | 851 JAIRUS DR | 067 | LEX | 2025-05-14 | U124604 | U137248 | 2025-05-13 | 2025-10-14 | 2027-04-30 |  | TROE | 2025-05-13 | 2025-05-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 10.65 | 5 | 1201.58 | 712.76 | 447.52 | 41.3 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332276500 |  | 100309514 |  | 6712208K |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | APACHE | 837 APACHE TL | 067 | LEX | 2025-05-14 | U124604 | U137248 | 2025-05-13 | 2025-09-03 | 2027-03-31 |  | RSTRONG | 2025-05-13 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.2667 | 2 | 1239.21 | 947.51 | 157.1 | 134.6 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25332287500 |  | 100282357 |  | 6712228B |  |  |  | 565 | EX | SERVICE REPLACE/RELOCATE | 2621P | COURT | 100 N COURT ST | 209 | GEO | 2025-06-02 | U124604 | U124604 | 2025-05-13 | 2025-05-30 |  |  | DCOLLIN | 2025-05-30 | 2025-05-27 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26230031 | 68.0333 | 8 | 12411 | 6016.59 | 183.56 | 1037.85 | 5173 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332300500 |  | 501383028 |  | 6720212N |  |  |  | 563 | EX | 1" P SHORT/PRMT RCVD | 2600B | SHERMAN | 245 SHERMAN AV | 067 | LEX | 2025-06-11 | U123111 | U126856 | 2025-05-13 | 2025-06-10 | 2025-06-10 |  | LYN STAFFORD | 2025-06-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 2101.73 | 0 | 257.68 | 0 | 1844.05 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25332356800 |  | 100343128 |  | 7240212A | 1313371 |  |  | 565 | EX | SERVICE LINE REPAIR | 2621P | MAIN | 468 W MAIN ST | 173 | MT | 2025-05-15 | U124604 | U134902 | 2025-05-14 | 2025-05-14 | 2025-05-14 |  | NRICHIE | 2025-05-15 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 96.5 | 7 | 23209.37 | 7558.86 | 519.65 | 437.69 | 14693.17 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25332359800 |  | 100424654 |  | 7240212A |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D514654 | 2621P | BROOKMEDE | 615 BROOKMEDE DR | 173 | MT | 2025-05-20 | DENNING | U124604 | 2025-05-14 | 2025-05-16 | 2025-06-03 |  | DENNING | 2025-05-20 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 15.1333 | 2 | 3337.76 | 1191.3 | 58.79 | 68.99 | 2018.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332365900 |  | 100412958 |  | 6720208M |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D333446 | 2621P | MONTAVESTA | 2945 MONTAVESTA RD | 067 | LEX | 2025-06-19 | U124604 | U124604 | 2025-05-14 | 2025-11-13 | 2027-05-31 |  | WCRIM | 2025-06-18 | 2025-06-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.1167 | 4 | 1047.31 | 666.04 | 197.16 | 39.07 | 145.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332366800 |  | 100465418 |  | 6712212K |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D514643 | 2621P | PARTERRE | 2433 PARTERRE PL | 067 | LEX | 2025-06-20 | U124604 | U124604 | 2025-05-14 | 2025-11-13 | 2027-05-31 |  | MCRAIG | 2025-06-19 | 2025-06-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.5333 | 4 | 3469.17 | 1131.36 | 277.81 | 1240.84 | 819.16 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25332374200 |  | 100265958 |  | 7348252D |  |  |  | 566 | EX | ABANDON SL/ DEMO/FIRE | 2621P | STATE RT 716 | 927 STATE RT 716 RD | 019 | ASH | 2025-06-04 | RECUMP | U123688 | 2025-05-14 | 2025-12-31 |  |  | RECUMP | 2025-06-04 | 2025-05-30 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 12.35 | 4 | 1141.39 | 800.27 | 21.09 | 320.03 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332395100 |  | 100310631 |  | 6712208L |  |  |  | 565 | EX | SERVICE LINE REPLACE | 2621P | NAKOMI | 644 NAKOMI DR | 067 | LEX | 2025-05-15 | U124604 | U137248 | 2025-05-14 | 2025-05-14 | 2025-05-14 |  | HMCKUNE | 2025-05-14 | 2025-05-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.7 | 3 | 1556.3 | 687.4 | 377.11 | 320.11 | 171.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332416800 |  | 501377299 |  | 6716216N | 2512552 |  |  | 563 | EX | 1" P LONG/MAIN IN PRIVATE EAS | 2600B | TURNER COMMONS | 152 TURNER COMMONS WY LTBLD Q | 067 | LEX | 2025-05-28 | U123111 | U126856 | 2025-05-14 | 2025-05-28 | 2025-05-28 |  | LYN STAFFORD | 2025-05-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 5.5 | 1 | 5206.93 | 380.79 | 402.05 | 22.06 | 4402.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332417100 |  | 501368851 |  | 6728212M | 2405655 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | BLACKFORD | 2853 BLACKFORD PY | 067 | LEX | 2025-05-28 | U123111 | U126856 | 2025-05-14 | 2025-05-28 | 2025-05-28 |  | LYN STAFFORD | 2025-05-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 2097.81 | 276.95 | 293.69 | 16.04 | 1511.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332417300 |  | 501368856 |  | 6728212M | 2405655 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | BLACKFORD | 2833 BLACKFORD PY | 067 | LEX | 2025-05-28 | U123111 | U126856 | 2025-05-14 | 2025-05-28 | 2025-05-28 |  | LYN STAFFORD | 2025-05-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1804.82 | 0 | 293.69 | 0 | 1511.13 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25332436800 |  | 100268007 |  | 7356260N | 2514451 |  |  | 563 | EX | 1"P SHORT/PRMT SENT 5/15 | 2621P | 16TH | 236 16TH ST | 019 | ASH | 2025-05-23 | U124604 | U134341 | 2025-05-14 | 2025-05-28 | 2025-05-28 |  | MCOLLET | 2025-05-22 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 24 | 5 | 4628.06 | 1705.4 | 205.07 | 1345.01 | 1372.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332438100 |  | 100310679 |  | 6712208L |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | NAKOMI | 612 NAKOMI DR | 067 | LEX | 2025-06-02 | KKINDER | U137248 | 2025-05-14 | 2025-05-16 | 2025-06-04 |  | KKINDER | 2025-06-02 | 2025-05-21 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 27.3333 | 7 | 2591.08 | 1852.15 | 330.84 | 351.85 | 56.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332440400 |  | 100464640 |  | 6716200D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | WOODGLEN | 921 WOODGLEN CT | 067 | LEX | 2025-05-15 | U124604 | U132424 | 2025-05-14 | 2025-10-09 | 2027-04-30 |  | JOCHOA | 2025-05-14 | 2025-05-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 21.7 | 5 | 1937.63 | 1507.19 | 272.12 | 87.28 | 71.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332601300 |  | 100291799 |  | 6720216G |  |  |  | 566 | EX | ABANDON SL - DEMO/FIRE | 2621P | PIERSON | 2339 PIERSON DR | 067 | LEX | 2025-06-04 | U930915 | U140273 | 2025-05-15 | 2025-06-04 | 2025-06-25 |  | HSTANFI | 2025-06-04 | 2025-06-03 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.2833 | 2 | 473.32 | 447.12 | 0 | 26.2 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332612300 |  | 100462555 |  | 6720200A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | EDGEWOOD | 865 EDGEWOOD DR | 067 | LEX | 2025-05-16 | U124604 | U137248 | 2025-05-15 | 2025-10-09 | 2027-04-30 |  | MCRAIG | 2025-05-15 | 2025-05-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 15.4333 | 4 | 1827.03 | 922.35 | 348.14 | 461.82 | 94.72 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 25332617900 |  | 100355882 |  | 7260276B |  |  |  | 566 | EX | ABANDON SL | 2621P | WOOD | 522 WOOD ST | 161 | MAY | 2025-05-15 | SDADAMS | U132625 | 2025-05-15 | 2025-05-15 |  |  | SDADAMS | 2025-05-15 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 0.31667 | 1 | 23.26 | 21.98 | 0 | 1.28 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332646200 |  | 100310567 |  | 6712208L |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | SEATTLE | 703 SEATTLE DR | 067 | LEX | 2025-05-16 | U137585 | U137248 | 2025-05-15 | 2025-05-15 | 2025-05-15 |  | SSHIMFE | 2025-05-15 | 2025-05-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 27.5 | 5 | 1633.37 | 1543.98 | 0 | 89.39 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25332670300 |  | 100275849 |  | 6684228G |  |  |  | 563 | EX | 1"P LONG/NO PRMT REQ | 2600B | LEESTOWN | 857 LEESTOWN LN | 073 | FRA | 2025-06-12 | U123111 | U128266 | 2025-05-15 | 2025-05-16 | 2025-06-10 |  | LYN STAFFORD | 2025-06-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 5.5 | 1 | 4396.42 | 377.37 | 421.75 | 22.11 | 3575.19 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332704400 |  | 100336710 | 18 | 6720212I |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | 4TH | 275 E 4TH ST | 067 | LEX | 2025-06-19 | U930915 | BLINDSA | 2025-05-15 | 2025-06-13 |  |  | STGOFF | 2025-06-19 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.6833 | 2 | 1430.47 | 841.14 | 0 | 49.33 | 540 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332704500 |  | 100310597 |  | 6712208H |  |  |  | 565 | EX | REPLACE SERVICE D514660 | 2621P | SEATTLE | 730 SEATTLE DR | 067 | LEX | 2025-05-29 | U124604 | U124604 | 2025-05-15 | 2025-05-18 | 2025-06-05 |  | ABLAKE | 2025-05-28 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.7167 | 2 | 1221.93 | 759.25 | 418.7 | 43.98 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25332888900 |  | 100247716 |  | 7352256L |  |  |  | 565 | EX | REPAIR GR 1 LEAK | 2621P | BLACKBURN | 2315 BLACKBURN AV | 019 | ASH | 2025-05-19 | RECUMP | U132928 | 2025-05-16 | 2025-05-16 | 2025-05-16 |  | RECUMP | 2025-05-19 | 2025-05-16 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 21.1333 | 4 | 6406.02 | 1436.56 | 257.42 | 414.12 | 4297.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332900400 |  | 500048354 |  | 6728200D |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | ATHENS BOONESB | 6366 ATHENS BOONESB RD FG 57 | 067 | LEX | 2025-06-12 | HMCKUNE | U140273 | 2025-05-16 | 2025-06-06 | 2025-06-27 |  | HMCKUNE | 2025-06-12 | 2025-06-12 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 20.8333 | 3 | 1280.63 | 1195.45 | 15.08 | 70.1 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332900700 |  | 100302674 |  | 6712212K | 0674885 |  |  | 565 | EX | NBT REPLACE SVC GOODWILL | 2621P | VERSAILLES | 2285 VERSAILLES RD | 067 | LEX | 2025-05-21 | U123111 | U124604 | 2025-05-16 | 2025-05-27 |  |  | LYN STAFFORD | 2025-05-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 9.25 | 1 | 2645.76 | 640.48 | 247.94 | 37.09 | 1720.25 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25332901900 |  | 100274184 |  | 6684228O |  |  |  | 565 | EX | PAPERWORK | 2621P | STATE | 130 W STATE ST 2 | 073 | FRA | 2025-05-16 | U128410 | U132928 | 2025-05-16 | 2025-05-16 |  |  | CDESPAIN | 2025-05-08 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26230031 | 6.9667 | 3 | 938.15 | 581.33 | 323.15 | 33.67 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332923900 |  | 501383208 |  | 6716216N |  |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | TURNER COMMONS | 141 TURNER COMMONS WY | 067 | LEX | 2025-06-04 | U126604 | U126856 | 2025-05-16 | 2025-06-10 | 2025-06-10 |  | WILLIAM FULKS | 2025-06-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1057.75 | 0 | 0 | 0 | 1057.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25332936700 |  | 100331036 |  | 6720212N |  |  |  | 565 | EX | METER MOVE OUT | 2621P | PRESTON | 308 PRESTON AV | 067 | LEX | 2025-06-17 | STGOFF | U124604 | 2025-05-16 | 2025-12-31 |  |  | STGOFF | 2025-06-17 | 2025-06-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.7833 | 6 | 1417.06 | 1174.79 | 173.37 | 68.9 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25333075000 |  | 100462118 |  | 6720204M |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | JAIRUS | 951 JAIRUS DR | 067 | LEX | 2025-05-19 | TROE | U137248 | 2025-05-19 | 2025-10-15 | 2027-04-30 |  | TROE | 2025-05-19 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 12.7167 | 2 | 751.1 | 709.98 | 0 | 41.12 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25333077200 |  | 501382462 |  | 6716208D |  |  |  | 563 | EX | 99 1"P LONG/PRMT READY 6/4/25 | 2600B | SCOVILLE | 1267 SCOVILLE RD | 067 | LEX | 2025-06-13 | U128762 | U132253 | 2025-05-19 | 2025-06-09 | 2025-06-16 |  | RANDALL TINCHER | 2025-06-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 2669.33 | 0 | 0 | 0 | 2669.33 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25333112000 |  | 501374553 |  | 6748208M | 2511828 |  |  | 563 | EX | 2" P SHORT | 2600B | HIGHLAND | 1 S HIGHLAND ST | 049 | WIN | 2025-06-04 | U126602 | U134341 | 2025-05-19 | 2025-06-10 | 2025-06-10 |  | DEREK PAYTON | 2025-06-03 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 |  | 1 | 2987.31 | 0 | 625.31 | 0 | 2362 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25333118300 |  | 100463665 |  | 6716200D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | FAIRHAVEN | 875 FAIRHAVEN DR | 067 | LEX | 2025-05-19 | MSHARON | U141869 | 2025-05-19 | 2025-10-14 | 2027-04-30 |  | MSHARON | 2025-05-19 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 18.6667 | 4 | 1226.81 | 1159.66 | 0 | 67.15 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25333128800 |  | 100332070 |  | 6720212J |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | AURORA | 714 AURORA AV | 067 | LEX | 2025-05-28 | U124604 | U132424 | 2025-05-19 | 2025-05-10 | 2025-05-28 |  | SSHIMFE | 2025-05-19 | 2025-05-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 12.6833 | 2 | 6908.61 | 1423.46 | 280.01 | 242.72 | 4962.42 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25333359900 |  | 100245430 |  | 7360248A |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTRQD | 2621P | VALLEY | 3516 VALLEY ST | 019 | CAT | 2025-06-16 | U124604 | U140273 | 2025-05-20 | 2025-06-10 | 2025-07-01 |  | ABHATFIE | 2025-06-13 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.3167 | 1 | 341.03 | 322.14 | 0 | 18.89 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25333369300 |  | 501317319 |  | 6716236J | 2178365 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | MEADOW LARK | 129 MEADOW LARK TR | 209 | GEO | 2025-06-10 | U123111 | U126856 | 2025-05-20 | 2025-06-10 | 2025-06-10 |  | LYN STAFFORD | 2025-06-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4 | 1 | 2432.31 | 274.43 | 297.73 | 16.1 | 1844.05 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25333615300 |  | 100467515 |  | 6716200D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | FAIRHAVEN | 907 FAIRHAVEN DR | 067 | LEX | 2025-05-22 | U124604 | U137248 | 2025-05-21 | 2025-10-10 | 2027-04-30 |  | MSHARON | 2025-05-21 | 2025-05-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 15.85 | 4 | 989.9 | 749.33 | 197.16 | 43.41 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25333617300 |  | 501317363 |  | 6716236J | 2178365 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | NUTHATCH | 149 NUTHATCH TR | 209 | GEO | 2025-06-03 | U128336 | U126856 | 2025-05-21 | 2025-06-10 | 2025-06-10 |  | JOSHUA COX | 2025-06-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 2215.3 | 0 | 408.12 | 0 | 1807.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25333641300 |  | 500008788 |  | 6708204H |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | VALE | 2413 VALE DR | 067 | LEX | 2025-05-22 | U124604 | U141174 | 2025-05-21 | 2025-10-16 | 2027-04-30 |  | MCRAIG | 2025-05-21 | 2025-05-21 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 25.5167 | 5 | 2106.38 | 1558.21 | 284.52 | 263.65 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25333645700 |  | 100345062 |  | 6696212G | 2512356 |  |  | 565 | EX | NBT SERVICE LINE/METER UPGRADE | 2621P | ELM | 171 ELM ST | 239 | VER | 2025-06-12 | U930915 | U124604 | 2025-05-21 | 2025-06-18 | 2025-06-18 |  | RJCRAWF | 2025-06-12 | 2025-06-02 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26230031 | 45.1667 | 6 | 12979.35 | 3289.91 | 414.74 | 1364.84 | 7909.86 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25333650800 |  | 100284616 |  | 6748180L | 1635077 |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | COLLEGE HILL | 325 COLLEGE HILL RD | 151 | WAC | 2025-05-21 | DENNING | U141174 | 2025-05-21 | 2025-09-19 | 2027-03-31 |  | DENNING | 2025-05-21 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 0.76667 | 2 | 6829.56 | 1650.92 | 579.09 | 828.03 | 3771.52 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25333657100 |  | 501350546 |  | 6716232J | 2398315 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | OXFORD LANDING | 133 OXFORD LANDING DR | 209 | GEO | 2025-06-06 | U123111 | U126856 | 2025-05-21 | 2025-06-10 | 2025-06-10 |  | LYN STAFFORD | 2025-06-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 1342.06 | 0 | 284.31 | 0 | 1057.75 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25333657300 |  | 501350531 |  | 6716232J | 2398315 |  |  | 563 | CO | 1" P SHORT (BALL HOMES) | 2600B | OXFORD LANDING | 165 OXFORD LANDING DR | 209 | GEO | 2025-06-02 |  | U126856 | 2025-05-21 | 2025-06-10 | 2025-06-10 |  | JOSHUA COX | 2025-06-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1 | 1057.75 | 0 | 0 | 0 | 1057.75 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25333658500 |  | 501350507 |  | 6716232J | 2398315 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | OXFORD LANDING | 148 OXFORD LANDING DR | 209 | GEO | 2025-06-10 | U123111 | U126856 | 2025-05-21 | 2025-06-10 | 2025-06-10 |  | LYN STAFFORD | 2025-06-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4 | 1 | 2321.34 | 274.43 | 297.73 | 16.1 | 1733.08 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25333658800 |  | 501350512 |  | 6716232J | 2398315 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | OXFORD LANDING | 158 OXFORD LANDING DR | 209 | GEO | 2025-06-09 | U123111 | U126856 | 2025-05-21 | 2025-06-10 | 2025-06-10 |  | LYN STAFFORD | 2025-06-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4 | 1 | 2321.34 | 274.43 | 297.73 | 16.1 | 1733.08 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25333659100 |  | 501350516 |  | 6716232J | 2398315 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | OXFORD LANDING | 166 OXFORD LANDING DR | 209 | GEO | 2025-06-10 | U123111 | U126856 | 2025-05-21 | 2025-06-10 | 2025-06-10 |  | LYN STAFFORD | 2025-06-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 7.9833 | 1 | 3164.97 | 508.41 | 277.6 | 645.88 | 1733.08 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25334073900 |  | 100421962 |  | 16740232M |  |  |  | 563 | EX | 20 1" P SHORT | 2621P | 7TH | 336 W 7TH ST | 017 | PAR | 2025-06-04 | DENNING | U132805 | 2025-05-22 | 2025-05-23 | 2025-06-05 |  | DENNING | 2025-06-04 | 2025-05-23 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 34.0333 | 7 | 8618.33 | 2539 | 446.2 | 1134.53 | 4498.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 25334089300 |  | 100357278 |  | 7236280D |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | R1 KY 10 | R1 KY 10 BX32 | 023 | GER | 2025-06-20 | RALLISO | U939463 | 2025-05-22 | 2025-07-08 | 2025-07-08 |  | RALLISO | 2025-06-20 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 13.2667 | 3 | 2438.31 | 843.13 | 0 | 497.18 | 1098 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25334108400 |  | 501361971 |  | 6716216E | 2403608 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | DITTANY | 2471 DITTANY LN | 067 | LEX | 2025-06-02 | U126604 | U126856 | 2025-05-22 | 2025-06-10 | 2025-06-10 |  | WILLIAM FULKS | 2025-06-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1057.75 | 0 | 0 | 0 | 1057.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25334108600 |  | 501361952 |  | 6716216E | 2403608 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | DAHLIA | 717 DAHLIA DR | 067 | LEX | 2025-06-02 | U126604 | U126856 | 2025-05-22 | 2025-06-10 | 2025-06-10 |  | WILLIAM FULKS | 2025-06-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1712.95 | 0 | 0 | 0 | 1712.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25334109100 |  | 501361958 |  | 6716216E | 2403608 |  |  | 563 | EX | 1" P SHORT(BALL HOMES) | 2600B | DAHLIA | 724 DAHLIA DR | 067 | LEX | 2025-06-02 | U126604 | U126856 | 2025-05-22 | 2025-06-10 | 2025-06-10 |  | WILLIAM FULKS | 2025-06-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1057.75 | 0 | 0 | 0 | 1057.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25334109800 |  | 501348629 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | CLEMATIS | 2217 CLEMATIS WY | 067 | LEX | 2025-06-02 | U126604 | U126856 | 2025-05-22 | 2025-06-10 | 2025-06-10 |  | WILLIAM FULKS | 2025-06-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1057.75 | 0 | 0 | 0 | 1057.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25334109900 |  | 501348649 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | CALISTA FLAT | 808 CALISTA FLAT | 067 | LEX | 2025-06-06 | U123111 | U126856 | 2025-05-22 | 2025-06-10 | 2025-06-10 |  | LYN STAFFORD | 2025-06-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 3014.42 | 269.95 | 343.9 | 15.84 | 2384.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25334124000 |  | 501346215 |  | 6728208I | 2396366 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | SQUIRREL NEST | 1080 SQUIRREL NEST LN | 067 | LEX | 2025-06-03 | U126604 | U126856 | 2025-05-22 | 2025-06-10 | 2025-06-10 |  | WILLIAM FULKS | 2025-06-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1057.75 | 0 | 0 | 0 | 1057.75 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25334366800 |  | 501381607 |  | 7344268P |  |  |  | 563 | EX | 1' P LONG | 2621P | MCCLOUD | 1025 MCCLOUD DR | 089 | WOR | 2025-06-06 | U124604 | U133050 | 2025-05-23 | 2025-06-09 | 2025-06-09 |  | MCOLLET | 2025-06-05 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 16 | 2 | 2583.95 | 1128.08 | 222.12 | 1137.55 | 96.2 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25334377600 |  | 100241443 |  | 7356256G |  |  |  | 566 | EX | ABANDON SL - DEMO/FIRE | 2621P | RINGO | 363 RINGO ST | 019 | ASH | 2025-06-05 | ABHATFIE | U141668 | 2025-05-23 | 2025-07-08 | 2025-07-08 |  | ABHATFIE | 2025-06-05 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 | 20.5833 | 3 | 1563.58 | 1476.97 | 0 | 86.61 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25334384100 |  | 501348607 |  | 6716216F | 2397485 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | CALISTA FLAT | 757 CALISTA FLAT | 067 | LEX | 2025-06-03 | U126604 | U126856 | 2025-05-23 | 2025-06-10 | 2025-06-10 |  | WILLIAM FULKS | 2025-06-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1511.13 | 0 | 0 | 0 | 1511.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25334384400 |  | 501354002 |  | 6724204F | 2399927 |  |  | 563 | EX | 1" P LONG/NO PRMT REQ | 2600B | WESTON | 376 WESTON PK | 067 | LEX | 2025-06-09 | U123111 | U126856 | 2025-05-23 | 2025-06-10 | 2025-06-10 |  | LYN STAFFORD | 2025-06-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 4121.15 | 269.95 | 297.73 | 15.84 | 3537.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25334595000 |  | 100291787 |  | 6720216G |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | RUSSELL CAVE | 2200 RUSSELL CAVE RD | 067 | LEX | 2025-05-28 | U124604 | U132928 | 2025-05-27 | 2025-05-27 |  |  | RSTRONG | 2025-05-27 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 2.05 | 1 | 2431.27 | 1323.23 | 803.26 | 107.94 | 196.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25334601800 |  | 501319195 |  | 6740204H | 2177603 |  |  | 563 | EX | 1" P SHORT | 2600B | ALEXIS | 426 ALEXIS WY | 049 | WIN | 2025-06-04 | U126602 | U126856 | 2025-05-27 | 2025-06-10 | 2025-06-10 |  | DEREK PAYTON | 2025-06-04 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26290012 |  | 1 | 1808.86 | 0 | 297.73 | 0 | 1511.13 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25334602100 |  | 501358739 |  | 6700212O | 2398395 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | ABINGDON | 517 ABINGDON AV | 239 | VER | 2025-06-06 | U129731 | U126856 | 2025-05-27 | 2025-06-10 | 2025-06-10 |  | EDWARD F GOINS | 2025-06-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8 | 1 | 3487.83 | 531.09 | 262.8 | 31.14 | 2662.8 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25334651000 |  | 100268592 |  | 7356256G |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | 34TH | 222 34TH ST | 019 | ASH | 2025-06-13 | ABHATFIE | U140273 | 2025-05-27 | 2025-06-17 | 2025-07-08 |  | ABHATFIE | 2025-06-13 | 2025-06-13 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 7.1833 | 2 | 542.75 | 512.68 | 0 | 30.07 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25334788000 |  | 100324072 |  | 6724208G |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | BRYANT | 1770 BRYANT RD | 067 | LEX | 2025-06-09 | HMCKUNE | U140273 | 2025-05-28 | 2025-06-18 | 2025-07-09 |  | HMCKUNE | 2025-06-09 | 2025-06-09 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 22.5667 | 3 | 1962.27 | 1308.44 | 15.08 | 638.75 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25334805400 |  | 501368854 |  | 6728212M | 2405655 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | BLACKFORD | 2841 BLACKFORD PY | 067 | LEX | 2025-06-11 | U123111 | U126856 | 2025-05-28 | 2025-06-11 | 2025-06-11 |  | LYN STAFFORD | 2025-06-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 2076.18 | 269.95 | 279.26 | 15.84 | 1511.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25334805700 |  | 501368858 |  | 6728212M | 2405655 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | BLACKFORD | 2825 BLACKFORD PY | 067 | LEX | 2025-06-06 | U123111 | U126856 | 2025-05-28 | 2025-06-11 | 2025-06-11 |  | LYN STAFFORD | 2025-06-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 2081.23 | 269.95 | 284.31 | 15.84 | 1511.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25334805900 |  | 501368925 |  | 6728212M | 2405655 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | BELHURST | 1901 BELHURST WY | 067 | LEX | 2025-06-03 | U128336 | U126856 | 2025-05-28 | 2025-06-11 | 2025-06-11 |  | JOSHUA COX | 2025-06-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 1808.86 | 0 | 297.73 | 0 | 1511.13 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25334806100 |  | 501313780 |  | 6716232B | 2289995 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | OAK HILL | 111 OAK HILL LN | 209 | GEO | 2025-06-13 | U123111 | U126856 | 2025-05-28 | 2025-06-16 | 2025-06-16 |  | LYN STAFFORD | 2025-06-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4 | 1 | 1625.88 | 274.43 | 277.6 | 16.1 | 1057.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25334806900 |  | 100301211 |  | 6716212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | DELMONT | 153 DELMONT DR 2 | 067 | LEX | 2025-05-29 | U124604 | U132928 | 2025-05-28 | 2025-11-07 | 2027-05-31 |  | KKINDER | 2025-05-28 | 2025-05-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 17.6167 | 3 | 2064.51 | 1256.79 | 540.84 | 266.88 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25334811500 |  | 100295650 |  | 6716216K |  |  |  | 565 | EX | REPLACE SERVICE | 2621P | CEDARWOOD | 833 CEDARWOOD DR | 067 | LEX | 2025-06-11 | MCRAIG | U124604 | 2025-05-28 | 2025-12-31 |  |  | MCRAIG | 2025-06-11 | 2025-05-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 25.6333 | 6 | 2671.78 | 1558.44 | 553.18 | 444.72 | 115.44 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25334812800 |  | 100247058 |  | 7352256L | 2403760 |  |  | 565 | EX | REPLACE SL/24026321400 | 2600B | NOLTE | 2815 NOLTE ST | 019 | ASH | 2025-05-28 | U123965 | U132386 | 2025-05-28 | 2025-12-19 |  |  | MBLANKE/CJH KYLE BLANKENSHIP | 2025-05-28 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1964.73 | 0 | 0 | 0 | 1964.73 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25334834800 |  | 501361880 |  | 6712228L | 2292762 |  |  | 563 | EX | 1' P LONG/PRMT RCVD | 2600B | BILL PERKINS | 137 BILL PERKINS LN LT63 | 209 | GEO | 2025-06-18 | U123111 | U133050 | 2025-05-28 | 2025-06-19 | 2025-06-19 |  | LYN STAFFORD | 2025-06-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 13 | 2 | 902.77 | 852.76 | 0 | 50.01 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25334840700 |  | 501361916 |  | 6712228L | 2292762 |  |  | 563 | EX | 99 1" P SHORT A&E HOMES 2ND | 2600B | RUTH MILLER | 153 RUTH MILLER DR LT87 | 209 | GEO | 2025-06-11 | U123111 | U132805 | 2025-05-28 | 2025-05-29 | 2025-06-11 |  | LYN STAFFORD | 2025-06-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 4 | 1 | 2348.88 | 274.43 | 279.26 | 16.1 | 1779.09 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25334846900 |  | 500162390 |  | 7336276J |  |  |  | 566 | EX | PAPER ABANDONMENT | 2621P | MUSKETEER | 146 MUSKETEER DR | 089 | GRE | 2025-06-03 | U123688 | U132928 | 2025-05-28 | 2025-05-28 |  |  | MCOLLET | 2025-05-28 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.15 | 1 | 242.32 | 86.49 | 0 | 155.83 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25334847300 |  | 500802545 |  | 6712232H | 0251147 |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | OSBORNE | 100 OSBORNE WY | 209 | GEO | 2025-06-19 | U126332 | U140273 | 2025-05-28 | 2025-06-18 | 2025-06-18 |  | DCOLLIN | 2025-06-11 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 12.8 | 2 | 4424.5 | 954.98 | 0 | 237.52 | 3232 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25334852800 |  | 100310598 |  | 6712208L |  |  |  | 565 | EX | SERVICE LINE REPLACEMENT | 2621P | SEATTLE | 728 SEATTLE DR | 067 | LEX | 2025-05-29 | U124604 | U132928 | 2025-05-28 | 2025-05-28 |  |  | CHEMMER | 2025-05-28 | 2025-05-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 10.7833 | 2 | 1232.36 | 593.06 | 604.94 | 34.36 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25334853100 |  | 501381917 |  | 7240216F |  |  |  | 563 | EX | 1" P SHORT | 2621P | OLD SILO HILL | 1643 OLD SILO HILL RD | 173 | MT | 2025-06-16 | DENNING | U132256 | 2025-05-28 | 2025-06-18 | 2025-06-18 |  | DENNING | 2025-06-16 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 13.8667 | 2 | 4276.39 | 1046.52 | 348.93 | 985.44 | 1895.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25334860800 |  | 501338092 |  | 6712208M | 2288773 |  |  | 563 | EX | 1" P SHORT DAILEY HOMES | 2600B | COCOS | 4159 COCOS WY LT20 | 067 | LEX | 2025-06-12 | U123111 | U134341 | 2025-05-28 | 2025-06-13 | 2025-06-13 |  | LYN STAFFORD | 2025-06-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 1574.67 | 270 | 231.09 | 15.83 | 1057.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25334860900 |  | 501338091 |  | 6712208M | 2288773 |  |  | 563 | EX | MANIFOLD W/ MASTER 501338092 | 2600B | COCOS | 4161 COCOS WY LT19 | 067 | LEX | 2025-06-12 | U123111 | U134341 | 2025-05-28 | 2025-06-13 | 2025-06-13 |  | LYN STAFFORD | 2025-06-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 312.92 | 0 | 0 | 0 | 312.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25334861000 |  | 501338090 |  | 6712208M | 2288773 |  |  | 563 | EX | MANIFOLD W/ MASTER 501338092 | 2600B | COCOS | 4163 COCOS WY LT18 | 067 | LEX | 2025-06-12 | U123111 | U134341 | 2025-05-28 | 2025-06-13 | 2025-06-13 |  | LYN STAFFORD | 2025-06-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 330.68 | 0 | 0 | 0 | 330.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25334939100 |  | 100322804 |  | 6716208H | 2293736 |  |  | 565 | EX | REPLACE SL/22026238800 | 2600B | KASTLE | 1258 KASTLE RD | 067 | LEX | 2025-05-30 | U128762 | U132386 | 2025-05-29 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-05-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2471.97 | 0 | 0 | 0 | 2471.97 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25334945900 |  | 100251023 |  | 7340268E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SEATON | 932 SEATON AV | 089 | GRE | 2025-06-02 | U124604 | U131366 | 2025-05-29 | 2025-05-29 | 2026-08-31 |  | RECUMP | 2025-05-30 | 2025-05-29 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 21.8 | 5 | 2525.59 | 1732.84 | 482.24 | 214.31 | 96.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25334969900 |  | 501361980 |  | 6716216E | 2403608 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2600B | DITTANY | 2462 DITTANY LN | 067 | LEX | 2025-06-13 | U123111 | U126856 | 2025-05-29 | 2025-06-16 | 2025-06-16 |  | LYN STAFFORD | 2025-06-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 2296.47 | 269.95 | 277.6 | 15.84 | 1733.08 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25334971700 |  | 501317318 |  | 6716236J | 2178365 |  |  | 563 | EX | 1" P LONG/PRMT RCVD | 2600B | MEADOW LARK | 131 MEADOW LARK TR | 209 | GEO | 2025-06-19 | U461322 | U126856 | 2025-05-29 | 2025-06-19 | 2025-06-19 |  | STEVE CANOY | 2025-06-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 10.65 | 1 | 1613.22 | 747.22 | 0 | 866 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25334982000 |  | 100312257 |  | 6716208I |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | BRADFORD | 248 BRADFORD DR | 067 | LEX | 2025-05-29 | KKINDER | U131366 | 2025-05-29 | 2025-05-29 | 2025-05-29 |  | KKINDER | 2025-05-29 | 2025-05-29 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.2167 | 4 | 1498.62 | 1115.96 | 325.85 | 56.81 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25334984000 |  | 501374462 |  | 6696112P | 2410689 |  |  | 563 | CO | 99 1" P SHORT/PRMT RCVD | 2600B | AZALEA | 745 AZALEA LN | 239 | VER | 2025-06-17 |  | U134375 | 2025-05-29 | 2025-06-12 | 2025-06-19 |  | LYN STAFFORD | 2025-06-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 |  | 1
KY | KY - WEST | 2621 | 25334999700 |  | 500076046 |  | 6720208I | 2513475 |  |  | 563 | EX | 20 1" P SHORT/PRMT RCVD | 2600B | CHINOE | 929 CHINOE PL | 067 | LEX | 2025-06-19 | U123111 | U132805 | 2025-05-29 | 2025-05-30 | 2025-06-19 |  | LYN STAFFORD | 2025-06-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 12 | 2 | 816.55 | 771.31 | 0 | 45.24 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25335007600 |  | 501381258 |  | 6720208O | 2514570 |  |  | 563 | EX | 1"P SHORT/NO PRMT REQ | 2600B | LAKE CLAIR | 605 LAKE CLAIR CT | 067 | LEX | 2025-06-19 | U123111 | U128266 | 2025-05-29 | 2025-05-30 | 2025-06-20 |  | LYN STAFFORD | 2025-06-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 285.79 | 269.95 | 0 | 15.84 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25335163300 |  | 500260515 |  | 7352260E |  |  |  | 565 | EX | NBT: UPGRADE SERVICE LINE | 2621P | AMANDA FURNACE | 507 AMANDA FURNACE DR | 089 | ASH | 2025-06-17 | U124604 | U123688 | 2025-05-30 | 2025-06-20 | 2025-06-20 |  | MCOLLET | 2025-06-16 | 2025-06-16 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 35.9833 | 5 | 4698.46 | 2535.63 | 567.81 | 1595.02 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25335411200 |  | 501379063 |  | 6728208J | 2513070 |  |  | 563 | EX | 1" P SHORT/NO PRMT REQ | 2600B | MEADOWLARK | 4109 MEADOWLARK RD | 067 | LEX | 2025-06-16 | U123111 | U126856 | 2025-06-02 | 2025-06-19 | 2025-06-19 |  | LYN STAFFORD | 2025-06-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1
KY | KY - EAST | 2631 | 25335421200 |  | 100248719 |  | 7356256E |  |  |  | 565 | EX | LEAK REPAIR - SERVICE LINE | 2621P | MOORE | 2433 MOORE ST | 019 | ASH | 2025-06-02 | MCOLLET | U137248 | 2025-06-02 | 2025-06-02 | 2025-06-02 |  | MCOLLET | 2025-06-02 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 6.55 | 1 | 2915.52 | 488.95 | 243.22 | 55.33 | 2128.02 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25335421900 |  | 501343072 |  | 7356220N | 2398575 |  |  | 563 | EX | 1 1/4" P SHORT | 2621P | FALLS CREEK | 191 FALLS CREEK DR | 127 | LOU | 2025-06-11 | U124604 | U126856 | 2025-06-02 | 2025-06-16 | 2025-06-16 |  | MCOLLET | 2025-06-10 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 24 | 3 | 4254.18 | 1711.5 | 667.26 | 1847.3 | 28.12 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25335422900 |  | 501383363 |  | 7356220N |  |  |  | 563 | EX | 1" P SHORT | 2621P | LOUISA TRACE | 4999 LOUISA TRACE | 127 | LOU | 2025-06-12 | U124604 | U126856 | 2025-06-02 | 2025-06-16 | 2025-06-16 |  | MCOLLET | 2025-06-11 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26310011 | 15.35 | 3 | 2854.42 | 1087.87 | 257.11 | 1376.24 | 133.2 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25335431100 |  | 100248650 |  | 7356256E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | MOORE | 2608 MOORE ST | 019 | ASH | 2025-06-04 | U124604 | U137248 | 2025-06-02 | 2025-06-02 | 2025-06-02 |  | ABHATFIE | 2025-06-03 | 2025-06-02 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 50.9833 | 8 | 4211.18 | 3452.87 | 39.97 | 515.58 | 202.76 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25335610700 |  | 100350592 |  | 6744204B | 1635077 |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | COLBY | 626 COLBY RD | 049 | WIN | 2025-06-03 | DENNING | U141176 | 2025-06-02 | 2025-06-02 | 2025-06-02 |  | DENNING | 2025-06-03 | 2025-06-03 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0021 | KYACN |  | 100 | 056532B26290021 | 17.2333 | 5 | 3407.42 | 1272 | 677.58 | 527.24 | 930.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25335644600 |  | 501320869 |  | 6728208I | 2182500 |  |  | 563 | EX | 99 1" P SHORT SKIP THOMAS | 2600B | ANGUS | 1348 ANGUS TL LT37 | 067 | LEX | 2025-06-16 | U123111 | U120250 | 2025-06-03 | 2025-06-17 | 2025-06-19 |  | LYN STAFFORD | 2025-06-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 5.25 | 1 | 375.08 | 354.31 | 0 | 20.77 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25335670200 |  | 100310735 |  | 6712204C |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | CORNWALL | 3307 CORNWALL DR | 067 | LEX | 2025-06-04 | U930915 | U137248 | 2025-06-03 | 2025-06-03 | 2025-06-03 |  | KOBRYAN | 2025-06-04 | 2025-06-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.1167 | 4 | 1253.4 | 1091.74 | 97.67 | 63.99 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25335680300 |  | 500187044 |  | 6708204I |  |  |  | 565 | VO | REPLACE SERVICE LINE - LEAKAGE | 2621P | DELANEY FERRY | 1185 DELANEY FERRY RD | 113 | NIC | 2025-06-10 | U124604 | U137248 | 2025-06-03 | 2025-05-25 | 2025-06-12 |  | KKINDER | 2025-06-03 | 2025-05-30 |  | A | [11 empty] | 25336872300 | 100 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25335683300 |  | 100312286 |  | 6716208I |  |  |  | 565 | EX | REPLACE SERVICE D514721 | 2621P | MILLBROOK | 2367 MILLBROOK DR | 067 | LEX | 2025-06-11 | RSTRONG | U124604 | 2025-06-03 | 2025-06-06 | 2025-06-24 |  | RSTRONG | 2025-06-11 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.8833 | 2 | 989.49 | 727.23 | 174.22 | 88.04 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25335704000 |  | 100303228 |  | 6712208C |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D512005 | 2621P | LILY | 948 LILY DR | 067 | LEX | 2025-06-05 | U124604 | U124604 | 2025-06-03 | 2025-06-03 | 2025-06-03 |  | MCRAIG | 2025-06-04 | 2025-06-04 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.6667 | 2 | 1839.71 | 950.42 | 428.29 | 400.32 | 60.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25335705300 |  | 100310755 |  | 6712208O |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D341715 | 2621P | BRAVINGTON | 3282 BRAVINGTON CT | 067 | LEX | 2025-06-05 | U124604 | U124604 | 2025-06-03 | 2025-06-03 | 2025-06-03 |  | MSHARON | 2025-06-04 | 2025-06-04 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.0167 | 3 | 1517.51 | 1063 | 392.19 | 62.32 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25335892500 |  | 100273695 |  | 6684228M |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | ASHLAND | 217 ASHLAND DR | 073 | FRA | 2025-06-05 | U930915 | U137248 | 2025-06-04 | 2025-06-04 | 2025-06-04 |  | RJCRAWF | 2025-06-04 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 10.3667 | 2 | 1341.95 | 753.6 | 60.72 | 443.27 | 84.36 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25335921500 |  | 100263427 |  | 7352256B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D359312 | 2621P | COMMANCHE | 1002 COMMANCHE DR | 019 | ASH | 2025-06-17 | MCOLLET | U123688 | 2025-06-04 | 2025-06-06 | 2025-06-25 |  | MCOLLET | 2025-06-17 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 23.55 | 3 | 3118.06 | 1618.93 | 388.52 | 1009.97 | 100.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25335932800 |  | 501266491 |  | 6720204O | 1963066 |  |  | 563 | EX | 1' P LONG/NO PRMT REQ | 2600B | HARPER WOODS | 3525 HARPER WOODS LN LT27 | 067 | LEX | 2025-06-16 | U123111 | U133050 | 2025-06-04 | 2025-06-19 | 2025-06-19 |  | LYN STAFFORD | 2025-06-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 4 | 1 | 285.79 | 269.96 | 0 | 15.83 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25335933100 |  | 501266492 |  | 6720204O | 1963066 |  |  | 563 | EX | 1' P LONG/NO PRMT REQ | 2600B | HARPER WOODS | 3529 HARPER WOODS LN LT26 | 067 | LEX | 2025-06-16 | U123111 | U133050 | 2025-06-04 | 2025-06-19 | 2025-06-19 |  | LYN STAFFORD | 2025-06-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 |  | 1 | 25845.92 | 0 | 0 | 0 | 25845.92 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25335934800 |  | 100275740 |  | 6684228C |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | FRAZIER | 120 FRAZIER RD | 073 | FRA | 2025-06-19 | RJCRAWF | U939463 | 2025-06-04 | 2025-07-18 | 2025-07-18 |  | RJCRAWF | 2025-06-19 | 2025-06-06 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 6.7833 | 4 | 1796.31 | 494.37 | 0 | 157.92 | 1144.02 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25335938200 |  | 100441073 |  | 6684228C |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | WILKINSON | 950 WILKINSON BV | 073 | FRA | 2025-06-19 | U930915 | U939463 | 2025-06-04 | 2025-07-18 | 2025-07-18 |  | RJCRAWF | 2025-06-19 | 2025-06-06 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 11.6833 | 4 | 2895.38 | 851.02 | 83.34 | 530.86 | 1430.16 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25335939500 |  | 100273711 |  | 6684228M |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D514724 | 2621P | ASHLAND | 116 ASHLAND DR | 073 | FRA | 2025-06-06 | U124604 | U124604 | 2025-06-04 | 2025-06-07 | 2025-06-25 |  | RJCRAWF | 2025-06-05 | 2025-06-04 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 14.9333 | 5 | 1706.67 | 1055.62 | 226.31 | 424.74 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25336149400 |  | 501383345 |  | 6748180 |  |  |  | 563 | EX | 1"P-LONG/NO PRMT REQ | 2621P | WACO LOOP | 227 WACO LOOP | 151 | WAC | 2025-06-17 | DENNING | U128727 | 2025-06-05 | 2025-06-06 | 2025-06-26 |  | DENNING | 2025-06-17 | 2025-06-16 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 26.5667 | 5 | 4961.73 | 2005.74 | 331.03 | 599.76 | 2025.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25336167800 |  | 100326098 |  | 6720208A |  |  |  | 565 | EX | SERVICE LINE UPGRADE | 2621P | LOUISIANA | 145 LOUISIANA AV | 067 | LEX | 2025-06-17 | JOCHOA | U124604 | 2025-06-05 | 2025-07-03 | 2025-07-03 |  | JOCHOA | 2025-06-17 | 2025-06-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 22.75 | 4 | 1643.46 | 1335.08 | 230.11 | 78.27 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25336174200 |  | 100312309 |  | 6716208I |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MAPLEWOOD | 2400 MAPLEWOOD DR | 067 | LEX | 2025-06-06 | U930915 | U137248 | 2025-06-05 | 2025-06-05 | 2025-06-05 |  | JOCHOA | 2025-06-05 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 26.8833 | 5 | 2088.02 | 1680.88 | 166.49 | 98.57 | 142.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25336233600 |  | 501348655 |  | 6716216F | 2397485 |  |  | 563 | CO | 1" P SHORT (BALL HOMES) | 2600B | CORSAGE | 2205 CORSAGE CT | 067 | LEX | 2025-06-17 |  | U126856 | 2025-06-06 | 2025-06-23 | 2025-06-23 |  | LYN STAFFORD | 2025-06-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 5.5 | 1 | 392.95 | 371.19 | 0 | 21.76 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25336235200 |  | 100263311 |  | 7352256F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D259749 | 2621P | WOODMONT | 333 W WOODMONT DR | 019 | ASH | 2025-06-10 | U124604 | U123688 | 2025-06-06 | 2025-06-05 | 2025-06-05 |  | ABHATFIE | 2025-06-09 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 16 | 3 | 1233.23 | 1164.92 | 0 | 68.31 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25336243400 |  | 100239444 |  | 7352264-I |  |  |  | 563 | EX | PAPER TAP W/100239441 | 2621P | BELLEFONTE | 416 BELLEFONTE ST | 089 | RUS | 2025-06-09 | U123688 | U128266 | 2025-06-06 | 2025-06-09 | 2025-06-20 |  | OFFICE | 2025-06-09 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26310011 |  | 1
KY | KY - EAST | 2631 | 25336244600 |  | 501373919 |  | 7352264I |  |  |  | 563 | EX | PAPER TAP W/100239441 | 2621P | BELLEFONTE | 420 BELLEFONTE ST A | 089 | RUS | 2025-06-09 | U123688 | U128266 | 2025-06-06 | 2025-06-09 | 2025-06-20 |  | OFFICE | 2025-06-09 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26310011 |  | 1
KY | KY - EAST | 2631 | 25336244800 |  | 501373917 |  | 7352264I |  |  |  | 563 | EX | PAPER TAP W/100239441 | 2621P | BELLEFONTE | 420 BELLEFONTE ST B | 089 | RUS | 2025-06-09 | U123688 | U128266 | 2025-06-06 | 2025-06-09 | 2025-06-20 |  | OFFICE | 2025-06-09 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26310011 |  | 1
KY | KY - EAST | 2631 | 25336244900 |  | 501373918 |  | 7352264I |  |  |  | 563 | EX | PAPER TAP W/100239441 | 2621P | BELLEFONTE | 420 BELLEFONTE ST C | 089 | RUS | 2025-06-09 | U123688 | U128266 | 2025-06-06 | 2025-06-09 | 2025-06-20 |  | OFFICE | 2025-06-09 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26310011 |  | 1
KY | KY - CENTRAL | 2629 | 25336263300 |  | 500512961 |  | 7240212B | 2514881 |  |  | 563 | EX | 2" P LONG/NO PRMT NEEDED | 2621P | LOCUST | 107 E LOCUST ST | 173 | MT | 2025-06-18 | DENNING | U130192 | 2025-06-06 | 2025-06-20 | 2025-06-20 |  | DENNING | 2025-06-18 | 2025-06-11 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 29.3333 | 5 | 3241.46 | 2203.15 | 819.42 | 218.89 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25336276100 |  | 501372635 |  | 6736228K | 2398765 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2621P | LINZI | 117 LINZI WY | 017 | PAR | 2025-06-20 | U123688 | U126856 | 2025-06-06 | 2025-06-20 | 2025-06-20 |  | NRICHIE | 2025-06-17 | 2025-06-12 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 4.7 | 4 | 416.26 | 347.08 | 0 | 20.34 | 48.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25336276300 |  | 501372634 |  | 6736228K | 2398765 |  |  | 563 | EX | 1" P LONG (BALL HOMES) | 2621P | LINZI | 116 LINZI WY | 017 | PAR | 2025-06-20 | U123688 | U126856 | 2025-06-06 | 2025-06-20 | 2025-06-20 |  | NRICHIE | 2025-06-17 | 2025-06-12 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26290011 | 16.1 | 5 | 46495.5 | 1171.18 | 0 | 68.66 | 45255.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25336675900 |  | 501379071 |  | 6728208J | 2513070 |  |  | 563 | EX | 1" P SHORT CUSTOM KY HOME | 2600B | MEADOWLARK | 4141 MEADOWLARK RD LT81 | 067 | LEX | 2025-06-17 | U461322 | U142144 | 2025-06-09 | 2025-06-10 | 2025-06-23 |  | STEVE CANOY | 2025-06-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 2.1 | 1 | 320.08 | 147.02 | 0 | 173.06 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25336676000 |  | 501379070 |  | 6728208J | 2513070 |  |  | 563 | EX | 1" P SHORT CUSTOM KY HOME | 2600B | MEADOWLARK | 4137 MEADOWLARK RD LT80 | 067 | LEX | 2025-06-17 | U461322 | U142144 | 2025-06-09 | 2025-06-10 | 2025-06-23 |  | STEVE CANOY | 2025-06-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26210012 | 6.05 | 1 | 903.03 | 414.76 | 0 | 488.27 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25336684800 |  | 100249932 |  | 7360248E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D359302 | 2621P | MAYO TRAIL | 10112 MAYO TRAIL RD | 019 | CAT | 2025-06-11 | U124604 | U123688 | 2025-06-09 | 2025-10-23 | 2027-04-30 |  | RECUMP | 2025-06-10 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 27.75 | 5 | 2369.41 | 1885.77 | 91.47 | 392.17 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25336687700 |  | 501358745 |  | 6700212O | 2398395 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | ABINGDON | 556 ABINGDON AV | 239 | VER | 2025-06-18 | U461322 | U126856 | 2025-06-09 | 2025-06-23 | 2025-06-23 |  | STEVE CANOY | 2025-06-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 2.9667 | 1 | 452.91 | 209.81 | 0 | 243.1 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25336687800 |  | 501358746 |  | 6700212O | 2398395 |  |  | 563 | EX | 1" P SHORT (BALL HOMES) | 2600B | ABINGDON | 560 ABINGDON AV | 239 | VER | 2025-06-18 | U461322 | U126856 | 2025-06-09 | 2025-06-23 | 2025-06-23 |  | STEVE CANOY | 2025-06-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00563 | 3200563 |  |  | WP0012 |  |  | 100 | 056332B26230012 | 8.0333 | 1 | 1213.29 | 561.96 | 0 | 651.33 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 25336704700 |  | 501383644 |  | 7352144T |  |  |  | 563 | EX | 1" P SHORT NO PERMIT NEEDED | 2621P | KY ROUTE 979 | 7617 KY ROUTE 979 | 071 | GRE | 2025-06-18 | U130172 | U129176 | 2025-06-09 | 2025-06-09 | 2025-06-23 |  | J HOWARD | 2025-06-18 | 2025-06-13 |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26330011 | 20.2667 | 3 | 2208.31 | 1612.01 | 0 | 596.3 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25336705100 |  | 501361324 |  | 6716216E | 2403608 |  |  | 563 | CO | 1" P LONG (BALL HOMES) | 2600B | DAHLIA | 661 DAHLIA DR | 067 | LEX | 2025-06-17 |  | U126856 | 2025-06-09 | 2025-06-23 | 2025-06-23 |  | LYN STAFFORD | 2025-06-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00563 | 3200563 |  |  | WP0011 |  |  | 100 | 056332B26210011 | 4 | 1 | 285.83 | 270 | 0 | 15.83 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25336846000 |  | 100262176 |  | 7352256D | 2409943 |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | OLD STAGE | 538 OLD STAGE RD | 019 | ASH | 2025-06-10 | U124015 | U137248 | 2025-06-10 | 2025-06-10 |  |  | ORA SLONE | 2025-06-10 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 |  | 1 | 2148.39 | 0 | 0 | 0 | 2148.39 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25336900000 |  | 100345809 |  | 6696212D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MILDRED | 783 MILDRED ST | 239 | VER | 2025-06-10 | U128410 | U137248 | 2025-06-10 | 2025-10-15 | 2027-04-30 |  | CDESPAIN | 2025-06-10 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 |  | 1
KY | KY - EAST | 2631 | 25337198200 |  | 100247107 |  | 7352256L | 2403760 |  |  | 565 | EX | REPLACE W/ 24-0263214-00 | 2600B | CAMPBELL | 2723 CAMPBELL ST | 019 | ASH | 2025-06-11 | U123965 | U125768 | 2025-06-11 | 2025-12-23 |  |  | MBLANKE/CJH MITCHELL DICKESS | 2025-06-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1964.73 | 0 | 0 | 0 | 1964.73 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25337198300 |  | 100247108 |  | 7352256L | 2403760 |  |  | 565 | EX | REPLACE W/ 24-0263214-00 | 2600B | CAMPBELL | 2801 CAMPBELL ST | 019 | ASH | 2025-06-12 | U123965 | U125768 | 2025-06-11 | 2025-12-23 |  |  | MBLANKE/CJH MITCHELL DICKESS | 2025-06-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1964.73 | 0 | 0 | 0 | 1964.73 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25337224100 |  | 100273676 |  | 6684228M |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | EXMOOR | 209 EXMOOR DR | 073 | FRA | 2025-06-11 | DCOLLIN | U137248 | 2025-06-11 | 2025-06-11 | 2025-06-11 |  | DCOLLIN | 2025-06-11 | 2025-06-11 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8.6167 | 3 | 920.54 | 599.32 | 226.5 | 94.72 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25337261200 |  | 100302196 |  | 6712212K |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BORDEAUX | 1308 BORDEAUX DR | 067 | LEX | 2025-06-12 | U124604 | U137248 | 2025-06-11 | 2025-11-12 | 2027-05-31 |  | TROE | 2025-06-11 | 2025-05-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 20.5333 | 6 | 1583.28 | 1183.79 | 329.62 | 69.87 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25337271800 |  | 100273584 |  | 6680224C |  |  |  | 565 | EX | REPLACE SL-LEAKAGE D341912 | 2621P | HAWKEEGAN | 255 HAWKEEGAN DR | 073 | FRA | 2025-06-13 | U124604 | U124604 | 2025-06-11 | 2025-06-11 | 2025-06-11 |  | RJCRAWF | 2025-06-12 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 18.5833 | 3 | 4549.56 | 1349.87 | 321.03 | 79.14 | 2799.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25337291900 |  | 100340437 |  | 6724212E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | RALEIGH | 1615 RALEIGH RD | 067 | LEX | 2025-06-12 | U930915 | U137607 | 2025-06-11 | 2025-06-11 | 2025-06-11 |  | TROE | 2025-06-12 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 15.0667 | 2 | 1285.38 | 1005.59 | 220.82 | 58.97 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25337455200 |  | 100423675 |  | 7352256D |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | OLD STAGE | 532 OLD STAGE RD | 019 | ASH | 2025-06-12 | U124015 | U132990 | 2025-06-12 | 2025-06-12 |  |  | ORA SLONE | 2025-06-12 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2844.59 | 0 | 0 | 0 | 2844.59 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25337543300 |  | 100241861 |  | 7356252D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | WILLIAMS | 5033 WILLIAMS AV | 019 | ASH | 2025-06-13 | U124604 | U137607 | 2025-06-12 | 2025-04-15 | 2026-10-31 |  | MCOLLET | 2025-06-12 | 2025-06-12 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 57 | 5 | 10588.42 | 4104.23 | 531.71 | 2308.96 | 3643.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25337787600 |  | 100324619 |  | 6720204B |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SUTHERLAND | 3368 SUTHERLAND DR | 067 | LEX | 2025-06-16 | U124604 | U132928 | 2025-06-13 | 2025-06-06 | 2025-06-24 |  | WCRIM | 2025-06-13 | 2025-06-12 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 16.5167 | 3 | 1379.19 | 918.45 | 328.46 | 53.84 | 78.44 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25337797400 |  | 501384273 |  | 7356260M |  |  |  | 563 | EX | PAPER W/100264457 | 2621P | BATH | 804 BATH AV UPPER | 019 | ASH | 2025-06-16 | U123688 | U134375 | 2025-06-13 | 2025-06-27 | 2025-06-27 |  | OFFICE | 2025-06-16 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00563 | 3200563 |  |  | WP0011 | NBPEX |  | 100 | 056332B26310011 |  | 1
KY | KY - EAST | 2631 | 25338013900 |  | 100252908 |  | 7356256F |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | 29TH | 1028 29TH ST | 019 | ASH | 2025-06-16 | ABHATFIE | U137248 | 2025-06-16 | 2025-06-16 | 2025-06-16 |  | ABHATFIE | 2025-06-16 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.48333 | 1 | 40.3 | 38.07 | 0 | 2.23 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25338015700 |  | 100465551 |  | 6716200D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | EDGEWOOD | 857 EDGEWOOD DR | 067 | LEX | 2025-06-17 | U124604 | U137248 | 2025-06-16 | 2025-10-09 | 2027-04-30 |  | MCRAIG | 2025-06-16 | 2025-05-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 24.6833 | 6 | 3991.44 | 2175.66 | 259.2 | 1492.94 | 63.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25338039000 |  | 500085027 |  | 6720204N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | ABBEYWOOD | 2332 ABBEYWOOD RD | 067 | LEX | 2025-06-17 | U124604 | U144763 | 2025-06-16 | 2025-10-31 | 2027-05-31 |  | JOCHOA | 2025-06-16 | 2025-06-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 16.2833 | 6 | 1413.59 | 979.51 | 231.63 | 57.41 | 145.04 | 0 | 0 | 0
KY | KY - EAST | 2631 | 25338169700 |  | 100247706 |  | 7352256H |  |  |  | 565 | EX | SERVICE LINE REPAIR | 2621P | EMERSON | 2133 EMERSON ST | 019 | ASH | 2025-06-17 | MCOLLET | U134902 | 2025-06-17 | 2025-06-17 |  |  | MCOLLET | 2025-06-17 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 0.11667 | 1 | 2595.59 | 1143.71 | 273.39 | 1070.45 | 108.04 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25338186700 |  | 100281218 |  | 6700220K |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | OLD FRANKFORT | 3527 OLD FRANKFORT PK FG40 | 239 | VER | 2025-06-17 | U128410 | U137248 | 2025-06-17 | 2025-06-17 |  |  | CDESPAIN | 2025-06-12 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2.96 | 0 | 0 | 0 | 2.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25338242400 |  | 100305177 |  | 6712212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | DARIEN | 1808 DARIEN DR | 067 | LEX | 2025-06-18 | U130722 | U137248 | 2025-06-17 | 2025-11-19 | 2027-05-31 |  | MCRAIG | 2025-06-17 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 6.0167 | 2 | 939.56 | 389.07 | 0 | 399.53 | 150.96 | 0 | 0 | 0
KY | KY - EAST | 2633 | 25338354300 |  | 501343451 |  | 7344156T |  |  |  | 566 | EX | ABANDON SL | 2621P | KY ROUTE 3188 | 590 KY ROUTE 3188 | 071 | LAN | 2025-06-18 | U129900 | U132625 | 2025-06-18 | 2025-06-18 |  |  | U129900 | 2025-06-18 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - WEST | 2621 | 25338371100 |  | 100322769 |  | 6716208D | 2293736 |  |  | 565 | EX | REPLACE SL/22026238800 | 2600B | SCOVILLE | 1274 SCOVILLE RD | 067 | LEX | 2025-06-18 | U128762 | U132386 | 2025-06-18 | 2025-12-19 |  |  | RANDALL TINCHER | 2025-06-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 56.24 | 0 | 0 | 0 | 56.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 25338663700 |  | 100325533 |  | 6720208E | 2514289 |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | INDIAN MOUND | 1204 INDIAN MOUND RD | 067 | LEX | 2025-06-20 | U930915 | U139417 | 2025-06-20 | 2025-06-20 |  |  | JBURFOR | 2025-06-20 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 1.2167 | 1 | 227.3 | 76.17 | 17.9 | 4.47 | 128.76 | 0 | 0 | 0
KY | KY - WEST | 2623 | 25338681800 |  | 100450218 |  | 6684228F |  |  |  | 566 | EX | ABANDON SERVICE | 2621P | KENTUCKY | 874 KENTUCKY AV | 073 | FRA | 2025-06-20 | DCOLLIN | U124604 | 2025-06-20 | 2025-06-20 |  |  | DCOLLIN | 2025-06-20 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 1.3 | 1 | 188.61 | 99.97 | 44.49 | 44.15 | 0 | 0 | 0 | 0

## SAP Data (hidden)
Location | City | Description | Order | WBS order header | System status | User Status | MaintActivityType | Total planned costs | Total actual costs | Basic start date | Basic finish date | Actual start date | Final Due Month | Final Due Day | Final Due Yr | Entered By
2621 | LEXINGTON | FACILITY DAMAGE MAIN LINE 253320172 | 4000094590 | ANC32.0000.00001 | REL MANC PRC SETC | NEW ADJ FCMP NSFS RCFO REIM | MAI | 850.94 | 2600.23 | 2025-11-28 | 2025-11-29 |  |  |  |  | BTC_ALL
2629 | PARIS | Leak Repair | 4000096451 | ANC32.0000.00001 | CRTD MANC PRC | NEW NSFS RCFO | MAI | 633.18 | 0 | 2026-01-01 | 2026-01-22 |  | 1899-12-31 | 1900-01-21 | 1905-07-18 | BTC_ALL
2629 | PARIS | Leak Repair | 4000096519 | ANC32.0000.00001 | CRTD MANC PRC | NEW NSFS RCFO | MAI | 633.18 | 0 | 2026-01-01 | 2026-01-22 |  | 1899-12-31 | 1900-01-21 | 1905-07-18 | BTC_ALL
2629 | PARIS | Leak Repair | 4000096531 | ANC32.0000.00001 | CRTD MANC PRC | NEW NSFS RCFO | MAI | 633.18 | 0 | 2026-01-01 | 2026-01-22 |  | 1899-12-31 | 1900-01-21 | 1905-07-18 | BTC_ALL
2629 | PARIS | Leak Repair | 4000096657 | ANC32.0000.00001 | CRTD MANC PRC | NEW NSFS RCFO | MAI | 633.18 | 0 | 2026-01-01 | 2026-01-22 |  | 1899-12-31 | 1900-01-21 | 1905-07-18 | BTC_ALL
2629 | PARIS | Leak Repair | 4000096746 | ANC32.0000.00001 | CRTD MANC PRC | NEW NSFS RCFO | MAI | 633.18 | 0 | 2026-01-01 | 2026-01-22 |  | 1899-12-31 | 1900-01-21 | 1905-07-18 | BTC_ALL
2629 | PARIS | Leak Repair | 4000096859 | ANC32.0000.00001 | CRTD MANC PRC | NEW NSFS RCFO | MAI | 633.18 | 0 | 2026-01-01 | 2026-01-22 |  | 1899-12-31 | 1900-01-21 | 1905-07-18 | BTC_ALL
2629 | PARIS | Leak Repair | 4000096962 | ANC32.0000.00001 | CRTD MANC PRC | NEW NSFS RCFO | MAI | 633.18 | 0 | 2026-01-01 | 2026-01-22 |  | 1899-12-31 | 1900-01-21 | 1905-07-18 | BTC_ALL
2621 |  | FCLTY DMG MAIN LINE | 4000097062 | ANC32.0000.00001 | REL MANC NMAT PRC SETC | NEW FCMP MIFE NSFS RCFO REIM | MAI | 710.28 | 682.01 | 2026-01-23 | 2026-01-23 |  |  |  |  | BTC_ALL
2621 | LEXINGTON | Repair Distribution Main | 4000097116 | ANC32.0000.00001 | REL MANC NMAT PRC SETC | NEW FCMP MIFE NSFS RCFO | MAI | 847.8 | 110.81 | 2026-01-27 | 2026-01-28 |  | 1899-12-31 | 1900-01-27 | 1905-07-18 | BTC_ALL
2621 | LEXINGTON | Repair Distribution Main | 4000097292 | ANC32.0000.00001 | REL MANC NMAT PRC SETC | NEW FCMP MIFE NSFS RCFO | MAI | 847.8 | 93.47 | 2026-01-26 | 2026-01-27 |  | 1899-12-31 | 1900-01-26 | 1905-07-18 | BTC_ALL
2623 | GEORGETOWN | Repair Distribution Main | 4000097293 | ANC32.0000.00001 | REL MANC NMAT PRC SETC | NEW FCMP MIFE NSFS RCFO | MAI | 847.8 | 131.32 | 2026-01-28 | 2026-01-29 |  | 1899-12-31 | 1900-01-28 | 1905-07-18 | BTC_ALL
2621 |  | Leak Repair | 4000098701 | ANC32.0000.00001 | REL CSER MANC NMAT PRC SETC | NEW FCMP MIFE NSFS RCFO | MAI | 847.8 | 0 | 2025-07-08 | 2025-07-23 |  | 1900-01-06 | 1900-01-22 | 1905-07-17 | BTC_ALL
2623 | GEORGETOWN | REPAIR DIST MAIN - 1202 OLD OXFORD RD GE | 4000098702 | ANC32.0000.00001 | REL MANC NMAT PRC SETC | NEW FCMP MIFE NSFS RCFO | MAI | 2268.56 | 469.01 | 2025-10-01 | 2025-10-02 |  | 1900-01-09 | 1900-01-01 | 1905-07-17 | BTC_ALL
2621 |  | MAINTENANCE OF MAIN | 4000098900 | ANC32.0000.00001 | REL MANC NMAT PRC SETC | NEW FCMP MIFE NSFS RCFO | MAI | 1913.42 | 0 | 2025-10-23 | 2025-12-22 |  | 1899-12-31 | 1900-01-20 | 1905-07-18 | BTC_ALL
2631 | Ashland | Leak Repair/NO PRMT REQURIED | 4000098958 | ANC32.0000.00001 | CRTD MANC PRC | NEW NSFS RCFO | MAI | 251.46 | 0 | 2026-02-13 | 2026-03-06 |  | 1900-01-02 | 1900-01-05 | 1905-07-18 | BTC_ALL
2621 | LEXINGTON | Leak Repair/NO PRMT REQUIRED | 4000100375 | ANC32.0000.00001 | CRTD MANC PRC | NEW NSFS RCFO | MAI | 522.79 | 0 | 2026-02-09 | 2027-02-04 |  | 1900-01-04 | 1900-01-04 | 1905-07-19 | BTC_ALL
2631 | ASHLAND | FCLTY DMG MAIN LINE/PRMT RCVD | 4000100428 | ANC32.0000.00001 | REL CSER MANC NMAT PRC SETC | NEW FCMP MIFE NSFS RCFO REIM | MAI | 536.46 | 2352.46 | 2026-03-20 | 2026-03-20 |  |  |  |  | BTC_ALL
2629 | PARIS | Repair Distribution Main | 4000101419 | ANC32.0003.00911 | REL CSER MANC NMAT PRC SETC | NEW FCMP MIFE NSFS RCFO | MAI | 2497.44 | 8.13 | 2026-01-27 | 2026-02-17 |  | 1900-01-01 | 1900-01-16 | 1905-07-18 | BTC_ALL
2629 | PARIS | Repair Distribution Main | 4000101420 | ANC32.0003.00911 | REL CSER MANC NMAT PRC SETC | NEW FCMP MIFE NSFS RCFO | MAI | 932.32 | 4.65 | 2026-01-27 | 2027-01-22 |  | 1900-01-03 | 1900-01-21 | 1905-07-19 | BTC_ALL
2621 | LEXINGTON | Reset/Raise/Lower/Replace Vlv Box | 4000101841 | ANC32.0003.00911 | CRTD MANC NMAT PRC | NEW NSFS RCFO | MAI | 125.84 | 0 | 2026-02-27 | 2026-05-02 |  | 1900-01-04 | 1900-01-01 | 1905-07-18 | BTC_ALL
2623 | FRANKFORT | Leak Repair/NO PRMT REQUIRED | 4000102257 | ANC32.0003.00911 | CRTD MANC PRC | NEW NSFS RCFO | MAI | 283.72 | 0 | 2026-02-15 | 2027-01-11 |  | 1900-01-01 | 1900-01-09 | 1905-07-19 | BTC_ALL
2621 |  | REPAIR MAIN - 144 TURNER COMMONS WAY | 4000103401 | ANC32.0003.00911 | REL MANC NMAT PRC SETC | NEW FCMP MIFE NSFS RCFO | MAI | 22979.53 | 0 | 2025-11-18 | 2025-12-18 |  | 1900-01-11 | 1900-01-17 | 1905-07-17 | BTC_ALL
2631 |  | CNV-19026913100 RETIRE 705'-2/3/4\" BS/P | 4000074117 | ANC32.0000.00001 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 116.6 | 2024-12-31 | 2024-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-16 | C_U139391
2631 |  | CNV-19026913000 INSTALL 730'-2\\\PMMP.. | 4000075944 | ANC32.0000.00001 | REL PCNF MANC NMAT PRC SETC | NEW REV | MAI | 0 | 96680.57 | 2024-01-08 | 2024-12-31 | 2025-07-31 | 12 | 31 | 2024 | C_U139391
2623 |  | Cutover Validation Overhead KY - RHARDEN | 4000082774 | ANC32.0000.00001 | CRTD ESTC MANC NTUP PRC SKKP | PLN CAN | MAI | 40840.9 | 0 | 2025-09-02 | 2025-11-29 |  | 11 | 29 | 2025 | U134232
2631 |  | CNV-24026354400 INSTALL 20'-4\" PMLP | 4000074002 | ANC32.0000.00002 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1.86 | 2024-12-31 | 2024-12-31 |  | 12 | 31 | 2024 | C_U139391
2631 |  | CNV-20026983300 INSTALL 6,600'-2\\\/4\. | 4000076073 | ANC32.0000.00002 | REL PCNF MANC NMAT PRC SETC | NEW REV | MAI | 0 | 675213.22 | 2024-03-01 | 2024-12-31 | 2025-07-31 | 12 | 31 | 2024 | C_U139391
2629 |  | ANC-SMRP Sunset Dr-Paris | 4000078454 | ANC32.0000.00004 | REL PCNF MANC NMAT PRC SETC | SCHD | MAI | 46.68 | 2227.51 | 2025-07-16 | 2025-12-31 | 2025-09-02 | 12 | 31 | 2025 | C_U139391
2629 |  | ANC-SMRP Sunset Dr ABN-Paris | 4000078456 | ANC32.0000.00004 | REL PCNF NMAT PRC SETC | NEW | MAI | 0 | 572.15 | 2025-12-31 | 2025-12-31 | 2025-07-31 | 12 | 31 | 2025 | C_U139391
2629 |  | ANC-SMRP Sunset Dr Land-Paris | 4000084799 | ANC32.0000.00004 | REL NMAT PRC SETC | NEW NSFS | LND | 0 | 19854.2 | 2025-12-30 | 2025-12-31 |  | 12 | 31 | 2025 | C_U141034
2629 |  | ANC-SMRP Camelot Dr IP-Winchester | 4000075824 | ANC32.0000.00005 | REL GMPS MANC PRC SETC | NPRG ADJ | MAI | 40844.66 | 95096.44 | 2025-07-21 | 2025-12-31 |  | 12 | 31 | 2025 | C_U139391
2629 |  | ANC-SMRP Camelot Dr MP-Winchester | 4000078458 | ANC32.0000.00005 | REL PCNF GMPS MANC PRC SETC | COCO ADJ FCMP | MAI | 1791702.55 | 569724.87 | 2025-08-20 | 2025-12-31 | 2025-08-03 | 12 | 31 | 2025 | C_U139391
2629 |  | ANC-SMRP Camelot Dr ABN-Winchester | 4000078481 | ANC32.0000.00005 | REL PCNF MANC PRC SETC | NEW ADJ | MAI | 175952.55 | 608.48 | 2025-08-20 | 2025-12-31 | 2025-08-05 | 12 | 31 | 2025 | C_U139391
2629 |  | CNV-24026349200 ACQUIRE EASEMENT | 4000084795 | ANC32.0000.00005 | TECO JBFI NMAT PRC SETC | NEW FCMP NSFS | LND | 0 | 1800 | 2025-12-30 | 2025-12-31 |  | 12 | 31 | 2025 | C_U141034
2629 |  | CNV-17026724700 RETIRE 350' - 3\" PMLP | 4000074081 | BET32.0000.00014 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6408.49 | 2023-12-29 | 2023-12-31 | 2025-07-31 | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2633 |  | CNV-25026394000 EMER INSERT 280'-1.2\\\. | 4000080083 | ANC32.0000.00006 | REL MANC NMAT PRC SETC | SCHD | MAI | 0 | 180.59 | 2025-10-28 | 2025-10-31 |  | 10 | 31 | 2025 | C_U139391
2633 |  | CNV-25026394100 EMER - RETIRE 284'-2\"BS | 4000080085 | ANC32.0000.00006 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 19.15 | 2025-10-31 | 2025-10-31 |  | 10 | 31 | 2025 | C_U139391
2632 |  | CNV-21026127100 RETIRE 9400'-2\"&4\" BS& | 4000074120 | ANC32.0000.00168 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2631 |  | CNV-21026130500 RETIRE 25,000' OF BSLP M | 4000074121 | ANC32.0000.00167 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1026.35 | 2023-12-29 | 2023-12-31 | 2025-07-31 | 1900-01-11 | 1900-01-07 | 1905-07-16 | C_U139391
2629 |  | CNV-21026140501 INSTALL 1,985'-6\" CSHP | 4000074122 | ANC32.0000.00189 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2629 |  | CNV-21026140600 RETIRE 2,598'- 6\" BSHP | 4000074123 | ANC32.0000.00189 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2631 |  | CNV-21026154800 RETIRE 35'-3\" CSMP | 4000074124 | ANC32.0000.00167 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2621 |  | CNV-21026997900 RETIRE 6300' OF 4\"/6\"C | 4000074125 | ANC32.0000.00164 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 1900-01-07 | 1900-01-30 | 1905-07-16 | C_U139391
2631 |  | CNV-20026978200 RETIRE 8983' LP - 2520' | 4000074158 | ANC32.0000.00161 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 233.2 | 2023-12-29 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2631 |  | CNV-20026983400 RETIRE 5374'-4\" BSLP/CS | 4000074159 | ANC32.0000.00002 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 92.88 | 2023-12-29 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-16 | C_U139391
2631 |  | CNV-20026983600 ABANDON 1667'-2/3/4\" PM | 4000074160 | ANC32.0000.00162 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 290.24 | 2023-12-29 | 2023-12-31 | 2025-07-30 | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2629 |  | CNV-22026230500 RETIRE 1,368' - MP MAIN | 4000074332 | ANC32.0000.00190 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2633 |  | CNV-25026396700 INSTALL RECTIFIER/BULLHO | 4000080089 | ANC32.0000.00006 | REL MANC PRC SETC | NPRG ADJ FCMP MIFE | MAI | 7471.7 | 1080.72 | 2025-08-28 | 2025-08-28 |  |  |  |  | C_U139391
2629 |  | ANC-Wisemantown Rd Rectifier-Irvine | 4000080091 | ANC32.0000.00006 | REL MANC PRC SETC | NPRG ADJ FCMP MIFE | MAI | 15373.08 | 4338.37 | 2025-08-28 | 2025-08-28 |  | 8 | 31 | 2025 | C_U139391
2629 |  | ANC-SMRP Rowland Ave-Winchester | 4000076071 | ANC32.0000.00007 | REL CSER GMPS MANC PRC SETC | NEW ADJ | MAI | 193773.65 | 16615.18 | 2026-01-01 | 2026-12-31 |  | 12 | 31 | 2026 | C_U139391
2621 |  | CNV-22026241600 RETIRE 30'-2\" PMMP | 4000074336 | BET32.0000.00031 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2621 |  | CNV-22026163300 RETIRE 800' OF 4\"BSLP M | 4000074354 | ANC32.0000.00173 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2629 |  | CNV-22026164100 RETIRE 6,711'-BS/CS IP | 4000074355 | ANC32.0000.00174 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 663.38 | 2023-12-29 | 2023-12-31 | 2025-07-31 | 1900-01-11 | 1900-01-30 | 1905-07-16 | C_U139391
2629 |  | CNV-22026164300 RETIRE 3,574'-BSLP | 4000074356 | ANC32.0000.00175 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 136.8 | 2023-12-29 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2621 |  | ANC-BOB O LINK SMRP-LEXINGTON PLANNED F | 4000078064 | ANC32.0000.00010 | REL PCNF GMPS MANC PRC SETC | SCHD ADJ | MAI | 1710160.13 | 1002334.59 | 2025-10-22 | 2026-12-31 | 2026-02-16 | 12 | 31 | 2026 | C_U139391
2623 |  | CNV-22026170800 INSTALL 15,885'-2\"&4\"P | 4000076819 | ANC32.0000.00014 | REL CSER NMAT PRC SETC | NEW NSFS | MAI | 0 | 0 | 2026-05-20 | 2026-12-31 |  | 12 | 31 | 2026 | C_U139391
2631 |  | CNV-22026172400 RETIRE 4792'-2/4/8\" PL/ | 4000074374 | ANC32.0000.00181 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 233.2 | 2023-12-29 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-16 | C_U139391
2621 |  | CNV-22026183200 RETIRE 3765' OF 2-4\" CS | 4000074375 | PIG32.0000.00027 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2621 |  | CNV-22026183400 RETIRE 702' OF 6\" BSHP | 4000074376 | PIG32.0000.00027 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 233.2 | 2023-12-29 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2621 | LEXINGTON |  | 4000077985 | ANC32.0000.00017 | REL MANC PRC SETC | COCO ADJ FCMP | MAI | 21327.92 | 73009.05 | 2025-07-17 | 2025-12-31 |  | 12 | 31 | 2025 | C_U139391
2621 |  | CNV-22026213000 RETIRE 2015'-8/4/2\" BSM | 4000074378 | ANC32.0000.00177 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 233.2 | 2023-12-29 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2621 |  | CNV-22026219500 RETIRE 380' OF 4\"BSMP M | 4000074379 | ANC32.0000.00186 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 91.2 | 2023-12-29 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2629 |  | CNV-23026248800 RETIRE 50' - 2\" CSMP | 4000074671 | BET32.0000.00033 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2621 |  | CNV-23026264800 RETIRE 100' OF 3\"BSLP M | 4000074672 | ANC32.0000.00220 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 1900-01-07 | 1900-01-10 | 1905-07-16 | C_U139391
2623 |  | CNV-23026268600 PM-DE LINE ILI PH2 DENT | 4000074673 | BET32.0000.00032 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 798261.74 | 2023-12-29 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2629 |  | CNV-23026268700 PM-DE LINE PH 2 DENT 2/S | 4000074674 | BET32.0000.00032 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 92219 | 2023-12-29 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2623 |  | CNV-23026269200 PM-DE LINE ILI PH2 BEND | 4000074675 | BET32.0000.00032 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 130268.57 | 2023-12-29 | 2023-12-29 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2623 |  | CNV-23026269300 PM-DE LINE ILI PH2 DENT | 4000074676 | BET32.0000.00032 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1444.19 | 2023-12-29 | 2023-12-29 | 2025-07-31 | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2629 |  | CNV-23026269400 PM-DE LINE ILI PH2 DENT2 | 4000074677 | BET32.0000.00032 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 26843.67 | 2023-12-29 | 2023-12-29 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2631 |  | CNV-23026270300 EMER - INSTALL 2'-4\" PM | 4000074678 | BET32.0000.00035 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-29 |  | 1900-01-11 | 1900-01-29 | 1905-07-15 | C_U139391
2631 |  | CNV-23026270400 EMER - RETIRE 110'-4\" P | 4000074679 | BET32.0000.00035 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-29 |  | 1900-01-11 | 1900-01-29 | 1905-07-15 | C_U139391
2631 |  | CNV-23026271400 EMER - INSTALL ~5'-2\" P | 4000074680 | ANC32.0000.00224 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2631 |  | CNV-23026271500 EMER - RETIRE ~5'-2\" PM | 4000074681 | ANC32.0000.00224 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2631 |  | CNV-23026277700 RETIRE 2881'-12\" BSMP | 4000074682 | ANC32.0000.00230 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 440.15 | 2023-12-29 | 2023-12-31 | 2025-07-31 | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2621 |  | 2621-TRAFTON SMRP-LEXINGTON | 4000088149 | ANC32.0000.00017 | CRTD MANC NTUP PRC | EST | MAI | 44.58 | 0 | 2025-08-18 | 2025-08-18 |  |  |  |  | U127466
2621 |  | CNV-23026280100 RETIRE 10' OF 10\"CSMP M | 4000074684 | ANC32.0000.00115 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 290.02 | 2023-12-29 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2623 |  | ANC-SMRP HIGH STREET-FRANKFORT | 4000076615 | ANC32.0000.00018 | REL MANC PRC SETC | NEW ADJ NSFS WENG | MAI | 1441844.36 | 7149.16 | 2026-10-13 | 2026-12-31 |  | 12 | 31 | 2026 | C_U139391
2621 |  | CNV-23026287700 RETIRE ~30'-4\" PMP | 4000074686 | BET32.0000.00038 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6450.91 | 2023-12-29 | 2023-12-31 |  | 1900-01-11 | 1900-01-24 | 1905-07-16 | C_U139391
2621 |  | CNV-23026294500 RETIRE 338' OF 4\"BSLP M | 4000074687 | BET32.0000.00015 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6590.43 | 2023-12-29 | 2023-12-31 | 2025-07-31 | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2623 |  | CNV-23026294600 ABANDON ~790'-2\" PMMP | 4000074688 | GRT32.0000.00001 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2629 |  | CNV-23026297000 INSTALL PCF'S LP | 4000074689 | ANC32.0000.00003 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2621 |  | ANC - Rand Ave SMRP - Lexington | 4000077602 | ANC32.0000.00019 | REL PCNF GMPS MANC PRC SETC | NEW WGMA | MAI | 125669.49 | 546413.67 | 2025-07-16 | 2026-12-31 | 2026-03-04 | 12 | 31 | 2026 | C_U139391
2621 |  | CNV-23026304100 RETIRE 667' OF 2\"PMMP M | 4000074691 | PIG32.0000.00017 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4671.25 | 2023-12-29 | 2023-12-31 | 2025-07-31 | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2621 |  | RICHMOND ROAD PHASE 2 2025 SMRP CNV-2202 | 4000077604 | ANC32.0000.00020 | REL PCNF GMPS MANC PRC SETC | COCO ADJ FCMP | MAI | 130238.25 | 1492718.41 | 2025-09-25 | 2025-12-31 | 2025-08-03 | 12 | 31 | 2025 | C_U139391
2629 |  | ANC-SMRP Rio Vista-Paris | 4000078057 | ANC32.0000.00024 | REL PCNF MANC PRC SETC | NEW | MAI | 2471492.73 | 1939.39 | 2026-10-31 | 2027-12-31 | 2026-03-04 |  |  |  | C_U139391
2621 |  | LEX SUNSET DR 2025 SMRP CNV-23026290300 | 4000079351 | ANC32.0000.00049 | REL GMPS MANC PRC SETC | NPRG ADJ WGMA | MAI | 157274.21 | 1825203.45 | 2025-09-02 | 2025-12-31 |  | 4 | 1 | 2026 | C_U139391
2621 |  | BLUE RIDGE 2025 SMRP CNV-23026290600 | 4000079353 | ANC32.0000.00050 | REL GMPS MANC PRC SETC | NPRG ADJ FCMP RSHD | MAI | 163265.34 | 1060907.48 | 2025-07-07 | 2025-12-23 |  | 12 | 23 | 2025 | C_U139391
2623 |  | CNV-24026310000 EMER-INSTALL 4' OF 2\"PM | 4000079662 | ANC32.0000.00051 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4013.16 | 2024-11-26 | 2024-11-30 |  | 7 | 28 | 2025 | C_U139391
2623 |  | CNV-24026313000 INSTALL 1570'-2\\\ PMM. | 4000079671 | ANC32.0000.00052 | REL PCNF MANC NMAT NTUP PRC SETC | NEW | MAI | 0 | 170437.9 | 2025-08-19 | 2025-09-30 | 2025-08-01 | 9 | 30 | 2025 | C_U139391
2621 |  | SMRP JESSELIN DR 2025 CNV 24-0263154-00 | 4000076403 | ANC32.0000.00054 | REL PCNF GMPS MANC PRC SETC | SCHD FCMP REV | MAI | 896582.69 | 6058159.51 | 2025-08-05 | 2025-12-31 | 2026-04-27 | 5 | 1 | 2026 | C_U139391
2629 |  | CNV-25026409900 EMER - INSTALL 10'-2\" P | 4000075744 | SUP32.0002.00001 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 6262 | 2025-05-08 | 2025-05-08 |  | 1900-01-04 | 1900-01-18 | 1905-07-17 | C_U139391
2631 |  | ANC-SMRP Algonquin Ave-Ashland | 4000079320 | ANC32.0000.00056 | REL GMPS MANC PRC SETC | NPRG ADJ FCMP | MAI | 157818.06 | 1550175.42 | 2026-07-10 | 2026-12-31 |  | 12 | 31 | 2026 | C_U139391
2623 |  | ANC - GANO AVE SMRP | 4000079322 | ANC32.0000.00057 | REL PCNF GMPS MANC PRC SETC | NEW ADJ | MAI | 52698.27 | 1729753.98 | 2026-05-14 | 2026-12-31 | 2026-02-13 | 12 | 31 | 2026 | C_U139391
2621 |  | CNV-24026318600 EMER - INSTALL 11' OF 2\ | 4000075749 | ANC32.0000.00254 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 5951.21 | 2024-03-26 | 2024-03-31 | 2025-07-31 | 1900-01-02 | 1900-01-30 | 1905-07-16 | C_U139391
2621 |  | CNV-24026318700 EMER - RETIRE 11' OF 2\" | 4000075751 | ANC32.0000.00254 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 157.3 | 2024-03-28 | 2024-03-31 | 2025-07-31 | 1900-01-02 | 1900-01-30 | 1905-07-16 | C_U139391
2623 |  | SMRP - MOCKINGBIRD | 4000075747 | ANC32.0000.00058 | REL PCNF GMPS MANC PRC SETC | NPRG ADJ MIFE | MAI | 1413114.51 | 1399970.23 | 2025-08-01 | 2025-08-01 | 2026-03-23 | 5 | 1 | 2026 | C_U139391
2623 | FRANKFORT | STA - Station Upgrade | 4000100505 | ANC32.0000.00058 | REL ESTC CSER MANC PRC SETC | NEW ADJ | STA | 41296.74 | 5.21 | 2026-03-31 | 2026-03-31 |  |  |  |  | U132703
2621 |  | CNV-24026342000 EMER - INSTALL 2' OF 2\" | 4000075756 | ANC32.0000.00268 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1762.13 | 2024-05-31 | 2024-05-31 |  | 1900-01-04 | 1900-01-30 | 1905-07-16 | C_U139391
2621 |  | CNV-24026342100 EMER - RETIRE 2' OF 2\"P | 4000075758 | ANC32.0000.00268 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 90.98 | 2024-05-31 | 2024-05-31 | 2025-07-31 | 1900-01-04 | 1900-01-30 | 1905-07-16 | C_U139391
2623 |  | ANC - SMRP - TURNER ST | 4000079323 | ANC32.0000.00059 | REL PCNF GMPS MANC PRC SETC | NEW | MAI | 34754.19 | 2677857.55 | 2026-04-28 | 2026-12-30 | 2026-03-04 | 12 | 30 | 2026 | C_U139391
2629 |  | CNV-24026329400 EMER - INSTALL 2'-3\" PM | 4000079768 | ANC32.0000.00060 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4119.43 | 2024-12-18 | 2024-12-31 |  | 12 | 31 | 2024 | C_U139391
2629 |  | CNV-24026329700 EMER - 2'-2\" PMMP | 4000079771 | ANC32.0000.00061 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4824.51 | 2024-12-17 | 2024-12-31 |  | 12 | 31 | 2024 | C_U139391
2623 |  | CNV-24026331100 EMER - INSTALL ~5'-2\" P | 4000079773 | ANC32.0000.00062 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 847.97 | 2024-12-27 | 2024-12-27 |  | 12 | 29 | 2024 | C_U139391
2629 |  | CNV-24026332600 EMER INSTALL 10'-6\" PMM | 4000079779 | ANC32.0000.00063 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 20910.63 | 2025-03-20 | 2025-03-31 |  | 11 | 20 | 2025 | C_U139391
2629 |  | CNV-24026335100 EMER - INSTALL 4'-3\" PM | 4000082716 | ANC32.0000.00065 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 5732.51 | 2024-11-11 | 2024-11-30 |  |  |  |  | C_U139391
2629 |  | CNV-24026335400 EMER - INSTALL 2'-2\" PM | 4000082717 | ANC32.0000.00066 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4746.17 | 2024-11-21 | 2024-11-30 |  |  |  |  | C_U139391
2621 |  | CNV-24026346700 EMER-RETIRE 8' OF 4\"PML | 4000075794 | ANC32.0000.00270 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 10.01 | 2024-08-30 | 2024-08-30 | 2025-08-01 | 1900-01-08 | 1900-01-27 | 1905-07-16 | C_U139391
2621 |  | CNV-24026348000 EMER-INSTALL 4' OF 3\"PM | 4000075796 | ANC32.0000.00073 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1654.69 | 2024-06-10 | 2024-06-10 | 2025-08-01 | 1900-01-08 | 1900-01-27 | 1905-07-16 | C_U139391
2623 |  | CNV-24026338200 EMER - INSTALL 5'-3\" PM | 4000079819 | ANC32.0000.00068 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 5210.66 | 2025-01-30 | 2025-01-31 |  | 9 | 19 | 2025 | C_U139391
2631 |  | CNV-24026344300 EMER-INSTALL 6' OF 4\" P | 4000079381 | ANC32.0000.00071 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 12417.86 | 2025-07-31 | 2025-07-31 |  | 3 | 13 | 2026 | C_U139391
2629 |  | CNV-24026349900 EMER - INSTALL 3'-2\" PM | 4000079398 | ANC32.0000.00074 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6187.75 | 2024-12-23 | 2024-12-31 |  | 12 | 31 | 2024 | C_U139391
2632 |  | CNV-24026351600 EMER - INSTALL 2'-2\" PM | 4000079420 | ANC32.0000.00075 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 1335.05 | 2025-03-28 | 2025-03-31 |  | 3 | 31 | 2025 | C_U139391
2629 |  | CNV-24026353200 EMER - INSTALL 3'-4\" PM | 4000079758 | ANC32.0000.00076 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 2039.58 | 2025-03-25 | 2025-03-31 |  | 3 | 31 | 2025 | C_U139391
2631 |  | CNV-20026952500 REPLACE VALVE C-16 | 4000075827 | BET32.0000.00028 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-12 | 2023-12-25 |  | 1900-01-11 | 1900-01-24 | 1905-07-15 | C_U139391
2623 |  | CNV-24026357700 EMER-INSTALL 2' OF 3\"PM | 4000079849 | ANC32.0000.00077 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 8659.42 | 2025-10-28 | 2025-10-31 | 2025-08-02 | 6 | 27 | 2026 | C_U139391
2631 |  | CNV-20026952600 RETIRE VALVE C-16 | 4000075829 | BET32.0000.00028 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-21 | 2023-12-25 |  | 1900-01-11 | 1900-01-24 | 1905-07-15 | C_U139391
2621 |  | CNV-24026351800 EMER-INSTALL 8' OF 3\" P | 4000075830 | ANC32.0000.00276 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4560.47 | 2024-08-29 | 2024-08-30 |  | 1900-01-07 | 1900-01-29 | 1905-07-16 | C_U139391
2631 |  | CNV-20026968700 EMER - INSTALL 5' - 2\" | 4000075831 | ANC32.0000.00159 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 241.92 | 2023-12-21 | 2023-12-21 | 2025-07-30 | 1900-01-11 | 1900-01-24 | 1905-07-15 | C_U139391
2621 |  | CNV-24026351900 EMER-RETIRE 8' OF 3\" PM | 4000075832 | ANC32.0000.00276 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6.09 | 2024-08-30 | 2024-08-30 | 2025-08-01 | 1900-01-07 | 1900-01-29 | 1905-07-16 | C_U139391
2621 |  | CNV-24026352600 EMER - INSTALL 2'-2\" PM | 4000075833 | ANC32.0000.00278 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1553.45 | 2024-08-14 | 2024-08-15 | 2025-08-01 | 1900-01-07 | 1900-01-14 | 1905-07-16 | C_U139391
2631 |  | CNV-20026968800 EMER - RETIRE 5'- 2\" PM | 4000075834 | ANC32.0000.00159 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 182.33 | 2023-12-21 | 2023-12-21 | 2025-07-30 | 1900-01-11 | 1900-01-24 | 1905-07-15 | C_U139391
2621 |  | CNV-24026352700 EMER - RETIRE 2'-2\" PMM | 4000075835 | ANC32.0000.00278 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 122.61 | 2024-08-15 | 2024-08-15 | 2025-08-01 | 1900-01-07 | 1900-01-14 | 1905-07-16 | C_U139391
2623 |  | CNV-20026974601 INSTALL 6,500'-4\"PMLP | 4000075836 | ANC32.0000.00160 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 11043.04 | 2023-02-08 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-08-10 | C_U139391
2629 |  | ANC-SMRP Basin Springs-Winchester | 4000079856 | ANC32.0000.00078 | REL PCNF GMPS MANC PRC SETC | SCHD ADJ | MAI | 942649.29 | 510290.27 | 2026-09-21 | 2026-12-01 | 2026-04-20 | 12 | 31 | 2026 | C_U139391
2631 |  | CNV-20026978100 INSTALL 8620'- 2\" PMMP | 4000075860 | ANC32.0000.00161 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 442357.23 | 2023-05-30 | 2023-12-31 | 2025-07-30 | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2629 |  | CNV-24026361500 EMER - INSTALL 2'-3\" PM | 4000079862 | ANC32.0000.00080 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1680.46 | 2024-09-27 | 2024-09-30 |  | 9 | 30 | 2024 | C_U139391
2621 |  | ANC-SMRP GEORGETOWN RD BSHP-LEXINGTON | 4000076975 | ANC32.0000.00081 | REL MANC PRC SETC | NEW ADJ NSFS REV WENV | MAI | 291270.15 | 2.52 | 2025-12-02 | 2025-12-31 |  | 12 | 31 | 2025 | C_U139391
2621 |  | CNV-24026313800 INVESTIGATE LAND RIGHTS | 4000079421 | ANC32.0000.00081 | TECO JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL | PSI | 0 | 54333.24 | 2025-12-30 | 2025-12-31 |  | 12 | 31 | 2025 | C_U139391
2621 |  | CNV-25026404500 EASEMENT PAYMENT 24-0263 | 4000085079 | ANC32.0000.00081 | REL NMAT PRC SETC | NEW NSFS | LND | 0 | 12827.47 | 2025-05-15 | 2025-05-15 |  | 5 | 17 | 2025 | C_U141034
2621 |  | CNV-24026363600 INSTALL 620' OF 4\"PMMP | 4000076481 | ANC32.0000.00082 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 109530.33 | 2024-12-02 | 2024-12-31 | 2025-08-01 | 12 | 31 | 2024 | C_U139391
2633 |  | CNV-24026364700 INSTALL 518'-4\" PMIP | 4000079463 | ANC32.0000.00083 | REL GMPS MANC PRC SETC | COCO ADJ FCMP | MAI | 35276.7 | 30580.52 | 2025-07-30 | 2025-08-08 |  | 8 | 8 | 2025 | C_U139391
2621 |  | ANC-CASSIDY AVE SMRP-LEXINGTON | 4000076487 | ANC32.0000.00084 | REL PCNF MANC PRC SETC | NEW ADJ | MAI | 645287.17 | 1471.17 | 2026-08-07 | 2026-12-31 | 2026-03-04 | 12 | 31 | 2026 | C_U139391
2631 |  | CNV-18026793901 INSTALL 4,123' - 2\" PMM | 4000075875 | ANC32.0000.00156 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 20127.52 | 2023-08-01 | 2023-12-31 | 2025-07-31 | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2629 | CYNTHIANA | CNV-18026795501 INSTALL 14,600'-2,4,6,8. | 4000075877 | ANC32.0000.00158 | REL CSER MANC NMAT PRC SETC | NEW REV | MAI | 0 | 14815.83 | 2022-11-28 | 2024-03-31 |  | 1900-01-10 | 1900-01-07 | 1905-07-16 | C_U139391
2621 |  | CNV-24026369000 INSTALL 65'-8\" PMLP | 4000075865 | ANC32.0000.00085 | REL NMAT PRC SETC | NEW FCMP NSFS WENG | MAI | 0 | 46796.4 | 2025-07-18 | 2025-07-31 |  | 7 | 31 | 2025 | C_U139391
2621 |  | CNV-24026371100 EMER-INSTALL 6' OF 8\"PM | 4000075867 | ANC32.0000.00086 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 3770.63 | 2025-07-01 | 2025-07-01 | 2025-08-03 | 7 | 1 | 2025 | C_U139391
2621 |  | CNV-24026371200 EMER-RETIRE 6' OF 8\"PMP | 4000075869 | ANC32.0000.00086 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 15.06 | 2025-04-28 | 2025-04-28 | 2025-08-03 | 7 | 1 | 2025 | C_U139391
2631 |  | CNV-24026371300 EMER - INSTALL 1'-2\" PM | 4000073977 | ANC32.0000.00087 | REL NMAT PRC SETC | NEW NSFS REV | MAI | 0 | 2816.02 | 2024-12-31 | 2024-12-31 |  | 12 | 31 | 2024 | C_U139391
2621 |  | CNV-24026371600 EMER - INSTALL 5' - 2\" | 4000073978 | ANC32.0000.00088 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2756.63 | 2024-12-31 | 2024-12-31 | 2025-08-03 | 7 | 1 | 2025 | C_U139391
2621 |  | CNV-24026371700 EMER - RETIRE 5' - 2\" P | 4000073979 | ANC32.0000.00088 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 24.65 | 2024-12-31 | 2024-12-31 |  | 7 | 1 | 2025 | C_U139391
2629 |  | CNV-24026371800 EMER - INSTALL 3'-2\" PM | 4000079507 | ANC32.0000.00089 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 15303.77 | 2024-12-12 | 2024-12-31 |  | 12 | 31 | 2024 | C_U139391
2629 |  | CNV-24026373800 EMER - INSTALL 3'-2\" PM | 4000079512 | ANC32.0000.00090 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2998.84 | 2024-12-27 | 2024-12-31 |  | 12 | 31 | 2024 | C_U139391
2621 |  | CNV-24026375200 EMER-INSTALL 6' OF 2\"PM | 4000082671 | ANC32.0000.00091 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 4863.68 | 2025-08-29 | 2025-08-31 |  |  |  |  | C_U139391
2629 |  | CNV-24026376300 EMER - INSTALL 5'-2\" PM | 4000079516 | ANC32.0000.00092 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3004.9 | 2024-12-23 | 2024-12-31 |  | 12 | 31 | 2024 | C_U139391
2621 |  | CNV-25026404400 LAND AND ENVIRONMENTAL | 4000080430 | ANC32.0000.00093 | REL GMPS NMAT PRC SETC | NEW NSFS | PSI | 0 | 150455.15 | 2025-10-01 | 2025-10-01 |  | 10 | 1 | 2025 | C_U139391
2623 |  | CNV-21026115500 INSTALL 9560' OF 2\"PMMP | 4000075984 | ANC32.0000.00166 | REL PCNF GMPS NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 53259.86 | 2022-08-04 | 2023-02-21 | 2025-07-30 | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2621 |  | ANC-JONES CREEK HP-LEXINGTON | 4000082485 | ANC32.0000.00093 | REL MANC NMAT PRC SETC | NEW NSFS | MAI | 0 | 1197.37 | 2026-10-01 | 2027-12-31 |  |  |  |  | C_U139391
2632 |  | CNV-21026127000 INSTALL 8021'-2\"&4\" PM | 4000075988 | ANC32.0000.00168 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 932.48 | 2023-08-29 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2631 |  | CNV-21026130200 EMER-INSTALL 5'-2\" PMIP | 4000075990 | ANC32.0000.00169 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2022-09-29 | 2022-09-30 |  | 1900-01-04 | 1900-01-12 | 1905-07-15 | C_U139391
2631 |  | CNV-21026130300 EMER-RETIRE 5'-2\" BSIP | 4000075992 | ANC32.0000.00169 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2022-09-30 | 2022-09-30 |  | 1900-01-04 | 1900-01-12 | 1905-07-15 | C_U139391
2631 |  | CNV-21026130400 INSTALL 25,111'-2\",4\" | 4000075994 | ANC32.0000.00167 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 194477.23 | 2022-08-04 | 2023-12-31 | 2025-07-30 | 1900-01-11 | 1900-01-07 | 1905-07-16 | C_U139391
2629 |  | CNV-25026378800 EMER - INSTALL 25'-2\\\. | 4000080039 | ANC32.0000.00094 | REL GMPS MANC NMAT NTUP PRC SETC | NEW FCMP REV | MAI | 0 | 21884.96 | 2024-11-13 | 2024-11-13 |  | 1 | 7 | 2025 | C_U139391
2623 |  | CNV-25026397400 EMER-INSTALL 3' OF 2\"PM | 4000080096 | ANC32.0000.00095 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 4664.52 | 2025-07-01 | 2025-07-01 | 2025-08-03 | 7 | 1 | 2025 | C_U139391
2633 |  | CNV-25026398400 EMER - INSTALL FITTINGS. | 4000081864 | ANC32.0000.00096 | REL MANC NMAT NTUP PRC SETC | NEW CAN | MAI | 0 | 4387.89 | 2025-11-25 | 2025-11-30 |  |  |  |  | C_U139391
2621 |  | CNV-25026399300 EMER - INSTALL 5'-2\" PM | 4000082499 | ANC32.0000.00097 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 1473.33 | 2025-11-26 | 2025-11-30 |  |  |  |  | C_U139391
2621 |  | CNV-25026399700 EMER - INSTALL 3'-2\" PM | 4000076564 | ANC32.0000.00098 | REL NMAT PRC SETC | NEW NSFS | MAI | 0 | 0 | 2025-11-26 | 2025-11-30 |  | 11 | 30 | 2025 | C_U139391
2621 |  | CNV-24026328300 EMER - INSTALL 26'-6\" P | 4000076068 | ANC32.0000.00258 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 9947.87 | 2024-02-28 | 2024-03-07 | 2025-07-31 | 1900-01-02 | 1900-01-09 | 1905-07-16 | C_U139391
2621 |  | CNV-24026328400 EMER - RETIRE 26'-6\" BS | 4000076070 | ANC32.0000.00258 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3033.08 | 2024-02-28 | 2024-03-07 | 2025-07-31 | 1900-01-02 | 1900-01-09 | 1905-07-16 | C_U139391
2621 |  | CNV-25026400500 EMER - INSTALL 5'-2\" PM | 4000076567 | ANC32.0000.00099 | REL PRC SETC | NEW NSFS | MAI | 34.35 | 2436.44 | 2025-11-25 | 2025-11-30 |  | 11 | 30 | 2025 | C_U139391
2621 |  | CNV-24026331900 EMER - INSTALL 1' OF 2\" | 4000076072 | ANC32.0000.00261 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2305.11 | 2024-05-01 | 2024-05-01 | 2025-07-31 | 1900-01-04 | 1899-12-31 | 1905-07-16 | C_U139391
2621 |  | CNV-25026400900 EMER - INSTALL 2'-4\" PM | 4000076569 | ANC32.0000.00100 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 4133.67 | 2025-11-25 | 2025-11-30 |  | 11 | 30 | 2025 | C_U139391
2621 |  | CNV-24026332000 EMER - RETIRE 1' OF 2\"P | 4000076074 | ANC32.0000.00261 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 294.9 | 2024-05-01 | 2024-05-01 | 2025-07-31 | 1900-01-04 | 1899-12-31 | 1905-07-16 | C_U139391
2631 |  | CNV-20026983500 INSTALL 1670' - 2\" PMMP | 4000076075 | ANC32.0000.00162 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 81119.08 | 2023-11-08 | 2023-12-31 | 2025-07-30 | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2631 |  | CNV-23026280300 RETIRE 1107'-2\"&8\" CS& | 4000077928 | ANC32.0000.00101 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 665.59 | 2023-06-26 | 2049-12-31 | 2025-07-31 | 12 | 31 | 2049 | C_U139391
2631 |  | CNV-20026991600 INSTALL RECTIFIER- JOHNS | 4000076077 | ANC32.0000.00138 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 716.73 | 2023-12-18 | 2023-12-20 | 2025-07-31 | 1900-01-11 | 1900-01-19 | 1905-07-15 | C_U139391
2623 |  | CNV-24026316600 EMER - ABANDON ~15'-2\" | 4000079296 | ANC32.0000.00110 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6716.07 | 2024-09-30 | 2024-09-30 |  | 5 | 18 | 2025 | C_U139391
2621 |  | CNV-24026333000 EMER-INSTALL 18'-4\"PMLP | 4000076100 | ANC32.0000.00064 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 752.02 | 2024-07-29 | 2024-07-31 |  | 1900-01-02 | 1900-01-09 | 1905-07-17 | C_U139391
2621 |  | CNV-24026334000 INSTALL 5' OF 2\" PMMP | 4000076102 | ANC32.0000.00265 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6723.58 | 2024-03-28 | 2024-03-30 | 2025-07-31 | 1900-01-01 | 1900-01-07 | 1905-07-18 | C_U139391
2621 |  | CNV-24026355100 EMER - RETIRE 12'-2\" PM | 4000076038 | ANC32.0000.00113 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 456.5 | 2024-10-31 | 2024-10-31 | 2025-08-01 | 10 | 31 | 2024 | C_U139391
2621 |  | CNV-24026336800 EMER - INSTALL 5' OF 2\" | 4000076106 | ANC32.0000.00067 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4721.53 | 2024-07-31 | 2024-07-31 |  | 1900-01-07 | 1900-01-30 | 1905-07-16 | C_U139391
2631 |  | CNV-25026381500 EMER - RETIRE ~870'-3\" | 4000080049 | ANC32.0000.00114 | REL PCNF MANC PRC SETC | COCO FCMP NSFS | MAI | 2276.13 | 4189.61 | 2025-01-27 | 2025-01-30 | 2025-08-03 | 12 | 31 | 2049 | C_U139391
2629 |  | ANC-Levee Rd POD Valves-Mt Sterling | 4000080302 | ANC32.0000.00119 | REL NMAT PRC SETC | NEW NSFS | STA | 0 | 2052.03 | 2025-12-30 | 2025-12-31 |  | 12 | 31 | 2025 | C_U139391
2621 | LEXINGTON | CNV-22026211900 INSTALL 1\" BYPASS VALVE | 4000080780 | ANC32.0000.00120 | REL NMAT PRC SETC | NEW NSFS | STA | 0 | 0 | 2025-09-25 | 2025-10-01 |  | 10 | 1 | 2025 | C_U139391
2633 | HONAKER | CNV-23026276000 REPLACE ODORIZER R-1439 | 4000080002 | ANC32.0000.00121 | REL NMAT PRC SETC | NEW NSFS | STA | 0 | 0 | 2025-12-23 | 2025-12-31 |  | 12 | 31 | 2025 | C_U139391
2631 | GREENUP | CNV-23026306800 INSTALL METER RUN | 4000080005 | ANC32.0000.00122 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 6792.46 | 2024-11-26 | 2024-12-01 | 2025-08-01 | 12 | 1 | 2024 | C_U139391
2629 | PARIS | CNV-23026264000 INSTALL NEW METER | 4000076139 | ANC32.0000.00124 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 20617.11 | 2024-12-30 | 2024-12-31 | 2025-07-31 | 12 | 31 | 2024 | C_U139391
2632 | MAYSVILLE | CNV-23026286900 HIGHLAND HEIGHTS BREAK M | 4000076165 | ANC32.0000.00126 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 8521.83 | 2024-12-30 | 2024-12-31 | 2025-08-01 | 12 | 31 | 2024 | C_U139391
2621 |  | CNV-24026357600 RETIRE 490' OF 2\"/4\"PM | 4000076140 | PIG32.0000.00023 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2673.58 | 2024-08-30 | 2024-09-01 | 2025-08-01 | 1900-01-08 | 1899-12-31 | 1905-07-16 | C_U139391
2631 | ASHLAND | CNV-24026309600 INSTALL METER | 4000076923 | ANC32.0000.00127 | REL PCNF MANC PRC SETC | NEW ADJ MIFE NSFS | STA | 178.67 | 14941.24 | 2024-12-09 | 2024-12-31 | 2025-08-02 | 12 | 31 | 2024 | C_U139391
2631 | GREENUP | CNV-23026308100 INSTALL NEW METER | 4000080006 | ANC32.0000.00128 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 1799.98 | 2024-12-23 | 2024-12-31 | 2025-08-01 | 12 | 31 | 2024 | C_U139391
2633 | PIPPA PASSES | CNV-24026312800 INSTALL REGULATOR STATIO | 4000076925 | ANC32.0000.00129 | REL NMAT PRC SETC | NEW NSFS | STA | 0 | 0 | 2025-11-25 | 2025-12-31 |  | 12 | 31 | 2025 | C_U139391
2633 |  | CNV-25026399000 INVESTIGATE SITE | 4000080429 | ANC32.0000.00129 | REL NMAT PRC SETC | NEW NSFS | PSI | 0 | 21304.09 | 2025-08-01 | 2025-08-01 |  | 8 | 1 | 2025 | C_U139391
2631 | CATLETTSBURG | CNV-24026335800 EMER - INSTALL PF REGULA | 4000076961 | ANC32.0000.00132 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 11803.01 | 2024-09-25 | 2024-10-01 |  | 10 | 1 | 2024 | C_U139391
2633 | GREEN MEADOW | CNV-23026302100 RETIRE PAPER GAUGE | 4000080957 | ANC32.0000.00133 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 306.23 | 2024-12-13 | 2024-12-15 |  | 12 | 15 | 2024 | C_U139391
2631 |  | CNV-23026308300 INVESTIGATE EASEMENTS AN | 4000076167 | PSI32.0000.00013 | TECO JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL REV | PSI | 0 | 5120.81 | 2024-12-31 | 2024-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-16 | C_U139391
2633 | HAROLD | CNV-23026302200 RETIRE PAPER GAUGE | 4000080958 | ANC32.0000.00133 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 1191.8 | 2024-12-13 | 2024-12-15 | 2025-07-31 | 12 | 15 | 2024 | C_U139391
2629 | WACO | CNV-23026302300 RETIRE PAPER GAUGE | 4000080959 | ANC32.0000.00133 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 835.24 | 2024-12-13 | 2024-12-15 | 2025-07-31 | 12 | 15 | 2024 | C_U139391
2621 |  | CNV-24026321100 INSTALL 1400' OF 2\" PMM | 4000076407 | GRT32.0000.00099 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 36755.9 | 2024-05-17 | 2024-06-01 | 2025-07-31 | 1900-01-05 | 1899-12-31 | 1905-07-16 | C_U139391
2629 | RICHMOND | ANC-Country Club Heights PG RET-Richmond | 4000082570 | ANC32.0000.00133 | REL PCNF NMAT PRC SETC | NEW NSFS REV | STA | 0 | 1046.86 | 2024-12-13 | 2024-12-15 | 2025-07-31 |  |  |  | C_U139391
2623 |  | CNV-18026845002 INSTALL THREE SSD UNITS | 4000075879 | ANC32.0000.00136 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 8156.02 | 2024-10-31 | 2024-12-01 |  | 12 | 1 | 2024 | C_U139391
2621 |  | CNV-24026342400 INSTALL ~585'-2\" PMMP | 4000076413 | PIG32.0000.00045 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 39880.08 | 2024-07-17 | 2024-07-30 | 2025-08-01 | 1900-01-06 | 1900-01-29 | 1905-07-16 | C_U139391
2621 |  | CNV-24026342500 RETIRE ~600'-2\" PMMP | 4000076414 | PIG32.0000.00045 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 321.09 | 2024-07-30 | 2024-07-30 | 2025-08-01 | 1900-01-06 | 1900-01-29 | 1905-07-16 | C_U139391
2621 |  | CNV-24026343500 INSTALL 25'-8\" PMLP | 4000076418 | PIG32.0000.00046 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 16995.11 | 2024-06-21 | 2024-06-30 | 2025-07-31 | 1900-01-05 | 1900-01-29 | 1905-07-16 | C_U139391
2621 |  | CNV-24026343600 RETIRE 15'-8\" CSLP | 4000076440 | PIG32.0000.00046 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 116.6 | 2024-06-28 | 2024-06-30 |  | 1900-01-05 | 1900-01-29 | 1905-07-16 | C_U139391
2629 |  | CNV-24026365600 INSTALL SSD UNIT W/ZINC | 4000082652 | ANC32.0000.00137 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 59384.05 | 2024-12-18 | 2024-12-31 | 2025-08-01 | 12 | 31 | 2024 | C_U139391
2633 |  | ANC-Caney Circle- Pippa Passes | 4000076565 | ANC32.0000.00140 | TECO MANC PRC SETC | NEW ADJ WENV | MAI | 60386.93 | 6712.5 | 2025-07-02 | 2025-12-31 |  | 12 | 31 | 2025 | C_U139391
2621 |  | FAYETTE PARK 2025 SMRP CNV-24026317600 | 4000075745 | ANC32.0000.00141 | REL PCNF GMPS MANC PRC SETC | NPRG ADJ | MAI | 51053.85 | 232457.82 | 2025-11-04 | 2025-12-31 | 2025-08-03 | 12 | 31 | 2025 | C_U139391
2629 |  | ANC-Wilson Ln Abandonment-Winchester | 4000075784 | ANC32.0000.00143 | REL MANC PRC SETC | NPRG ADJ FCMP MIFE WGMA | MAI | 30868.63 | 1973.6 | 2025-12-30 | 2025-12-31 |  | 12 | 31 | 2025 | C_U139391
2623 |  | CNV-24026367900 INSTALL 1060' OF 2\"PMMP | 4000079502 | ANC32.0000.00144 | REL MANC PRC SETC | NPRG ADJ FCMP | MAI | 101110.57 | 3411.34 | 2025-08-06 | 2025-08-08 |  | 8 | 8 | 2025 | C_U139391
2621 |  | NICHOLASVILLE RD MP SMRP CNV-24026370900 | 4000076499 | ANC32.0000.00145 | REL GMPS MANC PRC SETC | COCO ADJ FCMP | MAI | 340620.69 | 1040845.26 | 2026-11-23 | 2026-12-31 |  | 12 | 31 | 2026 | C_U139391
2629 |  | GRT-Adena Dr MLE-Mt Sterling | 4000079514 | ANC32.0000.00146 | REL GMPS MANC PRC SETC | NPRG ADJ FCMP | MAI | 71358.4 | 80873.14 | 2025-07-28 | 2025-08-09 |  | 8 | 9 | 2025 | C_U139391
2629 |  | ANC-SMRP E Main St-Mt Sterling | 4000080087 | ANC32.0000.00147 | REL PCNF GMPS MANC PRC SETC | SCHD ADJ FCMP | MAI | 42430.62 | 218977.66 | 2025-06-26 | 2025-07-31 | 2025-08-03 | 7 | 31 | 2025 | C_U139391
2623 |  | CNV-25026397000 UPGRADE RECTIFIER W/ RMU | 4000080093 | ANC32.0000.00148 | TECO MANC PRC SETC | NPRG ADJ FCMP MIFE | MAI | 16611.6 | 276.39 | 2025-08-28 | 2025-08-28 |  | 8 | 31 | 2025 | C_U139391
2623 | FRANKFORT | CNV-25026403300 INSTALL MONITOR REGULATO | 4000077308 | ANC32.0000.00149 | TECO NMAT PRC SETC | NEW FCMP NSFS | STA | 0 | 172.4 | 2025-05-29 | 2025-05-29 |  | 6 | 1 | 2025 | C_U139391
2623 | FRANKFORT | CNV-25026403400 RETIRE MONITORING REG | 4000077310 | ANC32.0000.00149 | TECO NMAT PRC SETC | NEW FCMP NSFS | STA | 0 | 0 | 2025-05-30 | 2025-05-30 |  | 6 | 1 | 2025 | C_U139391
2621 |  | CNV-25026405400 EMER - INSTALL 2'-2\" PM | 4000076573 | ANC32.0000.00150 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 2365.36 | 2025-06-30 | 2025-06-30 |  | 7 | 1 | 2025 | C_U139391
2621 |  | CNV-25026405500 EMER - RETIRE 2'-2\" PMP | 4000076575 | ANC32.0000.00150 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 108.37 | 2025-07-01 | 2025-07-01 | 2025-08-03 | 7 | 1 | 2025 | C_U139391
2629 |  | CNV-25026406000 EMER - INSTALL 2'-2\" PM | 4000075687 | ANC32.0000.00151 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 2561.78 | 2025-04-11 | 2025-04-18 |  | 4 | 18 | 2025 | C_U139391
2629 |  | CNV-25026406100 EMER - RETIRE 2'-2\" PML | 4000075689 | ANC32.0000.00151 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 29.09 | 2025-04-17 | 2025-04-18 | 2025-08-03 | 4 | 18 | 2025 | C_U139391
2621 |  | CNV-25026406300 INSTALL 15'-6\" PMLP | 4000076577 | ANC32.0000.00152 | REL MANC PRC SETC | NEW ADJ FCMP MIFE NSFS WENG | MAI | 203.85 | 1732.64 | 2025-05-01 | 2025-05-04 |  | 7 | 31 | 2025 | C_U139391
2621 |  | CNV-25026406400 RETIRE ~15'-6\" BSLP | 4000076688 | ANC32.0000.00152 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS WENG | MAI | 0 | 303.26 | 2025-05-02 | 2025-05-04 | 2025-08-03 | 7 | 31 | 2025 | C_U139391
2621 |  | CNV-25026407500 INSTALL 2'-4\" PMMP | 4000076690 | ANC32.0000.00153 | REL CSER NMAT PRC SETC | SCHD NSFS | MAI | 0 | 15.32 | 2027-04-06 | 2027-04-10 |  | 4 | 10 | 2027 | C_U139391
2623 |  | CNV-22026229200 INSTALL 80'-2\" PMMP | 4000076561 | GRT32.0000.00007 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-03-15 | 2023-03-17 |  | 1900-01-02 | 1900-01-16 | 1905-07-15 | C_U139391
2621 |  | CNV-25026407600 RETIRE 2'-4\" PMP | 4000076692 | ANC32.0000.00153 | REL CSER NMAT PRC SETC | SCHD NSFS | MAI | 0 | 867.16 | 2027-04-09 | 2027-04-10 |  | 4 | 10 | 2027 | C_U139391
2631 |  | CNV-25026404000 SMRP - INSTALL 650'-2\" | 4000076571 | ANC32.0000.00154 | REL GMPS MANC PRC SETC | NPRG ADJ | MAI | 31956.67 | 202446.55 | 2025-08-01 | 2025-08-29 |  | 9 | 19 | 2025 | C_U139391
2631 |  | CNV-18026794000 RETIRE 4748'-2\"/3\"/4\" | 4000074109 | ANC32.0000.00156 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 116.6 | 2024-12-31 | 2024-12-31 |  | 12 | 31 | 2023 | C_U139391
2631 |  | CNV-18026794401 INSTALL 4400'-2\"/4\"PMM | 4000076985 | ANC32.0000.00157 | REL MANC PRC SETC | COCO FCMP NSFS | MAI | 52711.71 | 179108.98 | 2025-06-30 | 2025-12-31 |  | 12 | 31 | 2025 | C_U139391
2631 |  | CNV-18026794500 RETIRE 2450' - CS/BSMP | 4000076987 | ANC32.0000.00157 | REL PCNF MANC PRC SETC | COCO FCMP NSFS | MAI | 312.06 | 570.95 | 2025-12-31 | 2025-12-31 | 2025-08-03 | 12 | 31 | 2025 | C_U139391
2631 |  | CNV-25026392800 RETIRE MP - PAPER ONLY | 4000080059 | ANC32.0000.00157 | REL MANC PRC SETC | COCO FCMP NSFS | MAI | 91.28 | 122.88 | 2026-12-31 | 2026-12-31 |  | 12 | 31 | 2026 | C_U139391
2623 |  | CNV-22026230700 EMER-RETIRE 5' OF 3\"PAM | 4000076568 | ANC32.0000.00102 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-09-29 | 2023-09-30 |  | 1900-01-04 | 1900-01-09 | 1905-07-16 | C_U139391
2629 |  | CNV-22026161900 RETIRE LP MAIN - LEAKAGE | 4000076683 | ANC32.0000.00158 | REL PCNF CSER NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 1465.95 | 2049-12-31 | 2049-12-31 | 2025-08-01 | 12 | 31 | 2024 | C_U139391
2623 |  | CNV-22026231200 INSTALL 1870'-2\"/4\" PM | 4000076570 | GRT32.0000.00001 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 130704.28 | 2023-09-11 | 2023-09-30 | 2025-07-30 | 1900-01-09 | 1900-01-29 | 1905-07-15 | C_U139391
2623 |  | CNV-20026974700 RETIRE 6,900'-BSLP,CSLP, | 4000075838 | ANC32.0000.00160 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 233.2 | 2020-09-18 | 2049-12-31 |  | 12 | 31 | 2049 | C_U139391
2629 |  | CNV-22026234901 INSTALL 4,100'-2\" PMMP | 4000076572 | GRT32.0000.00085 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 23273.07 | 2023-10-23 | 2023-12-01 | 2025-07-31 | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2621 | LEXINGTON | CNV-21026152101 INSTALL 535' OF 8\\\"CS. | 4000077556 | ANC32.0000.00163 | REL MANC NMAT PRC SETC | NPRG | MAI | 788 | 116434.39 | 2025-12-02 | 2025-12-31 |  | 12 | 31 | 2025 | C_U139391
2623 |  | CNV-22026235100 INSTALL 2160'-2\"/4\" PM | 4000076574 | GRT32.0000.00084 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 102021.49 | 2023-06-09 | 2024-02-29 | 2025-07-31 | 1900-01-01 | 1900-01-28 | 1905-07-16 | C_U139391
2621 |  | CNV-21026152200 RETIRE 457' OF 6 5/8\"BS | 4000077559 | ANC32.0000.00163 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 1873.19 | 2025-12-31 | 2025-12-31 | 2025-08-01 | 12 | 31 | 2025 | C_U139391
2623 |  | ANC - Highland Parkway - Frankfort WR27 | 4000075870 | ANC32.0000.00165 | REL MANC PRC SETC | NEW ADJ NSFS WENG WENV WGMA WLND WPMT* | MAI | 235494.3 | 37820.61 | 2026-10-31 | 2027-12-31 |  |  |  |  | C_U139391
2623 |  | CNV-18026776800 RETIRE 3,439' - 8\" BS,C | 4000075872 | ANC32.0000.00165 | REL NMAT PRC SETC | NEW NSFS | MAI | 0 | 0 | 2025-11-21 | 2025-12-31 |  | 12 | 31 | 2026 | C_U139391
2629 |  | CNV-22026236400 INSTALL 450'-4\" PMMP | 4000076579 | GRT32.0000.00009 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2693.93 | 2023-06-21 | 2023-07-15 | 2025-07-30 | 1900-01-06 | 1900-01-14 | 1905-07-15 | C_U139391
2623 |  | CNV-23026267900 PS&I HIGHLAND PARKWAY | 4000076161 | ANC32.0000.00165 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 22236.34 | 2024-12-30 | 2024-12-31 |  | 12 | 31 | 2024 | C_U139391
2623 |  | CNV-21026115600 RETIRE 9,590' OF BSLP & | 4000075986 | ANC32.0000.00166 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 182.4 | 2021-04-13 | 2049-12-31 |  | 12 | 31 | 2049 | C_U139391
2631 |  | CNV-23026305600 RETIRE RECTIFIER | 4000074692 | ANC32.0000.00167 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1383.22 | 2024-12-31 | 2024-12-31 | 2025-07-31 | 12 | 31 | 2024 | C_U139391
2629 |  | CNV-22026237500 RETIRE MP MAIN | 4000076607 | ANC32.0000.00195 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 561.2 | 2024-01-31 | 2024-01-31 | 2025-07-31 | 1900-01-11 | 1900-01-30 | 1905-07-16 | C_U139391
2631 |  | CNV-23026305700 RETIRE RECTIFIER | 4000074693 | ANC32.0000.00167 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2180.6 | 2024-12-31 | 2024-12-31 | 2025-07-31 | 12 | 31 | 2024 | C_U139391
2623 |  | CNV-22026238301 INSTALL 2505'-4\" PHHP | 4000076611 | GRT32.0000.00081 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 8013.44 | 2023-09-11 | 2023-12-30 | 2025-07-31 | 1899-12-31 | 1900-01-30 | 1905-07-16 | C_U139391
2629 |  | ANC-SMRP Burns Ave Retirement-Winchester | 4000076659 | ANC32.0000.00170 | REL PCNF NMAT PRC SETC | NEW | MAI | 0 | 626.39 | 2025-11-26 | 2025-11-30 | 2025-11-06 | 12 | 31 | 2025 | C_U139391
2629 |  |  | 4000077037 | ANC32.0000.00170 | REL PCNF GMPS MANC PRC SETC | NEW ADJ | MAI | 137535.3 | 1585256.47 | 2025-12-31 | 2025-12-31 | 2026-03-04 | 12 | 31 | 2025 | C_U139391
2623 |  | CNV-22026241001 INSTALL 6375'-2\"/4\" PM | 4000076617 | GRT32.0000.00011 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 5088.06 | 2023-08-30 | 2023-12-31 | 2025-07-31 | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2623 |  | CNV-22026241701 INSTALL 1425' OF 2\"PMMP | 4000076619 | PIG32.0000.00033 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 36869.35 | 2024-01-15 | 2024-06-01 | 2025-07-31 | 1900-01-05 | 1899-12-31 | 1905-07-16 | C_U139391
2623 |  | CNV-22026241800 RETIRE 1175' OF 3\"/4\"B | 4000076641 | PIG32.0000.00033 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2024-05-31 | 2024-06-01 |  | 1900-01-05 | 1899-12-31 | 1905-07-16 | C_U139391
2633 |  | CNV-22026241900 INSTALL 249'-2\" PMIP | 4000076642 | PIG32.0000.00034 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-05-17 | 2023-05-31 |  | 1900-01-04 | 1900-01-30 | 1905-07-15 | C_U139391
2633 |  | CNV-22026242000 RETIRE 135'-3\" BSIP | 4000076644 | PIG32.0000.00034 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-05-31 | 2023-05-31 |  | 1900-01-04 | 1900-01-30 | 1905-07-15 | C_U139391
2629 |  | CNV-22026245300 EMER - INSTALL 5'-2\" PM | 4000076646 | ANC32.0000.00021 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-01-16 | 2023-01-16 |  | 1900-01-05 | 1899-12-31 | 1905-07-15 | C_U139391
2629 |  | ANC-SMRP Burns Av LP Install-Winchester | 4000077608 | ANC32.0000.00170 | REL GMPS MANC PRC SETC | NPRG ADJ MIFE | MAI | 3768.12 | 3427397.34 | 2025-05-05 | 2025-12-31 |  | 12 | 31 | 2026 | C_U139391
2629 |  | CNV-22026161800 INSTALL 8\" PCF | 4000076681 | ANC32.0000.00158 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1391.52 | 2024-01-08 | 2024-01-08 | 2025-08-01 | 1900-01-11 | 1900-01-30 | 1905-07-16 | C_U139391
2629 |  | S BURNS RS RETIREMENT, PREMISE 200449 | 4000091436 | ANC32.0000.00170 | CRTD MANC NTUP PRC | EST NSFS | STA | 185.09 | 0 | 2025-10-03 | 2025-10-03 |  |  |  |  | U137440
2621 |  | CNV-21026145700 RETIRE 1840' OF 4\" BSMP | 4000077554 | ANC32.0000.00171 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 116.6 | 2024-09-30 | 2024-09-30 |  | 12 | 31 | 2024 | C_U139391
2629 |  | CNV-22026164201 INSTALL 2,300'-2\\\ PM. | 4000076687 | ANC32.0000.00175 | REL PCNF MANC NMAT PRC SETC | NEW REV | MAI | 0 | 20887.85 | 2023-10-03 | 2023-12-31 | 2025-07-30 | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2629 |  | CNV-22026164000 INSTALL 5,100'-2\" PMMP | 4000076685 | ANC32.0000.00174 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 570375.53 | 2024-08-08 | 2024-12-31 | 2025-07-30 | 12 | 31 | 2024 | C_U139391
2629 |  | CNV-24026331400 RETIRE R-1279 | 4000081418 | ANC32.0000.00174 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 1587.82 | 2024-12-31 | 2024-12-31 | 2025-07-31 | 12 | 31 | 2024 | C_U139391
2621 |  | CNV-22026165600 RETIRE 2715'-BSLP & 425' | 4000074357 | ANC32.0000.00176 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | -329.95 | 2024-12-31 | 2024-12-31 | 2025-08-01 | 12 | 31 | 2024 | C_U139391
2621 |  | CNV-22026165501 INSTALL 3385' OF 2\" PMM | 4000078066 | ANC32.0000.00176 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2024-01-22 | 2024-12-31 |  | 12 | 31 | 2024 | C_U139391
2621 |  | CNV-22026181300 RETIRE PIT REG STATION 1 | 4000079113 | ANC32.0000.00178 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 3197.48 | 2024-10-01 | 2024-10-01 | 2025-07-31 | 10 | 1 | 2024 | C_U139391
2623 |  | CNV-22026225400 INSTALL APROX 180'-6\" P | 4000076805 | ANC32.0000.00188 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 93563.17 | 2023-09-18 | 2023-09-29 | 2025-07-30 | 1900-01-08 | 1900-01-29 | 1905-07-15 | C_U139391
2623 |  | CNV-22026225500 RETIRE 200' - 6\" BSLP | 4000076807 | ANC32.0000.00188 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 510.72 | 2023-03-31 | 2023-03-31 |  | 1900-01-08 | 1900-01-29 | 1905-07-15 | C_U139391
2629 |  | CNV-22026228201 INSTALL 4,225'-2\"/6\" P | 4000076809 | ANC32.0000.00189 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2706.98 | 2023-06-07 | 2024-01-31 |  | 1900-01-08 | 1900-01-19 | 1905-07-16 | C_U139391
2629 |  | CNV-22026228300 RETIRE 6,106'- LP MAIN | 4000076811 | ANC32.0000.00189 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2024-01-31 | 2024-01-31 |  | 1900-01-08 | 1900-01-19 | 1905-07-16 | C_U139391
2623 |  | CNV-22026168600 INSTALL 13,800'-2\"PMMP | 4000076813 | ANC32.0000.00012 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 105908.53 | 2023-03-31 | 2023-12-31 | 2025-07-30 | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2623 |  | CNV-22026169200 EMER-INSTALL 4' OF 2\"PM | 4000076815 | ANC32.0000.00013 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-09-01 | 2023-09-01 |  | 1900-01-11 | 1900-01-30 | 1905-07-16 | C_U139391
2629 |  | CNV-22026170600 INSTALL 7,200'-2\"/4\" P | 4000076817 | ANC32.0000.00003 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 153514.73 | 2023-04-06 | 2023-12-31 | 2025-07-30 | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2632 |  | ANC-Fernleaf Dr-Maysville | 4000076861 | ANC32.0000.00179 | REL PCNF GMPS MANC PRC SETC | NEW ADJ NSFS | MAI | 801667.68 | 1185363.99 | 2025-10-02 | 2026-10-30 | 2026-03-12 | 12 | 31 | 2026 | C_U139391
2623 |  | SMRP - MAIN ST (JIM BEAM) | 4000076831 | PSI32.0000.00025 | TECO JBFI NMAT PRC SETC | NEW CAN NSFS RECL | PSI | 0 | 74921.25 | 2026-12-31 | 2026-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-18 | C_U139391
2623 |  | CNV-24026343100 PS&I HOLMES STREET RELO | 4000076833 | PSI32.0000.00037 | REL PCNF MANC NMAT PRC SETC | NEW | PSI | 46.68 | 2935.54 | 2026-12-31 | 2026-12-31 | 2026-03-04 | 1900-01-11 | 1900-01-30 | 1905-07-18 | C_U139391
2621 |  | CNV-24026311700 INSTALL 360' OF 2\"PMMP | 4000076851 | GRT32.0000.00049 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 23934.84 | 2024-04-09 | 2024-04-12 | 2025-07-31 | 1900-01-03 | 1900-01-11 | 1905-07-16 | C_U139391
2621 |  | CNV-24026314600 EMER-INSTALL 170' OF 2\" | 4000076854 | ANC32.0000.00053 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 52732.18 | 2024-02-05 | 2024-02-14 | 2025-07-31 | 1900-01-01 | 1900-01-16 | 1905-07-16 | C_U139391
2632 |  | DO NOT EXECUTE | 4100555746 | ANC32.0000.00179 | REL MACM PRC SETC | NEW CAN | LND | 2.52 | 0 | 2025-12-30 | 2025-12-31 |  | 12 | 31 | 2025 | C_U139391
2632 |  | CNV-22026171800 INSTALL 3178'-2\" PMIP | 4000076864 | ANC32.0000.00015 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 19573.98 | 2023-11-02 | 2023-12-31 | 2025-07-30 | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2632 |  | CNV-23026283900 ACQUIRE EASEMENTS | 4000084016 | ANC32.0000.00179 | REL NMAT PRC SETC | NEW NSFS | LND | 0 | 40497 | 2025-12-30 | 2025-12-31 |  | 12 | 31 | 2025 | C_U141034
2633 |  | CNV-22026175100 INSTALL 3\" OUTLET VALVE | 4000076867 | BET32.0000.00029 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6469.02 | 2023-07-26 | 2023-08-01 |  | 1900-01-07 | 1899-12-31 | 1905-07-15 | C_U139391
2633 |  | CNV-22026175200 RETIRE ~10' - 3\" CSHP | 4000076869 | BET32.0000.00029 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-08-01 | 2023-08-01 |  | 1900-01-07 | 1899-12-31 | 1905-07-15 | C_U139391
2629 |  | CNV-22026182101 INSTALL 8,450' - 2\"/4\" | 4000076871 | GRT32.0000.00080 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 59520.36 | 2023-05-30 | 2023-12-01 | 2025-07-30 | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2632 |  | CNV-22026171600 INSTALL 4371'-2\"&4\" PM | 4000077663 | ANC32.0000.00180 | REL GMPS MANC PRC SETC | NPRG ADJ | MAI | 192726.47 | 399600.77 | 2025-07-18 | 2025-12-31 |  | 12 | 31 | 2025 | C_U139391
2623 |  | CNV-22026205401 INSTALL 1330'-4\" PMMP | 4000076875 | GRT32.0000.00005 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 24550.76 | 2024-03-08 | 2024-04-05 | 2025-07-31 | 1900-01-03 | 1900-01-04 | 1905-07-16 | C_U139391
2631 |  | CNV-22026172301 INSTALL 5000' OF 2\"PMMP | 4000076866 | ANC32.0000.00181 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 8107.65 | 2023-06-30 | 2024-12-31 | 2025-07-31 | 12 | 31 | 2024 | C_U139391
2631 |  | CNV-22026207200 RETIRE 6009'-2\",3\", 4\ | 4000074377 | ANC32.0000.00184 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 872.75 | 2024-12-31 | 2024-12-31 | 2025-08-01 | 8 | 15 | 2025 | C_U139391
2631 |  | CNV-23026283600 INSTALL LP FITTINGS | 4000074685 | ANC32.0000.00184 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4179.66 | 2024-12-31 | 2024-12-31 | 2025-07-31 | 12 | 31 | 2024 | C_U139391
2623 |  | CNV-22026210901 INSTALL 8OO' OF 2\\\PM. | 4000076902 | GRT32.0000.00082 | REL PCNF MANC NMAT PRC SETC | NEW REV | MAI | 0 | 31681.55 | 2024-02-26 | 2024-02-26 | 2025-07-31 | 1900-01-02 | 1900-01-07 | 1905-07-16 | C_U139391
2631 |  | CNV-22026207100 INSTALL 7870'-2\\\, 4\. | 4000076878 | ANC32.0000.00184 | REL PCNF GMPS MANC NMAT PRC SETC | NEW REV | MAI | 0 | 560952.85 | 2024-01-02 | 2024-12-31 | 2025-07-31 | 8 | 15 | 2025 | C_U139391
2629 |  | BET-Winchester Plaza-Winchester | 4000076900 | ANC32.0000.00185 | REL MANC NMAT PRC SETC | NEW NSFS | MAI | 0 | 0 | 2026-12-30 | 2030-12-31 |  | 12 | 31 | 2030 | C_U139391
2629 |  | PSI-Winchester Plaza ROW-Winchester | 4000079115 | ANC32.0000.00185 | REL MANC NMAT PRC SETC | NEW NSFS | PSI | 0 | 0 | 2026-12-30 | 2028-12-31 |  | 12 | 31 | 2028 | C_U139391
2621 |  | CNV-22026224300 RETIRE 4500' OF 6\"/4\"B | 4000074373 | ANC32.0000.00187 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2313.44 | 2024-12-31 | 2024-12-31 |  | 12 | 31 | 2024 | C_U139391
2621 |  | CNV-22026224201 INSTALL 2300' OF 2\"/4\" | 4000078299 | ANC32.0000.00187 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6065.09 | 2024-09-05 | 2024-12-31 | 2025-08-01 | 12 | 31 | 2024 | C_U139391
2621 |  | CNV-23026270100 RETIRE REG STATION# 1020 | 4000082569 | ANC32.0000.00187 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 1846.92 | 2024-12-13 | 2024-12-15 | 2025-07-31 |  |  |  | C_U139391
2629 |  | CNV-22026230301 INSTALL 1,725'-2\" PMMP | 4000076563 | ANC32.0000.00190 | REL CSER NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 3483.73 | 2049-10-24 | 2049-10-24 |  | 12 | 31 | 2049 | C_U139391
2629 |  | CNV-22026230400 RETIRE 5,578' - IP MAIN | 4000076566 | ANC32.0000.00190 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2022-10-10 | 2049-12-31 |  | 12 | 31 | 2049 | C_U139391
2621 |  | CNV-22026231400 RETIRE 975' OF 8\"BSLP M | 4000074333 | ANC32.0000.00191 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 116.6 | 2024-12-31 | 2024-12-31 |  | 12 | 31 | 2024 | C_U139391
2621 |  | CNV-22026231301 INSTALL 925' OF 2\"PMMP | 4000077981 | ANC32.0000.00191 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2024-11-11 | 2024-12-31 |  | 12 | 31 | 2024 | C_U139391
2621 |  | CNV-24026337000 INSTALL 675' OF 2\"PMMP | 4000076936 | GRT32.0000.00053 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 27451.39 | 2024-04-17 | 2024-04-30 | 2025-07-31 | 1900-01-05 | 1900-01-29 | 1905-07-16 | C_U139391
2621 |  | CNV-24026338000 INSTALL 65'-2\"&4\" PMMP | 4000076938 | PIG32.0000.00010 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 21820.66 | 2024-05-07 | 2024-05-17 | 2025-07-31 | 1900-01-04 | 1900-01-29 | 1905-07-16 | C_U139391
2621 |  | CNV-24026333900 INVESTIGATE ROAD R/W LIM | 4000076939 | PSI32.0000.00019 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 8026.24 | 2024-11-26 | 2024-12-01 |  | 1900-01-11 | 1899-12-31 | 1905-07-16 | C_U139391
2621 |  | CNV-24026338100 RETIRE 42'-2\"&4\" CSMP | 4000076960 | PIG32.0000.00010 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2024-05-17 | 2024-05-17 |  | 1900-01-04 | 1900-01-16 | 1905-07-16 | C_U139391
2623 |  | CNV-22026235400 RETIRE 2111'- 2\",4\",6\ | 4000074334 | ANC32.0000.00192 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 233.2 | 2024-12-31 | 2024-12-31 |  | 12 | 31 | 2024 | C_U139391
2621 |  | CNV-24026338500 INSTALL 585' OF 2\"PMMP | 4000076962 | GRT32.0000.00054 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 20415.57 | 2024-06-24 | 2024-06-28 | 2025-07-31 | 1900-01-05 | 1900-01-27 | 1905-07-16 | C_U139391
2623 |  | CNV-22026235300 INST 1865'-8\" & 390'-2\ | 4000076576 | ANC32.0000.00192 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 400226.28 | 2024-10-17 | 2024-12-31 | 2025-07-31 | 12 | 31 | 2024 | C_U139391
2623 |  | CNV-22026236901 INSTALL 11300'-2\" PMMP | 4000076601 | ANC32.0000.00193 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 80401.8 | 2024-01-15 | 2024-12-31 | 2025-08-01 | 12 | 31 | 2024 | C_U139391
2621 |  | SMRP LAFAYETTE HS | 4000077991 | ANC32.0000.00194 | REL PCNF GMPS MANC PRC SETC | COCO ADJ FCMP | MAI | 3481319.88 | 1322123.24 | 2025-08-05 | 2025-12-31 | 2025-08-01 | 12 | 31 | 2025 | C_U139391
2629 | WINCHESTER | CNV-22026237301 INSTALL 11,150'-8\\\"6\. | 4000076603 | ANC32.0000.00195 | REL CSER MANC NMAT PRC SETC | NEW REV | MAI | 0 | 143037.72 | 2024-12-18 | 2026-02-28 |  | 10 | 21 | 2026 | C_U139391
2629 |  | CNV-22026237400 RETIRE LP MAIN.. | 4000076605 | ANC32.0000.00195 | REL MANC NMAT PRC SETC | NEW | MAI | 0 | 252.59 | 2025-12-31 | 2025-12-31 |  | 8 | 8 | 2026 | C_U139391
2629 | WINCHESTER | ANC-Mutual Ave Reg ABN-Winchester | 4000081704 | ANC32.0000.00195 | REL PCNF MANC NMAT PRC SETC | NEW | STA | 2240.64 | 2460.9 | 2025-12-31 | 2025-12-31 | 2025-08-01 | 12 | 31 | 2025 | C_U139391
2631 |  | CNV-24026357900 INVESTIGATE LAND RIGHTS | 4000076969 | PSI32.0000.00028 | TECO JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL REV | PSI | 0 | 4975.16 | 2024-11-27 | 2024-12-01 |  | 1900-01-11 | 1899-12-31 | 1905-07-16 | C_U139391
2629 |  | CNV-22026237900 RETIRE 5,265' IP MAIN | 4000074335 | ANC32.0000.00196 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2024-12-31 | 2024-12-31 |  | 12 | 31 | 2024 | C_U139391
2629 |  | CNV-22026237801 INSTALL 4,100'-2\" PMMP | 4000076609 | ANC32.0000.00196 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 7412.99 | 2024-08-09 | 2024-12-31 | 2025-07-31 | 12 | 31 | 2024 | C_U139391
2629 | CYNTHIANA | CNV-22026238100 RETIRE R-1230-A | 4000081705 | ANC32.0000.00196 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 3401.79 | 2024-12-31 | 2024-12-31 | 2025-07-31 | 12 | 31 | 2024 | C_U139391
2623 |  | CNV-23026276700 RETIRE STATION R-1581 | 4000076163 | ANC32.0000.00197 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 1721.37 | 2024-12-31 | 2024-12-31 | 2025-08-01 | 12 | 31 | 2024 | C_U139391
2623 |  | CNV-22026238401 INSTALL 5765'-2\" PMMP | 4000076613 | ANC32.0000.00197 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 709396.34 | 2023-11-28 | 2049-12-31 | 2025-07-31 | 12 | 31 | 2049 | C_U139391
2621 |  | MONTCLAIR/COOPER 2025 SMRP CNV-220262388 | 4000077996 | ANC32.0000.00198 | REL PCNF GMPS MANC PRC SETC | COCO ADJ FCMP | MAI | 197771.79 | 1074876.42 | 2025-08-01 | 2025-12-01 | 2025-08-01 | 12 | 31 | 2025 | C_U139391
2621 |  | CNV-22026239702 INSTALL 8650' - 2,4,6\" | 4000077998 | ANC32.0000.00199 | REL PCNF MANC PRC SETC | COCO FCMP NSFS REV WENG | MAI | 161307.39 | 159842.86 | 2024-06-20 | 2025-02-28 | 2025-08-01 | 2 | 28 | 2025 | C_U139391
2621 |  | SMRP-Castlewood Dr-Lexington.. | 4000088170 | ANC32.0000.00199 | REL ESTC MACM PRC SETC SKKP | NEW | MAI | 336560.8 | 0 | 2025-08-18 | 2025-12-31 |  |  |  |  | U128885
2631 |  | RIVERSIDE 2025 SMPR -CNV-23026293500 | 4000078048 | ANC32.0000.00200 | REL PCNF GMPS MANC PRC SETC | COCO ADJ FCMP | MAI | 149415.74 | 397969.27 | 2025-07-29 | 2025-10-01 | 2025-07-31 | 10 | 1 | 2025 | C_U139391
2629 |  | ANC-SMRP Harrsion Ave-Mt Sterling | 4000078081 | ANC32.0000.00202 | REL PCNF GMPS MANC PRC SETC | NPRG | MAI | 3808532.52 | 846811.19 | 2026-01-01 | 2026-12-31 | 2026-03-12 | 12 | 31 | 2026 | C_U139391
2629 |  | DO NOT EXECUTE | 4100509673 | ANC32.0000.00202 | REL CSER MACM PRC SETC | NEW CAN | LND | 1 | 0 | 2024-12-31 | 2024-12-31 |  | 12 | 31 | 2024 | C_U139391
2621 |  | CNV-25026398000 INSTALL 1100'-8\" PMLP | 4000077166 | ANC32.0002.00002 | REL PCNF GMPS MANC PRC SETC | COCO ADJ FCMP | MAI | 241177.63 | 96648.21 | 2025-08-01 | 2025-08-08 | 2025-08-03 | 1900-01-07 | 1900-01-07 | 1905-07-17 | C_U139391
2629 |  | ANC-SMRP Harrison Ave Land-Mt Sterling | 4000084798 | ANC32.0000.00202 | REL NMAT PRC SETC | NEW NSFS REV | LND | 0 | 475 | 2024-12-31 | 2024-12-31 |  | 12 | 31 | 2024 | C_U141034
2621 |  | CNV-23026309300 EMER - INSTALL 5'-4\" PM | 4000078528 | ANC32.0000.00209 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 761.85 | 2024-10-30 | 2024-10-31 | 2025-07-31 | 6 | 24 | 2025 | C_U139391
2621 |  | CNV-23026309400 EMER - RETIRE 5'-4\" PMP | 4000078530 | ANC32.0000.00209 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 198.08 | 2024-10-31 | 2024-10-31 | 2025-07-31 | 6 | 24 | 2025 | C_U139391
2631 |  | CNV-23026258600 EMER - INSTALL 5'-4\" PM | 4000077789 | ANC32.0000.00213 | REL CSER NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 23.1 | 2049-12-31 | 2049-12-31 |  | 12 | 31 | 2049 | C_U139391
2631 |  | CNV-23026258700 EMER- RETIRE 5'-4\" PMIP | 4000077791 | ANC32.0000.00213 | REL CSER NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 13716.55 | 2049-12-31 | 2049-12-31 |  | 12 | 31 | 2049 | C_U139391
2623 |  | CNV-25026393900 INVESTIGATE HP CONFLICTS | 4000077302 | PSI32.0000.00029 | REL NMAT PRC SETC | NEW NSFS | PSI | 0 | 4705.03 | 2025-07-01 | 2025-07-01 |  | 1900-01-06 | 1899-12-31 | 1905-07-17 | C_U139391
2621 |  | CNV-25026395100 INVESTIGATE AND MAP MAIN | 4000077304 | PSI32.0000.00040 | TECO JBFI MANC NMAT PRC SETC | NEW CAN FCMP NSFS RECL | PSI | 0.76 | 6658.73 | 2025-06-30 | 2025-06-30 |  | 1900-01-05 | 1900-01-29 | 1905-07-17 | C_U139391
2621 |  | CNV-25026403200 MAINS & SERVICES LOCATE/ | 4000077306 | PSI32.0000.00042 | TECO GMPS JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL | PSI | 0 | 9674.22 | 2025-06-30 | 2025-06-30 |  | 1900-01-06 | 1899-12-31 | 1905-07-17 | C_U139391
2631 |  | CNV-23026262200 EMER - INSTALL 4'-2\" PM | 4000077793 | ANC32.0000.00215 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-03-03 | 2049-12-31 |  | 12 | 31 | 2049 | C_U139391
2631 |  | CNV-23026262300 EMER - RETIRE 4'-2\" PMM | 4000077795 | ANC32.0000.00215 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-03-03 | 2049-12-31 |  | 12 | 31 | 2049 | C_U139391
2621 |  | CNV-21026145601 INSTALL 1885' - 4\" PMMP | 4000077552 | ANC32.0000.00171 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 13402.78 | 2023-07-05 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-16 | C_U139391
2621 |  | CNV-23026263500 RETIRE 20'-4\" PMMP | 4000079268 | ANC32.0000.00217 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-02-24 | 2049-12-31 |  | 12 | 31 | 2049 | C_U139391
2621 |  | CNV-23026273800 RETIRE 2\" POLY VALVE C9 | 4000078343 | ANC32.0000.00226 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3542.89 | 2024-09-30 | 2024-09-30 | 2025-07-31 | 5 | 3 | 2025 | C_U139391
2629 |  | CNV-23026275000 EMER - RETIRE 4'-2\" PMM | 4000077881 | ANC32.0000.00227 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-05-16 | 2049-12-31 |  | 12 | 31 | 2049 | C_U139391
2621 |  | CNV-21026997801 INSTALL 4600' OF 2\"/6\" | 4000077581 | ANC32.0000.00164 | REL PCNF MANC PRC SETC | NEW ADJ FCMP NSFS | MAI | 29313.8 | 104311.15 | 2023-01-30 | 2023-12-31 | 2025-07-30 | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2631 |  | CNV-23026277800 RETIRE RECTIFIER | 4000074683 | ANC32.0000.00230 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2472.49 | 2024-12-31 | 2024-12-31 | 2025-07-31 | 12 | 31 | 2024 | C_U139391
2629 |  | CNV-23026281600 EMER-INSTALL 3'-3\" PMMP | 4000077934 | ANC32.0000.00234 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | -333.3 | 2024-09-25 | 2024-09-30 |  | 5 | 27 | 2025 | C_U139391
2629 |  | CNV-23026281700 EMER-RETIRE 3'-3\" PMAP | 4000077936 | ANC32.0000.00234 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2024-09-30 | 2024-09-30 |  | 5 | 27 | 2025 | C_U139391
2621 |  | CNV-22026166900 INSTALL 2010' - 8\" & 6\ | 4000077661 | ANC32.0000.00177 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 269020.5 | 2024-04-23 | 2024-05-31 | 2025-07-30 | 1899-12-31 | 1900-01-07 | 1905-07-17 | C_U139391
2621 |  | CNV-23026283400 EMER - INSTALL 5'-3\" PM | 4000078385 | ANC32.0000.00235 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3224.58 | 2024-09-30 | 2024-09-30 | 2025-07-30 | 5 | 3 | 2025 | C_U139391
2621 |  | CNV-23026283500 EMER - RETIRE 5'-3\" PMP | 4000078387 | ANC32.0000.00235 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 20.18 | 2024-09-30 | 2024-09-30 | 2025-07-30 | 5 | 3 | 2025 | C_U139391
2631 |  | CNV-23026246800 INSTALL 800'-4\" PMMP | 4000077744 | PIG32.0000.00036 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-03-17 | 2023-03-17 |  | 1900-01-03 | 1900-01-27 | 1905-07-15 | C_U139391
2629 |  | CNV-23026286000 EMER - INSTALL 6'-2\" PM | 4000077978 | ANC32.0000.00239 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4064.86 | 2024-10-21 | 2024-10-31 |  | 6 | 15 | 2025 | C_U139391
2631 |  | CNV-23026248600 RETIRE 3'-3\" PMLP | 4000077748 | ANC32.0000.00104 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-01-10 | 2023-01-10 |  | 1900-01-11 | 1900-01-30 | 1905-08-10 | C_U139391
2629 |  | CNV-23026248700 INSTALL 2\" SS | 4000077750 | BET32.0000.00033 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-28 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2631 |  | CNV-23026249100 INSTALL 100'-2\" PMMP | 4000077752 | GRT32.0000.00028 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 136.4 | 2023-01-26 | 2023-03-27 |  | 1900-01-02 | 1900-01-26 | 1905-07-15 | C_U139391
2623 |  | CNV-23026249500 INSTALL 870'-2\" PMMP | 4000077754 | GRT32.0000.00012 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-04-04 | 2023-04-15 |  | 1900-01-03 | 1900-01-14 | 1905-07-15 | C_U139391
2623 |  | CNV-23026249600 PM- DE ILI PH 2 JIM BEA. | 4000077756 | BET32.0000.00032 | REL MANC NMAT PRC SETC | NEW REV | MAI | 0 | -432898.53 | 2023-12-28 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2623 |  | CNV-23026249700 PM- DE ILI PH 2 JIM BEAM | 4000077758 | BET32.0000.00032 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-28 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2623 |  | CNV-23026251500 INSTALL 70'-2\" PMLP | 4000077780 | GRT32.0000.00029 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-05-03 | 2023-05-08 |  | 1900-01-04 | 1900-01-07 | 1905-07-15 | C_U139391
2623 |  | CNV-23026254300 TAP W/MAIN 23-0262543-00 | 4000077782 | GRT32.0000.00030 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-03-22 | 2023-03-24 |  | 1900-01-02 | 1900-01-23 | 1905-07-15 | C_U139391
2623 |  | CNV-23026256000 INSTALL 800'OF 2\"PMMP M | 4000077783 | ANC32.0000.00188 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 49280.99 | 2023-10-11 | 2023-10-31 | 2025-07-30 | 1900-01-09 | 1900-01-30 | 1905-07-15 | C_U139391
2633 |  | CNV-23026256300 INSTALL 130'-2\" PMIP | 4000077785 | GRT32.0000.00032 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 12275.65 | 2023-07-26 | 2023-07-31 | 2025-07-30 | 1900-01-06 | 1900-01-30 | 1905-07-15 | C_U139391
2623 |  | CNV-23026257100 INSTALL 300'-2\" PMMP | 4000077787 | GRT32.0000.00031 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 44932.26 | 2023-10-26 | 2023-11-01 | 2025-07-30 | 1900-01-10 | 1899-12-31 | 1905-07-15 | C_U139391
2629 |  | CNV-23026286100 EMER - RETIRE 6'-2\" PMM | 4000078000 | ANC32.0000.00239 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 509.79 | 2024-10-31 | 2024-10-31 | 2025-07-30 | 6 | 15 | 2025 | C_U139391
2629 |  | CNV-23026288600 EMER - RETIRE 3'-2\" PMP | 4000078006 | ANC32.0000.00241 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3766.85 | 2023-08-11 | 2049-12-31 |  | 12 | 31 | 2049 | C_U139391
2621 |  | CNV-24026311800 EMER-INSTALL 5' OF 2\"PM | 4000075941 | ANC32.0000.00248 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1865.23 | 2024-09-30 | 2024-09-30 | 2025-07-31 | 9 | 30 | 2024 | C_U139391
2621 |  | CNV-24026311900 EMER-RETIRE 5' OF 2\"PAM | 4000075943 | ANC32.0000.00248 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 24.43 | 2024-09-30 | 2024-09-30 | 2025-07-31 | 9 | 30 | 2024 | C_U139391
2623 |  | CNV-23026266100 INSTALL 880'-4\" PHHP | 4000077797 | GRT32.0000.00034 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 39603.07 | 2023-09-05 | 2023-09-15 | 2025-07-30 | 1900-01-08 | 1900-01-14 | 1905-07-15 | C_U139391
2623 |  | CNV-23026266200 INSTALL 1100'-4\" PHHP | 4000077820 | GRT32.0000.00035 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 50705.26 | 2023-09-21 | 2023-09-30 | 2025-07-30 | 1900-01-08 | 1900-01-29 | 1905-07-15 | C_U139391
2629 |  | CNV-23026267600 INSTALL 110'-4\"PMLP | 4000077822 | GRT32.0000.00036 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 21198.05 | 2023-09-01 | 2023-09-01 | 2025-07-30 | 1900-01-08 | 1900-01-14 | 1905-07-15 | C_U139391
2623 |  | CNV-23026268500 PM-DE LINE ILI PH 2 BEND | 4000077823 | BET32.0000.00032 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 371961.49 | 2023-12-28 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2623 |  | CNV-23026269000 EMER-INSTALL 4' OF 2\"PM | 4000077825 | ANC32.0000.00040 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-11-30 | 2023-11-30 |  | 1900-01-10 | 1900-01-29 | 1905-07-15 | C_U139391
2623 |  | CNV-23026271000 INSTALL 70'-2\" PMMP | 4000077827 | BET32.0000.00036 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 70.4 | 2023-04-26 | 2023-04-30 |  | 1900-01-03 | 1900-01-29 | 1905-07-15 | C_U139391
2623 |  | CNV-23026271100 ABANDON 60'-2\" PMMP | 4000077829 | BET32.0000.00036 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-04-28 | 2023-04-30 |  | 1900-01-03 | 1900-01-29 | 1905-07-15 | C_U139391
2629 |  | CNV-23026273200 EMER-RETIRE 741'-1\" PMP | 4000077831 | ANC32.0000.00106 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-04-27 | 2023-04-27 |  | 1900-01-03 | 1900-01-28 | 1905-07-15 | C_U139391
2623 |  | CNV-23026273500 EMER-INSTALL 65' OF 2\"P | 4000077833 | ANC32.0000.00225 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-04-18 | 2023-04-18 |  | 1900-01-03 | 1900-01-18 | 1905-07-15 | C_U139391
2623 |  | CNV-23026273600 EMER-RETIRE 55' OF 2\"PA | 4000077835 | ANC32.0000.00225 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 311.11 | 2023-04-19 | 2023-04-19 | 2025-07-30 | 1900-01-03 | 1900-01-18 | 1905-07-15 | C_U139391
2633 |  | CNV-23026274600 EMER - INSTALL 5'-2\" PM | 4000077837 | BET32.0000.00008 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-05-26 | 2023-05-30 |  | 1900-01-04 | 1900-01-29 | 1905-07-15 | C_U139391
2629 |  | CNV-23026274900 EMER - INSTALL 4'-2\" PM | 4000077839 | ANC32.0000.00227 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-04-05 | 2023-04-05 |  | 1900-01-04 | 1900-01-08 | 1905-07-15 | C_U139391
2621 |  | CNV-24026314000 EMER-INSTALL 5' OF 4\"PM | 4000075947 | ANC32.0000.00249 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 249.15 | 2024-09-30 | 2024-09-30 | 2025-07-31 | 9 | 30 | 2024 | C_U139391
2629 |  | CNV-23026275100 RETIRE 276'-3\" BSLP | 4000077883 | PIG32.0000.00018 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-05-25 | 2023-05-26 |  | 1900-01-04 | 1900-01-25 | 1905-07-15 | C_U139391
2631 |  | CNV-23026275200 EMER - INSTALL 3'-2\" PM | 4000077885 | ANC32.0000.00228 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 24.2 | 2023-06-29 | 2023-06-30 |  | 1900-01-05 | 1900-01-29 | 1905-07-15 | C_U139391
2631 |  | CNV-23026275300 EMER - RETIRE 3'-2\" PIP | 4000077887 | ANC32.0000.00228 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-06-30 | 2023-06-30 |  | 1900-01-05 | 1900-01-29 | 1905-07-15 | C_U139391
2631 |  | CNV-23026276500 EMER - ABANDON 5'-4\"CSL | 4000077889 | BET32.0000.00047 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-06-09 | 2023-06-09 |  | 1900-01-11 | 1900-01-29 | 1905-07-15 | C_U139391
2631 |  | CNV-23026277600 INSTALL 595'-2\"PMMP | 4000077891 | ANC32.0000.00230 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 71122.9 | 2023-11-30 | 2023-12-31 | 2025-07-31 | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2629 |  | CNV-23026278500 EMER - INSTALL 3'-2\" PM | 4000077893 | ANC32.0000.00232 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 15.4 | 2023-06-01 | 2023-06-01 |  | 1900-01-05 | 1900-01-05 | 1905-07-15 | C_U139391
2629 |  | CNV-23026278600 EMER - RETIRE 3'-2\" PMM | 4000077895 | ANC32.0000.00232 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 8.22 | 2023-06-06 | 2023-06-06 | 2025-07-30 | 1900-01-05 | 1900-01-05 | 1905-07-15 | C_U139391
2631 |  | CNV-23026278700 INSTALL 105'-2\" PMMP | 4000077897 | GRT32.0000.00041 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 493.49 | 2023-06-14 | 2023-06-15 | 2025-07-30 | 1900-01-05 | 1900-01-14 | 1905-07-15 | C_U139391
2623 |  | CNV-23026278900 INSTALL 150'-2\" PMMP | 4000077899 | GRT32.0000.00042 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6557.82 | 2023-08-28 | 2023-08-31 | 2025-07-30 | 1900-01-07 | 1900-01-30 | 1905-07-15 | C_U139391
2621 |  | CNV-24026314100 EMER-RETIRE 5' OF 4\"PAM | 4000075949 | ANC32.0000.00249 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 39.03 | 2024-09-30 | 2024-09-30 | 2025-07-31 | 9 | 30 | 2024 | C_U139391
2621 |  | WILSON ST SMRP - CNV-24026315000 | 4000075741 | ANC32.0000.00250 | REL PCNF GMPS MANC PRC SETC | COCO FCMP | MAI | 49600.16 | 135400.19 | 2025-10-21 | 2025-12-31 | 2025-08-03 | 12 | 31 | 2025 | C_U139391
2623 |  | CNV-23026279800 INSTALL 1800'-2\" PMMP | 4000077924 | GRT32.0000.00094 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 38792.39 | 2023-08-16 | 2023-08-31 | 2025-07-30 | 1900-01-07 | 1900-01-30 | 1905-07-15 | C_U139391
2631 |  | CNV-23026280200 RETIRE 18570'-2\"-16\" S | 4000077926 | ANC32.0000.00101 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 78531.65 | 2024-07-31 | 2024-07-31 | 2025-07-31 | 1900-01-02 | 1900-01-15 | 1905-07-17 | C_U139391
2629 |  | ANC-SMRP Horseshoe Dr-Paris | 4000075743 | ANC32.0000.00251 | REL PCNF GMPS MANC PRC SETC | SCHD ADJ FCMP WGMA | MAI | 1377904 | 3912671.17 | 2025-07-24 | 2025-12-31 | 2026-03-16 | 12 | 31 | 2026 | C_U139391
2623 |  | CNV-23026281200 EMER-INSTALL 2' OF 2\"PM | 4000077930 | ANC32.0000.00045 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | -263.32 | 2023-06-26 | 2023-06-26 |  | 1900-01-05 | 1900-01-25 | 1905-07-15 | C_U139391
2623 |  | CNV-23026281400 INSTALL 1865'-2\"/4\" PM | 4000077932 | GRT32.0000.00043 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 49484.4 | 2023-10-17 | 2023-10-31 | 2025-07-31 | 1900-01-10 | 1900-01-16 | 1905-07-15 | C_U139391
2621 |  | CNV-24026316800 RETIRE 9920' OF 4\\\"/6. | 4000073963 | ANC32.0000.00252 | REL MANC NMAT PRC SETC | NEW REV WENG | MAI | 0 | 0 | 2024-12-31 | 2024-12-31 |  | 12 | 31 | 2024 | C_U139391
2621 |  | CNV-24026316701 INSTALL 11245' OF 2\\\". | 4000076405 | ANC32.0000.00252 | REL MANC NMAT PRC SETC | NEW REV WENG | MAI | 0 | 116711.13 | 2024-05-28 | 2024-12-31 |  | 12 | 31 | 2024 | C_U139391
2633 |  | CNV-23026282000 INSTALL 40'-4\" PMIP | 4000077938 | PIG32.0000.00042 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 31561.33 | 2023-07-24 | 2023-07-30 | 2025-07-30 | 1900-01-06 | 1900-01-29 | 1905-07-15 | C_U139391
2621 |  | CNV-22026228500 INSTALL 167'-2\" PMMP | 4000077957 | PIG32.0000.00031 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 34180.49 | 2024-06-14 | 2024-06-30 | 2025-07-31 | 1900-01-05 | 1900-01-29 | 1905-07-16 | C_U139391
2621 |  | CNV-22026228600 RETIRE 136'-2\" PMMP | 4000077959 | PIG32.0000.00031 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 50.08 | 2024-06-28 | 2024-06-30 | 2025-07-31 | 1900-01-05 | 1900-01-29 | 1905-07-16 | C_U139391
2633 |  | CNV-23026282100 RETIRE 36'-4\" BSIP | 4000077960 | PIG32.0000.00042 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 124.11 | 2023-07-28 | 2023-07-30 | 2025-07-30 | 1900-01-06 | 1900-01-29 | 1905-07-15 | C_U139391
2629 |  | CNV-23026282600 EMER - RETIRE 216'-2\" P | 4000077962 | ANC32.0000.00107 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 5051.47 | 2024-08-28 | 2024-08-31 |  | 1900-01-03 | 1900-01-16 | 1905-07-17 | C_U139391
2623 |  | CNV-23026282800 EMER - INSTALL 5'-2\" PM | 4000077964 | ANC32.0000.00046 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 7813.18 | 2024-03-21 | 2024-03-31 | 2025-07-31 | 1900-01-03 | 1900-01-27 | 1905-07-16 | C_U139391
2621 |  | CNV-25026409300 PAPER ONLY LP STOPPLE FI | 4000077274 | ANC32.0000.00252 | REL NMAT PRC SETC | NEW FCMP NSFS WENG | MAI | 0 | 0 | 2025-05-30 | 2025-06-01 |  | 6 | 15 | 2025 | C_U139391
2623 |  | CNV-23026283801 INSTALL 5705'-2\"/4\" PM | 4000077968 | GRT32.0000.00095 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 222206.91 | 2024-01-22 | 2024-03-01 | 2025-07-31 | 1900-01-04 | 1900-01-30 | 1905-07-16 | C_U139391
2623 |  | CNV-23026284000 EMER-INSTALL 2' OF 3\"PM | 4000077970 | ANC32.0000.00047 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 11033.96 | 2023-11-30 | 2023-11-30 | 2025-07-30 | 1900-01-06 | 1900-01-24 | 1905-07-16 | C_U139391
2631 |  | CNV-23026284800 EMER - INSTALL 40'-4\" P | 4000077972 | ANC32.0000.00238 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 389.63 | 2024-03-27 | 2024-03-31 | 2025-07-30 | 1900-01-02 | 1900-01-30 | 1905-07-16 | C_U139391
2631 |  | CNV-23026284900 EMER - RETIRE 40'-4\" BS | 4000077974 | ANC32.0000.00238 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 320.17 | 2024-03-28 | 2024-03-31 | 2025-07-30 | 1900-01-02 | 1900-01-30 | 1905-07-16 | C_U139391
2623 |  | CNV-23026285800 EMER-INSTALL 3' OF 2\"PM | 4000077976 | ANC32.0000.00048 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3521.71 | 2023-07-24 | 2023-07-24 | 2025-07-30 | 1900-01-06 | 1900-01-24 | 1905-07-15 | C_U139391
2621 |  | 2621-ST THERESA ABN - EMER - LEXINGTON | 4000088152 | ANC32.0000.00252 | CRTD MANC NTUP PRC | EST | MAI | 44.58 | 0 | 2025-08-18 | 2025-08-18 |  |  |  |  | U127466
2633 |  | CNV-24026317800 EMER - INSTALL 5'-2\\\. | 4000073964 | ANC32.0000.00253 | REL PCNF MANC NMAT PRC SETC | NEW REV | MAI | 0 | 4186.94 | 2024-12-31 | 2024-12-31 | 2025-07-31 | 8 | 8 | 2025 | C_U139391
2621 |  | CNV-22026234001 INSTALL 500' OF 2\"/4\"P | 4000077983 | GRT32.0000.00008 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-03-21 | 2023-04-15 |  | 1900-01-03 | 1900-01-14 | 1905-07-15 | C_U139391
2633 |  | CNV-24026317900 EMER - RETIRE 5'-2\" PIP | 4000073965 | ANC32.0000.00253 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 162.76 | 2024-12-31 | 2024-12-31 | 2025-07-31 | 8 | 8 | 2025 | C_U139391
2621 |  | CNV-22026236700 INSTALL 134'-4\" PMLP | 4000077987 | PIG32.0000.00032 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 12290.93 | 2024-03-18 | 2024-03-20 | 2025-07-31 | 1900-01-02 | 1900-01-19 | 1905-07-16 | C_U139391
2621 |  | CNV-22026236800 RETIRE 130'-4\" PLP | 4000077989 | PIG32.0000.00032 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 7455.47 | 2024-03-20 | 2024-03-20 | 2025-07-31 | 1900-01-02 | 1900-01-19 | 1905-07-16 | C_U139391
2631 |  | ANC - SMRP FLOYD STREET - ASHLAND | 4000075753 | ANC32.0000.00256 | REL GMPS MANC PRC SETC | NPRG ADJ FCMP MEQD WGMA | MAI | 242958.47 | 3291186.21 | 2025-07-17 | 2025-12-31 |  | 12 | 31 | 2026 | C_U139391
2621 |  | CNV-22026238200 INSTALL 205' OF 2\"PMMP | 4000077994 | GRT32.0000.00010 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 237.6 | 2023-01-25 | 2023-01-31 |  | 1899-12-31 | 1900-01-30 | 1905-07-15 | C_U139391
2621 |  | WOLF RUN 2025 SMRP CNV-24026322000 | 4000076409 | ANC32.0000.00257 | REL GMPS MANC PRC SETC | COCO ADJ FCMP | MAI | 730195.39 | 681714.43 | 2025-07-31 | 2025-12-31 |  | 12 | 31 | 2025 | C_U139391
2621 |  | CNV-24026330300 EMER - INSTALL 5'- 2\" P | 4000074003 | ANC32.0000.00259 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6479.76 | 2024-12-31 | 2024-12-31 | 2025-07-31 | 8 | 24 | 2025 | C_U139391
2621 |  | CNV-24026330400 EMER-RETIRE 5'-2\"PMMP | 4000074004 | ANC32.0000.00259 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 180.15 | 2024-12-31 | 2024-12-31 | 2025-07-31 | 8 | 24 | 2025 | C_U139391
2632 |  | CNV-23026287300 INSTALL 121'-4\" CSMP | 4000078002 | PIG32.0000.00009 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 79739.32 | 2024-03-08 | 2024-03-30 | 2025-08-01 | 1900-01-11 | 1900-01-29 | 1905-07-16 | C_U139391
2629 |  | CNV-23026287800 INSTALL 500'-4\" PMMP | 4000078004 | BET32.0000.00010 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 92799.54 | 2023-11-13 | 2023-11-30 | 2025-07-30 | 1900-01-10 | 1900-01-29 | 1905-07-15 | C_U139391
2623 |  | CNV-24026331601 INSTALL 475' OF 2\"PMMP | 4000079775 | ANC32.0000.00260 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 568.23 | 2025-04-15 | 2025-04-30 |  | 12 | 5 | 2025 | C_U139391
2623 |  | CNV-24026331700 REITRE 435' OF 2\"BSLP M | 4000079777 | ANC32.0000.00260 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 396.72 | 2025-04-30 | 2025-04-30 | 2025-07-31 | 12 | 5 | 2025 | C_U139391
2623 |  | CNV-23026289700 INSTALL 70' OF 3\"PMLP M | 4000078009 | ANC32.0000.00242 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1556.55 | 2023-11-28 | 2023-11-30 |  | 1900-01-07 | 1900-01-30 | 1905-07-16 | C_U139391
2623 |  | CNV-23026289800 RETIRE 271' OF 2\"/3\"BS | 4000078011 | ANC32.0000.00242 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 15400.09 | 2023-11-30 | 2023-11-30 | 2025-07-31 | 1900-01-07 | 1900-01-30 | 1905-07-16 | C_U139391
2629 |  | CNV-23026289900 EMER-INSTALL 8'-3\" PMMP | 4000078013 | ANC32.0000.00243 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2245.29 | 2023-08-23 | 2023-09-03 |  | 1900-01-08 | 1900-01-05 | 1905-07-15 | C_U139391
2629 |  | CNV-23026290000 EMER-RETIRE 8'-3\" PAMP | 4000078016 | ANC32.0000.00243 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3557.52 | 2023-08-23 | 2023-09-03 | 2025-07-30 | 1900-01-08 | 1900-01-05 | 1905-07-15 | C_U139391
2633 |  | CNV-23026291200 EMER - INSTALL 8'-3\" PM | 4000078018 | ANC32.0000.00246 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 18113.32 | 2023-08-30 | 2023-08-31 |  | 1900-01-07 | 1900-01-30 | 1905-07-15 | C_U139391
2621 |  | CNV-22026241500 INSTALL 40'-2\" PMMP | 4000078020 | BET32.0000.00031 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-26 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2621 |  | CNV-22026242301 INSTALL 8\"POLY VALVE W/ | 4000078022 | ANC32.0000.00115 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 18738.58 | 2023-10-02 | 2023-10-15 |  | 1900-01-09 | 1900-01-14 | 1905-07-15 | C_U139391
2621 |  | CNV-22026242600 INSTALL 500' - 4\" PMMP | 4000078025 | ANC32.0000.00115 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-09-18 | 2023-10-01 |  | 1900-01-09 | 1899-12-31 | 1905-07-15 | C_U139391
2621 |  | CNV-22026242700 INSTALL 350' OF 8\"CSHP | 4000078027 | PIG32.0000.00004 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 312402.5 | 2023-07-10 | 2023-09-01 | 2025-07-30 | 1900-01-08 | 1900-01-29 | 1905-07-15 | C_U139391
2621 |  | CNV-24026332100 INSERT 50' OF 3\" PMLP | 4000076076 | ANC32.0000.00262 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 7319.46 | 2024-10-29 | 2024-10-31 |  | 6 | 12 | 2025 | C_U139391
2621 |  | CNV-22026158800 INSTALL 540' OF 4\"/8\"P | 4000078033 | ANC32.0000.00009 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-11-21 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2621 |  | CNV-24026332200 RETIRE 52' - 4\" CSLP | 4000076078 | ANC32.0000.00262 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 9131.55 | 2024-10-31 | 2024-10-31 | 2025-07-31 | 6 | 12 | 2025 | C_U139391
2623 |  | CNV-24026332800 EMER - INSTALL 5'-4\" PM | 4000079801 | ANC32.0000.00263 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 4699.68 | 2025-02-28 | 2025-02-28 | 2025-07-31 | 10 | 10 | 2025 | C_U139391
2621 |  | CNV-22026162102 INSTALL 8150' OF 2\"/4\" | 4000078038 | ANC32.0000.00172 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 28375.28 | 2023-11-01 | 2023-12-31 | 2025-07-31 | 1900-01-10 | 1899-12-31 | 1905-07-15 | C_U139391
2633 |  | CNV-23026291300 EMER - RETIRE 7'3\" BS&P | 4000078040 | ANC32.0000.00246 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 392.92 | 2023-08-31 | 2023-08-31 | 2025-07-30 | 1900-01-07 | 1900-01-30 | 1905-07-15 | C_U139391
2623 |  | CNV-23026292201 INSTALL 360'-4\" PMMP | 4000078042 | GRT32.0000.00003 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2024-01-15 | 2024-02-29 |  | 1900-01-01 | 1900-01-28 | 1905-07-16 | C_U139391
2631 |  | CNV-23026292300 INSTALL 2\" SS | 4000078044 | BET32.0000.00039 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 772.22 | 2024-02-27 | 2024-02-28 | 2025-07-31 | 1900-01-01 | 1900-01-27 | 1905-07-16 | C_U139391
2631 |  | CNV-23026292400 RETIRE 154'-2\" CSIP | 4000078046 | BET32.0000.00039 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 13099.19 | 2024-02-28 | 2024-02-28 | 2025-07-31 | 1900-01-01 | 1900-01-27 | 1905-07-16 | C_U139391
2623 |  | CNV-24026332900 EMER - ABANDON 5'-4\" PM | 4000079803 | ANC32.0000.00263 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 0 | 2025-02-27 | 2025-02-28 |  | 10 | 10 | 2025 | C_U139391
2629 |  | CNV-23026293900 EMER-INSTALL 3' OF 2\"PM | 4000078050 | ANC32.0000.00022 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 5282 | 2023-09-05 | 2023-09-05 |  | 1900-01-08 | 1900-01-06 | 1905-07-15 | C_U139391
2631 |  | CNV-23026294700 INSTALL 70'-2\" PMIP | 4000078052 | GRT32.0000.00013 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 8507.52 | 2023-12-28 | 2024-01-02 | 2025-07-31 | 1899-12-31 | 1900-01-01 | 1905-07-16 | C_U139391
2623 |  | CNV-23026296400 INSTALL 110' OF 2\"PMMP | 4000078054 | ANC32.0000.00023 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 27214.96 | 2023-12-18 | 2023-12-31 | 2025-07-31 | 1899-12-31 | 1900-01-09 | 1905-07-16 | C_U139391
2631 |  | CNV-23026296700 INSTALL 165' OF 2\" PMIP | 4000078056 | GRT32.0000.00016 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3877.96 | 2023-11-27 | 2023-11-30 | 2025-07-31 | 1900-01-10 | 1900-01-29 | 1905-07-15 | C_U139391
2631 |  | CNV-24026333201 EMER - INSTALL 478'-4\\. | 4000079805 | ANC32.0000.00264 | REL PCNF MANC NMAT NTUP PRC SETC | NEW | MAI | 0 | 81563.52 | 2025-02-17 | 2025-02-28 | 2025-08-01 | 2 | 28 | 2025 | C_U139391
2623 |  | CNV-23026298800 INSTALL 900'-2\" PMMP MA | 4000078059 | GRT32.0000.00017 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 59974.8 | 2024-04-04 | 2024-04-17 | 2025-07-31 | 1900-01-03 | 1900-01-16 | 1905-07-16 | C_U139391
2621 |  | CNV-22026162200 RETIRE 4600' OF 4\"/6\"B | 4000078060 | ANC32.0000.00172 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1449.39 | 2023-12-31 | 2023-12-31 | 2025-07-31 | 1900-01-07 | 1900-01-10 | 1905-07-16 | C_U139391
2621 |  | CNV-22026163200 INSTALL 775' OF 2\"PMMP | 4000078062 | ANC32.0000.00173 | REL GMPS NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2180.97 | 2023-12-05 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2631 |  | CNV-24026333301 EMER - RETIRE 477'-4\" C | 4000079807 | ANC32.0000.00264 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 0 | 2025-02-28 | 2025-02-28 |  | 2 | 28 | 2025 | C_U139391
2621 |  | CNV-24026334200 RETIRE 5' OF 2\" PMP | 4000076104 | ANC32.0000.00265 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 47.46 | 2025-03-28 | 2025-03-30 | 2025-07-31 | 2 | 8 | 2026 | C_U139391
2621 |  | CNV-24026339800 INSTALL 35' OF 6\"PMLP M | 4000076110 | ANC32.0000.00266 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 9350.15 | 2024-09-27 | 2024-10-01 | 2025-08-01 | 10 | 1 | 2024 | C_U139391
2621 |  | CNV-24026339900 RETIRE 25' OF 6\"BSLP MA | 4000076112 | ANC32.0000.00266 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3735.71 | 2024-10-01 | 2024-10-01 | 2025-08-01 | 10 | 1 | 2024 | C_U139391
2629 |  | CNV-23026300401 INSTALL 1150' 4/2\" PMMP | 4000078085 | PIG32.0000.00035 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 202.42 | 2024-02-22 | 2024-03-15 |  | 1900-01-03 | 1900-01-25 | 1905-07-16 | C_U139391
2629 |  | CNV-23026300600 INSTALL 180'-4\" PMLP | 4000078087 | PIG32.0000.00006 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 49799.74 | 2023-12-18 | 2023-12-31 | 2025-07-31 | 1899-12-31 | 1900-01-25 | 1905-07-16 | C_U139391
2631 |  | ANC-BBQ HOLLOW HP SMRP-ASHLAND | 4000075755 | ANC32.0000.00267 | REL NMAT PRC SETC | NEW NSFS | MAI | 0 | 0 | 2025-01-23 | 2025-01-31 |  | 12 | 31 | 2026 | C_U139391
2621 |  | CNV-24026346300 EMER-INSTALL 3' OF 2\"PM | 4000075788 | ANC32.0000.00269 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4206.97 | 2024-09-30 | 2024-10-01 | 2025-08-01 | 10 | 1 | 2024 | C_U139391
2629 |  | CNV-23026302800 EMER - INSTALL 2'-3\" PM | 4000078093 | ANC32.0000.00203 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2064.2 | 2023-10-18 | 2023-10-27 |  | 1900-01-09 | 1900-01-29 | 1905-07-15 | C_U139391
2629 |  | CNV-23026302900 EMER - RETIRE 2'-3\" PMP | 4000078095 | ANC32.0000.00203 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1224.64 | 2023-10-27 | 2023-10-27 |  | 1900-01-09 | 1900-01-29 | 1905-07-15 | C_U139391
2629 |  | CNV-23026303000 EMER - RETIRE 13'-3\" BS | 4000078097 | ANC32.0000.00103 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 18214.32 | 2023-10-26 | 2023-10-31 | 2025-08-01 | 1900-01-11 | 1900-01-30 | 1905-07-16 | C_U139391
2621 |  | CNV-24026346400 EMER-RETIRE 3' OF 2\"PMM | 4000075790 | ANC32.0000.00269 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 157.44 | 2024-10-01 | 2024-10-01 | 2025-08-01 | 10 | 1 | 2024 | C_U139391
2623 |  | CNV-19026878100 INVESTIGATE LAND RIGHT/E | 4000078119 | PSI32.0000.00004 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 13171.38 | 2024-11-26 | 2024-11-26 |  | 1900-01-11 | 1899-12-31 | 1905-07-16 | C_U139391
2621 |  | CNV-24026346600 EMER-INSTALL 8' OF 4\"PM | 4000075792 | ANC32.0000.00270 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4789.73 | 2024-09-26 | 2024-09-26 | 2025-08-01 | 9 | 28 | 2024 | C_U139391
2629 |  | CNV-23026306000 EMER-INSTALL 2'-3\" PMMP | 4000078123 | ANC32.0000.00028 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4274.2 | 2023-11-08 | 2023-11-08 |  | 1900-01-10 | 1900-01-16 | 1905-07-15 | C_U139391
2633 |  | CNV-23026307300 INSTALL ~100'-2\" PMIP | 4000078125 | GRT32.0000.00023 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 22820.46 | 2024-01-02 | 2024-01-15 | 2025-07-31 | 1899-12-31 | 1900-01-30 | 1905-07-16 | C_U139391
2623 |  | CNV-23026307400 EMER-INSTALL 3' OF 2\"PM | 4000078127 | ANC32.0000.00029 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 824.94 | 2024-03-01 | 2024-03-01 |  | 1900-01-02 | 1899-12-31 | 1905-07-16 | C_U139391
2623 |  | CNV-23026308601 INSTALL 675'-2\" PMMP | 4000078128 | GRT32.0000.00024 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6607.39 | 2024-04-24 | 2024-04-30 |  | 1900-01-04 | 1900-01-29 | 1905-07-16 | C_U139391
2623 |  | CNV-19026881800 ACQUIRE EASEMENT/LAND RI | 4000078141 | PSI32.0000.00004 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 0 | 2020-12-31 | 2020-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-12 | C_U139391
2621 |  | CNV-19026907000 OBTAIN USABLE EASEMENT | 4000078143 | PSI32.0000.00003 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 0 | 2022-12-29 | 2022-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-14 | C_U139391
2623 |  | CNV-19026907200 INVESTIGATE ENCROACHMENT | 4000078145 | PSI32.0000.00037 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 0 | 2020-12-31 | 2020-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-12 | C_U139391
2629 |  | PSI-Colby Rd HP ROW-Winchester | 4000078189 | PSI32.0000.00007 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 6842.64 | 2021-12-30 | 2021-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-13 | C_U139391
2629 |  | ANC-Levee Rd POD Valve-Mt Sterling | 4000078191 | ANC32.0000.00118 | REL NMAT PRC SETC | NEW NSFS REV | STA | 0 | 0 | 2023-12-28 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2623 |  | CNV-21026145400 INVESTIGATE &/OR ACQUIRE | 4000078193 | PSI32.0000.00008 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 0 | 2021-12-29 | 2021-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-13 | C_U139391
2629 |  | CNV-21026149800 RETIRE R-1615 | 4000078195 | ANC32.0000.00189 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-12-21 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2629 |  | PSI-Wisemantown Rd-Irvine | 4000078197 | PSI32.0000.00037 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 10955.18 | 2022-12-29 | 2022-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-14 | C_U139391
2621 |  | CNV-23026248200 EMER - INSTALL 2'-2\" PM | 4000078235 | ANC32.0000.00211 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-01-06 | 2023-01-06 |  | 1899-12-31 | 1900-01-08 | 1905-07-15 | C_U139391
2621 |  | CNV-23026248300 EMER - RETIRE ~2'-2\"PMP | 4000078237 | ANC32.0000.00211 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-01-09 | 2023-01-09 |  | 1899-12-31 | 1900-01-08 | 1905-07-15 | C_U139391
2621 |  | CNV-23026248400 EMER-INSTALL 3' OF 2\"PM | 4000078239 | ANC32.0000.00031 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-09-29 | 2023-09-30 |  | 1900-01-08 | 1900-01-29 | 1905-07-15 | C_U139391
2631 |  | CNV-24026347300 EMER - INSTALL 12'-3\" P | 4000082667 | ANC32.0000.00271 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 15910.58 | 2025-02-24 | 2025-02-28 | 2025-07-31 |  |  |  | C_U139391
2621 |  | CNV-22026167200 INSTALL 720'- 4\" PMMP | 4000078247 | ANC32.0000.00011 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-11-14 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2631 |  | CNV-24026347400 EMER - RETIRE 12'-3\" PI | 4000082668 | ANC32.0000.00271 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 139.93 | 2025-02-28 | 2025-02-28 | 2025-07-31 |  |  |  | C_U139391
2621 |  | CNV-24026348800 EMER-LEAK RETIRE C14-37 | 4000073967 | ANC32.0000.00272 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 693.83 | 2024-12-31 | 2024-12-31 | 2025-08-01 | 12 | 31 | 2024 | C_U139391
2621 |  | CNV-22026171100 INSTALL 2715' OF 2\"/4\" | 4000078253 | ANC32.0000.00178 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 341540.67 | 2024-01-22 | 2024-08-19 | 2025-07-31 | 1900-01-07 | 1900-01-18 | 1905-07-16 | C_U139391
2621 |  | CNV-22026171200 RETIRE 2300' OF 3\"/6\"B | 4000078255 | ANC32.0000.00178 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 233.2 | 2024-08-19 | 2024-08-19 |  | 1900-01-07 | 1900-01-18 | 1905-07-16 | C_U139391
2621 |  | CNV-22026178900 INSTALL 620' OF 12\"CSHP | 4000078257 | ANC32.0000.00182 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 55631.6 | 2023-06-09 | 2023-07-31 | 2025-07-30 | 1900-01-02 | 1900-01-30 | 1905-07-16 | C_U139391
2621 |  | CNV-22026179100 RETIRE 520' OF 12\"MJBSH | 4000078259 | ANC32.0000.00182 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1186.35 | 2023-07-31 | 2023-07-31 | 2025-07-30 | 1900-01-02 | 1900-01-30 | 1905-07-16 | C_U139391
2621 |  | CNV-23026249300 EMER-INSTALL 5' OF 2\"PM | 4000078261 | ANC32.0000.00212 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-01-13 | 2023-01-13 |  | 1899-12-31 | 1900-01-12 | 1905-07-15 | C_U139391
2621 |  | CNV-23026249400 EMER-RETIRE 5' OF 2\"PMM | 4000078263 | ANC32.0000.00212 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-01-13 | 2023-01-13 |  | 1899-12-31 | 1900-01-12 | 1905-07-15 | C_U139391
2621 |  | CNV-23026251700 INSTALL 2060' OF 2\" PMM | 4000078265 | GRT32.0000.00087 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-03-29 | 2023-04-15 |  | 1900-01-03 | 1900-01-14 | 1905-07-15 | C_U139391
2621 |  | CNV-23026252000 EMER-INSTALL 3' OF 6\"PM | 4000078267 | ANC32.0000.00032 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-09-27 | 2023-09-30 |  | 1900-01-08 | 1900-01-29 | 1905-07-15 | C_U139391
2621 |  | CNV-23026252200 EMER-INSTALL 3' OF 4\"PM | 4000078269 | ANC32.0000.00033 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-09-28 | 2023-09-30 |  | 1900-01-08 | 1900-01-29 | 1905-07-15 | C_U139391
2621 |  | CNV-23026252600 INSTALL 3' OF 4\"PMLP MA | 4000078271 | ANC32.0000.00034 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-28 | 2023-12-31 |  | 1900-01-07 | 1900-01-25 | 1905-07-16 | C_U139391
2621 |  | CNV-23026256400 INSTALL 25' OF 2\"PMMP M | 4000078273 | GRT32.0000.00033 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6647.08 | 2023-07-28 | 2023-07-31 | 2025-07-30 | 1900-01-09 | 1900-01-25 | 1905-07-15 | C_U139391
2621 |  | CNV-23026259000 EMER-INST 85'-4\"PMMP MN | 4000078275 | ANC32.0000.00214 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 100.1 | 2023-02-15 | 2023-02-21 |  | 1900-01-01 | 1900-01-23 | 1905-07-15 | C_U139391
2621 |  | CNV-23026259100 EMER-RETIRE 85' OF 4\"PA | 4000078277 | ANC32.0000.00214 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-02-21 | 2023-02-21 |  | 1900-01-01 | 1900-01-23 | 1905-07-15 | C_U139391
2621 |  | CNV-23026262700 EMER-INSTALL 5' OF 2\"PM | 4000078279 | ANC32.0000.00216 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-03-07 | 2023-09-30 |  | 1900-01-04 | 1900-01-18 | 1905-07-16 | C_U139391
2621 |  | CNV-22026183100 INSTALL 3090' OF 2-4\" P | 4000078281 | PIG32.0000.00027 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 136292.1 | 2023-07-03 | 2023-08-30 | 2025-07-30 | 1900-01-09 | 1900-01-29 | 1905-07-15 | C_U139391
2621 |  | CNV-22026183301 SMRP INSTALL 1120' 8-12\ | 4000078283 | PIG32.0000.00027 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 23594.6 | 2023-11-29 | 2024-03-15 |  | 1900-01-02 | 1900-01-14 | 1905-07-16 | C_U139391
2621 |  | CNV-22026184800 INSTALL 3775'-2\" PMMP | 4000078285 | PIG32.0000.00029 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-03-15 | 2023-06-30 |  | 1900-01-05 | 1900-01-29 | 1905-07-15 | C_U139391
2621 |  | CNV-22026184900 RETIRE 3315'-2\"&4\"BSLP | 4000078287 | PIG32.0000.00029 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-06-30 | 2023-06-30 |  | 1900-01-05 | 1900-01-29 | 1905-07-15 | C_U139391
2621 |  | CNV-22026210301 INSTALL 850' OF 4\"PMMP | 4000078289 | GRT32.0000.00006 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 413.67 | 2022-12-06 | 2023-02-01 |  | 1900-01-01 | 1899-12-31 | 1905-07-15 | C_U139391
2621 |  | CNV-22026219400 INSTALL 380' OF 4\"PMMP | 4000078291 | ANC32.0000.00186 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 41.65 | 2023-12-07 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2621 |  | CNV-22026223600 INSTALL 3000' OF 2\"PMMP | 4000078293 | GRT32.0000.00083 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 51747.22 | 2023-07-03 | 2023-07-31 | 2025-07-30 | 1900-01-07 | 1900-01-29 | 1905-07-15 | C_U139391
2621 |  | CNV-22026223700 INSTALL 1296'-2\"&4\" PM | 4000078295 | PIG32.0000.00003 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | -695.88 | 2023-01-23 | 2023-03-30 |  | 1900-01-03 | 1900-01-29 | 1905-07-15 | C_U139391
2621 |  | CNV-22026223900 INSTALL 1067'-4\" PMMP | 4000078297 | PIG32.0000.00002 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 317.13 | 2023-03-17 | 2023-03-30 |  | 1900-01-02 | 1900-01-29 | 1905-07-15 | C_U139391
2621 |  | CNV-24026348700 EMER - INSTALL 5' OF 2\" | 4000075820 | ANC32.0000.00272 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4003.47 | 2024-12-30 | 2024-12-31 |  | 12 | 31 | 2024 | C_U139391
2621 |  | CNV-23026262800 EMER-RETIRE 5' OF 2\"PMP | 4000078301 | ANC32.0000.00216 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-03-07 | 2023-09-30 |  | 1900-01-04 | 1900-01-18 | 1905-07-16 | C_U139391
2621 |  | CNV-23026264700 INSTALL 100' OF 3\"PMLP | 4000078303 | ANC32.0000.00220 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 108.9 | 2023-12-21 | 2023-12-31 |  | 1900-01-07 | 1900-01-10 | 1905-07-16 | C_U139391
2621 |  | CNV-23026266300 EMER-INSTALL 3' OF 2\"PM | 4000078306 | ANC32.0000.00037 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-11-29 | 2023-11-30 |  | 1900-01-10 | 1900-01-29 | 1905-07-15 | C_U139391
2621 |  | CNV-23026267700 EMER-RETIRE 40' OF 6\"BS | 4000078308 | ANC32.0000.00105 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-28 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2621 |  | CNV-23026268200 INSERT 160' OF 3\"PMLP M | 4000078310 | ANC32.0000.00223 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 179.3 | 2023-12-27 | 2023-12-31 |  | 1900-01-07 | 1900-01-09 | 1905-07-16 | C_U139391
2621 |  | CNV-23026268300 RETIRE 160' OF 4\"BSLP M | 4000078312 | ANC32.0000.00223 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-04-04 | 2023-04-04 |  | 1900-01-07 | 1900-01-09 | 1905-07-16 | C_U139391
2621 |  | CNV-23026272300 EMER-INSTALL 3\" NC POLY | 4000078314 | BET32.0000.00037 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-09-29 | 2023-10-01 |  | 1900-01-09 | 1899-12-31 | 1905-07-15 | C_U139391
2621 |  | CNV-23026272400 EMER-RETIRE 3\"PV C16-87 | 4000078316 | BET32.0000.00037 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-09-29 | 2023-10-01 |  | 1900-01-09 | 1899-12-31 | 1905-07-15 | C_U139391
2621 |  | CNV-23026273000 INSTALL 20'-4\"PMMP W/NE | 4000078318 | BET32.0000.00007 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3025.27 | 2023-06-26 | 2023-10-01 |  | 1900-01-09 | 1899-12-31 | 1905-07-15 | C_U139391
2621 |  | CNV-23026273700 INSTALL 6' OF 2\"PMMP MA | 4000078341 | ANC32.0000.00226 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 59 | 2024-07-11 | 2024-07-12 | 2025-08-01 | 1900-01-04 | 1900-01-02 | 1905-07-17 | C_U139391
2631 |  | CNV-24026349700 EMER INSTALL 2' OF 2\" P | 4000082669 | ANC32.0000.00274 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 3768.7 | 2025-03-31 | 2025-03-31 | 2025-08-01 |  |  |  | C_U139391
2621 |  | CNV-23026276300 EMER-INSTALL 2\"POLY VAL | 4000078345 | BET32.0000.00009 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 25.98 | 2023-09-28 | 2023-10-01 |  | 1900-01-09 | 1899-12-31 | 1905-07-15 | C_U139391
2621 |  | CNV-23026276900 RETIRE 250' OF 3\"BSLP M | 4000078347 | PIG32.0000.00019 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-09-01 | 2023-09-01 |  | 1900-01-08 | 1899-12-31 | 1905-07-15 | C_U139391
2621 |  | CNV-23026277000 EMER-INSTALL 15' OF 8\"P | 4000078349 | ANC32.0000.00229 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4392.43 | 2024-07-29 | 2024-07-31 | 2025-07-30 | 1900-01-02 | 1900-01-12 | 1905-07-17 | C_U139391
2621 |  | CNV-23026277100 EMER-RETIRE 15' OF 8\"BS | 4000078351 | ANC32.0000.00229 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 305.34 | 2024-07-31 | 2024-07-31 | 2025-07-30 | 1900-01-02 | 1900-01-12 | 1905-07-17 | C_U139391
2621 |  | CNV-23026277200 EMER-RETIRE 55' OF 6\"PM | 4000078353 | PIG32.0000.00020 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 91.2 | 2023-06-30 | 2023-07-01 |  | 1900-01-06 | 1899-12-31 | 1905-07-15 | C_U139391
2621 |  | CNV-23026277900 EMER - INSTALL 69'-6\" P | 4000078354 | ANC32.0000.00231 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 328.02 | 2024-08-31 | 2024-08-31 | 2025-07-30 | 1900-01-03 | 1900-01-26 | 1905-07-17 | C_U139391
2621 |  | CNV-23026278000 EMER - RETIRE 69'-6\" BS | 4000078357 | ANC32.0000.00231 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2024-08-31 | 2024-08-31 |  | 1900-01-03 | 1900-01-26 | 1905-07-17 | C_U139391
2621 |  | CNV-23026280800 EMER-INSTALL 62' OF 4\"P | 4000078359 | ANC32.0000.00233 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3419.1 | 2023-11-30 | 2023-12-01 | 2025-07-30 | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2621 |  | CNV-23026280900 EMER-RETIRE 62' OF 4\"BS | 4000078381 | ANC32.0000.00233 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2158.04 | 2023-12-01 | 2023-12-01 | 2025-07-30 | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2621 |  | CNV-23026282700 EMER-ABANDON 333' OF 2\" | 4000078383 | ANC32.0000.00108 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2814.68 | 2023-07-06 | 2023-07-06 | 2025-07-30 | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2631 |  | CNV-24026349800 EMER ABANDON 2' OF 2\" P | 4000082670 | ANC32.0000.00274 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 267.85 | 2025-03-31 | 2025-03-31 |  |  |  |  | C_U139391
2621 |  | CNV-24026351400 EMER - INSTALL 2'-2\" PM | 4000075826 | ANC32.0000.00275 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 1375.93 | 2025-03-31 | 2025-03-31 | 2025-08-01 | 3 | 31 | 2025 | C_U139391
2621 |  | CNV-23026284300 EMER-INSTALL 490' OF 2\" | 4000078389 | ANC32.0000.00236 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 34965.39 | 2023-09-25 | 2023-10-01 |  | 1900-01-09 | 1899-12-31 | 1905-07-15 | C_U139391
2621 |  | CNV-23026284400 EMER-RETIRE 520' OF 4\"B | 4000078391 | ANC32.0000.00236 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 223.87 | 2023-09-29 | 2023-10-01 | 2025-07-30 | 1900-01-09 | 1899-12-31 | 1905-07-15 | C_U139391
2621 |  | CNV-23026284500 INSTALL 80'4\" PMLP | 4000078393 | ANC32.0000.00237 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4827.81 | 2024-08-26 | 2024-08-31 | 2025-07-30 | 1900-01-03 | 1900-01-24 | 1905-07-17 | C_U139391
2621 |  | CNV-23026284600 RETIRE 80'-4\" BSLP | 4000078395 | ANC32.0000.00237 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3894.31 | 2024-08-30 | 2024-08-31 | 2025-07-30 | 1900-01-03 | 1900-01-24 | 1905-07-17 | C_U139391
2621 |  | CNV-23026285300 EMER - RETIRE 159'-3\"BS | 4000078397 | ANC32.0000.00291 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2373.67 | 2023-07-24 | 2023-07-24 | 2025-07-30 | 1900-01-06 | 1900-01-23 | 1905-07-15 | C_U139391
2621 |  | CNV-23026286300 RETIRE 306' OF 3\"BSLP M | 4000078399 | PIG32.0000.00021 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3360.3 | 2023-09-15 | 2023-09-15 | 2025-07-30 | 1900-01-08 | 1900-01-14 | 1905-07-15 | C_U139391
2629 |  | PSI-Danimer Phase 3 ROW-Winchester | 4000078402 | PSI32.0000.00006 | TECO MANC NMAT PRC SETC | NEW CAN NSFS REV | PSI | 0 | 0 | 2021-12-28 | 2021-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-13 | C_U139391
2621 |  | CNV-23026286800 INSTALL 100' OF 2\"PMIP | 4000078441 | GRT32.0000.00045 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 12460.73 | 2023-11-16 | 2023-11-17 | 2025-07-31 | 1900-01-10 | 1900-01-16 | 1905-07-15 | C_U139391
2621 |  | CNV-23026287600 INSTALL 30'-4\" PMMP | 4000078443 | BET32.0000.00038 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 7282.62 | 2023-12-27 | 2023-12-31 | 2025-07-31 | 1900-01-11 | 1900-01-24 | 1905-07-16 | C_U139391
2621 |  | CNV-23026288000 EMER - INSTALL 5'-2\" PM | 4000078445 | ANC32.0000.00240 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 216.09 | 2023-08-10 | 2023-08-10 | 2025-07-30 | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2621 |  | CNV-23026288100 EMER - RETIRE 5'-2\" PMM | 4000078447 | ANC32.0000.00240 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1.31 | 2023-08-10 | 2023-08-10 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2621 |  | CNV-23026290800 INSERT/INSTALL 160'-3\"P | 4000078450 | ANC32.0000.00245 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 17580.75 | 2023-10-16 | 2023-10-20 | 2025-07-30 | 1900-01-11 | 1900-01-14 | 1905-07-15 | C_U139391
2621 |  | CNV-23026290900 RETIRE 60' OF 3\"BSLP MA | 4000078452 | ANC32.0000.00245 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6100.78 | 2023-10-20 | 2023-10-20 | 2025-07-30 | 1900-01-11 | 1900-01-14 | 1905-07-15 | C_U139391
2621 |  | CNV-24026351500 EMER - RETIRE 2'-2\" PMP | 4000075828 | ANC32.0000.00275 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 14.2 | 2025-03-31 | 2025-03-31 | 2025-08-01 | 3 | 31 | 2025 | C_U139391
2629 |  | ANC-SMRP Rogers Av-Mt Sterling | 4000079424 | ANC32.0000.00277 | REL NMAT PRC SETC | NEW NSFS REV | MAI | 0 | 478.34 | 2024-12-30 | 2024-12-31 |  | 8 | 21 | 2025 | C_U139391
2629 |  | DO NOT EXECUTE | 4100509750 | ANC32.0000.00277 | REL CSER MACM PRC SETC | NEW CAN | LND | 1 | 0 | 2024-12-31 | 2024-12-31 |  | 12 | 31 | 2024 | C_U139391
2629 |  | ANC-SMRP Rogers Av Land-Mt Sterling | 4000084801 | ANC32.0000.00277 | REL NMAT PRC SETC | NEW NSFS REV | LND | 0 | 2799.85 | 2024-12-31 | 2024-12-31 |  | 12 | 31 | 2024 | C_U141034
2621 |  | CNV-23026300800 EMER-INSTALL 5' OF 3\"PM | 4000078483 | ANC32.0000.00025 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3055.81 | 2023-10-10 | 2023-10-10 | 2025-07-31 | 1900-01-09 | 1900-01-09 | 1905-07-15 | C_U139391
2621 |  | CNV-23026301000 EMER-INSTALL 2' OF 4\"PM | 4000078485 | ANC32.0000.00026 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1923.97 | 2023-12-01 | 2023-12-01 |  | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2621 |  | CNV-23026303700 EMER - INSTALL 5' OF 2\" | 4000078487 | ANC32.0000.00204 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 206.72 | 2023-11-03 | 2023-11-03 | 2025-07-31 | 1900-01-05 | 1900-01-29 | 1905-07-16 | C_U139391
2621 |  | CNV-23026303800 EMER - RETIRE 3' OF 2\" | 4000078489 | ANC32.0000.00204 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 114.38 | 2023-11-03 | 2023-11-03 | 2025-07-31 | 1900-01-05 | 1900-01-29 | 1905-07-16 | C_U139391
2621 |  | CNV-23026303900 EMER-INSTALL 3'-2\" PMMP | 4000078490 | ANC32.0000.00027 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1192.62 | 2024-06-28 | 2024-06-30 |  | 1900-01-05 | 1900-01-29 | 1905-07-16 | C_U139391
2621 |  | CNV-23026305300 EMER-INSTALL 11'-2\" PMM | 4000078492 | ANC32.0000.00205 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4025.96 | 2023-11-10 | 2023-11-10 | 2025-07-31 | 1900-01-10 | 1900-01-12 | 1905-07-15 | C_U139391
2621 |  | CNV-23026305400 EMER-RETIRE 11'-2\" PMMP | 4000078494 | ANC32.0000.00205 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 383.65 | 2023-11-13 | 2023-11-13 | 2025-07-31 | 1900-01-10 | 1900-01-12 | 1905-07-15 | C_U139391
2621 |  | CNV-23026307900 EMER-INSTALL 10'-4\"PMMP | 4000078497 | ANC32.0000.00206 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 5370.7 | 2024-08-29 | 2024-08-31 | 2025-07-31 | 1900-01-07 | 1900-01-30 | 1905-07-16 | C_U139391
2621 |  | CNV-23026308000 EMER-RETIRE 10'-4\"PMP/C | 4000078499 | ANC32.0000.00206 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 147.12 | 2024-08-30 | 2024-08-31 | 2025-07-31 | 1900-01-07 | 1900-01-30 | 1905-07-16 | C_U139391
2621 |  | CNV-23026308900 EMER INSTALL 4' OF 3\" P | 4000078521 | ANC32.0000.00207 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2047.52 | 2024-04-29 | 2024-04-30 | 2025-07-31 | 1900-01-03 | 1900-01-29 | 1905-07-16 | C_U139391
2621 |  | CNV-23026309000 EMER RETIRE 4' OF 3\" PM | 4000078523 | ANC32.0000.00207 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 176.13 | 2024-04-30 | 2024-04-30 | 2025-07-31 | 1900-01-03 | 1900-01-29 | 1905-07-16 | C_U139391
2621 |  | CNV-23026309100 EMER-INSTALL 4'OF 2\"PMM | 4000078525 | ANC32.0000.00208 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1804 | 2023-12-19 | 2023-12-19 | 2025-07-31 | 1900-01-11 | 1900-01-18 | 1905-07-15 | C_U139391
2621 |  | CNV-23026309200 EMER-RETIRE 4' OF 3\"PMP | 4000078527 | ANC32.0000.00208 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 269.86 | 2023-12-19 | 2023-12-19 | 2025-07-31 | 1900-01-11 | 1900-01-18 | 1905-07-15 | C_U139391
2621 |  | CNV-24026353800 INSTALL 180' OF 4\"PMMP | 4000076897 | ANC32.0000.00280 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 82257.59 | 2024-09-25 | 2024-10-01 | 2025-08-01 | 4 | 19 | 2025 | C_U139391
2621 |  | CNV-24026353900 RETIRE 164' OF 4\"CSMP M | 4000076920 | ANC32.0000.00280 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 109.38 | 2024-10-01 | 2024-10-01 |  | 4 | 19 | 2025 | C_U139391
2621 |  | CNV-22026240800 INVESTIGATE MAINS | 4000079035 | PSI32.0000.00012 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 7908.12 | 2023-06-29 | 2023-06-30 |  | 1900-01-05 | 1900-01-29 | 1905-07-15 | C_U139391
2621 | LEXINGTON | CNV-22026243500 RETIRE RECORDING GAUGE | 4000079037 | SUP32.0002.00001 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-12-01 | 2023-12-01 |  | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2621 |  | CNV-22026227500 PS&I BRANNON RD RELO | 4000079111 | PSI32.0000.00010 | TECO JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL REV | PSI | 0 | 8676.77 | 2023-12-28 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2621 |  | CNV-24026355400 EMER-INSTALL 2' OF 2\"PM | 4000076060 | ANC32.0000.00281 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 29.54 | 2025-10-31 | 2025-10-31 | 2025-08-01 | 6 | 11 | 2026 | C_U139391
2621 |  | CNV-24026355500 EMER-RETIRE 2' OF 2\"PAM | 4000076062 | ANC32.0000.00281 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 7.3 | 2025-10-31 | 2025-10-31 | 2025-08-01 | 6 | 11 | 2026 | C_U139391
2621 | LEXINGTON | CNV-22026212500 REPLACE VALVES AT R-1084 | 4000079119 | ANC32.0000.00115 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 5700.95 | 2023-09-27 | 2023-09-30 | 2025-07-30 | 1900-01-08 | 1900-01-29 | 1905-07-15 | C_U139391
2633 | HAROLD | CNV-22026218600 INSTALL NEW 1ST CUT REGU | 4000079145 | ANC32.0000.00291 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 2733.71 | 2023-12-01 | 2023-12-01 | 2025-07-31 | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2633 | HAROLD | CNV-22026218700 RETIRE 1ST CUT REGULATOR | 4000079147 | ANC32.0000.00291 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 1618.6 | 2023-12-01 | 2023-12-01 | 2025-07-31 | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2621 |  | CNV-23026246401 INSTALL 3100' OF 2\"PMMP | 4000079233 | BET32.0000.00001 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 665.82 | 2023-03-08 | 2023-06-01 |  | 1900-01-05 | 1899-12-31 | 1905-07-15 | C_U139391
2621 |  | CNV-23026248900 INSTALL 100' OF 2\"PMMP | 4000079235 | BET32.0000.00006 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-08-28 | 2023-09-01 |  | 1900-01-08 | 1899-12-31 | 1905-07-15 | C_U139391
2621 |  | CNV-23026251800 RETIRE 900' OF 2\"CSHP M | 4000079237 | GRT32.0000.00069 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 5320.14 | 2023-12-01 | 2023-12-01 | 2025-07-30 | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2621 |  | CNV-23026254400 INSTALL 420' OF 6\"PMMP | 4000079238 | PIG32.0000.00004 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-09-01 | 2023-09-01 |  | 1900-01-08 | 1900-01-29 | 1905-07-15 | C_U139391
2621 |  | CNV-24026356000 INSTALL 475' OF 2\\\PM. | 4000076928 | ANC32.0000.00282 | REL GMPS MANC NMAT PRC SETC | NEW | MAI | 0 | 111063.73 | 2025-10-31 | 2025-12-01 |  | 12 | 1 | 2025 | C_U139391
2621 |  | CNV-24026356200 INSTALL NEW 4\" CRITICAL | 4000076064 | ANC32.0000.00283 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1175.54 | 2024-10-14 | 2024-10-15 | 2025-08-01 | 4 | 16 | 2026 | C_U139391
2621 |  | CNV-23026263000 INSTALL 5875' OF 2\"/4\" | 4000079264 | ANC32.0000.00035 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 223134.97 | 2023-06-02 | 2023-11-01 | 2025-07-30 | 1900-01-10 | 1899-12-31 | 1905-07-15 | C_U139391
2621 |  | CNV-23026263400 INSTALL 40'-4\" PMMP | 4000079266 | ANC32.0000.00217 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-10-25 | 2023-10-31 |  | 1900-01-09 | 1900-01-30 | 1905-07-15 | C_U139391
2621 |  | CNV-24026356300 RETIRE 4\" POLY VALVE C1 | 4000076066 | ANC32.0000.00283 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 5606.01 | 2025-08-29 | 2025-08-31 | 2025-08-01 | 4 | 16 | 2026 | C_U139391
2621 |  | CNV-23026265100 INSTALL 10'-3\"PMLP | 4000079270 | ANC32.0000.00221 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 140835.81 | 2023-11-22 | 2023-11-30 |  | 1900-01-10 | 1900-01-29 | 1905-07-15 | C_U139391
2621 |  | CNV-23026265200 RETIRE 10'-3\" BSLP | 4000079272 | ANC32.0000.00221 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-06-02 | 2023-06-02 |  | 1900-01-10 | 1900-01-29 | 1905-07-15 | C_U139391
2621 |  | CNV-23026267200 INSTALL 60'-4\" PMLP | 4000079274 | ANC32.0000.00222 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 16588.53 | 2024-02-12 | 2024-02-12 | 2025-07-31 | 1900-01-05 | 1900-01-29 | 1905-07-16 | C_U139391
2621 |  | CNV-23026267300 RETIRE ~60'-4\" BSLP | 4000079276 | ANC32.0000.00222 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 136.25 | 2023-11-30 | 2023-11-30 | 2025-07-31 | 1900-01-05 | 1900-01-29 | 1905-07-16 | C_U139391
2621 |  | CNV-23026267800 INSTALL 580' OF 2\"PMMP | 4000079278 | GRT32.0000.00037 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 859.74 | 2023-06-08 | 2023-06-19 |  | 1900-01-05 | 1900-01-18 | 1905-07-15 | C_U139391
2629 |  | CNV-24026316000 EMER - INSTALL 2'-3\" PM | 4000079294 | ANC32.0000.00055 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6325.04 | 2024-01-16 | 2024-01-16 |  | 1899-12-31 | 1900-01-28 | 1905-07-16 | C_U139391
2621 |  | CNV-24026357000 EMER-INSTALL 50' OF 4\"P | 4000076116 | ANC32.0000.00285 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 8511.32 | 2025-11-24 | 2025-11-30 | 2025-08-01 | 7 | 13 | 2026 | C_U139391
2623 |  | CNV-24026317300 INSTALL 270'-2\" PMMP | 4000079298 | GRT32.0000.00050 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 18665.67 | 2024-04-26 | 2024-04-30 | 2025-07-31 | 1900-01-03 | 1900-01-29 | 1905-07-16 | C_U139391
2621 |  | CNV-23026268400 INSTALL 2000' OF 2\"PMMP | 4000079300 | GRT32.0000.00088 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-05-04 | 2023-05-31 |  | 1900-01-04 | 1900-01-30 | 1905-07-15 | C_U139391
2621 |  | CNV-24026357100 EMER-RETIRE 50' OF 4\"BS | 4000076118 | ANC32.0000.00285 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 4851.43 | 2025-11-26 | 2025-11-30 | 2025-08-01 | 7 | 13 | 2026 | C_U139391
2621 |  | CNV-23026272200 INSTALL 200' OF 2\"PMMP | 4000079303 | GRT32.0000.00039 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 319.22 | 2023-06-06 | 2023-06-15 |  | 1900-01-05 | 1900-01-26 | 1905-07-15 | C_U139391
2621 |  | CNV-23026272600 INSTALL 875' OF 2\"PMMP | 4000079305 | GRT32.0000.00089 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-08-14 | 2023-08-18 |  | 1900-01-07 | 1900-01-17 | 1905-07-15 | C_U139391
2621 |  | CNV-23026272700 EMER - INSTALL 5'-2\" PM | 4000079307 | ANC32.0000.00042 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-04-25 | 2023-04-25 |  | 1900-01-03 | 1900-01-24 | 1905-07-15 | C_U139391
2621 |  | CNV-23026272901 INSTALL 2500' OF 2\"PMMP | 4000079309 | GRT32.0000.00090 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 98246.22 | 2024-02-01 | 2024-03-22 | 2025-07-31 | 1900-01-02 | 1900-01-21 | 1905-07-16 | C_U139391
2621 |  | CNV-23026273300 INSTALL 290' OF 4\" PMMP | 4000079311 | ANC32.0000.00043 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2614.92 | 2023-12-14 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2621 |  | CNV-23026274301 INSTALL 3400' OF 2\"PMMP | 4000079313 | GRT32.0000.00091 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 14303.12 | 2023-07-26 | 2023-08-11 | 2025-07-30 | 1900-01-09 | 1900-01-26 | 1905-07-15 | C_U139391
2621 |  | CNV-23026277300 INSTALL 265' OF 6\"PMMP | 4000079315 | PIG32.0000.00040 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 11880.36 | 2023-08-22 | 2023-09-01 | 2025-07-30 | 1900-01-08 | 1899-12-31 | 1905-07-15 | C_U139391
2621 |  | CNV-23026277400 RETIRE 285' OF 6\"PMMP M | 4000079317 | PIG32.0000.00040 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 439.64 | 2023-09-01 | 2023-09-01 | 2025-07-30 | 1900-01-08 | 1899-12-31 | 1905-07-15 | C_U139391
2621 |  | CNV-23026278200 EMER-INSTALL 185' OF 4\" | 4000079319 | ANC32.0000.00044 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 205.8 | 2024-01-29 | 2024-01-31 |  | 1900-01-08 | 1900-01-05 | 1905-07-16 | C_U139391
2623 |  | CNV-24026362000 EMER-INSTALL 3' OF 3\"PM | 4000079439 | ANC32.0000.00286 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 6505.22 | 2025-10-31 | 2025-10-31 |  | 6 | 27 | 2026 | C_U139391
2629 |  | PSI-SMRP Broadway Av P2 ROW-Cynthiana | 4000079321 | PSI32.0000.00018 | REL NMAT PRC SETC | NEW FCMP | PSI | 0 | 41920.4 | 2025-12-30 | 2025-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-17 | C_U139391
2623 |  | CNV-24026362100 EMER-RETIRE 2' OF 3\"PMP | 4000079461 | ANC32.0000.00286 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 3316 | 2025-10-31 | 2025-10-31 |  | 6 | 27 | 2026 | C_U139391
2621 |  | CNV-24026365100 EMER-RETIRE 10' - 2\" PM | 4000073976 | ANC32.0000.00287 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 7.6 | 2024-12-31 | 2024-12-31 | 2025-08-01 | 12 | 31 | 2024 | C_U139391
2631 |  | CNV-24026320800 EMER - INSTALL 5'-3\" PM | 4000079325 | ANC32.0000.00255 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 10006.55 | 2024-03-28 | 2024-03-30 | 2025-07-31 | 1900-01-02 | 1900-01-29 | 1905-07-16 | C_U139391
2631 |  | CNV-24026320900 EMER RETIRE 5'-3\" PIP | 4000079327 | ANC32.0000.00255 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 338.64 | 2024-03-28 | 2024-03-30 | 2025-07-31 | 1900-01-02 | 1900-01-29 | 1905-07-16 | C_U139391
2621 |  | CNV-24026365000 EMER-INSTALL 10' - 2\" P | 4000075863 | ANC32.0000.00287 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2308.37 | 2024-12-30 | 2024-12-31 | 2025-08-01 | 12 | 31 | 2024 | C_U139391
2623 |  | CNV-24026340800 EMER - INSTALL 15'-2\" P | 4000079331 | ANC32.0000.00069 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 523.95 | 2024-04-29 | 2024-05-01 | 2025-08-01 | 1900-01-02 | 1899-12-31 | 1905-07-17 | C_U139391
2631 |  | CNV-24026365300 EMER INSTALL 5\" OF 4\" | 4000079469 | ANC32.0000.00288 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 15339.42 | 2025-06-25 | 2025-06-30 | 2025-08-01 | 6 | 30 | 2025 | C_U139391
2629 |  | CNV-24026342300 EMER - RETIRE 267'-2\" P | 4000079335 | ANC32.0000.00111 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2666.67 | 2024-05-07 | 2024-05-09 |  | 1900-01-04 | 1900-01-16 | 1905-07-16 | C_U139391
2633 |  | CNV-24026342600 EMER ABANDON 200' OF 2\" | 4000079337 | ANC32.0000.00112 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 5142.92 | 2024-05-17 | 2024-05-20 |  | 1900-01-06 | 1900-01-16 | 1905-07-16 | C_U139391
2629 |  | CNV-24026343700 EMER - INSTALL 3'-3\" PM | 4000079339 | ANC32.0000.00070 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4126.3 | 2024-05-10 | 2024-05-17 |  | 1900-01-04 | 1900-01-16 | 1905-07-16 | C_U139391
2621 |  | CNV-23026278401 INSTALL 2300' OF 2\"/4\" | 4000079341 | GRT32.0000.00092 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 13917.31 | 2023-09-27 | 2023-10-31 | 2025-07-31 | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2621 |  | CNV-23026279100 INSTALL 300' OF 2\"PMIP | 4000079343 | GRT32.0000.00093 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 5117.78 | 2023-08-09 | 2023-08-11 | 2025-07-30 | 1900-01-07 | 1900-01-10 | 1905-07-15 | C_U139391
2621 |  | CNV-23026283200 INSTALL 480' OF 2\"PMMP | 4000079345 | PIG32.0000.00008 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 31110.85 | 2023-08-21 | 2023-09-01 | 2025-07-30 | 1900-01-08 | 1899-12-31 | 1905-07-15 | C_U139391
2621 |  | CNV-23026285400 RETIRE 300' OF 2\"PIP MA | 4000079347 | BET32.0000.00020 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 15489.39 | 2024-02-28 | 2024-03-01 | 2025-07-31 | 1900-01-02 | 1899-12-31 | 1905-07-16 | C_U139391
2621 |  | CNV-23026288401 INSTALL 5500' OF 4\"PMMP | 4000079349 | GRT32.0000.00046 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 32023.98 | 2024-02-12 | 2024-08-16 | 2025-08-01 | 1900-01-07 | 1900-01-15 | 1905-07-16 | C_U139391
2631 |  | CNV-24026365400 EMER RETIRE 5\" OF 4\" P | 4000079471 | ANC32.0000.00288 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 410.02 | 2025-06-30 | 2025-06-30 | 2025-08-01 | 6 | 30 | 2025 | C_U139391
2621 |  | ELM TREE 2025 SMRP CROSSBORE CNV-2402636 | 4000076485 | ANC32.0000.00289 | REL GMPS MANC PRC SETC | COCO ADJ FCMP | MAI | 55039.42 | 275901.46 | 2025-11-21 | 2025-12-31 |  | 12 | 31 | 2025 | C_U139391
2621 |  | CNV-23026292000 INSTALL 2450' OF 2\"PMMP | 4000079355 | GRT32.0000.00047 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 43855.25 | 2024-02-12 | 2024-03-01 | 2025-07-31 | 1900-01-02 | 1899-12-31 | 1905-07-16 | C_U139391
2621 |  | CNV-23026292501 INSTALL 800' OF 2-4\" PM | 4000079357 | PIG32.0000.00027 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 8382.25 | 2023-10-18 | 2023-10-31 |  | 1900-01-10 | 1900-01-29 | 1905-07-16 | C_U139391
2621 |  | CNV-23026293700 INSTALL 74'-2\" PMMP | 4000079359 | PIG32.0000.00037 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 17676.74 | 2024-06-05 | 2024-06-30 | 2025-07-31 | 1900-01-05 | 1900-01-29 | 1905-07-16 | C_U139391
2621 |  | CNV-23026293800 RETIRE 88'-2\"&4\" PMMP | 4000079361 | PIG32.0000.00037 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 9244 | 2024-06-28 | 2024-06-30 | 2025-07-31 | 1900-01-05 | 1900-01-29 | 1905-07-16 | C_U139391
2621 |  | CNV-23026294800 INSTALL 225' OF 2\"PMMP | 4000079363 | GRT32.0000.00014 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 17369.41 | 2023-12-14 | 2023-12-18 | 2025-07-31 | 1900-01-11 | 1900-01-17 | 1905-07-15 | C_U139391
2621 |  | CNV-23026296000 INSTALL 220' OF 2\" PMMP | 4000079365 | GRT32.0000.00015 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 29995.76 | 2024-01-26 | 2024-02-01 | 2025-07-31 | 1900-01-01 | 1899-12-31 | 1905-07-16 | C_U139391
2621 |  | CNV-23026296200 INSTALL 1429'-6\" PMMP | 4000079367 | PIG32.0000.00026 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 566587.69 | 2024-01-15 | 2024-03-21 | 2025-07-31 | 1900-01-05 | 1900-01-27 | 1905-07-16 | C_U139391
2621 |  | CNV-23026296300 RETIRE 1479'-6\" CS&PMMP | 4000079369 | PIG32.0000.00026 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 577.39 | 2024-03-21 | 2024-03-21 | 2025-07-31 | 1900-01-03 | 1900-01-25 | 1905-07-16 | C_U139391
2621 |  | CNV-23026296800 EMER - INSTALL 40'-4\" P | 4000079371 | PIG32.0000.00005 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 20616.63 | 2023-12-21 | 2023-12-30 | 2025-08-12 | 1900-01-11 | 1900-01-29 | 1905-07-15 | C_U139391
2621 |  | CNV-23026297200 EMER - INSTALL 13'-2\" P | 4000079373 | ANC32.0000.00201 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 211.73 | 2023-10-06 | 2023-10-09 | 2025-07-31 | 1900-01-09 | 1900-01-11 | 1905-07-15 | C_U139391
2621 |  | CNV-23026297300 EMER - RETIRE 2'-2\" PMP | 4000079375 | ANC32.0000.00201 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 5935.69 | 2023-10-09 | 2023-10-09 | 2025-07-31 | 1900-01-09 | 1900-01-11 | 1905-07-15 | C_U139391
2621 |  | CNV-23026299700 INSTALL 325' OF 2\"PMMP | 4000079377 | GRT32.0000.00018 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 26876.53 | 2024-04-22 | 2024-04-26 | 2025-07-31 | 1900-01-03 | 1900-01-25 | 1905-07-16 | C_U139391
2621 |  | CNV-23026302701 INSTALL 2700' OF 2\"/4\" | 4000079379 | GRT32.0000.00086 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 29483.1 | 2024-05-13 | 2024-07-01 | 2025-07-31 | 1900-01-06 | 1899-12-31 | 1905-07-16 | C_U139391
2631 |  | CNV-24026367000 EMER INSTALL 5'-2\" PMMP | 4000079475 | ANC32.0000.00290 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 5780.2 | 2024-10-09 | 2024-10-09 | 2025-08-01 | 10 | 10 | 2024 | C_U139391
2631 |  | CNV-24026367100 EMER RETIRE 5'-2\" PMMP | 4000079478 | ANC32.0000.00290 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 451.33 | 2024-10-10 | 2024-10-10 | 2025-08-01 | 10 | 10 | 2024 | C_U139391
2633 |  | CNV-24026347600 EMER - INSTALL 7'-2\" PM | 4000079385 | ANC32.0000.00072 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4739.55 | 2024-06-10 | 2024-06-10 |  | 1900-01-05 | 1900-01-09 | 1905-07-16 | C_U139391
2621 |  | CNV-24026376700 EMER - INSTALL 3'-2\" PM | 4000075871 | ANC32.0000.00292 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 2391.9 | 2025-08-28 | 2025-08-31 | 2025-08-01 | 8 | 31 | 2025 | C_U139391
2621 |  | CNV-24026376800 EMER - RETIRE 3'-2\" PMP | 4000075873 | ANC32.0000.00292 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 6.11 | 2025-08-29 | 2025-08-31 |  | 8 | 31 | 2025 | C_U139391
2629 |  | CNV-25026379000 EMER - INSTALL 9'-2\" PM | 4000080041 | ANC32.0000.00293 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 0 | 2025-01-02 | 2025-01-02 |  | 1 | 13 | 2025 | C_U139391
2629 |  | CNV-25026379101 EMER - RETIRE 9'-2\" PMP | 4000080043 | ANC32.0000.00293 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 2522.61 | 2025-01-02 | 2025-01-02 |  | 1 | 13 | 2025 | C_U139391
2631 |  | CNV-24026349500 INSTALL 40'-12\\\ CSMP. | 4000079394 | ANC32.0000.00273 | REL MANC NMAT PRC SETC | NEW REV | MAI | 0 | 83922.03 | 2024-08-31 | 2024-08-31 |  | 1900-01-03 | 1900-01-19 | 1905-07-17 | C_U139391
2631 |  | CNV-24026349600 RETIRE ~40'-12\" CSHP | 4000079396 | ANC32.0000.00273 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 233.2 | 2024-08-31 | 2024-08-31 |  | 1900-01-03 | 1900-01-19 | 1905-07-17 | C_U139391
2623 |  | CNV-25026381300 EMER-INSTALL 180' OF 4\" | 4000080045 | ANC32.0000.00294 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 73.05 | 2025-01-28 | 2026-03-31 | 2025-08-01 | 11 | 15 | 2026 | C_U139391
2621 |  | CNV-24026313700 INVESTIGATE HP EASEMENT/ | 4000079399 | PSI32.0000.00004 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 9480.15 | 2024-12-31 | 2024-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-16 | C_U139391
2623 |  | CNV-25026381400 EMER-RETIRE 180' OF 6\"B | 4000080047 | ANC32.0000.00294 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 34.48 | 2025-01-28 | 2026-03-31 | 2025-08-03 | 11 | 15 | 2026 | C_U139391
2621 |  | CNV-25026385100 EMER-INSTALL 4' OF 4\"PM | 4000076560 | ANC32.0000.00295 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 6298.29 | 2025-06-30 | 2025-06-30 | 2025-08-03 | 7 | 1 | 2025 | C_U139391
2621 |  | CNV-25026385200 EMER-RETIRE 4' OF 4\"PMP | 4000076562 | ANC32.0000.00295 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 1275.57 | 2025-01-29 | 2025-01-29 |  | 7 | 1 | 2025 | C_U139391
2621 |  | CNV-25026395600 EMER-INSTALL 3' OF 3\"PM | 4000077161 | ANC32.0000.00296 | REL CSER NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 0 | 2026-06-30 | 2026-06-30 |  | 2 | 18 | 2027 | C_U139391
2621 |  | CNV-25026395700 EMER-RETIRE 3' OF 3\"PMP | 4000077163 | ANC32.0000.00296 | REL CSER NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 384.19 | 2026-06-30 | 2026-06-30 |  | 2 | 18 | 2027 | C_U139391
2632 |  | CNV-24026352800 INSTALL SS FITTING | 4000079426 | ANC32.0000.00279 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1303.48 | 2024-08-01 | 2024-08-02 | 2025-08-01 | 1900-01-07 | 1900-01-04 | 1905-07-16 | C_U139391
2632 |  | CNV-24026352900 RETIRE 4'-3\"&4\"CSMP | 4000079428 | ANC32.0000.00279 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1085.55 | 2024-08-02 | 2024-08-02 | 2025-08-01 | 1900-01-07 | 1900-01-04 | 1905-07-16 | C_U139391
2631 |  | CNV-24026335700 INVESTIGATE EASEMENTS FO | 4000079435 | PSI32.0000.00021 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 7231.22 | 2024-12-31 | 2024-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-16 | C_U139391
2632 | MAYSVILLE | CNV-23026258300 INSTALL VRG CONTROLLER | 4000079947 | ANC32.0000.00297 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 9623.8 | 2024-12-23 | 2024-12-31 | 2025-07-31 | 12 | 31 | 2024 | C_U139391
2632 | MAYSVILLE | CNV-23026258400 RETIRE BRISTOL CONTROL U | 4000081095 | ANC32.0000.00297 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 600.77 | 2024-12-31 | 2024-12-31 | 2025-08-01 | 12 | 31 | 2024 | C_U139391
2621 | LEXINGTON | CNV-24026340000 EMER-INSTALL NEW PF REGU | 4000076965 | ANC32.0000.00299 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 1735.02 | 2024-10-01 | 2024-10-01 | 2025-07-31 | 10 | 1 | 2024 | C_U139391
2621 | LEXINGTON | CNV-24026340100 EMER-RETIRE PF REGULATOR | 4000076967 | ANC32.0000.00299 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 1087.64 | 2024-10-01 | 2024-10-01 | 2025-07-31 | 10 | 1 | 2024 | C_U139391
2629 | IRVINE | CNV-24026359000 EMER - INSTALL NEW REGUL | 4000080339 | ANC32.0000.00300 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 20764.74 | 2024-09-23 | 2024-09-28 |  | 9 | 28 | 2024 | C_U139391
2629 | IRVINE | CNV-24026359100 EMER - RETIRE REGULATOR | 4000080360 | ANC32.0000.00300 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 1814.05 | 2024-09-30 | 2024-09-30 | 2025-08-02 | 9 | 30 | 2024 | C_U139391
2629 |  | CNV-23026301900 RETIRE RECTIFIER/GROUND | 4000074690 | ANC32.0000.00301 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 71.7 | 2024-12-31 | 2024-12-31 | 2025-07-31 | 12 | 31 | 2024 | C_U139391
2629 |  | CNV-23026248100 INSTALL GROUND BED | 4000077746 | ANC32.0000.00301 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 68163.34 | 2023-11-06 | 2024-12-31 | 2025-07-31 | 12 | 31 | 2024 | C_U139391
2629 |  | CNV-24026368000 EMER - INSTALL 5'-2\" PM | 4000079504 | ANC32.0000.00302 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3448.45 | 2024-11-01 | 2024-11-01 |  | 11 | 1 | 2024 | C_U139391
2629 |  | CNV-24026368100 EMER - RETIRE 5'-2\" PMM | 4000079506 | ANC32.0000.00302 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 204.97 | 2024-11-01 | 2024-11-01 | 2025-08-01 | 11 | 1 | 2024 | C_U139391
2633 |  | Install 518'-4" PMIP | 4000085428 | ANC32.0000.00303 | CRTD MANC NTUP PRC | EST REV WENV | MAI | 426369.71 | 0 | 2025-07-14 | 2025-08-08 |  |  |  |  | U122858
2631 |  | ANC - SMRP RIDGEWAY DRIVE - ASHLAND | 4000087673 | ANC32.0000.00304 | REL PCNF ESTC GMPS MANC PPRT PRC SETC | SCHD | MAI | 612331.21 | 934464.53 | 2025-08-12 | 2026-12-31 | 2026-03-12 |  |  |  | U141016
2623 |  | ANC-CAPITOL AVE SMRP-FRANKFORT | 4000085545 | ANC32.0000.00305 | REL ESTC GMPS MANC PRC SETC SKKP | NEW ADJ | MAI | 871145.84 | 7694.5 | 2026-07-08 | 2026-12-31 |  | 12 | 31 | 2026 | U132703
2631 |  | Mavity Odorant Injection Point Replaceme | 4000085987 | ANC32.0000.00306 | REL ESTC MACM PRC SETC | NEW MIFE NSFS | MAI | 1.67 | 0 | 2025-07-16 | 2025-07-16 |  |  |  |  | U136909
2621 |  | ANC-ROSALIE HP SMRP-LEXINGTON | 4000085778 | ANC32.0000.00307 | REL ESTC MANC PRC SETC | NEW NSFS WENG | MAI | 2482476.25 | 5022.1 | 2026-10-31 | 2027-12-31 |  |  |  |  | U127466
2623 |  | ANC - Cardinal Ave SMRP | 4000085542 | ANC32.0000.00308 | REL PCNF ESTC MANC PRC SETC | NEW ADJ | MAI | 3326316 | 2904.09 | 2026-10-31 | 2027-12-31 | 2026-03-04 |  |  |  | U132703
2621 |  | RELOCATION - ARMSTRONG MILL RD | 4000086377 | ANC32.0000.00310 | CRTD MANC NMAT PRC | NEW CAN NSFS RCFO | MAI | 0 | 0 | 2025-12-30 | 2025-12-31 |  | 12 | 31 | 2025 | U132703
2621 |  | RELOCATION - ARMSTRONG MILL RD | 4000086378 | ANC32.0000.00310 | CRTD MANC NMAT PRC | NEW CAN NSFS RCFO | MAI | 0 | 0 | 2025-12-30 | 2025-12-31 |  | 12 | 31 | 2025 | U132703
2621 |  | RELOCATION - ARMSTRONG MILL RD | 4000086379 | ANC32.0000.00310 | CRTD MANC NMAT PRC | PLN CAN NSFS RCFO | MAI | 0 | 0 | 2025-12-30 | 2025-12-31 |  | 12 | 31 | 2025 | U132703
2621 |  | RELOCATION - ARMSTRONG MILL RD | 4000079630 | PSI32.0000.00035 | TECO JBFI MANC NMAT NTUP PRC SETC | NEW CAN FCMP RECL | PSI | 0 | 10616.54 | 2025-12-30 | 2025-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-17 | C_U139391
2621 |  | CNV-25026397600 INVESTIGATE CONFLICTS | 4000079632 | PSI32.0000.00041 | TECO JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL | PSI | 0 | 7735.95 | 2025-12-30 | 2025-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-17 | C_U139391
2623 |  | CNV-24026309500 INSTALL 215'-2\" PMMP | 4000079638 | GRT32.0000.00026 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 10703.61 | 2024-05-22 | 2024-05-27 | 2025-07-31 | 1900-01-04 | 1900-01-26 | 1905-07-16 | C_U139391
2629 |  | CNV-24026309800 INSTALL 75' - 2\" PMMP | 4000079660 | GRT32.0000.00025 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 7578.53 | 2024-02-13 | 2024-02-15 | 2025-08-12 | 1900-01-01 | 1900-01-14 | 1905-07-16 | C_U139391
2621 |  | RELOCATION - ARMSTRONG MILL RD | 4000086387 | ANC32.0000.00310 | CRTD MANC NMAT PRC | NEW CAN NSFS RCFO | MAI | 0 | 0 | 2025-12-30 | 2025-12-31 |  | 12 | 31 | 2025 | U132703
2621 |  | RELOCATION - ARMSTRONG MILL RD | 4000086388 | ANC32.0000.00310 | CRTD MANC NMAT PRC | NEW CAN NSFS RCFO | MAI | 0 | 0 | 2025-12-30 | 2025-12-31 |  | 12 | 31 | 2025 | U132703
2623 |  | CNV-24026311500 EMER-RETIRE 350' OF 4\"P | 4000079666 | ANC32.0000.00109 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1508.07 | 2024-01-10 | 2024-01-10 |  | 1899-12-31 | 1900-01-09 | 1905-07-16 | C_U139391
2623 |  | CNV-24026312200 INSTALL 230'-2\" PMMP | 4000079669 | GRT32.0000.00048 | REL PCNF GMPS NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 20413.05 | 2024-06-12 | 2024-06-14 | 2025-07-31 | 1900-01-05 | 1900-01-13 | 1905-07-16 | C_U139391
2621 |  | RELOCATION - ARMSTRONG MILL RD | 4000086390 | ANC32.0000.00310 | CRTD MANC NMAT PRC | NEW CAN NSFS RCFO | MAI | 0 | 0 | 2025-12-30 | 2025-12-31 |  | 12 | 31 | 2025 | U132703
2629 |  | CNV-24026313400 REPLACE EXISTING RECTIFI | 4000079673 | ANC32.0000.00139 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3648.09 | 2024-02-28 | 2024-02-28 | 2025-07-31 | 1900-01-01 | 1900-01-27 | 1905-07-16 | C_U139391
2621 |  | RELOCATION - ARMSTRONG MILL RD | 4000086391 | ANC32.0000.00310 | CRTD MANC NMAT PRC | NEW CAN NSFS RCFO | MAI | 0 | 0 | 2025-12-30 | 2025-12-31 |  | 12 | 31 | 2025 | U132703
2623 |  | CNV-24026341700 INVESTIGATE ROW/EASEMENT | 4000086426 | ANC32.0000.00310 | CRTD MANC NMAT PRC | NEW CAN NSFS RCFO | MAI | 0 | 0 | 2026-12-31 | 2026-12-31 |  | 12 | 31 | 2026 | U132703
2629 |  | CNV-24026354100 EMER - RETIRE 308'-2\" P | 4000079760 | BET32.0000.00017 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1102.7 | 2024-07-17 | 2024-07-18 |  | 1900-01-06 | 1900-01-17 | 1905-07-16 | C_U139391
2623 |  | ANC - MAIN ST HP - FRANKFORT (JIM BEAM) | 4000086454 | ANC32.0000.00310 | REL MANC NMAT PRC SETC | NEW CAN NSFS RCFO | MAI | 0 | 2379.02 | 2026-10-31 | 2027-12-31 |  |  |  |  | U132703
2631 |  | Replace Coalton Rectifier - 25026408100 | 4000086412 | ANC32.0000.00311 | TECO ESTC MANC PRC SETC | NPRG ADJ FCMP MIFE | MAI | 5858.32 | 1714.45 | 2025-07-24 | 2025-10-24 |  |  |  |  | U141016
2623 |  | ANC - E College St SMRP | 4000086464 | ANC32.0000.00312 | REL PCNF ESTC MANC PRC SETC | NEW ADJ | MAI | 3222324.31 | 409.28 | 2026-10-31 | 2027-12-31 | 2026-03-06 |  |  |  | U132703
2621 |  | IDLE HOUR PARK RECTIFIER | 4000086939 | ANC32.0000.00313 | CRTD ESTC MANC NTUP PRC | NEW ADJ REV | MAI | 151555.84 | 0 | 2025-07-30 | 2026-07-30 |  |  |  |  | U145347
2631 |  | ANC - SMRP RAILROAD STREET - RUSSELL | 4000087675 | ANC32.0000.00314 | REL ESTC MANC PRC SETC | NEW NSFS | MAI | 10240.24 | 10181.72 | 2025-08-12 | 2026-12-31 |  |  |  |  | U141016
2633 |  | Abandon ~279'-2" BSIP | 4000088050 | ANC32.0000.00316 | REL ESTC MANC PRC SETC | NPRG ADJ WARR WPWT | MAI | 2651.7 | 6303.25 | 2025-08-15 | 2025-11-28 |  |  |  |  | U122858
2629 |  | 2629-EMER 499 Indian mound-Mt Sterling | 4000088098 | ANC32.0000.00317 | REL ESTC MACM PRC SETC SKKP | NEW | MAI | 2723.68 | 0 | 2025-08-15 | 2025-12-31 |  |  |  |  | U128885
2631 |  | BRUCE DRIVE WO RE-CREATE FOR ACCOUNTING | 4000088357 | ANC32.0000.00318 | CRTD MANC PRC | EST | MAI | 0.59 | 0 | 2025-08-19 | 2025-08-19 |  |  |  |  | U141016
2621 |  | ARMSTRONG MILL RELO | 4000086395 | ANC32.0000.00319 | REL MANC PRC SETC | NEW RCFO | MAI | 59157.42 | 1212.65 | 2025-12-30 | 2025-12-31 |  | 12 | 31 | 2026 | U132703
2621 |  | ANC - NEWCIRCLELEAK - LEXINGTON | 4000087349 | ANC32.0000.00320 | REL PCNF ESTC GMPS MANC PRC SETC | NEW FCMP | MAI | 163562.32 | 486838.19 | 2025-08-06 | 2025-08-06 | 2026-03-04 | 12 | 31 | 2026 | U127466
2621 |  | ANC-Richmond Rd Phase III SMRP-Lexington | 4000090243 | ANC32.0000.00321 | REL ESTC CSER MANC PRC SETC | NEW | MAI | 167196.98 | 1083.28 | 2026-12-31 | 2026-12-31 |  |  |  |  | U938437
2621 | LEXINGTON | STA-Richmond Rd Ph III-Lexington | 4000094767 | ANC32.0000.00321 | CRTD MANC NMAT NTUP PRC | EST | STA | 356.64 | 0 | 2025-12-04 | 2025-12-04 |  |  |  |  | U938437
2623 |  | SMRP -PAUL SAWYIER DR | 4000090540 | ANC32.0000.00322 | REL ESTC GMPS MANC PRC SETC | SCHD ADJ | MAI | 452957.48 | 862363.9 | 2025-09-17 | 2025-09-17 |  | 3 | 13 | 2026 | U132703
2623 |  | ANC-GOVERNORS MANSION SMRP-FRANKFORT | 4000090547 | ANC32.0000.00323 | REL ESTC MANC PRC SETC SKKP | NEW ADJ | MAI | 279264.65 | 3332.41 | 2025-09-17 | 2025-09-17 |  | 12 | 31 | 2026 | U132703
2629 |  | CNV-24026337600 INSTALL 30'-2\" PMMP | 4000079811 | PIG32.0000.00044 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 10081.09 | 2024-05-24 | 2024-05-31 | 2025-07-31 | 1900-01-04 | 1900-01-30 | 1905-07-16 | C_U139391
2629 |  | CNV-24026337700 RETIRE 20'-2\" PMMP | 4000079813 | PIG32.0000.00044 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 19.74 | 2024-05-31 | 2024-05-31 |  | 1900-01-04 | 1900-01-30 | 1905-07-16 | C_U139391
2631 |  | CNV-24026337800 INSTALL 8\" SS | 4000079815 | ANC32.0000.00001 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2024-04-30 | 2024-04-30 |  | 1900-01-03 | 1900-01-29 | 1905-07-16 | C_U139391
2629 |  | CNV-24026337900 INSTALL 2,550'-2\" PMMP | 4000079817 | GRT32.0000.00085 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 51672.95 | 2024-06-10 | 2024-06-30 | 2025-07-31 | 1900-01-05 | 1900-01-29 | 1905-07-16 | C_U139391
2621 |  | Georgetown Street Anode Bed Install | 4000090524 | ANC32.0000.00324 | CRTD ESTC MANC NTUP PRC | NEW ADJ | MAI | 4755.23 | 0 | 2025-09-17 | 2025-09-17 |  |  |  |  | U145347
2631 |  | CNV-24026356500 EMER - INSTALL 2'-2\" PM | 4000079841 | ANC32.0000.00284 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3486.96 | 2024-08-29 | 2024-09-01 |  | 1900-01-08 | 1899-12-31 | 1905-07-16 | C_U139391
2631 |  | CNV-24026356600 EMER - RETIRE 2'-2\" PIP | 4000079843 | ANC32.0000.00284 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 49.72 | 2024-08-30 | 2024-09-01 | 2025-08-01 | 1900-01-08 | 1899-12-31 | 1905-07-16 | C_U139391
2632 |  | ANC- Maysville BSHP SMRP - Maysville | 4000090558 | ANC32.0000.00325 | REL PCNF GMPS MANC NMAT PRC SETC | NEW RCFO WENV | MAI | 365.12 | 49388.39 | 2026-06-20 | 2026-12-31 | 2026-02-19 | 12 | 31 | 2026 | U938437
2629 | WINCHESTER | ANC-Mutual Ave Land ABN-Winchester | 4100801141 | ANC32.0000.00326 | REL ESTC MACM PRC SETC | NEW | LND | 12527.5 | 10389.92 | 2025-09-19 | 2025-12-31 |  | 12 | 31 | 2025 | U128885
2629 |  | ANC-SMRP Broadway Av P2-Cynthiana | 4000090920 | ANC32.0000.00327 | CRTD MANC NTUP PRC SKKP | NEW REV | MAI | 285883.65 | 0 | 2026-01-01 | 2026-12-31 |  | 12 | 31 | 2026 | U128885
2629 |  | ANC-SMRP Broadway Av P2-Cynthiana | 4000095394 | ANC32.0000.00327 | REL PCNF ESTC GMPS MANC PRC SETC SKKP | NPRG ADJ MIFE | MAI | 2639748.16 | 2510760.62 | 2025-12-29 | 2026-10-02 | 2026-03-12 | 10 | 2 | 2026 | U128885
2629 |  | ANC-SMRP Broadway Av P2 Land-Cynthiana | 4100828092 | ANC32.0000.00327 | REL ESTC MACM PRC SETC | NEW | LND | 6263.7 | 750 | 2026-01-05 | 2026-12-31 |  | 12 | 31 | 2026 | U128885
2629 |  | ANC-SMRP W Lexington Av-Winchester | 4000090923 | ANC32.0000.00328 | REL MANC PRC SETC | NEW ADJ NSFS RCFO WLND WPMT | MAI | 4461116.06 | 27114.24 | 2026-05-06 | 2027-12-31 |  | 12 | 31 | 2027 | U128885
2629 |  | ANC-SMRP Evergreen Dr-Irvine | 4000090925 | ANC32.0000.00329 | REL PCNF GMPS MANC PRC SETC | SCHD | MAI | 2413451.55 | 1422468.38 | 2026-01-01 | 2026-12-31 | 2026-03-23 | 12 | 31 | 2027 | U128885
2623 |  | CNV-24026360200 EMER-INSTALL 3' OF 2\"PM | 4000079859 | ANC32.0000.00079 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2024-08-21 | 2024-08-21 |  | 1900-01-08 | 1900-01-02 | 1905-07-16 | C_U139391
2623 |  | ANC-CLEVELAND AVE. SMRP - VERSAILLES | 4000092292 | ANC32.0000.00330 | REL PCNF ESTC GMPS MANC PRC SETC | NPRG MIFE | MAI | 202788.23 | 2324364.56 | 2025-10-21 | 2025-10-21 | 2026-03-13 | 12 | 31 | 2026 | U127466
2621 |  | ANC-DOVER ROAD SMRP-LEX | 4000095269 | ANC32.0000.00331 | REL ESTC MANC PRC SETC | NEW NSFS WENG | MAI | 10.34 | 10776.81 | 2026-10-31 | 2027-12-31 |  |  |  |  | U127466
2621 | LEXINGTON | CNV-23026254000 RETIRE PRESSURE GAUGE | 4000079895 | ANC32.0000.00134 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-09-29 | 2023-10-01 |  | 1900-01-09 | 1899-12-31 | 1905-07-15 | C_U139391
2632 | MAYSVILLE | CNV-23026254100 RETIRE PRESSURE GAUGE | 4000079896 | ANC32.0000.00134 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-09-29 | 2023-10-01 |  | 1900-01-09 | 1899-12-31 | 1905-07-15 | C_U139391
2631 | GREENUP | CNV-23026254200 RETIRE RECORDING GAUGE | 4000079897 | ANC32.0000.00134 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-09-29 | 2023-10-01 |  | 1900-01-09 | 1899-12-31 | 1905-07-15 | C_U139391
2621 | LEXINGTON | CNV-23026254700 RETIRE PAPER GAUGE | 4000079898 | ANC32.0000.00134 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-12-01 | 2023-12-01 |  | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2621 | LEXINGTON | CNV-23026256201 INSTALL VRG CONTROLLERS | 4000079899 | GRT32.0000.00111 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 8134.45 | 2023-11-27 | 2023-12-01 |  | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2623 |  | CNV-21026101200 NEWTOWNNANNER FARM CHARG | 4000079909 | PSI32.0000.00011 | TECO JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL | PSI | 0 | 5557.13 | 2025-12-30 | 2025-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-17 | C_U139391
2621 |  | ANC-SAINT ANN SMRP 2026 - IDLE HOUR FINA | 4000092297 | ANC32.0000.00333 | REL PCNF ESTC GMPS MANC PRC SETC | NEW MIFE | MAI | 209584.94 | 529467.29 | 2025-10-21 | 2025-10-21 | 2026-03-04 | 12 | 31 | 2026 | U127466
2623 |  | CNV-23026256600 RETIRE PAPER GAUGE | 4000079940 | ANC32.0000.00134 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-12-01 | 2023-12-01 |  | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2631 | GREENUP | CNV-23026256700 RETIRE PAPER GAUGE | 4000079941 | ANC32.0000.00134 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-12-01 | 2023-12-01 |  | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2632 | MAYSVILLE | CNV-23026256800 RETIRE PAPER GAUGE | 4000079942 | ANC32.0000.00134 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-12-01 | 2023-12-01 |  | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2631 | WORTHINGTON | CNV-23026257300 RETIRE CHART | 4000079943 | SUP32.0002.00001 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 385.91 | 2023-12-01 | 2023-12-01 | 2025-07-30 | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2631 | ASHLAND | CNV-23026257600 RETIRE PAPER CHAT | 4000079944 | SUP32.0002.00001 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 575.02 | 2023-12-01 | 2023-12-01 | 2025-07-30 | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2631 | LOUISA | CNV-23026257800 RETIRE PAPER CHART | 4000079945 | SUP32.0002.00001 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 1139.64 | 2023-12-01 | 2023-12-01 | 2025-07-30 | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2632 | MAYSVILLE | CNV-23026258000 RETIRE PAPER CHART | 4000079946 | SUP32.0002.00001 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 555.74 | 2023-12-01 | 2023-12-01 | 2025-07-30 | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2631 |  | CREATE:NEED TO DEFINE EXISTING EASEMENTS | 4000091540 | ANC32.0000.00334 | CRTD MANC NMAT PRC | NEW NSFS RCFO | MAI | 0 | 0 | 2024-12-31 | 2024-12-31 |  | 12 | 31 | 2024 | U122858
2631 | LOUISA | CNV-23026259500 RETIRE PAPER CHART | 4000079948 | SUP32.0002.00001 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 347.03 | 2023-12-01 | 2023-12-01 | 2025-07-30 | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2623 | VERSAILLES | CNV-23026259700 RETIRE PAPER CHART | 4000079949 | SUP32.0002.00001 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-12-01 | 2023-12-01 |  | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2631 | LOUISA | CNV-23026259900 RETIRE PAPER CHART | 4000079950 | SUP32.0002.00001 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-12-01 | 2023-12-01 |  | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2631 | LOUISA | CNV-23026260100 RETIRE PAPER GAUGE | 4000079951 | SUP32.0002.00001 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-12-01 | 2023-12-01 |  | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2631 | WORTHINGTON | CNV-23026260300 RETIRE PAPER CHART | 4000079952 | SUP32.0002.00001 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-12-01 | 2023-12-01 |  | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2631 | GREENUP | CNV-23026260500 RETIRE PAPER CHART | 4000079953 | SUP32.0002.00001 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-12-01 | 2023-12-01 |  | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2621 | LEXINGTON | CNV-23026260800 RETIRE PAPER CHART | 4000079955 | SUP32.0002.00001 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-12-01 | 2023-12-01 |  | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2631 | GREENUP | CNV-23026261000 RETIRE PAPER CHART | 4000079956 | SUP32.0002.00001 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-12-01 | 2023-12-01 |  | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2633 | HAROLD | CNV-23026261600 RETIRE PAPER CHART | 4000079957 | SUP32.0002.00001 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 366.29 | 2023-12-01 | 2023-12-01 | 2025-07-30 | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2631 | CATLETTSBURG | CNV-23026261800 RETIRE PAPER CHART | 4000079958 | SUP32.0002.00001 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 642.64 | 2023-12-01 | 2023-12-01 | 2025-07-30 | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2631 |  | ANC-Catletts Creek-Ashland | 4000091541 | ANC32.0000.00334 | REL GMPS MANC PRC SETC | NEW ADJ MIFE NSFS WENV WLND | MAI | 177986.08 | 77643.24 | 2025-11-04 | 2026-11-06 |  | 11 | 6 | 2026 | U122858
2629 | PARIS | STA - Paris-Cynthiana POD Repl - Paris | 4000091562 | ANC32.0000.00335 | REL ESTC MACM PRC SETC | NEW MIFE NSFS WENG | STA | 402481.39 | 8041.64 | 2025-10-07 | 2025-10-07 |  |  |  |  | U938437
2623 |  | CNV-23026287500 PS&I VANDALAY & WESTRIDG | 4000080003 | PSI32.0000.00014 | REL GMPS NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 24066.53 | 2023-12-28 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2621 |  | ANC - JONES CREEK SMRP - LEXINGTON | 4000088361 | ANC32.0000.00336 | REL ESTC MANC PRC SETC | NEW NSFS WENG WENV | MAI | 399961.11 | 13773.58 | 2025-08-19 | 2025-08-19 |  |  |  |  | U127466
2629 |  | ANC-SMRP Regan Dr-Winchester | 4000092090 | ANC32.0000.00338 | REL PCNF GMPS MANC PRC SETC | NPRG ADJ | MAI | 507048.2 | 24071.55 | 2026-01-01 | 2026-12-31 | 2026-05-18 | 12 | 31 | 2026 | U128885
2631 |  | EMER-10th Street-Catlettsburg | 4000094732 | ANC32.0000.00339 | REL ESTC MANC PRC SETC | NEW ADJ FCMP | MAI | 1792.45 | 2.8 | 2025-12-04 | 2025-12-19 |  |  |  |  | U122858
2631 |  | EMER-10th Street-Catlettsburg RECREATE | 4000095766 | ANC32.0000.00339 | REL ESTC MACM PRC SETC SKKP | NEW | MAI | 121797.85 | 0 | 2025-10-24 | 2025-10-25 |  |  |  |  | U141016
2631 |  | ANC-ROBERTS DRIVE CASING-ASHLAND | 4000093713 | ANC32.0000.00340 | CRTD MANC NMAT NTUP PRC | EST | MAI | 0 | 0 | 2026-07-01 | 2026-07-18 |  | 7 | 18 | 2026 | U141016
2631 |  | ANC-Worthington-Ashland | 4000094681 | ANC32.0000.00341 | REL PCNF ESTC MANC PRC SETC | NEW ADJ WENG | MAI | 4241260.92 | 97.91 | 2026-10-31 | 2027-12-31 | 2026-05-14 |  |  |  | U122858
2631 | WORTHINGTON | ANC-Retire R-1314-Worthington | 4000098339 | ANC32.0000.00341 | CRTD ESTC MANC NTUP PRC SKKP | NEW CAN NSFS | STA | 21065.6 | 0 | 2026-02-19 | 2027-12-31 |  |  |  |  | U122858
2631 | WORTHINGTON | ANC-Retire R-1314-Worthington. | 4000098360 | ANC32.0000.00341 | REL PCNF MANC PRC SETC SKKP | NPRG ADJ MIFE WENG | STA | 16286.5 | 264.06 | 2026-02-19 | 2027-12-31 | 2026-02-23 |  |  |  | U122858
2621 |  | ANC-Hunters Rest Ct-Lexington | 4000095706 | ANC32.0000.00342 | REL PCNF ESTC MACM PRC SETC | NEW ADJ | MAI | 11955.89 | 209.55 | 2026-01-05 | 2026-12-28 | 2026-03-04 | 12 | 28 | 2026 | U122858
2621 |  | ANC-SOUTHLAND DRIVE HP -LEXINGTON | 4000095936 | ANC32.0000.00343 | REL ESTC MANC PRC SETC | NEW NSFS | MAI | 1879 | 8788.26 | 2026-07-01 | 2026-12-31 |  |  |  |  | U127466
2621 |  | INSTALL 200' - 8" PMLP | 4000095938 | ANC32.0000.00344 | REL ESTC MANC PRC SETC | NEW NSFS | MAI | 26.65 | 10713.28 | 2026-10-31 | 2027-12-31 |  |  |  |  | U127466
2621 |  | 2621 - ANC - THIRD ST LEAK SMRP - LEX | 4000095939 | ANC32.0000.00344 | CRTD MANC NTUP PRC | EST | MAI | 2.41 | 0 | 2026-01-08 | 2026-01-08 |  |  |  |  | U127466
2621 |  | ANC - LIBERTY HGTS SMRP - LEX | 4000095962 | ANC32.0000.00345 | CRTD MANC NTUP PRC | NEW ADJ NSFS | MAI | 4.71 | 0 | 2026-10-31 | 2027-12-31 |  |  |  |  | U127466
2621 |  | ANC - CULPEPPER SMRP - LEX | 4000095963 | ANC32.0000.00346 | REL MANC PRC SETC | NEW ADJ NSFS | MAI | 4.71 | 0 | 2026-10-31 | 2027-12-31 |  |  |  |  | U127466
2621 |  | ANC - SUBURBAN CT SMRP - LEX | 4000095964 | ANC32.0000.00347 | REL MANC PRC SETC | NEW NSFS | MAI | 4.71 | 5118.27 | 2026-10-31 | 2027-12-31 |  |  |  |  | U127466
2621 |  | ANC - LEGENDS LN SMRP - LEX | 4000095965 | ANC32.0000.00348 | REL MANC PRC SETC | NEW NSFS | MAI | 4.71 | 7753.86 | 2026-10-31 | 2027-12-31 |  |  |  |  | U127466
2621 |  | ANC - BON AIR SMRP - LEX | 4000095967 | ANC32.0000.00350 | REL MANC PRC SETC | NEW NSFS | MAI | 4.71 | 4655.1 | 2026-10-31 | 2027-12-31 |  |  |  |  | U127466
2621 |  | ANC - ROBIN RD GLENDOVER SMRP - LEX | 4000095968 | ANC32.0000.00351 | REL MANC PRC SETC | NEW ADJ NSFS | MAI | 4.71 | 0 | 2026-10-31 | 2027-12-31 |  |  |  |  | U127466
2621 |  | ANC - DEERHAVEN HP SMRP - LEX | 4000095969 | ANC32.0000.00352 | REL ESTC MANC PRC SETC | NEW NSFS | MAI | 1.93 | 1697.73 | 2026-10-31 | 2027-12-31 |  |  |  |  | U127466
2621 |  | 2621 - ANC - LEXINGTON IBHP REP PH1 - LE | 4000095970 | ANC32.0000.00353 | REL ESTC MACM PRC SETC | NEW NSFS | MAI | 533.84 | 33713.41 | 2026-01-08 | 2026-01-08 |  |  |  |  | U127466
2621 |  | ANC - FAIRFIELD LEAK SMRP - LEX | 4000095971 | ANC32.0000.00354 | REL ESTC MANC PRC SETC | NEW NSFS | MAI | 4.71 | 6880.34 | 2026-10-31 | 2027-12-31 |  |  |  |  | U127466
2621 |  | ANC - PRICE RD TRLR PK SMRP - LEX | 4000095972 | ANC32.0000.00355 | REL MANC PRC SETC | NEW NSFS | MAI | 3.31 | 1018.5 | 2026-10-31 | 2027-12-31 |  |  |  |  | U127466
2621 |  | ANC - DELMONT DR SMRP - LEX | 4000096753 | ANC32.0000.00356 | REL ESTC MANC PRC SETC | NEW MIFE NSFS WENG | MAI | 2.37 | 12283.27 | 2026-10-31 | 2027-12-31 |  |  |  |  | U938437
2623 | GEORGETOWN | Toyota Line-Blowdown Valve C206A&B | 4000098635 | ANC32.0000.00357 | CRTD MANC NMAT NTUP PRC | EST WENG | MAI | 0 | 0 | 2027-01-01 | 2027-12-31 |  |  |  |  | U141016
2623 |  | Toyota Line-Blowdown Valve C-205A&B | 4000098789 | ANC32.0000.00357 | CRTD MANC NMAT NTUP PRC | EST WENG | MAI | 0 | 0 | 2027-01-01 | 2027-12-31 |  |  |  |  | U141016
2623 |  | Toyota Line-Blowdown Valve C203A&B | 4000098790 | ANC32.0000.00357 | CRTD MANC NMAT NTUP PRC | EST CAN WENG | MAI | 0 | 0 | 2027-01-01 | 2027-12-31 |  |  |  |  | U141016
2631 | CANNONSBURG | CNV-24026316400 EMER-INSTALL CATALYTIC H | 4000080256 | ANC32.0000.00291 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 1812.91 | 2024-07-01 | 2024-07-01 | 2025-07-31 | 1900-01-06 | 1899-12-31 | 1905-07-16 | C_U139391
2633 | SOUTH WILLIAMSON | CNV-24026320600 INSTALL ERX BATTERY | 4000080257 | ANC32.0000.00130 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 1980 | 2024-03-28 | 2024-03-30 |  | 1900-01-02 | 1900-01-29 | 1905-07-16 | C_U139391
2629 |  | CNV-24026345200 PM PARIS-CYNTHIANA POD R | 4000080259 | PSI32.0000.00023 | REL PCNF CSER NMAT PRC SETC | NEW NSFS WENG | PSI | 0 | 15497.83 | 2027-04-01 | 2027-10-01 | 2026-03-04 | 1900-01-09 | 1900-01-29 | 1905-07-19 | C_U139391
2623 |  | CNV-24026346800 LAND AND CONFLICT ASSESM | 4000080281 | PSI32.0000.00026 | TECO JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL REV | PSI | 0 | 29608.59 | 2024-07-29 | 2024-07-30 |  | 1900-01-06 | 1900-01-29 | 1905-07-16 | C_U139391
2633 |  | CNV-24026352100 INVESTIGATE MAINS | 4000080282 | PSI32.0000.00027 | TECO JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL REV | PSI | 0 | 39866.93 | 2024-09-30 | 2024-09-30 |  | 1900-01-08 | 1900-01-29 | 1905-07-16 | C_U139391
2629 |  | PSI-SMRP Rogers Av ROW-Mt Sterling | 4000080283 | ANC32.0000.00277 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 17954.07 | 2024-08-29 | 2024-08-31 |  | 1900-01-07 | 1900-01-30 | 1905-07-16 | C_U139391
2621 |  | CNV-24026369400 MAINS & SERVICES LOCATE/ | 4000080286 | PSI32.0000.00032 | REL NMAT PRC SETC | NEW NSFS | PSI | 0 | 15967.77 | 2025-01-30 | 2025-01-31 |  | 1899-12-31 | 1900-01-30 | 1905-07-17 | C_U139391
2633 |  | CNV-24026370800 ENVIROMENTAL CONSULTANT | 4000080287 | PSI32.0000.00031 | REL NMAT PRC SETC | NEW NSFS | PSI | 0 | 10970.06 | 2025-01-31 | 2025-01-31 |  | 1899-12-31 | 1900-01-30 | 1905-07-17 | C_U139391
2631 |  | ANC - SMRP CHINN STREET - ASHLAND | 4000096262 | ANC32.0000.00358 | REL PCNF ESTC GMPS MANC PRC SETC SKKP | SCHD | MAI | 1005995.84 | 175352.31 | 2026-04-02 | 2027-12-31 | 2026-04-07 |  |  |  | U141016
2631 |  | ANC-SMRP BSHP SOUTHPOINT-ASHLAND | 4000096778 | ANC32.0000.00359 | CRTD ESTC MANC NTUP PRC | PLN NSFS | MAI | 14860.02 | 0 | 2026-10-31 | 2027-12-31 |  |  |  |  | U141016
2633 |  | CNV-22026221400 PS&I - INDUSTRIAL PARK | 4000080303 | PSI32.0000.00036 | TECO JBFI MANC NMAT PRC SETC | NEW CAN FCMP NSFS RECL | PSI | 0.76 | 0 | 2025-12-30 | 2025-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-17 | C_U139391
2633 | PIPPA PASSES | CNV-24026311300 EMER - INSTALL 2\" 461S | 4000080322 | ANC32.0000.00298 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 2090.56 | 2024-03-26 | 2024-04-01 | 2025-07-31 | 1900-01-03 | 1899-12-31 | 1905-07-16 | C_U139391
2633 | PIPPA PASSES | CNV-24026311400 EMER - RETIRE 2\" MOONEY | 4000080323 | ANC32.0000.00298 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 721.31 | 2024-04-01 | 2024-04-01 | 2025-07-31 | 1900-01-03 | 1899-12-31 | 1905-07-16 | C_U139391
2631 |  | CNV-24026354700 INVESTIGATE REG STATION | 4000080335 | ANC32.0000.00267 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 5556.87 | 2024-08-29 | 2024-08-31 |  | 1900-01-07 | 1900-01-30 | 1905-07-16 | C_U139391
2631 | ASHLAND | CNV-24026325200 INSTALL BYPASS VALVE | 4000080336 | ANC32.0000.00131 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV WENG | STA | 0 | 13743.6 | 2024-05-24 | 2024-06-01 | 2025-07-31 | 1900-01-05 | 1899-12-31 | 1905-07-16 | C_U139391
2631 |  | CNV-24026334700 INVESTIGATE LAND RIGHTS | 4000080337 | PSI32.0000.00020 | TECO JBFI MANC NMAT PRC SETC | NEW CAN FCMP NSFS RECL | PSI | 0.76 | 30335.71 | 2025-01-30 | 2025-01-30 |  | 1899-12-31 | 1900-01-29 | 1905-07-17 | C_U139391
2632 |  | CNV-24026336300 INVESTIGATE EASEMENTS | 4000080338 | PSI32.0000.00022 | TECO GMPS JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL | PSI | 0 | 194084.06 | 2025-02-28 | 2025-03-01 |  | 1900-01-02 | 1899-12-31 | 1905-07-17 | C_U139391
2631 |  | ANC-BEVERLY BLVD SMRP-ASHLAND | 4000096838 | ANC32.0000.00360 | CRTD ESTC MANC NTUP PRC | PLN NSFS | MAI | 14860.02 | 0 | 2026-10-31 | 2027-12-31 |  |  |  |  | U141016
2631 |  | ANC-11th Street-Catlettsburg | 4000096892 | ANC32.0000.00361 | REL ESTC MANC PRC SETC SKKP | NEW ADJ NSFS | MAI | 3187 | 0 | 2026-10-31 | 2027-12-31 |  |  |  |  | U122858
2631 | CATLETTSBURG | VCU | 4000096894 | ANC32.0000.00361 | CRTD MANC NMAT NTUP PRC | EST | STA | 0 | 0 | 2026-01-22 | 2027-12-30 |  |  |  |  | U122858
2629 |  | PSI-SMRP Regan Dr ROW-Winchester | 4000080425 | PSI32.0000.00033 | TECO JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL | PSI | 0 | 12437.99 | 2025-10-31 | 2025-10-31 |  | 1900-01-09 | 1900-01-30 | 1905-07-17 | C_U139391
2629 |  | PSI-SMRP W Lexington Av ROW-Winchester | 4000080426 | PSI32.0000.00030 | TECO JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL | PSI | 0 | 52843.54 | 2025-10-31 | 2025-10-31 |  | 1900-01-09 | 1900-01-30 | 1905-07-17 | C_U139391
2629 |  | PSI-SMRP Evergreen Dr ROW-Irvine | 4000080427 | PSI32.0000.00039 | TECO JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL | PSI | 0 | 22398.79 | 2025-10-31 | 2025-10-31 |  | 1900-01-09 | 1900-01-30 | 1905-07-17 | C_U139391
2621 |  | CNV-25026392200 DESIGN CONFLICT RELOCATI | 4000080428 | PSI32.0000.00034 | TECO JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL | PSI | 0 | 4554.68 | 2025-04-30 | 2025-04-30 |  | 1900-01-04 | 1899-12-31 | 1905-07-17 | C_U139391
2629 |  | ANC-SMRP Franklin Ave-Winchester | 4000096978 | ANC32.0000.00363 | CRTD MANC NMAT NTUP PRC | EST CAN | MAI | 0 | 0 | 2026-10-31 | 2027-12-31 |  |  |  |  | U128885
2629 |  | ANC-SMRP Franklin Ave-Winchester | 4000100876 | ANC32.0000.00363 | REL ESTC MANC PRC SETC SKKP | NEW ADJ NSFS WENV WLND | MAI | 2477250.83 | 257.9 | 2026-10-31 | 2027-12-31 |  |  |  |  | U128885
2621 |  | CNV-25026407000 INVESTIGATE EASEMENTS | 4000080464 | PSI32.0000.00043 | REL NMAT PRC SETC | NEW NSFS | PSI | 0 | 79956.78 | 2025-07-30 | 2025-07-30 |  | 1900-01-06 | 1900-01-29 | 1905-07-17 | C_U139391
2629 |  | PSI-Hollow Creek ROW-Mt Sterling | 4000080587 | PSI32.0000.00005 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 0 | 2020-12-29 | 2020-12-30 |  | 1900-01-11 | 1900-01-29 | 1905-07-12 | C_U139391
2621 |  | CNV-21026151000 MAP & INVESTIGATE CONFLI | 4000080624 | PSI32.0000.00002 | TECO GMPS JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL REV WENG WENV* | PSI | 0 | 15252.52 | 2022-06-30 | 2022-06-30 |  | 1900-01-05 | 1900-01-29 | 1905-07-14 | C_U139391
2633 |  | ANC-Main St-Hindman | 4000097076 | ANC32.0000.00364 | REL PCNF MANC PRC SETC | NEW ADJ RCFO WENV | MAI | 11311.59 | 2524.7 | 2024-12-30 | 2024-12-30 | 2026-04-30 | 12 | 30 | 2024 | U122858
2621 | LEXINGTON | CNV-23026246100 RETIRE PAPER GAUGE | 4000080949 | ANC32.0000.00291 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-02-01 | 2023-02-01 |  | 1900-01-01 | 1899-12-31 | 1905-07-15 | C_U139391
2621 | LEXINGTON | CNV-23026271600 PAPER ONLY TO SET UP WMS | 4000080951 | BET32.0000.00001 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-06-30 | 2023-07-01 |  | 1900-01-06 | 1899-12-31 | 1905-07-15 | C_U139391
2621 | LEXINGTON | CNV-23026273900 INSTALL 441 REG (WEST RU | 4000080952 | ANC32.0000.00125 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-11-01 | 2023-11-01 |  | 1900-01-10 | 1899-12-31 | 1905-07-15 | C_U139391
2633 |  | CNV-23026275400 INVESTIGATE MAINS | 4000080953 | PSI32.0000.00001 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 53321.38 | 2023-08-01 | 2023-08-01 |  | 1900-01-07 | 1899-12-31 | 1905-07-15 | C_U139391
2631 |  | CNV-23026280700 RETIRE STATIONS R-1375 | 4000080954 | ANC32.0000.00101 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 1925.19 | 2024-04-30 | 2024-04-30 | 2025-07-31 | 1900-01-03 | 1900-01-29 | 1905-07-16 | C_U139391
2621 |  | CNV-23026285500 RETIRE REG STATION #1129 | 4000080955 | BET32.0000.00020 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 12134 | 2024-03-01 | 2024-03-01 | 2025-08-12 | 1900-01-02 | 1899-12-31 | 1905-07-16 | C_U139391
2623 | VERSAILLES | CNV-23026288700 INSTALL NEW RELIEF VALVE | 4000080956 | ANC32.0000.00291 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 603.94 | 2023-11-01 | 2023-11-01 | 2025-07-30 | 1900-01-10 | 1899-12-31 | 1905-07-15 | C_U139391
2623 |  | ANC - E MAIN ST GEO SMRP | 4000097442 | ANC32.0000.00365 | REL ESTC MANC PRC SETC | NEW WLND | MAI | 294394.2 | 1269.21 | 2026-10-31 | 2027-12-31 |  |  |  |  | U132703
2623 |  | ANC - NE 4TH ST FRA SMRP | 4000097443 | ANC32.0000.00366 | REL ESTC MANC PRC SETC | NEW WLND | MAI | 1849.2 | 5693.21 | 2026-10-31 | 2027-12-31 |  |  |  |  | U132703
2623 |  | ANC - SE 4TH ST FRA SMRP | 4000097444 | ANC32.0000.00367 | REL ESTC MANC PRC SETC | NEW WLND | MAI | 2596.3 | 1896 | 2026-10-31 | 2027-12-31 |  |  |  |  | U132703
2632 | MAYSVILLE | CNV-23026302500 RETIRE PAPER GAUGE | 4000080980 | ANC32.0000.00133 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 994.07 | 2023-12-15 | 2023-12-15 | 2025-07-31 | 1900-01-11 | 1900-01-14 | 1905-07-15 | C_U139391
2633 | PIPPA PASSES | CNV-23026306500 INSTALL DRIP TANK | 4000080981 | ANC32.0000.00123 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 13157.5 | 2024-06-25 | 2024-07-01 | 2025-07-31 | 1900-01-06 | 1899-12-31 | 1905-07-16 | C_U139391
2623 |  | ANC - PINEHURST DR FRA SMRP | 4000097447 | ANC32.0000.00368 | CRTD ESTC MANC NTUP PRC | NEW WLND | MAI | 1291 | 0 | 2026-10-31 | 2027-12-31 |  |  |  |  | U132703
2631 | CANNONSBURG | PSI-T-4 Transmission Derate-Ashland | 4000081096 | PSI32.0000.00015 | REL MANC NMAT PRC SETC | NEW NSFS WENG | PSI | 0 | 691279.34 | 2025-12-30 | 2026-12-30 |  | 1900-01-11 | 1900-01-30 | 1905-07-18 | C_U139391
2623 |  | CNV-24026344100 PS&I 329 ST CLAIR ST | 4000081374 | PSI32.0000.00024 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 3858.74 | 2024-12-30 | 2024-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-16 | C_U139391
2623 |  | ANC - WINDING WAY DR FRA SMRP | 4000097448 | ANC32.0000.00369 | CRTD MANC NTUP PRC | NEW WLND | MAI | 1291 | 0 | 2026-10-31 | 2027-12-31 |  |  |  |  | U132703
2623 |  | CNV-24026310300 PS&I EAST WEST CONNECTOR | 4000081410 | PSI32.0000.00038 | TECO JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL REV | PSI | 0 | 2789.84 | 2024-12-30 | 2024-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-16 | C_U139391
2623 |  | CNV-24026311000 PS&I 400 STEADMANTOWN LN | 4000081411 | PSI32.0000.00016 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 6769.63 | 2024-12-30 | 2024-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-16 | C_U139391
2621 |  | CNV-24026313600 INVESTIGATE HP EASEMENT/ | 4000081412 | PSI32.0000.00004 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 9525.67 | 2024-12-30 | 2024-12-30 |  | 1900-01-11 | 1900-01-30 | 1905-07-16 | C_U139391
2621 |  | CNV-24026353500 ENCROACHMENT INV. & AGRE | 4000081417 | PSI32.0000.00037 | REL NMAT PRC SETC | NEW NSFS | PSI | 0 | 3637.5 | 2025-12-31 | 2025-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-17 | C_U139391
2623 |  | ANC - CLIFTON RD FRA SMRP | 4000097450 | ANC32.0000.00370 | CRTD ESTC MANC NTUP PRC | NEW WLND | MAI | 2596.3 | 0 | 2026-10-31 | 2027-12-31 |  |  |  |  | U132703
2633 |  | CNV-24026332400 INVESTIGATE EASEMENTS AN | 4000081419 | PSI32.0000.00009 | TECO JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL REV | PSI | 0 | 7297.56 | 2024-12-30 | 2024-12-30 |  | 1900-01-11 | 1900-01-29 | 1905-07-16 | C_U139391
2631 |  | CNV-24026335600 INVESTIGATE EASEMENTS FO | 4000081420 | PSI32.0000.00021 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 4137.58 | 2024-12-30 | 2024-12-30 |  | 1900-01-11 | 1900-01-30 | 1905-07-16 | C_U139391
2629 |  | ANC-Levee Rd VRG Pilots-Mt Sterling | 4000081560 | ANC32.0000.00116 | REL NMAT PRC SETC | NEW NSFS REV | STA | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2631 | ASHLAND | CNV-18026753500 INSTALL NEW REGULATORS | 4000081561 | ANC32.0000.00117 | REL NMAT PRC SETC | NEW NSFS REV | STA | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2631 |  | CNV-21026154600 RETIRE R-1354 | 4000081566 | ANC32.0000.00167 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 8911.51 | 2023-12-29 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2623 |  | ANC - ELM ST VER SMRP | 4000097453 | ANC32.0000.00371 | CRTD ESTC MANC NTUP PRC | NEW WLND | MAI | 2596.3 | 0 | 2026-10-31 | 2027-12-31 |  |  |  |  | U132703
2623 |  | ANC - PAYNES MILL RD VER SMRP | 4000097455 | ANC32.0000.00372 | REL ESTC MANC PRC SETC | NEW WLND | MAI | 1857.3 | 0 | 2026-10-31 | 2027-12-31 |  |  |  |  | U132703
2629 |  | ANC-SMRP Lola Dr-Cynthiana | 4000096900 | ANC32.0000.00374 | CRTD MANC PRC | EST CAN WLND | MAI | 54967.84 | 0 | 2027-01-01 | 2027-12-31 |  | 12 | 31 | 2028 | U128885
2629 |  | CNV-22026205900 RETIRE R-1682 | 4000081716 | ANC32.0000.00003 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 603.94 | 2023-12-29 | 2023-12-31 | 2025-07-30 | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2621 | LEXINGTON | CNV-22026212600 RETIRE STATION VALVES R- | 4000081717 | ANC32.0000.00115 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 1269.95 | 2023-12-29 | 2023-12-31 | 2025-07-30 | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2629 |  | ANC-SMRP Lola Dr-Cynthiana | 4000100818 | ANC32.0000.00374 | REL ESTC MANC PRC SETC SKKP | NEW ADJ NSFS WENG WLND | MAI | 2724583.25 | 0 | 2026-10-31 | 2027-12-31 |  | 12 | 31 | 2027 | U128885
2631 |  | ANC-Poplar St-Ashland | 4000098118 | ANC32.0000.00375 | REL ESTC MANC PRC SETC | NEW NSFS WLND | MAI | 55263.94 | 1272.06 | 2026-10-31 | 2027-12-31 |  |  |  |  | U122858
2623 |  | CNV-22026178300 EMER-INSTALL 5'OF 2\"PMM | 4000081951 | ANC32.0000.00016 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2022-11-30 | 2022-11-30 |  |  |  |  | C_U139391
2631 |  | CNV-22026180700 EMER - INSTALL 3'-3\" PM | 4000081952 | ANC32.0000.00183 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 157.87 | 2022-09-12 | 2022-09-13 | 2025-07-30 |  |  |  | C_U139391
2631 |  | CNV-22026180800 EMER - RETIRE 3'-3\" PMI | 4000081953 | ANC32.0000.00183 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 61.32 | 2022-09-13 | 2022-09-13 | 2025-07-30 |  |  |  | C_U139391
2631 |  | CNV-23026247100 EMER - INSTALL 9'-4\" CS | 4000082025 | ANC32.0000.00210 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-09-25 | 2023-09-30 |  |  |  |  | C_U139391
2631 |  | CNV-23026247200 EMER - RETIRE 9'-4\" CSM | 4000082026 | ANC32.0000.00210 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-09-29 | 2023-09-30 |  |  |  |  | C_U139391
2621 |  | CNV-23026264300 EMER-INSTALL 5' OF 4\"PM | 4000082027 | ANC32.0000.00218 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-03-09 | 2023-03-10 |  |  |  |  | C_U139391
2621 |  | CNV-23026264400 EMER-RETIRE 520'- 4\"PAI | 4000082028 | ANC32.0000.00218 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-03-10 | 2023-03-10 |  |  |  |  | C_U139391
2631 |  | CNV-23026264500 EMER - INSTALL ~5'-4\" P | 4000082029 | ANC32.0000.00219 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 136.4 | 2023-11-30 | 2023-11-30 | 2025-07-30 |  |  |  | C_U139391
2631 |  | CNV-23026264600 EMER - RETIRE ~5'-4\" CS | 4000082030 | ANC32.0000.00219 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 207.26 | 2023-11-30 | 2023-11-30 | 2025-07-30 |  |  |  | C_U139391
2621 |  | CNV-23026265400 EMER - INSTALL 12' - 2\" | 4000082031 | BET32.0000.00034 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 840 | 2023-03-08 | 2023-03-08 |  |  |  |  | C_U139391
2621 |  | CNV-23026265500 EMER - RETIRE 12' - 2\" | 4000082032 | BET32.0000.00034 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-03-08 | 2023-03-08 |  |  |  |  | C_U139391
2631 |  | CNV-23026265600 EMER - INSTALL 4'-6\" PM | 4000082033 | ANC32.0000.00036 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 25.3 | 2023-11-27 | 2023-11-30 |  |  |  |  | C_U139391
2629 |  | CNV-23026266800 EMER - INSTALL 7'-2\" P | 4000082034 | ANC32.0000.00038 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-11-10 | 2023-11-30 |  |  |  |  | C_U139391
2629 |  | CNV-23026267000 EMER - INSTALL 2'-2\" PM | 4000082035 | ANC32.0000.00039 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-11-29 | 2023-11-30 |  |  |  |  | C_U139391
2631 |  | CNV-23026269500 EMER - INSTALL 4'-2\" PI | 4000082036 | ANC32.0000.00041 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 20.9 | 2023-11-29 | 2023-11-30 |  |  |  |  | C_U139391
2629 |  | CNV-23026288500 EMER - INSTALL 3'-2\" PM | 4000082037 | ANC32.0000.00241 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 24.2 | 2024-04-10 | 2024-04-30 |  |  |  |  | C_U139391
2631 |  | CNV-23026289300 INSTALL 7'-2\"&6\" PMLP | 4000082038 | ANC32.0000.00162 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 279.67 | 2024-04-30 | 2024-04-30 |  |  |  |  | C_U139391
2631 |  | CNV-23026290100 EMER - 3'-3\" PMIP | 4000082039 | ANC32.0000.00244 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2933.74 | 2024-04-26 | 2024-04-30 | 2025-07-30 |  |  |  | C_U139391
2631 |  | CNV-23026290200 EMER-RETIRE 3'-PIP | 4000082060 | ANC32.0000.00244 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 192.16 | 2024-04-30 | 2024-04-30 | 2025-07-30 |  |  |  | C_U139391
2631 |  | CNV-23026291700 EMER - INSTALL 3'-4\" PM | 4000082061 | ANC32.0000.00247 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 801.39 | 2024-05-30 | 2024-05-31 | 2025-07-30 |  |  |  | C_U139391
2631 |  | CNV-23026291800 EMER - RETIRE 3'-4\" PIP | 4000082062 | ANC32.0000.00247 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 573.92 | 2024-05-31 | 2024-05-31 | 2025-07-30 |  |  |  | C_U139391
2621 |  | CNV-23026307700 EMER - INSTALL 5'-2\" PM | 4000082063 | ANC32.0000.00030 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2260.97 | 2024-08-29 | 2024-08-31 |  |  |  |  | C_U139391
2631 |  | ANC-Oakview Rd-Ashland | 4000098209 | ANC32.0000.00376 | REL MANC PRC SETC | NEW NSFS | MAI | 0 | 0 | 2026-10-31 | 2027-12-31 |  |  |  |  | U122858
2631 |  | ANC-Hagen Ct-Ashland | 4000098266 | ANC32.0000.00377 | REL ESTC MANC PRC SETC | NEW NSFS | MAI | 13049.54 | 0 | 2026-10-31 | 2027-12-31 |  |  |  |  | U122858
2633 |  | ANC-SR 550-Hindman | 4000098280 | ANC32.0000.00378 | CRTD MANC NTUP PRC | NEW NSFS | MAI | 42805.94 | 0 | 2026-10-31 | 2028-12-31 |  |  |  |  | U122858
2633 |  | ANC-E Main St-Betsy Lane (2633) | 4000098292 | ANC32.0000.00379 | REL ESTC MANC PRC SETC | NEW NSFS WLND | MAI | 8.11 | 0 | 2026-10-31 | 2027-12-31 |  |  |  |  | U122858
2631 |  | ANC-34th St-Ashland | 4000098407 | ANC32.0000.00380 | REL MANC PRC SETC | NEW NSFS | MAI | 14068.32 | 0 | 2026-10-31 | 2027-12-31 |  |  |  |  | U122858
2631 |  | ANC-SMRP BRAMBLE DR-CATLETTSBURG | 4000098859 | ANC32.0000.00381 | CRTD MANC NMAT NTUP PRC | EST CAN | MAI | 0 | 0 | 2027-01-01 | 2027-12-31 |  |  |  |  | U141016
2631 |  | ANC-BRAMBLE DR SMRP-CATLETTSBURG | 4000099985 | ANC32.0000.00381 | CRTD MANC NMAT NTUP PRC | EST | MAI | 0 | 0 | 2026-10-31 | 2027-12-31 |  |  |  |  | U141016
2623 |  | 2623-SMRP NEWTOWN ANNER-VERSAILLES | 4000100006 | ANC32.0000.00382 | REL NMAT PRC SETC | NEW NSFS RCFO | MAI | 0 | 1289.51 | 2025-12-30 | 2025-12-31 |  | 12 | 31 | 2025 | U126783
2623 |  | 2623-EAST WEST CONNECTOR-FRANKFORT | 4000100142 | ANC32.0000.00383 | REL NMAT PRC SETC | NEW NSFS RCFO | MAI | 0 | 0 | 2024-12-30 | 2024-12-31 |  | 12 | 31 | 2024 | U126783
2631 |  | ANC-16th St-Ashland | 4000099141 | ANC32.0000.00384 | REL ESTC MACM PRC SETC | NEW NSFS | MAI | 31361 | 0 | 2026-03-04 | 2028-12-31 |  |  |  |  | U122858
2621 |  | ANC - St Martins Village SMRP -Lexington | 4000099200 | ANC32.0000.00385 | REL ESTC MANC PRC | NEW MIFE NSFS | MAI | 1.67 | 0 | 2026-10-31 | 2027-12-31 |  |  |  |  | U938437
2621 |  | ANC-MONTGOMERY AVE SMRP-LEXINGTON | 4000100007 | ANC32.0000.00386 | CRTD MANC NTUP PRC | EST | MAI | 183.31 | 0 | 2026-03-16 | 2026-03-16 |  |  |  |  | U126783
2623 |  | ANC-N COURT ST SMRP-GEORGETOWN | 4000101432 | ANC32.0000.00387 | CRTD MANC NTUP PRC | EST | MAI | 907.29 | 0 | 2026-04-09 | 2026-04-09 |  |  |  |  | U126783
2631 |  | ANC-SMRP Huckleberry St-Catlettsburg | 4000101746 | ANC32.0000.00388 | CRTD MANC NMAT NTUP PRC | EST | MAI | 42719.04 | 0 | 2026-10-31 | 2027-12-31 |  |  |  |  | U128885
2631 |  | ANC-Pocahantas St-Louisa | 4000101894 | ANC32.0000.00389 | REL ESTC MACM PRC SETC | NEW NSFS | MAI | 4.42 | 0 | 2026-04-17 | 2028-12-31 |  |  |  |  | U122858
2632 |  | DO NOT EXECUTE | 4100449775 | GRT32.0002.00002 | REL CSER MANC NTUP PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2023-12-28 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2629 |  | DO NOT EXECUTE | 4100508576 | PIG32.0000.00035 | REL CSER MANC PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2024-03-27 | 2024-03-31 |  | 1900-01-05 | 1900-01-23 | 1905-07-17 | C_U139391
2631 |  | ANC-Hackworth St-Ashland | 4000102193 | ANC32.0000.00390 | REL ESTC MACM PRC SETC | NEW NSFS | MAI | 8150.69 | 0 | 2026-04-23 | 2026-04-23 |  |  |  |  | U122858
2629 |  | DO NOT EXECUTE | 4100509621 | ANC32.0000.00195 | REL CSER MANC PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2024-05-30 | 2024-05-30 |  | 1900-01-04 | 1900-01-30 | 1905-07-16 | C_U139391
2621 |  | ANC-Narows Subsidence-Narrows | 4000091653 | ANC38.0000.00513 | REL PCNF ESTC GMPS MANC PRC SETC | SCHD ADJ | MAI | 91485.93 | 2637.75 | 2026-06-01 | 2026-09-01 | 2026-05-26 |  |  |  | U139606
2621 |  | ANC - SAVE GRANDVIEW DR - LEXINGTON | 4000094996 | ANC38.0000.00548 | REL MANC PRC SETC | NEW NSFS WLND | MAI | 90212.48 | 0 | 2025-12-10 | 2026-12-31 |  |  |  |  | U146250
2621 |  | ANC - SAVE KANAWHA - GLASGOW | 4000094999 | ANC38.0000.00550 | REL MANC PRC SETC | NEW NSFS WLND | MAI | 88031.7 | 0 | 2025-12-10 | 2026-12-31 |  |  |  |  | U146250
2621 |  | ANC - SAVE ROSS LN - LEXINGTON | 4000095000 | ANC38.0000.00551 | REL ESTC MANC PRC SETC | NEW NSFS WLND | MAI | 87204.7 | 0 | 2025-12-10 | 2026-12-31 |  |  |  |  | U146250
2621 |  | CNV-24026348300 RETIRE ~30'-4\" PMMP | 4000073966 | BET32.0000.00002 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2834.93 | 2024-12-31 | 2024-12-31 | 2025-08-01 | 2 | 28 | 2025 | C_U139391
2621 |  | DO NOT EXECUTE | 4100547582 | ANC32.0002.00002 | REL MANC PRC SETC | NEW CAN NSFS | LND | 4.32 | 0 | 2025-04-29 | 2025-04-30 |  | 1900-01-03 | 1900-01-29 | 1905-07-17 | C_U139391
2621 |  | CNV-24026348200 INSTALL ~30'-4\" PMMP | 4000075798 | BET32.0000.00002 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 9174.51 | 2024-12-27 | 2024-12-31 | 2025-08-01 | 2 | 28 | 2025 | C_U139391
2623 |  | DO NOT EXECUTE | 4100553223 | ANC32.0000.00291 | REL CSER MANC PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2021-12-21 | 2021-12-21 |  | 1900-01-11 | 1900-01-20 | 1905-07-13 | C_U139391
2631 |  | DO NOT EXCUTE. | 4100555682 | SUP32.0002.00001 | REL CSER MANC PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2023-06-30 | 2023-06-30 |  | 1900-01-05 | 1900-01-29 | 1905-07-15 | C_U139391
2623 |  | DO NOT EXECUTE | 4100555721 | GRT32.0002.00002 | REL CSER MANC PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2023-09-28 | 2023-10-01 |  | 1900-01-09 | 1899-12-31 | 1905-07-15 | C_U139391
2623 |  | DO NOT EXECUTE | 4100555740 | ANC32.0000.00192 | REL CSER MACM PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2023-09-28 | 2023-09-28 |  | 1900-01-09 | 1899-12-31 | 1905-07-15 | C_U139391
2631 |  | CNV-21026135500 INSTALL 75'-4/6/12\" CSH | 4000077033 | BET32.0000.00003 | REL MANC PRC SETC | NPRG ADJ | MAI | 183004.72 | 28066.03 | 2025-07-25 | 2025-07-31 |  | 12 | 31 | 2025 | C_U139391
2621 |  | DO NOT EXECUTE | 4100555789 | ANC32.0000.00187 | REL CSER MANC PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2023-09-29 | 2023-09-29 |  | 1900-01-09 | 1899-12-31 | 1905-07-15 | C_U139391
2629 |  | DO NOT EXECUTE | 4100555850 | ANC32.0000.00301 | REL CSER MANC PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2024-03-01 | 2024-03-01 |  | 1900-01-02 | 1899-12-31 | 1905-07-16 | C_U139391
2621 |  | DO NOT EXECUTE | 4100569108 | GRT32.0002.00002 | REL CSER MANC PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2023-12-28 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2631 |  | CNV-21026135600 RETIRE 10'-6/12\" CSHP & | 4000077035 | BET32.0000.00003 | REL PCNF NMAT PRC SETC | NEW NSFS | MAI | 0 | 306.69 | 2025-12-31 | 2025-12-31 | 2025-08-03 | 12 | 31 | 2025 | C_U139391
2621 |  | CNV-22026211700 RETIRE LAND AND REG SITE | 4100577544 | GRT32.0002.00003 | CRTD MANC PRC | NEW FCMP NSFS REV | LND | 2.52 | 0 | 2023-12-01 | 2023-12-01 |  | 1900-01-11 | 1899-12-31 | 1905-07-15 | C_U139391
2629 |  | DO NOT EXECUTE | 4100577553 | ANC32.0000.00174 | REL CSER MACM PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2023-12-28 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2629 |  | DO NOT EXECUTE | 4100577557 | ANC32.0000.00158 | REL CSER MACM PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2023-12-28 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2621 |  | DO NOT EXECUTE | 4100577559 | PIG32.0000.00027 | REL CSER MANC PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2023-12-28 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U139391
2621 |  | DO NOT EXECUTE | 4100577602 | ANC32.0000.00182 | REL CSER MACM PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2023-06-01 | 2023-06-01 |  | 1900-01-05 | 1899-12-31 | 1905-07-15 | C_U139391
2621 |  | CNV-18026779401 ACQ 25X25 SITE FOR NEW R | 4000082857 | GRT32.0002.00002 | REL NMAT PRC SETC | NEW FCMP NSFS REV WENG | LND | 0 | 0 | 2023-12-28 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U141034
2632 |  | CNV-20026950500 ACQUIRE LAND FOR STATION | 4000082959 | GRT32.0002.00002 | REL NMAT PRC SETC | NEW FCMP NSFS REV | LND | 0 | 0 | 2023-12-28 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U141034
2623 |  | CNV-21026123000 INVESTIGATE/AQUIRE EASEM | 4000083108 | ANC32.0000.00291 | REL NMAT PRC SETC | NEW FCMP NSFS REV | LND | 0 | 2027.42 | 2021-12-21 | 2021-12-21 |  | 1900-01-11 | 1900-01-20 | 1905-07-13 | C_U141034
2621 |  | CV - LARKSPUR INSTALL 16'- 6" PMMP | 4000078036 | BET32.0000.00004 | REL MANC PRC SETC | NEW ADJ NSFS | MAI | 30134.34 | 10.04 | 2026-12-29 | 2026-12-31 |  | 12 | 31 | 2026 | C_U139391
2629 |  | CNV-22026221100 ACQUIRE EASEMENT | 4000083416 | ANC32.0000.00174 | REL NMAT PRC SETC | NEW FCMP NSFS REV | LND | 0 | 0 | 2023-12-28 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U141034
2629 |  | CNV-22026224600 ACQUIRE LAND RIGHTS | 4000083417 | ANC32.0000.00158 | REL NMAT PRC SETC | NEW FCMP NSFS REV | LND | 0 | 500 | 2023-12-28 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U141034
2621 |  | CNV-22026235500 ACQUIRE EASEMENT | 4000083418 | PIG32.0000.00027 | REL NMAT PRC SETC | NEW FCMP NSFS REV | LND | 0 | 0 | 2023-12-28 | 2023-12-31 |  | 1900-01-11 | 1900-01-30 | 1905-07-15 | C_U141034
2621 |  | CNV-22026242400 OBTAIN NEW HP EASEMENT | 4000083419 | ANC32.0000.00182 | REL NMAT PRC SETC | NEW FCMP NSFS REV | LND | 0 | 0 | 2023-06-01 | 2023-06-01 |  | 1900-01-05 | 1899-12-31 | 1905-07-15 | C_U141034
2631 |  | CNV-23026266501 ACQUIRE EASEMENT | 4000084011 | SUP32.0002.00001 | REL NMAT PRC SETC | NEW FCMP NSFS REV | LND | 0 | 0 | 2023-06-30 | 2023-06-30 |  | 1900-01-05 | 1900-01-29 | 1905-07-15 | C_U141034
2623 |  | CNV-23026271300 OBTAIN ADDITIONAL LAND R | 4000084013 | GRT32.0002.00002 | REL NMAT PRC SETC | NEW FCMP NSFS REV | LND | 0 | 0 | 2023-09-28 | 2023-10-01 |  | 1900-01-09 | 1899-12-31 | 1905-07-15 | C_U141034
2623 |  | CNV-23026281000 OBTAIN NEW EASEMENT | 4000084015 | ANC32.0000.00192 | REL NMAT PRC SETC | NEW FCMP NSFS REV | LND | 0 | 4092.58 | 2023-09-28 | 2023-09-28 |  | 1900-01-09 | 1899-12-31 | 1905-07-15 | C_U141034
2621 |  | CNV-22026166700 INSTALL 16'-2\"PMMP | 4000078245 | BET32.0000.00005 | REL CSER NMAT PRC SETC | NEW NSFS | MAI | 0 | 0 | 2026-12-29 | 2026-12-31 |  | 12 | 31 | 2026 | C_U139391
2621 |  | CNV-23026292600 DOCUMENT 20'EASEMENT FRO | 4000084019 | ANC32.0000.00187 | REL NMAT PRC SETC | NEW FCMP NSFS REV | LND | 0 | 25257.44 | 2023-09-29 | 2023-09-29 |  | 1900-01-09 | 1899-12-31 | 1905-07-15 | C_U141034
2629 |  | CNV-23026302000 ACQUIRE LAND FOR GROUND | 4000084023 | ANC32.0000.00301 | TECO JBFI NMAT PRC SETC | NEW FCMP NSFS REV | LND | 0 | 10681.06 | 2024-03-01 | 2024-03-01 |  | 1900-01-02 | 1899-12-31 | 1905-07-16 | C_U141034
2629 |  | CNV-24026312500 ACQUIRE EASEMENT FOR REL | 4000084727 | PIG32.0000.00035 | TECO JBFI NMAT PRC SETC | NEW FCMP NSFS REV | LND | 0 | 500 | 2024-03-27 | 2024-03-31 |  |  |  |  | C_U141034
2621 |  | CNV-24026350500 EMER-INSTALL 2\"VALVE KY | 4000075823 | BET32.0000.00011 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2018.47 | 2024-09-30 | 2024-10-01 | 2025-08-01 | 10 | 1 | 2024 | C_U139391
2629 |  | CNV-24026341800 LAND PAYMENT FOR REG SIT | 4000084794 | ANC32.0000.00195 | REL NMAT PRC SETC | NEW FCMP NSFS REV | LND | 0 | 500 | 2024-05-30 | 2024-05-30 |  | 1900-01-04 | 1900-01-30 | 1905-07-16 | C_U141034
2623 |  | CNV-25026377600 EMER-INSTALL 4' OF 2\"PM | 4000080036 | BET32.0000.00013 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 4751.4 | 2025-05-29 | 2025-06-01 |  | 6 | 1 | 2025 | C_U139391
2621 |  | CNV-24026345300 RETIRE 350' OF 4\"CSLP M | 4000075786 | BET32.0000.00016 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4736.69 | 2024-09-30 | 2024-10-01 | 2025-08-01 | 10 | 1 | 2024 | C_U139391
2623 |  | CNV-24026356800 REPLACE 20'-6\" CSLP | 4000076114 | BET32.0000.00018 | REL PCNF NMAT PRC SETC | NEW NSFS | MAI | 0 | 1069.37 | 2025-12-30 | 2025-12-31 | 2025-08-01 | 12 | 31 | 2025 | C_U139391
2629 |  | CNV-23026303400 INSTALL 20'-2\" CSHP | 4000078099 | BET32.0000.00021 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 79958.27 | 2024-12-02 | 2024-12-02 | 2025-07-31 | 12 | 15 | 2024 | C_U139391
2629 | RICHMOND | CNV-23026303200 R-1647 REBUILD INSTALL | 4000080004 | BET32.0000.00021 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 22781.66 | 2024-12-16 | 2024-12-16 | 2025-07-31 | 12 | 31 | 2024 | C_U139391
2621 |  | CNV-25026399900 OBTAIN EASEMENTS | 4000085076 | ANC32.0002.00002 | TECO JBFI NMAT PRC SETC | NEW FCMP NSFS | LND | 0 | 7294.7 | 2025-04-29 | 2025-04-30 |  | 1900-01-03 | 1900-01-29 | 1905-07-17 | C_U141034
2629 |  | BET-Red Lick Rd Reg IP-Irvine | 4000077665 | BET32.0000.00022 | REL MANC PRC SETC | NPRG | MAI | 1.17 | 11081.96 | 2025-12-30 | 2025-12-31 |  | 12 | 31 | 2025 | C_U139391
2621 |  | Damage To Company Fac - Main | 4000087006 | ANC32.0002.00001 | REL MANC PRC SETC | NPRG ADJ FCMP MIFE NSFS RCFO REIM | MAI | 1243.06 | 1443.28 | 2025-07-30 | 2025-07-31 |  |  |  |  | SAP_WFRT
2623 |  | Damage To Company Fac - Main | 4000087304 | ANC32.0002.00001 | REL MANC PRC SETC | NEW ADJ FCMP MIFE NSFS RCFO REIM | MAI | 1781.13 | 406.59 | 2025-07-31 | 2025-08-01 |  |  |  |  | SAP_WFRT
2629 | IRVINE | Design for CU Tab | 4000090723 |  | CRTD MANC NMAT NTUP PRC | EST | MAI | 0 | 0 | 2025-09-21 | 2025-09-21 |  |  |  |  | SAP_WFRT
2621 | LEXINGTON | DAMAGED MAIN LINE TKT 253011846 | 4000092953 | ANC32.0002.00001 | REL MANC NMAT PRC SETC | NEW FCMP MIFE NSFS RCFO REIM | MAI | 710.28 | 3153.89 | 2025-10-28 | 2025-10-29 |  |  |  |  | SAP_WFRT
2621 |  | JOB CREATED TO CLEAR DPI FROM DAMAGE | 4000093937 | ANC32.0002.00001 | REL MANC NMAT PRC SETC | NEW ADJ FCMP NSFS RCFO | MAI | 847.8 | 350.58 | 2025-10-02 | 2025-10-03 |  | 1900-01-09 | 1900-01-02 | 1905-07-17 | SAP_WFRT
2621 | LEXINGTON | Leak Repair | 4000099530 | ANC32.0002.00001 | REL MANC NMAT PRC SETC | NEW FCMP MIFE NSFS RCFO | MAI | 1025.52 | 2489.56 | 2026-02-14 | 2026-03-07 |  | 1900-01-02 | 1900-01-06 | 1905-07-18 | SAP_WFRT
2629 | IRVINE | ANC-Red Lick Rd Regulator Station-Irvine | 4000080301 | BET32.0000.00022 | REL PCNF GMPS MANC PRC SETC | NPRG FCMP | STA | 561.33 | 111062.47 | 2025-12-30 | 2025-12-31 | 2025-08-01 | 12 | 31 | 2025 | C_U139391
2623 |  | CNV-24026346800 LAND AND CONFLICT ASSESM | 4000086913 | PIG32.0000.00053 | CRTD MANC NMAT PRC | NEW CAN NSFS RCFO | MAI | 0 | 0 | 2024-07-29 | 2024-07-30 |  | 1900-01-06 | 1900-01-29 | 1905-07-16 | U122858
2629 | IRVINE | ANC-Red Lick Rd Regulator ABN-Irvine | 4000081715 | BET32.0000.00022 | REL PCNF MANC PRC SETC | NPRG FCMP | STA | 94.53 | 19171.8 | 2025-12-31 | 2025-12-31 | 2025-08-01 | 12 | 31 | 2025 | C_U139391
2629 |  | CNV-25026400700 RETIRE 100'-4\" PMMP | 4000080100 | BET32.0000.00023 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | -3146.07 | 2025-05-14 | 2025-05-15 | 2025-08-03 | 5 | 15 | 2025 | C_U139391
2629 |  | CNV-25026403100 EMER - RETIRE 2'-3\" PAM | 4000080102 | BET32.0000.00024 | REL PCNF MANC PRC SETC | COCO FCMP NSFS | MAI | 3218.22 | 11554.81 | 2025-04-07 | 2025-04-07 | 2025-08-03 | 4 | 9 | 2025 | C_U139391
2631 |  | CNV-25026382100 INSTALL 110'-4\" PMLP | 4000080055 | BET32.0000.00025 | REL GMPS MANC PRC SETC | NPRG FCMP MIFE | MAI | 211351.06 | 348136.85 | 2025-10-17 | 2025-10-30 |  | 10 | 30 | 2025 | C_U139391
2629 |  | CNV-25026400200 INSTALL 550'-2\\\ PMMP. | 4000080098 | BET32.0000.00026 | REL PCNF MANC NMAT NTUP PRC SETC | NEW | MAI | 0 | 19463.81 | 2025-04-28 | 2025-05-01 | 2025-08-02 | 5 | 1 | 2025 | C_U139391
2633 |  | CNV-19026867802 INSTALL 376'-4\\\" PMIP. | 4000075940 | BET32.0000.00027 | REL MANC PRC SETC | NEW FCMP WENG | MAI | 11431.35 | 159288.9 | 2025-09-11 | 2025-09-30 |  | 9 | 30 | 2025 | C_U139391
2633 |  | CNV-19026867900 RETIRE 396'-3\" P&CS | 4000075942 | BET32.0000.00027 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 33.42 | 2025-09-30 | 2025-09-30 |  | 9 | 30 | 2025 | C_U139391
2621 |  | CNV-22026167800 INSTALL CRITICAL VALVE | 4000078249 | BET32.0000.00030 | REL CSER NMAT PRC SETC | NEW NSFS | MAI | 0 | 0 | 2026-12-29 | 2026-12-31 |  | 12 | 31 | 2026 | C_U139391
2621 |  | CNV-22026167900 RERTIRE APPROX 12'-4\" C | 4000078251 | BET32.0000.00030 | REL CSER NMAT PRC SETC | NEW NSFS | MAI | 0 | 0 | 2026-12-31 | 2026-12-31 |  | 12 | 31 | 2026 | C_U139391
2621 |  | CNV-24026310500 RETIRE VALVE & 5' OF 2\" | 4000073998 | BET32.0000.00040 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2024-12-31 | 2024-12-31 |  | 12 | 31 | 2024 | C_U139391
2621 |  | CNV-24026310400 INSTALL VALVE & 5' OF 2\ | 4000075917 | BET32.0000.00040 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 7598.07 | 2024-12-30 | 2024-12-31 |  | 12 | 31 | 2024 | C_U139391
2631 |  | CNV-24026341000 INSTALL 300'OF 2\" PMIP | 4000079333 | BET32.0000.00042 | REL PCNF MANC PRC SETC | NEW ADJ FCMP MIFE NSFS WENG | MAI | 1109.39 | 23226.43 | 2025-04-24 | 2025-04-30 | 2025-08-02 | 4 | 30 | 2025 | C_U139391
2621 |  | CNV-24026343300 INSTALL 4\" POLY VALVE | 4000075780 | BET32.0000.00043 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 5484.09 | 2024-10-31 | 2024-11-01 | 2025-07-31 | 11 | 1 | 2024 | C_U139391
2621 |  | CNV-24026343400 RETIRE 4\"POLY VALVE C19 | 4000075782 | BET32.0000.00043 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 796.67 | 2024-11-01 | 2024-11-01 | 2025-07-31 | 11 | 1 | 2024 | C_U139391
2621 |  | CNV-24026349300 INSTALL 4\"POLY VALVE KY | 4000076442 | BET32.0000.00044 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 10019.67 | 2025-05-28 | 2025-06-01 | 2025-08-01 | 6 | 1 | 2025 | C_U139391
2621 |  | CNV-24026349400 RETIRE 10' OF 3\"PMP MAI | 4000076444 | BET32.0000.00044 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 21.76 | 2025-05-30 | 2025-06-01 | 2025-08-01 | 6 | 1 | 2025 | C_U139391
2631 |  | BET-ROBERTS DRIVE CASING-ASHLAND | 4000079387 | BET32.0000.00045 | REL PCNF MANC NMAT PRC SETC | NEW WENV WPMT | MAI | 365.12 | 204.22 | 2026-07-09 | 2026-07-18 | 2026-04-30 | 7 | 18 | 2026 | C_U139391
2631 |  | CNV-24026348600 RETIRE 360' OF 3\" CSIP | 4000079388 | BET32.0000.00045 | REL NMAT PRC SETC | NEW NSFS | MAI | 0 | 1779.35 | 2025-11-30 | 2025-11-30 |  | 7 | 18 | 2026 | C_U139391
2631 |  | CNV-25026381600 ENVIROMENTAL CONSULTANT | 4000080424 | BET32.0000.00045 | REL CSER NMAT PRC SETC | NEW NSFS | PSI | 0 | 1885.5 | 2026-07-16 | 2026-07-18 |  | 7 | 18 | 2026 | C_U139391
2621 |  | CNV-24026368800 INSTALL 5' OF 6\\\ PML. | 4000076491 | BET32.0000.00046 | REL PCNF MANC NMAT PRC SETC | NEW | MAI | 0 | 12900.04 | 2025-06-26 | 2025-06-30 | 2025-08-01 | 6 | 30 | 2025 | C_U139391
2621 |  | CNV-24026368900 RETIRE 5' OF 6\" BSLP | 4000076493 | BET32.0000.00046 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 820.05 | 2025-06-30 | 2025-06-30 | 2025-08-01 | 6 | 30 | 2025 | C_U139391
2629 |  | CNV-24026310700 ABANDON ~ 150'- 2\" CSIP | 4000073999 | BET32.0000.00048 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 577.39 | 2024-12-31 | 2024-12-31 | 2025-07-31 | 12 | 31 | 2024 | C_U139391
2629 |  | CNV-24026310600 INSTALL 2, 2\" STOPPLE F | 4000075919 | BET32.0000.00048 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 13907.28 | 2025-12-23 | 2025-12-31 | 2025-07-31 | 12 | 31 | 2025 | C_U139391
2623 |  | EMER - E Broadway St Crossbore FRANKFORT | 4000087431 | BET32.0000.00049 | REL ESTC MANC PRC SETC | NPRG ADJ FCMP | MAI | 157244.84 | 2978.58 | 2025-08-06 | 2025-08-29 |  | 8 | 29 | 2025 | U122858
2621 | LEXINGTON | Fence for co prem 200874 | 4100791310 | BET32.0000.00050 | CRTD ESTC MANC NTUP PRC | PLN ADJ NSFS | STA | 12697.86 | 0 | 2025-08-15 | 2025-12-15 |  |  |  |  | U122858
2621 |  | REG STATION 1073 OUTLET VALVE INSTALL - | 4000088155 | BET32.0000.00052 | REL ESTC GMPS MANC PRC SETC | NPRG ADJ FCMP | MAI | 38183.75 | 88181.36 | 2025-08-18 | 2025-08-18 |  |  |  |  | U127466
2621 |  | 2621 - STA 1073 VALVE REP - LEXINGTON | 4000088181 | BET32.0000.00052 | CRTD MANC PRC | EST | STA | 708.84 | 0 | 2025-08-18 | 2025-08-18 |  |  |  |  | U127466
2621 |  | EMER - Install 10'-2" PMMP | 4000088222 | BET32.0000.00053 | CRTD MANC NTUP PRC | EST NSFS | MAI | 455.12 | 0 | 2025-08-18 | 2025-09-05 |  |  |  |  | U122858
2621 |  | EMER - Retire 10'-2" PMMP | 4000088266 | BET32.0000.00053 | CRTD MANC NTUP PRC | EST NSFS | MAI | 0 | 0 | 2025-08-18 | 2025-08-18 |  |  |  |  | U122858
2621 |  | Install valve | 4000088271 | BET32.0000.00054 | REL PCNF ESTC MANC PRC SETC | NPRG ADJ | MAI | 7435.86 | 2214.33 | 2025-08-18 | 2025-10-31 | 2026-03-26 |  |  |  | U122858
2621 |  | Install Valve | 4000093791 | BET32.0000.00054 | CRTD ESTC CSER MANC NTUP PRC SKKP | NEW CAN | STA | 5126.44 | 0 | 2025-11-18 | 2025-12-05 |  |  |  |  | U122858
2621 |  | BET-Mitchell Ave-Lexington | 4000093901 | BET32.0000.00054 | REL ESTC MACM PRC SETC SKKP | NEW ADJ MIFE | STA | 7976.78 | 0 | 2025-11-19 | 2025-11-19 |  |  |  |  | U122858
2623 |  | STA-Industry Rd Station Upgrade-GEO | 4000090475 | BET32.0000.00059 | REL ESTC MACM PRC SETC SKKP | NEW ADJ WENG | STA | 48273.88 | 1100 | 2025-09-17 | 2025-09-17 |  | 10 | 1 | 2026 | U126783
2621 |  | Duke Rd. / Cooper Dr. Relocation | 4000094778 | BET32.0000.00060 | REL PCNF ESTC MANC PRC SETC | COCO ADJ FCMP | MAI | 11380.49 | 112.75 | 2025-12-05 | 2025-12-19 | 2026-02-13 | 1 | 31 | 2026 | U145347
2629 | RICHMOND | BET-Boone Village Topworks-Richmond | 4000093519 | BET32.0000.00061 | CRTD MANC NMAT NTUP PRC | EST WENG | STA | 0 | 0 | 2025-11-13 | 2026-12-31 |  | 12 | 31 | 2026 | U128885
2629 | PARIS | 2629-Clintonville POD Meter-Paris | 4000095315 | BET32.0000.00062 | CRTD MANC NMAT NTUP PRC | EST WENG | STA | 0 | 0 | 2026-05-01 | 2026-05-29 |  |  |  |  | U128885
2631 |  | CNV-24026357900 INVESTIGATE LAND RIGHTS | 4000096631 | BET32.0000.00063 | REL NMAT PRC SETC | NEW NSFS RCFO | MAI | 0 | 0 | 2024-11-27 | 2024-12-01 |  | 12 | 1 | 2024 | U122858
2631 | ASHLAND | STA-Hoods Creek M&R-Ashland | 4000100700 | BET32.0000.00063 | CRTD ESTC CSER MANC NTUP PRC | PLN ADJ | STA | 2216.72 | 0 | 2026-03-26 | 2026-03-26 |  |  |  |  | U122858
2629 |  | BET-Vojecaro POD Retirement-Winchester | 4000101069 | BET32.0000.00065 | CRTD ESTC CSER MANC PRC SKKP | PLN | MAI | 482621.43 | 0 | 2026-04-02 | 2028-12-31 |  | 12 | 31 | 2028 | U128885
2631 |  | CNV-25026381700 INSTALL 230' OF 2\\\ P. | 4000080051 | GRT32.0000.00002 | REL MANC NMAT PRC SETC | NEW | MAI | 0 | 31499.98 | 2025-02-04 | 2025-02-07 |  | 4 | 14 | 2025 | C_U139391
2623 |  | CNV-22026183001 INSTALL 4955'-2\" PMMP | 4000076873 | GRT32.0000.00004 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2024-11-26 | 2024-12-25 |  | 12 | 25 | 2024 | C_U139391
2631 |  | CNV-23026300300 INSTALL 1810'-2\" PMMP | 4000078083 | GRT32.0000.00019 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 92698.16 | 2024-08-23 | 2024-09-20 | 2025-08-01 | 9 | 20 | 2024 | C_U139391
2629 |  | GRT-Locust Hill Acres MLE-Winchester | 4000078091 | GRT32.0000.00020 | REL PCNF GMPS MANC PRC SETC | COCO ADJ FCMP | MAI | 59513.98 | 163090.85 | 2025-09-11 | 2025-10-31 | 2025-08-03 | 10 | 31 | 2025 | C_U139391
2629 |  | GRT-Harrison Cty HS MLE-Cynthiana | 4000078121 | GRT32.0000.00021 | REL MANC NMAT PRC SETC | NEW NSFS | MAI | 0 | 0 | 2026-02-02 | 2026-10-25 |  | 10 | 25 | 2026 | C_U139391
2632 | MAYSVILLE | RMU REPLACEMENT | 4100801218 | ANC32.0002.00006 | TECO ESTC MANC PRC SETC | NPRG ADJ FCMP MIFE | MAI | 716.3 | 509.66 | 2025-09-19 | 2025-10-17 |  | 1900-01-09 | 1900-01-30 | 1905-07-17 | U122858
2632 | FOSTER | ANC-Heater Repl-Western Hills | 4100853558 | ANC32.0002.00007 | REL ESTC MACM PRC SETC SKKP | NEW | STA | 7268.1 | 29468.84 | 2026-03-06 | 2026-07-03 |  |  |  |  | U122858
2629 |  | GRT-Harrison Cty HS & ATC MLE-Cynthiana | 4000098573 | GRT32.0000.00021 | CRTD MANC NTUP PRC SKKP | PLN ADJ WENG | MAI | 93492.19 | 0 | 2026-04-21 | 2026-10-31 |  |  |  |  | U128885
2629 |  | CNV-25026393800 INSTALL 2,100'-2\\\ PM. | 4000080081 | GRT32.0000.00022 | REL PCNF MANC NMAT PRC SETC | NEW | MAI | 0 | 72432.63 | 2025-05-13 | 2025-05-30 | 2025-08-03 | 5 | 30 | 2025 | C_U139391
2629 |  | CNV-24026310800 INSTALL 1400' OF 2\" PMM | 4000079664 | GRT32.0000.00027 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 46770.14 | 2024-08-29 | 2024-09-10 | 2025-08-01 | 9 | 10 | 2024 | C_U139391
2621 |  | CNV-23026270600 INSTALL 550' OF 2\" PMMP | 4000079301 | GRT32.0000.00038 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 24207.76 | 2024-10-02 | 2024-10-11 | 2025-08-01 | 10 | 11 | 2024 | C_U139391
2623 |  | CNV-23026288901 INSTALL 880'-4\" PMMP | 4000078007 | GRT32.0000.00040 | REL GMPS MANC PRC SETC | NPRG ADJ FCMP | MAI | 382159.46 | 31525.46 | 2025-07-31 | 2025-07-31 |  | 7 | 31 | 2025 | C_U139391
2631 |  | CNV-23026283101 INSTALL 780'-2\" PMMP | 4000077966 | GRT32.0000.00044 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS WENG | MAI | 0 | 25623.87 | 2025-05-21 | 2025-05-30 | 2025-08-03 | 5 | 30 | 2025 | C_U139391
2631 |  | CNV-24026324100 INSTALL 670'-2' PMIP | 4000079766 | GRT32.0000.00051 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 16053.74 | 2024-08-15 | 2024-10-10 | 2025-08-01 | 10 | 10 | 2024 | C_U139391
2633 |  | CNV-24026333600 INSTALL 75'-2\" PMIP | 4000079809 | GRT32.0000.00052 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 14353.53 | 2024-09-19 | 2024-09-20 | 2025-08-01 | 9 | 20 | 2024 | C_U139391
2629 |  | CNV-24026352000 INSTALL 700'-2\\\ PMMP. | 4000079422 | GRT32.0000.00055 | REL PCNF MANC NMAT NTUP PRC SETC | NEW | MAI | 0 | 30619.26 | 2025-01-24 | 2025-01-30 | 2025-08-01 | 1 | 30 | 2025 | C_U139391
2621 |  | GRT-BALL HOMES PENINSULA DOCKSIDE-LEX | 4000076922 | GRT32.0000.00056 | REL PCNF GMPS MANC PRC SETC | NPRG ADJ | MAI | 14249.76 | 79755.73 | 2025-11-18 | 2025-12-31 | 2025-08-01 | 12 | 31 | 2025 | C_U139391
2631 |  | CNV-24026358700 INSTALL 100' OF 2\" PMMP | 4000079852 | GRT32.0000.00057 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 15229.56 | 2024-10-29 | 2024-10-31 | 2025-08-01 | 10 | 31 | 2024 | C_U139391
2621 |  | CNV-24026354300 INSTALL 1750' OF 2\"PMMP | 4000076924 | GRT32.0000.00058 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 29842.78 | 2024-11-14 | 2024-12-31 | 2025-08-01 | 12 | 31 | 2024 | C_U139391
2623 |  | CNV-24026355200 INSTALL 150'-4\" PMLP | 4000079762 | GRT32.0000.00059 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 20757.3 | 2024-12-16 | 2024-12-31 | 2025-08-01 | 12 | 31 | 2024 | C_U139391
2623 |  | CNV-24026355300 INSTALL 250'-2\" PMMP | 4000079764 | GRT32.0000.00060 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 11652.49 | 2024-09-23 | 2024-09-30 |  | 9 | 30 | 2024 | C_U139391
2621 |  | CNV-24026355900 INSTALL 250' OF 2\"PMMP | 4000076926 | GRT32.0000.00061 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 38937.28 | 2024-11-18 | 2024-11-21 | 2025-08-01 | 11 | 21 | 2024 | C_U139391
2623 |  | BALL HOMES ROSE RIDGE PH 2 NB | 4000079845 | GRT32.0000.00062 | REL PCNF GMPS MANC PRC SETC | SCHD ADJ FCMP | MAI | 23249.7 | 49509.72 | 2025-07-16 | 2025-08-01 | 2025-09-02 | 8 | 1 | 2025 | C_U139391
2621 |  | GRT - THE GROVE MLE - NICHOLASVILLE | 4000076970 | GRT32.0000.00063 | REL GMPS MANC PRC SETC | NPRG FCMP | MAI | 399772.9 | 2627219.86 | 2025-09-02 | 2025-11-29 |  | 3 | 16 | 2026 | C_U139391
2621 |  | CNV-24026365700 INSTALL 320' OF 2\\\PM. | 4000076483 | GRT32.0000.00064 | REL MANC NMAT PRC SETC | NEW | MAI | 0 | 17437.01 | 2025-01-02 | 2025-01-10 |  | 1 | 10 | 2025 | C_U139391
2621 |  | CNV-24026368600 INSTALL 640' OF 2\\\ P. | 4000076489 | GRT32.0000.00065 | REL PCNF MANC NMAT PRC SETC | NEW | MAI | 0 | 31021.74 | 2025-05-23 | 2025-06-01 | 2025-08-03 | 6 | 1 | 2025 | C_U139391
2623 |  | CNV-24026372000 INSTALLING 500'-2\" PMMP | 4000079510 | GRT32.0000.00066 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 21681.94 | 2025-02-28 | 2025-03-14 | 2025-08-01 | 3 | 14 | 2025 | C_U139391
2621 |  | SUMMERFIELD MLE CNV-25026385000 BALL HOM | 4000076538 | GRT32.0000.00067 | REL GMPS MANC PRC SETC | SCHD | MAI | 8618.47 | 168479.71 | 2025-09-29 | 2025-11-15 |  | 3 | 10 | 2026 | C_U139391
2633 | PIPPA PASSES | CNV-23026265300 INSTALL PILOT REGULATORS | 4000080000 | GRT32.0000.00068 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 7990.65 | 2024-09-30 | 2024-10-01 | 2025-07-31 | 10 | 1 | 2024 | C_U139391
2631 |  | CNV-25026404300 INSTALL 80' OF 2\" PMMP | 4000075685 | GRT32.0000.00074 | REL MANC PRC SETC | NPRG ADJ FCMP | MAI | 33570.17 | 6906.46 | 2025-08-12 | 2025-08-31 |  |  |  |  | C_U139391
2621 |  | CNV-25026407800 EMER - INSTALL 5'-2\" PM | 4000076694 | GRT32.0000.00075 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 1181.61 | 2025-05-13 | 2025-05-13 |  | 5 | 13 | 2025 | C_U139391
2621 |  | EMER - Retire 5'-2" PMMP | 4000088162 | GRT32.0000.00075 | CRTD MANC NTUP PRC | EST NSFS | MAI | 0 | 0 | 2025-08-18 | 2025-09-05 |  |  |  |  | U122858
2621 | LEXINGTON | CNV-25026408500 INSTALL ANODE BED FOR D. | 4000081875 | GRT32.0000.00076 | REL MANC NMAT PRC SETC | NEW | MAI | 0 | 12635.05 | 2025-12-31 | 2025-12-31 |  |  |  |  | C_U139391
2623 |  | CNV-25026392000 INSTALL 140'-2\" PMMP | 4000080057 | GRT32.0000.00077 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 10453.86 | 2025-02-27 | 2025-05-28 | 2025-08-05 | 5 | 28 | 2025 | C_U139391
2621 |  | DYER COVE MLE CNV-25026398900 | 4000077170 | GRT32.0000.00078 | REL GMPS MANC PRC SETC | NPRG ADJ FCMP | MAI | 7741 | 83056.5 | 2025-08-25 | 2025-09-15 |  | 9 | 15 | 2025 | C_U139391
2629 |  | CNV-24026364900 INSTALL 2,300'-4\" PMMP | 4000079465 | GRT32.0000.00096 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 93727.11 | 2025-01-08 | 2025-01-31 | 2025-08-01 | 1 | 31 | 2025 | C_U139391
2623 |  | 2623 - SOARDS RD ENCROACHMENT PSI GTOWN | 4000088324 | PSI32.0000.00048 | REL ESTC MACM PRC SETC | NEW | PSI | 1.2 | 8831 | 2025-08-19 | 2025-08-19 |  |  |  |  | U127466
2629 |  | GRT-Bourbon Oaks Phase 1 MLE-Paris | 4000079467 | GRT32.0000.00096 | REL PCNF MANC PRC SETC | SCHD ADJ FCMP | MAI | 9884.28 | 46175.8 | 2025-06-20 | 2025-06-30 | 2025-08-05 | 6 | 30 | 2025 | C_U139391
2621 |  | CANCEL | 4000076964 | GRT32.0000.00097 | TECO JBFI MANC PRC SETC | NPRG CAN FCMP | MAI | 0 | -533931.53 | 2025-08-21 | 2025-12-01 |  | 12 | 1 | 2025 | C_U139391
2621 | LEXINGTON | CNV-24026340200 INSTALL 600' OF 8\\\PM. | 4000076966 | GRT32.0000.00097 | REL MANC NMAT PRC SETC | NEW CAN | MAI | 0 | -170812.19 | 2025-01-08 | 2025-01-31 |  | 1 | 31 | 2025 | C_U139391
2621 |  | BET2621 - UK WEST BETTERMENT - LEXINGTON | 4000091870 | GRT32.0000.00097 | REL PCNF ESTC GMPS MANC PRC SETC SKKP | NPRG ADJ FCMP | MAI | 769.08 | 838100.89 | 2025-10-13 | 2025-10-13 | 2025-10-28 |  |  |  | U127466
2629 |  | CNV-24026314400 INSTALL 1,200'-4\\\ PM. | 4000079675 | GRT32.0000.00098 | REL PCNF GMPS MANC NMAT NTUP PRC SETC | NEW | MAI | 0 | 200725.69 | 2025-03-31 | 2025-04-11 | 2025-08-02 | 4 | 11 | 2025 | C_U139391
2629 |  | DO NOT EXECUTE | 4100509755 | GRT32.0000.00098 | REL CSER MANC PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2024-12-31 | 2024-12-31 |  | 12 | 31 | 2024 | C_U139391
2629 |  | CNV-24026370500 ACQUIRE LAND RIGHTS | 4000084802 | GRT32.0000.00098 | REL NMAT PRC SETC | NEW FCMP NSFS REV | LND | 0 | 20000 | 2024-12-31 | 2024-12-31 |  | 12 | 31 | 2024 | C_U141034
2623 |  | CNV-24026339700 OBTAIN HP EASEMENT | 4000076963 | GRT32.0000.00100 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 8024.52 | 2024-11-26 | 2024-12-01 |  | 12 | 1 | 2024 | C_U139391
2623 |  | CNV-24026340300 INSTALL 2280' OF 4\"CSHP | 4000079329 | GRT32.0000.00100 | TECO MANC NMAT PRC SETC | NEW CAN NSFS | MAI | 0 | 108.36 | 2026-11-09 | 2026-12-31 |  | 12 | 31 | 2026 | C_U139391
2621 |  | CNV-24026331500 INSTALL 300' OF 2\"PMMP | 4000076934 | GRT32.0000.00101 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 17818.52 | 2024-10-25 | 2024-10-31 | 2025-07-31 | 10 | 31 | 2024 | C_U139391
2621 |  | CNV-24026341900 INSTALL 4250' OF 2\"/4\" | 4000076411 | GRT32.0000.00102 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 86676.99 | 2024-08-26 | 2024-09-30 | 2025-08-01 | 9 | 30 | 2024 | C_U139391
2621 |  | CNV-24026351200 INSTALL 150' OF 2\"PMIP | 4000076446 | GRT32.0000.00103 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 7979.42 | 2024-09-26 | 2024-09-27 | 2025-08-01 | 9 | 27 | 2024 | C_U139391
2631 |  | CNV-24026359401 INSTALL 200' OF 4\" PMIP | 4000079854 | GRT32.0000.00104 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 7249.07 | 2025-02-13 | 2025-02-19 | 2025-08-01 | 2 | 19 | 2025 | C_U139391
2621 |  | 2621 - ANC - MAXWELL DOWNTOWN SMRP - LEX | 4000095966 |  | CRTD MANC NTUP PRC | EST | MAI | 2.41 | 0 | 2026-01-08 | 2026-01-08 |  |  |  |  | U127466
2631 |  | CNV-24026361400 INSTALL 100' OF 2\\\ P. | 4000079861 | GRT32.0000.00105 | REL PCNF MANC NMAT NTUP PRC SETC | NEW | MAI | 0 | 14243.95 | 2025-02-12 | 2025-02-16 | 2025-08-05 | 3 | 26 | 2025 | C_U139391
2632 |  | CNV-24026366400 INSTALL ~390'-2\" PMIP | 4000079473 | GRT32.0000.00106 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 17758.81 | 2025-02-06 | 2025-02-14 | 2025-08-01 | 2 | 14 | 2025 | C_U139391
2629 |  | CNV-25026381800 INSTALL 250'-2\" PMMP | 4000080053 | GRT32.0000.00107 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 30046.4 | 2025-04-09 | 2025-04-11 | 2025-08-05 | 4 | 11 | 2025 | C_U139391
2621 |  | CNV-25026398800 INSTALL 3670' OF 2\"/4\" | 4000077168 | GRT32.0000.00108 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 67712.09 | 2025-05-02 | 2025-05-30 |  | 5 | 30 | 2025 | C_U139391
2631 |  | CNV-20026949600 PSI FOR CWT HEATER INSTA | 4000078032 | GRT32.0000.00109 | REL NMAT PRC SETC | NEW NSFS | PSI | 0 | 0 | 2025-12-29 | 2025-12-29 |  | 12 | 31 | 2025 | C_U139391
2631 | SOUTH SHORE | CNV-20026971400 INSTALL CWT MODEL 140 HE | 4000078034 | GRT32.0000.00109 | REL NMAT PRC SETC | NEW NSFS | STA | 0 | 0 | 2025-12-23 | 2025-12-31 |  | 12 | 31 | 2025 | C_U139391
2631 |  | CNV-21026122400 OBTAIN EASEMENT FOR MLE | 4000079911 | GRT32.0000.00109 | REL NMAT PRC SETC | NEW NSFS | PSI | 0 | 0 | 2025-12-30 | 2025-12-30 |  | 12 | 31 | 2025 | C_U139391
2631 |  | CNV-22026162900 INVESTIGATE/BUY-OUT CUST | 4000082435 | GRT32.0000.00109 | REL CSER NMAT PRC SETC | NEW NSFS | PSI | 0 | 0 | 2049-12-31 | 2049-12-31 |  |  |  |  | C_U139391
2629 |  | 2629-Patsy Way MLE-Mt Sterling | 4000085472 | GRT32.0000.00118 | REL ESTC GMPS MANC PRC SETC | NPRG ADJ | MAI | 26720.71 | 23675.7 | 2025-07-31 | 2025-10-30 |  | 10 | 31 | 2025 | U128885
2623 |  | 275 Heritage Dr MLE Versailles | 4000085536 | GRT32.0000.00119 | TECO PCNF ESTC GMPS JBFI MANC PRC SETC | NPRG ADJ FCMP MIFE | MAI | 15748.01 | 10194.51 | 2025-07-30 | 2025-08-14 | 2026-03-04 |  |  |  | U126783
2631 | ASHLAND | GRT - 2804 PLEASANT AVE MLE - ASHLAND | 4000086902 | GRT32.0000.00120 | REL ESTC GMPS MANC PRC SETC | SCHD FCMP | MAI | 30420.98 | 217321.22 | 2025-10-01 | 2025-10-31 |  | 10 | 31 | 2025 | U141016
2623 |  | GRT-Paddocks of Frankfort MLE | 4000086825 | GRT32.0000.00121 | REL PCNF ESTC GMPS MANC PRC SETC | SCHD REV | MAI | 596391.42 | 753323.74 | 2025-09-02 | 2025-12-31 | 2026-03-12 | 5 | 1 | 2026 | U126783
2621 |  | 2621-Ball Homes Masterson Hills-Lex.. | 4000088260 | GRT32.0000.00122 | REL ESTC MACM PRC SETC | NEW | MAI | 35331.68 | 0 | 2025-08-18 | 2025-08-18 |  |  |  |  | U128885
2621 |  | BALL HOMES - MASTERSON HILLS MLE | 4000087198 | GRT32.0000.00122 | REL ESTC GMPS MANC PRC SETC | COCO ADJ FCMP | MAI | 68908.83 | 136154.07 | 2025-09-03 | 2025-10-18 |  | 10 | 18 | 2025 | U145347
2621 |  | GRT-BALL HOMES SUMMERFIELD-LEXINGTON | 4000087365 | GRT32.0000.00123 | CRTD ESTC MANC NTUP PRC RELR | NEW ADJ WENG | MAI | 39021.25 | 0 | 2025-12-17 | 2026-02-14 |  | 2 | 14 | 2026 | U145347
2621 |  | GRT - PALOMAR FOUNTAINS MLE - LEXINGTON | 4000087395 | GRT32.0000.00124 | REL PCNF ESTC GMPS MANC PRC SETC | NPRG ADJ | MAI | 102007.66 | 101406.76 | 2025-09-02 | 2025-12-31 | 2026-04-13 | 5 | 1 | 2026 | U141016
2621 |  | UK DORM WOODLAND | 4000087397 | GRT32.0000.00125 | TECO ESTC GMPS JBFI MANC PRC SETC | SCHD ADJ FCMP | MAI | 61809.85 | 35464.16 | 2025-08-06 | 2025-08-30 |  |  |  |  | U141016
2621 |  | RE-CREATE UK DORM WOODLAND JO | 4000088355 | GRT32.0000.00125 | REL MACM PRC SETC | NEW NSFS | MAI | 65702.01 | 0 | 2025-08-19 | 2025-08-19 |  |  |  |  | U141016
2623 |  | Fortune Dr Frankfort Tierney MLE | 4000087557 | GRT32.0000.00126 | REL ESTC GMPS MANC PRC SETC SKKP | NPRG ADJ | MAI | 85824.43 | 208369.03 | 2025-08-07 | 2025-08-07 |  |  |  |  | U126783
2629 | WINCHESTER | 2629-Deer Lawn MLE-Winchester | 4000087556 | GRT32.0000.00127 | CRTD ESTC MANC NTUP PRC | PLN ADJ WENG | MAI | 93130.66 | 0 | 2026-04-21 | 2026-08-31 |  |  |  |  | U128885
2621 |  | 2621-Quintana Estates MLE-Lexington WMS. | 4000088317 | GRT32.0000.00130 | REL PCNF ESTC GMPS MANC PRC SETC SKKP | SCHD FCMP | MAI | 163229.55 | 119825.18 | 2025-09-17 | 2025-11-14 | 2025-10-06 | 11 | 14 | 2025 | U128885
2621 |  | CNV-25026392200 DESIGN CONFLICT RELOCATI | 4000093964 | GRT32.0000.00130 | REL NMAT PRC SETC | NEW NSFS RCFO | MAI | 0 | 0 | 2025-04-30 | 2025-04-30 |  | 5 | 1 | 2025 | U141016
2621 |  | GRT - CARRIAGE LN MLE - LEXINGTON | 4000088552 | GRT32.0000.00131 | REL ESTC GMPS MANC PRC SETC | COCO FCMP | MAI | 495629.82 | 357427.11 | 2025-10-01 | 2025-12-31 |  | 12 | 31 | 2025 | U141016
2631 | Wurtland | 2631 - 206 Jacobs Ln - Wurtland | 4000088502 | GRT32.0000.00132 | CRTD ESTC MANC PRC | PLN ADJ CAN NSFS WENG | MAI | 36503.51 | 0 | 2025-08-20 | 2025-11-01 |  |  |  |  | U141016
2631 |  | GRT-206 JACOBS LN MLE-WURTLAND | 4000093040 | GRT32.0000.00132 | REL ESTC GMPS MANC PRC SETC | NPRG FCMP | MAI | 33358.89 | 31397.95 | 2026-01-12 | 2026-01-31 |  |  |  |  | U141016
2623 |  | Ball Homes South Crossing P3 Georgetown | 4000087665 | GRT32.0000.00133 | REL ESTC GMPS MANC PRC SETC | NEW ADJ | MAI | 367711.37 | 281612.34 | 2025-09-02 | 2025-11-01 |  | 11 | 1 | 2025 | U126783
2623 |  | ACE HARDWARE MIDWAY | 4000088987 | GRT32.0000.00134 | TECO ESTC GMPS JBFI MANC PRC SETC | NPRG ADJ FCMP WENG | MAI | 46804.6 | 382863.3 | 2025-09-02 | 2025-10-31 |  | 10 | 31 | 2025 | U126783
2623 |  | Ball Homes Payne Crossing P2 Versailles | 4000089773 | GRT32.0000.00135 | REL ESTC GMPS MANC PRC SETC | NPRG ADJ FCMP | MAI | 164510.5 | 250951.48 | 2025-09-04 | 2025-09-04 |  |  |  |  | U126783
2623 |  | GRT-Elkhorn Village Georgetown West | 4000089985 | GRT32.0000.00136 | CRTD MANC NTUP PRC | EST | MAI | 177.5 | 0 | 2026-04-16 | 2026-08-29 |  |  |  |  | U126783
2631 |  | GRT - 2029 FERN DR MLE - LOUISA | 4000090832 | GRT32.0000.00139 | REL ESTC GMPS JBFI MANC PRC SETC | NPRG FCMP | MAI | 31131.04 | 13372.78 | 2025-12-01 | 2025-12-10 |  | 12 | 10 | 2025 | U141016
2631 | Russell | GRT - 124 AUDOBON CT MLE - RUSSELL | 4000090908 | GRT32.0000.00140 | TECO PCNF ESTC GMPS MANC PRC SETC SKKP | SCHD FCMP | MAI | 46515.12 | 72150.8 | 2026-02-25 | 2026-03-09 | 2026-02-13 | 3 | 9 | 2026 | U141016
2629 |  | GRT-Boones Crossing MLE-Winchester | 4000090868 | GRT32.0000.00141 | REL ESTC MANC PRC SETC SKKP | NEW NSFS WENG WLND WPMT WSTR | MAI | 377533.57 | 31474.64 | 2026-04-30 | 2026-07-31 |  | 7 | 31 | 2026 | U128885
2629 |  | GRT-Mcclure Rd Betterment-Winchester | 4000103310 | GRT32.0000.00141 | CRTD MANC PRC | EST | MAI | 120214.83 | 0 | 2026-05-14 | 2026-12-31 |  |  |  |  | U128885
2623 |  | 2623-VILLAGE AT LEMON MILL-GEORGETOWN | 4000090938 | GRT32.0000.00142 | REL PCNF ESTC GMPS MANC PRC SETC | NPRG ADJ FCMP | MAI | 107957.12 | 89467.15 | 2026-02-15 | 2026-03-31 | 2026-03-13 | 3 | 31 | 2026 | U126783
2629 |  | Design for CU Tab | 4000101075 |  | CRTD MANC NMAT NTUP PRC | EST | PSI | 0 | 0 | 2026-04-02 | 2026-04-02 |  |  |  |  | U128885
2623 | Nicholasville | 2621-50 & 52 LANTERN WAY-NICHOLASVILLE | 4000091838 | GRT32.0000.00143 | TECO ESTC GMPS JBFI MANC NTUP PRC SETC | NPRG FCMP REV | MAI | 22677.35 | 60519.1 | 2025-10-09 | 2025-10-09 |  |  |  |  | U126783
|  | BET-Rolling Hills POD-Winchester | 4000102399 |  | CRTD MANC NMAT NTUP PRC | EST WENG | STA | 0 | 0 | 2026-04-28 | 2030-12-31 |  |  |  |  | U128885
2623 | Georgetown | GRT-RUMPKE CNG MLE-GEORGETOWN | 4000092061 | GRT32.0000.00144 | REL PCNF ESTC GMPS MANC NTUP PRC SETC* | SCHD ADJ | MAI | 252594.58 | 94560.87 | 2026-05-04 | 2026-07-01 | 2026-05-12 | 7 | 1 | 2026 | U126783
2621 | LEXINGTON | GRT-TURNER COMMONS MLE-LEXINGTON | 4000092674 | GRT32.0000.00145 | REL ESTC GMPS MANC PRC PRTB SETC SKKP | NPRG | MAI | 81269.6 | 133757.7 | 2025-10-28 | 2025-12-01 |  |  |  |  | U141016
2632 |  | GRT-350 AA Hwy Grocery-Maysville | 4000093143 | GRT32.0000.00147 | CRTD ESTC MANC NTUP PRC SKKP | PLN ADJ | MAI | 135201.42 | 0 | 2026-04-21 | 2026-12-31 |  |  |  |  | U122858
2621 |  | GRT-LEGACY BUSINESS PARK MLE-LEXINGTON | 4000093541 | GRT32.0000.00148 | REL ESTC MACM PRC SETC SKKP | NEW WENG WLND | MAI | 922940.88 | 0 | 2026-04-21 | 2026-11-07 |  |  |  |  | U141016
2621 | LEXINGTON | GRT - SPRINGS AT POLO CLUB - LEXINGTON | 4000093774 | GRT32.0000.00149 | REL PCNF ESTC CSER GMPS MANC PRC SETC | COCO FCMP | MAI | 48540.19 | 73287.2 | 2026-03-23 | 2026-04-20 | 2026-03-25 | 4 | 20 | 2026 | U141016
2623 |  | 2623-SHOPS AT WOODFORD FARM-VERSAILLES | 4000093861 | GRT32.0000.00150 | CRTD ESTC MANC NTUP PRC SKKP | PLN ADJ WENG | MAI | 183861.61 | 0 | 2026-04-21 | 2026-12-19 |  |  |  |  | U126783
2621 |  | Design for CU Tab | 4000086376 |  | CRTD MANC NMAT NTUP PRC | EST | PSI | 0 | 0 | 2025-07-23 | 2025-07-23 |  |  |  |  | U132703
2621 |  | GRT-THE SANCUARY MLE-(CANCELED) | 4000094269 | GRT32.0000.00151 | CRTD MANC NTUP PRC | EST CAN | MAI | 10207.86 | 0 | 2025-11-25 | 2026-10-30 |  |  |  |  | U145347
2621 |  | GRT-THE SANCTUARY MLE-(CANCELED) | 4000097238 | GRT32.0000.00151 | CRTD ESTC CSER MANC NTUP PRC SKKP | PLN CAN | MAI | 209798.46 | 0 | 2026-01-29 | 2026-12-31 |  |  |  |  | U145347
2621 |  | GRT-THE SANCTUARY MLE-LEXINGTON | 4000100570 | GRT32.0000.00151 | CRTD ESTC CSER MANC NTUP PRC | PLN WENG | MAI | 219626.52 | 0 | 2026-03-25 | 2026-12-31 |  |  |  |  | U145347
2631 |  | GRT-BOURBON STREET MLE-GREENUP | 4000095213 | GRT32.0000.00152 | CRTD ESTC MANC NTUP PRC | PLN NSFS | MAI | 658417.65 | 0 | 2026-12-31 | 2026-12-31 |  |  |  |  | U141016
2631 | ASHLAND | GRT-STARBUCKS CAMP LANDING-ASHLAND | 4000095261 | GRT32.0000.00153 | CRTD MANC PRC | EST | MAI | 4603.7 | 0 | 2026-01-24 | 2026-01-30 |  |  |  |  | U141016
2621 |  | Design for CU Tab | 4000086389 |  | CRTD MANC NMAT NTUP PRC | EST | PSI | 0 | 0 | 2025-07-24 | 2025-07-24 |  |  |  |  | U132703
2631 |  | GRT - 995 FERN DR MLE - LOUISA | 4000095304 | GRT32.0000.00154 | CRTD ESTC MANC NTUP PRC | PLN CAN WENG | MAI | 32209.98 | 0 | 2026-06-04 | 2026-06-11 |  |  |  |  | U141016
2629 |  | GRT-College Hill Estates MLE-Waco | 4000096101 | GRT32.0000.00155 | CRTD ESTC MANC NTUP PRC | PLN ADJ WENG | MAI | 288392.89 | 0 | 2026-04-21 | 2026-10-31 |  |  |  |  | U128885
2631 | GREENUP | GRT - ALICE STREET MLE-GREENUP | 4000097588 | GRT32.0000.00156 | CRTD ESTC MANC NTUP PRC | PLN NSFS | MAI | 49442.4 | 0 | 2026-03-18 | 2026-03-25 |  |  |  |  | U141016
2629 |  | GRT-Mt Sterling Rd Development-Wincheste | 4000097611 | GRT32.0000.00157 | CRTD ESTC CSER MANC PRC SKKP | PLN ADJ WENG | MAI | 1145544.29 | 0 | 2026-08-01 | 2026-12-31 |  |  |  |  | U128885
2623 |  | Design for CU Tab | 4000086437 |  | CRTD MANC NMAT NTUP PRC | EST | PSI | 0 | 0 | 2025-07-24 | 2025-07-24 |  |  |  |  | U132703
2621 |  | GRT-HARTLAND PKWY MLE-LEXINGTON | 4000097613 | GRT32.0000.00158 | CRTD MANC NTUP PRC SKKP | NEW CAN NSFS REV WLND | MAI | 27177.48 | 0 | 2026-02-05 | 2026-04-30 |  |  |  |  | U145347
2621 |  | GRT - LUCILLE DR MLE - LEX | 4000097883 | GRT32.0000.00159 | REL PCNF ESTC GMPS MANC PRC SETC | NPRG ADFR FCMP | MAI | 235026.11 | 89202.77 | 2026-03-03 | 2026-03-25 | 2026-03-09 |  |  |  | U127466
2623 |  | ps & i for capitol ave | 4000088340 | PSI32.0000.00045 | CRTD MANC NMAT NTUP PRC | EST CAN | PSI | 0 | 0 | 2025-08-19 | 2025-08-19 |  |  |  |  | U132703
2623 |  | CARDINAL AVE SMRP | 4000088395 | PSI32.0000.00047 | CRTD MANC NMAT NTUP PRC | EST CAN | PSI | 0 | 0 | 2025-08-19 | 2025-08-19 |  |  |  |  | U132703
2623 |  | E COLLEGE ST - SMRP | 4000088396 | PSI32.0000.00046 | CRTD MANC NMAT NTUP PRC | EST CAN | PSI | 0 | 0 | 2025-08-19 | 2025-08-19 |  |  |  |  | U132703
2631 |  | GRT - SPRINGHAVEN ST MLE - CATLETTSBURG | 4000097946 | GRT32.0000.00160 | REL PCNF ESTC CSER GMPS MANC PRC SETC* | COCO FCMP | MAI | 25818.31 | 21189.24 | 2026-05-07 | 2026-05-15 | 2026-04-22 |  |  |  | U141016
2621 |  | GRT-BALL HOMES PATCHEN WILKES-LEXINGTON | 4000098070 | GRT32.0000.00161 | REL PCNF ESTC CSER GMPS MANC PRC SETC | NPRG ADJ WENG | MAI | 539151.6 | 118963.06 | 2026-04-15 | 2026-06-05 | 2026-04-13 |  |  |  | U126783
2629 |  | GRT-Colby Rd Development MLE-Winchester | 4000099022 | GRT32.0000.00162 | REL ESTC MACM PRC SETC SKKP | NEW ADJ NSFS | MAI | 123656.17 | 1032.61 | 2026-08-01 | 2026-08-31 |  | 8 | 31 | 2026 | U128885
2629 | Mount Sterling | GRT-Countryside Dr MLE-Mt Sterling | 4000099212 | GRT32.0000.00163 | CRTD ESTC MANC NTUP PRC | PLN CAN | MAI | 315961.06 | 0 | 2026-03-06 | 2026-03-13 |  |  |  |  | U128885
2621 |  | GRT-KROGER PATCHEN WILKES-LEXINGTON | 4000099571 | GRT32.0000.00164 | REL MANC PRC SETC SKKP | NEW ADJ NSFS WENV WLND | MAI | 263714.23 | 0 | 2026-05-06 | 2026-10-10 |  |  |  |  | U145347
2623 |  | GRT-LIVESTOCK INNOVATION CENTER MLE-VER | 4000100528 | GRT32.0000.00165 | CRTD ESTC CSER MANC NTUP PRC SKKP | PLN WENG | MAI | 111669.28 | 0 | 2026-03-24 | 2026-03-24 |  |  |  |  | U126783
2631 |  | GRT-SOUTH OHIO MED CENTER MLE-RACELAND | 4000100519 | GRT32.0000.00166 | REL ESTC CSER GMPS MACM PRC SETC SKKP | NEW | MAI | 47565.64 | 886.74 | 2026-06-15 | 2026-06-25 |  |  |  |  | U141016
2631 |  | ANC-SOUTH OHIO MED CENTER BET-RACELAND | 4000100580 | GRT32.0000.00166 | CRTD ESTC CSER MANC NTUP PRC | PLN | MAI | 122201.95 | 0 | 2026-06-01 | 2026-06-25 |  |  |  |  | U141016
2621 |  | GRT-WILLOWS AT ANDOVER-LEXINGTON | 4000100966 | GRT32.0000.00168 | REL ESTC MANC PRC SETC | NEW WGMA WLND | MAI | 277736.39 | 0 | 2026-04-01 | 2026-10-31 |  |  |  |  | U145347
2631 |  | GRT - 41 TOWN HILL RD MLE - LOUISA | 4000101837 | GRT32.0000.00169 | CRTD ESTC CSER MANC PRC SKKP | PLN ADJ WENG | MAI | 49724.33 | 0 | 2026-06-16 | 2026-06-26 |  |  |  |  | U141016
2621 |  | GRT-3258 AQUEDUCT DR. MLE-LEXINGTON | 4000102117 | GRT32.0000.00170 | CRTD ESTC MANC NTUP PRC | PLN WENG WLND | MAI | 43771.49 | 0 | 2026-04-22 | 2026-07-03 |  |  |  |  | U145347
2623 |  | GRT-GEORGETOWN COMMONS MLE-GEORGETOWN | 4000102522 | GRT32.0000.00171 | CRTD ESTC CSER MANC PRC SKKP | PLN ADJ | MAI | 556155.87 | 0 | 2026-04-29 | 2026-04-29 |  |  |  |  | U126783
2623 |  | GRT-Ball Homes Old Oxford P4-Georgetown | 4000103017 | GRT32.0000.00172 | CRTD ESTC MANC NTUP PRC SKKP | PLN ADJ | MAI | 489395.77 | 0 | 2026-05-08 | 2026-05-08 |  |  |  |  | U126783
2629 | MOUNT STERLING | Maintenance of Main / Check CP low read | 4100807913 | ANC32.0002.00006 | REL ESTC MANC NMAT PRC SETC | NPRG FCMP MIFE | MAI | 518.07 | 2086.74 | 2025-10-23 | 2026-10-18 |  | 1899-12-31 | 1900-01-15 | 1905-07-19 | U133262
2629 | CYNTHIANA | Remediate Test Point Issues | 4100809328 | ANC32.0002.00006 | REL MANC NMAT PRC SETC | NPRG FCMP | MAI | 518.07 | 2775.65 | 2025-10-29 | 2026-10-24 |  | 1899-12-31 | 1900-01-21 | 1905-07-19 | U133262
2629 | CYNTHIANA | Remediate Test Point Issues | 4100809572 | ANC32.0002.00006 | CRTD MANC NMAT NTUP PRC | NEW CAN | MAI | 0 | 0 | 2025-10-30 | 2026-10-25 |  | 1899-12-31 | 1900-01-22 | 1905-07-19 | U133262
2621 |  | GRT-1336 TANFORAN DR MLE-LEXINGTON | 4000103899 | GRT32.0000.00173 | CRTD ESTC MANC NTUP PRC | PLN NSFS WENG | MAI | 11147.6 | 0 | 2026-06-22 | 2026-06-26 |  |  |  |  | U141016
2621 |  | GRT-Rocky Mountain Cir MLE - Lex | 4000101699 | GRT32.0000.00174 | CRTD MANC NTUP PRC | EST WENG | MAI | 2.2 | 0 | 2026-04-14 | 2026-07-30 |  |  |  |  | U132703
2623 | GEORGETOWN | MOVE METER/4100776679 | 4100795172 | GRT32.0002.00001 | CRTD MANC NMAT NTUP PRC | EST | MAI | 0 | 0 | 2025-09-02 | 2026-07-29 |  | 8 | 28 | 2026 | U132386
2629 |  | DO NOT EXECUTE | 4100509593 | GRT32.0002.00002 | REL MANC PRC SETC | NEW CAN NSFS | LND | 4.32 | 0 | 2025-12-30 | 2025-12-31 |  | 12 | 31 | 2025 | C_U139391
2629 |  | DO NOT EXECUTE | 4100577488 | GRT32.0002.00002 | REL MANC PRC SETC | SCHD CAN | LND | 2.72 | 0 | 2024-12-31 | 2024-12-31 |  | 12 | 31 | 2024 | C_U139391
2629 |  | CNV-22026207901 PM- LAND MILLER DR POD | 4000083412 | GRT32.0002.00002 | REL NMAT PRC SETC | NEW NSFS REV | LND | 0 | 0 | 2024-12-31 | 2024-12-31 |  | 12 | 31 | 2024 | C_U141034
2629 |  | CNV-24026340500 ACQUIRE EASEMENT | 4000084793 | GRT32.0002.00002 | TECO JBFI NMAT PRC SETC | NEW FCMP NSFS | LND | 0 | 17825 | 2025-12-30 | 2025-12-31 |  | 12 | 31 | 2025 | C_U141034
2621 |  | GRT - SVU NEW BUILDING - BUENA VISTA | 4000094276 | GRT38.0000.00423 | CRTD ESTC MANC NTUP PRC | PLN ADJ NSFS | MAI | 454769.21 | 0 | 2025-11-25 | 2025-12-31 |  |  |  |  | U146250
2633 |  | CNV-24026345800 INSTALL 1400'-2\\\ PMI. | 4000079383 | PIG32.0000.00001 | REL PCNF MANC NMAT NTUP PRC SETC | NEW | MAI | 0 | 107970.38 | 2025-03-26 | 2025-04-15 | 2025-08-01 | 4 | 15 | 2025 | C_U139391
2623 |  | CNV-23026301200 INSTALL 60' OF 6\"PMMP M | 4000078089 | PIG32.0000.00007 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | -18585.12 | 2025-03-26 | 2025-04-01 | 2025-08-02 | 4 | 1 | 2025 | C_U139391
2621 |  | CNV-24026361300 INSTALL 750'-2\\\ PMMP. | 4000076145 | PIG32.0000.00011 | REL PCNF GMPS MANC NMAT PRC SETC | NEW | MAI | 0 | 171116.42 | 2025-03-04 | 2025-03-30 | 2025-08-01 | 3 | 30 | 2025 | C_U139391
2629 |  | SANDE RIDGE RELOCATION | 4000088349 | PSI32.0000.00049 | REL ESTC MACM PRC SETC | NEW CAN FCMP NSFS | PSI | 4694.82 | 0 | 2025-08-19 | 2025-11-30 |  |  |  |  | U141016
2632 |  | CNV-24026357400 INSTALL 275'-3\" CSMP | 4000079847 | PIG32.0000.00012 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 47284.21 | 2024-10-17 | 2024-10-30 | 2025-08-01 | 10 | 30 | 2024 | C_U139391
2621 |  | CNV-24026363100 INSTALL 481'-8\" CSHP | 4000076459 | PIG32.0000.00013 | REL PCNF MANC PRC SETC | COCO ADJ FCMP RSHD | MAI | 195428.52 | 47018.3 | 2025-07-15 | 2025-07-30 | 2025-09-06 | 7 | 30 | 2025 | C_U139391
2621 |  | retire pipe | 4000088089 | PIG32.0000.00013 | CRTD MANC NTUP PRC | EST NSFS | MAI | 0 | 0 | 2025-08-15 | 2025-08-29 |  |  |  |  | U122858
2621 |  | CNV-24026370600 INSTALL 32'-6\" PMLP | 4000082483 | PIG32.0000.00014 | REL PCNF MANC PRC SETC | NEW ADJ FCMP NSFS WENG | MAI | 790.12 | 4096.57 | 2025-05-23 | 2025-05-30 | 2025-08-02 |  |  |  | C_U139391
2621 |  | 2621-LAND RENEW LEASE AGREEMENT (200103) | 4000089074 | PSI32.0000.00050 | REL ESTC MACM PRC SETC | NEW NSFS | PSI | 30810.1 | 18091.32 | 2025-08-29 | 2025-12-31 |  |  |  |  | U141016
2629 |  | Design for CU Tab | 4000090027 |  | CRTD MANC NMAT NTUP PRC | EST | PSI | 0 | 0 | 2025-09-09 | 2025-09-09 |  |  |  |  | U141016
2621 |  | CNV-24026370700 RETIRE 20'-6\" BSLP | 4000082484 | PIG32.0000.00014 | REL PCNF MANC PRC SETC | COCO FCMP NSFS WENG | MAI | 44.58 | 6023.38 | 2025-05-30 | 2025-05-30 | 2025-08-03 |  |  |  | C_U139391
2621 |  | CNV-25026378600 INSTALL 42' OF 2\"/4\" P | 4000077139 | PIG32.0000.00015 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 13087.99 | 2025-02-26 | 2025-03-01 | 2025-08-01 | 3 | 1 | 2025 | C_U139391
2621 |  | CNV-25026402200 INSTALL 270' OF 8"CSHP | 4000077173 | PIG32.0000.00016 | REL MANC PRC SETC | COCO ADJ FCMP MIFE | MAI | 34375.7 | 21065.27 | 2025-07-11 | 2025-07-31 |  | 7 | 31 | 2025 | C_U139391
2621 |  | UK PMMP RELOCATION-25026402500 INSTALL 3 | 4000077175 | PIG32.0000.00016 | REL PCNF MANC PRC SETC | NEW ADJ FCMP | MAI | 37503.8 | -58733.53 | 2025-07-16 | 2025-07-31 | 2025-08-03 | 7 | 31 | 2025 | C_U139391
2621 |  | CNV-24026312700 RETIRE 310' OF 2\"PMMP M | 4000075945 | PIG32.0000.00017 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1335.37 | 2024-11-27 | 2024-12-01 | 2025-07-31 | 12 | 1 | 2024 | C_U139391
2621 |  | CNV-24026339400 RETIRE 322'-4\" CSLP | 4000076108 | PIG32.0000.00022 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2689.01 | 2024-09-30 | 2024-10-01 | 2025-07-31 | 10 | 1 | 2024 | C_U139391
2621 |  | CNV-25026409400 INSTALL ANODE BED. | 4000076696 | PIG32.0000.00024 | REL MANC NMAT PRC SETC | NEW | MAI | 0 | 13182.42 | 2025-12-23 | 2025-12-23 |  | 12 | 31 | 2025 | C_U139391
2621 |  | CNV-24026363000 NEW CIRCLE RD REVISION | 4000081389 | PIG32.0000.00027 | TECO JBFI MANC NMAT PRC SETC | NEW CAN FCMP NSFS RECL | PSI | 0.76 | 39676.23 | 2025-12-31 | 2025-12-31 |  | 12 | 31 | 2025 | C_U139391
2621 |  | CNV-24026376901 INSTALL 1218'-6\" PMMP | 4000076501 | PIG32.0000.00028 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 4735.83 | 2025-02-28 | 2025-04-30 |  | 4 | 30 | 2025 | C_U139391
2621 |  | CNV-24026377000 RETIRE 1140'-6\" PMP | 4000076503 | PIG32.0000.00028 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 571.78 | 2025-09-30 | 2025-09-30 |  | 9 | 30 | 2025 | C_U139391
2621 |  | CNV-24026370200 INSTALL 1415'-2\" PMMP | 4000076495 | PIG32.0000.00030 | REL PCNF MANC PRC SETC | SCHD ADJ MIFE | MAI | 1.78 | 78682.95 | 2025-04-24 | 2025-05-30 | 2025-08-05 | 5 | 30 | 2025 | C_U139391
2621 |  | CNV-24026370300 RETIRE 679'-3\" CSMP | 4000076497 | PIG32.0000.00030 | REL PCNF NMAT PRC SETC | NEW NSFS | MAI | 0 | 643.86 | 2025-05-30 | 2025-05-30 | 2025-08-05 | 5 | 30 | 2025 | C_U139391
2621 |  | CNV-24026360500 INSTALL 18'-2\" PMMP | 4000076142 | PIG32.0000.00037 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 8026.04 | 2024-11-22 | 2024-11-30 | 2025-08-01 | 11 | 30 | 2024 | C_U139391
2621 |  | CNV-24026360600 RETIRE 10'-2\" PMMP | 4000076143 | PIG32.0000.00037 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3300.87 | 2024-11-27 | 2024-11-30 | 2025-08-01 | 11 | 30 | 2024 | C_U139391
2621 |  | CNV-23026254900 INSTALL 620' OF 8\"CSHP | 4000079260 | PIG32.0000.00038 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 121750.93 | 2024-07-23 | 2024-10-01 | 2025-07-31 | 10 | 1 | 2024 | C_U139391
2621 |  | CNV-23026255000 RETIRE 620' OF 8\"CSHP M | 4000079262 | PIG32.0000.00038 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 349.8 | 2024-10-01 | 2024-10-01 |  | 10 | 1 | 2024 | C_U139391
2621 | LEXINGTON | CNV-24026358801 INSTALL 4200' OF 2\\\"/. | 4000076968 | PIG32.0000.00039 | REL CSER MANC NMAT PRC SETC | NEW REV | MAI | 0 | 50990.81 | 2024-09-19 | 2025-06-01 |  | 6 | 1 | 2025 | C_U139391
2621 |  | CNV-24026360700 INSTALL 230' OF 4\"PMLP | 4000076972 | PIG32.0000.00039 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 38.22 | 2025-05-30 | 2025-06-01 |  | 6 | 1 | 2025 | C_U139391
2631 |  | CNV-23026279500 INSTALL 339'-8\" PMLP | 4000077920 | PIG32.0000.00041 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 24140.5 | 2024-12-13 | 2024-12-30 | 2025-07-31 | 12 | 30 | 2024 | C_U139391
2631 |  | CNV-23026279600 RETIRE 339'-8\" BSLP | 4000077922 | PIG32.0000.00041 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1460.29 | 2024-05-10 | 2024-12-30 | 2025-07-31 | 12 | 30 | 2024 | C_U139391
2621 |  | CNV-24026328800 NEWTOWN PIKE MP RELOCATI | 4000076930 | PIG32.0000.00043 | REL MANC PRC SETC | NEW ADJ NSFS | MAI | 136097.17 | 1897.5 | 2025-07-09 | 2025-08-30 |  | 9 | 5 | 2025 | C_U139391
2621 |  | CNV-24026329000 INSTALL 175' OF 4\" CSHP | 4000076932 | PIG32.0000.00043 | REL PCNF MANC PRC SETC | COCO ADJ FCMP | MAI | 188082.25 | 193324.54 | 2025-07-16 | 2025-09-01 | 2025-08-01 | 9 | 1 | 2025 | C_U139391
2621 |  | CNV-23026304900 INSTALL 4450' OF 2-4\" P | 4000079401 | PIG32.0000.00043 | REL PCNF GMPS MANC PRC SETC | NPRG ADJ | MAI | 6357.31 | 1345562.37 | 2025-07-15 | 2025-10-03 | 2025-08-03 | 10 | 3 | 2025 | C_U139391
2631 |  | CNV-24026348900 INSTALL 70'-8\" PMMP | 4000079390 | PIG32.0000.00047 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 59062.03 | 2024-10-10 | 2024-10-30 | 2025-08-01 | 10 | 30 | 2024 | C_U139391
2631 |  | CNV-24026349000 RETIRE 70' OF 10\"CSMP M | 4000079392 | PIG32.0000.00047 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 116.6 | 2024-10-30 | 2024-10-30 |  | 10 | 30 | 2024 | C_U139391
2631 |  | CNV-24026367500 INSTALL 1600'-2\" PMMP | 4000079479 | PIG32.0000.00049 | REL PCNF GMPS MANC PRC SETC | NEW ADJ FCMP NSFS WENG | MAI | 179.48 | 305253.06 | 2025-05-13 | 2025-07-01 | 2025-08-03 | 7 | 1 | 2025 | C_U139391
2629 |  | CNV-24026358600 INSTALL 175' - 4\\\ PM. | 4000079850 | PIG32.0000.00050 | REL PCNF MANC NMAT NTUP PRC SETC | NEW REV | MAI | 0 | 39248.49 | 2024-10-24 | 2024-12-31 | 2025-08-01 | 12 | 31 | 2024 | C_U139391
2629 |  | 2629 - 325 SANDE RIDGE LN - MT. STERLING | 4000086733 | PIG32.0000.00051 | REL ESTC GMPS MANC PRC SETC | COCO FCMP | MAI | 37169.36 | 28187.08 | 2025-07-28 | 2025-10-28 |  | 10 | 28 | 2025 | U141016
2629 |  | SANDE RIDGE RELOCATION | 4000090053 | PIG32.0000.00051 | CRTD MANC PRC | NEW NSFS RCFO | MAI | 4694.82 | 0 | 2025-08-19 | 2025-11-30 |  |  |  |  | U141016
2629 |  | SANDE RIDGE RELOCATION | 4000093966 | PIG32.0000.00051 | CRTD MANC PRC | NEW NSFS RCFO | MAI | 4694.82 | 0 | 2025-08-19 | 2025-11-30 |  |  |  |  | U141016
2621 |  | PSI-ALUMNI DRIVE PATH RELO-LEXINGTON | 4100832925 | PSI32.0000.00053 | REL ESTC GMPS MANC PRC SETC SKKP | NEW NSFS | PSI | 13106.22 | 21817.42 | 2026-01-15 | 2026-03-02 |  |  |  |  | U141016
2629 |  | 325 SANDE RIDGE LN RELOC. 25026409100 | 4100780082 | PIG32.0000.00051 | CRTD MANC NMAT NTUP PRC | EST CAN | MAI | 0 | 0 | 2025-07-28 | 2025-10-28 |  |  |  |  | U141016
2633 |  | PIG-KY 292 Shallow Main-South Williamson | 4000088505 | PIG32.0000.00052 | REL PCNF GMPS MANC PRC SETC | NPRG ADJ MIFE RCFO | MAI | 1406753.85 | 280696.77 | 2026-01-19 | 2026-06-30 | 2026-04-13 | 12 | 31 | 2026 | U938437
2623 |  | Finnely Development | 4000086944 | PIG32.0000.00053 | REL MANC PRC SETC | NEW ADJ CAN NSFS RCFO WENG | MAI | 68801.26 | 0 | 2025-08-04 | 2025-09-26 |  | 9 | 26 | 2025 | U122858
2623 |  | Install 965'-4" PMMP | 4000087576 | PIG32.0000.00053 | REL ESTC GMPS MANC PRC SETC | NPRG ADJ FCMP REIM | MAI | 87286.17 | 271321.62 | 2025-08-08 | 2025-09-26 |  |  |  |  | U122858
2623 |  | Land Rights | 4000088138 | PIG32.0000.00053 | CRTD MANC PRC | EST NSFS | MAI | 1 | 0 | 2025-08-18 | 2025-08-18 |  |  |  |  | U122858
2629 |  | 2629-S Highland Relocation-Winchester | 4000087344 | PIG32.0000.00055 | CRTD ESTC MANC NTUP PRC | PLN ADJ REIM | MAI | 34563.32 | 0 | 2025-08-06 | 2025-09-13 |  | 9 | 15 | 2025 | U128885
2623 |  | Vandalay Dr Frankfort Relo | 4000088075 | PIG32.0000.00056 | REL ESTC MANC PRC SETC | NPRG | MAI | 18975.45 | 4123.36 | 2025-08-15 | 2025-08-15 |  |  |  |  | U126783
2631 |  | PIG-S 5th Street-Greenup | 4000088972 | PIG32.0000.00057 | REL PCNF ESTC GMPS MANC PRC SETC | SCHD ADJ | MAI | 76248.19 | 87406.17 | 2025-08-28 | 2025-08-28 | 2026-03-04 | 12 | 31 | 2026 | U122858
2623 |  | Vandalay & Westridge Dr Relo Frankfort | 4000090198 | PIG32.0000.00058 | REL ESTC GMPS MANC PRC | NPRG ADJ FCMP | MAI | 285738.67 | 1527223.44 | 2025-09-11 | 2025-09-11 |  |  |  |  | U126783
2631 |  | EMER - Dixon St- Ashland | 4000090728 | PIG32.0000.00059 | REL ESTC GMPS MANC PRC SETC SKKP | NPRG ADJ FCMP | MAI | 49189.54 | 293936.73 | 2025-09-22 | 2025-09-22 |  |  |  |  | U122858
2621 |  | PIG-MNA Rosemary Ave-Lexington | 4000090770 | PIG32.0000.00060 | REL ESTC GMPS MANC PRC SETC SKKP | NPRG ADJ | MAI | 451435.3 | 1900152.14 | 2025-09-22 | 2025-09-22 |  |  |  |  | U122858
|  | GRT-THE SANCTUARY MLE-LEXINGTON | 4000100569 |  | CRTD MANC NMAT NTUP PRC | EST | MAI | 0 | 0 | 2026-03-25 | 2026-12-31 |  |  |  |  | U145347
2621 |  | PIG - ARMSTRONG MILL | 4000096152 | PIG32.0000.00061 | REL ESTC CSER MANC PRC SETC | NEW ADJ | MAI | 162362.04 | 10.42 | 2026-02-02 | 2026-02-02 |  | 10 | 30 | 2026 | U132703
2621 |  | PIG -SR27-7-412 Relocation - Lexington | 4000093050 | PIG32.0000.00062 | REL ESTC MACM PRC SETC | NEW NSFS | MAI | 42600.9 | 7497.08 | 2025-11-05 | 2025-11-05 |  |  |  |  | U938437
2621 |  | PIG-BOBWHITE TRAIL RELOCATION-LEXINGTON | 4000093818 | PIG32.0000.00063 | REL PCNF PRT GMPS MANC PRC SETC SKKP | NPRG ADJ FCMP REIM | MAI | 7782.24 | -12902.79 | 2025-11-19 | 2026-01-31 | 2026-02-04 |  |  |  | U145347
2621 |  | Design for CU Tab | 4000103038 |  | CRTD MANC NMAT NTUP PRC | EST | MAI | 0 | 0 | 2026-05-08 | 2026-05-08 |  |  |  |  | U145347
2621 |  | PIG-Liberty Road-Lexington | 4000095180 | PIG32.0000.00064 | REL GMPS MANC PRC SETC | NPRG ADJ FCMP RCFO WENG | MAI | 120380.39 | 61401.74 | 2026-03-30 | 2026-12-31 |  | 12 | 31 | 2026 | U122858
2621 |  | PIG-N Limestone-Lexington | 4000095889 | PIG32.0000.00065 | REL PCNF ESTC GMPS MANC PRC SETC | NEW ADJ WENV WLND | MAI | 1244662.41 | 37496.41 | 2026-07-01 | 2026-12-31 | 2026-03-04 | 12 | 31 | 2026 | U122858
2623 |  | PIG - HOLMES ST RELOCATION - FRANKFORT | 4000095961 | PIG32.0000.00066 | REL ESTC MACM PRC SETC | SCHD NSFS WENG | MAI | 3.31 | 23116.8 | 2026-01-08 | 2026-01-08 |  | 12 | 31 | 2026 | U127466
2621 |  | PIG-Coleman Ct-Lexington | 4000096670 | PIG32.0000.00067 | REL ESTC MACM PRC SETC | NEW NSFS | MAI | 719.82 | 0 | 2026-01-20 | 2026-01-20 |  |  |  |  | U122858
2629 |  | PIG-Stone Trace Dr Relo-Mt Sterling | 4000097800 | PIG32.0000.00068 | CRTD ESTC MANC NTUP PRC | PLN REIM | MAI | 61025.06 | 0 | 2026-02-10 | 2026-04-30 |  | 4 | 30 | 2026 | U128885
2621 |  | PIG-REDMILE RD. ABANDONMENT-LEXINGTON | 4000097968 | PIG32.0000.00069 | REL ESTC CSER GMPS MANC PRC SETC | NPRG FCMP | MAI | 8923.55 | 15435.22 | 2026-02-12 | 2026-04-16 |  |  |  |  | U145347
2621 |  | PIG-LAKEWOOD DRIVE RELOC-LEXINGTON | 4000099056 | PIG32.0000.00070 | REL PCNF GMPS MANC PRC SETC | NPRG RCFO | MAI | 9977 | 36786.48 | 2025-06-30 | 2025-06-30 | 2026-05-12 | 7 | 1 | 2025 | U141016
2623 |  | PIG-BRANNON ROAD RELO-NICHOLASVILLE | 4000099103 | PIG32.0000.00071 | REL MANC NMAT PRC SETC | NEW NSFS RCFO | MAI | 0 | 506 | 2026-08-01 | 2026-12-31 |  |  |  |  | U126783
2621 |  | PIG - LIMA DR HP - LEXINGTON | 4000099136 | PIG32.0000.00072 | REL ESTC MANC PRC SETC | NEW MIFE NSFS WENG | MAI | 1.67 | 0 | 2026-10-31 | 2027-12-31 |  |  |  |  | U938437
2621 |  | PIG-Buchanan St-Lexington | 4000099164 | PIG32.0000.00073 | REL MANC PRC SETC | NEW ADJ NSFS RCFO | MAI | 251704.78 | 18.14 | 2026-03-12 | 2026-12-31 |  |  |  |  | U122858
2621 |  | PIG-Innovation Dr-Lexington | 4000099994 | PIG32.0000.00074 | REL ESTC GMPS MANC PRC SETC SKKP | NEW ADJ WENG | MAI | 91710.66 | 4721.58 | 2026-06-30 | 2026-08-30 |  |  |  |  | U122858
2621 |  | PIG-UK PATIENT CARE HP/MP RELO-LEXINGTON | 4000101430 | PIG32.0000.00075 | REL MANC PRC SETC | NEW NSFS | MAI | 1518.69 | 0 | 2026-10-31 | 2027-05-01 |  |  |  |  | U127466
2621 |  | PIG-US 25-Lexington | 4000102123 | PIG32.0000.00076 | REL NMAT PRC SETC | NEW NSFS RCFO | MAI | 0 | 0 | 2025-12-30 | 2025-12-31 |  | 12 | 31 | 2025 | U122858
2629 |  | STA- FISH 1301F REPL 200860-OWINGSVILLE | 4100836975 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW MIFE | STA | 4461.53 | 0 | 2026-02-01 | 2026-03-01 |  | 1900-01-11 | 1900-01-30 | 1905-07-18 | U938437
2623 | FRANKFORT | STA- FISH 1301F REPL 200162- | 4100836976 | ANC32.0003.00011 | REL ESTC CSER MANC PRC SETC | SCHD MIFE | STA | 2676.63 | 0 | 2026-02-01 | 2026-03-01 |  | 1900-01-11 | 1900-01-30 | 1905-07-18 | U938437
2631 | SOUTH SHORE | STA- FISH 1301F REPL 200311- | 4100836977 | ANC32.0003.00011 | REL ESTC CSER MANC PRC SETC | SCHD MIFE | STA | 4179.93 | 0 | 2026-02-01 | 2026-03-01 |  | 1900-01-11 | 1900-01-30 | 1905-07-18 | U938437
2621 | LEXINGTON | STA- FISH 1301F REPL 211853- | 4100836978 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | SCHD MIFE | STA | 4461.53 | 0 | 2026-02-01 | 2026-03-01 |  | 1900-01-11 | 1900-01-30 | 1905-07-18 | U938437
2621 | LEXINGTON | STA- FISH 1301F REPL 211762- | 4100837015 | ANC32.0003.00011 | REL ESTC CSER MANC PRC SETC | SCHD MIFE | STA | 4179.93 | 0 | 2026-03-01 | 2026-04-01 |  | 1900-01-11 | 1900-01-30 | 1905-07-18 | U938437
2623 | FRANKFORT | STA- FISH 1301F REPL 200653- | 4100837048 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW MIFE | STA | 4461.53 | 0 | 2026-03-01 | 2026-04-01 |  | 1900-01-11 | 1900-01-30 | 1905-07-18 | U938437
2623 | GEORGETOWN | STA- FISH 1301F REPL 213027- | 4100837060 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW | STA | 7468.13 | 0 | 2026-03-01 | 2026-04-01 |  | 1900-01-11 | 1900-01-30 | 1905-07-18 | U938437
2629 | PARIS | STA- FISH 1301F REPL 200933- | 4100837070 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW | STA | 4461.53 | 0 | 2026-03-01 | 2026-04-01 |  | 1900-01-11 | 1900-01-30 | 1905-07-18 | U938437
2632 | MAYSVILLE | STA- FISH 1301F REPL 208891- | 4100837080 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW MIFE | STA | 2958.23 | 0 | 2026-03-01 | 2026-04-01 |  | 1900-01-11 | 1900-01-30 | 1905-07-18 | U938437
2629 | CARLISLE | STA- FISH 1301F REPL 200958 | 4100837093 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | SCHD MIFE | STA | 23756.85 | 0 | 2026-03-01 | 2026-04-01 |  | 1900-01-11 | 1900-01-30 | 1905-07-18 | U938437
2631 | ASHLAND | STA- FISH 1301F REPL 210271- | 4100837104 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW | STA | 7468.13 | 0 | 2026-03-01 | 2026-04-01 |  | 1900-01-11 | 1900-01-30 | 1905-07-18 | U938437
2623 | MIDWAY | STA- FISH 1301F REPL 212294- | 4100837119 | ANC32.0003.00011 | REL ESTC MACM PRC SETC | NEW MIFE | STA | 4461.03 | 0 | 2026-04-01 | 2026-05-01 |  | 1900-01-11 | 1900-01-30 | 1905-07-18 | U938437
2623 | FRANKFORT | STA- FISH 1301F REPL 200170- | 4100837141 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW | STA | 4461.53 | 0 | 2026-04-01 | 2026-05-01 |  | 1900-01-11 | 1900-01-30 | 1905-07-18 | U938437
2623 | VERSAILLES | STA- FISH 1301F REPL 200246- | 4100837142 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW MIFE | STA | 2958.23 | 0 | 2026-05-01 | 2026-06-01 |  | 1900-01-11 | 1900-01-30 | 1905-07-18 | U938437
2629 |  | STA- FISH 1301F REPL 200709 | 4100837143 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW MIFE | STA | 7468.13 | 0 | 2026-05-01 | 2026-06-01 |  | 1900-01-11 | 1900-01-30 | 1905-07-18 | U938437
2629 | IRVINE | STA- FISH 1301F REPL 212043- | 4100837144 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW MIFE | STA | 4461.53 | 0 | 2026-05-01 | 2026-06-01 |  | 1900-01-11 | 1900-01-30 | 1905-07-18 | U938437
2623 | GEORGETOWN | STA- FISH 1301F REPL 210385 | 4100837146 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW MIFE | STA | 4461.53 | 0 | 2026-05-01 | 2026-06-01 |  | 1900-01-11 | 1900-01-30 | 1905-07-18 | U938437
2631 | CATLETTSBURG | STA- FISH 1301F REPL 209199- | 4100837147 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW | STA | 7468.13 | 0 | 2026-05-01 | 2026-06-01 |  | 1900-01-11 | 1900-01-30 | 1905-07-18 | U938437
2633 | GREEN MEADOW | STA- FISH 1301F REPL 210363- | 4100837148 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW MIFE | STA | 2958.23 | 0 | 2026-05-01 | 2026-06-01 |  | 1900-01-11 | 1900-01-30 | 1905-07-18 | U938437
2633 | PIPPA PASSES | STA- FISH 1301F REPL 200198- | 4100837149 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW MIFE | STA | 2958.23 | 0 | 2026-06-01 | 2026-07-01 |  | 1900-01-11 | 1900-01-30 | 1905-07-18 | U938437
2623 | FRANKFORT | STA- FISH 1301F REPL 211194- | 4100837150 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW MIFE | STA | 4461.53 | 0 | 2026-06-01 | 2026-07-07 |  | 1900-01-11 | 1900-01-30 | 1905-07-18 | U938437
2623 | GEORGETOWN | STA- FISH 1301F REPL 212339- | 4100837151 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW MIFE | STA | 7468.13 | 0 | 2026-07-01 | 2026-08-01 |  | 1900-01-11 | 1900-01-30 | 1905-07-18 | U938437

## DTA Pulled Data (hidden)
Adjusted WBS L2 | AFUDC | DIRECT | INDIRECT | SEGA | (blank) | Grand Total |  |  | Schedule Data |  |  |  | Construction Amount (D) | AFUDC Capitalized (E) | Indirect Costs Other (F)*
0 | 596233.71 | 13925972.22 | 460069.9 | 11956567.71 |  | 26938843.54 | TRUE | ANC32.0000.00002 | ANC32 | 0000 | 00002 | ANC32000000002 | 0 | 0 | 0 | 0
ANC32000000001 | 34.66 | 33456.5 | 14798.3 | 2157.12 |  | 50446.58 | TRUE | ANC32.0000.00004 | ANC32 | 0000 | 00004 | ANC32000000004 | 867.4 | 0 | 451.94 | 1319.34
ANC32000000004 |  | 867.4 | 451.94 |  |  | 1319.34 | TRUE | ANC32.0000.00005 | ANC32 | 0000 | 00005 | ANC32000000005 | 417866.35 | 0 | 11295.19 | 429161.54
ANC32000000005 |  | 417866.35 | 11295.19 |  |  | 429161.54 | TRUE | ANC32.0000.00006 | ANC32 | 0000 | 00006 | ANC32000000006 | 4282.4 | 0 | 3014.87 | 7297.27
ANC32000000006 |  | 4282.4 | 3014.87 |  |  | 7297.27 | TRUE | ANC32.0000.00007 | ANC32 | 0000 | 00007 | ANC32000000007 | 7118.22 | 0 | 0 | 7118.22
ANC32000000007 |  | 7118.22 |  |  |  | 7118.22 | TRUE | ANC32.0000.00010 | ANC32 | 0000 | 00010 | ANC32000000010 | 522169.75 | 0 | 33435.26 | 555605.01
ANC32000000010 |  | 522169.75 | 33435.26 |  |  | 555605.01 | TRUE | ANC32.0000.00014 | ANC32 | 0000 | 00014 | ANC32000000014 | 0 | 0 | 0 | 0
ANC32000000017 |  | 3284.99 | 704.72 |  |  | 3989.71 | TRUE | ANC32.0000.00017 | ANC32 | 0000 | 00017 | ANC32000000017 | 3284.99 | 0 | 704.72 | 3989.71
ANC32000000019 |  | 236484.6 | 17633.01 |  |  | 254117.61 | TRUE | ANC32.0000.00018 | ANC32 | 0000 | 00018 | ANC32000000018 | 0 | 0 | 0 | 0
ANC32000000020 |  | 759337.58 | 28090.75 |  |  | 787428.33 | TRUE | ANC32.0000.00019 | ANC32 | 0000 | 00019 | ANC32000000019 | 236484.6 | 0 | 17633.01 | 254117.61
ANC32000000024 |  | 2069.32 | 274.1 |  |  | 2343.42 | TRUE | ANC32.0000.00020 | ANC32 | 0000 | 00020 | ANC32000000020 | 759337.58 | 0 | 28090.75 | 787428.33
ANC32000000049 |  | 1283963.37 | 43097.01 |  |  | 1327060.38 | TRUE | ANC32.0000.00049 | ANC32 | 0000 | 00049 | ANC32000000049 | 1283963.37 | 0 | 43097.01 | 1327060.38
ANC32000000050 |  | 1078865.68 | 47346.44 |  |  | 1126212.12 | TRUE | ANC32.0000.00050 | ANC32 | 0000 | 00050 | ANC32000000050 | 1078865.68 | 0 | 47346.44 | 1126212.12
ANC32000000054 |  | 1007374.35 | 222222.52 |  |  | 1229596.87 | TRUE | ANC32.0000.00051 | ANC32 | 0000 | 00051 | ANC32000000051 | 0 | 0 | 0 | 0
ANC32000000056 |  | 1119365.58 | 22793.58 |  |  | 1142159.16 | TRUE | ANC32.0000.00052 | ANC32 | 0000 | 00052 | ANC32000000052 | 0 | 0 | 0 | 0
ANC32000000057 |  | 884899.8 | 20193.74 |  |  | 905093.54 | TRUE | ANC32.0000.00054 | ANC32 | 0000 | 00054 | ANC32000000054 | 1007374.35 | 0 | 222222.52 | 1229596.87
ANC32000000058 | 1.92 | 1032988.36 | 52617.29 | 89.19 |  | 1085696.76 | TRUE | ANC32.0000.00056 | ANC32 | 0000 | 00056 | ANC32000000056 | 1119365.58 | 0 | 22793.58 | 1142159.16
ANC32000000059 |  | 1682056.86 | 10100.56 |  |  | 1692157.42 | TRUE | ANC32.0000.00057 | ANC32 | 0000 | 00057 | ANC32000000057 | 884899.8 | 0 | 20193.74 | 905093.54
ANC32000000078 |  | 238153.75 | 3225.52 |  |  | 241379.27 | TRUE | ANC32.0000.00058 | ANC32 | 0000 | 00058 | ANC32000000058 | 1032988.36 | 1.92 | 52706.48 | 1085696.76
ANC32000000081 |  | 255.51 | 75.11 |  |  | 330.62 | TRUE | ANC32.0000.00059 | ANC32 | 0000 | 00059 | ANC32000000059 | 1682056.86 | 0 | 10100.56 | 1692157.42
ANC32000000083 |  | 12197.86 | 815.45 |  |  | 13013.31 | TRUE | ANC32.0000.00060 | ANC32 | 0000 | 00060 | ANC32000000060 | 0 | 0 | 0 | 0
ANC32000000084 |  | 1188.1 | 374.67 |  |  | 1562.77 | TRUE | ANC32.0000.00061 | ANC32 | 0000 | 00061 | ANC32000000061 | 0 | 0 | 0 | 0
ANC32000000086 |  | 382.32 |  |  |  | 382.32 | TRUE | ANC32.0000.00062 | ANC32 | 0000 | 00062 | ANC32000000062 | 0 | 0 | 0 | 0
ANC32000000093 |  | 1918.09 | 63.33 |  |  | 1981.42 | TRUE | ANC32.0000.00063 | ANC32 | 0000 | 00063 | ANC32000000063 | 0 | 0 | 0 | 0
ANC32000000119 |  | 1331.16 |  |  |  | 1331.16 | TRUE | ANC32.0000.00068 | ANC32 | 0000 | 00068 | ANC32000000068 | 0 | 0 | 0 | 0
ANC32000000140 |  | 6712.5 |  |  |  | 6712.5 | TRUE | ANC32.0000.00071 | ANC32 | 0000 | 00071 | ANC32000000071 | 0 | 0 | 0 | 0
ANC32000000141 |  | 61619.53 | 1996.73 |  |  | 63616.26 | TRUE | ANC32.0000.00074 | ANC32 | 0000 | 00074 | ANC32000000074 | 0 | 0 | 0 | 0
ANC32000000143 |  | 2292.84 | 249.85 |  |  | 2542.69 | TRUE | ANC32.0000.00075 | ANC32 | 0000 | 00075 | ANC32000000075 | 0 | 0 | 0 | 0
ANC32000000144 |  | 687.93 | 559.31 |  |  | 1247.24 | TRUE | ANC32.0000.00076 | ANC32 | 0000 | 00076 | ANC32000000076 | 0 | 0 | 0 | 0
ANC32000000145 |  | 305155.33 | 14957.92 |  |  | 320113.25 | TRUE | ANC32.0000.00077 | ANC32 | 0000 | 00077 | ANC32000000077 | 0 | 0 | 0 | 0
ANC32000000146 |  | 32007.28 | 5850.86 |  |  | 37858.14 | TRUE | ANC32.0000.00078 | ANC32 | 0000 | 00078 | ANC32000000078 | 238153.75 | 0 | 3225.52 | 241379.27
ANC32000000147 |  | 110955.66 | 646.76 |  |  | 111602.42 | TRUE | ANC32.0000.00080 | ANC32 | 0000 | 00080 | ANC32000000080 | 0 | 0 | 0 | 0
ANC32000000148 |  | 1808.74 | 264.31 |  |  | 2073.05 | TRUE | ANC32.0000.00081 | ANC32 | 0000 | 00081 | ANC32000000081 | 255.51 | 0 | 75.11 | 330.62
ANC32000000154 |  | 114421.57 | 6916.3 |  |  | 121337.87 | TRUE | ANC32.0000.00082 | ANC32 | 0000 | 00082 | ANC32000000082 | 0 | 0 | 0 | 0
ANC32000000157 |  | 94927.76 |  |  |  | 94927.76 | TRUE | ANC32.0000.00083 | ANC32 | 0000 | 00083 | ANC32000000083 | 12197.86 | 0 | 815.45 | 13013.31
ANC32000000158 |  | 535.09 | 546.12 |  |  | 1081.21 | TRUE | ANC32.0000.00084 | ANC32 | 0000 | 00084 | ANC32000000084 | 1188.1 | 0 | 374.67 | 1562.77
ANC32000000163 |  | 1487.13 | 966.37 |  |  | 2453.5 | TRUE | ANC32.0000.00085 | ANC32 | 0000 | 00085 | ANC32000000085 | 0 | 0 | 0 | 0
ANC32000000166 |  | 9981.35 |  |  |  | 9981.35 | TRUE | ANC32.0000.00086 | ANC32 | 0000 | 00086 | ANC32000000086 | 382.32 | 0 | 0 | 382.32
ANC32000000170 |  | 2032589.11 | 50360.2 |  |  | 2082949.31 | TRUE | ANC32.0000.00087 | ANC32 | 0000 | 00087 | ANC32000000087 | 0 | 0 | 0 | 0
ANC32000000179 |  | 592689.96 | 23880.82 |  |  | 616570.78 | TRUE | ANC32.0000.00088 | ANC32 | 0000 | 00088 | ANC32000000088 | 0 | 0 | 0 | 0
ANC32000000180 |  | 178351.44 | 13582.31 |  |  | 191933.75 | TRUE | ANC32.0000.00089 | ANC32 | 0000 | 00089 | ANC32000000089 | 0 | 0 | 0 | 0
ANC32000000184 |  | 13881.9 | 295.64 |  |  | 14177.54 | TRUE | ANC32.0000.00090 | ANC32 | 0000 | 00090 | ANC32000000090 | 0 | 0 | 0 | 0
ANC32000000193 |  | 279.76 | 317.16 |  |  | 596.92 | TRUE | ANC32.0000.00092 | ANC32 | 0000 | 00092 | ANC32000000092 | 0 | 0 | 0 | 0
ANC32000000194 |  | 358413.18 | 18277.5 |  |  | 376690.68 | TRUE | ANC32.0000.00093 | ANC32 | 0000 | 00093 | ANC32000000093 | 1918.09 | 0 | 63.33 | 1981.42
ANC32000000195 |  | 464.31 | 409.81 |  |  | 874.12 | TRUE | ANC32.0000.00094 | ANC32 | 0000 | 00094 | ANC32000000094 | 0 | 0 | 0 | 0
ANC32000000198 |  | 218540.75 | 10068.34 |  |  | 228609.09 | TRUE | ANC32.0000.00095 | ANC32 | 0000 | 00095 | ANC32000000095 | 0 | 0 | 0 | 0
ANC32000000200 |  | 43611.23 | 2811.32 |  |  | 46422.55 | TRUE | ANC32.0000.00098 | ANC32 | 0000 | 00098 | ANC32000000098 | 0 | 0 | 0 | 0
ANC32000000202 |  | 553021.67 | 33132.18 |  |  | 586153.85 | TRUE | ANC32.0000.00099 | ANC32 | 0000 | 00099 | ANC32000000099 | 0 | 0 | 0 | 0
ANC32000000209 |  | 0.02 | 0.34 |  |  | 0.36 | TRUE | ANC32.0000.00100 | ANC32 | 0000 | 00100 | ANC32000000100 | 0 | 0 | 0 | 0
ANC32000000221 |  | 140810.22 |  |  |  | 140810.22 | TRUE | ANC32.0000.00110 | ANC32 | 0000 | 00110 | ANC32000000110 | 0 | 0 | 0 | 0
ANC32000000250 |  | 12394.74 | 2044.4 |  |  | 14439.14 | TRUE | ANC32.0000.00113 | ANC32 | 0000 | 00113 | ANC32000000113 | 0 | 0 | 0 | 0
ANC32000000251 |  | 2475796.36 | 68624.82 |  |  | 2544421.18 | TRUE | ANC32.0000.00119 | ANC32 | 0000 | 00119 | ANC32000000119 | 1331.16 | 0 | 0 | 1331.16
ANC32000000256 |  | 1856668.07 | 37568.45 |  |  | 1894236.52 | TRUE | ANC32.0000.00120 | ANC32 | 0000 | 00120 | ANC32000000120 | 0 | 0 | 0 | 0
ANC32000000257 |  | 407173.62 | 41891.77 |  |  | 449065.39 | TRUE | ANC32.0000.00121 | ANC32 | 0000 | 00121 | ANC32000000121 | 0 | 0 | 0 | 0
ANC32000000273 |  | 351.54 | 106.95 |  |  | 458.49 | TRUE | ANC32.0000.00122 | ANC32 | 0000 | 00122 | ANC32000000122 | 0 | 0 | 0 | 0
ANC32000000282 |  | 24442.13 |  |  |  | 24442.13 | TRUE | ANC32.0000.00124 | ANC32 | 0000 | 00124 | ANC32000000124 | 0 | 0 | 0 | 0
ANC32000000289 |  | 138617.28 | 12433.79 |  |  | 151051.07 | TRUE | ANC32.0000.00126 | ANC32 | 0000 | 00126 | ANC32000000126 | 0 | 0 | 0 | 0
ANC32000000304 | 8741.04 | 590401.57 | 25786.59 | 181750.5 |  | 806679.7 | TRUE | ANC32.0000.00127 | ANC32 | 0000 | 00127 | ANC32000000127 | 0 | 0 | 0 | 0
ANC32000000305 | 133.6 | 5036.78 |  | 2534.6 |  | 7704.98 | TRUE | ANC32.0000.00128 | ANC32 | 0000 | 00128 | ANC32000000128 | 0 | 0 | 0 | 0
ANC32000000307 | 18.13 | 5106.27 | 24.52 | 839.29 |  | 5988.21 | TRUE | ANC32.0000.00129 | ANC32 | 0000 | 00129 | ANC32000000129 | 0 | 0 | 0 | 0
ANC32000000308 | 713.75 | 26238.78 | 435.6 | 15839.36 |  | 43227.49 | TRUE | ANC32.0000.00132 | ANC32 | 0000 | 00132 | ANC32000000132 | 0 | 0 | 0 | 0
ANC32000000310 | 50.67 | 2783.74 | 107.81 | 131.96 |  | 3074.18 | TRUE | ANC32.0000.00133 | ANC32 | 0000 | 00133 | ANC32000000133 | 0 | 0 | 0 | 0
ANC32000000311 | 15.48 | 2722.72 | 1185.77 | 1192.09 |  | 5116.06 | TRUE | ANC32.0000.00136 | ANC32 | 0000 | 00136 | ANC32000000136 | 0 | 0 | 0 | 0
ANC32000000312 | 30.87 | 2510.79 | 889.67 |  |  | 3431.33 | TRUE | ANC32.0000.00137 | ANC32 | 0000 | 00137 | ANC32000000137 | 0 | 0 | 0 | 0
ANC32000000313 | 2285.72 | 154044.75 | 12304.96 |  |  | 168635.43 | TRUE | ANC32.0000.00140 | ANC32 | 0000 | 00140 | ANC32000000140 | 6712.5 | 0 | 0 | 6712.5
ANC32000000314 | 368.3 | 8347.92 | 27.1 | 3998.74 |  | 12742.06 | TRUE | ANC32.0000.00141 | ANC32 | 0000 | 00141 | ANC32000000141 | 61619.53 | 0 | 1996.73 | 63616.26
ANC32000000316 |  | 5676.31 | 1324.6 |  |  | 7000.91 | TRUE | ANC32.0000.00143 | ANC32 | 0000 | 00143 | ANC32000000143 | 2292.84 | 0 | 249.85 | 2542.69
ANC32000000320 | 2969.54 | 293245.77 | 27218.62 | 67104.55 |  | 390538.48 | TRUE | ANC32.0000.00144 | ANC32 | 0000 | 00144 | ANC32000000144 | 687.93 | 0 | 559.31 | 1247.24
ANC32000000321 | 3.8 | 1074.78 |  | 175.81 |  | 1254.39 | TRUE | ANC32.0000.00145 | ANC32 | 0000 | 00145 | ANC32000000145 | 305155.33 | 0 | 14957.92 | 320113.25
ANC32000000322 | 1738.08 | 490330.43 | 28322.24 | 158799.07 |  | 679189.82 | TRUE | ANC32.0000.00146 | ANC32 | 0000 | 00146 | ANC32000000146 | 32007.28 | 0 | 5850.86 | 37858.14
ANC32000000323 | 63.86 | 3750.54 | 121.9 | 1176.48 |  | 5112.78 | TRUE | ANC32.0000.00147 | ANC32 | 0000 | 00147 | ANC32000000147 | 110955.66 | 0 | 646.76 | 111602.42
ANC32000000325 | 1069.05 | 49039.88 | 1527.94 | 12933.6 |  | 64570.47 | TRUE | ANC32.0000.00148 | ANC32 | 0000 | 00148 | ANC32000000148 | 1808.74 | 0 | 264.31 | 2073.05
ANC32000000326 | 2.98 | 0 |  |  |  | 2.98 | TRUE | ANC32.0000.00149 | ANC32 | 0000 | 00149 | ANC32000000149 | 0 | 0 | 0 | 0
ANC32000000327 | 16456.46 | 1323627.78 | 26940.21 | 367282.64 |  | 1734307.09 | TRUE | ANC32.0000.00150 | ANC32 | 0000 | 00150 | ANC32000000150 | 0 | 0 | 0 | 0
ANC32000000328 | 1301.57 | 27114.24 |  | 11861.94 |  | 40277.75 | TRUE | ANC32.0000.00151 | ANC32 | 0000 | 00151 | ANC32000000151 | 0 | 0 | 0 | 0
ANC32000000329 | 2769.9 | 595777.18 | 10429.28 | 104663.94 |  | 713640.3 | TRUE | ANC32.0000.00152 | ANC32 | 0000 | 00152 | ANC32000000152 | 0 | 0 | 0 | 0
ANC32000000330 | 5726.74 | 1641708.5 | 25864.56 | 303183.42 |  | 1976483.22 | TRUE | ANC32.0000.00153 | ANC32 | 0000 | 00153 | ANC32000000153 | 0 | 0 | 0 | 0
ANC32000000331 | 39.54 | 11105.4 | 89.61 | 1831.28 |  | 13065.83 | TRUE | ANC32.0000.00154 | ANC32 | 0000 | 00154 | ANC32000000154 | 114421.57 | 0 | 6916.3 | 121337.87
ANC32000000333 | 1550.24 | 283102.16 | 4065.95 | 51593.06 |  | 340311.41 | TRUE | ANC32.0000.00157 | ANC32 | 0000 | 00157 | ANC32000000157 | 94927.76 | 0 | 0 | 94927.76
ANC32000000334 | 859.07 | 89394.9 | 189.68 | 20100.92 |  | 110544.57 | TRUE | ANC32.0000.00158 | ANC32 | 0000 | 00158 | ANC32000000158 | 535.09 | 0 | 546.12 | 1081.21
ANC32000000335 | 75.11 | 23866.64 | 24.53 | 1863.96 |  | 25830.24 | TRUE | ANC32.0000.00163 | ANC32 | 0000 | 00163 | ANC32000000163 | 1487.13 | 0 | 966.37 | 2453.5
ANC32000000336 | 51.15 | 14320.71 | 159.47 | 2368.66 |  | 16899.99 | TRUE | ANC32.0000.00165 | ANC32 | 0000 | 00165 | ANC32000000165 | 0 | 0 | 0 | 0
ANC32000000338 | 16.5 | 3831.94 | 244.85 | 397 |  | 4490.29 | TRUE | ANC32.0000.00167 | ANC32 | 0000 | 00167 | ANC32000000167 | 0 | 0 | 0 | 0
ANC32000000339 | 0.02 | 2894.75 | 1.18 | 2.42 |  | 2898.37 | TRUE | ANC32.0000.00170 | ANC32 | 0000 | 00170 | ANC32000000170 | 2032589.11 | 0 | 50360.2 | 2082949.31
ANC32000000341 | 137.92 | 15101.63 | 362.16 | 3444.2 |  | 19045.91 | TRUE | ANC32.0000.00171 | ANC32 | 0000 | 00171 | ANC32000000171 | 0 | 0 | 0 | 0
ANC32000000342 | 10.9 | 252.48 | 81.86 | 221.75 |  | 566.99 | TRUE | ANC32.0000.00174 | ANC32 | 0000 | 00174 | ANC32000000174 | 0 | 0 | 0 | 0
ANC32000000343 |  | 2.8422e-14 | 0 |  |  | 2.8422e-14 | TRUE | ANC32.0000.00176 | ANC32 | 0000 | 00176 | ANC32000000176 | 0 | 0 | 0 | 0
ANC32000000344 | 38.99 | 10965.79 | 73.6 | 1805.83 |  | 12884.21 | TRUE | ANC32.0000.00178 | ANC32 | 0000 | 00178 | ANC32000000178 | 0 | 0 | 0 | 0
ANC32000000347 | 18.47 | 5202.44 | 24.52 | 855.02 |  | 6100.45 | TRUE | ANC32.0000.00179 | ANC32 | 0000 | 00179 | ANC32000000179 | 592689.96 | 0 | 23880.82 | 616570.78
ANC32000000348 | 27.78 | 7838.03 | 24.52 | 1286.15 |  | 9176.48 | TRUE | ANC32.0000.00180 | ANC32 | 0000 | 00180 | ANC32000000180 | 178351.44 | 0 | 13582.31 | 191933.75
ANC32000000350 | 17.59 | 4907.61 | 73.6 | 814.83 |  | 5813.63 | TRUE | ANC32.0000.00181 | ANC32 | 0000 | 00181 | ANC32000000181 | 0 | 0 | 0 | 0
ANC32000000352 | 7.15 | 1950.24 | 73.6 | 331.06 |  | 2362.05 | TRUE | ANC32.0000.00184 | ANC32 | 0000 | 00184 | ANC32000000184 | 13881.9 | 0 | 295.64 | 14177.54
ANC32000000353 | 196.34 | 62685.28 | 565.35 | 6733.87 |  | 70180.84 | TRUE | ANC32.0000.00187 | ANC32 | 0000 | 00187 | ANC32000000187 | 0 | 0 | 0 | 0
ANC32000000354 | 25.46 | 7132.85 | 73.6 | 1178.84 |  | 8410.75 | TRUE | ANC32.0000.00191 | ANC32 | 0000 | 00191 | ANC32000000191 | 0 | 0 | 0 | 0
ANC32000000355 | 4.36 | 1186.84 | 49.04 | 202.16 |  | 1442.4 | TRUE | ANC32.0000.00192 | ANC32 | 0000 | 00192 | ANC32000000192 | 0 | 0 | 0 | 0
ANC32000000356 | 43.39 | 12283.27 |  | 2009.3 |  | 14335.96 | TRUE | ANC32.0000.00193 | ANC32 | 0000 | 00193 | ANC32000000193 | 279.76 | 0 | 317.16 | 596.92
ANC32000000358 | 166.61 | 53872.45 | 2003.34 | 7715.09 |  | 63757.49 | TRUE | ANC32.0000.00194 | ANC32 | 0000 | 00194 | ANC32000000194 | 358413.18 | 0 | 18277.5 | 376690.68
ANC32000000361 | 5.79 | 191.62 | 93.26 | 98.21 |  | 388.88 | TRUE | ANC32.0000.00195 | ANC32 | 0000 | 00195 | ANC32000000195 | 464.31 | 0 | 409.81 | 874.12
ANC32000000363 | 0.91 | 257.9 |  | 42.19 |  | 301 | TRUE | ANC32.0000.00196 | ANC32 | 0000 | 00196 | ANC32000000196 | 0 | 0 | 0 | 0
ANC32000000364 | 0.48 | 104.53 | 30.13 | 22.03 |  | 157.17 | TRUE | ANC32.0000.00197 | ANC32 | 0000 | 00197 | ANC32000000197 | 0 | 0 | 0 | 0
ANC32000000365 | 6.39 | 1687.34 | 121.9 | 295.96 |  | 2111.59 | TRUE | ANC32.0000.00198 | ANC32 | 0000 | 00198 | ANC32000000198 | 218540.75 | 0 | 10068.34 | 228609.09
ANC32000000366 | 33.26 | 7375.34 | 121.9 | 295.96 |  | 7826.46 | TRUE | ANC32.0000.00199 | ANC32 | 0000 | 00199 | ANC32000000199 | 0 | 0 | 0 | 0
ANC32000000367 |  | 1896 |  |  |  | 1896 | TRUE | ANC32.0000.00200 | ANC32 | 0000 | 00200 | ANC32000000200 | 43611.23 | 0 | 2811.32 | 46422.55
ANC32000000375 | 15.28 | 2112.92 | 266.24 | 309.91 |  | 2704.35 | TRUE | ANC32.0000.00202 | ANC32 | 0000 | 00202 | ANC32000000202 | 553021.67 | 0 | 33132.18 | 586153.85
ANC32000000376 | 3 | 180.34 | 84.12 | 67.43 |  | 334.89 | TRUE | ANC32.0000.00209 | ANC32 | 0000 | 00209 | ANC32000000209 | 0.02 | 0 | 0.34 | 0.36
ANC32000000377 | 2.26 | 448.32 | 193.33 | 104.97 |  | 748.88 | TRUE | ANC32.0000.00226 | ANC32 | 0000 | 00226 | ANC32000000226 | 0 | 0 | 0 | 0
ANC32000000380 | 0.91 | 179.33 | 77.38 | 41.99 |  | 299.61 | TRUE | ANC32.0000.00230 | ANC32 | 0000 | 00230 | ANC32000000230 | 0 | 0 | 0 | 0
ANC32000000382 | 11.75 | 1289.51 |  |  |  | 1301.26 | TRUE | ANC32.0000.00234 | ANC32 | 0000 | 00234 | ANC32000000234 | 0 | 0 | 0 | 0
ANC32000200001 | 24.91 | 35250.63 | 3566.82 | 1678.82 |  | 40521.18 | TRUE | ANC32.0000.00235 | ANC32 | 0000 | 00235 | ANC32000000235 | 0 | 0 | 0 | 0
ANC32000200002 |  | 526171.12 | 150937.8 |  |  | 677108.92 | TRUE | ANC32.0000.00239 | ANC32 | 0000 | 00239 | ANC32000000239 | 0 | 0 | 0 | 0
ANC32000200003 |  | 215549.07 | 74254.34 |  |  | 289803.41 | TRUE | ANC32.0000.00248 | ANC32 | 0000 | 00248 | ANC32000000248 | 0 | 0 | 0 | 0
ANC32000200004 |  | 696.46 | 200.55 |  |  | 897.01 | TRUE | ANC32.0000.00249 | ANC32 | 0000 | 00249 | ANC32000000249 | 0 | 0 | 0 | 0
ANC32000200006 | 8.59 | 514731.72 | 133132.8 | 860.7 |  | 648733.81 | TRUE | ANC32.0000.00250 | ANC32 | 0000 | 00250 | ANC32000000250 | 12394.74 | 0 | 2044.4 | 14439.14
ANC32000200007 |  | 0 |  |  |  | 0 | TRUE | ANC32.0000.00251 | ANC32 | 0000 | 00251 | ANC32000000251 | 2475796.36 | 0 | 68624.82 | 2544421.18
ANC32000200008 | 3.33 | 811.67 | 284.91 |  |  | 1099.91 | TRUE | ANC32.0000.00252 | ANC32 | 0000 | 00252 | ANC32000000252 | 0 | 0 | 0 | 0
ANC32000300011 | 720.78 | 63060.97 |  | 16078.66 |  | 79860.41 | TRUE | ANC32.0000.00253 | ANC32 | 0000 | 00253 | ANC32000000253 | 0 | 0 | 0 | 0
ANC32000300911 | 0.27 | 1100.7 | 798.13 | 12.36 |  | 1911.46 | TRUE | ANC32.0000.00256 | ANC32 | 0000 | 00256 | ANC32000000256 | 1856668.07 | 0 | 37568.45 | 1894236.52
BET32000000002 |  | 697.46 |  |  |  | 697.46 | TRUE | ANC32.0000.00257 | ANC32 | 0000 | 00257 | ANC32000000257 | 407173.62 | 0 | 41891.77 | 449065.39
BET32000000003 |  | 3921 | 2374.5 |  |  | 6295.5 | TRUE | ANC32.0000.00259 | ANC32 | 0000 | 00259 | ANC32000000259 | 0 | 0 | 0 | 0
BET32000000004 |  | 819.48 | 215.62 |  |  | 1035.1 | TRUE | ANC32.0000.00260 | ANC32 | 0000 | 00260 | ANC32000000260 | 0 | 0 | 0 | 0
BET32000000022 |  | 101350.69 | 24164.39 |  |  | 125515.08 | TRUE | ANC32.0000.00262 | ANC32 | 0000 | 00262 | ANC32000000262 | 0 | 0 | 0 | 0
BET32000000025 |  | 132431.2 | 3151.42 |  |  | 135582.62 | TRUE | ANC32.0000.00263 | ANC32 | 0000 | 00263 | ANC32000000263 | 0 | 0 | 0 | 0
BET32000000027 |  | 67.25 | 20.46 |  |  | 87.71 | TRUE | ANC32.0000.00264 | ANC32 | 0000 | 00264 | ANC32000000264 | 0 | 0 | 0 | 0
BET32000000041 |  | 4781.04 | 2521.73 |  |  | 7302.77 | TRUE | ANC32.0000.00265 | ANC32 | 0000 | 00265 | ANC32000000265 | 0 | 0 | 0 | 0
BET32000000045 |  | 757.41 | 283.93 |  |  | 1041.34 | TRUE | ANC32.0000.00266 | ANC32 | 0000 | 00266 | ANC32000000266 | 0 | 0 | 0 | 0
BET32000000049 | 0.09 | 0 | 0 | -2.4009e-15 |  | 0.09 | TRUE | ANC32.0000.00267 | ANC32 | 0000 | 00267 | ANC32000000267 | 0 | 0 | 0 | 0
BET32000000052 |  | 43904.78 | 4238.7 |  |  | 48143.48 | TRUE | ANC32.0000.00269 | ANC32 | 0000 | 00269 | ANC32000000269 | 0 | 0 | 0 | 0
BET32000000054 |  | 2490.65 | 1266.8 |  |  | 3757.45 | TRUE | ANC32.0000.00270 | ANC32 | 0000 | 00270 | ANC32000000270 | 0 | 0 | 0 | 0
BET32000000057 |  | 0 | 0 |  |  | 0 | TRUE | ANC32.0000.00272 | ANC32 | 0000 | 00272 | ANC32000000272 | 0 | 0 | 0 | 0
BET32000000058 |  | 3812.09 | 1.08 | 3146.6 |  | 6959.77 | TRUE | ANC32.0000.00275 | ANC32 | 0000 | 00275 | ANC32000000275 | 0 | 0 | 0 | 0
BET32000000059 | 1126.61 | 97054.56 |  | 23045.4 |  | 121226.57 | TRUE | ANC32.0000.00277 | ANC32 | 0000 | 00277 | ANC32000000277 | 0 | 0 | 0 | 0
BET32000000060 |  | -7519.36 | 136.66 | -2440.68 |  | -9823.38 | TRUE | ANC32.0000.00280 | ANC32 | 0000 | 00280 | ANC32000000280 | 0 | 0 | 0 | 0
GRT32000000001 |  | 107348.61 | 3755.29 |  |  | 111103.9 | TRUE | ANC32.0000.00281 | ANC32 | 0000 | 00281 | ANC32000000281 | 0 | 0 | 0 | 0
GRT32000000014 |  | 223.3 | 66.05 |  |  | 289.35 | TRUE | ANC32.0000.00282 | ANC32 | 0000 | 00282 | ANC32000000282 | 24442.13 | 0 | 0 | 24442.13
GRT32000000020 |  | 82681.3 | 3630.75 |  |  | 86312.05 | TRUE | ANC32.0000.00283 | ANC32 | 0000 | 00283 | ANC32000000283 | 0 | 0 | 0 | 0
GRT32000000022 |  | 1117.15 | 311.46 |  |  | 1428.61 | TRUE | ANC32.0000.00285 | ANC32 | 0000 | 00285 | ANC32000000285 | 0 | 0 | 0 | 0
GRT32000000040 |  | 19346.1 | 5203.85 |  |  | 24549.95 | TRUE | ANC32.0000.00286 | ANC32 | 0000 | 00286 | ANC32000000286 | 0 | 0 | 0 | 0
GRT32000000056 |  | 28325.74 | 3350.4 |  |  | 31676.14 | TRUE | ANC32.0000.00287 | ANC32 | 0000 | 00287 | ANC32000000287 | 0 | 0 | 0 | 0
GRT32000000062 |  | 11506.74 | 3465.08 |  |  | 14971.82 | TRUE | ANC32.0000.00288 | ANC32 | 0000 | 00288 | ANC32000000288 | 0 | 0 | 0 | 0
GRT32000000063 |  | 299286.06 | 24634.87 |  |  | 323920.93 | TRUE | ANC32.0000.00289 | ANC32 | 0000 | 00289 | ANC32000000289 | 138617.28 | 0 | 12433.79 | 151051.07
GRT32000000066 |  | 0 | 0 |  |  | 0 | TRUE | ANC32.0000.00290 | ANC32 | 0000 | 00290 | ANC32000000290 | 0 | 0 | 0 | 0
GRT32000000067 |  | 105062.46 | 11364.33 |  |  | 116426.79 | TRUE | ANC32.0000.00292 | ANC32 | 0000 | 00292 | ANC32000000292 | 0 | 0 | 0 | 0
GRT32000000074 |  | 2419.51 | 1388.49 |  |  | 3808 | TRUE | ANC32.0000.00293 | ANC32 | 0000 | 00293 | ANC32000000293 | 0 | 0 | 0 | 0
GRT32000000076 |  | 97.18 | 82.57 |  |  | 179.75 | TRUE | ANC32.0000.00294 | ANC32 | 0000 | 00294 | ANC32000000294 | 0 | 0 | 0 | 0
GRT32000000078 |  | 49584.82 | 5432.68 |  |  | 55017.5 | TRUE | ANC32.0000.00295 | ANC32 | 0000 | 00295 | ANC32000000295 | 0 | 0 | 0 | 0
GRT32000000083 |  | 7.88 | 4.56 |  |  | 12.44 | TRUE | ANC32.0000.00296 | ANC32 | 0000 | 00296 | ANC32000000296 | 0 | 0 | 0 | 0
GRT32000000084 |  | -2.3093e-14 | -5.3291e-15 |  |  | -2.8422e-14 | TRUE | ANC32.0000.00297 | ANC32 | 0000 | 00297 | ANC32000000297 | 0 | 0 | 0 | 0
GRT32000000091 |  | 0 | -1.5099e-14 |  |  | -1.5099e-14 | TRUE | ANC32.0000.00299 | ANC32 | 0000 | 00299 | ANC32000000299 | 0 | 0 | 0 | 0
GRT32000000095 |  | 0 | -5.862e-14 |  |  | -5.862e-14 | TRUE | ANC32.0000.00300 | ANC32 | 0000 | 00300 | ANC32000000300 | 0 | 0 | 0 | 0
GRT32000000096 |  | 267.59 | 260.03 |  |  | 527.62 | TRUE | ANC32.0000.00301 | ANC32 | 0000 | 00301 | ANC32000000301 | 0 | 0 | 0 | 0
GRT32000000097 | 2076.33 | 444459.95 | 9583.75 | 291100.55 |  | 747220.58 | TRUE | ANC32.0000.00302 | ANC32 | 0000 | 00302 | ANC32000000302 | 0 | 0 | 0 | 0
GRT32000000099 |  | -1.0658e-14 | -1.0769e-14 |  |  | -2.1427e-14 | TRUE | ANC32.0000.00305 | ANC32 | 0000 | 00305 | ANC32000000305 | 5036.78 | 133.6 | 2534.6 | 7704.98
GRT32000000102 |  | 0 | 1.0614e-13 |  |  | 1.0614e-13 | TRUE | ANC32.0000.00310 | ANC32 | 0000 | 00310 | ANC32000000310 | 2783.74 | 50.67 | 239.77 | 3074.18
GRT32000000107 |  | 0 | 8.8818e-16 |  |  | 8.8818e-16 | TRUE | ANC32.0000.00319 | ANC32 | 0000 | 00319 | ANC32000000319 | 0 | 0 | 0 | 0
GRT32000000108 |  | 12198.48 | 0 |  |  | 12198.48 | TRUE | ANC32.0000.00320 | ANC32 | 0000 | 00320 | ANC32000000320 | 293245.77 | 2969.54 | 94323.17 | 390538.48
GRT32000000111 |  | 29039.46 | 3370.25 |  |  | 32409.71 | TRUE | ANC32.0000.00322 | ANC32 | 0000 | 00322 | ANC32000000322 | 490330.43 | 1738.08 | 187121.31 | 679189.82
GRT32000000113 |  | 2969.23 | 1967.15 |  |  | 4936.38 | TRUE | ANC32.0000.00323 | ANC32 | 0000 | 00323 | ANC32000000323 | 3750.54 | 63.86 | 1298.38 | 5112.78
GRT32000000118 | 322.45 | 8615.74 | 1349.12 | 3890.33 |  | 14177.64 | TRUE | ANC32.0000.00325 | ANC32 | 0000 | 00325 | ANC32000000325 | 49039.88 | 1069.05 | 14461.54 | 64570.47
GRT32000000119 | 953.69 | 6775.16 | 4323.79 | 4504.35 |  | 16556.99 | TRUE | ANC32.0000.00326 | ANC32 | 0000 | 00326 | ANC32000000326 | 0 | 2.98 | 0 | 2.98
GRT32000000120 | 1595.26 | 118431.53 | 9283.1 | 83028.38 |  | 212338.27 | TRUE | ANC32.0000.00327 | ANC32 | 0000 | 00327 | ANC32000000327 | 1323627.78 | 16456.46 | 394222.85 | 1734307.09
GRT32000000121 | 7133.4 | 365884.74 | 23897.02 | 157868.22 |  | 554783.38 | TRUE | ANC32.0000.00328 | ANC32 | 0000 | 00328 | ANC32000000328 | 27114.24 | 1301.57 | 11861.94 | 40277.75
GRT32000000122 | 481.57 | 59345.65 | 5166.7 | 22391.69 |  | 87385.61 | TRUE | ANC32.0000.00329 | ANC32 | 0000 | 00329 | ANC32000000329 | 595777.18 | 2769.9 | 115093.22 | 713640.3
GRT32000000124 | 749.73 | 60689.44 | 3287.21 | 13631.99 |  | 78358.37 | TRUE | ANC32.0000.00330 | ANC32 | 0000 | 00330 | ANC32000000330 | 1641708.5 | 5726.74 | 329047.98 | 1976483.22
GRT32000000125 | 122.15 | 11892.02 | 176.44 | 5241.12 |  | 17431.73 | TRUE | ANC32.0000.00333 | ANC32 | 0000 | 00333 | ANC32000000333 | 283102.16 | 1550.24 | 55659.01 | 340311.41
GRT32000000126 | 335.16 | 69909.45 | 7481.98 | 26247.16 |  | 103973.75 | TRUE | ANC32.0000.00334 | ANC32 | 0000 | 00334 | ANC32000000334 | 89394.9 | 859.07 | 20290.6 | 110544.57
GRT32000000131 | 1435.48 | 172216.33 | 10546.52 | 70465.25 |  | 254663.58 | TRUE | ANC32.0000.00338 | ANC32 | 0000 | 00338 | ANC32000000338 | 3831.94 | 16.5 | 641.85 | 4490.29
GRT32000000132 | 463.82 | 25548.92 | 3982.38 | 14780.3 |  | 44775.42 | TRUE | ANC32.0000.00340 | ANC32 | 0000 | 00340 | ANC32000000340 | 0 | 0 | 0 | 0
GRT32000000133 | 7471.36 | 125238.18 | 7129 | 47761.32 |  | 187599.86 | TRUE | ANC32.0000.00342 | ANC32 | 0000 | 00342 | ANC32000000342 | 252.48 | 10.9 | 303.61 | 566.99
GRT32000000134 | 562.73 | 135864.52 | 6186.08 | 43309.8 |  | 185923.13 | TRUE | ANC32.0000.00364 | ANC32 | 0000 | 00364 | ANC32000000364 | 104.53 | 0.48 | 52.16 | 157.17
GRT32000000135 | 1689.85 | 145856.19 | 16893.85 | 72005.54 |  | 236445.43 | TRUE | ANC32.0000.00365 | ANC32 | 0000 | 00365 | ANC32000000365 | 1687.34 | 6.39 | 417.86 | 2111.59
GRT32000000137 | 1762.99 | 43676.76 | 1480.89 | 19670.55 |  | 66591.19 | TRUE | ANC32.0000.00366 | ANC32 | 0000 | 00366 | ANC32000000366 | 7375.34 | 33.26 | 417.86 | 7826.46
GRT32000000139 | 114.56 | 10772.98 | 1019.77 | 7184.93 |  | 19092.24 | TRUE | ANC32.0000.00367 | ANC32 | 0000 | 00367 | ANC32000000367 | 1896 | 0 | 0 | 1896
GRT32000000140 | 160.53 | 38507.78 | 879.66 | 11711.5 |  | 51259.47 | TRUE | ANC32.0000.00368 | ANC32 | 0000 | 00368 | ANC32000000368 | 0 | 0 | 0 | 0
GRT32000000141 | 517.81 | 42719.82 | 139.04 | 9495.78 |  | 52872.45 | TRUE | ANC32.0000.00369 | ANC32 | 0000 | 00369 | ANC32000000369 | 0 | 0 | 0 | 0
GRT32000000142 | 531.8 | 51348.94 | 7982.99 | 19174.85 |  | 79038.58 | TRUE | ANC32.0000.00370 | ANC32 | 0000 | 00370 | ANC32000000370 | 0 | 0 | 0 | 0
GRT32000000143 | 69.88 | 38622.66 | 1682.71 | 19046.03 |  | 59421.28 | TRUE | ANC32.0000.00371 | ANC32 | 0000 | 00371 | ANC32000000371 | 0 | 0 | 0 | 0
GRT32000000144 | 155.45 | 52876.9 | 80.53 | 7198.49 |  | 60311.37 | TRUE | ANC32.0000.00372 | ANC32 | 0000 | 00372 | ANC32000000372 | 0 | 0 | 0 | 0
GRT32000000145 | 585.97 | 77279.29 | 4575.56 | 31436.07 |  | 113876.89 | TRUE | ANC32.0000.00373 | ANC32 | 0000 | 00373 | ANC32000000373 | 0 | 0 | 0 | 0
GRT32000000149 | 50.6 | 15712.88 | 5465.22 | 2792.88 |  | 24021.58 | TRUE | ANC32.0000.00374 | ANC32 | 0000 | 00374 | ANC32000000374 | 0 | 0 | 0 | 0
GRT32000000159 | 195.68 | 48565.98 | 7722.83 | 13117.06 |  | 69601.55 | TRUE | ANC32.0000.00382 | ANC32 | 0000 | 00382 | ANC32000000382 | 1289.51 | 11.75 | 0 | 1301.26
GRT32000000160 | 40.61 | 10648.11 | 848.18 | 1880.56 |  | 13417.46 | TRUE | BET32.0000.00002 | BET32 | 0000 | 00002 | BET32000000002 | 697.46 | 0 | 0 | 697.46
GRT32000000161 | 200.43 | 55551.93 | 2734.52 | 9281.37 |  | 67768.25 | TRUE | BET32.0000.00003 | BET32 | 0000 | 00003 | BET32000000003 | 3921 | 0 | 2374.5 | 6295.5
GRT32000000162 | 6.27 | 1031.61 |  |  |  | 1037.88 | TRUE | BET32.0000.00004 | BET32 | 0000 | 00004 | BET32000000004 | 819.48 | 0 | 215.62 | 1035.1
GRT32000200001 |  | 2403425.36 | 263405.88 |  |  | 2666831.24 | TRUE | BET32.0000.00005 | BET32 | 0000 | 00005 | BET32000000005 | 0 | 0 | 0 | 0
GRT32000200002 |  | 38851.38 | 5742.37 |  |  | 44593.75 | TRUE | BET32.0000.00011 | BET32 | 0000 | 00011 | BET32000000011 | 0 | 0 | 0 | 0
GRT32000200005 |  | 3651.58 | 754.6 |  |  | 4406.18 | TRUE | BET32.0000.00013 | BET32 | 0000 | 00013 | BET32000000013 | 0 | 0 | 0 | 0
PIG32000000001 |  | 484 |  |  |  | 484 | TRUE | BET32.0000.00016 | BET32 | 0000 | 00016 | BET32000000016 | 0 | 0 | 0 | 0
PIG32000000011 |  | 59945.4 |  |  |  | 59945.4 | TRUE | BET32.0000.00018 | BET32 | 0000 | 00018 | BET32000000018 | 0 | 0 | 0 | 0
PIG32000000013 |  | 4680.98 | 3374.1 |  |  | 8055.08 | TRUE | BET32.0000.00022 | BET32 | 0000 | 00022 | BET32000000022 | 101350.69 | 0 | 24164.39 | 125515.08
PIG32000000016 |  | -85440.98 |  |  |  | -85440.98 | TRUE | BET32.0000.00023 | BET32 | 0000 | 00023 | BET32000000023 | 0 | 0 | 0 | 0
PIG32000000026 |  | 425 |  |  |  | 425 | TRUE | BET32.0000.00024 | BET32 | 0000 | 00024 | BET32000000024 | 0 | 0 | 0 | 0
PIG32000000039 |  | 314.96 | 351.93 |  |  | 666.89 | TRUE | BET32.0000.00025 | BET32 | 0000 | 00025 | BET32000000025 | 132431.2 | 0 | 3151.42 | 135582.62
PIG32000000043 |  | 254279.38 | 12623.34 |  |  | 266902.72 | TRUE | BET32.0000.00026 | BET32 | 0000 | 00026 | BET32000000026 | 0 | 0 | 0 | 0
PIG32000000049 |  | 68805.32 |  |  |  | 68805.32 | TRUE | BET32.0000.00027 | BET32 | 0000 | 00027 | BET32000000027 | 67.25 | 0 | 20.46 | 87.71
PIG32000000051 |  | 16102.63 | 2143.62 |  |  | 18246.25 | TRUE | BET32.0000.00030 | BET32 | 0000 | 00030 | BET32000000030 | 0 | 0 | 0 | 0
PIG32000000052 | 900.58 | 125294.6 | 4767.77 | 25877.19 |  | 156840.14 | TRUE | BET32.0000.00040 | BET32 | 0000 | 00040 | BET32000000040 | 0 | 0 | 0 | 0
PIG32000000053 | 243.91 | 66806.98 | 5024.43 | 10047.63 |  | 82122.95 | TRUE | BET32.0000.00042 | BET32 | 0000 | 00042 | BET32000000042 | 0 | 0 | 0 | 0
PIG32000000056 | 154.5 | 2605.84 | 940.27 | 1081.17 |  | 4781.78 | TRUE | BET32.0000.00043 | BET32 | 0000 | 00043 | BET32000000043 | 0 | 0 | 0 | 0
PIG32000000057 | 231.75 | 11769.83 | 442.43 | 2371.54 |  | 14815.55 | TRUE | BET32.0000.00044 | BET32 | 0000 | 00044 | BET32000000044 | 0 | 0 | 0 | 0
PIG32000000058 | 1826.02 | 262641.57 | 16522.84 | 115061.86 |  | 396052.29 | TRUE | BET32.0000.00045 | BET32 | 0000 | 00045 | BET32000000045 | 757.41 | 0 | 283.93 | 1041.34
PIG32000000059 | 694.96 | 133232.01 | 1357.84 | 49397.44 |  | 184682.25 | TRUE | BET32.0000.00046 | BET32 | 0000 | 00046 | BET32000000046 | 0 | 0 | 0 | 0
PIG32000000060 | 3174.59 | 1278345.32 | 31641.93 | 401193.12 |  | 1714354.96 | TRUE | BET32.0000.00048 | BET32 | 0000 | 00048 | BET32000000048 | 0 | 0 | 0 | 0
PIG32000000061 | 458.22 | 12557.87 | 243.8 | 9847.96 |  | 23107.85 | TRUE | BET32.0000.00049 | BET32 | 0000 | 00049 | BET32000000049 | 0 | 0.09 | -2.4009e-15 | 0.09
PIG32000000062 | 36.09 | 7497.08 |  | 1329.49 |  | 8862.66 | TRUE | BET32.0000.00059 | BET32 | 0000 | 00059 | BET32000000059 | 97054.56 | 1126.61 | 23045.4 | 121226.57
PIG32000000063 | 55.23 | 23866.22 | 5206.97 | -20788.33 |  | 8340.09 | TRUE | BET32.0000.00060 | BET32 | 0000 | 00060 | BET32000000060 | -7519.36 | 0 | -2304.02 | -9823.38
PIG32000000064 | 87.16 | 56173.32 | 1207.64 | 3493.81 |  | 60961.93 | TRUE | BET32.0000.00061 | BET32 | 0000 | 00061 | BET32000000061 | 0 | 0 | 0 | 0
PIG32000000065 | 748.95 | 41335.49 | 1879.53 | 13957.02 |  | 57920.99 | TRUE | BET32.0000.00063 | BET32 | 0000 | 00063 | BET32000000063 | 0 | 0 | 0 | 0
PIG32000000066 | 322.3 | 23614.33 | 150.61 | 6486.65 |  | 30573.89 | TRUE | GRT32.0000.00002 | GRT32 | 0000 | 00002 | GRT32000000002 | 0 | 0 | 0 | 0
PIG32000000069 | 74.53 | 13576.26 | 4351.94 | 2603.34 |  | 20606.07 | TRUE | GRT32.0000.00004 | GRT32 | 0000 | 00004 | GRT32000000004 | 0 | 0 | 0 | 0
PIG32000000070 |  | -2.2098e-12 | -3.2685e-13 |  |  | -2.5366e-12 | TRUE | GRT32.0000.00019 | GRT32 | 0000 | 00019 | GRT32000000019 | 0 | 0 | 0 | 0
PIG32000000071 | 4.6 | 506 |  |  |  | 510.6 | TRUE | GRT32.0000.00020 | GRT32 | 0000 | 00020 | GRT32000000020 | 82681.3 | 0 | 3630.75 | 86312.05
PIG32000000073 | 17.02 | 1478.94 | 389.2 |  |  | 1885.16 | TRUE | GRT32.0000.00021 | GRT32 | 0000 | 00021 | GRT32000000021 | 0 | 0 | 0 | 0
PIG32000000074 | 8.03 | 2963.7 | 193.42 | 371.59 |  | 3536.74 | TRUE | GRT32.0000.00022 | GRT32 | 0000 | 00022 | GRT32000000022 | 1117.15 | 0 | 311.46 | 1428.61
PSI32000000035 | 71.71 | 1792.92 | 592.24 | 1345.65 |  | 3802.52 | TRUE | GRT32.0000.00027 | GRT32 | 0000 | 00027 | GRT32000000027 | 0 | 0 | 0 | 0
SUP32000200001 | 68.27 | 30351.79 | 15984.96 |  |  | 46405.02 | TRUE | GRT32.0000.00038 | GRT32 | 0000 | 00038 | GRT32000000038 | 0 | 0 | 0 | 0
SUP32000200004 | 466.88 | 8273.38 | 4736.96 |  |  | 13477.22 | TRUE | GRT32.0000.00040 | GRT32 | 0000 | 00040 | GRT32000000040 | 19346.1 | 0 | 5203.85 | 24549.95
SUP32000300002 | 201.76 | 15152.78 | 8112.98 |  |  | 23467.52 | TRUE | GRT32.0000.00044 | GRT32 | 0000 | 00044 | GRT32000000044 | 0 | 0 | 0 | 0
[7 empty] | TRUE | GRT32.0000.00051 | GRT32 | 0000 | 00051 | GRT32000000051 | 0 | 0 | 0 | 0
[7 empty] | TRUE | GRT32.0000.00052 | GRT32 | 0000 | 00052 | GRT32000000052 | 0 | 0 | 0 | 0
[7 empty] | TRUE | GRT32.0000.00055 | GRT32 | 0000 | 00055 | GRT32000000055 | 0 | 0 | 0 | 0
[7 empty] | TRUE | GRT32.0000.00056 | GRT32 | 0000 | 00056 | GRT32000000056 | 28325.74 | 0 | 3350.4 | 31676.14
[7 empty] | TRUE | GRT32.0000.00057 | GRT32 | 0000 | 00057 | GRT32000000057 | 0 | 0 | 0 | 0
[7 empty] | TRUE | GRT32.0000.00058 | GRT32 | 0000 | 00058 | GRT32000000058 | 0 | 0 | 0 | 0
[7 empty] | TRUE | GRT32.0000.00059 | GRT32 | 0000 | 00059 | GRT32000000059 | 0 | 0 | 0 | 0
[7 empty] | TRUE | GRT32.0000.00060 | GRT32 | 0000 | 00060 | GRT32000000060 | 0 | 0 | 0 | 0
[7 empty] | TRUE | GRT32.0000.00061 | GRT32 | 0000 | 00061 | GRT32000000061 | 0 | 0 | 0 | 0
[7 empty] | TRUE | GRT32.0000.00062 | GRT32 | 0000 | 00062 | GRT32000000062 | 11506.74 | 0 | 3465.08 | 14971.82
[7 empty] | TRUE | GRT32.0000.00063 | GRT32 | 0000 | 00063 | GRT32000000063 | 299286.06 | 0 | 24634.87 | 323920.93
[7 empty] | TRUE | GRT32.0000.00064 | GRT32 | 0000 | 00064 | GRT32000000064 | 0 | 0 | 0 | 0
[7 empty] | TRUE | GRT32.0000.00065 | GRT32 | 0000 | 00065 | GRT32000000065 | 0 | 0 | 0 | 0
[7 empty] | TRUE | GRT32.0000.00066 | GRT32 | 0000 | 00066 | GRT32000000066 | 0 | 0 | 0 | 0
[7 empty] | TRUE | GRT32.0000.00067 | GRT32 | 0000 | 00067 | GRT32000000067 | 105062.46 | 0 | 11364.33 | 116426.79
[7 empty] | TRUE | GRT32.0000.00068 | GRT32 | 0000 | 00068 | GRT32000000068 | 0 | 0 | 0 | 0
[7 empty] | TRUE | GRT32.0000.00075 | GRT32 | 0000 | 00075 | GRT32000000075 | 0 | 0 | 0 | 0
[7 empty] | TRUE | GRT32.0000.00077 | GRT32 | 0000 | 00077 | GRT32000000077 | 0 | 0 | 0 | 0
[7 empty] | TRUE | GRT32.0000.00078 | GRT32 | 0000 | 00078 | GRT32000000078 | 49584.82 | 0 | 5432.68 | 55017.5
[7 empty] | TRUE | GRT32.0000.00096 | GRT32 | 0000 | 00096 | GRT32000000096 | 267.59 | 0 | 260.03 | 527.62
[7 empty] | TRUE | GRT32.0000.00097 | GRT32 | 0000 | 00097 | GRT32000000097 | 444459.95 | 2076.33 | 300684.3 | 747220.58
[7 empty] | TRUE | GRT32.0000.00098 | GRT32 | 0000 | 00098 | GRT32000000098 | 0 | 0 | 0 | 0
[7 empty] | TRUE | GRT32.0000.00100 | GRT32 | 0000 | 00100 | GRT32000000100 | 0 | 0 | 0 | 0
[7 empty] | TRUE | GRT32.0000.00101 | GRT32 | 0000 | 00101 | GRT32000000101 | 0 | 0 | 0 | 0
[7 empty] | TRUE | GRT32.0000.00102 | GRT32 | 0000 | 00102 | GRT32000000102 | 0 | 0 | 1.0614e-13 | 1.0614e-13
[7 empty] | TRUE | GRT32.0000.00103 | GRT32 | 0000 | 00103 | GRT32000000103 | 0 | 0 | 0 | 0
[7 empty] | TRUE | GRT32.0000.00104 | GRT32 | 0000 | 00104 | GRT32000000104 | 0 | 0 | 0 | 0
[7 empty] | TRUE | GRT32.0000.00105 | GRT32 | 0000 | 00105 | GRT32000000105 | 0 | 0 | 0 | 0
[7 empty] | TRUE | GRT32.0000.00106 | GRT32 | 0000 | 00106 | GRT32000000106 | 0 | 0 | 0 | 0
[7 empty] | TRUE | GRT32.0000.00107 | GRT32 | 0000 | 00107 | GRT32000000107 | 0 | 0 | 8.8818e-16 | 8.8818e-16
[7 empty] | TRUE | GRT32.0000.00108 | GRT32 | 0000 | 00108 | GRT32000000108 | 12198.48 | 0 | 0 | 12198.48
[7 empty] | TRUE | GRT32.0000.00109 | GRT32 | 0000 | 00109 | GRT32000000109 | 0 | 0 | 0 | 0
[7 empty] | TRUE | GRT32.0000.00118 | GRT32 | 0000 | 00118 | GRT32000000118 | 8615.74 | 322.45 | 5239.45 | 14177.64
[7 empty] | TRUE | GRT32.0000.00120 | GRT32 | 0000 | 00120 | GRT32000000120 | 118431.53 | 1595.26 | 92311.48 | 212338.27
[7 empty] | TRUE | GRT32.0000.00121 | GRT32 | 0000 | 00121 | GRT32000000121 | 365884.74 | 7133.4 | 181765.24 | 554783.38
[7 empty] | TRUE | GRT32.0000.00122 | GRT32 | 0000 | 00122 | GRT32000000122 | 59345.65 | 481.57 | 27558.39 | 87385.61
[7 empty] | TRUE | GRT32.0000.00123 | GRT32 | 0000 | 00123 | GRT32000000123 | 0 | 0 | 0 | 0
[7 empty] | TRUE | GRT32.0000.00124 | GRT32 | 0000 | 00124 | GRT32000000124 | 60689.44 | 749.73 | 16919.2 | 78358.37
[7 empty] | TRUE | GRT32.0000.00130 | GRT32 | 0000 | 00130 | GRT32000000130 | 0 | 0 | 0 | 0
[7 empty] | TRUE | GRT32.0000.00131 | GRT32 | 0000 | 00131 | GRT32000000131 | 172216.33 | 1435.48 | 81011.77 | 254663.58
[7 empty] | TRUE | GRT32.0000.00133 | GRT32 | 0000 | 00133 | GRT32000000133 | 125238.18 | 7471.36 | 54890.32 | 187599.86
[7 empty] | TRUE | GRT32.0000.00134 | GRT32 | 0000 | 00134 | GRT32000000134 | 135864.52 | 562.73 | 49495.88 | 185923.13
[7 empty] | TRUE | GRT32.0000.00139 | GRT32 | 0000 | 00139 | GRT32000000139 | 10772.98 | 114.56 | 8204.7 | 19092.24
[7 empty] | TRUE | GRT32.0000.00140 | GRT32 | 0000 | 00140 | GRT32000000140 | 38507.78 | 160.53 | 12591.16 | 51259.47
[7 empty] | TRUE | GRT32.0000.00141 | GRT32 | 0000 | 00141 | GRT32000000141 | 42719.82 | 517.81 | 9634.82 | 52872.45
[7 empty] | TRUE | GRT32.0000.00142 | GRT32 | 0000 | 00142 | GRT32000000142 | 51348.94 | 531.8 | 27157.84 | 79038.58
[7 empty] | TRUE | GRT32.0000.00144 | GRT32 | 0000 | 00144 | GRT32000000144 | 52876.9 | 155.45 | 7279.02 | 60311.37
[7 empty] | TRUE | GRT32.0000.00149 | GRT32 | 0000 | 00149 | GRT32000000149 | 15712.88 | 50.6 | 8258.1 | 24021.58
[7 empty] | TRUE | GRT32.0000.00159 | GRT32 | 0000 | 00159 | GRT32000000159 | 48565.98 | 195.68 | 20839.89 | 69601.55
[7 empty] | TRUE | GRT32.0000.00160 | GRT32 | 0000 | 00160 | GRT32000000160 | 10648.11 | 40.61 | 2728.74 | 13417.46
[7 empty] | TRUE | GRT32.0000.00161 | GRT32 | 0000 | 00161 | GRT32000000161 | 55551.93 | 200.43 | 12015.89 | 67768.25
[7 empty] | TRUE | GRT32.0000.00162 | GRT32 | 0000 | 00162 | GRT32000000162 | 1031.61 | 6.27 | 0 | 1037.88
[7 empty] | TRUE | PIG32.0000.00001 | PIG32 | 0000 | 00001 | PIG32000000001 | 484 | 0 | 0 | 484
[7 empty] | TRUE | PIG32.0000.00007 | PIG32 | 0000 | 00007 | PIG32000000007 | 0 | 0 | 0 | 0
[7 empty] | TRUE | PIG32.0000.00011 | PIG32 | 0000 | 00011 | PIG32000000011 | 59945.4 | 0 | 0 | 59945.4
[7 empty] | TRUE | PIG32.0000.00012 | PIG32 | 0000 | 00012 | PIG32000000012 | 0 | 0 | 0 | 0
[7 empty] | TRUE | PIG32.0000.00013 | PIG32 | 0000 | 00013 | PIG32000000013 | 4680.98 | 0 | 3374.1 | 8055.08
[7 empty] | TRUE | PIG32.0000.00015 | PIG32 | 0000 | 00015 | PIG32000000015 | 0 | 0 | 0 | 0
[7 empty] | TRUE | PIG32.0000.00016 | PIG32 | 0000 | 00016 | PIG32000000016 | -85440.98 | 0 | 0 | -85440.98
[7 empty] | TRUE | PIG32.0000.00017 | PIG32 | 0000 | 00017 | PIG32000000017 | 0 | 0 | 0 | 0
[7 empty] | TRUE | PIG32.0000.00022 | PIG32 | 0000 | 00022 | PIG32000000022 | 0 | 0 | 0 | 0
[7 empty] | TRUE | PIG32.0000.00024 | PIG32 | 0000 | 00024 | PIG32000000024 | 0 | 0 | 0 | 0
[7 empty] | TRUE | PIG32.0000.00027 | PIG32 | 0000 | 00027 | PIG32000000027 | 0 | 0 | 0 | 0
[7 empty] | TRUE | PIG32.0000.00028 | PIG32 | 0000 | 00028 | PIG32000000028 | 0 | 0 | 0 | 0
[7 empty] | TRUE | PIG32.0000.00030 | PIG32 | 0000 | 00030 | PIG32000000030 | 0 | 0 | 0 | 0
[7 empty] | TRUE | PIG32.0000.00037 | PIG32 | 0000 | 00037 | PIG32000000037 | 0 | 0 | 0 | 0
[7 empty] | TRUE | PIG32.0000.00038 | PIG32 | 0000 | 00038 | PIG32000000038 | 0 | 0 | 0 | 0
[7 empty] | TRUE | PIG32.0000.00039 | PIG32 | 0000 | 00039 | PIG32000000039 | 314.96 | 0 | 351.93 | 666.89
[7 empty] | TRUE | PIG32.0000.00041 | PIG32 | 0000 | 00041 | PIG32000000041 | 0 | 0 | 0 | 0
[7 empty] | TRUE | PIG32.0000.00043 | PIG32 | 0000 | 00043 | PIG32000000043 | 254279.38 | 0 | 12623.34 | 266902.72
[7 empty] | TRUE | PIG32.0000.00047 | PIG32 | 0000 | 00047 | PIG32000000047 | 0 | 0 | 0 | 0
[7 empty] | TRUE | PIG32.0000.00049 | PIG32 | 0000 | 00049 | PIG32000000049 | 68805.32 | 0 | 0 | 68805.32
[7 empty] | TRUE | PIG32.0000.00050 | PIG32 | 0000 | 00050 | PIG32000000050 | 0 | 0 | 0 | 0
[7 empty] | TRUE | PIG32.0000.00051 | PIG32 | 0000 | 00051 | PIG32000000051 | 16102.63 | 0 | 2143.62 | 18246.25
[7 empty] | TRUE | PIG32.0000.00052 | PIG32 | 0000 | 00052 | PIG32000000052 | 125294.6 | 900.58 | 30644.96 | 156840.14
[7 empty] | TRUE | PIG32.0000.00053 | PIG32 | 0000 | 00053 | PIG32000000053 | 66806.98 | 243.91 | 15072.06 | 82122.95
[7 empty] | TRUE | PIG32.0000.00055 | PIG32 | 0000 | 00055 | PIG32000000055 | 0 | 0 | 0 | 0
[7 empty] | TRUE | PIG32.0000.00057 | PIG32 | 0000 | 00057 | PIG32000000057 | 11769.83 | 231.75 | 2813.97 | 14815.55
[7 empty] | TRUE | PIG32.0000.00061 | PIG32 | 0000 | 00061 | PIG32000000061 | 12557.87 | 458.22 | 10091.76 | 23107.85
[7 empty] | TRUE | PIG32.0000.00064 | PIG32 | 0000 | 00064 | PIG32000000064 | 56173.32 | 87.16 | 4701.45 | 60961.93
[7 empty] | TRUE | PIG32.0000.00065 | PIG32 | 0000 | 00065 | PIG32000000065 | 41335.49 | 748.95 | 15836.55 | 57920.99
[7 empty] | TRUE | PIG32.0000.00066 | PIG32 | 0000 | 00066 | PIG32000000066 | 23614.33 | 322.3 | 6637.26 | 30573.89
[7 empty] | TRUE | PIG32.0000.00067 | PIG32 | 0000 | 00067 | PIG32000000067 | 0 | 0 | 0 | 0
[7 empty] | TRUE | PIG32.0000.00068 | PIG32 | 0000 | 00068 | PIG32000000068 | 0 | 0 | 0 | 0
[7 empty] | TRUE | PIG32.0000.00069 | PIG32 | 0000 | 00069 | PIG32000000069 | 13576.26 | 74.53 | 6955.28 | 20606.07
[7 empty] | TRUE | PIG32.0000.00070 | PIG32 | 0000 | 00070 | PIG32000000070 | -2.2098e-12 | 0 | -3.2685e-13 | -2.5366e-12
[7 empty] | TRUE | PIG32.0000.00071 | PIG32 | 0000 | 00071 | PIG32000000071 | 506 | 4.6 | 0 | 510.6
[7 empty] | TRUE | PIG32.0000.00072 | PIG32 | 0000 | 00072 | PIG32000000072 | 0 | 0 | 0 | 0
[7 empty] | TRUE | PIG32.0000.00073 | PIG32 | 0000 | 00073 | PIG32000000073 | 1478.94 | 17.02 | 389.2 | 1885.16
[7 empty] | TRUE | PIG32.0000.00074 | PIG32 | 0000 | 00074 | PIG32000000074 | 2963.7 | 8.03 | 565.01 | 3536.74
[7 empty] | TRUE | PIG32.0000.00075 | PIG32 | 0000 | 00075 | PIG32000000075 | 0 | 0 | 0 | 0
[7 empty] | TRUE | PIG32.0000.00076 | PIG32 | 0000 | 00076 | PIG32000000076 | 0 | 0 | 0 | 0
[7 empty] | TRUE | PIG32.0000.00077 | PIG32 | 0000 | 00077 | PIG32000000077 | 0 | 0 | 0 | 0
18026779401
18026794401
18026795501
19026867802
20026983300
21026123000
21026152101
22026161800
22026165501
22026178300
22026207100
22026224201
22026231301
22026236501
22026236901
22026237301
22026238401
22026239702
23026258300
23026270600
23026283101
23026283600
23026286900
23026287300
23026300300
23026301200
23026306800
23026308100
24026312301
24026312500
24026313000
24026314400
24026316701
24026324100
24026333201
24026333600
24026336600
24026340200
24026340500
24026340800
24026341000
24026341800
24026341900
24026345800
24026348200
24026348900
24026349200
24026349300
24026349500
24026351200
24026352000
24026354300
24026355200
24026355300
24026355900
24026356000
24026356200
24026356500
24026357000
24026357400
24026358600
24026358700
24026358801
24026359401
24026360200
24026360500
24026360700
24026361300
24026361400
24026361500
24026362000
24026363600
24026363800
24026364900
24026365000
24026365300
24026365700
24026366400
24026367000
24026367700
24026368000
24026368600
24026368800
24026369000
24026370500
24026370600
24026371100
24026371600
24026371800
24026372000
24026373800
24026375200
24026376300
24026376700
24026376901
25026377300
25026377600
25026377900
25026378600
25026378800
25026379000
25026381300
25026381700
25026381800
25026385100
25026392000
25026393800
25026394000
25026395600
25026396000
25026397400
25026398400
25026398800
25026399300
25026399900
25026400200
25026400900
25026403000
25026403300
25026405400
25026406000
25026406300
25026407800
25026409300
25026409900
25026410100
25026410400
25026410600
25026410800