KY | KY - CENTRAL | 2629 | 22125012100 |  | 100352271 |  | 6744208K |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | CAROLINA | 337 CAROLINA AV | 049 | WIN | 2022-08-28 | U938684 | U125763 | 2022-08-18 | 2022-12-30 |  |  | CHARLES COMBS | 2022-08-15 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2610 | 0 | 0 | 0 | 2610 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22125012200 |  | 100352203 |  | 6744208K |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | ROBINSON | 200 W ROBINSON CT | 049 | WIN | 2022-08-28 | U938684 | U125763 | 2022-08-18 | 2022-12-30 |  |  | CHARLES COMBS | 2022-08-15 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2610 | 0 | 0 | 0 | 2610 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22125012300 |  | 100348162 |  | 6748208I |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | COOK | 253 COOK AV | 049 | WIN | 2022-08-29 | U938684 | U125763 | 2022-08-18 | 2022-12-30 |  |  | CHARLES COMBS | 2022-08-15 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2610 | 0 | 0 | 0 | 2610 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22125012400 |  | 100348177 |  | 6748208I |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | MUTUAL | 106 MUTUAL AV | 049 | WIN | 2022-08-29 | U938684 | U125763 | 2022-08-18 | 2022-12-30 |  |  | CHARLES COMBS | 2022-08-15 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2610 | 0 | 0 | 0 | 2610 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22125012500 |  | 100467404 |  | 6744204I |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | HEATHER | 42 HEATHER LN | 049 | WIN | 2022-09-27 | U125559 | U125763 | 2022-08-18 | 2022-12-30 |  |  | CHARLES COMBS | 2022-08-15 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2849.61 | 0 | 0 | 0 | 2849.61 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22125014000 |  | 500108015 |  | 6744208J |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | WESTSIDE | 178 WESTSIDE DR | 049 | WIN | 2022-08-29 | U938684 | U125763 | 2022-08-18 | 2022-12-30 |  |  | CHARLES COMBS | 2022-08-15 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2610 | 0 | 0 | 0 | 2610 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964253000 |  | 100348011 |  | 6748208I | 2075093 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | STERLING | 104 STERLING ST | 049 | WIN | 2022-08-28 | U938684 | U134723 | 2022-01-06 | 2022-12-30 |  |  | CHARLES COMBS | 2022-08-15 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26290043 |  | 1 | 2675 | 0 | 0 | 0 | 2675 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22970120100 |  | 100280349 |  | 6688228J | 2181158 |  |  | 565 | EX | REPLACE SL W/21-0261319-00 | 2600B | LYONS | 142 LYONS DR | 073 | FRA | 2022-08-15 | U128410 | U134723 | 2022-01-27 | 2022-12-30 |  |  | CDESPAIN | 2022-08-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3527.6 | 0 | 0 | 0 | 3527.6 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979016300 |  | 100241518 |  | 7356256B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CARTER | 2539 CARTER AV B | 019 | ASH | 2022-08-30 | U135195 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | KEITH HEDGES | 2022-08-15 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 780.44 | 0 | 0 | 0 | 780.44 | 0 | 0 | 0
KY | KY - EAST | 2631 | 13121088600 |  | 100264964 |  | 7348248-K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CANNONSBURG | 1621 CANNONSBURG RD | 019 | CAN | 2022-11-14 | U125881 | U124967 | 2013-03-01 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-08-16 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18658935400 |  | 100242093 | 28 | 7356252D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | HARRIS | 926 HARRIS ST | 019 | CAT | 2022-11-14 | U125881 | SJUDE | 2018-11-28 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-08-16 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21026152700 |  |  |  | 6748204H | 2183464 | U128885 |  | 583 | EX | EMER - INSTALL ODORIZER | 2629M | STATE RT 89 | STATE RT 89 | 049 | WIN | 2023-02-14 | U123258 | U128885 | 2021-11-30 | 2023-12-21 | 2023-12-31 | 2022-08-16 | JPASLEY | 2022-08-16 | 2022-08-15 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00583 | 3200583 |  |  | WP1527 |  |  | 100 | 058332210261527 | 22.5667 | 12 | 170463.75 | 1785.6 | 131413.21 | 570.34 | 16774.8 | 0 | 1580.32 | 18339.48
KY | KY - CENTRAL | 2629 | 21026152800 |  |  |  | 6748204H | 2183464 | U128885 |  | 584 | EX | EMER - RETIRE ODORIZER | 2629M | STATE RT 89 | STATE RT 89 | 049 | WIN | 2023-02-14 | U123258 | U128885 | 2021-11-30 | 2023-12-29 | 2023-12-31 | 2022-08-16 | JPASLEY | 2022-08-16 | 2022-08-15 |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00584 | 3200584 |  |  | WP1528 |  |  | 100 | 058432210261528 | 43.2333 | 0 | 62508.06 | 2891.92 | 59442.35 | 173.79 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883060900 |  | 501180421 |  | 7356252F | 1427105 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | GARDEN | 6534 GARDEN LN | 019 | CAT | 2022-11-14 | U125881 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-08-16 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1402.64 | 0 | 0 | 0 | 1402.64 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883066600 |  | 100264903 |  | 7348248K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | COPLEY | 12619 COPLEY RD | 019 | CAN | 2022-11-14 | U125881 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-08-16 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883095400 |  | 100264931 |  | 7348248K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CANNONSBURG | 1920 CANNONSBURG RD | 019 | CAN | 2022-11-14 | U125881 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-08-16 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883101500 |  | 500624775 |  | 7348248L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MIDLAND TRAIL | 11834 MIDLAND TRAIL RD | 019 | CAN | 2022-08-16 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-08-16 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883141600 |  | 501152808 |  | 7348244L | 1421890 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BONANZA | 3019 BONANZA DR | 019 | CAT | 2022-11-14 | U125881 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-08-16 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883145200 |  | 500473317 |  | 7348248L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | JASON | 2731 JASON RD | 019 | CAN | 2022-09-13 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-08-16 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1535.48 | 0 | 0 | 0 | 1535.48 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883246800 |  | 100264830 |  | 7348248L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | JOHNSON | 11734 E JOHNSON RD | 019 | CAN | 2022-08-16 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-08-16 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883255600 |  | 500555967 |  | 7348248K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | STATE RT 180 | 13233 STATE RT 180 | 019 | CAN | 2022-08-16 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-08-16 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1836.7 | 0 | 0 | 0 | 1836.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916439400 |  | 100264038 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2500 MAIN ST W | 019 | ASH | 2022-08-16 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-08-16 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2463.56 | 0 | 0 | 0 | 2463.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916439600 |  | 100263546 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2505 MAIN ST W | 019 | ASH | 2022-08-16 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-08-16 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2303.21 | 0 | 0 | 0 | 2303.21 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958609000 |  | 100331717 |  | 6720212N | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | MENTELLE | 48 MENTELLE PR | 067 | LEX | 2022-08-16 | U126308 | U134723 | 2021-12-08 | 2022-12-30 |  |  | J ENSMINGER | 2022-08-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4214.18 | 0 | 0 | 0 | 4214.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959035100 |  | 100445829 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | LIMESTONE | 800 S LIMESTONE ST | 067 | LEX | 2022-08-17 | U128336 | U134723 | 2021-12-10 | 2022-12-30 |  |  | JOSHUA COX | 2022-08-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1447.94 | 0 | 0 | 0 | 1447.94 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959970900 |  | 500438618 |  | 6760172G |  |  |  | 566 | EX | ABANDON SL | 2600B | KIMBALL | 82 KIMBALL RD | 065 | IRV | 2022-08-17 | U126602 | U131066 | 2021-12-16 | 2021-12-30 |  |  | DEREK PAYTPN | 2022-08-16 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 3491.69 | 0 | 0 | 0 | 3491.69 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22026191500 |  |  |  | 7332132J | 2289123 | U122858 |  | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2621M | SR899 1429 | SR899 1429 | 119 | PIP | 2022-08-25 | U125936 | U136124 | 2022-05-26 | 2022-12-30 | 2022-12-31 | 2022-07-12 | M.RYAN | 2022-08-16 |  |  | F | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00909 | 3200909 |  |  | WP1915 |  |  | 100 | 090932220261915 |  | 0 | 1457.43 | 0 | 0 | 0 | 1456 | 0 | 1.43 | 0
KY | KY - EAST | 2633 | 22026191600 |  |  |  | 7332132J | 2289123 | U122858 |  | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2621M | SR899 1429 | SR899 1429 | 119 | PIP | 2022-08-25 | U125936 | U136124 | 2022-05-26 | 2022-12-30 | 2022-12-31 | 2022-07-12 | M. RYAN | 2022-08-16 | 2022-07-12 |  | F | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00910 | 3200910 |  |  | WP1916 |  |  | 100 | 091032220261916 | 5.5167 | 0 | 447.49 | 423.56 | 0 | 23.93 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22122140900 |  | 100240863 |  | 7324132E | 2290467 |  |  | 566 | EX | ABANDON SL - HINDMAN FLOOD | 2600B | DYER | 65 DYER RD | 119 | HIN | 2022-08-29 | U125566 | U125208 | 2022-08-08 | 2022-08-08 |  |  | DESKAGG | 2022-08-16 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.0667 | 1 | 65.22 | 48.82 | 0 | 16.4 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22122141500 |  | 100436645 |  | 7324132E | 2290467 |  |  | 566 | EX | ABANDON SL - HINDMAN FLOOD | 2600B | KENTUCKY | 11 KENTUCKY DR | 119 | HIN | 2022-08-29 | U125566 | U125208 | 2022-08-08 | 2022-08-08 |  |  | DESKAGG | 2022-08-16 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.55 | 1 | 34.16 | 25.58 | 0 | 8.58 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22122146300 |  | 100240937 |  | 7324132H | 2290467 |  |  | 566 | EX | ABANDON SL - HINDMAN FLOOD | 2600B | HIGHWAY 550 E | 2028 HIGHWAY 550 E 5 | 119 | LEB | 2022-08-16 | DESKAGG | U125208 | 2022-08-08 | 2022-08-08 |  |  | DESKAGG | 2022-08-16 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.05 | 1 | 191.24 | 143.15 | 0 | 48.09 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22122670300 |  | 100437110 |  | 7324132E | 2290467 |  |  | 566 | EX | ABANDON SL - HINDMAN FLOOD | 2600B | KENTUCKY | 11 KENTUCKY DR | 119 | HIN | 2022-08-29 | U125566 | U125208 | 2022-08-09 | 2022-08-08 |  |  | DESKAGG | 2022-08-16 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 11.2833 | 2 | 658.77 | 523.37 | 0 | 135.4 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22122901600 |  | 100343112 |  | 7236212D |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTRQD | 2621P | WINCHESTER | 921 WINCHESTER RD | 173 | MT | 2022-08-16 | U930915 | U132002 | 2022-08-10 | 2022-08-23 | 2022-09-08 |  | DENNING | 2022-08-16 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22124033200 |  | 100258120 |  | 7348268M | 1313372 |  |  | 565 | EX | SERVICE LINE - REPLACE D258012 | 2621P | 2ND | 400 2ND AV | 089 | WOR | 2022-08-16 | RECUMP | U132823 | 2022-08-15 | 2022-08-15 | 2022-08-15 |  | RECUMP | 2022-08-16 | 2022-08-16 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 22.7833 | 4 | 2356.3 | 759.65 | 189.05 | 1364.7 | 42.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22124214700 |  | 100312818 |  | 6716208E |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | SOUTHGATE | 2333 SOUTHGATE DR | 067 | LEX | 2022-08-22 | U125208 | U124449 | 2022-08-16 | 2022-08-16 |  |  | KKINDER | 2022-08-16 | 2022-08-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.4167 | 4 | 2220.44 | 1286.89 | 0 | 77.32 | 856.23 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22124222800 |  | 100264036 |  | 7352260N | 2176770 |  |  | 565 | EX | RPLC SL/21026993400 | 2600B | MAIN | 2434 MAIN ST W | 019 | ASH | 2022-08-16 | U124015 | U125763 | 2022-08-16 | 2022-12-30 |  |  | ORA SLONE | 2022-08-16 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2821.04 | 0 | 0 | 0 | 2821.04 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22125012600 |  | 100404295 |  | 6744208L |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | SPRUCE | 105 SPRUCE CT | 049 | WIN | 2022-08-30 | U938684 | U125763 | 2022-08-18 | 2022-12-30 |  |  | CHARLES COMBS | 2022-08-16 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2610 | 0 | 0 | 0 | 2610 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979031300 |  | 100284361 |  | 6764176N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CEDAR GROVE | 265 W CEDAR GROVE RD | 065 | IRV | 2022-08-16 | U126602 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | DEREK PAYTON | 2022-08-16 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10 | 1 | 2674.07 | 774.45 | 0 | 46.55 | 1853.07 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979031600 |  | 100286454 |  | 6768172B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DANIELS ADDITI | 409 DANIELS ADDITI | 065 | RAV | 2022-08-18 | U126602 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | DEREK PAYTON | 2022-08-16 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 3006.93 | 0 | 0 | 0 | 3006.93 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979053500 |  | 500513579 |  | 7348248L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MIDLAND TRAIL | 11901 MIDLAND TRAIL RD | 019 | CAN | 2022-08-16 | U135195 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | KEITH HEDGES | 2022-08-16 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22994325600 |  | 100353334 |  | 7256280K | 2180424 |  |  | 565 | EX | REPLACE SL W/21-0261272-00 | 2600B | 3RD | 466 W 3RD ST | 161 | MAY | 2022-08-24 | U126286 | U134723 | 2022-04-19 | 2022-12-30 |  |  | TYLER ALLISON | 2022-08-16 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 3062.92 | 0 | 0 | 0 | 3062.92 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22999241300 |  | 100240016 |  | 7352264E |  |  |  | 565 | EX | SERVICE LINE - RELO SL/MTR | 2621P | FERRY | 404 FERRY ST | 089 | RUS | 2022-08-19 | U125208 | U125208 | 2022-05-06 | 2022-05-16 | 2022-05-18 |  | MCOLLET | 2022-08-16 | 2022-05-16 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 51.2167 | 8 | 5771.33 | 2406.06 | 884.8 | 2437.57 | 42.9 | 0 | 0 | 0
KY | KY - EAST | 2633 | 05603964700 |  | 100424079 | 31 | 7324132F | 2290467 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SR550 | SR550 | 119 | HIN | 2022-08-29 | U125566 | BFMULLI | 2005-03-09 | 2022-08-17 | 2022-12-31 |  | DESKAGG | 2022-08-17 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.68333 | 1 | 42.25 | 31.64 | 0 | 10.61 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 11877548900 |  | 100240952 |  | 7324132F | 2290467 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SR550 | SR550 | 119 | HIN | 2022-08-18 | U125566 | U906609 | 2011-01-06 | 2022-07-01 | 2022-12-31 |  | DESKAGG | 2022-08-17 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.48333 | 1 | 30.44 | 22.78 | 0 | 7.66 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11881744900 |  | 100242215 | 12 | 7356252D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CENTER | 1016 CENTER ST | 019 | CAT | 2022-08-23 | U938516 | DHORN | 2011-01-28 | 2022-07-01 | 2022-12-31 |  | C HUNGATE | 2022-08-17 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - EAST | 2631 | 16456087200 |  | 100242155 |  | 7356252D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 10TH | 325 10TH ST | 019 | CAT | 2022-11-14 | U125881 | U125208 | 2016-11-15 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-08-17 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883050400 |  | 100242383 |  | 7356252H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CENTER | 1418 CENTER ST | 019 | CAT | 2022-08-23 | U938516 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | C HUNGATE | 2022-08-17 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883055200 |  | 100245543 |  | 7360252I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 26TH | 116 26TH ST | 019 | CAT | 2022-08-23 | U938516 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | C HUNGATE | 2022-08-17 |  |  | D | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883065600 |  | 100284997 |  | 6764176G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WINCHESTER | 1197 WINCHESTER RD | 065 | IRV | 2022-08-18 | U126602 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DEREK PAYTON | 2022-08-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 3093.37 | 0 | 0 | 0 | 3093.37 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883119200 |  | 100265877 |  | 7348256P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | ROBERTS | 5601 ROBERTS DR | 019 | ASH | 2022-08-17 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-08-17 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 2992.4 | 0 | 0 | 0 | 2992.4 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883176000 |  | 100242157 |  | 7356260M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 10TH | 502 10TH ST | 019 | CAT | 2022-11-14 | U125881 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-08-17 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1775.09 | 0 | 0 | 0 | 1775.09 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883204000 |  | 500818686 |  | 7348248G | 0252965 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WOLOHAN | 1550< WOLOHAN DR | 019 | CAN | 2022-08-17 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-08-17 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1836.7 | 0 | 0 | 0 | 1836.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883227200 |  | 100242076 |  | 7356252D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | GREENUP | 972 GREENUP ST | 019 | CAT | 2022-08-17 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-08-17 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 3851.57 | 0 | 2014.87 | 0 | 1836.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883287200 |  | 100242136 |  | 7356252D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 10TH | 322 10TH ST | 019 | CAT | 2022-11-14 | U125881 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-08-17 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883297200 |  | 100250192 |  | 7356248D | 2180320 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | FLEMING | 8417 FLEMING CT | 019 | CAT | 2022-08-17 | U135195 | U120245 | 2021-01-30 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-17 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 |  | 1 | 1836.7 | 0 | 0 | 0 | 1836.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916439500 |  | 100264039 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2502 MAIN ST W | 019 | ASH | 2022-08-17 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-08-17 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3084.67 | 0 | 0 | 0 | 3084.67 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916439800 |  | 100263545 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2509 MAIN ST W | 019 | ASH | 2022-08-17 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-08-17 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1664.08 | 0 | 0 | 0 | 1664.08 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916439900 |  | 100264041 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2516 MAIN ST W | 019 | ASH | 2022-08-17 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-08-17 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1886.73 | 0 | 0 | 0 | 1886.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958605800 |  | 100331694 |  | 6720212N | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | MENTELLE | 10 MENTELLE PR | 067 | LEX | 2022-08-18 | U129722 | U134723 | 2021-12-08 | 2022-12-30 |  |  | M YOUNG | 2022-08-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3133.04 | 0 | 0 | 0 | 3133.04 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959960000 |  | 100447355 |  | 6736232L | 2075121 |  |  | 565 | EX | REPLACE SL W/20-0269806-00 | 2600B | STEWART | 1004 STEWART ST | 017 | PAR | 2022-08-25 | U123111 | U134723 | 2021-12-16 | 2022-09-30 |  |  | LYN STAFFORD | 2022-08-17 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2859.55 | 0 | 0 | 0 | 2859.55 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22026193400 |  |  |  | 7356156P | 2289174 | U122858 |  | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2621M | US23 BLAIRTOWN 1420 | US23 BLAIRTOWN 1420 | 195 | BLA | 2022-08-18 | U125936 | U136124 | 2022-05-31 | 2022-12-30 | 2022-12-31 | 2022-07-27 | M.RYAN | 2022-08-17 | 2022-07-27 |  | F | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00909 | 3200909 |  |  | WP1934 |  |  | 100 | 090932220261934 | 5.3 | 0 | 1938.82 | 394.21 | 0 | 88.28 | 1456 | 0 | 0.33 | 0
KY | KY - EAST | 2633 | 22026193500 |  |  |  | 7356156P | 2289174 | U122858 |  | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2621M | US23 BLAIRTOWN 1420 | US23 BLAIRTOWN 1420 | 195 | BLA | 2022-08-18 | U125936 | U136124 | 2022-05-31 | 2022-12-30 | 2022-12-31 | 2022-07-27 | M.RYAN | 2022-08-17 | 2022-07-27 |  | F | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00910 | 3200910 |  |  | WP1935 |  |  | 100 | 091032220261935 | 0.21667 | 0 | 22.08 | 16.97 | 0 | 5.11 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110056000 |  | 500640843 |  | 7356216D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN CROSS | 114< N MAIN CROSS ST | 127 | LOU | 2022-08-17 | JCYRUS | U125208 | 2022-06-15 | 2022-06-09 | 2022-08-09 |  | JCYRUS | 2022-08-17 | 2022-08-15 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.2667 | 3 | 47.99 | 45.28 | 0 | 2.71 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22114794700 |  | 100265134 |  | 7352260O |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTREQD | 2621P | BELLEFONTE | 331 BELLEFONTE RD | 019 | ASH | 2022-08-17 | JCYRUS | U125208 | 2022-07-08 | 2022-07-13 | 2022-08-10 |  | JCYRUS | 2022-08-17 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 18.8833 | 4 | 2164.46 | 727.3 | 239.52 | 1197.64 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22115401900 |  | 100285817 |  | 6764172D |  |  |  | 566 | EX | ABANDON SL | 2600B | STEVENS | 133 STEVENS AV | 065 | IRV | 2022-08-17 | U126602 | U125201 | 2022-07-12 | 2022-12-20 | 2022-12-20 |  | DEREK PAYTON | 2022-08-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10 | 1 | 5087.89 | 774.45 | 0 | 46.55 | 4266.89 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22121094700 |  | 100278667 |  | 6688232O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303142 | 2621P | MENOMINEE | 432 MENOMINEE TL | 073 | FRA | 2022-08-17 | BWHITE | U125208 | 2022-08-03 | 2022-08-05 | 2022-08-23 |  | BWHITE | 2022-08-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.5833 | 1 | 2221.4 | 534.05 | 0 | 32.09 | 1655.26 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22121773400 |  | 100415286 |  | 6688232O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311974 | 2621P | STEADMANTOWN | 1515 STEADMANTOWN LN 1 | 073 | FRA | 2022-08-19 | UIPBOT05 | U125208 | 2022-08-05 | 2022-08-05 | 2022-08-25 |  | BWHITE | 2022-08-17 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.25 | 1 | 2886.75 | 368.75 | 122.69 | 22.15 | 2373.16 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22122146600 |  | 100240932 |  | 7324132C | 2290467 |  |  | 566 | EX | ABANDON SL - HINDMAN FLOOD | 2600B | HIGHWAY 550 E | 2102 HIGHWAY 550 E | 119 | LEB | 2022-08-23 | U125566 | U125208 | 2022-08-08 | 2022-08-08 |  |  | DESKAGG | 2022-08-17 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.28333 | 1 | 18.01 | 13.47 | 0 | 4.54 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22122674000 |  | 100240933 |  | 7324132C | 2290467 |  |  | 566 | EX | ABANDON SL - HINDMAN FLOOD | 2600B | KY RT 550 | KY RT 550 | 119 | LEB | 2022-08-17 | DESKAGG | U125208 | 2022-08-09 | 2022-08-08 |  |  | DESKAGG | 2022-08-17 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.15 | 1 | 9.3 | 6.96 | 0 | 2.34 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22123146900 |  | 500681509 |  | 6712228B |  |  |  | 566 | EX | ABANDON SL - DEMO/LNBRK | 2621P | BROADWAY | 175 N BROADWAY ST 2 | 209 | GEO | 2022-08-17 | CHERNDO | U125208 | 2022-08-11 | 2022-08-16 | 2022-09-01 |  | CHERNDO | 2022-08-17 | 2022-08-17 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 11.7 | 2 | 740.12 | 698.15 | 0 | 41.97 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22123631900 |  | 100340729 |  | 6736180C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D246261 | 2621P | PLEASURE | 237 PLEASURE DR | 151 | RIC | 2022-08-22 | U125208 | U125208 | 2022-08-12 | 2022-08-12 | 2022-09-01 |  | DENNING | 2022-08-17 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 14.9333 | 2 | 1545.56 | 1106.92 | 263.48 | 114.66 | 60.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22124663900 |  | 500022594 |  | 6764176G |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | WINCHESTER | 1432 WINCHESTER RD | 065 | IRV | 2022-08-24 | U126285 | U125763 | 2022-08-17 | 2022-12-30 |  |  | DDAVIS | 2022-08-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10 | 1 | 3765.72 | 656.64 | 0 | 39.47 | 3069.61 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22125012700 |  | 500719369 |  | 6744208N |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | LINDSEY | 216 LINDSEY CT | 049 | WIN | 2022-08-30 | U938684 | U125763 | 2022-08-18 | 2022-12-30 |  |  | CHARLES COMBS | 2022-08-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2610 | 0 | 0 | 0 | 2610 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22125012800 |  | 500179610 |  | 6744208N |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | SKYLARK | 30 SKYLARK DR | 049 | WIN | 2022-08-30 | U938684 | U125763 | 2022-08-18 | 2022-12-30 |  |  | CHARLES COMBS | 2022-08-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2610 | 0 | 0 | 0 | 2610 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22125012900 |  | 500619105 |  | 6744204E | 9828814 |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | WOODDUCK | 209 WOODDUCK CT | 049 | WIN | 2022-08-30 | U938684 | U125763 | 2022-08-18 | 2022-12-30 |  |  | CHARLES COMBS | 2022-08-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2610 | 0 | 0 | 0 | 2610 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22125013000 |  | 500018151 |  | 6748204C |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | AUBREY | 204 AUBREY LN | 049 | WIN | 2022-08-30 | U938684 | U125763 | 2022-08-18 | 2022-12-30 |  |  | CHARLES COMBS | 2022-08-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2610 | 0 | 0 | 0 | 2610 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22126008400 |  | 500028189 |  | 6744204I |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | HEATHER | 110 HEATHER LN | 049 | WIN | 2022-09-27 | U125559 | U125763 | 2022-08-23 | 2022-12-30 |  |  | CHARLES COMBS | 2022-08-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2610 | 0 | 0 | 0 | 2610 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22970119900 |  | 100280375 |  | 6684228N | 2181158 |  |  | 565 | EX | REPLACE SL W/21-0261319-00 | 2600B | LYONS | 136 LYONS DR | 073 | FRA | 2022-08-18 | U128410 | U134723 | 2022-01-27 | 2022-12-30 |  |  | CDESPAIN | 2022-08-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3145.22 | 0 | 0 | 0 | 3145.22 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22979057200 |  | 501223333 |  | 7324132I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HIGHWAY 160 | 195 HIGHWAY 160 S | 119 | HIN | 2022-08-18 | U125566 | U128070 | 2022-02-17 | 2022-08-17 | 2022-12-31 |  | DESKAGG | 2022-08-17 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.5333 | 1 | 94.38 | 70.65 | 0 | 23.73 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 05611113400 |  | 100240787 | 12 | 7324132F | 2290467 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SR550 | SR550 | 119 | HIN | 2022-08-23 | U125566 | BFMULLI | 2005-05-17 | 2022-07-01 | 2022-12-31 |  | DESKAGG | 2022-08-18 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.35 | 1 | 21.74 | 16.27 | 0 | 5.47 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18026762800 |  |  |  | 7348252O | 1851676 | U461383 |  | 585 | EX | INSTALL NEW CHAIN LINK FENCE | 2600E | US ROUTE 60 | US ROUTE 60 | 019 | CAN | 2022-09-29 | U125936 | U461383 | 2018-03-22 | 2021-11-30 | 2021-12-01 | 2022-08-18 | AMCCORMICK | 2022-08-18 | 2022-08-15 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00585 | 3200585 |  |  | WP7628 |  |  | 100 | 058532180267628 | 8.7333 | 2 | 16843.44 | 348.28 | 0 | 173.18 | 13754.25 | 0 | 11.08 | 2556.65
KY | KY - EAST | 2631 | 18026762900 |  |  |  | 7348252-O | 1851676 | U461383 |  | 586 | EX | REPLACE CHAIN LINK FENCE | 2600E | US ROUTE 60 | US ROUTE 60 | 019 | CAN | 2022-09-29 | U125936 | U461383 | 2018-03-22 | 2020-12-01 | 2020-12-01 | 2022-08-18 | AMCCORMICK | 2022-08-18 | 2022-08-18 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00586 | 3200586 |  |  | WP7629 |  |  | 100 | 058632180267629 | 8 | 0 | 429.99 | 300.3 | 0 | 129.69 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 20849640000 |  | 100329076 |  | 720208P | 1635077 |  |  | 565 | EX | GRADE 1 REPLACE SERVICE | 2621D | LOCKHURST | 2776 LOCKHURST RD | 067 | LEX | 2022-08-18 | HMCKUNE | AOC SYST | 2020-10-01 | 2022-08-17 | 2022-08-17 |  | HMCKUNE | 2022-08-18 | 2022-08-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.0833 | 4 | 1614.67 | 1242.62 | 235.77 | 74.68 | 61.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21883050800 |  | 100354261 |  | 7256280K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | 4TH | 135 W 4TH ST B | 161 | MAY | 2022-08-22 | U930915 | U120245 | 2021-01-30 | 2022-08-18 |  |  | SDADAMS | 2022-08-18 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 0.58333 | 1 | 429.55 | 39.3 | 0 | 2.36 | 387.89 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883107300 |  | 100242169 |  | 7356252D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 10TH | 528 10TH ST | 019 | CAT | 2022-08-18 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-08-18 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883136100 |  | 500064093 |  | 7356252P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 28TH | 413 28TH ST | 019 | CAT | 2022-11-14 | U125881 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-08-18 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883163700 |  | 100242170 |  | 7356252D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 10TH | 526 10TH ST | 019 | CAT | 2022-08-18 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-08-18 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883249500 |  | 100245854 |  | 7360252M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 28TH | 642 28TH ST | 019 | CAT | 2022-11-14 | U125881 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-08-18 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883270000 |  | 100245814 |  | 7360252M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LOUISA | 2706 LOUISA ST | 019 | CAT | 2022-08-18 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-08-18 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1659.31 | 0 | 0 | 0 | 1659.31 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883306000 |  | 100439601 |  | 7324132F | 2290467 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SR550 | SR550 | 119 | HIN | 2022-08-23 | U125566 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DESKAGG | 2022-08-18 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.5 | 1 | 31.07 | 23.26 | 0 | 7.81 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916440100 |  | 100264042 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2518 MAIN ST W | 019 | ASH | 2022-08-18 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-08-18 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2061.73 | 0 | 0 | 0 | 2061.73 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916440400 |  | 100263542 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2525 MAIN ST W | 019 | ASH | 2022-08-18 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-08-18 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2141.2 | 0 | 0 | 0 | 2141.2 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21928151700 |  | 100264044 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400 D244419 | 2600B | MAIN | 2520 MAIN ST W | 019 | ASH | 2022-08-18 | U124015 | U131066 | 2021-07-26 | 2022-11-01 | 2023-08-31 |  | ORA SLONE | 2022-08-18 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2503.34 | 13.44 | 0 | 5.07 | 2484.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958606100 |  | 100331695 |  | 6720212N | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | MENTELLE | 12 MENTELLE PR | 067 | LEX | 2022-08-23 | U129722 | U134723 | 2021-12-08 | 2022-12-30 |  |  | M YOUNG | 2022-08-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3007.09 | 0 | 0 | 0 | 3007.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958606300 |  | 100331696 |  | 6720212M | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | MENTELLE | 16 MENTELLE PR | 067 | LEX | 2022-08-23 | U129722 | U134723 | 2021-12-08 | 2022-12-30 |  |  | M YOUNG | 2022-08-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2336.29 | 0 | 0 | 0 | 2336.29 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959032900 |  | 100315234 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | CONN TER | 212 CONN TER | 067 | LEX | 2022-08-18 | U128336 | U134723 | 2021-12-10 | 2022-12-30 |  |  | JOSHUA COX | 2022-08-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.0167 | 1 | 1249.43 | 155.02 | 0 | 9.31 | 1085.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960889400 |  | 100409600 |  | 7360248A | 2180320 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | LOUISA | 3822 LOUISA RD | 019 | CAT | 2022-08-28 | U938516 | U134723 | 2021-12-21 | 2023-06-30 |  |  | C HUNGATE | 2022-08-18 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 |  | 1 | 1836.7 | 0 | 0 | 0 | 1836.7 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026207500 |  |  |  | 6712228B | 2289681 | U461383 |  | 583 | EX | INSTALL NEW CONTROL REGULATOR | 2623M | RUCKER | 177 RUCKER AV | 209 | GEO | 2022-12-20 | U125936 | U461383 | 2022-06-23 | 2023-09-01 | 2023-09-01 | 2022-08-18 | CWEMPE | 2022-08-18 | 2022-08-18 |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00583 | 3200583 |  |  | WP2075 |  |  | 100 | 058332220262075 | 10.0833 | 3 | 893.82 | 728.32 | 0 | 42.28 | 0 | 0 | 0.15 | 123.07
KY | KY - WEST | 2623 | 22026207600 |  |  |  | 6712228B | 2289681 | U461383 |  | 584 | EX | REPLACE CONTROL REG | 2623M | RUCKER | 177 RUCKER AV | 209 | GEO | 2022-12-20 | U125936 | U461383 | 2022-06-23 | 2023-09-01 | 2023-09-01 | 2022-08-18 | CWEMPE | 2022-08-18 | 2022-08-18 |  | F | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00584 | 3200584 |  |  | WP2076 |  |  | 100 | 058432220262076 | 6.0667 | 0 | 487.94 | 461.68 | 0 | 26.26 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026217800 |  |  |  | 6716208E | 2290789 | U461383 |  | 557 | EX | EMER-INSTALL 3' OF 4"PMLP MAIN | 2621P | ROSEMILL | 591 ROSEMILL DR | 067 | LEX | 2022-11-08 | U130872 | U461383 | 2022-08-12 | 2023-10-31 | 2024-06-29 | 2022-08-17 | R CRAWFORD | 2022-08-18 | 2022-08-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2178 | AMRCB |  | 100 | 055732220262178 | 54.3167 | 110 | 12300.82 | 4908.31 | 1034.64 | 300.96 | 4447.36 | 0 | 0.5 | 1609.05 | 10
KY | KY - WEST | 2621 | 22026217900 |  |  |  | 6716208E | 2290789 | U461383 |  | 558 | EX | EMER-RETIRE 3' OF 4"BSLP MAIN | 2621P | ROSEMILL | 591 ROSEMILL DR | 067 | LEX | 2022-11-08 | U130872 | U461383 | 2022-08-12 | 2023-10-31 | 2024-06-29 | 2022-08-17 | R CRAWFORD | 2022-08-18 | 2022-08-16 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2179 | AMRCB |  | 100 | 055832220262179 | 10.5 | 0 | 4448.33 | 2934.78 | 0 | 182.35 | 1331.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22104162000 |  | 100354262 |  | 7256280K |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2600B | 4TH | 135 W 4TH ST | 161 | MAY | 2022-08-19 | U930915 | U134723 | 2022-05-31 | 2022-08-18 |  |  | SDADAMS | 2022-08-18 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 0.68333 | 1 | 48.68 | 45.93 | 0 | 2.75 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22112512800 |  | 100240834 |  | 7324132I |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2621P | MAIN | 18 W MAIN ST | 119 | HIN | 2022-08-18 | DESKAGG | U134723 | 2022-06-27 | 2022-07-01 | 2022-12-31 |  | DESKAGG | 2022-08-18 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.25 | 1 | 15.52 | 11.61 | 0 | 3.91 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22117007900 |  | 100304927 |  | 6712212P | 1855043 |  |  | 566 | EX | ABANDON SL - SOII/INSIDE | 2621P | DELLA | 1019 DELLA DR | 067 | LEX | 2022-08-19 | U125208 | U130868 | 2022-07-19 | 2022-07-19 | 2022-11-22 |  | TROE | 2022-08-18 | 2022-08-16 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.6333 | 6 | 932.46 | 879.57 | 0 | 52.89 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22123915500 |  | 100415965 |  | 6716204J |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311374 | 2621P | TIVERTON | 256 E TIVERTON WY | 067 | LEX | 2022-08-19 | U125208 | U125208 | 2022-08-15 | 2022-08-18 | 2022-09-05 |  | KKINDER | 2022-08-18 | 2022-08-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 49.5 | 8 | 3045.83 | 2835.82 | 0 | 170.41 | 39.6 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22124660500 |  | 100424735 |  | 7320132L | 2290467 |  |  | 565 | EX | RPLC SL/ | 2600B | COWTOWN | 125 COWTOWN RD | 119 | HIN | 2022-08-18 | MBLANKE | U125763 | 2022-08-17 | 2022-12-30 |  |  | MBLANKE | 2022-08-18 |  |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26330032 | 0.16667 | 1 | 11.96 | 9.22 | 0 | 2.74 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22124928100 |  | 100333558 |  | 6720212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311888 | 2621P | 3RD | 126 E 3RD ST | 067 | LEX | 2022-08-22 | U125208 | U136526 | 2022-08-18 | 2022-12-22 | 2024-06-30 |  | LSTANFI | 2022-08-18 | 2022-08-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 21.7167 | 4 | 5154.99 | 2934.57 | 299.92 | 597.5 | 1323 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22124930100 |  | 100244800 |  | 7356216D |  |  |  | 566 | VO | ABANDN SL/LGCY | 2600B | PIKE | 105 W PIKE ST | 127 | LOU | 2022-08-19 |  | U125763 | 2022-08-18 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-18 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22124947000 |  | 500303965 |  | 6760172L |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | WINN | 187 S WINN AV | 065 | IRV | 2022-08-18 | U127206 | U125763 | 2022-08-18 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-08-18 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10 | 1 | 3681.52 | 774.45 | 0 | 46.55 | 2860.52 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22124953600 |  | 100435997 |  | 7320132L | 2290467 |  |  | 565 | EX | REPLACE SL | 2600B | COWTOWN | 89 COWTOWN RD | 119 | HIN | 2022-08-29 | U123965 | U124396 | 2022-08-18 | 2022-12-22 |  |  | MBLANKE | 2022-08-18 |  |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26330032 | 0.16667 | 1 | 11.96 | 9.22 | 0 | 2.74 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22124957800 |  | 100250056 |  | 7360252M |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | LOUISA | 3250 LOUISA HT | 019 | CAT | 2022-08-28 | U938516 | U125763 | 2022-08-18 | 2022-12-30 |  |  | C HUNGATE | 2022-08-18 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22125013100 |  | 100350610 |  | 6744208M |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | CHICKADEE | 10 CHICKADEE LN | 049 | WIN | 2022-08-31 | U938684 | U125763 | 2022-08-18 | 2022-12-30 |  |  | CHARLES COMBS | 2022-08-18 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2555 | 0 | 0 | 0 | 2555 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22125246500 |  | 100245800 |  | 7360252M |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | LOUISA | 2609 LOUISA ST | 019 | CAT | 2022-08-19 | U135195 | U125763 | 2022-08-19 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-18 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22126067600 |  | 501010127 |  | 6740208D |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | CATHERINE | 238 CATHERINE DR | 049 | WIN | 2022-08-30 | U938684 | U125763 | 2022-08-23 | 2022-12-30 |  |  | CHARLES COMBS | 2022-08-18 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2555 | 0 | 0 | 0 | 2555 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22963707400 |  | 500123182 |  | 6764176G |  |  |  | 566 | EX | ABANDON SL I/I/LGCY | 2600B | WINCHESTER | 1491 WINCHESTER RD | 065 | IRV | 2022-08-18 | U126602 | U134723 | 2022-01-04 | 2022-12-30 |  |  | DEREK PAYTON | 2022-08-18 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10 | 1 | 7375.53 | 774.45 | 0 | 46.55 | 6554.53 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22970120300 |  | 100280348 |  | 6688228J | 2181158 |  |  | 565 | EX | REPLACE SL W/21-0261319-00 | 2600B | LYONS | 144 LYONS DR | 073 | FRA | 2022-08-22 | U128410 | U134723 | 2022-01-27 | 2022-12-30 |  |  | CDESPAIN | 2022-08-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2336.28 | 0 | 0 | 0 | 2336.28 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979018000 |  | 100245914 |  | 7360252I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ANNE | 405 ANNE ST | 019 | CAT | 2022-11-14 | U125881 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | HERBERT HAYDEN | 2022-08-18 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979044900 |  | 100416948 |  | 6736212K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WILLIAMSBURG | 701 WILLIAMSBURG DR | 049 | WIN | 2022-08-31 | U938684 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | CHARLES COMBS | 2022-08-18 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1840 | 0 | 0 | 0 | 1840 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979056600 |  | 501187189 |  | 6744204I | 1639699 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | TEAKWOOD | 118 TEAKWOOD CT | 049 | WIN | 2022-08-31 | U938684 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | CHARLES COMBS | 2022-08-18 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 3313.63 | 0 | 0 | 0 | 3313.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 17495130800 |  | 100331258 | 40 | 6720212N |  |  |  | 565 | EX | RELOC S/L - DECK OVER SL & MTR | 2621P | LINCOLN | 169 LINCOLN AV | 067 | LEX | 2022-08-22 | U125208 | MPILON | 2017-04-05 | 2018-12-26 |  |  | RSTRONG | 2022-08-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.8667 | 1 | 6428.79 | 375.78 | 205.4 | 1013.11 | 4834.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883123300 |  | 100245673 |  | 7360252I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BROADWAY | 2424 BROADWAY ST | 019 | CAT | 2022-08-19 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-08-19 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883132700 |  | 100424088 |  | 7368156T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | PW6882 | PW6882 | 195 | PIK | 2022-08-19 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JOHN HOWARD | 2022-08-19 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - EAST | 2631 | 21883178500 |  | 100242137 |  | 7356252D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 10TH | 324 10TH ST | 019 | CAT | 2022-08-19 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-08-19 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 2231 | 0 | 0 | 0 | 2231 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883222500 |  | 100245645 |  | 7360252I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BROADWAY | 2013 BROADWAY ST | 019 | CAT | 2022-08-19 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-08-19 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883259900 |  | 100242241 |  | 7356252H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 11TH | 416 11TH ST | 019 | CAT | 2022-11-14 | U125881 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-08-19 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1779.17 | 0 | 0 | 0 | 1779.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22123908500 |  | 100322797 |  | 6716208D |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTREQD | 2621P | KASTLE | 1257 KASTLE RD | 067 | LEX | 2022-08-22 | U125208 | U125208 | 2022-08-15 | 2022-08-18 | 2022-09-05 |  | TROE | 2022-08-19 | 2022-08-16 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.9667 | 4 | 617.21 | 582.22 | 0 | 34.99 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22124227100 |  | 100258249 |  | 7348268M |  |  |  | 565 | EX | REPLACE SL - GRADE 1 D244474 | 2621P | 3RD | 349 3RD AV | 089 | WOR | 2022-08-22 | U125208 | U124449 | 2022-08-16 | 2022-08-16 | 2022-08-16 |  | MCOLLET | 2022-08-19 | 2022-08-16 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 41.1167 | 7 | 7488.74 | 1854.04 | 497.22 | 5045.08 | 92.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125266400 |  | 100306806 |  | 6716212I |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311756 | 2621P | TERRACE VIEW | 747 TERRACE VIEW DR | 067 | LEX | 2022-08-22 | U125208 | U125208 | 2022-08-19 | 2022-08-19 | 2024-06-30 |  | RSTRONG | 2022-08-19 | 2022-08-17 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.35 | 2 | 6189.37 | 341.27 | 451.54 | 920.06 | 4476.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125315100 |  | 100421958 |  | 6720204J | 1313369 |  |  | 565 | EX | SERVICE LINE REPLACE | 2621P | STEPHEN FOSTER | 1371 STEPHEN FOSTER DR | 067 | LEX | 2022-08-22 | U930915 | U136526 | 2022-08-19 | 2022-08-19 | 2022-08-19 |  | RJCRAWF | 2022-08-19 | 2022-08-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.4667 | 4 | 1552.91 | 1219.57 | 260.1 | 73.24 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22994326600 |  | 100353337 |  | 7256280K | 2180424 |  |  | 565 | EX | REPLACE SL W/21-0261272-00 | 2600B | 3RD | 474 W 3RD ST | 161 | MAY | 2022-10-13 | U461478 | U134723 | 2022-04-19 | 2022-12-30 |  |  | DAVID STAGGS | 2022-08-19 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2536.37 | 0 | 0 | 0 | 2536.37 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22994327100 |  | 100353343 |  | 7256280K | 2180424 |  |  | 565 | EX | REPLACE SL W/21-0261272-00 | 2600B | 3RD | 490 W 3RD ST | 161 | MAY | 2022-09-16 | U461478 | U134723 | 2022-04-19 | 2022-12-30 |  |  | DAVID STAGGS | 2022-08-19 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2893.74 | 0 | 0 | 0 | 2893.74 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 10869458200 |  | 100433339 |  | 6748180L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | COLLEGE HILL | 401 COLLEGE HILL RD | 151 | WAC | 2022-09-12 | U938684 | U906307 | 2010-11-23 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-08-20 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2370 | 0 | 0 | 0 | 2370 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11926002700 |  | 100337350 |  | 16720212E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | OHIO | 523< OHIO ST | 067 | LEX | 2022-11-22 | U938516 | U125208 | 2011-09-22 | 2022-07-01 | 2022-12-31 |  | CHRIS HUNGATE | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 13121089500 |  | 100445119 |  | 6712212L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OXFORD | 1812 OXFORD CR L | 067 | LEX | 2022-08-24 | U125208 | U124967 | 2013-03-01 | 2024-03-01 | 2024-03-01 |  | LSTONE | 2022-08-22 | 2022-08-16 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.0667 | 5 | 499.59 | 471.27 | 0 | 28.32 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19026860400 |  |  |  | 7356248P | 1853795 | U131982 |  | 909 | EX | INSTALLING I&C EQUIPMENT | 2630M | US 23 | US 23 | 019 | CAT | 2022-12-29 | U123258 | U131982 | 2019-02-07 | 2023-12-12 | 2023-12-31 | 2021-06-22 | DASH | 2022-08-22 | 2021-06-09 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP8604 |  |  | 100 | 090932190268604 | 202.6167 | 0 | 174669.84 | 13526.39 | 39605.84 | 4784.12 | 108291.95 | 0 | 8461.54 | 0
KY | KY - EAST | 2631 | 19026860500 |  |  |  | 7356248P | 1853795 | U131982 |  | 910 | EX | RETIRE I&C EQUIPMENT | 2630M | US 23 | US 23 | 019 | CAT | 2022-12-27 | U123258 | U131982 | 2019-02-07 | 2023-12-29 | 2023-12-31 | 2021-06-22 | DASH | 2022-08-22 | 2022-08-22 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00910 | 3200910 |  |  | WP8605 |  |  | 100 | 091032190268605 | 8.7667 | 0 | 511.34 | 482.35 | 0 | 28.99 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 20026960600 |  |  |  | 6688228D | 2073253 | U461383 |  | 909 | EX | INSTALL NEW TRANSMITTERS | 2623M | US 460 - GEORGETOWN RD | US 460 - GEORGETOWN RD | 073 | FRA | 2022-09-19 | U125936 | U461383 | 2020-07-16 | 2023-09-29 | 2023-10-01 | 2022-08-22 | GHALE | 2022-08-22 | 2022-08-22 |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00909 | 3200909 |  |  | WP9606 |  |  | 100 | 090932200269606 | 21.35 | 0 | 9652.42 | 1309.59 | 0 | 448.76 | 7558 | 0 | 336.07 | 0
KY | KY - WEST | 2623 | 20026960700 |  |  |  | 6688228D | 2073253 | U461383 |  | 910 | EX | RETIRE DAMAGE TRANSMITTER | 2623M | US 460 - GEORGETOWN RD | US 460 - GEORGETOWN RD | 073 | FRA | 2022-09-19 | U125936 | U461383 | 2020-07-16 | 2022-09-30 | 2022-10-01 | 2022-08-22 | GHALE | 2022-08-22 | 2022-08-22 |  | F | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00910 | 3200910 |  |  | WP9607 |  |  | 100 | 091032200269607 | 7.2667 | 0 | 542.77 | 475.16 | 0 | 67.61 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 20772128200 |  | 100338433 | 39 | 6720212F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 7TH | 227 E 7TH ST | 067 | LEX | 2022-08-25 | U930915 | JFAWNS | 2020-01-18 | 2022-08-22 |  |  | RSTRONG | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.6167 | 1 | 1829.62 | 102.26 | 33.24 | 275.66 | 1418.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 20849649400 |  | 100329048 |  | 6720208O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMED - D303149 | 2621D | FOLKSTONE | 621 FOLKSTONE DR | 067 | LEX | 2022-08-22 | U930915 | AOC SYST | 2020-10-01 | 2022-08-15 | 2022-09-02 |  | RJCRAWF | 2022-08-22 | 2022-08-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 32.1167 | 7 | 2315.03 | 1935.74 | 210.12 | 116.37 | 52.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21026112400 |  |  |  | 6724212O | 2177781 | U461383 |  | 587 | EX | INSTALL NEW GMB SETTING | 2600M | POLO CLUB | 2000 POLO CLUB BV | 067 | LEX | 2022-11-11 | U126425 | U461383 | 2021-03-24 | 2022-12-27 | 2022-12-31 | 2022-08-22 | AJPARKS | 2022-08-22 | 2022-02-17 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00587 | 3200587 |  |  | WP1124 |  |  | 100 | 058732210261124 | 72.3167 | 228 | 55082.19 | 4490.55 | 27890.67 | 787.8 | 9624.32 | 0 | 2111.3 | 10177.55
KY | KY - EAST | 2631 | 21026155700 |  |  |  | 7356248P | 1853795 | U132280 |  | 577 | EX | INSTALL FENCE - SCADA BUILDING | 2631M | US 23 | US 23 | 019 | CAT | 2022-12-22 | U123258 | U132280 | 2021-12-13 | 2023-12-01 | 2023-12-01 | 2022-08-22 | DASH | 2022-08-22 |  |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00577 | 3200577 |  |  | WP1557 |  |  | 100 | 057732210261557 |  | 1 | 7557.57 | 0 | 0 | 0 | 6270 | 0 | 45.72 | 1241.85
KY | KY - WEST | 2621 | 21883064900 |  | 100465849 |  | 6716212P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WOODLAND | 353 WOODLAND AV B | 067 | LEX | 2022-08-23 | U125881 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 390.22 | 0 | 0 | 0 | 390.22 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883266500 |  | 100351308 |  | 6744208E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEXINGTON | 2500 LEXINGTON RD | 049 | WIN | 2022-09-02 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2295 | 0 | 0 | 0 | 2295 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883273700 |  | 100349520 |  | 6744208P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEXINGTON | 35 E LEXINGTON AV | 049 | WIN | 2022-09-02 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1805 | 0 | 0 | 0 | 1805 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883288600 |  | 500128482 |  | 6744208J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | GARY | 106 GARY CT | 049 | WIN | 2022-09-02 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1805 | 0 | 0 | 0 | 1805 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958604700 |  | 100443849 |  | 6720212M | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | MENTELLE | 1 MENTELLE PR C | 067 | LEX | 2022-08-22 | U126308 | U134723 | 2021-12-08 | 2022-12-30 |  |  | J ENSMINGER | 2022-08-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2045.74 | 0 | 0 | 0 | 2045.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958604800 |  | 100445093 |  | 6720212M | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | MENTELLE | 1 MENTELLE PR D | 067 | LEX | 2022-08-22 | U126308 | U134723 | 2021-12-08 | 2022-12-30 |  |  | J ENSMINGER | 2022-08-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 307.84 | 0 | 0 | 0 | 307.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958604900 |  | 100452003 |  | 6720212M | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | MENTELLE | 1 MENTELLE PR E | 067 | LEX | 2022-08-31 | U126308 | U134723 | 2021-12-08 | 2022-12-30 |  |  | J ENSMINGER | 2022-08-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2150.07 | 0 | 0 | 0 | 2150.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958605000 |  | 100447130 |  | 6720212M | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | MENTELLE | 1 MENTELLE PR F | 067 | LEX | 2022-08-22 | U126308 | U134723 | 2021-12-08 | 2022-12-30 |  |  | J ENSMINGER | 2022-08-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 710.5 | 0 | 0 | 0 | 710.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958605100 |  | 100442420 |  | 6720212M | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | MENTELLE | 1 MENTELLE PR G | 067 | LEX | 2022-08-22 | U126308 | U134723 | 2021-12-08 | 2022-12-30 |  |  | J ENSMINGER | 2022-08-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2174.31 | 0 | 0 | 0 | 2174.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960255500 |  | 100321610 |  | 6716212P | 2176779 |  |  | 566 | EX | ABANDON SL W/CAPTIOL JOB | 2600B | ROSE | 368 ROSE ST | 067 | LEX | 2022-08-22 | U135195 | U134723 | 2021-12-17 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026195400 |  |  |  | 6696212C | 2289217 | U122858 |  | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2621M | US60 | US60 | 239 | VER | 2022-11-17 | U123258 | U136124 | 2022-06-02 | 2023-12-29 | 2023-12-31 | 2022-08-22 | BLONE | 2022-08-22 | 2022-08-22 |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00909 | 3200909 |  |  | WP1954 |  |  | 100 | 090932220261954 | 9.65 | 0 | 682.09 | 643.4 | 0 | 38.55 | 0 | 0 | 0.14 | 0
KY | KY - WEST | 2623 | 22026195500 |  |  |  | 6696212C | 2289217 | U122858 |  | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2621M | US60 | US60 | 239 | VER | 2022-11-17 | U123258 | U136124 | 2022-06-02 | 2023-12-29 | 2023-12-31 | 2022-08-22 | BLONE | 2022-08-22 | 2022-08-22 |  | F | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00910 | 3200910 |  |  | WP1955 |  |  | 100 | 091032220261955 | 9.5833 | 0 | 676.72 | 638.36 | 0 | 38.36 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026215700 |  |  |  | 6712228B | 2290492 | U461383 |  | 557 | EX | EMER-INSTALL 2' OF 2"PMMP MAIN | 2621P | MAIN | W MAIN ST | 209 | GEO | 2022-10-04 | U128132 | U461383 | 2022-08-01 | 2022-08-17 |  | 2022-07-11 | KKINDER | 2022-08-22 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP2157 |  |  | 100 | 055732220262157 | 0.066667 | 2 | 4910.67 | 3844.71 | 43.52 | 217.47 | 0 | 0 | 0 | 804.97 | 2
KY | KY - WEST | 2623 | 22026215800 |  |  |  | 6712228B | 2290492 | U461383 |  | 558 | EX | EMER-RETIRE 2' OF 2"PMP MAIN | 2621P | MAIN | W MAIN ST | 209 | GEO | 2022-08-26 | U128132 | U461383 | 2022-08-01 | 2022-08-19 |  | 2022-07-11 | KKINDER | 2022-08-22 | 2022-08-19 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP2158 |  |  | 100 | 055832220262158 | 2.9167 | 0 | 224.99 | 212.2 | 0 | 12.79 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026215900 |  |  |  | 6712204C | 2290527 | U461383 |  | 559 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | 2621P | BIRKENHEAD | BIRKENHEAD DR | 067 | LEX | 2022-09-28 | U128132 | U461383 | 2022-08-02 | 2022-08-22 |  | 2022-07-13 | KKINDER | 2022-08-22 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP2159 |  |  | 100 | 055932220262159 | 0.63333 | 3 | 1854.5 | 48 | 0 | 2.88 | 1499.62 | 0 | 0 | 304 | 3
KY | KY - WEST | 2621 | 22026216000 |  |  |  | 6712204C | 2290527 | U461383 |  | 560 | EX | EMER-RETIRE 3' OF 2"PAMP MAIN | 2621P | BIRKENHEAD | BIRKENHEAD DR | 067 | LEX | 2022-09-28 | U128132 | U461383 | 2022-08-02 | 2022-08-19 | 2022-11-01 | 2022-07-13 | KKINDER | 2022-08-22 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00560 | 3200560 |  |  | WP2160 |  |  | 100 | 056032220262160 | 1.8667 | 0 | 143.19 | 135.09 | 0 | 8.1 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22105844200 |  | 500224929 |  | 6712208L | 1635077 |  |  | 565 | EX | AOC REPLACE - ENCROACHMENT | 2621D | TULIP | 3001 TULIP TC | 067 | LEX | 2022-08-22 | MCRAIG | AOC SYST | 2022-06-02 | 2022-07-01 | 2022-08-01 |  | MCRAIG | 2022-08-22 | 2022-07-12 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 27.7 | 6 | 4769.94 | 1499.02 | 187.15 | 2986.97 | 96.8 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22121060900 |  | 100262313 |  | 7352256G |  |  |  | 565 | EX | SERVICE LINE -REPLACE/RELOCATE | 2621P | IROQUOIS | 2672 IROQUOIS AV | 019 | ASH | 2022-08-24 | U125208 | U125208 | 2022-08-03 | 2022-08-05 | 2022-08-24 |  | MCOLLET | 2022-08-22 | 2022-08-22 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 30.5667 | 4 | 5127.55 | 1397.77 | 293.41 | 3397.87 | 38.5 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22122670500 |  | 100240972 |  | 7324132E | 2290467 |  |  | 566 | EX | ABANDON SL - HINDMAN FLOOD | 2600B | MAIN | 534 E MAIN ST | 119 | HIN | 2022-08-22 | U125566 | U125208 | 2022-08-09 | 2022-08-08 |  |  | DAVID SKAGGS | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 0
KY | KY - EAST | 2633 | 22122673200 |  | 100240938 |  | 7324132H | 2290467 |  |  | 566 | EX | ABANDON SL - HINDMAN FLOOD | 2600B | HIGHWAY 550 E | 2028 HIGHWAY 550 E 4 | 119 | LEB | 2022-08-22 | U125566 | U125208 | 2022-08-09 | 2022-08-08 |  |  | DAVID SKAGGS | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 0
KY | KY - EAST | 2633 | 22122673400 |  | 100240940 |  | 7324132H | 2290467 |  |  | 566 | EX | ABANDON SL - HINDMAN FLOOD | 2600B | HIGHWAY 550 E | 2028 HIGHWAY 550 E 3 | 119 | LEB | 2022-08-22 | U125566 | U125208 | 2022-08-09 | 2022-08-08 |  |  | DAVID SKAGGS | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 0
KY | KY - EAST | 2633 | 22122673500 |  | 100240941 |  | 7324132H | 2290467 |  |  | 566 | EX | ABANDON SL - HINDMAN FLOOD | 2600B | HIGHWAY 550 E | 2028 HIGHWAY 550 E 2 | 119 | LEB | 2022-08-22 | U125566 | U125208 | 2022-08-09 | 2022-08-08 |  |  | DAVID SKAGGS | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 0
KY | KY - EAST | 2633 | 22122673600 |  | 100240943 |  | 7324132H | 2290467 |  |  | 566 | EX | ABANDON SL - HINDMAN FLOOD | 2600B | HIGHWAY 550 E | 2028 HIGHWAY 550 E 1 | 119 | LEB | 2022-08-29 | U125566 | U125208 | 2022-08-09 | 2022-08-08 |  |  | DAVID SKAGGS | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - CENTRAL | 2629 | 22124943700 |  | 100342071 |  | 7240216N |  |  |  | 565 | EX | SERVICE LINE - REPLACE 8/22/22 | 2621P | JOHNSON | 19 JOHNSON AV | 173 | MT | 2022-08-23 | U125208 | U125208 | 2022-08-18 | 2022-08-22 | 2022-08-22 |  | DENNING | 2022-08-22 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26290031 | 16 | 2 | 1444.67 | 1188.59 | 140.65 | 71.43 | 44 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22125301100 |  | 100354264 |  | 7256280K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | 4TH | 133 W 4TH ST B | 161 | MAY | 2022-08-22 | SDADAMS | U125208 | 2022-08-19 | 2022-08-18 |  |  | SDADAMS | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 0.11667 | 1 | 8.46 | 7.98 | 0 | 0.48 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22125324000 |  | 100279430 |  | 6688224D |  |  |  | 565 | EX | SERVICE LINE REPLACE D221460 | 2621P | ALEXANDER | 1055 ALEXANDER RD | 073 | FRA | 2022-08-22 | BWHITE | U136526 | 2022-08-19 | 2022-08-19 | 2022-08-19 |  | BWHITE | 2022-08-22 | 2022-08-19 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.4 | 2 | 1881.43 | 170.98 | 270.77 | 10.28 | 1429.4 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22125348300 |  | 100450010 |  | 7320132L | 1313374 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE + | 2621P | GAYHEART | GAYHEART ST | 119 | HIN | 2022-08-22 | MBLANKE | U132823 | 2022-08-19 | 2022-08-19 |  |  | MBLANKE | 2022-08-22 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.5167 | 1 | 105.77 | 81.62 | 0 | 24.15 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22125348700 |  | 100451468 |  | 7320132L | 1313374 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE + | 2621P | GAYHEART | GAYHEART ST | 119 | HIN | 2022-08-22 | MBLANKE | U132823 | 2022-08-19 | 2022-08-19 |  |  | MBLANKE | 2022-08-22 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26330043 | 0.05 | 1 | 3.54 | 2.72 | 0 | 0.82 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22125569200 |  | 100417668 |  | 6684228I | 1313370 |  |  | 565 | EX | SERVICE LINE - REPLACE D221461 | 2621P | SKYVIEW | 148 SKYVIEW DR | 073 | FRA | 2022-08-22 | BWHITE | U132823 | 2022-08-21 | 2022-08-21 | 2022-08-21 |  | BWHITE | 2022-08-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.75 | 1 | 3671.84 | 475.42 | 182.02 | 28.57 | 2985.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125580900 |  | 100336503 |  | 6720212I |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | OHIO | 353 OHIO ST | 067 | LEX | 2022-11-23 | U938516 | U125763 | 2022-08-22 | 2022-12-30 |  |  | CHRIS HUNGATE | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125581100 |  | 100337345 |  | 6720212E |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | OHIO | 545 OHIO ST | 067 | LEX | 2022-11-23 | U938516 | U125763 | 2022-08-22 | 2022-12-30 |  |  | CHRIS HUNGATE | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1639.55 | 0 | 0 | 0 | 1639.55 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125586300 |  | 100314001 |  | 6716212N |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | BURLEY | 310 BURLEY AV | 067 | LEX | 2022-08-22 | U127206 | U125763 | 2022-08-22 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 2699.7 | 774.45 | 0 | 46.55 | 1878.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125589800 |  | 100295162 |  | 6716212H |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | SMITH | 458 SMITH ST | 067 | LEX | 2022-08-22 | U135195 | U125763 | 2022-08-22 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125590000 |  | 100337337 |  | 6720212E |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | OHIO | 563 OHIO ST | 067 | LEX | 2022-08-22 | U135195 | U125763 | 2022-08-22 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125600200 |  | 100313883 |  | 6716212N |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | SOUTHERN | 1310 SOUTHERN AV | 067 | LEX | 2022-08-22 | U127206 | U125763 | 2022-08-22 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1708.57 | 0 | 0 | 0 | 1708.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125617200 |  | 100313904 |  | 6716208B |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | CAMDEN | 1321 CAMDEN AV | 067 | LEX | 2022-08-22 | U127206 | U125763 | 2022-08-22 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1708.57 | 0 | 0 | 0 | 1708.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125619600 |  | 100296321 |  | 6716216O |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | PRICE | 425 PRICE RD | 067 | LEX | 2022-08-23 | U125881 | U125763 | 2022-08-22 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2180.38 | 0 | 0 | 0 | 2180.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125645900 |  | 100296579 |  | 6716216O |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | ROOSEVELT | 448 N ROOSEVELT BV | 067 | LEX | 2022-08-23 | U125881 | U125763 | 2022-08-22 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125661400 |  | 100313604 |  | 6716208B |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | HUMMINGBIRD | 366 HUMMINGBIRD LN | 067 | LEX | 2022-08-22 | U127206 | U125763 | 2022-08-22 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1793.63 | 0 | 0 | 0 | 1793.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125683600 |  | 500117902 |  | 6720208H |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | CODELL | 371 CODELL DR 4 | 067 | LEX | 2022-08-23 | U135195 | U125763 | 2022-08-22 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1743.62 | 0 | 0 | 0 | 1743.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125962900 |  | 100338579 |  | 6720212F |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | YORK | 184 YORK ST | 067 | LEX | 2022-08-23 | U135195 | U125763 | 2022-08-23 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2044.84 | 0 | 0 | 0 | 2044.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126044400 |  | 100307332 |  | 6716212J |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | PORTER | 836 PORTER PL | 067 | LEX | 2022-08-23 | U125881 | U125763 | 2022-08-23 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22127078700 |  | 100435406 |  | 6736208D |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | LEXINGTON | 5703 LEXINGTON RD | 049 | WIN | 2022-09-02 | U938684 | U125763 | 2022-08-26 | 2022-12-30 |  |  | CHARLES COMBS | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2295 | 0 | 0 | 0 | 2295 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22127078800 |  | 501146384 |  | 6736212O |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | LEXINGTON | 6229 LEXINGTON RD | 049 | WIN | 2022-11-09 | U461383 | U125763 | 2022-08-26 | 2022-12-30 |  |  | CHARLES COMBS | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2295 | 0 | 0 | 0 | 2295 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22127078900 |  | 100351358 |  | 6736212O |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | LEXINGTON | 6402 LEXINGTON RD | 049 | WIN | 2022-09-02 | U938684 | U125763 | 2022-08-26 | 2022-12-30 |  |  | CHARLES COMBS | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2295 | 0 | 0 | 0 | 2295 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22127079000 |  | 100349413 |  | 6748208M |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | BROADWAY | 130 E BROADWAY ST 1 | 049 | WIN | 2022-09-02 | U938684 | U125763 | 2022-08-26 | 2022-12-30 |  |  | CHARLES COMBS | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2295 | 0 | 0 | 0 | 2295 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22140564200 |  | 100463287 |  | 6748208M |  |  |  | 566 | EX | ABN METER/SL ABANDONED | 2621P | BROADWAY | 130 E BROADWAY ST 2 | 049 | WIN | 2022-10-21 | DMCCULL | DMCCULL | 2022-10-21 | 2022-10-28 |  |  | CHARLES COMBS | 2022-08-22 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - CENTRAL | 2629 | 22140564400 |  | 100463288 |  | 6748208M |  |  |  | 566 | EX | ABN MTR/SL ABANDONED | 2621P | BROADWAY | 130 E BROADWAY ST 3 | 049 | WIN | 2022-10-21 | DMCCULL | DMCCULL | 2022-10-21 | 2022-09-30 |  |  | CHARLES COMBS | 2022-08-22 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - CENTRAL | 2629 | 22140564800 |  | 100463260 |  | 6748208M |  |  |  | 566 | EX | ABN MTR/SL ABANDONED | 2621P | BROADWAY | 130 E BROADWAY ST 4 | 049 | WIN | 2022-10-21 | DMCCULL | DMCCULL | 2022-10-21 | 2022-09-30 |  |  | CHARLES COMBS | 2022-08-22 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - WEST | 2623 | 22970120200 |  | 100279885 |  | 6688228J | 2181158 |  |  | 565 | EX | REPLACE SL W/21-0261319-00 | 2600B | LYONS | 143 LYONS DR | 073 | FRA | 2022-08-22 | U126602 | U134723 | 2022-01-27 | 2022-12-30 |  |  | DEREK PAYTON | 2022-08-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 10 | 1 | 3062.45 | 774.45 | 0 | 46.55 | 2241.45 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22970120600 |  | 100280347 |  | 6688228J | 2181158 |  |  | 565 | EX | REPLACE SL W/21-0261319-00 | 2600B | LYONS | 150 LYONS DR | 073 | FRA | 2022-08-22 | U128410 | U134723 | 2022-01-27 | 2022-12-30 |  |  | CDESPAIN | 2022-08-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2345.72 | 0 | 0 | 0 | 2345.72 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22970120700 |  | 100279889 |  | 6688228J | 2181158 |  |  | 565 | EX | REPLACE SL W/21-0261319-00 | 2600B | LYONS | 153 LYONS DR | 073 | FRA | 2022-08-22 | U128410 | U134723 | 2022-01-27 | 2022-12-30 |  |  | CDESPAIN | 2022-08-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2277.28 | 0 | 0 | 0 | 2277.28 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22979037400 |  | 100337218 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RAND | 156 RAND AV | 067 | LEX | 2022-08-23 | U125881 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | HERBERT HAYDEN | 2022-08-22 | 2022-04-27 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.9167 | 2 | 2470.44 | 229.73 | 0 | 345.91 | 1894.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979042400 |  | 100351712 |  | 6744208O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | VICTORY | 13 VICTORY AV | 049 | WIN | 2022-09-02 | U938684 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | CHARLES COMBS | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1805 | 0 | 0 | 0 | 1805 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979048600 |  | 100461153 |  | 6744208N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BARLOW | 507 BARLOW DR | 049 | WIN | 2022-09-02 | U938684 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | CHARLES COMBS | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1805 | 0 | 0 | 0 | 1805 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979049800 |  | 500010294 |  | 6744208J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | STAMPER | 3466 STAMPER DR B | 049 | WIN | 2022-09-02 | U938684 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | CHARLES COMBS | 2022-08-22 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1805 | 0 | 0 | 0 | 1805 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22994325800 |  | 100353345 |  | 7256280K | 2180424 |  |  | 565 | EX | REPLACE SL W/21-0261272-00 | 2600B | 3RD | 502 W 3RD ST | 161 | MAY | 2022-08-22 | U126286 | U134723 | 2022-04-19 | 2022-12-30 |  |  | TYLER ALLISON | 2022-08-22 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2027.3 | 0 | 0 | 0 | 2027.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22994327200 |  | 100353361 |  | 7256280G | 2180424 |  |  | 565 | EX | REPLACE SL W/21-0261272-00 | 2600B | 3RD | 541 W 3RD ST | 161 | MAY | 2022-08-22 | U126286 | U134723 | 2022-04-19 | 2022-12-30 |  |  | TYLER ALLISON | 2022-08-22 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2283.54 | 0 | 0 | 0 | 2283.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07699555900 |  | 100300065 |  | 16716212B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | THOMPSON | 108< THOMPSON RD | 067 | LEX | 2022-11-23 | U938516 | DMCCULL | 2007-08-23 | 2022-07-01 | 2022-12-31 |  | CHRIS HUNGATE | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - EAST | 2633 | 11900950300 |  | 100240968 |  | 7324132F | 2290467 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAIN | 750 E MAIN ST | 119 | HIN | 2022-08-23 | U125566 | U906631 | 2011-04-13 | 2022-07-01 | 2022-12-31 |  | UNKNOWN/PAPER ONLY DSKAGGS | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - EAST | 2633 | 11919343100 |  | 100240970 |  | 7324132F | 2290467 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAIN | 660 E MAIN ST | 119 | HIN | 2022-08-23 | U125566 | U124449 | 2011-08-08 | 2022-07-01 | 2022-12-31 |  | UNKNOWN/ PAPER ONLY DSKAGGS | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - WEST | 2623 | 21026119600 |  |  |  | 6712236G | 2070683 | U124399 |  | 559 | CO | PM- TURNER STATION REPLACEMENT | 5320E | CHERRY BLOSSOM | CHERRY BLOSSOM | 209 | GEO | 2022-12-05 |  | U124399 | 2021-04-28 | 2021-12-29 | 2021-12-31 | 2022-08-23 | SWBISHOP | 2022-08-23 | 2022-10-03 |  | C | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00559 | 3201013 |  |  | WP1196 | KSMRP |  | 100 | 101332210261196 | 285.5833 | 2108 | 3311444.82 | 16624.45 | 527433.31 | 29883.64 | 2239066.83 | 0 | 54708.18 | 443728.41 | 68
KY | KY - WEST | 2623 | 21026119700 |  |  |  | 6712236H | 2070683 | U124399 |  | 560 | CO | PM- TURNER STATION ABANDONMENT | 5320E | CHERRY BLOSSOM | CHERRY BLOSSOM | 209 | GEO | 2022-12-27 |  | U124399 | 2021-04-28 | 2021-12-29 | 2021-12-31 | 2022-08-23 | SWBISHOP | 2022-08-23 |  |  | C | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00560 | 3201014 |  |  | WP1197 | KSMRP |  | 100 | 101432210261197 |  | 0 | 378972.89 | 50079.42 | 233233.04 | 0 | 95660.43 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883063500 |  | 100348545 |  | 6748208J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | IRONWORKS | 1031 IRONWORKS RD | 049 | WIN | 2022-09-02 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1320 | 0 | 0 | 0 | 1320 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883125000 |  | 100322029 |  | 16716212P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | TRANSYLVANIA | 429 TRANSYLVANIA PR | 067 | LEX | 2022-11-15 | U125881 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1941.14 | 0 | 0 | 0 | 1941.14 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883150300 |  | 500816091 |  | 6716212F | 0252691 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | VERSAILLES | 1109 VERSAILLES RD 500 | 067 | LEX | 2022-11-14 | U125881 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883219200 |  | 100449142 |  | 7324132E | 2290467 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | KENTUCKY | 65 KENTUCKY DR | 119 | HIN | 2022-08-23 | U125566 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | UNKNOWN/PAPER ONLY DSKAGGS | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - CENTRAL | 2629 | 21883270300 |  | 100348505 |  | 6748208J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | IRONWORKS | 1407 IRONWORKS RD | 049 | WIN | 2022-09-02 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2295 | 0 | 0 | 0 | 2295 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21884271800 |  | 100349609 |  | 6748208M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | KENTUCKY | 19 KENTUCKY ST 1F | 049 | WIN | 2022-09-27 | U125559 | U128293 | 2021-02-04 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 3201 | 0 | 0 | 0 | 3201 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958604400 |  | 100447129 |  | 6720212M | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | MENTELLE | 1 MENTELLE PR A | 067 | LEX | 2022-08-24 | U129722 | U134723 | 2021-12-08 | 2022-12-30 |  |  | M YOUNG | 2022-08-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2330.94 | 0 | 0 | 0 | 2330.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958604600 |  | 100444790 |  | 6720212M | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | MENTELLE | 1 MENTELLE PR B | 067 | LEX | 2022-08-24 | U129722 | U134723 | 2021-12-08 | 2022-12-30 |  |  | M YOUNG | 2022-08-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 519.04 | 0 | 0 | 0 | 519.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958628300 |  | 100331909 |  | 6720212N | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 198 N ASHLAND AV | 067 | LEX | 2022-08-23 | U126308 | U134723 | 2021-12-08 | 2022-12-30 |  |  | J ENSMINGER | 2022-08-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1857.65 | 0 | 0 | 0 | 1857.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959033000 |  | 100315233 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | CONN TER | 216 CONN TER | 067 | LEX | 2022-08-23 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-08-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1990.45 | 0 | 0 | 0 | 1990.45 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959048700 |  | 100315159 |  | 6716212O | 2176780 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | TRANSCRIPT | 200 TRANSCRIPT AV | 067 | LEX | 2022-08-29 | U125881 | U134723 | 2021-12-10 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1 | 1618.84 | 0 | 0 | 0 | 1618.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026178500 |  |  |  | 6720216L | 2184395 | U122858 |  | 561 | EX | INSTALL 44'-6" PMMP | 2600B | PARKSIDE | 620 PARKSIDE DR | 067 | LEX | 2022-10-24 | U127644 | U122858 | 2022-03-25 | 2022-09-19 | 2022-09-30 | 2022-08-22 | CORY TINCHER | 2022-08-23 | 2022-08-09 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP1785 |  |  | 100 | 056132220261785 | 134.8333 | 882 | 65200.97 | 10284.34 | 8390.44 | 2555.21 | 33689.39 | 0 | 111.37 | 10170.22 | 63
KY | KY - WEST | 2621 | 22026178600 |  |  |  | 6720216L | 2184395 | U122858 |  | 562 | EX | RETIRE 26'-6" CSMP | 2600B | PARKSIDE | 620 PARKSIDE DR | 067 | LEX | 2022-10-14 | U127644 | U122858 | 2022-03-25 | 2022-09-30 | 2022-09-30 | 2022-08-22 | CORY TINCHER | 2022-08-23 | 2022-08-17 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP1786 |  |  | 100 | 056232220261786 | 20 | 0 | 1859.72 | 1452.44 | 0 | 87.28 | 320 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026231800 |  |  |  | 6716208A |  | U461383 |  | 584 | EX | RETIRE PAPER CHART | 2621M | LANE ALLEN | 707 LANE ALLEN RD | 067 | LEX | 2022-12-21 | U123258 | U461383 | 2022-10-17 | 2023-12-29 | 2023-12-31 | 2022-08-23 | CCOX | 2022-08-23 |  |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00584 | 3200584 |  |  | WP2318 |  |  | 100 | 058432220262318 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22122144100 |  | 500735006 |  | 7324132I | 2290467 |  |  | 566 | EX | ABANDON SL - HINDMAN FLOOD | 2600B | MAIN | 169 W MAIN ST UPSTAIR | 119 | HIN | 2022-08-28 | U123965 | U125208 | 2022-08-08 | 2022-08-08 |  |  | UNKNOWN/PAPER ONLY DSKAGGS | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - CENTRAL | 2632 | 22124945500 |  | 100356657 |  | 7260280M |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTREQD | 2621P | LEXINGTON | 668 LEXINGTON ST | 161 | MAY | 2022-08-23 | SDADAMS | U125208 | 2022-08-18 | 2022-08-31 | 2022-08-31 |  | SDADAMS | 2022-08-23 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 12.75 | 3 | 2847.57 | 843.61 | 71.68 | 121.48 | 1810.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125034100 |  | 100319112 |  | 6716208O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D304116 | 2621P | LARKIN | 2416 LARKIN RD | 067 | LEX | 2022-08-24 | U125208 | U136097 | 2022-08-18 | 2022-08-19 | 2022-09-08 |  | HMCKUNE | 2022-08-23 | 2022-08-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 36.5833 | 7 | 2359.73 | 1839.98 | 345.4 | 110.55 | 63.8 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22125348900 |  | 100450690 |  | 7320132L | 1313374 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE + | 2621P | GAYHEART | GAYHEART ST | 119 | HIN | 2022-08-23 | MBLANKE | U132823 | 2022-08-19 | 2022-08-19 |  |  | MBLANKE | 2022-08-23 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26330043 | 0.28333 | 1 | 20.42 | 15.76 | 0 | 4.66 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22125349000 |  | 100240778 |  | 7320132L | 1313374 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE + | 2621P | ROYHILL | 254 ROYHILL RD | 119 | HIN | 2022-08-23 | MBLANKE | U132823 | 2022-08-19 | 2022-08-19 |  |  | MBLANKE | 2022-08-23 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26330043 | 1.2167 | 1 | 84.61 | 65.28 | 0 | 19.33 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125589600 |  | 100297431 |  | 6716212H |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | ROSS | 333 ROSS ST | 067 | LEX | 2022-08-23 | U135195 | U125763 | 2022-08-22 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1743.62 | 0 | 0 | 0 | 1743.62 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22125957900 |  | 100284726 |  | 6760172G |  |  |  | 565 | EX | SERVICE LINE - REPLACE D311057 | 2621P | PEA RIDGE | 1600 PEA RIDGE RD | 065 | IRV | 2022-08-24 | U125208 | U132625 | 2022-08-23 | 2022-08-22 | 2022-08-22 |  | DENNING | 2022-08-23 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 24.4833 | 3 | 1992.81 | 1735.02 | 89.71 | 104.28 | 63.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125962100 |  | 100300005 |  | 6716212F |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | THOMPSON | 315 THOMPSON RD | 067 | LEX | 2022-11-28 | U938516 | U125763 | 2022-08-23 | 2022-12-30 |  |  | CHRIS HUNGATE | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1732.63 | 0 | 0 | 0 | 1732.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125963000 |  | 100294833 |  | 6716212E |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | UPPER | 458 N UPPER ST | 067 | LEX | 2022-08-23 | U135195 | U125763 | 2022-08-23 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125963200 |  | 501097866 |  | 6728208E |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | FALLING LEAVES | 1909 FALLING LEAVES LN | 067 | LEX | 2022-08-23 | U135195 | U125763 | 2022-08-23 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125963400 |  | 501097828 |  | 6724208E |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | FALLING LEAVES | 2057 FALLING LEAVES LN | 067 | LEX | 2022-08-23 | U135195 | U125763 | 2022-08-23 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22125963900 |  | 500106540 |  | 7356256E |  |  |  | 566 | EX | ABANDON SL- I/I/LGCY | 2600B | HACKWORTH | 2532 HACKWORTH ST | 019 | ASH | 2022-08-23 | U125566 | U134723 | 2022-08-23 | 2022-12-30 |  |  | DESKAGG | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.5833 | 1 | 1742.45 | 212.41 | 0 | 71.34 | 1458.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125964200 |  | 100313632 |  | 6716208B |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | MOCKINGBIRD | 337 MOCKINGBIRD LN | 067 | LEX | 2022-08-23 | U127206 | U125763 | 2022-08-23 | 2022-12-30 |  |  | JUSTIIN HOBBS | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 2529.57 | 774.45 | 0 | 46.55 | 1708.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125982800 |  | 100310145 |  | 6712208H |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | LONGVIEW | 667 LONGVIEW DR | 067 | LEX | 2022-08-23 | U127206 | U125763 | 2022-08-23 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1878.7 | 0 | 0 | 0 | 1878.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125984100 |  | 100338319 |  | 6720212J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 7TH | 567 E 7TH ST | 067 | LEX | 2022-08-25 | U930915 | U136526 | 2022-08-23 | 2022-08-23 |  |  | RSTRONG | 2022-08-23 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 0.33333 | 1 | 1300.37 | 21.09 | 15.22 | 56.86 | 1207.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125984300 |  | 100291089 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 7TH | 311 W 7TH ST | 067 | LEX | 2022-08-25 | U930915 | U136526 | 2022-08-23 | 2022-08-23 |  |  | RSTRONG | 2022-08-23 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 4.2667 | 1 | 2244.29 | 271.59 | 33.24 | 732.26 | 1207.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22126003200 |  | 100353369 |  | 7256280G | 2180424 |  |  | 565 | EX | REPLACE W/ 21026127200 | 2600B | 2ND | 564 W 2ND ST | 161 | MAY | 2022-08-23 | U126286 | U125768 | 2022-08-23 | 2049-12-31 |  |  | TYLER ALLISON | 2022-08-23 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26320032 |  | 1 | 2307.64 | 0 | 0 | 0 | 2307.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126007800 |  | 100325503 |  | 6720208E |  |  |  | 565 | EX | SERVICE LINE - REPLACE D311017 | 2621P | ANDOVER | 415 ANDOVER DR | 067 | LEX | 2022-08-24 | U125208 | U136526 | 2022-08-23 | 2022-08-23 | 2022-08-23 |  | RSTRONG | 2022-08-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26210022 | 2.2667 | 1 | 2925.89 | 147 | 339.2 | 396.29 | 2043.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126015700 |  | 100309847 |  | 6712208H |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | TUCSON | 2251 TUCSON DR | 067 | LEX | 2022-08-23 | U127206 | U125763 | 2022-08-23 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1793.63 | 0 | 0 | 0 | 1793.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126027500 |  | 501229811 |  | 6724212M |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | CARNER BLUFF | 1509 CARNER BLUFF | 067 | LEX | 2022-11-14 | U125881 | U125763 | 2022-08-23 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126030300 |  | 501229818 |  | 6724212M |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | CARNER BLUFF | 1516 CARNER BLUFF | 067 | LEX | 2022-11-14 | U125881 | U125763 | 2022-08-23 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126068100 |  | 100297933 |  | 6716212H |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | OLD GEORGETOWN | 211 OLD GEORGETOWN ST | 067 | LEX | 2022-08-23 | U135195 | U125763 | 2022-08-23 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1743.62 | 0 | 0 | 0 | 1743.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126068300 |  | 100297934 |  | 6716212H |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | OLD GEORGETOWN | 209 OLD GEORGETOWN ST | 067 | LEX | 2022-08-23 | U135195 | U125763 | 2022-08-23 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22970120400 |  | 100279886 |  | 6688228J | 2181158 |  |  | 565 | EX | REPLACE SL W/21-0261319-00 | 2600B | LYONS | 145 LYONS DR | 073 | FRA | 2022-08-23 | U128410 | U134723 | 2022-01-27 | 2022-12-30 |  |  | CDESPAIN | 2022-08-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2560.33 | 0 | 0 | 0 | 2560.33 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22979016000 |  | 100240948 |  | 7324132F | 2290467 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KY RT 550 | KY RT 550 | 119 | LEB | 2022-08-23 | U125566 | U128070 | 2022-02-17 | 2022-08-09 | 2022-12-31 |  | UNKNOWN/PAPER ONLY DSKAGGS | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - EAST | 2631 | 22979020800 |  | 100253110 |  | 7356256J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HACKWORTH | 3211 HACKWORTH ST | 019 | ASH | 2022-08-23 | U125566 | U128070 | 2022-02-17 | 2022-08-23 |  |  | DESKAGG | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.0167 | 1 | 1708.92 | 187.31 | 0 | 62.91 | 1458.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979021900 |  | 100255983 |  | 7356256E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HAMPTON | 2620 HAMPTON ST | 019 | ASH | 2022-08-23 | U125566 | U128070 | 2022-02-17 | 2022-08-23 | 2022-12-31 |  | DESKAGG | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.4 | 1 | 1344.44 | 65.09 | 0 | 21.85 | 1257.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979040900 |  | 100348037 |  | 6748208I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PEPPER | 100 PEPPER AL | 049 | WIN | 2022-09-02 | U938684 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | CHARLES COMBS | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2295 | 0 | 0 | 0 | 2295 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979041000 |  | 100348136 |  | 6748208I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MUTUAL | 225 MUTUAL AV | 049 | WIN | 2022-09-02 | U938684 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | CHARLES COMBS | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 3056.75 | 0 | 0 | 0 | 3056.75 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979041200 |  | 100348481 |  | 6748208K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | IRONWORKS | 1857 IRONWORKS RD | 049 | WIN | 2022-09-27 | U125559 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | CHARLES COMBS | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2295 | 0 | 0 | 0 | 2295 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979041800 |  | 100349676 |  | 6748208M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GEORGIA | 2 GEORGIA ST | 049 | WIN | 2022-09-02 | U938684 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | CHARLES COMBS | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2295 | 0 | 0 | 0 | 2295 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979042500 |  | 100351892 |  | 6744208O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FULTON | 220 FULTON AV | 049 | WIN | 2022-09-02 | U938684 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | CHARLES COMBS | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2295 | 0 | 0 | 0 | 2295 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979042900 |  | 100352618 |  | 6744204F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CHEROKEE | 47 CHEROKEE CT | 049 | WIN | 2022-09-02 | U938684 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | CHARLES COMBS | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2295 | 0 | 0 | 0 | 2295 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979051400 |  | 500210386 |  | 6748208J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | IRONWORKS | 1423 IRONWORKS RD | 049 | WIN | 2022-09-02 | U938684 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | CHARLES COMBS | 2022-08-23 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2295 | 0 | 0 | 0 | 2295 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22994325900 |  | 100353366 |  | 7256280G | 2180424 |  |  | 565 | EX | REPLACE SL W/21-0261272-00 | 2600B | 3RD | 549 W 3RD ST | 161 | MAY | 2022-08-23 | U126286 | U134723 | 2022-04-19 | 2022-12-30 |  |  | TYLER ALLISON | 2022-08-23 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2222.41 | 0 | 0 | 0 | 2222.41 | 0 | 0 | 0
KY | KY - WEST | 2621 | 05618092100 |  | 100324358 |  | 6720204E | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | OCTAVIAN | 1175 OCTAVIAN WY | 067 | LEX | 2022-08-24 | U135195 | SSUTHER | 2005-07-26 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-08-24 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 6907.91 | 0 | 0 | 0 | 6907.91 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11889579100 |  | 500820457 |  | 16744184F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | UNION CITY | 2412 UNION CITY RD | 151 | RIC | 2022-09-05 | U938684 | U906307 | 2011-02-17 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-08-24 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2295 | 0 | 0 | 0 | 2295 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18653070000 |  | 100312876 | 31 | 6716208E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HOLLYHILL | 479 HOLLYHILL DR | 067 | LEX | 2022-08-24 | U127206 | AJPARKS | 2018-10-24 | 2049-12-31 |  |  | JUSTIN HOBBS | 2022-08-24 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2540.9 | 0 | 0 | 0 | 2540.9 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883083400 |  | 100240924 |  | 7324132F | 2290467 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | KY RT 550 | KY RT 550 | 119 | LEB | 2022-08-28 | U123965 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | MBLANKE/CJH CASEY PACK | 2022-08-24 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - CENTRAL | 2629 | 21883167500 |  | 500556421 |  | 6744184J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | DURBIN | 150 DURBIN LN | 151 | RIC | 2022-09-05 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-08-24 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2295 | 0 | 0 | 0 | 2295 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883214900 |  | 500413697 |  | 6732208D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | COMBS FERRY | 3640 COMBS FERRY RD | 067 | LEX | 2022-12-08 | U126308 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHRIS HUNGATE | 2022-08-24 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 3210.31 | 647.93 | 0 | 543.6 | 2018.78 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883276100 |  | 500043132 |  | 6752204I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | IRVINE | 3485 IRVINE RD SHOP | 049 | WIN | 2022-09-05 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-08-24 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2295 | 0 | 0 | 0 | 2295 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21916424800 |  | 100336413 |  | 6720212E | 1858813 |  |  | 565 | EX | RPLC SL/18026843300/ | 2600B | M L KING | 357 M L KING BV | 067 | LEX | 2022-08-24 | U126532 | U131066 | 2021-06-03 | 2022-06-30 |  |  | LESLIE SHARON | 2022-08-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2315.33 | 0 | 0 | 0 | 2315.33 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916430500 |  | 100264046 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | JOY | 172 JOY LN | 019 | ASH | 2022-08-24 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-08-24 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3495.59 | 0 | 0 | 0 | 3495.59 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916440500 |  | 100264045 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2528 MAIN ST W | 019 | ASH | 2022-08-24 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-08-24 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1865.04 | 0 | 0 | 0 | 1865.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958595200 |  | 100331905 |  | 6720212N | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 188 N ASHLAND AV | 067 | LEX | 2022-08-25 | U129722 | U134723 | 2021-12-08 | 2022-12-30 |  |  | M YOUNG | 2022-08-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1655.99 | 0 | 0 | 0 | 1655.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958595300 |  | 100331906 |  | 6720212N | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 190 N ASHLAND AV | 067 | LEX | 2022-08-25 | U129722 | U134723 | 2021-12-08 | 2022-12-30 |  |  | M YOUNG | 2022-08-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1788.49 | 0 | 0 | 0 | 1788.49 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958595400 |  | 100331907 |  | 6720212N | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 192 N ASHLAND AV | 067 | LEX | 2022-08-25 | U129722 | U134723 | 2021-12-08 | 2022-12-30 |  |  | M YOUNG | 2022-08-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1997.01 | 0 | 0 | 0 | 1997.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959032600 |  | 100315236 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | CONN TER | 204 CONN TER | 067 | LEX | 2022-08-24 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-08-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1368.79 | 0 | 0 | 0 | 1368.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959046700 |  | 100315237 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | CONN TER | 200 CONN TER | 067 | LEX | 2022-08-24 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-08-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1254.4 | 0 | 0 | 0 | 1254.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026200700 |  |  |  | 6704228E | 2289376 | U122858 |  | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2621M | US 460 & IRONWORKS PK | US 460 & IRONWORKS PK | 209 | GEO | 2022-09-19 | U125936 | U136124 | 2022-06-08 | 2022-12-30 | 2022-12-31 | 2022-08-24 | CWEMPE | 2022-08-24 | 2022-08-24 |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00909 | 3200909 |  |  | WP2007 |  |  | 100 | 090932220262007 | 5.35 | 0 | 5573.15 | 358.7 | 0 | 21.56 | 5174.3 | 0 | 18.59 | 0
KY | KY - WEST | 2623 | 22026200800 |  |  |  | 6704228E | 2289376 | U122858 |  | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2621M | US 460 & IRONWORKS PK | US 460 & IRONWORKS PK | 209 | GEO | 2022-09-19 | U125936 | U136124 | 2022-06-08 | 2022-12-30 | 2022-12-31 | 2022-08-24 | CWEMPE | 2022-08-24 | 2022-08-24 |  | F | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00910 | 3200910 |  |  | WP2008 |  |  | 100 | 091032220262008 | 4.0333 | 0 | 285.19 | 269.02 | 0 | 16.17 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22122143800 |  | 100240802 |  | 7324132I | 2290467 |  |  | 566 | EX | ABANDON SL - HINDMAN FLOOD | 2600B | MAIN | 88 W MAIN ST | 119 | HIN | 2022-08-24 | U123965 | U125208 | 2022-08-08 | 2022-08-08 |  |  | MBLANKE/CJH CASEY PACK | 2022-08-24 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - EAST | 2631 | 22124936500 |  | 100263543 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400 | 2600B | MAIN | 2517 MAIN ST W | 019 | ASH | 2022-08-24 | U124015 | U124396 | 2022-08-18 | 2022-12-22 |  |  | ORA SLONE | 2022-08-24 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2312.85 | 0 | 0 | 0 | 2312.85 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22125293900 |  | 100258424 |  | 7344264D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D244475 | 2621P | HIGHLAND | 152 HIGHLAND AV | 089 | RAC | 2022-08-24 | JCYRUS | U125208 | 2022-08-19 | 2022-08-19 | 2022-08-19 |  | JCYRUS | 2022-08-24 | 2022-08-23 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 42.4333 | 9 | 5925.31 | 1699.27 | 472.1 | 3658.24 | 95.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126296000 |  | 100313818 |  | 6716208B |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | WALLER | 393 WALLER AV 10 | 067 | LEX | 2022-08-24 | MCRAIG | U124447 | 2022-08-23 | 2022-08-23 | 2022-08-23 |  | MCRAIG | 2022-08-24 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 46.9667 | 7 | 10235.08 | 3113.88 | 467.93 | 4023.11 | 2630.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126297400 |  | 100312861 |  | 6716208E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D304117 | 2621P | STRATFORD | 470 STRATFORD DR | 067 | LEX | 2022-08-26 | U125208 | U132625 | 2022-08-24 | 2022-08-23 | 2022-08-23 |  | RSTRONG | 2022-08-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.9667 | 1 | 5184.6 | 444.15 | 228.43 | 1197.48 | 3314.54 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22126306900 |  | 100255930 |  | 7356256E |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2600B | CROOKS | 1915 CROOKS ST | 019 | ASH | 2022-08-24 | U125566 | U134723 | 2022-08-24 | 2022-12-30 |  |  | DESKAGG | 2022-08-24 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.75 | 1 | 1907.69 | 34.89 | 0 | 11.7 | 1861.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22126307000 |  | 100248926 |  | 7356256I |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2600B | SHUTE | 3033 SHUTE ST | 019 | ASH | 2022-08-24 | U125566 | U134723 | 2022-08-24 | 2022-12-30 |  |  | DESKAGG | 2022-08-24 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.73333 | 1 | 1805.84 | 33.94 | 0 | 11.4 | 1760.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22126307100 |  | 100265204 |  | 7352256C |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2600B | WHEATLEY | 205 WHEATLEY RD | 019 | ASH | 2022-08-24 | U125566 | U134723 | 2022-08-24 | 2022-12-30 |  |  | DESKAGG | 2022-08-24 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.1333 | 1 | 2054.83 | 145.02 | 0 | 48.71 | 1861.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126328300 |  | 501139014 |  | 6724208L |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | AUTUMN RIDGE | 1212 AUTUMN RIDGE DR | 067 | LEX | 2022-08-24 | U135195 | U125763 | 2022-08-24 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-24 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126328600 |  | 500574330 |  | 6724208E |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | CHECKERBERRY | 2604 CHECKERBERRY DR | 067 | LEX | 2022-08-24 | U135195 | U125763 | 2022-08-24 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-24 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1836.7 | 0 | 0 | 0 | 1836.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126329000 |  | 500536022 |  | 6724208E |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | GRAFTONS MILL | 696 GRAFTONS MILL LN | 067 | LEX | 2022-11-14 | U125881 | U125763 | 2022-08-24 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-08-24 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126329700 |  | 501229823 |  | 6724212M |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | RUTLEDGE | 2161 RUTLEDGE AV LT74 | 067 | LEX | 2022-11-14 | U125881 | U125763 | 2022-08-24 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-08-24 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126330000 |  | 501229824 |  | 6724212M |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | RUTLEDGE | 2165 RUTLEDGE AV LT75 | 067 | LEX | 2022-11-14 | U125881 | U125763 | 2022-08-24 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-08-24 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126330200 |  | 501229810 |  | 6724212M |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | RUTLEDGE | 2152 RUTLEDGE AV LT115C | 067 | LEX | 2022-11-14 | U125881 | U125763 | 2022-08-24 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-08-24 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126339000 |  | 500536435 |  | 6724208E |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | GRAFTONS MILL | 712 GRAFTONS MILL LN | 067 | LEX | 2022-11-14 | U125881 | U125763 | 2022-08-24 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-08-24 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126339500 |  | 500536431 |  | 6724208E |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | GRAFTONS MILL | 728 GRAFTONS MILL LN | 067 | LEX | 2022-11-14 | U125881 | U125763 | 2022-08-24 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-08-24 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1639.55 | 0 | 0 | 0 | 1639.55 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126371100 |  | 100312649 |  | 6716208E |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | LONGVIEW | 489 LONGVIEW DR | 067 | LEX | 2022-08-24 | U127206 | U125763 | 2022-08-24 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-08-24 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 2784.76 | 774.45 | 0 | 46.55 | 1963.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126390800 |  | 501217669 |  | 6724212M |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | COVINGTON | 1985 COVINGTON DR | 067 | LEX | 2022-11-28 | U938516 | U125763 | 2022-08-24 | 2022-12-30 |  |  | CHRIS HUNGATE | 2022-08-24 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1898.97 | 0 | 0 | 0 | 1898.97 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126406500 |  | 100329162 |  | 6720208P |  |  |  | 565 | EX | REPLACE SERV LINE | 2621P | PLAINVIEW | 508 PLAINVIEW RD | 067 | LEX | 2022-08-25 | U930915 | U136097 | 2022-08-24 | 2022-08-24 |  |  | LSTANFI | 2022-08-24 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 14.8333 | 3 | 1081.1 | 828.74 | 145.36 | 49.8 | 57.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964234800 |  | 100347770 |  | 6744208L | 2292377 |  |  | 566 | EX | ABANDON SL/22026228200 | 2600B | HOLLY | 128 HOLLY AV | 049 | WIN | 2023-05-22 | U126603 | U134723 | 2022-01-06 | 2023-07-31 |  |  | SHAWN DENNIS/CHALES COMBS | 2022-08-24 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26290043 |  | 1
KY | KY - CENTRAL | 2629 | 22964252500 |  | 100347936 |  | 6748208I | 2075093 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | MAIN | 614 N MAIN ST | 049 | WIN | 2022-09-05 | U938684 | U134723 | 2022-01-06 | 2022-12-30 |  |  | CHARLES COMBS | 2022-08-24 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26290043 |  | 1 | 2295 | 0 | 0 | 0 | 2295 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22970120000 |  | 100279884 |  | 6688228J | 2181158 |  |  | 565 | EX | REPLACE SL W/21-0261319-00 | 2600B | LYONS | 141 LYONS DR | 073 | FRA | 2022-08-29 | U128410 | U134723 | 2022-01-27 | 2022-12-30 |  |  | CDESPAIN | 2022-08-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2683.05 | 0 | 0 | 0 | 2683.05 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22970120500 |  | 100279888 |  | 6688228J | 2181158 |  |  | 565 | EX | REPLACE SL W/21-0261319-00 | 2600B | LYONS | 149 LYONS DR | 073 | FRA | 2022-08-24 | U126602 | U134723 | 2022-01-27 | 2022-12-30 |  |  | DEREK PAYTON | 2022-08-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 10 | 1 | 4471.78 | 774.45 | 0 | 46.55 | 3650.78 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979025800 |  | 100265072 |  | 7352260O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DALTON | 2000 DALTON AV | 019 | ASH | 2022-08-24 | U125566 | U128070 | 2022-02-17 | 2022-08-24 | 2022-12-31 |  | DESKAGG | 2022-08-24 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.1667 | 1 | 1855.48 | 146.42 | 0 | 49.16 | 1659.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979052600 |  | 500432409 |  | 6748204H | 9611669 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | IRVINE | 1591 IRVINE RD | 049 | WIN | 2022-09-05 | U938684 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | CHARLES COMBS | 2022-08-24 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2295 | 0 | 0 | 0 | 2295 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22994325200 |  | 100353319 |  | 7256280K | 2180424 |  |  | 565 | EX | REPLACE SL W/21-0261272-00 | 2600B | 3RD | 414 W 3RD ST | 161 | MAY | 2022-10-13 | U461478 | U134723 | 2022-04-19 | 2022-12-30 |  |  | DAVID STAGGS | 2022-08-24 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 4023.22 | 0 | 0 | 0 | 4023.22 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 07683922400 |  | 500498114 |  | 16 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CHARLIE NORRIS | 947 CHARLIE NORRIS RD | 151 | RIC | 2022-09-05 | U938684 | DMCCULL | 2007-04-20 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2620 | 0 | 0 | 0 | 2620 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 10851285500 |  | 500160452 |  | W-1126/50 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | DOYLESVILLE | 2545 DOYLESVILLE RD | 151 | RIC | 2022-09-05 | U938684 | DMCCULL | 2010-07-21 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2295 | 0 | 0 | 0 | 2295 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11892909000 |  | 100432732 |  | X-1103-29 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WACO LOOP | 624 WACO LOOP | 151 | WAC | 2022-09-05 | U938684 | U906307 | 2011-03-01 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 3185 | 0 | 0 | 0 | 3185 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12968006200 |  | 100316374 |  | 6716208F |  |  |  | 566 | EX | SOII - METER ABANDON ONLY | 2621P | CHERRYBARK | 125 CHERRYBARK DR 2 | 067 | LEX | 2022-08-25 | U127206 | U124967 | 2012-05-02 | 2019-11-27 |  |  | JUSTIN HOBBS | 2022-08-25 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 19760828600 |  | 100316376 |  | 6716208F |  |  |  | 566 | EX | SOII - METER ABANDON ONLY | 2621P | CHERRYBARK | 125 CHERRYBARK DR 3 | 067 | LEX | 2022-08-25 | U127206 | U125208 | 2019-11-22 | 2019-11-27 |  |  | JUSTIN HOBBS | 2022-08-25 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 20772128000 |  | 100338431 | 61 | 32010143P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 7TH | 227< E 7TH ST | 067 | LEX | 2022-08-25 | RSTRONG | JFAWNS | 2020-01-18 | 2020-03-20 |  |  | RSTRONG | 2022-08-25 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.15 | 1 | 35.45 | 9.59 | 0 | 25.86 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883050500 |  | 500730282 |  | 6736180C |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SAMUEL ROSS | 205 SAMUEL ROSS CT | 151 | RIC | 2022-09-05 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2620 | 0 | 0 | 0 | 2620 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883051300 |  | 500568598 |  | 6744208D | 9613807 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BAY HILL | 133 BAY HILL DR | 049 | WIN | 2022-09-05 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2620 | 0 | 0 | 0 | 2620 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883160300 |  | 100340823 |  | 6744184F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | UNION CITY | 2381 UNION CITY RD TR1 | 151 | RIC | 2022-09-05 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2620 | 0 | 0 | 0 | 2620 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883276900 |  | 500704111 |  | 6724208H | 9935860 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | ROYAL TROON | 3285 ROYAL TROON RD | 067 | LEX | 2022-08-25 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958595000 |  | 100331903 |  | 6720212N | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 180 N ASHLAND AV | 067 | LEX | 2022-08-25 | U129722 | U134723 | 2021-12-08 | 2022-12-30 |  |  | M YOUNG | 2022-08-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1907.74 | 0 | 0 | 0 | 1907.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959033200 |  | 100315231 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | CONN TER | 224 CONN TER | 067 | LEX | 2022-08-25 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-08-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1087.78 | 0 | 0 | 0 | 1087.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959034900 |  | 100433150 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | LEADER | 178 LEADER AV | 067 | LEX | 2022-08-25 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-08-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1070.36 | 0 | 0 | 0 | 1070.36 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026194800 |  |  |  | 6744208H | 2289197 | U122858 |  | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2621M | ROLLING HILLS | 555 ROLLING HILLS DR | 049 | WIN | 2022-11-03 | U123258 | U136124 | 2022-06-01 | 2022-12-30 | 2022-12-31 | 2022-08-25 | JPASLEY | 2022-08-25 | 2022-08-25 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00909 | 3200909 |  |  | WP1948 |  |  | 100 | 090932220261948 | 8 | 0 | 5891.93 | 553.81 | 0 | 144.91 | 5174.3 | 0 | 18.91 | 0
KY | KY - CENTRAL | 2629 | 22026194900 |  |  |  | 6744208H | 2289197 | U122858 |  | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2621M | ROLLING HILLS | 555 ROLLING HILLS DR | 049 | WIN | 2022-11-03 | U123258 | U136124 | 2022-06-01 | 2022-12-30 | 2022-12-31 | 2022-08-25 | JPASLEY | 2022-08-25 |  |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00910 | 3200910 |  |  | WP1949 |  |  | 100 | 091032220261949 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22111242600 |  | 100337545 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 6TH | 229 E 6TH ST 1FR | 067 | LEX | 2022-08-26 | U125208 | U125208 | 2022-06-20 | 2022-12-30 |  |  | RSTRONG | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.0167 | 1 | 1917.9 | 131 | 15.22 | 353.22 | 1418.46 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22112530500 |  | 100273792 |  | 6680228K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311853 | 2621P | SINGLETON | 118 SINGLETON LN | 073 | FRA | 2022-08-26 | U125208 | U125208 | 2022-06-27 | 2022-08-23 | 2024-06-30 |  | BWHITE | 2022-08-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.7833 | 2 | 3947.41 | 548.86 | 194.91 | 32.97 | 3170.67 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22112530800 |  | 100273762 |  | 6680228L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311854 | 2621P | PEA RIDGE | 105 PEA RIDGE RD | 073 | FRA | 2022-08-26 | U125208 | U125208 | 2022-06-27 | 2022-08-24 | 2024-06-30 |  | BWHITE | 2022-08-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.6833 | 2 | 3106.95 | 269.13 | 194.91 | 16.19 | 2626.72 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22112531100 |  | 100273765 |  | 6680228L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311855 | 2621P | PEA RIDGE | 283 PEA RIDGE RD | 073 | FRA | 2022-08-25 | DCOLLIN | U125208 | 2022-06-27 | 2022-08-24 | 2024-06-30 |  | DCOLLIN | 2022-08-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.4333 | 1 | 5566.78 | 434.67 | 431.59 | 2182.36 | 2518.16 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22112531400 |  | 100434449 |  | 6680228L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311856 | 2621P | PEA RIDGE | 340 PEA RIDGE RD L | 073 | FRA | 2022-08-25 | DCOLLIN | U125208 | 2022-06-27 | 2022-08-24 | 2024-06-30 |  | DCOLLIN | 2022-08-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.95 | 1 | 5713.17 | 338.89 | 234.76 | 1701.55 | 3437.97 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22121160300 |  | 100252976 |  | 7356256F |  |  |  | 566 | EX | ABANDON SERIVE LINE | 2621P | PARK | 3220 PARK ST | 019 | ASH | 2022-08-25 | U125566 | U129939 | 2022-08-03 | 2022-08-03 |  |  | DESKAGG | 2022-08-25 | 2022-08-24 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.5667 | 2 | 1821.38 | 120.88 | 0 | 40.6 | 1659.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22124596700 |  | 100275935 |  | 6684228G |  | U129939 |  | 565 | EX | REPLACE SERVICE LINE | 2621P | MERO | 215 MERO ST | 073 | FRA | 2022-08-26 | U125208 | U129939 | 2022-08-17 | 2022-08-18 |  |  | BWHITE | 2022-08-25 | 2022-08-18 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 11.7833 | 2 | 6268.82 | 832.1 | 621.64 | 50 | 4765.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22124645500 |  | 100329163 |  | 6720208P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303226 | 2621P | PLAINVIEW | 504 PLAINVIEW RD | 067 | LEX | 2022-08-25 | U930915 | U125208 | 2022-08-17 | 2022-08-19 | 2022-09-06 |  | LSTANFI | 2022-08-25 | 2022-08-24 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 64.2 | 7 | 6388.72 | 3946.99 | 196.54 | 1571.39 | 673.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125033700 |  | 100404240 |  | 6724208E |  |  |  | 565 | EX | REPLACE SERVICE LINE D311055 | 2621P | PEACHTREE | 380 PEACHTREE RD | 067 | LEX | 2022-08-26 | U125208 | U129939 | 2022-08-18 | 2022-08-19 | 2022-09-08 |  | RJCRAWF | 2022-08-25 | 2022-08-25 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 31.5 | 4 | 2379.15 | 1888.85 | 282.19 | 113.51 | 94.6 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22126295600 |  | 100273793 |  | 6680228K |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | SINGLETON | 134 SINGLETON LN | 073 | FRA | 2022-08-25 | BWHITE | U136097 | 2022-08-23 | 2022-08-23 |  |  | BWHITE | 2022-08-25 | 2022-08-23 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 17.6833 | 3 | 6741.24 | 1169.07 | 0 | 70.23 | 5501.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126327800 |  | 500755655 |  | 6724208B |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | ASTARITA | 2473 ASTARITA WY | 067 | LEX | 2022-08-30 | U135195 | U125763 | 2022-08-24 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1560.88 | 0 | 0 | 0 | 1560.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126618700 |  | 100324257 |  | 6720204F |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | VENETIAN | 1216 VENETIAN CR | 067 | LEX | 2022-08-26 | U125208 | U136526 | 2022-08-25 | 2022-08-25 |  |  | WISHII | 2022-08-25 | 2022-08-25 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.5833 | 2 | 2938.85 | 855.52 | 198.85 | 1789.88 | 94.6 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22126648800 |  | 100253141 |  | 7356256E |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2600B | HOLT | 3230 HOLT ST | 019 | ASH | 2022-08-25 | U125566 | U134723 | 2022-08-25 | 2022-12-30 |  |  | DESKAGG | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.0833 | 1 | 1625.74 | 49.74 | 0 | 16.7 | 1559.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126651900 |  | 100331904 |  | 6720212N | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 184 N ASHLAND AV | 067 | LEX | 2022-08-25 | U129722 | U134723 | 2022-08-25 | 2022-12-30 |  |  | M YOUNG | 2022-08-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2376.69 | 0 | 0 | 0 | 2376.69 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126655800 |  | 100312771 |  | 6716208E |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | STRATFORD | 479 STRATFORD DR | 067 | LEX | 2022-08-25 | U127206 | U125763 | 2022-08-25 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 2529.57 | 774.45 | 0 | 46.55 | 1708.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126657000 |  | 500690136 |  | 6724208F | 9934174 |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | RED LEAF | 2701 RED LEAF DR | 067 | LEX | 2022-08-25 | U135195 | U125763 | 2022-08-25 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126657100 |  | 500690103 |  | 6724208F | 9934174 |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | RED LEAF | 2661 RED LEAF DR | 067 | LEX | 2022-08-25 | U135195 | U125763 | 2022-08-25 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1535.48 | 0 | 0 | 0 | 1535.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126657200 |  | 500704103 |  | 6724208H | 9935860 |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | ROYAL TROON | 3293 ROYAL TROON RD | 067 | LEX | 2022-08-25 | U135195 | U125763 | 2022-08-25 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126657300 |  | 500351076 |  | 6724208K | 9402231 |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | PUTTER | 3213 PUTTER LN | 067 | LEX | 2022-08-25 | U135195 | U125763 | 2022-08-25 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1535.48 | 0 | 0 | 0 | 1535.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126657400 |  | 100316372 |  | 6716208F |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | CHERRYBARK | 125 CHERRYBARK DR 1 | 067 | LEX | 2022-08-29 | U127206 | U125763 | 2022-08-25 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 321.94 | 0 | 0 | 0 | 321.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126659100 |  | 100316573 |  | 6716208F |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | PENMOKEN | 162 PENMOKEN PR | 067 | LEX | 2022-08-25 | U127206 | U125763 | 2022-08-25 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1878.7 | 0 | 0 | 0 | 1878.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126686700 |  | 100331897 |  | 6720212N | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 166 N ASHLAND AV | 067 | LEX | 2022-08-25 | U129722 | U134723 | 2022-08-25 | 2022-12-30 |  |  | M YOUNG | 2022-08-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2105.37 | 0 | 0 | 0 | 2105.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126694100 |  | 501229788 |  | 6724212M | 1850232 |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | RUTLEDGE | 2145 RUTLEDGE AV LT70 | 067 | LEX | 2022-11-14 | U125881 | U125763 | 2022-08-25 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126694200 |  | 501229832 |  | 6724212M | 1850232 |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | RUTLEDGE | 2197 RUTLEDGE AV LT83 | 067 | LEX | 2022-11-14 | U125881 | U125763 | 2022-08-25 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126694500 |  | 501229826 |  | 6724212M | 1850232 |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | RUTLEDGE | 2173 RUTLEDGE AV LT77 | 067 | LEX | 2022-11-14 | U125881 | U125763 | 2022-08-25 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 5467.95 | 0 | 0 | 0 | 5467.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126694600 |  | 501229825 |  | 6724212M | 1850232 |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | RUTLEDGE | 2169 RUTLEDGE AV LT76 | 067 | LEX | 2022-11-14 | U125881 | U125763 | 2022-08-25 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126694700 |  | 501229828 |  | 6724212M | 1850232 |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | RUTLEDGE | 2181 RUTLEDGE AV LT79 | 067 | LEX | 2022-11-14 | U125881 | U125763 | 2022-08-25 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126701900 |  | 100333471 |  | 6720212I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 2ND | 321 E 2ND ST | 067 | LEX | 2022-08-26 | U125208 | U136526 | 2022-08-25 | 2022-08-25 |  |  | RSTRONG | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.46667 | 1 | 1390.31 | 30.07 | 1.63 | 80.99 | 1277.62 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22127079100 |  | 100417779 |  | 6752176B |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | REEVES | 130 REEVES RD | 151 | WAC | 2022-09-05 | U938684 | U125763 | 2022-08-26 | 2022-12-30 |  |  | CHARLES COMBS | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2620 | 0 | 0 | 0 | 2620 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22127079200 |  | 100284599 |  | 6748180H |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | COLLEGE HILL | 730 COLLEGE HILL RD | 151 | WAC | 2022-09-05 | U938684 | U125763 | 2022-08-26 | 2022-12-30 |  |  | CHARLES COMBS | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 3785 | 0 | 0 | 0 | 3785 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22970119100 |  | 100279877 |  | 6684228N | 2181158 |  |  | 565 | EX | REPLACE SL W/21-0261319-00 | 2600B | LYONS | 115 LYONS DR | 073 | FRA | 2022-08-25 | U126602 | U134723 | 2022-01-27 | 2022-08-25 |  |  | DEREK PAYTON | 2022-08-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 10 | 1 | 4860.11 | 774.45 | 0 | 46.55 | 4039.11 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22970119700 |  | 100279882 |  | 6684228N | 2181158 |  |  | 565 | EX | REPLACE SL W/21-0261319-00 | 2600B | LYONS | 133 LYONS DR | 073 | FRA | 2022-08-25 | U128816 | U134723 | 2022-01-27 | 2022-12-30 |  |  | OLIVER MAYNARD | 2022-08-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.4667 | 1 | 3089.46 | 501.36 | 0 | 30.13 | 2557.97 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979018300 |  | 100246425 |  | 7356256I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | EUCLID | 2514 E EUCLID AV | 019 | ASH | 2022-08-25 | U125566 | U128070 | 2022-02-17 | 2022-08-25 | 2022-12-31 |  | DESKAGG | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.0833 | 1 | 1525.14 | 49.74 | 0 | 16.7 | 1458.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979018800 |  | 100247696 |  | 7352256H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MANTZ | 2136 MANTZ ST | 019 | ASH | 2022-08-25 | U125566 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | DESKAGG | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.4667 | 1 | 1610.83 | 113.88 | 0 | 38.25 | 1458.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979027500 |  | 100268116 |  | 7356256C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WINCHESTER | 2869 WINCHESTER AV | 019 | ASH | 2022-08-25 | U125566 | U128070 | 2022-02-17 | 2022-08-25 | 2022-12-31 |  | DESKAGG | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.35 | 1 | 2080.88 | 202.18 | 0 | 67.9 | 1810.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979053300 |  | 500498577 |  | 6744184K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CHARLIE NORRIS | 970 CHARLIE NORRIS RD | 151 | RIC | 2022-09-05 | U938684 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | CHARLES COMBS | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2620 | 0 | 0 | 0 | 2620 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979055600 |  | 500795023 |  | 6744184K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CHARLIE NORRIS | 955 CHARLIE NORRIS RD | 151 | RIC | 2022-09-05 | U938684 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | CHARLES COMBS | 2022-08-25 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2675 | 0 | 0 | 0 | 2675 | 0 | 0 | 0
KY | KY - WEST | 2623 | 12965304900 |  | 500206089 |  | 6712228C |  |  |  | 566 | EX | ABANDON SL - SOII/INSIDE+ | 2621P | WARRENDALE | 119 WARRENDALE AV C | 209 | GEO | 2022-08-31 | U125208 | U124967 | 2012-04-16 | 2014-12-23 | 2015-12-31 |  | CHERNDO | 2022-08-26 | 2022-08-18 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 5.2 | 3 | 327.85 | 309.25 | 0 | 18.6 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21026134500 |  |  |  | 7260276D | 2181540 | U122858 |  | 561 | EX | INSTALL 1537'-2"PMIP | 2600B | KENNEDY CREEK | KENNEDY CREEK RD | 161 | MAY | 2022-09-26 | U128132 | U122858 | 2021-07-28 | 2022-07-28 | 2022-08-30 | 2022-05-02 | DAVID STAGGS | 2022-08-26 | 2022-04-27 |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00561 | 3200561 |  |  | WP1345 |  |  | 100 | 056132210261345 | 116.7333 | 23430 | 332303.55 | 8148.6 | 5562 | 835.99 | 263062.87 | 0 | 421.47 | 54272.62 | 1562
KY | KY - CENTRAL | 2632 | 21026134600 |  |  |  | 7260276D | 2181540 | U122858 |  | 562 | EX | RETIRE 1053'-2" CSIP | 2600B | KENNEDY CREEK | KENNEDY CREEK RD | 161 | MAY | 2022-09-22 | U128132 | U122858 | 2021-07-28 | 2022-08-30 | 2022-08-30 | 2022-05-09 | DAVID STAGGS | 2022-08-26 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00562 | 3200562 |  |  | WP1346 |  |  | 100 | 056232210261346 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883106600 |  | 501139030 |  | 6724208L | 1316464 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LAWSON | 3337 LAWSON LN LT38 | 067 | LEX | 2022-08-26 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-08-26 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960237300 |  | 100321169 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | MAXWELL | 324 E MAXWELL ST | 067 | LEX | 2022-08-26 | U126309 | U134723 | 2021-12-17 | 2022-12-30 |  |  | JAMIE LYNN | 2022-08-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2548.07 | 0 | 0 | 0 | 2548.07 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026175400 |  |  |  | 6736232P | 2075121 | U128885 |  | 584 | EX | RETIRE R-1258 | 2629M | THOMAS | THOMAS ST | 017 | PAR | 2022-09-19 | U123258 | U128885 | 2022-03-10 | 2022-12-30 | 2022-12-31 | 2022-08-26 | WSHIMFESSEL | 2022-08-26 | 2022-08-18 |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00584 | 3200584 |  |  | WP1754 | AMRCB |  | 100 | 058432220261754 | 1.5667 | 0 | 114.11 | 107.64 | 0 | 6.47 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026175500 |  |  |  | 6740232M | 2075121 | U128885 |  | 584 | EX | RETIRE R-1275 | 2629M | SHORT | SHORT ST | 017 | PAR | 2022-09-19 | U123258 | U128885 | 2022-03-10 | 2022-12-30 | 2022-12-31 | 2022-08-26 | WSHIMFESSEL | 2022-08-26 | 2022-08-18 |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00584 | 3200584 |  |  | WP1755 | AMRCB |  | 100 | 058432220261755 | 3.4833 | 0 | 648.29 | 609.68 | 0 | 38.61 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026196900 |  |  |  | 6748208I | 2289271 | U122858 |  | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2621M | LINDEN | LINDEN AV | 049 | WIN | 2022-11-09 | U121330 | U136124 | 2022-06-03 | 2022-12-30 | 2022-12-31 | 2022-08-26 | JPASLEY | 2022-08-26 |  |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00909 | 3200909 |  |  | WP1969 |  |  | 100 | 090932220261969 |  | 0 | 5192.52 | 0 | 0 | 0 | 5174.3 | 0 | 18.22 | 0
KY | KY - CENTRAL | 2629 | 22026197000 |  |  |  | 6748208I | 2289271 | U122858 |  | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2621M | LINDEN | LINDEN AV | 049 | WIN | 2022-11-09 | U121330 | U136124 | 2022-06-03 | 2022-12-30 | 2022-12-31 | 2022-08-26 | JPASLEY | 2022-08-26 | 2022-08-26 |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00910 | 3200910 |  |  | WP1970 |  |  | 100 | 091032220261970 | 8 | 0 | 698.72 | 553.81 | 0 | 144.91 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22102151400 |  | 100312757 |  | 6716208E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309226 | 2621P | SHERIDAN | 486 SHERIDAN DR | 067 | LEX | 2022-08-31 | U125208 | U125208 | 2022-05-19 | 2022-11-18 | 2024-05-31 |  | RSTRONG | 2022-08-26 | 2022-06-29 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.3 | 3 | 5540.07 | 345.29 | 122.92 | 640.66 | 4431.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22111242800 |  | 100337546 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE + | 2621P | 6TH | 229 E 6TH ST 1FL | 067 | LEX | 2022-08-26 | RSTRONG | U125208 | 2022-06-20 | 2022-12-30 |  |  | RSTRONG | 2022-08-26 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.0833 | 1 | 486.57 | 131.64 | 0 | 354.93 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22121932700 |  | 100268449 |  | 7356256B |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | GREENUP | 2404 GREENUP AV | 019 | ASH | 2022-08-26 | RECUMP | U132002 | 2022-08-05 | 2022-08-19 | 2022-09-04 |  | RECUMP | 2022-08-26 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 15.45 | 4 | 1881.22 | 540.03 | 36.89 | 1304.3 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22124274500 |  | 100295070 |  | 6716212H |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | BOURBON | 453 BOURBON AV | 067 | LEX | 2022-08-26 | U930915 | U132002 | 2022-08-16 | 2022-08-30 | 2022-09-15 |  | TROE | 2022-08-26 | 2022-08-22 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 24.1833 | 5 | 1511.43 | 1407.22 | 19.65 | 84.56 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22125010300 |  | 100441066 |  | 6712232P |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | EDWARDS | 112 EDWARDS AV | 209 | GEO | 2022-08-31 | U125208 | U132002 | 2022-08-18 | 2022-09-01 | 2022-09-17 |  | CHERNDO | 2022-08-26 | 2022-08-25 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 13.85 | 3 | 856.33 | 807.79 | 0 | 48.54 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22125342900 |  | 100281895 |  | 6712232O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BOOKER T | 109 BOOKER T AV | 209 | GEO | 2022-08-31 | U125208 | U125208 | 2022-08-19 | 2022-08-24 | 2022-09-09 |  | CHERNDO | 2022-08-26 | 2022-08-25 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 10.5 | 3 | 610.32 | 575.71 | 0 | 34.61 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22126074000 |  | 100283749 |  | 6712228B |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | LEWIS | 108 LEWIS CT | 209 | GEO | 2022-08-26 | DCOLLIN | U125208 | 2022-08-23 | 2022-08-26 |  |  | DCOLLIN | 2022-08-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 7.8 | 1 | 5939.93 | 529.75 | 498.81 | 2659.75 | 2251.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127010600 |  | 501251721 |  | 6724208G |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | HELMSDALE | 3050 HELMSDALE PL 14101 | 067 | LEX | 2022-08-26 | U135195 | U125763 | 2022-08-26 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-26 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 3448.22 | 0 | 0 | 0 | 3448.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127010700 |  | 500571449 |  | 6724208E |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | HUGGING BEAR | 601 HUGGING BEAR DR | 067 | LEX | 2022-08-26 | U135195 | U125763 | 2022-08-26 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-26 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127023900 |  | 501173003 |  | 6724212M |  |  |  | 566 | EX | ABANDON SL | 2600B | GRIMBALL | 1120 GRIMBALL TR | 067 | LEX | 2022-08-29 | U938516 | U125201 | 2022-08-26 | 2022-09-30 |  |  | CHRIS HUNGATE | 2022-08-26 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2973.31 | 0 | 0 | 0 | 2973.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127024000 |  | 501097941 |  | 6724208E |  |  |  | 566 | EX | ABANDON SL | 2600B | HARDWOOD | 3766 HARDWOOD RD | 067 | LEX | 2022-08-29 | U938516 | U125201 | 2022-08-26 | 2022-09-30 |  |  | CHRIS HUNGATE | 2022-08-26 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127047300 |  | 100313536 |  | 6716208B |  |  |  | 565 | EX | SERVICE LINE - REPLACE D311019 | 2621P | HERON | 1540 HERON LN | 067 | LEX | 2022-08-31 | U125208 | U132823 | 2022-08-26 | 2022-08-26 | 2022-08-26 |  | RJCRAWF | 2022-08-26 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.4333 | 3 | 1565.7 | 931.66 | 482.36 | 55.98 | 95.7 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22127048300 |  | 100344809 |  | 6700224P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D308864 | 2621P | HIGHVIEW | 103 HIGHVIEW DR | 239 | MID | 2022-08-31 | U125208 | U132823 | 2022-08-26 | 2022-08-25 | 2022-08-25 |  | BWHITE | 2022-08-26 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 16 | 2 | 992.43 | 883.26 | 0 | 53.07 | 56.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127059100 |  | 100421679 |  | 6716204D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D247568 | 2621P | KIRKLEVINGTON | 3114 KIRKLEVINGTON DR | 067 | LEX | 2022-08-31 | U125208 | U125208 | 2022-08-26 | 2022-10-21 | 2024-04-30 |  | RSTRONG | 2022-08-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.4167 | 1 | 3739.04 | 217.28 | 185.87 | 585.81 | 2750.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127062500 |  | 100318608 |  | 6716204F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303175 | 2621P | WILSON DOWNING | 301 WILSON DOWNING RD | 067 | LEX | 2022-08-31 | U125208 | U132823 | 2022-08-26 | 2022-08-15 | 2022-09-02 |  | KKINDER | 2022-08-26 | 2022-08-25 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 31.8833 | 4 | 2715.08 | 2181.74 | 402.23 | 131.11 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127078300 |  | 501139192 |  | 6724212M | 1316677 |  |  | 566 | VO | ABANDN SL/LGCY | 2600B | HADDRELL | 1028 HADDRELL PT | 067 | LEX | 2022-11-14 |  | U125763 | 2022-08-26 | 2022-12-30 |  |  | HHAYDEN | 2022-08-26 |  |  | B | [11 empty] | 22144258200 | 100 |  |  | 1
KY | KY - WEST | 2621 | 22127078400 |  | 501177313 |  | 6724212M | 1427466 |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | HADDRELL | 1141 HADDRELL PT | 067 | LEX | 2022-11-14 | U125881 | U125763 | 2022-08-26 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-08-26 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127078500 |  | 501050527 |  | 6724208P | 0889492 |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | LOCHMERE | 805 LOCHMERE PL | 067 | LEX | 2022-11-14 | U125881 | U125763 | 2022-08-26 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-08-26 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127078600 |  | 501029104 |  | 6724204D | 0782622 |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | LOCHMERE | 4108 LOCHMERE LP | 067 | LEX | 2022-11-14 | U125881 | U125763 | 2022-08-26 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-08-26 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22979047300 |  | 100441137 |  | 6688224D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SLICKAWAY | 257 SLICKAWAY RD TRLR | 073 | FRA | 2022-08-26 | JMARSHA | U128070 | 2022-02-17 | 2022-08-19 | 2022-12-31 |  | JMARSHA | 2022-08-26 | 2022-08-19 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 11.3 | 3 | 748.67 | 706.24 | 0 | 42.43 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22994322800 |  | 100353500 |  | 7256280L | 2180424 |  |  | 565 | EX | REPLACE SL W/21-0261272-00 | 2600B | 3RD | 215 W 3RD ST | 161 | MAY | 2022-10-13 | U461478 | U134723 | 2022-04-19 | 2022-12-30 |  |  | DAVID STAGGS | 2022-08-26 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2575.19 | 0 | 0 | 0 | 2575.19 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22994323000 |  | 100353501 |  | 7256280K | 2180424 |  |  | 565 | EX | REPLACE SL W/21-0261272-00 | 2600B | 3RD | 217 W 3RD ST | 161 | MAY | 2022-10-13 | U461478 | U134723 | 2022-04-19 | 2022-12-30 |  |  | DAVID STAGGS | 2022-08-26 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1880.94 | 0 | 0 | 0 | 1880.94 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 08751719000 |  | 100461988 | 05 | X110310 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | COLLEGE HILL | 190 COLLEGE HILL RD | 151 | WAC | 2022-09-12 | U938684 | KSTEEL1 | 2008-09-30 | 2022-06-30 | 2022-12-31 |  | CHARLES COMBS | 2022-08-29 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2370 | 0 | 0 | 0 | 2370 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12981338200 |  | 500061226 |  | W-1008/ |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | KINGPOST | 5800 KINGPOST CT F | 067 | LEX | 2022-09-05 | U125881 | U125208 | 2012-07-23 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-08-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2874.52 | 0 | 0 | 0 | 2874.52 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572270900 |  | 100279890 |  | 6688228J | 2181158 |  |  | 565 | EX | REPLACE SL W/21-0261319-00 | 2600B | LYONS | 159 LYONS DR | 073 | FRA | 2022-08-29 | U128410 | U131066 | 2018-01-04 | 2022-12-30 |  |  | CDESPAIN | 2022-08-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2756.21 | 0 | 0 | 0 | 2756.21 | 0 | 0 | 0
KY | KY - EAST | 2633 | 20026926600 |  |  |  | 7344168K | 2070106 | U128885 |  | 587 | EX | INSTALL NETWORK UPGRADE | 2600M | JARRELL FORK | JARRELL FORK | 071 | LAN | 2022-09-29 | U125936 | U128885 | 2020-02-19 | 2022-12-29 | 2022-12-31 | 2022-08-29 | MRYAN | 2022-08-29 | 2022-08-29 |  | F | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00587 | 3200587 |  |  | WP9266 |  |  | 100 | 058732200269266 | 14.95 | 0 | 6560.17 | 907.35 | 0 | 275.41 | 4500 | 0 | 118.44 | 758.97
KY | KY - CENTRAL | 2629 | 21883085700 |  | 100284587 |  | 6748180L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | COLLEGE HILL | 378 COLLEGE HILL RD | 151 | WAC | 2022-09-12 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-08-29 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2880 | 0 | 0 | 0 | 2880 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883306800 |  | 100284540 |  | 6748180L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | COLLEGE HILL | 304 COLLEGE HILL RD | 151 | WAC | 2022-09-12 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-08-29 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2370 | 0 | 0 | 0 | 2370 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21884179300 |  | 100406956 |  | 6752180A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | COLLEGE HILL | 620 COLLEGE HILL RD | 151 | WAC | 2022-09-12 | U938684 | U128293 | 2021-02-04 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-08-29 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2370 | 0 | 0 | 0 | 2370 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958594800 |  | 100331900 |  | 6720212N | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 170 N ASHLAND AV 1F | 067 | LEX | 2022-08-29 | U129722 | U134723 | 2021-12-08 | 2022-12-30 |  |  | M YOUNG | 2022-08-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1993.6 | 0 | 0 | 0 | 1993.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959035200 |  | 500115934 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | LIMESTONE | 807< S LIMESTONE ST | 067 | LEX | 2022-08-29 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-08-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10 | 1 | 2267.6 | 709.26 | 0 | 170.79 | 1387.55 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960237400 |  | 100321170 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | MAXWELL | 326 E MAXWELL ST 1F | 067 | LEX | 2022-08-29 | U126309 | U134723 | 2021-12-17 | 2022-12-30 |  |  | JAMIE LYNN | 2022-08-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1996.39 | 0 | 0 | 0 | 1996.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026195000 |  |  |  | 6728200F | 2289200 | U122858 |  | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2621M | ATHENS WALNUT | 5540 ATHENS WALNUT PK | 067 | LEX | 2022-09-20 | U125936 | U136124 | 2022-06-01 | 2022-12-30 | 2022-12-31 | 2022-08-29 | AJPARKS | 2022-08-29 |  |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP1950 |  |  | 100 | 090932220261950 | 5 | 0 | 5607.88 | 325.57 | 0 | 89.37 | 5174.3 | 0 | 18.64 | 0
KY | KY - WEST | 2621 | 22026195100 |  |  |  | 6728200F | 2289200 | U122858 |  | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2621M | ATHENS WALNUT | 5540 ATHENS WALNUT PK | 067 | LEX | 2022-09-20 | U125936 | U136124 | 2022-06-01 | 2022-12-30 | 2022-12-31 | 2022-08-29 | AJPARKS | 2022-08-29 |  |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00910 | 3200910 |  |  | WP1951 |  |  | 100 | 091032220261951 | 3 | 0 | 248.95 | 195.35 | 0 | 53.6 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026220400 |  |  |  | 6712228N | 2291102 | U461383 |  | 562 | EX | ABANDON 550' OF 2"PMP MAIN | 2621P | GEORGETOWN | 1175 GEORGETOWN RD | 209 | GEO | 2023-10-27 | U128132 | U461383 | 2022-08-26 | 2022-11-01 | 2022-11-01 | 2022-08-29 | C HERNDON | 2022-08-29 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00562 | 3200562 |  |  | WP2204 |  |  | 100 | 056232220262204 | 0 | 0 | 184.67 | 0 | 184.67 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22125285900 |  | 100251228 |  | 7340268F |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | RIVERSIDE | 1600 RIVERSIDE DR | 089 | GRE | 2022-08-29 | RECUMP | U132002 | 2022-08-19 | 2022-09-02 | 2022-09-18 |  | RECUMP | 2022-08-29 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 11.45 | 3 | 1166.39 | 445.74 | 36.89 | 683.76 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22127315600 |  | 100263752 |  | 7352260O |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2600B | CENTRAL | 310 W CENTRAL AV | 019 | ASH | 2022-08-29 | U125566 | U134723 | 2022-08-29 | 2022-12-30 |  |  | DESKAGG | 2022-08-29 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.8667 | 1 | 2983.21 | 86.92 | 0 | 29.19 | 2867.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127316300 |  | 100331898 |  | 6720212N | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 168 N ASHLAND AV | 067 | LEX | 2022-08-29 | U129722 | U134723 | 2022-08-29 | 2022-12-30 |  |  | M YOUNG | 2022-08-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3034.01 | 0 | 0 | 0 | 3034.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127322000 |  | 501226836 |  | 6712208N |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | SUMMERHAYES | 2013 SUMMERHAYES CT | 067 | LEX | 2022-08-29 | U127206 | U125763 | 2022-08-29 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-08-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 2529.57 | 774.45 | 0 | 46.55 | 1708.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127342300 |  | 500291607 |  | 6720208N |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | COLT NECK | 3504 COLT NECK LN | 067 | LEX | 2022-08-29 | U127206 | U125763 | 2022-08-29 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-08-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1853.07 | 0 | 0 | 0 | 1853.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127342400 |  | 501241453 |  | 6728208I |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | MOON RISE | 1212 MOON RISE WY LT141 | 067 | LEX | 2022-08-29 | U135195 | U125763 | 2022-08-29 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127342500 |  | 100450833 |  | 6724208E |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | PALUMBO | 2555 PALUMBO DR | 067 | LEX | 2022-08-29 | U135195 | U125763 | 2022-08-29 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2231 | 0 | 0 | 0 | 2231 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127342600 |  | 501241459 |  | 6728208I |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | MORNING GLORY | 3941 MORNING GLORY LN | 067 | LEX | 2022-08-29 | U135195 | U125763 | 2022-08-29 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127343500 |  | 100309334 |  | 6712208K |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | HYDE PARK | 3116 HYDE PARK DR | 067 | LEX | 2022-09-01 | U127206 | U125763 | 2022-08-29 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-08-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2048.83 | 0 | 0 | 0 | 2048.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127388700 |  | 100417691 |  | 6720208H |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | HEDGEWOOD | 217 HEDGEWOOD CT | 067 | LEX | 2022-11-04 | U938516 | U125763 | 2022-08-29 | 2022-12-30 |  |  | CHRIS HUNGATE | 2022-08-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127389200 |  | 100413341 |  | 6724208E |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | HEDGEWOOD | 285 HEDGEWOOD CT | 067 | LEX | 2022-11-04 | U938516 | U125763 | 2022-08-29 | 2022-12-30 |  |  | CHRIS HUNGATE | 2022-08-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127398700 |  | 100327445 |  | 6720212M |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | OLD LAFAYETTE | 124 OLD LAFAYETTE AV | 067 | LEX | 2022-08-29 | U127206 | U125763 | 2022-08-29 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-08-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2048.83 | 0 | 0 | 0 | 2048.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127398900 |  | 100327444 |  | 6720212M |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | OLD LAFAYETTE | 124< OLD LAFAYETTE AV | 067 | LEX | 2022-08-29 | U127206 | U125763 | 2022-08-29 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-08-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 321.94 | 0 | 0 | 0 | 321.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127401900 |  | 100468402 |  | 6724208A |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | LOCUST HILL | 115 N LOCUST HILL DR 114 | 067 | LEX | 2022-08-29 | U135195 | U125763 | 2022-08-29 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127403300 |  | 100412158 |  | 6712204C |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | ALDERSHOT | 3478 ALDERSHOT DR | 067 | LEX | 2022-08-29 | U127206 | U125763 | 2022-08-29 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-08-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1708.57 | 0 | 0 | 0 | 1708.57 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129023700 |  | 100284589 |  | 6748180L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | COLLEGE HILL | 430 COLLEGE HILL RD | 151 | WAC | 2022-09-12 | U938684 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHARLES COMBS | 2022-08-29 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2370 | 0 | 0 | 0 | 2370 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129023800 |  | 100284593 |  | 6748180L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | COLLEGE HILL | 490 COLLEGE HILL RD | 151 | WAC | 2022-09-12 | U938684 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHARLES COMBS | 2022-08-29 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1330 | 0 | 0 | 0 | 1330 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979021800 |  | 100255919 |  | 7356256E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HOLT | 2813 HOLT ST | 019 | ASH | 2022-08-29 | U125566 | U128070 | 2022-02-17 | 2022-08-24 | 2022-12-31 |  | DESKAGG | 2022-08-29 | 2022-08-25 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.55 | 2 | 1883.46 | 167.36 | 0 | 56.2 | 1659.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979024400 |  | 100262517 |  | 7352256D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LONG | 617 LONG ST | 019 | ASH | 2022-08-29 | U125566 | U128070 | 2022-02-17 | 2022-08-02 | 2022-12-31 |  | DESKAGG | 2022-08-29 | 2022-08-29 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.65 | 2 | 2000.08 | 182.01 | 0 | 57.57 | 1760.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979025200 |  | 100263977 |  | 7352260N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BELLEFONTE | 720 BELLEFONTE RD | 019 | ASH | 2022-08-29 | U123965 | U128070 | 2022-02-17 | 2022-08-29 | 2022-12-31 |  | MBLANKE | 2022-08-29 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.5333 | 1 | 1988.26 | 137.6 | 0 | 40.7 | 1809.96 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979026600 |  | 100266821 |  | 7356256B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GREENUP | 2429 GREENUP AV | 019 | ASH | 2022-08-29 | U123965 | U128070 | 2022-02-17 | 2022-08-29 | 2022-12-31 |  | MBLANKE | 2022-08-29 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.7 | 1 | 3066.28 | 93.55 | 0 | 27.67 | 2945.06 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979051900 |  | 500290073 |  | 7352260P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WINCHESTER | 601 WINCHESTER AV UNIT 11 | 019 | ASH | 2022-08-29 | U123965 | U128070 | 2022-02-17 | 2022-08-29 | 2022-12-31 |  | MBLANKE | 2022-08-29 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.05 | 1 | 1542.92 | 220.28 | 0 | 65.14 | 1257.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979052000 |  | 500290090 |  | 7352260P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WINCHESTER | 601 WINCHESTER AV UNIT 7 | 019 | ASH | 2022-08-29 | U123965 | U128070 | 2022-02-17 | 2022-08-29 | 2022-12-31 |  | MBLANKE | 2022-08-29 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.083333 | 1 | 1263.13 | 4.35 | 0 | 1.28 | 1257.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 06667778200 |  | 100329522 |  | 6720208C |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SAINT WILLIAM | 145 SAINT WILLIAM DR | 067 | LEX | 2022-08-30 | U127206 | SSUTHER | 2006-12-06 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-08-30 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2330.66 | 0 | 0 | 0 | 2330.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 08735937400 |  | 100334583 |  | 16720208D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | PALUMBO | 2345 PALUMBO DR | 067 | LEX | 2022-08-30 | U135195 | SSUTHER | 2008-06-20 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-08-30 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 3391.07 | 0 | 0 | 0 | 3391.07 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12983765000 |  | 100408605 |  | 6752180M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | FIKE | 5205 FIKE RD | 151 | WAC | 2022-09-12 | U938684 | U908784 | 2012-08-09 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-08-30 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2370 | 0 | 0 | 0 | 2370 | 0 | 0 | 0
KY | KY - WEST | 2621 | 16462435700 |  | 100460715 | 44 | 6716212E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | UPPER | 663< N UPPER ST | 067 | LEX | 2022-08-30 | U135195 | JLYNN | 2016-12-22 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-08-30 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 20803505800 |  | 100282048 |  | 6712232O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | M L KING JR | 353 M L KING JR DR | 209 | GEO | 2022-09-12 | U938684 | U125208 | 2020-04-23 | 2020-05-29 |  |  | CHARLES COMBS | 2022-08-30 | 2020-06-22 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 13.85 | 4 | 4152.72 | 769.18 | 0 | 1013.54 | 2370 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21026146701 |  |  |  | 7320132L | 2290467 | U132280 |  | 559 | EX | INSTALL 100'-2" PMIP | 2600E | COWTOWN | 89 COWTOWN RD | 119 | HIN | 2022-11-14 | U128132 | U132280 | 2022-08-16 | 2022-12-16 | 2022-12-21 | 2022-08-19 | MBLANKE/CJ HUGHES CASEY PACK | 2022-08-30 | 2021-11-10 |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00559 | 3200559 |  |  | WP1467 |  |  | 100 | 055932210261467 | 4.7167 | 101 | 6197.36 | 310.96 | 642.23 | 19.51 | 4349.96 | 0 | 26.06 | 848.64 | 101
KY | KY - CENTRAL | 2629 | 21883109000 |  | 100413004 |  | 6752180F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NEW IRVINE | 4228 NEW IRVINE RD | 151 | WAC | 2022-09-12 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-08-30 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2965.5 | 0 | 0 | 0 | 2965.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883126400 |  | 501094510 |  | 6724212I | 0991247 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | PATCHEN WILKES | 2409 PATCHEN WILKES DR | 067 | LEX | 2022-11-14 | U125881 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-08-30 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2333.69 | 0 | 0 | 0 | 2333.69 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958594700 |  | 501129911 |  | 6720212M | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 164 N ASHLAND AV | 067 | LEX | 2022-08-31 | U129722 | U134723 | 2021-12-08 | 2022-12-30 |  |  | M YOUNG | 2022-08-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2683.91 | 0 | 0 | 0 | 2683.91 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958595600 |  | 100331908 |  | 6720212N | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 196 N ASHLAND AV | 067 | LEX | 2022-08-31 | U129722 | U134723 | 2021-12-08 | 2022-12-30 |  |  | M YOUNG | 2022-08-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3226.33 | 0 | 0 | 0 | 3226.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959034500 |  | 100315071 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | GAZETTE | 127 GAZETTE AV | 067 | LEX | 2022-08-30 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-08-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.0167 | 1 | 2282.3 | 569.54 | 0 | 137.15 | 1575.61 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960237500 |  | 100321173 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | MAXWELL | 404 E MAXWELL ST | 067 | LEX | 2022-08-30 | U461375 | U134723 | 2021-12-17 | 2022-12-30 |  |  | LARRY BROWN | 2022-08-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3129.5 | 0 | 0 | 0 | 3129.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026184000 |  |  |  | 7240212B | 2288553 | U128885 |  | 561 | EX | INSTALL 200'-6"/8" PMLP | 2600B | MAIN | MAIN ST | 173 | MT | 2022-09-14 | U128132 | U128885 | 2022-04-29 | 2022-08-11 | 2022-08-31 | 2022-08-24 | WGRAVES | 2022-08-30 | 2022-07-11 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00561 | 3200561 |  |  | WP1840 | AMRCB |  | 100 | 056132220261840 | 541.4833 | 12470 | 210431.38 | 38690.93 | 20586.29 | 6969.35 | 109309.81 | 0 | 411.71 | 34463.29 | 215
KY | KY - CENTRAL | 2629 | 22026184100 |  |  |  | 7240212B | 2288553 | U128885 |  | 562 | EX | RETIRE 100'-BSLP | 2600B | MAIN | MAIN ST | 173 | MT | 2022-09-13 | U128132 | U128885 | 2022-04-29 | 2022-08-31 | 2022-08-31 | 2022-08-24 | WGRAVES | 2022-08-30 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00562 | 3200562 |  |  | WP1841 | AMRCB |  | 100 | 056232220261841 |  | 0 | 400 | 0 | 0 | 0 | 400 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22026195800 |  |  |  | 7252280M | 2289222 | U122858 |  | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2621M | KY 546 | KY 546 | 161 | MAY | 2022-09-23 | U125936 | U136124 | 2022-06-02 | 2022-12-30 | 2022-12-31 | 2022-08-30 | JMARTIN | 2022-08-30 | 2022-08-30 |  | F | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00909 | 3200909 |  |  | WP1958 |  |  | 100 | 090932220261958 | 5.6 | 0 | 5580.46 | 365.6 | 0 | 21.96 | 5174.3 | 0 | 18.6 | 0
KY | KY - CENTRAL | 2632 | 22026195900 |  |  |  | 7252280M | 2289222 | U122858 |  | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2621M | KY 546 | KY 546 | 161 | MAY | 2022-09-23 | U125936 | U136124 | 2022-06-02 | 2022-12-30 | 2022-12-31 | 2022-08-30 | JMARTIN | 2022-08-30 | 2022-08-30 |  | F | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00910 | 3200910 |  |  | WP1959 |  |  | 100 | 091032220261959 | 1 | 0 | 69.23 | 65.31 | 0 | 3.92 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22123425400 |  | 100257217 |  | 7348264F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D244432 | 2621P | RACELAND | 1004 RACELAND AV | 089 | RAC | 2022-08-30 | MCOLLET | U125208 | 2022-08-11 | 2022-08-12 | 2022-08-31 |  | MCOLLET | 2022-08-30 | 2022-08-25 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 36.4333 | 6 | 14036.08 | 1677.16 | 188.12 | 8479.5 | 3691.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22127406100 |  | 100342863 |  | 7240216N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D253721 | 2621P | HIGH | 112 W HIGH ST | 173 | MT | 2022-08-31 | U125208 | U125208 | 2022-08-29 | 2022-08-29 | 2022-08-29 |  | DENNING | 2022-08-30 | 2022-08-30 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 29.95 | 3 | 3494.08 | 2132.29 | 251.45 | 296.44 | 813.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127695400 |  | 501096894 |  | 6724208C |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2600B | PASCOLI | 2457 PASCOLI PL | 067 | LEX | 2022-11-28 | U938516 | U134723 | 2022-08-30 | 2022-12-30 |  |  | CHRIS HUNGATE | 2022-08-30 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127708100 |  | 500704206 |  | 6728208E |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | POLO CLUB | 3261 POLO CLUB BV | 067 | LEX | 2022-08-30 | U135195 | U125763 | 2022-08-30 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-30 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127708700 |  | 500440636 |  | 6724208A |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | KINGSBURY | 693 KINGSBURY RD | 067 | LEX | 2022-11-14 | U125881 | U125763 | 2022-08-30 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-08-30 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1929.78 | 0 | 0 | 0 | 1929.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127721000 |  | 100326019 |  | 6720208E |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | ROMANY | 344 ROMANY RD | 067 | LEX | 2022-08-30 | U126602 | U125763 | 2022-08-30 | 2022-12-30 |  |  | DEREK PAYTON | 2022-08-30 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 3069.66 | 774.45 | 0 | 46.55 | 2248.66 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22127737400 |  | 500316698 |  | 6740204H |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | PRIMROSE | 110 PRIMROSE LN | 049 | WIN | 2022-09-12 | U938684 | U125763 | 2022-08-30 | 2022-12-30 |  |  | CHARLES COMBS | 2022-08-30 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2370 | 0 | 0 | 0 | 2370 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127894200 |  | 500480336 |  | 6728204O |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | KINGPOST | 5804 KINGPOST CT WHS | 067 | LEX | 2022-11-15 | U125881 | U125763 | 2022-08-31 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-08-30 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 390.22 | 0 | 0 | 0 | 390.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127894400 |  | 100331044 |  | 6720212N |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | PRESTON | 336 PRESTON AV | 067 | LEX | 2022-09-15 | U126602 | U125763 | 2022-08-31 | 2022-12-30 |  |  | DEREK PAYTON | 2022-08-30 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2218.96 | 0 | 0 | 0 | 2218.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129085300 |  | 500530921 |  | 6724208B | 9614946 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | REVERE RUN | 877 REVERE RUN DR | 067 | LEX | 2022-11-28 | U938516 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHRIS HUNGATE | 2022-08-30 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22979035600 |  | 100326890 |  | 6720208A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MCDOWELL | 316 MCDOWELL RD | 067 | LEX | 2022-08-30 | U127206 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | JUSTIN HOBBS | 2022-08-30 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 2189.31 | 774.45 | 0 | 46.55 | 1368.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983426100 |  | 100402257 |  | 6720204B | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 3370 GREENTREE RD | 067 | LEX | 2022-08-31 | U129731 | U134723 | 2022-03-03 | 2022-12-30 |  |  | F.GOINS | 2022-08-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 2355.75 | 0 | 0 | 0 | 2355.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 06639858200 |  | 100459877 | 18 | 6720212B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WITHERS | 120< WITHERS AV | 067 | LEX | 2022-08-31 | RSTRONG | RSTOKLE | 2006-02-28 | 2022-08-31 | 2022-12-31 |  | RSTRONG | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.83333 | 1 | 3010.02 | 55.62 | 0 | 149.91 | 2804.49 | 0 | 0 | 0
KY | KY - WEST | 2621 | 08727635700 |  | 100290780 |  | 16720212B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WITHERS | 109 WITHERS AV | 067 | LEX | 2022-08-31 | RSTRONG | RPOLLY | 2008-04-16 | 2022-08-31 | 2022-12-31 |  | RSTRONG | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.0833 | 1 | 5196.41 | 322.72 | 0 | 870.11 | 4003.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11931682800 |  | 100290758 |  | 6720212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WITHERS | 116 WITHERS AV | 067 | LEX | 2022-08-31 | RSTRONG | U125208 | 2011-11-03 | 2022-08-31 | 2022-12-31 |  | RSTRONG | 2022-08-31 | 2022-07-12 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2 | 2 | 2482.06 | 149.22 | 0 | 154.42 | 2178.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12982935900 |  | 500375388 |  | 16724208E | 9404532 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WOODHILL | 2584 WOODHILL DR | 067 | LEX | 2022-11-28 | U938516 | U125208 | 2012-08-02 | 2022-07-01 | 2022-12-31 |  | CHRIS HUNGATE | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883169100 |  | 100271581 |  | 6736252M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | ODDVILLE | 353 ODDVILLE AV | 097 | CYN | 2022-09-13 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2370 | 0 | 0 | 0 | 2370 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883186600 |  | 100290756 |  | 6720212B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WITHERS | 110 WITHERS AV | 067 | LEX | 2022-08-31 | RSTRONG | U120245 | 2021-01-30 | 2022-08-31 | 2022-12-31 |  | RSTRONG | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.48333 | 1 | 2953.3 | 30.69 | 0 | 82.7 | 2839.91 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883195100 |  | 500375390 |  | 6724208E | 9404532 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WOODHILL | 2576 WOODHILL DR | 067 | LEX | 2022-11-28 | U938516 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHRIS HUNGATE | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883275900 |  | 500117481 |  | 6720212J | 1319261 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NATIONAL | 710 NATIONAL AV | 067 | LEX | 2022-08-31 | U127206 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2674.39 | 0 | 0 | 0 | 2674.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883297500 |  | 500763123 |  | 6712212C | 0145843 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | ENTERPRISE | 1020 ENTERPRISE DR 4 | 067 | LEX | 2022-11-14 | U125881 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1884.19 | 0 | 0 | 0 | 1884.19 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958593900 |  | 100331890 |  | 6720212M | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 142 N ASHLAND AV | 067 | LEX | 2022-09-01 | U129722 | U134723 | 2021-12-08 | 2022-12-30 |  |  | M YOUNG | 2022-08-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2059.3 | 0 | 0 | 0 | 2059.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958594300 |  | 100450074 |  | 6720212M | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 150 N ASHLAND AV 1F | 067 | LEX | 2022-09-01 | U129722 | U134723 | 2021-12-08 | 2022-12-30 |  |  | M YOUNG | 2022-08-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2524.99 | 0 | 0 | 0 | 2524.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959044900 |  | 100315122 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | LIMESTONE | 905 S LIMESTONE ST | 067 | LEX | 2022-08-31 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-08-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2267.23 | 567.4 | 0 | 136.63 | 1563.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960236200 |  | 100321122 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | MAXWELL | 302 E MAXWELL ST | 067 | LEX | 2022-08-31 | U461375 | U134723 | 2021-12-17 | 2022-12-30 |  |  | LARRY BROWN | 2022-08-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3015.4 | 0 | 0 | 0 | 3015.4 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026196700 |  |  |  | 7244216F | 2289270 | U122858 |  | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2621M | EWINGTON | EWINGTON RD | 173 | MT | 2022-09-15 | U125936 | U136124 | 2022-06-03 | 2022-12-30 | 2022-12-31 | 2022-08-31 | WSHIMFESSEL | 2022-08-31 | 2022-08-31 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00909 | 3200909 |  |  | WP1967 |  |  | 100 | 090932220261967 | 2.5 | 0 | 5374.37 | 171.37 | 0 | 10.3 | 5174.3 | 0 | 18.4 | 0
KY | KY - CENTRAL | 2629 | 22026196800 |  |  |  | 7244216F | 2289270 | U122858 |  | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2621M | EWINGTON | EWINGTON RD | 173 | MT | 2022-09-15 | U125936 | U136124 | 2022-06-03 | 2022-12-30 | 2022-12-31 | 2022-08-31 | WSHIMFESSEL | 2022-08-31 |  |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00910 | 3200910 |  |  | WP1968 |  |  | 100 | 091032220261968 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126014800 |  | 100467399 |  | 6720208L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311058 | 2621P | CHIPPENDALE | 204 CHIPPENDALE CR | 067 | LEX | 2022-08-31 | U930915 | U125208 | 2022-08-23 | 2022-08-26 | 2022-09-13 |  | RJCRAWF | 2022-08-31 | 2022-08-25 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 36.1667 | 10 | 4845.48 | 2114.34 | 89.38 | 127.13 | 2514.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126068200 |  | 100423135 |  | 6720208H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D247716 | 2621P | HEDGEWOOD | 173 HEDGEWOOD CT | 067 | LEX | 2022-09-01 | U125208 | U125208 | 2022-08-23 | 2022-08-26 | 2022-09-13 |  | WISHII | 2022-08-31 | 2022-08-29 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 28.4167 | 4 | 4559.32 | 1101.28 | 201.66 | 3239.88 | 16.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127136900 |  | 100310798 |  | 6712204C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311018 | 2621P | LANNETTE | 3453 LANNETTE LN | 067 | LEX | 2022-09-01 | U125208 | U125208 | 2022-08-26 | 2022-08-29 | 2022-09-16 |  | KKINDER | 2022-08-31 | 2022-08-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 22.35 | 6 | 1689.67 | 1052.94 | 492.05 | 63.28 | 81.4 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22127137500 |  | 100285497 |  | 6768172A |  |  |  | 565 | EX | REPLACE SERVICE LINE - D247721 | 2621P | PINE | 105 PINE ST | 065 | IRV | 2022-09-01 | U125208 | U125208 | 2022-08-26 | 2022-08-29 | 2022-09-16 |  | DENNING | 2022-08-31 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 13.8 | 2 | 820.16 | 513.69 | 118.83 | 127.14 | 60.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22127315800 |  | 100241552 |  | 7356256B |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2600B | CARTER | 2229 CARTER AV | 019 | ASH | 2022-08-31 | U123965 | U134723 | 2022-08-29 | 2022-12-30 |  |  | MBLANKE | 2022-08-31 | 2022-08-29 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 14.75 | 3 | 3215.03 | 696.55 | 0 | 230.67 | 2287.81 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22127315900 |  | 100468192 |  | 7356256C |  |  |  | 566 | EX | ABANON SL-I/I/LGCY | 2600B | CARTER | 2765 CARTER AV | 019 | ASH | 2022-08-31 | U123965 | U134723 | 2022-08-29 | 2022-12-30 |  |  | MBLANKE | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.6667 | 1 | 2345.96 | 90.81 | 0 | 26.86 | 2228.29 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22127649200 |  | 100261434 |  | 7352256L |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2600B | BEECH | 1810 BEECH ST | 019 | ASH | 2022-08-31 | U125566 | U134723 | 2022-08-30 | 2022-12-30 |  |  | DESKAGG | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.1833 | 1 | 2056.64 | 146.38 | 0 | 49.16 | 1861.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22127658200 |  | 100267573 |  | 7352260K |  |  |  | 566 | EX | ABND SERVICE LINE | 2600B | BELLEF PRIN | 116 BELLEF PRIN RD | 019 | ASH | 2022-08-31 | U123965 | U125768 | 2022-08-30 | 2049-12-31 |  |  | MBLANKE | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.2833 | 1 | 1246.38 | 69.06 | 0 | 20.42 | 1156.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22127661500 |  | 100263943 |  | 7352260N |  |  |  | 566 | EX | ABND SERVICE LINE | 2600B | HOODS CREEK | 1843 HOODS CREEK PK | 019 | ASH | 2022-08-31 | U123965 | U125768 | 2022-08-30 | 2049-12-31 |  |  | MBLANKE | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.2 | 1 | 1541.84 | 64.16 | 0 | 18.98 | 1458.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127755200 |  | 100467398 |  | 6720208L | 1635077 |  |  | 565 | EX | SL REPLACE | 2621P | CHIPPENDALE | 208 CHIPPENDALE CR | 067 | LEX | 2022-08-31 | U930915 | U136526 | 2022-08-30 | 2022-08-30 |  |  | RJCRAWF | 2022-08-31 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACN |  | 100 | 056532B26210031 | 0 | 1 | 324.85 | 0 | 313.85 | 0 | 11 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127909400 |  | 100323154 |  | 6716208P |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | ALBANY | 775 ALBANY RD | 067 | LEX | 2022-08-31 | U127206 | U125763 | 2022-08-31 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 3423.13 | 774.45 | 0 | 46.55 | 2602.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127911000 |  | 501241447 |  | 6728208I |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | SQUIRREL NEST | 1008 SQUIRREL NEST LN LT55 | 067 | LEX | 2022-11-14 | U125881 | U125763 | 2022-08-31 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127911200 |  | 500834224 |  | 6712212C |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | ENTERPRISE | 1020 ENTERPRISE DR 1 | 067 | LEX | 2022-11-14 | U125881 | U125763 | 2022-08-31 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 22127911300 |  | 500879415 |  | 6712212C |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | ENTERPRISE | 1020 ENTERPRISE DR 2 | 067 | LEX | 2022-11-14 | U125881 | U125763 | 2022-08-31 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 22127911400 |  | 500796645 |  | 16712212C | 0250485 |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | ENTERPRISE | 1020 ENTERPRISE DR 3 | 067 | LEX | 2022-11-14 | U125881 | U125763 | 2022-08-31 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 22127911500 |  | 500825184 |  | 6712212C | 0253777 |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | ENTERPRISE | 1050 ENTERPRISE DR STE 1 | 067 | LEX | 2022-11-14 | U125881 | U125763 | 2022-08-31 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 390.22 | 0 | 0 | 0 | 390.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127917600 |  | 501157262 |  | 6724208N | 1423415 |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | SAWGRASS | 1045 SAWGRASS CV | 067 | LEX | 2022-08-31 | U135195 | U125763 | 2022-08-31 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127917700 |  | 501220357 |  | 6724208N | 1746946 |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | SAWGRASS | 1048 SAWGRASS CV LT89 | 067 | LEX | 2022-08-31 | U135195 | U125763 | 2022-08-31 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127917800 |  | 500573978 |  | 6724208E | 9721496 |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | SMUGGLERS NOTC | 660 SMUGGLERS NOTC DR | 067 | LEX | 2022-11-14 | U125881 | U125763 | 2022-08-31 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127917900 |  | 500350186 |  | 6724208J | 9402450 |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | WAVECREST | 3064 WAVECREST WY | 067 | LEX | 2022-08-31 | U135195 | U125763 | 2022-08-31 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127918200 |  | 500350188 |  | 6724208J | 9402450 |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | WAVECREST | 3072 WAVECREST WY | 067 | LEX | 2022-08-31 | U135195 | U125763 | 2022-08-31 | 2022-12-30 |  |  | KEITH HEDGES | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127932300 |  | 100405381 |  | 6720208H |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | WOODHILL | 2465 WOODHILL DR | 067 | LEX | 2022-11-28 | U938516 | U125763 | 2022-08-31 | 2022-12-30 |  |  | CHRIS HUNGATE | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127963300 |  | 100325950 |  | 6720208A |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | CASSIDY | 207 CASSIDY AV | 067 | LEX | 2022-09-15 | U126602 | U125763 | 2022-08-31 | 2022-12-30 |  |  | DEREK PAYTON | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 3039.96 | 774.45 | 0 | 46.55 | 2218.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127963800 |  | 100321343 |  | 6716212P |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | KENTUCKY | 249 KENTUCKY AV | 067 | LEX | 2022-09-15 | U126602 | U125763 | 2022-08-31 | 2022-12-30 |  |  | DEREK PAYTON | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2248.66 | 0 | 0 | 0 | 2248.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22128397000 |  | 100329725 |  | 6720208D |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | SAINT MICHAEL | 2012 SAINT MICHAEL DR | 067 | LEX | 2022-09-28 | U126602 | U125763 | 2022-09-01 | 2022-12-30 |  |  | DEREK PAYTON | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1368.31 | 0 | 0 | 0 | 1368.31 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22130713100 |  | 500508650 |  | 6748180L |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | COLLEGE HILL | 401 COLLEGE HILL RD | 151 | WAC | 2022-09-12 | U938684 | U125763 | 2022-09-12 | 2022-12-30 |  |  | CHARLES COMBS | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2370 | 0 | 0 | 0 | 2370 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964244600 |  | 100347945 |  | 6748208I | 2075093 |  |  | 565 | EX | REPLACE SL W/20-0269804-00 | 2600B | SYCAMORE | 108 SYCAMORE ST | 049 | WIN | 2022-08-31 | U126603 | U134723 | 2022-01-06 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-08-31 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4277.67 | 0 | 0 | 0 | 4277.67 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22970119800 |  | 100279883 |  | 6684228N | 2181158 |  |  | 565 | EX | REPLACE SL W/21-0261319-00 | 2600B | LYONS | 135 LYONS DR | 073 | FRA | 2022-08-31 | U128410 | U134723 | 2022-01-27 | 2022-12-30 |  |  | CDESPAIN | 2022-08-31 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3745.9 | 0 | 0 | 0 | 3745.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979026800 |  | 100267173 |  | 7352260M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DOYLE | 2626 DOYLE ST | 019 | ASH | 2022-08-31 | U123965 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | MBLANKE | 2022-08-31 | 2022-08-30 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.25 | 2 | 2650.44 | 182.16 | 0 | 53.88 | 2414.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22979040300 |  | 100346304 |  | 6696212L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | BELL | 111 BELL CT | 239 | VER | 2022-09-12 | U938684 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | CHARLES COMBS | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 2370 | 0 | 0 | 0 | 2370 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979051800 |  | 500252103 |  | 6736248B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ROBYNWOOD | 201 ROBYNWOOD DR OFFICE | 097 | CYN | 2022-09-12 | U938684 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | CHARLES COMBS | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2370 | 0 | 0 | 0 | 2370 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979052200 |  | 500334360 |  | 6732252P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 4TH | 211 4TH ST | 097 | CYN | 2022-09-12 | U938684 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | CHARLES COMBS | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2370 | 0 | 0 | 0 | 2370 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979052500 |  | 500383672 |  | 6732252N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RAINTREE | 225 RAINTREE DR | 097 | CYN | 2022-09-13 | U938684 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | CHARLES COMBS | 2022-08-31 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2370 | 0 | 0 | 0 | 2370 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979054200 |  | 500612608 |  | 7352256P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RANDY | 3340 RANDY DR | 019 | ASH | 2022-08-31 | U123965 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | MBLANKE | 2022-08-31 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.1 | 1 | 1737.4 | 59.81 | 0 | 17.69 | 1659.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983425000 |  | 100404293 |  | 6720204B | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 3374 GREENTREE CR | 067 | LEX | 2022-08-31 | U129731 | U134723 | 2022-03-03 | 2022-12-30 |  |  | F.GOINS | 2022-08-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 1586.48 | 0 | 0 | 0 | 1586.48 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22994322700 |  | 100353497 |  | 7256280K | 2180424 |  |  | 565 | EX | REPLACE SL W/21-0261272-00 | 2600B | 3RD | 205 W 3RD ST | 161 | MAY | 2022-10-13 | U461478 | U134723 | 2022-04-19 | 2022-12-30 |  |  | DAVID STAGGS | 2022-08-31 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2049.87 | 0 | 0 | 0 | 2049.87 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22994323200 |  | 100353566 |  | 7256280K | 2180424 |  |  | 565 | EX | REPLACE SL W/21-0261272-00 | 2600B | 3RD | 228 W 3RD ST | 161 | MAY | 2022-09-06 | U461478 | U134723 | 2022-04-19 | 2022-12-30 |  |  | DAVID STAGGS | 2022-08-31 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 3586.36 | 0 | 0 | 0 | 3586.36 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21026138900 |  | 501314395 |  | 6712228L | 2182306 | U126783 |  | 555 | EX | INSTALL 650'-6" PMMP | 2600B | KADEN | 111 KADEN LN | 209 | GEO | 2022-11-04 | U128132 | U126783 | 2021-08-31 | 2022-08-18 | 2022-09-23 | 2022-08-30 | KKOUNS | 2022-09-01 | 2022-07-21 | 2022-07-21 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP1389 |  |  | 100 | 055532210261389 | 338.9833 | 27000 | 111751.03 | 23390.68 | 6829.27 | 4740.95 | 59195.86 | 0 | 237.46 | 17356.81 | 675
KY | KY - WEST | 2621 | 21883291000 |  | 100335461 |  | 6716220J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | GEORGETOWN | 3401 GEORGETOWN RD | 067 | LEX | 2022-10-21 | U125881 | U120245 | 2021-01-30 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-01 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 390.22 | 0 | 0 | 0 | 390.22 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21942497400 |  | 100353569 |  | 7256280K | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2632D | 3RD | 224 W 3RD ST | 161 | MAY | 2022-09-06 | U461478 | AOC SYST | 2021-09-27 | 2022-12-31 | 2022-12-31 |  | DAVID STAGGS | 2022-09-01 |  |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26320031 |  | 1 | 4251.18 | 0 | 0 | 0 | 4251.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958594900 |  | 100331902 |  | 6720212N | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 176 N ASHLAND AV | 067 | LEX | 2022-09-06 | U129722 | U134723 | 2021-12-08 | 2022-12-30 |  |  | M YOUNG | 2022-09-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1843.37 | 0 | 0 | 0 | 1843.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958628200 |  | 100331901 |  | 6720212N | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 172 N ASHLAND AV | 067 | LEX | 2022-09-06 | U129722 | U134723 | 2021-12-08 | 2022-12-30 |  |  | M YOUNG | 2022-09-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2130.13 | 0 | 0 | 0 | 2130.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959043700 |  | 100415008 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | GAZETTE | 159 GAZETTE AV | 067 | LEX | 2022-09-01 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-09-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.5 | 1 | 2766.13 | 738.51 | 0 | 150.74 | 1876.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960236400 |  | 100321123 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | MAXWELL | 304 E MAXWELL ST 1F | 067 | LEX | 2022-10-12 | U461375 | U134723 | 2021-12-17 | 2022-12-30 |  |  | LARRY BROWN | 2022-09-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2647.97 | 0 | 0 | 0 | 2647.97 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026195600 |  |  |  | 6700224O | 2289218 | U122858 |  | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2621M | VERSAILLES | 510 VERSAILLES RD | 239 | MID | 2022-10-06 | U462463 | U136124 | 2022-06-02 | 2022-12-30 | 2022-12-31 | 2022-08-23 | B.LONE | 2022-09-01 | 2022-08-22 |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00909 | 3200909 |  |  | WP1956 |  |  | 100 | 090932220261956 | 2.9333 | 0 | 5406.36 | 201.54 | 0 | 12.1 | 5174.3 | 0 | 18.42 | 0
KY | KY - WEST | 2623 | 22026195700 |  |  |  | 6700224O | 2289218 | U122858 |  | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2621M | VERSAILLES | 510 VERSAILLES RD | 239 | MID | 2022-10-06 | U462463 | U136124 | 2022-06-02 | 2022-12-30 | 2022-12-31 | 2022-08-23 | B. LONE | 2022-09-01 | 2022-08-23 |  | F | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00910 | 3200910 |  |  | WP1957 |  |  | 100 | 091032220261957 | 5.3333 | 0 | 381.79 | 360.15 | 0 | 21.64 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026199300 |  |  |  | 6684228D | 2289338 | U122858 |  | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2621M | GREAT BUFFALO | 113 GREAT BUFFALO TC | 073 | FRA | 2022-09-19 | U125936 | U136124 | 2022-06-07 | 2022-12-30 | 2022-12-31 | 2022-09-01 | GHALE | 2022-09-01 | 2022-09-01 |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00909 | 3200909 |  |  | WP1993 |  |  | 100 | 090932220261993 | 1.0333 | 0 | 5269.21 | 64.31 | 0 | 3.59 | 5174.3 | 0 | 27.01 | 0
KY | KY - WEST | 2623 | 22026199400 |  |  |  | 6684228D | 2289338 | U122858 |  | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2621M | GREAT BUFFALO | 113 GREAT BUFFALO TC | 073 | FRA | 2022-09-19 | U125936 | U136124 | 2022-06-07 | 2022-12-30 | 2022-12-31 | 2022-09-01 | GHALE | 2022-09-01 | 2022-09-01 |  | F | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00910 | 3200910 |  |  | WP1994 |  |  | 100 | 091032220261994 | 2.55 | 0 | 169.77 | 160.79 | 0 | 8.98 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026219700 |  |  |  | 6736228C | 2290976 | U461383 |  | 557 | EX | EMER-INSTALL 8" STOPPLE FITS | 2600B | PARIS BY PASS | PARIS BY PASS RD | 017 | PAR | 2022-09-14 | U128132 | U461383 | 2022-08-22 | 2022-09-12 | 2022-09-15 | 2022-08-31 | ED FOX | 2022-09-01 | 2022-08-29 | 2022-08-29 | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP2197 |  |  | 100 | 055732220262197 | 97.6667 | 0 | 39002.9 | 10063.21 | 3995.27 | 1677.38 | 17035.01 | 0 | 19.78 | 6212.25
KY | KY - CENTRAL | 2629 | 22026219800 |  |  |  | 6736228C | 2290976 | U461383 |  | 558 | EX | EMER-RETIRE 1' OF 8"CSHP MAIN | 2600B | PARIS BY PASS | PARIS BY PASS RD | 017 | PAR | 2022-09-14 | U128132 | U461383 | 2022-08-22 | 2022-09-15 | 2022-09-15 | 2022-08-31 | ED FOX | 2022-09-01 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP2198 |  |  | 100 | 055832220262198 |  | 0 | 160 | 0 | 0 | 0 | 160 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22109774200 |  | 500891641 |  | 6728208M | 0461824 |  |  | 566 | EX | ABANDON SL | 2621P | SPYGLASS | 791 SPYGLASS LN CABLE | 067 | LEX | 2022-09-28 | U135195 | U132625 | 2022-06-14 | 2022-06-14 |  |  | KEITH HEDGES | 2022-09-01 | 2022-06-16 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.86667 | 1 | 3011.07 | 48.52 | 0 | 127.3 | 2835.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22111560000 |  | 100347709 |  | 6744208L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MADISON | 11 MADISON AV | 049 | WIN | 2022-09-01 | U930915 | U125208 | 2022-06-21 | 2023-09-29 | 2023-12-31 |  | NRICHIE | 2022-09-01 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10.7667 | 2 | 1381.42 | 748.37 | 13.59 | 327.54 | 291.92 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22121479800 |  | 100359292 |  | 6740232M | 2075121 |  |  | 565 | VO | RPLC SL/20026980600 | 2600B | PINECREST | 150 PINECREST ST 7 | 017 | PAR | 2022-09-07 |  | U125763 | 2022-08-04 | 2022-12-30 |  |  | LYN STAFFORD | 2022-09-01 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1
KY | KY - EAST | 2631 | 22127648800 |  | 100248160 |  | 7352260N |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2600B | MAIN | 2418 MAIN ST | 019 | ASH | 2022-09-01 | U123965 | U134723 | 2022-08-30 | 2022-12-30 |  |  | MBLANKE | 2022-09-01 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.9 | 1 | 1648.41 | 153.24 | 0 | 36.47 | 1458.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22127658100 |  | 100246958 |  | 7352252D |  |  |  | 566 | EX | ABND SERVICE LINE | 2600B | BOY SCOUT | 2925 BOY SCOUT RD | 019 | ASH | 2022-09-01 | U123965 | U125768 | 2022-08-30 | 2049-12-31 |  |  | MBLANKE | 2022-09-01 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.2333 | 1 | 2612.17 | 220.71 | 0 | 52.51 | 2338.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22128372300 |  | 100298779 |  | 6716216O |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | CRANBERRY | 301 CRANBERRY ST | 067 | LEX | 2022-09-01 | U135195 | U125763 | 2022-09-01 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22128372600 |  | 100298835 |  | 6716216O |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | EMBASSY | 233 EMBASSY DR | 067 | LEX | 2022-09-01 | U135195 | U125763 | 2022-09-01 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1836.7 | 0 | 0 | 0 | 1836.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22128372800 |  | 100296107 |  | 6716216O |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | ERIE | 459 ERIE RD | 067 | LEX | 2022-11-04 | U938516 | U125763 | 2022-09-01 | 2022-12-30 |  |  | CHRIS HUNGATE | 2022-09-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22128377700 |  | 100263782 |  | 7352260O |  |  |  | 566 | EX | ABND SERVICE LINE | 2600B | LAUREL | 370 LAUREL AV | 019 | ASH | 2022-09-01 | U123965 | U125768 | 2022-09-01 | 2049-12-31 |  |  | MBLANKE | 2022-09-01 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.85 | 1 | 2091.15 | 44.47 | 0 | 10.58 | 2036.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22128381300 |  | 100314193 |  | 6716212L |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | BROADWAY | 305 BROADWAY PR SO | 067 | LEX | 2022-09-01 | U127206 | U125763 | 2022-09-01 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 2247.11 | 602.79 | 0 | 33.63 | 1610.69 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22128396900 |  | 501050797 |  | 6720212N |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | SHERMAN | 211 SHERMAN AV | 067 | LEX | 2022-09-15 | U126602 | U125763 | 2022-09-01 | 2022-12-30 |  |  | DEREK PAYTON | 2022-09-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 2844.98 | 592.94 | 0 | 33.08 | 2218.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22128397100 |  | 100335400 |  | 6716216K |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | GEORGETOWN | 1401 GEORGETOWN RD | 067 | LEX | 2022-10-21 | U125881 | U125763 | 2022-09-01 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1868.17 | 0 | 0 | 0 | 1868.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22128397200 |  | 100299101 |  | 6716212B |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | FORBES | 1434 N FORBES RD | 067 | LEX | 2022-10-21 | U125881 | U125763 | 2022-09-01 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2218.44 | 0 | 0 | 0 | 2218.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22128397300 |  | 100298962 |  | 6716212B |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | FORBES | 1435 N FORBES RD 4 | 067 | LEX | 2022-10-21 | U125881 | U125763 | 2022-09-01 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22128397400 |  | 100298958 |  | 6716212B |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | FORBES | 1435 N FORBES RD 8 | 067 | LEX | 2022-10-21 | U125881 | U125763 | 2022-09-01 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1431.41 | 0 | 0 | 0 | 1431.41 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22128398400 |  | 100314179 |  | 6716212O |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | BROADWAY | 340 BROADWAY PR SO | 067 | LEX | 2022-09-01 | U127206 | U125763 | 2022-09-01 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1610.69 | 0 | 0 | 0 | 1610.69 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22128474400 |  | 100298703 |  | 6716212C |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | CANTALOUPE | 102 CANTALOUPE ST | 067 | LEX | 2022-11-04 | U938516 | U125763 | 2022-09-01 | 2022-12-30 |  |  | CHRIS HUNGATE | 2022-09-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22128482500 |  | 100309166 |  | 6716208A |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | HARRODSBURG | 1999 HARRODSBURG RD | 067 | LEX | 2022-09-06 | U127206 | U125763 | 2022-09-01 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1731.88 | 0 | 0 | 0 | 1731.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22128552600 |  | 100332022 |  | 6720212N |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | WALTON | 214 WALTON AV B | 067 | LEX | 2022-09-28 | U126602 | U125763 | 2022-09-01 | 2022-12-30 |  |  | DEREK PAYTON | 2022-09-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2960.02 | 0 | 0 | 0 | 2960.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22128557100 |  | 100335499 |  | 6716220A |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | GEORGETOWN | 4130 GEORGETOWN RD I4 | 067 | LEX | 2022-10-21 | U125881 | U125763 | 2022-09-01 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22128778900 |  | 100269177 |  | 6736252M |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2600B | CHURCH | 206 N CHURCH ST | 097 | CYN | 2022-09-13 | U938684 | U134723 | 2022-09-02 | 2022-12-30 |  |  | CHARLES COMBS | 2022-09-01 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2370 | 0 | 0 | 0 | 2370 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22970119200 |  | 100279878 |  | 6684228N | 2181158 |  |  | 565 | EX | REPLACE SL W/21-0261319-00 | 2600B | LYONS | 119 LYONS DR | 073 | FRA | 2022-09-01 | U126285 | U134723 | 2022-01-27 | 2022-12-30 |  |  | DDAVIS | 2022-09-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 10 | 1 | 4319.16 | 631.78 | 0 | 565.44 | 3121.94 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979050800 |  | 500144605 |  | 6732252N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MASON | 111 MASON LN | 097 | CYN | 2022-09-13 | U938684 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | CHARLES COMBS | 2022-09-01 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2370 | 0 | 0 | 0 | 2370 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979054900 |  | 500696309 |  | 7352252C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BOY SCOUT | 3058 BOY SCOUT RD | 019 | ASH | 2022-09-01 | U123965 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | MBLANKE | 2022-09-01 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.0167 | 1 | 2468.44 | 104.6 | 0 | 24.89 | 2338.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983425100 |  | 100404292 |  | 6720204B | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 3378 GREENTREE CR | 067 | LEX | 2022-09-01 | U129731 | U134723 | 2022-03-03 | 2022-12-30 |  |  | F.GOINS | 2022-09-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1093.14 | 0 | 0 | 0 | 1093.14 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883209100 |  | 100334260 |  | 6720212P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LAKEVIEW | 721 LAKEVIEW DR | 067 | LEX | 2022-09-02 | LSTONE | U120245 | 2021-01-30 | 2022-09-02 | 2022-12-31 |  | LSTONE | 2022-09-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.3667 | 2 | 2138.75 | 634.22 | 0 | 35.4 | 1469.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21912568000 |  | 100447028 |  | 6720216N |  |  |  | 566 | EX | ABANDON W/100447029-100447030 | 2621P | HOLLOW CREEK | 500 HOLLOW CREEK RD 44 | 067 | LEX | 2022-09-05 | U125881 | U125208 | 2021-05-19 | 2021-07-19 | 2021-07-19 |  | HERBERT HAYDEN | 2022-09-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1176.73 | 0 | 0 | 0 | 1176.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21912568200 |  | 100447029 |  | 6720216N |  |  |  | 566 | EX | ABANDON W/100447028-100447030 | 2621P | HOLLOW CREEK | 500 HOLLOW CREEK RD 46 | 067 | LEX | 2022-09-05 | U125881 | U125208 | 2021-05-19 | 2021-07-19 | 2021-07-19 |  | HERBERT HAYDEN | 2022-09-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 21912568400 |  | 100447030 |  | 6720216N |  |  |  | 566 | EX | ABANDON W/100447028-100447029 | 2621P | HOLLOW CREEK | 500 HOLLOW CREEK RD 48 | 067 | LEX | 2022-09-05 | U125881 | U125208 | 2021-05-19 | 2021-07-19 | 2021-07-19 |  | HERBERT HAYDEN | 2022-09-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 21912568700 |  | 100446945 |  | 6720216N |  |  |  | 566 | EX | ABANDON W/100447048-100446944 | 2621P | HOLLOW CREEK | 500 HOLLOW CREEK RD 45 | 067 | LEX | 2022-09-05 | U125881 | U125208 | 2021-05-19 | 2021-07-19 | 2021-07-19 |  | HERBERT HAYDEN | 2022-09-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1176.73 | 0 | 0 | 0 | 1176.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21912568800 |  | 100447048 |  | 6720216N |  |  |  | 566 | EX | ABANDON W/100446945-100446944 | 2621P | HOLLOW CREEK | 500 HOLLOW CREEK RD 43 | 067 | LEX | 2022-09-05 | U125881 | U125208 | 2021-05-19 | 2021-07-19 | 2021-07-19 |  | HERBERT HAYDEN | 2022-09-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 21912568900 |  | 100446944 |  | 6720216N |  |  |  | 566 | EX | ABANDON W/100446945-100447048 | 2621P | HOLLOW CREEK | 500 HOLLOW CREEK RD 47 | 067 | LEX | 2022-09-05 | U125881 | U125208 | 2021-05-19 | 2021-07-19 | 2021-07-19 |  | HERBERT HAYDEN | 2022-09-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 21912569100 |  | 100447026 |  | 6720216N |  |  |  | 566 | EX | ABANDON W/100447027-100447948 | 2621P | HOLLOW CREEK | 500 HOLLOW CREEK RD 53 | 067 | LEX | 2022-09-05 | U125881 | U125208 | 2021-05-19 | 2021-07-19 | 2021-07-19 |  | HERBERT HAYDEN | 2022-09-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1176.73 | 0 | 0 | 0 | 1176.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21912569200 |  | 100447027 |  | 6720216N |  |  |  | 566 | EX | ABANDON W/100447026-100447948 | 2621P | HOLLOW CREEK | 500 HOLLOW CREEK RD 49 | 067 | LEX | 2022-09-05 | U125881 | U125208 | 2021-05-19 | 2021-07-19 | 2021-07-19 |  | HERBERT HAYDEN | 2022-09-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 21912569500 |  | 100447948 |  | 6720216N |  |  |  | 566 | EX | ABANDON W/100447027-100447026* | 2621P | HOLLOW CREEK | 500 HOLLOW CREEK RD 51 | 067 | LEX | 2022-09-05 | U125881 | U125208 | 2021-05-19 | 2021-07-19 | 2021-07-19 |  | HERBERT HAYDEN | 2022-09-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 21912569600 |  | 100446941 |  | 6720216N |  |  |  | 566 | EX | ABANDON W/100467891-100446943 | 2621P | HOLLOW CREEK | 500 HOLLOW CREEK RD 50 | 067 | LEX | 2022-10-28 | U125881 | U125208 | 2021-05-19 | 2021-07-19 | 2021-07-19 |  | HERBERT HAYDEN | 2022-09-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1176.73 | 0 | 0 | 0 | 1176.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21912569700 |  | 100467891 |  | 6720216N |  |  |  | 566 | EX | ABANDON W/100446941-100446943 | 2621P | HOLLOW CREEK | 500 HOLLOW CREEK RD 52 | 067 | LEX | 2022-09-05 | U125881 | U125208 | 2021-05-19 | 2021-07-19 | 2021-07-19 |  | HERBERT HAYDEN | 2022-09-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 21912569900 |  | 100446943 |  | 6720216N |  |  |  | 566 | EX | ABANDON W/100446941-100467891 | 2621P | HOLLOW CREEK | 500 HOLLOW CREEK RD 54 | 067 | LEX | 2022-10-28 | U125881 | U125208 | 2021-05-19 | 2021-07-19 | 2021-07-19 |  | HERBERT HAYDEN | 2022-09-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 21912570100 |  | 100446938 |  | 6720216N |  |  |  | 566 | EX | ABANDON W/100446940 | 2621P | HOLLOW CREEK | 500 HOLLOW CREEK RD 59 | 067 | LEX | 2022-09-05 | U125881 | U125208 | 2021-05-19 | 2021-07-19 | 2021-07-19 |  | HERBERT HAYDEN | 2022-09-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1176.73 | 0 | 0 | 0 | 1176.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21912570200 |  | 100446940 |  | 6720216N |  |  |  | 566 | EX | ABANDON W/100446938 | 2621P | HOLLOW CREEK | 500 HOLLOW CREEK RD 55 | 067 | LEX | 2022-09-05 | U125881 | U125208 | 2021-05-19 | 2021-07-19 | 2021-07-19 |  | HERBERT HAYDEN | 2022-09-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 21912570300 |  | 100446937 |  | 6720216N |  |  |  | 566 | EX | ABANDON 56-57-58-60 | 2621P | HOLLOW CREEK | 500 HOLLOW CREEK RD 56 | 067 | LEX | 2022-09-05 | U125881 | U125208 | 2021-05-19 | 2021-07-19 | 2021-07-19 |  | HERBERT HAYDEN | 2022-09-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1176.73 | 0 | 0 | 0 | 1176.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21912570400 |  | 100446963 |  | 6720216N |  |  |  | 566 | EX | ABANDON 56-57-58-60 | 2621P | HOLLOW CREEK | 500 HOLLOW CREEK RD 58 | 067 | LEX | 2022-09-05 | U125881 | U125208 | 2021-05-19 | 2021-07-19 | 2021-07-19 |  | HERBERT HAYDEN | 2022-09-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 21912570500 |  | 100446801 |  | 6720216N |  |  |  | 566 | EX | ABANDON 56-57-58-60 | 2621P | HOLLOW CREEK | 500 HOLLOW CREEK RD 60 | 067 | LEX | 2022-09-05 | U125881 | U125208 | 2021-05-19 | 2021-07-19 | 2021-07-19 |  | HERBERT HAYDEN | 2022-09-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 21912570600 |  | 100446939 |  | 6720216N |  |  |  | 566 | EX | ABANDON 56-57-58-60 | 2621P | HOLLOW CREEK | 500 HOLLOW CREEK RD 57 | 067 | LEX | 2022-09-05 | U125881 | U125208 | 2021-05-19 | 2021-07-19 | 2021-07-19 |  | HERBERT HAYDEN | 2022-09-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 22026199100 |  |  |  | 6716216P | 2289337 | U122858 |  | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2621M | NEWTOWN | 800 NEWTOWN CT | 067 | LEX | 2022-09-16 | U125936 | U136124 | 2022-06-07 | 2022-12-30 | 2022-12-31 | 2022-09-02 | EBLANTON | 2022-09-02 | 2022-09-02 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP1991 |  |  | 100 | 090932220261991 | 4 | 0 | 5602.7 | 288.47 | 0 | 112.6 | 5174.3 | 0 | 27.33 | 0
KY | KY - WEST | 2621 | 22026199200 |  |  |  | 6716216P | 2289337 | U122858 |  | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2621M | NEWTOWN | 800 NEWTOWN CT | 067 | LEX | 2022-09-16 | U125936 | U136124 | 2022-06-07 | 2022-12-30 | 2022-12-31 | 2022-09-02 | EBLANTON | 2022-09-02 | 2022-09-02 |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00910 | 3200910 |  |  | WP1992 |  |  | 100 | 091032220261992 | 8.5833 | 0 | 880.44 | 620.48 | 0 | 259.96 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127918000 |  | 100334671 |  | 6724208E |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | WILDERNESS | 522 WILDERNESS RD | 067 | LEX | 2022-11-04 | U938516 | U125763 | 2022-08-31 | 2022-12-30 |  |  | CHRIS HUNGATE | 2022-09-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1868.17 | 0 | 0 | 0 | 1868.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22128821200 |  | 501192623 |  | 6728208B |  |  |  | 566 | EX | ABANDON | 2600B | TRANQUILITY | 3574 TRANQUILITY PT | 067 | LEX | 2022-11-03 | U938516 | U124960 | 2022-09-02 | 2049-12-31 |  |  | CHRIS HUNGATE | 2022-09-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1402.64 | 0 | 0 | 0 | 1402.64 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22128835000 |  | 100278614 |  | 6688232O |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | TATATO | 434 TATATO TL | 073 | FRA | 2022-09-02 | DCOLLIN | U134852 | 2022-09-02 | 2022-09-02 |  |  | DCOLLIN | 2022-09-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.3333 | 1 | 2322.48 | 292.52 | 231.71 | 32.75 | 1765.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22128846500 |  | 500654241 |  | 6712208B |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2600B | ALLEGHENY | 2036 ALLEGHENY WY | 067 | LEX | 2022-09-02 | U135195 | U125768 | 2022-09-02 | 2049-12-31 |  |  | KEITH HEDGES | 2022-09-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22128846600 |  | 500654174 |  | 6712208C |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2600B | ALLEGHENY | 2068 ALLEGHENY WY | 067 | LEX | 2022-09-02 | U135195 | U125768 | 2022-09-02 | 2049-12-31 |  |  | KEITH HEDGES | 2022-09-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22128846700 |  | 500939507 |  | 6712208G |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2600B | BEAUMONT CENTR | 3317 BEAUMONT CENTR CI | 067 | LEX | 2022-09-02 | U135195 | U125768 | 2022-09-02 | 2049-12-31 |  |  | KEITH HEDGES | 2022-09-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22128846800 |  | 500939513 |  | 6712208G |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2600B | BEAUMONT CENTR | 3329 BEAUMONT CENTR CI | 067 | LEX | 2022-09-02 | U135195 | U125768 | 2022-09-02 | 2049-12-31 |  |  | KEITH HEDGES | 2022-09-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 05626828300 |  | 100442964 |  | 6732212N | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WINCHESTER | 4822< WINCHESTER RD FG 70 | 067 | LEX | 2022-09-06 | U135195 | SSUTHER | 2005-10-24 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 06644226900 |  | 500220817 |  | 6708212M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NEW VINE | 4349 NEW VINE LN | 067 | LEX | 2022-09-06 | U125881 | SSUTHER | 2006-04-10 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1972.24 | 0 | 0 | 0 | 1972.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07698111300 |  | 100309073 |  | 6716212M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | DELLA | 820 DELLA DR | 067 | LEX | 2022-09-06 | U127206 | DMCCULL | 2007-08-10 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 4418.31 | 0 | 0 | 0 | 4418.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11911888100 |  | 100320379 |  | 6716208G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | NICHOLASVILLE | 1626 NICHOLASVILLE RD | 067 | LEX | 2022-09-06 | U129731 | U906631 | 2011-06-16 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-09-06 | 2020-09-03 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.2167 | 1 | 1937.65 | 137.09 | 0 | 91.99 | 1708.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11926489700 |  | 100303991 |  | 16712208D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | JASMINE | 2136 JASMINE DR | 067 | LEX | 2022-09-06 | U127206 | U125208 | 2011-09-27 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 3347.83 | 0 | 0 | 0 | 3347.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 16418834700 |  | 500445712 |  | 6716212D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NEWTOWN | 501 NEWTOWN PK | 067 | LEX | 2022-09-06 | HMCKUNE | U122906 | 2016-06-17 | 2022-07-01 | 2022-12-31 |  | HMCKUNE | 2022-09-06 | 2022-09-06 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.5 | 3 | 197.35 | 186.91 | 0 | 10.44 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 20026977500 |  |  |  | 7356256O | 2074825 | U938437 |  | 557 | EX | INSTALL 4335'-4" & 6" PMLP | 2600B | FREDERICK | FREDERICK | 019 | ASH | 2022-10-13 | U128132 | U122858 | 2020-09-29 | 2022-09-06 | 2022-12-31 | 2022-06-14 | ORA SLONE | 2022-09-06 | 2022-04-12 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP9775 | AMRCB |  | 100 | 055732200269775 | 534.65 | 56210 | 1014309.73 | 31499.13 | 54376.72 | 6971.68 | 764644.06 | 0 | 2428.96 | 154389.18 | 1022
KY | KY - EAST | 2631 | 20026977600 |  |  |  | 7356256O | 2074825 | U938437 |  | 558 | EX | RETIRE 4766'-2"/3"/4"/6" BSLP | 2600B | FREDERICK | FREDERICK | 019 | ASH | 2022-10-13 | U128132 | U122858 | 2020-09-29 | 2022-12-30 | 2022-12-31 | 2022-09-01 | ORA SLONE | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP9776 | AMRCB |  | 100 | 055832200269776 | 0.86667 | 0 | 11052.89 | 262.79 | 0 | 24.13 | 10765.97 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883051600 |  | 100242995 |  | 356256O | 2074825 |  |  | 566 | EX | ABANDON SL W/20-0269775-00 | 2600B | BLACKBURN | 5251 BLACKBURN AV | 019 | ASH | 2022-09-06 | U124015 | U120245 | 2021-01-30 | 2022-12-30 |  |  | ORA SLONE | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 |  | 1
KY | KY - CENTRAL | 2629 | 21883077800 |  | 100341675 |  | 7240216O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | HIGH | 213 E HIGH ST | 173 | MT | 2022-12-28 | U132761 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DENNING | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.3333 | 2 | 134.24 | 93.5 | 0 | 40.74 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883121400 |  | 100301440 |  | 6712212H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SUTTON | 116 SUTTON PL | 067 | LEX | 2022-09-06 | U129731 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 3667.67 | 0 | 0 | 0 | 3667.67 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883127000 |  | 100242983 |  | 356256O | 2074825 |  |  | 566 | EX | ABANDON SL W/20-0269775-00 | 2600B | BLACKBURN | 5113 BLACKBURN AV | 019 | ASH | 2022-09-06 | U124015 | U120245 | 2021-01-30 | 2022-12-30 |  |  | ORA SLONE | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 |  | 1
KY | KY - WEST | 2621 | 21883135800 |  | 100449224 |  | 6724212K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WINCHESTER | 2575 WINCHESTER RD | 067 | LEX | 2022-09-06 | U125881 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883145600 |  | 100242994 |  | 7356256O | 2074825 |  |  | 566 | EX | ABANDON SL W/20-0269775-00 | 2600B | BLACKBURN | 5235 BLACKBURN AV | 019 | ASH | 2022-09-06 | U124015 | U120245 | 2021-01-30 | 2022-12-30 |  |  | ORA SLONE | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 |  | 1
KY | KY - WEST | 2621 | 21883173100 |  | 100323979 |  | 6732212N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WINCHESTER | 4937 WINCHESTER RD | 067 | LEX | 2022-09-06 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2231 | 0 | 0 | 0 | 2231 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883179300 |  | 100308638 |  | 6716212M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | DELLA | 767 DELLA DR | 067 | LEX | 2022-09-06 | U127206 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 5418.54 | 482.23 | 0 | 26.9 | 4909.41 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883180300 |  | 500018304 |  | 6720212L | 0040999 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WINCHESTER | 1300 WINCHESTER RD 5 | 067 | LEX | 2022-09-07 | U125208 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | RSTRONG | 2022-09-06 | 2022-09-01 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.8167 | 2 | 1678.98 | 121.64 | 1.63 | 10.25 | 1545.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883284500 |  | 100320380 |  | 6716208G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NICHOLASVILLE | 1620 NICHOLASVILLE RD | 067 | LEX | 2022-09-06 | U129731 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.25 | 1 | 2183.42 | 393.37 | 0 | 81.48 | 1708.57 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21958572400 |  | 100242989 |  | 7356256O | 2074825 |  |  | 566 | EX | ABANDON SL W/20-0269775-00 | 2600B | BLACKBURN | 5201 BLACKBURN AV | 019 | ASH | 2022-09-06 | U124015 | U134723 | 2021-12-08 | 2022-12-30 |  |  | ORA SLONE | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 |  | 1
KY | KY - WEST | 2621 | 21958594400 |  | 100331895 |  | 6720212M | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 158 N ASHLAND AV | 067 | LEX | 2022-09-06 | U126308 | U134723 | 2021-12-08 | 2022-12-30 |  |  | J ENSMINGER | 2022-09-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2078.93 | 0 | 0 | 0 | 2078.93 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958594600 |  | 100331896 |  | 6720212M | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 162 N ASHLAND AV | 067 | LEX | 2022-09-07 | U129722 | U134723 | 2021-12-08 | 2022-12-30 |  |  | M YOUNG | 2022-09-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3536.78 | 0 | 0 | 0 | 3536.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959034600 |  | 100315148 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | JOURNAL | 901 JOURNAL HL | 067 | LEX | 2022-09-06 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-09-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 1522.65 | 513.76 | 0 | 71.05 | 937.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026198900 |  |  |  | 6712228I | 2289297 | U122858 |  | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2621M | US 460 BYPASS | US 460 BYPASS | 209 | GEO | 2022-09-23 | U125936 | U136124 | 2022-06-06 | 2022-12-30 | 2022-12-31 | 2022-09-06 | C. WEMPE | 2022-09-06 | 2022-09-06 |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00909 | 3200909 |  |  | WP1989 |  |  | 100 | 090932220261989 | 3.6833 | 0 | 5462.44 | 247.16 | 0 | 13.79 | 5174.3 | 0 | 27.19 | 0
KY | KY - WEST | 2623 | 22026199000 |  |  |  | 6712228I | 2289297 | U122858 |  | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2621M | US 460 BYPASS | US 460 BYPASS | 209 | GEO | 2022-09-23 | U125936 | U136124 | 2022-06-06 | 2022-12-30 | 2022-12-31 | 2022-09-06 | C. WEMPE | 2022-09-06 | 2022-09-06 |  | F | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00910 | 3200910 |  |  | WP1990 |  |  | 100 | 091032220261990 | 3.5667 | 0 | 252.74 | 239.37 | 0 | 13.37 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22026213800 |  |  |  | 7332288M | 2290312 | U132280 |  | 560 | EX | EMER - RETIRE 150'-2" P-IP | 2621P | TOOTSIE | TOOTSIE DR | 089 | S S | 2023-02-01 | U128132 | U132280 | 2022-07-25 | 2022-09-06 |  | 2022-08-01 | BROBERT | 2022-09-06 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00560 | 3200560 |  |  | WP2138 |  |  | 100 | 056032220262138 | 0.1 | 0 | 4136.05 | 2098.88 | 129.23 | 1907.94 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22114296900 |  | 100319505 |  | 6716208K | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER | 2621D | HEATHER | 1998 HEATHER WY | 067 | LEX | 2022-09-07 | U930915 | AOC SYST | 2022-07-06 | 2022-08-05 | 2022-09-04 |  | WISHII | 2022-09-06 | 2022-08-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 23.1 | 6 | 2458.44 | 1310.96 | 362.26 | 757.72 | 27.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125049800 |  | 100328973 |  | 6720208L | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER | 2621D | PLAINVIEW | 417 PLAINVIEW RD | 067 | LEX | 2022-09-06 | U930915 | AOC SYST | 2022-08-18 | 2022-09-15 | 2022-10-15 |  | LSTANFI | 2022-09-06 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 18.5667 | 3 | 1508.7 | 1171.4 | 196.54 | 78.06 | 62.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125981500 |  | 100294130 |  | 6716212E |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | UPPER | 656 N UPPER ST | 067 | LEX | 2022-09-06 | U125881 | U125763 | 2022-08-23 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127937300 |  | 500445713 |  | 6716212D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NEWTOWN | 503 NEWTOWN PK | 067 | LEX | 2022-09-06 | HMCKUNE | U125208 | 2022-08-31 | 2022-07-01 | 2022-09-19 |  | HMCKUNE | 2022-09-06 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.5667 | 2 | 248.45 | 235.29 | 0 | 13.16 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22128377200 |  | 100266779 |  | 7356256C |  |  |  | 566 | EX | ABND SERVICE LINE | 2600B | GREENUP | 2821 GREENUP AV | 019 | ASH | 2022-09-06 | U123965 | U125768 | 2022-09-01 | 2049-12-31 |  |  | MBLANKE | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.3667 | 1 | 1499.03 | 73.22 | 0 | 17.41 | 1408.4 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22128377400 |  | 100241855 |  | 7356252D |  |  |  | 566 | EX | ABND SERVICE LINE | 2600B | WILLIAMS | 5231 WILLIAMS AV | 019 | ASH | 2022-09-06 | U123965 | U125768 | 2022-09-01 | 2049-12-31 |  |  | MBLANKE | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.3167 | 1 | 1744.06 | 67.98 | 0 | 16.18 | 1659.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129048600 |  | 501241406 |  | 6728208I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | STOLEN HORSE | 3556 STOLEN HORSE TR LT10 | 067 | LEX | 2022-09-06 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129084900 |  | 100428742 |  | 6720212I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RACE | 189 RACE ST | 067 | LEX | 2022-09-06 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129085400 |  | 501285061 |  | 6728208I | 1966851 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | TWILIGHT SHADO | 1103 TWILIGHT SHADO DR LT58C | 067 | LEX | 2022-09-06 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129085600 |  | 501257799 |  | 6716216A | 1960987 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HALFORD | 761 HALFORD PL | 067 | LEX | 2022-11-03 | U938516 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHRIS HUNGATE | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129085700 |  | 100416638 |  | 6720216J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HOLLOW CREEK | 537 HOLLOW CREEK RD | 067 | LEX | 2022-11-03 | U938516 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHRIS HUNGATE | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 3876.59 | 0 | 0 | 0 | 3876.59 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129085900 |  | 500709192 |  | 6712216H | 9935863 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LEMON DROP | 400 LEMON DROP LN | 067 | LEX | 2022-11-03 | U938516 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHRIS HUNGATE | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129094400 |  | 100256248 |  | 7356256G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | BROOM | 501 BROOM ST | 019 | ASH | 2022-09-06 | U123965 | U125768 | 2022-09-06 | 2049-12-31 |  |  | MBLANKE | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.3333 | 1 | 1673.67 | 173.66 | 0 | 41.31 | 1458.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129099600 |  | 100334669 |  | 6724208A |  | U136526 |  | 565 | EX | REPLACE SERVICE LINE | 2621P | WILDERNESS | 540 WILDERNESS RD | 067 | LEX | 2022-09-06 | TROE | U136526 | 2022-09-06 | 2022-09-06 |  |  | TROE | 2022-09-06 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.9333 | 3 | 4296.92 | 1814.46 | 631.52 | 101.34 | 1749.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129131900 |  | 100325288 |  | 6720208M |  |  |  | 565 | EX | LEAK REPAIR - S.L. D311104 | 2621P | MONTAVESTA | 921 MONTAVESTA CR | 067 | LEX | 2022-09-07 | U125208 | U136526 | 2022-09-06 | 2022-09-06 | 2022-09-06 |  | LSTONE | 2022-09-06 | 2022-09-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 29.1167 | 4 | 2251.48 | 1811.47 | 292.75 | 101.06 | 46.2 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129141000 |  | 100268082 |  | 7356256B |  |  |  | 566 | EX | ABND SERVICE LINE | 2600B | 22ND | 227 22ND ST | 019 | ASH | 2022-09-06 | U123965 | U125768 | 2022-09-06 | 2049-12-31 |  |  | MBLANKE | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.58333 | 1 | 37.58 | 30.36 | 0 | 7.22 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129170800 |  | 100437045 |  | 6744208N |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | HOLIDAY | 216 HOLIDAY RD | 049 | WIN | 2022-09-13 | U938684 | U125763 | 2022-09-06 | 2022-12-30 |  |  | CHARLES COMBS | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 4256.75 | 0 | 0 | 0 | 4256.75 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129170900 |  | 100349007 |  | 6748208M |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | VINE | 26 VINE ST | 049 | WIN | 2022-09-13 | U938684 | U125763 | 2022-09-06 | 2022-12-30 |  |  | CHARLES COMBS | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 5210 | 0 | 0 | 0 | 5210 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129368300 |  | 100349314 |  | 6748208M |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | BROADWAY | 144 E BROADWAY ST | 049 | WIN | 2022-09-13 | U938684 | U125763 | 2022-09-07 | 2022-12-30 |  |  | CHARLES COMBS | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 6128 | 0 | 0 | 0 | 6128 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22970119300 |  | 100279880 |  | 6684228N | 2181158 |  |  | 565 | EX | REPLACE SL W/21-0261319-00 | 2600B | LYONS | 127 LYONS DR | 073 | FRA | 2022-09-06 | U128410 | U134723 | 2022-01-27 | 2022-12-30 |  |  | CDESPAIN | 2022-09-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2543.81 | 0 | 0 | 0 | 2543.81 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979026000 |  | 100265413 |  | 7352256N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RAYBURN | 1785 RAYBURN RD | 019 | ASH | 2022-09-06 | U123965 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | MBLANKE | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.25 | 1 | 1740.83 | 65.36 | 0 | 15.57 | 1659.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979027400 |  | 100268083 |  | 7356256B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 22ND | 227< 22ND ST | 019 | ASH | 2022-09-06 | U123965 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | MBLANKE | 2022-09-06 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.1 | 1 | 1465.19 | 5.24 | 0 | 1.25 | 1458.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983768500 |  | 100404291 |  | 6720204B | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 3380 GREENTREE CR | 067 | LEX | 2022-09-06 | U126530 | U134723 | 2022-03-04 | 2022-12-30 |  |  | JDUNN | 2022-09-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1283.17 | 0 | 0 | 0 | 1283.17 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22994323100 |  | 100353509 |  | 7256280K | 2180424 |  |  | 565 | EX | REPLACE SL W/21-0261272-00 | 2600B | 3RD | 223 W 3RD ST | 161 | MAY | 2022-10-13 | U461478 | U134723 | 2022-04-19 | 2022-12-30 |  |  | DAVID STAGGS | 2022-09-06 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2603.33 | 0 | 0 | 0 | 2603.33 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22994323300 |  | 100353564 |  | 7256280K | 2180424 |  |  | 565 | EX | REPLACE SL W/21-0261272-00 | 2600B | 3RD | 230 W 3RD ST | 161 | MAY | 2022-10-18 | U461478 | U134723 | 2022-04-19 | 2022-12-30 |  |  | DAVID STAGGS | 2022-09-06 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1691.72 | 0 | 0 | 0 | 1691.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 02499473300 |  | 100335618 |  | X00000000 | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | NEWTOWN | 750 NEWTOWN CT | 067 | LEX | 2022-09-07 | U135195 | DMCCULL | 2002-03-04 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2623 | 03528760400 |  | 100347090 |  | 6696212J | 1315787 |  |  | 566 | EX | PAPER ABAND / IDLE / BLDG GONE | 2621P | TYRONE | 800 TYRONE PK | 239 | VER | 2022-09-07 | BWHITE | DMCCULL | 2003-01-24 | 2022-09-07 |  |  | BWHITE | 2022-09-07 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 9.9833 | 6 | 597.85 | 490.53 | 0 | 107.32 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 06645584100 |  | 500768837 |  | 16716212J | 0146400 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | RED MILE | 975 RED MILE RD | 067 | LEX | 2022-09-07 | U127206 | SSUTHER | 2006-04-24 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-09-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1878.7 | 0 | 0 | 0 | 1878.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 06663390800 |  | 100301377 |  | 6712212H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SUTTON | 218 SUTTON PL | 067 | LEX | 2022-09-07 | U128816 | SSUTHER | 2006-10-17 | 2022-07-01 | 2022-12-31 |  | OLIVER MAYNARD | 2022-09-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.5 | 1 | 3409.76 | 156.56 | 239.5 | 8.74 | 3004.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 13113840400 |  | 500768839 |  | 16716212J | 0146400 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | RED MILE | 967 RED MILE RD | 067 | LEX | 2022-09-07 | U127206 | U908786 | 2013-01-23 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-09-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2218.96 | 0 | 0 | 0 | 2218.96 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916440600 |  | 100264048 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2536 MAIN ST W | 019 | ASH | 2022-09-07 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-07 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2047.27 | 0 | 0 | 0 | 2047.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958594000 |  | 100331937 |  | 6720212M | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 145 N ASHLAND AV 1 | 067 | LEX | 2022-09-08 | U129722 | U134723 | 2021-12-08 | 2022-12-30 |  |  | M YOUNG | 2022-09-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2104.9 | 0 | 0 | 0 | 2104.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958594100 |  | 100331891 |  | 6720212M | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 146 N ASHLAND AV | 067 | LEX | 2022-09-08 | U129722 | U134723 | 2021-12-08 | 2022-12-30 |  |  | M YOUNG | 2022-09-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3185.97 | 0 | 0 | 0 | 3185.97 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958594200 |  | 100331934 |  | 6720212M | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 149 N ASHLAND AV | 067 | LEX | 2022-09-08 | U129722 | U134723 | 2021-12-08 | 2022-12-30 |  |  | M YOUNG | 2022-09-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1795.67 | 0 | 0 | 0 | 1795.67 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960238200 |  | 100321220 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | MAXWELL | 428 E MAXWELL ST | 067 | LEX | 2022-10-12 | U461375 | U134723 | 2021-12-17 | 2022-12-30 |  |  | LARRY BROWN | 2022-09-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2287.46 | 0 | 0 | 0 | 2287.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026180100 |  | 501328343 |  | 6708204C | 2287992 | U461383 |  | 555 | EX | INSTALL 805' OF 2"/4"PMMP MAIN | 2600B | KEENE | 5035 KEENE RD HOUSE | 067 | LEX | 2022-09-08 | U460266 | U461383 | 2022-04-06 | 2022-10-17 | 2022-11-01 | 2022-08-30 | SCANOY | 2022-09-07 | 2022-07-21 | 2022-08-01 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP1801 |  |  | 100 | 055532220261801 | 262.85 | 22069 | 116760.6 | 19245.52 | 6353.37 | 5169.64 | 67059.99 | 0 | 117.53 | 18814.55 | 761
KY | KY - WEST | 2621 | 22026197100 |  |  |  | 6716216N | 2289272 | U122858 |  | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2621M | TOWNLEY | TOWNLEY DR | 067 | LEX | 2022-09-19 | U123258 | U136124 | 2022-06-03 | 2022-12-30 | 2022-12-31 | 2022-09-07 | EBLANTON | 2022-09-07 | 2022-09-07 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP1971 |  |  | 100 | 090932220261971 | 2.3667 | 0 | 5373.93 | 163.39 | 0 | 9.12 | 5174.3 | 0 | 27.12 | 0
KY | KY - WEST | 2621 | 22026197200 |  |  |  | 6716216N | 2289272 | U122858 |  | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2621M | TOWNLEY | TOWNLEY DR | 067 | LEX | 2022-09-19 | U123258 | U136124 | 2022-06-03 | 2022-12-30 | 2022-12-31 | 2022-09-07 | EBLANTON | 2022-09-07 | 2022-09-07 |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00910 | 3200910 |  |  | WP1972 |  |  | 100 | 091032220261972 | 3.45 | 0 | 251.1 | 237.82 | 0 | 13.28 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026202900 |  |  |  | 6708204C | 2287992 | U461383 |  | 560 | EX | RETIRE 135' OF 2"PMP MAIN | 2600B | KEENE | 5035 KEENE RD | 067 | LEX | 2022-09-08 | U460266 | U461383 | 2022-06-09 | 2022-11-01 | 2022-11-01 | 2022-08-30 | SCANOY | 2022-09-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00560 | 3200560 |  |  | WP2029 |  |  | 100 | 056032220262029 | 0.016667 | 0 | 2.29 | 1.17 | 0 | 1.12 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22127046700 |  | 500684963 |  | 6684228C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FAIR OAKS | 350 FAIR OAKS DR | 073 | FRA | 2022-09-08 | U125208 | U125208 | 2022-08-26 | 2022-08-31 | 2022-09-14 |  | CHERNDO | 2022-09-07 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 14.75 | 2 | 888.25 | 841.32 | 0 | 46.93 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129017500 |  | 100295844 |  | 6716216G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MARK | 1990 MARK AV | 067 | LEX | 2022-09-07 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129017600 |  | 500588886 |  | 6712216H | 9723002 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MASTERSON STAT | 265 MASTERSON STAT DR | 067 | LEX | 2022-09-07 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1777.87 | 0 | 0 | 0 | 1777.87 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129048900 |  | 500640802 |  | 6712216H | 9829830 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MABLE | 2757 MABLE LN | 067 | LEX | 2022-11-03 | U938516 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHRIS HUNGATE | 2022-09-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129049000 |  | 500923328 |  | 6712216D | 0465553 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAJESTIC VIEW | 2856 MAJESTIC VIEW WK | 067 | LEX | 2022-09-07 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1535.48 | 0 | 0 | 0 | 1535.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129049200 |  | 100443171 |  | 6716216L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NANDINO | 1042 NANDINO BV | 067 | LEX | 2022-09-07 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129086000 |  | 500183849 |  | 6716216L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NANDINO | 978 NANDINO BV A | 067 | LEX | 2022-09-07 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129086100 |  | 501101624 |  | 6716216K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | TROTWOOD | 1034 TROTWOOD DR A | 067 | LEX | 2022-09-07 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129086400 |  | 500654084 |  | 6712208B | 9829045 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BENJAMIN | 1113 BENJAMIN LN | 067 | LEX | 2022-09-07 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129086500 |  | 100447204 |  | 6712208J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FORT HARRODS | 2140 FORT HARRODS DR 19 | 067 | LEX | 2022-09-07 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129086700 |  | 500615983 |  | 6712208K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SNAFFLE | 3294 SNAFFLE RD A | 067 | LEX | 2022-09-07 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129101800 |  | 500584173 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | GAZETTE | 178 GAZETTE AV | 067 | LEX | 2022-09-07 | U129673 | U125768 | 2022-09-06 | 2049-12-31 |  |  | ALEX WILLIAMSON | 2022-09-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 3272.5 | 513.76 | 0 | 104.86 | 2653.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129191600 |  | 100416855 |  | 6716204K |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | NORTHAMPTON | 3930 NORTHAMPTON DR | 067 | LEX | 2022-09-07 | HMCKUNE | U136526 | 2022-09-06 | 2022-09-02 | 2022-09-22 |  | HMCKUNE | 2022-09-07 | 2022-09-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.4333 | 4 | 1501.82 | 1131.18 | 193.1 | 63.14 | 114.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129362000 |  | 500768838 |  | 6716212J |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | RED MILE | 971 RED MILE RD | 067 | LEX | 2022-09-07 | U127206 | U125763 | 2022-09-07 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 831.07 | 482.23 | 0 | 26.9 | 321.94 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129414300 |  | 100282181 |  | 6712228C |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | PENN | 214 PENN AL | 209 | GEO | 2022-09-07 | DCOLLIN | U129939 | 2022-09-07 | 2022-09-07 | 2022-09-22 |  | DCOLLIN | 2022-09-07 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26230022 | 2.65 | 1 | 2316.45 | 181.47 | 378.11 | 10.13 | 1746.74 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129417600 |  | 100264049 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400 | 2600B | MAIN | 2600 MAIN ST W | 019 | ASH | 2022-09-07 | U124015 | U125768 | 2022-09-07 | 2049-12-31 |  |  | ORA SLONE | 2022-09-07 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2077.25 | 0 | 0 | 0 | 2077.25 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22970119500 |  | 100279881 |  | 6684228N | 2181158 |  |  | 565 | EX | REPLACE SL W/21-0261319-00 | 2600B | LYONS | 131 LYONS DR | 073 | FRA | 2022-09-07 | U128410 | U134723 | 2022-01-27 | 2022-12-30 |  |  | CDESPAIN | 2022-09-07 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3026.75 | 0 | 0 | 0 | 3026.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22979033900 |  | 100301382 |  | 6712212H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SUTTON | 228 SUTTON PL | 067 | LEX | 2022-09-07 | U128816 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | OLIVER MAYNARD | 2022-09-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.6667 | 1 | 3429.74 | 104.58 | 239.5 | 5.84 | 3079.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983422800 |  | 100324758 |  | 6720204B | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 3382 GREENTREE RD | 067 | LEX | 2022-09-07 | U129731 | U134723 | 2022-03-03 | 2022-12-30 |  |  | F.GOINS | 2022-09-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1074.38 | 0 | 0 | 0 | 1074.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22985783400 |  | 100437819 |  | 6712208K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D247726 | 2621P | HARRODSBURG | 3080 HARRODSBURG RD 1FL | 067 | LEX | 2022-09-07 | MCRAIG | U125208 | 2022-03-14 | 2022-09-09 | 2024-03-31 |  | MCRAIG | 2022-09-07 | 2022-03-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 36.7667 | 9 | 3615.38 | 2108.59 | 888.87 | 441.92 | 176 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22994322900 |  | 100353572 |  | 7256280K | 2180424 |  |  | 565 | EX | REPLACE SL W/21-0261272-00 | 2600B | 3RD | 216 W 3RD ST | 161 | MAY | 2022-10-18 | U461478 | U134723 | 2022-04-19 | 2022-12-30 |  |  | DAVID STAGGS | 2022-09-07 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 4168.58 | 0 | 0 | 0 | 4168.58 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22994323400 |  | 100353515 |  | 7256280K | 2180424 |  |  | 565 | EX | REPLACE SL W/21-0261272-00 | 2600B | 3RD | 234 W 3RD ST | 161 | MAY | 2022-10-18 | U461478 | U134723 | 2022-04-19 | 2022-12-30 |  |  | DAVID STAGGS | 2022-09-07 | 2022-09-13 |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 | 8 | 1 | 2941.53 | 488.47 | 0 | 27.25 | 2425.81 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22999312600 |  | 100300984 |  | 6712212H |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2600B | LONDONDERRY | 118 LONDONDERRY DR 1FR | 067 | LEX | 2022-09-07 | U128816 | U134723 | 2022-05-09 | 2022-12-20 |  |  | OLIVER MAYNARD | 2022-09-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.8333 | 1 | 2345.78 | 239.82 | 239.5 | 13.39 | 1853.07 | 0 | 0 | 0
KY | KY - EAST | 2633 | 03557387200 |  | 100266563 | 14 | 7356152E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | US23 | US23 | 195 | BLA | 2022-09-08 | JAHOWARD | DHANSFO | 2003-11-19 | 2022-09-08 | 2022-12-31 |  | JAHOWARD | 2022-09-08 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.16667 | 1 | 12.06 | 11.42 | 0 | 0.64 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 12969070200 |  | 100266564 |  | 7356152E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | US23 | US23 | 195 | BLA | 2022-09-08 | JAHOWARD | PBRUNTY | 2012-05-09 | 2021-12-30 | 2021-12-31 |  | JAHOWARD | 2022-09-08 | 2022-03-08 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 38.8167 | 10 | 3018.54 | 2313.94 | 0 | 704.6 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19703633700 |  | 100331938 |  | 6720212M | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 141 N ASHLAND AV | 067 | LEX | 2022-09-09 | U129722 | U125208 | 2019-05-06 | 2022-12-30 |  |  | M YOUNG | 2022-09-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4071.16 | 0 | 0 | 0 | 4071.16 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21026137900 |  |  |  | 6740208C | 2182168 | U128885 |  | 583 | EX | INSTALL OUTLET VLV R-1643 | 2629M | GAWTHROP | GAWTHROP DR | 049 | WIN | 2023-01-24 | U462081 | U128885 | 2021-08-24 | 2023-12-18 | 2023-12-31 | 2022-09-08 | JPASLEY | 2022-09-08 | 2022-08-31 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00583 | 3200583 |  |  | WP1379 |  |  | 100 | 058332210261379 | 147.5 | 132 | 80161.67 | 11059.63 | 10362.15 | 3064.41 | 45228.36 | 0 | 66.82 | 10380.3
KY | KY - CENTRAL | 2629 | 21026138000 |  |  |  | 6740208C | 2182168 | U128885 |  | 584 | EX | RETIRE OUTLET VLV R-1643 | 2629M | GAWTHROP | GAWTHROP DR | 049 | PIN | 2022-12-30 | U462081 | U128885 | 2021-08-24 | 2023-12-28 | 2023-12-31 | 2022-09-08 | JPASLEY | 2022-09-08 |  |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00584 | 3200584 |  |  | WP1380 |  |  | 100 | 058432210261380 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883296300 |  | 100341565 |  | 7240216N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | HIGH | 114 E HIGH ST | 173 | MT | 2022-09-08 | DENNING | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DENNING | 2022-09-08 | 2022-09-06 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.6 | 4 | 863.52 | 601.41 | 0 | 262.11 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883320300 |  | 100301678 |  | 6712212H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LIVERPOOL | 217 LIVERPOOL RD | 067 | LEX | 2022-09-08 | U128816 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | OLIVER MAYNARD | 2022-09-08 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.3333 | 1 | 3667.27 | 148.41 | 258.03 | 8.28 | 3252.55 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21884243100 |  | 100302151 |  | 6712212H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CAMBRIDGE | 1938 CAMBRIDGE DR | 067 | LEX | 2022-09-08 | U128816 | U128293 | 2021-02-04 | 2022-07-01 | 2022-12-31 |  | OLIVER MAYNARD | 2022-09-08 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.2333 | 1 | 2250.12 | 264.27 | 0 | 14.75 | 1971.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916441100 |  | 501252075 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2602< MAIN ST W | 019 | ASH | 2022-09-08 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-08 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2650.16 | 0 | 0 | 0 | 2650.16 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916441300 |  | 100264050 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2608 MAIN ST W | 019 | ASH | 2022-09-08 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-08 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2845.34 | 0 | 0 | 0 | 2845.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959034700 |  | 100315220 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | JOURNAL | 919 JOURNAL HL | 067 | LEX | 2022-09-08 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-09-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2934.29 | 474.35 | 0 | 26.46 | 2433.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959034800 |  | 100315222 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | JOURNAL | 927 JOURNAL HL | 067 | LEX | 2022-09-08 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-09-08 | 2022-09-08 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 1713.1 | 513.76 | 0 | 104.86 | 1094.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960236600 |  | 100321125 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | MAXWELL | 306 E MAXWELL ST 1F | 067 | LEX | 2022-10-12 | U461375 | U134723 | 2021-12-17 | 2022-12-30 |  |  | LARRY BROWN | 2022-09-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3912.69 | 0 | 0 | 0 | 3912.69 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026199500 |  |  |  | 6684228L | 2289339 | U122858 |  | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2621M | GLENNS CREEK | 110 GLENNS CREEK RD | 073 | FRA | 2022-10-25 | U123258 | U136124 | 2022-06-07 | 2022-12-30 | 2022-12-31 | 2022-09-08 | GHALE | 2022-09-08 |  |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00909 | 3200909 |  |  | WP1995 |  |  | 100 | 090932220261995 | 1.2167 | 0 | 5358.86 | 88.89 | 0 | 68.58 | 5174.3 | 0 | 27.09 | 0
KY | KY - WEST | 2623 | 22026199600 |  |  |  | 6684228L | 2289339 | U122858 |  | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2621M | GLENNS CREEK | 110 GLENNS CREEK RD | 073 | FRA | 2022-10-03 | U460266 | U136124 | 2022-06-07 | 2022-12-30 | 2022-12-31 | 2022-09-08 | GHALE | 2022-09-08 | 2022-09-08 |  | F | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00910 | 3200910 |  |  | WP1996 |  |  | 100 | 091032220261996 | 6.4833 | 0 | 509.01 | 421.84 | 0 | 87.17 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026201100 |  |  |  | 6688228E | 2289378 | U122858 |  | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2621M | ROLLING ACRES | ROLLING ACRES DR | 073 | FRA | 2022-10-03 | U462463 | U136124 | 2022-06-08 | 2022-12-30 | 2022-12-31 | 2022-09-08 | GHALE | 2022-09-08 | 2022-09-08 |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00909 | 3200909 |  |  | WP2011 |  |  | 100 | 090932220262011 | 3.95 | 0 | 5540.17 | 260.43 | 0 | 78.17 | 5174.3 | 0 | 27.27 | 0
KY | KY - WEST | 2623 | 22026201200 |  |  |  | 6688228E | 2289378 | U122858 |  | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2621M | ROLLING ACRES | ROLLING ACRES DR | 073 | FRA | 2022-10-03 | U462463 | U136124 | 2022-06-08 | 2022-12-30 | 2022-12-31 | 2022-09-08 | GHALE | 2022-09-08 |  |  | F | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00910 | 3200910 |  |  | WP2012 |  |  | 100 | 091032220262012 | 1.2167 | 0 | 157.47 | 88.89 | 0 | 68.58 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026217300 |  | 100454171 |  | 6720212M | 2180410 | U461383 |  | 566 | EX | RETIRE 3"PLP SERVICE LINE | 2600B | ASHLAND | 124 N ASHLAND AV | 067 | LEX | 2022-11-08 | U128132 | U461383 | 2022-08-10 | 2022-09-30 | 2022-10-01 | 2022-09-08 | M YOUNG | 2022-09-08 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP2173 | AMRSL |  | 100 | 056632220262173 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22123000500 |  | 100454171 |  | 6720212M | 2180410 |  |  | 565 | EX | INSTALL 120' OF 1"PMMP S/L | 2600B | ASHLAND | 124 N ASHLAND AV | 067 | LEX | 2022-09-20 | U128381 | U461383 | 2022-08-10 | 2022-09-30 | 2022-10-01 |  | M YOUNG | 2022-09-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2089.24 | 0 | 0 | 0 | 2089.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22124931600 |  | 100463177 |  | 6716212G |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTRQD | 2621P | MAXWELL | 817 W MAXWELL ST | 067 | LEX | 2022-09-08 | HMCKUNE | U132002 | 2022-08-18 | 2022-08-31 | 2022-09-16 |  | HMCKUNE | 2022-09-08 | 2022-08-22 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 17.7667 | 5 | 2022.09 | 1041.38 | 33.24 | 178.34 | 769.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126060000 |  | 500407104 |  | 6724208J | 9507325 |  |  | 566 | EX | ABANDON SL - DEMO/CUSTREQD | 2621P | MAPLE LEAF | 3151 MAPLE LEAF DR | 067 | LEX | 2022-09-20 | U461383 | U125208 | 2022-08-23 | 2022-08-26 | 2022-09-13 |  | MCRAIG | 2022-09-08 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10.1333 | 3 | 525.19 | 464.32 | 33.24 | 27.63 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22127125700 |  | 100244073 |  | 7356256J |  |  |  | 565 | EX | REPLACE SERVICE LINE - D258033 | 2621P | BELMONT | 2116 BELMONT ST | 019 | ASH | 2022-09-08 | RECUMP | U125208 | 2022-08-26 | 2022-08-26 | 2022-09-15 |  | RECUMP | 2022-09-08 | 2022-09-07 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 28.8 | 6 | 3459.27 | 1590.85 | 197.33 | 103.99 | 1567.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22127649000 |  | 100247305 |  | 7352256L |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2600B | BEECH | 2315 BEECH ST 9 | 019 | ASH | 2022-09-08 | U123965 | U134723 | 2022-08-30 | 2022-12-30 |  |  | MBLANKE | 2022-09-08 | 2022-08-31 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 6.4833 | 2 | 5867.15 | 316.79 | 0 | 94.28 | 5456.08 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129027000 |  | 100244440 |  | 7356256K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 39TH | 1019 39TH ST | 019 | ASH | 2022-09-08 | U123965 | U130722 | 2022-09-05 | 2022-12-30 |  |  | MBLANKE | 2022-09-08 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.83333 | 1 | 1512.43 | 43.4 | 0 | 10.33 | 1458.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129049300 |  | 500363837 |  | 6712204E | 9402987 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | COPPER RUN | 1477 COPPER RUN BV | 067 | LEX | 2022-09-08 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-08 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1402.64 | 0 | 0 | 0 | 1402.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129049500 |  | 500494276 |  | 6712204H | 9610755 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WILLOW RIDGE | 3724 WILLOW RIDGE RD | 067 | LEX | 2022-09-08 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-08 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1883.24 | 0 | 0 | 0 | 1883.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129049600 |  | 500218026 |  | 6720204P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FARMVIEW | 1756 FARMVIEW DR | 067 | LEX | 2022-09-08 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-08 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1743.62 | 0 | 0 | 0 | 1743.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129049700 |  | 500150248 |  | 6720204N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KENESAW | 3816 KENESAW DR B | 067 | LEX | 2022-09-08 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-08 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129049800 |  | 500070112 |  | 6720204M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | TANBARK | 1029 TANBARK RD | 067 | LEX | 2022-09-08 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-08 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1627.25 | 0 | 0 | 0 | 1627.25 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129064700 |  | 100257414 |  | 7356256E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 3RD CIRCLE PRO | 2023 3RD CIRCLE PRO | 019 | ASH | 2022-09-08 | U123965 | U130722 | 2022-09-05 | 2022-12-30 |  |  | MBLANKE | 2022-09-08 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.15 | 1 | 1395.43 | 111.41 | 0 | 26.52 | 1257.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129079600 |  | 100301604 |  | 6712212H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DEAUVILLE | 1911 DEAUVILLE DR | 067 | LEX | 2022-09-08 | U128816 | U130722 | 2022-09-05 | 2022-12-30 |  |  | OLIVER MAYNARD | 2022-09-08 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.4333 | 1 | 2212.11 | 88.94 | 239.5 | 4.97 | 1878.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129086800 |  | 500654146 |  | 6712208B | 9829045 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SOVEREIGN | 2116 SOVEREIGN LN | 067 | LEX | 2022-09-08 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-08 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1176.73 | 0 | 0 | 0 | 1176.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129086900 |  | 500141410 |  | 6716204P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FAIRHAVEN | 938 FAIRHAVEN DR | 067 | LEX | 2022-09-08 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-08 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129087000 |  | 500141468 |  | 6720200A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | JAIRUS | 863 JAIRUS DR | 067 | LEX | 2022-09-08 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-08 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129087200 |  | 100458620 |  | 6716204H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GATEWOOD | 3352 GATEWOOD CT | 067 | LEX | 2022-11-03 | U938516 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHRIS HUNGATE | 2022-09-08 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129127800 |  | 500588902 |  | 6712216H | 9723002 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MASTERSON STAT | 292 MASTERSON STAT DR | 067 | LEX | 2022-09-08 | U125881 | U125208 | 2022-09-06 | 2022-12-30 |  |  | HERBERT HAYEN | 2022-09-08 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129127900 |  | 500654132 |  | 6712208B | 9829045 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SOVEREIGN | 2133 SOVEREIGN LN | 067 | LEX | 2022-09-08 | U125881 | U125208 | 2022-09-06 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-08 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1176.73 | 0 | 0 | 0 | 1176.73 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964239300 |  | 100347815 |  | 6748208I | 2075093 |  |  | 565 | EX | REPLACE SL W/20-0269804-00 | 2600B | MAGNOLIA | 102 MAGNOLIA ST | 049 | WIN | 2022-09-08 | U126603 | U134723 | 2022-01-06 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-09-08 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1980.59 | 0 | 0 | 0 | 1980.59 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964239500 |  | 100347865 |  | 6748208I | 2075093 |  |  | 565 | EX | REPLACE SL W/20-0269804-00 | 2600B | MAGNOLIA | 105 MAGNOLIA ST | 049 | WIN | 2022-09-08 | U126603 | U134723 | 2022-01-06 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-09-08 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1855.72 | 0 | 0 | 0 | 1855.72 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22970119400 |  | 100280377 |  | 6684228N | 2181158 |  |  | 565 | EX | REPLACE SL W/21-0261319-00 | 2600B | LYONS | 128 LYONS DR | 073 | FRA | 2022-09-08 | U128410 | U134723 | 2022-01-27 | 2022-12-30 |  |  | CDESPAIN | 2022-09-08 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3293.15 | 0 | 0 | 0 | 3293.15 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979017600 |  | 100244427 |  | 7356256K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WALLACE | 1030< WALLACE ST | 019 | ASH | 2022-09-08 | U123965 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | MBLANKE | 2022-09-08 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.7333 | 1 | 3139.4 | 89.94 | 0 | 21.4 | 3028.06 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979018700 |  | 100247645 |  | 7352256H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PHELPS | 2115 PHELPS AV | 019 | ASH | 2022-09-08 | U123965 | U128070 | 2022-02-17 | 2022-09-08 | 2022-12-31 |  | MBLANKE | 2022-09-08 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.78333 | 1 | 1512.43 | 43.4 | 0 | 10.33 | 1458.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983422400 |  | 100409727 |  | 6720204B | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 3388 GREENTREE PL | 067 | LEX | 2022-09-08 | U129731 | U134723 | 2022-03-03 | 2022-12-30 |  |  | F.GOINS | 2022-09-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1149.96 | 0 | 0 | 0 | 1149.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983425900 |  | 100409376 |  | 6720204B | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 3386 GREENTREE PL | 067 | LEX | 2022-09-08 | U129731 | U134723 | 2022-03-03 | 2022-12-30 |  |  | F.GOINS | 2022-09-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1090.46 | 0 | 0 | 0 | 1090.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 09816491600 |  | 100301198 | 57 | 16716212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | DELMONT | 143< DELMONT DR | 067 | LEX | 2022-09-09 | U128816 | RSTOKLE | 2009-12-30 | 2020-12-23 |  |  | OLIVER MAYNARD | 2022-09-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.5 | 1 | 99.17 | 93.93 | 0 | 5.24 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 09816492500 |  | 100301197 | 36 | 16716212E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | DELMONT | 143 DELMONT DR | 067 | LEX | 2022-09-09 | U128816 | RSTOKLE | 2009-12-30 | 2022-07-01 | 2022-12-31 |  | OLIVER MAYNARD | 2022-09-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.35 | 1 | 3241.44 | 21.92 | 40.6 | 1.22 | 3177.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 10870597400 |  | 100450077 |  | W-1001-15 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | YELLOWSTONE | 3236 YELLOWSTONE CT | 067 | LEX | 2022-10-21 | U125881 | U906307 | 2010-12-02 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-09-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11891009000 |  | 100455080 |  | W-1001-15 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | YELLOWSTONE | 3240 YELLOWSTONE PY | 067 | LEX | 2022-10-21 | U125881 | U123933 | 2011-02-22 | 2022-07-01 | 2022-12-31 |  | HERBERT HYADEN | 2022-09-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1402.64 | 0 | 0 | 0 | 1402.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12980742400 |  | 100302790 |  | V-924-64 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | PARKERS MILL | 1613 PARKERS MILL RD | 067 | LEX | 2022-09-09 | U128816 | U125208 | 2012-07-18 | 2022-07-01 | 2022-12-31 |  | OLIVER MAYNARD | 2022-09-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.2167 | 1 | 2029.41 | 77.03 | 239.5 | 4.31 | 1708.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 13170474000 |  | 100306787 | 71 | 3843-D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | TERRACE VIEW | 705 TERRACE VIEW DR | 067 | LEX | 2022-09-09 | U128816 | DWELLS | 2013-10-24 | 2022-07-01 | 2022-12-31 |  | OLIVER MAYNARD | 2022-09-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 18026843301 |  |  |  | 6716212L | 1858813 | U461383 |  | 557 | EX | INSTALL 3000' OF 4/6/8"PMLP | 2600B | M L KING | M L KING | 067 | LEX | 2022-10-04 | U460266 | U461383 | 2022-07-14 | 2022-02-17 | 2022-12-01 | 2022-09-07 | LESLIE SHARON | 2022-09-09 | 2022-07-19 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP8433 | AMRCB |  | 100 | 055732180268433 | 1587.9333 | 527696 | 1711065.31 | 104738.04 | 252068.2 | 18994.55 | 1089155.48 | 0 | 12853.5 | 233255.54 | 3068
KY | KY - EAST | 2633 | 20026926400 |  |  |  | 7340180P | 2070106 | U128885 |  | 587 | EX | INSTALL NETWORK UPGRADE | 2600M | US23 | 400 E US23 | 115 | PAI | 2022-09-19 | U123258 | U128885 | 2020-02-19 | 2022-12-29 | 2022-12-31 | 2022-08-23 | M.RYAN | 2022-09-09 | 2022-08-23 |  | F | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00587 | 3200587 |  |  | WP9264 |  |  | 100 | 058732200269264 | 19.4667 | 18 | 7131.29 | 1320.28 | 0 | 328.6 | 4500 | 0 | 108.35 | 874.06
KY | KY - EAST | 2633 | 20026926500 |  |  |  | 7340180P | 2070106 | U128885 |  | 588 | VO | RETIRE NETWORK | 2600M | US23 | 400 E US23 | 115 | PAI | 2022-09-09 |  | U128885 | 2020-02-19 | 2022-12-30 | 2022-12-31 | 2022-08-23 | M.RYAN | 2022-09-09 |  |  | F | [11 empty] | 20026926400 | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21883063300 |  | 100445582 |  | 7256280N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | US 68 | 1152 US 68 | 161 | MAY | 2022-09-13 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-09-09 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1 | 3505 | 0 | 0 | 0 | 3505 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21883206100 |  | 100439401 |  | 7240280G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | KY 10 | 4387 KY 10 | 161 | GER | 2022-09-13 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-09-09 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1 | 3505 | 0 | 0 | 0 | 3505 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883233800 |  | 100348303 |  | 6748208I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MUTUAL | 20 MUTUAL AV | 049 | WIN | 2022-09-13 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-09-09 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 3505 | 0 | 0 | 0 | 3505 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883286700 |  | 100301209 |  | 6716212E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | DELMONT | 151 DELMONT DR | 067 | LEX | 2022-09-09 | U128816 | U120245 | 2021-01-30 | 2022-12-20 |  |  | OLIVER MAYNARD | 2022-09-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.81667 | 1 | 3321.73 | 51.37 | 239.5 | 2.87 | 3027.99 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21897158200 |  | 500823923 |  | 7244280F | 9722832 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | BEAUMONT | 4001 BEAUMONT DR | 161 | DOV | 2022-09-13 | U938684 | U124841 | 2021-03-25 | 2021-12-30 |  |  | CHARLES COMBS | 2022-09-09 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1 | 3505 | 0 | 0 | 0 | 3505 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916441700 |  | 100263459 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2645 MAIN ST W | 019 | ASH | 2022-09-09 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1932.53 | 0 | 0 | 0 | 1932.53 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916441800 |  | 100415958 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2647 MAIN ST W | 019 | ASH | 2022-09-09 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2465.74 | 0 | 0 | 0 | 2465.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958593400 |  | 100331941 |  | 6720212M | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 121 N ASHLAND AV | 067 | LEX | 2022-09-12 | U129722 | U134723 | 2021-12-08 | 2022-12-30 |  |  | M YOUNG | 2022-09-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2083.7 | 0 | 0 | 0 | 2083.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958593600 |  | 100331939 |  | 6720212M | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 139 N ASHLAND AV | 067 | LEX | 2022-09-12 | U129722 | U134723 | 2021-12-08 | 2022-12-30 |  |  | M YOUNG | 2022-09-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2182.35 | 0 | 0 | 0 | 2182.35 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959046900 |  | 100315227 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | CONN TER | 236 CONN TER A | 067 | LEX | 2022-09-09 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-09-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 2 | 1653.82 | 513.76 | 0 | 104.86 | 1035.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026216200 |  | 501334593 |  | 6716216E | 2290521 | U461383 |  | 555 | EX | INSTALL 950' OF 2"/4"PMMP MAIN | 2600B | CALENDULA | CALENDULA RD LT272 | 067 | LEX | 2022-09-21 | U460266 | U461383 | 2022-08-02 | 2022-09-27 | 2022-10-07 | 2022-09-09 | R.HUMPHREYS | 2022-09-09 | 2022-08-24 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2162 |  |  | 100 | 055532220262162 | 92 | 10190 | 47379.78 | 6368.23 | 4245.79 | 1412.88 | 27747.99 | 0 | 103.99 | 7500.9 | 1019
KY | KY - WEST | 2621 | 22127677100 |  | 100332923 |  | 6720208H |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | CODELL | 100 CODELL DR | 067 | LEX | 2022-09-09 | U930915 | U132002 | 2022-08-30 | 2022-09-12 | 2022-09-28 |  | RJCRAWF | 2022-09-09 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15 | 3 | 933.78 | 865.8 | 19.65 | 48.33 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129011200 |  | 100250060 |  | 7360248A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LOUISA | 3246 LOUISA ST | 019 | CAT | 2022-09-09 | U123965 | U130722 | 2022-09-05 | 2022-09-09 |  |  | MBLANKE | 2022-09-09 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.6667 | 2 | 1630.28 | 138.6 | 0 | 32.98 | 1458.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129017800 |  | 500639728 |  | 6716204H | 9724090 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SHERARD | 631 SHERARD CR | 067 | LEX | 2022-10-21 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2570.6 | 0 | 0 | 0 | 2570.6 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129026700 |  | 100258776 |  | 7356256F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 27TH | 625 27TH ST | 019 | ASH | 2022-09-09 | U123965 | U130722 | 2022-09-05 | 2022-09-09 |  |  | MBLANKE | 2022-09-09 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.9333 | 1 | 1863.03 | 100.43 | 0 | 23.9 | 1738.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129043800 |  | 500605927 |  | 6716208N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | STONEGATE | 305 STONEGATE WY | 067 | LEX | 2022-09-19 | U127206 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 2 | 3820.61 | 482.23 | 1262.65 | 26.9 | 2048.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129050300 |  | 100324441 |  | 6720204E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OLYMPIA | 3552 OLYMPIA DR | 067 | LEX | 2022-10-21 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129050400 |  | 500073366 |  | 6720204J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RIVER PARK | 1305 RIVER PARK CR A | 067 | LEX | 2022-10-21 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129050500 |  | 500458408 |  | 6716204L | 9403370 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SUGAR CREEK | 3852 SUGAR CREEK DR | 067 | LEX | 2022-09-09 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129079500 |  | 100319689 |  | 6716208K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ZANDALE | 228 ZANDALE DR | 067 | LEX | 2022-09-13 | U127206 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1878.7 | 0 | 0 | 0 | 1878.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129087300 |  | 100414682 |  | 6720204J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OXHILL | 1320 OXHILL DR | 067 | LEX | 2022-10-21 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1717.56 | 0 | 0 | 0 | 1717.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129087400 |  | 100434385 |  | 6716204B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | REYNOLDS | 123 E REYNOLDS RD | 067 | LEX | 2022-09-09 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129087500 |  | 100317829 |  | 6716204G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | TEMPLE | 3749 TEMPLE DR | 067 | LEX | 2022-09-09 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129952900 |  | 100283417 |  | 6712228E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | POCAHONTAS | 508 POCAHONTAS TL | 209 | GEO | 2022-09-09 | DCOLLIN | U129939 | 2022-09-08 | 2022-09-08 |  |  | DCOLLIN | 2022-09-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 8.3667 | 1 | 3118.95 | 566.76 | 241.53 | 63.44 | 2247.22 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22130462500 |  | 500851887 |  | 7256280O | 2180424 |  |  | 565 | EX | REPLACE W/ 21026127400 | 2600B | EDGEMONT | 179 EDGEMONT RD | 161 | MAY | 2022-10-18 | U461478 | U125768 | 2022-09-09 | 2049-12-31 |  |  | DAVID STAGGS | 2022-09-09 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1757.08 | 0 | 0 | 0 | 1757.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22130481300 |  | 100459371 |  | 6720204D |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | CUSTER | 3161 CUSTER DR 8 | 067 | LEX | 2022-09-09 | U135195 | U125763 | 2022-09-09 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 718.83 | 0 | 0 | 0 | 718.83 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22970119000 |  | 100279876 |  | 6684228N | 2181158 |  |  | 565 | EX | REPLACE SL W/21-0261319-00 | 2600B | LYONS | 111 LYONS DR | 073 | FRA | 2022-09-09 | U128410 | U134723 | 2022-01-27 | 2022-12-30 |  |  | CDESPAIN | 2022-09-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2915.64 | 0 | 0 | 0 | 2915.64 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979056700 |  | 501194436 |  | 7348252L | 1637765 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HERITAGE HEIGH | 7516 HERITAGE HEIGH RD | 019 | ASH | 2022-09-09 | U123965 | U128070 | 2022-02-17 | 2022-09-09 | 2022-12-31 |  | MBLANKE | 2022-09-09 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.55 | 1 | 2028.14 | 134.94 | 0 | 32.1 | 1861.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983426000 |  | 100409375 |  | 6720204B | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 3390 GREENTREE PL | 067 | LEX | 2022-09-09 | U126530 | U134723 | 2022-03-03 | 2022-12-30 |  |  | JDUNN | 2022-09-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1370.81 | 0 | 0 | 0 | 1370.81 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22994320800 |  | 100356475 |  | 7256280O | 2180424 |  |  | 565 | EX | REPLACE SL W/21-0261274-00 | 2600B | FORT HILL | 701 FORT HILL RD | 161 | MAY | 2022-10-18 | U461478 | U134723 | 2022-04-19 | 2022-12-30 |  |  | DAVID STAGGS | 2022-09-09 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1584.5 | 0 | 0 | 0 | 1584.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22998828700 |  | 100301210 |  | 6716212E |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2600B | DELMONT | 151< DELMONT DR | 067 | LEX | 2022-09-09 | U128816 | U134723 | 2022-05-05 | 2022-12-20 |  |  | OLIVER MAYNARD | 2022-09-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.0667 | 0 | 201.68 | 191.01 | 0 | 10.67 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 03530771200 |  | 100297651 |  | 6716212H |  |  |  | 566 | EX | ABANDON SL - SOII/INSIDE | 2621P | LIMESTONE | 255 N LIMESTONE ST | 067 | LEX | 2022-09-12 | RSTRONG | DMCCULL | 2003-02-12 | 2022-09-12 |  |  | RSTRONG | 2022-09-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.16667 | 1 | 12.36 | 11.39 | 0 | 0.97 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 06653328400 |  | 100325028 |  | 6720204A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | GREENTREE | 3495 GREENTREE RD | 067 | LEX | 2022-09-13 | U125881 | SSUTHER | 2006-07-11 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-09-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 5949.34 | 0 | 0 | 0 | 5949.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 08762118300 |  | 500064950 | 19 | V-919/27 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | LEESTOWN | 3795 LEESTOWN RD | 067 | LEX | 2022-09-12 | U125881 | RSTOKLE | 2008-12-05 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-09-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 10819896800 |  | 100337933 | 33 | 6712220M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | LEESTOWN | 3885 LEESTOWN RD | 067 | LEX | 2022-09-12 | U125881 | RSTOKLE | 2010-01-15 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-09-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11878467500 |  | 100302718 |  | 6712212K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | VERSAILLES | 2516 VERSAILLES RD | 067 | LEX | 2022-09-12 | U128816 | U906307 | 2011-01-11 | 2022-07-01 | 2022-12-31 |  | OLIVER MAYNARD | 2022-09-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 4425.65 | 626.18 | 239.5 | 34.93 | 3525.04 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11915919700 |  | 100343766 |  | 7240204J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEVEE | 1004 LEVEE RD | 173 | MT | 2022-09-12 | DENNING | U124964 | 2011-07-14 | 2022-07-01 | 2022-12-31 |  | DENNING | 2022-09-12 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9.2333 | 3 | 4182.66 | 607.02 | 0 | 34.9 | 3540.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11916280500 |  | 100335635 |  | 16720212K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WINCHESTER | 1205 WINCHESTER RD | 067 | LEX | 2022-09-13 | U125208 | U124964 | 2011-07-18 | 2022-07-01 | 2022-12-31 |  | RSTRONG | 2022-09-12 | 2022-09-01 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.91667 | 3 | 2512.5 | 61.5 | 175.14 | 5.19 | 2270.67 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11922363300 |  | 500645774 |  | 16708220P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | LEESTOWN | 3888 LEESTOWN RD | 067 | LEX | 2022-09-12 | U125881 | U907001 | 2011-08-30 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-09-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18026843400 |  |  |  | 6716212L | 1858813 | U461383 |  | 558 | EX | RETIRE 2670' OF 3"/6"CILP MAIN | 2600B | M L KING | M L KING | 067 | LEX | 2022-10-03 | U460266 | U461383 | 2018-10-29 | 2022-12-01 | 2022-12-01 | 2022-09-07 | LESLIE SHARON | 2022-09-12 | 2022-05-25 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP8434 | AMRCB |  | 100 | 055832180268434 | 0.016667 | 0 | 598.25 | 98.75 | 0 | 19.5 | 480 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916441900 |  | 100411560 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2649 MAIN ST W | 019 | ASH | 2022-09-12 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2611.06 | 0 | 0 | 0 | 2611.06 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959033700 |  | 100315226 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | CONN TER | 240 CONN TER 1 | 067 | LEX | 2022-09-12 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-09-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.3333 | 1 | 2946.46 | 534.98 | 0 | 109.19 | 2302.29 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959043900 |  | 100315221 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | JOURNAL | 923 JOURNAL HL | 067 | LEX | 2022-09-12 | U461423 | U134723 | 2021-12-10 | 2022-12-30 |  |  | KKOUNS | 2022-09-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.6667 | 2 | 3498.67 | 519.38 | 0 | 479.65 | 2499.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026200500 |  | 100336378 |  | 6720212I | 1858813 | U461383 |  | 566 | EX | RETIRE 2' OF 3"PLP S/L | 2600B | 3RD | 213 E 3RD ST | 067 | LEX | 2022-10-04 | U460266 | U461383 | 2022-06-07 | 2022-11-01 | 2022-11-01 | 2022-08-15 | LESLIE SHARON | 2022-09-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP2005 |  |  | 100 | 056632220262005 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026210600 |  |  |  | 6720212B | 2289965 | U461383 |  | 558 | EX | EMER-RETIRE 50' OF 3"BSLP MAIN | 2621P | LIMESTONE | LIMESTONE | 067 | LEX | 2022-09-29 | U460266 | U461383 | 2022-07-08 | 2022-11-01 | 2022-11-01 | 2022-07-10 | LSTANFIELD | 2022-09-12 | 2022-09-12 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2106 | AMRCB |  | 100 | 055832220262106 | 1.9333 | 0 | 2854.75 | 2368.96 | 339.46 | 146.33 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026211500 |  |  |  | 6744208I | 2290075 | U128885 |  | 557 | EX | EMER-INSTALL 5'-2" PMMP | 2621P | STRODE STATION | 164 STRODE STATION CR | 049 | WIN | 2022-09-19 | U128132 | U128885 | 2022-07-13 | 2022-07-08 | 2022-07-10 | 2022-07-11 | WDENNING | 2022-09-12 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP2115 |  |  | 100 | 055732220262115 |  | 2 | 5656.19 | 0 | 0 | 38.36 | 5319.6 | 0 | 0 | 298.23 | 2
KY | KY - CENTRAL | 2629 | 22026211600 |  |  |  | 6744208I | 2290075 | U128885 |  | 558 | EX | EMER-RETIRE 5'-2" PMMP | 2621P | STRODE STATION | 164 STRODE STATION CR | 049 | WIN | 2022-09-19 | U128132 | U128885 | 2022-07-13 | 2022-07-07 | 2022-07-10 | 2022-07-11 | WDENNING | 2022-09-12 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP2116 |  |  | 100 | 055832220262116 |  | 0 | 3884.45 | 3626.56 | 0 | 257.89 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026221200 |  |  |  | 6716212F | 2291287 | U122858 |  | 557 | EX | EMER - INSTALL 8'-6"PMMP | 2621P | MANCHESTER | 1228 MANCHESTER | 067 | LEX | 2022-09-28 | U460266 | U122858 | 2022-09-02 | 2022-10-28 | 2022-11-01 | 2022-08-31 | LSTANFI | 2022-09-12 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2212 |  |  | 100 | 055732220262212 | 3.95 | 6 | 11736.48 | 6013.81 | 257.03 | 359.81 | 3340 | 0 | 0 | 1765.83 | 3
KY | KY - WEST | 2621 | 22026221300 |  |  |  | 6716212F | 2291287 | U122858 |  | 558 | EX | EMER - RETIRE 8'-6" PMP | 2621P | MANCHESTER | 1228 MANCHESTER | 067 | LEX | 2022-09-28 | U460266 | U122858 | 2022-09-02 | 2022-11-01 | 2022-11-01 | 2022-08-31 | LSTANFI | 2022-09-12 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2213 |  |  | 100 | 055832220262213 | 7.2833 | 0 | 595.27 | 550.73 | 0 | 44.54 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026222800 |  |  |  | 6720212B | 2291435 | U461383 |  | 557 | EX | EMER-INSTALL 2' OF 4"PMMP MAIN | 2621P | LIMESTONE | 820 N LIMESTONE ST | 067 | LEX | 2022-09-19 | U460266 | U461383 | 2022-09-07 | 2023-05-26 |  | 2022-08-11 | LSTANFIELD | 2022-09-12 | 2022-09-12 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2228 |  |  | 100 | 055732220262228 | 2.5 | 2 | 21988.24 | 9225.28 | 108.5 | 5303.26 | 4011.88 | 0 | 0 | 3339.32 | 2
KY | KY - WEST | 2621 | 22026222900 |  |  |  | 6720212B | 2291435 | U461383 |  | 558 | EX | EMER-RETIRE 2' OF 4"PMMP MAIN | 2621P | LIMESTONE | 820 N LIMESTONE ST | 067 | LEX | 2022-09-19 | U460266 | U461383 | 2022-09-07 | 2023-05-31 |  | 2022-08-11 | LSTANFIELD | 2022-09-12 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2229 |  |  | 100 | 055832220262229 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22111845600 |  | 100331674 |  | 6720212N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311881 | 2621P | RICHMOND | 27 RICHMOND AV | 067 | LEX | 2022-09-13 | U125208 | U125208 | 2022-06-22 | 2022-12-21 | 2024-06-30 |  | RSTRONG | 2022-09-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.6667 | 1 | 2708.78 | 509.85 | 189.5 | 42.96 | 1966.47 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22112121300 |  | 100273576 |  | 6680224C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311851 | 2621P | HAWKEEGAN | 246 HAWKEEGAN DR | 073 | FRA | 2022-09-12 | DCOLLIN | U125208 | 2022-06-23 | 2022-08-24 | 2024-06-30 |  | DCOLLIN | 2022-09-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.05 | 1 | 2192.86 | 342 | 302.32 | 38.3 | 1510.24 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22113724400 |  | 100420342 |  | 6684228I |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311862 | 2621P | PIERCE | 531 PIERCE LN | 073 | FRA | 2022-09-13 | UIPBOT03 | U125208 | 2022-07-01 | 2022-09-12 | 2024-06-30 |  | DCOLLIN | 2022-09-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.95 | 1 | 2823.94 | 267.47 | 233.31 | 29.94 | 2293.22 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22125019300 |  | 100241602 |  | 7356256B |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | CARTER | 1901< CARTER AV RR | 019 | ASH | 2022-09-12 | RECUMP | U132002 | 2022-08-18 | 2022-09-01 | 2022-09-17 |  | RECUMP | 2022-09-12 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 7.8333 | 3 | 450.37 | 399.02 | 28.63 | 22.72 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22125020200 |  | 100241603 |  | 7356256B |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | CARTER | 1901 CARTER AV | 019 | ASH | 2022-09-13 | U125208 | U132002 | 2022-08-18 | 2022-09-01 | 2022-09-17 |  | RECUMP | 2022-09-12 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 7.7833 | 1 | 541.85 | 472.1 | 28.63 | 41.12 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129009100 |  | 100258711 |  | 7356256F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MONTGOMERY | 2501 MONTGOMERY AV | 019 | ASH | 2022-09-12 | U123965 | U130722 | 2022-09-05 | 2022-09-09 |  |  | MBLANKE | 2022-09-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.05 | 1 | 2535.76 | 211.79 | 0 | 50.41 | 2273.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129011300 |  | 100250033 |  | 7360252M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OAKLAND | 3110 OAKLAND AV | 019 | CAT | 2022-09-12 | U123965 | U130722 | 2022-09-05 | 2022-09-09 |  |  | MBLANKE | 2022-09-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.95 | 1 | 2045.09 | 311.15 | 0 | 74.04 | 1659.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129016200 |  | 100316256 |  | 6716208F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PICADOME | 309 PICADOME PR | 067 | LEX | 2022-09-19 | U129731 | U130722 | 2022-09-05 | 2022-12-30 |  |  | F.GOINS | 2022-09-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1708.57 | 0 | 0 | 0 | 1708.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129017700 |  | 500494279 |  | 6712204L | 9610755 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WILLOW RIDGE | 3740 WILLOW RIDGE RD | 067 | LEX | 2022-09-13 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129049900 |  | 100318763 |  | 6716204B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | EDINBURGH | 2909 EDINBURGH DR | 067 | LEX | 2022-09-12 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129050100 |  | 100420263 |  | 6720204F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HOT SPRINGS | 1261 HOT SPRINGS CT | 067 | LEX | 2022-09-13 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129079200 |  | 100320206 |  | 6716208G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SHADY | 204 SHADY LN | 067 | LEX | 2022-09-19 | U129731 | U130722 | 2022-09-05 | 2022-12-30 |  |  | F.GOINS | 2022-09-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1878.7 | 0 | 0 | 0 | 1878.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129079300 |  | 100320161 |  | 6716208K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | TAHOMA | 221 TAHOMA RD | 067 | LEX | 2022-09-19 | U129731 | U130722 | 2022-09-05 | 2022-12-30 |  |  | F.GOINS | 2022-09-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.1167 | 1 | 2116.53 | 197.02 | 0 | 40.81 | 1878.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129169900 |  | 100336919 |  | 6720212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311443 | 2621P | M L KING | 435 M L KING BV 1F | 067 | LEX | 2022-09-13 | U930915 | U125208 | 2022-09-06 | 2022-09-12 | 2022-09-27 |  | TROE | 2022-09-12 | 2022-09-12 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.7 | 4 | 2259.65 | 1650.11 | 480.04 | 92.1 | 37.4 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129205300 |  | 501133085 |  | 6760172L | 1316108 |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | WISEMANTOWN | 2294 WISEMANTOWN RD | 065 | IRV | 2022-09-12 | DENNING | U132002 | 2022-09-06 | 2022-09-20 | 2022-10-06 |  | DENNING | 2022-09-12 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 11.2333 | 2 | 1127.98 | 785.65 | 0 | 342.33 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22130683000 |  | 100331947 |  | 6720212M | 2180410 |  |  | 565 | EX | REPLACE SL W/21026126800 | 2600B | MAIN | 735 E MAIN ST | 067 | LEX | 2022-09-13 | U129722 | U134723 | 2022-09-12 | 2022-12-30 |  |  | M YOUNG | 2022-09-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2848.13 | 0 | 0 | 0 | 2848.13 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22130687400 |  | 100431716 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400 | 2600B | MAIN | 2660 MAIN ST W 2 | 019 | ASH | 2022-09-12 | U124015 | U125768 | 2022-09-12 | 2049-12-31 |  |  | ORA SLONE | 2022-09-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2102.7 | 0 | 0 | 0 | 2102.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22130770800 |  | 100254174 |  | 7348264N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | COLLINS | 1215 W COLLINS ST | 089 | FLA | 2022-09-12 | MCOLLET | U136526 | 2022-09-12 | 2022-09-12 | 2022-09-12 |  | MCOLLET | 2022-09-12 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 11.5 | 3 | 1361.1 | 708.35 | 182.72 | 407.33 | 62.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983422500 |  | 100324756 |  | 6720204B | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 3392 GREENTREE PL | 067 | LEX | 2022-09-12 | U126530 | U134723 | 2022-03-03 | 2022-12-30 |  |  | JDUNN | 2022-09-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1337.69 | 0 | 0 | 0 | 1337.69 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983422900 |  | 100324757 |  | 6720204B | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 3384 GREENTREE RD | 067 | LEX | 2022-09-12 | U126530 | U134723 | 2022-03-03 | 2022-12-30 |  |  | JDUNN | 2022-09-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1067.68 | 0 | 0 | 0 | 1067.68 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22994326000 |  | 100353549 |  | 7256280K | 2180424 |  |  | 565 | EX | REPLACE SL W/21-0261272-00 | 2600B | LEXINGTON | 301 LEXINGTON PK | 161 | MAY | 2022-09-13 | U126286 | U134723 | 2022-04-19 | 2022-12-30 |  |  | TYLER ALLISON | 2022-09-12 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 3556 | 0 | 0 | 0 | 3556 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22994326200 |  | 100353558 |  | 7256280K | 2180424 |  |  | 565 | EX | REPLACE SL W/21-0261272-00 | 2600B | LEXINGTON | 355 LEXINGTON PK | 161 | MAY | 2022-09-13 | U126286 | U134723 | 2022-04-19 | 2022-12-30 |  |  | TYLER ALLISON | 2022-09-12 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 | 8 | 1 | 2412.43 | 488.47 | 0 | 27.25 | 1896.71 | 0 | 0 | 0
KY | KY - WEST | 2621 | 02523364300 |  | 100422378 |  | 670000000 | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | ROYSTER | 3659 ROYSTER RD | 067 | LEX | 2022-09-20 | U125881 | DMCCULL | 2002-11-25 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-09-13 | 2007-02-28 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.75 | 1 | 1594.09 | 33.11 | 0 | 7.73 | 1553.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 10866396600 |  | 100453183 | 36 | ? |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | FONTAINE | 2077 FONTAINE RD 1 | 067 | LEX | 2022-09-13 | U127206 | LABRAMS | 2010-10-27 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2881.16 | 0 | 0 | 0 | 2881.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 10866413600 |  | 100453245 | 43 | 6 |  |  |  | 566 | EX | ABANDON SL- I/I/LGCY | 2600B | FONTAINE | 2077 FONTAINE RD 2 | 067 | LEX | 2022-09-13 | U127206 | LABRAMS | 2010-10-27 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 10866707200 |  | 100453186 | 36 | 000000 |  |  |  | 566 | EX | ABANDON SL- I/I/LGCY | 2600B | FONTAINE | 2077 FONTAINE RD 5 | 067 | LEX | 2022-09-13 | U127206 | U463032 | 2010-10-29 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - CENTRAL | 2629 | 21883201900 |  | 100359105 |  | 6740232M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 8TH | 144 W 8TH ST | 017 | PAR | 2022-09-26 | U123111 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | LYN STAFFORD | 2022-09-13 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - EAST | 2631 | 21916450000 |  | 100263478 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | WESTVIEW | 636 WESTVIEW DR | 019 | ASH | 2022-09-13 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1717.56 | 0 | 0 | 0 | 1717.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916450200 |  | 100263479 |  | 7341145B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | WESTVIEW | 640 WESTVIEW DR | 019 | ASH | 2022-09-13 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1708.55 | 0 | 0 | 0 | 1708.55 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958593300 |  | 100331943 |  | 6720212M | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 117 N ASHLAND AV | 067 | LEX | 2022-09-13 | U129722 | U134723 | 2021-12-08 | 2022-12-30 |  |  | M YOUNG | 2022-09-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1879.32 | 0 | 0 | 0 | 1879.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958593500 |  | 100331940 |  | 6720212M | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 133 N ASHLAND AV | 067 | LEX | 2022-09-13 | U129722 | U134723 | 2021-12-08 | 2022-12-30 |  |  | M YOUNG | 2022-09-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4078.3 | 0 | 0 | 0 | 4078.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959033300 |  | 100315214 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | CONN TER | 225 CONN TER | 067 | LEX | 2022-09-13 | U461423 | U134723 | 2021-12-10 | 2022-12-30 |  |  | KKOUNS | 2022-09-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 3034.97 | 478.57 | 0 | 450.85 | 2105.55 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959033600 |  | 100315228 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | CONN TER | 232 CONN TER A | 067 | LEX | 2022-09-13 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-09-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2015.4 | 513.76 | 0 | 71.53 | 1430.11 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22026198700 |  |  |  | 7352252B | 2289296 | U122858 |  | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2621M | BOY SCOUT | 100 BOY SCOUT RD | 019 | ASH | 2022-09-27 | U460266 | U136124 | 2022-06-06 | 2022-12-30 | 2022-12-31 | 2022-09-13 | SGIORDANO | 2022-09-13 | 2022-09-13 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP1987 |  |  | 100 | 090932220261987 | 9.1 | 0 | 6293.17 | 577.6 | 0 | 514.69 | 5174.3 | 0 | 26.58 | 0
KY | KY - EAST | 2631 | 22026198800 |  |  |  | 7352252B | 2289296 | U122858 |  | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2621M | BOY SCOUT | 100 BOY SCOUT RD | 019 | ASH | 2022-09-27 | U460266 | U136124 | 2022-06-06 | 2022-12-30 | 2022-12-31 | 2022-09-13 | SGIORDANO | 2022-09-13 | 2022-09-13 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00910 | 3200910 |  |  | WP1988 |  |  | 100 | 091032220261988 | 8.3833 | 0 | 1014.14 | 538.7 | 0 | 475.44 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127674100 |  | 100290684 |  | 6720212B |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTRQD | 2621P | BROADVIEW | 206 BROADVIEW DR | 067 | LEX | 2022-09-14 | U125208 | U132002 | 2022-08-30 | 2022-09-12 | 2022-09-28 |  | RJCRAWF | 2022-09-13 | 2022-09-09 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.4167 | 5 | 864 | 707.45 | 117.05 | 39.5 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129016300 |  | 100300662 |  | 6716212J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | VERSAILLES | 1405 VERSAILLES RD RR | 067 | LEX | 2022-09-13 | U126602 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DEREK PAYTON | 2022-09-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 5396.11 | 592.94 | 0 | 33.08 | 4770.09 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129017900 |  | 100277616 |  | 6688228E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ALLNUTT | 132 ALLNUTT DR | 073 | FRA | 2022-09-13 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-13 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1957.17 | 0 | 0 | 0 | 1957.17 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129018000 |  | 100277620 |  | 6688228E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ALLNUTT | 138 ALLNUTT DR | 073 | FRA | 2022-09-13 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-13 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129047900 |  | 100337244 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | M L KING | 530 N M L KING BV | 067 | LEX | 2022-09-14 | U125208 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RSTRONG | 2022-09-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.3833 | 1 | 1100.87 | 91.53 | 146.51 | 7.73 | 855.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129048700 |  | 100299691 |  | 6716212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LEESTOWN | 1408 LEESTOWN RD | 067 | LEX | 2022-09-20 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129050200 |  | 100418237 |  | 6720204F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KEENELAND | 1233 KEENELAND CT | 067 | LEX | 2022-09-20 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129051300 |  | 500780342 |  | 6688232N | 9402970 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BLUERIDGE | 207 BLUERIDGE DR | 073 | FRA | 2022-09-13 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-13 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1784.75 | 0 | 0 | 0 | 1784.75 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129052500 |  | 100280960 |  | 6684228L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HARDY | 317 HARDY ST | 073 | FRA | 2022-09-13 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-13 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129084600 |  | 100337669 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | M L KING | 652 M L KING BV | 067 | LEX | 2022-09-14 | U125208 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RSTRONG | 2022-09-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.2333 | 1 | 1180.17 | 148.35 | 164.23 | 12.49 | 855.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129087100 |  | 100325138 |  | 6720204A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DIXIANA | 3436 DIXIANA DR | 067 | LEX | 2022-09-13 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129087700 |  | 500330838 |  | 6688232N | 9402970 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BLUERIDGE | 220 BLUERIDGE DR | 073 | FRA | 2022-09-13 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-13 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129087800 |  | 100466045 |  | 6688228I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | COLLEGE PARK | 325 COLLEGE PARK DR | 073 | FRA | 2022-09-13 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-13 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1535.48 | 0 | 0 | 0 | 1535.48 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129892800 |  | 500226533 |  | 7344264L |  |  |  | 565 | EX | SERVICE LINE - RELOCATE | 2621P | DEER CREEK | 3239 DEER CREEK CT | 089 | FLA | 2022-09-13 | JCYRUS | U125208 | 2022-09-08 | 2022-09-13 | 2022-09-29 |  | JCYRUS | 2022-09-13 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 26.5667 | 4 | 1882.32 | 1514.68 | 174.58 | 99.56 | 93.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22130689100 |  | 100264063 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400 | 2600B | MAIN | 2660 MAIN ST 3WWD | 019 | ASH | 2022-09-13 | U124015 | U125768 | 2022-09-12 | 2049-12-31 |  |  | ORA SLONE | 2022-09-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2085.83 | 0 | 0 | 0 | 2085.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22130778200 |  | 500579907 |  | 6720212E |  |  |  | 566 | EX | SERVICE LINE ABANDON | 2621P | M L KING | 435 M L KING BV 3F | 067 | LEX | 2022-09-13 | LSTONE | U136526 | 2022-09-12 | 2022-09-12 |  |  | LSTONE | 2022-09-13 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 4.6333 | 2 | 349.03 | 330.56 | 0 | 18.47 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22130880700 |  | 500952327 |  | 6712208P |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | CLAYS MILL | 3340 CLAYS MILL RD STE 140 | 067 | LEX | 2022-09-14 | U127206 | U125763 | 2022-09-13 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 958.36 | 602.79 | 0 | 33.63 | 321.94 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22970119600 |  | 100280376 |  | 6684228N | 2181158 |  |  | 565 | EX | REPLACE SL W/21-0261319-00 | 2600B | LYONS | 132 LYONS DR | 073 | FRA | 2022-09-13 | U128410 | U134723 | 2022-01-27 | 2022-12-30 |  |  | CDESPAIN | 2022-09-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3374.44 | 0 | 0 | 0 | 3374.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22979177300 |  | 100453184 |  | 6720208G |  |  |  | 566 | EX | ABANDON SL- I/I/LGCY | 2600B | FONTAINE | 2077 FONTAINE RD 3 | 067 | LEX | 2022-09-13 | U127206 | U134723 | 2022-02-18 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 22979177500 |  | 100453185 |  | 6720208G |  |  |  | 566 | EX | ABANDON SL- I/I/LGCY | 2600B | FONTAINE | 2077 FONTAINE RD 4 | 067 | LEX | 2022-09-13 | U127206 | U134723 | 2022-02-18 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 22979178300 |  | 100453219 |  | 6720208G |  |  |  | 566 | EX | ABANDON SL- I/I/LGCY | 2600B | FONTAINE | 2077 FONTAINE RD 6 | 067 | LEX | 2022-09-13 | U127206 | U134723 | 2022-02-18 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 321.94 | 0 | 0 | 0 | 321.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22979178500 |  | 100453187 |  | 6720208G |  |  |  | 566 | EX | ABANDON SL- I/I/LGCY | 2600B | FONTAINE | 2077 FONTAINE RD 7 | 067 | LEX | 2022-09-13 | U127206 | U134723 | 2022-02-18 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 22979182500 |  | 100453188 |  | 6720208G |  |  |  | 566 | EX | ABANDON SL- I/I/LGCY | 2600B | FONTAINE | 2077 FONTAINE RD 8 | 067 | LEX | 2022-09-13 | U127206 | U134723 | 2022-02-18 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 321.94 | 0 | 0 | 0 | 321.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22979189700 |  | 100453189 |  | 6720208G |  |  |  | 566 | EX | ABANDON SL- I/I/LGCY | 2600B | FONTAINE | 2077 FONTAINE RD 9 | 067 | LEX | 2022-09-13 | U127206 | U134723 | 2022-02-18 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 22979190800 |  | 100453190 |  | 6720208G |  |  |  | 566 | EX | ABANDON SL- I/I/LGCY | 2600B | FONTAINE | 2077 FONTAINE RD 10 | 067 | LEX | 2022-09-13 | U127206 | U134723 | 2022-02-18 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 22979191100 |  | 100453191 |  | 6720208G |  |  |  | 566 | EX | ABANDON SL- I/I/LGCY | 2600B | FONTAINE | 2077 FONTAINE RD 11 | 067 | LEX | 2022-09-13 | U127206 | U134723 | 2022-02-18 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 22979191400 |  | 100453192 |  | 6720208G |  |  |  | 566 | EX | ABANDON SL- I/I/LGCY | 2600B | FONTAINE | 2077 FONTAINE RD 12 | 067 | LEX | 2022-09-13 | U127206 | U134723 | 2022-02-18 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 22983422000 |  | 100324762 |  | 6720204B | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 1123 GREENTREE CT | 067 | LEX | 2022-09-13 | U461309 | U134723 | 2022-03-03 | 2022-12-30 |  |  | R.HUMPHREYS | 2022-09-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10 | 1 | 2431.69 | 594.26 | 347.84 | 128.4 | 1361.19 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22994324300 |  | 100353523 |  | 7256280K | 2180424 |  |  | 565 | EX | REPLACE SL W/21-0261272-00 | 2600B | 3RD | 249 W 3RD ST | 161 | MAY | 2022-09-13 | U126286 | U134723 | 2022-04-19 | 2022-12-30 |  |  | TYLER ALLISON | 2022-09-13 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 3723.17 | 0 | 0 | 0 | 3723.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 06656810600 |  | 100308300 |  | 6716212N0 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BROADWAY | 1017 S BROADWAY ST 2F | 067 | LEX | 2022-09-28 | U126602 | SSUTHER | 2006-08-14 | 2022-07-01 | 2022-12-31 |  | DEREK PAYTON | 2022-09-14 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 21883145900 |  | 100456651 |  | V-930-57 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WELLINGTON | 616 WELLINGTON WY B | 067 | LEX | 2022-09-14 | U127206 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-09-14 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 321.94 | 0 | 0 | 0 | 321.94 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916448600 |  | 100263484 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | WESTVIEW | 602 WESTVIEW DR | 019 | ASH | 2022-09-14 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1755.92 | 0 | 0 | 0 | 1755.92 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916449300 |  | 100263482 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | WESTVIEW | 622 WESTVIEW DR | 019 | ASH | 2022-09-14 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1656.85 | 0 | 0 | 0 | 1656.85 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916450300 |  | 100263481 |  | 7341145B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | WESTVIEW | 650 WESTVIEW DR | 019 | ASH | 2022-09-14 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1927.64 | 0 | 0 | 0 | 1927.64 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916453500 |  | 100263480 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | WESTVIEW | 652 WESTVIEW DR | 019 | ASH | 2022-09-14 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2320.08 | 0 | 0 | 0 | 2320.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958593100 |  | 100331945 |  | 6720212M | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 111 N ASHLAND AV | 067 | LEX | 2022-09-15 | U126308 | U134723 | 2021-12-08 | 2022-12-30 |  |  | J ENSMINGER | 2022-09-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1882.22 | 0 | 0 | 0 | 1882.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958593200 |  | 100331944 |  | 6720212M | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 115 N ASHLAND AV | 067 | LEX | 2022-09-15 | U126308 | U134723 | 2021-12-08 | 2022-12-30 |  |  | J ENSMINGER | 2022-09-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2775.63 | 0 | 0 | 0 | 2775.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959032800 |  | 100315210 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | CONN TER | 209 CONN TER | 067 | LEX | 2022-09-14 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-09-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2611.14 | 513.76 | 0 | 69.63 | 2027.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959033500 |  | 100315230 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | CONN TER | 228 CONN TER | 067 | LEX | 2022-09-15 | U461423 | U134723 | 2021-12-10 | 2022-12-30 |  |  | KKOUNS | 2022-09-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2611.94 | 478.57 | 0 | 450.85 | 1682.52 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22026200900 |  |  |  | 7348248E | 2289377 | U122858 |  | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2621M | PAUL COFFEY | PAUL COFFEY BV | 019 | CAN | 2022-09-21 | U123258 | U136124 | 2022-06-08 | 2022-12-30 | 2022-12-31 | 2022-09-14 | S.GIORDANO | 2022-09-14 | 2022-09-14 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP2009 |  |  | 100 | 090932220262009 | 7.7 | 0 | 6137.4 | 501.99 | 0 | 434.67 | 5174.3 | 0 | 26.44 | 0
KY | KY - EAST | 2631 | 22026201000 |  |  |  | 7348248E | 2289377 | U122858 |  | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2621M | PAUL COFFEY | PAUL COFFEY BV | 019 | CAN | 2022-09-21 | U123258 | U136124 | 2022-06-08 | 2022-12-30 | 2022-12-31 | 2022-09-14 | S.GIODANO | 2022-09-14 | 2022-09-14 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00910 | 3200910 |  |  | WP2010 |  |  | 100 | 091032220262010 | 3.9333 | 0 | 485.58 | 261.05 | 0 | 224.53 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026222300 |  |  |  | 6736252M | 2291399 | U128885 |  | 557 | EX | EMER - INSTALL 7'-4" PMLP | 2621P | PLEASANT | PLEASANT | 097 | CYN | 2022-10-10 | U128132 | U128885 | 2022-09-07 | 2022-09-29 | 2022-09-30 | 2022-08-29 | NRICHIE | 2022-09-14 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP2223 |  |  | 100 | 055732220262223 |  | 7 | 13873.55 | 2690.06 | 642.59 | 428.2 | 7748.49 | 0 | 0 | 2364.21 | 7
KY | KY - CENTRAL | 2629 | 22026222400 |  |  |  | 6736252M | 2291399 | U128885 |  | 558 | EX | EMER - RETIRE 7'-4" PLP | 2621P | PLEASANT | PLEASANT | 097 | CYN | 2022-09-21 | U128132 | U128885 | 2022-09-07 | 2022-09-30 | 2022-09-30 | 2022-08-29 | NRICHIE | 2022-09-14 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP2224 |  |  | 100 | 055832220262224 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22124324900 |  | 100436758 |  | 6720208P | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER | 2621D | HIDDEN POINT | 628 HIDDEN POINT DR | 067 | LEX | 2022-09-14 | WISHII | AOC SYST | 2022-08-16 | 2022-09-15 | 2022-10-15 |  | WISHII | 2022-09-14 | 2022-08-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 36.2333 | 12 | 2215.79 | 1904.64 | 0 | 244.05 | 67.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127017200 |  | 500568661 |  | 6704204O | 9616899 |  |  | 566 | EX | ABANDON SL- DEMO/CUST REQ | 2621P | WOODS | 1489 WOODS RD | 113 | NIC | 2022-09-14 | LSTONE | KWELLS | 2022-08-26 | 2022-09-07 | 2022-09-23 |  | LSTONE | 2022-09-14 | 2022-09-09 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 39.0333 | 10 | 3877.35 | 2486.86 | 1.37 | 138.79 | 1250.33 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22127684400 |  | 500025735 |  | 7356256C |  |  |  | 565 | EX | NBT - SERVICE LINE/MTR UPG 2" | 2621P | GREENUP | 2548 GREENUP AV | 019 | ASH | 2022-09-14 | MCOLLET | U125208 | 2022-08-30 | 2022-08-29 | 2022-09-09 |  | MCOLLET | 2022-09-14 | 2022-09-12 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 92.4333 | 12 | 8673.29 | 5552.97 | 718.32 | 2320.6 | 81.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129018200 |  | 100467641 |  | 6680228H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CLIFTON | 812 CLIFTON DR LS | 073 | FRA | 2022-09-14 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-14 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1984.56 | 0 | 0 | 0 | 1984.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129043400 |  | 100315665 |  | 6716208C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NICHOLASVILLE | 1529 NICHOLASVILLE RD 1 | 067 | LEX | 2022-09-14 | U127206 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-14 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 321.94 | 0 | 0 | 0 | 321.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129043600 |  | 100438940 |  | 6716208C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NICHOLASVILLE | 1529 NICHOLASVILLE RD 4 | 067 | LEX | 2022-09-14 | U127206 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-14 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 958.36 | 602.79 | 0 | 33.63 | 321.94 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129050600 |  | 100271752 |  | 6684228K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 2ND | 221 E 2ND ST 1F | 073 | FRA | 2022-09-15 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-14 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1779.17 | 0 | 0 | 0 | 1779.17 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129050800 |  | 100276758 |  | 6684228D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 5TH | 830 5TH AV | 073 | FRA | 2022-09-15 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-14 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129050900 |  | 100276764 |  | 6684228D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 5TH | 926 5TH AV | 073 | FRA | 2022-09-15 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-14 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1176.73 | 0 | 0 | 0 | 1176.73 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129051000 |  | 100276783 |  | 6684228D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 5TH | 917 5TH AV | 073 | FRA | 2022-09-15 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-14 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129051700 |  | 100278173 |  | 6688228B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CHEYENNE | 1009 CHEYENNE TL | 073 | FRA | 2022-09-14 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-14 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1535.48 | 0 | 0 | 0 | 1535.48 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129052000 |  | 500313024 |  | 6680228P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DONALYNN | 236 DONALYNN DR | 073 | FRA | 2022-09-15 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-14 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1671.02 | 0 | 0 | 0 | 1671.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129079400 |  | 100309477 |  | 6712208O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WELLINGTON | 729 WELLINGTON WY | 067 | LEX | 2022-09-19 | U126602 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DEREK PAYTON | 2022-09-14 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 3695.63 | 592.94 | 0 | 33.08 | 3069.61 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129084500 |  | 100336921 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | M L KING | 425 N M L KING BV | 067 | LEX | 2022-09-15 | U125208 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RSTRONG | 2022-09-14 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.8667 | 1 | 1302.78 | 192.44 | 244.49 | 10.75 | 855.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129087600 |  | 100276882 |  | 6684228D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 1ST | 912 1ST AV | 073 | FRA | 2022-09-15 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-14 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129088000 |  | 500026770 |  | 6684228H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DOUGLAS | 126 DOUGLAS AV | 073 | FRA | 2022-09-15 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-14 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129415100 |  | 100315357 |  | 6716208C |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | CRESCENT | 1205 CRESCENT AV | 067 | LEX | 2022-09-15 | U125208 | U132002 | 2022-09-07 | 2022-09-21 | 2022-10-07 |  | RSTRONG | 2022-09-14 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.9833 | 1 | 1239.33 | 332.09 | 33.6 | 18.54 | 855.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22130697900 |  | 100335766 |  | 6720212H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311177 | 2621P | INDUSTRY | 1290 INDUSTRY RD | 067 | LEX | 2022-09-15 | UIPBOT05 | U125208 | 2022-09-12 | 2022-09-12 | 2022-09-30 |  | HMCKUNE | 2022-09-14 | 2022-09-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 28.2833 | 5 | 1809.15 | 1578.65 | 133.57 | 88.13 | 8.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22131156500 |  | 100436917 |  | 6720208P |  |  |  | 565 | EX | GRADE ONE LEAK | 2621P | HIDDEN POINT | 608 HIDDEN POINT DR | 067 | LEX | 2022-09-15 | UIPBOT05 | U124447 | 2022-09-14 | 2022-09-14 | 2022-09-14 |  | LSTANFI | 2022-09-14 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.8333 | 3 | 1183.6 | 856.01 | 199.26 | 56.83 | 71.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22131238100 |  | 100353367 |  | 7256280G |  |  |  | 565 | EX | RPLC SVC W/ 21-0261272-00 | 2600B | 2ND | 560 W 2ND ST | 161 | MAY | 2022-09-14 | U126286 | U126286 | 2022-09-14 | 2022-09-14 |  |  | TYLER ALLISON | 2022-09-14 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 | 8 | 1 | 4314.23 | 488.47 | 0 | 27.25 | 3798.51 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22131267100 |  | 100271751 |  | 6684228K |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | 2ND | 221 E 2ND ST 2F | 073 | FRA | 2022-09-15 | U125881 | U125763 | 2022-09-14 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-14 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 0 | 343.68 | 0 | 0 | 0 | 343.68 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22970122200 |  | 100280379 |  | 6684228N | 2181158 |  |  | 565 | EX | REPLACE SL W/21-0261319-00 | 2600B | LYONS | 118 LYONS DR | 073 | FRA | 2022-09-14 | U128410 | U134723 | 2022-01-27 | 2022-12-30 |  |  | CDESPAIN | 2022-09-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3218.22 | 0 | 0 | 0 | 3218.22 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22979029800 |  | 100277621 |  | 6688228E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ALLNUTT | 140 ALLNUTT DR | 073 | FRA | 2022-09-14 | U135195 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | KEITH HEDGES | 2022-09-14 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22979029900 |  | 100277622 |  | 6688228E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ALLNUTT | 142 ALLNUTT DR | 073 | FRA | 2022-09-14 | U135195 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | KEITH HEDGES | 2022-09-14 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983422100 |  | 100324761 |  | 6720204B | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 1127 GREENTREE CT | 067 | LEX | 2022-09-14 | U461309 | U134723 | 2022-03-03 | 2022-12-30 |  |  | R.HUMPHREYS | 2022-09-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10 | 1 | 2496.95 | 594.26 | 314.87 | 128.4 | 1459.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983423000 |  | 100324760 |  | 6720204B | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 3387 GREENTREE RD | 067 | LEX | 2022-09-14 | U126530 | U134723 | 2022-03-03 | 2022-12-30 |  |  | JDUNN | 2022-09-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 5434.17 | 0 | 0 | 0 | 5434.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07672395900 |  | 500117601 |  | 6712208N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PALOMAR CENTRE | 3735 PALOMAR CENTRE DR STE 80 | 067 | LEX | 2022-09-15 | RSTRONG | SSUTHER | 2007-01-15 | 2020-12-31 | 2021-12-31 |  | RSTRONG | 2022-09-15 | 2022-09-13 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.1333 | 2 | 349.72 | 75.51 | 0 | 6.37 | 267.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19754568800 |  | 100297880 |  | 6716212H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MARYLAND | 546 MARYLAND AV | 067 | LEX | 2022-09-15 | U126602 | U125208 | 2019-10-28 | 2019-11-27 |  |  | DEREK PAYTON | 2022-09-15 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1403.95 | 0 | 0 | 0 | 1403.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883076900 |  | 100295210 |  | 6716212H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 4TH | 505 W 4TH ST | 067 | LEX | 2022-09-16 | U125208 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | RSTRONG | 2022-09-15 | 2022-09-07 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.4833 | 2 | 3918.94 | 299.36 | 168.44 | 25.24 | 3425.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916449000 |  | 100263466 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | WESTVIEW | 615 WESTVIEW DR | 019 | ASH | 2022-09-15 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1722.17 | 0 | 0 | 0 | 1722.17 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916449700 |  | 100263469 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | WESTVIEW | 625 WESTVIEW DR | 019 | ASH | 2022-09-15 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2029.84 | 0 | 0 | 0 | 2029.84 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916449900 |  | 100263470 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | WESTVIEW | 627 WESTVIEW DR | 019 | ASH | 2022-09-15 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3645.31 | 0 | 0 | 0 | 3645.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21940548600 |  | 100432955 |  | 6716204B |  |  |  | 566 | EX | ABANDON/CFCB/ BLDG GONE / CFCB | 2621P | REYNOLDS | 125 E REYNOLDS RD 115 | 067 | LEX | 2022-09-15 | RSTRONG | U125208 | 2021-09-17 | 2021-12-30 | 2021-12-31 |  | RSTRONG | 2022-09-15 | 2021-12-13 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.6667 | 4 | 572.11 | 180.43 | 0 | 123.84 | 267.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958628100 |  | 100331946 |  | 6720212M | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 109 N ASHLAND AV | 067 | LEX | 2022-09-15 | U126308 | U134723 | 2021-12-08 | 2022-12-30 |  |  | J ENSMINGER | 2022-09-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2439.04 | 0 | 0 | 0 | 2439.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959032500 |  | 100315208 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | CONN TER | 201 CONN TER | 067 | LEX | 2022-09-15 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-09-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2454.66 | 513.76 | 0 | 104.86 | 1836.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959033400 |  | 100315215 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | CONN TER | 227 CONN TER | 067 | LEX | 2022-09-15 | U461423 | U134723 | 2021-12-10 | 2022-12-30 |  |  | KKOUNS | 2022-09-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2521.89 | 478.57 | 0 | 450.85 | 1592.47 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959331900 |  | 500710174 |  | 6716212H |  |  |  | 566 | EX | ABANDON SL | 2600B | 4TH | 507 W 4TH ST | 067 | LEX | 2022-09-16 | U125208 | U131066 | 2021-12-13 | 2021-12-30 |  |  | RSTRONG | 2022-09-15 | 2022-09-02 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.15 | 4 | 684.63 | 144.36 | 262.28 | 10.15 | 267.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026181900 |  |  |  | 6712216L | 2288234 | U133035 |  | 909 | EX | LAB EQUIPMENT INSTALL | 2600E | MERCER | 2001 MERCER RD | 067 | LEX | 2023-04-26 | U123258 | U133035 | 2022-04-14 | 2022-04-13 | 2022-12-31 | 2022-09-15 | LLEDERER & CONTRACTOR | 2022-09-15 |  |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP1819 |  |  | 100 | 090932220261819 |  | 0 | 5312.84 | 0 | 0 | 0 | 5285.89 | 0 | 26.95 | 0
KY | KY - EAST | 2631 | 22026199900 |  |  |  | 7348264A | 2289341 | U122858 |  | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2621M | 3RD | 516 3RD ST RR | 089 | WOR | 2022-10-13 | U127644 | U136124 | 2022-06-07 | 2022-12-30 | 2022-12-31 | 2022-09-15 | SGIORDANO | 2022-09-15 | 2022-09-15 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP1999 |  |  | 100 | 090932220261999 | 6.3333 | 0 | 6476.38 | 405.11 | 0 | 339.32 | 5702.2 | 0 | 29.75 | 0
KY | KY - EAST | 2631 | 22026200200 |  |  |  | 7348264A | 2289341 | U122858 |  | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2621M | 3RD | 516 3RD AVE RR | 089 | WOR | 2022-10-13 | U127644 | U136124 | 2022-06-07 | 2022-12-30 | 2022-12-31 | 2022-09-15 | SGIORDANO | 2022-09-15 | 2022-09-15 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00910 | 3200910 |  |  | WP2002 |  |  | 100 | 091032220262002 | 9.2 | 0 | 1400.9 | 563.56 | 425.05 | 412.29 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127696800 |  | 100414488 |  | 6716204G |  |  |  | 565 | EX | REPLACE SERVICE LINE - D304118 | 2621P | LANCELOT | 444 LANCELOT LN | 067 | LEX | 2022-09-16 | U125208 | U125208 | 2022-08-30 | 2022-08-30 | 2022-09-17 |  | J.OCHOA | 2022-09-15 | 2022-09-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 30.9667 | 7 | 2336.86 | 1973.08 | 198.67 | 110.11 | 55 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129009400 |  | 500218522 |  | 7352260K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PRICE | 1309< PRICE ST | 019 | ASH | 2022-09-15 | U125566 | U130722 | 2022-09-05 | 2022-09-12 |  |  | DAVID SKAGGS | 2022-09-15 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 4436.46 | 0 | 0 | 0 | 4436.46 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129018100 |  | 500133659 |  | 6684220A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ANDERSON | 91 ANDERSON RD | 073 | FRA | 2022-09-20 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-15 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129018400 |  | 100280280 |  | 6688228J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DEWEY | 220 DEWEY CT | 073 | FRA | 2022-09-15 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-15 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129026900 |  | 100244397 |  | 7356256K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 39TH | 528 39TH ST | 019 | ASH | 2022-09-15 | U123965 | U130722 | 2022-09-05 | 2022-09-15 |  |  | MBLANKE | 2022-09-15 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.7667 | 1 | 4705.69 | 249.98 | 0 | 59.49 | 4396.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129048000 |  | 100338724 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAPLE | 707 MAPLE AV | 067 | LEX | 2022-09-16 | U125208 | U130722 | 2022-09-05 | 2022-09-15 |  |  | RSTRONG | 2022-09-15 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.1333 | 1 | 1675.72 | 141.68 | 244.49 | 11.93 | 1277.62 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129050700 |  | 100274525 |  | 6684228J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 4TH | 409 W 4TH ST | 073 | FRA | 2022-09-20 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-15 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129051100 |  | 500999216 |  | 6680224J | 0676074 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ARBOR VIEW | 112 ARBOR VIEW DR LT7 | 073 | FRA | 2022-09-20 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-15 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129051200 |  | 500550916 |  | 6692228O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | AUTUMNVIEW | 2107 AUTUMNVIEW DR | 073 | FRA | 2022-09-20 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-15 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 2013.73 | 0 | 0 | 0 | 2013.73 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129051800 |  | 500810272 |  | 6688228G | 0251936 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CORRAL | 1349 CORRAL WY | 073 | FRA | 2022-09-20 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-15 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1864.87 | 0 | 132.24 | 0 | 1732.63 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129051900 |  | 100281134 |  | 6688228K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | COUNTRY | 301 COUNTRY LN | 073 | FRA | 2022-09-20 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-15 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1868.17 | 0 | 0 | 0 | 1868.17 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129052200 |  | 500931207 |  | 6688228O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ENTRADA | 1000 ENTRADA | 073 | FRA | 2022-09-20 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-15 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 2315.92 | 0 | 0 | 0 | 2315.92 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129052400 |  | 100277024 |  | 6684228D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GRAND | 1107 GRAND AV | 073 | FRA | 2022-09-20 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-15 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 2380.94 | 0 | 0 | 0 | 2380.94 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129064800 |  | 100255939 |  | 7356256F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ASHLAND | 1924 ASHLAND AV | 019 | ASH | 2022-09-15 | U123965 | U130722 | 2022-09-05 | 2022-09-12 |  |  | MBLANKE | 2022-09-15 | 2022-09-13 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 25.2333 | 3 | 4263.39 | 1318.87 | 0 | 313.83 | 2630.69 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129083300 |  | 100338460 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 7TH | 137 E 7TH ST | 067 | LEX | 2022-09-15 | U127206 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-15 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 2855.38 | 602.79 | 0 | 33.63 | 2218.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129083400 |  | 100298298 |  | 6716212H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BALLARD | 620 BALLARD ST | 067 | LEX | 2022-09-19 | U126602 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DEREK PAYTON | 2022-09-15 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 2874.68 | 592.94 | 0 | 33.08 | 2248.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129083500 |  | 100298322 |  | 6716212H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BALLARD | 636 BALLARD ST | 067 | LEX | 2022-09-19 | U126602 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DEREK PAYTON | 2022-09-15 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2254.6 | 0 | 0 | 0 | 2254.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129083600 |  | 100338233 |  | 6720212J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BRECKENRIDGE | 530 BRECKENRIDGE ST | 067 | LEX | 2022-09-19 | U127206 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-15 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1878.7 | 0 | 0 | 0 | 1878.7 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129088200 |  | 500500074 |  | 6692228N | 9612530 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FARMBROOK | 213 FARMBROOK CR | 073 | FRA | 2022-09-15 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-15 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129088500 |  | 100277110 |  | 6684228D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GRANT | 903 GRANT ST | 073 | FRA | 2022-09-15 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-15 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 2400.84 | 0 | 0 | 0 | 2400.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129088600 |  | 100273603 |  | 6680224C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HAWKEEGAN | 112 HAWKEEGAN DR | 073 | FRA | 2022-09-15 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-15 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129120700 |  | 100338524 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | EDDIE | 141 EDDIE ST | 067 | LEX | 2022-09-15 | U127206 | U125208 | 2022-09-06 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-15 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1708.57 | 0 | 0 | 0 | 1708.57 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22130527800 |  | 100350556 |  | 6744204C |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | WESTERN | 14 WESTERN AV | 049 | WIN | 2022-09-15 | NRICHIE | U132002 | 2022-09-09 | 2022-09-23 | 2022-10-09 |  | NRICHIE | 2022-09-15 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 6.5 | 2 | 744.12 | 406.78 | 159.27 | 178.07 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22131421800 |  | 100346973 |  | 6696212K |  |  |  | 565 | EX | SERVICE LINE REPLACE | 2621P | HIGH | 120 HIGH ST | 239 | VER | 2022-09-16 | U125208 | U136526 | 2022-09-15 | 2022-09-15 |  |  | DCOLLIN | 2022-09-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5 | 1 | 3984.12 | 336.57 | 268.93 | 37.68 | 3340.94 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22131460400 |  | 500999217 |  | 6680224J |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | ARBOR VIEW | 116 ARBOR VIEW DR LT8 | 073 | FRA | 2022-09-20 | U125881 | U125763 | 2022-09-15 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-15 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 239.61 | 0 | 0 | 0 | 239.61 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983421800 |  | 100324763 |  | 6720204B | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 1119 GREENTREE CT | 067 | LEX | 2022-09-15 | U461309 | U134723 | 2022-03-03 | 2022-12-30 |  |  | R.HUMPHREYS | 2022-09-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20 | 2 | 3458.88 | 1188.52 | 347.84 | 161.56 | 1760.96 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22994324600 |  | 100353545 |  | 7256280K | 2180424 |  |  | 565 | EX | REPLACE SL W/21-0261272-00 | 2600B | 3RD | 320 W 3RD ST | 161 | MAY | 2022-09-15 | U126286 | U134723 | 2022-04-19 | 2022-12-30 |  |  | TYLER ALLISON | 2022-09-15 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 | 8 | 1 | 5295.2 | 488.47 | 0 | 27.25 | 4779.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 03528318200 |  | 100326245 |  | 6708212M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | R2 VERSAILLES | R2 VERSAILLES RD | 067 | LEX | 2022-09-16 | WISHII | DMCCULL | 2003-01-20 | 2022-09-16 | 2022-12-31 |  | WISHII | 2022-09-16 | 2022-09-16 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.1 | 3 | 157.78 | 149.44 | 0 | 8.34 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11919119000 |  | 500350047 |  | 7240204J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEVEE | 1140 LEVEE RD D | 173 | MT | 2022-09-16 | U930915 | U907469 | 2011-08-05 | 2022-07-01 | 2022-12-31 |  | DENNING | 2022-09-16 | 2022-09-06 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9 | 4 | 658.61 | 623.81 | 0 | 34.8 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883321400 |  | 500567123 |  | 7240212F | 9722951 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEVEE | 1140 LEVEE RD E | 173 | MT | 2022-09-16 | DENNING | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DENNING | 2022-09-16 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.26667 | 2 | 26.12 | 18.19 | 0 | 7.93 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959033100 |  | 100315213 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | CONN TER | 221 CONN TER | 067 | LEX | 2022-09-16 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-09-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16 | 3 | 3615.55 | 992.33 | 0 | 479.52 | 2143.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22127013800 |  | 100260403 |  | 7352256H |  |  |  | 566 | EX | ABANDON SL- DEMO/CUST REQ 8-31 | 2621P | VIRGINIA | 2609 VIRGINIA AV | 019 | ASH | 2022-09-19 | U125208 | KWELLS | 2022-08-26 | 2022-09-01 | 2022-09-23 |  | RECUMP | 2022-09-16 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 20.0667 | 3 | 1218.71 | 1139.9 | 0 | 78.81 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129018600 |  | 100444347 |  | 6692228A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GEORGETOWN | 3600 GEORGETOWN RD | 073 | FRA | 2022-09-16 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-16 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129052100 |  | 100279178 |  | 6688228F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ELKHORN | 136 ELKHORN DR | 073 | FRA | 2022-09-20 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-16 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1402.64 | 0 | 0 | 0 | 1402.64 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129087900 |  | 100273845 |  | 6680228K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DEVILS HOLLOW | 983 DEVILS HOLLOW RD | 073 | FRA | 2022-09-20 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-16 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1176.73 | 0 | 0 | 0 | 1176.73 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129088300 |  | 500818131 |  | 6692228A | 0253076 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GEORGETOWN | 3732 GEORGETOWN RD | 073 | FRA | 2022-09-16 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-16 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129088400 |  | 100275310 |  | 6684228F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GLASS | 204 GLASS AV | 073 | FRA | 2022-09-16 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-16 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129088700 |  | 100276713 |  | 6684228H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HILLCREST | 720 HILLCREST AV | 073 | FRA | 2022-09-16 | U135195 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-16 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129138200 |  | 100360967 |  | 6740216E |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | AUSTERLITZ | 174 AUSTERLITZ RD | 017 | PAR | 2022-09-19 | U930915 | U132002 | 2022-09-06 | 2022-09-16 | 2022-10-02 |  | NRICHIE | 2022-09-16 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 6.9167 | 3 | 794.05 | 474.03 | 1.63 | 26.47 | 291.92 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129973900 |  | 100269748 |  | 6732252P |  |  |  | 565 | EX | GRADE 1 REPLACE SERVICE LINE | 2621P | PLEASANT | 442 W PLEASANT ST | 097 | CYN | 2022-09-19 | U930915 | U136526 | 2022-09-08 | 2022-09-08 | 2022-09-08 |  | NRICHIE | 2022-09-16 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 16.9333 | 3 | 1790.79 | 1164.43 | 201.3 | 64.94 | 360.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22131494200 |  | 100289629 |  | 6720216P |  |  |  | 565 | EX | SERVICE LINE REPLACE D311339 | 2621P | SPRING STATION | 2053 SPRING STATION DR | 067 | LEX | 2022-09-19 | U125208 | U136526 | 2022-09-15 | 2022-09-15 | 2022-09-15 |  | LSTANFI | 2022-09-16 | 2022-09-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.45 | 5 | 1389.36 | 620.41 | 701.7 | 35.35 | 31.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22131748600 |  | 100356450 |  | 7256280K |  |  |  | 565 | EX | RPLC SVC W/21-0261274-00 | 2600B | WADSWORTH | 278 WADSWORTH PT | 161 | MAY | 2022-09-16 | U126286 | U461478 | 2022-09-16 | 2022-09-16 |  |  | TYLER ALLISON | 2022-09-16 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2778.06 | 0 | 0 | 0 | 2778.06 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22131796300 |  | 100254344 |  | 7348264O | 1313372 |  |  | 565 | EX | REPLACE SL | 2621P | HAMER | 1303 HAMER ST | 089 | FLA | 2022-09-16 | MCOLLET | U132823 | 2022-09-16 | 2022-09-16 | 2022-09-16 |  | MCOLLET | 2022-09-16 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 15.8333 | 3 | 1591.14 | 1010.55 | 147.73 | 377.86 | 55 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22138323700 |  | 500160360 |  | 6684228I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DEVILS HOLLOW | 209< DEVILS HOLLOW RD | 073 | FRA | 2022-10-20 | U125881 | U123981 | 2022-10-11 | 2023-06-16 | 2023-06-18 |  | HERBERT HAYDEN | 2022-09-16 |  |  | D | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 2018.78 | 0 | 0 | 0 | 2018.78 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22994321000 |  | 100356449 |  | 7256280K | 2180424 |  |  | 565 | EX | REPLACE SL W/21-0261274-00 | 2600B | WADSWORTH | 268 WADSWORTH PT | 161 | MAY | 2022-09-16 | U126286 | U134723 | 2022-04-19 | 2022-12-30 |  |  | TYLER ALLISON | 2022-09-16 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 | 8 | 1 | 2842.99 | 488.47 | 0 | 27.25 | 2327.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 01479328000 |  | 100297653 |  | 6716212H |  |  |  | 566 | EX | ABANDON SL - SOII/INSIDE | 2621P | LIMESTONE | 253 N LIMESTONE ST | 067 | LEX | 2022-09-19 | RSTRONG | JTOY | 2001-08-14 | 2021-12-30 | 2021-12-31 |  | RSTRONG | 2022-09-19 | 2022-09-02 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.7667 | 4 | 537.51 | 250.54 | 0 | 19.13 | 267.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11882424200 |  | 100295348 |  | 6716212D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NEWTOWN | 533 NEWTOWN PK | 067 | LEX | 2022-09-19 | HMCKUNE | U906307 | 2011-01-31 | 2022-07-01 | 2022-12-31 |  | HMCKUNE | 2022-09-19 | 2022-09-07 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 17.05 | 6 | 3095.26 | 1029.28 | 13.59 | 57.46 | 1994.93 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12968001700 |  | 100297499 |  | 16716212H |  |  |  | 566 | EX | SOII - METER ABANDON ONLY | 2621P | 3RD | 515 W 3RD ST 2F | 067 | LEX | 2022-09-19 | U126602 | U124967 | 2012-05-02 | 2014-12-23 |  |  | DEREK PAYTON | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 14211144400 |  | 100338496 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | EDDIE | 176 EDDIE ST | 067 | LEX | 2022-09-19 | U127206 | U125208 | 2014-04-07 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 2515.12 | 602.79 | 0 | 33.63 | 1878.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 20026930900 |  |  |  | 7356256B | 2177548 | U131983 |  | 587 | EX | UPGRADE ELECTRONICS | 2631M | MONTGOMERY | 2236 MONTGOMERY AV | 019 | ASH | 2022-10-05 | U460266 | U131983 | 2020-02-25 | 2022-12-29 | 2022-12-31 | 2022-09-19 | DASH | 2022-09-19 |  |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00587 | 3200587 |  |  | WP9309 |  |  | 100 | 058732200269309 | 1.2 | 0 | 3329.3 | 125.69 | 2704.09 | 70.65 | 0 | 0 | 63.15 | 365.72
KY | KY - WEST | 2621 | 21883118700 |  | 100462271 |  | 6716212P | 2176779 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | MAXWELL | 325 E MAXWELL ST 5 | 067 | LEX | 2022-10-12 | U461375 | U120245 | 2021-01-30 | 2022-12-30 |  |  | LARRY BROWN | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1 | 1368.31 | 0 | 0 | 0 | 1368.31 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883127100 |  | 500506024 |  | 7348260H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SUNSET | 408 SUNSET DR | 089 | ASH | 2022-09-19 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883163400 |  | 100408538 |  | 7320280B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | FIREBRICK INDI | 708< FIREBRICK INDI RD | 135 | FIR | 2022-09-20 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 2500 | 0 | 0 | 0 | 2500 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883189500 |  | 100408532 |  | 7320284-N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | INDIAN RUN | 15 INDIAN RUN RD | 135 | FIR | 2022-09-19 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883203200 |  | 100255683 |  | 7348264G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 4TH | 536 N 4TH ST | 089 | FLA | 2022-09-19 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883224800 |  | 100439681 |  | 7320284N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | KY 8 | 19031 E KY 8 | 135 | FIR | 2022-09-19 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21884270500 |  | 500046834 |  | 7320280B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | FIREBRICK INDI | 374 FIREBRICK INDI RD | 135 | FIR | 2022-09-19 | U135195 | U128293 | 2021-02-04 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916449100 |  | 100263475 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | WESTVIEW | 618 WESTVIEW DR | 019 | ASH | 2022-09-19 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1829.85 | 103.16 | 0 | 84.3 | 1642.39 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916449600 |  | 100263474 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | WESTVIEW | 624 WESTVIEW DR | 019 | ASH | 2022-09-19 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1931.64 | 0 | 0 | 0 | 1931.64 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916450100 |  | 100263473 |  | 7341145B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | WESTVIEW | 637 WESTVIEW DR | 019 | ASH | 2022-09-19 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1839.08 | 0 | 0 | 0 | 1839.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959037200 |  | 100315158 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | TRANSCRIPT | 204 TRANSCRIPT AV | 067 | LEX | 2022-09-19 | U461423 | U134723 | 2021-12-10 | 2022-12-30 |  |  | KKOUNS | 2022-09-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.75 | 1 | 3542.82 | 523.44 | 0 | 493.12 | 2526.26 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959037300 |  | 100315157 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | TRANSCRIPT | 208 TRANSCRIPT AV | 067 | LEX | 2022-09-20 | U461423 | U134723 | 2021-12-10 | 2022-12-30 |  |  | KKOUNS | 2022-09-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2373.25 | 10.67 | 0 | 0.6 | 2361.98 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959046800 |  | 100315216 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | CONN TER | 233 CONN TER 1 | 067 | LEX | 2022-09-19 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-09-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.5 | 1 | 4759.74 | 610.11 | 0 | 111.2 | 4038.43 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959048000 |  | 100451576 |  | 6716212O | 2176780 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | CONN TER | 233 CONN TER WH | 067 | LEX | 2022-09-19 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 21960237200 |  | 100321005 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | MAXWELL | 323 E MAXWELL ST 1F | 067 | LEX | 2022-10-12 | U461375 | U134723 | 2021-12-17 | 2022-12-30 |  |  | LARRY BROWN | 2022-09-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2794.15 | 0 | 0 | 0 | 2794.15 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22026206400 |  |  |  | 7356256B | 2177548 | U461383 |  | 588 | EX | RETIRE ELECTRONIC | 2631M | MONTGOMERY | 2236 MONTGOMERY AV | 019 | ASH | 2022-10-05 | U460266 | U461383 | 2022-06-20 | 2023-09-01 | 2023-09-01 | 2022-09-19 | DASH | 2022-09-19 | 2022-09-19 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00588 | 3200588 |  |  | WP2064 |  |  | 100 | 058832220262064 | 19.9 | 0 | 2331.95 | 1320.5 | 0 | 137.34 | 874.11 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22113306600 |  | 100331221 |  | 6720212N | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER | 2621D | LINCOLN | 341 LINCOLN AV | 067 | LEX | 2022-09-19 | U930915 | AOC SYST | 2022-06-30 | 2022-07-28 | 2022-08-27 |  | LSTANFI | 2022-09-19 | 2022-08-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 29.5667 | 12 | 2428.79 | 1893 | 267.07 | 201.62 | 67.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129017000 |  | 501246681 |  | 6716212H | 1743881 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HAMPTON | 308 HAMPTON CT GAS LIT | 067 | LEX | 2022-09-19 | U126602 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DEREK PAYTON | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2843.49 | 0 | 0 | 0 | 2843.49 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129018900 |  | 500826312 |  | 6688228F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | IVY | 851 IVY AV | 073 | FRA | 2022-09-20 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 9 | 1 | 2581.63 | 549.53 | 0 | 30.66 | 2001.44 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129019000 |  | 100280840 |  | 6688228I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LANGFORD | 249 LANGFORD AV | 073 | FRA | 2022-09-20 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1732.63 | 0 | 0 | 0 | 1732.63 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129028600 |  | 100244314 |  | 7356256P | 1960437 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GARTRELL | 505 GARTRELL ST | 019 | ASH | 2022-09-19 | U123965 | U130722 | 2022-09-05 | 2022-09-19 |  |  | MBLANKE | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.6833 | 1 | 2101.94 | 194.55 | 0 | 46.29 | 1861.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129031000 |  | 100263430 |  | 7352256B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | COMMANCHE | 920 COMMANCHE DR | 019 | ASH | 2022-09-19 | U125566 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DAVID SKAGGS | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1458.7 | 0 | 0 | 0 | 1458.7 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129053000 |  | 100278382 |  | 6688232N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HOPI | 559 HOPI TL | 073 | FRA | 2022-09-21 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129053200 |  | 100279124 |  | 6688228F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LAFFOON | 227 LAFFOON DR | 073 | FRA | 2022-09-21 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129053300 |  | 100279133 |  | 6688228F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LAFFOON | 205 LAFFOON DR | 073 | FRA | 2022-09-20 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 4478.27 | 0 | 3452.15 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129069400 |  | 100263517 |  | 7352256B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LEE | 332 LEE ST | 019 | ASH | 2022-09-19 | U125566 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DAVID SKAGGS | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1458.7 | 0 | 0 | 0 | 1458.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129069900 |  | 100263369 |  | 7352256B |  |  |  | 566 | EX | ABANDON SL - PEND OS 09/30/22 | 2621P | OHIO | 2931 OHIO ST | 019 | ASH | 2022-09-19 | U125566 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DAVID SKAGGS | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1257.5 | 0 | 0 | 0 | 1257.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129082600 |  | 100287831 |  | 6720212G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SHAWNEE | 437 SHAWNEE AV | 067 | LEX | 2022-09-20 | U930915 | U130722 | 2022-09-05 | 2022-09-19 |  |  | RSTRONG | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.68333 | 1 | 904.37 | 45.44 | 0 | 3.83 | 855.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129082700 |  | 100287857 |  | 6720212G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SHAWNEE | 436 SHAWNEE AV | 067 | LEX | 2022-09-20 | U125208 | U130722 | 2022-09-05 | 2022-09-19 |  |  | RSTRONG | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.1 | 1 | 1240.98 | 342.1 | 14.96 | 28.82 | 855.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129088800 |  | 100280452 |  | 6688228F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | IVY | 854 IVY AV | 073 | FRA | 2022-09-19 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129088900 |  | 100280832 |  | 6688228E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LANGFORD | 117< LANGFORD AV | 073 | FRA | 2022-09-20 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129089400 |  | 500453722 |  | 6680228K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MILLIE | 600 MILLIE DR | 073 | FRA | 2022-09-20 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129121900 |  | 100294689 |  | 6716212D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | JEFFERSON | 526 JEFFERSON ST | 067 | LEX | 2022-09-28 | U126602 | U125208 | 2022-09-06 | 2022-12-30 |  |  | DEREK PAYTON | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 3215.51 | 592.94 | 0 | 33.08 | 2589.49 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129124100 |  | 100338528 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | EDDIE | 133 EDDIE ST | 067 | LEX | 2022-09-19 | U127206 | U125208 | 2022-09-06 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2218.96 | 0 | 0 | 0 | 2218.96 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22130953900 |  | 100412719 |  | 6748208M |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333629 | 2621P | JACKSON | 18 JACKSON ST | 049 | WIN | 2022-09-20 | UIPBOT10 | U125208 | 2022-09-13 | 2022-09-15 | 2022-10-03 |  | NRICHIE | 2022-09-19 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 11.8667 | 2 | 1458.76 | 826.1 | 196.31 | 361.55 | 74.8 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22132024900 |  | 100254496 |  | 7348264K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D259779 | 2621P | ARGILLITE | 1813 ARGILLITE RD | 089 | FLA | 2022-09-20 | U125208 | U129939 | 2022-09-19 | 2022-09-16 | 2022-09-16 |  | MCOLLET | 2022-09-19 | 2022-09-19 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 18.45 | 2 | 4063.53 | 1511.64 | 200.92 | 701.13 | 1649.84 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979017900 |  | 100245477 |  | 7360248A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 3513 MAIN ST | 019 | CAT | 2022-09-19 | U123965 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | MBLANKE | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.9167 | 1 | 2448.65 | 255.21 | 0 | 60.72 | 2132.72 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979020500 |  | 100252493 |  | 7348264P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CALLIHAN | 1611 CALLIHAN ST | 089 | FLA | 2022-09-19 | U938684 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | CHARLES COMBS | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22979029400 |  | 100277133 |  | 6684228D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HOLMES | 757 HOLMES ST | 073 | FRA | 2022-09-20 | U125881 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | HERBERT HAYDEN | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22979052300 |  | 500346059 |  | 6680228K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MILLIE | 611 MILLIE DR | 073 | FRA | 2022-09-20 | U125881 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | HERBERT HAYDEN | 2022-09-19 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1431.41 | 0 | 0 | 0 | 1431.41 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983425400 |  | 100404847 |  | 6720204A | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 1113 GREENTREE CT | 067 | LEX | 2022-09-19 | U461309 | U134723 | 2022-03-03 | 2022-12-30 |  |  | R.HUMPHREYS | 2022-09-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10 | 1 | 3231.87 | 594.26 | 347.84 | 128.4 | 2161.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983426200 |  | 100324759 |  | 6720204B | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 3383 GREENTREE RD | 067 | LEX | 2022-09-19 | U126530 | U134723 | 2022-03-03 | 2022-12-30 |  |  | JDUNN | 2022-09-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 34171.65 | 0 | 0 | 0 | 34171.65 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22994323500 |  | 100353516 |  | 7256280K | 2180424 |  |  | 565 | EX | REPLACE SL W/21-0261272-00 | 2600B | 3RD | 235 W 3RD ST | 161 | MAY | 2022-10-13 | U461478 | U134723 | 2022-04-19 | 2022-12-30 |  |  | DAVID STAGGS | 2022-09-19 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 3083.12 | 0 | 0 | 0 | 3083.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 03533975300 |  | 100295343 |  | 6716212D | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NEWTOWN | 543 NEWTOWN PK | 067 | LEX | 2022-09-20 | HMCKUNE | DMCCULL | 2003-03-18 | 2022-07-01 | 2022-12-31 |  | HMCKUNE | 2022-09-20 | 2022-09-07 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 21.15 | 12 | 1145.31 | 1084.73 | 0 | 60.58 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 13161971000 |  | 100313348 |  | 16716212N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | HARRODSBURG | 1618 HARRODSBURG RD | 067 | LEX | 2022-09-20 | U127206 | U126921 | 2013-09-17 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-09-20 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1368.31 | 0 | 0 | 0 | 1368.31 | 0 | 0 | 0
KY | KY - WEST | 2623 | 14234609000 |  | 500113412 |  | 6684224M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | US 127 | 2589 US 127 SO | 073 | FRA | 2022-09-20 | DCOLLIN | U125208 | 2014-07-15 | 2022-07-01 | 2022-12-31 |  | DCOLLIN | 2022-09-20 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 2.85 | 1 | 1821.67 | 193.01 | 0 | 21.62 | 1607.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 17522366300 |  | 100321823 |  | 6716208D | 1635077 |  |  | 565 | EX | AOC REPLACE - ENCROACHMENT | 2621P | COLUMBIA | 608 COLUMBIA AV | 067 | LEX | 2022-09-20 | LSTANFI | U125208 | 2017-07-07 | 2022-09-12 | 2022-10-24 |  | LSTANFI | 2022-09-20 | 2022-08-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 47.95 | 12 | 3754.87 | 3165.27 | 281.84 | 307.76 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21026998900 |  | 500296569 |  | 6720212I | 2289018 | U461383 |  | 566 | EX | RETIRE 3"PLP SERVICE LINE | 2600B | RACE | 437 RACE ST | 067 | LEX | 2022-11-01 | U123258 | U120245 | 2021-01-30 | 2022-10-31 | 2022-11-01 | 2022-09-07 | DEREK PAYTON | 2022-09-20 | 2022-09-06 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP9989 |  |  | 100 | 056632210269989 | 16.6667 | 3 | 9085.7 | 990.66 | 163.28 | 55.4 | 7876.36 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883197300 |  | 100255335 |  | 7348264K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | ARGILLITE | 1603 ARGILLITE RD | 089 | FLA | 2022-09-20 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-09-20 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 10406.16 | 0 | 0 | 0 | 10406.16 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883288200 |  | 100408060 |  | 7348260B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LUCI MAE | 1602 LUCI MAE DR | 089 | FLA | 2022-09-20 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-20 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 3108.63 | 0 | 0 | 0 | 3108.63 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883290700 |  | 500144943 |  | 7340268I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | STATE RT 1 | 101 STATE RT 1 | 089 | GRE | 2022-09-20 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-20 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916441500 |  | 100263494 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2633 MAIN ST W | 019 | ASH | 2022-09-20 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-20 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1748.87 | 0 | 0 | 0 | 1748.87 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916441600 |  | 100263461 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2635 MAIN ST W | 019 | ASH | 2022-09-20 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-20 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1985.43 | 0 | 0 | 0 | 1985.43 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916448200 |  | 100263463 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | WESTVIEW | 501 WESTVIEW DR | 019 | ASH | 2022-09-20 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-20 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1958.45 | 0 | 0 | 0 | 1958.45 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959037100 |  | 100440883 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | TRANSCRIPT | 135 TRANSCRIPT AV | 067 | LEX | 2022-09-20 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-09-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2567.61 | 513.76 | 0 | 62.01 | 1991.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959037400 |  | 100315155 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | TRANSCRIPT | 212 TRANSCRIPT AV | 067 | LEX | 2022-09-20 | U461423 | U134723 | 2021-12-10 | 2022-12-30 |  |  | KKOUNS | 2022-09-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 3488.84 | 478.57 | 0 | 450.85 | 2559.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959039000 |  | 100315343 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | UNIVERSITY | 209 UNIVERSITY AV | 067 | LEX | 2022-09-20 | U461423 | U134723 | 2021-12-10 | 2022-12-30 |  |  | KKOUNS | 2022-09-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1441.55 | 0 | 0 | 0 | 1441.55 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026199700 |  |  |  | 6736248A | 2289340 | U122858 |  | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2621M | COUNTY | COUNTY LN | 097 | CYN | 2022-09-29 | U460266 | U136124 | 2022-06-07 | 2022-12-30 | 2022-12-31 | 2022-09-20 | EBLANTON | 2022-09-20 | 2022-09-20 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00909 | 3200909 |  |  | WP1997 |  |  | 100 | 090932220261997 | 5.2 | 0 | 5650.33 | 366.02 | 0 | 84.06 | 5174.3 | 0 | 25.95 | 0
KY | KY - CENTRAL | 2629 | 22026199800 |  |  |  | 6736248A | 2289340 | U122858 |  | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2621M | COUNTY | COUNTY LN | 097 | CYN | 2022-09-29 | U460266 | U136124 | 2022-06-07 | 2022-12-30 | 2022-12-31 | 2022-09-20 | EBLANTON | 2022-09-20 | 2022-09-20 |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00910 | 3200910 |  |  | WP1998 |  |  | 100 | 091032220261998 | 7.2 | 0 | 592.76 | 501.17 | 0 | 91.59 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22128392300 |  | 100353270 |  | 7256280G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 2ND | 556 W 2ND ST | 161 | MAY | 2022-09-20 | SDADAMS | U125208 | 2022-09-01 | 2022-09-01 |  |  | SDADAMS | 2022-09-20 | 2022-09-20 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 14.9 | 2 | 4874.59 | 970.84 | 0 | 478.32 | 3425.43 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129016700 |  | 100338325 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAGOFFIN | 716 MAGOFFIN ST | 067 | LEX | 2022-09-20 | WISHII | U130722 | 2022-09-05 | 2022-12-30 |  |  | WISHII | 2022-09-20 | 2022-09-19 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.5667 | 4 | 715.99 | 645.52 | 14.96 | 55.51 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129017100 |  | 100338583 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LANCASTER | 737 LANCASTER AV | 067 | LEX | 2022-09-20 | U127206 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-20 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1368.31 | 0 | 0 | 0 | 1368.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129017200 |  | 100338595 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LANCASTER | 711 LANCASTER AV | 067 | LEX | 2022-09-20 | U127206 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-20 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1538.44 | 0 | 0 | 0 | 1538.44 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129018800 |  | 100420622 |  | 6684228D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HOLMES | 1110 HOLMES ST | 073 | FRA | 2022-09-21 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-09-20 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129019100 |  | 100279946 |  | 6688228J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LYONS | 215 LYONS DR | 073 | FRA | 2022-09-21 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-20 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1686.09 | 0 | 0 | 0 | 1686.09 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129019300 |  | 100276965 |  | 684228D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NOEL | 217 NOEL AV | 073 | FRA | 2022-09-20 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-09-20 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129032000 |  | 100265215 |  | 7352256C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PRICHARD | 108 PRICHARD ST | 019 | ASH | 2022-09-20 | U125566 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DAVID SKAGGS | 2022-09-20 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1861.1 | 0 | 0 | 0 | 1861.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129046200 |  | 100337177 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 6TH | 158 E 6TH ST | 067 | LEX | 2022-09-20 | U127206 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-20 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 2685.25 | 602.79 | 0 | 33.63 | 2048.83 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129051400 |  | 100275617 |  | 6684228F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BRAWNER | 820 BRAWNER ST | 073 | FRA | 2022-09-28 | U125559 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHRIS HUNGATE | 2022-09-20 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129052900 |  | 100459833 |  | 6684228G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HOLMES | 217 HOLMES ST 2F | 073 | FRA | 2022-09-20 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-09-20 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129053400 |  | 100276850 |  | 6684228D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LETCHER | 940 LETCHER AV | 073 | FRA | 2022-09-28 | U125559 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHRIS HUNGATE | 2022-09-20 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129054000 |  | 100276998 |  | 6684228D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NOEL | 105 NOEL AV | 073 | FRA | 2022-09-20 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-09-20 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 10 | 1 | 1670.77 | 610.59 | 0 | 34.06 | 1026.12 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129064200 |  | 100264364 |  | 7356260M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 10TH | 616 10TH ST | 019 | ASH | 2022-09-20 | U125566 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DAVID SKAGGS | 2022-09-20 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1861.1 | 0 | 0 | 0 | 1861.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129065900 |  | 100242607 |  | 7356256O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GALLAHER | 1226 GALLAHER DR | 019 | ASH | 2022-09-20 | U123965 | U130722 | 2022-09-05 | 2022-09-19 |  |  | MBLANKE | 2022-09-20 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.4667 | 1 | 2229.69 | 232.73 | 0 | 55.38 | 1941.58 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129067400 |  | 100243891 |  | 7356256J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RAY | 1908 RAY ST | 019 | ASH | 2022-09-20 | U123965 | U130722 | 2022-09-05 | 2022-09-09 |  |  | MBLANKE | 2022-09-20 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.5333 | 1 | 3024.84 | 290.26 | 0 | 69.06 | 2665.52 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129089100 |  | 100279390 |  | 6688228P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LOCUST | 160 LOCUST DR | 073 | FRA | 2022-09-21 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-20 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1431.41 | 0 | 0 | 0 | 1431.41 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129089500 |  | 500285666 |  | 6688232N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NORTHWOOD | 121 NORTHWOOD RD | 073 | FRA | 2022-09-21 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-09-20 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129090000 |  | 100272884 |  | 6684224A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | REED | 730 REED DR | 073 | FRA | 2022-09-21 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-09-20 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1535.48 | 0 | 0 | 0 | 1535.48 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22131005400 |  | 100451662 |  | 6756176J |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTREQD | 2621P | WINSTON | 1550 WINSTON RD | 065 | IRV | 2022-09-20 | DENNING | U125208 | 2022-09-13 | 2022-09-16 | 2022-10-23 |  | DENNING | 2022-09-20 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.3 | 2 | 330.63 | 230.29 | 0 | 100.34 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22131440500 |  | 100297023 |  | 6716212C |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | CHARLES | 908 CHARLES AV | 067 | LEX | 2022-09-20 | WISHII | U132002 | 2022-09-15 | 2022-09-28 | 2022-10-14 |  | WISHII | 2022-09-20 | 2022-09-19 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.9833 | 4 | 607.28 | 539.42 | 15.22 | 52.64 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22132015000 |  | 100316575 |  | 6716208F |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | PENMOKEN | 156 PENMOKEN PA | 067 | LEX | 2022-09-22 | U125208 | U125208 | 2022-09-19 | 2022-09-22 |  |  | RSTRONG | 2022-09-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 5.5833 | 1 | 1990.41 | 372.19 | 138.23 | 31.35 | 1448.64 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22132060300 |  | 100346979 |  | 6696212K |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HIGH | 156 HIGH ST | 239 | VER | 2022-09-20 | DCOLLIN | U129939 | 2022-09-19 | 2022-09-19 |  |  | DCOLLIN | 2022-09-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.85 | 1 | 2866.47 | 57.57 | 260.81 | 6.47 | 2541.62 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22132376300 |  | 100452518 |  | 6688228G |  |  |  | 566 | EX | ABANDON SL | 2600B | LOCUST | 138 LOCUST AV | 073 | FRA | 2022-09-21 | U125881 | U125201 | 2022-09-20 | 2022-12-01 | 2022-12-01 |  | HERBERT HAYDEN | 2022-09-20 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2623 | 22132455700 |  | 100276596 |  | 6684228H |  |  |  | 566 | EX | ABANDON SL | 2600B | LIME | 608 S LIME ST | 073 | FRA | 2022-09-21 | U125881 | U125201 | 2022-09-20 | 2022-12-01 | 2022-12-01 |  | HERBERT HAYDEN | 2022-09-20 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22134530000 |  | 100408537 |  | 7320280B |  |  |  | 566 | EX | ABANDN SL/LGCY | 2621P | FIREBRICK INDI | 708 FIREBRICK INDI RD | 135 | FIR | 2023-03-08 | U125559 | U125763 | 2022-09-26 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-20 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1
KY | KY - WEST | 2623 | 22138315900 |  | 100445435 |  | 6684228K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 100 W MAIN ST | 073 | FRA | 2022-10-20 | U125881 | U123981 | 2022-10-11 | 2023-11-27 | 2023-11-27 |  | HERBERT HAYDEN | 2022-09-20 |  |  | D | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 2258.39 | 0 | 0 | 0 | 2258.39 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22140179700 |  | 100450470 |  | 6684228K |  |  |  | 566 | EX | ABANDON SL/LGCY | 2600B | MAIN | 100 W MAIN ST 2F | 073 | FRA | 2022-10-20 | U125881 | U125763 | 2022-10-20 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-20 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - EAST | 2631 | 22979020600 |  | 100252515 |  | 7348264P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MARY ELLEN | 1709 MARY ELLEN DR | 089 | FLA | 2022-09-20 | U135195 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | KEITH HEDGES | 2022-09-20 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22979030500 |  | 100279254 |  | 6688228G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LOCUST | 136 LOCUST AV | 073 | FRA | 2022-09-21 | U125881 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | HERBERT HAYDEN | 2022-09-20 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983421300 |  | 100324767 |  | 6720204A | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 1108 GREENTREE CT | 067 | LEX | 2022-09-21 | U461309 | U134723 | 2022-03-03 | 2022-12-30 |  |  | R.HUMPHREYS | 2022-09-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2318.65 | 0 | 347.84 | 0 | 1970.81 | 0 | 0 | 0
KY | KY - WEST | 2623 | 05613309500 |  | 100279230 |  | 600000000 | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | VERSAILLES | 260 VERSAILLES RD 107 | 073 | FRA | 2022-09-22 | U930915 | RPOLLY | 2005-06-07 | 2022-07-01 | 2022-12-31 |  | DCOLLIN | 2022-09-21 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 1.5 | 1 | 970.34 | 103.64 | 0 | 11.6 | 855.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883057500 |  | 100279228 |  | 6688228F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | VERSAILLES | 260 VERSAILLES RD 109 | 073 | FRA | 2022-09-22 | U930915 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DCOLLIN | 2022-09-21 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.58333 | 1 | 1024.31 | 39.96 | 124.79 | 4.46 | 855.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883071000 |  | 100251526 |  | 7336276N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | RUPPS | 153 RUPPS WY | 089 | GRE | 2022-09-21 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-21 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1576.36 | 0 | 0 | 0 | 1576.36 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883114100 |  | 100277655 |  | 6688228E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAIN | 682 E MAIN ST | 073 | FRA | 2022-10-20 | U125881 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-09-21 | 2022-09-26 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 2.55 | 1 | 1820.61 | 172.7 | 0 | 19.35 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883131700 |  | 100425441 |  | 6728212O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WINCHESTER | 3913 WINCHESTER RD | 067 | LEX | 2022-09-22 | U123111 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | LYN STAFFORD | 2022-09-21 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.45 | 2 | 2297.9 | 265.83 | 0 | 252.9 | 1779.17 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883295300 |  | 500067514 |  | 6684228H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | PHILLIPS | 100 PHILLIPS ST | 073 | FRA | 2022-09-28 | U125559 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHRIS HUNGATE | 2022-09-21 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1265.73 | 0 | 0 | 0 | 1265.73 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21884186300 |  | 100254331 |  | 7348264O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | ARGILLITE | 2009 ARGILLITE RD | 089 | FLA | 2022-09-26 | U938684 | U128293 | 2021-02-04 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-09-21 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 7040.46 | 0 | 0 | 0 | 7040.46 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21884269800 |  | 100251091 |  | 7340268J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | OLIVE | 304 OLIVE ST | 089 | GRE | 2022-09-21 | U135195 | U128293 | 2021-02-04 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-21 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916448100 |  | 100263485 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | WESTVIEW | 500 WESTVIEW DR | 019 | ASH | 2022-09-21 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-21 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1695.19 | 0 | 0 | 0 | 1695.19 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916448300 |  | 100263464 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | WESTVIEW | 505 WESTVIEW DR | 019 | ASH | 2022-09-21 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-21 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2207.44 | 0 | 0 | 0 | 2207.44 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916448400 |  | 100263465 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | WESTVIEW | 507 WESTVIEW DR | 019 | ASH | 2022-09-21 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-21 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2958.18 | 0 | 0 | 0 | 2958.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958628900 |  | 100453747 |  | 6720212M | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | HANOVER | 121 N HANOVER AV 1 | 067 | LEX | 2022-09-21 | U126308 | U134723 | 2021-12-08 | 2022-12-30 |  |  | O MAYNARD | 2022-09-21 | 2022-09-20 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10 | 1 | 8946.82 | 626.18 | 0 | 34.93 | 8285.71 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959036200 |  | 100315273 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | STATE | 203 STATE ST 1 | 067 | LEX | 2022-09-21 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-09-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12 | 1 | 6282.44 | 770.63 | 0 | 113.98 | 5397.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959036400 |  | 100315308 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | STATE | 206 STATE ST | 067 | LEX | 2022-09-21 | U461423 | U134723 | 2021-12-10 | 2022-12-30 |  |  | KKOUNS | 2022-09-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2572.7 | 0 | 0 | 0 | 2572.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959037000 |  | 100315288 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | STATE | 221 STATE ST | 067 | LEX | 2022-09-21 | U461423 | U134723 | 2021-12-10 | 2022-12-30 |  |  | KKOUNS | 2022-09-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.5 | 1 | 3082.64 | 605.86 | 0 | 537.5 | 1939.28 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960237100 |  | 100321006 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | MAXWELL | 321 E MAXWELL ST | 067 | LEX | 2022-10-12 | U461375 | U134723 | 2021-12-17 | 2022-12-30 |  |  | LARRY BROWN | 2022-09-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2680.39 | 0 | 0 | 0 | 2680.39 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026198400 |  |  |  | 7240212B | 2289295 | U122858 |  | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2621M | RICHMOND | RICHMOND AV | 173 | MT | 2022-09-30 | U460266 | U136124 | 2022-06-06 | 2022-12-30 | 2022-12-31 | 2022-09-21 | CCOX | 2022-09-21 | 2022-09-21 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00909 | 3200909 |  |  | WP1984 |  |  | 100 | 090932220261984 | 3.65 | 0 | 5538.33 | 260.04 | 0 | 78.15 | 5174.3 | 0 | 25.84 | 0
KY | KY - CENTRAL | 2629 | 22026198500 |  |  |  | 7240212B | 2289295 | U122858 |  | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2621M | RICHMOND | RICHMOND AV | 173 | MT | 2022-09-29 | U460266 | U136124 | 2022-06-06 | 2022-12-30 | 2022-12-31 | 2022-09-21 | CCOX | 2022-09-21 | 2022-09-21 |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00910 | 3200910 |  |  | WP1985 |  |  | 100 | 091032220261985 | 5.0667 | 0 | 450.09 | 368.03 | 0 | 82.06 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22100787300 |  | 100271816 |  | 6684228K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309097 | 2621P | LOGAN | 219 LOGAN ST | 073 | FRA | 2022-09-21 | DCOLLIN | U125208 | 2022-05-16 | 2022-09-21 | 2024-05-31 |  | DCOLLIN | 2022-09-21 | 2022-06-24 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 9.8833 | 2 | 5028.76 | 660.67 | 762.36 | 70.65 | 3535.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125998000 |  | 100333662 |  | 6720212I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 3RD | 408 E 3RD ST | 067 | LEX | 2022-09-22 | U127206 | U130722 | 2022-08-23 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-21 | 2022-09-07 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.0167 | 3 | 4676.8 | 676.04 | 0 | 37.75 | 3963.01 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129019400 |  | 100423982 |  | 6684228D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OLD DAILEY | 218 OLD DAILEY AV | 073 | FRA | 2022-10-19 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-09-21 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129019500 |  | 500899023 |  | 6680224K | 0356194 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OLD STATION | 116 OLD STATION RD | 073 | FRA | 2023-01-23 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-09-21 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129029100 |  | 100262834 |  | 7356256K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HIGHLAND | 1528 HIGHLAND AV WWD | 019 | ASH | 2022-09-21 | U125566 | U130722 | 2022-09-05 | 2022-09-19 |  |  | DAVID SKAGGS | 2022-09-21 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1458.7 | 0 | 0 | 0 | 1458.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129029700 |  | 100244000 |  | 7356256J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NERVIE | 1738 NERVIE ST | 019 | ASH | 2022-09-21 | U125566 | U130722 | 2022-09-05 | 2022-09-19 |  |  | DAVID SKAGGS | 2022-09-21 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1458.7 | 0 | 0 | 0 | 1458.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129050000 |  | 100402485 |  | 6720208O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FOLKSTONE | 518 FOLKSTONE DR | 067 | LEX | 2022-09-21 | U123111 | U130722 | 2022-09-05 | 2022-12-30 |  |  | LYN STAFFORD | 2022-09-21 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.6 | 2 | 3919.44 | 329.18 | 0 | 313.15 | 3277.11 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129054100 |  | 100277041 |  | 6684228D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OLD DAILEY | 215 OLD DAILEY AV | 073 | FRA | 2022-10-19 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-09-21 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129067700 |  | 100243753 |  | 7356256G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SIMPSON | 3316 SIMPSON RD | 019 | ASH | 2022-09-21 | U123965 | U130722 | 2022-09-05 | 2022-09-09 |  |  | MBLANKE | 2022-09-21 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.5833 | 1 | 1701.22 | 134.42 | 0 | 7.5 | 1559.3 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129068300 |  | 100246807 |  | 7352256L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 29TH | 3106 S 29TH ST | 019 | ASH | 2022-09-21 | U125566 | U130722 | 2022-09-05 | 2022-09-09 |  |  | DAVID SKAGGS | 2022-09-21 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1458.7 | 0 | 0 | 0 | 1458.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129083200 |  | 100336699 |  | 6720212I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 4TH | 413 E 4TH ST | 067 | LEX | 2022-09-22 | U127206 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-21 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1708.57 | 0 | 0 | 0 | 1708.57 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129089300 |  | 100277776 |  | 6688228E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 754 E MAIN ST | 073 | FRA | 2022-10-20 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-21 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1732.63 | 0 | 0 | 0 | 1732.63 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129089700 |  | 100462045 |  | 6688228E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PICKETT | 144 PICKETT AV | 073 | FRA | 2022-10-19 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-09-21 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129089800 |  | 100273733 |  | 6684228M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PIERCE | 501 PIERCE LN | 073 | FRA | 2022-09-28 | U125559 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHRIS HUNGATE | 2022-09-21 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129089900 |  | 100279268 |  | 6688228G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PLAINVIEW | 281 PLAINVIEW AV | 073 | FRA | 2022-09-21 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-09-21 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 9 | 1 | 1979.19 | 549.53 | 0 | 30.66 | 1399 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129095700 |  | 100349163 |  | 6748208N |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTREQD | 2621P | BROADWAY | 431 E BROADWAY ST | 049 | WIN | 2022-09-21 | NRICHIE | U125208 | 2022-09-06 | 2022-09-09 | 2022-09-30 |  | NRICHIE | 2022-09-21 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10.3333 | 2 | 1027.92 | 714.99 | 0 | 312.93 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129118800 |  | 100320517 |  | 6716212L |  |  |  | 566 | EX | ABANDON SL-IDLE/INACTIVE | 2621P | M L KING | 343 S M L KING BV | 067 | LEX | 2022-09-22 | U125208 | U461383 | 2022-09-06 | 2022-09-21 | 2022-12-31 |  | RSTRONG | 2022-09-21 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.1333 | 1 | 2378.69 | 476.41 | 21.16 | 40.14 | 1840.98 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22133371000 |  | 100336821 |  | 6720212E | 2177145 |  |  | 565 | EX | REPLACE SL W/21-0269978-00 | 2600B | 4TH | 123 E 4TH ST 1F | 067 | LEX | 2022-09-21 | U126532 | U134723 | 2022-09-21 | 2022-12-30 |  |  | LESLIE SHARON | 2022-09-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2977.52 | 0 | 0 | 0 | 2977.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22133411200 |  | 100321007 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | MAXWELL | 319 E MAXWELL ST | 067 | LEX | 2022-10-12 | U461375 | U125201 | 2022-09-21 | 2022-11-30 |  |  | LARRY BROWN | 2022-09-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2696.94 | 0 | 0 | 0 | 2696.94 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22970121300 |  | 100280380 |  | 6688228F | 2181158 |  |  | 565 | EX | REPLACE SL W/21-0261319-00 | 2600B | VERSAILLES | 265 VERSAILLES RD | 073 | FRA | 2022-09-21 | U128410 | U134723 | 2022-01-27 | 2022-12-30 |  |  | CDESPAIN | 2022-09-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 7767.71 | 0 | 0 | 0 | 7767.71 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979018200 |  | 100246097 |  | 7320284H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | STATE RT 8 | 2667 STATE RT 8 | 089 | S P | 2022-09-21 | U135195 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | KEITH HEDGES | 2022-09-21 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979022800 |  | 100258505 |  | 7344264C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CHINN | 414 CHINN ST | 089 | WUR | 2022-09-21 | U135195 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | KEITH HEDGES | 2022-09-21 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22979029200 |  | 100276493 |  | 6684228H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MEAGHER | 206 MEAGHER AV | 073 | FRA | 2022-10-20 | U125881 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | HERBERT HAYDEN | 2022-09-21 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1836.7 | 0 | 0 | 0 | 1836.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979048300 |  | 100458243 |  | 7352264I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ETNA | 424 ETNA ST | 089 | RUS | 2022-09-21 | U135195 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | KEITH HEDGES | 2022-09-21 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983422600 |  | 100402258 |  | 6720204B | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 3375 GREENTREE RD | 067 | LEX | 2022-09-21 | U129731 | U134723 | 2022-03-03 | 2022-12-30 |  |  | F.GOINS | 2022-09-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2544.7 | 0 | 0 | 0 | 2544.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983768100 |  | 100324776 |  | 6720204B | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 1136 GREENTREE CT | 067 | LEX | 2022-09-21 | U461309 | U134723 | 2022-03-04 | 2022-12-30 |  |  | R.HUMPHREYS | 2022-09-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10 | 1 | 2429.73 | 594.26 | 347.84 | 128.4 | 1359.23 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21026120000 |  |  |  | 6736236A | 2070683 | U124399 |  | 559 | EX | PM-PARIS CYNTHIANA REPLACEMENT | 5320E | US 27 | US 27 | 017 | PAR | 2024-01-19 | U128132 | U124399 | 2021-04-28 | 2021-12-29 | 2021-12-31 | 2022-09-22 | SWBISHOP | 2022-09-22 |  |  | C | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00559 | 3201013 |  |  | WP1200 | KSMRP |  | 100 | 101332210261200 |  | 4 | 1437073.2 | -6871.44 | 282024.39 | 7952.61 | 925471.58 | 0 | 28603.08 | 199892.98 | 4
KY | KY - CENTRAL | 2629 | 21026120100 |  |  |  | 6736236A | 2070683 | U124399 |  | 560 | EX | PM-PARIS CYNTHIANA ABANDONMENT | 5320E | US 27 | US 27 | 017 | PAR | 2024-01-19 | U128132 | U124399 | 2021-04-28 | 2021-12-29 | 2021-12-31 | 2022-09-22 | SWBISHOP | 2022-09-22 |  |  | C | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00560 | 3201014 |  |  | WP1201 | KSMRP |  | 100 | 101432210261201 |  | 0 | 325920.13 | 21373.74 | 268595.92 | 6.3 | 35944.17 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883066300 |  | 500061525 |  | 6676224L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LOUISVILLE | 3395 LOUISVILLE RD | 073 | FRA | 2022-10-20 | U125881 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-09-22 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 2180.38 | 0 | 0 | 0 | 2180.38 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883073200 |  | 100257671 |  | 7344268A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CAROLINE | 208 CAROLINE AV | 089 | WUR | 2022-09-22 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-22 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883157100 |  | 500188420 |  | 7352260P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WINCHESTER | 500 WINCHESTER AV SP 568 | 019 | ASH | 2022-09-22 | U123965 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | MBLANKE | 2022-09-22 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4 | 1 | 1717.63 | 209.16 | 0 | 49.77 | 1458.7 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883217900 |  | 100280385 |  | 6688228F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | VERSAILLES | 195 VERSAILLES RD | 073 | FRA | 2022-09-22 | DCOLLIN | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DCOLLIN | 2022-09-22 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.86667 | 1 | 939.14 | 58.92 | 18.53 | 6.59 | 855.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883221800 |  | 500019544 |  | 7344268P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | GAINESWAY | 1624 GAINESWAY DR | 089 | WOR | 2022-09-22 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-22 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883231100 |  | 100287133 |  | 6720212G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DARLEY | 832 DARLEY DR | 067 | LEX | 2022-09-26 | U125208 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | HMCKUNE | 2022-09-22 | 2022-01-04 |  | D | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 18.2833 | 8 | 1112.17 | 1034.37 | 19.65 | 58.15 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883269600 |  | 500033444 |  | 7324284A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 12TH | 101 12TH ST | 089 | S P | 2022-09-22 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-22 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883270500 |  | 100279606 |  | 6688228O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | VERSAILLES | 635 VERSAILLES RD | 073 | FRA | 2022-09-22 | DCOLLIN | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DCOLLIN | 2022-09-22 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.33333 | 1 | 880.14 | 23.71 | 0 | 1.33 | 855.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21884195500 |  | 500499369 |  | 7328284K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | GENE | 23 GENE RD | 089 | S S | 2022-09-22 | U135195 | U128293 | 2021-02-04 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-22 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1487.89 | 0 | 0 | 0 | 1487.89 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916448000 |  | 100263472 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | WESTVIEW | 349 WESTVIEW DR | 019 | ASH | 2022-09-22 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-22 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1717.56 | 0 | 0 | 0 | 1717.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916448500 |  | 100263471 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | WESTVIEW | 601 WESTVIEW DR | 019 | ASH | 2022-09-22 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-22 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3000.3 | 0 | 0 | 0 | 3000.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959036500 |  | 100315280 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | STATE | 207 STATE ST | 067 | LEX | 2022-09-22 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-09-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2760.45 | 513.76 | 0 | 62.01 | 2184.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959036900 |  | 100315287 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | STATE | 219 STATE ST | 067 | LEX | 2022-10-05 | U461423 | U134723 | 2021-12-10 | 2022-12-30 |  |  | KKOUNS | 2022-09-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2906.49 | 478.57 | 0 | 450.85 | 1977.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959047400 |  | 100315345 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | UNIVERSITY | 213 UNIVERSITY AV | 067 | LEX | 2022-09-26 | U461423 | U134723 | 2021-12-10 | 2022-12-30 |  |  | KKOUNS | 2022-09-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1131.54 | 0 | 0 | 0 | 1131.54 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026173700 |  |  |  | 6764176N | 2286833 | U132703 |  | 909 | EX | 2022 SCADA VISIBILITY PROGRAM | 2600E | WISEMANTOWN | WISEMANTOWN RD | 065 | IRV | 2022-10-03 | U462463 | U132703 | 2022-03-04 | 2022-10-25 | 2022-11-30 | 2022-09-22 | EBLANTON | 2022-09-22 | 2022-05-13 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00909 | 3200909 |  |  | WP1737 | SCADA |  | 100 | 090932220261737 | 30.6667 | 0 | 28387.14 | 1996.1 | 0 | 180.07 | 26153.42 | 0 | 57.55 | 0
KY | KY - WEST | 2621 | 22114555200 |  | 100292386 |  | 6720216K |  |  |  | 565 | EX | SERVICE LINE - REPLACE/UNMTRD | 2621P | THURMAN | 517 THURMAN DR | 067 | LEX | 2022-09-22 | LSTANFI | U125208 | 2022-07-07 | 2022-08-05 | 2022-09-07 |  | LSTANFI | 2022-09-22 | 2022-09-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 34.5667 | 11 | 2852.33 | 2480.63 | 137.72 | 150.38 | 83.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129006600 |  | 100271043 |  | 6744288I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | WILLOW LNXBURG | 4878 WILLOW LNXBURG RD | 023 | FOS | 2022-09-22 | SDADAMS | U130722 | 2022-09-05 | 2022-12-30 |  |  | SDADAMS | 2022-09-22 | 2022-09-22 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 3.0333 | 2 | 300.92 | 196.75 | 16.31 | 87.86 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129009800 |  | 500130541 |  | 7352260P | 0992282 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WINCHESTER | 500 WINCHESTER AV SP 142 | 019 | ASH | 2022-09-22 | U123965 | U130722 | 2022-09-05 | 2022-12-30 |  |  | MBLANKE | 2022-09-22 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.066667 | 1 | 1463.22 | 3.65 | 0 | 0.87 | 1458.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129010100 |  | 100263991 |  | 7352260O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KELLEYS | 742 KELLEYS CR | 019 | ASH | 2022-11-23 | U125566 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DAVID SKAGGS | 2022-09-22 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1861.1 | 0 | 0 | 0 | 1861.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129016400 |  | 100290121 |  | 6720212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LOCUST | 217 LOCUST AV | 067 | LEX | 2022-09-27 | U123111 | U130722 | 2022-09-05 | 2022-12-30 |  |  | LYN STAFFORD | 2022-09-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0 | 1 | 1779.17 | 0 | 0 | 0 | 1779.17 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129019600 |  | 100280293 |  | 6688228J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ROLLING ACRES | 207 ROLLING ACRES DR | 073 | FRA | 2022-09-28 | U125559 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHRIS HUNGATE | 2022-09-22 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129019700 |  | 100280491 |  | 6688228J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ROLLING ACRES | 191 ROLLING ACRES DR | 073 | FRA | 2022-09-28 | U125559 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHRIS HUNGATE | 2022-09-22 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129019800 |  | 100280969 |  | 6684228L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SAINT CHARLES | 324 SAINT CHARLES ST | 073 | FRA | 2022-09-27 | U129731 | U130722 | 2022-09-05 | 2022-12-30 |  |  | F.GOINS | 2022-09-22 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129032100 |  | 100246495 |  | 7356256I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RIDGEWAY | 3204 RIDGEWAY DR | 019 | ASH | 2022-09-22 | U123965 | U130722 | 2022-09-05 | 2022-09-09 |  |  | MBLANKE | 2022-09-22 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 9.2667 | 2 | 3306.32 | 485.34 | 0 | 61.86 | 2759.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129045400 |  | 100287285 |  | 6720212G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MEADOW | 1054 MEADOW LN | 067 | LEX | 2022-09-26 | U123111 | U130722 | 2022-09-05 | 2022-12-30 |  |  | LYN STAFFORD | 2022-09-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.95 | 1 | 2928.67 | 589.1 | 0 | 560.4 | 1779.17 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129052800 |  | 100277172 |  | 6684228H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HOLMES | 533 HOLMES ST FT | 073 | FRA | 2022-09-27 | U129731 | U130722 | 2022-09-05 | 2022-12-30 |  |  | F.GOINS | 2022-09-22 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1929.78 | 0 | 0 | 0 | 1929.78 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129053600 |  | 100280428 |  | 6688228F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 859 E MAIN ST 6 | 073 | FRA | 2022-09-27 | U129731 | U130722 | 2022-09-05 | 2022-12-30 |  |  | F.GOINS | 2022-09-22 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129053700 |  | 100280933 |  | 6684228L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 315 E MAIN ST | 073 | FRA | 2022-10-20 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-22 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1930.34 | 0 | 0 | 0 | 1930.34 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129054200 |  | 100277048 |  | 6684228D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OLD DAILEY | 405 OLD DAILEY AV | 073 | FRA | 2022-09-27 | U129731 | U130722 | 2022-09-05 | 2022-09-22 |  |  | F.GOINS | 2022-09-22 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 10 | 1 | 1785.88 | 629.41 | 0 | 130.35 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129054400 |  | 500601436 |  | 6684228K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RIVER RIDGE | 2011 RIVER RIDGE RD 2 | 073 | FRA | 2022-09-28 | U125559 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHRIS HUNGATE | 2022-09-22 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1535.48 | 0 | 0 | 0 | 1535.48 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129067500 |  | 100267144 |  | 7352256L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SARAH | 2332 SARAH RD | 019 | ASH | 2022-09-22 | U125566 | U130722 | 2022-09-05 | 2022-09-09 |  |  | DAVID SKAGGS | 2022-09-22 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1659.9 | 0 | 0 | 0 | 1659.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129068200 |  | 100261238 |  | 7352256G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 13TH | 2841 13TH ST | 019 | ASH | 2022-09-26 | U125208 | U130722 | 2022-09-05 | 2022-09-09 |  |  | MBLANKE | 2022-09-22 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.2833 | 1 | 1606.29 | 119.22 | 0 | 28.37 | 1458.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129084200 |  | 100336676 |  | 6720212I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HAWKINS | 454 HAWKINS AV | 067 | LEX | 2022-09-22 | U127206 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 4470.46 | 602.79 | 0 | 33.63 | 3834.04 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22131270600 |  | 100271042 |  | 6744288I |  |  |  | 565 | EX | SERVICE LINE - RELOCATE | 2621P | WILLOW LNXBURG | 4858 WILLOW LNXBURG RD | 023 | FOS | 2022-09-22 | U930915 | U125208 | 2022-09-14 | 2022-09-16 | 2022-09-23 |  | SDADAMS | 2022-09-22 | 2022-09-21 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 | 13.1833 | 2 | 1402.7 | 857.4 | 423.77 | 47.83 | 73.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22132010600 |  | 100316574 |  | 6716208F |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | PENMOKEN | 158 PENMOKEN PA | 067 | LEX | 2022-09-26 | U125208 | U125208 | 2022-09-19 | 2022-09-22 |  |  | RSTRONG | 2022-09-22 | 2022-09-20 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.3667 | 3 | 3657.86 | 626.09 | 264.48 | 51.09 | 2716.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22133458500 |  | 100328865 |  | 6720208F |  |  |  | 565 | EX | GRADE 1 REPLACE SERV LINE | 2621P | LAKESHORE | 401 LAKESHORE DR | 067 | LEX | 2022-09-22 | WISHII | U136097 | 2022-09-21 | 2022-09-21 | 2022-09-21 |  | WISHII | 2022-09-22 | 2022-09-22 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.4167 | 2 | 1424.21 | 937.82 | 307.45 | 84.34 | 94.6 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979022400 |  | 100257680 |  | 7344264A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KENTUCKY | 118 KENTUCKY AV | 089 | WUR | 2022-09-22 | U135195 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | KEITH HEDGES | 2022-09-22 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979023400 |  | 100259603 |  | 7348264C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PROSPECT | 1405 PROSPECT AV | 089 | WOR | 2022-09-22 | U135195 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | KEITH HEDGES | 2022-09-22 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22979037100 |  | 100336677 |  | 6720212I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HAWKINS | 456 HAWKINS AV | 067 | LEX | 2022-09-22 | U127206 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | JUSTIN HOBBS | 2022-09-22 | 2022-04-15 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.1167 | 3 | 2839.09 | 179.81 | 0 | 440.32 | 2218.96 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979051500 |  | 500214150 |  | 7348244H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | STATE RT 3117 | 269 STATE RT 3117 | 089 | S S | 2022-09-22 | U135195 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | KEITH HEDGES | 2022-09-22 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983421600 |  | 100324768 |  | 6720204A | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 1112 GREENTREE CT | 067 | LEX | 2022-09-22 | U461309 | U134723 | 2022-03-03 | 2022-12-30 |  |  | R.HUMPHREYS | 2022-09-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10 | 1 | 2412.89 | 594.26 | 347.84 | 128.4 | 1342.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983423100 |  | 100324755 |  | 6720204B | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 3394 GREENTREE RD | 067 | LEX | 2022-09-22 | U126530 | U134723 | 2022-03-03 | 2022-12-30 |  |  | JDUNN | 2022-09-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3386.94 | 0 | 0 | 0 | 3386.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 05612244800 |  | 100297918 |  | 6716212G | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NEWTOWN | 275 NEWTOWN PK | 067 | LEX | 2022-09-23 | TROE | SSUTHER | 2005-05-26 | 2022-07-01 | 2022-12-31 |  | TROE | 2022-09-23 | 2022-09-15 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.9833 | 5 | 996.95 | 944.23 | 0 | 52.72 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 11881795500 |  | 100264574 |  | 7384168G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SR 292 | 2948 SR 292 | 195 | S W | 2022-09-26 | U125208 | U906307 | 2011-01-28 | 2022-07-01 | 2022-12-31 |  | JCKIRK | 2022-09-23 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 8.5 | 1 | 612.22 | 579.87 | 0 | 32.35 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12964557000 |  | 100336627 |  | V-1021-59 |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | RACE | 449 RACE ST 2 | 067 | LEX | 2022-09-23 | TROE | U125208 | 2012-04-10 | 2014-12-23 |  |  | TROE | 2022-09-23 | 2022-06-06 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.4667 | 5 | 685.56 | 365.06 | 0 | 320.5 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21882323100 |  | 100425885 |  | 6740232M | 2075121 |  |  | 566 | EX | ABANDONED SL W/CAPITOL JOB | 2600B | 8TH | 220 W 8TH ST | 017 | PAR | 2022-09-28 | U123111 | U131066 | 2021-01-28 | 2022-09-30 |  |  | LYN STAFFORD | 2022-09-23 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26290043 |  | 1
KY | KY - EAST | 2631 | 21883092100 |  | 500508681 |  | 7348264K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | ARGILLITE | 1513 ARGILLITE RD | 089 | FLA | 2022-09-23 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-23 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883240300 |  | 100273267 |  | 6684224A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LOUISVILLE | 1201 LOUISVILLE RD | 073 | FRA | 2022-11-02 | U125881 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-09-23 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 2877.78 | 0 | 0 | 0 | 2877.78 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883291600 |  | 500765418 |  | 6688228P | 0147606 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | VERSAILLES | 1348 VERSAILLES RD | 073 | FRA | 2022-09-28 | U930915 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DCOLLIN | 2022-09-23 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 1.8833 | 1 | 1022.92 | 126.63 | 27 | 14.19 | 855.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959039500 |  | 100315348 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | UNIVERSITY | 221 UNIVERSITY AV | 067 | LEX | 2022-09-23 | U126308 | U134723 | 2021-12-10 | 2022-12-30 |  |  | J ENSMINGER | 2022-09-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1442.31 | 0 | 0 | 0 | 1442.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959044000 |  | 100315284 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | STATE | 213 STATE ST 1FL | 067 | LEX | 2022-09-23 | U126308 | U134723 | 2021-12-10 | 2022-12-30 |  |  | J ENSMINGER | 2022-09-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2402.45 | 0 | 0 | 0 | 2402.45 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22026222500 |  |  |  | 7256280P | 2291412 | U128885 |  | 557 | EX | EMER - INSTALL 5'-6" PMMP | 2621P | 3RD | 206 E 3RD ST | 161 | MAY | 2022-09-27 | U128132 | U128885 | 2022-09-07 | 2022-08-26 | 2022-09-02 | 2022-09-02 | LSTANFIELD | 2022-09-23 | 2022-09-22 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00557 | 3200557 |  |  | WP2225 |  |  | 100 | 055732220262225 | 2.5 | 3 | 5673.45 | 4560.94 | 0 | 258.56 | 0 | 0 | 5.33 | 848.62 | 3
KY | KY - CENTRAL | 2632 | 22026222600 |  |  |  | 7256280P | 2291412 | U128885 |  | 558 | EX | EMER - RETIRE 5'-6" PMMP | 2621P | 3RD | 206 E 3RD ST | 161 | MAY | 2022-09-27 | U128132 | U128885 | 2022-09-07 | 2022-09-02 | 2022-09-02 | 2022-09-02 | LSTANFIELD | 2022-09-23 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00558 | 3200558 |  |  | WP2226 |  |  | 100 | 055832220262226 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129018500 |  | 100271849 |  | 6684228K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DIXIE ALY | 305 DIXIE ALY | 073 | FRA | 2022-10-03 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-09-23 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129018700 |  | 100277102 |  | 6684228D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HOLMES | 911 HOLMES ST | 073 | FRA | 2022-10-10 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-09-23 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8 | 1 | 1843.06 | 488.47 | 0 | 27.25 | 1327.34 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129019200 |  | 100273898 |  | 6680228H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MOSS | 905 MOSS LN | 073 | FRA | 2022-09-26 | U125559 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHRIS HUNGATE | 2022-09-23 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129053500 |  | 100273036 |  | 6684224A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LOUISVILLE | 1101 LOUISVILLE RD | 073 | FRA | 2022-10-20 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-23 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129089000 |  | 500564205 |  | 6684224I | 9722175 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LEONARDWOOD | 325 LEONARDWOOD DR | 073 | FRA | 2022-10-07 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-09-23 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 930.23 | 66.64 | 0 | 4.59 | 859 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129089200 |  | 100273564 |  | 6680224G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LOUISVILLE | 1730 LOUISVILLE RD | 073 | FRA | 2022-10-04 | U132386 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-09-23 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129090100 |  | 100273869 |  | 6680228H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RICHARDSON | 706 RICHARDSON LN | 073 | FRA | 2022-09-26 | U125559 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHRIS HUNGATE | 2022-09-23 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 2320 | 0 | 0 | 0 | 2320 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22130999000 |  | 501294291 |  | 6716220M | 2072675 |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | BARLEYS PASS | 1116 BARLEYS PASS | 067 | LEX | 2022-09-23 | WISHII | U132002 | 2022-09-13 | 2022-09-27 | 2022-10-13 |  | WISHII | 2022-09-23 | 2022-09-20 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.3667 | 3 | 785.8 | 708.59 | 14.96 | 62.25 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22131833000 |  | 100330290 |  | 6720208B |  |  |  | 565 | EX | SERVICE LINE - REPLACE D303818 | 2621P | QUEENSWAY | 331 QUEENSWAY DR | 067 | LEX | 2022-09-26 | U930915 | U129939 | 2022-09-16 | 2022-09-19 | 2022-10-07 |  | HMCKUNE | 2022-09-23 | 2022-09-22 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.3667 | 4 | 1389.98 | 1227.27 | 94.21 | 68.5 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22132405000 |  | 100258702 |  | 7356256B |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | MONTGOMERY | 2401 MONTGOMERY AV | 019 | ASH | 2022-09-26 | DYOUNG | U132002 | 2022-09-20 | 2022-10-04 | 2022-10-20 |  | RECUMP | 2022-09-23 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 15.3333 | 2 | 1042.38 | 955.41 | 19.04 | 67.93 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22134004900 |  | 100290228 |  | 6720212B | 1635077 |  |  | 566 | EX | RETIRE SERVICE LINE - LEAKAGE | 2621P | EDGELAWN | 1405 EDGELAWN AV | 067 | LEX | 2022-09-23 | LSTANFI | U129005 | 2022-09-23 | 2022-09-23 | 2022-10-23 |  | LSTANFI | 2022-09-23 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.0833 | 7 | 1571.75 | 1465.13 | 19.65 | 86.97 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22134063100 |  | 100353467 |  | 7256280K | 2180424 |  |  | 565 | EX | REPLACE SL W/21-0261272-00 | 2600B | SHORT | 213 SHORT ST | 161 | MAY | 2022-10-18 | U461478 | U125768 | 2022-09-23 | 2049-12-31 |  |  | DAVID STAGGS | 2022-09-23 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2944.29 | 0 | 0 | 0 | 2944.29 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22134063300 |  | 100353468 |  | 7256280K | 2180424 |  |  | 565 | EX | REPLACE SL W/21-0261272-00 | 2600B | SHORT | 215 SHORT ST | 161 | MAY | 2022-10-18 | U461478 | U125768 | 2022-09-23 | 2049-12-31 |  |  | DAVID STAGGS | 2022-09-23 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2893.88 | 0 | 0 | 0 | 2893.88 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979021300 |  | 100254123 |  | 7348264M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BELLEFONTE | 1425 BELLEFONTE RD | 089 | FLA | 2022-09-23 | U135195 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | KEITH HEDGES | 2022-09-23 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11898558400 |  | 100332575 |  | 16720212I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BELL | 219 BELL PL | 067 | LEX | 2022-09-26 | RSTRONG | U906631 | 2011-03-30 | 2022-07-01 | 2022-12-31 |  | RSTRONG | 2022-09-26 | 2022-09-01 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.15 | 2 | 1106.7 | 210.49 | 0 | 11.86 | 884.35 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18026772300 |  |  |  | 7348264H | 1100065 | U461383 |  | 588 | EX | CONVERT FROM GMB TO CAB ACCT | 2634M | VERNON | 900 VERNON ST | 089 | RUS | 2022-10-18 | SREYNOL | U461383 | 2018-05-11 | 2022-12-29 | 2022-12-31 | 2022-09-26 | DASH | 2022-09-26 |  |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00588 | 3200588 |  |  | WP7723 |  |  | 100 | 058832180267723 |  | 0 | 725.53 | 54.17 | 653.63 | 17.73 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883079500 |  | 100274834 |  | 6684228J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | TAYLOR | 603 TAYLOR AV | 073 | FRA | 2022-10-20 | U125881 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-09-26 | 2022-10-11 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.75 | 1 | 2096.17 | 47.42 | 0 | 33.93 | 2014.82 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883197200 |  | 100255334 |  | 7348264K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | ARGILLITE | 1609 ARGILLITE RD | 089 | FLA | 2022-09-26 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-26 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883250300 |  | 100344103 |  | 7356248T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LAKE BONITA | 5842 LAKE BONITA RD | 019 | CAT | 2022-09-26 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-09-26 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883265500 |  | 100252336 |  | 7348264K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | ARGILLITE | 1408 ARGILLITE RD | 089 | FLA | 2022-09-26 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-26 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 6584.96 | 0 | 0 | 0 | 6584.96 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883288400 |  | 100344110 |  | 7356248T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LAKE BONITA | 5208 LAKE BONITA RD | 019 | CAT | 2022-09-26 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-09-26 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883320200 |  | 100307971 |  | 6716212K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MERINO | 603 MERINO ST | 067 | LEX | 2022-09-26 | WISHII | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WISHII | 2022-09-26 | 2022-09-26 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.7833 | 4 | 404.05 | 377.11 | 0 | 26.94 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21897553900 |  | 100290123 |  | LOCUST A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | LOCUST | 215 LOCUST AV | 067 | LEX | 2022-09-26 | U129731 | AOC SYST | 2021-03-26 | 2021-09-24 | 2022-12-31 |  | F.GOINS | 2022-09-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26210032 | 4.0833 | 1 | 5444.53 | 258.05 | 0 | 53.47 | 5133.01 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916430800 |  | 500967920 |  | 7352256C | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2621P | LEE | 296 LEE ST | 019 | ASH | 2022-09-26 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2434.48 | 0 | 0 | 0 | 2434.48 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916447800 |  | 501190197 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2621P | WESTVIEW | 180 WESTVIEW DR | 019 | ASH | 2022-09-26 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1677.89 | 0 | 0 | 0 | 1677.89 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916447900 |  | 100463164 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | WESTVIEW | 337 WESTVIEW DR | 019 | ASH | 2022-09-26 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2629.85 | 0 | 0 | 0 | 2629.85 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958596200 |  | 100332036 |  | 6720212N | 2180410 |  |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | CRAMER | 735 CRAMER AV 1 | 067 | LEX | 2022-09-26 | U126308 | U134723 | 2021-12-08 | 2022-12-30 |  |  | J ENSMINGER | 2022-09-26 | 2022-06-22 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3 | 2 | 8034.41 | 191.03 | 0 | 529.63 | 7313.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959032400 |  | 100315239 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | CONN TER | 122 CONN TER | 067 | LEX | 2022-09-26 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-09-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 3253.33 | 513.76 | 0 | 104.86 | 2634.71 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959036700 |  | 100315281 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | STATE | 209 STATE ST | 067 | LEX | 2022-09-26 | U461423 | U134723 | 2021-12-10 | 2022-12-30 |  |  | KKOUNS | 2022-09-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 3683.46 | 478.57 | 0 | 450.85 | 2754.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960236500 |  | 100427030 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | MAXWELL | 305 E MAXWELL ST 2-1FL | 067 | LEX | 2022-10-12 | U461375 | U134723 | 2021-12-17 | 2022-12-30 |  |  | LARRY BROWN | 2022-09-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3121.44 | 0 | 0 | 0 | 3121.44 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026233200 |  |  |  | 6712236G | 2070683 | U124399 |  | 559 | VO | PM- GREENSITE TRABU INSTALL | 5320E | TRABU | TRABU RD | 209 | GEO | 2023-03-15 |  | U124399 | 2022-10-24 | 2022-12-29 | 2022-12-31 | 2022-09-26 | SWBISHOP | 2022-09-26 |  |  | C | [11 empty] | 23026253100 | 100 |  |  | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026233300 |  |  |  | 6712236G | 2070683 | U124399 |  | 560 | VO | PM- GREENSITE TRABU ABANDON | 5320E | TRABU | TRABU RD | 209 | GEO | 2023-03-15 |  | U124399 | 2022-10-24 | 2022-12-29 | 2022-12-31 | 2022-09-26 | SWBISHOP | 2022-09-26 |  |  | C | [11 empty] | 23026253200 | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22111228800 |  | 100294552 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BROADWAY | 516 N BROADWAY ST | 067 | LEX | 2022-09-27 | U930915 | U130722 | 2022-06-20 | 2022-12-30 |  |  | RSTRONG | 2022-09-26 | 2022-08-31 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.7833 | 2 | 1414.16 | 383.65 | 0 | 175.41 | 855.1 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22128772300 |  | 100240961 |  | 7324132F |  |  |  | 566 | EX | ABANDON SL- DEMO/CUST REQ | 2621P | MAIN | 898 MAIN ST E | 119 | HIN | 2022-09-26 | JAHOWARD | KWELLS | 2022-09-02 | 2022-09-15 | 2022-10-01 |  | JAHOWARD | 2022-09-26 | 2022-09-26 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 14.95 | 3 | 1051.96 | 996.35 | 0 | 55.61 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129009300 |  | 100262688 |  | 7352256D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | POLLARD | 505 POLLARD RD | 019 | ASH | 2022-11-23 | U125566 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DAVID SKAGGS | 2022-09-26 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1760.5 | 0 | 0 | 0 | 1760.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129010300 |  | 100264103 |  | 7352256A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PIQUA | 2755 PIQUA ST | 019 | ASH | 2022-11-23 | U125566 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DAVID SKAGGS | 2022-09-26 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1861.1 | 0 | 0 | 0 | 1861.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129020100 |  | 100276495 |  | 6684228H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | TRIPLETT | 430 TRIPLETT AV | 073 | FRA | 2022-10-02 | U128762 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CORY TINCHER | 2022-09-26 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129020600 |  | 500337036 |  | 6692228N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | VILLAGE | 336 VILLAGE DR | 073 | FRA | 2022-10-02 | U128762 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CORY TINCHER | 2022-09-26 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129031200 |  | 500836233 |  | 7348248A | 1961710 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DONNA | 2201 DONNA DR B | 019 | ASH | 2022-09-26 | MBLANKE | U130722 | 2022-09-05 | 2022-09-09 |  |  | MBLANKE | 2022-09-26 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.2667 | 1 | 275.16 | 222.28 | 0 | 52.88 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129054700 |  | 500511241 |  | 6688224B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | STONEHAVEN | 1750 STONEHAVEN DR | 073 | FRA | 2022-10-02 | U128762 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CORY TINCHER | 2022-09-26 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 10 | 1 | 1825.12 | 595.06 | 0 | 128.45 | 1101.61 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129054800 |  | 100276890 |  | 6684228D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SWIGERT | 207 SWIGERT AV | 073 | FRA | 2022-10-20 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-26 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129054900 |  | 100274212 |  | 6684228N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | TODD | 217 W TODD ST | 073 | FRA | 2022-10-27 | U938516 | U130722 | 2022-09-05 | 2022-12-30 |  |  | C HUNGATE | 2022-09-26 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129064900 |  | 100243806 |  | 7356256F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BELMONT | 1008 BELMONT ST | 019 | ASH | 2022-09-26 | U123965 | U130722 | 2022-09-05 | 2022-12-30 |  |  | MBLANKE | 2022-09-26 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.6333 | 1 | 1693.05 | 189.3 | 0 | 45.05 | 1458.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129066800 |  | 100258793 |  | 7356256F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MONTGOMERY | 2721 MONTGOMERY AV | 019 | ASH | 2022-09-29 | U123965 | U130722 | 2022-09-05 | 2022-09-19 |  |  | MBLANKE | 2022-09-26 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.95 | 1 | 1469.65 | 103.52 | 0 | 24.63 | 1341.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129090600 |  | 500761206 |  | 6688228G | 0041904 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | STEPHEN | 322 STEPHEN RD | 073 | FRA | 2022-10-27 | U938516 | U130722 | 2022-09-05 | 2022-12-30 |  |  | C HUNGATE | 2022-09-26 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1843.31 | 0 | 0 | 0 | 1843.31 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129091100 |  | 100275490 |  | 6684228F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WILSON | 707 WILSON ST | 073 | FRA | 2022-10-02 | U128762 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CORY TINCHER | 2022-09-26 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 2231 | 0 | 0 | 0 | 2231 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22131445400 |  | 100338340 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | MAGOFFIN | 717 MAGOFFIN ST | 067 | LEX | 2022-09-26 | WISHII | U132002 | 2022-09-15 | 2022-09-28 | 2022-10-14 |  | WISHII | 2022-09-26 | 2022-09-26 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 20.2833 | 4 | 1102.24 | 1012.37 | 14.96 | 74.91 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22134036500 |  | 500282510 |  | 6716204K |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | WHITEWATER | 4048 WHITEWATER DR | 067 | LEX | 2022-09-27 | U128711 | U129005 | 2022-09-23 | 2022-09-23 | 2022-09-23 |  | KKINDER | 2022-09-26 | 2022-09-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.6333 | 4 | 1455.43 | 959.98 | 186.29 | 294.86 | 14.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22134063400 |  | 100353469 |  | 7256280K | 2180424 |  |  | 565 | EX | REPLACE SL W/21-0261272-00 | 2600B | SHORT | 217 SHORT ST | 161 | MAY | 2022-10-18 | U461478 | U125768 | 2022-09-23 | 2049-12-31 |  |  | DAVID STAGGS | 2022-09-26 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 3998.17 | 0 | 0 | 0 | 3998.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22134094800 |  | 100404289 |  | 6720204I |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | NILES | 3669 NILES CT | 067 | LEX | 2022-09-26 | U930915 | U125208 | 2022-09-23 | 2022-09-28 | 2022-10-14 |  | LSTANFI | 2022-09-26 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.1667 | 2 | 1015.41 | 810.98 | 149.63 | 54.8 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22134659500 |  | 100273559 |  | 6680224F |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | GAME FARM | 10 GAME FARM RD B | 073 | FRA | 2022-09-26 | DCOLLIN | U129939 | 2022-09-26 | 2022-09-26 | 2024-06-30 |  | DCOLLIN | 2022-09-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.75 | 1 | 8453.9 | 256.61 | 416.87 | 28.74 | 7751.68 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22134975900 |  | 100275489 |  | 6684228F |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | WILSON | 709 WILSON ST | 073 | FRA | 2022-10-02 | U128762 | U125763 | 2022-09-27 | 2022-12-30 |  |  | CORY TINCHER | 2022-09-26 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2623 | 22979028600 |  | 100274856 |  | 6684228J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | TAYLOR | 701 TAYLOR AV | 073 | FRA | 2022-10-20 | U125881 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | HERBERT HAYDEN | 2022-09-26 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979047700 |  | 100445869 |  | 7352256C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PRICHARD | 203 PRICHARD ST | 019 | ASH | 2022-09-26 | U123965 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | MBLANKE | 2022-09-26 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.15 | 1 | 1926.83 | 7.86 | 0 | 1.87 | 1917.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983426300 |  | 100324777 |  | 6720204B | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 3395 GREENTREE RD | 067 | LEX | 2022-09-26 | U126530 | U134723 | 2022-03-03 | 2022-12-30 |  |  | JDUNN | 2022-09-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2120.85 | 0 | 0 | 0 | 2120.85 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026253100 |  |  |  | 6736240L | 2070683 | U124399 |  | 559 | CO | PM- GREENSITE TRABU INSTALL | 5320E | TRABU | TRABU RD | 017 | PAR | 2023-01-25 |  | U124399 | 2023-01-24 | 2022-12-29 | 2022-12-31 | 2022-09-26 | SWBISHOP | 2022-09-26 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00559 | 3201013 |  |  | WP2531 | KSMRP |  | 100 | 101332230262531 |  | 44 | 30739.67 | 337.01 | 86.92 | 306.36 | 24987.3 | 0 | 0 | 5022.08 | 44
KY | KY - CENTRAL | 2629 | 23026253200 |  |  |  | 6736240L | 2070683 | U124399 |  | 560 | CO | PM- GREENSITE TRABU ABANDON | 5320E | TRABU | TRABU RD | 017 | PAR | 2023-01-25 |  | U124399 | 2023-01-24 | 2022-12-29 | 2022-12-31 | 2022-09-26 | SWBISHOP | 2022-09-26 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00560 | 3201014 |  |  | WP2532 | KSMRP |  | 100 | 101432230262532 |  | 0 | 172.67 | 89.29 | 0 | 83.38 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 20026918201 |  |  |  | 6748208E | 2177770 | GSULLI1 |  | 909 | EX | INSTALL ELECTRONICS | 2600E | EARLY | EARLY DR | 049 | WIN | 2022-11-02 | U123258 | GSULLI1 | 2020-02-03 | 2021-12-30 | 2021-12-31 | 2022-09-27 | JPASLEY | 2022-09-27 | 2021-03-25 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00909 | 3200909 |  |  | WP9182 |  |  | 100 | 090932200269182 | 283.1333 | 0 | 199238.05 | 17259.88 | 2021.15 | 7694.54 | 163040.51 | 0 | 9221.97 | 0
KY | KY - CENTRAL | 2629 | 21026104700 |  |  |  | 6748208E | 2177770 | GSULLI1 |  | 910 | EX | REMOVE OBSOLETE ELECTRONICS | 2600E | EARLY | EARLY DR | 049 | WIN | 2022-11-02 | U123258 | GSULLI1 | 2021-02-22 | 2021-12-30 | 2021-12-31 | 2022-09-27 | JPASLEY | 2022-09-27 |  |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00910 | 3200910 |  |  | WP1047 |  |  | 100 | 091032210261047 | 1.8167 | 0 | 236.27 | 133.37 | 0 | 102.9 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883051500 |  | 100242329 |  | 7356252D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WADKINS | 321 WADKINS ST | 019 | CAT | 2022-09-27 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883067900 |  | 100245587 |  | 7360252I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BROADWAY | 2421 BROADWAY ST A1 | 019 | CAT | 2022-09-27 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883068000 |  | 100245608 |  | 7360252I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BROADWAY | 2421 BROADWAY ST A2 | 019 | CAT | 2022-09-27 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 350 | 0 | 0 | 0 | 350 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883128300 |  | 100242209 |  | 7356252D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 10TH | 511 10TH ST | 019 | CAT | 2022-09-27 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 2028 | 0 | 0 | 0 | 2028 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883163800 |  | 100245895 |  | 7360252I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SYCAMORE | 2412 SYCAMORE ST | 019 | CAT | 2022-09-27 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883168600 |  | 100245631 |  | 7360252I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BROADWAY | 2115 BROADWAY ST | 019 | CAT | 2022-09-27 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883227100 |  | 100242287 |  | 7356252D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WADKINS | 330 WADKINS ST | 019 | CAT | 2022-09-27 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883242200 |  | 100291098 |  | 6720212A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BROADWAY | 724 N BROADWAY ST | 067 | LEX | 2022-09-27 | U930915 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | RSTRONG | 2022-09-27 | 2022-09-02 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.3667 | 2 | 1591.92 | 291.33 | 0 | 22.97 | 1277.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21884272900 |  | 100291106 |  | 6720212A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BROADWAY | 734 N BROADWAY ST 2 | 067 | LEX | 2022-10-24 | U930915 | U128293 | 2021-02-04 | 2022-07-01 | 2022-12-31 |  | RSTRONG | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.9667 | 1 | 1507.96 | 199.1 | 14.45 | 16.79 | 1277.62 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916444100 |  | 100263573 |  | 7352256C | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | PRICHARD | 340 PRICHARD ST | 019 | ASH | 2022-09-27 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-27 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2936.21 | 0 | 0 | 0 | 2936.21 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959033800 |  | 100315290 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | CRESCENT | 1041 CRESCENT AV | 067 | LEX | 2022-09-27 | U461322 | U134723 | 2021-12-10 | 2022-12-30 |  |  | STEVE CANOY | 2022-09-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.3 | 2 | 4347.65 | 666.53 | 0 | 635.24 | 3045.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959038800 |  | 100315342 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | UNIVERSITY | 207 UNIVERSITY AV | 067 | LEX | 2022-09-27 | U461423 | U134723 | 2021-12-10 | 2022-12-30 |  |  | KKOUNS | 2022-09-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 1666.12 | 478.57 | 0 | 450.85 | 736.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960889500 |  | 100249909 |  | 7356248H | 2180320 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | MAYO TRAIL | 10408 MAYO TRAIL RD | 019 | CAT | 2022-09-27 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 | 3.7167 | 1 | 2499.78 | 195.07 | 0 | 46.41 | 2258.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026174600 |  |  |  | 6712204A | 2286833 | U126783 |  | 909 | EX | 2022 SCADA VISIBILITY PROGRAM | 2600E | HARRODSBURG | 4290 HARRODSBURG RD | 067 | LEX | 2022-10-18 | U127644 | U126783 | 2022-03-07 | 2022-10-25 | 2022-11-30 | 2022-09-27 | CCOX | 2022-09-27 | 2022-05-11 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3201029 |  |  | WP1746 | SCADA |  | 100 | 102932220261746 | 22.4 | 0 | 38527.05 | 1665.92 | 0 | 154.78 | 36652.26 | 0 | 54.09 | 0
KY | KY - WEST | 2621 | 22026182000 |  | 501329800 |  | 6716216N | 2288219 | U134275 |  | 555 | EX | INSTALL 2185' OF 2" PMMP | 2600B | TURNER COMMONS | 112 TURNER COMMONS WY | 067 | LEX | 2022-11-11 | U130992 | U134275 | 2022-04-14 | 2022-09-12 | 2022-09-30 | 2022-09-27 | WGRAVES | 2022-09-27 | 2022-09-12 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP1820 |  |  | 100 | 055532220261820 | 154.4833 | 38000 | 141899.3 | 9360.43 | 5057.35 | 6811.01 | 100227.29 | 0 | 185.99 | 20257.23 | 2000
KY | KY - WEST | 2621 | 22026204000 |  |  |  | 16712204A | 2286833 | U461383 |  | 584 | EX | RETIRE PAPER GAUGE | 2621M | HARRODSBURG | 4290 HARRODSBURG RD | 067 | LEX | 2022-10-13 | U127644 | U461383 | 2022-06-10 | 2023-09-29 | 2023-10-01 | 2022-09-27 | CCOX | 2022-09-27 |  |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00584 | 3200584 |  |  | WP2040 |  |  | 100 | 058432220262040 | 1.5 | 0 | 157.99 | 96.17 | 0 | 61.82 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026231900 |  |  |  | 6712204A | 2286833 | U461383 |  | 584 | VO | RETIRE PAPER GAUGE | 2621M | HARRODSBURG | 4290 HARRODSBURG RD | 067 | LEX | 2022-12-14 |  | U461383 | 2022-10-17 | 2023-12-01 | 2023-12-01 | 2022-09-27 | CCOX | 2022-09-27 |  |  | F | [11 empty] | 22026204000 | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026233400 |  |  |  | 6712236G | 2070683 | U124399 |  | 559 | VO | PM- GREENSITE HWY 27 INSTALL | 5320E |  |  | 209 | GEO | 2023-03-15 |  | U124399 | 2022-10-24 | 2022-12-30 | 2022-12-31 | 2022-09-27 | SWBISHOP | 2022-09-27 |  |  | C | [11 empty] | 23026253700 | 100 |  |  | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026233500 |  |  |  | 6712236G | 2070683 | U124399 |  | 560 | VO | PM- GREENSITE HWY 27 ABANDON | 5320E |  |  | 209 | GEO | 2023-03-15 |  | U124399 | 2022-10-24 | 2022-12-29 | 2022-12-31 | 2022-09-27 | SWBISHOP | 2022-09-27 |  |  | C | [11 empty] | 23026253800 | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026234100 |  |  |  | 6748208E | 2177770 | U461383 |  | 577 | EX | NEW RTU/COMM BUILDING | 2629M | EARLY | EARLY DR | 049 | WIN | 2022-11-02 | U123258 | U461383 | 2022-11-02 | 2022-12-30 | 2022-12-31 | 2022-09-27 | JPASLEY | 2022-09-27 |  |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00577 | 3200577 |  |  | WP2341 |  |  | 100 | 057732220262341 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22127351600 |  | 100240593 |  | 7328284D |  |  |  | 566 | EX | ABANDON SL - DEMO/FIRE | 2621P | CHRISTOPHER | 37 CHRISTOPHER DR | 089 | S S | 2022-09-27 | JCYRUS | U125208 | 2022-08-29 | 2022-09-26 | 2022-09-26 |  | JCYRUS | 2022-09-27 | 2022-09-13 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 18.1167 | 4 | 1254.31 | 1149.92 | 28.63 | 75.76 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129008900 |  | 100241669 |  | 7356256P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BOYD | 4631 BOYD ST | 019 | ASH | 2022-09-29 | U123965 | U130722 | 2022-09-05 | 2022-12-30 |  |  | MBLANKE | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.4667 | 1 | 2012.74 | 285.01 | 0 | 67.83 | 1659.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129009500 |  | 100259119 |  | 7356256A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PROSPECT | 914 PROSPECT AV | 019 | ASH | 2023-01-20 | U125566 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DAVID SKAGGS | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 2464.7 | 0 | 0 | 0 | 2464.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129016500 |  | 100338765 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LOUDON | 222 E LOUDON AV | 067 | LEX | 2022-09-27 | U129731 | U130722 | 2022-09-05 | 2022-09-27 |  |  | F.GOINS | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.1333 | 1 | 2322.38 | 450.02 | 0 | 93.19 | 1779.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129016600 |  | 100338984 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LOUDON | 257 E LOUDON AV | 067 | LEX | 2022-10-06 | U129731 | U130722 | 2022-09-05 | 2022-12-30 |  |  | F.GOINS | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1779.17 | 0 | 0 | 0 | 1779.17 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129020200 |  | 100277554 |  | 6688228E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | VALLEY VIEW | 104 VALLEY VIEW DR | 073 | FRA | 2022-10-20 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129020300 |  | 100277555 |  | 6688228E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | VALLEY VIEW | 106 VALLEY VIEW DR | 073 | FRA | 2022-10-20 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129020400 |  | 100277558 |  | 6688228E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | VALLEY VIEW | 112 VALLEY VIEW DR | 073 | FRA | 2022-10-20 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129044400 |  | 100335346 |  | 6720212L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HELM | 110 HELM ST | 067 | LEX | 2022-10-20 | U126602 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DEREK PAYTON | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2574.04 | 0 | 0 | 0 | 2574.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129046600 |  | 100294192 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ELSMERE | 674 ELSMERE PA 1FR | 067 | LEX | 2022-10-03 | U126602 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DEREK PAYTON | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 2880.62 | 592.94 | 0 | 33.08 | 2254.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129047300 |  | 100336678 |  | 6720212I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HAWKINS | 460 HAWKINS AV | 067 | LEX | 2022-09-27 | U127206 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 4671.85 | 602.79 | 0 | 33.63 | 4035.43 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129090300 |  | 100277659 |  | 6688228E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SCHENKEL | 112 SCHENKEL LN | 073 | FRA | 2022-10-21 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 2552.35 | 0 | 0 | 0 | 2552.35 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129090500 |  | 100274169 |  | 6684228N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SHELBY | 616 SHELBY ST | 073 | FRA | 2022-10-20 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129090700 |  | 100276887 |  | 6684228D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SWIGERT | 201 SWIGERT AV | 073 | FRA | 2022-10-20 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129090800 |  | 100276888 |  | 6684228D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SWIGERT | 203 SWIGERT AV | 073 | FRA | 2022-10-20 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22132003300 |  | 100443361 |  | 6712220M | 1635077 |  |  | 565 | EX | AOC SERVICE LINE REPLACE | 2621P | LEESTOWN | 3785 LEESTOWN RD | 067 | LEX | 2022-09-28 | U131790 | U125208 | 2022-09-19 | 2022-09-23 | 2022-10-24 |  | ABLAKE | 2022-09-27 | 2022-09-26 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 29.3333 | 6 | 2123.28 | 1798.17 | 116.6 | 117.21 | 91.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22133661200 |  | 100316002 |  | 6716208F |  |  |  | 565 | EX | SERVICE LINE - RELOCATE | 2621P | SUBURBAN | 173 SUBURBAN CT | 067 | LEX | 2022-09-27 | U930915 | U125208 | 2022-09-22 | 2022-09-27 | 2022-10-13 |  | TROE | 2022-09-27 | 2022-09-26 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 35.9833 | 6 | 3508.16 | 2616.07 | 685.82 | 161.17 | 45.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22134095100 |  | 100273985 |  | 6684224A |  |  |  | 565 | EX | REPLACE SERVICE LINE - D222061 | 2621P | CAVERN | 113 CAVERN DR | 073 | FRA | 2022-09-27 | DCOLLIN | U125208 | 2022-09-23 | 2022-09-26 | 2022-10-14 |  | DCOLLIN | 2022-09-27 | 2022-09-26 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8.4667 | 2 | 2401.35 | 569.51 | 383.75 | 63.79 | 1384.3 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22134913500 |  | 100245588 |  | 7360252I |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | BROADWAY | 2421 BROADWAY ST APT4 | 019 | CAT | 2022-09-27 | U135195 | U125763 | 2022-09-27 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 350 | 0 | 0 | 0 | 350 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22134913800 |  | 100245607 |  | 7360252I |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | BROADWAY | 2421 BROADWAY ST 3 | 019 | CAT | 2022-09-27 | U135195 | U125763 | 2022-09-27 | 2022-12-30 |  |  | KEITH HEDGES | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22134950000 |  | 100430865 |  | 6684228N |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | SHELBY | 618 SHELBY ST | 073 | FRA | 2022-10-20 | U125881 | U125763 | 2022-09-27 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 390.22 | 0 | 0 | 0 | 390.22 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22134978300 |  | 100351196 |  | 6744208O |  |  |  | 565 | EX | GRADE 1 REPLACE SERVICE | 2621P | CHURCHILL | 5 CHURCHILL DR | 049 | WIN | 2022-09-28 | U930915 | U129939 | 2022-09-27 | 2022-09-27 | 2022-09-27 |  | NRICHIE | 2022-09-27 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 17.85 | 3 | 1926.1 | 1226.2 | 257.68 | 383.92 | 58.3 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979016700 |  | 100242364 |  | 7356216G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 13TH | 309 13TH ST | 019 | CAT | 2022-09-27 | U135195 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | KEITH HEDGES | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1772.5 | 0 | 0 | 0 | 1772.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22979029500 |  | 100277150 |  | 6684228H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HOLMES | 745 HOLMES ST | 073 | FRA | 2022-10-02 | U128762 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | CORY TINCHER | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 3006.29 | 0 | 0 | 0 | 3006.29 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983422700 |  | 100402693 |  | 6720204B | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 3379 GREENTREE RD | 067 | LEX | 2022-09-27 | U126530 | U134723 | 2022-03-03 | 2022-12-30 |  |  | JDUNN | 2022-09-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3128.03 | 0 | 0 | 0 | 3128.03 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026253700 |  |  |  | 6736240M | 2070683 | U124399 |  | 559 | CO | PM-GREENSITE HWY 27 INSTALL | 5320E |  |  | 017 | PAR | 2023-01-25 |  | U124399 | 2023-01-25 | 2022-12-30 | 2022-12-31 | 2022-09-27 | SWBISHOP | 2022-09-27 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00559 | 3201013 |  |  | WP2537 | KSMRP |  | 100 | 101332230262537 |  | 55 | 20730.94 | 336.18 | 0 | 313.97 | 16687.78 | 0 | 0 | 3393.01 | 55
KY | KY - CENTRAL | 2629 | 23026253800 |  |  |  | 6736240M | 2070683 | U124399 |  | 560 | CO | PM-GREENSITE HWY 27 ABANDON | 5320E |  |  | 017 | PAR | 2023-01-25 |  | U124399 | 2023-01-25 | 2022-12-29 | 2022-12-31 | 2022-09-27 | SWBISHOP | 2022-09-27 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00560 | 3201014 |  |  | WP2538 | KSMRP |  | 100 | 101432230262538 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 05618091700 |  | 100315279 |  | 6716208C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | STATE | 205 STATE ST 2FL | 067 | LEX | 2022-09-28 | U129673 | SSUTHER | 2005-07-26 | 2014-12-01 |  |  | ALEX WILLIAMSON | 2022-09-28 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 10874251600 |  | 100296879 | 57 | ? |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | GEORGETOWN | 507 GEORGETOWN ST | 067 | LEX | 2022-09-28 | MCRAIG | RSTOKLE | 2010-12-29 | 2022-07-01 | 2022-12-31 |  | MCRAIG | 2022-09-28 | 2022-09-23 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 17.3667 | 9 | 1930.52 | 985.48 | 133.12 | 64.92 | 747 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11931950600 |  | 100434289 |  | 16716212O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | VIRGINIA | 323 W VIRGINIA AV B | 067 | LEX | 2022-09-28 | U126602 | U125208 | 2011-11-07 | 2020-12-31 |  |  | DEREK PAYTON | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 12981450200 |  | 500011522 |  | 16716212D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | GEORGETOWN | 661 GEORGETOWN ST | 067 | LEX | 2022-09-28 | MCRAIG | U125208 | 2012-07-24 | 2022-07-01 | 2022-12-31 |  | MCRAIG | 2022-09-28 | 2022-09-23 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.6167 | 6 | 687.33 | 514.41 | 133.12 | 39.8 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 14220326700 |  | 500137459 | 15 | 6736228L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CLINTONVILLE | 454 CLINTONVILLE RD | 017 | PAR | 2022-10-20 | U125881 | SRICHIE | 2014-05-15 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 5787.59 | 0 | 0 | 0 | 5787.59 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 16426428000 |  | 100340819 |  | NEW |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | PEARSON | 165 PEARSON LN | 151 | RIC | 2022-09-28 | U126604 | U122906 | 2016-07-13 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2704.42 | 0 | 0 | 0 | 2704.42 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21026999000 |  | 100403787 |  | 6768172B | 2290900 | U461383 |  | 566 | EX | RETIRE 4"PLP SERVICE LINE | 2600B | 4TH | 405 4TH ST | 065 | RAV | 2022-10-04 | U128132 | U120245 | 2021-01-30 | 2022-12-01 | 2022-12-01 | 2022-09-28 | WILL FULKS | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP9990 |  |  | 100 | 056632210269990 | 14.5 | 2 | 4696.25 | 927.73 | 112.96 | 189.87 | 3465.69 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883055300 |  | 100245545 |  | 7360252I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CENTER | 2521 CENTER ST | 019 | CAT | 2022-09-28 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883070900 |  | 100245804 |  | 7360252I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LOUISA | 2606 LOUISA ST | 019 | CAT | 2022-09-28 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883099500 |  | 100360768 |  | 6736228G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEXINGTON | 4002 LEXINGTON RD | 017 | PAR | 2022-10-20 | U125881 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883134100 |  | 100249807 |  | 7356248H | 2180320 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | PADDLE CREEK | 8415 PADDLE CREEK RD | 019 | CAT | 2022-09-28 | U123965 | U120245 | 2021-01-30 | 2022-09-28 |  |  | MBLANKE | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 | 2.2333 | 1 | 1401.23 | 116.1 | 0 | 27.63 | 1257.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883178800 |  | 100242294 |  | 7356252H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MITCHELL | 1128 MITCHELL ST | 019 | CAT | 2022-09-28 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883196300 |  | 100245303 |  | 7360252M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | OAKLAND | 3241 OAKLAND AV | 019 | CAT | 2022-09-28 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883202400 |  | 100249982 |  | 7360248A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 34TH | 314 34TH ST | 019 | CAT | 2022-09-28 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883206900 |  | 100249810 |  | 7356248H | 2180320 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | PADDLE CREEK | 8411 PADDLE CREEK RD | 019 | CAT | 2022-09-28 | U123965 | U120245 | 2021-01-30 | 2022-09-28 |  |  | MBLANKE | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 | 0.11667 | 1 | 1466.47 | 6.27 | 0 | 1.5 | 1458.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883230000 |  | 100242299 |  | 7356252H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MITCHELL | 1140 MITCHELL ST | 019 | CAT | 2022-09-28 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 2150 | 0 | 0 | 0 | 2150 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883257800 |  | 100249855 |  | 7356248H | 2180320 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | PADDLE CREEK | 8326 PADDLE CREEK RD | 019 | CAT | 2022-09-29 | U123965 | U120245 | 2021-01-30 | 2022-09-28 |  |  | MBLANKE | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 | 3.3167 | 1 | 1474.37 | 175.18 | 0 | 41.69 | 1257.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883260300 |  | 100334866 |  | 6720212P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NEW CIRCLE | 1081 E NEW CIRCLE RD 39 | 067 | LEX | 2022-09-28 | U126602 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DEREK PAYTON | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - CENTRAL | 2629 | 21883262500 |  | 100360857 |  | 6736228J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEXINGTON | 4197 LEXINGTON RD | 017 | PAR | 2022-10-20 | U125881 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2076.31 | 0 | 0 | 0 | 2076.31 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883279100 |  | 100245592 |  | 7360252I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 25TH | 207 25TH ST | 019 | CAT | 2022-09-28 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883314400 |  | 100296693 |  | 6716212D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | GEORGETOWN | 651 GEORGETOWN ST | 067 | LEX | 2022-09-28 | MCRAIG | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | MCRAIG | 2022-09-28 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.8167 | 5 | 1124.87 | 925.33 | 133.12 | 66.42 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883329100 |  | 500323088 |  | 6716212E | 9402880 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CAHILL | 1365 CAHILL DR B-1FL | 067 | LEX | 2022-09-28 | U126602 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DEREK PAYTON | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - EAST | 2631 | 21884180500 |  | 100422653 |  | 7360252M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LOUISA | 2709< LOUISA ST | 019 | CAT | 2022-09-28 | U135195 | U128293 | 2021-02-04 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21884244000 |  | 100293903 |  | 6720212A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BROADWAY | 873 N BROADWAY ST | 067 | LEX | 2022-09-30 | U930915 | U128293 | 2021-02-04 | 2022-07-01 | 2022-12-31 |  | RSTRONG | 2022-09-28 | 2022-09-01 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.4333 | 2 | 2734.83 | 496.43 | 0 | 41.83 | 2196.57 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916429400 |  | 100264023 |  | 7352260N | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | FAIRVIEW | 617 FAIRVIEW AV | 019 | ASH | 2022-09-28 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-09-28 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2795.6 | 0 | 0 | 0 | 2795.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959036800 |  | 100315302 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | STATE | 216 STATE ST | 067 | LEX | 2022-09-28 | U461423 | U134723 | 2021-12-10 | 2022-12-30 |  |  | KKOUNS | 2022-09-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2845.16 | 478.57 | 0 | 450.85 | 1915.74 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960890000 |  | 100249857 |  | 7356248H | 2180320 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | PADDLE CREEK | 8410 PADDLE CREEK RD | 019 | CAT | 2022-09-28 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 | 4.3333 | 1 | 1738.36 | 225.9 | 0 | 53.76 | 1458.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026173600 |  |  |  | 6716212F | 2286833 | U132703 |  | 909 | EX | 2022 SCADA VISIBILITY PROGRAM | 2600E | OLD FRANKFORT | 1313 OLD FRANKFORT PK | 067 | LEX | 2022-10-25 | U123258 | U132703 | 2022-03-04 | 2022-10-31 | 2022-11-30 | 2022-09-28 | EBLANTON | 2022-09-28 | 2022-09-28 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP1736 | SCADA |  | 100 | 090932220261736 | 7.8167 | 0 | 25271.05 | 537.76 | 0 | 30.01 | 24653.44 | 0 | 49.84 | 0
KY | KY - CENTRAL | 2629 | 22026177500 |  |  |  | 6764176O | 2286885 | U128885 |  | 557 | EX | EMER - INSTALL 800'-6" CSHP | 2600B | KY RIVER | KY RIVER | 065 | IRV | 2022-10-04 | U128132 | U128885 | 2022-03-21 | 2023-06-05 | 2024-02-23 | 2022-09-20 | WILL FULKS | 2022-09-28 | 2022-08-18 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP1775 | AMRCB |  | 100 | 055732220261775 | 510.0833 | 48601 | 1030814.44 | 44749.72 | 132057.98 | 39484.85 | 662212.21 | 0 | 1002.84 | 151306.84 | 917
KY | KY - CENTRAL | 2629 | 22026177600 |  |  |  | 6764176O | 2286885 | U128885 |  | 558 | EX | EMER-RETIRE 800'-4" CSHP | 2600B | KY RIVER | KY RIVER | 065 | IRV | 2022-10-03 | U128132 | U128885 | 2022-03-21 | 2023-06-30 | 2024-02-23 | 2022-09-20 | WILL FULKS | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP1776 | AMRCB |  | 100 | 055832220261776 |  | 0 | 1361.76 | 1172.51 | 0 | 189.25 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026227600 |  |  |  | 6744204D | 2292274 | U128885 |  | 557 | EX | EMER - INSTALL 60'-4" PMLP | 2600B | MAPLE | 504 S MAPLE ST | 049 | WIN | 2022-10-10 | U128132 | U128885 | 2022-09-28 | 2022-09-27 | 2024-09-07 | 2022-09-28 | ED FOX | 2022-09-28 | 2022-09-29 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP2276 | AMRCB |  | 100 | 055732220262276 | 15.3 | 165 | 21421.89 | 930.81 | 0 | 192.82 | 17356.23 | 0 | 15.54 | 2926.49 | 55
KY | KY - CENTRAL | 2629 | 22026227700 |  |  |  | 6744204D | 2292274 | U128885 |  | 558 | EX | EMER - RETIRE 60'-4" BSLP | 2600B | MAPLE | 504 S MAPLE ST | 049 | WIN | 2022-10-10 | U128132 | U128885 | 2022-09-28 | 2022-09-30 | 2024-09-07 | 2022-09-28 | ED FOX | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP2277 | AMRCB |  | 100 | 055832220262277 |  | 0 | 8123.84 | 3690.84 | 0 | 1177.83 | 3255.17 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129010500 |  | 100414551 |  | 7352256A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | TANNER | 2621 TANNER DR | 019 | ASH | 2023-01-20 | U125566 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DAVID SKAGGS | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1257.5 | 0 | 0 | 0 | 1257.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129016800 |  | 500613219 |  | 6720212D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MCKENNA | 408 MCKENNA CT | 067 | LEX | 2022-09-28 | U129731 | U130722 | 2022-09-05 | 2022-09-26 |  |  | F.GOINS | 2022-09-28 | 2022-09-26 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.9167 | 2 | 4817.88 | 1000.78 | 0 | 207.24 | 3609.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129020500 |  | 100279407 |  | 6688228P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | VERSAILLES | 1350 VERSAILLES RD | 073 | FRA | 2022-10-02 | U128762 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CORY TINCHER | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 2044.84 | 0 | 0 | 0 | 2044.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129044200 |  | 100290197 |  | 6720212C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | EDGELAWN | 1424 EDGELAWN AV | 067 | LEX | 2022-09-29 | U127206 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-28 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1708.57 | 0 | 0 | 0 | 1708.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129045600 |  | 100335716 |  | 6720212H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NEW CIRCLE | 588 E NEW CIRCLE RD | 067 | LEX | 2022-10-04 | U127206 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 2685.25 | 602.79 | 0 | 33.63 | 2048.83 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129055100 |  | 100275746 |  | 6684228C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WILKINSON | 976 WILKINSON BV | 073 | FRA | 2022-10-02 | U128762 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CORY TINCHER | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 2018.78 | 0 | 0 | 0 | 2018.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129080000 |  | 100287663 |  | 6720212G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CARNEAL | 966 CARNEAL RD | 067 | LEX | 2022-09-29 | U127206 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1708.57 | 0 | 0 | 0 | 1708.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129080300 |  | 100335803 |  | 6720212L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | COMMERCIAL | 1145 COMMERCIAL DR | 067 | LEX | 2022-09-28 | U126602 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DEREK PAYTON | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2284.3 | 0 | 0 | 0 | 2284.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129080800 |  | 100287396 |  | 6720212C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | EMERSON | 442 EMERSON DR | 067 | LEX | 2022-09-28 | U127206 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1538.44 | 0 | 0 | 0 | 1538.44 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129130000 |  | 500230192 |  | 7352260N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | JOHNSON | 709 JOHNSON PL W | 019 | ASH | 2022-11-23 | U125566 | U125208 | 2022-09-06 | 2022-12-30 |  |  | DAVID SKAGGS | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1458.7 | 0 | 0 | 0 | 1458.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129130700 |  | 100338280 |  | 6720212J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | JACKSON | 654 JACKSON ST | 067 | LEX | 2022-11-02 | U126602 | U125208 | 2022-09-06 | 2022-12-30 |  |  | DEREK PAYTON | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.2833 | 2 | 3956.8 | 665.05 | 0 | 63.89 | 3227.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129131000 |  | 500285686 |  | 6684224M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | US 127 | 2247 US 127 SO | 073 | FRA | 2022-10-04 | U123119 | U125208 | 2022-09-06 | 2022-12-30 |  |  | CORY TINCHER | 2022-09-28 | 2022-09-27 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 20 | 3 | 3096.73 | 1190.12 | 0 | 161.66 | 1744.95 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22134639000 |  | 100350916 |  | 6744208O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D096869 | 2621P | LOCUST | 4 LOCUST DR | 049 | WIN | 2022-09-28 | NRICHIE | U125208 | 2022-09-26 | 2022-09-26 | 2022-09-26 |  | NRICHIE | 2022-09-28 | 2022-09-27 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 22.3 | 5 | 2311.41 | 1528.87 | 414.57 | 367.97 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22134907700 |  | 500338037 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | STATE | 205 STATE ST 1FL | 067 | LEX | 2022-09-28 | U129673 | U125768 | 2022-09-27 | 2049-12-31 |  |  | ALEX WILLIAMSON | 2022-09-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2437.43 | 513.76 | 0 | 71.53 | 1852.14 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22135265000 |  | 100274527 |  | 6684228J |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | 4TH | 411 W 4TH ST | 073 | FRA | 2022-09-30 | U125208 | U131169 | 2022-09-28 | 2022-09-28 |  |  | DCOLLIN | 2022-09-28 | 2022-09-28 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8.5333 | 1 | 4744.94 | 578.95 | 0 | 64.83 | 4101.16 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979018100 |  | 100245921 |  | 7360252I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SYCAMORE | 2414 SYCAMORE ST | 019 | CAT | 2022-09-28 | U135195 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | KEITH HEDGES | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1800 | 0 | 0 | 0 | 1800 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979018400 |  | 100246747 |  | 7352256L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MONROE | 2936 MONROE ST | 019 | ASH | 2022-11-16 | U125566 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | DAVID SKAGGS | 2022-09-28 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1458.7 | 0 | 0 | 0 | 1458.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22979044800 |  | 100416918 |  | 6712204C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MERRIMAC | 611 MERRIMAC DR | 067 | LEX | 2022-09-28 | LSTONE | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | LSTONE | 2022-09-28 | 2022-07-15 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 27.5833 | 6 | 1953.86 | 1798.31 | 55.21 | 100.34 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983422300 |  | 100324775 |  | 6720204B | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 1132 GREENTREE CT | 067 | LEX | 2022-09-28 | U126530 | U134723 | 2022-03-03 | 2022-12-30 |  |  | JDUNN | 2022-09-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2108.98 | 0 | 0 | 0 | 2108.98 | 0 | 0 | 0
KY | KY - WEST | 2621 | 00453921300 |  | 100314639 |  | 6716212L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAXWELL | 116 W MAXWELL ST 1F | 067 | LEX | 2022-09-29 | TROE | JTOY | 2000-12-06 | 2022-09-29 | 2022-12-31 |  | TROE | 2022-09-29 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.38333 | 1 | 31.93 | 30.24 | 0 | 1.69 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 06642220100 |  | 100290092 |  | 6720212B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LOCUST | 134 LOCUST AV | 067 | LEX | 2022-09-29 | U127206 | SSUTHER | 2006-03-22 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-09-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 3027.99 | 0 | 0 | 0 | 3027.99 | 0 | 0 | 0
KY | KY - EAST | 2631 | 06651199800 |  | 500550163 | 18 | 7344246A | 9720480 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | STATE RT 854 | 15804 STATE RT 854 | 019 | RUS | 2022-09-29 | U135195 | U801205 | 2006-06-19 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-29 | 2020-04-10 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.88333 | 1 | 1162.27 | 48.42 | 0 | 13.85 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 07682075700 |  | 500550195 | 13 | 7344246-A | 9720480 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SR1654 | 2745 SR1654 | 019 | RUS | 2022-09-29 | U135195 | JWHEATL | 2007-04-06 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-29 | 2020-04-10 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.3 | 1 | 1121.24 | 16.52 | 0 | 4.72 | 1100 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 08721927400 |  | 500133951 | 06 | 16736216H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CLINTONVILLE | 2697 CLINTONVILLE RD | 017 | PAR | 2022-09-29 | U126284 | PMCNABB | 2008-02-29 | 2022-07-01 | 2022-12-31 |  | JOSH PASLEY | 2022-09-29 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10 | 1 | 4386.66 | 631.78 | 0 | 565.44 | 3189.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12968005500 |  | 100314638 |  | 6716212L |  |  |  | 566 | EX | ABANDON SL - SOII/INSIDE | 2621P | MAXWELL | 116 W MAXWELL ST 2F | 067 | LEX | 2022-09-29 | TROE | U124967 | 2012-05-02 | 2014-12-23 |  |  | TROE | 2022-09-29 | 2022-09-15 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 28.5667 | 8 | 2842.12 | 1911.22 | 133.12 | 106.65 | 691.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12980739900 |  | 100314632 |  | 167162NAL |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAXWELL | 121 W MAXWELL ST | 067 | LEX | 2022-09-29 | HMCKUNE | U125208 | 2012-07-18 | 2022-07-01 | 2022-12-31 |  | HMCKUNE | 2022-09-29 | 2022-09-08 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 27.4 | 6 | 1580.27 | 1456.76 | 42.22 | 81.29 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 16445522800 |  | 100245324 | 18 | 7360248A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | OAKLAND | 3309 OAKLAND AV | 019 | CAT | 2022-09-29 | U135195 | JWHEATL | 2016-09-28 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-29 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18026766400 |  |  |  | 7240204B | 1852103 | U131369 |  | 909 | EX | I&C - INSTALL SCADA EQUIPMENT | 2600E | LEVEE | LEVEE RD | 173 | MT | 2022-11-21 | U125936 | U131369 | 2018-04-10 | 2018-12-07 | 2018-12-31 | 2022-09-29 | JMULLINS | 2022-09-29 | 2022-09-29 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00909 | 3200909 |  |  | WP7664 |  |  | 100 | 090932180267664 | 115.6 | 0 | 143824.82 | 10420.37 | 63016.76 | 2256.93 | 59241.98 | 0 | 8888.78 | 0
KY | KY - WEST | 2621 | 18622074100 |  | 100334131 | 29 | 6720212O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | EMERY | 595 EMERY CT | 067 | LEX | 2022-09-29 | U129731 | BLINDSA | 2018-06-21 | 2022-09-29 |  |  | F.GOINS | 2022-09-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 2844.57 | 629.41 | 0 | 130.35 | 2084.81 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 20026980401 |  |  |  | 6748208I | 2075093 | U128885 |  | 557 | EX | INSTALL 13,025'-PMMP/CSHP | 2600B | MT STERLING | MT STERLING PK | 049 | WIN | 2022-10-19 | U132783 | U128885 | 2022-09-23 | 2022-02-25 | 2022-12-31 | 2022-09-06 | SHAWN DENNIS | 2022-09-29 | 2022-09-27 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP9804 | AMRCB |  | 100 | 055732200269804 | 1754.6667 | 1288602 | 2258910.28 | 115957.78 | 81548.14 | 30559.43 | 1678725.45 | 0 | 12957.86 | 339161.62 | 6818
KY | KY - CENTRAL | 2629 | 20026980500 |  |  |  | 6748208I | 2075093 | U128885 |  | 558 | EX | RETIRE 12,520' - LP MAIN | 2600B | MT STERLING | MT STERLING PK | 049 | WIN | 2022-10-13 | U132783 | U128885 | 2020-10-09 | 2022-12-30 | 2022-12-31 | 2022-09-20 | SHAWN DENNIS | 2022-09-29 | 2022-05-05 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP9805 | AMRCB |  | 100 | 055832200269805 | 11.5 | 0 | 809.88 | 743.61 | 0 | 66.27 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 20026980601 |  |  |  | 6740232M | 2075121 | U128885 |  | 557 | EX | INSTALL 16,200'-2"/4" PMMP | 2600B | HIGGINS | HIGGINS ST | 017 | PAR | 2022-11-22 | U128132 | U128885 | 2022-09-22 | 2020-05-11 | 2023-06-10 | 2021-10-12 | LYN STAFFORD | 2022-09-29 | 2022-09-26 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP9806 | AMRCB |  | 100 | 055732200269806 | 2098.5833 | 5209286 | 4720247.08 | 308762.2 | 34325.7 | 65553.65 | 3647763.3 | 0 | 27610.67 | 636231.56 | 20509
KY | KY - CENTRAL | 2629 | 20026980700 |  |  |  | 6740232M | 2075121 | U128885 |  | 558 | EX | RETIRE MAIN - LEAKAGE | 2600B | HIGGINS | HIGGINS ST | 017 | PAR | 2022-11-14 | U128132 | U128885 | 2020-10-12 | 2022-10-31 | 2023-06-10 | 2022-09-14 | LYN STAFFORD | 2022-09-29 | 2021-07-14 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP9807 | AMRCB |  | 100 | 055832200269807 | 2.5667 | 0 | 2546.03 | 2055.92 | 0 | 330.11 | 160 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883054200 |  | 100250089 |  | 7360252M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SPRINGHAVEN | 3307 SPRINGHAVEN ST | 019 | CAT | 2022-09-29 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-09-29 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1209.27 | 0 | 0 | 0 | 1209.27 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883054600 |  | 100250088 |  | 7360252M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SPRINGHAVEN | 3309 SPRINGHAVEN ST | 019 | CAT | 2022-09-29 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-09-29 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883101400 |  | 501087941 |  | 7344264A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | STATE RT 854 | 15705 STATE RT 854 | 019 | RUS | 2022-09-29 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-29 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883104300 |  | 100245384 |  | 7360248A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | VALLEY | 3726 VALLEY ST | 019 | CAT | 2022-09-29 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-29 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883120000 |  | 500214796 |  | 7356248H | 2180320 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | MAYO TRAIL | 10331 S MAYO TRAIL RD | 019 | CAT | 2022-09-29 | U123965 | U120245 | 2021-01-30 | 2023-06-30 |  |  | MBLANKE | 2022-09-29 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 | 4.9167 | 1 | 1979.1 | 257.83 | 0 | 61.37 | 1659.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883142100 |  | 100245385 |  | 7360248A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | VALLEY | 3724 VALLEY ST | 019 | CAT | 2022-09-29 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-29 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883177600 |  | 100250189 |  | 7356248O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | RADIO PARK | 10537 RADIO PARK RD | 019 | CAT | 2022-09-29 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-09-29 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883252600 |  | 100249904 |  | 7356248H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NEAL | 7936 NEAL RD | 019 | CAT | 2022-09-29 | U135195 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | KEITH HEDGES | 2022-09-29 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959038900 |  | 100315371 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | UNIVERSITY | 208 UNIVERSITY AV | 067 | LEX | 2022-09-29 | U461322 | U134723 | 2021-12-10 | 2022-12-30 |  |  | STEVE CANOY | 2022-09-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.9833 | 1 | 3041.43 | 589.72 | 0 | 562.03 | 1889.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959047200 |  | 100315310 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | STATE | 202 STATE ST | 067 | LEX | 2022-09-29 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-09-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7 | 1 | 2617.26 | 449.54 | 0 | 91.75 | 2075.97 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959047300 |  | 100315376 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | UNIVERSITY | 204 UNIVERSITY AV | 067 | LEX | 2022-09-30 | U461423 | U134723 | 2021-12-10 | 2022-12-30 |  |  | KKOUNS | 2022-09-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2871.14 | 478.57 | 0 | 450.85 | 1941.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960236900 |  | 100321127 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | MAXWELL | 320 E MAXWELL ST 1F | 067 | LEX | 2022-09-29 | U126309 | U134723 | 2021-12-17 | 2022-12-30 |  |  | JAMIE LYNN | 2022-09-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 5241.73 | 0 | 0 | 0 | 5241.73 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960889600 |  | 100451659 |  | 7360248E | 2180320 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | MAYO TRAIL | MAYO TRAIL RD | 019 | CAT | 2022-09-29 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE | 2022-09-29 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 | 4.6667 | 1 | 1960.97 | 243.19 | 0 | 57.88 | 1659.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026173800 |  |  |  | 6720212H | 2286833 | U134275 |  | 909 | EX | 2022 SCADA VISIBILITY PROGRAM | 2600E | CONTINENTAL | 1521 CONTINENTAL SQ | 067 | LEX | 2022-10-31 | U123258 | U134275 | 2022-03-04 | 2022-10-25 | 2022-11-30 | 2022-09-29 | RHAYES | 2022-09-29 | 2022-05-10 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3201029 |  |  | WP1738 | SCADA |  | 100 | 102932220261738 | 10.5167 | 0 | 24972.3 | 672.71 | 0 | 37.88 | 24213.44 | 0 | 48.27 | 0
KY | KY - CENTRAL | 2629 | 22026228700 |  |  |  | 7240204B | 1852103 | U461383 |  | 910 | EX | RETIRE ELECTRONIC | 2600E | LEVEE | LEVEE RD | 173 | MT | 2022-11-21 | U125936 | U461383 | 2022-10-03 | 2022-12-01 | 2022-12-01 | 2022-09-29 | JMULLINS | 2022-09-29 |  |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00910 | 3200910 |  |  | WP2287 |  |  | 100 | 091032220262287 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026234500 |  |  |  | 7240204B | 1852103 | U461383 |  | 577 | EX | INSTALL NEW RTU/COMM BUILDING | 2629M | LEVEE | LEVEE RD | 173 | MT | 2022-11-21 | U125936 | U461383 | 2022-11-04 | 2022-12-15 | 2022-12-15 | 2022-09-29 | JMULLINS | 2022-09-29 |  |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00577 | 3200577 |  |  | WP2345 |  |  | 100 | 057732220262345 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129016100 |  | 500814252 |  | 6716208D | 0354950 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PROVIDENCE | 740 PROVIDENCE RD CABLE | 067 | LEX | 2022-10-25 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129045100 |  | 100290137 |  | 6720212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LOCUST | 117 LOCUST AV | 067 | LEX | 2022-10-04 | U127206 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-29 | 2022-09-29 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.1667 | 1 | 2130.68 | 77.51 | 0 | 4.34 | 2048.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129045500 |  | 100287456 |  | 6720212G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MEADOW | 945 MEADOW LN | 067 | LEX | 2023-01-20 | U126602 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DEREK PAYTON | 2022-09-29 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 2844.98 | 592.94 | 0 | 33.08 | 2218.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129046900 |  | 100296708 |  | 6716212C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GLEN ARVIN | 407 GLEN ARVIN AV | 067 | LEX | 2022-10-20 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1779.17 | 0 | 0 | 0 | 1779.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129080400 |  | 100287483 |  | 6720212G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DARLEY | 928 DARLEY DR | 067 | LEX | 2023-01-20 | U126602 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DEREK PAYTON | 2022-09-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2218.96 | 0 | 0 | 0 | 2218.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129080600 |  | 100290225 |  | 6720212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | EDGELAWN | 1411 EDGELAWN AV | 067 | LEX | 2022-10-04 | U127206 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-09-29 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 2685.25 | 602.79 | 0 | 33.63 | 2048.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129130200 |  | 100338370 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SHELBY | 524 SHELBY ST | 067 | LEX | 2022-09-29 | U129731 | U125208 | 2022-09-06 | 2022-12-30 |  |  | F.GOINS | 2022-09-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22131843200 |  | 100324233 |  | 6720204E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER | 2621D | OLYMPIA | 3608 OLYMPIA CR | 067 | LEX | 2022-09-30 | U930915 | AOC SYST | 2022-09-16 | 2022-10-14 | 2022-11-15 |  | LSTANFI | 2022-09-29 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.2 | 3 | 2258.56 | 1519.62 | 364.84 | 374.1 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22132017200 |  | 500616426 |  | 7348244L | 0146027 |  |  | 565 | EX | NBT - SERVICE LINE UPG - 1"PMP | 2621P | CRESTVIEW | 2700 CRESTVIEW DR | 019 | CAT | 2022-09-29 | MCOLLET | U125208 | 2022-09-19 | 2022-09-16 | 2022-10-14 |  | MCOLLET | 2022-09-29 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 25.3167 | 2 | 3952.34 | 1833.75 | 472.9 | 1543.39 | 102.3 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22135012100 |  | 100260407 |  | 7352256H |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | KENTUCKY | 1518 KENTUCKY AV | 019 | ASH | 2022-09-29 | JCYRUS | U129939 | 2022-09-27 | 2022-09-27 |  |  | JCYRUS | 2022-09-29 | 2022-09-29 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 11.6167 | 2 | 1467.54 | 1028.52 | 294.46 | 75.26 | 69.3 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22135375500 |  | 500613438 |  | 6688228D | 9829117 |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HMB | 2 HMB CR A | 073 | FRA | 2022-09-30 | UIPBOT10 | U136097 | 2022-09-28 | 2022-09-28 | 2022-09-28 |  | DCOLLIN | 2022-09-29 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 9.5667 | 3 | 3894.04 | 676.65 | 347.78 | 52.81 | 2816.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22135698800 |  | 100347026 |  | 6696212K |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | WOODLAWN | 104 WOODLAWN DR | 239 | VER | 2022-10-20 | U125881 | U125763 | 2022-09-29 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-29 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979016500 |  | 100242144 |  | 7356252D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 10TH | 330 10TH ST | 019 | CAT | 2023-01-13 | U125566 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | DAVID SKAGGS | 2022-09-29 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1458.7 | 0 | 0 | 0 | 1458.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979016600 |  | 100242145 |  | 7356252D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 10TH | 328 10TH ST | 019 | CAT | 2022-11-23 | U125566 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | DAVID SKAGGS | 2022-09-29 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1760.5 | 0 | 0 | 0 | 1760.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22979053600 |  | 500530716 |  | 6696212O | 9616001 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HEDDINGTON | 405 HEDDINGTON CT | 239 | VER | 2022-10-20 | U125881 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | HERBERT HAYDEN | 2022-09-29 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983422200 |  | 100324774 |  | 6720204B | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 1128 GREENTREE CT | 067 | LEX | 2022-09-29 | U126530 | U134723 | 2022-03-03 | 2022-12-30 |  |  | JDUNN | 2022-09-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1670.74 | 0 | 0 | 0 | 1670.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 08727867800 |  | 500561521 |  | 6708204F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | FONDA | 122 FONDA LN | 113 | NIC | 2022-10-03 | U125208 | RPOLLY | 2008-04-17 | 2022-09-30 | 2022-12-31 |  | RSTRONG | 2022-09-30 | 2019-09-23 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.4 | 3 | 1842.16 | 441.29 | 15.82 | 37.01 | 1348.04 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11899958800 |  | 100360100 |  | 6740232M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAIN | 813 MAIN ST | 017 | PAR | 2022-10-21 | U125881 | U906631 | 2011-04-06 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-09-30 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2409 | 0 | 0 | 0 | 2409 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12961107800 |  | 100360550 |  | 6736228D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAIN | 1493 MAIN ST | 017 | PAR | 2022-10-20 | U125881 | U125208 | 2012-03-20 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-09-30 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 14234560600 |  | 100360562 |  | 6740228A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAIN | 1431 MAIN ST | 017 | PAR | 2022-10-20 | U125881 | U127104 | 2014-07-15 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-09-30 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 15314018500 |  | 100359814 | 13 | 6740232M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAIN | 1124 MAIN ST | 017 | PAR | 2022-10-20 | U125881 | PMCNABB | 2015-05-21 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-09-30 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19026875300 |  |  |  | 7344168D | 1960337 | U122858 |  | 587 | EX | INSTALL ODORIZER | 2600M | LAKE | 100 LAKE RD | 071 | PRE | 2023-01-12 | U462081 | U122858 | 2019-05-07 | 2023-12-29 | 2023-12-31 | 2022-09-30 | JMULLINS | 2022-09-30 |  |  | F | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00587 | 3200587 |  |  | WP8753 |  |  | 100 | 058732190268753 |  | 1 | 9263.2 | 0 | 6647.29 | 0 | 0 | 0 | 423.4 | 2192.51
KY | KY - EAST | 2633 | 19026875400 |  |  |  | 7348176B | 1960337 | U122858 |  | 587 | EX | INSTALL ODORIZER | 2600M | SR 3 JOHNS CREEK 1434 | SR 3 JOHNS CREEK 1434 | 115 | VAN | 2022-12-22 | U125936 | U122858 | 2019-05-07 | 2023-12-29 | 2023-12-31 | 2022-09-30 | JMULLINS | 2022-09-30 |  |  | F | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00587 | 3200587 |  |  | WP8754 |  |  | 100 | 058732190268754 |  | 1 | 1315.89 | 0 | 1122.28 | 0 | 0 | 0 | 27.62 | 165.99
KY | KY - WEST | 2621 | 21883174100 |  | 500235305 |  | 6708204M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | OLDE VILLAGE | 1 OLDE VILLAGE DR | 113 | NIC | 2022-10-03 | U125208 | U120245 | 2021-01-30 | 2022-09-30 | 2022-12-31 |  | RSTRONG | 2022-09-30 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.9833 | 1 | 1652.47 | 265.93 | 16.08 | 22.42 | 1348.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959039100 |  | 100315369 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | UNIVERSITY | 212 UNIVERSITY AV | 067 | LEX | 2022-09-30 | U461423 | U134723 | 2021-12-10 | 2022-12-30 |  |  | KKOUNS | 2022-09-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2387.94 | 0 | 0 | 0 | 2387.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959039200 |  | 100315367 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | UNIVERSITY | 216 UNIVERSITY AV | 067 | LEX | 2022-09-30 | U461423 | U134723 | 2021-12-10 | 2022-12-30 |  |  | KKOUNS | 2022-09-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2727.28 | 478.57 | 0 | 450.85 | 1797.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959044300 |  | 100315344 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | UNIVERSITY | 211 UNIVERSITY AV | 067 | LEX | 2022-09-30 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-09-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2750.19 | 513.76 | 0 | 104.86 | 2131.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026227000 |  |  |  | 6712208J | 2292182 | U461383 |  | 557 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | 2621P | FORT HARRODS | FORT HARRODS | 067 | LEX | 2023-01-25 | U128132 | U461383 | 2022-09-26 | 2023-05-30 |  | 2022-06-02 | MCRAIG | 2022-09-30 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2270 |  |  | 100 | 055732220262270 | 0.81667 | 3 | 5707.92 | 1858.24 | 114.55 | 2878.36 | 0 | 0 | -3.19 | 859.96 | 3
KY | KY - WEST | 2621 | 22026227100 |  |  |  | 6712208J | 2292182 | U461383 |  | 558 | EX | EMER-RETIRE 3' OF 2"PMP MAIN | 2621P | FORT HARRODS | FORT HARRODS | 067 | LEX | 2023-01-25 | U128132 | U461383 | 2022-09-26 | 2023-05-31 |  | 2022-06-02 | MCRAIG | 2022-09-30 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2271 |  |  | 100 | 055832220262271 | 4.2333 | 0 | 316.08 | 284.16 | 0 | 31.92 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129004300 |  | 100240720 |  | 7324132J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FROGTOWN | FROGTOWN RD | 119 | HIN | 2022-09-30 | JAHOWARD | U130722 | 2022-09-05 | 2022-12-30 |  |  | JAHOWARD | 2022-09-30 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.3 | 1 | 233.78 | 221.41 | 0 | 12.37 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129005700 |  | 100357707 |  | 6740228A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LINK | 630 LINK AV | 017 | PAR | 2022-10-20 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-30 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129006000 |  | 100360205 |  | 6740232M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 301 MAIN ST | 017 | PAR | 2022-10-21 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-30 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 390.22 | 0 | 0 | 0 | 390.22 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129006100 |  | 100467445 |  | 6740232M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 619 MAIN ST | 017 | PAR | 2022-10-21 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-09-30 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22134914500 |  | 100276525 |  | 6684228H |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | WILLOW | 113 WILLOW ST | 073 | FRA | 2022-10-03 | U125208 | U125208 | 2022-09-27 | 2022-09-27 |  |  | CHERNDO | 2022-09-30 | 2022-09-29 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 7.4333 | 2 | 3881.6 | 541.69 | 3.54 | 30.25 | 3306.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22135382000 |  | 100351900 |  | 6744208O | 1635077 |  |  | 565 | EX | REPLACE SERVICE LINE - D096873 | 2621P | ARLINGTON | 116 ARLINGTON RD | 049 | WIN | 2022-09-30 | U125208 | U136097 | 2022-09-28 | 2022-09-28 | 2022-09-28 |  | NRICHIE | 2022-09-30 | 2022-09-29 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 41.8167 | 6 | 3792.61 | 2873.73 | 238.38 | 533.1 | 147.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22135796100 |  | 100319643 |  | 6716208K |  |  |  | 565 | EX | SERV LINE REPLACE | 2621P | ZANDALE | 141 ZANDALE DR | 067 | LEX | 2022-09-30 | LSTANFI | U136097 | 2022-09-29 | 2022-09-29 |  |  | LSTANFI | 2022-09-30 | 2022-09-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 43.5167 | 8 | 3947.67 | 2865.05 | 614.84 | 188.88 | 278.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22136107500 |  | 100351901 |  | 6744208O |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | ARLINGTON | 114 ARLINGTON RD | 049 | WIN | 2022-09-30 | U930915 | U125208 | 2022-09-30 | 2022-09-30 |  |  | NRICHIE | 2022-09-30 | 2022-09-30 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 3.1833 | 3 | 474.84 | 223.89 | 238.45 | 12.5 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22136116000 |  | 500535204 |  | 6716204B | 9721151 |  |  | 566 | EX | RETIRE SERVICE LINE - LEAKAGE | 2621P | NICHOLASVILLE | 3220 NICHOLASVILLE RD | 067 | LEX | 2022-12-28 | U125208 | U132823 | 2022-09-30 | 2022-09-29 |  |  | SSHIMFE | 2022-09-30 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 0.31667 | 0 | 32.58 | 22.53 | 0 | 10.05 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979043700 |  | 100359497 |  | 6736228D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HINTON | 1707 HINTON ST | 017 | PAR | 2022-10-21 | U125881 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | HERBERT HAYDEN | 2022-09-30 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 00424216800 |  | 100429382 |  | 600000000 | 1315787 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GROT | 672 GROT DR | 067 | LEX | 2022-10-03 | WISHII | KEMBERT | 2000-03-01 | 2022-10-03 |  |  | WISHII | 2022-10-03 | 2022-10-03 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.76667 | 2 | 57.93 | 40.22 | 0 | 17.71 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 04575204400 |  | 100335931 |  | 16720212K | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WINCHESTER | 1005 WINCHESTER RD | 067 | LEX | 2022-10-25 | U125881 | SSUTHER | 2004-05-17 | 2022-07-01 | 2022-12-31 |  | NERBERT HAYDEN | 2022-10-03 | 2022-09-01 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.7833 | 3 | 1917.93 | 163.03 | 0 | 9.11 | 1745.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 05603334000 |  | 100335848 | 26 | 600000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WINCHESTER | 1117 WINCHESTER RD | 067 | LEX | 2022-10-25 | U125881 | MPILON | 2005-03-02 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-10-03 | 2022-09-01 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.6167 | 3 | 1995.74 | 93.78 | 0 | 5.56 | 1896.4 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883073500 |  | 100249878 |  | 7356248H | 2180320 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | ROBIN | 8315 ROBIN LN | 019 | CAT | 2022-10-03 | U938684 | U120245 | 2021-01-30 | 2023-06-30 |  |  | CHARLES COMBS | 2022-10-03 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883158400 |  | 100456198 |  | 6716208J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LOWRY | 150 W LOWRY LN 126 | 067 | LEX | 2022-10-03 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-10-03 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.5167 | 1 | 1889.28 | 339.22 | 0 | 67.94 | 1482.12 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883262300 |  | 100463348 |  | 7344240A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NEEDMORE | 2917 NEEDMORE HW | 019 | RUS | 2022-10-03 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-10-03 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916441400 |  | 100264052 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2612 MAIN ST W | 019 | ASH | 2022-10-03 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-10-03 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1617.08 | 0 | 0 | 0 | 1617.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959044400 |  | 100315346 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | UNIVERSITY | 217 UNIVERSITY AV | 067 | LEX | 2022-10-03 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-10-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10 | 1 | 2958.72 | 564.14 | 0 | 33.54 | 2361.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959044500 |  | 100315347 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | UNIVERSITY | 219 UNIVERSITY AV | 067 | LEX | 2022-10-03 | U461322 | U134723 | 2021-12-10 | 2022-12-30 |  |  | STEVE CANOY | 2022-10-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.9833 | 1 | 3339.08 | 444.16 | 0 | 324.91 | 2570.01 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22115128000 |  | 100345466 |  | 6696212H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311976 | 2621P | LOCUST | 222 N LOCUST ST 1 | 239 | VER | 2022-10-03 | DCOLLIN | U125208 | 2022-07-11 | 2023-01-06 | 2024-07-31 |  | DCOLLIN | 2022-10-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.4167 | 1 | 3620.86 | 343.4 | 458.04 | 245.5 | 2573.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126727100 |  | 100316066 |  | 6716208F |  |  |  | 566 | EX | ABANDON SL/LGCY | 2600B | ROSEMONT | 193 ROSEMONT GN | 067 | LEX | 2022-10-03 | LSTANFI | U124960 | 2022-08-25 | 2022-10-03 |  |  | LSTANFI | 2022-10-03 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.75 | 1 | 3118.02 | 371.4 | 33.24 | 140.65 | 2572.73 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129005800 |  | 100358684 |  | 6740232I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LITER | 122 LITER LN | 017 | PAR | 2022-10-03 | U126284 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JOSH PASLEY | 2022-10-03 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.05 | 1 | 2132.99 | 297.8 | 0 | 206.63 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129006300 |  | 500661973 |  | 6740232A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SANDRA | 54 SANDRA LN | 017 | PAR | 2022-10-03 | U126603 | U130722 | 2022-09-05 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-10-03 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2141.76 | 0 | 0 | 0 | 2141.76 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129006500 |  | 100411254 |  | 6740228A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | VINE | 1160 VINE ST | 017 | PAR | 2022-10-03 | U126603 | U130722 | 2022-09-05 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-10-03 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129044000 |  | 100286837 |  | 6720212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DEVONIA | 180 DEVONIA AV | 067 | LEX | 2022-10-04 | U930915 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HMCKUNE | 2022-10-03 | 2022-09-29 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 23.0667 | 4 | 1106.19 | 1025.77 | 19.59 | 60.83 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129044500 |  | 100335764 |  | 6720212K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | INDUSTRY | 1202 INDUSTRY RD | 067 | LEX | 2022-10-04 | UIPBOT10 | U130722 | 2022-09-05 | 2022-12-30 |  |  | LSTANFI | 2022-10-03 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.6667 | 1 | 1752.31 | 107.15 | 256.53 | 40.59 | 1348.04 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129051500 |  | 500019449 |  | 6680224I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BRIDGEPORT BEN | 65 BRIDGEPORT BEN RD | 073 | FRA | 2022-10-25 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-03 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129052600 |  | 100275153 |  | 6684228K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HIGH | 306 HIGH ST | 073 | FRA | 2022-10-25 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-03 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129053800 |  | 100280875 |  | 6688228I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MISSOURI | 248 MISSOURI AV | 073 | FRA | 2022-10-25 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-03 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129053900 |  | 100271702 |  | 6684228K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MURRAY | 129 MURRAY ST | 073 | FRA | 2022-10-25 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-03 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129054600 |  | 100422966 |  | 6688228A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SCHENKEL | 565 SCHENKEL LN 615 | 073 | FRA | 2022-10-04 | U930915 | U130722 | 2022-09-05 | 2022-10-03 |  |  | DCOLLIN | 2022-10-03 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.68333 | 1 | 976.64 | 43.01 | 47.78 | 30.75 | 855.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129056000 |  | 100281159 |  | 6692224E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SHADY | 935 SHADY LN | 239 | MID | 2022-10-25 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-03 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1577.31 | 0 | 99.36 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129080200 |  | 100292166 |  | 6720216L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CIRCLE | 2219 CIRCLE DR | 067 | LEX | 2022-10-03 | U930915 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KKINDER | 2022-10-03 | 2022-09-29 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 18.5667 | 6 | 1244.51 | 1153.49 | 0 | 91.02 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129082100 |  | 100287735 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OAKHILL | 1012 OAKHILL DR | 067 | LEX | 2022-10-20 | U126602 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DEREK PAYTON | 2022-10-03 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16 | 2 | 3640.89 | 860.38 | 0 | 51.16 | 2729.35 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22131527900 |  | 501055814 |  | 7348252H | 0991996 |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | US ROUTE 60 | 6930 US ROUTE 60 | 019 | ASH | 2022-10-06 | U125208 | U132002 | 2022-09-15 | 2022-09-29 | 2022-10-15 |  | RECUMP | 2022-10-03 | 2022-09-28 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 22.7333 | 5 | 1667.36 | 1400.76 | 14.09 | 252.51 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22135659800 |  | 100351243 |  | 6744208N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D096871 | 2621P | HOLIDAY | 91 HOLIDAY RD | 049 | WIN | 2022-10-06 | U125208 | U125208 | 2022-09-29 | 2022-09-30 | 2022-10-19 |  | DENNING | 2022-10-03 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 6.9 | 3 | 1614.3 | 427.54 | 1037.78 | 98.38 | 50.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22136410400 |  | 100288114 |  | 6720212C |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MARGATE | 1665 MARGATE DR | 067 | LEX | 2022-10-03 | WISHII | U129939 | 2022-10-03 | 2022-12-30 |  |  | WISHII | 2022-10-03 | 2022-10-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 18.45 | 4 | 1465.61 | 1128.69 | 0 | 305.02 | 31.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22136420400 |  | 100422967 |  | 6688228A |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | SCHENKEL | 565 SCHENKEL LN 616 | 073 | FRA | 2022-10-03 | DCOLLIN | U129939 | 2022-10-03 | 2022-10-03 |  |  | DCOLLIN | 2022-10-03 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.16667 | 1 | 18.42 | 10.75 | 0 | 7.67 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22136458200 |  | 100358636 |  | 6740232A |  |  |  | 566 | EX | ABANDON | 2621P | SANDRA | 52 SANDRA LN | 017 | PAR | 2022-10-03 | U126603 | U124960 | 2022-10-03 | 2049-12-31 |  |  | SHAWN DENNIS | 2022-10-03 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10 | 1 | 719.44 | 597.07 | 0 | 122.37 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22136458800 |  | 500661972 |  | IP |  |  |  | 566 | EX | ABANDON | 2621P | SANDRA | 53 SANDRA LN | 017 | PAR | 2022-10-03 | U126603 | U124960 | 2022-10-03 | 2049-12-31 |  |  | SHAWN DENNIS | 2022-10-03 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - CENTRAL | 2629 | 22136459300 |  | 500661974 |  | IP |  |  |  | 566 | EX | ABANDON | 2621P | SANDRA | 55 SANDRA LN | 017 | PAR | 2022-10-03 | U126603 | U124960 | 2022-10-03 | 2049-12-31 |  |  | SHAWN DENNIS | 2022-10-03 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - WEST | 2621 | 22979035200 |  | 100320065 |  | 6716208K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | JESSELIN | 143 JESSELIN DR | 067 | LEX | 2022-10-03 | U123111 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | LYN STAFFORD | 2022-10-03 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 3775.61 | 448.86 | 0 | 325.95 | 3000.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979053000 |  | 500483331 |  | 6740232E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CATHY | 124 CATHY DR | 017 | PAR | 2022-10-03 | U126284 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | JOSH PASLEY | 2022-10-03 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.95 | 1 | 2123 | 291.91 | 0 | 202.53 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983421900 |  | 100324771 |  | 6720204B | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 1120 GREENTREE CT | 067 | LEX | 2022-10-03 | U129731 | U134723 | 2022-03-03 | 2022-12-30 |  |  | F.GOINS | 2022-10-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1029.98 | 0 | 0 | 0 | 1029.98 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983768400 |  | 100324769 |  | 6720204B | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 1116 GREENTREE CT | 067 | LEX | 2022-10-03 | U129731 | U134723 | 2022-03-04 | 2022-12-30 |  |  | F.GOINS | 2022-10-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1028.5 | 0 | 0 | 0 | 1028.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 03538302000 |  | 100336036 |  | 6720212K | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | ROYAL | 902 ROYAL AV | 067 | LEX | 2022-10-04 | U127206 | DMCCULL | 2003-04-29 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-10-04 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 3198.12 | 0 | 0 | 0 | 3198.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 07671544400 |  | 100359655 |  | 6736228C |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CYPRESS | 1956 CYPRESS ST | 017 | PAR | 2022-10-04 | U126603 | SKSMITH | 2007-01-08 | 2022-07-01 | 2022-12-31 |  | SHAWN DENNIS | 2022-10-04 | 2022-10-04 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5 | 1 | 9982.2 | 297.34 | 0 | 60.95 | 9623.91 | 0 | 0 | 0
KY | KY - WEST | 2621 | 16426864900 |  | 100333539 |  | 6716212H | 0252212 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LIMESTONE | 240 N LIMESTONE ST N-CAMP | 067 | LEX | 2022-10-25 | U125881 | U122906 | 2016-07-14 | 2022-07-01 | 2022-12-31 |  | HERBERT HAYDEN | 2022-10-04 | 2022-09-07 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.2333 | 2 | 3351.28 | 281.96 | 0 | 23.76 | 3045.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21026139300 |  |  |  | 7256280G | 2180424 | U122858 |  | 584 | EX | RETIRE STATION R-1455 | 2621M | 2ND | W 2ND ST | 161 | MAY | 2022-11-10 | U123258 | U122858 | 2021-09-01 | 2022-12-29 | 2022-12-30 | 2022-10-04 | JMARTIN | 2022-10-04 |  |  | F | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00584 | 3200584 |  |  | WP1393 | AMRCB |  | 100 | 058432210261393 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883161100 |  | 100335873 |  | 6720212K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LOUDON | 821 E LOUDON AV | 067 | LEX | 2022-10-10 | U127206 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-10-04 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 2330.74 | 426.66 | 0 | 25.38 | 1878.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883245500 |  | 100290607 |  | 6720216O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | OLD PARIS | 1813 OLD PARIS RD STE 100 | 067 | LEX | 2022-10-10 | U127206 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-10-04 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 492.07 | 0 | 0 | 0 | 492.07 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916434500 |  | 100264056 |  | 7356256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | LINDA | 743 LINDA LN | 019 | ASH | 2022-10-04 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-10-04 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2088.39 | 0 | 0 | 0 | 2088.39 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916434600 |  | 100264055 |  | 7356256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | LINDA | 744 LINDA LN | 019 | ASH | 2022-10-04 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-10-04 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3109.26 | 0 | 0 | 0 | 3109.26 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959038700 |  | 100315374 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | UNIVERSITY | 206 UNIVERSITY AV | 067 | LEX | 2022-10-04 | U461322 | U134723 | 2021-12-10 | 2022-12-30 |  |  | STEVE CANOY | 2022-10-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.9833 | 1 | 3252.69 | 444.16 | 0 | 324.91 | 2483.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959039300 |  | 100315366 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | UNIVERSITY | 218 UNIVERSITY AV | 067 | LEX | 2022-10-04 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-10-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 3039.39 | 451.31 | 0 | 96.34 | 2491.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026173000 |  |  |  | 6720208I | 2286833 | U134275 |  | 909 | EX | 2022 SCADA VISABILITY PROGRAM | 2600E | ALUMNI | ALUMNI DR | 067 | LEX | 2022-10-25 | U123258 | GSULLI1 | 2022-03-03 | 2022-10-25 | 2022-11-30 | 2022-10-04 | SMCHOLAN | 2022-10-04 | 2022-05-12 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3201029 |  |  | WP1730 | SCADA |  | 100 | 102932220261730 | 17.9167 | 0 | 47294.28 | 3564.31 | 9048.32 | 1681.24 | 32868.11 | 0 | 132.3 | 0
KY | KY - WEST | 2621 | 22026204200 |  |  |  | 6720208I |  | U122858 |  | 584 | EX | RETIRED GAUGE | 2621M | ALUMNI | ALUMNI DR | 067 | LEX | 2022-10-25 | U123258 | U136124 | 2022-06-13 | 2023-06-01 | 2023-06-01 | 2022-10-04 | SMCHOLAN | 2022-10-04 |  |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00584 | 3200584 |  |  | WP2042 |  |  | 100 | 058432220262042 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22026205600 |  |  |  | 7352256H | 2289560 | U132280 |  | 557 | EX | INSTALL 1200'-2" PMMP | 2600B | CENTRAL | CENTRAL PY | 019 | ASH | 2022-11-17 | U128132 | U132280 | 2022-06-16 | 2022-09-27 | 2024-12-25 | 2022-10-03 | DAVID SKAGGS | 2022-10-04 | 2022-08-31 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP2056 | AMRCB |  | 100 | 055732220262056 | 201.85 | 31700 | 162971.11 | 10645.56 | 6415.71 | 1922.96 | 125499.62 | 0 | 309.91 | 18177.35 | 1268
KY | KY - CENTRAL | 2629 | 22026221900 |  |  |  | 6744208J | 2291343 | U122858 |  | 558 | EX | EMER - RETIRE 20'-3" PMP | 2621P | OREO | 423 OREO | 049 | WIN | 2022-10-05 | U128132 | U122858 | 2022-09-06 |  | 2049-12-31 | 2022-09-03 | AHATFIELD | 2022-10-04 | 2022-09-07 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP2219 |  |  | 100 | 055832220262219 | 2.2833 | 0 | 6987.81 | 2236.99 | 0 | 124.82 | 4626 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026228100 |  |  |  | 6724212N | 2292352 | U461383 |  | 558 | EX | EMER-RETIRE 3' OF 2"PMMP MAIN | 2621P | COSIMO | COSIMO | 067 | LEX | 2022-10-05 | U460266 | U461383 | 2022-09-28 | 2023-05-31 |  | 2022-09-21 | LSTANFIELD | 2022-10-04 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2281 |  |  | 100 | 055832220262281 | 8 | 0 | 590.32 | 559.8 | 0 | 30.52 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22117001800 |  | 100353785 |  | 7256280L | 1855043 |  |  | 566 | EX | ABANDON SL - SOII/INSIDE | 2621P | 2ND | 42 W 2ND ST | 161 | MAY | 2022-10-04 | SDADAMS | U130868 | 2022-07-19 | 2022-07-19 | 2022-10-14 |  | SDADAMS | 2022-10-04 | 2022-08-18 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 3.9667 | 3 | 971.26 | 244.1 | 94.64 | 14.52 | 618 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22121190300 |  | 100278664 |  | 6688232O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER | 2623D | MENOMINEE | 426 MENOMINEE TL | 073 | FRA | 2022-10-04 | DCOLLIN | AOC SYST | 2022-08-03 | 2022-10-02 | 2022-10-02 |  | DCOLLIN | 2022-10-04 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 4.8667 | 1 | 3217.29 | 308.64 | 420.17 | 18.36 | 2470.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129005400 |  | 100360963 |  | 6736216H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | AUSTERLITZ | 128 AUSTERLITZ RD | 017 | PAR | 2022-10-05 | U127414 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ED FOX | 2022-10-04 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.5333 | 1 | 1713.63 | 151.39 | 0 | 8.99 | 1553.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129005500 |  | 501179802 |  | 6736228L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CASTLE | 201 CASTLE BV | 017 | PAR | 2022-10-05 | U127414 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ED FOX | 2022-10-04 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.0333 | 1 | 1623.59 | 120.91 | 0 | 24.73 | 1477.95 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129005600 |  | 500647390 |  | 6736228K | 9717751 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DAVID | 659 DAVID LN | 017 | PAR | 2022-10-05 | U127414 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ED FOX | 2022-10-04 | 2022-10-04 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.5333 | 1 | 1899.93 | 151.39 | 0 | 30.98 | 1717.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129006400 |  | 501165534 |  | 6740232M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SQUIRES POINTE | 206 SQUIRES POINTE RD | 017 | PAR | 2022-10-05 | U127414 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ED FOX | 2022-10-04 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.4 | 1 | 1727.03 | 144.26 | 0 | 29.52 | 1553.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129045200 |  | 100338782 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LOUDON | 264 E LOUDON AV | 067 | LEX | 2022-10-04 | LSTANFI | U130722 | 2022-09-05 | 2022-12-30 |  |  | LSTANFI | 2022-10-04 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.6167 | 1 | 2434.52 | 172.08 | 34.04 | 18.52 | 2209.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129047000 |  | 100333594 |  | 6720212I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GUNN | 410 GUNN ST | 067 | LEX | 2022-10-25 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-04 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129078700 |  | 100312084 |  | 6716208I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HILL N DALE | 273 HILL N DALE RD | 067 | LEX | 2022-10-25 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-04 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129083000 |  | 100297733 |  | 6716212H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MARKET | 253 MARKET ST | 067 | LEX | 2022-10-05 | U930915 | U130722 | 2022-09-05 | 2022-12-30 |  |  | LSTANFI | 2022-10-04 | 2022-09-29 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.5833 | 2 | 2281.68 | 427.62 | 16.08 | 151.68 | 1686.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22134889800 |  | 500024346 |  | 6720208L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D305533 | 2621P | RICHMOND | 2601 RICHMOND RD HOTEL | 067 | LEX | 2022-10-06 | U125208 | U125208 | 2022-09-27 | 2022-09-29 | 2022-10-17 |  | TROE | 2022-10-04 | 2022-10-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 34.5 | 8 | 1981.55 | 1657.85 | 219.59 | 98.61 | 5.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22135029000 |  | 100255014 |  | 7348264N |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | FIELDS | 2600 FIELDS AV | 089 | FLA | 2022-10-04 | JCYRUS | U125208 | 2022-09-27 | 2022-09-30 | 2022-10-18 |  | JCYRUS | 2022-10-04 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 6.7833 | 2 | 657.56 | 409.89 | 155.09 | 24.38 | 68.2 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22136611800 |  | 100284272 |  | 6712224H |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | LISLE | 1102 LISLE RD | 209 | GEO | 2022-10-04 | DCOLLIN | U129939 | 2022-10-04 | 2022-10-04 |  |  | DCOLLIN | 2022-10-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 1.7333 | 1 | 2578.14 | 259.89 | 248.31 | 185.84 | 1884.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22136639700 |  | 100319685 |  | 6716208K |  |  |  | 565 | EX | GRADE 1 REPLACE SERVICE | 2621P | ZANDALE | 212 ZANDALE DR | 067 | LEX | 2022-10-04 | TROE | U129939 | 2022-10-04 | 2022-10-04 | 2022-10-04 |  | TROE | 2022-10-04 | 2022-10-04 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.5833 | 3 | 2498.92 | 1259.52 | 779.76 | 394.74 | 64.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22136658800 |  | 500288547 |  | 6720212K |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | LIBERTY | 924 LIBERTY RD A-1FR | 067 | LEX | 2022-10-04 | U126602 | U125763 | 2022-10-04 | 2022-12-30 |  |  | DEREK PAYTON | 2022-10-04 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 3619.92 | 433.72 | 0 | 25.78 | 3160.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22979036600 |  | 100333946 |  | 6720212K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LIBERTY | 924 LIBERTY RD B-1FL | 067 | LEX | 2022-10-04 | U126602 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | DEREK PAYTON | 2022-10-04 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 3865.09 | 0 | 0 | 0 | 3865.09 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979043600 |  | 100359438 |  | 6736228D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CYPRESS | 1633 CYPRESS ST | 017 | PAR | 2022-10-04 | U126603 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | SHAWN DENNIS | 2022-10-04 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4 | 1 | 1917.81 | 240.05 | 0 | 49.2 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983421700 |  | 100324764 |  | 6720204A | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 1115 GREENTREE CT | 067 | LEX | 2022-10-04 | U126530 | U134723 | 2022-03-03 | 2022-12-30 |  |  | JDUNN | 2022-10-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1048.88 | 0 | 0 | 0 | 1048.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983425600 |  | 100324772 |  | 6720204B | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 1124 GREENTREE CT | 067 | LEX | 2022-10-04 | U129731 | U134723 | 2022-03-03 | 2022-12-30 |  |  | F.GOINS | 2022-10-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1152.4 | 0 | 0 | 0 | 1152.4 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22986441400 |  | 100359656 |  | 6736228C |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2600B | CYPRESS | 1952 CYPRESS ST | 017 | PAR | 2022-10-04 | U126603 | U134723 | 2022-03-16 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-10-04 | 2022-03-16 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10 | 1 | 2410.29 | 607.97 | 0 | 34.46 | 1767.86 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22994327600 |  | 100353546 |  | 7256280K | 2180424 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | 3RD | 246 W 3RD ST | 161 | MAY | 2022-10-20 | U461478 | U134723 | 2022-04-19 | 2022-12-30 |  |  | DAVID STAGGS | 2022-10-04 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26320043 |  | 1
KY | KY - WEST | 2621 | 03528741500 |  | 100298414 |  | 6716212H | 1528079 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SHORT ** BLDG GONE ** | 434 W SHORT ** BLDG GONE ** ST | 067 | LEX | 2022-10-05 | LSTONE | DMCCULL | 2003-01-24 | 2022-07-01 | 2022-12-31 |  | LSTONE | 2022-10-05 | 2022-09-07 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.0333 | 4 | 431.78 | 154.59 | 0 | 9.35 | 267.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 03533820900 |  | 100336427 |  | V-1021-50 | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | M L KING | 303 M L KING BV | 067 | LEX | 2022-10-05 | U930915 | DMCCULL | 2003-03-17 | 2022-07-01 | 2022-12-31 |  | TROE | 2022-10-05 | 2022-09-07 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.4667 | 5 | 1480.64 | 208.29 | 0 | 15.43 | 1256.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11900875200 |  | 100290595 |  | 6720216O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | OLD PARIS | 1833 OLD PARIS RD | 067 | LEX | 2022-10-05 | U128410 | U123853 | 2011-04-12 | 2022-07-01 | 2022-12-31 |  | CDESPAIN | 2022-10-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1708.57 | 0 | 0 | 0 | 1708.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18576147400 |  | 500260940 |  | 6716212G |  |  |  | 566 | EX | ABANDON METER SET ONLY | 2621P | MADISON | 300 MADISON PL B | 067 | LEX | 2022-10-05 | U930915 | U461383 | 2018-01-19 | 2022-12-30 |  |  | LSTONE | 2022-10-05 | 2022-10-05 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 1.3333 | 3 | 76.84 | 72.52 | 0 | 4.32 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18576151800 |  | 100307706 |  | 6716212G | 1746168 |  |  | 566 | EX | METER ABANDON ONLY | 2621P | MADISON | 318 MADISON PL | 067 | LEX | 2022-10-05 | U930915 | U461383 | 2018-01-19 | 2019-12-31 |  |  | TROE | 2022-10-05 | 2022-10-05 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 4.1833 | 3 | 244.58 | 230.83 | 0 | 13.75 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19705060700 |  | 100312643 |  | 6716208E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SOUTHVIEW | 2318 SOUTHVIEW DR | 067 | LEX | 2022-10-05 | LSTANFI | U125208 | 2019-05-10 | 2022-10-05 |  |  | LSTANFI | 2022-10-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.3833 | 1 | 2694.53 | 284.44 | 145.85 | 107.68 | 2156.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883159400 |  | 500781159 |  | 6720212C |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NEW CIRCLE | 175 E NEW CIRCLE RD | 067 | LEX | 2022-11-01 | U128410 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CDESPAIN | 2022-10-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1708.57 | 0 | 0 | 0 | 1708.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21884249900 |  | 100290401 |  | 6720212C |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NEW CIRCLE | 171 E NEW CIRCLE RD | 067 | LEX | 2022-11-01 | U128410 | U128293 | 2021-02-04 | 2022-07-01 | 2022-12-31 |  | CDESPAIN | 2022-10-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1708.57 | 0 | 0 | 0 | 1708.57 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916433900 |  | 100264051 |  | 7356256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | LINDA | 728 LINDA LN | 019 | ASH | 2022-10-05 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-10-05 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2089.59 | 0 | 0 | 0 | 2089.59 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916434100 |  | 100264053 |  | 7356256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | LINDA | 732 LINDA LN | 019 | ASH | 2022-10-05 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-10-05 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2392.95 | 0 | 0 | 0 | 2392.95 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916434300 |  | 100264057 |  | 7356256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | LINDA | 735 LINDA LN | 019 | ASH | 2022-10-05 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-10-05 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1852.61 | 0 | 0 | 0 | 1852.61 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959034100 |  | 100315350 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | CRESCENT | 1109 CRESCENT AV | 067 | LEX | 2022-10-05 | U461423 | U134723 | 2021-12-10 | 2022-12-30 |  |  | KKOUNS | 2022-10-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2846.43 | 450.25 | 0 | 26.76 | 2369.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959039400 |  | 100315365 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | UNIVERSITY | 220 UNIVERSITY AV | 067 | LEX | 2022-10-05 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-10-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.25 | 1 | 3587.23 | 521.83 | 0 | 111.39 | 2954.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959039600 |  | 100315364 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | UNIVERSITY | 222 UNIVERSITY AV | 067 | LEX | 2022-10-05 | U461322 | U134723 | 2021-12-10 | 2022-12-30 |  |  | STEVE CANOY | 2022-10-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.9833 | 1 | 2737.79 | 444.16 | 0 | 324.91 | 1968.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026174500 |  |  |  | 6712208K | 2286833 | U126783 |  | 909 | EX | 2022 SCADA VISIBILITY PROGRAM | 2600E | HARRODSBURG | 3090 HARRODSBURG RD | 067 | LEX | 2022-10-20 | U123258 | U126783 | 2022-03-07 | 2022-10-25 | 2022-11-30 | 2022-10-05 | CCOX | 2022-10-05 | 2022-05-11 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3201029 |  |  | WP1745 | SCADA |  | 100 | 102932220261745 | 39.2667 | 0 | 29029.69 | 2622.62 | 0 | 164.12 | 26153.44 | 0 | 89.51 | 0
KY | KY - WEST | 2621 | 22026203900 |  |  |  | 6712208K | 2286833 | U461383 |  | 584 | EX | RETIRE PAPER GAUGE | 2621M | HARRODSBURG | 3090 HARRODSBURG RD | 067 | LEX | 2022-10-20 | U123258 | U461383 | 2022-06-10 | 2022-12-01 | 2022-12-01 | 2022-10-05 | CCOX | 2022-10-05 |  |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00584 | 3200584 |  |  | WP2039 |  |  | 100 | 058432220262039 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22103220400 |  | 100313343 |  | 6716208A | 2069466 |  |  | 565 | EX | REPLACE SL W/22-0261850-00 | 2600B | CLAYS MILL | 1602 CLAYS MILL RD 1F | 067 | LEX | 2022-10-06 | U128762 | U134723 | 2022-05-24 | 2022-12-30 |  |  | CORY TINCHER | 2022-10-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3703.57 | 0 | 0 | 0 | 3703.57 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22116104100 |  | 100345092 |  | 6696212G | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER | 2623D | WALNUT | 134 WALNUT ST | 239 | VER | 2022-10-05 | CHERNDO | AOC SYST | 2022-07-14 | 2022-08-12 | 2022-09-12 |  | CHERNDO | 2022-10-05 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 20.3333 | 4 | 1879.12 | 1016.91 | 293.14 | 59.92 | 509.15 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129010700 |  | 100264951 |  | 7348248L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CANNONSBURG | 1524 CANNONSBURG RD | 019 | CAN | 2022-10-06 | U938684 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHARLES COMBS | 2022-10-05 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129010800 |  | 100245446 |  | 7360248A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 34TH | 211 34TH ST | 019 | CAT | 2022-10-06 | U938684 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHARLES COMBS | 2022-10-05 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129015500 |  | 100249410 |  | 7348264A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 1ST | 91 1ST ST | 127 | LOU | 2022-11-09 | U938684 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHARLES COMBS | 2022-10-05 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1530 | 0 | 0 | 0 | 1530 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129017300 |  | 100290940 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LIMESTONE | 791 N LIMESTONE ST | 067 | LEX | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1732.63 | 0 | 0 | 0 | 1732.63 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129020800 |  | 100360315 |  | 6736228H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BRENT | 1945 BRENT ST | 017 | PAR | 2022-10-05 | U126603 | U130722 | 2022-09-05 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-10-05 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.9167 | 1 | 1539.61 | 176.15 | 0 | 36.12 | 1327.34 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129021000 |  | 100359535 |  | 6736232P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RIO VISTA | 1869 RIO VISTA DR | 017 | PAR | 2022-10-05 | U126603 | U130722 | 2022-09-05 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-10-05 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.5833 | 1 | 1991.4 | 213.15 | 0 | 43.7 | 1734.55 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129021100 |  | 100411340 |  | 6740228A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | VINE | 1132 VINE ST | 017 | PAR | 2022-10-05 | U126603 | U130722 | 2022-09-05 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-10-05 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129021300 |  | 100408098 |  | 6736228B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WESTWOOD | 806 WESTWOOD DR | 017 | PAR | 2022-10-05 | U126603 | U130722 | 2022-09-05 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-10-05 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.5 | 1 | 1984.94 | 207.81 | 0 | 42.58 | 1734.55 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129021700 |  | 100349895 |  | 6748204A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ELIZABETH | 39 ELIZABETH ST | 049 | WIN | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-05 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129021900 |  | 100348881 |  | 6748208N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | JOHNSON | 24 JOHNSON ST | 049 | WIN | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-05 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129040800 |  | 100267799 |  | 7356216C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RICE | 117 N RICE ST | 127 | LOU | 2022-10-06 | U938684 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHARLES COMBS | 2022-10-05 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129041300 |  | 100468138 |  | 7356216G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WREN | 99 WREN LN | 127 | LOU | 2022-10-06 | U938684 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHARLES COMBS | 2022-10-05 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129045700 |  | 100290727 |  | 6720212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PARIS | 139 PARIS AV | 067 | LEX | 2022-10-05 | HMCKUNE | U130722 | 2022-09-05 | 2022-12-30 |  |  | HMCKUNE | 2022-10-05 | 2022-10-03 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 28.3333 | 8 | 1727.72 | 1419.54 | 223.79 | 84.39 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129046000 |  | 100334023 |  | 6720212O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SPARKS | 1141 SPARKS RD | 067 | LEX | 2022-10-05 | LSTANFI | U130722 | 2022-09-05 | 2022-10-05 |  |  | LSTANFI | 2022-10-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.7667 | 1 | 1557.84 | 178.56 | 34.04 | 67.62 | 1277.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129047100 |  | 100336668 |  | 6720212I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HAWKINS | 430 HAWKINS AV | 067 | LEX | 2022-10-05 | U127414 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ED FOX | 2022-10-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.6 | 1 | 3007.59 | 275.26 | 0 | 56.33 | 2676 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129047600 |  | 100294402 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LIMESTONE | 575 N LIMESTONE ST | 067 | LEX | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1402.64 | 0 | 0 | 0 | 1402.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129047700 |  | 500007522 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LIMESTONE | 407 N LIMESTONE ST | 067 | LEX | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129048100 |  | 100296856 |  | 6716212C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MICHIGAN | 435 MICHIGAN ST | 067 | LEX | 2022-10-06 | U123111 | U130722 | 2022-09-05 | 2022-12-30 |  |  | LYN STAFFORD | 2022-10-05 | 2022-10-05 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.05 | 2 | 1988.23 | 339.48 | 0 | 20.19 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129048200 |  | 100295345 |  | 6716212D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NEWTOWN | 537 NEWTOWN PK | 067 | LEX | 2022-10-06 | U123111 | U130722 | 2022-09-05 | 2022-12-30 |  |  | LYN STAFFORD | 2022-10-05 | 2022-10-05 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.95 | 2 | 2338.92 | 670.51 | 0 | 39.85 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129082300 |  | 100290594 |  | 6720216O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OLD PARIS | 1837 OLD PARIS RD | 067 | LEX | 2022-10-05 | U128410 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CDESPAIN | 2022-10-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1708.57 | 0 | 0 | 0 | 1708.57 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129090400 |  | 100457339 |  | 6688228B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SCHENKEL | 740 SCHENKEL LN | 073 | FRA | 2022-10-05 | DCOLLIN | U130722 | 2022-09-05 | 2022-10-05 |  |  | DCOLLIN | 2022-10-05 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 1.3 | 1 | 1226.61 | 83.5 | 228.31 | 59.7 | 855.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129123900 |  | 100466072 |  | 7356216F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HIGHWAY 32 | 407 HIGHWAY 32 | 127 | LOU | 2022-10-20 | U938684 | U125208 | 2022-09-06 | 2022-12-30 |  |  | CHARLES COMBS | 2022-10-05 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22136674000 |  | 100319493 |  | 6716208K |  |  |  | 565 | EX | GRADE 1 REPLACE SERVICE | 2621P | ZANDALE | 293 ZANDALE DR | 067 | LEX | 2022-10-05 | MCRAIG | U129939 | 2022-10-04 | 2022-10-04 | 2022-10-04 |  | MCRAIG | 2022-10-05 | 2022-10-04 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 30.4667 | 6 | 2006.16 | 1331.85 | 276.56 | 344.95 | 52.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22136841900 |  | 100416146 |  | 6688232O |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | TONKAWA | 216 TONKAWA TL | 073 | FRA | 2022-10-05 | DCOLLIN | U129939 | 2022-10-05 | 2022-10-05 |  |  | DCOLLIN | 2022-10-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.6167 | 1 | 2307.05 | 353.51 | 286.8 | 252.74 | 1414 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22136922100 |  | 500011133 |  | 6688228L |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | ISAAC SHELBY | 740 ISAAC SHELBY CR W | 073 | FRA | 2022-10-05 | DCOLLIN | U129939 | 2022-10-05 | 2022-10-05 |  |  | DCOLLIN | 2022-10-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.9667 | 1 | 2266.33 | 251.73 | 177.82 | 179.96 | 1656.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22136942000 |  | 100319203 |  | 6716208O |  |  |  | 565 | EX | GRADE 1 REPLACE SERVICE | 2621P | MELBOURNE | 277 MELBOURNE WY | 067 | LEX | 2022-10-05 | MCRAIG | U129939 | 2022-10-05 | 2022-10-05 | 2022-10-05 |  | MCRAIG | 2022-10-05 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.25 | 4 | 1524.75 | 877.32 | 356.28 | 222.95 | 68.2 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979025700 |  | 100264854 |  | 7348248P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MUSIC | 2920 MUSIC BR | 019 | CAN | 2022-10-06 | U938684 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | CHARLES COMBS | 2022-10-05 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22979036800 |  | 100335155 |  | 6720212K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LIBERTY | 999 LIBERTY RD | 067 | LEX | 2022-10-05 | U126602 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | DEREK PAYTON | 2022-10-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 4518.8 | 433.72 | 0 | 25.78 | 4059.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983421500 |  | 100324773 |  | 6720204A | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 1109 GREENTREE CT | 067 | LEX | 2022-10-05 | U129731 | U134723 | 2022-03-03 | 2022-12-30 |  |  | F.GOINS | 2022-10-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1445.07 | 0 | 0 | 0 | 1445.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 95231123000 |  | 100431692 |  | 6716212L |  |  |  | 566 | EX | METER ABANDON ONLY | 2621P | ESPLANADE | 114 ESPLANADE ST | 067 | LEX | 2022-10-05 | U930915 | MNBEINK | 1995-10-12 | 2018-12-21 |  |  | TROE | 2022-10-05 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.7 | 3 | 94.06 | 88.78 | 0 | 5.28 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 12979116400 |  | 100353736 |  | 17256280L | 1747939 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | 2ND | 144 W 2ND ST | 161 | MAY | 2022-10-06 | SDADAMS | U125208 | 2012-07-03 | 2022-06-30 | 2022-12-31 |  | SDADAMS | 2022-10-06 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 0.63333 | 1 | 40.98 | 38.67 | 0 | 2.31 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 17497737200 |  | 500349774 |  | 6716212L | 1318533 |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | KALMIA | 271 KALMIA AV A LLFT | 067 | LEX | 2022-10-06 | TROE | U122906 | 2017-04-14 | 2019-12-31 |  |  | TROE | 2022-10-06 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.0833 | 3 | 115.95 | 109.44 | 0 | 6.51 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18576145300 |  | 100290835 |  | 6720212B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 12TH | 103 12TH ST 1FR | 067 | LEX | 2022-10-06 | U126602 | U461673 | 2018-01-19 | 2022-07-01 | 2022-12-31 |  | DEREK PAYTON | 2022-10-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 3188.85 | 433.72 | 0 | 25.78 | 2729.35 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18576145500 |  | 100290836 |  | 6720212B |  |  |  | 566 | EX | METER ABANDON ONLY | 2621P | 12TH | 105 12TH ST 1FL | 067 | LEX | 2022-10-06 | U126602 | U461673 | 2018-01-19 | 2018-02-28 |  |  | DEREK PAYTON | 2022-10-06 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1368.31 | 0 | 0 | 0 | 1368.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18577385500 |  | 100459242 |  | 6716212G | 1746168 |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | HIGH | 822 W HIGH ST 1FRR | 067 | LEX | 2022-10-06 | U930915 | U131066 | 2018-01-26 | 2019-12-31 |  |  | LSTONE | 2022-10-06 | 2022-10-06 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.9833 | 3 | 111.09 | 104.87 | 0 | 6.22 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21026119400 |  |  |  | 6712236H | 2070683 | U124399 |  | 559 | CO | PM- INST FIL/SEP TOYOTA STA | 5320E | CHERRY BLOSSOM SPUR | CHERRY BLOSSOM SPUR | 209 | GEO | 2022-12-29 |  | U124399 | 2021-04-28 | 2021-12-29 | 2021-12-31 | 2022-10-06 | SWBISHOP | 2022-10-06 |  |  | C | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00559 | 3201013 |  |  | WP1194 | KSMRP |  | 100 | 101332210261194 |  | 119 | 2073205.75 | 6348.42 | 262829.57 | 20145.44 | 1470532.08 | 0 | 35508.95 | 277841.29 | 119
KY | KY - WEST | 2623 | 21026119500 |  |  |  | 6712236H | 2070683 | U124399 |  | 560 | CO | PM-ABAN FOR FILTER INST TOYOTA | 5320E | CHERRY BLOSSOM SPUR | CHERRY BLOSSOM SPUR | 209 | GEO | 2022-12-29 |  | U124399 | 2021-04-28 | 2021-12-29 | 2021-12-31 | 2022-10-06 | SWBISHOP | 2022-10-06 |  |  | C | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00560 | 3201014 |  |  | WP1195 | KSMRP |  | 100 | 101432210261195 |  | 0 | 522788.31 | 47802.24 | 240014.49 | 18.61 | 234952.97 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21026127300 |  |  |  | 7256280K | 2180424 | U122858 |  | 558 | EX | RETIRE 2100'-2"&4" BSMP | 2600B |  |  | 161 | MAY | 2022-11-10 | U128132 | U122858 | 2021-06-08 | 2022-12-30 | 2022-12-31 | 2022-10-06 | DAVID STAGGS | 2022-10-06 | 2022-10-04 |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00558 | 3200558 |  |  | WP1273 | AMRCB |  | 100 | 055832210261273 | 5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21026131900 |  |  |  | 6688228J | 2181158 | U126783 |  | 557 | EX | INSTALL 3843' OF 2"/4"PMMP MN | 2600B | LYONS | LYONS DR | 073 | FRA | 2023-01-04 | U128132 | U126783 | 2021-07-12 | 2022-09-01 | 2022-12-31 | 2022-08-16 | CDESPAIN | 2022-10-06 | 2022-03-03 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP1319 | AMRCB |  | 100 | 055732210261319 | 1133.3833 | 478296 | 1468486.46 | 72569.15 | 228788.89 | 7437.33 | 884160.54 | 0 | 5054.39 | 270476.16 | 3796
KY | KY - WEST | 2623 | 21026132000 |  |  |  | 6688228J | 2181158 | U126783 |  | 558 | EX | RETIRE 3700' OF 4"/6"BSLP MAIN | 2600B | LYONS | LYONS | 073 | FRA | 2022-12-28 | U128132 | U126783 | 2021-07-12 | 2022-12-30 | 2022-12-31 | 2022-09-27 | CDESPAIN | 2022-10-06 | 2022-03-18 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP1320 | AMRCB |  | 100 | 055832210261320 | 48.5167 | 0 | 3419.35 | 3217.73 | 0 | 201.62 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883107000 |  | 100319761 |  | 6716208J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NICHOLASVILLE | 2220 NICHOLASVILLE RD STE 140 | 067 | LEX | 2022-10-06 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-10-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.4833 | 1 | 2063.77 | 154.18 | 0 | 30.89 | 1878.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883107100 |  | 100319762 |  | 6716208J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NICHOLASVILLE | 2220 NICHOLASVILLE RD STE 138 | 067 | LEX | 2022-10-06 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-10-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.5167 | 1 | 2285.86 | 339.22 | 0 | 67.94 | 1878.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916433700 |  | 100264060 |  | 7356256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | LINDA | 701 LINDA LN | 019 | ASH | 2022-10-06 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-10-06 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3019.56 | 0 | 0 | 0 | 3019.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916434000 |  | 100264058 |  | 7356256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | LINDA | 731 LINDA LN | 019 | ASH | 2022-10-06 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-10-06 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3187.58 | 0 | 0 | 0 | 3187.58 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916453000 |  | 100264059 |  | 7356256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | LINDA | 711 LINDA LN | 019 | ASH | 2022-10-06 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-10-06 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2311.64 | 0 | 0 | 0 | 2311.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959033900 |  | 100315295 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | CRESCENT | 1105 CRESCENT AV | 067 | LEX | 2022-10-06 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-10-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 1922.86 | 451.31 | 0 | 96.34 | 1375.21 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959034300 |  | 100315354 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | CRESCENT | 1115 CRESCENT AV | 067 | LEX | 2022-10-06 | U461423 | U134723 | 2021-12-10 | 2022-12-30 |  |  | KKOUNS | 2022-10-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2760.9 | 450.25 | 0 | 326.02 | 1984.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959036600 |  | 100315307 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | STATE | 208 STATE ST | 067 | LEX | 2022-10-06 | U461322 | U134723 | 2021-12-10 | 2022-12-30 |  |  | STEVE CANOY | 2022-10-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.5 | 1 | 2988.11 | 528.76 | 0 | 31.42 | 2427.93 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959965500 |  | 100358929 |  | 6736232L | 2075121 |  |  | 566 | EX | ABANDON SL W/ CAPITOL JOB | 2600B | HANSON | 425 HANSON ST | 017 | PAR | 2022-10-06 | U126603 | U134723 | 2021-12-16 | 2022-09-30 |  |  | SHAWN DENNIS | 2022-10-06 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26290043 | 4.5833 | 1 | 1957.4 | 272.89 | 0 | 55.95 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960236700 |  | 100321010 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | MAXWELL | 309 E MAXWELL ST 1F | 067 | LEX | 2022-10-07 | U126309 | U134723 | 2021-12-17 | 2022-12-30 |  |  | JAMIE LYNN | 2022-10-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 6058.47 | 0 | 0 | 0 | 6058.47 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22026205200 |  | 501330833 |  | 7348264K | 2289386 | U938437 |  | 555 | EX | INSTALL 115'-2" PMMP | 2600B | MAPLE | 1519 MAPLE ST | 089 | FLA | 2022-10-24 | U128132 | U132280 | 2022-06-14 | 2022-10-04 | 2022-10-07 | 2022-10-05 | MBLANKE/CJH C PACK | 2022-10-06 | 2022-10-03 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP2052 |  |  | 100 | 055532220262052 | 40.2667 | 618 | 21273.79 | 2686.04 | 1460.71 | 1421.22 | 13702.94 | 0 | 22.66 | 1980.22 | 103
KY | KY - CENTRAL | 2632 | 22026206300 |  |  |  | 7256280N | 2289591 | U122858 |  | 558 | EX | RETIRE 22'-4" WIIP | 2600B | RT 62 | RT 62 | 161 | MAY | 2022-11-01 | U131995 | U122858 | 2022-06-18 | 2022-10-28 | 2022-11-30 | 2022-10-06 | DAVID STAGGS | 2022-10-06 | 2022-09-30 |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00558 | 3200558 |  |  | WP2063 | AMRCB |  | 100 | 055832220262063 | 23.7167 | 0 | 3252.3 | 1469.73 | 0 | 154.33 | 1628.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026217400 |  | 100321282 |  | 6716212P | 2176779 | U461383 |  | 566 | EX | RETIRE 6"PLP SERVICE LINE | 2600B | WOODLAND | 301 WOODLAND AV | 067 | LEX | 2022-12-15 | U125936 | U461383 | 2022-08-11 | 2022-12-01 | 2022-12-01 | 2022-10-06 | LARRY BROWN | 2022-10-06 | 2022-10-06 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP2174 | AMRSL |  | 100 | 056632220262174 | 6.05 | 1 | 827.26 | 353.61 | 0 | 473.65 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026218800 |  |  |  | 6716208N | 2286833 | U461383 |  | 909 | EX | INSTALL MI WIRELESS UNIT | 2600E | SURFSIDE | 108 SURFSIDE DR | 067 | LEX | 2022-10-20 | U123258 | U461383 | 2022-08-17 | 2022-12-01 | 2022-12-01 | 2022-10-06 | CCOX | 2022-10-06 | 2022-09-06 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP2188 |  |  | 100 | 090932220262188 | 23.1 | 0 | 10259.75 | 1522.15 | 0 | 114.05 | 8588 | 0 | 35.55 | 0
KY | KY - WEST | 2621 | 22026228000 |  |  |  | 6724212N | 2292352 | U461383 |  | 557 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | 2621P | COSIMO | COSIMO | 067 | LEX | 2022-11-14 | U130992 | U461383 | 2022-09-28 | 2023-05-31 |  | 2022-09-21 | LSTANFI | 2022-10-06 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2280 |  |  | 100 | 055732220262280 | 0.18333 | 3 | 2032.93 | 1559.62 | 51.1 | 118.83 | 0 | 0 | 1.18 | 302.2 | 3
KY | KY - WEST | 2621 | 22026230100 |  |  |  | 6720208N | 2292657 | U461383 |  | 557 | EX | EMER-INSTALL 2' OF 2"PMMP | 2621P | 3533 COLT NECK | 3533 COLT NECK LN | 067 | LEX | 2022-12-06 | U134191 | U461383 | 2022-10-10 | 2022-10-06 | 2022-10-06 | 2022-10-06 | TANNER ROE | 2022-10-06 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2301 |  |  | 100 | 055732220262301 |  | 3 | 2249.75 | 1662.65 | 263.95 | 122.45 | 0 | 0 | 1.92 | 198.78 | 3
KY | KY - WEST | 2621 | 22026230200 |  |  |  | 6720208N | 2292657 | U461383 |  | 558 | EX | EMER-RETIRE 2' OF 2"PMP MAIN | 2621P | 3533 COLT NECK | 3533 COLT NECK LN | 067 | LEX | 2022-10-27 | U134191 | U461383 | 2022-10-10 | 2022-10-06 | 2022-10-06 | 2022-10-06 | TROE | 2022-10-06 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2302 |  |  | 100 | 055832220262302 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026230600 |  |  |  | 6688228A | 2292673 | U461383 |  | 557 | CO | EMER-INSTALL 5' OF 3"PMMP MAIN | 2621P | COLONIAL | 806 COLONIAL | 073 | FRA | 2024-04-24 |  | U461383 | 2022-10-10 | 2023-09-29 | 2024-05-10 |  | D COLLINS | 2022-10-06 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP2306 |  |  | 100 | 055732220262306 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026230700 |  |  |  | 6688228A | 2292673 | U461383 |  | 558 | CO | EMER-RETIRE 5' OF 3"PAMP MAIN | 2621P | COLONIAL | 806 COLONIAL | 073 | FRA | 2024-04-24 |  | U461383 | 2022-10-10 | 2023-09-29 | 2024-05-10 |  | D COLLINS | 2022-10-06 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP2307 |  |  | 100 | 055832220262307 |  | 0 | 12302.62 | 1589.05 | 0 | 2412.84 | 8300.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22123439500 |  | 100321282 |  | 6716212P | 2176779 | U461383 |  | 565 | EX | INSTALL 225' OF 2"PMMP S/L | 2600B | WOODLAND | 301 WOODLAND AV | 067 | LEX | 2022-12-22 | U461383 | U461383 | 2022-08-11 | 2022-12-01 | 2022-12-01 |  | LARRY BROWN | 2022-10-06 | 2022-10-06 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.5333 | 3 | 11630.23 | 788.66 | 0 | 309.88 | 10531.69 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129010900 |  | 100468225 |  | 7360252I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CENTER | 2508 CENTER ST | 019 | CAT | 2022-10-06 | U938684 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHARLES COMBS | 2022-10-06 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1733 | 0 | 0 | 0 | 1733 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129011000 |  | 100242082 |  | 7356252D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GREENUP | 954 GREENUP ST | 019 | CAT | 2022-10-06 | U938684 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHARLES COMBS | 2022-10-06 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 829.25 | 0 | 0 | 0 | 829.25 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129012400 |  | 100267446 |  | 7352260I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BUENA VISTA | 122 BUENA VISTA DR | 089 | ASH | 2022-10-07 | U938684 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHARLES COMBS | 2022-10-06 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129014800 |  | 500106736 |  | 7352256L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | STEWART | 312 STEWART AV | 089 | WOR | 2022-10-06 | U938684 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHARLES COMBS | 2022-10-06 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129014900 |  | 100258186 |  | 7348268N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WILSON | 170 WILSON ST | 089 | WOR | 2022-10-06 | U938684 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHARLES COMBS | 2022-10-06 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129020900 |  | 100358052 |  | 6740232J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 136 E MAIN ST | 017 | PAR | 2022-10-07 | U126603 | U130722 | 2022-09-05 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-10-06 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2141.76 | 0 | 0 | 0 | 2141.76 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129021800 |  | 100349908 |  | 6748204A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FRENCH | 213 FRENCH AV | 049 | WIN | 2022-10-07 | U127414 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ED FOX | 2022-10-06 | 2022-10-06 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.05 | 1 | 1173.93 | 122.7 | 0 | 25.11 | 1026.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129022000 |  | 100349533 |  | 6748208M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LEXINGTON | 118 E LEXINGTON AV | 049 | WIN | 2022-10-07 | U127414 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ED FOX | 2022-10-06 | 2022-10-06 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.3333 | 1 | 1346.13 | 140.62 | 0 | 28.78 | 1176.73 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129022300 |  | 100422659 |  | 6744208P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 50 S MAIN ST | 049 | WIN | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-06 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129022500 |  | 100349902 |  | 6748204A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MUDDY CREEK | 916 MUDDY CREEK RD | 049 | WIN | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-06 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129022600 |  | 100348202 |  | 6748208I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PENDLETON | 115 PENDLETON ST | 049 | WIN | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-06 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1984.56 | 0 | 0 | 0 | 1984.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129022700 |  | 100348714 |  | 6748208M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WASHINGTON | 225 E WASHINGTON ST | 049 | WIN | 2022-10-07 | U127414 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ED FOX | 2022-10-06 | 2022-10-06 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.55 | 1 | 1661.8 | 152.6 | 0 | 31.25 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129045800 |  | 100290366 |  | 6720212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ROSEMARY | 107 ROSEMARY AV | 067 | LEX | 2022-10-06 | U930915 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HMCKUNE | 2022-10-06 | 2022-10-06 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.7667 | 4 | 869.12 | 788.22 | 34.04 | 46.86 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129058300 |  | 100348708 |  | 6748208M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WASHINGTON | 201 E WASHINGTON ST | 049 | WIN | 2022-10-07 | U127414 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ED FOX | 2022-10-06 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.0667 | 1 | 1671.36 | 182.55 | 0 | 10.86 | 1477.95 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129071200 |  | 100245594 |  | 7360252I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CENTER | 2502 CENTER ST | 019 | CAT | 2022-10-06 | U938684 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHARLES COMBS | 2022-10-06 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129081000 |  | 100335233 |  | 6720212K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GLASS | 96 GLASS AV | 067 | LEX | 2022-10-07 | U930915 | U130722 | 2022-09-05 | 2022-12-30 |  |  | LSTANFI | 2022-10-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.5333 | 1 | 1637.71 | 162.3 | 22.84 | 34.11 | 1418.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129081900 |  | 500725551 |  | 6720212C | 0041696 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NEW CIRCLE | 234 E NEW CIRCLE RD | 067 | LEX | 2022-10-06 | LSTANFI | U130722 | 2022-09-05 | 2022-12-30 |  |  | LSTANFI | 2022-10-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.4167 | 1 | 1655.63 | 160.37 | 16.08 | 60.72 | 1418.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129121700 |  | 100288918 |  | 6724212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ENDON | 1821 ENDON DR | 067 | LEX | 2022-10-06 | WISHII | U125208 | 2022-09-06 | 2022-12-30 |  |  | WISHII | 2022-10-06 | 2022-10-06 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 23.3667 | 4 | 1730.82 | 1085.16 | 276.89 | 368.77 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129171100 |  | 100349366 |  | 6748208M |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2600B | FLANAGAN | 33 FLANAGAN ST | 049 | WIN | 2022-10-10 | U125208 | U125763 | 2022-09-06 | 2022-10-07 |  |  | DENNING | 2022-10-06 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 8.85 | 3 | 2211.3 | 548.19 | 511.79 | 32.62 | 1118.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22132381800 |  | 100242083 |  | 7356252D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | GREENUP | 954 GREENUP ST RR | 019 | CAT | 2022-10-06 | U938684 | U125208 | 2022-09-20 | 2022-12-30 | 2022-12-31 |  | CHARLES COMBS | 2022-10-06 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 255 | 0 | 0 | 0 | 255 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22136940400 |  | 100358054 |  | 6740232J |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | MAIN | 140 E MAIN ST | 017 | PAR | 2022-10-07 | U126603 | U125763 | 2022-10-05 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-10-06 | 2022-10-06 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.9167 | 1 | 354.68 | 294.35 | 0 | 60.33 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22136956700 |  | 100349896 |  | 6748204A |  |  |  | 565 | EX | REPLACE SERV LINE | 2621P | ELIZABETH | 41 ELIZABETH ST | 049 | WIN | 2022-10-07 | U123111 | U136097 | 2022-10-05 | 2022-10-05 |  |  | LYN STAFFORD | 2022-10-06 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 0.56667 | 1 | 3805.29 | 31.98 | 0 | 23.23 | 3750.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22999207700 |  | 500936239 |  | 6716216F | 0466634 |  |  | 566 | EX | PAPER ABANDON - 500931006* | 2621P | CAPSTONE | 2131< CAPSTONE DR | 067 | LEX | 2022-10-06 | TROE | U125208 | 2022-05-06 | 2022-12-30 |  |  | TROE | 2022-10-06 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10.8333 | 3 | 577.23 | 544.82 | 0 | 32.41 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18594168800 |  | 100294438 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - SOII/INSIDE | 2621P | LIMESTONE | 503< N LIMESTONE ST | 067 | LEX | 2022-10-07 | LSTONE | U125765 | 2018-03-13 | 2018-12-21 |  |  | LSTONE | 2022-10-07 | 2022-10-06 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 21.4167 | 7 | 952.29 | 898.87 | 0 | 53.42 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 20026930000 |  |  |  | 6744208H | 2177547 | U131983 |  | 587 | EX | UPGRADE ELECTRONICS | 2600M | TECH | 700 TECH DR | 049 | WIN | 2022-10-20 | U123258 | U131983 | 2020-02-20 | 2022-12-29 | 2022-12-31 | 2022-10-07 | JPASLEY | 2022-10-07 | 2022-07-13 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00587 | 3200587 |  |  | WP9300 |  |  | 100 | 058732200269300 | 13.7 | 2 | 4491.87 | 932.75 | 2704.09 | 203.58 | 0 | 0 | 90.14 | 561.31
KY | KY - CENTRAL | 2629 | 20026937200 |  |  |  | 6744208H | 2070106 | U131983 |  | 588 | EX | RETIRE ELECTRONICS | 2600M | TECH | 700 TECH DR | 049 | WIN | 2022-10-20 | U123258 | U131983 | 2020-03-12 | 2022-12-30 | 2022-12-31 | 2022-10-07 | JPASLEY | 2022-10-07 |  |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00588 | 3200588 |  |  | WP9372 |  |  | 100 | 058832200269372 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883091200 |  | 501147392 |  | 6720212L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WINCHESTER | 1314 WINCHESTER RD | 067 | LEX | 2022-10-10 | U131790 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | LSTONE | 2022-10-07 | 2022-09-01 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.9333 | 5 | 787.75 | 235.9 | 0 | 16.17 | 535.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883183100 |  | 500572998 |  | 6716212L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LIMESTONE | 319 S LIMESTONE ST | 067 | LEX | 2022-10-07 | LSTONE | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | LSTONE | 2022-10-07 | 2021-12-16 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.9333 | 8 | 1777.56 | 480.08 | 0 | 49.46 | 1248.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883201000 |  | 100335816 |  | 6720212K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | EASTLAND | 1225 EASTLAND DR | 067 | LEX | 2022-10-07 | U126602 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DEREK PAYTON | 2022-10-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 3777.74 | 433.72 | 0 | 25.78 | 3318.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883317900 |  | 500836742 |  | 6716212L | 0355200 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LIMESTONE | 129 N LIMESTONE ST LT | 067 | LEX | 2022-10-07 | LSTONE | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | LSTONE | 2022-10-07 | 2022-09-07 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.2667 | 4 | 377.33 | 102.33 | 0 | 7.16 | 267.84 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916435400 |  | 100264002 |  | 7352260O | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 1920 MAIN ST W | 019 | ASH | 2022-10-07 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-10-07 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2119.47 | 0 | 0 | 0 | 2119.47 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959034200 |  | 100315353 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | CRESCENT | 1113 CRESCENT AV | 067 | LEX | 2022-10-07 | U461322 | U134723 | 2021-12-10 | 2022-10-07 |  |  | STEVE CANOY | 2022-10-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.4667 | 1 | 2175.7 | 415.75 | 0 | 304.16 | 1455.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959043600 |  | 100315355 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | CRESCENT | 1201 CRESCENT AV | 067 | LEX | 2022-10-07 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-10-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2563.08 | 451.31 | 0 | 96.34 | 2015.43 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026185001 |  |  |  | 6716208A | 2069466 | U461383 |  | 561 | EX | INSTALL 260' OF 2"PMMP MAIN | 2600B | CLAYS MILL | 1602 CLAYS MILL RD | 067 | LEX | 2022-10-19 | U128132 | U461383 | 2022-10-07 | 2022-10-10 | 2022-10-15 | 2022-10-05 | CORY TINCHER | 2022-10-07 | 2022-10-05 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP1850 |  |  | 100 | 056132220261850 | 41 | 1140 | 30483.21 | 2239.25 | 1031.92 | 272.15 | 24230.59 | 0 | 35.12 | 2674.18 | 228
KY | KY - WEST | 2623 | 22026213400 |  |  |  | 6700212I | 2290280 | U461383 |  | 583 | EX | INSTALL NEW 1" REGULATORS | 2623M | LEXINGTON | 488 LEXINGTON RD | 239 | VER | 2022-11-17 | U123258 | U461383 | 2022-07-21 | 2022-12-01 | 2022-12-01 | 2022-10-07 | BLONE | 2022-10-07 | 2022-10-07 |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00583 | 3200583 |  |  | WP2134 |  |  | 100 | 058332220262134 | 27.0667 | 28 | 2234.49 | 1910.1 | 0 | 113.63 | 0 | 0 | 2.19 | 208.57
KY | KY - WEST | 2623 | 22026213500 |  |  |  | 6700212I | 2290280 | U461383 |  | 584 | EX | RETIRE REGULATORS | 2623M | LEXINGTON | 488 LEXINGTON RD | 239 | VER | 2022-11-17 | U123258 | U461383 | 2022-07-21 | 2022-12-01 | 2022-12-01 | 2022-10-07 | BLONE | 2022-10-07 | 2022-09-29 |  | F | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00584 | 3200584 |  |  | WP2135 |  |  | 100 | 058432220262135 | 12.6167 | 0 | 856.14 | 810.21 | 0 | 45.93 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22117364100 |  | 100346892 |  | 6696212K | 1635077 |  |  | 565 | EX | AOC SERVICE LINE ENCROACHMENT | 2623D | SAINT CLAIR | 131 SAINT CLAIR ST | 239 | VER | 2022-10-10 | U131790 | AOC SYST | 2022-07-20 | 2022-08-19 | 2022-09-18 |  | DCOLLIN | 2022-10-07 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0 | 1 | 3100.9 | 0 | 405.08 | 0 | 2695.82 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129012300 |  | 500400340 |  | 7348260H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BELLEFONTE | 225 BELLEFONTE CR | 089 | ASH | 2022-10-07 | U938684 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHARLES COMBS | 2022-10-07 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129014600 |  | 100258244 |  | 7348268M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 3RD | 309 3RD AV | 089 | WOR | 2022-10-07 | U938684 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHARLES COMBS | 2022-10-07 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129022400 |  | 500039484 |  | 6744204D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 399 S MAIN ST | 049 | WIN | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-07 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 4238.25 | 0 | 0 | 0 | 4238.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129057800 |  | 500180116 |  | 6744204C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | AL FAN | 217 AL FAN CT | 049 | WIN | 2022-10-07 | U127414 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ED FOX | 2022-10-07 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.55 | 1 | 1867.31 | 212.42 | 0 | 12.64 | 1642.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129057900 |  | 100349720 |  | 6744204D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CENTRAL | 28 CENTRAL AV | 049 | WIN | 2022-10-10 | U127414 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ED FOX | 2022-10-07 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.9333 | 1 | 2091.32 | 236.39 | 0 | 48.37 | 1806.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129117300 |  | 100335220 |  | 6720212K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GLASS | 74 GLASS AV | 067 | LEX | 2022-10-20 | U126602 | U125208 | 2022-09-06 | 2022-12-30 |  |  | DEREK PAYTON | 2022-10-07 | 2022-10-03 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.4833 | 1 | 3035.5 | 154.18 | 0 | 30.89 | 2850.43 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22136487600 |  | 100302734 |  | 6712212N |  |  |  | 565 | EX | SERVICE LINE - REPLACE 10/07 | 2621P | STANDISH | 1261 STANDISH WY | 067 | LEX | 2022-10-12 | U128711 | U125208 | 2022-10-03 | 2049-12-31 |  |  | JOCHOA | 2022-10-07 | 2022-10-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.7833 | 4 | 1684.9 | 1477.15 | 0 | 87.85 | 119.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22136920100 |  | 100311539 |  | 6712204D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311023 | 2621P | HALIFAX | 607 HALIFAX DR | 067 | LEX | 2022-10-07 | U930915 | U125208 | 2022-10-05 | 2022-10-07 | 2022-10-26 |  | ABLAKE | 2022-10-07 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 31.4333 | 5 | 1998.25 | 1467.71 | 325.55 | 87.29 | 117.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22137228000 |  | 100297572 |  | 6716212H |  |  |  | 565 | EX | LEAK REPAIR -S.L.GR 1 D311075 | 2621P | 3RD | 556 W 3RD ST | 067 | LEX | 2022-10-10 | U930915 | U125208 | 2022-10-06 | 2022-10-06 | 2022-10-06 |  | LSTANFI | 2022-10-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.3833 | 1 | 3851.08 | 412.3 | 142.09 | 86.69 | 3210 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22137483000 |  | 500043434 |  | 6744208J |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | STAMPER | 3459 STAMPER DR | 049 | WIN | 2022-10-07 | U127414 | U125763 | 2022-10-07 | 2022-12-30 |  |  | ED FOX | 2022-10-07 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.0167 | 1 | 1786.45 | 119.71 | 0 | 24.49 | 1642.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22137503700 |  | 100351734 |  | 6744208O |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | LEXINGTON | 702 W LEXINGTON AV | 049 | WIN | 2022-10-31 | U125881 | U125763 | 2022-10-07 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-07 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22137530900 |  | 100351817 |  | 6744208O |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | FULTON | 102 FULTON AV | 049 | WIN | 2022-10-26 | U125881 | U125763 | 2022-10-07 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-07 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22137543300 |  | 100332078 |  | 6720212N |  |  |  | 565 | EX | REPLACE SL | 2621P | AURORA | 730 AURORA AV | 067 | LEX | 2022-10-07 | U126308 | U132823 | 2022-10-07 | 2022-10-07 |  |  | J ENSMINGER | 2022-10-07 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.75 | 1 | 1898.78 | 211.16 | 0 | 12.55 | 1675.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 08737624300 |  | 100336139 |  | V-1021-61 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MONTGOMERY | 686 MONTGOMERY AV | 067 | LEX | 2022-10-12 | U126602 | SSUTHER | 2008-06-30 | 2022-07-01 | 2022-12-31 |  | DEREK PAYTON | 2022-10-10 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2637.72 | 0 | 0 | 0 | 2637.72 | 0 | 0 | 0
KY | KY - WEST | 2623 | 12965303700 |  | 100281317 |  | 6712228B |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | MAIN | 245 W MAIN ST 2FL | 209 | GEO | 2022-10-24 | U125559 | U124967 | 2012-04-16 | 2017-12-29 |  |  | JUSTIN HOBBS | 2022-10-10 | 2022-07-25 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 6.0167 | 2 | 402.12 | 380.61 | 0 | 21.51 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 12965324700 |  | 100281318 |  | 6712228B |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | MAIN | 245 W MAIN ST 2F | 209 | GEO | 2022-10-24 | U125559 | U124967 | 2012-04-16 | 2017-12-29 |  |  | JUSTIN HOBBS | 2022-10-10 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2621 | 21026126800 |  |  |  | 6720212N | 2180410 | U461383 |  | 557 | EX | INSTALL 11,170' OF 2"/6"PMMP | 2600B | MENTELLE | MENTELLE PR | 067 | LEX | 2022-12-01 | U128132 | U461383 | 2021-06-08 | 2022-12-30 | 2022-12-31 | 2022-08-15 | J ENSMINGER | 2022-10-10 | 2022-02-21 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP1268 | AMRCB |  | 100 | 055732210261268 | 2220.1833 | 2707168 | 1672773.41 | 140038.84 | 51052.73 | 35850.88 | 1198450.72 | 0 | 9423.41 | 237956.83 | 10916
KY | KY - WEST | 2621 | 21026126900 |  |  |  | 6720212N | 2180410 | U461383 |  | 558 | EX | RETIRE 9000' OF 4"/6"BSLP MAIN | 2600B | MENTELLE | MENTELLE PR | 067 | LEX | 2022-11-03 | U128132 | U461383 | 2021-06-08 | 2023-10-31 | 2024-06-21 | 2022-10-10 | J ENSMINGER | 2022-10-10 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP1269 | AMRCB |  | 100 | 055832210261269 |  | 0 | 24.95 | 0 | 24.95 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883147700 |  | 100344089 |  | NEW |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MOOREFIELD | 858 MOOREFIELD RD | 181 | CAR | 2022-10-19 | U461383 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-10-10 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.5167 | 1 | 1148.22 | 339.22 | 0 | 67.94 | 741.06 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883198700 |  | 100248408 |  | 7356256J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | BLACKBURN | 3725 BLACKBURN AV | 019 | ASH | 2022-11-23 | U125566 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DESKAGG | 2022-10-10 | 2021-08-20 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 18.1833 | 3 | 5392.72 | 973.27 | 0 | 68.88 | 4350.57 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883254000 |  | 100271156 |  | NEW |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | PIQUA KENTONTO | 2975 PIQUA KENTONTO RD | 201 | MT | 2022-10-19 | U461383 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-10-10 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2964.24 | 0 | 0 | 0 | 2964.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883311300 |  | 100316607 |  | 6716208G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NICHOLASVILLE | 1851 NICHOLASVILLE RD | 067 | LEX | 2022-10-10 | U127206 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-10-10 | 2022-07-08 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.2333 | 3 | 3784.79 | 689.01 | 0 | 40.2 | 3055.58 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21884195100 |  | 100344099 |  | NEW |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SUGAR CREEK | 3590 SUGAR CREEK RD | 181 | CAR | 2022-10-19 | U461383 | U128293 | 2021-02-04 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-10-10 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.4833 | 1 | 926.13 | 154.18 | 0 | 30.89 | 741.06 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916435500 |  | 100265048 |  | 7352260O | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2001 MAIN ST W W | 019 | ASH | 2022-10-10 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-10-10 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2546.33 | 0 | 0 | 0 | 2546.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958595500 |  | 100331927 |  | 6720212N | 2180410 | U134723 |  | 565 | EX | REPLACE SL W/21-0261268-00 | 2600B | ASHLAND | 195 N ASHLAND AV | 067 | LEX | 2022-10-10 | U129722 | U134723 | 2021-12-08 | 2022-12-30 |  |  | M YOUNG | 2022-10-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2055.35 | 0 | 104.98 | 0 | 1950.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959034000 |  | 100315297 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | CRESCENT | 1107 CRESCENT AV | 067 | LEX | 2022-10-10 | U461423 | U134723 | 2021-12-10 | 2022-12-30 |  |  | KKOUNS | 2022-10-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2139.84 | 450.25 | 0 | 326.02 | 1363.57 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129012500 |  | 100254396 |  | 7348264K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LEXINGTON | 1512 LEXINGTON AV | 089 | FLA | 2022-10-11 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-10 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129012700 |  | 100254464 |  | 7348264J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MARTIN | 1609 MARTIN ST | 089 | FLA | 2022-10-11 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-10 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129014700 |  | 500649763 |  | 7344268P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MCCLOUD | 913 MCCLOUD DR | 089 | WOR | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RAY HAYDEN | 2022-10-10 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129015000 |  | 100257641 |  | 7344268M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WURTLAND | 212 WURTLAND AV | 089 | WUR | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RAY HAYDEN | 2022-10-10 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129022900 |  | 100286230 |  | 6756176I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | IRVINE | 1290 S IRVINE RD | 065 | IRV | 2022-10-12 | U938684 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHARLES COMBS | 2022-10-10 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 3038.83 | 0 | 0 | 0 | 3038.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129043200 |  | 500816372 |  | 6720208E | 0355441 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ROMANY | 300 ROMANY RD CABLE | 067 | LEX | 2022-10-19 | U461383 | U130722 | 2022-09-05 | 2022-10-10 |  |  | RSTRONG | 2022-10-10 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.3167 | 1 | 1056.08 | 129.53 | 16.08 | 55.37 | 855.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129047500 |  | 100295206 |  | 6716212H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | JEFFERSON | 466 JEFFERSON ST | 067 | LEX | 2022-10-12 | U123111 | U130722 | 2022-09-05 | 2022-12-30 |  |  | LYN STAFFORD | 2022-10-10 | 2022-10-10 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 19.3167 | 3 | 7617.43 | 1084.57 | 0 | 787.58 | 5745.28 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129058800 |  | 100286238 |  | 6764172G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SPARKS | 100 SPARKS AV | 065 | IRV | 2022-10-12 | U938684 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHARLES COMBS | 2022-10-10 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2231 | 0 | 0 | 0 | 2231 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129064100 |  | 100271154 |  | NEW |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | R1 | R1 | 201 | MT | 2022-10-10 | U126604 | U130722 | 2022-09-05 | 2022-12-30 |  |  | WILL FULKS | 2022-10-10 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 741.06 | 0 | 0 | 0 | 741.06 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129121800 |  | 100288489 |  | 6720212D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ROOKWOOD | 468 ROOKWOOD PY | 067 | LEX | 2022-10-10 | MCRAIG | U125208 | 2022-09-06 | 2022-12-30 |  |  | MCRAIG | 2022-10-10 | 2022-09-30 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 20.15 | 4 | 1652.69 | 995.09 | 290.47 | 367.13 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22134728800 |  | 500377152 |  | 6684228I | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER | 2623D | RIVER BEND | 1054 RIVER BEND RD | 073 | FRA | 2022-10-10 | DCOLLIN | AOC SYST | 2022-09-26 | 2022-10-10 | 2022-11-22 |  | DCOLLIN | 2022-10-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 10.0333 | 1 | 3120.72 | 634.3 | 208.7 | 453.9 | 1823.82 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22135664800 |  | 100274749 |  | 6684228J |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | 3RD | 323 W 3RD ST 2F | 073 | FRA | 2022-10-10 | DCOLLIN | U132002 | 2022-09-29 | 2022-10-12 | 2022-10-28 |  | DCOLLIN | 2022-10-10 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.033333 | 1 | 3.26 | 1.91 | 0 | 1.35 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22135666300 |  | 100274751 |  | 6684228J |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | 3RD | 323 W 3RD ST WH | 073 | FRA | 2022-10-11 | U930915 | U132002 | 2022-09-29 | 2022-10-12 | 2022-10-28 |  | DCOLLIN | 2022-10-10 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.35 | 1 | 1848.61 | 22.12 | 92.65 | 15.84 | 1718 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22135666600 |  | 100274750 |  | 6684228J |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | 3RD | 323 W 3RD ST 1F | 073 | FRA | 2022-10-10 | DCOLLIN | U132002 | 2022-09-29 | 2022-10-12 | 2022-10-28 |  | DCOLLIN | 2022-10-10 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.083333 | 1 | 9.75 | 5.68 | 0 | 4.07 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22136705700 |  | 100323672 |  | 6716204C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D304938 | 2621P | BROOKHAVEN | 3415 BROOKHAVEN DR | 067 | LEX | 2022-10-10 | ABLAKE | U136097 | 2022-10-04 | 2022-10-07 | 2022-10-25 |  | ABLAKE | 2022-10-10 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.1 | 4 | 1509.76 | 1052.6 | 325.27 | 62.59 | 69.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22137746400 |  | 100357067 |  | 7248280G | 1313373 |  |  | 565 | EX | REPLACE SL | 2621P | HIGHLAND | 3023 HIGHLAND DR | 161 | MAY | 2022-10-10 | SDADAMS | U132823 | 2022-10-08 | 2022-10-10 |  |  | SDADAMS | 2022-10-10 | 2022-10-10 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 | 16.8833 | 2 | 1561.7 | 1016.46 | 412.22 | 60.42 | 72.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22137949700 |  | 100285820 |  | 6764172D |  |  |  | 566 | EX | LEGACY ABN | 2621P | STEVENS | 125 STEVENS AV | 065 | IRV | 2022-10-11 | U127414 | U126286 | 2022-10-10 | 2022-10-10 | 2022-12-31 |  | ED FOX | 2022-10-10 | 2022-10-10 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26290043 | 3.05 | 1 | 1622.49 | 182.5 | 0 | 37.35 | 1402.64 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22137950200 |  | 100459796 |  | 6764176K |  |  |  | 566 | EX | LEGACY ABN | 2621P | WINCHESTER | 1003 WINCHESTER RD APT 12 | 065 | IRV | 2022-10-11 | U127414 | U126286 | 2022-10-10 | 2022-10-10 | 2022-12-31 |  | ED FOX | 2022-10-10 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26290043 | 3.05 | 1 | 1835.6 | 182.5 | 0 | 10.85 | 1642.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22138541500 |  | 100285289 |  | 6764176O |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | CHURCH | 112 CHURCH ST | 065 | IRV | 2022-10-12 | U938684 | U125763 | 2022-10-12 | 2022-12-30 |  |  | CHARLES COMBS | 2022-10-10 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22138541600 |  | 100285287 |  | 6764176O |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | CHURCH | 116 CHURCH ST | 065 | IRV | 2022-10-12 | U938684 | U125763 | 2022-10-12 | 2022-12-30 |  |  | CHARLES COMBS | 2022-10-10 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979020100 |  | 100251074 |  | 7340268E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WINIFRED | 1317 WINIFRED ST | 089 | GRE | 2022-10-26 | U125881 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | RAY HAYDEN | 2022-10-10 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979020300 |  | 100251311 |  | 7340268T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ASHLAND | 2113 ASHLAND RD | 089 | GRE | 2022-10-26 | U125881 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | HERBERT HAYDEN | 2022-10-10 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 255 | 0 | 0 | 0 | 255 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979021400 |  | 100254297 |  | 7348264N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PATTERSON | 1400 PATTERSON ST | 089 | FLA | 2022-10-11 | U125881 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | HERBERT HAYDEN | 2022-10-10 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983421100 |  | 100324765 |  | 6720204A | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 1100 GREENTREE CT | 067 | LEX | 2022-10-10 | U129731 | U134723 | 2022-03-03 | 2022-12-30 |  |  | F.GOINS | 2022-10-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1173.52 | 0 | 0 | 0 | 1173.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983421200 |  | 100324766 |  | 6720204A | 2184517 |  |  | 565 | EX | REPLACE SL W/21-0261512-00 | 2600B | GREENTREE | 1104 GREENTREE CT | 067 | LEX | 2022-10-10 | U129731 | U134723 | 2022-03-03 | 2022-12-30 |  |  | F.GOINS | 2022-10-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 998.14 | 0 | 0 | 0 | 998.14 | 0 | 0 | 0
KY | KY - WEST | 2621 | 98349506100 |  | 500024959 |  | V-930/38 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NICHOLASVILLE | 1641 NICHOLASVILLE RD | 067 | LEX | 2022-10-10 | U127206 | TDORTEN | 1998-06-09 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-10-10 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1731.88 | 0 | 0 | 0 | 1731.88 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 17569845500 |  | 100270803 | 09 | 6736248A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ELMARCH | 519 S ELMARCH AV | 097 | CYN | 2022-10-11 | U127414 | PMCNABB | 2017-12-27 | 2019-12-31 |  |  | ED FOX | 2022-10-11 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.05 | 1 | 1694.63 | 242.38 | 0 | 49.61 | 1402.64 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 20026992600 |  |  |  | 6740232I | 2075121 | U128885 |  | 558 | EX | RETIRE MP MAIN | 2600B | RUCKER | RUCKER ST | 017 | PAR | 2022-11-14 | U128132 | U128885 | 2020-12-23 | 2023-12-29 | 2023-12-31 | 2022-09-14 | LYN STAFFORD | 2022-10-11 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP9926 | AMRCB |  | 100 | 055832200269926 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21026140700 |  |  |  | 6748208I | 2075093 | U128885 |  | 558 | EX | RETIRE 2,200' - CSMP | 2600B | MAPLE | N MAPLE ST | 049 | WIN | 2022-10-13 | U132783 | U128885 | 2021-09-09 | 2022-12-30 | 2022-12-31 | 2022-09-20 | SHAWN DENNIS | 2022-10-11 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP1407 | AMRCB |  | 100 | 055832210261407 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21883146100 |  | 100271134 |  | 7360 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | DAY | 8103 DAY PK | 161 | MAY | 2022-10-11 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-10-11 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 5.5167 | 1 | 1518.75 | 339.22 | 0 | 67.94 | 1111.59 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916434400 |  | 100264054 |  | 7356256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | LINDA | 736 LINDA LN | 019 | ASH | 2022-10-11 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-10-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2469.98 | 0 | 0 | 0 | 2469.98 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026174400 |  |  |  | 6724208E | 2286833 | U126783 |  | 909 | EX | 2022 SCADA VISIBILITY PROGRAM | 2600E | WOODWARD | 600 WOODWARD LN REAR | 067 | LEX | 2022-10-31 | U123258 | U126783 | 2022-03-07 | 2022-10-25 | 2022-11-30 | 2022-10-11 | AJPARKS | 2022-10-11 | 2022-05-10 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3201029 |  |  | WP1744 | SCADA |  | 100 | 102932220261744 | 23.75 | 0 | 28643.37 | 1666.47 | 0 | 733.77 | 26153.44 | 0 | 89.69 | 0
KY | KY - WEST | 2621 | 22026183700 |  | 500414716 |  | 6712204D | 2288473 | U461383 |  | 555 | EX | INSTALL 100' OF 2"PMMP MAIN | 2621P | FRASERDALE | 3405 FRASERDALE DR | 067 | LEX | 2022-12-23 | U128132 | U461383 | 2022-04-28 | 2022-11-01 | 2022-11-04 | 2022-10-11 | KKINDER | 2022-10-11 | 2022-09-22 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP1837 |  |  | 100 | 055532220261837 | 133.0833 | 3980 | 19814.52 | 8519.58 | 1028.47 | 801.03 | 7473.96 | 0 | 20.77 | 1970.71 | 199
KY | KY - WEST | 2621 | 22026223100 |  |  |  | 6708200A | 2291477 | U461383 |  | 557 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | 2621P | CAMBRIDGE | 109 CAMBRIDGE LN | 113 | NIC | 2022-12-07 | U128132 | U461383 | 2022-09-09 | 2023-05-30 | 2023-05-31 | 2022-03-07 | RJCRAWF | 2022-10-11 | 2022-10-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2231 |  |  | 100 | 055732220262231 | 8.1167 | 6 | 4059.84 | 3187.13 | 117.75 | 182.15 | 0 | 0 | -2.03 | 574.84 | 3
KY | KY - WEST | 2623 | 22118373600 |  | 100282090 |  | 6712232O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303130 | 2621P | BOURBON | 600 BOURBON ST | 209 | GEO | 2022-10-11 | DCOLLIN | U125208 | 2022-07-25 | 2022-10-11 | 2024-07-31 |  | DCOLLIN | 2022-10-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.6 | 1 | 2806.22 | 165.07 | 285.27 | 118.03 | 2237.85 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22118974900 |  | 100282985 |  | 6712228B | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER | 2623D | CLAYTON | 205 CLAYTON AV | 209 | GEO | 2022-10-11 | DCOLLIN | AOC SYST | 2022-07-27 | 2022-08-26 | 2022-09-25 |  | DCOLLIN | 2022-10-11 | 2022-09-20 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 5.2833 | 2 | 2712.38 | 333.11 | 233.6 | 240.17 | 1905.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22124654800 |  | 100280895 |  | 6684228H |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTRQD | 2621P | MAIN | 485 E MAIN ST | 073 | FRA | 2022-10-11 | U930915 | U132002 | 2022-08-17 | 2022-08-31 | 2022-09-16 |  | CHERNDO | 2022-10-11 | 2022-09-30 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8.5 | 5 | 1270.62 | 494.39 | 0 | 29.23 | 747 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127057200 |  | 100332979 |  | 6728196T |  |  |  | 566 | EX | ABANDON SL - DEMO/LNDBK | 2621P | OLD RICHMOND | 7641 OLD RICHMOND RD | 067 | LEX | 2022-10-13 | U125208 | U125208 | 2022-08-26 | 2022-08-31 | 2022-09-25 |  | HMCKUNE | 2022-10-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 20.5 | 4 | 976.74 | 921.91 | 0 | 54.83 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22127322600 |  | 100284016 |  | 6712228N | 2291102 |  |  | 566 | EX | RETIRE S/L W/22-0262204-00 | 2621P | LEXINGTON | 1189 LEXINGTON RD | 209 | GEO | 2022-10-11 | CHERNDO | U461383 | 2022-08-29 | 2022-09-30 | 2022-09-30 |  | CHERNDO | 2022-10-11 | 2022-09-08 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 38.7667 | 9 | 8807.97 | 2775.43 | 0 | 154.96 | 5877.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22128474600 |  | 500588948 |  | 6712216H |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | DEERFIELD | 285 DEERFIELD LN | 067 | LEX | 2022-10-11 | U127206 | U125763 | 2022-09-01 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-10-11 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 2305.11 | 426.66 | 0 | 25.38 | 1853.07 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129005900 |  | 100360060 |  | 6740232M | 0783353 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 730 MAIN ST | 017 | PAR | 2022-11-03 | U125208 | U130722 | 2022-09-05 | 2022-12-30 | 2022-12-31 |  | CHARLES COMBS | 2022-10-11 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - CENTRAL | 2629 | 22129007400 |  | 100270889 |  | 6736248A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SPRINGDALE | 202 SPRINGDALE AV | 097 | CYN | 2022-10-11 | U127414 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ED FOX | 2022-10-11 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.45 | 1 | 1963.04 | 266.29 | 0 | 54.5 | 1642.25 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129009700 |  | 100268176 |  | 7356256B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WINCHESTER | 2317 WINCHESTER AV RR APTS | 019 | ASH | 2022-11-14 | U125208 | U130722 | 2022-09-05 | 2022-10-11 |  |  | DESKAGG | 2022-10-11 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.53333 | 1 | 1044.29 | 31.63 | 0 | 6.66 | 1006 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129010000 |  | 100262323 |  | 7352256G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | IROQUOIS | 2689 IROQUOIS AV | 019 | ASH | 2022-11-14 | U125208 | U130722 | 2022-09-05 | 2022-10-11 |  |  | DESKAGG | 2022-10-11 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.2167 | 1 | 3290.91 | 183.87 | 0 | 38.74 | 3068.3 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129012800 |  | 100252516 |  | 7348264P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MARY ELLEN | 1707 MARY ELLEN DR | 089 | FLA | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RAY HAYDEN | 2022-10-11 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129012900 |  | 100252504 |  | 7348264P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | POWELL | 621 POWELL LN | 089 | FLA | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-11 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129013200 |  | 100250416 |  | 7340264B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PLUM GROVE | 236 PLUM GROVE RD | 089 | GRE | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RAY HAYDEN | 2022-10-11 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129013400 |  | 100251047 |  | 7340268E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WINIFRED | 1106 WINIFRED ST | 089 | GRE | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RAY HAYDEN | 2022-10-11 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129023500 |  | 100270890 |  | 6736248A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WEBSTER | 210 WEBSTER AV | 097 | CYN | 2022-10-17 | U126285 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DDAVIS | 2022-10-11 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 1890.43 | 460.42 | 0 | 27.37 | 1402.64 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129023600 |  | 100269040 |  | 6736252M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WILSON | 213 WILSON AV | 097 | CYN | 2022-10-11 | U126285 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DDAVIS | 2022-10-11 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1617.87 | 0 | 0 | 0 | 1617.87 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129035300 |  | 100254732 |  | 7348260C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BELLEFONTE | 737 BELLEFONTE RD | 089 | FLA | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RAY HAYDEN | 2022-10-11 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1420 | 0 | 0 | 0 | 1420 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129037500 |  | 100251064 |  | 7340268E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WINIFRED | 1001 WINIFRED ST | 089 | GRE | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RAY HAYDEN | 2022-10-11 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129046300 |  | 100296666 |  | 6716212C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DOUGLAS | 411 DOUGLAS AV | 067 | LEX | 2022-10-13 | U930915 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RSTRONG | 2022-10-11 | 2022-10-04 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.9167 | 2 | 1241.8 | 284.77 | 0 | 101.93 | 855.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129046400 |  | 100300487 |  | 6716212G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DRISCOLL | 246 DRISCOLL ST | 067 | LEX | 2022-10-13 | U930915 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RSTRONG | 2022-10-11 | 2022-10-04 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.45 | 4 | 1699.74 | 734.62 | 0 | 110.02 | 855.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129056800 |  | 100358368 |  | 6740232I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ELIZABETH | 318 ELIZABETH ST | 017 | PAR | 2022-10-11 | U126603 | U130722 | 2022-09-05 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-10-11 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9.5 | 1 | 2486.09 | 567.2 | 0 | 33.73 | 1885.16 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129056900 |  | 100358375 |  | 6740232I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ELIZABETH | 220 ELIZABETH ST | 017 | PAR | 2022-10-11 | U126603 | U130722 | 2022-09-05 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-10-11 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2897.26 | 0 | 0 | 0 | 2897.26 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129058500 |  | 100453256 |  | 6764176P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HOOD | 215 HOOD AV 6 | 065 | IRV | 2022-10-11 | U127414 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ED FOX | 2022-10-11 | 2022-10-10 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 12.4 | 2 | 2447.23 | 723.74 | 0 | 81.24 | 1642.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129059000 |  | 100445772 |  | X120640 | 1855957 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 826 MAIN ST 1F | 065 | RAV | 2022-10-11 | U938684 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHARLES COMBS | 2022-10-11 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 3340.05 | 0 | 0 | 0 | 3340.05 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129091000 |  | 100280066 |  | 6688228N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WESTLAND | 316 WESTLAND DR | 073 | FRA | 2022-10-11 | DCOLLIN | U130722 | 2022-09-05 | 2022-10-11 |  |  | DCOLLIN | 2022-10-11 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.45 | 1 | 1867.8 | 28.46 | 1.54 | 20.36 | 1817.44 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129118300 |  | 500346482 |  | 7348260B | 9404108 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | REED | 3021 REED ST | 089 | FLA | 2022-10-26 | U125881 | U125208 | 2022-09-06 | 2022-12-30 |  |  | RAY HAYDEN | 2022-10-11 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129125100 |  | 100284020 |  | 6712228N | 2291102 |  |  | 566 | EX | RETIRE S/L W/22-0262204-00 | 2621P | LEXINGTON | 1221 LEXINGTON RD | 209 | GEO | 2022-10-11 | CHERNDO | U461383 | 2022-09-06 | 2022-09-30 | 2022-10-01 |  | CHERNDO | 2022-10-11 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.26667 | 2 | 13.46 | 12.71 | 0 | 0.75 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129125600 |  | 100284017 |  | 6712228N | 2291102 |  |  | 566 | EX | RETIRE S/L W/22-0262204-00 | 2621P | LEXINGTON | 1175 LEXINGTON RD | 209 | GEO | 2022-10-11 | CHERNDO | U461383 | 2022-09-06 | 2022-09-30 | 2022-10-01 |  | CHERNDO | 2022-10-11 | 2022-09-08 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 4.0333 | 3 | 189.79 | 178.23 | 1.54 | 10.02 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22133780900 |  | 100270950 |  | 6736248E |  |  |  | 565 | EX | SERVICE LINE REPLACE D097402 | 2621P | NEW LAIR | 819 NEW LAIR RD | 097 | CYN | 2022-10-11 | U930915 | U136526 | 2022-09-22 | 2022-09-23 | 2022-10-13 |  | NRICHIE | 2022-10-11 | 2022-10-10 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 18.7667 | 6 | 2545.99 | 1153.85 | 332.91 | 305.73 | 753.5 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22134641400 |  | 100240882 |  | 7352156L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 639 E MAIN ST | 119 | HIN | 2022-10-12 | U930915 | U125208 | 2022-09-26 | 2022-09-29 | 2022-10-17 |  | BPREECE | 2022-10-11 | 2022-10-10 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 10.15 | 3 | 675.73 | 637.8 | 0 | 37.93 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22134915300 |  | 100276826 |  | 6684228D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 1ST | 818 1ST AV | 073 | FRA | 2022-10-11 | DCOLLIN | U130722 | 2022-09-27 | 2022-10-11 |  |  | DCOLLIN | 2022-10-11 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.3 | 1 | 894.6 | 18.96 | 3.08 | 13.56 | 859 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22136131800 |  | 100313876 |  | 6716212N |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | SOUTHERN | 1323 SOUTHERN AV | 067 | LEX | 2022-10-11 | MCRAIG | U132002 | 2022-09-30 | 2022-10-13 | 2022-10-29 |  | MCRAIG | 2022-10-11 | 2022-10-10 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.8 | 4 | 919.89 | 398.52 | 168.79 | 352.58 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22138227400 |  | 100465248 |  | 6764176P |  |  |  | 565 | EX | REPLACE SL | 2621P | HOOD | 215 HOOD AV 5 | 065 | IRV | 2022-10-12 | U123111 | U124960 | 2022-10-11 | 2049-12-31 |  |  | LYN STAFFORD | 2022-10-11 | 2022-10-11 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26290032 | 8.1167 | 2 | 5926.73 | 455.58 | 0 | 330.85 | 5140.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22138236100 |  | 100324478 |  | 6720204E |  |  |  | 565 | EX | SERVICE LINE - REPLACE D311179 | 2621P | OLYMPIA | 3565 OLYMPIA RD | 067 | LEX | 2022-10-13 | U125208 | U129939 | 2022-10-11 | 2022-10-11 | 2022-10-11 |  | WISHII | 2022-10-11 | 2022-10-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.1167 | 2 | 1070.8 | 604.65 | 157.54 | 256.91 | 51.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22138255100 |  | 500716340 |  | 6712216D |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | JESSICA | 500 JESSICA CR | 067 | LEX | 2022-10-11 | U127206 | U125763 | 2022-10-11 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-10-11 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1731.88 | 0 | 0 | 0 | 1731.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22138292800 |  | 100324403 |  | 6720204E |  |  |  | 565 | EX | SERVICE LINE - REPLACE D311112 | 2621P | MILANO | 3519 MILANO RD | 067 | LEX | 2022-10-12 | U125208 | U129939 | 2022-10-11 | 2022-10-11 | 2022-10-11 |  | RJCRAWF | 2022-10-11 | 2022-10-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.4833 | 3 | 1372.89 | 850.05 | 418.4 | 50.54 | 53.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22138310800 |  | 501281360 |  | 6764180P |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | DRY BRANCH | 484 DRY BRANCH RD | 065 | IRV | 2022-10-20 | U938684 | U125763 | 2022-10-11 | 2022-12-30 |  |  | CHARLES COMBS | 2022-10-11 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 3579.66 | 0 | 0 | 0 | 3579.66 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979016200 |  | 100241511 |  | 7356256B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CARTER | 2543 CARTER AV A | 019 | ASH | 2022-10-11 | U125566 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | DESKAGG | 2022-10-11 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.25 | 1 | 2357.95 | 244.21 | 0 | 51.44 | 2062.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23220799600 |  | 100322713 |  | 6720208A | 2286046 |  |  | 565 | EX | RPLC SL/22026162101 | 2600B | TATES CREEK | 1482 TATES CREEK RD | 067 | LEX | 2023-10-12 | U126530 | U125763 | 2023-10-12 | 2023-12-29 |  |  | JDUNN | 2022-10-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3275.59 | 0 | 0 | 0 | 3275.59 | 0 | 0 | 0
KY | KY - WEST | 2621 | 03533830200 |  | 100332694 |  | 6720212I | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAIN | 337 E MAIN ST | 067 | LEX | 2022-10-12 | U930915 | DMCCULL | 2003-03-17 | 2022-07-01 | 2022-12-31 |  | HMCKUNE | 2022-10-12 | 2022-10-11 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.5667 | 7 | 414.73 | 342.98 | 0 | 71.75 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916434900 |  | 100265052 |  | 7352260O | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 1913 MAIN ST W W | 019 | ASH | 2022-10-12 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-10-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2230.89 | 0 | 0 | 0 | 2230.89 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916435100 |  | 100264001 |  | 7352260O | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 1916 MAIN ST W | 019 | ASH | 2022-10-12 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-10-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2005.28 | 0 | 0 | 0 | 2005.28 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916435600 |  | 100264003 |  | 7352260O | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2004 MAIN ST W | 019 | ASH | 2022-10-12 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-10-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1760.77 | 0 | 0 | 0 | 1760.77 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960237900 |  | 100321000 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | MAXWELL | 413 E MAXWELL ST 1F | 067 | LEX | 2022-10-12 | U461375 | U134723 | 2021-12-17 | 2022-12-30 |  |  | LARRY BROWN | 2022-10-12 | 2022-10-11 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 3675.06 | 471.77 | 0 | 327.3 | 2875.99 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026194600 |  |  |  | 6752176B | 2289196 | U122858 |  | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2621M | HWY 977 | HWY 977 | 151 | WAC | 2022-11-09 | U123258 | U136124 | 2022-06-01 | 2022-12-30 | 2022-12-31 | 2022-10-12 | WSHIMFESSEL | 2022-10-12 | 2022-10-12 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00909 | 3200909 |  |  | WP1946 |  |  | 100 | 090932220261946 | 7.1833 | 0 | 4024.88 | 258.16 | 0 | 15.35 | 3718.3 | 0 | 33.07 | 0
KY | KY - CENTRAL | 2629 | 22026194700 |  |  |  | 6752176B | 2289196 | U122858 |  | 910 | EX | RETIRED ELECTRONIC EXCHANGE | 2621M | HWY 977 | HWY 977 | 151 | WAC | 2022-11-09 | U123258 | U136124 | 2022-06-01 | 2022-12-30 | 2022-12-31 | 2022-10-12 | WSHIMFESSEL | 2022-10-12 |  |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00910 | 3200910 |  |  | WP1947 |  |  | 100 | 091032220261947 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129007300 |  | 100270826 |  | 6736248A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ELMARCH | 522 S ELMARCH AV | 097 | CYN | 2022-10-12 | U938684 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHARLES COMBS | 2022-10-12 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129009600 |  | 100244043 |  | 7356256J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SUMMIT | 2024 SUMMIT ST | 019 | ASH | 2022-11-14 | U125208 | U130722 | 2022-09-05 | 2022-10-12 |  |  | DESKAGG | 2022-10-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.7333 | 1 | 1980.75 | 98.84 | 0 | 20.81 | 1861.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129010400 |  | 500302292 |  | 7348256N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | STATE RT 5 | 6227 STATE RT 5 | 019 | ASH | 2022-11-14 | U125208 | U130722 | 2022-09-05 | 2022-10-12 |  |  | DESKAGG | 2022-10-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.5167 | 1 | 1098.59 | 201.13 | 0 | 42.36 | 855.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129012600 |  | 100255296 |  | 7348264K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAPLE | 1206 MAPLE ST | 089 | FLA | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RAY HAYDEN | 2022-10-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129013700 |  | 100256683 |  | 7348264B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | VINE | 844 VINE ST | 089 | RAC | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RAY HAYDEN | 2022-10-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129013800 |  | 100240025 |  | 7352264E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BEECH | 412 BEECH ST | 089 | RUS | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RAY HAYDEN | 2022-10-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129023100 |  | 100269197 |  | 6736252M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CHURCH | 240 N CHURCH ST | 097 | CYN | 2022-10-12 | U127414 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ED FOX | 2022-10-12 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.0667 | 1 | 2101.72 | 182.51 | 0 | 37.35 | 1881.86 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129023300 |  | 100270745 |  | 6736252M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PIKE | 451 E PIKE ST | 097 | CYN | 2022-10-12 | U127414 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ED FOX | 2022-10-12 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.0667 | 1 | 1862.11 | 182.51 | 0 | 37.35 | 1642.25 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129027300 |  | 100243835 |  | 7356256K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | AKERS | 1409 AKERS ST | 019 | ASH | 2022-11-14 | U125208 | U130722 | 2022-09-05 | 2022-10-12 |  |  | DESKAGG | 2022-10-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.75 | 1 | 1652.09 | 159.75 | 0 | 33.64 | 1458.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129043500 |  | 100408088 |  | 6716208J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NICHOLASVILLE | 2191 NICHOLASVILLE RD | 067 | LEX | 2022-10-13 | U930915 | U130722 | 2022-09-05 | 2022-10-12 |  |  | RSTRONG | 2022-10-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.2167 | 1 | 1112.41 | 180.26 | 0 | 77.05 | 855.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129045900 |  | 100338391 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SHELBY | 559 SHELBY ST | 067 | LEX | 2022-10-13 | U930915 | U130722 | 2022-09-05 | 2022-10-12 |  |  | RSTRONG | 2022-10-12 | 2022-10-10 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.0167 | 2 | 1025.49 | 117.4 | 0 | 52.99 | 855.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129056400 |  | 100357497 |  | 6740232M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 8TH | 812 E 8TH ST | 017 | PAR | 2022-10-18 | U126603 | U130722 | 2022-09-05 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-10-12 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.35 | 1 | 1647.06 | 140.34 | 0 | 28.77 | 1477.95 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129056600 |  | 100359580 |  | 6736232P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BOURBON | 1905 BOURBON LN | 017 | PAR | 2022-10-13 | U126603 | U130722 | 2022-09-05 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-10-12 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.9333 | 1 | 1624.52 | 235.86 | 0 | 48.32 | 1340.34 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129057500 |  | 100357603 |  | 6740232M |  |  |  | 566 | EX | ABANDON SL - IDLE/CONVERSION | 2621P | VINE | 630 VINE ST | 017 | PAR | 2022-10-12 | U126603 | U130722 | 2022-09-05 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-10-12 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.7167 | 1 | 2072.72 | 280.65 | 0 | 57.52 | 1734.55 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129059200 |  | 100269192 |  | 6736252M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CHURCH | 236 N CHURCH ST | 097 | CYN | 2022-10-12 | U938684 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHARLES COMBS | 2022-10-12 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129059300 |  | 100269229 |  | 6736252M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CHURCH | 229 N CHURCH ST DN | 097 | CYN | 2022-10-12 | U938684 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHARLES COMBS | 2022-10-12 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129059400 |  | 100269242 |  | 6736252M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CHURCH | 207 N CHURCH ST | 097 | CYN | 2022-10-12 | U938684 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHARLES COMBS | 2022-10-12 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129059700 |  | 100268956 |  | 6736252M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | VINE | 110 VINE ST | 097 | CYN | 2022-11-16 | U938684 | U130722 | 2022-09-05 | 2022-12-30 |  |  | 1HARLES COMBS | 2022-10-12 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129086200 |  | 500012312 |  | 6720216I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ZOELLER | 1097< ZOELLER CT | 067 | LEX | 2022-10-14 | U127206 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-10-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 4147.21 | 426.66 | 0 | 25.38 | 3695.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22136722100 |  | 100407389 |  | 6720216E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE SERVICE | 2621D | RITTENHOUSE | 1860 RITTENHOUSE CT | 067 | LEX | 2022-10-14 | U125208 | AOC SYST | 2022-10-04 | 2022-11-03 | 2022-12-03 |  | RJCRAWF | 2022-10-12 | 2022-10-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 16.8 | 4 | 1041.28 | 804.06 | 189.41 | 47.81 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22138275700 |  | 100315979 |  | 6716208F |  |  |  | 565 | EX | SERVICE LINE - REPLACE D310250 | 2621P | SUBURBAN | 129 SUBURBAN CT | 067 | LEX | 2022-10-24 | U130722 | U129939 | 2022-10-11 | 2022-10-11 | 2022-10-11 |  | HMCKUNE | 2022-10-12 | 2022-10-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.9833 | 6 | 1577.62 | 1108.37 | 371.43 | 65.92 | 31.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22138551800 |  | 100345153 |  | 6696212G |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | FRANKFORT | 181 FRANKFORT ST | 239 | VER | 2022-10-12 | DCOLLIN | U129939 | 2022-10-12 | 2022-10-12 |  |  | DCOLLIN | 2022-10-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.66667 | 1 | 2532.54 | 44.26 | 351.5 | 31.66 | 2105.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22138609200 |  | 100438593 |  | 6732252P |  |  |  | 566 | EX | ABANDON | 2621P | PLEASANT | 209 W PLEASANT ST | 097 | CYN | 2022-10-12 | U938684 | U124960 | 2022-10-12 | 2049-12-31 |  |  | CHARLES COMBS | 2022-10-12 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2710.22 | 0 | 0 | 0 | 2710.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22138622700 |  | 100289854 |  | 6720212D |  |  |  | 565 | EX | SERVICE LINE - REPLACE D311340 | 2621P | SIERRA | 359 SIERRA DR | 067 | LEX | 2022-10-14 | U125208 | U129939 | 2022-10-12 | 2022-10-12 | 2022-10-12 |  | KKINDER | 2022-10-12 | 2022-10-12 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.05 | 2 | 2171.55 | 1168.07 | 575.37 | 369.81 | 58.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22138634300 |  | 100270628 |  | 6736248A |  |  |  | 566 | EX | ABANDON SL | 2621P | WEBSTER | 311 WEBSTER AV A | 097 | CYN | 2022-10-17 | U127414 | U126286 | 2022-10-12 | 2022-10-12 | 2022-12-31 |  | ED FOX | 2022-10-12 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26290043 | 9.8667 | 2 | 3030.73 | 592.41 | 474.31 | 82.15 | 1881.86 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979022100 |  | 100256702 |  | 7348264B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | VINE | 901 VINE ST | 089 | RAC | 2022-10-26 | U125881 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | RAY HAYDEN | 2022-10-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979022700 |  | 100258455 |  | 7344264D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CHESTNUT | 2 CHESTNUT ST | 089 | RAC | 2022-10-26 | U125881 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | RAY HAYDEN | 2022-10-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2621 | 02497595300 |  | 100332646 |  | 6720212M | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAIN | 489 E MAIN ST | 067 | LEX | 2022-10-14 | U930915 | DMCCULL | 2002-02-14 | 2022-07-01 | 2022-12-31 |  | HMCKUNE | 2022-10-13 | 2022-10-11 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 25.8667 | 9 | 1179.9 | 1113.64 | 0 | 66.26 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 03528737600 |  | 100442016 |  | 6716212L | 1315787 |  |  | 566 | EX | ABANDON SL - SOII/INSIDE | 2621P | MAXWELL | 311 W MAXWELL ST FR | 067 | LEX | 2022-10-14 | U125208 | DMCCULL | 2003-01-24 | 2003-12-31 | 2005-01-01 |  | HMCKUNE | 2022-10-13 | 2022-09-07 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.8333 | 5 | 147.67 | 139.57 | 0 | 8.1 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11908240800 |  | 100300540 |  | 6716212G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY*SEE F10* | 2621P | HIGH *F10 NEEDS ARRG* | 1032 W HIGH *F10 NEEDS ARRG* ST | 067 | LEX | 2022-10-14 | U125208 | U906631 | 2011-05-25 | 2022-07-01 | 2022-12-31 |  | RJCRAWF | 2022-10-13 | 2022-09-14 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 37.35 | 9 | 2052.15 | 1938.93 | 1.63 | 111.59 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18594262000 |  | 500012709 |  | 6720212N |  |  |  | 566 | EX | ABANDON SL - SOII/INSIDE | 2621P | SHERMAN **MNFLD** | 179 SHERMAN **MNFLD** AV RR | 067 | LEX | 2022-10-13 | U930915 | U125765 | 2018-03-14 | 2018-12-21 |  |  | LSTANFI | 2022-10-13 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.0167 | 2 | 356.97 | 300.73 | 0 | 56.24 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18594262500 |  | 100322070 |  | 6716212P |  |  |  | 566 | EX | ABANDON SL - SOII/INSIDE | 2621P | COLUMBIA | 457 COLUMBIA AV | 067 | LEX | 2022-10-13 | U930915 | U125765 | 2018-03-14 | 2018-12-21 |  |  | LSTANFI | 2022-10-13 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.8167 | 2 | 214.78 | 173.56 | 0 | 41.22 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21026111600 |  |  |  | 7256276J | 2178491 | GSULLI1 |  | 577 | EX | INSTALL FENCE | 2632M | MAPLE LEAF | MAPLE LEAF RD | 161 | MAY | 2022-12-21 | U125936 | GSULLI1 | 2021-03-22 | 2023-12-28 | 2023-12-31 | 2022-10-13 | JMARTIN | 2022-10-13 | 2022-09-02 |  | F | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00577 | 3200577 |  |  | WP1116 |  |  | 100 | 057732210261116 | 17 | 2 | 21225.79 | 1123.05 | 0 | 62.67 | 16763.9 | 0 | 62.07 | 3214.1
KY | KY - CENTRAL | 2629 | 21026119200 |  |  |  | 6760248M | 2070683 | U124399 |  | 559 | CO | PM- LAKE CARNICO REPLACEMENT | 5320E | LAKESHORE | LAKESHORE RD | 181 | CAR | 2022-12-27 |  | U124399 | 2021-04-28 | 2021-12-29 | 2021-12-31 | 2022-10-13 | SWBISHOP | 2022-10-13 |  |  | C | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00559 | 3201013 |  |  | WP1192 | KSMRP |  | 100 | 101332210261192 |  | 165 | 3041283.83 | -23796.11 | 969039.63 | 39429.66 | 1638836.06 | 0 | 50389.78 | 367384.81 | 165
KY | KY - CENTRAL | 2629 | 21026119300 |  |  |  | 6760248M | 2070683 | U124399 |  | 560 | CO | PM- LAKE CARNICO ABANDONMENT | 5320E | LAKESHORE | LAKESHORE RD | 181 | CAR | 2022-12-29 |  | U124399 | 2021-04-28 | 2021-12-29 | 2021-12-31 | 2022-10-13 | SWBISHOP | 2022-10-13 |  |  | C | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00560 | 3201014 |  |  | WP1193 | KSMRP |  | 100 | 101432210261193 |  | 0 | 729097.27 | 66535.07 | 497919.85 | 197.55 | 164444.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883068400 |  | 100347519 |  | 6744208L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 4TH | 28 4TH ST | 049 | WIN | 2022-10-13 | U461443 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WGRAVES | 2022-10-13 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.45 | 1 | 2337.44 | 184.69 | 0 | 10.99 | 2141.76 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883134600 |  | 100441433 |  | 6744208K |  |  |  | 566 | VO | ABANDON SL - PEND CN/OFL 10-3 | 2621P | ARLINGTON | 10 ARLINGTON RD | 049 | WIN | 2022-10-14 |  | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-10-13 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - CENTRAL | 2629 | 21883241400 |  | 100349171 |  | 6748208N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BROADWAY | 502 E BROADWAY ST A | 049 | WIN | 2022-10-13 | U126308 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-10-13 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1940.77 | 0 | 0 | 0 | 1940.77 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883270200 |  | 100350253 |  | 6744208P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BOONE | 132 BOONE AV | 049 | WIN | 2022-10-13 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-10-13 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883297100 |  | 100352284 |  | 6744208K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CAROLINA | 313 CAROLINA AV | 049 | WIN | 2022-10-13 | U126308 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-10-13 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883301700 |  | 500583560 |  | 6748204B | 9504879 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BUFFALO TRACE | 230 BUFFALO TRACE | 049 | WIN | 2022-10-13 | U126308 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-10-13 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916434700 |  | 100265056 |  | 7352260O | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 1901< MAIN ST W UPST | 019 | ASH | 2022-10-13 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-10-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2375.54 | 0 | 0 | 0 | 2375.54 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916453100 |  | 100265053 |  | 7352260O | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 1905 MAIN ST WW | 019 | ASH | 2022-10-13 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-10-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2497.4 | 0 | 0 | 0 | 2497.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960238100 |  | 100320999 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | MAXWELL | 415 E MAXWELL ST | 067 | LEX | 2022-10-13 | U126309 | U134723 | 2021-12-17 | 2022-12-30 |  |  | JAMIE LYNN | 2022-10-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2796.17 | 0 | 0 | 0 | 2796.17 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22026228900 |  |  |  | 7348260G | 2292082 | U132280 |  | 561 | EX | EMER - INSTALL 40'-2" PMIP | 2600B | TONI | TONI DR | 089 | RUS | 2023-01-19 | U132280 | U132280 | 2022-10-04 | 2023-01-16 | 2023-01-25 | 2022-10-13 | MBLANKE/CJH C PACK | 2022-10-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00561 | 3200561 |  |  | WP2289 |  |  | 100 | 056132220262289 | 8 | 88 | 37570.14 | 3985.64 | 0 | 2317.2 | 28039.24 | 0 | 30.04 | 3198.02 | 88
KY | KY - EAST | 2631 | 22026229000 |  |  |  | 7348260G | 2292082 | U132280 |  | 562 | EX | EMER - RETIRE 40'-2" PIP | 2600B | TONI | TONI DR | 089 | RUS | 2023-01-19 | U128132 | U132280 | 2022-10-04 | 2023-01-25 | 2023-01-25 | 2022-10-13 | MBLANKE/CJH C PACK | 2022-10-13 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00562 | 3200562 |  |  | WP2290 |  |  | 100 | 056232220262290 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22114176300 |  | 100312956 |  | 6716208E | 1635077 |  |  | 565 | EX | AOC ENCHROACHMENT*PLANT* | 2621P | CLAYS MILL | 2200 CLAYS MILL RD | 067 | LEX | 2022-10-13 | U930915 | U125208 | 2022-07-06 | 2022-07-29 | 2022-08-29 |  | LSTANFI | 2022-10-13 | 2022-08-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 28.55 | 10 | 3929.14 | 1665.87 | 201.17 | 122.9 | 1939.2 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129013600 |  | 100256740 |  | 7352260O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HOWLAND | 614 HOWLAND AV | 089 | RAC | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RAY HAYDEN | 2022-10-13 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129014100 |  | 100249117 |  | 7328284F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 721 MAIN ST | 089 | S S | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RAY HAYDEN | 2022-10-13 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129014200 |  | 100249080 |  | 7328284B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MORTON | 89 MORTON ST | 089 | S S | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RAY HAYDEN | 2022-10-13 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129014300 |  | 100251766 |  | 7328284B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RIDGE | 188 RIDGE ST | 089 | S S | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RAY HAYDEN | 2022-10-13 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129014400 |  | 100267680 |  | 7328284K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | STATE RT 784 | 536 STATE RT 784 | 089 | S S | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RAY HAYDEN | 2022-10-13 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 2280.5 | 0 | 0 | 0 | 2280.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129014500 |  | 100249061 |  | 7348264K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WHEELER | 79 WHEELER ST | 089 | S S | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RAY HAYDEN | 2022-10-13 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129027100 |  | 100241770 |  | 7356256P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 49TH | 335 49TH ST 1 | 019 | ASH | 2022-10-13 | U125566 | U130722 | 2022-09-05 | 2022-10-13 |  |  | DESKAGG | 2022-10-13 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.3667 | 1 | 1924 | 135.05 | 0 | 28.45 | 1760.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129027200 |  | 100264372 |  | 7356260M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 9TH | 513 9TH ST | 019 | ASH | 2022-10-13 | DESKAGG | U130722 | 2022-09-05 | 2022-10-13 |  |  | DESKAGG | 2022-10-13 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.66667 | 1 | 1304.11 | 38.49 | 0 | 8.12 | 1257.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129056500 |  | 100360504 |  | 6736228D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 19TH | 141 W 19TH ST FRONT | 017 | PAR | 2022-10-13 | U126603 | U130722 | 2022-09-05 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-10-13 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.3833 | 1 | 2273.67 | 322.43 | 0 | 66.08 | 1885.16 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129056700 |  | 100360329 |  | 6736228D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CLIFTON | 1924 CLIFTON AV | 017 | PAR | 2022-10-13 | U126603 | U130722 | 2022-09-05 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-10-13 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.6167 | 1 | 2472.69 | 274.65 | 0 | 56.28 | 2141.76 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129064300 |  | 100446930 |  | 7356256A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 12TH | 711 12TH ST | 019 | ASH | 2022-11-14 | U125208 | U130722 | 2022-09-05 | 2022-10-13 |  |  | DESKAGG | 2022-10-13 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.76667 | 1 | 2457.9 | 44.24 | 0 | 9.32 | 2404.34 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129064500 |  | 100258810 |  | 7356256G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 28TH | 616 28TH ST | 019 | ASH | 2022-10-26 | U125566 | U130722 | 2022-09-05 | 2022-10-13 |  |  | DESKAGG | 2022-10-13 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.2333 | 1 | 2628.35 | 185.02 | 0 | 38.99 | 2404.34 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129075800 |  | 100267671 |  | 7328284J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | STATE RT 784 | 827 STATE RT 784 | 089 | S S | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RAY HAYDEN | 2022-10-13 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129075900 |  | 100249048 |  | 7348264K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WHEELER | 40 WHEELER ST | 089 | S S | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RAY HAYDEN | 2022-10-13 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129084000 |  | 100337756 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ELM TREE | 658 ELM TREE LN | 067 | LEX | 2022-10-13 | U127206 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-10-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 3054.17 | 426.66 | 0 | 25.38 | 2602.13 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129120800 |  | 100348323 |  | 6748208I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WINN | 218 WINN AV | 049 | WIN | 2022-10-13 | U461443 | U125208 | 2022-09-06 | 2022-12-30 |  |  | WGRAVES | 2022-10-13 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.55 | 1 | 3494.87 | 190.05 | 0 | 11.31 | 3293.51 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129126000 |  | 100284019 |  | 6712228N | 2291102 |  |  | 566 | EX | RETIRE S/L W/22-0262204-00 | 2621P | LEXINGTON | 1191 LEXINGTON RD | 209 | GEO | 2022-10-13 | U930915 | U461383 | 2022-09-06 | 2022-09-30 | 2022-10-01 |  | CHERNDO | 2022-10-13 | 2022-10-11 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 4.8333 | 3 | 263.85 | 249.04 | 0 | 14.81 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129126200 |  | 500119516 |  | 6712228N | 2291102 |  |  | 566 | EX | RETIRE S/L W/22-0262204-00 | 2621P | LEXINGTON | 1191 LEXINGTON RD RR | 209 | GEO | 2022-10-24 | U126332 | U461383 | 2022-09-06 | 2022-09-30 | 2022-10-01 |  | CHERNDO | 2022-10-13 | 2022-09-09 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 27.35 | 4 | 2256.29 | 1256.36 | 0 | 70.93 | 929 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22135003300 |  | 500970954 |  | 6716204B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | REYNOLDS | 103 E REYNOLDS RD A | 067 | LEX | 2022-10-14 | U125208 | U130722 | 2022-09-27 | 2022-12-30 |  |  | LSTANFI | 2022-10-13 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.8833 | 2 | 214.37 | 174.75 | 0 | 39.62 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22136402500 |  | 100410755 |  | 6688228L |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | TIMBERLAWN | 39 TIMBERLAWN CR | 073 | FRA | 2022-10-13 | CHERNDO | U125208 | 2022-10-03 | 2022-10-07 | 2022-10-07 |  | CHERNDO | 2022-10-13 | 2022-10-07 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 19.6333 | 4 | 1961.77 | 1002.27 | 49.47 | 59.63 | 850.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22138548100 |  | 100413490 |  | 6720204E |  |  |  | 565 | EX | GRADE 1 LEAK REPAIR | 2621P | ARMSTRONG MILL | 1125 ARMSTRONG MILL RD | 067 | LEX | 2022-10-14 | U930915 | U129939 | 2022-10-12 | 2022-10-12 | 2022-10-12 |  | TROE | 2022-10-13 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 26.7167 | 6 | 1999.29 | 1483.77 | 375.58 | 88.24 | 51.7 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22138551500 |  | 100279661 |  | 6688228O |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | WHIPPORWILL | 333 WHIPPORWILL LN | 073 | FRA | 2022-10-13 | DCOLLIN | U129939 | 2022-10-12 | 2022-10-12 |  |  | DCOLLIN | 2022-10-13 | 2022-10-12 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 16.5833 | 2 | 6068.49 | 1046.64 | 280.02 | 748.27 | 3993.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22138610700 |  | 100293879 |  | 6720212A |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | KEES | 1105 KEES RD | 067 | LEX | 2022-10-14 | U125208 | U129939 | 2022-10-12 | 2022-10-12 |  |  | HMCKUNE | 2022-10-13 | 2022-10-12 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 43.1333 | 6 | 2368.83 | 1902.19 | 277.65 | 113.09 | 75.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22138922900 |  | 100336397 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL W CAP JOB | 2600B | 4TH | 136 E 4TH ST | 067 | LEX | 2022-10-13 | U126602 | U125763 | 2022-10-13 | 2022-12-30 |  |  | DEREK PAYTON | 2022-10-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3020.68 | 0 | 0 | 0 | 3020.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22138923500 |  | 100336398 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL W/CAP JOB | 2600B | 4TH | 142 E 4TH ST 1 | 067 | LEX | 2022-10-14 | U126602 | U125763 | 2022-10-13 | 2022-12-30 |  |  | DEREK PAYTON | 2022-10-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4543.09 | 0 | 0 | 0 | 4543.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22138966200 |  | 500023446 |  | 6720204I |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311115 | 2621P | TANBARK | 1181 TANBARK RD | 067 | LEX | 2022-11-14 | U125208 | U136097 | 2022-10-13 | 2022-10-13 | 2022-10-13 |  | ABLAKE | 2022-10-13 | 2022-10-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 15.2167 | 4 | 1253.57 | 988.92 | 205.81 | 58.84 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979041300 |  | 100348492 |  | 6748208K |  |  |  | 566 | EX | ABANDON SL - CN/CGI 08-23-22 | 2621P | CENTER | 214 CENTER DR | 049 | WIN | 2022-10-13 | U938684 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | CHARLES COMBS | 2022-10-13 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2710.22 | 0 | 0 | 0 | 2710.22 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979051600 |  | 500215989 |  | 7348244H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | STATE RT 3117 | 509 STATE RT 3117 | 089 | S S | 2022-10-26 | U125881 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | RAY HAYDEN | 2022-10-13 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 2120 | 0 | 0 | 0 | 2120 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979053900 |  | 500595171 |  | 7328284D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CHRISTOPHER | 84 CHRISTOPHER DR | 089 | S S | 2022-10-26 | U125881 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | RAY HAYDEN | 2022-10-13 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1929.25 | 0 | 0 | 0 | 1929.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23154578400 |  | 500327594 |  | 6748208N |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | BROADWAY | 502 E BROADWAY ST B | 049 | WIN | 2023-01-13 | U125559 | U125763 | 2023-01-10 | 2023-12-29 |  |  | J ENSMINGER | 2022-10-13 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - CENTRAL | 2629 | 21883051700 |  | 100348661 |  | 6748208M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | JACKSON | 216 JACKSON ST | 049 | WIN | 2022-10-14 | U126308 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-10-14 | 2022-10-04 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.36667 | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883093900 |  | 100432518 |  | 6744204B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | COLBY | 813 COLBY RD | 049 | WIN | 2022-10-14 | U938684 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-10-14 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1566.95 | 0 | 0 | 0 | 1566.95 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883150700 |  | 100245919 |  | 7356256B |  |  |  | 565 | EX | RERUN ABN SL - OFL/OS 10-05-22 | 2621P | 25TH | 412 25TH ST | 019 | CAT | 2022-10-14 | U125566 | U120245 | 2021-01-30 | 2022-10-14 | 2022-12-31 |  | DESKAGG | 2022-10-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 6.6167 | 1 | 7085.76 | 378.09 | 0 | 79.65 | 6628.02 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916435000 |  | 100265051 |  | 7352260O | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 1915 MAIN ST W W | 019 | ASH | 2022-10-14 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-10-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2272.56 | 0 | 0 | 0 | 2272.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916435300 |  | 100265050 |  | 7352260O | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 1917 MAIN ST W W | 019 | ASH | 2022-10-14 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-10-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2198.69 | 0 | 0 | 0 | 2198.69 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129034500 |  | 100241959 |  | 7344168K |  |  |  | 566 | VO | ABANDON SL - IDLE/INACTIVE | 2600B | EVERGREEN | 55 N EVERGREEN LN | 071 | LNC | 2022-10-17 |  | U130722 | 2022-09-05 | 2022-12-30 |  |  | ASHEPHE | 2022-10-14 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - EAST | 2631 | 22129038400 |  | 100243451 |  | 7328284B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 1ST | 453 E 1ST AV | 089 | S S | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RAY HAYDEN | 2022-10-14 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129038500 |  | 100413483 |  | 7328284B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 1ST | 479 E 1ST AV | 089 | S S | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RAY HAYDEN | 2022-10-14 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129038600 |  | 100251778 |  | 7328284B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 2ND | 46 W 2ND AV | 089 | S S | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RAY HAYDEN | 2022-10-14 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129038800 |  | 100249144 |  | 7328284B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 544 MAIN ST | 089 | S S | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RAY HAYDEN | 2022-10-14 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129045000 |  | 100291880 |  | 6720216K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LISA | 617 LISA CT | 067 | LEX | 2022-10-14 | HMCKUNE | U130722 | 2022-09-05 | 2022-12-30 |  |  | HMCKUNE | 2022-10-14 | 2022-09-29 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 31.4667 | 9 | 1479.43 | 1352.2 | 47.2 | 80.03 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129057000 |  | 100434707 |  | 6736228J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LEXINGTON | 4145 LEXINGTON RD | 017 | PAR | 2022-10-14 | U126603 | U130722 | 2022-09-05 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-10-14 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.45 | 1 | 2389.97 | 205.99 | 0 | 42.22 | 2141.76 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129057400 |  | 500329832 |  | 6736228K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PARK PLACE | 160 PARK PLACE CT | 017 | PAR | 2022-10-14 | U126603 | U130722 | 2022-09-05 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-10-14 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.55 | 1 | 2212.5 | 271.66 | 0 | 55.68 | 1885.16 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129075600 |  | 100249269 |  | 7328284B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | JAMES HANNAH | 436 JAMES HANNAH DR | 089 | S S | 2022-10-26 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RAY HAYDEN | 2022-10-14 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22138237800 |  | 100293823 |  | 6720212A |  |  |  | 565 | EX | SERVICE LINE - REPLACE / RLA | 2621P | MCCLAIN | 908 MCCLAIN DR | 067 | LEX | 2022-10-17 | U125208 | U125208 | 2022-10-11 | 2022-10-14 |  |  | RSTRONG | 2022-10-14 | 2022-10-13 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.5167 | 2 | 3012.88 | 589.7 | 104.3 | 252.06 | 2066.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22138926000 |  | 100324860 |  | 6720204A |  |  |  | 565 | EX | GRADE 1 REPLACE | 2621P | GAINESWAY | 1134 GAINESWAY DR | 067 | LEX | 2022-10-14 | U930915 | U129939 | 2022-10-13 | 2022-10-13 | 2022-10-13 |  | LSTANFI | 2022-10-14 | 2022-10-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25.2 | 7 | 1575.75 | 1228.43 | 201.85 | 87.17 | 58.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22138945000 |  | 100352296 |  | 6744208K |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | CAROLINA | 306 CAROLINA AV | 049 | WIN | 2022-10-14 | U461443 | U129939 | 2022-10-13 | 2022-10-13 |  |  | WGRAVES | 2022-10-14 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 8 | 1 | 3710.43 | 428.24 | 329.89 | 25.47 | 2926.83 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22139097600 |  | 100347098 |  | 6696212J |  |  |  | 565 | EX | SERVICE LINE REPLACE D308869 | 2621P | M L KING JR | 824 M L KING JR CT | 239 | VER | 2022-10-14 | DCOLLIN | U134852 | 2022-10-14 | 2023-04-13 | 2024-10-31 |  | DCOLLIN | 2022-10-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.15 | 1 | 4407.81 | 202.4 | 289.52 | 144.67 | 3771.22 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22139098000 |  | 100281948 |  | 6712232O |  |  |  | 566 | EX | SERVICE LINE - ABANDONMENT | 2621P | MAIN | 443 MAIN AV | 209 | GEO | 2022-10-17 | U125208 | U134852 | 2022-10-14 | 2022-10-14 |  |  | DCOLLIN | 2022-10-14 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26230043 | 2.5667 | 1 | 1254.87 | 161.28 | 123.2 | 115.29 | 855.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22139111400 |  | 500026635 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL W/21-0269978-00 | 2600B | 4TH | 141 E 4TH ST 2F | 067 | LEX | 2022-10-14 | U126602 | U125763 | 2022-10-14 | 2022-12-30 |  |  | DEREK PAYTON | 2022-10-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 6179.65 | 0 | 0 | 0 | 6179.65 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979041100 |  | 100348168 |  | 6748208I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | COOK | 242 COOK AV | 049 | WIN | 2022-10-14 | U938684 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | CHARLES COMBS | 2022-10-14 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1566.95 | 0 | 0 | 0 | 1566.95 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 20026982100 |  | 501299856 |  | 7252276G | 2075188 | U122858 |  | 555 | EX | INSTALL 800'-2" PMIP | 2600B | CLARKS RUN | 725 CLARKS RUN RD MIDDLE | 161 | MAY | 2022-10-24 | U128132 | U122858 | 2020-10-19 | 2022-10-19 | 2022-11-01 | 2022-10-17 | DAVID STAGGS | 2022-10-17 | 2022-10-10 |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00555 | 3200555 |  |  | WP9821 |  |  | 100 | 055532200269821 | 64 | 7136 | 69244.93 | 3452.98 | 2236.35 | 205.37 | 56940.99 | 0 | 64.92 | 6344.32 | 892
KY | KY - WEST | 2621 | 21026151200 |  |  |  | 6720204B | 2184517 | U122858 |  | 561 | EX | INSTALL 2065'-2"&6" PMMP | 2600B | GREENTREE | GREENTREE | 067 | LEX | 2023-01-20 | U133347 | U122858 | 2021-11-17 | 2022-09-13 | 2022-11-30 | 2022-08-29 | JDUNN | 2022-10-17 | 2022-02-09 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP1512 |  |  | 100 | 056132210261512 | 1476.45 | 360288 | 493527.08 | 93154.57 | 6704.75 | 15959.39 | 307450.35 | 0 | 1555.33 | 68702.69 | 2224
KY | KY - WEST | 2621 | 21026151300 |  |  |  | 6720204B | 2184517 | U122858 |  | 562 | EX | RETIRE 2111'-2"&6" CSMP | 2600B | GREENTREE | GREENTREE | 067 | LEX | 2022-11-09 | U133347 | U122858 | 2021-11-17 | 2022-11-30 | 2022-11-30 | 2022-10-12 | JDUNN | 2022-10-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP1513 |  |  | 100 | 056232210261513 |  | 0 | 80 | 0 | 0 | 0 | 80 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883060400 |  | 500313936 |  | 6740204H | 9402647 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | PRIMROSE | 105 PRIMROSE LN | 049 | WIN | 2022-10-18 | U129722 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-10-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883094100 |  | 100349950 |  | 6744204D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAIN | 335 S MAIN ST | 049 | WIN | 2022-10-17 | U126286 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | TYLER ALLISON | 2022-10-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883134700 |  | 100348397 |  | 6748208J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SPICER | 107 SPICER RD | 049 | WIN | 2022-10-17 | U127414 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | ED FOX | 2022-10-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.3833 | 1 | 2136.94 | 323.15 | 0 | 66.11 | 1747.68 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883190600 |  | 500694139 |  | 6712232K | 9830429 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BEVELED GLASS | 113 BEVELED GLASS LN | 209 | GEO | 2022-10-18 | U127206 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-10-17 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8 | 1 | 2330.74 | 426.66 | 0 | 25.38 | 1878.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883205900 |  | 100348742 |  | 6748208M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PARK | 109 PARK AV | 049 | WIN | 2022-10-18 | U129722 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-10-17 | 2022-10-05 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.26667 | 1 | 2005.08 | 0 | 0 | 0 | 2005.08 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883210200 |  | 100422402 |  | 6740212N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | KERRY | 250 KERRY DR | 049 | WIN | 2022-10-18 | U129722 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-10-17 | 2022-10-14 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 2279.36 | 448.11 | 0 | 325.91 | 1505.34 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883237500 |  | 100349957 |  | 6744204D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAIN | 365 S MAIN ST | 049 | WIN | 2022-10-17 | U126286 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | TYLER ALLISON | 2022-10-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9 | 1 | 2033.64 | 524.5 | 0 | 31.19 | 1477.95 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883242000 |  | 500602761 |  | 6740204H | 9402647 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | ORCHID | 203 ORCHID CT | 049 | WIN | 2022-10-17 | U126285 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DDAVIS | 2022-10-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883253600 |  | 100347432 |  | 6744208L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SPRING | 109 SPRING ST | 049 | WIN | 2022-10-17 | U126286 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | TYLER ALLISON | 2022-10-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883253700 |  | 100443739 |  | 6748208I | 2075093 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | STERLING | 53 STERLING ST | 049 | WIN | 2022-10-17 | U126285 | U120245 | 2021-01-30 | 2022-12-30 |  |  | DDAVIS | 2022-10-17 | 2022-10-05 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26290043 | 9.0167 | 2 | 1886.97 | 503.58 | 0 | 357.27 | 1026.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21884214700 |  | 100416460 |  | 6736212K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MOUNT VERNON | 433 MOUNT VERNON DR | 049 | WIN | 2022-10-17 | U127414 | U128293 | 2021-02-04 | 2022-07-01 | 2022-12-31 |  | ED FOX | 2022-10-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.6167 | 1 | 2039.3 | 275.26 | 0 | 16.36 | 1747.68 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916435800 |  | 100265046 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2009 MAIN ST W W | 019 | ASH | 2022-10-17 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-10-17 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2546.29 | 0 | 0 | 0 | 2546.29 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026223200 |  |  |  | 6720800A | 2291477 | U461383 |  | 558 | EX | EMER-RETIRE 3' OF 2"PMP MAIN | 2621P | CAMBRIDGE | 109 CAMBRIDGE LN | 113 | NIC | 2022-12-07 | U128132 | U461383 | 2022-09-09 | 2023-05-31 | 2023-05-31 | 2022-03-07 | RJCRAWF | 2022-10-17 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2232 |  |  | 100 | 055832220262232 | 1.9167 | 0 | 125.23 | 118.2 | 0 | 7.03 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129027400 |  | 100248438 |  | 7356256J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BELMONT | 2313 BELMONT ST | 019 | ASH | 2022-11-23 | U125566 | U130722 | 2022-09-05 | 2022-10-17 |  |  | DESKAGG | 2022-10-17 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.7333 | 1 | 1851.19 | 158.01 | 0 | 33.28 | 1659.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129036900 |  | 100251114 |  | 7340268F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 1918 MAIN ST | 089 | GRE | 2022-10-25 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-17 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129037100 |  | 100250415 |  | 7340264F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PLUM GROVE | 188 PLUM GROVE RD | 089 | GRE | 2022-10-25 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-17 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129037300 |  | 100251630 |  | 7336272F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SMITH BRANCH | 181 SMITH BRANCH RD | 089 | GRE | 2022-10-25 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-17 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129037400 |  | 100251635 |  | 7336272F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | TEAGUE | 191 TEAGUE DR | 089 | GRE | 2022-10-25 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-17 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 6.0667 | 1 | 1530.21 | 406.44 | 0 | 23.77 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129038700 |  | 500017702 |  | 7328284C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 9TH | 69 9TH AV | 089 | S S | 2022-10-25 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-17 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1962 | 0 | 0 | 0 | 1962 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129057200 |  | 100358209 |  | 6740232N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 41 E MAIN ST | 017 | PAR | 2022-10-18 | U126603 | U130722 | 2022-09-05 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-10-17 | 2022-10-17 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9.5 | 1 | 2568.62 | 567.2 | 0 | 116.26 | 1885.16 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129073800 |  | 100250723 |  | 7336268D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CHESAPEAKE | 518 CHESAPEAKE AV | 089 | GRE | 2022-10-25 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-17 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129074300 |  | 100251558 |  | 7336276N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OHIO RIVER | 1165 OHIO RIVER RD | 089 | GRE | 2022-10-25 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-17 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129074400 |  | 100409145 |  | 7340268N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | STATE RT 1 | 1145 STATE RT 1 | 089 | GRE | 2022-10-25 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-17 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 255 | 0 | 0 | 0 | 255 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129075500 |  | 500562918 |  | 7332288N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 4TH | 107 4TH ST | 089 | S S | 2022-10-25 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-17 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129075700 |  | 500184890 |  | 7328288O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LOCUST | 63 LOCUST ST | 089 | S S | 2022-10-25 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-17 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129082800 |  | 500399118 |  | 6720212B |  |  |  | 565 | EX | RPLC SL | 2600B | WITHERS | 115 WITHERS AV | 067 | LEX | 2022-10-17 | U124003 | U130722 | 2022-09-05 | 2022-12-30 |  |  | BPULLIAM/MILLER | 2022-10-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 7.7167 | 1 | 4497.54 | 451.79 | 0 | 605.17 | 3440.58 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129088100 |  | 100274591 |  | 6684228J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | EWING | 321 EWING ST B | 073 | FRA | 2022-10-17 | U126602 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DEREK PAYTON | 2022-10-17 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1482.12 | 0 | 0 | 0 | 1482.12 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129120900 |  | 100241740 |  | 7356252D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 52ND | 322 52ND ST | 019 | ASH | 2022-10-18 | U125566 | U125208 | 2022-09-06 | 2022-10-13 |  |  | DESKAGG | 2022-10-17 | 2022-10-13 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 7.6167 | 3 | 2385.41 | 440.75 | 0 | 83.56 | 1861.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129122400 |  | 100250748 |  | 7336268H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SYCAMORE | 400 SYCAMORE ST | 089 | GRE | 2022-10-25 | U125881 | U125208 | 2022-09-06 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-17 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1355 | 0 | 0 | 0 | 1355 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22134915200 |  | 100272040 |  | 6684228K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 4TH | 223 E 4TH ST | 073 | FRA | 2022-10-20 | U126602 | U130722 | 2022-09-27 | 2022-12-30 |  |  | DEREK PAYTON | 2022-10-17 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8 | 1 | 3188.85 | 433.72 | 0 | 25.78 | 2729.35 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22138958900 |  | 100324560 |  | 6720204B |  |  |  | 565 | EX | GRADE 1 REPLACE SERVICE LINE | 2621P | COLDSTREAM | 3410 COLDSTREAM CT | 067 | LEX | 2022-10-17 | TROE | U129939 | 2022-10-13 | 2022-10-13 | 2022-10-13 |  | TROE | 2022-10-17 | 2022-10-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 34.6833 | 7 | 2594.74 | 1879.28 | 544.36 | 111.7 | 59.4 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22139128300 |  | 100261391 |  | 7352256K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D188394 | 2621P | BEECH | 1633 BEECH ST | 019 | ASH | 2022-10-18 | U125208 | U134852 | 2022-10-14 | 2022-10-14 | 2022-10-14 |  | MCOLLET | 2022-10-17 | 2022-10-14 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 20.0667 | 4 | 5602.36 | 1412.03 | 339.69 | 478.37 | 3372.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22139320700 |  | 100312066 |  | 6716208I |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CLEARVIEW | 258 CLEARVIEW DR | 067 | LEX | 2022-10-18 | U930915 | U129939 | 2022-10-17 | 2022-10-14 | 2022-10-14 |  | LSTANFI | 2022-10-17 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.0833 | 1 | 2052.2 | 1730.06 | 142.09 | 125.05 | 55 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22139447900 |  | 100343084 |  | 7240212A |  |  |  | 566 | EX | ABN ON PAPER/W/613 WINCHESTER | 2621P | WINCHESTER | 615 WINCHESTER RD | 173 | MT | 2022-10-17 | DMCCULL | DMCCULL | 2022-10-17 | 2022-10-20 |  |  | OFFICE | 2022-10-17 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 0
KY | KY - WEST | 2623 | 22979047900 |  | 100448296 |  | 6712232O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CHAMBERS | 305 CHAMBERS AV | 209 | GEO | 2022-10-18 | U127206 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | JUSTIN HOBBS | 2022-10-17 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1878.7 | 0 | 0 | 0 | 1878.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 16426400200 |  | 100439845 |  | 6764176N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | RICHMOND | 993 RICHMOND RD | 065 | IRV | 2022-10-18 | U126286 | U122906 | 2016-07-13 | 2022-07-01 | 2022-12-31 |  | TYLER ALLISON | 2022-10-18 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 6475.6 | 0 | 0 | 0 | 6475.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18576584000 |  | 100285628 |  | 6768172A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | HIGH | 232 HIGH ST | 065 | IRV | 2022-10-18 | U126286 | U125765 | 2018-01-23 | 2022-07-01 | 2022-12-31 |  | TYLER ALLISON | 2022-10-18 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - CENTRAL | 2629 | 21883115700 |  | 500399693 |  | 6748208I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | WINN | 34 WINN AV | 049 | WIN | 2022-10-19 | U126603 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | SHAWN DENNIS | 2022-10-18 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.6833 | 1 | 3194.46 | 219.1 | 0 | 44.92 | 2930.44 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883202700 |  | 100348271 |  | 6748208I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WINN | 37 WINN AV | 049 | WIN | 2022-10-19 | U126603 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | SHAWN DENNIS | 2022-10-18 | 2022-10-18 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.4167 | 1 | 1873.19 | 203 | 0 | 41.63 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883261700 |  | 100281700 |  | 6712232O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | ELM | 102 ELM ST | 209 | GEO | 2022-10-19 | U127206 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-10-18 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8 | 1 | 2841.13 | 426.66 | 0 | 25.38 | 2389.09 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883304800 |  | 100441057 |  | 6740208H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | HUD | 101 HUD RD | 049 | WIN | 2022-10-18 | U127414 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | ED FOX | 2022-10-18 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.6333 | 1 | 2250.09 | 276.47 | 0 | 16.45 | 1957.17 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883330800 |  | 500076425 |  | 6744208H | 9614864 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | ROLLING HILLS | 605 ROLLING HILLS LN | 049 | WIN | 2022-10-19 | U461383 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-10-18 | 2022-10-17 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 16.75 | 2 | 3582.72 | 918.79 | 0 | 200.15 | 2463.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959048100 |  | 100315048 |  | 6716212O | 2176780 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | LEADER | 156 LEADER AV 1 | 067 | LEX | 2022-10-19 | U123111 | U134723 | 2021-12-10 | 2022-12-30 |  |  | LYN STAFFORD | 2022-10-18 | 2022-10-05 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 8.5 | 3 | 10867.32 | 490.93 | 0 | 234.78 | 10141.61 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959048200 |  | 100315049 |  | 6716212O | 2176780 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | LEADER | 156 LEADER AV 2 | 067 | LEX | 2022-10-19 | U123111 | U134723 | 2021-12-10 | 2022-12-30 |  |  | LYN STAFFORD | 2022-10-18 | 2022-10-18 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 5.4167 | 2 | 525.92 | 304.68 | 0 | 221.24 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959048300 |  | 100315050 |  | 6716212O | 2176780 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | LEADER | 156 LEADER AV 3 | 067 | LEX | 2022-10-19 | U123111 | U134723 | 2021-12-10 | 2022-12-30 |  |  | LYN STAFFORD | 2022-10-18 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 21959048400 |  | 100315052 |  | 6716212O | 2176780 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | LEADER | 156 LEADER AV 4 | 067 | LEX | 2022-10-19 | U123111 | U134723 | 2021-12-10 | 2022-12-30 |  |  | LYN STAFFORD | 2022-10-18 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 0.016667 | 1 | 1.92 | 1.11 | 0 | 0.81 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959048500 |  | 100315053 |  | 6716212O | 2176780 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | LEADER | 156 LEADER AV 5 | 067 | LEX | 2022-10-19 | U123111 | U134723 | 2021-12-10 | 2022-12-30 |  |  | LYN STAFFORD | 2022-10-18 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 21959048600 |  | 100315054 |  | 6716212O | 2176780 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | LEADER | 156 LEADER AV 6 | 067 | LEX | 2022-10-19 | U123111 | U134723 | 2021-12-10 | 2022-12-30 |  |  | LYN STAFFORD | 2022-10-18 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 0.016667 | 1 | 1.92 | 1.11 | 0 | 0.81 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960238400 |  | 100320994 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | MAXWELL | 435 E MAXWELL ST 1 | 067 | LEX | 2022-10-18 | U128410 | U134723 | 2021-12-17 | 2022-12-30 |  |  | CDESPAIN | 2022-10-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2916.84 | 0 | 0 | 0 | 2916.84 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22026193600 |  |  |  | 7364188A | 2289175 | U122858 |  | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2621M | MIDDLE FORK RD. | MIDDLE FORK RD. | 159 | INE | 2022-11-10 | U123258 | U136124 | 2022-05-31 | 2022-12-30 | 2022-12-31 | 2022-10-18 | MRYAN | 2022-10-18 | 2022-10-18 |  | F | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00909 | 3200909 |  |  | WP1936 |  |  | 100 | 090932220261936 | 4.4667 | 0 | 1911.78 | 270.89 | 0 | 184.44 | 1456 | 0 | 0.45 | 0
KY | KY - EAST | 2633 | 22026193700 |  |  |  | 7364188A | 2289175 | U122858 |  | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2621M | MIDDLE FORK RD. | MIDDLE FORK RD. | 159 | INE | 2022-11-10 | U123258 | U136124 | 2022-05-31 | 2022-12-30 | 2022-12-31 | 2022-10-18 | MRYAN | 2022-10-18 | 2022-10-18 |  | F | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00910 | 3200910 |  |  | WP1937 |  |  | 100 | 091032220261937 | 2.1667 | 0 | 217.55 | 129.42 | 0 | 88.13 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22109475200 |  | 500453596 |  | 6712228N | 9508787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY + | 2621P | MARY LYNN | 100 MARY LYNN DR 26 | 209 | GEO | 2022-10-18 | U127206 | U125208 | 2022-06-13 | 2022-05-17 |  |  | JUSTIN HOBBS | 2022-10-18 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1368.31 | 0 | 0 | 0 | 1368.31 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22122643200 |  | 100278432 |  | 6688232N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311971 | 2621P | HOPI | 582 HOPI TL | 073 | FRA | 2022-10-19 | U125208 | U125208 | 2022-08-09 | 2022-10-17 | 2024-08-31 |  | BWHITE | 2022-10-18 | 2022-10-17 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 11.3333 | 2 | 1319.07 | 700.43 | 209.36 | 339.98 | 69.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129007200 |  | 100348599 |  | 6748208I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WINN | 54 WINN AV | 049 | WIN | 2022-10-19 | U126603 | U130722 | 2022-09-05 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-10-18 | 2022-10-18 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.4 | 1 | 1875.33 | 204.8 | 0 | 41.97 | 1628.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129036800 |  | 100250731 |  | 7336268H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LAUREL | 537 LAUREL ST | 089 | GRE | 2022-10-25 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-18 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 2885 | 0 | 0 | 0 | 2885 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129039300 |  | 100435101 |  | 7344264B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OAK | 515 OAK ST | 089 | WUR | 2022-10-25 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-18 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129058700 |  | 100284375 |  | 6764176M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RICHMOND | 2722 RICHMOND RD | 065 | IRV | 2022-10-19 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-10-18 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129073900 |  | 100458728 |  | 7340264B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | COLLINS | 305 COLLINS LN | 089 | GRE | 2022-10-25 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-18 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129074000 |  | 100419840 |  | 7340268J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ELM | 404 ELM ST | 089 | GRE | 2022-10-25 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-18 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129074100 |  | 500682613 |  | 7336276J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LEWIS | 210 LEWIS LN | 089 | GRE | 2022-10-25 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-18 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129074500 |  | 501247871 |  | 7340268J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | VINE | 200 VINE ST | 089 | GRE | 2022-10-25 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-18 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129076200 |  | 100419024 |  | 7344264A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KENTUCKY | 214 KENTUCKY AV | 089 | WUR | 2022-10-25 | U125881 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-18 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129091200 |  | 500784737 |  | 6716232A | 0145013 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CHERRY HILL | 127 CHERRY HILL DR | 209 | GEO | 2022-10-18 | U126602 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DEREK PAYTON | 2022-10-18 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8 | 1 | 3188.85 | 433.72 | 0 | 25.78 | 2729.35 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129130500 |  | 100462062 |  | 7332288M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BIGGS | 170 BIGGS LN | 089 | S S | 2022-10-25 | U125881 | U125208 | 2022-09-06 | 2022-12-30 |  |  | HERBERT HAYDEN | 2022-10-18 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22134093600 |  | 100360688 |  | 6736228C |  |  |  | 566 | EX | ABANDON SL - IDLE/CONVERTION | 2621P | MOUNT VIEW | 510 MOUNT VIEW DR | 017 | PAR | 2022-10-18 | WHIMES | U125208 | 2022-09-23 | 2022-09-28 | 2022-10-31 |  | WHIMES | 2022-10-18 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 12.3167 | 2 | 1038.09 | 686.45 | 14.45 | 337.19 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22139351600 |  | 100261266 |  | 352256H |  |  |  | 565 | EX | SERVICE LINE - REPLACE D258015 | 2621P | CUMBERLAND | 2606 CUMBERLAND AV | 019 | ASH | 2023-01-10 | U125208 | U129939 | 2022-10-17 | 2022-10-17 | 2022-10-17 |  | JAHOWARD | 2022-10-18 | 2022-10-17 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 34.5667 | 5 | 2293.64 | 2113.01 | 0 | 125.63 | 55 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22139466900 |  | 100281945 |  | 6712232O |  |  |  | 565 | EX | EMR SERVICE LINE - REPLACE RLA | 2621P | MAIN | 433 MAIN AV | 209 | GEO | 2022-10-19 | U125208 | U125208 | 2022-10-17 | 2022-10-17 |  |  | BWHITE | 2022-10-18 | 2022-10-17 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 4.5 | 2 | 587.93 | 278.45 | 124.59 | 147.49 | 37.4 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22139619200 |  | 500259018 |  | 7348264F |  |  |  | 565 | EX | SERVICE LINE REPLACEMENT | 2621P | WALKER | 490 WALKER AV | 089 | RAC | 2022-10-19 | U125566 | U131946 | 2022-10-18 | 2022-10-18 |  |  | DESKAGG | 2022-10-18 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 | 9.75 | 1 | 4218.93 | 560.25 | 0 | 118 | 3540.68 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22139658600 |  | 100348711 |  | 6748208M |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | WASHINGTON | 213 E WASHINGTON ST 1 | 049 | WIN | 2022-10-20 | U127414 | U125763 | 2022-10-18 | 2022-12-30 |  |  | ED FOX | 2022-10-18 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2107.78 | 0 | 0 | 0 | 2107.78 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22139663200 |  | 100278388 |  | 6688232N |  |  |  | 565 | EX | SERVICE LINE - REPLACE D303143 | 2621P | OJIBWA | 1154 OJIBWA TL | 073 | FRA | 2022-10-24 | U126332 | U131946 | 2022-10-18 | 2023-02-03 | 2024-08-31 |  | BWHITE | 2022-10-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.45 | 1 | 123.04 | 27.88 | 0 | 1.66 | 93.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979047500 |  | 100442921 |  | 6748208M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WASHINGTON | 213 E WASHINGTON ST 3 2F | 049 | WIN | 2022-10-20 | U127414 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | ED FOX | 2022-10-18 | 2022-10-18 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.3667 | 1 | 315.75 | 262.12 | 0 | 53.63 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979049300 |  | 100465509 |  | 6744204C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WILLOWBROOK | 422 WILLOWBROOK RD | 049 | WIN | 2022-10-18 | U126285 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | DDAVIS | 2022-10-18 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.5 | 1 | 1370.47 | 201.45 | 0 | 142.9 | 1026.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979049500 |  | 100466235 |  | 6760176I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SUB STATION | 425 SUB STATION RD | 065 | IRV | 2022-10-19 | U126286 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | TYLER ALLISON | 2022-10-18 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11917022200 |  | 500483703 |  | X-1110/10 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | RICE STATION | 1252 RICE STATION RD | 065 | IRV | 2022-10-19 | U126286 | U124964 | 2011-07-22 | 2022-07-01 | 2022-12-31 |  | TYLER ALLISON | 2022-10-19 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 7001.58 | 0 | 0 | 0 | 7001.58 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 14270154100 |  | 100286295 |  | 6756176O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | IRVINE | 760 S IRVINE RD | 065 | IRV | 2022-10-19 | U129722 | U122906 | 2014-12-11 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-10-19 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2933.83 | 0 | 0 | 0 | 2933.83 | 0 | 0 | 0
KY | KY - WEST | 2623 | 17569041100 |  | 500321975 |  | 6708228H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WILLOW | 128 WILLOW LN LT26 | 209 | GEO | 2022-10-19 | U126602 | U125765 | 2017-12-20 | 2022-07-01 | 2022-12-31 |  | DEREK PAYTON | 2022-10-19 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 741.06 | 0 | 0 | 0 | 741.06 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883056900 |  | 500402713 |  | 6712224L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LISLE | 1191 LISLE RD 9 | 209 | GEO | 2022-10-19 | U127206 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-10-19 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1610.69 | 0 | 0 | 0 | 1610.69 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883070700 |  | 100348293 |  | 6748208I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | WINN | 139 WINN AV | 049 | WIN | 2022-10-19 | U126603 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | SHAWN DENNIS | 2022-10-19 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.65 | 1 | 1963.14 | 277.68 | 0 | 56.9 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883153500 |  | 100270470 |  | 6736248A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CHURCH | 318 S CHURCH ST | 097 | CYN | 2022-10-20 | U126285 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DDAVIS | 2022-10-19 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.5 | 2 | 2444.42 | 201.45 | 0 | 11.97 | 2231 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883156700 |  | 100270178 |  | 6732252P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | COURT | 102 COURT ST | 097 | CYN | 2022-10-20 | U126285 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DDAVIS | 2022-10-19 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.5 | 1 | 1300.48 | 258.97 | 0 | 15.39 | 1026.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883165400 |  | 501049779 |  | 7240208B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEVEE | 3826 LEVEE RD | 173 | MT | 2022-10-19 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-10-19 | 2022-10-11 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 6.8833 | 2 | 3401.71 | 425.55 | 0 | 85.25 | 2890.91 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883189400 |  | 100422675 |  | 6732252P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SMITH | 113 SMITH AV | 097 | CYN | 2022-10-19 | U126285 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DDAVIS | 2022-10-19 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883205600 |  | 500341443 |  | 6760172D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | STACY LANE | 1905 STACY LANE RD | 065 | IRV | 2022-10-19 | U126286 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | TYLER ALLISON | 2022-10-19 | 2022-06-01 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9.6333 | 2 | 2466.35 | 559.41 | 0 | 33.36 | 1873.58 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883290900 |  | 100283039 |  | 6712228H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEMONS MILL | 794 LEMONS MILL RD | 209 | GEO | 2022-10-19 | U127206 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-10-19 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8 | 1 | 2305.11 | 426.66 | 0 | 25.38 | 1853.07 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883306500 |  | 100271409 |  | 6736252N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MEADOW | 204 W MEADOW LN | 097 | CYN | 2022-10-19 | U126285 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DDAVIS | 2022-10-19 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0 | 1 | 1505.34 | 0 | 0 | 0 | 1505.34 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883316900 |  | 500851581 |  | 6712228I | 0254210 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WARREN PASS | 102 WARREN PASS LT458 | 209 | GEO | 2022-10-19 | U126602 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DEREK PAYTON | 2022-10-19 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8 | 1 | 3188.85 | 433.72 | 0 | 25.78 | 2729.35 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916435700 |  | 100265047 |  | 7352260O | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2005 MAIN ST W W | 019 | ASH | 2022-10-19 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-10-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2380.01 | 0 | 0 | 0 | 2380.01 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21947535900 |  | 100344757 |  | 6700224P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | BRAND | 122 BRAND ST R | 239 | MID | 2023-01-10 | U125559 | U131066 | 2021-10-19 | 2022-07-01 | 2022-12-31 |  | CHARLES COMBS | 2022-10-19 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2621 | 22026197300 |  |  |  | 6716204F | 2289273 | U122858 |  | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2621M | TIVERTON | 110 E TIVERTON WY | 067 | LEX | 2022-11-09 | U121330 | U136124 | 2022-06-03 | 2022-12-30 | 2022-12-31 | 2022-10-19 | CCOX | 2022-10-19 | 2022-10-19 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP1973 |  |  | 100 | 090932220261973 | 3.5167 | 0 | 6904.6 | 227.71 | 0 | 13.55 | 6630.3 | 0 | 33.04 | 0
KY | KY - WEST | 2621 | 22026197400 |  |  |  | 6716204F | 2289273 | U122858 |  | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2621M | TIVERTON | 110 E TIVERTON WY | 067 | LEX | 2022-11-09 | U121330 | U136124 | 2022-06-03 | 2022-12-30 | 2022-12-31 | 2022-10-19 | CCOX | 2022-10-19 | 2022-10-19 |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00910 | 3200910 |  |  | WP1974 |  |  | 100 | 091032220261974 | 4.4833 | 0 | 305.47 | 288.31 | 0 | 17.16 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026220800 |  |  |  | 6720212E | 2177145 | U461383 |  | 558 | EX | *PAPER ONLY* 2022 CAST IRON | 2600B | 4TH | 4TH | 067 | LEX | 2022-10-21 | U128132 | U461383 | 2022-08-31 | 2022-10-23 | 2022-10-26 | 2022-10-19 | LES SHARON | 2022-10-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2208 | AMRCB |  | 100 | 055832220262208 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22119124200 |  | 100282873 |  | 6712228C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311968 | 2621P | JACKSON | 610 E JACKSON ST | 209 | GEO | 2022-10-19 | BWHITE | U125208 | 2022-07-28 | 2022-10-19 | 2024-07-31 |  | BWHITE | 2022-10-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.1167 | 1 | 114.98 | 71.16 | 0 | 4.22 | 39.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129007100 |  | 100348294 |  | 6748208I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WINN | 143 WINN AV | 049 | WIN | 2022-10-19 | U126603 | U130722 | 2022-09-05 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-10-19 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.8333 | 1 | 1530.23 | 168.38 | 0 | 34.51 | 1327.34 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129039400 |  | 100257638 |  | 7344268M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PLUM | 208 PLUM ST | 089 | WUR | 2022-10-19 | U938684 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHARLES COMBS | 2022-10-19 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 2002.72 | 0 | 0 | 0 | 2002.72 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129039500 |  | 100257768 |  | 7344268N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RIVERSIDE | 1104 RIVERSIDE DR | 089 | WUR | 2022-10-19 | U938684 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CHARLES COMBS | 2022-10-19 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129044900 |  | 100291264 |  | 6720216H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KINGSTON | 605 KINGSTON RD | 067 | LEX | 2022-10-19 | HMCKUNE | U130722 | 2022-09-05 | 2022-12-30 |  |  | HMCKUNE | 2022-10-19 | 2022-10-13 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 17.4 | 5 | 913.99 | 823.58 | 41.41 | 49 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129117800 |  | 100343907 |  | 7240212N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LEVEE | 3707 LEVEE RD | 173 | MT | 2022-10-19 | U126604 | U125208 | 2022-09-06 | 2022-12-30 |  |  | WILL FULKS | 2022-10-19 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.6 | 1 | 3494.38 | 345.39 | 559.42 | 69.19 | 2520.38 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129121000 |  | 100260999 |  | 7352256C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BARTLETT | 420 BARTLETT ST | 019 | ASH | 2022-11-22 | U125208 | U125208 | 2022-09-06 | 2022-10-17 |  |  | DESKAGG | 2022-10-19 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 8 | 1 | 2216.4 | 459.68 | 0 | 96.82 | 1659.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22136699500 |  | 500170184 |  | 6736240L | 2070683 | U461383 |  | 565 | EX | 1" TRANSMISSION CLASS STEEL SL | 2600B | RUDDLES MILL | 1201 RUDDLES MILL RD | 017 | PAR | 2023-01-20 | U126604 | U461383 | 2022-10-04 | 2022-11-01 | 2022-11-01 |  | WILL FULKS | 2022-10-19 | 2022-10-13 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26290032 | 48.5 | 6 | 15832.95 | 2977.84 | 2.29 | 1353.53 | 11499.29 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22137501100 |  | 100292347 |  | 6720216O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SOUTHRIDGE | 501 SOUTHRIDGE DR | 067 | LEX | 2022-10-19 | WISHII | U130722 | 2022-10-07 | 2022-12-30 |  |  | WISHII | 2022-10-19 | 2022-10-17 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 19.8667 | 5 | 1300.28 | 952.61 | 0 | 347.67 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22139723600 |  | 100273655 |  | 6684228M |  |  |  | 565 | EX | REPLACE SERV LINE | 2621P | JUNIPER | 237 JUNIPER DR | 073 | FRA | 2022-10-20 | U125208 | U136097 | 2022-10-18 | 2022-10-18 |  |  | BWHITE | 2022-10-19 | 2022-10-18 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26230031 | 6.7833 | 2 | 542.63 | 420.79 | 0 | 25.04 | 96.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22139892300 |  | 100328274 |  | 6720200D |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | DELONG | 2050 DELONG RD | 067 | LEX | 2022-10-19 | ABLAKE | U129939 | 2022-10-19 | 2022-10-19 |  |  | ABLAKE | 2022-10-19 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.1667 | 1 | 5746.4 | 4465.71 | 332.96 | 673.83 | 273.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22139960500 |  | 100325256 |  | 6720204A |  |  |  | 565 | EX | SERVICE LINE - REPLACE D304133 | 2621P | CASTLETON | 3489 CASTLETON HL | 067 | LEX | 2022-10-20 | U930915 | U129939 | 2022-10-19 | 2022-10-19 | 2022-10-19 |  | TROE | 2022-10-19 | 2022-10-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25.4 | 6 | 2155.47 | 1396.76 | 460.81 | 209.9 | 88 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22139961500 |  | 100267477 |  | 7352260E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MOUNT SAVAGE | 136 MOUNT SAVAGE DR | 089 | ASH | 2022-10-19 | MCOLLET | U129939 | 2022-10-19 | 2022-10-19 | 2022-10-19 |  | MCOLLET | 2022-10-19 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.51667 | 1 | 1268.48 | 473.57 | 230.3 | 479.91 | 84.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22978416900 |  | 100321222 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | MAXWELL | 430 E MAXWELL ST 1F | 067 | LEX | 2022-10-19 | U128410 | U134723 | 2022-02-15 | 2022-12-30 |  |  | CDESPAIN | 2022-10-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2597.8 | 0 | 0 | 0 | 2597.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979052700 |  | 500442146 |  | 6748208I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | WINN | 38 WINN AV A | 049 | WIN | 2022-10-21 | U126603 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | SHAWN DENNIS | 2022-10-19 | 2022-10-05 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.2833 | 2 | 1289.03 | 180.93 | 0 | 37.08 | 1071.02 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11896521800 |  | 100270046 |  | 6732252P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | PLEASANT | 421 W PLEASANT ST | 097 | CYN | 2022-10-20 | U126285 | U906631 | 2011-03-18 | 2022-07-01 | 2022-12-31 |  | DDAVIS | 2022-10-20 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.5 | 2 | 2471.81 | 201.45 | 0 | 11.97 | 2258.39 | 0 | 0 | 0
KY | KY - WEST | 2623 | 12967996600 |  | 100281319 |  | 6712228B |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | MAIN | 245 W MAIN ST 2FR | 209 | GEO | 2022-10-24 | U125559 | U124967 | 2012-05-02 | 2020-07-06 |  |  | JUSTIN HOBBS | 2022-10-20 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - CENTRAL | 2629 | 21883118500 |  | 100271505 |  | 6736252M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | PIKE | 410 E PIKE ST | 097 | CYN | 2022-10-21 | U129722 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-10-20 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883124800 |  | 500449567 |  | 7244216G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | STEPSTONE | 2201 STEPSTONE RD | 173 | MT | 2022-10-20 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-10-20 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.5333 | 1 | 3477.68 | 340.49 | 0 | 20.25 | 3116.94 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883130200 |  | 100281306 |  | 6712228B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAIN | 409 W MAIN ST | 209 | GEO | 2022-10-20 | U127206 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-10-20 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 2499.82 | 0 | 0 | 0 | 2499.82 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883162600 |  | 100286403 |  | 6768172B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 3RD | 304 3RD ST | 065 | RAV | 2022-12-14 | U123110 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | TYLER ALLISON | 2022-10-20 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 11316.34 | 480.88 | 0 | 28.12 | 10807.34 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883172700 |  | 100270156 |  | 6732252P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | PLEASANT | 115 W PLEASANT ST | 097 | CYN | 2022-10-20 | U126285 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DDAVIS | 2022-10-20 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.5 | 2 | 1752.31 | 258.97 | 0 | 15.39 | 1477.95 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883229600 |  | 100270924 |  | 6736248A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | PARKLAND | 260 PARKLAND HT | 097 | CYN | 2022-10-21 | U127414 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | ED FOX | 2022-10-20 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.5 | 1 | 2100.37 | 329.16 | 0 | 67.35 | 1703.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883264800 |  | 100281323 |  | 6712228B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAIN | 225 W MAIN ST | 209 | GEO | 2022-10-20 | U127206 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-10-20 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8 | 1 | 4044.37 | 426.66 | 0 | 25.38 | 3592.33 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883289400 |  | 100271504 |  | 6736252M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | PIKE | 412 E PIKE ST | 097 | CYN | 2022-10-21 | U129722 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-10-20 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 2313.58 | 438.82 | 0 | 95.59 | 1779.17 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916435900 |  | 100265044 |  | 7352260O | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2017 MAIN ST W | 019 | ASH | 2022-10-20 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-10-20 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2350.23 | 0 | 0 | 0 | 2350.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960238800 |  | 100321281 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | MAXWELL | 462 E MAXWELL ST 1F | 067 | LEX | 2022-10-20 | U128410 | U134723 | 2021-12-17 | 2022-12-30 |  |  | CDESPAIN | 2022-10-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1815.49 | 0 | 0 | 0 | 1815.49 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22128552000 |  | 500825534 |  | 6724208M |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | YORKSHIRE MEDI | 3401 YORKSHIRE MEDI PK | 067 | LEX | 2022-10-26 | U126602 | U125763 | 2022-09-01 | 2022-12-30 |  |  | DEREK PAYTON | 2022-10-20 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 3668.07 | 433.72 | 0 | 25.78 | 3208.57 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129002800 |  | 100270090 |  | 6732252P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 1ST | 108 1ST ST | 097 | CYN | 2022-10-21 | U127414 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ED FOX | 2022-10-20 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.5 | 1 | 1877.65 | 269.29 | 0 | 55.11 | 1553.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129059100 |  | 100286486 |  | 6768172B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | POPLAR | 406 POPLAR ST | 065 | RAV | 2022-10-20 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-10-20 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22136114700 |  | 100288830 |  | 6720212D | 1855043 |  |  | 566 | EX | ABANDON SL - SOII/INSIDE | 2621P | SAINT ANTHONY | 621 SAINT ANTHONY DR | 067 | LEX | 2022-11-09 | U125208 | U130868 | 2022-09-30 | 2022-12-30 | 2022-12-31 |  | HMCKUNE | 2022-10-20 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.7 | 2 | 628 | 561.85 | 32.74 | 33.41 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22138847200 |  | 100324486 |  | 6720204E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094430 | 2621P | OLYMPIA | 3581 OLYMPIA DR | 067 | LEX | 2022-10-20 | LSTANFI | U125208 | 2022-10-13 | 2022-10-14 | 2022-11-02 |  | LSTANFI | 2022-10-20 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25.7667 | 4 | 2069.74 | 1328.37 | 561.82 | 179.55 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22140269300 |  | 501194194 |  | 6712204B |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | KINGS GLEN | 3742 KINGS GLEN PR | 067 | LEX | 2022-10-26 | U126602 | U125763 | 2022-10-20 | 2022-12-30 |  |  | DEREK PAYTON | 2022-10-20 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2109.37 | 0 | 0 | 0 | 2109.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22978417100 |  | 100321280 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | MAXWELL | 460 E MAXWELL ST 1F | 067 | LEX | 2022-10-28 | U461375 | U134723 | 2022-02-15 | 2022-12-30 |  |  | LARRY BROWN | 2022-10-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3108.48 | 0 | 0 | 0 | 3108.48 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22979030700 |  | 100281316 |  | 6712228B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 245 W MAIN ST 1FR | 209 | GEO | 2022-10-24 | U125559 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | JUSTIN HOBBS | 2022-10-20 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 492.07 | 0 | 0 | 0 | 492.07 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 08743094100 |  | 100269746 |  | U-1014/47 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | PLEASANT | 438 W PLEASANT ST | 097 | CYN | 2022-10-24 | U127414 | SSUTHER | 2008-08-04 | 2022-07-01 | 2022-12-31 |  | ED FOX | 2022-10-21 | 2022-10-21 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.05 | 1 | 1992.62 | 302.21 | 0 | 61.85 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19692267300 |  | 100442528 |  | 6744204J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | OLD BOONESBORO | 2719 OLD BOONESBORO RD | 049 | WIN | 2022-10-21 | U126285 | DMCCULL | 2019-03-29 | 2022-07-01 | 2022-12-31 |  | DDAVIS | 2022-10-21 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 2972.09 | 460.42 | 0 | 27.37 | 2484.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883097200 |  | 100270743 |  | 6736252M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY D311815 | 2621P | PIKE | 447 E PIKE ST | 097 | CYN | 2022-10-21 | U129722 | U120245 | 2021-01-30 | 2023-04-06 | 2024-10-31 |  | M YOUNG | 2022-10-21 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 2313.58 | 438.82 | 0 | 95.59 | 1779.17 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883128400 |  | 100283677 |  | 6712228B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BROADWAY | 411 S BROADWAY ST | 209 | GEO | 2022-10-21 | U129731 | U120245 | 2021-01-30 | 2022-10-21 | 2022-12-31 |  | F.GOINS | 2022-10-21 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8 | 1 | 2786.91 | 470.49 | 0 | 97.46 | 2218.96 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883131800 |  | 100284013 |  | 6712228J | 0675144 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEXINGTON | 1163 LEXINGTON RD | 209 | GEO | 2022-10-21 | U129731 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-10-21 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8 | 1 | 4486.99 | 458.96 | 0 | 27.29 | 4000.74 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21884194200 |  | 100271202 |  | 6736252N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | PIKE | 503 E PIKE ST DN | 097 | CYN | 2022-10-24 | U127414 | U128293 | 2021-02-04 | 2022-07-01 | 2022-12-31 |  | ED FOX | 2022-10-21 | 2022-10-21 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.95 | 1 | 2450.89 | 296.2 | 0 | 60.61 | 2094.08 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916436000 |  | 100265043 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2023 MAIN ST W | 019 | ASH | 2022-10-21 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-10-21 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2820.52 | 0 | 0 | 0 | 2820.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959035300 |  | 100315322 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | LIMESTONE | 1101 S LIMESTONE ST | 067 | LEX | 2022-10-21 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-10-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2598.71 | 451.31 | 0 | 96.34 | 2051.06 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026195200 |  |  |  | 6740208C | 2289216 | U122858 |  | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2621M | GAWTHROP | GAWTHROP DR | 049 | PIN | 2022-11-03 | U123258 | U136124 | 2022-06-01 | 2022-12-30 | 2022-12-31 | 2022-10-21 | JPASLEY | 2022-10-21 | 2022-10-13 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00909 | 3200909 |  |  | WP1952 |  |  | 100 | 090932220261952 | 17.3167 | 0 | 6702.65 | 1021.13 | 0 | 472.95 | 5174.3 | 0 | 34.27 | 0
KY | KY - CENTRAL | 2629 | 22026195300 |  |  |  | 6740208C | 2289216 | U122858 |  | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2621M | GAWTHROP | GAWTHROP DR | 049 | PIN | 2022-11-03 | U123258 | U136124 | 2022-06-01 | 2022-12-30 | 2022-12-31 | 2022-10-21 | JPASLEY | 2022-10-21 | 2022-10-21 |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00910 | 3200910 |  |  | WP1953 |  |  | 100 | 091032220261953 | 0.56667 | 0 | 34.29 | 32.36 | 0 | 1.93 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026198601 |  | 501331979 |  | 6716216E | 2289300 | U461383 |  | 555 | EX | INSTALL 1900' OF 2"PMMP MAIN | 2600B | DAHLIA | DAHLIA DR LT78 | 067 | LEX | 2022-10-31 | U127810 | U461383 | 2022-08-17 | 2022-10-17 | 2022-11-01 | 2022-10-20 | OLIVER MAYNARD | 2022-10-21 | 2022-09-29 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP1986 |  |  | 100 | 055532220261986 | 190.95 | 52992 | 71556.52 | 10422.98 | 4102.79 | 1173.63 | 49187.04 | 0 | 71.2 | 6598.88 | 2208
KY | KY - WEST | 2623 | 22026214100 |  |  |  | 6700212M | 2290216 | U126783 |  | 562 | EX | ABANDON 200'-2" PMMP | 2600B | SUGARTREE | SUGARTREE LN | 239 | VER | 2022-11-18 | U128132 | U126783 | 2022-07-26 | 2022-10-20 | 2022-10-20 | 2022-10-21 | J ENSMINGER | 2022-10-21 | 2022-10-18 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00562 | 3200562 |  |  | WP2141 |  |  | 100 | 056232220262141 | 9.5167 | 0 | 921.07 | 533.23 | 0 | 387.84 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22137980400 |  | 100264732 |  | 7384168O |  |  |  | 565 | VO | SERVICE LINE - REPLACE CAT 2 | 2621P | NEW CAMP | 439 NEW CAMP RD | 195 | S W | 2022-10-26 |  | U131790 | 2022-10-10 | 2022-10-14 | 2022-11-01 |  | JCKIRK | 2022-10-21 |  |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26330031 | 17.5 | 2 | 1168.81 | 1103.23 | 0 | 65.58 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22139660100 |  | 100324945 |  | 6720204E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311064 | 2621P | CASTLETON | 1037 CASTLETON WY | 067 | LEX | 2022-10-21 | LSTONE | U125208 | 2022-10-18 | 2022-10-21 | 2022-11-08 |  | LSTONE | 2022-10-21 | 2022-10-21 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.6333 | 4 | 2698.26 | 1410.92 | 1032.89 | 119.15 | 135.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22140297200 |  | 100467911 |  | 6720204M |  |  |  | 565 | EX | REPLACE SERVICE LINE - D310000 | 2621P | SHAGBARK | 1125 SHAGBARK LN | 067 | LEX | 2022-10-24 | U125208 | U125208 | 2022-10-20 | 2022-10-21 | 2022-11-10 |  | RJCRAWF | 2022-10-21 | 2022-10-21 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.3333 | 3 | 1761.99 | 1146.1 | 219.86 | 316.83 | 79.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22140558600 |  | 100271201 |  | 6736252N |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | PIKE | 503 E PIKE ST UP | 097 | CYN | 2022-10-24 | U127414 | U125763 | 2022-10-21 | 2022-12-30 |  |  | ED FOX | 2022-10-21 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - CENTRAL | 2629 | 22964252800 |  | 100348010 |  | 6748208I | 2075093 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | STERLING | 26 STERLING ST | 049 | WIN | 2022-10-21 | U126286 | U134723 | 2022-01-06 | 2022-12-30 |  |  | TYLER ALLISON | 2022-10-21 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26290043 |  | 1 | 1868.17 | 0 | 0 | 0 | 1868.17 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 07689004500 |  | 100284556 |  | 6752180F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | FLINT | 380 FLINT RD | 151 | WAC | 2022-10-25 | U129722 | U903504 | 2007-05-31 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-10-24 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4 | 1 | 1936.31 | 219.41 | 0 | 13.04 | 1703.86 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11920312900 |  | 500285816 |  | 6736180C |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MILLER | 247 MILLER DR | 151 | RIC | 2022-10-24 | U129722 | U124449 | 2011-08-16 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-10-24 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4 | 1 | 1710.4 | 219.41 | 0 | 13.04 | 1477.95 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883095600 |  | 100463360 |  | 7348252H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | US ROUTE 60 | 7117 US ROUTE 60 | 019 | ASH | 2022-10-24 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-10-24 | 2022-10-21 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 8.0667 | 2 | 2376.31 | 497.71 | 0 | 99.7 | 1778.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916436700 |  | 500008198 |  | 7352260N | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2040 MAIN ST W | 019 | ASH | 2022-10-24 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-10-24 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2095.05 | 64.28 | 0 | 6.73 | 2024.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960235500 |  | 100443560 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | HIGH | 466 E HIGH ST 2-1FL | 067 | LEX | 2022-10-24 | U128410 | U134723 | 2021-12-17 | 2022-12-30 |  |  | CDESPAIN | 2022-10-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1406.17 | 0 | 0 | 0 | 1406.17 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026213900 |  | 501328791 |  | 6700212M | 2290216 | U126783 |  | 555 | EX | INSTALL 200'-2"PMMP | 2600B | SUGARTREE | 216 SUGARTREE LN | 239 | VER | 2022-11-21 | U128132 | U126783 | 2022-07-25 | 2022-10-25 | 2022-10-31 | 2022-10-20 | J ENSMINGER | 2022-10-24 | 2022-10-19 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2139 |  |  | 100 | 055532220262139 | 36.6833 | 1232 | 35208.99 | 2052.27 | 2173.13 | 1187.41 | 27035.49 | 0 | 27.07 | 2733.62 | 308
KY | KY - CENTRAL | 2629 | 22129007600 |  | 100437206 |  | W1103-12 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FIKE | 5324 FIKE RD | 151 | WAC | 2022-10-24 | U129731 | U130722 | 2022-09-05 | 2022-10-24 |  |  | F.GOINS | 2022-10-24 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 2196.51 | 470.49 | 0 | 97.46 | 1628.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129030700 |  | 100247095 |  | 7352256L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BEECH | 2414 BEECH ST | 019 | ASH | 2022-11-23 | U125566 | U130722 | 2022-09-05 | 2022-10-24 |  |  | DESKAGG | 2022-10-24 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.35 | 1 | 2303.7 | 307.43 | 0 | 64.75 | 1931.52 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129063200 |  | 500111526 |  | 7240212A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BROOKVIEW | 602 BROOKVIEW DR | 173 | MT | 2022-10-25 | U126285 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DDAVIS | 2022-10-24 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4 | 1 | 2351.68 | 230.21 | 0 | 13.69 | 2107.78 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129063400 |  | 100343327 |  | 7240212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FOGG | 325 FOGG PK | 173 | MT | 2022-10-24 | U124003 | U130722 | 2022-09-05 | 2022-12-30 |  |  | BPULLIAM/MILLER | 2022-10-24 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 7.45 | 1 | 2641.8 | 433.11 | 0 | 580.13 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129063500 |  | 500214149 |  | 7240204G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LEVEE | 8515 LEVEE RD | 173 | MT | 2022-10-26 | U124003 | U130722 | 2022-09-05 | 2022-12-30 |  |  | BPULLIAM/MILLER | 2022-10-24 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.55 | 1 | 1982.73 | 151.39 | 0 | 202.78 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22139435100 |  | 500345809 |  | 6712208M |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTREQD | 2621P | HARRODSBURG | 4085 HARRODSBURG RD HSE | 067 | LEX | 2022-10-25 | U930915 | U125208 | 2022-10-17 | 2022-10-20 | 2022-11-17 |  | KKINDER | 2022-10-24 | 2022-10-24 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.0333 | 3 | 489.69 | 462.2 | 0 | 27.49 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22139435400 |  | 500043269 |  | 6712208M |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTREQD | 2621P | HARRODSBURG | 4085 HARRODSBURG RD LODGE | 067 | LEX | 2022-10-25 | U930915 | U125208 | 2022-10-17 | 2022-10-20 | 2022-11-17 |  | KKINDER | 2022-10-24 | 2022-10-21 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.2333 | 3 | 827.91 | 781.45 | 0 | 46.46 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22140566800 |  | 100291107 |  | 6720212A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BROADWAY | 734 N BROADWAY ST 1 | 067 | LEX | 2022-10-24 | RSTRONG | U125208 | 2022-10-21 | 2022-09-27 |  |  | RSTRONG | 2022-10-24 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.7833 | 1 | 142.34 | 99.71 | 0 | 42.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22140566900 |  | 100291105 |  | 6720212A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BROADWAY | 734 N BROADWAY ST 3 | 067 | LEX | 2022-10-24 | RSTRONG | U125208 | 2022-10-21 | 2022-09-27 |  |  | RSTRONG | 2022-10-24 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.26667 | 1 | 21.71 | 15.21 | 0 | 6.5 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22140567000 |  | 100431704 |  | 6720212A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BROADWAY | 734 N BROADWAY ST 4 | 067 | LEX | 2022-10-24 | RSTRONG | U125208 | 2022-10-21 | 2022-09-27 |  |  | RSTRONG | 2022-10-24 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.28333 | 1 | 22.52 | 15.78 | 0 | 6.74 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22140567100 |  | 100431937 |  | 6720212A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BROADWAY | 734 N BROADWAY ST 5 | 067 | LEX | 2022-10-24 | RSTRONG | U125208 | 2022-10-21 | 2022-09-27 |  |  | RSTRONG | 2022-10-24 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.35 | 1 | 28.15 | 19.72 | 0 | 8.43 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22140708800 |  | 100278233 |  | 6688228A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SCHENKEL | 500 SCHENKEL LN | 073 | FRA | 2022-10-24 | DCOLLIN | U129939 | 2022-10-24 | 2022-10-24 |  |  | DCOLLIN | 2022-10-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 4.7167 | 1 | 2879.83 | 296.59 | 226.4 | 212.06 | 2144.78 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22140721900 |  | 500112747 |  | 7236212L |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | IROQUOIS | 1084 IROQUOIS DR | 173 | MT | 2022-10-25 | U126285 | U125763 | 2022-10-24 | 2022-12-30 |  |  | DDAVIS | 2022-10-24 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.5 | 1 | 1902.93 | 258.98 | 0 | 15.39 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22140756500 |  | 100410167 |  | 6684228D |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | REILLY | 67 REILLY RD | 073 | FRA | 2022-10-24 | DCOLLIN | U129939 | 2022-10-24 | 2022-10-24 |  |  | DCOLLIN | 2022-10-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.65 | 1 | 4415.19 | 357.29 | 273.84 | 255.43 | 3528.63 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979024000 |  | 100261606 |  | 7352256H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CYPRESS | 1406 CYPRESS ST | 019 | ASH | 2022-11-23 | U125566 | U128070 | 2022-02-17 | 2022-10-24 |  |  | DESKAGG | 2022-10-24 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.65 | 1 | 1643.04 | 152.27 | 0 | 32.07 | 1458.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22987756100 |  | 100350493 |  | 6744204C | 2182509 |  |  | 565 | EX | REPLACE SL W/22-0261585-00 | 2600B | HOOD | 109 HOOD AV | 049 | WIN | 2022-10-28 | U125208 | U134723 | 2022-03-22 | 2022-10-24 | 2022-10-24 |  | DENNING | 2022-10-24 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 21.8833 | 4 | 1865.58 | 1354.45 | 374.48 | 80.55 | 56.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 07691241500 |  | 100413088 |  | V-1222-28 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | OLDFIELD TRAIL | 118 OLDFIELD TRAIL CT LT12 | 173 | MT | 2022-10-25 | U126285 | U903504 | 2007-06-18 | 2022-07-01 | 2022-12-31 |  | DDAVIS | 2022-10-25 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.5 | 1 | 1239.54 | 201.45 | 0 | 11.97 | 1026.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 10872748400 |  | 100417715 |  | V-1227/41 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SOUTHDALE | 121 SOUTHDALE DR | 173 | MT | 2022-10-25 | U126284 | U906609 | 2010-12-17 | 2022-06-30 | 2022-12-31 |  | JOSH PASLEY | 2022-10-25 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.9 | 1 | 1515.56 | 288.94 | 0 | 200.5 | 1026.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11883974100 |  | 100270335 |  | 6736252M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | PIKE | 133 E PIKE ST | 097 | CYN | 2022-10-25 | U129722 | U906307 | 2011-02-03 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-10-25 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 2162.97 | 438.82 | 0 | 95.59 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 14265203800 |  | 100271450 |  | 6736252N |  |  |  | 565 | EX | SERVICE LINE - REPLACE UNMTRD | 2621P | TAYLOR | 109 TAYLOR DR | 097 | CYN | 2022-10-25 | NRICHIE | DMCCULL | 2014-11-18 | 2015-05-01 | 2022-12-31 |  | NRICHIE | 2022-10-25 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 23 | 3 | 2418.62 | 1339.67 | 272.75 | 691.8 | 114.4 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883072600 |  | 100348638 |  | 6748208M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WASHINGTON | 161 E WASHINGTON ST A | 049 | WIN | 2022-10-26 | U123111 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | LYN STAFFORD | 2022-10-25 | 2022-10-25 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.8 | 2 | 1995.61 | 212.64 | 0 | 154.41 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883086300 |  | 500493964 |  | 7240204G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEVEE | 8205< LEVEE RD | 173 | MT | 2022-10-28 | U126308 | U120245 | 2021-01-30 | 2022-10-25 | 2022-12-31 |  | J ENSMINGER | 2022-10-25 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.1167 | 1 | 2535.76 | 176.43 | 0 | 128.33 | 2231 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883089100 |  | 100348555 |  | 6748208I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | WINN | 263 WINN AV | 049 | WIN | 2022-10-25 | U129731 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-10-25 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 2196.51 | 470.49 | 0 | 97.46 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883132800 |  | 100343832 |  | 7240204G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEVEE | 7075 LEVEE RD | 173 | MT | 2022-11-07 | U126308 | U120245 | 2021-01-30 | 2022-10-25 | 2022-12-31 |  | JENSMINGER | 2022-10-25 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.2167 | 2 | 1866.38 | 123.25 | 0 | 89.63 | 1653.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883151500 |  | 100249584 |  | 7360212T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | HIGHWAY 644 | 744 HIGHWAY 644 | 127 | LOU | 2022-10-25 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-10-25 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.9167 | 1 | 1551.27 | 119.03 | 0 | 23.87 | 1408.37 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883224500 |  | 100427894 |  | 7360212T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BOW BRANCH | 68 BOW BRANCH RD | 127 | LOU | 2022-10-26 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-10-25 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.5 | 1 | 1222.91 | 154.19 | 0 | 30.88 | 1037.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883248100 |  | 100348718 |  | 6748208M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WASHINGTON | 233 E WASHINGTON ST | 049 | WIN | 2022-10-25 | U129731 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-10-25 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883267400 |  | 100249585 |  | 7360212T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | HWY 644 | 624 HWY 644 | 127 | LOU | 2022-10-26 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-10-25 | 2022-10-24 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 6.45 | 2 | 2404.76 | 397.78 | 0 | 79.69 | 1927.29 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883283200 |  | 100461519 |  | 7236212G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | PREWITT | 571 PREWITT PK | 173 | MT | 2022-10-25 | U126532 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | LESLIE SHARON | 2022-10-25 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10 | 1 | 3639.67 | 573.73 | 0 | 34.1 | 3031.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883308000 |  | 100343841 |  | 7240204G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEVEE | 7445 LEVEE RD | 173 | MT | 2022-10-26 | U126603 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | SHAWN DENNIS | 2022-10-25 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21884271100 |  | 100343523 |  | 7240212A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SPRING | 403 SPRING ST 2F | 173 | MT | 2022-10-25 | U126284 | U128293 | 2021-02-04 | 2022-07-01 | 2022-12-31 |  | JOSH PASLEY | 2022-10-25 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.1 | 1 | 2311.03 | 300.74 | 0 | 208.67 | 1801.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960235600 |  | 100320943 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | HIGH | 476 E HIGH ST | 067 | LEX | 2022-10-25 | U128410 | U134723 | 2021-12-17 | 2022-12-30 |  |  | CDESPAIN | 2022-10-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2270.46 | 0 | 0 | 0 | 2270.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960238900 |  | 100320981 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | MAXWELL | 463 E MAXWELL ST | 067 | LEX | 2022-10-28 | U461375 | U134723 | 2021-12-17 | 2022-12-30 |  |  | LARRY BROWN | 2022-10-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2552.6 | 0 | 0 | 0 | 2552.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22026206200 |  |  |  | 7256280N | 2289591 | U122858 |  | 557 | EX | INSTALL 33'-2" PMIP | 2600B | RT 62 | RT 62 | 161 | MAY | 2022-11-01 | U131995 | U122858 | 2022-06-18 | 2022-11-17 | 2022-11-30 | 2022-10-06 | DAVID STAGGS | 2022-10-25 | 2022-09-23 |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00557 | 3200557 |  |  | WP2062 | AMRCB |  | 100 | 055732220262062 | 84.9167 | 247 | 37112.14 | 5415.84 | 4214.73 | 1044.43 | 22826.91 | 0 | 46.77 | 3563.46 | 19
KY | KY - WEST | 2623 | 22119123600 |  | 100283066 |  | 6712228C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303135 | 2621P | CLAYTON | 620 CLAYTON AV | 209 | GEO | 2022-10-25 | BWHITE | U125208 | 2022-07-28 | 2022-10-20 | 2024-07-31 |  | BWHITE | 2022-10-25 | 2022-10-20 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 9.9667 | 2 | 1386.05 | 615.67 | 117.5 | 36.58 | 616.3 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22126717800 |  | 100282859 |  | 6712228C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303167 | 2621P | FOUNTAIN | 515 FOUNTAIN AV | 209 | GEO | 2022-10-25 | BWHITE | U125208 | 2022-08-25 | 2022-10-20 | 2024-08-31 |  | BWHITE | 2022-10-25 | 2022-10-20 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.3333 | 2 | 919.52 | 454.79 | 117.5 | 27.03 | 320.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129023400 |  | 500126019 |  | 6736252I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | US 27 S | 734 US 27 S | 097 | CYN | 2022-10-25 | U129722 | U130722 | 2022-09-05 | 2022-12-30 |  |  | M YOUNG | 2022-10-25 | 2022-10-21 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.5 | 1 | 3714.25 | 495.37 | 0 | 29.44 | 3189.44 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129026400 |  | 100343833 |  | 7240204G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LEVEE | 7095 LEVEE RD | 173 | MT | 2022-11-07 | U126308 | U130722 | 2022-09-05 | 2022-10-25 |  |  | J ENSMINGER | 2022-10-25 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.6667 | 2 | 1476.01 | 260.45 | 0 | 189.44 | 1026.12 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129039100 |  | 100419210 |  | 7344268P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CHERYLL ANN | 832 CHERYLL ANN CT | 089 | WOR | 2022-10-28 | U127414 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ED FOX | 2022-10-25 | 2022-10-25 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.8667 | 1 | 1817.11 | 352.48 | 0 | 72.13 | 1392.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129039200 |  | 100259678 |  | 7348268N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MARKET | 1112 MARKET ST | 089 | WOR | 2022-10-26 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-10-25 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 12 | 1 | 1905.9 | 699.33 | 0 | 41.57 | 1165 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129063800 |  | 100343073 |  | 7240212A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WINCHESTER | 489 WINCHESTER RD | 173 | MT | 2022-10-25 | U126532 | U130722 | 2022-09-05 | 2022-12-30 |  |  | LESLIE SHARON | 2022-10-25 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2635.63 | 0 | 0 | 0 | 2635.63 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129076000 |  | 100258139 |  | 7348268M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 3RD | 436 3RD AV | 089 | WOR | 2022-11-03 | U127414 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ED FOX | 2022-10-25 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 6.1333 | 1 | 2055.49 | 365.65 | 0 | 74.84 | 1615 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129076100 |  | 100259679 |  | 7348268N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MARKET | 1104 MARKET ST | 089 | WOR | 2022-10-28 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-10-25 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 10.5 | 1 | 2008.29 | 611.92 | 0 | 36.37 | 1360 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129082200 |  | 100290569 |  | 6720216L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OLD PARIS | 2111 OLD PARIS RD | 067 | LEX | 2022-10-25 | MCRAIG | U130722 | 2022-09-05 | 2022-12-30 |  |  | MCRAIG | 2022-10-25 | 2022-10-17 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 18.4167 | 7 | 1168.62 | 883.06 | 34.04 | 251.52 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22139085800 |  | 500192709 |  | 7236212L |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | MCCROSKY | 1308 MCCROSKY WY | 173 | MT | 2022-10-26 | U930915 | U132002 | 2022-10-14 | 2022-10-27 | 2022-11-12 |  | DENNING | 2022-10-25 | 2022-10-24 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.2333 | 4 | 542.73 | 512.28 | 0 | 30.45 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22140593800 |  | 100347255 |  | 6696212K |  |  |  | 565 | EX | SERV LINE REPLACE | 2621P | MACK | 101 MACK ST | 239 | VER | 2022-10-25 | BWHITE | U136097 | 2022-10-21 | 2022-10-21 |  |  | BWHITE | 2022-10-25 | 2022-10-21 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 9.2 | 2 | 1340.74 | 569.3 | 192.19 | 33.85 | 545.4 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22140957400 |  | 100265049 |  | 7352260O | 2176770 |  |  | 565 | EX | RPLC SL/21026993400 | 2600B | MAIN | 1925 MAIN ST | 019 | ASH | 2022-10-25 | U124015 | U125768 | 2022-10-25 | 2049-12-31 |  |  | ORA SLONE | 2022-10-25 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2451.41 | 42.82 | 0 | 2.62 | 2405.97 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22140978300 |  | 100288991 |  | 6720212D |  |  |  | 565 | EX | SERVICE LINE - REPLACE D094371 | 2621P | SANDALWOOD | 404 SANDALWOOD DR | 067 | LEX | 2022-10-28 | U125208 | U129939 | 2022-10-25 | 2022-10-25 | 2022-10-25 |  | LSTANFI | 2022-10-25 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.8667 | 2 | 608.97 | 298.3 | 234.63 | 17.74 | 58.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22140979600 |  | 500012446 |  | 6720204M |  |  |  | 565 | EX | SERVICE LINE - REPLACE D311120 | 2621P | ROCKBRIDGE | 1143 ROCKBRIDGE RD | 067 | LEX | 2022-10-28 | U125208 | U129939 | 2022-10-25 | 2022-10-25 | 2022-10-25 |  | WISHII | 2022-10-25 | 2022-10-25 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 27.4833 | 4 | 2042.82 | 1382.82 | 183.96 | 364.94 | 111.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22141045700 |  | 100347201 |  | 6696212J |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | CLIFTON | 511 CLIFTON RD | 239 | VER | 2022-10-25 | DCOLLIN | U129939 | 2022-10-25 | 2022-10-28 | 2022-11-15 |  | DCOLLIN | 2022-10-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.7333 | 1 | 2350.98 | 173.93 | 395.56 | 10.35 | 1771.14 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979021000 |  | 100253309 |  | 7360232T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CUB | 175 CUB LN | 127 | CAT | 2022-10-25 | U126604 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | WILL FULKS | 2022-10-25 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.55 | 1 | 1448.71 | 342.3 | 0 | 68.57 | 1037.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979039600 |  | 100343824 |  | 7240208E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LEVEE | 5060 LEVEE RD | 173 | MT | 2022-10-26 | U126603 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | SHAWN DENNIS | 2022-10-25 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1991.15 | 0 | 0 | 0 | 1991.15 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979041400 |  | 100348898 |  | 6748208M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WASHINGTON | 170 E WASHINGTON ST | 049 | WIN | 2022-10-26 | U123111 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | LYN STAFFORD | 2022-10-25 | 2022-10-25 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.1833 | 2 | 2039.25 | 237.92 | 0 | 172.77 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979047600 |  | 100443674 |  | 7240208E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LEVEE | 4960 LEVEE RD | 173 | MT | 2022-10-26 | U126603 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | SHAWN DENNIS | 2022-10-25 | 2022-10-25 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10.5 | 1 | 2233.37 | 626.93 | 0 | 128.49 | 1477.95 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979054300 |  | 500615741 |  | 7240204G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LEVEE | 8290 LEVEE RD | 173 | MT | 2022-10-25 | DENNING | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | DENNING | 2022-10-25 | 2022-10-19 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9.1667 | 4 | 748.95 | 567.42 | 0 | 181.53 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22984457300 |  | 500711114 |  | 7240216O | 9937553 |  |  | 566 | EX | ABANDON SL- I/I/LGCY | 2600B | CREEKSIDE | 205 CREEKSIDE CR | 173 | MT | 2022-10-25 | U126285 | U134723 | 2022-03-08 | 2022-12-30 |  |  | DDAVIS | 2022-10-25 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.5 | 1 | 1300.48 | 258.97 | 0 | 15.39 | 1026.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23154578600 |  | 500976743 |  | 6748208M |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | WASHINGTON | 161 E WASHINGTON ST B | 049 | WIN | 2023-01-12 | U125559 | U125763 | 2023-01-10 | 2023-12-29 |  |  | LYN STAFFORD | 2022-10-25 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - CENTRAL | 2632 | 07679058700 |  | 100354225 |  | 7256280P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | MARKET | 325< MARKET ST | 161 | MAY | 2022-10-26 | SDADAMS | DMCCULL | 2007-03-15 | 2022-07-01 | 2022-12-31 |  | SDADAMS | 2022-10-26 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 5.8667 | 4 | 398.89 | 282.24 | 0 | 116.65 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 08735936000 |  | 500345328 |  | V-1227/1 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | ELAINE | 251 ELAINE DR | 173 | MT | 2022-10-26 | U126284 | SSUTHER | 2008-06-20 | 2022-07-01 | 2022-12-31 |  | JOSH PASLEY | 2022-10-26 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.8667 | 1 | 1513.58 | 287.79 | 0 | 199.67 | 1026.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11878259800 |  | 100342943 |  | 7240212B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAIN | 209 W MAIN ST | 173 | MT | 2022-10-26 | U129731 | U906609 | 2011-01-10 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-10-26 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 2196.51 | 470.49 | 0 | 97.46 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11916627900 |  | 500186455 |  | 7236212C |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WINCHESTER | 1801 WINCHESTER RD | 173 | MT | 2022-10-26 | U126285 | U124964 | 2011-07-20 | 2022-07-01 | 2022-12-31 |  | DDAVIS | 2022-10-26 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9 | 2 | 2177.27 | 517.93 | 0 | 30.78 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11919327800 |  | 100467037 |  | 6748208M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WASHINGTON | 419 E WASHINGTON ST 4 | 049 | WIN | 2022-10-26 | U123111 | U907469 | 2011-08-08 | 2022-07-01 | 2022-12-31 |  | LYN STAFFORD | 2022-10-26 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.8333 | 1 | 1998.52 | 214.33 | 0 | 155.63 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 13127390900 |  | 100348854 | 07 | 6748208N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WASHINGTON | 409 E WASHINGTON ST | 049 | WIN | 2022-10-26 | U123111 | SGRIFFE | 2013-04-01 | 2022-07-01 | 2022-12-31 |  | LYN STAFFORD | 2022-10-26 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.0167 | 1 | 2015.98 | 224.44 | 0 | 162.98 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 17569042200 |  | 500877896 |  | 7240204G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | LEVEE | 7820 LEVEE RD | 173 | MT | 2022-10-26 | U126603 | U125765 | 2017-12-20 | 2022-10-25 | 2022-12-31 |  | SHAWN DENNIS | 2022-10-26 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.8667 | 1 | 2054.98 | 291.39 | 0 | 59.73 | 1703.86 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19688245600 |  | 100460861 |  | 7256280P |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | 4TH | 5 W 4TH ST UPS | 161 | MAY | 2022-10-26 | SDADAMS | U125208 | 2019-03-14 | 2019-04-04 |  |  | SDADAMS | 2022-10-26 | 2022-07-15 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 0.73333 | 2 | 48.07 | 45.4 | 0 | 2.67 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 20862339200 |  | 500204687 |  | X |  |  |  | 566 | EX | REMOVE SETTING/REG - HP TCO | 2621P | LONAKER | 183 LONAKER LN | 023 | BRO | 2022-11-11 | U461383 | U125208 | 2020-11-24 | 2020-11-30 |  |  | SDADAMS | 2022-10-26 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 2.4833 | 1 | 160.54 | 151.54 | 0 | 9 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883052900 |  | 501197139 |  | 6716204F | 1639493 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LARUE | 251 LARUE DR | 067 | LEX | 2022-10-26 | LSTANFI | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | LSTANFI | 2022-10-26 | 2022-10-24 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 14.0167 | 4 | 947.58 | 845.98 | 19.59 | 82.01 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883078200 |  | 100459880 |  | 7240216O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAIN | 428 E MAIN ST | 173 | MT | 2022-10-26 | U129731 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-10-26 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883236400 |  | 100343243 |  | 7236212G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WINCHESTER | 2092 WINCHESTER RD | 173 | MT | 2022-10-27 | U126285 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DDAVIS | 2022-10-26 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 7 | 2 | 2055.39 | 402.89 | 0 | 23.94 | 1628.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883253000 |  | 100257735 |  | 7344268-O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | RIVERSIDE | 2105 RIVERSIDE DR | 089 | WUR | 2022-10-26 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-10-26 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 10 | 1 | 5031.84 | 616.73 | 0 | 123.56 | 4291.55 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883296700 |  | 100415560 |  | 7244216I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | EUBANK TRAILER | 81 EUBANK TRAILER PR | 173 | MT | 2022-10-27 | U129722 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-10-26 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1703.86 | 0 | 0 | 0 | 1703.86 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21884179100 |  | 500263969 |  | 7240204G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEVEE | 8585 LEVEE RD | 173 | MT | 2022-10-26 | U126308 | U128293 | 2021-02-04 | 2022-10-24 | 2022-12-31 |  | J ENSMINGER | 2022-10-26 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9.5 | 1 | 1945.27 | 532.12 | 0 | 387.03 | 1026.12 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916436100 |  | 100413917 |  | 7352260O | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2025< MAIN ST W | 019 | ASH | 2022-10-26 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLOEN | 2022-10-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2034.54 | 0 | 0 | 0 | 2034.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959035000 |  | 100404843 |  | 6716212O | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | LIMESTONE | 700 S LIMESTONE ST | 067 | LEX | 2022-10-26 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-10-26 | 2022-10-24 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 28.25 | 3 | 7540.55 | 1593.69 | 0 | 340.2 | 5606.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959039800 |  | 100315440 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | WALLER | 114 WALLER AV | 067 | LEX | 2022-10-26 | U128336 | U134723 | 2021-12-10 | 2022-12-30 |  |  | JOSHUA COX | 2022-10-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10 | 1 | 1709.37 | 601.87 | 0 | 35.8 | 1071.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960253900 |  | 100320947 |  | 6720212M | 2176779 |  |  | 566 | EX | ABANDON SL W/CAPTIOL JOB | 2600B | HIGH | 492 E HIGH ST | 067 | LEX | 2022-10-27 | U128410 | U134723 | 2021-12-17 | 2022-12-30 |  |  | CDESPAIN | 2022-10-26 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1 | 2850.43 | 0 | 0 | 0 | 2850.43 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129003700 |  | 100432390 |  | 7240216O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 654 E MAIN ST | 173 | MT | 2022-10-27 | U129731 | U130722 | 2022-09-05 | 2022-12-30 |  |  | F.GOINS | 2022-10-26 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 479.22 | 0 | 0 | 0 | 479.22 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129008500 |  | 100343876 |  | 7240216O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OLD HIGHWAY 11 | 140 OLD HIGHWAY 11 | 173 | JEF | 2022-10-26 | U124003 | U130722 | 2022-09-05 | 2022-12-30 |  |  | BPULLIAM/MILLER | 2022-10-26 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.45 | 1 | 1242.41 | 28.08 | 0 | 37.6 | 1176.73 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129035400 |  | 100254162 |  | 7348264N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | COLLINS | 1413 W COLLINS ST | 089 | FLA | 2022-10-26 | U127414 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ED FOX | 2022-10-26 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.9167 | 1 | 1787.53 | 354.91 | 0 | 72.62 | 1360 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129037900 |  | 100239610 |  | 7348264L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | POPLAR | 108 POPLAR ST | 089 | RUS | 2022-11-07 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-10-26 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1360 | 0 | 0 | 0 | 1360 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129039000 |  | 100258147 |  | 7348268M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 4TH | 401 4TH AV | 089 | WOR | 2022-11-03 | U127414 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ED FOX | 2022-10-26 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 6.0833 | 1 | 1797.59 | 363.25 | 0 | 74.34 | 1360 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129063100 |  | 100342598 |  | 7240216N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ANTWERP | 201 ANTWERP AV | 173 | MT | 2022-10-26 | U126284 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JOSH PASLEY | 2022-10-26 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.1333 | 1 | 2256.38 | 301.94 | 0 | 209.49 | 1744.95 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22140947100 |  | 100460477 |  | 6744208P |  |  |  | 566 | EX | PAPER ABANDON | 2621P | LEXINGTON | 406 W LEXINGTON AV 2F | 049 | WIN | 2022-10-26 | DENNING | U129939 | 2022-10-25 | 2022-10-25 |  |  | DENNING | 2022-10-26 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 6.75 | 3 | 443.04 | 418.11 | 0 | 24.93 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22141158000 |  | 100282481 |  | 6712228C |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | MILITARY | 112 MILITARY ST A | 209 | GEO | 2022-10-26 | DCOLLIN | U129939 | 2022-10-26 | 2022-10-26 |  |  | DCOLLIN | 2022-10-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 1 | 3796.44 | 505.91 | 410.22 | 202.09 | 2678.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22141187700 |  | 500144656 |  | 6720212M | 2176779 |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | MAXWELL | 475 E MAXWELL ST 2FL | 067 | LEX | 2022-10-26 | U128410 | U129939 | 2022-10-26 | 2022-10-26 |  |  | CDESPAIN | 2022-10-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 2286.72 | 0 | 0 | 0 | 2286.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22141207100 |  | 500070119 |  | 6720204M |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | TANBARK | 1040 TANBARK RD | 067 | LEX | 2022-10-26 | U930915 | U129939 | 2022-10-26 | 2022-10-21 | 2022-11-10 |  | LSTANFI | 2022-10-26 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 5.2 | 2 | 962.33 | 611.14 | 194.04 | 57.05 | 100.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979039700 |  | 100343881 |  | 7240216O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OLD HIGHWAY 11 | 160 OLD HIGHWAY 11 | 173 | JEF | 2022-10-26 | U124003 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | BPULLIAM/MILLER | 2022-10-26 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9.55 | 1 | 2930.36 | 556.48 | 0 | 745.32 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979046900 |  | 100433664 |  | 7240204G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LEVEE | 7750 LEVEE RD | 173 | MT | 2022-10-26 | U126603 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | SHAWN DENNIS | 2022-10-26 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 6.1333 | 1 | 3095.27 | 365.41 | 0 | 74.9 | 2654.96 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22984728700 |  | 100463123 |  | 7240216O |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2600B | FOX | 2790 FOX RD | 173 | MT | 2022-10-27 | U129722 | U134723 | 2022-03-09 | 2022-12-30 |  |  | M YOUNG | 2022-10-26 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 2549.96 | 438.82 | 0 | 95.59 | 2015.55 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 06660741500 |  | 100271103 | 22 | 7 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PEA RIDGE | 350 PEA RIDGE | 023 | AUG | 2022-10-27 | U930915 | DBURFOR | 2006-09-20 | 2020-12-31 |  |  | SDADAMS | 2022-10-27 | 2022-10-26 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 2.4833 | 2 | 161.24 | 152.18 | 0 | 9.06 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11916294500 |  | 100343354 |  | V-1221/48 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAIN | 438 W MAIN ST | 173 | MT | 2022-10-28 | U126603 | U124964 | 2011-07-18 | 2022-07-01 | 2022-12-31 |  | SHAWN DENNIS | 2022-10-27 | 2022-10-27 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.65 | 1 | 2289.5 | 335.57 | 0 | 68.77 | 1885.16 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 14270170300 |  | 100341594 |  | 7240216O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MILLROW | 39 MILLROW ST | 173 | MT | 2022-10-27 | U126308 | U122906 | 2014-12-11 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-10-27 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 513.2 | 0 | 0 | 0 | 513.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 16415195500 |  | 100352544 |  | 6744204F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BOONESBORO | 2000 BOONESBORO RD | 049 | WIN | 2022-11-16 | U123111 | SPENDLE | 2016-06-07 | 2022-07-01 | 2022-12-31 |  | LYN STAFFORD | 2022-10-27 | 2022-11-01 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 14.1333 | 4 | 12547.43 | 827.28 | 0 | 106.06 | 11614.09 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883057200 |  | 100255169 |  | 7344156T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | HANNAHS | 65 HANNAHS BR | 071 | MAR | 2022-10-31 | U461383 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-10-27 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1 | 741.06 | 0 | 0 | 0 | 741.06 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883072900 |  | 500566852 |  | 6700212M | 9721521 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MARTIN | 492 MARTIN DR | 239 | VER | 2022-11-15 | U127206 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-10-27 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8 | 1 | 2123.29 | 426.64 | 0 | 25.37 | 1671.28 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883097800 |  | 100345063 |  | 6696212G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | ELM | 167 ELM ST | 239 | VER | 2022-10-27 | U127206 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-10-27 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1853.07 | 0 | 0 | 0 | 1853.07 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883104600 |  | 100348631 |  | 6748208M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | HIGHLAND | 111 N HIGHLAND ST | 049 | WIN | 2022-10-28 | U129731 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-10-27 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 16 | 2 | 5678.38 | 940.96 | 0 | 125.42 | 4612 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883164300 |  | 100437029 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2633S | HUNTER BRANCH | 478 HUNTER BRANCH RD | 071 | GAR | 2022-11-22 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-10-27 |  |  | B | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 5.5333 | 1 | 2631.88 | 340.49 | 0 | 68.21 | 2223.18 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883232700 |  | 100345916 |  | 6704208A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | LILAC | 309 LILAC CT | 239 | VER | 2022-10-27 | U126602 | U120245 | 2021-01-30 | 2022-10-24 | 2022-12-31 |  | DEREK PAYTON | 2022-10-27 | 2022-10-24 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 15.2833 | 2 | 2247.11 | 829.5 | 0 | 49.3 | 1368.31 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883261200 |  | 100345452 |  | 6696212H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | DOUGLAS | 244 DOUGLAS AV | 239 | VER | 2022-10-27 | U126602 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DEREK PAYTON | 2022-10-27 | 2022-10-24 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 2.9333 | 2 | 2898.99 | 160.14 | 0 | 9.5 | 2729.35 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883290200 |  | 100352484 |  | 6748204E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MUDDY CREEK | 1999 MUDDY CREEK RD | 049 | WIN | 2022-10-28 | U126308 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-10-27 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 3005.02 | 448.11 | 0 | 325.91 | 2231 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883303700 |  | 100341141 |  | 7240216O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | OLDFIELD TRAIL | 13 OLDFIELD TRAIL CT | 173 | MT | 2022-10-27 | U126284 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JOSH PASLEY | 2022-10-27 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.05 | 1 | 2132.97 | 297.81 | 0 | 206.6 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883308800 |  | 500022714 |  | 6748204A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | HAMILTON | 343 HAMILTON ST LT4 | 049 | WIN | 2022-10-27 | U126285 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DDAVIS | 2022-10-27 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21884219200 |  | 100452932 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | ROCK FORK | 526 ROCK FORK RD | 071 | GAR | 2022-10-27 | U126604 | U128293 | 2021-02-04 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-10-27 |  |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 4.4667 | 1 | 1813.74 | 276.26 | 0 | 55.36 | 1482.12 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916436300 |  | 100265039 |  | 7352260O | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2029 MAIN ST W | 019 | ASH | 2022-10-27 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-10-27 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2508 | 0 | 0 | 0 | 2508 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959039700 |  | 100315441 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | WALLER | 110 WALLER AV | 067 | LEX | 2022-10-27 | U128336 | U134723 | 2021-12-10 | 2022-12-30 |  |  | JOSHUA COX | 2022-10-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10 | 1 | 2621.49 | 601.85 | 0 | 35.77 | 1983.87 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959041200 |  | 100315422 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | WALLER | 220 WALLER AV | 067 | LEX | 2022-10-27 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-10-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.5 | 3 | 2429.14 | 924.4 | 0 | 442.42 | 1062.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960239100 |  | 100320979 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | MAXWELL | 473 E MAXWELL ST | 067 | LEX | 2022-10-28 | U461375 | U134723 | 2021-12-17 | 2022-12-30 |  |  | LARRY BROWN | 2022-10-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3166.29 | 0 | 0 | 0 | 3166.29 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026167600 |  |  |  | 6716208L | 2286549 | U461383 |  | 557 | EX | INSTALL 6' OF 3"PMLP MAIN | 2621P | ALBANY | 595 ALBANY RD | 067 | LEX | 2022-11-03 | U124014 | U461383 | 2022-02-14 | 2022-10-27 | 2022-10-31 | 2022-10-26 | RJCRAWF | 2022-10-27 | 2022-09-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP1676 |  |  | 100 | 055732220261676 | 63.2167 | 52 | 8748.35 | 3857.7 | 2120.87 | 263.4 | 1552.5 | 0 | 43.09 | 910.79 | 4
KY | KY - WEST | 2621 | 22026167700 |  |  |  | 6716208L | 2286549 | U461383 |  | 558 | EX | RETIRE 6' OF 3"CSLP MAIN | 2621P | ALBANY | 595 ALBANY RD | 067 | LEX | 2022-11-03 | U124014 | U461383 | 2022-02-14 | 2022-10-31 | 2022-10-31 | 2022-10-26 | RJCRAWF | 2022-10-27 | 2022-10-24 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP1677 |  |  | 100 | 055832220261677 | 56.7667 | 0 | 9674.55 | 3407.1 | 0 | 800.97 | 5466.48 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22026218500 |  | 501335119 |  | 7352264E | 2290090 | U132280 |  | 555 | EX | INSTALL 35'-2"/4 PMLP | 2621P | BELLEFONTE | 508 BELLEFONTE ST A | 089 | RUS | 2023-05-04 | U132743 | U132280 | 2022-08-16 | 2022-10-11 | 2022-10-15 | 2022-09-07 | MCOLLET | 2022-10-27 | 2022-09-07 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP2185 |  |  | 100 | 055532220262185 | 59.5167 | 546 | 8610.21 | 3999.75 | 1489.2 | 1812.15 | 42.9 | 0 | 7.35 | 1258.86 | 39
KY | KY - WEST | 2623 | 22124637200 |  | 100279447 |  | 6688224C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303161 | 2621P | INVERNESS | 974 INVERNESS RD | 073 | FRA | 2022-10-27 | DCOLLIN | U125208 | 2022-08-17 | 2022-10-27 | 2024-08-31 |  | DCOLLIN | 2022-10-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.35 | 1 | 3049.95 | 149.25 | 416.31 | 106.73 | 2377.66 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129008600 |  | 100343356 |  | 7240212A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 430 W MAIN ST | 173 | MT | 2022-10-28 | U126603 | U130722 | 2022-09-05 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-10-27 | 2022-10-27 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.35 | 1 | 2328.61 | 261.55 | 0 | 53.6 | 2013.46 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129008700 |  | 100446816 |  | 7240212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 6 W MAIN ST | 173 | MT | 2022-10-27 | U126284 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JOSH PASLEY | 2022-10-27 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.95 | 1 | 1923.23 | 173.97 | 0 | 120.7 | 1628.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129073200 |  | 100254345 |  | 7348264O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HAMER | 1301 HAMER ST | 089 | FLA | 2022-10-31 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-10-27 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 24 | 2 | 3991.78 | 1398.64 | 0 | 83.14 | 2510 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129121300 |  | 100253939 |  | 7348264N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GREENBO | 2614 GREENBO BV | 089 | FLA | 2022-11-03 | U127414 | U125208 | 2022-09-06 | 2022-12-30 |  |  | ED FOX | 2022-10-27 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 12 | 1 | 2219.04 | 712.08 | 0 | 146.96 | 1360 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22135700100 |  | 100240660 |  | 7328284D |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTREQD | 2621P | ELIZABETH | 6 ELIZABETH LN | 089 | S S | 2022-10-27 | RECUMP | U125208 | 2022-09-29 | 2022-10-05 | 2022-10-20 |  | RECUMP | 2022-10-27 | 2022-10-27 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 11.0333 | 2 | 895.25 | 660.17 | 41.41 | 193.67 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22136145500 |  | 100281160 |  | 6692224E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303173 | 2621P | SHADY | 825 SHADY LN | 239 | MID | 2022-10-27 | DCOLLIN | U125208 | 2022-09-30 | 2022-10-27 | 2024-09-30 |  | DCOLLIN | 2022-10-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.0833 | 1 | 3145.94 | 447.09 | 206.68 | 319.65 | 2172.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22139914900 |  | 100330185 |  | 6720212O |  |  |  | 565 | EX | SERVICE LINE - REPLACE/MMO | 2621P | QUEENSWAY | 414 QUEENSWAY DR | 067 | LEX | 2022-10-27 | RSTRONG | U125208 | 2022-10-19 | 2022-10-21 | 2022-10-26 |  | RSTRONG | 2022-10-27 | 2022-10-26 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.3 | 3 | 1005.29 | 774.17 | 125.68 | 46.04 | 59.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22140745100 |  | 100465813 |  | 6720204M |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311119 | 2621P | CROSBY | 3945 CROSBY DR | 067 | LEX | 2022-10-28 | U930915 | U125208 | 2022-10-24 | 2022-10-27 | 2022-11-14 |  | LSTANFI | 2022-10-27 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16 | 2 | 1510.41 | 978.1 | 195.05 | 223.96 | 113.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22141350700 |  | 100310045 |  | 6716208E |  |  |  | 565 | EX | GRADE 1 REPLACE SERVICE LINE | 2621P | SHERIDAN | 653 SHERIDAN DR | 067 | LEX | 2022-10-27 | MCRAIG | U129939 | 2022-10-27 | 2022-10-27 | 2022-10-27 |  | MCRAIG | 2022-10-27 | 2022-10-27 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 33.0333 | 4 | 3042.25 | 1749.93 | 561.99 | 432.35 | 297.98 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22976456400 |  | 100344426 |  | 7240212C |  |  |  | 566 | EX | ABANDON SL - IDLE/INA **RUSH** | 2621P | LOCUST | 615 E LOCUST ST | 173 | MT | 2022-10-27 | U126308 | U125208 | 2022-02-04 | 2022-02-23 |  |  | J ENSMINGER | 2022-10-27 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10 | 1 | 1993.65 | 560.14 | 0 | 407.39 | 1026.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979038600 |  | 100341794 |  | 7240216O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | QUEEN | 209 N QUEEN ST | 173 | MT | 2022-10-27 | U126308 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | J ENSMINGER | 2022-10-27 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2231 | 0 | 0 | 0 | 2231 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979039900 |  | 100344426 |  | 7240212C |  |  |  | 566 | VO | ABANDON SL - IDLE/INACTIVE | 2621P | LOCUST | 615 E LOCUST ST | 173 | MT | 2022-10-27 |  | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | J ENSMINGER | 2022-10-27 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - CENTRAL | 2629 | 22979042700 |  | 100352001 |  | 6748204C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | AUBREY | 225 AUBREY LN | 049 | WIN | 2022-10-27 | U124003 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | BPULLIAM/MILLER | 2022-10-27 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10 | 1 | 4303.01 | 584.53 | 0 | 782.91 | 2935.57 | 0 | 0 | 0
KY | KY - WEST | 2623 | 06640903000 |  | 100346310 | 12 | 6696212L | 1639457 |  |  | 566 | EX | ABANDON SL - CAPITAL PROJ | 2600B | SIMMONS | 124 SIMMONS ST | 239 | VER | 2022-10-28 | U126602 | BURCHET | 2006-03-08 | 2022-07-01 | 2022-12-31 |  | DEREK PAYTON | 2022-10-28 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1368.31 | 0 | 0 | 0 | 1368.31 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 17569047600 |  | 100343120 |  | 7240212A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WINCHESTER | 674 WINCHESTER RD 1FFT | 173 | MT | 2022-11-08 | U126603 | U125765 | 2017-12-20 | 2022-07-01 | 2022-12-31 |  | SHAWN DENNIS | 2022-10-28 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 6.7833 | 2 | 1906.31 | 396.07 | 0 | 182.9 | 1327.34 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 17569047700 |  | 100343118 |  | 7240212A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WINCHESTER | 674 WINCHESTER RD 1FR | 173 | MT | 2022-10-28 | U126603 | U125765 | 2017-12-20 | 2018-04-03 |  |  | SHAWN DENNIS | 2022-10-28 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.6333 | 1 | 523.76 | 96.71 | 0 | 19.84 | 407.21 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 17569047900 |  | 100343121 |  | 7240212A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WINCHESTER | 674 WINCHESTER RD 2F | 173 | MT | 2022-11-02 | U126603 | U125765 | 2017-12-20 | 2018-04-03 |  |  | SHAWN DENNIS | 2022-10-28 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.3667 | 1 | 504.34 | 80.62 | 0 | 16.51 | 407.21 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 17569048000 |  | 100343122 |  | 7240212A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WINCHESTER | 674 WINCHESTER RD TRAILER | 173 | MT | 2022-11-02 | U126603 | U125765 | 2017-12-20 | 2018-11-19 |  |  | SHAWN DENNIS | 2022-10-28 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.2167 | 1 | 721.17 | 135.56 | 0 | 27.79 | 557.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18641847700 |  | 100332944 |  | 6724204D |  |  |  | 566 | EX | ABANDON W/100421682 + | 2621P | CHILESBURG | 501 CHILESBURG RD | 067 | LEX | 2022-12-28 | U125208 | U125208 | 2018-09-10 | 2049-12-31 |  |  | LSTANFI | 2022-10-28 | 2022-10-13 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 20.4667 | 10 | 1501.75 | 1065.54 | 0 | 436.21 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883064400 |  | 100412370 |  | 7360240T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | US ROUTE 23 | 14305 US ROUTE 23 | 019 | CAT | 2022-11-02 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-10-28 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.5667 | 1 | 2634.06 | 342.3 | 0 | 68.58 | 2223.18 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883090600 |  | 100352782 |  | 6744208P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEXINGTON | 417 W LEXINGTON AV | 049 | WIN | 2022-10-28 | U128816 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | OLIVER MAYNARD | 2022-10-28 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.3833 | 1 | 1880.81 | 238.1 | 0 | 14.15 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883091400 |  | 100352764 |  | 6744208O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEXINGTON | 707 W LEXINGTON AV | 049 | WIN | 2022-10-28 | U128816 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | OLIVER MAYNARD | 2022-10-28 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.6 | 1 | 1837.52 | 197.23 | 0 | 11.73 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883135600 |  | 100349905 |  | 6748204A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MUDDY CREEK | 977 MUDDY CREEK RD | 049 | WIN | 2022-10-31 | U129722 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-10-28 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 2162.97 | 438.82 | 0 | 95.59 | 1628.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883189100 |  | 100429346 |  | 7360236T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAYO TRAIL | 30243 MAYO TRAIL RD | 019 | BUC | 2022-10-28 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-10-28 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.4333 | 1 | 1811.52 | 274.43 | 0 | 54.97 | 1482.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883200700 |  | 100346850 |  | 6696212O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | HIGHLAND | 321 HIGHLAND AV | 239 | VER | 2022-11-30 | U126602 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DEREK PAYTON | 2022-10-28 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1368.31 | 0 | 0 | 0 | 1368.31 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883221000 |  | 100346790 |  | 6696212O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | MACEY | 312 MACEY AV | 239 | VER | 2022-11-30 | U126602 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DEREK PAYTO | 2022-10-28 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8 | 1 | 3188.82 | 433.69 | 0 | 25.78 | 2729.35 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883229700 |  | 500049829 |  | 6700208H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WILDWOOD | 100 WILDWOOD DR | 239 | VER | 2022-10-28 | U126602 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DEREK PAYTON | 2022-10-28 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 2729.35 | 0 | 0 | 0 | 2729.35 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916436400 |  | 100265038 |  | 7352260O | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2033 MAIN ST W | 019 | ASH | 2022-10-28 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-10-28 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2529.08 | 0 | 0 | 0 | 2529.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959040000 |  | 100315438 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | WALLER | 122 WALLER AV | 067 | LEX | 2022-10-28 | U128336 | U134723 | 2021-12-10 | 2022-12-30 |  |  | JOSHUA COX | 2022-10-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2010.83 | 481.48 | 0 | 28.62 | 1500.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959041500 |  | 100315419 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | WALLER | 224 WALLER AV FRONT | 067 | LEX | 2022-10-28 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-10-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.9333 | 2 | 2559.24 | 892.71 | 0 | 419.22 | 1247.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960235400 |  | 100327129 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | HIGH | 465 E HIGH ST | 067 | LEX | 2022-10-28 | U126309 | U134723 | 2021-12-17 | 2022-12-30 |  |  | JAMIE LYNN | 2022-10-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3203.27 | 0 | 0 | 0 | 3203.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026233900 |  |  |  | 6728204M | 1855693 | U461383 |  | 575 | EX | OBTAIN EASEMENT FOR REG #1220 | 2621M | ATHENS BOONESBORO | 4940 ATHENS BOONESBORO RD | 067 | LEX | 2022-11-11 | U126374 | U461383 | 2022-10-28 | 2022-12-14 | 2022-12-15 | 2022-10-28 | CHRIS BOWLIN | 2022-10-28 |  |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00575 | 3200575 |  |  | WP2339 |  |  | 100 | 057532220262339 |  | 1 | 12619.05 | 0 | 0 | 0 | 12619.05 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22124590800 |  | 100240946 |  | 7324132C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D103134 | 2621P | HIGHWAY 550 E | 1870 HIGHWAY 550 E | 119 | LEB | 2022-10-28 | U123965 | U125208 | 2022-08-17 | 2023-02-10 | 2024-08-31 |  | MBLANKE | 2022-10-28 | 2022-10-27 |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 12.1167 | 2 | 13365.06 | 705.02 | 0 | 147.06 | 12512.98 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129007000 |  | 100349567 |  | 6744208P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 113 S MAIN ST | 049 | WIN | 2022-10-28 | U123111 | U130722 | 2022-09-05 | 2022-12-30 |  |  | LYN STAFFORD | 2022-10-28 | 2022-10-27 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.0167 | 2 | 2405.29 | 449.97 | 0 | 326.76 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129044600 |  | 100292196 |  | 6720216K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | JUDY | 573 JUDY LN | 067 | LEX | 2022-10-28 | U930915 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RJCRAWF | 2022-10-28 | 2022-10-13 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 26.1167 | 9 | 1418.16 | 1226 | 28.9 | 163.26 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129044800 |  | 100292238 |  | 6720216L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | JUDY | 564 JUDY LN | 067 | LEX | 2022-10-28 | U930915 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RJCRAWF | 2022-10-28 | 2022-10-04 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 24.9 | 11 | 1498.34 | 1273.34 | 0 | 225 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129073600 |  | 100255838 |  | 7348264L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | TURLEY | 1122 TURLEY AV | 089 | FLA | 2022-11-01 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-10-28 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 10.25 | 1 | 1992.83 | 597.32 | 0 | 35.51 | 1360 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22136441900 |  | 500277705 |  | 6680228P |  |  |  | 566 | EX | ABANDON SL - DEMO/FIRE | 2621P | HOLLY BERRY | 254 HOLLY BERRY DR | 073 | FRA | 2022-10-28 | U125208 | U132002 | 2022-10-03 | 2022-10-17 | 2022-11-02 |  | DCOLLIN | 2022-10-28 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0 | 1 | 73.91 | 0 | 73.91 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22139613400 |  | 500026153 |  | 6720204M |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094431 | 2621P | SPRING CREEK | 4673 SPRING CREEK DR | 067 | LEX | 2022-12-30 | U128711 | U125208 | 2022-10-18 | 2022-10-20 | 2022-11-07 |  | KKINDER | 2022-10-28 | 2022-10-21 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 28.3833 | 7 | 1985.69 | 1757.97 | 0 | 143.02 | 84.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22141417700 |  | 100255011 |  | 7348264N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D259785 | 2621P | FIELDS | 2510 FIELDS AV | 089 | FLA | 2022-10-28 | JCYRUS | U125208 | 2022-10-27 | 2022-10-27 | 2022-10-27 |  | JCYRUS | 2022-10-28 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 13.95 | 2 | 1268.36 | 843.8 | 169.18 | 201.48 | 53.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22141588800 |  | 500758945 |  | 6740204H |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | TEAL | 111 TEAL LN | 049 | WIN | 2022-11-17 | U123111 | U125763 | 2022-10-28 | 2022-12-30 |  |  | LYN STAFFORD | 2022-10-28 | 2022-10-28 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 14.9667 | 2 | 4390.28 | 840.49 | 0 | 292.39 | 3257.4 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22141589000 |  | 500108023 |  | 6744208J |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | WESTSIDE | 154 WESTSIDE DR | 049 | WIN | 2022-10-31 | U123111 | U125763 | 2022-10-28 | 2022-12-30 |  |  | LYN STAFFORD | 2022-10-28 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22141598800 |  | 100349386 |  | 6748208M | 1313371 |  |  | 566 | EX | ABAND SL | 2621P | BUCKNER | 125 BUCKNER ST | 049 | WIN | 2022-11-01 | U128410 | U132823 | 2022-10-28 | 2022-10-28 |  |  | CDESPAIN | 2022-10-28 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26290043 | 8 | 1 | 2081.56 | 427.57 | 0 | 25.43 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22141604500 |  | 100332943 |  | 6724204D | 1313369 |  |  | 566 | EX | ABANDON SL | 2621P | CHILESBURG | 391 CHILESBURG RD | 067 | LEX | 2022-12-30 | U128711 | U132823 | 2022-10-28 | 2022-10-28 |  |  | LSTANFI | 2022-10-28 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 5.1333 | 2 | 332.91 | 314.22 | 0 | 18.69 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22141606300 |  | 100350440 |  | 6744204C |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | HAMPTON | 120 HAMPTON AV | 049 | WIN | 2022-10-31 | U129731 | U125763 | 2022-10-28 | 2022-12-30 |  |  | F.GOINS | 2022-10-28 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1779.17 | 0 | 0 | 0 | 1779.17 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22141624000 |  | 100343117 |  | 7240212A |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | WINCHESTER | 676 WINCHESTER RD RR | 173 | MT | 2022-10-28 | U126603 | U125763 | 2022-10-28 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-10-28 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 557.82 | 0 | 0 | 0 | 557.82 | 0 | 0 | 0
KY | KY - WEST | 2623 | 10841456600 |  | 100273613 |  | 6680224D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | LOUISVILLE | 1300 LOUISVILLE RD | 073 | FRA | 2022-10-31 | U128816 | RPOLLY | 2010-05-20 | 2022-07-01 | 2022-12-31 |  | OLIVER MAYNARD | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 6.4833 | 1 | 1229.13 | 353.03 | 0 | 21 | 855.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 10841477300 |  | 100346617 |  | ? |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | MCDONALD | 359 MCDONALD DR | 239 | VER | 2022-10-31 | U127206 | RPOLLY | 2010-05-20 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1974.26 | 0 | 0 | 0 | 1974.26 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12968041600 |  | 500570932 |  | NEW000000 | 2176779 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | MAXWELL | 513< E MAXWELL ST | 067 | LEX | 2022-11-08 | U126309 | U124967 | 2012-05-02 | 2022-12-30 |  |  | JAMIE LYNN | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - CENTRAL | 2629 | 13117530100 |  | 100348268 |  | 6744208L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAIN | 221 N MAIN ST | 049 | WIN | 2022-10-31 | U126602 | U908786 | 2013-02-11 | 2022-07-01 | 2022-12-31 |  | DEREK PAYTON | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1518.66 | 0 | 0 | 0 | 1518.66 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 17531392300 |  | 100361046 |  | 6736228L | 1638587 |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | CLINTONVILLE | 501 CLINTONVILLE RD L15 | 017 | PAR | 2022-10-31 | U126603 | U917287 | 2017-08-07 | 2019-12-31 |  |  | SHAWN DENNIS | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.3833 | 1 | 2017.04 | 322.41 | 0 | 66.07 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21026127200 |  |  |  | 7256280K | 2180424 | U122858 |  | 557 | EX | INSTALL 2200'-2"&4" PMMP | 2600B | LEXINGTON | LEXINGTON | 161 | MAY | 2022-12-06 | U128132 | U122858 | 2021-06-08 | 2022-09-21 | 2022-12-31 | 2022-08-25 | DAVID STAGGS | 2022-10-31 | 2022-02-11 |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00557 | 3200557 |  |  | WP1272 | AMRCB |  | 100 | 055732210261272 | 389.7667 | 90612 | 570820.34 | 32517.52 | 207063.89 | 4154.04 | 250321.87 | 0 | 1115.09 | 75647.93 | 1678
KY | KY - CENTRAL | 2632 | 21026127600 |  |  |  | 7256280K | 2180424 | U122858 |  | 558 | EX | RETIRE 4700'-4" BSLP | 2600B |  |  | 161 | MAY | 2022-11-09 | U128132 | U122858 | 2021-06-08 | 2022-12-30 | 2022-12-31 | 2022-10-06 | DAVID STAGGS | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00558 | 3200558 |  |  | WP1276 | AMRCB |  | 100 | 055832210261276 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883079300 |  | 100347930 |  | 6748208I | 2075093 |  |  | 566 | EX | ABANDON SL W/CAPTIOL JOB | 2600B | LINDEN | 15 LINDEN AV | 049 | WIN | 2022-10-31 | U129722 | U120245 | 2021-01-30 | 2022-12-30 |  |  | M YOUNG | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26290043 | 8 | 1 | 1867.53 | 438.8 | 0 | 26.09 | 1402.64 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883088100 |  | 501078180 |  | 6748208I | 2075093 |  |  | 566 | EX | ABANDON SL W/CAPTIOL JOB | 2600B | MAIN | 604 N MAIN ST | 049 | WIN | 2022-10-31 | U126285 | U120245 | 2021-01-30 | 2022-12-30 |  |  | DDAVIS | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26290043 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883126700 |  | 100347804 |  | 6748208I | 2075093 |  |  | 566 | EX | ABANDON SL W/CAPTIOL JOB | 2600B | MAIN | 420 N MAIN ST | 049 | WIN | 2022-10-31 | U126285 | U120245 | 2021-01-30 | 2022-12-30 |  |  | DDAVIS | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26290043 | 8 | 1 | 2415.59 | 460.41 | 0 | 326.62 | 1628.56 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883164600 |  | 100426829 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2633S | OLD 114 | 1205 OLD 114 | 071 | PRE | 2022-11-22 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 5.55 | 1 | 1779.12 | 342.25 | 0 | 68.56 | 1368.31 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883167300 |  | 100351709 |  | 6744208O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEXINGTON | 636 W LEXINGTON AV | 049 | WIN | 2022-10-31 | U129722 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883203100 |  | 100446751 |  | 6748204A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MUDDY CREEK | 1163 MUDDY CREEK RD | 049 | WIN | 2022-10-31 | U126284 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JOSH PASLEY | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.95 | 1 | 3121.28 | 173.97 | 0 | 120.7 | 2826.61 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883224100 |  | 500190209 |  | 6748204J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MUDDY CREEK | 2478 MUDDY CREEK RD | 049 | WIN | 2022-10-31 | U126284 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JOSH PASLEY | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.05 | 1 | 1982.36 | 297.81 | 0 | 206.6 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883251600 |  | 100346296 |  | 6696212L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | LAVAL | 327 LAVAL HT | 239 | VER | 2022-11-01 | U127206 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 2079.3 | 0 | 0 | 0 | 2079.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883297800 |  | 100460470 |  | 6744208P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEXINGTON | 17 W LEXINGTON AV HWT | 049 | WIN | 2022-10-31 | U129731 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 2729.43 | 470.47 | 0 | 27.96 | 2231 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916436200 |  | 100265040 |  | 7352260O | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2027 MAIN ST W W | 019 | ASH | 2022-10-31 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-10-31 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2444.32 | 0 | 0 | 0 | 2444.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959041000 |  | 100315424 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | WALLER | 214 WALLER AV | 067 | LEX | 2022-10-31 | U461322 | U134723 | 2021-12-10 | 2022-12-30 |  |  | STEVE CANOY | 2022-10-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.9833 | 1 | 2257 | 499.8 | 0 | 365.63 | 1391.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959047500 |  | 100315423 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | WALLER | 218 WALLER AV A | 067 | LEX | 2022-10-31 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-10-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 1986.47 | 451.31 | 0 | 26.84 | 1508.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960251200 |  | 100410827 |  | 6720212M | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | HIGH | 518 E HIGH ST | 067 | LEX | 2022-11-08 | U126309 | U134723 | 2021-12-17 | 2022-12-30 |  |  | JAMIE LYNN | 2022-10-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2416.58 | 0 | 0 | 0 | 2416.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960254000 |  | 500549892 |  | 6720212M | 2176779 |  |  | 566 | EX | ABANDON SL W/CAPTIOL JOB | 2600B | HIGH | 516 E HIGH ST 2FR | 067 | LEX | 2022-11-08 | U126309 | U134723 | 2021-12-17 | 2022-12-30 |  |  | JAMIE LYNN | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - EAST | 2633 | 22122669700 |  | 100240824 |  | 7324132I | 2290467 |  |  | 566 | EX | ABANDON SL - HINDMAN FLOOD | 2600B | DUKES BRANCH | 189 DUKES BRANCH RD | 119 | HIN | 2022-11-10 | U123965 | U125208 | 2022-08-09 | 2022-08-08 |  |  | MBLANKE/CJH J HIERONIMUS | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - WEST | 2623 | 22129020700 |  | 100345166 |  | 6696212G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FRANKFORT | 197 FRANKFORT ST B | 239 | VER | 2022-11-01 | U124003 | U130722 | 2022-09-05 | 2022-12-30 |  |  | BPULLIAM/MILLER | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8 | 1 | 4340.9 | 467.61 | 0 | 626.32 | 3246.97 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129036000 |  | 100254298 |  | 7348264N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PATTERSON | 1402 PATTERSON ST | 089 | FLA | 2022-11-02 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1360 | 0 | 0 | 0 | 1360 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129073100 |  | 100417555 |  | 7348264O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CALLIHAN | 1702 CALLIHAN ST | 089 | FLA | 2022-11-02 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 12 | 1 | 2100.88 | 699.31 | 0 | 41.57 | 1360 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129073500 |  | 100255803 |  | 7348264L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | TURLEY | 1014 TURLEY AV | 089 | FLA | 2022-11-07 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-10-31 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1360 | 0 | 0 | 0 | 1360 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129073700 |  | 100255836 |  | 7348264H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | VOYER | 1118 VOYER ST | 089 | FLA | 2022-11-10 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1360 | 0 | 0 | 0 | 1360 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129076300 |  | 100258553 |  | 7344268M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WURTLAND | 1102 WURTLAND AV | 089 | WUR | 2022-11-02 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-10-31 | 2022-10-28 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 21 | 2 | 2981.88 | 1333.71 | 0 | 288.17 | 1360 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129085000 |  | 100294817 |  | 6716212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | UPPER | 414 N UPPER ST | 067 | LEX | 2022-10-31 | U930915 | U130722 | 2022-09-05 | 2022-12-30 |  |  | MCRAIG | 2022-10-31 | 2022-10-17 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 19.5 | 5 | 1409.43 | 914.77 | 178.29 | 316.37 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22138315800 |  | 100349578 |  | 6744208P | 1858944 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HICKMAN | 103 E HICKMAN ST 2 | 049 | WIN | 2022-10-31 | U126602 | U123981 | 2022-10-11 | 2023-11-29 | 2023-11-29 |  | DEREK PAYTON | 2022-10-31 |  |  | D | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - CENTRAL | 2629 | 22141170900 |  | 100269747 |  | 6732252P |  |  |  | 565 | EX | SERVICE LINE - REPLACE/MMO | 2621P | PLEASANT | 440 W PLEASANT ST | 097 | CYN | 2022-11-01 | U125208 | U125208 | 2022-10-26 | 2022-10-31 | 2022-10-31 |  | NRICHIE | 2022-10-31 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 21.9 | 3 | 2867.26 | 1278.59 | 661.6 | 349.09 | 577.98 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22141445900 |  | 100340623 |  | 6724212E |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTREQD | 2621P | CHARLESTON | 1714 CHARLESTON CT | 067 | LEX | 2022-11-01 | U125208 | U125208 | 2022-10-27 | 2022-11-01 | 2022-11-30 |  | KKINDER | 2022-10-31 | 2022-10-31 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.9333 | 2 | 931.86 | 640.34 | 253.46 | 38.06 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22141867800 |  | 100460718 |  | 6744208P |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | LEXINGTON | 17 W LEXINGTON AV 1 | 049 | WIN | 2022-10-31 | U129731 | U125763 | 2022-10-31 | 2022-12-30 |  |  | F.GOINS | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 239.61 | 0 | 0 | 0 | 239.61 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22141868700 |  | 100460564 |  | 6744208P |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | LEXINGTON | 17 W LEXINGTON AV 2 | 049 | WIN | 2022-10-31 | U129731 | U125763 | 2022-10-31 | 2022-12-30 |  |  | F.GOINS | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - CENTRAL | 2629 | 22141869000 |  | 100352929 |  | 6744208P |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | LEXINGTON | 17 W LEXINGTON AV 3 | 049 | WIN | 2022-10-31 | U129731 | U125763 | 2022-10-31 | 2022-12-30 |  |  | F.GOINS | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 239.61 | 0 | 0 | 0 | 239.61 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22141869200 |  | 100461133 |  | 6744208P |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | LEXINGTON | 17 W LEXINGTON AV 4 | 049 | WIN | 2022-10-31 | U129731 | U125763 | 2022-10-31 | 2022-12-30 |  |  | F.GOINS | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 0
KY | KY - CENTRAL | 2629 | 22141869400 |  | 100460782 |  | 6744208P |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | LEXINGTON | 17 W LEXINGTON AV 5 | 049 | WIN | 2022-10-31 | U129731 | U125763 | 2022-10-31 | 2022-12-30 |  |  | F.GOINS | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 239.61 | 0 | 0 | 0 | 239.61 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22141869700 |  | 100461300 |  | 6744208P |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | LEXINGTON | 17 W LEXINGTON AV 6 | 049 | WIN | 2022-10-31 | U129731 | U125763 | 2022-10-31 | 2022-12-30 |  |  | F.GOINS | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - CENTRAL | 2629 | 22141869900 |  | 100460563 |  | 6744208P |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | LEXINGTON | 17 W LEXINGTON AV 7 | 049 | WIN | 2022-10-31 | U129731 | U125763 | 2022-10-31 | 2022-12-30 |  |  | F.GOINS | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 239.61 | 0 | 0 | 0 | 239.61 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22141870100 |  | 100461268 |  | 6744208P |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | LEXINGTON | 17 W LEXINGTON AV 8 | 049 | WIN | 2022-10-31 | U129731 | U125763 | 2022-10-31 | 2022-12-30 |  |  | F.GOINS | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - WEST | 2623 | 22141874400 |  | 100347203 |  | 6696212J | 1313370 |  |  | 565 | EX | REPLACE SL | 2621P | CLIFTON | 505 CLIFTON RD | 239 | VER | 2022-10-31 | DCOLLIN | U132823 | 2022-10-31 | 2022-10-31 |  |  | DCOLLIN | 2022-10-31 | 2022-10-31 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 16.5167 | 2 | 1631.39 | 794.77 | 497.55 | 339.07 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22141879200 |  | 100348712 |  | 6748208M |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | WASHINGTON | 217 E WASHINGTON ST | 049 | WIN | 2022-10-31 | U126602 | U125763 | 2022-10-31 | 2022-12-30 |  |  | DEREK PAYTON | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 3331.97 | 433.69 | 0 | 25.78 | 2872.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22141890500 |  | 100347093 |  | 6696212J | 1313370 |  |  | 565 | EX | REPLACE SL | 2621P | M L KING | 109 M L KING BV | 239 | VER | 2022-11-01 | U128410 | U132823 | 2022-10-31 | 2022-10-31 |  |  | CDESPAIN | 2022-10-31 | 2022-10-31 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 1 | 2530.05 | 427.57 | 560.21 | 25.43 | 1516.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22141906000 |  | 100292174 |  | 6720216L |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | JUDY | 509 JUDY LN | 067 | LEX | 2022-11-01 | U930915 | U132823 | 2022-10-31 | 2022-10-28 | 2022-11-15 |  | RSTRONG | 2022-10-31 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 19.1833 | 3 | 1471.09 | 992.06 | 254.22 | 224.81 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22979040100 |  | 100345630 |  | 6696212C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MILDRED | 817 MILDRED ST | 239 | VER | 2022-10-31 | U127206 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | JUSTIN HOBBS | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1853.07 | 0 | 0 | 0 | 1853.07 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22979056400 |  | 501165566 |  | 6700212A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | QUAIL RUN | 410 QUAIL RUN RD | 239 | VER | 2022-11-03 | U127206 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | JUSTIN HOBBS | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 10 | 1 | 2418.1 | 533.32 | 0 | 31.71 | 1853.07 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23154569600 |  | 500016913 |  | 6684224E |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | RAVEN | 641 RAVEN DR | 073 | FRA | 2023-01-10 | U125559 | U125763 | 2023-01-10 | 2023-12-29 |  |  | OLIVER MAYNARD | 2022-10-31 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2623 | 04578917800 |  | 500034357 |  | V-909/23 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SLONE | 751 SLONE DR 36 | 209 | GEO | 2022-11-01 | U126532 | SSUTHER | 2004-06-24 | 2022-07-01 | 2022-12-31 |  | LESLIE SHARON | 2022-11-01 | 2022-10-26 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8 | 1 | 1338.3 | 426.66 | 0 | 25.38 | 886.26 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 06663651200 |  | 100422695 |  | 6732252P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | POPLAR | 314 N POPLAR ST | 097 | CYN | 2022-11-01 | U126602 | CTAULBE | 2006-10-19 | 2022-07-01 | 2022-12-31 |  | DEREK PAYTON | 2022-11-01 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1579.22 | 0 | 0 | 0 | 1579.22 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 08727652800 |  | 100285120 |  | 6764176K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LAUREL | 527 LAUREL ST | 065 | IRV | 2022-11-01 | U126285 | RPOLLY | 2008-04-16 | 2022-07-01 | 2022-12-31 |  | DDAVIS | 2022-11-01 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 2525.74 | 511.26 | 0 | 29.92 | 1984.56 | 0 | 0 | 0
KY | KY - EAST | 2633 | 11899917000 |  | 100240850 |  | 7324132F | 2290467 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | SR550 | SR550 | 119 | HIN | 2022-11-01 | U123965 | U124449 | 2011-04-05 | 2022-07-01 | 2022-12-31 |  | MBLANKE/CJH JORDAN HIERONIMUS | 2022-11-01 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1 | 1096.54 | 0 | 0 | 0 | 1096.54 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11900856900 |  | 100467662 |  | 6736224D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | KARLA | 1159 KARLA DR | 017 | PAR | 2022-11-02 | U126603 | U123853 | 2011-04-12 | 2022-07-01 | 2022-12-31 |  | SHAWN DENNIS | 2022-11-01 | 2022-11-01 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.3667 | 2 | 3939.35 | 360.55 | 0 | 81.61 | 3497.19 | 0 | 0 | 0
KY | KY - WEST | 2623 | 11900949600 |  | 500423062 |  | 6680224C |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CARDWELL | 145 CARDWELL LN | 073 | FRA | 2022-11-09 | U128410 | U906631 | 2011-04-13 | 2022-11-01 | 2022-12-31 |  | CDESPAIN | 2022-11-01 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 2.8667 | 1 | 1055.63 | 189.43 | 0 | 11.1 | 855.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11918801700 |  | 100284528 |  | X-1103-09 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | COLLEGE HILL | 130 COLLEGE HILL RD | 151 | WAC | 2022-11-01 | U129731 | U124449 | 2011-08-03 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-11-01 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.5 | 1 | 2286.36 | 530.95 | 0 | 126.85 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11939496000 |  | 500661961 |  | 16740232A |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | SANDRA | 3 SANDRA LN | 017 | PAR | 2022-11-02 | U126603 | U124965 | 2011-12-21 | 2019-12-31 |  |  | SHAWN DENNIS | 2022-11-01 | 2022-11-01 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.9 | 1 | 1511.91 | 396.13 | 0 | 89.66 | 1026.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12960999400 |  | 500497991 |  | W-1126/13 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | UNION CITY | 2360 UNION CITY RD | 151 | RIC | 2022-11-01 | U126284 | U125208 | 2012-03-19 | 2022-07-01 | 2022-12-31 |  | JOSH PASLEY | 2022-11-01 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.9667 | 1 | 2649.21 | 266.43 | 0 | 275 | 2107.78 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 14270119000 |  | 100269230 |  | 6736252M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CHURCH | 227 N CHURCH ST | 097 | CYN | 2022-11-01 | U126602 | U122906 | 2014-12-11 | 2022-02-08 | 2022-12-31 |  | DEREK PAYTON | 2022-11-01 | 2022-02-08 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.51667 | 1 | 1218.51 | 30.38 | 0 | 88.13 | 1100 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 14270146100 |  | 100284514 |  | 6752180J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | FIKE | 185 FIKE RD | 151 | WAC | 2022-12-28 | U125208 | U122906 | 2014-12-11 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-11-01 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 2243.64 | 495.93 | 0 | 119.15 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21026998201 |  | 501304849 |  | 6712228I | 2177127 | U126783 |  | 555 | EX | INSTALL 1930'-2"/4" PMMP | 2600B | MAGELLAN | MAGELLAN LN LT1 | 209 | GEO | 2022-12-22 | U128132 | U126783 | 2022-08-08 | 2022-10-06 | 2022-10-28 | 2022-11-01 | R.HUMPHREYS | 2022-11-01 | 2022-09-26 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP9982 |  |  | 100 | 055532210269982 | 208.25 | 48350 | 114169.59 | 11451.5 | 8860.87 | 1838.82 | 80524.12 | 0 | 529.71 | 10964.57 | 1934
KY | KY - WEST | 2623 | 21883145500 |  | 100345128 |  | 6696212G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | VIRGINIA | 143 VIRGINIA AV | 239 | VER | 2022-11-01 | U127206 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-11-01 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1974.26 | 0 | 0 | 0 | 1974.26 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883182000 |  | 500449847 |  | 6696212G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | VIRGINIA | 190 VIRGINIA AV REAR | 239 | VER | 2022-11-01 | U127206 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-11-01 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1731.88 | 0 | 0 | 0 | 1731.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883185200 |  | 100404935 |  | 6704208A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | RAVENWOOD | 134 RAVENWOOD RD | 239 | VER | 2022-11-01 | U127206 | U120245 | 2021-01-30 | 2022-11-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-11-01 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8 | 1 | 4283.9 | 477.86 | 0 | 27.95 | 3778.09 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883229100 |  | 100260585 |  | 7344140T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | KY ROUTE 122 | 15946 KY ROUTE 122 | 071 | HI | 2022-11-01 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-11-01 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1 | 1111.59 | 0 | 0 | 0 | 1111.59 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883240200 |  | 100426450 |  | 7340136T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2633S | MILL CREEK | 3 MILL CREEK | 071 | WAY | 2022-11-22 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-11-01 |  |  | B | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 4.4167 | 1 | 1748.78 | 312.28 | 0 | 68.19 | 1368.31 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883317700 |  | 100405331 |  | 6744184G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CHARLIE NORRIS | 1113 CHARLIE NORRIS RD | 151 | RIC | 2022-11-01 | U126284 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JOSH PASLEY | 2022-11-01 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.0333 | 1 | 2551.03 | 336.01 | 0 | 346.85 | 1868.17 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883321100 |  | 500061426 |  | 6712228F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SLONE | 751 SLONE DR 37 | 209 | GEO | 2022-11-01 | U126532 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | LESLIE SHARON | 2022-11-01 | 2022-10-24 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 16 | 2 | 2233.47 | 853.32 | 0 | 50.76 | 1329.39 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21884240200 |  | 100426875 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2633S | ABBOTT CREEK | 3404 ABBOTT CREEK RD | 071 | PRE | 2022-11-22 | U126604 | U128293 | 2021-02-04 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-11-01 |  |  | B | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 |  | 1 | 741.06 | 0 | 0 | 0 | 741.06 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21884270300 |  | 100269578 |  | 6732252P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | POPLAR | 302 N POPLAR ST | 097 | CYN | 2022-11-01 | U126602 | U128293 | 2021-02-04 | 2022-07-01 | 2022-12-31 |  | DEREK PAYTON | 2022-11-01 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2126.4 | 0 | 0 | 0 | 2126.4 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916436900 |  | 100264009 |  | 7352260N | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2120 MAIN ST W | 019 | ASH | 2022-11-01 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-11-01 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1930.59 | 0 | 0 | 0 | 1930.59 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959040800 |  | 100315432 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | WALLER | 140 WALLER AV 1F | 067 | LEX | 2022-11-01 | U461322 | U134723 | 2021-12-10 | 2022-12-30 |  |  | STEVE CANOY | 2022-11-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.2333 | 1 | 2700.01 | 683.18 | 0 | 706.75 | 1310.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959040900 |  | 100315430 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | WALLER | 200 WALLER AV | 067 | LEX | 2022-11-01 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-11-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2920.54 | 506.65 | 0 | 119.77 | 2294.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960238600 |  | 100321278 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | MAXWELL | 456 E MAXWELL ST | 067 | LEX | 2022-11-09 | U461375 | U134723 | 2021-12-17 | 2022-12-30 |  |  | LARRY BROWN | 2022-11-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3222.93 | 0 | 0 | 0 | 3222.93 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026230000 |  |  |  | 6688228K | 2292578 | U132703 |  | 562 | EX | ABANDON 470'-2"&3"PLP | 2600E | BRIGHTON PARK | 105 BRIGHTON PARK BV | 073 | FRA | 2023-03-16 | U128132 | U132703 | 2022-10-05 | 2023-12-28 | 2023-12-31 | 2022-11-01 | M. COLLINS | 2022-11-01 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00562 | 3200562 |  |  | WP2300 |  |  | 100 | 056232220262300 | 22.6667 | 0 | 5899.02 | 1903.46 | 0 | -426.44 | 4422 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22103390100 |  | 500023282 |  | 6736228H |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2621P | BRADFORD | 142 BRADFORD DR UP | 017 | PAR | 2022-11-02 | U126603 | U134723 | 2022-05-25 | 2022-07-01 | 2022-12-31 |  | SHAWN DENNIS | 2022-11-01 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.7167 | 1 | 954.43 | 114.16 | 0 | 25.85 | 814.42 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129035500 |  | 500609902 |  | 7348264K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | JONES | 1515 JONES ST | 089 | FLA | 2022-11-04 | U461478 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DAVID STAGGS | 2022-11-01 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.3833 | 1 | 1766.45 | 326.49 | 0 | 79.96 | 1360 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129035800 |  | 100437093 |  | 7348264O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OAK | 1919 OAK ST | 089 | FLA | 2022-11-03 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-11-01 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 12.25 | 1 | 2260.58 | 850.8 | 0 | 49.78 | 1360 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129035900 |  | 500016461 |  | 7348264O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OAK | 1915 OAK ST | 089 | FLA | 2022-11-03 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-11-01 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1360 | 0 | 0 | 0 | 1360 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129036500 |  | 100255824 |  | 7348264L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | TURLEY | 832 TURLEY AV | 089 | FLA | 2022-11-01 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-11-01 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1967.6 | 0 | 0 | 0 | 1967.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129059800 |  | 500751786 |  | 6752180F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FLINT | 343< FLINT RD | 151 | WAC | 2022-11-03 | U129731 | U130722 | 2022-09-05 | 2022-12-30 |  |  | F.GOINS | 2022-11-01 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22135003200 |  | 100332021 |  | 6720212N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WALTON | 214 WALTON AV A | 067 | LEX | 2022-11-01 | MCRAIG | U130722 | 2022-09-27 | 2022-12-30 |  |  | MCRAIG | 2022-11-01 | 2022-10-17 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 37.4 | 11 | 2090.64 | 1810.43 | 34.04 | -130.33 | 376.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22142221000 |  | 500499610 |  | 6696212G |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2600B | VIRGINIA | 143< VIRGINIA AV | 239 | VER | 2022-11-01 | U127206 | U125201 | 2022-11-01 | 2022-12-01 | 2022-12-01 |  | JUSTIN HOBBS | 2022-11-01 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 321.94 | 0 | 0 | 0 | 321.94 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22142258300 |  | 100345111 |  | 6696212G |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | CAMDEN | 147 CAMDEN AV | 239 | VER | 2022-11-01 | U128410 | U129939 | 2022-11-01 | 2022-11-01 |  |  | CDESPAIN | 2022-11-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.6333 | 1 | 3563.17 | 501.14 | 459.95 | 29.32 | 2572.76 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979027800 |  | 100269572 |  | 6732252P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | POPLAR | 205 N POPLAR ST | 097 | CYN | 2022-11-01 | U126602 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | DEREK PAYTON | 2022-11-01 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - EAST | 2682 | 22979046000 |  | 100427578 |  | 7328128T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2633S | SAMS BRANCH | 111 SAMS BRANCH RD | 119 | MAL | 2022-12-05 | U123965 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | MBLANKE/CJH J HIERONIMUS | 2022-11-01 |  |  | B | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 |  | 1 | 2032.12 | 0 | 0 | 0 | 2032.12 | 0 | 0 | 0
KY | KY - EAST | 2682 | 22979046800 |  | 100430360 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2633S | RIGHT FORK BUL | 185 RIGHT FORK BUL CK | 071 | PRE | 2022-11-22 | U126604 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | WILL FULKS | 2022-11-01 |  |  | B | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 5.5833 | 1 | 1846.72 | 392.68 | 0 | 85.73 | 1368.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 03533820200 |  | 100332782 |  | 6716212L | 1528079 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SHORT | 230 E SHORT ST | 067 | LEX | 2022-11-02 | TROE | DMCCULL | 2003-03-17 | 2022-07-01 | 2022-12-31 |  | TROE | 2022-11-02 | 2022-09-07 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 32.1833 | 11 | 2821.19 | 1725.23 | 0 | 103.15 | 992.81 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11893911600 |  | 500050366 |  | W-1128-51 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WALTER | 171 WALTER LN | 151 | WAC | 2022-11-02 | U129731 | U906307 | 2011-03-03 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-11-02 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9 | 1 | 1722.6 | 562.18 | 0 | 134.3 | 1026.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11898472000 |  | 100285965 |  | X-1206-30 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | KIRKLAND | 216 KIRKLAND AV RR | 065 | IRV | 2022-11-02 | U126285 | U906631 | 2011-03-30 | 2022-07-01 | 2022-12-31 |  | DDAVIS | 2022-11-02 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1779.17 | 0 | 0 | 0 | 1779.17 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12100802400 |  | 100406444 | 55 | 6752180N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | FIKE | 154 FIKE RD TR 2 | 151 | WAC | 2022-11-02 | U129722 | TJROSEN | 2012-12-03 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-11-02 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1109.05 | 0 | 0 | 0 | 1109.05 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12962119000 |  | 100284516 |  | W1103-12 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | FIKE | 155 FIKE RD | 151 | WAC | 2022-11-03 | U129731 | U125208 | 2012-03-27 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-11-02 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9 | 1 | 5533.74 | 562.18 | 0 | 70.63 | 4900.93 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 17517716600 |  | 500028829 | 48 | 6736228H |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | BRADFORD | 151 BRADFORD DR | 017 | PAR | 2022-11-02 | U126603 | PMCNABB | 2017-06-21 | 2018-04-05 |  |  | SHAWN DENNIS | 2022-11-02 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.5167 | 1 | 1102.56 | 234.96 | 0 | 53.18 | 814.42 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 17517754100 |  | 500028834 |  | 6736228H |  |  |  | 566 | EX | ABANDON SL - DEMO/CUST RQD | 2621P | BRADFORD | 153 BRADFORD DR | 017 | PAR | 2022-11-29 | U126603 | U125208 | 2017-06-21 | 2017-12-29 | 2017-12-29 |  | SHAWN DENNIS | 2022-11-02 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.4833 | 1 | 716.58 | 165.84 | 0 | 37.54 | 513.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 17517754200 |  | 500028835 |  | 6736228H |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | BRADFORD | 155 BRADFORD DR | 017 | PAR | 2022-11-02 | U126603 | U125208 | 2017-06-21 | 2017-12-29 |  |  | SHAWN DENNIS | 2022-11-02 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.5167 | 1 | 724.8 | 172.54 | 0 | 39.06 | 513.2 | 0 | 0 | 0
KY | KY - EAST | 2631 | 20026922500 |  |  |  | 7348248F | 1968457 | GSULLI1 |  | 909 | EX | INSTALL ELECTRONICS | 2630M | US 60 | US 60 | 019 | CAN | 2023-09-27 | U123258 | GSULLI1 | 2020-02-03 | 2023-12-28 | 2023-12-31 | 2022-11-02 | DASH | 2022-11-02 | 2021-08-19 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP9225 |  |  | 100 | 090932200269225 | 424.2833 | 0 | 238947.63 | 32297.94 | 23513.06 | 5865.45 | 168060.18 | 0 | 9211 | 0
KY | KY - EAST | 2631 | 20026922600 |  |  |  | 7348248F | 1968457 | GSULLI1 |  | 910 | EX | RETIRE ELECTRONICS | 2631M | US 60 | US 60 | 019 | CAN | 2023-09-27 | U123258 | GSULLI1 | 2020-02-03 | 2023-12-29 | 2023-12-31 | 2022-11-02 | DASH | 2022-11-02 | 2022-12-08 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00910 | 3200910 |  |  | WP9226 |  |  | 100 | 091032200269226 | 1.6167 | 0 | 144.18 | 137.03 | 0 | 7.15 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21026133900 |  |  |  | 7348248F | 1968457 | GSULLI1 |  | 583 | EX | INSTALL VRG CONTROLER | 2631M | US 60 | US 60 | 019 | CAN | 2023-02-24 | U123258 | GSULLI1 | 2021-07-26 | 2023-12-29 | 2023-12-31 | 2021-11-02 | DASH | 2022-11-02 |  |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00583 | 3200583 |  |  | WP1339 |  |  | 100 | 058332210261339 |  | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21026134000 |  |  |  | 7348248F | 1968457 | GSULLI1 |  | 584 | EX | RETIRE DAMAGED CONTROLLER | 2631M | US 60 | US 60 | 019 | CAN | 2023-02-28 | U123258 | GSULLI1 | 2021-07-26 | 2023-12-29 | 2023-12-31 | 2021-11-02 | DASH | 2022-11-02 |  |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00584 | 3200584 |  |  | WP1340 |  |  | 100 | 058432210261340 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883067500 |  | 100414479 |  | 7356148T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | DEADENING FORK | 333 DEADENING FORK RD | 071 | HAR | 2022-11-02 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-11-02 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 4.4667 | 1 | 1753.05 | 315.79 | 0 | 68.95 | 1368.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883174000 |  | 100290618 |  | 6720216O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | OLD PARIS | 1739 OLD PARIS RD | 067 | LEX | 2022-11-02 | U127206 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-11-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 4135.08 | 477.86 | 0 | 27.95 | 3629.27 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883203600 |  | 500175824 |  | 111111 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2633S | RT FORK BULL | 637 RT FORK BULL CR | 071 | PRE | 2022-11-02 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-11-02 |  |  | B | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 |  | 1 | 1368.31 | 0 | 0 | 0 | 1368.31 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883205100 |  | 100348224 |  | 6744208L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | HILL | 353 HILL ST | 049 | WIN | 2022-11-02 | U124003 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | BPULLIAM/MILLER | 2022-11-02 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.8333 | 1 | 3816.7 | 258.44 | 0 | 513.08 | 3045.18 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883239800 |  | 100438192 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2633S | SALLY STEPHENS | 212 SALLY STEPHENS BR | 071 | PRE | 2022-11-22 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-11-02 |  |  | B | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 5.5333 | 1 | 1215.19 | 389.15 | 0 | 84.98 | 741.06 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883241600 |  | 100412834 |  | 6752180E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WALTER | 112 WALTER LN | 151 | WAC | 2022-11-02 | U126284 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JOSH PASLEY | 2022-11-02 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.1333 | 1 | 2324.99 | 342.67 | 0 | 353.76 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883280600 |  | 500830176 |  | 6688232N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BLUERIDGE | 226 BLUERIDGE DR | 073 | FRA | 2022-11-02 | U128816 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | OLIVER MAYNARD | 2022-11-02 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 3.5333 | 1 | 1304.51 | 221.69 | 0 | 12.97 | 1069.85 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883314500 |  | 500282671 |  | 6712216L | 9402948 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | MERCER | 2001 MERCER RD CNG | 067 | LEX | 2022-11-28 | U461383 | U120245 | 2021-01-30 | 2022-10-27 | 2022-12-31 |  | LSTONE | 2022-11-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883319900 |  | 500182940 |  | 6688228O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | VERSAILLES | 922 VERSAILLES RD | 073 | FRA | 2022-11-02 | U128816 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | OLIVER MAYNARD | 2022-11-02 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 3.8333 | 1 | 3305.79 | 238.54 | 0 | 13.95 | 3053.3 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916430100 |  | 100263551 |  | 7352256B | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | HORSLEY | 200 HORSLEY LN | 019 | ASH | 2022-11-02 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-11-02 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2078.35 | 0 | 0 | 0 | 2078.35 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959041300 |  | 100315410 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | WALLER | 221 WALLER AV | 067 | LEX | 2022-11-02 | U461322 | U134723 | 2021-12-10 | 2022-12-30 |  |  | STEVE CANOY | 2022-11-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10 | 1 | 3215.74 | 667.83 | 0 | 690.85 | 1857.06 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959041600 |  | 100315418 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | WALLER | 226 WALLER AV | 067 | LEX | 2022-11-02 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-11-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2238.3 | 506.65 | 0 | 119.77 | 1611.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960235700 |  | 100320968 |  | 6720212M | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | HIGH | 514 E HIGH ST 2FL | 067 | LEX | 2022-11-09 | U461375 | U134723 | 2021-12-17 | 2022-12-30 |  |  | LARRY BROWN | 2022-11-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2791.38 | 0 | 0 | 0 | 2791.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960251100 |  | 100327072 |  | 6720212M | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | HIGH | 513 E HIGH ST | 067 | LEX | 2022-11-09 | U461375 | U134723 | 2021-12-17 | 2022-12-30 |  |  | LARRY BROWN | 2022-11-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2478.05 | 0 | 0 | 0 | 2478.05 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026202500 |  | 501331104 |  | 6696212M | 2289106 | U126783 |  | 555 | EX | INSTALL 1120'-2"/4" PMMP | 2600B | TRINITY | TRINITY LN LT154 | 239 | VER | 2022-11-16 | U128132 | U126783 | 2022-06-08 | 2022-10-21 | 2022-11-04 | 2022-11-02 | JDUNN | 2022-11-02 | 2022-10-19 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2025 |  |  | 100 | 055532220262025 | 120.25 | 14248 | 50092.05 | 6992.44 | 5040.72 | 526.85 | 33591.26 | 0 | 188.64 | 3752.14 | 1096
KY | KY - EAST | 2631 | 22109814000 |  | 100252338 |  | 7348264K |  |  |  | 566 | EX | ABANODN SL-I/I/LGCY | 2600B | ARGILLITE | 1412 ARGILLITE RD | 089 | FLA | 2022-11-02 | U126286 | U134723 | 2022-06-14 | 2022-07-01 | 2022-12-31 |  | TYLER ALLISON | 2022-11-02 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 12 | 1 | 2497.18 | 833.42 | 0 | 48.76 | 1615 | 0 | 0 | 0
KY | KY - EAST | 2682 | 22129035000 |  | 100426854 |  | 123456789 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2633S | SHOP BRANCH | 256 SHOP BRANCH RD | 071 | PRE | 2022-11-22 | U126604 | U130722 | 2022-09-05 | 2022-12-30 |  |  | WILL FULKS | 2022-11-02 |  |  | B | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 |  | 1 | 1368.31 | 0 | 0 | 0 | 1368.31 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129035600 |  | 100255652 |  | 7348264H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MEADE | 1408 MEADE ST | 089 | FLA | 2022-11-08 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-11-02 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1360 | 0 | 0 | 0 | 1360 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129058100 |  | 100347470 |  | 6744208L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ELM | 140 ELM ST | 049 | WIN | 2022-11-02 | U124003 | U130722 | 2022-09-05 | 2022-12-30 |  |  | BPULLIAM/MILLER | 2022-11-02 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 6.1667 | 1 | 2876.75 | 418.14 | 0 | 830.05 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129082400 |  | 100290622 |  | 6720216O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OLD PARIS | 1727 OLD PARIS RD | 067 | LEX | 2022-11-03 | U125208 | U130722 | 2022-09-05 | 2022-12-30 |  |  | MCRAIG | 2022-11-02 | 2022-10-17 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 22.95 | 6 | 1113.35 | 1100.1 | 173.89 | -160.64 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129102100 |  | 501095669 |  | 6712216L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MERCER | 2001 MERCER RD | 067 | LEX | 2022-11-02 | LSTONE | U125208 | 2022-09-06 | 2022-12-30 |  |  | LSTONE | 2022-11-02 | 2022-10-10 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 40.8 | 13 | 4122.57 | 2531.5 | 0 | 149.07 | 1442 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22141582500 |  | 100278644 |  | 6688232O | 1313370 |  |  | 565 | EX | REPLACE SL | 2621P | SENECA | 1205 SENECA TL | 073 | FRA | 2022-11-02 | DCOLLIN | U132823 | 2022-10-28 | 2022-10-28 |  |  | DCOLLIN | 2022-11-02 | 2022-10-28 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 11.65 | 3 | 4421.4 | 738.89 | 429.7 | 481.13 | 2771.68 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22141851600 |  | 100255617 |  | 7348264H |  |  |  | 566 | EX | ABANDON SL - IDLE/CUSTRQD | 2621P | 1ST | 723 N 1ST ST | 089 | FLA | 2022-11-02 | RECUMP | U125208 | 2022-10-31 | 2022-11-03 | 2022-11-28 |  | RECUMP | 2022-11-02 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 9.7667 | 3 | 541.76 | 535.66 | 19.04 | -12.94 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22141856600 |  | 100417667 |  | 6684228I |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | SKYLINE | 629 SKYLINE RD | 073 | FRA | 2022-11-02 | U128410 | U125208 | 2022-10-31 | 2022-11-03 | 2022-11-21 |  | CDESPAIN | 2022-11-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.45 | 1 | 2454.87 | 226.93 | 222.33 | 13.27 | 1992.34 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22142517500 |  | 100284719 |  | 6760172G |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | PEA RIDGE | 1390 PEA RIDGE RD | 065 | IRV | 2022-11-02 | U126285 | U125763 | 2022-11-02 | 2022-12-30 |  |  | DDAVIS | 2022-11-02 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22142530900 |  | 100327073 |  | 6720212M | 2176779 |  |  | 565 | EX | RPLC SL/21026993800 | 2600B | HIGH | 511 E HIGH ST | 067 | LEX | 2022-11-09 | U461375 | U125763 | 2022-11-02 | 2022-12-30 |  |  | LARRY BROWN | 2022-11-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2481.35 | 0 | 0 | 0 | 2481.35 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22142533100 |  | 501293244 |  | 6692228N | 2072392 |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | WHISPERING PIN | 165 WHISPERING PIN DR | 073 | FRA | 2022-11-02 | U126308 | U129939 | 2022-11-02 | 2022-11-02 |  |  | J ENSMINGER | 2022-11-02 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 10.5 | 1 | 2330.45 | 747.26 | 0 | 728.09 | 855.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22142587100 |  | 100447397 |  | 6764176K |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | WINCHESTER | 1039 WINCHESTER RD | 065 | IRV | 2022-11-02 | U126285 | U125763 | 2022-11-02 | 2022-12-30 |  |  | DDAVIS | 2022-11-02 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.5 | 1 | 2376.89 | 287.59 | 0 | 310.13 | 1779.17 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22979048100 |  | 100449510 |  | 7356152E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OLD COUNTY | 87 OLD COUNTY RD | 071 | HAR | 2022-11-02 | JCKIRK | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | JCKIRK | 2022-11-02 | 2022-10-28 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 15.2333 | 3 | 1146.36 | 1082.96 | 0 | 63.4 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 01477789400 |  | 100437564 |  | 6720216A | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | NEWTOWN | 1825 NEWTOWN PK 3009 | 067 | LEX | 2022-11-04 | U930915 | JTOY | 2001-07-30 | 2022-07-01 | 2022-12-31 |  | LSTONE | 2022-11-03 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.0333 | 2 | 69.85 | 65.97 | 0 | 3.88 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 01485517900 |  | 100337861 |  | 6712216L | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | LEESTOWN | 2551 LEESTOWN RD | 067 | LEX | 2022-11-03 | LSTONE | DMCCULL | 2001-10-16 | 2022-07-01 | 2022-12-31 |  | LSTONE | 2022-11-03 | 2022-11-03 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.9 | 3 | 430.71 | 386.76 | 0 | 43.95 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 01491307600 |  | 100437614 |  | 6720216A | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | NEWTOWN | 1825 NEWTOWN PK 3196 | 067 | LEX | 2022-11-04 | U930915 | DMCCULL | 2001-12-19 | 2022-07-01 | 2022-12-31 |  | LSTONE | 2022-11-03 | 2022-11-03 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.5667 | 3 | 87.04 | 82.2 | 0 | 4.84 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 02508372200 |  | 100437500 | 09 | 6720216A | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | NEWTOWN | 1825 NEWTOWN PK 3146 | 067 | LEX | 2022-11-04 | U930915 | OWHITT | 2002-06-05 | 2022-07-01 | 2022-12-31 |  | LSTONE | 2022-11-03 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.0667 | 2 | 136.01 | 128.48 | 0 | 7.53 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 03527355400 |  | 100295948 |  | ? | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | LIMA | 364 LIMA DR B | 067 | LEX | 2022-11-03 | LSTONE | DMCCULL | 2003-01-10 | 2022-07-01 | 2022-12-31 |  | LSTONE | 2022-11-03 | 2022-11-03 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.7667 | 3 | 2757.63 | 211.43 | 0 | 12.38 | 2533.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 06651973600 |  | 100462696 |  | 6716216F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | SANDERSVILLE | 2370 SANDERSVILLE RD | 067 | LEX | 2022-11-03 | LSTONE | SSUTHER | 2006-06-26 | 2022-07-01 | 2022-12-31 |  | LSTONE | 2022-11-03 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.15 | 2 | 77.31 | 73.03 | 0 | 4.28 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 08731987100 |  | 100284575 |  | W1128-53 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | FLINT | 344 FLINT RD | 151 | WAC | 2022-11-03 | U129722 | U901436 | 2008-05-21 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-11-03 | 2022-11-02 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.8667 | 1 | 4243.5 | 326.65 | 0 | 337.19 | 3579.66 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 09803518000 |  | 100284541 |  | W1128-58 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | COLLEGE HILL | 320 COLLEGE HILL RD | 151 | WAC | 2022-11-03 | U129722 | U123688 | 2009-09-09 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-11-03 | 2022-11-02 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9 | 1 | 4151.6 | 557.93 | 0 | 134.05 | 3459.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11898558800 |  | 100436659 |  | 6716216F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | SANDERSVILLE | 2370< SANDERSVILLE RD | 067 | LEX | 2022-11-03 | LSTONE | U906631 | 2011-03-30 | 2022-07-01 | 2022-12-31 |  | LSTONE | 2022-11-03 | 2022-01-12 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 17.2167 | 6 | 1064.6 | 940.87 | 0 | 123.73 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 16417907200 |  | 500216593 |  | 6716224N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | IRON WORKS | 3250 IRON WORKS PK 3394 | 067 | LEX | 2022-11-04 | U461383 | U122906 | 2016-06-15 | 2022-07-01 | 2022-12-31 |  | LSTONE | 2022-11-03 | 2022-01-13 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.3667 | 3 | 3097.27 | 136.98 | 0 | 20.69 | 2939.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18571896100 |  | 500011961 |  | 6716220J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | GEORGETOWN | 3130 GEORGETOWN RD FG 36 | 067 | LEX | 2022-11-07 | U461383 | U125208 | 2018-01-03 | 2022-07-01 | 2022-12-31 |  | LSTONE | 2022-11-03 | 2022-07-08 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.9833 | 4 | 136.44 | 129.01 | 0 | 7.43 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19740836900 |  | 100465834 | 33 | 6764176M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GARRETT | 251 GARRETT AV | 065 | IRV | 2022-11-03 | U129731 | TJROSEN | 2019-09-11 | 2049-12-31 |  |  | F.GOINS | 2022-11-03 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21026127400 |  |  |  | 7256280K | 2180424 | U122858 |  | 557 | EX | INSTALL 1900'-2"&4" PMIP | 2600B |  |  | 161 | MAY | 2022-11-11 | U128132 | U122858 | 2021-06-08 | 2022-11-16 | 2022-12-31 | 2022-09-22 | DAVID STAGGS | 2022-11-03 | 2022-06-21 |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00557 | 3200557 |  |  | WP1274 | AMRCB |  | 100 | 055732210261274 | 377.8333 | 98900 | 479284.77 | 31209.99 | 80516.79 | 3074.72 | 296887.17 | 0 | 1680.3 | 65915.8 | 1978
KY | KY - CENTRAL | 2632 | 21026127500 |  |  |  | 7256280K | 2180424 | U122858 |  | 558 | EX | RETIRE 1071'-3"&4" WIIP | 2600B |  |  | 161 | MAY | 2022-11-10 | U128132 | U122858 | 2021-06-08 | 2022-12-30 | 2022-12-31 | 2022-09-22 | DAVID STAGGS | 2022-11-03 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00558 | 3200558 |  |  | WP1275 | AMRCB |  | 100 | 055832210261275 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883083500 |  | 501188461 |  | 7356152E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 1ST | 43 1ST ST | 071 | HAR | 2022-11-03 | BPREECE | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | BPREECE | 2022-11-03 | 2022-10-28 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 17.6167 | 3 | 1300.14 | 1228.21 | 0 | 71.93 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883089300 |  | 100351621 |  | 6744208P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEXINGTON | 148 W LEXINGTON AV 1F | 049 | WIN | 2022-11-03 | U126532 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | LESLIE SHARON | 2022-11-03 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.5167 | 1 | 4592.34 | 539.91 | 0 | 586.89 | 3465.54 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883155600 |  | 100343198 |  | 7240212A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WINCHESTER | 1995 WINCHESTER RD B | 173 | MT | 2022-11-03 | U126603 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | SHAWN DENNIS | 2022-11-03 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.5833 | 1 | 2271.05 | 105.44 | 0 | 23.85 | 2141.76 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883166200 |  | 100426589 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | GENERAL DELIVE | GENERAL DELIVE | 119 | LEB | 2022-11-04 | U123965 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | MBLANKE/CJH J HIERONIMUS | 2022-11-03 |  |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 |  | 1 | 1270.07 | 0 | 0 | 0 | 1270.07 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883171000 |  | 100426583 |  | SW50 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | GENERAL DELIVE | GENERAL DELIVE | 119 | HIN | 2022-12-05 | U123965 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | MBLANKE/CJH J HIERONIMUS | 2022-11-03 |  |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 |  | 1 | 1149.35 | 0 | 0 | 0 | 1149.35 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883171900 |  | 100285654 |  | 6764172D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | RIVER | 707 RIVER DR | 065 | IRV | 2022-11-03 | U129722 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-11-03 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9.5 | 1 | 2768.13 | 588.9 | 0 | 85.15 | 2094.08 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883178700 |  | 100406356 |  | 7348140T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NEDS | 420 NEDS FK | 071 | MCD | 2022-11-22 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-11-03 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 6.8833 | 2 | 2815.81 | 486.4 | 0 | 106.23 | 2223.18 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883194100 |  | 100426738 |  | SW50 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | GENERAL DELIVE | GENERAL DELIVE | 119 | HIN | 2022-11-04 | U123965 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | MBLANKE/CJH J HIERONIMUS | 2022-11-03 |  |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 |  | 1 | 1149.35 | 0 | 0 | 0 | 1149.35 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883282000 |  | 100260558 |  | 7348140T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | FRASURE | 4002 FRASURE CK | 071 | MCD | 2022-11-03 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-11-03 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 11.1167 | 2 | 2435.46 | 782.49 | 0 | 170.85 | 1482.12 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883308300 |  | 100261898 |  | 7320132T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | P45 | P45 | 119 | HIN | 2022-11-04 | U123965 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | MBLANKE/CJH J HIERONIMUS | 2022-11-03 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1 | 1270.07 | 0 | 0 | 0 | 1270.07 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883331500 |  | 100403758 |  | 6688228E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | ALLNUTT | 121 ALLNUTT DR | 073 | FRA | 2022-11-03 | U126308 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-11-03 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 429.5 | 0 | 0 | 0 | 429.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883331700 |  | 100461466 |  | 6716212B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | LISLE INDUSTRI | 301 LISLE INDUSTRI AV | 067 | LEX | 2022-11-03 | LSTONE | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | LSTONE | 2022-11-03 | 2022-11-03 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.75 | 3 | 166.44 | 157.22 | 0 | 9.22 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959041100 |  | 100315409 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | WALLER | 219 WALLER AV | 067 | LEX | 2022-11-03 | U461322 | U134723 | 2021-12-10 | 2022-12-30 |  |  | STEVE CANOY | 2022-11-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.5 | 1 | 3922.84 | 701.23 | 0 | 725.39 | 2496.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959041400 |  | 100315411 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | WALLER | 223 WALLER AV | 067 | LEX | 2022-11-03 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-11-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10 | 1 | 3282.88 | 633.32 | 0 | 149.73 | 2499.83 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129036400 |  | 100255550 |  | 7348264K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SUNRISE | 1206 SUNRISE AV | 089 | FLA | 2022-11-07 | U127414 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ED FOX | 2022-11-03 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1615 | 0 | 0 | 0 | 1615 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129044300 |  | 100292125 |  | 6720216G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FREEMAN | 617 FREEMAN DR | 067 | LEX | 2022-11-28 | U127206 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-11-03 | 2022-10-17 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.0667 | 3 | 1734.84 | 231.55 | 0 | 13.79 | 1489.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129080500 |  | 100291859 |  | 6720216G |  |  |  | 566 | VO | ABANDON SL - IDLE/INACTIVE | 2621P | EDEN | 704 EDEN CT | 067 | LEX | 2022-11-07 |  | U130722 | 2022-09-05 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-11-03 |  |  | B | [11 empty] | 22143215000 | 100 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129090900 |  | 100272180 |  | 6684228O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | TODD | 120 E TODD ST | 073 | FRA | 2022-11-03 | U126308 | U130722 | 2022-09-05 | 2022-12-30 |  |  | J ENSMINGER | 2022-11-03 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 10 | 1 | 3742.31 | 711.67 | 0 | 693.42 | 2337.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22141252200 |  | 100336079 |  | 6720212J |  |  |  | 565 | EX | REPLACE SERVICE LINE - D305545 | 2621P | 7TH (763-765) | 761 E 7TH (763-765) ST | 067 | LEX | 2022-11-03 | RSTRONG | U125208 | 2022-10-26 | 2022-10-28 | 2022-11-16 |  | RSTRONG | 2022-11-03 | 2022-10-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 46.1333 | 8 | 7085.72 | 2678.47 | 152.25 | 115.7 | 4139.3 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22141847600 |  | 100282340 |  | 6712228B |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | BROADWAY | 216 N BROADWAY ST | 209 | GEO | 2022-11-03 | U128410 | U125208 | 2022-10-31 | 2022-10-31 | 2022-11-07 |  | CDESPAIN | 2022-11-03 | 2022-11-02 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 17.05 | 2 | 5972.6 | 1121.35 | 442.57 | 65.58 | 4343.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22141894000 |  | 100342139 |  | 7240216N |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | WINN | 219 WINN ST | 173 | MT | 2022-11-03 | DENNING | U132002 | 2022-10-31 | 2022-11-14 | 2022-11-30 |  | DENNING | 2022-11-03 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 12.1 | 2 | 954.65 | 901.84 | 0 | 52.81 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22142562200 |  | 100287805 |  | 6720212C |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | MEADOW | 406 MEADOW PR | 067 | LEX | 2022-11-03 | U127206 | U125763 | 2022-11-02 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-11-03 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1853.07 | 0 | 0 | 0 | 1853.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22142562400 |  | 100289731 |  | 6720216P |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | SPRING STATION | 1988 SPRING STATION DR | 067 | LEX | 2022-11-03 | U127206 | U125763 | 2022-11-02 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-11-03 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1489.5 | 0 | 0 | 0 | 1489.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22142565700 |  | 100347202 |  | 6696212J |  |  |  | 565 | EX | SERVICE LINE - REPLACE EMER | 2621P | CLIFTON | 509 CLIFTON RD | 239 | VER | 2022-11-03 | BSEXTON | U125208 | 2022-11-02 | 2022-11-03 |  |  | BSEXTON | 2022-11-03 | 2022-11-03 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 21.5667 | 5 | 1550.18 | 1242.57 | 0 | -82.39 | 390 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22142744400 |  | 500511327 |  | 7344264C |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | POWELL | 306 POWELL ST | 089 | WUR | 2022-11-07 | U126286 | U125763 | 2022-11-03 | 2022-12-30 |  |  | TYLER ALLISON | 2022-11-03 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 10 | 1 | 2095.16 | 694.52 | 0 | 40.64 | 1360 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22142786300 |  | 100351623 |  | 6744208P |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | LEXINGTON | 148 W LEXINGTON AV 2F | 049 | WIN | 2022-11-03 | U126532 | U125763 | 2022-11-03 | 2022-12-30 |  |  | LESLIE SHARON | 2022-11-03 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - EAST | 2631 | 22142787600 |  | 100259688 |  | 7348264B |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | ALLEN | 1201 ALLEN AV | 089 | WOR | 2022-11-09 | U127414 | U125763 | 2022-11-03 | 2022-12-30 |  |  | ED FOX | 2022-11-03 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.9333 | 1 | 2038.09 | 399.7 | 0 | 23.39 | 1615 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22142815900 |  | 100278645 |  | 6688232O |  |  |  | 565 | EX | SERVICE LINE REPLACE | 2621P | SENECA | 1207 SENECA TL | 073 | FRA | 2022-11-04 | U125208 | U134852 | 2022-11-03 | 2022-11-03 |  |  | DCOLLIN | 2022-11-03 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.7167 | 1 | 373.83 | 121.82 | 232.79 | 7.12 | 12.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22142816200 |  | 100468254 |  | 7240216J |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | MAYSVILLE | 508 MAYSVILLE RD 2 | 173 | MT | 2022-11-03 | U126603 | U125763 | 2022-11-03 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-11-03 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.3833 | 1 | 1828.08 | 162.47 | 0 | 36.77 | 1628.84 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979020000 |  | 100250739 |  | 7336268H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SYCAMORE | 608 SYCAMORE ST | 089 | GRE | 2022-11-03 | U126286 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | TYLER ALLISON | 2022-11-03 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 12 | 1 | 2242.18 | 833.42 | 0 | 48.76 | 1360 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979049700 |  | 100468031 |  | 7240216J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAYSVILLE | 508 MAYSVILLE RD 1 | 173 | MT | 2022-11-03 | U126603 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | SHAWN DENNIS | 2022-11-03 | 2022-10-27 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10.9 | 2 | 5704.81 | 633.54 | 0 | 139.66 | 4931.61 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22985296400 |  | 100342209 |  | 7240216N |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2600B | VIRGINIA | 10 VIRGINIA CT | 173 | MT | 2022-11-03 | U126603 | U134723 | 2022-03-11 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-11-03 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.6333 | 1 | 2340.49 | 175.91 | 0 | 39.81 | 2124.77 | 0 | 0 | 0
KY | KY - WEST | 2621 | 94160134200 |  | 100296047 |  | 6716216O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | LIMA | 660 LIMA DR | 067 | LEX | 2022-11-03 | LSTONE | THAGGAR | 1994-02-11 | 2022-07-01 | 2022-12-31 |  | LSTONE | 2022-11-03 | 2022-11-03 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.7667 | 3 | 879.37 | 97.85 | 0 | 5.74 | 775.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 02496134200 |  | 100333235 |  | 6720212I |  |  |  | 566 | EX | ABANDON SL - SOII/INSIDE | 2621P | CLARK | 212 CLARK ST | 067 | LEX | 2022-11-10 | U125208 | DMCCULL | 2002-01-31 | 2022-11-04 | 2022-11-04 |  | LSTONE | 2022-11-04 | 2022-11-04 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.1667 | 4 | 203.05 | 191.8 | 0 | 11.25 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 02521883600 |  | 100291183 |  | 6724216E | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PARIS | 2600 PARIS PK | 067 | LEX | 2022-11-04 | U930915 | DMCCULL | 2002-11-05 | 2022-07-01 | 2022-12-31 |  | LSTONE | 2022-11-04 | 2022-11-04 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.1 | 3 | 259.13 | 244.81 | 0 | 14.32 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 05627144300 |  | 100335475 |  | 6712224P | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | GEORGETOWN | 4054 GEORGETOWN RD | 067 | LEX | 2022-11-04 | U126308 | SSUTHER | 2005-10-27 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-11-04 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.5 | 1 | 1334.85 | 676.1 | 0 | 658.75 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11918566600 |  | 100442881 |  | 7240216N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WINN | 117 WINN ST 1FL | 173 | MT | 2022-11-04 | U124003 | U907469 | 2011-08-02 | 2022-07-01 | 2022-12-31 |  | BPULLIAM/MILLER | 2022-11-04 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.1667 | 1 | 636.24 | 213.15 | 0 | 423.09 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 11922358300 |  | 100240909 |  | 7324132F | 2290467 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAIN | 651 E MAIN ST | 119 | HIN | 2022-11-04 | U123965 | U124449 | 2011-08-30 | 2022-07-01 | 2022-12-31 |  | MBLANKE/CJH J HADLEY | 2022-11-04 | 2022-10-06 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 21.2333 | 4 | 2387 | 1331.98 | 0 | 79.2 | 975.82 | 0 | 0 | 0
KY | KY - EAST | 2633 | 12967969800 |  | 100414590 |  | 7324132F | 2290467 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | OLD GARNER | 582 OLD GARNER RD | 119 | HIN | 2022-11-09 | U123965 | U908560 | 2012-05-02 | 2022-07-01 | 2022-12-31 |  | MBLANKE/CJH JOE HADLEY | 2022-11-04 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1 | 1171.99 | 0 | 0 | 0 | 1171.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883187100 |  | 100320497 |  | 6716212O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | WASHINGTON | 152 WASHINGTON AV | 067 | LEX | 2022-11-04 | LSTONE | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | LSTONE | 2022-11-04 | 2022-10-04 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.6 | 4 | 150.42 | 142.09 | 0 | 8.33 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883187200 |  | 100320498 |  | 6716212O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | WASHINGTON | 148 WASHINGTON AV | 067 | LEX | 2022-11-04 | LSTONE | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | LSTONE | 2022-11-04 | 2022-11-04 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.5833 | 3 | 219.27 | 207.16 | 0 | 12.11 | 0 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883208300 |  | 100426657 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2633S | SWIFT SHOAL | 21 SWIFT SHOAL BR | 119 | HIN | 2022-12-05 | U123965 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | MBLANKE/CJH JORDAN HIERONIMUS | 2022-11-04 |  |  | B | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 |  | 1 | 1292.71 | 0 | 0 | 0 | 1292.71 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883322600 |  | 500727322 |  | 6724212M | 0041732 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | FORTUNE | 2473 FORTUNE DR 6 | 067 | LEX | 2022-11-04 | U126308 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-11-04 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1163.67 | 0 | 0 | 0 | 1163.67 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883323300 |  | 100332857 |  | 6720208L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | RICHMOND | 2840 RICHMOND RD | 067 | LEX | 2022-11-04 | LSTONE | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | LSTONE | 2022-11-04 | 2022-11-04 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.3333 | 3 | 130.41 | 123.19 | 0 | 7.22 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883332000 |  | 100432959 |  | 6716204B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | REYNOLDS | 113 E REYNOLDS RD | 067 | LEX | 2022-11-04 | U930915 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | TROE | 2022-11-04 | 2021-08-25 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.0167 | 7 | 353.23 | 333.62 | 0 | 19.61 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21884186200 |  | 100264594 |  | 7384168G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY D327175 | 2621P | SR292 | 2975 SR292 | 195 | S W | 2022-11-04 | JCKIRK | U128293 | 2021-02-04 | 2022-10-13 | 2022-10-13 |  | JCKIRK | 2022-11-04 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 16 | 2 | 4284.82 | 1163.55 | 0 | 68.06 | 3053.21 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21916436800 |  | 100265025 |  | 7352260N | 2176770 |  |  | 565 | EX | RPLC SL/21026993400/ | 2600B | MAIN | 2105 MAIN ST W | 019 | ASH | 2022-11-04 | U124015 | U131066 | 2021-06-03 | 2022-11-01 |  |  | ORA SLONE | 2022-11-04 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2069.18 | 0 | 0 | 0 | 2069.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21928446600 |  | 100299998 |  | 6716212F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | THOMPSON | 309 THOMPSON RD | 067 | LEX | 2022-11-04 | U127206 | U125208 | 2021-07-27 | 2022-07-29 | 2022-12-31 |  | JUSTIN HOBBS | 2022-11-04 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 505.81 | 477.86 | 0 | 27.95 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22130538500 |  | 100353802 |  | 7256280L | 1855043 |  |  | 566 | EX | ABANDON SL - SOII/INSIDE | 2621P | STANLEY REED | 210 STANLEY REED CT | 161 | MAY | 2022-11-04 | SDADAMS | U130868 | 2022-09-09 | 2022-09-09 | 2022-12-31 |  | SDADAMS | 2022-11-04 | 2022-10-03 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 14.1167 | 6 | 2402.98 | 895.43 | 190.99 | 183.56 | 1133 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22142774000 |  | 100302766 |  | 6712212N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | COLONIAL | 1264 COLONIAL DR | 067 | LEX | 2022-11-04 | U930915 | U134852 | 2022-11-03 | 2023-12-21 |  |  | KKINDER | 2022-11-04 | 2022-11-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 53.8833 | 7 | 6199.86 | 3127.46 | 439.04 | 33.03 | 2600.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22142992200 |  | 100289609 |  | 6720215P |  |  |  | 565 | EX | GRADE 1 LK | 2621P | GLENGARRY | 1902 GLENGARRY WY | 067 | LEX | 2022-11-04 | RSTRONG | U124449 | 2022-11-04 | 2022-11-04 | 2022-11-04 |  | RSTRONG | 2022-11-04 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18 | 3 | 1404.39 | 1022.42 | 301.04 | -11.47 | 92.4 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22143005500 |  | 100351373 |  | 6736212P |  |  |  | 566 | EX | ABANDONMENT ON PAPER | 2621P | CLINTONVILLE | 200 CLINTONVILLE RD | 049 | WIN | 2022-11-04 | U126532 | U126532 | 2022-11-04 | 2049-12-31 |  |  | LESLIE SHARON | 2022-11-04 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 | AMRMR |  | 100 | 056632B26290057 |  | 1
KY | KY - WEST | 2621 | 22988121500 |  | 100332847 |  | 6720208H |  |  |  | 566 | EX | ABANDON SL- I/I/LGCY | 2600B | RICHMOND | 2450 RICHMOND RD | 067 | LEX | 2022-11-04 | U126308 | U134723 | 2022-03-23 | 2022-12-30 |  |  | J ENSMINGER | 2022-11-04 | 2022-10-12 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.5667 | 2 | 150.14 | 86.97 | 0 | 63.17 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 94195303200 |  | 100332853 |  | X00000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | RICHMOND | 2880 RICHMOND RD | 067 | LEX | 2022-11-04 | U930915 | KEMBERT | 1994-12-15 | 2022-07-01 | 2022-12-31 |  | LSTONE | 2022-11-04 | 2022-10-04 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.5667 | 4 | 151.4 | 143.03 | 0 | 8.37 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 98342593800 |  | 100328288 |  | 6716204H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | OLD TATES CRK | 3748 OLD TATES CRK PK | 067 | LEX | 2022-11-04 | TROE | TDORTEN | 1998-04-15 | 2022-07-01 | 2022-12-31 |  | TROE | 2022-11-04 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.55 | 3 | 3387.75 | 265.37 | 0 | 19.26 | 3103.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22143190100 |  | 100455081 |  | 6720204C |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | YELLOWSTONE | 3224 YELLOWSTONE PY | 067 | LEX | 2022-11-06 | KKINDER | U134852 | 2022-11-05 | 2022-11-05 | 2022-11-05 |  | KKINDER | 2022-11-06 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 12 | 4 | 971.49 | 692.88 | 195.17 | 40.54 | 42.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 00433185200 |  | 100281237 |  | 16704216D | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | OLD FRANKFORT | 729 OLD FRANKFORT PK FG13 | 239 | VER | 2022-11-07 | U126308 | KEMBERT | 2000-05-15 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-11-07 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 246.8 | 0 | 0 | 0 | 246.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 03528760300 |  | 100347112 |  | 6696212J | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | M L KING | M L KING BV | 239 | VER | 2022-11-07 | U126308 | DMCCULL | 2003-01-24 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-11-07 | 2022-10-06 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.18333 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 03534018200 |  | 100409745 |  | X00000000 | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | R3 LAWRENCEBUR | R3 LAWRENCEBUR RD | 239 | VER | 2022-11-09 | U126308 | DMCCULL | 2003-03-18 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-11-07 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 100.6 | 0 | 0 | 0 | 100.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 04565633700 |  | 100416915 |  | 6716216O | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | ROOSEVELT | 430 N ROOSEVELT BV | 067 | LEX | 2022-11-07 | U127206 | SSUTHER | 2004-02-11 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-11-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 4585.24 | 477.86 | 0 | 27.95 | 4079.43 | 0 | 0 | 0
KY | KY - WEST | 2621 | 06650409300 |  | 500011246 |  | 6720200A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | TATES CREEK | 4900 TATES CREEK RD | 067 | LEX | 2022-11-07 | LSTONE | SSUTHER | 2006-06-08 | 2022-10-10 | 2022-12-31 |  | LSTONE | 2022-11-07 | 2022-10-04 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.5167 | 5 | 1445.92 | 572.93 | 0 | 69.47 | 803.52 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 06663654900 |  | 500504292 |  | 6764176B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | WHITE OAK | 460 WHITE OAK RD | 065 | IRV | 2022-11-07 | U129731 | CTAULBE | 2006-10-19 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-11-07 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 2537.55 | 499.72 | 0 | 119.38 | 1918.45 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11913450300 |  | 500225363 |  | W-1128/60 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | FLINT | 280 FLINT RD | 151 | WAC | 2022-11-07 | U129722 | U124964 | 2011-06-27 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-11-07 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 2917.74 | 495.93 | 0 | 119.15 | 2302.66 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11916281500 |  | 100343815 |  | 7240208A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEVEE | 4822 LEVEE RD | 173 | MT | 2022-11-07 | U126603 | U124964 | 2011-07-18 | 2022-07-01 | 2022-12-31 |  | SHAWN DENNIS | 2022-11-07 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.4 | 1 | 2295.9 | 230.31 | 0 | 52.13 | 2013.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18026757700 |  |  |  | 6732216L | 1851238 | U461383 |  | 909 | EX | INSTALL MI WIRELESS EFC | 2600E | BRIAR HILL | BRIAR HILL RD | 067 | LEX | 2022-11-17 | U123258 | U461383 | 2018-03-08 | 2018-10-01 | 2018-10-01 | 2022-11-07 | JMULLINS | 2022-11-07 | 2022-11-07 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP7577 |  |  | 100 | 090932180267577 | 10 | 0 | 14191.42 | 1287.02 | 9086.44 | 1100.04 | 2308.06 | 0 | 409.86 | 0
KY | KY - WEST | 2621 | 18026757800 |  |  |  | 6732216L | 1851238 | U461383 |  | 584 | EX | RETIRE RECORDING GAUGE | 2600E | BRIAR HILL | BRIAR HILL RD | 067 | LEX | 2022-11-17 | U123258 | U461383 | 2018-03-08 | 2020-10-01 | 2020-10-01 | 2022-11-07 | JMULLINS | 2022-11-07 |  |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00584 | 3200584 |  |  | WP7578 |  |  | 100 | 058432180267578 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883139500 |  | 100426702 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | ALUM LICK | 369 ALUM LICK RD | 071 | MAR | 2022-11-22 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-11-07 |  |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 |  | 1 | 1368.31 | 0 | 0 | 0 | 1368.31 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883140300 |  | 100426780 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2633S | SJK | 52 SJK DR | 119 | PIN | 2022-11-08 | U123965 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | MBLANKE/CJH J HIERONIMUS | 2022-11-07 |  |  | B | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 |  | 1 | 1398.34 | 0 | 0 | 0 | 1398.34 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883159700 |  | 100429232 |  | 7324124T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | HIGHWAY 582 | 3132 HIGHWAY 582 | 119 | PIN | 2022-12-05 | U123965 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | MBLANKE/CJH CASEY PACK | 2022-11-07 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1 | 855.1 | 0 | 0 | 0 | 855.1 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883176100 |  | 100426426 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2633S | MARTIN | 126 MARTIN BR | 071 | HUE | 2022-11-07 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-11-07 |  |  | B | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 4.4333 | 1 | 1864.3 | 313.68 | 0 | 68.5 | 1482.12 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883201500 |  | 100428973 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2633S | BRANHAMS CREEK | 2624 BRANHAMS CREEK RD | 119 | MAL | 2022-11-08 | U123965 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | MBLANKE/CJH CASEY PACK | 2022-11-07 |  |  | B | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 |  | 1 | 855.1 | 0 | 0 | 0 | 855.1 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883272000 |  | 100426417 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2633S | SALYERS | 64 SALYERS BR | 071 | HUE | 2022-11-22 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-11-07 |  |  | B | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 5.5667 | 1 | 1958.79 | 391.26 | 0 | 85.41 | 1482.12 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883290800 |  | 100452285 |  | Y161616 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2633S | EAGLES NEST | 494 EAGLES NEST RD | 119 | EMM | 2022-11-08 | U123965 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | MBLANKE/CJH CASEY PACK | 2022-11-07 |  |  | B | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 |  | 1 | 855.1 | 0 | 0 | 0 | 855.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883312700 |  | 100444843 |  | 7240208A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEVEE | 4793 LEVEE RD | 173 | MT | 2022-11-07 | U126603 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | SHAWN DENNIS | 2022-11-07 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.8833 | 1 | 2120.64 | 192.01 | 0 | 43.47 | 1885.16 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883316400 |  | 100343061 |  | 7240212A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAIN | 407 W MAIN ST | 173 | MT | 2022-11-07 | U126532 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | LESLIE SHARON | 2022-11-07 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2013.46 | 0 | 0 | 0 | 2013.46 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883329600 |  | 500342830 |  | 6712228E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | REDDING | REDDING RD | 209 | GEO | 2023-01-23 | U126308 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-11-07 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2623 | 21947535600 |  | 100274257 |  | 6684228N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | COLEMAN | 312 COLEMAN AV WS | 073 | FRA | 2022-11-07 | U128816 | U131066 | 2021-10-19 | 2022-07-01 | 2022-12-31 |  | OLIVER MAYNARD | 2022-11-07 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 1.9167 | 1 | 1030.08 | 118.66 | 0 | 6.94 | 904.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959040100 |  | 100315437 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | WALLER | 124 WALLER AV | 067 | LEX | 2022-11-08 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-11-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2247.38 | 506.65 | 0 | 119.77 | 1620.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959040700 |  | 100315433 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | WALLER | 136 WALLER AV | 067 | LEX | 2022-11-07 | U461322 | U134723 | 2021-12-10 | 2022-12-30 |  |  | STEVE CANOY | 2022-11-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.9833 | 1 | 2430.35 | 666.5 | 0 | 689.47 | 1074.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960235800 |  | 100327071 |  | 6720212M | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | HIGH | 521 E HIGH ST 2F | 067 | LEX | 2022-11-17 | U461375 | U134723 | 2021-12-17 | 2022-12-30 |  |  | LARRY BROWN | 2022-11-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 5297.39 | 0 | 0 | 0 | 5297.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960251000 |  | 100320949 |  | 6720212M | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | HIGH | 496 E HIGH ST | 067 | LEX | 2022-11-17 | U461375 | U134723 | 2021-12-17 | 2022-12-30 |  |  | LARRY BROWN | 2022-11-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 7888.11 | 0 | 0 | 0 | 7888.11 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129035200 |  | 500579507 |  | 7348264O | 9723038 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ARGILLITE | 2000 ARGILLITE RD 28 | 089 | FLA | 2022-11-09 | U127414 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ED FOX | 2022-11-07 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.05 | 1 | 1611.27 | 204.91 | 0 | 46.36 | 1360 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129058600 |  | 100284759 |  | 6760176M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PEA RIDGE | 195 PEA RIDGE RD | 065 | IRV | 2022-11-11 | U126284 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JOSH PASLEY | 2022-11-07 | 2022-10-18 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 41.5 | 5 | 14560.1 | 2523.22 | 0 | 1228.34 | 10808.54 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129072800 |  | 100267014 |  | 7352260J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BROTHERS | 115 BROTHERS CT | 089 | ASH | 2022-11-10 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-11-07 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1360 | 0 | 0 | 0 | 1360 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129081700 |  | 100338971 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LOUDON | 295 E LOUDON AV | 067 | LEX | 2022-11-07 | HMCKUNE | U130722 | 2022-09-05 | 2022-12-30 |  |  | HMCKUNE | 2022-11-07 | 2022-11-03 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.2833 | 4 | 2660.53 | 963.44 | 33.49 | 56.37 | 1607.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22141245100 |  | 100338970 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE + | 2621P | LOUDON | 295 E LOUDON AV 1FR | 067 | LEX | 2022-11-07 | HMCKUNE | U125208 | 2022-10-26 | 2022-12-30 |  |  | HMCKUNE | 2022-11-07 | 2022-11-03 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 14.2667 | 4 | 1075.81 | 586.56 | 0 | 489.25 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22141251600 |  | 100325361 |  | 6720208M |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303481 | 2621P | MONTAVESTA | 2974 MONTAVESTA RD | 067 | LEX | 2022-11-07 | JOCHOA | U125208 | 2022-10-26 | 2022-10-28 | 2022-11-16 |  | JOCHOA | 2022-11-07 | 2022-11-04 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 22.15 | 5 | 2071.01 | 1518.11 | 401.42 | 88.78 | 62.7 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22143205000 |  | 100283003 |  | 6712228C | 1313370 |  |  | 565 | EX | REPLACE SL | 2621P | CLAYTON | 605 CLAYTON AV | 209 | GEO | 2022-11-07 | DCOLLIN | U132823 | 2022-11-07 | 2022-11-07 |  |  | DCOLLIN | 2022-11-07 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 21.2667 | 2 | 2145.06 | 1484.16 | 262.35 | -483.38 | 881.93 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22143208200 |  | 100344311 |  | 7240212C |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | FOX | 307 FOX ST | 173 | MT | 2022-11-07 | U126532 | U125763 | 2022-11-07 | 2022-12-30 |  |  | LESLIE SHARON | 2022-11-07 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10.5 | 1 | 2332.86 | 665.39 | 0 | 38.91 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22143209500 |  | 100343527 |  | 7240212A |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | SPRING | 407< SPRING ST | 173 | MT | 2022-11-07 | U126603 | U125763 | 2022-11-07 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-11-07 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.7167 | 1 | 2272.12 | 315.54 | 0 | 71.42 | 1885.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22143215000 |  | 100291859 |  | 6720216G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | EDEN | 704 EDEN CT | 067 | LEX | 2022-11-07 | U127206 | U123119 | 2022-11-07 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-11-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 8 | 1 | 6202.85 | 477.86 | 245.03 | 27.95 | 5452.01 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22143232900 |  | 100239581 |  | 7352264I |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | BOYD | 453 BOYD ST | 089 | RUS | 2022-11-07 | U127414 | U125763 | 2022-11-07 | 2022-12-30 |  |  | ED FOX | 2022-11-07 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.8833 | 1 | 1633.64 | 329.16 | 0 | 74.48 | 1230 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22143241400 |  | 100282922 |  | 6712228C | 1313370 |  |  | 565 | EX | REPLACE SL | 2621P | DUDLEY | 512 DUDLEY AV | 209 | GEO | 2022-11-08 | U930915 | U132823 | 2022-11-07 | 2022-11-07 |  |  | DCOLLIN | 2022-11-07 | 2022-11-07 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 23.2833 | 6 | 1991.22 | 1543.11 | 425.52 | -30.21 | 52.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22143243400 |  | 100327066 |  | 6720212M | 2176779 |  |  | 565 | EX | RPLC SL/21026993800 | 2600B | KENTUCKY | 195 KENTUCKY AV 1F | 067 | LEX | 2022-11-09 | U461375 | U125763 | 2022-11-07 | 2022-12-30 |  |  | LARRY BROWN | 2022-11-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2831.32 | 0 | 0 | 0 | 2831.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22143274100 |  | 500140951 |  | 6716212L |  |  |  | 566 | EX | ABANDN SL/ | 2600B | LIMESTONE | 1536 N LIMESTONE ST RR | 067 | LEX | 2022-11-08 | U128762 | U125763 | 2022-11-07 | 2022-12-30 |  |  | CORY TINCHER | 2022-11-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 538.12 | 0 | 0 | 0 | 538.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22143276400 |  | 500287309 |  | 6700220P | 1313370 |  |  | 566 | EX | ABANDON SL | 2621P | OLD FRANKFORT | 2787 OLD FRANKFORT PK FT-FG31 | 239 | VER | 2022-11-08 | U461383 | U132823 | 2022-11-07 | 2022-11-07 |  |  | J ENSMINGER | 2022-11-07 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26230043 | 11.5 | 0 | 2045.38 | 818.44 | 0 | 797.44 | 429.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22143420700 |  | 100343999 |  | 7240208A |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | LEVEE | 4855 LEVEE RD | 173 | MT | 2022-11-11 | U126603 | U125763 | 2022-11-08 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-11-07 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - EAST | 2631 | 22979021500 |  | 100254583 |  | 7348264O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BAILEY | 1905 BAILEY LN | 089 | FLA | 2022-11-10 | U127414 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | ED FOX | 2022-11-07 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.0667 | 1 | 1693.63 | 272.08 | 0 | 61.55 | 1360 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979026700 |  | 100267018 |  | 7352260J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BROTHERS | 111 BROTHERS CT | 089 | ASH | 2022-11-11 | U126286 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | TYLER ALLISON | 2022-11-07 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1615 | 0 | 0 | 0 | 1615 | 0 | 0 | 0
KY | KY - WEST | 2623 | 06651830800 |  | 100407383 |  | 6680224D | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | LOUISVILLE | 1358 LOUISVILLE RD | 073 | FRA | 2023-06-15 | U128816 | RPOLLY | 2006-06-23 | 2022-11-07 | 2023-12-31 |  | OLIVER MAYNARD | 2022-11-08 | 2022-11-07 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 10.1833 | 3 | 3417.31 | 637.01 | 64.62 | 37.28 | 2678.4 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 06659979900 |  | 100461692 |  | 6764176C |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | WHITE OAK | 335 WHITE OAK RD | 065 | IRV | 2022-11-08 | U129722 | SKSMITH | 2006-09-12 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-11-08 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2436.39 | 0 | 0 | 0 | 2436.39 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 07689004300 |  | 100451314 |  | W-1103/20 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WACO LOOP | 526 WACO LOOP | 151 | WAC | 2022-11-08 | U129722 | U903504 | 2007-05-31 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-11-08 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9 | 1 | 2320.54 | 557.93 | 0 | 134.05 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11898472200 |  | 100286245 |  | X-1206/43 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | IRVINE | 1190 S IRVINE RD | 065 | IRV | 2022-11-08 | U126602 | U906631 | 2011-03-30 | 2022-07-01 | 2022-12-31 |  | DEREK PAYTON | 2022-11-08 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 6678.45 | 480.88 | 0 | 28.12 | 6169.45 | 0 | 0 | 0
KY | KY - WEST | 2621 | 13121089700 |  | 100313678 |  | 6716208B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WALLER | 366 WALLER AV 112 | 067 | LEX | 2022-11-08 | U127206 | U124967 | 2013-03-01 | 2020-12-31 |  |  | JUSTIN HOBBS | 2022-11-08 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1610.69 | 0 | 0 | 0 | 1610.69 | 0 | 0 | 0
KY | KY - WEST | 2623 | 14234564800 |  | 100447596 |  | 6684224E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | US 127 | 1303 US 127 SO STE 113 | 073 | FRA | 2022-11-08 | U126308 | U127104 | 2014-07-15 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-11-08 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 12 | 1 | 2594.84 | 854.02 | 0 | 832.1 | 908.72 | 0 | 0 | 0
KY | KY - WEST | 2623 | 16424860400 |  | 100282004 |  | 6712232O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WEST | 112 WEST ST | 209 | GEO | 2022-11-08 | U126308 | U122906 | 2016-07-08 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-11-08 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1238.6 | 0 | 0 | 0 | 1238.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21874916800 |  | 100448454 |  | 6740296F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | RIVERTON | 240 RIVERTON RD | 023 | FOS | 2022-12-07 | U125559 | U123981 | 2021-01-15 | 2022-07-01 | 2022-12-31 |  | BJACKSON | 2022-11-08 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1
KY | KY - EAST | 2631 | 21883049800 |  | 501169540 |  | 7360216E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | TOMAHAWK | 85 TOMAHAWK DR | 127 | LOU | 2022-11-08 | U126286 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | TYLER ALLISON | 2022-11-08 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1360 | 0 | 0 | 0 | 1360 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883062700 |  | 100253552 |  | 7360196T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LITTLE LICK | 618 LITTLE LICK RD | 159 | INE | 2022-11-09 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-11-08 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1 | 2850.43 | 0 | 0 | 0 | 2850.43 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883113700 |  | 100426616 |  | IGC1 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2633S | VEST TALCUM | 5362 VEST TALCUM | 119 | TAL | 2022-11-08 | U123965 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | MBLANKE/CJH J HIERONIMUS | 2022-11-08 |  |  | B | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 |  | 1 | 1217.26 | 0 | 0 | 0 | 1217.26 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883121300 |  | 100252063 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | FITCH BRANCH | 446 FITCH BRANCH | 159 | INE | 2022-11-10 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-11-08 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1 | 2850.43 | 0 | 0 | 0 | 2850.43 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883122400 |  | 100462102 |  | 6764176F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WINCHESTER | 1984 WINCHESTER RD | 065 | IRV | 2022-11-08 | U126532 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | LESLIE SHARON | 2022-11-08 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.5 | 1 | 2422.5 | 285.18 | 0 | 16.69 | 2120.63 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883131200 |  | 500687658 |  | 7356216H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NUTMEG | 24 NUTMEG CT | 127 | LOU | 2022-11-08 | U127414 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | ED FOX | 2022-11-08 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 8.1 | 1 | 2409.75 | 544.14 | 0 | 123.11 | 1742.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883254700 |  | 500440454 |  | 7356216H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | APPLE | 8 APPLE CT | 127 | LOU | 2022-11-08 | U126286 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | TYLER ALLISON | 2022-11-08 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 2023 | 0 | 0 | 0 | 2023 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883283100 |  | 100439372 |  | 6764176F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WINCHESTER | 1975 WINCHESTER RD | 065 | IRV | 2022-11-08 | U126532 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | LESLIE SHARON | 2022-11-08 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.5 | 1 | 1997.5 | 348.55 | 0 | 20.39 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883316800 |  | 500283655 |  | 6748208P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | GREENWAY | 476 GREENWAY DR | 049 | WIN | 2022-11-17 | U129731 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-11-08 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 1550.15 | 499.72 | 0 | 119.38 | 931.05 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21884244300 |  | 100276570 |  | 6684228H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | OWENTON | 719 OWENTON AV | 073 | FRA | 2022-11-08 | U126308 | U128293 | 2021-02-04 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-11-08 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1499.35 | 0 | 0 | 0 | 1499.35 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959040300 |  | 100315436 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | WALLER | 126 WALLER AV B-REAR | 067 | LEX | 2022-11-08 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-11-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.75 | 1 | 2213.87 | 617.49 | 0 | 145.98 | 1450.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129004900 |  | 100313680 |  | 6716208B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WALLER | 366 WALLER AV 113 | 067 | LEX | 2022-11-28 | U127206 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-11-08 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 3179.75 | 0 | 0 | 0 | 3179.75 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129024100 |  | 100354934 |  | 7260280M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 2ND | 838 E 2ND ST | 161 | MAY | 2022-11-08 | SDADAMS | U130722 | 2022-09-05 | 2022-12-30 |  |  | SDADAMS | 2022-11-08 | 2022-11-07 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 4.8667 | 2 | 615.44 | 316.86 | 16.08 | 282.5 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129024200 |  | 100354941 |  | 7260280M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | 2ND | 830 E 2ND ST | 161 | MAY | 2022-11-08 | SDADAMS | U130722 | 2022-09-05 | 2022-12-30 |  |  | SDADAMS | 2022-11-08 | 2022-11-07 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 10.8 | 3 | 976.36 | 710.16 | 16.08 | 250.12 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129024400 |  | 100354154 |  | 7256280P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | 4TH | 330 E 4TH ST | 161 | MAY | 2022-11-08 | SDADAMS | U130722 | 2022-09-05 | 2022-12-30 |  |  | SDADAMS | 2022-11-08 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 9.75 | 2 | 968.24 | 637.85 | 16.08 | 314.31 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129044700 |  | 100292206 |  | 6720216G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | JUDY | 611 JUDY LN | 067 | LEX | 2022-11-08 | JOCHOA | U130722 | 2022-09-05 | 2022-12-30 |  |  | JOCHOA | 2022-11-08 | 2022-10-14 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 20.6833 | 8 | 1336.03 | 1261.95 | 0 | 74.08 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129046700 |  | 100295378 |  | 6716212D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GEORGETOWN | 450 GEORGETOWN ST | 067 | LEX | 2022-11-08 | U127206 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-11-08 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 6002.6 | 0 | 0 | 0 | 6002.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129083700 |  | 100296961 |  | 6716212D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CHARLES | 737 CHARLES AV | 067 | LEX | 2022-11-08 | U930915 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KKINDER | 2022-11-08 | 2022-10-18 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 17.8 | 8 | 1168 | 1047.38 | 34.04 | 86.58 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22137501000 |  | 100338390 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SHELBY | 563 SHELBY ST | 067 | LEX | 2022-11-08 | U930915 | U130722 | 2022-10-07 | 2022-12-30 |  |  | KKINDER | 2022-11-08 | 2022-10-31 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 23.4 | 9 | 1520.17 | 1414.17 | 22.84 | 83.16 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22141228900 |  | 100333611 |  | 6720212I |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | 3RD | 206 E 3RD ST | 067 | LEX | 2022-11-08 | HMCKUNE | U132002 | 2022-10-26 | 2022-11-09 | 2022-11-26 |  | HMCKUNE | 2022-11-08 | 2022-10-31 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 49.4333 | 16 | 3624.14 | 2336.88 | 19.59 | 765.17 | 502.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22141252700 |  | 100259784 |  | 7356256F |  |  |  | 565 | EX | AOC ENCROACHMENT-COMPLIANT | 2621P | HILTON | 2425 HILTON AV | 019 | ASH | 2022-11-08 | RECUMP | U125208 | 2022-10-26 | 2022-10-28 | 2022-11-14 |  | RECUMP | 2022-11-08 | 2022-11-02 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26310031 | 69.3333 | 10 | 5230.87 | 3969.3 | 79.81 | 1069.56 | 112.2 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22141940200 |  | 100347041 |  | 6696212K | 1313370 |  |  | 565 | EX | REPLACE SL | 2621P | WOODLAWN | 115 WOODLAWN DR 1 | 239 | VER | 2022-11-09 | U128410 | U132823 | 2022-10-31 | 2022-10-31 |  |  | CDESPAIN | 2022-11-08 | 2022-11-07 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 36.05 | 3 | 9553.83 | 2201.88 | 897.82 | 128.77 | 6325.36 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22142282000 |  | 100431855 |  | 7240212B |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | BANK | 25 S BANK ST 2FR | 173 | MT | 2022-11-08 | DENNING | U132002 | 2022-11-01 | 2022-11-15 | 2022-12-01 |  | DENNING | 2022-11-08 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 17.35 | 6 | 1321.11 | 1248.08 | 0 | 73.03 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22142283400 |  | 100343460 |  | 7240212B |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | BANK | 25 S BANK ST 2FL | 173 | MT | 2022-11-08 | DENNING | U132002 | 2022-11-01 | 2022-11-15 | 2022-12-01 |  | DENNING | 2022-11-08 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.5 | 3 | 416.03 | 393.02 | 0 | 23.01 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22142285000 |  | 100343461 |  | 7240212B |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | BANK | 25 S BANK ST | 173 | MT | 2022-11-08 | U930915 | U132002 | 2022-11-01 | 2022-11-15 | 2022-12-01 |  | DENNING | 2022-11-08 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9.4 | 3 | 1477.62 | 673.65 | 0 | 39.45 | 764.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22143272100 |  | 100315384 |  | 6716208C | 2176780 |  |  | 565 | EX | RPLC SL/21026994000 | 2600B | UNIVERSITY | 122 UNIVERSITY AV | 067 | LEX | 2022-11-08 | U461322 | U125763 | 2022-11-07 | 2022-12-30 |  |  | STEVE CANOY | 2022-11-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10 | 1 | 3022.52 | 667.83 | 0 | 690.85 | 1663.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22143436900 |  | 100347035 |  | 6696212K |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | WOODLAWN | 115 WOODLAWN DR 6 | 239 | VER | 2022-11-10 | U128410 | U129939 | 2022-11-08 | 2022-11-08 |  |  | CDESPAIN | 2022-11-08 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 8313.15 | 0 | 705.71 | 0 | 7607.44 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22143441300 |  | 500542786 |  | 6748180L |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | WACO LOOP | 556 WACO LOOP | 151 | WAC | 2022-11-08 | U129722 | U125763 | 2022-11-08 | 2022-12-30 |  |  | M YOUNG | 2022-11-08 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - WEST | 2623 | 22143518300 |  | 100447477 |  | 6684224E |  |  |  | 566 | VO | ABANDON SERVICE LINE | 2621P | US 127 | 1303 US 127 SO STE 109 | 073 | FRA | 2022-11-08 |  | U129939 | 2022-11-08 | 2022-11-08 |  |  | J ENSMINGER | 2022-11-08 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2621 | 22146419400 |  | 500232016 |  | 6716208B |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2600B | WALLER | 366 WALLER AV 213 | 067 | LEX | 2022-11-28 | U127206 | U134723 | 2022-11-28 | 2023-12-29 |  |  | JUSTIN HOBBS | 2022-11-08 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - CENTRAL | 2629 | 22979038800 |  | 100342704 |  | 7240216N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HOWARD | 100 HOWARD AV | 173 | MT | 2022-11-09 | U126603 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | SHAWN DENNIS | 2022-11-08 | 2022-11-08 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.4333 | 1 | 2605.25 | 98.67 | 0 | 22.34 | 2484.24 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979054700 |  | 500676809 |  | 7356216H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NUTMEG | 9 NUTMEG CT | 127 | LOU | 2022-11-09 | U127414 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | ED FOX | 2022-11-08 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.4 | 1 | 2187.3 | 362.73 | 0 | 82.07 | 1742.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 94164101600 |  | 100411676 | 01 | 6696212H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | R1 RUSSELLTOWN | R1 RUSSELLTOWN RD | 239 | VER | 2022-11-08 | U126308 | KAUSTIN | 1994-03-17 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-11-08 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 804.8 | 0 | 0 | 0 | 804.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 06668189100 |  | 100273607 |  | 6680224D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | LOUISVILLE | 1408 LOUISVILLE RD | 073 | FRA | 2023-06-19 | U128816 | RPOLLY | 2006-12-11 | 2022-07-01 | 2023-12-31 |  | OLIVER MAYNARD | 2022-11-09 | 2022-11-08 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 9.6 | 3 | 6277.1 | 598.92 | 64.62 | 35.04 | 5578.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07675236200 |  | 100340003 |  | 6724212E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | RALEIGH | 1633 RALEIGH RD 2 | 067 | LEX | 2022-11-09 | U127206 | SSUTHER | 2007-02-08 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-11-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 3032.97 | 0 | 0 | 0 | 3032.97 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 08721535000 |  | 500138286 | 10 | 6736228C |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | ARLINGTON | 1000 ARLINGTON DR | 017 | PAR | 2022-11-09 | U126603 | PMCNABB | 2008-02-26 | 2022-07-01 | 2022-12-31 |  | SHAWN DENNIS | 2022-11-09 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 6.4 | 1 | 2110.88 | 429.68 | 0 | 97.26 | 1583.94 | 0 | 0 | 0
KY | KY - EAST | 2633 | 11901993000 |  | 100255260 |  | 7352176T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RICHMOND | 79 RICHMOND ST | 115 | VAN | 2022-11-09 | U130172 | U906631 | 2011-04-19 | 2022-07-01 | 2022-12-31 |  | JOHN HOWARD | 2022-11-09 | 2022-09-28 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 14.5667 | 2 | 1057.76 | 1000.43 | 0 | 57.33 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11906402300 |  | 100341099 |  | V-1222/36 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAIN | 700 E MAIN ST | 173 | MT | 2022-11-09 | U126603 | U906631 | 2011-05-12 | 2022-07-01 | 2022-12-31 |  | SHAWN DENNIS | 2022-11-09 | 2022-11-08 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.7333 | 1 | 2648.7 | 249.05 | 0 | 56.38 | 2343.27 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11918566900 |  | 500697706 |  | X-1110-38 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | STACY LANE | 1797 STACY LANE RD | 065 | IRV | 2022-11-09 | U126602 | U907469 | 2011-08-02 | 2022-07-01 | 2022-12-31 |  | DEREK PAYTON | 2022-11-09 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2623 | 11918567000 |  | 100281101 |  | 6696216F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | R1 VERSAILLES | R1 VERSAILLES RD | 239 | VER | 2022-11-09 | U126308 | U907469 | 2011-08-02 | 2022-07-01 | 2022-12-31 |  | J ENSMMINGER | 2022-11-09 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 889 | 0 | 33.9 | 0 | 855.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11920311500 |  | 100461063 |  | W-1202-43 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEVEE | 4700 LEVEE RD | 173 | MT | 2022-11-09 | U126603 | U124449 | 2011-08-16 | 2022-07-01 | 2022-12-31 |  | SHAWN DENNIS | 2022-11-09 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.6 | 1 | 2219.26 | 308.81 | 0 | 69.91 | 1840.54 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12981345800 |  | 100447809 |  | W-1207/28 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEVEE | 8545 LEVEE RD | 173 | MT | 2022-11-09 | U126603 | U125208 | 2012-07-23 | 2022-07-01 | 2022-12-31 |  | SHAWN DENNIS | 2022-11-09 | 2022-11-08 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.2 | 1 | 2405.28 | 214.88 | 0 | 48.64 | 2141.76 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12993215900 |  | 500287270 |  | W-1207/28 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEVEE | 8565 LEVEE RD | 173 | MT | 2022-11-09 | U126603 | U125208 | 2012-10-12 | 2022-07-01 | 2022-12-31 |  | SHAWN DENNIS | 2022-11-09 | 2022-11-08 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.1333 | 1 | 2059.69 | 142.32 | 0 | 32.21 | 1885.16 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 13152886700 |  | 500618609 | 28 | 6764172G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | OLIVE | 42 OLIVE ST | 065 | IRV | 2022-11-09 | U126602 | TJROSEN | 2013-08-02 | 2022-07-01 | 2022-12-31 |  | DEREK PAYTON | 2022-11-09 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 2863.15 | 480.88 | 0 | 28.12 | 2354.15 | 0 | 0 | 0
KY | KY - WEST | 2621 | 14191696700 |  | 100340009 |  | 6724212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RALEIGH | 1633 RALEIGH RD 6 | 067 | LEX | 2022-11-09 | U127206 | U125208 | 2014-01-08 | 2017-06-26 |  |  | JUSTIN HOBBS | 2022-11-09 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 14191697600 |  | 100340007 |  | 6724212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RALEIGH | 1633 RALEIGH RD 4 | 067 | LEX | 2022-11-09 | U127206 | U125208 | 2014-01-08 | 2017-06-26 |  |  | JUSTIN HOBBS | 2022-11-09 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 14191699100 |  | 100340015 |  | 6724212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RALEIGH | 1633 RALEIGH RD 10 | 067 | LEX | 2022-11-09 | U127206 | U125208 | 2014-01-08 | 2017-06-26 |  |  | JUSTIN HOBBS | 2022-11-09 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 641.05 | 0 | 0 | 0 | 641.05 | 0 | 0 | 0
KY | KY - WEST | 2621 | 14191700300 |  | 100340013 |  | 6724212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RALEIGH | 1633 RALEIGH RD 8 | 067 | LEX | 2022-11-09 | U127206 | U125208 | 2014-01-08 | 2017-06-26 |  |  | JUSTIN HOBBS | 2022-11-09 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - CENTRAL | 2629 | 17557308400 |  | 100347394 |  | 6744208L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 7TH | 33 7TH ST | 049 | WIN | 2022-11-09 | U129731 | DMCCULL | 2017-10-25 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-11-09 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 2247.66 | 499.72 | 0 | 119.38 | 1628.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883075800 |  | 500721158 |  | 7356216D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | POWHATAN | 206 S POWHATAN ST | 127 | LOU | 2022-11-09 | U126286 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | TYLER ALLISON | 2022-11-09 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 2385 | 0 | 0 | 0 | 2385 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883109200 |  | 500549052 |  | 6752176B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BYBEE LOOP | 201 BYBEE LOOP | 151 | WAC | 2022-11-09 | U126532 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | LESLIE SHARON | 2022-11-09 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10 | 1 | 5494.02 | 633.71 | 0 | 688.85 | 4171.46 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883111600 |  | 100253487 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MARY | 43 MARY LN | 159 | INE | 2022-11-09 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-11-09 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.5833 | 1 | 3328.84 | 392.68 | 0 | 85.73 | 2850.43 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883115100 |  | 500491995 |  | 7344264C |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WURTLAND | 1307 WURTLAND AV | 089 | WUR | 2022-11-09 | MCOLLET | U120245 | 2021-01-30 | 2022-11-07 | 2022-12-31 |  | MCOLLET | 2022-11-09 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.36667 | 1 | 27.24 | 25.61 | 0 | 1.63 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883165600 |  | 500245728 |  | 6744208N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | QUAIL RIDGE | 111 QUAIL RIDGE RD | 049 | WIN | 2022-11-09 | U129731 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-11-09 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883254600 |  | 100426501 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2633S | WOLF PEN CREEK | 13 WOLF PEN CREEK RD | 119 | LIT | 2022-11-09 | U123965 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | MBLANKE/CJH J HIERONIMUS | 2022-11-09 |  |  | B | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 |  | 1 | 1217.26 | 0 | 0 | 0 | 1217.26 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883265400 |  | 100252208 |  | 7368192T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SPRUCE PINE | 112 SPRUCE PINE RD | 159 | INE | 2022-11-09 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-11-09 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 4.4167 | 1 | 3230.9 | 312.28 | 0 | 68.19 | 2850.43 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883267700 |  | 100342273 |  | 7240216J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | DARE | 524 DARE DR | 173 | MT | 2022-11-09 | U129722 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-11-09 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.5 | 1 | 5380.66 | 526.93 | 0 | 126.61 | 4727.12 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883283300 |  | 500778302 |  | 7356216H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NUTMEG | 16 NUTMEG CT | 127 | LOU | 2022-11-09 | U127414 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | ED FOX | 2022-11-09 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.3 | 1 | 1793.27 | 353.33 | 0 | 79.94 | 1360 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883309600 |  | 100261770 |  | 7340136T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | HWY 7 SOUTH | 6064 HWY 7 SOUTH | 119 | TOP | 2022-11-09 | U123965 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | MBLANKE/CJH J HIERONIMUS | 2022-11-09 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1 | 1398.34 | 0 | 0 | 0 | 1398.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959038200 |  | 100315379 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | UNIVERSITY | 136 UNIVERSITY AV | 067 | LEX | 2022-11-09 | U129673 | U134723 | 2021-12-10 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-11-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10 | 1 | 2785.22 | 633.32 | 0 | 98.45 | 2053.45 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959038300 |  | 100315378 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | UNIVERSITY | 138 UNIVERSITY AV | 067 | LEX | 2022-11-09 | U461322 | U134723 | 2021-12-10 | 2022-11-08 |  |  | STEVE CANOY | 2022-11-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.2 | 1 | 3113.6 | 681.22 | 0 | 704.66 | 1727.72 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22026216700 |  |  |  | 7324132I | 2290467 | U122858 |  | 559 | EX | EMER - INSTALL 456'-4" CS/PMIP | 2600B | PRATT HOLLOW | PRATT HOLLOW | 119 | HIN | 2022-12-19 | U128132 | U122858 | 2022-08-05 | 2022-12-29 | 2022-12-31 | 2022-11-08 | MBLANKE/CJH CASEY PACK | 2022-11-09 |  |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00559 | 3200559 |  |  | WP2167 | AMRCB |  | 100 | 055932220262167 |  | 533 | 85192.39 | 13099.93 | 0 | 9669.35 | 57860 | 0 | 158.39 | 4404.72 | 533
KY | KY - EAST | 2633 | 22026216801 |  |  |  | 7324132I | 2290467 | U132280 |  | 560 | EX | EMER-RETIRE 130'-4" CS/BS/PIP | 2600B | PRATT HOLLOW | PRATT HOLLOW | 119 | HIN | 2022-12-15 | U128132 | U132280 | 2022-11-14 | 2022-12-30 | 2022-12-31 | 2022-11-08 | MBLANKE/CJH CASEY PACK | 2022-11-09 | 2022-11-16 |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00560 | 3200560 |  |  | WP2168 |  |  | 100 | 056032220262168 | 5.0333 | 0 | 439.01 | 361.52 | 0 | 77.49 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129022800 |  | 100284768 |  | 6764176N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DUG HILL | 5 DUG HILL RD | 065 | IRV | 2022-12-14 | U126602 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DEREK PAYTON | 2022-11-09 | 2022-11-07 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 11816.01 | 480.88 | 0 | 28.12 | 11307.01 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129040100 |  | 100468054 |  | 7356216H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 3RD | 248 3RD ST LOT 8 | 127 | LOU | 2022-11-10 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-11-09 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 13.5 | 1 | 2352.46 | 937.6 | 0 | 54.86 | 1360 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129040900 |  | 501163924 |  | 7356216H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ROSE | 108 ROSE ST | 127 | LOU | 2022-11-10 | U127414 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ED FOX | 2022-11-09 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.8 | 1 | 2012.06 | 323.79 | 0 | 73.27 | 1615 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129041000 |  | 100249484 |  | 7356216H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ROUTE 32 | 38 ROUTE 32 | 127 | LOU | 2022-11-10 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-11-09 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 2380 | 0 | 0 | 0 | 2380 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129056300 |  | 100346895 |  | 6696212K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SAINT CLAIR | 113 SAINT CLAIR ST | 239 | VER | 2022-11-17 | U126308 | U130722 | 2022-09-05 | 2022-12-30 |  |  | J ENSMINGER | 2022-11-09 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 10.5 | 1 | 1692.86 | 747.26 | 46.79 | 43.71 | 855.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22136895400 |  | 100275454 |  | 6684228F |  |  |  | 566 | EX | ABANDON SL - NON COMPLIANT | 2621P | ROSE | 610 ROSE ST | 073 | FRA | 2022-11-11 | U930915 | U127297 | 2022-10-05 | 2022-11-01 | 2022-11-01 |  | BSEXTON | 2022-11-09 | 2022-11-09 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 10.9333 | 2 | 644.82 | 609.19 | 0 | 35.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22137265300 |  | 100420408 |  | 6720204F | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | KEENELAND | 1248 KEENELAND CT | 067 | LEX | 2022-11-09 | HMCKUNE | AOC SYST | 2022-10-06 | 2022-11-08 | 2023-12-31 |  | HMCKUNE | 2022-11-09 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 1.0667 | 1 | 163.34 | 68.06 | 0 | 3.98 | 91.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22142781800 |  | 500335061 |  | 6764176N |  |  |  | 566 | EX | ABAND SL/LGCY | 2600B | DUG HILL | 35 DUG HILL RD TR | 065 | IRV | 2022-11-30 | U126602 | U125763 | 2022-11-03 | 2022-12-30 |  |  | DEREK PAYTON | 2022-11-09 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - WEST | 2621 | 22142989200 |  | 100445263 |  | 6720208N |  |  |  | 565 | EX | SERVICE LINE - REPLACE 11/10 | 2621P | SHADYBROOK | 1976 SHADYBROOK LN | 067 | LEX | 2022-11-10 | U930915 | U125208 | 2022-11-04 | 2022-11-10 | 2022-11-25 |  | WISHII | 2022-11-09 | 2022-11-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25.5667 | 3 | 1129.64 | 1275.14 | 22 | -273.1 | 105.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22143266000 |  | 100342530 |  | 7240216N |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | HOLT | 205 HOLT AV | 173 | MT | 2022-11-09 | U129722 | U125763 | 2022-11-07 | 2022-12-30 |  |  | M YOUNG | 2022-11-09 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1477.95 | 0 | 0 | 0 | 1477.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22143651100 |  | 100308870 |  | 6716208A |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | LYNN | 760 LYNN DR | 067 | LEX | 2022-11-09 | U127206 | U125763 | 2022-11-09 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-11-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 2214.38 | 477.86 | 0 | 27.95 | 1708.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22143659700 |  | 100312777 |  | 6716208E |  |  |  | 565 | EX | SERVICE LINE - REPLACE D310257 | 2621P | STRATFORD | 541 STRATFORD DR | 067 | LEX | 2022-11-10 | U930915 | U129939 | 2022-11-09 | 2022-11-09 | 2022-11-09 |  | LSTANFI | 2022-11-09 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 27.2333 | 3 | 6253.71 | 1585.1 | 199.22 | 92.75 | 4376.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22143682200 |  | 100320830 |  | 6716212L | 2176779 |  |  | 565 | EX | RPLC SL/21026993800 | 2600B | GROSVENOR | 302 GROSVENOR AV | 067 | LEX | 2022-11-09 | U126309 | U125763 | 2022-11-09 | 2022-12-30 |  |  | JAMIE LYNN | 2022-11-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1795.5 | 0 | 0 | 0 | 1795.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22146979700 |  | 100448312 |  | 6764176N |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | DUG HILL | 5 DUG HILL RD APT2 | 065 | IRV | 2022-12-14 | U126602 | U125763 | 2022-12-01 | 2022-12-30 |  |  | DEREK PAYTON | 2022-11-09 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 0
KY | KY - WEST | 2621 | 04574684500 |  | 500123544 |  | 16720204F | 1315787 |  |  | 566 | EX | ABANDON SL - PEND OS 12/01/22 | 2621P | SWOONALONG | 1309 SWOONALONG CT | 067 | LEX | 2022-11-10 | U127206 | SSUTHER | 2004-05-11 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2602.13 | 0 | 0 | 0 | 2602.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 08727650300 |  | 100339597 |  | 16724212A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MARIETTA | 1863< MARIETTA DR | 067 | LEX | 2022-11-10 | U127206 | RPOLLY | 2008-04-16 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 3695.17 | 0 | 0 | 0 | 3695.17 | 0 | 0 | 0
KY | KY - WEST | 2623 | 09806943900 |  | 100425428 |  | V-909/15 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEMONS MILL | 204 LEMONS MILL RD RR | 209 | GEO | 2022-11-10 | U126308 | DMCCULL | 2009-10-06 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8 | 1 | 3550.5 | 569.33 | 256.53 | 554.74 | 2169.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 11900949800 |  | 100273567 |  | 6680224G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | LOUISVILLE | 1620 LOUISVILLE RD | 073 | FRA | 2023-06-21 | U128816 | U906631 | 2011-04-13 | 2022-07-01 | 2023-12-31 |  | OLIVER MAYNARD | 2022-11-10 | 2022-11-09 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 11.4833 | 5 | 2967.97 | 718.79 | 64.62 | 41.84 | 2142.72 | 0 | 0 | 0
KY | KY - EAST | 2633 | 11931677100 |  | 100240833 |  | 7324132F | 2290467 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | MAIN | MAIN ST | 119 | HIN | 2022-11-10 | U123965 | U125208 | 2011-11-03 | 2022-07-01 | 2022-12-31 |  | MBLANKE/CJH J HIERONIMUS | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1 | 4163.08 | 0 | 0 | 0 | 4163.08 | 0 | 0 | 0
KY | KY - WEST | 2623 | 12975340500 |  | 100283121 | 19 | V-909/8 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEMONS MILL | 209 LEMONS MILL RD | 209 | GEO | 2022-11-10 | U126308 | WWRICHA | 2012-06-06 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 429.5 | 0 | 0 | 0 | 429.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12984338900 |  | 100412754 |  | 6736228L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | CLINTONVILLE | 501 CLINTONVILLE RD L19 | 017 | PAR | 2022-11-15 | U123111 | U908784 | 2012-08-14 | 2022-07-01 | 2022-12-31 |  | LYN STAFFORD | 2022-11-10 | 2022-11-10 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 14 | 2 | 4497.49 | 863.39 | 0 | 571.93 | 3062.17 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 16415220800 |  | 100359364 |  | 16740232M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CYPRESS | 1404 CYPRESS ST | 017 | PAR | 2022-11-10 | U129731 | SPENDLE | 2016-06-07 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1020.05 | 0 | 0 | 0 | 1020.05 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 16441615500 |  | 100360321 | 54 | 6736228H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BRENT | 1919 BRENT ST RT | 017 | PAR | 2022-11-10 | U129731 | PMCNABB | 2016-09-14 | 2022-12-30 | 2022-12-31 |  | F.GOINS | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 780.44 | 0 | 0 | 0 | 780.44 | 0 | 0 | 0
KY | KY - WEST | 2623 | 17569039000 |  | 500442979 |  | 6712228F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | HAWTHORNE | 103 HAWTHORNE DR LT109C | 209 | GEO | 2022-11-10 | U126308 | U125765 | 2017-12-20 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-11-10 | 2020-09-09 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 1.0667 | 2 | 179.79 | 60.06 | 0 | 119.73 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 20800039200 |  | 500814247 | 10 | 6732248D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | KY HWY 3016 | 20 KY HWY 3016 | 097 | CYN | 2022-11-10 | U129722 | NRICHIE | 2020-04-10 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 682.41 | 0 | 0 | 0 | 682.41 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883069500 |  | 100426374 |  | 7360184T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MCGINNIS | 185 MCGINNIS BR | 159 | DAV | 2022-11-10 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.6 | 1 | 2590.35 | 394.79 | 0 | 86.19 | 2109.37 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883086200 |  | 500578146 |  | 6736252I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | US HIGHWAY 27 | 846 US HIGHWAY 27 N REAR | 097 | CYN | 2022-11-10 | U129722 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1628.84 | 0 | 0 | 0 | 1628.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883263400 |  | 100462940 |  | 6736228H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CLINTONVILLE | 220 CLINTONVILLE RD | 017 | PAR | 2022-11-10 | U129731 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 958.44 | 0 | 0 | 0 | 958.44 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883309100 |  | 100428688 |  | 6740232M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAIN | 1112 MAIN ST DN | 017 | PAR | 2022-11-11 | U126603 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | SHAWN DENNIS | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 1986 | 537.1 | 0 | 121.56 | 1327.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959035400 |  | 100315390 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | LIMESTONE | 1229 S LIMESTONE ST | 067 | LEX | 2022-11-10 | U128336 | U134723 | 2021-12-10 | 2022-12-30 |  |  | JOSHUA COX | 2022-11-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.7667 | 1 | 4149.19 | 671.49 | 0 | 39.28 | 3438.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959044200 |  | 100465664 |  | 6716208C | 2176780 |  |  | 565 | EX | REPLACE SL W/21-0269940-00 | 2600B | UNIVERSITY | 134 UNIVERSITY AV 1F-A | 067 | LEX | 2022-11-10 | U461322 | U134723 | 2021-12-10 | 2022-12-30 |  |  | STEVE CANOY | 2022-11-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.5 | 1 | 2985.59 | 701.23 | 0 | 725.39 | 1558.97 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960236000 |  | 100320974 |  | 6720212M | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | HIGH | 524 E HIGH ST 1F | 067 | LEX | 2022-11-17 | U461375 | U134723 | 2021-12-17 | 2022-12-30 |  |  | LARRY BROWN | 2022-11-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 6924.47 | 0 | 0 | 0 | 6924.47 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129002300 |  | 100358751 |  | 6740232M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 7TH | 319 W 7TH ST | 017 | PAR | 2022-11-10 | U126602 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DEREK PAYTON | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - CENTRAL | 2629 | 22129002400 |  | 100359068 |  | 6740232M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 7TH | 200 W 7TH ST 2 | 017 | PAR | 2022-11-10 | U126602 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DEREK PAYTON | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - CENTRAL | 2629 | 22129003600 |  | 100343660 |  | 7240212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LOCUST | 256 W LOCUST ST | 173 | MT | 2022-11-10 | U126602 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DEREK PAYTON | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - CENTRAL | 2632 | 22129025500 |  | 100354806 |  | 7260280N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | MAIN | 214 MAIN ST | 161 | MAY | 2022-11-11 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 14 | 2 | 2477.82 | 949.58 | 0 | 168.24 | 1360 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129049400 |  | 501194183 |  | 6712204B | 1637431 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KINGS GLEN | 3751 KINGS GLEN PR | 067 | LEX | 2022-11-10 | U127206 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 731.68 | 0 | 0 | 0 | 731.68 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129055900 |  | 100283710 |  | 6712228B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LEXINGTON | 304 LEXINGTON AV | 209 | GEO | 2022-11-17 | U126308 | U130722 | 2022-09-05 | 2022-12-30 |  |  | J ENSMINGER | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 12 | 1 | 3120.4 | 854.02 | 15.82 | 832.1 | 1418.46 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129061500 |  | 100354503 |  | 7260280M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | LIBERTY | 111 LIBERTY ST | 161 | MAY | 2022-11-11 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 10 | 1 | 2860.16 | 694.52 | 0 | 40.64 | 2125 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129084100 |  | 100300606 |  | 6716212F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FERGUSON | 316 FERGUSON ST | 067 | LEX | 2022-11-10 | U130761 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KKINDER | 2022-11-10 | 2022-10-18 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 30.9167 | 12 | 1971.9 | 1748.49 | 34.04 | 189.37 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22131235200 |  | 100263467 |  | 7352256B | 2176770 |  |  | 566 | EX | ABND SL W/21026993400 | 2600B | WESTVIEW | 621 WESTVIEW DR | 019 | ASH | 2022-11-10 | U124015 | U125768 | 2022-09-14 | 2049-12-31 |  |  | ORA SLONE | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1
KY | KY - WEST | 2623 | 22143878100 |  | 100281781 |  | 6712232N |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | GANO | 320 GANO AV UPR | 209 | GEO | 2022-11-16 | U128410 | U129939 | 2022-11-10 | 2022-11-10 |  |  | CDESPAIN | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2623 | 22143878400 |  | 100281778 |  | 6712232N |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | GANO | 320 GANO AV DNL | 209 | GEO | 2022-11-16 | U128410 | U129939 | 2022-11-10 | 2022-11-10 |  |  | CDESPAIN | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2623 | 22143878600 |  | 100281783 |  | 6712232N |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | GANO | 320 GANO AV DNR | 209 | GEO | 2022-11-10 | U128410 | U129939 | 2022-11-10 | 2022-11-10 |  |  | CDESPAIN | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2623 | 22143878800 |  | 100457117 |  | 6712232N |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | GANO | 320 GANO AV UPL | 209 | GEO | 2022-11-10 | U128410 | U129939 | 2022-11-10 | 2022-11-10 |  |  | CDESPAIN | 2022-11-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 1 | 5032.58 | 526.12 | 388.66 | 30.77 | 4087.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22143906400 |  | 100449407 |  | 6716212L | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | ROSE | 266 ROSE ST 1FRR | 067 | LEX | 2022-12-13 | U126309 | U131066 | 2022-11-10 | 2022-12-30 |  |  | JAMIE LYNN | 2022-11-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2627.99 | 0 | 0 | 0 | 2627.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22143936900 |  | 500353114 |  | 6720212M |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | WALTON | 165< WALTON AV | 067 | LEX | 2022-11-10 | U127206 | U125763 | 2022-11-10 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 22143937100 |  | 500347241 |  | 6720212M |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | WALTON | 165 WALTON AV | 067 | LEX | 2022-11-14 | U127206 | U125763 | 2022-11-10 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 2384.51 | 477.86 | 0 | 27.95 | 1878.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22143945600 |  | 100359809 |  | 6740232M |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | MAIN | 1112< MAIN ST | 017 | PAR | 2022-11-11 | U126603 | U125763 | 2022-11-10 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1402.64 | 0 | 0 | 0 | 1402.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22143948000 |  | 100311942 |  | 6716208I |  |  |  | 565 | EX | SERVICE LINE - REPLACE D310258 | 2621P | LAMONT | 482 LAMONT DR | 067 | LEX | 2022-11-11 | U125208 | U129939 | 2022-11-10 | 2022-11-10 | 2022-11-10 |  | KKINDER | 2022-11-10 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.5833 | 3 | 1640.71 | 882.91 | 661.05 | 51.65 | 45.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979028000 |  | 100271508 |  | 6736252M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MILLER | 108 S MILLER ST | 097 | CYN | 2022-11-10 | U129722 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | M YOUNG | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 2933.92 | 495.92 | 0 | 29 | 2409 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979038400 |  | 100341384 |  | 7240216L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 2ND | 900 2ND ST | 173 | MT | 2022-11-10 | U126602 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | DEREK PAYTON | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 629.83 | 0 | 0 | 0 | 629.83 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979039400 |  | 100343492 |  | 7240212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SYCAMORE | 16 S SYCAMORE ST RS | 173 | MT | 2022-11-10 | U126602 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | DEREK PAYTON | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - EAST | 2633 | 22979045200 |  | 100423436 |  | 7376184T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BUCK BRANCH | 205 BUCK BRANCH | 159 | LOV | 2022-11-15 | U126604 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | WILL FULKS | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.9167 | 1 | 992.74 | 206.58 | 0 | 45.1 | 741.06 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22979046100 |  | 100428121 |  | 7364200T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BLANKENSHIP HO | 778 BLANKENSHIP HO RD | 159 | LOU | 2022-11-10 | U126604 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | WILL FULKS | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1 | 2109.37 | 0 | 0 | 0 | 2109.37 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979048800 |  | 100461694 |  | 6764176C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WHITE OAK | 1295 WHITE OAK RD APT 7 | 065 | IRV | 2022-11-10 | U126602 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | DEREK PAYTON | 2022-11-10 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - CENTRAL | 2629 | 21883240100 |  | 500827693 |  | 6740232M | 0254151 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAIN | 1303 MAIN ST REST | 017 | PAR | 2022-11-11 | U126603 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | SHAWN DENNIS | 2022-11-11 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026212100 |  |  |  | 7244216F | 2289270 | U461383 |  | 577 | EX | INSTALL CHAIN LINK FENCE | 2629M | EWINGTON | EWINGTON RD | 173 | MT | 2022-12-21 | U125936 | U461383 | 2022-07-19 | 2023-12-28 | 2023-12-31 | 2022-11-11 | JMULLINS | 2022-11-11 | 2022-11-08 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00577 | 3200577 |  |  | WP2121 |  |  | 100 | 057732220262121 | 67.5833 | 6 | 9226.54 | 5794.64 | 0 | 1806.3 | 1179.92 | 0 | 3.07 | 442.61
KY | KY - EAST | 2631 | 22026231600 |  |  |  | 7348264K | 2292887 | U132280 |  | 557 | EX | EMER - INSTALL 2'-4" PMMP | 2621P | BRENDA SUE | BRENDA SUE | 089 | FLA | 2022-12-16 | U128132 | U132280 | 2022-10-17 | 2023-06-29 |  | 2022-10-18 | MCOLLET | 2022-11-11 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP2316 |  |  | 100 | 055732220262316 | 2.55 | 2 | 196.47 | 179.98 | 0 | 11.5 | 0 | 0 | 0 | 4.99 | 2
KY | KY - EAST | 2631 | 22026231700 |  |  |  | 7348264K | 2292887 | U132280 |  | 558 | EX | EMER - RETIRE 2'-4" PMMP | 2621P | BRENDA SUE | BRENDA SUE | 089 | FLA | 2022-11-16 | U128132 | U132280 | 2022-10-17 | 2023-06-30 |  | 2022-10-18 | MCOLLET | 2022-11-11 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP2317 |  |  | 100 | 055832220262317 | 0.31667 | 0 | 24.23 | 22.77 | 0 | 1.46 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026236000 |  |  |  | 6688228D | 2070683 | U461383 |  | 575 | EX | ADDITIONAL EASEMENT/LAND | 2623M | GEORGETOWN | 3200 GEORGETOWN RD | 073 | FRA | 2022-11-11 | U128132 | U461383 | 2022-11-11 | 2022-12-30 | 2022-12-31 | 2022-11-11 | LAND SERVICES | 2022-11-11 |  |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00575 | 3200575 |  |  | WP2360 |  |  | 100 | 057532220262360 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22102922200 |  | 100304748 |  | 6712212P |  |  |  | 565 | EX | REPLACE SERV - D305549 D309137 | 2621P | BLUE LICKS | 1754 BLUE LICKS RD | 067 | LEX | 2022-11-11 | SSHIMFE | U125208 | 2022-05-23 | 2022-11-11 | 2022-11-29 |  | SSHIMFE | 2022-11-11 | 2022-07-29 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 31.3667 | 8 | 2607.74 | 1899.2 | 505.11 | 111.03 | 92.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 08727635200 |  | 500032355 |  | 16720204C |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | PIMLICO | 3130 PIMLICO PY STE 101 | 067 | LEX | 2022-11-14 | U127206 | RPOLLY | 2008-04-16 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-11-14 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 886.26 | 0 | 0 | 0 | 886.26 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11898684700 |  | 100339635 |  | 16724212A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MARIETTA | 1838 MARIETTA DR 6 | 067 | LEX | 2022-11-14 | U125559 | U123933 | 2011-03-30 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-11-14 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 11900029800 |  | 100339630 |  | 16724212A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MARIETTA | 1838 MARIETTA DR 2 | 067 | LEX | 2022-11-14 | U125559 | U123933 | 2011-04-06 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-11-14 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 443.13 | 0 | 0 | 0 | 443.13 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883062100 |  | 100250568 |  | 7376188M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LOCUST | 48 LOCUST CT | 159 | LOV | 2022-11-14 | U123965 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | MBLANKE | 2022-11-14 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.5667 | 1 | 1543.63 | 114.26 | 0 | 24.49 | 1404.88 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883228900 |  | 100352700 |  | 6744204B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MCCLURE | 106 MCCLURE RD | 049 | WIN | 2022-11-14 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-11-14 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.5167 | 1 | 4756.25 | 387.75 | 0 | 84.67 | 4283.83 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883330300 |  | 500230282 |  | 6700224L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | 1ST | 341 1ST ST | 239 | MID | 2022-11-14 | U126308 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-11-14 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - EAST | 2633 | 21884270000 |  | 100247971 |  | 7364188B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CASSADY | CASSADY AV | 159 | INE | 2022-11-14 | U123965 | U128293 | 2021-02-04 | 2022-07-01 | 2022-12-31 |  | MBLANKE | 2022-11-14 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.6833 | 1 | 1720.59 | 265.36 | 0 | 56.89 | 1398.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960234500 |  | 100327193 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | HIGH | 419 E HIGH ST 1F | 067 | LEX | 2022-11-17 | U461375 | U134723 | 2021-12-17 | 2022-12-30 |  |  | LARRY BROWN | 2022-11-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3922.72 | 0 | 0 | 0 | 3922.72 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026221000 |  | 501077663 |  | 6676224P | 2290985 | U134275 |  | 555 | EX | INSTALL 160'-4"PMMP | 2600B | EVERGREEN | 515 EVERGREEN RD | 073 | FRA | 2022-12-19 | U128132 | U134275 | 2022-08-31 | 2022-11-10 | 2022-11-15 | 2022-11-14 | R.HUMPHREYS | 2022-11-14 | 2022-11-02 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2210 |  |  | 100 | 055532220262210 | 100.5 | 2301 | 36375.08 | 6248.51 | 3104.55 | 2507.31 | 23278.51 | 0 | 74.36 | 1161.84 | 177
KY | KY - CENTRAL | 2632 | 22129025100 |  | 100355215 |  | 7260280N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | ELIZABETH | 921 ELIZABETH ST | 161 | MAY | 2022-11-14 | U125566 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DESKAGG | 2022-11-14 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 6.2167 | 1 | 1898.05 | 411.16 | 0 | 94.39 | 1392.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129060000 |  | 100354638 |  | 7260280N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | 2ND | 927 E 2ND ST | 161 | MAY | 2022-11-15 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-11-14 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1 | 1360 | 0 | 0 | 0 | 1360 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129060100 |  | 100354144 |  | 7256280P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | 4TH | 302 E 4TH ST | 161 | MAY | 2022-11-14 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-11-14 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1 | 1360 | 0 | 0 | 0 | 1360 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129060200 |  | 100457984 |  | 7256280P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | 4TH | 352 E 4TH ST | 161 | MAY | 2022-11-15 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-11-14 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 10 | 1 | 1835.16 | 694.52 | 0 | 40.64 | 1100 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129060400 |  | 100354466 |  | 7256280P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | 5TH | 134 E 5TH ST | 161 | MAY | 2022-11-15 | U461478 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DAVID STAGGS | 2022-11-14 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 4 | 1 | 1616.02 | 241.87 | 0 | 14.15 | 1360 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129060500 |  | 100354477 |  | 7256280P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | 5TH | 214 E 5TH ST | 161 | MAY | 2022-11-14 | U461478 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DAVID STAGGS | 2022-11-14 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 1.9667 | 1 | 1486.08 | 119.1 | 0 | 6.98 | 1360 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129083100 |  | 100333560 |  | 6720212I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 3RD | 132 E 3RD ST 101 | 067 | LEX | 2022-11-15 | U127206 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-11-14 | 2022-11-10 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.1667 | 1 | 1109.03 | 210.47 | 0 | 12.3 | 886.26 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22138861600 |  | 100273023 |  | 6684224A |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTRQD | 2621P | LOUISVILLE | 931 LOUISVILLE RD | 073 | FRA | 2022-11-14 | DCOLLIN | U132002 | 2022-10-13 | 2022-10-26 | 2022-11-11 |  | DCOLLIN | 2022-11-14 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 18.5833 | 2 | 968.55 | 1302.7 | 0 | -334.15 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22144235800 |  | 100320823 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | ROSE | 282 ROSE ST 1 | 067 | LEX | 2022-11-16 | U126309 | U125768 | 2022-11-14 | 2049-12-31 |  |  | JAMIE LYNN | 2022-11-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2991.14 | 0 | 0 | 0 | 2991.14 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22144285000 |  | 100273050 |  | 6684224A |  |  |  | 566 | EX | ABANDN SL - I/I/LGCY | 2600B | LOUISVILLE | 1121 LOUISVILLE RD | 073 | FRA | 2022-11-14 | U128816 | U125763 | 2022-11-14 | 2022-12-30 |  |  | OLIVER MAYNARD | 2022-11-14 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1607.04 | 0 | 0 | 0 | 1607.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22144295000 |  | 100338456 |  | 6720212E |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | 7TH | 151 E 7TH ST | 067 | LEX | 2022-11-14 | U127206 | U125763 | 2022-11-14 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-11-14 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1853.07 | 0 | 0 | 0 | 1853.07 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22144652200 |  | 100354465 |  | 7256280P |  |  |  | 566 | EX | ABANDON SL | 2600B | 5TH | 134< E 5TH ST | 161 | MAY | 2022-11-15 | U461478 | U125765 | 2022-11-15 | 2022-12-30 |  |  | DAVID STAGGS | 2022-11-14 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1
KY | KY - WEST | 2621 | 22965932200 |  | 100416164 |  | 6720212H |  |  |  | 566 | EX | ABANDON SL- I/I/LGCY | 2621P | KILKENNY | 1591 KILKENNY DR | 067 | LEX | 2022-11-14 | U127206 | U134723 | 2022-01-13 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-11-14 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 2116.5 | 477.86 | 0 | 27.95 | 1610.69 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22979050400 |  | 500085876 |  | 6692224E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SHADY | 1015 SHADY LN | 239 | MID | 2022-11-14 | U126308 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | J ENSMINGER | 2022-11-14 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 12 | 1 | 2650.53 | 854.02 | 109.31 | 832.1 | 855.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 02504668400 |  | 500173449 |  | 6700212M | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | HUNTERTOWN | 1000 HUNTERTOWN RD FG68 | 239 | VER | 2022-11-15 | U126308 | DMCCULL | 2002-04-26 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-11-15 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - CENTRAL | 2629 | 07677004200 |  | 100404624 |  | X-1206-10 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | R5 OLD RICHMON | R5 OLD RICHMON RD | 065 | IRV | 2022-11-15 | DENNING | SKSMITH | 2007-02-26 | 2022-11-15 |  |  | DENNING | 2022-11-15 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10.45 | 3 | 794.67 | 750.73 | 0 | 43.94 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 07689049600 |  | 100358579 |  | 16740232I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | 2ND | 505 2ND ST UP | 017 | PAR | 2022-11-15 | U126603 | U903504 | 2007-05-31 | 2020-12-31 |  |  | SHAWN DENNIS | 2022-11-15 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.8833 | 1 | 1173.24 | 328.98 | 0 | 74.46 | 769.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22138255600 |  | 100286315 |  | X120640 | 1855957 |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | MAIN | 826 MAIN ST 2F | 065 | RAV | 2022-11-15 | U129722 | U125763 | 2022-10-11 | 2022-12-30 |  |  | M YOUNG | 2022-11-15 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - WEST | 2621 | 22144231000 |  | 100288495 |  | 6720212D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D304057 | 2621P | HARROGATE | 1719 HARROGATE RD | 067 | LEX | 2022-11-15 | U930915 | U125208 | 2022-11-14 | 2022-11-15 | 2022-12-03 |  | LSTANFI | 2022-11-15 | 2022-11-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 22 | 3 | 1529.98 | 1266.77 | 270.73 | -55.92 | 48.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22144254200 |  | 100312749 |  | 6716208E | 1313369 |  |  | 565 | EX | REPLACE SL | 2621P | SHERIDAN | 554 SHERIDAN DR | 067 | LEX | 2022-11-15 | U930915 | U132823 | 2022-11-14 | 2022-11-14 |  |  | RJCRAWF | 2022-11-15 | 2022-11-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 59.25 | 6 | 8941.44 | 3903.17 | 423.93 | 228.29 | 4386.05 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22144299100 |  | 100421639 |  | 6736248A |  |  |  | 565 | EX | SERVICE LINE - REPLACE D304761 | 2621P | OLD LAIR | 107 OLD LAIR RD | 097 | CYN | 2022-11-22 | U125208 | U132823 | 2022-11-14 | 2022-11-14 | 2022-11-14 |  | NRICHIE | 2022-11-15 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 51.6167 | 6 | 6733.18 | 3905.49 | 871.79 | 228.5 | 1727.4 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22144468400 |  | 100270592 |  | 6736248A |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | OLD LAIR | 109 OLD LAIR RD | 097 | CYN | 2022-11-15 | NRICHIE | U124447 | 2022-11-15 | 2022-11-15 |  |  | NRICHIE | 2022-11-15 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 7.1 | 3 | 1659.69 | 490.63 | 1110.62 | 28.74 | 29.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22144601400 |  | 100412527 |  | 6724208E |  |  |  | 565 | EX | GRADE 1 REPLACE SERVICE | 2621P | HEDGEWOOD | 428 HEDGEWOOD DR | 067 | LEX | 2022-11-16 | U930915 | U129939 | 2022-11-15 | 2022-11-15 |  |  | KKINDER | 2022-11-15 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.65 | 3 | 959.99 | 782.7 | 34.67 | 45.82 | 96.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979038900 |  | 100342933 |  | 7240212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SYCAMORE | 17 N SYCAMORE ST 2FL | 173 | MT | 2022-11-15 | U124003 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | BPULLIAM/MILLER | 2022-11-15 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - CENTRAL | 2629 | 22979039000 |  | 100342934 |  | 7240212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SYCAMORE | 17 N SYCAMORE ST 1FL | 173 | MT | 2022-11-15 | U124003 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | BPULLIAM/MILLER | 2022-11-15 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - CENTRAL | 2629 | 22979039100 |  | 100342936 |  | 7240212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SYCAMORE | 17 N SYCAMORE ST 1FR | 173 | MT | 2022-11-15 | U124003 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | BPULLIAM/MILLER | 2022-11-15 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - WEST | 2623 | 01475363800 |  | 100281642 |  | V90448 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAPLE | 543 MAPLE ST | 209 | GEO | 2022-11-16 | U126308 | DMCCULL | 2001-07-03 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-11-16 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0 | 1 | 2289.49 | 0 | 118.67 | 0 | 2170.82 | 0 | 0 | 0
KY | KY - WEST | 2623 | 03537796100 |  | 500354414 |  | 16688/228 | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEESTOWN | 1018 LEESTOWN RD B | 073 | FRA | 2022-11-16 | U128816 | RPOLLY | 2003-04-24 | 2022-07-01 | 2022-12-31 |  | OLIVER MAYNARD | 2022-11-16 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 2.5333 | 1 | 1711.18 | 157.37 | 0 | 9.23 | 1544.58 | 0 | 0 | 0
KY | KY - WEST | 2623 | 10833249000 |  | 100282442 | 21 | 6712232O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | PARIS | 1233 PARIS PK | 209 | GEO | 2022-11-16 | U126308 | RSTOKLE | 2010-04-02 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-11-16 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 3005.59 | 0 | 100.16 | 0 | 2905.43 | 0 | 0 | 0
KY | KY - WEST | 2621 | 10872147800 |  | 100334748 |  | 6724208A | 0779343 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 2 | 2621P | LIBERTY | 2446 LIBERTY RD | 067 | LEX | 2022-11-16 | LSTONE | U906609 | 2010-12-14 | 2022-07-01 | 2022-12-31 |  | LSTONE | 2022-11-16 | 2022-11-07 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.1833 | 5 | 679.75 | 623.66 | 19.59 | 36.5 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11879632400 |  | 100448363 |  | 6720204E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | TANFORAN | 1328 TANFORAN DR | 067 | LEX | 2022-11-16 | U127206 | U906307 | 2011-01-18 | 2022-11-16 | 2022-12-31 |  | JUSTIN HOBBS | 2022-11-16 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 4208.13 | 477.86 | 0 | 27.95 | 3702.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11927134900 |  | 100334750 |  | 6724208F | 0779343 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 2 | 2621P | LIBERTY | 2449 LIBERTY RD | 067 | LEX | 2022-11-17 | U930915 | U125208 | 2011-09-30 | 2022-07-01 | 2022-12-31 |  | LSTONE | 2022-11-16 | 2022-10-04 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.1167 | 4 | 805.9 | 729.21 | 34.04 | 42.65 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12968037500 |  | 100459309 |  | 6736252M |  |  |  | 566 | EX | SOII - METER ABANDON ONLY | 2621P | PLEASANT | 310 E PLEASANT ST | 097 | CYN | 2022-11-16 | U126284 | U124967 | 2012-05-02 | 2014-12-31 |  |  | JOSH PASLEY | 2022-11-16 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 513.2 | 0 | 0 | 0 | 513.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 17531395300 |  | 100408846 |  | 6736228L |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | CLINTONVILLE | 501 CLINTONVILLE RD L21 | 017 | PAR | 2022-11-16 | U126284 | U917287 | 2017-08-07 | 2019-12-31 |  |  | JOSH PASLEY | 2022-11-16 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - CENTRAL | 2629 | 17531409100 |  | 100416957 |  | 6736228L | 1638587 |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | CLINTONVILLE | 501 CLINTONVILLE RD L5A | 017 | PAR | 2022-11-16 | U126284 | U917287 | 2017-08-07 | 2019-12-31 |  |  | JOSH PASLEY | 2022-11-16 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - WEST | 2621 | 19736099500 |  | 100323258 |  | 6716208P | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE*PLANT | 2621P | ROBIN | 782 ROBIN RD | 067 | LEX | 2022-11-16 | LSTONE | AOC SYST | 2019-08-23 | 2020-02-21 | 2020-12-31 |  | LSTONE | 2022-11-16 | 2022-11-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 38.9 | 11 | 6624.71 | 2469.93 | 970.92 | 104.7 | 3079.16 | 0 | 0 | 0
KY | KY - WEST | 2623 | 20803493200 |  | 100284001 |  | 6712228F | 1103323 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEXINGTON | 930 LEXINGTON RD | 209 | GEO | 2022-11-16 | U126308 | U125208 | 2020-04-23 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-11-16 | 2020-10-05 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 14.6167 | 2 | 4951.99 | 1002.18 | 0 | 1066.68 | 2883.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21026129900 |  |  |  | 6716212O | 2176780 | U461383 |  | 584 | EX | RETIRE PIT REG STATION W/AMRP | 2621M | PRESS | 800 PRESS AV | 067 | LEX | 2022-12-22 | U125936 | U461383 | 2021-06-28 | 2022-12-30 | 2022-12-31 | 2022-11-16 | SMCHOLAN | 2022-11-16 | 2022-11-16 |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00584 | 3200584 |  |  | WP1299 |  |  | 100 | 058432210261299 | 4.2667 | 0 | 3639 | 1526.85 | 0 | 507.35 | 1604.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21026994000 |  |  |  | 6716208C | 2176780 | U461383 |  | 557 | EX | INSTALL 10930 - 2"/4"PMMP MAIN | 2600B | STATE | STATE ST | 067 | LEX | 2022-12-05 | U128132 | U461383 | 2021-01-06 | 2022-01-05 | 2022-12-31 | 2022-11-16 | JOSHUA COX | 2022-11-16 | 2022-04-26 | 2022-05-18 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP9940 | AMRCB |  | 100 | 055732210269940 | 1774.35 | 2064307 | 1681569.14 | 116583.59 | 38448 | 26484.22 | 1280693.02 | 0 | 9785.01 | 209575.3 | 10169
KY | KY - CENTRAL | 2632 | 21897159200 |  | 500882790 |  | 7260280N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | FOREST | 1435 FOREST AV | 161 | MAY | 2022-11-16 | U126286 | U124841 | 2021-03-25 | 2022-11-15 |  |  | TYLER ALLISON | 2022-11-16 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 10.55 | 3 | 2425.02 | 733.44 | 0 | 48.78 | 1642.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960243000 |  | 100320963 |  | 6720212M | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | WOODLAND | 206 WOODLAND AV | 067 | LEX | 2022-12-02 | U461375 | U134723 | 2021-12-17 | 2022-12-30 |  |  | LARRY BROWN | 2022-11-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 14162.45 | 0 | 0 | 0 | 14162.45 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026209800 |  |  |  | 6716212O | 2176780 | U461383 |  | 586 | EX | RETIRE VAULT STRUCTURE | 2621M | PRESS | 800 PRESS AV | 067 | LEX | 2022-12-22 | U125936 | U461383 | 2022-07-05 | 2022-12-30 | 2022-12-31 | 2022-11-16 | SMCHOLAN | 2022-11-16 |  |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00586 | 3200586 |  |  | WP2098 | AMRCB |  | 100 | 058632220262098 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129018300 |  | 500287371 |  | 6680228H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CLIFTON | 811 CLIFTON DR | 073 | FRA | 2022-11-16 | U128816 | U130722 | 2022-09-05 | 2022-12-30 |  |  | OLIVER MAYNARD | 2022-11-16 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 3.5 | 1 | 1086.48 | 218.58 | 0 | 12.8 | 855.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129060700 |  | 100356765 |  | 7260276D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | ASH | 1717 ASH ST | 161 | MAY | 2022-11-16 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-11-16 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 9.5 | 1 | 2422.38 | 659.76 | 0 | 38.62 | 1724 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22142562100 |  | 100333778 |  | 6720212J |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | DELAWARE | 924 DELAWARE AV | 067 | LEX | 2022-11-16 | U127206 | U125763 | 2022-11-02 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-11-16 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 3695.17 | 0 | 0 | 0 | 3695.17 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22144675700 |  | 100276710 |  | 6684228H |  |  |  | 565 | EX | GRADE 1 REPAIR SERVICE LINE | 2621P | HILLCREST | 704 HILLCREST AV | 073 | FRA | 2022-11-16 | DCOLLIN | U129939 | 2022-11-15 | 2022-11-15 | 2022-11-15 |  | DCOLLIN | 2022-11-16 | 2022-11-15 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 48.1833 | 7 | 3723.02 | 2970.63 | 311.64 | -278.51 | 719.26 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22144912500 |  | 100274347 |  | 6684228N |  |  |  | 566 | EX | PAPER ABANDONMENT | 2621P | CAMPBELL | 307 W CAMPBELL ST | 073 | FRA | 2022-11-16 | U128816 | U129939 | 2022-11-16 | 2022-11-16 |  |  | OLIVER MAYNARD | 2022-11-16 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 1.85 | 1 | 124.27 | 117.4 | 0 | 6.87 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22144912900 |  | 100274348 |  | 6684228N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309228 | 2621P | CAMPBELL | 307 W CAMPBELL ST | 073 | FRA | 2022-11-16 | U128816 | U129939 | 2022-11-16 | 2022-11-24 | 2024-05-31 |  | OLIVER MAYNARD | 2022-11-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.5333 | 1 | 3939.17 | 94.9 | 441.81 | 5.55 | 3396.91 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22979031200 |  | 100284071 |  | 6712224G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LEXINGTON | 1879 LEXINGTON RD | 209 | GEO | 2022-11-16 | U126604 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | WILL FULKS | 2022-11-16 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 5.5833 | 1 | 3396.52 | 392.68 | 0 | 85.73 | 2918.11 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22999351400 |  | 100301798 |  | 6712212H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309070 | 2621P | DEAUVILLE | 1914 DEAUVILLE DR | 067 | LEX | 2022-11-16 | U930915 | U125208 | 2022-05-09 | 2022-11-17 | 2022-12-05 |  | LSTANFI | 2022-11-16 | 2022-11-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.55 | 6 | 1829.5 | 1471.9 | 297.33 | -62.93 | 123.2 | 0 | 0 | 0
KY | KY - WEST | 2623 | 07680932200 |  | 100281199 |  | ? |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | OLD FRANKFORT | 70 OLD FRANKFORT PK | 239 | MID | 2022-11-17 | U126604 | SSUTHER | 2007-03-29 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 5.6167 | 1 | 1956.14 | 394.79 | 0 | 86.19 | 1475.16 | 0 | 0 | 0
KY | KY - EAST | 2633 | 07685214400 |  | 100264741 | 23 | X-18-15-1 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NEW CAMP | 605 NEW CAMP RD | 195 | S W | 2022-11-17 | U123965 | LDAVIS | 2007-05-01 | 2022-07-01 | 2022-12-31 |  | MBLANKE | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.45 | 1 | 4029.74 | 394.09 | 0 | 84.47 | 3551.18 | 0 | 0 | 0
KY | KY - WEST | 2623 | 08737634000 |  | 100461203 |  | 6696212L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | LOCUST | 250 S LOCUST ST | 239 | VER | 2022-11-17 | U126308 | DMCCULL | 2008-06-30 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8 | 1 | 2132.2 | 569.34 | 148.92 | 554.75 | 859.19 | 0 | 0 | 0
KY | KY - EAST | 2633 | 11913707900 |  | 100264740 |  | 7384168O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NEW CAMP | 595 NEW CAMP RD | 195 | S W | 2022-11-17 | U123965 | U907001 | 2011-06-28 | 2022-07-01 | 2022-12-31 |  | MBLANKE | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.4333 | 1 | 3456.32 | 394.09 | 0 | 84.47 | 2977.76 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12965308000 |  | 100360134 |  | 16740232M |  |  |  | 566 | EX | ABANDON SL- DOWNSTREAM | 2621P | MAIN | 617< MAIN ST | 017 | PAR | 2022-11-17 | U126284 | U124967 | 2012-04-16 | 2014-12-31 |  |  | JOSH PASLEY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 814.42 | 0 | 0 | 0 | 814.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12993572900 |  | 100315057 |  | 6716212O | 2176780 |  |  | 566 | EX | ABANDON SL W/CAPITAL JOB | 2600B | LEADER | 144 LEADER AV B | 067 | LEX | 2022-11-17 | U461322 | U125765 | 2012-10-16 | 2023-12-29 |  |  | STEVE CANOY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - CENTRAL | 2629 | 13165680800 |  | 100269082 |  | 6736252M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SAINT CLAIR | 109 SAINT CLAIR ST | 097 | CYN | 2022-11-17 | U126284 | U126921 | 2013-10-02 | 2049-12-31 |  |  | JOSH PASLEY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18601935800 |  | 100321121 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | MAXWELL | 300 E MAXWELL ST 1F | 067 | LEX | 2022-11-17 | U126309 | U125964 | 2018-04-11 | 2023-12-28 |  |  | JAMIE LYNN | 2022-11-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2768.22 | 0 | 0 | 0 | 2768.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21026132400 |  | 500512127 |  | 6716212L | 2181300 | U461383 |  | 555 | EX | INSTALL 225' OF 2"PMMP | 2600B | VINE | 200 W VINE ST GENERAT | 067 | LEX | 2022-11-22 | U124014 | U461383 | 2021-07-20 | 2022-11-09 | 2022-11-18 | 2022-11-09 | WGRAVES | 2022-11-17 | 2022-10-25 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP1324 |  |  | 100 | 055532210261324 | 197.4167 | 5226 | 85412.94 | 11936.27 | 1865.05 | 3487.55 | 60748.14 | 0 | 18.28 | 7357.65 | 201
KY | KY - EAST | 2631 | 21026993401 |  |  |  | 7352256B | 2176770 | U461383 |  | 557 | EX | INSTALL 10750'-2"/4"PMMP MAIN | 2600B | LEE | LEE ST | 019 | ASH | 2023-01-25 | U128132 | U461383 | 2022-09-22 | 2022-01-21 | 2022-12-31 | 2022-09-16 | ORA SLONE | 2022-11-17 | 2022-09-26 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP9934 | AMRCB |  | 100 | 055732210269934 | 1581.6833 | 2079573 | 2072101.63 | 129411.4 | 61580.04 | 22069.11 | 1559702.03 | 0 | 29901.16 | 269437.89 | 11749
KY | KY - EAST | 2631 | 21026993500 |  |  |  | 7352256B | 2176770 | U461383 |  | 558 | EX | RETIRE 13650' OF 4"/6"BSLP | 2600B | LEE | LEE ST | 019 | ASH | 2022-11-29 | U128132 | U461383 | 2021-01-06 | 2022-12-30 | 2022-12-31 | 2022-11-09 | ORA SLONE | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP9935 | AMRCB |  | 100 | 055832210269935 |  | 0 | 80 | 0 | 0 | 0 | 80 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883291700 |  | 100352482 |  | 6748204F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 2 | 2621P | MUDDY CREEK | 2065 MUDDY CREEK RD | 049 | WIN | 2022-11-17 | U129722 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-11-17 | 2022-10-04 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.3667 | 2 | 2396.9 | 495.93 | 0 | 119.15 | 1781.82 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883329900 |  | 500284296 |  | 6684232O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | OLD-FRANKFT | 4963 OLD-FRANKFT PK | 073 | FRA | 2022-11-17 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 4.3833 | 1 | 3039.3 | 310.17 | 0 | 67.74 | 2661.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959035500 |  | 100315320 |  | 6716208C | 2176780 |  |  | 566 | EX | ABANDON SL W/CAPITAL JOB | 2600B | STATE | 110 STATE ST 1F | 067 | LEX | 2022-11-17 | U461322 | U134723 | 2021-12-10 | 2022-12-30 |  |  | STEVE CANOY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 21959035600 |  | 100315319 |  | 6716208C | 2176780 |  |  | 566 | EX | ABANDON SL W/CAPITAL JOB | 2600B | STATE | 112 STATE ST | 067 | LEX | 2022-11-17 | U461322 | U134723 | 2021-12-10 | 2022-12-30 |  |  | STEVE CANOY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 21959035700 |  | 100315316 |  | 6716208C | 2176780 |  |  | 566 | EX | ABANDON SL W/CAPITAL JOB | 2600B | STATE | 120 STATE ST | 067 | LEX | 2022-11-17 | U461322 | U134723 | 2021-12-10 | 2022-12-30 |  |  | STEVE CANOY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 21959035800 |  | 100315268 |  | 6716208C | 2176780 |  |  | 566 | EX | ABANDON SL W/CAPITAL JOB | 2600B | STATE | 127 STATE ST | 067 | LEX | 2022-11-17 | U461322 | U134723 | 2021-12-10 | 2022-12-30 |  |  | STEVE CANOY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 21959037700 |  | 100315383 |  | 6716208C | 2176780 |  |  | 566 | EX | ABANDON SL W/CAPITAL JOB | 2600B | UNIVERSITY | 126 UNIVERSITY AV 1F | 067 | LEX | 2022-11-17 | U461322 | U134723 | 2021-12-10 | 2022-12-30 |  |  | STEVE CANOY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 21959037900 |  | 100315381 |  | 6716208C | 2176780 |  |  | 566 | EX | ABANDON SL W/CAPITAL JOB | 2600B | UNIVERSITY | 130 UNIVERSITY AV | 067 | LEX | 2022-11-17 | U461322 | U134723 | 2021-12-10 | 2022-12-30 |  |  | STEVE CANOY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 21959044100 |  | 100315328 |  | 6716208C | 2176780 |  |  | 566 | EX | ABANDON SL W/CAPITAL JOB | 2600B | UNIVERSITY | 111 UNIVERSITY AV | 067 | LEX | 2022-11-17 | U461322 | U134723 | 2021-12-10 | 2022-12-30 |  |  | STEVE CANOY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 21959047000 |  | 100315292 |  | 6716208C | 2176780 |  |  | 566 | EX | ABANDON SL W/CAPITAL JOB | 2600B | CRESCENT | 1045 CRESCENT AV A | 067 | LEX | 2022-11-17 | U461322 | U134723 | 2021-12-10 | 2022-12-30 |  |  | STEVE CANOY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - CENTRAL | 2629 | 21959968400 |  | 100358936 |  | 6736232L | 2075121 |  |  | 566 | EX | ABANDON SL W/ CAPITOL JOB | 2600B | HANSON | 426 HANSON ST | 017 | PAR | 2022-11-29 | U124003 | U134723 | 2021-12-16 | 2022-09-30 |  |  | BPULLIAM/MILLER | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26290043 | 8 | 1 | 3244.35 | 541.27 | 0 | 1074.52 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129023200 |  | 100271564 |  | 6736252N |  |  |  | 566 | EX | ABANDON SL - PEND CN/OFL 10/14 | 2621P | HARRISON | 113 HARRISON AV | 097 | CYN | 2022-11-17 | U123111 | U130722 | 2022-09-05 | 2022-12-30 |  |  | LYN STAFFORD | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129025800 |  | 500023456 |  | 7260276M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | STONELICK | 8057 STONELICK RD | 161 | MAY | 2022-11-17 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 8 | 1 | 1948.12 | 555.61 | 0 | 32.51 | 1360 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129058400 |  | 500107991 |  | 6744208J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WESTSIDE | 144 WESTSIDE DR | 049 | WIN | 2022-11-17 | U129731 | U130722 | 2022-09-05 | 2022-12-30 |  |  | F.GOINS | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 6.6667 | 1 | 2625.07 | 415.41 | 0 | 99.23 | 2110.43 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129061600 |  | 100356756 |  | 7260276C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | MAPLE | 1698 MAPLE PY | 161 | MAY | 2023-01-20 | U125566 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DESKAGG | 2022-11-17 | 2022-11-16 |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 3.5167 | 2 | 1645.16 | 231.93 | 0 | 53.23 | 1360 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129061700 |  | 100356712 |  | 7260276D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | MASON LEWIS | 9073 MASON LEWIS RD | 161 | MAY | 2022-11-17 | DESKAGG | U130722 | 2022-09-05 | 2022-12-30 |  |  | DESKAGG | 2022-11-17 | 2022-11-16 |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 7.4833 | 2 | 1998.6 | 492.97 | 0 | 113.13 | 1392.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129062600 |  | 501169791 |  | 7256280J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | PLATINUM | 700 PLATINUM DR | 161 | MAY | 2022-11-29 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 17 | 2 | 2609.78 | 1180.68 | 0 | 69.1 | 1360 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129081200 |  | 100417299 |  | 6720212H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KILKENNY | 1821 KILKENNY CT | 067 | LEX | 2022-11-17 | U127206 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2053.55 | 0 | 0 | 0 | 2053.55 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22131005600 |  | 100315398 |  | 6716208C | 2176780 |  |  | 566 | EX | RETIRE S/L WITH 21-0269940-00 | 2600B | WALLER | 135 WALLER AV | 067 | LEX | 2022-11-17 | U461322 | U461383 | 2022-09-13 | 2022-12-30 | 2022-12-31 |  | STEVE CANOY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 22131005700 |  | 500604465 |  | 6716208C | 2176780 |  |  | 566 | EX | RETIRE S/L W/21-0269940-00 | 2600B | WALLER | 127 WALLER AV 2 | 067 | LEX | 2022-11-17 | U461322 | U461383 | 2022-09-13 | 2022-12-30 | 2022-12-31 |  | STEVE CANOY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 22131005800 |  | 100315397 |  | 6716208C | 2176780 |  |  | 566 | EX | RETIRE S/L W/21-0269940-00 | 2600B | WALLER | 127 WALLER AV 1 | 067 | LEX | 2022-11-17 | U461322 | U461383 | 2022-09-13 | 2022-12-30 | 2022-12-31 |  | STEVE CANOY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 22131006000 |  | 500778520 |  | 6716208C | 2176780 |  |  | 566 | EX | RETIRE S/L W/21-0269940-00 | 2600B | LIMESTONE | 1229 S LIMESTONE ST REAR | 067 | LEX | 2022-11-17 | U461322 | U461383 | 2022-09-13 | 2022-12-30 | 2022-12-31 |  | STEVE CANOY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 22133749800 |  | 100315400 |  | 6716208C | 2176780 |  |  | 566 | EX | RETIRE S/L WITH 21-0269940-00 | 2600B | WALLER | 201 WALLER AV | 067 | LEX | 2022-11-17 | U461322 | U461383 | 2022-09-22 | 2022-12-30 | 2022-12-30 |  | STEVE CANOY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 22135660800 |  | 100315386 |  | 6716208C | 2176780 |  |  | 566 | EX | RETIRE S/L W/21-0269940-00 | 2600B | UNIVERSITY | 114 UNIVERSITY AV | 067 | LEX | 2022-11-17 | U461322 | U461383 | 2022-09-29 | 2022-12-15 | 2022-12-15 |  | STEVE CANOY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 22135661200 |  | 100315385 |  | 6716208C | 2176780 |  |  | 566 | EX | RETIRE S/L W/21-0269940-00 | 2600B | UNIVERSITY | 118 UNIVERSITY AV | 067 | LEX | 2022-11-17 | U461322 | U461383 | 2022-09-29 | 2022-12-15 | 2022-12-15 |  | STEVE CANOY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 22135661700 |  | 100315335 |  | 6716208C | 2176780 |  |  | 566 | EX | RETIRE SL W/21-0269940-00 | 2600B | UNIVERSITY | 131 UNIVERSITY AV | 067 | LEX | 2022-11-17 | U461322 | U461383 | 2022-09-29 | 2022-12-15 | 2022-12-15 |  | STEVE CANOY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 22135662100 |  | 100315336 |  | 6716208C | 2176780 |  |  | 566 | EX | RETIRE SL W/21-0269940-00 | 2600B | UNIVERSITY | 135 UNIVERSITY AV | 067 | LEX | 2022-11-21 | U461322 | U461383 | 2022-09-29 | 2022-12-15 | 2022-12-15 |  | STEVE CANOY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 22135662500 |  | 100315338 |  | 6716208C | 2176780 |  |  | 566 | EX | RETIRE SL W/21-0269940-00 | 2600B | UNIVERSITY | 141 UNIVERSITY AV | 067 | LEX | 2022-11-17 | U461322 | U461383 | 2022-09-29 | 2022-12-15 | 2022-12-15 |  | STEVE CANOY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 22135666200 |  | 100315395 |  | 6716208C | 2176780 |  |  | 566 | EX | RETIRE S/L W/21-0269940-00 | 2600B | WALLER | 121 WALLER AV | 067 | LEX | 2022-11-17 | U461322 | U461383 | 2022-09-29 | 2022-12-15 | 2022-12-15 |  | STEVE CANOY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 22135666400 |  | 100315396 |  | 6716208C | 2176780 |  |  | 566 | EX | RETIRE S/L W/-21-0269940-00 | 2600B | WALLER | 125 WALLER AV | 067 | LEX | 2022-11-17 | U461322 | U461383 | 2022-09-29 | 2022-12-15 | 2022-12-15 |  | STEVE CANOY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 22142561200 |  | 100315313 |  | 6716208C | 2176780 |  |  | 566 | EX | RETIRE SL W/21-0269940-00 | 2600B | STATE | 136 STATE ST | 067 | LEX | 2022-11-18 | U461322 | U461383 | 2022-11-02 | 2022-12-30 | 2022-12-31 |  | STEVE CANOY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - EAST | 2631 | 22143681200 |  | 100264988 |  | 7352260N | 2176770 |  |  | 566 | EX | ABND SL W/21026993400 | 2600B | MAIN | 2409 MAIN ST W | 019 | ASH | 2022-11-17 | U124015 | U125768 | 2022-11-09 | 2049-12-31 |  |  | ORA SLONE | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1
KY | KY - CENTRAL | 2629 | 22144339100 |  | 100448467 |  | 6736248A |  |  |  | 566 | EX | ABANDON SL -I/I/LGCY | 2600B | WEBSTER | 311 WEBSTER AV B | 097 | CYN | 2022-11-17 | U126532 | U134723 | 2022-11-14 | 2022-12-30 |  |  | LESLIE SHARON | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.5167 | 1 | 3832.11 | 538.64 | 0 | 585.52 | 2707.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22144603000 |  | 500890709 |  | 6716208C | 2176780 |  |  | 566 | EX | ABANDON SL W/CAPITAL JOB | 2600B | CRESCENT | 1045 CRESCENT AV B | 067 | LEX | 2022-11-17 | U461322 | U134723 | 2022-11-15 | 2023-12-29 |  |  | STEVE CANOY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 22144603300 |  | 100315382 |  | 6716208C | 2176780 |  |  | 566 | EX | ABANDON SL W/CAPITAL JOB | 2600B | UNIVERSITY | 126 UNIVERSITY AV 2F | 067 | LEX | 2022-11-17 | U461322 | U134723 | 2022-11-15 | 2023-12-29 |  |  | STEVE CANOY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 22144603400 |  | 100315321 |  | 6716208C | 2176780 |  |  | 566 | EX | ABANDON SL W/CAPITAL JOB | 2600B | STATE | 110 STATE ST 2F | 067 | LEX | 2022-11-17 | U461322 | U134723 | 2022-11-15 | 2023-12-29 |  |  | STEVE CANOY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - CENTRAL | 2629 | 22145085200 |  | 100359355 |  | 6736232P |  |  |  | 566 | EX | ABANDON SL- I/I/LGCY | 2600B | CYPRESS | 1439 CYPRESS ST | 017 | PAR | 2022-11-17 | U126284 | U134723 | 2022-11-17 | 2022-12-30 |  |  | JOSH PASLEY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.95 | 1 | 1731.29 | 197.46 | 0 | 203.84 | 1329.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22145093000 |  | 100417019 |  | 6720212H |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2600B | KILKENNY | 1819 KILKENNY CT | 067 | LEX | 2022-11-17 | U127206 | U134723 | 2022-11-17 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 827.75 | 477.86 | 0 | 27.95 | 321.94 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22145095100 |  | 500510298 |  | 6692228E | 9613348 |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | STONEHEDGE | 316 STONEHEDGE | 073 | FRA | 2022-11-17 | U128816 | U129939 | 2022-11-17 | 2022-11-17 |  |  | OLIVER MAYNARD | 2022-11-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 4.5667 | 1 | 3467.46 | 533.97 | 227.47 | 31.24 | 2674.78 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22145105500 |  | 100270038 |  | 6732252P |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2600B | 2ND | 120 2ND ST | 097 | CYN | 2022-11-17 | U123111 | U134723 | 2022-11-17 | 2022-12-30 |  |  | LYN STAFFORD | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1665.66 | 0 | 0 | 0 | 1665.66 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22145132500 |  | 100344673 |  | 6700224L |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | WINTER | 413 N WINTER ST | 239 | MID | 2022-11-17 | U128816 | U129939 | 2022-11-17 | 2022-11-17 |  |  | OLIVER MAYNARD | 2022-11-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 12.9667 | 2 | 5650.48 | 793.68 | 273.05 | 46.45 | 4537.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22979041900 |  | 100349856 |  | 6748204A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FRENCH | 120 FRENCH AV | 049 | WIN | 2022-11-18 | U129731 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | F.GOINS | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1957.17 | 0 | 0 | 0 | 1957.17 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22979056900 |  | 501210211 |  | 6696212H | 1744638 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PRESTON | 121 PRESTON CT | 239 | VER | 2022-11-17 | U126308 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | J ENSMINGER | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 865.65 | 0 | 10.55 | 0 | 855.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22993606400 |  | 100315334 |  | 6716208C | 2176780 |  |  | 566 | EX | RETIRE S/L SRMP 21-0269940-00 | 2600B | UNIVERSITY | 127 UNIVERSITY AV | 067 | LEX | 2022-11-17 | U461322 | U461383 | 2022-04-14 | 2022-12-01 | 2022-12-01 |  | STEVE CANOY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 98359008500 |  | 100315005 |  | 16716212O | 2176780 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | LEADER | 113 LEADER AV | 067 | LEX | 2022-11-17 | U461322 | TDORTEN | 1998-08-27 | 2022-12-30 |  |  | STEVE CANOY | 2022-11-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 04564860600 |  | 100336140 |  | 600000000 | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MONTGOMERY | 688 MONTGOMERY AV | 067 | LEX | 2022-11-18 | U127206 | SSUTHER | 2004-02-03 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-11-18 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 6930.33 | 477.86 | 0 | 27.95 | 6424.52 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 06668988600 |  | 100417462 |  | 6736248A | 1315787 |  |  | 566 | EX | NEEDS REVIEWED - RETIRE | 2621P | NEW LAIR | 550 NEW LAIR RD DN | 097 | CYN | 2022-11-18 | U126284 | SKSMITH | 2006-12-19 | 2014-12-23 |  |  | JOSH PASLEY | 2022-11-18 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.15 | 1 | 3957.91 | 344.68 | 0 | 355.83 | 3257.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 07696379900 |  | 100281136 | 13 | 16692/228 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEESTOWN | 1500 LEESTOWN RD | 073 | FRA | 2022-11-18 | U128816 | JCOLYER | 2007-07-30 | 2022-07-01 | 2022-12-31 |  | OLIVER MAYNARD | 2022-11-18 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 3.05 | 1 | 2272.47 | 154.24 | 0 | 9.03 | 2109.2 | 0 | 0 | 0
KY | KY - WEST | 2623 | 10869360100 |  | 100281098 |  | 6692216B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | FRANKFORT | 5095 FRANKFORT RD | 239 | VER | 2022-11-18 | U126308 | U906314 | 2010-11-22 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-11-18 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 9 | 1 | 1533.07 | 640.49 | 0 | 37.48 | 855.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11898551500 |  | 500130629 |  | X-1206/43 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | IRVINE | 1420 S IRVINE RD REAR | 065 | IRV | 2022-11-18 | U126602 | U906631 | 2011-03-30 | 2022-11-18 |  |  | DEREK PAYTON | 2022-11-18 | 2022-10-20 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 17.5 | 2 | 8498.65 | 1034.51 | 0 | 61.03 | 7403.11 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12968026500 |  | 100348990 |  | 6748208M |  |  |  | 566 | EX | ABANDON SL - SOII/INSIDE | 2621P | BROADWAY | 125 E BROADWAY ST 2F | 049 | WIN | 2022-11-18 | U129731 | U124967 | 2012-05-02 | 2017-12-29 |  |  | F.GOINS | 2022-11-18 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 479.22 | 0 | 0 | 0 | 479.22 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12968027600 |  | 100353109 |  | 6744208P |  |  |  | 566 | EX | SOII - METER ABANDON ONLY | 2621P | MAIN | 8 N MAIN ST | 049 | WIN | 2022-11-18 | U129731 | U124967 | 2012-05-02 | 2014-12-31 |  |  | F.GOINS | 2022-11-18 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 780.44 | 0 | 0 | 0 | 780.44 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12968027700 |  | 100353110 |  | 6744208P |  |  |  | 566 | EX | SOII - METER ABANDON ONLY | 2621P | BROADWAY | 5 W BROADWAY ST | 049 | WIN | 2022-11-18 | U129731 | U124967 | 2012-05-02 | 2014-12-31 |  |  | F.GOINS | 2022-11-18 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 1399.54 | 499.72 | 0 | 119.38 | 780.44 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12968590400 |  | 100360170 |  | 16740232M |  |  |  | 566 | EX | ABANDON SL- DOWNSTREAM | 2621P | 5TH | 8 W 5TH ST | 017 | PAR | 2022-11-18 | U126284 | U124967 | 2012-05-07 | 2014-12-31 |  |  | JOSH PASLEY | 2022-11-18 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 814.42 | 0 | 0 | 0 | 814.42 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12975875300 |  | 100348994 |  | 6748208M |  |  |  | 566 | EX | ABANDON SL - SOII/INSIDE | 2621P | BROADWAY | 125 E BROADWAY ST 1FR | 049 | WIN | 2022-11-28 | U129731 | U123854 | 2012-06-11 | 2017-12-29 |  |  | F.GOINS | 2022-11-18 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 479.22 | 0 | 0 | 0 | 479.22 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12975875400 |  | 100348995 |  | 6748208M |  |  |  | 566 | EX | ABANDON SL - SOII/INSIDE | 2621P | BROADWAY | 125 E BROADWAY ST 1FL | 049 | WIN | 2022-11-28 | U129731 | U123854 | 2012-06-11 | 2017-12-29 |  |  | F.GOINS | 2022-11-18 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2005.08 | 0 | 0 | 0 | 2005.08 | 0 | 0 | 0
KY | KY - EAST | 2631 | 20026932501 |  |  |  | 7360244A | 2070383 | U132280 |  | 575 | VO | INSTALL NEW BUILDING AT MAP | 2630M | US23--ASHLAND OIL | US23--ASHLAND OIL | 019 | CAT | 2023-07-31 |  | U132280 | 2021-11-29 | 2023-12-27 | 2023-12-31 | 2022-11-18 | DASH | 2022-11-18 | 2022-08-01 |  | F | [11 empty] | 22026245500 | 25 |  | 338.2833 | 104 | 182447.76 | 21648.29 | 122227.36 | 10031.13 | 27742.5 | 0 | 798.48 | 0
KY | KY - WEST | 2623 | 21883055600 |  | 100282788 |  | 6712228B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BROADWAY | 202 S BROADWAY ST | 209 | GEO | 2022-11-18 | U126308 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-11-18 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 876.24 | 0 | 16.08 | 0 | 860.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026185301 |  | 501328825 |  | 6712208M | 2288773 | U461383 |  | 555 | EX | INSTALL 875' OF 2"PMMP MAIN | 2600B | COCOS | COCOS WY LT1 | 067 | LEX | 2022-11-22 | U128132 | U461383 | 2022-11-17 | 2022-10-31 | 2022-11-18 | 2022-11-17 | JDUNN | 2022-11-18 | 2022-11-16 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP1853 |  |  | 100 | 055532220261853 | 136.2833 | 11600 | 69561.33 | 8804.4 | 1987.36 | 603.32 | 54656.03 | 0 | 154.15 | 3356.07 | 725
KY | KY - CENTRAL | 2629 | 22129021200 |  | 100448558 |  | 6740232N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WASHINGTON | 399 WASHINGTON ST STE 108 | 017 | PAR | 2022-11-18 | U126284 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JOSH PASLEY | 2022-11-18 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.85 | 1 | 1987.05 | 324.6 | 0 | 335.11 | 1327.34 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129021600 |  | 100352523 |  | 6732208L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | COMBS FERRY | 100 COMBS FERRY RD | 049 | WIN | 2022-11-18 | U126602 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DEREK PAYTON | 2022-11-18 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2233.65 | 0 | 0 | 0 | 2233.65 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129060800 |  | 100354814 |  | 7260280N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | BROADWAY | 222 BROADWAY ST | 161 | MAY | 2022-11-18 | U125566 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DESKAGG | 2022-11-18 | 2022-11-17 |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 6.2667 | 2 | 1835.48 | 413.15 | 0 | 94.83 | 1327.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129061300 |  | 100355565 |  | 7260276B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | CLARK | 503 CLARK ST | 161 | MAY | 2022-11-18 | U125566 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DESKAGG | 2022-11-18 | 2022-11-17 |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 6.8333 | 2 | 1881.76 | 448.74 | 0 | 73.02 | 1360 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22139143700 |  | 100315315 |  | 6716208C | 2176780 |  |  | 566 | EX | RETIRE S/L W/21-0269940-00 | 2600B | STATE | 130 STATE ST | 067 | LEX | 2022-11-18 | U461322 | U461383 | 2022-10-14 | 2022-12-15 | 2022-12-15 |  | STEVE CANOY | 2022-11-18 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 22139965600 |  | 100305276 |  | 6712212O |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTRQD | 2621P | LINSTEAD | 1668 LINSTEAD DR | 067 | LEX | 2022-11-18 | U930915 | U132002 | 2022-10-19 | 2022-11-01 | 2022-11-17 |  | KKINDER | 2022-11-18 | 2022-10-26 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 39.0667 | 11 | 2469.52 | 2332.23 | 0 | 137.29 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22141220200 |  | 100346141 |  | 6700212I |  |  |  | 566 | EX | ABANDON - DEMO/LNDBRK 11-2-22 | 2621P | LEXINGTON | 400 LEXINGTON RD | 239 | VER | 2022-11-18 | BWHITE | U125208 | 2022-10-26 | 2022-10-28 | 2022-11-30 |  | BWHITE | 2022-11-18 | 2022-11-16 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 12.7833 | 4 | 1248.39 | 807.69 | 0 | -95.3 | 536 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22141360500 |  | 100328363 |  | 6720208F |  |  |  | 565 | EX | SERVICE LINE - RELOCATE | 2621P | COOPER | 1313 COOPER DR | 067 | LEX | 2022-11-18 | TROE | U125208 | 2022-10-27 | 2022-10-28 | 2022-11-17 |  | TROE | 2022-11-18 | 2022-11-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.8667 | 6 | 7334.45 | 1360.98 | 232.06 | 15.06 | 5726.35 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22142561300 |  | 100315314 |  | 6716208C | 2176780 |  |  | 566 | EX | RETIRE S/L W/21-0269940-00 | 2600B | STATE | 132 STATE ST | 067 | LEX | 2022-11-18 | U461322 | U461383 | 2022-11-02 | 2022-12-30 | 2022-12-31 |  | STEVE CANOY | 2022-11-18 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - CENTRAL | 2629 | 22142794700 |  | 100458770 |  | 6748208I |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | STERLING | 15 STERLING ST 1 | 049 | WIN | 2022-11-18 | NRICHIE | U132002 | 2022-11-03 | 2022-11-17 | 2022-12-03 |  | NRICHIE | 2022-11-18 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2 | 2 | 212.11 | 138.81 | 0 | 73.3 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22142795800 |  | 100348040 |  | 6748208I |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | STERLING | 15 STERLING ST 3 | 049 | WIN | 2022-11-18 | U930915 | U132002 | 2022-11-03 | 2022-11-17 | 2022-12-03 |  | NRICHIE | 2022-11-18 | 2022-11-09 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9.6833 | 5 | 1289.81 | 666.87 | 0 | 331.02 | 291.92 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22142797300 |  | 100348039 |  | 6748208I |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | STERLING | 15 STERLING ST 4 | 049 | WIN | 2022-11-18 | NRICHIE | U132002 | 2022-11-03 | 2022-11-17 | 2022-12-03 |  | NRICHIE | 2022-11-18 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.4667 | 2 | 364.88 | 238.79 | 0 | 126.09 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22144934000 |  | 100310677 |  | 6712208L |  |  |  | 565 | EX | SERVICE LINE - REPLACE D310259 | 2621P | NAKOMI | 616 NAKOMI DR | 067 | LEX | 2022-11-18 | JOCHOA | U129939 | 2022-11-16 | 2022-11-16 | 2022-11-16 |  | JOCHOA | 2022-11-18 | 2022-11-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 33.2 | 7 | 3313.13 | 2234.53 | 415.46 | 600.44 | 62.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22145320100 |  | 501181777 |  | 6740232M |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2600B | MAIN | 420 MAIN ST RR | 017 | PAR | 2022-11-18 | U126284 | U134723 | 2022-11-18 | 2023-12-29 |  |  | JOSH PASLEY | 2022-11-18 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1633.86 | 0 | 0 | 0 | 1633.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22145422900 |  | 500332809 |  | 6720208D | 1313369 |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | CODELL | 425 CODELL DR | 067 | LEX | 2022-11-22 | U125208 | U132823 | 2022-11-18 | 2022-11-18 |  |  | LSTANFI | 2022-11-18 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.2 | 2 | 1682.87 | 487.08 | 216.24 | -48.17 | 1027.72 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22145468900 |  | 100257589 |  | 7344264B | 0042214 |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | EAST | 611 EAST ST | 089 | WUR | 2022-11-18 | RECUMP | U132823 | 2022-11-18 | 2022-11-17 | 2022-11-17 |  | RECUMP | 2022-11-18 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 13.9 | 3 | 1041.06 | 963.06 | 200.69 | -122.69 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22978965100 |  | 100270590 |  | 6736248A |  |  |  | 566 | EX | ABANDON / IDLE | 2600B | OLD LAIR | 103 OLD LAIR RD | 097 | CYN | 2023-01-23 | U126286 | U125208 | 2022-02-17 | 2022-04-01 | 2022-04-01 |  | TYLER ALLISON | 2022-11-18 | 2022-10-24 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 20 | 2 | 3595.08 | 1288.1 | 0 | 75.98 | 2231 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 20026969900 |  |  |  | 7240216N | 2074023 | U128885 |  | 585 | EX | INSTALL FENCE & BOLLARDS | 2629M | JOHNSON | JOHNSON ST | 173 | MT | 2023-01-24 | U462081 | U128885 | 2020-08-24 | 2023-12-27 | 2023-12-31 | 2022-11-19 | JMULLINS | 2022-11-19 | 2021-09-13 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00585 | 3200585 |  |  | WP9699 |  |  | 100 | 058532200269699 | 0.2 | 1 | 9603.34 | 11.51 | 0 | 28.19 | 8267.99 | 0 | 209.69 | 1085.96
KY | KY - CENTRAL | 2629 | 20026970000 |  |  |  | 7240216N | 2074023 | U128885 |  | 586 | EX | RETIRE BUILDING | 2629M | JOHNSON | JOHNSON ST | 173 | MT | 2023-01-24 | U462081 | U128885 | 2020-08-24 | 2023-12-29 | 2023-12-31 | 2022-11-19 | JMULLINS | 2022-11-19 | 2021-09-13 |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00586 | 3200586 |  |  | WP9700 |  |  | 100 | 058632200269700 | 52.9667 | 0 | 26427.16 | 3372.47 | 13024.67 | 255.38 | 9774.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22145660700 |  | 100303551 |  | 6712208C |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | PALMS | 2155 PALMS DR | 067 | LEX | 2022-11-20 | SSHIMFE | U134917 | 2022-11-20 | 2022-11-19 | 2022-11-19 |  | SSHIMFE | 2022-11-20 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 11.5 | 4 | 1648.74 | 959.43 | 548.49 | 56.12 | 84.7 | 0 | 0 | 0
KY | KY - WEST | 2623 | 16420137900 |  | 500775943 |  | 6688228K | 0147501 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | VERSAILLES | 456 VERSAILLES RD | 073 | FRA | 2022-11-22 | U126309 | U122906 | 2016-06-22 | 2022-07-01 | 2022-12-31 |  | JAMIE LYNN | 2022-11-21 | 2022-11-18 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 3.15 | 1 | 6056.8 | 160.51 | 0 | 9.38 | 5886.91 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883275100 |  | 500690174 |  | 6724208F | 9934174 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LITTLE SILVER | 813 LITTLE SILVER CT | 067 | LEX | 2022-11-21 | U126308 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-11-21 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2263.09 | 0 | 0 | 0 | 2263.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21959036000 |  | 100315312 |  | 6716208C | 2176780 |  |  | 566 | EX | ABANDON SL W/CAPITAL JOB | 2600B | STATE | 138 STATE ST | 067 | LEX | 2022-11-21 | U461322 | U134723 | 2021-12-10 | 2022-12-30 |  |  | STEVE CANOY | 2022-11-21 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 21959036100 |  | 100315311 |  | 6716208C | 2176780 |  |  | 566 | EX | ABANDON SL W/CAPITAL JOB | 2600B | STATE | 144 STATE ST | 067 | LEX | 2022-11-21 | U461322 | U134723 | 2021-12-10 | 2022-12-30 |  |  | STEVE CANOY | 2022-11-21 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - EAST | 2631 | 22026234300 |  |  |  | 7356256B | 1100065 | U461383 |  | 588 | EX | RETIRE GMB SETTING | 2631M | 23RD | 101 23RD ST | 019 | ASH | 2022-12-08 | U123258 | U461383 | 2022-11-02 | 2023-03-31 | 2023-04-01 | 2022-11-21 | DASH | 2022-11-21 |  |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00588 | 3200588 |  |  | WP2343 |  |  | 100 | 058832220262343 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22101268500 |  | 100274113 |  | 6684228N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309225 | 2621P | WOODLAND | 617 WOODLAND AV | 073 | FRA | 2022-11-21 | U128410 | U125208 | 2022-05-17 | 2022-11-16 | 2024-05-31 |  | CDESPAIN | 2022-11-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 1 | 5882.81 | 526.12 | 442.36 | 30.77 | 4883.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22143488600 |  | 100438034 |  | 6716216P |  |  |  | 566 | EX | ABANDON SL - DEMO/LNDMRK | 2621P | KENNEDY | 698 KENNEDY RD B | 067 | LEX | 2022-11-21 | TROE | U125208 | 2022-11-08 | 2022-12-08 | 2022-12-08 |  | TROE | 2022-11-21 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.6167 | 2 | 365.89 | 301.06 | 47.2 | 17.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22144127100 |  | 100278319 |  | 6688228B |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTRQD | 2621P | PAWNEE | 500 PAWNEE TL | 073 | FRA | 2022-11-21 | DCOLLIN | U132002 | 2022-11-11 | 2022-11-23 | 2022-12-11 |  | DCOLLIN | 2022-11-21 | 2022-11-21 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 22.5167 | 3 | 1355.87 | 1345.01 | 61.77 | -50.91 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22145685300 |  | 501094574 |  | 6724212I | 1313369 |  |  | 566 | EX | ABAND SL | 2621P | BATTERY | 1765 BATTERY ST | 067 | LEX | 2023-01-23 | U126308 | U132823 | 2022-11-21 | 2022-11-21 |  |  | J ENSMINGER | 2022-11-21 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 4.4833 | 2 | 1424.34 | 317.42 | 13.67 | 18.58 | 1074.67 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22145701100 |  | 501299179 |  | 6724212M |  |  |  | 566 | EX | ABAND SL | 2621P | HAYMAKER | 1734 HAYMAKER PY | 067 | LEX | 2022-11-21 | U126308 | U132823 | 2022-11-21 | 2022-11-21 |  |  | J ENSMINGER | 2022-11-21 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 7.5167 | 1 | 1435.1 | 536.63 | 0 | 40.96 | 857.51 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22145727700 |  | 100279311 |  | 6688228K |  |  |  | 565 | EX | RPLC SL/ | 2600B | MCDOWELL | 457 MCDOWELL AV | 073 | FRA | 2022-11-22 | U126309 | U125768 | 2022-11-21 | 2049-12-31 |  |  | JAMIE LYNN | 2022-11-21 | 2022-11-21 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 22.0667 | 3 | 5317.91 | 1597.93 | 0 | 342.17 | 3377.81 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127911600 |  | 500828845 |  | 6712212C | 0253777 |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | ENTERPRISE | 1050 ENTERPRISE DR STE 110 | 067 | LEX | 2022-11-22 | U126308 | U125763 | 2022-08-31 | 2022-12-30 |  |  | J ENSMINGER | 2022-11-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 214.75 | 0 | 0 | 0 | 214.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127911700 |  | 500828846 |  | 6712212C | 0253777 |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | ENTERPRISE | 1050 ENTERPRISE DR STE 115 | 067 | LEX | 2022-11-22 | U126308 | U125763 | 2022-08-31 | 2022-12-30 |  |  | J ENSMINGER | 2022-11-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 214.75 | 0 | 0 | 0 | 214.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127911900 |  | 500826619 |  | 6712212C | 0253777 |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | ENTERPRISE | 1050 ENTERPRISE DR STE 120 | 067 | LEX | 2022-11-22 | U126308 | U125763 | 2022-08-31 | 2022-12-30 |  |  | J ENSMINGER | 2022-11-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 429.5 | 0 | 0 | 0 | 429.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22145708800 |  | 500866191 |  | 6720212M | 0358135 |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | MAIN | 701 E MAIN ST CABLE | 067 | LEX | 2022-11-22 | LSTANFI | U125208 | 2022-11-21 | 2022-11-22 |  |  | LSTANFI | 2022-11-22 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 25.7833 | 3 | 4423.95 | 1505.86 | 241.54 | -91.14 | 2767.69 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22145883800 |  | 500011078 |  | 6720204K |  |  |  | 565 | EX | SERVICE LINE - REPLACE D311068 | 2621P | CROSSEN | 1629 CROSSEN WY | 067 | LEX | 2022-11-23 | U125208 | U132823 | 2022-11-22 | 2022-11-22 | 2022-11-22 |  | TROE | 2022-11-22 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.8333 | 2 | 1052.69 | 640.25 | 304.57 | 37.47 | 70.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22145884600 |  | 100274634 |  | 6684228J | 1313370 |  |  | 565 | EX | SERVICE LINE - REPLACE D221427 | 2621P | 4TH | 322 W 4TH ST | 073 | FRA | 2022-11-28 | U128410 | U132823 | 2022-11-22 | 2022-11-22 | 2022-11-22 |  | CDESPAIN | 2022-11-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 13.95 | 2 | 5180.96 | 819.1 | 359.64 | 47.92 | 3954.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22145886000 |  | 100298626 |  | 6716216O | 1313369 |  |  | 566 | EX | ABAND SL | 2621P | FAIRDALE | 236 FAIRDALE DR | 067 | LEX | 2022-11-22 | U126308 | U132823 | 2022-11-22 | 2022-11-22 |  |  | J ENSMINGER | 2022-11-22 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 12 | 1 | 2593.24 | 854.02 | 47.2 | 832.1 | 859.92 | 0 | 0 | 0
KY | KY - WEST | 2623 | 04592246900 |  | 100276491 |  | 6684228 | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 2 | 2621P | HOLMES | 440 HOLMES ST | 073 | FRA | 2022-11-23 | U126309 | RPOLLY | 2004-11-11 | 2022-07-01 | 2022-12-31 |  | JAMIE LYNN | 2022-11-23 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 2.6333 | 1 | 1754.92 | 160.74 | 0 | 39.04 | 1555.14 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21026994100 |  |  |  | 6716208C | 2176780 | U461383 |  | 558 | EX | RETIRE 14,600 - 4"CI/BSLP MAIN | 2600B | STATE | STATE ST | 067 | LEX | 2022-12-01 | U128132 | U461383 | 2021-01-06 | 2022-12-30 | 2022-12-31 | 2022-11-16 | JOSHUA COX | 2022-11-23 |  | 2022-05-18 | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP9941 | AMRCB |  | 100 | 055832210269941 | 2.6333 | 0 | 269.51 | 179.03 | 0 | 10.48 | 80 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883233600 |  | 500530984 |  | 6724208B | 9614946 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MARBLEHEAD | 868 MARBLEHEAD DR | 067 | LEX | 2022-11-23 | U126308 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-11-23 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 859.92 | 0 | 0 | 0 | 859.92 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883332100 |  | 500021307 |  | 6688228P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEESTOWN | 1022 LEESTOWN LN F | 073 | FRA | 2022-11-23 | U126309 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JAMIE LYNN | 2022-11-23 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 4.45 | 1 | 1409.37 | 271.96 | 0 | 66.05 | 1071.36 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22145915900 |  | 500022426 |  | 6696212K | 1313370 |  |  | 565 | EX | REPLACE SL | 2621P | CLIFTON | 228 CLIFTON RD | 239 | VER | 2022-11-23 | U461322 | U132823 | 2022-11-22 | 2022-11-22 |  |  | STEVE CANOY | 2022-11-23 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.5167 | 1 | 2642.96 | 434.14 | 0 | 449.08 | 1759.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22145927900 |  | 500028449 |  | 6712208M | 1313369 |  |  | 566 | EX | ABANDON SL | 2621P | PALOMAR | 4140 PALOMAR BV | 067 | LEX | 2022-11-23 | U126308 | U132823 | 2022-11-22 | 2022-11-22 |  |  | J ENSMINGER | 2022-11-23 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 9 | 1 | 1537.89 | 640.49 | 0 | 37.48 | 859.92 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22146172400 |  | 100422233 |  | 6680224H | 1313370 |  |  | 566 | VO | ABAND SL | 2621P | WILDWOOD | 213 WILDWOOD PL 1 | 073 | FRA | 2023-01-20 |  | U132823 | 2022-11-23 | 2022-11-23 |  |  | STEVE CANOY | 2022-11-23 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26230043 | 0.88333 | 1 | 119.54 | 58.75 | 0 | 60.79 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 13113068300 |  | 100269431 |  | 6736252I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAIN | 426 N MAIN ST | 097 | CYN | 2022-11-28 | U129673 | U123694 | 2013-01-18 | 2022-07-01 | 2022-12-31 |  | ALEX WILLIAMSON | 2022-11-28 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1631.21 | 0 | 0 | 0 | 1631.21 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 14270130100 |  | 100270837 |  | 6736248A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | OLD LAIR | 301 OLD LAIR RD C | 097 | CYN | 2022-11-28 | U129673 | U122906 | 2014-12-11 | 2022-07-01 | 2022-12-31 |  | ALEX WILLIAMSON | 2022-11-28 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 337.05 | 0 | 0 | 0 | 337.05 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21883082200 |  | 100271029 |  | NEW |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | SPARKS | 540 SPARKS RD | 023 | BRO | 2022-11-28 | U461478 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DAVID STAGGS | 2022-11-28 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 4 | 1 | 766 | 241.85 | 0 | 14.15 | 510 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21883100500 |  | 100271032 |  | NEW |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | WILLOW NEAVE | 619 WILLOW NEAVE RD | 023 | BRO | 2022-11-28 | U461478 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DAVID STAGGS | 2022-11-28 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 4 | 1 | 766 | 241.85 | 0 | 14.15 | 510 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883138500 |  | 100348888 |  | 6748208M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WASHINGTON | 332 E WASHINGTON ST | 049 | WIN | 2022-11-29 | U126284 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JOSH PASLEY | 2022-11-28 | 2022-11-28 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3 | 1 | 2039.27 | 200.77 | 0 | 207.29 | 1631.21 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883276800 |  | 100435557 |  | 6748204J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 2 | 2621P | MUDDY CREEK | 2416 MUDDY CREEK RD TR1 | 049 | WIN | 2022-11-28 | U126602 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DEREK PAYTON | 2022-11-28 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 3115.53 | 480.88 | 0 | 28.12 | 2606.53 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883293100 |  | 100352488 |  | 6748204E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 2 | 2621P | MUDDY CREEK | 1919 MUDDY CREEK RD | 049 | WIN | 2022-11-28 | U129731 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-11-28 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 2548.88 | 499.72 | 0 | 119.38 | 1929.78 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22102160000 |  | 100270858 |  | 6736248A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ELMARCH | 412 S ELMARCH AV | 097 | CYN | 2022-11-28 | U129673 | U125208 | 2022-05-19 | 2049-12-31 |  |  | ALEX WILLIAMSON | 2022-11-28 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129006900 |  | 100349854 |  | 6744204D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FRENCH | 40 FRENCH AV | 049 | WIN | 2022-11-29 | U129722 | U130722 | 2022-09-05 | 2022-12-30 |  |  | M YOUNG | 2022-11-28 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1628.56 | 0 | 0 | 0 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129025200 |  | 100356573 |  | 7260276A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | FLEMING | 782 FLEMING RD | 161 | MAY | 2022-11-30 | U461478 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-11-28 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1 | 1360 | 0 | 0 | 0 | 1360 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129025700 |  | 100357051 |  | 7252276H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | OLD MAIN | 1906 OLD MAIN ST | 161 | MAY | 2022-11-30 | U126286 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-11-28 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 10.6167 | 2 | 2162.28 | 730.25 | 0 | 72.03 | 1360 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129059600 |  | 100429870 |  | 6732252P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | POPLAR | 210 N POPLAR ST | 097 | CYN | 2022-11-28 | U129673 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-11-28 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10 | 1 | 2414.26 | 633.32 | 0 | 149.73 | 1631.21 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129084300 |  | 100336902 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | JOHNSON | 442 JOHNSON AV | 067 | LEX | 2022-12-08 | U125208 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KKINDER | 2022-11-28 | 2022-11-01 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.4167 | 3 | 1004.72 | 825.8 | 130.63 | 48.29 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22136125500 |  | 100353094 |  | 6744208P | 1855043 |  |  | 566 | EX | ABANDON SL - SOII/INSIDE | 2621P | BROADWAY | 23 W BROADWAY ST | 049 | WIN | 2022-11-29 | U129722 | U130868 | 2022-09-30 | 2022-12-30 | 2022-12-31 |  | M YOUNG | 2022-11-28 | 2022-11-01 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.7333 | 3 | 2299.13 | 545.84 | 0 | 122.08 | 1631.21 | 0 | 0 | 0
KY | KY - EAST | 2682 | 22145147300 |  | 100426644 |  | SW50 |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2633S | CORNETT | 161 CORNETT RD | 119 | HIN | 2022-11-28 | U130172 | U132002 | 2022-11-17 | 2022-12-01 | 2022-12-17 |  | JOHN HOWARD | 2022-11-28 |  |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 6.9667 | 1 | 516.78 | 488.22 | 0 | 28.56 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22146381100 |  | 501280234 |  | 6716204C |  |  |  | 566 | EX | ABANDON SL -I/I/LGCY | 2600B | LAREDO | 414 LAREDO CT | 067 | LEX | 2022-11-28 | U127206 | U134723 | 2022-11-28 | 2023-12-29 |  |  | JUSTIN HOBBS | 2022-11-28 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 1149.69 | 477.86 | 0 | 27.95 | 643.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22146386900 |  | 100422232 |  | 6680224H |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | WILDWOOD | 213 WILDWOOD PL 2 | 073 | FRA | 2022-11-28 | U128816 | U129939 | 2022-11-28 | 2022-11-28 |  |  | OLIVER MAYNARD | 2022-11-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.5667 | 1 | 3921.29 | 285.99 | 283.61 | 16.75 | 3334.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22146419300 |  | 500232015 |  | 6716208B |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2600B | WALLER | 366 WALLER AV 211 | 067 | LEX | 2022-11-28 | U127206 | U134723 | 2022-11-28 | 2023-12-29 |  |  | JUSTIN HOBBS | 2022-11-28 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2623 | 03533960700 |  | 100281746 |  | 6712232O | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | HICKMAN | 332 HICKMAN ST | 209 | GEO | 2022-11-29 | U129731 | DMCCULL | 2003-03-18 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-11-29 | 2020-04-24 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 32 | 7 | 3543.45 | 1688.45 | 0 | 294.12 | 1560.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 05599123800 |  | 100281904 |  | 6712232O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MIDLAND | 146 MIDLAND AV | 209 | GEO | 2022-11-29 | U129731 | SSUTHER | 2005-01-21 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-11-29 | 2020-05-04 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 12.75 | 4 | 3220.2 | 752.77 | 0 | 287.25 | 2180.18 | 0 | 0 | 0
KY | KY - WEST | 2623 | 05611184800 |  | 100282554 |  | 6712228B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HAMILTON | 135 S HAMILTON ST DN | 209 | GEO | 2022-11-29 | U129722 | SSUTHER | 2005-05-17 | 2020-12-23 |  |  | M YOUNG | 2022-11-29 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - CENTRAL | 2629 | 08727747900 |  | 500345156 |  | 6736180G | 9403769 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | RED HOUSE | 942 RED HOUSE RD | 151 | RIC | 2022-11-29 | U126284 | RPOLLY | 2008-04-16 | 2022-07-01 | 2022-12-31 |  | JOSH PASLEY | 2022-11-29 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.6667 | 1 | 2397.11 | 378.17 | 0 | 390.38 | 1628.56 | 0 | 0 | 0
KY | KY - WEST | 2623 | 11920172500 |  | 100281728 |  | 6712228B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | HAMILTON | 802 N HAMILTON ST | 209 | GEO | 2022-11-29 | U129722 | U124449 | 2011-08-15 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-11-29 | 2020-04-22 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 1.4833 | 2 | 3569.19 | 78.58 | 0 | 82.6 | 3408.01 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12998731500 |  | 100452815 |  | X-1110-38 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | STACY LANE | 2202 STACY LANE RD | 065 | IRV | 2022-11-29 | U126285 | DMCCULL | 2012-11-15 | 2022-07-01 | 2022-12-31 |  | DDAVIS | 2022-11-29 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.5 | 1 | 4639.9 | 543.23 | 0 | 585.82 | 3510.85 | 0 | 0 | 0
KY | KY - WEST | 2621 | 14234566600 |  | 100424481 |  | 6720216L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | PARKSIDE | 551 PARKSIDE DR GYM | 067 | LEX | 2022-11-29 | U127206 | U127104 | 2014-07-15 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-11-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 2554.63 | 477.85 | 0 | 27.95 | 2048.83 | 0 | 0 | 0
KY | KY - WEST | 2623 | 17569036600 |  | 500694165 |  | 6712232K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CARRIAGE | 106 CARRIAGE LN LT3C | 209 | GEO | 2022-11-29 | U129673 | U125765 | 2017-12-20 | 2022-07-01 | 2022-12-31 |  | ALEX WILLIAMSON | 2022-11-29 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.11667 | 1 | 415.94 | 8.24 | 0 | 0.49 | 407.21 | 0 | 0 | 0
KY | KY - WEST | 2623 | 17569039700 |  | 500755698 |  | 6708232H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NEW HAVEN PATH | 100 NEW HAVEN PATH 6 | 209 | GEO | 2022-11-29 | U129673 | U125765 | 2017-12-20 | 2022-07-01 | 2022-12-31 |  | ALEX WILLIAMSON | 2022-11-29 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 10.8667 | 1 | 1134.54 | 687.13 | 0 | 40.2 | 407.21 | 0 | 0 | 0
KY | KY - WEST | 2623 | 17569039800 |  | 500755699 |  | V-904-28 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NEW HAVEN PATH | 100 NEW HAVEN PATH 7 | 209 | GEO | 2022-11-29 | U129673 | U125765 | 2017-12-20 | 2006-05-02 |  |  | ALEX WILLIAMSON | 2022-11-29 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2623 | 17569039900 |  | 500755700 |  | V-904-28 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NEW HAVEN PATH | 100 NEW HAVEN PATH 8 | 209 | GEO | 2022-11-29 | U129673 | U125765 | 2017-12-20 | 2006-05-02 |  |  | ALEX WILLIAMSON | 2022-11-29 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2623 | 17569040000 |  | 500755701 |  | V-904-28 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NEW HAVEN PATH | 100 NEW HAVEN PATH 9 | 209 | GEO | 2022-11-29 | U129673 | U125765 | 2017-12-20 | 2006-05-02 |  |  | ALEX WILLIAMSON | 2022-11-29 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2623 | 17569040100 |  | 500755702 |  | V-904-28 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NEW HAVEN PATH | 100 NEW HAVEN PATH 10 | 209 | GEO | 2022-11-29 | U129673 | U125765 | 2017-12-20 | 2006-05-02 |  |  | ALEX WILLIAMSON | 2022-11-29 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2623 | 17569040200 |  | 500755703 |  | V-904-28 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NEW HAVEN PATH | 100 NEW HAVEN PATH 11 | 209 | GEO | 2022-11-29 | U129673 | U125765 | 2017-12-20 | 2006-05-02 |  |  | ALEX WILLIAMSON | 2022-11-29 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2623 | 17569040300 |  | 500755704 |  | V-904-28 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NEW HAVEN PATH | 100 NEW HAVEN PATH 12 | 209 | GEO | 2022-11-29 | U129673 | U125765 | 2017-12-20 | 2006-05-02 |  |  | ALEX WILLIAMSON | 2022-11-29 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - CENTRAL | 2629 | 20853263400 |  | 100425579 |  | 6744208K | 2293467 |  |  | 566 | EX | ABANDON SL W/22-0262347-00 | 2600B | LEXINGTON | 1107 W LEXINGTON AV | 049 | WIN | 2022-11-30 | U126603 | U125208 | 2020-10-15 | 2022-07-01 | 2022-12-31 |  | SHAWN DENNIS | 2022-11-29 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 7.1167 | 1 | 4418.04 | 478.67 | 0 | 108.34 | 3831.03 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883091500 |  | 100426812 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2633S | CLARK | 88 W CLARK DR | 071 | PRE | 2022-11-29 | U124015 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | ORA SLONE | 2022-11-29 |  |  | B | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 2.5833 | 1 | 2006.22 | 156.92 | 0 | 38.5 | 1810.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883173400 |  | 100332961 |  | 6732196T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | OLD RICHMOND | 7959 OLD RICHMOND RD | 067 | LEX | 2022-11-29 | U126308 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-11-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.5 | 2 | 3819.94 | 970.67 | 0 | 451.65 | 2397.62 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883324300 |  | 100282317 |  | 6712232N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | HAMILTON | 333 N HAMILTON ST | 209 | GEO | 2022-11-29 | U129722 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-11-29 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2621 | 21960243100 |  | 100320955 |  | 6720212M | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | WOODLAND | 223 WOODLAND AV | 067 | LEX | 2022-12-02 | U461375 | U134723 | 2021-12-17 | 2022-12-30 |  |  | LARRY BROWN | 2022-11-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1967.78 | 0 | 0 | 0 | 1967.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960243200 |  | 100320957 |  | 6720212M | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | WOODLAND | 235 WOODLAND AV | 067 | LEX | 2022-12-02 | U461375 | U134723 | 2021-12-17 | 2022-12-30 |  |  | LARRY BROWN | 2022-11-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4637.03 | 0 | 0 | 0 | 4637.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960251600 |  | 100321619 |  | 6716212P | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | ROSE | 320 ROSE ST 3-2FFT | 067 | LEX | 2022-11-29 | U126309 | U134723 | 2021-12-17 | 2022-12-30 |  |  | JAMIE LYNN | 2022-11-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.6333 | 1 | 4089.47 | 161.93 | 0 | 9.47 | 3918.07 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026234800 |  |  |  | 6744208K | 2293467 | U461383 |  | 560 | EX | RETIRE 75' OF 3"BSMP MAIN | 2600B | LEXINGTON | 1107 W LEXINGTON AV | 049 | WIN | 2022-12-02 | U128132 | U461383 | 2022-11-08 | 2022-12-30 | 2022-12-31 | 2022-11-29 | EGOINS | 2022-11-29 | 2022-12-01 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00560 | 3200560 |  |  | WP2348 | AMRCB |  | 100 | 056032220262348 | 1.2333 | 0 | 114.9 | 94.01 | 0 | 20.89 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129020000 |  | 100411658 |  | 6688228F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | THOMPSON | 118 THOMPSON ST | 073 | FRA | 2023-01-18 | U126308 | U130722 | 2022-09-05 | 2022-12-30 |  |  | J ENSMINGER | 2022-11-29 | 2022-11-28 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 6.9167 | 2 | 2270.37 | 461.41 | 269.24 | 255.12 | 1284.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129025400 |  | 100355138 |  | 7260280M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | LEXINGTON | 303 LEXINGTON ST | 161 | MAY | 2022-11-30 | U461478 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-11-29 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1 | 2040.4 | 0 | 0 | 0 | 2040.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129055200 |  | 501203685 |  | 6708228D | 1641980 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ANNE JENNINGS | 144 ANNE JENNINGS WY | 209 | GEO | 2022-11-29 | U129722 | U130722 | 2022-09-05 | 2022-12-30 |  |  | M YOUNG | 2022-11-29 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 9 | 1 | 2175.23 | 557.93 | 0 | 134.05 | 1483.25 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129055400 |  | 100281475 |  | 6712232N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BROADWAY | 420 N BROADWAY ST | 209 | GEO | 2022-11-29 | U129673 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-11-29 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.016667 | 1 | 1687.44 | 1.27 | 0 | 0.08 | 1686.09 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129060600 |  | 100356044 |  | 7260280M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | 5TH | 911 E 5TH ST | 161 | MAY | 2022-11-30 | U461478 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-11-29 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1 | 2048.8 | 0 | 0 | 0 | 2048.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129061800 |  | 100355970 |  | 7260280N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | PELHAM | 420 PELHAM ST | 161 | MAY | 2022-11-30 | U461478 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-11-29 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 8 | 1 | 1688.1 | 555.6 | 0 | 32.5 | 1100 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129062900 |  | 100355875 |  | 7260280N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | WOOD | 508 WOOD ST | 161 | MAY | 2022-11-30 | U461478 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ED FOX | 2022-11-29 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 4.4333 | 1 | 1929.26 | 296.89 | 0 | 17.37 | 1615 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129063000 |  | 100355923 |  | 7260276B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | WOOD | 515 WOOD ST | 161 | MAY | 2022-11-30 | U461478 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ED FOX | 2022-11-29 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 11.5667 | 2 | 2166.89 | 724.2 | 0 | 82.69 | 1360 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129081400 |  | 100333948 |  | 6720212K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LIBERTY | 932 LIBERTY RD | 067 | LEX | 2022-11-29 | U930915 | U130722 | 2022-09-05 | 2022-12-30 |  |  | KKINDER | 2022-11-29 | 2022-11-01 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 31.1 | 7 | 2656.22 | 1882.93 | 130.63 | 110.16 | 532.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22138629800 |  | 100465764 |  | 6732212O |  |  |  | 565 | EX | SERVICE LINE - REPLACE D304055 | 2621P | EASTPOINT | 2584 EASTPOINT DR | 067 | LEX | 2022-11-30 | UIPBOT21 | U125208 | 2022-10-12 | 2023-04-10 | 2024-10-31 |  | LSTANFI | 2022-11-29 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 30.4167 | 4 | 2035.69 | 1837.1 | 0 | 108.39 | 90.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22142553900 |  | 500015793 |  | 6764171K |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | MAIN | 314 MAIN ST | 065 | IRV | 2022-12-08 | U125208 | U129939 | 2022-11-02 | 2022-11-02 |  |  | DENNING | 2022-11-29 | 2022-11-02 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26290031 | 6.2333 | 2 | 1122.27 | 466.56 | 9.12 | 27.29 | 619.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22145939800 |  | 100321891 |  | 6716212P |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | PENNSYLVANIA | 450 PENNSYLVANIA AV UK 122 | 067 | LEX | 2022-11-30 | U128711 | U132002 | 2022-11-22 | 2022-12-06 | 2022-12-22 |  | HMCKUNE | 2022-11-29 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 22.2167 | 3 | 3064.17 | 1079.72 | 7.74 | 63.16 | 1913.55 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22146416900 |  | 100271978 |  | 6684228K |  |  |  | 565 | EX | SERVICE LINE - REPLACE W/309 | 2621P | STANLEY | 301 STANLEY ST | 073 | FRA | 2022-11-29 | DCOLLIN | U125208 | 2022-11-28 | 2022-11-29 | 2022-12-19 |  | DCOLLIN | 2022-11-29 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 29.1167 | 4 | 2551.26 | 1800.2 | 357.34 | -240.28 | 634 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22146539700 |  | 100345460 |  | 6696212H |  |  |  | 565 | EX | REPLACE SL | 2600B | LOCUST | 252 N LOCUST ST A | 239 | VER | 2022-11-29 | U128816 | U134723 | 2022-11-29 | 2023-12-29 |  |  | OLIVER MAYNARD | 2022-11-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 3.75 | 1 | 3991.52 | 234.19 | 717.83 | 13.7 | 3025.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22146540000 |  | 100345461 |  | 6696212H |  |  |  | 566 | EX | ABANDON SL | 2600B | LOCUST | 252 N LOCUST ST B | 239 | VER | 2022-11-29 | U128816 | U134723 | 2022-11-29 | 2023-12-29 |  |  | OLIVER MAYNARD | 2022-11-29 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.66667 | 1 | 44.31 | 41.86 | 0 | 2.45 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22146540400 |  | 500063777 |  | 6696212H |  |  |  | 566 | EX | ABANDON SL | 2600B | LOCUST | 252 N LOCUST ST C | 239 | VER | 2022-11-29 | U128816 | U134723 | 2022-11-29 | 2023-12-29 |  |  | OLIVER MAYNARD | 2022-11-29 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 3.5833 | 1 | 236.61 | 223.53 | 0 | 13.08 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22979030300 |  | 100278862 |  | 6688228D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 2 | 2621P | GEORGETOWN | GEORGETOWN RD | 073 | FRA | 2022-11-29 | U126308 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | J ENSMINGER | 2022-11-29 | 2022-10-06 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 4.6833 | 2 | 1597.45 | 320.24 | 0 | 312.03 | 965.18 | 0 | 0 | 0
KY | KY - WEST | 2623 | 07680932100 |  | 100345185 |  | V-921-35 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | FRANKFORT | 140 FRANKFORT ST | 239 | VER | 2022-11-30 | U126602 | SSUTHER | 2007-03-29 | 2022-07-01 | 2022-12-31 |  | DEREK PAYTON | 2022-11-30 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 10 | 1 | 4256.88 | 601.08 | 0 | 35.16 | 3620.64 | 0 | 0 | 0
KY | KY - EAST | 2633 | 07685214200 |  | 100264727 | 22 | X1815-3 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NEW CAMP | 385 NEW CAMP RD | 195 | S W | 2022-11-30 | U124015 | LDAVIS | 2007-05-01 | 2022-07-01 | 2022-12-31 |  | ORA SLONE | 2022-11-30 | 2022-11-30 |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.6333 | 1 | 4701.58 | 337.4 | 0 | 58.5 | 4305.68 | 0 | 0 | 0
KY | KY - WEST | 2623 | 08723829900 |  | 100281179 | 05 | ? |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 2 | 2621P | OLD FRANKFORT (KY1681) | 2641 OLD FRANKFORT (KY1681) PK | 239 | MID | 2022-11-30 | U126308 | JCOLYER | 2008-03-17 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-11-30 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 4.5 | 1 | 338.94 | 320.22 | 0 | 18.72 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 10869052600 |  | 100344887 |  | V91235 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WALNUT | 124 WALNUT ST | 239 | MID | 2022-11-30 | U126602 | U906314 | 2010-11-18 | 2022-07-01 | 2022-12-31 |  | DEREK PAYTON | 2022-11-30 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2623 | 16383098400 |  | 501057464 |  | 6700212I | 0992837 |  |  | 566 | EX | ABANDON SL - NON COMPLIANT | 2621P | WOODFORD | 480 WOODFORD PZ STE F | 239 | VER | 2022-11-30 | DCOLLIN | U125208 | 2016-02-09 | 2022-07-14 | 2022-09-14 |  | DCOLLIN | 2022-11-30 | 2022-09-13 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26230043 | 17.85 | 5 | 1313.47 | 1169.53 | 0 | -276.58 | 420.52 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18576412600 |  | 100285399 |  | 6764176P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BROADWAY | 263 BROADWAY ST | 065 | IRV | 2022-12-01 | U126285 | U125765 | 2018-01-22 | 2019-12-31 |  |  | DDAVIS | 2022-11-30 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.75 | 1 | 3521.94 | 559.21 | 0 | 603.04 | 2359.69 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883278600 |  | 100264765 |  | 7384168K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NEW CAMP | 36 NEW CAMP RD | 195 | S W | 2022-11-30 | U124015 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | ORA SLONE | 2022-11-30 | 2022-11-30 |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.3 | 1 | 1506.14 | 78.49 | 0 | 19.25 | 1408.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883328800 |  | 500468604 |  | 6684228I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 2 | 2621P | KIMBERLY | KIMBERLY DR LT7 | 073 | FRA | 2022-11-30 | U126308 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-11-30 | 2022-10-06 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.18333 | 1 | 965.18 | 0 | 0 | 0 | 965.18 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883330600 |  | 500206025 |  | 6692224B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CINNAMON-TEAL | 103 CINNAMON-TEAL CT LT70 | 073 | FRA | 2022-11-30 | U126308 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-11-30 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 4.5 | 1 | 983.19 | 320.22 | 0 | 18.72 | 644.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026234700 |  |  |  | 6744208K | 2293467 | U461383 |  | 559 | EX | INSTALL 3" STOPPLE FITTING | 2600B | LEXINGTON | 1107 W LEXINGTON AV | 049 | WIN | 2022-12-03 | U128132 | U461383 | 2022-11-08 | 2022-12-28 | 2022-12-31 | 2022-11-29 | SHAWN DENNIS | 2022-11-30 | 2022-11-29 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00559 | 3200559 |  |  | WP2347 | AMRCB |  | 100 | 055932220262347 | 21.6333 | 0 | 7929.81 | 1609.02 | 704.79 | 372.48 | 4852.93 | 0 | 10.28 | 380.31
KY | KY - CENTRAL | 2629 | 22026240700 |  |  |  | 6760172J | 2074684 | U128885 |  | 577 | EX | INSTALL FENCE FOR NEW LAND | 2629M | DUG HILL | 724 DUG HILL RD | 065 | IRV | 2023-05-08 | U123258 | U128885 | 2022-11-28 | 2023-12-28 | 2023-12-31 | 2022-11-30 | JOSH MULLINS | 2022-11-30 | 2022-12-27 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00577 | 3200577 |  |  | WP2407 |  |  | 100 | 057732220262407 | 19.35 | 3 | 63926.63 | 1435.96 | 0 | 585.38 | 57325.97 | 0 | 171.93 | 4407.39
KY | KY - WEST | 2621 | 22026240900 |  |  |  | 6716212O | 2176780 | U461383 |  | 560 | EX | PAPER ONLY EXECUTE | 2600B | PRESS | PRESS AV | 067 | LEX | 2022-12-01 | U128132 | U461383 | 2022-11-30 | 2022-12-30 | 2022-12-31 | 2022-11-16 | JOSHUA COX | 2022-11-30 |  | 2022-05-18 | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00560 | 3200560 |  |  | WP2409 |  |  | 100 | 056032220262409 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22127353100 |  | 100282161 |  | 6712228B |  |  |  | 566 | EX | PAPER ABANDON | 2621P | MULBERRY | 232 N MULBERRY ST UP | 209 | GEO | 2022-11-30 | U129731 | U125208 | 2022-08-29 | 2022-08-29 |  |  | F.GOINS | 2022-11-30 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 780.44 | 0 | 0 | 0 | 780.44 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129005300 |  | 100438368 |  | 6696212L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CURRY | 204 CURRY CT 1FR | 239 | VER | 2022-11-30 | U126532 | U130722 | 2022-09-05 | 2022-12-30 |  |  | LESLIE SHARON | 2022-11-30 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2623 | 22129055700 |  | 501188648 |  | 6716232I | 1853242 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DUNN | 136 DUNN CR | 209 | GEO | 2022-11-30 | U129722 | U130722 | 2022-09-05 | 2022-12-30 |  |  | M YOUNG | 2022-11-30 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8 | 1 | 2248.93 | 495.92 | 0 | 119.15 | 1633.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129055800 |  | 501188659 |  | 6716232I | 1853242 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DUNN | 152 DUNN CR | 209 | GEO | 2022-11-30 | U129722 | U130722 | 2022-09-05 | 2022-12-30 |  |  | M YOUNG | 2022-11-30 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1483.25 | 0 | 0 | 0 | 1483.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129061200 |  | 100355784 |  | 7260276B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | CENTRAL | 613 CENTRAL AV | 161 | MAY | 2022-11-30 | U461478 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ED FOX | 2022-11-30 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 3.4 | 1 | 1640.08 | 228.39 | 0 | 51.69 | 1360 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129061400 |  | 100355627 |  | 7260276B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | FLORENCE | 618 FLORENCE ST | 161 | MAY | 2022-11-30 | U461478 | U130722 | 2022-09-05 | 2022-12-30 |  |  | TYLER ALLISON | 2022-11-30 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 16 | 2 | 2566.58 | 1143.41 | 0 | 63.17 | 1360 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129062800 |  | 100355843 |  | 7260280N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | WOOD | 410 WOOD ST | 161 | MAY | 2022-11-30 | U461478 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ED FOX | 2022-11-30 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 4.6 | 1 | 1687.09 | 309.02 | 0 | 18.07 | 1360 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129071400 |  | 100242240 |  | 7356252H |  |  |  | 566 | VO | ABANDON SL - PEND CN 11-30-22 | 2621P | HORSE BRANCH | 420 HORSE BRANCH RD | 019 | CAT | 2022-12-14 |  | U130722 | 2022-09-05 | 2022-12-30 |  |  | BCRUM | 2022-11-30 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1
KY | KY - WEST | 2621 | 22129086600 |  | 100454772 |  | 6712208F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LYON | 3321 LYON DR | 067 | LEX | 2022-11-30 | U126308 | U130722 | 2022-09-05 | 2022-12-30 |  |  | J ENSMINGER | 2022-11-30 | 2022-10-21 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.05 | 3 | 4374.81 | 750.8 | 0 | 343.66 | 3280.35 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129117600 |  | 100438370 |  | 6696212L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CURRY | 204 CURRY CT 3-2FR | 239 | VER | 2022-11-30 | U126532 | U125208 | 2022-09-06 | 2022-12-30 |  |  | LESLIE SHARON | 2022-11-30 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2623 | 22129117700 |  | 100438371 |  | 6696212L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CURRY | 204 CURRY CT 4-2FL | 239 | VER | 2022-11-30 | U126532 | U125208 | 2022-09-06 | 2022-12-30 |  |  | LESLIE SHARON | 2022-11-30 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 643.88 | 0 | 0 | 0 | 643.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22134915500 |  | 100459554 |  | 6688232O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | STEADMANTOWN | 1880 STEADMANTOWN LN | 073 | FRA | 2022-11-30 | U124003 | U130722 | 2022-09-27 | 2022-12-30 |  |  | BPULLIAM/FISHEL | 2022-11-30 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 4088.24 | 0 | 0 | 0 | 4088.24 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22142995900 |  | 100441431 |  | 6700212E |  |  |  | 565 | EX | REPLACE SL | 2621P | YELLOW JACKET | 228 YELLOW JACKET DR | 239 | VER | 2022-11-30 | U128816 | U124449 | 2022-11-04 | 2022-11-04 |  |  | OLIVER MAYNARD | 2022-11-30 | 2022-11-04 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 22 | 2 | 9355.13 | 1405.31 | 706.08 | 82.21 | 7161.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22144258200 |  | 501139192 |  | 6724212M | 1316677 |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HADDRELL | 1028 HADDRELL PT | 067 | LEX | 2022-11-30 | U129673 | U123119 | 2022-11-14 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-11-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 10 | 1 | 5324.38 | 633.3 | 0 | 98.45 | 4592.63 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22144339000 |  | 100286272 |  | 6764172G |  |  |  | 566 | EX | ABANDON SL -I/I/LGCY | 2600B | CRABTREE | 70 CRABTREE LN | 065 | IRV | 2022-11-30 | U126285 | U134723 | 2022-11-14 | 2022-12-30 |  |  | DDAVIS | 2022-11-30 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1561.2 | 0 | 0 | 0 | 1561.2 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22145710100 |  | 100452062 |  | 6696212H |  |  |  | 566 | EX | ABANDN SL/ | 2600B | FRANKFORT | 140< FRANKFORT ST | 239 | VER | 2022-11-30 | U126602 | U125763 | 2022-11-21 | 2022-12-30 |  |  | DEREK PAYTON | 2022-11-30 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - CENTRAL | 2629 | 22146822100 |  | 100270224 |  | 6736252M |  |  |  | 565 | EX | REINSTALL SL - WORK AS 563 | 2600B | BRIDGE | 105 E BRIDGE ST | 097 | CYN | 2022-11-30 | U126284 | U134723 | 2022-11-30 | 2022-12-13 | 2022-12-13 |  | JOSH PASLEY | 2022-11-30 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26290032 | 12.5 | 1 | 6961.81 | 836.6 | 0 | 863.68 | 5261.53 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22979025500 |  | 100264585 |  | 7384168B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FALLS BRANCH | 77 FALLS BRANCH RD | 195 | S W | 2022-11-30 | U124015 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | ORA SLONE | 2022-11-30 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.0667 | 1 | 1892.2 | 186.57 | 0 | 45.73 | 1659.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22994321200 |  | 500375158 |  | 7256280O | 2180424 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | FORT HILL | 703 FORT HILL RD | 161 | MAY | 2022-11-30 | U461478 | U134723 | 2022-04-19 | 2022-12-30 |  |  | TYLER ALLISON | 2022-11-30 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26320043 | 16 | 2 | 2490.44 | 1071.49 | 0 | 58.95 | 1360 | 0 | 0 | 0
KY | KY - WEST | 2621 | 00455704400 |  | 100332946 |  | 600000000 | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 2 | 2621P | WALNUT HILL | 750 WALNUT HILL RD | 067 | LEX | 2022-12-01 | U126308 | DMCCULL | 2000-12-28 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-12-01 | 2022-10-04 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.9833 | 4 | 1971.18 | 1021.77 | 0 | 53.61 | 895.8 | 0 | 0 | 0
KY | KY - EAST | 2633 | 07673013500 |  | 100264591 | 13 | X1810-33 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SR292 | 3073 SR292 W | 195 | S W | 2022-12-01 | U124015 | CESTEP | 2007-01-19 | 2022-07-01 | 2022-12-31 |  | ORA SLONE | 2022-12-01 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.8833 | 1 | 780.95 | 144.18 | 0 | 33.17 | 603.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07679106800 |  | 100453540 |  | V-930-41 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NAKOMI | 716 NAKOMI DR | 067 | LEX | 2022-12-01 | U127206 | DMCCULL | 2007-03-15 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-12-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1708.57 | 0 | 0 | 0 | 1708.57 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 10860732000 |  | 100285016 |  | 6764176B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WINCHESTER | 1960 WINCHESTER RD APT 1 | 065 | IRV | 2022-12-01 | U126285 | DMCCULL | 2010-09-16 | 2022-11-17 | 2022-12-31 |  | DDAVIS | 2022-12-01 | 2022-06-06 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 38.65 | 5 | 11800.31 | 2468.74 | 0 | 1204.84 | 8126.73 | 0 | 0 | 0
KY | KY - EAST | 2633 | 11909073100 |  | 100266542 |  | 7360152A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAYO | 5079 N MAYO TL | 195 | BLA | 2022-12-01 | U124015 | U906631 | 2011-05-31 | 2022-07-01 | 2022-12-31 |  | ORA SLONE | 2022-12-01 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.55 | 1 | 2509.63 | 410.25 | 0 | 67.26 | 2032.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11909718700 |  | 100299790 |  | V-925/37 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | FORBES | 138 S FORBES RD 2F | 067 | LEX | 2022-12-01 | U126308 | U123933 | 2011-06-02 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-12-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 214.75 | 0 | 0 | 0 | 214.75 | 0 | 0 | 0
KY | KY - WEST | 2623 | 15283224200 |  | 100280821 |  | 6688228E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 2 | 2621P | MAIN | 529 E MAIN ST | 073 | FRA | 2022-12-01 | U129722 | U128293 | 2015-01-30 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-12-01 | 2022-10-04 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 3.15 | 2 | 114.41 | 107.99 | 0 | 6.42 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18634505100 |  | 100272076 |  | 6684228K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LOGAN | 412 LOGAN ST 1F | 073 | FRA | 2022-12-01 | U129722 | U125208 | 2018-08-13 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-12-01 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 9 | 1 | 3522.54 | 656.52 | 0 | 153.15 | 2712.87 | 0 | 0 | 0
KY | KY - WEST | 2621 | 20826419000 |  | 100298217 |  | 6716212H | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE-PLANT | 2621D | BROADWAY | 157 N BROADWAY ST | 067 | LEX | 2022-12-01 | LSTANFI | AOC SYST | 2020-07-10 | 2020-12-23 | 2021-12-31 |  | LSTANFI | 2022-12-01 | 2022-06-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 26.9333 | 8 | 2695.94 | 1751.44 | 224.49 | 312.71 | 407.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 20845440400 |  | 100328045 |  | 6720208A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CATALPA | 228 CATALPA RD FURN | 067 | LEX | 2022-12-01 | U127206 | U120245 | 2020-09-17 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-12-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 492.07 | 0 | 0 | 0 | 492.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883070500 |  | 100292665 |  | 6720216J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CAMERON | 1709 CAMERON CT | 067 | LEX | 2022-12-01 | U129731 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-12-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1853.07 | 0 | 0 | 0 | 1853.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883184900 |  | 500679235 |  | 6716204H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | OLD TATES CRK | 3752 OLD TATES CRK PK | 067 | LEX | 2022-12-01 | U129731 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-12-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 2948.38 | 571.89 | 0 | 135.53 | 2240.96 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883216700 |  | 100430630 |  | 7360156T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | COWPEN | 787 COWPEN RD | 195 | PIK | 2022-12-01 | U124015 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | ORA SLONE | 2022-12-01 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.5667 | 1 | 1641.52 | 189.56 | 0 | 43.56 | 1408.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883226300 |  | 500230566 |  | 6720208N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CHEDDINGTON | 3505 CHEDDINGTON LN | 067 | LEX | 2022-12-01 | U127206 | U120245 | 2021-01-30 | 2022-12-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-12-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 2504.04 | 553.13 | 0 | 28.87 | 1922.04 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883274800 |  | 501055187 |  | 6696212H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NORTH | 127 NORTH ST W | 239 | VER | 2022-12-01 | U129673 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | ALEX WILLIAMSON | 2022-12-01 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 2 | 1 | 855.16 | 146.96 | 0 | 34.1 | 674.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883310600 |  | 100328072 |  | 6720208A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CATALPA | 210 CATALPA RD FURN | 067 | LEX | 2022-12-01 | U127206 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-12-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 492.07 | 0 | 0 | 0 | 492.07 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883328100 |  | 500499371 |  | 6696212J | 9615773 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | M L KING | 140 M L KING BV | 239 | VER | 2022-12-01 | U129673 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | ALEX WILLIAMSON | 2022-12-01 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 6 | 1 | 1963.05 | 440.92 | 0 | 102.27 | 1419.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883332500 |  | 100334598 |  | ER VALVE |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LIBERTY | 2100 LIBERTY RD 1FR | 067 | LEX | 2022-12-01 | U126308 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-12-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2623 | 21925678400 |  | 100284077 |  | 6712224H |  |  |  | 566 | EX | ABANDON / RI 10-16-20 DC 2017 | 2621P | MULHOLLAND | 111 MULHOLLAND DR | 209 | GEO | 2022-12-01 | U126284 | U125208 | 2021-07-15 | 2022-10-14 | 2022-12-31 |  | JOSH PASLEY | 2022-12-01 | 2022-02-07 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 7.3667 | 2 | 3749.86 | 581.52 | 0 | 41.18 | 3127.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960233700 |  | 100327204 |  | 6716212L | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | HIGH | 343 E HIGH ST 1 | 067 | LEX | 2022-12-02 | U461375 | U134723 | 2021-12-17 | 2022-12-30 |  |  | LARRY BROWN | 2022-12-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 12719.84 | 0 | 0 | 0 | 12719.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21961518600 |  | 100337830 |  | 6720212F | 2074752 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | CHESTNUT | 609 CHESTNUT ST | 067 | LEX | 2022-12-01 | U129731 | U134723 | 2021-12-27 | 2022-12-30 |  |  | F.GOINS | 2022-12-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1 | 2004.08 | 0 | 0 | 0 | 2004.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22127911100 |  | 501241426 |  | 6728208I |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | SQUIRREL NEST | 1009 SQUIRREL NEST LN LT34 | 067 | LEX | 2022-12-01 | U126308 | U125763 | 2022-08-31 | 2022-12-30 |  |  | J ENSMINGER | 2022-12-01 | 2022-10-31 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 3329.66 | 448.11 | 0 | 36.19 | 2845.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129048400 |  | 501229806 |  | 6724212M | 1850232 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RUTLEDGE | 2132 RUTLEDGE AV | 067 | LEX | 2022-12-01 | U126308 | U130722 | 2022-09-05 | 2022-12-30 |  |  | J ENSMINGER | 2022-12-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 869.46 | 0 | 0 | 9.54 | 859.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129048500 |  | 500405583 |  | 6724208E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SHADOW GLEN | 349 SHADOW GLEN CT | 067 | LEX | 2022-12-01 | U126308 | U130722 | 2022-09-05 | 2022-12-30 |  |  | J ENSMINGER | 2022-12-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1454.8 | 0 | 0 | 0 | 1454.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129055300 |  | 100281875 |  | 6712232O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BOURBON | 401 BOURBON ST | 209 | GEO | 2022-12-01 | U126603 | U130722 | 2022-09-05 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-12-01 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 2.05 | 1 | 1828.5 | 159.25 | 0 | 35.39 | 1633.86 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129061900 |  | 100355980 |  | 7260280N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | PELHAM | 502 PELHAM ST | 161 | MAY | 2022-12-06 | U461478 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DAVID STAGGS | 2022-12-01 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1 | 1295 | 0 | 0 | 0 | 1295 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129062000 |  | 100355981 |  | 7260280N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | PELHAM | 504 PELHAM ST | 161 | MAY | 2022-12-06 | U461478 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DAVID STAGGS | 2022-12-01 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1 | 1295 | 0 | 0 | 0 | 1295 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129062100 |  | 100355983 |  | 7260280N |  |  |  | 566 | EX | ABANDON SL - PEND CN 9/22 OFL | 2600B | PELHAM | 508 PELHAM ST | 161 | MAY | 2022-12-06 | U461478 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DAVID STAGGS | 2022-12-01 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1 | 1230 | 0 | 0 | 0 | 1230 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129062200 |  | 100355988 |  | 7260280N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | PELHAM | 518 PELHAM ST | 161 | MAY | 2022-12-07 | U461478 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DAVID STAGGS | 2022-12-01 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1 | 1230 | 0 | 0 | 0 | 1230 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129062300 |  | 100355990 |  | 7260280N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | PELHAM | 522 PELHAM ST | 161 | MAY | 2022-12-06 | U461478 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DAVID STAGGS | 2022-12-01 | 2022-12-02 |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 4.6667 | 2 | 1633.3 | 321.52 | 0 | 16.78 | 1295 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129062400 |  | 100356002 |  | 7260276A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | PELHAM | 608 PELHAM ST | 161 | MAY | 2022-12-06 | U461478 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DAVID STAGGS | 2022-12-01 | 2022-12-01 |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 12.5 | 2 | 2204.44 | 864.34 | 0 | 45.1 | 1295 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22138277000 |  | 100337742 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTREQD | 2621P | ELM TREE | 606 ELM TREE LN | 067 | LEX | 2022-12-01 | U930915 | U125208 | 2022-10-11 | 2022-10-14 | 2022-11-01 |  | HMCKUNE | 2022-12-01 | 2022-10-18 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 34.3333 | 12 | 1873.02 | 1771.8 | 0 | 101.22 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22145732800 |  | 100319202 |  | 6716208O |  |  |  | 565 | EX | AOC - SERVICE LINE REPLACE | 2621P | MELBOURNE | 281 MELBOURNE WY | 067 | LEX | 2022-12-05 | U930915 | U125208 | 2022-11-21 | 2022-11-28 | 2022-12-07 |  | WISHII | 2022-12-01 | 2022-12-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.5833 | 3 | 2107.58 | 1428.5 | 167.93 | 442.95 | 68.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22146809300 |  | 100312863 |  | 6716208E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | STRATFORD | 462 STRATFORD DR | 067 | LEX | 2022-12-01 | KKINDER | U129939 | 2022-11-30 | 2022-11-30 | 2022-11-30 |  | KKINDER | 2022-12-01 | 2022-11-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.85 | 4 | 1951.14 | 1414.6 | 402.34 | 82.5 | 51.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22146864900 |  | 100356834 |  | 7256276A |  |  |  | 565 | EX | SERVICE LINE - REPLACE W/643 | 2621P | BEVERLY | 664 BEVERLY DR | 161 | MAY | 2022-12-29 | JTOY | U125208 | 2022-11-30 | 2022-11-30 | 2022-12-21 |  | SDADAMS | 2022-12-01 |  |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 | 23.5833 | 2 | 2709.29 | 2064.14 | 464.8 | 107.75 | 72.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22146894600 |  | 100319538 |  | 6716208L |  |  |  | 565 | EX | GRADE 1 REPLACE SERVICE | 2621P | GREENBRIAR | 401 GREENBRIAR RD | 067 | LEX | 2022-12-01 | U930915 | U129939 | 2022-11-30 | 2022-11-30 | 2022-11-30 |  | RJCRAWF | 2022-12-01 | 2022-11-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25.3 | 6 | 2028.49 | 1711.39 | 174.47 | 97.53 | 45.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22146979600 |  | 100278754 |  | 6688232O |  |  |  | 565 | EX | RPLC SL/NO PROJ ID PER SBARKER | 2600B | SEQUOYAH | 215 SEQUOYAH TL | 073 | FRA | 2022-12-01 | U128816 | U125763 | 2022-12-01 | 2022-12-30 |  |  | OLIVER MAYNARD | 2022-12-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 8 | 1 | 3186.34 | 573.43 | 283.6 | 29.94 | 2299.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22147017600 |  | 100321605 |  | 6716212P | 2176779 |  |  | 565 | EX | RPLC SL/21026993800 | 2600B | EUCLID | 305 E EUCLID AV FURN | 067 | LEX | 2022-12-01 | U126309 | U125763 | 2022-12-01 | 2022-12-30 |  |  | JAMIE LYNN | 2022-12-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.05 | 1 | 2501.13 | 360.99 | 0 | 85.56 | 2054.58 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22979030900 |  | 100281703 |  | 6712232O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | POPLAR | 608 POPLAR ST UP | 209 | GEO | 2022-12-01 | U126603 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | SHAWN DENNIS | 2022-12-01 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 5.2333 | 1 | 1309.97 | 405.43 | 0 | 90.12 | 814.42 | 0 | 0 | 0
KY | KY - WEST | 2623 | 99391186100 |  | 100441010 |  | 6712228J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEXINGTON | 1021 LEXINGTON RD | 209 | GEO | 2022-12-01 | U126603 | KEMBERT | 1999-05-24 | 2022-12-01 | 2022-12-31 |  | SHAWN DENNIS | 2022-12-01 | 2020-06-23 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 15.7667 | 7 | 2806.51 | 859.63 | 0 | 256.56 | 1690.32 | 0 | 0 | 0
KY | KY - WEST | 2623 | 01474168400 |  | 100408069 |  | 6692224L | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 2 | 2621P | OLD FRANKFORT | 725 OLD FRANKFORT PK FG17 | 239 | VER | 2022-12-02 | U128816 | DMCCULL | 2001-06-21 | 2022-07-01 | 2022-12-31 |  | OLIVER MAYNARD | 2022-12-02 | 2022-10-06 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 4.1 | 2 | 2172.55 | 281.68 | 0 | 14.71 | 1876.16 | 0 | 0 | 0
KY | KY - WEST | 2623 | 06663719600 |  | 500225843 |  | 6692224G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | DUCKERS | 517 DUCKERS RD | 239 | MID | 2022-12-02 | U126285 | CTAULBE | 2006-10-20 | 2022-07-01 | 2022-12-31 |  | DDAVIS | 2022-12-02 | 2022-11-29 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 12.3333 | 3 | 5992.98 | 908.6 | 0 | 49.28 | 5035.1 | 0 | 0 | 0
KY | KY - EAST | 2633 | 12970803600 |  | 100427871 |  | 7360152J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CHURCH | 50 CHURCH ST | 195 | COA | 2022-12-02 | U124015 | U125208 | 2012-05-22 | 2022-07-01 | 2022-12-31 |  | ORA SLONE | 2022-12-02 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 4.6333 | 1 | 1277.42 | 343.39 | 0 | 78.93 | 855.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 12975821300 |  | 100274122 |  | 6684228N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | STATE | 211 W STATE ST | 073 | FRA | 2022-12-02 | U126603 | U123854 | 2012-06-11 | 2049-12-31 |  |  | SHAWN DENNIS | 2022-12-02 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1327.34 | 0 | 0 | 0 | 1327.34 | 0 | 0 | 0
KY | KY - WEST | 2623 | 16420193600 |  | 100461725 |  | 6700212E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CROSSFIELD | 216 CROSSFIELD DR L-BLDG | 239 | VER | 2022-12-02 | U129731 | U122906 | 2016-06-22 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-12-02 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1853.07 | 0 | 0 | 0 | 1853.07 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18642258500 |  | 501044034 |  | 6684228N | 1635077 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BERRY HILL | 2038 BERRY HILL DR | 073 | FRA | 2022-12-02 | U126603 | AOC SYST | 2018-09-11 | 2022-07-01 | 2022-12-31 |  | SHAWN DENNIS | 2022-12-02 | 2021-02-09 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 | KYACA |  | 100 | 056632B26230057 | 6.0833 | 4 | 4115.57 | 358.91 | 0 | 476.9 | 3279.76 | 0 | 0 | 0
KY | KY - WEST | 2623 | 20801276800 |  | 100271961 |  | 6684228K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 4TH | 214 E 4TH ST | 073 | FRA | 2022-12-14 | U125559 | U131367 | 2020-04-16 | 2020-04-22 |  |  | M YOUNG | 2022-12-02 | 2020-04-22 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 9.45 | 4 | 3815.21 | 513.47 | 0 | 262.36 | 3039.38 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21871716500 |  | 100347057 |  | 6696212K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | HIGH | 133 HIGH ST DONTUSE | 239 | VER | 2022-12-02 | U129731 | U125208 | 2021-01-11 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-12-02 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1772.52 | 0 | 0 | 0 | 1772.52 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883096300 |  | 500141726 |  | 6700212M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | REGENT | 518 REGENT CT | 239 | VER | 2022-12-02 | U126532 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | LESLIE SHARON | 2022-12-02 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 10 | 1 | 3741.48 | 766.34 | 0 | 40 | 2935.14 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883109800 |  | 100346967 |  | 6696212K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | WATER | 124 WATER ST | 239 | VER | 2022-12-02 | U129731 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-12-02 | 2022-11-02 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 7.4667 | 1 | 5175.73 | 473.38 | 0 | 27.68 | 4674.67 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883323200 |  | 100281183 |  | 6696220C |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 2 | 2621P | OLD FRANKFORT | OLD FRANKFORT PK | 239 | MID | 2022-12-02 | U128816 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | OLIVER MAYNARD | 2022-12-02 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 4.0833 | 1 | 1378.29 | 291.7 | 0 | 15.23 | 1071.36 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883332800 |  | 100277525 |  | 6684228H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 2 | 2621P | COLLEGE | 501 COLLEGE ST | 073 | FRA | 2022-12-02 | U126603 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | SHAWN DENNIS | 2022-12-02 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1628.84 | 0 | 0 | 0 | 1628.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960236100 |  | 100321373 |  | 6720212M | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | HIGH | 552 E HIGH ST | 067 | LEX | 2022-12-02 | U126309 | U134723 | 2021-12-17 | 2022-12-30 |  |  | JAMIE LYNN | 2022-12-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1709.21 | 0 | 0 | 0 | 1709.21 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22100669600 |  | 100281691 |  | 6712232O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER | 2623D | POPLAR | 622 POPLAR ST | 209 | GEO | 2022-12-05 | U128410 | AOC SYST | 2022-05-13 | 2022-12-02 |  |  | CDESPAIN | 2022-12-02 | 2022-09-09 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 8.3833 | 2 | 4043.71 | 719.61 | 364.56 | 102.85 | 2856.69 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129021500 |  | 100351874 |  | 6744208K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ARLINGTON | 3 ARLINGTON RD | 049 | WIN | 2022-12-02 | U126603 | U130722 | 2022-09-05 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-12-02 | 2022-11-16 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 16 | 2 | 4706.64 | 1022.52 | 0 | 581.27 | 3102.85 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129060900 |  | 100355680 |  | 7260280N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | BUCKNER | 508 BUCKNER ST | 161 | MAY | 2022-12-07 | U461478 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DAVID STAGGS | 2022-12-02 | 2022-12-02 |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 11.3333 | 2 | 2185.8 | 784.85 | 0 | 40.95 | 1360 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129061000 |  | 100355691 |  | 7260276B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | BUCKNER | 608 BUCKNER ST | 161 | MAY | 2022-12-07 | U461478 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DAVID STAGGS | 2022-12-02 | 2022-12-05 |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 11.5 | 2 | 2196.67 | 795.17 | 0 | 41.5 | 1360 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22146117200 |  | 100356836 |  | 7256276A |  |  |  | 565 | EX | REPLACE SERVICE LINE - D096461 | 2621P | BEVERLY | 643 BEVERLY DR | 161 | MAY | 2022-12-02 | SDADAMS | U125208 | 2022-11-23 | 2023-05-22 | 2024-11-30 |  | SDADAMS | 2022-12-02 | 2022-12-01 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 | 28.5333 | 3 | 3062 | 2435.67 | 441.67 | 127.46 | 57.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22147081300 |  | 100319541 |  | 6716208K |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | GREENBRIAR | 351 GREENBRIAR RD | 067 | LEX | 2022-12-02 | U930915 | U132761 | 2022-12-01 | 2022-12-02 | 2022-12-22 |  | RJCRAWF | 2022-12-02 | 2022-12-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 22.1167 | 3 | 2430.92 | 1707.42 | 557.38 | 89.12 | 77 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22147400500 |  | 100296145 |  | 6716216O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | DOMINICAN | 466 DOMINICAN DR | 067 | LEX | 2022-12-02 | JOCHOA | U134852 | 2022-12-02 | 2022-11-29 | 2022-11-29 |  | JOCHOA | 2022-12-02 | 2022-11-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 46.1 | 9 | 4268.27 | 3110.92 | 535.72 | 518.23 | 103.4 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22147432500 |  | 100351873 |  | 6744208K |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | ARLINGTON | 5 ARLINGTON RD | 049 | WIN | 2022-12-02 | U126603 | U125763 | 2022-12-02 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-12-02 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9.5 | 1 | 3043.63 | 737.88 | 0 | 163.99 | 2141.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22147445800 |  | 100328967 |  | 6720208L |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | PLAINVIEW | 416 PLAINVIEW RD | 067 | LEX | 2022-12-05 | UIPBOT19 | U134852 | 2022-12-02 | 2023-02-16 | 2024-08-31 |  | MCRAIG | 2022-12-02 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 4.2833 | 1 | 925.75 | 352.31 | 240.07 | 226.67 | 106.7 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22147474200 |  | 100281232 |  | 6704216B |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | PISGAH | 4120 PISGAH RD FG2 | 239 | VER | 2022-12-02 | U128816 | U125763 | 2022-12-02 | 2022-12-30 |  |  | OLIVER MAYNARD | 2022-12-02 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - EAST | 2631 | 22147507300 |  | 100260129 |  | 7356256A |  |  |  | 565 | EX | SERVICE LINE ABANDON | 2621P | ASHLAND | 907 ASHLAND AV | 019 | ASH | 2022-12-02 | JDICKES | U134852 | 2022-12-02 | 2022-12-02 |  |  | JDICKES | 2022-12-02 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 2.1833 | 1 | 361.28 | 123.7 | 180.51 | 6.47 | 50.6 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22979026200 |  | 100266007 |  | 7356156T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | STONEY BROOK | 1173 N STONEY BROOK | 195 | BET | 2022-12-02 | U124015 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | ORA SLONE | 2022-12-02 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.6167 | 1 | 1369.73 | 418.42 | 0 | 96.21 | 855.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22979028300 |  | 100274111 |  | 6684228N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WOODLAND | 613 WOODLAND AV | 073 | FRA | 2022-12-02 | U129722 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | M YOUNG | 2022-12-02 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8 | 1 | 3435.09 | 583.56 | 0 | 136.13 | 2715.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21938477700 |  | 100301394 |  | 6712212H | 1635077 |  |  | 565 | EX | GRADE 1 LEAK | 2621D | SUTTON | 201 SUTTON PL | 067 | LEX | 2022-12-03 | MCRAIG | AOC SYST | 2021-09-08 | 2022-12-02 | 2022-12-02 |  | MCRAIG | 2022-12-03 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 | KYACA |  | 100 | 056532B26210021 | 20.25 | 6 | 2319.76 | 1411.54 | 356.28 | 438.64 | 113.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026231000 |  |  |  | 6740228A | 2292767 | U128885 |  | 557 | EX | EMER - INSTALL 1'-2" PMMP | 2621P | VINE | VINE | 017 | PAR | 2022-12-05 | U128132 | U128885 | 2022-10-12 | 2022-12-21 | 2022-12-31 | 2022-10-06 | NRICHIE | 2022-12-04 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP2310 |  |  | 100 | 055732220262310 |  | 2 | 6865.44 | 2364.95 | 115.37 | 690.51 | 3068.06 | 0 | 6.29 | 620.26 | 2
KY | KY - CENTRAL | 2629 | 22026231100 |  |  |  | 6740228A | 2292767 | U128885 |  | 558 | EX | EMER - RETIRE 1'-2" PMP | 2621P | VINE | VINE | 017 | PAR | 2022-12-05 | U128132 | U128885 | 2022-10-12 | 2022-12-30 | 2022-12-31 | 2022-10-06 | NRICHIE | 2022-12-04 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP2311 |  |  | 100 | 055832220262311 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 01478607800 |  | 500011473 |  | V-909/30 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | PARKSIDE | 1038 PARKSIDE DR LT20 | 209 | GEO | 2022-12-05 | U126602 | BBRIGHT | 2001-08-07 | 2022-07-01 | 2022-12-31 |  | DEREK PAYTON | 2022-12-05 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 2747.2 | 0 | 0 | 0 | 2747.2 | 0 | 0 | 0
KY | KY - WEST | 2623 | 08724148100 |  | 100284167 |  | 6712224H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LAURIE | 104 LAURIE LN | 209 | GEO | 2022-12-05 | U129731 | U461383 | 2008-03-18 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-12-05 | 2022-11-29 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 26 | 3 | 7712.3 | 1712.55 | 0 | 202.23 | 5797.52 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12965306700 |  | 100348933 |  | W-1102-5 |  |  |  | 566 | EX | ABANDON SL- DOWNSTREAM | 2621P | MAIN | 21 N MAIN ST 2F | 049 | WIN | 2022-12-05 | U126602 | U124967 | 2012-04-16 | 2014-12-23 |  |  | DEREK PAYTON | 2022-12-05 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 2216.52 | 558.78 | 0 | 29.18 | 1628.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12975887700 |  | 100359985 |  | 16740232M |  |  |  | 566 | EX | ABANDON SL- DOWNSTREAM | 2621P | MAIN | 322< MAIN ST | 017 | PAR | 2022-12-06 | U129673 | U123854 | 2012-06-11 | 2014-12-31 |  |  | ALEX WILLIAMSON | 2022-12-05 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 595.04 | 0 | 0 | 0 | 595.04 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18621396600 |  | 100279198 |  | 6688228F |  |  |  | 566 | EX | ABN / RI 06-12-18 100279199+ | 2621P | VERSAILLES | 144 VERSAILLES RD | 073 | FRA | 2022-12-05 | U126603 | U125208 | 2018-06-19 | 2049-12-31 |  |  | SHAWN DENNIS | 2022-12-05 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 769.8 | 0 | 0 | 0 | 769.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 20771343300 |  | 100415168 | 38 | 6724208M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RICHMOND | 3725 RICHMOND RD | 067 | LEX | 2022-12-05 | U126308 | JFAWNS | 2020-01-16 | 2020-03-20 |  |  | J ENSMINGER | 2022-12-05 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 859.92 | 0 | 0 | 0 | 859.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883053200 |  | 100328302 |  | 6712204G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | HIGBEE MILL | 1220 HIGBEE MILL RD | 067 | LEX | 2022-12-05 | U126604 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | WILL FULKS | 2022-12-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 4854.18 | 813.05 | 0 | 174.53 | 3866.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883071500 |  | 500885124 |  | 6720212L | 0460881 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | JENNIFER | 1602 JENNIFER RD CABLE | 067 | LEX | 2022-12-05 | U127206 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-12-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 3061.27 | 0 | 0 | 0 | 3061.27 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883079700 |  | 100250819 |  | 7336268D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | PERRY | 105 PERRY ST | 089 | GRE | 2022-12-07 | U123965 | U120245 | 2021-01-30 | 2022-12-05 | 2022-12-31 |  | MBLANKE | 2022-12-05 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.95 | 1 | 4976.4 | 239.66 | 0 | 51.74 | 4685 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883153800 |  | 100465254 |  | 6716208N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | PASADENA | 176 PASADENA DR 2B | 067 | LEX | 2022-12-05 | U127206 | U120245 | 2021-01-30 | 2022-11-30 | 2022-12-31 |  | JUSTIN HOBBS | 2022-12-05 | 2022-11-30 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 3690.58 | 477.85 | 0 | 27.95 | 3184.78 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883244200 |  | 500742611 |  | 6712228F | 9828953 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | GATEWAY PATH | 109 GATEWAY PATH | 209 | GEO | 2022-12-05 | U129722 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-12-05 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 9 | 1 | 3744.72 | 656.52 | 0 | 153.15 | 2935.05 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883326400 |  | 500559110 |  | 6688224D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | VERSAILLES | 1438 VERSAILLES RD REAR | 073 | FRA | 2022-12-05 | U126603 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | SHAWN DENNIS | 2022-12-05 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 6.5 | 1 | 1515.76 | 504.86 | 0 | 26.35 | 984.55 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883330000 |  | 500241727 |  | 6680224G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | GARDEN-POINT | 354 GARDEN-POINT DR LT3 | 073 | FRA | 2023-01-03 | U125559 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | BJACKSON | 2022-12-05 | 2022-12-05 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 17.3167 | 3 | 1737.12 | 1329.98 | 0 | 407.14 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129021400 |  | 100437536 |  | 7240280J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | BRIDGEVILLE | 670 BRIDGEVILLE RD TRL | 023 | GER | 2022-12-07 | U461478 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ED FOX | 2022-12-05 | 2022-12-05 |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 16 | 2 | 2584.57 | 1156.07 | 0 | 166 | 1262.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129054300 |  | 100460015 |  | 6688228K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PULLIAM | 103 PULLIAM DR | 073 | FRA | 2022-12-05 | U126603 | U130722 | 2022-09-05 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-12-05 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 4.5 | 1 | 1137.62 | 349.55 | 0 | 18.27 | 769.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129057100 |  | 501287796 |  | 6740232I | 1966890 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LILLESTON | 240 LILLESTON AV | 017 | PAR | 2022-12-05 | U126532 | U130722 | 2022-09-05 | 2022-12-30 |  |  | LESLIE SHARON | 2022-12-05 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.6667 | 1 | 6245.95 | 358.67 | 0 | 316.95 | 5570.33 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129058900 |  | 100463843 |  | 6764176C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WHITE OAK | 1295 WHITE OAK RD APT 10 | 065 | IRV | 2022-12-05 | U126603 | U130722 | 2022-09-05 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-12-05 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 4257.28 | 0 | 0 | 0 | 4257.28 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129085800 |  | 500669064 |  | 6708220L | 9935462 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LEESTOWN | 4468 LEESTOWN RD GRNHSES | 067 | LEX | 2022-12-05 | U126308 | U130722 | 2022-09-05 | 2022-12-30 |  |  | J ENSMINGER | 2022-12-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.9833 | 1 | 2929.54 | 483.51 | 0 | 25.23 | 2420.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22141467700 |  | 100324493 |  | 6720204I | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE SERVICE | 2621D | APPIAN | 3597 APPIAN WY | 067 | LEX | 2022-12-05 | WISHII | AOC SYST | 2022-10-27 | 2022-11-23 | 2022-12-24 |  | WISHII | 2022-12-05 | 2022-11-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 32.05 | 8 | 2352.21 | 1856.72 | 0 | 417.39 | 78.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22147610700 |  | 500742171 |  | 6708220L | 0143892 |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | LEESTOWN | 4468 LEESTOWN RD FRM SHP | 067 | LEX | 2022-12-05 | U126308 | U129939 | 2022-12-05 | 2022-12-05 |  |  | J ENSMINGER | 2022-12-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.0167 | 1 | 1454.21 | 569.4 | 0 | 29.71 | 855.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22979028900 |  | 100275742 |  | 6684228C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FRAZIER | 107 FRAZIER RD | 073 | FRA | 2022-12-05 | U126308 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | J ENSMINGER | 2022-12-05 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 214.75 | 0 | 0 | 0 | 214.75 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22979029000 |  | 100276038 |  | 6684228K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ANN | 406 ANN ST 1FL | 073 | FRA | 2022-12-05 | U129722 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | M YOUNG | 2022-12-05 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1631.21 | 0 | 0 | 0 | 1631.21 | 0 | 0 | 0
KY | KY - WEST | 2621 | 06659740700 |  | 500774848 |  | 6716204P | 0146382 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | DUVAL | 1057 DUVAL ST | 067 | LEX | 2022-12-08 | U461375 | SSUTHER | 2006-09-11 | 2022-07-01 | 2022-12-31 |  | LARRY BROWN | 2022-12-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 3644.14 | 0 | 0 | 0 | 3644.14 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07676359100 |  | 100459266 |  | 6720212L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WINCHESTER | 1575 WINCHESTER RD 119 | 067 | LEX | 2022-12-08 | U461375 | SSUTHER | 2007-02-20 | 2022-07-01 | 2022-12-31 |  | LARRY BROWN | 2022-12-06 | 2022-09-01 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.11667 | 1 | 1363.54 | 8.01 | 0 | 0.68 | 1354.85 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 07684641300 |  | 100286306 |  | X-1206-40 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAIN | 801 MAIN ST A-HOUSE | 065 | RAV | 2022-12-06 | U129722 | SSUTHER | 2007-04-26 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-12-06 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9 | 1 | 2917.45 | 656.52 | 0 | 153.15 | 2107.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 08735915300 |  | 100334041 |  | 6720212O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SPARKS | 1107 SPARKS RD | 067 | LEX | 2022-12-06 | U127206 | SSUTHER | 2008-06-20 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-12-06 | 2022-09-01 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.016667 | 1 | 3223.76 | 1.33 | 0 | 0.11 | 3222.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 10874167700 |  | 100334027 | 13 | 16720212O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SPARKS | 1133 SPARKS RD | 067 | LEX | 2022-12-06 | U127206 | SCHASTE | 2010-12-28 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-12-06 | 2022-09-01 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.05 | 2 | 3807.96 | 556.48 | 0 | 29.16 | 3222.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12968019100 |  | 100332458 |  | 00NEW |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | SAYRE | 526 SAYRE AV | 067 | LEX | 2022-12-08 | U461375 | U124967 | 2012-05-02 | 2022-07-01 | 2022-12-31 |  | LARRY BROWN | 2022-12-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 443.13 | 0 | 0 | 0 | 443.13 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18635535800 |  | 100444273 |  | 7240216H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MIDLAND TRAIL | 256 MIDLAND TRAIL DR 101 | 173 | MT | 2022-12-06 | U126532 | DMCCULL | 2018-08-16 | 2022-07-01 | 2022-12-31 |  | LESLIE SHARON | 2022-12-06 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0 | 1 | 1329.99 | 0 | 0 | 0 | 1329.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 20845438800 |  | 100303132 |  | 6712208C |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | ALEXANDRIA | 2233 ALEXANDRIA DR | 067 | LEX | 2022-12-06 | U127206 | U120245 | 2020-09-17 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-12-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2431.52 | 0 | 0 | 0 | 2431.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 20845439000 |  | 100305536 |  | 6712212K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | ALEXANDRIA | 1565 ALEXANDRIA DR SUIT 1 | 067 | LEX | 2022-12-06 | U127206 | U120245 | 2020-09-17 | 2022-12-05 | 2022-12-31 |  | JUSTIN HOBBS | 2022-12-06 | 2022-12-05 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 2863.81 | 553.13 | 0 | 28.87 | 2281.81 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883049900 |  | 100245869 |  | 7356252L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BARBEQUE | 2400 BARBEQUE RD | 019 | CAT | 2022-12-06 | U123965 | U120245 | 2021-01-30 | 2022-12-06 | 2022-12-31 |  | MBLANKE | 2022-12-06 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.6833 | 1 | 1518.48 | 214.63 | 0 | 46.35 | 1257.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883095900 |  | 100409636 |  | 6724208J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | TODDS | 3031 TODDS RD | 067 | LEX | 2022-12-08 | U126308 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-12-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1195.24 | 0 | 0 | 0 | 1195.24 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883306100 |  | 100417510 |  | 7240216J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 2 | 2621P | VIRGINIA | VIRGINIA AV | 173 | MT | 2022-12-06 | U126308 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-12-06 | 2022-11-17 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.18333 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883308500 |  | 500375561 |  | 6680224G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LOUISVILLE | 1629 LOUISVILLE RD REAR | 073 | FRA | 2022-12-06 | U126603 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | SHAWN DENNIS | 2022-12-06 | 2022-11-10 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 7.5833 | 3 | 2794.39 | 559.3 | 0 | 103.95 | 2131.14 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883317500 |  | 100344405 |  | 7240216P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 2 | 2621P | SPENCER | 1075 SPENCER RD | 173 | MT | 2022-12-06 | U126532 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | LESLIE SHARON | 2022-12-06 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.5 | 1 | 1696.54 | 651.39 | 0 | 34 | 1011.15 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22026234200 |  | 500725700 |  | 7356252H | 2292662 | U132280 |  | 565 | EX | INSTALL 100'-6"PMMP S/L | 2600B | CENTER | 74 CENTER ST | 019 | CAT | 2023-02-06 | U125566 | U132280 | 2022-11-02 | 2022-12-16 | 2022-12-25 | 2022-12-06 | DESKAGG | 2022-12-06 | 2022-11-29 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP2342 |  |  | 100 | 056532220262342 | 76.3667 | 9 | 60246.05 | 7568.56 | 10175.43 | 3474.55 | 35299.38 | 0 | 106 | 3622.13
KY | KY - CENTRAL | 2629 | 22129002600 |  | 100351968 |  | 6744208J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ORANGE | 342 ORANGE AV | 049 | WIN | 2022-12-06 | U129722 | U130722 | 2022-09-05 | 2022-12-30 |  |  | M YOUNG | 2022-12-06 | 2022-10-28 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 14.0167 | 3 | 7134.6 | 902 | 0 | 416.13 | 5816.47 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129004000 |  | 500028164 |  | 7356256F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 26TH | 708< 26TH ST A3 | 019 | ASH | 2022-12-06 | MBLANKE | U130722 | 2022-09-05 | 2022-12-30 |  |  | MBLANKE | 2022-12-06 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.4833 | 1 | 1700.12 | 198.57 | 0 | 42.85 | 1458.7 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22131563800 |  | 100276574 |  | 6684228H | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | LIME | 602 N LIME ST | 073 | FRA | 2022-12-08 | U128410 | AOC SYST | 2022-09-15 | 2022-12-05 | 2023-12-31 |  | CDESPAIN | 2022-12-06 | 2022-12-06 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 7.55 | 1 | 2906.36 | 585.98 | 192.2 | 30.59 | 2097.59 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22131566900 |  | 100276591 |  | 6684228H | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | PHILLIPS | 113 PHILLIPS ST | 073 | FRA | 2022-12-08 | U128410 | AOC SYST | 2022-09-15 | 2022-12-05 | 2023-12-31 |  | CDESPAIN | 2022-12-06 | 2022-12-05 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 11.7 | 2 | 3294.72 | 906.1 | 289.54 | 47.28 | 2051.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22147799400 |  | 100429445 |  | 6748208M |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | KENTUCKY | 19 KENTUCKY ST 2F | 049 | WIN | 2022-12-06 | U126603 | U125763 | 2022-12-06 | 2022-12-30 |  |  | SHAWN DENNIS | 2022-12-06 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.3833 | 1 | 1539.06 | 419.43 | 0 | 93.23 | 1026.4 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22147816800 |  | 100349323 |  | 6748208M |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | FLANAGAN | 52 FLANAGAN ST | 049 | WIN | 2022-12-06 | U129731 | U125763 | 2022-12-06 | 2022-12-30 |  |  | F.GOINS | 2022-12-06 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9 | 1 | 2757.37 | 643.38 | 0 | 33.6 | 2080.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22147830500 |  | 100289487 |  | 6724212A |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | RANGE | 2009 RANGE CT | 067 | LEX | 2022-12-06 | U127206 | U125763 | 2022-12-06 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-12-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1538.44 | 0 | 0 | 0 | 1538.44 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22979023800 |  | 100260462 |  | 7344152T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HUNTER BRANCH | 420 HUNTER BRANCH RD | 071 | PRT | 2022-12-06 | U124015 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | ORA SLONE | 2022-12-06 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 6.75 | 2 | 1581.51 | 503.89 | 0 | 71.62 | 1006 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979024300 |  | 100262413 |  | 7356256G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BRADLEY | 616 BRADLEY ST | 019 | ASH | 2022-12-06 | U123965 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | MBLANKE | 2022-12-06 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.35 | 1 | 1889.48 | 354.29 | 0 | 76.49 | 1458.7 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22979028200 |  | 100273325 |  | 6680224G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CARDWELL | 200 CARDWELL LN | 073 | FRA | 2022-12-06 | U128816 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | OLIVER MAYNARD | 2022-12-06 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8 | 1 | 2305.92 | 573.43 | 0 | 29.94 | 1702.55 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23154577400 |  | 500774849 |  | 6716204P |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | DUVAL | 1059 DUVAL ST | 067 | LEX | 2023-01-12 | U461375 | U125763 | 2023-01-10 | 2023-12-29 |  |  | LARRY BROWN | 2022-12-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 99390480800 |  | 100442419 |  | 6728200D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CLEVELAND | 185 CLEVELAND RD | 067 | LEX | 2022-12-06 | U126308 | KEMBERT | 1999-05-18 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-12-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.9 | 4 | 1359.68 | 687.47 | 0 | 242.71 | 429.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 06663615000 |  | 500105877 |  | U-1711-31 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | US ROUTE 60 | 10699 US ROUTE 60 SP 600 | 019 | CAN | 2022-12-07 | MBLANKE | CTAULBE | 2006-10-19 | 2022-12-07 | 2022-12-31 |  | MBLANKE | 2022-12-07 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.083333 | 1 | 863.92 | 7.26 | 0 | 1.56 | 855.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 07672541100 |  | 500046090 |  | U-1711-31 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | US ROUTE 60 | 10699 US ROUTE 60 SP 525 | 019 | CAN | 2022-12-07 | MBLANKE | U901436 | 2007-01-16 | 2022-12-07 | 2022-12-31 |  | MBLANKE | 2022-12-07 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.15 | 1 | 869.86 | 12.13 | 0 | 2.63 | 855.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11894023600 |  | 500042337 |  | U-1711-31 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | US ROUTE 60 | 10699 US ROUTE 60 SP 940 | 019 | CAN | 2022-12-07 | MBLANKE | U906307 | 2011-03-03 | 2022-12-07 | 2022-12-31 |  | MBLANKE | 2022-12-07 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 13.3 | 2 | 2275.39 | 1021.75 | 0 | 126.92 | 1126.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11900050100 |  | 100458622 |  | 6720204A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | TATES CREEK | 3514< TATES CREEK RD | 067 | LEX | 2022-12-07 | U461443 | U123933 | 2011-04-06 | 2022-07-01 | 2022-12-31 |  | WGRAVES | 2022-12-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.7333 | 1 | 1969.67 | 187.38 | 0 | 9.77 | 1772.52 | 0 | 0 | 0
KY | KY - EAST | 2631 | 13175751300 |  | 500054017 |  | U-1711-31 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | US ROUTE 60 | 10699 US ROUTE 60 SP 100 | 019 | CAN | 2022-12-07 | MBLANKE | U125201 | 2013-11-15 | 2022-12-07 | 2022-12-31 |  | MBLANKE | 2022-12-07 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.21667 | 1 | 876.7 | 17.77 | 0 | 3.83 | 855.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 16426422500 |  | 100358440 |  | 6740232M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAIN | 200 MAIN ST | 017 | PAR | 2022-12-07 | U126532 | U122906 | 2016-07-13 | 2022-07-01 | 2022-12-31 |  | LESLIE SHARON | 2022-12-07 | 2022-12-05 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 27.25 | 3 | 15861.66 | 2018.28 | 0 | 559.35 | 13284.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883059500 |  | 100290589 |  | 6720216O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | OLD PARIS | 1881 OLD PARIS RD | 067 | LEX | 2022-12-07 | U127206 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-12-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 5593.18 | 0 | 0 | 0 | 5593.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883083600 |  | 501097841 |  | 6724208E | 1102270 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | FALLING LEAVES | 2005 FALLING LEAVES LN | 067 | LEX | 2022-12-07 | U126308 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-12-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.7 | 1 | 1762.8 | 302.12 | 0 | 253.48 | 1207.2 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883090300 |  | 100253241 |  | 7360236T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | US ROUTE 23 | 19108 US ROUTE 23 | 019 | CAT | 2022-12-07 | U125566 | U120245 | 2021-01-30 | 2022-12-07 | 2022-12-31 |  | DESKAGG | 2022-12-07 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.1667 | 1 | 2071.89 | 329.51 | 0 | 72.42 | 1669.96 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883111700 |  | 500613507 |  | 7348248C |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | US ROUTE 60 | 10699 US ROUTE 60 SP 445 | 019 | CAN | 2022-12-07 | U123965 | U120245 | 2021-01-30 | 2022-12-07 | 2022-12-31 |  | MBLANKE | 2022-12-07 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.23333 | 1 | 877.67 | 18.57 | 0 | 4 | 855.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883131400 |  | 501149570 |  | 6728208A | 1426050 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CHERRY MEADOW | 3140 CHERRY MEADOW PA | 067 | LEX | 2022-12-07 | U126308 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-12-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1144.01 | 0 | 0 | 0 | 1144.01 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883134800 |  | 500047925 |  | 7348248C |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | US ROUTE 60 | 10699 US ROUTE 60 SP 1000 | 019 | CAN | 2022-12-07 | U123965 | U120245 | 2021-01-30 | 2022-12-07 | 2022-12-31 |  | MBLANKE | 2022-12-07 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.53333 | 2 | 1176.71 | 40.86 | 0 | 9.13 | 1126.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883235800 |  | 100332919 |  | 6724208I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | TODDS | 1345 TODDS RD | 067 | LEX | 2022-12-08 | U126308 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-12-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1201.85 | 0 | 0 | 0 | 1201.85 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883249800 |  | 100265423 |  | 7352252A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | US ROUTE 60 | 5756 US ROUTE 60 | 019 | ASH | 2022-12-07 | MBLANKE | U120245 | 2021-01-30 | 2022-12-07 | 2022-12-31 |  | MBLANKE | 2022-12-07 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.8667 | 1 | 1510.18 | 234.01 | 0 | 50.54 | 1225.63 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026222700 |  | 100460492 |  | 6712232O | 2291310 | U126783 |  | 555 | EX | INSTALL 86'-2" PMMP | 2600B | LYNN | 209 W LYNN ST | 209 | GEO | 2023-01-03 | U128132 | U126783 | 2022-09-07 | 2023-01-11 | 2023-01-14 | 2022-12-07 | R.HUMPHREYS | 2022-12-07 | 2022-12-05 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2227 |  |  | 100 | 055532220262227 | 35.4667 | 300 | 13511.21 | 2609.33 | 839.11 | 604.2 | 8718.57 | 0 | 24.24 | 715.76 | 60
KY | KY - WEST | 2623 | 22026245100 |  |  |  | 6700228K | 2294541 | U461383 |  | 557 | CO | EMER-INSTALL 3' OF 2"PHHP MAIN | 2600B | ROCKY WATERS | ROCKY WATERS | 209 | GEO | 2024-04-10 |  | U461383 | 2022-12-21 | 2024-12-31 | 2024-12-31 | 2022-12-07 | KEVIN KOUNS | 2022-12-07 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP2451 |  |  | 100 | 055732220262451 |  | 3 | 2752.76 | 1940.88 | 0 | 347.03 | 301.5 | 0 | 18.18 | 145.17 | 3
KY | KY - WEST | 2623 | 22122445400 |  | 100409357 |  | 6688228O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | SADDLEBACK | 1300 SADDLEBACK TL | 073 | FRA | 2022-12-08 | U128410 | AOC SYST | 2022-08-08 | 2023-02-08 | 2023-12-31 |  | CDESPAIN | 2022-12-07 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 |  | 1 | 2048.7 | 0 | 209.93 | 0 | 1838.77 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129006200 |  | 100358669 |  | 6740232E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OLD PEACOCK | 650 OLD PEACOCK RD 21 | 017 | PAR | 2022-12-07 | U126532 | U130722 | 2022-09-05 | 2022-12-30 |  |  | LESLIE SHARON | 2022-12-07 | 2022-12-07 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5 | 1 | 4248.96 | 383.19 | 0 | 338.62 | 3527.15 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129007500 |  | 100461291 |  | 6732240D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | US 27 S | 676 US 27 S | 097 | CYN | 2022-12-07 | U126284 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JOSH PASLEY | 2022-12-07 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10 | 1 | 2513.03 | 807.52 | 0 | 679.39 | 1026.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129023000 |  | 100269940 |  | 6732252P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 4TH | 208 4TH ST | 097 | CYN | 2022-12-07 | U126602 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DEREK PAYTON | 2022-12-07 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2603.88 | 0 | 0 | 0 | 2603.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129053100 |  | 100275437 |  | 6684228F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KENTUCKY | 634 KENTUCKY AV | 073 | FRA | 2022-12-07 | U126602 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DEREK PAYTON | 2022-12-07 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 17 | 2 | 3145.85 | 1187.43 | 0 | 62.02 | 1896.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22145878700 |  | 100331264 |  | 6720212N | 1313369 |  |  | 565 | EX | REPLACE SL | 2621P | LINCOLN | 145 LINCOLN AV | 067 | LEX | 2022-12-07 | ABLAKE | U132823 | 2022-11-22 | 2022-11-22 |  |  | ABLAKE | 2022-12-07 | 2022-11-22 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 58.4833 | 12 | 9498.87 | 4227.37 | 217.55 | 228.75 | 4825.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22148023000 |  | 100293202 |  | 6720216K |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | RADCLIFFE | 411 RADCLIFFE RD B | 067 | LEX | 2022-12-07 | U127206 | U125763 | 2022-12-07 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-12-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 2120.44 | 553.13 | 0 | 28.87 | 1538.44 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22979028800 |  | 100275411 |  | 6684228F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | POLSGROVE | 744 POLSGROVE ST | 073 | FRA | 2022-12-07 | U126602 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | DEREK PAYTON | 2022-12-07 | 2022-11-16 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.016667 | 1 | 2084.15 | 1.24 | 0 | 0.07 | 2082.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22996202000 |  | 100345798 |  | 6696212D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | GEORGIA | 108 GEORGIA ST | 239 | VER | 2022-12-07 | DCOLLIN | AOC SYST | 2022-04-26 | 2023-12-31 | 2023-12-31 |  | DCOLLIN | 2022-12-07 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 22.75 | 3 | 3102.01 | 1654.51 | 0 | 424.55 | 1022.95 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23158499900 |  | 100262751 |  | 7352260K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | PRICE | 1313 PRICE ST | 019 | ASH | 2023-01-25 | U125566 | U125763 | 2023-01-25 | 2023-12-29 |  |  | DAVID SKAGGS | 2022-12-07 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 882.65 | 0 | 0 | 0 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11878836600 |  | 100402411 |  | 7352256J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | FRIENDSHIP | 3708 FRIENDSHIP RD | 019 | ASH | 2022-12-08 | U123965 | U906609 | 2011-01-13 | 2022-07-01 | 2022-12-31 |  | MBLANKE | 2022-12-08 | 2021-11-23 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 14.4333 | 2 | 3092.13 | 849.56 | 0 | 121.27 | 2121.3 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883183900 |  | 100463716 |  | 7348248E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | US ROUTE 60 | 138 US ROUTE 60 WE | 019 | ASH | 2022-12-08 | U123965 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | MBLANKE | 2022-12-08 | 2022-10-12 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 8 | 2 | 962.76 | 493.4 | 0 | 98.83 | 370.53 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026240500 |  |  |  | 6760172J | 2293972 | U128885 |  | 583 | EX | INSTALL VRG | 2629M | DUG HILL | 724 DUG HILL RD | 065 | IRV | 2023-07-17 | U123258 | U128885 | 2022-11-28 | 2023-12-28 | 2023-12-31 | 2022-12-08 | WADE SHIMFESSEL | 2022-12-08 | 2022-12-16 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00583 | 3200583 |  |  | WP2405 |  |  | 100 | 058332220262405 | 57.65 | 0 | 7577.2 | 4543.24 | 0 | 1667.77 | 925.52 | 0 | 40.58 | 400.09
KY | KY - CENTRAL | 2629 | 22026240600 |  |  |  | 6760172J | 2293972 | U128885 |  | 584 | EX | RETIRE VRG | 2629M | DUG HILL | 724 DUG HILL RD | 065 | IRV | 2023-05-16 | U123258 | U128885 | 2022-11-28 | 2023-12-29 | 2023-12-31 | 2022-12-08 | WADE SHIMFESSEL | 2022-12-08 | 2023-01-11 |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00584 | 3200584 |  |  | WP2406 |  |  | 100 | 058432220262406 | 13.0667 | 0 | 1416.09 | 875.57 | 0 | 540.52 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129005000 |  | 500024383 |  | 6720212I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 4TH | 235 E 4TH ST 2F | 067 | LEX | 2022-12-08 | U127206 | U130722 | 2022-09-05 | 2022-10-10 |  |  | JUSTIN HOBBS | 2022-12-08 | 2022-10-10 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.2833 | 1 | 2780.36 | 74.36 | 0 | 31.79 | 2674.21 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129117500 |  | 100441396 |  | 6716212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | UPPER | 425 N UPPER ST 1FRR-3 | 067 | LEX | 2022-12-08 | U461375 | U125208 | 2022-09-06 | 2022-12-30 |  |  | LARRY BROWN | 2022-12-08 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.5 | 1 | 1377.25 | 494.13 | 0 | 439.99 | 443.13 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22136864200 |  | 100265945 |  | 7348252D |  |  |  | 565 | EX | NBT - RELOCATE MTR/SL UPGRADE | 2621P | STATE RT 716 | 831 STATE RT 716 | 019 | ASH | 2022-12-08 | LAMAY | U125208 | 2022-10-05 | 2022-10-07 | 2022-10-25 |  | LAMAY | 2022-12-08 | 2022-11-03 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 21.3167 | 6 | 1873.87 | 1563.06 | 184.98 | 85.13 | 40.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22147878100 |  | 100340144 |  | 6724212E |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | HI CREST | 728 HI CREST DR B | 067 | LEX | 2022-12-08 | U127206 | U125763 | 2022-12-06 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-12-08 | 2022-12-07 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.4333 | 2 | 2395.34 | 660.31 | 0 | 124.34 | 1610.69 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22148021500 |  | 100265525 |  | 7348252L | 1313372 |  |  | 565 | EX | REPLACE SL | 2621P | US ROUTE 60 | 7723 US ROUTE 60 | 019 | ASH | 2022-12-15 | DYOUNG | U132823 | 2022-12-07 | 2022-12-07 | 2022-12-07 |  | BROBERT | 2022-12-08 | 2022-12-07 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 23.6667 | 4 | 3260.77 | 1697.36 | 769.75 | 630.86 | 162.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22148168900 |  | 100274606 |  | 6684228J |  |  |  | 565 | EX | SERVICE LINE REPLACE | 2621P | CONWAY | 324 CONWAY ST | 073 | FRA | 2022-12-08 | U128410 | U134852 | 2022-12-08 | 2022-12-07 | 2022-12-07 |  | CDESPAIN | 2022-12-08 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 10.5 | 1 | 4873.77 | 813.86 | 399.1 | 42.47 | 3618.34 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22979022900 |  | 100259278 |  | 7356148T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | TOLER CREEK | 3109 TOLER CREEK LFT FRK | 071 | HAR | 2022-12-09 | U124015 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | ORA SLONE | 2022-12-08 | 2022-12-08 |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.7667 | 2 | 1350.6 | 280.15 | 0 | 64.45 | 1006 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22979046500 |  | 100429599 |  | 7352148T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KY ROUTE 3379 | 1198 KY ROUTE 3379 | 071 | GRE | 2022-12-08 | U124015 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | ORA SLONE | 2022-12-08 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.75 | 1 | 1166.01 | 130.09 | 0 | 29.92 | 1006 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22979048200 |  | 100455401 |  | 6716212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | UPPER | 425 N UPPER ST 2F-2 | 067 | LEX | 2022-12-08 | U461375 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | LARRY BROWN | 2022-12-08 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.5 | 1 | 946.19 | 266.11 | 0 | 236.95 | 443.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 97320303000 |  | 100314162 |  | 6716212O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BROADWAY | 912 S BROADWAY ST | 067 | LEX | 2022-12-08 | U126308 | MPINKST | 1997-10-09 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-12-08 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 01474163000 |  | 500076063 |  | 16720212B | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BROADWAY | 1390 N BROADWAY ST | 067 | LEX | 2022-12-09 | U461375 | DMCCULL | 2001-06-21 | 2022-07-01 | 2022-12-31 |  | LARRY BROWN | 2022-12-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.5 | 1 | 3344.37 | 342.06 | 0 | 304.61 | 2697.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11910270100 |  | 100316839 |  | 16716208J | 9830102 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NICHOLASVILLE | 1915 NICHOLASVILLE RD SUITE B | 067 | LEX | 2022-12-09 | U126532 | U124017 | 2011-06-07 | 2022-07-01 | 2022-12-31 |  | LESLIE SHARON | 2022-12-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 3028.9 | 613.06 | 0 | 32 | 2383.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 13134931300 |  | 100338449 |  | 6720212E | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 7TH | 175< E 7TH ST | 067 | LEX | 2022-12-09 | U127206 | U123694 | 2013-05-07 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-12-09 | 2022-09-07 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.3167 | 3 | 1663.72 | 154.36 | 0 | 11.35 | 1498.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21026993800 |  |  |  | 6716212P | 2176779 | U461383 |  | 557 | EX | INSTALL 7200' OF 2"/6"PMMP | 2600B | HIGH | 456 E HIGH ST | 067 | LEX | 2023-01-06 | U128132 | U461383 | 2021-01-06 | 2021-11-24 | 2022-12-31 | 2022-02-21 | JAMIE LYNN | 2022-12-09 | 2022-01-03 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP9938 | AMRCB |  | 100 | 055732210269938 | 2477.0833 | 2324228 | 3006825.55 | 153143.56 | 400630.7 | 54889.28 | 1998364.76 | 0 | 594.53 | 399202.72 | 7402
KY | KY - WEST | 2621 | 21026993900 |  |  |  | 6716212P | 2176779 | U461383 |  | 558 | EX | RETIRE 9500' OF 4"CI/6"BSLP MN | 2600B | HIGH | 456 E HIGH ST | 067 | LEX | 2022-12-27 | U128132 | U461383 | 2021-01-06 | 2022-12-30 | 2022-12-31 | 2022-12-09 | JAMIE LYNN | 2022-12-09 | 2022-01-25 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP9939 | AMRCB |  | 100 | 055832210269939 | 15.9167 | 0 | 5876.52 | 993.48 | 0 | 219.04 | 4664 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883106500 |  | 100430881 |  | 6716212G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | PAYNE | 167 PAYNE ST | 067 | LEX | 2022-12-09 | U126285 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DDAVIS | 2022-12-09 | 2022-06-09 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10 | 1 | 4085.35 | 556.94 | 0 | 34.61 | 3493.8 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883158300 |  | 500070095 |  | NEW |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2633S | LEFT FK ABBOTT | 2640 LEFT FK ABBOTT CR | 071 | PRE | 2022-12-09 | U124015 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | ORA SLONE | 2022-12-09 |  |  | B | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 3.1167 | 1 | 1289.38 | 230.39 | 0 | 52.99 | 1006 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883215600 |  | 100429824 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2633S | OLD 114 | 1182 OLD 114 | 071 | PRE | 2022-12-09 | U124015 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | ORA SLONE | 2022-12-09 | 2022-10-31 |  | B | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 7.55 | 2 | 2359.81 | 504.8 | 0 | 107.95 | 1747.06 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883220000 |  | 100404212 |  | 6716220A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 2 | 2621P | GEORGETOWN | 4130 GEORGETOWN RD L15 | 067 | LEX | 2022-12-09 | U126308 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-12-09 | 2022-11-03 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.1833 | 1 | 1086.02 | 48.71 | 0 | 2.84 | 1034.47 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883222600 |  | 500219605 |  | 7348264N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | CLARK | 1525 CLARK ST | 089 | FLA | 2022-12-09 | RECUMP | U120245 | 2021-01-30 | 2022-12-09 | 2022-12-31 |  | RECUMP | 2022-12-09 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.9 | 1 | 222.01 | 148.96 | 19.04 | 54.01 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883256200 |  | 100439544 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BROADWAY | 438 N BROADWAY ST 2F | 067 | LEX | 2022-12-09 | U127206 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-12-09 | 2022-09-23 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.8167 | 3 | 1056.89 | 583.21 | 0 | 30.55 | 443.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883279300 |  | 100295010 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BROADWAY | 470 N BROADWAY ST 2F | 067 | LEX | 2022-12-09 | U127206 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-12-09 | 2022-09-23 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.2667 | 3 | 203.67 | 192.61 | 0 | 11.06 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883279600 |  | 100295009 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BROADWAY | 470 N BROADWAY ST | 067 | LEX | 2022-12-09 | U127206 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-12-09 | 2022-09-23 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.9167 | 3 | 2297.87 | 193.78 | 0 | 10.81 | 2093.28 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883312200 |  | 100426855 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2633S | SHOP BRANCH | 479 SHOP BRANCH RD | 071 | PRE | 2022-12-09 | U124015 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | ORA SLONE | 2022-12-09 | 2022-11-29 |  | B | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 5.3833 | 2 | 2410.3 | 371.34 | 0 | 87.32 | 1951.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960239200 |  | 100320966 |  | 6720212M | 2176779 |  |  | 565 | EX | REPLACE SL W/21-0269938-00 | 2600B | MAXWELL | 505 E MAXWELL ST | 067 | LEX | 2022-12-09 | U126309 | U134723 | 2021-12-17 | 2022-12-30 |  |  | JAMIE LYNN | 2022-12-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2227.62 | 0 | 0 | 0 | 2227.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960254400 |  | 100320992 |  | 6716212P | 2176779 |  |  | 566 | EX | ABANDON SL W/CAPTIOL JOB | 2600B | MAXWELL | 445 E MAXWELL ST 1FFT-1 | 067 | LEX | 2022-12-14 | U126309 | U134723 | 2021-12-17 | 2022-12-30 |  |  | JAMIELYNN | 2022-12-09 | 2022-08-30 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 1.7667 | 2 | 154.02 | 124.13 | 0 | 29.89 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960254500 |  | 100442936 |  | 6716212P | 2176779 |  |  | 566 | EX | ABANDON SL W/CAPTIOL JOB | 2600B | MAXWELL | 445 E MAXWELL ST 1FRR-2 | 067 | LEX | 2022-12-14 | U126309 | U134723 | 2021-12-17 | 2022-12-30 |  |  | JAMIE LYNN | 2022-12-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 21960254600 |  | 100320990 |  | 6716212P | 2176779 |  |  | 566 | EX | ABANDON SL W/CAPTIOL JOB | 2600B | MAXWELL | 445 E MAXWELL ST 2FFT-3 | 067 | LEX | 2022-12-14 | U126309 | U134723 | 2021-12-17 | 2022-12-30 |  |  | JAMIE LYNN | 2022-12-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 21960254700 |  | 100320991 |  | 6716212P | 2176779 |  |  | 566 | EX | ABANDON SL W/CAPTIOL JOB | 2600B | MAXWELL | 445 E MAXWELL ST 2FRR-4 | 067 | LEX | 2022-12-14 | U126309 | U134723 | 2021-12-17 | 2022-12-30 |  |  | JAMIE LYNN | 2022-12-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 21960255600 |  | 100320953 |  | 6720212M | 2176779 |  |  | 566 | EX | ABANDON SL W/CAPTIOL JOB | 2600B | WOODLAND | 201 WOODLAND AV 2FL | 067 | LEX | 2022-12-14 | U126309 | U134723 | 2021-12-17 | 2022-12-30 |  |  | JAMIE LYNN | 2022-12-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 21960255700 |  | 100320959 |  | 6720212M | 2176779 | U134723 |  | 566 | EX | ABANDON SL/21026993800 | 2600B | WOODLAND | 210 WOODLAND AV 1 | 067 | LEX | 2022-12-14 | U126309 | U134723 | 2021-12-17 | 2022-12-30 |  |  | JAMIE LYNN | 2022-12-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 21960260400 |  | 100442406 |  | 6716212P | 2176779 |  |  | 566 | EX | ABANDON SL W/CAPTIOL JOB | 2600B | MAXWELL | 453 E MAXWELL ST 1-1FL | 067 | LEX | 2022-12-14 | U126309 | U134723 | 2021-12-17 | 2022-12-30 |  |  | JAMIE LYNN | 2022-12-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1 | 1368.31 | 0 | 0 | 0 | 1368.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960260500 |  | 100441174 |  | 6716212P | 2176779 |  |  | 566 | EX | ABANDON SL W/CAPTIOL JOB | 2600B | MAXWELL | 453 E MAXWELL ST 2-1FR | 067 | LEX | 2022-12-14 | U126309 | U134723 | 2021-12-17 | 2022-12-30 |  |  | JAMIE LYNN | 2022-12-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 21960260600 |  | 100320987 |  | 6716212P | 2176779 |  |  | 566 | EX | ABANDON SL W/CAPTIOL JOB | 2600B | MAXWELL | 453 E MAXWELL ST 3-2FR | 067 | LEX | 2022-12-14 | U126309 | U134723 | 2021-12-17 | 2022-12-30 |  |  | JAMIELYNN | 2022-12-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 21960260700 |  | 100320988 |  | 6716212P | 2176779 |  |  | 566 | EX | ABANDON SL W/CAPTIOL JOB | 2600B | MAXWELL | 453 E MAXWELL ST 4-2FL | 067 | LEX | 2022-12-14 | U126309 | U134723 | 2021-12-17 | 2022-12-30 |  |  | JAMIE LYNN | 2022-12-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 22026245000 |  |  |  | 6716212L | 2176779 | U461383 |  | 560 | EX | PAPER ONLY EXECUTE | 2600B | ROSE | ROSE ST | 067 | LEX | 2022-12-27 | U128132 | U461383 | 2022-12-21 | 2023-01-31 | 2023-01-31 | 2022-12-09 | JAMIE LYNN | 2022-12-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00560 | 3200560 |  |  | WP2450 | AMRCB |  | 100 | 056032220262450 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22100067100 |  | 100271958 |  | 6684228K | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | LOGAN | 321 LOGAN ST | 073 | FRA | 2022-12-12 | U128410 | AOC SYST | 2022-05-11 | 2022-11-11 | 2023-12-31 |  | CDESPAIN | 2022-12-09 | 2022-12-09 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 8 | 1 | 3740.19 | 620.06 | 399.1 | 32.36 | 2688.67 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129051600 |  | 100273336 |  | 6680224G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CARDWELL | 77 CARDWELL LN 1 | 073 | FRA | 2022-12-09 | U128816 | U130722 | 2022-09-05 | 2022-12-30 |  |  | OLIVER MAYNARD | 2022-12-09 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 2.7 | 1 | 7676.92 | 194.97 | 0 | 10.18 | 7471.77 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22131243100 |  | 100308299 |  | 6716212O |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | BROADWAY | 1017 S BROADWAY ST 1F | 067 | LEX | 2022-12-09 | U461375 | U125763 | 2022-09-14 | 2022-12-30 |  |  | LARRY BROWN | 2022-12-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.5 | 1 | 1389.23 | 266.05 | 0 | 236.92 | 886.26 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22147883500 |  | 100273337 |  | 6680224G |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | CARDWELL | 77 CARDWELL LN 2 | 073 | FRA | 2022-12-09 | U128816 | U125763 | 2022-12-06 | 2022-12-30 |  |  | OLIVER MAYNARD | 2022-12-09 | 2022-12-07 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 10.8167 | 2 | 814.51 | 774.09 | 0 | 40.42 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22147883700 |  | 100273338 |  | 6680224G |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | CARDWELL | 77 CARDWELL LN 3 | 073 | FRA | 2022-12-09 | U128816 | U125763 | 2022-12-06 | 2022-12-30 |  |  | OLIVER MAYNARD | 2022-12-09 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.13333 | 1 | 9.85 | 9.35 | 0 | 0.5 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22147883900 |  | 500209603 |  | 6680224G |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | CARDWELL | 77 CARDWELL LN 4 | 073 | FRA | 2022-12-09 | U128816 | U125763 | 2022-12-06 | 2022-12-30 |  |  | OLIVER MAYNARD | 2022-12-09 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.25 | 1 | 18.86 | 17.93 | 0 | 0.93 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22148316200 |  | 100313469 |  | 6716208B |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BOB O LINK | 491 BOB O LINK DR | 067 | LEX | 2022-12-09 | HMCKUNE | U132823 | 2022-12-09 | 2022-12-08 | 2022-12-08 |  | HMCKUNE | 2022-12-09 | 2022-12-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.05 | 3 | 2987.66 | 2293.27 | 524.03 | 119.76 | 50.6 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22148321800 |  | 100260145 |  | 7356256A | 1313372 |  |  | 565 | EX | REPLACE SL | 2621P | ASHLAND | 908 ASHLAND AV | 019 | ASH | 2022-12-09 | LAMAY | U132823 | 2022-12-09 | 2022-12-09 |  |  | LAMAY | 2022-12-09 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.71667 | 1 | 69.24 | 65.8 | 0 | 3.44 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22148322000 |  | 100260130 |  | 7356256A | 1313372 |  |  | 565 | EX | REPLACE SL | 2621P | ASHLAND | 909 ASHLAND AV | 019 | ASH | 2022-12-09 | LAMAY | U132823 | 2022-12-09 | 2022-12-09 |  |  | LAMAY | 2022-12-09 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 5.35 | 1 | 1304.25 | 490.89 | 738.23 | 25.63 | 49.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22148331900 |  | 100323170 |  | 6716208P | 1313369 |  |  | 565 | EX | REPLACE SL | 2621P | STARLING | 3145 STARLING DR | 067 | LEX | 2022-12-09 | KKINDER | U132823 | 2022-12-09 | 2022-12-09 | 2022-12-09 |  | KKINDER | 2022-12-09 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.8 | 2 | 1760.37 | 1224.51 | 392.73 | 63.93 | 79.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22148960300 |  | 100320989 |  | 6716212P | 2176779 |  |  | 566 | EX | ABANDON SL | 2600B | MAXWELL | 453 E MAXWELL ST WH | 067 | LEX | 2022-12-14 | U126309 | U131066 | 2022-12-14 | 2022-12-30 |  |  | JAMIE LYNN | 2022-12-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 99390528600 |  | 100326247 |  | 6708212J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 2 | 2621P | VERSAILLES | 5015 VERSAILLES RD | 067 | LEX | 2022-12-09 | U126308 | KEMBERT | 1999-05-18 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-12-09 | 2022-11-01 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 29.2833 | 7 | 5104.59 | 2168.53 | 0 | 1692.55 | 1243.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 08757938900 |  | 100442153 |  | V-930-61 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NICHOLASVILLE | 2553 NICHOLASVILLE RD M5 | 067 | LEX | 2022-12-12 | U129731 | U123166 | 2008-11-06 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-12-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9 | 1 | 2358.85 | 643.38 | 0 | 152.48 | 1562.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 10871478300 |  | 100438729 |  | V-930-61 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NICHOLASVILLE | 2553 NICHOLASVILLE RD M1 | 067 | LEX | 2022-12-12 | U129722 | U906307 | 2010-12-08 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-12-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9 | 1 | 3040.67 | 656.52 | 0 | 153.15 | 2231 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11891653700 |  | 100438733 |  | 6716208N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NICHOLASVILLE | 2553 NICHOLASVILLE RD M6 | 067 | LEX | 2022-12-12 | U129731 | U123933 | 2011-02-23 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-12-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 2421.99 | 0 | 0 | 0 | 2421.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11891656900 |  | 100438731 |  | V-930-61 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NICHOLASVILLE | 2553 NICHOLASVILLE RD M3 | 067 | LEX | 2022-12-12 | U126532 | U123933 | 2011-02-23 | 2022-07-01 | 2022-12-31 |  | LESLIE SHARON | 2022-12-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9 | 1 | 1754.47 | 689.69 | 0 | 36.01 | 1028.77 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11891657500 |  | 100438730 |  | V-930-61 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NICHOLASVILLE | 2553 NICHOLASVILLE RD M2 | 067 | LEX | 2022-12-12 | U129722 | U123933 | 2011-02-23 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-12-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1026.12 | 0 | 0 | 0 | 1026.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11892964400 |  | 100438732 |  | V-930-61 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NICHOLASVILLE | 2553 NICHOLASVILLE RD M4 | 067 | LEX | 2022-12-12 | U126532 | U123933 | 2011-03-01 | 2022-07-01 | 2022-12-31 |  | LESLIE SHARON | 2022-12-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1036.72 | 0 | 0 | 0 | 1036.72 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11897052600 |  | 100409033 |  | 6744208E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LEXINGTON | 1510 W LEXINGTON AV | 049 | WIN | 2022-12-13 | U126603 | U124961 | 2011-03-22 | 2022-07-01 | 2022-12-31 |  | SHAWN DENNIS | 2022-12-12 | 2022-12-12 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 27.5 | 3 | 9789.33 | 2073.38 | 0 | 365.81 | 7350.14 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12978300600 |  | 100331186 | 63 | V-1026-13 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 2 | 2621P | LINCOLN | 308 LINCOLN AV | 067 | LEX | 2022-12-12 | U127206 | OWHITT | 2012-06-28 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-12-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 4921.05 | 553.13 | 0 | 28.87 | 4339.05 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 16462127000 |  | 100449069 |  | 6736216D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | PINE GROVE | 2514 PINE GROVE RD | 017 | PAR | 2022-12-12 | U126602 | U125208 | 2016-12-20 | 2022-07-01 | 2022-12-31 |  | DEREK PAYTON | 2022-12-12 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 35.0667 | 12 | 5876.87 | 1942.32 | 0 | 242.15 | 3692.4 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883160600 |  | 100408171 |  | 7356216D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LOCK | 618 N LOCK AV L16 | 127 | LOU | 2022-12-12 | U126286 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | TYLER ALLISON | 2022-12-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 12 | 1 | 2092.72 | 881.7 | 0 | 46.02 | 1165 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883180700 |  | 100293460 |  | 6720216I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | MONTROSE | 1550 MONTROSE DR | 067 | LEX | 2022-12-12 | U126308 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-12-12 | 2022-01-31 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.3333 | 1 | 3041.3 | 419.01 | 0 | 145.35 | 2476.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883205000 |  | 100309111 |  | 6716208A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | HARRODSBURG | 1891 HARRODSBURG RD | 067 | LEX | 2022-12-12 | U461375 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | LARRY BROWN | 2022-12-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.5 | 1 | 3643.89 | 266.11 | 0 | 236.95 | 3140.83 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883210700 |  | 100249429 |  | 7356216H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | ACORN | 53 ACORN AV | 127 | LOU | 2022-12-12 | U126286 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | TYLER ALLISON | 2022-12-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1360 | 0 | 0 | 0 | 1360 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883259200 |  | 100458704 |  | 6680224G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | CARDWELL | 94 CARDWELL LN | 073 | FRA | 2022-12-12 | U128816 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | OLIVER MAYNARD | 2022-12-12 | 2022-12-07 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 18.1 | 3 | 6839.81 | 1297.4 | 0 | 67.73 | 5474.68 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22026229500 |  |  |  | 7360244A | 2292560 | GSULLI1 |  | 587 | VO | EMER - REPLACE FAILED METER | 2631M | US23--ASHLAND OIL | US23--ASHLAND OIL | 019 | CAT | 2022-12-12 |  | GSULLI1 | 2022-10-05 | 2023-12-29 | 2023-12-31 | 2022-12-12 | DASH | 2022-12-12 | 2022-10-20 |  | F | [11 empty] | 22026216300 | 100 |  | 0.18333 | 0 | 0.67 | 0 | 0 | 0 | 0 | 0 | 0.07 | 0.6
KY | KY - EAST | 2631 | 22026229700 |  |  |  | 7360244A | 2292560 | GSULLI1 |  | 588 | VO | EMER-REPLACE METER | 2631M | US23--ASHLAND OIL | US23--ASHLAND OIL | 019 | CAT | 2022-12-12 |  | GSULLI1 | 2022-10-05 | 2023-12-29 | 2023-12-31 | 2022-12-12 | DASH | 2022-12-12 | 2022-10-20 |  | F | [11 empty] | 22026216300 | 100 |  | 0.033333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22136144600 |  | 100351242 |  | 6744208N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D246266 | 2621P | HOLIDAY | 89 HOLIDAY RD | 049 | WIN | 2022-12-12 | NRICHIE | U125208 | 2022-09-30 | 2023-03-28 | 2024-09-30 |  | NRICHIE | 2022-12-12 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 3.25 | 3 | 1056.16 | 257.73 | 86.38 | 82.95 | 629.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22138659800 |  | 100324400 |  | 6720204E |  |  |  | 565 | EX | SERVICE LINE - LOCATE/REPLACE | 2621P | MILANO | 3542 MILANO RD | 067 | LEX | 2022-12-12 | MCRAIG | U125208 | 2022-10-12 | 2022-10-27 | 2022-11-02 |  | MCRAIG | 2022-12-12 | 2022-11-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 37.3833 | 9 | 3635.03 | 2653.91 | 506.54 | 376.68 | 97.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22148337700 |  | 100274471 |  | 6684228J | 1313370 |  |  | 565 | EX | REPLACE SL | 2621P | SHELBY | 410 SHELBY ST | 073 | FRA | 2022-12-13 | U930915 | U132823 | 2022-12-09 | 2023-02-28 |  |  | CHERNDO | 2022-12-12 | 2022-12-09 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 47 | 6 | 5246.67 | 3622.33 | 117 | 305.88 | 1201.46 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22148532100 |  | 100344901 |  | 6700224O |  |  |  | 565 | EX | REPLACE SERVICE | 2621P | STEPHENS | 112 E STEPHENS ST | 239 | MID | 2022-12-12 | U128410 | U132864 | 2022-12-12 | 2022-12-12 |  |  | CDESPAIN | 2022-12-12 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.0667 | 1 | 4932.17 | 391.46 | 790.23 | 20.43 | 3730.05 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22148617600 |  | 100462453 |  | 6696212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BERLIN | 539 BERLIN DR | 239 | VER | 2022-12-13 | U930915 | U132864 | 2022-12-12 | 2022-12-12 | 2022-12-12 |  | DCOLLIN | 2022-12-12 | 2022-12-12 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8.9667 | 2 | 1452.66 | 721.74 | 209.1 | 37.66 | 484.16 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979024600 |  | 100263397 |  | 7352256B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OHIO | 2861 OHIO ST | 019 | ASH | 2022-12-12 | U124015 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | ORA SLONE | 2022-12-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.4667 | 1 | 1685.4 | 184.32 | 0 | 42.38 | 1458.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22979032300 |  | 100290313 |  | 6720212B | 0146583 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LIMESTONE | 1410 N LIMESTONE ST | 067 | LEX | 2022-12-12 | U461375 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | LARRY BROWN | 2022-12-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.5 | 1 | 4074.95 | 494.13 | 0 | 439.99 | 3140.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 04564709500 |  | 100462437 |  | 6712204D | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 2 | 2621P | HOLWYN | 3340 HOLWYN RD | 067 | LEX | 2022-12-14 | U126603 | SSUTHER | 2004-02-02 | 2022-07-01 | 2022-12-31 |  | SHAWN DENNIS | 2022-12-13 | 2022-12-08 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 1746.09 | 583.56 | 0 | 136.13 | 1026.4 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 07687306500 |  | 100358914 |  | 6736232L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | GANO | 443 GANO ST | 017 | PAR | 2022-12-14 | U126603 | DMCCULL | 2007-05-16 | 2022-07-01 | 2022-12-31 |  | SHAWN DENNIS | 2022-12-13 | 2022-11-15 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.6167 | 1 | 1864.84 | 308.84 | 0 | 69.92 | 1486.08 | 0 | 0 | 0
KY | KY - EAST | 2631 | 10874133400 |  | 100250042 |  | 7360252M | 1533898 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | LOUISA | 3150 LOUISA ST | 019 | CAT | 2022-12-13 | U124015 | U906609 | 2010-12-27 | 2022-12-13 | 2022-12-31 |  | ORA SLONE | 2022-12-13 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.1833 | 1 | 1910.68 | 235.61 | 0 | 54.17 | 1620.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11890748700 |  | 100293816 |  | 6720212A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BROADWAY | 909 N BROADWAY ST | 067 | LEX | 2022-12-13 | U127206 | U906609 | 2011-02-21 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-12-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 3353.92 | 0 | 0 | 0 | 3353.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11890749200 |  | 100293815 |  | 6720212A |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2600B | BROADWAY | 911 N BROADWAY ST | 067 | LEX | 2022-12-13 | U127206 | U906609 | 2011-02-21 | 2020-12-31 |  |  | JUSTIN HOBBS | 2022-12-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 11891653100 |  | 100438725 |  | 6716208N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NICHOLASVILLE | 2553 NICHOLASVILLE RD L1 | 067 | LEX | 2022-12-13 | U126532 | U123933 | 2011-02-23 | 2022-07-01 | 2022-12-31 |  | DDAVIS | 2022-12-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 17 | 2 | 2740.09 | 1272.03 | 0 | 66.41 | 1401.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11891655500 |  | 100438210 |  | V-930-61 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NICHOLASVILLE | 2553 NICHOLASVILLE RD 180 | 067 | LEX | 2022-12-13 | U126532 | U123933 | 2011-02-23 | 2022-07-01 | 2022-12-31 |  | LESLIE SHARON | 2022-12-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1399 | 0 | 0 | 0 | 1399 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11891655800 |  | 100438728 |  | 6716208N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NICHOLASVILLE | 2553 NICHOLASVILLE RD L4 | 067 | LEX | 2022-12-13 | U126532 | U123933 | 2011-02-23 | 2022-07-01 | 2022-12-31 |  | DDAVIS | 2022-12-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1401.65 | 0 | 0 | 0 | 1401.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11915922100 |  | 100249118 |  | 7328284B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | STATE RT 7 | 1216 STATE RT 7 | 089 | S S | 2022-12-13 | U126286 | U124964 | 2011-07-14 | 2022-07-01 | 2022-12-31 |  | TYLER ALLISON | 2022-12-13 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 10 | 1 | 2388.1 | 734.75 | 0 | 38.35 | 1615 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12968016100 |  | 100327825 |  | 6720212N |  |  |  | 566 | EX | SOII - METER ABANDON ONLY | 2621P | IRVINE | 104 IRVINE RD FURN | 067 | LEX | 2022-12-14 | U930915 | U124967 | 2012-05-02 | 2014-12-23 |  |  | LSTANFI | 2022-12-13 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.1 | 1 | 10.7 | 7.84 | 0 | 2.86 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12968035200 |  | 100433431 |  | 6720212N |  |  |  | 566 | EX | SOII - METER ABANDON ONLY | 2621P | IRVINE | 104 IRVINE RD 5 | 067 | LEX | 2022-12-14 | U930915 | U124967 | 2012-05-02 | 2014-12-23 |  |  | LSTANFI | 2022-12-13 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.2 | 1 | 21.43 | 15.72 | 0 | 5.71 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12975908000 |  | 100441520 |  | 6720212M | 2176779 |  |  | 566 | EX | METER ABANDON W/21-0269938-00 | 2600B | HIGH | 508 E HIGH ST | 067 | LEX | 2022-12-13 | U126309 | U123854 | 2012-06-11 | 2022-12-15 | 2022-12-15 |  | JAMIE LYNN | 2022-12-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 12998429900 |  | 100340238 |  | 16720212H |  |  |  | 566 | EX | MTR ABANDON / RA 12-07-2010 | 2621P | ARUNDEL | 1840 ARUNDEL DR 1FL | 067 | LEX | 2022-12-30 | U128711 | U125208 | 2012-11-14 | 2049-12-31 |  |  | KKINDER | 2022-12-13 | 2022-12-09 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.1667 | 5 | 982.55 | 933.76 | 0 | 48.79 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 13157533800 |  | 100320318 |  | 16716208G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NICHOLASVILLE | 1740 NICHOLASVILLE RD | 067 | LEX | 2022-12-13 | U126284 | U461383 | 2013-08-23 | 2022-07-01 | 2022-12-31 |  | JOSH PASLEY | 2022-12-13 | 2022-10-07 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.45 | 2 | 4765.94 | 351.15 | 0 | 76.07 | 4338.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 16438384700 |  | 100438727 |  | 6716208N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NICHOLASVILLE | 2553 NICHOLASVILLE RD L3 | 067 | LEX | 2022-12-13 | U126532 | U122906 | 2016-08-30 | 2022-07-01 | 2022-12-31 |  | DDAVIS | 2022-12-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1401.65 | 0 | 0 | 0 | 1401.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883107900 |  | 100445053 |  | 6716220A | 1530969 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 2 | 2621P | GEORGETOWN | 4130 GEORGETOWN RD I2 | 067 | LEX | 2023-01-11 | U126308 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-12-13 | 2022-11-03 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.6 | 1 | 686.64 | 40.05 | 0 | 2.34 | 644.25 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883109900 |  | 500516898 |  | 7348252D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | SUMMIT | 539< SUMMIT RD | 019 | ASH | 2022-12-15 | U124015 | U120245 | 2021-01-30 | 2022-12-13 | 2022-12-31 |  | ORA SLONE | 2022-12-13 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.85 | 1 | 1539.09 | 65.36 | 0 | 15.03 | 1458.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883115000 |  | 100301356 |  | 6712212H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | RUGBY | 223 RUGBY RD | 067 | LEX | 2022-12-13 | U461375 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | LARRY BROWN | 2022-12-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.5 | 1 | 4998.12 | 266.05 | 0 | 236.92 | 4495.15 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883140800 |  | 100461815 |  | 6720212J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 7TH | 769 E 7TH ST | 067 | LEX | 2022-12-13 | U127206 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-12-13 | 2021-12-17 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16 | 3 | 9981.2 | 1324.66 | 0 | 183.39 | 8473.15 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883236900 |  | 100295027 |  | 6716212H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BROADWAY | 415 N BROADWAY ST | 067 | LEX | 2022-12-13 | U127206 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-12-13 | 2022-09-23 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.1833 | 4 | 2786.62 | 607.28 | 0 | 32.8 | 2146.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883316100 |  | 100336078 |  | 6720212J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 7TH | 767 E 7TH ST B | 067 | LEX | 2022-12-13 | U127206 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JUSTIN HOBBS | 2022-12-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 321.94 | 0 | 0 | 0 | 321.94 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21884240700 |  | 100242301 |  | 7356252H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MITCHELL | 1139 MITCHELL ST | 019 | CAT | 2022-12-13 | U124015 | U128293 | 2021-02-04 | 2022-12-13 | 2022-12-31 |  | ORA SLONE | 2022-12-13 | 2022-12-13 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.75 | 1 | 1508.86 | 204.36 | 0 | 47 | 1257.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960242900 |  | 100320965 |  | 6720212M | 2176779 |  |  | 566 | EX | ABANDON SL W/CAPITAL JOB | 2600B | WOODLAND | 200 WOODLAND AV | 067 | LEX | 2022-12-13 | U126309 | U134723 | 2021-12-17 | 2022-12-30 |  |  | JAMIE LYN | 2022-12-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1 | 1368.31 | 0 | 0 | 0 | 1368.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960253700 |  | 100327194 |  | 6716212P | 2176779 |  |  | 566 | EX | ABANDON SL W/CAPTIOL JOB | 2600B | HIGH | 419 E HIGH ST 2F | 067 | LEX | 2022-12-13 | U126309 | U134723 | 2021-12-17 | 2022-12-30 |  |  | JAMIE LYNN | 2022-12-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 21960254100 |  | 100441880 |  | 6720212M | 2176779 |  |  | 566 | EX | ABANDON SL W/CAPTIOL JOB | 2600B | HIGH | 520 E HIGH ST | 067 | LEX | 2022-12-13 | U461375 | U134723 | 2021-12-17 | 2022-12-30 |  |  | LARRY BROWN | 2022-12-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 4.5 | 1 | 1532.93 | 342.06 | 0 | 304.61 | 886.26 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21960254300 |  | 100321004 |  | 6716212P | 2176779 |  |  | 566 | EX | ABANDON SL W/CAPTIOL JOB | 2600B | MAXWELL | 325 E MAXWELL ST 1 | 067 | LEX | 2022-12-13 | U126309 | U134723 | 2021-12-17 | 2022-12-30 |  |  | JAMIE LYNN | 2022-12-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 21960254800 |  | 100442173 |  | 6716212P | 2176779 |  |  | 566 | EX | ABANDON SL W/CAPTIOL JOB | 2600B | MAXWELL | 445 E MAXWELL ST 3F-5 | 067 | LEX | 2022-12-14 | U126309 | U134723 | 2021-12-17 | 2022-12-30 |  |  | JAMIE LYNN | 2022-12-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 21960254900 |  | 100320993 |  | 6716212P | 2176779 |  |  | 566 | EX | ABANDON SL W/CAPTIOL JOB | 2600B | MAXWELL | 445 E MAXWELL ST W-HEAT | 067 | LEX | 2022-12-14 | U126309 | U134723 | 2021-12-17 | 2022-12-30 |  |  | JAMIE LYNN | 2022-12-13 | 2022-05-09 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 8 | 1 | 1838.47 | 443.51 | 0 | 26.65 | 1368.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026242500 |  |  |  | 6716224M | 1530969 | U461383 |  | 560 | EX | EMER-RETIRE 385' OF 2"/3"PAIP | 2600B | GEORGETOWN | 4130 GEORGETOWN RD | 067 | LEX | 2022-12-22 | U128132 | U461383 | 2022-12-09 | 2022-12-29 | 2022-12-31 | 2022-12-12 | JENSMINGER | 2022-12-13 | 2022-12-12 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00560 | 3200560 |  |  | WP2425 |  |  | 100 | 056032220262425 | 27 | 0 | 5628.45 | 2186.75 | 0 | 1834.66 | 1607.04 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129003800 |  | 500178324 |  | 6752244J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAYSVILLE | 2199 MAYSVILLE RD | 181 | CAR | 2022-12-13 | U126604 | U130722 | 2022-09-05 | 2022-12-30 |  |  | WILL FULKS | 2022-12-13 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 3058.01 | 0 | 0 | 0 | 3058.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22138660500 |  | 100324398 |  | 6720204E |  |  |  | 565 | EX | SERVICE LINE - LOCATE/REPLACE | 2621P | MILANO | 3550 MILANO RD | 067 | LEX | 2022-12-13 | TROE | U125208 | 2022-10-12 | 2022-10-27 | 2022-11-02 |  | TROE | 2022-12-13 | 2022-10-24 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 35.35 | 7 | 3754.32 | 2504.86 | 607.29 | 545.37 | 96.8 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22142592100 |  | 500725700 |  | 7356252H | 2292662 |  |  | 566 | EX | RETIRE 76'-2/3" CSMP | 2621P | CENTER | 74 CENTER ST | 019 | CAT | 2022-12-28 | U132761 | U132280 | 2022-11-02 | 2022-11-28 | 2022-12-25 |  | DESKAGG | 2022-12-13 | 2022-12-12 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 |  |  | 100 | 056632B26310043 | 17.25 | 2 | 1535.05 | 1357.33 | 0 | 177.72 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22146184400 |  | 100307360 |  | 6716212J |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | ANGLIANA | 842 ANGLIANA AV | 067 | LEX | 2022-12-13 | HMCKUNE | U125208 | 2022-11-23 | 2022-11-29 | 2022-12-15 |  | HMCKUNE | 2022-12-13 | 2022-12-05 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 24.7833 | 5 | 1606.38 | 1504.98 | 22.84 | 78.56 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22148697900 |  | 100244265 |  | 7356256J |  |  |  | 565 | EX | SERVICE LINE - REPLACE D188396 | 2621P | OLD ORCHARD | 3627 OLD ORCHARD DR | 019 | ASH | 2022-12-28 | U132761 | U129939 | 2022-12-13 | 2022-12-13 | 2022-12-13 |  | JDICKES | 2022-12-13 | 2022-12-13 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 19.55 | 4 | 2443.41 | 1522.96 | 197.31 | 665.94 | 57.2 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22148729000 |  | 100345570 |  | 6696212L |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LOCUST | 142 N LOCUST ST | 239 | VER | 2022-12-14 | U128410 | U129939 | 2022-12-13 | 2022-12-13 |  |  | CDESPAIN | 2022-12-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 10 | 1 | 4392.04 | 775.1 | 386.1 | 34.72 | 3196.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22148814400 |  | 100353369 |  | 7256280G |  | U129939 |  | 566 | EX | ABANDON SERVICE LINE | 2621P | 2ND | 564 W 2ND ST | 161 | MAY | 2022-12-14 | U930915 | U129939 | 2022-12-13 | 2022-12-13 |  |  | SDADAMS | 2022-12-13 | 2022-12-13 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 7.95 | 2 | 1217.3 | 1141.63 | 16.08 | 59.59 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12975854100 |  | 100327739 |  | 6720212M |  |  |  | 566 | EX | SOII - METER ABANDON ONLY | 2621P | DESHA | 206 DESHA RD 3 | 067 | LEX | 2022-12-14 | U930915 | U123854 | 2012-06-11 | 2014-12-23 |  |  | LSTANFI | 2022-12-14 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.43333 | 4 | 30.47 | 26.63 | 0 | 3.84 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21897157600 |  | 100353477 |  | 7256280K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | 2ND | 228 W 2ND ST | 161 | MAY | 2022-12-14 | U127414 | U124841 | 2021-03-25 | 2021-12-30 | 2022-12-31 |  | ED FOX | 2022-12-14 | 2022-12-13 |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 8 | 1 | 2413.59 | 568.26 | 0 | 135.33 | 1710 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026232100 |  |  |  | 6716208P |  | U461383 |  | 584 | EX | RETIRE PAPER GAUGE | 2621M | LANSDOWNE | 3301 LANSDOWNE DR | 067 | LEX | 2022-12-21 | U123258 | U461383 | 2022-10-17 | 2023-12-15 | 2023-12-15 | 2022-12-01 | CMCHOLAN | 2022-12-14 | 2022-12-02 |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00584 | 3200584 |  |  | WP2321 |  |  | 100 | 058432220262321 | 5.5 | 0 | 719.12 | 471.45 | 0 | 247.67 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22148316500 |  | 100250365 |  | 7340268N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | STATE RT 1 | 1173 STATE RT 1 | 089 | GRE | 2022-12-14 | JDICKES | U132823 | 2022-12-09 | 2022-12-06 |  |  | JDICKES | 2022-12-14 | 2022-12-14 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 5.4667 | 2 | 1073.64 | 401.82 | 274.94 | 369.38 | 27.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22148747400 |  | 100296078 |  | 6716216O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | DEPORRES | 972 DEPORRES AV | 067 | LEX | 2022-12-16 | U132761 | U129939 | 2022-12-13 | 2022-12-12 | 2022-12-30 |  | LSTANFI | 2022-12-14 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.0333 | 4 | 596.29 | 318.34 | 187.39 | 21.26 | 69.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22148779500 |  | 100315982 |  | 6716208F |  |  |  | 565 | EX | GRADE 1 REPLACE SERVICE LINE | 2621P | SUBURBAN | 135 SUBURBAN CT | 067 | LEX | 2022-12-14 | U930915 | U129939 | 2022-12-13 | 2022-12-13 | 2022-12-13 |  | LSTANFI | 2022-12-14 | 2022-12-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.9667 | 5 | 1574.05 | 1160.7 | 201.17 | 127.48 | 84.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22148882500 |  | 500363221 |  | 7244280E | 9505572 |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | KY HIGHWAY 10 | 4223 KY HIGHWAY 10 | 161 | DOV | 2022-12-14 | U930915 | U129939 | 2022-12-14 | 2022-12-14 |  |  | SDADAMS | 2022-12-14 |  |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26320031 | 0.7 | 1 | 1636.67 | 1155.91 | 350 | 60.36 | 70.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22148907700 |  | 100459200 |  | 6684228H |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | HUDSON | 415 HUDSON ST | 073 | FRA | 2022-12-14 | U126308 | U125763 | 2022-12-14 | 2022-12-30 |  |  | J ENSMINGER | 2022-12-14 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2623 | 22979029300 |  | 100276509 |  | 6684228H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HOLMES | 546 HOLMES ST NS | 073 | FRA | 2022-12-14 | U126308 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | J ENSMINGER | 2022-12-14 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2621 | 03534410900 |  | 100317191 |  | 6716208N | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NICHOLASVILLE | 2483 NICHOLASVILLE RD | 067 | LEX | 2022-12-15 | U129722 | DMCCULL | 2003-03-21 | 2022-07-01 | 2022-12-31 |  | M YOUNG | 2022-12-15 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.2833 | 1 | 1557.5 | 602.52 | 0 | 140.56 | 814.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 04589671800 |  | 100334687 |  | 6720208D | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 2 | 2621P | LIBERTY | 2156 LIBERTY RD | 067 | LEX | 2022-12-15 | U126308 | SSUTHER | 2004-10-15 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-12-15 | 2022-10-31 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.4167 | 3 | 9166.42 | 930.5 | 14.45 | 623.54 | 7597.93 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11891657100 |  | 100317202 |  | 6716208N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | NICHOLASVILLE | 2553 NICHOLASVILLE RD J | 067 | LEX | 2022-12-15 | U129731 | U123933 | 2011-02-23 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2022-12-15 | 2022-11-28 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 29 | 3 | 5642.88 | 2110.12 | 0 | 1068.98 | 2463.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11894377400 |  | 100286679 |  | 6720212I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 3RD | 403 E 3RD ST | 067 | LEX | 2022-12-15 | U126284 | U906307 | 2011-03-04 | 2022-07-01 | 2022-12-31 |  | JOSH PASLEY | 2022-12-15 | 2022-09-07 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10.5167 | 4 | 8194.03 | 841.99 | 0 | 681.4 | 6670.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18026848701 |  |  |  | 6728204M | 1961267 | U122858 |  | 909 | EX | STATION UPGRADES (SEP RELATED) | 2600E | ATHENS BOONESBORO | 4940 ATHENS BOONESBORO RD | 067 | LEX | 2022-12-22 | U125936 | U122858 | 2019-02-06 | 2019-12-23 | 2019-12-31 | 2022-12-15 | AJPARKS | 2022-12-15 | 2021-05-07 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP8487 |  |  | 100 | 090932180268487 | 92.3667 | 0 | 206545.63 | 4944.68 | 141786.31 | 1704 | 45591.68 | 0 | 12518.96 | 0
KY | KY - CENTRAL | 2629 | 20026940900 |  |  |  | 6740232J | 2177768 | U122858 |  | 909 | EX | INSTALL I&C EQUIPMENT | 2600E | PARIS BYPASS | PARIS BYPASS | 017 | PAR | 2022-12-27 | U123258 | U122858 | 2020-03-27 | 2021-12-28 | 2021-12-31 | 2022-12-15 | JBRADFORD | 2022-12-15 | 2022-02-18 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00909 | 3200909 |  |  | WP9409 |  |  | 100 | 090932200269409 | 13.6833 | 0 | 12849.77 | 751.61 | 0 | 76.84 | 11400 | 0 | 621.32 | 0
KY | KY - CENTRAL | 2629 | 20026941000 |  |  |  | 6740232J | 2177768 | U122858 |  | 584 | EX | RETIRE GAUGE | 2629M | PARIS BYPASS | PARIS BYPASS | 017 | PAR | 2022-12-27 | U123258 | U122858 | 2020-03-27 | 2023-12-29 | 2023-12-31 | 2022-12-15 | JBRADFORD | 2022-12-15 | 2022-02-18 |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00584 | 3200584 |  |  | WP9410 |  |  | 100 | 058432200269410 | 20.1167 | 0 | 1582.1 | 1356.21 | 0 | 225.89 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21026120600 |  |  |  | 7352256B | 2176770 | U461383 |  | 584 | EX | RETIRE REG STATION WITH AMRP | 2631M | BUCKLEY | 419 BUCKLEY RD | 019 | ASH | 2022-12-21 | U123258 | U461383 | 2021-04-29 | 2022-12-30 | 2022-12-31 | 2022-12-15 | DASH | 2022-12-15 | 2022-11-09 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00584 | 3200584 |  |  | WP1206 | AMRCB |  | 100 | 058432210261206 | 13.6833 | 0 | 1058.49 | 1003.32 | 0 | 55.17 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21874918600 |  | 100353562 |  | 7256280K | 2180424 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | LEXINGTON | 340 LEXINGTON PK | 161 | MAY | 2022-12-15 | U126286 | U123981 | 2021-01-15 | 2022-12-30 |  |  | TYLER ALLISON | 2022-12-15 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26320043 |  | 1
KY | KY - EAST | 2631 | 21883165800 |  | 100264885 |  | 7356216L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | JACKSON | 2816 E JACKSON ST | 019 | CAN | 2022-12-15 | U124015 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | ORA SLONE | 2022-12-15 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.7333 | 1 | 2145.9 | 276.47 | 0 | 14.43 | 1855 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883245400 |  | 100289957 |  | 6720212C |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BRYAN STATION | 1705 BRYAN STATION RD | 067 | LEX | 2022-12-15 | U461375 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | LARRY BROWN | 2022-12-15 | 2022-12-14 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16 | 2 | 7455.09 | 1216.3 | 0 | 1083.06 | 5155.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883328700 |  | 100338121 |  | 6720212F | 2074752 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | 7TH | 428 E 7TH ST | 067 | LEX | 2022-12-15 | U127206 | U120245 | 2021-01-30 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-12-15 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1 | 443.13 | 0 | 0 | 0 | 443.13 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026175300 |  |  |  | 6740232I | 2292664 | U128885 |  | 584 | EX | RETIRE R-1278 | 2629M | HIGGINS | HIGGINS ST | 017 | PAR | 2023-04-04 | U123258 | U128885 | 2022-03-10 | 2023-12-28 | 2023-12-31 | 2022-12-15 | JBRADFORD | 2022-12-15 | 2022-12-15 |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00584 | 3200584 |  |  | WP1753 | AMRCB |  | 100 | 058432220261753 | 21.6167 | 0 | 1891.36 | 1268.49 | 0 | 622.87 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22026210700 |  |  |  | 7352256B | 2176770 | U461383 |  | 586 | EX | RETIRE METAL BUILDING | 2631M | BUCKLEY | 419 BUCKLEY RD | 019 | ASH | 2022-12-21 | U123258 | U461383 | 2022-07-11 | 2023-01-31 | 2023-01-31 | 2022-12-15 | DASH | 2022-12-15 |  |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00586 | 3200586 |  |  | WP2107 |  |  | 100 | 058632220262107 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026227200 |  |  |  | 6728204M | 1961267 | U461383 |  | 910 | EX | RETIRE ELECTRONICS | 2600E | ATHENS BOONESBORO | 4940 ATHENS BOONESBORO RD | 067 | LEX | 2022-12-22 | U125936 | U461383 | 2022-09-27 | 2023-12-29 | 2023-12-31 | 2022-12-15 | AJPARKS | 2022-12-15 |  |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00910 | 3200910 |  |  | WP2272 |  |  | 100 | 091032220262272 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22026230800 |  |  |  | 7348260G | 2294008 | U122858 |  | 558 | EX | EMER - RETIRE 3'-2" P-IP | 2621P | TONI | 215 TONI DR C | 089 | RUS | 2022-12-31 | U128132 | U132280 | 2022-10-11 | 2022-10-06 | 2022-10-06 | 2022-10-06 | MCOLLET | 2022-12-15 | 2022-12-07 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP2308 |  |  | 100 | 055832220262308 | 4.7 | 0 | 1400.06 | 585.32 | 27.34 | 787.4 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22026232200 |  |  |  | 7356252H | 2292662 | U132280 |  | 587 | EX | INSTALL SKID MOUNTED GMB | 2631M | CENTER | CENTER ST | 019 | CAT | 2023-01-18 | U123258 | U132280 | 2022-10-18 | 2022-12-22 | 2022-12-31 | 2022-12-15 | DASH | 2022-12-15 | 2022-11-29 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00587 | 3200587 |  |  | WP2322 |  |  | 100 | 058732220262322 | 157.7667 | 115 | 40259.26 | 16068.61 | 1367.44 | 4835.86 | 14906.41 | 0 | 110.62 | 2970.32
KY | KY - EAST | 2631 | 22026232300 |  |  |  | 7356252H | 2292662 | U132280 |  | 588 | EX | RETIRE GMB SETTING | 2631M | CENTER | CENTER ST | 019 | CAT | 2023-01-18 | U123258 | U132280 | 2022-10-18 | 2022-12-30 | 2022-12-31 | 2022-12-15 | DASH | 2022-12-15 | 2022-11-01 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00588 | 3200588 |  |  | WP2323 |  |  | 100 | 058832220262323 | 17.0667 | 0 | 1984.01 | 1216.48 | 0 | 767.53 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22026235800 |  |  |  | 7320284K | 2293579 | U122858 |  | 557 | EX | EMER - INSTALL 3'-4" PMMP | 2621P | OLD LOCKANDDAM | OLD LOCKANDDAM | 135 | FIR | 2023-01-03 | U128132 | U132280 | 2022-11-11 | 2023-07-20 |  | 2022-10-10 | MCOLLET | 2022-12-15 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP2358 |  |  | 100 | 055732220262358 | 0.41667 | 3 | 7089.71 | 2648.7 | 0 | 1177.04 | 2887.6 | 0 | 0 | 376.37 | 3
KY | KY - EAST | 2631 | 22026235900 |  |  |  | 7320284K | 2293579 | U122858 |  | 558 | EX | EMER - RETIRE 3'-4" P-MP | 2621P | OLD LOCKANDDAM | OLD LOCKANDDAM | 135 | FIR | 2022-12-21 | U128132 | U132280 | 2022-11-11 | 2023-07-31 |  | 2022-10-10 | MCOLLET | 2022-12-15 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP2359 |  |  | 100 | 055832220262359 | 0.35 | 0 | 22647.66 | 16011.34 | 66.18 | 6570.14 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22026241300 |  |  |  | 7340268N | 2294069 | U122858 |  | 557 | EX | EMER - INSTALL 5'-4" PMMP | 2621P | STATE RT 1 | 1173 STATE RT 1 | 089 | GRE | 2023-01-09 | U128132 | U122858 | 2022-12-06 | 2023-08-29 | 2023-08-31 | 2022-12-06 | MCOLLET | 2022-12-15 | 2022-12-14 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP2413 |  |  | 100 | 055732220262413 | 10.6167 | 6 | 1144.39 | 910.53 | 0 | 171.15 | 0 | 0 | 2.07 | 60.64 | 3
KY | KY - EAST | 2631 | 22026241400 |  |  |  | 7340268N | 2294069 | U122858 |  | 558 | EX | EMER - RETIRE 5'-4" PMP | 2621P | STATE RT 1 | STATE RT 1 | 089 | GRE | 2022-12-30 | U128132 | U122858 | 2022-12-06 | 2023-08-31 | 2023-08-31 | 2022-12-06 | MCOLLET | 2022-12-15 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP2414 |  |  | 100 | 055832220262414 | 0.45 | 0 | 91.78 | 39.14 | 0 | 52.64 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129023900 |  | 100353778 |  | 7256280L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 2ND | 46 W 2ND ST | 161 | MAY | 2022-12-15 | SDADAMS | U130722 | 2022-09-05 | 2022-12-30 |  |  | SDADAMS | 2022-12-15 | 2022-12-12 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 18.4333 | 3 | 1538.22 | 1446.66 | 16.08 | 75.48 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22144381900 |  | 100340137 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER | 2621D | HI CREST | 720 HI CREST DR A | 067 | LEX | 2022-12-15 | MCRAIG | AOC SYST | 2022-11-14 | 2022-12-12 | 2023-01-11 |  | MCRAIG | 2022-12-15 | 2022-12-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 24 | 3 | 2622.85 | 1631.01 | 487.7 | 474.44 | 29.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22149025400 |  | 100336814 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL/LGCY | 2600B | 4TH | 141 E 4TH ST 1F | 067 | LEX | 2022-12-15 | U127206 | U125763 | 2022-12-15 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-12-15 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.85 | 1 | 868.74 | 404.49 | 0 | 21.12 | 443.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22149058300 |  | 500962945 |  | 6720212I |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | 3RD | 132 E 3RD ST 102 | 067 | LEX | 2022-12-15 | U127206 | U125763 | 2022-12-15 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-12-15 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1731.88 | 0 | 0 | 0 | 1731.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22149058500 |  | 500962946 |  | 6720212I |  |  |  | 566 | EX | ABANDN SL/LGCY | 2600B | 3RD | 132 E 3RD ST 201 | 067 | LEX | 2022-12-15 | U127206 | U125763 | 2022-12-15 | 2022-12-30 |  |  | JUSTIN HOBBS | 2022-12-15 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 22149123800 |  | 100333559 |  | 6720212I |  |  |  | 565 | EX | RPLC SL/ | 2600B | 3RD | 128 E 3RD ST | 067 | LEX | 2022-12-15 | U129722 | U125763 | 2022-12-15 | 2022-12-30 |  |  | M YOUNG | 2022-12-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 4.7167 | 1 | 3495.14 | 345.82 | 236.63 | 80.68 | 2832.01 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979025600 |  | 100264826 |  | 7348248H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MIDLAND TRAIL | 11520 MIDLAND TRAIL RD | 019 | CAN | 2022-12-15 | U125566 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | DESKAGG | 2022-12-15 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.7333 | 1 | 1116.61 | 214.4 | 0 | 47.11 | 855.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979027600 |  | 100268138 |  | 7356256C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WINCHESTER | 2749 WINCHESTER AV | 019 | ASH | 2022-12-15 | U125566 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | DESKAGG | 2022-12-15 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.75 | 1 | 1409.89 | 454.83 | 0 | 99.96 | 855.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22979046600 |  | 100430052 |  | 6716208N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NICHOLASVILLE | 2419 NICHOLASVILLE RD | 067 | LEX | 2022-12-15 | U129722 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | M YOUNG | 2022-12-15 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1355.08 | 0 | 0 | 0 | 1355.08 | 0 | 0 | 0
KY | KY - EAST | 2631 | 16026666400 |  |  |  | 7360244M | 1640097 | U132280 |  | 587 | EX | INSTALL NEW CWT HEATER | 2630M | OLD US 23 | 15035 E OLD US 23 | 019 | CAT | 2023-03-22 | U125936 | BKSLONE | 2016-09-06 | 2023-12-14 | 2023-12-31 | 2022-03-03 | DASH | 2022-12-16 | 2022-01-26 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00587 | 3200587 |  |  | WP6664 |  |  | 100 | 058732160266664 | 438.45 | 110 | 188315.11 | 29284.08 | 74726.32 | 3613.66 | 60812.88 | 0 | 1801.08 | 18077.09
KY | KY - CENTRAL | 2632 | 21874917200 |  | 100456638 |  | 7256276A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | KENTON STATION | 752 KENTON STATION RD | 161 | MAY | 2022-12-16 | U127414 | U123981 | 2021-01-15 | 2022-07-01 | 2022-12-31 |  | ED FOX | 2022-12-16 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 3.5 | 1 | 307.8 | 248.6 | 0 | 59.2 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21874917900 |  | 100354030 |  | 7256280P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | 4TH | 3 W 4TH ST | 161 | MAY | 2022-12-16 | U126286 | U123981 | 2021-01-15 | 2022-07-01 | 2022-12-31 |  | DAVID STAGGS | 2022-12-16 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 12.5 | 2 | 954.82 | 907.46 | 0 | 47.36 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883304900 |  | 100245712 |  | 7360252I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 26TH | 203 26TH ST | 019 | CAT | 2022-12-16 | U124015 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | ORA SLONE | 2022-12-16 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 945.64 | 0 | 0 | 0 | 945.64 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883305100 |  | 100245908 |  | 7360252I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | WALNUT | 2108< WALNUT ST | 019 | CAT | 2022-12-16 | U124015 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | ORA SLONE | 2022-12-16 | 2022-12-14 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 9.1 | 2 | 2275.98 | 676.33 | 0 | 140.95 | 1458.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026232600 |  | 501338646 |  | 6764176K | 2292946 | U128885 |  | 555 | EX | INSTALL 200'-2" PMMP | 2600B | GENEVA | 325 GENEVA AV | 065 | IRV | 2023-01-06 | U128132 | U128885 | 2022-10-19 | 2023-01-23 | 2023-01-26 | 2022-12-16 | R.HUMPHREYS | 2022-12-16 | 2022-12-13 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP2326 |  |  | 100 | 055532220262326 | 44.25 | 996 | 20049.03 | 3098.06 | 1435.26 | 640.56 | 13789.02 | 0 | 31.14 | 1054.99 | 166
KY | KY - EAST | 2631 | 22026245500 |  |  |  | 7360244A | 2070383 | U132280 |  | 577 | EX | INSTALL REG STATION BUILDING | 2631M | US23--ASHLAND OIL | US23--ASHLAND OIL | 019 | CAT | 2023-01-20 | U123258 | U132280 | 2022-12-22 | 2023-12-20 | 2023-12-25 | 2022-11-18 | DASH | 2022-12-16 |  |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00577 | 3200577 |  |  | WP2455 |  |  | 100 | 057732220262455 |  | 1 | 12285 | 0 | 0 | 0 | 10500 | 0 | 0 | 1785
KY | KY - CENTRAL | 2632 | 22104080300 |  | 100354029 |  | 7256280P |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2600B | MARKET | 325 MARKET ST | 161 | MAY | 2022-12-16 | U127414 | U134723 | 2022-05-31 | 2022-07-01 | 2022-12-31 |  | DAVID STAGGS | 2022-12-16 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1
KY | KY - EAST | 2631 | 23026246000 |  |  |  | 7360244A | 2070383 | U132280 |  | 587 | EX | INSTALL M&R CRANE - MARATHON | 2631M | US23--ASHLAND OIL | US23--ASHLAND OIL | 019 | CAT | 2023-01-20 | U123258 | U132280 | 2023-01-03 | 2049-12-31 |  | 2022-11-18 | DASH | 2022-12-16 |  |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00587 | 3200587 |  |  | WP2460 |  |  | 100 | 058732230262460 |  | 1 | 14182.67 | 0 | 0 | 0 | 10917.77 | 0 | 0 | 3264.9
KY | KY - EAST | 2631 | 23026246200 |  |  |  | 7348248F | 2394657 | U132280 |  | 585 | EX | INSTALL VRG - MIS FACILITY | 2631M | US 60 | US 60 | 019 | CAN | 2023-02-23 | U123258 | U132280 | 2023-01-03 | 2049-12-31 |  | 2022-11-02 | DASH | 2022-12-16 |  |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00585 | 3200585 |  |  | WP2462 |  |  | 100 | 058532230262462 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026246300 |  |  |  | 7348248F | 2394657 | U132280 |  | 586 | EX | INSTALL VRG - RETIRE MIS FAC | 2631M | US 60 | US 60 | 019 | CAN | 2023-02-23 | U123258 | U132280 | 2023-01-03 | 2049-12-31 |  | 2022-11-02 | DASH | 2022-12-16 |  |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00586 | 3200586 |  |  | WP2463 |  |  | 100 | 058632230262463 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23152891000 |  | 100339832 |  | 6720212H |  |  |  | 565 | VO | REPLACE SERVICE LINE - D311158 | 2621P | MEADE | 1576 MEADE CT 1 | 067 | LEX | 2023-02-07 |  | U125208 | 2023-01-03 | 2023-05-01 | 2024-11-30 |  | KTURNER/JTOMAK/MPL | 2022-12-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1
KY | KY - WEST | 2621 | 11898019800 |  | 100335528 |  | 1 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | GEORGETOWN | 4123 GEORGETOWN RD | 067 | LEX | 2022-12-19 | U129673 | U124961 | 2011-03-28 | 2022-07-01 | 2022-12-31 |  | ALEX WILLIAMSON | 2022-12-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 741.06 | 0 | 0 | 0 | 741.06 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22026219600 |  | 501334026 |  | 7336272B | 2290416 | U132280 |  | 555 | EX | INSTALL 90'-2" PMIP | 2600B | YANKEES | 85 YANKEES LN | 089 | GRE | 2023-03-31 | U133347 | U132280 | 2022-08-22 | 2022-12-13 | 2022-12-18 | 2022-12-15 | MARCUS BLANKENSHIP | 2022-12-19 | 2022-12-08 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP2196 |  |  | 100 | 055532220262196 | 55.05 | 342 | 50608.23 | 4440.03 | 315.4 | 859.19 | 39578.09 | 0 | 36.56 | 5378.96 | 57
KY | KY - EAST | 2631 | 22026235200 |  | 501133177 |  | 7336272B | 2293223 | U132280 |  | 555 | EX | INSTALL 200'-2" PMIP | 2600B | BROWN | 65 BROWN LN | 089 | GRE | 2023-03-31 | U133347 | U132280 | 2022-11-09 | 2023-02-15 | 2023-02-20 | 2022-12-15 | MBLANKE/ CJH CASEY PACK | 2022-12-19 | 2022-12-15 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP2352 |  |  | 100 | 055532220262352 | 28.65 | 964 | 11987.46 | 2310.39 | 305.8 | 462.73 | 8033.8 | 0 | 17.1 | 857.64 | 241
KY | KY - EAST | 2631 | 22026240400 |  |  |  | 7352256B | 2176770 | U461383 |  | 560 | EX | PAPER ONLY - RETIRE BSIP MAIN | 2600B | OLD BUCKLEY | OLD BUCKLEY RD | 019 | ASH | 2022-12-19 | U128132 | U461383 | 2022-11-22 | 2022-12-15 | 2022-12-15 | 2022-11-17 | ORA SLONE | 2022-12-19 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00560 | 3200560 |  |  | WP2404 | AMRCB |  | 100 | 056032220262404 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22145726800 |  | 100330325 |  | 6720212N | 2292504 |  |  | 565 | EX | NBT - SERVICE LINE UPGRADE | 2621P | KINGSWAY | 340 KINGSWAY DR | 067 | LEX | 2022-12-28 | U125208 | U125208 | 2022-11-21 | 2022-11-18 | 2022-12-13 |  | LSTANFI | 2022-12-19 | 2022-11-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 34.8 | 9 | 6094.35 | 2477.79 | 446.06 | 138.92 | 3031.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22149449300 |  | 100324528 |  | 6720204B | 1313369 |  |  | 565 | EX | REPLACE SL | 2621P | SUTHERLAND | 3424 SUTHERLAND DR | 067 | LEX | 2022-12-19 | LSTONE | U132823 | 2022-12-17 | 2022-12-17 | 2022-12-17 |  | LSTONE | 2022-12-19 | 2022-12-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 58.6333 | 10 | 13183.67 | 4174.7 | 85.03 | 505.52 | 8418.42 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22149489700 |  | 500250412 |  | 7352260P |  |  |  | 566 | EX | ABANDON SL-I/I/LGCY | 2600B | WINCHESTER | 601 WINCHESTER AV UNIT 10 | 019 | ASH | 2022-12-19 | DESKAGG | U134723 | 2022-12-19 | 2022-12-19 |  |  | DESKAGG | 2022-12-19 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.85 | 1 | 1321.4 | 382.29 | 0 | 84.01 | 855.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22149517400 |  | 100318651 |  | 6716204F | 1313369 |  |  | 565 | EX | REPLACE SL | 2621P | LOCH LOMOND | 118 LOCH LOMOND DR | 067 | LEX | 2022-12-19 | KKINDER | U132823 | 2022-12-19 | 2022-12-19 | 2022-12-19 |  | KKINDER | 2022-12-19 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.35 | 3 | 1819.01 | 1100.11 | 575.66 | 57.44 | 85.8 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22149633200 |  | 100254538 |  | 7348264O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | WASHINGTON | 1910 WASHINGTON ST | 089 | FLA | 2022-12-22 | DYOUNG | U136097 | 2022-12-19 | 2022-12-19 | 2022-12-19 |  | BROBERT | 2022-12-19 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 22.5333 | 3 | 2530.92 | 1685.94 | 212.92 | 594.66 | 37.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22979028400 |  | 100274714 |  | 6684228K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CAPITOL | 318 CAPITOL AV 2FR | 073 | FRA | 2022-12-19 | U129673 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | ALEX WILLIAMSON | 2022-12-19 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - CENTRAL | 2632 | 10869570300 |  | 500623893 |  | 7256280P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | 3RD | 100< E 3RD ST | 161 | MAY | 2022-12-20 | U126286 | U906314 | 2010-11-24 | 2022-07-01 | 2022-12-31 |  | DAVID STAGGS | 2022-12-20 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1
KY | KY - WEST | 2623 | 21883055800 |  | 501201568 |  | 6692228A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SCRUGGS | 36 N SCRUGGS LN | 073 | FRA | 2022-12-21 | U126309 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | JAMIE LYNN | 2022-12-20 | 2022-12-20 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 4.9833 | 2 | 1513.52 | 357.45 | 0 | 84.71 | 1071.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22147876200 |  | 100325966 |  | 6720208A |  |  |  | 565 | EX | SERVICE LINE - REPLACE /AMRSL | 2621P | COCHRAN | 310 COCHRAN RD | 067 | LEX | 2022-12-28 | U132761 | U125208 | 2022-12-06 | 2022-12-09 | 2022-12-27 |  | KKINDER | 2022-12-20 | 2022-12-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25.5333 | 3 | 2579.19 | 1844.4 | 573.62 | 96.27 | 64.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22148828900 |  | 100457867 |  | 6720208J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | NORBORNE | 2067 NORBORNE DR | 067 | LEX | 2022-12-20 | MCRAIG | U136097 | 2022-12-13 | 2022-12-16 | 2023-01-03 |  | MCRAIG | 2022-12-20 | 2022-12-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 20.9833 | 7 | 2275.78 | 1475.89 | 243.82 | 474.67 | 81.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22979028500 |  | 100274716 |  | 6684228K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CAPITOL | 316 CAPITOL AV | 073 | FRA | 2022-12-21 | U126309 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | JAMIE LYNN | 2022-12-20 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.58333 | 1 | 1122.64 | 41.46 | 0 | 9.82 | 1071.36 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979045700 |  | 100425376 |  | 7352256K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 13TH | 3700 13TH ST | 019 | ASH | 2022-12-21 | U125566 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | DESKAGG | 2022-12-20 | 2022-12-19 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 10.8667 | 2 | 2805.23 | 856.83 | 0 | 127.54 | 1820.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22996191500 |  | 100345688 |  | 6696212D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | JANET | 805 JANET ST | 239 | VER | 2022-12-21 | U128410 | AOC SYST | 2022-04-26 | 2022-10-26 | 2023-12-31 |  | CDESPAIN | 2022-12-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 |  | 1 | 2059.62 | 0 | 485.66 | 0 | 1573.96 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22996201400 |  | 100345685 |  | 6696212D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | JANET | 799 JANET ST | 239 | VER | 2022-12-20 | U128410 | AOC SYST | 2022-04-26 | 2022-10-26 | 2023-12-31 |  | CDESPAIN | 2022-12-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 4.1 | 1 | 2735.74 | 317.8 | 487.68 | 16.59 | 1913.67 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22996201700 |  | 100345689 |  | 6696212D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | JANET | 807 JANET ST | 239 | VER | 2022-12-20 | U128410 | AOC SYST | 2022-04-26 | 2022-10-26 | 2023-12-31 |  | CDESPAIN | 2022-12-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 5.8167 | 1 | 2981.37 | 451.11 | 485.66 | 23.55 | 2021.05 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21883084300 |  | 100416230 |  | NEW |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | LNXBURG FOSTER | 2139 LNXBURG FOSTER RD | 023 | FOS | 2022-12-21 | U126286 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | TYLER ALLISON | 2022-12-21 | 2022-12-14 |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 8 | 1 | 618.48 | 587.81 | 0 | 30.67 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21883221600 |  | 500465154 |  | NEW |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | CUMMSVL BERLIN | 1686 CUMMSVL BERLIN RD | 023 | BRO | 2022-12-22 | U126286 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | TYLER ALLISON | 2022-12-21 | 2022-12-14 |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 16 | 2 | 1301.51 | 1136.52 | 0 | 164.99 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22026232700 |  |  |  | 7352256K |  | U461383 |  | 588 | EX | RETIRE GMB W/22-9790457-00 | 2631M | 13TH | 3700 13TH ST | 019 | ASH | 2023-01-19 | U123258 | U461383 | 2022-10-20 | 2023-12-15 | 2023-12-15 | 2022-12-21 | DASH | 2022-12-21 |  |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00588 | 3200588 |  |  | WP2327 |  |  | 100 | 058832220262327 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22148133000 |  | 100344748 |  | 6700224P |  |  |  | 565 | EX | RELOCATE METER/REPLACE SERVICE | 2621P | GRATZ | 110 S GRATZ ST | 239 | MID | 2022-12-21 | U128410 | U132761 | 2022-12-08 | 2023-12-29 |  |  | CDESPAIN | 2022-12-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 10 | 1 | 4371.42 | 775.1 | 398.07 | 40.47 | 3157.78 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22993651000 |  | 100412023 |  | 6704208E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | JUNIPER | 191 JUNIPER DR | 239 | VER | 2022-12-21 | U126309 | AOC SYST | 2022-04-14 | 2022-10-14 | 2023-12-31 |  | JAMIE LYNN | 2022-12-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 4.6667 | 1 | 2201.11 | 333.84 | 0 | 79.11 | 1788.16 | 0 | 0 | 0
KY | KY - WEST | 2623 | 12975823700 |  | 100275001 |  | 6684228J |  |  |  | 566 | EX | SOII - METER ABANDON ONLY | 2621P | WAPPING | 407 WAPPING ST | 073 | FRA | 2022-12-22 | DCOLLIN | U123854 | 2012-06-11 | 2014-12-23 |  |  | DCOLLIN | 2022-12-22 | 2022-12-16 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 9.2667 | 3 | 1180.89 | 737.06 | 0 | 443.83 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21883061800 |  | 100271031 |  | NEW |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | PVILL HARRISON | 3303 PVILL HARRISON RD | 023 | BRO | 2022-12-22 | U126286 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | TYLER ALLISON | 2022-12-22 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1
KY | KY - CENTRAL | 2632 | 21883074900 |  | 100436225 |  | NEW |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | NEW ZION | 172 NEW ZION RD | 023 | FOS | 2022-12-22 | U126286 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | TYLER ALLISON | 2022-12-22 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21883202600 |  | 100271034 |  | NEW |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | HALEY RIDGE | 371 HALEY RIDGE RD | 023 | BRO | 2022-12-22 | U126286 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | TYLER ALLISON | 2022-12-22 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21883226800 |  | 100271078 |  | 7360 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | ASBURY | 5140 ASBURY RD | 023 | AUG | 2022-12-22 | U126286 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | TYLER ALLISON | 2022-12-22 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1
KY | KY - WEST | 2621 | 22112487700 |  | 500253044 |  | 6724208M |  |  |  | 566 | EX | ABANDON SL - DEMO/LNDMRK 12/12 | 2621P | RICHMOND | 3390 RICHMOND RD | 067 | LEX | 2022-12-22 | U930915 | U125208 | 2022-06-27 | 2022-12-09 | 2022-12-12 |  | HMCKUNE | 2022-12-22 | 2022-12-08 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.1 | 6 | 499.7 | 459.62 | 16.09 | 23.99 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22131779400 |  | 500332809 |  | 6720208D | 9403303 |  |  | 565 | EX | SERV LINE - RELOC/MTR WK 10/31 | 2621P | CODELL | 425 CODELL DR | 067 | LEX | 2022-12-22 | LSTONE | U125208 | 2022-09-16 | 2022-10-31 | 2022-11-04 |  | LSTONE | 2022-12-22 | 2022-10-25 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 74.3 | 15 | 6853.12 | 4734.12 | 208.21 | 351.19 | 1559.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22147794700 |  | 100463181 |  | 6724208M |  |  |  | 566 | EX | ABANDON SL - DEMO/LNDMRK | 2621P | RICHMOND | 3440 RICHMOND RD STE 120 | 067 | LEX | 2022-12-22 | HMCKUNE | U125208 | 2022-12-06 | 2022-12-09 | 2022-12-12 |  | HMCKUNE | 2022-12-22 | 2022-12-15 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 74.1333 | 15 | 9497.16 | 4677.7 | 47.2 | 244.21 | 4528.05 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22150308000 |  | 100258158 |  | 7348268M |  |  |  | 565 | EX | GRADE 1 SERVICE REPLACE | 2621P | 4TH | 444 4TH AV | 089 | WOR | 2022-12-28 | U132761 | U129939 | 2022-12-22 | 2022-12-22 | 2022-12-22 |  | RECUMP | 2022-12-22 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 10.9 | 2 | 1274.82 | 927.81 | 165.25 | 181.76 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22150352800 |  | 100417266 |  | 6688228A |  |  |  | 565 | EX | SERVICE LINE - REPLACE D308926 | 2621P | SCHENKEL | 418 SCHENKEL LN | 073 | FRA | 2022-12-28 | U128410 | U129939 | 2022-12-22 | 2022-12-22 | 2022-12-22 |  | CDESPAIN | 2022-12-22 | 2022-12-22 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.7167 | 1 | 4031.85 | 443.36 | 331.16 | 23.15 | 3234.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883066200 |  | 500112864 |  | 6716216O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | GEORGETOWN | 866 GEORGETOWN ST BLDG1 | 067 | LEX | 2023-01-11 | U126308 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | J ENSMINGER | 2022-12-27 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883184600 |  | 500332180 |  | 6716216O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2600B | GEORGETOWN | 866 GEORGETOWN ST BLDG3 | 067 | LEX | 2022-12-27 | U126308 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | J ENSMINGER | 2022-12-27 | 2022-06-09 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 26 | 3 | 9942.98 | 1856.09 | 0 | 1324.77 | 6762.12 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22148587300 |  | 100247062 |  | 7352256L |  |  |  | 566 | EX | ABANDON SL-DEMO/FIRE | 2621P | 29TH | 3431 S 29TH ST | 019 | ASH | 2022-12-28 | U125208 | DYOUNG | 2022-12-12 | 2022-12-15 | 2022-12-23 |  | BMEEK | 2022-12-27 | 2022-12-27 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 11.9333 | 4 | 955.86 | 899.53 | 9.37 | 46.96 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22150559600 |  | 100311925 |  | V-930-50 | 1313369 |  |  | 565 | EX | SERVICE LINE - REPLACE D310264 | 2621P | SOUTHVIEW | 2822 SOUTHVIEW DR | 067 | LEX | 2022-12-28 | U125208 | U132823 | 2022-12-27 | 2022-12-27 | 2022-12-27 |  | RJCRAWF | 2022-12-27 | 2022-12-27 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25.2167 | 4 | 1868.88 | 1561.91 | 128.63 | 81.54 | 96.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22996198800 |  | 100345710 |  | 6696212D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | JANET | 796 JANET ST | 239 | VER | 2022-12-28 | U128410 | AOC SYST | 2022-04-26 | 2022-10-26 | 2023-12-31 |  | CDESPAIN | 2022-12-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 10 | 1 | 3887.83 | 775.1 | 511.46 | 40.45 | 2560.82 | 0 | 0 | 0
KY | KY - EAST | 2631 | 06664147300 |  | 100466073 | 09 | ? |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | ROUTE 32 | ROUTE 32 | 127 | LOU | 2022-12-28 | U129673 | LDAVIS | 2006-10-25 | 2022-07-01 | 2022-12-31 |  | ALEX WILLIAMSON | 2022-12-28 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1
KY | KY - EAST | 2631 | 08726671900 |  | 100267822 |  | 7356216D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | RICE | 429 W RICE ST | 127 | LOU | 2022-12-28 | U129673 | SSUTHER | 2008-04-08 | 2022-07-01 | 2022-12-31 |  | ALEX WILLIAMSON | 2022-12-28 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1
KY | KY - EAST | 2631 | 10874409400 |  | 500131400 |  | 7356216D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | BOONE | 101 N BOONE ST RR | 127 | LOU | 2022-12-28 | U129673 | U906307 | 2010-12-30 | 2022-07-01 | 2022-12-31 |  | ALEX WILLIAMSON | 2022-12-28 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1
KY | KY - CENTRAL | 2632 | 11881170800 |  | 100271074 |  | 6756288T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | ASBURY | 4518 ASBURY RD | 023 | AUG | 2023-01-20 | U129673 | U124017 | 2011-01-26 | 2022-06-30 | 2022-12-31 |  | ALEX WILLIAMSON | 2022-12-28 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1
KY | KY - CENTRAL | 2632 | 19713435700 |  | 100457514 |  | 7260280M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | FOREST | 802 FOREST AV | 161 | MAY | 2023-01-27 | U461383 | U125208 | 2019-06-12 | 2022-07-01 | 2022-12-31 |  | ALEX WILLIAMSON | 2022-12-28 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 0.7 | 4 | 1651.3 | 41.74 | 0 | 2.52 | 1607.04 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21883096600 |  | 100433724 |  | NEW |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | WILLOW LNXBURG | 4326 WILLOW LNXBURG RD | 023 | FOS | 2023-01-27 | U461383 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | ALEX WILLIAMSON | 2022-12-28 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1
KY | KY - EAST | 2631 | 21883187800 |  | 100249427 |  | 7356216 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 1ST | 23 1ST ST | 127 | LOU | 2022-12-28 | U129673 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | ALEX WILLIAMSON | 2022-12-28 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1
KY | KY - CENTRAL | 2632 | 21897157700 |  | 100353271 |  | 7256280G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2600B | 2ND | 546 W 2ND ST | 161 | MAY | 2023-01-04 | U127414 | U124841 | 2021-03-25 | 2021-12-30 |  |  | TYLER ALLISON | 2022-12-28 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1 | 2094.98 | 0 | 0 | 0 | 2094.98 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026245700 |  |  |  | 6748204H | 2183464 | U128885 |  | 585 | EX | INSTALL BUILDING R-1667 | 2629M | STATE RT 89 | STATE RT 89 | 049 | WIN | 2023-02-22 | U123258 | U128885 | 2022-12-27 | 2023-12-29 | 2023-12-31 | 2022-08-16 | JPASLEY | 2022-12-28 |  |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00585 | 3200585 |  |  | WP2457 |  |  | 100 | 058532220262457 | 8 | 1 | 651.28 | 510 | 0 | 108.5 | 0 | 0 | 0 | 32.78
KY | KY - CENTRAL | 2629 | 22026245800 |  |  |  | 6748204H | 2183464 | U128885 |  | 586 | EX | RETIRE MIS FACILITIES R-1639 | 2629M | STATE RT 89 | STATE RT 89 | 049 | WIN | 2023-02-22 | U123258 | U128885 | 2022-12-27 | 2023-12-29 | 2023-12-31 | 2022-08-16 | JPASLEY | 2022-12-28 |  |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00586 | 3200586 |  |  | WP2458 |  |  | 100 | 058632220262458 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129002900 |  | 100353484 |  | 7256280L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | 2ND | 214< W 2ND ST | 161 | MAY | 2022-12-28 | U129673 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ALEX WILLIAMSON | 2022-12-28 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1
KY | KY - WEST | 2623 | 22994741800 |  | 100345929 |  | 6700208D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | BAYBERRY | 128 BAYBERRY RD | 239 | VER | 2022-12-28 | U126308 | AOC SYST | 2022-04-20 | 2022-12-28 |  |  | J ENSMINGER | 2022-12-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 8.5 | 1 | 3419.17 | 688.43 | 109.42 | 577.6 | 2043.72 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22994744400 |  | 100346019 |  | 6700208D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | BAYBERRY | 169 BAYBERRY RD | 239 | VER | 2022-12-29 | U126308 | AOC SYST | 2022-04-20 | 2022-10-20 | 2023-12-31 |  | J ENSMINGER | 2022-12-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 8 | 1 | 3246.14 | 647.93 | 83.58 | 543.6 | 1971.03 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22995876800 |  | 100345677 |  | 6696212D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | NANCY | 796 NANCY ST | 239 | VER | 2022-12-28 | U128410 | AOC SYST | 2022-04-25 | 2022-12-28 | 2023-12-31 |  | CDESPAIN | 2022-12-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 10 | 1 | 3887.85 | 775.1 | 511.46 | 40.47 | 2560.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22152321600 |  | 100461911 |  | 6720200A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | TURNBRIDGE | 1004 TURNBRIDGE RD | 067 | LEX | 2022-12-30 | U930915 | U136097 | 2022-12-29 | 2022-12-22 | 2023-01-10 |  | RJCRAWF | 2022-12-29 | 2022-12-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.7167 | 4 | 835.28 | 477.95 | 256.46 | 24.97 | 75.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22152321900 |  | 100323244 |  | 6716208P |  |  |  | 565 | EX | SERVICE LINE - REPLACE D311073 | 2621P | SHERWOOD | 767 SHERWOOD DR | 067 | LEX | 2022-12-30 | U125208 | U136097 | 2022-12-29 | 2022-12-29 | 2022-12-29 |  | RJCRAWF | 2022-12-29 | 2022-12-29 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 22.2 | 4 | 1979.29 | 1512.36 | 317.56 | 78.97 | 70.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22995872200 |  | 100345674 |  | 6696212D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | NANCY | 802 NANCY ST | 239 | VER | 2022-12-29 | U128410 | AOC SYST | 2022-04-25 | 2022-12-29 | 2023-12-31 |  | CDESPAIN | 2022-12-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 10 | 1 | 4509.11 | 775.1 | 511.46 | 40.47 | 3182.08 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22996203100 |  | 100345763 |  | 6696212D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | MILDRED | 782 MILDRED ST | 239 | VER | 2022-12-29 | U126309 | AOC SYST | 2022-04-26 | 2022-12-29 | 2023-12-31 |  | JAMIE LYNN | 2022-12-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 6.0667 | 1 | 2109.16 | 434.62 | 0 | 102.99 | 1571.55 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22026240200 |  |  |  | 7356256A | 2293799 | U122858 |  | 557 | EX | EMER - INSTALL 100'-4" PMLP | 2621P | ASHLAND | 909 ASHLAND AV | 019 | ASH | 2023-04-28 | U128132 | U132280 | 2022-11-21 | 2049-12-31 |  | 2022-12-02 | MCOLLET | 2022-12-30 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP2402 | AMRCB |  | 100 | 055732220262402 | 0.93333 | 93 | 5141.88 | 2103.07 | 0 | 762.26 | 1477.74 | 0 | 0.76 | 798.05 | 93
KY | KY - EAST | 2631 | 22026240300 |  |  |  | 7356256A | 2293799 | U122858 |  | 558 | EX | EMER - RETIRE 100'-4" BSLP | 2621P | ASHLAND | 909 ASHLAND AV | 019 | ASH | 2023-01-05 | U128132 | U132280 | 2022-11-21 | 2049-12-31 |  | 2022-12-02 | MCOLLET | 2022-12-30 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP2403 | AMRCB |  | 100 | 055832220262403 | 1.25 | 0 | 285.28 | 108.73 | 0 | 176.55 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22152246900 |  | 100346196 |  | 6696212L |  |  |  | 565 | EX | SERVICE LINE - REPLACE D308928 | 2621P | LEXINGTON | 126 LEXINGTON ST 1F | 239 | VER | 2023-01-03 | U125208 | U134852 | 2022-12-29 | 2022-12-29 | 2022-12-29 |  | DCOLLIN | 2022-12-30 | 2022-12-29 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 40.55 | 6 | 4046.46 | 2998.07 | 0 | 621.26 | 427.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22152707800 |  | 100304376 |  | 6712208D |  |  |  | 565 | EX | REPLACE SL | 2621P | MAYWICK | 916 MAYWICK DR | 067 | LEX | 2023-01-03 | U930915 | U132823 | 2022-12-30 | 2022-12-30 | 2022-12-30 |  | LSTONE | 2022-12-30 | 2022-12-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.05 | 3 | 584.85 | 363.83 | 130.54 | 18.98 | 71.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22994745100 |  | 100346035 |  | 6700208D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | SYCAMORE | 106 SYCAMORE PY | 239 | VER | 2022-12-30 | U129673 | AOC SYST | 2022-04-20 | 2022-10-20 | 2023-12-31 |  | ALEX WILLIAMSON | 2022-12-30 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 8 | 1 | 2958.95 | 587.89 | 235.27 | 136.35 | 1999.44 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22995873300 |  | 100345663 |  | 6696212D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | NANCY | 811 NANCY ST | 239 | VER | 2022-12-30 | U128410 | AOC SYST | 2022-04-25 | 2022-12-30 | 2023-12-31 |  | CDESPAIN | 2022-12-30 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 10 | 1 | 3934.29 | 775.1 | 261.22 | 40.47 | 2857.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22996493600 |  | 100345650 |  | 6696212D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | MEREWOOD | 111 MEREWOOD DR | 239 | VER | 2022-12-30 | U128336 | AOC SYST | 2022-04-27 | 2022-10-27 | 2023-12-31 |  | JOSHUA COX | 2022-12-30 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 10 | 1 | 3794.06 | 813.8 | 323.74 | 42.47 | 2614.05 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22152755700 |  | 100302416 |  | 6712212G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | ALEXANDRIA | 1155 ALEXANDRIA DR | 067 | LEX | 2022-12-31 | LSTONE | U134852 | 2022-12-31 | 2022-12-31 | 2022-12-31 |  | LSTONE | 2022-12-31 | 2022-12-31 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.5 | 4 | 2034.34 | 686.74 | 0 | 35.84 | 1311.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22999240300 |  | 100305272 |  | 6712212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309084 | 2600B | LINSTEAD | 1684 LINSTEAD DR | 067 | LEX | 2023-01-04 | U461309 | U125208 | 2022-05-06 | 2022-11-04 | 2024-05-31 |  | R.HUMPHREYS | 2023-01-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9 | 1 | 5636.62 | 542.6 | 300.33 | 119.93 | 4673.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026246100 |  |  |  | 6712204D |  | U461383 |  | 584 | EX | RETIRE PAPER GAUGE | 2621M | HOLWYN | 3369 HOLWYN RD | 067 | LEX | 2023-01-24 | U123258 | U461383 | 2023-01-03 | 2023-02-01 | 2023-02-01 | 2023-01-02 | CCOX | 2023-01-02 | 2023-01-11 |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00584 | 3200584 |  |  | WP2461 |  |  | 100 | 058432230262461 | 5.4 | 0 | 389.08 | 364.26 | 0 | 24.82 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11902015000 |  | 100318578 |  | 6716204C |  |  |  | 566 | EX | PAPER ABN / RI 04-29-2010 | 2600B | LANSDOWNE | 3515 LANSDOWNE DR | 067 | LEX | 2023-01-03 | RJCRAWF | U906631 | 2011-04-19 | 2023-01-03 |  |  | RJCRAWF | 2023-01-03 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.9667 | 2 | 139.44 | 130.56 | 0 | 8.88 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12965296500 |  | 100333525 |  | 6716212L |  |  |  | 566 | EX | SOII - METER ABANDON ONLY | 2621P | CONSTITUTION | 115 CONSTITUTION ST 1F | 067 | LEX | 2023-01-03 | LSTANFI | U124967 | 2012-04-16 | 2014-12-23 |  |  | LSTANFI | 2023-01-03 | 2022-12-16 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 20.7 | 5 | 1396.45 | 1146.97 | 0 | 249.48 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12965299900 |  | 100427544 |  | 6716212P |  |  |  | 566 | EX | SOII - METER ABANDON ONLY | 2621P | MAXWELL | 435 E MAXWELL ST 3 | 067 | LEX | 2023-01-03 | U930915 | U124967 | 2012-04-16 | 2014-12-23 |  |  | RJCRAWF | 2023-01-03 | 2022-12-14 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.5667 | 5 | 436.1 | 410.69 | 0 | 25.41 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12968003100 |  | 100298111 |  | 6716212L |  |  |  | 566 | EX | ABANDON SL- DOWNSTREAM | 2621P | UPPER | 183 N UPPER ST 2FL | 067 | LEX | 2023-01-03 | LSTONE | U124967 | 2012-05-02 | 2014-12-23 |  |  | LSTONE | 2023-01-03 | 2022-12-13 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.1 | 4 | 207.61 | 195.8 | 0 | 11.81 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12968003600 |  | 100298313 |  | 6716212H |  |  |  | 566 | EX | SOII - METER ABANDON ONLY | 2621P | SHORT | 623 W SHORT ST 2F | 067 | LEX | 2023-01-03 | U930915 | U124967 | 2012-05-02 | 2014-12-23 |  |  | MCRAIG | 2023-01-03 | 2022-12-27 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.1167 | 4 | 402.2 | 321.32 | 0 | 80.88 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12968004200 |  | 100308896 |  | 16716208A |  |  |  | 566 | EX | SOII - METER ABANDON ONLY | 2621P | LYNN | 733 LYNN DR 2F | 067 | LEX | 2023-01-04 | U930915 | U124967 | 2012-05-02 | 2014-12-23 |  |  | KKINDER | 2023-01-03 | 2022-12-27 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.25 | 4 | 318.37 | 299.62 | 0 | 18.75 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12968006100 |  | 100316318 |  | 600000000 |  |  |  | 566 | EX | SOII - METER ABANDON ONLY | 2621P | VISTA | 238 E VISTA DR 2F | 067 | LEX | 2023-01-03 | KKINDER | U124967 | 2012-05-02 | 2014-12-23 |  |  | KKINDER | 2023-01-03 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.05 | 1 | 293.16 | 274.46 | 0 | 18.7 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12968019400 |  | 100332706 |  | 16716212L |  |  |  | 566 | EX | SOII - METER ABANDON ONLY | 2621P | MAIN | 235 E MAIN ST | 067 | LEX | 2023-01-04 | U930915 | U124967 | 2012-05-02 | 2014-12-23 |  |  | LSTANFI | 2023-01-03 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.7 | 3 | 255.72 | 206.71 | 0 | 49.01 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12968020100 |  | 100333524 |  | 6716212L |  |  |  | 566 | EX | SOII - METER ABANDON ONLY | 2621P | CONSTITUTION | 115 CONSTITUTION ST 2F | 067 | LEX | 2023-01-03 | LSTANFI | U124967 | 2012-05-02 | 2014-12-23 |  |  | LSTANFI | 2023-01-03 | 2022-12-20 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.4 | 4 | 23.51 | 20.89 | 0 | 2.62 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12968021800 |  | 100336830 |  | 6720212E |  |  |  | 566 | EX | METER ABANDON ONLY | 2621P | LIMESTONE | 404 N LIMESTONE ST RR | 067 | LEX | 2023-01-03 | LSTANFI | U124967 | 2012-05-02 | 2014-12-23 |  |  | LSTANFI | 2023-01-03 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.85 | 3 | 128.98 | 104.23 | 0 | 24.75 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12968032800 |  | 100404440 |  | 6716208C |  |  |  | 566 | EX | SOII - METER ABANDON ONLY | 2621P | NICHOLASVILLE | 1401 NICHOLASVILLE RD 2F | 067 | LEX | 2023-01-04 | U930915 | U124967 | 2012-05-02 | 2014-12-23 |  |  | KKINDER | 2023-01-03 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.0833 | 1 | 78.14 | 73.18 | 0 | 4.96 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12975837700 |  | 100294083 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LIMESTONE | 607< N LIMESTONE ST | 067 | LEX | 2023-01-03 | LSTONE | U123854 | 2012-06-11 | 2017-04-10 |  |  | LSTONE | 2023-01-03 | 2022-12-14 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.45 | 5 | 2047.61 | 270.63 | 0 | 16.79 | 1760.19 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12975908900 |  | 100443192 |  | 6716212H |  |  |  | 566 | EX | SOII - METER ABANDON ONLY | 2621P | 2ND | 324 W 2ND ST | 067 | LEX | 2023-01-03 | LSTONE | U123854 | 2012-06-11 | 2018-05-25 |  |  | LSTONE | 2023-01-03 | 2023-01-03 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.7833 | 3 | 105.29 | 98.56 | 0 | 6.73 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 13143505500 |  | 100294860 |  | 6720212E |  |  |  | 566 | EX | PAPER ABANDON PER BJACKSON | 2621P | 4TH | 217 W 4TH ST 2 | 067 | LEX | 2023-01-03 | LSTONE | U126129 | 2013-06-18 | 2049-12-31 |  |  | LSTONE | 2023-01-03 | 2022-12-27 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.1833 | 3 | 649.17 | 614.91 | 0 | 34.26 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 14234018100 |  | 100318577 |  | 6716204C |  |  |  | 566 | EX | PAPER ABN / RI 04-30-2010 | 2621P | LANSDOWNE | 3513 LANSDOWNE DR | 067 | LEX | 2023-01-03 | RJCRAWF | U125208 | 2014-07-11 | 2023-01-03 |  |  | RJCRAWF | 2023-01-03 | 2022-12-09 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.2167 | 4 | 235.3 | 222.41 | 0 | 12.89 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23152867500 |  | 100318583 |  | 6716204C |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | LANSDOWNE | 3523 LANSDOWNE DR | 067 | LEX | 2023-01-03 | RJCRAWF | U129939 | 2023-01-03 | 2023-01-03 |  |  | RJCRAWF | 2023-01-03 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.3 | 2 | 20.75 | 19.43 | 0 | 1.32 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959955900 |  | 100446682 |  | 6736232L | 2075121 |  |  | 565 | EX | REPLACE SL W/20-0269806-00 | 2600B | HANSON | 430 HANSON ST | 017 | PAR | 2023-01-04 | U126284 | U134723 | 2021-12-16 | 2022-09-30 |  |  | JOSH PASLEY | 2023-01-04 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 10 | 1 | 3220.43 | 664.65 | 0 | 646.4 | 1909.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22103686800 |  | 100465973 |  | 6712216P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D247559 | 2600B | TRADE | 125 TRADE ST A-B | 067 | LEX | 2023-01-04 | U461322 | U125208 | 2022-05-26 | 2022-11-23 | 2024-05-31 |  | STEVE CANOY | 2023-01-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.4833 | 1 | 7123.18 | 854.04 | 0 | 808.35 | 5460.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22104774800 |  | 100293546 |  | 6720216J |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311750 | 2600B | KILPATRICK | 441 KILPATRICK CT | 067 | LEX | 2023-01-05 | U128410 | U125208 | 2022-06-01 | 2022-11-30 | 2024-05-31 |  | CDESPAIN | 2023-01-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.5 | 1 | 4641.62 | 693.94 | 225.41 | 47.24 | 3675.03 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22114618900 |  | 100347239 |  | 6696212G | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | BEECH | 536 BEECH ST | 239 | VER | 2023-01-04 | DCOLLIN | AOC SYST | 2022-07-07 | 2023-01-04 | 2023-12-31 |  | DCOLLIN | 2023-01-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 4.8 | 1 | 2659.75 | 300.35 | 410.04 | 293.2 | 1656.16 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129069200 |  | 100265198 |  | 7352256C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KENTUCKY | 229 KENTUCKY ST WW | 019 | ASH | 2023-01-04 | RECUMP | U130722 | 2022-09-05 | 2022-12-30 |  |  | RECUMP | 2023-01-04 | 2022-11-28 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 17.1833 | 4 | 1351.94 | 1057.85 | 19.89 | 274.2 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964239000 |  | 100347869 |  | 6748208I | 2075093 |  |  | 565 | EX | REPLACE SL W/20-0269804-00 | 2600B | MAGNOLIA | 27 MAGNOLIA ST | 049 | WIN | 2023-01-05 | U126602 | U134723 | 2022-01-06 | 2022-12-30 |  |  | DEREK PAYTON | 2023-01-04 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3710.5 | 0 | 0 | 0 | 3710.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22993653400 |  | 100415618 |  | 6704208E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | JUNIPER | 200 JUNIPER DR | 239 | VER | 2023-01-04 | DCOLLIN | AOC SYST | 2022-04-14 | 2023-01-04 | 2023-12-31 |  | DCOLLIN | 2023-01-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 2.7333 | 1 | 3083.22 | 170.21 | 221.22 | 166.17 | 2525.62 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23153122300 |  | 100408475 |  | 6704208E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | JUNIPER | 198 JUNIPER DR | 239 | VER | 2023-01-04 | DCOLLIN | U129939 | 2023-01-04 | 2023-01-04 |  |  | DCOLLIN | 2023-01-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.8333 | 1 | 2913.88 | 175.82 | 470.46 | 171.64 | 2095.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23153168800 |  | 100419141 |  | 6720204F |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HOT SPRINGS | 1268 HOT SPRINGS CT | 067 | LEX | 2023-01-05 | UIPBOT24 | U129939 | 2023-01-04 | 2022-12-30 | 2022-12-31 |  | DMARSTO | 2023-01-04 | 2023-01-04 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.58333 | 2 | 336.31 | 39.77 | 227.83 | 2.71 | 66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23153198100 |  | 100340636 |  | 6724212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SARASOTA | 1703 SARASOTA CT | 067 | LEX | 2023-01-04 | LSTANFI | U129939 | 2023-01-04 | 2022-12-30 | 2023-01-17 |  | LSTANFI | 2023-01-04 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.95 | 3 | 1411.52 | 877.72 | 382.54 | 89.66 | 61.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23153371200 |  | 100292859 |  | 6720216K |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2600B | BISHOP | 640 BISHOP DR | 067 | LEX | 2023-01-10 | U125208 | U125768 | 2023-01-05 | 2049-12-31 |  |  | ALEX WILLIAMSON | 2023-01-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 2839.46 | 0 | 204.61 | 0 | 2634.85 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12975858000 |  | 100332431 |  | 6720212M |  |  |  | 566 | EX | METER ABANDON ONLY | 2621P | MAIN | 637 E MAIN ST 1F2F | 067 | LEX | 2023-01-06 | U125208 | U123854 | 2012-06-11 | 2014-12-23 |  |  | HMCKUNE | 2023-01-05 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.1833 | 3 | 515.11 | 326.37 | 0 | 188.74 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959956300 |  | 100358923 |  | 6736232L | 2075121 |  |  | 565 | EX | REPLACE SL W/20-0269806-00 | 2600B | HANSON | 441 HANSON ST | 017 | PAR | 2023-01-05 | U126286 | U134723 | 2021-12-16 | 2022-09-30 |  |  | TYLER ALLISON | 2023-01-05 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2115.37 | 0 | 0 | 0 | 2115.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22102551600 |  | 100304907 |  | 6712212P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309135 | 2600B | SHENANDOAH | 1732 SHENANDOAH DR | 067 | LEX | 2023-01-05 | U126284 | U125208 | 2022-05-20 | 2022-11-18 | 2024-05-31 |  | JOSH PASLEY | 2023-01-05 | 2022-07-28 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25.55 | 4 | 7327.67 | 1699.8 | 0 | 1081.29 | 4546.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22104105800 |  | 100311157 |  | 6712208O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309176 | 2600B | TUDOR | 3209 TUDOR DR | 067 | LEX | 2023-01-20 | U129673 | U125208 | 2022-05-31 | 2022-11-23 | 2024-05-31 |  | ATWILLI | 2023-01-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.4333 | 1 | 5382.47 | 613.41 | 333.01 | 128.84 | 4307.21 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22104106400 |  | 100465396 |  | 6712208L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309230 | 2600B | AZOV | 2908 AZOV CT | 067 | LEX | 2023-01-06 | U128410 | U125208 | 2022-05-31 | 2022-11-23 | 2024-05-31 |  | CDESPAIN | 2023-01-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.4667 | 2 | 3464.53 | 559.78 | 231.44 | 38.14 | 2635.17 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22114620400 |  | 100347241 |  | 6696212J | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | BEECH | 526 BEECH ST | 239 | VER | 2023-01-05 | U129731 | AOC SYST | 2022-07-07 | 2023-01-06 | 2023-12-31 |  | F.GOINS | 2023-01-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 |  | 1 | 1829.49 | 0 | 0 | 0 | 1829.49 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129004400 |  | 100240730 |  | 7324132E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633D | HIGHWAY 160 S | 238 HIGHWAY 160 S | 119 | HIN | 2023-01-05 | U130172 | U130722 | 2022-09-05 | 2022-12-30 | 2023-12-31 |  | JOHN HOWARD | 2023-01-05 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.2833 | 2 | 95.11 | 89.04 | 0 | 6.07 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129025000 |  | 100355549 |  | 7260276B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CLARK | 618 CLARK ST | 161 | MAY | 2023-01-05 | SDADAMS | U130722 | 2022-09-05 | 2022-12-30 |  |  | SDADAMS | 2023-01-05 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 2.6667 | 2 | 173.59 | 162.52 | 0 | 11.07 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129129300 |  | 100295385 |  | 6716212D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BOOKER | 516 BOOKER ST | 067 | LEX | 2023-01-05 | MCRAIG | U125208 | 2022-09-06 | 2022-12-30 |  |  | MCRAIG | 2023-01-05 | 2022-10-14 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 27.6333 | 15 | 1964.13 | 1469.39 | 34.39 | 460.35 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22136417200 |  | 100319612 |  | 6716208K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303183 | 2621P | GREENBRIAR | 224 GREENBRIAR RD | 067 | LEX | 2023-01-06 | U129722 | U125208 | 2022-10-03 | 2023-03-30 | 2024-09-30 |  | M YOUNG | 2023-01-05 | 2022-12-15 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.0333 | 3 | 4662.63 | 999.24 | 381.53 | 98.07 | 3183.79 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22143285900 |  | 100263656 |  | 7352256C |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | IOWA | 206 IOWA ST | 019 | ASH | 2023-01-05 | RECUMP | DYOUNG | 2022-11-07 | 2022-11-14 |  |  | RECUMP | 2023-01-05 | 2022-11-10 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 23.4333 | 6 | 1634.67 | 1328.45 | 0 | 306.22 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22152669500 |  | 100458461 |  | 6728208B |  |  |  | 565 | VO | REPLACE SERVICE LINE - D311448 | 2621P | BAHAMA | 2186 BAHAMA RD | 067 | LEX | 2023-01-09 | UIPBOT19 | U125208 | 2022-12-30 | 2022-12-30 | 2023-01-19 |  | HMCKUNE | 2023-01-05 | 2023-01-03 |  | A | [11 empty] | 23154135500 | 100 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964238800 |  | 100347871 |  | 6748208I | 2075093 |  |  | 565 | EX | REPLACE SL W/20-0269804-00 | 2600B | MAGNOLIA | 23 MAGNOLIA ST | 049 | WIN | 2023-01-09 | U126602 | U134723 | 2022-01-06 | 2022-12-30 |  |  | DEREK PAYTON | 2023-01-05 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4656.39 | 0 | 0 | 0 | 4656.39 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964238900 |  | 100347809 |  | 6748208I | 2075093 |  |  | 565 | EX | REPLACE SL W/20-0269804-00 | 2600B | MAGNOLIA | 24 MAGNOLIA ST | 049 | WIN | 2023-01-05 | U126602 | U134723 | 2022-01-06 | 2022-12-30 |  |  | DEREK PAYTON | 2023-01-05 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2587.69 | 0 | 0 | 0 | 2587.69 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22996193800 |  | 100345773 |  | 6696212D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | GEORGIA | 123 GEORGIA ST | 239 | VER | 2023-01-05 | U129731 | AOC SYST | 2022-04-26 | 2023-12-31 | 2023-12-31 |  | F.GOINS | 2023-01-05 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 11 | 1 | 3373.4 | 705.48 | 0 | 48.04 | 2619.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22996196600 |  | 100345768 |  | 6696212D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | GEORGIA | 113 GEORGIA ST | 239 | VER | 2023-01-05 | U129731 | AOC SYST | 2022-04-26 | 2022-10-26 | 2023-12-31 |  | F.GOINS | 2023-01-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 |  | 1 | 3061.33 | 0 | 0 | 0 | 3061.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23152805200 |  | 500008565 |  | 6720212D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D310407 | 2621P | COLLIER | 532 COLLIER CT | 067 | LEX | 2023-01-10 | U128381 | U125208 | 2023-01-03 | 2023-01-05 | 2023-01-23 |  | LSTANFI | 2023-01-05 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.8833 | 5 | 695.74 | 612.17 | 12.15 | 50.52 | 20.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23153349900 |  | 100358922 |  | 6736232L | 2075121 |  |  | 565 | EX | REPLACE SL W/20-0269806-00 | 2600B | HANSON | 443 HANSON ST | 017 | PAR | 2023-01-05 | U126286 | U125768 | 2023-01-05 | 2049-12-31 |  |  | TYLER ALLISON | 2023-01-05 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2583.77 | 0 | 0 | 0 | 2583.77 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12968012000 |  | 100320976 |  | 6720208A |  |  |  | 566 | EX | SOII - METER ABANDON ONLY | 2621P | MAXWELL | 511 E MAXWELL ST | 067 | LEX | 2023-01-09 | U125208 | U124967 | 2012-05-02 | 2014-12-23 |  |  | ABLAKE | 2023-01-06 | 2022-12-16 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.85 | 6 | 440.51 | 414.81 | 0 | 25.7 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959956400 |  | 100358921 |  | 6736232L | 2075121 |  |  | 565 | EX | REPLACE SL W/20-0269806-00 | 2600B | HANSON | 445 HANSON ST | 017 | PAR | 2023-01-10 | U126286 | U134723 | 2021-12-16 | 2022-09-30 |  |  | TYLER ALLISON | 2023-01-06 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 8 | 1 | 2942.22 | 495.18 | 0 | 33.71 | 2413.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22101722300 |  | 100301479 |  | 6712212H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309117 | 2600B | RUGBY | 151 RUGBY RD | 067 | LEX | 2023-01-06 | U461322 | U125208 | 2022-05-18 | 2022-11-17 | 2024-05-31 |  | STEVE CANOY | 2023-01-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.9833 | 1 | 7017.96 | 751.4 | 0 | 711.19 | 5555.37 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22114620000 |  | 100346319 |  | 6696212L | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | BELL | 111 BELL AV | 239 | VER | 2023-01-06 | U129731 | AOC SYST | 2022-07-07 | 2023-01-06 | 2023-12-31 |  | F.GOINS | 2023-01-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 |  | 1 | 2385.25 | 0 | 0 | 0 | 2385.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22133695900 |  | 100309391 |  | 6712208P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311022 | 2621P | BUCKINGHAM | 620 BUCKINGHAM LN | 067 | LEX | 2023-01-09 | U129722 | U125208 | 2022-09-22 | 2023-03-21 | 2024-09-30 |  | M YOUNG | 2023-01-06 | 2022-12-15 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9 | 3 | 3435.21 | 545.1 | 225.38 | 50.51 | 2614.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22137501400 |  | 100296387 |  | 6716212C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BREATHITT | 748 BREATHITT AV | 067 | LEX | 2023-01-06 | MCRAIG | U130722 | 2022-10-07 | 2022-12-30 |  |  | MCRAIG | 2023-01-06 | 2022-10-24 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 30.0667 | 12 | 2202.78 | 1609.13 | 34.39 | 559.26 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22148085300 |  | 100337719 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL - DEMO/LNDMRK | 2621P | 7TH | 232 E 7TH ST | 067 | LEX | 2023-01-06 | LSTANFI | U125208 | 2022-12-07 | 2022-12-09 | 2023-01-07 |  | LSTANFI | 2023-01-06 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.4 | 3 | 990.3 | 527.24 | 34.39 | 102.67 | 326 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22148085500 |  | 100337718 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL - DEMO/LNDMRK | 2621P | 7TH | 230 E 7TH ST | 067 | LEX | 2023-01-06 | LSTANFI | U125208 | 2022-12-07 | 2022-12-09 | 2023-01-07 |  | LSTANFI | 2023-01-06 | 2023-01-06 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.7 | 3 | 515.38 | 274.03 | 19.7 | 20.65 | 201 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22150004800 |  | 100301116 |  | 6716212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2600B | SAVOY | 209 SAVOY RD | 067 | LEX | 2023-01-20 | U129673 | U124960 | 2022-12-21 | 2022-11-23 | 2024-05-31 |  | ALEX WILLIAMSON | 2023-01-06 | 2023-01-03 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26210022 | 16.5 | 2 | 4404.1 | 1072.17 | 200.7 | 225.16 | 2906.07 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22150351400 |  | 100252589 |  | 7348264P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D259830 | 2621P | LA GAR | 610 LA GAR ST | 089 | FLA | 2023-01-09 | U125208 | U132761 | 2022-12-22 | 2022-12-22 | 2023-01-11 |  | RECUMP | 2023-01-06 | 2023-01-06 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 23.05 | 3 | 1496.03 | 1213.12 | 0 | 282.91 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964242300 |  | 100347868 |  | 6748208I | 2075093 |  |  | 565 | EX | REPLACE SL W/20-0269804-00 | 2600B | MAPLE | 511 N MAPLE ST | 049 | WIN | 2023-01-09 | U126602 | U134723 | 2022-01-06 | 2022-12-30 |  |  | DEREK PAYTON | 2023-01-06 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3140.16 | 0 | 0 | 0 | 3140.16 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22994742800 |  | 100346033 |  | 6700208D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | HAWTHORNE | 97 HAWTHORNE CT | 239 | VER | 2023-01-06 | U129731 | AOC SYST | 2022-04-20 | 2022-10-20 | 2023-12-31 |  | F.GOINS | 2023-01-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 |  | 1 | 2701.53 | 0 | 0 | 0 | 2701.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23153492100 |  | 500192396 |  | 6720212I |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HAWKINS | 455 HAWKINS AV | 067 | LEX | 2023-01-09 | U125208 | U129939 | 2023-01-05 | 2023-01-06 |  |  | LSTANFI | 2023-01-06 | 2023-01-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 14.0333 | 3 | 9180.53 | 2537.66 | 280.96 | 300.73 | 6061.18 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23153729900 |  | 100345067 |  | 6696212G |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | ELM | 151 ELM ST 1F | 239 | VER | 2023-01-06 | U129731 | U134852 | 2023-01-06 | 2023-01-06 |  |  | F.GOINS | 2023-01-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 14 | 1 | 4736.32 | 897.89 | 0 | 190.26 | 3648.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23153773600 |  | 500511874 |  | 6720212M |  |  |  | 566 | EX | SERVICE LINE ABANDON | 2621P | MAXWELL | 509 E MAXWELL ST | 067 | LEX | 2023-01-09 | U125208 | U134852 | 2023-01-06 | 2023-01-06 |  |  | ABLAKE | 2023-01-06 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.5667 | 2 | 99 | 92.67 | 0 | 6.33 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12968033400 |  | 100423007 |  | 16716204B |  |  |  | 566 | EX | SOII - METER ABANDON ONLY | 2621P | NICHOLASVILLE | 3401 NICHOLASVILLE RD STE 316 | 067 | LEX | 2023-01-09 | RJCRAWF | U124967 | 2012-05-02 | 2014-12-23 |  |  | RJCRAWF | 2023-01-09 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.9333 | 4 | 480.5 | 449.86 | 0 | 30.64 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959955700 |  | 100358935 |  | 6736232L | 2075121 |  |  | 565 | EX | REPLACE SL W/20-0269806-00 | 2600B | HANSON | 424 HANSON ST | 017 | PAR | 2023-01-09 | U126286 | U134723 | 2021-12-16 | 2022-09-30 |  |  | TYLER ALLISON | 2023-01-09 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2044.7 | 0 | 0 | 0 | 2044.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959956100 |  | 100358924 |  | 6736232L | 2075121 |  |  | 565 | EX | REPLACE SL W/20-0269806-00 | 2600B | HANSON | 439 HANSON ST | 017 | PAR | 2023-01-09 | U126286 | U134723 | 2021-12-16 | 2022-09-30 |  |  | TYLER ALLISON | 2023-01-09 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 18 | 2 | 3266.71 | 1114.14 | 0 | 75.86 | 2076.71 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959956700 |  | 100358886 |  | 6736232L | 2075121 |  |  | 565 | EX | REPLACE SL W/20-0269806-00 | 2600B | HANSON | 522 HANSON ST | 017 | PAR | 2023-01-09 | U126604 | U134723 | 2021-12-16 | 2022-09-30 |  |  | WILL FULKS | 2023-01-09 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2161.11 | 0 | 0 | 0 | 2161.11 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959956900 |  | 100358895 |  | 6736232L | 2075121 |  |  | 565 | EX | REPLACE SL W/20-0269806-00 | 2600B | HANSON | 529 HANSON ST | 017 | PAR | 2023-01-09 | U126604 | U134723 | 2021-12-16 | 2022-09-30 |  |  | WILL FULKS | 2023-01-09 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2594.34 | 0 | 0 | 0 | 2594.34 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960861500 |  | 100249833 |  | 7356248H | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | PADDLE CREEK | 8023 PADDLE CREEK RD | 019 | CAT | 2023-01-09 | U124015 | U134723 | 2021-12-21 | 2023-06-30 |  |  | ORA SLONE | 2023-01-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2213.75 | 0 | 0 | 0 | 2213.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026242400 |  |  |  | 6728208G | 2287856 | U461383 |  | 575 | EX | OBTAIN NEW HP EASEMENT | 2600E | BIG POND | 1320 BIG POND CR | 067 | LEX | 2023-01-09 | U128132 | U461383 | 2022-12-09 | 2023-06-01 | 2023-06-01 | 2023-01-09 | LAND SERVICES | 2023-01-09 |  |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00575 | 3200575 |  |  | WP2424 | AMRCB |  | 100 | 057532220262424 |  | 1 | 7607.73 | 0 | 0 | 7589.7 | 0 | 0 | 18.03 | 0
KY | KY - WEST | 2621 | 22102551000 |  | 100304712 |  | 6712212P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309120 | 2600B | GETTYSBURG | 1726 GETTYSBURG RD | 067 | LEX | 2023-01-12 | U128410 | U125208 | 2022-05-20 | 2022-11-18 | 2024-05-31 |  | CDESPAIN | 2023-01-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.5 | 1 | 4372.86 | 693.94 | 206.68 | 47.24 | 3425 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22102922800 |  | 100304777 |  | 6712212P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309138 | 2600B | BLUE LICKS | 1761 BLUE LICKS RD | 067 | LEX | 2023-01-09 | U461322 | U125208 | 2022-05-23 | 2022-11-18 | 2024-05-31 |  | STEVE CANOY | 2023-01-09 | 2022-07-29 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.1667 | 2 | 6376.88 | 891.94 | 0 | 689.9 | 4795.04 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22116407100 |  | 100347000 |  | 6696212K | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | HIGH | 300 HIGH ST | 239 | VER | 2023-01-09 | U128816 | AOC SYST | 2022-07-15 | 2023-01-13 | 2023-12-31 |  | OLIVER MAYNARD | 2023-01-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 4.2333 | 1 | 2973.07 | 271.47 | 419.97 | 18.5 | 2263.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22137507200 |  | 100319221 |  | 6716208O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303185 | 2621P | RANDOLPH | 2373 RANDOLPH CT | 067 | LEX | 2023-01-11 | U129722 | U125208 | 2022-10-07 | 2023-04-06 | 2024-10-31 |  | M YOUNG | 2023-01-09 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.75 | 1 | 2683.8 | 222.95 | 384.82 | 15.17 | 2060.86 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964238400 |  | 100347873 |  | 6748208I | 2075093 |  |  | 565 | EX | REPLACE SL W/20-0269804-00 | 2600B | MAGNOLIA | 19 MAGNOLIA ST | 049 | WIN | 2023-01-09 | U126602 | U134723 | 2022-01-06 | 2022-12-30 |  |  | DEREK PAYTON | 2023-01-09 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2875.75 | 34.33 | 0 | 2.52 | 2838.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964238600 |  | 100347872 |  | 6748208I | 2075093 |  |  | 565 | EX | REPLACE SL W/20-0269804-00 | 2600B | MAGNOLIA | 21 MAGNOLIA ST | 049 | WIN | 2023-01-09 | U126602 | U134723 | 2022-01-06 | 2022-12-30 |  |  | DEREK PAYTON | 2023-01-09 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2391.94 | 0 | 0 | 0 | 2391.94 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964238700 |  | 100347808 |  | 6748208I | 2075093 |  |  | 565 | EX | REPLACE SL W/20-0269804-00 | 2600B | MAGNOLIA | 22 MAGNOLIA ST | 049 | WIN | 2023-01-09 | U126602 | U134723 | 2022-01-06 | 2022-12-30 |  |  | DEREK PAYTON | 2023-01-09 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2875.46 | 29.11 | 0 | 2.09 | 2844.26 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22998854100 |  | 100466732 |  | 6728208B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303874 | 2600B | ANTIGUA | 2148 ANTIGUA DR | 067 | LEX | 2023-01-17 | U125559 | U125208 | 2022-05-05 | 2022-11-04 | 2024-05-31 |  | R.HUMPHREYS | 2023-01-09 | 2023-01-03 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.3833 | 3 | 5116.99 | 1227.44 | 258.32 | 240.35 | 3390.88 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23153391100 |  | 100264958 |  | 7348248K |  |  |  | 566 | EX | ABANDON SL - IDLE/CUSTRQD | 2621P | CANNONSBURG | 1336 CANNONSBURG RD | 019 | ASH | 2023-01-09 | RECUMP | U125208 | 2023-01-05 | 2023-01-06 | 2023-01-26 |  | RECUMP | 2023-01-09 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 11.4333 | 2 | 949.45 | 657.51 | 19.89 | 272.05 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23153716900 |  | 100344515 |  | 6700224O |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2600B | HIGGINS | 243 W HIGGINS ST | 239 | MID | 2023-01-09 | U128816 | U125208 | 2023-01-06 | 2023-01-09 |  |  | OLIVER MAYNARD | 2023-01-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.7667 | 1 | 3070.61 | 431.17 | 385.54 | 29.36 | 2224.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23154064800 |  | 100288631 |  | 6720212H |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BELLCASTLE | 609 BELLCASTLE RD | 067 | LEX | 2023-01-09 | U930915 | U134852 | 2023-01-08 | 2023-01-06 | 2023-01-08 |  | LSTANFI | 2023-01-09 | 2023-01-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 7.6 | 4 | 812.83 | 510.83 | 197.9 | 50.2 | 53.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23154076400 |  | 501224872 |  | 6700228 | 1745078 |  |  | 565 | EX | RPLC SL/ | 2600B | ROCKY WATERS | 132 ROCKY WATERS WY | 209 | GEO | 2023-01-09 | U126530 | U125763 | 2023-01-09 | 2023-12-29 |  |  | JDUNN | 2023-01-09 | 2023-01-09 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 15.55 | 2 | 4772.39 | 984.74 | 0 | 67.06 | 3720.59 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23154134900 |  | 100301247 |  | 6716212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | DUNKIRK | 1863 DUNKIRK DR | 067 | LEX | 2023-01-10 | U930915 | U129939 | 2023-01-09 | 2022-11-03 | 2024-05-31 |  | MCRAIG | 2023-01-09 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 6.8333 | 5 | 1866.01 | 1212.01 | 77.98 | 506.72 | 69.3 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23154189300 |  | 100423836 |  | 6700224O |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | WALNUT | 115 WALNUT ST | 239 | MID | 2023-01-09 | U129731 | U129939 | 2023-01-09 | 2023-01-09 |  |  | F.GOINS | 2023-01-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 9 | 1 | 2301.52 | 577.25 | 0 | 122.31 | 1601.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12968006300 |  | 100316600 |  | 167162086 |  |  |  | 566 | EX | SOII - METER ABANDON ONLY | 2621P | PENMOKEN | 110 PENMOKEN PA 1FR | 067 | LEX | 2023-01-10 | RJCRAWF | U124967 | 2012-05-02 | 2014-12-23 |  |  | RJCRAWF | 2023-01-10 | 2023-01-09 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.7 | 5 | 315.83 | 295.71 | 0 | 20.12 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 15281081600 |  | 100413929 | 09 | 6704208E | 1635077 |  |  | 565 | EX | AOC SERVICE LINE ENCROACHMENT | 2621P | JUNIPER | 199 JUNIPER DR | 239 | VER | 2023-01-20 | U126308 | JLYNN | 2015-01-21 | 2022-12-22 |  |  | J ENSMINGER | 2023-01-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 9.5333 | 1 | 4020.77 | 613 | 77.08 | 616.04 | 2714.65 | 0 | 0 | 0
KY | KY - WEST | 2623 | 20785262700 |  | 100345382 |  | 6696212H | 1635077 |  |  | 565 | EX | AOC - UNMETERED GAS | 2621P | DOUGLAS | 225 DOUGLAS AV | 239 | VER | 2023-01-10 | U128816 | U125208 | 2020-02-24 | 2049-12-31 |  |  | OLIVER MAYNARD | 2023-01-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 10 | 1 | 4799.87 | 638.81 | 474.06 | 43.5 | 3643.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959956800 |  | 100358887 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | HANSON | 526 HANSON ST | 017 | PAR | 2023-01-10 | U126604 | U134723 | 2021-12-16 | 2023-12-29 |  |  | WILL FULKS | 2023-01-10 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2872.2 | 0 | 0 | 0 | 2872.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959957000 |  | 100358888 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | HANSON | 532 HANSON ST | 017 | PAR | 2023-01-10 | U126604 | U134723 | 2021-12-16 | 2023-12-29 |  |  | WILL FULKS | 2023-01-10 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2705.01 | 0 | 0 | 0 | 2705.01 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959961100 |  | 100358964 |  | 6740232I | 2075121 |  |  | 565 | EX | REPLACE SL W/20-0269806-00 | 2600B | MARSHALL | 529 MARSHALL ST | 017 | PAR | 2023-01-10 | U126286 | U134723 | 2021-12-16 | 2022-09-30 |  |  | TYLER ALLISON | 2023-01-10 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1534.98 | 0 | 0 | 0 | 1534.98 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959962200 |  | 100358941 |  | 6736232L | 2075121 |  |  | 565 | EX | REPLACE SL W/20-0269806-00 | 2600B | HANSON | 432 HANSON ST | 017 | PAR | 2023-01-10 | U126286 | U134723 | 2021-12-16 | 2022-09-30 |  |  | TYLER ALLISON | 2023-01-10 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 9 | 1 | 3246.73 | 557.07 | 0 | 37.93 | 2651.73 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22026211800 |  |  |  | 7344268N |  | U461383 |  | 588 | EX | RETIRE GMB SETTING | 2631M | WURTS | 100 WURTS RD R | 089 | WUR | 2023-01-18 | U123258 | U461383 | 2022-07-15 | 2023-11-01 | 2023-12-01 | 2023-01-10 | WSGIORDANO | 2023-01-10 | 2023-01-10 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00588 | 3200588 |  |  | WP2118 |  |  | 100 | 058832220262118 | 8 | 0 | 1541.41 | 992.92 | 0 | 548.49 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22104774400 |  | 100402805 |  | 6720216J |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309146 | 2600B | ASBURY | 505 ASBURY LN | 067 | LEX | 2023-01-10 | U461322 | U125208 | 2022-06-01 | 2022-11-30 | 2024-05-31 |  | STEVE CANOY | 2023-01-10 | 2023-01-03 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.5333 | 4 | 6282 | 1405.57 | 0 | 1330.42 | 3546.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22109506100 |  | 100302587 |  | 6712212K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311760 | 2600B | BORDEAUX | 1305 BORDEAUX DR | 067 | LEX | 2023-01-10 | U461309 | U125208 | 2022-06-13 | 2022-12-09 | 2024-06-30 |  | R.HUMPHREYS | 2023-01-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.1167 | 1 | 4336.16 | 370.15 | 376.7 | 25.23 | 3564.08 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110064700 |  | 100251296 |  | 7340268F |  |  |  | 566 | EX | ABANDON - DEMO/CUSTREQ D258112 | 2621P | LINCOLN | 1919 LINCOLN AV | 089 | GRE | 2023-01-10 | RECUMP | U125208 | 2022-06-15 | 2022-12-14 | 2024-06-30 |  | RECUMP | 2023-01-10 | 2023-01-10 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 6.8 | 3 | 392.24 | 330.78 | 0 | 61.46 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129081500 |  | 100335077 |  | 6720212O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE (S) | 2621P | LIBERTY - ACT 1645 | 1649 LIBERTY - ACT 1645 RD | 067 | LEX | 2023-01-11 | U930915 | U130722 | 2022-09-05 | 2022-12-30 |  |  | LSTANFI | 2023-01-10 | 2022-11-16 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.0167 | 5 | 1136.32 | 903.76 | 34.39 | 198.17 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22136875800 |  | 100344119 |  | 7352248T |  |  |  | 566 | EX | PAPER ABANDON | 2621P | TARPIN | 6612 TARPIN RG | 019 | CAT | 2023-01-11 | U125208 | U129939 | 2022-10-05 | 2022-10-05 |  |  | RECUMP | 2023-01-10 | 2022-12-22 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 27.3167 | 7 | 1885.33 | 1575.56 | 0 | 309.77 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22137155900 |  | 100319227 |  | 6716208O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303184 | 2621P | MELBOURNE | 213 MELBOURNE WY | 067 | LEX | 2023-01-10 | U129731 | U125208 | 2022-10-06 | 2023-04-05 | 2024-10-31 |  | F.GOINS | 2023-01-10 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10 | 1 | 2724.56 | 641.38 | 0 | 135.91 | 1947.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22148589000 |  | 100330778 |  | 6720212O |  |  |  | 566 | EX | ABANDON SL - DEMO/LNDMRK | 2621P | SHERMAN | 341 SHERMAN AV | 067 | LEX | 2023-01-11 | U930915 | U125208 | 2022-12-12 | 2022-12-15 | 2023-01-09 |  | HMCKUNE | 2023-01-10 | 2022-12-15 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.3333 | 7 | 861.87 | 794.81 | 16.76 | 50.3 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22150004500 |  | 100464931 |  | 6716216J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2600B | BAUMANN | 1601 BAUMANN RD | 067 | LEX | 2023-01-20 | U129673 | U124960 | 2022-12-21 | 2022-10-04 | 2024-04-30 |  | ALEX WILLIAMSON | 2023-01-10 | 2023-01-09 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26210022 | 62.75 | 9 | 21096.59 | 4087.43 | 676.36 | 1837.31 | 14495.49 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22150614000 |  | 100331026 |  | 6720212N |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTREQD | 2621P | PRESTON | 252 PRESTON AV | 067 | LEX | 2023-01-10 | HMCKUNE | U125208 | 2022-12-27 | 2023-01-17 | 2023-01-27 |  | HMCKUNE | 2023-01-10 | 2023-01-06 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 20.4 | 8 | 1061.76 | 961.87 | 34.39 | 65.5 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964238000 |  | 100347805 |  | 6748208I | 2075093 |  |  | 565 | EX | REPLACE SL W/20-0269804-00 | 2600B | MAGNOLIA | 2 MAGNOLIA ST | 049 | WIN | 2023-01-11 | U126602 | U134723 | 2022-01-06 | 2022-12-30 |  |  | DEREK PAYTON | 2023-01-10 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2639.1 | 0 | 0 | 0 | 2639.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964238100 |  | 100347875 |  | 6748208I | 2075093 |  |  | 565 | EX | REPLACE SL W/20-0269804-00 | 2600B | MAGNOLIA | 3 MAGNOLIA ST | 049 | WIN | 2023-01-11 | U126602 | U134723 | 2022-01-06 | 2022-12-30 |  |  | DEREK PAYTON | 2023-01-10 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3058.41 | 0 | 0 | 0 | 3058.41 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23154517500 |  | 100462596 |  | 6720204P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303176 | 2621P | OAK PLACE | 1700 OAK PLACE CT | 067 | LEX | 2023-01-11 | U125208 | U129939 | 2023-01-10 | 2023-02-17 | 2024-08-31 |  | DMARSTO | 2023-01-10 | 2023-01-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.1 | 3 | 1329.34 | 994.71 | 183.3 | 67.73 | 83.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23154525000 |  | 100301267 |  | 6716212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D247670 | 2621P | DUNKIRK | 1893 DUNKIRK DR | 067 | LEX | 2023-01-11 | U125208 | U129939 | 2023-01-10 | 2022-11-03 | 2024-05-31 |  | WISHII | 2023-01-10 | 2023-01-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.9167 | 4 | 1963.01 | 1130.39 | 295.76 | 475.26 | 61.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12968017500 |  | 100331500 |  | 6720212N |  |  |  | 566 | EX | SOII - METER ABANDON ONLY | 2621P | RICHMOND | 24 RICHMOND AV B | 067 | LEX | 2023-01-11 | HMCKUNE | U124967 | 2012-05-02 | 2014-12-23 |  |  | HMCKUNE | 2023-01-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.5 | 3 | 426.61 | 399.39 | 0 | 27.22 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19758235700 |  | 100345060 |  | 6696212G |  |  |  | 565 | EX | REPLACE SERVICE | 2621P | ELM | 181 ELM ST | 239 | VER | 2023-01-11 | U128816 | U131560 | 2019-11-12 | 2019-11-12 |  |  | OLIVER MAYNARD | 2023-01-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 11 | 1 | 6197.28 | 702.65 | 699.02 | 47.86 | 4747.75 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959957100 |  | 500016278 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | HANSON | 536 HANSON ST | 017 | PAR | 2023-01-11 | U126604 | U134723 | 2021-12-16 | 2023-12-29 |  |  | WILL FULKS | 2023-01-11 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3039.88 | 0 | 0 | 0 | 3039.88 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959957500 |  | 100358962 |  | 6740232I | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | MARSHALL | 521 MARSHALL ST | 017 | PAR | 2023-01-11 | U126286 | U134723 | 2021-12-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-01-11 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2517.34 | 0 | 0 | 0 | 2517.34 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960861300 |  | 100249834 |  | 7356248H | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | PADDLE CREEK | 8019 PADDLE CREEK RD | 019 | CAT | 2023-01-11 | U124015 | U134723 | 2021-12-21 | 2023-06-30 |  |  | ORA SLONE | 2023-01-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1933.35 | 0 | 0 | 0 | 1933.35 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22108240900 |  | 100311074 |  | 6712208N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309179 | 2600B | CINDY BLAIR | 802 CINDY BLAIR WY | 067 | LEX | 2023-01-12 | U128410 | U125208 | 2022-06-07 | 2022-12-02 | 2024-06-30 |  | CDESPAIN | 2023-01-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10 | 1 | 3886.43 | 660.88 | 282.74 | 45.02 | 2897.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22109790800 |  | 100305291 |  | 6712212K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311761 | 2600B | WILLIAMSBURG | 1684 WILLIAMSBURG RD | 067 | LEX | 2023-01-11 | U461322 | U125208 | 2022-06-14 | 2022-12-13 | 2024-06-30 |  | STEVE CANOY | 2023-01-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.25 | 1 | 4859.97 | 769.84 | 0 | 52.42 | 4037.71 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129024300 |  | 100354852 |  | 7260280N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | 3RD | 1411 E 3RD ST | 161 | MAY | 2023-01-11 | SDADAMS | U130722 | 2022-09-05 | 2022-12-30 |  |  | SDADAMS | 2023-01-11 | 2023-01-11 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 12.5667 | 2 | 841.45 | 772.12 | 16.76 | 52.57 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22138328400 |  | 100319186 |  | 6716208O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303187 | 2621P | MELBOURNE | 324 MELBOURNE WY | 067 | LEX | 2023-01-12 | U129722 | U125208 | 2022-10-11 | 2023-04-06 | 2024-10-31 |  | M YOUNG | 2023-01-11 | 2022-12-15 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.2 | 3 | 3363.59 | 962.45 | 262.42 | 70.16 | 2068.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22146894900 |  | 500351822 |  | 7348252H |  |  |  | 566 | EX | ABANDON SL - IDLE/INA/CUSTRQD | 2621P | US ROUTE 60 | 7101 US ROUTE 60 | 019 | ASH | 2023-01-13 | U125208 | U125208 | 2022-11-30 | 2022-12-30 | 2022-12-30 |  | RECUMP | 2023-01-11 | 2023-01-10 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 23.5833 | 4 | 1561.45 | 1242.7 | 19.89 | 298.86 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964238200 |  | 100347806 |  | 6748208I | 2075093 |  |  | 565 | EX | REPLACE SL W/20-0269804-00 | 2600B | MAGNOLIA | 16 MAGNOLIA ST | 049 | WIN | 2023-01-13 | U126602 | U134723 | 2022-01-06 | 2022-12-30 |  |  | DEREK PAYTON | 2023-01-11 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3240.37 | 0 | 0 | 0 | 3240.37 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964239100 |  | 100347810 |  | 6748208I | 2075093 |  |  | 565 | EX | REPLACE SL W/20-0269804-00 | 2600B | MAGNOLIA | 30 MAGNOLIA ST | 049 | WIN | 2023-01-13 | U126602 | U134723 | 2022-01-06 | 2022-12-30 |  |  | DEREK PAYTON | 2023-01-11 | 2023-01-11 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 8 | 1 | 4068.62 | 516.78 | 0 | 35.18 | 3516.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22979055000 |  | 500710200 |  | 6732212I | 0038696 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CLEVELAND | 3281 N CLEVELAND RD | 067 | LEX | 2023-01-23 | U126308 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | J ENSMINGER | 2023-01-11 | 2022-12-13 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.78333 | 1 | 461.32 | 40.23 | 0 | 2.11 | 418.98 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22992020400 |  | 100246059 |  | 7328284J |  |  |  | 565 | EX | REPLACE SERVICE LINE - D258069 | 2600B | STATE RT 8 | 1583 STATE RT 8 | 089 | S P | 2023-01-11 | DESKAGG | U131172 | 2022-04-07 | 2022-10-06 | 2024-04-30 |  | DESKAGG | 2023-01-11 | 2023-01-05 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 19.25 | 2 | 8548.32 | 1201.34 | 310.48 | 259.3 | 6777.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22998256700 |  | 100305289 |  | 6712212K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309079 | 2600B | WILLIAMSBURG | 1692 WILLIAMSBURG RD | 067 | LEX | 2023-01-11 | U461309 | U125208 | 2022-05-03 | 2022-11-02 | 2024-05-31 |  | R.HUMPHREYS | 2023-01-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.5 | 2 | 5190.77 | 994.76 | 381.49 | 219.9 | 3594.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026248200 |  |  |  | 6716212F | 2394810 | U122858 |  | 557 | EX | EMER - INSTALL 2'-2" PMMP | 2621P | TRAFTON | 107 TRAFTON ST 2150 | 067 | LEX | 2023-01-31 | U128132 | U122858 | 2023-01-10 | 2023-01-06 | 2023-01-09 | 2023-01-09 | JOCHOA | 2023-01-11 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2482 |  |  | 100 | 055732230262482 | 1.7667 | 2 | 135.67 | 120.38 | 0 | 8.18 | 0 | 0 | 0.3 | 6.81 | 2
KY | KY - WEST | 2621 | 23026248300 |  |  |  | 6716212F | 2394810 | U122858 |  | 558 | EX | EMER - RETIRE ~2'-2"PMP | 2621P | TRAFTON | 107 TRAFTON ST 2150 | 067 | LEX | 2023-01-23 | U128132 | U122858 | 2023-01-10 | 2023-01-09 | 2023-01-09 | 2023-01-09 | JOCHOA | 2023-01-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2483 |  |  | 100 | 055832230262483 | 0.5 | 0 | 1647.72 | 1377.62 | 0 | 270.1 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23152795100 |  | 100273429 |  | 6680224G |  |  |  | 565 | EX | REPLACE SERVICE -RLA - D304429 | 2621P | SPRUCE | 210 SPRUCE DR | 073 | FRA | 2023-01-11 | DCOLLIN | U125208 | 2023-01-03 | 2023-06-30 | 2025-01-31 |  | DCOLLIN | 2023-01-11 | 2023-01-11 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 14.75 | 2 | 1753.43 | 954.95 | 264.12 | 448.56 | 85.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23153062200 |  | 100466740 |  | 6720216E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311081 | 2621P | SNOW GOOSE | 1673 SNOW GOOSE CR | 067 | LEX | 2023-01-11 | MCRAIG | U125208 | 2023-01-04 | 2023-07-03 | 2025-01-31 |  | MCRAIG | 2023-01-11 | 2023-01-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.3833 | 3 | 1901.23 | 1083.09 | 248.84 | 545.1 | 24.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23154904000 |  | 100461523 |  | 6740232I | 2075121 |  |  | 565 | EX | REPLACE SL W/20-0269806-00 | 2600B | MARSHALL | 525 MARSHALL ST | 017 | PAR | 2023-01-11 | U126286 | U125768 | 2023-01-11 | 2049-12-31 |  |  | TYLER ALLISON | 2023-01-11 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 9 | 1 | 2679.57 | 557.07 | 0 | 37.93 | 2084.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23154923700 |  | 100457033 |  | 6720208I |  |  |  | 565 | EX | GRADE 1 REPLACE SL | 2621P | GRAY HAWK | 1348 GRAY HAWK CT | 067 | LEX | 2023-01-12 | U930915 | U129939 | 2023-01-11 | 2023-01-11 | 2023-01-11 |  | RJCRAWF | 2023-01-11 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.2667 | 2 | 1529.97 | 1095.8 | 185.2 | 248.97 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21902732700 |  | 100291776 |  | 6720216H | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMED - D309183 | 2600B | ZORN | 725 ZORN CT | 067 | LEX | 2023-01-13 | U461322 | AOC SYST | 2021-04-13 | 2022-12-09 | 2024-06-30 |  | STEVE CANOY | 2023-01-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.25 | 1 | 5060.94 | 769.84 | 0 | 728.69 | 3562.41 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21933791900 |  | 100463006 |  | 6688232O | 1635357 |  |  | 565 | EX | AOC INSTALL SLEEVE IN HARD SUR | 2623D | QUACHITA | 101 QUACHITA TL | 073 | FRA | 2023-01-13 | U129731 | AOC SYST | 2021-08-18 | 2022-02-04 | 2022-12-31 |  | F.GOINS | 2023-01-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACN |  | 100 | 056532B26230032 | 8 | 1 | 3800.47 | 513.08 | 0 | 108.72 | 3178.67 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959956600 |  | 100358897 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | HANSON | 509 HANSON ST | 017 | PAR | 2023-01-13 | U126604 | U134723 | 2021-12-16 | 2023-12-29 |  |  | WILL FULKS | 2023-01-13 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2998.36 | 0 | 0 | 0 | 2998.36 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959957600 |  | 100358966 |  | 6740232I | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | MARSHALL | 539 MARSHALL ST | 017 | PAR | 2023-01-13 | U126286 | U134723 | 2021-12-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-01-13 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 8 | 1 | 2675.3 | 495.18 | 0 | 33.71 | 2146.41 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22121585500 |  | 100279478 |  | 6688228O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | ESPERANZA | 305 ESPERANZA DR | 073 | FRA | 2023-01-13 | U128816 | AOC SYST | 2022-08-04 | 2023-02-03 | 2023-12-31 |  | OLIVER MAYNARD | 2023-01-13 | 2022-12-19 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 12.25 | 2 | 5035.91 | 887.89 | 366.11 | 55.24 | 3726.67 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22138328200 |  | 100319175 |  | 6716208O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303188 | 2621P | MELBOURNE | 348 MELBOURNE WY | 067 | LEX | 2023-01-16 | U129722 | U125208 | 2022-10-11 | 2023-04-06 | 2024-10-31 |  | M YOUNG | 2023-01-13 | 2022-12-15 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.1 | 2 | 2957.02 | 481.21 | 265.94 | 35.07 | 2174.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23152801100 |  | 100457460 |  | 6712208J |  |  |  | 565 | EX | REPLACE SERVICE LINE - D310406 | 2621P | LYON | 3475 LYON DR 48 | 067 | LEX | 2023-01-13 | U930915 | U125208 | 2023-01-03 | 2023-01-03 | 2023-01-21 |  | KKINDER | 2023-01-13 | 2023-01-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 75.75 | 13 | 15515.99 | 4235 | 40.05 | 672.48 | 10568.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23154583600 |  | 100418824 |  | 6716216N |  | U125208 |  | 565 | EX | SERVICE LINE REPLACE - D094432 | 2621P | FISTER | 806 FISTER WY | 067 | LEX | 2023-01-13 | DMEDLEY | U125208 | 2023-01-10 | 2023-01-13 | 2023-01-31 |  | DMEDLEY | 2023-01-13 | 2023-01-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25.1167 | 7 | 2668.84 | 1522.65 | 291.51 | 832.68 | 22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23155982200 |  | 500007048 |  | NEW |  |  |  | 566 | EX | LEGACY CLEAN UP | 2621P | ZZZZ | 999 ZZZZ ST | 067 | LEX | 2023-01-13 | MDULANE | MDULANE | 2023-01-13 | 2023-12-29 | 2023-12-31 |  | OFFICE/MDULANE | 2023-01-13 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 23156234000 |  | 100319295 |  | 6716208K |  | U134852 |  | 565 | EX | SERVICE LINE REPLACE | 2621P | LOWRY | 152 E LOWRY LN | 067 | LEX | 2023-01-15 | TROE | U134852 | 2023-01-15 | 2023-01-13 |  |  | TROE | 2023-01-15 | 2023-01-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 2.3333 | 3 | 433.94 | 158.54 | 264.6 | 10.8 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 11919326500 |  | 100273929 |  | 6680228L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | SKYVIEW | 2 SKYVIEW DR | 073 | FRA | 2023-01-16 | U129731 | U907469 | 2011-08-08 | 2022-07-01 | 2022-12-31 |  | F.GOINS | 2023-01-16 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 2.3667 | 1 | 2115.22 | 125.18 | 0 | 287.26 | 1702.78 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21900903100 |  | 100421834 |  | 6680224H | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | RIDGEWOOD | 311 RIDGEWOOD LN | 073 | FRA | 2023-01-16 | U129731 | AOC SYST | 2021-04-06 | 2021-10-06 | 2022-12-31 |  | F.GOINS | 2023-01-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 3.2333 | 1 | 3024.51 | 208.42 | 0 | 44.16 | 2771.93 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959955500 |  | 100407694 |  | 6740232I | 2292664 |  |  | 565 | EX | REPLACE SL W/22-0262303-00 | 2600B | HANSON | 310 HANSON ST | 017 | PAR | 2023-01-16 | U126286 | U134723 | 2021-12-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-01-16 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 9 | 2 | 2753.36 | 557.07 | 0 | 37.93 | 2158.36 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959955600 |  | 100358934 |  | 6740232I | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | HANSON | 312 HANSON ST | 017 | PAR | 2023-01-16 | U126286 | U134723 | 2021-12-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-01-16 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2896.7 | 0 | 0 | 0 | 2896.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959957700 |  | 100359004 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | MARSHALL | 600 MARSHALL ST | 017 | PAR | 2023-01-16 | U126286 | U134723 | 2021-12-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-01-16 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2692.24 | 0 | 0 | 0 | 2692.24 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959958300 |  | 100402591 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | MARSHALL | 619 MARSHALL ST | 017 | PAR | 2023-01-16 | U126286 | U134723 | 2021-12-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-01-16 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1912.92 | 0 | 0 | 0 | 1912.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026238200 |  | 501337683 |  | 6724208G | 2293698 | U461383 |  | 555 | EX | INSTALL 205' OF 2"PMMP MAIN | 2600B | VENDOR | 1770 VENDOR WY STE 100 | 067 | LEX | 2023-01-26 | U128132 | U461383 | 2022-11-16 | 2023-01-25 | 2023-01-31 | 2023-01-16 | JDUNN | 2023-01-16 | 2023-01-11 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2382 |  |  | 100 | 055532220262382 | 39.7667 | 1075 | 13604.24 | 2529.97 | 986.72 | 269.14 | 9075.94 | 0 | 29.03 | 713.44 | 215
KY | KY - WEST | 2621 | 22105101000 |  | 100293455 |  | 6720216I |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311752 | 2600B | MONTROSE | 1559 MONTROSE DR | 067 | LEX | 2023-01-16 | U126284 | U125208 | 2022-06-02 | 2022-12-01 | 2024-06-30 |  | JOSH PASLEY | 2023-01-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11 | 1 | 4370.23 | 731.1 | 0 | 711.03 | 2928.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22108243000 |  | 100465589 |  | 6712208L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309231 | 2600B | DARDANELLES | 716 DARDANELLES DR | 067 | LEX | 2023-01-18 | U461309 | U125208 | 2022-06-07 | 2022-12-02 | 2024-06-30 |  | R.HUMPHREYS | 2023-01-16 | 2023-01-16 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.05 | 2 | 3311.24 | 305.61 | 222.52 | 67.58 | 2715.53 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22111911200 |  | 100273569 |  | 6680224G | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2600B | HAWKEEGAN | 264 HAWKEEGAN DR | 073 | FRA | 2023-01-16 | U128816 | AOC SYST | 2022-06-22 | 2022-12-22 | 2023-12-31 |  | OLIVER MAYNARD | 2023-01-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 10 | 1 | 5365.5 | 638.81 | 452.41 | 43.5 | 4230.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22116766600 |  | 100318083 |  | 6716204G |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309190 | 2600B | KING ARTHUR | 3468 KING ARTHUR DR | 067 | LEX | 2023-01-16 | U461322 | U125208 | 2022-07-18 | 2023-01-13 | 2024-07-31 |  | STEVE CANOY | 2023-01-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.5 | 1 | 4577.8 | 741.31 | 0 | 681.66 | 3154.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22117933300 |  | 100319509 |  | 6716208K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303129 | 2600B | GREENBRIAR | 312 GREENBRIAR RD | 067 | LEX | 2023-01-16 | U124003 | U125208 | 2022-07-22 | 2023-01-20 | 2024-07-31 |  | BPULLIAM/STANLEY | 2023-01-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10 | 1 | 7110.35 | 643.71 | 0 | 1246.08 | 5220.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964243300 |  | 100348032 |  | 6748208I | 2075093 |  |  | 565 | EX | REPLACE SL W/20-0269804-00 | 2600B | STERLING | 45 STERLING ST | 049 | WIN | 2023-01-18 | U126602 | U134723 | 2022-01-06 | 2022-12-30 |  |  | DEREK PAYTON | 2023-01-16 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 6875.7 | 0 | 0 | 0 | 6875.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964247900 |  | 100348014 |  | 6748208I | 2075093 |  |  | 565 | EX | REPLACE SL W/20-0269804-00 | 2600B | STERLING | 110 STERLING ST | 049 | WIN | 2023-01-18 | U126602 | U134723 | 2022-01-06 | 2022-12-30 |  |  | DEREK PAYTON | 2023-01-16 | 2023-01-16 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 12 | 1 | 7857.37 | 775.19 | 0 | 52.76 | 7029.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23156452400 |  | 100336118 |  | 6720212J | 9830863 |  |  | 565 | EX | REPLACE SERVICE LINE - D311449 | 2621P | MAGNOLIA | 664 MAGNOLIA AV | 067 | LEX | 2023-01-19 | U125208 | U137248 | 2023-01-16 | 2023-01-16 | 2023-02-03 |  | LSTANFI | 2023-01-16 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 6.6667 | 3 | 1847.52 | 832.44 | 339.13 | 56.69 | 619.26 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07671551400 |  | 100291159 |  | 6720212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INA - MNFLD | 2621P | BROADWAY | 1412 N BROADWAY ST 103 | 067 | LEX | 2023-01-17 | LSTONE | SSUTHER | 2007-01-08 | 2014-12-01 | 2014-12-31 |  | LSTONE | 2023-01-17 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.75 | 1 | 177.51 | 166.2 | 0 | 11.31 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21900898800 |  | 100273167 |  | 6680224H | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | GLENWOOD | 200 GLENWOOD PL | 073 | FRA | 2023-01-17 | U129731 | AOC SYST | 2021-04-06 | 2021-10-06 | 2022-12-31 |  | F.GOINS | 2023-01-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 11 | 1 | 2839.44 | 705.48 | 0 | 149.49 | 1984.47 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959955300 |  | 100358932 |  | 6740232I | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | HANSON | 305 HANSON ST | 017 | PAR | 2023-01-17 | U126286 | U134723 | 2021-12-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-01-17 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 9 | 1 | 4642.4 | 557.07 | 0 | 37.93 | 4047.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22105095700 |  | 100293465 |  | 6720216I |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309147 | 2600B | MONTROSE | 1578 MONTROSE DR | 067 | LEX | 2023-01-20 | U129673 | U125208 | 2022-06-02 | 2022-12-01 | 2024-06-30 |  | ALEX WILLIAMSON | 2023-01-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9 | 1 | 3520.15 | 584.83 | 306.97 | 122.82 | 2505.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22109791600 |  | 100302177 |  | 6712212L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311785 | 2600B | OXFORD | 1916 OXFORD CR | 067 | LEX | 2023-01-18 | U461309 | U125208 | 2022-06-14 | 2022-12-13 | 2024-06-30 |  | R.HUMPHREYS | 2023-01-17 | 2023-01-12 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11 | 2 | 6726.4 | 684.92 | 535.83 | 115.54 | 5390.11 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22113737400 |  | 100319884 |  | 6716208K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311934 | 2600B | ALBANY | 341 ALBANY RD | 067 | LEX | 2023-01-18 | U128410 | U125208 | 2022-07-01 | 2022-12-30 | 2024-06-30 |  | CDESPAIN | 2023-01-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11 | 1 | 4594 | 726.94 | 355.23 | 49.51 | 3462.32 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22123460200 |  | 100409354 |  | 6688228L | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | TIMBERLAWN | 49 TIMBERLAWN CR | 073 | FRA | 2023-01-17 | U128816 | AOC SYST | 2022-08-11 | 2023-02-10 | 2023-12-31 |  | OLIVER MAYNARD | 2023-01-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 |  | 1 | 3588.69 | 0 | 280.91 | 0 | 3307.78 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22123767000 |  | 100410752 |  | 6688228L | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | TIMBERLAWN | 7 TIMBERLAWN LN | 073 | FRA | 2023-01-17 | U128816 | AOC SYST | 2022-08-12 | 2023-02-10 | 2023-12-31 |  | OLIVER MAYNARD | 2023-01-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 7.1333 | 1 | 4046.63 | 456.09 | 286.36 | 31.06 | 3273.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22137154300 |  | 100324280 |  | 6720204F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094426 | 2621P | OCTAVIAN | 1205 OCTAVIAN CR | 067 | LEX | 2023-01-17 | U126284 | U125208 | 2022-10-06 | 2023-04-05 | 2024-10-31 |  | JOSH PASLEY | 2023-01-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10 | 1 | 3363.82 | 664.65 | 0 | 45.27 | 2653.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22150002400 |  | 100460045 |  | 7320284H |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2600B | UNDERWOOD | 33 UNDERWOOD LN | 089 | S P | 2023-01-18 | U125566 | U124960 | 2022-12-21 | 2022-10-11 | 2024-04-30 |  | DESKAGG | 2023-01-17 | 2023-01-09 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26310022 | 37 | 4 | 6247.61 | 2309.01 | 256.05 | 415.41 | 3267.14 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964243700 |  | 100442129 |  | 6748208I | 2075093 |  |  | 565 | EX | REPLACE SL W/20-0269804-00 | 2600B | STERLING | 116 STERLING ST | 049 | WIN | 2023-01-18 | U126602 | U134723 | 2022-01-06 | 2022-12-30 |  |  | DEREK PAYTON | 2023-01-17 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 6766.77 | 0 | 0 | 0 | 6766.77 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026249200 |  |  |  | 7344268M | 2394931 | U461383 |  | 588 | EX | GMB TO CAB CONVERSION | 2631M | HARRIS | 23 HARRIS RD | 089 | WUR | 2023-02-03 | U123258 | U461383 | 2023-01-13 | 2023-12-01 | 2023-12-01 | 2023-01-17 | SGIORDANO | 2023-01-17 | 2023-01-18 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00588 | 3200588 |  |  | WP2492 |  |  | 100 | 058832230262492 | 11.15 | 0 | 858.55 | 687.32 | 0 | 171.23 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026249400 |  |  |  | 6716208A | 2394938 | U461383 |  | 558 | EX | EMER-RETIRE 5' OF 2"PMMP MAIN | 2621P | BLUE ASH | 620 BLUE ASH DR | 067 | LEX | 2023-03-14 | U128132 | U461383 | 2023-01-16 | 2023-01-13 | 2023-01-13 | 2023-01-17 | DMALONE | 2023-01-17 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2494 |  |  | 100 | 055832230262494 | 3.4167 | 0 | 219.4 | 205.41 | 0 | 13.99 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23156429500 |  | 100291151 |  | 6720212B |  |  |  | 566 | EX | PAPER ABANDON W/100291159 | 2621P | BROADWAY | 1412 N BROADWAY ST 204 | 067 | LEX | 2023-01-19 | U125208 | U125208 | 2023-01-16 | 2023-02-03 |  |  | LSTONE | 2023-01-17 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.6667 | 2 | 184.45 | 172.67 | 0 | 11.78 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23156429700 |  | 100291150 |  | 6720212B |  |  |  | 566 | EX | PAPER ABANDON W/100291159 | 2621P | BROADWAY | 1412 N BROADWAY ST 203 | 067 | LEX | 2023-01-17 | LSTONE | U125208 | 2023-01-16 | 2023-02-03 |  |  | LSTONE | 2023-01-17 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.6 | 2 | 246.31 | 230.61 | 0 | 15.7 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23156429900 |  | 100291158 |  | 6720212B |  |  |  | 566 | EX | PAPER ABANDON W/100291159 | 2621P | BROADWAY | 1412 N BROADWAY ST 109 | 067 | LEX | 2023-01-19 | U125208 | U125208 | 2023-01-16 | 2023-02-03 |  |  | TROE | 2023-01-17 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.5167 | 2 | 110.99 | 103.91 | 0 | 7.08 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23156430200 |  | 500080485 |  | 6720212B |  |  |  | 566 | EX | PAPER ABANDON W/100291159 | 2621P | BROADWAY | 1412 N BROADWAY ST 106 | 067 | LEX | 2023-01-17 | TROE | U125208 | 2023-01-16 | 2023-02-03 |  |  | TROE | 2023-01-17 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.5333 | 2 | 255.69 | 239.41 | 0 | 16.28 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 07689164800 |  | 100271020 |  | 77415297 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LNXBURG FOSTER | 4137 LNXBURG FOSTER RD | 023 | FOS | 2023-01-19 | JTOY | U903504 | 2007-06-01 | 2020-12-31 |  |  | SADAMS | 2023-01-18 | 2022-09-21 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 14.05 | 2 | 1599.4 | 910.76 | 0 | 688.64 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11899704600 |  | 100253783 |  | 7356220P |  |  |  | 565 | EX | RELOCATE SL - PEND OS 01/04/23 | 2621P | SYCAMORE | 403 E SYCAMORE ST | 127 | LOU | 2023-01-20 | U125208 | U123933 | 2011-04-04 | 2023-01-04 | 2023-01-26 |  | BMEEK | 2023-01-18 | 2023-01-04 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 38.6333 | 9 | 4003.37 | 2358.22 | 1043.4 | 522.55 | 79.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21026139400 |  |  |  | 7256280G | 2180424 | U122858 |  | 586 | EX | REMOVE BUILDING FOR R-1455 | 2600E | 2ND | W 2ND ST | 161 | MAY | 2023-01-19 | U123258 | U122858 | 2021-09-01 | 2023-06-30 | 2023-06-30 | 2023-01-18 | JMULLINS | 2023-01-18 | 2022-12-16 |  | F | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00586 | 3200586 |  |  | WP1394 | AMRCB |  | 100 | 058632210261394 | 11.3833 | 0 | 3989.86 | 975.54 | 212 | 50.91 | 2751.41 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959957800 |  | 100359003 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | MARSHALL | 606 MARSHALL ST | 017 | PAR | 2023-01-19 | U126286 | U134723 | 2021-12-16 | 2023-12-29 |  |  | ED FOX | 2023-01-18 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3237.83 | 0 | 0 | 0 | 3237.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22108900900 |  | 100310870 |  | 6712204B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309220 | 2600B | CROMWELL | 717 CROMWELL CT | 067 | LEX | 2023-01-18 | U461309 | U125208 | 2022-06-09 | 2022-12-08 | 2024-06-30 |  | R.HUMPHREYS | 2023-01-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17 | 2 | 5914.14 | 1080.53 | 392.63 | 151.98 | 4289 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22122732700 |  | 100421132 |  | 6688228N | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | MAVERICK | 1308 MAVERICK TL | 073 | FRA | 2023-01-18 | U128816 | AOC SYST | 2022-08-09 | 2023-02-09 | 2023-12-31 |  | OLIVER MAYNARD | 2023-01-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 10.15 | 1 | 6038.11 | 648.39 | 280.91 | 44.13 | 5064.68 | 0 | 0 | 0
KY | KY - EAST | 2682 | 22129012100 |  | 501242008 |  | 7344168G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2633S | LAKE | 1040 LAKE RD | 071 | PRE | 2023-01-18 | U130172 | U130722 | 2022-09-05 | 2022-12-30 | 2022-12-31 |  | JOHN HOWARD | 2023-01-18 | 2023-01-12 |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 3.4333 | 1 | 256.11 | 239.78 | 0 | 16.33 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22137155500 |  | 100324279 |  | 6720204F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094428 | 2621P | OCTAVIAN | 1209 OCTAVIAN CR | 067 | LEX | 2023-01-20 | U129722 | U125208 | 2022-10-06 | 2023-04-05 | 2024-10-31 |  | M YOUNG | 2023-01-18 | 2022-12-15 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.0167 | 2 | 3841.88 | 556.84 | 576.92 | 61.66 | 2646.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026248400 |  |  |  | 6720208A | 2394820 | U461383 |  | 557 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | 2621P | FONTAINE | 1384 FONTAINE RD | 067 | LEX | 2023-02-17 | U128132 | U461383 | 2023-01-10 | 2023-09-29 | 2023-09-30 | 2023-01-18 | LSTANFI | 2023-01-18 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2484 |  |  | 100 | 055732230262484 |  | 4 | 2322.97 | 2002.71 | 35.96 | 157.7 | 0 | 0 | 5.06 | 121.54 | 4
KY | KY - WEST | 2621 | 23026248500 |  |  |  | 6720208A | 2394820 | U461383 |  | 558 | EX | EMER-RETIRE 3' OF 2"PMMP MAIN | 2621P | FONTAINE | 1384 FONTAINE RD | 067 | LEX | 2023-02-16 | U128132 | U461383 | 2023-01-10 | 2023-09-29 | 2023-09-30 | 2023-01-18 | LSTANFI | 2023-01-18 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2485 |  |  | 100 | 055832230262485 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026249300 |  |  |  | 6716208A | 2394938 | U461383 |  | 557 | EX | EMER-INSTALL 5' OF 2"PMMP | 2621P | BLUE ASH | 620 BLUE ASH DR | 067 | LEX | 2023-03-14 | U128132 | U461383 | 2023-01-16 | 2023-01-13 | 2023-01-13 | 2023-01-17 | DMALONE | 2023-01-18 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2493 |  |  | 100 | 055732230262493 | 0.7 | 6 | 5012.41 | 4241.86 | 0 | 442.32 | 0 | 0 | 10.46 | 317.77 | 3
KY | KY - WEST | 2621 | 23154899000 |  | 100325052 |  | 6720204B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D310408 | 2621P | GREENTREE | 3406 GREENTREE RD | 067 | LEX | 2023-01-19 | U930915 | U125208 | 2023-01-11 | 2023-01-13 | 2023-01-31 |  | JOCHOA | 2023-01-18 | 2023-01-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 36.1833 | 7 | 2866.35 | 2277.55 | 213.92 | 337.48 | 37.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23157270700 |  | 100322990 |  | 6716208L |  |  |  | 565 | EX | SERVICE LINE REPLACE D310268 | 2621P | BELLEFONTE | 1832 BELLEFONTE DR | 067 | LEX | 2023-01-20 | U125208 | U137248 | 2023-01-18 | 2023-01-18 | 2023-01-18 |  | KKINDER | 2023-01-18 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.3 | 2 | 1025.13 | 740.41 | 203.51 | 50.41 | 30.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23157305200 |  | 100309599 |  | 6712208H |  |  |  | 565 | EX | SERVICE LINE REPLACE D303822 | 2621P | PHOENIX | 2814 PHOENIX RD | 067 | LEX | 2023-01-20 | U125208 | U137248 | 2023-01-18 | 2023-01-18 | 2023-01-18 |  | WISHII | 2023-01-18 | 2023-01-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.95 | 3 | 2060.52 | 1101.71 | 288.13 | 566.18 | 104.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 01474580500 |  | 500449649 | 12 | 6716212F |  |  |  | 566 | EX | PAPER ABANDON SL-IDLE/INACTIVE | 2621P | VERSAILLES | 1234 VERSAILLES RD 1FR | 067 | LEX | 2023-01-19 | WISHII | GMCALPI | 2001-06-26 | 2020-12-31 |  |  | WISHII | 2023-01-19 | 2023-01-19 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.5167 | 3 | 220.34 | 144.29 | 0 | 76.05 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 13135148000 |  | 100458105 |  | 6716212G | 1315787 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | VALLEY | 947 VALLEY AV | 067 | LEX | 2023-01-19 | U930915 | U123694 | 2013-05-08 | 2014-12-23 |  |  | MCRAIG | 2023-01-19 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.8667 | 3 | 275.13 | 168.14 | 0 | 106.99 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 13179332300 |  | 100303486 |  | 6712208C |  |  |  | 566 | EX | PAPER ABANDON SL-IDLE/INACTIVE | 2621P | OLEANDER | 2145 OLEANDER DR 1FR | 067 | LEX | 2023-01-19 | U930915 | U126921 | 2013-12-03 | 2020-12-31 |  |  | WISHII | 2023-01-19 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.95 | 3 | 283.86 | 175.03 | 0 | 108.83 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19743884800 |  | 100348015 |  | 6748208I |  |  |  | 565 | EX | AOC CSL-REPLACE *HOLD AMRP* | 2621P | STERLING *HOLD AMRP* | 112 STERLING *HOLD AMRP* ST | 049 | WIN | 2023-01-23 | U126602 | U125208 | 2019-09-20 | 2019-10-18 |  |  | DEREK PAYTON | 2023-01-19 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 0 | 1 | 8458.98 | 0 | 0 | 0 | 8458.98 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959957900 |  | 100359002 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | MARSHALL | 612 MARSHALL ST | 017 | PAR | 2023-01-19 | U126286 | U134723 | 2021-12-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-01-19 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 9 | 1 | 3846.03 | 557.07 | 0 | 37.93 | 3251.03 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959958200 |  | 100358968 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | MARSHALL | 617 MARSHALL ST | 017 | PAR | 2023-01-19 | U126286 | U134723 | 2021-12-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-01-19 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2504.95 | 0 | 0 | 0 | 2504.95 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026245300 |  |  |  | 6736208M | 2294549 | U128885 |  | 557 | EX | EMER - INSTALL 5'-2" PMMP | 2621P | COMBS FERRY | 711 COMBS FERRY RD | 049 | WIN | 2023-01-21 | U128132 | U128885 | 2022-12-22 | 2023-01-16 | 2023-06-01 | 2022-12-19 | WDENNING | 2023-01-19 | 2023-01-16 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP2453 |  |  | 100 | 055732220262453 | 1.7333 | 6 | 3807.72 | 2811.41 | 0 | 793.57 | 0 | 0 | 6.08 | 196.66 | 3
KY | KY - CENTRAL | 2629 | 22026245400 |  |  |  | 6736208M | 2294549 | U128885 |  | 558 | EX | EMER - RETIRE 5'-2" PMMP | 2621P | COMBS FERRY | 711 COMBS FERRY RD | 049 | WIN | 2023-01-21 | U128132 | U128885 | 2022-12-22 | 2023-06-01 | 2023-06-01 | 2022-12-19 | WDENNING | 2023-01-19 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP2454 |  |  | 100 | 055832220262454 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22105101500 |  | 100293454 |  | 6720216I |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311753 | 2600B | MONTROSE | 1563 MONTROSE DR | 067 | LEX | 2023-01-20 | U129673 | U125208 | 2022-06-02 | 2022-12-01 | 2024-06-30 |  | ALEX WILLIAMSON | 2023-01-19 | 2023-01-12 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.2667 | 2 | 4102.73 | 927.93 | 238.07 | 194.88 | 2741.85 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22108901300 |  | 100304851 |  | 6712212L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311782 | 2600B | CELIA | 1001 CELIA LN | 067 | LEX | 2023-01-20 | U128410 | U125208 | 2022-06-09 | 2022-12-08 | 2024-06-30 |  | CDESPAIN | 2023-01-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.5 | 1 | 4354.82 | 693.94 | 253.47 | 47.24 | 3360.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129084700 |  | 100457679 |  | 6716212G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MANCHESTER | 1116 MANCHESTER PL | 067 | LEX | 2023-01-19 | MCRAIG | U130722 | 2022-09-05 | 2022-12-30 |  |  | MCRAIG | 2023-01-19 | 2022-10-18 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 19.2667 | 14 | 1989.85 | 1162.89 | 19.7 | 370.2 | 437.06 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23154933600 |  | 100344667 |  | 6700224L |  |  |  | 566 | EX | ABANDON SL - RA/CUSTREQD | 2621P | WINTER | 345 N WINTER ST | 239 | MID | 2023-01-19 | BWHITE | U125208 | 2023-01-11 | 2023-02-10 | 2023-02-11 |  | BWHITE | 2023-01-19 | 2023-01-16 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 13.2 | 4 | 887.82 | 656.96 | 18.58 | 44.78 | 167.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23156036500 |  | 100276942 |  | 6684228D |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | NOEL | 404 NOEL AV | 073 | FRA | 2023-01-20 | U125208 | U132002 | 2023-01-13 | 2023-01-27 | 2023-02-12 |  | BWHITE | 2023-01-19 | 2023-01-19 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 1.7167 | 2 | 253.11 | 78.31 | 1.95 | 5.35 | 167.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23156620100 |  | 100280842 |  | 6688228I |  |  |  | 565 | EX | SERVICE LINE - REPLACE - RLA | 2621P | LANGFORD | 257 LANGFORD AV | 073 | FRA | 2023-01-19 | U128816 | U125208 | 2023-01-17 | 2023-01-31 |  |  | OLIVER MAYNARD | 2023-01-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 18.1833 | 2 | 7395.9 | 1163.54 | 667.76 | 79.26 | 5485.34 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23157505900 |  | 100280841 |  | 6688228I |  |  |  | 565 | EX | RPLC SL/ | 2600B | LANGFORD | 253 LANGFORD AV | 073 | FRA | 2023-01-19 | U128816 | U125763 | 2023-01-19 | 2023-12-29 |  |  | OLIVER MAYNARD | 2023-01-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 0.033333 | 1 | 1757.5 | 2.54 | 564.6 | 0.16 | 1190.2 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23157506000 |  | 100280844 |  | 6688228I |  |  |  | 565 | EX | RPLC SL/ | 2600B | MISSOURI | 270 MISSOURI AV | 073 | FRA | 2023-01-19 | U128816 | U125763 | 2023-01-19 | 2023-12-29 |  |  | OLIVER MAYNARD | 2023-01-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 0.68333 | 1 | 2245.06 | 44.73 | 789.92 | 3.07 | 1407.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07671553800 |  | 100291171 |  | 16720212B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PARIS | PARIS PK | 067 | LEX | 2023-01-20 | LSTONE | SSUTHER | 2007-01-08 | 2023-01-20 | 2023-12-31 |  | LSTONE | 2023-01-20 | 2022-10-06 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.1333 | 3 | 231.87 | 217.11 | 0 | 14.76 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11905023200 |  | 100339041 |  | 6720212E |  |  |  | 566 | EX | PAPER ABANDON SL-IDLE/INACTIVE | 2621P | LOUDON | 101 E LOUDON AV | 067 | LEX | 2023-01-20 | U930915 | U123933 | 2011-05-04 | 2014-12-01 | 2022-12-31 |  | LSTONE | 2023-01-20 | 2023-01-17 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.8833 | 4 | 140.98 | 120.77 | 0 | 20.21 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22109153200 |  | 100305405 |  | 6712212K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311759 | 2600B | TRAVELLER | 1650 TRAVELLER RD | 067 | LEX | 2023-01-20 | U461322 | U125208 | 2022-06-10 | 2022-12-09 | 2024-06-30 |  | STEVE CANOY | 2023-01-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.5 | 1 | 4565.9 | 718.54 | 0 | 680.11 | 3167.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22119372500 |  | 100356256 |  | 7256280J | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMED D404965 | 2632D | TERRE HAUTE | 825 TERRE HAUTE DR | 161 | MAY | 2023-01-20 | SDADAMS | AOC SYST | 2022-07-28 | 2023-01-27 | 2024-07-31 |  | SDADAMS | 2023-01-20 |  |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 | 16 | 2 | 1392.77 | 990.5 | 294.11 | 67.46 | 40.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23154197000 |  | 100269174 |  | 6736252M |  |  |  | 565 | EX | SERVICE LINE - RELOCATE | 2621P | ODDVILLE | 202 ODDVILLE AV | 097 | CYN | 2023-01-20 | NRICHIE | U125208 | 2023-01-09 | 2023-01-12 | 2023-01-30 |  | NRICHIE | 2023-01-20 | 2023-01-18 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26290031 | 22.3 | 6 | 1923.9 | 1439.81 | 218.82 | 221.27 | 44 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23155588400 |  | 100264869 |  | 7348248L |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD-3843 | 2621P | MIDLAND TRAIL | 11802 MIDLAND TRAIL RD | 019 | CAN | 2023-01-20 | RECUMP | U132002 | 2023-01-12 | 2023-01-26 | 2023-02-11 |  | RECUMP | 2023-01-20 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 14.7167 | 2 | 2482.16 | 1332.55 | 32.87 | 509.24 | 607.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23156621000 |  | 100345740 |  | 6696212D |  |  |  | 565 | EX | SERVICE LINE - REPLACE - RLA | 2621P | MARCELLA | 784 MARCELLA ST | 239 | VER | 2023-01-20 | U129731 | U125208 | 2023-01-17 | 2023-01-31 |  |  | F.GOINS | 2023-01-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 1 | 2668.43 | 555 | 0 | 111.6 | 2001.83 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23156622100 |  | 100272247 |  | 6684228O |  |  |  | 565 | EX | SERVICE LINE - REPLACE - RLA | 2621P | LOGAN | 619 LOGAN ST | 073 | FRA | 2023-01-20 | U128816 | U125208 | 2023-01-17 | 2023-01-31 |  |  | OLIVER MAYNARD | 2023-01-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.9667 | 1 | 4535.05 | 511.66 | 787.03 | 34.82 | 3201.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23157261400 |  | 100410830 |  | 6720208H |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | OSAGE | 286 OSAGE CT | 067 | LEX | 2023-01-20 | DETERRIL | U137248 | 2023-01-18 | 2023-01-18 |  |  | DETERRIL | 2023-01-20 | 2023-01-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25.9667 | 6 | 2483.22 | 1411.3 | 302.47 | 725.45 | 44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23157482600 |  | 100315935 |  | 6716208F |  |  |  | 565 | EX | SERVICE LINE REPLACE D310270 | 2621P | CHEROKEE | 136 CHEROKEE PR 1F | 067 | LEX | 2023-01-24 | U125208 | U137248 | 2023-01-19 | 2023-01-19 | 2023-01-19 |  | KKINDER | 2023-01-20 | 2023-01-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 33.5 | 6 | 2748.49 | 2034.67 | 263.74 | 402.78 | 47.3 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23157523600 |  | 100347047 |  | 6696212K |  |  |  | 565 | EX | REPLACE SERVICE LINE D308930 | 2621P | WOODLAWN | 103 WOODLAWN DR | 239 | VER | 2023-01-20 | U125208 | U137248 | 2023-01-19 | 2023-01-19 | 2023-01-19 |  | BWHITE | 2023-01-20 | 2023-01-19 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 22.3333 | 4 | 2706.79 | 1185.07 | 335.52 | 80.7 | 1105.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23157643100 |  | 100313172 |  | 6716208B |  |  |  | 565 | EX | SERVICE LINE REPLACE | 2621P | LAFAYETTE | 298 LAFAYETTE PY | 067 | LEX | 2023-01-20 | MCRAIG | U134852 | 2023-01-20 | 2023-01-20 | 2023-01-20 |  | MCRAIG | 2023-01-20 | 2023-01-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.4833 | 5 | 2725.87 | 1431.53 | 458.14 | 769.1 | 67.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23157977000 |  | 100438058 |  | 6744208N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303510 | 2621P | HOLIDAY | 224 HOLIDAY RD | 049 | WIN | 2023-01-24 | U125208 | U131169 | 2023-01-22 | 2023-01-22 | 2023-01-22 |  | DENNING | 2023-01-22 | 2023-01-22 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26290021 | 14.6167 | 6 | 1618.79 | 1064.92 | 211.08 | 269.09 | 73.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12968037300 |  | 100459035 |  | 6720212M |  |  |  | 566 | EX | SOII - ABANDON /MNFLD | 2621P | ASHLAND | 273 S ASHLAND AV 3F | 067 | LEX | 2023-01-24 | U125208 | U124967 | 2012-05-02 | 2049-12-31 |  |  | RJCRAWF | 2023-01-23 | 2022-09-01 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.3333 | 4 | 720.65 | 422.09 | 0 | 32.32 | 266.24 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960861200 |  | 501179760 |  | 7356248H | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | PADDLE CREEK | 8018 PADDLE CREEK RD | 019 | CAT | 2023-01-23 | U125566 | U134723 | 2021-12-21 | 2023-06-30 |  |  | DAVID SKAGGS | 2023-01-23 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 4531.69 | 0 | 0 | 0 | 4531.69 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026210301 |  | 501333276 |  | 6716212F | 2289879 | U461383 |  | 555 | EX | INSTALL 850' OF 4"PMMP MAIN | 2600B | FORBES | 554 S FORBES RD VAUGHN | 067 | LEX | 2023-01-26 | U128132 | U461383 | 2023-01-06 | 2022-12-06 | 2023-02-01 | 2023-01-11 | JOSHUA COX | 2023-01-23 | 2023-01-09 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2103 |  |  | 100 | 055532220262103 | 339.6667 | 33538 | 172217.52 | 25766.24 | 6711.81 | 3353.69 | 125046.63 | 0 | 738.15 | 10601 | 818
KY | KY - WEST | 2621 | 22113724000 |  | 100312653 |  | 6716208E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311861 | 2600B | LONGVIEW | 497 LONGVIEW DR | 067 | LEX | 2023-01-23 | U461322 | U125208 | 2022-07-01 | 2022-12-30 | 2024-06-30 |  | STEVE CANOY | 2023-01-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.25 | 1 | 4709.4 | 632.99 | 0 | 599.14 | 3477.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22114209400 |  | 100316111 |  | 6716208F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311914 | 2600B | PIN OAK | 110 PIN OAK DR | 067 | LEX | 2023-01-23 | U129673 | U125208 | 2022-07-06 | 2023-01-05 | 2024-07-31 |  | ALEX WILLIAMSON | 2023-01-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.75 | 1 | 5292.34 | 759.68 | 261.11 | 150.85 | 4120.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22115125900 |  | 100311296 |  | 6712204C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D246253 | 2600B | CROMWELL | 615 CROMWELL WY | 067 | LEX | 2023-01-23 | U461309 | U125208 | 2022-07-11 | 2023-01-06 | 2024-07-31 |  | R.HUMPHREYS | 2023-01-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 4947.25 | 527.92 | 590.9 | 35.95 | 3792.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22138328900 |  | 100319182 |  | 6716208O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303186 | 2621P | NANTUCKET | 3284 NANTUCKET RD | 067 | LEX | 2023-01-24 | U129722 | U125208 | 2022-10-11 | 2023-04-06 | 2024-10-31 |  | M YOUNG | 2023-01-23 | 2022-12-15 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4 | 2 | 3126.58 | 260.95 | 494.04 | 43.13 | 2328.46 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22138957900 |  | 100460438 |  | 7344264A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE 565 | 2621P | UHLEN BRANCH | 512 UHLEN BRANCH RD L2 | 089 | WUR | 2023-01-23 | JKEENER | U463030 | 2022-10-13 | 2023-05-08 | 2023-05-08 |  | JKEENER | 2023-01-23 | 2023-01-23 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 24.4333 | 4 | 1527.21 | 1258.26 | 0 | 268.95 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22148975600 |  | 100347179 |  | 6696212K | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER | 2623D | CLIFTON | 119 CLIFTON RD | 239 | VER | 2023-01-23 | BWHITE | AOC SYST | 2022-12-14 | 2023-01-06 | 2023-02-05 |  | BWHITE | 2023-01-23 | 2023-01-23 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 26.2667 | 3 | 2560.13 | 1441.23 | 325.93 | 98.17 | 694.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964243600 |  | 100348013 |  | 6748208I | 2075093 |  |  | 565 | EX | REPLACE SL W/20-0269804-00 | 2600B | STERLING | 108 STERLING ST | 049 | WIN | 2023-01-23 | U126602 | U134723 | 2022-01-06 | 2022-12-30 |  |  | DEREK PAYTON | 2023-01-23 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 5717.24 | 0 | 0 | 0 | 5717.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23153063200 |  | 100297925 |  | 6716212H |  |  |  | 566 | EX | ABANDON SL - DEMO/LNDMRK | 2621P | LEE | 225 LEE ST 6 | 067 | LEX | 2023-01-23 | MCRAIG | U125208 | 2023-01-04 | 2023-01-06 | 2023-01-30 |  | MCRAIG | 2023-01-23 | 2023-01-16 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 14.5167 | 7 | 1656.92 | 862.28 | 255.99 | 538.65 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23156621900 |  | 100279461 |  | 6688228O |  |  |  | 565 | EX | SERVICE LINE - REPLACE - RLA | 2600B | GALBRAITH | 1704 GALBRAITH RD | 073 | FRA | 2023-01-23 | U128816 | U125208 | 2023-01-17 | 2023-01-31 |  |  | OLIVER MAYNARD | 2023-01-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8.95 | 1 | 3626.41 | 574.93 | 385.76 | 39.16 | 2626.56 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23156622300 |  | 100347029 |  | 6696212K |  |  |  | 565 | EX | SERVICE LINE - REPLACE - RLA | 2621P | WOODLAWN | 110 WOODLAWN DR | 239 | VER | 2023-01-23 | U129731 | U125208 | 2023-01-17 | 2023-01-31 |  |  | F.GOINS | 2023-01-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 1 | 2336.7 | 569.02 | 0 | 73.8 | 1693.88 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23158038800 |  | 100447792 |  | 6740232M | 2075121 |  |  | 565 | EX | REPLACE W/ 22026230300 | 2600B | THOMAS | 519 THOMAS AV | 017 | PAR | 2023-01-23 | U126286 | U125768 | 2023-01-23 | 2049-12-31 |  |  | TYLER ALLISON | 2023-01-23 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 8.5 | 1 | 2603.4 | 526.15 | 0 | 35.85 | 2041.4 | 0 | 0 | 0
KY | KY - EAST | 2633 | 04578133700 |  | 100414455 |  | 7384168I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ROGERS PR 160 NOSBEN F | ROGERS PR 160 NOSBEN F RD | 195 | S W | 2023-01-26 | U125208 | DYOUNG | 2004-06-16 | 2014-12-31 |  |  | JCKIRK | 2023-01-24 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 12.3333 | 3 | 861.4 | 806.49 | 0 | 54.91 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959957300 |  | 100359007 |  | 6740232I | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | MARSHALL | 412 MARSHALL ST | 017 | PAR | 2023-01-24 | U126286 | U134723 | 2021-12-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-01-24 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 9 | 1 | 4474.21 | 557.07 | 0 | 37.93 | 3879.21 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026211700 |  |  |  | 6716216N | 1855322 | U461383 |  | 576 | EX | RETIRE LAND AND REG SITE | 2600E | BURKE | 247 BURKE RD | 067 | LEX | 2023-02-22 | U123258 | U461383 | 2022-07-14 | 2023-12-01 | 2023-12-01 | 2023-01-24 | LAND SERVICES | 2023-01-24 |  |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00576 | 3200576 |  |  | WP2117 |  |  | 100 | 057632220262117 |  | 0 | 46152.61 | 0 | 0 | 0 | 46152.61 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22108241500 |  | 100457757 |  | 6712204C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309217 | 2600B | CORNWALL | 3436 CORNWALL DR | 067 | LEX | 2023-02-06 | U128410 | U125208 | 2022-06-07 | 2022-12-02 | 2024-06-30 |  | CDESPAIN | 2023-01-24 | 2023-01-12 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.4167 | 3 | 5787.83 | 1581.77 | 325.19 | 945.7 | 2935.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22124645900 |  | 100418665 |  | 6720204C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311480 | 2600B | TANFORAN | 1324 TANFORAN DR | 067 | LEX | 2023-01-24 | U461322 | U125208 | 2022-08-17 | 2023-02-14 | 2024-08-31 |  | STEVE CANOY | 2023-01-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.25 | 1 | 4287.9 | 701.44 | 0 | 663.91 | 2922.55 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22137508400 |  | 100319365 |  | 6716208O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333647 | 2621P | LOWRY | 307 E LOWRY LN | 067 | LEX | 2023-01-25 | U129722 | U125208 | 2022-10-07 | 2023-04-06 | 2024-10-31 |  | M YOUNG | 2023-01-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 3560.42 | 473.09 | 546.86 | 32.22 | 2508.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22150006300 |  | 100335092 |  | 6720212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2600B | HENRY CLAY | 812 HENRY CLAY BV | 067 | LEX | 2023-01-24 | U129673 | U124960 | 2022-12-21 | 2022-12-15 | 2024-06-30 |  | ALEX WILLIAMSON | 2023-01-24 | 2022-08-25 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26210022 | 11.5833 | 6 | 9813.47 | 910.21 | 440.86 | 133.51 | 8328.89 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964243500 |  | 100348012 |  | 6748208I | 2075093 |  |  | 565 | EX | REPLACE SL W/20-0269804-00 | 2600B | STERLING | 106 STERLING ST | 049 | WIN | 2023-01-27 | U126602 | U134723 | 2022-01-06 | 2022-12-30 |  |  | DEREK PAYTON | 2023-01-24 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 5245.1 | 0 | 0 | 0 | 5245.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026251100 |  |  |  | 7360240B | 2394960 | U461383 |  | 587 | EX | INSTALL EC-350 UNIT | 2631M | OLD US 23 | 15085 OLD US 23 CAT | 019 | CAT | 2023-02-02 | U123258 | U461383 | 2023-01-17 | 2023-09-29 | 2023-10-01 | 2023-01-24 | DASH | 2023-01-24 | 2023-01-24 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00587 | 3200587 |  |  | WP2511 |  |  | 100 | 058732230262511 | 22.2667 | 6 | 1808.88 | 1336.86 | 0 | 377.17 | 0 | 0 | 4.01 | 90.84
KY | KY - EAST | 2631 | 23026251200 |  |  |  | 7360240B | 2394960 | U461383 |  | 588 | EX | RETIRE PAPER BILLING CHART | 2631M | LINE-B/OLD-US23 | LINE-B/OLD-US23 CAT | 019 | CAT | 2023-02-02 | U123258 | U461383 | 2023-01-17 | 2023-09-29 | 2023-10-01 | 2023-01-24 | DASH | 2023-01-24 | 2023-01-24 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00588 | 3200588 |  |  | WP2512 |  |  | 100 | 058832230262512 | 10.5 | 0 | 975.93 | 640.74 | 0 | 335.19 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23156622500 |  | 100280569 |  | 6688228I |  |  |  | 565 | EX | SERVICE LINE - REPLACE - RLA | 2621P | HICKORY | 155 HICKORY DR | 073 | FRA | 2023-01-24 | U128816 | U125208 | 2023-01-17 | 2023-01-31 |  |  | OLIVER MAYNARD | 2023-01-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.05 | 1 | 3261.38 | 390.32 | 562.12 | 26.59 | 2282.35 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23156622900 |  | 100406038 |  | 6688232O |  |  |  | 565 | EX | SERVICE LINE - REPLACE - RLA | 2621P | TONKAWA | 214 TONKAWA TL | 073 | FRA | 2023-01-24 | U128816 | U125208 | 2023-01-17 | 2023-01-31 |  |  | OLIVER MAYNARD | 2023-01-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.9 | 1 | 3372.05 | 248.49 | 665.06 | 16.92 | 2441.58 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23156624300 |  | 100347025 |  | 6696212K |  |  |  | 565 | EX | SERVICE LINE - REPLACE - RLA | 2621P | WOODLAWN | 102 WOODLAWN DR | 239 | VER | 2023-01-24 | U129731 | U125208 | 2023-01-17 | 2023-01-31 |  |  | F.GOINS | 2023-01-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 1 | 3317.77 | 883.71 | 0 | 133.97 | 2300.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23157508300 |  | 100460914 |  | 6716204K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D310269 | 2621P | FOREST GREEN | 3937 FOREST GREEN DR | 067 | LEX | 2023-01-26 | U125208 | U125208 | 2023-01-19 | 2023-01-20 | 2023-02-08 |  | RJCRAWF | 2023-01-24 | 2023-01-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.8 | 6 | 2376.87 | 2133.25 | 40.05 | 145.27 | 58.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23158264700 |  | 100286669 |  | 6768172F |  |  |  | 566 | EX | RETIRE SERVICE LINE - LEAKAGE | 2621P | ELM | 313 ELM ST | 065 | RAV | 2023-01-24 | DENNING | U137248 | 2023-01-24 | 2023-02-24 | 2024-08-31 |  | DENNING | 2023-01-24 | 2023-01-19 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 7.0333 | 6 | 1580.49 | 1479.73 | 0 | 100.76 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23158327400 |  | 100248782 |  | 7356256I |  |  |  | 565 | EX | SERVICE LINE - REPL/RELOC | 2621P | SHUTE | 2913 SHUTE ST | 019 | ASH | 2023-01-27 | U125208 | U137248 | 2023-01-24 | 2023-01-24 |  |  | RECUMP | 2023-01-24 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 16.85 | 3 | 1860.29 | 1479.26 | 18.21 | 316.62 | 46.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 06669230700 |  | 100332475 |  | 6720212M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SAYRE | 637 SAYRE AV | 067 | LEX | 2023-01-26 | U125208 | SSUTHER | 2006-12-21 | 2015-01-27 |  |  | LSTANFI | 2023-01-25 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.7833 | 5 | 342.7 | 274.9 | 0 | 67.8 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18589868700 |  | 100293637 |  | 6720212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BROADWAY *INVALID ADD* | 1203 N BROADWAY *INVALID ADD* ST | 067 | LEX | 2023-01-25 | TROE | U131168 | 2018-02-26 | 2049-12-31 |  |  | TROE | 2023-01-25 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.05 | 1 | 296.19 | 277.31 | 0 | 18.88 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19698763000 |  | 100338661 | 40 | 6720212F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LOUDON | 128 E LOUDON AV | 067 | LEX | 2023-01-25 | LSTANFI | EBLANTO | 2019-04-18 | 2019-05-17 |  |  | LSTANFI | 2023-01-25 | 2022-10-07 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 40.8833 | 18 | 2856.14 | 2134.65 | 0 | 185.49 | 536 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959957400 |  | 100359006 |  | 6740232I | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | MARSHALL | 416 MARSHALL ST | 017 | PAR | 2023-01-25 | U126286 | U134723 | 2021-12-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-01-25 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 9 | 1 | 3565.22 | 557.03 | 0 | 37.92 | 2970.27 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964243000 |  | 100348007 |  | 6748208I | 2075093 |  |  | 565 | EX | REPLACE SL W/20-0269804-00 | 2600B | STERLING | 22 STERLING ST | 049 | WIN | 2023-02-02 | U126602 | U134723 | 2022-01-06 | 2022-12-30 |  |  | DEREK PAYTON | 2023-01-25 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 5392.03 | 0 | 0 | 0 | 5392.03 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964243400 |  | 100447659 |  | 6748208I | 2075093 |  |  | 565 | EX | REPLACE SL W/20-0269804-00 | 2600B | STERLING | 51 STERLING ST | 049 | WIN | 2023-01-25 | U126602 | U134723 | 2022-01-06 | 2022-12-30 |  |  | DEREK PAYTON | 2023-01-25 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 9349.52 | 0 | 0 | 0 | 9349.52 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026248600 |  |  |  | 7356256B | 2395165 | U132280 |  | 558 | EX | RETIRE 3'-3" PMLP | 2621P | 22ND | 22ND | 019 | ASH | 2023-03-23 | U128132 | U132280 | 2023-01-10 | 2023-01-10 | 2049-12-31 | 2023-01-10 | MCOLLET | 2023-01-25 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP2486 |  |  | 100 | 055832230262486 | 10.4167 | 0 | 3012.93 | 1241.6 | 74.62 | 1696.71 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026249800 |  |  |  | 6720208B | 2394960 | U461383 |  | 587 | EX | INSTALL EC 350 UNIT | 2600M | RICHMOND | 1900 RICHMOND RD | 067 | LEX | 2023-02-01 | U123258 | U461383 | 2023-01-16 | 2023-09-29 | 2023-10-01 | 2023-01-25 | CMCHOLAN | 2023-01-25 | 2023-01-24 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00587 | 3200587 |  |  | WP2498 |  |  | 100 | 058732230262498 | 18.3167 | 6 | 5379.35 | 1194.7 | 1176.37 | 405.38 | 1940 | 0 | 3.76 | 659.14
KY | KY - WEST | 2621 | 23026249900 |  |  |  | 6720208B | 2394960 | U461383 |  | 588 | EX | RETIRE PAPER BILLING CHART | 2600M | RICHMOND | 1900 RICHMOND RD | 067 | LEX | 2023-02-01 | U123258 | U461383 | 2023-01-16 | 2023-09-29 | 2023-10-01 | 2023-01-25 | SMCHOLAN | 2023-01-25 | 2023-01-25 |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00588 | 3200588 |  |  | WP2499 |  |  | 100 | 058832230262499 | 6.7167 | 0 | 463.02 | 433.49 | 0 | 29.53 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026252600 |  |  |  | 6720212B | 2395075 | U461383 |  | 557 | EX | INSTALL 3' OF 4"PMLP MAIN | 2621P | LOCUST | 216 LOCUST AV | 067 | LEX | 2023-02-16 | U128132 | U461383 | 2023-01-20 | 2023-12-28 | 2024-08-26 | 2023-01-25 | LSTANFI | 2023-01-25 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2526 | AMRCB |  | 100 | 055732230262526 | 0.23333 | 5 | 16571.37 | 3932.04 | 307.2 | 278.6 | 9758.8 | 0 | 7.8 | 2286.93 | 5
KY | KY - WEST | 2621 | 23026252700 |  |  |  | 6720212B | 2395075 | U461383 |  | 558 | EX | RETIRE 69' OF 4"BSLP MAIN | 2621P | LOCUST | 216 LOCUST AV | 067 | LEX | 2023-02-16 | U128132 | U461383 | 2023-01-20 | 2023-12-29 | 2024-08-26 | 2023-01-25 | LSTANFI | 2023-01-25 | 2023-01-24 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2527 | AMRCB |  | 100 | 055832230262527 | 49.3833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23155012100 |  | 100310198 |  | 6716208A |  |  |  | 565 | EX | REPLACE SERVICE - RJCRAWF 1/24 | 2621P | SPRINGRIDGE | 667 SPRINGRIDGE DR | 067 | LEX | 2023-01-25 | ABLAKE | U125208 | 2023-01-11 | 2023-01-24 |  |  | ABLAKE | 2023-01-25 | 2023-01-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25.5833 | 5 | 4651.49 | 1690.13 | 253.5 | 114.61 | 2593.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23158483200 |  | 100294703 |  | 6716212D | 2286524 |  |  | 565 | EX | RPLC SL/22026167200 | 2600B | JEFFERSON | 549 JEFFERSON ST | 067 | LEX | 2023-01-26 | U461375 | U125763 | 2023-01-25 | 2023-12-29 |  |  | LARRY BROWN | 2023-01-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2270.39 | 0 | 0 | 0 | 2270.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23158484200 |  | 100294704 |  | 6716212D | 2286524 |  |  | 565 | EX | RPLC SL/22026167200 | 2600B | JEFFERSON | 547 JEFFERSON ST | 067 | LEX | 2023-01-26 | U461375 | U125763 | 2023-01-25 | 2023-12-29 |  |  | LARRY BROWN | 2023-01-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2599.9 | 311.57 | 1.1 | 20.14 | 2267.09 | 0 | 0 | 0
KY | KY - EAST | 2633 | 11899916700 |  | 500008383 |  | 7324132F | 2290467 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SR550 (MAIN) | 933 SR550 (MAIN) ST E | 119 | HIN | 2023-01-30 | U125208 | U124449 | 2011-04-05 | 2020-12-31 |  |  | JAHOWARD | 2023-01-26 | 2023-01-26 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 20.05 | 3 | 1424.68 | 1333.86 | 0 | 90.82 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 14211148200 |  | 100466915 |  | 6720212K |  |  |  | 566 | EX | PAPER ABANDON - IDLE/INACTIVE | 2621P | (MTR ABN ) EASTLAND | 1008 (MTR ABN ) EASTLAND DR B | 067 | LEX | 2023-01-30 | U125208 | U125208 | 2014-04-07 | 2020-12-31 |  |  | LSTANFI | 2023-01-26 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.1667 | 3 | 546.51 | 467.23 | 0 | 79.28 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959954600 |  | 100358979 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | FIELDS | 206 FIELDS ST | 017 | PAR | 2023-01-30 | U126286 | U134723 | 2021-12-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-01-26 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2961.86 | 0 | 0 | 0 | 2961.86 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959954700 |  | 100358980 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | FIELDS | 211 FIELDS ST | 017 | PAR | 2023-01-30 | U126286 | U134723 | 2021-12-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-01-26 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 9 | 1 | 3724.64 | 557.03 | 0 | 37.92 | 3129.69 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22113733100 |  | 100310272 |  | 6716208A |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311902 | 2600B | PERSHING | 1910 PERSHING DR | 067 | LEX | 2023-01-26 | U461322 | U125208 | 2022-07-01 | 2022-12-28 | 2024-06-30 |  | STEVE CANOY | 2023-01-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.5 | 1 | 7401 | 650.08 | 0 | 615.33 | 6135.59 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22114601300 |  | 100282489 |  | 6712228C |  |  |  | 565 | EX | REPLACE SERVICE - RLA- D311847 | 2621P | MAIN | 524 E MAIN ST | 209 | GEO | 2023-01-26 | U128816 | U125208 | 2022-07-07 | 2023-01-06 | 2024-07-31 |  | OLIVER MAYNARD | 2023-01-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.6667 | 1 | 5793.62 | 575.25 | 701.49 | 39.18 | 4477.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22122234400 |  | 100292621 |  | 6720216N |  |  |  | 565 | EX | SERVICE LINE - REPLACE/RELOCAT | 2621P | HAWTHORNE | 1724 HAWTHORNE LN | 067 | LEX | 2023-01-26 | TROE | U125208 | 2022-08-08 | 2022-10-31 | 2022-12-31 |  | TROE | 2023-01-26 | 2022-11-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 42.5 | 13 | 8237.29 | 2564.82 | 528.16 | 211.7 | 4932.61 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129026100 |  | 100437855 |  | 7240216L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 1ST | 901 1ST ST B | 173 | MT | 2023-01-26 | DENNING | U130722 | 2022-09-05 | 2022-12-30 |  |  | DENNING | 2023-01-26 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 15.1 | 3 | 1109.15 | 1038.44 | 0 | 70.71 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129026300 |  | 100438493 |  | 7240216L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 1ST | 901 1ST ST C | 173 | MT | 2023-01-30 | U125208 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DENNING | 2023-01-26 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.9 | 3 | 658.46 | 616.49 | 0 | 41.97 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22142991300 |  | 100337929 |  | 6712220M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LEESTOWN | 3745 LEESTOWN RD | 067 | LEX | 2023-01-26 | WISHII | U125208 | 2022-11-04 | 2022-12-02 | 2022-12-04 |  | WISHII | 2023-01-26 | 2022-11-28 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 20.95 | 12 | 1756.92 | 1278.95 | 19.46 | 458.51 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964242900 |  | 100348038 |  | 6748208I | 2075093 |  |  | 565 | EX | REPLACE SL W/20-0269804-00 | 2600B | STERLING | 17 STERLING ST | 049 | WIN | 2023-01-27 | U126603 | U134723 | 2022-01-06 | 2022-12-30 |  |  | SHAWN DENIS | 2023-01-26 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3143.29 | 0 | 0 | 0 | 3143.29 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964243100 |  | 100348036 |  | 6748208I | 2075093 |  |  | 565 | EX | REPLACE SL W/20-0269804-00 | 2600B | STERLING | 37 STERLING ST | 049 | WIN | 2023-01-27 | U126603 | U134723 | 2022-01-06 | 2022-12-30 |  |  | SHAWN DENNIS | 2023-01-26 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3624.65 | 0 | 0 | 0 | 3624.65 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22994266700 |  | 500011762 |  | 6700212A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | ASHBY | 236 ASHBY CR | 239 | VER | 2023-01-26 | U129731 | AOC SYST | 2022-04-18 | 2022-10-18 | 2023-12-31 |  | F.GOINS | 2023-01-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 9 | 1 | 2285.92 | 577.25 | 0 | 79.43 | 1629.24 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23156624900 |  | 100282429 |  | 6712232L |  |  |  | 565 | EX | SERVICE LINE - REPLACE - RLA | 2621P | DEGARIS MILL | 1060 DEGARIS MILL RD | 209 | GEO | 2023-01-26 | U128816 | U125208 | 2023-01-17 | 2023-01-31 |  |  | OLIVER MAYNARD | 2023-01-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.25 | 1 | 4285.6 | 272.75 | 604.47 | 18.6 | 3389.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23158330200 |  | 100301317 |  | 6712212H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309115 | 2621P | DUNKIRK | 1926 DUNKIRK DR | 067 | LEX | 2023-01-26 | WISHII | U137248 | 2023-01-24 | 2022-11-16 | 2024-05-31 |  | WISHII | 2023-01-26 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 2.1833 | 2 | 1363.99 | 518.91 | 375.38 | 356.4 | 113.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23158483300 |  | 100294696 |  | 6716212D | 2286524 |  |  | 565 | EX | RPLC SL/22026167200 | 2600B | JEFFERSON | 550 JEFFERSON ST | 067 | LEX | 2023-01-27 | U461375 | U125763 | 2023-01-25 | 2023-12-29 |  |  | LARRY BROWN | 2023-01-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2207.69 | 0 | 0 | 0 | 2207.69 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23158662900 |  | 100336939 |  | 6720212E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | M L KING | 468 M L KING BV | 067 | LEX | 2023-01-26 | U126532 | U137248 | 2023-01-26 | 2023-01-25 | 2023-01-25 |  | LESLIE SHARON | 2023-01-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26210022 | 7.9833 | 1 | 1062.48 | 517.83 | 0 | 514.95 | 29.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23159112800 |  | 100335026 |  | 6720212K | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMED-D311762 | 2600B | WYATT | 1613 WYATT PY | 067 | LEX | 2023-01-31 | U126285 | U125763 | 2023-01-30 | 2022-12-15 | 2024-06-30 |  | DDAVIS | 2023-01-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 88 | 0 | 0 | 0 | 88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 98349381600 |  | 100336185 |  | 6720212J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | (MTR ABN) WINCHESTER | 623 (MTR ABN) WINCHESTER RD | 067 | LEX | 2023-01-30 | U125208 | TDORTEN | 1998-06-08 | 2014-12-31 |  |  | LSTANFI | 2023-01-26 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.8333 | 2 | 153.38 | 118.85 | 0 | 34.53 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026229200 |  | 500613366 |  | 6688228A | 2292456 | U126783 |  | 555 | EX | INSTALL 80'-2" PMMP | 2600B | COLONIAL | 760 COLONIAL TC | 073 | FRA | 2023-02-06 | U128132 | U126783 | 2022-10-04 | 2023-03-15 | 2023-03-17 | 2023-01-27 | ALEX WILLIAMSON | 2023-01-27 | 2023-01-25 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2292 |  |  | 100 | 055532220262292 | 32.5 | 480 | 10781.29 | 2111.87 | 333.14 | 443.52 | 7042.51 | 0 | 18.25 | 832 | 160
KY | KY - CENTRAL | 2629 | 22129026200 |  | 100438492 |  | 7240216L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 1ST | 901 1ST ST D | 173 | MT | 2023-01-27 | DENNING | U130722 | 2022-09-05 | 2022-12-30 |  |  | DENNING | 2023-01-27 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4 | 2 | 298.66 | 279.62 | 0 | 19.04 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129063300 |  | 501226999 |  | 7240216E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CLUB HOUSE | 1344 CLUB HOUSE LN | 173 | MT | 2023-01-27 | DENNING | U130722 | 2022-09-05 | 2022-12-30 |  |  | DENNING | 2023-01-27 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.1 | 2 | 1089.51 | 289.36 | 0 | 19.71 | 780.44 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129074900 |  | 100239402 |  | 7352264I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ETNA | 421 ETNA ST | 089 | RUS | 2023-01-27 | RECUMP | U130722 | 2022-09-05 | 2022-12-30 |  |  | RECUMP | 2023-01-27 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 15.5167 | 2 | 1041.19 | 914.67 | 64.28 | 62.24 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129371000 |  | 100315740 |  | 6716208G |  |  |  | 565 | EX | REPLACE SERV - D192563 D303177 | 2600B | NICHOLASVILLE | 1603 NICHOLASVILLE RD | 067 | LEX | 2023-02-01 | U128711 | U125208 | 2022-09-07 |  |  |  | KKINDER | 2023-01-27 | 2023-01-26 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 62.15 | 7 | 7586.92 | 3729.28 | 534.21 | 253.89 | 3069.54 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026249600 |  |  |  | 6688228D | 2394770 | U132257 |  | 559 | CO | PM- DE ILI PH 2 JIM BEAM INST | 5320E | GEORGETOWN | 3200 GEORGETOWN RD | 073 | FRA | 2023-05-15 |  | U134275 | 2023-01-16 | 2023-12-28 | 2023-12-31 | 2023-01-27 | BJOHNSON | 2023-01-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00559 | 3201033 |  |  | WP2496 |  |  | 100 | 103332230262496 |  | 22 | 965942.08 | 329.88 | 82793.73 | 118.19 | 768217.03 | 0 | 1299.99 | 113183.26 | 22
KY | KY - WEST | 2623 | 23026249700 |  |  |  | 6688228D | 2394770 | U132257 |  | 560 | CO | PM- DE ILI PH 2 JIM BEAM ABAN | 5320E | GEORGETOWN | 3200 GEORGETOWN RD | 073 | FRA | 2023-05-15 |  | U134275 | 2023-01-16 | 2023-12-28 | 2023-12-31 | 2023-01-27 | BJOHNSON | 2023-01-27 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00560 | 3201032 |  |  | WP2497 |  |  | 100 | 103232230262497 |  | 0 | 234155.55 | 0 | 51522.36 | 0 | 182633.19 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026253900 |  |  |  | 6720212K | 2395179 | U461383 |  | 584 | EX | RETIRE PRESSURE GAUGE | 2621M | GOODWIN | 1039 GOODWIN DR | 067 | LEX | 2023-02-01 | U123258 | U461383 | 2023-01-25 | 2023-09-29 | 2023-10-01 | 2023-01-27 | JMULLINS | 2023-01-27 |  |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00584 | 3200584 |  |  | WP2539 |  |  | 100 | 058432230262539 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23157277100 |  | 100360927 |  | 6740224T |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | CLINTONVILLE | 1608 CLINTONVILLE RD | 017 | PAR | 2023-01-30 | JTOY | U125208 | 2023-01-18 | 2023-01-20 | 2023-02-08 |  | NRICHIE | 2023-01-27 | 2023-01-26 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 36.6667 | 8 | 9505.45 | 2453.9 | 322.87 | 767.16 | 5961.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23158990300 |  | 100459176 |  | 6720208L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309376 | 2621P | CHIPPENDALE | 100 CHIPPENDALE CT A | 067 | LEX | 2023-01-30 | U125208 | U134852 | 2023-01-29 | 2023-01-29 | 2023-01-29 |  | RJCRAWF | 2023-01-29 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 12.4667 | 5 | 969.5 | 828.61 | 56.96 | 56.43 | 27.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959954800 |  | 100358977 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | FIELDS | 301 FIELDS ST | 017 | PAR | 2023-01-30 | U126286 | U134723 | 2021-12-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-01-30 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 9 | 1 | 3424.65 | 557.03 | 0 | 37.92 | 2829.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959954900 |  | 100358976 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | FIELDS | 302 FIELDS ST | 017 | PAR | 2023-01-30 | U126286 | U134723 | 2021-12-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-01-30 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2638.84 | 0 | 0 | 0 | 2638.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959955000 |  | 100358975 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | FIELDS | 304 FIELDS ST | 017 | PAR | 2023-01-30 | U126286 | U134723 | 2021-12-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-01-30 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2934.52 | 0 | 0 | 0 | 2934.52 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22127153700 |  | 100457044 |  | 6712232O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | DAVIS | 104 DAVIS CT | 209 | GEO | 2023-01-30 | U128816 | AOC SYST | 2022-08-26 | 2023-01-30 |  |  | OLIVER MAYNARD | 2023-01-30 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 3.9833 | 1 | 2568.46 | 253.58 | 157.53 | 17.27 | 2140.08 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22127155200 |  | 100456770 |  | 6712232O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | DAVIS | 115 DAVIS CT | 209 | GEO | 2023-01-30 | U128816 | AOC SYST | 2022-08-26 | 2023-02-24 | 2023-12-31 |  | OLIVER MAYNARD | 2023-01-30 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 4.2333 | 1 | 2278.77 | 270.83 | 157.53 | 18.44 | 1831.97 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22141614100 |  | 100325372 |  | 6720208I |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303192 | 2621P | MONTAVESTA | 3017 MONTAVESTA RD | 067 | LEX | 2023-01-30 | U129722 | U125208 | 2022-10-28 | 2023-04-27 | 2024-10-31 |  | M YOUNG | 2023-01-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 3019.71 | 473.09 | 280.05 | 32.22 | 2234.35 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23156623200 |  | 100345280 |  | 6696212H |  |  |  | 565 | EX | SERVICE LINE - REPLACE - RLA | 2621P | KILMER | 161 KILMER ST | 239 | VER | 2023-01-30 | U129731 | U125208 | 2023-01-17 | 2023-01-31 |  |  | F.GOINS | 2023-01-30 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 1 | 3057.14 | 513.08 | 0 | 108.72 | 2435.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23158482600 |  | 100294684 |  | 6716212D | 2286524 |  |  | 565 | EX | RPLC SL/22026167200 | 2600B | JEFFERSON | 514 JEFFERSON ST | 067 | LEX | 2023-01-30 | U461375 | U125763 | 2023-01-25 | 2023-12-29 |  |  | LARRY BROWN | 2023-01-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2246.19 | 0 | 0 | 0 | 2246.19 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23158483700 |  | 100294686 |  | 6716212D | 2286524 |  |  | 565 | EX | RPLC SL/22026167200 | 2600B | JEFFERSON | 518 JEFFERSON ST | 067 | LEX | 2023-01-30 | U461375 | U125763 | 2023-01-25 | 2023-12-29 |  |  | LARRY BROWN | 2023-01-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2876.63 | 0 | 0 | 0 | 2876.63 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23159112500 |  | 100457658 |  | 6712232O |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | DAVIS | 102 DAVIS CT | 209 | GEO | 2023-01-30 | U128816 | U136097 | 2023-01-30 | 2023-01-30 |  |  | OLIVER MAYNARD | 2023-01-30 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 3.7833 | 1 | 2559.33 | 242.72 | 157.53 | 16.52 | 2142.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22026204100 |  |  |  | 7260280N | 2074375 | U122858 |  | 586 | EX | RETIRE BUILDING | 2632M | CARNATION STATION-1458 | CARNATION STATION-1458 | 161 | MAY | 2023-02-03 | U123258 | U122858 | 2022-06-10 | 2023-12-29 | 2023-12-31 | 2023-01-31 | WADE SHIMFESSEL | 2023-01-31 |  |  | F | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00586 | 3200586 |  |  | WP2041 |  |  | 100 | 058632220262041 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22026204400 |  |  |  | 7260280M | 2074375 | U122858 |  | 586 | EX | RETIRE BUILDING | 2632M | REYNOLDS | REYNOLDS DR | 161 | MAY | 2023-02-03 | U123258 | U122858 | 2022-06-13 | 2023-12-29 | 2023-12-31 | 2023-01-31 | WADE SHIMFESSEL | 2023-01-31 |  |  | F | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00586 | 3200586 |  |  | WP2044 |  |  | 100 | 058632220262044 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026247100 |  |  |  | 7352264E | 2394691 | U132280 |  | 557 | EX | EMER - INSTALL 9'-4" CSMP/PMP | 2621P | ELWOOD | ELWOOD | 089 | RUS | 2023-05-16 | U128132 | U132280 | 2023-01-04 | 2023-09-25 |  | 2022-09-26 | MCOLLET | 2023-01-31 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP2471 |  |  | 100 | 055732230262471 | 10.9 | 27 | 5323.15 | 1735.69 | 253.28 | 2711.43 | 0 | 0 | 0 | 622.75 | 9
KY | KY - EAST | 2631 | 23026247200 |  |  |  | 7352264E | 2394691 | U132280 |  | 558 | EX | EMER - RETIRE 9'-4" CSMP | 2621P | ELWOOD | ELWOOD | 089 | RUS | 2023-02-08 | U128132 | U132280 | 2023-01-04 | 2023-09-29 |  | 2022-09-26 | MCOLLET | 2023-01-31 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP2472 |  |  | 100 | 055832230262472 | 5.8 | 0 | 806.29 | 330.75 | 0 | 475.54 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026254000 |  |  |  | 6716212J | 2395179 | U461383 |  | 584 | EX | RETIRE PRESSURE GAUGE | 2621M | VERSAILLES | 1406 VERSAILLES RD | 067 | LEX | 2023-02-07 | U123258 | U461383 | 2023-01-25 | 2023-09-29 | 2023-10-01 | 2023-01-31 | EBLANTON | 2023-01-31 | 2023-01-31 |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00584 | 3200584 |  |  | WP2540 |  |  | 100 | 058432230262540 | 8.65 | 0 | 768.43 | 579.78 | 0 | 188.65 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23153677800 |  | 100303833 |  | 6712208D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311804 | 2621P | HONEYSUCKLE | 900 HONEYSUCKLE RD | 067 | LEX | 2023-01-31 | U930915 | U134852 | 2023-01-06 | 2022-12-21 | 2024-06-30 |  | KKINDER | 2023-01-31 | 2023-01-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 35.9333 | 5 | 3345.12 | 2314.46 | 14.69 | 157.67 | 858.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 14242017600 |  | 100351275 |  | TCO 7350 |  |  |  | 566 | EX | PAPER ABANDON - IDLE/INACTIVE | 2621P | MLT ** STONER EPHESUS | 1740 MLT ** STONER EPHESUS RD | 049 | WIN | 2023-02-03 | JTOY | U125208 | 2014-08-12 | 2014-06-20 |  |  | NRICHIE | 2023-02-01 | 2023-02-01 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.8 | 3 | 1394.78 | 354.69 | 0 | 20.04 | 1020.05 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959965000 |  | 100359008 |  | 6740232I | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | MARSHALL | 406 MARSHALL ST | 017 | PAR | 2023-02-01 | U126286 | U134723 | 2021-12-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-02-01 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 8 | 1 | 5327.08 | 546.27 | 0 | 30.84 | 4749.97 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22122673100 |  | 500732237 |  | 7324132F | 2290467 |  |  | 566 | EX | ABANDON SL - HINDMAN FLOOD | 2621P | OLD GARNER | 425 OLD GARNER RD | 119 | HIN | 2023-02-09 | U130172 | U125208 | 2022-08-09 | 2022-08-08 | 2023-01-26 |  | JAHOWARD | 2023-02-01 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 8 | 1 | 588.43 | 556.99 | 0 | 31.44 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22127162500 |  | 100282175 |  | 6712228C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | WASHINGTON | 325 E WASHINGTON ST | 209 | GEO | 2023-02-01 | U128816 | AOC SYST | 2022-08-26 | 2023-02-24 | 2023-12-31 |  | OLIVER MAYNARD | 2023-02-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 7.05 | 1 | 3727.93 | 541.54 | 700.06 | 30.56 | 2455.77 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22127500200 |  | 100420119 |  | 6712232O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | WEST | 111 WEST ST | 209 | GEO | 2023-02-01 | U128816 | AOC SYST | 2022-08-29 | 2023-02-28 | 2023-12-31 |  | OLIVER MAYNARD | 2023-02-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 4.45 | 1 | 3584.8 | 341.81 | 697.17 | 19.31 | 2526.51 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129063600 |  | 100340956 |  | 7240212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAYSVILLE | 59 S MAYSVILLE ST | 173 | MT | 2023-02-01 | DENNING | U130722 | 2022-09-05 | 2022-12-30 |  |  | DENNING | 2023-02-01 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 19.6 | 3 | 1516.71 | 1435.64 | 0 | 81.07 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22141443900 |  | 100464625 |  | 6720204M |  |  |  | 565 | EX | REPLACE SERVICE LINE - D305585 | 2621P | CROSBY | 3961 CROSBY DR | 067 | LEX | 2023-02-02 | U129722 | U125208 | 2022-10-27 | 2023-04-25 | 2024-10-31 |  | M YOUNG | 2023-02-01 | 2022-12-15 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.1833 | 2 | 3246.3 | 545.88 | 220.16 | 35.11 | 2445.15 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964243200 |  | 100348033 |  | 6748208I | 2075093 |  |  | 565 | EX | REPLACE SL W/20-0269804-00 | 2600B | STERLING | 41 STERLING ST 2F | 049 | WIN | 2023-02-02 | U126602 | U134723 | 2022-01-06 | 2022-12-30 |  |  | DEREK PAYTON | 2023-02-01 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 9279.51 | 0 | 0 | 0 | 9279.51 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964252900 |  | 100348034 |  | 6748208I | 2075093 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | STERLING | 41 STERLING ST 1FL | 049 | WIN | 2023-02-02 | U126602 | U134723 | 2022-01-06 | 2022-12-30 |  |  | DEREK PAYTON | 2023-02-01 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26290043 |  | 1
KY | KY - WEST | 2621 | 23156447900 |  | 100331085 |  | 6720212N |  |  |  | 566 | EX | ABANDON SL-DEMO/CUSTRQD | 2621P | PRESTON | 305 PRESTON AV | 067 | LEX | 2023-02-02 | U930915 | U134784 | 2023-01-16 | 2023-01-30 | 2023-02-15 |  | LSTANFI | 2023-02-01 | 2023-01-30 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.2833 | 4 | 692.62 | 614.85 | 34.39 | 43.38 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164165600 |  | 100310672 |  | 6712208L |  |  |  | 565 | EX | GRADE 1 REPLACE SERV LINE | 2621P | NAKOMI | 626 NAKOMI DR | 067 | LEX | 2023-02-01 | U930915 | U129939 | 2023-02-01 | 2023-02-01 | 2023-02-01 |  | RJCRAWF | 2023-02-01 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.7333 | 3 | 1792 | 1380.59 | 268.54 | 77.97 | 64.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21912265100 |  | 100344632 |  | 6700224K | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | 2ND | 335 2ND ST | 239 | MID | 2023-02-02 | U128816 | AOC SYST | 2021-05-18 | 2021-11-18 | 2022-12-31 |  | OLIVER MAYNARD | 2023-02-02 | 2022-01-03 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 11.0667 | 2 | 4393.44 | 823.61 | 619.72 | 47.35 | 2902.76 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959958000 |  | 100359001 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | MARSHALL | 614 MARSHALL ST | 017 | PAR | 2023-02-22 | U127414 | U134723 | 2021-12-16 | 2023-07-31 |  |  | ED FOX | 2023-02-02 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 3.5167 | 1 | 7607.17 | 240.77 | 0 | 13.57 | 7352.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22102919000 |  | 100291733 |  | 6720216D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D258110 | 2600B | FAULKNER | 764 FAULKNER AV | 067 | LEX | 2023-02-02 | U127206 | U125208 | 2022-05-23 | 2022-11-18 | 2024-05-31 |  | JUSTIN HOBBS | 2023-02-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.5 | 1 | 7230.02 | 663.08 | 332.18 | 37.43 | 6197.33 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22124066400 |  | 100282990 |  | 6712228B | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | CLAYTON | 311 CLAYTON AV DN | 209 | GEO | 2023-02-02 | U129731 | AOC SYST | 2022-08-15 | 2023-02-15 | 2023-12-31 |  | F.GOINS | 2023-02-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 10 | 1 | 2341.68 | 707.64 | 0 | 123.84 | 1510.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22137577300 |  | 100407834 |  | 6716208O |  |  |  | 565 | EX | GR 1 LK | 2621D | LARKIN | 2461 LARKIN RD | 067 | LEX | 2023-02-03 | U930915 | AOC SYST | 2022-10-07 | 2023-02-02 | 2023-02-02 |  | DMARSTO | 2023-02-02 | 2023-02-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.2333 | 3 | 1544.66 | 1094.7 | 240.08 | 172.48 | 37.4 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22142507200 |  | 100250711 |  | 7376184A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE * | 2621P | RIVER FRONT | 1336 RIVER FRONT RD | 159 | LOV | 2023-02-06 | U125208 | U125208 | 2022-11-02 | 2023-12-29 | 2023-12-31 |  | JCKIRK | 2023-02-02 | 2023-02-01 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 13.5667 | 3 | 1012 | 957.93 | 0 | 54.07 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22142508100 |  | 100250709 |  | 7376184A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE + | 2621P | SR292 | SR292 | 159 | LOV | 2023-02-02 | JCKIRK | U125208 | 2022-11-02 | 2023-12-29 | 2023-12-31 |  | JCKIRK | 2023-02-02 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.6167 | 1 | 200.71 | 189.99 | 0 | 10.72 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964237900 |  | 100347876 |  | 6748208I | 2075093 |  |  | 565 | EX | REPLACE SL W/20-0269804-00 | 2600B | MAGNOLIA | 1 MAGNOLIA ST APT A | 049 | WIN | 2023-02-02 | U126602 | U134723 | 2022-01-06 | 2022-12-30 |  |  | DEREK PAYTON | 2023-02-02 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3433.37 | 0 | 0 | 0 | 3433.37 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964250800 |  | 100431581 |  | 6748208I | 2075093 |  |  | 565 | EX | REPLACE SL W/20-0269804-00 | 2600B | MAIN | 506 N MAIN ST | 049 | WIN | 2023-02-02 | U126602 | U134723 | 2022-01-06 | 2022-12-30 |  |  | DEREK PAYTON | 2023-02-02 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 10 | 1 | 5434.17 | 748 | 0 | 42.19 | 4643.98 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026252200 |  |  |  | 6716204B | 2395042 | U461383 |  | 557 | EX | EMER-INSTALL 3' OF 4"PMMP MAIN | 2621P | REYNOLDS | 249 E REYNOLDS RD | 067 | LEX | 2023-03-13 | U128132 | U461383 | 2023-01-19 | 2023-09-28 | 2023-09-30 | 2023-01-19 | RCRAWFORD | 2023-02-02 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2522 |  |  | 100 | 055732230262522 |  | 3 | 5339.51 | 2807.03 | 563.92 | 420.74 | 1126.24 | 0 | 8.89 | 412.69 | 3
KY | KY - WEST | 2621 | 23026252300 |  |  |  | 6716204B | 2395042 | U461383 |  | 558 | EX | EMER-RETIRE 3' OF 4"PAMP MAIN | 2621P | REYNOLDS | 249 REYNOLDS RD | 067 | LEX | 2023-02-02 | U128132 | U461383 | 2023-01-19 | 2023-09-29 | 2023-09-30 | 2023-01-19 | RCRAWFORD | 2023-02-02 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2523 |  |  | 100 | 055832230262523 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23153492500 |  | 100316221 |  | 6716208F |  |  |  | 566 | EX | ABANDON SL - CONV/CUSREQ MNFLD | 2621P | PIN OAK | 105 PIN OAK DR A-1FL | 067 | LEX | 2023-02-02 | U930915 | KWELLS | 2023-01-05 | 2023-01-18 | 2023-02-04 |  | MCRAIG | 2023-02-02 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.9667 | 2 | 726.33 | 270.62 | 162.61 | 293.1 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23153493400 |  | 100316223 |  | 6716208F |  |  |  | 566 | EX | ABANDON SL - CONV/CUSREQ MNFLD | 2621P | PIN OAK | 105 PIN OAK DR B-1FR | 067 | LEX | 2023-02-02 | MCRAIG | KWELLS | 2023-01-05 | 2023-01-19 | 2023-02-04 |  | MCRAIG | 2023-02-02 | 2023-01-09 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.4667 | 5 | 1338.8 | 940.13 | 0 | 398.67 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23158482700 |  | 100294690 |  | 6716212D | 2286524 |  |  | 565 | EX | RPLC SL/22026167200 | 2600B | JEFFERSON | 528 JEFFERSON ST | 067 | LEX | 2023-02-02 | U461375 | U125763 | 2023-01-25 | 2023-12-29 |  |  | LARRY BROWN | 2023-02-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2267.09 | 0 | 0 | 0 | 2267.09 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164481000 |  | 100344631 |  | 6700224K |  |  |  | 566 | EX | ABANDN SL/ | 2600B | 2ND | 337 2ND ST | 239 | MID | 2023-02-02 | U128816 | U125763 | 2023-02-02 | 2023-12-29 |  |  | OLIVER MAYNARD | 2023-02-02 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0043 |  |  | 100 | 056632B26230043 | 0.38333 | 1 | 32.48 | 30.74 | 0 | 1.74 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164552700 |  | 100313100 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | SOUTHBEND | 523 SOUTHBEND DR | 067 | LEX | 2023-02-03 | U128762 | U125763 | 2023-02-02 | 2023-12-29 |  |  | CORY TINCHER | 2023-02-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2769.39 | 0 | 0 | 0 | 2769.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 14200994100 |  | 500827762 | 22 | 6720208A | 9613887 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HIGH | 808 E HIGH ST END | 067 | LEX | 2023-02-03 | RJCRAWF | WCFULKS | 2014-02-24 | 2020-12-31 |  |  | RJCRAWF | 2023-02-03 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.5167 | 3 | 177.13 | 167.66 | 0 | 9.47 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026248900 |  |  |  | 6712208C | 2394889 | U461383 |  | 559 | EX | INSTALL 100' OF 2"PMMP MAIN | 2600B | FALLON | 2093 FALLON RD | 067 | LEX | 2023-03-31 | U124014 | U461383 | 2023-01-12 | 2023-08-28 | 2023-09-01 | 2023-02-02 | ALEX WILLIAMSON/M.JONES | 2023-02-03 | 2023-01-23 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP2489 |  |  | 100 | 055932230262489 | 122.9167 | 1955 | 28889.25 | 9064.78 | 2253.8 | 2277.42 | 10849.14 | 0 | 66.03 | 4378.08 | 115
KY | KY - WEST | 2621 | 23026252000 |  |  |  | 6724208E | 2395041 | U461383 |  | 557 | EX | EMER-INSTALL 3' OF 6"PMMP MAIN | 2621P | PALUMBO | 2575 PALUMBO DR | 067 | LEX | 2023-02-17 | U128132 | U461383 | 2023-01-18 | 2023-09-27 | 2023-09-30 | 2023-01-17 | MCRAIG | 2023-02-03 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2520 |  |  | 100 | 055732230262520 |  | 3 | 13052.34 | 8139.75 | 380.89 | 2262.64 | 1469.35 | 0 | 26.58 | 773.13 | 3
KY | KY - WEST | 2621 | 23026252100 |  |  |  | 6724208E | 2395041 | U461383 |  | 558 | EX | RETIRE 3' OF 6"PMP MAIN | 2621P | PALUMBO | 2575 PALUMBO DR | 067 | LEX | 2023-02-06 | U128132 | U461383 | 2023-01-18 | 2023-09-29 | 2023-09-30 | 2023-01-17 | MCRAIG | 2023-02-03 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2521 |  |  | 100 | 055832230262521 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23026254100 |  |  |  | 7256276B | 2395179 | U461383 |  | 584 | EX | RETIRE PRESSURE GAUGE | 2632M | US 68 | US 68 | 161 | MAY | 2023-02-08 | U123258 | U461383 | 2023-01-25 | 2023-09-29 | 2023-10-01 | 2023-02-03 | JMARTIN | 2023-02-03 | 2023-02-03 |  | F | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00584 | 3200584 |  |  | WP2541 |  |  | 100 | 058432230262541 | 1.05 | 0 | 72.46 | 68.58 | 0 | 3.88 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23157811900 |  | 100272038 | 17 | 6684228K | 1635077 |  |  | 565 | EX | AOC SERVICE REPLACE - UNMTRD | 2621P | 4TH | 229 E 4TH ST | 073 | FRA | 2023-02-03 | DCOLLIN | NARTRIP | 2023-01-20 | 2023-02-20 | 2023-03-20 |  | DCOLLIN | 2023-02-03 | 2023-02-02 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 52.0333 | 5 | 5739.13 | 3448.6 | 82.88 | 1398.6 | 809.05 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23159094300 |  | 100420931 |  | 7348260C |  |  |  | 566 | EX | ABANDON SL - DEMO/FIRE | 2621P | BARKLEY | 144 BARKLEY CT | 089 | RUS | 2023-02-03 | RECUMP | U133234 | 2023-01-30 | 2023-02-13 | 2023-03-01 |  | RECUMP | 2023-02-03 | 2023-01-31 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 20.1667 | 7 | 1757.88 | 1202.88 | 19.89 | 535.11 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 09814394500 |  | 100285194 | 28 | 7236164T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | WAGERSVILLE | 2850 WAGERSVILLE RD | 065 | IRV | 2023-02-08 | U125208 | JMMCDON | 2009-12-10 | 2022-06-30 | 2022-12-31 |  | DENNING | 2023-02-06 | 2023-01-13 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 13.7167 | 5 | 1189.63 | 1004.67 | 0 | 56.87 | 128.09 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959958400 |  | 100358999 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | MARSHALL | 620 MARSHALL ST | 017 | PAR | 2023-02-06 | U126286 | U134723 | 2021-12-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-02-06 | 2023-01-20 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 18 | 2 | 7235.37 | 1178.01 | 0 | 72.25 | 5985.11 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22124641000 |  | 100436585 |  | 6720208P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303213 | 2600B | HIDDEN POINT | 645 HIDDEN POINT DR | 067 | LEX | 2023-02-07 | U128410 | U125208 | 2022-08-17 | 2023-02-16 | 2024-08-31 |  | CDESPAIN | 2023-02-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.6833 | 1 | 2701.46 | 335.41 | 244.51 | 18.93 | 2102.61 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22127161900 |  | 100282216 |  | 6712228B | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | WASHINGTON | 220 E WASHINGTON ST | 209 | GEO | 2023-02-06 | U128816 | AOC SYST | 2022-08-26 | 2023-12-31 | 2023-12-31 |  | OLIVER MAYNARD | 2023-02-06 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 8.9833 | 1 | 3473.22 | 689.82 | 400.62 | 38.95 | 2343.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22140599900 |  | 100325042 |  | 6720204A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMED - D303190 | 2621D | GREENTREE | 3446 GREENTREE RD | 067 | LEX | 2023-02-07 | U129722 | AOC SYST | 2022-10-21 | 2023-04-21 | 2024-10-31 |  | M YOUNG | 2023-02-06 | 2022-12-15 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.083333 | 1 | 2238.05 | 6.51 | 249.74 | 2.29 | 1979.51 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964241800 |  | 100347997 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | MAIN | 517 N MAIN ST | 049 | WIN | 2023-02-08 | U126603 | U134723 | 2022-01-06 | 2023-07-31 |  |  | SHAWN DENNIS | 2023-02-06 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1923.88 | 0 | 0 | 0 | 1923.88 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026252400 |  |  |  | 6752176B |  | U461383 |  | 588 | EX | RETIRE GMB MS#804399 RUN | 2600M | HWY 977 | HWY 977 | 151 | WAC | 2023-02-06 | U126552 | U461383 | 2023-01-19 | 2023-06-01 | 2023-06-01 | 2023-02-06 | JBRADFORD | 2023-02-06 | 2023-01-23 |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00588 | 3200588 |  |  | WP2524 |  |  | 100 | 058832230262524 | 25.7833 | 0 | 21780.96 | 8392.1 | 0 | 3108.86 | 10280 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23158483800 |  | 100294695 |  | 6716212D | 2286524 |  |  | 565 | EX | RPLC SL/22026167200 | 2600B | JEFFERSON | 546 JEFFERSON ST | 067 | LEX | 2023-02-06 | U461375 | U125763 | 2023-01-25 | 2023-12-29 |  |  | LARRY BROWN | 2023-02-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3107.48 | 0 | 0 | 0 | 3107.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164552900 |  | 100313101 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL W/22026184800 | 2600B | SOUTHBEND | 531 SOUTHBEND DR | 067 | LEX | 2023-02-07 | U128762 | U125763 | 2023-02-02 | 2023-12-29 |  |  | CORY TINCHER | 2023-02-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2545.69 | 0 | 0 | 0 | 2545.69 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165041100 |  | 100413755 |  | 6720204F |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HIALEIAH | 1252 HIALEIAH CT | 067 | LEX | 2023-02-06 | DMARSTO | U129939 | 2023-02-06 | 2023-02-06 | 2023-02-06 |  | DMARSTO | 2023-02-06 | 2023-02-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 10.5 | 3 | 1103.41 | 708.51 | 261.41 | 39.99 | 93.5 | 0 | 0 | 0
KY | KY - EAST | 2633 | 11895826500 |  | 100256455 |  | 7352148T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HALE | 151 HALE RD | 071 | HAR | 2023-02-07 | JAHOWARD | U906609 | 2011-03-16 | 2020-12-31 |  |  | JAHOWARD | 2023-02-07 | 2023-02-07 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 13.35 | 2 | 977.36 | 925.13 | 0 | 52.23 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 20026952500 |  |  |  | 7356256P | 2072290 | U938437 |  | 559 | EX | REPLACE VALVE C-16 | 2600B | CHESTNUT | CHESTNUT ST | 019 | ASH | 2023-03-09 | U128132 | U132280 | 2020-05-27 | 2023-12-12 | 2023-12-25 | 2023-02-06 | DAVID SKAGGS | 2023-02-07 | 2023-01-25 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00559 | 3200559 |  |  | WP9525 | AMRCB |  | 100 | 055932200269525 | 115.9333 | 435 | 47582.37 | 8182.95 | 4964.23 | 1736.58 | 26964.27 | 0 | 185.6 | 5548.74 | 29
KY | KY - EAST | 2631 | 20026952600 |  |  |  | 7356256P | 2072290 | U938437 |  | 560 | EX | RETIRE VALVE C-16 | 2600B | CHESTNUT | CHESTNUT ST | 019 | ASH | 2023-02-13 | U128132 | U132280 | 2020-05-27 | 2023-12-21 | 2023-12-25 | 2023-02-06 | DAVID SKAGGS | 2023-02-07 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00560 | 3200560 |  |  | WP9526 | AMRCB |  | 100 | 056032200269526 | 6.05 | 0 | 5789.59 | 5360 | 0 | 429.59 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959958500 |  | 100410194 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | MARSHALL | 621 MARSHALL ST | 017 | PAR | 2023-02-07 | U126286 | U134723 | 2021-12-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-02-07 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 9 | 1 | 4600.04 | 614.57 | 0 | 34.69 | 3950.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22102175400 |  | 500007473 |  | 6720200B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311360 | 2600B | HEMPSTEAD | 4833 HEMPSTEAD DR | 067 | LEX | 2023-02-07 | U461309 | U125208 | 2022-05-19 | 2022-11-18 | 2024-05-31 |  | R.HUMPHREYS | 2023-02-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 4794.42 | 540.34 | 211.75 | 97.61 | 3944.72 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22127156500 |  | 100282221 |  | 6712228B | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | WASHINGTON | 229 E WASHINGTON ST | 209 | GEO | 2023-02-07 | U128816 | AOC SYST | 2022-08-26 | 2023-12-31 | 2023-12-31 |  | OLIVER MAYNARD | 2023-02-07 | 2023-02-06 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 10.0167 | 2 | 6578.63 | 769.71 | 403.5 | 43.42 | 5362 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129002700 |  | 100284678 |  | 6764172B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | WISEMANTOWN | 1910 WISEMANTOWN RD | 065 | IRV | 2023-02-07 | DENNING | U130722 | 2022-09-05 | 2022-12-30 |  |  | DENNING | 2023-02-07 | 2023-02-06 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 26.65 | 7 | 2551.04 | 1998.14 | 0 | 112.81 | 440.09 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129933100 |  | 100351666 |  | 6744208P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333626 | 2621P | LEXINGTON | 302 W LEXINGTON AV | 049 | WIN | 2023-02-08 | JTOY | U125208 | 2022-09-08 | 2023-03-07 | 2024-09-30 |  | NRICHIE | 2023-02-07 | 2023-02-06 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 20.1833 | 5 | 2589.31 | 1485.5 | 263.8 | 816.91 | 23.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22150010200 |  | 100315505 |  | 6716208B |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2600B | FLORAL | 219 FLORAL PR | 067 | LEX | 2023-02-08 | U128410 | U124960 | 2022-12-21 | 2023-02-10 | 2024-08-31 |  | CDESPAIN | 2023-02-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26210022 | 10 | 1 | 4819.19 | 713.69 | 449.86 | 40.27 | 3615.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22150010500 |  | 100317701 |  | 6716204F |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2600B | TULANE | 337 TULANE DR | 067 | LEX | 2023-02-07 | U461322 | U124960 | 2022-12-21 | 2023-02-10 | 2024-08-31 |  | STEVE CANOY | 2023-02-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9 | 1 | 5662.2 | 673 | 0 | 449.84 | 4539.36 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964247800 |  | 100348044 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | MAIN | 415 N MAIN ST | 049 | WIN | 2023-02-07 | U126602 | U134723 | 2022-01-06 | 2023-07-31 |  |  | DEREK PAYTON | 2023-02-07 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 6133 | 0 | 506.57 | 0 | 5626.43 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964250900 |  | 501184418 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | MAIN | 525 N MAIN ST B | 049 | WIN | 2023-03-08 | U126602 | U134723 | 2022-01-06 | 2023-07-31 |  |  | DEREK PAYTON | 2023-02-07 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4265.32 | 0 | 0 | 0 | 4265.32 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026250900 |  |  |  | 6744208C | 2394960 | U461383 |  | 587 | EX | INSTALL EC 350 | 2600M | ENTERPRISE | 1330 ENTERPRISE DR | 049 | WIN | 2023-02-15 | U123258 | U461383 | 2023-01-16 | 2023-09-29 | 2023-10-01 | 2023-02-07 | JBRADFORD | 2023-02-07 | 2023-02-07 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00587 | 3200587 |  |  | WP2509 |  |  | 100 | 058732230262509 | 6.3167 | 2 | 755.31 | 409.33 | 0 | 220.8 | 0 | 0 | 1.67 | 123.51
KY | KY - CENTRAL | 2629 | 23026251000 |  |  |  | 6744208C | 2394960 | U461383 |  | 588 | EX | RETIRE PAPER BILLING CHART | 2600M | ENTERPRISE | 1330 ENTERPRISE DR | 049 | WIN | 2023-02-15 | U123258 | U461383 | 2023-01-16 | 2023-09-29 | 2023-10-01 | 2023-02-07 | JBRADFORD | 2023-02-07 | 2023-02-03 |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00588 | 3200588 |  |  | WP2510 |  |  | 100 | 058832230262510 | 8.7 | 0 | 803.89 | 567.34 | 0 | 236.55 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23158484600 |  | 100294354 |  | 6716212D | 2286524 |  |  | 565 | EX | RPLC SL/22026167200 | 2600B | JEFFERSON | 555 JEFFERSON ST | 067 | LEX | 2023-02-07 | U461375 | U125763 | 2023-01-25 | 2023-12-29 |  |  | LARRY BROWN | 2023-02-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2779.96 | 0 | 0 | 0 | 2779.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164548700 |  | 100313105 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | CLAYS MILL | 1848 CLAYS MILL RD | 067 | LEX | 2023-02-07 | U124003 | U125763 | 2023-02-02 | 2023-12-29 |  |  | BPULLIAM/FISHEL | 2023-02-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3392.77 | 0 | 0 | 0 | 3392.77 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165042600 |  | 100304943 |  | 6712212P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D310274 | 2621P | TARLETON | 1731 TARLETON CT | 067 | LEX | 2023-02-08 | U125208 | U125208 | 2023-02-06 | 2023-02-09 | 2023-02-27 |  | WISHII | 2023-02-07 | 2023-02-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.05 | 3 | 1886.35 | 968.61 | 132.3 | 711.74 | 73.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165271200 |  | 100324916 |  | 6720204E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | DANADA | 3505 DANADA DR | 067 | LEX | 2023-02-07 | DMARSTO | U129939 | 2023-02-07 | 2023-02-07 |  |  | DMARSTO | 2023-02-07 | 2023-02-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.2167 | 3 | 1262.86 | 705.34 | 447.34 | 39.78 | 70.4 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23165331900 |  | 100286411 |  | 6768172B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D247717 | 2621P | 3RD | 401 3RD ST | 065 | RAV | 2023-02-08 | U125208 | U129939 | 2023-02-07 | 2023-02-24 | 2024-08-31 |  | DENNING | 2023-02-07 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 12.6 | 10 | 1151.65 | 180.89 | 280.75 | 10.21 | 679.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 20026950500 |  |  |  | 7256272E | 2072091 | U122858 |  | 575 | EX | ACQUIRE LAND FOR STATION | 2600E | US68 | US68 | 161 | MAY | 2023-02-10 | U128132 | U122858 | 2020-05-15 | 2023-12-28 | 2023-12-31 | 2023-02-08 | CDAVIS | 2023-02-08 |  |  | F | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00575 | 3200575 |  |  | WP9505 |  |  | 100 | 057532200269505 |  | 1 | 13667.26 | 0 | 0 | 0 | 13667.26 | 0 | 0 | 0
KY | KY - WEST | 2623 | 20822559100 |  | 100345915 |  | 6704208A |  |  |  | 565 | EX | REPLACE SERV LINE | 2621P | BAYBERRY | 113 BAYBERRY RD | 239 | VER | 2023-02-08 | U128816 | U129939 | 2020-06-26 | 2020-06-26 |  |  | OLIVER MAYNARD | 2023-02-08 | 2020-06-26 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.4 | 2 | 3062.77 | 562.5 | 319.47 | 43.2 | 2137.6 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883171800 |  | 100253070 |  | 7356256J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | HAMPTON | 3232 HAMPTON ST | 019 | ASH | 2023-02-08 | RECUMP | U120245 | 2021-01-30 | 2022-12-07 | 2022-12-31 |  | RECUMP | 2023-02-08 | 2022-12-13 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 9.8167 | 3 | 802.59 | 603.42 | 0 | 199.17 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959955100 |  | 100358974 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | FIELDS | 309 FIELDS ST | 017 | PAR | 2023-02-08 | U126286 | U134723 | 2021-12-16 | 2023-07-31 |  |  | TYLER ALLISON | 2023-02-08 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 9 | 1 | 4100.59 | 614.57 | 0 | 34.69 | 3451.33 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959955200 |  | 500663295 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | FIELDS | 312 FIELDS ST | 017 | PAR | 2023-02-08 | U126286 | U134723 | 2021-12-16 | 2023-07-31 |  |  | TYLER ALLISON | 2023-02-08 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2957.88 | 0 | 0 | 0 | 2957.88 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22100639500 |  | 100246457 |  | 7356256I |  |  |  | 565 | EX | REPLACE SERVICE LINE - D258107 | 2600B | AUBURN | 2545 AUBURN AV | 019 | ASH | 2023-02-08 | DESKAGG | U125208 | 2022-05-13 | 2022-11-11 | 2024-05-31 |  | DESKAGG | 2023-02-08 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 7.3667 | 1 | 4647.28 | 524.96 | 385.46 | 91.56 | 3645.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22123463100 |  | 100317329 |  | 6716204J | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMED - D309196 | 2600B | WINNIPEG | 4012 WINNIPEG WY | 067 | LEX | 2023-02-08 | U461309 | AOC SYST | 2022-08-11 | 2023-02-10 | 2024-08-31 |  | R.HUMPHREYS | 2023-02-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 4634.94 | 604.13 | 339.58 | 101.22 | 3590.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22126077200 |  | 100443353 |  | 6716204C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D246262 | 2600B | WARWICK | 3441 WARWICK CT 1FR | 067 | LEX | 2023-02-08 | U461322 | U125208 | 2022-08-23 | 2023-02-17 | 2024-08-31 |  | STEVE CANOY | 2023-02-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.25 | 1 | 6866.8 | 778.41 | 0 | 513.09 | 5575.3 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129028900 |  | 100255978 |  | 7356256E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HAMPTON | 2804 HAMPTON ST | 019 | ASH | 2023-02-10 | U125208 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RECUMP | 2023-02-08 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 7.6333 | 2 | 624.48 | 430.1 | 19.89 | 174.49 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22146529100 |  | 100464163 |  | 6716204L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311122 | 2621P | TATES CREEK | 4030 TATES CREEK RD 1158 | 067 | LEX | 2023-02-09 | U129722 | U125208 | 2022-11-29 | 2023-05-26 | 2024-11-30 |  | M YOUNG | 2023-02-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.85 | 2 | 3633.78 | 987.4 | 1025.89 | 55.73 | 1564.76 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964242000 |  | 100347992 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | MAIN | 613 N MAIN ST | 049 | WIN | 2023-02-09 | U126603 | U134723 | 2022-01-06 | 2023-07-31 |  |  | SHAWN DENNIS | 2023-02-08 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3109.68 | 0 | 0 | 0 | 3109.68 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964242100 |  | 100347989 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | MAIN | 625 N MAIN ST | 049 | WIN | 2023-02-09 | U126603 | U134723 | 2022-01-06 | 2023-07-31 |  |  | SHAWN DENNIS | 2023-02-08 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3188.55 | 0 | 0 | 0 | 3188.55 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964242200 |  | 100347987 |  | 6748208E | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | MAIN | 633 N MAIN ST | 049 | WIN | 2023-02-09 | U126603 | U134723 | 2022-01-06 | 2023-07-31 |  |  | SHAWN DENNIS | 2023-02-08 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3698.28 | 0 | 0 | 0 | 3698.28 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026254300 |  | 501342133 |  | 6688232N | 2395066 | U126783 |  | 555 | EX | TAP W/MAIN 23-0262543-00 | 2600B | DISCHER | 1220 DISCHER DR | 073 | FRA | 2023-03-20 | U124014 | U126783 | 2023-01-26 | 2023-03-22 | 2023-03-24 | 2023-02-08 | F.GOINS | 2023-02-08 | 2023-02-06 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2543 | NBTWM |  | 100 | 055532230262543 | 20.15 | 27 | 4459.75 | 1425.58 | 689.96 | 148.83 | 1456.39 | 0 | 9.86 | 729.13 | 9
KY | KY - WEST | 2623 | 23156623800 |  | 100347213 |  | 6696212F |  |  |  | 565 | EX | SERVICE LINE - REPLACE - RLA | 2621P | OAK | 503 OAK ST | 239 | VER | 2023-02-08 | U128816 | U125208 | 2023-01-17 | 2023-01-31 |  |  | OLIVER MAYNARD | 2023-02-08 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.7333 | 1 | 3414.74 | 254.51 | 462.94 | 14.89 | 2682.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23158484500 |  | 100294697 |  | 6716212D | 2286524 |  |  | 565 | EX | RPLC SL/22026167200 | 2600B | JEFFERSON | 554 JEFFERSON ST | 067 | LEX | 2023-02-08 | U461375 | U125763 | 2023-01-25 | 2023-12-29 |  |  | LARRY BROWN | 2023-02-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2270.4 | 16.02 | 0 | 7.09 | 2247.29 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164552200 |  | 100313096 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | SOUTHBEND | 507 SOUTHBEND DR | 067 | LEX | 2023-02-09 | U128762 | U125763 | 2023-02-02 | 2023-12-29 |  |  | CORY TINCHER | 2023-02-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3477.81 | 0 | 0 | 0 | 3477.81 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164754000 |  | 100281521 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | FORDLAND | 114 FORDLAND DR | 209 | GEO | 2023-02-08 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-02-08 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.1167 | 1 | 2266.15 | 210.2 | 0 | 37.94 | 2018.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165059800 |  | 100330878 |  | 6720212N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311284 | 2621P | BASSETT | 264 BASSETT AV | 067 | LEX | 2023-02-09 | UIPBOT06 | U125208 | 2023-02-06 | 2023-02-09 | 2023-02-27 |  | JOCHOA | 2023-02-08 | 2023-02-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.3667 | 3 | 1598.13 | 1269.66 | 201.81 | 71.66 | 55 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165286800 |  | 100336937 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | M L KING | 460 M L KING BV | 067 | LEX | 2023-02-08 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-02-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 8495.54 | 0 | 0 | 0 | 8495.54 | 0 | 0 | 0
KY | KY - EAST | 2633 | 06645144600 |  | 100259386 |  | 7344148I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PERRY | 7162 PERRY ST | 071 | DRI | 2023-02-09 | JCKIRK | DYOUNG | 2006-04-19 | 2022-07-01 | 2023-12-31 |  | JCKIRK | 2023-02-09 | 2022-11-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 19.15 | 4 | 4237.01 | 1322.33 | 0 | 74.66 | 2840.02 | 0 | 0 | 0
KY | KY - WEST | 2623 | 07689167700 |  | 500021276 |  | V-921/37 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KUHLMAN | 104 KUHLMAN AV | 239 | VER | 2023-02-10 | U125208 | U903504 | 2007-06-01 | 2020-12-31 |  |  | DCOLLIN | 2023-02-09 | 2023-01-30 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 9.9167 | 5 | 1153.04 | 663.91 | 0 | 489.13 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 11920316000 |  | 100259385 |  | 7344148I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | NEED ADDR > 811 | NEED ADDR > 811 | 071 | DRI | 2023-02-09 | BPREECE | U124449 | 2011-08-16 | 2023-02-09 | 2023-12-31 |  | BPREECE | 2023-02-09 | 2022-11-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.6333 | 2 | 173.7 | 164.43 | 0 | 9.27 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 14196113000 |  | 100264634 |  | 7348168I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NOSBEN FORK | 204 NOSBEN FORK RD | 195 | S W | 2023-02-09 | U125208 | U125208 | 2014-01-28 | 2020-12-31 | 2022-12-31 |  | JCKIRK | 2023-02-09 | 2023-02-08 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.1333 | 2 | 390.78 | 369.9 | 0 | 20.88 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 14258056800 |  | 100263718 |  | 7352260P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | HILLCREST | 134 HILLCREST CT | 019 | ASH | 2023-02-17 | U125208 | U125201 | 2014-10-16 | 2022-07-01 | 2022-12-31 |  | RECUMP | 2023-02-09 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.7167 | 2 | 456.69 | 317.11 | 19.89 | 119.69 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 20785318800 |  | 100281544 |  | 6712232N |  |  |  | 565 | EX | REPLACE SL W/LCV | 2621P | CHESTNUT | 608 CHESTNUT ST | 209 | GEO | 2023-02-09 | U128816 | U125208 | 2020-02-24 | 2020-03-11 |  |  | OLIVER MAYNARD | 2023-02-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.25 | 3 | 3587.23 | 380.43 | 587.35 | 119.04 | 2500.41 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883249400 |  | 100462541 |  | 6764176C |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY *OFL | 2621P | WHITE OAK | 760 WHITE OAK RD | 065 | IRV | 2023-02-13 | U125208 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | DENNING | 2023-02-09 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 16.35 | 3 | 1928.44 | 1200.75 | 19.89 | 67.8 | 640 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959959200 |  | 100461800 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | STERNS | 304 STERNS ST | 017 | PAR | 2023-02-09 | U126286 | U134723 | 2021-12-16 | 2023-07-31 |  |  | TYLER ALLISON | 2023-02-09 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2886.64 | 0 | 0 | 0 | 2886.64 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959959300 |  | 100358983 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | STERNS | 305 STERNS ST | 017 | PAR | 2023-02-09 | U126286 | U134723 | 2021-12-16 | 2023-07-31 |  |  | TYLER ALLISON | 2023-02-09 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 8 | 1 | 3466.49 | 546.27 | 0 | 30.84 | 2889.38 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22026216300 |  |  |  | 7356248P | 2070383 | U461383 |  | 587 | EX | INSTALL VRG CONTROLLER | 2631M | US23--ASHLAND OIL | US23--ASHLAND OIL | 019 | CAT | 2023-02-24 | U123258 | U461383 | 2022-08-02 | 2023-12-01 | 2023-12-01 | 2023-02-09 | SGIORDANO | 2023-02-09 | 2022-09-13 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00587 | 3200587 |  |  | WP2163 |  |  | 100 | 058732220262163 | 172.0167 | 92 | 28545.09 | 11886.04 | 6016.64 | 3097.08 | 3262.51 | 0 | 199.12 | 4083.7
KY | KY - EAST | 2631 | 22026216400 |  |  |  | 7356248P | 2070383 | U461383 |  | 588 | EX | RETIRE CONTROLLERS | 2631M | US23--ASHLAND OIL | US23--ASHLAND OIL | 019 | CAT | 2023-02-24 | U123258 | U461383 | 2022-08-02 | 2023-12-01 | 2023-12-01 | 2023-02-09 | SGIORDANO | 2023-02-09 | 2023-01-31 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00588 | 3200588 |  |  | WP2164 |  |  | 100 | 058832220262164 | 8.45 | 0 | 572.67 | 540.65 | 0 | 32.02 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22125685800 |  | 100326456 |  | 6720208A |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303221 | 2600B | COCHRAN | 107 COCHRAN RD | 067 | LEX | 2023-02-09 | U461322 | U125208 | 2022-08-22 | 2023-02-17 | 2024-08-31 |  | STEVE CANOY | 2023-02-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.8833 | 2 | 7647.57 | 1378.11 | 0 | 637.8 | 5631.66 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22127158500 |  | 100281992 |  | 6712232O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | LYNN | 104 E LYNN ST | 209 | GEO | 2023-02-09 | U128816 | AOC SYST | 2022-08-26 | 2023-02-09 | 2023-12-31 |  | OLIVER MAYNARD | 2023-02-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 7.3833 | 1 | 3804.38 | 566.95 | 700.06 | 32 | 2505.37 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22136876200 |  | 100259905 |  | 7356256A |  |  |  | 565 | EX | REPLACE SERVICE LINE - D258087 | 2600B | CENTRAL | 1416 CENTRAL AV | 019 | ASH | 2023-02-09 | DESKAGG | U125208 | 2022-10-05 | 2023-04-05 | 2024-10-31 |  | DESKAGG | 2023-02-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 9 | 1 | 4899.83 | 640.25 | 375.28 | 111.66 | 3772.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22150017600 |  | 100318678 |  | 6716204F |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2600B | LOCH LOMOND | 203 LOCH LOMOND DR | 067 | LEX | 2023-02-10 | U128410 | U124960 | 2022-12-21 | 2023-02-17 | 2024-08-31 |  | CDESPAIN | 2023-02-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.6 | 1 | 3779.7 | 542.4 | 283.93 | 30.62 | 2922.75 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964235400 |  | 100347933 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | LINDEN | 9 LINDEN AV | 049 | WIN | 2023-02-09 | U126602 | U134723 | 2022-01-06 | 2023-07-31 |  |  | DEREK PAYTON | 2023-02-09 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3550.1 | 0 | 0 | 0 | 3550.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964237800 |  | 100347884 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | LINDEN | 2 LINDEN LN | 049 | WIN | 2023-02-24 | U126602 | U134723 | 2022-01-06 | 2023-07-31 |  |  | DEREK PAYTON | 2023-02-09 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3259.13 | 0 | 0 | 0 | 3259.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026249000 |  |  |  | 6712208C | 2394889 | U461383 |  | 560 | EX | RETIRE 86' OF 2"CSMP MAIN | 2600B | FALLON | 2093 FALLON RD | 067 | LEX | 2023-02-16 | U124014 | U461383 | 2023-01-12 | 2023-04-30 | 2023-12-20 | 2023-02-02 | ALEX WILLIAMSON | 2023-02-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00560 | 3200560 |  |  | WP2490 |  |  | 100 | 056032230262490 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23155012000 |  | 100316521 |  | 6716208G |  |  |  | 565 | EX | REPLACE SL - KKINDER 01/17/23 | 2621P | NICHOLASVILLE | 1835 NICHOLASVILLE RD | 067 | LEX | 2023-02-10 | U125208 | U125208 | 2023-01-11 | 2023-01-17 |  |  | TROE | 2023-02-09 | 2023-01-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.7333 | 5 | 2421.96 | 1775.17 | 0 | 103.61 | 543.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23158482800 |  | 100294692 |  | 6716212D | 2286524 |  |  | 565 | EX | RPLC SL/22026167200 | 2600B | JEFFERSON | 536 JEFFERSON ST | 067 | LEX | 2023-02-09 | U461375 | U125763 | 2023-01-25 | 2023-12-29 |  |  | LARRY BROWN | 2023-02-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2261.59 | 0 | 0 | 0 | 2261.59 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164554000 |  | 100313099 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | SOUTHBEND | 519 SOUTHBEND DR | 067 | LEX | 2023-02-09 | U124003 | U125763 | 2023-02-02 | 2023-12-29 |  |  | BPULLIAM/FISHEL | 2023-02-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3609.06 | 0 | 0 | 0 | 3609.06 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165286300 |  | 100336915 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | M L KING | 447 M L KING BV 1F | 067 | LEX | 2023-02-09 | U127206 | U125763 | 2023-02-07 | 2023-12-29 |  |  | JUSTIN HOBBS | 2023-02-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2755.25 | 0 | 0 | 0 | 2755.25 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23165563500 |  | 100281975 |  | 6712232O |  |  |  | 565 | EX | REPLACE SERVICE LINE - * NO DP | 2621P | CHAMBERS | 312 CHAMBERS AV | 209 | GEO | 2023-02-10 | U125208 | U129939 | 2023-02-08 | 2023-09-27 | 2023-09-27 |  | DCOLLIN | 2023-02-09 | 2023-02-08 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26230031 | 27.6167 | 5 | 3884.79 | 2315.09 | 351.19 | 1173.41 | 45.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23165907200 |  | 500011125 |  | 6680224G |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2600B | HIGHLANDS | 1512 HIGHLANDS DR | 073 | FRA | 2023-02-09 | U129731 | U125768 | 2023-02-09 | 2049-12-31 |  |  | F.GOINS | 2023-02-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 8 | 1 | 2594.91 | 566.09 | 0 | 31.95 | 1996.87 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165926500 |  | 100329131 |  | 6720208P | 1635077 |  |  | 566 | EX | RETIRE SERVICE LINE - LEAKAGE | 2621P | PLAINVIEW | 541 PLAINVIEW RD | 067 | LEX | 2023-02-10 | U930915 | U129939 | 2023-02-09 | 2023-02-18 | 2023-02-18 |  | DMARSTO | 2023-02-09 | 2023-02-09 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.15 | 5 | 1047.4 | 889.78 | 104.72 | 52.9 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959959100 |  | 100358982 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | STERNS | 301 STERNS ST | 017 | PAR | 2023-02-10 | U126285 | U134723 | 2021-12-16 | 2023-07-31 |  |  | DDAVIS | 2023-02-10 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 5014.44 | 0 | 353.65 | 0 | 4660.79 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959964000 |  | 100358997 |  | 6736232L | 2292664 |  |  | 566 | EX | ABANDN SL/22026230300 | 2600B | STEWART | 654 STEWART ST | 017 | PAR | 2023-02-16 | U126285 | U134723 | 2021-12-16 | 2023-07-31 |  |  | DDAVIS | 2023-02-10 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 2049.34 | 0 | 0 | 0 | 2049.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026223900 |  |  |  | 6720200E | 2183057 | U122858 |  | 561 | EX | INSTALL 1067'-4" PMMP | 2600E | BRANNON | BRANNON RD | 113 | NIC | 2023-02-13 | U124014 | U122858 | 2022-09-17 | 2023-03-17 | 2023-03-30 | 2023-02-08 | JDUNN | 2023-02-10 | 2023-01-17 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP2239 |  |  | 100 | 056132220262239 | 217.05 | 27375 | 149979.89 | 15002.24 | 8011.53 | 2993.68 | 103447.91 | 0 | 491.7 | 20032.83 | 1095
KY | KY - WEST | 2621 | 22026224000 |  |  |  | 6720200E | 2183057 | U122858 |  | 562 | EX | RETIRE 1150'-4" PMMP | 2600E | BRANNON | BRANNON RD | 113 | NIC | 2023-02-13 | U124014 | U122858 | 2022-09-17 | 2023-03-30 | 2023-03-30 | 2023-02-08 | JDUNN | 2023-02-10 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP2240 |  |  | 100 | 056232220262240 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22101266500 |  | 100263304 |  | 7352256F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D244430 | 2600B | WOODMONT | 328 W WOODMONT DR | 019 | ASH | 2023-02-10 | DESKAGG | U125208 | 2022-05-17 | 2022-11-16 | 2024-05-31 |  | DESKAGG | 2023-02-10 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 8 | 1 | 5280.38 | 1509.17 | 257.8 | 170.16 | 3343.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22113087700 |  | 100312755 |  | 6716208E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMED D311907 | 2600B | SHERIDAN | 494 SHERIDAN DR | 067 | LEX | 2023-02-13 | U461309 | AOC SYST | 2022-06-29 | 2022-12-29 | 2024-06-30 |  | R.HUMPHREYS | 2023-02-10 | 2022-07-28 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.5667 | 2 | 5279.2 | 307.42 | 511.59 | 50.9 | 4409.29 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22127159400 |  | 100282179 |  | 6712228C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | WASHINGTON | 339 E WASHINGTON ST | 209 | GEO | 2023-02-10 | U129731 | AOC SYST | 2022-08-26 | 2023-02-06 | 2023-12-31 |  | F.GOINS | 2023-02-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 9.5 | 1 | 4334.88 | 672.24 | 0 | 117.64 | 3545 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129373800 |  | 100290954 |  | 6716212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D305570 | 2600B | UPPER | 755 N UPPER ST | 067 | LEX | 2023-02-10 | U461322 | U125208 | 2022-09-07 | 2023-03-06 | 2024-09-30 |  | STEVE CANOY | 2023-02-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9 | 1 | 5362.3 | 672.97 | 0 | 37.98 | 4651.35 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964235700 |  | 100347931 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | LINDEN | 13 LINDEN AV | 049 | WIN | 2023-02-10 | U126603 | U134723 | 2022-01-06 | 2023-07-31 |  |  | SHAWN DENNIS | 2023-02-10 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3602.16 | 0 | 0 | 0 | 3602.16 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964250300 |  | 100451079 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | LINDEN | 12 LINDEN AV | 049 | WIN | 2023-02-10 | U126603 | U134723 | 2022-01-06 | 2023-07-31 |  |  | SHAWN DENNIS | 2023-02-10 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3968.91 | 0 | 0 | 0 | 3968.91 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026254700 |  |  |  | 6720212D | 2395179 | U461383 |  | 584 | EX | RETIRE PAPER GAUGE | 2621M | ANNISTON | 400 ANNISTON DR | 067 | LEX | 2023-02-10 | U123258 | U461383 | 2023-01-27 | 2023-12-01 | 2023-12-01 | 2023-02-01 | SMCHOLAN | 2023-02-10 | 2023-02-01 |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00584 | 3200584 |  |  | WP2547 |  |  | 100 | 058432230262547 | 1.9833 | 0 | 247.65 | 146.49 | 0 | 101.16 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23157268600 |  | 100312719 |  | 6716208E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | SHERIDAN | 495 SHERIDAN DR | 067 | LEX | 2023-02-13 | U461309 | U137248 | 2023-01-18 | 2023-01-18 |  |  | R.HUMPHREYS | 2023-02-10 | 2023-02-10 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4 | 1 | 5077.58 | 270.13 | 301.77 | 48.8 | 4456.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23158482900 |  | 100294706 |  | 6716212D | 2286524 |  |  | 565 | EX | RPLC SL/22026167200 | 2600B | JEFFERSON | 537 JEFFERSON ST | 067 | LEX | 2023-02-10 | U461375 | U125763 | 2023-01-25 | 2023-12-29 |  |  | LARRY BROWN | 2023-02-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2375.47 | 0 | 0 | 0 | 2375.47 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23164791400 |  | 100250359 |  | 7340268N |  |  |  | 565 | EX | SERVICE LINE - REPLACE W/OS | 2621P | STATE RT 1 | 1069 STATE RT 1 | 089 | GRE | 2023-02-10 | BMEEK | U125208 | 2023-02-03 | 2023-02-08 | 2023-02-24 |  | BMEEK | 2023-02-10 | 2023-02-09 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 21.75 | 4 | 1830.01 | 1212.67 | 243.02 | 351.22 | 23.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23165026400 |  | 100265674 |  | 7348252C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D259857 | 2621P | THURBURY | 6517 THURBURY RD | 019 | ASH | 2023-02-10 | MCOLLET | U125208 | 2023-02-06 | 2023-02-06 | 2023-02-24 |  | MCOLLET | 2023-02-10 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 16 | 2 | 3371.07 | 1181.24 | 205.97 | 1929.96 | 53.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165285600 |  | 100336919 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | M L KING | 435 M L KING BV 1F | 067 | LEX | 2023-02-10 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-02-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2295.84 | 0 | 0 | 0 | 2295.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165286900 |  | 100336911 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | M L KING | 469 M L KING BV | 067 | LEX | 2023-02-10 | U126532 | U125763 | 2023-02-07 | 2023-02-10 |  |  | LESLIE SHARON | 2023-02-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2644.45 | 0 | 0 | 0 | 2644.45 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19735414800 |  | 100459425 |  | 6700224P |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | RICHARDSON | 114 RICHARDSON ST | 239 | MID | 2023-02-13 | U129731 | U125208 | 2019-08-22 | 2049-12-31 |  |  | F.GOINS | 2023-02-13 | 2019-11-01 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 14.5667 | 5 | 4514.68 | 959.37 | 0 | 630.43 | 2924.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19751370700 |  | 100272101 |  | 6684228O |  |  |  | 565 | EX | SERVICE LNE - REPLACE | 2621P | MURRAY | 416 MURRAY ST | 073 | FRA | 2023-02-13 | U128816 | U125208 | 2019-10-16 | 2020-01-22 |  |  | OLIVER MAYNARD | 2023-02-13 | 2020-01-27 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 12.1 | 3 | 7179.99 | 904.52 | 668.81 | 256.92 | 5349.74 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959959000 |  | 100358981 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | STERNS | 209 STERNS ST | 017 | PAR | 2023-02-13 | U126286 | U134723 | 2021-12-16 | 2023-07-31 |  |  | TYLER ALLISON | 2023-02-13 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 9 | 1 | 6293.13 | 614.57 | 0 | 34.69 | 5643.87 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026167200 |  |  |  | 6716212D | 2286524 | U132703 |  | 557 | EX | INSTALL 720'- 4" PMMP | 2600B | JEFFERSON | JEFFERSON ST | 067 | LEX | 2023-04-04 | U124014 | U132703 | 2022-02-14 | 2023-11-14 | 2023-12-31 | 2023-01-23 | LARRY BROWN | 2023-02-13 | 2023-01-03 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP1672 | AMRCB |  | 100 | 055732220261672 | 277.4833 | 22620 | 293269.78 | 18788.61 | 39375.84 | 16633.59 | 182129.57 | 0 | 243.64 | 36098.53 | 754
KY | KY - WEST | 2621 | 22026167300 |  |  |  | 6716212D | 2286524 | U132703 |  | 558 | EX | RETIRE 720'-4" BS-LP | 2600B | JEFFERSON | JEFFERSON ST | 067 | LEX | 2023-02-22 | U124014 | U132703 | 2022-02-14 | 2023-12-29 | 2023-12-31 | 2023-02-13 | LARRY BROWN | 2023-02-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP1673 | AMRCB |  | 100 | 055832220261673 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22113733600 |  | 100313022 |  | 6716208E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311904 | 2600B | MITCHELL | 572 MITCHELL AV | 067 | LEX | 2023-02-13 | U461309 | U125208 | 2022-07-01 | 2022-12-28 | 2024-06-30 |  | R.HUMPHREYS | 2023-02-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9 | 1 | 6987.83 | 607.88 | 149.6 | 109.8 | 6120.55 | 0 | 0 | 0
KY | KY - EAST | 2682 | 22129033500 |  | 100463384 |  | MLT |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2633S | BOLEN BRANCH | 308 BOLEN BRANCH RD | 071 | GAR | 2023-02-13 | U130172 | U130722 | 2022-09-05 | 2023-02-13 |  |  | JOHN HOWARD | 2023-02-13 |  |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 8.45 | 1 | 1004.64 | 586.24 | 0 | 418.4 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22130952600 |  | 100331153 |  | 6720212N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311153 | 2621P | MONROE | 1311 MONROE AV | 067 | LEX | 2023-02-17 | U129722 | U125208 | 2022-09-13 | 2023-03-10 | 2024-09-30 |  | M YOUNG | 2023-02-13 | 2022-12-15 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.66667 | 1 | 3504 | 54.5 | 341.81 | 19.15 | 3088.54 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964235800 |  | 100347887 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | LINDEN | 14 LINDEN AV | 049 | WIN | 2023-02-15 | U126602 | U134723 | 2022-01-06 | 2023-07-31 |  |  | DEREK PAYTON | 2023-02-13 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3740.08 | 0 | 0 | 0 | 3740.08 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164753100 |  | 100281512 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | FORDLAND | 104 FORDLAND DR | 209 | GEO | 2023-02-13 | U126284 | U125763 | 2023-02-03 | 2023-12-29 |  |  | JOSH PASLEY | 2023-02-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.0667 | 1 | 2585.03 | 374.65 | 0 | 252.25 | 1958.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165286200 |  | 100336932 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | M L KING | 444 M L KING BV 1-DOWN | 067 | LEX | 2023-02-13 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-02-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2260.27 | 0 | 0 | 0 | 2260.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166139300 |  | 100313896 |  | 3716212N | 1635077 |  |  | 565 | EX | SERVICE LINE REPAIR | 2621P | AMERICAN | 136 AMERICAN AV | 067 | LEX | 2023-02-13 | MSHARON | U134822 | 2023-02-09 | 2023-02-10 |  |  | MSHARON | 2023-02-13 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACN |  | 100 | 056532B26210031 | 33.3833 | 3 | 5850.55 | 2982.58 | 535.21 | 166.84 | 2165.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166194600 |  | 100289252 |  | 6724212A |  |  |  | 565 | EX | SERVICE LINE - REPAIR | 2621P | LOMBARDY | 664 LOMBARDY DR | 067 | LEX | 2023-02-13 | JOCHOA | U134852 | 2023-02-10 | 2023-02-10 | 2023-02-10 |  | JOCHOA | 2023-02-13 | 2023-02-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.8833 | 4 | 1878.68 | 1200.68 | 282.11 | 395.89 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 20859996800 |  | 100358618 |  | 6740232I |  |  |  | 566 | EX | DEMO / ABANDON / IDLE *HOLD* | 2621P | HIGHLAND *HOLD AMRP* | 125 HIGHLAND *HOLD AMRP* LN | 017 | PAR | 2023-02-14 | NRICHIE | U132002 | 2020-11-12 | 2023-02-14 |  |  | NRICHIE | 2023-02-14 | 2022-01-21 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 7.75 | 12 | 498.43 | 413.85 | 0 | 84.58 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21900903000 |  | 100273278 |  | 6684224E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | WOODHILL | 102 WOODHILL LN 1 | 073 | FRA | 2023-02-14 | U126602 | AOC SYST | 2021-04-06 | 2022-12-31 | 2022-12-31 |  | DEREK PAYTON | 2023-02-14 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 8 | 1 | 4318.95 | 598.39 | 266.56 | 33.77 | 3420.23 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959959400 |  | 100358984 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | STERNS | 308 STERNS ST | 017 | PAR | 2023-02-14 | U126286 | U134723 | 2021-12-16 | 2023-07-31 |  |  | TYLER ALLISON | 2023-02-14 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 8 | 1 | 3567.36 | 546.27 | 0 | 30.84 | 2990.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22113722300 |  | 100320039 |  | 6716208K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311844 | 2600B | GLENDOVER | 231 GLENDOVER RD | 067 | LEX | 2023-02-14 | U461309 | U125208 | 2022-07-01 | 2022-12-30 | 2024-06-30 |  | R.HUMPHREYS | 2023-02-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.5 | 1 | 5909.15 | 506.53 | 473.02 | 91.51 | 4838.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22113723100 |  | 100312498 |  | 6716208F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311860 | 2600B | SOUTHLAND | 318 SOUTHLAND DR | 067 | LEX | 2023-02-14 | U461322 | U125208 | 2022-07-01 | 2022-12-29 | 2024-06-30 |  | STEVE CANOY | 2023-02-14 | 2023-02-13 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.75 | 2 | 9226.26 | 1476.85 | 0 | 987.09 | 6762.32 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22122636300 |  | 100268295 |  | 7356260M |  |  |  | 565 | EX | REPLACE SERVICE LINE - D259755 | 2600B | WINCHESTER | 801 WINCHESTER AV | 019 | ASH | 2023-02-14 | DESKAGG | U125208 | 2022-08-09 | 2023-02-08 | 2024-08-31 |  | DESKAGG | 2023-02-14 | 2023-02-13 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 15.35 | 2 | 6253.02 | 1156.98 | 459.3 | 194.11 | 4442.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22122637700 |  | 100316310 |  | 6716208B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303144 | 2600B | VISTA | 206 E VISTA ST | 067 | LEX | 2023-02-17 | U128410 | U125208 | 2022-08-09 | 2023-02-08 | 2024-08-31 |  | CDESPAIN | 2023-02-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10 | 1 | 5028.32 | 722.26 | 466.88 | 40.74 | 3798.44 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129028500 |  | 100242761 |  | 7356256O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GALLAHER | 1233 GALLAHER DR | 019 | ASH | 2023-02-14 | BMEEK | U130722 | 2022-09-05 | 2022-12-30 | 2023-02-28 |  | BMEEK | 2023-02-14 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 10.3 | 2 | 1017.2 | 676.38 | 19.89 | 320.93 | 0 | 0 | 0 | 0
KY | KY - EAST | 2682 | 22129039800 |  | 100426767 |  | 7388156T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2633S | WILLARD | 314 WILLARD BR | 119 | PIN | 2023-02-14 | U130172 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JOHN HOWARD | 2023-02-14 | 2023-02-10 |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 22 | 3 | 1611.73 | 1525.63 | 0 | 86.1 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964236100 |  | 100347928 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | LINDEN | 19 LINDEN AV | 049 | WIN | 2023-02-21 | U126603 | U134723 | 2022-01-06 | 2023-07-31 |  |  | SHAWN DENNIS | 2023-02-14 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 7780.11 | 0 | 0 | 0 | 7780.11 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23156444700 |  | 500854510 |  | 6732236C | 0569934 | U125208 |  | 565 | EX | SERVICE LINE - REPLACE | 2600B | MCNEASE | 360 MCNEASE RD | 017 | PAR | 2023-02-28 | U461423 | U125208 | 2023-01-16 | 2023-02-28 | 2023-02-28 |  | KKOUNS | 2023-02-14 | 2023-02-13 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26290032 | 42.2167 | 5 | 11051.44 | 3049.95 | 0 | 1258.48 | 6743.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164549300 |  | 100313124 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LAFAYETTE | 289 LAFAYETTE PY 1FL | 067 | LEX | 2023-02-14 | U127206 | U125763 | 2023-02-02 | 2023-12-29 |  |  | JUSTIN HOBBS | 2023-02-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2532.02 | 0 | 0 | 0 | 2532.02 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164753000 |  | 100281508 |  | 6712232N | 2286608 |  |  | 566 | EX | ABANDN SL/22026168600 | 2600B | FORDLAND | 101 FORDLAND DR | 209 | GEO | 2023-02-14 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-02-14 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1412.39 | 0 | 0 | 0 | 1412.39 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164753200 |  | 100281507 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | FORDLAND | 105 FORDLAND DR | 209 | GEO | 2023-02-14 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-02-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2390.29 | 0 | 0 | 0 | 2390.29 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165279300 |  | 100336728 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | 4TH | 203 E 4TH ST | 067 | LEX | 2023-02-14 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-02-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3283.38 | 0 | 0 | 0 | 3283.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165286000 |  | 100336917 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | M L KING | 439 M L KING BV | 067 | LEX | 2023-02-14 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-02-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3492.82 | 0 | 0 | 0 | 3492.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166681900 |  | 100423758 |  | 6720212J | 2285539 |  |  | 566 | EX | ABANDN SL/22026158800 | 2600B | WALTON | 239 WALTON AV 1FL | 067 | LEX | 2023-02-14 | U126604 | U125763 | 2023-02-14 | 2023-12-29 |  |  | WILL FULKS | 2023-02-14 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 23166708300 |  | 100332281 |  | 6720212J | 2285539 |  |  | 565 | EX | RPLC SL/22026158800 | 2600B | WALTON | 239 WALTON AV 1FR | 067 | LEX | 2023-02-14 | U126604 | U125763 | 2023-02-14 | 2023-12-29 |  |  | WILL FULKS | 2023-02-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3816.05 | 0 | 0 | 0 | 3816.05 | 0 | 0 | 0
KY | KY - WEST | 2623 | 17550817000 |  | 100344551 |  | 6700224O |  |  |  | 565 | EX | REPL SERV - ATMOS CORR | 2621P | MAIN | 218 W MAIN ST | 239 | MID | 2023-02-15 | U129731 | U125208 | 2017-10-04 | 2017-12-29 |  |  | F.GOINS | 2023-02-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.6167 | 1 | 2466.79 | 474.96 | 0 | 74.94 | 1916.89 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959959500 |  | 100358985 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | STERNS | 311 STERNS ST | 017 | PAR | 2023-02-15 | U126286 | U134723 | 2021-12-16 | 2023-07-31 |  |  | TYLER ALLISON | 2023-02-15 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 8 | 1 | 4372.91 | 546.27 | 0 | 30.84 | 3795.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959964200 |  | 100358988 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | STEWART | 850 STEWART ST | 017 | PAR | 2023-02-15 | U126286 | U134723 | 2021-12-16 | 2023-07-31 |  |  | TYLER ALLISON | 2023-02-15 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4743.55 | 0 | 0 | 0 | 4743.55 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22108825300 |  | 500943949 |  | 6712228A | 2289184 |  |  | 565 | EX | NBT - SERVICE LINE/MTR UPG | 2621P | SEMINOLE | 624 SEMINOLE TL | 209 | GEO | 2023-02-15 | U128816 | U125208 | 2022-06-09 | 2022-06-08 | 2022-06-22 |  | OLIVER MAYNARD | 2023-02-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 6.5667 | 1 | 3818.37 | 503.86 | 541.17 | 28.46 | 2744.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129047200 |  | 100336674 |  | 6720212I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HAWKINS | 446 HAWKINS AV | 067 | LEX | 2023-02-16 | U125208 | U130722 | 2022-09-05 | 2022-12-30 |  |  | LSTANFI | 2023-02-15 | 2023-02-03 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10.9833 | 5 | 2619.25 | 650.47 | 0 | 126.84 | 1841.94 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964235600 |  | 100347932 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | LINDEN | 11 LINDEN AV | 049 | WIN | 2023-02-15 | U126602 | U134723 | 2022-01-06 | 2023-07-31 |  |  | DEREK PAYTON | 2023-02-15 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3448.37 | 0 | 0 | 0 | 3448.37 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964236000 |  | 100347929 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | LINDEN | 17 LINDEN AV | 049 | WIN | 2023-02-15 | U126602 | U134723 | 2022-01-06 | 2023-07-31 |  |  | DEREK PAYTON | 2023-02-15 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 5690.23 | 0 | 0 | 0 | 5690.23 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979019300 |  | 100249126 |  | 7328284F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OLD SUNSHINE | 188 OLD SUNSHINE RD | 089 | S S | 2023-02-15 | BMEEK | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | BMEEK | 2023-02-15 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.0833 | 2 | 313.2 | 205.04 | 19.89 | 88.27 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22994324100 |  | 100353521 |  | 7256280K | 2180424 |  |  | 565 | VO | REPLACE SL W/21-0261272-00 | 2600B | 3RD | 245 W 3RD ST | 161 | MAY | 2023-02-20 |  | U134723 | 2022-04-19 | 2022-12-30 |  |  | BGADDIS | 2023-02-15 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1
KY | KY - WEST | 2621 | 23164553000 |  | 100313102 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | SOUTHBEND | 535 SOUTHBEND DR | 067 | LEX | 2023-02-15 | U128762 | U125763 | 2023-02-02 | 2023-12-29 |  |  | CORY TINCHER | 2023-02-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3546.75 | 0 | 0 | 0 | 3546.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164553100 |  | 100313103 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | SOUTHBEND | 539 SOUTHBEND DR | 067 | LEX | 2023-02-15 | U124003 | U125763 | 2023-02-02 | 2023-12-29 |  |  | BPULLIAM/FISHEL | 2023-02-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2816.78 | 0 | 0 | 0 | 2816.78 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164746100 |  | 100281436 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | BROADWAY | 600 N BROADWAY ST | 209 | GEO | 2023-02-15 | U126284 | U125763 | 2023-02-03 | 2023-12-29 |  |  | JOSH PASLEY/TEAM FISHEL | 2023-02-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.9333 | 1 | 2846.8 | 367.24 | 0 | 247.25 | 2232.31 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164752900 |  | 100281510 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | FORDLAND | 100 FORDLAND DR | 209 | GEO | 2023-02-15 | U126284 | U125763 | 2023-02-03 | 2023-12-29 |  |  | JOSH PASLEY/TEAM FISHEL | 2023-02-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.0667 | 1 | 4686.4 | 374.65 | 0 | 252.25 | 4059.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23165081700 |  | 100459834 |  | 6712232P | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER | 2623D | OLD MILL | 210 OLD MILL RD | 209 | GEO | 2023-02-15 | DCOLLIN | AOC SYST | 2023-02-06 | 2023-03-01 | 2023-03-31 |  | DCOLLIN | 2023-02-15 | 2023-02-14 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 28 | 4 | 3855.41 | 2309.9 | 269.51 | 1205.6 | 70.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166639500 |  | 100293862 |  | 6720212A |  |  |  | 565 | EX | GRADE 1 REPLACE SERV LINE | 2621P | RUSSELL CAVE | 924 RUSSELL CAVE RD | 067 | LEX | 2023-02-15 | KOBRYAN | U129939 | 2023-02-14 | 2023-02-14 | 2023-02-14 |  | KOBRYAN | 2023-02-15 | 2023-02-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.85 | 3 | 1711.12 | 848.82 | 332.7 | 47.9 | 481.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166682100 |  | 100332277 |  | 6720212J | 2285539 |  |  | 565 | EX | RPLC SL/22026158800 | 2600B | WALTON | 249 WALTON AV | 067 | LEX | 2023-02-15 | U126604 | U125763 | 2023-02-14 | 2023-12-29 |  |  | WILL FULKS | 2023-02-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3471.71 | 0 | 0 | 0 | 3471.71 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166683400 |  | 100332278 |  | 6720212J | 2285539 |  |  | 565 | EX | RPLC SL/22026158800 | 2600B | WALTON | 243 WALTON AV | 067 | LEX | 2023-02-15 | U126604 | U125763 | 2023-02-14 | 2023-12-29 |  |  | WILL FULKS | 2023-02-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3644.36 | 0 | 0 | 0 | 3644.36 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166729400 |  | 100280828 |  | 6688228I |  |  |  | 565 | EX | LEAK REPAIRS - S.L.D308933 | 2621P | LANGFORD | 133 LANGFORD AV | 073 | FRA | 2023-02-16 | U125208 | U129939 | 2023-02-14 | 2023-02-14 | 2023-02-14 |  | BWHITE | 2023-02-15 | 2023-02-14 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8.8167 | 4 | 1259.52 | 499.21 | 67.34 | 28.17 | 664.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166790100 |  | 100308819 |  | 6712212P |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | FURLONG | 853 FURLONG DR | 067 | LEX | 2023-02-15 | MSHARON | U136097 | 2023-02-14 | 2022-12-08 | 2024-06-30 |  | MSHARON | 2023-02-15 | 2023-02-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.8833 | 3 | 1704.05 | 1469.67 | 108.54 | 82.94 | 42.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166992400 |  | 100277217 |  | 6684228H |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2600B | HUDSON | 409 HUDSON ST | 073 | FRA | 2023-02-16 | U128816 | U125768 | 2023-02-15 | 2049-12-31 |  |  | OLIVER MAYNARD | 2023-02-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 18.7667 | 2 | 6222.07 | 1233.05 | 345.78 | 69.56 | 4573.68 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23167098800 |  | 100358283 |  | 6740232I |  |  |  | 566 | EX | ABANDON SL/PR 2413 /RI PENDING | 2621P | MOUNT AIRY | 317 MOUNT AIRY AV | 017 | PAR | 2023-03-03 | U125208 | U125208 | 2023-02-15 | 2023-02-15 |  |  | NRICHIE | 2023-02-15 | 2023-02-15 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.85 | 3 | 85.2 | 67.23 | 0 | 17.97 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22112989000 |  | 500337816 |  | 7348264F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY /MNFLD | 2621P | JESSICA | 459 JESSICA DR 10 | 089 | RAC | 2023-02-16 | BMEEK | U134723 | 2022-06-29 | 2022-07-01 | 2022-12-31 |  | BMEEK | 2023-02-16 | 2023-02-15 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 11.8667 | 3 | 1187.6 | 964.5 | 0 | 223.1 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23165898600 |  | 100248505 |  | 7356256J |  |  |  | 565 | EX | REPLACE SERVICE LINE - D259831 | 2621P | BELMONT | 2013 BELMONT ST | 019 | ASH | 2023-02-16 | LAMAY | U125208 | 2023-02-09 | 2023-02-10 | 2023-03-01 |  | LAMAY | 2023-02-16 | 2023-02-13 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 23.3667 | 5 | 3953.73 | 1624.7 | 613.6 | 707.17 | 1008.26 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23167103500 |  | 100301994 |  | 6712212H |  |  |  | 565 | EX | LEAK REPAIRS - S.L. D310410 G1 | 2621P | CAMBRIDGE | 1985 CAMBRIDGE DR 1 | 067 | LEX | 2023-02-16 | U125208 | U134822 | 2023-02-15 | 2023-02-15 | 2023-02-15 |  | TROE | 2023-02-16 | 2023-02-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.9833 | 6 | 3355.05 | 1751.11 | 697.53 | 98.81 | 807.6 | 0 | 0 | 0
KY | KY - WEST | 2623 | 17546439900 |  | 100415117 |  | 6712228J |  |  |  | 565 | EX | REPL SERV - PITTING @ RISER | 2621P | FAIRFAX | 170 FAIRFAX WY B | 209 | GEO | 2023-02-17 | U129731 | U125208 | 2017-09-21 | 2017-09-26 |  |  | F.GOINS | 2023-02-17 | 2019-03-15 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 9.75 | 7 | 3361.92 | 667 | 0 | 216.26 | 2478.66 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959959800 |  | 100358992 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | STEWART | 900 STEWART ST | 017 | PAR | 2023-02-17 | U126286 | U134723 | 2021-12-16 | 2023-07-31 |  |  | TYLER ALLISON | 2023-02-17 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 8 | 1 | 4978.3 | 546.27 | 0 | 30.84 | 4401.19 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22110545500 |  | 100274394 |  | 6684228N | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | CAMPBELL | 407 W CAMPBELL ST 1FE | 073 | FRA | 2023-02-17 | U128816 | AOC SYST | 2022-06-16 | 2022-12-16 | 2023-12-31 |  | OLIVER MAYNARD | 2023-02-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 10.5 | 1 | 6366.07 | 806.57 | 609.76 | 45.5 | 4904.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22113952700 |  | 100312105 |  | 6716208I |  |  |  | 565 | EX | REPLACE SERVICE LINE - D304112 | 2600B | HILL N DALE | 529 HILL N DALE RD | 067 | LEX | 2023-02-20 | U128410 | U125208 | 2022-07-05 | 2023-01-03 | 2024-07-31 |  | CDESPAIN | 2023-02-17 | 2023-02-16 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.4167 | 2 | 7295.3 | 1555.94 | 358.34 | 453.93 | 4927.09 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129931100 |  | 100261961 |  | 7352256H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D259764 | 2600B | STEPHENS | 2103 STEPHENS ST | 019 | ASH | 2023-02-17 | DESKAGG | U125208 | 2022-09-08 | 2023-03-07 | 2024-09-30 |  | DESKAGG | 2023-02-17 | 2023-02-15 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 18.3 | 3 | 5244.24 | 1299.67 | 518.79 | 198.12 | 3227.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22150011100 |  | 100462273 |  | 6720204C | 0992290 |  |  | 565 | EX | REPLACE SL - D303225 & D310378 | 2600B | ALUMNI | 2351 ALUMNI DR | 067 | LEX | 2023-02-17 | U461322 | U124960 | 2022-12-21 | 2023-02-15 | 2024-08-31 |  | STEVE CANOY | 2023-02-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.4167 | 2 | 5087.03 | 1052.95 | 0 | 479.46 | 3554.62 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964243800 |  | 100347938 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | SYCAMORE | 6 SYCAMORE ST | 049 | WIN | 2023-02-17 | U126602 | U134723 | 2022-01-06 | 2023-07-31 |  |  | DEREK PAYTON | 2023-02-17 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2774.26 | 0 | 0 | 0 | 2774.26 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964248000 |  | 100347984 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | SYCAMORE | 3 SYCAMORE ST | 049 | WIN | 2023-02-17 | U126602 | U134723 | 2022-01-06 | 2023-07-31 |  |  | DEREK PAYTON | 2023-02-17 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2606 | 0 | 0 | 0 | 2606 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22979036900 |  | 100336100 |  | 6720212J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 7TH | 644 E 7TH ST | 067 | LEX | 2023-02-17 | U125208 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | LSTANFI | 2023-02-17 | 2023-02-02 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 21.7833 | 6 | 2338.28 | 1391.22 | 34.39 | 322.73 | 589.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164552400 |  | 100313097 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | SOUTHBEND | 509 SOUTHBEND DR | 067 | LEX | 2023-02-17 | U128762 | U125763 | 2023-02-02 | 2023-12-29 |  |  | CORY TINCHER | 2023-02-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3722.51 | 0 | 0 | 0 | 3722.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166434400 |  | 100338123 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | 7TH | 434 E 7TH ST | 067 | LEX | 2023-02-17 | LSTANFI | U133234 | 2023-02-13 | 2023-02-24 | 2023-03-12 |  | LSTANFI | 2023-02-17 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.65 | 3 | 51.44 | 41.34 | 0 | 10.1 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166439000 |  | 501205292 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | 7TH | 432 E 7TH ST | 067 | LEX | 2023-02-20 | U125208 | U133234 | 2023-02-13 | 2023-02-24 | 2023-03-12 |  | LSTANFI | 2023-02-17 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1 | 0 | 227.96 | 62.05 | 16.76 | 15.15 | 134 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166683200 |  | 500866183 |  | 6720212J | 2285539 |  |  | 565 | EX | RPLC SL/22026158800 | 2600B | WALTON | 225 WALTON AV CABLE | 067 | LEX | 2023-02-17 | U126284 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JOSH PASLEY/MILLER PIPELINE | 2023-02-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2903.3 | 593.55 | 0 | 399.57 | 1910.18 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959959600 |  | 100358969 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | STEWART | 648 STEWART ST | 017 | PAR | 2023-02-20 | U126286 | U134723 | 2021-12-16 | 2023-07-31 |  |  | TYLER ALLISON | 2023-02-20 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 9 | 1 | 4209.51 | 614.57 | 0 | 34.69 | 3560.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959959700 |  | 100358970 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | STEWART | 650 STEWART ST | 017 | PAR | 2023-02-20 | U126286 | U134723 | 2021-12-16 | 2023-07-31 |  |  | TYLER ALLISON | 2023-02-20 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3416.69 | 0 | 0 | 0 | 3416.69 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960861100 |  | 100249835 |  | 7356248H | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | PADDLE CREEK | 8017 PADDLE CREEK RD | 019 | CAT | 2023-02-20 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH JERRY NEWSOME | 2023-02-20 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2028.53 | 0 | 0 | 0 | 2028.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22115126500 |  | 100311246 |  | 6712204C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D246254 | 2600B | BERWYN | 3514 BERWYN CT | 067 | LEX | 2023-02-20 | U461322 | U125208 | 2022-07-11 | 2023-01-06 | 2024-07-31 |  | STEVE CANOY | 2023-02-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 3430.7 | 598.21 | 0 | 33.76 | 2798.73 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22116765000 |  | 100265803 |  | 7348252H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D258122 | 2600B | SUMMIT | 927 SUMMIT RD | 019 | ASH | 2023-02-20 | DESKAGG | U125208 | 2022-07-18 | 2023-01-13 | 2024-07-31 |  | DESKAGG | 2023-02-20 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 6.8 | 1 | 4758.66 | 480.9 | 280.32 | 83.86 | 3913.58 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22127154700 |  | 100282320 |  | 6712232N | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | COURT | 360 N COURT ST | 209 | GEO | 2023-02-20 | U129731 | AOC SYST | 2022-08-26 | 2023-12-31 | 2023-12-31 |  | F.GOINS | 2023-02-20 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 8 | 1 | 3726.19 | 568.07 | 0 | 99.17 | 3058.95 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129230600 |  | 100275692 |  | 6684228F | 1635077 |  |  | 565 | EX | AOC EXPOSED PLASTIC SL | 2600B | KENTUCKY | 635 KENTUCKY AV | 073 | FRA | 2023-02-20 | U128816 | AOC SYST | 2022-09-06 | 2022-10-06 | 2022-11-05 |  | OLIVER MAYNARD | 2023-02-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 10 | 1 | 6327.84 | 768.16 | 347.94 | 43.33 | 5168.41 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22150056300 |  | 100315148 |  | 6716212O |  |  |  | 566 | EX | ABANDON S/L - PROPERTY TO DEMO | 2621P | JOURNAL | 901 JOURNAL HL | 067 | LEX | 2023-02-20 | MSHARON | U461383 | 2022-12-21 | 2023-03-01 | 2023-03-01 |  | MSHARON | 2023-02-20 | 2023-02-15 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 28.7 | 7 | 1846.48 | 1731.95 | 16.76 | 97.77 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964243900 |  | 100347983 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | SYCAMORE | 7 SYCAMORE ST | 049 | WIN | 2023-02-20 | U126602 | U134723 | 2022-01-06 | 2023-07-31 |  |  | DEREK PAYTON | 2023-02-20 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4195.79 | 0 | 0 | 0 | 4195.79 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964244200 |  | 100347940 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | SYCAMORE | 12 SYCAMORE ST | 049 | WIN | 2023-02-20 | U126602 | U134723 | 2022-01-06 | 2023-07-31 |  |  | DEREK PAYTON | 2023-02-20 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3354.66 | 0 | 0 | 0 | 3354.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026259000 |  |  |  | 6728208B | 2395609 | U461383 |  | 557 | EX | EMER-INST 85'-4"PMMP MND311494 | 2621P | BAHAMA | BAHAMA RD | 067 | LEX | 2023-04-12 | U121331 | U461383 | 2023-02-15 | 2023-02-15 | 2023-02-24 | 2023-02-20 | HMCKUNE | 2023-02-20 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2590 |  |  | 100 | 055732230262590 | 0.26667 | 85 | 23726.73 | 5976.1 | 862.06 | 337.27 | 12632.14 | 0 | 44.46 | 3874.7 | 85
KY | KY - WEST | 2621 | 23026259100 |  |  |  | 6728208B | 2395609 | U461383 |  | 558 | EX | EMER-RETIRE 85' OF 4"PAMP MAIN | 2621P | BAHAMA | BAHAMA RD | 067 | LEX | 2023-04-12 | U121331 | U461383 | 2023-02-15 | 2023-02-21 | 2023-02-24 | 2023-02-20 | HMCKUNE | 2023-02-20 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2591 |  |  | 100 | 055832230262591 | 4.1833 | 0 | 260.66 | 246.44 | 0 | 14.22 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164552500 |  | 100313098 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | SOUTHBEND | 511 SOUTHBEND DR | 067 | LEX | 2023-02-20 | U124003 | U125763 | 2023-02-02 | 2023-12-29 |  |  | BPULLIAM/FISHEL | 2023-02-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 5661.59 | 0 | 0 | 0 | 5661.59 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164753700 |  | 100281504 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | FORDLAND | 111 FORDLAND DR | 209 | GEO | 2023-02-20 | U126284 | U125763 | 2023-02-03 | 2023-12-29 |  |  | JOSH PASLEY/TEAM FISHEL | 2023-02-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 10.4667 | 2 | 3383.76 | 734.28 | 0 | 276.2 | 2373.28 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165285800 |  | 100336918 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | M L KING | 437 M L KING BV | 067 | LEX | 2023-02-20 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-02-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4322.92 | 0 | 0 | 0 | 4322.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165286700 |  | 100336912 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | M L KING | 459 M L KING BV | 067 | LEX | 2023-02-20 | U127206 | U125763 | 2023-02-07 | 2023-12-29 |  |  | JUSTIN HOBBS | 2023-02-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2710.64 | 0 | 0 | 0 | 2710.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166683700 |  | 100332233 |  | 6720212J | 2285539 |  |  | 565 | VO | RPLC SL/22026158800 | 2600B | WALTON | 264 WALTON AV | 067 | LEX | 2023-02-23 | U126604 | U125763 | 2023-02-14 | 2023-12-29 |  |  | WILL FULKS | 2023-02-20 |  |  | B | [11 empty] | 23169042100 | 100 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23168125800 |  | 100330627 |  | 6720212O |  |  |  | 565 | EX | GRADE 1 REPLACE SERVICE | 2621P | HENRY CLAY | 439 HENRY CLAY BV | 067 | LEX | 2023-02-20 | HMCKUNE | U129939 | 2023-02-20 | 2023-02-20 | 2023-02-20 |  | HMCKUNE | 2023-02-20 | 2023-02-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.6833 | 4 | 1939.78 | 1329.33 | 498.05 | 75 | 37.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23168144500 |  | 100306210 |  | 6712212L |  |  |  | 565 | EX | REPAIR/REPLACE SL D305419 | 2600B | PORT ROYAL | 1904 PORT ROYAL CT | 067 | LEX | 2023-02-22 | U129722 | U134723 | 2023-02-20 | 2022-11-10 | 2024-05-31 |  | M YOUNG | 2023-02-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26210022 | 10 | 1 | 3119.09 | 664.03 | 388.48 | 37.47 | 2029.11 | 0 | 0 | 0
KY | KY - WEST | 2623 | 20857121100 |  | 100442956 |  | 6712228F | 1528079 |  |  | 565 | EX | CONT: B - SERVICE LINE REPLACE | 2621P | SLONE | 701 SLONE DR 9 | 209 | GEO | 2023-02-21 | U128816 | U125208 | 2020-10-29 | 2020-12-14 |  |  | OLIVER MAYNARD | 2023-02-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 13.0167 | 3 | 5471.19 | 969.21 | 381.07 | 223.84 | 3897.07 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883206700 |  | 100252205 |  | 7364200T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | YELLOW CREEK | YELLOW CREEK RD | 127 | LOU | 2023-02-22 | U129900 | U120245 | 2021-01-30 | 2022-07-01 | 2022-12-31 |  | U129900 | 2023-02-21 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - CENTRAL | 2629 | 21959954500 |  | 500172172 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | CURTIS | 303 CURTIS ST | 017 | PAR | 2023-02-21 | U126286 | U134723 | 2021-12-16 | 2023-07-31 |  |  | TYLER ALLISON | 2023-02-21 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 8.5 | 1 | 3519.01 | 580.42 | 0 | 32.77 | 2905.82 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959961800 |  | 100358989 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/220262303-00 | 2600B | CURTIS | 316 CURTIS ST | 017 | PAR | 2023-02-21 | U126286 | U134723 | 2021-12-16 | 2023-07-31 |  |  | TYLER ALLISON | 2023-02-21 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2903.08 | 0 | 0 | 0 | 2903.08 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964251200 |  | 100347939 |  | 6748208I |  |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | SYCAMORE | 8 SYCAMORE ST | 049 | WIN | 2023-02-22 | U126602 | U134723 | 2022-01-06 | 2023-07-31 |  |  | DEREK PAYTON | 2023-02-21 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 5515.4 | 0 | 0 | 0 | 5515.4 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026256700 |  |  |  | 7340268E | 2395179 | U461383 |  | 584 | EX | RETIRE PAPER GAUGE | 2631M | US 23 | 964 US 23 | 089 | GRE | 2023-03-07 | U123258 | U461383 | 2023-02-13 | 2023-12-01 | 2023-12-01 | 2023-02-21 | SHANE GIORDANO | 2023-02-21 | 2023-02-21 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00584 | 3200584 |  |  | WP2567 |  |  | 100 | 058432230262567 | 6.4833 | 0 | 756.49 | 435.82 | 0 | 320.67 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23164187100 |  | 500850867 |  | 7236216H | 0148530 |  |  | 565 | EX | NBT - SERVICE LINE : 1"P 106' | 2621P | SILVER LAKE | 390 SILVER LAKE DR | 173 | MT | 2023-02-21 | U461309 | U125208 | 2023-02-01 | 2023-01-31 | 2023-03-02 |  | R.HUMPHREYS | 2023-02-21 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26290032 | 8 | 1 | 4704.12 | 540.34 | 301.33 | 97.61 | 3764.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164749300 |  | 100281517 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | EASTWOOD | 102 EASTWOOD DR | 209 | GEO | 2023-02-21 | U126284 | U125763 | 2023-02-03 | 2023-12-29 |  |  | JOSH PASLEY/TEAM FISHEL | 2023-02-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 1 | 4254.09 | 593.55 | 0 | 399.57 | 3260.97 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164749500 |  | 100281515 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | EASTWOOD | 105 EASTWOOD DR | 209 | GEO | 2023-02-21 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-02-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2069.04 | 0 | 0 | 0 | 2069.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165285900 |  | 100336930 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | M L KING | 438 M L KING BV | 067 | LEX | 2023-02-21 | U127206 | U125763 | 2023-02-07 | 2023-12-29 |  |  | JUSTIN HOBBS | 2023-02-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2469.58 | 0 | 0 | 0 | 2469.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166683300 |  | 100332284 |  | 6720212J | 2285539 |  |  | 565 | EX | RPLC SL/22026158800 | 2600B | WALTON | 235 WALTON AV | 067 | LEX | 2023-02-21 | U126604 | U125763 | 2023-02-14 | 2023-12-29 |  |  | WILL FULKS | 2023-02-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3586.16 | 0 | 0 | 0 | 3586.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23168275800 |  | 100311928 |  | 6716208I |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309452 | 2621P | SOUTHVIEW | 2816 SOUTHVIEW DR | 067 | LEX | 2023-02-21 | U930915 | U125208 | 2023-02-20 | 2023-02-20 | 2023-02-20 |  | KKINDER | 2023-02-21 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 22.8 | 3 | 1736.74 | 1435.49 | 146.5 | 81.05 | 73.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23168443700 |  | 100290166 |  | 6720212B |  |  |  | 565 | EX | LOWER GAS LINE | 2621P | BLUE GRASS | 220 BLUE GRASS AV | 067 | LEX | 2023-02-21 | LSTANFI | U129939 | 2023-02-21 | 2023-02-21 |  |  | LSTANFI | 2023-02-21 | 2023-02-21 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 17.4833 | 3 | 1562.24 | 1166.92 | 72.83 | 292.79 | 29.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959964700 |  | 100406204 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | CURTIS | 302 CURTIS ST | 017 | PAR | 2023-02-22 | U126286 | U134723 | 2021-12-16 | 2023-07-31 |  |  | TYLER ALLISON | 2023-02-22 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 8 | 1 | 3711.47 | 546.27 | 0 | 30.84 | 3134.36 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22127160900 |  | 100282416 |  | 6712228C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE *RLA* | 2623D | MAIN | 601 E MAIN ST | 209 | GEO | 2023-02-22 | U129731 | AOC SYST | 2022-08-26 | 2023-02-24 | 2023-12-31 |  | F.GOINS | 2023-02-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 8 | 1 | 3887.06 | 566.09 | 0 | 99.06 | 3221.91 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22148433800 |  | 100269149 | 26 | 6736252M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | REYNOLDS | 113 REYNOLDS AV | 097 | CYN | 2023-02-22 | NRICHIE | PMCNABB | 2022-12-09 | 2023-12-29 |  |  | NRICHIE | 2023-02-22 | 2023-01-18 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 14.65 | 5 | 1798.88 | 1059.07 | 16.76 | 136.79 | 586.26 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964244000 |  | 100347982 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | SYCAMORE | 11 SYCAMORE ST | 049 | WIN | 2023-02-22 | U126602 | U134723 | 2022-01-06 | 2023-07-31 |  |  | DEREK PAYTON | 2023-02-22 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3013.78 | 0 | 0 | 0 | 3013.78 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964244300 |  | 100347981 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | SYCAMORE | 13 SYCAMORE ST | 049 | WIN | 2023-02-22 | U126602 | U134723 | 2022-01-06 | 2023-07-31 |  |  | DEREK PAYTON | 2023-02-22 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 5710.48 | 0 | 0 | 0 | 5710.48 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026260200 |  |  |  | 7344268P | 2294088 | U461383 |  | 909 | EX | INSTALL ERX W/SUPER SOLAR | 2631M | RIVERSIDE | 1001 RIVERSIDE DR | 089 | WOR | 2023-03-07 | U123258 | U461383 | 2023-02-16 | 2023-12-01 | 2023-12-01 | 2023-02-22 | SHANE GIORDANO | 2023-02-22 | 2023-02-22 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP2602 |  |  | 100 | 090932230262602 | 13.9833 | 0 | 4114.48 | 892.01 | 0 | 760.66 | 2460 | 0 | 1.81 | 0
KY | KY - EAST | 2631 | 23026260300 |  |  |  | 7344268P | 2294088 | U461383 |  | 584 | EX | RETIRE PAPER CHART | 2631M | RIVERSIDE | 1001 RIVERSIDE DR | 089 | WOR | 2023-03-07 | U123258 | U461383 | 2023-02-16 | 2023-12-01 | 2023-12-01 | 2023-02-22 | SHANE GIORDANO | 2023-02-22 | 2023-02-22 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00584 | 3200584 |  |  | WP2603 |  |  | 100 | 058432230262603 | 4.85 | 0 | 564.75 | 325.35 | 0 | 239.4 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026266300 |  |  |  | 6712216H | 2396224 | U461383 |  | 557 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | 2621P | HORTON | HORTON | 067 | LEX | 2023-04-06 | U124014 | U461383 | 2023-03-15 | 2023-11-29 | 2023-11-30 | 2023-02-22 | MCRAIG | 2023-02-22 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2663 |  |  | 100 | 055732230262663 |  | 3 | 4867.28 | 3075.41 | 76.08 | 945.55 | 0 | 0 | 0 | 770.24 | 3
KY | KY - WEST | 2621 | 23026266400 |  |  |  | 6712216H | 2396224 | U461383 |  | 558 | EX | EMER-RETIRE 3' OF 2"PMP MAIN | 2621P | HORTON | HORTON | 067 | LEX | 2023-04-06 | U124014 | U461383 | 2023-03-15 | 2023-11-30 | 2023-11-30 | 2023-02-22 | MCRAIG | 2023-02-22 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2664 |  |  | 100 | 055832230262664 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164553500 |  | 100313123 |  | 6716208B | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LAFAYETTE | 291 LAFAYETTE PY | 067 | LEX | 2023-02-22 | U124003 | U125763 | 2023-02-02 | 2023-12-29 |  |  | BPULLIAM/FISHEL | 2023-02-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2661.45 | 0 | 0 | 0 | 2661.45 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164749200 |  | 100281518 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | EASTWOOD | 100 EASTWOOD DR | 209 | GEO | 2023-02-22 | U126284 | U125763 | 2023-02-03 | 2023-12-29 |  |  | JOSH PASLEY/TEAM FISHEL | 2023-02-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.1333 | 1 | 3314.75 | 379.84 | 0 | 255.74 | 2679.17 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164749400 |  | 500460868 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | EASTWOOD | 103 EASTWOOD DR | 209 | GEO | 2023-02-22 | U126284 | U125763 | 2023-02-03 | 2023-12-29 |  |  | JOSH PASLEY/TEAM FISHEL | 2023-02-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.8667 | 1 | 3760.67 | 436.24 | 0 | 293.72 | 3030.71 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165285500 |  | 100336920 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | M L KING | 433 M L KING BV | 067 | LEX | 2023-02-22 | U127206 | U125763 | 2023-02-07 | 2023-12-29 |  |  | JUSTIN HOBBS | 2023-02-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2824.85 | 0 | 0 | 0 | 2824.85 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23165648700 |  | 100269019 |  | 6736252M |  |  |  | 566 | EX | ABANDON SL - CNVRT/CUSTRQD | 2621P | MILLER | 117 N MILLER ST DN | 097 | CYN | 2023-02-22 | NRICHIE | U133234 | 2023-02-08 | 2023-02-10 | 2023-03-01 |  | NRICHIE | 2023-02-22 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 11.85 | 3 | 926.93 | 875.45 | 2.07 | 49.41 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23168762200 |  | 100306436 |  | 6716212M |  |  |  | 565 | EX | REPAIR/REPLACE D311864 | 2600B | LAUREL HILL | 833 LAUREL HILL RD | 067 | LEX | 2023-02-23 | U129722 | U134723 | 2023-02-22 | 2023-01-08 | 2024-07-31 |  | M YOUNG | 2023-02-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26210022 | 6.65 | 1 | 3131.05 | 441.57 | 191.98 | 24.94 | 2472.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23168769500 |  | 100290169 |  | 6720212B | 2075272 |  |  | 565 | EX | SERVICE LINE REPLACE | 2621P | BLUE GRASS | 302 BLUE GRASS AV | 067 | LEX | 2023-02-22 | LSTANFI | U134852 | 2023-02-22 | 2023-02-24 | 2023-03-31 |  | LSTANFI | 2023-02-22 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 20.6 | 4 | 3071.8 | 1296.85 | 0 | 274.79 | 1500.16 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959954300 |  | 100419452 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | CURTIS | 213 CURTIS ST | 017 | PAR | 2023-02-23 | U126286 | U134723 | 2021-12-16 | 2023-07-31 |  |  | TYLER ALLISON | 2023-02-23 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2793.41 | 0 | 0 | 0 | 2793.41 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959954400 |  | 100406205 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | CURTIS | 301 CURTIS ST | 017 | PAR | 2023-02-23 | U126286 | U134723 | 2021-12-16 | 2023-07-31 |  |  | TYLER ALLISON | 2023-02-23 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 8 | 1 | 3513.07 | 546.27 | 0 | 30.84 | 2935.96 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22124326600 |  | 100282912 |  | 6712228C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE *RLA* | 2623D | DUDLEY | 422 DUDLEY AV | 209 | GEO | 2023-02-23 | U128816 | AOC SYST | 2022-08-16 | 2023-02-16 | 2023-12-31 |  | OLIVER MAYNARD | 2023-02-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 6.4667 | 1 | 4517.48 | 497 | 746.16 | 28.06 | 3246.26 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22127158100 |  | 100281998 |  | 6712232O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE *RLA* | 2623D | LYNN | 115 E LYNN ST | 209 | GEO | 2023-02-23 | U129731 | AOC SYST | 2022-08-26 | 2023-02-24 | 2023-12-31 |  | F.GOINS | 2023-02-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 8 | 1 | 3412.79 | 566.09 | 0 | 99.06 | 2747.64 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22127497200 |  | 100282008 |  | 6712232O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE *RLA* | 2623D | WEST | 113 WEST ST | 209 | GEO | 2023-02-23 | U128816 | AOC SYST | 2022-08-29 | 2023-02-28 | 2023-12-31 |  | OLIVER MAYNARD | 2023-02-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 4.0333 | 1 | 4298.77 | 309.56 | 705.56 | 17.47 | 3266.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22139143800 |  | 100329399 |  | 6720208G | 1635077 |  |  | 565 | EX | AOC ATMOSPHERIC - UNMETERED | 2621P | COBURN *RLA* | 2137 COBURN *RLA* BV 1 | 067 | LEX | 2023-02-24 | U129722 | U125208 | 2022-10-14 | 2022-12-08 | 2022-12-08 |  | M YOUNG | 2023-02-23 | 2022-12-13 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26210032 | 23.6333 | 8 | 12117.81 | 1570.59 | 694.48 | 169.77 | 9682.97 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22150002600 |  | 100251522 |  | 7336276N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2600B | OHIO RIVER | 1072 OHIO RIVER RD | 089 | GRE | 2023-02-23 | DESKAGG | U124960 | 2022-12-21 | 2022-10-12 | 2024-04-30 |  | DESKAGG | 2023-02-23 | 2023-02-21 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26310022 | 4.6167 | 2 | 4866.54 | 382.04 | 367.97 | 66.64 | 4049.89 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22150030400 |  | 500209212 |  | 6728208M |  | U124960 |  | 565 | EX | REPLACE SERVICE LINE - D311021 | 2600B | DEER HAVEN | 1270 DEER HAVEN LN | 067 | LEX | 2023-02-23 | U930915 | U124960 | 2022-12-21 | 2023-02-27 | 2024-08-31 |  | HMCKUNE | 2023-02-23 | 2023-02-13 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26210022 | 35.1833 | 8 | 10594.34 | 2054.73 | 153.06 | 115.94 | 8270.61 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964244400 |  | 100347980 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | SYCAMORE | 15 SYCAMORE ST | 049 | WIN | 2023-02-24 | U126602 | U134723 | 2022-01-06 | 2023-07-31 |  |  | DEREK PAYTON | 2023-02-23 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2575.86 | 0 | 0 | 0 | 2575.86 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979017800 |  | 100245186 |  | 7356256N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | VALLEY VIEW | 4410 VALLEY VIEW DR | 019 | ASH | 2023-02-24 | U125208 | U128070 | 2022-02-17 | 2022-12-30 | 2022-12-31 |  | RECUMP | 2023-02-23 | 2023-02-09 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 14.3833 | 3 | 1598.19 | 1235.84 | 9.82 | 352.53 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026260400 |  |  |  | 7336272G | 2294088 | U461383 |  | 909 | EX | INSTALL ERX W/SUPER SOLAR | 2631M | OLD US 23 | 2149 OLD US 23 | 089 | GRE | 2023-03-07 | U123258 | U461383 | 2023-02-16 | 2023-12-01 | 2023-12-01 | 2023-02-23 | SHANE GIORDANO | 2023-02-23 | 2023-02-23 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP2604 |  |  | 100 | 090932230262604 | 10.3333 | 0 | 3437.82 | 659.84 | 0 | 317.13 | 2460 | 0 | 0.85 | 0
KY | KY - EAST | 2631 | 23026260500 |  |  |  | 7336272G | 2294088 | U461383 |  | 584 | EX | RETIRE PAPER CHART | 2631M | OLD US 23 | 2149 OLD US 23 | 089 | GRE | 2023-03-07 | U123258 | U461383 | 2023-02-16 | 2023-12-01 | 2023-12-01 | 2023-02-23 | SHANE GIORDANO | 2023-02-23 | 2023-02-23 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00584 | 3200584 |  |  | WP2605 |  |  | 100 | 058432230262605 | 5.1833 | 0 | 605.66 | 348.92 | 0 | 256.74 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164549600 |  | 100313121 |  | 6716208B | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LAFAYETTE | 295 LAFAYETTE PY | 067 | LEX | 2023-02-23 | U124003 | U125763 | 2023-02-02 | 2023-12-29 |  |  | BPULLIAM/FISHEL | 2023-02-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3846.06 | 0 | 0 | 0 | 3846.06 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164757800 |  | 100281561 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | OAK | 506 OAK ST | 209 | GEO | 2023-02-23 | U126284 | U125763 | 2023-02-03 | 2023-12-29 |  |  | JOSH PASLEY/TEAM FISHEL | 2023-02-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 1 | 3003.84 | 593.55 | 0 | 399.57 | 2010.72 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164757900 |  | 100281500 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | OAK | 509 OAK ST | 209 | GEO | 2023-02-23 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-02-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2375.71 | 0 | 0 | 0 | 2375.71 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165285400 |  | 100336928 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | M L KING | 430 M L KING BV APT1-DN | 067 | LEX | 2023-02-23 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-02-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3547.67 | 0 | 0 | 0 | 3547.67 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166682000 |  | 100332232 |  | 6720212J | 2285539 |  |  | 565 | EX | RPLC SL/22026158800 | 2600B | WALTON | 246 WALTON AV | 067 | LEX | 2023-02-23 | U126604 | U125763 | 2023-02-14 | 2023-12-29 |  |  | WILL FULKS | 2023-02-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 5075.36 | 0 | 0 | 0 | 5075.36 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166693800 |  | 100272331 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 109 TANGLEWOOD DR | 073 | FRA | 2023-02-23 | U126308 | U125763 | 2023-02-14 | 2023-12-29 |  |  | J ENSMINGER | 2023-02-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1662.04 | 0 | 0 | 0 | 1662.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23168947900 |  | 100293861 |  | 6720212A |  |  |  | 565 | EX | REPLACE SERVICE LINE - D310477 | 2621P | RUSSELL CAVE | 920 RUSSELL CAVE RD | 067 | LEX | 2023-02-23 | U930915 | U125208 | 2023-02-23 | 2023-02-24 | 2023-03-15 |  | LSTANFI | 2023-02-23 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.4 | 4 | 3700.81 | 1162.69 | 253.98 | 307.72 | 1976.42 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23169023600 |  | 100347941 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | SYCAMORE | 14 SYCAMORE ST | 049 | WIN | 2023-02-24 | U126602 | U125763 | 2023-02-23 | 2023-12-29 |  |  | DEREK PAYTON | 2023-02-23 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2912.8 | 0 | 0 | 0 | 2912.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129123500 |  | 100270343 |  | 6736248A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WALNUT | 301 S WALNUT ST | 097 | CYN | 2023-02-24 | NRICHIE | U125208 | 2022-09-06 | 2022-12-30 |  |  | NRICHIE | 2023-02-24 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 13.65 | 3 | 3727.83 | 1012.95 | 14.69 | 266.3 | 2433.89 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964235500 |  | 100347885 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | LINDEN | 10 LINDEN AV | 049 | WIN | 2023-02-24 | U126602 | U134723 | 2022-01-06 | 2023-07-31 |  |  | DEREK PAYTON | 2023-02-24 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2662.64 | 0 | 0 | 0 | 2662.64 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23153445700 |  | 100349309 |  | 6748208M |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTRQD | 2621P | BROADWAY | 220 E BROADWAY ST | 049 | WIN | 2023-02-24 | NRICHIE | U125208 | 2023-01-05 | 2023-02-03 | 2023-02-05 |  | NRICHIE | 2023-02-24 | 2023-01-19 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 17.1 | 5 | 3668.1 | 1240.05 | 14.69 | 289.55 | 2123.81 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164758100 |  | 100281559 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | OAK | 512 OAK ST | 209 | GEO | 2023-02-24 | U126284 | U125763 | 2023-02-03 | 2023-12-29 |  |  | JOSH PASLEY/TEAM FISHEL | 2023-02-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 1 | 3665.77 | 593.55 | 0 | 399.57 | 2672.65 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166694600 |  | 100272326 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 119 TANGLEWOOD DR | 073 | FRA | 2023-02-24 | U126308 | U125763 | 2023-02-14 | 2023-12-29 |  |  | J ENSMINGER | 2023-02-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1957.77 | 0 | 0 | 0 | 1957.77 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166695000 |  | 100272324 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 123 TANGLEWOOD DR | 073 | FRA | 2023-02-24 | U126308 | U125763 | 2023-02-14 | 2023-12-29 |  |  | J ENSMINGER | 2023-02-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2122.28 | 0 | 0 | 0 | 2122.28 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168814300 |  | 100273593 |  | 6680224C |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | HAWKEEGAN | 121 HAWKEEGAN DR | 073 | FRA | 2023-02-24 | U128816 | U125208 | 2023-02-22 | 2023-03-31 | 2023-03-31 |  | OLIVER MAYNARD | 2023-02-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 1 | 3772.85 | 614.53 | 369.81 | 34.67 | 2753.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168814400 |  | 100273601 |  | 6680224C |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | HAWKEEGAN | 126 HAWKEEGAN DR | 073 | FRA | 2023-02-24 | U129731 | U125208 | 2023-02-22 | 2023-03-31 | 2023-03-31 |  | F.GOINS | 2023-02-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 9.5 | 1 | 3705.38 | 672.24 | 0 | 117.64 | 2915.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23168995300 |  | 100412209 |  | 6716208P |  |  |  | 565 | EX | LEAK REPAIR - S.L. D309408 | 2621P | LANSDOWNE | 3119 LANSDOWNE DR | 067 | LEX | 2023-02-24 | KKINDER | U132864 | 2023-02-23 | 2023-02-23 | 2023-02-23 |  | KKINDER | 2023-02-24 | 2023-02-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25.3167 | 5 | 1855.36 | 1493.78 | 215.68 | 84.3 | 61.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23169058700 |  | 100330194 |  | 6720212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311774 | 2621P | QUEENSWAY | 432 QUEENSWAY DR | 067 | LEX | 2023-03-01 | U125208 | U132864 | 2023-02-23 | 2022-12-16 | 2024-06-30 |  | HMCKUNE | 2023-02-24 | 2023-02-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 15.6667 | 5 | 2195.02 | 1660 | 441.34 | 93.68 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23169196700 |  | 100412615 |  | 6736232L |  |  |  | 565 | EX | REPLACE SERV/22-0262303-00 | 2621P | CURTIS | 211 CURTIS ST | 017 | PAR | 2023-02-24 | U126286 | BDAWES | 2023-02-24 | 2023-12-29 | 2023-12-31 |  | TYLER ALLISON | 2023-02-24 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 8 | 1 | 3937.89 | 546.27 | 0 | 30.84 | 3360.78 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 17569041900 |  | 500307958 |  | 7240216L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DOE RUN | 608 DOE RUN DR B | 173 | MT | 2023-02-27 | DENNING | U125765 | 2017-12-20 | 2018-11-27 |  |  | DENNING | 2023-02-27 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9.6333 | 2 | 752.91 | 712.67 | 0 | 40.24 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959958600 |  | 500175660 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | PATTERSON | 303 PATTERSON ST | 017 | PAR | 2023-02-27 | U127414 | U134723 | 2021-12-16 | 2023-07-31 |  |  | ED FOX | 2023-02-27 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 4.2 | 1 | 2883.58 | 286.47 | 0 | 51.39 | 2545.72 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960884300 |  | 100249844 |  | 7356248H | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | PADDLE CREEK | 8006 PADDLE CREEK RD | 019 | CAT | 2023-02-27 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH JERRY NEWSOME | 2023-02-27 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2038.64 | 0 | 0 | 0 | 2038.64 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964242600 |  | 500550425 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | MAPLE | 731 N MAPLE ST LIQUOR | 049 | WIN | 2023-03-02 | U126603 | U134723 | 2022-01-06 | 2023-07-31 |  |  | SHAWN DENNIS | 2023-02-27 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 5685.47 | 0 | 0 | 0 | 5685.47 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164757700 |  | 100281499 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | OAK | 505 OAK ST | 209 | GEO | 2023-02-27 | U126284 | U125763 | 2023-02-03 | 2023-12-29 |  |  | JOSH PASLEY/TEAM FISHEL | 2023-02-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 10 | 1 | 3797.05 | 741.93 | 0 | 499.46 | 2555.66 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166687600 |  | 100272378 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | COMMONWEALTH | 205 COMMONWEALTH BV | 073 | FRA | 2023-03-31 | U126308 | U125763 | 2023-02-14 | 2023-12-29 |  |  | J ENSMINGER | 2023-02-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1979.8 | 0 | 0 | 0 | 1979.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166694000 |  | 100272330 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 111 TANGLEWOOD DR | 073 | FRA | 2023-02-27 | U126308 | U125763 | 2023-02-14 | 2023-12-29 |  |  | J ENSMINGER | 2023-02-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1979.8 | 0 | 0 | 0 | 1979.8 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23168260100 |  | 100239487 |  | 7348264J |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | BELLEFONTE | 305 BELLEFONTE ST | 089 | RUS | 2023-02-27 | RECUMP | DYOUNG | 2023-02-20 | 2023-02-24 | 2023-03-13 |  | RECUMP | 2023-02-27 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.35 | 4 | 420.24 | 281.78 | 19.89 | 118.57 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23169411300 |  | 100301014 |  | 6716212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SAVOY | 208 SAVOY RD | 067 | LEX | 2023-02-27 | U930915 | U134902 | 2023-02-27 | 2022-11-03 | 2024-05-31 |  | MCRAIG | 2023-02-27 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.3 | 3 | 2390 | 860.85 | 359.46 | 382.99 | 786.7 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18588738800 |  | 500725550 | 17 | 6712232P | 0041677 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CHERRY BLOSSOM | 1470 CHERRY BLOSSOM WY PAINT | 209 | GEO | 2023-02-28 | DCOLLIN | CMCOX | 2018-02-20 | 2020-04-24 |  |  | DCOLLIN | 2023-02-28 | 2023-02-15 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 38.6 | 8 | 4436.3 | 2624.32 | 18.58 | 1004.53 | 788.87 | 0 | 0 | 0
KY | KY - WEST | 2623 | 20026952900 |  |  |  | 6688228I | 2072326 | GSULLI1 |  | 585 | EX | REPLACE ROOF | 2623M | MYRTLE | 298 MYRTLE AV | 073 | FRA | 2023-03-06 | U123258 | GSULLI1 | 2020-05-28 | 2023-12-28 | 2023-12-31 | 2023-02-28 | ALVARO PARKS | 2023-02-28 | 2023-01-25 |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00585 | 3200585 |  |  | WP9529 |  |  | 100 | 058532200269529 | 22.45 | 3 | 12246.18 | 1540.14 | 0 | 486.71 | 8285.42 | 0 | 6.22 | 1927.69
KY | KY - CENTRAL | 2629 | 21959958800 |  | 100439852 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | PATTERSON | 308 PATTERSON ST | 017 | PAR | 2023-02-28 | U127414 | U134723 | 2021-12-16 | 2023-07-31 |  |  | ED FOX | 2023-02-28 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 4 | 1 | 3977.18 | 351.74 | 0 | 53.42 | 3572.02 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959958900 |  | 500210618 |  | 6736232L | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | PATTERSON | 316 PATTERSON ST | 017 | PAR | 2023-02-28 | U127414 | U134723 | 2021-12-16 | 2023-07-31 |  |  | ED FOX | 2023-02-28 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 4 | 1 | 2859.28 | 272.82 | 0 | 48.96 | 2537.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129006800 |  | 100357229 |  | 7240280F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | WATER | 45 WATER ST | 023 | GER | 2023-02-28 | SDADAMS | U130722 | 2022-09-05 | 2022-12-30 |  |  | SDADAMS | 2023-02-28 | 2023-02-23 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 6.3 | 2 | 474.73 | 435.46 | 14.69 | 24.58 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964251100 |  | 500430807 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | MAPLE | 715 N MAPLE ST SHOP | 049 | WIN | 2023-03-02 | U126603 | U134723 | 2022-01-06 | 2023-07-31 |  |  | SHAWN DENNIS | 2023-02-28 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2231.88 | 0 | 0 | 0 | 2231.88 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026260000 |  |  |  | 7360216E | 2294088 | U461383 |  | 909 | EX | INSTALL ERX W/SUPER SOLAR | 2631M | RT 5 | 1271 RT 5 | 127 | LOU | 2023-03-22 | U123258 | U461383 | 2023-02-15 | 2023-12-01 | 2023-12-01 | 2023-02-28 | DASH | 2023-02-28 | 2023-02-28 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP2600 |  |  | 100 | 090932230262600 | 10.3667 | 0 | 3193.7 | 693.09 | 0 | 39.88 | 2460 | 0 | 0.73 | 0
KY | KY - EAST | 2631 | 23026260100 |  |  |  | 7360216E | 2294088 | U461383 |  | 584 | EX | RETIRE PAPER GAUGE | 2631M | RT 5 | 1271 RT 5 | 127 | LOU | 2023-03-22 | U123258 | U461383 | 2023-02-15 | 2023-12-01 | 2023-12-01 | 2023-02-28 | DASH | 2023-02-28 | 2023-02-28 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00584 | 3200584 |  |  | WP2601 |  |  | 100 | 058432230262601 | 3.5 | 0 | 257.79 | 244.02 | 0 | 13.77 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164553600 |  | 100313120 |  | 6716208B | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LAFAYETTE | 297 LAFAYETTE PY | 067 | LEX | 2023-03-01 | U128762 | U125763 | 2023-02-02 | 2023-12-29 |  |  | CORY TINCHER | 2023-02-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3161.45 | 0 | 0 | 0 | 3161.45 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164757500 |  | 100281497 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | OAK | 501 OAK ST | 209 | GEO | 2023-02-28 | U126284 | U125763 | 2023-02-03 | 2023-12-29 |  |  | JOSH PASLEY/TEAM FISHEL | 2023-02-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.0667 | 1 | 3276.76 | 374.64 | 0 | 252.23 | 2649.89 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164757600 |  | 100281562 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | OAK | 504 OAK ST | 209 | GEO | 2023-02-28 | U126284 | U125763 | 2023-02-03 | 2023-12-29 |  |  | JOSH PASLEY/TEAM FISHEL | 2023-02-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.9333 | 1 | 2627.59 | 367.2 | 0 | 247.24 | 2013.15 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165285700 |  | 100336929 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | M L KING | 436 M L KING BV 2F | 067 | LEX | 2023-02-28 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-02-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2747.41 | 0 | 0 | 0 | 2747.41 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23165692100 |  | 100279437 |  | 6692224A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE *RLA* | 2621P | SLICKAWAY | 330 SLICKAWAY RD | 073 | FRA | 2023-02-28 | U128816 | AOC SYST | 2023-02-08 | 2023-03-09 | 2023-04-08 |  | OLIVER MAYNARD | 2023-02-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.7167 | 1 | 3131.85 | 395.79 | 294.72 | 22.31 | 2419.03 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166693900 |  | 100272335 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 110 TANGLEWOOD DR | 073 | FRA | 2023-02-28 | U126308 | U125763 | 2023-02-14 | 2023-12-29 |  |  | J ENSMINGER | 2023-02-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1863.87 | 0 | 0 | 0 | 1863.87 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166694100 |  | 100272336 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 112 TANGLEWOOD DR | 073 | FRA | 2023-02-28 | U126308 | U125763 | 2023-02-14 | 2023-12-29 |  |  | J ENSMINGER | 2023-02-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2080.33 | 0 | 0 | 0 | 2080.33 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168160900 |  | 100283568 |  | 6712228A |  |  |  | 565 | EX | SERVICE LINE - REPLACE 2/28/23 | 2621P | PUEBLO | 612 PUEBLO TL | 209 | GEO | 2023-02-28 | DCOLLIN | U125208 | 2023-02-20 | 2023-02-28 | 2023-03-13 |  | DCOLLIN | 2023-02-28 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 14.1667 | 2 | 1376.81 | 861.51 | 375.49 | 139.81 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23168802800 |  | 100290178 |  | 6720212B | 2075272 |  |  | 565 | EX | RPLC SL/20026982700/ | 2621P | BLUE GRASS | 336 BLUE GRASS AV | 067 | LEX | 2023-03-31 | U128711 | U125208 | 2023-02-22 | 2023-02-27 | 2023-03-31 |  | LSTANFIELD | 2023-02-28 | 2023-02-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 20.7333 | 7 | 2226.23 | 1248.72 | 488.89 | 71.9 | 416.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23168803200 |  | 500340819 |  | 6720212B | 2075272 |  |  | 565 | EX | RPLC SL/20026982700/ | 2621P | BLUE GRASS | 338 BLUE GRASS AV | 067 | LEX | 2023-02-28 | LSTANFI | U125208 | 2023-02-22 | 2023-02-27 | 2023-03-31 |  | LSTANFI | 2023-02-28 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 1.35 | 2 | 970.01 | 181.5 | 109.64 | 57.61 | 621.26 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168812900 |  | 100457387 |  | 6680224E |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | VICKY | 170 VICKY WY | 073 | FRA | 2023-02-28 | U129731 | U125208 | 2023-02-22 | 2023-03-31 | 2023-03-31 |  | F.GOINS | 2023-02-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 9.9667 | 1 | 3055.58 | 704.06 | 0 | 39.72 | 2311.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168813700 |  | 100273592 |  | 6680224C |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | HAWKEEGAN | 111 HAWKEEGAN DR | 073 | FRA | 2023-02-28 | U128816 | U125208 | 2023-02-22 | 2023-03-31 | 2023-03-31 |  | OLIVER MAYNARD | 2023-02-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.2833 | 1 | 3106.04 | 483.91 | 439.86 | 27.31 | 2154.96 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23169608400 |  | 100443519 |  | 6680224E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2600B | VICKY | 163 VICKY WY | 073 | FRA | 2023-02-28 | U129731 | U125768 | 2023-02-28 | 2049-12-31 |  |  | F.GOINS | 2023-02-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.5333 | 1 | 1866.23 | 180.44 | 0 | 10.19 | 1675.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23169653800 |  | 500229438 |  | 6716208A |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309016 | 2621P | HARRODSBURG | 2001 HARRODSBURG RD | 067 | LEX | 2023-03-03 | U125208 | U129939 | 2023-02-28 | 2022-10-07 | 2024-04-30 |  | KKINDER | 2023-02-28 | 2023-02-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 30.7167 | 7 | 4714.46 | 2017.64 | 729.03 | 113.87 | 1853.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11937999700 |  | 500607400 |  | 6724208J | 0355907 |  |  | 566 | EX | PAPER ABANDON - IDLE/INACTIVE | 2621P | HELMSDALE | 3090 HELMSDALE PL STE 370 | 067 | LEX | 2023-03-01 | HMCKUNE | FJGLENN | 2011-12-15 | 2014-12-23 |  |  | HMCKUNE | 2023-03-01 | 2023-02-28 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.6 | 2 | 182.63 | 172.35 | 0 | 10.28 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22112527100 |  | 100284410 |  | 6764176M |  |  |  | 565 | EX | REPLACE SERVICE LINE - D305423 | 2621P | STACY LANE | 74 N STACY LANE RD | 065 | IRV | 2023-03-02 | U130722 | U125208 | 2022-06-27 | 2022-12-22 | 2024-06-30 |  | DENNING | 2023-03-01 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 14.7 | 3 | 1024.99 | 944.23 | 0 | 60.96 | 19.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22114600500 |  | 100319539 |  | 6716208L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311938 | 2600B | GREENBRIAR | 359 GREENBRIAR RD | 067 | LEX | 2023-03-01 | U461322 | U125208 | 2022-07-07 | 2023-01-06 | 2024-07-31 |  | STEVE CANOY | 2023-03-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9 | 1 | 5547.42 | 538.23 | 0 | 534.19 | 4475 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129006700 |  | 100433807 |  | 7240280F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | R1 KY 10 | 6226 R1 KY 10 | 023 | GER | 2023-03-01 | SDADAMS | U130722 | 2022-09-05 | 2022-12-30 |  |  | SDADAMS | 2023-03-01 | 2023-02-23 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 13.8333 | 3 | 1262.22 | 835.21 | 373.26 | 53.75 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964233800 |  | 100347800 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | HOLLY | 5 HOLLY AV | 049 | WIN | 2023-03-01 | U123111 | U134723 | 2022-01-06 | 2023-07-31 |  |  | LYN STAFFORD | 2023-03-01 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2736.31 | 0 | 0 | 0 | 2736.31 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964233900 |  | 100347799 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | HOLLY | 7 HOLLY AV | 049 | WIN | 2023-03-01 | U123111 | U134723 | 2022-01-06 | 2023-07-31 |  |  | LYN STAFFORD | 2023-03-01 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2837.85 | 0 | 0 | 0 | 2837.85 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026250700 |  |  |  | 6716208N | 2394960 | U461383 |  | 587 | EX | INSTALL EC 350 | 2600M | GOLD RUSH | 223 GOLD RUSH RD | 067 | LEX | 2023-03-06 | U123258 | U461383 | 2023-01-16 | 2023-09-29 | 2023-10-01 | 2023-03-01 | CCOX | 2023-03-01 | 2023-03-01 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00587 | 3200587 |  |  | WP2507 |  |  | 100 | 058732230262507 | 3.6667 | 2 | 5810.87 | 233.84 | 3521.9 | 15.1 | 1097.29 | 0 | 18.75 | 923.99
KY | KY - WEST | 2621 | 23026250800 |  |  |  | 6716208N | 2394960 | U461383 |  | 588 | EX | RETIRE PAPER BILLING CHART | 2600M | GOLD RUSH | 223 GOLD RUSH RD | 067 | LEX | 2023-03-06 | U123258 | U461383 | 2023-01-16 | 2023-09-29 | 2023-10-01 | 2023-03-01 | CCOX | 2023-03-01 | 2023-02-27 |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00588 | 3200588 |  |  | WP2508 |  |  | 100 | 058832230262508 | 7.7167 | 0 | 528.15 | 496.98 | 0 | 31.17 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026254200 |  |  |  | 7336276N | 2395179 | U461383 |  | 584 | EX | RETIRE RECORDING GAUGE | 2631M | LOCK | 220 LOCK LN | 089 | GRE | 2023-03-07 | U123258 | U461383 | 2023-01-25 | 2023-09-29 | 2023-10-01 | 2023-03-01 | SHANE GIORDANO | 2023-03-01 | 2023-03-01 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00584 | 3200584 |  |  | WP2542 |  |  | 100 | 058432230262542 | 0.88333 | 0 | 107.1 | 53.68 | 0 | 53.42 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23026256800 |  |  |  | 7256276D | 2395179 | U461383 |  | 584 | EX | RETIRE PAPER GAUGE | 2632M | HILL CITY | S HILL CITY RD | 161 | MAY | 2023-03-08 | U123258 | U461383 | 2023-02-13 | 2023-12-01 | 2023-12-01 | 2023-03-01 | JOSH MARTIN | 2023-03-01 | 2023-03-01 |  | F | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00584 | 3200584 |  |  | WP2568 |  |  | 100 | 058432230262568 | 0.7 | 0 | 43.28 | 40.65 | 0 | 2.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23158994900 |  | 100334166 |  | 6720212O |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | CLAYTON | 1620 CLAYTON AV | 067 | LEX | 2023-03-01 | TROE | U125208 | 2023-01-30 | 2023-02-02 |  |  | TROE | 2023-03-01 | 2023-01-31 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.95 | 4 | 1427.86 | 1023.45 | 308.48 | 66.23 | 29.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23158995200 |  | 100334177 |  | 6720212O |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | CLAYTON | 1625 CLAYTON AV | 067 | LEX | 2023-03-01 | LSTANFI | U125208 | 2023-01-30 | 2022-12-15 | 2024-06-30 |  | LSTANFI | 2023-03-01 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.2167 | 3 | 3369.27 | 1537.81 | 350.86 | 127.2 | 1353.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164549500 |  | 100313122 |  | 6716208B | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LAFAYETTE | 293 LAFAYETTE PY | 067 | LEX | 2023-03-01 | U124003 | U125763 | 2023-02-02 | 2023-12-29 |  |  | BPULLIAM/FISHEL | 2023-03-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3063.3 | 0 | 0 | 0 | 3063.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164551500 |  | 100313144 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LONE OAK | 535 LONE OAK DR | 067 | LEX | 2023-03-01 | U128762 | U125763 | 2023-02-02 | 2023-12-29 |  |  | CORY TINCHER | 2023-03-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3201.05 | 0 | 0 | 0 | 3201.05 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165286100 |  | 100336931 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | M L KING | 440 M L KING BV 1FFT | 067 | LEX | 2023-03-01 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-03-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2834.17 | 0 | 0 | 0 | 2834.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166451900 |  | 100410413 |  | 6720208M | 2395897 |  |  | 565 | EX | SERVICE LINE - PERMIT RDY 2/24 | 2621P | DOVE RUN | 1055 DOVE RUN RD | 067 | LEX | 2023-03-01 | DMARSTO | U125208 | 2023-02-13 | 2023-02-16 | 2023-03-03 |  | DMARSTO | 2023-03-01 | 2023-02-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 52.2667 | 10 | 7549.73 | 3121.46 | 233.26 | 177.29 | 4017.72 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166693700 |  | 100272334 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 106 TANGLEWOOD DR | 073 | FRA | 2023-03-01 | U126308 | U125763 | 2023-02-14 | 2023-12-29 |  |  | J ENSMINGER | 2023-03-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2375.44 | 0 | 0 | 0 | 2375.44 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166696500 |  | 100272303 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 215 TANGLEWOOD DR | 073 | FRA | 2023-03-01 | DCOLLIN | U125763 | 2023-02-14 | 2023-02-28 |  |  | DCOLLIN | 2023-03-01 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 35.25 | 3 | 4469.74 | 2011.32 | 294.43 | 656.59 | 1507.4 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23167921100 |  | 100244970 |  | 7356216D |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | POWHATAN | 315 S POWHATAN ST | 127 | LOU | 2023-03-01 | JCYRUS | U132002 | 2023-02-17 | 2023-03-03 | 2023-03-19 |  | JCYRUS | 2023-03-01 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 12.2833 | 2 | 995.01 | 765.42 | 19.89 | 209.7 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168814000 |  | 100273591 |  | 6680224G |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | HAWKEEGAN | 109 HAWKEEGAN DR | 073 | FRA | 2023-03-01 | U128816 | U125208 | 2023-02-22 | 2023-03-31 | 2023-03-31 |  | OLIVER MAYNARD | 2023-03-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 1 | 3258.59 | 524.63 | 337.5 | 33.87 | 2362.59 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23169000400 |  | 100290178 |  | 6720212B |  |  |  | 565 | VO | LOWERED SERV | 2621P | BLUE GRASS | 336 BLUE GRASS AV | 067 | LEX | 2023-03-07 |  | U132864 | 2023-02-23 | 2023-02-23 |  |  | LSTANFI | 2023-03-01 | 2023-02-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 0 | 3 | 0.01 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23169653900 |  | 100327278 |  | 6716212L |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | QUALITY | 10 QUALITY ST | 067 | LEX | 2023-03-02 | U461383 | U137585 | 2023-02-28 | 2023-02-27 | 2023-02-27 |  | TROE | 2023-03-01 | 2023-02-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 73.15 | 8 | 11108.34 | 4793.97 | 1538.69 | 267.94 | 4507.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 03533399000 |  | 100332287 |  | 16 | 2285539 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | WALTON | 229 WALTON AV 1F | 067 | LEX | 2023-03-03 | U126604 | DMCCULL | 2003-03-12 | 2021-05-25 | 2023-12-31 |  | WILL FULKS | 2023-03-02 | 2022-10-04 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.25 | 2 | 2160.48 | 313.26 | 0 | 278.9 | 1568.32 | 0 | 0 | 0
KY | KY - EAST | 2633 | 06640714800 |  | 100264520 | 70 | ADVISE |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CENTRAL | 909 CENTRAL AV | 195 | S W | 2023-03-02 | BPREECE | CESTEP | 2006-03-07 | 2020-12-31 |  |  | BPREECE | 2023-03-02 | 2023-02-01 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 42.35 | 7 | 6579.47 | 2698.68 | 0 | 168.51 | 3712.28 | 0 | 0 | 0
KY | KY - WEST | 2621 | 10872147100 |  | 100334651 |  | 6720208D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WILDERNESS | 597 WILDERNESS RD | 067 | LEX | 2023-03-03 | U125208 | U906609 | 2010-12-14 | 2017-03-31 |  |  | HMCKUNE | 2023-03-02 | 2023-03-01 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 17.5833 | 4 | 942.79 | 854.75 | 32.87 | 55.17 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21959957200 |  | 100359005 |  | 6740232I | 2292664 |  |  | 565 | EX | RPLC SL/22026230300 | 2600B | MARSHALL | 315 MARSHALL ST | 017 | PAR | 2023-03-02 | U127414 | U134723 | 2021-12-16 | 2023-07-31 |  |  | ED FOX | 2023-03-02 | 2023-03-01 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 8 | 1 | 2960.57 | 499.31 | 0 | 141.67 | 2319.59 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22126421100 |  | 100282872 |  | 6712228C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE *RLA* | 2623D | JACKSON | 612 E JACKSON ST | 209 | GEO | 2023-03-02 | U128816 | AOC SYST | 2022-08-24 | 2023-02-24 | 2023-12-31 |  | OLIVER MAYNARD | 2023-03-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 8 | 1 | 4078.45 | 524.63 | 412.87 | 33.87 | 3107.08 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964234000 |  | 100347798 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | HOLLY | 9 HOLLY AV | 049 | WIN | 2023-03-02 | U123111 | U134723 | 2022-01-06 | 2023-07-31 |  |  | LYN STAFFORD | 2023-03-02 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3222.83 | 0 | 0 | 0 | 3222.83 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026256600 |  |  |  | 6688228P | 2395179 | U461383 |  | 584 | EX | RETIRE PAPER GAUGE | 2623M | CAPITAL CENTER | 1024 CAPITAL CENTER DR | 073 | FRA | 2023-03-08 | U123258 | U461383 | 2023-02-13 | 2023-12-01 | 2023-12-01 | 2023-03-02 | WADE SHIMFESSEL | 2023-03-02 | 2023-03-02 |  | F | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00584 | 3200584 |  |  | WP2566 |  |  | 100 | 058432230262566 | 7.35 | 0 | 468 | 439.63 | 0 | 28.37 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026259800 |  |  |  | 7356216H | 2294088 | U461383 |  | 909 | EX | INSTALL ERX W/SUPER SOLAR | 2631M | JEFFERSON | JEFFERSON ST | 127 | LOU | 2023-03-21 | U123258 | U461383 | 2023-02-15 | 2023-12-01 | 2023-12-01 | 2023-03-02 | AMCORMICK | 2023-03-02 | 2023-02-24 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP2598 |  |  | 100 | 090932230262598 | 14.9833 | 0 | 3465.31 | 939.3 | 0 | 57.92 | 2460 | 0 | 8.09 | 0
KY | KY - EAST | 2631 | 23026259900 |  |  |  | 7356216H | 2294088 | U461383 |  | 584 | EX | RETIRE PAPER CHART | 2631M | JEFFERSON | JEFFERSON ST | 127 | LOU | 2023-03-21 | U123258 | U461383 | 2023-02-15 | 2023-12-01 | 2023-12-01 | 2023-03-02 | AMCORMICK | 2023-03-02 | 2023-03-02 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00584 | 3200584 |  |  | WP2599 |  |  | 100 | 058432230262599 | 4.4667 | 0 | 277.39 | 260.57 | 0 | 16.82 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164551100 |  | 100313142 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LONE OAK | 527 LONE OAK DR | 067 | LEX | 2023-03-02 | U128762 | U125763 | 2023-02-02 | 2023-12-29 |  |  | CORY TINCHER | 2023-03-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3226.29 | 0 | 0 | 0 | 3226.29 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164758700 |  | 100281556 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | OAK | 518 OAK ST | 209 | GEO | 2023-03-02 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-03-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.7833 | 1 | 3508.37 | 335.83 | 0 | 76.83 | 3095.71 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166694300 |  | 100272328 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 115 TANGLEWOOD DR | 073 | FRA | 2023-03-02 | U126308 | U125763 | 2023-02-14 | 2023-12-29 |  |  | J ENSMINGER | 2023-03-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2653.75 | 0 | 0 | 0 | 2653.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166707200 |  | 100309867 |  | 6712208H | 2184394 |  |  | 565 | EX | RPLC SL/22026223700 | 2600B | TUCSON | 2320 TUCSON DR | 067 | LEX | 2023-03-02 | U128410 | U125763 | 2023-02-14 | 2023-12-29 |  |  | CDESPAIN | 2023-03-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 2458.35 | 0 | 373.42 | 0 | 2084.93 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23170226700 |  | 100439213 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/21026140500 | 2600B | HOLLY | 10 HOLLY AV | 049 | WIN | 2023-03-02 | U123111 | U125763 | 2023-03-02 | 2023-12-29 |  |  | LYN STAFFORD | 2023-03-02 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3037.54 | 0 | 0 | 0 | 3037.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 08752722000 |  | 500192432 |  | 6716208M |  |  |  | 566 | EX | PAPER ABANDON/W100317136 | 2621P | STONE | 550 STONE RD INCIN | 067 | LEX | 2023-03-21 | U461383 | JTOY | 2008-10-06 | 2049-12-31 |  |  | KKINDER | 2023-03-03 | 2016-10-19 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.7667 | 4 | 626.13 | 588.06 | 0 | 38.07 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026158800 |  |  |  | 6720212J | 2285539 | U461383 |  | 557 | EX | INSTALL 540' OF 4"/8"PMMP MAIN | 2600B | WALTON | WALTON AV | 067 | LEX | 2023-03-20 | U124014 | U461383 | 2022-01-07 | 2023-11-21 | 2023-12-31 | 2023-02-13 | WILL FULKS | 2023-03-03 | 2023-01-03 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP1588 | AMRCB |  | 100 | 055732220261588 | 477.9833 | 29862 | 378932.24 | 33305.06 | 9752.6 | 5498.72 | 273969.46 | 0 | 1781.63 | 54624.77 | 553
KY | KY - WEST | 2621 | 22026158900 |  |  |  | 6720212J | 2285539 | U461383 |  | 558 | EX | RETIRE 594' OF 8"BSMP MAIN | 2600B | WALTON | WALTON AV | 067 | LEX | 2023-03-20 | U124014 | U461383 | 2022-01-07 | 2023-12-29 | 2023-12-31 | 2023-02-13 | WILL FULKS | 2023-03-03 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP1589 | AMRCB |  | 100 | 055832220261589 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129030300 |  | 100241736 |  | 7356252D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WINCHESTER | 5216 WINCHESTER AV | 019 | ASH | 2023-03-06 | U125208 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JCYRUS | 2023-03-03 | 2023-02-08 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 7.7333 | 4 | 856.56 | 665.5 | 41.57 | 149.49 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22150547100 |  | 100414574 |  | 6740228A |  |  |  | 565 | EX | REPLACE SERVICE LINE - D304835 | 2621P | VINE | 1152 VINE ST | 017 | PAR | 2023-03-11 | U930915 | U125208 | 2022-12-27 | 2023-06-20 | 2024-12-31 |  | NRICHIE | 2023-03-03 | 2023-02-28 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 79.0167 | 10 | 8009.67 | 4863.72 | 264.31 | 572.6 | 2309.04 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026249100 |  | 501340288 |  | 7348244L | 2394775 | U132280 |  | 555 | EX | INSTALL 100'-2" PMMP | 2621P | RICHLAND | 15514 RICHLAND CT | 019 | CAT | 2023-03-24 | U136251 | U132280 | 2023-01-12 | 2023-01-26 | 2023-03-27 | 2023-02-28 | MCOLLET | 2023-03-03 | 2023-02-14 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP2491 |  |  | 100 | 055532230262491 | 74.3833 | 1664 | 13611.51 | 4863.15 | 0 | 5144.74 | 1395.76 | 0 | 20.47 | 2187.39 | 128
KY | KY - EAST | 2631 | 23026262200 |  |  |  | 7348248F | 2395693 | U132280 |  | 557 | EX | EMER - INSTALL 4'-2" PMMP | 2621P | US 60 | US 60 | 019 | ASH | 2023-05-05 | U136251 | U132280 | 2023-02-20 |  | 2049-12-31 | 2023-02-21 | BROBERT | 2023-03-03 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP2622 |  |  | 100 | 055732230262622 | 1.0833 | 4 | 15777.13 | 7059.39 | 1820.11 | 2955.71 | 1332.12 | 0 | 0 | 2609.8 | 4
KY | KY - EAST | 2631 | 23026262300 |  |  |  | 7348248F | 2395693 | U132280 |  | 558 | EX | EMER - RETIRE 4'-2" PMMP | 2621P | US 60 | US 60 | 019 | ASH | 2023-05-02 | U136251 | U132280 | 2023-02-20 |  | 2049-12-31 | 2023-02-21 | BROBERT | 2023-03-03 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP2623 |  |  | 100 | 055832230262623 | 1.9833 | 0 | 242.84 | 123.86 | 0 | 118.98 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883062400 |  | 100247770 |  | 7364188A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | MAIN | 117 E MAIN ST | 159 | INE | 2023-03-07 | U125208 | U120245 | 2021-01-30 | 2020-08-14 |  |  | JAHOWARD | 2023-03-06 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 20.3833 | 3 | 1483.31 | 1244 | 159 | 80.31 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22112527400 |  | 100284381 |  | 6764176N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D305424 | 2621P | CEDAR GROVE | 290 W CEDAR GROVE RD | 065 | IRV | 2023-03-07 | U125208 | U125208 | 2022-06-27 | 2022-12-22 | 2024-06-30 |  | DENNING | 2023-03-06 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 15.95 | 3 | 1457.39 | 1185.24 | 146.11 | 76.54 | 49.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22127381300 |  | 100286191 |  | 6764172G |  |  |  | 565 | EX | REPLACE SERVICE LINE - D247722 | 2621P | LINCOLN | 195 LINCOLN AV | 065 | IRV | 2023-03-07 | U125208 | U125208 | 2022-08-29 | 2023-02-27 | 2024-08-31 |  | DENNING | 2023-03-06 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 11.4 | 3 | 855.93 | 738.15 | 38.2 | 47.68 | 31.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129046100 |  | 100314593 |  | 6716212L | 0148638 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HIGH | 102 W HIGH ST 1F | 067 | LEX | 2023-03-06 | JOCHOA | U130722 | 2022-09-05 | 2022-12-30 |  |  | JOCHOA | 2023-03-06 | 2022-09-27 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 40.9667 | 17 | 3463.34 | 2216.42 | 34.39 | 151.72 | 1060.81 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964234300 |  | 100347760 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | HOLLY | 26 HOLLY AV | 049 | WIN | 2023-03-06 | U126602 | U134723 | 2022-01-06 | 2023-07-31 |  |  | DEREL PAYTON | 2023-03-06 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3542.45 | 0 | 0 | 0 | 3542.45 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026251700 |  | 501342456 |  | 6716220M | 2394864 | U134275 |  | 555 | EX | INSTALL 2060' OF 2" PMMP | 2600B | MARLENA | MARLENA LN LT92 | 067 | LEX | 2023-05-06 | U128132 | U134275 | 2023-01-18 | 2023-03-29 | 2023-04-15 | 2023-03-16 | R.HUMPHREYS | 2023-03-06 | 2023-02-02 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2517 |  |  | 100 | 055532230262517 | 129 | 40368 | 65881.72 | 7777.86 | 5054.23 | 1611.17 | 40812.09 | 0 | 176.22 | 10450.15 | 2523
KY | KY - WEST | 2621 | 23026260700 |  |  |  | 6716208L | 2294088 | U461383 |  | 909 | EX | INSTALL ERX W/SUPER SOLAR | 2600E | REBECCA | 881 REBECCA DR | 067 | LEX | 2023-03-20 | U123258 | U461383 | 2023-02-16 | 2023-12-01 | 2023-12-01 | 2023-03-06 | SMCHOLAN | 2023-03-06 | 2023-03-06 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP2607 |  |  | 100 | 090932230262607 | 14.35 | 0 | 3972.47 | 903.56 | 0 | 601.96 | 2460 | 0 | 6.95 | 0
KY | KY - WEST | 2621 | 23026260800 |  |  |  | 6716208L | 2294088 | U461383 |  | 584 | EX | RETIRE PAPER CHART | 2621M | REBECCA | 881 REBECCA DR | 067 | LEX | 2023-03-20 | U123258 | U461383 | 2023-02-16 | 2023-12-01 | 2023-12-01 | 2023-03-06 | SMCHOLAN | 2023-03-06 | 2023-03-06 |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00584 | 3200584 |  |  | WP2608 |  |  | 100 | 058432230262608 | 0.65 | 0 | 78.59 | 39.94 | 0 | 38.65 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164548900 |  | 100313135 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LAFAYETTE | 271 LAFAYETTE PY | 067 | LEX | 2023-03-07 | U128762 | U125763 | 2023-02-02 | 2023-12-29 |  |  | CORY TINCHER | 2023-03-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3168.74 | 0 | 0 | 0 | 3168.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164549800 |  | 100313154 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LONE OAK | 502 LONE OAK DR | 067 | LEX | 2023-03-07 | U128762 | U125763 | 2023-02-02 | 2023-12-29 |  |  | CORY TINCHER | 2023-03-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2300.38 | 0 | 0 | 0 | 2300.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164550100 |  | 100313153 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LONE OAK | 506 LONE OAK DR | 067 | LEX | 2023-03-06 | U124003 | U125763 | 2023-02-02 | 2023-12-29 |  |  | BPULLIAM/FISHEL | 2023-03-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2898.36 | 0 | 0 | 0 | 2898.36 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164719100 |  | 100420852 |  | 6692228A |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | SCRUGGS | 315 N SCRUGGS LN | 073 | FRA | 2023-03-07 | U130722 | U133234 | 2023-02-03 | 2023-02-17 | 2023-03-05 |  | BWHITE | 2023-03-06 | 2023-02-16 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 21.2167 | 5 | 1313.82 | 1236.12 | 0 | 77.7 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164758300 |  | 100281558 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | OAK | 514 OAK ST | 209 | GEO | 2023-03-06 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-03-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2008.29 | 0 | 0 | 0 | 2008.29 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166694400 |  | 100272345 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 116 TANGLEWOOD DR | 073 | FRA | 2023-03-06 | U126308 | U125763 | 2023-02-14 | 2023-12-29 |  |  | J ENSMINGER | 2023-03-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2693.65 | 0 | 0 | 0 | 2693.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23168781300 |  | 100288744 |  | 6720212D |  |  |  | 566 | EX | ABANDON SL - DEMO/LNDMK | 2621P | HI CREST | 639 HI CREST DR | 067 | LEX | 2023-03-06 | LSTANFI | U125208 | 2023-02-22 | 2023-02-24 | 2023-03-22 |  | LSTANFI | 2023-03-06 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.7667 | 3 | 1010.27 | 604.77 | 254.35 | 151.15 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23168956400 |  | 100247771 |  | 7364188A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 123 E MAIN ST | 159 | INE | 2023-03-06 | JAHOWARD | U125208 | 2023-02-23 | 2023-03-16 | 2023-03-16 |  | JAHOWARD | 2023-03-06 | 2023-02-28 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.1 | 2 | 207.36 | 194.93 | 0 | 12.43 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23171915100 |  | 100347794 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | HOLLY | 29 HOLLY AV | 049 | WIN | 2023-03-06 | U126602 | U125763 | 2023-03-06 | 2023-12-29 |  |  | DEREK PAYTON | 2023-03-06 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3283.77 | 0 | 0 | 0 | 3283.77 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23171927300 |  | 500128185 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | KENTON | 463 KENTON ST | 067 | LEX | 2023-03-06 | U126532 | U125763 | 2023-03-06 | 2023-12-29 |  |  | LESLIE SHARON | 2023-03-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2496.48 | 0 | 0 | 0 | 2496.48 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23171956300 |  | 100404658 |  | 6700208D |  |  |  | 565 | EX | LEAK REPAIR - SERVICE D308934 | 2621P | BAYBERRY | 171 BAYBERRY RD | 239 | VER | 2023-03-07 | U125208 | U129939 | 2023-03-06 | 2023-03-06 | 2023-03-06 |  | CHERNDO | 2023-03-06 | 2023-03-06 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 16.1167 | 3 | 1554.74 | 1184.36 | 177.32 | 76.46 | 116.6 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19730229000 |  | 100344444 |  | 6700224L |  | U125208 |  | 565 | EX | SERVICE LINE - REPLACE * RLA | 2621P | MIDWAY | 5745 MIDWAY RD | 239 | MID | 2023-03-08 | U128816 | U125208 | 2019-08-05 | 2019-08-09 | 2019-08-23 |  | OLIVER MAYNARD | 2023-03-07 | 2022-09-27 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 47.5833 | 8 | 22795.83 | 3060.05 | 1681.14 | 874.17 | 17180.47 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22120755800 |  | 100284451 |  | 6764176N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D253717 | 2621P | RIVERVIEW | 20 RIVERVIEW RD | 065 | IRV | 2023-03-09 | U125208 | U125208 | 2022-08-02 | 2023-02-02 | 2024-08-31 |  | DENNING | 2023-03-07 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 18 | 3 | 1565.26 | 1152.56 | 255.85 | 74.35 | 82.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129122700 |  | 100443606 |  | 6716212L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | VINE | 262 E VINE ST | 067 | LEX | 2023-03-09 | U125208 | U125208 | 2022-09-06 | 2022-12-30 |  |  | JOCHOA | 2023-03-07 | 2022-10-10 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 29.3167 | 13 | 2436.17 | 1580.09 | 14.69 | 111.26 | 730.13 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964234100 |  | 100347758 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | HOLLY | 14 HOLLY AV | 049 | WIN | 2023-03-08 | U126602 | U134723 | 2022-01-06 | 2023-07-31 |  |  | DEREK PAYTON | 2023-03-07 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2990.72 | 0 | 0 | 0 | 2990.72 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026259600 |  |  |  | 6696216L | 2294088 | U461383 |  | 909 | EX | INSTALL ERX AND SUPER SOLAR | 2623M | MIDWAY | 1625 MIDWAY RD | 239 | VER | 2023-07-17 | U123258 | U461383 | 2023-02-15 | 2023-12-01 | 2023-12-01 | 2023-03-07 | BRANDON LONE | 2023-03-07 | 2023-03-07 |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00909 | 3200909 |  |  | WP2596 |  |  | 100 | 090932230262596 | 18.1833 | 0 | 3652.44 | 1115.36 | 0 | 70.24 | 2460 | 0 | 6.84 | 0
KY | KY - WEST | 2623 | 23026259700 |  |  |  | 6696216L | 2294088 | U461383 |  | 584 | EX | RETIRE PAPER CHART | 2623M | US 62 AT LANES END FRM | US 62 AT LANES END FRM | 239 | VER | 2023-03-16 | U123258 | U461383 | 2023-02-15 | 2023-12-01 | 2023-12-01 | 2023-03-07 | BRANDON LONE | 2023-03-07 | 2023-03-03 |  | F | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00584 | 3200584 |  |  | WP2597 |  |  | 100 | 058432230262597 | 4.1667 | 0 | 269.78 | 253.41 | 0 | 16.37 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026262700 |  |  |  | 6712208M | 2395746 | U461383 |  | 557 | EX | EMER-INSTALL 5' OF 2"PMMP MAIN | 2621P | PALOMAR COVE | 3905 PALOMAR COVE LN | 067 | LEX | 2023-03-28 | U121331 | U461383 | 2023-02-21 | 2023-03-07 | 2024-05-19 | 2023-02-23 | KKINDER | 2023-03-07 | 2023-02-22 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2627 |  |  | 100 | 055732230262627 | 22.8333 | 25 | 3582.24 | 1399.43 | 125.14 | 79.33 | 1397.45 | 0 | 4.16 | 576.73 | 5
KY | KY - WEST | 2621 | 23026262800 |  |  |  | 6712208M | 2395746 | U461383 |  | 558 | EX | EMER-RETIRE 5' OF 2"PMP MAIN | 2621P | PALOMAR COVE | 3905 PALOMAR COVE LN | 067 | LEX | 2023-03-14 | U121331 | U461383 | 2023-02-21 | 2023-03-07 | 2024-05-19 | 2023-02-23 | KKINDER | 2023-03-07 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2628 |  |  | 100 | 055832230262628 | 0.95 | 0 | 726.04 | 686.79 | 0 | 39.25 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164549900 |  | 100313136 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LONE OAK | 503 LONE OAK DR | 067 | LEX | 2023-03-08 | U128762 | U125763 | 2023-02-02 | 2023-12-29 |  |  | CORY TINCHER | 2023-03-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3084.57 | 0 | 0 | 0 | 3084.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164550800 |  | 100313149 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LONE OAK | 522 LONE OAK DR | 067 | LEX | 2023-03-07 | U124003 | U125763 | 2023-02-02 | 2023-12-29 |  |  | BPULLIAM/FISHEL | 2023-03-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3159.9 | 0 | 0 | 0 | 3159.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164693000 |  | 100310507 |  | 6712208L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D305594 | 2621P | SEATTLE | 634 SEATTLE DR | 067 | LEX | 2023-03-09 | U125208 | U125208 | 2023-02-03 | 2023-08-02 | 2025-02-28 |  | KKINDER | 2023-03-07 | 2023-03-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.2 | 3 | 1717.21 | 1032.28 | 509.39 | 66.64 | 108.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164758500 |  | 100281557 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | OAK | 516 OAK ST | 209 | GEO | 2023-03-07 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-03-07 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.16667 | 1 | 2034.98 | 9.86 | 0 | 2.25 | 2022.87 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164758900 |  | 100281555 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | OAK | 520 OAK ST | 209 | GEO | 2023-03-07 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-03-07 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.6333 | 1 | 2255.31 | 210.2 | 0 | 48.1 | 1997.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165281800 |  | 100294934 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | KENTON | 434 KENTON ST | 067 | LEX | 2023-03-07 | U126284 | U125763 | 2023-02-07 | 2023-12-29 |  |  | JOSH PASLEY/TEAM FISHEL | 2023-03-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12 | 1 | 5182.6 | 733.05 | 0 | 713.25 | 3736.3 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166694500 |  | 100272346 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 118 TANGLEWOOD DR | 073 | FRA | 2023-03-07 | U126308 | U125763 | 2023-02-14 | 2023-12-29 |  |  | J ENSMINGER | 2023-03-07 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2475.25 | 0 | 0 | 0 | 2475.25 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166695200 |  | 100272322 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 127 TANGLEWOOD DR | 073 | FRA | 2023-03-07 | U126308 | U125763 | 2023-02-14 | 2023-12-29 |  |  | J ENSMINGER | 2023-03-07 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2344.79 | 0 | 0 | 0 | 2344.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166720600 |  | 100330624 |  | 6720212O |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HENRY CLAY | 445 HENRY CLAY BV | 067 | LEX | 2023-03-09 | U125208 | U132761 | 2023-02-14 | 2023-12-29 |  |  | HMCKUNE | 2023-03-07 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 31.0333 | 4 | 1894.64 | 1503.94 | 251.82 | 97.08 | 41.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23168489300 |  | 100299892 |  | 6716212B |  |  |  | 566 | EX | ABANDON - DEMO/PERMIT RDY 3/6 | 2621P | CLYDE | 116 CLYDE ST 1F | 067 | LEX | 2023-03-07 | MCRAIG | U133234 | 2023-02-21 | 2023-03-07 | 2023-03-27 |  | MCRAIG | 2023-03-07 | 2023-03-07 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.25 | 3 | 436.22 | 377.44 | 34.39 | 24.39 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23171899000 |  | 100360655 |  | 6736228G |  |  |  | 565 | EX | EMR SERVICE LINE - REPLACE | 2621P | DOBBIN | 514 DOBBIN DR | 017 | PAR | 2023-03-07 | NRICHIE | U125208 | 2023-03-06 | 2023-03-06 |  |  | NRICHIE | 2023-03-07 | 2023-03-06 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 17.25 | 6 | 1830.25 | 1121.91 | 305.91 | 380.43 | 22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23172182700 |  | 100326401 |  | 6720208A |  |  |  | 565 | EX | SERVICE REPLACE & RELOC MTR | 2621P | CHENAULT | 224 CHENAULT RD | 067 | LEX | 2023-03-07 | MCRAIG | U125208 | 2023-03-07 | 2023-03-07 | 2023-03-10 |  | MCRAIG | 2023-03-07 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 10.9 | 3 | 1258.45 | 608.56 | 200.71 | 325.98 | 123.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964234200 |  | 100347759 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | HOLLY | 20 HOLLY AV | 049 | WIN | 2023-03-08 | U126602 | U134723 | 2022-01-06 | 2023-07-31 |  |  | DEREK PAYTON | 2023-03-08 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2908.85 | 0 | 0 | 0 | 2908.85 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23154351200 |  | 100418181 |  | 6720208J |  |  |  | 565 | EX | REPLACE SERVICE LINE - D000296 | 2621P | BRIDGEPORT | 2043 BRIDGEPORT DR | 067 | LEX | 2023-03-09 | U930915 | U125208 | 2023-01-10 | 2023-01-31 | 2025-01-31 |  | RJCRAWF | 2023-03-08 | 2023-01-31 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 22.4 | 5 | 1911.89 | 1308.44 | 385.23 | 85.12 | 133.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164550200 |  | 100313152 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LONE OAK | 510 LONE OAK DR | 067 | LEX | 2023-03-09 | U128762 | U125763 | 2023-02-02 | 2023-03-30 |  |  | CORY TINCHER | 2023-03-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2048.82 | 0 | 0 | 0 | 2048.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164550300 |  | 100313138 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LONE OAK | 511 LONE OAK DR | 067 | LEX | 2023-03-09 | U128762 | U125763 | 2023-02-02 | 2023-12-29 |  |  | CORY TINCHER | 2023-03-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2324.83 | 0 | 0 | 0 | 2324.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164550900 |  | 100313141 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LONE OAK | 523 LONE OAK DR | 067 | LEX | 2023-03-09 | U128762 | U125763 | 2023-02-02 | 2023-03-30 |  |  | CORY TINCHER | 2023-03-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1970.9 | 0 | 0 | 0 | 1970.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164754300 |  | 100281462 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | GANO | 123 GANO AV | 209 | GEO | 2023-03-08 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-03-08 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.25 | 1 | 2038.52 | 75.31 | 0 | 17.23 | 1945.98 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165083800 |  | 100405719 |  | 6720216F | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE SERVICE | 2621D | PENNEBAKER | 1061 PENNEBAKER DR | 067 | LEX | 2023-03-09 | U125208 | AOC SYST | 2023-02-06 | 2023-03-03 | 2023-04-02 |  | LSTONE | 2023-03-08 | 2023-02-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.8167 | 6 | 1592.02 | 1342.32 | 59.02 | 85.08 | 105.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165281900 |  | 100294960 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | KENTON | 461 KENTON ST | 067 | LEX | 2023-03-08 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-03-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2186.33 | 0 | 0 | 0 | 2186.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165290100 |  | 100294961 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | KENTON | 457 KENTON ST | 067 | LEX | 2023-03-08 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-03-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 26792.05 | 0 | 24135.11 | 0 | 2656.94 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166694200 |  | 100272329 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 113 TANGLEWOOD DR | 073 | FRA | 2023-03-08 | U126308 | U125763 | 2023-02-14 | 2023-12-29 |  |  | J ENSMINGER | 2023-03-08 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2207.22 | 0 | 0 | 0 | 2207.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23172546600 |  | 100325550 |  | 6720208E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LAKEWOOD | 1185 LAKEWOOD DR | 067 | LEX | 2023-03-09 | U129722 | U129939 | 2023-03-08 | 2023-02-23 | 2024-08-31 |  | M YOUNG | 2023-03-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26210022 | 8 | 1 | 4371.43 | 455.8 | 343.22 | 29.43 | 3542.98 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23172552300 |  | 100301389 |  | 6712212H |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SUTTON | 225 SUTTON PL | 067 | LEX | 2023-03-08 | MCRAIG | U129939 | 2023-03-08 | 2022-11-17 | 2024-05-31 |  | MCRAIG | 2023-03-08 | 2023-02-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.7167 | 10 | 2397.72 | 1191.84 | 452.48 | 650 | 103.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11888220700 |  | 100424404 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LIMESTONE | 760 N LIMESTONE ST RR | 067 | LEX | 2023-03-10 | U125208 | U906307 | 2011-02-14 | 2020-12-31 |  |  | LSTANFI | 2023-03-09 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.7 | 0 | 237.99 | 197.64 | 0 | 40.35 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22123733100 |  | 100340756 |  | 6736180C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D246260 | 2621P | DEE DEE | 1219 DEE DEE DR | 151 | RIC | 2023-03-16 | JTOY | U125208 | 2022-08-12 | 2023-02-10 | 2024-08-31 |  | DENNING | 2023-03-09 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 18.25 | 3 | 1335.51 | 1169.77 | 0 | 75.54 | 90.2 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129042100 |  | 100250663 |  | 7376184A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WOLF CREEK | 6818 N WOLF CREEK RD | 159 | LOV | 2023-03-10 | U125208 | U130722 | 2022-09-05 | 2023-03-07 |  |  | JCKIRK | 2023-03-09 | 2023-03-09 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 21.45 | 3 | 2225.37 | 1334.53 | 0 | 890.84 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129043700 |  | 500629466 |  | 6716208M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SEVERN | 460 SEVERN WY | 067 | LEX | 2023-03-09 | JOCHOA | U130722 | 2022-09-05 | 2022-12-30 |  |  | JOCHOA | 2023-03-09 | 2023-02-27 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.3833 | 7 | 994.31 | 847.02 | 34.39 | 112.9 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964250700 |  | 100347750 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | MAIN | 302 N MAIN ST | 049 | WIN | 2023-03-09 | U126602 | U134723 | 2022-01-06 | 2023-07-31 |  |  | DEREK PAYTON | 2023-03-09 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 0.85 | 1 | 6402.55 | 48.2 | 0 | 3.11 | 6351.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23152819100 |  | 100304791 |  | 6712212P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311129 | 2621P | APPOMATTOX | 1744 APPOMATTOX RD | 067 | LEX | 2023-03-09 | KKINDER | U125208 | 2023-01-03 | 2023-06-30 | 2024-12-31 |  | KKINDER | 2023-03-09 | 2023-03-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 32.3 | 4 | 1916.91 | 1720.03 | 0 | 111.08 | 85.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23156390900 |  | 501194182 |  | 6712204B | 1637431 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KINGS GLEN | 3741 KINGS GLEN PR | 067 | LEX | 2023-03-10 | U930915 | MDULANE | 2023-01-16 | 2023-07-19 | 2023-07-19 |  | JGILES | 2023-03-09 | 2023-02-28 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.3333 | 8 | 789.9 | 598.69 | 34.39 | 156.82 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164550000 |  | 100313137 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LONE OAK | 505 LONE OAK DR | 067 | LEX | 2023-03-10 | U128762 | U125763 | 2023-02-02 | 2023-12-29 |  |  | CORY TINCHER | 2023-03-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4046.66 | 0 | 0 | 0 | 4046.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164551000 |  | 100313148 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LONE OAK | 526 LONE OAK DR | 067 | LEX | 2023-03-10 | U128762 | U125763 | 2023-02-02 | 2023-12-29 |  |  | CORY TINCHER | 2023-03-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3262 | 0 | 0 | 0 | 3262 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164759200 |  | 100281552 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | OAK | 524 OAK ST | 209 | GEO | 2023-03-09 | U126284 | U125763 | 2023-02-03 | 2023-12-29 |  |  | JOSH PASLEY/TEAM FISHEL | 2023-03-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.1 | 1 | 3105.2 | 311.56 | 0 | 303.14 | 2490.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164759300 |  | 100281528 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | OAK | 525 OAK ST | 209 | GEO | 2023-03-09 | U126284 | U125763 | 2023-02-03 | 2023-12-29 |  |  | JOSH PASLEY/TEAM FISHEL | 2023-03-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.9 | 1 | 2631.32 | 177.15 | 0 | 172.36 | 2281.81 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165290000 |  | 100294962 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | KENTON | 453 KENTON ST | 067 | LEX | 2023-03-09 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-03-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2669.49 | 0 | 0 | 0 | 2669.49 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166694800 |  | 100272325 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 121 TANGLEWOOD DR | 073 | FRA | 2023-03-09 | U126308 | U125763 | 2023-02-14 | 2023-12-29 |  |  | J ENSMINGER | 2023-03-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 4869.37 | 0 | 0 | 0 | 4869.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166706000 |  | 100309871 |  | 6712208H | 2184394 |  |  | 565 | EX | RPLC SL/22026223700 | 2600B | TUCSON | 2280 TUCSON DR | 067 | LEX | 2023-03-10 | U128410 | U125763 | 2023-02-14 | 2023-12-29 |  |  | CDESPAIN | 2023-03-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 1633.83 | 0 | 0 | 0 | 1633.83 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23169643700 |  | 100348996 |  | 6748208M |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | BROADWAY | 127 E BROADWAY ST | 049 | WIN | 2023-03-09 | NRICHIE | U133234 | 2023-02-28 | 2023-03-14 | 2023-03-30 |  | NRICHIE | 2023-03-09 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 11.2 | 3 | 1334.22 | 727.82 | 116.45 | 152.45 | 337.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23172599100 |  | 100294499 |  | 6716212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303243 | 2621P | UPPER | 559 N UPPER ST | 067 | LEX | 2023-03-10 | U125208 | U129939 | 2023-03-08 | 2023-03-01 | 2024-09-30 |  | LSTANFI | 2023-03-09 | 2023-03-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 24.1667 | 9 | 3367.48 | 2101.47 | 226.56 | 144.7 | 894.75 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23172825400 |  | 100274958 |  | 6684228J |  | U129939 |  | 565 | EX | LEAK REPAIR - S.L. - D304481 | 2621P | MAIN | 201 W MAIN ST 1FE | 073 | FRA | 2023-03-10 | U125208 | U129939 | 2023-03-09 | 2023-03-09 | 2023-03-09 |  | BSEXTON | 2023-03-09 | 2023-03-09 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 15.9333 | 3 | 1377.86 | 858.54 | 258.48 | 55.44 | 205.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 95235724100 |  | 100459317 |  | 600000000 |  |  |  | 566 | EX | METER ABANDON ONLY | 2621P | WESTLAND | 790 WESTLAND DR RR | 067 | LEX | 2023-03-09 | MCRAIG | MNBEINK | 1995-11-20 | 2020-12-31 |  |  | MCRAIG | 2023-03-09 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.8 | 2 | 391.74 | 251.93 | 4.77 | 135.04 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12959635500 |  | 100453128 |  | 16720208G |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LAKESHORE | 209 LAKESHORE DR 1 | 067 | LEX | 2023-03-10 | JOCHOA | U125208 | 2012-03-09 | 2020-12-31 |  |  | JOCHOA | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.35 | 2 | 91.46 | 85.93 | 0 | 5.53 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12959635800 |  | 100453129 |  | 16720208G |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LAKESHORE | 209 LAKESHORE DR 3 | 067 | LEX | 2023-03-10 | JGILES | U125208 | 2012-03-09 | 2020-12-31 |  |  | JGILES | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.3667 | 1 | 56.74 | 53.3 | 0 | 3.44 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12959635900 |  | 100453130 |  | 16720208G |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LAKESHORE | 209 LAKESHORE DR 4 | 067 | LEX | 2023-03-10 | JOCHOA | U125208 | 2012-03-09 | 2020-12-31 |  |  | JOCHOA | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.16667 | 1 | 11.66 | 10.96 | 0 | 0.7 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12959636300 |  | 100453132 |  | 16720208G |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LAKESHORE | 209 LAKESHORE DR 13 | 067 | LEX | 2023-03-10 | JOCHOA | U125208 | 2012-03-09 | 2020-12-31 |  |  | JOCHOA | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.2333 | 1 | 156.56 | 147.07 | 0 | 9.49 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12959636400 |  | 100453133 |  | 16720208G |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LAKESHORE | 209 LAKESHORE DR 6 | 067 | LEX | 2023-03-10 | JGILES | U125208 | 2012-03-09 | 2020-12-31 |  |  | JGILES | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.18333 | 1 | 7.48 | 7.02 | 0 | 0.46 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12959636500 |  | 100453136 |  | 16720208G |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LAKESHORE | 209 LAKESHORE DR 8 | 067 | LEX | 2023-03-10 | JGILES | U125208 | 2012-03-09 | 2020-12-31 |  |  | JGILES | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.16667 | 1 | 7.05 | 6.62 | 0 | 0.43 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12959636600 |  | 100453137 |  | 16720208G |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LAKESHORE | 209 LAKESHORE DR 9 | 067 | LEX | 2023-03-10 | JOCHOA | U125208 | 2012-03-09 | 2020-12-31 |  |  | JOCHOA | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.2333 | 1 | 84.48 | 79.36 | 0 | 5.12 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12959636700 |  | 100453138 |  | 16720208G |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LAKESHORE | 209 LAKESHORE DR 10 | 067 | LEX | 2023-03-10 | JGILES | U125208 | 2012-03-09 | 2020-12-31 |  |  | JGILES | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.45 | 1 | 18.65 | 17.52 | 0 | 1.13 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12959636800 |  | 100453139 |  | 16720208G |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LAKESHORE | 209 LAKESHORE DR 11 | 067 | LEX | 2023-03-10 | JGILES | U125208 | 2012-03-09 | 2020-12-31 |  |  | JGILES | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.3333 | 1 | 138.74 | 130.33 | 0 | 8.41 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12959636900 |  | 100453140 |  | 16720208G |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LAKESHORE | 209 LAKESHORE DR 12 | 067 | LEX | 2023-03-10 | JOCHOA | U125208 | 2012-03-09 | 2020-12-31 |  |  | JOCHOA | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.5 | 1 | 34.35 | 32.27 | 0 | 2.08 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12959637000 |  | 100453182 |  | 16720208G |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LAKESHORE | 209 LAKESHORE DR 2 | 067 | LEX | 2023-03-10 | KOBRYAN | U125208 | 2012-03-09 | 2020-12-31 |  |  | KOBRYAN | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.4833 | 1 | 90.47 | 84.98 | 0 | 5.49 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12959637300 |  | 100453134 |  | 16720208G |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LAKESHORE | 209 LAKESHORE DR 14 | 067 | LEX | 2023-03-10 | JGILES | U125208 | 2012-03-09 | 2020-12-31 |  |  | JGILES | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.28333 | 1 | 11.61 | 10.91 | 0 | 0.7 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12959637500 |  | 100453131 |  | 16720208G |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LAKESHORE | 209 LAKESHORE DR 5 | 067 | LEX | 2023-03-10 | JGILES | U125208 | 2012-03-09 | 2020-12-31 |  |  | JGILES | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.41667 | 1 | 17.38 | 16.33 | 0 | 1.05 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12959637600 |  | 100453232 |  | 16720208G |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LAKESHORE | 201 LAKESHORE DR 1 | 067 | LEX | 2023-03-10 | U930915 | U125208 | 2012-03-09 | 2020-12-31 |  |  | KOBRYAN | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.16667 | 1 | 10.46 | 9.83 | 0 | 0.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12959637800 |  | 100453233 |  | 16720208G |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LAKESHORE | 201 LAKESHORE DR 2 | 067 | LEX | 2023-03-10 | KOBRYAN | U125208 | 2012-03-09 | 2020-12-31 |  |  | KOBRYAN | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.2 | 1 | 12.31 | 11.56 | 0 | 0.75 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12959638000 |  | 100453234 |  | 16720208G |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LAKESHORE | 201 LAKESHORE DR 3 | 067 | LEX | 2023-03-10 | KOBRYAN | U125208 | 2012-03-09 | 2020-12-31 |  |  | KOBRYAN | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.7 | 1 | 104.64 | 98.29 | 0 | 6.35 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12959638600 |  | 100453235 |  | 16720208G |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LAKESHORE | 201 LAKESHORE DR 4 | 067 | LEX | 2023-03-10 | KOBRYAN | U125208 | 2012-03-09 | 2020-12-31 |  |  | KOBRYAN | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.05 | 1 | 3.05 | 2.87 | 0 | 0.18 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12959638700 |  | 100453236 |  | 16720208G |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LAKESHORE | 201 LAKESHORE DR 5 | 067 | LEX | 2023-03-10 | KOBRYAN | U125208 | 2012-03-09 | 2020-12-31 |  |  | KOBRYAN | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.11667 | 1 | 7.4 | 6.95 | 0 | 0.45 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12959638800 |  | 100453237 |  | 16720208G |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LAKESHORE | 201 LAKESHORE DR 6 | 067 | LEX | 2023-03-10 | KOBRYAN | U125208 | 2012-03-09 | 2020-12-31 |  |  | KOBRYAN | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.1 | 1 | 6.2 | 5.81 | 0 | 0.39 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12959638900 |  | 100453238 |  | 16720208G |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LAKESHORE | 201 LAKESHORE DR 7 | 067 | LEX | 2023-03-10 | KOBRYAN | U125208 | 2012-03-09 | 2020-12-31 |  |  | KOBRYAN | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.1 | 1 | 6.2 | 5.81 | 0 | 0.39 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12959639100 |  | 100453239 |  | 16720208G |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LAKESHORE | 201 LAKESHORE DR 8 | 067 | LEX | 2023-03-10 | KOBRYAN | U125208 | 2012-03-09 | 2020-12-31 |  |  | KOBRYAN | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.05 | 1 | 3.05 | 2.87 | 0 | 0.18 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12959639400 |  | 100453240 |  | 16720208G |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LAKESHORE | 201 LAKESHORE DR 9 | 067 | LEX | 2023-03-10 | KOBRYAN | U125208 | 2012-03-09 | 2020-12-31 |  |  | KOBRYAN | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.1 | 1 | 6.2 | 5.81 | 0 | 0.39 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12959639600 |  | 100453241 |  | 16720208G |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LAKESHORE | 201 LAKESHORE DR 10 | 067 | LEX | 2023-03-10 | KOBRYAN | U125208 | 2012-03-09 | 2020-12-31 |  |  | KOBRYAN | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.65 | 1 | 40.02 | 37.59 | 0 | 2.43 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12959639800 |  | 100453242 |  | 16720208G |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LAKESHORE | 201 LAKESHORE DR 11 | 067 | LEX | 2023-03-10 | KOBRYAN | U125208 | 2012-03-09 | 2020-12-31 |  |  | KOBRYAN | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.95 | 1 | 121.25 | 113.9 | 0 | 7.35 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12959639900 |  | 100453243 |  | 16720208G |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LAKESHORE | 201 LAKESHORE DR 12 | 067 | LEX | 2023-03-10 | KOBRYAN | U125208 | 2012-03-09 | 2020-12-31 |  |  | KOBRYAN | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.3 | 1 | 80.03 | 75.17 | 0 | 4.86 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12959640900 |  | 100453135 |  | 16720208G |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LAKESHORE | 209 LAKESHORE DR 7 | 067 | LEX | 2023-03-10 | JOCHOA | U125208 | 2012-03-09 | 2020-12-31 |  |  | JOCHOA | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.13333 | 1 | 8.97 | 8.41 | 0 | 0.56 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129011900 |  | 100261691 |  | 7344144T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BUTTERFLY | 54 BUTTERFLY ST | 071 | MCD | 2023-03-10 | U130172 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JOHN HOWARD | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 8 | 1 | 528.5 | 496.45 | 0 | 32.05 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964241500 |  | 100347752 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | MAIN | 306 N MAIN ST | 049 | WIN | 2023-03-10 | U126602 | U134723 | 2022-01-06 | 2023-07-31 |  |  | DEREK PAYTON | 2023-03-10 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 5706.32 | 0 | 0 | 0 | 5706.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026264300 |  |  |  | 6720208M | 2395897 | U461383 |  | 557 | EX | EMER-INSTALL 5' OF 4"PMMP MAIN | 2621P | DOVE RUN | 1055 DOVE RUN RD | 067 | LEX | 2023-03-24 | U136251 | U461383 | 2023-02-28 | 2023-03-09 |  | 2023-02-28 | DMARSTO | 2023-03-10 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2643 |  |  | 100 | 055732230262643 | 1.5667 | 3 | 267.86 | 85.83 | 134.11 | 5.53 | 0 | 0 | 0 | 42.39 | 3
KY | KY - WEST | 2621 | 23026264400 |  |  |  | 6720208M | 2395897 | U461383 |  | 558 | EX | EMER-RETIRE 520'- 4"PAIP MAIN | 2621P | DOVE RUN | 1055 DOVE RUN RD | 067 | LEX | 2023-04-03 | U128381 | U461383 | 2023-02-28 | 2023-03-10 |  | 2023-02-28 | DMARSTO | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2644 |  |  | 100 | 055832230262644 | 5.15 | 0 | 325.83 | 306.07 | 0 | 19.76 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164759100 |  | 100281526 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | OAK | 523 OAK ST | 209 | GEO | 2023-03-10 | U126284 | U125763 | 2023-02-03 | 2023-12-29 |  |  | JOSH PASLEY/TEAM FISHEL | 2023-03-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 1 | 3538.69 | 488.7 | 0 | 475.5 | 2574.49 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165282100 |  | 500194642 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | KENTON | 465 KENTON ST | 067 | LEX | 2023-03-10 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-03-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2574.03 | 0 | 0 | 0 | 2574.03 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166688900 |  | 100272338 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | HAY | 103 HAY AV | 073 | FRA | 2023-03-10 | U126308 | U125763 | 2023-02-14 | 2023-12-29 |  |  | J ENSMINGER | 2023-03-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1709.35 | 0 | 0 | 0 | 1709.35 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166706100 |  | 100309870 |  | 6712208H | 2184394 |  |  | 565 | EX | RPLC SL/22026223700 | 2600B | TUCSON | 2290 TUCSON DR | 067 | LEX | 2023-03-13 | U128410 | U125763 | 2023-02-14 | 2023-12-29 |  |  | CDESPAIN | 2023-03-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 1639.35 | 0 | 0 | 0 | 1639.35 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166712500 |  | 100308611 |  | 6716212N | 2286252 |  |  | 565 | EX | RPLC SL/22026163200 | 2600B | PARKWAY | 454 PARKWAY DR | 067 | LEX | 2023-03-10 | U461322 | U125763 | 2023-02-14 | 2023-12-29 |  |  | STEVE CANOY | 2023-03-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.5 | 1 | 1661.14 | 270.93 | 0 | 268.9 | 1121.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166712700 |  | 100308610 |  | 6716212N | 2286252 |  |  | 565 | EX | RPLC SL/22026163200 | 2600B | PARKWAY | 469 PARKWAY DR | 067 | LEX | 2023-03-10 | U461322 | U125763 | 2023-02-14 | 2023-12-29 |  |  | STEVE CANOY | 2023-03-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.6667 | 1 | 2481.84 | 158.48 | 0 | 157.31 | 2166.05 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23169268400 |  | 100301110 |  | 6716212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER | 2621P | SAVOY | 229 SAVOY RD | 067 | LEX | 2023-03-10 | WISHII | AOC SYST | 2023-02-24 | 2023-03-24 | 2023-04-24 |  | WISHII | 2023-03-10 | 2023-03-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 16.3333 | 4 | 1356.71 | 841.73 | 0 | 420.38 | 94.6 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23173119800 |  | 100281094 |  | 6692216A |  |  |  | 565 | EX | RPLC SL/RLA- D308868 | 2600B | MCCRACKEN | 5185 MCCRACKEN PK FG 45 | 239 | VER | 2023-03-10 | U128816 | U125763 | 2023-03-10 | 2023-04-04 | 2024-10-31 |  | OLIVER MAYNARD | 2023-03-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26230022 | 7.2333 | 1 | 4285.73 | 608.02 | 715.46 | 39.27 | 2922.98 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23173192100 |  | 100445049 |  | 6716216L |  | U134852 |  | 566 | EX | SERVICE LINE ABANDON | 2621P | PRIMROSE | 983 PRIMROSE CT | 067 | LEX | 2023-03-15 | U125208 | U134852 | 2023-03-10 | 2023-03-10 |  |  | TROE | 2023-03-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.65 | 3 | 144.21 | 135.45 | 0 | 8.76 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883225900 |  | 100250574 |  | 7376184A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | WALNUT | 126 WALNUT ST | 159 | LOV | 2023-03-13 | BPREECE | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BPREECE | 2023-03-13 | 2023-03-13 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 20.6167 | 3 | 1432.91 | 1346 | 0 | 86.91 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960852900 |  | 100250229 |  | 7356248H | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | CANNONSBURG | 8110 CANNONSBURG RD | 019 | CAT | 2023-03-13 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH CASEY PACK | 2023-03-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1246.53 | 0 | 0 | 0 | 1246.53 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960861000 |  | 100249843 |  | 7356248H | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | PADDLE CREEK | 8000 PADDLE CREEK RD | 019 | CAT | 2023-03-13 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH JERRY NEWMAN | 2023-03-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1981.35 | 0 | 0 | 0 | 1981.35 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129090200 |  | 100275198 |  | 6684228J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SAINT CLAIR | 305 SAINT CLAIR ST | 073 | FRA | 2023-04-27 | U126332 | U130722 | 2022-09-05 | 2022-12-30 |  |  | DCOLLIN | 2023-03-13 | 2023-03-08 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 17.75 | 7 | 2135.33 | 1118.84 | 42.29 | 438.52 | 535.68 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129205100 |  | 100343173 |  | 7236212D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311811 | 2621P | COLLINS | 111 COLLINS AV | 173 | MT | 2023-03-14 | U125208 | U125208 | 2022-09-06 | 2023-03-01 | 2024-09-30 |  | DENNING | 2023-03-13 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 24 | 3 | 2149.13 | 1652.64 | 328.19 | 106.7 | 61.6 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026251300 |  |  |  | 7344268M | 2394960 | U461383 |  | 587 | EX | INSTALL EC 350 UNIT | 2631M | HARRIS | 23< HARRIS RD | 089 | WUR | 2023-04-04 | U123258 | U461383 | 2023-01-17 | 2023-09-29 | 2023-10-01 | 2023-03-13 | SGIORDANO | 2023-03-13 | 2023-03-01 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00587 | 3200587 |  |  | WP2513 |  |  | 100 | 058732230262513 | 4.1 | 2 | 8141.46 | 245.01 | 3521.9 | 31.36 | 3027.29 | 0 | 23.92 | 1291.98
KY | KY - EAST | 2631 | 23026251400 |  |  |  | 7344268M | 2394960 | U461383 |  | 588 | EX | RETIRE PAPER BILLING CHART | 2631M | HARRIS | 23< HARRIS RD | 089 | WUR | 2023-04-04 | U123258 | U461383 | 2023-01-17 | 2023-09-29 | 2023-10-01 | 2023-03-13 | SGIORDANO | 2023-03-13 | 2023-03-14 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00588 | 3200588 |  |  | WP2514 |  |  | 100 | 058832230262514 | 7.35 | 0 | 870.82 | 436.43 | 0 | 434.39 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23152816900 |  | 100453244 |  | 6720208J |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303532 | 2621P | NORBORNE | 2056 NORBORNE DR | 067 | LEX | 2023-03-23 | U125208 | U125208 | 2023-01-03 | 2023-06-30 | 2024-12-31 |  | DMARSTO | 2023-03-13 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.2833 | 3 | 1122.87 | 758.31 | 194.59 | 48.97 | 121 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166695100 |  | 100272323 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 125 TANGLEWOOD DR | 073 | FRA | 2023-03-13 | U126308 | U125763 | 2023-02-14 | 2023-12-29 |  |  | J ENSMINGER | 2023-03-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3485.82 | 0 | 0 | 0 | 3485.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166705800 |  | 100309873 |  | 6712208H | 2184394 |  |  | 565 | EX | RPLC SL/22026223700 | 2600B | TUCSON | 2260 TUCSON DR | 067 | LEX | 2023-03-15 | U128410 | U125763 | 2023-02-14 | 2023-12-29 |  |  | CDESPAIN | 2023-03-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 1629.69 | 0 | 0 | 0 | 1629.69 | 0 | 0 | 0
KY | KY - WEST | 2621 | 03533610400 |  | 100463220 |  | X00000000 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LONGVIEW | 354 LONGVIEW PZ | 067 | LEX | 2023-03-14 | U930915 | DMCCULL | 2003-03-13 | 2020-12-31 |  |  | JOCHOA | 2023-03-14 | 2023-02-27 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 14.4167 | 11 | 875.23 | 718.39 | 0 | 156.84 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 09811915600 |  | 500908879 |  | 6712240O | 0463432 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | COMMERCE | 130< COMMERCE CT | 209 | GEO | 2023-03-21 | U461383 | U124017 | 2009-11-17 | 2020-12-23 |  |  | DMILLS | 2023-03-14 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.93333 | 1 | 117.69 | 62.07 | 0 | 55.62 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11911133500 |  | 100426199 |  | 7240216O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | MILLROW | MILLROW ST | 173 | MT | 2023-03-14 | DENNING | U906631 | 2011-06-13 | 2022-07-01 | 2023-12-31 |  | DENNING | 2023-03-14 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 13.95 | 3 | 954.02 | 896.15 | 0 | 57.87 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22124690600 |  | 100258211 |  | 7348268M | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE SERVICE | 2631D | 4TH | 213 4TH AV | 089 | WOR | 2023-03-14 | JKEENER | AOC SYST | 2022-08-17 | 2023-02-17 | 2023-12-31 |  | JKEENER | 2023-03-14 | 2023-03-13 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 20.4667 | 4 | 1557.43 | 1277.93 | 0 | 184.9 | 94.6 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129012000 |  | 100261732 |  | 7344144T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KY RT 680 | 703 KY RT 680 | 071 | MCD | 2023-03-14 | U130172 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JOHN HOWARD | 2023-03-14 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.5667 | 1 | 236.48 | 222.15 | 0 | 14.33 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22148624700 |  | 100246607 |  | 7356256M | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER | 2631D | CAROLYN | 2709 CAROLYN ST | 019 | ASH | 2023-03-14 | JKEENER | AOC SYST | 2022-12-12 | 2023-01-05 | 2023-02-04 |  | JKEENER | 2023-03-14 | 2023-02-09 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26310031 | 16 | 6 | 1362.44 | 1041.98 | 0 | 233.56 | 86.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964241400 |  | 100348260 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | MAIN | 303 N MAIN ST | 049 | WIN | 2023-03-14 | U126603 | U134723 | 2022-01-06 | 2023-07-31 |  |  | SHAWN DENNIS | 2023-03-14 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4695.9 | 14.42 | 0 | 0.94 | 4680.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026250200 |  |  |  | 6716212H | 2394960 | U461383 |  | 587 | EX | INSTALL EC-350 | 2600M | BROADWAY | 345 N BROADWAY ST | 067 | LEX | 2023-03-21 | U123258 | U461383 | 2023-01-16 | 2023-09-29 | 2023-10-01 | 2023-03-14 | EBLANTON | 2023-03-14 | 2023-03-14 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00587 | 3200587 |  |  | WP2502 |  |  | 100 | 058732230262502 | 2.8167 | 1 | 8105.28 | 170.84 | 3521.9 | 11.04 | 3027.29 | 0 | 336.41 | 1037.8
KY | KY - WEST | 2621 | 23026250300 |  |  |  | 6716212H | 2394960 | U461383 |  | 588 | EX | RETIRE PAPER BILLING CHART | 2600M | BROADWAY | 345 N BROADWAY ST | 067 | LEX | 2023-03-21 | U123258 | U461383 | 2023-01-16 | 2023-09-29 | 2023-10-01 | 2023-03-14 | EBLANTON | 2023-03-14 | 2023-03-14 |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00588 | 3200588 |  |  | WP2503 |  |  | 100 | 058832230262503 | 2.85 | 0 | 185.13 | 173.9 | 0 | 11.23 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156274800 |  | 100356290 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | US 68 | 1117 US 68 | 161 | MAY | 2023-03-14 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-14 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1930.39 | 47.78 | 0 | 3.08 | 1879.53 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156274900 |  | 100356291 |  | 7256280N | 2180423 |  |  | 565 | EX | REPL SVC W/ 21-0261270-00 | 2600B | US 68 | 1125 US 68 | 161 | MAY | 2023-03-14 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-14 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1815.53 | 0 | 0 | 0 | 1815.53 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166688700 |  | 100272339 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | HAY | 100 HAY AV | 073 | FRA | 2023-03-14 | U126308 | U125763 | 2023-02-14 | 2023-12-29 |  |  | J ENSMINGER | 2023-03-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 194.54 | 0 | 0 | 0 | 194.54 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168123100 |  | 100345860 |  | 6704212M |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309377 | 2621P | GAYBOURNE | 125 GAYBOURNE WY | 239 | VER | 2023-03-14 | U128816 | U125208 | 2023-02-20 | 2023-08-18 | 2025-02-28 |  | OLIVER MAYNARD | 2023-03-14 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 9 | 1 | 3986.38 | 590.22 | 291.84 | 38.11 | 3066.21 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23173292400 |  | 100328976 |  | 6720208P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D310452 | 2621P | PADDOCK | 2693 PADDOCK CT | 067 | LEX | 2023-03-23 | U125208 | U134822 | 2023-03-10 | 2023-03-10 | 2023-03-10 |  | JOCHOA | 2023-03-14 | 2023-03-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 30.05 | 5 | 2182.82 | 1599.39 | 259.26 | 266.97 | 57.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23173551100 |  | 100312312 |  | 6716208I |  |  |  | 565 | EX | SERVICE LINE - REPLACE D309227 | 2621P | MAPLEWOOD | 2421 MAPLEWOOD DR | 067 | LEX | 2023-03-24 | U129722 | U129939 | 2023-03-14 | 2023-01-31 |  |  | M YOUNG | 2023-03-14 | 2023-03-14 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.2833 | 2 | 2888.55 | 699.07 | 676.3 | 45.14 | 1468.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23173599800 |  | 100462742 |  | 6720200A |  |  |  | 565 | EX | REPLACE SERVICE LINE - D310375 | 2621P | EDGEWOOD | 872 EDGEWOOD DR | 067 | LEX | 2023-03-16 | U125208 | U129939 | 2023-03-14 | 2023-06-09 | 2024-12-31 |  | DMARSTO | 2023-03-14 | 2023-03-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.0833 | 3 | 645.1 | 273.42 | 205.48 | 17.7 | 148.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 10868565600 |  | 100340841 |  | 6736184T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | LOST FORK | 433 LOST FORK RD | 151 | RIC | 2023-03-16 | U125208 | U906314 | 2010-11-15 | 2022-06-30 | 2023-12-31 |  | DENNING | 2023-03-15 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 25.8667 | 10 | 3183.14 | 1670.39 | 0 | 290.45 | 1222.3 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883209900 |  | 100247833 |  | 7364188A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | MAIN | 726 E MAIN ST | 159 | INE | 2023-03-15 | JCKIRK | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JCKIRK | 2023-03-15 | 2022-11-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 20.3833 | 4 | 1297.51 | 1218.82 | 0 | 78.69 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960860900 |  | 100249836 |  | 7356248G | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | PADDLE CREEK | 7941 PADDLE CREEK RD | 019 | CAT | 2023-03-15 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH JERRY NEWSOME | 2023-03-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3395.57 | 0 | 0 | 0 | 3395.57 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22026241900 |  |  |  | 7352156G | 2294177 | U122858 |  | 561 | EX | INSTALL 249'-2" PMIP | 2600B | MAIN | E MAIN ST | 071 | STA | 2023-03-24 | U133347 | U122858 | 2022-12-08 | 2023-05-17 | 2023-05-31 | 2023-03-14 | DAVID SKAGGS | 2023-03-15 | 2023-02-27 |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00561 | 3200561 |  |  | WP2419 | AMRCB |  | 100 | 056132220262419 | 150.0667 | 4260 | 101153.64 | 9935.12 | 3440.32 | 2866.58 | 68752.44 | 0 | 87.64 | 16071.54 | 284
KY | KY - EAST | 2633 | 22026242000 |  |  |  | 7352156G | 2294177 | U122858 |  | 562 | EX | RETIRE 135'-3" BSIP | 2600E | MAIN | E MAIN ST | 071 | STA | 2023-03-17 | U133347 | U122858 | 2022-12-08 | 2023-05-31 | 2023-05-31 | 2023-03-14 | DAVID SKAGGS | 2023-03-15 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00562 | 3200562 |  |  | WP2420 | AMRCB |  | 100 | 056232220262420 | 2.05 | 0 | 139.7 | 131.23 | 0 | 8.47 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026250500 |  |  |  | 6716216J | 2394960 | U461383 |  | 587 | EX | INSTALL EC 350 | 2600M | BAUMANN | 1587 BAUMANN DR | 067 | LEX | 2023-07-17 | U123258 | U461383 | 2023-01-16 | 2023-09-29 | 2023-10-01 | 2023-03-15 | EBLANTON | 2023-03-15 | 2023-03-15 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00587 | 3200587 |  |  | WP2505 |  |  | 100 | 058732230262505 | 2.1 | 1 | 6654.67 | 128.13 | 3521.9 | 8.27 | 1930 | 0 | 15.77 | 1050.6
KY | KY - WEST | 2621 | 23026250600 |  |  |  | 6716216J | 2394960 | U461383 |  | 588 | EX | RETIRE PAPER BILLING CHART | 2600M | BAUMANN | 1587 BAUMANN DR | 067 | LEX | 2023-03-22 | U123258 | U461383 | 2023-01-16 | 2023-09-29 | 2023-10-01 | 2023-03-15 | EBLANTON | 2023-03-15 | 2023-03-15 |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00588 | 3200588 |  |  | WP2506 |  |  | 100 | 058832230262506 | 2.2333 | 0 | 144.2 | 135.45 | 0 | 8.75 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156275000 |  | 100356324 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | US 68 | 1131 US 68 | 161 | MAY | 2023-03-15 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-15 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1862.51 | 37.13 | 0 | 2.41 | 1822.97 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156275200 |  | 100356326 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | US 68 | 1135 US 68 | 161 | MAY | 2023-03-16 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-15 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1698.98 | 22.42 | 0 | 1.45 | 1675.11 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156275300 |  | 100356327 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | US 68 | 1137 US 68 | 161 | MAY | 2023-03-16 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-15 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1578.39 | 0 | 0 | 0 | 1578.39 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156275500 |  | 100356328 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | US 68 | 1139 US 68 | 161 | MAY | 2023-03-15 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-15 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2283.97 | 85.5 | 0 | 5.52 | 2192.95 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166689100 |  | 100272340 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | HAY | 105 HAY AV | 073 | FRA | 2023-03-31 | U126308 | U125763 | 2023-02-14 | 2023-12-29 |  |  | J ENSMINGER | 2023-03-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2995.88 | 9.56 | 0 | 0.52 | 2985.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166689300 |  | 100272342 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | HAY | 108 HAY AV | 073 | FRA | 2023-03-31 | U126308 | U125763 | 2023-02-14 | 2023-12-29 |  |  | J ENSMINGER | 2023-03-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2532.7 | 0 | 0 | 0 | 2532.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166705600 |  | 100309875 |  | 6712208H | 2184394 |  |  | 565 | EX | RPLC SL/22026223700 | 2600B | TUCSON | 2240 TUCSON DR | 067 | LEX | 2023-03-15 | U128410 | U125763 | 2023-02-14 | 2023-12-29 |  |  | CDESPAIN | 2023-03-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 1615.89 | 0 | 0 | 0 | 1615.89 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166712300 |  | 100308613 |  | 6716212N | 2286252 |  |  | 565 | EX | RPLC SL/22026163200 | 2600B | PARKWAY | 450 PARKWAY DR | 067 | LEX | 2023-03-15 | U461322 | U125763 | 2023-02-14 | 2023-12-29 |  |  | STEVE CANOY | 2023-03-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.4667 | 1 | 3053.64 | 387.53 | 0 | 384.61 | 2281.5 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23169810600 |  | 100268853 |  | 7352156G | 2294177 |  |  | 565 | EX | RPLC SL/22026241900 | 2600B | OLD US 23 | OLD US 23 | 071 | STA | 2023-03-15 | U125566 | U125763 | 2023-03-01 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-03-15 |  |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 |  | 1 | 4205.53 | 0 | 0 | 0 | 4205.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23171910600 |  | 100338924 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL - DEMO/CODE ENFORCE | 2621P | LOUDON | 643 E LOUDON AV | 067 | LEX | 2023-03-15 | LSTANFI | U125208 | 2023-03-06 | 2023-03-10 | 2023-04-06 |  | LSTANFI | 2023-03-15 | 2023-03-14 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.1667 | 3 | 720.56 | 378.46 | 15.8 | 27.8 | 298.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23173649500 |  | 100283575 |  | 6712228A |  |  |  | 565 | EX | REPLACE SERVICE LINE - D253668 | 2621P | PUEBLO | 607 PUEBLO TL | 209 | GEO | 2023-03-15 | DCOLLIN | U125208 | 2023-03-14 | 2023-03-17 | 2023-04-04 |  | DCOLLIN | 2023-03-15 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 28.2667 | 3 | 1992.02 | 1555.7 | 266.24 | 100.78 | 69.3 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23173909300 |  | 100345806 |  | 6696212D |  |  |  | 565 | EX | GR 1 REPLACE SERVICE - D308936 | 2621P | MILDRED | 777 MILDRED ST | 239 | VER | 2023-03-16 | U930915 | U129939 | 2023-03-15 | 2023-03-15 | 2023-03-15 |  | BSEXTON | 2023-03-15 | 2023-03-15 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 41.2333 | 5 | 4540.56 | 2430.18 | 318.05 | 835.61 | 956.72 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23173949300 |  | 100283633 |  | 6712228B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D253669 | 2621P | HIGHLAND | 127 HIGHLAND CT | 209 | GEO | 2023-03-16 | U125208 | U134822 | 2023-03-15 | 2023-03-15 | 2023-03-15 |  | DCOLLIN | 2023-03-15 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 | 0.83333 | 2 | 1038.91 | 619.49 | 288.1 | 40.02 | 91.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 16426409800 |  | 500318461 |  | 7240216L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | OLD OWINGSVILL | OLD OWINGSVILL RD | 173 | MT | 2023-03-16 | DENNING | U122906 | 2016-07-13 | 2022-07-01 | 2023-12-31 |  | DENNING | 2023-03-16 | 2022-11-17 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.6833 | 4 | 240.34 | 160.59 | 0 | 79.75 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883304000 |  | 500987702 |  | 7240216E | 0041088 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | CLUB HOUSE | CLUB HOUSE LN | 173 | MT | 2023-03-16 | DENNING | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | DENNING | 2023-03-16 | 2022-11-17 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 6.5333 | 3 | 428.71 | 286.46 | 0 | 142.25 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960860700 |  | 100249845 |  | 7356248G | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | PADDLE CREEK | 7930 PADDLE CREEK RD | 019 | CAT | 2023-03-17 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH JERRY NEWSOME | 2023-03-16 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2863.12 | 0 | 0 | 0 | 2863.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22026209201 |  |  |  | 7256280L | 2074435 | U122858 |  | 586 | EX | RETIRE BUILDING FOR R-1451 | 2632M | BUGLE | BUGLE AL | 161 | MAY | 2023-03-22 | U123258 | U122858 | 2023-03-13 | 2023-12-28 | 2023-12-31 | 2023-03-16 | WADE SHIMFESSEL | 2023-03-16 |  |  | F | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00586 | 3200586 |  |  | WP2092 | AMRCB |  | 100 | 058632220262092 | 11.4167 | 0 | 3422.43 | 688.23 | 33.89 | 44.45 | 2655.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22122935200 |  | 100322907 |  | 6716208L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303204 | 2600B | TATES CREEK | 2721 TATES CREEK RD | 067 | LEX | 2023-03-21 | U128410 | U125208 | 2022-08-10 | 2023-02-09 | 2024-08-31 |  | CDESPAIN | 2023-03-16 | 2023-03-16 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 36.1167 | 5 | 13725.02 | 1761.04 | 0 | 113.41 | 11850.57 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964241600 |  | 100348254 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | MAIN | 317 N MAIN ST | 049 | WIN | 2023-03-16 | U126532 | U134723 | 2022-01-06 | 2023-07-31 |  |  | LESLIE SHARON | 2023-03-16 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3577 | 0 | 0 | 0 | 3577 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026250000 |  |  |  | 6716216E | 2394960 | U461383 |  | 587 | EX | INSTALL EC 350 UNIT | 2600M | BULL LEA | 1490 BULL LEA RD | 067 | LEX | 2023-03-21 | U123258 | U461383 | 2023-01-16 | 2023-09-29 | 2023-10-01 | 2023-03-16 | EBLANTON | 2023-03-16 | 2023-03-16 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00587 | 3200587 |  |  | WP2500 |  |  | 100 | 058732230262500 | 5.7833 | 2 | 6158.92 | 352.05 | 3521.9 | 189.21 | 1097.29 | 0 | 19.53 | 978.94
KY | KY - WEST | 2621 | 23026250100 |  |  |  | 6716216E | 2394960 | U461383 |  | 588 | EX | RETIRE PAPER BILLING CHART | 2600M | BULL LEA | 1490 BULL LEA RD | 067 | LEX | 2023-03-21 | U123258 | U461383 | 2023-01-16 | 2023-09-29 | 2023-10-01 | 2023-03-16 | EBLANTON | 2023-03-16 | 2023-03-16 |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00588 | 3200588 |  |  | WP2501 |  |  | 100 | 058832230262501 | 5.5 | 0 | 525.01 | 336.78 | 0 | 188.23 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026267700 |  |  |  | 6720208E | 2396286 | U461383 |  | 558 | EX | EMER-RETIRE 40' OF 6"BSLP MAIN | 2621P | INDIAN MOUND | INDIAN MOUND | 067 | LEX | 2023-03-31 | U121331 | U461383 | 2023-03-17 | 2023-12-28 | 2023-12-31 | 2023-03-16 | VANDERPOOL | 2023-03-16 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2677 | AMRCB |  | 100 | 055832230262677 |  | 0 | 8203.54 | 2258.17 | 146.42 | 325.13 | 5473.82 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166689400 |  | 100272341 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | HAY | 110 HAY AV | 073 | FRA | 2023-03-16 | U461375 | U125763 | 2023-02-14 | 2023-12-29 |  |  | LARRY BROWN | 2023-03-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2720.65 | 0 | 0 | 0 | 2720.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166712600 |  | 100308609 |  | 6716212N | 2286252 |  |  | 565 | EX | RPLC SL/22026163200 | 2600B | PARKWAY | 460 PARKWAY DR | 067 | LEX | 2023-03-16 | U461322 | U125763 | 2023-02-14 | 2023-12-29 |  |  | STEVE CANOY | 2023-03-16 | 2023-03-15 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.3667 | 2 | 3454.93 | 438.38 | 0 | 435.09 | 2581.46 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23173148600 |  | 100415605 |  | 6692228A |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | SCRUGGS | 297 N SCRUGGS LN 5 | 073 | FRA | 2023-03-16 | U930915 | U133234 | 2023-03-10 | 2023-03-23 | 2023-04-08 |  | BWHITE | 2023-03-16 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.43333 | 1 | 24.51 | 23.03 | 0 | 1.48 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23173153100 |  | 100414597 |  | 6692228A |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | SCRUGGS | 287 N SCRUGGS LN 6 | 073 | FRA | 2023-03-16 | BWHITE | U133234 | 2023-03-10 | 2023-03-23 | 2023-04-08 |  | BWHITE | 2023-03-16 | 2023-03-15 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 14.1333 | 3 | 1144.43 | 852.43 | 0 | 292 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23173157400 |  | 100436904 |  | 6692228A |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | SCRUGGS | 277 N SCRUGGS LN | 073 | FRA | 2023-03-16 | BSEXTON | U133234 | 2023-03-10 | 2023-03-23 | 2023-04-08 |  | BSEXTON | 2023-03-16 | 2023-03-14 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 15.7 | 3 | 744.04 | 698.89 | 0 | 45.15 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23173948700 |  | 500021087 |  | 6716208J |  |  |  | 565 | EX | SERVICE LINE - REPLACE D247711 | 2621P | REGENCY | 2250 REGENCY RD | 067 | LEX | 2023-03-21 | U125208 | U134822 | 2023-03-15 | 2023-02-18 | 2024-08-31 |  | MCRAIG | 2023-03-16 | 2023-03-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 | KYACN |  | 100 | 056532B26210021 | 26.7167 | 4 | 4055.7 | 2274.92 | 653.23 | 793.15 | 334.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23174306500 |  | 100346429 |  | 6696212L |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | MONTGOMERY | 157 MONTGOMERY AV | 239 | VER | 2023-03-17 | U128816 | U129939 | 2023-03-16 | 2023-03-16 |  |  | OLIVER MAYNARD | 2023-03-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.6 | 2 | 6396.35 | 236.76 | 611.38 | 15.29 | 5532.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026163200 |  |  |  | 6716212N | 2286252 | U461383 |  | 557 | EX | INSTALL 775' OF 2"PMMP MAIN | 2600B | PARKWAY | PARKWAY DR | 067 | LEX | 2023-04-11 | U128132 | U461383 | 2022-02-02 | 2023-12-05 | 2023-12-31 | 2023-03-09 | STEVE CANOY | 2023-03-17 | 2023-03-02 | 2023-03-06 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP1632 | AMRCB |  | 100 | 055732220261632 | 63.5667 | 6318 | 49762.97 | 3970.03 | 3032.92 | 3826.47 | 30983.57 | 0 | 115.28 | 7834.7 | 702
KY | KY - WEST | 2621 | 22026163300 |  |  |  | 6716212N | 2286252 | U461383 |  | 558 | EX | RETIRE 800' OF 4"BSLP MAIN | 2600B | PARKWAY | PARKWAY DR | 067 | LEX | 2023-03-21 | U128132 | U461383 | 2022-02-02 | 2023-12-29 | 2023-12-31 | 2023-03-16 | STEVE CANOY | 2023-03-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP1633 | AMRCB |  | 100 | 055832220261633 | 0.18333 | 0 | 21.45 | 10.77 | 0 | 10.68 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026230301 |  |  |  | 6736232L | 2292664 | U128885 |  | 557 | EX | INSTALL 1,725'-2" PMMP | 2600B | MARSHALL | MARSHALL ST | 017 | PAR | 2023-04-03 | U128132 | U128885 | 2023-03-21 | 2049-10-24 | 2049-12-31 | 2023-02-26 | ED FOX | 2023-03-17 | 2023-01-03 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP2303 | AMRCB |  | 100 | 055732220262303 | 516.5 | 116046 | 676511.46 | 33751.34 | 99840.73 | 6654.71 | 451325.51 | 0 | 1329.21 | 83609.96 | 1842
KY | KY - CENTRAL | 2629 | 22026230400 |  |  |  | 6736232L | 2292664 | U128885 |  | 558 | EX | RETIRE 5,578' - IP MAIN | 2600B | MARSHALL | MARSHALL ST | 017 | PAR | 2023-03-28 | U128132 | U128885 | 2022-10-10 |  | 2049-12-31 | 2023-03-14 | ED FOX | 2023-03-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP2304 | AMRCB |  | 100 | 055832220262304 | 0.5 | 0 | 1019.8 | 551.72 | 0 | 285.68 | 182.4 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026230500 |  |  |  | 6740232I | 2292664 | U128885 |  | 558 | EX | RETIRE 1,368' - MP MAIN | 2600B | RUCKER | RUCKER ST | 017 | PAR | 2023-03-23 | U128132 | U128885 | 2022-10-10 | 2023-12-29 | 2023-12-31 | 2023-03-14 | ED FOX | 2023-03-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP2305 | AMRCB |  | 100 | 055832220262305 | 0.18333 | 0 | 14.31 | 11.65 | 0 | 2.66 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22979054400 |  | 500632768 |  | 7356152E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | US23 | 11964 US23 | 071 | HAR | 2023-03-17 | JAHOWARD | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | JAHOWARD | 2023-03-17 | 2022-10-05 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 17.4667 | 3 | 1035.83 | 973 | 0 | 62.83 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026260900 |  |  |  | 7336268H | 2294088 | U461383 |  | 909 | EX | INSTALL ERX W/SUPER SOLAR | 2631M | LAUREL | LAUREL ST | 089 | GRE | 2023-07-17 | U123258 | U461383 | 2023-02-16 | 2023-12-01 | 2023-12-01 | 2023-03-17 | SHANE GIORDANO | 2023-03-17 | 2023-03-17 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP2609 |  |  | 100 | 090932230262609 | 15.3167 | 0 | 1872.11 | 969.55 | 0 | 56.7 | 844.74 | 0 | 1.12 | 0
KY | KY - EAST | 2631 | 23026261000 |  |  |  | 7336268H | 2294088 | U461383 |  | 584 | EX | RETIRE PAPER CHART | 2631M | LAUREL | LAUREL ST | 089 | GRE | 2023-05-12 | U123258 | U461383 | 2023-02-16 | 2023-12-01 | 2023-12-01 | 2023-03-17 | SHANE GIORDANO | 2023-03-17 | 2023-03-17 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00584 | 3200584 |  |  | WP2610 |  |  | 100 | 058432230262610 | 2.7333 | 0 | 174.56 | 163.97 | 0 | 10.59 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23174594800 |  | 100272333 |  | 6684224B | 2179094 |  |  | 565 | EX | RPCL SL/PER DEDAVIS | 2621P | TANGLEWOOD | 104 TANGLEWOOD DR | 073 | FRA | 2023-03-17 | U126285 | U136332 | 2023-03-17 | 2023-03-17 |  |  | DDAVIS | 2023-03-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 |  | 1 | 2155.9 | 0 | 0 | 0 | 2155.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21895167700 |  | 100288295 |  | 6720212H | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | DARTMOOR | 629 DARTMOOR DR | 067 | LEX | 2023-03-20 | LSTANFI | AOC SYST | 2021-03-17 | 2022-12-31 | 2022-12-31 |  | LSTANFI | 2023-03-20 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 13.4333 | 2 | 1674.1 | 819.63 | 568.94 | 199.73 | 85.8 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960860600 |  | 100249840 |  | 7356248G | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | PADDLE CREEK | 7825 PADDLE CREEK RD | 019 | CAT | 2023-03-21 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH JERRY NEWSOME | 2023-03-20 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1804.68 | 0 | 0 | 0 | 1804.68 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129040000 |  | 100249579 |  | 7360212T |  |  |  | 566 | EX | ABANDON SL - IDL/INA *TCO TAP* | 2621P | MILE CREEK | 3 MILE CREEK RD | 127 | LOU | 2023-04-05 | U125208 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JKEENER | 2023-03-20 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 7.3833 | 1 | 468.94 | 440.5 | 0 | 28.44 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22985444700 |  | 100306653 |  | 6716212I | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | PINE MEADOWS | 1445 PINE MEADOWS RD | 067 | LEX | 2023-03-20 | U930915 | AOC SYST | 2022-03-11 | 2023-12-31 | 2023-12-31 |  | ABLAKE | 2023-03-20 | 2023-03-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 18.2833 | 5 | 1340.39 | 1117.81 | 94.31 | 72.17 | 56.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164551300 |  | 100313143 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LONE OAK | 531 LONE OAK DR | 067 | LEX | 2023-03-20 | U128762 | U125763 | 2023-02-02 | 2023-12-29 |  |  | CORY TINCHER | 2023-03-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2494.51 | 0 | 0 | 0 | 2494.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164553800 |  | 100313088 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LONE OAK | 557 LONE OAK DR | 067 | LEX | 2023-03-30 | U124003 | U125763 | 2023-02-02 | 2023-12-29 |  |  | BPULLIAM/FISHEL | 2023-03-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3717.48 | 0 | 0 | 0 | 3717.48 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166688800 |  | 100272344 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | HAY | 102 HAY AV | 073 | FRA | 2023-03-20 | U126308 | U125763 | 2023-02-14 | 2023-12-29 |  |  | J ENSMINGER | 2023-03-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3702.89 | 0 | 0 | 0 | 3702.89 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23173380800 |  | 100290624 |  | 6720216O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OLD PARIS | 1717 OLD PARIS RD | 067 | LEX | 2023-03-20 | LSTONE | U125208 | 2023-03-13 | 2023-04-06 | 2023-05-07 |  | LSTONE | 2023-03-20 | 2023-03-15 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.1167 | 6 | 675.56 | 616.06 | 19.7 | 39.8 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23174301500 |  | 100283621 |  | 6712228A |  |  |  | 565 | EX | REPLACE SERVICE LINE - D253670 | 2621P | -399 SEMINOLE | 397 -399 SEMINOLE TL A | 209 | GEO | 2023-03-20 | DCOLLIN | U125208 | 2023-03-16 | 2023-03-17 | 2023-04-06 |  | DCOLLIN | 2023-03-20 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 22.6833 | 3 | 2575.41 | 1431.98 | 651.63 | 451.1 | 40.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23174573300 |  | 100433783 |  | 6768172A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE '04 | 2621P | 7TH | 107 7TH ST | 065 | RAV | 2023-03-20 | DENNING | U125208 | 2023-03-17 | 2023-03-21 |  |  | DENNING | 2023-03-20 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.6833 | 1 | 206.59 | 107 | 0 | 99.59 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23175307500 |  | 500521346 |  | 6736252M |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MAIN | 102 S MAIN ST | 097 | CYN | 2023-03-21 | JTOY | JTOY | 2023-03-21 | 2023-03-20 | 2023-03-20 |  | SRICHIE | 2023-03-20 | 2023-03-20 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 11.7833 | 2 | 3262.88 | 153.53 | 256.2 | 140.33 | 2712.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21895458500 |  | 100288242 |  | 6720212H | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | HASTINGS | 1616 HASTINGS CT | 067 | LEX | 2023-03-21 | LSTANFI | AOC SYST | 2021-03-18 | 2022-12-31 | 2022-12-31 |  | LSTANFI | 2023-03-21 | 2023-03-21 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 18.9 | 3 | 1692 | 955.84 | 571.21 | 113.25 | 51.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960860500 |  | 500223409 |  | 7356248G | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | PADDLE CREEK | 7816 PADDLE CREEK RD | 019 | CAT | 2023-03-22 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH JERRY NEWSOME | 2023-03-21 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 4195.68 | 0 | 0 | 0 | 4195.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026241600 |  |  |  | 6712212G | 2294097 | U132703 |  | 560 | EX | RETIRE 30'-2" PMMP | 2600B | CUMMINS | 2051 CUMMINS CT | 067 | LEX | 2023-04-29 | U128132 | U132703 | 2022-12-06 | 2023-12-29 | 2023-12-31 | 2023-03-23 | R.HUMPHREYS | 2023-03-21 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00560 | 3200560 |  |  | WP2416 |  |  | 100 | 056032220262416 |  | 0 | 193.2 | 0 | 0 | 0 | 193.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22985446200 |  | 100306652 |  | 6716212I | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | PINE MEADOWS | 1441 PINE MEADOWS RD | 067 | LEX | 2023-03-21 | U930915 | AOC SYST | 2022-03-11 | 2023-12-31 | 2023-12-31 |  | ABLAKE | 2023-03-21 | 2023-03-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 20.9833 | 4 | 1310.89 | 1100.99 | 73.9 | 71.1 | 64.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156272400 |  | 100356318 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 592 CIRCLE DR | 161 | MAY | 2023-03-22 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-21 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1662.26 | 0 | 0 | 0 | 1662.26 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156272600 |  | 100356320 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 594 CIRCLE DR | 161 | MAY | 2023-03-22 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-21 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1734.15 | 0 | 0 | 0 | 1734.15 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164550700 |  | 100313140 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LONE OAK | 519 LONE OAK DR | 067 | LEX | 2023-03-22 | U128762 | U125763 | 2023-02-02 | 2023-12-29 |  |  | CORY TINCHER | 2023-03-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3772.98 | 0 | 0 | 0 | 3772.98 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164551600 |  | 100313145 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LONE OAK | 538 LONE OAK DR | 067 | LEX | 2023-03-21 | U124003 | U125763 | 2023-02-02 | 2023-12-29 |  |  | BPULLIAM/FISHEL | 2023-03-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2030.16 | 0 | 0 | 0 | 2030.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164551900 |  | 100313083 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LONE OAK | 558 LONE OAK DR | 067 | LEX | 2023-03-22 | U128762 | U125763 | 2023-02-02 | 2023-12-29 |  |  | CORY TINCHER | 2023-03-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2350.95 | 0 | 0 | 0 | 2350.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164552100 |  | 100313085 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LONE OAK | 562 LONE OAK DR | 067 | LEX | 2023-03-22 | U128762 | U125763 | 2023-02-02 | 2023-12-29 |  |  | CORY TINCHER | 2023-03-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1793.74 | 0 | 0 | 0 | 1793.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165899600 |  | 500007881 |  | 6712208J |  |  |  | 565 | EX | LEAK REPAIR - S.L. - D311286 | 2621P | MCNAIR | 2020 MCNAIR CT | 067 | LEX | 2023-03-21 | WISHII | U125208 | 2023-02-09 | 2023-08-08 | 2025-02-28 |  | WISHII | 2023-03-21 | 2023-03-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.5833 | 7 | 2219.54 | 1244.1 | 228.07 | 651.67 | 95.7 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166690900 |  | 100272349 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | RESERVOIR | 109 RESERVOIR RD | 073 | FRA | 2023-03-21 | U126308 | U125763 | 2023-02-14 | 2023-12-29 |  |  | J ENSMINGER | 2023-03-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2617.62 | 0 | 0 | 0 | 2617.62 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166691100 |  | 100272379 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | RESERVOIR | 112 RESERVOIR RD | 073 | FRA | 2023-03-24 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-03-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3252.64 | 0 | 0 | 0 | 3252.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23172238100 |  | 100319847 |  | 6716208K |  |  |  | 565 | EX | SERVICE LINE - REPLACE KKINDER | 2621P | ALBANY | 328 ALBANY RD | 067 | LEX | 2023-03-21 | U930915 | U125208 | 2023-03-07 | 2023-03-07 |  |  | KKINDER | 2023-03-21 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.2167 | 1 | 296.25 | 56.7 | 131.39 | 3.66 | 104.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23175347600 |  | 100345756 |  | 6696212D |  |  |  | 565 | EX | REPLACE SL | 2621P | MILDRED | 796 MILDRED ST | 239 | VER | 2023-03-21 | BWHITE | U137585 | 2023-03-21 | 2023-03-21 |  |  | BWHITE | 2023-03-21 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26230031 | 7.1333 | 3 | 711.76 | 411.2 | 222.29 | 26.57 | 51.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960860400 |  | 100249839 |  | 7356248G | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | PADDLE CREEK | 7800 PADDLE CREEK RD | 019 | CAT | 2023-03-23 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH JERRY NEWSOME | 2023-03-22 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2575.7 | 0 | 0 | 0 | 2575.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026248700 |  |  |  | 6740232I | 2394873 | U128885 |  | 559 | EX | INSTALL 2" SS | 2600E | HIGHLAND | HIGHLAND LN | 017 | PAR | 2023-03-23 | U128132 | U128885 | 2023-01-11 | 2023-12-28 | 2023-12-31 | 2023-02-14 | NRICHIE | 2023-03-22 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00559 | 3200559 |  |  | WP2487 |  |  | 100 | 055932230262487 |  | 0 | 2373.93 | 569.52 | 1138.95 | 271.93 | 0 | 0 | 7.29 | 386.24
KY | KY - CENTRAL | 2629 | 23026248800 |  |  |  | 6740232I | 2394873 | U128885 |  | 560 | EX | RETIRE 50' - 2" CSMP | 2600E | HIGHLAND | HIGHLAND AV | 017 | PAR | 2023-03-22 | U128132 | U128885 | 2023-01-11 | 2023-12-29 | 2023-12-31 | 2023-02-14 | NRICHIE | 2023-03-22 | 2023-02-13 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00560 | 3200560 |  |  | WP2488 |  |  | 100 | 056032230262488 | 65.7 | 0 | 6678.36 | 4932.49 | 0 | 1745.87 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156271500 |  | 100356312 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 568 CIRCLE DR | 161 | MAY | 2023-03-23 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-22 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1194.17 | 0 | 0 | 0 | 1194.17 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156271800 |  | 100356317 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 572 CIRCLE DR | 161 | MAY | 2023-03-22 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-22 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1578.39 | 0 | 0 | 0 | 1578.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164550500 |  | 100313139 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LONE OAK | 515 LONE OAK DR | 067 | LEX | 2023-03-23 | U128762 | U125763 | 2023-02-02 | 2023-12-29 |  |  | CORY TINCHER | 2023-03-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3288.51 | 0 | 0 | 0 | 3288.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164551700 |  | 100447277 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LONE OAK | 542 LONE OAK DR | 067 | LEX | 2023-03-23 | U128762 | U125763 | 2023-02-02 | 2023-12-29 |  |  | CORY TINCHER | 2023-03-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3204.93 | 0 | 0 | 0 | 3204.93 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164551800 |  | 100313086 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LONE OAK | 554 LONE OAK DR | 067 | LEX | 2023-03-24 | U128762 | U125763 | 2023-02-02 | 2023-12-29 |  |  | CORY TINCHER | 2023-03-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1901.45 | 0 | 0 | 0 | 1901.45 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166689000 |  | 100272343 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | HAY | 104 HAY AV | 073 | FRA | 2023-03-22 | U126308 | U125763 | 2023-02-14 | 2023-12-29 |  |  | J ENSMINGER | 2023-03-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3013.81 | 196.45 | 0 | 55.18 | 2762.18 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166691200 |  | 100272380 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | RESERVOIR | 114 RESERVOIR RD | 073 | FRA | 2023-03-22 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-03-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1729.42 | 0 | 0 | 0 | 1729.42 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23175309200 |  | 100283574 |  | 6712228A |  |  |  | 565 | EX | SERVICE LINE - REPLACE D253671 | 2621P | PUEBLO | 609 PUEBLO TL | 209 | GEO | 2023-03-22 | DCOLLIN | U137585 | 2023-03-21 | 2023-03-21 | 2023-03-21 |  | DCOLLIN | 2023-03-22 | 2023-03-21 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 51.1833 | 6 | 4688.68 | 3374.78 | 431.24 | 829.86 | 52.8 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23175323900 |  | 100438485 |  | 7328284D |  | U137585 |  | 565 | EX | SERVICE LINE - REPLACE D259797 | 2621P | FOREST | 162 E FOREST AV | 089 | S S | 2023-03-23 | U125208 | U137585 | 2023-03-21 | 2023-03-21 | 2023-03-21 |  | RECUMP | 2023-03-22 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.85 | 1 | 671.83 | 303.25 | 228.3 | 73.18 | 67.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960860800 |  | 500012150 |  | 7356248G | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | PADDLE CREEK | 7940 PADDLE CREEK RD | 019 | CAT | 2023-03-23 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH JERRY NEWSOME | 2023-03-23 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3348 | 0 | 0 | 0 | 3348 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026241500 |  |  |  | 6712212G | 2294097 | U132703 |  | 559 | EX | INSTALL 40'-2" PMMP | 2600B | CUMMINS | 2051 CUMMINS CT | 067 | LEX | 2023-04-29 | U128132 | U132703 | 2022-12-06 | 2023-12-26 | 2023-12-31 | 2023-03-23 | R.HUMPHREYS | 2023-03-23 | 2023-03-21 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP2415 |  |  | 100 | 055932220262415 | 24 | 75 | 14054.24 | 1388.79 | 1207.59 | 317.91 | 8944.76 | 0 | 25.2 | 2169.99 | 25
KY | KY - EAST | 2631 | 22129032700 |  | 100245864 |  | 7360252M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HUCKLEBERRY | 2502 HUCKLEBERRY ST | 019 | CAT | 2023-03-23 | RECUMP | U130722 | 2022-09-05 | 2022-12-30 |  |  | RECUMP | 2023-03-23 | 2023-02-20 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 30.0167 | 7 | 2584.21 | 1951.33 | 19.89 | 612.99 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156271000 |  | 100416771 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 556 CIRCLE DR | 161 | MAY | 2023-03-24 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-23 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1578.39 | 0 | 0 | 0 | 1578.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164552800 |  | 100313092 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | SOUTHBEND | 524 SOUTHBEND DR | 067 | LEX | 2023-03-24 | U128762 | U125763 | 2023-02-02 | 2023-12-29 |  |  | CORY TINCHER | 2023-03-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3626.94 | 0 | 0 | 0 | 3626.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164553700 |  | 100313087 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LONE OAK | 550 LONE OAK DR | 067 | LEX | 2023-03-23 | U124003 | U125763 | 2023-02-02 | 2023-12-29 |  |  | CTINCHER/FISHEL | 2023-03-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1856.07 | 0 | 0 | 0 | 1856.07 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166687700 |  | 100272377 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | COMMONWEALTH | 207 COMMONWEALTH BV | 073 | FRA | 2023-03-23 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-03-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3429.4 | 0 | 0 | 0 | 3429.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166690200 |  | 100272351 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | RESERVOIR | 101 RESERVOIR RD | 073 | FRA | 2023-03-23 | U126308 | U125763 | 2023-02-14 | 2023-12-29 |  |  | J ENSMINGER | 2023-03-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2588.39 | 0 | 0 | 0 | 2588.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166706300 |  | 100309877 |  | 6712208H | 2184394 |  |  | 565 | EX | RPLC SL/22026223700 | 2600B | TUCSON | 2220 TUCSON DR | 067 | LEX | 2023-03-23 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-03-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 1618.65 | 0 | 0 | 0 | 1618.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23171958700 |  | 500135779 |  | 6716208N |  |  |  | 566 | EX | ABANDON 2" ONLY - PER RVANDER | 2621P | GOLD RUSH | 223 GOLD RUSH RD RUN2 | 067 | LEX | 2023-04-03 | U125208 | U125208 | 2023-03-06 | 2023-03-24 | 2023-03-24 |  | KKINDER | 2023-03-23 | 2023-03-15 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP9587 |  |  | 100 | 056632231719587 | 53.3333 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23173837900 |  | 100467615 |  | 6720212J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 7TH | 753 E 7TH ST | 067 | LEX | 2023-03-23 | LSTANFI | U125208 | 2023-03-15 | 2023-04-10 | 2023-05-10 |  | LSTANFI | 2023-03-23 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.2167 | 2 | 900.88 | 312.95 | 0 | 55.43 | 532.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23173838100 |  | 500384367 |  | 6720212J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 7TH | 755< E 7TH ST 1FR | 067 | LEX | 2023-03-23 | LSTANFI | U125208 | 2023-03-15 | 2023-04-10 | 2023-05-10 |  | LSTANFI | 2023-03-23 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.05 | 2 | 105.76 | 98.3 | 0 | 7.46 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23173838300 |  | 500226239 |  | 6720212J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 7TH | 755 E 7TH ST | 067 | LEX | 2023-03-23 | LSTANFI | U125208 | 2023-03-15 | 2023-04-10 | 2023-05-10 |  | LSTANFI | 2023-03-23 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.8833 | 3 | 531.44 | 472.89 | 19.7 | 38.85 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23174597100 |  | 100461787 |  | 6720216E | 1635077 |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HEATHER HILLS | 1056 HEATHER HILLS LN | 067 | LEX | 2023-03-23 | MCRAIG | U125208 | 2023-03-17 | 2023-03-21 | 2023-04-10 |  | MCRAIG | 2023-03-23 | 2023-03-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACN |  | 100 | 056532B26210031 | 17.45 | 5 | 1631.19 | 964.8 | 242.76 | 398.33 | 25.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23174967600 |  | 100304116 |  | 6712208D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D310453 | 2621P | VIOLET | 2112 VIOLET RD | 067 | LEX | 2023-03-23 | U930915 | U125208 | 2023-03-20 | 2023-03-20 | 2023-04-07 |  | KKINDER | 2023-03-23 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.95 | 3 | 1327.89 | 866.46 | 316.39 | 55.94 | 89.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23175988100 |  | 501342865 |  | 67868172A |  |  |  | 566 | EX | PAPER EXECUTE - COMPANY ERROR | 2621P | HUDSON | 126< HUDSON AV | 065 | IRV | 2023-03-23 | U125201 | U125201 | 2023-03-23 | 2023-03-30 |  |  | OFFICE PER NB | 2023-03-23 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - WEST | 2621 | 23176031000 |  | 100312669 |  | 6716208E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309456 | 2621P | LONGVIEW | 591 LONGVIEW DR | 067 | LEX | 2023-03-24 | U930915 | U134822 | 2023-03-23 | 2023-03-23 | 2023-03-23 |  | ABLAKE | 2023-03-23 | 2023-03-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 5.6667 | 2 | 2513.8 | 1667.79 | 682.23 | 107.68 | 56.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23175067200 |  | 100283536 |  | 6712228E |  |  |  | 565 | EX | SERVICE LINE - REPLACE D305599 | 2621P | HIAWATHA | 502 HIAWATHA TL | 209 | GEO | 2023-03-28 | U125208 | U137585 | 2023-03-20 | 2023-03-23 | 2023-04-10 |  | CHERNDO | 2023-03-24 | 2023-03-21 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 25.05 | 5 | 2365.48 | 1581.85 | 260.98 | 452.25 | 70.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23175087300 |  | 100283542 |  | 6712228E | 1635077 |  |  | 565 | EX | SERVICE LINE - REPLACE | 2623D | HIAWATHA | 501 HIAWATHA TL | 209 | GEO | 2023-03-28 | U125208 | AOC SYST | 2023-03-20 | 2023-03-21 | 2024-12-31 |  | CHERNDO | 2023-03-24 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.6 | 2 | 627.4 | 164.89 | 379.25 | 10.66 | 72.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23175675200 |  | 100414495 |  | 6720204F |  |  |  | 565 | EX | SERVICE LINE - REPLACE D310382 | 2621P | HIALEIAH | 1268 HIALEIAH CT | 067 | LEX | 2023-03-24 | U930915 | U125208 | 2023-03-22 | 2023-03-22 | 2023-03-22 |  | RSTRONG | 2023-03-24 | 2023-03-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 30.05 | 6 | 2118.77 | 1542.64 | 165.94 | 335.39 | 74.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23176182900 |  | 100352314 |  | 6744208K |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | CAROLINA | 324 CAROLINA AV | 049 | WIN | 2023-03-24 | NRICHIE | U134852 | 2023-03-24 | 2023-03-24 | 2023-03-24 |  | NRICHIE | 2023-03-24 | 2023-03-24 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 19.6167 | 4 | 2245.25 | 1276.09 | 293.91 | 627.95 | 47.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21900550700 |  | 100339480 |  | 6724212A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | ANNISTON | 1461 ANNISTON DR | 067 | LEX | 2023-03-27 | LSTANFI | AOC SYST | 2021-04-05 | 2022-12-31 | 2022-12-31 |  | LSTANFI | 2023-03-27 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 19.9 | 3 | 1627.62 | 1065 | 283.87 | 217.15 | 61.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21917508700 |  | 100295809 |  | 6716216G | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | KNIGHT | 1995 KNIGHT LN | 067 | LEX | 2023-03-27 | TROE | AOC SYST | 2021-06-08 | 2022-12-31 | 2022-12-31 |  | TROE | 2023-03-27 | 2023-03-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 22.25 | 5 | 2101.39 | 1326.65 | 617.8 | 93.14 | 63.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22138984100 |  | 100324778 |  | 6720204B | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | GAINESWAY | 1137 GAINESWAY DR | 067 | LEX | 2023-03-27 | WISHII | AOC SYST | 2022-10-13 | 2023-04-13 | 2023-12-31 |  | WISHII | 2023-03-27 | 2023-03-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 13.25 | 4 | 1146.83 | 721.27 | 0 | 362.86 | 62.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22138984400 |  | 100324780 |  | 6720204A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | GAINESWAY | 1133 GAINESWAY DR | 067 | LEX | 2023-03-27 | WISHII | AOC SYST | 2022-10-13 | 2023-04-13 | 2023-12-31 |  | WISHII | 2023-03-27 | 2023-03-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 13.9333 | 4 | 1197.86 | 742.32 | 225.39 | 146.55 | 83.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22985445300 |  | 100306667 |  | 6716212I | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | PINE MEADOWS | 1505 PINE MEADOWS RD | 067 | LEX | 2023-03-27 | ABLAKE | AOC SYST | 2022-03-11 | 2023-12-31 | 2023-12-31 |  | ABLAKE | 2023-03-27 | 2023-03-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 26.8167 | 6 | 1998.98 | 1452.56 | 387.66 | 93.86 | 64.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156270400 |  | 100356304 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 549 CIRCLE DR | 161 | MAY | 2023-03-28 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-27 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1860.17 | 0 | 0 | 0 | 1860.17 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156270700 |  | 100356306 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 552 CIRCLE DR | 161 | MAY | 2023-03-28 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-27 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2035.77 | 0 | 0 | 0 | 2035.77 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156270800 |  | 500090660 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 553 CIRCLE DR | 161 | MAY | 2023-03-28 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-27 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1694.95 | 0 | 0 | 0 | 1694.95 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156270900 |  | 100432734 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 555 CIRCLE DR | 161 | MAY | 2023-03-28 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-27 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1680.07 | 0 | 0 | 0 | 1680.07 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156271100 |  | 100356307 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 557 CIRCLE DR | 161 | MAY | 2023-03-28 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-27 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1837.85 | 0 | 0 | 0 | 1837.85 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164549200 |  | 100313126 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LAFAYETTE | 287 LAFAYETTE PY | 067 | LEX | 2023-03-27 | U124003 | U125763 | 2023-02-02 | 2023-12-29 |  |  | BPULLIAM/FISHEL | 2023-03-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2630.74 | 0 | 0 | 0 | 2630.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164550600 |  | 100313150 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LONE OAK | 518 LONE OAK DR | 067 | LEX | 2023-03-28 | U128762 | U125763 | 2023-02-02 | 2023-12-29 |  |  | CORY TINCHER | 2023-03-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4797.7 | 0 | 0 | 0 | 4797.7 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164746600 |  | 500171042 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | CHESTNUT | 505 CHESTNUT ST | 209 | GEO | 2023-03-27 | U128410 | U125763 | 2023-02-03 | 2023-12-29 |  |  | CDESPAIN | 2023-03-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2348.98 | 0 | 0 | 0 | 2348.98 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166687800 |  | 100272360 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | COMMONWEALTH | 210 COMMONWEALTH BV | 073 | FRA | 2023-03-31 | U126308 | U125763 | 2023-02-14 | 2023-12-29 |  |  | J ENSMINGER | 2023-03-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1879.23 | 0 | 0 | 0 | 1879.23 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166690400 |  | 100272352 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | RESERVOIR | 103 RESERVOIR RD | 073 | FRA | 2023-03-27 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-03-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3131.03 | 0 | 0 | 0 | 3131.03 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166690500 |  | 100272353 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | RESERVOIR | 105 RESERVOIR RD | 073 | FRA | 2023-03-27 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-03-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2576.23 | 0 | 0 | 0 | 2576.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176532800 |  | 100319311 |  | 6716208O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LOWRY | 226 E LOWRY LN | 067 | LEX | 2023-03-27 | KKINDER | U137585 | 2023-03-27 | 2023-03-24 | 2023-03-24 |  | KKINDER | 2023-03-27 | 2023-03-24 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 30.25 | 7 | 2393.18 | 1663.46 | 524.44 | 161.28 | 44 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 06663640000 |  | 100459937 |  | 675224J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | WALNUT GROVE | 120 WALNUT GROVE RD | 065 | IRV | 2023-04-05 | U125208 | CTAULBE | 2006-10-19 | 2022-07-01 | 2023-12-31 |  | DENNING | 2023-03-28 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.05 | 3 | 600.72 | 526.17 | 40.56 | 33.99 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 07674512900 |  | 500234598 |  | 6760172D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | STACY LANE | 1744 STACY LANE RD | 065 | IRV | 2023-03-28 | DENNING | SKSMITH | 2007-02-01 | 2022-07-01 | 2023-12-31 |  | DENNING | 2023-03-28 | 2022-06-01 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 12.85 | 5 | 6943.4 | 801.78 | 0 | 51.51 | 6090.11 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 16426429000 |  | 100455431 |  | 6748180P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | COLLEGE HILL | COLLEGE HILL RD | 151 | WAC | 2023-03-29 | U930915 | U122906 | 2016-07-13 | 2022-07-01 | 2023-12-31 |  | DENNING | 2023-03-28 | 2022-10-06 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 11.2333 | 4 | 750.88 | 705.33 | 0 | 45.55 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21895165400 |  | 100288474 |  | 6720212D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | CRICKLEWOOD | 511 CRICKLEWOOD DR | 067 | LEX | 2023-03-29 | U930915 | AOC SYST | 2021-03-17 | 2022-12-31 | 2022-12-31 |  | LSTANFI | 2023-03-28 | 2023-02-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 9.35 | 4 | 852.46 | 516.67 | 200.17 | 78.42 | 57.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129017400 |  | 100465971 |  | 6724212L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WINCHESTER | 2741 WINCHESTER RD | 067 | LEX | 2023-04-05 | U125208 | U130722 | 2022-09-05 | 2022-12-30 |  |  | HMCKUNE | 2023-03-28 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 21.25 | 3 | 3298.71 | 929.81 | 0 | 464.34 | 1904.56 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22979018900 |  | 100247829 |  | 7364188A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | MAIN | 729 E MAIN ST | 159 | INE | 2023-03-28 | JAHOWARD | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | JAHOWARD | 2023-03-28 | 2023-03-08 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 25.3833 | 5 | 1655.15 | 1554.77 | 0 | 100.38 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156269800 |  | 100356299 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 543 CIRCLE DR | 161 | MAY | 2023-03-29 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-28 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1886.19 | 0 | 0 | 0 | 1886.19 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156269900 |  | 100356300 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 544 CIRCLE DR | 161 | MAY | 2023-03-29 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-28 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2312.13 | 0 | 0 | 0 | 2312.13 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156270100 |  | 100356302 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 545 CIRCLE DR | 161 | MAY | 2023-03-29 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-28 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2907.47 | 0 | 0 | 0 | 2907.47 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156270200 |  | 100356301 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 546 CIRCLE DR | 161 | MAY | 2023-03-29 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-28 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2304.69 | 0 | 0 | 0 | 2304.69 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156270300 |  | 100356303 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 547 CIRCLE DR | 161 | MAY | 2023-03-29 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-28 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2120.93 | 0 | 0 | 0 | 2120.93 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156270500 |  | 100416314 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 550 CIRCLE DR | 161 | MAY | 2023-03-28 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-28 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2025.85 | 0 | 0 | 0 | 2025.85 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156270600 |  | 100356305 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 551 CIRCLE DR | 161 | MAY | 2023-03-28 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-28 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1905.27 | 0 | 0 | 0 | 1905.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164549000 |  | 100313134 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LAFAYETTE | 273 LAFAYETTE PY | 067 | LEX | 2023-03-29 | U128762 | U125763 | 2023-02-02 | 2023-12-29 |  |  | CORY TINCHER | 2023-03-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2352.05 | 0 | 0 | 0 | 2352.05 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164552600 |  | 100313093 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | SOUTHBEND | 520 SOUTHBEND DR | 067 | LEX | 2023-03-29 | U128762 | U125763 | 2023-02-02 | 2023-12-29 |  |  | CORY TINCHER | 2023-03-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2608.87 | 0 | 0 | 0 | 2608.87 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165279600 |  | 100294865 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | 4TH | 221 W 4TH ST | 067 | LEX | 2023-03-29 | U129722 | U125763 | 2023-02-07 | 2023-12-29 |  |  | M YOUNG | 2023-03-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2689.94 | 0 | 0 | 0 | 2689.94 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166690600 |  | 100272356 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | RESERVOIR | 106 RESERVOIR RD | 073 | FRA | 2023-03-28 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-03-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2393.93 | 0 | 0 | 0 | 2393.93 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166691400 |  | 100272381 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | RESERVOIR | 116 RESERVOIR RD | 073 | FRA | 2023-03-31 | U126308 | U125763 | 2023-02-14 | 2023-12-29 |  |  | J ENSMINGER | 2023-03-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2115.28 | 0 | 0 | 0 | 2115.28 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23174213300 |  | 100328338 |  | 6720208F | 2395587 |  |  | 565 | EX | NBT - SERVICE/MTR UPGRADE 2" | 2621P | COOPER | 1308 COOPER DR | 067 | LEX | 2023-03-30 | U930915 | U125208 | 2023-03-16 | 2023-03-15 | 2023-03-29 |  | RJCRAWF | 2023-03-28 | 2023-03-22 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 52.7 | 10 | 10248.08 | 2734.42 | 352.52 | 176.34 | 6984.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176532700 |  | 100293885 |  | 6720212A |  |  |  | 565 | EX | REPLACE SL D310454 | 2621P | KEES | 1025 KEES RD | 067 | LEX | 2023-03-29 | U930915 | U137585 | 2023-03-27 | 2023-03-28 | 2023-04-17 |  | LSTANFI | 2023-03-28 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.2667 | 3 | 1584.49 | 904.8 | 376.67 | 222.72 | 80.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176717800 |  | 100294403 |  | 6720212E |  |  |  | 566 | EX | ABANDON SERVICE | 2621P | LIMESTONE | 569 N LIMESTONE ST | 067 | LEX | 2023-03-28 | MCRAIG | U129939 | 2023-03-28 | 2023-03-28 |  |  | MCRAIG | 2023-03-28 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.2667 | 3 | 329.08 | 236.67 | 0 | 92.41 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11899690100 |  | 100284510 |  | X-1103-11 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | FIKE | FIKE RD | 151 | WAC | 2023-03-30 | U930915 | U123933 | 2011-04-04 | 2022-07-01 | 2023-12-31 |  | DENNING | 2023-03-29 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9.1 | 4 | 625.75 | 587.8 | 0 | 37.95 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883049700 |  | 100417512 |  | 7240216J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | MANNIX | MANNIX LN | 173 | MT | 2023-03-29 | U930915 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | DENNING | 2023-03-29 | 2023-03-21 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 18 | 6 | 1224.84 | 1150.53 | 0 | 74.31 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883188200 |  | 100437187 |  | 7364188H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | MAIN | 273 W MAIN ST | 159 | INE | 2023-03-29 | JCKIRK | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JCKIRK | 2023-03-29 | 2023-03-08 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 16.35 | 3 | 1079.31 | 1013.85 | 0 | 65.46 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960862200 |  | 100249825 |  | 7356248H | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | PADDLE CREEK | 8221 PADDLE CREEK RD | 019 | CAT | 2023-03-29 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH JERRY NEWSOME | 2023-03-29 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 4359.17 | 0 | 0 | 0 | 4359.17 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960862400 |  | 100249824 |  | 7356248H | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | PADDLE CREEK | 8227 PADDLE CREEK RD | 019 | CAT | 2023-03-29 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH JERRY NEWSOME | 2023-03-29 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2322.17 | 0 | 0 | 0 | 2322.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026243400 |  |  |  | 6716220C | 2294088 | U461383 |  | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2621M | RESEARCH PARK | 2540 RESEARCH PARK DR | 067 | LEX | 2023-04-04 | U123258 | U461383 | 2022-12-14 | 2023-11-30 | 2023-12-01 | 2023-03-29 | CWEMPE | 2023-03-29 | 2023-03-29 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP2434 |  |  | 100 | 090932220262434 | 12 | 0 | 15857.32 | 715.02 | 0 | 46.17 | 15069.33 | 0 | 26.8 | 0
KY | KY - WEST | 2621 | 22026243500 |  |  |  | 6716220C | 2294088 | U461383 |  | 584 | EX | RETIRE RECORDING GAUGE | 2621M | RESEARCH PARK | 2540 RESEARCH PARK DR | 067 | LEX | 2023-04-04 | U123258 | U461383 | 2022-12-14 | 2023-12-01 | 2023-12-01 | 2023-03-29 | CWEMPE | 2023-03-29 | 2023-03-29 |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00584 | 3200584 |  |  | WP2435 |  |  | 100 | 058432220262435 | 4 | 0 | 241.8 | 227.13 | 0 | 14.67 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22128589400 |  | 100313884 |  | 6716212N | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE SERVICE | 2621D | SOUTHERN | 1308< SOUTHERN AV | 067 | LEX | 2023-03-31 | U930915 | AOC SYST | 2022-09-01 | 2023-03-01 | 2023-12-31 |  | LSTANFI | 2023-03-29 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.1833 | 3 | 675.93 | 342.62 | 207.41 | 41.2 | 84.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22128594500 |  | 100313872 |  | DI16212N | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE SERVICE | 2621D | SOUTHERN | 1315 SOUTHERN AV | 067 | LEX | 2023-04-03 | U930915 | AOC SYST | 2022-09-01 | 2023-03-01 | 2023-12-31 |  | LSTANFI | 2023-03-29 | 2023-03-27 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.3667 | 6 | 1619.4 | 1083.14 | 207.41 | 246.35 | 82.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22138984600 |  | 100324849 |  | 6720204A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | GAINESWAY | 1118 GAINESWAY DR | 067 | LEX | 2023-03-29 | WISHII | AOC SYST | 2022-10-13 | 2023-04-13 | 2023-12-31 |  | WISHII | 2023-03-29 | 2023-03-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 12.1167 | 4 | 1284.07 | 652.79 | 228.07 | 364.71 | 38.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22140027500 |  | 100325204 |  | 6720204A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | GAINESWAY | 1009 GAINESWAY DR | 067 | LEX | 2023-03-30 | U930915 | AOC SYST | 2022-10-19 | 2023-04-19 | 2023-12-31 |  | WISHII | 2023-03-29 | 2023-03-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 13.9 | 5 | 1375.98 | 725.32 | 228.07 | 355.49 | 67.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026269000 |  |  |  | 6696212K | 2396485 | U461383 |  | 557 | EX | EMER-INSTALL 4' OF 2"PMMP MAIN | 2621P | MACK | MACK ST | 239 | VER | 2023-03-30 | U128132 | U461383 | 2023-03-27 | 2023-11-30 | 2023-11-30 | 2023-03-17 | MCOLLINS | 2023-03-29 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP2690 |  |  | 100 | 055732230262690 |  | 4 | 6353.99 | 2593.44 | 0 | 378.53 | 2428.65 | 0 | 7.68 | 945.69 | 4
KY | KY - WEST | 2623 | 23026269100 |  |  |  | 6696212K | 2396485 | U461383 |  | 558 | EX | EMER-RETIRE 4' OF 2"PAMP MAIN | 2621P | MACK | MACK ST | 239 | VER | 2023-03-30 | U128132 | U461383 | 2023-03-27 | 2023-11-30 | 2023-11-30 | 2023-03-17 | MCOLLINS | 2023-03-29 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP2691 |  |  | 100 | 055832230262691 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156269300 |  | 100356296 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 520 CIRCLE DR | 161 | MAY | 2023-03-30 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-29 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2108.53 | 0 | 0 | 0 | 2108.53 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156269500 |  | 100356295 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 527 CIRCLE DR | 161 | MAY | 2023-03-30 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-29 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2306.45 | 0 | 0 | 0 | 2306.45 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156269600 |  | 100356298 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 539 CIRCLE DR | 161 | MAY | 2023-03-30 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-29 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2470.37 | 0 | 0 | 0 | 2470.37 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156269700 |  | 100356297 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 542 CIRCLE DR | 161 | MAY | 2023-03-30 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-29 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2120.93 | 0 | 0 | 0 | 2120.93 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164553900 |  | 100313091 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LONE OAK | 569 LONE OAK DR | 067 | LEX | 2023-03-29 | U124003 | U125763 | 2023-02-02 | 2023-12-29 |  |  | BPULLIAM/FISHEL | 2023-03-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2206.48 | 0 | 0 | 0 | 2206.48 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164768400 |  | 100435103 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | CHESTNUT | 501 CHESTNUT ST | 209 | GEO | 2023-03-31 | U128410 | U125763 | 2023-02-03 | 2023-12-29 |  |  | CDESPAIN | 2023-03-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2296.39 | 0 | 0 | 0 | 2296.39 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166689200 |  | 100272337 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | HAY | 107 HAY AV | 073 | FRA | 2023-03-29 | U126308 | U125763 | 2023-02-14 | 2023-12-29 |  |  | J ENSMINGER | 2023-03-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3103.62 | 0 | 0 | 0 | 3103.62 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166690100 |  | 100272354 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | RESERVOIR | 100 RESERVOIR RD | 073 | FRA | 2023-03-29 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-03-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2168.74 | 0 | 0 | 0 | 2168.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166705700 |  | 100309874 |  | 6712208H | 2184394 |  |  | 565 | EX | RPLC SL/22026223700 | 2600B | TUCSON | 2250 TUCSON DR | 067 | LEX | 2023-03-29 | U461309 | U125763 | 2023-02-14 | 2023-12-29 |  |  | R.HUMPHREYS | 2023-03-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 8 | 1 | 3583.21 | 462.93 | 366.86 | 105.97 | 2647.45 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166706400 |  | 100309844 |  | 6712208H | 2184394 |  |  | 565 | EX | RPLC SL/22026223700 | 2600B | TUCSON | 2221 TUCSON DR | 067 | LEX | 2023-03-29 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-03-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 1622.79 | 0 | 0 | 0 | 1622.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176942400 |  | 100326350 |  | 6720208A |  |  |  | 565 | EX | GRADE 1 REPLACE SERV LINE | 2621P | OLD CASSIDY | 132 OLD CASSIDY AV | 067 | LEX | 2023-03-29 | ABLAKE | U129939 | 2023-03-29 | 2023-03-29 | 2023-03-29 |  | ABLAKE | 2023-03-29 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.4667 | 5 | 3325.08 | 1256.96 | 373.92 | 80.56 | 1613.64 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883075700 |  | 100341102 |  | 7240216L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | OLD OWINGSVILL | OLD OWINGSVILL RD | 173 | MT | 2023-03-31 | U125208 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | DENNING | 2023-03-30 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 6.3333 | 2 | 606.23 | 404.69 | 20.03 | 181.51 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21924513000 |  | 100295987 |  | 6716216O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | LIMA | 488 LIMA DR | 067 | LEX | 2023-03-30 | LSTONE | AOC SYST | 2021-07-09 | 2022-01-07 | 2022-12-31 |  | LSTONE | 2023-03-30 | 2023-03-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 37.4667 | 12 | 2645.64 | 2095.09 | 336.04 | 135.31 | 79.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22140029300 |  | 100325202 |  | 6720204A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | GAINESWAY | 1013 GAINESWAY DR | 067 | LEX | 2023-03-30 | WISHII | AOC SYST | 2022-10-19 | 2023-04-19 | 2023-12-31 |  | WISHII | 2023-03-30 | 2023-03-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 19.85 | 7 | 1809.86 | 1008.18 | 348.7 | 385.88 | 67.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156269200 |  | 100356293 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 504 CIRCLE DR | 161 | MAY | 2023-03-30 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-30 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2737.39 | 0 | 0 | 0 | 2737.39 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156269400 |  | 100356294 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 525 CIRCLE DR | 161 | MAY | 2023-03-30 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-03-30 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2210.33 | 0 | 0 | 0 | 2210.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164552000 |  | 100313089 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LONE OAK | 561 LONE OAK DR | 067 | LEX | 2023-03-31 | U128762 | U125763 | 2023-02-02 | 2023-12-29 |  |  | CORY TINCHER | 2023-03-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4364.52 | 0 | 0 | 0 | 4364.52 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164758200 |  | 100281522 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | OAK | 513 OAK ST | 209 | GEO | 2023-03-30 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-03-30 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.7833 | 1 | 3235.42 | 335.83 | 0 | 76.83 | 2822.76 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166690800 |  | 100272357 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | RESERVOIR | 108 RESERVOIR RD | 073 | FRA | 2023-03-30 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-03-30 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2512.81 | 0 | 0 | 0 | 2512.81 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166706200 |  | 100309849 |  | 6712208H | 2184394 |  |  | 565 | EX | RPLC SL/22026223700 | 2600B | TUCSON | 2321 TUCSON DR | 067 | LEX | 2023-03-30 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-03-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 1615.89 | 0 | 0 | 0 | 1615.89 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166707100 |  | 100309868 |  | 6712208H | 2184394 |  |  | 565 | EX | RPLC SL/22026223700 | 2600B | TUCSON | 2310 TUCSON DR | 067 | LEX | 2023-03-30 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-03-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 1626.93 | 0 | 0 | 0 | 1626.93 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166707500 |  | 100309876 |  | 6712208H | 2184394 |  |  | 565 | EX | RPLC SL/22026223700 | 2600B | TUCSON | 2230 TUCSON DR | 067 | LEX | 2023-03-30 | U461309 | U125763 | 2023-02-14 | 2023-12-29 |  |  | R.HUMPHREYS | 2023-03-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 8 | 1 | 3473.3 | 462.93 | 258.33 | 105.97 | 2646.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23169605700 |  | 100316872 |  | 6716208J |  |  |  | 565 | EX | NBT - SERV LINE/MTR UPG 85'2" | 2621P | SOUTHLAND | 225 SOUTHLAND DR | 067 | LEX | 2023-03-30 | U930915 | U125208 | 2023-02-28 | 2023-02-28 | 2023-03-28 |  | RJCRAWF | 2023-03-30 | 2023-03-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 50.0833 | 15 | 4881.08 | 2634.58 | 505.9 | 185.14 | 1555.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176175700 |  | 500309329 |  | 6724208P | 1635077 |  |  | 565 | VO | REPLACE SERVICE LINE - D310327 | 2621P | DEER CROSSING | 984 DEER CROSSING WY | 067 | LEX | 2023-04-05 | SSHIMFE | U125208 | 2023-03-24 | 2023-03-24 | 2023-04-13 |  | SSHIMFE | 2023-03-30 | 2023-03-30 |  | A | [11 empty] | 23179175300 | 100 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23177177900 |  | 100311758 |  | 6716208I | 1313369 |  |  | 565 | EX | REPLACE GAS SERVICE | 2621P | SOUTHVIEW | 2817 SOUTHVIEW DR | 067 | LEX | 2023-03-30 | KKINDER | U130871 | 2023-03-30 | 2023-03-30 | 2023-03-30 |  | KKINDER | 2023-03-30 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.2833 | 3 | 1706.71 | 1005.86 | 571.01 | 64.94 | 64.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 07679068100 |  | 500729835 |  | V-940-60 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | FRANKFORT | 4182 FRANKFORT RD | 209 | GEO | 2023-04-10 | U126332 | DMCCULL | 2007-03-15 | 2022-07-01 | 2023-12-31 |  | J. PARKS | 2023-03-31 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 1.0333 | 1 | 136.96 | 58.32 | 0 | 78.64 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07689207700 |  | 100300647 |  | 6716212K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FERGUSON | 449 FERGUSON ST | 067 | LEX | 2023-04-04 | U125208 | U903504 | 2007-06-01 | 2020-12-31 |  |  | WISHII | 2023-03-31 | 2023-03-31 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.5 | 3 | 360.94 | 240.3 | 0 | 120.64 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07689208000 |  | 100291544 |  | ? |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PARIS | 2313 PARIS PK | 067 | LEX | 2023-03-31 | LSTONE | U903504 | 2007-06-01 | 2020-12-31 |  |  | LSTONE | 2023-03-31 | 2023-03-31 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3 | 2 | 190.23 | 178.7 | 0 | 11.53 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 09808406900 |  | 100336489 |  | 16720212I |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | 4TH | 266 E 4TH ST B | 067 | LEX | 2023-04-03 | U930915 | RPOLLY | 2009-10-19 | 2020-12-23 |  |  | LSTANFI | 2023-03-31 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.2 | 3 | 592.1 | 491.96 | 0 | 100.14 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11894719900 |  | 100294557 |  | ? |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BROADWAY | 530 N BROADWAY ST 3 | 067 | LEX | 2023-03-31 | U930915 | U124961 | 2011-03-08 | 2020-12-31 |  |  | LSTONE | 2023-03-31 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.85 | 2 | 174.23 | 163.67 | 0 | 10.56 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11899015800 |  | 100336021 |  | 16720212K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HIGHLAND | 905 HIGHLAND DR | 067 | LEX | 2023-04-03 | U930915 | U906631 | 2011-04-01 | 2020-12-31 |  |  | LSTANFI | 2023-03-31 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.4 | 3 | 93.15 | 77.41 | 0 | 15.74 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11905213900 |  | 100338748 |  | V-1021-44 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAPLE | 758 MAPLE AV 1FR | 067 | LEX | 2023-04-03 | U930915 | U124961 | 2011-05-05 | 2020-12-31 |  |  | LSTANFI | 2023-03-31 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.4 | 3 | 867.77 | 721.03 | 0 | 146.74 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12971488100 |  | 100298378 |  | 6716212H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SHORT | 628 W SHORT ST 1F | 067 | LEX | 2023-04-04 | U125208 | U125208 | 2012-05-29 | 2020-12-31 |  |  | WISHII | 2023-03-31 | 2023-03-31 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.65 | 3 | 216.43 | 144.13 | 0 | 72.3 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12992692900 |  | 100459166 |  | ? |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BROADWAY | 263 N BROADWAY ST BSM | 067 | LEX | 2023-03-31 | U930915 | U123694 | 2012-10-11 | 2020-12-31 |  |  | LSTONE | 2023-03-31 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.5 | 2 | 215.71 | 202.64 | 0 | 13.07 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 20026944900 |  | 100403681 |  | 7340268A | 2072743 | U132280 |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 311 MAIN ST | 089 | GRE | 2023-08-04 | U128132 | U461492 | 2020-04-09 | 2022-12-29 |  | 2020-04-20 | BROBERT | 2023-03-31 | 2023-02-21 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP9449 |  |  | 100 | 056632200269449 | 21.7 | 6 | 5427.36 | 3161.01 | 764.39 | 1501.96 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21026130200 |  |  |  | 7344268N | 2180888 | U132280 |  | 557 | EX | EMER-INSTALL 5'-2" PMIP/CSIP | 2621P | CENTRAL | 610 CENTRAL AV | 089 | WUR | 2023-05-16 | U128132 | U132280 | 2021-06-29 | 2022-09-29 | 2023-05-13 | 2021-06-29 | BROBERTS | 2023-03-31 | 2023-03-24 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP1302 | AMRCB |  | 100 | 055732210261302 | 8.0167 | 18 | 7558.85 | 3164.07 | 0 | 3533.85 | 0 | 0 | -43.08 | 904.01 | 6
KY | KY - EAST | 2631 | 21026130300 |  |  |  | 7344268N | 2180888 | U132280 |  | 558 | EX | EMER-RETIRE 5'-2" BSIP | 2621P | CENTRAL | 610 CENTRAL AV | 089 | WUR | 2023-05-16 | U128132 | U132280 | 2021-06-29 | 2022-09-30 | 2023-05-13 | 2021-06-29 | BROBERTS | 2023-03-31 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP1303 | AMRCB |  | 100 | 055832210261303 | 1.9167 | 0 | 230.72 | 117.67 | 0 | 113.05 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883169400 |  | 501147462 |  | 6744184G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | CHARLIE NORRIS | 1129 CHARLIE NORRIS RD | 151 | RIC | 2023-03-31 | U930915 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | DENNING | 2023-03-31 | 2022-12-06 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 20.1167 | 7 | 3214.22 | 1333.58 | 0 | 251.8 | 1628.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883313400 |  | 100343604 |  | 7240212B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | RICHMOND | 286 RICHMOND AV | 173 | MT | 2023-03-31 | U930915 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | DENNING | 2023-03-31 | 2022-10-05 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 7.0167 | 4 | 461.59 | 433.6 | 0 | 27.99 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165279500 |  | 100294861 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | 4TH | 217 W 4TH ST 1 | 067 | LEX | 2023-03-31 | U129722 | U125763 | 2023-02-07 | 2023-12-29 |  |  | M YOUNG | 2023-03-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3888.3 | 0 | 0 | 0 | 3888.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23177179600 |  | 100295989 |  | 6716216O | 1635077 |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | LIMA | 490 LIMA DR | 067 | LEX | 2023-03-31 | LSTONE | U130871 | 2023-03-30 | 2023-03-30 |  |  | LSTONE | 2023-03-31 | 2023-03-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.3667 | 3 | 1462.7 | 617.92 | 266.66 | 39.92 | 538.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23177179800 |  | 100295988 |  | 6716216O | 1635077 |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | LIMA | 492 LIMA DR | 067 | LEX | 2023-04-04 | U125208 | U130871 | 2023-03-30 | 2023-03-30 |  |  | LSTONE | 2023-03-31 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 1.6833 | 2 | 191.64 | 95.82 | 89.61 | 6.21 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23177290600 |  | 100350009 |  | 6744204D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303632 | 2621P | AUTUMN | 180 AUTUMN CT | 049 | WIN | 2023-03-31 | NRICHIE | U125208 | 2023-03-30 | 2023-03-30 | 2023-03-30 |  | NRICHIE | 2023-03-31 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 14.1333 | 2 | 2979.81 | 963.88 | 1493.32 | 470.91 | 51.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21900548900 |  | 100289303 |  | 6724212A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | GREENLEAF | 600 GREENLEAF CT | 067 | LEX | 2023-04-04 | U930915 | AOC SYST | 2021-04-05 | 2021-10-05 | 2022-12-31 |  | LSTANFI | 2023-04-03 | 2023-02-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 12.35 | 4 | 1079.6 | 706.29 | 199.64 | 128.57 | 45.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026168000 |  |  |  | 6688288D | 2286582 | GSULLI1 |  | 909 | EX | HVAC AND RTU PANEL UPGRADE | 2600E | US 460 - GEORGETOWN RD | US 460 - GEORGETOWN RD | 073 | FRA | 2023-04-04 | U123258 | GSULLI1 | 2022-02-15 | 2022-12-29 | 2022-12-31 | 2023-04-03 | WADE SHIMFESSEL | 2023-04-03 | 2022-10-27 |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00909 | 3200909 |  |  | WP1680 |  |  | 100 | 090932220261680 | 28.6667 | 0 | 22883.04 | 1761.27 | 0 | 103.63 | 20385 | 0 | 633.14 | 0
KY | KY - WEST | 2623 | 22026214500 |  |  |  | 6688288D | 2286582 | GSULLI1 |  | 910 | EX | JIM BEAN RTU PANEL | 2621M | US 460 - GEORGETOWN RD | US 460 - GEORGETOWN RD | 073 | FRA | 2023-04-04 | U123258 | U136124 | 2022-07-28 | 2023-12-29 | 2023-12-31 | 2023-04-03 | WADE SHIMFESSEL | 2023-04-03 | 2022-10-26 |  | F | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00910 | 3200910 |  |  | WP2145 |  |  | 100 | 091032220262145 | 30.8667 | 0 | 2091.18 | 1978.36 | 0 | 112.82 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026257000 |  |  |  | 6716212N | 2294088 | U134275 |  | 910 | EX | ST JOE - RETIRE RTU | 2600E | HARRODSBURG | 1590 HARRODSBURG RD | 067 | LEX | 2023-05-04 | U123258 | U134275 | 2023-02-14 | 2023-12-29 | 2023-12-31 | 2023-04-03 | EBLANTON | 2023-04-03 | 2023-04-03 |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00910 | 3200910 |  |  | WP2570 |  |  | 100 | 091032230262570 | 4.45 | 0 | 310.19 | 294.14 | 0 | 16.05 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026271200 |  |  |  | 6716212N | 2294088 | U461383 |  | 587 | EX | INSTALL LEGACY ERX | 2600M | HARRODSBURG | 1400 HARRODSBURG RD | 067 | LEX | 2023-07-17 | U123258 | U461383 | 2023-04-10 | 2003-12-01 | 2023-12-01 | 2023-04-03 | EBLANTON | 2023-04-03 |  |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00587 | 3200587 |  |  | WP2712 |  |  | 100 | 058732230262712 |  | 0 | 2465.58 | 224.48 | 0 | 12.51 | 1830 | 0 | 5.86 | 392.73
KY | KY - CENTRAL | 2632 | 23156272300 |  | 100356316 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 589 CIRCLE DR | 161 | MAY | 2023-04-04 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-03 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2084.79 | 0 | 0 | 0 | 2084.79 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156272500 |  | 100356319 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 593 CIRCLE DR | 161 | MAY | 2023-04-03 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-03 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2188.83 | 0 | 0 | 0 | 2188.83 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156272700 |  | 100356321 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 596 CIRCLE DR | 161 | MAY | 2023-04-04 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-03 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2374.59 | 0 | 0 | 0 | 2374.59 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164551400 |  | 100313146 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LONE OAK | 534 LONE OAK DR | 067 | LEX | 2023-04-03 | U124003 | U125763 | 2023-02-02 | 2023-12-29 |  |  | BPULLIAM/FISHEL | 2023-04-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1335.98 | 0 | 0 | 0 | 1335.98 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164552300 |  | 100313094 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | SOUTHBEND | 508 SOUTHBEND DR | 067 | LEX | 2023-04-03 | U124003 | U125763 | 2023-02-02 | 2023-12-29 |  |  | BPULLIAM/FISHEL | 2023-04-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2748.74 | 0 | 0 | 0 | 2748.74 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164747000 |  | 100281568 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | CHESTNUT | 511 CHESTNUT ST | 209 | GEO | 2023-04-03 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-04-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.05 | 1 | 2449.32 | 314.9 | 0 | 77.53 | 2056.89 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166691000 |  | 100272358 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | RESERVOIR | 110 RESERVOIR RD | 073 | FRA | 2023-04-03 | U126309 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JAMIE LYNN | 2023-04-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2018.36 | 0 | 0 | 0 | 2018.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23175675100 |  | 100335598 |  | 6716220C |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | IRON WORKS | 3250 IRON WORKS PK 2819 | 067 | LEX | 2023-04-03 | TROE | U133234 | 2023-03-22 | 2023-04-05 | 2023-04-21 |  | TROE | 2023-04-03 | 2023-03-24 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.75 | 5 | 867.32 | 817.74 | 0 | 49.58 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23176725500 |  | 500298389 |  | 7352260F |  |  |  | 565 | EX | SERVICE LINE - REPL/REMODEL | 2621P | RUSSELL | 410 RUSSELL RD | 089 | RUS | 2023-04-03 | BMEEK | U125208 | 2023-03-28 | 2023-03-31 | 2023-04-18 |  | BMEEK | 2023-04-03 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 16.2167 | 4 | 1501.71 | 1033.18 | 20.27 | 388.86 | 59.4 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23176979300 |  | 100285439 |  | 6764176P |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTRQD | 2621P | ROSE | 203 ROSE ST | 065 | IRV | 2023-04-03 | DENNING | U137008 | 2023-03-29 | 2023-04-12 | 2023-04-28 |  | DENNING | 2023-04-03 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 21.1 | 3 | 1438.24 | 1363.87 | 0 | 74.37 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21900910200 |  | 100289314 |  | 6724212A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | KINGTREE | 1931 KINGTREE DR | 067 | LEX | 2023-04-05 | U930915 | AOC SYST | 2021-04-06 | 2021-10-06 | 2022-12-31 |  | LSTANFI | 2023-04-04 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 7.0167 | 3 | 718.2 | 395.66 | 191.94 | 72.3 | 58.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026240100 |  |  |  | 6720204B | 2293764 | U461383 |  | 588 | EX | GMB TO CAB CONVERSION | 2600M | CENTRE | 1310 CENTRE PY | 067 | LEX | 2023-04-13 | U123258 | U461383 | 2022-11-18 | 2023-08-01 | 2023-08-01 | 2023-04-04 | SMCHOLAN | 2023-04-04 | 2023-03-31 |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00588 | 3200588 |  |  | WP2401 |  |  | 100 | 058832220262401 | 29.0667 | 0 | 2136.59 | 1895.74 | 0 | 240.85 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026244400 |  |  |  | 6760172K | 2294088 | U461383 |  | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2621M | PEA RIDGE | PEA RIDGE RD | 065 | IRV | 2023-07-17 | U123258 | U461383 | 2022-12-15 | 2023-11-30 | 2023-12-01 | 2023-04-04 | JOSH MARTIN | 2023-04-04 | 2023-03-27 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00909 | 3200909 |  |  | WP2444 |  |  | 100 | 090932220262444 | 30.3 | 0 | 17382.14 | 1889.99 | 0 | 326.34 | 15069.33 | 0 | 96.48 | 0
KY | KY - WEST | 2621 | 22129081300 |  | 100289341 |  | 6724212A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KINGTREE | 1932 KINGTREE DR | 067 | LEX | 2023-04-05 | U930915 | U130722 | 2022-09-05 | 2022-12-30 |  |  | LSTANFI | 2023-04-04 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.8 | 3 | 225.2 | 160.12 | 48.13 | 16.95 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026249500 |  | 501331107 |  | 6716232I | 2294450 | U126783 |  | 555 | EX | INSTALL 870'-2" PMMP | 2600B | IKEBANA | 150 IKEBANA DR | 209 | GEO | 2023-06-20 | U128132 | U126783 | 2023-01-16 | 2023-04-04 | 2023-04-15 | 2023-04-04 | STEVE CANOY | 2023-04-04 | 2023-03-20 | 2023-03-21 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2495 |  |  | 100 | 055532230262495 | 92 | 11388 | 52378.28 | 5500.47 | 2461.29 | 2033.83 | 33863.19 | 0 | 227.18 | 8292.32 | 876
KY | KY - WEST | 2623 | 23026260600 |  |  |  | 6692228M | 1100065 | U461383 |  | 588 | EX | GMB TO CAB CONVERSION | 2600M | COMMERCE | 141 COMMERCE BV | 073 | FRA | 2023-04-12 | U123258 | U461383 | 2023-02-16 | 2023-12-01 | 2023-12-01 | 2023-04-04 | GHALE | 2023-04-04 | 2023-03-31 |  | F | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00588 | 3200588 |  |  | WP2606 |  |  | 100 | 058832230262606 | 14.1667 | 0 | 1404.11 | 923.89 | 0 | 480.22 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156272200 |  | 100356315 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 587 CIRCLE DR | 161 | MAY | 2023-04-04 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-04 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2612.33 | 0 | 0 | 0 | 2612.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164549100 |  | 100313133 |  | 6716208A | 2181472 |  |  | 565 | EX | RPLC SL/22026184800 | 2600B | LAFAYETTE | 275 LAFAYETTE PY | 067 | LEX | 2023-04-04 | U124003 | U125763 | 2023-02-02 | 2023-12-29 |  |  | BPULLIAM/FISHEL | 2023-04-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4427.96 | 0 | 0 | 0 | 4427.96 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164746400 |  | 100433394 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | CHESTNUT | 504 CHESTNUT ST | 209 | GEO | 2023-04-04 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-04-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.15 | 1 | 3115.12 | 383.51 | 0 | 94.43 | 2637.18 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166694700 |  | 100272347 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 120 TANGLEWOOD DR | 073 | FRA | 2023-04-04 | U126309 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JAMIE LYNN | 2023-04-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2721.64 | 0 | 0 | 0 | 2721.64 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166695300 |  | 100272321 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 129 TANGLEWOOD DR | 073 | FRA | 2023-04-04 | U126309 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JAMIE LYNN | 2023-04-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2142.54 | 0 | 0 | 0 | 2142.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166705300 |  | 100309791 |  | 6712208H | 2184394 |  |  | 565 | EX | RPLC SL/22026223700 | 2600B | TOPEKA | 2401 TOPEKA RD | 067 | LEX | 2023-04-04 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-04-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 1562.55 | 0 | 0 | 0 | 1562.55 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23178744500 |  | 100310365 |  | 6716208A |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309459 | 2621P | MITCHELL | 629 MITCHELL AV | 067 | LEX | 2023-04-05 | U930915 | U125208 | 2023-04-03 | 2023-04-03 | 2023-04-03 |  | RJCRAWF | 2023-04-04 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 29.6167 | 3 | 2351.85 | 1641.49 | 521.82 | 89.54 | 99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23178894300 |  | 100295221 |  | 6716212D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HASKINS | 563 HASKINS DR | 067 | LEX | 2023-04-04 | U930915 | U129939 | 2023-04-04 | 2023-05-01 | 2024-11-30 |  | LSTONE | 2023-04-04 | 2023-03-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.8167 | 8 | 2157.82 | 1649.59 | 343.75 | 94.08 | 70.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24247867600 |  | 100282950 |  | 6712228B | 2293665 |  |  | 565 | EX | RPLC SL/22026236900 | 2600B | ESTILL | 520 ESTILL CT | 209 | GEO | 2024-04-04 | U461443 | U125763 | 2024-02-27 | 2024-12-31 |  |  | WILLIAM GRAVES | 2023-04-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3281.78 | 0 | 0 | 0 | 3281.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11894359300 |  | 100318494 |  | 1 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HIGHTOWER | 284 HIGHTOWER RD | 067 | LEX | 2023-04-05 | U930915 | U124961 | 2011-03-04 | 2020-12-31 |  |  | DMARSTO | 2023-04-05 | 2023-04-05 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1 | 2 | 65.51 | 62.12 | 0 | 3.39 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11898923500 |  | 100409483 |  | 6716204B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NICHOLASVILLE | 3401 NICHOLASVILLE RD STE 220 | 067 | LEX | 2023-04-05 | U930915 | U906631 | 2011-03-31 | 2020-12-31 | 2023-04-20 |  | DMARSTO | 2023-04-05 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.5 | 2 | 163.32 | 154.88 | 0 | 8.44 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11927124700 |  | 100269870 |  | 6732252P |  |  |  | 566 | EX | PAPER ABANDON - IDLE/INACTIVE | 2621P | PLEASANT | 473 W PLEASANT ST G | 097 | CYN | 2023-04-05 | ASNICHO | U125208 | 2011-09-30 | 2020-12-31 |  |  | ASNICHO | 2023-04-05 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.3833 | 1 | 365.87 | 215.67 | 0 | 150.2 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11927128700 |  | 100404233 |  | 6732252O |  |  |  | 566 | EX | PAPER ABANDON - IDLE/INACTIVE | 2621P | 5TH | 206 5TH ST B | 097 | CYN | 2023-04-05 | ASNICHO | U125208 | 2011-09-30 | 2049-12-31 | 2049-12-31 |  | ASNICHO | 2023-04-05 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.3333 | 1 | 143.32 | 84.5 | 0 | 58.82 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026266800 |  |  |  | 6740228A | 2396250 | U128885 |  | 557 | EX | EMER - INSTALL 7'-2" PMMP | 2621P | VINE | 1152 VINE ST | 017 | PAR | 2023-05-18 | U128132 | U128885 | 2023-03-16 | 2023-11-10 |  | 2023-03-03 | NRICHIE | 2023-04-05 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP2668 |  |  | 100 | 055732230262668 |  | 7 | 537.54 | 0 | 451.56 | 0 | 0 | 0 | 1.04 | 84.94 | 7
KY | KY - CENTRAL | 2629 | 23026266900 |  |  |  | 6740228A | 2396250 | U128885 |  | 558 | EX | EMER - RETIRE 7'-2" PMAP | 2621P | VINE | 1152 VINE | 017 | PAR | 2023-04-05 | U128132 | U128885 | 2023-03-16 | 2023-11-30 |  | 2023-03-03 | NRICHIE | 2023-04-05 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP2669 |  |  | 100 | 055832230262669 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026267000 |  |  |  | 6732252P | 2396253 | U128885 |  | 557 | EX | EMER - INSTALL 2'-2" PMLP | 2621P | ELM | ELM ST | 097 | CYN | 2023-05-18 | U128132 | U128885 | 2023-03-16 | 2023-11-29 |  | 2023-03-07 | NRICHIE | 2023-04-05 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP2670 |  |  | 100 | 055732230262670 |  | 2 | 1235.74 | 499.13 | 481.61 | 57.22 | 0 | 0 | 2.53 | 195.25 | 2
KY | KY - CENTRAL | 2629 | 23026267100 |  |  |  | 6732252P | 2396253 | U128885 |  | 558 | EX | EMER - RETIRE 2'-2" PLP | 2621P | ELM | ELM ST | 097 | CYN | 2023-04-11 | U128132 | U128885 | 2023-03-16 | 2023-11-29 |  | 2023-03-07 | NRICHIE | 2023-04-05 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP2671 |  |  | 100 | 055832230262671 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156271600 |  | 100356311 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 569 CIRCLE DR | 161 | MAY | 2023-04-06 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-05 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2110.62 | 0 | 0 | 0 | 2110.62 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156271700 |  | 100356313 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 571 CIRCLE DR | 161 | MAY | 2023-04-06 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-05 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 | 8 | 1 | 2417.32 | 510.75 | 0 | 27.86 | 1878.71 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156271900 |  | 100356314 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 575 CIRCLE DR | 161 | MAY | 2023-04-06 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-05 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1861.35 | 0 | 0 | 0 | 1861.35 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23159176500 |  | 100402252 |  | 6744288I | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER | 2632D | WILLOW LNXBURG | 5108 WILLOW LNXBURG RD | 023 | FOS | 2023-04-05 | SDADAMS | AOC SYST | 2023-01-30 | 2023-02-24 | 2023-03-28 |  | SDADAMS | 2023-04-05 | 2023-02-28 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 | 23.5667 | 5 | 1908.21 | 1576.06 | 212.14 | 88.11 | 31.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166695600 |  | 100272382 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 200 TANGLEWOOD DR | 073 | FRA | 2023-04-05 | U126309 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JAMIE LYNN | 2023-04-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1771.64 | 0 | 0 | 0 | 1771.64 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166696100 |  | 100272311 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 205 TANGLEWOOD DR | 073 | FRA | 2023-04-05 | U126309 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JAMIE LYNN | 2023-04-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1639 | 0 | 0 | 0 | 1639 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166706800 |  | 100309796 |  | 6712208H | 2184394 |  |  | 565 | EX | RPLC SL/22026223700 | 2600B | TOPEKA | 2400 TOPEKA RD | 067 | LEX | 2023-04-05 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-04-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 3741.86 | 0 | 0 | 0 | 3741.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166707000 |  | 100309792 |  | 6712208H | 2184394 |  |  | 565 | EX | RPLC SL/22026223700 | 2600B | TOPEKA | 2405 TOPEKA RD | 067 | LEX | 2023-04-05 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-04-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 1288.46 | 0 | 0 | 0 | 1288.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23174290500 |  | 100330156 |  | 6720208B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309483 | 2621P | QUEENSWAY | 236 QUEENSWAY DR | 067 | LEX | 2023-04-05 | TROE | U125208 | 2023-03-16 | 2023-09-15 | 2025-03-31 |  | TROE | 2023-04-05 | 2023-04-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 31.4 | 4 | 2259.55 | 1807.69 | 254.28 | 98.58 | 99 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23174664200 |  | 500449430 |  | 7348260H | 2396088 |  |  | 565 | EX | NBT - SERVICE/METER UPG 1"P | 2621P | SUNSET | 600 SUNSET DR | 089 | ASH | 2023-04-05 | BMEEK | U125208 | 2023-03-17 | 2023-03-20 | 2023-03-31 |  | BMEEK | 2023-04-05 | 2023-04-04 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 29.0167 | 6 | 2659.77 | 1834.65 | 295.08 | 399.14 | 130.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23178740900 |  | 100303081 |  | 6712208C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309458 | 2621P | LANSILL | 2155 LANSILL RD | 067 | LEX | 2023-04-06 | U930915 | U125208 | 2023-04-03 | 2023-04-06 | 2023-04-24 |  | ABLAKE | 2023-04-05 | 2023-04-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 22.8167 | 3 | 1864.77 | 1441.53 | 285.23 | 78.61 | 59.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23178951500 |  | 100344530 |  | 6700224O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D308938 | 2621P | HIGGINS | 238 W HIGGINS ST | 239 | MID | 2023-04-05 | U128410 | U125208 | 2023-04-04 | 2023-04-04 | 2023-04-04 |  | CDESPAIN | 2023-04-05 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 16 | 2 | 2614.93 | 2118.72 | 299.25 | 115.56 | 81.4 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179262800 |  | 100406899 |  | 7344268O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CALUMET | 1476 W CALUMET DR | 089 | WOR | 2023-04-06 | UIPBOT12 | U137585 | 2023-04-05 | 2023-04-05 | 2023-04-05 |  | BMEEK | 2023-04-05 | 2023-04-05 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 5.4833 | 4 | 815.08 | 358.34 | 214.4 | 162.04 | 80.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 07680905100 |  | 100452691 |  | 6732252P |  |  |  | 566 | EX | PAPER ABANDON - IDLE/INACTIVE | 2621P | 1ST | 114 1ST ST A | 097 | CYN | 2023-04-06 | ASNICHO | DMCCULL | 2007-03-29 | 2020-12-31 |  |  | ASNICHO | 2023-04-06 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.66667 | 1 | 72.77 | 42.91 | 0 | 29.86 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 14270122800 |  | 500192389 |  | 6732252P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LOCUST | 112 N LOCUST ST UP | 097 | CYN | 2023-04-06 | U930915 | U122906 | 2014-12-11 | 2049-12-25 |  |  | ASNICHO | 2023-04-06 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.6333 | 1 | 245.26 | 168.3 | 0 | 76.96 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22139749100 |  | 100325005 |  | 6720204E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | GREENTREE | 3536 GREENTREE RD | 067 | LEX | 2023-04-06 | U126308 | AOC SYST | 2022-10-18 | 2023-04-18 | 2023-12-31 |  | J ENSMINGER | 2023-04-06 | 2023-04-04 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 16.9667 | 5 | 1551.43 | 1065.57 | 324.5 | 96.46 | 64.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026265400 |  |  |  | 6720212M | 2396041 | U134275 |  | 559 | EX | EMER - INSTALL 12' - 2" PMMP | 2621P | DESHA | 232 DESHA RD | 067 | LEX | 2023-08-07 | U136251 | U134275 | 2023-03-07 | 2023-03-08 |  | 2023-04-06 | LSTANFI | 2023-04-06 | 2023-03-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP2654 |  |  | 100 | 055932230262654 | 74.8833 | 240 | 9462.49 | 3648.71 | 0 | 834.08 | 3431.47 | 0 | 33.66 | 1514.57 | 12
KY | KY - WEST | 2621 | 23026265500 |  |  |  | 6720212M | 2396041 | U134275 |  | 560 | EX | EMER - RETIRE 12' - 2" PMMP | 2621P | DESHA | 232 DESHA RD | 067 | LEX | 2023-06-08 | U136251 | U134275 | 2023-03-07 | 2023-03-08 |  | 2023-04-06 | LSTANFI | 2023-04-06 | 2023-03-14 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00560 | 3200560 |  |  | WP2655 |  |  | 100 | 056032230262655 | 3.8333 | 0 | 165.55 | 155.5 | 0 | 10.05 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166695500 |  | 100272319 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 135 TANGLEWOOD DR | 073 | FRA | 2023-04-06 | U126309 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JAMIE LYNN | 2023-04-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1859.34 | 0 | 0 | 0 | 1859.34 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166696000 |  | 100272383 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 204 TANGLEWOOD DR | 073 | FRA | 2023-04-06 | U126309 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JAMIE LYNN | 2023-04-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1750.04 | 0 | 0 | 0 | 1750.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21895867200 |  | 100288591 |  | 6720212D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | BRYANWOOD | 412 BRYANWOOD PY | 067 | LEX | 2023-04-07 | LSTONE | AOC SYST | 2021-03-19 | 2021-09-17 | 2022-12-31 |  | LSTONE | 2023-04-07 | 2023-04-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 5.9 | 3 | 597.56 | 350.85 | 170.34 | 19.17 | 57.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156271300 |  | 100433732 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 565 CIRCLE DR | 161 | MAY | 2023-04-07 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-07 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1833.03 | 0 | 0 | 0 | 1833.03 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156271400 |  | 100356310 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 567 CIRCLE DR | 161 | MAY | 2023-04-07 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-07 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1913.32 | 0 | 0 | 0 | 1913.32 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156272100 |  | 100418244 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 585 CIRCLE DR | 161 | MAY | 2023-04-11 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-07 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2233.11 | 0 | 0 | 0 | 2233.11 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156272800 |  | 100356323 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 597 CIRCLE DR | 161 | MAY | 2023-04-07 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-07 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1871.27 | 0 | 0 | 0 | 1871.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166705500 |  | 100309793 |  | 6712208H | 2184394 |  |  | 565 | EX | RPLC SL/22026223700 | 2600B | TOPEKA | 2409 TOPEKA RD | 067 | LEX | 2023-04-07 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-04-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 1333.36 | 0 | 0 | 0 | 1333.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23171925600 |  | 100311984 |  | 6716208I |  |  |  | 565 | EX | SERVICE LINE - REPL W/MC - MMO | 2621P | SOUTHVIEW | 2614 SOUTHVIEW DR | 067 | LEX | 2023-04-07 | U126308 | U125208 | 2023-03-06 | 2023-03-09 | 2023-03-27 |  | J ENSMINGER | 2023-04-07 | 2023-03-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 36.7167 | 13 | 2882.45 | 2130.81 | 556.24 | 118.4 | 77 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23173362300 |  | 100244473 |  | 7356256K |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | 39TH | 513 39TH ST | 019 | ASH | 2023-04-07 | BMEEK | U133234 | 2023-03-13 | 2023-03-24 | 2023-04-09 |  | BMEEK | 2023-04-07 | 2023-04-04 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 16.1167 | 3 | 1407.1 | 1020.75 | 45.19 | 341.16 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23179801200 |  | 100312539 |  | 6716208E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SHERIDAN | 398 SHERIDAN DR | 067 | LEX | 2023-04-11 | U132743 | U134852 | 2023-04-07 | 2023-04-07 | 2023-04-07 |  | LSTONE | 2023-04-07 | 2023-04-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 12.2667 | 3 | 1633.53 | 1443.67 | 0 | 78.76 | 111.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 03533958700 |  | 100345194 |  | X00000000 | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | MAIN | N MAIN ST | 239 | VER | 2023-04-10 | U131418 | DMCCULL | 2003-03-18 | 2022-07-01 | 2023-12-31 |  | J. PARKS | 2023-04-10 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2621 | 11931120600 |  | 100290691 | 67 | 6720212B |  |  |  | 566 | EX | ABANDON - IDLE/PRMT RDY 4/4/23 | 2621P | LIMESTONE | 1403 N LIMESTONE ST | 067 | LEX | 2023-04-10 | LSTONE | RSTOKLE | 2011-10-31 | 2014-04-30 | 2023-04-30 |  | LSTONE | 2023-04-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.9333 | 7 | 2760.72 | 785.07 | 21.92 | 135.85 | 1817.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883095200 |  | 100275123 |  | 6684228J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | MAIN | 308 W MAIN ST | 073 | FRA | 2023-04-10 | U131418 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | J. PARKS | 2023-04-10 | 2022-12-20 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.033333 | 2 | 783.09 | 2.14 | 0 | 0.51 | 780.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21900910100 |  | 100289263 |  | 6724212A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | LOMBARDY | 653 LOMBARDY DR A | 067 | LEX | 2023-04-10 | LSTANFI | AOC SYST | 2021-04-06 | 2021-10-06 | 2022-12-31 |  | LSTANFI | 2023-04-10 | 2023-03-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 19.85 | 5 | 1928.91 | 1123.7 | 580.55 | 188.36 | 36.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21938173800 |  | 100301015 |  | 6716212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | SAVOY | 212 SAVOY RD | 067 | LEX | 2023-04-10 | MCRAIG | AOC SYST | 2021-09-07 | 2022-03-07 | 2022-12-31 |  | MCRAIG | 2023-04-10 | 2023-03-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 20.6167 | 7 | 2118.49 | 1463.16 | 0 | 608.03 | 47.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026244500 |  |  |  | 6764176O | 2294088 | U461383 |  | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2621M | RT 89 | RT 89 | 065 | IRV | 2023-07-17 | U123258 | U461383 | 2022-12-15 | 2023-11-30 | 2023-12-01 | 2023-04-10 | JOSH MARTIN | 2023-04-10 | 2023-03-27 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00909 | 3200909 |  |  | WP2445 |  |  | 100 | 090932220262445 | 41.4833 | 0 | 17938.12 | 2616.6 | 0 | 155.78 | 15069.33 | 0 | 96.41 | 0
KY | KY - WEST | 2623 | 23026271000 |  |  |  | 6712228B | 2396743 | U126783 |  | 559 | EX | INSTALL 70'-2" PMMP | 2621P | MAIN | 155 W MAIN ST | 209 | GEO | 2023-08-11 | U136251 | U126783 | 2023-04-05 | 2023-04-26 | 2023-04-30 | 2023-04-10 | DCOLLINS | 2023-04-10 | 2023-04-10 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00559 | 3200559 |  |  | WP2710 |  |  | 100 | 055932230262710 | 5.5333 | 210 | 606.43 | 379.18 | 0 | 67.96 | 70.4 | 0 | 1.26 | 87.63 | 70
KY | KY - WEST | 2623 | 23026271100 |  |  |  | 6712228B | 2396743 | U126783 |  | 560 | EX | ABANDON 60'-2" PMMP | 2621P | MAIN | 155 W MAIN ST | 209 | GEO | 2023-05-23 | U136251 | U126783 | 2023-04-05 | 2023-04-28 | 2023-04-30 | 2023-04-10 | MOLIVER | 2023-04-10 | 2023-04-10 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00560 | 3200560 |  |  | WP2711 |  |  | 100 | 056032230262711 | 39.5 | 0 | 4210.59 | 2745.49 | 0 | 1465.1 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165279700 |  | 100336883 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | JOHNSON | 409 JOHNSON AV | 067 | LEX | 2023-04-10 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-04-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2390.38 | 0 | 0 | 0 | 2390.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165280200 |  | 100336878 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | JOHNSON | 419 JOHNSON AV | 067 | LEX | 2023-04-10 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-04-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2391.48 | 0 | 0 | 0 | 2391.48 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166694900 |  | 100272348 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 122 TANGLEWOOD DR | 073 | FRA | 2023-04-12 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-04-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3075.41 | 0 | 0 | 0 | 3075.41 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166695400 |  | 100272320 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 131 TANGLEWOOD DR | 073 | FRA | 2023-04-12 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-04-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3734.76 | 0 | 0 | 0 | 3734.76 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166695700 |  | 100272318 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 201 TANGLEWOOD DR | 073 | FRA | 2023-04-12 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-04-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2534.5 | 0 | 0 | 0 | 2534.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166706900 |  | 100309795 |  | 6712208H | 2184394 |  |  | 565 | EX | RPLC SL/22026223700 | 2600B | TOPEKA | 2404 TOPEKA RD | 067 | LEX | 2023-04-11 | U126309 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JAMIE LYNN | 2023-04-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 3666.21 | 0 | 0 | 0 | 3666.21 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23173904100 |  | 100346626 |  | 6696212P | 2396134 |  |  | 565 | EX | NBT - CSL METER RELOC | 2621P | MCDONALD | 327 MCDONALD DR | 239 | VER | 2023-04-11 | U128410 | U125208 | 2023-03-15 | 2023-03-14 | 2023-04-11 |  | CDESPAIN | 2023-04-10 | 2023-03-29 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26230031 | 36.6167 | 7 | 2384.59 | 2213.71 | 0 | 121.38 | 49.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23179496900 |  | 100321839 |  | 6716208D |  |  |  | 565 | EX | REPLACE SL - W/23-0262647-00 | 2621P | COLUMBIA | 623 COLUMBIA AV | 067 | LEX | 2023-04-10 | HMCKUNE | U125208 | 2023-04-06 | 2023-04-06 |  |  | HMCKUNE | 2023-04-10 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.35 | 1 | 346.34 | 23.8 | 291.55 | 1.29 | 29.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23179497500 |  | 100321828 |  | 6716208D |  |  |  | 565 | EX | REPLACE SL - W/23-0262647-00 | 2621P | COLUMBIA | 622 COLUMBIA AV | 067 | LEX | 2023-04-10 | HMCKUNE | U125208 | 2023-04-06 | 2023-04-06 |  |  | HMCKUNE | 2023-04-10 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.45 | 1 | 289.59 | 30.58 | 174.83 | 1.68 | 82.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23179498300 |  | 100321838 |  | 6716208D |  | U125208 |  | 565 | EX | REPLACE SL - W/23-0262647-00 | 2621P | COLUMBIA | 625 COLUMBIA AV | 067 | LEX | 2023-04-10 | HMCKUNE | U125208 | 2023-04-06 | 2023-04-06 |  |  | HMCKUNE | 2023-04-10 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.3 | 1 | 223.16 | 20.41 | 168.64 | 1.11 | 33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23179940800 |  | 100325295 |  | 6720208M |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | ALBANY | 917 ALBANY CR | 067 | LEX | 2023-04-10 | KKINDER | U131552 | 2023-04-10 | 2023-04-10 | 2023-04-10 |  | KKINDER | 2023-04-10 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 22.2667 | 3 | 1787.54 | 1277.38 | 330.52 | 69.64 | 110 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23179958500 |  | 100325292 |  | 6720208M |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | ALBANY | 920 ALBANY CR | 067 | LEX | 2023-04-10 | LSTONE | U131552 | 2023-04-10 | 2023-04-10 | 2023-04-10 |  | LSTONE | 2023-04-10 | 2023-04-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.9 | 3 | 1456.93 | 1015.15 | 201.65 | 142.23 | 97.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 01458883600 |  | 100420630 |  | 6700212M | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | HUNTERTOWN | 393 HUNTERTOWN RD | 239 | VER | 2023-04-11 | U131418 | DMCCULL | 2001-01-24 | 2022-11-15 | 2023-12-31 |  | J. PARKS | 2023-04-11 | 2022-11-15 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8 | 1 | 602.64 | 569.33 | 0 | 33.31 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 01491294700 |  | 100346946 |  | 6696212L | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | MAIN | 271 S MAIN ST | 239 | VER | 2023-04-11 | U131418 | JTOY | 2001-12-19 | 2022-11-15 | 2023-12-31 |  | J. PARKS | 2023-04-11 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 03529556600 |  | 100416699 |  | 6716216O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | GEORGETOWN | 866 GEORGETOWN ST BLDG2-4 | 067 | LEX | 2023-04-11 | U131418 | DMCCULL | 2003-01-31 | 2022-07-01 | 2023-12-31 |  | J. PARKS | 2023-04-11 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 03533608000 |  | 100344770 |  | 6700224O | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | HIGGINS | HIGGINS ST | 239 | MID | 2023-04-11 | U131418 | DMCCULL | 2003-03-13 | 2022-07-01 | 2023-12-31 |  | J. PARKS | 2023-04-11 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 03534019100 |  | 100345486 |  | 6696212H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | AMSDEN | 349 AMSDEN AV | 239 | VER | 2023-04-11 | U131418 | DMCCULL | 2003-03-18 | 2022-07-01 | 2023-12-31 |  | J. PARKS | 2023-04-11 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 38.55 | 36.56 | 0 | 1.99 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 17557740000 |  | 500008643 |  | 6696212J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | M L KING | 110 M L KING BV | 239 | VER | 2023-04-11 | U131418 | DMCCULL | 2017-10-26 | 2022-07-01 | 2023-12-31 |  | J. PARKS | 2023-04-11 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2621 | 22026243200 |  |  |  | 6720204P | 2294088 | U461383 |  | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2621M | SUMMERHILL | 1750 SUMMERHILL DR | 067 | LEX | 2023-07-17 | U123258 | U461383 | 2022-12-14 | 2023-11-30 | 2023-12-01 | 2023-04-11 | ALVARO PARKS | 2023-04-11 | 2023-03-17 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP2432 |  |  | 100 | 090932220262432 | 56.9333 | 0 | 20634.93 | 3690.14 | 0 | 1034.81 | 15811.63 | 0 | 98.35 | 0
KY | KY - WEST | 2621 | 22129082900 |  | 100333507 |  | 6720212I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CONSTITUTION | 155 CONSTITUTION ST 1F | 067 | LEX | 2023-04-11 | SSHIMFE | U130722 | 2022-09-05 | 2022-12-30 |  |  | SSHIMFE | 2023-04-11 | 2022-09-27 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.8667 | 4 | 877.6 | 442.24 | 0 | 26.68 | 408.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22139749500 |  | 100325033 |  | 6720204A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | GREENTREE | 3478 GREENTREE RD | 067 | LEX | 2023-04-11 | U126308 | AOC SYST | 2022-10-18 | 2023-12-31 | 2023-12-31 |  | J ENSMINGER | 2023-04-11 | 2023-04-04 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 19.3 | 5 | 2360.57 | 1266.99 | 946.17 | 81.41 | 66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22979032700 |  | 100293634 |  | 6720212B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | BALLPARK | 208 BALLPARK DR STE 115 | 067 | LEX | 2023-04-11 | U131418 | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | J. PARKS | 2023-04-11 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 23026263400 |  |  |  | 6720200A | 2395811 | U132703 |  | 557 | EX | INSTALL 40'-4" PMMP | 2600B | ROCKBRIDGE | 1095 ROCKBRIDGE RD | 067 | LEX | 2023-04-14 | U128132 | U132703 | 2023-02-24 | 2023-10-25 | 2023-10-31 | 2023-04-10 | STEVE CANOY | 2023-04-11 | 2023-04-05 | 2023-04-05 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2634 |  |  | 100 | 055732230262634 | 41.3667 | 135 | 24778.88 | 2655.82 | 553.42 | 3138.56 | 14504 | 0 | 46.96 | 3880.12 | 27
KY | KY - WEST | 2621 | 23026263500 |  |  |  | 6720200A | 2395811 | U132703 |  | 558 | EX | RETIRE 20'-4" PMMP | 2600B | ROCKBRIDGE | 1095 ROCKBRIDGE | 067 | LEX | 2023-04-14 | U128132 | U132703 | 2023-02-24 |  | 2049-12-31 | 2023-04-10 | STEVE CANOY | 2023-04-11 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2635 |  |  | 100 | 055832230262635 | 0.7 | 0 | 98.08 | 44.96 | 0 | 53.12 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156267000 |  | 100356332 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | BISOTTI | 1201 BISOTTI DR | 161 | MAY | 2023-04-12 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-11 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2514.43 | 0 | 0 | 0 | 2514.43 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156267100 |  | 100356333 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | BISOTTI | 1203 BISOTTI DR | 161 | MAY | 2023-04-12 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-11 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2064.23 | 0 | 0 | 0 | 2064.23 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156267300 |  | 100356334 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | BISOTTI | 1205 BISOTTI DR | 161 | MAY | 2023-04-11 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-11 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 | 8 | 1 | 2598.6 | 510.75 | 0 | 27.86 | 2059.99 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156267400 |  | 100356335 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | BISOTTI | 1207 BISOTTI DR | 161 | MAY | 2023-04-11 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-11 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2245.51 | 0 | 0 | 0 | 2245.51 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156271200 |  | 100356308 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | CIRCLE | 561 CIRCLE DR | 161 | MAY | 2023-04-12 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-11 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2346.97 | 0 | 0 | 0 | 2346.97 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164746700 |  | 100434767 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | CHESTNUT | 508 CHESTNUT ST | 209 | GEO | 2023-04-11 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-04-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.25 | 1 | 2616.04 | 327.38 | 0 | 80.62 | 2208.04 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164746800 |  | 100281576 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | CHESTNUT | 510 CHESTNUT ST | 209 | GEO | 2023-04-11 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-04-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.2667 | 1 | 2808.58 | 79.84 | 0 | 19.66 | 2709.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165280000 |  | 100336879 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | JOHNSON | 417 JOHNSON AV | 067 | LEX | 2023-04-11 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-04-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3319.34 | 0 | 0 | 0 | 3319.34 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166688200 |  | 100272312 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | DAKOTA | 101 DAKOTA RD | 073 | FRA | 2023-04-13 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-04-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2064.26 | 0 | 0 | 0 | 2064.26 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166688300 |  | 100272316 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | DAKOTA | 102 DAKOTA RD | 073 | FRA | 2023-04-12 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-04-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2299.54 | 0 | 0 | 0 | 2299.54 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166697200 |  | 100272308 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | VALLEY VISTA | 233 VALLEY VISTA DR | 073 | FRA | 2023-04-13 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-04-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1952.15 | 0 | 0 | 0 | 1952.15 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23173575900 |  | 100317249 |  | 6716204I |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | FOXE BASIN | 4057 FOXE BASIN RD | 067 | LEX | 2023-04-11 | RSTRONG | U132002 | 2023-03-14 | 2023-03-27 | 2023-04-12 |  | RSTRONG | 2023-04-11 | 2023-04-05 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 24.75 | 5 | 2042.85 | 1812.63 | 5.93 | 224.29 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23178903200 |  | 100349385 |  | 6748208M |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | BUCKNER | 121 BUCKNER ST | 049 | WIN | 2023-04-11 | NRICHIE | U133234 | 2023-04-04 | 2023-04-17 | 2023-05-03 |  | NRICHIE | 2023-04-11 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9.7 | 2 | 1014.94 | 610.4 | 20.27 | 384.27 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23179913700 |  | 100320023 |  | 6716208L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309463 | 2621P | GLENDOVER | 341 GLENDOVER RD | 067 | LEX | 2023-04-11 | U930915 | U124449 | 2023-04-09 | 2023-04-06 | 2023-04-09 |  | RJCRAWF | 2023-04-11 | 2023-04-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.8833 | 4 | 1354.83 | 1043.25 | 166.66 | 56.92 | 88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23180007400 |  | 100316535 |  | 6716208F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309464 | 2621P | PENMOKEN | 121 PENMOKEN PA | 067 | LEX | 2023-04-11 | KKINDER | U125208 | 2023-04-10 | 2023-04-10 | 2023-04-10 |  | KKINDER | 2023-04-11 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.9 | 3 | 1976.58 | 1389.82 | 460.38 | 75.78 | 50.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11889363500 |  | 100316484 |  | 6716208F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ROSEMONT | 206 ROSEMONT RD | 067 | LEX | 2023-04-12 | KKINDER | U906631 | 2011-02-16 | 2016-12-22 |  |  | KKINDER | 2023-04-12 | 2023-03-24 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.4667 | 3 | 174.61 | 164.98 | 0 | 9.63 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11938087900 |  | 100460118 |  | 7240216L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE * | 2621P | DOE RUN 500390529 +ACT | 601 DOE RUN 500390529 +ACT DR 8 | 173 | MT | 2023-04-14 | U930915 | U125208 | 2011-12-15 | 2020-12-31 |  |  | DENNING | 2023-04-12 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9.15 | 3 | 628.07 | 595.6 | 0 | 32.47 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12997089400 |  | 500513450 |  | 6716208N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NICHOLASVILLE | 2463 NICHOLASVILLE RD A | 067 | LEX | 2023-04-12 | KKINDER | U125208 | 2012-11-02 | 2020-12-18 |  |  | KKINDER | 2023-04-12 | 2023-03-02 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.3667 | 7 | 433.38 | 410.6 | 0 | 22.78 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883224300 |  | 100253643 |  | 7364188H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | BLACK LOG | 2553 BLACK LOG RD | 159 | INE | 2023-04-12 | JCKIRK | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JCKIRK | 2023-04-12 | 2023-03-08 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 11.4167 | 4 | 774.47 | 733.99 | 0 | 40.48 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960865300 |  | 100249879 |  | 7356248L | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | ROBIN | 8313 ROBIN LN | 019 | CAT | 2023-04-12 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH JERRY NEWSOME | 2023-04-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3665.41 | 0 | 0 | 0 | 3665.41 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960888200 |  | 100249881 |  | 7356248L | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | ROBIN | 8300 ROBIN LN | 019 | CAT | 2023-04-12 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH JERRY NEWSOME | 2023-04-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2034.31 | 0 | 0 | 0 | 2034.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026184800 |  |  |  | 6716208A | 2181472 | U122858 |  | 561 | EX | INSTALL 3775'-2" PMMP | 2600B | LONE OAK | LONE OAK DR | 067 | LEX | 2023-04-25 | U124014 | U122858 | 2022-05-06 | 2023-03-15 | 2023-06-30 | 2023-02-28 | BPULLIAM | 2023-04-12 | 2022-12-30 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP1848 | AMRCB |  | 100 | 056132220261848 | 872.4833 | 467310 | 689655.43 | 57217.26 | 11534.7 | 51216.94 | 480824.29 | 0 | 1783.9 | 87078.34 | 4210
KY | KY - WEST | 2621 | 22026184900 |  |  |  | 6716208A | 2181472 | U122858 |  | 562 | EX | RETIRE 3315'-2"&4"BSLP | 2600B | LONE OAK | LONE OAK DR | 067 | LEX | 2023-04-24 | U124014 | U122858 | 2022-05-06 | 2023-06-30 | 2023-06-30 | 2023-04-11 | BPULLIAM | 2023-04-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP1849 | AMRCB |  | 100 | 056232220261849 |  | 0 | 23.53 | 0 | 23.53 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026243300 |  |  |  | 6716208E | 2294088 | U461383 |  | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2621M | MITCHELL | 567 MITCHELL AV | 067 | LEX | 2023-07-17 | U123258 | U461383 | 2022-12-14 | 2023-11-30 | 2023-12-01 | 2023-04-12 | CHRIS COX | 2023-04-12 | 2023-03-17 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP2433 |  |  | 100 | 090932220262433 | 58.8 | 0 | 20996.21 | 3874.88 | 0 | 574.56 | 16444.46 | 0 | 102.31 | 0
KY | KY - WEST | 2621 | 22127708300 |  | 500890564 |  | 6724208E |  |  |  | 566 | EX | ABANDN SL/LGCY | 2621P | PALUMBO | 2770 PALUMBO DR CABLE | 067 | LEX | 2023-04-14 | U930915 | U125763 | 2022-08-30 | 2022-12-30 |  |  | HMCKUNE | 2023-04-12 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.0667 | 3 | 600.81 | 549.63 | 21.21 | 29.97 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22139742200 |  | 100325047 |  | 6720204B | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | GREENTREE | 3426 GREENTREE RD | 067 | LEX | 2023-04-12 | ABLAKE | AOC SYST | 2022-10-18 | 2023-04-18 | 2023-12-31 |  | ABLAKE | 2023-04-12 | 2023-04-04 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 30.2833 | 10 | 2754.43 | 1901.37 | 596.24 | 196.32 | 60.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22983466300 |  | 100309501 |  | 6712208K | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | CHELSEA | 3104 CHELSEA DR | 067 | LEX | 2023-04-17 | U930915 | AOC SYST | 2022-03-03 | 2022-09-02 | 2023-12-31 |  | LSTANFI | 2023-04-12 | 2023-04-12 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 15.3667 | 3 | 1768.3 | 875.28 | 634.17 | 151.05 | 107.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22984924200 |  | 100466080 |  | 7240216H |  |  |  | 566 | EX | ABANDON SL- I/I/LGCY | 2621P | MIDLAND | 211 MIDLAND TL C2 | 173 | MT | 2023-04-12 | DENNING | U134723 | 2022-03-10 | 2022-12-30 |  |  | DENNING | 2023-04-12 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 13.6 | 3 | 924.77 | 876.94 | 0 | 47.83 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026268100 |  |  |  | 6688228H | 2396353 | U126783 |  | 558 | EX | RETIRE MAIN - LEAKAGE | 2621P | ELMENDORF | ELMENDORF | 073 | FRA | 2023-06-19 | U128132 | U126783 | 2023-03-21 | 2023-11-30 | 2023-11-30 | 2023-02-27 | BWHITE | 2023-04-12 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP2681 |  |  | 100 | 055832230262681 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026268800 |  |  |  | 6716208E | 2294088 | U461383 |  | 910 | EX | RETIRE ER350 UNIT | 2600E | MITCHELL | 567 MITCHELL AV | 067 | LEX | 2023-05-04 | U123258 | U461383 | 2023-03-24 | 2023-12-01 | 2023-12-01 | 2023-04-12 | CCOX | 2023-04-12 | 2023-04-17 |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00910 | 3200910 |  |  | WP2688 |  |  | 100 | 091032230262688 | 1.6833 | 0 | 116.17 | 110.16 | 0 | 6.01 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156275700 |  | 500916692 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | US 68 | 1205 US 68 | 161 | MAY | 2023-04-12 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-12 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 | 8 | 1 | 3166.5 | 510.75 | 0 | 27.86 | 2627.89 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164747200 |  | 100281569 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | CHESTNUT | 513 CHESTNUT ST | 209 | GEO | 2023-04-12 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-04-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.31667 | 1 | 2415.17 | 19.96 | 0 | 4.92 | 2390.29 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164747400 |  | 100281570 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | CHESTNUT | 515 CHESTNUT ST | 209 | GEO | 2023-04-12 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-04-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.58333 | 1 | 3020.05 | 36.18 | 0 | 8.91 | 2974.96 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164747900 |  | 100281573 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | CHESTNUT | 521 CHESTNUT ST | 209 | GEO | 2023-04-12 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-04-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.1 | 1 | 2825.36 | 130.95 | 0 | 32.25 | 2662.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165279900 |  | 100336886 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | JOHNSON | 414 JOHNSON AV | 067 | LEX | 2023-04-12 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-04-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2678.07 | 0 | 0 | 0 | 2678.07 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166688400 |  | 100272313 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | DAKOTA | 103 DAKOTA RD | 073 | FRA | 2023-04-13 | U126309 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JAMIE LYNN | 2023-04-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1608.86 | 0 | 0 | 0 | 1608.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166688500 |  | 100272315 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | DAKOTA | 104 DAKOTA RD | 073 | FRA | 2023-04-13 | U126309 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JAMIE LYNN | 2023-04-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1546.11 | 0 | 0 | 0 | 1546.11 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166690300 |  | 100272355 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | RESERVOIR | 102 RESERVOIR RD | 073 | FRA | 2023-04-13 | U126309 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JAMIE LYNN | 2023-04-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3169.37 | 0 | 0 | 0 | 3169.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166705400 |  | 100309794 |  | 6712208H | 2184394 |  |  | 565 | EX | RPLC SL/22026223700 | 2600B | TOPEKA | 2408 TOPEKA RD | 067 | LEX | 2023-04-14 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-04-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 4980.58 | 0 | 0 | 0 | 4980.58 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23172609600 |  | 100253642 |  | 7364188H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | BLACK LOG | 2553< BLACK LOG RD | 159 | INE | 2023-04-12 | JCKIRK | U125208 | 2023-03-08 | 2023-03-10 | 2023-05-10 |  | JCKIRK | 2023-04-12 | 2023-04-11 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 14.9833 | 3 | 1017.95 | 965.3 | 0 | 52.65 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23174196900 |  | 500545360 |  | 6712232I | 2395680 |  |  | 565 | EX | RPLC SL/23026263600 | 2600B | MINUTEMAN | 100 MINUTEMAN PY H-HANGR | 073 | FRA | 2023-04-12 | U126602 | U136332 | 2023-03-16 | 2023-03-16 |  |  | DEREK PAYTON | 2023-04-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 8.1 | 1 | 7458.9 | 555.69 | 450.58 | 78.06 | 6374.57 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23177394500 |  | 100283078 |  | 6712228C |  |  |  | 566 | EX | ABANDON SL - IDLE/CONVRT | 2621P | CLAYTON | 504 CLAYTON AV | 209 | GEO | 2023-04-12 | DCOLLIN | U125208 | 2023-03-31 | 2023-04-05 | 2023-04-30 |  | DCOLLIN | 2023-04-12 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 11.4667 | 2 | 1405.34 | 748.03 | 111.48 | 277.83 | 268 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179217100 |  | 100244277 |  | 7356256I |  |  |  | 565 | EX | REPLACE SERVICE LINE - D258022 | 2621P | OLD ORCHARD | 3600 OLD ORCHARD DR | 019 | ASH | 2023-04-12 | BMEEK | U125208 | 2023-04-05 | 2023-04-05 | 2023-04-05 |  | BMEEK | 2023-04-12 | 2023-04-11 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 30.6667 | 5 | 2808.54 | 2004.59 | 190.57 | 511.08 | 102.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23179521100 |  | 100295526 |  | 6716216K |  |  |  | 565 | EX | SERVICE REPLACE - UNLOCATABLE | 2621P | BRIARWOOD | 1117 BRIARWOOD DR | 067 | LEX | 2023-04-14 | U930915 | U125208 | 2023-04-06 | 2023-04-12 | 2023-04-27 |  | TROE | 2023-04-12 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.2833 | 3 | 1034.91 | 875 | 0 | 47.71 | 112.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21924760800 |  | 100296124 |  | 6716216O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE | 2621D | SAINT MARTINS | 985 SAINT MARTINS DR | 067 | LEX | 2023-04-13 | LSTONE | AOC SYST | 2021-07-12 | 2022-01-12 | 2022-12-31 |  | LSTONE | 2023-04-13 | 2023-04-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.8167 | 2 | 1220.44 | 863 | 254.28 | 47.06 | 56.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960865200 |  | 100249880 |  | 7356248H | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | ROBIN | 8311 ROBIN LN | 019 | CAT | 2023-04-14 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH JERRY NEWSOME | 2023-04-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2713.87 | 0 | 0 | 0 | 2713.87 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129019900 |  | 100276921 |  | 6684228D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SWIGERT | 404 SWIGERT AV | 073 | FRA | 2023-04-13 | U126332 | U130722 | 2022-09-05 | 2022-12-30 |  |  | SLBARKER | 2023-04-13 | 2023-03-02 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 22 | 7 | 1320.51 | 1159.71 | 0 | 160.8 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129068700 |  | 100262930 |  | 7352260N |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTREQD | 2621P | CHEEK | 1015 CHEEK AV | 019 | ASH | 2023-04-13 | JROGER1 | U130722 | 2022-09-05 | 2022-12-30 | 2023-03-24 |  | JROGER1 | 2023-04-13 | 2023-03-13 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 12.0667 | 3 | 1895.68 | 1287.25 | 248.09 | 360.34 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22139747700 |  | 100325024 |  | 6720204E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | GREENTREE | 3500 GREENTREE RD | 067 | LEX | 2023-04-13 | U930915 | AOC SYST | 2022-10-18 | 2023-12-31 | 2023-12-31 |  | JOCHOA | 2023-04-13 | 2023-04-04 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 23.15 | 5 | 1670.82 | 1267.32 | 248.19 | 95.91 | 59.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026268300 |  |  |  | 6716208B | 2396396 | U461383 |  | 558 | EX | RETIRE 160' OF 4"BSLP MAIN | 2621P | SAINT JOSEPH | SAINT JOSEPH DR | 067 | LEX | 2023-04-19 | U128132 | U461383 | 2023-03-22 | 2023-04-04 | 2024-08-10 | 2023-04-13 | JOSHUA COX | 2023-04-13 | 2023-04-04 | 2023-04-11 | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2683 | AMRCB |  | 100 | 055832230262683 | 82.25 | 0 | 8055.67 | 4778.23 | 0 | 1536.44 | 1741 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156275600 |  | 500632455 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | US 68 | 1203 US 68 | 161 | MAY | 2023-04-13 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-13 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2351.02 | 0 | 0 | 0 | 2351.02 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156276600 |  | 100356330 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | VALENTINE | 509 VALENTINE DR | 161 | MAY | 2023-04-13 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-13 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2096.47 | 0 | 0 | 0 | 2096.47 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156276800 |  | 100356338 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | VALENTINE | 521 VALENTINE DR | 161 | MAY | 2023-04-14 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-13 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2144.73 | 24.57 | 0 | 1.36 | 2118.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164747100 |  | 100281577 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | CHESTNUT | 512 CHESTNUT ST | 209 | GEO | 2023-04-13 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-04-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.2333 | 1 | 3288.59 | 202.67 | 0 | 49.91 | 3036.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165280400 |  | 100336877 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | JOHNSON | 421 JOHNSON AV 1 | 067 | LEX | 2023-04-13 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-04-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3188.85 | 0 | 0 | 0 | 3188.85 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166688600 |  | 100272314 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | DAKOTA | 105 DAKOTA RD | 073 | FRA | 2023-04-13 | U126309 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JAMIE LYNN | 2023-04-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1908.64 | 0 | 0 | 0 | 1908.64 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166695800 |  | 100272317 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 203 TANGLEWOOD DR | 073 | FRA | 2023-04-13 | U126309 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JAMIE LYNN | 2023-04-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2730.63 | 0 | 0 | 0 | 2730.63 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166696800 |  | 100272306 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | VALLEY VISTA | 221 VALLEY VISTA DR | 073 | FRA | 2023-04-13 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-04-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2880.57 | 0 | 0 | 0 | 2880.57 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23180955600 |  | 100275685 |  | 6684228F |  |  |  | 566 | EX | ABANDON SL @ MAIN - FIRE DMG | 2621P | KENTUCKY | 884 KENTUCKY AV | 073 | FRA | 2023-04-27 | U125208 | U136241 | 2023-04-13 | 2023-04-13 |  |  | EFGOINS | 2023-04-13 | 2023-04-13 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 18.2167 | 3 | 1675.99 | 1092.51 | 42.65 | 540.83 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21026105201 |  |  |  | 6732216L | 1851238 | U461383 |  | 577 | EX | INSTALL CHAIN LINK FENCE | 2621M | BRIAR HILL | BRIAR HILL RD | 067 | LEX | 2023-08-22 | U123258 | U461383 | 2023-02-07 | 2023-12-29 | 2023-12-31 | 2023-04-14 | ALVARO PARKS | 2023-04-14 | 2023-04-13 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00577 | 3200577 |  |  | WP1052 |  |  | 100 | 057732210261052 | 64.45 | 14 | 84349.67 | 4152.22 | 0 | 1315.11 | 69095.37 | 0 | 1551.8 | 8235.17
KY | KY - EAST | 2631 | 21960865400 |  | 100249876 |  | 7356248L | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | ROBIN | 8319 ROBIN LN | 019 | CAT | 2023-04-14 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH CASEY PACK | 2023-04-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3907.07 | 0 | 0 | 0 | 3907.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026243600 |  |  |  | 6720212A | 2294088 | U461383 |  | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2621M | LOUDON | 250 W LOUDON AV | 067 | LEX | 2023-07-17 | U123258 | U461383 | 2022-12-15 | 2023-11-30 | 2023-12-01 | 2023-04-14 | ERIC BLANTON | 2023-04-14 | 2023-03-17 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP2436 |  |  | 100 | 090932220262436 | 39.1167 | 0 | 18807.4 | 2579.32 | 0 | 1061.47 | 15069.33 | 0 | 97.28 | 0
KY | KY - EAST | 2631 | 22129013900 |  | 100239484 |  | 7352264J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BELLEFONTE | 245 BELLEFONTE ST | 089 | RUS | 2023-04-14 | BMEEK | U130722 | 2022-09-05 | 2022-12-30 |  |  | BMEEK | 2023-04-14 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 10.8167 | 2 | 1354.05 | 694.89 | 20.27 | 128.89 | 510 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026268200 |  |  |  | 6716208B | 2396396 | U461383 |  | 557 | EX | INSERT 160' OF 3"PMLP MAIN | 2621P | SAINT JOSEPH | SAINT JOSEPH DR | 067 | LEX | 2023-06-20 | U128132 | U461383 | 2023-03-22 | 2023-12-27 | 2024-08-10 | 2023-04-13 | JOSHUA COX | 2023-04-14 | 2023-04-10 | 2023-04-11 | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2682 | AMRCB |  | 100 | 055732230262682 | 84.2833 | 2310 | 12586.85 | 5594.02 | 3451.23 | 1097.83 | 179.3 | 0 | 26.07 | 2238.4 | 165
KY | KY - CENTRAL | 2632 | 23156277100 |  | 100356339 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | VALENTINE | 527 VALENTINE DR | 161 | MAY | 2023-04-14 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-14 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1985.67 | 0 | 0 | 0 | 1985.67 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156277200 |  | 100356340 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | VALENTINE | 529 VALENTINE DR | 161 | MAY | 2023-04-14 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-14 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 | 8 | 1 | 2695.66 | 720.31 | 0 | 39.28 | 1936.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165280300 |  | 100336889 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | JOHNSON | 420 JOHNSON AV | 067 | LEX | 2023-04-14 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-04-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3183.77 | 0 | 0 | 0 | 3183.77 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166691700 |  | 100272385 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | RIVERVIEW | 219 RIVERVIEW ST | 073 | FRA | 2023-04-14 | U126309 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JAMIE LYNN | 2023-04-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2347.89 | 70.02 | 0 | 3.81 | 2274.06 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23169479600 |  | 100331033 |  | 6720212N | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER | 2621D | PRESTON | 280 PRESTON AV | 067 | LEX | 2023-04-14 | U930915 | AOC SYST | 2023-02-27 | 2023-03-24 | 2023-04-25 |  | HMCKUNE | 2023-04-14 | 2023-03-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 19.45 | 8 | 2508.81 | 1106.75 | 228.94 | 538.12 | 635 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23173154800 |  | 100301281 |  | 6712212H |  |  |  | 565 | EX | AOC ATMOS CORR REPLCE | 2621P | DUNKIRK | 1919 DUNKIRK DR | 067 | LEX | 2023-04-27 | U125208 | U134852 | 2023-03-10 | 2023-03-10 |  |  | RSTRONG | 2023-04-14 | 2023-04-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25.4 | 11 | 2066.83 | 1551.26 | 246.02 | 200.25 | 69.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23181378700 |  | 100294565 |  | 6720212E |  |  |  | 565 | EX | REPLACE SERVICE | 2621P | BROADWAY | 568 N BROADWAY ST | 067 | LEX | 2023-04-14 | LSTANFI | U130871 | 2023-04-14 | 2023-04-14 |  |  | LSTANFI | 2023-04-14 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.2 | 1 | 7300.09 | 4047.46 | 1895.25 | 317.05 | 1040.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23181385500 |  | 100319094 |  | 6716208O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CURTIN | 327 CURTIN DR | 067 | LEX | 2023-04-14 | LSTONE | U130871 | 2023-04-14 | 2023-04-14 | 2023-04-14 |  | LSTONE | 2023-04-14 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 24 | 4 | 2097.44 | 1416.46 | 486.03 | 77.25 | 117.7 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23181425600 |  | 100272303 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 215 TANGLEWOOD DR | 073 | FRA | 2023-04-14 | U126309 | U125763 | 2023-04-14 | 2023-12-29 |  |  | JAMIE LYNN | 2023-04-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.5 | 1 | 1853.07 | 93.99 | 0 | 23.06 | 1736.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23181457600 |  | 100319095 |  | 6716208O |  |  |  | 565 | EX | REPLACE SERVICE | 2621P | CURTIN | 323 CURTIN DR | 067 | LEX | 2023-04-14 | LSTONE | U130871 | 2023-04-14 | 2023-04-14 |  |  | LSTONE | 2023-04-14 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 |  | 1 | 108.9 | 0 | 0 | 0 | 108.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 08731010500 |  | 100287842 | 47 | 6720212B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | SHAWNEE | 407 SHAWNEE AV | 067 | LEX | 2023-04-17 | U131418 | MPILON | 2008-05-13 | 2022-07-01 | 2023-12-31 |  | J. PARKS | 2023-04-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 643.88 | 0 | 0 | 0 | 643.88 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11906401000 |  | 500062449 |  | T-1624-30 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | LOIS | LOIS AV | 089 | GRE | 2023-04-17 | U131418 | U906631 | 2011-05-12 | 2022-07-01 | 2023-12-31 |  | J. PARKS | 2023-04-17 | 2022-11-17 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.18333 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 12984344000 |  | 100263653 |  | 7352256C |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | IOWA | 218 IOWA ST | 019 | ASH | 2023-04-17 | U131418 | U908784 | 2012-08-14 | 2022-08-29 | 2023-12-31 |  | J. PARKS | 2023-04-17 | 2021-12-29 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 10.8333 | 4 | 939.95 | 858.92 | 0 | 81.03 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21897157500 |  | 100354539 |  | 7260280M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY | 2621P | 2ND | 409 E 2ND ST | 161 | MAY | 2023-04-18 | U930915 | U124841 | 2021-03-25 | 2021-12-30 |  |  | ABHATFIE | 2023-04-17 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 12.05 | 2 | 841.18 | 797.68 | 0 | 43.5 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21917510700 |  | 100295475 |  | 6716216L | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | NANDINO | 1057 NANDINO BV | 067 | LEX | 2023-04-17 | TROE | AOC SYST | 2021-06-08 | 2021-12-08 | 2022-12-31 |  | TROE | 2023-04-17 | 2023-03-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 22.8667 | 4 | 2367.81 | 1423.23 | 693.88 | 78 | 172.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960865500 |  | 100249877 |  | 7356248H | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | ROBIN | 8327 ROBIN LN | 019 | CAT | 2023-04-17 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH CASEY PACK | 2023-04-17 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3336.49 | 0 | 0 | 0 | 3336.49 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026243700 |  |  |  | 6712224L | 2294088 | U461383 |  | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2621M | LISLE | 1175 LISLE RD | 209 | GEO | 2023-07-17 | U123258 | U461383 | 2022-12-15 | 2023-11-30 | 2023-12-01 | 2023-04-17 | CONNOR WEMPE | 2023-04-17 | 2023-03-29 |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00909 | 3200909 |  |  | WP2437 |  |  | 100 | 090932220262437 | 40.5833 | 0 | 17949.62 | 2638.34 | 0 | 146.63 | 15069.33 | 0 | 95.32 | 0
KY | KY - WEST | 2621 | 22100968100 |  | 100301286 |  | 6712212H | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | DUNKIRK | 1927 DUNKIRK DR | 067 | LEX | 2023-04-17 | DMEDLEY | AOC SYST | 2022-05-16 | 2022-11-16 | 2023-12-31 |  | DMEDLEY | 2023-04-17 | 2023-04-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 16.4 | 3 | 1708.77 | 931.2 | 352.75 | 344.52 | 80.3 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129118100 |  | 500186375 |  | 7344140T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SPEWING CAMP | 1003 SPEWING CAMP BR | 071 | MCD | 2023-04-17 | U130172 | U125208 | 2022-09-06 | 2022-12-30 |  |  | JOHN HOWARD | 2023-04-17 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 4.5833 | 1 | 310.82 | 294.75 | 0 | 16.07 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22979034700 |  | 100306772 |  | 6716212I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | VERSAILLES | 1832 VERSAILLES RD | 067 | LEX | 2023-04-17 | U131418 | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | J. PARKS | 2023-04-17 | 2022-11-15 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8 | 1 | 1270.88 | 477.86 | 0 | 27.95 | 765.07 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156276700 |  | 100356336 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | VALENTINE | 516 VALENTINE DR | 161 | MAY | 2023-04-17 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-17 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2781.77 | 0 | 0 | 0 | 2781.77 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156276900 |  | 100356337 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | VALENTINE | 522 VALENTINE DR | 161 | MAY | 2023-04-17 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-17 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2353.42 | 218.9 | 0 | 11.94 | 2122.58 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164748000 |  | 100281546 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | CHESTNUT | 604 CHESTNUT ST | 209 | GEO | 2023-04-17 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-04-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.4833 | 1 | 2299.85 | 216.41 | 0 | 53.28 | 2030.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165280500 |  | 100336891 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | JOHNSON | 422 JOHNSON AV 1FL | 067 | LEX | 2023-04-17 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-04-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3458.85 | 0 | 0 | 0 | 3458.85 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166696900 |  | 100272310 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | VALLEY VISTA | 222 VALLEY VISTA DR | 073 | FRA | 2023-04-17 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-04-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3493.21 | 0 | 0 | 0 | 3493.21 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23167353600 |  | 100306723 |  | 6716212I |  |  |  | 565 | EX | SL REPL-MMO PRMT RDY 3/01*HLD | 2621P | TAZWELL | 1639 TAZWELL DR | 067 | LEX | 2023-04-17 | LSTANFI | U125208 | 2023-02-16 | 2023-02-22 | 2023-03-09 |  | LSTANFI | 2023-04-17 | 2023-02-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 29.2333 | 9 | 5094.2 | 1681.07 | 592.72 | 92.46 | 2727.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23173568500 |  | 100315449 |  | 6716208C |  |  |  | 566 | EX | ABANDON SL - DEMO | 2621P | HOLD TIL 4/16**AUDUBON | 1302 HOLD TIL 4/16**AUDUBON AV | 067 | LEX | 2023-04-17 | U930915 | U132002 | 2023-03-14 | 2023-04-17 | 2023-05-17 |  | RSTRONG | 2023-04-17 | 2023-03-17 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.6 | 3 | 913.25 | 731.61 | 21.92 | 159.72 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176930100 |  | 500316367 |  | 6716208J | 2394661 |  |  | 565 | EX | RPLC SL/23026246400 | 2600B | BURT | 160 BURT RD | 067 | LEX | 2023-04-17 | U126604 | U125763 | 2023-03-29 | 2023-12-29 |  |  | WILL FULKS | 2023-04-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3531.7 | 0 | 0 | 0 | 3531.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23179929200 |  | 100330786 |  | 6720212N |  |  |  | 565 | VO | REPLACE SERVICE LINE - D309461 | 2621P | SHERMAN | 321 SHERMAN AV | 067 | LEX | 2023-04-18 | HMCKUNE | U125208 | 2023-04-10 | 2023-04-12 | 2023-04-30 |  | HMCKUNE | 2023-04-17 | 2023-04-12 |  | A | [11 empty] | 23182141300 | 100 |  | 21.3333 | 3 | 1369.85 | 1299.01 | 0 | 70.84 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23181398700 |  | 100316167 |  | 6716208B |  |  |  | 565 | EX | GRD 1 LEAK | 2621P | NORWAY | 218 NORWAY ST | 067 | LEX | 2023-04-18 | U132743 | U130871 | 2023-04-14 | 2023-04-14 | 2023-04-14 |  | HMCKUNE | 2023-04-17 | 2023-04-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 27.3333 | 4 | 2558.89 | 1602.16 | 286.59 | 599.74 | 70.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23181455900 |  | 100278243 |  | 6688228B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D308939 | 2621P | COMANCHE | 521 COMANCHE TL | 073 | FRA | 2023-04-18 | U132743 | U125208 | 2023-04-14 | 2023-04-14 | 2023-04-14 |  | EFGOINS | 2023-04-17 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 18.2167 | 3 | 1252.03 | 1024.23 | 104.86 | 55.84 | 67.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23181877400 |  | 100260398 |  | 7352256H |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | VIRGINIA | 2630 VIRGINIA AV | 019 | ASH | 2023-04-17 | BMEEK | U131552 | 2023-04-17 | 2023-04-17 | 2023-04-17 |  | BMEEK | 2023-04-17 | 2023-04-17 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 11.7667 | 4 | 1683.88 | 763.89 | 297.4 | 558.79 | 63.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 10868559900 |  | 100416301 |  | 16724212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KILKENNY | 1822 KILKENNY CT | 067 | LEX | 2023-04-18 | RSTRONG | U906314 | 2010-11-15 | 2020-12-31 |  |  | RSTRONG | 2023-04-18 | 2023-04-18 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4 | 2 | 257.92 | 244.59 | 0 | 13.33 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11916457100 |  | 100341948 |  | 7240216N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HARRISON | 307 HARRISON AV LS | 173 | MT | 2023-04-18 | U930915 | U124964 | 2011-07-19 | 2020-12-31 |  |  | DENNING | 2023-04-18 | 2023-04-17 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 11.25 | 4 | 766.99 | 727.32 | 0 | 39.67 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21917174300 |  | 100443168 |  | 6716216L | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | NANDINO | 1020 NANDINO BV | 067 | LEX | 2023-04-18 | TROE | AOC SYST | 2021-06-07 | 2021-12-07 | 2022-12-31 |  | TROE | 2023-04-18 | 2023-03-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 28.0833 | 7 | 2363.1 | 1735.62 | 531.62 | 95.86 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026243800 |  |  |  | 6712232E | 2294088 | U461383 |  | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2621M | LONG LICK | LONG LICK RD | 209 | GEO | 2023-07-17 | U123258 | U461383 | 2022-12-15 | 2023-11-30 | 2023-12-01 | 2023-04-18 | CWEMPE | 2023-04-18 | 2023-03-29 |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00909 | 3200909 |  |  | WP2438 |  |  | 100 | 090932220262438 | 29.9333 | 0 | 17170.68 | 1898.17 | 0 | 109.28 | 15069.33 | 0 | 93.9 | 0
KY | KY - WEST | 2621 | 22129081100 |  | 100288537 |  | 6720212C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GLENEAGLES | 1713 GLENEAGLES DR | 067 | LEX | 2023-04-20 | U132743 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RSTRONG | 2023-04-18 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12 | 2 | 893.77 | 736.51 | 0 | 157.26 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22137263200 |  | 100319007 |  | 6716208O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | HEATHER | 2419 HEATHER WY | 067 | LEX | 2023-04-18 | U930915 | AOC SYST | 2022-10-06 | 2023-12-31 | 2023-12-31 |  | RJCRAWF | 2023-04-18 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 12.5 | 3 | 1071.48 | 682.52 | 284.63 | 37.23 | 67.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964251000 |  | 100347813 |  | 6748208I | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | MAPLE | 502 N MAPLE ST | 049 | WIN | 2023-04-21 | U126603 | U134723 | 2022-01-06 | 2023-07-31 |  |  | SHAWN DENNIS | 2023-04-18 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3584.22 | 0 | 0 | 0 | 3584.22 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156277300 |  | 100356342 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | VALENTINE | 533 VALENTINE DR | 161 | MAY | 2023-04-19 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-18 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1786.08 | 163.03 | 0 | 8.9 | 1614.15 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156277400 |  | 100356343 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | VALENTINE | 535 VALENTINE DR | 161 | MAY | 2023-04-18 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-18 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1738.15 | 0 | 0 | 0 | 1738.15 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156277600 |  | 100356345 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | VALENTINE | 560 VALENTINE DR | 161 | MAY | 2023-04-18 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-18 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2569.98 | 13.25 | 0 | 0.72 | 2556.01 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164748700 |  | 100281539 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | CHESTNUT | 609 CHESTNUT ST | 209 | GEO | 2023-04-18 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-04-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.3 | 1 | 3653.84 | 84.21 | 0 | 20.72 | 3548.91 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164748800 |  | 100281543 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | CHESTNUT | 610 CHESTNUT ST | 209 | GEO | 2023-04-18 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-04-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.6333 | 1 | 2243.45 | 225.75 | 0 | 55.58 | 1962.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164748900 |  | 100281540 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | CHESTNUT | 611 CHESTNUT ST | 209 | GEO | 2023-04-18 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-04-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.9333 | 1 | 2447.15 | 119.72 | 0 | 29.48 | 2297.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165280100 |  | 100336888 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | JOHNSON | 418 JOHNSON AV | 067 | LEX | 2023-04-19 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-04-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3676.98 | 0 | 0 | 0 | 3676.98 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166696300 |  | 100272305 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 209 TANGLEWOOD DR E | 073 | FRA | 2023-04-18 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-04-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2096.42 | 0 | 0 | 0 | 2096.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166704600 |  | 100309687 |  | 6712208L | 2184394 |  |  | 565 | EX | RPLC SL/22026223700 | 2600B | PASADENA | 613 PASADENA DR | 067 | LEX | 2023-04-18 | U461322 | U125763 | 2023-02-14 | 2023-12-29 |  |  | STEVE CANOY | 2023-04-18 | 2023-04-17 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 17 | 2 | 6250.85 | 1091.36 | 0 | 1289.74 | 3869.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176930200 |  | 100435808 |  | 6716208J | 2394661 |  |  | 565 | EX | RPLC SL/23026246400 | 2600B | BURT | 169 BURT RD A | 067 | LEX | 2023-04-18 | U126604 | U125763 | 2023-03-29 | 2023-12-29 |  |  | WILL FULKS | 2023-04-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 6111.89 | 0 | 0 | 0 | 6111.89 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23178649100 |  | 100265441 |  | 7352252E |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTREQD | 2621P | MIDLAND TRAIL | 6610 MIDLAND TRAIL RD | 019 | ASH | 2023-04-25 | DYOUNG | U129939 | 2023-04-03 | 2023-04-06 | 2023-05-03 |  | BMEEK | 2023-04-18 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 14.4 | 2 | 1163.45 | 920.2 | 45.19 | 198.06 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23178681100 |  | 500634041 |  | 6696212O | 9830036 |  |  | 565 | EX | NBT - SL/MTR UPG 1" W/MC AL425 | 2621P | SHEFFIELD | 543 SHEFFIELD DR | 239 | VER | 2023-04-19 | U128410 | U125208 | 2023-04-03 | 2023-03-31 | 2023-04-24 |  | CDESPAIN | 2023-04-18 | 2023-04-11 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26230031 | 27.2 | 5 | 6697.52 | 1793.13 | 263.95 | 97.78 | 4542.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23179507000 |  | 100333037 |  | 6728200D |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | ATHENS BOONESB | 6329 ATHENS BOONESB RD | 067 | LEX | 2023-04-18 | HMCKUNE | U133234 | 2023-04-06 | 2023-04-19 | 2023-05-05 |  | HMCKUNE | 2023-04-18 | 2023-04-12 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.6333 | 3 | 613.26 | 555.35 | 27.63 | 30.28 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23181695700 |  | 500087987 |  | 6716216L |  |  |  | 566 | EX | ABN SL | 2621P | NANDINO | 1057 NANDINO BV GARAGE | 067 | LEX | 2023-04-18 | U930915 | U131552 | 2023-04-17 | 2023-04-17 |  |  | LSTONE | 2023-04-18 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.35 | 2 | 223.56 | 211.99 | 0 | 11.57 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23182193900 |  | 100435886 |  | 6716208J | 2394661 |  |  | 566 | EX | ABANDN SL/23026246400 | 2600B | BURT | 169 BURT RD B | 067 | LEX | 2023-04-18 | U126604 | U125763 | 2023-04-18 | 2023-12-29 |  |  | WILL FULKS | 2023-04-18 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 23182194000 |  | 100435887 |  | 6716208J | 2394661 |  |  | 566 | EX | ABANDN SL/23026246400 | 2600B | BURT | 169 BURT RD C | 067 | LEX | 2023-04-19 | U126604 | U125763 | 2023-04-18 | 2023-12-29 |  |  | WILL FULKS | 2023-04-18 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 23182194100 |  | 100435888 |  | 6716208J | 2394661 |  |  | 566 | EX | ABANDN SL/23026246400 | 2600B | BURT | 169 BURT RD D | 067 | LEX | 2023-04-19 | U126604 | U125763 | 2023-04-18 | 2023-12-29 |  |  | WILL FULKS | 2023-04-18 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 21919361400 |  | 100297584 |  | 6716212H | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE | 2621D | 3RD | 530 W 3RD ST | 067 | LEX | 2023-04-19 | LSTONE | AOC SYST | 2021-06-16 | 2021-12-16 | 2022-12-31 |  | LSTONE | 2023-04-19 | 2023-03-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.1333 | 7 | 1792.55 | 1331.46 | 254.81 | 73.18 | 133.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21931304200 |  | 100302451 |  | 6712212G | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE | 2621D | SWANSEA | 1263 SWANSEA CT | 067 | LEX | 2023-04-19 | U930915 | AOC SYST | 2021-08-06 | 2022-02-04 | 2022-12-31 |  | ABLAKE | 2023-04-19 | 2023-03-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 22.45 | 7 | 1562.31 | 1259.34 | 124.9 | 117.57 | 60.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026244100 |  |  |  | 6712228A | 2294088 | U461383 |  | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2621M | HILLSIDE | HILLSIDE DR | 209 | GEO | 2023-07-17 | U123258 | U461383 | 2022-12-15 | 2023-11-30 | 2023-12-01 | 2023-04-19 | CONNOR WEMPE | 2023-04-19 | 2023-03-29 |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00909 | 3200909 |  |  | WP2441 |  |  | 100 | 090932220262441 | 24.4667 | 0 | 17388.43 | 1557.17 | 0 | 667.74 | 15069.33 | 0 | 94.19 | 0
KY | KY - WEST | 2621 | 22111274700 |  | 100311340 |  | 6712204C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | HOLWYN | 3425 HOLWYN RD | 067 | LEX | 2023-04-20 | U930915 | AOC SYST | 2022-06-20 | 2022-12-20 | 2023-12-31 |  | LSTANFI | 2023-04-19 | 2023-04-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 13.7667 | 5 | 1419.27 | 812.32 | 199.64 | 344.61 | 62.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129041200 |  | 100249506 |  | 7356216G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SILVER MAPLE | 11 SILVER MAPLE ST | 127 | LOU | 2023-04-25 | DYOUNG | U130722 | 2022-09-05 | 2022-12-30 |  |  | BMEEK | 2023-04-19 | 2023-04-05 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 14.6667 | 4 | 1091.44 | 935.32 | 10.01 | 146.11 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129121500 |  | 100244945 |  | 7356216D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 207 W MAIN ST | 127 | LOU | 2023-04-20 | U132743 | U125208 | 2022-09-06 | 2022-12-30 |  |  | BMEEK | 2023-04-19 | 2023-04-05 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 8.05 | 4 | 617.04 | 514.29 | 20.27 | 82.48 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026246800 |  |  |  | 7356256B | 2394672 | U132280 |  | 561 | EX | INSTALL 800'-4" PMMP | 2600B | MONTGOMERY | MONTGOMERY AV | 019 | ASH | 2023-10-18 | U128132 | U132280 | 2023-01-03 | 2023-03-17 | 2023-04-28 | 2023-04-13 | DAVID SKAGGS | 2023-04-19 | 2023-03-15 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00561 | 3200561 |  |  | WP2468 |  |  | 100 | 056132230262468 | 205.2833 | 10634 | 248116.67 | 15910.71 | 5826.94 | 2712.36 | 186093.74 | 0 | 0 | 37572.92 | 409
KY | KY - EAST | 2631 | 23026246900 |  |  |  | 7356256B | 2394672 | U132280 |  | 562 | EX | RETIRE 1000'-4" P-MP | 2600B | MONTGOMERY | MONTGOMERY AV | 019 | ASH | 2023-06-20 | U128132 | U132280 | 2023-01-03 | 2023-04-28 | 2023-04-28 | 2023-04-13 | DAVID SKAGGS | 2023-04-19 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00562 | 3200562 |  |  | WP2469 |  |  | 100 | 056232230262469 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026264700 |  |  |  | 6716208D | 2395969 | U461383 |  | 557 | EX | INSTALL 100' OF 3"PMLP MAIN | 2621P | COLUMBIA | 625 COLUMBIA AV | 067 | LEX | 2023-05-25 | U133347 | U461383 | 2023-03-03 | 2023-12-21 | 2024-08-11 | 2023-04-05 | HMCKUNE | 2023-04-19 | 2023-04-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2647 | AMRCB |  | 100 | 055732230262647 | 73.7667 | 1200 | 21922.36 | 4253.08 | 2943.07 | 478.99 | 10934.63 | 0 | 29.12 | 3283.47 | 100
KY | KY - WEST | 2621 | 23026264800 |  |  |  | 6716208D | 2395969 | U461383 |  | 558 | EX | RETIRE 100' OF 3"BSLP MAIN | 2621P | COLUMBIA | 625 COLUMBIA AV | 067 | LEX | 2023-05-23 | U133347 | U461383 | 2023-03-03 | 2023-12-29 | 2024-08-11 | 2023-04-05 | HMCKUNE | 2023-04-19 | 2023-04-03 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2648 | AMRCB |  | 100 | 055832230262648 | 83.3333 | 0 | 6487.75 | 4892.49 | 0 | 1595.26 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156273900 |  | 100356346 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | MILLER | 1161 MILLER AV | 161 | MAY | 2023-04-19 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-19 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1949.19 | 0 | 0 | 0 | 1949.19 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156274000 |  | 100356341 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | MILLER | 1162 MILLER AV | 161 | MAY | 2023-04-19 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-19 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1538.98 | 0 | 0 | 0 | 1538.98 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164749000 |  | 100281542 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | CHESTNUT | 612 CHESTNUT ST | 209 | GEO | 2023-04-19 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-04-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.3333 | 1 | 2819.81 | 331.73 | 0 | 81.68 | 2406.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164749100 |  | 100281541 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | CHESTNUT | 613 CHESTNUT ST | 209 | GEO | 2023-04-19 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-04-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.3167 | 1 | 2382.75 | 82.95 | 0 | 20.42 | 2279.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165281300 |  | 100336869 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | JOHNSON | 461 JOHNSON AV | 067 | LEX | 2023-04-19 | U126309 | U125763 | 2023-02-07 | 2023-12-29 |  |  | JAMIE LYNN | 2023-04-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3413.17 | 0 | 0 | 0 | 3413.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165289900 |  | 100336873 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | JOHNSON | 457 JOHNSON AV | 067 | LEX | 2023-04-19 | U126309 | U125763 | 2023-02-07 | 2023-12-29 |  |  | JAMIE LYNN | 2023-04-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2365.09 | 0 | 0 | 0 | 2365.09 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168136300 |  | 100275253 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WILKINSON | 307 WILKINSON ST | 073 | FRA | 2023-04-19 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-04-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2169.68 | 0 | 0 | 0 | 2169.68 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168136600 |  | 100275258 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WILKINSON | 314 WILKINSON ST | 073 | FRA | 2023-04-19 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-04-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3351.6 | 0 | 0 | 0 | 3351.6 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23176964200 |  | 500312399 |  | 6696212O |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTRQD | 2621P | BLACK HAWK | 238 BLACK HAWK CR A-1FR | 239 | VER | 2023-04-21 | U128410 | U125208 | 2023-03-29 | 2023-04-28 | 2023-04-29 |  | CDESPAIN | 2023-04-19 | 2023-04-19 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 38.7167 | 6 | 2721.2 | 2548.92 | 33.29 | 138.99 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23182510400 |  | 100317063 |  | 6716208J | 2394661 |  |  | 565 | EX | REPLACE SL W/23026246400 | 2600B | BURT | 145 BURT RD 3 | 067 | LEX | 2023-04-19 | U126604 | U131066 | 2023-04-19 | 2023-12-29 |  |  | WILL FULKS | 2023-04-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2653.02 | 0 | 0 | 0 | 2653.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23182510500 |  | 100317065 |  | 6716208J | 2394661 |  |  | 565 | EX | REPLACE SL W/23026246400 | 2600B | BURT | 145 BURT RD 5 | 067 | LEX | 2023-04-19 | U126604 | U131066 | 2023-04-19 | 2023-12-29 |  |  | WILL FULKS | 2023-04-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2653.02 | 0 | 0 | 0 | 2653.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11896995800 |  | 100462422 |  | 6716204E |  |  |  | 566 | EX | ABANDON SL - IDLE/INA + ACTIVE | 2621P | NICHOLASVILLE | 4001 NICHOLASVILLE RD H | 067 | LEX | 2023-04-21 | U132743 | U906631 | 2011-03-22 | 2020-12-31 |  |  | DMARSTO | 2023-04-20 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.6667 | 3 | 517.81 | 491 | 0 | 26.81 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026243000 |  |  |  | 6716216G | 2294088 | U461383 |  | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2621M | PARALLEL | 2032 PARALLEL DR | 067 | LEX | 2023-07-17 | U123258 | U461383 | 2022-12-14 | 2023-11-30 | 2023-12-01 | 2023-04-20 | BLONE | 2023-04-20 | 2023-03-20 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP2430 |  |  | 100 | 090932220262430 | 53.6833 | 0 | 20860 | 3538.58 | 0 | 774.82 | 16444.46 | 0 | 102.14 | 0
KY | KY - WEST | 2621 | 22124319600 |  | 100318656 |  | 6716204F | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | LOCH LOMOND | 202 LOCH LOMOND DR | 067 | LEX | 2023-04-20 | KKINDER | AOC SYST | 2022-08-16 | 2023-02-16 | 2023-12-31 |  | KKINDER | 2023-04-20 | 2023-04-04 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 16.85 | 9 | 1769.36 | 1026.17 | 609.47 | 71.02 | 62.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22124326500 |  | 100318662 |  | 6716204F | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | LOCH LOMOND | 214 LOCH LOMOND DR | 067 | LEX | 2023-04-20 | U930915 | AOC SYST | 2022-08-16 | 2023-02-16 | 2023-12-31 |  | KKINDER | 2023-04-20 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 16.5167 | 3 | 1296.66 | 950.55 | 229.39 | 51.82 | 64.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22137500900 |  | 100339604 |  | 6724212A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MARIETTA | 1845 MARIETTA DR | 067 | LEX | 2023-04-26 | U930915 | U130722 | 2022-10-07 | 2022-12-30 |  |  | MSHARON | 2023-04-20 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.85 | 2 | 465.89 | 441.81 | 0 | 24.08 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22150011400 |  | 500546198 |  | 6724204A | 9613371 |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2600B | SHORESIDE | 393 SHORESIDE DR | 067 | LEX | 2023-04-20 | U461322 | U124960 | 2022-12-21 | 2023-02-17 | 2024-08-31 |  | STEVE CANOY | 2023-04-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26210022 | 8 | 1 | 2739.27 | 513.57 | 0 | 606.93 | 1618.77 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156274100 |  | 100356351 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | MILLER | 1164 MILLER AV | 161 | MAY | 2023-04-20 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-20 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1755.51 | 0 | 0 | 0 | 1755.51 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156274200 |  | 100356347 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | MILLER | 1165 MILLER AV | 161 | MAY | 2023-04-20 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-20 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1926.87 | 0 | 0 | 0 | 1926.87 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156274300 |  | 100356350 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | MILLER | 1166 MILLER AV | 161 | MAY | 2023-04-20 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-20 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1755.51 | 0 | 0 | 0 | 1755.51 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23158585900 |  | 100353740 |  | 7256280L | 1855043 |  |  | 566 | EX | ABANDON SL - SOII/INSIDE | 2621P | 2ND | 134 W 2ND ST | 161 | MAY | 2023-04-24 | JTOY | U130868 | 2023-01-26 | 2023-04-24 | 2023-04-24 |  | ABHATFIE | 2023-04-20 | 2023-03-21 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 10.3667 | 3 | 735.95 | 682.94 | 15.52 | 37.49 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164748100 |  | 100281537 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | CHESTNUT | 605 CHESTNUT ST | 209 | GEO | 2023-04-20 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-04-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.5167 | 1 | 2529.53 | 218.27 | 0 | 53.75 | 2257.51 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164748300 |  | 100281538 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | CHESTNUT | 607 CHESTNUT ST | 209 | GEO | 2023-04-20 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-04-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.016667 | 1 | 2970.38 | 1.24 | 0 | 0.31 | 2968.83 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164760000 |  | 100281547 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 300 PAYNE AV | 209 | GEO | 2023-04-20 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-04-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2338.36 | 0 | 0 | 0 | 2338.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165279800 |  | 100336882 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | JOHNSON | 411 JOHNSON AV | 067 | LEX | 2023-04-20 | U126309 | U125763 | 2023-02-07 | 2023-12-29 |  |  | JAMIE LYNN | 2023-04-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3946.65 | 0 | 0 | 0 | 3946.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165281000 |  | 100336900 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | JOHNSON | 436 JOHNSON AV | 067 | LEX | 2023-04-20 | U126309 | U125763 | 2023-02-07 | 2023-12-29 |  |  | JAMIE LYNN | 2023-04-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2916.21 | 0 | 0 | 0 | 2916.21 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166691500 |  | 500534470 |  | 6684228J | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | RIVERVIEW | 105 RIVERVIEW ST | 073 | FRA | 2023-04-20 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-04-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3023.13 | 0 | 0 | 0 | 3023.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166704900 |  | 100309689 |  | 6712208L | 2184394 |  |  | 565 | EX | RPLC SL/22026223700 | 2600B | PASADENA | 617 PASADENA DR | 067 | LEX | 2023-04-20 | U126284 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JOSH PASLEY/STANLEY PIPELINE | 2023-04-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 8 | 1 | 6464.06 | 521.29 | 0 | 607.35 | 5335.42 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168135500 |  | 100275033 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WILKINSON | 112 WILKINSON ST | 073 | FRA | 2023-04-20 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-04-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2468.19 | 0 | 0 | 0 | 2468.19 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168136700 |  | 100275259 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WILKINSON | 316 WILKINSON ST | 073 | FRA | 2023-04-20 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-04-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2582.4 | 0 | 0 | 0 | 2582.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23172795100 |  | 100431280 |  | 6720212N |  |  |  | 565 | EX | NBT - SERVICE LINE - REPLACE | 2621P | NATIONAL | 938< NATIONAL AV | 067 | LEX | 2023-04-20 | LSTANFI | U125208 | 2023-03-09 | 2023-03-14 | 2023-03-30 |  | LSTANFI | 2023-04-20 | 2023-03-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.6333 | 7 | 1863.32 | 1049.63 | 609.45 | 173.44 | 30.8 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23176279200 |  | 100244825 |  | 7356216D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE SERVICE | 2631D | MADISON | 108 E MADISON ST | 127 | LOU | 2023-04-20 | BMEEK | AOC SYST | 2023-03-24 | 2023-04-21 | 2023-05-23 |  | BMEEK | 2023-04-20 | 2023-04-20 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 27.9333 | 3 | 5265.24 | 1823.9 | 228.59 | 510.27 | 2702.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176930000 |  | 100317061 |  | 6716208J | 2394661 |  |  | 565 | EX | RPLC SL/23026246400 | 2600B | BURT | 145 BURT RD 1 | 067 | LEX | 2023-04-20 | U126604 | U125763 | 2023-03-29 | 2023-12-29 |  |  | WILL FULKS | 2023-04-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2410.32 | 0 | 0 | 0 | 2410.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23178657000 |  | 100326824 |  | 6720208P |  |  |  | 565 | EX | NBT - SL/MTR UPGRADE 1" AL425 | 2621P | CHINOE | 508 CHINOE RD | 067 | LEX | 2023-04-20 | U930915 | U125208 | 2023-04-03 | 2023-03-31 | 2023-04-28 |  | RJCRAWF | 2023-04-20 | 2023-04-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 38.4833 | 8 | 4809.24 | 2148.01 | 516.9 | 117.18 | 2027.15 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23180965100 |  | 100457436 |  | 7356216L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D244436 | 2621P | GENE WILSON | 75 GENE WILSON BV 1103 | 127 | LOU | 2023-04-21 | U132743 | U125208 | 2023-04-13 | 2023-04-14 | 2023-05-03 |  | BROBERT | 2023-04-20 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 13.25 | 2 | 1535.31 | 883.19 | 30.01 | 590.21 | 31.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23181446100 |  | 100290639 |  | 6720216O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309429 | 2621P | OLD PARIS | 1663 OLD PARIS RD | 067 | LEX | 2023-04-20 | TROE | U125208 | 2023-04-14 | 2023-04-14 | 2023-05-04 |  | TROE | 2023-04-20 | 2023-04-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 22.1333 | 5 | 3268.97 | 1402.82 | 205.75 | 76.5 | 1583.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23182510600 |  | 100317067 |  | 6716208J | 2394661 |  |  | 565 | EX | REPLACE SL W/23026246400 | 2600B | BURT | 145 BURT RD 7 | 067 | LEX | 2023-04-20 | U126604 | U131066 | 2023-04-19 | 2023-12-29 |  |  | WILL FULKS | 2023-04-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2407.58 | 0 | 0 | 0 | 2407.58 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23182728500 |  | 500127887 |  | 6744208L | 2292377 |  |  | 565 | EX | RPLC SL/22026228200 | 2600B | MAPLE | 308 N MAPLE ST | 049 | WIN | 2023-04-21 | U126603 | U131066 | 2023-04-20 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-04-20 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2924.96 | 0 | 0 | 0 | 2924.96 | 0 | 0 | 0
KY | KY - WEST | 2623 | 06654122600 |  | 500218091 |  | V-905/50 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PARIS | 1541 PARIS PK B | 209 | GEO | 2023-04-24 | U132743 | RPOLLY | 2006-07-19 | 2020-12-31 |  |  | DCOLLIN | 2023-04-21 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 1.1 | 2 | 98.59 | 72.06 | 0 | 26.53 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 07689048700 |  | 100361008 | [5 empty] | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CLINTONVILLE | 1791 CLINTONVILLE RD | 017 | PAR | 2023-04-24 | JTOY | U903504 | 2007-05-31 | 2020-12-31 |  |  | ANICHOLS | 2023-04-21 | 2023-04-21 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.15 | 0 | 486.93 | 281.56 | 0 | 205.37 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11896742300 |  | 500275073 |  | 7240216L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE + | 2621P | DOE RUN | 600 DOE RUN DR 9 | 173 | MT | 2023-04-24 | U930915 | U906631 | 2011-03-21 | 2020-12-31 |  |  | DENNING | 2023-04-21 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.9667 | 2 | 319.54 | 193.22 | 0 | 126.32 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 12976847600 |  | 100282291 |  | 6712228B |  |  |  | 566 | EX | PAPER ABANDON - IDLE/INACTIVE | 2621P | HAMILTON | 215 N HAMILTON ST C | 209 | GEO | 2023-04-21 | DCOLLIN | U125208 | 2012-06-18 | 2020-12-31 |  |  | DCOLLIN | 2023-04-21 | 2023-04-19 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 4.3 | 3 | 547.97 | 374.71 | 0 | 173.26 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21930296400 |  | 100302278 |  | 6712212G | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE | 2621D | ROCKY POINT | 2313 ROCKY POINT CT B | 067 | LEX | 2023-04-21 | ABLAKE | AOC SYST | 2021-08-03 | 2022-02-03 | 2022-12-31 |  | ABLAKE | 2023-04-21 | 2023-03-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.2833 | 5 | 1982.89 | 1133.39 | 741.04 | 62.26 | 46.2 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026244300 |  |  |  | 6692224G | 2294088 | U461383 |  | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2621M | DUCKER STATION | DUCKER STATION RD | 239 | MID | 2023-07-17 | U123258 | U461383 | 2022-12-15 | 2023-11-30 | 2023-12-01 | 2023-04-21 | CONNOR WEMPE | 2023-04-21 | 2023-03-21 |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00909 | 3200909 |  |  | WP2443 |  |  | 100 | 090932220262443 | 43.9833 | 0 | 21295.01 | 2767.41 | 0 | 171.06 | 18257.26 | 0 | 99.28 | 0
KY | KY - WEST | 2621 | 22124327800 |  | 100318668 |  | 6716204F | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | LOCH LOMOND | 223 LOCH LOMOND DR | 067 | LEX | 2023-04-21 | KKINDER | AOC SYST | 2022-08-16 | 2023-02-16 | 2023-12-31 |  | KKINDER | 2023-04-21 | 2023-04-21 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 11.7 | 2 | 1475.98 | 763.19 | 632.66 | 41.63 | 38.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129082500 |  | 100289397 |  | 6724212A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ROSEWOOD | 608 ROSEWOOD DR | 067 | LEX | 2023-04-21 | MSHARON | U130722 | 2022-09-05 | 2022-12-30 |  |  | MSHARON | 2023-04-21 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 14.15 | 2 | 758.5 | 719.27 | 0 | 39.23 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22137501500 |  | 501139216 |  | 6724212M | 1316677 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HADDRELL | 2004 HADDRELL CV | 067 | LEX | 2023-04-24 | U930915 | U130722 | 2022-10-07 | 2022-12-30 |  |  | MSHARON | 2023-04-21 | 2023-04-20 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.7333 | 4 | 495.23 | 469.61 | 0 | 25.62 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026268400 |  | 501346021 |  | 6728208I | 2396366 | U461383 |  | 555 | EX | INSTALL 2000' OF 2"PMMP MAIN | 2600B | STOLEN HORSE | STOLEN HORSE TC LT64 | 067 | LEX | 2023-05-08 | U136251 | U461383 | 2023-03-22 | 2023-05-04 | 2023-05-31 | 2023-04-21 | DEREK PAYTON | 2023-04-21 | 2023-04-03 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2684 |  |  | 100 | 055532230262684 | 115 | 27958 | 56232.52 | 7310.73 | 5137.88 | 398.63 | 34371.85 | 0 | 126.67 | 8886.76 | 1997
KY | KY - WEST | 2623 | 23026273500 |  |  |  | 6712224H | 2397374 | U461383 |  | 557 | EX | EMER-INSTALL 65' OF 2"PMIP | 2621P | LEE | 124 LEE LN | 209 | GEO | 2024-04-11 | U136251 | U461383 | 2023-05-03 | 2023-04-18 | 2023-04-19 | 2023-04-21 | S.BARKER | 2023-04-21 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP2735 |  |  | 100 | 055732230262735 |  | 87 | 5983.61 | 4500.04 | 0 | 633 | 0 | 0 | 9.78 | 840.79 | 87
KY | KY - WEST | 2623 | 23026273600 |  |  |  | 6712224H | 2397374 | U461383 |  | 558 | EX | EMER-RETIRE 55' OF 2"PAIP | 2621P | LEE | 124 LEE LN | 209 | GEO | 2024-04-01 | U136251 | U461383 | 2023-05-03 | 2023-04-19 | 2023-04-19 | 2023-04-21 | MCOLLINS | 2023-04-21 | 2023-06-23 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP2736 |  |  | 100 | 055832230262736 | 11.6167 | 0 | 1024.42 | 787.63 | 0 | 236.79 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156274400 |  | 100356349 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | MILLER | 1168 MILLER AV | 161 | MAY | 2023-04-21 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-21 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1933.59 | 0 | 0 | 0 | 1933.59 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156274500 |  | 100356348 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | MILLER | 1169 MILLER AV | 161 | MAY | 2023-04-21 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-21 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1936.79 | 0 | 0 | 0 | 1936.79 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164754500 |  | 100281566 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | GANO | 213 GANO AV | 209 | GEO | 2023-04-21 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-04-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 1 | 2991.65 | 498.87 | 0 | 122.83 | 2369.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165280900 |  | 100336898 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | JOHNSON | 430 JOHNSON AV | 067 | LEX | 2023-04-21 | U126309 | U125763 | 2023-02-07 | 2023-12-29 |  |  | JAMIE LYNN | 2023-04-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4847.47 | 0 | 0 | 0 | 4847.47 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166691600 |  | 500659365 |  | 6684228J | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | RIVERVIEW | 107 RIVERVIEW ST | 073 | FRA | 2023-04-21 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-04-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3064.4 | 0 | 0 | 0 | 3064.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166704700 |  | 100309688 |  | 6712208L | 2184394 |  |  | 565 | EX | RPLC SL/22026223700 | 2600B | PASADENA | 615 PASADENA DR | 067 | LEX | 2023-04-21 | U126284 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JOSH PASLEY/STANLEY PIPELINE | 2023-04-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 2.85 | 1 | 4392.83 | 185.73 | 0 | 216.39 | 3990.71 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23167372700 |  | 100458549 |  | 6716216I |  |  |  | 565 | EX | SERVICE LINE - REPLACE PR 2413 | 2621P | MERCER | 1800 MERCER RD OLD BLG | 067 | LEX | 2023-04-21 | U930915 | U125208 | 2023-02-16 | 2023-02-22 | 2023-03-09 |  | DMEDLEY | 2023-04-21 | 2023-02-27 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 125.2333 | 17 | 18660.71 | 7652.49 | 193.43 | 2491.04 | 8323.75 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168136500 |  | 500181893 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WILKINSON | 309 WILKINSON ST | 073 | FRA | 2023-04-21 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-04-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2314.61 | 0 | 0 | 0 | 2314.61 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23179790600 |  | 500287449 |  | 7240216L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE + | 2621P | DOE RUN | 600 DOE RUN DR 10 | 173 | MT | 2023-04-24 | U132743 | U125208 | 2023-04-07 | 2010-12-30 | 2023-12-31 |  | DENNING | 2023-04-21 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.2667 | 2 | 221.7 | 210.22 | 0 | 11.48 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23179790900 |  | 500287451 |  | 7240216L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE + | 2621P | DOE RUN | 600 DOE RUN DR 12 | 173 | MT | 2023-04-24 | U132743 | U125208 | 2023-04-07 | 2021-12-30 | 2023-12-31 |  | DENNING | 2023-04-21 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.7667 | 2 | 529.72 | 242.93 | 0 | 286.79 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23181695600 |  | 100278242 |  | 6688228B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D221435 | 2621P | COMANCHE | 525 COMANCHE TL | 073 | FRA | 2023-04-24 | U132743 | U125208 | 2023-04-17 | 2023-04-17 | 2023-05-05 |  | EFGOINS | 2023-04-21 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 14 | 2 | 880.04 | 766.72 | 0 | 41.82 | 71.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23182480800 |  | 100282292 |  | 6712228B |  |  |  | 566 | EX | PAPER ABANDON - IDLE/INACTIVE | 2621P | HAMILTON | 215 N HAMILTON ST A | 209 | GEO | 2023-04-21 | DCOLLIN | U125208 | 2023-04-19 | 2023-04-19 |  |  | DCOLLIN | 2023-04-21 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 1.9333 | 2 | 183.53 | 136.26 | 0 | 47.27 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23182481000 |  | 100459422 |  | 6712228B |  |  |  | 566 | EX | PAPER ABANDON - IDLE/INACTIVE | 2621P | HAMILTON | 215 N HAMILTON ST B | 209 | GEO | 2023-04-21 | DCOLLIN | U125208 | 2023-04-19 | 2023-04-19 |  |  | DCOLLIN | 2023-04-21 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 7.1667 | 2 | 742.1 | 542.47 | 0 | 199.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23182510700 |  | 100317069 |  | 6716208J | 2394661 |  |  | 565 | EX | REPLACE SL W/23026246400 | 2600B | BURT | 145 BURT RD 9 | 067 | LEX | 2023-04-21 | U126604 | U131066 | 2023-04-19 | 2023-12-29 |  |  | WILL FULKS | 2023-04-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2988.06 | 0 | 0 | 0 | 2988.06 | 0 | 0 | 0
KY | KY - WEST | 2623 | 03533605000 |  | 100347250 |  | 6696212K | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | R1 CLIFTON | R1 CLIFTON RD | 239 | VER | 2023-04-24 | U131418 | DMCCULL | 2003-03-13 | 2022-07-01 | 2023-12-31 |  | J. PARKS | 2023-04-24 | 2022-11-17 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.2 | 3 | 537.03 | 1.27 | 0 | 0.08 | 535.68 | 0 | 0 | 0
KY | KY - WEST | 2623 | 03533607000 |  | 100347249 |  | X00000000 | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | R1 CLIFTON | R1 CLIFTON RD | 239 | VER | 2023-04-24 | U131418 | DMCCULL | 2003-03-13 | 2022-07-01 | 2023-12-31 |  | J. PARKS | 2023-04-24 | 2022-12-15 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 6.0667 | 1 | 994.24 | 435.81 | 0 | 22.75 | 535.68 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 06650509400 |  | 100412043 |  | 6764176P |  |  |  | 566 | EX | NEEDS REVIEWED - RETIRE | 2621P | KIRKLAND | 523 KIRKLAND AV ASSEMBL | 065 | RAV | 2023-04-24 | U930915 | SKSMITH | 2006-06-09 | 2020-12-31 |  |  | DENNING | 2023-04-24 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.3333 | 2 | 562.41 | 533.33 | 0 | 29.08 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 10872505000 |  | 100285996 |  | 6764176P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KIRKLAND | 198 KIRKLAND AV | 065 | IRV | 2023-05-03 | U125208 | U906609 | 2010-12-16 | 2020-12-31 |  |  | DENNING | 2023-04-24 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.8667 | 2 | 419.41 | 246.77 | 20.27 | 152.37 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 11898061900 |  | 100259401 |  | 7344148I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | HIGH | HIGH ST | 071 | DRI | 2023-04-24 | U131418 | U906631 | 2011-03-28 | 2022-07-01 | 2023-12-31 |  | J. PARKS | 2023-04-24 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - EAST | 2631 | 11898557500 |  | 500568530 |  | 7348252O | 0678421 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | US ROUTE 60 | 9427< US ROUTE 60 | 019 | ASH | 2023-04-24 | U131418 | U906631 | 2011-03-30 | 2022-07-01 | 2023-12-31 |  | J. PARKS | 2023-04-24 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 447.75 | 0 | 0 | 0 | 447.75 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11921677500 |  | 500661965 |  | 6740232A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE * | 2621P | SANDRA | 12 SANDRA LN | 017 | PAR | 2023-04-25 | U930915 | U124449 | 2011-08-25 | 2020-12-31 |  |  | NRICHIE | 2023-04-24 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.8333 | 2 | 254.26 | 241.12 | 0 | 13.14 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11921677800 |  | 500661966 |  | 6740232A |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM + | 2621P | SANDRA | 13 SANDRA LN | 017 | PAR | 2023-04-24 | NRICHIE | U124449 | 2011-08-25 | 2020-12-31 |  |  | NRICHIE | 2023-04-24 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.1 | 2 | 143.2 | 135.8 | 0 | 7.4 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 14270832800 |  | 100242104 | 42 | 7356252O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | GREENUP | 949 GREENUP ST | 019 | CAT | 2023-04-24 | U131418 | RSHORTR | 2014-12-16 | 2022-07-01 | 2023-12-31 |  | J. PARKS | 2023-04-24 | 2022-12-13 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.2167 | 3 | 673.94 | 163.53 | 0 | 37.59 | 472.82 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883058300 |  | 100458786 |  | 7344264A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | CAROLINE | 213 CAROLINE AV | 089 | WUR | 2023-04-24 | U131418 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | J. PARKS | 2023-04-24 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1
KY | KY - EAST | 2631 | 21883314200 |  | 500917462 |  | 7348264B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | GREENUP | 622 GREENUP AV C | 089 | RAC | 2023-04-24 | U131418 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | J. PARKS | 2023-04-24 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1
KY | KY - WEST | 2621 | 21932649500 |  | 100301646 |  | 6712212H | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | LIVERPOOL | 228 LIVERPOOL RD | 067 | LEX | 2023-04-24 | MCRAIG | AOC SYST | 2021-08-12 | 2022-02-11 | 2022-12-31 |  | MCRAIG | 2023-04-24 | 2023-03-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 11.9833 | 5 | 1455.87 | 685.96 | 432.23 | 271.68 | 66 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960866200 |  | 100249929 |  | 7360248E | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | SUNSET | 8513 SUNSET RD | 019 | CAT | 2023-04-25 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH JERRY NEWSOME | 2023-04-24 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1991.67 | 0 | 0 | 0 | 1991.67 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960890200 |  | 100249931 |  | 7360248E | 2180320 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | SUNSET | 8507 SUNSET RD | 019 | CAT | 2023-05-02 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJ HUGHES J NEWSOME | 2023-04-24 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 |  | 1 | 882.65 | 0 | 0 | 0 | 882.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026223700 |  |  |  | 6712208H | 2184394 | U122858 |  | 561 | EX | INSTALL 1296'-2"&4" PMMP | 2600B | TUSCON | TUSCON DR | 067 | LEX | 2023-05-16 | U124014 | U122858 | 2022-09-16 | 2023-01-23 | 2023-04-30 | 2023-04-12 | JDUNN | 2023-04-24 | 2023-02-13 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP2237 |  |  | 100 | 056132220262237 | 630.4 | 111540 | 286331.62 | 42372.17 | 13640.79 | 9752.58 | 173686.07 | 0 | 1596.14 | 45283.87 | 1430
KY | KY - WEST | 2621 | 22026223800 |  |  |  | 6712208H | 2184394 | U122858 |  | 562 | EX | RETIRE 1212'-2",3"&4" CSMP | 2600B | TUSCON | TUSCON DR | 067 | LEX | 2023-05-08 | U124014 | U122858 | 2022-09-16 | 2023-03-30 | 2023-04-30 | 2023-04-12 | JDUNN | 2023-04-24 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP2238 |  |  | 100 | 056232220262238 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23154552400 |  | 500917463 |  | 7348264B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | GREENUP | 622 GREENUP AV D | 089 | RAC | 2023-04-24 | U131418 | U125763 | 2023-01-10 | 2023-12-29 | 2023-12-31 |  | J. PARKS | 2023-04-24 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156268100 |  | 100356353 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | BOONE | 537 BOONE AV | 161 | MAY | 2023-04-25 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-24 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2176.46 | 0 | 0 | 0 | 2176.46 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156274600 |  | 100356352 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | MILLER | 1171 MILLER AV | 161 | MAY | 2023-04-24 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-24 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1758.29 | 0 | 0 | 0 | 1758.29 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165281100 |  | 100336901 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | JOHNSON | 440 JOHNSON AV | 067 | LEX | 2023-04-24 | U126309 | U125763 | 2023-02-07 | 2023-12-29 |  |  | JAMIE LYNN | 2023-04-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3781.46 | 0 | 0 | 0 | 3781.46 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166693600 |  | 100461053 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 92 TANGLEWOOD DR | 073 | FRA | 2023-04-24 | U126284 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JOSH PASLEY/MILLER PIPELINE | 2023-04-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.1167 | 1 | 3968.79 | 332.31 | 0 | 387.18 | 3249.3 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166697000 |  | 100272307 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | VALLEY VISTA | 225 VALLEY VISTA DR | 073 | FRA | 2023-04-24 | U126284 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JOSH PASLEY/MILLER PIPELINE | 2023-04-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.8833 | 1 | 4945.71 | 188.97 | 0 | 220.16 | 4536.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23175642700 |  | 100331477 |  | 6720212N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333578 | 2621P | VICTORY | 103 VICTORY AV | 067 | LEX | 2023-04-25 | U132743 | U125208 | 2023-03-22 | 2023-09-21 | 2025-03-31 |  | TROE | 2023-04-24 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.75 | 3 | 1870.88 | 1096.64 | 669.33 | 59.81 | 45.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23178743300 |  | 100462095 |  | 7328284J |  |  |  | 565 | EX | REPLACE SERVICE LINE - D244394 | 2621P | STATE RT 8 | 1312 STATE RT 8 | 089 | S P | 2023-04-24 | U125208 | U125208 | 2023-04-03 | 2023-04-06 | 2023-04-24 |  | RECUMP | 2023-04-24 | 2023-04-21 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 21.9 | 3 | 1859.1 | 1415.58 | 12.38 | 375.04 | 56.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23179821200 |  | 100278269 |  | 6688228B | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPL SL D332750 | 2623D | ARAPAHO | 1009 ARAPAHO TL | 073 | FRA | 2023-05-03 | U125208 | AOC SYST | 2023-04-07 | 2023-04-10 | 2023-04-28 |  | EFGOINS | 2023-04-24 | 2023-04-24 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 16 | 2 | 1379.51 | 938.93 | 276.08 | 51.2 | 113.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23182510800 |  | 100317071 |  | 6716208J | 2394661 |  |  | 565 | EX | REPLACE SL W/23026246400 | 2600B | BURT | 145 BURT RD 11 | 067 | LEX | 2023-04-24 | U126604 | U131066 | 2023-04-19 | 2023-12-29 |  |  | WILL FULKS | 2023-04-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2022.96 | 0 | 0 | 0 | 2022.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23182510900 |  | 100317073 |  | 6716208J | 2394661 |  |  | 565 | EX | REPLACE SL W/23026246400 | 2600B | BURT | 145 BURT RD 13 | 067 | LEX | 2023-04-24 | U126604 | U131066 | 2023-04-19 | 2023-12-29 |  |  | WILL FULKS | 2023-04-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2677.3 | 0 | 0 | 0 | 2677.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23183317900 |  | 100339605 |  | 6724212A |  |  |  | 566 | EX | PAPER ABANDON - PER RI | 2621P | MARIETTA | 1845< MARIETTA DR | 067 | LEX | 2023-04-26 | U132743 | U125208 | 2023-04-24 | 2023-04-25 |  |  | JGILES | 2023-04-24 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.45 | 1 | 20.28 | 19.22 | 0 | 1.06 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 07671786300 |  | 500546010 |  | 6764176P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE * | 2621P | HOOD | 215 HOOD AV 3 | 065 | IRV | 2023-04-26 | U132743 | SKSMITH | 2007-01-09 | 2020-12-31 |  |  | DENNING | 2023-04-25 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.65 | 3 | 500.02 | 170.69 | 0 | 9.33 | 320 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026234001 |  | 501339620 |  | 6712216K | 2293159 | U461383 |  | 555 | EX | INSTALL 500' OF 2"/4"PMMP MAIN | 2600B | LUCILLE | 112 LUCILLE DR | 067 | LEX | 2023-05-19 | U128132 | U461383 | 2023-04-12 | 2023-03-21 | 2023-04-15 | 2023-04-25 | R.HUMPHREYS | 2023-04-25 | 2023-04-13 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2340 |  |  | 100 | 055532220262340 | 157.1833 | 15520 | 88694.69 | 9761.73 | 3717.36 | 3609.25 | 58168.1 | 0 | 315.27 | 13122.98 | 776
KY | KY - WEST | 2623 | 22026244200 |  |  |  | 6692224B | 2294088 | U461383 |  | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2621M | VILLAGE | 413 VILLAGE DR | 073 | FRA | 2023-07-17 | U123258 | U461383 | 2022-12-15 | 2023-11-30 | 2023-12-01 | 2023-04-25 | GHALE | 2023-04-25 | 2023-03-28 |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00909 | 3200909 |  |  | WP2442 |  |  | 100 | 090932220262442 | 30.55 | 0 | 20934.82 | 1969.99 | 0 | 687.39 | 18190.22 | 0 | 87.22 | 0
KY | KY - WEST | 2621 | 22100669900 |  | 100302489 |  | 6712212G | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | REIMS | 2428 REIMS RD | 067 | LEX | 2023-04-25 | MCRAIG | AOC SYST | 2022-05-13 | 2022-11-11 | 2023-12-31 |  | MCRAIG | 2023-04-25 | 2023-03-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 19.2 | 6 | 1958.33 | 1101.93 | 375.9 | 415.6 | 64.9 | 0 | 0 | 0
KY | KY - EAST | 2682 | 22129015300 |  | 100426451 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE TCO | 2633S | BASKET | 42 BASKET DR | 119 | RAV | 2023-04-25 | U130172 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JOHN HOWARD | 2023-04-25 |  |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 14.05 | 2 | 947.63 | 898.63 | 0 | 49 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129118000 |  | 100450648 |  | 7352256H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 13TH | 2104 13TH ST | 019 | ASH | 2023-04-25 | BMEEK | U125208 | 2022-09-06 | 2022-12-30 |  |  | BMEEK | 2023-04-25 | 2023-04-25 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 21.9833 | 3 | 2394.11 | 1398.37 | 35.11 | 376.53 | 584.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22137263000 |  | 100319241 |  | 6716208O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | HEATHER | 2351 HEATHER WY | 067 | LEX | 2023-04-25 | DMARSTO | AOC SYST | 2022-10-06 | 2023-12-31 | 2023-12-31 |  | DMARSTO | 2023-04-25 | 2023-03-21 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 16.2167 | 4 | 1524.41 | 930.55 | 465.25 | 65.91 | 62.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22137264200 |  | 100319068 |  | 6716208O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | HEATHER | 2460 HEATHER CT | 067 | LEX | 2023-04-26 | U130722 | AOC SYST | 2022-10-06 | 2023-12-31 | 2023-12-31 |  | RSTRONG | 2023-04-25 | 2023-04-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 26.6 | 6 | 2010.22 | 1581.55 | 60.48 | 266.99 | 101.2 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22150002100 |  | 100416509 |  | 7320284N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2600B | KY 8 | 18731 E KY 8 | 135 | FIR | 2023-04-25 | DESKAGG | U124960 | 2022-12-21 | 2022-10-06 | 2024-04-30 |  | DESKAGG | 2023-04-25 | 2023-01-18 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26310022 | 24.5167 | 4 | 12608.64 | 1552.49 | 264.37 | 265.88 | 10525.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026272700 |  |  |  | 6720212B | 2397220 | U122858 |  | 557 | EX | EMER - INSTALL 5'-2" PMMP | 2600E | HIGHLAWN | 219 HIGHLAWN AV | 067 | LEX | 2023-06-06 | U133333 | U122858 | 2023-04-27 | 2023-04-25 | 2023-04-25 | 2023-04-25 | LSTANFI | 2023-04-25 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2727 |  |  | 100 | 055732230262727 |  | 3 | 2367.44 | 1660.84 | 243.31 | 93.01 | 0 | 0 | 3.93 | 366.35 | 3
KY | KY - WEST | 2621 | 23026272800 |  |  |  | 6720212B | 2397220 | U122858 |  | 558 | EX | EMER - RETIRE 5'-2" PMMP | 2600E | HIGHLAWN | 219 HIGHLAWN AV | 067 | LEX | 2023-06-02 | U133333 | U122858 | 2023-04-27 | 2023-04-25 | 2023-04-25 | 2023-04-25 | LSTANFI | 2023-04-25 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2728 |  |  | 100 | 055832230262728 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156267500 |  | 100356360 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | BOONE | 523 BOONE AV | 161 | MAY | 2023-04-25 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-25 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 | 8 | 1 | 2324.4 | 510.75 | 0 | 27.86 | 1785.79 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156267600 |  | 100356359 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | BOONE | 527 BOONE AV | 161 | MAY | 2023-04-25 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-25 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1965.51 | 0 | 0 | 0 | 1965.51 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156267800 |  | 100356356 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | BOONE | 531 BOONE AV | 161 | MAY | 2023-04-25 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-25 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1811.41 | 0 | 0 | 0 | 1811.41 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156267900 |  | 100356355 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | BOONE | 533 BOONE AV | 161 | MAY | 2023-04-25 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-25 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1778.35 | 0 | 0 | 0 | 1778.35 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23158457100 |  | 100281531 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 204 PAYNE AV | 209 | GEO | 2023-04-25 | U461443 | U125763 | 2023-01-25 | 2023-12-29 |  |  | WGRAVES | 2023-04-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.3667 | 1 | 2139.58 | 146.56 | 0 | 36.09 | 1956.93 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164759400 |  | 100281532 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 208 PAYNE AV | 209 | GEO | 2023-04-25 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-04-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2384.53 | 0 | 0 | 0 | 2384.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165281500 |  | 100336903 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | JOHNSON | 466 JOHNSON AV | 067 | LEX | 2023-04-25 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-04-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 5841.75 | 0 | 0 | 0 | 5841.75 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166692000 |  | 100272409 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | SHELBY | 804 SHELBY ST | 073 | FRA | 2023-04-25 | U126284 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JOSH PASLEY/MILLER PIPELINE | 2023-04-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 1 | 5209.15 | 521.29 | 0 | 607.35 | 4080.51 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168135400 |  | 100275032 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WILKINSON | 108 WILKINSON ST | 073 | FRA | 2023-04-25 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-04-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2606.7 | 0 | 0 | 0 | 2606.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23181435700 |  | 100462106 |  | 6764176P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE + | 2621P | HOOD | 215 HOOD AV 9 | 065 | IRV | 2023-04-25 | DENNING | U125208 | 2023-04-14 | 2020-12-31 |  |  | DENNING | 2023-04-25 | 2023-04-24 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 12.9833 | 5 | 926.59 | 840.95 | 0 | 85.64 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23181435800 |  | 100285897 |  | 6764176P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE + | 2621P | HOOD | 215 HOOD AV 2 | 065 | IRV | 2023-04-25 | DENNING | U125208 | 2023-04-14 | 2020-12-31 |  |  | DENNING | 2023-04-25 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.75 | 3 | 188.3 | 178.56 | 0 | 9.74 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23182511000 |  | 100317074 |  | 6716208J | 2394661 |  |  | 565 | EX | REPLACE SL W/23026246400 | 2600B | BURT | 145 BURT RD 14 | 067 | LEX | 2023-04-25 | U126604 | U131066 | 2023-04-19 | 2023-12-29 |  |  | WILL FULKS | 2023-04-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2407.19 | 0 | 0 | 0 | 2407.19 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23182511100 |  | 100317076 |  | 6716208J | 2394661 |  |  | 565 | EX | REPLACE SL W/23026246400 | 2600B | BURT | 145 BURT RD 16 | 067 | LEX | 2023-04-25 | U126604 | U131066 | 2023-04-19 | 2023-12-29 |  |  | WILL FULKS | 2023-04-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2531.26 | 0 | 0 | 0 | 2531.26 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23183349100 |  | 100275025 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WILKINSON | 103 WILKINSON ST | 073 | FRA | 2023-04-25 | U461375 | U125763 | 2023-04-24 | 2023-12-29 |  |  | LARRY BROWN | 2023-04-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2224.36 | 42.6 | 0 | 2.33 | 2179.43 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23183550300 |  | 100346869 |  | 6696212K |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | MAPLE | 106 MAPLE AV | 239 | VER | 2023-04-25 | U128410 | U131552 | 2023-04-25 | 2023-04-25 |  |  | CDESPAIN | 2023-04-25 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 17.95 | 2 | 1578.98 | 1192.85 | 262.78 | 65.05 | 58.3 | 0 | 0 | 0
KY | KY - EAST | 2633 | 05599108500 |  | 100259387 |  | 7344148J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | DRIFT HILL | DRIFT HILL | 071 | DRI | 2023-04-26 | JAHOWARD | DYOUNG | 2005-01-21 | 2022-07-01 | 2023-12-31 |  | JAHOWARD | 2023-04-26 | 2022-10-06 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 19.0667 | 4 | 1283.98 | 1217.58 | 0 | 66.4 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11889325800 |  | 500128401 |  | 6736228C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE * | 2621P | MARTIN LUTHER | 2226 MARTIN LUTHER BV | 017 | PAR | 2023-04-26 | U930915 | U906631 | 2011-02-16 | 2020-12-31 |  |  | NRICHIE | 2023-04-26 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9.9 | 2 | 1020.64 | 628.19 | 0 | 392.45 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 12101330900 |  | 100259388 |  | 7344148J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE + | 2621P | DRIFT HILL | DRIFT HILL | 071 | DRI | 2023-04-26 | U130172 | U125201 | 2012-12-06 | 2014-12-31 |  |  | JOHN HOWARD | 2023-04-26 | 2023-04-26 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 4.5167 | 2 | 302.83 | 287.17 | 0 | 15.66 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960857300 |  | 100249920 |  | 7360248E | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | MAYO TRAIL | 10118 MAYO TRAIL RD A1 | 019 | CAT | 2023-04-27 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH JERRY NEWSOME | 2023-04-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2587.56 | 0 | 0 | 0 | 2587.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026243100 |  |  |  | 6712216O | 2294088 | U461383 |  | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2621M | OLD FRANKFORT | OLD FRANKFORT PK | 067 | LEX | 2023-07-17 | U123258 | U461383 | 2022-12-14 | 2023-11-30 | 2023-12-01 | 2023-04-26 | BLONE | 2023-04-26 | 2023-03-21 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP2431 |  |  | 100 | 090932220262431 | 41.3667 | 0 | 18742.99 | 2689.35 | 0 | 155.13 | 15811.63 | 0 | 86.88 | 0
KY | KY - EAST | 2633 | 22129033300 |  | 100259390 |  | 7344148I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NEED ADDR > 811 | NEED ADDR > 811 | 071 | DRI | 2023-04-26 | JAHOWARD | U130722 | 2022-09-05 | 2023-04-26 |  |  | JAHOWARD | 2023-04-26 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.6 | 1 | 42.57 | 40.37 | 0 | 2.2 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156273000 |  | 100356358 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | LEWIS | 1230 LEWIS ST | 161 | MAY | 2023-04-27 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-26 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2541.13 | 0 | 0 | 0 | 2541.13 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164759500 |  | 100445118 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 209 PAYNE AV | 209 | GEO | 2023-04-27 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-04-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2974.46 | 0 | 0 | 0 | 2974.46 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164759700 |  | 100281534 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 216 PAYNE AV | 209 | GEO | 2023-04-27 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-04-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3007.58 | 0 | 0 | 0 | 3007.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165281700 |  | 100336865 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | JOHNSON | 469 JOHNSON AV | 067 | LEX | 2023-04-27 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-04-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3415.94 | 0 | 0 | 0 | 3415.94 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166696600 |  | 100272302 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 217 TANGLEWOOD DR | 073 | FRA | 2023-04-27 | U126284 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JOSH PASLEY/MILLER PIPELINE | 2023-04-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.1 | 1 | 5964.63 | 332.31 | 0 | 387.18 | 5245.14 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168135100 |  | 100275030 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WILKINSON | 104 WILKINSON ST | 073 | FRA | 2023-04-27 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-04-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2910.84 | 0 | 0 | 0 | 2910.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168135300 |  | 100275031 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WILKINSON | 106 WILKINSON ST | 073 | FRA | 2023-04-27 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-04-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2812.36 | 0 | 0 | 0 | 2812.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23180307200 |  | 100300824 |  | 6716212E |  |  |  | 566 | EX | ABANDON SL - DEMO/LNDRK - IDLE | 2621P | GARRETT | 132 GARRETT AV | 067 | LEX | 2023-04-26 | MCRAIG | U125208 | 2023-04-11 | 2023-04-19 | 2023-05-11 |  | MCRAIG | 2023-04-26 | 2023-04-26 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.3 | 3 | 854.99 | 481.68 | 180.48 | 192.83 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23182511200 |  | 100317079 |  | 6716208J | 2394661 |  |  | 565 | EX | REPLACE SL W/23026246400 | 2600B | BURT | 145 BURT RD 18 | 067 | LEX | 2023-04-27 | U126604 | U131066 | 2023-04-19 | 2023-12-29 |  |  | WILL FULKS | 2023-04-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2251.98 | 0 | 0 | 0 | 2251.98 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23182999700 |  | 100300822 |  | 6716212E |  |  |  | 566 | EX | ABN SL - DEMO/LNBRK - PRMT 5/4 | 2621P | GARRETT | 128 GARRETT AV | 067 | LEX | 2023-04-26 | MCRAIG | U125208 | 2023-04-21 | 2023-04-26 |  |  | MCRAIG | 2023-04-26 | 2023-04-26 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.2667 | 3 | 944.27 | 542.81 | 247.79 | 153.67 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23183570700 |  | 100292463 |  | 6720216O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D310458 | 2621P | DOVER | 501 DOVER RD | 067 | LEX | 2023-04-26 | U129673 | U131552 | 2023-04-25 | 2023-04-21 | 2023-04-21 |  | ATWILLI | 2023-04-26 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 30.6333 | 8 | 2982.19 | 1576.34 | 508.83 | 827.72 | 69.3 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23183846400 |  | 100278203 |  | 6688228B |  |  |  | 565 | VO | REPLACE SERVICE LINE - LEAKAGE | 2621P | COMANCHE | 404 COMANCHE TL | 073 | FRA | 2023-04-28 |  | U129939 | 2023-04-26 | 2023-04-17 | 2023-05-05 |  | EFGOINS | 2023-04-26 | 2023-04-26 |  | A | [11 empty] | 23184280600 | 100 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 11915983100 |  | 100282603 |  | 6712228B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 120 E MAIN ST | 209 | GEO | 2023-04-27 | DCOLLIN | U124964 | 2011-07-15 | 2020-12-31 |  |  | DCOLLIN | 2023-04-27 | 2023-04-27 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 20.7 | 3 | 1731.75 | 1261.73 | 0 | 171.52 | 298.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960865600 |  | 100249922 |  | 7348260H | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | SUNSET | 8208 SUNSET RD | 019 | CAT | 2023-04-28 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH JERRY NEWSOME | 2023-04-27 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1940.91 | 0 | 0 | 0 | 1940.91 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960866000 |  | 100249927 |  | 7360248E | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | SUNSET | 8234 SUNSET RD | 019 | CAT | 2023-04-28 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH CASEY PACK | 2023-04-27 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2018.42 | 0 | 0 | 0 | 2018.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22103800600 |  | 100311224 |  | 6712208P | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE | 2621D | BETH | 632 BETH LN | 067 | LEX | 2023-04-27 | DMEDLEY | AOC SYST | 2022-05-26 | 2022-11-23 | 2023-12-31 |  | DMEDLEY | 2023-04-27 | 2023-04-27 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.6833 | 2 | 1530.03 | 834.94 | 154 | 439.89 | 101.2 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129026600 |  | 100268007 |  | 7356260N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 16TH | 236 16TH ST | 019 | ASH | 2023-05-09 | U125208 | U130722 | 2022-09-05 | 2022-12-30 | 2023-05-10 |  | BMEEK | 2023-04-27 | 2023-02-15 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 30.2167 | 8 | 2533.29 | 1905.75 | 63.69 | 563.85 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22150001800 |  | 100408540 |  | 7320284N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2600B | INDIAN RUN | 164 INDIAN RUN RD | 135 | FIR | 2023-04-27 | DESKAGG | U124960 | 2022-12-21 | 2022-10-06 | 2024-04-30 |  | DESKAGG | 2023-04-27 | 2023-01-20 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26310022 | 27.3 | 6 | 8043.64 | 1758.32 | 321.29 | 382.21 | 5581.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22152669000 |  | 100459511 |  | 6712208J |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311080 | 2621P | LYON | 3414 LYON DR | 067 | LEX | 2023-05-03 | U125208 | U125208 | 2022-12-30 | 2023-06-29 | 2024-12-31 |  | KKINDER | 2023-04-27 | 2023-04-21 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.6667 | 6 | 1728.85 | 1453.17 | 168.93 | 79.25 | 27.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22992020100 |  | 100246060 |  | 7328284J |  |  |  | 565 | EX | REPLACE SERVICE LINE - D258068 | 2600B | STATE RT 8 | 1597 STATE RT 8 | 089 | S P | 2023-04-28 | DYOUNG | U131172 | 2022-04-07 | 2022-10-06 | 2024-04-30 |  | DESKAGG | 2023-04-27 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26310022 | 1.0833 | 1 | 6070.6 | 79.04 | 207.19 | 17.11 | 5767.26 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156268500 |  | 100465386 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | BOONE | 605 BOONE DR | 161 | MAY | 2023-04-27 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-27 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2743.15 | 0 | 0 | 0 | 2743.15 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156273100 |  | 100356361 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | LEWIS | 1233 LEWIS ST | 161 | MAY | 2023-04-28 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-27 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1916.24 | 0 | 0 | 0 | 1916.24 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156273200 |  | 500344605 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | LEWIS | 1234 LEWIS ST | 161 | MAY | 2023-04-28 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-27 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2167.99 | 0 | 0 | 0 | 2167.99 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156273400 |  | 100405734 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | LEWIS | 1236 LEWIS ST | 161 | MAY | 2023-04-28 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-27 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2115.91 | 0 | 0 | 0 | 2115.91 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164759800 |  | 100281535 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 220 PAYNE AV | 209 | GEO | 2023-04-27 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-04-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2030.16 | 0 | 0 | 0 | 2030.16 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164759900 |  | 100281536 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 224 PAYNE AV | 209 | GEO | 2023-04-27 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-04-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2049.6 | 0 | 0 | 0 | 2049.6 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166691800 |  | 100272411 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | SHELBY | 800 SHELBY ST | 073 | FRA | 2023-04-28 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-04-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2845.25 | 0 | 0 | 0 | 2845.25 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166691900 |  | 100272410 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | SHELBY | 802 SHELBY ST | 073 | FRA | 2023-04-28 | U126284 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JOSH PASLEY/MILLER PIPELINE | 2023-04-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2933.64 | 0 | 0 | 0 | 2933.64 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168134000 |  | 100275007 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WATSON | 105 WATSON CT 1F | 073 | FRA | 2023-04-27 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-04-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2246.19 | 0 | 0 | 0 | 2246.19 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168134300 |  | 500110551 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WATSON | 108 WATSON CT | 073 | FRA | 2023-04-27 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-04-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2251.69 | 0 | 0 | 0 | 2251.69 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23182464600 |  | 100406370 |  | 7244216F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303635 | 2621P | MONTCLAIR | 1810 MONTCLAIR DR | 173 | MT | 2023-04-28 | JTOY | U125208 | 2023-04-19 | 2023-10-19 | 2025-04-30 |  | DENNING | 2023-04-27 | 2023-04-26 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 25.3 | 6 | 1979.29 | 1635.54 | 158.85 | 89.2 | 95.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23184039500 |  | 100332249 |  | 6720212N |  |  |  | 566 | EX | RETIRE SERVICE LINE - LEAKAGE | 2621P | NATIONAL | 938< NATIONAL AV | 067 | LEX | 2023-04-27 | LSTANFI | U130871 | 2023-04-27 | 2023-04-27 |  |  | LSTANFI | 2023-04-27 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.0333 | 0 | 92 | 67.36 | 0 | 24.64 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23184054700 |  | 100336910 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | M L KING | 473 M L KING BV 2F | 067 | LEX | 2023-04-27 | U126532 | U125763 | 2023-04-27 | 2023-12-29 |  |  | LESLIE SHARON | 2023-04-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3211.87 | 0 | 0 | 0 | 3211.87 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23184055300 |  | 100336909 |  | 6720212E | 2177145 |  |  | 566 | EX | ABANDN SL/21026997800 | 2600B | M L KING | 473 M L KING BV 1F | 067 | LEX | 2023-04-27 | U126532 | U125763 | 2023-04-27 | 2023-12-29 |  |  | LESLIE SHARON | 2023-04-27 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 22138342000 |  | 100324479 |  | 6720204E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | OLYMPIA | 3567 OLYMPIA DR | 067 | LEX | 2023-04-28 | MSHARON | AOC SYST | 2022-10-11 | 2023-04-11 | 2023-12-31 |  | MSHARON | 2023-04-28 | 2023-04-27 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 32.3667 | 5 | 2631.64 | 1663.11 | 804.59 | 103.44 | 60.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026272300 |  |  |  | 6720204M | 2397141 | U461383 |  | 559 | EX | EMER-INSTALL 3" NC POLY VALVE | 2621P | ROCKBRIDGE | 1146 ROCKBRIDGE RD | 067 | LEX | 2023-05-05 | U128132 | U461383 | 2023-04-24 | 2023-09-29 | 2023-10-01 | 2023-04-26 | RJCRAWF | 2023-04-28 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP2723 |  |  | 100 | 055932230262723 | 5.2667 | 4 | 6810.69 | 2978.2 | 275.29 | 162.41 | 2421.75 | 0 | 0.94 | 972.1 | 4
KY | KY - WEST | 2621 | 23026272400 |  |  |  | 6720204M | 2397141 | U461383 |  | 560 | EX | EMER-RETIRE 3"PV C16-87 | 2621P | ROCKBRIDGE | 1146 ROCKBRIDGE RD | 067 | LEX | 2023-05-05 | U128132 | U461383 | 2023-04-24 | 2023-09-29 | 2023-10-01 | 2023-04-26 | RJCRAWF | 2023-04-28 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00560 | 3200560 |  |  | WP2724 |  |  | 100 | 056032230262724 | 1.2333 | 0 | 85.95 | 81.5 | 0 | 4.45 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156273600 |  | 100356379 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | LEWIS | 1238 LEWIS ST | 161 | MAY | 2023-04-28 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-04-28 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2162.51 | 0 | 0 | 0 | 2162.51 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166693500 |  | 100272388 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | SHELBY | 846 SHELBY ST | 073 | FRA | 2023-04-28 | U126284 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JOSH PASLEY/MILLER PIPELINE | 2023-04-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 1 | 4126.67 | 521.29 | 0 | 607.35 | 2998.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176931900 |  | 100450445 |  | 6716208J | 2394661 |  |  | 565 | EX | RPLC SL/23026246400 | 2600B | BURT | 128 BURT RD | 067 | LEX | 2023-04-28 | U126604 | U125763 | 2023-03-29 | 2023-12-29 |  |  | WILL FULKS | 2023-04-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 9079.86 | 0 | 0 | 0 | 9079.86 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23178621600 |  | 100245556 |  | 7360252I |  |  |  | 566 | EX | ABANDON LINE | 2621P | CENTER | 2503 CENTER ST | 019 | CAT | 2023-04-28 | MCOLLET | U129939 | 2023-04-01 | 2023-03-31 |  |  | MCOLLET | 2023-04-28 | 2023-04-01 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 53.3333 | 9 | 4879.9 | 3350.26 | 0 | 1529.64 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23181123800 |  | 100285551 |  | 6768172A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR ENCROACHMENT | 2629D | CANTRILL | 628 CANTRILL ST | 065 | IRV | 2023-05-01 | U132743 | AOC SYST | 2023-04-13 | 2023-05-11 | 2023-06-10 |  | DENNING | 2023-04-28 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 21 | 3 | 1566.9 | 1386.77 | 0 | 75.63 | 104.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23184084300 |  | 100269755 |  | 6732252J |  |  |  | 566 | EX | ABANDON SL W2313 - IDLE | 2621P | (111) MASON | 277 (111) MASON LN | 097 | CYN | 2023-04-28 | NRICHIE | U125208 | 2023-04-27 | 2023-04-28 | 2023-08-16 |  | NRICHIE | 2023-04-28 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 7.6333 | 2 | 1312.34 | 816.04 | 50.13 | 446.17 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23184260900 |  | 100442068 |  | 6724208N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303211 | 2621P | BLAZER | 3499 BLAZER PY | 067 | LEX | 2023-05-01 | U132743 | U136241 | 2023-04-28 | 2023-02-10 | 2024-08-31 |  | HMCKUNE | 2023-04-28 | 2023-02-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 88.9333 | 17 | 20827.25 | 7373.04 | 1046.51 | 811.82 | 11595.88 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23184298500 |  | 100245555 |  | 7360252I |  |  |  | 566 | EX | ABD LINE | 2621P | CENTER | 2503< CENTER ST UPST | 019 | CAT | 2023-04-28 | MCOLLET | U130871 | 2023-04-28 | 2023-04-28 |  |  | MCOLLET | 2023-04-28 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.7833 | 1 | 526.67 | 198.23 | 0 | 328.44 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026188200 |  |  |  | 6716208A | 2288925 | U122858 |  | 559 | VO | INSTALL ~15'-2" PMMP | 2600B | HARRODSBURG | 1787 HARRODSBURG RD | 067 | LEX | 2023-05-02 |  | U122858 | 2022-05-18 | 2023-12-21 | 2023-12-31 |  | R.HUMPHREYS | 2023-05-01 | 2023-04-27 |  | B | [11 empty] | 23185356200 | 100 |  | 24 | 0 | 549.37 | 0 | 363.47 | 0 | 0 | 0 | 9.27 | 176.63
KY | KY - WEST | 2621 | 22111276300 |  | 100311365 |  | 6712204D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | HALIFAX | 620 HALIFAX DR | 067 | LEX | 2023-05-01 | U930915 | AOC SYST | 2022-06-20 | 2022-12-20 | 2023-12-31 |  | ABLAKE | 2023-05-01 | 2023-04-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 29.5667 | 10 | 1994.59 | 1681.67 | 98.69 | 153.73 | 60.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22128591100 |  | 100314007 |  | 6716212N | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | BURLEY | 208 BURLEY AV | 067 | LEX | 2023-05-01 | MCRAIG | AOC SYST | 2022-09-01 | 2023-03-01 | 2023-12-31 |  | MCRAIG | 2023-05-01 | 2023-05-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 16.1333 | 3 | 1690.77 | 913.22 | 403.45 | 332.3 | 41.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22138343300 |  | 100324473 |  | 6720204E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | OLYMPIA | 3551 OLYMPIA DR | 067 | LEX | 2023-05-01 | MSHARON | AOC SYST | 2022-10-11 | 2023-04-11 | 2023-12-31 |  | MSHARON | 2023-05-01 | 2023-04-25 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 19.8167 | 4 | 1931.8 | 1225.79 | 584.86 | 67.25 | 53.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23155982600 |  | 500169117 |  | 6712236N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | CINCINNATI | 1695 CINCINNATI RD | 209 | GEO | 2023-05-01 | DCOLLIN | MDULANE | 2023-01-13 | 2023-12-29 | 2023-12-31 |  | DCOLLIN | 2023-05-01 | 2023-02-24 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 28.5333 | 5 | 5249.07 | 1921.45 | 0 | 403.87 | 2923.75 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156268000 |  | 100356354 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | BOONE | 535 BOONE AV | 161 | MAY | 2023-05-02 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-05-01 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2212.26 | 0 | 0 | 0 | 2212.26 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156268200 |  | 100356374 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | BOONE | 554 BOONE AV | 161 | MAY | 2023-05-01 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-05-01 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2116.43 | 0 | 0 | 0 | 2116.43 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156273300 |  | 100356363 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | LEWIS | 1235 LEWIS ST | 161 | MAY | 2023-05-02 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-05-01 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2764.73 | 0 | 0 | 0 | 2764.73 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156273500 |  | 100356366 |  | 7256276B | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | LEWIS | 1237 LEWIS ST | 161 | MAY | 2023-05-02 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-05-01 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 3057.19 | 0 | 0 | 0 | 3057.19 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164760200 |  | 100281549 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 308 PAYNE AV | 209 | GEO | 2023-05-01 | U124003 | U125763 | 2023-02-03 | 2023-12-29 |  |  | BPULLIAM/FISHEL | 2023-05-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2676.74 | 0 | 0 | 0 | 2676.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165289800 |  | 100336899 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | JOHNSON | 432 JOHNSON AV | 067 | LEX | 2023-05-01 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-05-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4084.93 | 0 | 0 | 0 | 4084.93 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166692100 |  | 100272408 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | SHELBY | 806 SHELBY ST | 073 | FRA | 2023-05-01 | U126284 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JOSH PASLEY/MILLER PIPELINE | 2023-05-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.1167 | 1 | 3161.52 | 333.96 | 0 | 295.54 | 2532.02 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166692300 |  | 100272405 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | SHELBY | 810 SHELBY ST | 073 | FRA | 2023-05-01 | U126284 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JOSH PASLEY/MILLER PIPELINE | 2023-05-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.8833 | 1 | 3124 | 189.9 | 0 | 168.05 | 2766.05 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168134100 |  | 100275015 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WATSON | 106 WATSON CT 1F | 073 | FRA | 2023-05-01 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-05-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2300.03 | 0 | 0 | 0 | 2300.03 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168513000 |  | 100342560 |  | 7240216M | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 507 HOLT AV | 173 | MT | 2023-05-03 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-01 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3499.25 | 0 | 0 | 0 | 3499.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168513100 |  | 500145539 |  | 7240216M | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 509 HOLT AV | 173 | MT | 2023-05-03 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-01 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2823.58 | 0 | 0 | 0 | 2823.58 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23176041400 |  | 100350063 |  | 6744204D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE SERVICE | 2629D | CRESCENT | 371 CRESCENT AV | 049 | WIN | 2023-05-01 | NRICHIE | AOC SYST | 2023-03-23 | 2023-04-21 | 2023-05-22 |  | NRICHIE | 2023-05-01 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 19.05 | 3 | 1919.64 | 1229.9 | 185.78 | 412.66 | 91.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23184610200 |  | 100285169 |  | 6756176J |  |  |  | 565 | EX | NBT - REPLACE SERVICE LINE | 2621P | WINSTON | 1410 WINSTON RD | 065 | IRV | 2023-05-12 | U125208 | U134852 | 2023-05-01 | 2023-04-25 | 2023-05-11 |  | DENNING | 2023-05-01 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 13.5 | 3 | 1472.63 | 863.75 | 346.64 | 48.84 | 213.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23184657100 |  | 100293736 |  | 6720212A |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | KEES | 1123 KEES RD | 067 | LEX | 2023-05-02 | U132743 | U134852 | 2023-05-01 | 2023-05-01 | 2023-05-01 |  | LSTONE | 2023-05-01 | 2023-05-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.7667 | 5 | 1390.12 | 1212.68 | 0 | 68.54 | 108.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 04564711700 |  | 100308321 |  | 6716212N |  |  |  | 566 | EX | NEEDS REVIEWED - RETIRE | 2621P | PYKE | 407 PYKE RD | 067 | LEX | 2023-05-02 | U930915 | SSUTHER | 2004-02-02 | 2020-12-23 |  |  | KKINDER | 2023-05-02 | 2023-04-24 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.8333 | 5 | 261.73 | 247.74 | 0 | 13.99 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 06651830500 |  | 100422225 |  | 6680224L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RIDGEWOOD | 211 RIDGEWOOD LN | 073 | FRA | 2023-05-03 | U132743 | RPOLLY | 2006-06-23 | 2020-12-31 |  |  | JMARSHA | 2023-05-02 | 2023-05-01 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 12.8 | 4 | 695.34 | 658.14 | 0 | 37.2 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07688448100 |  | 100308320 |  | 6716212N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PYKE | 405 PYKE RD | 067 | LEX | 2023-05-02 | U930915 | SSUTHER | 2007-05-25 | 2049-12-31 |  |  | KKINDER | 2023-05-02 | 2023-04-21 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.4667 | 4 | 433.04 | 410.46 | 0 | 22.58 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21938175700 |  | 100301484 |  | 6712212H | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | RUGBY | 141 RUGBY RD | 067 | LEX | 2023-05-02 | MCRAIG | AOC SYST | 2021-09-07 | 2022-03-07 | 2022-12-31 |  | MCRAIG | 2023-05-02 | 2023-03-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 10.15 | 4 | 1438.03 | 636.32 | 375.66 | 321.55 | 104.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960865800 |  | 100249923 |  | 7360248E | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | SUNSET | 8224 SUNSET RD | 019 | CAT | 2023-05-03 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH DEREK CRAGER | 2023-05-02 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2649.22 | 0 | 0 | 0 | 2649.22 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22997162300 |  | 100348414 |  | 6748208J |  |  |  | 565 | EX | REPLACE SERVICE LINE - D258101 | 2621P | LOCUST GROVE | 213 LOCUST GROVE RD | 049 | WIN | 2023-05-03 | U930915 | U125208 | 2022-04-29 | 2022-10-27 | 2024-04-30 |  | NRICHIE | 2023-05-02 | 2023-05-01 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 13.3 | 6 | 1396.3 | 924.96 | 156.89 | 294.65 | 19.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026263200 |  |  |  | 7240216L | 1100065 | U461383 |  | 588 | EX | GMB TO CAB CONVERSION | 2600M | OWINGSVILLE | 2001 OWINGSVILLE RD | 173 | MT | 2023-05-15 | U123258 | U461383 | 2023-02-23 | 2023-12-01 | 2023-12-01 | 2023-05-02 | WADE SHIMFESSEL | 2023-05-02 | 2023-02-23 |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00588 | 3200588 |  |  | WP2632 |  |  | 100 | 058832230262632 | 8.3667 | 0 | 758.88 | 552.46 | 0 | 206.42 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156267700 |  | 100356357 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | BOONE | 529 BOONE AV | 161 | MAY | 2023-05-03 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-05-02 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2109.31 | 0 | 0 | 0 | 2109.31 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156268600 |  | 100356377 |  | 7256276A | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | BROOKINGS | 542 BROOKINGS AV | 161 | MAY | 2023-05-03 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-05-02 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2084.07 | 0 | 0 | 0 | 2084.07 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156273700 |  | 100356367 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | LEWIS | 1239 LEWIS ST | 161 | MAY | 2023-05-03 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-05-02 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2747.05 | 0 | 0 | 0 | 2747.05 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164760400 |  | 100281600 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 332 PAYNE AV | 209 | GEO | 2023-05-02 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-05-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3478.72 | 0 | 0 | 0 | 3478.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165280800 |  | 100336897 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | JOHNSON | 428 JOHNSON AV | 067 | LEX | 2023-05-02 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-05-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3347.35 | 0 | 0 | 0 | 3347.35 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166696200 |  | 100272384 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 206 TANGLEWOOD DR | 073 | FRA | 2023-05-02 | U126284 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JOSH PASLEY/MILLER PIPELINE | 2023-05-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 1 | 6834.47 | 523.86 | 0 | 463.6 | 5847.01 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168134600 |  | 100275019 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WATSON | 114 WATSON CT | 073 | FRA | 2023-05-02 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-05-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2856.05 | 0 | 0 | 0 | 2856.05 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168513200 |  | 100342564 |  | 7240216M | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 510 HOLT AV | 173 | MT | 2023-05-03 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-02 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3349.97 | 0 | 0 | 0 | 3349.97 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176682000 |  | 100331402 |  | 6720212N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333583 | 2621P | OWSLEY | 131 OWSLEY AV | 067 | LEX | 2023-05-03 | U132743 | U125208 | 2023-03-28 | 2023-09-22 | 2025-03-31 |  | LSTANFI | 2023-05-02 | 2023-04-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.0667 | 3 | 961.29 | 821.37 | 0 | 46.42 | 93.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176929900 |  | 100317060 |  | 6716208J | 2394661 |  |  | 565 | EX | RPLC SL/23026246400 | 2600B | BURT | 125 BURT RD | 067 | LEX | 2023-05-02 | U126604 | U125763 | 2023-03-29 | 2023-12-29 |  |  | WILL FULKS | 2023-05-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3841.44 | 0 | 0 | 0 | 3841.44 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23182744300 |  | 100347474 |  | 6744208L |  |  |  | 566 | EX | ABANDON SL - IDLE/INA/CONVRT | 2621P | EVANS | 502 EVANS ST | 049 | WIN | 2023-05-02 | NRICHIE | U125208 | 2023-04-20 | 2023-04-25 | 2023-05-20 |  | NRICHIE | 2023-05-02 | 2023-04-24 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 12.7167 | 7 | 1044.2 | 821.84 | 0 | 222.36 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23183654200 |  | 100356362 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | WALLER | 1212 WALLER ST | 161 | MAY | 2023-05-02 | U126286 | U125763 | 2023-04-25 | 2023-12-29 |  |  | TYLER ALLISON | 2023-05-02 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2001.37 | 30.79 | 0 | 1.75 | 1968.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23185294400 |  | 100288917 |  | 6724212E |  |  |  | 565 | EX | SERVICE LINE - EMER REPLACE | 2621P | ENDON | 1825 ENDON DR | 067 | LEX | 2023-05-02 | LSTONE | U125208 | 2023-05-02 | 2023-05-02 |  |  | LSTONE | 2023-05-02 | 2023-05-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.9667 | 3 | 1582.62 | 1232.19 | 191.69 | 69.64 | 89.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23185342800 |  | 100421162 |  | 7348260B |  |  |  | 565 | EX | GRD 1 ON SERVICE | 2621P | FIELDS | 2708 FIELDS AV | 089 | FLA | 2023-05-02 | BROBERT | U130871 | 2023-05-02 | 2023-05-02 | 2023-05-02 |  | BROBERT | 2023-05-02 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 7.5 | 3 | 958 | 472.96 | 209.62 | 179.72 | 95.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23185381400 |  | 100464560 |  | 6748204A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | ELIZABETH | 106 ELIZABETH ST A | 049 | WIN | 2023-05-03 | U132743 | U130871 | 2023-05-02 | 2022-11-11 | 2024-05-31 |  | DENNING | 2023-05-02 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 9.8167 | 3 | 1100.07 | 788.6 | 0 | 193.77 | 117.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21904078200 |  | 100355449 |  | 7260276B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BRYANT | 28 BRYANT CR | 161 | MAY | 2023-05-04 | U125208 | U124841 | 2021-04-19 | 2021-10-19 |  |  | ABHATFIE | 2023-05-03 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 3.85 | 2 | 278.77 | 244.66 | 20.27 | 13.84 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129029200 |  | 100248164 |  | 7356256E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 2412 MAIN ST | 019 | ASH | 2023-05-17 | U125208 | U130722 | 2022-09-05 | 2022-12-30 |  |  | BMEEK | 2023-05-03 | 2023-03-29 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 20.7 | 10 | 1696.78 | 1265.34 | 20.27 | 411.17 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129031100 |  | 100265529 |  | 7348252H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DEAL | 1209 DEAL LN | 019 | ASH | 2023-05-03 | U124015 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ORA SLONE | 2023-05-03 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 3094.47 | 0 | 0 | 0 | 3094.47 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129031700 |  | 100247449 |  | 7352256L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MCGURK | 2500 MCGURK ST A2 | 019 | ASH | 2023-05-04 | U124015 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ORA SLONE | 2023-05-03 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 3094.47 | 0 | 0 | 0 | 3094.47 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165289700 |  | 100336815 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | 4TH | 137 E 4TH ST 1FL | 067 | LEX | 2023-05-03 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-05-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3093.81 | 0 | 0 | 0 | 3093.81 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165693300 |  | 100320038 |  | 6716208K | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE SERVICE | 2621D | GLENDOVER | 235 GLENDOVER RD | 067 | LEX | 2023-05-10 | U130722 | AOC SYST | 2023-02-08 | 2023-03-09 | 2023-04-08 |  | DMARSTO | 2023-05-03 | 2023-03-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.2833 | 6 | 1407.27 | 1287.55 | 0 | 73.52 | 46.2 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166697300 |  | 100272309 |  | 6684224B | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | VALLEY VISTA | 247 VALLEY VISTA DR | 073 | FRA | 2023-05-03 | U126284 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JOSH PASLEY/MILLER PIPELINE | 2023-05-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 10 | 1 | 4780.23 | 654.82 | 0 | 579.49 | 3545.92 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168134200 |  | 100275004 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WATSON | 107 WATSON CT | 073 | FRA | 2023-05-03 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-05-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2929.48 | 0 | 0 | 0 | 2929.48 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168512600 |  | 100342554 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 415 HOLT AV 1FL | 173 | MT | 2023-05-04 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-03 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3518.43 | 0 | 0 | 0 | 3518.43 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168512700 |  | 100342556 |  | 7240216M | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 501 HOLT AV | 173 | MT | 2023-05-04 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-03 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2315.64 | 0 | 0 | 0 | 2315.64 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168512900 |  | 100342558 |  | 7240216M | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 503 HOLT AV | 173 | MT | 2023-05-03 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-03 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2660.39 | 0 | 0 | 0 | 2660.39 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23181846200 |  | 100355785 |  | 7260276B |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | CENTRAL | 611 CENTRAL AV | 161 | MAY | 2023-05-12 | U125208 | U133234 | 2023-04-17 | 2023-04-26 | 2023-05-12 |  | ABHATFIE | 2023-05-03 | 2023-05-02 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 12.35 | 3 | 890.96 | 824.08 | 20.27 | 46.61 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23183654600 |  | 100404268 |  | 7256280M | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | WALLER | 1217 WALLER ST | 161 | MAY | 2023-05-03 | U126286 | U125763 | 2023-04-25 | 2023-12-29 |  |  | TYLER ALLISON | 2023-05-03 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2247.16 | 61.56 | 0 | 3.47 | 2182.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23185667200 |  | 100295562 |  | 6716216L |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | REDWOOD | 1054 REDWOOD DR | 067 | LEX | 2023-05-03 | MCRAIG | U130871 | 2023-05-03 | 2023-05-03 |  |  | MCRAIG | 2023-05-03 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.6333 | 2 | 1525.04 | 803.86 | 296.48 | 324.6 | 100.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23185679300 |  | 100323042 |  | 6716208L |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | OLD DOBBIN | 808 OLD DOBBIN RD | 067 | LEX | 2023-05-03 | MSHARON | U129939 | 2023-05-03 | 2023-05-01 | 2023-05-01 |  | MSHARON | 2023-05-03 | 2023-05-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 26.35 | 4 | 9495.47 | 1893.93 | 7399.65 | 107.29 | 94.6 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23185753600 |  | 100247450 |  | 7352256L |  |  |  | 566 | EX | REPLACE SERVICE LINE | 2621P | MCGURK | 2500 MCGURK ST A1 | 019 | ASH | 2023-05-04 | U124015 | U129939 | 2023-05-03 | 2023-05-03 |  |  | ORA SLONE | 2023-05-03 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1
KY | KY - EAST | 2631 | 21960865700 |  | 100249924 |  | 7348260H | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | SUNSET | 8220 SUNSET RD | 019 | CAT | 2023-05-05 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH DEREK CRAGER | 2023-05-04 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3710.71 | 0 | 0 | 0 | 3710.71 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026228400 |  |  |  | 6748208I | 2292377 | U128885 |  | 558 | EX | RETIRE 1133'- MP MAIN | 2600E | MAPLE | N MAPLE ST | 049 | WIN | 2023-06-15 | U128132 | U128885 | 2022-09-29 | 2023-12-29 | 2023-12-31 | 2023-05-04 | SHAWN DENNIS | 2023-05-04 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP2284 | AMRCB |  | 100 | 055832220262284 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026243900 |  |  |  | 6720204O | 2294088 | U461383 |  | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2621M | KENNESAW | KENNESAW DR | 067 | LEX | 2023-07-17 | U123258 | U461383 | 2022-12-15 | 2023-11-30 | 2023-12-01 | 2023-05-04 | SHAWN MCHOLAN | 2023-05-04 | 2023-03-23 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP2439 |  |  | 100 | 090932220262439 | 31.0167 | 0 | 13592.24 | 1977.26 | 0 | 446.86 | 11069.46 | 0 | 98.66 | 0
KY | KY - WEST | 2621 | 22026244000 |  |  |  | 6720204O | 2294088 | U461383 |  | 910 | EX | RETIRE ELECTRONICS | 2621M | KENNESAW | KENNESAW DR | 067 | LEX | 2023-05-15 | U123258 | U461383 | 2022-12-15 | 2023-12-01 | 2023-12-01 | 2023-05-04 | SMCHOLAN | 2023-05-04 | 2023-03-28 |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00910 | 3200910 |  |  | WP2440 |  |  | 100 | 091032220262440 | 1.0167 | 0 | 65.38 | 61.41 | 0 | 3.97 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22103800800 |  | 100310790 |  | 6712204C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | LANNETTE | 3421 LANNETTE LN | 067 | LEX | 2023-05-04 | KOBRYAN | AOC SYST | 2022-05-26 | 2022-11-23 | 2023-12-31 |  | KOBRYAN | 2023-05-04 | 2023-05-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.6 | 5 | 910.56 | 784.8 | 0 | 44.36 | 81.4 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129007900 |  | 100354980 |  | 7260280M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 3RD | 707 E 3RD ST | 161 | MAY | 2023-05-12 | U125208 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ABHATFIE | 2023-05-04 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 5.4333 | 2 | 400.46 | 359.85 | 20.27 | 20.34 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129008300 |  | 100356429 |  | 7256276J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAPLE LEAF | 401 E MAPLE LEAF RD | 161 | MAY | 2023-05-12 | U125208 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ABHATFIE | 2023-05-04 | 2023-04-24 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 11.45 | 3 | 946.72 | 754.66 | 149.53 | 42.53 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129028000 |  | 100262466 |  | 7352256G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CHINN | 2601 CHINN ST | 019 | ASH | 2023-05-04 | U124015 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ORA SLONE | 2023-05-04 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 2066.45 | 0 | 0 | 0 | 2066.45 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129032400 |  | 100261410 |  | 7352256L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WOODLAWN | 3116 WOODLAWN AV | 019 | ASH | 2023-05-04 | U124015 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ORA SLONE | 2023-05-04 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1194.17 | 0 | 0 | 0 | 1194.17 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22992019400 |  | 100246100 |  | 7320284L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D258065 | 2600B | STATE RT 8 | 2745 STATE RT 8 | 089 | S P | 2023-05-04 | U125566 | U131172 | 2022-04-07 | 2022-10-06 | 2024-04-30 |  | DESKAGG | 2023-05-04 | 2023-04-27 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 47.7667 | 6 | 21576.56 | 3222.77 | 270.56 | 658.81 | 17424.42 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156277900 |  | 100439851 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | WADSWORTH | 1216 WADSWORTH ST | 161 | MAY | 2023-05-04 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-05-04 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2728.55 | 34.09 | 0 | 1.94 | 2692.52 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164747300 |  | 100281579 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | CHESTNUT | 514 CHESTNUT ST | 209 | GEO | 2023-05-04 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-05-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2799.33 | 0 | 0 | 0 | 2799.33 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164760300 |  | 100281550 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 312 PAYNE AV | 209 | GEO | 2023-05-04 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-05-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2039.88 | 0 | 0 | 0 | 2039.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165280600 |  | 100336894 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | JOHNSON | 424 JOHNSON AV 1F | 067 | LEX | 2023-05-04 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-05-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2930.16 | 0 | 0 | 0 | 2930.16 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166692400 |  | 100272404 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | SHELBY | 812 SHELBY ST | 073 | FRA | 2023-05-05 | U126284 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JOSH PASLEY/MILLER PIPELINE | 2023-05-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 1 | 4447.81 | 523.86 | 0 | 463.6 | 3460.35 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166692600 |  | 100272402 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | SHELBY | 816 SHELBY ST | 073 | FRA | 2023-05-05 | U126284 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JOSH PASLEY/MILLER PIPELINE | 2023-05-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3398.87 | 0 | 0 | 0 | 3398.87 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168512300 |  | 100342580 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 412 HOLT AV | 173 | MT | 2023-05-05 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-04 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2562.16 | 0 | 0 | 0 | 2562.16 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168512400 |  | 100342553 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 413 HOLT AV | 173 | MT | 2023-05-05 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-04 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2865.24 | 0 | 0 | 0 | 2865.24 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23168991900 |  | 100403698 |  | 7348264B | 2394978 |  |  | 565 | EX | NBT-UPG SL 70' 2"PMLP MTR RELO | 2621P | CENTRAL | 800 CENTRAL AV | 089 | WOR | 2023-05-05 | U132743 | U125208 | 2023-02-23 | 2023-02-23 | 2023-03-23 |  | BMEEK | 2023-05-04 | 2023-03-14 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 29.0833 | 7 | 2686.61 | 1800.53 | 330.85 | 437.53 | 117.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176278500 |  | 100331296 |  | 6720212N | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMED D333584 | 2621D | OWSLEY | 134 OWSLEY AV | 067 | LEX | 2023-05-10 | U130722 | AOC SYST | 2023-03-24 | 2023-09-22 | 2025-03-31 |  | LSTANFI | 2023-05-04 | 2023-04-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.25 | 4 | 1236.57 | 1024.9 | 0 | 172.07 | 39.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176930300 |  | 100456107 |  | 6716208J | 2394661 |  |  | 565 | EX | RPLC SL/23026246400 | 2600B | BURT | 177 BURT RD | 067 | LEX | 2023-05-04 | U126604 | U125763 | 2023-03-29 | 2023-12-29 |  |  | WILL FULKS | 2023-05-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3489.7 | 0 | 0 | 0 | 3489.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23182703400 |  | 100330263 |  | 6720212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332801 | 2621P | QUEENSWAY | 433 QUEENSWAY DR | 067 | LEX | 2023-05-05 | U132743 | U125208 | 2023-04-20 | 2023-04-21 | 2023-05-10 |  | HMCKUNE | 2023-05-04 | 2023-04-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.8667 | 3 | 5390.54 | 916.75 | 306.59 | 51.66 | 4115.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23185733600 |  | 100328917 |  | 6720208P | 1635077 |  |  | 565 | EX | GRD 1 ON SERVICE | 2621P | MOUNT TABOR | 493 MOUNT TABOR RD | 067 | LEX | 2023-05-04 | U930915 | U130871 | 2023-05-03 | 2023-05-03 | 2023-05-03 |  | TROE | 2023-05-04 | 2023-05-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.1 | 4 | 1141.69 | 756.61 | 273.02 | 42.76 | 69.3 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23185745800 |  | 100441251 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | CHESTNUT | 514< CHESTNUT ST | 209 | GEO | 2023-05-04 | U461443 | U125763 | 2023-05-03 | 2023-12-29 |  |  | WGRAVES | 2023-05-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2614.19 | 0 | 0 | 0 | 2614.19 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23185755300 |  | 100254961 |  | 7348260B |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MELVIN | 2704 MELVIN ST | 089 | FLA | 2023-05-04 | U132743 | U130871 | 2023-05-03 | 2023-05-03 | 2023-05-03 |  | LAMAY | 2023-05-04 | 2023-05-03 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 7.3833 | 3 | 1057.85 | 559.06 | 0 | 401.99 | 96.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 04585723100 |  | 100324062 |  | 600000000 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DEER HAVEN | 1259 DEER HAVEN LN | 067 | LEX | 2023-05-05 | HMCKUNE | SSUTHER | 2004-09-02 | 2014-12-01 |  |  | HMCKUNE | 2023-05-05 | 2023-04-06 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.65 | 5 | 879 | 832.39 | 0 | 46.61 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960866400 |  | 100249925 |  | 7360248E | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | US ROUTE 23 | 10138 US ROUTE 23 | 019 | CAT | 2023-05-05 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH DEREK CRAGER | 2023-05-05 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2650.4 | 0 | 0 | 0 | 2650.4 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129029600 |  | 100264504 |  | 7356260M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MONTGOMERY | 852 MONTGOMERY AV | 019 | ASH | 2023-05-05 | U124015 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ORA SLONE | 2023-05-05 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 882.65 | 0 | 0 | 0 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129030600 |  | 100246828 |  | 7352256L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 29TH | 3200 S 29TH ST | 019 | ASH | 2023-05-05 | U124015 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ORA SLONE | 2023-05-05 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 882.65 | 0 | 0 | 0 | 882.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22137263300 |  | 100319017 |  | 6716208O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | HEATHER | 2459 HEATHER WY | 067 | LEX | 2023-05-10 | U130722 | AOC SYST | 2022-10-06 | 2023-04-06 | 2023-12-31 |  | DMARSTO | 2023-05-05 | 2023-04-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 19.6 | 6 | 2197.19 | 1199.85 | 0 | 67.84 | 929.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026251500 |  | 501341045 |  | 6700224O | 2394919 | U126783 |  | 555 | EX | INSTALL 70'-2" PMLP | 2600B | BRUEN | 244 W BRUEN ST | 239 | MID | 2023-06-28 | U128132 | U126783 | 2023-01-17 | 2023-05-03 | 2023-05-08 | 2023-05-05 | ED FOX | 2023-05-05 | 2023-05-01 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2515 |  |  | 100 | 055532230262515 | 36.9 | 610 | 16349.3 | 2344.26 | 902.05 | 598.46 | 10158.04 | 0 | 36.12 | 2310.37 | 122
KY | KY - CENTRAL | 2632 | 23156272900 |  | 100356380 |  | 7256276B | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | HENRY | 1280 HENRY LN | 161 | MAY | 2023-05-08 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-05-05 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2493.76 | 0 | 0 | 0 | 2493.76 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164746300 |  | 100433393 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | CHESTNUT | 502 CHESTNUT ST | 209 | GEO | 2023-05-05 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-05-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2544.24 | 0 | 0 | 0 | 2544.24 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164747600 |  | 100281571 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | CHESTNUT | 517 CHESTNUT ST | 209 | GEO | 2023-05-05 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-05-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2764.1 | 0 | 0 | 0 | 2764.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164747800 |  | 100281575 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | CHESTNUT | 520 CHESTNUT ST | 209 | GEO | 2023-05-05 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-05-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2609.33 | 0 | 0 | 0 | 2609.33 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166692200 |  | 100272407 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | SHELBY | 808 SHELBY ST | 073 | FRA | 2023-05-05 | U126284 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JOSH PASLEY/MILLER PIPELINE | 2023-05-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3072.16 | 0 | 0 | 0 | 3072.16 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166692700 |  | 100272401 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | SHELBY | 818 SHELBY ST | 073 | FRA | 2023-05-05 | U126284 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JOSH PASLEY/MILLER PIPELINE | 2023-05-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2570.38 | 0 | 0 | 0 | 2570.38 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166724700 |  | 100275068 |  | 6684228J | 1855043 |  |  | 566 | EX | ABANDON SL - SOII/INSIDE | 2621P | SAINT CLAIR | 236 SAINT CLAIR ST 1F | 073 | FRA | 2023-05-05 | JMARSHA | U130868 | 2023-02-14 | 2023-05-23 | 2023-05-23 |  | JMARSHA | 2023-05-05 | 2023-05-01 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 3.4 | 4 | 718.45 | 175.99 | 0 | 9.96 | 532.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168512200 |  | 100342552 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 411 HOLT AV | 173 | MT | 2023-05-08 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-05 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4129.3 | 0 | 0 | 0 | 4129.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23171960800 |  | 100328372 |  | 6720208F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309453 | 2621P | CULPEPPER | 536 CULPEPPER RD | 067 | LEX | 2023-05-08 | U930915 | U125208 | 2023-03-06 | 2023-09-06 | 2025-03-31 |  | WISHII | 2023-05-05 | 2023-04-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.2333 | 6 | 2120.25 | 1379.56 | 134.89 | 542 | 63.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23183581300 |  | 100271925 |  | 6684228K |  |  |  | 565 | EX | RPLC SL/ | 2600B | 3RD | 107 E 3RD ST | 073 | FRA | 2023-05-10 | U461423 | U125763 | 2023-04-25 | 2023-12-29 |  |  | KKOUNS | 2023-05-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 1.5667 | 1 | 3712.88 | 96.13 | 0 | 5.44 | 3611.31 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23183655000 |  | 100421858 |  | 7256280M | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | WALLER | 1220 WALLER ST | 161 | MAY | 2023-05-05 | U126286 | U125763 | 2023-04-25 | 2023-12-29 |  |  | TYLER ALLISON | 2023-05-05 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 3589.6 | 30.49 | 0 | 1.73 | 3557.38 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23185759400 |  | 100344540 |  | 6700224O | 2394919 |  |  | 565 | EX | RPLC SL/23026251500 | 2600B | BRUEN | 238 W BRUEN ST | 239 | MID | 2023-05-09 | U127414 | U125763 | 2023-05-03 | 2023-12-29 |  |  | ED FOX | 2023-05-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 |  | 1 | 1760.74 | 0 | 0 | 0 | 1760.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23186027700 |  | 100412963 |  | 6724208E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333559 | 2621P | HEDGEWOOD | 289 HEDGEWOOD CT | 067 | LEX | 2023-05-05 | TROE | U125208 | 2023-05-04 | 2023-05-05 | 2023-05-24 |  | TROE | 2023-05-05 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.7333 | 2 | 454.03 | 294.35 | 113.33 | 16.65 | 29.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23186028800 |  | 100414871 |  | 6720208H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333557 | 2621P | HEDGEWOOD | 249 HEDGEWOOD CT | 067 | LEX | 2023-05-05 | TROE | U125208 | 2023-05-04 | 2023-05-05 | 2023-05-24 |  | TROE | 2023-05-05 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.2667 | 2 | 872.44 | 707.73 | 106.01 | 40 | 18.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23186385600 |  | 100431409 |  | 7320284H |  |  |  | 565 | EX | RPLC SL/CONTRACTOR | 2600B | STATE RT 8 | 2679 STATE RT 8 | 089 | S P | 2023-05-05 | DESKAGG | U125763 | 2023-05-05 | 2023-12-29 |  |  | DESKAGG | 2023-05-05 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 | 9 | 1 | 4135.96 | 613.18 | 310.75 | 148.3 | 3063.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23186402800 |  | 100408090 |  | 6720208D |  |  |  | 565 | EX | GRD 1 | 2621P | CODELL | 512 CODELL DR | 067 | LEX | 2023-05-08 | UIPBOT18 | U130871 | 2023-05-05 | 2023-05-05 | 2023-05-05 |  | JOCHOA | 2023-05-05 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.95 | 2 | 1191.76 | 649.2 | 426.63 | 36.73 | 79.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23186405900 |  | 100336906 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | 5TH | 148 E 5TH ST | 067 | LEX | 2023-05-05 | U126532 | U125763 | 2023-05-05 | 2023-12-29 |  |  | LESLIE SHARON | 2023-05-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3701.72 | 0 | 0 | 0 | 3701.72 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23186406500 |  | 100351937 |  | 6744208J |  |  |  | 565 | EX | GRD 1 | 2621P | LEXINGTON | 1202 W LEXINGTON AV | 049 | WIN | 2023-05-05 | NRICHIE | U130871 | 2023-05-05 | 2023-05-05 | 2023-05-05 |  | NRICHIE | 2023-05-05 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 24.5333 | 4 | 5135.79 | 1600.64 | 361.38 | 523.38 | 2650.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23186450100 |  | 100411433 |  | 6720208D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CODELL | 518 CODELL DR | 067 | LEX | 2023-05-08 | U132743 | U130871 | 2023-05-05 | 2023-05-04 | 2023-05-04 |  | LSTANFI | 2023-05-05 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 9.1333 | 2 | 1294.67 | 1041.9 | 0 | 75.67 | 177.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11920341000 |  | 100335702 |  | 6720212H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | NEW CIRCLE | 649 E NEW CIRCLE RD | 067 | LEX | 2023-05-08 | JOCHOA | U124449 | 2011-08-16 | 2022-07-01 | 2023-12-31 |  | JOCHOA | 2023-05-08 | 2022-10-07 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.6167 | 4 | 2895.51 | 841.87 | 0 | 86.06 | 1967.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21938173100 |  | 100301483 |  | 6712212H | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | RUGBY | 143 RUGBY RD | 067 | LEX | 2023-05-08 | WISHII | AOC SYST | 2021-09-07 | 2022-03-07 | 2022-12-31 |  | WISHII | 2023-05-08 | 2023-03-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 26.4667 | 7 | 2200.58 | 1499.66 | 211.86 | 382.36 | 106.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129008200 |  | 100356082 |  | 7260280M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FOREST | 824 FOREST AV | 161 | MAY | 2023-05-08 | SDADAMS | U130722 | 2022-09-05 | 2022-12-30 |  |  | SDADAMS | 2023-05-08 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 1.45 | 1 | 97.26 | 92.05 | 0 | 5.21 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156268700 |  | 100356376 |  | 7256280M | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | BROOKINGS | 548 BROOKINGS AV | 161 | MAY | 2023-05-08 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-05-08 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2361.84 | 0 | 0 | 0 | 2361.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164747700 |  | 100281572 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | CHESTNUT | 519 CHESTNUT ST | 209 | GEO | 2023-05-08 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-05-08 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.033333 | 1 | 2631.03 | 1.87 | 0 | 0.49 | 2628.67 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164753400 |  | 100281506 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | FORDLAND | 107 FORDLAND DR | 209 | GEO | 2023-05-09 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-05-08 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.7333 | 1 | 4181.16 | 108.75 | 0 | 28.24 | 4044.17 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166696400 |  | 100272304 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | TANGLEWOOD | 213 TANGLEWOOD DR | 073 | FRA | 2023-05-08 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-05-08 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 5313.29 | 0 | 0 | 0 | 5313.29 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168132800 |  | 100275020 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WAPPING | 411 WAPPING ST 1FE | 073 | FRA | 2023-05-08 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-05-08 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2263.58 | 0 | 0 | 0 | 2263.58 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168512000 |  | 100342550 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 407 HOLT AV | 173 | MT | 2023-05-09 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-08 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3029.32 | 0 | 0 | 0 | 3029.32 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168512100 |  | 100342581 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 410 HOLT AV | 173 | MT | 2023-05-09 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-08 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3178.73 | 0 | 0 | 0 | 3178.73 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23176211500 |  | 100413317 |  | 6744184F | 2397341 |  |  | 566 | EX | ABANDON SL - IDL/INA 100422577 | 2621P | UNION CITY | 2450 UNION CITY RD 2TR | 151 | RIC | 2023-05-08 | DENNING | U125208 | 2023-03-24 | 2023-12-21 | 2023-12-25 |  | DENNING | 2023-05-08 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2 | 2 | 194.6 | 131.28 | 0 | 63.32 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23176212200 |  | 100413318 |  | 6744184F | 2397341 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | UNION CITY | 2450 UNION CITY RD 5TR | 151 | RIC | 2023-05-08 | DENNING | U125208 | 2023-03-24 | 2023-12-21 | 2023-12-25 |  | DENNING | 2023-05-08 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.1 | 2 | 103.88 | 70.09 | 0 | 33.79 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23176212300 |  | 100417284 |  | 6744184F | 2397341 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | UNION CITY | 2450 UNION CITY RD 7TR | 151 | RIC | 2023-05-08 | DENNING | U125208 | 2023-03-24 | 2023-12-21 | 2023-12-25 |  | DENNING | 2023-05-08 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.6333 | 2 | 154.91 | 104.51 | 0 | 50.4 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23176212700 |  | 500570369 |  | 6744184F | 2397341 |  |  | 566 | EX | ABANDON SL - IDL/INA 500567650 | 2621P | UNION CITY | 2450 UNION CITY RD 9TL | 151 | RIC | 2023-05-08 | DENNING | U125208 | 2023-03-24 | 2023-12-21 | 2023-12-25 |  | DENNING | 2023-05-08 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.2 | 2 | 18.91 | 12.74 | 0 | 6.17 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23176212800 |  | 500567650 |  | 6744184F | 2397341 |  |  | 566 | EX | ABANDON SL - IDL/INA 500570369 | 2621P | UNION CITY | 2450 UNION CITY RD 8TL | 151 | RIC | 2023-05-08 | DENNING | U125208 | 2023-03-24 | 2023-12-21 | 2023-12-25 |  | DENNING | 2023-05-08 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.0333 | 2 | 188.91 | 127.45 | 0 | 61.46 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176932000 |  | 100317083 |  | 6716208J | 2394661 |  |  | 565 | EX | RPLC SL/23026246400 | 2600B | BURT | 138 BURT RD | 067 | LEX | 2023-05-09 | U126604 | U125763 | 2023-03-29 | 2023-12-29 |  |  | WILL FULKS | 2023-05-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 10088.56 | 0 | 0 | 0 | 10088.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23183654700 |  | 100356368 |  | 7256280M | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | WALLER | 1218 WALLER ST | 161 | MAY | 2023-05-08 | U126286 | U125763 | 2023-04-25 | 2023-12-29 |  |  | TYLER ALLISON | 2023-05-08 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2415.91 | 39 | 0 | 2.23 | 2374.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23186406200 |  | 100336905 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | 5TH | 144 E 5TH ST | 067 | LEX | 2023-05-08 | U126532 | U125763 | 2023-05-05 | 2023-12-29 |  |  | LESLIE SHARON | 2023-05-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3740.99 | 0 | 0 | 0 | 3740.99 | 0 | 0 | 0
KY | KY - EAST | 2633 | 03553389700 |  | 100264675 | 07 | 7384168F |  |  |  | 566 | EX | ABANDON/ IDLE PRIOR 02-25-2008 | 2621P | TURKEY CREEK | 938 TURKEY CREEK RD | 195 | S W | 2023-05-09 | JAHOWARD | LDAVIS | 2003-10-07 | 2049-12-31 |  |  | JAHOWARD | 2023-05-09 | 2023-05-02 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 16.3333 | 3 | 3303.03 | 1037.77 | 0 | 58.66 | 2206.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21026149800 |  |  |  | 6748208I | 2292377 | U128885 |  | 584 | EX | RETIRE R-1615 | 2629M | ALLEY OFF MAIN | ALLEY OFF MAIN ST | 049 | WIN | 2023-07-17 | U123258 | U128885 | 2021-11-08 | 2023-12-21 | 2023-12-31 | 2023-05-09 | JAMES PASLEY | 2023-05-09 |  |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00584 | 3200584 |  |  | WP1498 | AMRCB |  | 100 | 058432210261498 | 8 | 0 | 552.62 | 523.06 | 0 | 29.56 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960860200 |  | 100249898 |  | 7356248H | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | NEAL | 7941 NEAL RD | 019 | CAT | 2023-05-10 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH DEREK CRAGER | 2023-05-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3186.06 | 0 | 0 | 0 | 3186.06 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129007800 |  | 100353306 |  | 7256280K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 2ND | 348 W 2ND ST DN | 161 | MAY | 2023-05-10 | U930915 | U130722 | 2022-09-05 | 2022-12-30 |  |  | SDADAMS | 2023-05-09 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 10.4 | 2 | 2596.66 | 653.65 | 36.94 | 36.95 | 1869.12 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129013500 |  | 100256698 |  | 7356252O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GREENUP | 951 GREENUP AV | 089 | RAC | 2023-05-09 | U124015 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ORA SLONE | 2023-05-09 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1902.65 | 0 | 0 | 0 | 1902.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129036100 |  | 100254575 |  | 7348264O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | POWELL | 1012 POWELL LN | 089 | FLA | 2023-05-09 | U124015 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ORA SLONE | 2023-05-09 | 2022-11-01 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 23.8333 | 3 | 6459.97 | 1522.05 | 0 | 87.67 | 4850.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129046800 |  | 500617456 |  | 6716212D | 9828747 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GEORGETOWN | 498< GEORGETOWN ST | 067 | LEX | 2023-05-09 | MCRAIG | U130722 | 2022-09-05 | 2022-12-30 |  |  | MCRAIG | 2023-05-09 | 2023-03-31 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.4167 | 6 | 2117.94 | 730.63 | 170.19 | 251.05 | 966.07 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026271400 |  |  |  | 7352256P | 2396809 | U122858 |  | 557 | EX | EMER - INSTALL ~5'-2" PMMP | 2621P | 29TH | 3624 29TH ST | 019 | ASH | 2023-05-18 | U128132 | U122858 | 2023-04-11 | 2023-12-29 | 2023-12-31 | 2023-04-10 | MCOLLET | 2023-05-09 | 2023-05-08 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP2714 |  |  | 100 | 055732230262714 | 9.2667 | 3 | 7739.82 | 2504.24 | 333.2 | 2034.88 | 1635.48 | 0 | 14.02 | 1218 | 1
KY | KY - EAST | 2631 | 23026271500 |  |  |  | 7352256P | 2396809 | U122858 |  | 558 | EX | EMER - RETIRE ~5'-2" PMMP | 2621P | 29TH | 3624 29TH ST | 019 | ASH | 2023-05-16 | U128132 | U122858 | 2023-04-11 | 2023-12-29 | 2023-12-31 | 2023-04-10 | MCOLLET | 2023-05-09 | 2023-04-14 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP2715 |  |  | 100 | 055832230262715 | 3.75 | 0 | 709.93 | 265.94 | 0 | 443.99 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026272600 |  | 501347012 |  | 6708204K | 2397152 | U461383 |  | 555 | EX | INSTALL 875' OF 2"PMMP MAIN | 2600B | HOMESTRETCH | HOMESTRETCH CR LT26 | 113 | NIC | 2023-05-19 | U128132 | U461383 | 2023-04-25 | 2023-08-14 | 2023-08-18 | 2023-05-09 | R.HUMPHREYS | 2023-05-09 | 2023-05-03 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2726 |  |  | 100 | 055532230262726 | 40 | 3695 | 29299.51 | 2520.9 | 1898.69 | 647.55 | 20033.3 | 0 | 62.52 | 4136.55 | 739
KY | KY - CENTRAL | 2632 | 23156268800 |  | 100356375 |  | 7256280M | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | BROOKINGS | 600 BROOKINGS AV | 161 | MAY | 2023-05-09 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-05-09 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2490.03 | 0 | 0 | 0 | 2490.03 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164754900 |  | 100281628 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | GANO | 403 GANO AV | 209 | GEO | 2023-05-09 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-05-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.95 | 1 | 2216.47 | 184.55 | 0 | 47.93 | 1983.99 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168133100 |  | 100275034 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WAPPING | 501 WAPPING ST | 073 | FRA | 2023-05-09 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-05-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3797.54 | 0 | 0 | 0 | 3797.54 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168134800 |  | 100275028 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WILKINSON | 100 WILKINSON ST | 073 | FRA | 2023-05-09 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-05-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2643.15 | 0 | 0 | 0 | 2643.15 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168511800 |  | 100342548 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 405 HOLT AV | 173 | MT | 2023-05-10 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-09 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2787.96 | 0 | 0 | 0 | 2787.96 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168511900 |  | 100342583 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 406 HOLT AV | 173 | MT | 2023-05-11 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-09 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4140.12 | 0 | 0 | 0 | 4140.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23175610900 |  | 100331478 |  | 6720212N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333577 | 2621P | VICTORY | 101 VICTORY AV | 067 | LEX | 2023-05-09 | U930915 | U125208 | 2023-03-22 | 2023-09-21 | 2025-03-31 |  | HMCKUNE | 2023-05-09 | 2023-05-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.2 | 7 | 1971.33 | 1208.36 | 221.06 | 502.31 | 39.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23176211800 |  | 100422577 |  | 6744184F | 2397341 |  |  | 566 | EX | ABANDON SL - IDL/INA 100413317 | 2621P | UNION CITY | 2450 UNION CITY RD 1TR | 151 | RIC | 2023-05-09 | DENNING | U125208 | 2023-03-24 | 2023-12-21 | 2023-12-25 |  | DENNING | 2023-05-09 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10.4667 | 2 | 701.54 | 663.99 | 0 | 37.55 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176930800 |  | 100444265 |  | 6716208J | 2394661 |  |  | 565 | EX | RPLC SL/23026246400 | 2600B | NICHOLASVILLE | 2263 NICHOLASVILLE RD 1FL | 067 | LEX | 2023-05-09 | U126604 | U125763 | 2023-03-29 | 2023-12-29 |  |  | WILL FULKS | 2023-05-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 5750.84 | 0 | 0 | 0 | 5750.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23181017000 |  | 100293880 |  | 6720212A |  |  |  | 565 | EX | LEAK REPAIR - S.L. - D310457 | 2621P | KEES | 1101 KEES RD | 067 | LEX | 2023-05-17 | U125208 | U125208 | 2023-04-13 | 2023-10-12 | 2025-04-30 |  | ATWILLI | 2023-05-09 | 2023-04-27 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.4 | 1 | 206.37 | 75.23 | 0 | 51.94 | 79.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23182855000 |  | 100317488 |  | 6716204J | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER | 2621D | TANGLEY | 267 TANGLEY WY | 067 | LEX | 2023-05-09 | JOCHOA | AOC SYST | 2023-04-20 | 2023-05-19 | 2023-06-18 |  | JOCHOA | 2023-05-09 | 2023-04-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.15 | 7 | 1617.89 | 1230.66 | 217.11 | 68.92 | 101.2 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23184094400 |  | 100258496 |  | 7344264C |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | CHINN | 405 CHINN ST | 089 | WUR | 2023-05-09 | RECUMP | U132002 | 2023-04-27 | 2023-05-10 | 2023-05-26 |  | RECUMP | 2023-05-09 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 7.15 | 3 | 793.44 | 677.74 | 0 | 115.7 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23186440900 |  | 500718719 |  | 6724208I | 9825379 |  |  | 566 | EX | PAPER ABN / INVESTIGATE | 2621P | PINEWOOD | 391 PINEWOOD CT | 067 | LEX | 2023-05-09 | HMCKUNE | U125208 | 2023-05-05 | 2023-06-05 | 2023-06-05 |  | HMCKUNE | 2023-05-09 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.55 | 1 | 172.18 | 162.97 | 0 | 9.21 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23186981900 |  | 100241888 |  | 7344168G |  | U125763 |  | 565 | EX | RPLC SL/CONTRACTOR | 2600B | LAKE | 2352 S LAKE DR | 071 | LNC | 2023-05-09 | U125566 | U125763 | 2023-05-09 | 2021-12-30 | 2023-06-30 |  | DAVID SKAGGS | 2023-05-09 |  |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26330022 | 2.8167 | 1 | 6509.66 | 476.85 | 1851.66 | 272.14 | 3909.01 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23186982200 |  | 100241889 |  | 7344168G |  |  |  | 565 | EX | RPLC SL/CONTRACTOR | 2600B | LAKE | 2378 S LAKE DR | 071 | LNC | 2023-05-09 | DESKAGG | U125763 | 2023-05-09 | 2023-12-29 |  |  | DESKAGG | 2023-05-09 |  |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26330032 | 6.35 | 1 | 3812.07 | 432.64 | 319.92 | 104.63 | 2954.88 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23186985800 |  | 100260139 |  | 7356256A |  |  |  | 566 | EX | ABANDON SL | 2621P | ASHLAND | 924 ASHLAND AV | 019 | ASH | 2023-05-09 | RECUMP | U134021 | 2023-05-09 | 2023-05-09 |  |  | RECUMP | 2023-05-09 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 15 | 3 | 2910.02 | 1247.77 | 0 | 260.41 | 1401.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23187014100 |  | 100353307 |  | 7256280K |  |  |  | 566 | EX | ABN SVC LINE | 2621P | 2ND | 348 W 2ND ST UP | 161 | MAY | 2023-05-10 | U930915 | U131552 | 2023-05-09 | 2023-05-09 |  |  | SDADAMS | 2023-05-09 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 0.8 | 2 | 53.38 | 50.52 | 0 | 2.86 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23187020800 |  | 500371853 |  | 6724208G | 9403236 |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | WEYMOUTH | 3113 WEYMOUTH CT | 067 | LEX | 2023-05-09 | LSTONE | U131552 | 2023-05-09 | 2023-09-27 | 2025-03-31 |  | LSTONE | 2023-05-09 | 2023-05-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 10.1667 | 3 | 1234.64 | 900.31 | 212 | 50.83 | 71.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960885400 |  | 100249899 |  | 7356248H | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | NEAL | 7937 NEAL RD | 019 | CAT | 2023-05-10 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH DEREK CRAGER | 2023-05-10 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1843.18 | 0 | 0 | 0 | 1843.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22124328800 |  | 100318663 |  | 6716204F | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | LOCH LOMOND | 216 LOCH LOMOND DR | 067 | LEX | 2023-05-11 | U130722 | AOC SYST | 2022-08-16 | 2023-02-16 | 2023-12-31 |  | LSTONE | 2023-05-10 | 2023-04-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 25.45 | 8 | 1708.06 | 1553.87 | 0 | 87.09 | 67.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129007700 |  | 100353278 |  | 7256280G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 2ND | 520 W 2ND ST | 161 | MAY | 2023-05-10 | SDADAMS | U130722 | 2022-09-05 | 2022-12-30 |  |  | SDADAMS | 2023-05-10 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 9.9667 | 2 | 679.73 | 627.14 | 17.13 | 35.46 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129013000 |  | 100458263 |  | 7340268J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ASHLAND | 2023 ASHLAND RD | 089 | GRE | 2023-05-15 | U124015 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ORA SLONE | 2023-05-10 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 882.65 | 0 | 0 | 0 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129036600 |  | 100251589 |  | 7336276N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CHURCH | 103 CHURCH ST | 089 | GRE | 2023-05-10 | U124015 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ORA SLONE | 2023-05-10 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 882.65 | 0 | 0 | 0 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129037200 |  | 100251584 |  | 7352252C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SLASH BRANCH | 313 SLASH BRANCH RD | 089 | GRE | 2023-05-10 | U124015 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ORA SLONE | 2023-05-10 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 882.65 | 0 | 0 | 0 | 882.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129079800 |  | 501287786 |  | 6724212E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ANNISTON DR A8 | 1474 ANNISTON DR A8 | 067 | LEX | 2023-05-10 | ATWILLI | U130722 | 2022-09-05 | 2022-12-30 |  |  | ATWILLI | 2023-05-10 | 2023-04-10 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 22.1833 | 12 | 1921.18 | 1377.58 | 15.02 | 528.58 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166693400 |  | 100272389 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | SHELBY | 838 SHELBY ST | 073 | FRA | 2023-05-10 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-05-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1569.69 | 0 | 0 | 0 | 1569.69 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176930700 |  | 500007885 |  | 6716208J | 2394661 |  |  | 565 | EX | RPLC SL/23026246400 | 2600B | NICHOLASVILLE | 2225< NICHOLASVILLE RD 1F | 067 | LEX | 2023-05-10 | U126604 | U125763 | 2023-03-29 | 2023-12-29 |  |  | WILL FULKS | 2023-05-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3501.19 | 0 | 0 | 0 | 3501.19 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23177275100 |  | 100331566 |  | 6720212N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333590 | 2621P | RICHMOND | 310 RICHMOND AV | 067 | LEX | 2023-05-10 | U930915 | U125208 | 2023-03-30 | 2023-09-29 | 2025-03-31 |  | HMCKUNE | 2023-05-10 | 2023-05-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.9667 | 4 | 782.08 | 548.6 | 189.25 | 31.03 | 13.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23183654800 |  | 100356373 |  | 7256280M | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | WALLER | 1219 WALLER ST | 161 | MAY | 2023-05-10 | U126286 | U125763 | 2023-04-25 | 2023-12-29 |  |  | TYLER ALLISON | 2023-05-10 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2516.75 | 20.49 | 0 | 1.16 | 2495.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23185670700 |  | 501292977 |  | 670024L | 2072215 |  |  | 566 | EX | ABANDON SL-W/2313/23-0262662-0 | 2600B | GEORGETOWN | 1050 GEORGETOWN RD | 239 | MID | 2023-05-26 | U461383 | U125208 | 2023-05-03 | 2023-05-03 |  |  | BWHITE | 2023-05-10 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 15.4 | 2 | 4532.99 | 995.94 | 0 | 56.32 | 3480.73 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23187104600 |  | 100352644 |  | 6744204F |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HILLCREST | 63 HILLCREST DR | 049 | WIN | 2023-05-10 | SSHIMFE | U137585 | 2023-05-09 | 2023-05-09 | 2023-05-09 |  | SSHIMFE | 2023-05-10 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 11.8667 | 2 | 1220.8 | 609 | 527.87 | 34.43 | 49.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23187197400 |  | 100336907 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | 5TH | 152 E 5TH ST | 067 | LEX | 2023-05-11 | U126532 | U125763 | 2023-05-10 | 2023-12-29 |  |  | LESLIE SHARON | 2023-05-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 5337.43 | 66.16 | 0 | 3.78 | 5267.49 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23187202000 |  | 100279733 |  | 6688228K |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | ROBIN | 504 ROBIN AV | 073 | FRA | 2023-05-16 | U132743 | U131552 | 2023-05-10 | 2023-05-10 | 2023-05-10 |  | EFGOINS | 2023-05-10 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 18.2 | 3 | 1475.69 | 1036.22 | 0 | 394.37 | 45.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23187228500 |  | 100353279 |  | 7256280G |  |  |  | 566 | EX | ABN SVC LINE | 2621P | 2ND | 520 W 2ND ST UPS | 161 | MAY | 2023-05-10 | SDADAMS | U131552 | 2023-05-10 | 2023-05-10 |  |  | SDADAMS | 2023-05-10 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 3.5 | 2 | 233.33 | 220.84 | 0 | 12.49 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23187273500 |  | 100279834 |  | 6688228J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SUNSET | 124 SUNSET DR | 073 | FRA | 2023-05-16 | U132743 | U131552 | 2023-05-10 | 2023-05-10 | 2023-05-29 |  | EFGOINS | 2023-05-10 | 2023-05-10 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 | 1.8833 | 3 | 1161.36 | 787.22 | 0 | 312.54 | 61.6 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960884100 |  | 100249901 |  | 7356248H | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | NEAL | 7901 NEAL RD | 019 | CAT | 2023-05-15 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH DEREK CRAGER | 2023-05-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1940.91 | 0 | 0 | 0 | 1940.91 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22123021900 |  | 100317874 |  | 6716204G | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | YALE | 421 YALE DR | 067 | LEX | 2023-05-11 | TROE | AOC SYST | 2022-08-10 | 2023-02-10 | 2023-12-31 |  | TROE | 2023-05-11 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 13.6667 | 2 | 2518.36 | 731.65 | 1701.36 | 41.35 | 44 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23026274600 |  |  |  | 7352156L | 2397533 | U122858 |  | 559 | EX | EMER - INSTALL 5'-2" PMIP | 2600E | RAILROAD | 143 RAILROAD CR | 071 | JUS | 2023-07-03 | U128132 | U122858 | 2023-05-10 | 2023-05-26 | 2023-05-30 | 2023-05-11 | DAVID SKAGGS | 2023-05-11 |  |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00559 | 3200559 |  |  | WP2746 |  |  | 100 | 055932230262746 |  | 3 | 2867.86 | 245.46 | 405.24 | 13.9 | 1791.26 | 0 | 6.79 | 405.21 | 3
KY | KY - EAST | 2633 | 23026274700 |  |  |  | 7352156L | 2397533 | U122858 |  | 560 | EX | EMER - INSTALL 5'-2" PM | 2600E | RAILROAD | 143 RAILROAD CR | 071 | JUS | 2023-05-31 | U128132 | U122858 | 2023-05-10 | 2023-05-30 | 2023-05-30 | 2023-05-11 | DAVID SKAGGS | 2023-05-11 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00560 | 3200560 |  |  | WP2747 |  |  | 100 | 056032230262747 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156273800 |  | 100356369 |  | 7256276B | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | LEWIS | 1241 LEWIS ST | 161 | MAY | 2023-05-11 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-05-11 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 3034.17 | 0 | 0 | 0 | 3034.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166675000 |  | 100322695 |  | 6716208D |  |  |  | 565 | EX | NBT - SERV LN/REPLACE UPGRADE | 2621P | PROVIDENCE | 716 PROVIDENCE RD | 067 | LEX | 2023-05-16 | U132743 | U125763 | 2023-02-14 | 2023-04-20 | 2023-05-18 |  | DMARSTO | 2023-05-11 | 2023-05-04 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 35.0833 | 6 | 3467.69 | 2185.42 | 0 | 123.53 | 1158.74 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166693200 |  | 100272393 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | SHELBY | 830 SHELBY ST | 073 | FRA | 2023-05-15 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-05-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3080.28 | 0 | 0 | 0 | 3080.28 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168133400 |  | 100275048 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WAPPING | 510 WAPPING ST | 073 | FRA | 2023-05-11 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-05-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2635.86 | 0 | 0 | 0 | 2635.86 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168511400 |  | 100342546 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 401 HOLT AV | 173 | MT | 2023-05-17 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-11 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4394.51 | 0 | 0 | 0 | 4394.51 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168511500 |  | 100342586 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 402 HOLT AV | 173 | MT | 2023-05-17 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-11 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2526.54 | 0 | 0 | 0 | 2526.54 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168511600 |  | 100342547 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 403 HOLT AV | 173 | MT | 2023-05-17 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-11 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2652.17 | 0 | 0 | 0 | 2652.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23173441600 |  | 100434073 |  | 6716212H | 1635357 |  |  | 565 | EX | AOC INSTALL SLEEVE IN HARD SUR | 2621D | 5TH | 543 W 5TH ST | 067 | LEX | 2023-05-11 | MCRAIG | AOC SYST | 2023-03-13 | 2018-12-18 | 2019-12-31 |  | MCRAIG | 2023-05-11 | 2023-04-25 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 47.8667 | 10 | 3739.68 | 2471.16 | 733.72 | 468.8 | 66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23174570100 |  | 100422503 |  | 6724212I |  |  |  | 565 | EX | REPLACE SERVICE LINE - D310413 | 2621P | DALNA | 1808 DALNA DR | 067 | LEX | 2023-05-16 | U132743 | U125208 | 2023-03-17 | 2023-09-15 | 2025-03-31 |  | LSTANFI | 2023-05-11 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.95 | 2 | 860.38 | 628.21 | 0 | 111.17 | 121 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176930400 |  | 100319777 |  | 6716208J | 2394661 |  |  | 565 | EX | RPLC SL/23026246400 | 2600B | NICHOLASVILLE | 2197 NICHOLASVILLE RD | 067 | LEX | 2023-05-11 | U126604 | U125763 | 2023-03-29 | 2023-12-29 |  |  | WILL FULKS | 2023-05-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3225.1 | 0 | 0 | 0 | 3225.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176930600 |  | 500007317 |  | 6716208J | 2394661 |  |  | 565 | EX | RPLC SL/23026246400 | 2600B | NICHOLASVILLE | 2225 NICHOLASVILLE RD | 067 | LEX | 2023-05-12 | U126604 | U125763 | 2023-03-29 | 2023-12-29 |  |  | WILL FULKS | 2023-05-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 5690.71 | 0 | 0 | 0 | 5690.71 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23181134500 |  | 100245665 |  | 7360252I | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPL SL /MMO | 2631D | BROADWAY | 2410 BROADWAY ST | 019 | CAT | 2023-05-11 | BMEEK | AOC SYST | 2023-04-13 | 2023-05-12 | 2023-06-12 |  | BMEEK | 2023-05-11 | 2023-05-10 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 14.9667 | 3 | 1327.62 | 929.38 | 26.98 | 293.16 | 78.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23182101900 |  | 100298043 |  | 6716212L | 1855043 |  |  | 566 | EX | ABANDON SL - SOII/INSIDE | 2621P | LIMESTONE | 173 N LIMESTONE ST | 067 | LEX | 2023-05-15 | U125208 | U131897 | 2023-04-18 | 2023-07-06 | 2023-07-06 |  | RJCRAWF | 2023-05-11 | 2023-05-03 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 18.2833 | 8 | 2503.8 | 1506.91 | 21.92 | 85.22 | 889.75 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23186993400 |  | 100275035 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WAPPING | 503 WAPPING ST | 073 | FRA | 2023-05-11 | U461375 | U125763 | 2023-05-09 | 2023-12-29 |  |  | LARRY BROWN | 2023-05-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3160.21 | 0 | 0 | 0 | 3160.21 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23187130600 |  | 100352644 |  | 6744204F | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2629D | HILLCREST | 63 HILLCREST DR | 049 | WIN | 2023-05-16 | U132743 | AOC SYST | 2023-05-09 | 2024-12-31 | 2024-12-31 |  | SSHIMFE | 2023-05-11 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26290031 | 0.23333 | 1 | 14.9 | 14.1 | 0 | 0.8 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23187269500 |  | 100352592 |  | 6744204F |  |  |  | 565 | EX | GRADE 1 REPLACE S/L | 2621P | CHEROKEE | 105 CHEROKEE DR | 049 | WIN | 2023-05-12 | U930915 | U129939 | 2023-05-10 | 2023-05-10 | 2023-05-10 |  | NRICHIE | 2023-05-11 | 2023-05-11 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 17.05 | 3 | 2363.87 | 1109.68 | 665.56 | 529.23 | 59.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23187275300 |  | 100295531 |  | 6716216K |  |  |  | 565 | EX | REPLACE SERVICE LINE D311261 | 2621P | BRIARWOOD | 1149 BRIARWOOD DR | 067 | LEX | 2023-05-11 | JOCHOA | U131552 | 2023-05-10 | 2023-05-11 |  |  | JOCHOA | 2023-05-11 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.9833 | 2 | 1195.8 | 798.96 | 240.6 | 45.14 | 111.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960884200 |  | 100249903 |  | 7356248H | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | NEAL | 7923 NEAL RD | 019 | CAT | 2023-05-15 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH DEREK CRAGER | 2023-05-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2558.85 | 0 | 0 | 0 | 2558.85 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22103288900 |  | 100268806 |  | 7352156L | 2397533 |  |  | 565 | EX | REPLACE SERVICE LINE - D222360 | 2600B | RAILROAD | 143 RAILROAD ST | 071 | JUS | 2023-05-15 | U125566 | U125208 | 2022-05-24 | 2022-11-23 | 2024-05-31 |  | DESKAGG | 2023-05-12 | 2023-02-23 |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 50.3667 | 7 | 7380.59 | 3467.57 | 306.94 | 635.05 | 2971.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22124072800 |  | 100318681 |  | 6716204F | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE | 2621D | LOCH LOMOND | 123 LOCH LOMOND DR | 067 | LEX | 2023-05-12 | JOCHOA | AOC SYST | 2022-08-15 | 2023-02-15 | 2023-12-31 |  | JOCHOA | 2023-05-12 | 2023-04-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 35.2167 | 7 | 2930.63 | 2341.22 | 341.57 | 130.14 | 117.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129043300 |  | 100316181 |  | 6716208F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KOSTER | 223 KOSTER ST | 067 | LEX | 2023-05-12 | ATWILLI | U130722 | 2022-09-05 | 2022-10-05 |  |  | ATWILLI | 2023-05-12 | 2023-03-28 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 28.3833 | 12 | 1915.49 | 1756.05 | 15.02 | 144.42 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164765800 |  | 100281624 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | WALNUT | 528 WALNUT ST | 209 | GEO | 2023-05-12 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-05-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2217.76 | 0 | 0 | 0 | 2217.76 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23166978500 |  | 500742320 |  | 7352256A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | TANNER | 2623 TANNER DR | 019 | ASH | 2023-05-16 | U132743 | MDULANE | 2023-02-15 | 2023-06-16 | 2023-06-18 |  | BROBERT | 2023-05-12 | 2023-05-08 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 12.5833 | 5 | 1224.68 | 760.07 | 31.39 | 433.22 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168134400 |  | 100275002 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WATSON | 111 WATSON CT | 073 | FRA | 2023-05-12 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-05-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2334.05 | 0 | 0 | 0 | 2334.05 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168511700 |  | 100342585 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 404 HOLT AV | 173 | MT | 2023-05-15 | U126603 | U125763 | 2023-02-21 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-05-12 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4431.09 | 0 | 0 | 0 | 4431.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176930500 |  | 100317057 |  | 6716208J | 2394661 |  |  | 565 | EX | RPLC SL/23026246400 | 2600B | NICHOLASVILLE | 2217 NICHOLASVILLE RD | 067 | LEX | 2023-05-12 | U126604 | U125763 | 2023-03-29 | 2023-12-29 |  |  | WILL FULKS | 2023-05-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2879.13 | 0 | 0 | 0 | 2879.13 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23184057700 |  | 500534422 |  | 6688232N |  |  |  | 565 | EX | NBT - SERVICE LINE/MTR UPG 1"P | 2621P | JEANNETTE | 109 JEANNETTE AV | 073 | FRA | 2023-05-16 | U132743 | U125208 | 2023-04-27 | 2023-05-02 | 2023-05-05 |  | EFGOINS | 2023-05-12 | 2023-05-08 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26230031 | 36.0667 | 5 | 2839.31 | 2013.27 | 0 | 710.54 | 115.5 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22143454600 |  | 100266518 |  | 7360156M |  |  |  | 565 | EX | REPLACE SERVICE LINE - D243548 | 2600B | MULLINS | 87 MULLINS HL | 195 | PIK | 2023-05-15 | U125566 | U125208 | 2022-11-08 | 2023-04-28 | 2024-10-31 |  | DESKAGG | 2023-05-15 |  |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 11.25 | 1 | 3040.85 | 766.49 | 93.55 | 43.33 | 2137.48 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026274800 |  |  |  | 6748208I | 2292377 | U128885 |  | 586 | EX | RETIRE REG BUILDING | 2629M | ALLEY OFF MAIN | ALLEY OFF MAIN ST | 049 | WIN | 2023-05-15 | U123258 | U128885 | 2023-05-12 | 2023-05-31 | 2023-05-31 | 2023-05-09 | JAMES PASLEY | 2023-05-15 |  |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00586 | 3200586 |  |  | WP2748 | AMRCB |  | 100 | 058632230262748 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164766100 |  | 100281622 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | WALNUT | 530< WALNUT ST | 209 | GEO | 2023-05-15 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-05-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2596.55 | 0 | 0 | 0 | 2596.55 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165279400 |  | 100462999 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | 4TH | 112 W 4TH ST | 067 | LEX | 2023-05-15 | U126284 | U125763 | 2023-02-07 | 2023-12-29 |  |  | JOSH PASLEY/TEAM FISHEL | 2023-05-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 9966.17 | 523.86 | 0 | 463.6 | 8978.71 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166668000 |  | 100322633 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 656 BERRY LN | 067 | LEX | 2023-05-15 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-05-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1722.8 | 0 | 0 | 0 | 1722.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168136100 |  | 100430149 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WILKINSON | 302 WILKINSON ST | 073 | FRA | 2023-05-15 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-05-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3585.34 | 0 | 0 | 0 | 3585.34 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168511200 |  | 100342544 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 315 HOLT AV | 173 | MT | 2023-05-17 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-15 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3460.88 | 0 | 0 | 0 | 3460.88 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168518300 |  | 100342543 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 311 HOLT AV | 173 | MT | 2023-05-17 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-15 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 5028.36 | 0 | 173.53 | 0 | 4854.83 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23187185500 |  | 100352563 |  | 6744204F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094438 | 2621P | HILLCREST | 72 HILLCREST DR | 049 | WIN | 2023-05-15 | NRICHIE | U125208 | 2023-05-10 | 2023-05-12 | 2023-05-30 |  | NRICHIE | 2023-05-15 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 12.9333 | 2 | 1644.73 | 842.81 | 315.29 | 397.53 | 89.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23187470000 |  | 100279793 |  | 6688228J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SUNSET | 185 SUNSET DR | 073 | FRA | 2023-05-16 | U132743 | U131552 | 2023-05-11 | 2023-05-11 | 2023-05-29 |  | EFGOINS | 2023-05-15 | 2023-05-11 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 | 12.3 | 5 | 1183.6 | 1020.3 | 0 | 57.7 | 105.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23187782400 |  | 100323365 |  | 6716208P | 1635077 |  |  | 565 | EX | SERVICE LINE - REPLACE D333504 | 2621P | LANSDOWNE | 3257 LANSDOWNE DR | 067 | LEX | 2023-05-16 | U930915 | U130871 | 2023-05-12 | 2023-05-12 | 2023-05-12 |  | HMCKUNE | 2023-05-15 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.95 | 3 | 1655.44 | 1285.1 | 214.08 | 72.66 | 83.6 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23188203700 |  | 100280113 |  | 6688228N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LYONS | 324 LYONS DR | 073 | FRA | 2023-05-16 | U132743 | U131366 | 2023-05-15 | 2023-05-12 | 2023-05-12 |  | EFGOINS | 2023-05-15 | 2023-05-15 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 | 9.8 | 3 | 660.59 | 559.64 | 0 | 31.65 | 69.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 03529536300 |  | 100409277 |  | 600000000 | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | R4 WILLOW | R4 WILLOW LN | 067 | LEX | 2023-05-16 | U126308 | DMCCULL | 2003-01-31 | 2022-07-01 | 2023-12-31 |  | J ENSMINGER | 2023-05-16 | 2022-11-17 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 24.6667 | 5 | 1636.65 | 1549.08 | 0 | 87.57 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 03529537600 |  | 100411667 |  | 600000000 | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | R4 HALEY | R4 HALEY RD | 067 | LEX | 2023-05-16 | U126308 | DMCCULL | 2003-01-31 | 2022-07-01 | 2023-12-31 |  | J ENSMINGER | 2023-05-16 | 2022-11-17 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.7 | 4 | 501.95 | 475.09 | 0 | 26.86 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22104259100 |  | 100311111 |  | 6712208O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | HAVERHILL | 720 HAVERHILL DR | 067 | LEX | 2023-05-16 | KOBRYAN | AOC SYST | 2022-05-31 | 2022-11-30 | 2023-12-31 |  | KOBRYAN | 2023-05-16 | 2023-05-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 10.9833 | 4 | 1053.44 | 682.31 | 254.45 | 38.58 | 78.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166693300 |  | 100272390 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | SHELBY | 836 SHELBY ST | 073 | FRA | 2023-05-16 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-05-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3798.9 | 0 | 0 | 0 | 3798.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168511300 |  | 100342606 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 316 HOLT AV | 173 | MT | 2023-05-18 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-16 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2534.76 | 0 | 0 | 0 | 2534.76 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23184291700 |  | 100344677 |  | 6700224K |  |  |  | 566 | EX | NBT - ABANDON SL - IDLE/INA | 2621P | LEESTOWN | 158 W LEESTOWN RD | 239 | MID | 2023-05-16 | BWHITE | U125208 | 2023-04-28 | 2023-05-03 | 2023-05-19 |  | BWHITE | 2023-05-16 | 2023-05-11 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 23.4333 | 4 | 3959.61 | 2393.7 | 0 | 135.3 | 1430.61 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23184642100 |  | 500045382 |  | 6708212K |  |  |  | 566 | EX | ABANDON - DEMO/LNDBK UPSTREAM | 2621P | VERSAILLES *3500 VERS* | 3295 VERSAILLES *3500 VERS* RD | 067 | LEX | 2023-06-18 | U128711 | U125208 | 2023-05-01 | 2023-04-28 | 2023-05-28 |  | MCRAIG | 2023-05-16 | 2023-05-16 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.2833 | 2 | 739.8 | 526.46 | 0 | 213.34 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23187015800 |  | 100241122 |  | 7356256B |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | CARTER | 2100 CARTER AV | 019 | ASH | 2023-05-16 | JKEENER | U133234 | 2023-05-09 | 2023-05-19 | 2023-06-04 |  | JKEENER | 2023-05-16 | 2023-05-16 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 11.0333 | 2 | 788.94 | 674.82 | 0 | 114.12 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23188162100 |  | 100330995 |  | 6720212N |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | PRESTON | 120 PRESTON AV | 067 | LEX | 2023-05-17 | UIPBOT12 | U131552 | 2023-05-15 | 2023-05-15 | 2023-05-15 |  | MSHARON | 2023-05-16 | 2023-05-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 17.9 | 3 | 1421.41 | 1105.27 | 182.17 | 62.47 | 71.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23188265200 |  | 100317441 |  | 6716204J |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333504 | 2621P | KENLOCK | 284 KENLOCK DR | 067 | LEX | 2023-05-22 | U125208 | U129939 | 2023-05-15 | 2023-10-05 | 2025-04-30 |  | RJCRAWF | 2023-05-16 | 2023-05-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 3.4833 | 4 | 1524.17 | 1069.5 | 289.25 | 58.72 | 106.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23188682500 |  | 100418828 |  | 6716204J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | WEM | 3836 WEM DR | 067 | LEX | 2023-05-17 | U132743 | U131552 | 2023-05-16 | 2023-10-05 | 2025-04-30 |  | ABLAKE | 2023-05-16 | 2023-04-27 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 7.1833 | 5 | 1549.61 | 1172.61 | 213.99 | 65.11 | 97.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 05613315000 |  | 100357277 |  | 7240280D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2600B | R1 KY 10 | R1 KY 10 | 023 | GER | 2023-05-17 | SDADAMS | RPOLLY | 2005-06-07 | 2022-07-01 | 2023-12-31 |  | SDADAMS | 2023-05-17 | 2022-11-17 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 7.0833 | 4 | 478.97 | 439.12 | 15.02 | 24.83 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960860100 |  | 100437156 |  | 7356248H | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | NEAL | 7915 NEAL RD | 019 | CAT | 2023-05-17 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH DEREK CRAGER | 2023-05-17 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2629.62 | 0 | 0 | 0 | 2629.62 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129031600 |  | 100263965 |  | 7352260O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 1800 MAIN ST W | 019 | ASH | 2023-06-12 | U124015 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ORA SLONE | 2023-05-17 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1474.55 | 0 | 0 | 0 | 1474.55 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22150003300 |  | 500364572 |  | 7384168L |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2600B | HAPPY VALLEY | 419 HAPPY VALLEY RD | 195 | S W | 2023-05-19 | U125566 | U124960 | 2022-12-21 | 2022-12-22 | 2024-06-30 |  | DESKAGG | 2023-05-17 | 2023-05-16 |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26330022 | 15.3833 | 2 | 2435.71 | 1067.79 | 201.05 | 193.19 | 973.68 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23026275900 |  |  |  | 7344160I | 2397787 | U461383 |  | 588 | EX | RETIRE BATTERY FACILITY | 2600M | JARRELL FORK | JARRELL FORK | 071 | LAN | 2023-06-01 | U123258 | U461383 | 2023-05-23 | 2023-12-01 | 2023-12-01 | 2023-05-17 | MRYAN | 2023-05-17 |  |  | F | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00588 | 3200588 |  |  | WP2759 |  |  | 100 | 058832230262759 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164766800 |  | 100281594 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | WALNUT | 537 WALNUT ST | 209 | GEO | 2023-05-17 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-05-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2278.51 | 0 | 0 | 0 | 2278.51 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164766900 |  | 100281618 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | WALNUT | 538 WALNUT ST | 209 | GEO | 2023-05-17 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-05-17 | 2023-05-17 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.4833 | 1 | 2563.18 | 215.64 | 0 | 56.01 | 2291.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166668300 |  | 100322635 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 664 BERRY LN | 067 | LEX | 2023-05-17 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-05-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2527.72 | 0 | 0 | 0 | 2527.72 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166692500 |  | 100272403 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | SHELBY | 814 SHELBY ST | 073 | FRA | 2023-05-17 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-05-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3430.53 | 0 | 0 | 0 | 3430.53 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166692800 |  | 100272398 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | SHELBY | 822 SHELBY ST | 073 | FRA | 2023-05-17 | U126285 | U125763 | 2023-02-14 | 2023-06-30 |  |  | DDAVIS | 2023-05-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2879.94 | 0 | 0 | 0 | 2879.94 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168134500 |  | 100275018 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WATSON | 112 WATSON CT | 073 | FRA | 2023-05-17 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-05-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2647.31 | 0 | 0 | 0 | 2647.31 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168134700 |  | 100275027 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WILKINSON | 98 WILKINSON ST | 073 | FRA | 2023-05-17 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-05-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3757.79 | 24.35 | 0 | 1.34 | 3732.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168511100 |  | 100342607 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 310 HOLT AV | 173 | MT | 2023-05-17 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-17 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3665.5 | 0 | 0 | 0 | 3665.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23177055900 |  | 100331489 |  | 6720212N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333589 | 2621P | RICHMOND | 4 RICHMOND AV | 067 | LEX | 2023-05-18 | U930915 | U125208 | 2023-03-29 | 2023-09-28 | 2025-03-31 |  | HMCKUNE | 2023-05-17 | 2023-05-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 33.4667 | 8 | 1974.89 | 1778.57 | 23.19 | 100.53 | 72.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23179491200 |  | 100413011 |  | 6716204J |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333509 | 2621P | WEM | 3845 WEM DR | 067 | LEX | 2023-05-18 | U132743 | U125208 | 2023-04-06 | 2023-10-05 | 2025-04-30 |  | JOCHOA | 2023-05-17 | 2023-04-27 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.8833 | 5 | 1398.61 | 1186.7 | 83.31 | 67 | 61.6 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23187197000 |  | 100279677 |  | 6688228O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332783 | 2621P | FLAMINGO | 527 FLAMINGO AV | 073 | FRA | 2023-05-18 | U126332 | U125208 | 2023-05-10 | 2023-05-12 | 2023-05-30 |  | EFGOINS | 2023-05-17 | 2023-05-17 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 22.5 | 3 | 1435.6 | 1304.65 | 0 | 73.75 | 57.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23188272800 |  | 100323426 |  | 6716208P |  |  |  | 565 | EX | SERVICE LINE - LEAKAGE D094442 | 2621P | BRAEMER | 3317 BRAEMER DR | 067 | LEX | 2023-05-17 | U128336 | U125208 | 2023-05-15 | 2023-05-17 | 2023-06-05 |  | JOSHUA COX | 2023-05-17 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20 | 2 | 1946.79 | 1265.14 | 518.83 | 71.52 | 91.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23188993700 |  | 100342542 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 309 HOLT AV | 173 | MT | 2023-05-18 | U123111 | U125763 | 2023-05-17 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-17 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2744.12 | 0 | 0 | 0 | 2744.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 05610969500 |  | 100271045 |  | 6744288T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2600B | R2 | R2 | 023 | FOS | 2023-05-18 | SDADAMS | RPOLLY | 2005-05-16 | 2022-07-01 | 2023-12-31 |  | SDADAMS | 2023-05-18 | 2022-10-06 |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 5.9 | 3 | 382.37 | 361.92 | 0 | 20.45 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883318500 |  | 100446337 |  | 6696220C |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | OLD FRANKFORT | 2629 OLD FRANKFORT PK POOL | 239 | MID | 2023-05-19 | U930915 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BWHITE | 2023-05-18 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 4.6333 | 3 | 319.39 | 297.51 | 5.05 | 16.83 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960884000 |  | 100249900 |  | 7356248H | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | NEAL | 7830 NEAL RD | 019 | CAT | 2023-05-19 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH DEREK CRAGER | 2023-05-18 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3284.91 | 0 | 0 | 0 | 3284.91 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22113735300 |  | 100320073 |  | 6716208K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311911 | 2621P | JESSELIN | 107 JESSELIN DR | 067 | LEX | 2023-06-27 | U132035 | U125208 | 2022-07-01 | 2022-12-30 | 2024-06-30 |  | HMCKUNE | 2023-05-18 | 2023-02-24 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.9833 | 7 | 4727.22 | 1529.44 | 312.12 | 472.12 | 2413.54 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129002500 |  | 100433623 |  | 6740232J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | VICTORY | VICTORY AV | 017 | PAR | 2023-05-18 | ASNICHO | U130722 | 2022-09-05 | 2022-12-30 | 2023-12-31 |  | ASNICHO | 2023-05-18 | 2022-11-17 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 16.6667 | 4 | 2278.77 | 1278.37 | 0 | 1000.4 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129009200 |  | 100258801 |  | 7356256F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MONTGOMERY | 2708 MONTGOMERY AV | 019 | ASH | 2023-05-18 | JKEENER | U130722 | 2022-09-05 | 2022-12-30 |  |  | JKEENER | 2023-05-18 | 2023-04-27 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 12.5833 | 3 | 927.99 | 771.25 | 0 | 156.74 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129030400 |  | 100258875 |  | 7356256F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WINDSOR | 820 WINDSOR CT | 019 | ASH | 2023-06-19 | U135005 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RECUMP | 2023-05-18 | 2023-05-17 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 7.6833 | 3 | 576.69 | 465.64 | 20.27 | 90.78 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22979045500 |  | 100424443 |  | 7364188A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | MAIN | 336 E MAIN ST | 159 | INE | 2023-05-18 | JCKIRK | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | JCKIRK | 2023-05-18 | 2022-11-17 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 8.1 | 4 | 525.75 | 497.37 | 0 | 28.38 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164766700 |  | 100281619 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | WALNUT | 536 WALNUT ST | 209 | GEO | 2023-05-18 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-05-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1974.27 | 0 | 0 | 0 | 1974.27 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23165047500 |  | 500075515 |  | 6684228J | 1855043 |  |  | 566 | EX | ABANDON SL - SOII/LGCY | 2621P | SAINT CLAIR | 309 SAINT CLAIR ST R | 073 | FRA | 2023-05-19 | U930915 | MDULANE | 2023-02-06 | 2023-05-23 | 2023-05-23 |  | EFGOINS | 2023-05-18 | 2023-03-29 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 4.15 | 4 | 260.96 | 235.28 | 0 | 25.68 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168133300 |  | 100275036 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WAPPING | 505 WAPPING ST | 073 | FRA | 2023-05-18 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-05-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3082.45 | 0 | 0 | 0 | 3082.45 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168136200 |  | 100275256 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WILKINSON | 304 WILKINSON ST | 073 | FRA | 2023-05-18 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-05-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 5143.55 | 0 | 0 | 0 | 5143.55 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168511000 |  | 100342608 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 308 HOLT AV | 173 | MT | 2023-05-19 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-18 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2741.14 | 0 | 0 | 0 | 2741.14 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23177393000 |  | 100323681 |  | 6716208P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D310455 | 2621P | LANSDOWNE | 3400 LANSDOWNE DR | 067 | LEX | 2023-06-18 | U128711 | U125208 | 2023-03-31 | 2023-09-29 | 2025-03-31 |  | LSTANFI | 2023-05-18 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.3333 | 3 | 1866.6 | 854.98 | 0 | 121.77 | 889.85 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23188227500 |  | 100422327 |  | 6728208C |  |  |  | 565 | EX | REPLACE SERVICE - LEAK D332807 | 2621P | BAHAMA | 1765 BAHAMA RD | 067 | LEX | 2023-05-31 | U130722 | U125208 | 2023-05-15 | 2023-05-18 | 2023-06-05 |  | LSTANFI | 2023-05-18 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.4667 | 5 | 1341.67 | 1087.04 | 0 | 111.63 | 143 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23188242900 |  | 100346105 |  | 6700212I | 0145212 |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | LEXINGTON | 516 LEXINGTON RD | 239 | VER | 2023-05-18 | BWHITE | U125208 | 2023-05-15 | 2023-05-31 | 2023-05-31 |  | BWHITE | 2023-05-18 | 2023-05-17 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26230031 | 22.3667 | 4 | 1636.63 | 1451.24 | 62.65 | 82.04 | 40.7 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23189027700 |  | 100272298 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | ROCKLAND | 2 ROCKLAND CT | 073 | FRA | 2023-05-18 | U126285 | U125763 | 2023-05-17 | 2023-12-29 |  |  | DDAVIS | 2023-05-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2410.65 | 0 | 0 | 0 | 2410.65 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23189027800 |  | 100272299 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | ROCKLAND | 6 ROCKLAND CT | 073 | FRA | 2023-05-18 | U126285 | U125763 | 2023-05-17 | 2023-12-29 |  |  | DDAVIS | 2023-05-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2296.78 | 0 | 0 | 0 | 2296.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23189041000 |  | 100411048 |  | 6716216K |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | REDWOOD | 1146 REDWOOD DR | 067 | LEX | 2023-05-18 | ATWILLI | U131552 | 2023-05-17 | 2023-05-17 |  |  | ATWILLI | 2023-05-18 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 9.4333 | 3 | 1974.01 | 1149.07 | 213.99 | 514.15 | 96.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23189368900 |  | 100280116 |  | 6688228N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LYONS | 318 LYONS DR | 073 | FRA | 2023-05-25 | U126332 | U131552 | 2023-05-18 | 2023-05-18 | 2023-06-02 |  | EFGOINS | 2023-05-18 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 | 12.3833 | 2 | 879.76 | 767.09 | 0 | 43.37 | 69.3 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23189389300 |  | 100443157 |  | 6700224P |  |  |  | 566 | EX | ABN SERVICE LINE | 2621P | GRATZ | 204 N GRATZ ST 1 | 239 | MID | 2023-05-18 | BWHITE | U131552 | 2023-05-18 | 2023-05-18 |  |  | BWHITE | 2023-05-18 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 1.9 | 2 | 129.89 | 122.94 | 0 | 6.95 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 94165377100 |  | 100441625 | 01 | 600000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | COLUMBIA | 435 COLUMBIA AV | 067 | LEX | 2023-05-18 | ATWILLI | KAUSTIN | 1994-03-29 | 2003-12-31 | 2023-12-31 |  | ATWILLI | 2023-05-18 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.6667 | 3 | 1050.38 | 359.1 | 0 | 248.15 | 443.13 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21026140501 |  |  |  | 6748208E | 2292377 | U128885 |  | 557 | EX | INSTALL 1,985'-6" CSHP | 2600B | PARIS | PARIS PK | 049 | WIN | 2024-05-01 | U128132 | U128885 | 2023-05-16 | 2023-12-29 | 2023-12-31 | 2023-05-04 | SHAWN DENNIS | 2023-05-19 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP1405 | AMRCB |  | 100 | 055732210261405 |  | 1874 | 140188.39 | 1141.25 | 115375.25 | 738.13 | 0 | 0 | 1939.86 | 20993.9 | 1874
KY | KY - CENTRAL | 2629 | 21026140600 |  |  |  | 6748208E | 2292377 | U128885 |  | 558 | EX | RETIRE 2,598'- 6" BSHP | 2600B | PARIS | PARIS PK | 049 | WIN | 2023-07-07 | U128132 | U128885 | 2021-09-09 | 2023-12-29 | 2023-12-31 | 2023-05-04 | SHAWN DENNIS | 2023-05-19 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP1406 | AMRCB |  | 100 | 055832210261406 |  | 0 | 182.4 | 0 | 0 | 0 | 182.4 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883064500 |  | 100247798 |  | 7364188A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | MAIN | 303 E MAIN ST | 159 | INE | 2023-05-19 | JCKIRK | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JCKIRK | 2023-05-19 | 2022-11-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 11.2333 | 5 | 6435.35 | 682.48 | 0 | 38.99 | 5713.88 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883323900 |  | 500626910 |  | 6732244H | 9828969 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | US 27 S | US 27 S | 097 | CYN | 2023-05-19 | ASNICHO | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | ASNICHO | 2023-05-19 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.1 | 2 | 403.54 | 265.66 | 0 | 137.88 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960854700 |  | 100410682 |  | 7348248H | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | HILLCREST | 7714 HILLCREST DR | 019 | CAT | 2023-05-19 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH DEREK CRAGER | 2023-05-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2035.27 | 0 | 0 | 0 | 2035.27 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026228300 |  |  |  | 6748208I | 2292377 | U128885 |  | 558 | EX | RETIRE 6,106'- LP MAIN | 2600E | MAPLE | N MAPLE ST | 049 | WIN | 2023-06-14 | U128132 | U128885 | 2022-09-29 | 2024-01-31 | 2024-09-20 | 2023-05-10 | SHAWN DENNIS | 2023-05-19 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP2283 | AMRCB |  | 100 | 055832220262283 |  | 0 | 182.4 | 0 | 0 | 0 | 182.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164765400 |  | 100281626 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | WALNUT | 524 WALNUT ST | 209 | GEO | 2023-05-22 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-05-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.8333 | 1 | 3621.62 | 301.41 | 0 | 78.27 | 3241.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165281600 |  | 100336866 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | JOHNSON | 467 JOHNSON AV | 067 | LEX | 2023-05-19 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-05-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 5077.16 | 0 | 0 | 0 | 5077.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166669200 |  | 100322639 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 680 BERRY LN | 067 | LEX | 2023-05-19 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-05-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1845.74 | 0 | 0 | 0 | 1845.74 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166692900 |  | 100272397 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | SHELBY | 824 SHELBY ST | 073 | FRA | 2023-05-19 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-05-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3888.75 | 0 | 0 | 0 | 3888.75 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168134900 |  | 100275026 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WILKINSON | 101 WILKINSON ST | 073 | FRA | 2023-05-19 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-05-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3758.93 | 18.28 | 0 | 0.99 | 3739.66 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168136400 |  | 100275257 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WILKINSON | 308 WILKINSON ST | 073 | FRA | 2023-05-19 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-05-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3802.5 | 0 | 0 | 0 | 3802.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168510700 |  | 100342609 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 304 HOLT AV | 173 | MT | 2023-05-19 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-19 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3092.77 | 0 | 0 | 0 | 3092.77 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168510800 |  | 100342539 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 305 HOLT AV | 173 | MT | 2023-05-22 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-19 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3774.97 | 0 | 0 | 0 | 3774.97 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23183654400 |  | 100356364 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | WALLER | 1214 WALLER ST | 161 | MAY | 2023-05-19 | U126286 | U125763 | 2023-04-25 | 2023-12-29 |  |  | TYLER ALLISON | 2023-05-19 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 3082.49 | 10.95 | 0 | 0.62 | 3070.92 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23183655600 |  | 100356365 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | WALLER | 1216 WALLER ST | 161 | MAY | 2023-05-19 | U126286 | U125763 | 2023-04-25 | 2023-12-29 |  |  | TYLER ALLISON | 2023-05-19 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 3135.07 | 0 | 0 | 0 | 3135.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23189688600 |  | 100325501 |  | 6720208E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | COOPER | 1238 COOPER DR | 067 | LEX | 2023-05-19 | MCRAIG | U130871 | 2023-05-19 | 2023-05-17 | 2023-05-17 |  | MCRAIG | 2023-05-19 | 2023-05-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 41.85 | 5 | 7180.92 | 2418.19 | 345.59 | 759.64 | 3657.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 03529539500 |  | 100318967 |  | 600000000 | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | NICHOLASVILLE | 2412 NICHOLASVILLE RD | 067 | LEX | 2023-05-22 | ATWILLI | DMCCULL | 2003-01-31 | 2022-12-28 | 2023-12-31 |  | ATWILLI | 2023-05-22 | 2022-10-14 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 25.4667 | 7 | 3352.49 | 1577.95 | 0 | 597.53 | 1177.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11892959800 |  | 100317198 |  | 6716208N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | NICHOLASVILLE | 2553 NICHOLASVILLE RD F | 067 | LEX | 2023-05-22 | ATWILLI | U123933 | 2011-03-01 | 2022-12-13 | 2023-12-31 |  | ATWILLI | 2023-05-22 | 2022-12-13 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 20.6333 | 4 | 2304.98 | 1366.7 | 0 | 197.22 | 741.06 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960854800 |  | 100249892 |  | 7360248E | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | HILLCREST | 7733 HILLCREST DR | 019 | CAT | 2023-05-23 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH DEREK CRAGER | 2023-05-22 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2015.05 | 0 | 0 | 0 | 2015.05 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026228201 |  |  |  | 6748208I | 2292377 | U128885 |  | 557 | EX | INSTALL 4,225'-2"/6" PMMP | 2600B | MAPLE | MAPLE ST | 049 | WIN | 2023-06-26 | U128132 | U128885 | 2023-04-04 | 2023-06-07 | 2024-09-20 | 2023-05-04 | SHAWN DENNIS | 2023-05-22 | 2023-01-03 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP2282 | AMRCB |  | 100 | 055732220262282 | 1232.6333 | 592952 | 1935349.38 | 87394.52 | 194217.88 | 23445.35 | 1330790.74 | 0 | 18527.52 | 280973.37 | 3901
KY | KY - EAST | 2631 | 22129028300 |  | 100252979 |  | 7356256F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FERGUSON | 1500 FERGUSON ST | 019 | ASH | 2023-06-22 | U135005 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RECUMP | 2023-05-22 | 2023-05-03 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 10.85 | 8 | 831.54 | 654.85 | 20.27 | 156.42 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22964252600 |  | 100430487 |  | 6748208I | 2292377 |  |  | 566 | EX | ABANDN SL/22026228200 | 2600B | MAIN | 614< N MAIN ST | 049 | WIN | 2023-05-22 | U126603 | U134723 | 2022-01-06 | 2023-07-31 |  |  | CHARLES COMBS/SHAWN DENNIS | 2023-05-22 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - WEST | 2621 | 23026246401 |  |  |  | 6716208J | 2394661 | U461383 |  | 559 | EX | INSTALL 3100' OF 2"PMMP MAIN | 2600B | NICHOLASVILLE | 2263 NICHOLASVILLE RD | 067 | LEX | 2023-05-25 | U124014 | U461383 | 2023-05-15 | 2023-03-08 | 2023-06-01 | 2023-04-13 | WILL FULKS | 2023-05-22 | 2023-05-16 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP2464 | AMRCB |  | 100 | 055932230262464 | 386.6667 | 136535 | 515222.82 | 30034.4 | 7849.86 | 9776.66 | 388571.91 | 0 | 1227.11 | 77762.88 | 2905
KY | KY - WEST | 2621 | 23026246500 |  |  |  | 6716208J | 2394661 | U461383 |  | 560 | EX | RETIRE 2400' OF 4"BS/CSLP MAIN | 2600E | NICHOLASVILLE | 2263 NICHOLASVILLE RD | 067 | LEX | 2023-05-25 | U124014 | U461383 | 2023-01-03 | 2023-06-01 | 2023-06-01 | 2023-05-19 | WILL FULKS | 2023-05-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00560 | 3200560 |  |  | WP2465 | AMRCB |  | 100 | 056032230262465 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164765200 |  | 100281587 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | WALNUT | 521 WALNUT ST | 209 | GEO | 2023-05-23 | U126309 | U125763 | 2023-02-03 | 2023-12-29 |  |  | JAMIE LYNN | 2023-05-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2782 | 0 | 0 | 0 | 2782 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164766600 |  | 100281593 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | WALNUT | 535 WALNUT ST | 209 | GEO | 2023-05-23 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-05-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2823.8 | 0 | 0 | 0 | 2823.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164767000 |  | 100281596 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | WALNUT | 558 WALNUT ST | 209 | GEO | 2023-05-23 | U126309 | U125763 | 2023-02-03 | 2023-12-29 |  |  | JAMIE LYNN | 2023-05-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2862.19 | 0 | 0 | 0 | 2862.19 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166669400 |  | 100322640 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 684 BERRY LN | 067 | LEX | 2023-05-23 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-05-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1529.79 | 0 | 0 | 0 | 1529.79 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168510200 |  | 100342611 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 222 HOLT AV | 173 | MT | 2023-05-24 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-22 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3256.81 | 0 | 0 | 0 | 3256.81 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168510400 |  | 500484109 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 230 HOLT AV | 173 | MT | 2023-05-24 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-22 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2498.3 | 0 | 0 | 0 | 2498.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23183654300 |  | 100356371 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | WALLER | 1213 WALLER ST | 161 | MAY | 2023-05-22 | U126286 | U125763 | 2023-04-25 | 2023-12-29 |  |  | TYLER ALLISON | 2023-05-22 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 | 8 | 1 | 3601.83 | 496.34 | 0 | 28.05 | 3077.44 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23183654500 |  | 100356372 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | WALLER | 1215 WALLER ST | 161 | MAY | 2023-05-23 | U126286 | U125763 | 2023-04-25 | 2023-12-29 |  |  | TYLER ALLISON | 2023-05-22 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 3055.42 | 30.79 | 0 | 1.75 | 3022.88 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23185368900 |  | 100260760 |  | 7352256K |  |  |  | 565 | EX | NBT -REINST/UPG SL-NO PRMT REQ | 2621P | 13TH | 3339 13TH ST | 019 | ASH | 2023-05-22 | MCOLLET | U125208 | 2023-05-02 | 2023-05-02 | 2023-05-12 |  | MCOLLET | 2023-05-22 | 2023-05-18 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 44.1167 | 6 | 7601.76 | 3030.84 | 481.65 | 3940.77 | 148.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23189027900 |  | 100272300 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | ROCKLAND | 8 ROCKLAND CT | 073 | FRA | 2023-05-24 | U126285 | U125763 | 2023-05-17 | 2023-12-29 |  |  | DDAVIS | 2023-05-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3289.65 | 0 | 0 | 0 | 3289.65 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23189028000 |  | 100272301 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | ROCKLAND | 10 ROCKLAND CT | 073 | FRA | 2023-05-24 | U126285 | U125763 | 2023-05-17 | 2023-12-29 |  |  | DDAVIS | 2023-05-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2389.29 | 0 | 0 | 0 | 2389.29 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23189720400 |  | 100323649 |  | 6716204C | 1635077 |  |  | 565 | EX | GRD 1 ON SERVICE | 2621P | LANSDOWNE | 3441 LANSDOWNE DR | 067 | LEX | 2023-05-22 | TROE | U130871 | 2023-05-19 | 2023-05-19 | 2023-05-19 |  | TROE | 2023-05-22 | 2023-05-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.7667 | 4 | 1521.52 | 986 | 387.4 | 55.72 | 92.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23190087900 |  | 100280034 |  | 6688228N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LYONS | 307 LYONS DR | 073 | FRA | 2023-05-23 | U132743 | U131552 | 2023-05-22 | 2023-05-15 | 2023-06-02 |  | BWHITE | 2023-05-22 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 | 4.4333 | 2 | 567.8 | 433.31 | 0 | 24.49 | 110 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23190110100 |  | 100331287 |  | 6720212N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | OWSLEY | 116 OWSLEY AV | 067 | LEX | 2023-05-23 | U132743 | U131552 | 2023-05-22 | 2023-09-24 | 2025-03-31 |  | LSTANFI | 2023-05-22 | 2023-05-22 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 10.9833 | 5 | 1132.23 | 902.38 | 0 | 105.55 | 124.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883321300 |  | 500623855 |  | 6720204F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | CENTRE | 1165 CENTRE PY STE 275 | 067 | LEX | 2023-05-23 | ATWILLI | U120245 | 2021-01-30 | 2022-10-10 | 2023-12-31 |  | ATWILLI | 2023-05-23 | 2022-10-10 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10.9 | 3 | 1862.18 | 601.56 | 0 | 348.9 | 911.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21924499400 |  | 100296311 |  | 6716216O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | TIBBS | 420 TIBBS LN | 067 | LEX | 2023-05-23 | MCRAIG | AOC SYST | 2021-07-09 | 2022-01-07 | 2022-12-31 |  | MCRAIG | 2023-05-23 | 2023-03-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 29.5667 | 15 | 3109.73 | 1802.53 | 505.47 | 720.33 | 81.4 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960883600 |  | 100410565 |  | 7348248H | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | HILLCREST | 7732 HILLCREST DR | 019 | CAT | 2023-05-23 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH DEREK CRAGER | 2023-05-23 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3493.33 | 0 | 0 | 0 | 3493.33 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026268700 |  |  |  | 6756244C | 2394770 | U132257 |  | 559 | CO | PM-DE LINE PH 2 DENT 2/STPL 3 | 5320E |  |  | 181 | CAR | 2023-07-18 |  | U132257 | 2023-03-23 | 2023-12-29 | 2023-12-31 | 2023-05-23 | BJOHNSON | 2023-05-23 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00559 | 3201033 |  |  | WP2687 |  |  | 100 | 103332230262687 |  | 25 | 703157.62 | 14413.99 | 629.49 | 6532.97 | 579967.72 | 0 | 658.69 | 100954.76 | 25
KY | KY - CENTRAL | 2629 | 23026275100 |  |  |  | 7240212C | 2397698 | U128885 |  | 562 | EX | RETIRE 276'-3" BSLP | 2600B | QUEEN | S QUEEN ST | 173 | MT | 2023-06-01 | U124014 | U128885 | 2023-05-17 | 2023-05-25 | 2023-05-26 | 2023-05-23 | WILL FULKS | 2023-05-23 | 2023-05-23 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00562 | 3200562 |  |  | WP2751 | AMRCB |  | 100 | 056232230262751 | 13.5333 | 0 | 5918.41 | 1142.38 | 0 | 361.14 | 4414.89 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23026275800 |  |  |  | 7344160I | 2397787 | U461383 |  | 587 | EX | INSTALL NEW BATTERY/EQUIPMENT | 2600M | JARRELL FORK | JARRELL FORK | 071 | LAN | 2023-06-01 | U123258 | U461383 | 2023-05-23 | 2023-12-01 | 2023-12-01 | 2023-05-23 | WADE SHIMFESSEL | 2023-05-23 |  |  | F | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00587 | 3200587 |  |  | WP2758 |  |  | 100 | 058732230262758 |  | 1 | 135.94 | 110.8 | 0 | 6.39 | 0 | 0 | 0 | 18.75
KY | KY - CENTRAL | 2632 | 23156278000 |  | 100461269 |  | 7256280M | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | WADSWORTH | 1219 WADSWORTH ST | 161 | MAY | 2023-05-23 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-05-23 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1926.4 | 3.77 | 0 | 0.22 | 1922.41 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164765300 |  | 100281627 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | WALNUT | 522 WALNUT ST | 209 | GEO | 2023-05-23 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-05-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2545.34 | 0 | 0 | 0 | 2545.34 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164767100 |  | 100281595 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | WALNUT | 560 WALNUT ST | 209 | GEO | 2023-05-23 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-05-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3804.36 | 0 | 0 | 0 | 3804.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23164958500 |  | 100325117 |  | 6720204A |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | ELMENDORF | 1038 ELMENDORF DR | 067 | LEX | 2023-05-24 | U128336 | U125208 | 2023-02-05 | 2023-03-31 | 2023-05-02 |  | JOSHUA COX | 2023-05-23 | 2023-04-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.9167 | 4 | 1391.84 | 937.4 | 310.36 | 52.78 | 91.3 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166689500 |  | 100439645 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | OWSLEY | 305 OWSLEY AV | 073 | FRA | 2023-05-23 | U126309 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JAMIE LYNN | 2023-05-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3643.83 | 0 | 0 | 0 | 3643.83 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168133600 |  | 100275043 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WAPPING | 514 WAPPING ST A | 073 | FRA | 2023-05-23 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-05-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 5098.6 | 0 | 0 | 0 | 5098.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168510100 |  | 100342536 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 221 HOLT AV | 173 | MT | 2023-05-24 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-23 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2635.73 | 0 | 0 | 0 | 2635.73 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168510300 |  | 100342537 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 225 HOLT AV | 173 | MT | 2023-05-24 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-23 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2739.79 | 0 | 0 | 0 | 2739.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23185788300 |  | 100324436 |  | 6720204E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER | 2621D | VENETIAN | 1147 VENETIAN WY | 067 | LEX | 2023-05-24 | U130722 | AOC SYST | 2023-05-03 | 2023-05-31 | 2023-06-30 |  | DMARSTO | 2023-05-23 | 2023-05-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 14.8167 | 3 | 962.9 | 852.05 | 0 | 48.15 | 62.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23189022600 |  | 100310500 |  | 6712208L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309468 | 2621P | NAKOMI | 635 NAKOMI DR | 067 | LEX | 2023-05-23 | KKINDER | U125208 | 2023-05-17 | 2023-05-19 | 2023-06-07 |  | KKINDER | 2023-05-23 | 2023-05-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.6167 | 2 | 1501.51 | 910.8 | 422.61 | 51.5 | 116.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23190318800 |  | 100404842 |  | 6716204J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | TANGLEY | 311 TANGLEY WY | 067 | LEX | 2023-05-24 | U132743 | U132864 | 2023-05-23 | 2023-10-05 | 2025-04-30 |  | ABLAKE | 2023-05-23 | 2023-05-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 3.65 | 3 | 1388.8 | 1020.19 | 213.99 | 55.62 | 99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11928894700 |  | 100333802 |  | 6720212O |  |  |  | 566 | EX | ABANDON SL - IDLE/INA UPSTREAM | 2621P | DELAWARE | 1107 DELAWARE AV | 067 | LEX | 2023-05-25 | U132743 | U124017 | 2011-10-14 | 2020-12-31 |  |  | LSTANFI | 2023-05-24 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.75 | 1 | 63.08 | 49.08 | 0 | 14 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960859400 |  | 100249895 |  | 7360248E | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | MCCOMIS | 7719 MCCOMIS DR | 019 | CAT | 2023-05-24 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH DEREK CRAGER | 2023-05-24 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1944.28 | 0 | 0 | 0 | 1944.28 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22026175100 |  |  |  | 7384168L | 2184598 | U938437 |  | 559 | EX | INSTALL 3" OUTLET VALVE | 2600B | HWY 119 | HWY 119 | 195 | S W | 2023-07-05 | U128132 | U938437 | 2022-03-09 | 2023-07-26 | 2023-08-01 | 2023-05-23 | DAVID SKAGGS | 2023-05-24 | 2023-05-17 |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00559 | 3200559 |  |  | WP1751 |  |  | 100 | 055932220261751 | 74.5833 | 112 | 36249.58 | 5352.33 | 3420.7 | 2632.2 | 19172.3 | 0 | 80.06 | 5591.99 | 14
KY | KY - EAST | 2633 | 22026175200 |  |  |  | 7384168L | 2184598 | U938437 |  | 560 | EX | RETIRE ~10' - 3" CSHP | 2600B | HWY 119 | HWY 119 | 195 | S W | 2023-05-26 | U128132 | U938437 | 2022-03-09 | 2023-08-01 | 2023-08-01 | 2023-05-23 | DAVID SKAGGS | 2023-05-24 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00560 | 3200560 |  |  | WP1752 |  |  | 100 | 056032220261752 | 3.0167 | 0 | 257.25 | 207.17 | 0 | 50.08 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026273200 |  |  |  | 6744184G | 2397341 | U128885 |  | 558 | EX | EMER-RETIRE 741'-1" PMP | 2621P | UNION CITY | 2450 UNION CITY RD | 151 | RIC | 2023-05-25 | U128132 | U128885 | 2023-05-03 | 2023-04-27 | 2023-04-29 | 2023-04-29 | WDENNING | 2023-05-24 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP2732 |  |  | 100 | 055832230262732 |  | 0 | 1327.21 | 844.06 | 0 | 483.15 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026274900 |  |  |  | 72402046 | 2397641 | U128885 |  | 557 | EX | EMER - INSTALL 4'-2" PMMP | 2621P | LEVEE | LEVEE RD | 173 | JEF | 2023-05-25 | U138344 | U128885 | 2023-05-16 | 2023-04-05 | 2023-05-09 | 2023-05-15 | WDENNING | 2023-05-24 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP2749 |  |  | 100 | 055732230262749 |  | 4 | 15519.62 | 10822.95 | 88.35 | 1315.77 | 1099.14 | 0 | 31 | 2162.41 | 4
KY | KY - CENTRAL | 2629 | 23026275000 |  |  |  | 72402046 | 2397641 | U128885 |  | 558 | EX | EMER - RETIRE 4'-2" PMMP | 2621P | LEVEE | LEVEE RD | 173 | JEF | 2023-05-25 | U138344 | U128885 | 2023-05-16 |  | 2049-12-31 | 2023-05-15 | WDENNING | 2023-05-24 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP2750 |  |  | 100 | 055832230262750 |  | 0 | 2331.35 | 1725.46 | 0 | 605.89 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23156275800 |  | 500201372 |  | 7256280N | 2180423 |  |  | 565 | EX | RPLC SL/21026127000 | 2600B | US 68 | 1231 US 68 | 161 | MAY | 2023-05-24 | U126286 | U125763 | 2023-01-16 | 2023-12-29 |  |  | TYLER ALLISON | 2023-05-24 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 7639.93 | 0 | 0 | 0 | 7639.93 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164754700 |  | 100281585 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | GANO | 321 GANO AV | 209 | GEO | 2023-05-24 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-05-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.3333 | 1 | 2681.4 | 147.27 | 0 | 8.33 | 2525.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164768900 |  | 100281588 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | WALNUT | 523 WALNUT ST | 209 | GEO | 2023-05-24 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-05-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2808.12 | 0 | 0 | 0 | 2808.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166669100 |  | 100322627 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 677 BERRY LN | 067 | LEX | 2023-05-25 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-05-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2315.22 | 0 | 0 | 0 | 2315.22 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166687300 |  | 100272375 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | CAPITAL HEIGHT | 209 CAPITAL HEIGHT DR | 073 | FRA | 2023-05-24 | U126309 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JAMIE LYNN | 2023-05-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 4886.25 | 0 | 0 | 0 | 4886.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168509800 |  | 100342535 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 219 HOLT AV | 173 | MT | 2023-05-25 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-24 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3651.13 | 0 | 0 | 0 | 3651.13 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168510900 |  | 100342541 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 307 HOLT AV | 173 | MT | 2023-06-01 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-24 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3943.11 | 0 | 0 | 0 | 3943.11 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23188227400 |  | 100255645 |  | 7348264H |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | MEADE | 1319 MEADE ST | 089 | FLA | 2023-05-24 | JKEENER | U133234 | 2023-05-15 | 2023-05-26 | 2023-06-14 |  | JKEENER | 2023-05-24 | 2023-05-24 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 14.6167 | 2 | 1052.45 | 896.25 | 6.19 | 150.01 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23189699500 |  | 100323508 |  | 6716208O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094446 | 2621P | FARMINGTON | 3409 FARMINGTON RD | 067 | LEX | 2023-05-25 | U128336 | U125208 | 2023-05-19 | 2023-05-19 | 2023-06-08 |  | JOSHUA COX | 2023-05-24 | 2023-05-24 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 28.5333 | 5 | 2514.47 | 1715.65 | 360.64 | 319.38 | 118.8 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23190299500 |  | 500032311 |  | 7324288M |  |  |  | 565 | EX | SERV LINE REPLACEMENT | 2621P | BEATTYVILLE | 426 BEATTYVILLE RD | 089 | S P | 2023-05-24 | MCOLLET | U132864 | 2023-05-23 | 2023-05-23 |  |  | MCOLLET | 2023-05-24 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 4 | 2 | 771.6 | 271.75 | 202.28 | 211.77 | 85.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23190585900 |  | 100465563 |  | 6716204J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | FOX HARBOUR | 317 FOX HARBOUR DR | 067 | LEX | 2023-05-25 | UIPBOT10 | U131552 | 2023-05-24 | 2023-10-04 | 2025-04-30 |  | KKINDER | 2023-05-24 | 2023-05-24 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 16.9333 | 5 | 1493.5 | 1275.32 | 65.93 | 71.95 | 80.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23190611600 |  | 500649151 |  | 6740204H | 9932914 |  |  | 566 | EX | ABN SERVICE | 2621P | HIBISCUS | 127 HIBISCUS LN | 049 | WIN | 2023-05-25 | U132743 | U131552 | 2023-05-24 | 2023-05-24 |  |  | NRICHIE | 2023-05-24 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 11.1667 | 2 | 1073.27 | 727.85 | 2.11 | 343.31 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 06638811400 |  | 100458640 |  | 6720212G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | NEW CIRCLE | 481 E NEW CIRCLE RD | 067 | LEX | 2023-05-25 | JGILES | SSUTHER | 2006-02-17 | 2022-07-01 | 2023-12-31 |  | JGILES | 2023-05-25 | 2023-05-12 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 21.5 | 6 | 1695.61 | 1282.95 | 0 | 412.66 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026169100 |  |  |  | 6748204H | 2286588 | GSULLI1 |  | 909 | EX | RT. 89 POD RTU BUILDING | 2600E | STATE RT 89 | STATE RT 89 | 049 | WIN | 2024-02-16 | U123258 | GSULLI1 | 2022-02-16 | 2022-12-27 | 2022-12-31 | 2023-05-25 | JPASLEY | 2023-05-25 | 2022-04-11 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00909 | 3200909 |  |  | WP1691 |  |  | 100 | 090932220261691 | 192.2833 | 0 | 221479.78 | 11983.32 | 0 | 5126.02 | 198183.81 | 0 | 6186.63 | 0
KY | KY - CENTRAL | 2629 | 23026251600 |  |  |  | 6748208N | 2286588 | U132280 |  | 577 | EX | INSTALL RTU BUILDING | 2629M | STATE RT 89 | STATE RT 89 | 049 | WIN | 2024-01-18 | U123258 | U132280 | 2023-01-17 | 2023-12-21 | 2023-12-25 | 2023-05-25 | JPASLEY | 2023-05-25 | 2023-05-05 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00577 | 3200577 |  |  | WP2516 |  |  | 100 | 057732230262516 | 14.35 | 3 | 2010.08 | 895.6 | 0 | 827.47 | 0 | 0 | 4.77 | 282.24
KY | KY - EAST | 2631 | 23026270300 |  |  |  | 7360252I | 2396648 | U132280 |  | 559 | EX | EMER - INSTALL 2'-4" PMMP | 2621P | CENTER | 2503 CENTER ST | 019 | CAT | 2023-08-14 | U128132 | U132280 | 2023-04-01 | 2023-12-29 | 2023-12-30 | 2023-04-02 | MCOLLETT | 2023-05-25 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00559 | 3200559 |  |  | WP2703 |  |  | 100 | 055932230262703 |  | 2 | 526.5 | 0 | 452.67 | 0 | 0 | 0 | 0 | 73.83 | 2
KY | KY - EAST | 2631 | 23026270400 |  |  |  | 7360252I | 2396648 | U132280 |  | 560 | EX | EMER - RETIRE 110'-4" P-MP | 2621P | CENTER | 2503 CENTER ST | 019 | CAT | 2023-06-02 | U128132 | U132280 | 2023-04-01 | 2023-12-29 | 2023-12-30 | 2023-04-02 | MCOLLET | 2023-05-25 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00560 | 3200560 |  |  | WP2704 |  |  | 100 | 056032230262704 | 4.3333 | 0 | 537.22 | 301.89 | 0 | 235.33 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164765900 |  | 100281590 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | WALNUT | 529 WALNUT ST | 209 | GEO | 2023-05-25 | U126602 | U125763 | 2023-02-03 | 2023-12-29 |  |  | DEREK PAYTON | 2023-05-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2559.98 | 0 | 0 | 0 | 2559.98 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164766200 |  | 100281621 |  | 6712232N | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | WALNUT | 532 WALNUT ST | 209 | GEO | 2023-05-25 | U126602 | U125763 | 2023-02-03 | 2023-12-29 |  |  | DEREK PAYTON | 2023-05-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3836.86 | 0 | 0 | 0 | 3836.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166669800 |  | 100322642 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 692 BERRY LN | 067 | LEX | 2023-05-25 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-05-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1538.07 | 0 | 0 | 0 | 1538.07 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166689600 |  | 100272362 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | OWSLEY | 307 OWSLEY AV | 073 | FRA | 2023-05-25 | U126309 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JAMIE LYNN | 2023-05-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2174.34 | 0 | 0 | 0 | 2174.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23185791600 |  | 100291257 |  | 6720216H | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER | 2621D | KINGSTON | 571 KINGSTON RD | 067 | LEX | 2023-05-26 | U132743 | AOC SYST | 2023-05-03 | 2023-05-26 | 2023-06-26 |  | LSTONE | 2023-05-25 | 2023-05-22 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.1 | 4 | 2596.12 | 1341 | 298.12 | 75.8 | 881.2 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23187591500 |  | 100279476 |  | 6688228O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMED D332787 | 2623D | HANLEY | 302 HANLEY LN | 073 | FRA | 2023-05-25 | U129731 | AOC SYST | 2023-05-11 | 2023-05-14 | 2023-06-01 |  | F.GOINS | 2023-05-25 | 2023-05-24 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 16.1833 | 5 | 1029.74 | 915.87 | 0 | 54.47 | 59.4 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23187810300 |  | 500792779 |  | 7324284E |  |  |  | 565 | EX | AOC ENCROACHMENT - RELOC SL | 2621P | WINDY HILLS | 121 WINDY HILLS RD | 089 | S P | 2023-05-25 | RECUMP | U125208 | 2023-05-12 | 2023-05-16 | 2023-06-12 |  | RECUMP | 2023-05-25 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 15.1833 | 2 | 1272.37 | 752.19 | 238.07 | 150.11 | 132 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23189401100 |  | 100335058 |  | 6720212O |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | LINDY | 1614 LINDY LN | 067 | LEX | 2023-05-26 | U132743 | U133234 | 2023-05-18 | 2023-06-01 | 2023-06-17 |  | JOCHOA | 2023-05-25 | 2023-05-24 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.6167 | 4 | 1225.48 | 789.94 | 133.22 | 302.32 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23190819600 |  | 100346806 |  | 6696212O |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HILLCREST | 355 HILLCREST DR | 239 | VER | 2023-05-25 | BWHITE | U131552 | 2023-05-25 | 2023-05-25 |  |  | BWHITE | 2023-05-25 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 27 | 3 | 2435.99 | 1755.05 | 0 | 587.44 | 93.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026242600 |  |  |  | 6712208J | 2288144 | U134275 |  | 559 | EX | INSTALL 500' - 4" PMMP | 2600B | MAN O WAR | 3725 MAN O WAR BD | 067 | LEX | 2023-06-28 | U128132 | U134275 | 2022-12-09 | 2023-09-18 | 2023-10-01 | 2023-05-26 | ED FOX | 2023-05-26 | 2023-04-25 | 2023-04-27 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP2426 |  |  | 100 | 055932220262426 | 130.85 | 9956 | 115979.71 | 9713.45 | 4420.44 | 6979.31 | 77476.14 | 0 | 277.72 | 17112.65 | 524
KY | KY - WEST | 2621 | 23166674000 |  | 100322673 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 693 PROVIDENCE RD | 067 | LEX | 2023-05-26 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-05-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3352.5 | 0 | 0 | 0 | 3352.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23189406100 |  | 100266702 |  | 7356256G |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | 31ST | 125 31ST ST | 019 | ASH | 2023-05-26 | RECUMP | U133234 | 2023-05-18 | 2023-06-01 | 2023-06-17 |  | RECUMP | 2023-05-26 | 2023-05-25 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 10.7833 | 3 | 811.6 | 631.2 | 45.19 | 135.21 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23190902000 |  | 100330168 |  | 6720208B |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | QUEENSWAY | 328 QUEENSWAY DR | 067 | LEX | 2023-05-26 | U930915 | U131552 | 2023-05-25 | 2023-10-05 | 2025-04-30 |  | HMCKUNE | 2023-05-26 | 2023-05-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 27.15 | 11 | 2472.52 | 1719.46 | 348.24 | 303.62 | 101.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23191075900 |  | 100310102 |  | 6716208E | 1635077 |  |  | 565 | EX | GRD 1 ON SERVICE | 2621P | LONGVIEW | 606 LONGVIEW DR | 067 | LEX | 2023-05-30 | U930915 | U130871 | 2023-05-26 | 2023-05-26 | 2023-05-26 |  | RJCRAWF | 2023-05-26 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.1 | 3 | 1592.97 | 827.72 | 542.88 | 126.67 | 95.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960859300 |  | 100249896 |  | 7360248E | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | MCCOMIS | 7711 MCCOMIS DR | 019 | CAT | 2023-05-30 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH DEREK CRAGER | 2023-05-30 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1361.67 | 0 | 0 | 0 | 1361.67 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166668700 |  | 100322637 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 672 BERRY LN | 067 | LEX | 2023-05-30 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-05-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2674.4 | 0 | 0 | 0 | 2674.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166693000 |  | 100272396 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | SHELBY | 826 SHELBY ST | 073 | FRA | 2023-05-30 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-05-30 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 1 | 6638.64 | 505.49 | 0 | 462.56 | 5670.59 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168510500 |  | 100342538 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 301 HOLT AV | 173 | MT | 2023-05-30 | U126604 | U125763 | 2023-02-21 | 2023-12-29 |  |  | WILL FULKS | 2023-05-30 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3472.82 | 0 | 0 | 0 | 3472.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23179497100 |  | 100336288 |  | 6720212I |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | 3RD | 349 E 3RD ST | 067 | LEX | 2023-05-31 | U132743 | BDAWES | 2023-04-06 | 2022-12-22 | 2024-06-30 |  | LSTANFI | 2023-05-30 | 2023-05-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 81.7667 | 11 | 18970.76 | 7396.7 | 0 | 404.86 | 11169.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23186130300 |  | 100313901 |  | 6716212N |  |  |  | 566 | EX | ABN - DEMO/CUSTR PRMT RDY 5-19 | 2621P | CAMDEN | 1311 CAMDEN AV | 067 | LEX | 2023-05-30 | KKINDER | U133234 | 2023-05-04 | 2023-05-12 | 2023-05-28 |  | KKINDER | 2023-05-30 | 2023-05-16 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.8 | 3 | 866.85 | 661.56 | 167.89 | 37.4 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23190284000 |  | 100323663 |  | 6716204C |  |  |  | 565 | EX | REPLACE SERV - D332501 D332502 | 2621P | BROOKHAVEN | 3430 BROOKHAVEN DR | 067 | LEX | 2023-06-02 | U125208 | U125208 | 2023-05-23 |  |  |  | RJCRAWF | 2023-05-30 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.0667 | 2 | 1187.78 | 779.01 | 209.3 | 43.27 | 156.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23190313600 |  | 500070434 |  | 6768172F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KIRKLAND | 523 KIRKLAND AV | 065 | RAV | 2023-05-30 | U930915 | U125208 | 2023-05-23 | 2023-05-26 | 2023-06-13 |  | DENNING | 2023-05-30 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.8333 | 2 | 595.16 | 563.31 | 0 | 31.85 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23190899100 |  | 100325501 |  | 6720208E |  |  |  | 565 | EX | UPGRADE NEWLY REPL SL - 05/30 | 2621P | COOPER | 1238 COOPER DR | 067 | LEX | 2023-05-30 | U128336 | U125208 | 2023-05-25 | 2023-05-30 | 2023-06-15 |  | JOSHUA COX | 2023-05-30 | 2023-05-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 17.95 | 3 | 3982.39 | 1130.41 | 323.99 | 63.91 | 2464.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23191302100 |  | 100337162 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SERV/210266997800/2177145 | 2621P | 5TH | 201 E 5TH ST 1FL | 067 | LEX | 2023-05-31 | U126532 | U136332 | 2023-05-30 | 2023-12-21 |  |  | LESLIE SHARON | 2023-05-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 6209.31 | 0 | 0 | 0 | 6209.31 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 08727612600 |  | 100360467 |  | 6736228G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | LEXINGTON | LEXINGTON RD | 017 | PAR | 2023-05-31 | ASNICHO | RPOLLY | 2008-04-16 | 2022-07-01 | 2023-12-31 |  | ASNICHO | 2023-05-31 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.6833 | 1 | 556.1 | 366.06 | 0 | 190.04 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 11897055300 |  | 100357274 |  | 7240280A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2600B | BROOKSVILLE GERMANTOWN | 4935 BROOKSVILLE GERMANTOWN RD | 023 | GER | 2023-05-31 | SDADAMS | U906631 | 2011-03-22 | 2022-07-01 | 2023-12-31 |  | SDADAMS | 2023-05-31 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 11.3 | 2 | 753.19 | 712.88 | 0 | 40.31 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960859200 |  | 100249897 |  | 7360248E | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | MCCOMIS | 7709 MCCOMIS DR | 019 | CAT | 2023-05-31 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH JERRY NEWSOME | 2023-05-31 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2080.74 | 0 | 0 | 0 | 2080.74 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026269400 |  |  |  | 6756244C | 2394770 | U132257 |  | 560 | CO | PM-DE LINE ILI PH2 DENT2,STPL3 | 5320E |  |  | 181 | CAR | 2023-07-18 |  | U132257 | 2023-03-28 | 2023-12-29 | 2023-12-31 | 2023-05-31 | BJOHNSON | 2023-05-31 |  |  | C | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00560 | 3201032 |  |  | WP2694 |  |  | 100 | 103232230262694 |  | 0 | 198957.22 | 0 | 0 | 0 | 198957.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026301000 |  |  |  | 6712212G | 2301003 | U461383 |  | 557 | EX | EMER-INSTALL 2' OF 4"PMMP MAIN | 2621P | KELSEY | 1071 KELSEY DR | 067 | LEX | 2023-12-14 | U136251 | U461383 | 2023-10-17 | 2023-12-01 | 2023-12-01 | 2023-05-31 | MCRAIG | 2023-05-31 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3010 |  |  | 100 | 055732230263010 |  | 2 | 3269.69 | 1633.33 | 208.12 | 336.99 | 0 | 0 | 0.46 | 1090.79 | 2
KY | KY - WEST | 2621 | 23026301100 |  |  |  | 6712212F | 2301003 | U461383 |  | 558 | EX | EMER-RETIRE 2' OF 4"PAMP MAIN | 2621P | KELSEY | 1071 KELSEY DR | 067 | LEX | 2023-12-14 | U136251 | U461383 | 2023-10-17 | 2023-12-01 | 2023-12-01 | 2023-05-31 | MCRAIG | 2023-05-31 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP3011 |  |  | 100 | 055832230263011 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164756600 |  | 100281633 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | MAPLE | 517 MAPLE ST | 209 | GEO | 2023-05-31 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-05-31 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.2167 | 1 | 3199.3 | 325.03 | 0 | 84.39 | 2789.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164756700 |  | 100457536 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | MAPLE | 518 MAPLE ST | 209 | GEO | 2023-05-31 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-05-31 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2576.99 | 0 | 0 | 0 | 2576.99 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166687200 |  | 100272366 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | CAPITAL HEIGHT | 206 CAPITAL HEIGHT DR | 073 | FRA | 2023-06-01 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-05-31 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3636.96 | 0 | 0 | 0 | 3636.96 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168509700 |  | 100342614 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 216 HOLT AV | 173 | MT | 2023-06-01 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-31 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2443.53 | 0 | 0 | 0 | 2443.53 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168510000 |  | 100342612 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 220 HOLT AV | 173 | MT | 2023-06-01 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-05-31 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2815.37 | 0 | 0 | 0 | 2815.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23190341700 |  | 100293734 |  | 6720212A |  |  |  | 565 | EX | REPLACE SERVICE LINE - D310483 | 2621P | KEES | 1127 KEES RD | 067 | LEX | 2023-05-31 | LSTONE | U125208 | 2023-05-23 | 2023-05-23 | 2023-06-08 |  | LSTONE | 2023-05-31 | 2023-05-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.7333 | 3 | 1302.36 | 1103.59 | 0 | 62.37 | 136.4 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23190557700 |  | 100466774 |  | 7328284K |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | KY 7 | 1783 KY 7 | 089 | S S | 2023-06-07 | U132743 | U133234 | 2023-05-24 | 2023-06-07 | 2023-06-23 |  | BMEEK | 2023-05-31 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 20.25 | 3 | 1795.32 | 1250.43 | 31.39 | 513.5 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23191278500 |  | 100254642 |  | 7348264N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | WILLIAMS | 1107 WILLIAMS ST | 089 | FLA | 2023-06-01 | U132743 | U134822 | 2023-05-29 | 2023-05-26 | 2023-05-29 |  | BROBERT | 2023-05-31 | 2023-05-30 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 29.8833 | 6 | 2859.95 | 1857.46 | 254.05 | 665.94 | 82.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23191311600 |  | 100429527 |  | 6688228F |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | MAIN | 920 E MAIN ST | 073 | FRA | 2023-06-01 | U132743 | U131552 | 2023-05-30 | 2023-05-30 |  |  | EFGOINS | 2023-05-31 | 2023-05-30 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 61.9833 | 6 | 4605.22 | 3473.04 | 0 | 847.28 | 284.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23191497300 |  | 100275246 |  | 6684228J | 2074544 |  |  | 565 | EX | REPLACE SL | 2600B | BROADWAY | 415 W BROADWAY ST | 073 | FRA | 2023-05-31 | U461375 | U125765 | 2023-05-31 | 2023-12-29 |  |  | LARRY BROWN | 2023-05-31 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2335.55 | 0 | 0 | 0 | 2335.55 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960865100 |  | 100249891 |  | 7360248F | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | RIVERVIEW | 7848 RIVERVIEW BV | 019 | CAT | 2023-06-01 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH JERRY NEWSOME | 2023-06-01 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3040.76 | 0 | 0 | 0 | 3040.76 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22113714400 |  | 100271266 |  | 6736248C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D247999 | 2621P | ROSE BAY | 76 ROSE BAY LN | 097 | CYN | 2023-06-05 | JTOY | U125208 | 2022-07-01 | 2022-12-29 | 2024-06-30 |  | NRICHIE | 2023-06-01 | 2023-05-25 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 32.6333 | 8 | 5763.48 | 2499.62 | 462.14 | 888.89 | 1912.83 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129008400 |  | 100356740 |  | 7260276D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OAK | 1727 OAK ST | 161 | MAY | 2023-06-01 | SDADAMS | U130722 | 2022-09-05 | 2022-12-30 |  |  | SDADAMS | 2023-06-01 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 15.15 | 3 | 1050.25 | 945.69 | 50.13 | 54.43 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129085200 |  | 500536010 |  | 6724208E | 9719143 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GRAFTONS MILL | 673 GRAFTONS MILL LN | 067 | LEX | 2023-06-02 | U132743 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ABLAKE | 2023-06-01 | 2023-05-15 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.2 | 4 | 1078.34 | 1004.17 | 16.42 | 57.75 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026255400 |  |  |  | 6696212J |  | U461383 |  | 588 | EX | GMB TO CAB CONVERSION | 2600M | TYRONE | 900 TYRONE PK FF | 239 | VER | 2023-06-07 | U123258 | U461383 | 2023-02-03 | 2023-12-29 | 2023-12-31 | 2023-06-01 | BLONE | 2023-06-01 | 2023-05-16 |  | F | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00588 | 3200588 |  |  | WP2554 |  |  | 100 | 058832230262554 | 120.2 | 0 | 9499.75 | 7962.86 | 326.43 | 1210.46 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164756900 |  | 100281644 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | MAPLE | 522 MAPLE ST L | 209 | GEO | 2023-06-01 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-06-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2566.91 | 0 | 0 | 0 | 2566.91 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164757200 |  | 100281638 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | MAPLE | 527 MAPLE ST | 209 | GEO | 2023-06-01 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-06-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1964.83 | 0 | 0 | 0 | 1964.83 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164757300 |  | 100281639 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | MAPLE | 529 MAPLE ST | 209 | GEO | 2023-06-01 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-06-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2570.73 | 0 | 0 | 0 | 2570.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166668600 |  | 100322629 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 669 BERRY LN | 067 | LEX | 2023-06-02 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-06-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2330.4 | 0 | 0 | 0 | 2330.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166687000 |  | 100272368 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | CAPITAL HEIGHT | 202 CAPITAL HEIGHT DR | 073 | FRA | 2023-06-01 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-06-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 2 | 5568.43 | 514.03 | 0 | 442.07 | 4612.33 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166687100 |  | 100272367 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | CAPITAL HEIGHT | 204 CAPITAL HEIGHT DR | 073 | FRA | 2023-06-01 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-06-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3718.1 | 0 | 0 | 0 | 3718.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168509400 |  | 100342615 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 214 HOLT AV | 173 | MT | 2023-06-06 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-01 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3462.71 | 0 | 0 | 0 | 3462.71 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168509600 |  | 100342534 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 215 HOLT AV | 173 | MT | 2023-06-06 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-01 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3058.46 | 0 | 0 | 0 | 3058.46 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23173331200 |  | 100260968 |  | 7352256G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE + | 2621P | 13TH | 2737 13TH ST 5 | 019 | ASH | 2023-06-01 | BROBERT | U130868 | 2023-03-11 | 2023-08-11 | 2023-08-13 |  | BROBERT | 2023-06-01 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 6.4333 | 3 | 580.61 | 411.32 | 0 | 169.29 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23173331300 |  | 100260970 |  | 7352256G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE + | 2621P | 13TH | 2733 13TH ST 1 | 019 | ASH | 2023-06-01 | BROBERT | U130868 | 2023-03-11 | 2023-08-11 | 2023-08-13 |  | BROBERT | 2023-06-01 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.3667 | 3 | 122.25 | 86.45 | 0 | 35.8 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23184059700 |  | 500339738 |  | 6688232N | 9402970 |  |  | 566 | EX | ABANDON SL - OFL/IDLE | 2621P | LINDENWOOD | 106 LINDENWOOD DR | 073 | FRA | 2023-06-02 | U125208 | U125208 | 2023-04-27 | 2023-05-02 | 2023-05-18 |  | JMARSHA | 2023-06-01 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 12.8667 | 3 | 1068.62 | 782 | 8.58 | 278.04 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23188293800 |  | 100281156 |  | 6692224F | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE SERVICE | 2623D | SHADY | 93 SHADY LN | 239 | MID | 2023-06-02 | U128410 | AOC SYST | 2023-05-15 | 2023-06-09 | 2023-07-09 |  | CDESPAIN | 2023-06-01 | 2023-05-31 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.13333 | 1 | 1110.9 | 9.02 | 201.82 | 0.52 | 899.54 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23189758100 |  | 100456239 |  | 7340268E |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTREQ | 2621P | WALNUT | 1110 WALNUT ST | 089 | GRE | 2023-06-01 | BMEEK | U125208 | 2023-05-19 | 2023-05-24 | 2023-06-18 |  | BMEEK | 2023-06-01 | 2023-06-01 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 14.6 | 3 | 1324.88 | 913.82 | 35.11 | 375.95 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23190520100 |  | 100323673 |  | 6716204C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332503 | 2621P | BROOKHAVEN | 3419 BROOKHAVEN DR | 067 | LEX | 2023-06-02 | U132743 | U125208 | 2023-05-24 | 2023-05-26 | 2023-06-13 |  | DMARSTO | 2023-06-01 | 2023-05-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.15 | 5 | 851.65 | 742.51 | 0 | 42.04 | 67.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23191497400 |  | 100275262 |  | 6684228F | 2074544 |  |  | 565 | EX | REPLACE SL | 2600B | BROADWAY | 501 W BROADWAY ST | 073 | FRA | 2023-06-01 | U461375 | U125765 | 2023-05-31 | 2023-12-29 |  |  | LARRY BROWN | 2023-06-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2412.2 | 0 | 0 | 0 | 2412.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23191577000 |  | 100334951 |  | 6720212O |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | WYATT | 1720 WYATT PY | 067 | LEX | 2023-06-01 | U930915 | U131552 | 2023-05-31 | 2023-05-31 | 2023-05-31 |  | HMCKUNE | 2023-06-01 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 12.1833 | 2 | 950.83 | 602.75 | 251.79 | 34.69 | 61.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23192077500 |  | 100410334 |  | 6712212G |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | KELSEY | 1071 KELSEY DR | 067 | LEX | 2023-06-01 | DMEDLEY | U131552 | 2023-06-01 | 2023-06-01 |  |  | DMEDLEY | 2023-06-01 | 2023-06-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 3.1 | 2 | 613.16 | 188.45 | 270.24 | 59.87 | 94.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 97310991600 |  | 100450034 |  | 6728208P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | CLEVELAND | 1903 N CLEVELAND RD FG 42 | 067 | LEX | 2023-06-18 | U128711 | TDORTEN | 1997-07-25 | 2022-07-01 | 2023-12-31 |  | MSHARON | 2023-06-01 | 2022-06-14 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.9333 | 4 | 3365.04 | 661.42 | 0 | 46.72 | 2656.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11906396100 |  | 100466799 |  | 6736236 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | CYNTHIANA | CYNTHIANA RD | 017 | PAR | 2023-06-02 | ASNICHO | U906631 | 2011-05-12 | 2022-07-01 | 2023-12-31 |  | ASNICHO | 2023-06-02 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8 | 1 | 786.02 | 537.21 | 0 | 248.81 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960865000 |  | 100249890 |  | 7360248F | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | RIVERVIEW | 7846 RIVERVIEW BV | 019 | CAT | 2023-06-02 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH JERRY NEWSOME | 2023-06-02 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3279.63 | 0 | 0 | 0 | 3279.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026265100 |  |  |  | 6716212D | 2396017 | U122858 |  | 557 | EX | INSTALL 10'-3"PMLP | 2600E | GEORGETOWN | 524 GEORGETOWN ST | 067 | LEX | 2023-07-07 | U133333 | U122858 | 2023-03-06 | 2023-11-22 | 2023-11-30 | 2023-06-01 | LSTANFI | 2023-06-02 | 2023-05-31 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2651 | AMRCB |  | 100 | 055732230262651 | 61.45 | 110 | 15746.7 | 3560.89 | 0 | 230.85 | 9698.91 | 0 | 16.1 | 2239.95 | 10
KY | KY - WEST | 2621 | 23026265200 |  |  |  | 6716212D | 2396017 | U122858 |  | 558 | EX | RETIRE 10'-3" BSLP | 2600E | GEORGETOWN | 524 GEORGETOWN ST | 067 | LEX | 2023-06-19 | U133333 | U122858 | 2023-03-06 | 2023-06-02 | 2023-11-30 | 2023-06-01 | LSTANFI | 2023-06-02 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2652 | AMRCB |  | 100 | 055832230262652 | 2.85 | 0 | 190.67 | 168.05 | 0 | 22.62 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164755000 |  | 100281631 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | GANO | 415 GANO AV | 209 | GEO | 2023-06-02 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-06-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.9333 | 1 | 3487.44 | 435.82 | 0 | 161.76 | 2889.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164757000 |  | 100281643 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | MAPLE | 524 MAPLE ST | 209 | GEO | 2023-06-02 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-06-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2260.33 | 0 | 0 | 0 | 2260.33 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168509300 |  | 100342533 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 211 HOLT AV | 173 | MT | 2023-06-07 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-02 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3426.1 | 0 | 0 | 0 | 3426.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23190864900 |  | 100256400 |  | 7356256B |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTREQ | 2621P | 25TH | 613 25TH ST | 019 | ASH | 2023-06-02 | JROGER1 | U125208 | 2023-05-25 | 2023-05-31 | 2023-06-23 |  | JROGER1 | 2023-06-02 | 2023-06-01 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 19.7167 | 4 | 1277.77 | 1146.3 | 20.27 | 111.2 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23192463000 |  | 100259083 |  | 7356256A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CHESTNUT | 900 CHESTNUT DR | 019 | ASH | 2023-06-02 | MCOLLET | U137248 | 2023-06-02 | 2023-06-02 | 2023-06-02 |  | MCOLLET | 2023-06-02 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 9.8833 | 3 | 2108.56 | 1274.6 | 271.39 | 533.97 | 28.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23192493400 |  | 100323833 |  | 6716208P |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BURKSHIRE | 700 BURKSHIRE DR | 067 | LEX | 2023-06-02 | MSHARON | U137248 | 2023-06-02 | 2023-06-01 | 2023-06-01 |  | MSHARON | 2023-06-02 | 2023-06-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 16.7833 | 3 | 2540.42 | 1558.27 | 825.34 | 89.71 | 67.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026268600 |  |  |  | 6716236D | 2394770 | U132257 |  | 559 | CO | PM-DE LINE ILI PH2 DENT 36 | 5320E |  |  | 209 | GEO | 2023-07-18 |  | U132257 | 2023-03-23 | 2023-12-29 | 2023-12-31 | 2023-06-03 | BJOHNSON | 2023-06-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00559 | 3201033 |  |  | WP2686 |  |  | 100 | 103332230262686 |  | 18 | 1598843.54 | 6843.6 | 32965.81 | 9484.77 | 1071290.47 | 0 | 1368.32 | 476890.57 | 18
KY | KY - EAST | 2631 | 23192501200 |  | 100259025 |  | 7356256A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | 17TH | 711 17TH ST 3 | 019 | ASH | 2023-06-03 | MCOLLET | U130871 | 2023-06-02 | 2023-06-02 | 2023-06-02 |  | MCOLLET | 2023-06-03 | 2023-06-02 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 44.85 | 8 | 7354 | 2866.99 | 429.23 | 1078.32 | 2979.46 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960864900 |  | 100249889 |  | 7360248E | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | RIVERVIEW | 7844 RIVERVIEW BV | 019 | CAT | 2023-06-05 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH DEREK CRAGER | 2023-06-05 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2629.14 | 0 | 0 | 0 | 2629.14 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22113714700 |  | 100288288 |  | 6720212H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311433 | 2600B | DARTMOOR | 657 DARTMOOR DR | 067 | LEX | 2023-06-26 | U128711 | U125208 | 2022-07-01 | 2022-12-29 | 2024-06-30 |  | LSTONE | 2023-06-05 | 2023-06-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.0833 | 4 | 2505.99 | 1230.46 | 453.96 | 99.17 | 722.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22122734500 |  | 100317268 |  | 6716204J | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | MANITOBA | 172 MANITOBA LN | 067 | LEX | 2023-06-05 | ATWILLI | AOC SYST | 2022-08-09 | 2023-02-09 | 2023-12-31 |  | ATWILLI | 2023-06-05 | 2023-05-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.85 | 4 | 1828.66 | 1163.25 | 0 | 571.91 | 93.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129008000 |  | 100355444 |  | 7260276B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CAROLINA | 1241 CAROLINA AV | 161 | MAY | 2023-06-06 | U930915 | U130722 | 2022-09-05 | 2022-12-30 |  |  | SDADAMS | 2023-06-05 | 2023-05-08 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 8.1667 | 3 | 588.59 | 521.62 | 36.94 | 30.03 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129056200 |  | 501145243 |  | 6704216D | 1319374 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OLD FRANKFORT | 3465 OLD FRANKFORT PK FG36 | 239 | VER | 2023-06-06 | U128410 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CDESPAIN | 2023-06-05 | 2023-03-06 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 54.0833 | 15 | 4282.91 | 3578.61 | 0 | 210.8 | 493.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129079100 |  | 500992098 |  | 6716204E | 0675079 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ROJAY | 135 ROJAY DR | 067 | LEX | 2023-06-22 | U135005 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ABLAKE | 2023-06-05 | 2023-06-02 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 19.2 | 5 | 1264.67 | 1195.85 | 0 | 68.82 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026269300 |  |  |  | 6716236D | 2394770 | U132257 |  | 560 | CO | PM-DE LINE ILI PH2 DENT 36 ABD | 5320E |  |  | 209 | GEO | 2023-07-18 |  | U132257 | 2023-03-28 | 2023-12-29 | 2023-12-31 | 2023-06-05 | BJOHNSON | 2023-06-05 |  |  | C | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00560 | 3201032 |  |  | WP2693 |  |  | 100 | 103232230262693 | 0.5 | 0 | 279860.8 | 116126.88 | 0 | 55273.63 | 108460.29 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164756800 |  | 100281634 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | MAPLE | 519 MAPLE ST | 209 | GEO | 2023-06-05 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-06-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.3667 | 1 | 2528.1 | 400.08 | 0 | 148.49 | 1979.53 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164768700 |  | 100281636 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | MAPLE | 523 MAPLE ST | 209 | GEO | 2023-06-05 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-06-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2823.88 | 0 | 0 | 0 | 2823.88 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168509100 |  | 100342618 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 208 HOLT AV | 173 | MT | 2023-06-06 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-05 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3101.49 | 0 | 0 | 0 | 3101.49 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168509200 |  | 100342616 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 210 HOLT AV | 173 | MT | 2023-06-06 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-05 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2737.17 | 0 | 0 | 0 | 2737.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23177480300 |  | 100340497 |  | 6724212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D310479 | 2621P | ATLANTA | 1607 ATLANTA DR | 067 | LEX | 2023-06-07 | U130722 | U125208 | 2023-03-31 | 2023-09-29 | 2025-03-31 |  | LSTANFI | 2023-06-05 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 29.2333 | 4 | 5323.24 | 1717.13 | 0 | 203.95 | 3402.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23184086900 |  | 100336923 |  | 6720212E | 2177145 |  |  | 566 | EX | RETIRE S/L WITH 21-0269978-00 | 2600B | M L KING | 423 M L KING BV 1F | 067 | LEX | 2023-06-05 | U126532 | U461383 | 2023-04-27 | 2023-11-01 | 2023-11-01 |  | LESLIE SHARON | 2023-06-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 535.81 | 0 | 0 | 0 | 535.81 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23189725300 |  | 501085389 |  | 6708204O | 2293073 |  |  | 565 | EX | NBT TIEIN - UPG MTR/SL 100' 2" | 2600V | KEENE MANOR | 107 KEENE MANOR WY | 113 | NIC | 2023-06-09 | KKINDER | U125208 | 2023-05-19 | 2023-05-18 | 2023-06-15 |  | KKINDER | 2023-06-05 | 2023-06-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 30.2667 | 5 | 2356.78 | 2008.56 | 156.74 | 115.58 | 75.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23192135200 |  | 100259046 |  | 7356256A |  |  |  | 565 | EX | REPLACE SERVICE LINE - D258096 | 2621P | LEXINGTON | 1509 LEXINGTON AV | 019 | ASH | 2023-06-05 | BROBERT | U125208 | 2023-06-01 | 2023-06-01 | 2023-06-01 |  | BROBERT | 2023-06-05 | 2023-06-02 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 40.2 | 5 | 6983.19 | 2558.43 | 271.37 | 1197.87 | 2955.52 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23192643900 |  | 100247352 |  | 7352256L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D258099 | 2621P | JOEL | 2507 JOEL ST | 019 | ASH | 2023-06-06 | UIPBOT21 | U137585 | 2023-06-02 | 2023-06-02 | 2023-06-02 |  | BROBERT | 2023-06-05 | 2023-06-02 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 6.55 | 2 | 1087.97 | 426.29 | 191.63 | 362.25 | 107.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23192741500 |  | 100336924 |  | 6720212E | 2177145 |  |  | 566 | EX | ABANDN SL/21026997800 | 2600B | M L KING | 415 N M L KING BV | 067 | LEX | 2023-06-05 | U126532 | U125763 | 2023-06-05 | 2023-12-29 |  |  | LESLIE SHARON | 2023-06-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 535.81 | 0 | 0 | 0 | 535.81 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 08727660700 |  | 100437247 |  | 6744208F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | *NEED ADDRESS*ROCKWELL | *NEED ADDRESS*ROCKWELL RD | 049 | WIN | 2023-06-06 | ASNICHO | RPOLLY | 2008-04-16 | 2022-07-01 | 2023-12-31 |  | ASNICHO | 2023-06-06 | 2022-11-17 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.7 | 2 | 250.57 | 171.25 | 0 | 79.32 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960864800 |  | 100249888 |  | 7360248E | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | RIVERVIEW | 7842 RIVERVIEW BV | 019 | CAT | 2023-06-07 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH DEREK CRAGER | 2023-06-06 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3505.23 | 0 | 0 | 0 | 3505.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22122735100 |  | 100405358 |  | 6716204J | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | MANITOBA | 180 MANITOBA LN | 067 | LEX | 2023-06-06 | ATWILLI | AOC SYST | 2022-08-09 | 2023-02-09 | 2023-12-31 |  | ATWILLI | 2023-06-06 | 2023-06-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.8667 | 4 | 1273.86 | 674.83 | 187.96 | 319.77 | 91.3 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129034800 |  | 501146904 |  | 7344168G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LAKE | 3243 S LAKE DR | 071 | PRE | 2023-06-06 | BPREECE | U130722 | 2022-09-05 | 2022-12-30 |  |  | BPREECE | 2023-06-06 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 4.4167 | 1 | 318.48 | 301.15 | 0 | 17.33 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026278100 |  |  |  | 7348256P |  | U128885 |  | 588 | EX | RETIRE REG FAC | 2631M | ROBERTS | 5726 ROBERTS DR | 019 | ASH | 2023-06-08 | U123258 | U128885 | 2023-06-06 | 2023-06-30 |  | 2023-06-06 | RWILLIAMS | 2023-06-06 |  |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00588 | 3200588 |  |  | WP2781 |  |  | 100 | 058832230262781 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164760500 |  | 100281679 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 500 PAYNE AV | 209 | GEO | 2023-06-06 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-06-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2023.63 | 0 | 0 | 0 | 2023.63 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164760600 |  | 100281680 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 504 PAYNE AV | 209 | GEO | 2023-06-06 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-06-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2028.53 | 0 | 0 | 0 | 2028.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165280700 |  | 100336875 |  | 6720212E | 2177145 |  |  | 566 | EX | ABANDN SL/21026997800 | 2600B | JOHNSON | 425 JOHNSON AV | 067 | LEX | 2023-06-06 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-06-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1198.24 | 0 | 0 | 0 | 1198.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165281200 |  | 100336872 |  | 6720212E | 2177145 |  |  | 566 | EX | ABANDN SL/21026997800 | 2600B | JOHNSON | 459 JOHNSON AV | 067 | LEX | 2023-06-06 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-06-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1198.24 | 0 | 0 | 0 | 1198.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166669300 |  | 100322626 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 681 BERRY LN | 067 | LEX | 2023-06-09 | U127414 | U125763 | 2023-02-14 | 2023-12-29 |  |  | ED FOX | 2023-06-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2551.34 | 0 | 0 | 0 | 2551.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166672500 |  | 100322681 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 664 PROVIDENCE RD | 067 | LEX | 2023-06-09 | U127414 | U125763 | 2023-02-14 | 2023-12-29 |  |  | ED FOX | 2023-06-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1843.86 | 0 | 0 | 0 | 1843.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166673500 |  | 100322686 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 684 PROVIDENCE RD | 067 | LEX | 2023-06-06 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-06-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2536.34 | 0 | 0 | 0 | 2536.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166673700 |  | 100322688 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 688 PROVIDENCE RD | 067 | LEX | 2023-06-06 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-06-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 980.45 | 0 | 0 | 0 | 980.45 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166687400 |  | 100272365 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | CAPITAL HEIGHT | 210 CAPITAL HEIGHT DR | 073 | FRA | 2023-06-06 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-06-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 1 | 4508.07 | 514.03 | 0 | 442.07 | 3551.97 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168509000 |  | 100342531 |  | 7240216M | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 207 HOLT AV | 173 | MT | 2023-06-07 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-06 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4222.49 | 0 | 0 | 0 | 4222.49 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23175640600 |  | 100280664 |  | 6688228E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BEAUMONT | 137 BEAUMONT AV | 073 | FRA | 2023-06-08 | U135005 | U125208 | 2023-03-22 | 2023-03-24 | 2023-04-12 |  | EFGOINS | 2023-06-06 | 2023-05-30 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 15.25 | 4 | 1204.66 | 1027.62 | 118.2 | 58.84 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23176980600 |  | 100356489 |  | 7256280K | 2286937 |  |  | 565 | EX | RPLC SL/22026171800 | 2600B | BUFFALO TRACE | 650 BUFFALO TRACE | 161 | MAY | 2023-06-06 | U126286 | U125763 | 2023-03-29 | 2023-12-29 |  |  | TYLER ALLISON | 2023-06-06 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 3210.85 | 0 | 0 | 0 | 3210.85 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23178700500 |  | 100333822 |  | 6720212J | 1635077 |  |  | 565 | EX | AOC ENCROACHMENT | 2621P | DELAWARE | 935 DELAWARE AV | 067 | LEX | 2023-06-06 | LSTONE | U125208 | 2023-04-03 | 2023-04-28 | 2023-05-31 |  | LSTONE | 2023-06-06 | 2023-04-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 33.2167 | 9 | 2709.84 | 1895.99 | 371.36 | 377.59 | 64.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23181741500 |  | 100316148 |  | 6716208B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311293 | 2621P | NORWAY | 217 NORWAY ST | 067 | LEX | 2023-06-06 | U128336 | U125208 | 2023-04-17 | 2023-10-13 | 2025-04-30 |  | JOSHUA COX | 2023-06-06 | 2023-04-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.05 | 6 | 1935.13 | 1390.87 | 354.74 | 89.42 | 100.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23192712100 |  | 100252558 |  | 7348264P |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | POWELL | 501 POWELL LN | 089 | FLA | 2023-06-08 | U135005 | U135005 | 2023-06-05 | 2023-06-02 | 2023-06-03 |  | RECUMP | 2023-06-06 | 2023-06-06 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 10.8667 | 2 | 977.87 | 682.77 | 171.89 | 119.91 | 3.3 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23192749100 |  | 100257527 |  | 7356256E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D244396 | 2621P | PROSPECT | 1907 PROSPECT AV | 019 | ASH | 2023-06-06 | MCOLLET | U125208 | 2023-06-05 | 2023-06-05 | 2023-06-05 |  | MCOLLET | 2023-06-06 | 2023-06-06 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 33.5667 | 5 | 5717.15 | 2420.98 | 218.6 | 1102.85 | 1974.72 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23192753900 |  | 100350074 |  | 6744204D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CRESCENT | 364 CRESCENT AV | 049 | WIN | 2023-06-06 | NRICHIE | U137585 | 2023-06-05 | 2023-06-05 | 2023-06-05 |  | NRICHIE | 2023-06-06 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 16 | 2 | 1843.9 | 1078.5 | 201.74 | 474.56 | 89.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23193004500 |  | 100336925 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | M L KING | 409 N M L KING BV | 067 | LEX | 2023-06-06 | U126532 | U125763 | 2023-06-06 | 2023-12-29 |  |  | LESLIE SHARON | 2023-06-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 5504.17 | 0 | 0 | 0 | 5504.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23193011000 |  | 100329373 |  | 6720208G |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | SAINT ANN | 177 SAINT ANN DR | 067 | LEX | 2023-06-08 | U135005 | U131552 | 2023-06-06 | 2023-06-06 | 2023-06-06 |  | DMARSTO | 2023-06-06 | 2023-06-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.8167 | 3 | 1430.44 | 1019.59 | 254.28 | 58.67 | 97.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23194744300 |  | 500070003 |  | 6716208D |  |  |  | 566 | EX | ABANDON SL | 2621P | PROVIDENCE | 664 PROVIDENCE RD RR | 067 | LEX | 2023-06-14 | U127414 | MDULANE | 2023-06-14 | 2023-06-14 |  |  | ED FOX | 2023-06-06 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - CENTRAL | 2632 | 21026127000 |  |  |  | 7256280N | 2180423 | U122858 |  | 557 | EX | INSTALL 8021'-2"&4" PMIP | 2600B | CIRCLE | CIRCLE | 161 | MAY | 2023-07-12 | U128132 | U122858 | 2021-06-08 | 2023-08-29 | 2023-12-31 | 2023-03-16 | TYLER ALLISON | 2023-06-07 | 2023-01-03 |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00557 | 3200557 |  |  | WP1270 | AMRCB |  | 100 | 055732210261270 | 943.6667 | 1012500 | 2281682.81 | 64154.59 | 1213386.14 | 6424.03 | 569034.71 | 0 | 5890.54 | 422792.8 | 8100
KY | KY - CENTRAL | 2632 | 21026127100 |  |  |  | 7256280N | 2180423 | U122858 |  | 558 | EX | RETIRE 9400'-2"&4" BS&CS | 2600B | CIRCLE | CIRCLE | 161 | MAY | 2023-07-12 | U128132 | U122858 | 2021-06-08 | 2023-12-29 | 2023-12-31 | 2023-06-07 | TYLER ALLISON | 2023-06-07 | 2023-04-28 |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00558 | 3200558 |  |  | WP1271 | AMRCB |  | 100 | 055832210261271 | 0.033333 | 0 | 1334.61 | 350.46 | 0 | 19.49 | 964.66 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960864600 |  | 100249887 |  | 7360248E | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | RIVERVIEW | 7820 RIVERVIEW BV | 019 | CAT | 2023-06-07 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH DEREK CRAGER | 2023-06-07 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3929.55 | 0 | 0 | 0 | 3929.55 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164760700 |  | 100281681 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 508 PAYNE AV | 209 | GEO | 2023-06-07 | U126602 | U125763 | 2023-02-03 | 2023-12-29 |  |  | DEREK PAYTON | 2023-06-07 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2417.1 | 0 | 0 | 0 | 2417.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23176980700 |  | 100356488 |  | 7256280K | 2286937 |  |  | 565 | EX | RPLC SL/22026171800 | 2600B | BUFFALO TRACE | 651 BUFFALO TRACE | 161 | MAY | 2023-06-07 | U126286 | U125763 | 2023-03-29 | 2023-12-29 |  |  | TYLER ALLISON | 2023-06-07 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 3326.64 | 0 | 0 | 0 | 3326.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23192215700 |  | 100335303 |  | 6720212L | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE SERVICE | 2621D | ASHTON | 132 ASHTON DR | 067 | LEX | 2023-06-08 | U135005 | AOC SYST | 2023-06-01 | 2023-06-30 | 2023-07-30 |  | LSTANFI | 2023-06-07 | 2023-06-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 35.9667 | 6 | 9574.12 | 2328.34 | 265.97 | 133.98 | 6845.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23192716900 |  | 100330771 |  | 6720212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D304068 | 2621P | SHERMAN | 367 SHERMAN AV | 067 | LEX | 2023-06-08 | U135005 | U125208 | 2023-06-05 | 2023-06-05 | 2023-06-05 |  | HMCKUNE | 2023-06-07 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 33.4 | 5 | 2101.58 | 1788.18 | 173.1 | 102.9 | 37.4 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23193360600 |  | 501190498 |  | 7356256A | 1636635 |  |  | 566 | EX | ABANDON SL | 2621P | CENTRAL | 1701< CENTRAL AV | 019 | ASH | 2023-06-07 | MDULANE | MDULANE | 2023-06-07 | 2023-06-30 | 2023-06-30 |  | OFFICE/MDULANE | 2023-06-07 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1
KY | KY - WEST | 2621 | 23193367300 |  | 100304306 |  | 6712208D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LARKSPUR | 2105 LARKSPUR DR | 067 | LEX | 2023-06-22 | U135005 | U131552 | 2023-06-07 | 2023-06-02 | 2023-06-03 |  | HMCKUNE | 2023-06-07 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 1.6667 | 5 | 704.12 | 141.04 | 418.59 | 57.59 | 86.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21883323100 |  | 500691909 |  | 7240280F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | WATER | 79 WATER ST | 023 | GER | 2023-06-09 | U135005 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | SDADAMS | 2023-06-08 | 2023-05-31 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 11.2667 | 5 | 1088.81 | 715.55 | 50.13 | 323.13 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960864400 |  | 100451116 |  | 7360248E | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | RIVERVIEW | 7741 RIVERVIEW BV | 019 | CAT | 2023-06-09 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH DEREK CRAGER | 2023-06-08 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 4621.16 | 0 | 0 | 0 | 4621.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026219400 |  |  |  | 6716212P | 2290930 | U461383 |  | 557 | EX | INSTALL 380' OF 4"PMMP MAIN | 2600B | ROSE | 452 ROSE ST | 067 | LEX | 2023-06-22 | U124014 | U461383 | 2022-08-19 | 2023-12-07 | 2023-12-31 | 2023-06-02 | BPULLIAM/FISHEL | 2023-06-08 | 2023-05-17 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2194 | AMRCB |  | 100 | 055732220262194 | 145.8667 | 9386 | 171665.76 | 9753.79 | 7400.7 | 12229.48 | 116429.25 | 0 | 636.29 | 25216.25 | 494
KY | KY - WEST | 2621 | 22026219500 |  |  |  | 6716212P | 2290930 | U461383 |  | 558 | EX | RETIRE 380' OF 4"BSMP MAIN | 2600B | ROSE | 452 ROSE ST | 067 | LEX | 2023-06-22 | U124014 | U461383 | 2022-08-19 | 2023-12-29 | 2023-12-31 | 2023-06-08 | BPULLIAM/FISHEL | 2023-06-08 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2195 | AMRCB |  | 100 | 055832220262195 |  | 0 | 91.2 | 0 | 0 | 0 | 91.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22123020800 |  | 100317863 |  | 6716204G | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | YALE | 414 YALE DR | 067 | LEX | 2023-06-09 | U135005 | AOC SYST | 2022-08-10 | 2023-02-10 | 2023-12-31 |  | LSTANFI | 2023-06-08 | 2023-04-21 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 16.3 | 3 | 1952.66 | 1076.63 | 598.62 | 167.41 | 110 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22123022600 |  | 100317871 |  | 6716204G | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | YALE | 433 YALE DR | 067 | LEX | 2023-06-09 | U930915 | AOC SYST | 2022-08-10 | 2023-02-10 | 2023-12-31 |  | ABLAKE | 2023-06-08 | 2023-04-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 20.2167 | 4 | 2082.1 | 1289.98 | 293.1 | 73.85 | 425.17 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129068100 |  | 100260969 |  | 7352256G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE * | 2621P | 13TH | 2735 13TH ST 2 | 019 | ASH | 2023-06-08 | RECUMP | U130722 | 2022-09-05 | 2022-12-30 | 2023-08-13 |  | RECUMP | 2023-06-08 | 2023-06-07 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 9.5333 | 4 | 708.29 | 605.08 | 0 | 103.21 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129080900 |  | 100290797 |  | 6720212B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FAIRLAWN | 103 FAIRLAWN AV | 067 | LEX | 2023-06-08 | TROE | U130722 | 2022-09-05 | 2022-12-30 |  |  | TROE | 2023-06-08 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.85 | 2 | 1092.83 | 998.44 | 36.94 | 57.45 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026267800 |  | 500518639 |  | 6720204A | 2396311 | U461383 |  | 555 | EX | INSTALL 580' OF 2"PMMP MAIN | 2600B | PEPPERHILL | 3381 PEPPERHILL RD | 067 | LEX | 2023-06-09 | U128132 | U461383 | 2023-03-20 | 2023-06-08 | 2023-06-19 | 2023-06-08 | R.HUMPHREYS | 2023-06-08 | 2023-05-30 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2678 |  |  | 100 | 055532230262678 | 56 | 4690 | 35753.76 | 3519.9 | 2274.68 | 1190.11 | 23665.75 | 0 | 68.26 | 5035.06 | 670
KY | KY - WEST | 2621 | 23026273900 |  |  |  | 6724208J | 2397449 | U461383 |  | 583 | EX | INSTALL 441 REG (WEST RUN) | 2621M | OLD TODDS | 3005 OLD TODDS RD | 067 | LEX | 2023-07-10 | U121330 | U461383 | 2023-05-05 | 2023-11-01 | 2023-11-01 | 2023-06-08 | ALVARO PARKS | 2023-06-08 | 2023-05-18 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00583 | 3200583 |  |  | WP2739 |  |  | 100 | 058332230262739 | 36.5167 | 22 | 4130.38 | 2371.45 | 0 | 1169.99 | 0 | 0 | 16.36 | 572.58
KY | KY - WEST | 2621 | 23026274000 |  |  |  | 6724208J |  | U461383 |  | 584 | EX | RETIRE 461 REGS (WEST RUN) | 2621M | OLD TODDS | 3005 OLD TODDS RD | 067 | LEX | 2023-06-28 | U123258 | U461383 | 2023-05-05 | 2023-11-01 | 2023-11-01 | 2023-06-08 | ALVARO PARKS | 2023-06-08 |  |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00584 | 3200584 |  |  | WP2740 |  |  | 100 | 058432230262740 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026277900 |  |  |  | 6716208E | 2397985 | U122858 |  | 557 | EX | EMER - INSTALL 69'-6" PMLP | 2621P | WINDSOR | WINDSOR | 067 | LEX | 2023-11-22 | U136251 | U122858 | 2023-06-02 | 2024-08-31 | 2025-04-27 | 2023-06-08 | KKINDER | 2023-06-08 | 2023-06-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2779 | AMRCB |  | 100 | 055732230262779 | 102.1333 | 900 | 31362.92 | 9317.88 | 4995.83 | 720.33 | 11478.56 | 0 | 50.02 | 4800.3 | 75
KY | KY - WEST | 2621 | 23026278000 |  |  |  | 6716208E | 2397985 | U122858 |  | 558 | EX | EMER - RETIRE 69'-6" BSLP | 2621P | WINDSOR | WINDSOR | 067 | LEX | 2023-08-30 | U136251 | U122858 | 2023-06-02 | 2024-08-31 | 2025-04-27 | 2023-06-08 | KKINDER | 2023-06-08 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2780 | AMRCB |  | 100 | 055832230262780 | 1.7667 | 0 | 124.77 | 117.99 | 0 | 6.78 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164757100 |  | 100281637 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | MAPLE | 525 MAPLE ST | 209 | GEO | 2023-06-08 | U126602 | U125763 | 2023-02-03 | 2023-12-29 |  |  | DEREK PAYTON | 2023-06-08 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3218.99 | 0 | 0 | 0 | 3218.99 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164761300 |  | 100281685 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 524 PAYNE AV | 209 | GEO | 2023-06-08 | U126602 | U125763 | 2023-02-03 | 2023-12-29 |  |  | DEREK PAYTON | 2023-06-08 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2726.6 | 0 | 0 | 0 | 2726.6 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164761400 |  | 100281686 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 528 PAYNE AV | 209 | GEO | 2023-06-08 | U126602 | U125763 | 2023-02-03 | 2023-12-29 |  |  | DEREK PAYTON | 2023-06-08 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2584.5 | 0 | 0 | 0 | 2584.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166693100 |  | 100272395 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | SHELBY | 828 SHELBY ST | 073 | FRA | 2023-06-08 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-06-08 | 2023-06-07 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 1 | 7474.43 | 514.03 | 0 | 442.07 | 6518.33 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23176980500 |  | 100356490 |  | 7256280K | 2286937 |  |  | 565 | EX | RPLC SL/22026171800 | 2600B | BUFFALO TRACE | 637 BUFFALO TRACE | 161 | MAY | 2023-06-08 | U126286 | U125763 | 2023-03-29 | 2023-12-29 |  |  | TYLER ALLISON | 2023-06-08 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 3183.7 | 0 | 0 | 0 | 3183.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23176980900 |  | 100356491 |  | 7256280K | 2286937 |  |  | 565 | EX | RPLC SL/22026171800 | 2600B | BUFFALO TRACE | 671 BUFFALO TRACE | 161 | MAY | 2023-06-08 | U126286 | U125763 | 2023-03-29 | 2023-12-29 |  |  | TYLER ALLISON | 2023-06-08 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2775.86 | 0 | 0 | 0 | 2775.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23187294800 |  | 100323205 |  | 6716208P | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE SERVICE | 2621D | HILDEEN | 763 HILDEEN RD | 067 | LEX | 2023-06-09 | U135005 | AOC SYST | 2023-05-10 | 2023-06-07 | 2023-07-07 |  | DMARSTO | 2023-06-08 | 2023-06-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.5 | 5 | 1776.9 | 1174.06 | 461.59 | 67.55 | 73.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23192766300 |  | 100323861 |  | 6716208P | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | OVERBROOK | 3365 OVERBROOK DR | 067 | LEX | 2023-06-08 | U930915 | AOC SYST | 2023-06-05 | 2023-06-08 | 2023-06-26 |  | J ENSMINGER | 2023-06-08 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 | KYACA |  | 100 | 056532B26210021 | 13.8 | 3 | 1400.89 | 893.37 | 369.22 | 51.4 | 86.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23193070100 |  | 100317231 |  | 6716204I |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | MANITOBA | 116 MANITOBA LN | 067 | LEX | 2023-06-08 | WISHII | U131552 | 2023-06-06 | 2023-06-06 |  |  | WISHII | 2023-06-08 | 2023-06-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 9.3 | 2 | 1092.13 | 527.98 | 201.65 | 262.4 | 100.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23193501300 |  | 100246514 |  | 7356256I |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | RIDGEWAY | 3449 RIDGEWAY DR | 019 | ASH | 2023-06-09 | U135005 | U131552 | 2023-06-07 | 2023-06-07 | 2023-06-07 |  | JCYRUS | 2023-06-08 | 2023-06-07 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 4.3833 | 3 | 1549.18 | 303.73 | 119.61 | 40.64 | 1085.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23193700200 |  | 100466926 |  | 6748204J |  |  |  | 565 | EX | REPLACE AFTER DAMAGE | 2621P | MUDDY CREEK | 2466 MUDDY CREEK RD | 049 | WIN | 2023-06-08 | NRICHIE | JTOY | 2023-06-08 | 2023-06-07 |  |  | NRICHIE | 2023-06-08 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 5.1667 | 3 | 727.35 | 346.67 | 206.2 | 36.98 | 137.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23193764100 |  | 100330415 |  | 6720212O |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | KINGSWOOD | 415 KINGSWOOD DR | 067 | LEX | 2023-06-09 | U135005 | U131552 | 2023-06-08 | 2023-06-08 |  |  | HMCKUNE | 2023-06-08 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 0.3 | 1 | 2139.88 | 1841.4 | 154.75 | 103.03 | 40.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 99406712600 |  | 100330606 |  | 6732216P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | HALEY | HALEY RD | 067 | LEX | 2023-06-19 | U126308 | KEMBERT | 1999-10-04 | 2023-05-05 | 2023-12-31 |  | J ENSMINGER | 2023-06-08 | 2023-05-05 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.6333 | 5 | 967.37 | 914.28 | 0 | 53.09 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 00451568400 |  | 500146257 |  | 6716204L | 1315787 |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | TATES CREEK | 4301 TATES CREEK RD GRNHSE | 067 | LEX | 2023-06-09 | U126308 | DMCCULL | 2000-11-09 | 2049-12-31 |  |  | J ENSMINGER | 2023-06-09 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.5167 | 2 | 254.99 | 241.11 | 0 | 13.88 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 02513004100 |  | 100445452 |  | 6716204L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 * | 2621P | TATES CREEK | 4301 TATES CREEK RD TRLR | 067 | LEX | 2023-06-09 | U126308 | DMCCULL | 2002-07-29 | 2022-07-01 | 2023-12-31 |  | J ENSMINGER | 2023-06-09 | 2022-06-20 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 37.6 | 9 | 4799.91 | 2309.56 | 0 | 435.65 | 2054.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960864500 |  | 100249886 |  | 7360248E | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | RIVERVIEW | 7800 RIVERVIEW BV | 019 | CAT | 2023-06-09 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH DEREK CRAGER | 2023-06-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2336.43 | 0 | 0 | 0 | 2336.43 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22111904700 |  | 100311514 |  | 6712204D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | BOSTON | 3466 BOSTON RD | 067 | LEX | 2023-06-09 | LSTONE | AOC SYST | 2022-06-22 | 2022-12-22 | 2023-12-31 |  | LSTONE | 2023-06-09 | 2023-06-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 22.5167 | 3 | 1381.26 | 1249.94 | 0 | 71.92 | 59.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22122731600 |  | 100317235 |  | 6716204J | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | MANITOBA | 140 MANITOBA LN | 067 | LEX | 2023-06-09 | WISHII | AOC SYST | 2022-08-09 | 2023-02-09 | 2023-12-31 |  | WISHII | 2023-06-09 | 2023-05-12 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.7167 | 6 | 1719.87 | 1172.04 | 206.61 | 299.42 | 41.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166689700 |  | 500154818 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | OWSLEY | 310 OWSLEY AV | 073 | FRA | 2023-06-09 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-06-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 1 | 4147.35 | 514.03 | 0 | 442.07 | 3191.25 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168135900 |  | 100468455 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WILKINSON | 209 WILKINSON ST A | 073 | FRA | 2023-06-09 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-06-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2297.05 | 0 | 0 | 0 | 2297.05 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168504300 |  | 100342595 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ANTWERP | 194 ANTWERP AV | 173 | MT | 2023-06-12 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-09 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3919.31 | 0 | 0 | 0 | 3919.31 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23176981100 |  | 100356485 |  | 7256280K | 2286937 |  |  | 565 | EX | RPLC SL/22026171800 | 2600B | HILLCREST | 654 HILLCREST RD | 161 | MAY | 2023-06-09 | U126286 | U125763 | 2023-03-29 | 2023-12-29 |  |  | TYLER ALLISON | 2023-06-09 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2490.72 | 0 | 0 | 0 | 2490.72 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23193705100 |  | 100468456 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WILKINSON | 207 WILKINSON ST B | 073 | FRA | 2023-06-09 | U461375 | U125763 | 2023-06-08 | 2023-12-29 |  |  | LARRY BROWN | 2023-06-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2206.43 | 0 | 0 | 0 | 2206.43 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23193705300 |  | 100468568 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WILKINSON | 205 WILKINSON ST C | 073 | FRA | 2023-06-09 | U461375 | U125763 | 2023-06-08 | 2023-12-29 |  |  | LARRY BROWN | 2023-06-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2306.83 | 0 | 0 | 0 | 2306.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23193716200 |  | 500185883 |  | 6720204A | 2396311 |  |  | 565 | EX | RPLC SL/23026267800 | 2600B | TISHOFF | 1233 TISHOFF DR | 067 | LEX | 2023-06-09 | U461309 | U125763 | 2023-06-08 | 2023-12-29 |  |  | R.HUMPHREYS | 2023-06-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 8 | 1 | 2389.37 | 502.31 | 271.52 | 186.22 | 1429.32 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23193759400 |  | 100346825 |  | 6696212O |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HILLCREST | 338 HILLCREST DR | 239 | VER | 2023-06-12 | U128410 | U131552 | 2023-06-08 | 2023-06-08 | 2023-06-08 |  | CDESPAIN | 2023-06-09 | 2023-06-08 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 36 | 5 | 3907.65 | 3015.89 | 353.67 | 496.29 | 41.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23193761200 |  | 100330385 |  | 6720212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | KINGSWOOD | 430 KINGSWOOD DR | 067 | LEX | 2023-06-12 | U135005 | U135005 | 2023-06-08 | 2023-06-08 | 2023-06-08 |  | HMCKUNE | 2023-06-09 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 22.0667 | 3 | 1537.01 | 1215.47 | 158.08 | 69.96 | 93.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22115510700 |  | 100445113 |  | 6716204H | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | WINDGATE | 3617 WINDGATE WY | 067 | LEX | 2023-06-12 | WISHII | AOC SYST | 2022-07-12 | 2023-01-12 | 2023-12-31 |  | WISHII | 2023-06-12 | 2023-06-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.45 | 3 | 1327.96 | 819.6 | 0 | 430.26 | 78.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22137500800 |  | 100291832 |  | 6720216G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FOXBOROUGH | 1722 FOXBOROUGH CR | 067 | LEX | 2023-06-13 | U135005 | U130722 | 2022-10-07 | 2022-12-30 |  |  | ABLAKE | 2023-06-12 | 2023-05-19 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 22.4167 | 10 | 1698.37 | 1388.01 | 230.64 | 79.72 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22988893500 |  | 100350054 |  | 6744204D |  |  |  | 566 | EX | ABANDON SL- I/I/LGCY | 2621P | BELMONT | 12 BELMONT AV | 049 | WIN | 2023-06-12 | WHIMES | U134723 | 2022-03-28 | 2022-12-30 |  |  | WHIMES | 2023-06-12 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 11.4667 | 2 | 1014.72 | 771.45 | 15.02 | 228.25 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026299800 |  | 500253895 |  | 7356256B | 2394672 | U461383 |  | 566 | EX | PAPER ONLY SL RETIRE | 2600E | MONTGOMERY | 2236 MONTGOMERY AV | 019 | ASH | 2023-10-18 | U128132 | U461383 | 2023-10-10 | 2023-12-01 | 2023-12-01 | 2023-06-12 | DAVID SKAGGS | 2023-06-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP2998 |  |  | 100 | 056632230262998 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164768800 |  | 100281641 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | MAPLE | 533 MAPLE ST | 209 | GEO | 2023-06-14 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-06-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2053.03 | 0 | 0 | 0 | 2053.03 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166690000 |  | 100272364 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | OWSLEY | 400 OWSLEY AV | 073 | FRA | 2023-06-12 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-06-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3640.56 | 0 | 0 | 0 | 3640.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168504400 |  | 100342594 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ANTWERP | 196 ANTWERP AV | 173 | MT | 2023-06-16 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-12 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3224.23 | 0 | 0 | 0 | 3224.23 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168504500 |  | 100342596 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ANTWERP | 197 ANTWERP AV | 173 | MT | 2023-06-16 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-12 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2816.49 | 0 | 0 | 0 | 2816.49 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23176981300 |  | 100356487 |  | 7256280K | 2286937 |  |  | 565 | EX | RPLC SL/22026171800 | 2600B | HILLCREST | 662 HILLCREST RD | 161 | MAY | 2023-06-12 | U126286 | U125763 | 2023-03-29 | 2023-12-29 |  |  | TYLER ALLISON | 2023-06-12 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2746.56 | 0 | 0 | 0 | 2746.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179192700 |  | 501196203 |  | 7352256C | 2075305 |  |  | 565 | EX | RPLC SL/20026983500 | 2600B | BARTLETT | 516 BARTLETT ST | 019 | ASH | 2023-06-12 | U125566 | U125763 | 2023-04-05 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-06-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2336.43 | 0 | 0 | 0 | 2336.43 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23179492000 |  | 100453069 |  | 6728208B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333595 | 2621P | CAICOS | 3508 CAICOS CT | 067 | LEX | 2023-06-13 | U135005 | U125208 | 2023-04-06 | 2023-10-05 | 2025-04-30 |  | LSTANFI | 2023-06-12 | 2023-05-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.8833 | 7 | 2090.61 | 767.19 | 45.34 | 89.5 | 1188.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23194208300 |  | 100319716 |  | 6716208K |  |  |  | 565 | EX | REPAIR/REPLACE SL | 2621P | HEATHER | 2069 HEATHER WY | 067 | LEX | 2023-09-05 | U135005 | U138664 | 2023-06-12 | 2023-06-12 | 2023-06-12 |  | RJCRAWF | 2023-06-12 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.7667 | 3 | 853.91 | 645.16 | 89.61 | 46.54 | 72.6 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960864300 |  | 100249885 |  | 7360248E | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | RIVERVIEW | 7722 RIVERVIEW BV | 019 | CAT | 2023-06-13 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/DEREK CRAGER | 2023-06-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3429.83 | 0 | 0 | 0 | 3429.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22112154000 |  | 100407247 |  | 6712204D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | BRUNSWICK | 3457 BRUNSWICK RD | 067 | LEX | 2023-06-14 | U135005 | AOC SYST | 2022-06-23 | 2022-12-22 | 2023-12-31 |  | LSTONE | 2023-06-13 | 2023-06-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 17.5833 | 2 | 1418.49 | 1104.96 | 192.75 | 63.58 | 57.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22137501600 |  | 501285064 |  | 6728208I | 1966851 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | TWILIGHT SHADO | 1115 TWILIGHT SHADO DR LT61 | 067 | LEX | 2023-06-13 | ABLAKE | U130722 | 2022-10-07 | 2022-12-30 |  |  | ABLAKE | 2023-06-13 | 2023-05-15 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.7167 | 4 | 1138.2 | 1041.35 | 36.94 | 59.91 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026258700 |  |  |  | 7348260H | 2395600 | U132280 |  | 558 | EX | EMER- RETIRE 5'-4" PMIP | 2621P | BELLEFONTE | BELLEFONTE ST | 089 | RUS | 2023-06-20 | U128132 | U132280 | 2023-02-14 | 2049-12-31 | 2049-12-31 | 2023-02-15 | MCOLLET | 2023-06-13 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP2587 |  |  | 100 | 055832230262587 | 1.4 | 0 | 1956.38 | 100.61 | 0 | 135.19 | 1720.58 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164761000 |  | 100281675 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 519 PAYNE AV | 209 | GEO | 2023-06-13 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-06-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2254.73 | 0 | 0 | 0 | 2254.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165283400 |  | 500007547 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | LIMESTONE | 413 N LIMESTONE ST | 067 | LEX | 2023-06-14 | U126309 | U125763 | 2023-02-07 | 2023-12-29 |  |  | JAMIE LYNN | 2023-06-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2794.73 | 61.84 | 0 | 3.55 | 2729.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166673600 |  | 100322675 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 685 PROVIDENCE RD | 067 | LEX | 2023-06-13 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-06-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3924.99 | 0 | 0 | 0 | 3924.99 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166689900 |  | 100272376 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | OWSLEY | 311 OWSLEY AV | 073 | FRA | 2023-06-13 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-06-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 4207.21 | 0 | 0 | 0 | 4207.21 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168515900 |  | 100342744 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HIGH | 401 W HIGH ST | 173 | MT | 2023-06-16 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-13 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2770.64 | 0 | 0 | 0 | 2770.64 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23176980400 |  | 100427473 |  | 7256280K | 2286937 |  |  | 565 | EX | RPLC SL/22026171800 | 2600B | BUFFALO TRACE | 620 BUFFALO TRACE | 161 | MAY | 2023-06-13 | U126286 | U125763 | 2023-03-29 | 2023-12-29 |  |  | TYLER ALLISON | 2023-06-13 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 3146.07 | 55.15 | 0 | 3.17 | 3087.75 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23176981600 |  | 100356486 |  | 7256280K | 2286937 |  |  | 565 | EX | RPLC SL/22026171800 | 2600B | HILLCREST | 672 HILLCREST RD | 161 | MAY | 2023-06-13 | U126286 | U125763 | 2023-03-29 | 2023-12-29 |  |  | TYLER ALLISON | 2023-06-13 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2733.09 | 0 | 0 | 0 | 2733.09 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179194400 |  | 100260974 |  | 7352256C | 2075305 |  |  | 565 | EX | RPLC SL/20026983500 | 2600B | BUSH | 440 BUSH ST | 019 | ASH | 2023-06-13 | U125566 | U125763 | 2023-04-05 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-06-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1900.38 | 0 | 0 | 0 | 1900.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23188719300 |  | 500345746 |  | 6712204J | 9402984 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WESTBROOK | 3957 WESTBROOK DR | 067 | LEX | 2023-06-13 | KOBRYAN | U125208 | 2023-05-16 | 2023-05-22 | 2023-06-16 |  | KOBRYAN | 2023-06-13 | 2023-05-23 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.5667 | 5 | 941.08 | 889.84 | 0 | 51.24 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23193955200 |  | 500232606 |  | 7256280J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | TERRE HAUTE | 827 TERRE HAUTE DR | 161 | MAY | 2023-06-14 | U135005 | U135005 | 2023-06-09 | 2023-06-07 | 2023-06-20 |  | SDADAMS | 2023-06-13 | 2023-06-13 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26320021 | 30.1833 | 5 | 3332.31 | 2133.3 | 355.19 | 795.42 | 48.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23194270200 |  | 100323989 |  | 6732212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | EASTPOINT | 2528 EASTPOINT DR | 067 | LEX | 2023-06-14 | U135005 | U137585 | 2023-06-12 | 2023-06-12 | 2023-06-12 |  | LSTANFI | 2023-06-13 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 2.3167 | 1 | 513.31 | 164.19 | 209.35 | 40.77 | 99 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23194456200 |  | 100261940 |  | 7352256H |  |  |  | 565 | EX | GRD 1 REPLACE | 2621P | BLACKBURN | 725 BLACKBURN AV | 019 | ASH | 2023-06-14 | U135005 | U138664 | 2023-06-13 | 2023-06-13 | 2023-06-13 |  | MCOLLET | 2023-06-13 | 2023-06-13 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 14.85 | 2 | 4643.9 | 1049.2 | 166.99 | 880.55 | 2547.16 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21883289300 |  | 100357298 |  | 7240280J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2600B | R1 FRANKFORT | 504 R1 FRANKFORT ST BX61 | 023 | GER | 2023-06-14 | SDADAMS | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | SDADAMS | 2023-06-14 | 2022-10-12 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 8.9333 | 3 | 565.32 | 376.52 | 15.02 | 173.78 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960859500 |  | 100249894 |  | 7360248E | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | MCCOMIS | 7731 MCCOMIS DR | 019 | CAT | 2023-06-14 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE/CJH DEREK CRAGER | 2023-06-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3815.6 | 0 | 0 | 0 | 3815.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22114620200 |  | 100311315 |  | 6712204C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | CARDIGAN | 621 CARDIGAN CT | 067 | LEX | 2023-06-14 | LSTONE | AOC SYST | 2022-07-07 | 2023-01-06 | 2023-12-31 |  | LSTONE | 2023-06-14 | 2023-06-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 16 | 2 | 1340.5 | 1008.27 | 193.92 | 58.01 | 80.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22137500600 |  | 500820055 |  | 6720208K | 0253147 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LAKETOWER | 500 LAKETOWER DR CABLE | 067 | LEX | 2023-06-14 | JOCHOA | U130722 | 2022-10-07 | 2022-12-30 |  |  | JOCHOA | 2023-06-14 | 2023-05-18 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 17.65 | 5 | 1189.83 | 1105.86 | 20.37 | 63.6 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026258600 |  |  |  | 7348260H | 2395600 | U122858 |  | 557 | EX | EMER - INSTALL 5'-4" PMIP | 2621P | BELLEFONTE | 104 BELLEFONTE CR | 089 | RUS | 2023-08-14 | U128132 | U132280 | 2023-02-14 | 2049-12-31 | 2049-12-31 | 2023-02-15 | MCOLLET | 2023-06-14 | 2023-06-13 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP2586 |  |  | 100 | 055732230262586 | 2.7667 | 6 | 29274.5 | 5549.33 | 157.37 | 2819.8 | 16626.27 | 0 | 0 | 4121.73 | 3
KY | KY - EAST | 2631 | 23026275200 |  |  |  | 7360232F | 2397746 | U122858 |  | 557 | EX | EMER - INSTALL 3'-2" PMIP | 2621P | US 23 | 31600 US 23 | 019 | CAT | 2023-07-06 | U128132 | U122858 | 2023-05-19 | 2023-06-29 | 2023-06-30 | 2023-05-05 | MCOLLET | 2023-06-14 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP2752 |  |  | 100 | 055732230262752 | 5.9 | 6 | 5562.78 | 3755.28 | 0 | 985.82 | 24.2 | 0 | 10.64 | 786.84 | 3
KY | KY - EAST | 2631 | 23026275300 |  |  |  | 7360232F | 2397746 | U122858 |  | 558 | EX | EMER - RETIRE 3'-2" PIP | 2621P | US 23 | 31600 US 23 | 019 | CAT | 2023-06-29 | U128132 | U122858 | 2023-05-19 | 2023-06-30 | 2023-06-30 | 2023-05-05 | MCOLLET | 2023-06-14 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP2753 |  |  | 100 | 055832230262753 | 1.4 | 0 | 235.76 | 100.56 | 0 | 135.2 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026277200 |  |  |  | 6716212O | 2397951 | U461383 |  | 562 | EX | EMER-RETIRE 55' OF 6"PMLP MN | 2621P | ROSE | ROSE ST | 067 | LEX | 2023-06-20 | U136251 | U461383 | 2023-06-01 | 2023-06-30 | 2023-07-01 | 2023-06-01 | M MALONE | 2023-06-14 | 2023-06-13 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP2772 |  |  | 100 | 056232230262772 | 28.1333 | 0 | 5550.64 | 4427.84 | 230.5 | 801.1 | 91.2 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164760900 |  | 100281683 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 516 PAYNE AV | 209 | GEO | 2023-06-14 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-06-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2640.97 | 0 | 0 | 0 | 2640.97 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165283500 |  | 100336834 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | LIMESTONE | 414 N LIMESTONE ST | 067 | LEX | 2023-06-15 | U126309 | U125763 | 2023-02-07 | 2023-12-29 |  |  | JAMIE LYNN | 2023-06-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3297.85 | 0 | 0 | 0 | 3297.85 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166687900 |  | 100272386 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | CRESCENT | 100 CRESCENT AV | 073 | FRA | 2023-06-14 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-06-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 4308.37 | 0 | 0 | 0 | 4308.37 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168504900 |  | 100342599 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ANTWERP | 203 ANTWERP AV | 173 | MT | 2023-06-16 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-14 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4999.98 | 0 | 0 | 0 | 4999.98 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179194100 |  | 100260972 |  | 7352256D | 2075305 |  |  | 565 | EX | RPLC SL/20026983500 | 2600B | BLACKBURN | 464 BLACKBURN AV | 019 | ASH | 2023-06-14 | U125566 | U125763 | 2023-04-05 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-06-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2549.3 | 0 | 0 | 0 | 2549.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23183304200 |  | 100458707 |  | 6720204K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333604 | 2621P | CROSSEN | 1649 CROSSEN WY | 067 | LEX | 2023-06-15 | U930915 | U125208 | 2023-04-24 | 2023-10-20 | 2025-04-30 |  | HMCKUNE | 2023-06-14 | 2023-05-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.75 | 4 | 868.52 | 691.41 | 56.73 | 60.98 | 59.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23189761800 |  | 100288509 |  | 6720212D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332934 | 2621P | DONCASTER | 484 DONCASTER CT | 067 | LEX | 2023-06-18 | U128711 | U125208 | 2023-05-19 | 2023-11-17 | 2025-05-31 |  | LSTANFI | 2023-06-14 | 2023-06-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.2 | 3 | 1351.39 | 1113.16 | 0 | 167.83 | 70.4 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23194678500 |  | 100244086 |  | 7356256J |  |  |  | 565 | EX | REPLACE SL | 2621P | BLACKBURN | 4013 BLACKBURN AV | 019 | ASH | 2023-06-14 | JROGER1 | U138664 | 2023-06-14 | 2023-06-14 |  |  | JROGER1 | 2023-06-14 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 16 | 2 | 4761.93 | 2168.1 | 41.98 | 290.75 | 2261.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23194690600 |  | 100356491 |  | 7256280K |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2600B | BUFFALO TRACE | 671 BUFFALO TRACE | 161 | MAY | 2023-06-14 | U126286 | BDAWES | 2023-06-14 | 2023-12-29 |  |  | TYLER ALLISON | 2023-06-14 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 3334.05 | 0 | 0 | 0 | 3334.05 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11927112700 |  | 100352034 |  | 6744208E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WINCHESTER | 10 WINCHESTER PZ G1 | 049 | WIN | 2023-06-15 | WHIMES | U125208 | 2011-09-30 | 2020-12-31 |  |  | WHIMES | 2023-06-15 | 2023-06-12 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 7.2167 | 3 | 532.38 | 489.19 | 15.02 | 28.17 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960883900 |  | 100249905 |  | 7360248E | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | MCCOMIS | 7623 MCCOMIS AV | 019 | CAT | 2023-06-15 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER/MBLANKE | 2023-06-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 7218.02 | 0 | 0 | 0 | 7218.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22104887800 |  | 100311065 |  | 6712208N | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | BURNHAM | 3187 BURNHAM CT | 067 | LEX | 2023-06-15 | TROE | AOC SYST | 2022-06-01 | 2022-12-01 | 2023-12-31 |  | TROE | 2023-06-15 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 16 | 2 | 1410.42 | 1008.27 | 268.24 | 58.01 | 75.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22123736200 |  | 100321806 |  | 6716208D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303208 | 2600B | OLDHAM | 516 OLDHAM CT | 067 | LEX | 2023-06-18 | U128711 | U125208 | 2022-08-12 | 2023-02-10 | 2024-08-31 |  | DMARSTO | 2023-06-15 | 2023-05-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 29.8167 | 10 | 2413.27 | 1686.39 | 0 | 96.88 | 630 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165283200 |  | 500007523 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | LIMESTONE | 409 N LIMESTONE ST | 067 | LEX | 2023-06-16 | U126309 | U125763 | 2023-02-07 | 2023-12-29 |  |  | JAMIE LYNN | 2023-06-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2452.33 | 0 | 0 | 0 | 2452.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165283300 |  | 500007545 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | LIMESTONE | 411 N LIMESTONE ST | 067 | LEX | 2023-06-16 | U126309 | U125763 | 2023-02-07 | 2023-12-29 |  |  | JAMIE LYNN | 2023-06-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2452.33 | 0 | 0 | 0 | 2452.33 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168504700 |  | 100462167 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ANTWERP | 200 ANTWERP AV | 173 | MT | 2023-06-16 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-15 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2742.91 | 0 | 0 | 0 | 2742.91 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23176981200 |  | 100356494 |  | 7256280K | 2286937 |  |  | 565 | EX | RPLC SL/22026171800 | 2600B | HILLCREST | 658 HILLCREST RD | 161 | MAY | 2023-06-15 | U126286 | U125763 | 2023-03-29 | 2023-12-29 |  |  | TYLER ALLISON | 2023-06-15 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2416.32 | 0 | 0 | 0 | 2416.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23188698900 |  | 100288493 |  | 6720212D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332927 | 2621P | HARROGATE | 1718 HARROGATE RD | 067 | LEX | 2023-06-18 | U128711 | U125208 | 2023-05-16 | 2023-11-15 | 2025-05-31 |  | LSTANFI | 2023-06-15 | 2023-06-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.15 | 4 | 1134.58 | 891.73 | 0 | 150.45 | 92.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23194459000 |  | 100319939 |  | 6716208K |  |  |  | 565 | EX | REPLACE SERVICE LINE - 24HR | 2621P | GLENDOVER | 242 GLENDOVER RD | 067 | LEX | 2023-06-15 | KOBRYAN | U135005 | 2023-06-13 | 2023-06-13 | 2023-06-13 |  | KOBRYAN | 2023-06-15 | 2023-06-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 26.3333 | 3 | 2082.84 | 1410.17 | 522.23 | 81.14 | 69.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23195005800 |  | 100438827 |  | 6740208D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | LANG | 304 LANG DR | 049 | WIN | 2023-06-15 | U930915 | U129939 | 2023-06-15 | 2023-06-15 |  |  | WHIMES | 2023-06-15 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 6.6667 | 2 | 1379.08 | 455.42 | 35.29 | 26.21 | 862.16 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23196545400 |  | 100260980 |  | 7352256D | 2075305 |  |  | 565 | EX | REPLACE SERVICE LINE | 2600B | BLACKBURN | 448 BLACKBURN AV | 019 | ASH | 2023-06-26 | U125566 | U129939 | 2023-06-22 | 2023-06-22 |  |  | DAVID SKAGGS | 2023-06-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3826.56 | 0 | 0 | 0 | 3826.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 21883121500 |  | 100444231 |  | 6736248A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | WALNUT*GPS* | S WALNUT*GPS* ST | 097 | CYN | 2023-06-19 | U135005 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | ASNICHO | 2023-06-16 | 2022-11-17 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 14.4333 | 5 | 2802.26 | 958.56 | 0 | 343.86 | 1499.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21883206300 |  | 100270974 |  | 6740296K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2600B | MAIN | 11 MAIN ST | 023 | FOS | 2023-06-16 | SDADAMS | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | SDADAMS | 2023-06-16 | 2022-10-06 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 13.9 | 5 | 1218.38 | 870.91 | 36.94 | 310.53 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129078800 |  | 100312673 |  | 6716208E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LONGVIEW | 598 LONGVIEW DR | 067 | LEX | 2023-06-16 | KOBRYAN | U130722 | 2022-09-05 | 2022-12-30 |  |  | KOBRYAN | 2023-06-16 | 2023-06-12 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.2 | 4 | 892.27 | 843.73 | 0 | 48.54 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026268500 |  |  |  | 6708228A | 2394770 | U132257 |  | 559 | CO | PM-DE LINE ILI PH 2 BEND 260 | 5320E |  |  | 209 | GEO | 2023-07-18 |  | U132257 | 2023-03-23 | 2023-12-28 | 2023-12-31 | 2023-06-16 | BJOHNSON | 2023-06-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00559 | 3201033 |  |  | WP2685 |  |  | 100 | 103332230262685 |  | 30 | 717133.15 | 10185.71 | 10420.43 | 3617.63 | 572730.45 | 0 | 826.15 | 119352.78 | 30
KY | KY - WEST | 2621 | 23026272200 |  | 100322868 |  | 6716208H | 2397032 | U461383 |  | 555 | EX | INSTALL 200' OF 2"PMMP MAIN | 2600E | MONTCLAIR | 604 MONTCLAIR DR | 067 | LEX | 2023-07-11 | U128132 | U461383 | 2023-04-19 | 2023-06-06 | 2023-06-27 | 2023-06-16 | JDUNN | 2023-06-16 | 2023-06-06 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2722 |  |  | 100 | 055532230262722 | 39.8833 | 1060 | 27418.37 | 2511.33 | 1071.28 | 928.75 | 18979.72 | 0 | 77.78 | 3849.51 | 212
KY | KY - WEST | 2621 | 23026278200 |  |  |  | 6720212E | 2398026 | U461383 |  | 557 | EX | EMER-INSTALL 185' OF 4"PMLP | 2600B | 5TH | 201 E 5TH ST | 067 | LEX | 2023-06-23 | U124014 | U461383 | 2023-06-06 | 2024-01-29 | 2024-09-06 | 2023-06-15 | LESLIE SHARON | 2023-06-16 | 2023-06-09 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2782 | AMRCB |  | 100 | 055732230262782 | 68.5 | 1472 | 41523.49 | 4449.03 | 3542.99 | 2962.98 | 24751.4 | 0 | 91.71 | 5725.38 | 184
KY | KY - WEST | 2621 | 23026278300 |  |  |  | 6720212E | 2398026 | U461383 |  | 558 | EX | EMER-RETIRE 181' OF 4"BSLP MN | 2600B | 5TH | 201 E 5TH ST | 067 | LEX | 2023-06-23 | U124014 | U461383 | 2023-06-06 | 2024-01-31 | 2024-09-06 | 2023-06-15 | LESLIE SHARON | 2023-06-16 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2783 | AMRCB |  | 100 | 055832230262783 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164756400 |  | 100281632 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | MAPLE | 515 MAPLE ST | 209 | GEO | 2023-06-16 | U126602 | U125763 | 2023-02-03 | 2023-12-29 |  |  | DEREK PAYTON | 2023-06-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 4827.55 | 0 | 0 | 0 | 4827.55 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164757400 |  | 100281640 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | MAPLE | 531 MAPLE ST | 209 | GEO | 2023-06-16 | U126602 | U125763 | 2023-02-03 | 2023-12-29 |  |  | DEREK PAYTON | 2023-06-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2306.85 | 0 | 0 | 0 | 2306.85 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165283000 |  | 500018243 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | LIMESTONE | 405 N LIMESTONE ST | 067 | LEX | 2023-06-16 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-06-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3105.71 | 0 | 0 | 0 | 3105.71 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166672600 |  | 100322680 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 665 PROVIDENCE RD | 067 | LEX | 2023-06-16 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-06-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1916 | 0 | 0 | 0 | 1916 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166673300 |  | 100322685 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 680 PROVIDENCE RD | 067 | LEX | 2023-06-16 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-06-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2119.43 | 0 | 0 | 0 | 2119.43 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168504600 |  | 100342597 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ANTWERP | 199 ANTWERP AV | 173 | MT | 2023-06-16 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-16 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4871.28 | 0 | 0 | 0 | 4871.28 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168504800 |  | 500028363 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ANTWERP | 202 ANTWERP AV | 173 | MT | 2023-06-16 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-16 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4116.59 | 0 | 0 | 0 | 4116.59 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168518000 |  | 100342593 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ANTWERP | 198 ANTWERP AV | 173 | MT | 2023-06-16 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-16 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2798.31 | 0 | 0 | 0 | 2798.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23193729100 |  | 100322792 |  | 6716208D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332854 | 2621P | KASTLE | 1231 KASTLE RD | 067 | LEX | 2023-06-16 | U126308 | U135005 | 2023-06-08 | 2023-06-09 | 2023-06-28 |  | J ENSMINGER | 2023-06-16 | 2023-06-12 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 22.55 | 5 | 3424.85 | 1361.69 | 488.4 | 161.7 | 1413.06 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23195308800 |  | 500861992 |  | 7352260K | 0357755 |  |  | 566 | EX | SERVICE LINE ABANDON | 2621P | ARMCO | 100< ARMCO RD | 019 | ASH | 2023-06-19 | U135005 | U134852 | 2023-06-16 | 2023-06-16 |  |  | BMEEK | 2023-06-16 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.05 | 1 | 3.81 | 2.96 | 0 | 0.85 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23195308900 |  | 500681104 |  | 7352260K |  |  |  | 566 | EX | SERVICE LINE ABANDON | 2621P | ARMCO | 100 ARMCO RD | 019 | ASH | 2023-06-19 | U135005 | U134852 | 2023-06-16 | 2023-06-16 |  |  | BMEEK | 2023-06-16 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.3333 | 1 | 100.91 | 78.41 | 0 | 22.5 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23195311600 |  | 100254750 |  | 7348260C |  |  |  | 565 | EX | SERVICE LINE REPLACE | 2621P | BELLEFONTE | 627 BELLEFONTE RD | 089 | FLA | 2023-06-16 | MCOLLET | U134852 | 2023-06-16 | 2023-06-16 |  |  | MCOLLET | 2023-06-16 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 8.5167 | 2 | 1175.71 | 727.91 | 219.94 | 202.56 | 25.3 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23195317100 |  | 100346858 |  | 6696212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MACEY | 317 MACEY AV | 239 | VER | 2023-06-16 | U128410 | U126332 | 2023-06-16 | 2023-06-09 | 2023-06-29 |  | CDESPAIN | 2023-06-16 | 2023-06-14 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 | 73.8 | 9 | 8825.07 | 5483.14 | 523.38 | 315.52 | 2503.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23195339200 |  | 100289320 |  | 6724212A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | KINGTREE | 1909 KINGTREE CT | 067 | LEX | 2023-06-19 | U135005 | U134852 | 2023-06-16 | 2023-11-09 | 2025-05-31 |  | LSTANFI | 2023-06-16 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 37.65 | 6 | 2554.71 | 1934.05 | 408.77 | 161.29 | 50.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23195387200 |  | 100271305 |  | 6736252N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LOLA | 103 LOLA DR | 097 | CYN | 2023-06-19 | U135005 | U134852 | 2023-06-16 | 2023-06-16 | 2023-06-16 |  | WHIMES | 2023-06-16 | 2023-06-16 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26290021 | 20.6 | 3 | 2261.61 | 1407.29 | 493.29 | 296.13 | 64.9 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21884249000 |  | 100426853 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | LEFT FORK BULL | 1330 LEFT FORK BULL CK | 071 | PRE | 2023-06-19 | U130172 | U128293 | 2021-02-04 | 2023-06-19 | 2023-12-31 |  | BRIAN PREECE | 2023-06-19 |  |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 3.8333 | 1 | 277.01 | 261.92 | 0 | 15.09 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22129003400 |  | 100344046 |  | NEW |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | MAIN | 12390 MAIN ST | 173 | JEF | 2023-07-21 | U123688 | U130722 | 2022-09-05 | 2022-12-30 | 2023-12-31 |  | DENNING | 2023-06-19 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.9 | 2 | 357.98 | 338.48 | 0 | 19.5 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166688000 |  | 100468563 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | CRESCENT | 104 CRESCENT AV | 073 | FRA | 2023-06-21 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-06-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 6261.59 | 0 | 0 | 0 | 6261.59 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23194262100 |  | 500029649 |  | 6700212E |  |  |  | 566 | EX | ABANDON SERVICE LINE - DEMO | 2621P | CROSSFIELD | 101 CROSSFIELD DR | 239 | VER | 2023-06-28 | U128410 | U135005 | 2023-06-12 | 2023-12-29 |  |  | CDESPAIN | 2023-06-19 | 2023-06-19 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 27.8 | 6 | 3316.15 | 2002.2 | 33.11 | 115.2 | 1165.64 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23195586600 |  | 500024713 |  | 7356256B |  |  |  | 565 | EX | GRADE ONE LEAK ON RISER | 2621P | CENTRAL | 2161 CENTRAL AV | 019 | ASH | 2023-06-22 | UIPBOT23 | U124447 | 2023-06-18 | 2023-06-18 | 2023-06-18 |  | RECUMP | 2023-06-19 | 2023-06-18 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 8.15 | 4 | 1378.98 | 938.62 | 160.8 | 279.56 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 14257701500 |  | 100437597 |  | 6740232M |  |  |  | 566 | EX | ABANDON W/ 100359750 | 2621P | HIGH | 810 HIGH ST A3C | 017 | PAR | 2023-06-20 | U930915 | U125201 | 2014-10-15 | 2049-12-25 |  |  | NRICHIE | 2023-06-20 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.5 | 3 | 747.74 | 569.57 | 0 | 178.17 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21883252700 |  | 100357216 |  | 7240280G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2600B | KY 10 | 6391 KY 10 | 023 | GER | 2023-06-20 | SDADAMS | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | SDADAMS | 2023-06-20 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 11.7 | 4 | 1072.46 | 746.35 | 15.02 | 311.09 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960854200 |  | 100249883 |  | 7356248E | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | CRIDER | 7640 CRIDER DR | 019 | CAT | 2023-06-21 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER/MBLANKE | 2023-06-20 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 4343.21 | 0 | 0 | 0 | 4343.21 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164761200 |  | 100281684 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 520 PAYNE AV | 209 | GEO | 2023-06-20 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-06-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2938.89 | 0 | 0 | 0 | 2938.89 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166673100 |  | 100322684 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 676 PROVIDENCE RD | 067 | LEX | 2023-06-20 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-06-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1139.88 | 3.21 | 0 | 0.18 | 1136.49 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23166688100 |  | 100272359 |  | 6684228N | 2179094 |  |  | 565 | EX | RPLC SL/21026115500 | 2600B | CRESCENT | 117 CRESCENT AV | 073 | FRA | 2023-06-21 | U126285 | U125763 | 2023-02-14 | 2023-12-29 |  |  | DDAVIS | 2023-06-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 9 | 2 | 4720.31 | 578.29 | 0 | 497.35 | 3644.67 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168505000 |  | 100342600 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ANTWERP | 205 ANTWERP AV | 173 | MT | 2023-06-20 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-20 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3047.17 | 0 | 0 | 0 | 3047.17 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23176981900 |  | 100356492 |  | 7256280K | 2286937 |  |  | 565 | EX | RPLC SL/22026171800 | 2600B | HILLCREST | 695 HILLCREST RD | 161 | MAY | 2023-06-20 | U126286 | U125763 | 2023-03-29 | 2023-12-29 |  |  | TYLER ALLISON | 2023-06-20 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 4898.46 | 0 | 0 | 0 | 4898.46 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23191337300 |  | 100275733 |  | 6684228C |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | FRAZIER | 115 FRAZIER RD | 073 | FRA | 2023-06-20 | JMARSHA | U132002 | 2023-05-30 | 2023-06-09 | 2023-06-25 |  | JMARSHA | 2023-06-20 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8.3 | 2 | 474.85 | 449.02 | 0 | 25.83 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23196036800 |  | 100322867 |  | 6716208H | 2397032 |  |  | 565 | EX | RPLC SL/23026272200 | 2600B | MONTCLAIR | 612 MONTCLAIR DR | 067 | LEX | 2023-06-21 | U127414 | U125763 | 2023-06-20 | 2023-12-29 |  |  | ED FOX | 2023-06-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 2251.37 | 0 | 0 | 0 | 2251.37 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23196096900 |  | 100342601 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ANTWERP | 207 ANTWERP AV | 173 | MT | 2023-06-20 | U123111 | U125763 | 2023-06-20 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-20 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3852.14 | 0 | 0 | 0 | 3852.14 | 0 | 0 | 0
KY | KY - WEST | 2621 | 00454373800 |  | 500075129 |  | 6708204H | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | CLUB | 104 CLUB CT | 113 | NIC | 2023-06-21 | LSTONE | DMCCULL | 2000-12-12 | 2022-09-30 | 2023-12-31 |  | LSTONE | 2023-06-21 | 2022-09-30 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 18.3167 | 8 | 3495.49 | 1165.04 | 0 | 243.73 | 2086.72 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 14270128000 |  | 100270137 |  | 6732252P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | POPLAR | 105 S POPLAR ST DN | 097 | CYN | 2023-06-22 | U135005 | U122906 | 2014-12-11 | 2049-12-25 |  |  | NRICHIE | 2023-06-21 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10.75 | 3 | 958.42 | 716.98 | 17.13 | 224.31 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165283100 |  | 100336832 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | LIMESTONE | 408 N LIMESTONE ST | 067 | LEX | 2023-06-22 | U126309 | U125763 | 2023-02-07 | 2023-12-29 |  |  | JAMIE LYNN | 2023-06-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2739.66 | 516.46 | 0 | 29.72 | 2193.48 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168135700 |  | 100275105 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WILKINSON | 202 WILKINSON ST | 073 | FRA | 2023-06-21 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-06-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3301.35 | 0 | 0 | 0 | 3301.35 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168505100 |  | 100342602 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ANTWERP | 209 ANTWERP AV | 173 | MT | 2023-06-26 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-21 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2094.84 | 0 | 0 | 0 | 2094.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168505200 |  | 100342591 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ANTWERP | 210 ANTWERP AV | 173 | MT | 2023-06-21 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-21 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2899.69 | 0 | 0 | 0 | 2899.69 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168505400 |  | 100342590 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ANTWERP | 212 ANTWERP AV | 173 | MT | 2023-06-21 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-21 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2790.88 | 0 | 0 | 0 | 2790.88 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23176980800 |  | 100356484 |  | 7256280K | 2286937 |  |  | 565 | EX | RPLC SL/22026171800 | 2600B | BUFFALO TRACE | 660 BUFFALO TRACE | 161 | MAY | 2023-06-21 | U126286 | U125763 | 2023-03-29 | 2023-12-29 |  |  | TYLER ALLISON | 2023-06-21 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2681 | 0 | 0 | 0 | 2681 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23176981500 |  | 100356495 |  | 7256280K | 2286937 |  |  | 565 | EX | RPLC SL/22026171800 | 2600B | HILLCREST | 669 HILLCREST RD | 161 | MAY | 2023-06-21 | U126286 | U125763 | 2023-03-29 | 2023-12-29 |  |  | TYLER ALLISON | 2023-06-21 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2024.89 | 0 | 0 | 0 | 2024.89 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23185681500 |  | 100459538 |  | 6716208L |  |  |  | 565 | VO | REPLACE SERVICE LINE - D333513 | 2621P | BEECHMONT | 720 BEECHMONT RD | 067 | LEX | 2023-06-21 |  | U125208 | 2023-05-03 | 2023-11-02 | 2025-05-31 |  | JOSHUA COX | 2023-06-21 | 2023-06-16 |  | A | [11 empty] | 23196343700 | 100 |  | 4.0167 | 2 | 408.62 | 367.06 | 0 | 41.56 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23196286700 |  | 100288423 |  | 6720212H |  |  |  | 565 | EX | GRADE 1 REPLACE S/L | 2621P | CRICKLEWOOD | 540 CRICKLEWOOD DR | 067 | LEX | 2023-06-22 | U135005 | U129939 | 2023-06-21 | 2023-06-21 | 2023-06-21 |  | LSTANFI | 2023-06-21 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.7167 | 3 | 1362.88 | 956.58 | 209.41 | 102.29 | 94.6 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21026117600 |  |  |  | 6684228N | 2179094 | U134275 |  | 584 | EX | RETIRE REG STATION 1522 | 2623M | TANGLEWOOD | TANGLEWOOD DR | 073 | FRA | 2023-06-28 | U123258 | U134275 | 2021-04-19 | 2023-12-28 | 2023-12-31 | 2023-06-22 | GREG HALE | 2023-06-22 |  |  | F | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00584 | 3200584 |  |  | WP1176 | AMRCB |  | 100 | 058432210261176 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883125200 |  | 100426840 |  | 7340168T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | OLD MIDDLE CR | OLD MIDDLE CR RD | 071 | W P | 2023-06-22 | U130172 | U120245 | 2021-01-30 | 2023-06-22 | 2023-12-31 |  | JOHN HOWARD | 2023-06-22 |  |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 4.05 | 1 | 290.94 | 275.1 | 0 | 15.84 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883136300 |  | 100428845 |  | 7344148T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW3762 | PW3762 | 071 | DRI | 2023-06-22 | U130172 | U120245 | 2021-01-30 | 2023-06-22 | 2023-12-31 |  | BRIAN PREECE | 2023-06-22 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 8 | 1 | 572.59 | 541.43 | 0 | 31.16 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 21883228100 |  | 100436361 |  | 7260272B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2600B | STONELICK | 8140 STONELICK RD | 161 | MAY | 2023-06-22 | SDADAMS | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | SDADAMS | 2023-06-22 | 2022-11-21 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 20.4333 | 5 | 3498.86 | 1349.93 | 15.02 | 360.25 | 1773.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21924504100 |  | 100296059 |  | 6716216O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | PRICE | 447 PRICE RD | 067 | LEX | 2023-06-22 | MCRAIG | AOC SYST | 2021-07-09 | 2022-01-07 | 2022-12-31 |  | MCRAIG | 2023-06-22 | 2023-03-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 21.0333 | 8 | 2128.85 | 1294.42 | 262.18 | 445.75 | 126.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164763100 |  | 100281722 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | POPLAR | 508 POPLAR ST | 209 | GEO | 2023-06-22 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-06-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2192.32 | 0 | 0 | 0 | 2192.32 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164763200 |  | 100281721 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | POPLAR | 510 POPLAR ST | 209 | GEO | 2023-06-22 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-06-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2591.97 | 0 | 0 | 0 | 2591.97 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165282700 |  | 500007138 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | LIMESTONE | 401 N LIMESTONE ST | 067 | LEX | 2023-06-22 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | JAMIE LYNN | 2023-06-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2436.12 | 516.46 | 0 | 29.72 | 1889.94 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168132900 |  | 100275022 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WAPPING | 413 WAPPING ST | 073 | FRA | 2023-06-22 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-06-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3518.45 | 0 | 0 | 0 | 3518.45 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168133800 |  | 100275088 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WASHINGTON | 200 WASHINGTON ST 1F | 073 | FRA | 2023-06-22 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-06-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2578.97 | 0 | 0 | 0 | 2578.97 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168505300 |  | 500121741 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ANTWERP | 211 ANTWERP AV | 173 | MT | 2023-06-26 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-22 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2397.86 | 0 | 0 | 0 | 2397.86 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168505500 |  | 100342604 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ANTWERP | 215 ANTWERP AV | 173 | MT | 2023-06-26 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-22 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2781.69 | 0 | 0 | 0 | 2781.69 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168505600 |  | 100342605 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ANTWERP | 217 ANTWERP AV | 173 | MT | 2023-06-26 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-22 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2707.4 | 0 | 0 | 0 | 2707.4 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168505900 |  | 100342447 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | CLAY | 101 CLAY ST | 173 | MT | 2023-06-26 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-22 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 6132.98 | 0 | 0 | 0 | 6132.98 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176223900 |  | 100331283 |  | 6720212N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333581 | 2621P | OWSLEY | 108 OWSLEY AV | 067 | LEX | 2023-06-23 | U135005 | U125208 | 2023-03-24 | 2023-09-22 | 2025-03-31 |  | LSTANFI | 2023-06-22 | 2023-04-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.2833 | 6 | 1548.13 | 187.91 | 260.14 | 15.76 | 1084.32 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23176981400 |  | 100356496 |  | 7256280K | 2286937 |  |  | 565 | EX | RPLC SL/22026171800 | 2600B | HILLCREST | 668 HILLCREST RD | 161 | MAY | 2023-06-23 | U126286 | U125763 | 2023-03-29 | 2023-12-29 |  |  | TYLER ALLISON | 2023-06-22 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2735.43 | 0 | 0 | 0 | 2735.43 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23193933300 |  | 100360864 |  | 6736228J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BOURBON HILLS | 145 BOURBON HILLS DR | 017 | PAR | 2023-06-22 | NRICHIE | U135005 | 2023-06-09 | 2023-06-09 | 2023-06-29 |  | NRICHIE | 2023-06-22 | 2023-06-20 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 18.3 | 6 | 1925.18 | 1225.89 | 315.77 | 383.52 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23194792800 |  | 100343379 |  | 7240212B |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | MAIN | 324 W MAIN ST | 173 | MT | 2023-06-22 | U930915 | U133234 | 2023-06-14 | 2023-06-28 | 2023-07-14 |  | DENNING | 2023-06-22 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 7.5 | 3 | 1210.51 | 512.71 | 0 | 29.55 | 668.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23196337200 |  | 100329173 |  | 6720208P | 1635077 |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MOUNT TABOR | 533 MOUNT TABOR RD | 067 | LEX | 2023-06-22 | U930915 | U129939 | 2023-06-21 |  |  |  | HMCKUNE | 2023-06-22 | 2023-06-21 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.2833 | 7 | 712.52 | 149.33 | 491.89 | 8.6 | 62.7 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23196496500 |  | 100276666 |  | 6684228H |  |  |  | 565 | EX | GRADE 1 REPLACE S/L | 2621P | MCCREARY | 502 MCCREARY AV | 073 | FRA | 2023-06-23 | U135005 | U129939 | 2023-06-22 | 2023-06-22 | 2023-06-22 |  | EFGOINS | 2023-06-22 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 19.6167 | 3 | 1455.3 | 1273.59 | 78.71 | 73.3 | 29.7 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23196508800 |  | 100276673 |  | 6684228H |  |  |  | 565 | EX | GRADE 1 REPLACE S/L | 2621P | BLACKBURN | 628 BLACKBURN AV | 073 | FRA | 2023-06-27 | U128410 | U129939 | 2023-06-22 | 2023-06-22 | 2023-06-22 |  | CDESPAIN | 2023-06-22 | 2023-06-22 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 128.4833 | 12 | 9305.92 | 6303.25 | 762.83 | 362.74 | 1877.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23196545700 |  | 100260979 |  | 7352256D | 2075305 |  |  | 565 | EX | REPLACE SERVICE LINE | 2600B | BLACKBURN | 456 BLACKBURN AV | 019 | ASH | 2023-06-26 | U125566 | U129939 | 2023-06-22 | 2023-06-22 |  |  | DAVID SKAGGS | 2023-06-22 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3568.61 | 167.8 | 0 | 9.67 | 3391.14 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23196545800 |  | 100261190 |  | 7352256D | 2075305 |  |  | 565 | EX | REPLACE SERVICE LINE | 2600B | BLACKBURN | 457 BLACKBURN AV | 019 | ASH | 2023-06-26 | U125566 | U129939 | 2023-06-22 | 2023-06-22 |  |  | DAVID SKAGGS | 2023-06-22 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3602.13 | 0 | 0 | 0 | 3602.13 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 07698372300 |  | 500315147 |  | 6736252J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | US 62 | 916 US 62 E | 097 | CYN | 2023-06-23 | NRICHIE | DMCCULL | 2007-08-14 | 2022-07-01 | 2023-12-31 |  | NRICHIE | 2023-06-23 | 2022-11-17 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 16.4833 | 7 | 1612.88 | 1084.92 | 50.13 | 477.83 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 11902008800 |  | 100356149 |  | 7260280M | 2074375 |  |  | 566 | EX | RETIRE WITH 20-0269730-01 | 2621P | FOREST *HOLD AMRP* | 394< FOREST *HOLD AMRP* AV | 161 | MAY | 2023-06-23 | U461383 | U906631 | 2011-04-19 | 2049-12-31 |  |  | OFFICE EXECUTE | 2023-06-23 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1
KY | KY - CENTRAL | 2632 | 12964386600 |  | 100356148 |  | 7260280M | 2074375 |  |  | 566 | EX | RETIRE SL WITH 20-0269730-01 | 2621P | FOREST *HOLD AMRP* | 394 FOREST *HOLD AMRP* AV | 161 | MAY | 2023-06-23 | U461383 | U125208 | 2012-04-09 | 2049-12-31 |  |  | OFFICE EXEC | 2023-06-23 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1
KY | KY - CENTRAL | 2632 | 12964386900 |  | 100356150 |  | 7260280M | 2074375 |  |  | 566 | EX | RETIRED S/L WITH 20-0269730-01 | 2621P | FOREST *HOLD AMRP* | 392< FOREST *HOLD AMRP* AV | 161 | MAY | 2023-06-23 | U461383 | U125208 | 2012-04-09 | 2049-12-31 |  |  | OFFICE EXECUTE | 2023-06-23 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1
KY | KY - EAST | 2633 | 21883280800 |  | 100261689 |  | 7344144T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | P2 | P2 | 071 | MCD | 2023-06-23 | U130172 | U120245 | 2021-01-30 | 2023-06-23 |  |  | JOHN HOWARD | 2023-06-23 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.9667 | 1 | 287.31 | 271.68 | 0 | 15.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883284400 |  | 100302921 |  | 6712212N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | ATHENIA | 1166 ATHENIA DR | 067 | LEX | 2023-06-23 | JOCHOA | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOCHOA | 2023-06-23 | 2023-06-07 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 28.2333 | 9 | 3549.79 | 1683.9 | 35.12 | 211.89 | 1618.88 | 0 | 0 | 0
KY | KY - EAST | 2682 | 22979045900 |  | 100426515 |  | 7348160T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | GENERAL DELIVE | GENERAL DELIVE | 071 | BAN | 2023-06-23 | U130172 | U128070 | 2022-02-17 | 2023-06-23 |  |  | BRIAN PREECE | 2023-06-23 |  |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 6.3 | 1 | 775.76 | 426.37 | 0 | 349.39 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026269200 |  |  |  | 6708228A | 2394770 | U132257 |  | 560 | CO | PM-DE LINE ILI PH2 BEND 260 AB | 5320E |  |  | 209 | GEO | 2023-07-18 |  | U132257 | 2023-03-28 | 2023-12-29 | 2023-12-31 | 2023-06-23 | BJOHNSON | 2023-06-23 |  |  | C | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00560 | 3201032 |  |  | WP2692 |  |  | 100 | 103232230262692 |  | 0 | 195099.48 | 0 | 0 | 0 | 195099.48 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164763600 |  | 100281719 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | POPLAR | 516 POPLAR ST | 209 | GEO | 2023-06-23 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-06-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1937.88 | 0 | 0 | 0 | 1937.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168137700 |  | 100467644 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WILKINSON | 218 WILKINSON ST | 073 | FRA | 2023-06-23 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-06-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 4704.68 | 0 | 0 | 0 | 4704.68 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23176981700 |  | 100356497 |  | 7256280K | 2286937 |  |  | 565 | EX | RPLC SL/22026171800 | 2600B | HILLCREST | 680 HILLCREST RD | 161 | MAY | 2023-06-23 | U126286 | U125763 | 2023-03-29 | 2023-12-29 |  |  | TYLER ALLISON | 2023-06-23 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 3007.94 | 0 | 0 | 0 | 3007.94 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23180255500 |  | 100343554 |  | 7240212A | 2286366 |  |  | 565 | EX | RPLC SL/22026164200 | 2600B | SPRING | 487 SPRING ST | 173 | MT | 2023-06-23 | U126604 | U125763 | 2023-04-11 | 2023-12-29 |  |  | WILL FULKS | 2023-06-23 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3157.56 | 0 | 0 | 0 | 3157.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23182453700 |  | 100328262 |  | 6724204N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333510 | 2621P | WALNUT HILL | 1101 WALNUT HILL RD | 067 | LEX | 2023-06-23 | HMCKUNE | U125208 | 2023-04-19 | 2023-10-17 | 2025-04-30 |  | HMCKUNE | 2023-06-23 | 2023-05-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 46.45 | 12 | 7999.13 | 2407.71 | 381.77 | 582.4 | 4627.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23186476100 |  | 100458229 |  | 6720208P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332776 | 2621P | STONEHEDGE | 417 STONEHEDGE PL | 067 | LEX | 2023-06-26 | U128711 | U125208 | 2023-05-05 | 2023-11-03 | 2025-05-31 |  | MCRAIG | 2023-06-23 | 2023-06-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.0167 | 4 | 1530.71 | 952.87 | 256.26 | 225.88 | 95.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23196088700 |  | 500687647 |  | 7320248L |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | STATE RT 10 | STATE RT 10 | 089 | S P | 2023-06-23 | LAMAY | U129939 | 2023-06-20 | 2023-06-20 |  |  | LAMAY | 2023-06-23 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 15.3667 | 2 | 1306.08 | 1077.46 | 0 | 121.92 | 106.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23196472600 |  | 500508194 |  | 7356248L | 2180320 |  |  | 565 | EX | REPLACE SL | 2600B | CENTERLINE | 6003 CENTERLINE DR | 019 | CAT | 2023-06-23 | U123965 | U125765 | 2023-06-22 | 2023-12-29 |  |  | CJH DEREK CRAGER/MBLANKE | 2023-06-23 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3344.67 | 0 | 0 | 0 | 3344.67 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21026999201 |  | 100469207 |  | 7348252H | 2291262 | U461383 |  | 566 | EX | RETIRE 3"PIP SERVICE LINE | 2621P | SUMMIT | 924 SUMMIT RD | 019 | ASH | 2023-07-11 | U128132 | U461383 | 2023-04-27 | 2023-05-31 | 2023-12-31 | 2023-06-26 | ORA SLONE | 2023-06-26 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP9992 |  |  | 100 | 056632210269992 | 31.85 | 8 | 14749.54 | 2041.34 | 56.65 | 1571.61 | 11079.94 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883088600 |  | 100260674 |  | 7336152T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY ROUTE 550 | 317 KY ROUTE 550 | 071 | EAS | 2023-06-26 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN HOWARD | 2023-06-26 | 2023-06-26 |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.7833 | 1 | 200.71 | 189.79 | 0 | 10.92 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883138600 |  | 100259218 |  | 7344152T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PM83 | PM83 | 071 | PRT | 2023-06-26 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN HOWARD | 2023-06-26 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - EAST | 2631 | 21960866500 |  | 500917373 |  | 7344264D | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | US ROUTE 23 | 10606 US ROUTE 23 | 019 | CAT | 2023-06-26 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER/MBLANKE | 2023-06-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3369.87 | 0 | 0 | 0 | 3369.87 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129079700 |  | 100304322 |  | 6712208D |  |  |  | 566 | EX | ABANDON SL - PEND CN 12-25-23 | 2621P | LANE ALLEN | 901 LANE ALLEN RD | 067 | LEX | 2023-06-26 | U930915 | U130722 | 2022-09-05 | 2022-12-30 |  |  | MCRAIG | 2023-06-26 | 2022-11-10 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 17.9833 | 9 | 1462.01 | 1121.99 | 0 | 340.02 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22138345700 |  | 100260981 |  | 7352256D | 2075305 |  |  | 565 | EX | RPLC SL | 2600B | BLACKBURN | 444 BLACKBURN AV | 019 | ASH | 2023-06-26 | U125566 | AOC SYST | 2022-10-11 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-06-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 4789.07 | 0 | 0 | 0 | 4789.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026273000 |  |  |  | 6724208K | 2397262 | U461383 |  | 559 | EX | INSTALL 20'-4"PMMP W/NEW VALVE | 2621P | ANDOVER FOREST | 1000 ANDOVER FOREST DR | 067 | LEX | 2023-09-23 | U128132 | U461383 | 2023-04-28 | 2023-06-26 | 2023-10-01 | 2023-06-26 | HMCKUNE | 2023-06-26 | 2023-06-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP2730 |  |  | 100 | 055932230262730 | 75.7 | 180 | 20711.38 | 4204.89 | 1366.24 | 241.97 | 11660.59 | 0 | 21.14 | 3216.55 | 20
KY | KY - WEST | 2621 | 23026273100 |  |  |  | 6724208K | 2397262 | U461383 |  | 560 | EX | RETIRE 20'-4"PMMP W/C19-314 | 2621P | ANDOVER FOREST | 1000 ANDOVER FOREST DR | 067 | LEX | 2023-09-23 | U128132 | U461383 | 2023-04-28 | 2023-09-29 | 2023-10-01 | 2023-06-26 | HMCKUNE | 2023-06-26 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00560 | 3200560 |  |  | WP2731 |  |  | 100 | 056032230262731 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026278700 |  | 501346639 |  | 7320284H | 2398090 | U122858 |  | 555 | EX | INSTALL 105'-2" PMMP | 2621P | KELLY | 120 KELLY LN | 089 | S P | 2023-07-26 | U128132 | U122858 | 2023-06-09 | 2023-06-14 | 2023-06-15 | 2023-06-22 | MCOLLET | 2023-06-26 | 2023-06-19 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP2787 |  |  | 100 | 055532230262787 | 61 | 1044 | 8200.66 | 3995.35 | 1386.19 | 1500.66 | 137.5 | 0 | 15.32 | 1165.64 | 116
KY | KY - CENTRAL | 2629 | 23026279900 |  |  |  | 6752184M | 2293505 | U128885 |  | 560 | EX | RETIRE 38'-3" PMP | 2600B | COLLEGE HILL | COLLEGE HILL RD | 151 | WAC | 2023-07-13 | U128132 | U128885 | 2023-06-21 | 2023-06-30 | 2023-06-30 | 2023-06-21 | KKOUNS | 2023-06-26 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00560 | 3200560 |  |  | WP2799 |  |  | 100 | 056032230262799 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026281200 |  |  |  | 6712228N | 2398470 | U461383 |  | 557 | EX | EMER-INSTALL 2' OF 2"PMMP MAIN | 2621P | MARKETPLACE | 111 MARKETPLACE CR | 209 | GEO | 2023-08-08 | U136251 | U461383 | 2023-06-27 | 2023-06-26 | 2023-06-26 | 2023-06-26 | CDESPAIN | 2023-06-26 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP2812 |  |  | 100 | 055732230262812 |  | 2 | 6222.18 | 4525.26 | 298.93 | 508.54 | 18.7 | 0 | 13.87 | 856.88 | 2
KY | KY - WEST | 2623 | 23026281300 |  |  |  | 6712228N | 2398470 | U461383 |  | 558 | EX | EMER-RETIRE 2' OF 2"PMMP MAIN | 2621P | MARKETPLACE | 111 MARKETPLACE CR | 209 | GEO | 2023-07-03 | U136251 | U461383 | 2023-06-27 | 2023-06-26 | 2023-06-26 | 2023-06-26 | CDESPAIN | 2023-06-26 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP2813 |  |  | 100 | 055832230262813 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164763000 |  | 100281723 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | POPLAR | 502 POPLAR ST | 209 | GEO | 2023-06-26 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-06-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3113.65 | 0 | 0 | 0 | 3113.65 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164763900 |  | 100281705 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | POPLAR | 600 POPLAR ST | 209 | GEO | 2023-06-26 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-06-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2031.02 | 61.4 | 0 | 3.89 | 1965.73 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164764100 |  | 100281704 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | POPLAR | 604 POPLAR ST | 209 | GEO | 2023-06-26 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-06-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1986.88 | 0 | 0 | 0 | 1986.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164764200 |  | 100281702 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | POPLAR | 608 POPLAR ST DN | 209 | GEO | 2023-06-26 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-06-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2355.85 | 0 | 0 | 0 | 2355.85 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165283600 |  | 100294812 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | LIMESTONE | 417 N LIMESTONE ST 1FL | 067 | LEX | 2023-06-27 | U126309 | U125763 | 2023-02-07 | 2023-12-29 |  |  | JAMIE LYNN | 2023-06-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 5311.07 | 0 | 0 | 0 | 5311.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166669500 |  | 100322625 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 685 BERRY LN | 067 | LEX | 2023-06-26 | U126284 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JOSH PASLEY/STANLEY PIPELINE | 2023-06-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2911.67 | 512.42 | 0 | 441.98 | 1957.27 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168132500 |  | 100274999 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WAPPING | 401 WAPPING ST | 073 | FRA | 2023-06-27 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-06-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3579.98 | 0 | 0 | 0 | 3579.98 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168510600 |  | 100342610 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 302 HOLT AV | 173 | MT | 2023-06-27 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-26 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3333.01 | 0 | 0 | 0 | 3333.01 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168515100 |  | 500030876 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | SUMMER | 205 SUMMER ST | 173 | MT | 2023-06-27 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-26 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3909 | 0 | 0 | 0 | 3909 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168515200 |  | 100342636 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | SUMMER | 206 SUMMER ST | 173 | MT | 2023-06-27 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-26 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3361.89 | 0 | 0 | 0 | 3361.89 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23176982300 |  | 100356451 |  | 7256280O | 2286937 |  |  | 565 | EX | RPLC SL/22026171800 | 2600B | LEXINGTON | 751 LEXINGTON PK | 161 | MAY | 2023-06-26 | U126286 | U125763 | 2023-03-29 | 2023-12-29 |  |  | TYLER ALLISON | 2023-06-26 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2392.43 | 37.87 | 0 | 2.15 | 2352.41 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23180254000 |  | 100343541 |  | 7240212A | 2286366 |  |  | 565 | EX | RPLC SL/22026164200 | 2600B | SPRING | 453 SPRING ST | 173 | MT | 2023-06-26 | U126604 | U125763 | 2023-04-11 | 2023-12-29 |  |  | WILL FULKS | 2023-06-26 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2637.28 | 0 | 0 | 0 | 2637.28 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23180254300 |  | 100343545 |  | 7240212A | 2286366 |  |  | 565 | EX | RPLC SL/22026164200 | 2600B | SPRING | 459 SPRING ST | 173 | MT | 2023-06-26 | U126604 | U125763 | 2023-04-11 | 2023-12-29 |  |  | WILL FULKS | 2023-06-26 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2444.76 | 0 | 0 | 0 | 2444.76 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23196473600 |  | 100438806 |  | 6752184M | 2293505 |  |  | 565 | EX | RPLC SL/22026236400 | 2600B | COLLEGE HILL | 749 COLLEGE HILL RD | 151 | WAC | 2023-06-30 | U461423 | U125763 | 2023-06-22 | 2023-12-29 |  |  | KKOUNS | 2023-06-26 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26290032 |  | 1 | 965.27 | 0 | 0 | 0 | 965.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23196798300 |  | 100331172 |  | 6720212N |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | LINCOLN | 260 LINCOLN AV | 067 | LEX | 2023-06-26 | U930915 | U134852 | 2023-06-23 | 2023-06-23 | 2023-06-23 |  | LSTONE | 2023-06-26 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.4833 | 4 | 1484.24 | 1345.44 | 0 | 100.3 | 38.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23196897800 |  | 100261191 |  | 7352256D | 2075305 |  |  | 566 | EX | ABANDN SL | 2600B | BLACKBURN | 465 BLACKBURN AV | 019 | ASH | 2023-06-27 | U125566 | U125763 | 2023-06-26 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-06-26 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1401.87 | 0 | 0 | 0 | 1401.87 | 0 | 0 | 0
KY | KY - WEST | 2621 | 04591462100 |  | 100328292 |  | 6716204L | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | WILSON DOWNING | 679 WILSON DOWNING RD | 067 | LEX | 2023-06-27 | ABLAKE | SSUTHER | 2004-11-03 | 2022-07-01 | 2023-12-31 |  | ABLAKE | 2023-06-27 | 2022-10-31 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 47.4 | 14 | 8407.9 | 2966.17 | 87.15 | 252.18 | 5102.4 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883147100 |  | 100434900 |  | 7372156T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | BENT BRANCH | 10126 BENT BRANCH RD | 195 | MET | 2023-06-27 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN HOWARD | 2023-06-27 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883258500 |  | 100259238 |  | 7356148T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | LFT FORK TOLER | 393 LFT FORK TOLER CK | 071 | HAR | 2023-06-27 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN HOWARD | 2023-06-27 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - CENTRAL | 2629 | 22026236400 |  | 501340092 |  | 6752184M | 2293505 | U128885 |  | 555 | EX | INSTALL 450'-4" PMMP | 2600B | COLLEGE HILL | 755 COLLEGE HILL RD | 151 | WAC | 2023-08-09 | U128132 | U128885 | 2022-11-14 | 2023-06-21 | 2023-07-15 | 2023-06-26 | KKOUNS | 2023-06-27 | 2023-06-12 | 2023-06-12 | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP2364 |  |  | 100 | 055532220262364 | 129.9667 | 8109 | 52709.69 | 8046.43 | 2440.07 | 4842.02 | 29805.16 | 0 | 101.87 | 7474.14 | 477
KY | KY - WEST | 2621 | 23026276300 |  |  |  | 6716204C | 2397850 | U461383 |  | 559 | EX | EMER-INSTALL 2"POLY VALVE | 2621P | LAREDO | 3441 LAREDO DR | 067 | LEX | 2023-10-10 | U128132 | U461383 | 2023-05-24 | 2023-09-28 | 2023-10-01 | 2023-06-27 | RJCRAWF | 2023-06-27 | 2023-06-21 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP2763 |  |  | 100 | 055932230262763 | 14.5667 | 16 | 6851.84 | 2081.86 | 585.79 | 119.77 | 3083.39 | 0 | 3.79 | 977.24 | 4
KY | KY - WEST | 2621 | 23026276400 |  |  |  | 6716204C | 2397850 | U461383 |  | 560 | EX | EMER-RETIRE 2"VALVE C14-27 | 2621P | LAREDO | 3441 LAREDO DR | 067 | LEX | 2023-10-10 | U128132 | U461383 | 2023-05-24 | 2023-09-29 | 2023-10-01 | 2023-06-27 | RJCRAWF | 2023-06-27 | 2023-06-21 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00560 | 3200560 |  |  | WP2764 |  |  | 100 | 056032230262764 | 20.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026276900 |  |  |  | 6716212H | 2397915 | U461383 |  | 562 | EX | RETIRE 250' OF 3"BSLP MAIN | 2621P | ADDIE | ADDIE ST | 067 | LEX | 2023-08-08 | U128132 | U461383 | 2023-05-30 | 2023-09-01 | 2023-09-01 | 2023-06-27 | LSTANFI | 2023-06-27 | 2023-06-27 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP2769 | AMRCB |  | 100 | 056232230262769 | 17.7833 | 0 | 1716.17 | 1005.3 | 567.91 | 142.96 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026291400 |  |  |  | 6684228N | 2179094 | U134275 |  | 560 | EX | PAPER JOB - MP RETIREMENT | 2600E | TANGLEWOOD | 100 TANGLEWOOD DR | 073 | FRA | 2023-09-28 | U136251 | U134275 | 2023-09-01 | 2023-12-29 | 2023-12-31 | 2023-06-27 | AWEBER | 2023-06-27 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00560 | 3200560 |  |  | WP2914 | AMRCB |  | 100 | 056032230262914 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164763700 |  | 100281663 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | POPLAR | 517 POPLAR ST | 209 | GEO | 2023-06-27 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-06-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2191.03 | 0 | 0 | 0 | 2191.03 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164764000 |  | 100281665 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | POPLAR | 601 POPLAR ST DN | 209 | GEO | 2023-06-27 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-06-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3007.08 | 54.36 | 0 | 49.54 | 2903.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165282800 |  | 500007520 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | LIMESTONE | 403 N LIMESTONE ST | 067 | LEX | 2023-06-27 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-06-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1947.12 | 0 | 0 | 0 | 1947.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166673800 |  | 100322674 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 689 PROVIDENCE RD | 067 | LEX | 2023-06-28 | U126284 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JOSH PASLEY/STANLEY PIPELINE | 2023-06-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.1167 | 1 | 2336.28 | 326.69 | 0 | 281.75 | 1727.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168132600 |  | 100275050 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WAPPING | 404 WAPPING ST | 073 | FRA | 2023-06-27 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-06-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3749.42 | 0 | 0 | 0 | 3749.42 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168133500 |  | 100275037 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WAPPING | 511 WAPPING ST | 073 | FRA | 2023-06-27 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-06-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2640 | 0 | 0 | 0 | 2640 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168506600 |  | 100342625 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | CLAY | 205 CLAY ST B | 173 | MT | 2023-06-28 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-27 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2291.62 | 0 | 0 | 0 | 2291.62 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168506700 |  | 100342627 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | CLAY | 207 CLAY ST | 173 | MT | 2023-06-28 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-27 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2525.65 | 0 | 0 | 0 | 2525.65 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168506800 |  | 100342664 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | CLAY | 208 CLAY ST | 173 | MT | 2023-06-28 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-27 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2458.43 | 0 | 0 | 0 | 2458.43 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23180254500 |  | 100343546 |  | 7240212A | 2286366 |  |  | 566 | EX | ABANDN SL/22026164200 | 2600B | SPRING | 463 SPRING ST | 173 | MT | 2023-06-27 | U126604 | U125763 | 2023-04-11 | 2023-12-29 |  |  | WILL FULKS | 2023-06-27 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1681.02 | 0 | 0 | 0 | 1681.02 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23180254700 |  | 100343548 |  | 7240212A | 2286366 |  |  | 565 | EX | RPLC SL/22026164200 | 2600B | SPRING | 465 SPRING ST | 173 | MT | 2023-06-27 | U126604 | U125763 | 2023-04-11 | 2023-12-29 |  |  | WILL FULKS | 2023-06-27 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3227.24 | 0 | 0 | 0 | 3227.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23188281400 |  | 100312990 |  | 6716208E | 1635357 |  |  | 565 | EX | AOC INSTALL SLEEVE IN HARD SUR | 2621D | ROSEMILL | 575 ROSEMILL DR | 067 | LEX | 2023-06-27 | MCRAIG | AOC SYST | 2023-05-15 | 2022-12-28 | 2023-12-31 |  | MCRAIG | 2023-06-27 | 2023-06-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.85 | 6 | 2308.8 | 1362.1 | 392.95 | 487.75 | 66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23189752300 |  | 100323603 |  | 6716208O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094450 | 2621P | BELLEFONTE | 3404 BELLEFONTE DR | 067 | LEX | 2023-06-27 | KKINDER | U125208 | 2023-05-19 | 2023-11-17 | 2025-05-31 |  | KKINDER | 2023-06-27 | 2023-06-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.9667 | 4 | 1939.16 | 1307.91 | 462.99 | 86.86 | 81.4 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23192716400 |  | 500015792 |  | 6752184M | 2293505 |  |  | 565 | EX | RPLC SL/22026236400 | 2600B | COLLEGE HILL | 761 COLLEGE HILL RD | 151 | WAC | 2023-06-27 | U461309 | U125763 | 2023-06-05 | 2023-12-29 |  |  | R.HUMPHREYS | 2023-06-27 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26290032 | 8 | 1 | 4209.53 | 502.31 | 270.47 | 186.22 | 3250.53 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23196895800 |  | 501315932 |  | 7256280K | 2181662 |  |  | 565 | EX | RPLC SL/22026171800 | 2600B | HILLCREST | 702 HILLCREST RD | 161 | MAY | 2023-06-27 | U126286 | U136332 | 2023-06-26 | 2023-06-26 |  |  | TYLER ALLISON | 2023-06-27 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26320032 |  | 1 | 1958.07 | 0 | 0 | 0 | 1958.07 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23196971100 |  | 100280758 |  | 6688228E |  |  |  | 565 | EX | REPLACE SERVICE LINE D380967 | 2621P | WINDING WAY | 156 WINDING WAY DR | 073 | FRA | 2023-06-28 | U135005 | U135005 | 2023-06-26 | 2023-06-29 | 2023-07-17 |  | EFGOINS | 2023-06-27 | 2023-06-27 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 25.5667 | 5 | 2462.03 | 1566 | 316.64 | 528.79 | 50.6 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23197451000 |  | 100280738 |  | 6688228E |  |  |  | 565 | EX | REPLACE SL | 2621P | WINDING WAY | 153 WINDING WAY DR | 073 | FRA | 2023-06-28 | U135005 | U137585 | 2023-06-27 | 2023-06-27 |  |  | EFGOINS | 2023-06-27 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 20.9 | 3 | 2013.95 | 1259.54 | 197.14 | 448.37 | 108.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129005100 |  | 100300307 |  | 6716212G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | HIGH | 839 W HIGH ST | 067 | LEX | 2023-06-28 | MSHARON | U130722 | 2022-09-05 | 2022-12-30 | 2023-12-31 |  | MSHARON | 2023-06-28 | 2023-06-22 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 14.4 | 5 | 1037.92 | 936.38 | 0 | 101.54 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129008100 |  | 100355563 |  | 7260276B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CLARK | 507 CLARK ST | 161 | MAY | 2023-06-28 | SDADAMS | U130722 | 2022-09-05 | 2022-12-30 |  |  | SDADAMS | 2023-06-28 | 2023-05-08 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 14.4333 | 7 | 1363.83 | 919.46 | 50.13 | 394.24 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129024900 |  | 100355535 |  | 7260276B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | CLARK | 506 CLARK ST | 161 | MAY | 2023-06-28 | SDADAMS | U130722 | 2022-09-05 | 2023-06-28 |  |  | SDADAMS | 2023-06-28 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 3.4833 | 2 | 1464.27 | 222.58 | 1115.43 | 126.26 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22137500700 |  | 100333827 |  | 6720212J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DELAWARE | 921 DELAWARE AV | 067 | LEX | 2023-06-28 | U930915 | U130722 | 2022-10-07 | 2022-12-30 |  |  | JOCHOA | 2023-06-28 | 2023-05-08 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 30.95 | 11 | 3645.83 | 1882.08 | 17.13 | 108.03 | 1638.59 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166672700 |  | 100322682 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 668 PROVIDENCE RD | 067 | LEX | 2023-06-28 | U126284 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JOSH PASLEY/STANLEY PIPELINE | 2023-06-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.8833 | 1 | 2902.08 | 185.75 | 0 | 160.22 | 2556.11 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168507600 |  | 100342645 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | CLAY | 310 CLAY ST | 173 | MT | 2023-06-29 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-28 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1857.97 | 0 | 0 | 0 | 1857.97 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168507700 |  | 100342635 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | CLAY | 311 CLAY ST | 173 | MT | 2023-06-29 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-28 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2446.18 | 0 | 0 | 0 | 2446.18 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168507800 |  | 100342643 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | CLAY | 314 CLAY ST | 173 | MT | 2023-06-29 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-28 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3122.75 | 0 | 0 | 0 | 3122.75 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23176981800 |  | 100356498 |  | 7256280K | 2286937 |  |  | 565 | EX | RPLC SL/22026171800 | 2600B | HILLCREST | 690 HILLCREST RD | 161 | MAY | 2023-06-28 | U126286 | U125763 | 2023-03-29 | 2023-12-29 |  |  | TYLER ALLISON | 2023-06-28 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2477.57 | 0 | 0 | 0 | 2477.57 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23180255100 |  | 100343549 |  | 7240212A | 2286366 |  |  | 565 | EX | RPLC SL/22026164200 | 2600B | SPRING | 469 SPRING ST | 173 | MT | 2023-06-28 | U126604 | U125763 | 2023-04-11 | 2023-12-29 |  |  | WILL FULKS | 2023-06-28 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3073.5 | 0 | 0 | 0 | 3073.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23180255300 |  | 100343551 |  | 7240212A | 2286366 |  |  | 565 | EX | RPLC SL/22026164200 | 2600B | SPRING | 475 SPRING ST | 173 | MT | 2023-06-28 | U126604 | U125763 | 2023-04-11 | 2023-12-29 |  |  | WILL FULKS | 2023-06-28 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2886.34 | 0 | 0 | 0 | 2886.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23183302800 |  | 100340655 |  | 6724212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D246270 | 2621P | CHICKASAW | 1706 CHICKASAW CT | 067 | LEX | 2023-06-28 | LSTONE | U125208 | 2023-04-24 | 2023-10-20 | 2025-04-30 |  | LSTONE | 2023-06-28 | 2023-05-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.9167 | 7 | 1200.02 | 995.12 | 50.15 | 71.15 | 83.6 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23197409000 |  | 100280845 |  | 6688228I |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MISSOURI | 268 MISSOURI AV | 073 | FRA | 2023-06-28 | DCOLLIN | U135005 | 2023-06-27 | 2023-06-27 | 2023-06-27 |  | DCOLLIN | 2023-06-28 | 2023-06-28 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 29.8333 | 4 | 3050.03 | 1996.17 | 196.95 | 230.61 | 626.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23197441000 |  | 100310063 |  | 6712208H |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HARRODSBURG | 2320 HARRODSBURG RD | 067 | LEX | 2023-06-28 | KKINDER | U135005 | 2023-06-27 | 2023-06-27 | 2023-06-27 |  | KKINDER | 2023-06-28 | 2023-06-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 29.9667 | 3 | 2373.66 | 1723.95 | 510.88 | 99.23 | 39.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23197704700 |  | 100410421 |  | 6740212N |  |  |  | 565 | EX | REROUTE SERVICE | 2621P | ASPEN | 310 ASPEN LN | 049 | WIN | 2023-06-28 | NRICHIE | JTOY | 2023-06-28 | 2023-06-27 |  |  | NRICHIE | 2023-06-28 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26290031 | 1.8333 | 1 | 329.24 | 121.66 | 66.05 | 100.83 | 40.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21931305100 |  | 100302639 |  | 6712212G | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE | 2621D | VILEY | 1298 VILEY RD | 067 | LEX | 2023-06-29 | MCRAIG | AOC SYST | 2021-08-06 | 2022-02-04 | 2022-12-31 |  | MCRAIG | 2023-06-29 | 2023-03-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 45.0667 | 13 | 4570 | 2525.1 | 746.79 | 366.91 | 931.2 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960854000 |  | 500522848 |  | 7356248H | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | CRIDER | 6001 CRIDER DR | 019 | CAT | 2023-06-29 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER/MBLANKE | 2023-06-29 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2687.13 | 0 | 0 | 0 | 2687.13 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164764500 |  | 100281692 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | POPLAR | 620 POPLAR ST | 209 | GEO | 2023-06-29 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-06-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2016.28 | 0 | 0 | 0 | 2016.28 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164764800 |  | 100281672 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | POPLAR | 623 POPLAR ST | 209 | GEO | 2023-06-29 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-06-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2252.28 | 0 | 0 | 0 | 2252.28 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166674100 |  | 100322690 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 696 PROVIDENCE RD | 067 | LEX | 2023-06-30 | U126284 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JOSH PASLEY/STANLEY PIPELINE | 2023-06-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 3358.48 | 512.39 | 0 | 441.98 | 2404.11 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168131000 |  | 100275108 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | MAIN | 416 W MAIN ST | 073 | FRA | 2023-06-29 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-06-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2207.69 | 0 | 0 | 0 | 2207.69 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168507500 |  | 100342634 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | CLAY | 309 CLAY ST | 173 | MT | 2023-07-19 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-06-29 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3438.33 | 0 | 0 | 0 | 3438.33 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23180255200 |  | 100343550 |  | 7240212A | 2286366 |  |  | 565 | EX | RPLC SL/22026164200 | 2600B | SPRING | 473 SPRING ST | 173 | MT | 2023-06-29 | U126604 | U125763 | 2023-04-11 | 2023-12-29 |  |  | WILL FULKS | 2023-06-29 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3107.55 | 0 | 0 | 0 | 3107.55 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23190141100 |  | 100329169 |  | 6720208P | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER | 2621D | MOUNT TABOR | 517 MOUNT TABOR RD | 067 | LEX | 2023-06-29 | U930915 | AOC SYST | 2023-05-22 | 2023-06-16 | 2023-07-18 |  | WISHII | 2023-06-29 | 2023-06-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 31.9833 | 8 | 2254.39 | 1823.63 | 211.87 | 170.49 | 48.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23196093800 |  | 100318224 |  | 6716204C |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | GREENLAWN | 3432 GREENLAWN DR | 067 | LEX | 2023-06-29 | WISHII | U135005 | 2023-06-20 | 2023-12-29 |  |  | WISHII | 2023-06-29 | 2023-06-29 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.7333 | 2 | 1445.55 | 766.19 | 212.75 | 397.31 | 69.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23197972200 |  | 100310069 |  | 6712208H |  |  |  | 565 | EX | GRADE 1 REPLACE SERVICE | 2621P | LONGVIEW | 670 LONGVIEW DR | 067 | LEX | 2023-06-29 | KKINDER | U129939 | 2023-06-29 | 2023-06-29 | 2023-06-29 |  | KKINDER | 2023-06-29 | 2023-06-29 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.6667 | 2 | 1566.4 | 993.64 | 251.26 | 229.1 | 92.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21026115500 |  |  |  | 6684228N | 2179094 | U134275 |  | 557 | EX | INSTALL 9560' OF 2"PMMP | 2600B | TANGLEWOOD | TANGLEWOOD DR | 073 | FRA | 2023-08-16 | U136251 | U134275 | 2021-04-13 | 2022-08-04 | 2023-12-31 | 2023-04-21 | DDAVIS | 2023-06-30 | 2023-01-03 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP1155 | AMRCB |  | 100 | 055732210261155 | 1344.9167 | 1394589 | 1791950.44 | 89786.33 | 28415.17 | 43938.06 | 1370423.72 | 0 | 9737.51 | 249649.65 | 8771
KY | KY - WEST | 2623 | 21026115600 |  |  |  | 6684228N | 2179094 | U134275 |  | 558 | EX | RETIRE 9,590' OF BSLP & OTHER | 2600B | TANGLEWOOD | TANGLEWOOD DR | 073 | FRA | 2023-07-14 | U136251 | U134275 | 2021-04-13 |  | 2049-12-31 | 2023-06-27 | DDAVIS | 2023-06-30 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP1156 | AMRCB |  | 100 | 055832210261156 |  | 0 | 182.4 | 0 | 0 | 0 | 182.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026178900 |  |  |  | 6728208J | 2287856 | U461383 |  | 557 | EX | INSTALL 620' OF 12"CSHP MAIN | 2600B | BIG POND | 1320 BIG POND CR | 067 | LEX | 2023-08-15 | U136251 | U461383 | 2022-03-30 | 2023-06-09 | 2024-03-31 | 2023-06-29 | BPULLIAM/FISHEL | 2023-06-30 | 2022-04-01 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP1789 | AMRCB |  | 100 | 055732220261789 | 169.8 | 14160 | 268220 | 22444.53 | 29912.65 | 51702.52 | 126168.36 | 0 | 2693.27 | 35298.67 | 590
KY | KY - WEST | 2621 | 22026179100 |  |  |  | 6728208J | 2287856 | U461383 |  | 558 | EX | RETIRE 520' OF 12"MJBSHP | 2600B | BIG POND | 1320 BIG POND CR | 067 | LEX | 2023-07-17 | U136251 | U461383 | 2022-03-30 | 2023-07-31 | 2024-03-31 | 2023-06-29 | BPULLIAM/FISHEL | 2023-06-30 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP1791 | AMRCB |  | 100 | 055832220261791 | 16 | 0 | 3152.18 | 986.74 | 0 | 1983.04 | 182.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026273300 |  |  |  | 6720208E | 2397369 | U134275 |  | 557 | EX | INSTALL 290' OF 4" PMMP | 2600B | CHINOE | 208 CHINOE RD | 067 | LEX | 2023-07-03 | U128132 | U134275 | 2023-05-03 | 2023-12-14 | 2023-12-31 | 2023-06-28 | SHAWN DENNIS | 2023-06-30 | 2023-06-19 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2733 | AMRCB |  | 100 | 055732230262733 | 32.05 | 2022 | 80935.68 | 2155.62 | 2312.68 | 753.9 | 64330.01 | 0 | 175.41 | 11208.06 | 337
KY | KY - WEST | 2621 | 23026273400 |  |  |  | 6720208E | 2397369 | U134275 |  | 558 | EX | RETIRE 283' OF 3" BSMP | 2600E | CHINOE | 208 CHINOE RD | 067 | LEX | 2023-07-11 | U128132 | U134275 | 2023-05-03 | 2023-01-31 | 2023-12-31 | 2023-06-28 | SHAWN DENNIS | 2023-06-30 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2734 | AMRCB |  | 100 | 055832230262734 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164763500 |  | 100281720 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | POPLAR | 514 POPLAR ST | 209 | GEO | 2023-06-30 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-06-30 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2210.63 | 0 | 0 | 0 | 2210.63 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168508500 |  | 100342650 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ELM | 112 ELM ST | 173 | MT | 2023-06-30 | U126604 | U125763 | 2023-02-21 | 2023-12-29 |  |  | WILL FULKS | 2023-06-30 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2447.08 | 0 | 0 | 0 | 2447.08 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168508600 |  | 100444220 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ELM | 114 ELM ST | 173 | MT | 2023-06-30 | U126604 | U125763 | 2023-02-21 | 2023-12-29 |  |  | WILL FULKS | 2023-06-30 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3881.76 | 0 | 0 | 0 | 3881.76 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23180253800 |  | 100343567 |  | 7240212A | 2286366 |  |  | 566 | EX | ABANDN SL/22026164200 | 2600B | SPRING | 440 SPRING ST | 173 | MT | 2023-07-05 | U126604 | U125763 | 2023-04-11 | 2023-12-29 |  |  | WILL FULKS | 2023-06-30 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1525.56 | 0 | 0 | 0 | 1525.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23180255600 |  | 100343556 |  | 7240212A | 2286366 |  |  | 566 | EX | ABANDN SL/22026164200 | 2600B | SPRING | 495 SPRING ST | 173 | MT | 2023-06-30 | U126604 | U125763 | 2023-04-11 | 2023-12-29 |  |  | WILL FULKS | 2023-06-30 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1015.32 | 0 | 0 | 0 | 1015.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23193122100 |  | 100466889 |  | 6720208G | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE SERVICE | 2621D | LAKESHORE | 100 LAKESHORE DR 169 | 067 | LEX | 2023-06-30 | WISHII | AOC SYST | 2023-06-06 | 2023-06-30 | 2023-07-30 |  | WISHII | 2023-06-30 | 2023-06-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.05 | 4 | 1693.22 | 980.62 | 142.22 | 531.88 | 38.5 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883170200 |  | 100405413 |  | 7376140T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | POWELLS | 1908 POWELLS CK | 195 | PIK | 2023-07-03 | U130172 | U120245 | 2021-01-30 | 2023-07-03 | 2023-12-31 |  | BRIAN PREECE | 2023-07-03 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.1667 | 2 | 209.39 | 197.52 | 0 | 11.87 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22979026400 |  | 100266213 |  | 7364140T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | SHELBY DRY | 2160 SHELBY DRY FK | 195 | SHE | 2023-07-03 | U130172 | U128070 | 2022-02-17 | 2023-07-03 | 2023-12-31 |  | BRIAN PREECE | 2023-07-03 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 4.8333 | 2 | 317.37 | 299.37 | 0 | 18 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23198809600 |  | 100329263 |  | 6720208N |  |  |  | 565 | EX | REPLACE SERV LINE | 2621P | LAKESIDE | 2149 LAKESIDE DR | 067 | LEX | 2023-07-05 | U930915 | U129939 | 2023-07-03 | 2023-07-03 |  |  | ABLAKE | 2023-07-03 | 2023-07-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 5.25 | 2 | 897.41 | 712.27 | 81.82 | 42.82 | 60.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22104890300 |  | 100311079 |  | 6712208N | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | CINDY BLAIR | 778 CINDY BLAIR WY | 067 | LEX | 2023-07-05 | TROE | AOC SYST | 2022-06-01 | 2022-12-01 | 2023-12-31 |  | TROE | 2023-07-05 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 15.6833 | 2 | 1393.42 | 984.69 | 212.02 | 59.21 | 137.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22128588300 |  | 100313703 |  | 6716208B | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE MNFLD | 2621D | ROYALTY | 1356 ROYALTY CT 8 | 067 | LEX | 2023-07-05 | MCRAIG | AOC SYST | 2022-09-01 | 2023-02-28 | 2023-12-31 |  | MCRAIG | 2023-07-05 | 2023-06-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 42.0667 | 7 | 4889.3 | 2359.39 | 1365.87 | 1037.54 | 126.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23026258000 |  |  |  | 7260280O | 2294088 | U132703 |  | 584 | EX | RETIRE PAPER CHART | 2632M | MAPLE | MAPLE DR | 161 | MAY | 2023-07-10 | U462463 | U132703 | 2023-02-14 | 2023-12-01 | 2023-12-01 | 2023-07-05 | JHOBBS | 2023-07-05 | 2023-07-05 |  | F | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00584 | 3200584 |  |  | WP2580 |  |  | 100 | 058432230262580 | 5.9167 | 0 | 555.95 | 350.31 | 0 | 205.64 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026282800 |  |  |  | 6688228L | 2398629 | U126783 |  | 557 | CO | EMER - INSTALL 5'-2" PMMP | 2621P | REGENTS PARK | REGENTS PARK | 073 | FRA | 2024-04-24 |  | U126783 | 2023-07-06 | 2024-03-21 | 2024-04-28 |  | EFGOINS | 2023-07-05 | 2023-11-16 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP2828 |  |  | 100 | 055732230262828 | 6.1667 | 0 | 9124.43 | 4994.36 | 0 | 1868.67 | 1642 | 0 | 232.43 | 386.97
KY | KY - WEST | 2623 | 23026282900 |  |  |  | 6688228L | 2398629 | U126783 |  | 558 | CO | EMER - ABANDON 5'-2" PMMP | 2621P | REGENTS PARK | REGENTS PARK | 073 | FRA | 2024-04-24 |  | U126783 | 2023-07-06 | 2024-03-28 | 2024-04-28 |  | EFGOINS | 2023-07-05 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP2829 |  |  | 100 | 055832230262829 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23192494700 |  | 100268166 |  | 7356256B |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | WINCHESTER | 2341 WINCHESTER AV | 019 | ASH | 2023-07-05 | JCYRUS | U132002 | 2023-06-02 | 2023-06-15 | 2023-07-01 |  | JCYRUS | 2023-07-05 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 6.2833 | 1 | 557.84 | 485.55 | 11.33 | 60.96 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23192497200 |  | 100268167 |  | 7356256B |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | WINCHESTER | 2341 WINCHESTER AV | 019 | ASH | 2023-07-12 | U135005 | U132002 | 2023-06-02 | 2023-06-15 | 2023-07-01 |  | JKEENER | 2023-07-05 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 8 | 1 | 512.03 | 482.99 | 0 | 29.04 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23194984700 |  | 100337635 |  | 6720212E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | 7TH | 154 E 7TH ST | 067 | LEX | 2023-07-06 | U135005 | U132761 | 2023-06-15 | 2024-12-31 |  |  | LSTANFI | 2023-07-05 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.3167 | 3 | 1972.84 | 1347.33 | 255.26 | 324.05 | 46.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23196351300 |  | 100285937 |  | 6764176P |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | MADISON | 154 S MADISON AV | 065 | IRV | 2023-07-06 | U930915 | U133234 | 2023-06-21 | 2023-07-05 | 2023-07-21 |  | DENNING | 2023-07-05 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 24 | 3 | 1914.52 | 1689.69 | 0 | 224.83 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23196520400 |  | 100406124 |  | 6724208E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | PEACHTREE | 436 PEACHTREE RD | 067 | LEX | 2023-07-05 | WISHII | U135005 | 2023-06-22 | 2023-11-03 | 2024-12-31 |  | WISHII | 2023-07-05 | 2023-06-27 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.1333 | 4 | 2197.56 | 1219.05 | 212.02 | 669.69 | 96.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23198985900 |  | 100278289 |  | 6688228B |  |  |  | 565 | EX | GRADE 1 REPLACE SERVICE LINE | 2621P | MOJAVE | 1013 MOJAVE TL | 073 | FRA | 2023-07-12 | U135005 | U129939 | 2023-07-05 | 2023-07-05 | 2023-07-05 |  | CDESPAIN | 2023-07-05 | 2023-07-05 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 33.75 | 4 | 3727.93 | 2236.54 | 0 | 134.49 | 1356.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 08730765100 |  | 100290644 |  | 6720212C |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | OLD PARIS | 1633 OLD PARIS RD | 067 | LEX | 2023-07-06 | LSTONE | SSUTHER | 2008-05-09 | 2022-07-01 | 2023-12-31 |  | LSTONE | 2023-07-06 | 2023-06-26 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.5833 | 6 | 895.94 | 845.74 | 0 | 50.2 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883269000 |  | 100334749 |  | 6724208A | 0779343 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | LIBERTY | 2454 LIBERTY RD | 067 | LEX | 2023-07-06 | MCRAIG | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | MCRAIG | 2023-07-06 | 2022-11-17 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 19.7833 | 9 | 1536.3 | 1086.1 | 37.51 | 412.69 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22100764800 |  | 100452543 |  | 6716208A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | LANE ALLEN | 807 LANE ALLEN RD | 067 | LEX | 2023-07-06 | U930915 | U134723 | 2022-05-16 | 2022-07-01 | 2023-12-31 |  | KKINDER | 2023-07-06 | 2022-07-19 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 30.2333 | 8 | 2884.72 | 1967.62 | 65.22 | 262.1 | 589.78 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026278500 |  |  |  | 6752176B | 2398063 | U128885 |  | 557 | EX | EMER - INSTALL 3'-2" PMMP | 2621P | BYBEE LOOP | 212 BYBEE LOOP | 151 | WAC | 2023-07-14 | U128132 | U128885 | 2023-06-08 | 2023-06-01 | 2023-06-06 | 2023-06-06 | WDENNING | 2023-07-06 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP2785 |  |  | 100 | 055732230262785 |  | 3 | 3085.38 | 1965.64 | 87.53 | 571.54 | 15.4 | 0 | 6.99 | 438.28 | 3
KY | KY - CENTRAL | 2629 | 23026278600 |  |  |  | 6752176B | 2398063 | U128885 |  | 558 | EX | EMER - RETIRE 3'-2" PMMP | 2621P | BYBEE LOOP | 212 BYBEE LOOP | 151 | WAC | 2023-07-14 | U128132 | U128885 | 2023-06-08 | 2023-06-06 | 2023-06-06 | 2023-06-06 | WDENNING | 2023-07-06 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP2786 |  |  | 100 | 055832230262786 | 0.15 | 0 | 10.24 | 9.7 | 0 | 0.54 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026282700 |  |  |  | 6720204J | 2398628 | U461383 |  | 558 | EX | EMER-ABANDON 333' OF 2"PAMP | 2621P | JANNELLE CT | JANNELLE CT | 067 | LEX | 2023-07-24 | U128132 | U461383 | 2023-07-06 | 2023-07-06 | 2023-12-01 | 2023-07-06 | JOSHUA COX | 2023-07-06 | 2023-07-10 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2827 |  |  | 100 | 055832230262827 | 33.3 | 0 | 2936.25 | 2668.43 | 107.37 | 160.45 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23189499300 |  | 100323585 |  | 6716208O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMED - D094448 | 2621D | BELVOIR | 3412 BELVOIR DR | 067 | LEX | 2023-07-07 | U123688 | AOC SYST | 2023-05-18 | 2023-11-17 | 2025-05-31 |  | RSTRONG | 2023-07-06 | 2023-06-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.4333 | 4 | 2000.13 | 1196.09 | 346.53 | 348.61 | 108.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23190059100 |  | 100323608 |  | 6716208P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332500 | 2621P | LANSDOWNE | 3405 LANSDOWNE DR | 067 | LEX | 2023-07-06 | KKINDER | U125208 | 2023-05-22 | 2023-11-17 | 2025-05-31 |  | KKINDER | 2023-07-06 | 2023-06-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.15 | 6 | 1736.52 | 1418.15 | 106.05 | 104.52 | 107.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23199251700 |  | 100352755 |  | 6744208K |  |  |  | 565 | EX | REPLACE SVC LINE 24HR D303643 | 2621P | BLOOMFIELD | 13 N BLOOMFIELD RD | 049 | WIN | 2023-07-07 | U123688 | U135005 | 2023-07-06 | 2023-07-06 | 2023-07-06 |  | NRICHIE | 2023-07-06 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 17.9667 | 3 | 1491.25 | 1136.27 | 165.65 | 68.33 | 121 | 0 | 0 | 0
KY | KY - WEST | 2621 | 20823744500 |  | 100406193 |  | 6732212O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | EASTPOINT | 2560 EASTPOINT DR | 067 | LEX | 2023-07-07 | LSTONE | AOC SYST | 2020-07-01 | 2020-12-31 | 2021-12-31 |  | LSTONE | 2023-07-07 | 2022-11-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 24.3667 | 8 | 1860.56 | 1466.41 | 226.64 | 93.81 | 73.7 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883140700 |  | 100261755 |  | 7344144T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW5679 | PW5679 | 071 | MCD | 2023-07-07 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN HOWARD | 2023-07-07 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 7.65 | 1 | 510.72 | 481.75 | 0 | 28.97 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23026257900 |  |  |  | 7260280O | 2294088 | U132703 |  | 909 | EX | INSTALL MIWI AND SUPER SOLAR | 2600E | MAPLE | MAPLE DR | 161 | MAY | 2023-07-10 | U462463 | U132703 | 2023-02-14 | 2023-12-01 | 2023-12-01 | 2023-07-05 | JUSTIN HOBBS | 2023-07-07 | 2023-07-05 |  | F | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00909 | 3200909 |  |  | WP2579 |  |  | 100 | 090932230262579 | 16.85 | 0 | 1323.01 | 1002.32 | 0 | 318.7 | 0 | 0 | 1.99 | 0
KY | KY - WEST | 2621 | 23189497400 |  | 100323568 |  | 6716204C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMED - D094449 | 2621D | BELVOIR | 3474 BELVOIR DR | 067 | LEX | 2023-07-07 | RSTRONG | AOC SYST | 2023-05-18 | 2023-11-17 | 2025-05-31 |  | RSTRONG | 2023-07-07 | 2023-06-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25.6333 | 6 | 2053.18 | 1245.32 | 337.44 | 394.52 | 75.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23191338700 |  | 100275736 |  | 6684228C |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | FRAZIER | 118 FRAZIER RD | 073 | FRA | 2023-07-07 | BSEXTON | U132002 | 2023-05-30 | 2023-06-09 | 2023-06-25 |  | BSEXTON | 2023-07-07 | 2023-06-20 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 23.8833 | 7 | 1783.44 | 1359.85 | 0 | 423.59 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23196093100 |  | 100318225 |  | 6716204C |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | GREENLAWN | 3430 GREENLAWN DR | 067 | LEX | 2023-07-07 | WISHII | U135005 | 2023-06-20 | 2023-12-29 |  |  | WISHII | 2023-07-07 | 2023-06-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.4667 | 3 | 1740.78 | 854.04 | 295.55 | 527.39 | 63.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23199259700 |  | 100268975 |  | 6736252M |  |  |  | 566 | EX | ABANDON SERV LINE | 2621P | MILLER | 214 N MILLER ST | 097 | CYN | 2023-07-07 | WHIMES | U129939 | 2023-07-06 | 2023-07-06 |  |  | WHIMES | 2023-07-07 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.2667 | 2 | 299.5 | 267.87 | 15.53 | 16.1 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 10841480700 |  | 500010140 |  | 6716236F |  |  |  | 566 | EX | ABANDON SL-TRANSMISSION CLASS | 2621P | BROOKLANE | 101 BROOKLANE DR | 209 | GEO | 2023-09-05 | U135005 | RPOLLY | 2010-05-20 | 2023-12-29 | 2023-12-31 |  | S. BARKER | 2023-07-10 | 2022-11-15 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 122.85 | 18 | 17986.65 | 8409.28 | 0 | 1537.29 | 8040.08 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23026261300 |  |  |  | 7356152A | 2294088 | U132703 |  | 909 | EX | INSTALL MIWI AND SUPER SOLAR | 2600E | LOWER HAROLD 1418 | LOWER HAROLD 1418 | 071 | HAR | 2023-08-15 | U123258 | U132703 | 2023-02-16 | 2023-12-01 | 2023-12-01 | 2023-07-10 | MATT RYAN | 2023-07-10 | 2023-07-10 |  | F | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00909 | 3200909 |  |  | WP2613 |  |  | 100 | 090932230262613 | 25.7833 | 0 | 4877.76 | 1680.75 | 0 | 657.7 | 2530 | 0 | 9.31 | 0
KY | KY - EAST | 2633 | 23026261400 |  |  |  | 7356152A | 2294088 | U132703 |  | 584 | EX | RETIRE PAPER CHART | 2633M | LOWER HAROLD 1418 | LOWER HAROLD 1418 | 071 | HAR | 2023-08-15 | U123258 | U132703 | 2023-02-16 | 2023-12-01 | 2023-12-01 | 2023-07-10 | MATT RYAN | 2023-07-10 |  |  | F | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00584 | 3200584 |  |  | WP2614 |  |  | 100 | 058432230262614 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026271300 |  |  |  | 6712236H | 1961125 | U461383 |  | 575 | EX | OBTAIN ADDITIONAL LAND RIGHTS | 2600E | INDUSTRY | INDUSTRY RD | 209 | GEO | 2023-10-02 | U128132 | U461383 | 2023-04-10 | 2023-09-28 | 2023-10-01 | 2023-07-10 | CHRIS DAVIS | 2023-07-10 |  |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00575 | 3200575 |  |  | WP2713 |  |  | 100 | 057532230262713 |  | 1 | 72514.71 | 0 | 0 | 60000 | 12006.2 | 0 | 508.51 | 0
KY | KY - WEST | 2623 | 23164763800 |  | 100281664 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | POPLAR | 519 POPLAR ST | 209 | GEO | 2023-07-10 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-07-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2631.05 | 0 | 0 | 0 | 2631.05 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164764400 |  | 100281693 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | POPLAR | 618 POPLAR ST | 209 | GEO | 2023-07-10 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-07-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2579.59 | 0 | 0 | 0 | 2579.59 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166668900 |  | 100322628 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 673 BERRY LN | 067 | LEX | 2023-07-10 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-07-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1126.83 | 0 | 0 | 0 | 1126.83 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168508100 |  | 100342653 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ELM | 102 ELM ST | 173 | MT | 2023-07-19 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-07-10 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3690.4 | 0 | 0 | 0 | 3690.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176935000 |  | 100302781 |  | 6712212K | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1208 COLONIAL DR | 067 | LEX | 2023-07-11 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-07-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3554.93 | 0 | 0 | 0 | 3554.93 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23181905800 |  | 100292395 |  | 6720216K | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER | 2621D | SILVER | 1724 SILVER LN | 067 | LEX | 2023-07-10 | TROE | AOC SYST | 2023-04-17 | 2023-05-12 | 2023-06-13 |  | TROE | 2023-07-10 | 2023-04-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 22.2667 | 6 | 1627.93 | 1293.53 | 158.11 | 77.29 | 99 | 0 | 0 | 0
KY | KY - EAST | 2682 | 23192063300 |  | 100426493 |  | 00000000 |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2633S | TEA BERRY | 37 TEA BERRY LN | 119 | MAL | 2023-07-10 | U130172 | U132002 | 2023-06-01 | 2023-06-14 | 2023-06-30 |  | JOHN HOWARD | 2023-07-10 |  |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 16 | 2 | 1062.99 | 1002.72 | 0 | 60.27 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23199792400 |  | 100309725 |  | 6712208H |  |  |  | 565 | EX | SERVICE LINE REPLACE | 2621P | WICHITA | 604 WICHITA DR | 067 | LEX | 2024-04-25 | U128381 | U138726 | 2023-07-10 | 2023-07-10 | 2023-07-10 |  | KYLE KINDER | 2023-07-10 | 2023-07-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.4833 | 2 | 343.97 | 323.83 | 0 | 20.14 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129003900 |  | 100268386 |  | 7356260M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | 14TH | 335 14TH ST | 019 | ASH | 2023-07-11 | RECUMP | U130722 | 2022-09-05 | 2022-12-30 | 2023-12-31 |  | RECUMP | 2023-07-11 | 2023-01-13 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.6333 | 3 | 213.83 | 96.63 | 0 | 117.2 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129010200 |  | 100261252 |  | 7352256K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAXWELL | 1405 MAXWELL ST | 019 | ASH | 2023-07-12 | U135005 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RECUMP | 2023-07-11 | 2023-07-10 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 6.4 | 2 | 1851.89 | 365.33 | 0 | 448.15 | 1038.41 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979047200 |  | 100439929 |  | 7340268E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3# | 2621P | SEATON | 900 SEATON AV | 089 | GRE | 2023-08-01 | DYOUNG | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | RECUMP | 2023-07-11 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.3833 | 1 | 1212.58 | 78.23 | 0 | 95.94 | 1038.41 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23026261500 |  |  |  | 7356152E | 2294088 | U132703 |  | 909 | EX | INSTALL MIWI AND SUPER SOLAR | 2600E | US23 UPPER HAROLD 1419 | US23 UPPER HAROLD 1419 | 071 | HAR | 2023-07-14 | U123258 | U132703 | 2023-02-16 | 2023-12-01 | 2023-12-01 | 2023-07-11 | MATT RYAN | 2023-07-11 | 2023-07-11 |  | F | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00909 | 3200909 |  |  | WP2615 |  |  | 100 | 090932230262615 | 15.2167 | 0 | 4069.95 | 977.93 | 0 | 553.62 | 2530 | 0 | 8.4 | 0
KY | KY - EAST | 2633 | 23026261600 |  |  |  | 7356152E | 2294088 | U132703 |  | 584 | EX | RETIRE PAPER CHART | 2633M | US23 UPPER HAROLD 1419 | US23 UPPER HAROLD 1419 | 071 | HAR | 2023-07-14 | U123258 | U132703 | 2023-02-16 | 2023-12-01 | 2023-12-01 | 2023-07-11 | MATT RYAN | 2023-07-11 | 2023-07-11 |  | F | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00584 | 3200584 |  |  | WP2616 |  |  | 100 | 058432230262616 | 3.9667 | 0 | 388.77 | 254.44 | 0 | 134.33 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23154578100 |  | 500290086 |  | 7352260P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3# | 2621P | WINCHESTER | 601 WINCHESTER AV UNIT 8 | 019 | ASH | 2023-07-27 | DYOUNG | U125763 | 2023-01-10 | 2023-12-29 | 2023-12-31 |  | RECUMP | 2023-07-11 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.85 | 1 | 513.01 | 104.49 | 0 | 128.14 | 280.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166674200 |  | 100322672 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 697 PROVIDENCE RD | 067 | LEX | 2023-07-11 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-07-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1422.42 | 0 | 0 | 0 | 1422.42 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168508900 |  | 100342646 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ELM | 126 ELM ST | 173 | MT | 2023-07-12 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-07-11 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2923.13 | 0 | 0 | 0 | 2923.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176935200 |  | 100302780 |  | 6712212K | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1212 COLONIAL DR | 067 | LEX | 2023-07-11 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-07-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 5373.99 | 0 | 0 | 0 | 5373.99 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23180253000 |  | 100343525 |  | 7240212A | 2286366 |  |  | 565 | EX | RPLC SL/22026164200 | 2600B | SPRING | 407 SPRING ST | 173 | MT | 2023-07-12 | U123111 | U125763 | 2023-04-11 | 2023-12-29 |  |  | LYN STAFFORD | 2023-07-11 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2428.14 | 0 | 0 | 0 | 2428.14 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23180253500 |  | 100343532 |  | 7240212B | 2286366 |  |  | 565 | EX | RPLC SL/22026164200 | 2600B | SPRING | 425 SPRING ST | 173 | MT | 2023-07-12 | U123111 | U125763 | 2023-04-11 | 2023-12-29 |  |  | LYN STAFFORD | 2023-07-11 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2634.68 | 0 | 0 | 0 | 2634.68 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23191339700 |  | 100417763 |  | 6684228C |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | WILKINSON | 966 WILKINSON BV | 073 | FRA | 2023-07-11 | JMARSHA | U132002 | 2023-05-30 | 2023-06-09 | 2023-06-25 |  | JMARSHA | 2023-07-11 | 2023-06-21 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 18.5833 | 4 | 1112.2 | 1049.86 | 0 | 62.34 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23196957000 |  | 100404780 |  | 6716204C |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HIGHTOWER | 324 HIGHTOWER RD | 067 | LEX | 2023-07-12 | U135005 | U135005 | 2023-06-26 | 2023-12-29 |  |  | RJCRAWF | 2023-07-11 | 2023-06-29 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.15 | 4 | 1506.01 | 1044.94 | 336.7 | 62.77 | 61.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23198594300 |  | 100315208 |  | 6716212O |  |  |  | 566 | EX | RETIRE SL HOUSE TO BE DEMO | 2621P | CONN TER | 201 CONN TER | 067 | LEX | 2023-07-11 | KKINDER | U461383 | 2023-06-30 | 2023-08-15 | 2023-08-15 |  | KKINDER | 2023-07-11 | 2023-07-10 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.7167 | 3 | 1135.74 | 1056.67 | 15.53 | 63.54 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23199778000 |  | 100329215 |  | 6720208N |  |  |  | 565 | EX | SERVICE LINE REPLACE | 2621P | LAKESIDE | 2085 LAKESIDE PL | 067 | LEX | 2023-07-11 | JOCHOA | U138726 | 2023-07-10 | 2023-07-10 | 2023-07-10 |  | JOCHOA | 2023-07-11 | 2023-07-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 22.5667 | 4 | 2111.27 | 1369.15 | 333.46 | 323.96 | 84.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23200009400 |  | 100316000 |  | 6716208F |  |  |  | 565 | EX | SERVICE LINE REPLACE | 2621P | SUBURBAN | 169 SUBURBAN CT | 067 | LEX | 2023-07-11 | KKINDER | U138726 | 2023-07-11 | 2023-07-11 |  |  | KKINDER | 2023-07-11 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.85 | 2 | 1110.96 | 516.84 | 526.74 | 31.08 | 36.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23200351900 |  | 100342658 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ELM | 115 ELM ST | 173 | MT | 2023-07-12 | U123111 | U125201 | 2023-07-12 | 2023-09-29 |  |  | LYN STAFFORD | 2023-07-11 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2385.08 | 0 | 0 | 0 | 2385.08 | 0 | 0 | 0
KY | KY - EAST | 2631 | 08726333500 |  | 100240473 |  | 7336272G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | US ROUTE 23 | US ROUTE 23 | 089 | S S | 2023-07-12 | RECUMP | SSUTHER | 2008-04-04 | 2023-07-12 | 2023-12-31 |  | RECUMP | 2023-07-12 | 2022-10-06 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.5333 | 3 | 1168.17 | 139.29 | 0 | 146.23 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883156600 |  | 100261683 |  | 7344144T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY RT 680 | 654 KY RT 680 | 071 | MCD | 2023-07-12 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN HOWARD | 2023-07-12 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 8 | 1 | 807.83 | 505.81 | 0 | 30.4 | 271.62 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883164000 |  | 100265389 |  | 7348260P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | STATE RT 5 | 3218 STATE RT 5 | 089 | ASH | 2023-07-12 | RECUMP | U120245 | 2021-01-30 | 2023-07-12 | 2023-12-31 |  | RECUMP | 2023-07-12 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.5 | 2 | 2519.16 | 198.65 | 0 | 243.69 | 2076.82 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21884241800 |  | 100249247 |  | 7328284B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | CLARK | 748 CLARK ST | 089 | S S | 2023-07-12 | RECUMP | U128293 | 2021-02-04 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-07-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.4167 | 2 | 458.34 | 79.93 | 0 | 98.03 | 280.38 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026257500 |  |  |  | 7352256J | 2294088 | U132703 |  | 909 | EX | INSTALL MIWI AND SUPER SOLAR | 2631M | WINSLOW | 1030 WINSLOW RD | 019 | ASH | 2023-08-03 | U123258 | U132703 | 2023-02-14 | 2023-12-01 | 2023-12-01 | 2023-07-12 | DANIEL ASH | 2023-07-12 | 2023-07-12 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP2575 |  |  | 100 | 090932230262575 | 10.75 | 0 | 3917.88 | 690.8 | 0 | 687.79 | 2530 | 0 | 9.29 | 0
KY | KY - EAST | 2631 | 23026257600 |  |  |  | 7352256J | 2294088 | U132703 |  | 584 | EX | RETIRE PAPER CHAT | 2631M | WINSLOW | 1030 WINSLOW RD | 019 | ASH | 2023-08-03 | U123258 | U132703 | 2023-02-14 | 2023-12-01 | 2023-12-01 | 2023-07-12 | DANIEL ASH | 2023-07-12 | 2023-07-12 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00584 | 3200584 |  |  | WP2576 |  |  | 100 | 058432230262576 | 4.4667 | 0 | 575.02 | 290.06 | 0 | 284.96 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026280800 |  |  |  | 6720212K | 2398452 | U461383 |  | 557 | EX | EMER-INSTALL 62' OF 4"PMLP | 2621P | LIBERTY | 944 LIBERTY | 067 | LEX | 2023-10-18 | U128132 | U461383 | 2023-06-26 | 2023-11-30 | 2023-12-01 | 2023-07-12 | LSTANFI | 2023-07-12 | 2023-07-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2808 | AMRCB |  | 100 | 055732230262808 | 27.5 | 434 | 63661.35 | 3397.79 | 1445.27 | 204.32 | 44570.56 | 0 | 37.7 | 14005.71 | 62
KY | KY - WEST | 2621 | 23026280900 |  |  |  | 6720212K | 2398452 | U461383 |  | 558 | EX | EMER-RETIRE 62' OF 4"BSLP | 2621P | LIBERTY | 944 LIBERTY | 067 | LEX | 2023-10-12 | U128132 | U461383 | 2023-06-26 | 2023-12-01 | 2023-12-01 | 2023-07-12 | LSTANFI | 2023-07-12 | 2023-07-11 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2809 | AMRCB |  | 100 | 055832230262809 | 36.3833 | 0 | 2161.53 | 2035.16 | 0 | 126.37 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164752400 |  | 100281694 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 101 ELM ST | 209 | GEO | 2023-07-13 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-07-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1865.89 | 0 | 0 | 0 | 1865.89 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168136000 |  | 100275104 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WILKINSON | 211 WILKINSON ST | 073 | FRA | 2023-07-12 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-07-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 7236.19 | 0 | 0 | 0 | 7236.19 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168508300 |  | 100342651 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ELM | 108 ELM ST | 173 | MT | 2023-07-12 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-07-12 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2996.51 | 0 | 0 | 0 | 2996.51 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168508400 |  | 100342657 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ELM | 111 ELM ST | 173 | MT | 2023-07-12 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-07-12 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4402.69 | 0 | 0 | 0 | 4402.69 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176935100 |  | 100302722 |  | 6712212K | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1209 COLONIAL DR | 067 | LEX | 2023-07-12 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-07-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2434.42 | 0 | 0 | 0 | 2434.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176935300 |  | 100302779 |  | 6712212K | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1216 COLONIAL DR | 067 | LEX | 2023-07-12 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-07-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2409.49 | 0 | 0 | 0 | 2409.49 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23180254100 |  | 100343565 |  | 7240212A | 2286366 |  |  | 565 | EX | RPLC SL/22026164200 | 2600B | SPRING | 456 SPRING ST | 173 | MT | 2023-07-12 | U123111 | U125763 | 2023-04-11 | 2023-12-29 |  |  | LYN STAFFORD | 2023-07-12 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3657.16 | 0 | 0 | 0 | 3657.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23183304800 |  | 100417493 |  | 6720204C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333512 | 2621P | PIMLICO | 3310 PIMLICO PY | 067 | LEX | 2023-07-12 | HMCKUNE | U125208 | 2023-04-24 | 2023-10-20 | 2025-04-30 |  | HMCKUNE | 2023-07-12 | 2023-05-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 35.15 | 13 | 2360.78 | 1886.68 | 214.96 | 132.64 | 126.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23186475600 |  | 100458195 |  | 6720208P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332775 | 2621P | STONEHEDGE | 404 STONEHEDGE PL | 067 | LEX | 2023-07-13 | U135005 | U125208 | 2023-05-05 | 2023-11-03 | 2025-05-31 |  | MCRAIG | 2023-07-12 | 2023-06-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25.45 | 6 | 4259.86 | 1575.94 | 304.74 | 964.47 | 1414.71 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23200422000 |  | 100271395 |  | 6736252N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MEADOW | 310 MEADOW LN | 097 | CYN | 2023-07-12 | NRICHIE | U138726 | 2023-07-12 | 2023-06-21 | 2024-12-31 |  | NRICHIE | 2023-07-12 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26290021 | 4.7833 | 3 | 5389.56 | 2186.18 | 286.05 | 131.47 | 2785.86 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883215500 |  | 100432511 |  | 7332288O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | DICKERSON | DICKERSON RD | 089 | S S | 2023-07-13 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-07-13 | 2022-10-06 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.7667 | 3 | 1349.75 | 149.2 | 0 | 162.14 | 1038.41 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883313100 |  | 100417455 |  | 7348264A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3# | 2621P | ROUTE 3 | ROUTE 3 | 127 | LOU | 2023-07-13 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-07-13 | 2022-11-17 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.9 | 3 | 1347.23 | 158.12 | 0 | 150.7 | 1038.41 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22100900000 |  | 500891109 |  | 6716212F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | TRAFTON | 107 TRAFTON ST 2120 | 067 | LEX | 2023-07-13 | U930915 | U134723 | 2022-05-16 | 2022-07-01 | 2023-12-31 |  | DMEDLEY | 2023-07-13 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.15 | 2 | 626.63 | 323.46 | 0 | 303.17 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979050900 |  | 500147969 |  | 7356216D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3# | 2621P | BURNS | 403< BURNS ST | 127 | LOU | 2023-07-13 | RECUMP | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | RECUMP | 2023-07-13 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.3833 | 2 | 1339.66 | 135.31 | 0 | 165.94 | 1038.41 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026258100 |  |  |  | 7356252D | 2294088 | U132703 |  | 909 | EX | INSTALL MIWI AND SUPER SOLAR | 2631M | 55TH | 210 55TH ST | 019 | ASH | 2023-08-18 | U123258 | U132703 | 2023-02-14 | 2023-12-01 | 2023-12-01 | 2023-07-13 | DANNY ASH | 2023-07-13 | 2023-07-13 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP2581 |  |  | 100 | 090932230262581 | 21.3167 | 0 | 4339.86 | 1379.84 | 0 | 420.82 | 2530 | 0 | 9.2 | 0
KY | KY - EAST | 2631 | 23026258200 |  |  |  | 7356252D | 2294088 | U132703 |  | 584 | EX | RETIRE PAPER CHART | 2631M | 55TH | 210 55TH ST | 019 | ASH | 2023-08-22 | U123258 | U132703 | 2023-02-14 | 2023-12-01 | 2023-12-01 | 2023-07-13 | DANNY ASH | 2023-07-13 |  |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00584 | 3200584 |  |  | WP2582 |  |  | 100 | 058432230262582 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164752600 |  | 100281698 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 106 ELM ST | 209 | GEO | 2023-07-13 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-07-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.5667 | 1 | 2134.48 | 152.95 | 0 | 9.2 | 1972.33 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164752800 |  | 100281695 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 114 ELM ST | 209 | GEO | 2023-07-17 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-07-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.65 | 1 | 2734.8 | 278.88 | 0 | 16.77 | 2439.15 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166672900 |  | 100322683 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 672 PROVIDENCE RD | 067 | LEX | 2023-07-13 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-07-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2034.25 | 0 | 0 | 0 | 2034.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168508800 |  | 100342660 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ELM | 123 ELM ST | 173 | MT | 2023-07-14 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-07-13 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 6815.69 | 0 | 0 | 0 | 6815.69 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176935400 |  | 100302778 |  | 6712212K | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1220 COLONIAL DR | 067 | LEX | 2023-07-13 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-07-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3375.83 | 0 | 0 | 0 | 3375.83 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23180254400 |  | 100343564 |  | 7240212A | 2286366 |  |  | 565 | EX | RPLC SL/22026164200 | 2600B | SPRING | 460 SPRING ST | 173 | MT | 2023-07-14 | U126604 | U125763 | 2023-04-11 | 2023-12-29 |  |  | WILL FULKS | 2023-07-13 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3800.65 | 0 | 0 | 0 | 3800.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23199263900 |  | 100261519 |  | 7356256E |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | WOODLAND | 1905 WOODLAND AV | 019 | ASH | 2023-07-13 | BROBERT | U133234 | 2023-07-06 | 2023-07-20 | 2023-08-05 |  | BROBERT | 2023-07-13 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 7.4 | 2 | 716.11 | 446.55 | 20.27 | 249.29 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 07687299500 |  | 500532678 |  | 7356216-L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3# | 2621P | ROSE | ROSE LN | 127 | LOU | 2023-07-14 | RECUMP | SSUTHER | 2007-05-16 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-07-14 | 2022-10-06 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.5667 | 4 | 1068.25 | 148.71 | 0 | 36.89 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11882423300 |  | 500784875 |  | 7356216C |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3# | 2621P | LACKEY | 520 N LACKEY AV | 127 | LOU | 2023-07-14 | RECUMP | U906307 | 2011-01-31 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-07-14 | 2023-07-13 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.9333 | 2 | 1062.82 | 225.49 | 0 | 276.57 | 560.76 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11910334400 |  | 100249350 |  | V-1719-33 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3# | 2621P | ROUTE 3 | ROUTE 3 | 127 | LOU | 2023-07-14 | RECUMP | U906631 | 2011-06-07 | 2023-07-14 | 2023-12-31 |  | RECUMP | 2023-07-14 | 2022-10-06 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.7833 | 3 | 1267.45 | 215.36 | 0 | 169.44 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883050700 |  | 500114909 |  | 7352256G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3# | 2621P | MCKNIGHT | 105 MCKNIGHT ST | 019 | ASH | 2023-07-14 | BROBERT | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BROBERT | 2023-07-14 | 2022-12-12 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 27.6833 | 6 | 4827.49 | 1724.83 | 35.11 | 605.52 | 2462.03 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883255300 |  | 100259279 |  | 7356148T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | P40 | P40 | 071 | OSB | 2023-07-14 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN HOWARD | 2023-07-14 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 8 | 1 | 536.21 | 505.81 | 0 | 30.4 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026259200 |  |  |  | 7352256B | 2294088 | U132703 |  | 909 | EX | INSTALL MIWI AND SUPER SOLAR | 2631M | BUCKLEY | 240 BUCKLEY RD | 019 | ASH | 2023-07-31 | U462463 | U132703 | 2023-02-15 | 2023-12-01 | 2023-12-01 | 2023-07-14 | SHANE GIORDANO | 2023-07-14 | 2023-07-14 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP2592 |  |  | 100 | 090932230262592 | 10.7333 | 0 | 4121.74 | 912.67 | 0 | 670.62 | 2530 | 0 | 8.45 | 0
KY | KY - EAST | 2631 | 23026259300 |  |  |  | 7352256B | 2294088 | U132703 |  | 584 | EX | RETIRE PAPER CHART | 2631M | BUCKLEY | 240 BUCKLEY RD | 019 | ASH | 2023-07-31 | U462463 | U132703 | 2023-02-15 | 2023-12-01 | 2023-12-01 | 2023-07-14 | SHANE GIORDANO | 2023-07-14 |  |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00584 | 3200584 |  |  | WP2593 |  |  | 100 | 058432230262593 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026282600 |  |  |  | 6740212N | 2398622 | U128885 |  | 558 | EX | EMER - RETIRE 216'-2" PAMP | 2621P | MIMOSA | 413 MIMOSA LN | 049 | WIN | 2023-07-14 | U128132 | U128885 | 2023-07-06 | 2024-08-28 | 2025-04-17 | 2023-06-27 | NRICHIE | 2023-07-14 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP2826 |  |  | 100 | 055832230262826 |  | 0 | 5057.99 | 1145.91 | 0 | 504.24 | 3407.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164763400 |  | 100281662 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | POPLAR | 513 POPLAR ST | 209 | GEO | 2023-07-14 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-07-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2733.08 | 0 | 0 | 0 | 2733.08 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23180254200 |  | 100343544 |  | 7240212A | 2286366 |  |  | 566 | EX | ABANDON SL/22026164200 | 2600B | SPRING | 457 SPRING ST | 173 | MT | 2023-07-14 | U126604 | U125763 | 2023-04-11 | 2023-12-29 |  |  | WILL FULKS | 2023-07-14 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26290043 |  | 1 | 2069.67 | 0 | 0 | 0 | 2069.67 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 17026706600 |  |  |  | 6740208C | 1100065 | U461383 |  | 588 | EX | CONVERT FROM GMB TO CAB ACCT | 2600M | ROCKWELL | 5555 ROCKWELL RD | 049 | WIN | 2023-08-02 | U123258 | U461383 | 2017-04-25 | 2023-09-29 | 2023-10-01 | 2023-07-17 | JAMES PASLEY | 2023-07-17 | 2023-05-23 |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00588 | 3200588 |  |  | WP7066 |  |  | 100 | 058832170267066 | 66.0833 | 0 | 14520.06 | 4281.07 | 5955.82 | 1157.01 | 3126.16 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883239500 |  | 100251378 |  | 7336268T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3# | 2621P | SEATON | 1101 SEATON AV | 089 | GRE | 2023-07-18 | U135005 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-07-17 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.9333 | 1 | 1409.55 | 166.68 | 0 | 204.46 | 1038.41 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22136983600 |  | 100409101 |  | 6716208O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | SURFSIDE | 247 SURFSIDE DR | 067 | LEX | 2023-07-18 | U930915 | AOC SYST | 2022-10-05 | 2023-04-05 | 2023-12-31 |  | RJCRAWF | 2023-07-17 | 2023-03-21 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 24.9 | 10 | 2491.94 | 1498.18 | 193.45 | 104.03 | 696.28 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026261700 |  |  |  | 7356252K | 2294088 | U132703 |  | 909 | EX | INSTALL MIWI AND SUPER SOLAR | 2631M | CATLETT CREEK ROAD | CATLETT CREEK ROAD | 019 | CAT | 2023-08-01 | U123258 | U132703 | 2023-02-16 | 2023-12-01 | 2023-12-01 | 2023-07-17 | DANIEL ASH | 2023-07-17 | 2023-07-17 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP2617 |  |  | 100 | 090932230262617 | 18.1833 | 0 | 3770.68 | 1120.83 | 0 | 111.65 | 2530 | 0 | 8.2 | 0
KY | KY - EAST | 2631 | 23026261800 |  |  |  | 7356252K | 2294088 | U132703 |  | 584 | EX | RETIRE PAPER CHART | 2631M | CATLETT CREEK ROAD | CATLETT CREEK ROAD | 019 | CAT | 2023-08-01 | U123258 | U132703 | 2023-02-16 | 2023-12-01 | 2023-12-01 | 2023-07-17 | DANNY ASH | 2023-07-17 | 2023-07-19 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00584 | 3200584 |  |  | WP2618 |  |  | 100 | 058432230262618 | 5.0333 | 0 | 642.64 | 322.09 | 0 | 320.55 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026281600 |  |  |  | 6764176K | 2398499 | U128885 |  | 557 | EX | EMER-INSTALL 3'-3" PMMP | 2621P | GRINDSTONE | 100 GRINDSTONE RD | 065 | IRV | 2023-07-25 | U128132 | U128885 | 2023-06-28 | 2024-09-25 | 2025-05-27 | 2023-06-22 | WDENNING | 2023-07-17 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP2816 |  |  | 100 | 055732230262816 |  | 3 | 5032.43 | 2732.55 | 490.04 | 466.18 | 631.7 | 0 | 10.5 | 701.46 | 3
KY | KY - CENTRAL | 2629 | 23026281700 |  |  |  | 6764176K | 2398499 | U128885 |  | 558 | EX | EMER-RETIRE 3'-3" PMAP | 2600B | GRINDSTONE | 100 GRINDSTONE RD | 065 | IRV | 2023-07-20 | U128132 | U128885 | 2023-06-28 | 2024-09-30 | 2025-05-27 | 2023-06-22 | WDENNING | 2023-07-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP2817 |  |  | 100 | 055832230262817 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164752700 |  | 100281696 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 112 ELM ST | 209 | GEO | 2023-07-17 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-07-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.3333 | 1 | 2165.7 | 80.97 | 0 | 21.9 | 2062.83 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168135000 |  | 100275029 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WILKINSON | 102 WILKINSON ST | 073 | FRA | 2023-07-25 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-07-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 4158.29 | 0 | 0 | 0 | 4158.29 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168508000 |  | 100342654 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ELM | 101 ELM ST | 173 | MT | 2023-07-17 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-07-17 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4520.8 | 0 | 0 | 0 | 4520.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168508200 |  | 100342656 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ELM | 107 ELM ST | 173 | MT | 2023-07-17 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-07-17 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3449.36 | 0 | 0 | 0 | 3449.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176935700 |  | 100302776 |  | 6712212K | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1228 COLONIAL DR | 067 | LEX | 2023-07-17 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-07-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2432.33 | 0 | 0 | 0 | 2432.33 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23180254800 |  | 100343561 |  | 7240212A | 2286366 |  |  | 565 | EX | RPLC SL/22026164200 | 2600B | SPRING | 466 SPRING ST | 173 | MT | 2023-07-17 | U126604 | U125763 | 2023-04-11 | 2023-12-29 |  |  | WILL FULKS | 2023-07-17 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3113.69 | 0 | 0 | 0 | 3113.69 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23196317600 |  | 100318223 |  | 6716204C |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | GREENLAWN | 3436 GREENLAWN DR | 067 | LEX | 2023-07-17 | WISHII | U135005 | 2023-06-21 | 2023-12-29 |  |  | WISHII | 2023-07-17 | 2023-07-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.8 | 4 | 1869.24 | 879.24 | 384.68 | 533.82 | 71.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23198965100 |  | 100271316 |  | 6736252N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D304911 | 2621P | SHERWOOD | 110 SHERWOOD DR | 097 | CYN | 2023-07-17 | U930915 | U135005 | 2023-07-05 | 2024-01-03 | 2025-07-31 |  | NRICHIE | 2023-07-17 | 2023-07-14 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 47.8333 | 8 | 8929.33 | 2996.79 | 353.1 | 709.19 | 4870.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19681322600 |  | 100292481 |  | 6720216J |  |  |  | 565 | EX | REPLACE SL - MOVE METER | 2621P | DOVER | 573 DOVER RD | 067 | LEX | 2023-07-19 | U930915 | U125208 | 2019-02-14 | 2020-02-07 |  |  | TROE | 2023-07-18 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24 | 3 | 1800.82 | 1351.95 | 254.29 | 81.28 | 113.3 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883132500 |  | 100265636 |  | 7348252A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3# | 2621P | STATE RT 5 | 7110 STATE RT 5 | 019 | ASH | 2023-07-18 | RECUMP | U120245 | 2021-01-30 | 2022-01-03 | 2023-12-31 |  | RECUMP | 2023-07-18 | 2022-10-21 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 31.6667 | 11 | 4789.41 | 1984.49 | 0 | 598.31 | 2206.61 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129010600 |  | 100265535 |  | 7348252H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE# | 2621P | US ROUTE 60 | 7023 US ROUTE 60 2 | 019 | ASH | 2023-07-31 | DYOUNG | U130722 | 2022-09-05 | 2022-12-30 |  |  | RECUMP | 2023-07-18 | 2023-07-17 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 8.9333 | 2 | 1991.76 | 509.78 | 0 | 599.33 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129041800 |  | 100444169 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ** NEED 811 INFO ** | ** NEED 811 INFO ** | 159 | INE | 2023-07-18 | U129900 | U130722 | 2022-09-05 | 2023-07-12 |  |  | JKIRK | 2023-07-18 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - WEST | 2621 | 22129085100 |  | 100314526 |  | 6716212L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | UPPER | 423 S UPPER ST 1F | 067 | LEX | 2023-07-18 | U930915 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JOCHOA | 2023-07-18 | 2023-05-19 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 20.75 | 6 | 2134.61 | 1263 | 17.64 | 75.59 | 778.38 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026259400 |  |  |  | 7356216D | 2294088 | U132703 |  | 909 | EX | INSTALL MIWI AND SUPER SOLAR | 2631M | PIKE | 309 PIKE ST RR | 127 | LOU | 2023-08-01 | U123258 | U132703 | 2023-02-15 | 2023-12-01 | 2023-12-01 | 2023-07-18 | DANNY ASH | 2023-07-18 | 2023-07-18 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP2594 |  |  | 100 | 090932230262594 | 11.1 | 0 | 3579.71 | 713.37 | 0 | 327.86 | 2530 | 0 | 8.48 | 0
KY | KY - EAST | 2631 | 23026259500 |  |  |  | 7356216D | 2294088 | U132703 |  | 584 | EX | RETIRE PAPER CHART | 2631M | PIKE | 309 PIKE ST RR | 127 | LOU | 2023-08-01 | U123258 | U132703 | 2023-02-15 | 2023-12-01 | 2023-12-01 | 2023-07-18 | DANNY ASH | 2023-07-18 | 2023-07-18 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00584 | 3200584 |  |  | WP2595 |  |  | 100 | 058432230262595 | 3.2333 | 0 | 347.11 | 208.35 | 0 | 138.76 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23026282000 |  |  |  | 7324132F | 2398519 | U122858 |  | 561 | EX | INSTALL 40'-4" PMIP | 2600B | HWY 550 | HWY 550 | 119 | HIN | 2023-07-26 | U128132 | U122858 | 2023-07-01 | 2023-07-24 | 2023-07-30 | 2023-07-17 | MBLANKE/CJH C PACK | 2023-07-18 | 2023-07-06 |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00561 | 3200561 |  |  | WP2820 | AMRCB |  | 100 | 056132230262820 | 88.3333 | 720 | 49257.58 | 6086.17 | 7048.25 | 2701.7 | 25125.77 | 0 | 43.04 | 8252.65 | 60
KY | KY - EAST | 2633 | 23026282100 |  |  |  | 7324132F | 2398519 | U122858 |  | 562 | EX | RETIRE 36'-4" BSIP | 2600B | HWY 550 | HWY 550 | 119 | HIN | 2023-07-26 | U128132 | U122858 | 2023-07-01 | 2023-07-28 | 2023-07-30 | 2023-07-17 | MBLANKE/CJH C PACK | 2023-07-18 | 2023-07-18 |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00562 | 3200562 |  |  | WP2821 | AMRCB |  | 100 | 056232230262821 | 1.5167 | 0 | 124.74 | 99.44 | 0 | 25.3 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164755200 |  | 100281660 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | GANO | 519 GANO AV | 209 | GEO | 2023-07-18 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-07-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.4833 | 1 | 2175.58 | 148.76 | 0 | 40.24 | 1986.58 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164761700 |  | 500449434 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 600< PAYNE AV | 209 | GEO | 2023-07-18 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-07-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1928.52 | 0 | 0 | 0 | 1928.52 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168507300 |  | 100342631 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | CLAY | 303 CLAY ST | 173 | MT | 2023-07-19 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-07-18 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3177.83 | 0 | 0 | 0 | 3177.83 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168507400 |  | 100342632 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | CLAY | 307 CLAY ST | 173 | MT | 2023-07-19 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-07-18 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3597.4 | 0 | 0 | 0 | 3597.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176935500 |  | 100302777 |  | 6712212K | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1224 COLONIAL DR | 067 | LEX | 2023-07-18 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-07-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2588.08 | 175.51 | 0 | 10.48 | 2402.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176935900 |  | 100302775 |  | 6712212K | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1232 COLONIAL DR | 067 | LEX | 2023-07-18 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-07-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2096.14 | 0 | 0 | 0 | 2096.14 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23180253600 |  | 100343573 |  | 7240212A | 2286366 |  |  | 565 | EX | RPLC SL/22026164200 | 2600B | SPRING | 426 SPRING ST | 173 | MT | 2023-07-18 | U126604 | U125763 | 2023-04-11 | 2023-12-29 |  |  | WILL FULKS | 2023-07-18 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3432.78 | 0 | 0 | 0 | 3432.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23185312100 |  | 100314527 |  | 6716212L |  |  |  | 566 | EX | ABANDON W/100314526* | 2621P | UPPER | 423 S UPPER ST 2F | 067 | LEX | 2023-07-18 | ABLAKE | U125208 | 2023-05-02 | 2023-07-31 | 2023-08-31 |  | ABLAKE | 2023-07-18 | 2023-05-10 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.3667 | 4 | 153.71 | 145.26 | 0 | 8.45 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23187482200 |  | 100352658 |  | 6744204F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094440 | 2621P | VALLEY | 23 VALLEY CT | 049 | WIN | 2023-07-19 | U123688 | U125208 | 2023-05-11 | 2023-11-10 | 2025-05-31 |  | DENNING | 2023-07-18 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 9.15 | 3 | 1468.82 | 1029.92 | 315.33 | 61.97 | 61.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23187733300 |  | 100351221 |  | 6744208N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303639 | 2621P | HOLIDAY | 114 HOLIDAY RD | 049 | WIN | 2023-07-19 | U123688 | U125208 | 2023-05-12 | 2023-11-10 | 2025-05-31 |  | DENNING | 2023-07-18 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 15.65 | 3 | 1468.71 | 1012.28 | 301.53 | 55.9 | 99 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23198031400 |  | 100279011 |  | 6688228F |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | MAIN | 951 E MAIN ST | 073 | FRA | 2023-07-18 | EFGOINS | U135005 | 2023-06-29 | 2023-12-29 |  |  | EFGOINS | 2023-07-18 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 17.25 | 3 | 1136.05 | 977.2 | 0 | 58.75 | 100.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23198957600 |  | 100354007 |  | 7256280L | 1855043 |  |  | 566 | EX | ABANDON SL - SOII/INSIDE | 2621P | SUTTON | 317 SUTTON ST | 161 | MAY | 2023-07-18 | SDADAMS | U131897 | 2023-07-05 | 2023-10-30 | 2023-10-30 |  | SDADAMS | 2023-07-18 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 18.3833 | 2 | 1230.57 | 1125.41 | 37.51 | 67.65 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23202113100 |  | 100458411 |  | 6704208A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LAUREL | 134 LAUREL WY | 239 | VER | 2023-07-19 | U128410 | U138726 | 2023-07-19 | 2023-07-10 | 2023-07-28 |  | CDESPAIN | 2023-07-18 | 2023-07-18 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 52.1 | 5 | 4030.5 | 3501.1 | 207.76 | 210.54 | 111.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23202114400 |  | 100458660 |  | 6704208A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LAUREL | 136 LAUREL WY | 239 | VER | 2023-07-19 | U128410 | U138726 | 2023-07-19 | 2023-07-19 |  |  | CDESPAIN | 2023-07-18 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.2333 | 2 | 454.67 | 120.85 | 207.76 | 7.26 | 118.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21883063600 |  | 100334625 |  | 6720208D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | LIBERTY | 2184 LIBERTY RD | 067 | LEX | 2023-07-19 | U930915 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | LSTONE | 2023-07-19 | 2023-06-30 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 24.7833 | 8 | 5821.39 | 1523.15 | 0 | 91.28 | 4206.96 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883296900 |  | 100250436 |  | 7340264B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | STATE RT 1 | 1458 STATE RT 1 | 089 | GRE | 2023-07-19 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-07-19 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.15 | 1 | 2686.24 | 125.55 | 0 | 146.4 | 2414.29 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129084400 |  | 100321140 |  | 6716212P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE * | 2621P | LINDEN | 361 LINDEN WK 1F | 067 | LEX | 2023-07-19 | U930915 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RJCRAWF | 2023-07-19 | 2023-06-09 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10.1667 | 7 | 585.47 | 552.73 | 0 | 32.74 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164762000 |  | 500214238 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 708 PAYNE AV | 209 | GEO | 2023-07-19 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-07-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2272.36 | 0 | 0 | 0 | 2272.36 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164762100 |  | 500214240 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 712 PAYNE AV | 209 | GEO | 2023-07-19 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-07-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2274.81 | 0 | 0 | 0 | 2274.81 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168133700 |  | 100275040 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WAPPING | 516 WAPPING ST | 073 | FRA | 2023-07-19 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-07-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 8369.5 | 0 | 0 | 0 | 8369.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168507100 |  | 100342629 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | CLAY | 215 CLAY ST | 173 | MT | 2023-07-20 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-07-19 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3772.91 | 0 | 0 | 0 | 3772.91 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168507200 |  | 100342630 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | CLAY | 219 CLAY ST | 173 | MT | 2023-07-20 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-07-19 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4091.84 | 0 | 0 | 0 | 4091.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176222000 |  | 100331416 |  | 6720212N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333579 | 2621P | OWSLEY | 105 OWSLEY AV | 067 | LEX | 2023-07-20 | U123688 | U125208 | 2023-03-24 | 2023-09-22 | 2025-03-31 |  | SSHIMFE | 2023-07-19 | 2023-04-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 30.1333 | 7 | 2235.64 | 1732.8 | 261.59 | 156.55 | 84.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176936100 |  | 100302774 |  | 6712212K | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1236 COLONIAL DR | 067 | LEX | 2023-07-20 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-07-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2438.05 | 0 | 0 | 0 | 2438.05 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176944800 |  | 100302772 |  | 6712212K | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1240 COLONIAL DR | 067 | LEX | 2023-07-20 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-07-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3056.14 | 0 | 0 | 0 | 3056.14 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23180253400 |  | 100343574 |  | 7240212A | 2286366 |  |  | 565 | EX | RPLC SL/22026164200 | 2600B | SPRING | 424 SPRING ST | 173 | MT | 2023-07-19 | U126604 | U125763 | 2023-04-11 | 2023-12-29 |  |  | WILL FULKS | 2023-07-19 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4399.54 | 0 | 0 | 0 | 4399.54 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23188231700 |  | 100260171 |  | 7352256H | 1635077 |  |  | 565 | EX | AOC ENCROACHMENT - REPLACE | 2621P | CRESTON | 1812 CRESTON PL | 019 | ASH | 2023-07-19 | RECUMP | U125208 | 2023-05-15 | 2023-05-18 |  |  | RECUMP | 2023-07-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 6.2 | 1 | 3004.33 | 353.9 | 241.3 | 410.85 | 1998.28 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23190624600 |  | 500785763 |  | 6716212P |  |  |  | 566 | EX | ABANDON SL - DOWNSTREAM | 2621P | LINDEN | 361 LINDEN WK 2F | 067 | LEX | 2023-07-19 | RJCRAWF | U125208 | 2023-05-24 | 2022-12-30 | 2023-06-14 |  | RJCRAWF | 2023-07-19 | 2023-06-05 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 18.5 | 6 | 1258.13 | 1187.2 | 0 | 70.93 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23196472800 |  | 500204715 |  | 7360248E | 2180320 |  |  | 565 | EX | REPLACE SL | 2600B | MAYO TRAIL | 10005 MAYO TRAIL RD | 019 | CAT | 2023-07-19 | U123965 | U125765 | 2023-06-22 | 2023-12-29 |  |  | CJH DEREK CRAGER/MBLANKE | 2023-07-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 7040.51 | 0 | 0 | 0 | 7040.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23196542100 |  | 100318245 |  | 6716204G |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | GREENLAWN | 3505 GREENLAWN DR | 067 | LEX | 2023-07-19 | U128336 | U135005 | 2023-06-22 | 2023-12-29 |  |  | JOSHUA COX | 2023-07-19 | 2023-07-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 27.95 | 4 | 2040.4 | 1460.58 | 388.6 | 87.82 | 103.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23200402100 |  | 100311183 |  | 6712208O |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | TUDOR | 3204 TUDOR DR | 067 | LEX | 2023-07-19 | KKINDER | U135005 | 2023-07-12 | 2023-12-29 |  |  | KKINDER | 2023-07-19 | 2023-07-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.95 | 4 | 1932.41 | 1199.82 | 548.41 | 71.98 | 112.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23200740200 |  | 100284374 |  | 6764176M |  | U461383 |  | 566 | EX | RETIRE SERVICE LINE PER JTOY | 2621P | RICHMOND | 2680 RICHMOND RD | 065 | IRV | 2023-07-20 | U930915 | U461383 | 2023-07-13 | 2023-07-31 | 2023-07-31 |  | DENNING | 2023-07-19 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 24 | 3 | 1869.52 | 1667.09 | 0 | 202.43 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23201330000 |  | 100325569 |  | 6720208E | 2396339 |  |  | 565 | EX | SERVICE LINE/METER UPGRADE | 2621P | LAKEWOOD | 1226 LAKEWOOD DR | 067 | LEX | 2023-07-20 | U930915 | U135005 | 2023-07-17 | 2023-07-19 | 2023-07-19 |  | RJCRAWF | 2023-07-19 | 2023-07-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 37.7667 | 6 | 7512.4 | 2174.67 | 439.05 | 130.77 | 4767.91 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23201812200 |  | 501296514 |  | 6724204F | 1968324 |  |  | 565 | EX | RPLC SL/19026912301 | 2600B | WESTON | 425 WESTON PK | 067 | LEX | 2023-07-19 | U461309 | U125763 | 2023-07-18 | 2023-12-29 |  |  | R.HUMPHREYS | 2023-07-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 3.5 | 1 | 3192.75 | 209.92 | 265.89 | 56.77 | 2660.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 09800484600 |  | 100334170 |  | 600000000 |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | CLAYTON | 1636 CLAYTON AV | 067 | LEX | 2023-07-21 | U123688 | DPATRIC | 2009-08-18 | 2020-12-31 |  |  | LSTANFI | 2023-07-20 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.1 | 4 | 2143.34 | 1391.8 | 404.25 | 347.29 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11916302700 |  | 100257051 |  | 7348264-J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3# | 2621P | BELLEFONTE | BELLEFONTE RD | 089 | RAC | 2023-07-20 | RECUMP | U124964 | 2011-07-18 | 2023-07-20 | 2023-12-31 |  | RECUMP | 2023-07-20 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.1667 | 1 | 1162.33 | 125.62 | 0 | 154.06 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883193900 |  | 100265382 |  | 7348260P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3# | 2621P | STATE RT 5 | 3130 STATE RT 5 | 019 | ASH | 2023-07-20 | RECUMP | U120245 | 2021-01-30 | 2022-01-03 | 2023-12-31 |  | RECUMP | 2023-07-20 | 2022-12-12 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 16.5167 | 7 | 2675.08 | 1098.92 | 0 | 537.75 | 1038.41 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22026171800 |  |  |  | 7256280K | 2286937 | U122858 |  | 557 | EX | INSTALL 3178'-2" PMIP | 2600B | 4TH | 4TH | 161 | MAY | 2023-09-23 | U128132 | U122858 | 2022-02-25 | 2023-11-02 | 2023-12-31 | 2023-06-13 | TYLER ALLISON | 2023-07-20 | 2023-04-17 |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00557 | 3200557 |  |  | WP1718 | AMRCB |  | 100 | 055732220261718 | 363.3167 | 135654 | 806129.21 | 27892.68 | 281707.22 | 5326.36 | 369173.38 | 0 | 3326.72 | 118702.85 | 2949
KY | KY - CENTRAL | 2632 | 22026171900 |  |  |  | 7256280K | 2286937 | U122858 |  | 558 | EX | RETIRE ~3325'-2" BS,CS & P | 2600B | 4TH | 4TH | 161 | MAY | 2023-08-02 | U128132 | U122858 | 2022-02-25 | 2023-12-29 | 2023-12-31 | 2023-07-14 | TYLER ALLISON | 2023-07-20 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00558 | 3200558 |  |  | WP1719 | AMRCB |  | 100 | 055832220261719 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129041500 |  | 100429161 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BREWER | 123 BREWER DR | 159 | INE | 2023-07-21 | U123688 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JCKIRK | 2023-07-20 | 2023-06-26 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.2833 | 2 | 1446.62 | 147.97 | 0 | 8.9 | 1289.75 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164762500 |  | 500214249 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 730 PAYNE AV | 209 | GEO | 2023-07-20 | U126284 | U125763 | 2023-02-03 | 2023-12-29 |  |  | JOSH PASLEY/TEAM FISHEL | 2023-07-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2762.91 | 0 | 0 | 0 | 2762.91 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164762700 |  | 500214252 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 736 PAYNE AV | 209 | GEO | 2023-07-20 | U126284 | U125763 | 2023-02-03 | 2023-12-29 |  |  | JOSH PASLEY | 2023-07-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2809.46 | 0 | 0 | 0 | 2809.46 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168133000 |  | 100275023 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WAPPING | 417 WAPPING ST | 073 | FRA | 2023-07-20 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-07-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2945.57 | 0 | 0 | 0 | 2945.57 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168506900 |  | 100342628 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | CLAY | 211 CLAY ST | 173 | MT | 2023-07-24 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-07-20 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3492.64 | 0 | 0 | 0 | 3492.64 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168507000 |  | 100342662 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | CLAY | 212 CLAY ST | 173 | MT | 2023-07-24 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-07-20 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2865.25 | 0 | 0 | 0 | 2865.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176936400 |  | 100302771 |  | 6712212K | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1244 COLONIAL DR | 067 | LEX | 2023-07-21 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-07-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1941.43 | 0 | 0 | 0 | 1941.43 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176936600 |  | 100302770 |  | 6712212J | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1248 COLONIAL DR | 067 | LEX | 2023-07-21 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-07-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2096.14 | 0 | 0 | 0 | 2096.14 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23180253300 |  | 100343577 |  | 7240212A | 2286366 |  |  | 565 | EX | RPLC SL/22026164200 | 2600B | SPRING | 416 SPRING ST | 173 | MT | 2023-07-20 | U126604 | U125763 | 2023-04-11 | 2023-12-29 |  |  | WILL FULKS | 2023-07-20 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4407.2 | 0 | 0 | 0 | 4407.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23196541400 |  | 100318205 |  | 6716204G |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | GREENLAWN | 3500 GREENLAWN DR | 067 | LEX | 2023-07-20 | WISHII | U135005 | 2023-06-22 | 2023-12-29 |  |  | WISHII | 2023-07-20 | 2023-07-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 41.1167 | 7 | 2763.28 | 2301.29 | 0 | 405.89 | 56.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23201818000 |  | 100319829 |  | 6716208K |  |  |  | 565 | EX | RPLC SVC LN - MTR MOVE OUT | 2621P | ALBANY | 236 ALBANY RD | 067 | LEX | 2023-07-20 | U930915 | U135005 | 2023-07-18 | 2023-06-30 |  |  | HMCKUNE | 2023-07-20 | 2023-07-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 28.4667 | 4 | 2008.82 | 1436.28 | 399.25 | 86.39 | 86.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23202142800 |  | 500550455 |  | 6688228L | 9717887 |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SARATOGA | 133 SARATOGA | 073 | FRA | 2023-07-21 | U123688 | U126332 | 2023-07-19 | 2023-02-10 | 2024-08-31 |  | EFGOINS | 2023-07-20 | 2023-07-06 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 | 32.8167 | 5 | 5138.94 | 2350.88 | 186.77 | 490.95 | 2110.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23202427900 |  | 100318246 |  | 6716204G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | GREENLAWN | 3507 GREENLAWN DR | 067 | LEX | 2023-07-21 | U128336 | U138726 | 2023-07-20 | 2023-12-29 |  |  | JOSHUA COX | 2023-07-20 | 2023-07-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 36.3 | 9 | 2378.21 | 1808.81 | 357.25 | 108.75 | 103.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23202435200 |  | 100329257 |  | 6720208J |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | LAKESIDE | 2189 LAKESIDE DR | 067 | LEX | 2023-07-20 | U930915 | U138726 | 2023-07-20 | 2023-07-20 |  |  | RJCRAWF | 2023-07-20 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.7667 | 3 | 1311.64 | 797.72 | 352.48 | 78.94 | 82.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23202514700 |  | 100464420 |  | 6684228K |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | GRAHAM | 23 GRAHAM AV | 073 | FRA | 2023-07-21 | U123688 | U137585 | 2023-07-20 | 2023-07-20 | 2023-07-20 |  | BSEXTON | 2023-07-20 | 2023-07-20 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 | 22.6667 | 4 | 2079.5 | 1333.2 | 615.52 | 80.18 | 50.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129024600 |  | 100355367 |  | 7260276B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | ARRINGTON | 11 ARRINGTON AV | 161 | MAY | 2023-07-21 | U930915 | U130722 | 2022-09-05 | 2023-09-15 | 2023-09-15 |  | SDADAMS | 2023-07-21 | 2023-07-19 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 15.3667 | 3 | 1482 | 944.3 | 0 | 537.7 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23026256300 |  | 501341019 |  | 7356152E | 2395382 | U128885 |  | 555 | EX | INSTALL 130'-2" PMIP | 2600B | 2ND | 40 2ND ST | 071 | HAR | 2023-08-07 | U128132 | U128885 | 2023-02-09 | 2023-07-26 | 2023-07-31 | 2023-07-21 | MBLANKE/CJH C PACK | 2023-07-21 | 2023-07-20 |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00555 | 3200555 |  |  | WP2563 |  |  | 100 | 055532230262563 | 20.95 | 258 | 19141.35 | 1360.16 | 0 | 214.22 | 13783.32 | 0 | 6.13 | 3777.52 | 129
KY | KY - WEST | 2623 | 23164762600 |  | 500214250 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 732 PAYNE AV | 209 | GEO | 2023-07-21 | U124003 | U125763 | 2023-02-03 | 2023-12-29 |  |  | BPULLIAM/FISHEL | 2023-07-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2731.06 | 0 | 0 | 0 | 2731.06 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164762900 |  | 500214254 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 740 PAYNE AV | 209 | GEO | 2023-07-21 | U124003 | U125763 | 2023-02-03 | 2023-12-29 |  |  | BPULLIAM/FISHEL | 2023-07-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2747.41 | 0 | 0 | 0 | 2747.41 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168508700 |  | 100342659 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ELM | 117 ELM ST | 173 | MT | 2023-07-24 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-07-21 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4748.56 | 0 | 0 | 0 | 4748.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176936800 |  | 100302769 |  | 6712212J | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1252 COLONIAL DR | 067 | LEX | 2023-07-21 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-07-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3142.01 | 0 | 0 | 0 | 3142.01 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23180252900 |  | 100343579 |  | 7240212A | 2286366 |  |  | 565 | EX | RPLC SL/22026164200 | 2600B | SPRING | 406 SPRING ST 1 | 173 | MT | 2023-07-21 | U126604 | U125763 | 2023-04-11 | 2023-12-29 |  |  | WILL FULKS | 2023-07-21 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3770.28 | 0 | 0 | 0 | 3770.28 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23188229900 |  | 100260199 |  | 7352256H | 1635077 |  |  | 565 | EX | AOC ENCROACHMENT - REPLACE | 2621P | BEVERLY | 1315 BEVERLY BV | 019 | ASH | 2023-07-21 | RECUMP | U125208 | 2023-05-15 | 2023-05-18 |  |  | RECUMP | 2023-07-21 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 4 | 1 | 2567.84 | 228.34 | 40.23 | 280.09 | 2019.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23196537400 |  | 100324435 |  | 6720204E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | VENETIAN | 1151 VENETIAN WY | 067 | LEX | 2023-07-21 | WISHII | U135005 | 2023-06-22 | 2023-12-29 |  |  | WISHII | 2023-07-21 | 2023-07-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.0833 | 3 | 942.08 | 795.24 | 0 | 85.24 | 61.6 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23202736700 |  | 500554435 |  | 6688228O | 2291968 |  |  | 565 | EX | RPLC SL/23026256000 | 2600B | VERSAILLES | 650 VERSAILLES RD | 073 | FRA | 2023-07-21 | U126285 | U136332 | 2023-07-21 | 2023-12-21 |  |  | DDAVIS | 2023-07-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | AMRCB |  | 100 | 056532B26230032 |  | 1 | 2459.62 | 0 | 0 | 0 | 2459.62 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23200015600 |  | 100247114 |  | 7352256L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D259513 | 2621P | WILLIS | 3412 WILLIS AV | 019 | ASH | 2023-07-25 | U135005 | U135005 | 2023-07-11 | 2023-07-13 | 2023-07-31 |  | MCOLLET | 2023-07-22 | 2023-07-19 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 43.0167 | 6 | 5563.62 | 2814.84 | 184.4 | 2506.08 | 58.3 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23202735700 |  | 100247115 |  | 7352256L |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | WILLIS | 3416 WILLIS AV | 019 | ASH | 2023-07-25 | U135005 | U134852 | 2023-07-21 | 2023-07-21 |  |  | MCOLLET | 2023-07-22 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 324.47 | 0 | 273.87 | 0 | 50.6 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883125700 |  | 100429671 |  | 7356132T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | LEFT PIN HOOK | 565 LEFT PIN HOOK HL | 071 | HAR | 2023-07-24 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN HOWARD | 2023-07-24 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 8 | 1 | 536.21 | 505.81 | 0 | 30.4 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21884221900 |  | 100410519 |  | 7320280B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3# | 2621P | FIREBRICK | FIREBRICK RD | 135 | FIR | 2023-07-24 | RECUMP | U128293 | 2021-02-04 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-07-24 | 2023-07-13 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 7.3 | 3 | 1555.88 | 422.11 | 0 | 251.12 | 882.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026283400 |  |  |  | 6716216L | 2398662 | U122858 |  | 557 | EX | EMER - INSTALL 5'-3" PMMP | 2621P | REDWOOD | 1054 REDWOOD DR | 067 | LEX | 2023-08-28 | U128132 | U122858 | 2023-07-10 | 2024-09-30 | 2025-05-03 | 2023-07-10 | MCRAIG | 2023-07-24 | 2023-07-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2834 |  |  | 100 | 055732230262834 | 0.25 | 5 | 4261.01 | 2700.8 | 249.46 | 686.68 | 0 | 0 | 10.1 | 613.97 | 5
KY | KY - WEST | 2621 | 23026283500 |  |  |  | 6716216L | 2398662 | U122858 |  | 558 | EX | EMER - RETIRE 5'-3" PMP | 2621P | REDWOOD | 1054 REDWOOD DR | 067 | LEX | 2023-08-11 | U128132 | U122858 | 2023-07-10 | 2024-09-30 | 2025-05-03 | 2023-07-10 | MCRAIG | 2023-07-24 | 2023-07-11 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2835 |  |  | 100 | 055832230262835 | 0.2 | 0 | 36.39 | 21.76 | 0 | 14.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164761800 |  | 500214232 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 700 PAYNE AV | 209 | GEO | 2023-07-24 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-07-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3058.35 | 0 | 0 | 0 | 3058.35 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168517400 |  | 100342456 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | SYCAMORE | 211 N SYCAMORE ST | 173 | MT | 2023-07-25 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-07-24 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3746.78 | 0 | 0 | 0 | 3746.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176937000 |  | 100302768 |  | 6712212N | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1256 COLONIAL DR | 067 | LEX | 2023-07-24 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-07-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2646.99 | 0 | 0 | 0 | 2646.99 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23180253200 |  | 100343578 |  | 7240212A | 2286366 |  |  | 565 | EX | RPLC SL/22026164200 | 2600B | SPRING | 412 SPRING ST | 173 | MT | 2023-07-24 | U126604 | U125763 | 2023-04-11 | 2023-12-29 |  |  | WILL FULKS | 2023-07-24 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4608.86 | 0 | 0 | 0 | 4608.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23196538300 |  | 100404607 |  | 6716204J |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | TANGLEY | 303 TANGLEY WY | 067 | LEX | 2023-07-24 | WISHII | U135005 | 2023-06-22 | 2023-12-29 |  |  | WISHII | 2023-07-24 | 2023-07-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.5333 | 5 | 1208.09 | 550.5 | 214 | 345.69 | 97.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23201757100 |  | 100347017 |  | 6696212K |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | WOOLDRIDGE | 209 WOOLDRIDGE LN | 239 | VER | 2023-07-24 | U128410 | U135005 | 2023-07-18 | 2023-07-31 | 2023-07-31 |  | CDESPAIN | 2023-07-24 | 2023-07-24 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 43.2667 | 5 | 3840.11 | 2884.49 | 219.86 | 654.36 | 81.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23202737000 |  | 500907254 |  | 6688228K | 2291968 |  |  | 565 | EX | RPLC SL/23026256000 | 2621P | VERSAILLES | 640 VERSAILLES RD | 073 | FRA | 2023-07-24 | U126285 | U136332 | 2023-07-21 | 2023-12-21 |  |  | DDAVIS | 2023-07-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | AMRCB |  | 100 | 056532B26230032 |  | 1 | 2581.05 | 0 | 0 | 0 | 2581.05 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23202738700 |  | 100435612 |  | 6688228O | 2291968 |  |  | 565 | EX | RPLC SL/23026256000 | 2600B | VERSAILLES | 634 VERSAILLES RD | 073 | FRA | 2023-07-24 | U126285 | U136332 | 2023-07-21 | 2023-12-21 |  |  | DDAVIS | 2023-07-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | AMRCB |  | 100 | 056532B26230032 |  | 1 | 2539.95 | 0 | 0 | 0 | 2539.95 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23203117400 |  | 100342457 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | SYCAMORE | 215 N SYCAMORE ST | 173 | MT | 2023-07-25 | U123111 | U125763 | 2023-07-24 | 2023-12-29 |  |  | LYN STAFFORD | 2023-07-24 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2822.15 | 0 | 0 | 0 | 2822.15 | 0 | 0 | 0
KY | KY - EAST | 2631 | 13175750100 |  | 100240471 |  | 7336272G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | US ROUTE 23 | US ROUTE 23 | 089 | S S | 2023-07-25 | RECUMP | U125201 | 2013-11-15 | 2023-07-24 | 2023-12-31 |  | RECUMP | 2023-07-25 | 2022-10-06 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.0833 | 3 | 1139.04 | 168.05 | 0 | 88.34 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883120900 |  | 500017143 |  | 7348248K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3# | 2621P | STATE RT 2 | STATE RT 2 | 089 | GRE | 2023-07-25 | RECUMP | U120245 | 2021-01-30 | 2023-07-25 | 2023-12-31 |  | RECUMP | 2023-07-25 | 2022-10-06 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.98333 | 3 | 946.82 | 48.59 | 0 | 15.58 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883126300 |  | 100257058 |  | 7348264I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3# | 2621P | OAKLAND | 40 OAKLAND CT A | 089 | RAC | 2023-07-25 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-07-25 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.1833 | 1 | 1090.92 | 126.72 | 0 | 81.55 | 882.65 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026279800 |  | 501350437 |  | 6716232J | 2398315 | U126783 |  | 555 | EX | INSTALL 1800'-2" PMMP | 2600B | OXFORD LANDING | 131 OXFORD LANDING DR | 209 | GEO | 2023-08-08 | U136251 | U126783 | 2023-06-20 | 2023-08-16 | 2023-08-31 | 2023-07-24 | DEREK PAYTON | 2023-07-25 | 2023-07-17 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2798 |  |  | 100 | 055532230262798 | 38.9833 | 9035 | 53278.51 | 2463.01 | 4117.01 | 148.39 | 37926.29 | 0 | 97.13 | 8526.68 | 1807
KY | KY - EAST | 2631 | 23026284800 |  |  |  | 7352256L | 2398947 | U122858 |  | 557 | EX | EMER - INSTALL 40'-4" PMLP | 2621P | WILLIS | 3412 WILLIS ST | 019 | ASH | 2023-09-12 | U128132 | U122858 | 2023-07-20 | 2024-03-27 | 2024-03-31 | 2023-07-21 | MCOLLET | 2023-07-25 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP2848 | AMRCB |  | 100 | 055732230262848 | 2.0833 | 34 | 630.98 | 138.17 | 0 | 347.54 | 45.1 | 0 | 1.36 | 98.81 | 34
KY | KY - EAST | 2631 | 23026284900 |  |  |  | 7352256L | 2398947 | U122858 |  | 558 | EX | EMER - RETIRE 40'-4" BSLP | 2621P | WILLIS | 3412 WILLIS ST | 019 | ASH | 2023-07-31 | U128132 | U122858 | 2023-07-20 | 2024-03-28 | 2024-03-31 | 2023-07-21 | MCOLLET | 2023-07-25 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP2849 | AMRCB |  | 100 | 055832230262849 | 1.9833 | 0 | 451.35 | 128.42 | 0 | 322.93 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026285800 |  |  |  | 6712228N | 2399065 | U461383 |  | 557 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | 2621P | MARKETPLACE | 111 MARKETPLACE CR | 209 | GEO | 2023-08-08 | U136251 | U461383 | 2023-07-27 | 2023-07-24 | 2023-07-25 | 2023-07-27 | CDESPAIN | 2023-07-25 | 2023-07-28 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP2858 |  |  | 100 | 055732230262858 | 16 | 6 | 8976.29 | 3676.03 | 130.02 | 221.03 | 3491.3 | 0 | 11.19 | 1446.72 | 3
KY | KY - WEST | 2623 | 23026285900 |  |  |  | 6712228N | 2399065 | U461383 |  | 558 | EX | EMER-RETIRE 3' OF 2"PMMP MAIN | 2621P | MARKETPLACE | 111 MARKETPLACE CR | 209 | GEO | 2023-08-08 | U136251 | U461383 | 2023-07-27 | 2023-07-25 | 2023-07-25 | 2023-07-27 | CDESPAIN | 2023-07-25 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP2859 |  |  | 100 | 055832230262859 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164761900 |  | 500214236 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 704 PAYNE AV | 209 | GEO | 2023-07-25 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-07-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2269.91 | 0 | 0 | 0 | 2269.91 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168135600 |  | 100467873 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WILKINSON | 201 WILKINSON ST D | 073 | FRA | 2023-07-17 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-07-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3459.36 | 222.46 | 0 | 115.57 | 3121.33 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168135800 |  | 100467874 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WILKINSON | 203 WILKINSON ST E | 073 | FRA | 2023-07-25 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-07-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3166.43 | 0 | 0 | 0 | 3166.43 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168517500 |  | 100342620 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | SYCAMORE | 212 N SYCAMORE ST | 173 | MT | 2023-07-28 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-07-25 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2707.46 | 0 | 0 | 0 | 2707.46 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168517600 |  | 100342619 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | SYCAMORE | 214 N SYCAMORE ST | 173 | MT | 2023-07-28 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-07-25 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2797.89 | 0 | 0 | 0 | 2797.89 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176937200 |  | 100302767 |  | 6712212N | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1260 COLONIAL DR | 067 | LEX | 2023-07-25 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-07-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2154.31 | 0 | 0 | 0 | 2154.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176937400 |  | 100302766 |  | 6712212N | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1264 COLONIAL DR | 067 | LEX | 2023-07-25 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-07-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2377.76 | 0 | 0 | 0 | 2377.76 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23180252800 |  | 100343522 |  | 7240212A | 2286366 |  |  | 565 | EX | RPLC SL/22026164200 | 2600B | SPRING | 403 SPRING ST 1FL | 173 | MT | 2023-07-25 | U126604 | U125763 | 2023-04-11 | 2023-12-29 |  |  | WILL FULKS | 2023-07-25 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4270.12 | 0 | 0 | 0 | 4270.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23196538500 |  | 100318862 |  | 6716204B |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | TARTAN | 115 TARTAN DR | 067 | LEX | 2023-07-25 | WISHII | U135005 | 2023-06-22 | 2023-12-29 |  |  | WISHII | 2023-07-25 | 2023-07-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 26.15 | 7 | 2509.61 | 1377 | 425.08 | 611.83 | 95.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23196539600 |  | 100324220 |  | 6720204J |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | BEAUFORT | 1442 BEAUFORT DR | 067 | LEX | 2023-07-25 | U128336 | U135005 | 2023-06-22 | 2023-12-29 |  |  | JOSHUA COX | 2023-07-25 | 2023-07-12 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25.4167 | 6 | 2117.08 | 1562.03 | 408.36 | 93.89 | 52.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23198802200 |  | 100308344 |  | 6716212N |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | INGLESIDE | 505 INGLESIDE DR | 067 | LEX | 2023-07-25 | U930915 | U135005 | 2023-07-03 | 2023-12-29 |  |  | KKINDER | 2023-07-25 | 2023-07-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.8 | 6 | 2550.4 | 1060.71 | 70.86 | 63.77 | 1355.06 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23203119200 |  | 100280547 |  | 6688228I |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HICKORY | 259 HICKORY DR | 073 | FRA | 2023-07-26 | U135005 | U135005 | 2023-07-24 | 2023-08-21 | 2023-08-21 |  | MCRAIG | 2023-07-25 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 16.5667 | 2 | 2778.48 | 1041.16 | 549.03 | 1123.39 | 64.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23203278900 |  | 100280402 |  | 6688228F |  |  |  | 565 | EX | REPLACE SL | 2621P | GREENHILL | 137 GREENHILL AV | 073 | FRA | 2023-07-26 | U135005 | U138664 | 2023-07-24 | 2023-07-24 | 2023-07-24 |  | EFGOINS | 2023-07-25 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 20 | 2 | 2521.39 | 1270.96 | 277.32 | 76.41 | 896.7 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23203683200 |  | 500774121 |  | V-804-51 | 0147140 |  |  | 566 | EX | ABANDON SL | 2621P | TETON | 801 TETON TL | 073 | FRA | 2023-07-26 | U135005 | U132864 | 2023-07-25 | 2023-07-25 |  |  | MCRAIG | 2023-07-25 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26230043 | 0.1 | 1 | 28.97 | 6.4 | 15.53 | 7.04 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883243700 |  | 500923003 |  | 7348252D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | REDBUD | 421 REDBUD DR | 019 | ASH | 2023-07-26 | BROBERT | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BROBERT | 2023-07-26 | 2022-10-05 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.5333 | 3 | 750.6 | 212.48 | 10.01 | 140.22 | 387.89 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22137501200 |  | 500974495 |  | 6716212H | 0572368 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 3RD | 616 W 3RD ST | 067 | LEX | 2023-07-27 | U930915 | U130722 | 2022-10-07 | 2022-12-30 |  |  | ABLAKE | 2023-07-26 | 2023-05-04 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 50.8667 | 13 | 3468.78 | 2969.1 | 37.51 | 462.17 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22138982300 |  | 100324815 |  | 6720204A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | SPENDTHRIFT | 3551 SPENDTHRIFT LN | 067 | LEX | 2023-07-26 | U128336 | AOC SYST | 2022-10-13 | 2023-04-13 | 2023-12-31 |  | JOSHUA COX | 2023-07-26 | 2023-07-24 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 25.0833 | 5 | 2160.38 | 1641.61 | 360.65 | 98.72 | 59.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026284000 |  |  |  | 6688228B | 2398759 | U461383 |  | 557 | EX | EMER-INSTALL 2' OF 3"PMMP MAIN | 2621P | COMANCHE | 615 COMANCHE TL | 073 | FRA | 2023-08-11 | U128132 | U461383 | 2023-07-13 | 2023-11-30 | 2024-07-25 | 2023-07-12 | CDESPAIN | 2023-07-26 | 2023-07-19 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP2840 |  |  | 100 | 055732230262840 | 8.7667 | 4 | 14848.12 | 7201.21 | 156.69 | 430.34 | 4823.42 | 0 | 30.98 | 2205.48 | 2
KY | KY - WEST | 2623 | 23026284100 |  |  |  | 6688228B | 2398759 | U461383 |  | 558 | EX | EMER-RETIRE 2' OF 3"PAMP MAIN | 2621P | COMANCHE | 615 COMANCHE TL | 073 | FRA | 2023-08-11 | U128132 | U461383 | 2023-07-13 | 2023-11-30 | 2024-07-25 | 2023-07-12 | CDESPAIN | 2023-07-26 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP2841 |  |  | 100 | 055832230262841 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164762300 |  | 500214244 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 720 PAYNE AV | 209 | GEO | 2023-07-26 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-07-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2221.65 | 0 | 0 | 0 | 2221.65 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164762400 |  | 500214246 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 724 PAYNE AV LOT 13 | 209 | GEO | 2023-07-26 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-07-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2206.95 | 0 | 0 | 0 | 2206.95 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168517200 |  | 100342665 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | SYCAMORE | 132 N SYCAMORE ST | 173 | MT | 2023-08-03 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-07-26 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3550.82 | 0 | 0 | 0 | 3550.82 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168517300 |  | 100342621 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | SYCAMORE | 210 N SYCAMORE ST | 173 | MT | 2023-07-28 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-07-26 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3447.43 | 0 | 0 | 0 | 3447.43 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23171719200 |  | 500867221 |  | 6716216M | 1968251 |  |  | 565 | EX | RPLC SL/22026183100 | 2600B | LEESTOWN | 2025 LEESTOWN RD CABLE | 067 | LEX | 2023-07-28 | U126309 | U125763 | 2023-03-03 | 2023-12-29 |  |  | JAMIE LYNN | 2023-07-26 | 2023-07-26 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 2.1333 | 1 | 2166.96 | 133.01 | 0 | 35.12 | 1998.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176935600 |  | 100302754 |  | 6712212K | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1225 COLONIAL DR | 067 | LEX | 2023-07-27 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-07-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2528.6 | 0 | 0 | 0 | 2528.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176935800 |  | 100302755 |  | 6712212K | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1229 COLONIAL DR | 067 | LEX | 2023-07-27 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-07-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2936.58 | 0 | 0 | 0 | 2936.58 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23180253700 |  | 100343571 |  | 7240212A | 2286366 |  |  | 565 | EX | RPLC SL/22026164200 | 2600B | SPRING | 432 SPRING ST | 173 | MT | 2023-07-26 | U126604 | U125763 | 2023-04-11 | 2023-12-29 |  |  | WILL FULKS | 2023-07-26 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3621.57 | 0 | 0 | 0 | 3621.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23202504600 |  | 100325694 |  | 6720208E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | ANDOVER | 395 ANDOVER DR | 067 | LEX | 2023-07-27 | U930915 | U132761 | 2023-07-20 | 2023-07-21 | 2023-08-10 |  | RJCRAWF | 2023-07-26 | 2023-07-24 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.0167 | 4 | 1734.07 | 1288.67 | 277.69 | 77.51 | 90.2 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23202739300 |  | 100279374 |  | 6688228O | 2291968 |  |  | 565 | EX | RPLC SL/23026256000 | 2600B | VERSAILLES | 632 VERSAILLES RD A | 073 | FRA | 2023-07-27 | U126285 | U136332 | 2023-07-21 | 2023-12-21 |  |  | DDAVIS | 2023-07-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | AMRCB |  | 100 | 056532B26230032 |  | 1 | 4181.78 | 0 | 0 | 0 | 4181.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23204069800 |  | 100291727 |  | 6720216H |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | KINGSTON | 721 KINGSTON RD | 067 | LEX | 2023-07-26 | LSTONE | U138664 | 2023-07-25 | 2023-07-25 | 2023-07-25 |  | LSTONE | 2023-07-26 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 16 | 2 | 1501.46 | 1064.98 | 293.57 | 63.71 | 79.2 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23204156100 |  | 100422669 |  | 6688228A |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | SCHENKEL | 565 SCHENKEL LN 407 | 073 | FRA | 2023-07-27 | U135005 | U134852 | 2023-07-26 | 2023-07-26 | 2023-07-26 |  | EFGOINS | 2023-07-26 | 2023-07-26 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 10.5833 | 3 | 1440.01 | 669.71 | 691.52 | 40.28 | 38.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 03534021500 |  | 100345821 |  | 6696212H | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | BIG SINK | BIG SINK RD | 239 | VER | 2023-07-31 | U126332 | DMCCULL | 2003-03-18 | 2022-07-01 | 2023-12-31 |  | S BARKER | 2023-07-27 | 2022-11-17 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 13.5333 | 5 | 1465.49 | 877.08 | 0 | 52.73 | 535.68 | 0 | 0 | 0
KY | KY - WEST | 2623 | 03534022000 |  | 100452669 |  | 6696212H | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | BIG SINK | BIG SINK RD | 239 | VER | 2023-07-31 | U126332 | DMCCULL | 2003-03-18 | 2022-07-01 | 2023-12-31 |  | S BARKER | 2023-07-27 | 2022-10-06 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 2.8 | 2 | 716.49 | 170.55 | 0 | 10.26 | 535.68 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026256000 |  |  |  | 6688228O | 2291968 | U132703 |  | 557 | EX | INSTALL 800'OF 2"PMMP MAIN | 2600E | TIMBERLAWN | TIMBERLAWN | 073 | FRA | 2023-09-01 | U136251 | U132703 | 2023-02-08 | 2023-10-11 | 2023-10-31 | 2023-07-19 | DDAVIS | 2023-07-27 | 2023-07-13 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP2560 | AMRCB |  | 100 | 055732230262560 | 63.5 | 5792 | 92592.66 | 4988.65 | 3341.95 | 1727.73 | 66410.13 | 0 | 209.56 | 15914.64 | 724
KY | KY - WEST | 2621 | 23026284500 |  |  |  | 6720212A | 2398833 | U122858 |  | 557 | EX | INSTALL 80'4" PMLP | 2621P | KEES | 1000 KEES RD | 067 | LEX | 2023-12-07 | U128132 | U122858 | 2023-07-17 | 2024-08-26 | 2025-04-25 | 2023-07-27 | LSTANFI | 2023-07-27 | 2023-07-24 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2845 | AMRCB |  | 100 | 055732230262845 | 58.5667 | 540 | 23619.02 | 3145.09 | 4496.43 | 341.83 | 11702.97 | 0 | 22.07 | 3910.63 | 60
KY | KY - WEST | 2621 | 23026284600 |  |  |  | 6720212A | 2398833 | U122858 |  | 558 | EX | RETIRE 80'-4" BSLP | 2621P | KEES | 1000 KEES RD | 067 | LEX | 2023-12-07 | U128132 | U122858 | 2023-07-17 | 2024-08-30 | 2025-04-25 | 2023-07-27 | LSTANFI | 2023-07-27 | 2023-07-24 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2846 | AMRCB |  | 100 | 055832230262846 | 44.2333 | 0 | 4684.11 | 4418.56 | 0 | 265.55 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026285300 |  |  |  | 6716208G |  | U122858 |  | 558 | EX | EMER - RETIRE 159'-3"BSLP | 2621P | NICHOLASVILLE | NICHOLASVILLE | 067 | LEX | 2023-10-12 | U128132 | U122858 | 2023-07-25 | 2023-07-24 | 2023-07-24 | 2023-07-24 | KKINDER | 2023-07-27 | 2023-07-26 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2853 | AMRCB |  | 100 | 055832230262853 | 3.4333 | 0 | 5197.96 | 2678.16 | 695.09 | 208.88 | 1615.83 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164762200 |  | 500214242 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | PAYNE | 716 PAYNE AV | 209 | GEO | 2023-07-27 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-07-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2353.21 | 0 | 0 | 0 | 2353.21 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168506300 |  | 100342455 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | CLAY | 119 CLAY ST | 173 | MT | 2023-07-28 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-07-27 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2490.37 | 0 | 0 | 0 | 2490.37 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168517100 |  | 100342669 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | SYCAMORE | 128 N SYCAMORE ST | 173 | MT | 2023-07-28 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-07-27 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2161.22 | 0 | 0 | 0 | 2161.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23171719500 |  | 100337857 |  | 6716216M | 1968251 |  |  | 565 | EX | RPLC SL/22026183100 | 2600B | LEESTOWN | 2107 LEESTOWN RD | 067 | LEX | 2023-07-28 | U126309 | U125763 | 2023-03-03 | 2023-12-29 |  |  | JAMIE LYNN | 2023-07-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 3472.54 | 0 | 0 | 0 | 3472.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176936000 |  | 100302756 |  | 6712212K | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1233 COLONIAL DR | 067 | LEX | 2023-07-27 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-07-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2675.22 | 0 | 0 | 0 | 2675.22 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23180253900 |  | 500151690 |  | 7240212A | 2286366 |  |  | 565 | EX | RPLC SL/22026164200 | 2600B | SPRING | 442 SPRING ST | 173 | MT | 2023-07-27 | U126604 | U125763 | 2023-04-11 | 2023-12-29 |  |  | WILL FULKS | 2023-07-27 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 5798.59 | 0 | 0 | 0 | 5798.59 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23187877500 |  | 100323362 |  | 6716208P | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | LANSDOWNE | 3245 LANSDOWNE DR | 067 | LEX | 2023-07-27 | U128336 | AOC SYST | 2023-05-12 | 2023-11-10 | 2024-12-31 |  | JOSHUA COX | 2023-07-27 | 2023-07-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 25.1667 | 6 | 2046.28 | 1491.8 | 408.68 | 89.7 | 56.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23188230800 |  | 100260174 |  | 7352256H |  |  |  | 565 | EX | AOC ENCROACHMENT - REPLACE | 2621P | CRESTON | 1800 CRESTON PL | 019 | ASH | 2023-07-27 | RECUMP | U125208 | 2023-05-15 | 2023-05-18 |  |  | RECUMP | 2023-07-27 | 2023-07-24 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 12.9833 | 3 | 3508.63 | 739.85 | 298.88 | 476.02 | 1993.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23196539000 |  | 100318853 |  | 6716204B |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | TARTAN | 155 TARTAN DR | 067 | LEX | 2023-07-27 | ATWILLI | U135005 | 2023-06-22 | 2023-12-29 |  |  | ATWILLI | 2023-07-27 | 2023-07-12 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.3833 | 3 | 1163.94 | 705.56 | 321.36 | 42.42 | 94.6 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23202063900 |  | 100453869 |  | 7340268E |  |  |  | 566 | EX | ABANDON CSL+ | 2621P | SEATON | 900 SEATON AV APT B | 089 | GRE | 2023-07-27 | RECUMP | U130722 | 2023-07-19 | 2023-12-29 | 2023-12-31 |  | RECUMP | 2023-07-27 | 2023-07-26 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3 | 0 | 1207.4 | 170.09 | 45.19 | 109.47 | 882.65 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23204486100 |  | 500531349 |  | 6692228E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SPENDTHRIFT | 20 SPENDTHRIFT DR | 073 | FRA | 2023-07-28 | U135005 | U138664 | 2023-07-27 | 2023-02-17 | 2024-08-31 |  | MCRAIG | 2023-07-27 | 2023-07-27 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 | 12.85 | 3 | 1919.44 | 1398.84 | 250.59 | 84.11 | 185.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 03533607200 |  | 100344491 |  | 6700224P | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | STEPHENS | 242 W STEPHENS ST | 239 | MID | 2023-07-31 | U126332 | DMCCULL | 2003-03-13 | 2022-07-01 | 2023-12-31 |  | C. DESPAIN | 2023-07-28 | 2022-11-17 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.2 | 2 | 298.5 | 0 | 0 | 0 | 298.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 03533818000 |  | 100335431 |  | 6716216G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | GEORGETOWN | 2073 GEORGETOWN RD | 067 | LEX | 2023-07-28 | U126308 | DMCCULL | 2003-03-17 | 2022-07-01 | 2023-12-31 |  | J ENSMINGER | 2023-07-28 | 2022-11-28 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 22.0333 | 5 | 4075.63 | 1352.71 | 0 | 129.21 | 2593.71 | 0 | 0 | 0
KY | KY - EAST | 2631 | 10874409200 |  | 100249446 |  | V-1718-46 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3# | 2621P | ROUTE 1 | ROUTE 1 | 127 | LOU | 2023-07-28 | RECUMP | U906307 | 2010-12-30 | 2023-07-27 | 2023-12-31 |  | RECUMP | 2023-07-28 | 2022-11-16 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 7.7833 | 5 | 1556.23 | 439.71 | 0 | 233.87 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 12988711800 |  | 500299952 |  | V-1719-34 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3# | 2621P | ROUTE 5 | ROUTE 5 | 127 | LOU | 2023-07-28 | RECUMP | U125208 | 2012-09-18 | 2023-07-28 |  |  | RECUMP | 2023-07-28 | 2022-11-17 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.9667 | 3 | 1337.14 | 282.38 | 20.27 | 151.84 | 882.65 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026278900 |  | 501317280 |  | 6716236J | 2398146 | U126783 |  | 555 | EX | INSTALL 150'-2" PMMP | 2600B | DOVE RUN | DOVE RUN CR LT160 | 209 | GEO | 2023-08-23 | U136251 | U126783 | 2023-06-13 | 2023-08-28 | 2023-08-31 | 2023-07-28 | DEREK PAYTON | 2023-07-28 | 2023-07-27 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2789 |  |  | 100 | 055532230262789 | 25 | 384 | 10151.75 | 1582.73 | 776.1 | 95.19 | 5953.8 | 0 | 11.07 | 1732.86 | 128
KY | KY - WEST | 2621 | 23026279100 |  | 501312430 |  | 6712212I | 2398229 | U461383 |  | 555 | EX | INSTALL 300' OF 2"PMIP MAIN | 2600B | WINNERS | 1590 WINNERS CR | 067 | LEX | 2023-08-03 | U128132 | U461383 | 2023-06-15 | 2023-08-09 | 2023-08-11 | 2023-07-27 | SHAWN DENNIS | 2023-07-28 | 2023-07-26 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2791 |  |  | 100 | 055532230262791 | 6.4 | 322 | 7749.44 | 430.49 | 1099.93 | 107.01 | 4943.7 | 0 | 17.66 | 1150.65 | 161
KY | KY - WEST | 2621 | 23166673900 |  | 100322689 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 692 PROVIDENCE RD | 067 | LEX | 2023-07-31 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-07-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2170.19 | 0 | 0 | 0 | 2170.19 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23180255400 |  | 100343552 |  | 7240212A | 2286366 |  |  | 565 | EX | RPLC SL/22026164200 | 2600B | SPRING | 479 SPRING ST | 173 | MT | 2023-07-28 | U126604 | U125763 | 2023-04-11 | 2023-12-29 |  |  | WILL FULKS | 2023-07-28 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4540.4 | 0 | 0 | 0 | 4540.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23204697600 |  | 500172648 |  | 6712212N | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1268 COLONIAL DR | 067 | LEX | 2023-07-31 | U126603 | U125763 | 2023-07-28 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-07-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2173.7 | 0 | 0 | 0 | 2173.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23204700000 |  | 100436052 |  | 6716204B |  |  |  | 566 | EX | ABANDON SL | 2621P | REYNOLDS | 121 E REYNOLDS RD | 067 | LEX | 2023-07-28 | SSHIMFE | U134852 | 2023-07-28 | 2023-07-28 |  |  | SSHIMFE | 2023-07-28 | 2023-07-28 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 3.0333 | 2 | 487.22 | 421.28 | 0 | 65.94 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 94162801400 |  | 100335430 | 02 | X00000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | GEORGETOWN | 2081 GEORGETOWN RD | 067 | LEX | 2023-07-28 | U126308 | KAUSTIN | 1994-03-04 | 2022-07-01 | 2023-12-31 |  | J ENSMINGER | 2023-07-28 | 2022-11-28 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 33.4833 | 7 | 5670.09 | 2255.65 | 625.4 | 195.33 | 2593.71 | 0 | 0 | 0
KY | KY - WEST | 2623 | 01478523100 |  | 100443158 |  | 6696212G | 1315787 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KENTUCKY | KENTUCKY AV | 239 | VER | 2023-07-31 | U126332 | JTOY | 2001-08-06 | 2023-12-29 | 2023-12-31 |  | S BARKER | 2023-07-31 | 2022-10-06 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.18333 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 05613438300 |  | 100433612 | 16 | 7360216E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3# | 2621P | ROUTE 5 | ROUTE 5 | 127 | LOU | 2023-07-31 | RECUMP | DHORN | 2005-06-08 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-07-31 | 2022-11-17 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.63333 | 3 | 2243.7 | 26.05 | 35.11 | 14.87 | 2167.67 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883200600 |  | 100256693 |  | 7348264B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | VINE | 880 VINE ST | 089 | RAC | 2023-07-31 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-07-31 | 2022-11-09 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.3167 | 2 | 871.8 | 308.92 | 0 | 174.99 | 387.89 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883281500 |  | 100249636 |  | 7332288O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3# | 2621P | STATE RT 5 | STATE RT 5 | 127 | LOU | 2023-07-31 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-07-31 | 2022-10-12 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 6.05 | 3 | 1168.26 | 178.32 | 0 | 107.29 | 882.65 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168516700 |  | 100342674 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | SYCAMORE | 118 N SYCAMORE ST | 173 | MT | 2023-08-02 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFOTRD | 2023-07-31 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2306.39 | 0 | 0 | 0 | 2306.39 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168516900 |  | 100342673 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | SYCAMORE | 122 N SYCAMORE ST | 173 | MT | 2023-08-02 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-07-31 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4191.6 | 0 | 0 | 0 | 4191.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168517000 |  | 100342671 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | SYCAMORE | 124 N SYCAMORE ST | 173 | MT | 2023-08-02 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-07-31 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3230.73 | 0 | 0 | 0 | 3230.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176936200 |  | 500212075 |  | 6712212K | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1237 COLONIAL DR | 067 | LEX | 2023-08-01 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-07-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2298.69 | 0 | 0 | 0 | 2298.69 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176936300 |  | 500025764 |  | 6712212K | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1241 COLONIAL DR | 067 | LEX | 2023-08-01 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-07-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2298.69 | 0 | 0 | 0 | 2298.69 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23180254600 |  | 100343562 |  | 7240212A | 2286366 |  |  | 565 | EX | RPLC SL/22026164200 | 2600B | SPRING | 464 SPRING ST | 173 | MT | 2023-07-31 | U126604 | U125763 | 2023-04-11 | 2023-12-29 |  |  | WILL FULKS | 2023-07-31 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3149.45 | 0 | 0 | 0 | 3149.45 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23200717800 |  | 100334854 |  | 6720212P |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | NEW CIRCLE | 1085 E NEW CIRCLE RD STE 2 | 067 | LEX | 2023-07-31 | LSTANFI | U135005 | 2023-07-13 | 2023-12-29 |  |  | LSTANFI | 2023-07-31 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19 | 2 | 4089.23 | 1304.67 | 0 | 394.75 | 2389.81 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23204419000 |  | 100283587 |  | 6712228A |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | SHOSHONI | 597 SHOSHONI TL | 209 | GEO | 2023-07-31 | DCOLLIN | U129939 | 2023-07-27 | 2023-07-27 |  |  | DCOLLIN | 2023-07-31 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.7167 | 1 | 755.38 | 170.95 | 270.03 | 193.4 | 121 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23204480200 |  | 100329354 |  | 6720208D |  |  |  | 565 | EX | 24HR GAS OFF SL REPLACEMENT | 2621P | SAINT ANN | 220 SAINT ANN DR | 067 | LEX | 2023-08-01 | U930915 | U135005 | 2023-07-27 | 2023-08-10 | 2023-08-10 |  | HMCKUNE | 2023-07-31 | 2023-07-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 28.3833 | 5 | 1634.6 | 1360.67 | 62.31 | 81.82 | 129.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23204726100 |  | 100440928 |  | 7240212A | 2286366 |  |  | 565 | EX | RPLC SL/22026164200 | 2600B | SPRING | 462 SPRING ST | 173 | MT | 2023-07-31 | U126604 | U125763 | 2023-07-28 | 2023-12-29 |  |  | WILL FULKS | 2023-07-31 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4004.03 | 0 | 0 | 0 | 4004.03 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21884250800 |  | 100244912 |  | 7356216D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3# | 2621P | CLAY | 416 N CLAY ST | 127 | LOU | 2023-08-01 | RECUMP | U128293 | 2021-02-04 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-01 | 2022-12-06 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 24.7 | 5 | 3244.98 | 1632.57 | 31.39 | 698.37 | 882.65 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22123462900 |  | 500550474 |  | 6688228L | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMED - D303159 | 2623D | SARATOGA | 114 SARATOGA | 073 | FRA | 2023-08-02 | U135005 | AOC SYST | 2022-08-11 | 2023-02-10 | 2024-08-31 |  | MCRAIG | 2023-08-01 | 2023-01-26 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 | KYACA |  | 100 | 056532B26230021 | 24.9333 | 10 | 2978.57 | 1569.05 | 0 | 1305.02 | 104.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22979028100 |  | 100272184 |  | 6684228O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | LOGAN | 514 LOGAN ST | 073 | FRA | 2023-08-02 | U135005 | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | EFGOINS | 2023-08-01 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 15 | 2 | 1688.9 | 762.15 | 883.03 | 43.72 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164756100 |  | 100281706 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | LOCUST | 607 LOCUST ST | 209 | GEO | 2023-08-01 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1957.18 | 0 | 0 | 0 | 1957.18 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168516400 |  | 100342681 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | SYCAMORE | 115 N SYCAMORE ST | 173 | MT | 2023-08-02 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-01 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 5243.78 | 0 | 0 | 0 | 5243.78 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168516500 |  | 100342675 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | SYCAMORE | 116 N SYCAMORE ST 1F | 173 | MT | 2023-08-02 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-01 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3314.28 | 0 | 0 | 0 | 3314.28 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168516600 |  | 100342682 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | SYCAMORE | 117 N SYCAMORE ST | 173 | MT | 2023-08-02 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-01 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2960.31 | 0 | 0 | 0 | 2960.31 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168516800 |  | 100342684 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | SYCAMORE | 121 N SYCAMORE ST APT B | 173 | MT | 2023-08-02 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-01 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2414.38 | 0 | 0 | 0 | 2414.38 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23174568700 |  | 100283586 |  | 6712228A |  |  |  | 565 | EX | REPLACE SERVICE LINE - D305597 | 2621P | SEMINOLE | 501 SEMINOLE TL | 209 | GEO | 2023-08-01 | DCOLLIN | U125208 | 2023-03-17 | 2023-09-15 | 2025-03-31 |  | DCOLLIN | 2023-08-01 | 2023-07-27 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 37.4833 | 7 | 4121.83 | 2374.42 | 270.03 | 1350.88 | 126.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23175428400 |  | 100283562 |  | 6712228A | 1635077 |  |  | 565 | EX | SERVICE LINE - REPLACE D333576 | 2623D | IROQUOIS | 595 IROQUOIS TL | 209 | GEO | 2023-08-01 | DCOLLIN | AOC SYST | 2023-03-21 | 2023-08-01 | 2025-03-31 |  | DCOLLIN | 2023-08-01 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 15.9 | 2 | 1848.17 | 1060.71 | 281.74 | 455.12 | 50.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176936700 |  | 100302758 |  | 6712212K | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1249 COLONIAL DR | 067 | LEX | 2023-08-02 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2534.82 | 0 | 0 | 0 | 2534.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23196538700 |  | 100318818 |  | 6716204B |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | TARTAN | 154 TARTAN DR | 067 | LEX | 2023-08-01 | WISHII | U135005 | 2023-06-22 | 2023-12-29 |  |  | WISHII | 2023-08-01 | 2023-07-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.4 | 5 | 1832.81 | 858.04 | 364.12 | 545.75 | 64.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23196773400 |  | 100402677 |  | 6716204C |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HIGHTOWER | 303 HIGHTOWER RD | 067 | LEX | 2023-08-01 | WISHII | U135005 | 2023-06-23 | 2023-12-29 |  |  | WISHII | 2023-08-01 | 2023-06-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.3833 | 5 | 1171.66 | 710.08 | 0 | 388.98 | 72.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23200404800 |  | 100311377 |  | 6712204D |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | WALLINGFORD | 3441 WALLINGFORD CT | 067 | LEX | 2023-08-01 | KKINDER | U135005 | 2023-07-12 | 2023-12-29 |  |  | KKINDER | 2023-08-01 | 2023-07-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.8167 | 9 | 2193.15 | 1411.06 | 636.64 | 82.75 | 62.7 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23200707100 |  | 100246243 |  | 7372188L |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | MAIN | MAIN ST | 159 | WAR | 2023-08-02 | U129900 | U135005 | 2023-07-13 | 2023-09-13 | 2023-09-13 |  | BPREECE | 2023-08-01 | 2023-07-31 |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26330031 | 38.6167 | 6 | 2760.15 | 2426.68 | 0 | 142.07 | 191.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23205062800 |  | 100280633 |  | 6688228E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MEREDITH | 130 MEREDITH AV | 073 | FRA | 2023-08-01 | U135005 | U137607 | 2023-07-31 | 2023-07-21 | 2023-08-10 |  | EFGOINS | 2023-08-01 | 2023-07-31 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 | 9.1667 | 4 | 728.89 | 414.83 | 184.78 | 24.78 | 104.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23205390500 |  | 100407662 |  | 7256276I |  |  |  | 565 | EX | REPLACE SERVICE LINE - DAMAGE | 2621P | CALVERT | 2282 CALVERT DR | 161 | MAY | 2023-08-01 | SDADAMS | U135005 | 2023-08-01 | 2023-08-08 | 2023-08-08 |  | SDADAMS | 2023-08-01 |  |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 | 14.9 | 2 | 1321.44 | 905.45 | 268.34 | 51.95 | 95.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23205394200 |  | 100334855 |  | 6720212P |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | NEW CIRCLE | 1085 E NEW CIRCLE RD STE 1 | 067 | LEX | 2023-08-01 | SSHIMFE | U129939 | 2023-08-01 | 2023-08-01 |  |  | SSHIMFE | 2023-08-01 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.26667 | 1 | 16.6 | 15.7 | 0 | 0.9 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23205453700 |  | 100339122 |  | 6720212F |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | BRYAN | 907 BRYAN AV | 067 | LEX | 2023-08-01 | LSTONE | U131552 | 2023-08-01 | 2023-08-01 |  |  | LSTONE | 2023-08-01 | 2023-08-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 4.8167 | 5 | 495.05 | 265.73 | 133.15 | 24.67 | 71.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23205454600 |  | 100334856 |  | 6720212P |  |  |  | 566 | EX | ABN SVC LINE | 2621P | NEW CIRCLE | 1087 E NEW CIRCLE RD STE 1 | 067 | LEX | 2023-08-01 | SSHIMFE | U131552 | 2023-08-01 | 2023-08-01 |  |  | SSHIMFE | 2023-08-01 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.083333 | 1 | 4.91 | 4.65 | 0 | 0.26 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23205478300 |  | 100325100 |  | 6720204A |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | ELMENDORF | 3409 ELMENDORF PL | 067 | LEX | 2023-08-02 | U128336 | U129939 | 2023-08-01 | 2023-08-01 |  |  | JOSHUA COX | 2023-08-01 | 2023-08-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 29.8833 | 6 | 2956.75 | 1621.56 | 682.7 | 573.29 | 79.2 | 0 | 0 | 0
KY | KY - EAST | 2631 | 07694395400 |  | 500267780 | 33 | T-1111-11 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | ROUTE 3 | ROUTE 3 | 127 | LOU | 2023-08-02 | RECUMP | DHORN | 2007-07-13 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-02 | 2022-10-06 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 7.1333 | 4 | 561.32 | 395.11 | 0 | 166.21 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 14234561200 |  | 100467352 |  | 7356216H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | ROUTE 3 | ROUTE 3 TL 4 | 127 | LOU | 2023-08-02 | RECUMP | U127104 | 2014-07-15 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-02 | 2023-07-10 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.4167 | 2 | 196.56 | 137.75 | 0 | 58.81 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 17491647800 |  | 100322812 | 59 | 6716208D | 1638340 |  |  | 565 | EX | REPL - AC: STEEL RISER | 2621P | KASTLE | 1216 KASTLE RD | 067 | LEX | 2023-08-02 | WISHII | MAWAN | 2017-03-24 | 2017-12-29 |  |  | WISHII | 2023-08-02 | 2023-07-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.3333 | 8 | 1978.28 | 1131.09 | 0 | 700.89 | 146.3 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883190500 |  | 100254329 |  | 7348264O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3# | 2621P | ARGILLITE | 2013 ARGILLITE RD | 089 | FLA | 2023-08-03 | U123688 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BROBERT | 2023-08-02 | 2023-07-31 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 20.9833 | 4 | 4190.15 | 1535.93 | 20.27 | 998.47 | 1635.48 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883205400 |  | 100259284 |  | 7356148T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | STURGILL | STURGILL BR | 071 | HAR | 2023-08-02 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN HOWARD | 2023-08-02 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.2667 | 1 | 352.99 | 333.84 | 0 | 19.15 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22132062200 |  | 100359482 |  | 6736228D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311813 | 2621P | CREEKVIEW | 220 CREEKVIEW DR | 017 | PAR | 2023-08-02 | NRICHIE | U125208 | 2022-09-19 | 2023-03-16 | 2024-09-30 |  | NRICHIE | 2023-08-02 | 2023-07-24 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 11.9 | 5 | 2779.6 | 741.98 | 229.41 | 297.57 | 1510.64 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979044100 |  | 100409144 |  | 7356216K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | ROUTE 1 | ROUTE 1 | 127 | LOU | 2023-08-04 | U123688 | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | RECUMP | 2023-08-02 | 2022-11-17 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.76667 | 3 | 42.74 | 36.35 | 0 | 6.39 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164755800 |  | 100414765 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | HAMILTON | 804 N HAMILTON ST 8 | 209 | GEO | 2023-08-02 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.91667 | 1 | 2138.73 | 55.18 | 0 | 13.67 | 2069.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164755900 |  | 100420343 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | HAMILTON | 808 N HAMILTON ST | 209 | GEO | 2023-08-02 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5 | 1 | 6205.16 | 296.57 | 0 | 73.52 | 5835.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166674300 |  | 100322691 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 700 PROVIDENCE RD | 067 | LEX | 2023-08-02 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-08-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2123.15 | 0 | 0 | 0 | 2123.15 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168516300 |  | 100342677 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | SYCAMORE | 112 N SYCAMORE ST | 173 | MT | 2023-08-02 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-02 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3554.22 | 0 | 0 | 0 | 3554.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176937100 |  | 100302760 |  | 6712212N | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1257 COLONIAL DR | 067 | LEX | 2023-08-02 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2840.64 | 0 | 0 | 0 | 2840.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176937300 |  | 100302761 |  | 6712212N | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1261 COLONIAL DR | 067 | LEX | 2023-08-02 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2793.55 | 0 | 0 | 0 | 2793.55 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179193700 |  | 100262505 |  | 7352256C | 2075305 |  |  | 565 | EX | RPLC SL/20026983500 | 2600B | RIGGLES | 2518 RIGGLES ST | 019 | ASH | 2023-08-02 | U125566 | U125763 | 2023-04-05 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-08-02 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 4375.06 | 0 | 0 | 0 | 4375.06 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23196539900 |  | 100402611 |  | 6720208K |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | TANNER | 2695 TANNER CT | 067 | LEX | 2023-08-03 | U123688 | U135005 | 2023-06-22 | 2023-12-29 |  |  | ABLAKE | 2023-08-02 | 2023-07-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25.4833 | 7 | 1747.73 | 1354.92 | 198.67 | 133.64 | 60.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23202745700 |  | 100418174 |  | 6684228C |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | FRAZIER | 100 FRAZIER RD | 073 | FRA | 2023-08-02 | U930915 | U133234 | 2023-07-21 | 2023-08-04 | 2023-08-20 |  | EFGOINS | 2023-08-02 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 22.8167 | 3 | 1324.53 | 1252.7 | 0 | 71.83 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883061100 |  | 500038323 |  | 7356216G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3# | 2621P | GREENLAWN CEME | 9 GREENLAWN CEME RD | 127 | LOU | 2023-08-03 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-03 | 2023-06-20 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.0167 | 4 | 407.21 | 274.43 | 0 | 132.78 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883109400 |  | 500452371 |  | 7356216H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | NEW CIRCLE | 315 NEW CIRCLE ST | 127 | LOU | 2023-08-03 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-03 | 2022-12-06 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 16.2167 | 3 | 2158.29 | 1187.86 | 20.27 | 67.51 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883169600 |  | 100253781 |  | 7356220P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | SYCAMORE | 409 E SYCAMORE ST | 127 | LOU | 2023-08-03 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-03 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.3333 | 1 | 1277.36 | 239.23 | 35.11 | 120.37 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883248500 |  | 100267774 |  | 7356216D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | CROSS | 309 CROSS ST | 127 | LOU | 2023-08-03 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-03 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.66667 | 1 | 56.04 | 37.29 | 0 | 18.75 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026164201 |  |  |  | 7240212A | 2286366 | U128885 |  | 557 | EX | INSTALL 2,300'-2" PMMP | 2600B | SPRING | SPRING ST | 173 | MT | 2023-08-04 | U124014 | U128885 | 2023-07-26 | 2023-10-03 | 2023-12-31 | 2023-06-22 | WILL FULKS | 2023-08-03 | 2023-08-02 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP1642 | AMRCB |  | 100 | 055732220261642 | 530.3833 | 145860 | 487634.39 | 35025.88 | 8588.86 | 9167.77 | 354833.88 | 0 | 1156.78 | 78861.22 | 2210
KY | KY - CENTRAL | 2629 | 22026164300 |  |  |  | 7240212A | 2286366 | U128885 |  | 558 | EX | RETIRE 3,574'-BSLP | 2600B | SPRING | SPRING ST | 173 | MT | 2023-08-04 | U124014 | U128885 | 2022-02-08 | 2023-12-29 | 2023-12-31 | 2023-08-01 | WILL FULKS | 2023-08-03 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP1643 | AMRCB |  | 100 | 055832220261643 |  | 0 | 136.8 | 0 | 0 | 0 | 136.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168516200 |  | 100342679 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | SYCAMORE | 107 N SYCAMORE ST | 173 | MT | 2023-08-07 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-03 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3913.58 | 0 | 0 | 0 | 3913.58 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179193900 |  | 100262507 |  | 7352256C | 2075305 |  |  | 565 | EX | RPLC SL/20026983500 | 2600B | RIGGLES | 2611 RIGGLES ST | 019 | ASH | 2023-08-03 | U125566 | U125763 | 2023-04-05 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-08-03 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 4854.99 | 0 | 0 | 0 | 4854.99 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23204724600 |  | 100360766 |  | 6736228G |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HUME BEDFORD | 28 HUME BEDFORD RD | 017 | PAR | 2023-08-04 | U135005 | U134852 | 2023-07-28 | 2023-07-28 |  |  | NRICHIE | 2023-08-03 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 14.3167 | 3 | 2292.58 | 1449.42 | 292.76 | 287.5 | 262.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23205955000 |  | 100339315 |  | 6724212F |  |  |  | 565 | EX | SERVICE LINE REPALCEMENT | 2621P | NEW ORLEANS | 2013 NEW ORLEANS DR | 067 | LEX | 2023-08-03 | U930915 | U134902 | 2023-08-02 | 2023-08-02 | 2023-08-02 |  | RJCRAWF | 2023-08-03 | 2023-08-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.55 | 3 | 1012.98 | 563.39 | 355.65 | 32.34 | 61.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23205963100 |  | 100339324 |  | 6724212F |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | GAINESVILLE | 2048 GAINESVILLE CT | 067 | LEX | 2023-08-04 | U135005 | U138664 | 2023-08-02 | 2023-08-02 | 2023-08-02 |  | LSTANFI | 2023-08-03 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 24 | 3 | 1940.07 | 1285.4 | 309.96 | 272.11 | 72.6 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23206170700 |  | 100443295 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | HAMILTON | 804 N HAMILTON ST 15 | 209 | GEO | 2023-08-03 | U461443 | U125763 | 2023-08-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2082.13 | 0 | 0 | 0 | 2082.13 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883058700 |  | 100249658 |  | 7360216E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | DOVE | 112 DOVE LN | 127 | LOU | 2023-08-04 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-04 | 2023-06-20 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 6.8667 | 3 | 1414.65 | 370.4 | 10.01 | 151.59 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883319800 |  | 500539375 |  | 7356216H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | ROUTE 5 | ROUTE 5 | 127 | LOU | 2023-08-04 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-04 | 2022-11-17 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.71667 | 3 | 1086.89 | 32.25 | 0 | 16.23 | 1038.41 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026247700 |  |  |  | 6716220I | 2184527 | U461383 |  | 587 | EX | INSTALL NEW GMB SETTING | 2600M | SPURR | 3111 SPURR RD | 067 | LEX | 2023-08-28 | U123258 | U461383 | 2023-01-06 | 2023-11-28 | 2023-12-01 | 2023-08-04 | CONNOR WEMPE | 2023-08-04 | 2023-07-27 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00587 | 3200587 |  |  | WP2477 |  |  | 100 | 058732230262477 | 183.15 | 264 | 96486.51 | 11584.18 | 53079.72 | 2209.58 | 12194.68 | 0 | 1407.1 | 16011.25
KY | KY - EAST | 2631 | 23026276500 |  |  |  | 7340268A | 2072743 | U122858 |  | 560 | EX | EMER - ABANDON 5'-4"CSLP | 2621P | MAIN | 301 MAIN ST | 089 | GRE | 2023-08-04 | U128132 | U122858 | 2023-05-26 | 2023-06-09 | 2023-12-30 | 2020-04-20 | BROBERTS | 2023-08-04 | 2023-06-09 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00560 | 3200560 |  |  | WP2765 |  |  | 100 | 056032230262765 | 0.083333 | 0 | 734.44 | 7.82 | 719.96 | 6.66 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164756300 |  | 100281711 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | LOCUST | 618 LOCUST ST | 209 | GEO | 2023-08-04 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.2 | 1 | 2720.41 | 427.08 | 0 | 105.85 | 2187.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166673400 |  | 100322676 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 681 PROVIDENCE RD | 067 | LEX | 2023-08-04 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-08-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1540.49 | 0 | 0 | 0 | 1540.49 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168515600 |  | 100342710 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HIGH | 127 W HIGH ST 2F | 173 | MT | 2023-08-04 | U126604 | U125763 | 2023-02-21 | 2023-12-29 |  |  | WILL FULKS | 2023-08-04 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4740.39 | 0 | 0 | 0 | 4740.39 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168515700 |  | 100342713 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HIGH | 201 W HIGH ST 1F | 173 | MT | 2023-08-04 | U126604 | U125763 | 2023-02-21 | 2023-12-29 |  |  | WILL FULKS | 2023-08-04 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2081.56 | 0 | 0 | 0 | 2081.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176936900 |  | 100302759 |  | 6712212I | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1253 COLONIAL DR | 067 | LEX | 2023-08-04 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3134.26 | 0 | 0 | 0 | 3134.26 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176937500 |  | 100302762 |  | 6712212N | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1265 COLONIAL DR | 067 | LEX | 2023-08-04 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2404.63 | 0 | 0 | 0 | 2404.63 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179193800 |  | 100262508 |  | 7352256C | 2075305 |  |  | 565 | EX | RPLC SL/20026983500 | 2600B | RIGGLES | 2521 RIGGLES ST | 019 | ASH | 2023-08-04 | U125566 | U125763 | 2023-04-05 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-08-04 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3522.37 | 0 | 0 | 0 | 3522.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23206253200 |  | 100312692 |  | 6716208E |  |  |  | 565 | EX | 24HR GAS OFF - REPLACE SL | 2621P | LONGVIEW | 498 LONGVIEW DR | 067 | LEX | 2023-08-07 | U123688 | U135005 | 2023-08-03 | 2023-08-03 | 2023-08-03 |  | HMCKUNE | 2023-08-04 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.4333 | 2 | 970.33 | 768.2 | 63.46 | 44.07 | 94.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23206255000 |  | 100322770 |  | 6716208D |  |  |  | 565 | EX | 24HR GAS OFF - REPLACE SL | 2621P | SCOVILLE | 1270 SCOVILLE RD | 067 | LEX | 2023-08-04 | U128336 | U135005 | 2023-08-03 | 2023-08-03 | 2023-08-03 |  | JOSHUA COX | 2023-08-04 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.5333 | 2 | 1190.53 | 754.16 | 273.22 | 43.25 | 119.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23206492500 |  | 100309967 |  | 6716208E | 1635077 |  |  | 565 | EX | REPAIR GAS SERVICE | 2621P | CARDINAL | 625 CARDINAL LN | 067 | LEX | 2023-08-04 | WISHII | U130871 | 2023-08-04 | 2023-08-04 | 2023-08-04 |  | WISHII | 2023-08-04 | 2023-08-04 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.15 | 3 | 1364.87 | 716.96 | 0 | 536.81 | 111.1 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883077500 |  | 100266166 |  | 7380144T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | GRAPEVINE | 15793 GRAPEVINE RD | 195 | PHY | 2023-08-07 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BLAKE MULLINS | 2023-08-07 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - EAST | 2633 | 21883211100 |  | 100252152 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | INE | 2023-08-07 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-08-07 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - EAST | 2633 | 21883238300 |  | 100266370 |  | 7380144T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | GRAPEVINE | 839 GRAPEVINE RD | 195 | PHY | 2023-08-07 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BLAKE MULLINS | 2023-08-07 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883247800 |  | 100244799 |  | 7356216D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PIKE | 100 N PIKE ST | 127 | LOU | 2023-08-07 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-07 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.8667 | 1 | 4589.35 | 271.49 | 0 | 257.61 | 4060.25 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21884241600 |  | 100422823 |  | 7344148T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW3739 | PW3739 | 071 | DRI | 2023-08-07 | U130172 | U128293 | 2021-02-04 | 2023-08-07 | 2023-12-31 |  | BRIAN PREECE | 2023-08-07 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.0333 | 1 | 333.16 | 315.09 | 0 | 18.07 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129042500 |  | 100266477 |  | 7388148T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | UPPER JOHNS CR | 6110 UPPER JOHNS CR RD | 195 | KIM | 2023-08-07 | U130172 | U130722 | 2022-09-05 | 2022-12-30 |  |  | BLAKE MULLINS | 2023-08-07 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - EAST | 2633 | 22979026500 |  | 100266351 |  | 7380144T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | GRAPEVINE | 16480 GRAPEVINE RD | 195 | PHY | 2023-08-07 | U130172 | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | BLAKE MULLINS | 2023-08-07 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - WEST | 2621 | 23026251800 |  |  |  | 6716220I | 2184527 | U461383 |  | 562 | EX | RETIRE 900' OF 2"CSHP MAIN | 2600B | SPURR | 3111 SPURR RD | 067 | LEX | 2023-08-16 | U461309 | U461383 | 2023-01-18 | 2023-12-01 | 2023-12-01 | 2023-08-07 | R.HUMPHREYS | 2023-08-07 | 2023-08-07 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP2518 |  |  | 100 | 056232230262518 | 4.9667 | 0 | 12666.75 | 4979.99 | 0 | 1054.69 | 6632.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23157255200 |  | 500330094 |  | 6712220P | 2184527 | U461383 |  | 565 | EX | INSTALL 80' OF 2"CSHP S/L | 2600B | SPURR | 3111 SPURR RD | 067 | LEX | 2023-08-14 | U461383 | U461383 | 2023-01-18 | 2023-06-26 | 2023-07-01 |  | R.HUMPHREYS | 2023-08-07 | 2023-07-24 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 92 | 12 | 27318.9 | 5534.78 | 5635.55 | 1422.33 | 14726.24 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164755600 |  | 501031420 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | HAMILTON | 804 N HAMILTON ST 1 | 209 | GEO | 2023-08-07 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-07 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.9667 | 1 | 2429.24 | 354.73 | 0 | 87.93 | 1986.58 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168506400 |  | 100342691 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | CLAY | 120 CLAY ST | 173 | MT | 2023-08-09 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-07 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4190.7 | 0 | 0 | 0 | 4190.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168515500 |  | 501242242 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HIGH | 121 W HIGH ST POOL | 173 | MT | 2023-08-07 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-07 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2427.06 | 0 | 0 | 0 | 2427.06 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176936500 |  | 100302757 |  | 6712212K | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1245 COLONIAL DR | 067 | LEX | 2023-08-07 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3350.93 | 0 | 0 | 0 | 3350.93 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23192652200 |  | 100286288 | 56 | 6756176O |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTREQ | 2621P | IRVINE | 830 S IRVINE RD | 065 | IRV | 2023-08-07 | DENNING | LSTANFI | 2023-06-04 | 2023-07-31 | 2023-08-31 |  | DENNING | 2023-08-07 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 19.1 | 3 | 1395.61 | 1273.94 | 0 | 121.67 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23196519000 |  | 100269961 |  | 6732252P |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | BROADWAY | 203 BROADWAY AV | 097 | CYN | 2023-08-07 | NRICHIE | U135005 | 2023-06-22 | 2023-12-29 |  |  | NRICHIE | 2023-08-07 | 2023-07-18 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 29.8 | 6 | 2971.32 | 1857.66 | 361.37 | 697.29 | 55 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23205871300 |  | 100339181 |  | 6724212I |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332571 | 2621P | BARWICK | 1828 BARWICK DR | 067 | LEX | 2023-08-07 | WISHII | U135005 | 2023-08-02 | 2023-08-04 | 2023-08-22 |  | WISHII | 2023-08-07 | 2023-08-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 22.9167 | 2 | 1854.66 | 1137.49 | 0 | 652.27 | 64.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23206251800 |  | 100304458 |  | 6712212P |  |  |  | 565 | EX | 24HR GAS OFF - REPLACE SL | 2621P | VICKSBURG | 1953 VICKSBURG RD | 067 | LEX | 2023-08-08 | U135005 | U135005 | 2023-08-03 | 2023-08-03 | 2023-08-03 |  | SSHIMFE | 2023-08-07 | 2023-08-04 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.9667 | 8 | 1092.21 | 828.78 | 147.04 | 48.19 | 68.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23206752200 |  | 500328287 |  | 6764176G |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | AVERY HOLLOW | 207 AVERY HOLLOW RD | 065 | IRV | 2023-08-07 | DENNING | U129939 | 2023-08-07 | 2023-08-07 |  |  | DENNING | 2023-08-07 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5 | 3 | 345.88 | 327.13 | 0 | 18.75 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21884242800 |  | 100466069 |  | 7356216F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3# | 2621P | R7 BOX 22350 | R7 BOX 22350 | 127 | LOU | 2023-08-08 | RECUMP | U128293 | 2021-02-04 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-08 | 2022-11-17 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.75 | 2 | 2093.7 | 141.87 | 0 | 134.62 | 1817.21 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21884269700 |  | 100249517 |  | 7356216K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3# | 2621P | ROUTE 1 | ROUTE 1 | 127 | LOU | 2023-08-08 | RECUMP | U128293 | 2021-02-04 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-08 | 2022-11-16 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 8.1333 | 3 | 2430.83 | 500.9 | 0 | 112.72 | 1817.21 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22130482300 |  | 100351632 |  | 6744208P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333627 | 2621P | BURNS | 117 S BURNS AV | 049 | WIN | 2023-08-09 | U135005 | U125208 | 2022-09-09 | 2023-03-08 | 2024-09-30 |  | DENNING | 2023-08-08 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 24 | 3 | 2811.75 | 1539.38 | 462.58 | 88.29 | 721.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026256400 |  | 501342833 |  | 6724208B | 2395531 | U461383 |  | 555 | EX | INSTALL 25' OF 2"PMMP MAIN | 2621P | VILLA MEDICI | 1600 VILLA MEDICI PS | 067 | LEX | 2023-11-07 | U128132 | U461383 | 2023-02-13 | 2023-07-28 | 2023-10-26 | 2023-08-08 | J ENSMINGER | 2023-08-08 | 2023-07-31 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2564 |  |  | 100 | 055532230262564 | 96.1833 | 270 | 9201.52 | 5725.86 | 349.16 | 1468.27 | 0 | 0 | 23.59 | 1634.64 | 18
KY | KY - CENTRAL | 2629 | 23168506100 |  | 100342692 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | CLAY | 116 CLAY ST | 173 | MT | 2023-08-09 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-08 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3692.13 | 0 | 0 | 0 | 3692.13 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168506200 |  | 100342452 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | CLAY | 117 CLAY ST | 173 | MT | 2023-08-09 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-08 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3439.1 | 0 | 0 | 0 | 3439.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176937600 |  | 100302763 |  | 6712212N | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1269 COLONIAL DR | 067 | LEX | 2023-08-08 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3094.12 | 0 | 0 | 0 | 3094.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176939300 |  | 100302747 |  | 6712212J | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | STANDISH | 1244 STANDISH WY | 067 | LEX | 2023-08-08 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2136.36 | 0 | 0 | 0 | 2136.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23198537800 |  | 100325144 |  | 6720204B |  |  |  | 565 | EX | REPLACE SERVICE LINE D332536 | 2621P | GREENTREE | 3423 GREENTREE RD | 067 | LEX | 2023-08-08 | U930915 | U135005 | 2023-06-30 | 2023-08-03 | 2025-06-30 |  | RJCRAWF | 2023-08-08 | 2023-07-21 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.65 | 5 | 1397.99 | 1070.94 | 157.64 | 61.61 | 107.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23203718300 |  | 100360553 |  | 6736228D |  |  |  | 565 | EX | SERVICE LINE/METER UPGRADE | 2621P | MAIN | 1487 MAIN ST | 017 | PAR | 2023-08-08 | NRICHIE | U135005 | 2023-07-25 | 2023-08-22 | 2023-08-22 |  | NRICHIE | 2023-08-08 | 2023-07-28 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26290031 | 43.7833 | 9 | 16789.1 | 3459.22 | 397.23 | 1511.75 | 11420.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23204692000 |  | 100304916 |  | 6712212L | 2397211 |  |  | 565 | EX | SERVICE LINE/METER UPGRADE | 2621P | SHENANDOAH | 1709 SHENANDOAH DR | 067 | LEX | 2023-08-08 | KKINDER | U135005 | 2023-07-28 | 2023-08-25 |  |  | KKINDER | 2023-08-08 | 2023-08-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 40.8333 | 7 | 5739.79 | 2489.67 | 1243.86 | 142.83 | 1863.43 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23206196400 |  | 100339311 |  | 6724212F |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | NEW ORLEANS | 2021 NEW ORLEANS DR | 067 | LEX | 2023-08-08 | WISHII | U132761 | 2023-08-03 | 2023-08-08 | 2023-08-23 |  | WISHII | 2023-08-08 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.95 | 2 | 652.52 | 360.43 | 0 | 237.09 | 55 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23207019600 |  | 100416565 |  | 6712232O | 2286608 |  |  | 566 | EX | RETIRE SERVICE LINE - LEAKAGE | 2621P | HAMILTON | 804 N HAMILTON ST 11 | 209 | GEO | 2023-08-08 | U461443 | U129939 | 2023-08-08 | 2023-12-29 |  |  | WGRAVES | 2023-08-08 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26230043 |  | 1 | 1426.51 | 0 | 0 | 0 | 1426.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23207028700 |  | 500172649 |  | 6712212N | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1272 COLONIAL DR | 067 | LEX | 2023-08-08 | U126603 | U125763 | 2023-08-08 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2181.72 | 0 | 0 | 0 | 2181.72 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11919349700 |  | 500261055 |  | 0000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | ROUTE 3 | ROUTE 3 TL 22 | 127 | LOU | 2023-09-14 | U461383 | U124449 | 2011-08-08 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-09 | 2022-10-12 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.3667 | 3 | 30.39 | 24.94 | 0 | 5.45 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 16420181300 |  | 500543430 |  | 6684224D | 9612815 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | GLENNS CREEK | 1127 GLENNS CREEK RD | 073 | FRA | 2023-08-09 | U930915 | U122906 | 2016-06-22 | 2022-07-01 | 2023-12-31 |  | EFGOINS | 2023-08-09 | 2023-08-07 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 48 | 6 | 7198.97 | 2895 | 1791.96 | 640.34 | 1871.67 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883228200 |  | 100253524 |  | 7368196T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | BEA | 2023-08-11 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-08-09 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - EAST | 2631 | 21883240800 |  | 100249395 |  | 7348264A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | ROUTE 3 | ROUTE 3 | 127 | LOU | 2023-08-09 | RECUMP | U120245 | 2021-01-30 | 2023-07-28 | 2023-12-31 |  | RECUMP | 2023-08-09 | 2022-11-16 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1 | 2 | 79.17 | 40.63 | 0 | 38.54 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883252000 |  | 100249516 |  | 7356216H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3# | 2621P | ROUTE 1 | ROUTE 1 | 127 | LOU | 2023-08-09 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-09 | 2022-10-06 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 9.8 | 4 | 5090.31 | 537.88 | 0 | 492.18 | 4060.25 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883327500 |  | 500525389 |  | 7356216F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | CARPET MILL | CARPET MILL RD | 127 | LOU | 2023-08-09 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-09 | 2022-11-17 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4 | 4 | 321.07 | 217.26 | 0 | 103.81 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23154897800 |  | 100461308 |  | 6696212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D304451 | 2621P | SCARBOROUGH | 505 SCARBOROUGH DR | 239 | VER | 2023-08-10 | U135005 | U125208 | 2023-01-11 | 2023-07-07 | 2025-01-31 |  | MCRAIG | 2023-08-09 | 2023-08-08 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 | 12.9333 | 4 | 2019.79 | 753.99 | 251.71 | 412.75 | 601.34 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164749600 |  | 500158568 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 101 ELM CT | 209 | GEO | 2023-08-09 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.4833 | 1 | 2547.6 | 443.68 | 0 | 109.99 | 1993.93 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164749700 |  | 500158569 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 103 ELM CT | 209 | GEO | 2023-08-09 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1989.03 | 0 | 0 | 0 | 1989.03 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164749800 |  | 500158570 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 105 ELM CT | 209 | GEO | 2023-08-09 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1981.68 | 0 | 0 | 0 | 1981.68 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164749900 |  | 500158571 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 107 ELM CT | 209 | GEO | 2023-08-09 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1981.68 | 0 | 0 | 0 | 1981.68 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168513900 |  | 100342697 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOWARD | 134 HOWARD AV | 173 | MT | 2023-08-11 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-09 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2999.84 | 0 | 0 | 0 | 2999.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168518200 |  | 100342449 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | CLAY | 107 CLAY ST | 173 | MT | 2023-08-11 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-09 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2849.45 | 0 | 0 | 0 | 2849.45 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176938900 |  | 500288332 |  | 6712212J | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | MAYFLOWER | 4025 MAYFLOWER LN | 067 | LEX | 2023-08-09 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3861.22 | 0 | 0 | 0 | 3861.22 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179194000 |  | 100262506 |  | 7352256C | 2075305 |  |  | 565 | EX | RPLC SL/20026983500 | 2600B | RIGGLES | 2614 RIGGLES ST | 019 | ASH | 2023-08-09 | U125566 | U125763 | 2023-04-05 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-08-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 4753.92 | 0 | 0 | 0 | 4753.92 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23195316100 |  | 500344282 |  | 6696212O |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | BLACK HAWK | 238 BLACK HAWK CR B-1FL | 239 | VER | 2023-08-09 | U128410 | U133234 | 2023-06-16 | 2023-06-29 | 2023-07-15 |  | CDESPAIN | 2023-08-09 | 2023-06-28 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 18.0833 | 3 | 2521.91 | 1309.04 | 0 | 75.35 | 1137.52 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23196268600 |  | 500312398 |  | 6696212N |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | BLACK HAWK | 236 BLACK HAWK CR A-1FR | 239 | VER | 2023-08-09 | U128410 | U133234 | 2023-06-21 | 2023-07-03 | 2023-07-20 |  | CDESPAIN | 2023-08-09 | 2023-08-08 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 41.8667 | 8 | 4625.74 | 2802.29 | 0 | 285.72 | 1537.73 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23196922200 |  | 100404232 |  | 6736252B |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | US HIGHWAY 27 | 2382 US HIGHWAY 27 N | 097 | CYN | 2023-08-09 | NRICHIE | U135005 | 2023-06-26 | 2023-12-21 | 2025-06-30 |  | NRICHIE | 2023-08-09 | 2023-07-24 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 29.1333 | 5 | 3830.78 | 1814.65 | 504.92 | 716.91 | 794.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23204127700 |  | 100296289 |  | 6716216O |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | PRICE | 421 PRICE RD 1 | 067 | LEX | 2023-08-10 | U135005 | U133234 | 2023-07-26 | 2023-08-09 | 2023-08-25 |  | TROE | 2023-08-09 | 2023-07-31 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 20.2167 | 8 | 1207.74 | 1058.18 | 88.54 | 61.02 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23204460200 |  | 100323573 |  | 6716204C |  |  |  | 565 | EX | SERVICE LINE/METER UPGRADE | 2621P | BELVOIR | 3452 BELVOIR DR | 067 | LEX | 2023-08-09 | WISHII | U135005 | 2023-07-27 | 2023-08-10 | 2023-08-10 |  | WISHII | 2023-08-09 | 2023-08-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.8167 | 2 | 962.9 | 542.43 | 0 | 319.27 | 101.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23205870900 |  | 100339236 |  | 6724212I |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332570 | 2621P | GAYLE | 1886 GAYLE DR | 067 | LEX | 2023-08-10 | U135005 | U135005 | 2023-08-02 | 2023-08-04 | 2023-08-22 |  | LSTANFI | 2023-08-09 | 2023-08-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.2333 | 4 | 1945.14 | 1094.76 | 482.57 | 249.01 | 118.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23207342500 |  | 500172650 |  | 6712212N | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1276 COLONIAL DR | 067 | LEX | 2023-08-09 | U126603 | U125763 | 2023-08-09 | 2023-12-29 |  |  | SHAWN DENIS | 2023-08-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2176.71 | 0 | 0 | 0 | 2176.71 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23207342600 |  | 500172651 |  | 6712212N | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1280 COLONIAL DR | 067 | LEX | 2023-08-09 | U126603 | U125763 | 2023-08-09 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2156.98 | 0 | 0 | 0 | 2156.98 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883268500 |  | 500409099 |  | 7356216D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | ROUTE 5 | ROUTE 5 | 127 | LOU | 2023-08-10 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-10 | 2022-11-17 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 6.3667 | 3 | 1554.9 | 344.94 | 0 | 327.31 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883268900 |  | 100249664 |  | 7360216E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | ROUTE 5 | ROUTE 5 | 127 | LOU | 2023-08-10 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-10 | 2023-07-11 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.43333 | 2 | 919.95 | 25.84 | 0 | 11.46 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979027200 |  | 100267776 |  | 7356216C |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | RICE | 107 N RICE ST | 127 | LOU | 2023-08-10 | RECUMP | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | RECUMP | 2023-08-10 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.15 | 1 | 1115.75 | 119.6 | 0 | 113.5 | 882.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026277000 |  |  |  | 6716212L | 2397942 | U461383 |  | 557 | EX | EMER-INSTALL 15' OF 8"PMLP MN | 2621P | MAXWELL | 210 W MAXWELL ST | 067 | LEX | 2023-11-17 | U136251 | U461383 | 2023-06-01 | 2024-07-29 | 2025-03-13 | 2023-08-10 | LSTANFI | 2023-08-10 | 2023-08-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2770 | AMRCB |  | 100 | 055732230262770 | 61.6333 | 110 | 19403.77 | 3523.31 | 6543.48 | 294.1 | 5254.99 | 0 | 89.43 | 3698.46 | 11
KY | KY - WEST | 2621 | 23026277100 |  |  |  | 6716212L | 2397942 | U461383 |  | 558 | EX | EMER-RETIRE 15' OF 8"BSLP MN | 2621P | MAXWELL | 210 W MAXWELL ST | 067 | LEX | 2023-11-07 | U136251 | U461383 | 2023-06-01 | 2024-07-31 | 2025-03-13 | 2023-08-10 | LSTANFI | 2023-08-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2771 |  |  | 100 | 055832230262771 | 4.4167 | 0 | 307.27 | 263.55 | 0 | 43.72 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026284300 |  |  |  | 6716208J | 2398803 | U461383 |  | 557 | EX | EMER-INSTALL 490' OF 2"PMMP | 2621P | NICHOLASVILLE | 2230 NICHOLASVILLE RD | 067 | LEX | 2023-10-16 | U136251 | U461383 | 2023-07-14 | 2023-09-25 | 2023-10-01 | 2023-07-14 | KKINDER | 2023-08-10 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2843 | AMRCB |  | 100 | 055732230262843 | 0.083333 | 493 | 132813.07 | 19870.71 | 37394.13 | 4430.87 | 48798.64 | 0 | 108.45 | 22210.27 | 493
KY | KY - WEST | 2621 | 23026284400 |  |  |  | 6716208J | 2398803 | U461383 |  | 558 | EX | EMER-RETIRE 520' OF 4"BSMP MN | 2621P | NICHOLASVILLE | 2230 NICHOLASVILLE RD | 067 | LEX | 2023-09-06 | U136251 | U461383 | 2023-07-14 | 2023-09-29 | 2023-10-01 | 2023-07-14 | KKINDER | 2023-08-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2844 | AMRCB |  | 100 | 055832230262844 | 0.25 | 0 | 223.9 | 16.51 | 0 | 207.39 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026288000 |  |  |  | 6712204C | 2399340 | U126783 |  | 557 | EX | EMER - INSTALL 5'-2" PMMP | 2621P | BIRKENHEAD | 3438 BIRKENHEAD | 067 | LEX | 2023-11-07 | U136251 | U126783 | 2023-08-09 | 2023-08-10 | 2023-12-31 | 2023-08-09 | KKINDER | 2023-08-10 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2880 |  |  | 100 | 055732230262880 | 2.7667 | 5 | 267.7 | 181.5 | 0 | 10.42 | 24.2 | 0 | 0.56 | 51.02 | 5
KY | KY - WEST | 2621 | 23026288100 |  |  |  | 6712204C | 2399340 | U126783 |  | 558 | EX | EMER - RETIRE 5'-2" PMMP | 2621P | BIRKENHEAD | 3438 BIRKENHEAD | 067 | LEX | 2023-08-24 | U136251 | U126783 | 2023-08-09 | 2023-08-10 | 2023-12-31 | 2023-08-10 | KKINDER | 2023-08-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2881 |  |  | 100 | 055832230262881 | 0.016667 | 0 | 1.39 | 1.32 | 0 | 0.07 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164750000 |  | 500158572 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 109 ELM CT | 209 | GEO | 2023-08-10 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.3333 | 1 | 3153.54 | 434.81 | 0 | 107.77 | 2610.96 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164750100 |  | 500112881 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 201 ELM CT | 209 | GEO | 2023-08-10 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2684.46 | 0 | 0 | 0 | 2684.46 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164750200 |  | 500112884 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 203 ELM CT | 209 | GEO | 2023-08-10 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2050.28 | 0 | 0 | 0 | 2050.28 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164768500 |  | 500158573 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 111 ELM CT | 209 | GEO | 2023-08-10 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1899.12 | 0 | 0 | 0 | 1899.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168505700 |  | 100342439 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | CLAY | 18 CLAY ST | 173 | MT | 2023-08-11 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-10 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3260.14 | 0 | 0 | 0 | 3260.14 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168505800 |  | 100342446 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | CLAY | 19 CLAY ST | 173 | MT | 2023-08-11 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-10 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3178.68 | 0 | 0 | 0 | 3178.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176937700 |  | 100302764 |  | 6712212N | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | COLONIAL | 1273 COLONIAL DR | 067 | LEX | 2023-08-11 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2945.9 | 0 | 0 | 0 | 2945.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176940700 |  | 100302765 |  | 6712212N | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | STANDISH | 1290 STANDISH WY | 067 | LEX | 2023-08-11 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3189.66 | 0 | 0 | 0 | 3189.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23205470000 |  | 100308650 |  | 6716212M |  |  |  | 566 | EX | ABANDON SL - CONV | 2621P | DELLA | 817 DELLA DR | 067 | LEX | 2023-08-11 | U135005 | U135005 | 2023-08-01 | 2023-12-29 |  |  | RSTRONG | 2023-08-10 | 2023-08-08 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 31.2667 | 6 | 2268.3 | 1841.51 | 0 | 426.79 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23207371500 |  | 100303093 |  | 6712208C |  |  |  | 565 | EX | GRADE 1 REPLACE SVC LINE | 2621P | PINEBLOOM | 1007 PINEBLOOM DR | 067 | LEX | 2023-08-10 | ABLAKE | U937740 | 2023-08-09 | 2023-08-09 | 2023-08-09 |  | ABLAKE | 2023-08-10 | 2023-08-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.8167 | 5 | 2491.82 | 1688.23 | 376.18 | 325.11 | 102.3 | 0 | 0 | 0
KY | KY - EAST | 2631 | 06651544100 |  | 500198331 |  | 7360216E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | ROUTE 5 | ROUTE 5 | 127 | LOU | 2023-08-11 | RECUMP | SSUTHER | 2006-06-21 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-11 | 2022-10-06 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.31667 | 2 | 14.09 | 7.23 | 0 | 6.86 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 06651550500 |  | 100249515 |  | V-1718-32 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | ROUTE 1 | ROUTE 1 | 127 | LOU | 2023-08-11 | RECUMP | SSUTHER | 2006-06-21 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-11 | 2022-10-06 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.36667 | 3 | 15.47 | 10.85 | 0 | 4.62 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883074700 |  | 100267868 |  | 7356256M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | EVANS | 712 W EVANS ST | 127 | LOU | 2023-08-11 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-11 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.1833 | 1 | 449.96 | 230.86 | 0 | 219.1 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883219600 |  | 100253763 |  | 7356220P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | WALNUT | 333 N WALNUT ST | 127 | LOU | 2023-08-11 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-11 | 2023-08-10 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.0833 | 2 | 1217.66 | 171.91 | 0 | 163.1 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883233000 |  | 500337820 |  | 7348264F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | JESSICA | 459 JESSICA DR 11 | 089 | RAC | 2023-08-11 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-11 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.15 | 1 | 16.27 | 8.34 | 0 | 7.93 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883251500 |  | 100267696 |  | 7356216D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | MAYO | 445 S MAYO TL | 127 | LOU | 2023-08-11 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-11 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.2 | 1 | 21.68 | 11.12 | 0 | 10.56 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129004100 |  | 500570615 |  | 7348268M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | SCOTT | 501 SCOTT ST HANGER1 | 089 | WOR | 2023-08-11 | RECUMP | U130722 | 2022-09-05 | 2022-12-30 | 2023-12-31 |  | RECUMP | 2023-08-11 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.91667 | 1 | 105.18 | 53.96 | 0 | 51.22 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026288700 |  |  |  | 6700212I |  | U461383 |  | 583 | EX | INSTALL NEW RELIEF VALVE | 2623M | LEXINGTON | 488 LEXINGTON RD | 239 | VER | 2023-09-25 | U123258 | U461383 | 2023-08-14 | 2023-11-01 | 2023-11-01 | 2023-08-11 | BLONE | 2023-08-11 |  |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00583 | 3200583 |  |  | WP2887 |  |  | 100 | 058332230262887 | 8 | 2 | 814.62 | 572.57 | 0 | 31.39 | 0 | 0 | 0 | 210.66
KY | KY - WEST | 2623 | 23026288800 |  |  |  | 6700212I |  | U461383 |  | 584 | EX | RETIRE RELIEF VALVE | 2623M | LEXINGTON | 488 LEXINGTON RD | 239 | VER | 2023-09-25 | U123258 | U461383 | 2023-08-14 | 2023-11-01 | 2023-11-01 | 2023-08-11 | BLONE | 2023-08-11 |  |  | F | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00584 | 3200584 |  |  | WP2888 |  |  | 100 | 058432230262888 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164750300 |  | 500112889 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 205 ELM CT | 209 | GEO | 2023-08-11 | U461322 | U125763 | 2023-02-03 | 2023-12-29 |  |  | STEVE CANOY | 2023-08-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.5833 | 1 | 2496.84 | 226.76 | 0 | 224.7 | 2045.38 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164750400 |  | 500112894 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 207 ELM CT | 209 | GEO | 2023-08-11 | U461322 | U125763 | 2023-02-03 | 2023-12-29 |  |  | STEVE CANOY | 2023-08-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.0167 | 1 | 2179.17 | 63.52 | 0 | 62.92 | 2052.73 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164750500 |  | 500112897 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 209 ELM CT | 209 | GEO | 2023-08-11 | U461322 | U125763 | 2023-02-03 | 2023-12-29 |  |  | STEVE CANOY | 2023-08-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.016667 | 1 | 2086.5 | 1.27 | 0 | 1.25 | 2083.98 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164750600 |  | 500040121 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 301 ELM CT | 209 | GEO | 2023-08-11 | U461322 | U125763 | 2023-02-03 | 2023-12-29 |  |  | STEVE CANOY | 2023-08-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.76667 | 1 | 2083.98 | 48.92 | 0 | 48.48 | 1986.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166670000 |  | 100322643 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 696 BERRY LN | 067 | LEX | 2023-08-11 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-08-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3124.02 | 0 | 0 | 0 | 3124.02 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168506500 |  | 100342624 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | CLAY | 203 CLAY ST | 173 | MT | 2023-08-11 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-11 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4380.57 | 0 | 0 | 0 | 4380.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176939400 |  | 100302732 |  | 6712212J | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | STANDISH | 1245 STANDISH WY | 067 | LEX | 2023-08-11 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2949.68 | 0 | 0 | 0 | 2949.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176940800 |  | 500611173 |  | 6712212N | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | STANDISH | 1299 STANDISH WY | 067 | LEX | 2023-08-11 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1982.48 | 0 | 0 | 0 | 1982.48 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179193500 |  | 100262503 |  | 7352256C | 2075305 |  |  | 565 | EX | RPLC SL/20026983500 | 2600B | RIGGLES | 2506 RIGGLES ST | 019 | ASH | 2023-08-11 | U125566 | U125763 | 2023-04-05 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-08-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2394.93 | 0 | 0 | 0 | 2394.93 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23187485400 |  | 100324422 |  | 6720204E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333521 | 2621P | CENTURIAN | 1116 CENTURIAN RD | 067 | LEX | 2023-08-14 | U129673 | U125208 | 2023-05-11 | 2023-11-10 | 2025-05-31 |  | WISHII | 2023-08-11 | 2023-06-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.1667 | 6 | 1575.46 | 981.47 | 0 | 540.09 | 53.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23205397600 |  | 100422306 |  | 6712204C | 2399340 |  |  | 565 | EX | REPLACE SERVICE LINE - D341307 | 2621P | BIRKENHEAD | 3438 BIRKENHEAD DR | 067 | LEX | 2023-08-11 | KKINDER | U135005 | 2023-08-01 | 2023-08-02 | 2023-08-20 |  | KKINDER | 2023-08-11 | 2023-08-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 40.5333 | 7 | 2785.87 | 2318.29 | 232.33 | 132.95 | 102.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23206978200 |  | 100334838 |  | 6720212P |  |  |  | 566 | EX | ABANDON SL - MANIFOLD METERS | 2621P | NEW CIRCLE | 1230 E NEW CIRCLE RD | 067 | LEX | 2023-08-14 | U128711 | U135005 | 2023-08-08 | 2023-08-11 |  |  | LSTANFI | 2023-08-11 | 2023-08-11 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 32 | 4 | 2133.5 | 1913.41 | 0 | 220.09 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23207661400 |  | 100288833 |  | 6720212D |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | SAINT ANTHONY | 609 SAINT ANTHONY DR | 067 | LEX | 2023-08-11 | U930915 | U132928 | 2023-08-10 | 2023-11-12 | 2025-05-31 |  | HMCKUNE | 2023-08-11 | 2023-08-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 6.1 | 2 | 2014.63 | 1525.88 | 283.41 | 87.64 | 117.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026257200 |  |  |  | 7348264A | 2294088 | U132703 |  | 909 | EX | INSTALL MIWI AND SUPER SOLAR | 2631M | 3RD | 516 3RD ST RR | 089 | WOR | 2023-08-22 | U123258 | U132703 | 2023-02-14 | 2023-12-01 | 2023-12-01 | 2023-08-15 | SHANE GIORDANO | 2023-08-12 | 2023-08-15 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP2572 |  |  | 100 | 090932230262572 | 8 | 0 | 3080.61 | 513.83 | 0 | 29.48 | 2530 | 0 | 7.3 | 0
KY | KY - EAST | 2631 | 07701715200 |  | 100249671 |  | 7360216E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | SWAN | 9 SWAN LN | 127 | LOU | 2023-08-14 | RECUMP | TNICHOL | 2007-09-11 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-14 | 2022-10-06 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 12.0333 | 5 | 2060.63 | 648.07 | 0 | 529.91 | 882.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176939800 |  | 100302743 |  | 6712212J | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | STANDISH | 1252 STANDISH WY | 067 | LEX | 2023-08-15 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3128.08 | 0 | 0 | 0 | 3128.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23196735900 |  | 100289748 |  | 6720216P |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SPRING STATION | 381 SPRING STATION CT | 067 | LEX | 2023-08-14 | U930915 | U135005 | 2023-06-23 | 2023-12-21 | 2025-06-30 |  | LSTONE | 2023-08-14 | 2023-08-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.6833 | 4 | 1926.04 | 1382.55 | 150.93 | 329.86 | 62.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23201032300 |  | 100402759 |  | 6712204H |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | POTOMAC | 461 POTOMAC RD | 067 | LEX | 2023-08-14 | WISHII | U135005 | 2023-07-14 | 2023-12-29 |  |  | WISHII | 2023-08-14 | 2023-08-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.7667 | 3 | 750.06 | 398.41 | 0 | 257.05 | 94.6 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979020400 |  | 100251579 |  | 7336276N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | HILLMAN | 47 HILLMAN DR TRAILER | 089 | GRE | 2023-08-15 | LAMAY | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | LAMAY | 2023-08-15 | 2023-07-31 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 18.2167 | 3 | 1407.05 | 1137.68 | 0 | 269.37 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026257300 |  |  |  | 7348264A | 2294088 | U132703 |  | 584 | EX | RETIRE CHART | 2631M | 3RD | 516 3RD ST RR | 089 | WOR | 2023-08-22 | U123258 | U132703 | 2023-02-14 | 2023-12-01 | 2023-12-01 | 2023-08-15 | SHANE GIORDANO | 2023-08-15 | 2023-07-19 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00584 | 3200584 |  |  | WP2573 |  |  | 100 | 058432230262573 | 3.0333 | 0 | 386.09 | 193.52 | 0 | 192.57 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164750700 |  | 500040124 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 303 ELM CT | 209 | GEO | 2023-08-15 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.8 | 2 | 2549.25 | 462.68 | 0 | 114.69 | 1971.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164750800 |  | 500040125 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 305 ELM CT | 209 | GEO | 2023-08-15 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1906.47 | 0 | 0 | 0 | 1906.47 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164750900 |  | 500040126 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 307 ELM CT | 209 | GEO | 2023-08-15 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | HERNY FERGUSON | 2023-08-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1993.93 | 0 | 0 | 0 | 1993.93 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164751100 |  | 500040127 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 311 ELM CT | 209 | GEO | 2023-08-15 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1906.47 | 0 | 0 | 0 | 1906.47 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166674600 |  | 100322693 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 708 PROVIDENCE RD | 067 | LEX | 2023-08-16 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-08-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3334.69 | 42.16 | 0 | 2.32 | 3290.21 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168506000 |  | 100342448 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | CLAY | 103 CLAY ST | 173 | MT | 2023-08-15 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-15 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4096.69 | 0 | 0 | 0 | 4096.69 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176938800 |  | 100302745 |  | 6712212J | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | MAYFLOWER | 4004 MAYFLOWER LN | 067 | LEX | 2023-08-15 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2198.53 | 0 | 0 | 0 | 2198.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176939000 |  | 100302729 |  | 6712212J | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | STANDISH | 1237 STANDISH WY | 067 | LEX | 2023-08-15 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3068.04 | 0 | 0 | 0 | 3068.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176939500 |  | 100302746 |  | 6712212J | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | STANDISH | 1248 STANDISH WY | 067 | LEX | 2023-08-15 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2940.36 | 0 | 0 | 0 | 2940.36 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179193600 |  | 100262509 |  | 7352256C | 2075305 |  |  | 565 | EX | RPLC SL/20026983500 | 2600B | RIGGLES | 2507 RIGGLES ST | 019 | ASH | 2023-08-15 | U125566 | U125763 | 2023-04-05 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-08-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3617.6 | 0 | 0 | 0 | 3617.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23190651500 |  | 100406449 |  | 6716204D | 1635077 |  |  | 565 | EX | REPLACE SERVICE LINE | 2621D | MALABU | 831 MALABU DR | 067 | LEX | 2023-08-15 | WISHII | AOC SYST | 2023-05-24 | 2023-11-22 | 2024-12-31 |  | WISHII | 2023-08-15 | 2023-08-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 18.6667 | 3 | 1668.88 | 1004.89 | 0 | 531.99 | 132 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23197984600 |  | 100325083 |  | 6720204A |  |  |  | 565 | VO | REPLACE SERVICE LINE D332532 | 2621P | ELMENDORF | 3485 ELMENDORF WY | 067 | LEX | 2023-08-18 |  | U135005 | 2023-06-29 | 2023-12-28 | 2025-06-30 |  |  | 2023-08-15 | 2023-07-21 |  | A | [11 empty] | 23209467200 | 100 |  |  | 1 | -61.76 | -58.26 | 0 | -3.5 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23206721200 |  | 100301432 |  | 6712212H |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | SUTTON | 102 SUTTON PL | 067 | LEX | 2023-08-15 | JOCHOA | U135005 | 2023-08-07 | 2023-12-29 |  |  | JOCHOA | 2023-08-15 | 2023-08-14 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.2167 | 3 | 994.39 | 512.69 | 234.69 | 247.01 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23207313600 |  | 100301489 |  | 6712212H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309436 | 2621P | RUGBY | 134 RUGBY RD | 067 | LEX | 2023-08-16 | U135005 | U135005 | 2023-08-09 | 2023-08-11 | 2023-08-29 |  | RSTRONG | 2023-08-15 | 2023-08-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 28.65 | 7 | 1994.41 | 1333.62 | 333.83 | 268.66 | 58.3 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23208137500 |  | 500290084 |  | 7352260P |  |  |  | 566 | EX | ABANDON SERVICE LINES | 2621P | WINCHESTER | 601 WINCHESTER AV UNIT 9 | 019 | ASH | 2023-09-05 | U135005 | U937740 | 2023-08-14 | 2023-08-14 |  |  | RECUMP | 2023-08-15 | 2023-08-14 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.9333 | 2 | 1685.72 | 332.12 | 0 | 315.19 | 1038.41 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23208160600 |  | 100331121 |  | 6720212N |  |  |  | 565 | EX | REPLACE SL | 2621P | PRESTON | 149 PRESTON AV | 067 | LEX | 2023-08-15 | U930915 | U137585 | 2023-08-14 | 2023-08-15 |  |  | HMCKUNE | 2023-08-15 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.8 | 1 | 324.26 | 229.57 | 23.21 | 13.18 | 58.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23208358800 |  | 100302744 |  | 6712212J | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | MAYFLOWER | 4008 MAYFLOWER LN | 067 | LEX | 2023-08-15 | U126603 | U125763 | 2023-08-15 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2381.49 | 0 | 0 | 0 | 2381.49 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23208374100 |  | 100420344 |  | 6712232O |  |  |  | 566 | EX | ABANDON SL 566 CLEAN UP | 2621P | HAMILTON | 810 N HAMILTON ST | 209 | GEO | 2023-08-15 | MDULANE | MDULANE | 2023-08-15 | 2023-12-29 | 2023-12-31 |  | OFFICE/MDULANE | 2023-08-15 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2621 | 23208416500 |  | 100325085 |  | 6720204A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | ELMENDORF | 1039 ELMENDORF DR | 067 | LEX | 2023-08-15 | U128336 | U937740 | 2023-08-15 | 2023-08-15 | 2025-06-30 |  | JOSHUA COX | 2023-08-15 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 21.25 | 3 | 2063.39 | 1315.32 | 573.63 | 75.44 | 99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23208423600 |  | 100312937 |  | 6716208E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | FAIRFIELD | 543 FAIRFIELD DR | 067 | LEX | 2023-08-15 | KOBRYAN | U134822 | 2023-08-15 | 2023-12-21 | 2025-06-30 |  | KOBRYAN | 2023-08-15 | 2023-07-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 23.4833 | 6 | 1480.63 | 1291.05 | 0 | 71.88 | 117.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 16434817100 |  | 100318434 |  | 6716204C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LANSDOWNE *HOLD* | 3500 LANSDOWNE *HOLD* DR A | 067 | LEX | 2023-08-16 | U930915 | U122906 | 2016-08-16 | 2017-12-20 |  |  | RJCRAWF | 2023-08-16 | 2023-02-27 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 23.7333 | 6 | 1858.49 | 1397.57 | 0.88 | 80.04 | 380 | 0 | 0 | 0
KY | KY - WEST | 2621 | 17540958400 |  | 100336562 | 14 | 6720212I |  |  |  | 565 | EX | SERV LINE - UNMTRD GAS | 2621P | CHESTNUT | 352 CHESTNUT ST | 067 | LEX | 2023-08-16 | LSTONE | MPILON | 2017-09-06 | 2017-12-06 |  |  | LSTONE | 2023-08-16 | 2023-07-12 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 24.8 | 4 | 2016.91 | 1305.04 | 96.91 | 273.36 | 341.6 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883165200 |  | 500295774 |  | 7348264F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3# | 2621P | US ROUTE 23 | US ROUTE 23 | 089 | RAC | 2023-08-16 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-16 | 2022-10-06 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 9.4667 | 5 | 1849.89 | 522.94 | 0 | 444.3 | 882.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958666600 |  | 100459038 |  | 6720212N | 2180410 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | HANOVER | 151 N HANOVER AV B | 067 | LEX | 2023-08-24 | U126308 | U134723 | 2021-12-08 | 2022-12-30 |  |  | J ENSMINGER | 2023-08-16 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 1.3333 | 0 | 69.93 | 66.13 | 0 | 3.8 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026257700 |  |  |  | 7356216H | 2294088 | U132703 |  | 909 | EX | INSTALL MIWI AND SUPER SOLAR | 2631M | ROSE STREET | 78 ROSE STREET | 127 | LOU | 2023-08-28 | U123258 | U132703 | 2023-02-14 | 2023-12-01 | 2023-12-01 | 2023-08-16 | ANDREW MCCORMICK | 2023-08-16 | 2023-08-16 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP2577 |  |  | 100 | 090932230262577 | 12.7 | 0 | 3552.01 | 781.26 | 0 | 232.86 | 2530 | 0 | 7.89 | 0
KY | KY - EAST | 2631 | 23026257800 |  |  |  | 7356216H | 2294088 | U132703 |  | 584 | EX | RETIRE PAPER CHART | 2631M | ROSE STREET | 78 ROSE STREET | 127 | LOU | 2023-08-28 | U123258 | U132703 | 2023-02-14 | 2023-12-01 | 2023-12-01 | 2023-08-16 | ANDREW MCCORMICK | 2023-08-16 | 2023-08-16 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00584 | 3200584 |  |  | WP2578 |  |  | 100 | 058432230262578 | 11.7 | 0 | 1141.91 | 751.9 | 0 | 390.01 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164751200 |  | 500040130 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 313 ELM CT | 209 | GEO | 2023-08-16 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1984.13 | 0 | 0 | 0 | 1984.13 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164751300 |  | 500040081 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 315 ELM CT | 209 | GEO | 2023-08-16 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1904.02 | 0 | 0 | 0 | 1904.02 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164752000 |  | 500018600 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 505 ELM CT | 209 | GEO | 2023-08-16 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2025.78 | 0 | 0 | 0 | 2025.78 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164752100 |  | 500018599 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 507 ELM CT | 209 | GEO | 2023-08-16 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2018.43 | 0 | 0 | 0 | 2018.43 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165284200 |  | 100294805 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | LIMESTONE | 431 N LIMESTONE ST | 067 | LEX | 2023-08-16 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-08-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.5167 | 1 | 6654.3 | 542.7 | 0 | 31.13 | 6080.47 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165284600 |  | 100294790 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | LIMESTONE | 449 N LIMESTONE ST | 067 | LEX | 2023-08-16 | U126309 | U125763 | 2023-02-07 | 2023-12-29 |  |  | JAMIE LYNN | 2023-08-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2467.02 | 0 | 0 | 0 | 2467.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166677500 |  | 100322671 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 701 PROVIDENCE RD | 067 | LEX | 2023-08-16 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-08-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2344.86 | 0 | 0 | 0 | 2344.86 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168516100 |  | 100342221 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | MAYSVILLE | 200 N MAYSVILLE ST | 173 | MT | 2023-08-22 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-16 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2576.83 | 0 | 0 | 0 | 2576.83 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168518100 |  | 100342445 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | CLAY | 15 CLAY ST | 173 | MT | 2023-08-22 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-16 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4173.68 | 0 | 0 | 0 | 4173.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176939100 |  | 100302748 |  | 6712212J | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | STANDISH | 1240 STANDISH WY | 067 | LEX | 2023-08-16 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3178.65 | 0 | 0 | 0 | 3178.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176940500 |  | 100302737 |  | 6712212N | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | STANDISH | 1273 STANDISH WY | 067 | LEX | 2023-08-16 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2502.66 | 0 | 0 | 0 | 2502.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176945000 |  | 100302740 |  | 6712212N | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | STANDISH | 1272 STANDISH WY | 067 | LEX | 2023-08-16 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2224.25 | 0 | 0 | 0 | 2224.25 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179193400 |  | 100262502 |  | 7352256C | 2075305 |  |  | 565 | EX | RPLC SL/20026983500 | 2600B | RIGGLES | 2440 RIGGLES ST | 019 | ASH | 2023-08-17 | U125566 | U125763 | 2023-04-05 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-08-16 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 4670.78 | 2.14 | 0 | 1.96 | 4666.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23190826600 |  | 100304531 |  | 6712212P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333733 | 2621P | MAYWICK | 983 MAYWICK DR | 067 | LEX | 2023-08-16 | KKINDER | U125208 | 2023-05-25 | 2023-11-22 | 2025-05-31 |  | KKINDER | 2023-08-16 | 2023-07-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.4833 | 4 | 1398.82 | 826.01 | 438.42 | 47.49 | 86.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23198765100 |  | 100446702 |  | 6720208L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332541 | 2621P | CEDARCREST | 2905 CEDARCREST DR | 067 | LEX | 2023-08-17 | U135005 | U135005 | 2023-07-03 | 2023-12-29 | 2025-06-30 |  | ABLAKE | 2023-08-16 | 2023-07-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.7667 | 5 | 1361.91 | 1158.35 | 63.73 | 81.53 | 58.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23200394200 |  | 100421987 |  | 6716204D |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | MALABU | 823 MALABU DR A | 067 | LEX | 2023-08-16 | WISHII | U135005 | 2023-07-12 | 2023-12-29 |  |  | WISHII | 2023-08-16 | 2023-08-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.8167 | 4 | 1635.9 | 854.15 | 0 | 658.55 | 123.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23200699800 |  | 100457827 |  | 6720204M |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | TANBARK | 1176 TANBARK RD | 067 | LEX | 2023-08-16 | WISHII | U135005 | 2023-07-13 | 2023-12-29 |  |  | WISHII | 2023-08-16 | 2023-08-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.2667 | 3 | 755.67 | 271.76 | 179.8 | 179.81 | 124.3 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23204418500 |  | 100345631 |  | 6696212C | 2398721 |  |  | 565 | EX | SERVICE LINE UPGRADE | 2621P | MOLLY | 103 MOLLY ST | 239 | VER | 2023-08-17 | U128410 | U135005 | 2023-07-27 | 2023-09-21 | 2023-09-21 |  | CDESPAIN | 2023-08-16 | 2023-08-08 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26230031 | 37.95 | 8 | 6287.15 | 2602.76 | 60.37 | 149.26 | 3474.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23208668100 |  | 100302750 |  | 6712212J | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | STANDISH | 1236 STANDISH WY | 067 | LEX | 2023-08-16 | U126603 | U131066 | 2023-08-16 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2156.98 | 0 | 0 | 0 | 2156.98 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21883049500 |  | 100274939 |  | 6684228K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | MAIN | 101 W MAIN ST | 073 | FRA | 2023-08-18 | U135005 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | EFGOINS | 2023-08-17 | 2022-12-01 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 37.8333 | 8 | 7305.3 | 2212.96 | 74.38 | 124.06 | 4893.9 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883112300 |  | 500075451 |  | NEW |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | GENERAL DELIVE | GENERAL DELIVE | 071 | BLU | 2023-08-17 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN HOWARD | 2023-08-17 |  |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 7.6667 | 1 | 511.46 | 483.72 | 0 | 27.74 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883192600 |  | 500044934 |  | 7344148T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW3858 | PW3858 | 071 | DRI | 2023-08-17 | U130172 | U120245 | 2021-01-30 | 2023-08-17 |  |  | BRIAN PREECE | 2023-08-17 | 2023-08-17 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 8 | 1 | 527.74 | 499.12 | 0 | 28.62 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883220400 |  | 100402689 |  | 7348264J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3# | 2621P | PENNINGTON | 1305 PENNINGTON RD | 089 | RAC | 2023-08-17 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-17 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.41667 | 1 | 928.21 | 23.37 | 0 | 22.19 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129004200 |  | 500141511 |  | 7344268N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | WURTS | 100 WURTS RD R | 089 | WUR | 2023-08-17 | RECUMP | U130722 | 2022-09-05 | 2022-12-30 | 2023-12-31 |  | RECUMP | 2023-08-17 | 2022-10-12 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 11.1333 | 5 | 2799.21 | 653.56 | 0 | 366.18 | 1779.47 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129008800 |  | 100262350 |  | 7352256H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BLACKBURN | 922 BLACKBURN AV | 019 | ASH | 2023-08-17 | RECUMP | U130722 | 2022-09-05 | 2023-08-17 |  |  | RECUMP | 2023-08-17 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.18333 | 1 | 1836.73 | 10.01 | 0 | 9.51 | 1817.21 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129036300 |  | 100253975 |  | 7348260A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SR 207 | SR 207 | 089 | FLA | 2023-08-18 | U135005 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RECUMP | 2023-08-17 | 2023-07-13 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 8.2 | 3 | 2511.5 | 500.07 | 0 | 194.22 | 1817.21 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026283200 |  |  |  | 6720208L | 2398638 | U461383 |  | 561 | EX | INSTALL 480' OF 2"PMMP MAIN | 2600B | CODELL | 100 CODELL DR | 067 | LEX | 2023-08-21 | U124014 | U461383 | 2023-07-07 | 2023-08-21 | 2023-09-01 | 2023-08-10 | WILL FULKS | 2023-08-17 | 2023-08-07 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP2832 | AMRCB |  | 100 | 056132230262832 | 60.8167 | 4024 | 47476.79 | 3821.54 | 1887.05 | 849.64 | 31898.39 | 0 | 5.22 | 9014.95 | 503
KY | KY - WEST | 2621 | 23026283300 |  |  |  | 6720208L | 2398638 | U461383 |  | 562 | EX | RETIRE 400' OF 2"BSMP MAIN | 2600B | CODELL | 100 CODELL DR | 067 | LEX | 2023-08-21 | U124014 | U461383 | 2023-07-07 | 2023-09-01 | 2023-09-01 | 2023-08-17 | WILL FULKS | 2023-08-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP2833 | AMRCB |  | 100 | 056232230262833 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026288200 |  |  |  | 6720212P | 2399357 | U461383 |  | 909 | EX | INSTALL VERIZON MODEM | 2621M | FORTUNE | 2350 FORTUNE DR | 067 | LEX | 2023-08-25 | U123258 | U461383 | 2023-08-09 | 2023-12-01 | 2023-12-01 | 2023-08-17 | APARKS | 2023-08-17 | 2023-08-11 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP2882 |  |  | 100 | 090932230262882 | 21.5833 | 0 | 1861.82 | 1338.89 | 0 | 518.52 | 0 | 0 | 4.41 | 0
KY | KY - WEST | 2621 | 23026288300 |  |  |  | 6720212P | 2399357 | U461383 |  | 910 | EX | RETIRE SATELLITE COMM EQUIP | 2621M | FORTUNE | 2350 FORTUNE DR | 067 | LEX | 2023-08-25 | U123258 | U461383 | 2023-08-09 | 2023-12-01 | 2023-12-01 | 2023-08-17 | APARKS | 2023-08-17 |  |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00910 | 3200910 |  |  | WP2883 |  |  | 100 | 091032230262883 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164751400 |  | 500018614 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 401 ELM CT | 209 | GEO | 2023-08-17 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.5667 | 1 | 3173.97 | 390.31 | 0 | 96.75 | 2686.91 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164751500 |  | 500018613 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 403 ELM CT | 209 | GEO | 2023-08-17 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2035.58 | 0 | 0 | 0 | 2035.58 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164752200 |  | 500018597 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 509 ELM CT | 209 | GEO | 2023-08-17 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2652.61 | 0 | 0 | 0 | 2652.61 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164752300 |  | 500018594 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 511 ELM CT | 209 | GEO | 2023-08-17 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2023.33 | 0 | 0 | 0 | 2023.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165284000 |  | 100336840 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | LIMESTONE | 426 N LIMESTONE ST | 067 | LEX | 2023-08-17 | U126309 | U125763 | 2023-02-07 | 2023-12-29 |  |  | JAMIE LYNN | 2023-08-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2369.02 | 0 | 0 | 0 | 2369.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166675400 |  | 100322697 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 724 PROVIDENCE RD | 067 | LEX | 2023-08-17 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-08-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2127.97 | 0 | 0 | 0 | 2127.97 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168513600 |  | 100342437 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOWARD | 125 HOWARD AV 2 | 173 | MT | 2023-08-22 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-17 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3814.81 | 0 | 0 | 0 | 3814.81 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176940300 |  | 100302736 |  | 6712212N | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | STANDISH | 1269 STANDISH WY | 067 | LEX | 2023-08-17 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2201.53 | 0 | 0 | 0 | 2201.53 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179193300 |  | 500371582 |  | 7352256C | 2075305 |  |  | 565 | EX | RPLC SL/20026983500 | 2600B | RIGGLES | 2435 RIGGLES ST | 019 | ASH | 2023-08-17 | U125566 | U125763 | 2023-04-05 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-08-17 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 4178.27 | 0 | 0 | 0 | 4178.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23197368300 |  | 100337222 |  | 6720212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332945 | 2621P | M L KING | 516 M L KING BV | 067 | LEX | 2023-08-17 | LSTONE | U135005 | 2023-06-27 | 2023-12-26 | 2025-06-30 |  | LSTONE | 2023-08-17 | 2023-07-26 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.6167 | 4 | 2504.55 | 1316.39 | 117.65 | 75.85 | 994.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23197985000 |  | 100325084 |  | 6720204A |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332533 | 2621P | ELMENDORF | 1041 ELMENDORF DR | 067 | LEX | 2023-08-17 | U128336 | U135005 | 2023-06-29 | 2023-12-28 | 2025-06-30 |  | JOSHUA COX | 2023-08-17 | 2023-08-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 31.0833 | 9 | 2494.06 | 1721.61 | 573.63 | 98.72 | 100.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23200404900 |  | 100416012 |  | 6720204B |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | SUTHERLAND | 3260 SUTHERLAND DR | 067 | LEX | 2023-08-17 | WISHII | U135005 | 2023-07-12 | 2023-12-29 |  |  | WISHII | 2023-08-17 | 2023-08-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.8 | 3 | 1882.36 | 905.41 | 306.52 | 572.53 | 97.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23202091100 |  | 100337222 |  | 6720212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | M L KING | 516 M L KING BV | 067 | LEX | 2023-08-17 | LSTONE | U123688 | 2023-07-19 | 2024-01-18 | 2025-07-31 |  | LSTONE | 2023-08-17 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 1.4333 | 2 | 91.7 | 86.72 | 0 | 4.98 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23203718400 |  | 100412324 |  | 6720208H |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | MIRAHILL | 2400 MIRAHILL DR A | 067 | LEX | 2023-08-17 | HMCKUNE | U135005 | 2023-07-25 | 2023-12-29 |  |  | HMCKUNE | 2023-08-17 | 2023-08-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 35.3167 | 11 | 3001.84 | 1972.65 | 839.11 | 113.08 | 77 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23205051400 |  | 100441744 |  | 7240280F |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | BROOKSVILLE GE | 6196 BROOKSVILLE GE RD | 023 | GER | 2023-08-17 | SDADAMS | U133234 | 2023-07-31 | 2023-08-14 | 2023-08-30 |  | SDADAMS | 2023-08-17 | 2023-08-16 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 16.2667 | 3 | 1572.02 | 1007.46 | 15.53 | 549.03 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23205902200 |  | 100334572 |  | 6720208H |  |  |  | 565 | EX | REPLACE SERVICE LINE/RISER | 2621P | MULBERRY | 333 MULBERRY RD | 067 | LEX | 2023-08-18 | U135005 | U135005 | 2023-08-02 | 2023-12-29 |  |  | RSTRONG | 2023-08-17 | 2023-08-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25.35 | 6 | 1860.35 | 1224.33 | 302.26 | 286.46 | 47.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23208668500 |  | 100302751 |  | 6712212J | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | STANDISH | 1232 STANDISH WY | 067 | LEX | 2023-08-17 | U126603 | U131066 | 2023-08-16 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2165.29 | 0 | 0 | 0 | 2165.29 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23208668700 |  | 100302752 |  | 6712212J | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | STANDISH | 1228 STANDISH WY | 067 | LEX | 2023-08-17 | U126603 | U131066 | 2023-08-16 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1997.93 | 0 | 0 | 0 | 1997.93 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23209056300 |  | 100302735 |  | 6712212N | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | STANDISH | 1265 STANDISH WY | 067 | LEX | 2023-08-17 | U126603 | U125763 | 2023-08-17 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2904.41 | 0 | 0 | 0 | 2904.41 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23209324400 |  | 100342433 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOWARD | 121 HOWARD AV | 173 | MT | 2023-08-23 | U123111 | U125763 | 2023-08-18 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-17 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1866.48 | 0 | 0 | 0 | 1866.48 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23209730700 |  | 100342436 |  | 7240216N | 2286853 |  |  | 566 | EX | ABANDN SL/22026170600 | 2600B | HOWARD | 125 HOWARD AV 2 | 173 | MT | 2023-08-23 | U123111 | U125763 | 2023-08-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1070.98 | 0 | 0 | 0 | 1070.98 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07675235700 |  | 100320319 |  | 6716208G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | NICHOLASVILLE | 1800 NICHOLASVILLE RD | 067 | LEX | 2023-08-18 | U126308 | SSUTHER | 2007-02-08 | 2022-07-01 | 2023-12-31 |  | J ENSMINGER | 2023-08-18 | 2023-06-23 | 2013-12-16 | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.1833 | 6 | 2765.9 | 925.12 | 0 | 53.26 | 1787.52 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22132383800 |  | 100264373 |  | 7356260M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | 9TH | 513< 9TH ST | 019 | ASH | 2023-08-18 | RECUMP | U125208 | 2022-09-20 | 2023-08-17 |  |  | RECUMP | 2023-08-18 | 2023-06-30 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.35 | 3 | 1350.96 | 245.43 | 0 | 222.88 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979019400 |  | 100249202 |  | 7328284B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | CLARK | 138 CLARK ST | 089 | S S | 2023-08-18 | RECUMP | U128070 | 2022-02-17 | 2023-08-18 |  |  | RECUMP | 2023-08-18 | 2022-10-05 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.4 | 2 | 1220.9 | 173.56 | 0 | 164.69 | 882.65 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026266100 |  | 501344280 |  | 6700224H | 2395869 | U126783 |  | 555 | EX | INSTALL 880'-4" PHHP | 2600B | LACEFIELD | 100 LACEFIELD ST | 239 | MID | 2023-09-12 | U128132 | U126783 | 2023-03-10 | 2023-09-05 | 2023-09-15 | 2023-08-18 | STEVE CANOY | 2023-08-18 | 2023-08-01 | 2023-08-01 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2661 |  |  | 100 | 055532230262661 | 128.8 | 16507 | 70247.34 | 8162.76 | 6153.1 | 8432.95 | 34730.93 | 0 | 172 | 12595.6 | 971
KY | KY - WEST | 2623 | 23164751900 |  | 500018607 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 501 ELM CT | 209 | GEO | 2023-08-18 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.65 | 1 | 2479.45 | 394.44 | 0 | 97.78 | 1987.23 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164760800 |  | 100281682 |  | 6712232O | 2286608 |  |  | 566 | EX | ABANDON SL/22026168600 | 2600B | PAYNE | 512 PAYNE AV | 209 | GEO | 2023-08-18 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-18 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26230043 |  | 1 | 1426.51 | 0 | 0 | 0 | 1426.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165282300 |  | 100297263 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | LIMESTONE | 355 N LIMESTONE ST 1F | 067 | LEX | 2023-08-18 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-08-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.6 | 1 | 2604.49 | 483.51 | 0 | 27.74 | 2093.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165290200 |  | 100297273 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | LIMESTONE | 343 N LIMESTONE ST | 067 | LEX | 2023-08-18 | U126309 | U125763 | 2023-02-07 | 2023-12-29 |  |  | JAMIE LYNN | 2023-08-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2034.03 | 0 | 0 | 0 | 2034.03 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168513700 |  | 100342699 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOWARD | 126 HOWARD AV | 173 | MT | 2023-08-18 | U126284 | U125763 | 2023-02-21 | 2023-12-29 |  |  | JOSH PASLEY/MILLER PIPELINE | 2023-08-18 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 2.9 | 1 | 5740.38 | 180.63 | 0 | 182.33 | 5377.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176944900 |  | 100302741 |  | 6712212N | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | STANDISH | 1264 STANDISH WY | 067 | LEX | 2023-08-21 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2746.46 | 0 | 0 | 0 | 2746.46 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23177458200 |  | 100281067 |  | 6684228K |  |  |  | 566 | EX | ABANDON SL - CONVRT/CUSTRQD | 2621P | MAIN | 147 E MAIN ST | 073 | FRA | 2023-08-18 | EFGOINS | U133234 | 2023-03-31 | 2023-04-12 | 2023-04-28 |  | EFGOINS | 2023-08-18 | 2023-06-01 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 20.3667 | 8 | 1191.14 | 1091.59 | 36.02 | 63.53 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23200698600 |  | 100311610 |  | 6712204D |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | STILLWATER | 3432 STILLWATER RD | 067 | LEX | 2023-08-18 | KKINDER | U135005 | 2023-07-13 | 2023-12-29 |  |  | KKINDER | 2023-08-18 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.15 | 2 | 1602.54 | 897.51 | 599.67 | 51.46 | 53.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23208415300 |  | 100273805 |  | 6680228K |  |  |  | 565 | EX | RELOCATE SERVICE LINE | 2621P | TRACEY | 1135 TRACEY LN | 073 | FRA | 2023-08-18 | MCRAIG | U135005 | 2023-08-15 | 2023-12-29 |  |  | MCRAIG | 2023-08-18 | 2023-08-18 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 11.15 | 2 | 1899.03 | 738.92 | 529.62 | 596.39 | 34.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23209334600 |  | 100260971 |  | 7352256D | 2075305 |  |  | 565 | EX | RPLC SL/20026983500 | 2600B | BLACKBURN | 500 BLACKBURN AV | 019 | ASH | 2023-08-18 | U125566 | U125763 | 2023-08-18 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-08-18 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2324.33 | 0 | 0 | 0 | 2324.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23209348800 |  | 100302728 |  | 6712212J | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | STANDISH | 1233 STANDISH WY | 067 | LEX | 2023-08-21 | U126603 | U125763 | 2023-08-18 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3066.27 | 0 | 0 | 0 | 3066.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23209456700 |  | 100334062 |  | 6720212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SPARKS | 1132 SPARKS RD | 067 | LEX | 2023-08-18 | LSTONE | U134852 | 2023-08-18 | 2023-12-08 | 2025-06-30 |  | LSTONE | 2023-08-18 | 2023-08-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 16.9 | 4 | 1712.75 | 1303.48 | 205.76 | 110.01 | 93.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 01491733400 |  | 100333030 |  | 6724208J | 1315787 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | R5 CLEVELAND | R5 CLEVELAND RD | 067 | LEX | 2023-08-21 | SOBRYAN | JTOY | 2001-12-26 | 2049-12-31 |  |  | SOBRYAN | 2023-08-21 | 2023-05-22 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.05 | 4 | 143.42 | 135.65 | 0 | 7.77 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026225400 |  |  |  | 6688228K | 2291968 | U132703 |  | 557 | EX | INSTALL APROX 180'-6" PMLP | 2600E | VERSAILLES | 601 VERSAILLES RD | 073 | FRA | 2023-11-07 | U136251 | U132703 | 2022-09-21 | 2023-09-18 | 2023-09-30 | 2023-08-17 | DDAVIS | 2023-08-21 | 2023-07-06 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP2254 | AMRCB |  | 100 | 055732220262254 | 186 | 5375 | 160069.05 | 11912.22 | 14084.94 | 2762.78 | 101576.51 | 0 | 489.63 | 29242.97 | 215
KY | KY - WEST | 2623 | 22026225500 |  |  |  | 6688228K | 2291968 | U132703 |  | 558 | EX | RETIRE 200' - 6" BSLP | 2600E | VERSAILLES | 601 VERSAILLES RD | 073 | FRA | 2023-09-11 | U136251 | U132703 | 2022-09-21 | 2023-03-31 | 2023-09-30 | 2023-08-17 | DDAVIS | 2023-08-21 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP2255 | AMRCB |  | 100 | 055832220262255 |  | 0 | 510.72 | 0 | 0 | 0 | 510.72 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129014000 |  | 100240664 |  | 7328284D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ELIZABETH | 54 ELIZABETH LN | 089 | S S | 2023-08-21 | RECUMP | U130722 | 2022-09-05 | 2023-08-18 |  |  | RECUMP | 2023-08-21 | 2023-08-18 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.2 | 2 | 1590.87 | 232.54 | 0 | 220.68 | 1137.65 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026286000 |  |  |  | 7240212A | 2399105 | U128885 |  | 557 | EX | EMER - INSTALL 6'-2" PMMP | 2621P | BROOKVIEW | 507 BROOKVIEW DRIVE | 173 | MT | 2023-08-24 | U128132 | U128885 | 2023-07-31 | 2024-10-21 | 2025-06-15 | 2023-07-12 | WDENNING | 2023-08-21 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP2860 |  |  | 100 | 055732230262860 |  | 6 | 5456.45 | 4366.45 | 0 | 262.54 | 24.2 | 0 | 12.86 | 790.4 | 6
KY | KY - CENTRAL | 2629 | 23026286100 |  |  |  | 7240212A | 2399105 | U128885 |  | 558 | EX | EMER - RETIRE 6'-2" PMMP | 2621P | BROOKVIEW | 507 BROOKVIEW DRIVE | 173 | MT | 2023-08-24 | U128132 | U128885 | 2023-07-31 | 2024-10-31 | 2025-06-15 | 2023-07-12 | WDENNING | 2023-08-21 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP2861 |  |  | 100 | 055832230262861 | 0.7 | 0 | 5375.26 | 44.71 | 0 | 2.55 | 5328 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026288500 |  |  |  | 7240204G | 2399394 | U128885 |  | 557 | EX | EMER - INSTALL 3'-2" PMMP | 2621P | LEVEE | LEVEE | 173 | MT | 2023-08-23 | U128132 | U128885 | 2023-08-11 | 2024-04-10 |  | 2023-08-03 | LCLARK | 2023-08-21 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP2885 |  |  | 100 | 055732230262885 |  | 8 | 33.23 | 0 | 0 | 0 | 24.2 | 0 | 0 | 9.03 | 8
KY | KY - CENTRAL | 2629 | 23026288600 |  |  |  | 7240204G | 2399394 | U128885 |  | 558 | EX | EMER - RETIRE 3'-2" PMP | 2621P | LEVEE | LEVEE | 173 | MT | 2023-08-23 | U128132 | U128885 | 2023-08-11 |  | 2049-12-31 | 2023-08-03 | LCLARK | 2023-08-21 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP2886 |  |  | 100 | 055832230262886 |  | 0 | 4237.6 | 3998.36 | 0 | 239.24 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164751600 |  | 500018611 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 405 ELM CT | 209 | GEO | 2023-08-21 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2015.98 | 0 | 0 | 0 | 2015.98 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164751800 |  | 500018609 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 409 ELM CT | 209 | GEO | 2023-08-21 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.7333 | 1 | 2530.3 | 400.37 | 0 | 99.25 | 2030.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165282200 |  | 100297267 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | LIMESTONE | 353 N LIMESTONE ST | 067 | LEX | 2023-08-21 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-08-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.0167 | 1 | 3040.6 | 381.72 | 0 | 21.9 | 2636.98 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165284100 |  | 100336841 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | LIMESTONE | 430 N LIMESTONE ST 1FR | 067 | LEX | 2023-08-21 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-08-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.5 | 1 | 3118.73 | 225.24 | 0 | 12.91 | 2880.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166674800 |  | 100322694 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 712 PROVIDENCE RD | 067 | LEX | 2023-08-21 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-08-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2845.68 | 0 | 0 | 0 | 2845.68 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168513500 |  | 100342432 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOWARD | 117 HOWARD AV | 173 | MT | 2023-08-22 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-21 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1899.6 | 0 | 0 | 0 | 1899.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168513800 |  | 100342438 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOWARD | 129 HOWARD AV | 173 | MT | 2023-08-22 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-21 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2159.12 | 0 | 0 | 0 | 2159.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176938300 |  | 501197686 |  | 6712212J | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | JOHN ALDEN | 4024 JOHN ALDEN LN | 067 | LEX | 2023-08-22 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3174.08 | 0 | 0 | 0 | 3174.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176938500 |  | 100302727 |  | 6712212J | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | JOHN ALDEN | 4028 JOHN ALDEN LN | 067 | LEX | 2023-08-22 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3596.03 | 0 | 0 | 0 | 3596.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176940100 |  | 100430446 |  | 6712212N | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | STANDISH | 1260 STANDISH WY | 067 | LEX | 2023-08-22 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2123.74 | 0 | 0 | 0 | 2123.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176940200 |  | 100302734 |  | 6712212N | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | STANDISH | 1261 STANDISH WY | 067 | LEX | 2023-08-22 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3096.72 | 0 | 0 | 0 | 3096.72 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179192800 |  | 500174063 |  | 7352256D | 2075305 |  |  | 565 | EX | RPLC SL/20026983500 | 2600B | RIGGLES | 2414 RIGGLES ST | 019 | ASH | 2023-08-21 | U125566 | U125763 | 2023-04-05 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-08-21 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2547.49 | 0 | 0 | 0 | 2547.49 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23193718000 |  | 100431393 |  | 7324132F |  |  |  | 566 | EX | ABANDON SERVICE LINE - DEMO | 2621P | OLD GARNER | 52 OLD GARNER RD | 119 | HIN | 2023-08-21 | JAHOWARD | U135005 | 2023-06-08 | 2023-07-31 | 2023-07-31 |  | JAHOWARD | 2023-08-21 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 16 | 2 | 1062.59 | 1004.95 | 0 | 57.64 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23193920100 |  | 100463527 |  | 6716204K |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | FOREST GREEN | 3973 FOREST GREEN DR | 067 | LEX | 2023-08-22 | U135005 | U135005 | 2023-06-09 | 2023-11-17 | 2025-05-31 |  | ABLAKE | 2023-08-21 | 2023-07-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 14.4167 | 4 | 1619.91 | 1263.46 | 215.09 | 75.36 | 66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23197678700 |  | 100324809 |  | 6720204A |  |  |  | 565 | EX | REPLACE SERVICE LINE D332525 | 2621P | SPENDTHRIFT | 1110 SPENDTHRIFT RD | 067 | LEX | 2023-08-21 | KKINDER | U135005 | 2023-06-28 | 2023-12-27 | 2025-06-30 |  | KKINDER | 2023-08-21 | 2023-07-21 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 22.7833 | 4 | 2213.7 | 1457.59 | 636.11 | 83.7 | 36.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23200393500 |  | 100435981 |  | 6716204D |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | MALABU | 827 MALABU DR 1FL | 067 | LEX | 2023-08-21 | WISHII | U135005 | 2023-07-12 | 2023-12-29 |  |  | WISHII | 2023-08-21 | 2023-08-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.9667 | 4 | 1802.68 | 849.7 | 341.66 | 503.52 | 107.8 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23207104300 |  | 100264126 |  | 7352260M | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2631D | MIDDLETOWN | 514 MIDDLETOWN AV | 019 | ASH | 2023-08-21 | BROBERT | AOC SYST | 2023-08-08 | 2024-02-08 | 2024-12-31 |  | BROBERT | 2023-08-21 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26310031 | 12.15 | 2 | 1780.63 | 937 | 320.24 | 523.39 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23208413800 |  | 500183899 |  | 6696212K |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | MACK | 116 MACK ST TLR | 239 | VER | 2023-08-22 | U135005 | U135005 | 2023-08-15 | 2023-12-29 |  |  | BWHITE | 2023-08-21 | 2023-08-17 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8.4333 | 3 | 608.62 | 575.61 | 0 | 33.01 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23209369100 |  | 100454081 |  | 6720212M | 1313369 |  |  | 566 | EX | SERVICE LINE ABANDON | 2621P | ASHLAND | 107 S ASHLAND AV 1FR | 067 | LEX | 2023-08-21 | SSHIMFE | U134852 | 2023-08-18 | 2023-08-18 |  |  | SSHIMFE | 2023-08-21 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 0.16667 | 1 | 10.48 | 9.9 | 0 | 0.58 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23209369300 |  | 100327587 |  | 6720212M | 1313369 |  |  | 566 | EX | SERVICE LINE ABANDON | 2621P | ASHLAND | 107 S ASHLAND AV 1FL | 067 | LEX | 2023-08-21 | SSHIMFE | U134852 | 2023-08-18 | 2023-08-18 |  |  | SSHIMFE | 2023-08-21 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 0.066667 | 1 | 14.17 | 13.39 | 0 | 0.78 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23209369400 |  | 100456520 |  | 6720212M | 1313369 |  |  | 566 | EX | SERVICE LINE ABANDON | 2621P | ASHLAND | 107 S ASHLAND AV 2FRR | 067 | LEX | 2023-08-21 | SSHIMFE | U134852 | 2023-08-18 | 2023-08-18 |  |  | SSHIMFE | 2023-08-21 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 7.7667 | 1 | 477.64 | 451.73 | 0 | 25.91 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23209633900 |  | 100342431 |  | 7240216N | 2286853 |  |  | 566 | EX | ABANDON SL W/22026170600 | 2621P | HOWARD | 115 HOWARD AV | 173 | MT | 2023-08-22 | U123111 | U131066 | 2023-08-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-21 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26290043 |  | 1 | 1493.98 | 0 | 0 | 0 | 1493.98 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23209706800 |  | 100345509 |  | 6696212H |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | PRESTON | 108 PRESTON CT | 239 | VER | 2023-08-21 | U128410 | U129939 | 2023-08-21 | 2023-08-21 |  |  | CDESPAIN | 2023-08-21 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2621 | 23209720800 |  | 100325115 |  | 6720204A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | ELMENDORF | 1028 ELMENDORF DR | 067 | LEX | 2023-08-21 | U128336 | U129939 | 2023-08-21 | 2023-08-21 | 2025-06-30 |  | JOSHUA COX | 2023-08-21 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 30.25 | 3 | 2208.5 | 1633.96 | 369.75 | 93.69 | 111.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23209730900 |  | 100342426 |  | 7240216N | 2286853 |  |  | 566 | EX | ABANDN SL/22026170600 | 2600B | HIGH | 49 W HIGH ST | 173 | MT | 2023-08-22 | U123111 | U125763 | 2023-08-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-21 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1385.36 | 0 | 0 | 0 | 1385.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 17553479400 |  | 100312203 | 31 | 6716208E |  |  |  | 565 | EX | REPL SERV/MOVE MTR - PER MC | 2621P | FAIRFIELD | 516 FAIRFIELD DR | 067 | LEX | 2023-08-22 | WISHII | CMCOX | 2017-10-12 | 2018-01-12 |  |  | WISHII | 2023-08-22 | 2023-07-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.6167 | 7 | 2001.42 | 1079.07 | 249.44 | 611.31 | 61.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 20026976900 |  |  |  | 6760172J | 2074684 | U128885 |  | 909 | EX | INSTALL RTU & INSTRUMENTATION | 2600E | DUG HILL | 724 DUG HILL RD | 065 | IRV | 2024-02-12 | U123258 | U128885 | 2020-09-28 | 2020-12-23 | 2020-12-31 | 2023-08-22 | WSHIMFE | 2023-08-22 | 2022-09-27 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00909 | 3200909 |  |  | WP9769 |  |  | 100 | 090932200269769 | 225.0833 | 0 | 362179.42 | 22225.94 | 0 | 4202.29 | 320534.33 | 0 | 15216.86 | 0
KY | KY - CENTRAL | 2629 | 20026977000 |  |  |  | 6760172J | 2074684 | U128885 |  | 910 | EX | RETIRE RTU & INSTRUMENTATION | 2600E | DUG HILL | 724 DUG HILL RD | 065 | IRV | 2024-02-12 | U123258 | U128885 | 2020-09-28 | 2020-12-31 | 2020-12-31 | 2023-08-22 | WSHIMFE | 2023-08-22 |  |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00910 | 3200910 |  |  | WP9770 |  |  | 100 | 091032200269770 | 32 | 0 | 2598.25 | 2460.96 | 0 | 137.29 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883107500 |  | 500550199 |  | 7344264A | 2178949 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | SR 1654 | 2822 SR 1654 | 019 | RUS | 2023-08-22 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-22 | 2022-12-15 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.1 | 3 | 14020.57 | 307.46 | 0 | 13713.11 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979022300 |  | 100257675 |  | 7344264-A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | UHLAN BRANCH | UHLAN BRANCH RD | 089 | WUR | 2023-08-22 | RECUMP | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | RECUMP | 2023-08-22 | 2023-07-12 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.0667 | 2 | 506.94 | 289.29 | 0 | 217.65 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164751000 |  | 500040052 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 309 ELM CT | 209 | GEO | 2023-08-22 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.9333 | 1 | 3329.05 | 410.48 | 0 | 101.74 | 2816.83 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164768600 |  | 500018606 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 503 ELM CT | 209 | GEO | 2023-08-22 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.0667 | 1 | 2651.87 | 64.06 | 0 | 15.88 | 2571.93 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168513300 |  | 100342703 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOWARD | 110 HOWARD AV | 173 | MT | 2023-08-23 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-22 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3770.54 | 0 | 0 | 0 | 3770.54 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168513400 |  | 100342702 |  | 7240216N | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOWARD | 114 HOWARD AV | 173 | MT | 2023-08-23 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-22 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 5268.05 | 0 | 0 | 0 | 5268.05 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176938700 |  | 500648371 |  | 6712212J | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | JOHN ALDEN | 4033 JOHN ALDEN LN | 067 | LEX | 2023-08-22 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2339.8 | 0 | 0 | 0 | 2339.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176939900 |  | 100302733 |  | 6712212N | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | STANDISH | 1253 STANDISH WY | 067 | LEX | 2023-08-22 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3211.34 | 0 | 0 | 0 | 3211.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176940000 |  | 100302742 |  | 6712212N | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | STANDISH | 1256 STANDISH WY | 067 | LEX | 2023-08-22 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2104.35 | 0 | 0 | 0 | 2104.35 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179193100 |  | 100262511 |  | 7352256C | 2075305 |  |  | 565 | EX | RPLC SL/20026983500 | 2600B | RIGGLES | 2427 RIGGLES ST | 019 | ASH | 2023-08-22 | U125566 | U125763 | 2023-04-05 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-08-22 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3305.71 | 0 | 0 | 0 | 3305.71 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23180721900 |  | 100251405 |  | 7336276T |  |  |  | 566 | EX | ABANDON SL - IDLE/INA **TCO** | 2621P | OHIO RIVER | 3901 OHIO RIVER RD | 089 | GRE | 2023-08-23 | U135005 | U125208 | 2023-04-12 | 2023-12-29 | 2024-12-31 |  | JKEENER | 2023-08-22 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.5833 | 2 | 421.89 | 398.86 | 0 | 23.03 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23200029900 |  | 100324498 |  | 6720204E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | ARMSTRONG MILL | 1153 ARMSTRONG MILL RD | 067 | LEX | 2023-08-22 | U128336 | U135005 | 2023-07-11 | 2023-12-29 |  |  | JOSHUA COX | 2023-08-22 | 2023-08-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.4667 | 3 | 3766.79 | 1615.28 | 545.49 | 1542.22 | 63.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23203727800 |  | 100337017 |  | 6720212I |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | OHIO | 447 OHIO ST | 067 | LEX | 2023-08-22 | TROE | U135005 | 2023-07-25 | 2023-12-29 |  |  | TROE | 2023-08-22 | 2023-07-31 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.4167 | 4 | 1544.5 | 1226.92 | 205.76 | 71.12 | 40.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23208722500 |  | 100286262 |  | 6764172G |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | LINCOLN | 120 LINCOLN AV | 065 | IRV | 2023-08-23 | U135005 | U133234 | 2023-08-16 | 2023-08-30 | 2023-09-15 |  | DENNING | 2023-08-22 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 12.2 | 3 | 844.38 | 779.37 | 20.27 | 44.74 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23209771600 |  | 501346237 |  | 6728208I | 2396366 |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | TWILIGHT SHADO | 1159 TWILIGHT SHADO DR LT132 | 067 | LEX | 2023-08-22 | U930915 | U129939 | 2023-08-21 | 2023-08-21 | 2023-08-21 |  | HMCKUNE | 2023-08-22 | 2023-08-21 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 18.6667 | 4 | 1303.66 | 941.27 | 200.61 | 53.98 | 107.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23209987000 |  | 100346093 |  | 6700212I |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | WOODFORD | 119 WOODFORD ST | 239 | VER | 2023-08-22 | U128410 | U135005 | 2023-08-22 | 2023-08-22 | 2023-08-22 |  | CDESPAIN | 2023-08-22 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 21.3333 | 4 | 1938.36 | 1273.88 | 554.05 | 73.03 | 37.4 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23210022900 |  | 500349436 |  | 7352252E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | US ROUTE 60 | 6417 US ROUTE 60 | 019 | ASH | 2023-08-22 | JROGER1 | U135005 | 2023-08-22 | 2023-10-20 | 2023-10-22 |  | JROGER1 | 2023-08-22 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 6.6333 | 3 | 1734.32 | 819.94 | 60.01 | 692.67 | 161.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23210043400 |  | 100297259 |  | 6720212E |  |  |  | 565 | EX | RPLC SL/ | 2600B | LIMESTONE | 363 N LIMESTONE ST 1FL | 067 | LEX | 2023-08-22 | U126532 | U125763 | 2023-08-22 | 2023-12-29 |  |  | LESLIE SHARON | 2023-08-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 3141.27 | 0 | 0 | 0 | 3141.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23210047900 |  | 100297257 |  | 6720212E |  |  |  | 566 | EX | ABANDN SL/ | 2600B | LIMESTONE | 363 N LIMESTONE ST 2FR | 067 | LEX | 2023-08-22 | U126532 | U125763 | 2023-08-22 | 2023-12-29 |  |  | LESLIE SHARON | 2023-08-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 23210048200 |  | 100297258 |  | 6720212E |  |  |  | 566 | EX | ABANDN SL/ | 2600B | LIMESTONE | 363 N LIMESTONE ST 2FL | 067 | LEX | 2023-08-22 | U126532 | U125763 | 2023-08-22 | 2023-12-29 |  |  | LESLIE SHARON | 2023-08-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 23210048400 |  | 100297260 |  | 6720212E |  |  |  | 566 | EX | ABANDN SL/ | 2600B | LIMESTONE | 363 N LIMESTONE ST 1FR | 067 | LEX | 2023-08-22 | U126532 | U125763 | 2023-08-22 | 2023-12-29 |  |  | LESLIE SHARON | 2023-08-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - EAST | 2633 | 21883245600 |  | 100431987 |  | 7356156T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW4653 | PW4653 | 071 | BET | 2023-08-23 | U130172 | U120245 | 2021-01-30 | 2023-08-23 | 2023-12-31 |  | BRIAN PREECE | 2023-08-23 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.15 | 1 | 209.8 | 198.41 | 0 | 11.39 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026223600 |  | 501337556 |  | 6724204A | 2291616 | U461383 |  | 555 | EX | INSTALL 3000' OF 2"PMMP MAIN | 2600B | BAY SHOALS | BAY SHOALS DR LT99 | 067 | LEX | 2023-08-29 | U124014 | U461383 | 2022-09-14 | 2023-07-03 | 2023-08-30 | 2023-08-23 | DEREK PAYTON | 2023-08-23 | 2023-07-31 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2236 |  |  | 100 | 055532220262236 | 126.5833 | 46928 | 80798.26 | 7254.3 | 6437.22 | 560.15 | 50946.47 | 0 | 448.8 | 15151.32 | 2933
KY | KY - CENTRAL | 2632 | 23154552300 |  | 100445135 |  | 7260276D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | MASON LEWIS | 9047 MASON LEWIS RD | 161 | MAY | 2023-08-23 | SDADAMS | U125763 | 2023-01-10 | 2023-12-29 | 2023-12-31 |  | SDADAMS | 2023-08-23 | 2023-05-31 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 33.3333 | 7 | 2738.53 | 2095.48 | 48.64 | 594.41 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23164751700 |  | 500018610 |  | 6712232O | 2286608 |  |  | 565 | EX | RPLC SL/22026168600 | 2600B | ELM | 407 ELM CT | 209 | GEO | 2023-08-23 | U461443 | U125763 | 2023-02-03 | 2023-12-29 |  |  | WGRAVES | 2023-08-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.0833 | 1 | 2476.05 | 358.86 | 0 | 88.96 | 2028.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165284900 |  | 100336847 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | LIMESTONE | 460 N LIMESTONE ST | 067 | LEX | 2023-08-23 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-08-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.8833 | 1 | 3318.27 | 311.77 | 0 | 17.91 | 2988.59 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168514800 |  | 100342569 |  | 7240216M | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ROGERS | 210 ROGERS AV | 173 | MT | 2023-08-28 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-23 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3989.64 | 0 | 0 | 0 | 3989.64 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168514900 |  | 100342568 |  | 7240216M | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ROGERS | 212 ROGERS AV | 173 | MT | 2023-08-28 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-23 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3951.73 | 0 | 0 | 0 | 3951.73 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23175085300 |  | 100283541 |  | 6712228E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | HIAWATHA | 503 HIAWATHA TL | 209 | GEO | 2023-08-23 | DCOLLIN | AOC SYST | 2023-03-20 | 2023-09-20 | 2024-12-31 |  | DCOLLIN | 2023-08-23 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 25.4333 | 4 | 3030.7 | 1693.33 | 255.83 | 977.04 | 104.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176938400 |  | 500648373 |  | 6712212J | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | JOHN ALDEN | 4025 JOHN ALDEN LN | 067 | LEX | 2023-08-23 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2901.58 | 0 | 0 | 0 | 2901.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176938600 |  | 500648372 |  | 6712212J | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | JOHN ALDEN | 4029 JOHN ALDEN LN | 067 | LEX | 2023-08-23 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3006.84 | 0 | 0 | 0 | 3006.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176939700 |  | 500008780 |  | 6712212J | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | STANDISH | 1249 STANDISH WY | 067 | LEX | 2023-08-23 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2173.6 | 0 | 0 | 0 | 2173.6 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179193000 |  | 100262512 |  | 7352256D | 2075305 |  |  | 565 | EX | RPLC SL/20026983500 | 2600B | RIGGLES | 2417 RIGGLES ST | 019 | ASH | 2023-08-23 | U125566 | U125763 | 2023-04-05 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-08-23 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2635.54 | 0 | 0 | 0 | 2635.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23200699300 |  | 100311395 |  | 6712204D |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | SAYBROOK | 3419 SAYBROOK RD | 067 | LEX | 2023-08-23 | KKINDER | U135005 | 2023-07-13 | 2023-12-29 |  |  | KKINDER | 2023-08-23 | 2023-07-21 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 20.3167 | 4 | 1895.79 | 1189.48 | 578.37 | 69.64 | 58.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23203015900 |  | 100337569 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | LIMESTONE | 600 N LIMESTONE ST B | 067 | LEX | 2023-08-29 | U135005 | U133234 | 2023-07-24 | 2023-08-07 | 2023-08-23 |  | TROE | 2023-08-23 | 2023-07-31 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 22.0667 | 6 | 2070.76 | 1324.22 | 21.98 | 76.56 | 648 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23206509500 |  | 100339267 |  | 6724212F |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | BILOXI | 1805 BILOXI CT | 067 | LEX | 2023-08-23 | HMCKUNE | U135005 | 2023-08-04 | 2023-12-29 |  |  | HMCKUNE | 2023-08-23 | 2023-08-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.0667 | 4 | 1378.6 | 803.83 | 460.44 | 46.13 | 68.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23211442000 |  | 500853531 |  | 6720212E | 0356751 |  |  | 566 | EX | PAPER ABANDON | 2621P | LIMESTONE | 600 N LIMESTONE ST A | 067 | LEX | 2023-08-29 | U135005 | U135005 | 2023-08-29 | 2023-12-29 |  |  | TROE | 2023-08-23 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - CENTRAL | 2632 | 21883199500 |  | 100344157 |  | NEW |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | RR2 BOX 363 | RR2 BOX 363 | 135 | TOL | 2023-08-28 | U135005 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | SDADAMS | 2023-08-24 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 3.6167 | 3 | 234.38 | 221.68 | 0 | 12.7 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883214800 |  | 100418061 |  | 7380144T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW5868 | PW5868 | 195 | PHY | 2023-08-25 | U130172 | U120245 | 2021-01-30 | 2023-08-24 |  |  | BRIAN PREECE | 2023-08-24 | 2023-08-24 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.1167 | 1 | 642.62 | 320.07 | 0 | 322.55 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883314600 |  | 100420474 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | INE | 2023-08-24 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN HOWARD | 2023-08-24 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.7833 | 1 | 252.73 | 239.01 | 0 | 13.72 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958665500 |  | 100331889 |  | 6720212M |  |  |  | 566 | EX | ABANDON SL | 2621P | ASHLAND | 142 N ASHLAND AV 2F | 067 | LEX | 2023-08-24 | U126308 | U134723 | 2021-12-08 | 2022-12-30 |  |  | J ENSMINGER | 2023-08-24 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 1.4667 | 2 | 76.71 | 72.55 | 0 | 4.16 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168515000 |  | 100342567 |  | 7240216M | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ROGERS | 214 ROGERS AV | 173 | MT | 2023-08-25 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-24 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 5593.78 | 0 | 0 | 0 | 5593.78 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23174360000 |  | 100283535 |  | 6712228E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | HIAWATHA | 500 HIAWATHA TL | 209 | GEO | 2023-08-24 | DCOLLIN | AOC SYST | 2023-03-16 | 2023-09-15 | 2024-12-31 |  | DCOLLIN | 2023-08-24 | 2023-08-23 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 34.3167 | 6 | 3934.09 | 2297.14 | 304.58 | 1255.37 | 77 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176938100 |  | 100302725 |  | 6712212J | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | JOHN ALDEN | 4017 JOHN ALDEN LN | 067 | LEX | 2023-08-24 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2032.33 | 0 | 0 | 0 | 2032.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176938200 |  | 100302726 |  | 6712212J | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | JOHN ALDEN | 4021 JOHN ALDEN LN | 067 | LEX | 2023-08-24 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3269.51 | 0 | 0 | 0 | 3269.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23196922000 |  | 100337535 |  | 6720212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | 6TH | 297 E 6TH ST | 067 | LEX | 2023-08-28 | U135005 | U135005 | 2023-06-26 | 2023-12-21 | 2025-06-30 |  | LSTONE | 2023-08-24 | 2023-07-26 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.7667 | 4 | 1742.96 | 1100.85 | 160.47 | 63.24 | 418.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23197680600 |  | 100325142 |  | 6720204A |  |  |  | 565 | EX | REPLACE SERVICE LINE D332947 | 2621P | DIXIANA | 3420 DIXIANA DR | 067 | LEX | 2023-08-24 | U930915 | U135005 | 2023-06-28 | 2023-12-27 | 2025-06-30 |  | ABLAKE | 2023-08-24 | 2023-08-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 49.55 | 7 | 3579.45 | 2866.11 | 452.11 | 164.43 | 96.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23200368200 |  | 100323697 |  | 6716204C |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | MALABU | 732 MALABU DR | 067 | LEX | 2023-08-24 | U930915 | U135005 | 2023-07-12 | 2023-12-29 |  |  | RJCRAWF | 2023-08-24 | 2023-08-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.6333 | 6 | 1676.11 | 1312.05 | 195.33 | 75.23 | 93.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23205925100 |  | 100334566 |  | 6720208H |  |  |  | 565 | EX | REPLACE SL/REPLACE RISER | 2621P | MULBERRY | 357 MULBERRY RD | 067 | LEX | 2023-08-28 | U135005 | U135005 | 2023-08-02 | 2023-12-29 |  |  | RSTRONG | 2023-08-24 | 2023-08-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 40.95 | 9 | 2254.18 | 1845.95 | 179.8 | 180.03 | 48.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23207640000 |  | 100296199 |  | 6716216O |  |  |  | 565 | EX | REPLACE/RELOCATE SERVICE LINE | 2621P | WAVERLY | 948 WAVERLY DR | 067 | LEX | 2023-08-24 | WISHII | U135005 | 2023-08-10 | 2023-10-09 | 2023-10-09 |  | WISHII | 2023-08-24 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 16 | 2 | 1617.04 | 816.76 | 218.59 | 521.19 | 60.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23210334900 |  | 100325143 |  | 6720204A |  |  |  | 565 | EX | REPLACE SL | 2621P | DIXIANA | 3416 DIXIANA DR | 067 | LEX | 2023-08-24 | U930915 | U138664 | 2023-08-23 | 2023-08-23 |  |  | ABLAKE | 2023-08-24 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 3.2667 | 2 | 794.22 | 185.63 | 525.34 | 10.65 | 72.6 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11881542200 |  | 500595834 |  | 7356248-H | 2180320 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | ICE CREEK | 8704< ICE CREEK RD | 019 | CAT | 2023-08-25 | RECUMP | U906609 | 2011-01-27 | 2023-08-24 |  |  | RECUMP | 2023-08-25 | 2023-08-24 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 | 5.55 | 2 | 1097.24 | 310.47 | 0 | 59.97 | 726.8 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11918603800 |  | 100243502 |  | 7356216D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PIKE | 309 N PIKE ST | 127 | LOU | 2023-08-25 | RECUMP | U907001 | 2011-08-02 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-25 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.5167 | 2 | 379.47 | 194.71 | 0 | 184.76 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 16462189900 |  | 100310539 |  | 6712208L |  |  |  | 565 | EX | REPLACE W/LCB / OS 02-26-20 | 2621P | SEATTLE | 550 SEATTLE DR | 067 | LEX | 2023-08-25 | WISHII | U125208 | 2016-12-21 | 2049-12-31 |  |  | WISHII | 2023-08-25 | 2023-07-31 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.1833 | 5 | 1953.33 | 1081.67 | 239.88 | 562.48 | 69.3 | 0 | 0 | 0
KY | KY - EAST | 2631 | 20026968700 |  |  |  | 7348264-B | 2073961 | U132280 |  | 557 | EX | EMER - INSTALL 5' - 2" PMIP | 2621P | NEW HAVEN | NEW HAVEN | 089 | FLA | 2023-08-25 | U128132 | U461492 | 2020-08-20 | 2023-12-21 | 2023-12-25 | 2020-08-17 | BROBERT | 2023-08-25 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP9687 |  |  | 100 | 055732200269687 | 2.6333 | 4 | 299.11 | 131.07 | 0 | 84.6 | 26.4 | 0 | 0 | 57.04 | 2
KY | KY - EAST | 2631 | 20026968800 |  |  |  | 7348260B | 2073961 | U132280 |  | 558 | EX | EMER - RETIRE 5'- 2" PMIP | 2621P | NEW HAVEN | NEW HAVEN | 089 | FLA | 2023-08-25 | U128132 | U461492 | 2020-08-20 | 2023-12-21 | 2023-12-25 | 2020-08-17 | BROBERT | 2023-08-25 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP9688 |  |  | 100 | 055832200269688 | 2.2 | 0 | 182.45 | 110.89 | 0 | 71.56 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883103700 |  | 100261754 |  | 7344144T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | P2 | P2 | 071 | MCD | 2023-08-25 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN HOWARD | 2023-08-25 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.2833 | 1 | 220.63 | 208.67 | 0 | 11.96 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883172000 |  | 100261741 |  | 7344144T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | P13 | P13 | 071 | MCD | 2023-08-25 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN HOWARD | 2023-08-25 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 4.7167 | 1 | 314.24 | 297.18 | 0 | 17.06 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21958666800 |  | 100327599 |  | 6720212M |  |  |  | 566 | EX | ABANDON SL DOWNSTREAM/SOII | 2621P | MAIN | 800 E MAIN ST | 067 | LEX | 2023-08-25 | U126308 | U134723 | 2021-12-08 | 2022-12-30 |  |  | J ENSMINGER | 2023-08-25 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 1.2833 | 1 | 87.6 | 82.86 | 0 | 4.74 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960854500 |  | 100250190 |  | 7356248D | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | FLEMING | 8427 FLEMING CT | 019 | CAT | 2023-08-25 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER/MBLANKE | 2023-08-25 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2727.31 | 0 | 0 | 0 | 2727.31 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960854600 |  | 100250191 |  | 7356248D | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | FLEMING | 8437 FLEMING CT | 019 | CAT | 2023-08-25 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER/MBLANKE | 2023-08-25 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2463.67 | 0 | 0 | 0 | 2463.67 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22026180700 |  |  |  | 7352256O | 2288081 | U132280 |  | 557 | EX | EMER - INSTALL 3'-3" PMIP | 2621P | WOODHAVEN | WOODHAVEN | 019 | ASH | 2023-10-27 | U128132 | U132280 | 2022-04-08 | 2022-09-12 |  | 2022-04-09 | BROBERT | 2023-08-25 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP1807 |  |  | 100 | 055732220261807 | 1.6 | 8 | 6701.19 | 2946.34 | 93.12 | 2569.98 | 25.3 | 0 | -12.96 | 1079.41 | 4
KY | KY - EAST | 2631 | 22026180800 |  |  |  | 7352256O | 2288081 | U132280 |  | 558 | EX | EMER - RETIRE 3'-3" PMIP | 2621P | WOODHAVEN | WOODHAVEN | 019 | ASH | 2023-08-29 | U128132 | U132280 | 2022-04-08 | 2022-09-13 |  | 2022-04-09 | BROBERT | 2023-08-25 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP1808 |  |  | 100 | 055832220261808 | 0.73333 | 0 | 61.4 | 37.3 | 0 | 24.1 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129062700 |  | 100356543 |  | 7256280P |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | US 68 | 783 US 68 | 161 | MAY | 2023-08-25 | SDADAMS | U130722 | 2022-09-05 | 2022-12-30 |  |  | SDADAMS | 2023-08-25 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 1.4833 | 1 | 95.36 | 90.19 | 0 | 5.17 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22134915400 |  | 100277289 |  | 6684228G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HOLMES | 217 HOLMES ST 1F | 073 | FRA | 2023-08-25 | EFGOINS | U130722 | 2022-09-27 | 2022-12-30 |  |  | EFGOINS | 2023-08-25 | 2023-08-24 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 10.7333 | 3 | 610.39 | 577.27 | 0 | 33.12 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026264500 |  |  |  | 7348248P | 2395955 | U122858 |  | 557 | EX | EMER - INSTALL ~5'-4" PM/CSMP | 2621P | MIDLAND TRAIL | MIDLAND TRAIL | 019 | CAN | 2023-10-23 | U128132 | U132280 | 2023-03-02 | 2023-11-30 |  | 2023-03-02 | BROBERT | 2023-08-25 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP2645 |  |  | 100 | 055732230262645 | 1.3333 | 10 | 929.35 | 378.05 | 0 | 291.09 | 25.3 | 0 | 0 | 234.91 | 5
KY | KY - EAST | 2631 | 23026264600 |  |  |  | 7348248P | 2395955 | U122858 |  | 558 | EX | EMER - RETIRE ~5'-4" CSMP | 2621P | MIDLAND TRAIL | MIDLAND TRAIL | 019 | CAN | 2023-10-27 | U128132 | U132280 | 2023-03-02 | 2023-11-30 |  | 2023-03-02 | BROBERT | 2023-08-25 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP2646 |  |  | 100 | 055832230262646 | 2.5 | 0 | 207.34 | 125.99 | 0 | 81.35 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026265700 |  |  |  | 7352256B | 2396051 | U132280 |  | 558 | EX | EMER - RETIRE 4'-6" P-IP | 2621P | OLD BUCKLEY | 508 OLD BUCKLEY RD | 019 | ASH | 2023-10-27 | U128132 | U132280 | 2023-03-07 | 2023-11-30 |  | 2023-03-07 | BROBERTS | 2023-08-25 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP2657 |  |  | 100 | 055832230262657 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026269600 |  |  |  | 7344264C | 2396545 | U132280 |  | 558 | EX | EMER - RETIRE 5'-2" PIP | 2621P | WURTLAND | WURTLAND | 089 | GRE | 2023-10-27 | U128132 | U132280 | 2023-03-28 | 2023-11-30 |  | 2023-03-28 | BROBERTS | 2023-08-25 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP2696 |  |  | 100 | 055832230262696 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168512800 |  | 100342566 |  | 7240216M | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | HOLT | 502 HOLT AV | 173 | MT | 2023-08-25 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-25 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3652.22 | 0 | 0 | 0 | 3652.22 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168514600 |  | 100342570 |  | 7240216M | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ROGERS | 206 ROGERS AV | 173 | MT | 2023-08-25 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-25 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2543.13 | 0 | 0 | 0 | 2543.13 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23173666300 |  | 100283576 |  | 6712228A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | PUEBLO | 505 PUEBLO TL | 209 | GEO | 2023-08-25 | DCOLLIN | AOC SYST | 2023-03-14 | 2023-09-14 | 2024-12-31 |  | DCOLLIN | 2023-08-25 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 16 | 2 | 1886.06 | 1067.38 | 304.58 | 458 | 56.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176938000 |  | 100302753 |  | 6712212K | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | JOHN ALDEN | 4016 JOHN ALDEN LN | 067 | LEX | 2023-08-28 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2416.56 | 0 | 0 | 0 | 2416.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23205453900 |  | 100295201 |  | 6716212H |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | JEFFERSON | 454 JEFFERSON ST | 067 | LEX | 2023-08-25 | RSTRONG | U133234 | 2023-08-01 | 2023-08-15 | 2023-08-31 |  | RSTRONG | 2023-08-25 | 2023-08-16 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 25.5333 | 8 | 2119.7 | 1207.08 | 35.11 | 286.75 | 590.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23208469000 |  | 100338880 |  | 6720212F | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER | 2621D | LOUDON | 653 E LOUDON AV | 067 | LEX | 2023-08-29 | U135005 | AOC SYST | 2023-08-15 | 2023-09-14 | 2023-10-14 |  | LSTANFI | 2023-08-25 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 8.75 | 2 | 1003.16 | 528.88 | 178.89 | 162.29 | 133.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23209650900 |  | 100435769 |  | 6704212L |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | WESTMORLAND | 2634 WESTMORLAND DR | 067 | LEX | 2023-08-25 | KKINDER | U133234 | 2023-08-21 | 2023-09-01 | 2023-09-20 |  | KKINDER | 2023-08-25 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16 | 2 | 1101.02 | 979.61 | 65.22 | 56.19 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23211024400 |  | 100294816 |  | 6716212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | UPPER | 412 N UPPER ST | 067 | LEX | 2023-08-25 | U126532 | U125763 | 2023-08-25 | 2023-12-29 |  |  | LESLIE SHARON | 2023-08-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.5167 | 1 | 2591.28 | 415.41 | 0 | 23.83 | 2152.04 | 0 | 0 | 0
KY | KY - EAST | 2682 | 23211058500 |  | 100426576 |  | NEW |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | GENERAL DELIVE | GENERAL DELIVE | 119 | BRI | 2023-08-25 | U130172 | U134852 | 2023-08-25 | 2023-08-25 |  |  | BRIAN PREECE | 2023-08-25 |  |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 4.5833 | 1 | 304.78 | 288.25 | 0 | 16.53 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026265600 |  |  |  | 7352256B | 2396051 | U132280 |  | 557 | EX | EMER - INSTALL 4'-6" PMIP | 2621P | OLD BUCKLEY | 508 OLD BUCKLEY RD | 019 | ASH | 2024-01-10 | U128132 | U132280 | 2023-03-07 | 2023-11-27 |  | 2023-03-07 | BROBERTS | 2023-08-26 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP2656 |  |  | 100 | 055732230262656 |  | 4 | 19713.32 | 12403.37 | 1571.52 | 2101.5 | 648.4 | 0 | 6.17 | 2982.36 | 4
KY | KY - EAST | 2631 | 23026269500 |  |  |  | 7344264C | 2396545 | U132280 |  | 557 | EX | EMER - INSTALL 4'-2" PIP | 2621P | WURTLAND | WURTLAND | 089 | GRE | 2024-01-10 | U128132 | U132280 | 2023-03-28 | 2023-11-29 |  | 2023-03-28 | BROBERTS | 2023-08-26 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP2695 |  |  | 100 | 055732230262695 |  | 4 | 2717.09 | 1515.81 | 218.69 | 575.51 | 20.9 | 0 | 0 | 386.18 | 4
KY | KY - EAST | 2631 | 20026983500 |  |  |  | 7352256C | 2075305 | U132280 |  | 557 | EX | INSTALL 1670' - 2" PMMP | 2600B | RIGGLES | RIGGLES | 019 | ASH | 2023-09-16 | U128132 | U461492 | 2020-10-20 | 2023-11-08 | 2023-12-31 | 2023-07-28 | DAVID SKAGGS | 2023-08-28 | 2023-05-25 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP9835 | AMRCB |  | 100 | 055732200269835 | 390.05 | 104690 | 426217.2 | 28001.12 | 15921.55 | 6639.88 | 310842.88 | 0 | 1207.17 | 63604.6 | 1805
KY | KY - EAST | 2631 | 20026983600 |  |  |  | 7352256C | 2075305 | U132280 |  | 558 | EX | ABANDON 1667'-2/3/4" PMLP/BSLP | 2600B | RIGGLES | RIGGLES | 019 | ASH | 2023-09-12 | U128132 | U461492 | 2020-10-20 | 2023-12-29 | 2023-12-31 | 2023-07-28 | DAVID SKAGGS | 2023-08-28 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP9836 | AMRCB |  | 100 | 055832200269836 | 1.4 | 0 | 290.24 | 87.24 | 0 | 20.6 | 182.4 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883294300 |  | 100257231 |  | 7348264J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | COUNTY | 925 COUNTY RD | 089 | RAC | 2023-08-28 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-28 | 2023-08-21 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 7.55 | 2 | 1701.19 | 420 | 0 | 398.54 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026289300 |  |  |  | 7352256D | 2075305 | U122858 |  | 557 | EX | INSTALL 7'-2"&6" PMLP | 2600B | BLACKBURN | BLACKBURN | 019 | ASH | 2023-09-12 | U128132 | U122858 | 2023-08-23 | 2024-04-30 |  | 2023-07-28 | DAVID SKAGGS | 2023-08-28 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP2893 | AMRCB |  | 100 | 055732230262893 | 0.016667 | 6 | 447.65 | 4.43 | 47.72 | 0.25 | 275 | 0 | 0 | 120.25 | 6
KY | KY - WEST | 2621 | 23165282600 |  | 100297249 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | LIMESTONE | 371 N LIMESTONE ST | 067 | LEX | 2023-08-28 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-08-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.4667 | 1 | 3536.12 | 285.01 | 0 | 16.36 | 3234.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165282900 |  | 100336831 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | LIMESTONE | 404 N LIMESTONE ST | 067 | LEX | 2023-08-28 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-08-28 | 2023-08-23 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.15 | 2 | 2879.4 | 422.1 | 0 | 24.21 | 2433.09 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168514000 |  | 100342572 |  | 7240216M | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ROGERS | 196 ROGERS AV | 173 | MT | 2023-08-28 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-28 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2618.38 | 0 | 0 | 0 | 2618.38 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168514100 |  | 100342571 |  | 7240216M | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ROGERS | 198 ROGERS AV | 173 | MT | 2023-08-28 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-28 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3148.22 | 0 | 0 | 0 | 3148.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176937900 |  | 100302724 |  | 6712212K | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | JOHN ALDEN | 4013 JOHN ALDEN LN | 067 | LEX | 2023-08-28 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2065.66 | 0 | 0 | 0 | 2065.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23206513300 |  | 100339268 |  | 6724212F |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | BILOXI | 1803 BILOXI CT | 067 | LEX | 2023-08-28 | HMCKUNE | U135005 | 2023-08-04 | 2023-12-29 |  |  | HMCKUNE | 2023-08-28 | 2023-08-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.0333 | 6 | 1897.76 | 1349.13 | 406.3 | 77.43 | 64.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23208103400 |  | 100308343 |  | 6716212N |  |  |  | 565 | EX | REPLACE STEEL SERVICE LINE | 2621P | INGLESIDE | 503 INGLESIDE DR | 067 | LEX | 2023-08-28 | KKINDER | U135005 | 2023-08-14 | 2023-10-13 | 2023-10-13 |  | KKINDER | 2023-08-28 | 2023-08-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.5167 | 3 | 1331.72 | 1051.34 | 187.07 | 60.31 | 33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19732796000 |  | 100303356 |  | 6712208C |  |  |  | 565 | EX | SERV LINE - REPL: UNLOCATABLE | 2621P | BALSAM | 1029 BALSAM DR | 067 | LEX | 2023-08-30 | U135005 | U125208 | 2019-08-14 | 2049-12-31 |  |  | RSTRONG | 2023-08-29 | 2023-07-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 34.3333 | 9 | 2439.88 | 1609.9 | 385.9 | 374.78 | 69.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19742840000 |  | 100306869 |  | 6716212I |  |  |  | 565 | EX | AOC - REPL SL & REBUILD MP LOO | 2621P | HILL RISE | 1715 HILL RISE DR 1 | 067 | LEX | 2023-08-29 | WISHII | U125208 | 2019-09-18 | 2019-09-30 |  |  | WISHII | 2023-08-29 | 2023-07-12 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.1667 | 8 | 1639.76 | 1018.57 | 0 | 580.49 | 40.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883322500 |  | 100249619 |  | 7356216D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | ROUTE 5 | ROUTE 5 | 127 | LOU | 2023-08-29 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-08-29 | 2022-11-16 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 17.5667 | 6 | 1873.13 | 966.09 | 0 | 907.04 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959269100 |  | 100261043 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | MCGUIRE | 141 MCGUIRE AV | 019 | ASH | 2023-08-29 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-08-29 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2647.58 | 0 | 0 | 0 | 2647.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129047800 |  | 500885016 |  | 6716212L | 0460888 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LIMESTONE | 357 S LIMESTONE ST CABLE | 067 | LEX | 2023-08-29 | HMCKUNE | U130722 | 2022-09-05 | 2022-12-30 |  |  | HMCKUNE | 2023-08-29 | 2023-07-06 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.8333 | 10 | 964 | 894.17 | 17.64 | 52.19 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22152711000 |  | 100318486 |  | 6716204C |  |  |  | 565 | EX | SERVICE LINE REPLACE | 2621P | HIGHTOWER | 275 HIGHTOWER RD | 067 | LEX | 2023-08-29 | KKINDER | U134852 | 2022-12-30 | 2022-12-30 |  |  | KKINDER | 2023-08-29 | 2023-07-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.3667 | 6 | 1775.53 | 1038.78 | 599.28 | 59.37 | 78.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165284700 |  | 100336845 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | LIMESTONE | 450 N LIMESTONE ST | 067 | LEX | 2023-08-29 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-08-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.5167 | 1 | 2993.88 | 542.7 | 0 | 31.13 | 2420.05 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168514200 |  | 100342573 |  | 7240216M | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ROGERS | 199 ROGERS AV | 173 | MT | 2023-09-05 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-29 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2288.77 | 0 | 0 | 0 | 2288.77 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168514400 |  | 100342574 |  | 7240216M | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ROGERS | 201 ROGERS AV | 173 | MT | 2023-09-05 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-29 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2816.21 | 0 | 0 | 0 | 2816.21 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176937800 |  | 100302723 |  | 6712212K | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | JOHN ALDEN | 4009 JOHN ALDEN LN | 067 | LEX | 2023-08-29 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2851.72 | 0 | 0 | 0 | 2851.72 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23180633900 |  | 100465695 |  | 6688228B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332754 | 2621P | TETON | 663 TETON TL A | 073 | FRA | 2023-08-30 | U135005 | U125208 | 2023-04-12 | 2023-10-11 | 2025-04-30 |  | BSEXTON | 2023-08-29 | 2023-08-29 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 19.65 | 3 | 2039.48 | 1423.86 | 371.44 | 81.38 | 162.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23209329300 |  | 100276193 |  | 6684228G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CHINN | 705 CHINN AV | 073 | FRA | 2023-08-30 | U135005 | U135005 | 2023-08-18 | 2023-08-16 | 2023-08-16 |  | DMEDLEY | 2023-08-29 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 | 1.3667 | 2 | 1180.83 | 986.74 | 0 | 119.29 | 74.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23211082600 |  | 100298885 |  | 6716212B |  |  |  | 565 | EX | SERVICE LINE UPGRADE | 2621P | LEESTOWN | 1301 LEESTOWN RD | 067 | LEX | 2023-08-29 | SSHIMFE | U135005 | 2023-08-25 | 2023-10-25 | 2023-10-25 |  | SSHIMFE | 2023-08-29 | 2023-08-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 35.25 | 6 | 6113.37 | 1904.47 | 434.32 | 109.23 | 3665.35 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23211276500 |  | 100328777 |  | 6720208F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309358 | 2621P | HART | 2020 HART RD | 067 | LEX | 2023-08-29 | U128336 | U135005 | 2023-08-28 | 2023-08-28 | 2023-08-28 |  | JOSHUA COX | 2023-08-29 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16 | 2 | 1657.66 | 979.43 | 496.68 | 56.15 | 125.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23211292100 |  | 100340281 |  | 6724212E |  |  |  | 565 | EX | GRADE 1 SERVICE REPLACE | 2621P | RALEIGH | 1714 RALEIGH RD | 067 | LEX | 2023-08-29 | U930915 | U129939 | 2023-08-28 | 2023-08-28 | 2023-08-28 |  | RSTRONG | 2023-08-29 | 2023-08-29 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.2167 | 3 | 1653.32 | 1076.36 | 278.08 | 242.78 | 56.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 17522362600 |  | 100321818 |  | 6716208D |  |  |  | 565 | EX | REPL SERV - UNMTRD GAS | 2621P | PARK | 516 PARK AV | 067 | LEX | 2023-08-30 | U930915 | U125208 | 2017-07-07 | 2017-07-27 |  |  | HMCKUNE | 2023-08-30 | 2023-08-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.15 | 4 | 1321.2 | 938.13 | 289.67 | 53.8 | 39.6 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959269200 |  | 100261040 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | MCGUIRE | 234 MCGUIRE ST | 019 | ASH | 2023-08-30 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-08-30 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2860.37 | 0 | 0 | 0 | 2860.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165284800 |  | 100336846 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | LIMESTONE | 456 N LIMESTONE ST | 067 | LEX | 2023-08-30 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-08-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.4667 | 1 | 2684.69 | 286.28 | 0 | 16.42 | 2381.99 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168514500 |  | 100342575 |  | 7240216M | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ROGERS | 205 ROGERS AV | 173 | MT | 2023-09-05 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-30 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2874.01 | 0 | 0 | 0 | 2874.01 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23168514700 |  | 100342577 |  | 7240216M | 2286853 |  |  | 565 | EX | RPLC SL/22026170600 | 2600B | ROGERS | 209 ROGERS AV | 173 | MT | 2023-09-05 | U123111 | U125763 | 2023-02-21 | 2023-12-29 |  |  | LYN STAFFORD | 2023-08-30 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2519.84 | 0 | 0 | 0 | 2519.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23174359600 |  | 100283514 |  | 6712228E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | HIAWATHA | 306 HIAWATHA TL | 209 | GEO | 2023-08-30 | DCOLLIN | AOC SYST | 2023-03-16 | 2023-09-15 | 2024-12-31 |  | DCOLLIN | 2023-08-30 | 2023-08-29 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 17.1 | 4 | 1971.86 | 1140.78 | 290.99 | 489.49 | 50.6 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23175425200 |  | 100283567 |  | 6712228A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | IROQUOIS | 551 IROQUOIS TL | 209 | GEO | 2023-08-30 | DCOLLIN | AOC SYST | 2023-03-21 | 2023-09-21 | 2024-12-31 |  | DCOLLIN | 2023-08-30 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 25.5 | 4 | 2601.27 | 1706.71 | 260.16 | 582.7 | 51.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23201811500 |  | 100323872 |  | 6716204D |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | CAHABA | 821 CAHABA RD | 067 | LEX | 2023-08-30 | JOCHOA | U135005 | 2023-07-18 | 2023-12-29 |  |  | JOCHOA | 2023-08-30 | 2023-08-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 44.6833 | 10 | 3404.29 | 2644.44 | 526.3 | 146.65 | 86.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23206515100 |  | 100339182 |  | 6724212I |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | CANTRILL | 1800 CANTRILL DR | 067 | LEX | 2023-08-31 | U135005 | U135005 | 2023-08-04 | 2023-12-29 |  |  | HSTANFI | 2023-08-30 | 2023-08-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17 | 5 | 1344.42 | 938.49 | 269.6 | 53.83 | 82.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23210039100 |  | 100282097 |  | 6712228C |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | CHAMBERS | 210 CHAMBERS AV A-DN | 209 | GEO | 2023-08-30 | DCOLLIN | U133234 | 2023-08-22 | 2023-09-05 | 2023-09-21 |  | DCOLLIN | 2023-08-30 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 19.2 | 4 | 1702.63 | 1278.17 | 0 | 424.46 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23210044600 |  | 500252841 |  | 6712228C |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | CHAMBERS | 210 CHAMBERS AV B-UP | 209 | GEO | 2023-08-30 | DCOLLIN | U133234 | 2023-08-22 | 2023-09-05 | 2023-09-21 |  | DCOLLIN | 2023-08-30 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.2 | 2 | 19.04 | 13.34 | 0 | 5.7 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23211515800 |  | 100304430 |  | 6712212P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D341310 | 2621P | STONEWALL | 957 STONEWALL RD | 067 | LEX | 2023-08-30 | KOBRYAN | U135005 | 2023-08-29 | 2023-08-29 | 2023-08-29 |  | KOBRYAN | 2023-08-30 | 2023-08-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.5167 | 3 | 1513.92 | 1177.64 | 225.69 | 66.59 | 44 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23211914900 |  | 100281722 |  | 6712232O | 2286608 |  |  | 566 | EX | RPLC SL/22026168600 | 2600B | POPLAR | 508 POPLAR ST | 209 | GEO | 2023-08-30 | U461443 | U125763 | 2023-08-30 | 2023-12-29 |  |  | WGRAVES | 2023-08-30 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1426.51 | 0 | 0 | 0 | 1426.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212202700 |  | 500926327 |  | 6720212E | 2177145 |  |  | 566 | EX | ABANDON SL/21026997801 | 2600B | LIMESTONE | 425 N LIMESTONE ST 1FL-2 | 067 | LEX | 2023-08-31 | U126532 | U125763 | 2023-08-31 | 2023-12-29 |  |  | LESLIE SHARON | 2023-08-30 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 0
KY | KY - EAST | 2631 | 21959273700 |  | 100261039 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | MCGUIRE | 242 MCGUIRE ST | 019 | ASH | 2023-08-31 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-08-31 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2510.85 | 0 | 0 | 0 | 2510.85 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026242700 |  |  |  | 6716216G | 2294344 | U461383 |  | 561 | EX | INSTALL 350' OF 8"CSHP MAIN | 2600B | GEORGETOWN | 2210 GEORGETOWN RD | 067 | LEX | 2023-10-10 | U124014 | U461383 | 2022-12-14 | 2023-07-10 | 2023-09-30 | 2023-08-24 | BPULLIAM | 2023-08-31 | 2023-07-11 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP2427 |  |  | 100 | 056132220262427 | 399.9833 | 19635 | 381751.32 | 25962.81 | 49848.81 | 29910.22 | 192317.02 | 0 | 0 | 83712.46 | 385
KY | KY - WEST | 2621 | 22026242800 |  |  |  | 6716216G | 2294344 | U461383 |  | 562 | EX | RETIRE 326' OF 8"CSHP MAIN | 2600B | GEORGETOWN | 2210 GEORGETOWN RD | 067 | LEX | 2023-09-08 | U124014 | U461383 | 2022-12-14 | 2023-09-01 | 2023-09-01 | 2023-08-24 | BPULLIAM | 2023-08-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP2428 |  |  | 100 | 056232220262428 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026254400 |  |  |  | 6716216G | 2294344 | U461383 |  | 561 | EX | INSTALL 420' OF 6"PMMP MAIN | 2600B | GEORGETOWN | 2210 GEORGETOWN RD | 067 | LEX | 2023-09-08 | U124014 | U461383 | 2023-01-27 | 2023-09-01 | 2023-09-30 | 2023-08-25 | BPULLIAM | 2023-08-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP2544 |  |  | 100 | 056132230262544 |  | 426 | -558.31 | 0 | 10084.03 | 0 | -12282.4 | 0 | 251.89 | 1388.17 | 426
KY | KY - WEST | 2621 | 23026254500 |  |  |  | 6716216G | 2294344 | U461383 |  | 562 | EX | RETIRE 356' OF 6"PMMP MAIN | 2600B | GEORGETOWN | 2210 GEORGETOWN RD | 067 | LEX | 2023-09-06 | U124014 | U461383 | 2023-01-27 | 2023-09-01 | 2023-09-01 | 2023-08-25 | BPULLIAM | 2023-08-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP2545 |  |  | 100 | 056232230262545 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026277300 |  |  |  | 6728212M | 2397784 | U461383 |  | 561 | EX | INSTALL 265' OF 6"PMMP MAIN | 2600B | POLO CLUB | 2585 POLO CLUB | 067 | LEX | 2023-09-01 | U128132 | U461383 | 2023-06-02 | 2023-08-22 | 2023-09-01 | 2023-08-30 | JAMIE LYNN | 2023-08-31 | 2023-08-22 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP2773 |  |  | 100 | 056132230262773 | 64.2833 | 2064 | 29277.24 | 4234.42 | 4663.24 | 856.03 | 14785.67 | 0 | 91.4 | 4646.48 | 258
KY | KY - WEST | 2621 | 23026277400 |  |  |  | 6728212M | 2397784 | U461383 |  | 562 | EX | RETIRE 285' OF 6"PMMP MAIN | 2600B | POLO CLUB | 2585 POLO CLUB | 067 | LEX | 2023-09-01 | U128132 | U461383 | 2023-06-02 | 2023-09-01 | 2023-09-01 | 2023-08-30 | JAMIE LYNN | 2023-08-31 | 2023-08-30 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP2774 |  |  | 100 | 056232230262774 | 3.7167 | 0 | 439.67 | 246.45 | 0 | 56.42 | 136.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166674900 |  | 100322668 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 713 PROVIDENCE RD | 067 | LEX | 2023-09-01 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-08-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3293.15 | 0 | 0 | 0 | 3293.15 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23176939200 |  | 100302730 |  | 6712212J | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | STANDISH | 1241 STANDISH WY | 067 | LEX | 2023-08-31 | U126603 | U125763 | 2023-03-29 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-08-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4935.79 | 0 | 0 | 0 | 4935.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23208432300 |  | 100319851 |  | 6716208K |  |  |  | 565 | EX | SERVICE LINE/METER UPGRADE | 2621P | ALBANY | 348 ALBANY RD | 067 | LEX | 2023-08-31 | U128336 | U135005 | 2023-08-15 | 2023-09-05 | 2023-09-05 |  | JOSHUA COX | 2023-08-31 | 2023-08-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 57.8667 | 8 | 7719.73 | 3464.04 | 1310.26 | 198.63 | 2746.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212003800 |  | 100340165 |  | 6724212E |  |  |  | 565 | EX | GRADE 1 SERVICE LINE REPLACE | 2621P | COURTLAND | 1840 COURTLAND DR | 067 | LEX | 2023-09-05 | U135005 | U129939 | 2023-08-30 | 2023-08-30 | 2023-08-30 |  | HSTANFI | 2023-08-31 | 2023-08-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.3667 | 6 | 1085.55 | 389.14 | 583.95 | 22.26 | 90.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212236600 |  | 500028887 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997801 | 2600B | 5TH | 316 W 5TH ST | 067 | LEX | 2023-08-31 | U126532 | U125763 | 2023-08-31 | 2023-12-29 |  |  | LESLIE SHARON | 2023-08-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.1 | 1 | 3072.61 | 199.16 | 0 | 11.41 | 2862.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 20768718200 |  | 100328925 | 18 | 6720208P |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | MOUNT TABOR | 485 MOUNT TABOR RD | 067 | LEX | 2023-09-01 | U930915 | U463010 | 2020-01-07 | 2020-03-06 |  |  | ABLAKE | 2023-09-01 | 2023-08-25 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.0333 | 8 | 1389.13 | 1175.07 | 147.12 | 66.94 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883129000 |  | 100429253 |  | 7352244M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | BEAR CREEK | BEAR CREEK RD | 127 | BUC | 2023-09-01 | RECUMP | U120245 | 2021-01-30 | 2023-08-30 | 2023-12-31 |  | RECUMP | 2023-09-01 | 2023-08-30 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 8.5167 | 3 | 952.2 | 494.94 | 0 | 457.26 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026258900 |  |  |  | 7348248F | 2294088 | U132703 |  | 909 | EX | INSTALL MIWI AND SUPER SOLAR | 2631M | PAUL COFFEY | PAUL COFFEY BV | 019 | CAN | 2023-09-11 | U123258 | U132703 | 2023-02-15 | 2023-12-01 | 2023-12-01 | 2023-09-01 | AMCCORMICK | 2023-09-01 | 2023-04-12 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP2589 |  |  | 100 | 090932230262589 | 44.3667 | 0 | 5852.27 | 2839.71 | 0 | 430.08 | 2530 | 0 | 52.48 | 0
KY | KY - CENTRAL | 2629 | 23026289900 |  |  |  | 6748180L | 2399734 | U128885 |  | 557 | EX | EMER-INSTALL 8'-3" PMMP | 2621P | COLLEGE HILL | 158 COLLEGE HILL RD | 151 | WAC | 2023-09-11 | U128132 | U128885 | 2023-08-25 | 2023-08-23 | 2023-09-06 | 2023-08-17 | WDENNING | 2023-09-01 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP2899 |  |  | 100 | 055732230262899 |  | 8 | 2980.18 | 0 | 0 | 0 | 2209.5 | 0 | 0 | 770.68 | 8
KY | KY - CENTRAL | 2629 | 23026290000 |  |  |  | 6748180L | 2399734 | U128885 |  | 558 | EX | EMER-RETIRE 8'-3" PAMP | 2621P | COLLEGE HILL | 158 COLLEGE HILL RD | 151 | WAC | 2023-09-11 | U128132 | U128885 | 2023-08-25 | 2023-08-23 | 2023-09-06 | 2023-08-17 | WDENNING | 2023-09-01 | 2023-08-29 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP2900 |  |  | 100 | 055832230262900 | 0.55 | 0 | 9034.26 | 3800.51 | 0 | 218.03 | 5015.72 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23175086400 |  | 100283572 |  | 6712228A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | PUEBLO | 613 PUEBLO TL | 209 | GEO | 2023-09-01 | DCOLLIN | AOC SYST | 2023-03-20 | 2023-09-20 | 2024-12-31 |  | DCOLLIN | 2023-09-01 | 2023-08-31 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 35.2 | 6 | 6966.84 | 2074.09 | 275.04 | 312.56 | 4305.15 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23201815000 |  | 100409492 |  | 6716204D |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | CAHABA | 836 CAHABA RD | 067 | LEX | 2023-09-01 | JOCHOA | U135005 | 2023-07-18 | 2023-12-29 |  |  | JOCHOA | 2023-09-01 | 2023-08-22 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.7167 | 6 | 2402.88 | 1493.73 | 827.05 | 82.1 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212017900 |  | 100340167 |  | 6724212E |  |  |  | 565 | EX | GRADE 1 REPLACE S/L | 2621P | COURTLAND | 1876 COURTLAND DR | 067 | LEX | 2023-09-05 | U135005 | U129939 | 2023-08-30 | 2023-08-30 | 2023-08-30 |  | HSTANFI | 2023-09-01 | 2023-08-31 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.2167 | 3 | 1194.27 | 798.34 | 350.23 | 45.7 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212708300 |  | 100340154 |  | 6724212E |  |  |  | 565 | EX | SERVICE LINE REPAIR | 2621P | HI CREST | 715 HI CREST DR A | 067 | LEX | 2023-09-05 | U930915 | U134902 | 2023-09-01 | 2023-09-01 | 2023-09-01 |  | LSTONE | 2023-09-01 | 2023-09-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 15.4833 | 2 | 2365.99 | 1801.09 | 466.19 | 98.71 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11915923100 |  | 100249128 |  | T-1601-55 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | OLD SUNSHINE | 81 OLD SUNSHINE RD | 089 | S S | 2023-09-05 | RECUMP | U124964 | 2011-07-14 | 2023-09-05 | 2023-12-31 |  | RECUMP | 2023-09-05 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.0333 | 2 | 1247.78 | 197.29 | 0 | 167.84 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883168800 |  | 100255177 |  | 7344172T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | LINE P | LINE P | 071 | WAT | 2023-09-05 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN HOWARD | 2023-09-05 | 2023-08-29 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 12.8667 | 2 | 904.1 | 856.16 | 0 | 47.94 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883273100 |  | 100249132 |  | 7328284F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | HAPPY CORNER | 4748 HAPPY CORNER DR | 089 | S S | 2023-09-05 | RECUMP | U120245 | 2021-01-30 | 2023-09-05 | 2023-12-31 |  | RECUMP | 2023-09-05 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.5833 | 1 | 1072.45 | 102.57 | 0 | 87.23 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959273900 |  | 100261037 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | MCGUIRE | 300 MCGUIRE ST | 019 | ASH | 2023-09-05 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-09-05 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1990.64 | 0 | 0 | 0 | 1990.64 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960854300 |  | 100250193 |  | 7356248D | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | FLEMING | 201 FLEMING CT 5 | 019 | CAT | 2023-09-05 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-09-05 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2693.75 | 0 | 0 | 0 | 2693.75 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026262000 |  |  |  | 6712236G | 2294088 | U134275 |  | 909 | VO | UPGRADE RTU & ADD SOLAR BACKUP | 2600E | DELAPLANE | DELAPLANE RD | 209 | GEO | 2023-09-26 |  | U134275 | 2023-02-17 | 2023-12-28 | 2023-12-31 |  | CWEMPE | 2023-09-05 | 2023-08-31 |  | F | [11 empty] | 23170126500 | 100 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026262100 |  |  |  | 6712236G | 2294088 | U134275 |  | 910 | VO | UPGRADE RTU & ADD SOLAR BACKUP | 2600E | DELAPLANE | DELAPLANE RD | 209 | GEO | 2023-09-26 |  | U134275 | 2023-02-17 | 2023-12-29 | 2023-12-31 |  | CWEMPE | 2023-09-05 |  |  | F | [11 empty] | 23170126500 | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026286300 |  |  |  | 6716212L | 2399149 | U461383 |  | 562 | EX | RETIRE 306' OF 3"BSLP MAIN | 2621P | CHRYSALIS | CHRYSALIS CT | 067 | LEX | 2023-11-17 | U136251 | U461383 | 2023-08-01 | 2023-09-15 | 2023-09-15 | 2023-09-05 | RJCRAWF | 2023-09-05 | 2023-08-18 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP2863 | AMRCB |  | 100 | 056232230262863 | 67.9167 | 0 | 4872.41 | 3754.31 | 139.58 | 214.67 | 763.85 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026286800 |  | 500514179 |  | 6720208M | 2399223 | U461383 |  | 555 | EX | INSTALL 100' OF 2"PMIP MAIN | 2621P | MONTAVESTA | 3422 MONTAVESTA RD | 067 | LEX | 2024-01-26 | U136251 | U461383 | 2023-08-03 | 2023-11-16 | 2023-11-17 | 2023-09-05 | RJCRAWF | 2023-09-05 | 2023-08-24 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2868 |  |  | 100 | 055532230262868 | 49.05 | 1212 | 13755.57 | 2747.4 | 672.83 | 797.59 | 6349 | 0 | 61.54 | 3127.21 | 101
KY | KY - WEST | 2621 | 23166675700 |  | 100322664 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 729 PROVIDENCE RD | 067 | LEX | 2023-09-06 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-09-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2136.11 | 0 | 0 | 0 | 2136.11 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23187483600 |  | 100458932 |  | 6720208P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332784 | 2621P | STONEHEDGE | 421 STONEHEDGE PL | 067 | LEX | 2023-09-06 | U135005 | U125208 | 2023-05-11 | 2023-11-10 | 2025-05-31 |  | ATWILLI | 2023-09-05 | 2023-06-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 30.4667 | 10 | 3344.12 | 1966.19 | 208.85 | 1169.08 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23205455700 |  | 100320561 |  | 6716212L | 2399149 |  |  | 566 | EX | RETIRE S/L W/23-0262863-00 | 2621P | CHRYSALIS | 120 CHRYSALIS CT | 067 | LEX | 2023-09-05 | RJCRAWF | U461383 | 2023-08-01 | 2023-09-15 | 2023-09-15 |  | RJCRAWF | 2023-09-05 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 2.6333 | 2 | 162.41 | 153.98 | 0 | 8.43 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212891900 |  | 100340505 |  | 6724212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | AUBURN | 1608 AUBURN DR | 067 | LEX | 2023-09-06 | U135005 | U137585 | 2023-09-05 | 2023-09-05 | 2023-09-05 |  | LSTANFI | 2023-09-05 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 7.0333 | 4 | 995.82 | 481.63 | 487.81 | 26.38 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 10841471000 |  | 100453080 |  | 1 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PISGAH | 2485 PISGAH PK FG25 | 239 | VER | 2023-09-06 | U128410 | RPOLLY | 2010-05-20 | 2022-07-01 | 2023-12-31 |  | CDESPAIN | 2023-09-06 | 2023-07-03 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 32.75 | 6 | 2208.39 | 2087.83 | 0 | 120.56 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 11899956800 |  | 100460752 |  | 6696220C |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | OLD FRANKFORT | 3530 OLD FRANKFORT PK | 239 | MID | 2023-09-12 | U135005 | U906631 | 2011-04-06 | 2022-07-01 | 2023-12-31 |  | CDESPAIN | 2023-09-06 | 2023-06-13 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 20.15 | 0 | 1422.17 | 1346.55 | 0 | 75.62 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883192900 |  | 100267676 |  | 7324284A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | STATE RT 1134 | STATE RT 1134 | 089 | S S | 2023-09-06 | RECUMP | U120245 | 2021-01-30 | 2023-08-29 |  |  | RECUMP | 2023-09-06 | 2023-07-12 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.5167 | 2 | 1264.31 | 229.46 | 0 | 152.2 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883213500 |  | 100260493 |  | 7344148T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY ROUTE 122 | 6004 KY ROUTE 122 | 071 | DRI | 2023-09-06 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN HOWARD | 2023-09-06 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 6.6167 | 1 | 490.74 | 465.22 | 0 | 25.52 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883220300 |  | 500349018 |  | 7324284A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | STATE RT 1134 | STATE RT 1134 | 089 | S S | 2023-09-06 | RECUMP | U120245 | 2021-01-30 | 2023-08-29 |  |  | RECUMP | 2023-09-06 | 2022-11-17 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 7.0833 | 4 | 1657.84 | 405.99 | 0 | 369.2 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883264300 |  | 100259255 |  | 7344140T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | P2 | P2 | 071 | HI | 2023-09-06 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BRIAN PREECE | 2023-09-06 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959265700 |  | 100261035 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | BLACKBURN | 316 BLACKBURN AV | 019 | ASH | 2023-09-06 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-09-06 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2608.58 | 0 | 0 | 0 | 2608.58 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960854400 |  | 100250194 |  | 7356248D | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | FLEMING | 500 FLEMING CT | 019 | CAT | 2023-09-07 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-09-06 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3436.55 | 0 | 0 | 0 | 3436.55 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026212500 |  |  |  | 6712208K | 2288144 | U134275 |  | 583 | EX | REPLACE VALVES AT R-1084 | 2600M | HARRODSBURG | 3090 HARRODSBURG RD | 067 | LEX | 2023-09-19 | U123258 | U938437 | 2022-07-19 | 2023-09-27 | 2023-09-30 | 2023-09-06 | CHRIS COX | 2023-09-06 | 2023-09-05 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00583 | 3200583 |  |  | WP2125 |  |  | 100 | 058332220262125 | 48.0333 | 32 | 9402.89 | 3420.4 | 1238.85 | 1521.22 | 773.5 | 0 | 22.29 | 2426.63
KY | KY - WEST | 2621 | 22026212600 |  |  |  | 6712208K | 2288144 | U938437 |  | 584 | EX | RETIRE STATION VALVES R-1084 | 2600M | HARRODSBURG | 3090 HARRODSBURG RD | 067 | LEX | 2023-09-18 | U123258 | U938437 | 2022-07-19 | 2023-12-29 | 2023-12-31 | 2023-09-06 | CCOX | 2023-09-06 | 2023-09-06 |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00584 | 3200584 |  |  | WP2126 |  |  | 100 | 058432220262126 | 10.8667 | 0 | 1269.98 | 777 | 0 | 492.98 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22979019200 |  | 100249091 |  | 7328284B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KZ RATLIFF | 947 KZ RATLIFF LN | 089 | S S | 2023-09-12 | U135005 | U128070 | 2022-02-17 | 2023-09-05 | 2023-12-31 |  | RECUMP | 2023-09-06 | 2023-09-05 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.8167 | 3 | 1350.51 | 252.8 | 0 | 215.06 | 882.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165285200 |  | 100336848 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | LIMESTONE | 468 N LIMESTONE ST 1 | 067 | LEX | 2023-09-06 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-09-06 | 2023-08-31 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.2167 | 3 | 11932.3 | 1481.1 | 0 | 82.15 | 10369.05 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166674400 |  | 100322692 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 704 PROVIDENCE RD | 067 | LEX | 2023-09-06 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-09-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2807.12 | 0 | 0 | 0 | 2807.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23193799800 |  | 100346814 |  | 6696212O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER | 2623D | HILLCREST | 382 HILLCREST DR | 239 | VER | 2023-09-06 | U128410 | AOC SYST | 2023-06-08 | 2023-07-07 | 2023-08-07 |  | CDESPAIN | 2023-09-06 | 2023-08-30 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 18.0333 | 2 | 1300.03 | 1229.48 | 0 | 70.55 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23204426100 |  | 100464864 |  | 6716200H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D310395 | 2621P | EDGEWOOD | 837 EDGEWOOD DR | 067 | LEX | 2024-01-26 | U461383 | U135005 | 2023-07-27 | 2023-08-31 | 2023-09-18 |  | JOSHUA COX | 2023-09-06 | 2023-09-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.95 | 4 | 1353.06 | 1225.81 | 59.66 | 67.59 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23205456000 |  | 100320559 |  | 6716212L | 2399149 |  |  | 566 | EX | RETIRE S/L W/23-0262863-00 | 2621P | CHRYSALIS | 116 CHRYSALIS CT | 067 | LEX | 2023-09-06 | RJCRAWF | U461383 | 2023-08-01 | 2023-09-15 | 2023-09-15 |  | RJCRAWF | 2023-09-06 | 2023-08-17 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 0.75 | 2 | 53.41 | 50.65 | 0 | 2.76 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23211473500 |  | 100338703 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL - INACTIVITY | 2621P | BELTLINE | 144 BELTLINE AV | 067 | LEX | 2023-09-06 | U930915 | U135005 | 2023-08-29 | 2023-12-29 |  |  | TROE | 2023-09-06 | 2023-09-05 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.6167 | 4 | 1253.64 | 572.14 | 2.11 | 31.39 | 648 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212880900 |  | 100340198 |  | 6720212H |  |  |  | 565 | EX | RPLC SL- D309315 24HR GAS OFF | 2621P | SHILOH | 1834 SHILOH CT | 067 | LEX | 2023-09-07 | U135005 | U135005 | 2023-09-05 | 2023-09-05 | 2023-09-05 |  | LSTANFI | 2023-09-06 | 2023-09-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.1 | 4 | 1735.01 | 972.76 | 616.62 | 145.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212903700 |  | 100339687 |  | 6724212E |  |  |  | 565 | EX | REPLACE SL | 2621P | AUBURN | 1505 AUBURN CT | 067 | LEX | 2023-09-07 | U135005 | U137585 | 2023-09-05 | 2023-09-05 | 2023-09-05 |  | RJCRAWF | 2023-09-06 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.4 | 4 | 786.12 | 745.25 | 0 | 40.87 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23213143600 |  | 100255947 |  | 7356256E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HACKWORTH | 2501 HACKWORTH ST | 019 | ASH | 2023-09-06 | BROBERT | U129939 | 2023-09-06 | 2023-09-05 | 2023-09-05 |  | BROBERT | 2023-09-06 | 2023-09-05 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 11.05 | 4 | 1384.45 | 763.79 | 175.6 | 445.06 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23213197900 |  | 100340647 |  | 6724212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SARASOTA | 1720 SARASOTA CT | 067 | LEX | 2023-09-07 | U135005 | U129939 | 2023-09-06 | 2023-09-06 | 2023-09-06 |  | LSTANFI | 2023-09-06 | 2023-09-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 9.7167 | 4 | 1149.97 | 718.94 | 325.34 | 105.69 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959265100 |  | 100261163 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | 6TH | 2312 6TH ST | 019 | ASH | 2023-09-07 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-09-07 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3047.74 | 0 | 0 | 0 | 3047.74 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960855200 |  | 100250214 |  | 7356248D | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | ICE CREEK | 8500 ICE CREEK RD | 019 | CAT | 2023-09-07 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-09-07 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2144.23 | 0 | 0 | 0 | 2144.23 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960883700 |  | 500372745 |  | 7356248D | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | ICE CREEK | 8429 ICE CREEK RD TRL1 | 019 | CAT | 2023-09-07 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-09-07 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 4500 | 0 | 0 | 0 | 4500 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026242301 |  |  |  | 6712208K | 2288144 | U134275 |  | 559 | EX | INSTALL 8"POLY VALVE W/10"SPH | 2600B | HARRODSBURG RD | 3090 HARRODSBURG RD | 067 | LEX | 2023-09-11 | U124014 | U134275 | 2023-09-07 | 2023-10-02 | 2023-10-15 | 2023-09-05 | WILL FULKS | 2023-09-07 | 2023-08-21 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP2423 |  |  | 100 | 055932220262423 | 98.2667 | 156 | 84380.42 | 6701.92 | 18312.24 | 2478.49 | 39651.93 | 0 | 352.03 | 16883.81 | 12
KY | KY - EAST | 2631 | 22129013300 |  | 100250767 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | STATE RT 2 | STATE RT 2 | 089 | GRE | 2023-09-07 | RECUMP | U130722 | 2022-09-05 | 2022-12-30 |  |  | RECUMP | 2023-09-07 | 2023-07-13 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 8.2667 | 5 | 2440.19 | 516 | 35.11 | 305.51 | 1583.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026280100 |  |  |  | 6712208K | 2288144 | U134275 |  | 560 | EX | RETIRE 10' OF 10"CSMP MAIN | 2600B | HARRODSBURG | 3090 HARRODSBURG RD | 067 | LEX | 2023-09-11 | U124014 | U461383 | 2023-06-22 | 2023-12-29 | 2023-12-31 | 2023-09-05 | WILL FULKS | 2023-09-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00560 | 3200560 |  |  | WP2801 |  |  | 100 | 056032230262801 |  | 0 | 273.6 | 0 | 0 | 0 | 273.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026292600 |  |  |  | 6716212P | 2291708 | U461383 |  | 575 | EX | DOCUMENT 20'EASEMENT FROM UK | 2600E | COLUMBIA | COLUMBIA AV | 067 | LEX | 2023-11-13 | U128132 | U461383 | 2023-09-07 | 2023-09-29 | 2023-10-01 | 2023-09-07 | CHRIS DAVIS | 2023-09-07 |  |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00575 | 3200575 |  |  | WP2926 |  |  | 100 | 057532230262926 |  | 1 | 34094.48 | 0 | 0 | 0 | 34019.06 | 0 | 75.42 | 0
KY | KY - WEST | 2621 | 23166677600 |  | 100322663 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 733 PROVIDENCE RD | 067 | LEX | 2023-09-07 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-09-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1332.28 | 0 | 0 | 0 | 1332.28 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23193492700 |  | 100302739 |  | 6712212O | 2395762 |  |  | 565 | EX | RPLC SL/23026263000 | 2600B | PARKERS MILL | 1867 PARKERS MILL RD | 067 | LEX | 2023-09-07 | U126603 | U131066 | 2023-06-07 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-09-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 9963.26 | 0 | 0 | 0 | 9963.26 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23206209800 |  | 100271707 |  | 6684228K | 1855043 |  |  | 566 | EX | ABANDON SL - SOII/INSIDE | 2621P | 2ND | 310 E 2ND ST | 073 | FRA | 2023-09-07 | EFGOINS | U131897 | 2023-08-03 | 2023-09-07 | 2023-12-31 |  | EFGOINS | 2023-09-07 | 2023-09-05 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 17.7167 | 4 | 1244.72 | 1179.99 | 0 | 64.73 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23206514200 |  | 100339261 |  | 6724212F |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | CHARLESTON | 1801 CHARLESTON DR | 067 | LEX | 2023-09-07 | RSTRONG | U135005 | 2023-08-04 | 2023-12-29 |  |  | RSTRONG | 2023-09-07 | 2023-08-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25.05 | 6 | 2158.85 | 1333.89 | 547.69 | 277.27 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210314100 |  | 100269853 |  | 6732252P | 2293704 |  |  | 565 | EX | GR 2+ LEAK ON SERVICE D309493 | 2600B | BROADWAY | 408 BROADWAY AV | 097 | CYN | 2023-09-12 | JTOY | U125763 | 2023-08-23 | 2023-08-25 | 2023-09-14 |  | NRICHIE | 2023-09-07 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 24 | 3 | 4113.13 | 1711.97 | 331.64 | 584.06 | 1485.46 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23212657100 |  | 100418045 |  | 7348252C |  |  |  | 565 | EX | INSTALL SPLIT SERVICE | 2621P | ALEXANDER | 912 W ALEXANDER DR | 019 | ASH | 2023-09-08 | U135005 | U135005 | 2023-09-01 | 2023-11-06 | 2023-11-06 |  | ABHATFIE | 2023-09-07 | 2023-09-07 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 42.5333 | 5 | 3683.62 | 3077.63 | 0 | 605.99 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23212665300 |  | 100418046 |  | 7348252C |  |  |  | 565 | EX | INSTALL SPLIT SERVICE | 2621P | ALEXANDER | 906 W ALEXANDER DR | 019 | ASH | 2023-09-07 | ABHATFIE | U135005 | 2023-09-01 | 2023-11-06 | 2023-11-06 |  | ABHATFIE | 2023-09-07 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 0.71667 | 1 | 56.46 | 53.52 | 0 | 2.94 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212671400 |  | 100323009 |  | 6716208L |  |  |  | 565 | EX | MOVE METER OUTSIDE | 2621P | BEECHMONT | 600 BEECHMONT RD | 067 | LEX | 2023-09-07 | U128336 | U135005 | 2023-09-01 | 2023-11-01 | 2023-11-01 |  | JOSHUA COX | 2023-09-07 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16 | 2 | 1888.16 | 1273.15 | 545.19 | 69.82 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23212848500 |  | 100255968 |  | 7356256E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D259807 | 2621P | HACKWORTH | 2817 HACKWORTH ST | 019 | ASH | 2023-09-07 | MCOLLET | U135005 | 2023-09-05 | 2023-09-08 | 2023-09-26 |  | MCOLLET | 2023-09-07 | 2023-09-06 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 17.3667 | 3 | 3036.65 | 1421.58 | 385.1 | 1229.97 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212903400 |  | 100340500 |  | 6724212E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | ATLANTA | 1601 ATLANTA DR | 067 | LEX | 2023-09-08 | U930915 | U131366 | 2023-09-05 | 2023-09-05 | 2023-09-05 |  | HMCKUNE | 2023-09-07 | 2023-09-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 30.2333 | 5 | 2399.01 | 1723.71 | 580.81 | 94.49 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23213187400 |  | 100340164 |  | 6724212E |  |  |  | 565 | EX | RPLC SL 24HR GAS OFF GR1 | 2621P | COURTLAND | 1834 COURTLAND DR | 067 | LEX | 2023-09-07 | LSTONE | U135005 | 2023-09-06 | 2023-09-06 | 2023-09-06 |  | LSTONE | 2023-09-07 | 2023-09-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.7667 | 2 | 1402.75 | 1051.55 | 293.57 | 57.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23213349300 |  | 100340501 |  | 6724212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | AUBURN | 1600 AUBURN DR | 067 | LEX | 2023-09-08 | U930915 | U129939 | 2023-09-07 | 2023-09-05 | 2023-09-05 |  | HMCKUNE | 2023-09-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26210022 | 14.0167 | 4 | 1560.32 | 1282.25 | 207.74 | 70.33 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11900942500 |  | 100249120 |  | 7328284G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | STATE RT 7 | 1312 STATE RT 7 | 089 | S S | 2023-09-08 | RECUMP | U906631 | 2011-04-13 | 2023-09-07 | 2023-12-31 |  | RECUMP | 2023-09-08 | 2023-09-07 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.7833 | 3 | 2274.79 | 248.22 | 0 | 209.36 | 1817.21 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883313800 |  | 100251633 |  | 7336272F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | SMITH BRANCH | SMITH BRANCH RD | 089 | GRE | 2023-09-08 | RECUMP | U120245 | 2021-01-30 | 2023-09-08 |  |  | RECUMP | 2023-09-08 | 2023-07-11 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 6.6833 | 2 | 1557.43 | 433.13 | 0 | 241.65 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959273200 |  | 100261162 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | 6TH | 2300 6TH ST | 019 | ASH | 2023-09-08 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-09-08 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1876.06 | 0 | 0 | 0 | 1876.06 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960854900 |  | 100250222 |  | 7360248A | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | ICE CREEK | 8420 ICE CREEK RD | 019 | CAT | 2023-09-11 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-09-08 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3339.67 | 0 | 0 | 0 | 3339.67 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026168600 |  |  |  | 6712232N | 2286608 | U132703 |  | 557 | EX | INSTALL 13,800'-2"PMMP | 2600B | PAYNE | 204 PAYNE AV | 209 | GEO | 2023-11-14 | U136251 | U132703 | 2022-02-16 | 2023-03-31 | 2023-12-31 | 2023-08-08 | WGRAVES | 2023-09-08 | 2023-01-03 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP1686 | AMRCB |  | 100 | 055732220261686 | 1250.8833 | 2139582 | 1531903.82 | 86418.18 | 43309.82 | 39474.25 | 1124451.56 | 0 | 26224.32 | 212025.69 | 11202
KY | KY - WEST | 2623 | 22026168700 |  |  |  | 6712232N | 2286608 | U132703 |  | 558 | EX | RETIRE 12,327'-BSLP,CSLP,PLP | 2600E | PAYNE | 204 PAYNE | 209 | GEO | 2023-09-25 | U136251 | U132703 | 2022-02-16 | 2023-10-31 | 2023-12-31 | 2023-08-08 | WGRAVES | 2023-09-08 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP1687 | AMRCB |  | 100 | 055832220261687 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026183100 |  |  |  | 6716216M | 1968251 | U134275 |  | 561 | EX | INSTALL 3090' OF 2-4" PMMP | 2600B | LEESTOWN | LEESTOWN RD | 067 | LEX | 2023-09-20 | U128132 | U134275 | 2022-04-25 | 2023-07-03 | 2023-10-30 | 2023-04-28 | JAMIE LYNN | 2023-09-08 | 2023-04-17 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP1831 |  |  | 100 | 056132220261831 | 617.8333 | 254640 | 609662.9 | 39622.95 | 20497.68 | 18469.68 | 442049.08 | 0 | 366.82 | 88656.69 | 3183
KY | KY - WEST | 2621 | 22026183200 |  |  |  | 6716216M | 1968251 | U134275 |  | 562 | EX | RETIRE 3765' OF 2-4" CS & PMMP | 2600B | LEESTOWN | LEESTOWN RD | 067 | LEX | 2023-09-18 | U128132 | U134275 | 2022-04-25 | 2023-12-29 | 2023-12-31 | 2023-09-07 | JAMIE LYNN | 2023-09-08 | 2023-06-19 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP1832 |  |  | 100 | 056232220261832 | 4 | 0 | 273.03 | 258.18 | 0 | 14.85 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129055000 |  | 500455841 |  | 6684224E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | US 127 | 1128 US 127 SO B | 073 | FRA | 2023-09-08 | EFGOINS | U130722 | 2022-09-05 | 2022-12-30 |  |  | EFGOINS | 2023-09-08 | 2023-09-08 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 16.6 | 3 | 1042.26 | 988.05 | 0 | 54.21 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23026291200 |  |  |  | 7364188A | 2399884 | U122858 |  | 557 | EX | EMER - INSTALL 8'-3" PMIP | 2621P | OLD MIDDLE FORK | 153 OLD MIDDLE FORK RD | 159 | INE | 2023-10-11 | U128132 | U122858 | 2023-09-01 | 2023-08-30 | 2023-08-31 | 2023-09-01 | JCKIRK | 2023-09-08 |  |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00557 | 3200557 |  |  | WP2912 | AMRCB |  | 100 | 055732230262912 | 0.083333 | 9 | 51065.27 | 15937.31 | 7296.71 | 915.29 | 13515.86 | 0 | 68.29 | 13331.81 | 9
KY | KY - EAST | 2633 | 23026291300 |  |  |  | 7364188A | 2399884 | U122858 |  | 558 | EX | EMER - RETIRE 7'3" BS&P | 2621P | OLD MIDDLE FORK | 153 OLD MIDDLE FORK RD | 159 | INE | 2023-09-22 | U128132 | U122858 | 2023-09-01 | 2023-08-31 | 2023-08-31 | 2023-09-01 | JCKIRK | 2023-09-08 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00558 | 3200558 |  |  | WP2913 | AMRCB |  | 100 | 055832230262913 | 5.2833 | 0 | 392.93 | 372.51 | 0 | 20.42 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026291700 |  |  |  | 7352252C | 2399908 | U122858 |  | 557 | EX | EMER - INSTALL 3'-4" PMIP | 2621P | SKYLINE | 5332 SKYLINE DR | 019 | ASH | 2023-12-26 | U128132 | U122858 | 2023-09-05 | 2024-05-30 |  | 2023-08-31 | MCOLLET | 2023-09-08 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP2917 |  |  | 100 | 055732230262917 | 5.25 | 6 | 2433.5 | 382.25 | 822.93 | 598.9 | 0 | 0 | 0 | 629.42 | 3
KY | KY - EAST | 2631 | 23026291800 |  |  |  | 7352252C | 2399908 | U122858 |  | 558 | EX | EMER - RETIRE 3'-4" PIP | 2621P | SKYLINE | 5332 SKYLINE DR | 019 | ASH | 2023-09-12 | U128132 | U122858 | 2023-09-05 | 2024-05-31 |  | 2023-08-31 | MCOLLET | 2023-09-08 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP2918 |  |  | 100 | 055832230262918 | 5.0667 | 0 | 685.77 | 366.29 | 0 | 319.48 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166675900 |  | 100322700 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 736 PROVIDENCE RD | 067 | LEX | 2023-09-11 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-09-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2519.73 | 0 | 0 | 0 | 2519.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23171719400 |  | 500687623 |  | 6716212B | 1968251 |  |  | 565 | EX | RPLC SL/22026183100 | 2600B | LEESTOWN | 1580 LEESTOWN RD | 067 | LEX | 2023-09-08 | U126309 | U125763 | 2023-03-03 | 2023-12-29 |  |  | JAMIE LYNN | 2023-09-08 | 2023-08-10 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 17.5833 | 4 | 7606.55 | 1206.56 | 0 | 207.05 | 6192.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23201812800 |  | 100404448 |  | 6716204D |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | CAHABA | 832 CAHABA RD | 067 | LEX | 2023-09-08 | ABLAKE | U135005 | 2023-07-18 | 2023-12-29 |  |  | ABLAKE | 2023-09-08 | 2023-08-22 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 31.7167 | 6 | 2905.06 | 2207.08 | 576.87 | 121.11 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23210299400 |  | 100328492 |  | 6720208F | 2398976 |  |  | 565 | EX | SERVICE LINE/METER UPGR *HOLD* | 2621P | CLINTON | 400 CLINTON RD | 067 | LEX | 2023-09-08 | SSHIMFE | U135005 | 2023-08-23 | 2023-11-22 | 2023-11-23 |  | SSHIMFE | 2023-09-08 | 2023-09-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 33.8 | 7 | 5038.3 | 2322.28 | 536.88 | 173.3 | 2005.84 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23213398400 |  | 100256114 |  | 7356256F |  |  |  | 565 | EX | GRADE 1 REPLACE S/L | 2621P | LYNNWOOD | 2634 LYNNWOOD AV | 019 | ASH | 2023-09-11 | U135005 | U129939 | 2023-09-07 | 2023-09-07 | 2023-09-07 |  | BROBERT | 2023-09-08 | 2023-09-07 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 8.0167 | 3 | 1562.19 | 488.94 | 743.76 | 329.49 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23213613800 |  | 100340499 |  | 6724212E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | ATLANTA | 1603 ATLANTA DR | 067 | LEX | 2023-09-08 | HMCKUNE | U134852 | 2023-09-08 | 2023-09-08 |  |  | HMCKUNE | 2023-09-08 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.4667 | 2 | 584.76 | 554.38 | 0 | 30.38 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23213643200 |  | 100347425 |  | 6744208L |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | SPRING | 110 SPRING ST | 049 | WIN | 2023-09-11 | U135005 | U134852 | 2023-09-08 | 2023-09-08 | 2023-09-08 |  | DENNING | 2023-09-08 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 11.2 | 2 | 1180.28 | 845.68 | 288.24 | 46.36 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23213677600 |  | 100306388 |  | 6716212M |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CELIA | 825 CELIA LN | 067 | LEX | 2023-09-08 | KKINDER | U134852 | 2023-09-08 | 2023-09-08 | 2023-09-08 |  | KKINDER | 2023-09-08 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 17.3833 | 3 | 1678.72 | 1064.64 | 555.7 | 58.38 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23213684300 |  | 100346752 |  | 6696212L |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MAIN | 329 S MAIN ST | 239 | VER | 2023-09-11 | UIPBOT24 | U134852 | 2023-09-08 | 2023-08-22 | 2025-02-28 |  | MCRAIG | 2023-09-08 | 2023-08-08 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 | 8.8167 | 8 | 2867.27 | 1932.55 | 416.22 | 518.5 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 09807811000 |  | 100265808 |  | 7348252D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | SUMMITT | 822 SUMMITT RD L8 | 019 | ASH | 2023-09-11 | RECUMP | RPOLLY | 2009-10-14 | 2023-08-31 | 2023-12-31 |  | RECUMP | 2023-09-11 | 2023-08-31 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 8.65 | 3 | 2716.22 | 551.53 | 35.11 | 466.49 | 1663.09 | 0 | 0 | 0
KY | KY - EAST | 2631 | 12949790900 |  | 100424797 |  | 7348264F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | US ROUTE 23 | US ROUTE 23 | 089 | RAC | 2023-09-11 | RECUMP | U125208 | 2012-01-16 | 2023-08-31 | 2023-12-31 |  | RECUMP | 2023-09-11 | 2023-08-31 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.0167 | 3 | 1523.31 | 307.29 | 63.69 | 269.68 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959264700 |  | 100261150 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | 6TH | 2216 6TH ST | 019 | ASH | 2023-09-11 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-09-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1933.35 | 0 | 0 | 0 | 1933.35 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960855000 |  | 100250215 |  | 7356248H | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | ICE CREEK | 8435 ICE CREEK RD | 019 | CAT | 2023-09-12 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-09-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2989.7 | 0 | 0 | 0 | 2989.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129061100 |  | 100355719 |  | 7260280N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | BUCKNER | 507 BUCKNER ST | 161 | MAY | 2023-09-11 | SDADAMS | U130722 | 2022-09-05 | 2022-12-30 |  |  | SDADAMS | 2023-09-11 | 2023-09-05 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 14.4333 | 4 | 1049.92 | 993.32 | 2.11 | 54.49 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026267600 |  | 501344891 |  | 6744204D | 2396103 | U128885 |  | 555 | EX | INSTALL 110'-4"PMLP | 2600B | WHIRLAWAY | 103 WHIRLAWAY DR | 049 | WIN | 2023-09-13 | U128132 | U128885 | 2023-03-17 | 2023-09-01 | 2023-09-15 | 2023-08-31 | ED FOX | 2023-09-11 | 2023-08-25 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP2676 |  |  | 100 | 055532230262676 | 41.25 | 500 | 32525.16 | 2469.03 | 1182.18 | 503.18 | 20016 | 0 | 10.14 | 8344.63 | 100
KY | KY - WEST | 2621 | 23166676200 |  | 100322661 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 741 PROVIDENCE RD | 067 | LEX | 2023-09-11 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-09-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2739.33 | 0 | 0 | 0 | 2739.33 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23196570500 |  | 100276671 |  | 6684228H | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | BLACKBURN | 623 BLACKBURN AV | 073 | FRA | 2023-09-11 | MCRAIG | AOC SYST | 2023-06-22 | 2023-12-21 | 2024-12-31 |  | MCRAIG | 2023-09-11 | 2023-07-21 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 25.7667 | 6 | 3364.35 | 1990.13 | 591.35 | 782.87 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23196570700 |  | 100276672 |  | 6684228H | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | BLACKBURN | 627 BLACKBURN AV | 073 | FRA | 2023-09-11 | MCRAIG | AOC SYST | 2023-06-22 | 2023-12-21 | 2024-12-31 |  | MCRAIG | 2023-09-11 | 2023-09-11 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 26.4333 | 4 | 2939.8 | 1645.88 | 614.56 | 679.36 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23203057000 |  | 100344223 |  | 7240212C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332856 | 2621P | QUEEN | 307 S QUEEN ST | 173 | MT | 2023-09-12 | U135005 | U135005 | 2023-07-24 | 2024-01-19 | 2025-07-31 |  | DENNING | 2023-09-11 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 16.3 | 3 | 2632.76 | 1206.02 | 469.62 | 66.12 | 891 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23209361900 |  | 100306522 |  | 6716212M |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | COLD HARBOR | 1728 COLD HARBOR DR | 067 | LEX | 2023-09-11 | KKINDER | U135005 | 2023-08-18 | 2023-11-17 | 2023-11-18 |  | KKINDER | 2023-09-11 | 2023-09-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.1333 | 2 | 1659.44 | 1046.36 | 555.7 | 57.38 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23213650400 |  | 100422424 |  | 6720208J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BRIDGEPORT | 2044 BRIDGEPORT DR | 067 | LEX | 2023-09-11 | LSTONE | U134852 | 2023-09-08 | 2023-09-08 | 2023-09-08 |  | LSTONE | 2023-09-11 | 2023-09-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 27.85 | 6 | 5141.1 | 2158.35 | 221.48 | 389.2 | 2372.07 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23213788800 |  | 100267260 |  | 7352260E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | AMHERST | 1160 AMHERST DR | 089 | ASH | 2023-09-11 | BROBERT | U134852 | 2023-09-10 | 2023-09-10 | 2023-09-10 |  | BROBERT | 2023-09-11 | 2023-09-10 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 13.8 | 4 | 1794.83 | 944.24 | 320.86 | 529.73 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23213795500 |  | 100414783 |  | 6704208E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | JUNIPER | 201 JUNIPER DR | 239 | VER | 2023-09-13 | U128410 | U129939 | 2023-09-11 | 2023-09-12 | 2023-09-30 |  | CDESPAIN | 2023-09-11 | 2023-09-11 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 20.2667 | 4 | 1714.08 | 1427.92 | 207.86 | 78.3 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23213994600 |  | 100459119 |  | 7240212C |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | QUEEN | 311 S QUEEN ST | 173 | MT | 2023-09-12 | U930915 | U129939 | 2023-09-11 | 2023-09-11 |  |  | DENNING | 2023-09-11 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.2 | 3 | 172.09 | 163.11 | 0 | 8.98 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883275400 |  | 100264621 |  | 7384168I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | TAYLOR FORK | 162 TAYLOR FORK RD | 195 | S W | 2023-09-12 | JAHOWARD | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JAHOWARD | 2023-09-12 | 2023-04-24 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 26.0833 | 4 | 2870.52 | 1835.36 | 0 | 100.6 | 934.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21884251000 |  | 100265564 |  | 7352252B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3# | 2621P | LITTLE GARNER | 822 W LITTLE GARNER RD | 019 | ASH | 2023-09-12 | RECUMP | U128293 | 2021-02-04 | 2023-09-12 | 2023-12-31 |  | RECUMP | 2023-09-12 | 2022-10-05 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.2333 | 4 | 4831.57 | 317.99 | 0 | 186.18 | 4327.4 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959265300 |  | 500723133 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | BARBER | 315 BARBER RD | 019 | ASH | 2023-09-12 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-09-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2547.92 | 0 | 0 | 0 | 2547.92 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960852700 |  | 100250179 |  | 7356248D | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | CANNONSBURG | 8473 CANNONSBURG PK | 019 | CAT | 2023-09-12 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-09-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2880.62 | 0 | 0 | 0 | 2880.62 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129011100 |  | 501235526 |  | 7352244J | 1853235 |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LONE OAK | 16205 LONE OAK DR LT | 019 | CAT | 2023-09-13 | U135005 | U130722 | 2022-09-05 | 2023-09-12 |  |  | RECUMP | 2023-09-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.8667 | 1 | 1472.49 | 315.54 | 0 | 274.3 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129128700 |  | 100264657 |  | 7384168F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | TAYLOR FORK | 277 TAYLOR FORK RD | 195 | TUR | 2023-09-12 | JAHOWARD | U125208 | 2022-09-06 | 2022-12-30 | 2023-12-31 |  | JAHOWARD | 2023-09-12 | 2023-04-24 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 6.1 | 3 | 2066.66 | 433.37 | 0 | 23.77 | 1609.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22138681100 |  | 100324704 |  | 6720204B | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | FOXTALE | 3276 FOXTALE CT | 067 | LEX | 2023-09-12 | JOCHOA | AOC SYST | 2022-10-12 | 2023-04-12 | 2023-12-31 |  | JOCHOA | 2023-09-12 | 2023-08-31 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 29.2667 | 7 | 2599.4 | 2067.75 | 418.27 | 113.38 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026263000 |  |  |  | 6712212K | 2395762 | U461383 |  | 557 | EX | INSTALL 5875' OF 2"/4"PMMP ENV | 2600B | STANDISH | 1228 STANDISH WY | 067 | LEX | 2023-09-26 | U128132 | U461383 | 2023-02-22 | 2023-06-02 | 2023-11-01 | 2023-09-05 | SHAWN DENNIS | 2023-09-12 | 2023-05-16 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2630 | AMRCB |  | 100 | 055732230262630 | 575.8667 | 458252 | 763454.52 | 38565.87 | 23969.42 | 9538.45 | 555386.1 | 0 | 9769.29 | 126225.39 | 6739
KY | KY - WEST | 2621 | 23026263100 |  |  |  | 6712212K | 2395762 | U461383 |  | 558 | EX | RETIRE 6090' OF 4"BSMP MAIN | 2600B | STANDISH | 1228 STANDISH WY | 067 | LEX | 2023-09-21 | U128132 | U461383 | 2023-02-22 | 2023-11-01 | 2023-11-01 | 2023-09-05 | SHAWN DENNIS | 2023-09-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2631 | AMRCB |  | 100 | 055832230262631 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026266200 |  | 501345244 |  | 6700224H | 2396045 | U126783 |  | 555 | EX | INSTALL 1100'-4" PHHP | 2600B | GEORGETOWN | 1050 GEORGETOWN RD BLDG C | 239 | MID | 2023-11-13 | U136251 | U126783 | 2023-03-13 | 2023-09-21 | 2023-09-30 | 2023-09-12 | DDAVIS | 2023-09-12 | 2023-08-21 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2662 |  |  | 100 | 055532230262662 | 121.5 | 16395 | 125731.21 | 8188.91 | 21871.96 | 2387.93 | 62895.59 | 0 | 964.79 | 29422.03 | 1093
KY | KY - WEST | 2621 | 23205914300 |  | 100308394 |  | 6716212N | 1855043 |  |  | 566 | EX | ABANDON SL - SOII/INSIDE | 2621P | GIBSON | 511 GIBSON AV | 067 | LEX | 2023-09-20 | U135005 | U131897 | 2023-08-02 | 2023-11-22 | 2023-11-22 |  | RSTRONG | 2023-09-12 | 2023-09-01 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 18.8167 | 5 | 1218.7 | 1010.35 | 37.51 | 170.84 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23206206700 |  | 100322421 |  | 6720208A | 1855043 |  |  | 566 | EX | ABANDON SL - SOII/INSIDE | 2621P | SUNSET | 800 SUNSET DR | 067 | LEX | 2023-09-13 | U135005 | U131897 | 2023-08-03 | 2023-12-29 | 2023-12-31 |  | RJCRAWF | 2023-09-12 | 2023-08-31 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.8167 | 3 | 790.57 | 368.56 | 118.2 | 20.31 | 283.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23213809100 |  | 100256058 |  | 7356256E |  |  |  | 565 | EX | GRADE 1 SERVICE REPLACE | 2621P | ELMWOOD | 1109 ELMWOOD AV | 019 | ASH | 2023-09-12 | BROBERT | U129939 | 2023-09-11 | 2023-09-11 | 2023-09-11 |  | BROBERT | 2023-09-12 | 2023-09-11 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 14.9 | 3 | 1764.05 | 886.39 | 308.2 | 569.46 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23213851300 |  | 100329604 |  | 6720208C |  |  |  | 565 | EX | GRADE 1 REPLACE S/L | 2621P | SAINT CHRISTOP | 2020 SAINT CHRISTOP DR | 067 | LEX | 2023-09-13 | U135005 | U129939 | 2023-09-11 | 2023-09-11 | 2023-09-11 |  | RSTRONG | 2023-09-12 | 2023-09-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.4667 | 4 | 1722.19 | 1009.68 | 447.11 | 265.4 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23213890400 |  | 100264444 |  | 7356260M |  |  |  | 565 | EX | 24HR GASOFF REPLACE SL D259601 | 2621P | BATH | 842 BATH AV | 019 | ASH | 2023-09-12 | JROGER1 | U135005 | 2023-09-11 | 2023-09-11 | 2023-09-11 |  | JROGER1 | 2023-09-12 | 2023-09-12 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 12.7 | 2 | 1631.09 | 826.53 | 351.75 | 452.81 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19702074600 |  | 100318393 |  | 6716204G |  |  |  | 565 | EX | REPL SL - MOVE MTR 7/10 08:30 | 2621P | LANSDOWNE | 3548 LANSDOWNE DR | 067 | LEX | 2023-09-13 | WISHII | U125208 | 2019-05-01 | 2020-06-29 |  |  | WISHII | 2023-09-13 | 2023-08-04 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.1167 | 7 | 1740.64 | 1010.04 | 162.85 | 567.75 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883094500 |  | 500148713 |  | 7352256B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | MAIN | 3023 MAIN ST W | 019 | ASH | 2023-09-14 | U135005 | U120245 | 2021-01-30 | 2023-09-13 | 2023-12-31 |  | RECUMP | 2023-09-13 | 2022-12-12 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 6.05 | 2 | 4034.54 | 396.73 | 0 | 336.56 | 3301.25 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959265500 |  | 100261160 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | BARBER | 324 BARBER RD | 019 | ASH | 2023-09-13 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-09-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2029.64 | 0 | 0 | 0 | 2029.64 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960883200 |  | 100250239 |  | 7360248A | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | 36TH | 425 36TH ST | 019 | CAT | 2023-09-13 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-09-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1911.69 | 0 | 0 | 0 | 1911.69 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129059900 |  | 500132378 |  | 7240280G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | KY 10 | 4394 KY 10 | 161 | GER | 2023-09-13 | SDADAMS | U130722 | 2022-09-05 | 2022-12-30 |  |  | SDADAMS | 2023-09-13 | 2023-09-12 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 9.5833 | 3 | 1086.08 | 691.83 | 48.64 | 345.61 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166675600 |  | 100322698 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 728 PROVIDENCE RD | 067 | LEX | 2023-09-21 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-09-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1673.06 | 0 | 0 | 0 | 1673.06 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168130600 |  | 100275094 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | MAIN | 403 W MAIN ST | 073 | FRA | 2023-09-14 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-09-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2283.67 | 0 | 0 | 0 | 2283.67 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168130700 |  | 100275095 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | MAIN | 407 W MAIN ST | 073 | FRA | 2023-09-14 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-09-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2303.27 | 0 | 0 | 0 | 2303.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23196303900 |  | 100321817 |  | 6716208D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | PARK | 518 PARK AV | 067 | LEX | 2023-09-13 | U930915 | U135005 | 2023-06-21 | 2023-12-20 | 2025-06-30 |  | RJCRAWF | 2023-09-13 | 2023-07-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.3667 | 5 | 1582.14 | 1119.06 | 401.38 | 61.7 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23199250500 |  | 100415348 |  | 6712204D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309473 | 2621P | FRASERDALE | 3465 FRASERDALE CT | 067 | LEX | 2023-09-13 | KKINDER | U135005 | 2023-07-06 | 2024-01-05 | 2025-07-31 |  | KKINDER | 2023-09-13 | 2023-08-31 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.1833 | 3 | 1238.25 | 928.79 | 258.36 | 51.1 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23201038800 |  | 100462145 |  | 6720208N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D412215 | 2621P | SHADYBROOK | 2004 SHADYBROOK LN | 067 | LEX | 2023-09-15 | U128336 | U135005 | 2023-07-14 | 2024-01-12 | 2025-07-31 |  | JOSHUA COX | 2023-09-13 | 2023-09-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.3333 | 6 | 1927.93 | 1451.66 | 396.73 | 79.54 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23206497800 |  | 100339297 |  | 6724212F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332975 | 2621P | NEW ORLEANS | 2058 NEW ORLEANS DR | 067 | LEX | 2023-09-13 | LSTONE | U135005 | 2023-08-04 | 2024-02-02 | 2025-08-31 |  | LSTONE | 2023-09-13 | 2023-08-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.55 | 6 | 1255.85 | 1126.8 | 67.27 | 61.78 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23212874200 |  | 100351526 |  | 6744208P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D096844 | 2621P | HICKMAN | 237 W HICKMAN ST | 049 | WIN | 2023-09-13 | NRICHIE | U135005 | 2023-09-05 | 2023-09-08 | 2023-09-26 |  | NRICHIE | 2023-09-13 | 2023-09-11 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 18.5 | 6 | 2037.51 | 1320.39 | 266.63 | 450.49 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23213447900 |  | 100275787 |  | 6684228C |  |  |  | 565 | EX | GR 2+ LK REPAIR | 2621P | PLEASANT HILL | 132 PLEASANT HILL DR | 073 | FRA | 2023-09-13 | MCRAIG | U138726 | 2023-09-07 | 2023-09-08 | 2023-09-28 |  | MCRAIG | 2023-09-13 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 12.4833 | 2 | 2138.22 | 1100.06 | 441.52 | 596.64 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23213651700 |  | 100294791 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997801 | 2600B | LIMESTONE | 441 N LIMESTONE ST 1 | 067 | LEX | 2023-09-13 | U126532 | U131066 | 2023-09-08 | 2023-12-29 |  |  | LESLIE SHARON | 2023-09-13 | 2023-09-11 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.4667 | 3 | 4425.87 | 971.31 | 0 | 53.21 | 3401.35 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23213651800 |  | 100294800 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997801 | 2600B | LIMESTONE | 441 N LIMESTONE ST 10 | 067 | LEX | 2023-09-13 | U126532 | U131066 | 2023-09-08 | 2023-12-29 |  |  | LESLIE SHARON | 2023-09-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4 | 1 | 3988.64 | 289.12 | 0 | 15.85 | 3683.67 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23213652000 |  | 100294801 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997801 | 2600B | LIMESTONE | 441 N LIMESTONE ST 11 | 067 | LEX | 2023-09-13 | U126532 | U131066 | 2023-09-08 | 2023-12-29 |  |  | LESLIE SHARON | 2023-09-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.5 | 1 | 5028.96 | 180.7 | 0 | 9.91 | 4838.35 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23213856100 |  | 100345275 |  | 6696212H |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | KILMER | 115 KILMER ST | 239 | VER | 2023-09-13 | U128410 | U135005 | 2023-09-11 | 2023-09-12 |  |  | CDESPAIN | 2023-09-13 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 15.8833 | 3 | 5149.59 | 1120.69 | 312.49 | 61.45 | 3654.96 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23213869400 |  | 100278715 |  | 6688232O |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | POWHATAN | 525 POWHATAN TL | 073 | FRA | 2023-09-14 | U135005 | U135005 | 2023-09-11 | 2023-09-13 |  |  | BSEXTON | 2023-09-13 | 2023-09-13 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 20 | 3 | 1896.4 | 1151.94 | 681.28 | 63.18 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959265400 |  | 100261151 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | BARBER | 323 BARBER RD | 019 | ASH | 2023-09-14 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-09-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1980.53 | 0 | 0 | 0 | 1980.53 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960851500 |  | 100250167 |  | 7360248A | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | 36TH | 424 36TH ST | 019 | CAT | 2023-09-14 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-09-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 7674.41 | 0 | 0 | 0 | 7674.41 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026205900 |  |  |  | 7240216M | 2286853 | U128885 |  | 584 | EX | RETIRE R-1682 | 2629M | ROGERS | ROGERS AV | 173 | MT | 2023-10-05 | U123258 | U128885 | 2022-06-17 | 2023-12-29 | 2023-12-31 | 2023-09-14 | JAMES PASLEY | 2023-09-14 |  |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00584 | 3200584 |  |  | WP2059 | AMRCB |  | 100 | 058432220262059 | 8 | 0 | 603.96 | 572.57 | 0 | 31.39 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129027800 |  | 100256255 |  | 7356256G | 1855043 |  |  | 566 | EX | ABANDON SL - SOII/LGCY | 2621P | CENTRAL | 2839< CENTRAL AV | 019 | ASH | 2023-09-14 | RECUMP | U130722 | 2022-09-05 | 2023-09-14 | 2023-12-31 |  | RECUMP | 2023-09-14 | 2022-09-21 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 14.55 | 10 | 3210.34 | 911.92 | 0 | 470.13 | 1828.29 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026274301 |  | 501348004 |  | 6716216F | 2397485 | U461383 |  | 555 | EX | INSTALL 3400' OF 2"PMMP MAIN | 2600B | CRAVAT PASS | CRAVAT PASS LT243 | 067 | LEX | 2023-09-22 | U124014 | U461383 | 2023-09-14 | 2023-07-26 | 2023-10-27 | 2023-09-14 | DEREK PAYTON | 2023-09-14 | 2023-08-28 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2743 |  |  | 100 | 055532230262743 | 103.05 | 40788 | 82979.94 | 6270.88 | 6956.63 | 808.36 | 48537.16 | 0 | 317.63 | 20089.28 | 3399
KY | KY - CENTRAL | 2629 | 23026297000 |  |  |  | 7240216N | 2286853 | U128885 |  | 559 | EX | INSTALL PCF'S LP | 2600B | HOLT | HOLT AV | 173 | MT | 2023-10-04 | U128132 | U128885 | 2023-10-02 | 2023-12-29 | 2023-12-31 | 2023-09-14 | LYN STAFFORD | 2023-09-14 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00559 | 3200559 |  |  | WP2970 | AMRCB |  | 100 | 055932230262970 |  | 0 | 2982.68 | 0 | 1925.8 | 0 | 0 | 0 | 0 | 1056.88
KY | KY - WEST | 2621 | 23165289100 |  | 100294834 |  | 6716212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | UPPER | 454 N UPPER ST | 067 | LEX | 2023-09-14 | U461443 | U125763 | 2023-02-07 | 2023-12-29 |  |  | WGRAVES | 2023-09-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.2 | 1 | 2725.99 | 281.9 | 0 | 62.82 | 2381.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166675100 |  | 100322667 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 717 PROVIDENCE RD | 067 | LEX | 2023-09-21 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-09-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4780.35 | 0 | 0 | 0 | 4780.35 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168130500 |  | 100275093 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | MAIN | 401 W MAIN ST | 073 | FRA | 2023-09-14 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-09-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2244.47 | 0 | 0 | 0 | 2244.47 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168131100 |  | 100275103 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | MAIN | 421 W MAIN ST | 073 | FRA | 2023-09-14 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-09-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2642.33 | 0 | 0 | 0 | 2642.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23203056300 |  | 100286756 |  | 6720212F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332547 | 2621P | AVON | 169 AVON AV | 067 | LEX | 2023-09-14 | TROE | U135005 | 2023-07-24 | 2024-01-19 | 2025-07-31 |  | TROE | 2023-09-14 | 2023-09-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.7333 | 4 | 2037.41 | 1627.34 | 320.84 | 89.23 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23203057600 |  | 100308035 |  | 6716212K |  |  |  | 565 | VO | REPLACE SERVICE LINE - D333738 | 2621P | PATTERSON | 522 PATTERSON ST | 067 | LEX | 2023-10-03 | RSTRONG | U135005 | 2023-07-24 | 2024-01-19 | 2025-07-31 |  | RSTRONG | 2023-09-14 | 2023-09-01 |  | A | [11 empty] | 23218742500 | 100 |  |  | 1 | 2482.45 | 2028.72 | 42.21 | 411.52 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23205883100 |  | 100250240 |  | 7360248A | 2180320 |  |  | 565 | EX | RPLC SL/21026130400 | 2600B | 36TH | 421 36TH ST | 019 | CAT | 2023-09-14 | U123965 | U125763 | 2023-08-02 | 2023-12-29 |  |  | CJH DEREK CRAGER | 2023-09-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 4636.55 | 0 | 0 | 0 | 4636.55 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23206486900 |  | 100326217 |  | 6704212L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D310351 | 2621P | WESTMORLAND | 2586 WESTMORLAND DR | 067 | LEX | 2023-09-14 | KKINDER | U135005 | 2023-08-04 | 2024-02-02 | 2025-08-31 |  | KKINDER | 2023-09-14 | 2023-09-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 26.5 | 3 | 2100.87 | 1598.21 | 415.02 | 87.64 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23206487300 |  | 100339218 |  | 6724212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332573 | 2621P | GAYLE | 1845 GAYLE CR | 067 | LEX | 2023-09-14 | WISHII | U135005 | 2023-08-04 | 2024-02-02 | 2025-08-31 |  | WISHII | 2023-09-14 | 2023-08-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.3333 | 3 | 900.38 | 575.81 | 0 | 324.57 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23206497500 |  | 100339302 |  | 6724212F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332574 | 2621P | NEW ORLEANS | 2057 NEW ORLEANS DR | 067 | LEX | 2023-09-15 | U123688 | U135005 | 2023-08-04 | 2024-02-02 | 2025-08-31 |  | LSTANFI | 2023-09-14 | 2023-08-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.2667 | 7 | 1761.4 | 1126.43 | 404.09 | 230.88 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212802100 |  | 100328825 |  | 6720208F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332613 | 2621P | BLAIRMORE | 1973 BLAIRMORE RD | 067 | LEX | 2023-09-14 | U128336 | U135005 | 2023-09-05 | 2023-09-05 | 2023-09-21 |  | JOSHUA COX | 2023-09-14 | 2023-09-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.25 | 5 | 2881.44 | 1643.44 | 621.39 | 90.11 | 526.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23213623600 |  | 100275806 |  | 6684228C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D308827 | 2621P | AUDUBON | 118 AUDUBON DR | 073 | FRA | 2023-09-14 | MCRAIG | U135005 | 2023-09-08 | 2023-09-08 | 2023-09-28 |  | MCRAIG | 2023-09-14 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 16.15 | 2 | 2572.86 | 1154.25 | 555.7 | 862.91 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23213819700 |  | 100255173 |  | 7344168G |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | LAKE | 290 LAKE RD | 071 | PRE | 2023-09-15 | U129900 | U133234 | 2023-09-11 | 2023-09-25 | 2023-10-11 |  | JOHN HOWARD | 2023-09-14 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 8 | 1 | 594.82 | 563.9 | 0 | 30.92 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23214467000 |  | 100330610 |  | 6732216O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BRIAR HILL | 5543 BRIAR HILL RD | 067 | LEX | 2023-09-15 | U123688 | U129939 | 2023-09-13 | 2023-09-13 | 2023-09-13 |  | LSTANFI | 2023-09-14 | 2023-09-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.0333 | 4 | 974.54 | 727.52 | 201.41 | 45.61 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883117800 |  | 100428611 |  | 7348140T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW3934 | PW3934 | 071 | ORK | 2023-09-15 | U129900 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | ASHEPHERD | 2023-09-15 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - EAST | 2631 | 21883297000 |  | 100414354 |  | 7340268J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | EK | EK RD | 089 | GRE | 2023-09-15 | RECUMP | U120245 | 2021-01-30 | 2023-09-14 | 2023-12-31 |  | RECUMP | 2023-09-15 | 2023-07-11 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 13.3333 | 4 | 2213.46 | 873.96 | 31.39 | 425.46 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959265600 |  | 100261159 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | BARBER | 330 BARBER RD | 019 | ASH | 2023-09-15 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-09-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1955.58 | 69 | 0 | 3.78 | 1882.8 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960856200 |  | 100447856 |  | 7360248A | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | MAYO | 10001 MAYO TL | 019 | CAT | 2023-09-18 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-09-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2643.66 | 0 | 0 | 0 | 2643.66 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129054500 |  | 100277668 |  | 6688228E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SCHENKEL | 130 SCHENKEL LN | 073 | FRA | 2023-10-02 | U461383 | U130722 | 2022-09-05 | 2022-12-30 |  |  | EFGOINS | 2023-09-15 | 2022-12-28 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 29.9 | 7 | 2822.6 | 1796.62 | 0 | 100.08 | 925.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23195346300 |  | 100305145 |  | 6712212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | TRAVELLER | 1853 TRAVELLER RD | 067 | LEX | 2023-09-15 | KKINDER | U132761 | 2023-06-16 | 2023-12-15 | 2025-06-30 |  | KKINDER | 2023-09-15 | 2023-08-31 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.9833 | 7 | 2251.86 | 1473.59 | 697.36 | 80.91 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23195708800 |  | 100330839 |  | 6720208B |  |  |  | 565 | EX | RPL SVC LINE - CORROSION | 2621P | RICHMOND | 1501 RICHMOND RD | 067 | LEX | 2023-09-18 | U930915 | U135005 | 2023-06-19 | 2023-12-29 |  |  | TROE | 2023-09-15 | 2023-07-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 38.9 | 13 | 3486.51 | 2451.47 | 331.41 | 136.63 | 567 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23206977800 |  | 100303198 |  | 6712208G |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332605 | 2621P | LILY | 921 LILY DR | 067 | LEX | 2023-09-18 | U930915 | U135005 | 2023-08-08 | 2024-02-05 | 2025-08-31 |  | RJCRAWF | 2023-09-15 | 2023-08-31 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.9167 | 4 | 1754.46 | 1178.92 | 510.81 | 64.73 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23213113200 |  | 100288303 |  | 6720212H |  |  |  | 565 | EX | REPLACE S/L | 2621P | SHAFTSBURY | 580 SHAFTSBURY DR | 067 | LEX | 2023-09-15 | U930915 | U131366 | 2023-09-05 | 2023-09-08 | 2023-09-26 |  | RJCRAWF | 2023-09-15 | 2023-09-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.9667 | 3 | 878.84 | 528.09 | 321.79 | 28.96 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23215105800 |  | 100322695 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 716 PROVIDENCE RD | 067 | LEX | 2023-09-15 | U126604 | U125763 | 2023-09-15 | 2023-12-29 |  |  | WILL FULKS | 2023-09-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1889.7 | 0 | 0 | 0 | 1889.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23215113200 |  | 100351839 |  | 6744208O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | FINLEY | 102 FINLEY RD | 049 | WIN | 2023-09-15 | NRICHIE | U134852 | 2023-09-15 | 2023-09-15 | 2023-09-15 |  | NRICHIE | 2023-09-15 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26290021 | 11.8333 | 2 | 1527.46 | 860.33 | 257.19 | 409.94 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 06641464600 |  | 100408447 |  | 7320280B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | FIREBRICK | FIREBRICK RD | 135 | FIR | 2023-09-18 | RECUMP | DYOUNG | 2006-03-15 | 2023-09-18 | 2023-12-31 |  | RECUMP | 2023-09-18 | 2022-10-06 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.4 | 5 | 243.58 | 143.89 | 31.39 | 68.3 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 13175749600 |  | 100243243 |  | T-1601-40 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | LOCUST | LOCUST ST RR | 089 | S S | 2023-09-18 | RECUMP | U125201 | 2013-11-15 | 2023-09-18 | 2023-12-31 |  | RECUMP | 2023-09-18 | 2022-11-16 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.4833 | 3 | 593.52 | 340.63 | 0 | 252.89 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883089700 |  | 500023132 |  | 7352160T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | STRATTON | 63 STRATTON ST | 071 | IVE | 2023-09-18 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BLAKE MULLINS | 2023-09-18 | 2023-09-14 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 4.0667 | 1 | 529.99 | 265.43 | 0 | 264.56 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883263700 |  | 100431178 |  | 7356156T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW4653 | PW4653 | 195 | BET | 2023-09-28 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BLAKE MULLINS | 2023-09-18 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - EAST | 2633 | 21883269100 |  | 100260467 |  | 7344152T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW4006 | PW4006 | 071 | HUN | 2023-09-18 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BLAKE MULLINS | 2023-09-18 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - WEST | 2623 | 21947536200 |  | 500207522 |  | 6684228C |  |  |  | 566 | EX | ABANDON SL | 2621P | COMPTON | 120 COMPTON DR 2 | 073 | FRA | 2023-09-18 | EFGOINS | U131066 | 2021-10-19 | 2021-12-30 |  |  | EFGOINS | 2023-09-18 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8.2167 | 4 | 441.93 | 418.93 | 0 | 23 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21947536400 |  | 500207523 |  | 6684228C |  |  |  | 566 | EX | ABANDON SL | 2621P | COMPTON | 120 COMPTON DR 3 | 073 | FRA | 2023-09-18 | EFGOINS | U131066 | 2021-10-19 | 2021-12-30 |  |  | EFGOINS | 2023-09-18 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8.3333 | 4 | 537.76 | 509.84 | 0 | 27.92 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21947536500 |  | 500207524 |  | 6684228C |  |  |  | 566 | EX | ABANDON SL | 2621P | COMPTON | 120 COMPTON DR 4 | 073 | FRA | 2023-09-19 | U123688 | U131066 | 2021-10-19 | 2021-12-30 |  |  | EFGOINS | 2023-09-18 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 15.45 | 3 | 1068.94 | 1013.37 | 0 | 55.57 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960855400 |  | 100250213 |  | 7360248A | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | ICE CREEK | 8618 ICE CREEK RD | 019 | CAT | 2023-09-19 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-09-18 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2773.09 | 0 | 0 | 0 | 2773.09 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026205800 |  |  |  | 7240216M | 2286853 | U128885 |  | 560 | EX | RETIRE 20'-2" PMP | 2600B | HOLT | HOLT AV | 173 | MT | 2023-10-04 | U128132 | U128885 | 2022-06-17 | 2023-12-29 | 2023-12-31 | 2023-09-18 | LYN STAFFORD | 2023-09-18 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00560 | 3200560 |  |  | WP2058 | AMRCB |  | 100 | 056032220262058 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22979023000 |  | 100259292 |  | 7356148T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | TOLER CREEK | 2984 TOLER CREEK | 071 | HAR | 2023-09-18 | U130172 | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | BLAKE MULLINS | 2023-09-18 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - EAST | 2633 | 22979045000 |  | 100422294 |  | 7348156T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY ROUTE 1426 | 5105 KY ROUTE 1426 | 071 | DAN | 2023-09-19 | U130172 | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | BLAKE MULLINS | 2023-09-18 | 2023-08-08 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.55 | 1 | 215.14 | 203.46 | 0 | 11.68 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026293900 |  |  |  | 6744208F | 2300046 | U461383 |  | 557 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | 2621P | WESTSIDE | 159 WESTSIDE DR | 049 | WIN | 2023-09-18 | U128132 | U461383 | 2023-09-11 | 2023-09-05 | 2023-09-07 | 2023-09-08 | NRICHIE | 2023-09-18 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP2939 |  |  | 100 | 055732230262939 |  | 3 | 7147.03 | 4263.16 | 0 | 1045.72 | 0 | 0 | 16.73 | 1821.42 | 3
KY | KY - CENTRAL | 2629 | 23026294000 |  |  |  | 6744208F | 2300046 | U461383 |  | 558 | EX | EMER-RETIRE 3' OF 2"PMMP MAIN | 2621P | WESTSIDE | 159 WESTSIDE DR | 049 | WIN | 2023-09-18 | U128132 | U461383 | 2023-09-11 | 2023-09-07 | 2023-09-07 | 2023-09-08 | NRICHIE | 2023-09-18 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP2940 |  |  | 100 | 055832230262940 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165288800 |  | 100294828 |  | 6716212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | UPPER | 448 N UPPER ST 3-2FRR | 067 | LEX | 2023-09-18 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-09-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.5167 | 1 | 9445.81 | 616.47 | 0 | 33.8 | 8795.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166675800 |  | 100322699 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 732 PROVIDENCE RD | 067 | LEX | 2023-09-18 | U461443 | U125763 | 2023-02-14 | 2023-12-29 |  |  | WGRAVES | 2023-09-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1957.32 | 0 | 0 | 0 | 1957.32 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168137400 |  | 100275051 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WAPPING | 320 WAPPING ST | 073 | FRA | 2023-09-19 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-09-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2544.33 | 0 | 0 | 0 | 2544.33 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23194689000 |  | 100264121 |  | 7352260M |  |  |  | 565 | EX | REPLACE SERVICE LINE - D259508 | 2621P | MIDDLETOWN | 526 MIDDLETOWN AV | 019 | ASH | 2023-09-18 | MCOLLET | U135005 | 2023-06-14 | 2023-12-13 | 2025-06-30 |  | MCOLLET | 2023-09-18 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 15.5667 | 2 | 3025.84 | 1127.26 | 395.78 | 1502.8 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212646400 |  | 100339437 |  | 6724212A |  |  |  | 565 | EX | REPLACE SERVICE LINE - D341475 | 2621P | HUNTSVILLE | 1430 HUNTSVILLE DR A | 067 | LEX | 2023-09-19 | U123688 | U135005 | 2023-09-01 | 2023-09-01 | 2023-09-21 |  | LSTANFI | 2023-09-18 | 2023-09-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.3833 | 4 | 1750.07 | 1335.96 | 333.09 | 81.02 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23214512700 |  | 100350579 |  | 6744204C |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | COLBY | 502 COLBY RD | 049 | WIN | 2023-09-18 | U930915 | U135005 | 2023-09-13 | 2023-11-13 | 2023-11-13 |  | WHIMES | 2023-09-18 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 12.5667 | 2 | 1864.01 | 945.91 | 310.27 | 51.83 | 556 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23215366500 |  | 100294831 |  | 6716212E | 2177145 |  |  | 566 | EX | ABANDN SL/21026997801 | 2600B | UPPER | 448 N UPPER ST 1FL | 067 | LEX | 2023-09-18 | U126532 | U125763 | 2023-09-18 | 2023-12-29 |  |  | LESLIE SHARON | 2023-09-18 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - EAST | 2631 | 06645586700 |  | 100262886 |  | 7352260O |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | HOODS CREEK | 1622 HOODS CREEK PK | 019 | ASH | 2023-09-19 | RECUMP | RRYAN | 2006-04-24 | 2023-09-19 | 2023-12-31 |  | RECUMP | 2023-09-19 | 2022-10-25 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 63.5667 | 41 | 7732.97 | 4033.05 | 0 | 1978.5 | 1721.42 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883170500 |  | 100251997 |  | 7376184T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | PIL | 2023-09-19 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-09-19 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - EAST | 2633 | 21883266300 |  | 100431153 |  | 7372180T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | PIL | 2023-09-19 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | CLYDE HAMMOND | 2023-09-19 | 2023-09-18 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.2667 | 1 | 168.33 | 95.49 | 0 | 72.84 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960855300 |  | 100467053 |  | 7356248H | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | ICE CREEK | 8530 ICE CREEK RD | 019 | CAT | 2023-09-20 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-09-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3080.47 | 0 | 0 | 0 | 3080.47 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026182101 |  | 501328813 |  | 6740204H | 2288186 | U128885 |  | 555 | EX | INSTALL 8,450' - 2"/4" PMMP | 2600B | MCCLURE | 2130 MCCLURE RD | 049 | WIN | 2023-11-03 | U128132 | U128885 | 2023-04-04 | 2023-05-30 | 2023-12-01 | 2023-09-19 | EFOX | 2023-09-19 | 2023-09-06 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP1821 |  |  | 100 | 055532220261821 | 1135.7833 | 1086096 | 940113.78 | 77274.77 | 33345.12 | 16801.36 | 638865.72 | 0 | 23608.27 | 150218.54 | 7986
KY | KY - EAST | 2633 | 22129015700 |  | 100453419 |  | 7376188T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GROUNDHOG | 123 GROUNDHOG RD | 159 | WAR | 2023-09-19 | U130172 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JOHN KIRK | 2023-09-19 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - EAST | 2633 | 22129120600 |  | 100430931 |  | 7364140T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | GREASY | GREASY CK | 195 | SHE | 2023-09-19 | U130172 | U125208 | 2022-09-06 | 2022-12-30 |  |  | BRIAN PREECE | 2023-09-19 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.4333 | 1 | 260.76 | 247.2 | 0 | 13.56 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026295300 |  |  |  | 7240216M | 2286853 | U461383 |  | 586 | EX | RETIRE FENCE | 2629M | ROGERS | ROGERS AV | 173 | MT | 2023-09-20 | U123258 | U461383 | 2023-09-19 | 2023-11-01 | 2023-11-01 | 2023-09-14 | JAMES PASLEY | 2023-09-19 |  |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00586 | 3200586 |  |  | WP2953 |  |  | 100 | 058632230262953 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165288700 |  | 100294845 |  | 6716212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | UPPER | 445 N UPPER ST | 067 | LEX | 2023-09-19 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-09-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.5167 | 1 | 3381.43 | 544.22 | 0 | 29.82 | 2807.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166670400 |  | 100322645 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 704 BERRY LN | 067 | LEX | 2023-09-19 | U461443 | U125763 | 2023-02-14 | 2023-12-29 |  |  | WGRAVES | 2023-09-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1130.97 | 0 | 0 | 0 | 1130.97 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179205200 |  | 500156512 |  | 7352260O | 2286985 |  |  | 565 | EX | RPLC SL/22026172300 | 2600B | WHEATLEY | 503 WHEATLEY RD | 019 | ASH | 2023-09-20 | U125566 | U125763 | 2023-04-05 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-09-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 5443.24 | 0 | 0 | 0 | 5443.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23211915500 |  | 100340337 |  | 6724212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332992 | 2621P | AUGUSTA | 1776 AUGUSTA CT G8 | 067 | LEX | 2023-09-20 | U135005 | U135005 | 2023-08-30 | 2024-02-29 | 2025-08-31 |  | LSTANFI | 2023-09-19 | 2023-09-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.8833 | 4 | 3037.66 | 1709.78 | 1026.19 | 301.69 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23211999500 |  | 100315962 |  | 6716208G |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | NICHOLASVILLE | 1737 NICHOLASVILLE RD | 067 | LEX | 2023-09-19 | RSTRONG | U133234 | 2023-08-30 | 2023-09-13 | 2023-09-29 |  | RSTRONG | 2023-09-19 | 2023-09-18 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 20.6667 | 4 | 2143.87 | 1194.54 | 0 | 266.19 | 683.14 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23214185400 |  | 100246130 |  | 7324284A |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | BENTLEY | 56 BENTLEY LN | 089 | S P | 2023-09-22 | U135005 | U135005 | 2023-09-12 | 2023-11-15 | 2023-12-31 |  | BROBERT | 2023-09-19 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 10.5 | 2 | 1065.83 | 687.38 | 20.27 | 358.18 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23215539500 |  | 100275084 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WASHINGTON | 213 WASHINGTON ST | 073 | FRA | 2023-09-20 | U461375 | U125763 | 2023-09-19 | 2023-12-29 |  |  | LARRY BROWN | 2023-09-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2376.77 | 0 | 0 | 0 | 2376.77 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23215554600 |  | 100294843 |  | 6716212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997801 | 2600B | UPPER | 453 N UPPER ST | 067 | LEX | 2023-09-19 | U126532 | U125763 | 2023-09-19 | 2023-12-29 |  |  | LESLIE SHARON | 2023-09-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 2308.49 | 0 | 0 | 0 | 2308.49 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23215559300 |  | 100331337 |  | 6720212N |  |  |  | 565 | EX | RPLC SL/ | 2600B | OWSLEY | 314 OWSLEY AV | 067 | LEX | 2023-09-20 | U461423 | U125763 | 2023-09-19 | 2023-12-29 |  |  | KKOUNS | 2023-09-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 1140.63 | 0 | 0 | 0 | 1140.63 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883145800 |  | 100427752 |  | 7376168T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW8969 | PW8969 | 195 | SID | 2023-09-26 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | CLYDE HAMMOND | 2023-09-20 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - WEST | 2623 | 21947536100 |  | 500207521 |  | 6684228C |  |  |  | 566 | EX | ABANDON SL | 2621P | COMPTON | 120 COMPTON DR 1 | 073 | FRA | 2023-09-20 | EFGOINS | U131066 | 2021-10-19 | 2023-09-20 |  |  | EFGOINS | 2023-09-20 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 4.8 | 3 | 306.08 | 290.18 | 0 | 15.9 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959270000 |  | 100261155 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | SANDERS | 2218 SANDERS RD | 019 | ASH | 2023-09-20 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-09-20 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2727.5 | 0 | 0 | 0 | 2727.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959274000 |  | 100261154 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | SANDERS | 2214 SANDERS RD | 019 | ASH | 2023-09-20 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-09-20 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2050.34 | 0 | 0 | 0 | 2050.34 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960852400 |  | 100250201 |  | 7356248D | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | CANNONSBURG | 8175 CANNONSBURG PK | 019 | CAT | 2023-09-20 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-09-20 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2720.13 | 0 | 0 | 0 | 2720.13 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129015800 |  | 500222530 |  | 7388156T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ST HWY 1056 | 388 ST HWY 1056 | 195 | PIN | 2023-09-20 | U130172 | U130722 | 2022-09-05 | 2022-12-30 |  |  | CLYDE HAMMOND | 2023-09-20 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - CENTRAL | 2632 | 22129024800 |  | 100355325 |  | 7260280N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BROADWAY | 312 BROADWAY ST | 161 | MAY | 2023-09-20 | SDADAMS | U130722 | 2022-09-05 | 2022-12-30 |  |  | SDADAMS | 2023-09-20 | 2023-09-06 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 11.45 | 3 | 1195.96 | 788.83 | 17.64 | 389.49 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22979019800 |  | 100250494 |  | 7376188T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | BEA | 2023-09-25 | U130172 | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | CLYDE HAMMOND | 2023-09-20 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - EAST | 2682 | 22979046700 |  | 100430341 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | GENERAL DELIVE | GENERAL DELIVE | 153 | GUN | 2023-09-20 | U130172 | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | BRIAN PREECE | 2023-09-20 |  |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 4.0167 | 1 | 299.69 | 284.11 | 0 | 15.58 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026290100 |  |  |  | 7344268P | 2399764 | U128885 |  | 557 | EX | EMER - 3'-3" PMIP | 2621P | BERNITA | BERNITA | 089 | WOR | 2023-12-26 | U128132 | U128885 | 2023-08-28 | 2024-04-26 |  | 2023-08-15 | MCOLLET | 2023-09-20 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP2901 |  |  | 100 | 055732230262901 | 4 | 6 | 5680.32 | 2219.57 | 597.76 | 1682.92 | 0 | 0 | 9.31 | 1170.76 | 3
KY | KY - EAST | 2631 | 23026290200 |  |  |  | 7344268P | 2399764 | U128885 |  | 558 | EX | EMER-RETIRE 3'-PIP | 2621P | BERNITA | BERNITA | 089 | WOR | 2023-09-28 | U128132 | U128885 | 2023-08-28 | 2024-04-30 |  | 2023-08-15 | MCOLLET | 2023-09-20 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP2902 |  |  | 100 | 055832230262902 | 1.1833 | 0 | 253 | 85.37 | 0 | 167.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165288400 |  | 100294826 |  | 6716212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | UPPER | 438 N UPPER ST | 067 | LEX | 2023-09-20 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-09-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.5 | 1 | 2811.35 | 469.76 | 0 | 25.75 | 2315.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166674700 |  | 100322669 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 709 PROVIDENCE RD | 067 | LEX | 2023-09-20 | U461443 | U125763 | 2023-02-14 | 2023-12-29 |  |  | WGRAVES | 2023-09-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1733.6 | 0 | 0 | 0 | 1733.6 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168130900 |  | 100275102 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | MAIN | 415 W MAIN ST | 073 | FRA | 2023-09-20 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-09-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3659.44 | 0 | 0 | 0 | 3659.44 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168133900 |  | 100275231 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WASHINGTON | 300 WASHINGTON ST | 073 | FRA | 2023-09-20 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-09-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2152.11 | 0 | 0 | 0 | 2152.11 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168969400 |  | 100274211 |  | 6684228N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | TODD | 215 W TODD ST | 073 | FRA | 2023-09-20 | EFGOINS | MDULANE | 2023-02-23 | 2024-02-20 | 2024-02-20 |  | EFGOINS | 2023-09-20 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 19.2 | 3 | 1196.29 | 1134.07 | 0 | 62.22 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23171853200 |  | 100461331 |  | 6696212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D310001 | 2621P | SCARBOROUGH | 511 SCARBOROUGH DR | 239 | VER | 2023-09-25 | U128410 | U125208 | 2023-03-06 | 2023-09-05 | 2025-03-31 |  | CDESPAIN | 2023-09-20 | 2023-09-21 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 20.45 | 5 | 2306.69 | 1609.68 | 0 | 697.01 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23171853400 |  | 100465853 |  | 6696212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D310002 | 2621P | CAMBRIDGE | 306 CAMBRIDGE CT | 239 | VER | 2023-09-25 | U128410 | U125208 | 2023-03-06 | 2023-09-05 | 2025-03-31 |  | CDESPAIN | 2023-09-20 | 2023-09-18 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 13.3333 | 6 | 1117.45 | 1011.73 | 0 | 105.72 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179205300 |  | 100265063 |  | 7352260O | 2286985 |  |  | 565 | EX | RPLC SL/22026172300 | 2600B | WHEATLEY | 515 WHEATLEY RD | 019 | ASH | 2023-09-21 | U125566 | U125763 | 2023-04-05 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-09-20 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3036.12 | 0 | 0 | 0 | 3036.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23206498300 |  | 100339185 |  | 6724212I |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332976 | 2621P | CANTRILL | 1812 CANTRILL DR | 067 | LEX | 2023-09-20 | LSTONE | U135005 | 2023-08-04 | 2024-02-02 | 2025-08-31 |  | LSTONE | 2023-09-20 | 2023-08-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.7833 | 5 | 1463.57 | 972.29 | 437.87 | 53.41 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23210774100 |  | 100316406 |  | 6716208F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D341453 | 2621P | VENICE | 111 VENICE PR | 067 | LEX | 2023-09-20 | RSTRONG | U135005 | 2023-08-24 | 2024-02-23 | 2025-08-31 |  | RSTRONG | 2023-09-20 | 2023-09-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 17.4667 | 3 | 1355.8 | 1005.96 | 204.99 | 144.85 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23211767800 |  | 100340329 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | AUGUSTA | 1776 AUGUSTA CT G1 | 067 | LEX | 2023-09-21 | U130722 | AOC SYST | 2023-08-29 | 2023-09-19 | 2024-12-31 |  | LSTANFI | 2023-09-20 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 1.5833 | 2 | 141.02 | 113.95 | 0 | 27.07 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23211915000 |  | 100340321 |  | 6724212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332991 | 2621P | AUGUSTA | 1780 AUGUSTA CT F1 | 067 | LEX | 2023-09-21 | U130722 | U135005 | 2023-08-30 | 2024-02-29 | 2025-08-31 |  | LSTANFI | 2023-09-20 | 2023-09-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.6333 | 4 | 2117.36 | 1805.22 | 0 | 312.14 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23214215200 |  | 100329736 |  | 6720208D |  |  |  | 565 | EX | REPLACE SL - UNMETERED GAS | 2621P | SAINT MICHAEL | 2048 SAINT MICHAEL DR | 067 | LEX | 2023-09-20 | WISHII | U135005 | 2023-09-12 | 2023-10-12 | 2023-10-12 |  | WISHII | 2023-09-20 | 2023-09-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.0833 | 4 | 1700.45 | 1085.2 | 0 | 615.25 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23215564400 |  | 100325427 |  | 6720208E |  |  |  | 565 | EX | GRADE 1 REPLACE S/L | 2621P | LAKEWOOD | 1089 LAKEWOOD DR | 067 | LEX | 2023-09-22 | U135005 | U129939 | 2023-09-19 | 2023-09-19 | 2023-09-19 |  | HMCKUNE | 2023-09-20 | 2023-09-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.8 | 3 | 1070.8 | 1015.12 | 0 | 55.68 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23215894900 |  | 100294825 |  | 6716212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997801 | 2600B | UPPER | 432 N UPPER ST | 067 | LEX | 2023-09-20 | U126532 | U125763 | 2023-09-20 | 2023-12-29 |  |  | LESLIE SHARON | 2023-09-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2760.96 | 0 | 0 | 0 | 2760.96 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883092300 |  | 100426776 |  | 7388156T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | GENERAL DELIVE | GENERAL DELIVE | 119 | PIN | 2023-09-25 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BRIAN PREECE | 2023-09-21 | 2023-09-08 |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 13.35 | 2 | 997.91 | 946.03 | 0 | 51.88 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883105800 |  | 100420311 |  | 7376188T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | BIG ELK | BIG ELK RD | 159 | BEA | 2023-09-25 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | CLYDE HAMMOND | 2023-09-21 | 2023-09-21 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.7333 | 1 | 740.48 | 420.06 | 0 | 320.42 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883191100 |  | 100253523 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | INE | 2023-09-25 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-09-21 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - EAST | 2631 | 21959269900 |  | 500730715 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | SANDERS | 2215 SANDERS RD | 019 | ASH | 2023-09-21 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-09-21 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2660.95 | 113.45 | 0 | 6.32 | 2541.18 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959276900 |  | 100261156 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | SANDERS | 2304 SANDERS RD | 019 | ASH | 2023-09-21 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-09-21 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2570.55 | 0 | 0 | 0 | 2570.55 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129030900 |  | 100247308 |  | 7352256L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BEECH | 2315 BEECH ST 3 | 019 | ASH | 2023-09-21 | JCYRUS | U130722 | 2022-09-05 | 2023-10-17 | 2023-10-17 |  | JCYRUS | 2023-09-21 | 2023-09-14 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 25.45 | 4 | 2125.09 | 1794.04 | 63.69 | 267.36 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165288900 |  | 100294844 |  | 6716212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | UPPER | 449 N UPPER ST | 067 | LEX | 2023-09-21 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-09-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.5 | 1 | 3446.5 | 469.76 | 0 | 25.75 | 2950.99 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168128600 |  | 500376942 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | LONG | 310 LONG LN | 073 | FRA | 2023-09-21 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-09-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2229.77 | 0 | 0 | 0 | 2229.77 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168130800 |  | 100275109 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | MAIN | 412 W MAIN ST | 073 | FRA | 2023-09-21 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-09-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2223.16 | 0 | 0 | 0 | 2223.16 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179205400 |  | 100265062 |  | 7352260O | 2286985 |  |  | 565 | EX | RPLC SL/22026172300 | 2600B | WHEATLEY | 517 WHEATLEY RD | 019 | ASH | 2023-09-22 | U125566 | U125763 | 2023-04-05 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-09-21 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 5356.13 | 0 | 0 | 0 | 5356.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23211978200 |  | 100322904 |  | 6716208H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309381 | 2621P | TATES CREEK | 1781 TATES CREEK RD | 067 | LEX | 2023-09-22 | U135005 | U135005 | 2023-08-30 | 2024-01-31 | 2025-08-31 |  | RJCRAWF | 2023-09-21 | 2023-09-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.4167 | 6 | 1845.12 | 1220.25 | 557.98 | 66.89 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23213146600 |  | 500347896 |  | 6724208M | 9404670 |  |  | 566 | EX | ABANDON SL - DEMO | 2621P | RICHMOND | 3450 RICHMOND RD 130 | 067 | LEX | 2023-09-21 | HMCKUNE | U135005 | 2023-09-06 | 2023-10-06 | 2023-10-06 |  | HMCKUNE | 2023-09-21 | 2023-09-07 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.7833 | 5 | 894.64 | 839.6 | 9.04 | 46 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23215333200 |  | 100267557 |  | 7352260F |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | PATTON | 304 PATTON DR | 019 | ASH | 2023-09-21 | MCOLLET | U132761 | 2023-09-18 | 2023-12-29 |  |  | MCOLLET | 2023-09-21 | 2023-09-20 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 31.5167 | 4 | 6113.59 | 2295.31 | 370.53 | 3447.75 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23215954400 |  | 100340323 |  | 6724212E |  |  |  | 565 | EX | REPLACE SERVICE | 2621P | AUGUSTA | 1780 AUGUSTA CT F3 | 067 | LEX | 2023-09-22 | U135005 | U129939 | 2023-09-20 | 2023-09-20 |  |  | LSTANFI | 2023-09-21 | 2023-09-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.7333 | 3 | 1519.41 | 671.16 | 752.73 | 95.52 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23216250400 |  | 100322646 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 708 BERRY LN | 067 | LEX | 2023-09-21 | U126530 | U125763 | 2023-09-21 | 2023-12-29 |  |  | JDUNN | 2023-09-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2112.53 | 0 | 0 | 0 | 2112.53 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026170600 |  |  |  | 7240216N | 2286853 | U128885 |  | 557 | EX | INSTALL 7,200'-2"/4" PMMP | 2600B | HOLT | HOLT AV | 173 | MT | 2023-11-28 | U128132 | U128885 | 2022-02-23 | 2023-04-06 | 2023-12-31 | 2023-06-20 | LYN STAFFORD | 2023-09-22 | 2023-03-20 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP1706 | AMRCB |  | 100 | 055732220261706 | 1000.6167 | 1021293 | 1526718.34 | 65788.19 | 26277.23 | 53072.54 | 1092812.21 | 0 | 6059.64 | 282708.53 | 7917
KY | KY - CENTRAL | 2629 | 22026170700 |  |  |  | 7240216N | 2286853 | U128885 |  | 558 | EX | RETIRE BSLP | 2600B | HOLT | HOLT AV | 173 | MT | 2023-10-04 | U128132 | U128885 | 2022-02-23 | 2023-12-29 | 2023-12-31 | 2023-09-14 | LYN STAFFORD | 2023-09-22 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP1707 | AMRCB |  | 100 | 055832220261707 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22100764900 |  | 500020111 |  | 6716212J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | RED MILE | 711 RED MILE RD A | 067 | LEX | 2023-09-25 | U135005 | U134723 | 2022-05-16 | 2022-07-01 | 2023-12-31 |  | KOBRYAN | 2023-09-22 | 2022-11-10 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10.1167 | 9 | 661.53 | 625.51 | 0 | 36.02 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22129078900 |  | 100320075 |  | 6716208K |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NICHOLASVILLE | 2000 NICHOLASVILLE RD | 067 | LEX | 2023-09-22 | U128336 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JOSHUA COX | 2023-09-22 | 2023-07-27 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 34.2 | 16 | 3178.53 | 2243.7 | 2.11 | 124.27 | 808.45 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166676400 |  | 100322660 |  | 6720208A | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 801 PROVIDENCE RD | 067 | LEX | 2023-09-22 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-09-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1271.56 | 0 | 0 | 0 | 1271.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179203300 |  | 100439370 |  | 7352260O | 2286985 |  |  | 565 | EX | RPLC SL/22026172300 | 2600B | MAIN | 1805 MAIN ST W | 019 | ASH | 2023-09-25 | U125566 | U125763 | 2023-04-05 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-09-22 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 4293.71 | 0 | 0 | 0 | 4293.71 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23208096900 |  | 100284033 |  | 6712228N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332609 | 2621P | GLENWOOD | 404 GLENWOOD DR | 209 | GEO | 2023-09-22 | DCOLLIN | U135005 | 2023-08-14 | 2024-02-09 | 2025-08-31 |  | DCOLLIN | 2023-09-22 | 2023-09-21 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 28.25 | 5 | 3124.38 | 1947.68 | 460.59 | 716.11 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23216192800 |  | 100250229 |  | 7356248H | 2180320 |  |  | 565 | EX | RPLC SL/21026130400 | 2600B | CANNONSBURG | 8110 CANNONSBURG RD | 019 | CAT | 2023-09-22 | U123965 | U131066 | 2023-09-21 | 2023-12-29 |  |  | CJH DEREK CRAGER | 2023-09-22 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 2724.95 | 0 | 0 | 0 | 2724.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23216246700 |  | 100331433 |  | 6720212N |  |  |  | 565 | EX | 24HR GAS OFF - RPLC SL D310426 | 2621P | VICTORY | 112 VICTORY AV | 067 | LEX | 2023-09-25 | U135005 | U135005 | 2023-09-21 | 2023-09-21 | 2023-09-21 |  | HMCKUNE | 2023-09-22 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 16 | 2 | 1208.97 | 1080.35 | 69.4 | 59.22 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23216562700 |  | 501178915 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | LONG | 324 LONG ST | 019 | ASH | 2023-09-22 | U124015 | U125201 | 2023-09-22 | 2023-10-30 |  |  | ORA SLONE | 2023-09-22 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2305.28 | 0 | 0 | 0 | 2305.28 | 0 | 0 | 0
KY | KY - WEST | 2623 | 03533169000 |  | 100449101 | 34 | X |  |  |  | 566 | EX | ABANDON COMPANY SERVICE LINE C | 2621P | MAIN | 141 E MAIN ST 2 | 239 | MID | 2023-09-25 | U128410 | AJAMES | 2003-03-10 | 2049-12-31 |  |  | CDESPAIN | 2023-09-25 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 5.4 | 2 | 401.16 | 380.31 | 0 | 20.85 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 08727605100 |  | 100273303 |  | 6680224D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LOUISVILLE | 1439 LOUISVILLE RD | 073 | FRA | 2023-10-02 | U461383 | RPOLLY | 2008-04-16 | 2017-03-31 |  |  | S. BARKER | 2023-09-25 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - CENTRAL | 2632 | 20804656300 |  | 100354104 |  | 7256280P | 2074435 | U132002 |  | 566 | EX | ABND - CONSTR/AMRP 20026973800 | 2600B | 3RD | 130 E 3RD ST | 161 | MAY | 2023-09-25 | SDADAMS | U132002 | 2020-04-28 | 2023-09-25 |  |  | SDADAMS | 2023-09-25 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 11.9167 | 3 | 700.82 | 663.94 | 0 | 36.88 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883146000 |  | 500509351 |  | 7352256H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | TURNER | 28 TURNER CT | 089 | S S | 2023-09-25 | RECUMP | U120245 | 2021-01-30 | 2023-09-25 | 2023-12-31 |  | RECUMP | 2023-09-25 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.5333 | 1 | 8698.18 | 298.51 | 0 | 253.98 | 8145.69 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959269800 |  | 100261153 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | SANDERS | 2210 SANDERS RD | 019 | ASH | 2023-09-25 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-09-25 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2591.73 | 0 | 0 | 0 | 2591.73 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959273600 |  | 100261066 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | JENKINS | 107 JENKINS ST | 019 | ASH | 2023-09-25 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-09-25 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1919.87 | 0 | 0 | 0 | 1919.87 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960883500 |  | 100250235 |  | 7360248A | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | CEMETERY | 8524 CEMETERY RD | 019 | CAT | 2023-09-25 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-09-25 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 5420.42 | 0 | 0 | 0 | 5420.42 | 0 | 0 | 0
KY | KY - EAST | 2682 | 22129015100 |  | 100426601 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2633S | BEN SLONE CEME | 71 BEN SLONE CEME RD | 119 | GAR | 2023-09-25 | U130172 | U130722 | 2022-09-05 | 2022-12-30 |  |  | BRIAN PREECE | 2023-09-25 |  |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 11.85 | 2 | 885.54 | 839.5 | 0 | 46.04 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165287800 |  | 100294818 |  | 6716212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | UPPER | 418 N UPPER ST | 067 | LEX | 2023-09-25 | U461443 | U125763 | 2023-02-07 | 2023-12-29 |  |  | WGRAVES | 2023-09-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2362.39 | 0 | 0 | 0 | 2362.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165289000 |  | 100294832 |  | 6716212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | UPPER | 450 N UPPER ST | 067 | LEX | 2023-09-25 | U461443 | U125763 | 2023-02-07 | 2023-12-29 |  |  | WGRAVES | 2023-09-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2847.19 | 0 | 0 | 0 | 2847.19 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166670800 |  | 100322618 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 713 BERRY LN | 067 | LEX | 2023-09-25 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-09-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1165.2 | 0 | 0 | 0 | 1165.2 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168128400 |  | 100275110 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | LONG | 306 LONG LN | 073 | FRA | 2023-09-25 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-09-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3408.89 | 0 | 0 | 0 | 3408.89 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168128500 |  | 100275111 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | LONG | 308 LONG LN | 073 | FRA | 2023-09-25 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-09-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3326.93 | 577.38 | 0 | 377.68 | 2371.87 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23187129800 |  | 100279695 |  | 6688228O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | BLUEBIRD | 313 BLUEBIRD LN | 073 | FRA | 2023-09-25 | MCRAIG | AOC SYST | 2023-05-09 | 2023-11-09 | 2024-12-31 |  | MCRAIG | 2023-09-25 | 2023-09-12 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 24.6667 | 7 | 3406.74 | 1763.24 | 687.4 | 956.1 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23191605500 |  | 100334966 |  | 6720212P | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | BENWOOD | 1724 BENWOOD DR | 067 | LEX | 2023-09-28 | U135005 | AOC SYST | 2023-05-31 | 2023-11-30 | 2024-12-31 |  | LSTANFI | 2023-09-25 | 2023-09-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 28.4333 | 6 | 2711.02 | 1927.76 | 532.72 | 250.54 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23212691500 |  | 100249747 |  | 7360248A |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | 38TH | 430 38TH ST | 019 | CAT | 2023-09-25 | JCYRUS | U133234 | 2023-09-01 | 2023-09-15 | 2023-10-01 |  | JCYRUS | 2023-09-25 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 14.6667 | 2 | 1330.04 | 1079.05 | 20.27 | 230.72 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23216181900 |  | 100450874 |  | 6712228F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PAWNEE | 1114 PAWNEE TL 1 | 209 | GEO | 2023-09-25 | DCOLLIN | U132761 | 2023-09-21 | 2023-12-29 |  |  | DCOLLIN | 2023-09-25 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 16.7 | 2 | 1688.04 | 1213.37 | 0 | 474.67 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23216182000 |  | 100451118 |  | 6712228F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PAWNEE | 1114 PAWNEE TL 3 | 209 | GEO | 2023-09-25 | DCOLLIN | U132761 | 2023-09-21 | 2024-12-31 |  |  | DCOLLIN | 2023-09-25 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.33333 | 2 | 34.9 | 24.7 | 0 | 10.2 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23216182100 |  | 100451119 |  | 6712228F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PAWNEE | 1114 PAWNEE TL 4 | 209 | GEO | 2023-09-25 | DCOLLIN | U132761 | 2023-09-21 | 2024-12-31 |  |  | DCOLLIN | 2023-09-25 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.13333 | 2 | 14.38 | 10.18 | 0 | 4.2 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23216182200 |  | 100451120 |  | 6712228F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PAWNEE | 1114 PAWNEE TL 5 | 209 | GEO | 2023-09-25 | DCOLLIN | U132761 | 2023-09-21 | 2024-12-31 |  |  | DCOLLIN | 2023-09-25 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.16667 | 2 | 18.49 | 13.09 | 0 | 5.4 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23216182300 |  | 100451121 |  | 6712228F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PAWNEE | 1114 PAWNEE TL 6 | 209 | GEO | 2023-09-25 | DCOLLIN | U132761 | 2023-09-21 | 2024-12-31 |  |  | DCOLLIN | 2023-09-25 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.13333 | 2 | 14.38 | 10.18 | 0 | 4.2 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23216182400 |  | 100451122 |  | 6712228F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PAWNEE | 1114 PAWNEE TL 7 | 209 | GEO | 2023-09-25 | DCOLLIN | U132761 | 2023-09-21 | 2024-12-31 |  |  | DCOLLIN | 2023-09-25 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.2 | 2 | 20.63 | 14.6 | 0 | 6.03 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23216182500 |  | 100451123 |  | 6712228F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PAWNEE | 1114 PAWNEE TL 8 | 209 | GEO | 2023-09-28 | U135005 | U132761 | 2023-09-21 | 2024-12-31 |  |  | DCOLLIN | 2023-09-25 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.23333 | 2 | 24.71 | 17.49 | 0 | 7.22 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23216763200 |  | 100248842 |  | 7356256I |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | BLACKBURN | 2923 BLACKBURN AV | 019 | ASH | 2023-09-25 | JROGER1 | U129939 | 2023-09-25 | 2023-09-25 |  |  | JROGER1 | 2023-09-25 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 11.1333 | 2 | 982.21 | 613.34 | 56.42 | 312.45 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23216832000 |  | 100450875 |  | 6712228F |  |  |  | 566 | EX | ABANDON SL | 2621P | PAWNEE | 1114 PAWNEE TL 2 | 209 | GEO | 2023-09-25 | DCOLLIN | U129939 | 2023-09-25 | 2023-09-25 |  |  | DCOLLIN | 2023-09-25 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.1 | 2 | 10.23 | 7.25 | 0 | 2.98 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11894691400 |  | 100246057 |  | 7320284K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | NEED ADDRESS > 811 | NEED ADDRESS > 811 | 089 | S P | 2023-09-26 | RECUMP | U906307 | 2011-03-08 | 2023-09-26 | 2023-12-31 |  | RECUMP | 2023-09-26 | 2023-07-13 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.8333 | 3 | 2045.73 | 250.83 | 0 | 211.33 | 1583.57 | 0 | 0 | 0
KY | KY - EAST | 2633 | 11909049200 |  | 100450747 |  | 7352142T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | MINK | 1346 MINK BR | 071 | CRA | 2023-09-27 | U130172 | U906631 | 2011-05-31 | 2022-07-01 | 2023-12-31 |  | BLAKE MULLINS | 2023-09-26 | 2022-12-05 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 16.5333 | 3 | 1863.35 | 1174.05 | 0 | 417.68 | 271.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12988296000 |  | 100306015 |  | 600000000 |  |  |  | 565 | EX | REPLACE SL FOR ELEC SHORT | 2621P | ALEXANDRIA | 1592 ALEXANDRIA DR 1A | 067 | LEX | 2023-09-26 | KKINDER | BBRIGHT | 2012-09-13 | 2012-09-19 |  |  | KKINDER | 2023-09-26 | 2023-07-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 86.0667 | 22 | 10164.44 | 5107.13 | 1281.97 | 794.83 | 2980.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 13181916100 |  | 100329625 |  | X |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | SAINT CHRISTOP | 2104 SAINT CHRISTOP DR | 067 | LEX | 2023-09-28 | U135005 | U125208 | 2013-12-17 | 2013-12-17 |  |  | HMCKUNE | 2023-09-26 | 2023-08-31 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.7 | 6 | 1746.53 | 1237.54 | 438.67 | 70.32 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 13181916400 |  | 100329623 |  | 6720208D |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | SAINT CHRISTOP | 2096 SAINT CHRISTOP DR | 067 | LEX | 2023-09-28 | U135005 | U125208 | 2013-12-17 | 2013-12-18 |  |  | HMCKUNE | 2023-09-26 | 2023-08-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25.5833 | 10 | 2157.42 | 1659.23 | 406.91 | 91.28 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883052700 |  | 100253414 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | INE | 2023-09-27 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | CLYDE HAMMOND | 2023-09-26 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - EAST | 2631 | 21959268800 |  | 100261063 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | JENKINS | 124 JENKINS ST | 019 | ASH | 2023-09-26 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-09-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1896.28 | 0 | 0 | 0 | 1896.28 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959275300 |  | 100261069 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | CHERRY | 2201 CHERRY ST | 019 | ASH | 2023-09-26 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-09-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2816.42 | 0 | 0 | 0 | 2816.42 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959275400 |  | 100261067 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | CHERRY | 2209 CHERRY ST | 019 | ASH | 2023-09-26 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-09-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1960.31 | 0 | 0 | 0 | 1960.31 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960853600 |  | 100250176 |  | 7360248A | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | CEMETERY | 8505 CEMETERY RD | 019 | CAT | 2023-09-26 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-09-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2780.96 | 0 | 0 | 0 | 2780.96 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960894100 |  | 100250175 |  | 7360248A | 2180320 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | 36TH | 438< 36TH ST | 019 | CAT | 2023-09-26 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-09-26 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 |  | 1
KY | KY - EAST | 2631 | 22129038200 |  | 100246081 |  | 100000000 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | STATE RT 10 | STATE RT 10 | 089 | S P | 2023-09-26 | RECUMP | U130722 | 2022-09-05 | 2023-09-25 |  |  | RECUMP | 2023-09-26 | 2023-07-13 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.6 | 3 | 2118.84 | 300.31 | 0 | 234.96 | 1583.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165287700 |  | 100294852 |  | 6716212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | UPPER | 417 N UPPER ST | 067 | LEX | 2023-09-26 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-09-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2473.95 | 0 | 0 | 0 | 2473.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166670600 |  | 100322619 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 709 BERRY LN | 067 | LEX | 2023-09-26 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-09-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1651.28 | 0 | 0 | 0 | 1651.28 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23187128600 |  | 100279697 |  | 6688228O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | BLUEBIRD | 325 BLUEBIRD LN | 073 | FRA | 2023-09-28 | U135005 | AOC SYST | 2023-05-09 | 2023-11-09 | 2024-12-31 |  | DMEDLEY | 2023-09-26 | 2023-09-12 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 30.2833 | 6 | 3025.58 | 2101.82 | 269.13 | 654.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23192771500 |  | 100323903 |  | 6716208P | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | BROOK HILL | 824 BROOK HILL DR | 067 | LEX | 2023-09-28 | U135005 | AOC SYST | 2023-06-05 | 2024-12-31 | 2024-12-31 |  | RJCRAWF | 2023-09-26 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 14.0333 | 2 | 825.42 | 782.51 | 0 | 42.91 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23207050100 |  | 100250178 |  | 7356248D | 2180320 |  |  | 565 | EX | RPLC SL/21026130400 | 2600B | 36TH | 444 36TH ST | 019 | CAT | 2023-09-26 | U123965 | U136332 | 2023-08-08 | 2023-12-21 |  |  | CJH DEREK CRAGER | 2023-09-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 |  | 1 | 3603.33 | 0 | 0 | 0 | 3603.33 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23208673100 |  | 500088762 |  | 7348264E |  |  |  | 565 | EX | AOC ATMOS CORR/REPLACE SL | 2621P | GREEN ACRES | 1107 GREEN ACRES DR | 089 | RAC | 2023-09-26 | JCYRUS | U135005 | 2023-08-16 | 2023-10-16 | 2023-10-16 |  | JCYRUS | 2023-09-26 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 12.8667 | 3 | 1241.67 | 976.56 | 209.65 | 55.46 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23211041400 |  | 100314749 |  | 6716212O |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | MONTMULLIN | 178 MONTMULLIN ST | 067 | LEX | 2023-09-26 | KKINDER | U133234 | 2023-08-25 | 2023-09-08 | 2023-09-24 |  | KKINDER | 2023-09-26 | 2023-09-26 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.5333 | 2 | 554.53 | 510.94 | 15.53 | 28.06 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23211075100 |  | 100333747 |  | 6720212I |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | MIDLAND | 276 MIDLAND AV | 067 | LEX | 2023-09-26 | TROE | U133234 | 2023-08-25 | 2023-09-08 | 2023-09-24 |  | TROE | 2023-09-26 | 2023-09-25 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.0667 | 7 | 949.74 | 898.41 | 2.11 | 49.22 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23217054100 |  | 100275238 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | BROADWAY | 409 W BROADWAY ST | 073 | FRA | 2023-09-26 | U461375 | U125763 | 2023-09-26 | 2023-12-29 |  |  | LARRY BROWN | 2023-09-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2897.49 | 0 | 0 | 0 | 2897.49 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883129300 |  | 100246117 |  | 7320284N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | SR10 | SR10 | 089 | S P | 2023-09-27 | RECUMP | U120245 | 2021-01-30 | 2023-09-27 | 2023-12-31 |  | RECUMP | 2023-09-27 | 2023-07-13 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.4667 | 3 | 1669.99 | 160.63 | 35.11 | 124.32 | 1349.93 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883183600 |  | 100467245 |  | U160147 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | US ROUTE 23 | US ROUTE 23 | 089 | S S | 2023-09-27 | RECUMP | U120245 | 2021-01-30 | 2023-09-27 | 2023-12-31 |  | RECUMP | 2023-09-27 | 2022-11-17 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 12.9333 | 5 | 2308.54 | 832.82 | 10.01 | 583.06 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883317100 |  | 100428896 |  | 7352152T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | P1027 | P1027 | 071 | HAR | 2023-09-27 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BLAKE MULLINS | 2023-09-27 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - EAST | 2631 | 21959268900 |  | 100261070 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | JENKINS | 133 JENKINS ST | 019 | ASH | 2023-09-27 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-09-27 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3088.35 | 0 | 0 | 0 | 3088.35 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165288100 |  | 100294850 |  | 6716212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | UPPER | 425 N UPPER ST 1FFT-1 | 067 | LEX | 2023-09-27 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-09-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2398.79 | 0 | 0 | 0 | 2398.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166670900 |  | 100322648 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 716 BERRY LN | 067 | LEX | 2023-09-27 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-09-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1930.18 | 0 | 0 | 0 | 1930.18 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23187127300 |  | 100279699 |  | 6688228O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | BLUEBIRD | 337 BLUEBIRD LN | 073 | FRA | 2023-09-27 | MCRAIG | AOC SYST | 2023-05-09 | 2023-11-09 | 2024-12-31 |  | MCRAIG | 2023-09-27 | 2023-09-13 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 19.1333 | 5 | 2592.19 | 1357.2 | 571.41 | 663.58 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23196747600 |  | 100304875 |  | 6712212L |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | DELLA | 1038 DELLA DR | 067 | LEX | 2023-09-27 | RSTRONG | U135005 | 2023-06-23 | 2023-12-29 |  |  | RSTRONG | 2023-09-27 | 2023-09-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 27.9667 | 7 | 1964.77 | 1510.91 | 135.22 | 318.64 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23205876100 |  | 100328920 |  | 6720208P |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | MOUNT TABOR | 465 MOUNT TABOR RD | 067 | LEX | 2023-09-27 | RSTRONG | U135005 | 2023-08-02 | 2023-12-29 |  |  | RSTRONG | 2023-09-27 | 2023-08-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 45.4833 | 12 | 4332.86 | 2408.05 | 321.74 | 772.82 | 830.25 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23206546600 |  | 100241014 |  | 7356260M |  |  |  | 565 | EX | SERVICE LINE RELOCATION | 2621P | CARTER | 734 CARTER AV | 019 | ASH | 2023-09-29 | U135005 | U135005 | 2023-08-04 | 2023-12-29 |  |  | MCOLLET | 2023-09-27 | 2023-09-13 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 73.9667 | 16 | 20082.9 | 5236.14 | 308.84 | 5227.26 | 9310.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23211448000 |  | 100340180 |  | 6724212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332990 | 2621P | RALEIGH | 1771 RALEIGH RD | 067 | LEX | 2023-09-27 | WISHII | U135005 | 2023-08-29 | 2024-02-29 | 2025-08-31 |  | WISHII | 2023-09-27 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.05 | 2 | 1228.96 | 720.71 | 0 | 508.25 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23216547300 |  | 100341685 |  | 7240216O |  |  |  | 566 | EX | ABANDON SL - DEMO | 2621P | QUEEN | 115 N QUEEN ST LS | 173 | MT | 2023-09-27 | U930915 | U135005 | 2023-09-22 | 2023-10-20 | 2023-10-22 |  | DENNING | 2023-09-27 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 16 | 2 | 1526.69 | 1201.75 | 259.06 | 65.88 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23216753400 |  | 100324105 |  | 6720204I |  |  |  | 565 | EX | REPLACE SERVICE LINE - D341476 | 2621P | NILES | 3653 NILES DR | 067 | LEX | 2023-09-27 | U930915 | U135005 | 2023-09-25 | 2023-09-25 | 2023-10-13 |  | RJCRAWF | 2023-09-27 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.1333 | 2 | 927.54 | 666.34 | 224.65 | 36.55 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23216769800 |  | 100281400 |  | 6712232N |  |  |  | 565 | EX | GRADE 1 REPLACE | 2621P | JEFFERSON | 117 W JEFFERSON ST | 209 | GEO | 2023-09-27 | DCOLLIN | U129939 | 2023-09-25 | 2023-09-25 | 2023-09-25 |  | DCOLLIN | 2023-09-27 | 2023-09-26 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 33.5333 | 4 | 5060.39 | 2433.96 | 275.42 | 913.26 | 1437.75 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23217251900 |  | 100261077 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | CEDAR | 2220 CEDAR ST | 019 | ASH | 2023-09-27 | U124015 | U131066 | 2023-09-27 | 2023-12-29 |  |  | ORA SLONE | 2023-09-27 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2231.85 | 0 | 0 | 0 | 2231.85 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23217284300 |  | 100468573 |  | 6684228N |  |  |  | 566 | EX | RETIRE SERVICE LINE - LEAKAGE | 2621P | ARNETT | 110 ARNETT AV | 073 | FRA | 2023-09-27 | BSEXTON | U129939 | 2023-09-27 | 2020-12-31 |  |  | BSEXTON | 2023-09-27 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 16 | 0 | 928 | 879.75 | 0 | 48.25 | 0 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883330700 |  | 500145568 |  | G39 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | SR404 | SR404 | 153 | SAL | 2023-09-28 | U461383 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | OFFICE EXECUTE | 2023-09-28 |  |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 |  | 1
KY | KY - WEST | 2623 | 23026257100 |  | 501343462 |  | 6712228N | 2395343 | U126783 |  | 555 | EX | INSTALL 300'-2" PMMP | 2600B | AMERICAN | 135 AMERICAN PH | 209 | GEO | 2023-10-19 | U128132 | U126783 | 2023-02-14 | 2023-10-26 | 2023-11-01 | 2023-09-28 | JOSH PASLEY/STANLEY PIPELINE | 2023-09-28 | 2023-09-25 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2571 |  |  | 100 | 055532230262571 | 32 | 1600 | 68581.44 | 2235.56 | 1685.87 | 2083.36 | 43852.55 | 0 | 100.54 | 18623.56 | 400
KY | KY - WEST | 2621 | 23165287500 |  | 100294853 |  | 6716212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | UPPER | 415 N UPPER ST | 067 | LEX | 2023-09-28 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-09-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2266.84 | 0 | 0 | 0 | 2266.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166671000 |  | 100322617 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 717 BERRY LN | 067 | LEX | 2023-09-28 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-09-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1660.94 | 0 | 0 | 0 | 1660.94 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168130200 |  | 100459718 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | MAIN | 324 W MAIN ST | 073 | FRA | 2023-09-28 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-09-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2620.28 | 0 | 0 | 0 | 2620.28 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23214172900 |  | 100256069 |  | 7356256E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D244438 | 2621P | WOODLAND | 2501 WOODLAND AV | 019 | ASH | 2023-09-28 | JROGER1 | U135005 | 2023-09-12 | 2023-09-14 | 2023-10-02 |  | JROGER1 | 2023-09-28 | 2023-09-27 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 17.9167 | 3 | 1868.16 | 989.67 | 236.29 | 642.2 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23217449000 |  | 100294824 |  | 6716212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997801 | 2600B | UPPER | 428 N UPPER ST | 067 | LEX | 2023-09-28 | U126532 | U125763 | 2023-09-28 | 2023-12-29 |  |  | LESLIE SHARON | 2023-09-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3173.12 | 0 | 0 | 0 | 3173.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23217451900 |  | 100402282 |  | 6720208O |  |  |  | 565 | EX | GRADE 1 REPLACE S/L | 2621P | TWINBROOKE | 2661 TWINBROOKE LN | 067 | LEX | 2023-09-29 | U135005 | U129939 | 2023-09-28 | 2023-09-28 | 2023-09-28 |  | RSTRONG | 2023-09-28 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.0833 | 4 | 2681.88 | 1158.44 | 485.62 | 234.34 | 803.48 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23217466000 |  | 100275091 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WASHINGTON | 210 WASHINGTON ST | 073 | FRA | 2023-09-28 | U461375 | U125763 | 2023-09-28 | 2023-12-29 |  |  | LARRY BROWN | 2023-09-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2492.88 | 0 | 0 | 0 | 2492.88 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11884266900 |  | 100249336 |  | 7328284A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | JAMES HANNAH | JAMES HANNAH DR | 089 | S S | 2023-09-29 | RECUMP | U906307 | 2011-02-04 | 2023-09-18 | 2023-12-31 |  | RECUMP | 2023-09-29 | 2023-07-12 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.7167 | 2 | 1250.1 | 239.58 | 0 | 127.87 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883067100 |  | 100251830 |  | 7328284A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | HOLLY | 241 HOLLY AV | 089 | S S | 2023-10-02 | U135005 | U120245 | 2021-01-30 | 2023-09-25 | 2023-12-31 |  | RECUMP | 2023-09-29 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.85 | 1 | 229.7 | 124.12 | 0 | 105.58 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883082300 |  | 100242044 |  | 7344168G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | RIVERVIEW | 37 S RIVERVIEW LN | 071 | LNC | 2023-09-29 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN HOWARD | 2023-09-29 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.4333 | 1 | 182.14 | 172.68 | 0 | 9.46 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883139300 |  | 100245951 |  | 7328284A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | JAMES HANNAH | 3820 JAMES HANNAH DR | 089 | S S | 2023-09-29 | RECUMP | U120245 | 2021-01-30 | 2023-09-29 |  |  | RECUMP | 2023-09-29 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.4833 | 1 | 1181.27 | 161.35 | 0 | 137.27 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959269000 |  | 500707179 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | JENKINS | 200 JENKINS ST | 019 | ASH | 2023-09-29 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-09-29 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2601.84 | 0 | 0 | 0 | 2601.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129025900 |  | 100456076 |  | 7256280J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | TERRE HAUTE | 835 TERRE HAUTE DR | 161 | MAY | 2023-09-29 | SDADAMS | U130722 | 2022-09-05 | 2022-12-30 |  |  | SDADAMS | 2023-09-29 | 2022-11-28 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 28.2 | 7 | 2422.02 | 1970.57 | 81.14 | 115.31 | 255 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129033900 |  | 100408212 |  | 7356148T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LFT FORK TOLER | 454 LFT FORK TOLER CK | 071 | HAR | 2023-10-02 | U130172 | U130722 | 2022-09-05 | 2022-12-30 |  |  | BRIAN PREECE | 2023-09-29 | 2023-09-29 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 6 | 1 | 449.55 | 426.19 | 0 | 23.36 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166670700 |  | 100322647 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 712 BERRY LN | 067 | LEX | 2023-09-29 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-09-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2681.81 | 0 | 0 | 0 | 2681.81 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23204707400 |  | 100250163 |  | 7360248A | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | 36TH | 414 36TH ST | 019 | CAT | 2023-10-02 | U123965 | U125201 | 2023-07-28 | 2023-09-29 |  |  | CJH DEREK CRAGER | 2023-09-29 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3555.93 | 0 | 0 | 0 | 3555.93 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212654400 |  | 100322824 |  | 6716208H | 2399728 |  |  | 565 | EX | SERVICE LINE/METER UPGRADE | 2621P | SUMMIT | 1252 SUMMIT DR | 067 | LEX | 2023-09-29 | JOCHOA | U135005 | 2023-09-01 | 2023-10-02 | 2023-10-02 |  | JOCHOA | 2023-09-29 | 2023-09-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 41.4167 | 9 | 6096.86 | 2975.46 | 414.82 | 467.93 | 2238.65 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23213475200 |  | 100275818 |  | 6684228C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | AUDUBON | 119 AUDUBON DR | 073 | FRA | 2023-09-29 | MCRAIG | AOC SYST | 2023-09-07 | 2024-03-07 | 2024-12-31 |  | MCRAIG | 2023-09-29 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 32 | 4 | 3440.08 | 2278.92 | 529.31 | 631.85 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23215050500 |  | 100321595 |  | 6716212P |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | EUCLID | 545 E EUCLID AV | 067 | LEX | 2023-09-29 | HMCKUNE | U133234 | 2023-09-15 | 2023-09-29 | 2023-10-15 |  | HMCKUNE | 2023-09-29 | 2023-09-29 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 21.4 | 3 | 1617.24 | 1144.38 | 1.11 | 62.75 | 409 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23215335600 |  | 100450501 |  | 6724208M |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | EAGLE CREEK | 193 S EAGLE CREEK DR | 067 | LEX | 2023-09-29 | RSTRONG | U133234 | 2023-09-18 | 2023-09-29 | 2023-10-15 |  | RSTRONG | 2023-09-29 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.4 | 3 | 1050.02 | 833.71 | 37.51 | 178.8 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23216833700 |  | 100346568 |  | 6696212P |  |  |  | 565 | EX | GRADE 1 REPLACE S/L | 2621P | DUELL | 429 DUELL DR | 239 | VER | 2023-10-02 | U126332 | U129939 | 2023-09-25 | 2023-09-25 | 2023-09-25 |  | BWHITE | 2023-09-29 | 2023-09-26 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 2 | 822.27 | 566.92 | 224.24 | 31.11 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23217655500 |  | 100303857 |  | 6712208D |  |  |  | 565 | EX | REPLACE SL | 2621P | LARKSPUR | 2053 LARKSPUR DR | 067 | LEX | 2023-09-29 | LSTONE | U138551 | 2023-09-28 | 2023-09-28 | 2023-09-28 |  | LSTONE | 2023-09-29 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.4667 | 2 | 1178.96 | 898.62 | 231.07 | 49.27 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23218012700 |  | 100330526 |  | 6728212P |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | ROYSTER | 3887 ROYSTER RD | 067 | LEX | 2023-10-02 | U135005 | U134852 | 2023-09-29 | 2023-09-18 | 2023-10-06 |  | LSTANFI | 2023-09-29 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.4667 | 2 | 700.78 | 182.94 | 474.79 | 43.05 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12990765800 |  | 100316081 | 42 | 16716208F |  |  |  | 565 | EX | REPLACE SERV LINE / MOVE MTR | 2621P | ROSEMONT GD | 225 ROSEMONT GD | 067 | LEX | 2023-10-02 | KKINDER | RSTOKLE | 2012-09-27 | 2012-12-31 |  |  | KKINDER | 2023-10-02 | 2023-07-31 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.6 | 8 | 1575.19 | 1252.76 | 222.76 | 99.67 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959265200 |  | 100261061 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | 6TH | 2319 6TH ST | 019 | ASH | 2023-10-02 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-02 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2594.1 | 0 | 0 | 0 | 2594.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960883300 |  | 100250233 |  | 7360248A | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | 36TH | 435 36TH ST | 019 | CAT | 2023-10-03 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-10-02 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3853.1 | 0 | 0 | 0 | 3853.1 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129033700 |  | 100423117 |  | 7348144T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KY ROUTE 680 | 4375 KY ROUTE 680 | 071 | GRE | 2023-10-03 | U130172 | U130722 | 2022-09-05 | 2022-12-30 |  |  | BRIAN PREECE | 2023-10-02 | 2023-10-02 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 7.2833 | 1 | 448.64 | 421.88 | 0 | 26.76 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129033800 |  | 100256603 |  | 7356152E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FIRST | 92 FIRST ST | 071 | HAR | 2023-10-02 | JAHOWARD | U130722 | 2022-09-05 | 2022-12-30 |  |  | JAHOWARD | 2023-10-02 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 6.4167 | 1 | 1280.14 | 373.8 | 0 | 23.69 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129034000 |  | 100256482 |  | 7356152E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | US RT 23 | 12260 US RT 23 S | 071 | HAR | 2023-10-02 | JAHOWARD | U130722 | 2022-09-05 | 2022-12-30 |  |  | JAHOWARD | 2023-10-02 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 6.0833 | 1 | 1256.73 | 351.77 | 0 | 22.31 | 882.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165282400 |  | 100441963 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | LIMESTONE | 359 N LIMESTONE ST | 067 | LEX | 2023-10-02 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-10-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4 | 1 | 3611.28 | 232.87 | 0 | 269.07 | 3109.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165288500 |  | 100294847 |  | 6716212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | UPPER | 439 N UPPER ST | 067 | LEX | 2023-10-02 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-10-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.5167 | 1 | 3705.8 | 322.52 | 0 | 372.64 | 3010.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166671500 |  | 100322614 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 729 BERRY LN | 067 | LEX | 2023-10-02 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-10-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2847.95 | 0 | 0 | 0 | 2847.95 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168130400 |  | 100275083 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | MAIN | 331 W MAIN ST | 073 | FRA | 2023-10-02 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-10-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3176.45 | 0 | 0 | 0 | 3176.45 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168131200 |  | 100275101 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | PETTICOAT | 1 PETTICOAT LN | 073 | FRA | 2023-10-02 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-10-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3195.13 | 0 | 0 | 0 | 3195.13 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23206210000 |  | 100347276 |  | 6696212L | 1855043 |  |  | 566 | EX | ABANDON SL - SOII/INSIDE | 2621P | COURT | 110 S COURT ST | 239 | VER | 2023-10-04 | U128410 | U131897 | 2023-08-03 | 2023-12-29 | 2023-12-31 |  | CDESPAIN | 2023-10-02 | 2023-09-18 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 10.0333 | 3 | 634.45 | 597.75 | 0 | 36.7 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23206210100 |  | 100347277 |  | 6696212L | 1855043 |  |  | 566 | EX | ABANDON SL - SOII/MANIFOLD | 2621P | COURT | 110 S COURT ST 2F | 239 | VER | 2023-10-04 | U128410 | U131897 | 2023-08-03 | 2023-12-29 | 2023-12-31 |  | CDESPAIN | 2023-10-02 | 2023-09-18 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 18.6333 | 4 | 1197.17 | 1127.29 | 0 | 69.88 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23209055900 |  | 100467256 |  | 6688228A |  |  |  | 565 | VO | REPLACE SERVICE LINE - D332980 | 2621P | COLONIAL | 626 COLONIAL TC | 073 | FRA | 2023-10-04 | U135005 | U135005 | 2023-08-17 | 2024-02-16 | 2025-08-31 |  | EFGOINS | 2023-10-02 |  |  | A | [11 empty] | 23218946000 | 100 |  |  | 1 | 1256.37 | 1181.46 | 0 | 74.91 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23211320200 |  | 100340256 |  | 6720212H | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | RALEIGH | 1804 RALEIGH RD | 067 | LEX | 2023-10-03 | U135005 | AOC SYST | 2023-08-28 | 2024-12-31 | 2024-12-31 |  | LSTANFI | 2023-10-02 | 2023-09-25 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 16.5333 | 3 | 1843.94 | 952.95 | 602.69 | 288.3 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212718900 |  | 100340133 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | HI CREST | 708 HI CREST DR | 067 | LEX | 2023-10-02 | WISHII | AOC SYST | 2023-09-01 | 2024-03-01 | 2024-12-31 |  | WISHII | 2023-10-02 | 2023-09-26 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 12.5167 | 3 | 1490.38 | 756.87 | 328.59 | 404.92 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23213471300 |  | 100275810 |  | 6684228C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | AUDUBON | 108 AUDUBON DR | 073 | FRA | 2023-10-02 | MCRAIG | AOC SYST | 2023-09-07 | 2024-03-07 | 2024-12-31 |  | MCRAIG | 2023-10-02 | 2023-09-28 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 22.4667 | 3 | 2519.91 | 1337.85 | 539.59 | 642.47 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23214689100 |  | 100351512 |  | 6744208P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333743 | 2621P | GARNER | 34 GARNER ST | 049 | WIN | 2023-10-03 | JTOY | U135005 | 2023-09-14 | 2024-03-13 | 2025-09-30 |  | NRICHIE | 2023-10-02 | 2023-09-29 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 33.9833 | 7 | 2948.06 | 2073.88 | 255.11 | 619.07 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23217049100 |  | 501119870 |  | 7344264A |  |  |  | 566 | EX | ABANDON SL - CUSTRQD | 2621P | CAROLINE | 210 CAROLINE AV | 089 | WUR | 2023-10-02 | ABHATFIE | U135005 | 2023-09-26 | 2023-10-26 | 2023-10-26 |  | ABHATFIE | 2023-10-02 | 2023-10-02 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 7.5833 | 2 | 967.82 | 750.89 | 0 | 216.93 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23218004700 |  | 100440579 |  | 6720208P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D310339 | 2621P | CEDARCREST | 2949 CEDARCREST DR | 067 | LEX | 2023-10-03 | UIPBOT16 | U135005 | 2023-09-29 | 2023-10-02 | 2023-10-20 |  | TROE | 2023-10-02 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.0333 | 2 | 777.97 | 651.58 | 85.11 | 41.28 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959274900 |  | 100261059 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | 6TH | 2315 6TH ST | 019 | ASH | 2023-10-03 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-03 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1940.09 | 0 | 0 | 0 | 1940.09 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959275200 |  | 100261071 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | CEDAR | 2221 CEDAR ST | 019 | ASH | 2023-10-23 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-03 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2770.79 | 0 | 0 | 0 | 2770.79 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960853700 |  | 100250234 |  | 7360248A | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | CEMETERY | 8514 CEMETERY RD | 019 | CAT | 2023-10-04 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-10-03 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2565.33 | 0 | 0 | 0 | 2565.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165287900 |  | 100294851 |  | 6716212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | UPPER | 423 N UPPER ST | 067 | LEX | 2023-10-03 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-10-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.75 | 1 | 3562.04 | 218.29 | 0 | 252.24 | 3091.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165288300 |  | 100294848 |  | 6716212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | UPPER | 437 N UPPER ST | 067 | LEX | 2023-10-03 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-10-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.7667 | 1 | 3535.59 | 278.27 | 0 | 321.51 | 2935.81 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166672000 |  | 100322611 |  | 6720208A | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 741 BERRY LN | 067 | LEX | 2023-10-03 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-10-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2199.2 | 0 | 0 | 0 | 2199.2 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168130000 |  | 100275116 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | MAIN | 320 W MAIN ST | 073 | FRA | 2023-10-03 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-10-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2330.22 | 0 | 0 | 0 | 2330.22 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23175053400 |  | 100345655 |  | 6696212D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D305598 | 2621P | LOY | 110 LOY ST | 239 | VER | 2023-10-03 | U128410 | U125208 | 2023-03-20 | 2023-09-15 | 2025-03-31 |  | CDESPAIN | 2023-10-03 | 2023-09-18 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 35.5667 | 6 | 8201.97 | 2203.38 | 3909.74 | 219.53 | 1869.32 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23182453300 |  | 100278244 |  | 6688228B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332758 | 2621P | COMANCHE | 517 COMANCHE TL | 073 | FRA | 2023-10-04 | U135005 | U125208 | 2023-04-19 | 2023-10-17 | 2025-04-30 |  | EFGOINS | 2023-10-03 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 24 | 3 | 1571.65 | 1181.46 | 315.28 | 74.91 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23211313200 |  | 100340402 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | RALEIGH | 1626 RALEIGH RD | 067 | LEX | 2023-10-04 | U135005 | AOC SYST | 2023-08-28 | 2024-12-31 | 2024-12-31 |  | LSTANFI | 2023-10-03 | 2023-09-25 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 14.35 | 4 | 1575.26 | 789.14 | 603.21 | 182.91 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23211318800 |  | 100340249 |  | 6720212H | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | RALEIGH | 1836 RALEIGH RD | 067 | LEX | 2023-10-04 | U135005 | AOC SYST | 2023-08-28 | 2024-12-31 | 2024-12-31 |  | LSTANFI | 2023-10-03 | 2023-09-25 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 11.7333 | 4 | 1382.69 | 646.09 | 602.69 | 133.91 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23216181700 |  | 100319528 |  | 6716208L | 2399937 |  |  | 565 | EX | SERVICE LINE UPGRADE - 2"PMLP | 2621P | GREENBRIAR | 416 GREENBRIAR RD | 067 | LEX | 2023-10-03 | U128336 | U132761 | 2023-09-20 | 2023-10-17 | 2023-10-17 |  | JOSHUA COX | 2023-10-03 | 2023-09-26 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 42.5 | 7 | 4642 | 2147.87 | 1896.08 | 598.05 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23216249900 |  | 100261595 |  | 7352256H |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | CYPRESS | 1501 CYPRESS ST | 019 | ASH | 2023-10-04 | U135005 | U133234 | 2023-09-21 | 2023-10-04 | 2023-10-20 |  | RECUMP | 2023-10-03 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 10.8333 | 2 | 802.29 | 585.87 | 20.27 | 196.15 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 10841473100 |  | 500053136 |  | V-921/42 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MACK | 116 MACK ST | 239 | VER | 2023-10-10 | U135005 | RPOLLY | 2010-05-20 | 2020-12-31 |  |  | CDESPAIN | 2023-10-04 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 16 | 2 | 995.76 | 936.41 | 0 | 59.35 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959266200 |  | 100261076 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | CEDAR | 2216 CEDAR ST | 019 | ASH | 2023-10-04 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-04 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3343.43 | 0 | 0 | 0 | 3343.43 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026231200 |  | 501337786 |  | 6696212P | 2292756 | U126783 |  | 555 | EX | INSTALL 1870'-2"/4" PMMP | 2600B | SAFFRON | SAFFRON LN LT19 | 239 | VER | 2023-12-20 | U128132 | U126783 | 2022-10-12 | 2023-09-11 | 2023-10-30 | 2023-10-03 | R.HUMPHREYS | 2023-10-04 | 2023-09-05 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2312 |  |  | 100 | 055532220262312 | 169.5 | 41727 | 89157.03 | 11225.95 | 5505.53 | 2258.58 | 46358.27 | 0 | 620.2 | 23188.5 | 1987
KY | KY - WEST | 2623 | 23026294600 |  |  |  | 6696212P | 2292756 | U126783 |  | 562 | EX | ABANDON ~790'-2" PMMP | 2600B | SAFFRON | SAFFRON LN | 239 | VER | 2023-12-20 | U128132 | U126783 | 2023-09-15 | 2023-12-29 | 2023-12-31 | 2023-10-03 | R. HUMPREYS | 2023-10-04 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00562 | 3200562 |  |  | WP2946 |  |  | 100 | 056232230262946 |  | 0 | 392.35 | 0 | 392.35 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23158487500 |  | 100252536 |  | 7348264P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D259792 | 2621P | POTTER | 1609 POTTER ST | 089 | FLA | 2023-10-04 | MCOLLET | U125208 | 2023-01-25 | 2023-07-24 | 2025-01-31 |  | MCOLLET | 2023-10-04 | 2023-10-03 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 16.5 | 3 | 3103.57 | 977.18 | 359.28 | 1767.11 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165288000 |  | 100294821 |  | 6716212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | UPPER | 424 N UPPER ST | 067 | LEX | 2023-10-04 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-10-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3 | 1 | 2710.76 | 176.4 | 0 | 203.8 | 2330.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165290300 |  | 100294815 |  | 6716212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | UPPER | 406 N UPPER ST | 067 | LEX | 2023-10-04 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-10-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.5167 | 1 | 2619.48 | 262 | 0 | 302.7 | 2054.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166671200 |  | 100322650 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 724 BERRY LN | 067 | LEX | 2023-10-04 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-10-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1581.87 | 0 | 0 | 0 | 1581.87 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23196735500 |  | 100271331 |  | 6736252N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D412207 | 2621P | OXLEY | 101 OXLEY AV | 097 | CYN | 2023-10-04 | U930915 | U135005 | 2023-06-23 | 2023-12-21 | 2025-06-30 |  | ASNICHO | 2023-10-04 | 2023-10-03 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 6.85 | 1 | 992.24 | 392.25 | 140.29 | 459.7 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23205012400 |  | 100337664 |  | 6720212E |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | M L KING | 636 M L KING BV | 067 | LEX | 2023-10-04 | U930915 | U135005 | 2023-07-31 | 2023-12-29 |  |  | RSTRONG | 2023-10-04 | 2023-08-21 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 22.25 | 7 | 2867.51 | 1039.01 | 0 | 213.6 | 1614.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23211311400 |  | 100340269 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | RALEIGH | 1754 RALEIGH RD | 067 | LEX | 2023-10-05 | U138038 | AOC SYST | 2023-08-28 | 2024-12-31 | 2024-12-31 |  | LSTANFI | 2023-10-04 | 2023-09-25 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 11.6667 | 4 | 971 | 602.04 | 211.87 | 157.09 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212715800 |  | 100340134 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | HI CREST | 712 HI CREST DR | 067 | LEX | 2023-10-04 | WISHII | AOC SYST | 2023-09-01 | 2024-03-01 | 2024-12-31 |  | WISHII | 2023-10-04 | 2023-09-26 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 11.95 | 3 | 1108.56 | 651.25 | 0 | 457.31 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212717600 |  | 100340142 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | HI CREST | 724 HI CREST DR A | 067 | LEX | 2023-10-04 | WISHII | AOC SYST | 2023-09-01 | 2024-12-31 | 2024-12-31 |  | WISHII | 2023-10-04 | 2023-09-26 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 5.3167 | 3 | 370.13 | 289.79 | 0 | 80.34 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23213718000 |  | 100275814 |  | 6684228C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | AUDUBON | 103 AUDUBON DR | 073 | FRA | 2023-10-04 | MCRAIG | AOC SYST | 2023-09-08 | 2024-12-31 | 2024-12-31 |  | MCRAIG | 2023-10-04 | 2023-09-20 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 28.95 | 8 | 3728.45 | 1735.64 | 617.05 | 1375.76 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23214154600 |  | 100277685 |  | 6688228E |  |  |  | 566 | EX | ABN SL - NON COMPLIANT | 2621P | BRADLEY | 714 BRADLEY ST | 073 | FRA | 2023-10-04 | EFGOINS | U127297 | 2023-09-12 | 2023-11-01 | 2023-11-01 |  | EFGOINS | 2023-10-04 | 2023-10-04 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 14.2667 | 3 | 756.01 | 710.95 | 0 | 45.06 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23216766300 |  | 100321812 |  | 6716208D |  |  |  | 566 | EX | ABANDON SL - DEMO/CITYRQD | 2621P | COLUMBIA | 560 COLUMBIA AV | 067 | LEX | 2023-10-04 | U128336 | U135005 | 2023-09-25 | 2023-11-22 | 2023-11-25 |  | JOSHUA COX | 2023-10-04 | 2023-10-02 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.75 | 4 | 782.78 | 700.35 | 38.01 | 44.42 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23217970600 |  | 500905627 |  | 6724204H | 0355499 |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | JANE BRIGGS | 256 JANE BRIGGS AV | 067 | LEX | 2023-10-04 | TROE | U133234 | 2023-09-29 | 2023-10-12 | 2023-10-28 |  | TROE | 2023-10-04 | 2023-10-04 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9 | 2 | 556.36 | 502.54 | 21.97 | 31.85 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23218756300 |  | 100402283 |  | 6720208O |  |  |  | 565 | EX | 24HR GAS OFF RPLC SL D341411 | 2621P | QUINCY | 2690 QUINCY CT | 067 | LEX | 2023-10-05 | U138038 | U135005 | 2023-10-03 | 2023-10-03 | 2023-10-03 |  | LSTANFI | 2023-10-04 | 2023-10-04 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.7833 | 2 | 1363.88 | 606.2 | 558.78 | 198.9 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23218761000 |  | 100329046 |  | 6720208O | 1635077 |  |  | 565 | EX | GRD 1 GAS OFF | 2621P | QUINCY | 2692 QUINCY CT | 067 | LEX | 2023-10-04 | HMCKUNE | U130871 | 2023-10-03 | 2023-10-03 | 2023-10-03 |  | HMCKUNE | 2023-10-04 | 2023-10-04 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.4333 | 2 | 1240.73 | 669.55 | 528.75 | 42.43 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883157400 |  | 100256458 |  | 7352152D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | BOYD | BOYD ST | 071 | HAR | 2023-10-05 | JAHOWARD | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JAHOWARD | 2023-10-05 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.15 | 1 | 1015.36 | 124.8 | 0 | 7.91 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959266000 |  | 100261072 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | CEDAR | 2211 CEDAR ST | 019 | ASH | 2023-10-05 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-05 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2170.91 | 0 | 0 | 0 | 2170.91 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960851600 |  | 100250172 |  | 7360248A | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | 36TH | 434 36TH ST | 019 | CAT | 2023-10-05 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-10-05 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2267.28 | 0 | 0 | 0 | 2267.28 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168130100 |  | 100275080 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | MAIN | 321 W MAIN ST | 073 | FRA | 2023-10-05 | U461375 | U125763 | 2023-02-20 | 2023-12-29 |  |  | LARRY BROWN | 2023-10-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2251.82 | 0 | 0 | 0 | 2251.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23194286500 |  | 100333066 |  | 6720212I | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | WILSON | 329 WILSON ST 1 | 067 | LEX | 2023-10-05 | TROE | AOC SYST | 2023-06-12 | 2023-12-12 | 2024-12-31 |  | TROE | 2023-10-05 | 2023-09-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 32.9 | 10 | 2917.55 | 1816.68 | 847.76 | 253.11 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23208647900 |  | 100422013 |  | 6688228A |  |  |  | 565 | EX | REPLACE SERVICE LINE - D221443 | 2621P | WILLIAMSBURG | 570 WILLIAMSBURG RD | 073 | FRA | 2023-10-06 | U135005 | U135005 | 2023-08-16 | 2024-02-15 | 2025-08-31 |  | EFGOINS | 2023-10-05 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 24 | 3 | 1256.37 | 1181.46 | 0 | 74.91 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23213397500 |  | 100338611 |  | 6720212F |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | YORK | 207 YORK ST | 067 | LEX | 2023-10-05 | WISHII | U133234 | 2023-09-07 | 2023-09-21 | 2023-10-07 |  | WISHII | 2023-10-05 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.2333 | 3 | 806.28 | 510.13 | 0 | 296.15 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23216765700 |  | 100321811 |  | 6716208D |  |  |  | 566 | EX | ABANDON SL - DEMO/CITYRQD | 2621P | COLUMBIA | 556 COLUMBIA AV | 067 | LEX | 2023-10-05 | U128336 | U135005 | 2023-09-25 | 2023-11-22 | 2023-11-25 |  | JOSHUA COX | 2023-10-05 | 2023-10-02 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 25.75 | 5 | 1382.59 | 1185.72 | 121.68 | 75.19 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23218746500 |  | 100275092 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WASHINGTON | 212 WASHINGTON ST BSM | 073 | FRA | 2023-10-05 | U461375 | U131066 | 2023-10-03 | 2023-12-29 |  |  | LARRY BROWN | 2023-10-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3089.28 | 0 | 0 | 0 | 3089.28 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23218936900 |  | 100307676 |  | 6716212K |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | MERINO | 347 MERINO ST 1FL | 067 | LEX | 2023-10-05 | KKINDER | U135005 | 2023-10-04 | 2023-11-03 | 2023-11-04 |  | KKINDER | 2023-10-05 | 2023-10-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 30 | 3 | 3355.94 | 1686.69 | 347.51 | 106.9 | 1214.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 09809415400 |  | 100441727 |  | V00000000 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HOLMES | 418 HOLMES ST 2 | 073 | FRA | 2023-10-09 | U930915 | RPOLLY | 2009-10-27 | 2020-12-23 |  |  | EFGOINS | 2023-10-06 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 12.45 | 3 | 944.58 | 609.91 | 0 | 38.67 | 296 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883060200 |  | 501151397 |  | 7332132G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | HIGHWAY 899 | 6533 HIGHWAY 899 | 119 | PIP | 2023-10-09 | U135005 | U120245 | 2021-01-30 | 2023-10-06 | 2023-12-31 |  | JAHOWARD | 2023-10-06 | 2022-07-14 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 14.65 | 5 | 2003.45 | 910.29 | 0 | 54.75 | 1038.41 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959265800 |  | 100261073 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | CEDAR | 2201 CEDAR ST | 019 | ASH | 2023-10-06 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-06 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1865.95 | 0 | 0 | 0 | 1865.95 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959268700 |  | 100261084 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | HINTON | 143 HINTON AV | 019 | ASH | 2023-10-06 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-06 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1872.69 | 0 | 0 | 0 | 1872.69 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129034400 |  | 501167385 |  | 7352152 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SR2030 | 7206 SR2030 | 071 | HON | 2023-10-06 | JAHOWARD | U130722 | 2022-09-05 | 2022-12-30 |  |  | JAHOWARD | 2023-10-06 | 2023-10-05 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 6.6333 | 2 | 1883.74 | 384.8 | 0 | 24.39 | 1474.55 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026292501 |  |  |  | 6716212B | 1968251 | U134275 |  | 561 | EX | INSTALL 800' OF 2-4" PMMP | 2600B | LEESTOWN | 1500 LEESTOWN RD | 067 | LEX | 2024-04-10 | U136251 | U134275 | 2023-11-01 | 2023-10-18 | 2024-11-30 | 2023-10-06 | JOSH PASLEY | 2023-10-06 | 2023-10-04 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP2925 | AMRCB |  | 100 | 056132230262925 | 30.5 | 2382 | 232050.11 | 2864.91 | 7199.81 | 4048.09 | 138102.28 | 0 | 514.38 | 79320.64 | 794
KY | KY - WEST | 2623 | 23213479100 |  | 100275815 |  | 6684228C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | AUDUBON | 105 AUDUBON DR | 073 | FRA | 2023-10-06 | MCRAIG | AOC SYST | 2023-09-07 | 2024-03-07 | 2024-12-31 |  | MCRAIG | 2023-10-06 | 2023-10-05 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 9.6333 | 3 | 1419.02 | 564.63 | 525.3 | 329.09 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23216226600 |  | 100308431 |  | 6716212N |  |  |  | 566 | EX | ABANDON SL PER FOL MMCKUNE | 2621P | ADDISON | 705 ADDISON AV | 067 | LEX | 2023-10-06 | WISHII | U135005 | 2023-09-21 | 2023-11-21 | 2023-11-21 |  | WISHII | 2023-10-06 | 2023-10-05 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.8167 | 5 | 1082.81 | 786.91 | 0 | 295.9 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23219708500 |  | 100328518 |  | 6720208F |  |  |  | 565 | EX | GRADE 1 REPLACE | 2621P | BRISTOL | 429 BRISTOL RD | 067 | LEX | 2023-10-09 | U135005 | U129939 | 2023-10-05 | 2023-10-05 | 2023-10-05 |  | LSTANFI | 2023-10-06 | 2023-10-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.75 | 7 | 1594.24 | 1056.99 | 323 | 214.25 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23219945300 |  | 100276481 |  | 6684228H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HOLMES | 418 HOLMES ST 1FL | 073 | FRA | 2023-10-06 | EFGOINS | U134852 | 2023-10-06 | 2023-10-06 |  |  | EFGOINS | 2023-10-06 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26230043 | 3.05 | 3 | 157.09 | 147.7 | 0 | 9.39 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23219945500 |  | 100441728 |  | 6684228H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HOLMES | 418 HOLMES ST 2F3 | 073 | FRA | 2023-10-06 | EFGOINS | U134852 | 2023-10-06 | 2023-10-06 |  |  | EFGOINS | 2023-10-06 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26230043 | 4.05 | 3 | 212.11 | 199.41 | 0 | 12.7 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883129700 |  | 100246171 |  | 7372188L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | FLOYD | FLOYD ST | 159 | WAR | 2023-10-09 | JAHOWARD | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JAHOWARD | 2023-10-09 | 2022-11-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.9833 | 2 | 1049.32 | 156.74 | 0 | 9.93 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883223600 |  | 100250593 |  | 7376184A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | MAPLE | MAPLE ST | 159 | LOV | 2023-10-09 | JAHOWARD | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JAHOWARD | 2023-10-09 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.8833 | 1 | 1124.62 | 227.55 | 0 | 14.42 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883225500 |  | 100250584 |  | 7376184A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | WALNUT | WALNUT ST | 159 | LOV | 2023-10-09 | JAHOWARD | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JAHOWARD | 2023-10-09 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.4 | 1 | 967.84 | 80.11 | 0 | 5.08 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883234900 |  | 100253527 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | INE | 2023-10-09 | U130172 | U120245 | 2021-01-30 | 2023-10-05 |  |  | JOHN KIRK | 2023-10-09 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.35 | 1 | 20.88 | 19.63 | 0 | 1.25 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883247600 |  | 100253360 |  | 7360196T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | JOB | 2023-10-09 | U130172 | U120245 | 2021-01-30 | 2023-10-05 | 2023-12-31 |  | JOHN KIRK | 2023-10-09 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.98333 | 1 | 58.44 | 54.95 | 0 | 3.49 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959264900 |  | 100261080 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | 6TH | 2305 6TH ST | 019 | ASH | 2023-10-09 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2615.32 | 0 | 0 | 0 | 2615.32 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960851800 |  | 100250177 |  | 7356248D | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | 36TH | 442 36TH ST | 019 | CAT | 2023-10-10 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-10-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2721.24 | 0 | 0 | 0 | 2721.24 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22118792900 |  | 100260690 |  | 7352256K |  |  |  | 566 | EX | ABANDN SL/LGCY | 2621P | GALLOWAY | 2134 GALLOWAY ST | 019 | ASH | 2023-10-09 | RECUMP | U125763 | 2022-07-27 | 2022-09-19 |  |  | RECUMP | 2023-10-09 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 9.4 | 2 | 4149.01 | 512.11 | 0 | 171.46 | 3465.44 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129120500 |  | 100427751 |  | 7376184T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WOLF CREEK | 3901 N WOLF CREEK RD | 159 | LOV | 2023-10-09 | U130172 | U125208 | 2022-09-06 | 2022-12-30 |  |  | JOHN KIRK | 2023-10-09 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.9333 | 1 | 235.46 | 221.44 | 0 | 14.02 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165287200 |  | 100424349 |  | 6716212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | UPPER | 402 N UPPER ST 2 | 067 | LEX | 2023-10-09 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-10-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.9667 | 1 | 6408.92 | 580.99 | 0 | 36.85 | 5791.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165288600 |  | 100294827 |  | 6716212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | UPPER | 444 N UPPER ST | 067 | LEX | 2023-10-09 | U461443 | U125763 | 2023-02-07 | 2023-09-09 | 2025-03-31 |  | WGRAVES | 2023-10-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3070.33 | 7.98 | 0 | 8.42 | 3053.93 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166671400 |  | 100322651 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 728 BERRY LN | 067 | LEX | 2023-10-09 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-10-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1962.05 | 0 | 0 | 0 | 1962.05 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212038700 |  | 100339408 |  | 4 AUGUSTA | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | AUGUSTA | 1960 AUGUSTA DR | 067 | LEX | 2023-10-10 | U135005 | AOC SYST | 2023-08-30 | 2024-02-29 | 2024-12-31 |  | LSTANFI | 2023-10-09 | 2023-10-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 15.55 | 3 | 1959.44 | 973.29 | 602.69 | 383.46 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212876900 |  | 100338609 |  | 6720212F |  |  |  | 566 | EX | ABN SL - NON COMPLIANT | 2621P | YORK | 209 YORK ST | 067 | LEX | 2023-10-09 | ABLAKE | U127297 | 2023-09-05 | 2023-11-01 | 2023-11-01 |  | ABLAKE | 2023-10-09 | 2023-10-06 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.0667 | 3 | 672.86 | 615.68 | 18.15 | 39.03 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23213472100 |  | 100275813 |  | 6684228C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | AUDUBON | 102 AUDUBON DR | 073 | FRA | 2023-10-09 | MCRAIG | AOC SYST | 2023-09-07 | 2024-03-08 | 2025-09-30 |  | MCRAIG | 2023-10-09 | 2023-09-20 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 | KYACA |  | 100 | 056532B26230021 | 21.4 | 6 | 2697.04 | 1276.6 | 379.25 | 1041.19 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23215902600 |  | 100325627 |  | 6720208J |  |  |  | 566 | EX | ABANDON SL - CITY DEMO | 2621P | LAKEWOOD | 1742 LAKEWOOD LN | 067 | LEX | 2023-10-09 | RSTRONG | U135005 | 2023-09-20 | 2023-10-20 | 2023-10-20 |  | RSTRONG | 2023-10-09 | 2023-10-09 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.15 | 2 | 1015.59 | 721.31 | 38.01 | 256.27 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23218013200 |  | 100281154 |  | 6692224J |  |  |  | 565 | EX | SERVICE LINE UPGRADE | 2621P | SHADY | 707 SHADY LN | 239 | MID | 2023-10-10 | U135005 | U135005 | 2023-09-29 | 2023-10-13 | 2023-10-13 |  | EFGOINS | 2023-10-09 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26230031 | 19.4167 | 3 | 2175.57 | 952.81 | 1162.36 | 60.4 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23218733400 |  | 100340195 |  | 6720212H |  |  |  | 565 | EX | RPLC SL AND RISER - POT. HAZ | 2621P | RALEIGH | 1831 RALEIGH RD | 067 | LEX | 2023-10-09 | U128336 | U135005 | 2023-10-03 | 2023-12-01 | 2023-12-03 |  | JOSHUA COX | 2023-10-09 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.4833 | 2 | 1339.71 | 1059.02 | 213.56 | 67.13 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23220169700 |  | 100339409 |  | 6724212E |  |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621P | AUGUSTA | 1964 AUGUSTA DR | 067 | LEX | 2023-10-10 | U135005 | U132928 | 2023-10-09 | 2023-10-09 |  |  | LSTANFI | 2023-10-09 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 1.4 | 2 | 471.75 | 81.56 | 364.42 | 25.77 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 17514926900 |  | 100313389 |  | 6716208B |  |  |  | 565 | EX | REPL/MOVE MTR - 15' UNMTRD GAS | 2621P | BOB O LINK | 472 BOB O LINK DR | 067 | LEX | 2023-10-10 | KKINDER | U125208 | 2017-06-13 | 2017-07-10 |  |  | KKINDER | 2023-10-10 | 2023-07-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 31.0833 | 10 | 2124.4 | 1761.11 | 229.27 | 134.02 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883073600 |  | 100260548 |  | 7352140T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | LEFT FK MINK | 44 LEFT FK MINK BR | 071 | HAR | 2023-10-10 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BRIAN PREECE | 2023-10-10 | 2023-09-20 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 10.2167 | 2 | 680.38 | 643.54 | 0 | 36.84 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883074600 |  | 100246297 |  | 7372188N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | BEAUTY | 7401 BEAUTY | 159 | BEA | 2023-10-10 | JAHOWARD | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JAHOWARD | 2023-10-10 | 2022-11-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 16.4833 | 5 | 4569.52 | 1097.43 | 0 | 123.12 | 3348.97 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129012200 |  | 100260495 |  | 7340144T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | STEELE CREEK | STEELE CREEK | 071 | WAY | 2023-10-10 | U130172 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JOHN HOWARD | 2023-10-10 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - EAST | 2633 | 22979045300 |  | 100424014 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | INE | 2023-10-10 | U130172 | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | JOHN KIRK | 2023-10-10 | 2023-10-10 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.68333 | 1 | 40.56 | 38.15 | 0 | 2.41 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22986760700 |  | 100267295 |  | 7352260E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | PINE GROVE | 606 PINE GROVE CT | 089 | ASH | 2023-10-10 | BROBERT | U134852 | 2022-03-17 | 2022-03-17 |  |  | BROBERT | 2023-10-10 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 6.5333 | 2 | 645.61 | 555.81 | 0 | 89.8 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026299900 |  | 500253895 |  | 7356256B | 2394672 | U461383 |  | 565 | EX | PAPER ONLY SL REPLACEMENT | 2600E | MONTGOMERY | 2236 MONTGOMERY AV | 019 | ASH | 2023-10-18 | U128132 | U461383 | 2023-10-10 | 2023-12-01 | 2023-12-01 | 2023-06-12 | DSKAGGS | 2023-10-10 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP2999 |  |  | 100 | 056532230262999 |  | 1 | 1201.76 | 559.92 | 0 | 322.79 | 0 | 0 | 0 | 319.05
KY | KY - EAST | 2631 | 23026300000 |  |  |  | 7352260K | 2294088 | U461383 |  | 909 | EX | INSTALL NEW EQUIPMENT | 2631M | FRENCH BROAD | 1403 FRENCH BROAD | 019 | ASH | 2024-02-05 | U123258 | U461383 | 2023-10-10 | 2024-05-31 | 2024-06-01 | 2023-10-10 | DASH | 2023-10-10 |  |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP3000 |  |  | 100 | 090932230263000 | 7.0167 | 0 | 570.56 | 542.83 | 0 | 27.73 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026300800 |  |  |  | 6720212I | 2300982 | U461383 |  | 557 | EX | EMER-INSTALL 5' OF 3"PMLP | 2621P | OHIO | 436 OHIO ST | 067 | LEX | 2023-12-15 | U136251 | U461383 | 2023-10-16 | 2023-10-10 | 2023-10-10 | 2023-10-10 | HMCKUNE | 2023-10-10 | 2023-10-27 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3008 |  |  | 100 | 055732230263008 | 0.68333 | 5 | 5351.34 | 3073.41 | 191.48 | 194.76 | 0 | 0 | 12.6 | 1879.09 | 5
KY | KY - WEST | 2621 | 23026300900 |  |  |  | 6720212I | 2300982 | U461383 |  | 558 | EX | EMER-RETIRE 5' OF 3"PLP MAIN | 2621P | OHIO | 436 OHIO ST | 067 | LEX | 2023-11-21 | U136251 | U461383 | 2023-10-16 | 2023-10-10 | 2023-10-10 | 2023-10-10 | RVANDERPOOL | 2023-10-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP3009 |  |  | 100 | 055832230263009 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165287400 |  | 100294854 |  | 6716212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | UPPER | 411 N UPPER ST 2 | 067 | LEX | 2023-10-10 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-10-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 6082.26 | 0 | 0 | 0 | 6082.26 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166671700 |  | 100322613 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 733 BERRY LN | 067 | LEX | 2023-10-10 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-10-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2539.53 | 0 | 0 | 0 | 2539.53 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168129500 |  | 100275124 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | MAIN | 306 W MAIN ST | 073 | FRA | 2023-10-11 | U461443 | U125763 | 2023-02-20 | 2023-12-29 |  |  | WGRAVES | 2023-10-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3808.54 | 0 | 0 | 0 | 3808.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23192220300 |  | 100323906 |  | 6716208P | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | BROOK HILL | 3314 BROOK HILL CR | 067 | LEX | 2023-10-10 | U128336 | AOC SYST | 2023-06-01 | 2023-12-01 | 2024-12-31 |  | JOSHUA COX | 2023-10-10 | 2023-10-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 19.8667 | 3 | 1782.83 | 1134.95 | 575.94 | 71.94 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23209809000 |  | 100435913 |  | 7356216K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | CARPET MILL | 9334 CARPET MILL RD | 127 | LOU | 2023-10-10 | RECUMP | U130722 | 2023-08-21 | 2023-12-29 | 2023-12-31 |  | RECUMP | 2023-10-10 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.35 | 1 | 29.69 | 18.22 | 0 | 11.47 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212647600 |  | 100340115 |  | 6724212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332993 | 2621P | COURTLAND | 1861 COURTLAND DR | 067 | LEX | 2023-10-11 | U135005 | U135005 | 2023-09-01 | 2024-02-29 | 2025-08-31 |  | LSTANFI | 2023-10-10 | 2023-10-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.1833 | 3 | 1514.86 | 877.03 | 372.44 | 265.39 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212799000 |  | 100328828 |  | 6720208F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332612 | 2621P | BLAIRMORE | 1961 BLAIRMORE RD | 067 | LEX | 2023-10-10 | U930915 | U135005 | 2023-09-05 | 2024-03-01 | 2025-09-30 |  | RJCRAWF | 2023-10-10 | 2023-10-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.9333 | 3 | 975.32 | 698.61 | 232.42 | 44.29 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23220421700 |  | 100311316 |  | 6712204C |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CARDIGAN | 625 CARDIGAN CT | 067 | LEX | 2023-10-10 | KOBRYAN | U131552 | 2023-10-10 | 2023-10-06 | 2023-10-25 |  | KOBRYAN | 2023-10-10 | 2023-10-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 6.0167 | 2 | 1030.43 | 624.17 | 366.72 | 39.54 | 0 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883083700 |  | 100440554 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | LEFT FK ABBOTT | 1675 LEFT FK ABBOTT CR | 071 | PRE | 2023-10-11 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-10-11 | 2023-10-11 |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 0.85 | 2 | 50.67 | 47.64 | 0 | 3.03 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883175100 |  | 100440425 |  | 7360148T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | L FORK ISLAND | 4416 L FORK ISLAND CK | 195 | PIK | 2023-10-11 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BRIAN PREECE | 2023-10-11 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.65 | 1 | 348.62 | 327.85 | 0 | 20.77 | 0 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883215700 |  | 100426870 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | LEFT FK ABBOTT | 1639 LEFT FK ABBOTT CR | 071 | PRE | 2023-10-11 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-10-11 | 2023-10-11 |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 1.8667 | 2 | 110.27 | 103.69 | 0 | 6.58 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883225300 |  | 100248009 |  | 7364188A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | MIDDLE FORK | MIDDLE FORK RD | 159 | INE | 2023-10-11 | JAHOWARD | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JAHOWARD | 2023-10-11 | 2022-11-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 9.0667 | 2 | 3277.61 | 509.07 | 0 | 32.28 | 2736.26 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959264300 |  | 100261148 |  | 7356252D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | 6TH | 2200 6TH ST | 019 | ASH | 2023-10-11 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1892.91 | 0 | 0 | 0 | 1892.91 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959264800 |  | 100261081 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | 6TH | 2221 6TH ST | 019 | ASH | 2023-10-12 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 4305.37 | 240.87 | 0 | 269.53 | 3794.97 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959265900 |  | 100261074 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | CEDAR | 2208 CEDAR ST | 019 | ASH | 2023-10-11 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1825.51 | 0 | 0 | 0 | 1825.51 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959266100 |  | 100261075 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | CEDAR | 2212 CEDAR ST | 019 | ASH | 2023-10-11 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 8055.9 | 0 | 0 | 0 | 8055.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960853000 |  | 100250228 |  | 7356248D | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | CEMETERY | 8232 CEMETERY RD | 019 | CAT | 2023-10-11 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-10-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2651.33 | 0 | 0 | 0 | 2651.33 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960853100 |  | 100250227 |  | 7356248D | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | CEMETERY | 8232 CEMETERY RD | 019 | CAT | 2023-10-11 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-10-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1
KY | KY - EAST | 2631 | 22110822500 |  | 100257195 |  | 7348264F | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | POND RUN | 79 POND RUN RD | 089 | RAC | 2023-10-11 | U123965 | U134723 | 2022-06-17 | 2023-12-29 |  |  | CJH CASEY PACK | 2023-10-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1984.72 | 0 | 0 | 0 | 1984.72 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129068500 |  | 100460850 |  | 7352260N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BELLEFONTE | 799 BELLEFONTE RD WW | 019 | ASH | 2023-10-11 | JROGER1 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JROGER1 | 2023-10-11 | 2023-10-11 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.5833 | 2 | 423.87 | 252.8 | 20.27 | 150.8 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165287100 |  | 100294859 |  | 6716212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | UPPER | 401 N UPPER ST | 067 | LEX | 2023-10-11 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-10-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.9167 | 1 | 2464.53 | 227.05 | 0 | 14.39 | 2223.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165288200 |  | 100294849 |  | 6716212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | UPPER | 429 N UPPER ST | 067 | LEX | 2023-10-11 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-10-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.0833 | 1 | 2569.79 | 180.47 | 0 | 11.44 | 2377.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168128900 |  | 100275131 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | MAIN | 226 W MAIN ST | 073 | FRA | 2023-10-12 | U461443 | U125763 | 2023-02-20 | 2023-12-29 |  |  | WGRAVES | 2023-10-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2963.76 | 0 | 0 | 0 | 2963.76 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168137500 |  | 100275049 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WAPPING | 410 WAPPING ST | 073 | FRA | 2023-10-12 | U461443 | U125763 | 2023-02-20 | 2023-12-29 |  |  | WGRAVES | 2023-10-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 4480.04 | 0 | 0 | 0 | 4480.04 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23175606900 |  | 100283538 |  | 6712228E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333575 | 2621P | HIAWATHA | 516 HIAWATHA TL | 209 | GEO | 2023-10-11 | DCOLLIN | U125208 | 2023-03-22 | 2023-09-20 | 2025-03-31 |  | DCOLLIN | 2023-10-11 | 2023-10-03 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 36.4 | 7 | 4680.13 | 2102 | 300.38 | 1251 | 1026.75 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23179954300 |  | 100278272 |  | 6688228B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332751 | 2621P | ARAPAHO | 1010 ARAPAHO TL | 073 | FRA | 2023-10-19 | U126332 | U125208 | 2023-04-10 | 2023-10-06 | 2025-04-30 |  | EFGOINS | 2023-10-11 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 23.4 | 3 | 1683.85 | 1078.3 | 0 | 605.55 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23192218200 |  | 100323907 |  | 6716208P | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | BROOK HILL | 3310 BROOK HILL CR | 067 | LEX | 2023-10-11 | U128336 | AOC SYST | 2023-06-01 | 2023-12-01 | 2024-12-31 |  | JOSHUA COX | 2023-10-11 | 2023-10-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 22.6167 | 4 | 1823.31 | 1289.16 | 452.45 | 81.7 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23192765200 |  | 100323859 |  | 6716208P | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | BROOK HILL | 820 BROOK HILL DR | 067 | LEX | 2023-10-11 | ABLAKE | AOC SYST | 2023-06-05 | 2023-12-05 | 2024-12-31 |  | ABLAKE | 2023-10-11 | 2023-10-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 20.5333 | 3 | 3985.79 | 1152.15 | 906.84 | 73.07 | 1853.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23202998300 |  | 100323831 |  | 6716208P |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | KIRKLAND | 707 KIRKLAND DR | 067 | LEX | 2023-10-11 | U930915 | U132761 | 2023-07-24 | 2024-12-31 |  |  | RJCRAWF | 2023-10-11 | 2023-08-22 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.7667 | 8 | 1155.07 | 982.03 | 112.91 | 60.13 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23209810200 |  | 100249382 |  | 7348268M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | ROUTE 3 | ROUTE 3 | 127 | LOU | 2023-10-11 | RECUMP | U130722 | 2023-08-21 | 2023-12-29 | 2023-12-31 |  | RECUMP | 2023-10-11 | 2023-10-09 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 12.25 | 6 | 861.31 | 670.11 | 0 | 191.2 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23214686100 |  | 100340567 |  | 6724212F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332618 | 2621P | KNOXVILLE | 1714 KNOXVILLE CT | 067 | LEX | 2023-10-18 | U128381 | U135005 | 2023-09-14 | 2024-03-07 | 2025-09-30 |  | LSTANFI | 2023-10-11 | 2023-10-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.3833 | 3 | 1146.08 | 876.45 | 0 | 269.63 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23218018900 |  | 100348129 |  | 6748208I |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | COOK | 157 COOK AV | 049 | WIN | 2023-10-12 | U930915 | U135005 | 2023-09-29 | 2023-10-10 | 2023-10-10 |  | LCLARK | 2023-10-11 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 12.9 | 2 | 783.55 | 736.85 | 0 | 46.7 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 05599126100 |  | 100293915 |  | 6720212A | 0992615 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | BROADWAY | 713 N BROADWAY ST | 067 | LEX | 2023-10-12 | TROE | SSUTHER | 2005-01-21 | 2022-07-01 | 2023-12-31 |  | TROE | 2023-10-12 | 2022-09-01 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 41.3667 | 18 | 4038.58 | 2468.74 | 21.97 | 142.15 | 1405.72 | 0 | 0 | 0
KY | KY - EAST | 2633 | 11918566200 |  | 100264698 |  | 7384168F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | TURKEY CREEK | TURKEY CREEK RD | 195 | S W | 2023-10-12 | JAHOWARD | U907469 | 2011-08-02 | 2022-07-01 | 2023-12-31 |  | JAHOWARD | 2023-10-12 | 2022-10-05 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 4.4167 | 3 | 2379.74 | 240.93 | 0 | 15.27 | 2123.54 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883157900 |  | 100252115 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | COLDWATER ?? | 317 COLDWATER ?? | 159 | INE | 2023-10-12 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-10-12 | 2023-10-12 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.5333 | 1 | 150.19 | 141.25 | 0 | 8.94 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883163100 |  | 100433774 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | INE | 2023-10-12 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-10-12 | 2023-10-12 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.4833 | 1 | 87.63 | 82.4 | 0 | 5.23 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883300700 |  | 100430043 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | INE | 2023-10-12 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-10-12 | 2023-10-12 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.8167 | 1 | 110.27 | 103.69 | 0 | 6.58 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883308600 |  | 100428138 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | INE | 2023-10-12 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-10-12 | 2023-10-12 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.68333 | 1 | 40.56 | 38.15 | 0 | 2.41 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959264500 |  | 100261085 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | 6TH | 2211 6TH ST | 019 | ASH | 2023-10-12 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2332.95 | 0 | 0 | 0 | 2332.95 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959268000 |  | 100262582 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | HARRISON | 309 HARRISON ST | 019 | ASH | 2023-10-12 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1916.5 | 0 | 0 | 0 | 1916.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960852600 |  | 100250197 |  | 7356248D | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | CANNONSBURG | 8211 CANNONSBURG PK | 019 | CAT | 2023-10-13 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-10-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3243.93 | 0 | 0 | 0 | 3243.93 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110822300 |  | 100256997 |  | 7348264F | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | POND RUN | 7 POND RUN RD | 089 | RAC | 2023-10-13 | U123965 | U134723 | 2022-06-17 | 2023-12-29 |  |  | CJH CASEY PACK | 2023-10-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2045.38 | 0 | 0 | 0 | 2045.38 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22979021100 |  | 100253341 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | INE | 2023-10-12 | U130172 | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | JOHN KIRK | 2023-10-12 | 2023-10-12 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.45 | 1 | 86.44 | 81.27 | 0 | 5.17 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22979057300 |  | 501227000 |  | 7384168G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | SR292 | 3095 SR292 W | 195 | BEL | 2023-10-12 | U130172 | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | JOHN HOWARD | 2023-10-12 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.3833 | 1 | 1371.12 | 312.88 | 0 | 19.83 | 1038.41 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026297200 |  |  |  | 6712204G | 2300544 | U122858 |  | 557 | EX | EMER - INSTALL 13'-2" PMMP | 2600E | GRASSY CREEK | 3832 GRASSY CREEK RD | 067 | LEX | 2024-01-26 | U136251 | U122858 | 2023-10-03 | 2023-10-06 | 2023-10-12 | 2023-10-12 | KKINDER | 2023-10-12 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2972 |  |  | 100 | 055732230262972 | 2.8667 | 23 | 4970.8 | 168.58 | 0 | 10.69 | 3022.56 | 0 | 11.8 | 1757.17 | 23
KY | KY - WEST | 2621 | 23026297300 |  |  |  | 6712204G | 2300544 | U122858 |  | 558 | EX | EMER - RETIRE 2'-2" PMP | 2600E | GRASSY CREEK | 3832 GRASSY CREEK RD | 067 | LEX | 2024-01-10 | U136251 | U122858 | 2023-10-03 | 2023-10-09 | 2023-10-12 | 2023-10-12 | KKINDER | 2023-10-12 | 2023-10-10 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2973 |  |  | 100 | 055832230262973 | 7.5833 | 0 | 5943.6 | 3468.46 | 0 | 193.98 | 2281.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165287300 |  | 100294858 |  | 6716212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | UPPER | 407 N UPPER ST | 067 | LEX | 2023-10-12 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-10-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.3833 | 1 | 2762.26 | 255 | 0 | 16.16 | 2491.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168129200 |  | 100274967 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | MAIN | 235 W MAIN ST 1FE | 073 | FRA | 2023-10-13 | U461443 | U125763 | 2023-02-20 | 2023-12-29 |  |  | WGRAVES | 2023-10-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1959.98 | 59.55 | 0 | 3.76 | 1896.67 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23192219600 |  | 100323910 |  | 6716208P | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | BROOK HILL | 3311 BROOK HILL CR | 067 | LEX | 2023-10-12 | U128336 | AOC SYST | 2023-06-01 | 2023-12-01 | 2024-12-31 |  | JOSHUA COX | 2023-10-12 | 2023-10-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 22.8333 | 3 | 1999.4 | 1290.16 | 627.45 | 81.79 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23208376000 |  | 100294080 |  | 6720212E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | LIMESTONE | 613 N LIMESTONE ST 3 | 067 | LEX | 2023-10-12 | RSTRONG | U135005 | 2023-08-15 | 2023-12-29 |  |  | RSTRONG | 2023-10-12 | 2023-09-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 37.8167 | 8 | 3229.78 | 1763.89 | 558.31 | 360.83 | 546.75 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23213478100 |  | 100275812 |  | 6684228C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | AUDUBON | 104 AUDUBON DR | 073 | FRA | 2023-10-12 | MCRAIG | AOC SYST | 2023-09-07 | 2024-03-07 | 2024-12-31 |  | MCRAIG | 2023-10-12 | 2023-09-20 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 16.7667 | 3 | 1928.04 | 992.96 | 479.87 | 455.21 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23213800200 |  | 100340663 |  | 6724212I |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332616 | 2621P | CANTRILL | 1708 CANTRILL DR | 067 | LEX | 2023-10-18 | U128381 | U135005 | 2023-09-11 | 2024-03-08 | 2025-09-30 |  | LSTANFI | 2023-10-12 | 2023-10-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.2667 | 4 | 1298.82 | 1221.39 | 0 | 77.43 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23216222500 |  | 100283337 |  | 6712228F |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HIAWATHA | 210 HIAWATHA TL | 209 | GEO | 2023-10-18 | U123688 | U135005 | 2023-09-21 | 2023-12-29 | 2023-12-31 |  | DCOLLIN | 2023-10-12 | 2023-10-12 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 15.0167 | 2 | 4908.91 | 915.96 | 245.81 | 479.14 | 3268 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23216533500 |  | 100301070 |  | 6716212E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | WOODFORD | 134 WOODFORD DR | 067 | LEX | 2023-10-12 | JGILES | U135005 | 2023-09-22 | 2023-12-21 | 2023-12-22 |  | JGILES | 2023-10-12 | 2023-10-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 31.2167 | 9 | 1693.72 | 1322.62 | 286.65 | 84.45 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23218018000 |  | 100350062 |  | 6744204D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D304070 | 2621P | CRESCENT | 369 CRESCENT AV | 049 | WIN | 2023-10-12 | U930915 | U135005 | 2023-09-29 | 2023-09-29 | 2023-10-19 |  | WHIMES | 2023-10-12 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 16 | 2 | 1594.29 | 1210.5 | 218.03 | 165.76 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23220165200 |  | 100322376 |  | 6720208A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SUNSET | 801 SUNSET DR | 067 | LEX | 2023-10-12 | U930915 | U132928 | 2023-10-09 | 2023-10-09 | 2023-10-09 |  | TROE | 2023-10-12 | 2023-10-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 29.05 | 7 | 1755.09 | 1352.05 | 317.29 | 85.75 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23220640000 |  | 100265698 |  | 7348252C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D259810 | 2621P | ALEXANDER | 704 W ALEXANDER CT | 019 | ASH | 2023-10-12 | JROGER1 | U135005 | 2023-10-11 | 2023-10-13 | 2023-11-01 |  | JROGER1 | 2023-10-12 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 16 | 2 | 1530.25 | 749.62 | 224.56 | 556.07 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23220799800 |  | 100322705 |  | 6720208A | 2286046 |  |  | 565 | EX | RPLC SL/22026162101 | 2600B | TATES CREEK | 1228 TATES CREEK RD | 067 | LEX | 2023-10-13 | U126530 | U125763 | 2023-10-12 | 2023-12-29 |  |  | JDUNN | 2023-10-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3237.16 | 0 | 0 | 0 | 3237.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23220841800 |  | 100421101 |  | 6720208M |  |  |  | 565 | EX | GRADE 1 REPLACE SL | 2621P | PEPPERHILL | 3242 PEPPERHILL RD | 067 | LEX | 2023-10-12 | LSTONE | U129939 | 2023-10-12 | 2023-10-12 | 2023-10-12 |  | LSTONE | 2023-10-12 | 2023-10-12 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.4 | 2 | 597.27 | 365.38 | 208.74 | 23.15 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23220871900 |  | 100346524 |  | 6696212P |  |  |  | 565 | EX | GRADE 1 REPLACE SL | 2621P | WOODFORD VILLA | 107 WOODFORD VILLA DR | 239 | VER | 2023-10-12 | MCRAIG | U129939 | 2023-10-12 | 2023-10-12 | 2023-10-12 |  | MCRAIG | 2023-10-12 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 17.7833 | 4 | 1739.21 | 1044.91 | 418.11 | 276.19 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 20026974601 |  |  |  | 6684228K | 2074544 | U126783 |  | 557 | EX | INSTALL 6,500'-4"PMLP | 2600B | ANN | ANN ST | 073 | FRA | 2024-02-07 | U136251 | U126783 | 2023-12-21 | 2023-02-08 | 2049-12-31 | 2023-10-13 | WGRAVES | 2023-10-13 | 2023-02-14 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP9746 | AMRCB |  | 100 | 055732200269746 | 1742.15 | 1402517 | 2600268.43 | 118558.23 | 46139.49 | 77644.44 | 1844788.7 | 0 | 38909.61 | 474227.96 | 6647
KY | KY - EAST | 2633 | 21883211400 |  | 100248001 |  | 7364188A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | MIDDLE FORK | MIDDLE FORK RD | 159 | INE | 2023-10-13 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN HOWARD | 2023-10-13 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 8 | 1 | 493.78 | 464.35 | 0 | 29.43 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959267900 |  | 500183560 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | HARRISON | 308 HARRISON ST | 019 | ASH | 2023-10-13 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3216.97 | 0 | 0 | 0 | 3216.97 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959273100 |  | 100261141 |  | 7356252D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | 6TH | 2114 6TH ST | 019 | ASH | 2023-10-13 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1987.27 | 0 | 0 | 0 | 1987.27 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960853200 |  | 100250185 |  | 7356248D | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | CEMETERY | 8421 CEMETERY RD | 019 | CAT | 2023-10-16 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-10-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2208.74 | 0 | 0 | 0 | 2208.74 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110822400 |  | 100256999 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | POND RUN | 9 POND RUN RD | 089 | RAC | 2023-10-13 | U123965 | U134723 | 2022-06-17 | 2023-12-29 |  |  | CJH CASEY PACK | 2023-10-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1324.12 | 0 | 0 | 0 | 1324.12 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23026302100 |  |  |  | 7356152C | 2301164 | U461383 |  | 584 | CO | RETIRE PAPER GAUGE | 2633M | DUDLEY | DUDLEY DR | 195 | GRN | 2024-03-11 |  | U461383 | 2023-10-23 | 2024-12-13 | 2024-12-15 | 2023-10-13 | TC ENERGY | 2023-10-13 |  |  | F | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00584 | 3200584 |  |  | WP3021 |  |  | 100 | 058432230263021 |  | 0 | 306.23 | 141.5 | 0 | 164.73 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23193014400 |  | 500011056 |  | 6696212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332961 | 2621P | COLONY | 319 COLONY DR | 239 | VER | 2023-10-18 | U123688 | U135005 | 2023-06-06 | 2023-12-05 | 2025-06-30 |  | BWHITE | 2023-10-13 | 2023-10-05 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 24.5667 | 8 | 3020.09 | 1074.82 | 188.55 | 68.17 | 1688.55 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23213476900 |  | 100275811 |  | 6684228C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | AUDUBON | 106 AUDUBON DR | 073 | FRA | 2023-10-13 | MCRAIG | AOC SYST | 2023-09-07 | 2024-03-07 | 2024-12-31 |  | MCRAIG | 2023-10-13 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 16 | 2 | 2070.17 | 925.54 | 379.25 | 765.38 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23214756000 |  | 100292933 |  | 6720216K |  |  |  | 565 | VO | REPLACE SL - CORROSION/STEEL | 2621P | BISHOP | 673 BISHOP DR | 067 | LEX | 2024-02-28 | TROE | U135005 | 2023-09-14 | 2023-12-14 | 2023-12-14 |  | TROE | 2023-10-13 | 2023-10-06 |  | A | [11 empty] | 24248053500 | 100 |  | 14.4833 | 5 | 1329.43 | 706.59 | 578.05 | 44.79 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23220145800 |  | 500362082 |  | 7356256B |  |  |  | 566 | EX | ABANDON SL-DEMO/CUST REQ | 2621P | GREENUP | 1900 GREENUP AV | 019 | ASH | 2023-10-13 | ABHATFIE | U139707 | 2023-10-09 | 2023-10-27 | 2023-11-20 |  | ABHATFIE | 2023-10-13 | 2023-10-13 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 16 | 2 | 1178.8 | 867.95 | 20.27 | 290.58 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23220338900 |  | 100347319 |  | 6696212H | 1635077 |  |  | 565 | EX | REPLACE SERVICE | 2621P | PARK | 140 PARK ST | 239 | VER | 2023-10-18 | U123688 | U130871 | 2023-10-10 | 2023-10-10 |  |  | BWHITE | 2023-10-13 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6 | 3 | 17363.14 | 6938.17 | 583.51 | 1794.34 | 8047.12 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23220848700 |  | 100265546 |  | 7348252C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D259811 | 2621P | HOENIG | 6439 HOENIG DR | 019 | ASH | 2023-10-18 | U123688 | U135005 | 2023-10-12 | 2023-10-13 | 2023-11-02 |  | JROGER1 | 2023-10-13 | 2023-10-13 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 15.2 | 2 | 3368.91 | 702.12 | 297.36 | 500.31 | 1869.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23221075900 |  | 100290683 |  | 6720212B |  |  |  | 565 | EX | SERVICE LINE REPLACE | 2621P | BROADVIEW | 210 BROADVIEW DR | 067 | LEX | 2023-10-18 | U123688 | U134852 | 2023-10-13 | 2023-10-13 |  |  | LSTANFI | 2023-10-13 | 2023-10-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.2 | 3 | 721.53 | 406.92 | 288.83 | 25.78 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23221122900 |  | 100257187 |  | 7348264I | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2621P | BELLEFONTE | 75 BELLEFONTE RD | 089 | RAC | 2023-10-16 | U123965 | U123235 | 2023-10-13 | 2024-12-31 |  |  | CJH JD CHURCH | 2023-10-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2585.83 | 0 | 65.09 | -61.7 | 2582.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24248053500 |  | 100292935 |  | 6720216K |  |  |  | 565 | EX | REPLACE SL - CORROSION/STEEL | 2621P | BISHOP | 681 BISHOP DR | 067 | LEX | 2024-02-28 | U123688 | U123688 | 2024-02-28 | 2024-12-31 |  |  | TROE | 2023-10-13 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1
KY | KY - EAST | 2633 | 11898370900 |  | 100266505 |  | 7356152E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | US23 | US23 | 195 | BLA | 2023-10-16 | JAHOWARD | DDURKIN | 2011-03-29 | 2023-10-16 | 2023-12-31 |  | JAHOWARD | 2023-10-16 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.3167 | 1 | 1086.35 | 191.56 | 0 | 12.14 | 882.65 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 12968589800 |  | 100354141 |  | 7256280P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2600B | 4TH | 232 E 4TH ST | 161 | MAY | 2023-10-16 | U461383 | U124967 | 2012-05-07 | 2023-12-29 | 2023-12-31 |  | SDADAMS | 2023-10-16 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 5.15 | 2 | 303.59 | 285.48 | 0 | 18.11 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 17513289500 |  | 100249176 |  | 7328284B |  |  |  | 565 | EX | REPLACE SERVICE | 2621P | S M ROBERSON | 470 S M ROBERSON DR | 089 | S S | 2023-10-16 | RECUMP | CBURCHA | 2017-06-06 | 2017-06-07 |  |  | RECUMP | 2023-10-16 | 2023-09-26 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 31.2833 | 14 | 2757.6 | 1769.51 | 255.41 | 732.68 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883098700 |  | 100255234 |  | 7352152T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | SYCAMORE | 126 SYCAMORE | 071 | HAR | 2023-10-17 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BLAKE MULLINS | 2023-10-16 | 2023-10-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.2833 | 1 | 127.28 | 119.68 | 0 | 7.6 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883129100 |  | 100255235 |  | 7352152T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PM30 | PM30 | 071 | HAR | 2023-10-17 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BLAKE MULLINS | 2023-10-16 | 2023-10-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.3833 | 1 | 132.88 | 124.95 | 0 | 7.93 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883218500 |  | 100260487 |  | 7348148T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW4251 | PW4251 | 071 | DRI | 2023-10-17 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | ANDREW SHEPHERD | 2023-10-16 | 2023-10-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.9 | 2 | 135.7 | 127.6 | 0 | 8.1 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883237400 |  | 100260637 |  | 7344148T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW4251 | PW4251 | 071 | DRI | 2023-10-17 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | ANDREW SHEPHERD | 2023-10-16 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.2333 | 2 | 88.63 | 83.33 | 0 | 5.3 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883248700 |  | 100260477 |  | 7344148T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW3858 | PW3858 | 071 | DRI | 2023-10-17 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | ANDREW SHEPHERD | 2023-10-16 | 2023-10-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.9 | 2 | 135.7 | 127.6 | 0 | 8.1 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883270600 |  | 100416514 |  | 7360156M |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | STEVENS | STEVENS ST | 195 | BLA | 2023-10-16 | U130172 | U120245 | 2021-01-30 | 2023-10-16 | 2023-12-31 |  | JAHOWARD | 2023-10-16 | 2022-11-17 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 4.2333 | 2 | 1133.86 | 236.24 | 0 | 14.97 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883308400 |  | 100266504 |  | 7356152E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | US23 | US23 | 195 | BLA | 2023-10-16 | JAHOWARD | U120245 | 2021-01-30 | 2023-10-16 | 2023-12-31 |  | JAHOWARD | 2023-10-16 | 2022-11-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.9 | 2 | 38.89 | 36.58 | 0 | 2.31 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959264100 |  | 100261132 |  | 7356252D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | 6TH | 2004 6TH ST | 019 | ASH | 2023-10-16 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-16 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2661.92 | 14.68 | 0 | 17.88 | 2629.36 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959267800 |  | 500503670 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | HARRISON | 302 HARRISON ST | 019 | ASH | 2023-10-16 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-16 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3049.54 | 30.7 | 0 | 27.51 | 2991.33 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960853300 |  | 100250184 |  | 7356248D | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | CEMETERY | 8427 CEMETERY RD | 019 | CAT | 2023-10-17 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-10-16 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1907.21 | 0 | 0 | 0 | 1907.21 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110826200 |  | 500399339 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | WILLIAMS | 1009 WILLIAMS AV | 089 | RAC | 2023-10-17 | U123965 | U134723 | 2022-06-17 | 2023-12-29 |  |  | CJH CASEY PACK | 2023-10-16 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2636.36 | 0 | 0 | 0 | 2636.36 | 0 | 0 | 0
KY | KY - EAST | 2682 | 22979046300 |  | 100429078 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | MAPLE | 89 MAPLE DR | 119 | HIN | 2023-10-17 | U130172 | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | BRIAN PREECE | 2023-10-16 | 2023-10-16 |  | B | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 4.9 | 1 | 302.36 | 284.34 | 0 | 18.02 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23165283800 |  | 100336836 |  | 6720212E | 2177145 |  |  | 565 | EX | RPLC SL/21026997800 | 2600B | LIMESTONE | 422 N LIMESTONE ST 3 | 067 | LEX | 2023-10-16 | U126532 | U125763 | 2023-02-07 | 2023-12-29 |  |  | LESLIE SHARON | 2023-10-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.5167 | 1 | 5482.15 | 554.82 | 94.06 | 35.18 | 4798.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166675300 |  | 100322666 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 721 PROVIDENCE RD | 067 | LEX | 2023-10-16 | U126603 | U125763 | 2023-02-14 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-10-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1917 | 0 | 0 | 0 | 1917 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23206599400 |  | 100339381 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | TAMPA | 1503 TAMPA CT | 067 | LEX | 2023-10-16 | LSTONE | AOC SYST | 2023-08-04 | 2024-02-02 | 2024-12-31 |  | LSTONE | 2023-10-16 | 2023-09-29 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 13.6667 | 3 | 1159.38 | 748.75 | 363.61 | 47.02 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212716600 |  | 100340132 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | HI CREST | 704 HI CREST DR | 067 | LEX | 2023-10-16 | WISHII | AOC SYST | 2023-09-01 | 2024-03-01 | 2024-12-31 |  | WISHII | 2023-10-16 | 2023-10-12 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 17.4 | 3 | 1912.27 | 932.48 | 418.47 | 561.32 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23214748500 |  | 100280406 |  | 6688228F |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | GREENHILL | 146 GREENHILL AV | 073 | FRA | 2023-10-16 | BWHITE | U133234 | 2023-09-14 | 2023-09-28 | 2023-10-14 |  | BWHITE | 2023-10-16 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 17.1 | 2 | 1076.67 | 1007.72 | 5.05 | 63.9 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23216220800 |  | 100283333 |  | 6712228F |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HIAWATHA | 198 HIAWATHA TL | 209 | GEO | 2023-10-16 | DCOLLIN | U135005 | 2023-09-21 | 2023-12-29 | 2023-12-31 |  | DCOLLIN | 2023-10-16 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 16 | 2 | 4641.04 | 974.35 | 293.77 | 532.9 | 2840.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23217455100 |  | 100328772 |  | 6720208F |  |  |  | 565 | EX | AOC ATMOS CORR RPLC SL & RISER | 2621P | HART | 1960 HART RD | 067 | LEX | 2023-10-16 | U930915 | U135005 | 2023-09-28 | 2023-10-27 | 2023-10-28 |  | HMCKUNE | 2023-10-16 | 2023-10-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 63.8833 | 9 | 3332.88 | 3026.62 | 41.36 | 264.9 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23220377200 |  | 100335666 |  | 6720212K |  |  |  | 566 | EX | ABDN SL - DEMO/CITY RQD MSTR | 2621P | INDUSTRY | 1020 INDUSTRY RD STE 70 | 067 | LEX | 2023-10-18 | U930915 | U135005 | 2023-10-10 | 2023-11-10 | 2023-11-10 |  | LSTANFI | 2023-10-16 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.53333 | 2 | 41.39 | 31.43 | 0 | 9.96 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23220377700 |  | 100335673 |  | 6720212K |  |  |  | 566 | EX | ABDN SL - DEMO/CITY RQD MNFLD | 2621P | INDUSTRY | 1020 INDUSTRY RD STE 72 | 067 | LEX | 2023-10-16 | LSTANFI | U135005 | 2023-10-10 | 2023-11-10 | 2023-11-10 |  | LSTANFI | 2023-10-16 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.8667 | 2 | 371.15 | 281.99 | 0 | 89.16 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23220378200 |  | 100335667 |  | 6720212K |  |  |  | 566 | EX | ABDN SL - DEMO/CITY RQD MNFLD | 2621P | INDUSTRY | 1020 INDUSTRY RD STE 76 | 067 | LEX | 2023-10-16 | LSTANFI | U135005 | 2023-10-10 | 2023-11-10 | 2023-11-10 |  | LSTANFI | 2023-10-16 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.6667 | 2 | 127.27 | 96.71 | 0 | 30.56 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23220378800 |  | 100335665 |  | 6720212K | 0779375 |  |  | 566 | EX | ABDN SL - DEMO/CITY RQD MNFLD | 2621P | INDUSTRY | 1020 INDUSTRY RD STE 78 | 067 | LEX | 2023-10-16 | LSTANFI | U135005 | 2023-10-10 | 2023-11-10 | 2023-11-10 |  | LSTANFI | 2023-10-16 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.13333 | 2 | 15.37 | 11.67 | 0 | 3.7 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23220588400 |  | 100324990 |  | 6720204E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | GREENTREE | 3517 GREENTREE RD | 067 | LEX | 2023-10-16 | HMCKUNE | U130871 | 2023-10-11 |  |  |  | HMCKUNE | 2023-10-16 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 4.1 | 2 | 241.28 | 226.9 | 0 | 14.38 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23221338700 |  | 100336292 |  | 6720212I |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | 3RD | 327 E 3RD ST | 067 | LEX | 2023-10-16 | U128336 | U138726 | 2023-10-14 | 2023-10-16 |  |  | JOSHUA COX | 2023-10-16 | 2023-10-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 55.8333 | 5 | 11294.66 | 3537.84 | 717.28 | 576.55 | 6462.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23221403800 |  | 100336839 |  | 6720212E |  |  |  | 566 | EX | ABANDN SL/ | 2600B | LIMESTONE | 422 N LIMESTONE ST WH | 067 | LEX | 2023-10-16 | U126532 | U125763 | 2023-10-16 | 2023-12-29 |  |  | LESLIE SHARON | 2023-10-16 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 0
KY | KY - EAST | 2633 | 21883129500 |  | 100266584 |  | 7356156P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | C | C ST | 195 | BLA | 2023-10-18 | U123688 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JAHOWARD | 2023-10-17 | 2022-11-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.1833 | 2 | 1061.66 | 168.34 | 0 | 10.67 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883230600 |  | 100253584 |  | 7360192T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | TOM | 2023-10-17 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-10-17 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.55 | 1 | 92.43 | 86.91 | 0 | 5.52 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21884246600 |  | 100253580 |  | 7360192T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | TOM | 2023-10-17 | U130172 | U128293 | 2021-02-04 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-10-17 | 2023-10-17 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 7.6833 | 2 | 461.24 | 433.74 | 0 | 27.5 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959264200 |  | 100261140 |  | 7356252D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | 6TH | 2104 6TH ST | 019 | ASH | 2023-10-17 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-17 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1983.9 | 0 | 0 | 0 | 1983.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959273300 |  | 100262580 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | HARRISON | 312 HARRISON ST | 019 | ASH | 2023-10-17 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-17 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2169.26 | 0 | 0 | 0 | 2169.26 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960883400 |  | 100250182 |  | 7356248D | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | CEMETERY | 8437 CEMETERY RD | 019 | CAT | 2023-10-18 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-10-17 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3573.78 | 0 | 0 | 0 | 3573.78 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129011500 |  | 500705869 |  | 7352156L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | REDTOWN | 70 REDTOWN | 071 | BET | 2023-10-17 | JAHOWARD | U130722 | 2022-09-05 | 2022-12-30 |  |  | JAHOWARD | 2023-10-17 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 4.65 | 1 | 1167.84 | 268.19 | 0 | 17 | 882.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166676100 |  | 100322701 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 740 PROVIDENCE RD | 067 | LEX | 2023-10-17 | U126603 | U125763 | 2023-02-14 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-10-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1998.51 | 0 | 0 | 0 | 1998.51 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168129100 |  | 100275127 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | MAIN | 234 W MAIN ST | 073 | FRA | 2023-10-17 | U461443 | U125763 | 2023-02-20 | 2023-12-29 |  |  | WGRAVES | 2023-10-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2020.88 | 0 | 0 | 0 | 2020.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168129400 |  | 100274970 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | MAIN | 241 W MAIN ST | 073 | FRA | 2023-10-17 | U461443 | U125763 | 2023-02-20 | 2023-12-29 |  |  | WGRAVES | 2023-10-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2909.48 | 0 | 0 | 0 | 2909.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23193117800 |  | 100322788 |  | 6716208D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | KASTLE | 1215 KASTLE RD | 067 | LEX | 2023-10-17 | KKINDER | AOC SYST | 2023-06-06 | 2023-12-06 | 2024-12-31 |  | KKINDER | 2023-10-17 | 2023-10-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 15.6833 | 3 | 1104.81 | 890.07 | 158.3 | 56.44 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23196921700 |  | 500017373 |  | 6684228H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332550 | 2621P | BLACKBURN | 614 BLACKBURN AV | 073 | FRA | 2023-10-18 | U123688 | U135005 | 2023-06-26 | 2023-12-21 | 2025-06-30 |  | EFGOINS | 2023-10-17 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 22.7 | 3 | 1785.83 | 1110.41 | 13.02 | 70.4 | 592 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23205498000 |  | 100339210 |  | 6724212I | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | GAYLE | 1877 GAYLE DR | 067 | LEX | 2023-10-18 | U123688 | AOC SYST | 2023-08-01 | 2024-12-31 | 2024-12-31 |  | LSTANFI | 2023-10-17 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 13.2 | 3 | 1570.12 | 765.53 | 562.6 | 241.99 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23211321300 |  | 100328765 |  | 6720208F | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | HART | 1957 HART RD | 067 | LEX | 2023-10-17 | U128336 | AOC SYST | 2023-08-28 | 2024-02-28 | 2024-12-31 |  | JOSHUA COX | 2023-10-17 | 2023-10-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 17.0833 | 3 | 1354.36 | 810.24 | 492.77 | 51.35 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212037200 |  | 100339528 |  | 6724212A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | VALDOSTA | 1470 VALDOSTA CT | 067 | LEX | 2023-10-17 | LSTONE | AOC SYST | 2023-08-30 | 2024-02-29 | 2024-12-31 |  | LSTONE | 2023-10-17 | 2023-09-29 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 14.0667 | 3 | 1123.51 | 778 | 296.54 | 48.97 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212041600 |  | 100339680 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | ANNISTON | 1500 ANNISTON DR | 067 | LEX | 2023-10-18 | U930915 | AOC SYST | 2023-08-30 | 2024-02-29 | 2024-12-31 |  | HMCKUNE | 2023-10-17 | 2023-10-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 15.3167 | 3 | 1738.96 | 713.96 | 412.73 | 45.27 | 567 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212273400 |  | 100339442 |  | 6724212A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | MARIETTA | 1923 MARIETTA DR | 067 | LEX | 2023-10-17 | WISHII | AOC SYST | 2023-08-31 | 2024-02-29 | 2024-12-31 |  | WISHII | 2023-10-17 | 2023-10-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 11.8667 | 3 | 967.83 | 639.92 | 0 | 327.91 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23215904000 |  | 500853266 |  | 6700212N | 2399274 |  |  | 565 | EX | SERVICE LINE/METER UPGRADE | 2621P | EUREKA | 400 EUREKA DR | 239 | VER | 2023-10-19 | U128410 | U135005 | 2023-09-20 | 2023-10-17 | 2023-10-17 |  | CDESPAIN | 2023-10-17 | 2023-10-05 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26230031 | 29.4667 | 8 | 9749.81 | 1722.76 | 277.73 | 109.2 | 7640.12 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23221420000 |  | 100405715 |  | 7348264J | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | BELLEFONTE | BELLEFONTE RD | 089 | RAC | 2023-10-18 | U123965 | U123235 | 2023-10-16 | 2024-12-31 |  |  | CJH CASEY PACK | 2023-10-17 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2181.15 | 0 | 0 | 0 | 2181.15 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23221625000 |  | 100247121 |  | 7352256L |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | WILLIS | 3438 WILLIS AV | 019 | ASH | 2023-10-18 | U123688 | U139677 | 2023-10-17 | 2023-10-16 | 2023-10-16 |  | RECUMP | 2023-10-17 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 15.85 | 2 | 1390.06 | 859.04 | 260.14 | 270.88 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23221646400 |  | 100266586 |  | 7356156P |  |  |  | 566 | EX | ABANDON CSL | 2621P | C | 5427 C ST | 195 | BLA | 2023-10-17 | JAHOWARD | U139677 | 2023-10-17 | 2023-10-17 |  |  | JAHOWARD | 2023-10-17 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.25 | 1 | 15.43 | 14.5 | 0 | 0.93 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23221649500 |  | 500118983 |  | 6736252I | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | US HIGHWAY 27 | 698 US HIGHWAY 27 S | 097 | CYN | 2023-10-18 | U123111 | U125763 | 2023-10-17 | 2023-12-29 |  |  | LYN STAFFORD | 2023-10-17 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2171.81 | 62.79 | 0 | 64.81 | 2044.21 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23221689500 |  | 100360676 |  | 6736228C |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SKYVIEW | 445 SKYVIEW DR | 017 | PAR | 2023-10-18 | U930915 | U129939 | 2023-10-17 | 2023-11-10 | 2025-05-31 |  | NRICHIE | 2023-10-17 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26290021 | 3.5 | 2 | 1242.31 | 592.4 | 288.13 | 361.78 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883141300 |  | 100432884 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | INE | 2023-10-18 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-10-18 | 2023-10-18 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.16667 | 2 | 10.18 | 9.57 | 0 | 0.61 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883203500 |  | 100424479 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | INE | 2023-10-18 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-10-18 | 2023-10-18 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.5 | 2 | 90.51 | 85.15 | 0 | 5.36 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883302100 |  | 100412892 |  | 7348140T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW5335 | PW5335 | 071 | MCD | 2023-10-18 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BRIAN PREECE | 2023-10-18 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.9333 | 1 | 122.19 | 114.9 | 0 | 7.29 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959268100 |  | 100262578 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | HARRISON | 316 HARRISON ST | 019 | ASH | 2023-10-18 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-18 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2759.35 | 0 | 0 | 0 | 2759.35 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959268200 |  | 100262586 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | HARRISON | 331 HARRISON ST | 019 | ASH | 2023-10-18 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-18 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1973.79 | 0 | 0 | 0 | 1973.79 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960853500 |  | 100250181 |  | 7356248D | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | CEMETERY | 8445 CEMETERY RD | 019 | CAT | 2023-10-19 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-10-18 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2616.14 | 0 | 0 | 0 | 2616.14 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110826100 |  | 100462689 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | WILLIAMS | 999 WILLIAMS AV | 089 | RAC | 2023-10-18 | U123965 | U134723 | 2022-06-17 | 2023-12-29 |  |  | CJH CASEY PACK | 2023-10-18 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2602.66 | 0 | 0 | 0 | 2602.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166671100 |  | 100322616 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 721 BERRY LN | 067 | LEX | 2023-10-18 | U126603 | U125763 | 2023-02-14 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-10-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1846.49 | 0 | 0 | 0 | 1846.49 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168129300 |  | 100274969 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | MAIN | 239 W MAIN ST 1F | 073 | FRA | 2023-10-18 | U461443 | U125763 | 2023-02-20 | 2023-12-29 |  |  | WGRAVES | 2023-10-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1872.17 | 0 | 0 | 0 | 1872.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23190923700 |  | 100323777 |  | 6716204D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | MALABU | 811 MALABU DR | 067 | LEX | 2023-10-18 | RSTRONG | AOC SYST | 2023-05-25 | 2023-11-22 | 2024-12-31 |  | RSTRONG | 2023-10-18 | 2023-09-29 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 30.5 | 4 | 4746.36 | 1366.48 | 568.99 | 382.25 | 2428.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23193986000 |  | 100323218 |  | 6716208P | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | HILDEEN | 808 HILDEEN DR | 067 | LEX | 2023-10-18 | U128336 | AOC SYST | 2023-06-09 | 2023-12-08 | 2024-12-31 |  | JOSHUA COX | 2023-10-18 | 2023-10-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 24.4 | 4 | 1959.22 | 1213 | 669.32 | 76.9 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23205505600 |  | 100339187 |  | 6724212I | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | CANTRILL | 1816 CANTRILL DR | 067 | LEX | 2023-10-20 | U135005 | AOC SYST | 2023-08-01 | 2024-02-01 | 2024-12-31 |  | LSTANFI | 2023-10-18 | 2023-09-29 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 19.4667 | 7 | 2717.33 | 1107.14 | 391.41 | 128.64 | 1090.14 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23206610100 |  | 100339363 |  | 6724212F | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | MEMPHIS | 2027 MEMPHIS CT | 067 | LEX | 2023-10-18 | WISHII | AOC SYST | 2023-08-04 | 2024-02-02 | 2024-12-31 |  | WISHII | 2023-10-18 | 2023-10-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 16.9833 | 3 | 1541.98 | 977.76 | 0 | 564.22 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212033200 |  | 100339527 |  | 6724212A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | VALDOSTA | 1466 VALDOSTA CT | 067 | LEX | 2023-10-20 | U135005 | AOC SYST | 2023-08-30 | 2024-02-29 | 2024-12-31 |  | LSTANFI | 2023-10-18 | 2023-09-29 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 8.1167 | 5 | 741.25 | 451.94 | 211.86 | 77.45 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212034600 |  | 100339519 |  | 6724212A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | VALDOSTA | 1465 VALDOSTA CT | 067 | LEX | 2023-10-20 | U135005 | AOC SYST | 2023-08-30 | 2024-02-29 | 2024-12-31 |  | LSTANFI | 2023-10-18 | 2023-09-29 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 13.45 | 5 | 1216.27 | 755.91 | 412.73 | 47.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23213475700 |  | 100275804 |  | 6684228C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | AUDUBON | 120 AUDUBON DR | 073 | FRA | 2023-10-18 | MCRAIG | AOC SYST | 2023-09-07 | 2024-03-07 | 2024-12-31 |  | MCRAIG | 2023-10-18 | 2023-10-03 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 18.9167 | 4 | 2469.17 | 1094.26 | 481.33 | 893.58 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23215056800 |  | 100246113 |  | 7324284A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | STATE RT 8 | 1886 STATE RT 8 | 089 | S P | 2023-10-18 | JKEENER | U124420 | 2023-09-15 | 2024-02-06 | 2024-02-06 |  | JKEENER | 2023-10-18 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 8.0667 | 2 | 528.12 | 446.25 | 0 | 81.87 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23215916700 |  | 100325554 |  | 6720208E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332681 | 2621P | LAKEWOOD | 1171 LAKEWOOD DR | 067 | LEX | 2023-10-20 | U135005 | U135005 | 2023-09-20 | 2024-03-19 | 2025-09-30 |  | RJCRAWF | 2023-10-18 | 2023-10-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 28.3167 | 7 | 1712.11 | 1610.04 | 0 | 102.07 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23216221100 |  | 100283334 |  | 6712228F |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HIAWATHA | 200 HIAWATHA TL | 209 | GEO | 2023-10-18 | DCOLLIN | U135005 | 2023-09-21 | 2023-12-29 | 2023-12-31 |  | DCOLLIN | 2023-10-18 | 2023-10-17 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 17.1333 | 4 | 5281.24 | 1043.84 | 304.71 | 570.88 | 3361.81 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23216221800 |  | 100283342 |  | 6712228F |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HIAWATHA | 207 HIAWATHA TL | 209 | GEO | 2023-10-18 | DCOLLIN | U135005 | 2023-09-21 | 2023-12-29 | 2023-12-31 |  | DCOLLIN | 2023-10-18 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 26.8667 | 2 | 7050.63 | 1635.69 | 288.25 | 895.21 | 4231.48 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23216257400 |  | 500687100 |  | 7348248K |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | CANNONSBURG | 1619 CANNONSBURG RD | 019 | ASH | 2023-10-18 | RECUMP | U133234 | 2023-09-21 | 2023-10-04 | 2023-10-20 |  | RECUMP | 2023-10-18 | 2023-10-03 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 22.0833 | 6 | 4345.26 | 1647.88 | 0 | 490.78 | 2206.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23221716200 |  | 100319360 |  | 6716208O |  |  |  | 565 | EX | EMERG REPLACE SERVICE LINE | 2621P | LOWRY | 317 E LOWRY LN | 067 | LEX | 2023-10-20 | U135005 | U135005 | 2023-10-17 | 2023-10-23 | 2023-10-23 |  | RJCRAWF | 2023-10-18 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 15.8167 | 2 | 937.45 | 881.57 | 0 | 55.88 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23221886000 |  | 100289772 |  | 6720216P |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | WICKLAND | 1934 WICKLAND DR | 067 | LEX | 2023-10-18 | KKINDER | U139701 | 2023-10-17 | 2023-10-17 | 2023-10-17 |  | KKINDER | 2023-10-18 | 2023-10-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16 | 2 | 1595.37 | 926.25 | 610.41 | 58.71 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23221895500 |  | 100411867 |  | 6720204J |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | STEPHEN FOSTER | 1474 STEPHEN FOSTER DR | 067 | LEX | 2023-10-18 | HMCKUNE | U129939 | 2023-10-18 | 2023-10-18 |  |  | HMCKUNE | 2023-10-18 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.76667 | 2 | 256.14 | 39.24 | 214.4 | 2.5 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23221930600 |  | 100275087 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | WASHINGTON | 207 WASHINGTON ST 1F | 073 | FRA | 2023-10-18 | U461443 | U125763 | 2023-10-18 | 2023-12-29 |  |  | WGRAVES | 2023-10-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2408.94 | 0 | 0 | 0 | 2408.94 | 0 | 0 | 0
KY | KY - EAST | 2633 | 08727337000 |  | 500720287 | 27 | 7360152E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | INDUSTRIAL | 311 INDUSTRIAL DR | 195 | PIK | 2023-10-20 | U135005 | DHANSFO | 2008-04-14 | 2023-10-17 | 2023-12-31 |  | JAHOWARD | 2023-10-19 | 2023-10-18 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 16 | 2 | 2462.11 | 928.7 | 0 | 58.86 | 1474.55 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21026997801 |  |  |  | 6720212E | 2177145 | U461383 |  | 557 | EX | INSTALL 4600' OF 2"/6"PMMP | 2600B | 4TH | E 4TH ST | 067 | LEX | 2023-11-03 | U128132 | U461383 | 2023-07-19 | 2023-01-30 | 2023-12-31 | 2023-08-07 | LESLIE SHARON | 2023-10-19 | 2023-08-14 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP9978 | AMRCB |  | 100 | 055732210269978 | 2112.85 | 1383021 | 2229938.96 | 135559.84 | 50754.59 | 64709.89 | 1594917.77 | 0 | 628.98 | 383367.89 | 4887
KY | KY - WEST | 2621 | 21026997900 |  |  |  | 6720212E | 2177145 | U461383 |  | 558 | EX | RETIRE 6300' OF 4"/6"CILP MN | 2600B | 4TH | E 4TH ST | 067 | LEX | 2023-11-01 | U128132 | U461383 | 2021-01-25 | 2023-12-29 | 2024-08-31 | 2023-10-19 | LESLIE SHARON | 2023-10-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP9979 | AMRCB |  | 100 | 055832210269979 |  | 0 | 747.19 | 0 | 0 | 0 | 747.19 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883117200 |  | 100252091 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | INE | 2023-10-19 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-10-19 | 2023-10-19 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.6333 | 1 | 96.56 | 90.8 | 0 | 5.76 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883153600 |  | 500054096 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | INE | 2023-10-19 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-10-19 | 2023-10-19 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.6833 | 1 | 99.55 | 93.61 | 0 | 5.94 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883173700 |  | 100253347 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | INE | 2023-10-19 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-10-19 | 2023-10-19 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.56667 | 1 | 33.99 | 31.97 | 0 | 2.02 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883177900 |  | 100436568 |  | 7360192T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | TOM | 2023-10-19 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-10-19 | 2023-10-19 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.8 | 1 | 47.71 | 44.87 | 0 | 2.84 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883262200 |  | 100253581 |  | 7360192T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | TOM | 2023-10-19 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-10-19 | 2023-10-19 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.43333 | 1 | 25.65 | 24.11 | 0 | 1.54 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959264600 |  | 100261149 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | 6TH | 2212 6TH ST | 019 | ASH | 2023-10-19 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3555.35 | 0 | 0 | 0 | 3555.35 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959268400 |  | 100262587 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | HARRISON | 333 HARRISON ST | 019 | ASH | 2023-10-19 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2654.08 | 0 | 0 | 0 | 2654.08 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959273500 |  | 100262577 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | HARRISON | 324 HARRISON ST | 019 | ASH | 2023-10-19 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2053.71 | 0 | 0 | 0 | 2053.71 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960853400 |  | 100441572 |  | 7356248D | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | CEMETERY | 8441 CEMETERY RD | 019 | CAT | 2023-10-20 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-10-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 4080.26 | 0 | 0 | 0 | 4080.26 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110826000 |  | 100462539 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | WILLIAMS | 989 WILLIAMS AV | 089 | RAC | 2023-10-19 | U123965 | U134723 | 2022-06-17 | 2023-12-29 |  |  | CJH CASEY PACK | 2023-10-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2626.25 | 0 | 0 | 0 | 2626.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129057700 |  | 100412416 |  | 7240280F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | KY 10 | 6203 KY 10 | 023 | GER | 2023-10-19 | SDADAMS | U130722 | 2022-09-05 | 2022-12-30 |  |  | SDADAMS | 2023-10-19 | 2022-11-17 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 15.9167 | 5 | 1374.24 | 935.57 | 51.86 | 386.81 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129075200 |  | 100436546 |  | 7348264H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | RAILROAD | RAILROAD ST | 089 | RUS | 2023-10-19 | JROGER1 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JROGER1 | 2023-10-19 | 2023-10-19 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 11.95 | 2 | 1189.72 | 706 | 141.46 | 342.26 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166676000 |  | 100322662 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 737 PROVIDENCE RD | 067 | LEX | 2023-10-19 | U126603 | U125763 | 2023-02-14 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-10-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2107.58 | 0 | 0 | 0 | 2107.58 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23168423900 |  | 100404502 |  | 7348264J |  |  |  | 565 | EX | REPLACE SERVICE LINE - D259796 | 2621P | CRESTVIEW | 1221 CRESTVIEW DR | 089 | RAC | 2023-10-19 | MCOLLET | U125208 | 2023-02-21 | 2023-08-18 | 2025-02-28 |  | MCOLLET | 2023-10-19 | 2023-10-03 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 23.6833 | 5 | 3579.72 | 1381.16 | 210.83 | 1987.73 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23199070700 |  | 100319397 |  | 6716208K | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | HEATHER | 2060 HEATHER WY | 067 | LEX | 2023-10-19 | U128336 | AOC SYST | 2023-07-05 | 2024-01-05 | 2024-12-31 |  | JOSHUA COX | 2023-10-19 | 2023-10-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 32.8 | 4 | 2492.65 | 1616.37 | 773.83 | 102.45 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23200766800 |  | 100330663 |  | 6720212N | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | HENRY CLAY | 305 HENRY CLAY BV | 067 | LEX | 2023-10-19 | U930915 | AOC SYST | 2023-07-13 | 2024-01-12 | 2024-12-31 |  | HMCKUNE | 2023-10-19 | 2023-10-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 24.5 | 6 | 2197.38 | 1196.78 | 480.73 | 75.87 | 444 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212041800 |  | 100339526 |  | 6724212A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | VALDOSTA | 1462 VALDOSTA CT | 067 | LEX | 2023-10-19 | U930915 | AOC SYST | 2023-08-30 | 2024-12-31 | 2024-12-31 |  | TROE | 2023-10-19 | 2023-10-12 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 15.5667 | 6 | 1662.58 | 1280.38 | 160.61 | 221.59 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212262400 |  | 100339501 |  | 6724212A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | HUNTSVILLE | 1454 HUNTSVILLE DR 1FL | 067 | LEX | 2023-10-19 | U930915 | AOC SYST | 2023-08-31 | 2024-02-29 | 2024-12-31 |  | ABLAKE | 2023-10-19 | 2023-10-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 20.6833 | 6 | 1854.13 | 1157.09 | 623.69 | 73.35 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23213473800 |  | 100275820 |  | 6684228C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | AUDUBON | 125 AUDUBON DR | 073 | FRA | 2023-10-19 | U930915 | AOC SYST | 2023-09-07 | 2024-03-07 | 2024-12-31 |  | MCRAIG | 2023-10-19 | 2023-09-22 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 12.5167 | 4 | 2885.85 | 727.89 | 1410.77 | 747.19 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23221649400 |  | 500031636 |  | 6736252I | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | US HIGHWAY 27 | 681 US HIGHWAY 27 S | 097 | CYN | 2023-10-20 | U127414 | U125763 | 2023-10-17 | 2023-12-29 |  |  | ED FOX | 2023-10-19 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3770.62 | 0 | 0 | 0 | 3770.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23222121400 |  | 100310136 |  | 6716208E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | LONGVIEW | 653 LONGVIEW DR | 067 | LEX | 2023-10-20 | U135005 | U139677 | 2023-10-19 | 2023-10-19 | 2023-10-19 |  | RSTRONG | 2023-10-19 | 2023-10-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.3 | 3 | 1816.55 | 1088.26 | 414.86 | 313.43 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23222136400 |  | 100287227 |  | 6720212G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | GAY | 606 GAY PL | 067 | LEX | 2023-10-19 | LSTONE | U139677 | 2023-10-19 | 2023-10-16 | 2023-11-03 |  | LSTONE | 2023-10-19 | 2023-10-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 20.4333 | 6 | 1521.64 | 1167.31 | 255.3 | 99.03 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23222138000 |  | 100346329 |  | 6696212L |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | BELL | 140 BELL AV | 239 | VER | 2023-10-19 | U128410 | U139677 | 2023-10-19 | 2023-10-19 | 2023-10-19 |  | CDESPAIN | 2023-10-19 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 14.4333 | 3 | 3376.15 | 840.44 | 405.11 | 53.3 | 2077.3 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883178200 |  | 100253582 |  | NEW |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | TOM | 2023-10-20 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-10-20 | 2023-10-20 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.4 | 2 | 87.35 | 82.17 | 0 | 5.18 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883179400 |  | 100443572 |  | 7360192T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | TOM | 2023-10-20 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-10-20 | 2023-10-20 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.1333 | 2 | 67.19 | 63.18 | 0 | 4.01 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883183000 |  | 100253577 |  | 7360192T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | TOM | 2023-10-20 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-10-20 | 2023-10-20 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.8833 | 2 | 365.4 | 343.72 | 0 | 21.68 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026290800 |  |  |  | 6720212A | 2399859 | U461383 |  | 557 | EX | INSERT/INSTALL 160'-3"PMLP MN | 2621P | BROADWAY | 901 N BROADWAY ST | 067 | LEX | 2024-01-25 | U136251 | U461383 | 2023-08-30 | 2023-10-16 | 2023-12-15 | 2023-10-20 | LSTANFI | 2023-10-20 | 2023-09-26 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2908 | AMRCB |  | 100 | 055732230262908 | 72.1667 | 1384 | 45549.98 | 4387.56 | 2850.55 | -4586.6 | 31955.68 | 0 | 71.52 | 10871.27 | 173
KY | KY - WEST | 2621 | 23026290900 |  |  |  | 6720212A | 2399859 | U461383 |  | 558 | EX | RETIRE 60' OF 3"BSLP MAIN | 2621P | BROADWAY | 901 N BROADWAY ST | 067 | LEX | 2024-01-19 | U136251 | U461383 | 2023-08-30 | 2023-10-20 | 2023-12-15 | 2023-10-20 | LSTANFI | 2023-10-20 | 2023-09-25 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2909 | AMRCB |  | 100 | 055832230262909 | 137.0833 | 0 | 7967.87 | 7437.94 | 0 | 529.93 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23215915400 |  | 100325432 |  | 6720208E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332680 | 2621P | LAKEWOOD | 1067 LAKEWOOD DR | 067 | LEX | 2023-10-20 | MSHARON | U135005 | 2023-09-20 | 2024-03-19 | 2025-09-30 |  | MSHARON | 2023-10-20 | 2023-10-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 26.8 | 8 | 4203.38 | 1401.72 | 541.57 | 147.8 | 2112.29 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23216222200 |  | 100283341 |  | 6712228F |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HIAWATHA | 209 HIAWATHA TL | 209 | GEO | 2023-10-20 | DCOLLIN | U135005 | 2023-09-21 | 2023-12-29 | 2023-12-31 |  | DCOLLIN | 2023-10-20 | 2023-10-19 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 29.1333 | 4 | 5861.33 | 1772.11 | 305.93 | 969.22 | 2814.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23222438800 |  | 100293818 |  | 6720212A |  |  |  | 566 | EX | SERVICE LINE ABANDON | 2621P | BROADWAY | 905 N BROADWAY ST | 067 | LEX | 2023-10-20 | TROE | U134852 | 2023-10-20 | 2023-10-20 |  |  | TROE | 2023-10-20 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 4.9833 | 3 | 300.06 | 282.17 | 0 | 17.89 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23222438900 |  | 100293817 |  | 6720212A |  |  |  | 565 | EX | SERVICE LINE REPLACE | 2621P | BROADWAY | 907 N BROADWAY ST | 067 | LEX | 2023-10-20 | U930915 | U134852 | 2023-10-20 | 2023-10-20 |  |  | TROE | 2023-10-20 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.3333 | 3 | 698.26 | 520.34 | 144.95 | 32.97 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23222484600 |  | 100308790 |  | 6716208A |  |  |  | 565 | EX | SERVICE LINE REPLACE | 2621P | FURLONG | 818 FURLONG DR | 067 | LEX | 2023-10-23 | U930915 | U134852 | 2023-10-20 | 2023-10-20 | 2023-10-20 |  | HMCKUNE | 2023-10-20 | 2023-10-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.1833 | 4 | 1465.47 | 917.84 | 489.45 | 58.18 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 08727586400 |  | 100241971 |  | 7344168K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | EVERGREEN | 22 S EVERGREEN LN | 071 | LNC | 2023-10-23 | JAHOWARD | RPOLLY | 2008-04-16 | 2023-10-23 | 2023-12-31 |  | JAHOWARD | 2023-10-23 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.1167 | 2 | 1012.71 | 126.18 | 0 | 3.88 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 12983678700 |  | 100241972 |  | 7344168K |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | EVERGREEN | 32 S EVERGREEN LN | 071 | LNC | 2023-10-23 | JAHOWARD | U908784 | 2012-08-09 | 2022-07-01 | 2023-12-31 |  | JAHOWARD | 2023-10-23 | 2022-10-05 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2 | 2 | 988.23 | 99.29 | 0 | 6.29 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883102300 |  | 100242050 |  | 7344168G |  |  |  | 566 | EX | ABN SL-I/I/LGCY STEP 3 D243549 | 2621P | RIVERVIEW | 30 S RIVERVIEW LN | 071 | LNC | 2023-10-23 | JAHOWARD | U120245 | 2021-01-30 | 2023-11-10 | 2025-05-31 |  | JAHOWARD | 2023-10-23 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.3667 | 1 | 1212.9 | 310.55 | 0 | 19.7 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959264400 |  | 100431723 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | 6TH | 2203 6TH ST | 019 | ASH | 2023-10-23 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-23 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2805.73 | 0 | 0 | 0 | 2805.73 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959268300 |  | 100262576 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | HARRISON | 332 HARRISON ST | 019 | ASH | 2023-10-23 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-23 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2531.07 | 0 | 0 | 0 | 2531.07 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960852500 |  | 100250196 |  | 7356248D | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | CANNONSBURG | 8207 CANNONSBURG PK | 019 | CAT | 2023-10-24 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-10-23 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2915.6 | 0 | 0 | 0 | 2915.6 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110825600 |  | 500550922 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | WILLIAMS | 940 WILLIAMS AV | 089 | RAC | 2023-10-24 | U123965 | U134723 | 2022-06-17 | 2023-12-29 |  |  | CJH CASEY PACK | 2023-10-23 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2944.93 | 0 | 0 | 0 | 2944.93 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22979023700 |  | 100260444 |  | 7344160T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | HITE | HITE RD | 071 | HIT | 2023-10-24 | U130172 | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | ANDREW SHEPHERD | 2023-10-23 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - CENTRAL | 2629 | 23026287800 |  |  |  | 6732248D | 2399336 | U128885 |  | 559 | EX | INSTALL 500'-4" PMMP | 2600B | PARIS | PARIS PK | 097 | CYN | 2023-12-20 | U136251 | U128885 | 2023-08-09 | 2023-11-13 | 2023-11-30 | 2023-10-11 | WILL FULKS | 2023-10-23 | 2023-09-07 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00559 | 3200559 |  |  | WP2878 |  |  | 100 | 055932230262878 | 112.55 | 28054 | 175667.6 | 7079.56 | 6778.04 | 1738.66 | 105767.82 | 0 | 636.08 | 53667.44 | 1079
KY | KY - CENTRAL | 2629 | 23026287900 |  |  |  | 6732248D | 2399336 | U128885 |  | 560 | EX | RETIRE 500'-3" PMP | 2600E | PARIS | PARIS PK | 097 | CYN | 2023-12-01 | U136251 | U128885 | 2023-08-09 | 2023-11-30 | 2023-11-30 | 2023-10-11 | WFULKS | 2023-10-23 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00560 | 3200560 |  |  | WP2879 |  |  | 100 | 056032230262879 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168128800 |  | 100274964 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | MAIN | 225 W MAIN ST | 073 | FRA | 2023-10-24 | U461443 | U125763 | 2023-02-20 | 2023-12-29 |  |  | WGRAVES | 2023-10-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1986.58 | 0 | 0 | 0 | 1986.58 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23208757700 |  | 100267759 |  | 7356216D | 1635077 |  |  | 565 | EX | REPLACE SERVICE LINE | 2631D | BOONE | 113 N BOONE ST A1 | 127 | LOU | 2023-10-23 | MCOLLET | AOC SYST | 2023-08-16 | 2024-02-16 | 2024-12-31 |  | MCOLLET | 2023-10-23 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 14.7 | 2 | 2219.79 | 822.69 | 250.09 | 1147.01 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212039000 |  | 100340130 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | COURTLAND | 1801 COURTLAND DR | 067 | LEX | 2023-10-31 | U128381 | AOC SYST | 2023-08-30 | 2024-02-29 | 2024-12-31 |  | LSTANFI | 2023-10-23 | 2023-10-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 12.7167 | 4 | 946.35 | 725.18 | 0 | 221.17 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212042000 |  | 100339671 |  | 6724121E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | ETAWAH | 1484 ETAWAH DR 1 | 067 | LEX | 2023-10-23 | WISHII | AOC SYST | 2023-08-30 | 2024-02-29 | 2024-12-31 |  | WISHII | 2023-10-23 | 2023-10-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 23.8167 | 4 | 2367.71 | 1165.83 | 663.92 | 537.96 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212799900 |  | 100328916 |  | 6720208G |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332615 | 2621P | LAKESHORE | 156 LAKESHORE DR | 067 | LEX | 2023-10-24 | U128336 | U135005 | 2023-09-05 | 2024-03-01 | 2025-09-30 |  | JOSHUA COX | 2023-10-23 | 2023-10-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 52.7167 | 9 | 4855.89 | 2960.1 | 514.94 | 187.6 | 1193.25 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23213624100 |  | 100275771 |  | 6684228D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332997 | 2621P | REILLY | 75 REILLY RD | 073 | FRA | 2023-10-25 | U126332 | U135005 | 2023-09-08 | 2024-03-07 | 2025-09-30 |  | EFGOINS | 2023-10-23 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 23.1167 | 3 | 1220.45 | 1147.7 | 0 | 72.75 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23214172700 |  | 100329773 |  | 6720208D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332619 | 2621P | WILL FANT | 2147 WILL FANT DR | 067 | LEX | 2023-10-23 | HMCKUNE | U135005 | 2023-09-12 | 2024-03-11 | 2025-09-30 |  | HMCKUNE | 2023-10-23 | 2023-10-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.1 | 3 | 1109.92 | 746.12 | 316.52 | 47.28 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23215056900 |  | 100263398 |  | 7352256B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OHIO | 2857 OHIO ST | 019 | ASH | 2023-10-23 | BROBERT | U124420 | 2023-09-15 | 2024-11-18 | 2024-11-18 |  | BROBERT | 2023-10-23 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 13.5 | 2 | 1959.21 | 962.11 | 141.46 | 855.64 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23216223200 |  | 100283339 |  | 6712228E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HIAWATHA | 300 HIAWATHA TL | 209 | GEO | 2023-10-23 | DCOLLIN | U135005 | 2023-09-21 | 2023-12-29 | 2023-12-31 |  | DCOLLIN | 2023-10-23 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 16 | 2 | 5341.28 | 974.35 | 292.71 | 307.34 | 3766.88 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23221904500 |  | 100262572 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | HARRISON | 340 HARRISON ST | 019 | ASH | 2023-10-23 | U124015 | U123235 | 2023-10-18 | 2024-12-31 |  |  | ORA SLONE | 2023-10-23 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2315.39 | 0 | 0 | 0 | 2315.39 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23222138500 |  | 100459747 |  | 7240204G |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | CREAM ALLEY | 7670 CREAM ALLEY RD | 173 | MT | 2023-11-01 | U135005 | U135005 | 2023-10-19 | 2023-12-19 | 2023-12-19 |  | DENNING | 2023-10-23 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 24 | 3 | 1475.95 | 1387.98 | 0 | 87.97 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23222650500 |  | 100322653 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 736 BERRY LN | 067 | LEX | 2023-10-23 | U126530 | U125763 | 2023-10-23 | 2023-12-29 |  |  | JDUNN | 2023-10-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2218.52 | 0 | 0 | 0 | 2218.52 | 0 | 0 | 0
KY | KY - EAST | 2631 | 17529168200 |  | 100418571 |  | 7340268J |  |  |  | 565 | EX | RELOCATE SERVICE LINE | 2621P | VINE | 43 VINE ST | 089 | S S | 2023-10-24 | MCOLLET | U461492 | 2017-07-31 | 2017-08-31 |  |  | MCOLLET | 2023-10-24 | 2023-09-26 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 25.55 | 7 | 4124.04 | 1471 | 458.96 | 2194.08 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19723712700 |  | 100306357 |  | 6712212L |  |  |  | 565 | EX | SERVICE LINE REPLACE/MMO 10/23 | 2621P | MASON HEADLEY | 938 MASON HEADLEY RD | 067 | LEX | 2023-10-24 | KKINDER | U131723 | 2019-07-12 | 2019-08-30 |  |  | KKINDER | 2023-10-24 | 2023-07-31 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 33.2667 | 11 | 3511.01 | 1793.35 | 509.47 | 134.94 | 1073.25 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883145700 |  | 100268662 |  | 7352156P |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | DOW HUNTER | DOW HUNTER RD | 071 | BET | 2023-10-24 | JAHOWARD | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JAHOWARD | 2023-10-24 | 2022-10-06 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 8.0833 | 3 | 1373.62 | 461.46 | 0 | 29.51 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883247300 |  | 100259308 |  | 7344136T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW3836 | PW3836 | 071 | BEV | 2023-10-24 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | ANDREW SHEPHERD | 2023-10-24 | 2023-10-24 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.8 | 1 | 128.61 | 120.95 | 0 | 7.66 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883305400 |  | 100260608 |  | 7348144T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PM3 | PM3 | 071 | GRE | 2023-10-24 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BLAKE MULLINS | 2023-10-24 | 2023-10-23 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.2667 | 1 | 72.92 | 68.56 | 0 | 4.36 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883308700 |  | 100260456 |  | 7344136T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW3836 | PW3836 | 071 | BEV | 2023-10-24 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | ANDREW SHEPHERD | 2023-10-24 | 2023-10-24 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.0667 | 1 | 146.46 | 137.72 | 0 | 8.74 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959268500 |  | 100262588 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | HARRISON | 341 HARRISON ST | 019 | ASH | 2023-10-24 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-24 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2521.68 | 0 | 0 | 0 | 2521.68 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959268600 |  | 100262590 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | HARRISON | 349 HARRISON ST | 019 | ASH | 2023-10-24 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-24 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2472.09 | 0 | 0 | 0 | 2472.09 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110825900 |  | 100462100 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | WILLIAMS | 979 WILLIAMS AV | 089 | RAC | 2023-10-25 | U123965 | U134723 | 2022-06-17 | 2023-12-29 |  |  | CJH CASEY PACK | 2023-10-24 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3410.7 | 0 | 0 | 0 | 3410.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129066100 |  | 100262589 |  | 7352256D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HARRISON | 345 HARRISON ST | 019 | ASH | 2023-10-24 | U124015 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ORA SLONE | 2023-10-24 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1038.41 | 0 | 0 | 0 | 1038.41 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22979046400 |  | 100429286 |  | 7356156I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | FLOYD | 500 FLOYD ST | 071 | BET | 2023-10-24 | JAHOWARD | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | JAHOWARD | 2023-10-24 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.75 | 1 | 1722.83 | 218.84 | 0 | 13.87 | 1490.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166670300 |  | 100322621 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 701 BERRY LN | 067 | LEX | 2023-10-24 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-10-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1380.08 | 0 | 0 | 0 | 1380.08 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168137300 |  | 100274965 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | MAIN | 227 W MAIN ST | 073 | FRA | 2023-10-24 | U461443 | U125763 | 2023-02-20 | 2023-12-29 |  |  | WGRAVES | 2023-10-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3327.21 | 0 | 0 | 0 | 3327.21 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212040000 |  | 100340129 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | COURTLAND | 1805 COURTLAND DR | 067 | LEX | 2023-10-25 | U123688 | AOC SYST | 2023-08-30 | 2024-02-29 | 2024-12-31 |  | LSTANFI | 2023-10-24 | 2023-10-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 9.7333 | 4 | 1107.54 | 550.72 | 407.69 | 149.13 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23213801000 |  | 100275781 |  | 6684228G |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332998 | 2621P | REILLY | 206 REILLY RD | 073 | FRA | 2023-10-25 | U126332 | U135005 | 2023-09-11 | 2024-03-08 | 2025-09-30 |  | EFGOINS | 2023-10-24 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 19.8 | 3 | 1884.94 | 1161.31 | 0 | 73.63 | 650 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23221374600 |  | 100288454 |  | 6720212H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309318 | 2621P | CRICKLEWOOD | 575 CRICKLEWOOD DR | 067 | LEX | 2023-10-25 | U123688 | U135005 | 2023-10-16 | 2023-10-16 | 2023-11-03 |  | LSTANFI | 2023-10-24 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.15 | 3 | 1386.53 | 683.83 | 557.16 | 145.54 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23221948200 |  | 500085907 |  | 7344148I |  |  |  | 565 | EX | EXTEND SERVICE LINE | 2621P | REED | 36 REED ST | 071 | DRI | 2023-10-24 | JCKIRK | U135005 | 2023-10-18 | 2023-12-18 | 2023-12-18 |  | JCKIRK | 2023-10-24 | 2023-10-24 |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26330031 | 16 | 2 | 970.52 | 912.67 | 0 | 57.85 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23222588900 |  | 100312780 |  | 6716208E |  |  |  | 565 | EX | SERVICE LINE REPLACE | 2621P | STRATFORD | 553 STRATFORD DR | 067 | LEX | 2023-10-25 | U123688 | U134852 | 2023-10-22 | 2023-10-20 | 2023-10-20 |  | RJCRAWF | 2023-10-24 | 2023-10-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 30.9333 | 6 | 1689.46 | 1434.92 | 163.6 | 90.94 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883077700 |  | 100268689 |  | 7356156E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | OFFICIAL | OFFICIAL RD | 071 | BET | 2023-10-25 | JAHOWARD | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JAHOWARD | 2023-10-25 | 2022-10-06 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 12.8333 | 4 | 1664.98 | 735.57 | 0 | 46.76 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883108600 |  | 100268750 |  | 7352156L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | 3RD | 3RD AV | 071 | BET | 2023-10-25 | JAHOWARD | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JAHOWARD | 2023-10-25 | 2022-11-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 4.6 | 3 | 1558.98 | 255.05 | 0 | 16.3 | 1287.63 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883156300 |  | 100443322 |  | 7352140T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | P8 | P8 | 071 | BEA | 2023-10-26 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BLAKE MULLINS | 2023-10-25 | 2023-10-25 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.0167 | 1 | 239.26 | 105.43 | 0 | 133.83 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883232600 |  | 100261904 |  | 7328132T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW5764 | PW5764 | 119 | GAR | 2023-10-26 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | ANDREW SHEPHERD | 2023-10-25 | 2023-10-25 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.1667 | 1 | 225 | 211.59 | 0 | 13.41 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883312000 |  | 100407906 |  | 7344140T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | P2 | P2 | 071 | HI | 2023-10-26 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | ANDREW SHEPHERD | 2023-10-25 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - EAST | 2631 | 21959267500 |  | 500173956 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | FERRY | 347 FERRY ST | 019 | ASH | 2023-10-25 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-25 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2555.69 | 28.73 | 0 | 19.48 | 2507.48 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959267600 |  | 100262601 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | FERRY | 348 FERRY ST | 019 | ASH | 2023-10-25 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-25 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1997.38 | 0 | 0 | 0 | 1997.38 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959269300 |  | 100262595 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | POLLARD | 2001 POLLARD RD | 019 | ASH | 2023-10-25 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-25 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1892.91 | 0 | 0 | 0 | 1892.91 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960852800 |  | 100250200 |  | 7356248D | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | CANNONSBURG | 7917 CANNONSBURG RD | 019 | CAT | 2023-10-26 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-10-25 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2001.57 | 0 | 0 | 0 | 2001.57 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110825800 |  | 100462099 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | WILLIAMS | 969 WILLIAMS AV | 089 | RAC | 2023-10-25 | U123965 | U134723 | 2022-06-17 | 2023-12-29 |  |  | CJH CASEY PACK | 2023-10-25 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1989.72 | 0 | 0 | 0 | 1989.72 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129015200 |  | 100414730 |  | 7332132T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | TRACE CANEY | 683 TRACE CANEY RD | 119 | PIP | 2023-10-26 | U130172 | U130722 | 2022-09-05 | 2022-12-30 |  |  | ANDREW SHEPHERD | 2023-10-25 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - WEST | 2621 | 23166676800 |  | 100322658 |  | 6720208A | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 809 PROVIDENCE RD | 067 | LEX | 2023-10-26 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-10-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2872.38 | 0 | 0 | 0 | 2872.38 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168131700 |  | 100274984 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | SAINT CLAIR | 213 SAINT CLAIR ST | 073 | FRA | 2023-10-26 | U461443 | U125763 | 2023-02-20 | 2023-12-29 |  |  | WGRAVES | 2023-10-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3266.59 | 0 | 0 | 0 | 3266.59 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23187230700 |  | 100265371 |  | 7348260P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D259874 | 2621P | STATE RT 5 | 3102 STATE RT 5 | 019 | ASH | 2023-10-25 | MCOLLET | U125208 | 2023-05-10 | 2023-11-09 | 2025-05-31 |  | MCOLLET | 2023-10-25 | 2023-09-28 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 24.9667 | 5 | 4606.64 | 1496.32 | 329.6 | 1145.24 | 1635.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23193794300 |  | 100323323 |  | 6716208L | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | WINDERMERE | 3066 WINDERMERE RD | 067 | LEX | 2023-10-26 | U930915 | AOC SYST | 2023-06-08 | 2023-12-08 | 2024-12-31 |  | RJCRAWF | 2023-10-25 | 2023-10-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 19.5 | 6 | 1463.14 | 1059.01 | 337.03 | 67.1 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23207420200 |  | 100434397 |  | 6720208E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | COOPER | 1117 COOPER DR | 067 | LEX | 2023-10-25 | U128336 | AOC SYST | 2023-08-09 | 2024-02-09 | 2024-12-31 |  | JOSHUA COX | 2023-10-25 | 2023-10-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 26.8667 | 4 | 3554.86 | 1446.4 | 1535.78 | 91.68 | 481 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210315600 |  | 100269858 |  | 6732252O | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | CLADORBON | 104 CLADORBON DR | 097 | CYN | 2023-10-25 | U126604 | U125763 | 2023-08-23 | 2023-12-29 |  |  | WILL FULKS | 2023-10-25 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2138.82 | 0 | 0 | 0 | 2138.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212038500 |  | 100340128 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | COURTLAND | 1809 COURTLAND DR | 067 | LEX | 2023-10-28 | U123688 | AOC SYST | 2023-08-30 | 2024-02-29 | 2024-12-31 |  | LSTANFI | 2023-10-25 | 2023-10-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 16.6167 | 3 | 1659.01 | 955.45 | 407.45 | 296.11 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23217458800 |  | 100286852 |  | 6720212B |  |  |  | 565 | EX | REPLACE STEEL SERVICE LINE | 2621P | DEVONIA | 245 DEVONIA AV | 067 | LEX | 2023-10-25 | TROE | U135005 | 2023-09-28 | 2023-12-28 | 2023-12-28 |  | TROE | 2023-10-25 | 2023-10-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.0333 | 4 | 1300.89 | 981.47 | 257.23 | 62.19 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23221691500 |  | 500576030 |  | 6744208J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MARKET | 632 MARKET ST | 049 | WIN | 2023-10-25 | NRICHIE | U135005 | 2023-10-17 | 2023-11-17 | 2023-11-17 |  | NRICHIE | 2023-10-25 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 24 | 3 | 3575.92 | 1394.38 | 18.15 | 596.94 | 1566.45 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23221914200 |  | 100357303 |  | 7240280J |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BRIDGEVILLE | 628 BRIDGEVILLE RD | 023 | GER | 2023-10-25 | DSTAGGS | U135005 | 2023-10-18 | 2023-12-29 |  |  | DSTAGGS | 2023-10-25 | 2023-10-23 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 16.85 | 4 | 1365.73 | 985.4 | 0 | 380.33 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 04595448000 |  | 100266599 | 08 | X1729-47 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | COMBS | COMBS DR | 195 | COA | 2023-10-26 | JAHOWARD | DHANSFO | 2004-12-22 | 2023-10-26 | 2023-12-31 |  | JAHOWARD | 2023-10-26 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 8 | 1 | 1376.43 | 464.35 | 0 | 29.43 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883148600 |  | 100426622 |  | IGC1 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | GENERAL DELIVE | GENERAL DELIVE | 119 | TAL | 2023-10-27 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BRIAN PREECE | 2023-10-26 | 2023-10-26 |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 1.55 | 1 | 96.87 | 91.1 | 0 | 5.77 | 0 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883245100 |  | 100426621 |  | IGC1 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | GENERAL DELIVE | GENERAL DELIVE | 119 | TAL | 2023-10-27 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BRIAN PREECE | 2023-10-26 | 2023-10-26 |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 1.8 | 1 | 111.07 | 104.45 | 0 | 6.62 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883309800 |  | 100414729 |  | 7348152T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW4527 | PW4527 | 071 | HON | 2023-10-27 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BLAKE MULLINS | 2023-10-26 | 2023-10-26 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.2333 | 1 | 294.35 | 276.8 | 0 | 17.55 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883317300 |  | 100426055 |  | 7344136T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW3836 | PW3836 | 071 | BEV | 2023-10-27 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | ANDREW SHEPHERD | 2023-10-26 | 2023-10-26 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.1167 | 1 | 221.42 | 208.2 | 0 | 13.22 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21900187100 |  | 100344611 |  | 6700224O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | WINTER | 119 N WINTER ST | 239 | MID | 2023-10-27 | U128410 | AOC SYST | 2021-04-02 | 2021-09-29 | 2022-12-31 |  | CDESPAIN | 2023-10-26 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 63.95 | 7 | 11753.63 | 3853.75 | 456.81 | 244.4 | 7198.67 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959267100 |  | 100262605 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | FERRY | 332 FERRY ST | 019 | ASH | 2023-10-26 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2072.2 | 82.3 | 0 | 39.7 | 1950.2 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959267400 |  | 100262602 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | FERRY | 344 FERRY ST | 019 | ASH | 2023-10-26 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2571.26 | 0 | 0 | 0 | 2571.26 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959276600 |  | 100262606 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | FERRY | 328 FERRY ST | 019 | ASH | 2023-10-26 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1950.2 | 0 | 0 | 0 | 1950.2 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110825500 |  | 100460617 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | WILLIAMS | 920 WILLIAMS AV | 089 | RAC | 2023-10-27 | U123965 | U134723 | 2022-06-17 | 2023-12-29 |  |  | CJH CASEY PACK | 2023-10-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2703.76 | 0 | 0 | 0 | 2703.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166676300 |  | 100322702 |  | 6720208A | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 800 PROVIDENCE RD | 067 | LEX | 2023-10-26 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-10-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2480.11 | 0 | 0 | 0 | 2480.11 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168132000 |  | 100274978 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | SAINT CLAIR | 223 SAINT CLAIR ST | 073 | FRA | 2023-10-26 | U461443 | U125763 | 2023-02-20 | 2023-12-29 |  |  | WGRAVES | 2023-10-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2489.53 | 0 | 0 | 0 | 2489.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23191601500 |  | 100323881 |  | 6716204D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | CAHABA | 816 CAHABA RD | 067 | LEX | 2023-10-27 | U930915 | AOC SYST | 2023-05-31 | 2023-11-30 | 2024-12-31 |  | RJCRAWF | 2023-10-26 | 2023-10-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 19.2333 | 7 | 1419.28 | 1061.15 | 290.88 | 67.25 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23194240000 |  | 100325793 |  | 6720208A |  |  |  | 565 | EX | SERVICE LINE - REPLACE MMO | 2621P | EASTOVER | 140 EASTOVER DR | 067 | LEX | 2023-10-26 | U128336 | U135005 | 2023-06-12 | 2023-12-29 |  |  | JOSHUA COX | 2023-10-26 | 2023-06-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 33.4167 | 11 | 5169.22 | 1842.82 | 503.96 | 115.79 | 2706.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23197732300 |  | 100256580 |  | 356152E |  |  |  | 565 | EX | GRADE 1 REPLACE SERV LINE | 2621P | 1ST | 185 1ST ST | 071 | HAR | 2023-10-28 | U123688 | U129939 | 2023-06-28 | 2023-06-28 | 2023-06-28 |  | JCKIRK | 2023-10-26 | 2023-06-28 |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 26.4667 | 5 | 1875.41 | 1696.44 | 75.2 | 103.77 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210315700 |  | 100269762 |  | 6732252O | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | CLADORBON | 105 CLADORBON DR | 097 | CYN | 2023-10-26 | U126604 | U125763 | 2023-08-23 | 2023-12-29 |  |  | WILL FULKS | 2023-10-26 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3083.27 | 0 | 0 | 0 | 3083.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212033100 |  | 100340159 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | COURTLAND | 1814 COURTLAND DR | 067 | LEX | 2023-10-28 | U123688 | AOC SYST | 2023-08-30 | 2024-02-29 | 2024-12-31 |  | LSTANFI | 2023-10-26 | 2023-10-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 10.2333 | 3 | 1085.39 | 587.71 | 407.45 | 90.23 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212040200 |  | 100340127 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | COURTLAND | 1813 COURTLAND DR | 067 | LEX | 2023-10-28 | U123688 | AOC SYST | 2023-08-30 | 2024-02-29 | 2024-12-31 |  | LSTANFI | 2023-10-26 | 2023-10-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 6.4833 | 3 | 992.66 | 381.97 | 412.73 | 197.96 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212263500 |  | 100339663 |  | 6724121E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | ETAWAH | 1470 ETAWAH DR 2 | 067 | LEX | 2023-10-26 | WISHII | AOC SYST | 2023-08-31 | 2024-02-29 | 2024-12-31 |  | WISHII | 2023-10-26 | 2023-10-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 24.3167 | 4 | 2028.97 | 1184.77 | 380.05 | 464.15 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212263800 |  | 100417297 |  | 6724121E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | ETAWAH | 1440 ETAWAH DR A | 067 | LEX | 2023-10-26 | ATWILLI | AOC SYST | 2023-08-31 | 2024-02-29 | 2024-12-31 |  | ATWILLI | 2023-10-26 | 2023-10-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 18.2167 | 4 | 1954.45 | 837.68 | 492.8 | 623.97 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212271300 |  | 100339411 |  | 6724212A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | HUNTSVILLE | 1461 HUNTSVILLE DR A | 067 | LEX | 2023-10-26 | ABLAKE | AOC SYST | 2023-08-31 | 2024-02-29 | 2024-12-31 |  | ABLAKE | 2023-10-26 | 2023-10-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 14.5833 | 3 | 1528.31 | 812 | 664.83 | 51.48 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23213478500 |  | 100275803 |  | 6684228G | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | AUDUBON | 124 AUDUBON DR | 073 | FRA | 2023-10-26 | MCRAIG | AOC SYST | 2023-09-07 | 2024-03-07 | 2024-12-31 |  | MCRAIG | 2023-10-26 | 2023-10-19 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 27.6833 | 9 | 3225.29 | 1554.89 | 543.26 | 1127.14 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23216223000 |  | 100283338 |  | 6712228E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HIAWATHA | 212 HIAWATHA TL | 209 | GEO | 2023-10-26 | CHERNDO | U135005 | 2023-09-21 | 2023-12-29 | 2023-12-31 |  | CHERNDO | 2023-10-26 | 2023-10-24 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 29.0333 | 5 | 6384.11 | 1745.97 | 0 | 580.61 | 4057.53 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23220570300 |  | 100281461 |  | 6712232N |  |  |  | 566 | EX | ABANDON SL/DEMO PER CUST | 2621P | GANO | 121 GANO AV | 209 | GEO | 2023-10-26 | CHERNDO | U139707 | 2023-10-11 | 2023-10-31 | 2023-11-22 |  | CHERNDO | 2023-10-26 | 2023-10-25 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 10.1333 | 5 | 598.3 | 562.64 | 0 | 35.66 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23220844300 |  | 100315384 |  | 6716208C |  |  |  | 566 | EX | RETIRE S/L BUILDING DEMO | 2621P | UNIVERSITY | 122 UNIVERSITY AV | 067 | LEX | 2023-10-26 | KKINDER | U461383 | 2023-10-12 | 2023-11-17 | 2023-11-17 |  | KKINDER | 2023-10-26 | 2023-10-26 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.5 | 2 | 969.57 | 896.7 | 16.04 | 56.83 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23221704700 |  | 100273926 |  | 6680228L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DEVILS HOLLOW | 534 DEVILS HOLLOW RD | 073 | FRA | 2023-10-26 | EFGOINS | U135005 | 2023-10-17 | 2023-12-15 | 2023-12-17 |  | EFGOINS | 2023-10-26 | 2023-10-23 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 21.3 | 5 | 1543.41 | 1146.69 | 0 | 72.72 | 324 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23223213200 |  | 100269763 |  | 6732252O | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | CLADORBON | 107 CLADORBON DR | 097 | CYN | 2023-10-26 | U126604 | U123235 | 2023-10-26 | 2024-12-31 |  |  | WILL FULKS | 2023-10-26 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2580.28 | 0 | 0 | 0 | 2580.28 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883212000 |  | 100247861 |  | 7364188A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | MAIN | MAIN ST | 159 | INE | 2023-10-27 | U126332 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | J. PARKS | 2023-10-27 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - EAST | 2633 | 21883310400 |  | 100261771 |  | 7340136T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW1905A | PW1905A | 119 | TOP | 2023-10-27 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | ANDREW SHEPHERD | 2023-10-27 | 2023-10-26 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 6.7667 | 1 | 485.68 | 456.74 | 0 | 28.94 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959266300 |  | 100262594 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | CRAFT | 2013 CRAFT ST | 019 | ASH | 2023-10-27 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-27 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2524.33 | 0 | 0 | 0 | 2524.33 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959266400 |  | 100262568 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | CRAFT | 2016 CRAFT ST | 019 | ASH | 2023-10-27 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-27 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1892.91 | 0 | 0 | 0 | 1892.91 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960853800 |  | 100462475 |  | 7360248A | 2180320 |  |  | 565 | EX | REPLACE SL W/21-0261304-00 | 2600B | COURT | 3501 COURT ST | 019 | CAT | 2023-10-27 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH DEREK CRAGER | 2023-10-27 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3099.57 | 0 | 0 | 0 | 3099.57 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110825400 |  | 100433961 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | WILLIAMS | 910 WILLIAMS AV | 089 | RAC | 2023-10-27 | U123965 | U134723 | 2022-06-17 | 2023-12-29 |  |  | CJH CASEY PACK | 2023-10-27 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1988.09 | 0 | 0 | 0 | 1988.09 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22979023100 |  | 100259309 |  | 7344136T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | RILEYS BRANCH | 313 RILEYS BRANCH | 071 | BEV | 2023-10-30 | U130172 | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | ANDREW SHEPHERD | 2023-10-27 | 2023-10-27 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.9 | 1 | 207.12 | 194.78 | 0 | 12.34 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166672300 |  | 100322656 |  | 6720208A | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | ELDEMERE | 1115 ELDEMERE RD | 067 | LEX | 2023-10-27 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-10-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3421.86 | 0 | 0 | 0 | 3421.86 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23218509000 |  | 100267465 |  | 7352260E |  |  |  | 565 | EX | RELO SERVICE LINE:ENCROACHMENT | 2621P | MOUNT SAVAGE | 112 MOUNT SAVAGE DR | 089 | ASH | 2023-10-27 | JROGER1 | U135005 | 2023-10-03 | 2023-12-01 | 2023-12-03 |  | JROGER1 | 2023-10-27 | 2023-10-25 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 45.8167 | 8 | 3812.03 | 2259.72 | 299.76 | 1252.55 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23218734000 |  | 100293481 |  | 6720216I |  |  |  | 565 | EX | RPLC SL AND RISER | 2621P | LA SALLE | 1547 LA SALLE RD | 067 | LEX | 2023-10-30 | U930915 | U135005 | 2023-10-03 | 2023-12-29 |  |  | TROE | 2023-10-27 | 2023-10-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25.15 | 4 | 1923.27 | 1429.8 | 176.11 | 317.36 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23222189100 |  | 100299678 |  | 6716212B | 1968251 |  |  | 565 | EX | RPLC SL/23026292500 | 2600B | LISLE INDUSTRI | 114 LISLE INDUSTRI AV | 067 | LEX | 2023-10-27 | U124003 | U125763 | 2023-10-19 | 2023-12-29 |  |  | BPULLIAM/FISHEL | 2023-10-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3552.44 | 0 | 0 | 0 | 3552.44 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23222803400 |  | 100252567 |  | 7348264P |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | POWELL | 606 POWELL LN | 089 | FLA | 2023-10-27 | BROBERT | U131169 | 2023-10-24 | 2023-10-24 |  |  | BROBERT | 2023-10-27 | 2023-10-24 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 24.6 | 4 | 3369.01 | 1328.67 | 267.15 | 693.19 | 1080 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23222853700 |  | 500218736 |  | 7240208E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KIDDVILLE | 425 KIDDVILLE RD | 173 | MT | 2023-10-30 | U930915 | U132761 | 2023-10-24 | 2024-12-31 |  |  | DENNING | 2023-10-27 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 18.55 | 3 | 1462.29 | 1070.45 | 0 | 67.84 | 324 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23223187600 |  | 100265370 |  | 7352260M |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | CRANCE | 3119 CRANCE CT | 019 | ASH | 2023-10-30 | U123688 | U129939 | 2023-10-26 | 2023-10-26 |  |  | MCOLLET | 2023-10-27 | 2023-10-26 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 21.4167 | 4 | 5277.99 | 1212.59 | 333.87 | 1862.41 | 1869.12 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23223206000 |  | 100260853 |  | 7352256G |  |  |  | 565 | EX | REPLACE SERVICE LINE - D259812 | 2621P | LADOKA | 3421 LADOKA ST | 019 | ASH | 2023-10-27 | BROBERT | U135005 | 2023-10-26 | 2023-10-26 | 2023-10-26 |  | BROBERT | 2023-10-27 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 12.0833 | 2 | 1287.58 | 562.29 | 311.41 | 413.88 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23223223300 |  | 100344831 |  | 6700224P |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | OAK | 109 OAK ST | 239 | MID | 2023-10-27 | U128410 | U131169 | 2023-10-26 | 2023-10-26 | 2023-10-26 |  | CDESPAIN | 2023-10-27 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 37 | 4 | 4329.39 | 2204.49 | 1514.04 | 610.86 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23223477300 |  | 100417166 |  | 6720204C |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LATONIA | 1291 LATONIA PR | 067 | LEX | 2023-10-27 | U128336 | U134852 | 2023-10-27 | 2023-10-20 | 2023-11-08 |  | JOSHUA COX | 2023-10-27 | 2023-10-27 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 32.4167 | 6 | 1916.47 | 1722.48 | 84.81 | 109.18 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883182400 |  | 100253579 |  | 7360192T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | TOM | 2023-10-31 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-10-30 | 2023-10-30 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.85 | 1 | 110.27 | 103.69 | 0 | 6.58 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883183300 |  | 100440048 |  | 7360192T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | TOM | 2023-10-31 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-10-30 | 2023-10-30 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.35 | 1 | 140.06 | 131.72 | 0 | 8.34 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 22129057600 |  | 100271098 |  | NEW |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | ASBURY | 2670 ASBURY RD | 023 | AUG | 2023-11-14 | U461383 | U130722 | 2022-09-05 | 2022-12-30 |  |  | SDADAMS | 2023-10-30 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 6.0667 | 3 | 347.2 | 326.49 | 0 | 20.71 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026289100 |  |  |  | 6716212F | 2070048 | U122858 |  | 577 | EX | INSTALL FENCE | 2621M | OLD FRANKFORT | 1313 OLD FRANKFORT PK | 067 | LEX | 2023-10-30 | U123258 | U122858 | 2023-08-22 | 2023-12-28 | 2023-12-31 | 2023-10-30 | WSHIMFESSEL | 2023-10-30 | 2023-10-25 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00577 | 3200577 |  |  | WP2891 |  |  | 100 | 057732230262891 | 32 | 4 | 23214.65 | 2081.3 | 0 | 332.22 | 18750.59 | 0 | 13.49 | 2037.05
KY | KY - CENTRAL | 2629 | 23026302800 |  |  |  | 6740208C | 2301220 | U128885 |  | 557 | EX | EMER - INSTALL 2'-3" PMP | 2621P | WESTCHESTER | 17 WESTCHESTER LANE | 049 | WIN | 2023-11-03 | U128132 | U128885 | 2023-10-25 | 2023-10-18 | 2023-10-30 | 2023-10-17 | WDENNING | 2023-10-30 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3028 |  |  | 100 | 055732230263028 |  | 2 | 3993.16 | 1908.47 | 804.67 | 120.98 | 0 | 0 | 7.47 | 1151.57 | 2
KY | KY - CENTRAL | 2629 | 23026302900 |  |  |  | 6740208C | 2301220 | U128885 |  | 558 | EX | EMER - RETIRE 2'-3" PMP | 2621P | WESTCHESTER | 17 WESTCHESTER LANE | 049 | WIN | 2023-11-02 | U128132 | U128885 | 2023-10-25 | 2023-10-27 | 2023-10-30 | 2023-10-17 | WDENNING | 2023-10-30 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP3029 |  |  | 100 | 055832230263029 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23218000600 |  | 100261883 |  | 7324124T |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | CRIMSON | 111 CRIMSON DR | 119 | BRI | 2023-10-30 | U130172 | U133234 | 2023-09-29 | 2023-10-13 | 2023-10-29 |  | JOHN HOWARD | 2023-10-30 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 8 | 1 | 493.78 | 464.35 | 0 | 29.43 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23223612800 |  | 100252806 |  | 7348264O |  |  |  | 565 | EX | SERVICE LINE REPAIR | 2621P | PINE | 1020 PINE ST | 089 | FLA | 2023-10-30 | MCOLLET | U134902 | 2023-10-30 | 2023-10-30 | 2023-10-30 |  | MCOLLET | 2023-10-30 | 2023-10-30 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 15.9167 | 4 | 1400.1 | 913.86 | 160.49 | 325.75 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 12992532300 |  | 500025955 |  | 7324132F | 2290467 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | SR550 | SR550 | 119 | HIN | 2023-10-31 | U130172 | U125765 | 2012-10-10 | 2022-07-01 | 2023-12-31 |  | JOHN HOWARD | 2023-10-31 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - EAST | 2633 | 21883272900 |  | 100433171 |  | 7328132T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW5764 | PW5764 | 119 | GAR | 2023-11-01 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | ANDREW SHEPHERD | 2023-10-31 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - EAST | 2633 | 21883299800 |  | 100261906 |  | 7328132T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW5764 | PW5764 | 119 | GAR | 2023-11-01 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | ANDREW SHEPHERD | 2023-10-31 | 2023-10-19 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 7.9 | 1 | 564.22 | 530.6 | 0 | 33.62 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883310000 |  | 100260651 |  | 7352152T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | P1027 | P1027 | 071 | HAR | 2023-10-31 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BRIAN PREECE | 2023-10-31 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 7 | 2 | 426.37 | 400.96 | 0 | 25.41 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883315500 |  | 100261907 |  | 7328132T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW5764 | PW5764 | 119 | GAR | 2023-11-01 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | ANDREW SHEPHERD | 2023-10-31 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - EAST | 2631 | 21959266600 |  | 100455911 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | FERRY | 310 FERRY ST | 019 | ASH | 2023-10-31 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-31 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2501.46 | 0 | 0 | 0 | 2501.46 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959267200 |  | 100262604 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | FERRY | 336 FERRY ST | 019 | ASH | 2023-10-31 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-31 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2305.28 | 0 | 0 | 0 | 2305.28 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959267300 |  | 100262603 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | FERRY | 340 FERRY ST | 019 | ASH | 2023-10-31 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-10-31 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1916.5 | 0 | 0 | 0 | 1916.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110825700 |  | 100257000 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | WILLIAMS | 959 WILLIAMS AV | 089 | RAC | 2023-10-31 | U123965 | U134723 | 2022-06-17 | 2023-12-29 |  |  | CJH CASEY PACK | 2023-10-31 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2891.05 | 0 | 0 | 0 | 2891.05 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026296800 |  |  |  | 6716200H | 2300514 | U122858 |  | 561 | EX | EMER - INSTALL 40'-4" PMMP | 2600E | BRANNON | BRANNON RD | 113 | NIC | 2023-11-09 | U128132 | U122858 | 2023-09-29 | 2023-12-21 | 2023-12-30 | 2023-10-25 | STEVE CANOY | 2023-10-31 | 2023-10-09 | 2023-10-09 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP2968 |  |  | 100 | 056132230262968 | 91.05 | 1170 | 47320.11 | 5172.85 | 4737.51 | 4398.95 | 16479.65 | 0 | 109.89 | 16421.26 | 90
KY | KY - WEST | 2621 | 23026296900 |  |  |  | 6716200H | 2300514 | U122858 |  | 562 | EX | EMER - RETIRE 40'-4" CSMP | 2600E | BRANNON | BRANNON RD | 113 | NIC | 2023-11-08 | U128132 | U122858 | 2023-09-29 | 2023-12-29 | 2023-12-30 | 2023-10-25 | STEVE CANOY | 2023-10-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP2969 |  |  | 100 | 056232230262969 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166668100 |  | 100322632 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 657 BERRY LN | 067 | LEX | 2023-11-01 | U123111 | U125763 | 2023-02-14 | 2023-12-29 |  |  | LYN STAFFORD | 2023-10-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2094.1 | 0 | 0 | 0 | 2094.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210313800 |  | 100269851 |  | 6732252P | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | BROADWAY | 404 BROADWAY AV | 097 | CYN | 2023-10-31 | U126604 | U125763 | 2023-08-23 | 2023-12-29 |  |  | WILL FULKS | 2023-10-31 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2192.25 | 0 | 0 | 0 | 2192.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212034000 |  | 100340123 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | COURTLAND | 1829 COURTLAND DR | 067 | LEX | 2023-11-01 | U135005 | AOC SYST | 2023-08-30 | 2024-02-29 | 2024-12-31 |  | LSTANFI | 2023-10-31 | 2023-10-26 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 4.5 | 3 | 581.83 | 227.99 | 339.39 | 14.45 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212037500 |  | 100340125 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | COURTLAND | 1821 COURTLAND DR | 067 | LEX | 2023-11-01 | U135005 | AOC SYST | 2023-08-30 | 2024-02-29 | 2024-12-31 |  | LSTANFI | 2023-10-31 | 2023-10-26 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 12.65 | 3 | 1180.93 | 727.36 | 407.45 | 46.12 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23213470600 |  | 100275769 |  | 6684228C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | COMPTON | 127 COMPTON DR | 073 | FRA | 2023-10-31 | MCRAIG | AOC SYST | 2023-09-07 | 2024-03-07 | 2024-12-31 |  | MCRAIG | 2023-10-31 | 2023-10-20 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 15.85 | 4 | 2077.72 | 972.54 | 434.13 | 671.05 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23217467400 |  | 100461295 |  | 6684228J | 2394831 |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | MAIN | 324 W MAIN ST 2F | 073 | FRA | 2023-11-03 | U135005 | U129939 | 2023-09-28 | 2023-09-28 |  |  | EFGOINS | 2023-10-31 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 5.9667 | 2 | 342.85 | 322.41 | 0 | 20.44 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883171700 |  | 100253416 |  | 7360192T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | TOM | 2023-11-01 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-01 | 2023-10-17 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 4.45 | 2 | 299.27 | 282.34 | 0 | 16.93 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883173000 |  | 100253578 |  | 7360192T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | TOM | 2023-11-09 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-01 | 2023-11-01 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.8 | 1 | 144.59 | 136.97 | 0 | 7.62 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883175800 |  | 100253588 |  | 7360192T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | TOM | 2023-11-01 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-01 | 2023-11-01 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.3167 | 1 | 104.45 | 98.94 | 0 | 5.51 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883193800 |  | 100253572 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | INE | 2023-11-01 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-01 | 2023-11-01 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.6 | 1 | 48.21 | 45.67 | 0 | 2.54 | 0 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883240900 |  | 100426612 |  | X172459 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | GENERAL DELIVE | GENERAL DELIVE | 119 | VES | 2023-11-01 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BRIAN PREECE | 2023-11-01 |  |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 4.7167 | 1 | 363.86 | 344.65 | 0 | 19.21 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959266700 |  | 100262608 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | FERRY | 320 FERRY ST | 019 | ASH | 2023-11-01 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-11-01 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2686.65 | 0 | 0 | 0 | 2686.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959266900 |  | 100262607 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | FERRY | 324 FERRY ST | 019 | ASH | 2023-11-01 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-11-01 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2693.39 | 0 | 0 | 0 | 2693.39 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959267000 |  | 100262610 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | FERRY | 329 FERRY ST | 019 | ASH | 2023-11-01 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-11-01 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2882.11 | 0 | 0 | 0 | 2882.11 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110827200 |  | 100460392 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | TEAKWOOD | 597 TEAKWOOD DR | 089 | RAC | 2023-11-01 | U123965 | U134723 | 2022-06-17 | 2023-12-29 |  |  | CJH DEREK CRAGER | 2023-11-01 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2013.31 | 0 | 0 | 0 | 2013.31 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110827300 |  | 100460247 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | TEAKWOOD | 599 TEAKWOOD DR L1 | 089 | RAC | 2023-11-01 | U123965 | U134723 | 2022-06-17 | 2023-12-29 |  |  | CJH CASEY PACK | 2023-11-01 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1713.38 | 0 | 0 | 0 | 1713.38 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026281400 |  | 501309025 |  | 6712228I | 2398438 | U126783 |  | 555 | EX | INSTALL 1865'-2"/4" PMMP | 2600B | HOURGLASS | HOURGLASS LN LT13 | 209 | GEO | 2023-12-11 | U128132 | U126783 | 2023-06-27 | 2023-10-17 | 2023-11-17 | 2023-11-01 | R.HUMPHREYS | 2023-11-01 | 2023-10-09 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2814 |  |  | 100 | 055532230262814 | 99.5 | 24349 | 90143.57 | 5606 | 7930.75 | 1248.27 | 46955.97 | 0 | 596.75 | 27805.83 | 1873
KY | KY - CENTRAL | 2629 | 23026302300 |  |  |  | 6752176B | 2301164 | U461383 |  | 584 | CO | RETIRE PAPER GAUGE | 2629M | HWY 977 | HWY 977 | 151 | WAC | 2024-03-11 |  | U461383 | 2023-10-23 | 2024-12-13 | 2024-12-15 | 2023-11-01 | TC ENERGY | 2023-11-01 | 2023-10-31 |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00584 | 3200584 |  |  | WP3023 |  |  | 100 | 058432230263023 | 9.1167 | 0 | 835.24 | 640.06 | 0 | 195.18 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168131900 |  | 100274979 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | SAINT CLAIR | 221 SAINT CLAIR ST 1F | 073 | FRA | 2023-11-02 | U461443 | U125763 | 2023-02-20 | 2023-12-29 |  |  | WGRAVES | 2023-11-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2265.09 | 0 | 0 | 0 | 2265.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23192217100 |  | 100412208 |  | 6716204D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | OVERBROOK | 3316 OVERBROOK DR | 067 | LEX | 2023-11-01 | U930915 | AOC SYST | 2023-06-01 | 2023-12-01 | 2024-12-31 |  | RJCRAWF | 2023-11-01 | 2023-10-25 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 14.6333 | 5 | 1338.57 | 1025.09 | 255.63 | 57.85 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23208383300 |  | 100357955 |  | 6740232N | 2286363 |  |  | 565 | EX | RPLC SL/22026164000 | 2600B | SCOTT | 336 SCOTT AV | 017 | PAR | 2023-11-09 | U127414 | U125763 | 2023-08-15 | 2023-12-29 |  |  | ED FOX | 2023-11-01 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1590.76 | 0 | 0 | 0 | 1590.76 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210313900 |  | 100269846 |  | 6732252P | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | BROADWAY | 405 BROADWAY AV | 097 | CYN | 2023-11-01 | U126604 | U125763 | 2023-08-23 | 2023-12-29 |  |  | WILL FULKS | 2023-11-01 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3010.03 | 0 | 0 | 0 | 3010.03 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210314000 |  | 100269845 |  | 6732252P | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | BROADWAY | 407 BROADWAY AV | 097 | CYN | 2023-11-01 | U126604 | U125763 | 2023-08-23 | 2023-12-29 |  |  | WILL FULKS | 2023-11-01 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2558.12 | 0 | 0 | 0 | 2558.12 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210314200 |  | 100269843 |  | 6732252P | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | BROADWAY | 409 BROADWAY AV | 097 | CYN | 2023-11-01 | U126604 | U125763 | 2023-08-23 | 2023-12-29 |  |  | WILL FULKS | 2023-11-01 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2851.72 | 0 | 0 | 0 | 2851.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212033800 |  | 100340117 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | COURTLAND | 1853 COURTLAND DR | 067 | LEX | 2023-11-03 | U135005 | AOC SYST | 2023-08-30 | 2024-02-29 | 2024-12-31 |  | LSTANFI | 2023-11-01 | 2023-10-26 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 1.65 | 2 | 575.26 | 95.29 | 450.99 | 28.98 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212037900 |  | 100339386 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | ANNISTON | 1507 ANNISTON DR | 067 | LEX | 2023-11-01 | ABLAKE | AOC SYST | 2023-08-30 | 2024-02-29 | 2024-12-31 |  | ABLAKE | 2023-11-01 | 2023-10-24 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 37.7667 | 6 | 3574.32 | 2610.15 | 374.38 | 145.79 | 444 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212041200 |  | 100340163 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | COURTLAND | 1830 COURTLAND DR | 067 | LEX | 2023-11-03 | U135005 | AOC SYST | 2023-08-30 | 2024-02-29 | 2024-12-31 |  | LSTANFI | 2023-11-01 | 2023-10-26 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 15.3 | 3 | 1785.18 | 1107.66 | 415.45 | 262.07 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212042100 |  | 100422081 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | AUGUSTA | 1880 AUGUSTA DR 1 | 067 | LEX | 2023-11-01 | WISHII | AOC SYST | 2023-08-30 | 2024-02-29 | 2024-12-31 |  | WISHII | 2023-11-01 | 2023-11-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 20 | 2 | 2246.36 | 1450.85 | 48.46 | 747.05 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212042600 |  | 100340122 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | COURTLAND | 1833 COURTLAND DR | 067 | LEX | 2023-11-03 | U135005 | AOC SYST | 2023-08-30 | 2024-02-29 | 2024-12-31 |  | LSTANFI | 2023-11-01 | 2023-10-26 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 1.55 | 3 | 511.38 | 84.81 | 407.45 | 19.12 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23213715700 |  | 100275768 |  | 6684228C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | COMPTON | 206 COMPTON DR | 073 | FRA | 2023-11-01 | MCRAIG | AOC SYST | 2023-09-08 | 2024-03-08 | 2024-12-31 |  | MCRAIG | 2023-11-01 | 2023-10-31 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 6.3833 | 5 | 772.72 | 454.09 | 15.13 | 303.5 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23213716400 |  | 100275765 |  | 6684228C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | COMPTON | 208 COMPTON DR | 073 | FRA | 2023-11-03 | U135005 | AOC SYST | 2023-09-08 | 2024-03-08 | 2024-12-31 |  | MCRAIG | 2023-11-01 | 2023-09-21 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 40.6667 | 6 | 4936.78 | 3164.08 | 632.85 | 1139.85 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23220587500 |  | 100242103 |  | 7356252D | 2397978 |  |  | 565 | EX | RPLC SL/23026277600 | 2600B | HARRIS | 947 HARRIS ST | 019 | CAT | 2023-11-01 | U123965 | U125763 | 2023-10-11 | 2023-12-29 |  |  | CJH JAMES ROWE | 2023-11-01 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1261.2 | 0 | 0 | 0 | 1261.2 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23224028200 |  | 100265839 |  | 7348252D |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | GILLUM | 6213 GILLUM ST | 019 | ASH | 2023-11-03 | U135005 | U135005 | 2023-11-01 | 2023-12-01 | 2023-12-01 |  | RECUMP | 2023-11-01 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 12.2 | 2 | 1346.36 | 911.5 | 201.06 | 233.8 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23224032100 |  | 100313950 |  | 6716212O |  |  |  | 565 | EX | SERVICE LINE REPLACE | 2621P | AMERICAN | 125 AMERICAN AV | 067 | LEX | 2023-11-01 | U128336 | U134852 | 2023-11-01 | 2023-11-01 |  |  | JOSHUA COX | 2023-11-01 | 2023-11-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 29.3667 | 3 | 2835.7 | 2185.44 | 528.47 | 121.79 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23224032500 |  | 100313952 |  | 6716212N |  |  |  | 565 | EX | SERVICE LINE REPLACE | 2621P | AMERICAN | 133 AMERICAN AV | 067 | LEX | 2023-11-07 | U135005 | U134852 | 2023-11-01 | 2023-11-01 |  |  | KKINDER | 2023-11-01 | 2023-11-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.4833 | 3 | 6702.34 | 4300.97 | 1913.56 | 487.81 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 03540967300 |  | 100256466 | 12 | 7352152-D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | OLD HAROLD | OLD HAROLD RD | 071 | HAR | 2023-11-02 | JAHOWARD | DHANSFO | 2003-05-27 | 2023-11-02 | 2023-12-31 |  | JAHOWARD | 2023-11-02 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 10.8333 | 1 | 1775.63 | 845.83 | 0 | 47.15 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 11887968200 |  | 100256438 |  | 7352152D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | SR979 | SR979 | 071 | HAR | 2023-11-02 | JAHOWARD | U906609 | 2011-02-11 | 2022-07-01 | 2023-12-31 |  | JAHOWARD | 2023-11-02 | 2022-11-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 12.5167 | 4 | 2475.61 | 693.36 | 0 | 307.7 | 1474.55 | 0 | 0 | 0
KY | KY - EAST | 2633 | 14211139600 |  | 100256470 |  | 7352152D |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | OLD HAROLD | OLD HAROLD RD | 071 | HAR | 2023-11-02 | JAHOWARD | U125208 | 2014-04-07 | 2023-11-02 | 2023-12-31 |  | JAHOWARD | 2023-11-02 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.033333 | 1 | 887.59 | 4.68 | 0 | 0.26 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883169700 |  | 100423531 |  | 7348156T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PM197 | PM197 | 071 | DAN | 2023-11-06 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BLAKE MULLINS | 2023-11-02 | 2023-11-01 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.8167 | 2 | 820.36 | 411.06 | 0 | 409.3 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883330200 |  | 100260546 |  | 7348144T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW5295 | PW5295 | 071 | CRA | 2023-11-06 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BLAKE MULLINS | 2023-11-02 | 2023-10-27 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.9667 | 2 | 401.87 | 207.03 | 0 | 194.84 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959266500 |  | 100261130 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | FERRY | 308 FERRY ST | 019 | ASH | 2023-11-02 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-11-02 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1876.06 | 0 | 0 | 0 | 1876.06 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959267700 |  | 100423367 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | FERRY | 376 FERRY ST | 019 | ASH | 2023-11-02 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-11-02 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2802.61 | 0 | 0 | 0 | 2802.61 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110824300 |  | 100438644 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | TEAKWOOD | 593 TEAKWOOD DR | 089 | RAC | 2023-11-03 | U123965 | U134723 | 2022-06-17 | 2023-12-29 |  |  | CJH DEREK CRAGER | 2023-11-02 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2716.28 | 0 | 0 | 0 | 2716.28 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110827100 |  | 100438080 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | TEAKWOOD | 595 TEAKWOOD DR | 089 | RAC | 2023-11-03 | U123965 | U134723 | 2022-06-17 | 2023-12-29 |  |  | CJH CASEY PACK | 2023-11-02 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2629.62 | 0 | 0 | 0 | 2629.62 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22129091500 |  | 500584600 |  | 6696212F | 9723006 |  |  | 566 | VO | ABANDON SL - IDLE/INACTIVE | 2621P | POPLAR | 412 POPLAR ST B | 239 | VER | 2023-11-07 |  | U130722 | 2022-09-05 | 2022-12-30 |  |  |  | 2023-11-02 | 2023-10-19 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 16.4667 | 5 | 1774.14 | 1068.38 | 0 | 63.04 | 642.72 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23026302500 |  |  |  | 7248280G | 2301164 | U461383 |  | 584 | EX | RETIRE PAPER GAUGE | 2632M | HIGHLAND | 3020 HIGHLAND DR | 161 | MAY | 2024-05-06 | U123258 | U461383 | 2023-10-23 | 2023-12-15 | 2023-12-15 | 2023-11-02 | JHOBBS | 2023-11-02 | 2023-10-31 |  | F | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00584 | 3200584 |  |  | WP3025 |  |  | 100 | 058432230263025 | 13.2833 | 0 | 994.29 | 941.37 | 0 | 52.92 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166676500 |  | 100322703 |  | 6720208A | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 804 PROVIDENCE RD | 067 | LEX | 2023-11-03 | U123111 | U125763 | 2023-02-14 | 2023-12-29 |  |  | LYN STAFFORD | 2023-11-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2385.61 | 0 | 0 | 0 | 2385.61 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166676600 |  | 100322659 |  | 6720208A | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 805 PROVIDENCE RD | 067 | LEX | 2023-11-02 | U123111 | U125763 | 2023-02-14 | 2023-12-29 |  |  | LYN STAFFORD | 2023-11-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1938.13 | 0 | 0 | 0 | 1938.13 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179205000 |  | 100265160 |  | 7352260O | 2286985 |  |  | 565 | EX | RPLC SL/22026172300 | 2600B | WHEATLEY | 421 WHEATLEY RD | 019 | ASH | 2023-11-02 | U124015 | U125763 | 2023-04-05 | 2023-12-29 |  |  | ORA SLONE | 2023-11-02 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2531.07 | 0 | 0 | 0 | 2531.07 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179205100 |  | 100265157 |  | 7352260O | 2286985 |  |  | 565 | EX | RPLC SL/22026172300 | 2600B | WHEATLEY | 425 WHEATLEY RD | 019 | ASH | 2023-11-02 | U124015 | U125763 | 2023-04-05 | 2023-12-29 |  |  | ORA SLONE | 2023-11-02 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1960.31 | 0 | 0 | 0 | 1960.31 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23184041000 |  | 100467869 |  | 6680224G |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333609 | 2621P | HIGHVIEW | 1642 HIGHVIEW CR | 073 | FRA | 2023-11-03 | U135005 | U125208 | 2023-04-27 | 2023-10-26 | 2025-04-30 |  | EFGOINS | 2023-11-02 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 16 | 2 | 1767.33 | 1214.61 | 432.61 | 120.11 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23191605700 |  | 100334962 |  | 6720212P | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | BENWOOD | 1737 BENWOOD DR | 067 | LEX | 2023-11-02 | LSTONE | AOC SYST | 2023-05-31 | 2023-11-30 | 2024-12-31 |  | LSTONE | 2023-11-02 | 2023-10-27 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 17.05 | 4 | 1334.54 | 1206.41 | 60.47 | 67.66 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23193015800 |  | 500015257 |  | 6696212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332962 | 2621P | COLCHESTER | 214 COLCHESTER DR | 239 | VER | 2023-11-06 | U128410 | U135005 | 2023-06-06 | 2023-12-05 | 2025-06-30 |  | CDESPAIN | 2023-11-02 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.0333 | 2 | 1844.07 | 451.97 | 0 | 25.22 | 1366.88 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23199018400 |  | 100350682 |  | 6744208O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333619 | 2621P | COLBY | 501 COLBY RD | 049 | WIN | 2023-11-03 | U135005 | U135005 | 2023-07-05 | 2024-01-05 | 2025-07-31 |  | DENNING | 2023-11-02 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 15.25 | 3 | 3896.36 | 2813.22 | 343.49 | 147.65 | 592 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23203501700 |  | 100280558 |  | 6688228I | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | HICKORY | 136 HICKORY DR | 073 | FRA | 2023-11-02 | MCRAIG | AOC SYST | 2023-07-24 | 2024-01-24 | 2024-12-31 |  | MCRAIG | 2023-11-02 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 9.35 | 2 | 1670.92 | 699.51 | 389.35 | 582.06 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23207708900 |  | 100338707 |  | 6720212F | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | BELTLINE | 152 BELTLINE AV | 067 | LEX | 2023-11-02 | LSTONE | AOC SYST | 2023-08-10 | 2024-02-09 | 2024-12-31 |  | LSTONE | 2023-11-02 | 2023-10-25 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 8.2 | 3 | 798.51 | 567.02 | 199.55 | 31.94 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23208096700 |  | 100284024 |  | 6712228N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332608 | 2621P | ETTER | 173 ETTER LN | 209 | GEO | 2023-11-03 | U135005 | U135005 | 2023-08-14 | 2024-02-09 | 2025-08-31 |  | DCOLLIN | 2023-11-02 | 2023-10-13 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 28.5 | 4 | 6995.55 | 2111.97 | 248.76 | 751.22 | 3883.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23208382900 |  | 100357961 |  | 6740232N | 2286363 |  |  | 565 | EX | RPLC SL/22026164000 | 2600B | MAYSVILLE | 348 MAYSVILLE ST | 017 | PAR | 2023-11-10 | U127414 | U125763 | 2023-08-15 | 2023-12-29 |  |  | ED FOX | 2023-11-02 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1991.17 | 0 | 0 | 0 | 1991.17 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23208383100 |  | 100357952 |  | 6740232N | 2286363 |  |  | 565 | EX | RPLC SL/22026164000 | 2600B | SCOTT | 318 SCOTT AV | 017 | PAR | 2023-11-09 | U127414 | U125763 | 2023-08-15 | 2023-12-29 |  |  | ED FOX | 2023-11-02 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1845.58 | 0 | 0 | 0 | 1845.58 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23208383200 |  | 100357954 |  | 6740232N | 2286363 |  |  | 565 | EX | RPLC SL/22026164000 | 2600B | SCOTT | 326 SCOTT AV | 017 | PAR | 2023-11-09 | U127414 | U125763 | 2023-08-15 | 2023-12-29 |  |  | ED FOX | 2023-11-02 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3055.06 | 0 | 0 | 0 | 3055.06 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210313700 |  | 100269849 |  | 6732252P | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | BROADWAY | 401 BROADWAY AV | 097 | CYN | 2023-11-02 | U126604 | U125763 | 2023-08-23 | 2023-12-29 |  |  | WILL FULKS | 2023-11-02 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3536.11 | 0 | 0 | 0 | 3536.11 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212267000 |  | 100421770 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | AUGUSTA | 1890 AUGUSTA DR 1 | 067 | LEX | 2023-11-02 | WISHII | AOC SYST | 2023-08-31 | 2024-02-29 | 2024-12-31 |  | WISHII | 2023-11-02 | 2023-10-24 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 19.3833 | 3 | 3257.77 | 1383.31 | 1180.94 | 693.52 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23221073800 |  | 100258443 |  | 7344264C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D244434 | 2621P | ALTAWOOD | 112 ALTAWOOD RD | 089 | RAC | 2023-11-02 | JKEENER | U135005 | 2023-10-13 | 2024-04-30 |  |  | JKEENER | 2023-11-02 | 2023-11-02 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 19.0833 | 3 | 1967.11 | 1386.01 | 0 | 581.1 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23223808800 |  | 100448554 |  | 6720212M |  |  |  | 566 | EX | ABANDON SL | 2621P | CENTRAL | 702 CENTRAL AV 1 | 067 | LEX | 2023-11-02 | SSHIMFE | U137585 | 2023-10-31 | 2023-10-31 |  |  | SSHIMFE | 2023-11-02 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.76667 | 1 | 56.57 | 53.58 | 0 | 2.99 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23223809000 |  | 100448518 |  | 6720212M |  |  |  | 566 | EX | ABANDON SL | 2621P | CENTRAL | 702 CENTRAL AV 5 | 067 | LEX | 2023-11-02 | SSHIMFE | U137585 | 2023-10-31 | 2023-10-31 |  |  | SSHIMFE | 2023-11-02 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.016667 | 1 | 1.48 | 1.4 | 0 | 0.08 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23223809200 |  | 100448519 |  | 6720212M |  |  |  | 566 | EX | ABANDON SL | 2621P | CENTRAL | 702 CENTRAL AV 6 | 067 | LEX | 2023-11-02 | SSHIMFE | U137585 | 2023-10-31 | 2023-10-31 |  |  | SSHIMFE | 2023-11-02 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.033333 | 1 | 2.23 | 2.11 | 0 | 0.12 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23223809400 |  | 100448528 |  | 6720212M |  |  |  | 566 | EX | ABANDON SL | 2621P | CENTRAL | 702 CENTRAL AV 2 | 067 | LEX | 2023-11-02 | SSHIMFE | U137585 | 2023-10-31 | 2023-10-31 |  |  | SSHIMFE | 2023-11-02 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.05 | 1 | 3.66 | 3.47 | 0 | 0.19 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23223809600 |  | 100448529 |  | 6720212M |  |  |  | 566 | EX | ABANDON SL | 2621P | CENTRAL | 702 CENTRAL AV 3 | 067 | LEX | 2023-11-02 | SSHIMFE | U137585 | 2023-10-31 | 2023-10-31 |  |  | SSHIMFE | 2023-11-02 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.05 | 1 | 3.66 | 3.47 | 0 | 0.19 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23223809700 |  | 100448530 |  | 6720212M |  |  |  | 566 | EX | ABANDON SL | 2621P | CENTRAL | 702 CENTRAL AV 4 | 067 | LEX | 2023-11-02 | SSHIMFE | U137585 | 2023-10-31 | 2023-10-31 |  |  | SSHIMFE | 2023-11-02 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.033333 | 1 | 2.23 | 2.11 | 0 | 0.12 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23224037700 |  | 100269848 |  | 6732252P | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | BROADWAY | 403 BROADWAY AV | 097 | CYN | 2023-11-02 | U126604 | U123235 | 2023-11-01 | 2024-12-31 |  |  | WILL FULKS | 2023-11-02 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26290032 |  | 1 | 3780.46 | 0 | 0 | 0 | 3780.46 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23224077900 |  | 100357962 |  | 6740232N | 2286363 |  |  | 565 | EX | RPLC SL/22026164000 | 2600B | MAYSVILLE | 342 MAYSVILLE ST | 017 | PAR | 2023-11-30 | U127414 | U125763 | 2023-11-01 | 2023-12-29 |  |  | ED FOX | 2023-11-02 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2244.37 | 0 | 0 | 0 | 2244.37 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23224281000 |  | 501342871 |  | 7356252H | 2397978 |  |  | 565 | EX | RPLC SL/23026277600 | 2600B | 12TH | 100 12TH ST MAINT | 019 | CAT | 2023-11-03 | U123965 | U123235 | 2023-11-02 | 2024-12-31 |  |  | CJH JAMES ROWE | 2023-11-02 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1149.99 | 0 | 0 | 0 | 1149.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 13121089900 |  | 100408679 |  | 6716204A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NICHOLASVILLE | 3401 NICHOLASVILLE RD STE 107 | 067 | LEX | 2023-11-03 | U128336 | U124967 | 2013-03-01 | 2018-02-27 |  |  | JOSHUA COX | 2023-11-03 | 2023-02-06 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 22.3667 | 11 | 1410.1 | 1332.07 | 0 | 78.03 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883084500 |  | 100250468 |  | 7372188T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | BEA | 2023-11-06 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-03 | 2023-11-03 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.85 | 1 | 68.34 | 64.73 | 0 | 3.61 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883162400 |  | 100250497 |  | 7376188T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | BEA | 2023-11-06 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-03 | 2023-11-03 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.3 | 1 | 104.46 | 98.94 | 0 | 5.52 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959269400 |  | 100262191 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | POLLARD | 2108 POLLARD RD | 019 | ASH | 2023-11-03 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-11-03 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1812.03 | 0 | 0 | 0 | 1812.03 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959269600 |  | 100262194 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | POLLARD | 2120 POLLARD RD | 019 | ASH | 2023-11-03 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-11-03 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1980.53 | 0 | 0 | 0 | 1980.53 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110824100 |  | 100460476 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | TEAKWOOD | 589 TEAKWOOD DR L6 | 089 | RAC | 2023-11-03 | U123965 | U134723 | 2022-06-17 | 2023-12-29 |  |  | CJH DEREK CRAGER | 2023-11-03 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2030.16 | 0 | 0 | 0 | 2030.16 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110824200 |  | 100438645 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | TEAKWOOD | 591 TEAKWOOD DR | 089 | RAC | 2023-11-03 | U123965 | U134723 | 2022-06-17 | 2023-12-29 |  |  | CJH CASEY PACK | 2023-11-03 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2639.73 | 0 | 0 | 0 | 2639.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026303700 |  |  |  | 6720204C | 2301286 | U134275 |  | 557 | EX | EMER - INSTALL 5' OF 2" PMMP | 2621P | LATONIA | 1291 LATONIA PK | 067 | LEX | 2023-11-13 | U128132 | U134275 | 2023-10-30 | 2023-11-03 | 2024-06-30 | 2023-10-27 | JOSHUA COX | 2023-11-03 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3037 |  |  | 100 | 055732230263037 | 2.2667 | 6 | 579.53 | 168.86 | 376.04 | 9.41 | 0 | 0 | 0 | 25.22 | 3
KY | KY - WEST | 2621 | 23026303800 |  |  |  | 6720204C | 2301286 | U134275 |  | 558 | EX | EMER - RETIRE 3' OF 2" PAMP | 2621P | LATONIA | 1291 LATONIA PK | 067 | LEX | 2023-11-13 | U128132 | U134275 | 2023-10-30 | 2023-11-03 | 2024-06-30 | 2023-10-27 | JOSHUA COX | 2023-11-03 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP3038 |  |  | 100 | 055832230263038 | 1.3333 | 0 | 114.6 | 108.55 | 0 | 6.05 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166672400 |  | 100322657 |  | 6720208A | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | ELDEMERE | 1119 ELDEMERE RD | 067 | LEX | 2023-11-03 | U123111 | U125763 | 2023-02-14 | 2023-12-29 |  |  | LYN STAFFORD | 2023-11-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1675.24 | 0 | 0 | 0 | 1675.24 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23208385600 |  | 100357959 |  | 6740232N | 2286363 |  |  | 565 | EX | RPLC SL/22026164000 | 2600B | WASHINGTON | 429 WASHINGTON ST | 017 | PAR | 2023-11-09 | U127414 | U125763 | 2023-08-15 | 2023-12-29 |  |  | ED FOX | 2023-11-03 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1900.98 | 0 | 0 | 0 | 1900.98 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23220346700 |  | 100291803 |  | 6720216G |  |  |  | 565 | EX | REPLACE STEEL SERVICE LINE | 2621P | BISKOFF | 715 BISKOFF CT | 067 | LEX | 2023-11-03 | TROE | U135005 | 2023-10-10 | 2024-12-31 |  |  | TROE | 2023-11-03 | 2023-10-26 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.5833 | 3 | 1423.98 | 1036.5 | 329.45 | 58.03 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23220587300 |  | 100242100 |  | 7356252D | 2397978 |  |  | 565 | EX | RPLC SL/23026277600 | 2600B | HARRIS | 943 HARRIS ST | 019 | CAT | 2023-11-03 | U123965 | U125763 | 2023-10-11 | 2023-12-29 |  |  | CJH JAMES ROWE | 2023-11-03 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2515.04 | 0 | 0 | 0 | 2515.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23221371800 |  | 100466272 |  | 6712208L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D341463 | 2621P | DARDANELLES | 625 DARDANELLES DR | 067 | LEX | 2023-11-03 | KKINDER | U135005 | 2023-10-16 | 2024-04-12 | 2025-10-31 |  | KKINDER | 2023-11-03 | 2023-11-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.3667 | 3 | 1007.32 | 899.35 | 57.51 | 50.46 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23223031100 |  | 100330809 |  | 6720212N |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | SHERMAN | 229 SHERMAN AV | 067 | LEX | 2023-11-03 | U930915 | U133234 | 2023-10-25 | 2023-11-08 | 2023-11-24 |  | RJCRAWF | 2023-11-03 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 25.8833 | 4 | 1902.88 | 1766.43 | 38.01 | 98.44 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 09814203100 |  | 100266620 |  | ADVISE |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | US23 | US23 | 195 | COA | 2023-12-05 | U130172 | DMCCULL | 2009-12-09 | 2022-07-01 | 2024-12-31 |  | JAHOWARD | 2023-11-05 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.6833 | 1 | 539.53 | 511.51 | 0 | 28.02 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 08728252800 |  | 100256485 |  | X1728-12 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | 4TH | 4TH ST | 071 | HAR | 2023-11-06 | JAHOWARD | SSUTHER | 2008-04-21 | 2022-07-01 | 2023-12-31 |  | JAHOWARD | 2023-11-06 | 2022-10-06 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.5167 | 4 | 1557.11 | 80.09 | 0 | 2.47 | 1474.55 | 0 | 0 | 0
KY | KY - EAST | 2633 | 11900860500 |  | 500150808 |  | 7352156L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | RAILROAD | RAILROAD AV | 071 | JUS | 2023-11-06 | JAHOWARD | U123853 | 2011-04-12 | 2023-11-06 | 2023-12-31 |  | JAHOWARD | 2023-11-06 | 2022-11-17 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 7.7833 | 2 | 1913.57 | 592.89 | 0 | 33.05 | 1287.63 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883236000 |  | 100421787 |  | 7328132T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW5764 | PW5764 | 119 | GAR | 2023-11-06 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | ANDREW SHEPHERD | 2023-11-06 | 2023-11-06 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.5833 | 1 | 317.4 | 300.64 | 0 | 16.76 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959269700 |  | 100262567 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | POLLARD | 2201 POLLARD RD | 019 | ASH | 2023-11-06 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-11-06 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1983.9 | 0 | 0 | 0 | 1983.9 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22026218600 |  |  |  | 7356152E |  | U461383 |  | 583 | EX | INSTALL NEW 1ST CUT REGULATOR | 2633M | US23 UPPER HAROLD 1419 | US23 UPPER HAROLD 1419 | 071 | HAR | 2023-11-10 | U123258 | U461383 | 2022-08-16 | 2023-12-01 | 2023-12-01 | 2023-11-06 | MRYAN | 2023-11-06 | 2022-08-31 |  | F | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00583 | 3200583 |  |  | WP2186 |  |  | 100 | 058332220262186 | 25 | 6 | 3338.51 | 1960.5 | 32.12 | 1006.33 | 0 | 0 | 17.01 | 322.55
KY | KY - EAST | 2633 | 22026218700 |  |  |  | 7356152E |  | U461383 |  | 584 | EX | RETIRE 1ST CUT REGULATOR | 2633M | US23 UPPER HAROLD 1419 | US23 UPPER HAROLD 1419 | 071 | HAR | 2023-11-10 | U123258 | U461383 | 2022-08-16 | 2023-12-01 | 2023-12-01 | 2023-11-06 | MRYAN | 2023-11-06 | 2023-10-31 |  | F | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00584 | 3200584 |  |  | WP2187 |  |  | 100 | 058432220262187 | 14.65 | 0 | 1644.86 | 1022.6 | 10.03 | 612.23 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110824000 |  | 100440367 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | TEAKWOOD | 587 TEAKWOOD DR | 089 | RAC | 2023-11-06 | U123965 | U134723 | 2022-06-17 | 2023-12-29 |  |  | CJH DANNY DAVIS | 2023-11-06 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2636.36 | 0 | 0 | 0 | 2636.36 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026301600 |  |  |  | 6700224O | 2294088 | U461383 |  | 909 | EX | INSTAL NEW MODEM | 2623M | WASSAU | 120 WASSAU AL | 239 | MID | 2023-11-06 | U123258 | U461383 | 2023-10-20 | 2023-12-29 | 2023-12-31 | 2023-11-06 | BRANDON LONE | 2023-11-06 |  |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00909 | 3200909 |  |  | WP3016 |  |  | 100 | 090932230263016 | 8 | 0 | 652.23 | 616.33 | 0 | 34.35 | 0 | 0 | 1.55 | 0
KY | KY - WEST | 2623 | 23026301700 |  |  |  | 6700224O | 2294088 | U461383 |  | 910 | EX | RETIRE MODEM | 2623M | WASSAU | 120 WASSAU AL | 239 | MID | 2023-11-06 | U123258 | U461383 | 2023-10-20 | 2023-12-29 | 2023-12-31 | 2023-11-06 | BLONE | 2023-11-06 | 2023-11-03 |  | F | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00910 | 3200910 |  |  | WP3017 |  |  | 100 | 091032230263017 | 2.3667 | 0 | 365.2 | 194.49 | 0 | 170.71 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179204800 |  | 100265159 |  | 7352260O | 2286985 |  |  | 565 | EX | RPLC SL/22026172300 | 2600B | WHEATLEY | 417 WHEATLEY RD | 019 | ASH | 2023-11-06 | U124015 | U125763 | 2023-04-05 | 2023-12-29 |  |  | ORA SLONE | 2023-11-06 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2571.51 | 0 | 0 | 0 | 2571.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23190387300 |  | 100323706 |  | 6716204C | 1635077 |  |  | 565 | EX | AOC ATMOS - WORK WITH UPG MC | 2621D | BRIARCLIFF | 3410 BRIARCLIFF CR | 067 | LEX | 2023-11-13 | U135005 | AOC SYST | 2023-05-23 | 2023-11-22 | 2024-12-31 |  | RJCRAWF | 2023-11-06 | 2023-09-29 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 26.3167 | 6 | 1955.65 | 1851.66 | 0 | 103.99 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23208385700 |  | 100357975 |  | 6740232N | 2286363 |  |  | 565 | EX | RPLC SL/22026164000 | 2600B | SCOTT | 406 SCOTT AV | 017 | PAR | 2023-11-06 | U126532 | U125763 | 2023-08-15 | 2023-12-29 |  |  | LESLIE SHARON | 2023-11-06 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 8.25 | 1 | 4595.75 | 625.62 | 0 | 34.88 | 3935.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210313600 |  | 100269850 |  | 6732252O | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | 5TH | 111 5TH ST | 097 | CYN | 2023-11-06 | U126604 | U125763 | 2023-08-23 | 2023-12-29 |  |  | WILL FULKS | 2023-11-06 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2391.05 | 0 | 0 | 0 | 2391.05 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210314500 |  | 100269855 |  | 6732252P | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | BROADWAY | 412 BROADWAY AV | 097 | CYN | 2023-11-06 | U126604 | U125763 | 2023-08-23 | 2023-12-29 |  |  | WILL FULKS | 2023-11-06 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1931.45 | 0 | 0 | 0 | 1931.45 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23213256700 |  | 100339615 |  | 6724212A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | MARIETTA | 1821 MARIETTA DR | 067 | LEX | 2023-11-06 | WISHII | AOC SYST | 2023-09-06 | 2024-03-06 | 2024-12-31 |  | WISHII | 2023-11-06 | 2023-10-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 16.5833 | 3 | 2076.63 | 1182.45 | 295.19 | 598.99 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23218903700 |  | 100329433 |  | 6720208C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332634 | 2621P | SAINT MATHILDA | 2143 SAINT MATHILDA DR | 067 | LEX | 2023-11-06 | HMCKUNE | U135005 | 2023-10-04 | 2024-04-02 | 2025-10-31 |  | HMCKUNE | 2023-11-06 | 2023-10-31 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.85 | 3 | 736.51 | 552.49 | 153.13 | 30.89 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23220587400 |  | 100242086 |  | 7356252D | 2397978 |  |  | 565 | EX | RPLC SL/23026277600 | 2600B | HARRIS | 945 HARRIS ST | 019 | CAT | 2023-11-06 | U123965 | U125763 | 2023-10-11 | 2023-12-29 |  |  | CJH JAMES ROWE | 2023-11-06 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2568.14 | 0 | 0 | 0 | 2568.14 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23223826300 |  | 100348131 |  | 6748208I |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | MUTUAL | 207 MUTUAL AV | 049 | WIN | 2023-11-07 | U930915 | U133234 | 2023-10-31 | 2023-11-13 | 2023-11-29 |  | DENNING | 2023-11-06 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 22.65 | 3 | 1947.08 | 1844.27 | 0 | 102.81 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23224052200 |  | 100270855 |  | 6736248A |  |  |  | 565 | EX | SERVICE LINE REPLACE | 2621P | ELMARCH | 418 S ELMARCH AV | 097 | CYN | 2023-11-06 | NRICHIE | U134852 | 2023-11-01 | 2023-11-01 | 2023-11-01 |  | NRICHIE | 2023-11-06 | 2023-11-02 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 19.35 | 6 | 2081.38 | 1551.54 | 280.17 | 249.67 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 08728253900 |  | 100268817 |  | X-1723-43 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | OHIO | OHIO ST | 071 | JUS | 2023-11-07 | JAHOWARD | SSUTHER | 2008-04-21 | 2023-11-07 | 2023-12-31 |  | JAHOWARD | 2023-11-07 | 2023-10-27 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 14.8833 | 2 | 2145.3 | 1000.84 | 0 | 59.32 | 1085.14 | 0 | 0 | 0
KY | KY - EAST | 2633 | 11908177100 |  | 100259379 |  | 7344148J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | 1ST | 1ST ST | 071 | DRI | 2023-11-07 | JAHOWARD | U907001 | 2011-05-24 | 2023-11-07 | 2023-12-31 |  | JAHOWARD | 2023-11-07 | 2022-10-06 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.5 | 2 | 1721.56 | 27.42 | 0 | 1.53 | 1692.61 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883093200 |  | 100266412 |  | 7360152T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW4516 | PW4516 | 195 | PIK | 2023-11-08 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BLAKE MULLINS | 2023-11-07 | 2023-09-27 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 6.6 | 2 | 733.87 | 453.62 | 0 | 280.25 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959265000 |  | 100261079 |  | 7352256C | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | 6TH | 2309 6TH ST | 019 | ASH | 2023-11-07 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-11-07 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2517.59 | 0 | 0 | 0 | 2517.59 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959266800 |  | 100262609 |  | 7352256D | 2074850 |  |  | 565 | EX | RPLC SL/20026978100 | 2600B | FERRY | 321 FERRY ST | 019 | ASH | 2023-11-07 | U124015 | U134723 | 2021-12-13 | 2023-12-29 |  |  | ORA SLONE | 2023-11-07 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2033.49 | 0 | 0 | 0 | 2033.49 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110823800 |  | 100460792 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | TEAKWOOD | 583 TEAKWOOD DR | 089 | RAC | 2023-11-08 | U123965 | U134723 | 2022-06-17 | 2023-12-29 |  |  | CJH DANNY DAVIS | 2023-11-07 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2562.22 | 0 | 0 | 0 | 2562.22 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110823900 |  | 100438081 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | TEAKWOOD | 585 TEAKWOOD DR | 089 | RAC | 2023-11-08 | U123965 | U134723 | 2022-06-17 | 2023-12-29 |  |  | CJH DANNY DAVIS | 2023-11-07 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2712.91 | 0 | 0 | 0 | 2712.91 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166676700 |  | 100322704 |  | 6720208A | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | PROVIDENCE | 808 PROVIDENCE RD | 067 | LEX | 2023-11-07 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-11-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2830.95 | 0 | 0 | 0 | 2830.95 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179204600 |  | 100265158 |  | 7352260O | 2286985 |  |  | 565 | EX | RPLC SL/22026172300 | 2600B | WHEATLEY | 411 WHEATLEY RD | 019 | ASH | 2023-11-07 | U124015 | U125763 | 2023-04-05 | 2023-12-29 |  |  | ORA SLONE | 2023-11-07 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2557.78 | 0 | 0 | 0 | 2557.78 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23208383600 |  | 100357976 |  | 6740232N | 2286363 |  |  | 565 | EX | RPLC SL/22026164000 | 2600B | SCOTT | 412 SCOTT AV | 017 | PAR | 2023-11-10 | U127414 | U125763 | 2023-08-15 | 2023-12-29 |  |  | ED FOX | 2023-11-07 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2652.02 | 0 | 0 | 0 | 2652.02 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23208383700 |  | 100357977 |  | 6740232N | 2286363 |  |  | 565 | EX | RPLC SL/22026164000 | 2600B | SCOTT | 414 SCOTT AV | 017 | PAR | 2023-11-10 | U127414 | U125763 | 2023-08-15 | 2023-12-29 |  |  | ED FOX | 2023-11-07 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2637.37 | 0 | 0 | 0 | 2637.37 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210314300 |  | 100269854 |  | 6732252P | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | BROADWAY | 410 BROADWAY AV | 097 | CYN | 2023-11-07 | U126604 | U125763 | 2023-08-23 | 2023-12-29 |  |  | WILL FULKS | 2023-11-07 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2441.5 | 0 | 0 | 0 | 2441.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212036100 |  | 100340113 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | COURTLAND | 1869 COURTLAND DR | 067 | LEX | 2023-11-08 | U137009 | AOC SYST | 2023-08-30 | 2024-02-29 | 2024-12-31 |  | LSTANFI | 2023-11-07 | 2023-10-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 5.5167 | 3 | 817.68 | 369.8 | 401.54 | 46.34 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212038300 |  | 100340111 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | COURTLAND | 1877 COURTLAND DR | 067 | LEX | 2023-11-08 | U137009 | AOC SYST | 2023-08-30 | 2024-02-29 | 2024-12-31 |  | LSTANFI | 2023-11-07 | 2023-10-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 11.1167 | 3 | 1484.57 | 835.48 | 399.94 | 249.15 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23217103500 |  | 100328805 |  | 6720208F |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621D | BLAIRMORE | 2016 BLAIRMORE RD | 067 | LEX | 2023-11-07 | U128336 | AOC SYST | 2023-09-26 | 2024-02-29 | 2024-12-31 |  | JOSHUA COX | 2023-11-07 | 2023-10-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.8833 | 7 | 1893.91 | 1569.61 | 214.02 | 110.28 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23220604800 |  | 100460757 |  | 6696220C |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | OLD FRANKFORT | 3530 OLD FRANKFORT PK HAL | 239 | MID | 2023-11-07 | U135005 | U124420 | 2023-10-11 | 2023-12-21 | 2023-12-25 |  | CDESPAIN | 2023-11-07 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 3.4 | 2 | 289.22 | 273.94 | 0 | 15.28 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23220844900 |  | 100315322 |  | 6716208C | 2301315 |  |  | 566 | EX | RETIRE S/L BUILDING DEMO | 2621P | LIMESTONE | 1101 S LIMESTONE ST | 067 | LEX | 2023-11-07 | RSTRONG | U461383 | 2023-10-12 | 2023-11-17 | 2023-11-17 |  | RSTRONG | 2023-11-07 | 2023-11-07 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.6167 | 3 | 1171.38 | 917.68 | 17.45 | 236.25 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23224865000 |  | 100460753 |  | E MP |  |  |  | 566 | EX | PAPER ABANDON | 2621P | OLD FRANKFORT | 3530 OLD FRANKFORT PK 4 | 239 | MID | 2023-11-07 | U135005 | U135005 | 2023-11-07 | 2023-11-07 |  |  | OFFICE | 2023-11-07 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2623 | 23224865100 |  | 100460754 |  | E MP |  |  |  | 566 | EX | PAPER ABANDON | 2621P | OLD FRANKFORT | 3530 OLD FRANKFORT PK 3 | 239 | MID | 2023-11-07 | U135005 | U135005 | 2023-11-07 | 2023-11-07 |  |  | OFFICE | 2023-11-07 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2623 | 23224865600 |  | 100460755 |  | E MP |  |  |  | 566 | EX | PAPER ABANDON | 2621P | OLD FRANKFORT | 3530 OLD FRANKFORT PK 1 | 239 | MID | 2023-11-07 | U135005 | U135005 | 2023-11-07 | 2023-11-07 |  |  | OFFICE | 2023-11-07 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2623 | 23224865800 |  | 100460756 |  | E MP |  |  |  | 566 | EX | PAPER ABANDON | 2621P | OLD FRANKFORT | 3530 OLD FRANKFORT PK 2 | 239 | MID | 2023-11-07 | U135005 | U135005 | 2023-11-07 | 2023-11-07 |  |  | OFFICE | 2023-11-07 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - EAST | 2633 | 21883100300 |  | 100253433 |  | 7356196T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | TOM | 2023-11-09 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-08 | 2023-11-08 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.25 | 1 | 100.45 | 95.15 | 0 | 5.3 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883194200 |  | 100253452 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | INE | 2023-11-09 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-08 | 2023-11-08 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.7 | 1 | 218.52 | 206.99 | 0 | 11.53 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883253300 |  | 100430300 |  | 7388136T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW9648 | PW9648 | 195 | MOU | 2023-11-08 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BLAKE MULLINS | 2023-11-08 | 2023-11-06 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.4333 | 1 | 342.28 | 171.51 | 0 | 170.77 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883266700 |  | 100257963 |  | 7320132T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | WELL 4868 | WELL 4868 | 119 | HIN | 2023-11-09 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | ANDREW SHEPHERD | 2023-11-08 | 2023-11-06 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.3 | 1 | 26.76 | 25.33 | 0 | 1.43 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883268600 |  | 100428527 |  | 7388148T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | UPPER JOHNS CR | 6501 UPPER JOHNS CR RD | 195 | KIM | 2023-11-09 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BLAKE MULLINS | 2023-11-08 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - EAST | 2633 | 21884186700 |  | 500183558 |  | 7324132C |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW5764 | PW5764 | 119 | LEB | 2023-11-09 | U130172 | U128293 | 2021-02-04 | 2022-07-01 | 2023-12-31 |  | ANDREW SHEPHERD | 2023-11-08 | 2023-11-01 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.65 | 1 | 325.4 | 308.21 | 0 | 17.19 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21884247900 |  | 100425865 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | INE | 2023-11-10 | U130172 | U128293 | 2021-02-04 | 2022-07-01 | 2023-12-31 |  | CLYDE HAMMOND | 2023-11-08 | 2023-10-09 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.2833 | 2 | 650.59 | 398.52 | 0 | 252.07 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110823700 |  | 100443984 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | TEAKWOOD | 579 TEAKWOOD DR | 089 | RAC | 2023-11-08 | U123965 | U134723 | 2022-06-17 | 2023-12-29 |  |  | CJH DANNY DAVIS | 2023-11-08 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3080.87 | 0 | 0 | 0 | 3080.87 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129015600 |  | 100459199 |  | 7376184T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LITTLE PETER C | 363 LITTLE PETER C RD | 159 | LOV | 2023-11-09 | U130172 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JOHN KIRK | 2023-11-08 | 2023-10-10 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.7667 | 2 | 116.75 | 110.12 | 0 | 6.63 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22979022500 |  | 100257993 |  | 7356148T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | LFT FORK TOLER | 733 LFT FORK TOLER CK | 071 | HAR | 2023-11-09 | U130172 | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | BLAKE MULLINS | 2023-11-08 | 2023-11-07 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 8.9667 | 2 | 1032.53 | 638.52 | 0 | 394.01 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166670500 |  | 100322620 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 705 BERRY LN | 067 | LEX | 2023-11-08 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-11-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1482.3 | 0 | 0 | 0 | 1482.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23191606500 |  | 100334952 |  | 6720212O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | WYATT | 1724 WYATT PY | 067 | LEX | 2023-11-08 | LSTONE | AOC SYST | 2023-05-31 | 2023-11-30 | 2024-12-31 |  | LSTONE | 2023-11-08 | 2023-11-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 12.35 | 2 | 1224.21 | 915.93 | 257.23 | 51.05 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23208383800 |  | 100357978 |  | 6740232N | 2286363 |  |  | 565 | EX | RPLC SL/22026164000 | 2600B | SCOTT | 416 SCOTT AV | 017 | PAR | 2023-11-10 | U127414 | U125763 | 2023-08-15 | 2023-12-29 |  |  | ED FOX | 2023-11-08 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2361.2 | 0 | 0 | 0 | 2361.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23208383900 |  | 100357979 |  | 6740232N | 2286363 |  |  | 565 | EX | RPLC SL/22026164000 | 2600B | SCOTT | 418 SCOTT AV | 017 | PAR | 2023-11-10 | U127414 | U125763 | 2023-08-15 | 2023-12-29 |  |  | ED FOX | 2023-11-08 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2241.68 | 0 | 0 | 0 | 2241.68 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210314400 |  | 100269842 |  | 6732252P | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | BROADWAY | 411 BROADWAY AV | 097 | CYN | 2023-11-08 | U126604 | U125763 | 2023-08-23 | 2023-12-29 |  |  | WILL FULKS | 2023-11-08 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2713.92 | 0 | 0 | 0 | 2713.92 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210314600 |  | 100269856 |  | 6732252P | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | BROADWAY | 414 BROADWAY AV | 097 | CYN | 2023-11-09 | U126604 | U125763 | 2023-08-23 | 2023-12-29 |  |  | WILL FULKS | 2023-11-08 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2548.92 | 116.16 | 0 | 6.48 | 2426.28 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212035800 |  | 100340112 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | COURTLAND | 1873 COURTLAND DR | 067 | LEX | 2023-11-13 | U135005 | AOC SYST | 2023-08-30 | 2024-02-29 | 2024-12-31 |  | LSTANFI | 2023-11-08 | 2023-10-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 13.5 | 3 | 1694.13 | 988.28 | 456.51 | 249.34 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212041000 |  | 100340169 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | COURTLAND | 1888 COURTLAND DR | 067 | LEX | 2023-11-08 | HMCKUNE | AOC SYST | 2023-08-30 | 2024-02-29 | 2024-12-31 |  | HMCKUNE | 2023-11-08 | 2023-10-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 12.5333 | 3 | 1179.32 | 763.05 | 373.49 | 42.78 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23213258200 |  | 100339593 |  | 6724212A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | MARIETTA | 1862 MARIETTA DR 1FL-A | 067 | LEX | 2023-11-08 | WISHII | AOC SYST | 2023-09-06 | 2024-03-06 | 2024-12-31 |  | WISHII | 2023-11-08 | 2023-10-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 14.9 | 3 | 1651.4 | 1065.6 | 0 | 585.8 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23213259000 |  | 100339617 |  | 6724212A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | MARIETTA | 1815 MARIETTA DR | 067 | LEX | 2023-11-08 | WISHII | AOC SYST | 2023-09-06 | 2024-03-06 | 2024-12-31 |  | WISHII | 2023-11-08 | 2023-10-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 11.2 | 5 | 1482.27 | 789.48 | 312.15 | 380.64 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23213260300 |  | 100339619 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | MARIETTA | 1809 MARIETTA DR | 067 | LEX | 2023-11-08 | WISHII | AOC SYST | 2023-09-06 | 2024-03-06 | 2024-12-31 |  | WISHII | 2023-11-08 | 2023-10-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 11.9 | 5 | 1361.05 | 908.51 | 0 | 452.54 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23217089800 |  | 100328838 |  | 6720208F |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621D | BLAIRMORE | 1889 BLAIRMORE RD | 067 | LEX | 2023-11-08 | U128336 | AOC SYST | 2023-09-26 | 2024-02-28 | 2024-12-31 |  | JOSHUA COX | 2023-11-08 | 2023-10-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 26.5 | 7 | 2494.29 | 1927.83 | 405.83 | 160.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23224845900 |  | 100274378 |  | 6684228J |  |  |  | 565 | EX | REPLACE SERVICE LINE - D252952 | 2621P | EWING | 407 EWING ST | 073 | FRA | 2023-11-09 | U137009 | U135005 | 2023-11-07 | 2023-11-10 | 2023-11-28 |  | EFGOINS | 2023-11-08 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 18.8333 | 2 | 1745.69 | 1379.05 | 289.77 | 76.87 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23224859900 |  | 100263860 |  | 7352260O |  |  |  | 565 | EX | 24HR GAS OFF RPLC SL - D259956 | 2621P | HOODS CREEK | 1607 HOODS CREEK PK | 019 | ASH | 2023-11-08 | RECUMP | U135005 | 2023-11-07 | 2023-11-07 | 2023-11-07 |  | RECUMP | 2023-11-08 | 2023-11-08 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 15.45 | 3 | 1501.68 | 1105.75 | 40.56 | 355.37 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23224958300 |  | 100265102 |  | 7352256B | 2286985 |  |  | 565 | EX | RPLC SL/22026172300 | 2600B | HOUSTON | 2012 HOUSTON AV | 019 | ASH | 2023-11-08 | U124015 | U131066 | 2023-11-08 | 2023-12-29 |  |  | ORA SLONE | 2023-11-08 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2570.94 | 40.84 | 0 | 2.4 | 2527.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23224958700 |  | 100265101 |  | 7352260O | 2286985 |  |  | 565 | EX | RPLC SL/22026172300 | 2600B | BERRY | 409< BERRY AV TRL 1 | 019 | ASH | 2023-11-08 | U124015 | U131066 | 2023-11-08 | 2023-12-29 |  |  | ORA SLONE | 2023-11-08 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 17121.36 | 0 | 15177.9 | 0 | 1943.46 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23224967800 |  | 100468018 |  | 7352256B | 2286985 |  |  | 565 | EX | RPLC SL/22026172300 | 2600B | HOUSTON | 2012< HOUSTON DR | 019 | ASH | 2023-11-08 | U124015 | U131066 | 2023-11-08 | 2023-12-29 |  |  | ORA SLONE | 2023-11-08 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1864.93 | 21.35 | 0 | 1.22 | 1842.36 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23225035100 |  | 100274379 |  | 6684228J |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | EWING | 409 EWING ST | 073 | FRA | 2023-11-09 | U137009 | U129939 | 2023-11-08 | 2023-11-08 |  |  | EFGOINS | 2023-11-08 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.1667 | 2 | 3882.66 | 88.03 | 285.11 | 4.92 | 3504.6 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883308200 |  | 100261858 |  | 7328132T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | HWY 1605 | 5555 HWY 1605 | 119 | LIT | 2023-11-09 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | ANDREW SHEPHERD | 2023-11-09 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1 | 2213.2 | 0 | 0 | 0 | 2213.2 | 0 | 0 | 0
KY | KY - WEST | 2623 | 21931985700 |  | 100345329 |  | 6696212H | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | HIGHVIEW | 122 HIGHVIEW DR | 239 | VER | 2023-11-10 | U128410 | AOC SYST | 2021-08-10 | 2022-02-10 | 2022-12-31 |  | CDESPAIN | 2023-11-09 | 2023-11-06 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 34.3 | 5 | 3199.49 | 2749.55 | 302.21 | 147.73 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110825000 |  | 100439738 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | WILD CHERRY | 574 WILD CHERRY CR | 089 | RAC | 2023-11-10 | U123965 | U134723 | 2022-06-17 | 2023-12-29 |  |  | CJH DANNY DAVIS | 2023-11-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2568.96 | 0 | 0 | 0 | 2568.96 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129070900 |  | 100242171 |  | 7356252D |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 10TH | 526 10TH ST RR | 019 | CAT | 2023-11-09 | RECUMP | U130722 | 2022-09-05 | 2022-12-30 |  |  | RECUMP | 2023-11-09 | 2023-11-07 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 14.1833 | 4 | 1398.55 | 1083.42 | 0 | 315.13 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129071300 |  | 100408365 |  | 7360252I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | CENTER | 2101 CENTER ST | 019 | CAT | 2023-11-09 | RECUMP | U130722 | 2022-09-05 | 2022-12-30 |  |  | RECUMP | 2023-11-09 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.6 | 2 | 254.11 | 194.28 | 10.01 | 49.82 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179199900 |  | 100265103 |  | 7352260O | 2286985 |  |  | 565 | EX | RPLC SL/22026172300 | 2600B | BERRY | 327 BERRY AV | 019 | ASH | 2023-11-09 | U124015 | U125763 | 2023-04-05 | 2023-12-29 |  |  | ORA SLONE | 2023-11-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1849.1 | 0 | 0 | 0 | 1849.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179201000 |  | 501129385 |  | 7352260O | 2286985 |  |  | 565 | EX | RPLC SL/22026172300 | 2600B | BERRY | 401 BERRY ST | 019 | ASH | 2023-11-09 | U124015 | U125763 | 2023-04-05 | 2023-12-29 |  |  | ORA SLONE | 2023-11-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2659.62 | 0 | 0 | 0 | 2659.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23191602000 |  | 100323821 |  | 6716204D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | KIRKLAND | 716 KIRKLAND DR | 067 | LEX | 2023-11-09 | RSTRONG | AOC SYST | 2023-05-31 | 2023-11-30 | 2024-12-31 |  | RSTRONG | 2023-11-09 | 2023-09-29 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 30.6667 | 7 | 2583.53 | 1632.87 | 636.15 | 314.51 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23203501000 |  | 100280560 |  | 6688228I | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | HICKORY | 137 HICKORY DR | 073 | FRA | 2023-11-09 | MCRAIG | AOC SYST | 2023-07-24 | 2024-01-24 | 2024-12-31 |  | MCRAIG | 2023-11-09 | 2023-11-02 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 45.55 | 8 | 5719.27 | 3065.09 | 735.19 | 858.15 | 1060.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23203502200 |  | 100280559 |  | 6688228I | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | HICKORY | 135 HICKORY DR | 073 | FRA | 2023-11-09 | MCRAIG | AOC SYST | 2023-07-24 | 2024-01-24 | 2024-12-31 |  | MCRAIG | 2023-11-09 | 2023-11-02 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 40.1833 | 7 | 6251.27 | 2832.15 | 15.13 | 1083.15 | 2320.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23208385500 |  | 100357971 |  | 6740232N | 2286363 |  |  | 565 | EX | RPLC SL/22026164000 | 2600B | WASHINGTON | 414 WASHINGTON ST | 017 | PAR | 2023-11-10 | U127414 | U125763 | 2023-08-15 | 2023-12-29 |  |  | ED FOX | 2023-11-09 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3364.06 | 0 | 0 | 0 | 3364.06 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210315000 |  | 100269767 |  | 6732252O | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | BROADWAY | 506 BROADWAY AV | 097 | CYN | 2023-11-09 | U126604 | U125763 | 2023-08-23 | 2023-12-29 |  |  | WILL FULKS | 2023-11-09 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2193.31 | 0 | 0 | 0 | 2193.31 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210315800 |  | 100269764 |  | 6732252O | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | CLADORBON | 109 CLADORBON DR | 097 | CYN | 2023-11-09 | U126604 | U125763 | 2023-08-23 | 2023-12-29 |  |  | WILL FULKS | 2023-11-09 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2358.68 | 0 | 0 | 0 | 2358.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23212272300 |  | 100339492 |  | 6724212A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | HUNTSVILLE | 1442 HUNTSVILLE DR A | 067 | LEX | 2023-11-09 | RSTRONG | AOC SYST | 2023-08-31 | 2024-02-29 | 2024-12-31 |  | RSTRONG | 2023-11-09 | 2023-10-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 32.1 | 6 | 4015.67 | 2750.35 | 767.18 | 498.14 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23219749000 |  | 100289224 |  | 6724212A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SILVERLEAF | 638 SILVERLEAF DR | 067 | LEX | 2023-11-13 | U135005 | U132761 | 2023-10-05 | 2024-04-04 | 2025-10-31 |  | LSTANFI | 2023-11-09 | 2023-11-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.2333 | 3 | 1806.76 | 975.45 | 585.82 | 245.49 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23222189400 |  | 100456305 |  | 6716212B | 1968251 |  |  | 565 | EX | RPLC SL/23026292500 | 2600B | LISLE INDUSTRI | 181 LISLE INDUSTRI AV | 067 | LEX | 2023-11-09 | U124003 | U125763 | 2023-10-19 | 2023-12-29 |  |  | BPULLIAM/FISHEL | 2023-11-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 6316.86 | 0 | 0 | 0 | 6316.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23223040400 |  | 100275066 |  | 6684228J | 2074544 |  |  | 566 | EX | ABANDON SL/20026974600 | 2600B | SAINT CLAIR | 232 SAINT CLAIR ST | 073 | FRA | 2023-11-09 | U461443 | U131066 | 2023-10-25 | 2023-12-29 |  |  | WGRAVES | 2023-11-09 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26230043 |  | 1 | 1426.51 | 0 | 0 | 0 | 1426.51 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883077000 |  | 100409712 |  | 7364140T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | SHELBY DRY | 2417 SHELBY DRY FK | 195 | SHE | 2023-11-10 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BLAKE MULLINS | 2023-11-10 | 2023-11-10 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.6167 | 2 | 792.09 | 396.9 | 0 | 395.19 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883100800 |  | 100257866 |  | 7360152T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | WELL 4203 | WELL 4203 | 195 | COA | 2023-11-10 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BLAKE MULLINS | 2023-11-10 | 2023-11-09 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 8.0667 | 2 | 682.85 | 569.8 | 0 | 113.05 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883167200 |  | 100253569 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | INE | 2023-11-10 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-10 | 2023-11-10 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.13333 | 1 | 10.45 | 9.9 | 0 | 0.55 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883191200 |  | 100255263 |  | 7352188T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | BUTTER MILK | 1420 BUTTER MILK BR | 115 | BOO | 2023-11-10 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | CLYDE HAMMOND | 2023-11-10 | 2023-08-07 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 9.0667 | 4 | 773.21 | 592.89 | 0 | 180.32 | 0 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883229900 |  | 100426773 |  | 7388156T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | GENERAL DELIVE | GENERAL DELIVE | 119 | PIN | 2023-11-10 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | ANDREW SHEPHERD | 2023-11-10 |  |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 |  | 1
KY | KY - EAST | 2682 | 21883249900 |  | 100426784 |  | 7388156T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | GENERAL DELIVE | GENERAL DELIVE | 119 | PIN | 2023-11-10 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | ANDREW SHEPHERD | 2023-11-10 |  |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 |  | 1
KY | KY - EAST | 2682 | 21883312400 |  | 100444960 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | GENERAL DELIVE | GENERAL DELIVE | 119 | PIN | 2023-11-10 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | ANDREW SHEPHERD | 2023-11-10 |  |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 |  | 1
KY | KY - EAST | 2633 | 22979054800 |  | 500679528 |  | 7348176A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PAINTSVILLE DP | PAINTSVILLE DP | 115 | VAN | 2023-11-10 | U130172 | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | JAHOWARD | 2023-11-10 | 2022-11-17 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 24.6333 | 5 | 2900.95 | 1911.78 | 0 | 106.52 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026277600 |  |  |  | 7356252D | 2397978 | U122858 |  | 557 | EX | INSTALL 595'-2"PMMP | 2600B | HARRIS | HARRIS | 019 | CAT | 2023-12-04 | U128132 | U122858 | 2023-06-02 | 2023-11-30 | 2023-12-31 | 2023-11-02 | CJH JAMES ROWE/M BLANKENSHIP | 2023-11-10 | 2023-10-17 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP2776 | AMRCB |  | 100 | 055732230262776 | 108.0333 | 14784 | 137119.9 | 8322.09 | 11648.08 | 2755.46 | 79328.82 | 0 | 826.35 | 34239.1 | 704
KY | KY - EAST | 2631 | 23026277700 |  |  |  | 7356252D | 2397978 | U122858 |  | 558 | EX | RETIRE 2881'-12" BSMP | 2600B | HARRIS | HARRIS | 019 | CAT | 2023-11-22 | U128132 | U122858 | 2023-06-02 | 2023-12-29 | 2023-12-31 | 2023-11-07 | CJH JAMES ROWE/M BLANKENSHIP | 2023-11-10 | 2023-11-08 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP2777 | AMRCB |  | 100 | 055832230262777 | 2.8833 | 0 | 430.39 | 220.15 | 0 | 45.24 | 165 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23193802500 |  | 100346811 |  | 6696212O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | HILLCREST | 375 HILLCREST DR | 239 | VER | 2023-11-10 | BWHITE | AOC SYST | 2023-06-08 | 2023-12-08 | 2024-12-31 |  | BWHITE | 2023-11-10 | 2023-11-06 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 77.5 | 11 | 12133.02 | 6210 | 148.7 | 1120.14 | 4654.18 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23208097300 |  | 100284042 |  | 6712228N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332610 | 2621P | DOGWOOD | 123 DOGWOOD DR | 209 | GEO | 2023-11-10 | DCOLLIN | U135005 | 2023-08-14 | 2024-02-09 | 2025-08-31 |  | DCOLLIN | 2023-11-10 | 2023-09-11 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 28.8 | 10 | 3710.33 | 2191.94 | 301.31 | 958.08 | 259 | 0 | 0 | 0
KY | KY - EAST | 2633 | 06652108500 |  | 500296494 |  | 7348168-I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | ROGERS PARK | ROGERS PARK RD | 195 | S W | 2023-11-13 | U130172 | U901436 | 2006-06-27 | 2022-07-01 | 2023-12-31 |  | JOHN HOWARD | 2023-11-13 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.7167 | 1 | 307.61 | 291.37 | 0 | 16.24 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 13125828400 |  | 100264629 |  | 7348168I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | ROGERS PARK | ROGERS PARK RD | 195 | TUR | 2023-11-13 | U130172 | U126642 | 2013-03-26 | 2022-07-01 | 2023-12-31 |  | JOHN HOWARD | 2023-11-13 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 4.2833 | 1 | 353.88 | 335.2 | 0 | 18.68 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 14258307600 |  | 100244013 |  | 7356256J |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | SKIDMORE | 4021 SKIDMORE ST | 019 | ASH | 2023-11-13 | MCOLLET | U125201 | 2014-10-17 | 2049-12-31 |  |  | MCOLLET | 2023-11-13 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 13.7833 | 2 | 2815.26 | 1045.74 | 366.73 | 1402.79 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883110900 |  | 100424646 |  | 7360196T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | MIL | 2023-11-13 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-13 | 2023-11-13 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.75 | 1 | 139 | 131.65 | 0 | 7.35 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883133200 |  | 100446835 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | INE | 2023-11-13 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | CLYDE HAMMOND | 2023-11-13 | 2023-11-13 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.85 | 1 | 125.27 | 70.35 | 0 | 54.92 | 0 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883146300 |  | 100430342 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | SAGE ALLEN | 649 SAGE ALLEN BR | 071 | HUE | 2023-11-13 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BRIAN PREECE | 2023-11-13 |  |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 1.25 | 1 | 96.75 | 91.65 | 0 | 5.1 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883162900 |  | 100427326 |  | 7344136T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY RT 1498 | 1029 KY RT 1498 | 071 | BEV | 2023-11-13 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BRIAN PREECE | 2023-11-13 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.25 | 2 | 96.75 | 91.65 | 0 | 5.1 | 0 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883191900 |  | 100463399 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | GENERAL DELIVE | GENERAL DELIVE | 071 | HUE | 2023-11-13 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BRIAN PREECE | 2023-11-13 |  |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 1 | 1 | 77.43 | 73.33 | 0 | 4.1 | 0 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883208000 |  | 100464092 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | GENERAL DELIVE | GENERAL DELIVE | 153 | SAL | 2023-11-13 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BRIAN PREECE | 2023-11-13 |  |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 1.25 | 1 | 96.75 | 91.65 | 0 | 5.1 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883210900 |  | 100430045 |  | 7372184T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | PIL | 2023-11-13 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-13 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.1833 | 1 | 98.03 | 92.85 | 0 | 5.18 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883244900 |  | 100253538 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | INE | 2023-11-13 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | CLYDE HAMMOND | 2023-11-13 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.81667 | 1 | 125.27 | 70.35 | 0 | 54.92 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883300300 |  | 100253519 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | INE | 2023-11-13 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | CLYDE HAMMOND | 2023-11-13 | 2023-11-13 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.83333 | 1 | 122.35 | 68.71 | 0 | 53.64 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883306300 |  | 100424738 |  | 7376188T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | WAR | 2023-11-13 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-13 | 2023-11-13 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.25 | 1 | 20.07 | 19.01 | 0 | 1.06 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883309700 |  | 100456981 |  | 7340156T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PM30 | PM30 | 071 | HIT | 2023-11-13 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BRIAN PREECE | 2023-11-13 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.25 | 1 | 174.19 | 164.99 | 0 | 9.2 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883314100 |  | 100252027 |  | 7360184T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | DEB | 2023-11-13 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-13 | 2023-11-13 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.4333 | 1 | 194.43 | 184.16 | 0 | 10.27 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21884242900 |  | 100422153 |  | 7364184T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | DEB | 2023-11-13 | U130172 | U128293 | 2021-02-04 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-13 | 2023-11-13 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.88333 | 1 | 70.7 | 66.97 | 0 | 3.73 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110825100 |  | 100440368 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | WILD CHERRY | 576 WILD CHERRY CR | 089 | RAC | 2023-11-13 | U123965 | U134723 | 2022-06-17 | 2023-12-29 |  |  | CJH DANNY DAVIS | 2023-11-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2501.88 | 0 | 0 | 0 | 2501.88 | 0 | 0 | 0
KY | KY - EAST | 2682 | 22129015400 |  | 100437272 |  | X172459 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2633S | GENERAL DELIVE | GENERAL DELIVE | 119 | VES | 2023-11-13 | U130172 | U130722 | 2022-09-05 | 2022-12-30 |  |  | BRIAN PREECE | 2023-11-13 |  |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 1 | 1 | 77.43 | 73.33 | 0 | 4.1 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026305300 |  |  |  | 6720200E | 2301713 | U122858 |  | 557 | EX | EMER-INSTALL 11'-2" PMMP | 2621P | TATES CREEKS | TATES CREEKS RD | 067 | LEX | 2023-11-22 | U128132 | U122858 | 2023-11-14 | 2023-11-10 | 2023-11-13 | 2023-11-13 | JOSHUA COX | 2023-11-13 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3053 |  |  | 100 | 055732230263053 | 3.2333 | 11 | 5028.51 | 3795.49 | 0 | 211.51 | 609.5 | 0 | 9.96 | 402.05 | 11
KY | KY - WEST | 2621 | 23026305400 |  |  |  | 6720200E | 2301713 | U122858 |  | 558 | EX | EMER-RETIRE 11'-2" PMMP | 2621P | TATES CREEKS | TATES CREEKS RD | 067 | LEX | 2023-11-22 | U128132 | U122858 | 2023-11-14 | 2023-11-13 | 2023-11-13 | 2023-11-13 | JOSHUA COX | 2023-11-13 | 2023-11-17 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP3054 |  |  | 100 | 055832230263054 | 5.0333 | 0 | 383.65 | 363.4 | 0 | 20.25 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179199400 |  | 100265107 |  | 7352260O | 2286985 |  |  | 565 | EX | RPLC SL/22026172300 | 2600B | BERRY | 308 BERRY AV | 019 | ASH | 2023-11-13 | U125566 | U125763 | 2023-04-05 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-11-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2632.73 | 0 | 0 | 0 | 2632.73 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179199500 |  | 100265108 |  | 7352260O | 2286985 |  |  | 565 | EX | RPLC SL/22026172300 | 2600B | BERRY | 310 BERRY AV | 019 | ASH | 2023-11-13 | U125566 | U125763 | 2023-04-05 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-11-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2715.65 | 0 | 0 | 0 | 2715.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23179200000 |  | 100265110 |  | 7352260O | 2286985 |  |  | 565 | EX | RPLC SL/22026172300 | 2600B | BERRY | 328 BERRY AV | 019 | ASH | 2023-11-13 | U125566 | U125763 | 2023-04-05 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-11-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1960.31 | 0 | 0 | 0 | 1960.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23198569000 |  | 500009739 |  | 6720208B | 2286441 |  |  | 565 | EX | RPLC SL/22026166900 | 2600B | RICHMOND | 1815 RICHMOND RD POOL | 067 | LEX | 2023-11-14 | U123111 | U125763 | 2023-06-30 | 2023-12-29 |  |  | LYN STFFORD | 2023-11-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 5797.59 | 1087.88 | 0 | 60.55 | 4649.16 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23203500300 |  | 100280562 |  | 6688228I | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | HICKORY | 141 HICKORY DR | 073 | FRA | 2023-11-13 | MCRAIG | AOC SYST | 2023-07-24 | 2024-01-24 | 2024-12-31 |  | MCRAIG | 2023-11-13 | 2023-11-01 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 18.3 | 4 | 2682.31 | 1367.59 | 279.62 | 1035.1 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23205512200 |  | 100411503 |  | 6724212I | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | CANTRILL | 1828 CANTRILL DR | 067 | LEX | 2023-11-13 | ABLAKE | AOC SYST | 2023-08-01 | 2024-02-01 | 2024-12-31 |  | ABLAKE | 2023-11-13 | 2023-11-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 18.9333 | 3 | 1783.95 | 1392.48 | 313.85 | 77.62 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23208383400 |  | 100357958 |  | 6740232N | 2286363 |  |  | 565 | EX | RPLC SL/22026164000 | 2600B | SCOTT | 356 SCOTT AV | 017 | PAR | 2023-11-14 | U126532 | U125763 | 2023-08-15 | 2023-12-29 |  |  | LESLIE SHARON | 2023-11-13 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4561.52 | 0 | 0 | 0 | 4561.52 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210314700 |  | 100269801 |  | 6732252O | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | BROADWAY | 503 BROADWAY AV | 097 | CYN | 2023-11-13 | U126284 | U125763 | 2023-08-23 | 2023-12-29 |  |  | JOSH PASLEY/MILLER PIPELINE | 2023-11-13 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 4.4333 | 1 | 3451.11 | 339.28 | 0 | 315.36 | 2796.47 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210314900 |  | 100269800 |  | 6732252O | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | BROADWAY | 505 BROADWAY AV | 097 | CYN | 2023-11-13 | U126284 | U125763 | 2023-08-23 | 2023-12-29 |  |  | JOSH PASLEY/MILLER PIPELINE | 2023-11-13 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 5.0667 | 1 | 4295.88 | 385.02 | 0 | 357.87 | 3552.99 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23213718400 |  | 100275788 |  | 6684228C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | PLEASANT HILL | 136 PLEASANT HILL DR | 073 | FRA | 2023-11-14 | U137009 | AOC SYST | 2023-09-08 | 2024-03-08 | 2024-12-31 |  | EFGOINS | 2023-11-13 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 16 | 2 | 1201.33 | 1006.59 | 138.66 | 56.08 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23222851100 |  | 100424823 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | MOORE | 438 MOORE BR | 159 | INE | 2023-11-13 | U130172 | U133234 | 2023-10-24 | 2023-11-07 | 2023-11-23 |  | JOHN KIRK | 2023-11-13 | 2023-11-13 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.5 | 1 | 120.52 | 114.15 | 0 | 6.37 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23223437600 |  | 100312549 |  | 6716208F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SHERIDAN | 358 SHERIDAN DR | 067 | LEX | 2023-11-13 | KKINDER | U135005 | 2023-10-27 | 2023-12-27 | 2023-12-27 |  | KKINDER | 2023-11-13 | 2023-11-03 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.8333 | 4 | 771.28 | 568.29 | 171.29 | 31.7 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23225556500 |  | 100316380 |  | 6716208F |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | CHERRYBARK | 129 CHERRYBARK DR | 067 | LEX | 2023-11-13 | RSTRONG | U138726 | 2023-11-12 | 2023-11-10 | 2023-11-10 |  | RSTRONG | 2023-11-13 | 2023-11-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 32.6167 | 4 | 5624.39 | 1916.85 | 306.17 | 348.98 | 3052.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23225573100 |  | 100317918 |  | 6716204G |  |  |  | 565 | EX | GRADE 1 SERVICE REPLACE | 2621P | CAMELOT | 3504 CAMELOT DR | 067 | LEX | 2023-11-14 | U128336 | U129939 | 2023-11-13 | 2023-11-13 | 2023-11-13 |  | JOSHUA COX | 2023-11-13 | 2023-11-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.1667 | 4 | 1577.05 | 1196.89 | 313.43 | 66.73 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23225624000 |  | 100330580 |  | 6732212M |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CLEVELAND | 3111 N CLEVELAND RD | 067 | LEX | 2023-11-14 | U137009 | U129939 | 2023-11-13 | 2024-03-15 | 2025-09-30 |  | LSTANFI | 2023-11-13 | 2023-11-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 2.15 | 3 | 2368.27 | 1167.47 | 587.04 | 87.26 | 526.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 05609616000 |  | 100257712 |  | ? |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | US ROUTE 23 | US ROUTE 23 | 089 | WUR | 2023-11-14 | U131418 | BHOLDER | 2005-05-03 | 2022-07-01 | 2023-12-31 |  | J. PARKS | 2023-11-14 | 2023-07-12 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 7.5833 | 3 | 454.83 | 427.88 | 0 | 26.95 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883163000 |  | 100409969 |  | 7344136T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW3836 | PW3836 | 071 | BEV | 2023-11-14 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BRIAN PREECE | 2023-11-14 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.91667 | 1 | 71.28 | 67.5 | 0 | 3.78 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883202500 |  | 100253350 |  | 7372184T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | BEA | 2023-11-14 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-14 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.4333 | 2 | 453.78 | 429.81 | 0 | 23.97 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883235100 |  | 100423326 |  | 7364188G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | INE | 2023-11-14 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-14 | 2023-11-14 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.9333 | 2 | 248.5 | 235.37 | 0 | 13.13 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883270700 |  | 100437269 |  | 7376184T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | PIL | 2023-11-14 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-14 | 2023-11-14 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.0333 | 2 | 85.8 | 81.28 | 0 | 4.52 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883313900 |  | 100458362 |  | 7388136T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW9391 | PW9391 | 195 | FED | 2023-11-14 | U130172 | U120245 | 2021-01-30 | 2023-11-02 | 2023-12-31 |  | BRIAN PREECE | 2023-11-14 | 2023-11-02 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.0667 | 3 | 217.19 | 148.9 | 0 | 68.29 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129117200 |  | 100258020 |  | 7344156T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW4045 | PW4045 | 071 | PRT | 2023-11-14 | U130172 | U125208 | 2022-09-06 | 2022-12-30 | 2023-12-31 |  | BRIAN PREECE | 2023-11-14 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.0167 | 1 | 84.4 | 79.95 | 0 | 4.45 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22979019900 |  | 100250506 |  | 7376188T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | BARRETT | 8796 BARRETT ST | 159 | WAR | 2023-11-14 | U130172 | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | JOHN KIRK | 2023-11-14 | 2023-11-14 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.5667 | 2 | 488.24 | 276.66 | 0 | 15.41 | 196.17 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22979044200 |  | 100412184 |  | 7364184T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY FIELD | KY FIELD | 159 | DEB | 2023-11-14 | U130172 | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | JOHN KIRK | 2023-11-14 | 2023-11-14 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 4.0333 | 2 | 330.03 | 312.6 | 0 | 17.43 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166671600 |  | 100322652 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 732 BERRY LN | 067 | LEX | 2023-11-15 | U123111 | U125763 | 2023-02-14 | 2023-12-29 |  |  | LYN STAFFORD | 2023-11-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1380.08 | 0 | 0 | 0 | 1380.08 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168131500 |  | 100274987 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | SAINT CLAIR | 201 SAINT CLAIR ST | 073 | FRA | 2023-11-14 | U461443 | U125763 | 2023-02-20 | 2023-12-29 |  |  | WGRAVES | 2023-11-14 | 2023-11-14 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.9333 | 2 | 2313.99 | 304.78 | 0 | 16.99 | 1992.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23198566200 |  | 100328607 |  | 6720208B | 2286441 |  |  | 565 | EX | RPLC SL/22026166900 | 2600B | RICHMOND | 1820 RICHMOND RD | 067 | LEX | 2023-11-15 | U123111 | U125763 | 2023-06-30 | 2023-12-29 |  |  | LYN STAFFORD | 2023-11-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4891.08 | 0 | 0 | 0 | 4891.08 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23208383000 |  | 100357951 |  | 6740232N | 2286363 |  |  | 566 | EX | ABND SL/22026164000 | 2600B | SCOTT | 314 SCOTT AV | 017 | PAR | 2023-11-14 | U126532 | U125763 | 2023-08-15 | 2023-12-29 |  |  | LESLIE SHARON | 2023-11-14 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26290043 |  | 1 | 2328.5 | 0 | 0 | 0 | 2328.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210314800 |  | 100269765 |  | 6732252O | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | BROADWAY | 504 BROADWAY AV | 097 | CYN | 2023-11-14 | U126604 | U125763 | 2023-08-23 | 2023-12-29 |  |  | WILL FULKS | 2023-11-14 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1719.35 | 59.17 | 0 | 3.34 | 1656.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210315100 |  | 100269768 |  | 6732252O | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | BROADWAY | 508 BROADWAY AV | 097 | CYN | 2023-11-14 | U126604 | U125763 | 2023-08-23 | 2023-12-29 |  |  | WILL FULKS | 2023-11-14 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1698.79 | 0 | 0 | 0 | 1698.79 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23215056500 |  | 100352948 |  | 6744208P |  |  |  | 566 | VO | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN | 66 S MAIN ST 2F | 049 | WIN | 2023-11-21 |  | U124420 | 2023-09-15 | 2024-08-06 | 2024-08-06 |  | DENNING | 2023-11-14 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 20.65 | 3 | 1768.84 | 1675.45 | 0 | 93.39 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23222871100 |  | 100328348 |  | 6720208F |  |  |  | 565 | EX | INSTALL 2"PMLP S/L W/METER CHG | 2621P | COOPER | 1344 COOPER DR | 067 | LEX | 2023-11-15 | U930915 | U132761 | 2023-10-24 | 2023-11-21 | 2023-11-21 |  | RJCRAWF | 2023-11-14 | 2023-11-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 47.5333 | 6 | 8775.67 | 4402.33 | 850.41 | 249.3 | 3273.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23223246900 |  | 500579716 |  | 6716216B | 9825149 |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | INNOVATION | 2201 INNOVATION DR | 067 | LEX | 2023-11-14 | ATWILLI | U135005 | 2023-10-26 | 2023-12-26 | 2023-12-26 |  | ATWILLI | 2023-11-14 | 2023-11-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 71.2333 | 11 | 6853.84 | 5076.94 | 311.42 | 1465.48 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23223643100 |  | 100328345 |  | 6720208F | 2300739 |  |  | 565 | EX | INSTALL 2"PMLP SL W/METER CHG | 2621P | COOPER | 1336 COOPER DR | 067 | LEX | 2023-11-15 | U930915 | U461383 | 2023-10-30 | 2023-11-22 | 2023-11-22 |  | RJCRAWF | 2023-11-14 | 2023-11-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 37.7333 | 6 | 12080.99 | 2574.86 | 844.91 | 143.53 | 8517.69 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23224048200 |  | 100279460 |  | 6688228O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332805 | 2621P | GALBRAITH | 1709 GALBRAITH RD | 073 | FRA | 2023-11-14 | MCRAIG | U135005 | 2023-11-01 | 2024-01-31 |  |  | MCRAIG | 2023-11-14 | 2023-11-07 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 32.5833 | 7 | 3908.28 | 2018.73 | 335.79 | 905.76 | 648 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23225825000 |  | 500009252 |  | 6720204M |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SHAGBARK | 1105 SHAGBARK LN | 067 | LEX | 2023-11-14 | U126308 | U129939 | 2023-11-14 | 2024-03-14 | 2025-09-30 |  | ENSMINGER/COX | 2023-11-14 | 2023-11-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 17.25 | 3 | 1526.18 | 1266.76 | 188.82 | 70.6 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 11913708500 |  | 500350293 |  | 7384168E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | HICKORY HILL | HICKORY HILL | 195 | S W | 2023-11-16 | U135005 | U907001 | 2011-06-28 | 2023-11-15 | 2023-11-15 |  | JAHOWARD | 2023-11-15 | 2022-11-17 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.5833 | 2 | 1081.1 | 187.98 | 0 | 10.47 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883111000 |  | 100264664 |  | 7384168I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | ROGERS PARK | ROGERS PARK RD | 195 | S W | 2023-11-15 | JAHOWARD | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JAHOWARD | 2023-11-15 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.4 | 1 | 1329.14 | 422.92 | 0 | 23.57 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883179500 |  | 100257886 |  | 7344140T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | WELL 3931 | WELL 3931 | 071 | HI | 2023-11-15 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-15 | 2023-11-15 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.2667 | 1 | 102.05 | 96.66 | 0 | 5.39 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883210800 |  | 100266392 |  | 7380172T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | SWINGE CAMP | 167 SWINGE CAMP RT FORK | 195 | HAT | 2023-11-15 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-15 | 2023-11-15 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.5333 | 1 | 122.12 | 115.68 | 0 | 6.44 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883318000 |  | 100455932 |  | 7344156T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PM83 | PM83 | 071 | PRT | 2023-11-15 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BRIAN PREECE | 2023-11-15 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.7167 | 1 | 131.59 | 124.65 | 0 | 6.94 | 0 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883330400 |  | 100426483 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | GENERAL DELIVE | GENERAL DELIVE | 133 | WHI | 2023-11-15 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-15 | 2023-11-15 |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 1.05 | 1 | 84.36 | 79.91 | 0 | 4.45 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110823400 |  | 100461278 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | TEAKWOOD | 575 TEAKWOOD DR L13 | 089 | RAC | 2023-11-15 | U125566 | U134723 | 2022-06-17 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-11-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2541.18 | 0 | 0 | 0 | 2541.18 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110823600 |  | 100461432 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | TEAKWOOD | 577 TEAKWOOD DR | 089 | RAC | 2023-11-15 | U125566 | U134723 | 2022-06-17 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-11-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2568.14 | 0 | 0 | 0 | 2568.14 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129016000 |  | 100264628 |  | 7384168I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | TAYLOR FORK | 228 TAYLOR FORK RD | 195 | S W | 2023-11-16 | U135005 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JAHOWARD | 2023-11-15 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.2 | 1 | 899.18 | 15.66 | 0 | 0.87 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2682 | 22979048900 |  | 100463393 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | LEFT FORK BULL | LEFT FORK BULL CK | 071 | PRE | 2023-11-15 | U130172 | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | JOHN KIRK | 2023-11-15 | 2023-11-15 |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 3.15 | 1 | 251.48 | 238.21 | 0 | 13.27 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166671800 |  | 100322612 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 737 BERRY LN | 067 | LEX | 2023-11-15 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-11-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1326.76 | 0 | 0 | 0 | 1326.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23198566100 |  | 100328606 |  | 6720208B | 2286441 |  |  | 565 | EX | RPLC SL/22026166900 | 2600B | RICHMOND | 1814 RICHMOND RD | 067 | LEX | 2023-11-16 | U123111 | U125763 | 2023-06-30 | 2023-12-29 |  |  | LYN STAFFORD | 2023-11-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3043.35 | 0 | 0 | 0 | 3043.35 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23198566300 |  | 100328608 |  | 6720208B | 2286441 |  |  | 565 | EX | RPLC SL/22026166900 | 2600B | RICHMOND | 1824 RICHMOND RD | 067 | LEX | 2023-11-16 | U123111 | U125763 | 2023-06-30 | 2023-12-29 |  |  | LYN STAFFORD | 2023-11-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3941.15 | 0 | 0 | 0 | 3941.15 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23203500200 |  | 100280561 |  | 6688228I | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | HICKORY | 139 HICKORY DR | 073 | FRA | 2023-11-15 | MCRAIG | AOC SYST | 2023-07-24 | 2024-01-24 | 2024-12-31 |  | MCRAIG | 2023-11-15 | 2023-11-13 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 37.7167 | 8 | 4359.94 | 2873.26 | 285.76 | 1200.92 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23205502600 |  | 100415695 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | GAYLE | 1804 GAYLE DR | 067 | LEX | 2023-11-15 | JOCHOA | AOC SYST | 2023-08-01 | 2024-02-01 | 2024-12-31 |  | JOCHOA | 2023-11-15 | 2023-11-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 17.35 | 3 | 1562.16 | 1281.99 | 208.74 | 71.43 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210315200 |  | 100269769 |  | 6732252O | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | BROADWAY | 510 BROADWAY AV | 097 | CYN | 2023-11-15 | U126604 | U125763 | 2023-08-23 | 2023-12-29 |  |  | WILL FULKS | 2023-11-15 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1775.49 | 0 | 0 | 0 | 1775.49 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210315300 |  | 100269770 |  | 6732252O | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | BROADWAY | 512 BROADWAY AV | 097 | CYN | 2023-11-15 | U126604 | U125763 | 2023-08-23 | 2023-12-29 |  |  | WILL FULKS | 2023-11-15 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1610.15 | 0 | 0 | 0 | 1610.15 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23218936400 |  | 100291708 |  | 6720216H |  |  |  | 565 | EX | REPLACE SL AND RISER | 2621P | FAULKNER | 712 FAULKNER AV | 067 | LEX | 2023-11-15 | RSTRONG | U135005 | 2023-10-04 | 2024-12-31 |  |  | RSTRONG | 2023-11-15 | 2023-11-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.8833 | 3 | 1978.48 | 1096.53 | 569.38 | 312.57 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23220341000 |  | 100328971 |  | 6720208K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332860 | 2621P | TANNER | 2690 TANNER CT | 067 | LEX | 2023-11-15 | U128336 | U135005 | 2023-10-10 | 2024-04-05 | 2025-10-31 |  | JOSHUA COX | 2023-11-15 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 30.8 | 3 | 2756.4 | 2304.2 | 323.79 | 128.41 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23224221600 |  | 100248063 |  | 7352256B |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | MAIN | 2824 MAIN ST | 019 | ASH | 2023-11-16 | U135005 | U133234 | 2023-11-02 | 2023-11-15 | 2023-12-01 |  | JROGER1 | 2023-11-15 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.7333 | 2 | 477.85 | 318.63 | 141.46 | 17.76 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23226027600 |  | 100289756 |  | 6720216P |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SPRING STATION | 2080 SPRING STATION DR | 067 | LEX | 2023-11-16 | U135005 | U129939 | 2023-11-15 | 2024-01-26 | 2025-07-31 |  | LSTANFI | 2023-11-15 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 3.4333 | 2 | 1767.44 | 1266.22 | 379.61 | 121.61 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 06637268800 |  | 100264643 |  | X1809-54 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | ROGERS PARK | ROGERS PARK RD | 195 | S W | 2023-11-16 | JAHOWARD | DYOUNG | 2006-02-02 | 2022-07-01 | 2023-12-31 |  | JAHOWARD | 2023-11-16 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.1167 | 1 | 1058.77 | 166.83 | 0 | 9.29 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883081800 |  | 100465005 |  | 7348140T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PM3 | PM3 | 071 | MCD | 2023-11-16 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BLAKE MULLINS | 2023-11-16 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.8667 | 1 | 261.64 | 131.1 | 0 | 130.54 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883139900 |  | 100426210 |  | 7344156T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PM83 | PM83 | 071 | PRT | 2023-11-17 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BRIAN PREECE | 2023-11-16 | 2023-11-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.5 | 1 | 118.44 | 112.19 | 0 | 6.25 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883143000 |  | 100264539 |  | 7384168F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | TURKEY CREEK | TURKEY CREEK RD | 195 | S W | 2023-11-16 | JAHOWARD | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JAHOWARD | 2023-11-16 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.1167 | 1 | 2342.79 | 399.44 | 0 | 22.25 | 1921.1 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883154600 |  | 100426771 |  | 7388156T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | HIGHWAY 582 | 8364 HIGHWAY 582 | 119 | PIN | 2023-11-16 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-16 | 2023-11-16 |  | B | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 1.3833 | 1 | 1287.09 | 104.26 | 0 | 5.81 | 1177.02 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883167100 |  | 500184118 |  | 7388156T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | HIGHWAY 582 | 25 HIGHWAY 582 | 119 | PIN | 2023-11-16 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-16 | 2023-11-16 |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 1.3667 | 1 | 108.46 | 102.74 | 0 | 5.72 | 0 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883190800 |  | 100430460 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | GENERAL DELIVE | GENERAL DELIVE | 153 | GUN | 2023-11-17 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-16 | 2023-11-16 |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 3.9 | 1 | 315.74 | 299.07 | 0 | 16.67 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883201400 |  | 100414675 |  | 7348140T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PM3 | PM3 | 071 | E M | 2023-11-17 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BLAKE MULLINS | 2023-11-16 | 2023-11-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.4 | 2 | 451.34 | 244.52 | 0 | 206.82 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883260800 |  | 100424222 |  | 7340156T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY RT 850 | 6328 KY RT 850 | 071 | HIP | 2023-11-16 | U130172 | U120245 | 2021-01-30 | 2023-11-16 | 2023-12-31 |  | JOHN KIRK | 2023-11-16 | 2023-11-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.4 | 1 | 32.14 | 30.44 | 0 | 1.7 | 0 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883300900 |  | 100426398 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | GENERAL DELIVE | GENERAL DELIVE | 071 | HIP | 2023-11-16 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-16 | 2023-11-16 |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 0.58333 | 1 | 46.61 | 44.14 | 0 | 2.47 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21960851700 |  | 100250231 |  | 7360248A | 2180320 |  |  | 566 | EX | ABANDON SL W/21-0261304-00 | 2600B | 36TH | 439 36TH ST | 019 | CAT | 2023-11-20 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | CJH CASEY PACK/MBLANKE | 2023-11-16 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 |  | 1
KY | KY - EAST | 2631 | 21960888000 |  | 100467605 |  | 7356248H | 2180320 |  |  | 566 | EX | ABANDON SL W/21-0261304-00 | 2600B | PADDLE CREEK | 8015 PADDLE CREEK RD | 019 | CAT | 2023-11-17 | U123965 | U134723 | 2021-12-21 | 2023-06-30 |  |  | MBLANKE | 2023-11-16 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 |  | 1
KY | KY - EAST | 2631 | 22110826900 |  | 500011512 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | TEAKWOOD | 569 TEAKWOOD DR | 089 | RAC | 2023-11-16 | U125566 | U134723 | 2022-06-17 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-11-16 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2000.75 | 0 | 0 | 0 | 2000.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026278401 |  | 501349282 |  | 6712204J | 2398051 | U461383 |  | 555 | EX | INSTALL 2300' OF 2"/4"PMMP MN | 2600B | LONGRIDGE | LONGRIDGE DR LT30 | 113 | NIC | 2023-11-20 | U128132 | U461383 | 2023-11-06 | 2023-09-27 | 2023-12-01 | 2023-11-15 | STEVE CANOY | 2023-11-16 | 2023-11-06 | 2023-09-20 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2784 |  |  | 100 | 055532230262784 | 256.65 | 106164 | 116796.05 | 17007.7 | 10120.85 | 14982.86 | 46299.02 | 0 | 1064.43 | 27321.19 | 2949
KY | KY - WEST | 2621 | 23166672200 |  | 100322610 |  | 6720208A | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 745 BERRY LN | 067 | LEX | 2023-11-16 | U461309 | U125763 | 2023-02-14 | 2023-02-19 | 2024-08-31 |  | R.HUMPHREYS | 2023-11-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 3659.92 | 578.07 | 265.88 | 124.13 | 2691.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23166677400 |  | 100322631 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 661 BERRY LN | 067 | LEX | 2023-11-16 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-11-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1821.08 | 0 | 0 | 0 | 1821.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23193790400 |  | 100323148 |  | 6716208L | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | ABBOTT | 790 ABBOTT RD | 067 | LEX | 2023-11-16 | RSTRONG | AOC SYST | 2023-06-08 | 2023-12-08 | 2024-12-31 |  | RSTRONG | 2023-11-16 | 2023-10-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 33.4333 | 8 | 2858.84 | 1951.61 | 459.76 | 447.47 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23205499300 |  | 100339232 |  | 4 GAYLE D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | GAYLE | 1860 GAYLE DR | 067 | LEX | 2023-11-20 | U135005 | AOC SYST | 2023-08-01 | 2024-02-01 | 2024-12-31 |  | ABLAKE | 2023-11-16 | 2023-11-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 21.7667 | 6 | 1682.6 | 1398.06 | 206.63 | 77.91 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210323000 |  | 100269860 |  | 6732252P | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | PLEASANT | 483 W PLEASANT ST | 097 | CYN | 2023-11-16 | U126604 | U125763 | 2023-08-23 | 2023-12-29 |  |  | WILL FULKS | 2023-11-16 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2760.39 | 0 | 0 | 0 | 2760.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23216219700 |  | 100330592 |  | 6732216P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332620 | 2621P | BRIAR HILL | 5680 BRIAR HILL RD | 067 | LEX | 2023-11-20 | U135005 | U135005 | 2023-09-21 | 2024-03-12 | 2025-09-30 |  | LSTANFI | 2023-11-16 | 2023-10-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.8 | 3 | 2455.82 | 1282.06 | 269.67 | 377.59 | 526.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23216223600 |  | 100283340 |  | 6712228E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HIAWATHA | 302 HIAWATHA TL | 209 | GEO | 2023-11-16 | DCOLLIN | U135005 | 2023-09-21 | 2023-12-29 | 2023-12-31 |  | DCOLLIN | 2023-11-16 | 2023-11-07 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 23.0667 | 6 | 6750.87 | 1810.61 | 288.87 | 583.46 | 4067.93 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23216223800 |  | 100283513 |  | 6712228E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HIAWATHA | 304 HIAWATHA TL | 209 | GEO | 2023-11-16 | DCOLLIN | U135005 | 2023-09-21 | 2023-12-29 | 2023-12-31 |  | DCOLLIN | 2023-11-16 | 2023-11-15 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 48.5833 | 5 | 10179.53 | 3847.35 | 314.51 | 1090.49 | 4927.18 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23225968100 |  | 100256408 |  | 7356256B |  |  |  | 566 | EX | ABANDON SL - DEMO | 2621P | BATH | 2408 BATH AV | 019 | ASH | 2023-11-17 | U132625 | U135005 | 2023-11-15 | 2023-11-15 | 2023-12-13 |  | JROGER1 | 2023-11-16 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 6.1833 | 3 | 444.24 | 387.98 | 0 | 56.26 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23226249200 |  | 100339233 |  | 6724212I | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621P | GAYLE | 1864 GAYLE DR | 067 | LEX | 2023-11-20 | U135005 | U129939 | 2023-11-16 | 2023-11-16 |  |  | ABLAKE | 2023-11-16 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 9.5167 | 2 | 1375.22 | 695.46 | 206.63 | 473.13 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23226526200 |  | 100262615 |  | 7352256D | 2074850 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | FERRY | 361 FERRY ST | 019 | ASH | 2023-11-27 | U124015 | U123235 | 2023-11-17 | 2024-12-31 |  |  | ORA SLONE | 2023-11-16 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 |  | 1
KY | KY - EAST | 2633 | 11913708200 |  | 500711377 |  | 7384168E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | HICKORY HILL | HICKORY HILL | 195 | S W | 2023-11-17 | U130172 | U907001 | 2011-06-28 | 2023-11-17 | 2023-12-31 |  | JAHOWARD | 2023-11-17 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 4.2333 | 1 | 1234.05 | 332.85 | 0 | 18.55 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 12995386000 |  | 100264653 |  | 7348168I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | ROGERS PARK | ROGERS PARK RD | 195 | S W | 2023-11-17 | JAHOWARD | U125208 | 2012-10-23 | 2023-11-17 | 2023-12-31 |  | JAHOWARD | 2023-11-17 | 2022-11-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.0333 | 2 | 1275.38 | 372.01 | 0 | 20.72 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883059000 |  | 100447381 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | KY ROUTE 114 | 4787 KY ROUTE 114 | 071 | PRE | 2023-11-17 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-17 | 2022-10-05 |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 1.5333 | 2 | 78.75 | 74.59 | 0 | 4.16 | 0 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883098800 |  | 100426846 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | LEFT FORK BULL | 406 LEFT FORK BULL CK | 071 | PRE | 2023-11-17 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-17 | 2023-11-17 |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 0.35 | 1 | 28.13 | 26.64 | 0 | 1.49 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883187400 |  | 100457373 |  | 7344144T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | WELL 3765 | WELL 3765 | 071 | MCD | 2023-11-17 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-17 | 2023-11-17 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.8167 | 1 | 146.23 | 138.5 | 0 | 7.73 | 0 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883248200 |  | 100426859 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | MEADE BRANCH | 738 MEADE BRANCH RD | 071 | PRE | 2023-11-17 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-17 | 2023-11-17 |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 0.73333 | 1 | 58.68 | 55.57 | 0 | 3.11 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883292400 |  | 100249275 |  | 7328284F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | MAIN | 828 MAIN ST | 089 | S S | 2023-11-17 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-11-17 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.75 | 1 | 77.32 | 51.93 | 0 | 25.39 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883304100 |  | 100443922 |  | 7328284B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | MAIN | 810 MAIN ST | 089 | S S | 2023-11-17 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | RECUMP | 2023-11-17 | 2023-01-13 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2 | 3 | 203.4 | 136.96 | 0 | 66.44 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21959277600 |  | 100466556 |  | 7352256D | 2074850 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | SANDERS | 2304< SANDERS RD | 019 | ASH | 2023-11-27 | U124015 | U134723 | 2021-12-13 | 2022-12-30 |  |  | ORA SLONE | 2023-11-17 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 |  | 1
KY | KY - EAST | 2631 | 21959277700 |  | 100261158 |  | 7352256D | 2074850 |  |  | 566 | EX | ABANDON SL W/CAPITOL JOB | 2600B | SANDERS | 2306 SANDERS RD | 019 | ASH | 2023-11-27 | U124015 | U134723 | 2021-12-13 | 2022-12-30 |  |  | ORA SLONE | 2023-11-17 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 |  | 1
KY | KY - WEST | 2621 | 23166671900 |  | 100322654 |  | 6716208D | 2286046 |  |  | 565 | EX | RPLC SL/22026162100 | 2600B | BERRY | 740 BERRY LN | 067 | LEX | 2023-11-17 | U126530 | U125763 | 2023-02-14 | 2023-12-29 |  |  | JDUNN | 2023-11-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2026.53 | 0 | 0 | 0 | 2026.53 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23211042700 |  | 100268853 |  | 7352156G |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | OLD US 23 | OLD US 23 | 071 | STA | 2023-11-17 | JCKIRK | U133234 | 2023-08-25 | 2023-09-08 | 2023-09-24 |  | JCKIRK | 2023-11-17 | 2023-11-17 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 7.7833 | 2 | 2028.11 | 582.64 | 0 | 32.47 | 1413 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23225776000 |  | 100326253 |  | 6708212M |  |  |  | 565 | EX | GRADE 1 - REPLACE SL | 2621P | OLD VERSAILLES | 4976 OLD VERSAILLES RD | 067 | LEX | 2023-11-17 | HMCKUNE | U135005 | 2023-11-14 | 2023-11-10 | 2023-11-10 |  | HMCKUNE | 2023-11-17 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.5667 | 4 | 7205.08 | 1809 | 1310.66 | 100.86 | 3984.56 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883200400 |  | 100441409 |  | 7344156T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | KY ROUTE 122 | 2165 KY ROUTE 122 | 071 | PRT | 2023-11-21 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-20 | 2023-11-20 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.1667 | 1 | 254.69 | 241.25 | 0 | 13.44 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026234901 |  | 501339588 |  | 6748204D | 2293331 | U128885 |  | 555 | EX | INSTALL 4,100'-2" PMMP | 2600B | DUCLAIR | DUCLAIR DR LT38 | 049 | WIN | 2023-12-04 | U128132 | U128885 | 2023-11-02 | 2023-10-23 | 2023-12-01 | 2023-11-10 | DDAVIS | 2023-11-20 | 2023-11-09 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP2349 |  |  | 100 | 055532220262349 | 235.1167 | 68160 | 217597.98 | 16036.76 | 8855.5 | 10331.81 | 121553.86 | 0 | 1550.68 | 59269.37 | 2130
KY | KY - EAST | 2682 | 22129011700 |  | 100426414 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2633S | GENERAL DELIVE | GENERAL DELIVE | 071 | HUE | 2023-11-21 | U130172 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JOHN KIRK | 2023-11-20 | 2023-11-20 |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 0.48333 | 1 | 38.58 | 36.54 | 0 | 2.04 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129015900 |  | 100264642 |  | 7384168I |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ROGERS PARK | 377 ROGERS PARK RD | 195 | S W | 2023-11-20 | JAHOWARD | U130722 | 2022-09-05 | 2022-12-30 |  |  | JAHOWARD | 2023-11-20 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 8 | 1 | 2177.69 | 626.55 | 41.68 | 34.91 | 1474.55 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129118200 |  | 100426214 |  | 7344156T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | KY ROUTE 2030 | 2825 KY ROUTE 2030 | 071 | PRT | 2023-11-21 | U130172 | U125208 | 2022-09-06 | 2022-12-30 |  |  | JOHN KIRK | 2023-11-20 | 2023-11-20 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.86667 | 1 | 69.89 | 66.21 | 0 | 3.68 | 0 | 0 | 0 | 0
KY | KY - EAST | 2682 | 22979047400 |  | 100441643 |  | 7340136T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | GENERAL DELIVE | GENERAL DELIVE | 071 | WAY | 2023-11-21 | U130172 | U128070 | 2022-02-17 | 2023-12-29 | 2023-12-31 |  | JOHN KIRK | 2023-11-20 | 2023-11-20 |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 1.85 | 1 | 148.63 | 140.79 | 0 | 7.84 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026276600 |  |  |  | 6748204H | 2286588 | U461383 |  | 910 | EX | RETIRE RTU FACILITY | 2629M | STATE RT 89 | STATE RT 89 | 049 | WIN | 2023-12-16 | U123258 | U461383 | 2023-05-30 | 2024-05-31 | 2024-06-01 | 2023-11-20 | JPASLEY | 2023-11-20 | 2023-06-14 |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00910 | 3200910 |  |  | WP2766 |  |  | 100 | 091032230262766 | 7.75 | 0 | 2357.33 | 470.8 | 0 | 206.53 | 1680 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026298400 |  |  |  | 6748204H | 2286588 | U461383 |  | 909 | EX | INSTALL MODEM AND ANTENNA | 2629M | STATE RT 89 | STATE RT 89 | 049 | WIN | 2024-05-08 | U123258 | U461383 | 2023-10-03 | 2024-10-01 | 2024-10-01 | 2023-11-20 | JPASLEY | 2023-11-20 |  |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00909 | 3200909 |  |  | WP2984 |  |  | 100 | 090932230262984 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23223211000 |  | 100319517 |  | 6716208K | 2300594 |  |  | 565 | EX | SERVICE LINE/METER UPGRADE | 2621P | GREENBRIAR | 340 GREENBRIAR RD | 067 | LEX | 2023-11-28 | U135005 | U135005 | 2023-10-26 | 2023-11-22 | 2023-11-22 |  | JOSHUA COX | 2023-11-20 | 2023-11-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 57.2333 | 14 | 6557.52 | 3889.24 | 2451.39 | 216.89 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23226810700 |  | 100274387 |  | 6684228J |  |  |  | 565 | CO | SERVICE LINE REPLACE - D341153 | 2621P | ROBERTS | 402 ROBERTS ST FURN | 073 | FRA | 2023-11-21 |  | U134852 | 2023-11-20 | 2023-11-20 | 2023-11-20 |  | CDESPAIN | 2023-11-20 | 2023-11-20 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 46.2 | 5 | 4098.76 | 3555.55 | 0 | 543.21 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23227353400 |  | 100274387 |  | 6684228J |  |  |  | 566 | CO | ABANDON SERVICE LINE | 2621P | ROBERTS | 402 ROBERTS ST FURN | 073 | FRA | 2023-11-27 |  | U139701 | 2023-11-27 | 2023-11-27 |  |  | CDESPAIN | 2023-11-20 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26230043 |  | 1
KY | KY - EAST | 2633 | 21883066500 |  | 100259344 |  | 7344156T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | DINWOOD | 352 DINWOOD RD | 071 | MAR | 2023-11-22 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-21 | 2023-11-21 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.5 | 1 | 40.19 | 38.06 | 0 | 2.13 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883082400 |  | 100259323 |  | 7344160T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | P4 | P4 | 071 | MAR | 2023-11-21 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-21 | 2023-11-21 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.2 | 1 | 16.1 | 15.24 | 0 | 0.86 | 0 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883207200 |  | 100426654 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | GENERAL DELIVE | GENERAL DELIVE | 119 | CAR | 2023-11-21 | U130172 | U120245 | 2021-01-30 | 2023-11-21 |  |  | JOHN KIRK | 2023-11-21 |  |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 |  | 1
KY | KY - EAST | 2633 | 21883214700 |  | 100259154 |  | 7344156T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | P4 | P4 | 071 | MAR | 2023-11-22 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-21 | 2023-11-21 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.23333 | 1 | 18.47 | 17.5 | 0 | 0.97 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883264600 |  | 100261686 |  | 7344144T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | P2 | P2 | 071 | MCD | 2023-11-21 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BLAKE MULLINS | 2023-11-21 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - EAST | 2633 | 21883295900 |  | 100259211 |  | 7344136T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PM3 | PM3 | 071 | HI | 2023-11-22 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-21 | 2023-11-21 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.1667 | 1 | 174.32 | 165.12 | 0 | 9.2 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883305700 |  | 100431646 |  | 7344156T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | LINE P | LINE P | 071 | MAR | 2023-11-22 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BRIAN PREECE | 2023-11-21 | 2023-11-21 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.9 | 2 | 151.91 | 143.88 | 0 | 8.03 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129011600 |  | 100260562 |  | 7348140T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PM3 | PM3 | 071 | E M | 2023-11-22 | U130172 | U130722 | 2022-09-05 | 2022-12-30 |  |  | BLAKE MULLINS | 2023-11-21 | 2023-11-20 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 11.0667 | 2 | 1037.04 | 786.66 | 0 | 250.38 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129034600 |  | 100259339 |  | 7344156T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | DINWOOD | 265 DINWOOD RD | 071 | MAR | 2023-11-22 | U130172 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JOHN KIRK | 2023-11-21 | 2023-11-21 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.05 | 1 | 84.36 | 79.91 | 0 | 4.45 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23226474700 |  | 500230774 |  | 6744208P |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | MAIN | 69 S MAIN ST A | 049 | WIN | 2023-11-28 | U135005 | U133234 | 2023-11-17 | 2023-11-30 | 2023-12-16 |  | DENNING | 2023-11-21 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.9 | 2 | 253.72 | 240.32 | 0 | 13.4 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22136456300 |  | 500193719 |  | 7324132I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | MAIN | MAIN ST | 119 | HIN | 2023-11-22 | U130172 | U125763 | 2022-10-03 | 2022-12-30 | 2023-12-31 |  | JOHN HOWARD | 2023-11-22 | 2022-10-06 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 9.85 | 2 | 661.46 | 626.55 | 0 | 34.91 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22136456400 |  | 500193710 |  | 7324132I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | MAIN | MAIN ST | 119 | HIN | 2023-11-22 | U130172 | U125763 | 2022-10-03 | 2022-12-30 | 2023-12-31 |  | JOHN HOWARD | 2023-11-22 | 2023-11-21 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 16 | 2 | 1374.71 | 1302.15 | 0 | 72.56 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23221641700 |  | 100321797 |  | 6716212P |  |  |  | 566 | EX | ABANDON SL - DEMO/CITYRQD | 2621P | COLUMBIA | 550 COLUMBIA AV | 067 | LEX | 2023-11-28 | U135005 | U135005 | 2023-10-17 | 2023-11-17 | 2023-11-17 |  | HMCKUNE | 2023-11-22 | 2023-11-21 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.85 | 3 | 940.99 | 870.25 | 22.23 | 48.51 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23224051200 |  | 100322599 |  | 6716208D |  | U135005 |  | 566 | EX | ABANDON SL - DEMO/CITY RQD | 2621P | MOUNT VERNON | 720 MOUNT VERNON DR | 067 | LEX | 2023-11-22 | MSHARON | U135005 | 2023-11-01 | 2023-12-01 | 2023-12-01 |  | MSHARON | 2023-11-22 | 2023-11-22 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16 | 2 | 1053.82 | 962.18 | 38.01 | 53.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23227230000 |  | 100272965 |  | 6684224E | 1635077 |  |  | 565 | EX | REPLACE SERVICE GRD 1 | 2621P | BLADE | 665 BLADE AV | 073 | FRA | 2023-11-28 | U135005 | U130871 | 2023-11-22 | 2023-11-22 | 2023-11-22 |  | EFGOINS | 2023-11-22 | 2023-11-22 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 38.8 | 6 | 4779.21 | 2996.85 | 28.41 | 1103.95 | 650 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23227318600 |  | 100323621 |  | 6716208O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | THISTLETON | 3411 THISTLETON DR | 067 | LEX | 2023-11-24 | WISHII | U137248 | 2023-11-23 | 2023-11-22 | 2023-11-23 |  | WISHII | 2023-11-24 | 2023-11-24 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.55 | 3 | 1450.77 | 964.24 | 326.27 | 160.26 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21026154600 |  |  |  | 7360248A | 2180320 | U938437 |  | 584 | EX | RETIRE R-1354 | 2631M | LOUISA | 4570 LOUISA RD | 019 | CAT | 2023-12-22 | U123258 | U938437 | 2021-12-06 | 2023-12-29 | 2023-12-31 | 2023-11-26 | SHANE GIORDANO | 2023-11-26 |  |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00584 | 3200584 |  |  | WP1546 | AMRCB |  | 100 | 058432210261546 |  | 0 | 8911.51 | 0 | 0 | 0 | 8911.51 | 0 | 0 | 0
KY | KY - EAST | 2631 | 20026978100 |  |  |  | 7352256D | 2074850 | U938437 |  | 557 | EX | INSTALL 8620'- 2" PMMP | 2600B | HARRISON | HARRISON | 019 | ASH | 2023-12-12 | U123258 | U122858 | 2020-09-30 | 2023-05-30 | 2023-12-31 | 2023-10-10 | ORA SLONE | 2023-11-27 | 2023-01-03 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP9781 | AMRCB |  | 100 | 055732200269781 | 1609 | 1953630 | 1699797.2 | 102001.91 | 45761.8 | 21764.65 | 1237423.25 | 0 | 25005.64 | 267839.95 | 9303
KY | KY - EAST | 2631 | 20026978200 |  |  |  | 7352256D | 2074850 | U938437 |  | 558 | EX | RETIRE 8983' LP - 2520' BS | 2600B | HARRISON | HARRISON | 019 | ASH | 2023-12-11 | U123258 | U122858 | 2020-09-30 | 2023-12-29 | 2023-12-31 | 2023-11-16 | ORA SLONE | 2023-11-27 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP9782 | AMRCB |  | 100 | 055832200269782 |  | 0 | 513.02 | 263.94 | 0 | 29.08 | 220 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883081900 |  | 100259173 |  | 7340156T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW1836 | PW1836 | 071 | HI | 2023-11-28 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | BRIAN PREECE | 2023-11-27 | 2023-11-27 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.11667 | 2 | 9.06 | 8.57 | 0 | 0.49 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883105500 |  | 100259192 |  | 7344140T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PW5197 | PW5197 | 071 | HI | 2023-11-28 | U130172 | U120245 | 2021-01-30 | 2023-11-27 |  |  | JOHN KIRK | 2023-11-27 | 2023-11-27 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.61667 | 2 | 51.05 | 48.31 | 0 | 2.74 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883116300 |  | 100431486 |  | 7344140T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | STUMBO BRANCH | 274 STUMBO BRANCH RT 122 | 071 | HI | 2023-11-28 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JOHN KIRK | 2023-11-27 | 2023-11-27 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.4667 | 2 | 453.74 | 429.33 | 0 | 24.41 | 0 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883127300 |  | 100426497 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | GENERAL DELIVE | GENERAL DELIVE | 119 | MAL | 2023-11-28 | U130172 | U120245 | 2021-01-30 | 2023-11-27 |  |  | JOHN KIRK | 2023-11-27 | 2023-11-15 |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 0.05 | 3 | 5 | 4.74 | 0 | 0.26 | 0 | 0 | 0 | 0
KY | KY - EAST | 2682 | 21883226700 |  | 100426745 |  | NEW000000 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2633S | GENERAL DELIVE | GENERAL DELIVE | 119 | MAL | 2023-11-28 | U130172 | U120245 | 2021-01-30 | 2023-11-27 |  |  | JOHN KIRK | 2023-11-27 | 2023-11-27 |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 5.3667 | 2 | 456.83 | 431.7 | 0 | 25.13 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883328300 |  | 500484269 |  | 7384168I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | ROGERS PARK | ROGERS PARK RD | 195 | S W | 2023-11-27 | JAHOWARD | U120245 | 2021-01-30 | 2022-07-01 | 2023-12-31 |  | JAHOWARD | 2023-11-27 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 9 | 1 | 1626.8 | 704.88 | 0 | 39.27 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110822600 |  | 500729736 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | TEAKWOOD | 559 TEAKWOOD L21 | 089 | RAC | 2023-11-27 | U125566 | U134723 | 2022-06-17 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-11-27 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2564.77 | 0 | 0 | 0 | 2564.77 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110822900 |  | 500011798 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | TEAKWOOD | 563 TEAKWOOD DR L19 | 089 | RAC | 2023-11-27 | U124015 | U134723 | 2022-06-17 | 2023-12-29 |  |  | ORA SLONE | 2023-11-27 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1983.9 | 0 | 0 | 0 | 1983.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110823200 |  | 500743928 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | TEAKWOOD | 565 TEAKWOOD DR | 089 | RAC | 2023-11-27 | U124015 | U134723 | 2022-06-17 | 2023-12-29 |  |  | ORA SLONE | 2023-11-27 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2517.59 | 0 | 0 | 0 | 2517.59 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110824500 |  | 100457454 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | WILD CHERRY | 568 WILD CHERRY CR | 089 | RAC | 2023-11-27 | U125566 | U134723 | 2022-06-17 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-11-27 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2232.81 | 0 | 0 | 0 | 2232.81 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22129011800 |  | 100260469 |  | 7344152T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | PW4006 | PW4006 | 071 | HUN | 2023-11-28 | U130172 | U130722 | 2022-09-05 | 2022-12-30 |  |  | BLAKE MULLINS | 2023-11-27 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - WEST | 2623 | 23168132200 |  | 100275067 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | SAINT CLAIR | 234 SAINT CLAIR ST | 073 | FRA | 2023-11-27 | U461443 | U125763 | 2023-02-20 | 2023-12-29 |  |  | WGRAVES | 2023-11-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2570.77 | 0 | 0 | 0 | 2570.77 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23208382700 |  | 100358000 |  | 6740232N | 2286363 |  |  | 566 | EX | ABANDN SL/22026164000 | 2600B | CHAMBERS | 436 CHAMBERS ST | 017 | PAR | 2023-11-30 | U127414 | U125763 | 2023-08-15 | 2023-12-29 |  |  | ED FOX | 2023-11-27 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 1070.98 | 0 | 0 | 0 | 1070.98 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23208382800 |  | 100358001 |  | 6740232N | 2286363 |  |  | 565 | EX | RPLC SL/22026164000 | 2600B | CHAMBERS | 440 CHAMBERS ST | 017 | PAR | 2023-11-30 | U127414 | U125763 | 2023-08-15 | 2023-12-29 |  |  | ED FOX | 2023-11-27 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2308.57 | 0 | 0 | 0 | 2308.57 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23208384200 |  | 100358002 |  | 6740232N | 2286363 |  |  | 565 | EX | RPLC SL/22026164000 | 2600B | SCOTT | 500 SCOTT AV | 017 | PAR | 2023-11-27 | U126532 | U125763 | 2023-08-15 | 2023-12-29 |  |  | LESLIE SHARON | 2023-11-27 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2383.36 | 0 | 0 | 0 | 2383.36 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210315400 |  | 100269859 |  | 6732252O | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | CLADORBON | 102 CLADORBON DR | 097 | CYN | 2023-11-27 | U126604 | U125763 | 2023-08-23 | 2023-12-29 |  |  | WILL FULKS | 2023-11-27 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2768.73 | 0 | 0 | 0 | 2768.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23213258600 |  | 100340615 |  | 6724212E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | CHARLESTON | 1703 CHARLESTON CT | 067 | LEX | 2023-11-28 | U135005 | AOC SYST | 2023-09-06 | 2024-03-06 | 2024-12-31 |  | KKINDER | 2023-11-27 | 2023-11-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 22.7667 | 7 | 2377.42 | 1655.35 | 629.83 | 92.24 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23224228500 |  | 100315948 |  | 6716208G |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | NICHOLASVILLE | 1729 NICHOLASVILLE RD 2 | 067 | LEX | 2023-11-28 | U135005 | U133234 | 2023-11-02 | 2023-11-16 | 2023-12-02 |  | RSTRONG | 2023-11-27 | 2023-11-17 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 18.6 | 4 | 1656.78 | 1312.54 | 18.18 | 326.06 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23224231200 |  | 100315947 |  | 6716208G |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | NICHOLASVILLE | 1729 NICHOLASVILLE RD 1 | 067 | LEX | 2023-11-27 | RSTRONG | U133234 | 2023-11-02 | 2023-11-16 | 2023-12-02 |  | RSTRONG | 2023-11-27 | 2023-11-27 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.3 | 0 | 1193.21 | 480.89 | 0 | 65.82 | 646.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23224240200 |  | 100315957 |  | 6716208G |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | NICHOLASVILLE | 1729 NICHOLASVILLE RD 10 | 067 | LEX | 2023-11-27 | RSTRONG | U133234 | 2023-11-02 | 2023-11-16 | 2023-12-02 |  | RSTRONG | 2023-11-27 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.05 | 1 | 5.43 | 3.72 | 0 | 1.71 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23224243200 |  | 100315958 |  | 6716208G |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | NICHOLASVILLE | 1729 NICHOLASVILLE RD 11 | 067 | LEX | 2023-11-27 | RSTRONG | U133234 | 2023-11-02 | 2023-11-16 | 2023-12-02 |  | RSTRONG | 2023-11-27 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.05 | 1 | 5.43 | 3.72 | 0 | 1.71 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23224247300 |  | 100315959 |  | 6716208G |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | NICHOLASVILLE | 1729 NICHOLASVILLE RD 12 | 067 | LEX | 2023-11-27 | RSTRONG | U133234 | 2023-11-02 | 2023-11-16 | 2023-12-02 |  | RSTRONG | 2023-11-27 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.05 | 1 | 5.43 | 3.72 | 0 | 1.71 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23224252400 |  | 100315949 |  | 6716208G |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | NICHOLASVILLE | 1729 NICHOLASVILLE RD 3 | 067 | LEX | 2023-11-27 | RSTRONG | U133234 | 2023-11-02 | 2023-11-16 | 2023-12-02 |  | RSTRONG | 2023-11-27 | 2023-11-17 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.85 | 3 | 306.15 | 234.57 | 0 | 71.58 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23224260300 |  | 100315951 |  | 6716208G |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | NICHOLASVILLE | 1729 NICHOLASVILLE RD 5 | 067 | LEX | 2023-11-27 | RSTRONG | U133234 | 2023-11-02 | 2023-11-16 | 2023-12-02 |  | RSTRONG | 2023-11-27 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.033333 | 1 | 3.27 | 2.24 | 0 | 1.03 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23224263300 |  | 100315952 |  | 6716208G |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | NICHOLASVILLE | 1729 NICHOLASVILLE RD 6 | 067 | LEX | 2023-11-27 | RSTRONG | U133234 | 2023-11-02 | 2023-11-16 | 2023-12-02 |  | RSTRONG | 2023-11-27 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.033333 | 1 | 3.27 | 2.24 | 0 | 1.03 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23224265400 |  | 100315953 |  | 6716208G |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | NICHOLASVILLE | 1729 NICHOLASVILLE RD 7 | 067 | LEX | 2023-11-27 | RSTRONG | U133234 | 2023-11-02 | 2023-11-16 | 2023-12-02 |  | RSTRONG | 2023-11-27 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.033333 | 1 | 3.27 | 2.24 | 0 | 1.03 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23224269500 |  | 100315956 |  | 6716208G |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | NICHOLASVILLE | 1729 NICHOLASVILLE RD 8 | 067 | LEX | 2023-11-27 | RSTRONG | U133234 | 2023-11-02 | 2023-11-16 | 2023-12-02 |  | RSTRONG | 2023-11-27 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.033333 | 1 | 3.27 | 2.24 | 0 | 1.03 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23224271700 |  | 100315954 |  | 6716208G |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | NICHOLASVILLE | 1729 NICHOLASVILLE RD 9 | 067 | LEX | 2023-11-27 | RSTRONG | U133234 | 2023-11-02 | 2023-11-16 | 2023-12-02 |  | RSTRONG | 2023-11-27 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.05 | 1 | 5.43 | 3.72 | 0 | 1.71 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23224417400 |  | 100315950 |  | 6716208G |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | NICHOLASVILLE | 1729 NICHOLASVILLE RD 4 | 067 | LEX | 2023-11-27 | RSTRONG | U133234 | 2023-11-03 | 2023-11-16 | 2023-12-02 |  | RSTRONG | 2023-11-27 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.3333 | 3 | 395.5 | 374.11 | 0 | 21.39 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23226421300 |  | 100349495 |  | 6744208P |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | MAIN | 71 S MAIN ST | 049 | WIN | 2023-11-28 | U135005 | U133234 | 2023-11-17 | 2023-11-30 | 2023-12-16 |  | DENNING | 2023-11-27 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 11.4 | 3 | 1027.51 | 929.57 | 46.1 | 51.84 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23226424800 |  | 100468584 |  | 6744208P |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | MAIN | 69 S MAIN ST B | 049 | WIN | 2023-11-28 | U135005 | U133234 | 2023-11-17 | 2023-11-30 | 2023-12-16 |  | DENNING | 2023-11-27 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.35 | 3 | 464.85 | 440.27 | 0 | 24.58 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23227340200 |  | 100317916 |  | 6716204G |  |  |  | 565 | EX | REPLACE SERVICE LINE D311132 | 2621P | CAMELOT | 3512 CAMELOT DR | 067 | LEX | 2023-11-28 | U135005 | U139701 | 2023-11-27 | 2023-11-28 | 2023-12-16 |  | LSTANFI | 2023-11-27 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.6333 | 2 | 1321.18 | 870.39 | 220.76 | 230.03 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23227384600 |  | 100449114 |  | 6716212C |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | CHILES | 712 CHILES AV | 067 | LEX | 2023-11-28 | U135005 | U139701 | 2023-11-27 | 2023-11-27 |  |  | TROE | 2023-11-27 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.8333 | 3 | 9505.1 | 4108.11 | 828.93 | 641.35 | 3926.71 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23227396000 |  | 500732883 |  | 7348264E | 1855482 |  |  | 565 | EX | RPLC SL/18026793901 | 2600B | TEAKWOOD | 555 TEAKWOOD DR | 089 | RAC | 2023-11-27 | U124015 | U125763 | 2023-11-27 | 2023-12-29 |  |  | ORA SLONE | 2023-11-27 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2119.67 | 0 | 0 | 0 | 2119.67 | 0 | 0 | 0
KY | KY - EAST | 2633 | 05610413100 |  | 100264793 | 30 | X-1815 3 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | LIGE FORK | LIGE FORK RD | 195 | S W | 2023-11-29 | U135005 | CESTEP | 2005-05-10 | 2023-11-28 | 2024-12-31 |  | JAHOWARD | 2023-11-28 | 2022-11-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.43333 | 2 | 1727.43 | 13.29 | 0 | 0.73 | 1713.41 | 0 | 0 | 0
KY | KY - EAST | 2633 | 06640986400 |  | 100264569 | 22 | X1810-33 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | MILLARD AD | MILLARD AD SR292 | 195 | S W | 2023-11-28 | JAHOWARD | LDAVIS | 2006-03-09 | 2023-11-28 | 2024-12-31 |  | JAHOWARD | 2023-11-28 | 2022-11-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 4.1 | 2 | 1199.34 | 299.98 | 0 | 16.71 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129071100 |  | 100245330 |  | 7360248B |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | 34TH | 200 34TH ST | 019 | CAT | 2024-01-02 | U135005 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RECUMP | 2023-11-28 | 2023-11-09 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 18.6333 | 7 | 1967.98 | 1349.27 | 20.27 | 598.44 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026306200 |  |  |  | 6760172J | 2074684 | U128885 |  | 577 | EX | INSTALL BUILDINGS R-1667 | 2629M | DUG HILL | 724 DUG HILL RD | 065 | IRV | 2024-01-10 | U123258 | U128885 | 2023-11-27 | 2023-12-29 | 2023-12-31 | 2023-11-28 | WADE SHIMFESSEL | 2023-11-28 |  |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00577 | 3200577 |  |  | WP3062 |  |  | 100 | 057732230263062 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23174358500 |  | 100283511 |  | 6712228E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | MOHEGAN | 904 MOHEGAN TL | 209 | GEO | 2023-11-29 | U135005 | AOC SYST | 2023-03-16 | 2023-09-15 | 2024-12-31 |  | DCOLLIN | 2023-11-28 | 2023-06-07 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 16.6833 | 3 | 2220.24 | 1304.07 | 328.29 | 587.88 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23198566400 |  | 100328609 |  | 6720208B | 2286441 |  |  | 565 | EX | RPLC SL/22026166900 | 2600B | RICHMOND | 1828 RICHMOND RD | 067 | LEX | 2023-11-29 | U126603 | U125763 | 2023-06-30 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-11-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2424.14 | 0 | 0 | 0 | 2424.14 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23198566500 |  | 100328610 |  | 6720208B | 2286441 |  |  | 565 | EX | RPLC SL/22026166900 | 2600B | RICHMOND | 1832 RICHMOND RD | 067 | LEX | 2023-11-28 | U126603 | U125763 | 2023-06-30 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-11-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 5034.71 | 0 | 0 | 0 | 5034.71 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23208384300 |  | 100358003 |  | 6740232N | 2286363 |  |  | 565 | EX | RPLC SL/22026164000 | 2600B | SCOTT | 508 SCOTT AV | 017 | PAR | 2023-11-28 | U126532 | U125763 | 2023-08-15 | 2023-12-29 |  |  | LESLIE SHARON | 2023-11-28 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2534.11 | 0 | 0 | 0 | 2534.11 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210315500 |  | 100269761 |  | 6732252O | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | CLADORBON | 103 CLADORBON DR | 097 | CYN | 2023-11-28 | U126604 | U125763 | 2023-08-23 | 2023-12-29 |  |  | WILL FULKS | 2023-11-28 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2497.18 | 0 | 0 | 0 | 2497.18 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23220366400 |  | 100269093 |  | 6736252M |  |  |  | 566 | EX | ABANDON SL | 2621P | PLEASANT | 320 E PLEASANT ST W-HEAT | 097 | CYN | 2023-11-28 | NRICHIE | U135005 | 2023-10-10 | 2023-12-08 |  |  | NRICHIE | 2023-11-28 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10.9 | 3 | 932.31 | 883.08 | 0 | 49.23 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23224819300 |  | 100305266 |  | 6712212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309083 | 2621P | WILLIAMSBURG | 1812 WILLIAMSBURG RD | 067 | LEX | 2023-11-29 | U135005 | U135005 | 2023-11-07 | 2024-01-31 |  |  | KKINDER | 2023-11-28 | 2023-11-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.1 | 3 | 1892.11 | 1138.74 | 689.9 | 63.47 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23227383800 |  | 100269760 |  | 6732252O | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | CLADORBON | 101 CLADORBON DR | 097 | CYN | 2023-11-28 | U126604 | U123235 | 2023-11-27 | 2024-12-31 |  |  | WILL FULKS | 2023-11-28 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2363.42 | 0 | 0 | 0 | 2363.42 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23227385600 |  | 100347082 |  | 6696212K |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | TYRONE | 850 TYRONE PK | 239 | VER | 2023-11-29 | U128410 | U135005 | 2023-11-27 | 2023-11-28 | 2024-01-29 |  | CDESPAIN | 2023-11-28 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3281.83 | 1832.29 | 853.42 | 102.12 | 494 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23227517400 |  | 100434569 |  | 7320284N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | KY 8 | 18694 E KY 8 | 135 | FIR | 2023-11-29 | U135005 | U129939 | 2023-11-28 | 2023-11-17 | 2023-12-05 |  | BROBERT | 2023-11-28 | 2023-11-27 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 34.25 | 5 | 7773.13 | 2150.13 | 71.88 | 1863.24 | 3687.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23227536100 |  | 100315960 |  | 6716208G |  |  |  | 566 | EX | PAPER ABANDON TAP | 2621P | NICHOLASVILLE | 1729 NICHOLASVILLE RD WH | 067 | LEX | 2023-11-28 | U135005 | U135005 | 2023-11-28 | 2023-11-28 |  |  | OFFICE | 2023-11-28 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - CENTRAL | 2629 | 23227539500 |  | 100460049 |  | 6744208P |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | LEXINGTON | 1 E LEXINGTON AV | 049 | WIN | 2023-11-28 | DENNING | U129939 | 2023-11-28 | 2023-11-28 |  |  | DENNING | 2023-11-28 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3 | 3 | 258.26 | 244.64 | 0 | 13.62 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23227555200 |  | 100264794 |  | 7384168G |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | HAPPY VALLEY | 166 HAPPY VALLEY RD | 195 | S W | 2023-11-28 | U130172 | U129939 | 2023-11-28 | 2023-11-28 |  |  | JAHOWARD | 2023-11-28 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 06663620200 |  | 500631751 |  | T-1602-40 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | US ROUTE 23 | US ROUTE 23 | 089 | S S | 2023-11-29 | RECUMP | CTAULBE | 2006-10-19 | 2022-07-01 | 2024-12-31 |  | RECUMP | 2023-11-29 | 2023-07-13 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.2667 | 5 | 285.23 | 220.04 | 0 | 65.19 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883134000 |  | 100421698 |  | 7372188N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | BEAUTY | BEAUTY RD | 159 | BEA | 2023-11-29 | JAHOWARD | U120245 | 2021-01-30 | 2022-07-01 | 2024-12-31 |  | JAHOWARD | 2023-11-29 | 2022-11-17 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.4 | 2 | 1895.31 | 172.29 | 0 | 9.61 | 1713.41 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110822800 |  | 500583773 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | TEAKWOOD | 558 TEAKWOOD DR | 089 | RAC | 2023-11-29 | U124015 | U134723 | 2022-06-17 | 2023-12-29 |  |  | ORA SLONE | 2023-11-29 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2591.73 | 0 | 0 | 0 | 2591.73 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110823100 |  | 500503990 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | TEAKWOOD | 564 TEAKWOOD DR | 089 | RAC | 2023-11-29 | U125566 | U134723 | 2022-06-17 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-11-29 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2608.58 | 0 | 0 | 0 | 2608.58 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110823300 |  | 100461640 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | TEAKWOOD | 573 TEAKWOOD DR | 089 | RAC | 2023-11-29 | U124015 | U134723 | 2022-06-17 | 2023-12-29 |  |  | ORA SLONE | 2023-11-29 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2563.81 | 0 | 0 | 0 | 2563.81 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110824600 |  | 100465077 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | WILD CHERRY | 571 WILD CHERRY CR | 089 | RAC | 2023-11-29 | U125566 | U134723 | 2022-06-17 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-11-29 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2551.29 | 0 | 0 | 0 | 2551.29 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110824800 |  | 100457471 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | WILD CHERRY | 572 WILD CHERRY CR | 089 | RAC | 2023-11-29 | U124015 | U134723 | 2022-06-17 | 2023-12-29 |  |  | ORA SLONE | 2023-11-29 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2456.93 | 0 | 0 | 0 | 2456.93 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110825300 |  | 500724571 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | WILLIAMS | 900 WILLIAMS AV | 089 | RAC | 2023-11-30 | U125566 | U134723 | 2022-06-17 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-11-29 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1747.08 | 0 | 0 | 0 | 1747.08 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110827000 |  | 100466773 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | TEAKWOOD | 571 TEAKWOOD DR | 089 | RAC | 2023-11-29 | U124015 | U134723 | 2022-06-17 | 2023-12-29 |  |  | ORA SLONE | 2023-11-29 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2813.2 | 0 | 0 | 0 | 2813.2 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110827400 |  | 100457251 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | WILD CHERRY | 570 WILD CHERRY CR | 089 | RAC | 2023-11-29 | U125566 | U134723 | 2022-06-17 | 2023-12-29 |  |  | DAVID SKAGGS | 2023-11-29 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2405.17 | 0 | 0 | 0 | 2405.17 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110827600 |  | 100465465 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | WILD CHERRY | 578 WILD CHERRY CR | 089 | RAC | 2023-11-29 | U124015 | U134723 | 2022-06-17 | 2023-12-29 |  |  | ORA SLONE | 2023-11-29 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2039.27 | 0 | 0 | 0 | 2039.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026304100 |  |  |  | 6716208C | 2301315 | U461383 |  | 562 | EX | RETIRE 667' OF 2"PMMP MAIN | 2621P | STATE | 144 STATE ST | 067 | LEX | 2023-12-19 | U128132 | U461383 | 2023-10-30 | 2023-12-29 | 2023-12-31 | 2023-11-29 | JOSHUA COX | 2023-11-29 | 2023-11-17 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP3041 |  |  | 100 | 056232230263041 | 50.6333 | 0 | 4930.16 | 3511.19 | 256.05 | 718.92 | 444 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23198566800 |  | 100328605 |  | 6720208B | 2286441 |  |  | 565 | EX | RPLC SL/22026166900 | 2600B | RICHMOND | 1810 RICHMOND RD | 067 | LEX | 2023-11-30 | U126603 | U125763 | 2023-06-30 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-11-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3190.22 | 0 | 0 | 0 | 3190.22 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23208382300 |  | 100357984 |  | 6740232N | 2286363 |  |  | 565 | EX | RPLC SL/22026164000 | 2600B | CHAMBERS | 423 CHAMBERS ST | 017 | PAR | 2023-11-30 | U127414 | U125763 | 2023-08-15 | 2023-12-29 |  |  | ED FOX | 2023-11-29 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2466.46 | 0 | 0 | 0 | 2466.46 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210318000 |  | 100269838 |  | 6732252O | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | EVERGREEN | 102 EVERGREEN CR | 097 | CYN | 2023-11-29 | U126604 | U125763 | 2023-08-23 | 2023-12-29 |  |  | WILL FULKS | 2023-11-29 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1587.99 | 0 | 0 | 0 | 1587.99 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210318100 |  | 100269837 |  | 6732252O | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | EVERGREEN | 106 EVERGREEN CR | 097 | CYN | 2023-11-29 | U126604 | U125763 | 2023-08-23 | 2023-12-29 |  |  | WILL FULKS | 2023-11-29 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2004.64 | 0 | 0 | 0 | 2004.64 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210318200 |  | 100269836 |  | 6732252O | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | EVERGREEN | 108 EVERGREEN CR | 097 | CYN | 2023-11-29 | U126604 | U125763 | 2023-08-23 | 2023-12-29 |  |  | WILL FULKS | 2023-11-29 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1785.03 | 0 | 0 | 0 | 1785.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23217083500 |  | 100340526 |  | 6724212E | 1635077 |  |  | 565 | EX | REPLACE SERVICE LINE | 2621D | ANNISTON | 1602 ANNISTON DR | 067 | LEX | 2023-11-30 | U135005 | AOC SYST | 2023-09-26 | 2024-03-05 | 2024-12-31 |  | ABLAKE | 2023-11-29 | 2023-11-29 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.0833 | 3 | 2273.49 | 1701.38 | 477.29 | 94.82 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23218562000 |  | 100329541 |  | 6720208G | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | COBURN | 2053 COBURN BV | 067 | LEX | 2023-11-30 | U135005 | AOC SYST | 2023-10-03 | 2024-04-02 | 2024-12-31 |  | WISHII | 2023-11-29 | 2023-11-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 22.9833 | 8 | 3052.97 | 1729.59 | 779.12 | 544.26 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23223427900 |  | 100269300 |  | 6736252M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | WALNUT | 144 N WALNUT ST UP | 097 | CYN | 2023-11-30 | U135005 | U135005 | 2023-10-27 | 2023-12-27 | 2023-12-27 |  | NRICHIE | 2023-11-29 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 18.8833 | 3 | 1994.84 | 1510.82 | 2.11 | 481.91 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23225225300 |  | 100322727 |  | 6716208D |  |  |  | 565 | EX | METER MOVE OUT | 2621P | COOPER | 739 COOPER DR | 067 | LEX | 2023-11-30 | U130722 | U135005 | 2023-11-09 | 2024-01-09 | 2024-01-09 |  | RJCRAWF | 2023-11-29 | 2023-11-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 41.1167 | 6 | 7184.51 | 3159.67 | 0 | 176.13 | 3848.71 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23226854000 |  | 100354359 |  | 7256280P |  |  |  | 565 | EX | REPLACE SL & RELOCATE METER | 2621P | 5TH | 306 E 5TH ST | 161 | MAY | 2023-11-30 | U135005 | RALLISO | 2023-11-20 | 2024-01-19 | 2024-02-21 |  | SDADAMS | 2023-11-29 | 2023-11-29 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26320031 | 12.8667 | 4 | 1540.21 | 934.21 | 240.8 | 365.2 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23227792000 |  | 501323800 |  | 7348264 | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2621P | TEAKWOOD | 572 TEAKWOOD DR | 089 | RAC | 2023-11-29 | U125566 | U124960 | 2023-11-29 | 2049-12-31 |  |  | DAVID SKAGGS | 2023-11-29 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1405.48 | 0 | 0 | 0 | 1405.48 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883103500 |  | 100246376 |  | 7372188N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | 3RD | 3RD ST | 159 | BEA | 2023-11-30 | JAHOWARD | U120245 | 2021-01-30 | 2022-07-01 | 2024-12-31 |  | JAHOWARD | 2023-11-30 | 2022-11-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 9.85 | 3 | 2268.35 | 751.9 | 0 | 41.9 | 1474.55 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883168500 |  | 100251674 |  | 7324288N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | RAILROAD | 542 RAILROAD ST | 089 | S P | 2023-11-30 | RECUMP | U120245 | 2021-01-30 | 2022-07-01 | 2024-12-31 |  | RECUMP | 2023-11-30 | 2023-10-23 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 7.3333 | 6 | 559.77 | 471.57 | 0 | 88.2 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21883328200 |  | 100251624 |  | 7340268E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | US ROUTE 23 | 1800 US ROUTE 23 | 089 | LLO | 2023-11-30 | RECUMP | U120245 | 2021-01-30 | 2023-08-24 | 2024-12-31 |  | RECUMP | 2023-11-30 | 2022-10-05 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 14.7667 | 12 | 1376.04 | 904.11 | 0 | 471.93 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026162102 |  |  |  | 6716208D | 2286046 | U461383 |  | 557 | EX | INSTALL 8150' OF 2"/4"PMMP | 2600B | BERRY | BERRY LN | 067 | LEX | 2024-01-24 | U136251 | U461383 | 2023-10-13 | 2023-11-01 | 2023-11-01 | 2023-08-30 | JDUNN | 2023-11-30 | 2023-10-16 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP1621 | AMRCB |  | 100 | 055732220261621 | 1252.7833 | 1308120 | 755714.67 | 83904.32 | 21718.23 | 12155.36 | 488522.91 | 0 | 6670.84 | 142743.01 | 7928
KY | KY - WEST | 2621 | 22026162200 |  |  |  | 6716208D | 2286046 | U461383 |  | 558 | EX | RETIRE 4600' OF 4"/6"BSLP MAIN | 2600B | BERRY | BERRY LN | 067 | LEX | 2024-01-10 | U136251 | U461383 | 2022-01-26 | 2023-12-31 | 2024-08-11 | 2023-11-27 | JDUNN | 2023-11-30 | 2023-11-27 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP1622 | AMRCB |  | 100 | 055832220261622 | 16.5 | 0 | 1442.96 | 1262.6 | 0 | 70.36 | 110 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026241001 |  | 501337737 |  | 6708228C | 2293887 | U126783 |  | 555 | EX | INSTALL 6375'-2"/4" PMMP ENV | 2600B | STREET B | STREET B LT15 | 209 | GEO | 2024-01-17 | U136251 | U126783 | 2023-06-20 | 2023-08-30 | 2023-12-31 | 2023-11-29 | DEREK PAYTON | 2023-11-30 | 2023-12-01 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2410 |  |  | 100 | 055532220262410 | 701.65 | 563640 | 797679.45 | 46244.33 | 26831.38 | 4441.06 | 553037.55 | 0 | 15277.99 | 151847.14 | 6405
KY | KY - EAST | 2631 | 22110822200 |  | 501056413 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | BENTWOOD | 596 BENTWOOD CR | 089 | RAC | 2023-11-30 | U124015 | U134723 | 2022-06-17 | 2023-12-29 |  |  | ORA SLONE | 2023-11-30 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2550.77 | 0 | 0 | 0 | 2550.77 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22110827500 |  | 100464478 |  | 7348264E | 1855482 |  |  | 565 | EX | REPLACE SL W/18-0267939-00 | 2600B | WILD CHERRY | 573 WILD CHERRY CR | 089 | RAC | 2023-11-30 | U124015 | U134723 | 2022-06-17 | 2023-12-29 |  |  | ORA SLONE | 2023-11-30 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2574.88 | 0 | 0 | 0 | 2574.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026285500 |  |  |  | 6716220A | 1530969 | U461383 |  | 584 | EX | RETIRE REG STATION #1129 | 2621M | GEORGETOWN | 4130 GEORGETOWN RD | 067 | LEX | 2024-02-12 | U123258 | U461383 | 2023-07-26 | 2024-03-01 | 2024-03-01 | 2023-11-30 | CONNOR WEMPE | 2023-11-30 | 2023-11-29 |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00584 | 3200584 |  |  | WP2855 |  |  | 100 | 058432230262855 | 21.9333 | 0 | 19139.56 | 1698.53 | 0 | 10437.19 | 7003.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168131600 |  | 100274985 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | SAINT CLAIR | 209 SAINT CLAIR ST | 073 | FRA | 2023-11-30 | U461443 | U125763 | 2023-02-20 | 2023-12-29 |  |  | WGRAVES | 2023-11-30 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3797.85 | 0 | 0 | 0 | 3797.85 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23168132100 |  | 100275062 |  | 6684228J | 2074544 |  |  | 565 | EX | RPLC SL/20026974600 | 2600B | SAINT CLAIR | 226 SAINT CLAIR ST | 073 | FRA | 2023-11-30 | U126309 | U125763 | 2023-02-20 | 2023-12-29 |  |  | JAMIE LYNN | 2023-11-30 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 12 | 2 | 5582.46 | 952.22 | 0 | 144.65 | 4485.59 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23192219100 |  | 100323924 |  | 6716208P | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | RAVEN | 828 RAVEN RD | 067 | LEX | 2023-11-30 | U128336 | AOC SYST | 2023-06-01 | 2023-12-01 | 2024-12-31 |  | JOSHUA COX | 2023-11-30 | 2023-10-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 25.0833 | 5 | 2476.1 | 1603.32 | 543.15 | 329.63 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23208382600 |  | 100357998 |  | 6740232N | 2286363 |  |  | 565 | EX | RPLC SL/22026164000 | 2600B | CHAMBERS | 430 CHAMBERS ST | 017 | PAR | 2023-11-30 | U126532 | U125763 | 2023-08-15 | 2023-12-29 |  |  | LESLIE SHARON | 2023-11-30 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2035.07 | 0 | 0 | 0 | 2035.07 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210318400 |  | 100269834 |  | 6732252O | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | EVERGREEN | 112 EVERGREEN CR | 097 | CYN | 2023-11-30 | U126604 | U125763 | 2023-08-23 | 2023-12-29 |  |  | WILL FULKS | 2023-11-30 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3041.16 | 0 | 0 | 0 | 3041.16 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23210318500 |  | 100269832 |  | 6732252O | 2293704 |  |  | 565 | EX | RPLC SL/22026237800 | 2600B | EVERGREEN | 114 EVERGREEN CR | 097 | CYN | 2023-11-30 | U126604 | U125763 | 2023-08-23 | 2023-12-29 |  |  | WILL FULKS | 2023-11-30 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2578.17 | 0 | 0 | 0 | 2578.17 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23213476100 |  | 100275817 |  | 6684228C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | AUDUBON | 109 AUDUBON DR | 073 | FRA | 2023-12-01 | U135005 | AOC SYST | 2023-09-07 | 2024-03-07 | 2024-12-31 |  | EFGOINS | 2023-11-30 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 36 | 5 | 3629.81 | 2572.18 | 914.28 | 143.35 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23216224100 |  | 100283539 |  | 6712228E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HIAWATHA | 509 HIAWATHA TL | 209 | GEO | 2023-12-01 | U135005 | U135005 | 2023-09-21 | 2023-12-29 | 2023-12-31 |  | DCOLLIN | 2023-11-30 | 2023-11-29 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 42.2167 | 5 | 5448.07 | 3105.38 | 361.91 | 1166.78 | 814 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23217664000 |  | 100329347 |  | 6720208G | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | SAINT ANN | 186 SAINT ANN DR | 067 | LEX | 2023-12-01 | U135005 | AOC SYST | 2023-09-28 | 2024-03-28 | 2024-12-31 |  | HMCKUNE | 2023-11-30 | 2023-10-31 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 62.7667 | 13 | 4538.47 | 3727.75 | 602.81 | 207.91 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23223763000 |  | 100319955 |  | 6716208L |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | BLUEBERRY | 342 BLUEBERRY RD | 067 | LEX | 2023-11-30 | RJCRAWF | U132761 | 2023-10-31 | 2024-01-02 | 2024-01-02 |  | RJCRAWF | 2023-11-30 | 2023-11-21 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.1 | 3 | 474.4 | 449.35 | 0 | 25.05 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23225639200 |  | 100271099 |  | 7244284I |  |  |  | 566 | EX | TWALKER/KY-PER RI#14 SL | 2621P | ASBURY | 2575 ASBURY RD | 023 | AUG | 2023-12-01 | U461383 | U461383 | 2023-11-13 | 2023-12-29 | 2023-12-31 |  | SDADAMS | 2023-11-30 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 2.3 | 1 | 188.46 | 178.51 | 0 | 9.95 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23228352800 |  | 100275052 |  | 6684228J |  |  |  | 566 | EX | PAPER ABANDN | 2600B | WAPPING | 316< WAPPING ST | 073 | FRA | 2023-12-01 | U125559 | U125763 | 2023-12-01 | 2023-12-29 |  |  | WILLIAM GRAVES | 2023-11-30 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - EAST | 2633 | 21883219500 |  | 100250585 |  | 7376184A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | WALNUT | WALNUT ST | 159 | LOV | 2023-12-01 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2024-12-31 |  | JAHOWARD | 2023-12-01 | 2022-11-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 8.2667 | 2 | 1639.91 | 717.93 | 0 | 39.33 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026307000 |  |  |  | 7360248A | 2180320 | U461383 |  | 586 | EX | RETIRE METAL BLDG | 2631M | LOUISA | 4570 LOUISA RD | 019 | CAT | 2023-12-04 | U123258 | U461383 | 2023-12-01 | 2023-12-29 | 2023-12-31 | 2023-11-26 | SHANE GIORDANO | 2023-12-01 |  |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00586 | 3200586 |  |  | WP3070 |  |  | 100 | 058632230263070 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23158293000 |  | 100275875 |  | 6684228F | 0994278 |  |  | 566 | EX | ABANDON SL - SOII/LGCY | 2621P | WILKINSON | 701 WILKINSON BV | 073 | FRA | 2023-12-04 | U461383 | U125208 | 2023-01-24 | 2023-12-08 | 2023-12-08 |  | CDESPAIN | 2023-12-01 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 13.2833 | 3 | 1192.34 | 1130.47 | 0 | 61.87 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23218177800 |  | 100329489 |  | 6720208G | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | SAINT WILLIAM | 138 SAINT WILLIAM DR | 067 | LEX | 2023-12-04 | U135005 | AOC SYST | 2023-09-29 | 2024-12-31 | 2024-12-31 |  | HMCKUNE | 2023-12-01 | 2023-11-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 27.8167 | 8 | 2324.5 | 1731.29 | 496.86 | 96.35 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23225415600 |  | 100449310 |  | 6720216L |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | PARIS | 2314 PARIS PK | 067 | LEX | 2023-12-04 | U135005 | U133234 | 2023-11-10 | 2023-11-22 | 2023-12-10 |  | JOCHOA | 2023-12-01 | 2023-11-28 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 50.3667 | 10 | 7731.32 | 3800.6 | 238.02 | 211.02 | 3481.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23227342100 |  | 100425526 |  | 6716212B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311025 | 2621P | FORBES | 137 S FORBES RD | 067 | LEX | 2023-12-04 | U135005 | U135005 | 2023-11-27 | 2024-05-22 | 2025-11-30 |  | LSTONE | 2023-12-01 | 2023-12-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 40.9333 | 4 | 10714.38 | 2976.03 | 353.21 | 165.23 | 7219.91 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23227943000 |  | 100409988 |  | 6716204A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NICHOLASVILLE | 3401 NICHOLASVILLE RD STE 106 | 067 | LEX | 2023-12-01 | U128336 | U135005 | 2023-11-30 | 2023-12-15 | 2023-12-30 |  | JOSHUA COX | 2023-12-01 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.8833 | 1 | 170.09 | 161.26 | 0 | 8.83 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23227943300 |  | 100412160 |  | 6716204A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NICHOLASVILLE | 3401 NICHOLASVILLE RD STE 102 | 067 | LEX | 2023-12-01 | U128336 | U135005 | 2023-11-30 | 2023-12-15 | 2023-12-30 |  | JOSHUA COX | 2023-12-01 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.8333 | 1 | 347.5 | 329.47 | 0 | 18.03 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23227943500 |  | 100410346 |  | 6716204A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | NICHOLASVILLE | 3401 NICHOLASVILLE RD STE 100 | 067 | LEX | 2023-12-01 | U128336 | U135005 | 2023-11-30 | 2023-12-15 | 2023-12-30 |  | JOSHUA COX | 2023-12-01 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.2833 | 1 | 211.07 | 200.11 | 0 | 10.96 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23227973600 |  | 100258467 |  | 7344264H |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | ST RT 693 | 1111 ST RT 693 | 089 | RAC | 2023-12-04 | U135005 | U139417 | 2023-11-30 | 2023-11-30 | 2023-11-30 |  | JROGER1 | 2023-12-01 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 7.8 | 2 | 644.44 | 429.07 | 191.62 | 23.75 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23228334900 |  | 100286908 |  | 6720212B |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CARLISLE | 180 CARLISLE AV | 067 | LEX | 2023-12-04 | U135005 | U139701 | 2023-12-01 | 2023-11-30 | 2023-11-30 |  | KKINDER | 2023-12-01 | 2023-11-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 24.0333 | 4 | 2916.51 | 2280.97 | 508.49 | 127.05 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 03534185200 |  | 100255258 | 11 | 7352176T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PAINTSVILLE DP | PAINTSVILLE DP | 115 | VAN | 2023-12-05 | U124015 | BFMULLI | 2003-03-19 | 2022-07-01 | 2024-12-31 |  | ORA SLONE | 2023-12-04 | 2022-11-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.26667 | 1 | 882.65 | 0 | 0 | 0 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883112200 |  | 100412042 |  | 7364188H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | SR40 | SR40 | 159 | INE | 2023-12-05 | U124015 | U120245 | 2021-01-30 | 2022-07-01 | 2024-12-31 |  | ORA SLONE | 2023-12-04 | 2022-11-17 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 4.7167 | 6 | 1351.87 | 405.07 | 0 | 64.15 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883149200 |  | 100253657 |  | 7364188H |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | SR40 | SR40 | 159 | INE | 2023-12-05 | U124015 | U120245 | 2021-01-30 | 2022-07-01 | 2024-12-31 |  | ORA SLONE | 2023-12-04 | 2023-11-29 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 8.3333 | 4 | 1784.05 | 766.06 | 0 | 135.34 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883285600 |  | 100250674 |  | 7376184E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | CHAPMAN | CHAPMAN ST | 159 | LOV | 2023-12-04 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2024-12-31 |  | JAHOWARD | 2023-12-04 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 7.9833 | 1 | 754.4 | 715.21 | 0 | 39.19 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23026302200 |  |  |  | 7356152A | 2301164 | U461383 |  | 584 | EX | RETIRE PAPER GAUGE | 2633M | LOWER HAROLD 1418 | LOWER HAROLD 1418 | 071 | HAR | 2024-03-04 | U128132 | U461383 | 2023-10-23 | 2024-12-13 | 2024-12-15 | 2023-12-04 | MATT RYAN | 2023-12-04 |  |  | F | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00584 | 3200584 |  |  | WP3022 |  |  | 100 | 058432230263022 | 8 | 0 | 1131.38 | 840.95 | 0 | 290.43 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026306000 |  |  |  | 6748180P | 2301940 | U128885 |  | 557 | EX | EMER-INSTALL 2'-3" PMMP | 2621P | WACO LOOP | 206 WACO LOOP RD | 151 | WAC | 2023-12-05 | U128132 | U128885 | 2023-11-22 | 2023-11-08 | 2023-11-17 | 2023-11-18 | WDENNING | 2023-12-04 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3060 |  |  | 100 | 055732230263060 |  | 2 | 6302.19 | 4426.08 | 625.17 | 930.21 | 0 | 0 | 14.61 | 306.12 | 2
KY | KY - CENTRAL | 2629 | 23026306100 |  |  |  | 6748180P | 2301940 | U128885 |  | 558 | EX | EMER-RETIRE 2'-3" PMMP | 2621P | WACO LOOP | 206 WACO LOOP RD | 151 | WAC | 2023-12-04 | U128132 | U128885 | 2023-11-22 | 2023-11-17 | 2023-11-17 | 2023-11-18 | WDENNING | 2023-12-04 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP3061 |  |  | 100 | 055832230263061 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23198565900 |  | 100328604 |  | 6720208B | 2286441 |  |  | 565 | EX | RPLC SL/22026166900 | 2600B | RICHMOND | 1800 RICHMOND RD | 067 | LEX | 2023-12-04 | U126603 | U125763 | 2023-06-30 | 2023-12-29 |  |  | SHAWN DENNIS | 2023-12-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2121.2 | 0 | 0 | 0 | 2121.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23221646000 |  | 100301680 |  | 6712212H |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | LIVERPOOL | 209 LIVERPOOL RD | 067 | LEX | 2023-12-05 | U135005 | U135005 | 2023-10-17 | 2024-12-31 |  |  | LSTONE | 2023-12-04 | 2023-12-04 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.6333 | 3 | 1639.85 | 1490.15 | 68.09 | 81.61 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23224454900 |  | 100275724 |  | 6684228C |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | FRAZIER | 102 FRAZIER RD | 073 | FRA | 2023-12-04 | EFGOINS | U133234 | 2023-11-03 | 2023-11-17 | 2023-12-03 |  | EFGOINS | 2023-12-04 | 2023-12-01 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 16.0333 | 3 | 1205.91 | 1143.28 | 0 | 62.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23225418800 |  | 500296422 |  | 6720216L |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | PARIS | 2314 PARIS PK RR | 067 | LEX | 2023-12-05 | U930915 | U133234 | 2023-11-10 | 2023-11-22 | 2023-12-10 |  | JOCHOA | 2023-12-04 | 2023-11-28 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 27.6 | 6 | 3873.09 | 2257.34 | 0 | 124.32 | 1491.43 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23227795600 |  | 100291173 |  | 6720216L |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | PARIS | 2314 PARIS PK COTT | 067 | LEX | 2023-12-05 | U930915 | U135005 | 2023-11-29 | 2023-12-13 | 2023-12-29 |  | JOCHOA | 2023-12-04 | 2023-12-04 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.85 | 2 | 361.47 | 342.72 | 0 | 18.75 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23227795900 |  | 501309568 |  | 6720216L |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | PARIS | 2314< PARIS PK COTT | 067 | LEX | 2023-12-04 | ABLAKE | U135005 | 2023-11-29 | 2023-12-13 | 2023-12-29 |  | ABLAKE | 2023-12-04 | 2023-12-04 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.75 | 2 | 163.75 | 155.26 | 0 | 8.49 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21026130400 |  |  |  | 7360248A | 2180320 | U938437 |  | 557 | EX | INSTALL 25,111'-2",4" PMMP | 2600B | PADDLE CREEK | PADDLE CREEK RD | 019 | CAT | 2023-12-22 | U128132 | U938437 | 2021-06-29 | 2022-08-04 | 2024-12-08 | 2023-08-15 | CJH C PACK/MBLANKE | 2023-12-05 | 2022-08-01 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP1304 | AMRCB |  | 100 | 055732210261304 | 3538.9667 | 10498840 | 4355642.45 | 266096.51 | 129550.37 | 61361.56 | 3231857.71 | 0 | -9169.45 | 675945.75 | 23540
KY | KY - EAST | 2631 | 21026130500 |  |  |  | 7360248A | 2180320 | U938437 |  | 558 | EX | RETIRE 25,000' OF BSLP MAINS | 2600B | PADDLE CREEK | PADDLE CREEK RD | 019 | CAT | 2023-12-20 | U128132 | U938437 | 2021-06-29 | 2023-12-29 | 2024-12-08 | 2023-11-16 | CJH C PACK/MBLANKE | 2023-12-05 | 2023-02-07 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP1305 | AMRCB |  | 100 | 055832210261305 | 20.6333 | 0 | 1741.22 | 1451.36 | 0 | 289.86 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21026154800 |  |  |  | 7360248A | 2180320 | U938437 |  | 558 | EX | RETIRE 35'-3" CSMP | 2600B | PADDLE CREEK | PADDLE CREEK RD | 019 | CAT | 2023-12-19 | U128132 | U938437 | 2021-12-06 | 2023-12-29 | 2023-12-31 | 2023-11-16 | CJH C PACK/MBLANKE | 2023-12-05 | 2022-09-29 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP1548 | AMRCB |  | 100 | 055832210261548 | 0.41667 | 0 | 27.2 | 21.98 | 0 | 5.22 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883125800 |  | 100250616 |  | 7376184A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | 1ST | 1ST ST | 159 | LOV | 2023-12-05 | U124015 | U120245 | 2021-01-30 | 2023-12-04 | 2024-12-31 |  | ORA SLONE | 2023-12-05 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 6.9667 | 2 | 1655.26 | 650.39 | 0 | 122.22 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883250700 |  | 100268804 |  | 7352156L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | EAST | EAST ST | 071 | JUS | 2023-12-05 | MBLANKE | U120245 | 2021-01-30 | 2023-12-04 | 2024-12-31 |  | MBLANKE | 2023-12-05 | 2022-10-06 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.1833 | 2 | 1217.07 | 281.71 | 0 | 52.71 | 882.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026294800 |  | 500457994 |  | 6712204H | 2300206 | U461383 |  | 555 | EX | INSTALL 225' OF 2"PMMP MAIN | 2600B | RETRAC | 491 RETRAC RD | 067 | LEX | 2023-12-20 | U128132 | U461383 | 2023-09-18 | 2023-12-14 | 2023-12-18 | 2023-12-05 | R.HUMPHREYS | 2023-12-05 | 2023-11-27 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2948 |  |  | 100 | 055532230262948 | 48 | 1578 | 28626.52 | 3668.37 | 1419.43 | 670.24 | 16361.59 | 0 | 76.8 | 6430.09 | 263
KY | KY - WEST | 2623 | 23026307400 |  |  |  | 6700224L | 2302214 | U461383 |  | 557 | EX | EMER-INSTALL 3' OF 2"PMMP | 2621P | OLD TOWNE | 122 OLD TOWNE | 239 | MID | 2024-01-09 | U128132 | U461383 | 2023-12-07 | 2024-03-01 | 2024-03-01 | 2023-12-05 | CDESPAIN | 2023-12-05 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP3074 |  |  | 100 | 055732230263074 |  | 3 | 1356.05 | 758.48 | 194.32 | 41.52 | 0 | 0 | 2.59 | 359.14 | 3
KY | KY - WEST | 2623 | 23026307500 |  |  |  | 6700224L | 2302214 | U461383 |  | 558 | EX | EMER-RETIRE 3' OF 2"PMP MAIN | 2621P | OLD TOWNE | 122 OLD TOWNE | 239 | MID | 2024-01-04 | U128132 | U461383 | 2023-12-07 | 2024-03-01 | 2024-03-01 | 2023-12-05 | CDESPAIN | 2023-12-05 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP3075 |  |  | 100 | 055832230263075 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23203500900 |  | 100406187 |  | 6688228I | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | HICKORY | 238 HICKORY DR | 073 | FRA | 2023-12-06 | U135005 | AOC SYST | 2023-07-24 | 2024-01-24 | 2024-12-31 |  | DMEDLEY | 2023-12-05 | 2023-11-17 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 19.6333 | 4 | 2939.54 | 1766.66 | 258.9 | 913.98 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23203501100 |  | 100280537 |  | 6688228I | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | HICKORY | 239 HICKORY DR | 073 | FRA | 2023-12-06 | U135005 | AOC SYST | 2023-07-24 | 2024-01-24 | 2024-12-31 |  | MCRAIG | 2023-12-05 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 18.3667 | 2 | 2749.39 | 1672.71 | 404.97 | 671.71 | 0 | 0 | 0 | 0
KY | KY - EAST | 2682 | 23221694100 |  | 100426754 |  | 7388156T |  |  |  | 566 | EX | ABANDON MAIN LINE TAP | 2633S | KY 582 | 2664 KY 582 | 119 | PIN | 2023-12-06 | U130172 | U135005 | 2023-10-17 | 2024-01-17 | 2024-01-17 |  | BRIAN PREECE | 2023-12-05 | 2023-12-05 |  | A | 00032 | 10800011 | 0326820 | 0326820 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26820057 | 5.9833 | 1 | 991.79 | 536.87 | 0 | 454.92 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23228691700 |  | 100318702 |  | 6716204B |  |  |  | 565 | EX | GRD 1 SERVICE LINE REPLACE | 2621P | BRIGADOON | 2909 BRIGADOON PY | 067 | LEX | 2023-12-06 | U135005 | U937740 | 2023-12-05 | 2023-12-05 | 2023-12-05 |  | LSTONE | 2023-12-05 | 2023-12-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.65 | 2 | 786.96 | 400.86 | 364.15 | 21.95 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 03537718300 |  | 500359227 | 27 | 7332132J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | SR899 | 6260 SR899 | 119 | PIP | 2023-12-06 | MBLANKE | BFMULLI | 2003-04-23 | 2023-12-06 | 2024-12-31 |  | MBLANKE | 2023-12-06 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.2833 | 2 | 4295.67 | 493.02 | 0 | 92.24 | 3710.41 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12992689100 |  | 100452930 |  | 6744208K | 2293467 |  |  | 566 | EX | UNMETERED-RETIRE W/22026234700 | 2600B | FOREST | FOREST AV | 049 | WIN | 2023-12-06 | U461383 | U125765 | 2012-10-11 | 2023-12-29 | 2023-12-31 |  | OFFICE EXECUTE | 2023-12-06 | 2021-02-02 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.5 | 1 | 379.81 | 254.38 | 0 | 125.43 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883106700 |  | 100247950 |  | 7364188B |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | CASSADY | CASSADY AV | 159 | INE | 2023-12-06 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2024-12-31 |  | JAHOWARD | 2023-12-06 | 2022-10-07 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 11.4833 | 3 | 798.66 | 757.17 | 0 | 41.49 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883290000 |  | 100424886 |  | 7372188N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | BEAUTY | BEAUTY RD | 159 | BEA | 2023-12-07 | U124015 | U120245 | 2021-01-30 | 2022-07-01 | 2024-12-31 |  | ORA SLONE | 2023-12-06 | 2022-11-17 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.18333 | 1 | 1583.57 | 0 | 0 | 0 | 1583.57 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883315400 |  | 100246309 |  | 7372188N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | BEAUTY | BEAUTY RD | 159 | BEA | 2023-12-07 | U124015 | U120245 | 2021-01-30 | 2022-07-01 | 2024-12-31 |  | ORA SLONE | 2023-12-06 | 2023-12-05 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 12.2167 | 2 | 2635.38 | 1142.5 | 0 | 142.95 | 1349.93 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026213100 |  | 100425532 |  | 6720208B | 2286441 | U134275 |  | 566 | EX | RETIRE 3"BSMP SERVICE LINE | 2600B | RICHMOND | 1900 RICHMOND RD | 067 | LEX | 2024-02-02 | U136251 | U134275 | 2022-07-21 | 2023-12-27 | 2023-12-31 | 2023-12-05 | SHAWN DENNIS | 2023-12-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP2131 | AMRSL |  | 100 | 056632220262131 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026213200 |  | 100425532 |  | 6720208B | 2286441 | U134275 |  | 565 | EX | INSTALL 30' OF 2-4" PMMP S/L | 2600B | RICHMOND | 1900 RICHMOND RD | 067 | LEX | 2024-02-02 | U136251 | U134275 | 2022-07-21 | 2023-12-26 | 2023-12-31 | 2023-12-05 | SHAWN DENNIS | 2023-12-06 | 2023-12-05 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP2132 | AMRSL |  | 100 | 056532220262132 | 32 | 4 | 33409.7 | 2814.71 | 5784.4 | 452.44 | 16255.12 | 0 | 196.9 | 7906.13
KY | KY - EAST | 2631 | 22129036700 |  | 100250825 |  | 7340268A |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HARRISON | 306 HARRISON ST | 089 | GRE | 2023-12-06 | RECUMP | U130722 | 2022-09-05 | 2022-12-30 |  |  | RECUMP | 2023-12-06 | 2023-10-09 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 10.8667 | 6 | 1232.11 | 905.35 | 0 | 326.76 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026266501 |  |  |  | 7332288M | 2395710 | U461383 |  | 575 | EX | ACQUIRE EASEMENT | 2600E | BIGGS | 624 BIGGS LN | 089 | S S | 2023-12-12 | U128132 | U461383 | 2023-04-20 | 2023-06-30 | 2023-06-30 | 2023-12-06 | CHRIS DAVIS | 2023-12-06 |  |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00575 | 3200575 |  |  | WP2665 |  |  | 100 | 057532230262665 |  | 1 | 62488.9 | 495.36 | 0 | 27550.98 | 33602 | 0 | 840.56 | 0
KY | KY - WEST | 2623 | 23203500000 |  | 100280553 |  | 6688228I | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | HICKORY | 148 HICKORY DR | 073 | FRA | 2023-12-07 | U135005 | AOC SYST | 2023-07-24 | 2024-01-24 | 2024-12-31 |  | MCRAIG | 2023-12-06 | 2023-11-16 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 17.8167 | 4 | 2341.49 | 1591.41 | 344.66 | 405.42 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23203500600 |  | 100280566 |  | 6688228I | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | HICKORY | 149 HICKORY DR | 073 | FRA | 2023-12-07 | U135005 | AOC SYST | 2023-07-24 | 2024-01-24 | 2024-12-31 |  | MCRAIG | 2023-12-06 | 2023-11-16 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 10.0667 | 3 | 1818.29 | 891.75 | 344.66 | 581.88 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23213260500 |  | 100339591 |  | 6724212A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | MARIETTA | 1854 MARIETTA DR 1FL | 067 | LEX | 2023-12-07 | U135005 | AOC SYST | 2023-09-06 | 2024-03-06 | 2024-12-31 |  | SSHIMFE | 2023-12-06 | 2023-10-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 12.1167 | 4 | 1364.04 | 825.74 | 492.87 | 45.43 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23213260600 |  | 100339544 |  | 6724212A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | DALTON | 1860 DALTON CT 1 | 067 | LEX | 2023-12-07 | U135005 | AOC SYST | 2023-09-06 | 2024-03-06 | 2024-12-31 |  | TROE | 2023-12-06 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 20.55 | 3 | 2192.88 | 1734.5 | 363.41 | 94.97 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23228721500 |  | 100409716 |  | 6720206K |  |  |  | 565 | EX | GRADE 1 SERVICE LINE | 2621P | RUSSELL CAVE | 1832 RUSSELL CAVE RD | 067 | LEX | 2023-12-07 | U135005 | U129939 | 2023-12-05 | 2023-12-05 | 2023-12-05 |  | SSHIMFE | 2023-12-06 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.4833 | 3 | 791.42 | 539.3 | 222.57 | 29.55 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23228837400 |  | 100312232 |  | 6716208I |  |  |  | 565 | EX | GRADE1 REPLACE SERVICE | 2621P | SOUTHVIEW | 2545 SOUTHVIEW DR | 067 | LEX | 2023-12-07 | U135005 | U129939 | 2023-12-06 | 2023-12-06 | 2023-12-06 |  | RJCRAWF | 2023-12-06 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.65 | 2 | 1620.06 | 1079.73 | 481.2 | 59.13 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23228877300 |  | 100464621 |  | 6716212H |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SHORT | 541 W SHORT ST 20 | 067 | LEX | 2023-12-07 | U135005 | U129939 | 2023-12-06 | 2023-12-06 | 2023-12-26 |  | JOCHOA | 2023-12-06 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 10.6333 | 3 | 2244.07 | 1983.79 | 151.69 | 108.59 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 04569596900 |  | 500035374 | 22 | 7356156I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PIKE FLOYD | 219 PIKE FLOYD HOLLOW | 071 | BET | 2023-12-07 | MBLANKE | DHANSFO | 2004-03-22 | 2023-12-06 | 2024-12-31 |  | MBLANKE | 2023-12-07 | 2023-12-06 |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 16.2167 | 4 | 4091.84 | 1416.07 | 0 | 173.2 | 2502.57 | 0 | 0 | 0
KY | KY - EAST | 2633 | 11920177000 |  | 100246401 |  | 7372188N |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | BEAUTY | BEAUTY RD | 159 | BEA | 2023-12-07 | U130172 | U124449 | 2011-08-15 | 2022-07-01 | 2024-12-31 |  | JAHOWARD | 2023-12-07 | 2022-10-07 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.75 | 4 | 203.62 | 173.42 | 0 | 30.2 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18026793901 |  |  |  | 7348264E | 1855482 | U134275 |  | 557 | EX | INSTALL 4,123' - 2" PMMP | 2600B | TEAKWOOD | TEAKWOOD DR | 089 | RAC | 2024-01-25 | U136251 | U134275 | 2023-06-27 | 2023-08-01 | 2023-12-31 | 2023-10-10 | CJH C PACK/MBLANKE | 2023-12-07 | 2023-11-27 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP7939 | AMRCB |  | 100 | 055732180267939 | 466.2 | 318780 | 603491.8 | 34942.38 | 15384.27 | 5713.45 | 415358.83 | 0 | 2786.11 | 129306.76 | 4140
KY | KY - EAST | 2631 | 18026794000 |  |  |  | 7348264E | 1855482 | U134275 |  | 558 | EX | RETIRE 4748'-2"/3"/4"/6"P-BSLP | 2600E | TEAKWOOD | TEAKWOOD DR | 089 | RAC | 2024-01-17 | U136251 | U127466 | 2018-09-12 | 2024-12-31 | 2023-12-31 | 2023-12-04 | CJH J HIERONIMUS/DSKAGGS | 2023-12-07 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP7940 | AMRCB |  | 100 | 055832180267940 |  | 0 | 110 | 0 | 0 | 0 | 110 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883324400 |  | 100247769 |  | 7364188A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | MAIN | MAIN ST | 159 | INE | 2023-12-07 | U124015 | U120245 | 2021-01-30 | 2022-07-01 | 2024-12-31 |  | ORA SLONE | 2023-12-07 | 2023-11-29 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 14.5833 | 4 | 2265.05 | 1241.28 | 0 | 141.12 | 882.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23214554000 |  | 100329816 |  | 6720208D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | WILL FANT | 2100 WILL FANT DR 1FR | 067 | LEX | 2023-12-08 | U135005 | AOC SYST | 2023-09-13 | 2024-03-13 | 2024-12-31 |  | LSTONE | 2023-12-07 | 2023-11-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 15.05 | 4 | 1714.83 | 1237.77 | 409.24 | 67.82 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23224986400 |  | 100331683 |  | 6720212N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333585 | 2621P | RICHMOND | 11 RICHMOND AV | 067 | LEX | 2023-12-08 | U135005 | U135005 | 2023-11-08 | 2023-11-30 |  |  | HMCKUNE | 2023-12-07 | 2023-12-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.1667 | 5 | 1949.37 | 1636.11 | 223.67 | 89.59 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23227906400 |  | 100406239 |  | 6684228F |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | BROADWAY | 402 W BROADWAY ST | 073 | FRA | 2024-01-22 | U461383 | U135005 | 2023-11-30 | 2023-12-14 | 2023-12-30 |  | EFGOINS | 2023-12-07 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 16 | 2 | 2143.48 | 1266.17 | 73.39 | 96.42 | 707.5 | 0 | 0 | 0
KY | KY - EAST | 2633 | 03550403300 |  | 500103261 | 27 | X1810-57 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | SR292 | SR292 | 195 | S W | 2023-12-08 | U130172 | CESTEP | 2003-09-04 | 2022-07-01 | 2024-12-31 |  | JOHN HOWARD | 2023-12-08 | 2022-11-17 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.18333 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883113000 |  | 100246198 |  | 7372188L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | BARRETT | BARRETT ST | 159 | WAR | 2023-12-08 | U130172 | U120245 | 2021-01-30 | 2022-07-01 | 2024-12-31 |  | JOHN HOWARD | 2023-12-08 | 2022-11-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 8.2667 | 2 | 757.26 | 717.93 | 0 | 39.33 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129033000 |  | 100250094 |  | 7360252M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SPRINGHAVEN | 3306 SPRINGHAVEN ST | 019 | CAT | 2023-12-21 | U135005 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JROGER1 | 2023-12-08 | 2023-12-08 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 14.15 | 2 | 1496.47 | 986.05 | 20.27 | 490.15 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026307700 |  |  |  | 6712204B | 2302251 | U122858 |  | 557 | EX | EMER - INSTALL 5'-2" PMMP | 2621P | WITTHUHN | 920 WITTHUHN WY | 067 | LEX | 2024-04-30 | U136251 | U122858 | 2023-12-08 | 2024-08-29 |  | 2023-12-07 | HMCKUNE | 2023-12-08 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3077 |  |  | 100 | 055732230263077 |  | 5 | 3376.54 | 2171.23 | 185.88 | 118.84 | 0 | 0 | 7.92 | 892.67 | 5
KY | KY - WEST | 2621 | 23026307800 |  |  |  | 6712204B | 2302251 | U122858 |  | 558 | CO | EMER - RETIRE 5'-2" PMP | 2621P | WITTHUHN | 920 WITTHUHN WY | 067 | LEX | 2024-04-26 |  | U122858 | 2023-12-08 | 2024-08-30 |  | 2023-12-07 | HMCKUNE | 2023-12-08 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP3078 |  |  | 100 | 055832230263078 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23203501500 |  | 100280548 |  | 6688228I | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | HICKORY | 158 HICKORY DR | 073 | FRA | 2023-12-11 | U130722 | AOC SYST | 2023-07-24 | 2024-01-24 | 2024-12-31 |  | MCRAIG | 2023-12-08 | 2023-11-09 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 22.2167 | 6 | 3115.74 | 2024.63 | 0 | 1091.11 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23224038700 |  | 100345530 |  | 6696212L |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | LOCUST | 161 N LOCUST ST | 239 | VER | 2023-12-08 | U128410 | U133234 | 2023-11-01 | 2023-11-14 | 2023-11-30 |  | CDESPAIN | 2023-12-08 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 32 | 4 | 3476.54 | 2509.74 | 195.33 | 137.47 | 634 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23229038200 |  | 100467186 |  | 7356256B |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | CARTER | 2212 CARTER AV | 019 | ASH | 2023-12-08 | BMEEK | U129939 | 2023-12-07 | 2023-12-07 |  |  | BMEEK | 2023-12-08 | 2023-12-07 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.1 | 2 | 365.29 | 254.75 | 0 | 110.54 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23229189700 |  | 100308408 |  | 6716212N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | ADDISON | 517 ADDISON AV | 067 | LEX | 2023-12-11 | U135005 | U139701 | 2023-12-08 | 2023-11-09 |  |  | KKINDER | 2023-12-08 | 2023-12-04 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 14.2167 | 4 | 2171.55 | 1918.73 | 147.75 | 105.07 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 03530162200 |  | 100264631 | 13 | X1809-54 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | ROGERS PARK | ROGERS PARK RD | 195 | S W | 2023-12-11 | U130172 | CESTEP | 2003-02-06 | 2022-07-01 | 2024-12-31 |  | JOHN HOWARD | 2023-12-11 | 2022-11-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.45 | 2 | 17.73 | 16.81 | 0 | 0.92 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 13112727800 |  | 100259459 |  | 7344148J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | TURNER | TURNER ST | 071 | DRI | 2023-12-11 | U130172 | U908786 | 2013-01-16 | 2022-07-01 | 2024-12-31 |  | JOHN HOWARD | 2023-12-11 | 2023-12-06 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 12.0667 | 2 | 1138.88 | 1079.74 | 0 | 59.14 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23154552700 |  | 100410737 |  | 7344148I |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | REED | REED ST | 071 | DRI | 2023-12-11 | U130172 | U125763 | 2023-01-10 | 2023-12-29 | 2024-12-31 |  | JOHN HOWARD | 2023-12-11 | 2023-11-08 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 4 | 1 | 1213.39 | 313.28 | 0 | 17.46 | 882.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23218175600 |  | 100334725 |  | 6724208A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | WOODWARD | 701 WOODWARD LN | 067 | LEX | 2023-12-12 | U135005 | AOC SYST | 2023-09-29 | 2024-03-28 | 2024-12-31 |  | KKINDER | 2023-12-11 | 2023-11-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 23.7167 | 7 | 2817.87 | 2021.36 | 334.91 | 461.6 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23220612400 |  | 100264595 |  | 7380168H |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SR 292 | SR 292 | 195 | S W | 2023-12-11 | U130172 | U124420 | 2023-10-11 | 2011-05-06 | 2011-05-08 |  | JOHN HOWARD | 2023-12-11 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - WEST | 2621 | 23224819700 |  | 100301103 |  | 6716212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309143 | 2621P | SAVOY | 248 SAVOY RD | 067 | LEX | 2023-12-12 | U135005 | U135005 | 2023-11-07 | 2024-01-31 |  |  | MCRAIG | 2023-12-11 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.1 | 2 | 2331.58 | 1226.53 | 532.39 | 572.66 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23227892000 |  | 100253649 |  | 7364188H |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | BLACKLOG | 2267 BLACKLOG RD | 159 | INE | 2023-12-12 | U135005 | U137009 | 2023-11-30 | 2023-12-15 | 2023-12-29 |  | JCKIRK | 2023-12-11 | 2023-12-11 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 34.95 | 3 | 3360.63 | 3186.13 | 0 | 174.5 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23229359900 |  | 100275232 |  | 6684228J | 2074544 |  |  | 566 | EX | RETIRE W/20-0269746-00 ANN ST | 2600B | WASHINGTON | 300 WASHINGTON ST RR | 073 | FRA | 2023-12-11 | U461383 | U461383 | 2023-12-11 | 2023-12-29 | 2023-12-31 |  | LARRY BROWN | 2023-12-11 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - EAST | 2633 | 23229366900 |  | 500345794 |  | 7372188N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SR40 | SR40 | 159 | BEA | 2023-12-11 | MDULANE | MDULANE | 2023-12-11 | 2023-12-29 | 2023-12-29 |  | OFFICE/MDULANE IC | 2023-12-11 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1
KY | KY - WEST | 2621 | 23231071100 |  | 100339503 |  | 6724212A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HUNTSVILLE | 1458 HUNTSVILLE DR A | 067 | LEX | 2023-12-26 | U135005 | U135005 | 2023-12-26 | 2024-02-29 | 2025-08-30 |  | LSTANFI | 2023-12-11 | 2023-12-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 20.2833 | 3 | 2651.46 | 1633.83 | 677.28 | 340.35 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 11897007600 |  | 100416053 |  | 7348176T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | PAINTSVILLE DP | PAINTSVILLE DP | 071 | VAN | 2023-12-12 | MBLANKE | U906631 | 2011-03-22 | 2022-07-01 | 2024-12-31 |  | MBLANKE | 2023-12-12 | 2022-11-17 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 11.9333 | 3 | 2766.64 | 1070.07 | 0 | 105.21 | 1591.36 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883248300 |  | 100259472 |  | 7344148J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | TURNER | TURNER ST | 071 | DRI | 2023-12-12 | MBLANKE | U120245 | 2021-01-30 | 2022-07-01 | 2024-12-31 |  | MBLANKE | 2023-12-12 | 2022-10-06 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 11.6333 | 3 | 3475.13 | 1075.13 | 0 | 201.17 | 2198.83 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883295600 |  | 100264709 |  | 7384168F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | TURKEY CREEK | TURKEY CREEK RD | 195 | S W | 2023-12-13 | U124015 | U120245 | 2021-01-30 | 2022-07-01 | 2024-12-31 |  | ORA SLONE | 2023-12-12 | 2022-11-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 12.3667 | 3 | 5096.72 | 1012.42 | 0 | 190.29 | 3894.01 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23190289800 |  | 100264770 |  | 7384168O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D243507 | 2621P | NEW CAMP | 464 NEW CAMP RD | 195 | S W | 2023-12-12 | JCKIRK | U125208 | 2023-05-23 | 2023-12-11 | 2025-05-31 |  | JCKIRK | 2023-12-12 |  |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 16.4167 | 2 | 2021.54 | 1499.83 | 439.55 | 82.16 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23225981500 |  | 100335427 |  | 6716216F |  |  |  | 566 | EX | ABANDON SL - DEMO/CITYRQD | 2621P | SANDERSVILLE | 2314 SANDERSVILLE RD | 067 | LEX | 2023-12-13 | U135005 | U135005 | 2023-11-15 | 2023-12-06 | 2023-12-15 |  | LSTONE | 2023-12-12 | 2023-12-08 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.5667 | 4 | 1614.6 | 1318.32 | 2.11 | 72.17 | 222 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23227791300 |  | 100287587 |  | 6720212G |  |  |  | 566 | EX | ABANDON SL - CONVERT TO ELECTR | 2621P | MARCELLUS | 1010 MARCELLUS DR | 067 | LEX | 2023-12-13 | U930915 | U135005 | 2023-11-29 | 2023-12-20 | 2023-12-29 |  | JOCHOA | 2023-12-12 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.15 | 3 | 1198.34 | 1136.14 | 0 | 62.2 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23229337400 |  | 100417770 |  | 6688228L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D308985 | 2621P | TIMBERLAWN | 3 TIMBERLAWN LN | 073 | FRA | 2023-12-13 | U135005 | U135005 | 2023-12-11 | 2023-12-14 | 2024-01-01 |  | EFGOINS | 2023-12-12 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26230021 | 19.0333 | 3 | 1790.43 | 1386.57 | 327.91 | 75.95 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23229438400 |  | 100348717 |  | 6748208M |  |  |  | 566 | EX | ABANDON SL | 2621P | MACK ALLEY | 100 MACK ALLEY | 049 | WIN | 2023-12-12 | DENNING | U125765 | 2023-12-12 | 2023-12-12 |  |  | DENNING | 2023-12-12 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.45 | 3 | 424.7 | 402.65 | 0 | 22.05 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 11899693600 |  | 500364573 |  | 7384168G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | SR292 | SR292 | 195 | S W | 2023-12-13 | U124015 | U123933 | 2011-04-04 | 2022-07-01 | 2024-12-31 |  | ORA SLONE | 2023-12-13 | 2023-12-08 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 31.0667 | 5 | 6740.29 | 2900.25 | 0 | 496.37 | 3343.67 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883194500 |  | 100247987 |  | 7364188A |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | MIDDLE FORK | MIDDLE FORK RD | 159 | INE | 2023-12-13 | MBLANKE | U120245 | 2021-01-30 | 2022-07-01 | 2024-12-31 |  | MBLANKE | 2023-12-13 | 2022-11-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 9.6 | 5 | 1817.16 | 829.42 | 0 | 105.09 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883309500 |  | 500336010 |  | 7356152E |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | 2ND | 2ND AV | 071 | HAR | 2023-12-13 | MBLANKE | U120245 | 2021-01-30 | 2022-07-01 | 2024-12-31 |  | MBLANKE | 2023-12-13 | 2022-10-06 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.1333 | 2 | 2835.92 | 280.8 | 0 | 52.55 | 2502.57 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22979021700 |  | 100255250 |  | 7352184T |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | DANIELS CREEK | 415 N DANIELS CREEK | 115 | VAN | 2023-12-13 | U130172 | U128070 | 2022-02-17 | 2024-12-31 | 2024-12-31 |  | JOHN KIRK | 2023-12-13 | 2022-11-29 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 20.35 | 8 | 2685.04 | 1590.99 | 0 | 148.41 | 945.64 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23193986500 |  | 100409744 |  | 6696212K | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | MAPLE | 113 MAPLE AV | 239 | VER | 2023-12-14 | U135005 | AOC SYST | 2023-06-09 | 2023-12-08 | 2024-12-31 |  | EFGOINS | 2023-12-13 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 23.5667 | 4 | 2148.09 | 1836.83 | 210.69 | 100.57 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23225569100 |  | 100312846 |  | 6716208E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D341468 | 2621P | BARKLEY | 434 BARKLEY DR | 067 | LEX | 2023-12-14 | U135005 | U135005 | 2023-11-13 | 2024-05-08 | 2025-11-30 |  | KKINDER | 2023-12-13 | 2023-12-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 28.3833 | 3 | 3219.82 | 2557.15 | 522.6 | 140.07 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23226043000 |  | 100291845 |  | 6720216G |  |  |  | 565 | EX | REPLACE SERVICE LINE - D305379 | 2621P | EDEN | 760 EDEN CT | 067 | LEX | 2023-12-14 | U135005 | U135005 | 2023-11-15 | 2023-12-29 |  |  | TROE | 2023-12-13 | 2023-12-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.6167 | 4 | 1924.87 | 1480.24 | 363.62 | 81.01 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23226044700 |  | 100337173 |  | 6720212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D305544 | 2621P | 6TH | 144 E 6TH ST | 067 | LEX | 2023-12-14 | U135005 | U135005 | 2023-11-15 | 2024-06-28 |  |  | LSTANFI | 2023-12-13 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.4167 | 4 | 3024.23 | 1740.11 | 546.06 | 454.56 | 283.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23229611800 |  | 100334783 |  | 6724208G |  |  |  | 565 | EX | GRADE 1 REPLACE SL | 2621P | CAMPBELL | 819 CAMPBELL LN | 067 | LEX | 2023-12-14 | U135005 | U125765 | 2023-12-13 | 2023-12-13 | 2023-12-13 |  | TROE | 2023-12-13 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.5667 | 2 | 847.47 | 736.83 | 70.3 | 40.34 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23229643200 |  | 100297459 |  | 6716212H |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | JEFFERSON | 340 JEFFERSON ST | 067 | LEX | 2023-12-14 | U135005 | U125765 | 2023-12-13 | 2023-11-15 |  |  | MCRAIG | 2023-12-13 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 0.8 | 1 | 1978.05 | 1362.45 | 56.87 | 558.73 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883221100 |  | 100268679 |  | 7352156L |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | OFFICIAL | OFFICIAL RD | 071 | BET | 2023-12-14 | MBLANKE | U120245 | 2021-01-30 | 2022-07-01 | 2024-12-31 |  | MBLANKE | 2023-12-14 | 2022-10-06 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 9.4833 | 2 | 1919.35 | 873.28 | 0 | 163.42 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129037700 |  | 100258408 |  | 7336272G |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | US ROUTE 23 | US ROUTE 23 | 089 | RAC | 2023-12-14 | RECUMP | U130722 | 2022-09-05 | 2022-12-30 |  |  | RECUMP | 2023-12-14 | 2023-12-13 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.0667 | 2 | 473.03 | 327.48 | 0 | 145.55 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129039900 |  | 100253316 |  | 7356228T |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | US 23 | 24557 US 23 | 127 | BUC | 2024-01-22 | U461383 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JCYRUS | 2023-12-14 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.8 | 2 | 436.13 | 413.46 | 0 | 22.67 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026261200 |  |  |  | 7348248F | 2294088 | U461383 |  | 909 | EX | INSTALL ULTRASONIC METER | 2631M | US 60 | US 60 | 019 | CAN | 2024-02-15 | U123258 | U461383 | 2023-02-16 | 2024-12-30 | 2024-12-31 | 2023-12-14 | DANNY ASH | 2023-12-14 | 2024-01-29 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP2612 |  |  | 100 | 090932230262612 | 5.8167 | 0 | 36758.54 | 1396.81 | 0 | -4024.64 | 39241.8 | 0 | 144.57 | 0
KY | KY - WEST | 2621 | 23026294500 |  |  |  | 672208F | 2300176 | U461383 |  | 560 | EX | RETIRE 338' OF 4"BSLP MAIN | 2621P | COCHRAN | COCHRAN DR | 067 | LEX | 2024-01-09 | U136251 | U461383 | 2023-09-15 | 2023-12-29 | 2023-12-31 | 2023-12-14 | ALEX WILLIAMSON | 2023-12-14 | 2023-12-13 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00560 | 3200560 |  |  | WP2945 | AMRCB |  | 100 | 056032230262945 | 59.6333 | 0 | 6772.76 | 4803.97 | 175.81 | 1792.98 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23222179800 |  | 100305366 |  | 6712212K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311190 | 2621P | PARKERS MILL | 1626 PARKERS MILL RD | 067 | LEX | 2023-12-18 | U135005 | U135005 | 2023-10-19 | 2024-04-19 | 2025-10-31 |  | KKINDER | 2023-12-14 | 2023-12-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.5833 | 3 | 2819.47 | 1528.31 | 559.96 | 83.7 | 647.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23224442800 |  | 100275745 |  | 6684228C |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | WILKINSON | 974 WILKINSON BV | 073 | FRA | 2023-12-18 | U135005 | U133234 | 2023-11-03 | 2023-11-17 | 2023-12-03 |  | EFGOINS | 2023-12-14 | 2023-12-01 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 23.8333 | 5 | 2146.21 | 1771.84 | 277.32 | 97.05 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23224984300 |  | 100288847 |  | 6720212D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D311346 | 2621P | SAINT ANTHONY | 543 SAINT ANTHONY DR | 067 | LEX | 2023-12-15 | U135005 | U135005 | 2023-11-08 | 2023-11-08 |  |  | S.LURTY | 2023-12-14 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1
KY | KY - WEST | 2621 | 23226441200 |  | 100291182 |  | 6724216I |  |  |  | 566 | EX | ABANDON SL - DEMO/CITYRQD | 2621P | PARIS | 2450 PARIS PK | 067 | LEX | 2023-12-18 | U135005 | U135005 | 2023-11-17 | 2023-12-01 | 2023-12-17 |  | ABLAKE | 2023-12-14 | 2023-12-06 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 14.2167 | 4 | 1609.85 | 1248.31 | 293.21 | 68.33 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23227572600 |  | 100444260 |  | 6720216L |  |  |  | 566 | EX | ABANDON SL - DEMO | 2621P | PARIS | 2400 PARIS PK | 067 | LEX | 2023-12-18 | U135005 | U135005 | 2023-11-28 | 2023-11-28 | 2023-12-28 |  | JOCHOA | 2023-12-14 | 2023-12-04 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 25.9 | 6 | 5560.68 | 2030.69 | 18.15 | 111.22 | 3400.62 | 0 | 0 | 0
KY | KY - EAST | 2633 | 21883181900 |  | 100264596 |  | 7384168G |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | SR292 | SR292 | 195 | S W | 2023-12-15 | MBLANKE | U120245 | 2021-01-30 | 2022-07-01 | 2024-12-31 |  | MBLANKE | 2023-12-15 | 2022-11-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 10.5167 | 3 | 3749.81 | 960.93 | 0 | 52.62 | 2736.26 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129121600 |  | 500122392 |  | 7360216E |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ROUTE 5 | ROUTE 5 | 127 | LOU | 2023-12-18 | U135005 | U125208 | 2022-09-06 | 2022-12-30 |  |  | JCYRUS | 2023-12-15 | 2023-12-08 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 16.4333 | 4 | 1497.74 | 1419.98 | 0 | 77.76 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23209322200 |  | 500227853 |  | 6688228M | 2399566 | U461383 |  | 565 | EX | INSTALL 60' OF 2"CSHP S/L | 2600B | SOWER | 150 SOWER BV BACK | 073 | FRA | 2023-12-15 | U126285 | U461383 | 2023-08-18 | 2023-12-12 | 2023-12-15 |  | DDAVIS | 2023-12-15 | 2023-11-30 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 203.7 | 26 | 72363.57 | 17685.48 | 6055.1 | 2645.66 | 45977.33 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23228331500 |  | 100341705 |  | 7240216O |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | MONTGOMERY | 213 MONTGOMERY AV | 173 | MT | 2023-12-18 | U135005 | U133234 | 2023-12-01 | 2023-12-14 | 2023-12-30 |  | DENNING | 2023-12-15 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10.75 | 3 | 1054.6 | 980.66 | 20.27 | 53.67 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23229759400 |  | 100317427 |  | 6716204J |  |  |  | 565 | EX | REPLACE SERVICE LINE - D341474 | 2621P | KENLOCK | 245 KENLOCK DR | 067 | LEX | 2023-12-18 | U135005 | U135005 | 2023-12-14 | 2023-12-14 | 2023-12-14 |  | LSTANFI | 2023-12-15 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.4833 | 3 | 1993.06 | 1396.95 | 352.77 | 243.34 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 04590994000 |  | 100268783 | 52 | 0 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | 2ND | 2ND AV | 071 | BET | 2023-12-18 | MBLANKE | DHANSFO | 2004-10-29 | 2022-07-01 | 2024-12-31 |  | MBLANKE | 2023-12-18 | 2022-10-06 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 7.05 | 2 | 2864.52 | 646.05 | 0 | 120.88 | 2097.59 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026307900 |  |  |  | 6708204G | 2302264 | U461383 |  | 557 | EX | EMER-INSTALL 10'-4"PMMP/VALVE | 2621P | FOREST | 103 FOREST TL | 113 | NIC | 2024-01-16 | U136251 | U461383 | 2023-12-11 | 2024-08-29 | 2024-08-31 | 2023-12-05 | KKINDER | 2023-12-18 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3079 |  |  | 100 | 055732230263079 | 0.95 | 10 | 8046.73 | 5072.51 | 549.68 | 278.33 | 0 | 0 | 19.07 | 2127.14 | 10
KY | KY - WEST | 2621 | 23026308000 |  |  |  | 6708204H | 2302264 | U461383 |  | 558 | EX | EMER-RETIRE 10'-4"PMP/C8-150 | 2621P | FOREST | 103 FOREST TL | 113 | NIC | 2024-01-16 | U136251 | U461383 | 2023-12-11 | 2024-08-30 | 2024-08-31 | 2023-12-05 | KKINDER | 2023-12-18 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP3080 |  |  | 100 | 055832230263080 | 1.4333 | 0 | 147.12 | 139.48 | 0 | 7.64 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23192215900 |  | 100323835 |  | 6716208P | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | BURKSHIRE | 708 BURKSHIRE DR | 067 | LEX | 2023-12-19 | U135005 | AOC SYST | 2023-06-01 | 2023-12-01 | 2024-12-31 |  | RJCRAWF | 2023-12-18 | 2023-10-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 18.15 | 4 | 1844.76 | 1470.43 | 293.24 | 81.09 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23200411700 |  | 100467350 |  | 7356220N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | ROUTE 3 | ROUTE 3 TL 6 | 127 | LOU | 2023-12-18 | JCYRUS | MDULANE | 2023-07-12 | 2024-07-09 | 2024-07-09 |  | JCYRUS | 2023-12-18 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 15.8 | 2 | 1441.52 | 1366.64 | 0 | 74.88 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23229915000 |  | 100264583 |  | 7384168G | 1960956 |  |  | 566 | EX | ABANDN SL/ | 2600B | SR 292 | 3151 SR 292 | 195 | S W | 2023-12-18 | U123965 | U125763 | 2023-12-15 | 2023-12-29 |  |  | MBLANKE | 2023-12-18 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.1333 | 1 | 347.85 | 293.02 | 0 | 54.83 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23229951500 |  | 100329689 |  | 6720208D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D309371 | 2621P | SAINT TERESA | 2116 SAINT TERESA DR | 067 | LEX | 2023-12-19 | U135005 | U135005 | 2023-12-15 | 2023-12-15 | 2023-12-15 |  | LSTANFI | 2023-12-18 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24 | 3 | 2264.93 | 1798.86 | 116.7 | 349.37 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026166900 |  |  |  | 6720208B | 2286441 | U134275 |  | 557 | EX | INSTALL 2010' - 8" & 6" PMMP | 2600B | RICHMOND | 1814 RICHMOND RD | 067 | LEX | 2024-01-03 | U128132 | U134275 | 2022-02-11 | 2024-04-23 | 2025-01-08 | 2023-11-08 | SHAWN DENNIS | 2023-12-19 | 2023-09-11 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP1669 | AMRCB |  | 100 | 055732220261669 | 523.9 | 133700 | 525084.39 | 38014.77 | 39529.23 | 11143.21 | 301364.3 | 0 | 3902.89 | 131129.99 | 1910
KY | KY - WEST | 2621 | 22026167000 |  |  |  | 6720208B | 2286441 | U134275 |  | 558 | EX | RETIRE 2260' OF 4-8" BSLP | 2600B | RICHMOND | RICHMOND RD | 067 | LEX | 2024-01-30 | U128132 | U134275 | 2022-02-11 | 2024-05-31 | 2025-01-08 | 2023-12-12 | SHAWN DENNIS | 2023-12-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP1670 | AMRCB |  | 100 | 055832220261670 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026213000 |  |  |  | 6720208B | 2286441 | U134275 |  | 558 | EX | RETIRE 2015'-8/4/2" BSMP/CSMP | 2600B | RICHMOND | 1900 RICHMOND RD | 067 | LEX | 2024-01-02 | U128132 | U134275 | 2022-07-21 | 2023-12-29 | 2023-12-31 | 2023-11-12 | SHAWN DENNIS | 2023-12-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP2130 | AMRCB |  | 100 | 055832220262130 |  | 0 | 220 | 0 | 0 | 0 | 220 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23180745500 |  | 100278261 |  | 6688228B | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | SHAWNEE | 1038 SHAWNEE TL | 073 | FRA | 2023-12-20 | U135005 | AOC SYST | 2023-04-12 | 2023-10-12 | 2024-12-31 |  | DCOLLIN | 2023-12-19 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 34.6 | 4 | 4072.15 | 3059.01 | 303.16 | 709.98 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23230348100 |  | 100329759 |  | 6720208D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SAINT ANN | 268 SAINT ANN DR | 067 | LEX | 2023-12-20 | U135005 | U125765 | 2023-12-19 | 2024-03-15 | 2025-09-30 |  | RJCRAWF | 2023-12-19 | 2023-12-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.95 | 3 | 1038.9 | 602.9 | 402.98 | 33.02 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129066400 |  | 100242551 |  | 7356256O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | HICKORY | 4615 HICKORY ST | 019 | ASH | 2023-12-21 | U135005 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JCYRUS | 2023-12-20 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 9.6333 | 2 | 927.42 | 835.57 | 46.1 | 45.75 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23185462400 |  | 100279515 |  | 6688228O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | LAGO | 1304 LAGO DR | 073 | FRA | 2023-12-21 | U135005 | AOC SYST | 2023-05-02 | 2023-11-02 | 2024-12-31 |  | DCOLLIN | 2023-12-20 | 2023-12-19 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26230031 | 32.5833 | 8 | 3765.6 | 2694.85 | 336.78 | 733.97 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23225221600 |  | 100331664 |  | 6720212N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333591 | 2621P | RICHMOND | 45 RICHMOND AV | 067 | LEX | 2023-12-21 | U135005 | U135005 | 2023-11-09 | 2023-11-30 |  |  | ABLAKE | 2023-12-20 | 2023-12-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 39.2667 | 8 | 3876.67 | 3331.74 | 244.91 | 300.02 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23225589200 |  | 100274804 |  | 6684228J |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | 2ND | 223 W 2ND ST | 073 | FRA | 2023-12-21 | U135005 | U133234 | 2023-11-13 | 2023-11-27 | 2023-12-13 |  | EFGOINS | 2023-12-20 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 12.3 | 2 | 898.95 | 822.95 | 0 | 76 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23228878400 |  | 100289059 |  | 6720212D |  |  |  | 565 | EX | SERVICE LINE/METER UPGRADE | 2621P | MOSS | 1936 MOSS CT | 067 | LEX | 2023-12-20 | U930915 | U135005 | 2023-12-06 | 2024-01-05 | 2024-01-05 |  | LSTANFI | 2023-12-20 | 2023-12-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 23.4833 | 4 | 2698.46 | 1753.6 | 614.62 | 330.24 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23230401600 |  | 100313077 |  | 6716208A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CLAYS MILL | 1894 CLAYS MILL RD | 067 | LEX | 2023-12-21 | U135005 | U125765 | 2023-12-19 | 2023-12-13 | 2023-12-31 |  | RSTRONG | 2023-12-20 | 2023-12-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 0.96667 | 3 | 1446.53 | 1243.25 | 41.14 | 162.14 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 04578217800 |  | 100264647 | 62 | X1809-54 |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | ROGERS PARK | ROGERS PARK RD | 195 | S W | 2023-12-21 | U124015 | CESTEP | 2004-06-17 | 2022-07-01 | 2024-12-31 |  | ORA SLONE | 2023-12-21 | 2023-12-06 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 5.15 | 2 | 1979.88 | 479.11 | 0 | 26.22 | 1474.55 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11898404900 |  | 100243549 |  | V-1718-16 |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | MAIN CROSS | 300< N MAIN CROSS ST | 127 | LOU | 2023-12-26 | U135005 | U906631 | 2011-03-29 | 2020-12-31 |  |  | JKEENER | 2023-12-21 | 2023-12-19 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 19.55 | 3 | 3766.11 | 1685.68 | 0 | 270.43 | 1810 | 0 | 0 | 0
KY | KY - EAST | 2633 | 11899916900 |  | 500541727 |  | 7324132F | 2290467 |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | SR550 | SR550 | 119 | HIN | 2023-12-21 | MBLANKE | U124449 | 2011-04-05 | 2022-07-01 | 2024-12-31 |  | MBLANKE | 2023-12-21 | 2022-10-06 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 4.2333 | 2 | 1334.15 | 380.34 | 0 | 71.16 | 882.65 | 0 | 0 | 0
KY | KY - EAST | 2633 | 13147746300 |  | 100264518 |  | 7384168F |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | TURKEY CREEK | 638 TURKEY CREEK RD | 195 | S W | 2023-12-21 | U124015 | U126643 | 2013-07-10 | 2022-07-01 | 2024-12-31 |  | ORA SLONE | 2023-12-21 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 |  | 1 | 3437.13 | 0 | 0 | 0 | 3437.13 | 0 | 0 | 0
KY | KY - WEST | 2623 | 20026974700 |  |  |  | 6684228K | 2074544 | U126783 |  | 558 | EX | RETIRE 6,900'-BSLP,CSLP,PLP | 2600E | ANN | ANN | 073 | FRA | 2024-01-25 | U136251 | U130604 | 2020-09-18 |  | 2049-12-31 | 2023-12-18 | WGRAVES | 2023-12-21 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP9747 | AMRCB |  | 100 | 055832200269747 |  | 0 | 220 | 0 | 0 | 0 | 220 | 0 | 0 | 0
KY | KY - EAST | 2633 | 22979023300 |  | 100259470 |  | 7344148J |  |  |  | 566 | EX | ABANDON SL - I/I/LGCY STEP 3 | 2621P | TURNER | TURNER ST | 071 | DRI | 2023-12-21 | MBLANKE | U128070 | 2022-02-17 | 2024-12-31 | 2024-12-31 |  | MBLANKE | 2023-12-21 | 2023-12-19 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 14.7 | 3 | 2521.31 | 1380.35 | 0 | 258.31 | 882.65 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026296400 |  |  |  | 6688228A | 2300379 | U461383 |  | 557 | EX | INSTALL 110' OF 2"PMMP MAIN | 2600B | SCHENKEL | 565 SCHENKEL | 073 | FRA | 2024-01-08 | U128132 | U461383 | 2023-09-25 | 2023-12-18 | 2024-01-10 | 2023-12-14 | JOSH PASLEY/STANLEY PIPELINE | 2023-12-21 | 2023-11-14 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP2964 |  |  | 100 | 055732230262964 | 115.8667 | 2460 | 58459.83 | 10068.37 | 2058.17 | 7635.7 | 23102.6 | 0 | 176.82 | 15418.17 | 164
KY | KY - WEST | 2623 | 23026296500 |  |  |  | 6688228A | 2300379 | U461383 |  | 558 | EX | RETIRE 88' OF 2"CSMP MAIN | 2600B | SCHENKEL | 565 SCHENKEL | 073 | FRA | 2024-01-08 | U128132 | U461383 | 2023-09-25 | 2024-01-10 | 2024-01-10 | 2023-12-14 | JOSH PASLEY/STANLEY PIPELINE | 2023-12-21 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP2965 |  |  | 100 | 055832230262965 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23224986900 |  | 100331136 |  | 6720212N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D333586 | 2621P | LINCOLN | 116 LINCOLN AV | 067 | LEX | 2023-12-26 | U135005 | U135005 | 2023-11-08 | 2023-11-30 |  |  | HMCKUNE | 2023-12-21 | 2023-12-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.2667 | 4 | 2099.84 | 1798.46 | 202.89 | 98.49 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23226049200 |  | 100264772 |  | 7384168O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D303681 | 2621P | NEW CAMP | 442 NEW CAMP RD | 195 | S W | 2023-12-26 | U135005 | U135005 | 2023-11-15 | 2024-05-15 | 2025-11-30 |  | JCKIRK | 2023-12-21 |  |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 10.55 | 2 | 1020.64 | 967.68 | 0 | 52.96 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23230549800 |  | 500789397 |  | 6712228I | 0249538 |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | RANSOM | 159 RANSOM TC REAR | 209 | GEO | 2023-12-21 | DCOLLIN | U133234 | 2023-12-20 | 2024-01-03 | 2024-01-19 |  | DCOLLIN | 2023-12-21 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 9.4667 | 2 | 1799.19 | 845.53 | 0 | 310.94 | 642.72 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23231055900 |  | 100243548 |  | 7356220P |  |  |  | 566 | EX | PAPER ABANDON SL | 2621P | MAIN CROSS | 300 N MAIN CROSS ST TRL | 127 | LOU | 2023-12-26 | U135005 | U135005 | 2023-12-26 | 2023-12-21 |  |  | JKEENER | 2023-12-21 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1
KY | KY - WEST | 2621 | 23026308900 |  |  |  | 6712212G | 2302491 | U134275 |  | 557 | EX | EMER INSTALL 4' OF 3" PMMP | 2621P | KELSEY | 1158 KELSEY DR | 067 | LEX | 2024-01-09 | U136251 | U134275 | 2023-12-20 | 2024-04-29 | 2024-04-30 | 2023-12-22 | MCRAIG | 2023-12-22 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3089 |  |  | 100 | 055732230263089 | 0.2 | 4 | 2961.2 | 1593.52 | 38.81 | 539.08 | 0 | 0 | 6.89 | 782.9 | 4
KY | KY - WEST | 2621 | 23026309000 |  |  |  | 6712212G | 2302491 | U134275 |  | 558 | EX | EMER RETIRE 4' OF 3" PMP | 2621P | KELSEY | 1158 KELSEY DR | 067 | LEX | 2024-01-09 | U136251 | U134275 | 2023-12-20 | 2024-04-30 | 2024-04-30 | 2023-12-22 | MCRAIG | 2023-12-22 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP3090 |  |  | 100 | 055832230263090 | 1.3667 | 0 | 218.46 | 126.86 | 0 | 91.6 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23225443200 |  | 100405432 |  | 6712212G |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094566 | 2621P | KELSEY | 1158 KELSEY DR | 067 | LEX | 2023-12-26 | U135005 | U135005 | 2023-11-10 | 2024-04-30 |  |  | MCRAIG | 2023-12-22 | 2023-12-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.7833 | 3 | 1594.22 | 1198.08 | 258.44 | 137.7 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23229951200 |  | 100316431 |  | 6716208F |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | VENICE | 102 VENICE PR | 067 | LEX | 2023-12-26 | U135005 | U135005 | 2023-12-15 | 2024-01-15 | 2024-02-15 |  | RJCRAWF | 2023-12-22 | 2023-12-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 13.6333 | 3 | 1754.91 | 1211.22 | 276.39 | 267.3 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23230939400 |  | 100418452 |  | 6712228E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | COMANCHE | 1121 COMANCHE TL | 209 | GEO | 2023-12-26 | U135005 | U137585 | 2023-12-21 | 2023-12-21 | 2023-12-21 |  | EFGOINS | 2023-12-22 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 40 | 5 | 3581.68 | 3206.03 | 200.03 | 175.62 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23226010500 |  | 100252915 |  | 7356256F |  |  |  | 566 | EX | PAPER ABANDON | 2621P | 29TH | 1076 29TH ST | 019 | ASH | 2023-12-26 | JCYRUS | U135005 | 2023-11-15 | 2023-11-15 |  |  | JCYRUS | 2023-12-26 | 2023-12-20 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 9.4333 | 4 | 857.62 | 813.09 | 0 | 44.53 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129029900 |  | 100252989 |  | 7356256F |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | SHORT | 3251 SHORT ST | 019 | ASH | 2023-12-27 | JKEENER | U130722 | 2022-09-05 | 2022-12-30 |  |  | JKEENER | 2023-12-27 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 15.9667 | 2 | 1457.04 | 1381.35 | 0 | 75.69 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129069000 |  | 100262980 |  | 7352260N |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | FAIRVIEW | 680 FAIRVIEW AV | 019 | ASH | 2023-12-28 | U135005 | U130722 | 2022-09-05 | 2022-12-30 |  |  | RECUMP | 2023-12-27 | 2023-12-26 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 7.6333 | 4 | 694.42 | 526.21 | 20.27 | 147.94 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23225444600 |  | 100462681 |  | 6720204P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094992 | 2621P | FARMVIEW | 1865 FARMVIEW DR | 067 | LEX | 2023-12-28 | U135005 | U135005 | 2023-11-10 | 2023-12-29 |  |  | RJCRAWF | 2023-12-27 | 2023-12-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.5 | 3 | 987.59 | 882.4 | 56.87 | 48.32 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22129032800 |  | 100250055 |  | 7360252M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2621P | LOUISA | 3244 LOUISA HT | 019 | CAT | 2023-12-29 | U135005 | U130722 | 2022-09-05 | 2022-12-30 |  |  | JROGER1 | 2023-12-28 | 2023-11-29 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 17.9 | 9 | 1671.3 | 1244.34 | 20.27 | 406.69 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23227735600 |  | 100299707 |  | 6712212D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D341317 | 2621P | OLD FRANKFORT | 1799 OLD FRANKFORT PK GYM | 067 | LEX | 2023-12-29 | U135005 | U135005 | 2023-11-29 | 2024-05-28 | 2025-11-30 |  | MCRAIG | 2023-12-28 | 2023-12-27 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 59.4667 | 9 | 9158.8 | 5356.49 | 1017.52 | 1650.79 | 1134 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23228512100 |  | 100325509 |  | 6720208E |  |  |  | 565 | EX | SERVICE LINE/METER UPGRADE | 2621P | INDIAN MOUND | 1237 INDIAN MOUND RD | 067 | LEX | 2023-12-29 | U135005 | U135005 | 2023-12-04 | 2024-01-03 | 2024-01-03 |  | WISHII | 2023-12-28 | 2023-12-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 52.3167 | 8 | 9989.72 | 4312.74 | 245.17 | 1138.29 | 4293.52 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23232492300 |  | 100342214 |  | 7240216N |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | MAYSVILLE | 310 N MAYSVILLE ST 2F | 173 | MT | 2023-12-28 | DENNING | U129939 | 2023-12-28 | 2023-12-28 |  |  | DENNING | 2023-12-28 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.7833 | 1 | 365.22 | 346.25 | 0 | 18.97 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026262601 |  |  |  | 7332288M | 2395710 | U461383 |  | 577 | EX | INSTALL CHAIN LINK FENCE | 2631M | BIGGS | 624 BIGGS LN | 089 | S S | 2024-01-22 | U123258 | U461383 | 2023-12-14 | 2024-09-30 | 2024-10-01 | 2023-12-29 | SGIORDANO | 2023-12-29 | 2023-12-20 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00577 | 3200577 |  |  | WP2626 |  |  | 100 | 057732230262626 | 58.1 | 10 | 72669.9 | 4339.99 | 0 | 3186.84 | 45862.61 | 0 | 38.72 | 19241.74
KY | KY - EAST | 2631 | 23026296700 |  | 501353979 |  | 7348264O | 2300359 | U134275 |  | 555 | EX | INSTALL 165' OF 2" PMIP | 2621P | BROOKE | 2114 BROOKE CR | 089 | FLA | 2024-01-23 | U128132 | U134275 | 2023-09-26 | 2023-11-27 | 2023-11-30 | 2023-11-16 | MCOLLET | 2023-12-29 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP2967 |  |  | 100 | 055532230262967 | 7.2167 | 304 | 17527.84 | 666.16 | 3890.72 | 898.37 | 8412.52 | 0 | 13.38 | 3646.69 | 152
KY | KY - WEST | 2623 | 23221093700 |  | 100346631 |  | 6696212P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D332710 | 2621P | MCDONALD | 307 MCDONALD DR | 239 | VER | 2023-12-29 | BWHITE | U135005 | 2023-10-13 | 2024-04-11 | 2025-10-31 |  | BWHITE | 2023-12-29 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2817.52 | 0 | 0 | 0 | 2817.52 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23228828500 |  | 100344626 |  | 6700224K |  |  |  | 566 | EX | ABANDON SL - DEMO/CUSTRQD | 2621P | 2ND | 313 2ND ST | 239 | MID | 2024-01-02 | U135005 | U133234 | 2023-12-06 | 2023-12-19 | 2024-01-04 |  | BWHITE | 2023-12-29 | 2023-12-26 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 30.8333 | 8 | 4208.56 | 2707.23 | 0 | 148.2 | 1353.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026309100 |  |  |  | 6720212P | 2302494 | U461383 |  | 557 | EX | EMER-INSTALL 4'OF 2"PMMP MAIN | 2621P | FAMILY | 2009 FAMILY CR 4 | 067 | LEX | 2024-01-12 | U136251 | U461383 | 2023-12-20 | 2023-12-19 | 2023-12-19 | 2023-12-20 | MCRAIG | 2024-01-03 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3091 |  |  | 100 | 055732230263091 | 2.0667 | 4 | 2952.18 | 348.27 | 240.84 | -154.18 | 1719.4 | 0 | 0 | 797.85 | 4
KY | KY - WEST | 2623 | 24026310000 |  |  |  | 6712228E | 2402717 | U461383 |  | 557 | EX | EMER-INSTALL 4' OF 2"PMIP MAIN | 2621P | CHOCTAW | 1112 CHOCTAW TL | 209 | GEO | 2024-04-05 | U136251 | U461383 | 2024-01-05 | 2024-11-26 | 2025-07-28 | 2024-01-04 | MCOLLINS | 2024-01-04 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP3100 |  |  | 100 | 055732240263100 |  | 4 | 11757.28 | 3632.8 | 326.16 | 453.91 | 4160.88 | 0 | 17.04 | 3166.49 | 4
KY | KY - EAST | 2631 | 23026294700 |  | 501354264 |  | 7356252L | 2300205 | U122858 |  | 555 | EX | INSTALL 70'-2" PMIP | 2600B | STATE RT 168 | 7914 STATE RT 168 | 019 | CAT | 2024-01-15 | U128132 | U122858 | 2023-09-18 | 2023-12-28 | 2024-01-02 | 2024-01-03 | MCOLLET | 2024-01-05 | 2024-01-02 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP2947 |  |  | 100 | 055532230262947 | 45.6167 | 740 | 12372.22 | 2958.7 | 0 | 2164.13 | 4021.99 | 0 | 31.55 | 3195.85 | 74
KY | KY - WEST | 2623 | 22026238301 |  | 501335909 |  | 6700224H | 2289685 | U126783 |  | 555 | EX | INSTALL 2505'-4" PHHP | 2600B | LEESTOWN | 158 W LEESTOWN RD BOILER | 239 | MID | 2024-03-15 | U128132 | U126783 | 2024-01-10 | 2023-09-11 | 2024-01-31 | 2024-01-01 | J ENSMINGER | 2024-01-08 | 2024-01-12 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2383 |  |  | 100 | 055532220262383 | 585.4667 | 236210 | 297291.9 | 39933.22 | 19240.5 | 20767.49 | 156571.46 | 0 | 7159.06 | 53620.17 | 2990
KY | KY - WEST | 2621 | 23026296000 |  | 501354452 |  | 6712212O | 2300248 | U134275 |  | 555 | EX | INSTALL 220' OF 2" PMMP | 2600B | ALEXANDRIA | 1801 ALEXANDRIA DR OUTLOT | 067 | LEX | 2024-01-12 | U124014 | U134275 | 2023-09-20 | 2024-01-26 | 2024-02-01 | 2024-01-11 | DDAVIS | 2024-01-11 | 2024-01-08 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2960 |  |  | 100 | 055532230262960 | 62 | 1680 | 50792.43 | 3929.9 | 2444.33 | 2485.79 | 28259.33 | 0 | 246.16 | 13426.92 | 210
KY | KY - CENTRAL | 2629 | 23026300600 |  |  |  | 6744208J | 2300593 | U128885 |  | 561 | EX | INSTALL 180'-4" PMLP | 2600B | KITTISON | KITTISON DR | 049 | WIN | 2024-02-01 | U124014 | U128885 | 2023-10-16 | 2023-12-18 | 2024-01-26 | 2024-01-05 | DEREK PAYTON | 2024-01-12 | 2023-12-11 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00561 | 3200561 |  |  | WP3006 |  |  | 100 | 056132230263006 | 143.45 | 3933 | 77710.69 | 10321.25 | 4342.53 | -4527.06 | 45057.52 | 0 | 465.47 | 22050.98 | 207
KY | KY - EAST | 2631 | 23026292300 |  |  |  | 7352256G | 2399973 | U122858 |  | 559 | EX | INSTALL 2" SS | 2600E | ROBERTS | 3308 ROBERTS DR | 019 | ASH | 2025-03-03 | U128132 | U122858 | 2023-09-06 | 2024-02-27 | 2024-02-28 | 2024-01-16 | RECUMP | 2024-01-16 | 2024-01-03 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00559 | 3200559 |  |  | WP2923 |  |  | 100 | 055932230262923 | 9.8333 | 0 | 1292.35 | 715.56 | 0 | 195.18 | 27.06 | 0 | 6.07 | 348.48
KY | KY - CENTRAL | 2629 | 24026309800 |  | 501358960 |  | 6748208I | 2302466 | U134275 |  | 555 | EX | INSTALL 75' - 2" PMMP | 2600B | SYCAMORE | 17 SYCAMORE ST | 049 | WIN | 2024-02-26 | U128132 | U134275 | 2024-01-03 | 2024-02-13 | 2024-02-15 | 2024-01-26 | JOSH PASLEY/STANLEY PIPELINE | 2024-01-29 | 2024-01-24 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP3098 |  |  | 100 | 055532240263098 | 16.1667 | 294 | 21399.98 | 1024.21 | 294.94 | 1577.46 | 13162.61 | 0 | 40.02 | 5300.74 | 98
KY | KY - EAST | 2633 | 23026307300 |  | 501356996 |  | 7364188G | 2301676 | U122858 |  | 555 | EX | INSTALL ~100'-2" PMIP | 2600B | BLACKLOG | 1825 BLACKLOG RD B | 159 | INE | 2024-02-22 | U128132 | U122858 | 2023-12-05 | 2024-01-02 | 2024-01-31 | 2024-01-11 | ORA SLONE | 2024-02-01 | 2024-01-02 |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00555 | 3200555 |  |  | WP3073 |  |  | 100 | 055532230263073 | 133.65 | 2831 | 40892.69 | 8372.79 | 932.79 | 1204.1 | 19338.31 | 0 | 93.6 | 10951.1 | 149
KY | KY - WEST | 2621 | 24026314600 |  |  |  | 6720212M | 2403381 | U461383 |  | 557 | EX | EMER-INSTALL 170' OF 2"/4"PMMP | 2600B | HANOVER | 100 S HANOVER AV | 067 | LEX | 2024-02-13 | U124014 | U461383 | 2024-02-01 | 2024-02-05 | 2024-02-17 | 2024-02-01 | DDAVIS | 2024-02-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3146 | AMRCB |  | 100 | 055732240263146 | 55.0667 | 805 | 141557.61 | 18708.78 | 7392.64 | 5097.17 | 71574.12 | 0 | 259.05 | 38525.85 | 161
KY | KY - WEST | 2621 | 24026310400 |  |  |  | 6724208I | 2402788 | U134275 |  | 559 | EX | INSTALL VALVE & 5' OF 2" PMMP | 2621P | RICHMOND | 3101 RICHMOND RD | 067 | LEX | 2024-09-24 | U132645 | U134275 | 2024-01-09 | 2024-12-30 | 2024-12-31 | 2024-02-07 | J OCHOA | 2024-02-07 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP3104 |  |  | 100 | 055932240263104 |  | 0 | 10413.42 | 3087.93 | 519.78 | 161.33 | 3782.14 | 0 | 46.18 | 2816.06
KY | KY - WEST | 2623 | 24026316500 |  |  |  | 6684228B | 2403545 | U126783 |  | 557 | EX | EMER - INSTALL 15'-2" PMMP | 2621P | KENTUCKY AVE | 879 KENTUCKY AVE | 073 | FRA | 2024-03-29 | U136251 | U126783 | 2024-02-07 | 2024-09-30 | 2025-05-18 | 2024-02-07 | MCOLLINS | 2024-02-07 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP3165 |  |  | 100 | 055732240263165 |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
KY | KY - WEST | 2623 | 22026235100 |  | 501338492 |  | 6712228L | 2292762 | U126783 |  | 555 | EX | INSTALL 2160'-2"/4" PMMP | 2600B | BILL PERKINS | BILL PERKINS LN LT62 | 209 | GEO | 2024-06-19 | U128132 | U126783 | 2022-11-09 | 2023-06-09 | 2024-02-29 | 2024-02-09 | R.HUMPHREYS | 2024-02-09 | 2023-10-04 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2351 |  |  | 100 | 055532220262351 | 303.0667 | 88640 | 179472.03 | 18704.02 | 8360.48 | 3310.74 | 100221.81 | 0 | 2045.45 | 46829.53 | 2216
KY | KY - CENTRAL | 2629 | 24026316000 |  |  |  | 6764176P | 2403473 | U128885 |  | 557 | EX | EMER - INSTALL 2'-3" PMLP | 2621P | PLUM | 145 PLUM ST | 065 | IRV | 2024-02-28 | U128132 | U128885 | 2024-02-06 | 2024-01-16 | 2024-01-29 | 2024-01-30 | WDENNING | 2024-02-13 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3160 |  |  | 100 | 055732240263160 |  | 2 | 6877.79 | 3653.22 | 571.71 | 756.08 | 29.66 | 0 | 0 | 1867.12 | 2
KY | KY - EAST | 2633 | 24026317800 |  |  |  | 7376184A | 2403650 | U122858 |  | 557 | EX | EMER - INSTALL 5'-2" PMIP | 2621P | WALNUT | 94 WALNUT ST | 159 | LOV | 2024-02-20 | U128132 | U122858 | 2024-02-13 | 2024-12-31 | 2025-08-08 | 2024-02-12 | JAHOWARD | 2024-02-16 |  |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00557 | 3200557 |  |  | WP3178 |  |  | 100 | 055732240263178 | 5.25 | 7 | 8355.27 | 5254.06 | 508.79 | 268.4 | 20.61 | 0 | 22.64 | 2280.77 | 7
KY | KY - WEST | 2623 | 22026210901 |  | 501313752 |  | 6716232B | 2289995 | U132703 |  | 555 | EX | INSTALL 8OO' OF 2"PMMP MAIN | 2600B | OAK HILL | OAK HILL LN LT1 | 209 | GEO | 2024-07-24 | U461309 | U132703 | 2023-11-13 | 2024-02-26 | 2024-03-08 | 2024-02-20 | R.HUMPHREYS | 2024-02-20 | 2024-02-12 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2109 |  |  | 100 | 055532220262109 | 56.25 | 6312 | 53441.52 | 3919.07 | 4251.75 | 3280.74 | 27957.48 | 0 | 273.89 | 13758.59 | 789
KY | KY - WEST | 2621 | 23026292000 |  | 501354002 |  | 6724204F | 2399927 | U461383 |  | 555 | EX | INSTALL 2450' OF 2"PMMP MAIN | 2600B | WESTON | 376 WESTON PK LT1 | 067 | LEX | 2024-02-27 | U124014 | U461383 | 2023-09-05 | 2024-02-12 | 2024-03-01 | 2024-02-20 | DDAVIS | 2024-02-20 | 2024-01-24 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2920 |  |  | 100 | 055532230262920 | 127.1833 | 47787 | 93897.7 | 8973.4 | 4556.47 | 8765.52 | 45780.34 | 0 | 385.02 | 25436.95 | 2811
KY | KY - WEST | 2621 | 24026311800 |  |  |  | 6716204D | 2402917 | U461383 |  | 557 | EX | EMER-INSTALL 5' OF 2"PMMP MAIN | 2621P | KIRKLEVINGTON | 3051 KIRKLEVINGTON | 067 | LEX | 2024-04-30 | U136251 | U461383 | 2024-01-15 | 2024-09-30 | 2024-09-30 | 2024-01-13 | LSTANFI | 2024-02-20 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3118 |  |  | 100 | 055732240263118 | 0.46667 | 4 | 2941.72 | 1716.5 | 285.21 | 119.46 | 30.07 | 0 | 7.8 | 782.68 | 4
KY | KY - WEST | 2621 | 24026314000 |  |  |  | 6712204H | 2403330 | U461383 |  | 557 | EX | EMER-INSTALL 5' OF 4"PMMP MAIN | 2621P | WINTHROP | 3451 WINTHROP DR | 067 | LEX | 2024-03-14 | U136251 | U461383 | 2024-01-30 | 2024-09-30 | 2024-09-30 | 2024-01-26 | KKINDER | 2024-02-20 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3140 |  |  | 100 | 055732240263140 | 1.6167 | 5 | 519.5 | 127.36 | 244.49 | 6.52 | 0 | 0 | 0 | 141.13 | 5
KY | KY - WEST | 2621 | 23026293700 |  |  |  | 6716216N | 2395080 | U122858 |  | 561 | EX | INSTALL 74'-2" PMMP | 2600E | FORBES | FORBES DR | 067 | LEX | 2025-02-05 | U132645 | U122858 | 2023-09-08 | 2024-06-05 | 2024-06-30 | 2024-02-21 | DBANKS | 2024-02-21 | 2024-02-19 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP2937 |  |  | 100 | 056132230262937 | 279.5667 | 3192 | 52073.55 | 19470.27 | 4151.73 | 4750.46 | 9390.79 | 0 | 79.13 | 14231.17 | 84
KY | KY - WEST | 2621 | 24026318600 |  |  |  | 6716208J | 2403677 | U134275 |  | 557 | EX | EMER - INSTALL 11' OF 2" PMMP | 2621P | LOWRY | 150 W LOWRY LN | 067 | LEX | 2024-03-08 | U136251 | U134275 | 2024-02-13 | 2024-03-26 | 2024-03-31 | 2024-02-08 | MCRAIG | 2024-02-21 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3186 |  |  | 100 | 055732240263186 | 0.36667 | 11 | 41990.31 | 5614.64 | 47.94 | 647.51 | 24123.64 | 0 | 25.15 | 11531.43 | 11
KY | KY - EAST | 2631 | 24026320800 |  |  |  | 7352256C | 2403719 | U122858 |  | 557 | EX | EMER - INSTALL 5'-3" PMIP | 2621P | KENTUCKY | 235 KENTUCKY ST | 019 | ASH | 2024-02-26 | U128132 | U122858 | 2024-02-14 | 2024-03-28 | 2024-03-30 | 2024-02-13 | MCOLLET | 2024-02-22 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP3208 |  |  | 100 | 055732240263208 | 0.95 | 4 | 25129.82 | 4573.73 | 0 | 5456.79 | 7992.48 | 0 | 39.98 | 7066.84 | 4
KY | KY - WEST | 2621 | 22026236700 |  |  |  | 6720212B | 2293506 | U122858 |  | 561 | EX | INSTALL 134'-4" PMLP | 2600E | LOCUST | 328 LOCUST AV | 067 | LEX | 2024-03-13 | U136251 | U122858 | 2022-11-14 | 2024-03-18 | 2024-03-20 | 2024-02-19 | MCRAIG | 2024-02-27 | 2024-02-12 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP2367 |  |  | 100 | 056132220262367 | 147.9 | 2880 | 27660 | 10788.78 | 1259.06 | 3429.77 | 4478.88 | 0 | 61.68 | 7641.83 | 160
KY | KY - CENTRAL | 2629 | 22026237801 |  |  |  | 6732252O | 2293704 | U128885 |  | 557 | EX | INSTALL 4,100'-2" PMMP | 2600B | BROADWAY | BROADWAY AV | 097 | CYN | 2024-03-07 | U128132 | U128885 | 2023-10-27 | 2024-08-09 | 2024-12-31 | 2024-01-25 | WILL FULKS | 2024-02-27 | 2024-02-22 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP2378 | AMRCB |  | 100 | 055732220262378 | 615.15 | 386910 | 836183.38 | 42436.64 | 17120.46 | 13359.02 | 534594.13 | 0 | 1499.81 | 227173.32 | 4299
KY | KY - WEST | 2621 | 24026328300 |  |  |  | 6716208H | 2403957 | U122858 |  | 557 | EX | EMER - INSTALL 26'-6" PMLP | 2621P | MONTCLAIR | MONTCLAIR DR | 067 | LEX | 2024-03-29 | U136251 | U141016 | 2024-02-26 | 2024-03-07 | 2024-03-10 | 2024-02-26 | KKINDER | 2024-02-28 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3283 | AMRCB |  | 100 | 055732240263283 | 3.05 | 26 | 14201.79 | 6673.29 | 2922.53 | 547.97 | 29.24 | 0 | 28.79 | 3999.97 | 26
KY | KY - WEST | 2623 | 24026331100 |  |  |  | 6708228G | 2404137 | U126783 |  | 557 | CO | EMER - INSTALL ~5'-2" PMMP | 2621P | WINDING CREEK | WINDING CREEK | 209 | GEO | 2024-08-23 |  | U126783 | 2024-03-04 | 2024-12-27 | 2024-12-29 | 2024-02-29 | D COLLINS | 2024-02-29 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP3311 |  |  | 100 | 055732240263311 |  | 0 | 523.81 | 312.43 | 0 | 29.94 | 0 | 0 | 1.25 | 180.19
KY | KY - CENTRAL | 2629 | 24026329400 |  |  |  | 6744208J | 2403993 | U128885 |  | 557 | EX | EMER - INSTALL 2'-3" PMLP | 2621P | ORAGE | ORAGE | 049 | WIN | 2024-03-07 | U128132 | U128885 | 2024-02-27 | 2024-12-18 | 2024-12-31 | 2024-02-21 | NRICHIE | 2024-03-01 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3294 |  |  | 100 | 055732240263294 |  | 2 | 6384.11 | 1473.73 | 833.51 | 1037.83 | 1250.71 | 0 | 15 | 1773.33 | 2
KY | KY - WEST | 2621 | 24026311700 |  | 501314322 |  | 6724208P | 2402885 | U461383 |  | 555 | EX | INSTALL 360' OF 2"PMMP MAIN | 2600B | CHILESBURG | 295 CHILESBURG RD FG 49 | 067 | LEX | 2024-03-05 | CRUCKER | U461383 | 2024-01-15 | 2024-04-09 | 2024-04-12 | 2024-03-04 | DDAVIS | 2024-03-04 | 2024-02-22 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3117 |  |  | 100 | 055532240263117 | 52.5 | 2905 | 38311.55 | 3728.82 | 1607.33 | 1817.4 | 20089.63 | 0 | 232.95 | 10835.42 | 415
KY | KY - WEST | 2623 | 23026289700 |  |  |  | 6712232N | 2399730 | U461383 |  | 557 | EX | INSTALL 70' OF 3"PMLP MAIN | 2621P | BROADWAY | 359 N BROADWAY ST DN | 209 | GEO | 2025-03-03 | U136251 | U461383 | 2023-08-25 | 2023-11-28 | 2024-08-31 | 2024-03-05 | DCOLLINS/SBARKER | 2024-03-05 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP2897 | AMRCB |  | 100 | 055732230262897 |  | 70 | 43735.5 | 11170.89 | 3115.89 | 4031.57 | 16309.88 | 0 | 218.82 | 8888.45 | 70
KY | KY - WEST | 2621 | 22026183301 |  |  |  | 6716212B | 1968251 | U134275 |  | 561 | EX | SMRP INSTALL 1120' 8-12" CSHP | 2600B | LEESTOWN | 1498 LEESTOWN RD | 067 | LEX | 2025-01-17 | U136251 | U134275 | 2024-03-11 | 2023-11-29 | 2024-03-15 | 2024-03-04 | JOSH PASLEY/TEAM FISHEL | 2024-03-06 | 2023-09-11 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP1833 | AMRCB |  | 100 | 056132220261833 | 824.8333 | 103494 | 1650295.52 | 68359.5 | 188179.55 | 81858.64 | 938297.41 | 0 | 31772.5 | 341827.92 | 1101
KY | KY - WEST | 2621 | 23026309300 |  |  |  | 6712204D | 2302539 | U122858 |  | 557 | EX | EMER - INSTALL 5'-4" PMMP | 2621P | MERRIMAC | 548 MERRIMAC DR | 067 | LEX | 2024-07-09 | U136251 | U122858 | 2023-12-21 | 2024-10-30 | 2025-06-24 | 2024-02-22 | LSTANFI | 2024-03-06 | 2024-02-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3093 |  |  | 100 | 055732230263093 | 7.5667 | 12 | 3958.19 | 547.34 | 1087.21 | 39.23 | 0 | 0 | 18.62 | 2265.79 | 6
KY | KY - WEST | 2621 | 23026299700 |  | 501354375 |  | 6716212N | 2300730 | U461383 |  | 555 | EX | INSTALL 325' OF 2"PMMP MAIN | 2600B | LEGION | 340 LEGION DR | 067 | LEX | 2024-03-25 | U124014 | U461383 | 2023-10-10 | 2024-04-22 | 2024-04-26 | 2024-03-14 | DDAVIS | 2024-03-14 | 2024-03-06 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2997 |  |  | 100 | 055532230262997 | 50 | 2556 | 52412.36 | 3252.86 | 1470.61 | 1429.99 | 30331.53 | 0 | 138.44 | 15788.93 | 426
KY | KY - CENTRAL | 2629 | 24026329700 |  |  |  | 6740208H | 2404044 | U128885 |  | 557 | EX | EMER - 2'-2" PMMP | 2621P | SHALA-MAR RUE | SHALA-MAR RUE | 049 | WIN | 2024-04-12 | U128132 | U128885 | 2024-02-28 | 2024-12-17 | 2024-12-31 | 2024-02-21 | NRICHIE | 2024-03-14 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3297 |  |  | 100 | 055732240263297 |  | 2 | 8583.87 | 2360.78 | 855.44 | 286.18 | 2462.37 | 0 | 0 | 2619.1 | 2
KY | KY - WEST | 2621 | 23026272901 |  | 501347263 |  | 6712204E | 2397231 | U461383 |  | 555 | EX | INSTALL 2500' OF 2"PMMP MAIN | 2600B | POLLY | POLLY CT LT1 | 113 | NIC | 2024-04-03 | U128132 | U461383 | 2024-02-09 | 2024-02-01 | 2024-03-22 | 2024-03-13 | JOSHUA COX | 2024-03-15 | 2024-02-08 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2729 |  |  | 100 | 055532230262729 | 355.3167 | 123050 | 251654.55 | 23500.97 | 5579.9 | -196.75 | 151177.03 | 0 | 2122.28 | 69471.12 | 2675
KY | KY - CENTRAL | 2629 | 24026332600 |  |  |  | 6740232I | 2404438 | U128885 |  | 557 | EX | EMER INSTALL 10'-6" PMMP | 2600B | 2ND | 2ND ST | 017 | PAR | 2024-09-25 | U128132 | U128885 | 2024-03-12 | 2025-03-20 | 2025-11-20 | 2024-03-14 | EDWARD FOX | 2024-03-15 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3326 |  |  | 100 | 055732240263326 |  | 10 | 32430.81 | 3962.07 | 0 | 1460.34 | 16970.54 | 0 | 117.7 | 9920.16 | 10
KY | KY - WEST | 2623 | 24026332800 |  |  |  | 6712224H | 2404460 | U126783 |  | 557 | CO | EMER - INSTALL 5'-4" PMIP | 2600B | SUNDOWN | 230 SUNDOWN | 209 | GEO | 2024-07-10 |  | U126783 | 2024-03-12 | 2025-02-28 | 2025-10-10 | 2024-03-16 | DCOLLINS | 2024-03-16 | 2024-03-14 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP3328 |  |  | 100 | 055732240263328 | 57.95 | 0 | 8388.17 | 3830.9 | 80.33 | 1877.88 | 0 | 0 | 30.6 | 2568.46
KY | KY - WEST | 2621 | 21026145601 |  |  |  | 6720212G | 2183195 | U134275 |  | 557 | EX | INSTALL 1885' - 4" PMMP MAIN | 2600B | NEW CIRCLE | 450 E NEW CIRCLE RD | 067 | LEX | 2024-06-25 | U128132 | U134275 | 2023-09-20 | 2023-07-05 | 2024-12-31 | 2024-03-14 | JAMIE LYNN | 2024-03-18 | 2023-09-11 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP1456 | AMRCB |  | 100 | 055732210261456 | 776.5167 | 198644 | 816623.03 | 52493.93 | 14058.6 | 11378.72 | 500636.69 | 0 | 18569.63 | 219485.46 | 1874
KY | KY - EAST | 2631 | 19026913000 |  |  |  | 7360252I | 1968534 | U132280 |  | 557 | EX | INSTALL 730'-2"PMMP | 2600B | PANOLA | PANOLA | 019 | CAT | 2024-09-19 | U128132 | U132280 | 2019-11-27 | 2024-01-08 | 2024-12-31 | 2024-02-22 | ORA SLONE | 2024-03-26 | 2024-01-02 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP9130 | AMRCB |  | 100 | 055732190269130 | 284.6333 | 26871 | 242981.39 | 19595.12 | 3004.13 | 4491.99 | 151007.87 | 0 | 366.67 | 64515.61 | 689
KY | KY - WEST | 2623 | 22026205401 |  | 501281464 |  | 6696212N | 2289302 | U126783 |  | 555 | EX | INSTALL 1330'-4" PMMP | 2600B | SCHOOL HOUSE | SCHOOL HOUSE RD | 239 | VER | 2024-04-12 | U136251 | U126783 | 2024-03-25 | 2024-03-08 | 2024-04-05 | 2024-03-26 | DEREK PAYTON | 2024-03-26 | 2024-03-26 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2054 |  |  | 100 | 055532220262054 | 174.9333 | 0 | 288486.41 | 11412.88 | 14380.31 | 5602.7 | 171075.54 | 0 | 2057.59 | 83957.39
KY | KY - CENTRAL | 2629 | 24026335100 |  |  |  | 6752180N | 2404593 | U141016 |  | 557 | EX | EMER - INSTALL 4'-3" PMMP | 2621P | WACO LOOP | WACO LOOP RD | 151 | WAC | 2024-04-02 | U128132 | U141016 | 2024-03-19 | 2024-11-11 |  | 2024-03-12 | LCLARK | 2024-03-27 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3351 |  |  | 100 | 055732240263351 |  | 4 | 12497.25 | 4787.36 | 978.73 | 475.46 | 2402.25 | 0 | 29.87 | 3823.58 | 4
KY | KY - WEST | 2621 | 24026336800 |  |  |  | 6724204D | 2404682 | U134275 |  | 557 | EX | EMER - INSTALL 5' OF 2" PMMP | 2621P | HORSEMINT | 3709 HORSEMINT TR | 067 | LEX | 2024-08-14 | U136251 | U134275 | 2024-03-22 | 2024-07-31 | 2024-08-31 | 2024-03-20 | RVANDERPOOL | 2024-03-27 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3368 |  |  | 100 | 055732240263368 |  | 5 | 5104.57 | 3018.04 | 0 | 504.2 | 0 | 0 | 18.71 | 1563.62 | 5
KY | KY - WEST | 2621 | 23026267200 |  |  |  | 6716208K | 2396254 | U122858 |  | 557 | EX | INSTALL 60'-4" PMLP | 2600B | JESSELIN | 107 JESSELIN DR | 067 | LEX | 2024-04-03 | U128132 | U122858 | 2023-03-16 | 2024-02-12 | 2024-06-30 | 2024-03-28 | JOSHUA COX | 2024-03-28 | 2024-03-20 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2672 | AMRCB |  | 100 | 055732230262672 | 62.9667 | 801 | 34888.84 | 3968.03 | 2926.07 | 389.48 | 17681.5 | 0 | 120.74 | 9803.02 | 89
KY | KY - CENTRAL | 2629 | 24026335400 |  |  |  | 6752180M | 2404602 | U141016 |  | 557 | EX | EMER - INSTALL 2'-2" PMMP | 2621P | FIKE | FIKE RD | 151 | WAC | 2024-04-02 | U128132 | U141016 | 2024-03-19 | 2024-11-21 |  | 2024-03-13 | NRICHIE | 2024-03-28 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3354 |  |  | 100 | 055732240263354 |  | 2 | 7568.56 | 2635.31 | 532.87 | 980.13 | 1093.5 | 0 | 21.58 | 2305.17 | 2
KY | KY - WEST | 2623 | 24026338200 |  |  |  | 6688228A | 2404991 | U126783 |  | 557 | CO | EMER - INSTALL 5'-3" PMMP | 2600B | COLONIEL TRACE | 1017 COLONIEL TRACE | 073 | FRA | 2024-04-19 |  | U126783 | 2024-04-03 | 2025-01-30 | 2025-09-19 | 2024-03-29 | M COLLINS | 2024-03-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP3382 |  |  | 100 | 055732240263382 |  | 0 | 12009.27 | 3234.33 | 0 | 1818.68 | 3724.75 | 0 | 3.51 | 3228
KY | KY - WEST | 2621 | 24026330300 |  |  |  | 6720200B | 2404124 | U141016 |  | 557 | EX | EMER - INSTALL 5'- 2" PMMP | 2600E | WILTSHIRE | 2104 WILTSHIRE PL | 067 | LEX | 2024-06-05 | U136251 | U141016 | 2024-03-04 | 2024-12-31 | 2025-08-24 | 2024-02-29 | KKINDER | 2024-04-02 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3303 |  |  | 100 | 055732240263303 | 2.0333 | 6 | 10905.49 | 6871.27 | 0 | 686.23 | 0 | 0 | 0 | 3347.99 | 6
KY | KY - WEST | 2621 | 24026331900 |  |  |  | 6716204D | 2404366 | U461383 |  | 557 | EX | EMER - INSTALL 1' OF 2"PMMP | 2621P | KIRKLEVINGTON | 3051 KIRKLEVINGTON DR | 067 | LEX | 2024-04-12 | U136251 | U461383 | 2024-03-08 | 2024-05-01 | 2024-05-01 | 2024-03-08 | RJCRAWF | 2024-04-02 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3319 |  |  | 100 | 055732240263319 | 0.9 | 1 | 3472.1 | 2054.55 | 143.37 | 201.89 | 0 | 0 | 9.79 | 1062.5 | 1
KY | KY - WEST | 2621 | 24026334000 |  |  |  | 6720200F | 2404516 | U134275 |  | 557 | EX | INSTALL 5' OF 2" PMMP | 2621P | MARCHMONT | 5004 MARCHMONT WY | 067 | LEX | 2024-04-29 | U136251 | U134275 | 2024-03-14 | 2024-03-28 | 2026-02-08 | 2024-03-14 | RSTRONG | 2024-04-02 | 2024-03-25 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3340 |  |  | 100 | 055732240263340 | 10.2 | 10 | 11358.98 | 6332.15 | 23.97 | 1463.33 | 1395.24 | 0 | 2.06 | 2142.23 | 5
KY | KY - WEST | 2623 | 23026298800 |  | 501171335 |  | 6712236C | 2300590 | U132703 |  | 555 | EX | INSTALL 900'-2" PMMP MAIN | 2600B | YUSEN | 335 E YUSEN DR REAR | 209 | GEO | 2024-08-07 | U136251 | U132703 | 2023-10-04 | 2024-04-04 | 2024-04-17 | 2024-04-08 | DUSTIN DAVIS | 2024-04-03 | 2024-03-18 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2988 |  |  | 100 | 055532230262988 | 98.0167 | 12054 | 154240.87 | 6278.96 | 1838.57 | 1962.07 | 102374.17 | 0 | 306.77 | 41480.33 | 861
KY | KY - WEST | 2623 | 24026317300 |  | 501361117 |  | 6696212P | 2403518 | U126783 |  | 555 | EX | INSTALL 270'-2" PMMP | 2600B | SUGARTREE | 224 SUGARTREE LN | 239 | VER | 2024-06-29 | U128132 | U126783 | 2024-02-12 | 2024-04-26 | 2024-04-30 | 2024-04-05 | JOSHUA COX | 2024-04-08 | 2024-04-01 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP3173 |  |  | 100 | 055532240263173 | 54.8667 | 1566 | 32804.09 | 3431.77 | 1504.66 | 214.91 | 18731.79 | 0 | 78.03 | 8842.93 | 174
KY | KY - EAST | 2631 | 24026337800 |  |  |  | 7360252I | 1968534 | U128885 |  | 559 | EX | INSTALL 8" SS | 2600B | PANOLA | PANOLA ST | 019 | CAT | 2024-09-19 | U128132 | U128885 | 2024-04-01 | 2024-04-30 | 2024-04-30 | 2024-02-22 | ORA SLONE | 2024-04-08 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00559 | 3200559 |  |  | WP3378 | AMRCB |  | 100 | 055932240263378 |  | 0 | 2650.82 | 0 | 2063.01 | 0 | 0 | 0 | 0 | 587.81
KY | KY - CENTRAL | 2629 | 22026164000 |  |  |  | 6740232N | 2286363 | U128885 |  | 557 | EX | INSTALL 5,100'-2" PMMP | 2600B | SCOTT | SCOTT AV | 017 | PAR | 2025-04-30 | U128132 | U128885 | 2022-02-08 | 2024-08-08 | 2024-12-31 | 2024-01-31 | EDWARD FOX | 2024-04-10 | 2023-09-11 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP1640 | AMRCB |  | 100 | 055732220261640 | 991.05 | 722522 | 1341919.13 | 68893.55 | 15773.36 | 28795.93 | 876042.25 | 0 | 5692.07 | 346721.97 | 5198
KY | KY - WEST | 2623 | 23026283801 |  | 501350442 |  | 6700212O | 2398395 | U126783 |  | 555 | EX | INSTALL 5705'-2"/4" PMMP | 2600B | GLENEAGLES | GLENEAGLES WY LT54 | 239 | VER | 2024-05-02 | U136251 | U126783 | 2023-11-01 | 2024-01-22 | 2024-05-31 | 2024-04-08 | DEREK PAYTON | 2024-04-11 | 2024-01-15 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2838 |  |  | 100 | 055532230262838 | 350.45 | 268875 | 388707.97 | 23921.42 | 25539.77 | 536.59 | 226573.11 | 0 | 4628.56 | 107508.52 | 5975
KY | KY - WEST | 2623 | 23026292201 |  | 501354062 |  | 6684228K | 2180883 | U126783 |  | 555 | EX | INSTALL 360'-4" PMMP | 2600E | BROADWAY | 106 E BROADWAY ST NEW | 073 | FRA | 2024-06-25 | U126783 | U126783 | 2024-03-04 | 2024-01-15 | 2024-02-29 | 2024-03-08 | KEVIN KOUNS | 2024-04-22 | 2024-01-26 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2922 |  |  | 100 | 055532230262922 | 114.25 | 4998 | 171750.99 | 7541.43 | 2418.18 | 3761.92 | 109171.99 | 0 | 1060.95 | 47796.52 | 357
KY | KY - WEST | 2621 | 24026331500 |  | 501362650 |  | 6716208J | 2404261 | U461383 |  | 555 | EX | INSTALL 300' OF 2"PMMP MAIN | 2600B | NORMAN | 2350 NORMAN LN | 067 | LEX | 2024-07-06 | U128132 | U461383 | 2024-03-06 | 2024-10-25 | 2024-10-31 | 2024-04-24 | JOSHUA COX | 2024-04-24 | 2024-04-17 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3315 |  |  | 100 | 055532240263315 | 56.75 | 2646 | 40161.78 | 3549.93 | 1529.59 | 222.3 | 24338.94 | 0 | 84.8 | 10436.22 | 378
KY | KY - EAST | 2631 | 24026340600 |  |  |  | 7352260O | 2286985 | U938437 |  | 557 | EX | INSTALL LP FITTINGS | 2600B | HOUSTON | HOUSTON ST | 019 | ASH | 2024-07-16 | U128132 | U938437 | 2024-04-23 | 2024-12-31 |  | 2024-04-25 | DAVID SKAGGS | 2024-04-25 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP3406 | AMRCB |  | 100 | 055732240263406 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 22026172301 |  |  |  | 7352260O | 2286985 | U461383 |  | 557 | EX | INSTALL 5000' OF 2"PMMP MAIN | 2600B | VERNA | VERNA | 019 | ASH | 2024-07-16 | U128132 | U461383 | 2024-04-24 | 2023-06-30 | 2024-12-31 | 2023-11-13 | DAVID SKAGGS | 2024-04-26 | 2024-04-24 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP1723 | AMRCB |  | 100 | 055732220261723 | 1256.8667 | 812295 | 1225170.53 | 86247.14 | 14782.26 | 14775.95 | 799964.93 | 0 | 3489.31 | 305910.94 | 4923
KY | KY - WEST | 2621 | 24026333000 |  |  |  | 6716212H | 2404461 | U461383 |  | 557 | EX | EMER-INSTALL 18'-4"PMLP MAIN | 2621P | LIMESTONE | 263 N LIMESTONE ST | 067 | LEX | 2024-08-13 | U136251 | U461383 | 2024-03-12 | 2024-07-29 | 2025-03-10 | 2024-04-30 | LSTAN | 2024-04-30 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3330 | AMRCB |  | 100 | 055732240263330 |  | 18 | 20568.01 | 4370.52 | 778.31 | 1107.09 | 9117.61 | 0 | 43.58 | 5150.9 | 18
KY | KY - WEST | 2621 | 24026338500 |  | 501364358 |  | 6728208A | 2405110 | U461383 |  | 555 | EX | INSTALL 585' OF 2"PMMP MAIN | 2600B | CAVERSHAM PARK | CAVERSHAM PARK LN LT2 | 067 | LEX | 2025-02-05 | U136251 | U461383 | 2024-04-10 | 2024-06-24 | 2024-06-28 | 2024-05-02 | JOSHUA COX | 2024-05-03 | 2024-04-29 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3385 |  |  | 100 | 055532240263385 | 50.4167 | 3228 | 30882.37 | 3580.91 | 2222.16 | 207.8 | 17283.4 | 0 | 145.86 | 7442.24 | 538
KY | KY - WEST | 2623 | 22026241701 |  |  |  | 6712228B | 2294169 | U461383 |  | 561 | EX | INSTALL 1425' OF 2"PMMP MAIN | 2600B | WASHINGTON | W WASHINGTON ST | 209 | GEO | 2024-08-07 | U136251 | U461383 | 2024-04-08 | 2024-01-15 | 2024-06-01 | 2024-04-12 | LESLIE SHARON | 2024-05-08 | 2024-04-10 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00561 | 3200561 |  |  | WP2417 | AMRCB |  | 100 | 056132220262417 | 540.5667 | 98325 | 698687.73 | 37331.49 | 4332.75 | 35214.92 | 424601.56 | 0 | 5905.4 | 191301.61 | 1425
KY | KY - CENTRAL | 2629 | 24026337900 |  | 501339588 |  | 6748204C | 2293331 | U128885 |  | 555 | EX | INSTALL 2,550'-2" PMMP | 2600B | DUCLAIR | 105 DUCLAIR DR LT38 | 049 | WIN | 2024-10-28 | U128132 | U128885 | 2024-04-02 | 2024-06-10 | 2024-06-30 | 2024-05-09 | DEREK PAYTON | 2024-05-09 | 2024-04-22 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP3379 |  |  | 100 | 055532240263379 | 115.5333 | 50032 | 82903.24 | 7805.98 | 5347.63 | 488.28 | 49508.1 | 0 | 328.86 | 19424.39 | 3127
KY | KY - EAST | 2631 | 23026279500 |  |  |  | 7356256B | 2398273 | U122858 |  | 561 | EX | INSTALL 339'-8" PMLP | 2600E | 18TH | 18TH ST | 019 | ASH | 2025-03-03 | U128132 | U122858 | 2023-06-16 | 2024-12-13 | 2024-12-30 | 2024-05-10 | MCOLLET | 2024-05-10 | 2024-04-22 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00561 | 3200561 |  |  | WP2795 | AMRCB |  | 100 | 056132230262795 | 381.7167 | 10125 | 110539.26 | 25696.51 | 16014.37 | 22894.28 | 18485.06 | 0 | 544.25 | 26904.79 | 225
KY | KY - WEST | 2621 | 24026321100 |  | 501361324 |  | 6716216E | 2403608 | U141016 |  | 555 | EX | INSTALL 1400' OF 2" PMMP MAIN | 2600B | DAHLIA | 661 DAHLIA DR LT88 | 067 | LEX | 2024-07-22 | U128132 | U141016 | 2024-02-14 | 2024-05-17 | 2024-06-01 | 2024-05-14 | RANDALL HUMPHREYS | 2024-05-14 | 2024-04-29 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3211 |  |  | 100 | 055532240263211 | 87 | 16212 | 68220.66 | 6412.76 | 3049.79 | 6441.3 | 36478.99 | 0 | 231.5 | 15606.32 | 1351
KY | KY - WEST | 2621 | 24026342000 |  |  |  | 6720208D | 2405691 | U132703 |  | 557 | EX | EMER - INSTALL 2' OF 2"PMMP | 2621P | CREATIVE | CREATIVE | 067 | LEX | 2024-06-18 | U132645 | U132703 | 2024-05-03 | 2024-05-31 | 2024-05-31 | 2024-05-02 | MCRAIG | 2024-05-14 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3420 | AMRCB |  | 100 | 055732240263420 | 0 | 2 | 6607.96 | 1486.29 | 23.97 | 549.11 | 3121.2 | 0 | 7.02 | 1420.37 | 2
KY | KY - CENTRAL | 2629 | 23026300401 |  |  |  | 6744208J | 2302060 | U128885 |  | 561 | EX | INSTALL 1150' 4/2" PMMP | 2600B | MARKET | MARKET ST | 049 | WIN | 2024-10-18 | U128132 | U128885 | 2024-05-08 | 2024-02-22 | 2024-04-26 | 2024-04-12 | RANDALL HUMPHREYS | 2024-05-16 | 2024-02-26 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00561 | 3200561 |  |  | WP3004 |  |  | 100 | 056132230263004 | 276.75 | 41004 | 291755.2 | 17945.91 | 6441.91 | 20519.45 | 163867.64 | 0 | 1429.17 | 81551.12 | 1139
KY | KY - WEST | 2621 | 24026337000 |  | 500518347 |  | 6712204H | 2404724 | U461383 |  | 555 | EX | INSTALL 675' OF 2"PMMP MAIN | 2600B | RETRAC | 470 RETRAC RD | 067 | LEX | 2024-06-20 | U128132 | U461383 | 2024-03-26 | 2024-04-17 | 2024-06-30 | 2024-05-15 | JOSHUA COX | 2024-05-21 | 2024-05-07 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3370 |  |  | 100 | 055532240263370 | 69.5167 | 5976 | 44370.55 | 5330 | 2251.58 | 296.31 | 26370.01 | 0 | 142.34 | 9980.31 | 664
KY | KY - WEST | 2623 | 24026309500 |  | 501351972 |  | 6716236I | 2302554 | U126783 |  | 555 | EX | INSTALL 215'-2" PMMP | 2600B | MEADOW LARK | 115 MEADOW LARK TR | 209 | GEO | 2024-05-23 | U132645 | U126783 | 2024-01-02 | 2024-05-22 | 2024-05-27 | 2024-05-22 | RANDALL HUMPHREYS | 2024-05-22 | 2024-05-17 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP3095 |  |  | 100 | 055532240263095 | 32 | 952 | 19486.43 | 2274.36 | 1519.34 | 1793.91 | 9547.6 | 0 | 50.22 | 4301 | 238
KY | KY - WEST | 2621 | 22026171100 |  |  |  | 6720208A | 2286912 | U461383 |  | 557 | EX | INSTALL 2715' OF 2"/4"PMMP | 2600B | ASHLAND | ASHLAND TR | 067 | LEX | 2025-01-17 | U128132 | U461383 | 2022-02-24 | 2024-01-22 | 2024-08-19 | 2024-05-22 | JDUNN | 2024-05-23 | 2024-01-22 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP1711 | AMRCB |  | 100 | 055732220261711 | 755.05 | 240422 | 734298.53 | 52313.43 | 19974.41 | 13805.35 | 449615.2 | 0 | 8729.91 | 189860.23 | 2642
KY | KY - CENTRAL | 2629 | 24026337600 |  |  |  | 6744208N | 2404846 | U128885 |  | 561 | EX | INSTALL 30'-2" PMMP | 2600B | BARLOW | 539 BARLOW DR | 049 | WIN | 2024-11-09 | U128132 | U128885 | 2024-04-01 | 2024-05-24 | 2024-05-31 | 2024-05-22 | DEREK PAYTON | 2024-05-23 | 2024-05-14 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00561 | 3200561 |  |  | WP3376 |  |  | 100 | 056132240263376 | 64.5 | 216 | 27755.6 | 4615.3 | 854.4 | 256.31 | 15977.07 | 0 | 56.14 | 5996.38 | 27
KY | KY - WEST | 2623 | 22026183001 |  | 501327244 |  | 6688228L | 2287144 | U126783 |  | 555 | EX | INSTALL 4955'-2" PMMP | 2600B | LEESTOWN | 1100 LEESTOWN RD | 073 | FRA | 2024-12-12 | U136251 | U126783 | 2024-04-30 | 2024-11-26 | 2024-12-25 | 2023-03-22 | ALEX WILLIAMSON | 2024-05-24 | 2023-02-14 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP1830 |  |  | 100 | 055532220261830 |  | 1705 | 124010.5 | 17739.46 | 15801.11 | 2375.96 | 67640.81 | 0 | 886.2 | 19566.96 | 1705
KY | KY - EAST | 2631 | 24026344300 |  |  |  | 7352260O | 2406121 | U141016 |  | 557 | EX | EMER-INSTALL 6' OF 4" PMIP | 2621P | MCNIPP | 2892 MCNIPP DR | 019 | ASH | 2024-06-05 | U128132 | U141016 | 2024-05-22 | 2025-07-31 | 2026-03-13 | 2024-05-21 | MCOLLETT | 2024-05-28 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP3443 |  |  | 100 | 055732240263443 |  | 6 | 20651.9 | 4919.05 | 1494.4 | 5169.12 | 4470 | 0 | 54.31 | 4545.02 | 6
KY | KY - WEST | 2621 | 24026332100 |  |  |  | 6716208K | 2404382 | U134275 |  | 557 | EX | INSERT 50' OF 3" PMLP | 2621P | HEATHER | 2069 HEATHER WY | 067 | LEX | 2024-10-18 | U136251 | U134275 | 2024-03-08 | 2024-10-29 | 2025-06-12 | 2024-05-29 | AWILLIAMSON | 2024-05-29 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3321 |  |  | 100 | 055732240263321 |  | 50 | 25644.18 | 8165.35 | 2659.74 | 1251.83 | 6838.99 | 0 | 107.6 | 6620.67 | 50
KY | KY - WEST | 2621 | 24026338000 |  |  |  | 6712212K | 2404974 | U122858 |  | 561 | EX | INSTALL 65'-2"&4" PMMP | 2600E | CROSS KEYS | 1295 CROSS KEYS RD | 067 | LEX | 2024-10-29 | U136251 | U122858 | 2024-04-03 | 2024-05-07 | 2024-05-30 | 2024-05-29 | RANDALL TINCHER | 2024-05-30 | 2024-05-20 | 2024-05-20 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP3380 |  |  | 100 | 056132240263380 | 117 | 1152 | 59541.79 | 10541.53 | 14159.29 | 2051.89 | 17702.45 | 0 | 226.31 | 14860.32 | 72
KY | KY - CENTRAL | 2629 | 24026343700 |  |  |  | 6744208K | 2406069 | U128885 |  | 557 | EX | EMER - INSTALL 3'-3" PMMP | 2621P | MEADOW | MEADOW | 049 | WIN | 2024-06-04 | U128132 | U128885 | 2024-05-21 | 2024-05-10 | 2024-05-17 | 2024-05-16 | NRICHIE | 2024-05-31 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3437 |  |  | 100 | 055732240263437 |  | 3 | 10177.86 | 3108.64 | 318.23 | 947.6 | 3592 | 0 | 15.14 | 2196.25 | 3
KY | KY - WEST | 2623 | 24026346100 |  |  |  | 6696212O | 2406369 | U126783 |  | 557 | EX | EMER - INSTALL 2'-2" PMMP | 2621P | SHEFFIELD | 531 SHEFFIELD DR | 239 | VER | 2025-02-14 | U136251 | U126783 | 2024-06-05 | 2025-02-25 | 2025-02-28 | 2024-06-05 | CDESPAIN | 2024-06-05 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP3461 |  |  | 100 | 055732240263461 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
KY | KY - WEST | 2621 | 24026343300 |  |  |  | 6724208G | 2406051 | U461383 |  | 559 | EX | INSTALL 4" POLY VALVE | 2621P | PAVILION | 1916 PAVILION WY | 067 | LEX | 2025-03-03 | U136251 | U461383 | 2024-05-20 | 2024-10-31 | 2024-11-01 | 2024-06-06 | AWILLIAMSON | 2024-06-06 | 2024-06-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP3433 |  |  | 100 | 055932240263433 | 35.1167 | 50 | 7689.14 | 2541.88 | 573.58 | 313.05 | 2631.14 | 0 | 24.49 | 1605 | 10
KY | KY - WEST | 2623 | 24026312200 |  | 501352315 |  | 6700212N | 2399932 | U126783 |  | 555 | EX | INSTALL 230'-2" PMMP | 2600B | NORMANDY | 200 NORMANDY RD | 239 | VER | 2024-09-20 | U128132 | U126783 | 2024-01-17 | 2024-06-12 | 2024-06-14 | 2024-06-07 | R.HUMPHREYS | 2024-06-07 | 2024-05-28 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP3122 |  |  | 100 | 055532240263122 | 68.8 | 2133 | 37251.74 | 4559.85 | 0 | 4448.65 | 20518.43 | 0 | 60.06 | 7664.75 | 237
KY | KY - WEST | 2623 | 23026308601 |  | 500675130 |  | 6688224K | 2302127 | U126783 |  | 555 | EX | INSTALL 675'-2" PMMP | 2600B | DUNCAN | 690 DUNCAN RD | 073 | FRA | 2024-08-07 | U136251 | U126783 | 2024-06-04 | 2024-04-24 | 2024-05-30 | 2024-05-13 | RANDALL TINCHER | 2024-06-10 | 2024-04-30 | 2024-04-30 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP3086 |  |  | 100 | 055532230263086 | 86.8333 | 11539 | 91036.22 | 6129.33 | 2793.76 | 343.87 | 59280.53 | 0 | 361.56 | 22127.17 | 1049
KY | KY - WEST | 2621 | 24026343500 |  |  |  | 6720212I | 2406067 | U122858 |  | 561 | EX | INSTALL 25'-8" PMLP | 2600E | ELM TREE | ELM TREE LN | 067 | LEX | 2024-08-01 | U128132 | U122858 | 2024-05-21 | 2024-06-21 | 2024-06-30 | 2024-06-10 | DEREK PAYTON | 2024-06-10 | 2024-06-03 | 2024-06-03 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP3435 |  |  | 100 | 056132240263435 | 91.85 | 264 | 48462.2 | 6589.78 | 16183.65 | 1503.84 | 13578.69 | 0 | 242.41 | 10363.83 | 24
KY | KY - EAST | 2633 | 24026347600 |  |  |  | 7352156G | 2406504 | U122858 |  | 557 | EX | EMER - INSTALL 7'-2" PMIP | 2621P | MAIN | E MAIN ST | 071 | STA | 2024-09-14 | U128132 | U122858 | 2024-06-11 | 2024-06-10 | 2024-06-10 | 2024-06-10 | JAHOWARD | 2024-06-10 |  |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00557 | 3200557 |  |  | WP3476 |  |  | 100 | 055732240263476 |  | 7 | 6613.86 | 3485.07 | 0 | 218.19 | 1491 | 0 | 13.09 | 1406.51 | 7
KY | KY - WEST | 2623 | 22026235300 |  |  |  | 6712228F | 2293486 | U132703 |  | 557 | EX | INST 1865'-8" & 390'-2" PMMP | 2600B | OLD LEMONS MILL | 325 OLD LEMONS MILL | 209 | GEO | 2024-10-18 | U136251 | U132703 | 2022-11-09 | 2024-10-17 | 2024-12-31 | 2024-05-18 | JOSH PASLEY/TEAM FISHEL | 2024-06-11 | 2024-03-08 | 2024-03-15 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP2353 | AMRCB |  | 100 | 055732220262353 | 407.2333 | 112965 | 1121157.31 | 29416.55 | 33900.84 | 22869.99 | 767455.57 | 0 | 5197.6 | 262316.76 | 2215
KY | KY - WEST | 2621 | 23026302701 |  | 501340576 |  | 6716216C | 2301170 | U461383 |  | 555 | EX | INSTALL 2700' OF 2"/4"PMMP | 2600B | STOCKTON | 1952 STOCKTON WY | 067 | LEX | 2024-08-27 | U128132 | U461383 | 2024-06-06 | 2024-05-13 | 2024-07-01 | 2024-06-11 | DUSTIN DAVIS | 2024-06-12 | 2024-06-06 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3027 |  |  | 100 | 055532230263027 | 304.0833 | 101156 | 288308.66 | 23534.85 | 16105.13 | 5564.21 | 173556.74 | 0 | 2704.71 | 66843.02 | 2662
KY | KY - CENTRAL | 2629 | 24026310600 |  |  |  | 6740232N | 2402791 | U132703 |  | 559 | EX | INSTALL 2, 2" STOPPLE FITTINGS | 2600B | WOODMONT | 133 WOODMONT DR | 017 | PAR | 2024-08-10 | U128132 | U132703 | 2024-01-09 | 2025-12-23 | 2025-12-31 | 2024-06-13 | STEVE CANOY | 2024-06-17 | 2024-06-11 | 2024-06-12 | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00559 | 3200559 |  |  | WP3106 |  |  | 100 | 055932240263106 | 26.5 | 0 | 21866.79 | 2131.9 | 1725.5 | 1313.75 | 11689.65 | 0 | 117.54 | 4888.45
KY | KY - EAST | 2631 | 24026347300 |  |  |  | 7356256M | 2406473 | U122858 |  | 557 | EX | EMER - INSTALL 12'-3" PMIP | 2621P | TANGLEWOOD | TANGLEWOOD | 019 | ASH | 2024-06-28 | U132645 | U122858 | 2024-06-10 | 2025-02-24 |  | 2024-06-07 | MCOLLET | 2024-06-17 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP3473 |  |  | 100 | 055732240263473 | 0.93333 | 12 | 52750.04 | 8769.65 | 1463.11 | 8637.18 | 23052.68 | 0 | 89.06 | 10738.36 | 12
KY | KY - WEST | 2621 | 22026228500 |  |  |  | 6728208M | 2290202 | U122858 |  | 561 | EX | INSTALL 167'-2" PMMP | 2600B | CULZEAN | CULZEAN CT | 067 | LEX | 2024-07-11 | U132645 | U122858 | 2022-09-30 | 2024-06-14 | 2024-06-30 | 2024-06-20 | JOSHUA COX | 2024-06-20 | 2024-05-20 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP2285 |  |  | 100 | 056132220262285 | 114.5833 | 3612 | 84729.46 | 8237.67 | 850.59 | 474.3 | 59112.94 | 0 | 1053.21 | 15000.75 | 258
KY | KY - WEST | 2621 | 23026287600 |  |  |  | 6712212H | 2399333 | U126783 |  | 559 | EX | INSTALL 30'-4" PMMP | 2621P | OXFORD CIRCLE | 1918 OXFORD CIRCLE | 067 | LEX | 2025-05-05 | U132645 | U126783 | 2023-08-09 | 2023-12-27 | 2024-12-25 | 2024-05-08 | AWILLIAMSON | 2024-06-20 | 2024-05-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP2876 |  |  | 100 | 055932230262876 | 87.3167 | 22 | 19740.37 | 6369.63 | 1167.9 | 2810.9 | 4830.67 | 0 | 52.6 | 4508.67 | 2
KY | KY - WEST | 2621 | 24026348700 |  |  |  | 6716204D | 2406685 | U134275 |  | 557 | EX | EMER - INSTALL 5' OF 2" PMMP | 2621P | OVERBROOK FOUNTAIN | OVERBROOK FOUNTAIN | 067 | LEX | 2024-07-30 | U132645 | U134275 | 2024-06-20 | 2024-12-30 | 2024-12-31 | 2024-06-26 | RANDY CRAWFORD | 2024-06-26 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3487 |  |  | 100 | 055732240263487 |  | 5 | 8763.23 | 3205.95 | 0 | 168.94 | 3631.56 | 0 | 0 | 1756.78 | 5
KY | KY - WEST | 2621 | 23026296200 |  |  |  | 6716204F | 1963805 | U122858 |  | 561 | EX | INSTALL 1429'-6" PMMP | 2600B | WILSON DOWNING | WILSON DOWNING RD | 067 | LEX | 2024-10-22 | U128132 | U122858 | 2023-09-22 | 2024-01-15 | 2024-06-28 | 2024-06-28 | JAMIE ENSMINGER | 2024-06-28 | 2024-01-22 | 2024-02-01 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP2962 | AMRCB |  | 100 | 056132230262962 | 731.5667 | 167226 | 975067.42 | 49988.1 | 41071.85 | 8928.95 | 606190 | 0 | 17889.41 | 250999.11 | 1779
KY | KY - WEST | 2621 | 24026350500 |  |  |  | 6720204F | 2406959 | U461383 |  | 559 | EX | EMER-INSTALL 2"VALVE KY-C1586 | 2621P | CENTRE | 1333 CENTRE PY | 067 | LEX | 2024-12-19 | U136251 | U461383 | 2024-07-02 | 2024-09-30 | 2024-10-01 | 2024-07-01 | RCRAWFORD | 2024-07-01 | 2024-07-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP3505 |  |  | 100 | 055932240263505 | 4.05 | 10 | 3282.54 | 1830.44 | 566.61 | 199.73 | 0 | 0 | 7.32 | 678.44 | 5
KY | KY - EAST | 2631 | 24026349700 |  |  |  | 7348264F | 2406867 | U141016 |  | 557 | EX | EMER INSTALL 2' OF 2" PMMP | 2621P | LINWOOD | 907 LINWOOD ST | 089 | RAC | 2024-09-05 | U128132 | U141016 | 2024-07-01 | 2025-03-31 |  | 2024-06-19 | MCOLLET | 2024-07-03 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP3497 |  |  | 100 | 055732240263497 | 1 | 2 | 6054.03 | 1947.98 | 615.51 | 2293.56 | 0 | 0 | 0 | 1196.98 | 2
KY | KY - WEST | 2621 | 24026346300 |  |  |  | 6720212O | 2406391 | U461383 |  | 557 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | 2621P | ALEXANDRIA | 1809 ALEXANDRIA DR | 067 | LEX | 2024-07-18 | U132645 | U461383 | 2024-06-06 | 2024-09-30 | 2024-10-01 | 2024-06-06 | RSTRONG | 2024-07-05 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3463 |  |  | 100 | 055732240263463 | 0.11667 | 3 | 6040.26 | 3993.88 | 139.3 | 628.16 | 0 | 0 | 17.44 | 1261.48 | 3
KY | KY - WEST | 2621 | 24026348000 |  |  |  | 6720208L | 2406530 | U461383 |  | 557 | EX | EMER-INSTALL 4' OF 3"PMMP MAIN | 2621P | GRIBBON | GRIBBON DR | 067 | LEX | 2024-12-19 | U136251 | U461383 | 2024-06-12 | 2024-06-10 | 2024-09-28 | 2024-06-10 | TROE | 2024-07-08 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3480 |  |  | 100 | 055732240263480 | 1.35 | 12 | 2333.5 | 1544.83 | 203 | 93 | 0 | 0 | 6.5 | 486.17 | 4
KY | KY - CENTRAL | 2629 | 24026310800 |  | 501356021 |  | 7236212K | 2302559 | U134275 |  | 555 | EX | INSTALL 1400' OF 2" PMMP | 2600B | FOGG | 1929 FOGG PK | 173 | MT | 2024-07-18 | U128132 | U134275 | 2024-01-09 | 2024-08-29 | 2024-09-10 | 2024-07-09 | JOSHUA COX | 2024-07-10 | 2024-07-02 | 2024-06-28 | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP3108 |  |  | 100 | 055532240263108 | 51 | 8160 | 67204.19 | 2936.83 | 3825.43 | 198.95 | 46093.83 | 0 | 372.09 | 13777.06 | 1360
KY | KY - CENTRAL | 2629 | 24026349900 |  |  |  | 6744208I | 2406889 | U128885 |  | 557 | EX | EMER - INSTALL 3'-2" PMMP | 2621P | STRODE STATION | STRODE STATION | 049 | WIN | 2024-07-16 | U128132 | U128885 | 2024-07-02 | 2024-12-23 | 2024-12-31 | 2024-06-17 | NRICHIE | 2024-07-10 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3499 |  |  | 100 | 055732240263499 |  | 3 | 8029.62 | 2184.53 | 267.25 | 832.5 | 3165.55 | 0 | 0 | 1579.79 | 3
KY | KY - WEST | 2621 | 23026273700 |  |  |  | 6712204A | 2397428 | U461383 |  | 557 | EX | INSTALL 6' OF 2"PMMP MAIN | 2621P | CLEMONS | 4184 CLEMONS DR | 067 | LEX | 2024-08-16 | U136251 | U461383 | 2023-05-05 | 2024-07-11 | 2025-05-03 | 2024-06-19 | KKINDER | 2024-07-12 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2737 |  |  | 100 | 055732230262737 | 0.15 | 3 | 5850.76 | 9.03 | 395.49 | 0.62 | 4315.83 | 0 | 14.22 | 1115.57 | 3
KY | KY - WEST | 2621 | 23026254900 |  |  |  | 6716208C | 2395330 | U461383 |  | 561 | EX | INSTALL 620' OF 8"CSHP MAIN | 2600B | CONN TERRACE | CONN TERRACE ST | 067 | LEX | 2024-08-12 | U132645 | U461383 | 2023-02-01 | 2024-07-23 | 2024-10-01 | 2024-07-19 | DUSTIN DAVIS | 2024-07-19 | 2024-06-17 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP2549 |  |  | 100 | 056132230262549 | 336.3 | 27778 | 230200.58 | 23085.31 | 15831.49 | 6807.45 | 134253.76 | 0 | 11.08 | 50211.49 | 646
KY | KY - WEST | 2623 | 24026331601 |  |  |  | 6696212L | 2404300 | U132703 |  | 557 | EX | INSTALL 475' OF 2"PMMP MAIN | 2600B | HENTON | 226 HENTON CT | 239 | VER | 2025-04-23 | U128132 | U132703 | 2024-06-28 | 2025-04-15 | 2025-12-05 | 2024-06-18 | RTINCHER | 2024-07-22 |  | 2024-06-03 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP3316 | AMRCB |  | 100 | 055732240263316 | 157.4833 | 9240 | 142820.44 | 11134.02 | 3480.96 | 3029.11 | 92987.99 | 0 | 266.19 | 31922.17 | 440
KY | KY - WEST | 2621 | 24026351800 |  |  |  | 6716212K | 2407081 | U134275 |  | 557 | EX | EMER-INSTALL 8' OF 3" PMMP | 2621P | PINE | 720 PINE ST B | 067 | LEX | 2024-10-30 | U132645 | U134275 | 2024-07-10 | 2024-08-29 | 2024-08-30 | 2024-07-25 | RJCRAWF | 2024-07-26 |  | 2024-07-10 | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3518 |  |  | 100 | 055732240263518 | 0.066667 | 16 | 6274.49 | 4612.13 | 98.49 | 312.33 | 0 | 0 | 17.78 | 1233.76 | 8
KY | KY - WEST | 2621 | 24026342400 |  |  |  | 6712208N | 2405849 | U122858 |  | 561 | EX | INSTALL ~585'-2" PMMP | 2600E | FOUNTAINBLUE | 3855 FOUNTAINBLUE LN | 067 | LEX | 2024-08-21 | U128132 | U122858 | 2024-05-10 | 2024-07-17 | 2024-07-30 | 2024-07-25 | JOSHUA COX | 2024-07-30 | 2024-07-11 | 2024-07-15 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP3424 |  |  | 100 | 056132240263424 | 109.8167 | 11102 | 81606.34 | 6330.67 | 3345.33 | 861.53 | 53794.21 | 0 | 0 | 17274.6 | 793
KY | KY - CENTRAL | 2632 | 24026351600 |  |  |  | 7256280P | 2407065 | U122858 |  | 557 | EX | EMER - INSTALL 2'-2" PMMP | 2621P | 2ND | 203 E 2ND ST | 161 | MAY | 2024-08-21 | U128132 | U122858 | 2024-07-10 | 2025-03-28 | 2025-03-31 | 2024-06-17 | TALLISON | 2024-07-30 |  |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00557 | 3200557 |  |  | WP3516 |  |  | 100 | 055732240263516 |  | 2 | 2939.49 | 2171.02 | 52.74 | 134.29 | 0 | 0 | 0 | 581.44 | 2
KY | KY - WEST | 2621 | 24026351400 |  |  |  | 6724212J | 2407044 | U122858 |  | 557 | EX | EMER - INSTALL 2'-2" PMMP | 2621P | EXECUTIVE | 2233 EXECUTIVE | 067 | LEX | 2024-11-01 | U136251 | U122858 | 2024-07-09 | 2025-03-31 | 2025-03-31 | 2024-07-31 | TROE | 2024-07-31 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3514 |  |  | 100 | 055732240263514 | 0.25 | 6 | 1846.55 | 1266.98 | 130.85 | 75.94 | 0 | 0 | 4.94 | 367.84 | 2
KY | KY - WEST | 2621 | 23026288401 |  | 501352417 |  | 6720216A | 2399299 | U461383 |  | 555 | EX | INSTALL 5500' OF 4"PMMP MAIN | 2600B | PROVIDENCE PL | 1021 PROVIDENCE PL PY | 067 | LEX | 2024-09-06 | U132645 | U461383 | 2024-07-23 | 2024-02-12 | 2024-08-16 | 2024-08-01 | LESLIE SHARON | 2024-08-01 | 2024-07-25 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2884 |  |  | 100 | 055532230262884 | 297.9667 | 242864 | 294615.62 | 18161.62 | 26531.56 | 6460.03 | 170524.98 | 0 | 3154.34 | 69783.09 | 5648
KY | KY - CENTRAL | 2632 | 24026352800 |  |  |  | 7260280N | 2407169 | U122858 |  | 557 | EX | INSTALL SS FITTING | 2621P | MAIN | MAIN ST | 161 | MAY | 2024-08-21 | U128132 | U122858 | 2024-07-16 | 2024-08-01 | 2024-08-05 | 2024-07-30 | TYLER ALLISON | 2024-08-01 | 2024-07-29 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00557 | 3200557 |  |  | WP3528 |  |  | 100 | 055732240263528 | 30.8333 | 0 | 5512.14 | 2542.33 | 1373.55 | 419.71 | 0 | 0 | 11.05 | 1165.5
KY | KY - CENTRAL | 2629 | 24026353200 |  |  |  | 7240216J | 2407193 | U128885 |  | 557 | EX | EMER - INSTALL 3'-4" PMMP | 2621P | GARDEN SPRINGS | GARDEN SPRINGS | 173 | MT | 2024-08-12 | U128132 | U128885 | 2024-07-16 | 2025-03-25 | 2025-03-31 | 2024-07-01 | WDENNING | 2024-08-01 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3532 |  |  | 100 | 055732240263532 |  | 3 | 3109.71 | 2192.29 | 72.34 | 148.55 | 99.16 | 0 | 8.72 | 588.65 | 3
KY | KY - WEST | 2621 | 24026354900 |  |  |  | 6720208A | 2286912 | U461383 |  | 559 | EX | PAPER ONLY-LP STOPPLE FITTINGS | 2600B | ASHLAND | ASHLAND TR | 067 | LEX | 2024-11-15 | U128132 | U461383 | 2024-08-02 | 2024-10-01 | 2024-10-01 | 2024-05-22 | OFFICE | 2024-08-02 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP3549 | AMRCB |  | 100 | 055932240263549 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026339800 |  |  |  | 6712212P | 2405285 | U461383 |  | 557 | EX | INSTALL 35' OF 6"PMLP MAIN | 2621P | GETTYSBURG | 1800 GETTYSBURG RD | 067 | LEX | 2024-09-04 | U132645 | U461383 | 2024-04-18 | 2024-09-27 | 2024-10-01 | 2024-07-25 | KKINDER | 2024-08-06 | 2024-07-12 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3398 | AMRCB |  | 100 | 055732240263398 | 112.8 | 896 | 43718.9 | 6166.57 | 4318.01 | 2073.4 | 20585.1 | 0 | 104.04 | 10471.78 | 56
KY | KY - WEST | 2621 | 24026352600 |  |  |  | 6716216M | 2407141 | U134275 |  | 557 | EX | EMER - INSTALL 2'-2" PMMP | 2621P | OLD LEESTOWN | 1649 OLD LEESTOWN RD | 067 | LEX | 2024-09-25 | U132645 | U134275 | 2024-07-15 | 2024-08-14 | 2024-08-15 | 2024-07-08 | KKINDER | 2024-08-06 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3526 |  |  | 100 | 055732240263526 | 0.21667 | 3 | 1939.02 | 1454.97 | 0 | 98.3 | 0 | 0 | 5.55 | 380.2 | 3
KY | KY - EAST | 2631 | 24026354400 |  |  |  | 7356256A | 2075304 | U128885 |  | 561 | EX | INSTALL 20'-4" PMLP | 2600B | PROSPECT | PROSPECT AV | 019 | ASH | 2025-02-13 | U128132 | U128885 | 2024-07-30 | 2024-12-31 | 2024-12-31 | 2024-08-05 | DAVID SKAGGS/CJH JOSEPH | 2024-08-07 | 2024-12-14 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00561 | 3200561 |  |  | WP3544 |  |  | 100 | 056132240263544 | 0.016667 | 116 | 287.45 | 1.76 | 236.06 | 0.11 | 0 | 0 | 0 | 49.52 | 58
KY | KY - CENTRAL | 2629 | 23026303400 |  |  |  | 6736180D | 2182441 | U128885 |  | 559 | EX | INSTALL 20'-2" CSHP | 2600B | MILLER | MILLER DR | 151 | RIC | 2025-01-27 | U128132 | U128885 | 2023-10-27 | 2024-12-02 | 2024-12-15 | 2024-07-30 | SHAWN DENNIS | 2024-08-12 | 2023-12-13 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00559 | 3200559 |  |  | WP3034 |  |  | 100 | 055932230263034 | 520.8333 | 1950 | 212847.86 | 36863.67 | 20358.21 | 6085.21 | 89181.2 | 0 | 6886.66 | 53472.91 | 30
KY | KY - CENTRAL | 2629 | 24026362300 |  |  |  | 6736180D | 2182441 | U128885 |  | 559 | EX | INSTALL 2" SS | 2600B | MILLER | MILLER DR | 151 | RIC | 2025-01-27 | U128132 | U128885 | 2024-09-25 | 2024-12-13 | 2024-12-15 | 2024-07-30 | SHAWN DENNIS | 2024-08-12 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00559 | 3200559 |  |  | WP3623 |  |  | 100 | 055932240263623 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24026357700 |  |  |  | 6696212D | 2407916 | U461383 |  | 557 | EX | EMER-INSTALL 2' OF 3"PMMP MAIN | 2621P | CHESTNUT | 335 CHESTNUT LN | 239 | VER | 2025-01-13 | U136251 | U461383 | 2024-08-16 | 2025-10-28 | 2026-06-27 | 2024-08-15 | CDESPAIN | 2024-08-23 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP3577 |  |  | 100 | 055732240263577 | 8 | 2 | 13806.96 | 7834.24 | 321.44 | 559.44 | 1666 | 0 | 33.11 | 3392.73 | 2
KY | KY - WEST | 2621 | 24026354000 |  | 501347882 |  | 6724204A | 2407250 | U461383 |  | 555 | EX | INSTALL 850' OF 2"PMMP MAIN | 2600B | DOCKSIDE | 700 DOCKSIDE PK LT54C | 067 | LEX | 2024-08-29 | U132645 | U461383 | 2024-07-18 | 2024-10-14 | 2024-10-18 | 2024-08-26 | LESLIE SHARON | 2024-08-26 | 2024-08-20 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3540 |  |  | 100 | 055532240263540 | 38.5 | 3276 | 61100.31 | 7579.66 | 4895.49 | 3710.41 | 32663.63 | 0 | 77.31 | 12173.81 | 546
KY | KY - WEST | 2621 | 24026355400 |  |  |  | 6720216I | 2407662 | U461383 |  | 557 | EX | EMER-INSTALL 2' OF 2"PMMP MAIN | 2621P | VAN BUREN | 1567 VAN BUREN | 067 | LEX | 2024-09-17 | U132645 | U461383 | 2024-08-06 | 2025-10-31 | 2026-06-11 | 2024-08-09 | TROE | 2024-08-28 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3554 |  |  | 100 | 055732240263554 | 0.4 | 4 | 4651.3 | 2917.33 | 446 | 147.69 | 0 | 0 | 13.47 | 1126.81 | 2
KY | KY - WEST | 2621 | 24026346600 |  |  |  | 6720212B | 2406415 | U461383 |  | 557 | EX | EMER-INSTALL 8' OF 4"PMLP | 2621P | LOCUST | 307 LOCUST AV | 067 | LEX | 2024-10-30 | U136251 | U461383 | 2024-06-06 | 2024-09-26 | 2024-09-28 | 2024-06-06 | KKINDER | 2024-08-29 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3466 |  |  | 100 | 055732240263466 | 0.25 | 8 | 6502.78 | 4410.1 | 336.17 | 383.38 | 0 | 0 | 18.64 | 1354.49 | 8
KY | KY - WEST | 2621 | 24026353800 |  |  |  | 6716204B | 2407257 | U461383 |  | 557 | EX | INSTALL 180' OF 4"PMMP MAIN | 2600B | NICHOLASVILLE | 3385 NICHOLASVILLE RD | 067 | LEX | 2024-09-18 | U128132 | U461383 | 2024-07-18 | 2024-09-25 | 2025-04-19 | 2024-08-29 | JOSHUA COX | 2024-08-30 | 2024-08-08 | 2024-08-12 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3538 |  |  | 100 | 055732240263538 | 161.9667 | 4020 | 167555.7 | 15805.88 | 7451.26 | 2732.66 | 101506.99 | 0 | 317.24 | 39741.67 | 201
KY | KY - EAST | 2631 | 24026356500 |  |  |  | 7344264B | 2407759 | U122858 |  | 557 | EX | EMER - INSTALL 2'-2" PMIP | 2621P | MONROE | 802 MONROE ST | 089 | WUR | 2024-09-21 | U128132 | U122858 | 2024-08-12 | 2024-08-29 | 2024-09-01 | 2024-08-07 | CWHEELE | 2024-09-04 | 2024-09-03 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP3565 |  |  | 100 | 055732240263565 | 3.1 | 6 | 4865.71 | 2508.8 | 101.58 | 987.48 | 87.32 | 0 | 12.32 | 1168.21 | 2
KY | KY - WEST | 2623 | 24026360200 |  |  |  | 6696212H | 2408530 | U461383 |  | 557 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | 2621P | FRANKFORT | FRANKFORT ST | 239 | VER | 2024-12-23 | U136251 | U461383 | 2024-09-10 | 2024-08-21 | 2024-09-03 | 2024-09-04 | CDESPAIN | 2024-09-04 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP3602 |  |  | 100 | 055732240263602 |  | 3 | 12791.75 | 5941.59 | 62.21 | 706.5 | 2950 | 0 | 26.42 | 3105.03 | 3
KY | KY - WEST | 2621 | 24026341900 |  | 501365269 |  | 6728212M | 2405655 | U461383 |  | 555 | EX | INSTALL 4250' OF 2"/4"PMMP | 2600B | BLACKFORD | BLACKFORD PY LT1 | 067 | LEX | 2024-09-23 | U128132 | U461383 | 2024-05-02 | 2024-08-26 | 2024-09-30 | 2024-09-06 | DUSTIN DAVIS | 2024-09-06 | 2024-07-25 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3419 |  |  | 100 | 055532240263419 | 232.5 | 140340 | 160153.35 | 16289.63 | 14622.07 | 6430.9 | 85858.52 | 0 | 1554.37 | 35397.86 | 4678
KY | KY - WEST | 2621 | 24026357000 |  |  |  | 6720208G | 2407867 | U461383 |  | 557 | EX | EMER-INSTALL 50' OF 4"PMLP | 2621P | SAINT ANN | 137 SAINT ANN DR | 067 | LEX | 2024-10-22 | U136251 | U461383 | 2024-08-14 | 2025-11-24 | 2026-07-13 | 2024-09-10 | RJCRAWF | 2024-09-10 | 2024-09-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3570 | AMRCB |  | 100 | 055732240263570 | 46 | 300 | 19570.62 | 6114.31 | 5569 | 881.08 | 2173.43 | 0 | 94.63 | 4738.17 | 50
KY | KY - EAST | 2633 | 24026333600 |  | 501028114 |  | 7356152E | 2404396 | U122858 |  | 555 | EX | INSTALL 75'-2" PMIP | 2600B | CHERRY | 111 CHERRY ST | 071 | HAR | 2024-10-11 | U128132 | U122858 | 2024-03-14 | 2024-09-19 | 2024-09-20 | 2024-09-11 | MBLANKE/CJH J HIERONIMUS | 2024-09-12 | 2024-09-09 | 2024-09-09 | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00555 | 3200555 |  |  | WP3336 |  |  | 100 | 055532240263336 | 12.55 | 166 | 28387.83 | 869.61 | 1162.08 | 143.56 | 18824.27 | 0 | 63.22 | 7325.09 | 83
KY | KY - WEST | 2621 | 22026165501 |  |  |  | 6716208G | 2286440 | U134275 |  | 557 | EX | INSTALL 3385' OF 2" PMMP | 2600B | CHEROKEE | CHEROKEE PK | 067 | LEX | 2024-10-17 | U128132 | U134275 | 2024-09-12 | 2024-01-22 | 2024-12-31 | 2024-06-19 | JPASLEY | 2024-09-13 | 2024-05-17 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP1655 | AMRCB |  | 100 | 055732220261655 | 119.6333 | 56712 | 347952.13 | 7525.87 | 8204.75 | 4302.81 | 249702.15 | 0 | 1645.51 | 76571.04 | 3336
KY | KY - WEST | 2621 | 24026351200 |  | 501312434 |  | 6712212I | 2407033 | U461383 |  | 555 | EX | INSTALL 150' OF 2"PMIP MAIN | 2600B | WINNERS | 1600 WINNERS CR LT40 | 067 | LEX | 2024-09-23 | U132645 | U461383 | 2024-07-09 | 2024-09-26 | 2024-09-27 | 2024-09-12 | JOSHUA COX | 2024-09-13 | 2024-09-10 | 2024-09-10 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3512 |  |  | 100 | 055532240263512 | 32 | 468 | 14499.2 | 2162.28 | 1054.57 | 123.36 | 7408.03 | 0 | 56.14 | 3694.82 | 117
KY | KY - WEST | 2621 | 22026224201 |  |  |  | 6716212P | 2291708 | U461383 |  | 557 | EX | INSTALL 2300' OF 2"/4"PMMP | 2600B | COLUMBIA | 321 COLUMBIA AV | 067 | LEX | 2024-11-01 | U128132 | U461383 | 2024-09-03 | 2024-09-05 | 2024-12-31 | 2024-09-06 | DEREK PAYTON | 2024-09-16 | 2024-09-06 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2242 | AMRCB |  | 100 | 055732220262242 | 626.5 | 180357 | 588766.29 | 42413.78 | 17138.41 | 10968.54 | 382843.68 | 0 | 6363.9 | 129037.98 | 2283
KY | KY - WEST | 2623 | 24026362000 |  |  |  | 6696212D | 2408757 | U461383 |  | 557 | EX | EMER-INSTALL 3' OF 3"PMMP MAIN | 2621P | CHESTNUT | 211 CHESTNUT LN | 239 | VER | 2025-02-12 | U136251 | U461383 | 2024-09-19 | 2025-10-31 | 2026-06-27 | 2024-09-17 | CDESPAIN | 2024-09-17 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP3620 |  |  | 100 | 055732240263620 |  | 3 | 18283.02 | 6279.54 | 120.86 | 1748.84 | 5298.9 | 0 | 58.57 | 4776.31 | 3
KY | KY - WEST | 2623 | 24026355300 |  | 501368702 |  | 6712232L | 2407579 | U126783 |  | 555 | EX | INSTALL 250'-2" PMMP | 2600B | FINANCIAL | 101 FINANCIAL WY | 209 | GEO | 2025-01-15 | U136251 | U126783 | 2024-08-06 | 2024-09-23 | 2024-09-30 | 2024-09-18 | DUSTIN DAVIS | 2024-09-18 | 2024-09-10 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP3553 |  |  | 100 | 055532240263553 | 48 | 1074 | 24464.47 | 3234.18 | 1523.85 | 1196.28 | 12075.68 | 0 | 58.25 | 6376.23 | 179
KY | KY - WEST | 2621 | 22026231301 |  |  |  | 6720212M | 2292814 | U461383 |  | 557 | EX | INSTALL 925' OF 2"PMMP MAIN | 2600B | HIGH | 626 E HIGH ST | 067 | LEX | 2024-12-11 | U128132 | U461383 | 2024-11-20 | 2024-11-11 | 2024-12-31 | 2024-09-10 | RANDALL HUMPHREYS | 2024-09-20 | 2024-06-11 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2313 | AMRCB |  | 100 | 055732220262313 | 246.8833 | 30168 | 388671.62 | 15375.78 | 7400.57 | 11263.48 | 263920.31 | 0 | 2049.43 | 88662.05 | 838
KY | KY - CENTRAL | 2632 | 23026287300 |  |  |  | 7256276A | 2398923 | U122858 |  | 561 | EX | INSTALL 121'-4" CSMP | 2600B | ALGONQUIN | ALGONQUIN DR E | 161 | MAY | 2025-05-01 | U132645 | U122858 | 2023-08-07 | 2024-03-08 | 2024-12-30 | 2024-09-16 | EDWARD FOX | 2024-09-20 | 2024-08-23 |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00561 | 3200561 |  |  | WP2873 |  |  | 100 | 056132230262873 | 159.5333 | 3948 | 188332.63 | 11340.25 | 36132.73 | 2901.23 | 91738.76 | 0 | 1571.06 | 44648.6 | 188
KY | KY - WEST | 2621 | 24026356200 |  |  |  | 6720200A | 2407712 | U461383 |  | 557 | EX | INSTALL NEW 4" CRITICAL VALVE | 2621P | HARTLAND | 4999 HARTLAND PY | 067 | LEX | 2024-10-24 | U132645 | U461383 | 2024-08-08 | 2024-10-14 | 2026-04-16 | 2024-09-19 | MCRAIG | 2024-09-20 | 2024-09-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3562 |  |  | 100 | 055732240263562 | 10.3833 | 6 | 6237.92 | 1829.07 | 1396.83 | 383.4 | 1096.84 | 0 | 23.41 | 1508.37 | 2
KY | KY - WEST | 2621 | 23026270600 |  | 501202041 |  | 6712208M | 2396687 | U134275 |  | 555 | EX | INSTALL 550' OF 2" PMMP | 2600B | MERRIDEW | 3833 MERRIDEW WY | 067 | LEX | 2024-10-04 | U128132 | U134275 | 2023-04-04 | 2024-10-02 | 2024-10-11 | 2024-09-26 | STEVE CANOY | 2024-09-26 | 2024-09-18 | 2024-09-20 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2706 |  |  | 100 | 055532230262706 | 79.6833 | 5300 | 43345.7 | 5273.65 | 821.42 | 5512.35 | 20569.45 | 0 | 112.86 | 11055.97 | 530
KY | KY - CENTRAL | 2629 | 24026361500 |  |  |  | 6744208I | 2408727 | U128885 |  | 557 | EX | EMER - INSTALL 2'-3" PMLP | 2621P | MARKET | MARKET | 049 | WIN | 2024-10-09 | U128132 | U128885 | 2024-09-18 | 2024-09-27 | 2024-09-30 | 2024-09-12 | NRICHIE | 2024-09-27 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3615 |  |  | 100 | 055732240263615 |  | 2 | 4884.17 | 1186.53 | 571.44 | 506.27 | 1467.44 | 0 | 8.61 | 1143.88 | 2
KY | KY - WEST | 2621 | 24026349300 |  |  |  | 6724208J | 2406339 | U461383 |  | 559 | EX | INSTALL 4"POLY VALVE KY-C1556 | 2600B | OLD TODDS | 3005 OLD TODDS RD | 067 | LEX | 2024-10-11 | U128132 | U461383 | 2024-06-27 | 2025-05-28 | 2025-06-01 | 2024-09-26 | JOSHUA COX | 2024-10-02 | 2024-09-23 | 2024-09-23 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP3493 |  |  | 100 | 055932240263493 | 44.1667 | 28 | 22343.49 | 4426.84 | 2284.93 | 1005.99 | 9153.18 | 0 | 42.51 | 5430.04 | 4
KY | KY - EAST | 2631 | 24026348900 |  |  |  | 7356256C | 2406689 | U122858 |  | 561 | EX | INSTALL 70'-8" PMMP | 2600B | GREENUP | GREENUP AV | 019 | ASH | 2024-10-29 | U128132 | U122858 | 2024-06-20 | 2024-10-10 | 2024-10-30 | 2024-10-04 | CJH CASEY PACK/M BLANKENSHIP | 2024-10-07 | 2024-07-15 | 2024-07-15 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00561 | 3200561 |  |  | WP3489 |  |  | 100 | 056132240263489 | 110.1833 | 2261 | 110389.69 | 9610.57 | 23925.88 | 3094.99 | 50507.26 | 0 | 1694.2 | 21556.79 | 119
KY | KY - EAST | 2631 | 24026367000 |  |  |  | 7356256A | 2409784 | U122858 |  | 557 | EX | EMER INSTALL 5'-2" PMMP | 2600E | CHESTNUT | 1511 CHESTNUT DR | 019 | ASH | 2025-03-24 | U132645 | U122858 | 2024-10-28 | 2024-10-09 | 2024-10-10 | 2024-10-11 | R CUMPSTON | 2024-10-11 | 2024-11-13 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP3670 |  |  | 100 | 055732240263670 | 36.5 | 45 | 7909.41 | 4847.43 | 379.1 | 950.89 | 22.2 | 0 | 6.25 | 1703.54 | 5
KY | KY - WEST | 2623 | 22026236901 |  |  |  | 6712228C | 2293665 | U132703 |  | 557 | EX | INSTALL 11300'-2" PMMP | 2600B | CLAYTON | CLAYTON | 209 | GEO | 2024-12-16 | U128132 | U132703 | 2024-09-10 | 2024-01-15 | 2024-12-31 | 2024-08-28 | WILLIAM GRAVES | 2024-10-21 | 2024-09-24 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP2369 | AMRCB |  | 100 | 055732220262369 | 1828.7833 | 2695585 | 2626590.92 | 120763.05 | 33133.93 | 33406.17 | 1819455.41 | 0 | 34581.37 | 585250.99 | 11185
KY | KY - CENTRAL | 2632 | 24026357400 |  |  |  | 7260280O | 2407133 | U122858 |  | 561 | EX | INSTALL 275'-3" CSMP | 2600B | RIVER | RIVER DR | 161 | MAY | 2025-01-24 | U128132 | U122858 | 2024-08-15 | 2024-10-17 | 2024-10-30 | 2024-10-21 | EDWARD FOX | 2024-10-24 | 2024-10-04 |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00561 | 3200561 |  |  | WP3574 |  |  | 100 | 056132240263574 | 150.9667 | 5548 | 104472.75 | 10177.67 | 15225.72 | 10919.53 | 43774.78 | 0 | 301.74 | 24073.31 | 292
KY | KY - EAST | 2631 | 22026207100 |  |  |  | 7352256H | 2289651 | U938437 |  | 557 | EX | INSTALL 7870'-2", 4" PMMP | 2600B | VIRGINIA | VIRGINIA | 019 | ASH | 2025-05-02 | U128132 | U132280 | 2022-06-21 | 2024-01-02 | 2025-08-15 | 2024-06-27 | M BLANKENSHIP/CJH C PACK | 2024-10-28 | 2024-01-02 | 2024-01-02 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP2071 | AMRCB |  | 100 | 055732220262071 | 1292.3667 | 1447780 | 1549123.72 | 96735.66 | 44479.86 | 16152.09 | 1001830.71 | 0 | 14496.31 | 375429.09 | 7580
KY | KY - EAST | 2631 | 23026283600 |  |  |  | 7352256H | 2289651 | U938437 |  | 557 | EX | INSTALL LP FITTINGS | 2600B | VIRGINIA | VIRGINIA AV | 019 | ASH | 2024-12-10 | U128132 | U938437 | 2023-07-10 | 2024-12-31 | 2024-12-31 | 2024-10-15 | CJH C PACK/M BLANKENSHIP | 2024-10-28 | 2024-01-02 | 2024-08-22 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP2836 | AMRCB |  | 100 | 055732230262836 | 2.0167 | 0 | 9658.7 | 133.85 | 3117.52 | 11.46 | 4032.78 | 0 | 79.82 | 2283.27
KY | KY - WEST | 2621 | 24026360500 |  |  |  | 6716216M | 2395080 | U122858 |  | 561 | EX | INSTALL 18'-2" PMMP | 2621P | FORBES | N FORBES RD | 067 | LEX | 2025-02-04 | U132645 | U122858 | 2024-09-13 | 2024-11-22 | 2024-11-30 | 2024-10-29 | MCRAIG | 2024-10-29 | 2024-10-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP3605 |  |  | 100 | 056132240263605 | 86.8 | 280 | 10627.85 | 4913.98 | 0 | -129.9 | 3668.15 | 0 | 22.57 | 2153.05 | 20
KY | KY - WEST | 2621 | 24026365000 |  |  |  | 6712208N | 2409284 | U134275 |  | 557 | EX | EMER-INSTALL 10' - 2" PMMP | 2621P | FOUNTAINBLUE | FOUNTAINBLUE LN | 067 | LEX | 2025-03-03 | U136251 | U134275 | 2024-10-09 | 2024-12-30 | 2024-12-31 | 2024-09-03 | MCRAIG | 2024-10-30 | 2024-10-29 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3650 |  |  | 100 | 055732240263650 | 1.6 | 30 | 3040.57 | 1939.06 | 81.82 | 425.2 | 0 | 0 | 0.49 | 594 | 10
KY | KY - WEST | 2621 | 21026152101 |  |  |  | 6716212N | 2075431 | U461383 |  | 557 | EX | INSTALL 535' OF 8"CSHP MAIN | 2600B | ADDISON | 629 ADDISON AV | 067 | LEX | 2024-12-05 | U132645 | U461383 | 2024-08-26 | 2025-12-02 | 2025-12-31 | 2024-10-29 | DDAVIS | 2024-10-31 | 2024-09-20 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP1521 | AMRCB |  | 100 | 055732210261521 | 356.9833 | 23268 | 480960.85 | 26006.06 | 62699.05 | 23775.4 | 252773.35 | 0 | 4902.8 | 110804.19 | 554
KY | KY - WEST | 2621 | 24026355900 |  | 501369361 |  | 6720204C | 2407692 | U461383 |  | 555 | EX | INSTALL 250' OF 2"PMMP MAIN | 2600B | CARRIAGE | 3216 CARRIAGE LN | 067 | LEX | 2025-05-20 | U132645 | U461383 | 2024-08-07 | 2024-11-18 | 2024-11-21 | 2024-10-17 | RANDALL HUMPHREYS | 2024-10-31 | 2024-10-07 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3559 |  |  | 100 | 055532240263559 | 63 | 2780 | 56306.29 | 3722.72 | 1431.29 | 3106.81 | 36864.25 | 0 | 156.57 | 11024.65 | 278
KY | KY - EAST | 2631 | 23026300300 |  | 501168502 |  | 7356216C | 2300812 | U122858 |  | 555 | EX | INSTALL 1810'-2" PMMP | 2600B | TOWN HILL | TOWN HILL RD | 127 | LOU | 2025-01-09 | U128132 | U122858 | 2023-10-13 | 2024-08-23 | 2024-09-20 | 2024-11-11 | M BLANKENSHIP/CJH CSAEY PACK | 2024-11-14 | 2024-10-17 | 2024-10-18 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP3003 |  |  | 100 | 055532230263003 | 50.2 | 18546 | 217275.5 | 3804.65 | 4535.42 | 793.92 | 159965.21 | 0 | 0 | 48176.3 | 1686
KY | KY - EAST | 2631 | 24026324100 |  | 100253182 |  | 7352256G | 2403829 | U122858 |  | 555 | EX | INSTALL 670'-2' PMIP | 2621P | OLYMPIC | 137 OLYMPIC DR | 019 | ASH | 2025-03-07 | U128132 | U122858 | 2024-02-19 | 2024-08-15 | 2024-10-10 | 2024-08-01 | MCOLLET | 2024-11-14 | 2024-07-12 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP3241 |  |  | 100 | 055532240263241 | 175.7333 | 19712 | 91180.5 | 12191.3 | 385.18 | 10579.19 | 47184.54 | 0 | 65.98 | 20774.31 | 704
KY | KY - CENTRAL | 2629 | 18026795501 |  |  |  | 6736248A | 1855582 | U128885 |  | 557 | EX | INSTALL 14,600'-2,4,6,8" PMMP | 2600B | MOY FOO | MOY FOO AL | 097 | CYN | 2025-03-07 | U128132 | U128885 | 2024-10-30 | 2022-11-28 | 2024-11-08 | 2024-10-15 | JPASLEY | 2024-11-15 | 2024-01-05 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP7955 | AMRCB |  | 100 | 055732180267955 | 1501.8167 | 2705912 | 3426043.78 | 106926.76 | 96759.65 | 32402.07 | 2314415.69 | 0 | 80451.23 | 795088.38 | 13948
KY | KY - CENTRAL | 2629 | 22026161800 |  |  |  | 6736248A | 1855582 | U128885 |  | 557 | EX | INSTALL 8" PCF | 2600B | MOY FOO | MOY FOO AL | 097 | CYN | 2025-01-03 | U128132 | U128885 | 2022-01-20 | 2024-01-08 | 2024-12-31 | 2024-10-28 | JPASLEY | 2024-11-15 | 2024-07-30 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP1618 | AMRCB |  | 100 | 055732220261618 | 25.6333 | 0 | 29544.9 | 1592.53 | 4801.94 | 529.43 | 20548.32 | 0 | 26.6 | 2046.08
KY | KY - WEST | 2621 | 24026363600 |  |  |  | 6720212D | 2409175 | U461383 |  | 557 | EX | INSTALL 620' OF 4"PMMP MAIN | 2600B | EASTIN | EASTIN RD | 067 | LEX | 2024-12-05 | U132645 | U461383 | 2024-10-07 | 2024-12-02 | 2024-12-31 | 2024-11-08 | DEREK PAYTON | 2024-11-19 | 2024-10-22 | 2024-10-22 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3636 | AMRCB |  | 100 | 055732240263636 | 329.3167 | 24552 | 275193.6 | 23804.19 | 6476.44 | 2510.56 | 185729.43 | 0 | 762.88 | 55910.1 | 682
KY | KY - WEST | 2623 | 24026340800 |  |  |  | 6712232O | 2405445 | U126783 |  | 557 | CO | EMER - INSTALL 15'-2" PMMP | 2621P | HAMILTON | 523 N HAMILTON ST | 209 | GEO | 2024-11-21 |  | U126783 | 2024-04-24 | 2024-04-29 | 2025-03-01 |  | D COLLINS | 2024-11-21 | 2024-11-20 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP3408 |  |  | 100 | 055732240263408 | 4.4833 | 0 | 15710.76 | 5891.24 | 0 | 1354.63 | 4410.9 | 0 | 501.84 | 3552.15
KY | KY - CENTRAL | 2629 | 24026358600 |  |  |  | 6744208P | 2407925 | U128885 |  | 561 | EX | INSTALL 175' - 4" PMMP | 2600B | CHURCH | S CHURCH AL | 049 | WIN | 2025-01-09 | U128132 | U128885 | 2024-08-19 | 2024-10-24 | 2024-12-31 | 2024-11-26 | DUSTIN DAVIS | 2024-12-02 | 2024-11-20 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00561 | 3200561 |  |  | WP3586 |  |  | 100 | 056132240263586 | 94.5 | 2340 | 90409.34 | 7614.31 | 1596.11 | 1459.15 | 60143.02 | 0 | 109.77 | 19486.98 | 195
KY | KY - WEST | 2623 | 22026238401 |  |  |  | 6700224L | 2293724 | U122858 |  | 557 | EX | INSTALL 5765'-2" PMMP | 2600B | WINTER | WINTER | 239 | MID | 2025-03-06 | U136251 | U122858 | 2023-11-28 |  | 2049-12-31 | 2024-03-20 | OLIVER MAYNARD | 2024-12-03 | 2024-03-19 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP2384 | AMRCB |  | 100 | 055732220262384 | 1384.1833 | 1197228 | 1422160.57 | 92178.27 | 78302.72 | 15549.79 | 899600.15 | 0 | 730.83 | 335798.81 | 6764
KY | KY - CENTRAL | 2629 | 24026368000 |  |  |  | 7240204J | 2410061 | U122858 |  | 557 | EX | EMER - INSTALL 5'-2" PMMP | 2621P | LEVEE | 6845 LEVEE RD | 173 | JEF | 2025-01-07 | U128132 | U122858 | 2024-11-07 | 2024-11-01 | 2024-11-01 | 2024-11-02 | WDENNING | 2024-12-09 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3680 |  |  | 100 | 055732240263680 |  | 6 | 4545.67 | 3257.63 | 0 | 198.36 | 23.68 | 0 | 13.09 | 1052.91 | 6
KY | KY - WEST | 2623 | 24026313000 |  |  |  | 6712232N | 2403101 | U132703 |  | 557 | EX | INSTALL 1570'-2" PMMP | 2600B | JEFFERSON | 124 JEFFERSON | 209 | GEO | 2025-01-29 | U136251 | U132703 | 2024-01-23 | 2025-08-19 | 2025-09-30 | 2024-11-22 | WILLIAM GRAVES | 2024-12-10 | 2024-10-26 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP3130 | AMRCB |  | 100 | 055732240263130 | 308.1167 | 56990 | 502657.55 | 22425.19 | 4319.95 | 5422.84 | 361278.77 | 0 | 826.08 | 108384.72 | 1390
KY | KY - WEST | 2621 | 24026375200 |  |  |  | 6716216P | 2410970 | U461383 |  | 557 | EX | EMER-INSTALL 6' OF 2"PMMP MAIN | 2621P | ADCOLOR | ADCOLOR DR | 067 | LEX | 2025-06-10 | U132645 | U461383 | 2024-12-12 | 2025-08-29 |  | 2024-12-11 | L STANFIELD | 2024-12-11 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3752 |  |  | 100 | 055732240263752 |  | 6 | 6850.53 | 3673.83 | 285.03 | 1532.08 | 105.08 | 0 | 22.85 | 1231.66 | 6
KY | KY - WEST | 2621 | 24026316701 |  |  |  | 6720208G | 2403558 | U461383 |  | 557 | EX | INSTALL 11245' OF 2"PMMP MAIN | 2600B | SAINT PHILLIP | SAINT PHILLIP DR | 067 | LEX | 2025-06-11 | U132645 | U461383 | 2024-12-05 | 2024-05-28 | 2024-12-31 | 2024-12-12 | RTINCHER | 2024-12-12 | 2024-12-06 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3167 | AMRCB |  | 100 | 055732240263167 | 1444.2333 | 2505036 | 1084887.24 | 100471.58 | 41050.9 | 11958.06 | 657218.01 | 0 | 14886.26 | 259302.43 | 10987
KY | KY - WEST | 2621 | 25026409300 |  |  |  | 6720208G | 2403558 | U461383 |  | 559 | EX | PAPER ONLY LP STOPPLE FITTINGS | 2600B | SAINT PHILLIPS | SAINT PHILLIPS | 067 | LEX | 2025-06-10 | U132645 | U461383 | 2025-05-23 | 2025-05-30 | 2025-06-15 | 2024-12-12 | RTINCHER | 2024-12-12 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP4093 | AMRCB |  | 100 | 055932250264093 |  | 0 | 6269.9 | 0 | 4975.29 | 0 | 0 | 0 | 0 | 1294.61
KY | KY - CENTRAL | 2629 | 22026237301 |  |  |  | 6748208I | 2293700 | U128885 |  | 557 | EX | INSTALL 11,150'-8"6"4"2" PMMP | 2600B | MUTUAL | MUTUAL AV | 049 | WIN | 2025-02-11 | U128132 | U128885 | 2024-11-01 | 2024-12-18 | 2026-10-21 | 2024-11-09 | WILLIAM FULKS | 2024-12-17 | 2024-11-08 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP2373 | AMRCB |  | 100 | 055732220262373 | 2217.45 | 3304272 | 3177275.55 | 151769.12 | 93208.58 | 36296.53 | 2097723.37 | 0 | 59811.55 | 738466.4 | 11972
KY | KY - CENTRAL | 2629 | 25026377900 |  |  |  | 6748208I | 2293700 | U128885 |  | 559 | EX | INSTALL LP FITTING-PAPER ONLY | 2600B | MAIN | MAIN ST | 049 | WIN | 2025-02-06 | U128132 | U128885 | 2025-01-10 | 2025-01-31 | 2025-01-31 | 2024-12-12 | WILLIAM FULKS | 2024-12-17 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00559 | 3200559 |  |  | WP3779 | AMRCB |  | 100 | 055932250263779 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24026355200 |  | 501358916 |  | 6684228J | 2407531 | U126783 |  | 555 | EX | INSTALL 150'-4" PMLP | 2600B | WAPPING | 403 WAPPING ST | 073 | FRA | 2025-01-28 | U136251 | U126783 | 2024-08-06 | 2024-12-16 | 2024-12-31 | 2024-12-13 | OLIVER MAYNARD | 2024-12-18 | 2024-12-09 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP3552 |  |  | 100 | 055532240263552 | 94.1833 | 2398 | 57369.63 | 7629.74 | 1097.14 | 616.93 | 37854.34 | 0 | 158.91 | 10012.57 | 218
KY | KY - WEST | 2621 | 24026365700 |  | 500514180 |  | 6720208M | 2409328 | U461383 |  | 555 | EX | INSTALL 320' OF 2"PMIP MAIN | 2600B | MONTAVESTA | 3426 MONTAVESTA RD | 067 | LEX | 2025-01-23 | U132645 | U461383 | 2024-10-14 | 2025-01-02 | 2025-01-10 | 2024-11-19 | RANDALL HUMPHREYS | 2024-12-18 | 2024-11-13 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3657 |  |  | 100 | 055532240263657 | 40 | 1825 | 29754.73 | 2768.05 | 1611.75 | 1344.15 | 17405.69 | 0 | 71.83 | 6553.26 | 365
KY | KY - EAST | 2631 | 20026983300 |  |  |  | 7356256A | 2075304 | U132280 |  | 557 | EX | INSTALL 6,600'-2"/4" PMMP | 2600B | CHESTNUT | CHESTNUT DR | 019 | ASH | 2025-02-13 | U128132 | U461492 | 2020-10-20 | 2024-03-01 | 2024-12-31 | 2024-09-17 | ORA SLONE | 2024-12-19 | 2024-04-30 | 2024-04-29 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP9833 | AMRCB |  | 100 | 055732200269833 | 1272.4 | 1231560 | 2015230.05 | 88325.98 | 62953.6 | 28160.7 | 1354878.82 | 0 | 11630.26 | 469280.69 | 6220
KY | KY - WEST | 2621 | 24026354300 |  | 501369434 |  | 6716216F | 2407470 | U461383 |  | 555 | EX | INSTALL 1750' OF 2"PMMP MAIN | 2600B | CRAVAT PASS | CRAVAT PASS LT241 | 067 | LEX | 2024-12-20 | U132645 | U461383 | 2024-07-29 | 2024-11-14 | 2024-12-31 | 2024-11-05 | RANDALL HUMPHREYS | 2024-12-19 | 2024-10-22 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3543 |  |  | 100 | 055532240263543 | 83.1 | 21000 | 49920.61 | 5214.01 | 4245.92 | 3450.34 | 26033.63 | 0 | 397.42 | 10579.29 | 1750
KY | KY - CENTRAL | 2629 | 24026371800 |  |  |  | 6736228C | 2410846 | U128885 |  | 557 | EX | EMER - INSTALL 3'-2" PMMP | 2621P | ARLINGTON | ARLINGTON | 017 | PAR | 2025-01-09 | U128132 | U128885 | 2024-12-09 | 2024-12-12 | 2024-12-31 | 2024-12-03 | NRICHIE | 2024-12-22 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3718 |  |  | 100 | 055732240263718 |  | 3 | 19259.53 | 7226.3 | 59.91 | 3696.58 | 4916.45 | 0 | 55.15 | 3305.14 | 3
KY | KY - CENTRAL | 2629 | 24026373800 |  |  |  | 6740228A | 2410951 | U128885 |  | 557 | EX | EMER - INSTALL 3'-2" PMMP | 2621P | VINE | VINE | 017 | PAR | 2025-01-03 | U128132 | U128885 | 2024-12-12 | 2024-12-27 | 2024-12-31 | 2024-12-05 | NRICHIE | 2024-12-22 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3738 |  |  | 100 | 055732240263738 |  | 3 | 6014.6 | 1910.03 | 148.31 | 1097.12 | 1563.76 | 0 | 10.75 | 1284.63 | 3
KY | KY - EAST | 2631 | 25026377300 |  |  |  | 7352256D | 2511329 | U122858 |  | 557 | VO | EMER - INSTALL 1'-2" PMLP | 2621P | BECKETT | 404 BECKETT ST | 019 | ASH | 2025-02-14 |  | U122858 | 2025-01-03 | 2025-01-30 | 2025-01-31 | 2024-12-30 | R CUMPSTON | 2024-12-30 | 2025-01-09 |  | A | 00032 | 88000000 | 0326310 | 0326310 | 00032 | 05007 | [6 empty] | 100 |  | 21.9833 | 0 | -823.67 | 0 | 0.64 | 0 | 0 | 0 | 0 | -824.31
KY | KY - WEST | 2623 | 25026377600 |  |  |  | 6696212K | 2511446 | U461383 |  | 559 | EX | EMER-INSTALL 4' OF 2"PMMP MAIN | 2621P | POCAHONTAS | 621 POCAHONTAS TL | 239 | VER | 2025-02-28 | U136251 | U461383 | 2025-01-08 | 2025-05-29 | 2025-06-01 | 2025-01-02 | CDESPAIN | 2025-01-02 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00559 | 3200559 |  |  | WP3776 |  |  | 100 | 055932250263776 |  | 4 | 8999.48 | 4760.11 | 168.32 | 1487.66 | 22.2 | 0 | 26.83 | 2534.36 | 4
KY | KY - WEST | 2621 | 24026376700 |  |  |  | 6720208H | 2411195 | U122858 |  | 557 | EX | EMER - INSTALL 3'-2" PMMP | 2621P | HEDGEWOOD | 188 HEDGEWOOD CT | 067 | LEX | 2025-06-13 | U132645 | U122858 | 2024-12-20 | 2025-08-28 | 2025-08-31 | 2024-11-25 | HMCKUNE | 2025-01-10 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3767 |  |  | 100 | 055732240263767 | 6.95 | 9 | 3141.8 | 2101.44 | 24 | 297.25 | 108.04 | 0 | 2.21 | 608.86 | 3
KY | KY - WEST | 2621 | 24026348200 |  |  |  | 6716208N | 2404653 | U122858 |  | 559 | EX | INSTALL ~30'-4" PMMP | 2621P | GOLD RUSH | 223 GOLD RUSH RD | 067 | LEX | 2025-02-12 | U123258 | U122858 | 2024-06-13 | 2024-12-27 | 2025-02-28 | 2024-10-03 | TROE | 2025-01-16 | 2024-10-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP3482 |  |  | 100 | 055932240263482 | 78.1333 | 470 | 16880.63 | 5035.55 | 1175.03 | 1005.86 | 6047.41 | 0 | 30.19 | 3586.59 | 47
KY | KY - EAST | 2631 | 24026365300 |  |  |  | 7356256M | 2409326 | U141016 |  | 557 | EX | EMER INSTALL 5" OF 4" PMLP | 2600E | GREENBRIAR RD | GREENBRIAR RD | 019 | ASH | 2025-02-08 | U128132 | U141016 | 2024-10-11 | 2025-06-25 | 2025-06-30 | 2024-10-09 | MCOLLET | 2025-01-17 | 2024-12-18 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP3653 |  |  | 100 | 055732240263653 | 19.0833 | 16 | 26234.06 | 8160.15 | 444.65 | 2775.86 | 9386.14 | 0 | 44.62 | 5422.64 | 2
KY | KY - CENTRAL | 2629 | 24026376300 |  |  |  | 6736212K | 2411100 | U128885 |  | 557 | EX | EMER - INSTALL 5'-2" PMIP | 2621P | CONSTITUTION | CONSTITUTION | 049 | WIN | 2025-02-19 | U128132 | U128885 | 2024-12-18 | 2024-12-23 | 2024-12-31 | 2024-12-13 | LSTANFI | 2025-01-24 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3763 |  |  | 100 | 055732240263763 |  | 5 | 6514.7 | 2596.97 | 596.56 | 151.69 | 1690.48 | 0 | 10.75 | 1468.25 | 5
KY | KY - CENTRAL | 2629 | 25026378800 |  |  |  | 6744208F | 2511563 | U128885 |  | 557 | EX | EMER - INSTALL 25'-2" PMMP | 2621P | WINCHESTER | 6 WINCHESTER PZ E | 049 | WIN | 2025-02-21 | U128132 | U128885 | 2025-01-14 | 2024-11-13 | 2025-01-07 | 2025-01-09 | TROE | 2025-01-24 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3788 |  |  | 100 | 055732250263788 |  | 25 | 81247.31 | 17392.42 | 2537.39 | 3118.61 | 35447.2 | 0 | 112.31 | 22639.38 | 25
KY | KY - CENTRAL | 2629 | 25026379000 |  |  |  | 6740208H | 2511570 | U128885 |  | 557 | EX | EMER - INSTALL 9'-2" PMMP | 2621P | LAMOND RUELLE | 213 LAMOND RUELLE | 049 | WIN | 2025-02-21 | U128132 | U128885 | 2025-01-14 | 2025-01-02 | 2025-01-13 | 2025-01-14 | WDENNING | 2025-01-28 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3790 |  |  | 100 | 055732250263790 |  | 9 | 1184.26 | 0 | 784.4 | 0 | 75.48 | 0 | 2.86 | 321.52 | 9
KY | KY - WEST | 2621 | 24026368800 |  |  |  | 6716208K | 2410260 | U134275 |  | 559 | EX | INSTALL 5' OF 6" PMLP (PIF) | 2600E | ZANDALE | 256 ZANDALE DR | 067 | LEX | 2025-02-07 | U132645 | U134275 | 2024-11-13 | 2025-06-26 | 2025-06-30 | 2025-02-03 | JOSH PASLEY | 2025-02-03 | 2025-01-17 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP3688 | AMRCB |  | 100 | 055932240263688 | 77.6167 | 72 | 53924.5 | 6309.92 | 16813.78 | 4085.08 | 9678.51 | 0 | 370.64 | 16666.57
KY | KY - EAST | 2631 | 24026333201 |  |  |  | 7356256E | 2404470 | U122858 |  | 557 | EX | EMER - INSTALL 478'-4" PMLP | 2600B | WILSHIRE | 2001 WILSHIRE BLVD | 019 | ASH | 2025-02-27 | U128132 | U122858 | 2025-01-16 | 2025-02-17 | 2025-02-28 | 2025-01-27 | BRANDON ROBERTS | 2025-02-06 | 2025-01-16 | 2025-01-14 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP3332 |  |  | 100 | 055732240263332 | 244.5167 | 17280 | 205447.29 | 16403.38 | 5000.19 | 9213.14 | 110802.43 | 0 | 615.39 | 63412.76 | 540
KY | KY - WEST | 2623 | 25026381300 |  |  |  | 6688228K | 2511609 | U126783 |  | 557 | CO | EMER-INSTALL 180' OF 4"PMLP MN | 2621P | RANDOLPH | 101 RANDOLPH RD | 073 | FRA | 2025-02-07 |  | U126783 | 2025-01-15 | 2025-01-28 | 2026-11-15 |  | KKINDER | 2025-02-07 | 2025-01-28 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP3813 | AMRCB |  | 100 | 055732250263813 | 0.93333 | 0 | 2921.66 | 68.93 | 1732.48 | 4.19 | 312.28 | 0 | 84.11 | 719.67
KY | KY - CENTRAL | 2629 | 24026352000 |  | 501367045 |  | 6744208M | 2407005 | U128885 |  | 555 | EX | INSTALL 700'-2" PMMP | 2600B | BULLION | 550 BULLION BV | 049 | WIN | 2025-02-18 | U136930 | U128885 | 2024-07-12 | 2025-01-24 | 2025-01-30 | 2025-02-10 | JOSH PASLEY | 2025-02-10 | 2025-02-04 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP3520 |  |  | 100 | 055532240263520 | 40.85 | 3580 | 75786.62 | 3812.81 | 2609.35 | 2575.32 | 36140.45 | 0 | 191.85 | 30456.84 | 716
KY | KY - WEST | 2621 | 25026410600 |  |  |  | 6720208D | 2403558 | U461383 |  | 557 | CO | EMER-INSTALL 3'-2"PMMP MAIN | 2600B | SAINT TERESA | 2021 SAINT TERESA | 067 | LEX | 2025-06-09 |  | U461383 | 2025-06-05 | 2026-06-30 | 2027-02-10 | 2025-02-10 | JAMIE ENSMINGER | 2025-02-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP4106 |  |  | 100 | 055732250264106 |  | 0 | 59.2 | 0 | 0 | 0 | 59.2 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24026372000 |  | 501374098 |  | 6700212M | 2410689 | U126783 |  | 555 | EX | INSTALLING 500'-2" PMMP | 2600B | AZALEA | AZALEA LN LT87 | 239 | VER | 2025-03-05 | U128132 | U126783 | 2024-12-09 | 2025-02-28 | 2025-03-14 | 2025-02-18 | STEVE CANOY | 2025-02-21 | 2025-02-05 | 2025-02-12 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP3720 |  |  | 100 | 055532240263720 | 53.6833 | 4510 | 47889.55 | 4101.13 | 1631.68 | 3343.89 | 18785.68 | 0 | 129.25 | 19897.92 | 451
KY | KY - WEST | 2621 | 24026340200 |  | 100425964 |  | 6720212I | 2398970 | U461383 |  | 555 | EX | INSTALL 600' OF 8"PMMP MAIN | 2600B | LIMESTONE | 409 S LIMESTONE ST | 067 | LEX | 2025-03-10 | U132645 | U461383 | 2024-04-18 | 2025-01-08 | 2025-01-31 | 2025-02-25 | WILLIAM FULKS | 2025-02-25 | 2025-01-13 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3402 |  |  | 100 | 055532240263402 | 282.0333 | 22015 | 388585.22 | 20959.13 | 24903.57 | 6407.15 | 200650.72 | 0 | 3.55 | 135661.1 | 629
KY | KY - WEST | 2621 | 25026378600 |  |  |  | 6716208C | 2511541 | U461383 |  | 561 | EX | INSTALL 42' OF 2"/4" PMMP MAIN | 2600B | STATE | 201 STATE ST | 067 | LEX | 2025-03-07 | U132645 | U461383 | 2025-01-13 | 2025-02-26 | 2025-03-01 | 2025-02-24 | JOSH PASLEY | 2025-02-26 | 2025-02-12 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP3786 |  |  | 100 | 056132250263786 | 80.9167 | 451 | 26011.02 | 6695.98 | 710.33 | 4651.5 | 9627.47 | 0 | 112.68 | 4213.06 | 41
KY | KY - EAST | 2631 | 24026359401 |  | 501019595 |  | 7344264L | 2408190 | U141016 |  | 555 | EX | INSTALL 200' OF 4" PMIP | 2600B | FAIRWAY | 1226 FAIRWAY DR LT67 | 089 | FLA | 2025-04-07 | U128132 | U141016 | 2025-02-17 | 2025-02-13 | 2025-02-19 | 2025-02-13 | BRANDON ROBERTS | 2025-02-27 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP3594 |  |  | 100 | 055532240263594 | 39.6333 | 770 | 61986.14 | 2877.18 | 3019.58 | 2459.88 | 30377.28 | 0 | 312.76 | 22939.46 | 154
KY | KY - WEST | 2623 | 23026301200 |  |  |  | 6712232L | 2300854 | U461383 |  | 561 | EX | INSTALL 60' OF 6"PMMP MAIN | 2600B | CONNECTOR | CONNECTOR RD | 209 | GEO | 2025-03-12 | U128132 | U461383 | 2023-10-18 | 2025-03-26 | 2025-04-01 | 2025-03-05 | EDWARD FOX | 2025-03-06 | 2025-02-24 | 2025-02-24 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00561 | 3200561 |  |  | WP3012 |  |  | 100 | 056132230263012 | 42.9667 | 450 | 43879.22 | 3210.07 | 2275.48 | 581.97 | 23174.78 | 0 | 0 | 14636.92 | 75
KY | KY - EAST | 2633 | 25026394000 |  |  |  | 7352156L | 2512421 | U122858 |  | 557 | EX | EMER INSERT 280'-1.2" PMIP | 2621P | DOW HUNTER | DOW HUNTER | 071 | BET | 2025-03-31 | U128132 | U122858 | 2025-02-19 | 2025-10-28 | 2025-10-31 | 2025-02-19 | JAHOWARD | 2025-03-10 |  |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00557 | 3200557 |  |  | WP3940 | AMRCB |  | 100 | 055732250263940 | 0.5 | 284 | 2217.44 | 264.48 | 1263.6 | 15.15 | 0 | 0 | 0 | 674.21 | 284
KY | KY - WEST | 2621 | 25026395600 |  |  |  | 6716212N | 2512799 | U461383 |  | 557 | EX | EMER-INSTALL 3' OF 3"PMMP MAIN | 2600B | GIBSON | 511 GIBSON AV | 067 | LEX | 2025-03-27 | U136251 | U461383 | 2025-02-28 | 2026-06-30 | 2027-02-18 | 2025-02-26 | JOSH PASLEY | 2025-03-13 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3956 |  |  | 100 | 055732250263956 |  | 3 | 330.23 | 0 | 172.22 | 0 | 78.44 | 0 | 0 | 79.57 | 3
KY | KY - EAST | 2631 | 24026349500 |  |  |  | 7352260J | 2406826 | U122858 |  | 557 | EX | INSTALL 40'-12" CSMP | 2600B | BELLEF PRIN | 213 BELLEF PRIN RD | 019 | ASH | 2025-03-19 | U128132 | U122858 | 2024-06-27 | 2024-08-31 | 2025-04-20 | 2025-03-10 | ORA SLONE | 2025-03-14 | 2025-01-15 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP3495 |  |  | 100 | 055732240263495 | 235.1 | 986 | 237894.26 | 20855.41 | 19784.24 | 9279.19 | 107820.3 | 0 | 3131.06 | 77024.06 | 34
KY | KY - EAST | 2631 | 24026358700 |  | 501368538 |  | 7328264K | 2407391 | U141016 |  | 555 | CO | INSTALL 100' OF 2" PMMP MLE | 2621P | LIME | 1037 LIME ST | 089 | FLA | 2025-03-14 |  | U141016 | 2024-08-19 | 2024-10-29 | 2024-10-31 | 2024-10-03 | ABHATFIE | 2025-03-14 | 2024-09-20 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP3587 |  |  | 100 | 055532240263587 | 109.2833 | 0 | 24604.17 | 7407.34 | 1248.65 | 1697.88 | 8155.42 | 0 | 115.35 | 5979.53
KY | KY - WEST | 2621 | 24026361300 |  |  |  | 6712208B | 2405283 | U122858 |  | 561 | EX | INSTALL 750'-2" PMMP | 2600B | SAVANNAH | SAVANNAH LN | 067 | LEX | 2025-03-27 | U132645 | U122858 | 2024-09-17 | 2025-03-04 | 2025-03-30 | 2025-03-11 | STEVE CANOY | 2025-03-19 | 2025-02-21 | 2025-02-25 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP3613 |  |  | 100 | 056132240263613 | 106.0333 | 12495 | 206114.64 | 7649.31 | 1991 | 6946.38 | 123343.26 | 0 | 828.59 | 65356.1 | 735
KY | KY - CENTRAL | 2629 | 24026364900 |  | 501351304 |  | 6736228K | 2398765 | U128885 |  | 555 | EX | INSTALL 2,300'-4" PMMP | 2600B | LINZI | LINZI WY LT45 | 017 | PAR | 2025-04-09 | U128132 | U128885 | 2024-10-09 | 2025-01-08 | 2025-01-31 | 2025-02-24 | RANDALL HUMPHREYS | 2025-03-24 | 2024-12-02 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP3649 |  |  | 100 | 055532240263649 | 291.8333 | 90250 | 215200.02 | 22289.22 | 12750.89 | 19641.15 | 94269.28 | 0 | 1946.52 | 64302.96 | 2375
KY | KY - EAST | 2631 | 25026381700 |  | 501375187 |  | 7348260H | 2511591 | U141016 |  | 555 | EX | INSTALL 230' OF 2" PMIP | 2600E | SUNSET | 524 SUNSET DR | 089 | ASH | 2025-04-04 | U128132 | U141016 | 2025-01-18 | 2025-02-04 | 2025-04-14 | 2025-03-24 | ORA SLONE | 2025-03-24 | 2025-03-17 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP3817 |  |  | 100 | 055532250263817 | 53.7167 | 2784 | 89700.18 | 3765.58 | 1743.92 | 844.36 | 59027.37 | 0 | 156.74 | 24162.21 | 348
KY | KY - EAST | 2633 | 25026398400 |  |  |  | 7352156L | 2513045 | U122858 |  | 557 | EX | EMER - INSTALL FITTINGS | 2621P | BOOOMERANG | BOOOMERANG | 071 | BET | 2025-04-04 | U128132 | U122858 | 2025-03-11 | 2025-11-25 |  | 2025-03-05 | JHOWARD | 2025-03-24 |  |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00557 | 3200557 |  |  | WP3984 | AMRCB |  | 100 | 055732250263984 |  | 0 | 6860.25 | 4256.46 | 0 | 334.21 | 128.76 | 0 | 20.36 | 2120.46
KY | KY - WEST | 2621 | 25026400900 |  |  |  | 6716204H | 2513468 | U122858 |  | 557 | EX | EMER - INSTALL 2'-4" PMMP | 2621P | RIDGEPOINT | RIDGEPOINT | 067 | LEX | 2025-04-14 | U132645 | U122858 | 2025-03-26 | 2025-11-25 | 2025-11-30 | 2025-03-23 | T ROE | 2025-03-24 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP4009 |  |  | 100 | 055732250264009 |  | 2 | 6330.01 | 3926.41 | 160.22 | 230.12 | 0 | 0 | 18.92 | 1994.34 | 2
KY | KY - CENTRAL | 2629 | 25026403000 |  |  |  | 6748180P | 2513719 | U128885 |  | 557 | CO | EMER - INSTALL 2'-3" PMMP | 2621P | WACO LOOP | 191 WACO LOOP | 151 | WAC | 2025-05-23 |  | U128885 | 2025-04-07 | 2025-03-26 | 2025-04-09 | 2025-03-27 | U125572 | 2025-03-27 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP4030 |  |  | 100 | 055732250264030 |  | 0 | 230.88 | 0 | 0 | 0 | 230.88 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 25026381800 |  | 501375602 |  | 6736228C | 2511455 | U128885 |  | 555 | EX | INSTALL 250'-2" PMMP | 2600B | DOGWOOD | 1200 DOGWOOD DR | 017 | PAR | 2025-04-04 | U128132 | U128885 | 2025-01-20 | 2025-04-09 | 2025-04-11 | 2025-03-25 | STEVE CANOY | 2025-03-28 | 2025-03-18 | 2025-03-20 | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP3818 |  |  | 100 | 055532250263818 | 49.6667 | 1864 | 52355.75 | 3626.25 | 1842.97 | 3098.94 | 27345.79 | 0 | 148.61 | 16293.19 | 233
KY | KY - EAST | 2631 | 24026361400 |  | 501368206 |  | 7348264I | 2408664 | U141016 |  | 555 | EX | INSTALL 100' OF 2" PMIP | 2600E | DOYLE | 150 DOYLE LN | 089 | FLA | 2025-04-14 | U128132 | U141016 | 2024-09-17 | 2025-02-12 | 2025-03-26 | 2025-03-31 | ORA SLONE | 2025-03-31 | 2025-03-14 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP3614 |  |  | 100 | 055532240263614 | 29.1 | 680 | 28089.92 | 2028.07 | 1217.13 | 485.7 | 15962.81 | 0 | 79.07 | 8317.14 | 136
KY | KY - CENTRAL | 2632 | 24026366400 |  | 501372394 |  | 7256276B | 2409391 | U122858 |  | 555 | EX | INSTALL ~390'-2" PMIP | 2621P | EVERGREEN | EVERGREEN LN LT1 | 161 | MAY | 2025-04-08 | U128132 | U122858 | 2024-10-22 | 2025-02-06 | 2025-02-14 | 2025-02-14 | TALLISON | 2025-03-31 | 2025-01-29 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00555 | 3200555 |  |  | WP3664 |  |  | 100 | 055532240263664 | 181.3 | 15428 | 44902.44 | 12792.64 | 4394.73 | 1004.11 | 11128.75 | 0 | 201.07 | 15381.14 | 532
KY | KY - EAST | 2633 | 24026345800 |  |  |  | 7344148I | 2397807 | U141016 |  | 561 | EX | INSTALL 1400'-2" PMIP | 2600B | COW HOLLOW | COW HOLLOW RD | 071 | DRI | 2025-05-15 | U128132 | U141016 | 2024-06-04 | 2025-03-26 | 2025-04-15 | 2025-03-21 | BRANDON ROBERTS | 2025-04-02 | 2025-01-17 | 2025-02-28 | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00561 | 3200561 |  |  | WP3458 | AMRCB |  | 100 | 056132240263458 | 212.75 | 31512 | 263557.02 | 13963.93 | 5148.73 | 13184.86 | 157469.99 | 0 | 1240.7 | 72548.81 | 1212
KY | KY - CENTRAL | 2629 | 24026314400 |  | 501359277 |  | 6736180C | 2402680 | U128885 |  | 555 | EX | INSTALL 1,200'-4" PMMP | 2600B | ROBERT MARTIN | 1414 ROBERT MARTIN | 151 | RIC | 2025-04-23 | U128132 | U128885 | 2024-01-31 | 2025-03-31 | 2025-04-11 | 2025-04-15 | DEREK PAYTON | 2025-04-15 | 2025-03-17 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP3144 |  |  | 100 | 055532240263144 | 66.1667 | 8976 | 441793.04 | 4881.39 | 10416.67 | 10169.09 | 288824.74 | 0 | 842.19 | 126658.96 | 1122
KY | KY - CENTRAL | 2629 | 25026406000 |  |  |  | 6744208P | 2514108 | U128885 |  | 557 | CO | EMER - INSTALL 2'-2" PMLP | 2621P | MAIN | 17 S MAIN ST | 049 | WIN | 2025-05-23 |  | U128885 | 2025-04-23 | 2025-04-11 | 2025-04-18 |  | U125572 | 2025-04-18 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP4060 |  |  | 100 | 055732250264060 |  | 0 | 4119.02 | 2419.63 | 566.27 | 147.64 | 54.76 | 0 | 59.66 | 871.06
KY | KY - CENTRAL | 2629 | 25026400200 |  |  |  | 6732248G | 2512967 | U128885 |  | 559 | EX | INSTALL 550'-2" PMMP | 2600B | US HIGHWAY 27 S | 1282 US HIGHWAY 27 S | 097 | CYN | 2025-05-23 | U136251 | U128885 | 2025-03-24 | 2025-04-28 | 2025-05-01 | 2025-04-23 | EDWARD F GOINS | 2025-04-25 | 2025-04-21 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00559 | 3200559 |  |  | WP4002 |  |  | 100 | 055932250264002 | 43.5 | 2615 | 47508 | 2933.96 | 1210.74 | 179.01 | 32671.05 | 0 | 77.64 | 10435.6 | 523
KY | KY - WEST | 2621 | 24026376901 |  |  |  | 6724208M | 2075930 | U122858 |  | 561 | EX | INSTALL 1218'-6" PMMP | 2600B | RICHMOND | RICHMOND RD | 067 | LEX | 2025-05-13 | U128132 | U122858 | 2025-05-01 | 2025-02-28 | 2025-04-30 | 2025-04-29 | WILLIAM FULKS | 2025-04-30 | 2025-03-04 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP3769 |  |  | 100 | 056132240263769 | 375.0667 | 66176 | 707094.52 | 24176.63 | 15262.68 | 7222.68 | 437081.86 | 0 | 5885.76 | 217464.91 | 1408
KY | KY - WEST | 2621 | 22026239702 |  |  |  | 6720212F | 2293756 | U134275 |  | 557 | CO | INSTALL 8650' - 2,4,6" PMMP | 2600B | CASTLEWOOD | 209 CASTLEWOOD DR | 067 | LEX | 2025-05-02 |  | U134275 | 2024-10-29 | 2024-06-20 | 2025-02-28 | 2025-03-18 | DAVID YOUNG | 2025-05-02 | 2025-02-03 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2397 | AMRCB |  | 100 | 055732220262397 | 2049.6667 | 2164932 | 1934664.05 | 147421.39 | 77147.36 | 13852.04 | 1209934.68 | 0 | 46321.39 | 439987.19 | 8591
KY | KY - WEST | 2621 | 25026398800 |  | 501378936 |  | 6728208J | 2513070 | U461383 |  | 555 | EX | INSTALL 3670' OF 2"/4"PMMP MN | 2600B | BUTTERMILK | BUTTERMILK RD LT1 | 067 | LEX | 2025-05-13 | U132645 | U461383 | 2025-03-12 | 2025-05-02 | 2025-05-30 | 2025-04-15 | OLIVER MAYNARD | 2025-05-05 | 2025-03-21 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3988 |  |  | 100 | 055532250263988 | 217.9667 | 99428 | 130345.4 | 14026.44 | 19385.68 | 841.97 | 66049.4 | 0 | 556.94 | 29484.97 | 3551
KY | KY - WEST | 2621 | 24026371100 |  |  |  | 6724212K | 2410765 | U461383 |  | 557 | EX | EMER-INSTALL 6' OF 8"PMMP | 2621P | WINCHESTER | 2550 WINCHESTER RD | 067 | LEX | 2025-06-10 | U132645 | U461383 | 2024-12-05 | 2025-07-01 | 2025-07-01 | 2024-12-16 | BDARNELL | 2025-05-09 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3711 |  |  | 100 | 055732240263711 | 2.2333 | 6 | 5742.34 | 3438.75 | 864.86 | 355.77 | 0 | 0 | 18.01 | 1064.95 | 6
KY | KY - WEST | 2621 | 24026371600 |  |  |  | 6720208A | 2410818 | U134275 |  | 557 | EX | EMER - INSTALL 5' - 2" PMMP | 2621P | FONTAINE | 1120 FONTAINE RD | 067 | LEX | 2025-06-09 | U138344 | U134275 | 2024-12-06 | 2024-12-31 | 2025-07-01 | 2024-11-27 | RSTRONG | 2025-05-09 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3716 |  |  | 100 | 055732240263716 | 0.65 | 5 | 6372.3 | 1968.74 | 23.89 | 136.52 | 2714.57 | 0 | 3.32 | 1525.26 | 5
KY | KY - WEST | 2621 | 25026385100 |  |  |  | 6720204M | 2511942 | U461383 |  | 557 | CO | EMER-INSTALL 4' OF 4"PMMP MAIN | 2621P | HARTLAND | 4541 HARTLAND PR | 067 | LEX | 2025-05-09 |  | U461383 | 2025-01-30 | 2025-06-30 | 2025-07-01 |  | HMCKUNE | 2025-05-09 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3851 |  |  | 100 | 055732250263851 | 1.3667 | 0 | 10551.81 | 6006.97 | 428.33 | 803.52 | 0 | 0 | 333.19 | 2979.8
KY | KY - WEST | 2623 | 25026392000 |  | 501376468 |  | 6712232N | 2511993 | U126783 |  | 555 | EX | INSTALL 140'-2" PMMP | 2600E | WHITE PINE | 309 WHITE PINE LN | 209 | GEO | 2025-05-23 | U136251 | U126783 | 2025-02-07 | 2025-02-27 | 2025-05-28 | 2025-05-09 | EDWARD F GOINS | 2025-05-12 | 2025-05-05 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP3920 |  |  | 100 | 055532250263920 | 40 | 690 | 21515.47 | 2899.8 | 1652.44 | 167.95 | 12337.67 | 0 | 71.04 | 4386.57 | 138
KY | KY - EAST | 2633 | 19026867802 |  |  |  | 7364188G | 1962537 | U122858 |  | 559 | CO | INSTALL 376'-4" PMIP | 2600E | SR 40 | SR 40 | 159 | INE | 2025-05-19 |  | U122858 | 2024-05-02 | 2025-09-11 | 2025-09-30 | 2025-05-06 | BRANDON ROBERTS | 2025-05-16 | 2025-04-07 | 2025-04-07 | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00559 | 3200559 |  |  | WP8678 |  |  | 100 | 055932190268678 | 233.9833 | 9800 | 262651.39 | 15540.81 | 6354.85 | 14531.31 | 168928.09 | 0 | 3543.4 | 53752.93 | 350
KY | KY - CENTRAL | 2629 | 25026409900 |  |  |  | 7240202G | 2514761 | U128885 |  | 557 | CO | EMER - INSTALL 10'-2" PMMP | 2621P | LEVEE | 6590 LEVEE RD | 173 | MT | 2025-06-17 |  | U128885 | 2025-05-29 | 2025-05-08 | 2025-05-19 |  | DENNING | 2025-05-19 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP4099 |  |  | 100 | 055732250264099 |  | 0 | 9748.17 | 5423.18 | 0 | 2226.64 | 48.84 | 0 | 87.45 | 1962.06
KY | KY - WEST | 2623 | 22026178300 |  |  |  | 6712228L | 2287686 | U461383 |  | 557 | CO | EMER-INSTALL 5'OF 2"PMMP MAIN | 2621P | RUTH MILLER | RUTH MILLER | 209 | GEO | 2025-05-20 |  | U461383 | 2022-03-24 | 2022-11-30 |  |  | SLBARKER | 2025-05-20 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP1783 |  |  | 100 | 055732220261783 |  | 0 | 2814.42 | 1228.94 | 149.13 | 832.63 | 112.48 | 0 | 94.82 | 396.42
KY | KY - CENTRAL | 2629 | 25026393800 |  | 501357014 |  | 7240216O | 2301540 | U128885 |  | 555 | EX | INSTALL 2,100'-2" PMMP | 2600E | HAWK | HAWK LN LT1 | 173 | MT | 2025-05-28 | U128132 | U128885 | 2025-02-18 | 2025-05-13 | 2025-05-30 | 2025-05-19 | ALEX WILLIAMSON | 2025-05-20 | 2025-05-05 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP3938 |  |  | 100 | 055532250263938 | 108.6833 | 28518 | 110997.26 | 9385.78 | 6615.74 | 2288.92 | 69739.38 | 0 | 341.85 | 22625.59 | 2037
KY | KY - WEST | 2623 | 25026397400 |  |  |  | 6712232K | 2512986 | U461383 |  | 557 | CO | EMER-INSTALL 3' OF 2"PMMP MAIN | 2621P | BEVELED GLASS | 108 BEVELED GLASS LN | 209 | GEO | 2025-05-20 |  | U461383 | 2025-03-07 | 2025-07-01 | 2025-07-01 |  | M. COLLINS | 2025-05-20 | 2025-05-15 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP3974 |  |  | 100 | 055732250263974 | 20.3167 | 0 | 7928.42 | 4332.7 | 168.32 | 1115.48 | 69.56 | 0 | 130.41 | 2111.95
KY | KY - WEST | 2621 | 24026358801 |  |  |  | 6720208E | 2396748 | U461383 |  | 561 | EX | INSTALL 4200' OF 2"/4"PMMP | 2600B | COOPER | COOPER DR | 067 | LEX | 2025-06-09 | U128132 | U461383 | 2025-03-27 | 2024-09-19 | 2025-06-01 | 2025-04-17 | JOSHUA COX | 2025-05-21 | 2025-04-17 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP3588 | AMRCB |  | 100 | 056132240263588 | 1456.4167 | 678078 | 782267.64 | 105673.31 | 24018.91 | 10651.64 | 442889.95 | 0 | 1821.46 | 197212.37 | 3897
KY | KY - WEST | 2621 | 24026360700 |  |  |  | 6720208E | 2396748 | U461383 |  | 561 | EX | INSTALL 230' OF 4"PMLP MAIN | 2600B | ROMANY | 310 ROMANY RD | 067 | LEX | 2025-06-10 | U128132 | U461383 | 2024-09-13 | 2025-05-30 | 2025-06-01 | 2025-04-29 | JOSHUA COX | 2025-05-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP3607 | AMRCB |  | 100 | 056132240263607 |  | 395 | 19505.93 | 0 | 13597.97 | 0 | 38.22 | 0 | 311.04 | 5558.7 | 395
KY | KY - EAST | 2631 | 18026794401 |  |  |  | 7356216D | 1855491 | U132703 |  | 557 | CO | INSTALL 4400'-2"/4"PMMP MAIN | 2600B | SULLIVAN | SULLIVAN ST | 127 | LOU | 2025-05-27 |  | U132703 | 2025-03-04 | 2025-06-30 | 2025-12-31 | 2024-11-07 | MBLANKE/CJH C PACK | 2025-05-27 | 2024-10-17 | 2024-10-22 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP7944 | AMRCB |  | 100 | 055732180267944 | 1012.55 | 297472 | 1250897.35 | 79735.63 | 11429.49 | 110151.8 | 709774.01 | 0 | 1850.82 | 337955.6 | 2324
KY | KY - EAST | 2631 | 25026411700 |  |  |  | 7356216D | 1855491 | U132703 |  | 559 | CO | INSTALL SHORTSTOP TEE | 2600B | PIKE | PIKE ST | 127 | LOU | 2025-06-19 |  | U132703 | 2025-06-17 | 2025-12-31 | 2025-12-31 | 2025-04-16 | MBLANKE/CJH CASEY PACK | 2025-05-27 |  | 2025-03-21 | C | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00559 | 3200559 |  |  | WP4117 | AMRCB |  | 100 | 055932250264117 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026283101 |  | 501343072 |  | 7356220N | 2398575 | U122858 |  | 555 | CO | INSTALL 780'-2" PMMP | 2600B | FALLS CREEK | 191 FALLS CREEK DR | 127 | LOU | 2025-05-30 |  | U122858 | 2025-02-20 | 2025-05-21 | 2025-05-30 | 2025-05-28 | BRANDON ROBERTS | 2025-05-28 | 2025-05-20 | 2025-05-20 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP2831 |  |  | 100 | 055532230262831 | 41.75 | 3850 | 71782.2 | 2963.64 | 7114.83 | 1037.83 | 44031.25 | 0 | 264.86 | 16369.79 | 770
KY | KY - WEST | 2621 | 22026236501 |  |  |  | 6716212F | 2293634 | U461383 |  | 557 | CO | INSTALL 1325' OF 4"/8"CSHP MN | 2600B | TRAFTON | TRAFTON ST | 067 | LEX | 2025-05-29 |  | U461383 | 2025-05-19 | 2025-07-17 | 2025-12-31 | 2025-05-28 | DUSTIN DAVIS | 2025-05-29 | 2025-05-22 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2365 | AMRCB |  | 100 | 055732220262365 | 998.9167 | 182952 | 1407086.76 | 79007.59 | 305419.19 | 25651.51 | 574860.04 | 0 | 20338.34 | 401810.09 | 1386
KY | KY - WEST | 2621 | 24026356000 |  |  |  | 6720212I | 2407694 | U461383 |  | 557 | EX | INSTALL 475' OF 2"PMMP MAIN | 2600B | WILGUS | WILGUS AV | 067 | LEX | 2025-06-04 | U136251 | U461383 | 2024-08-07 | 2025-10-31 | 2025-12-01 | 2025-04-29 | STEVE CANOY | 2025-05-29 | 2024-09-24 | 2025-04-07 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3560 | AMRCB |  | 100 | 055732240263560 | 227.15 | 17784 | 138117.86 | 15062.17 | 3890.16 | 14353.27 | 79748.06 | 0 | 757.69 | 24306.51 | 468
KY | KY - WEST | 2621 | 24026370600 |  |  |  | 6712212P | 2410683 | U122858 |  | 561 | CO | INSTALL 32'-6" PMLP | 2600E | FURLONG | 873 FURLONG DR | 067 | LEX | 2025-05-30 |  | U122858 | 2024-12-02 | 2025-05-23 |  | 2025-04-16 | KKINDER | 2025-05-30 | 2025-04-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP3706 | AMRCB |  | 100 | 056132240263706 | 82.6333 | 0 | 8317.84 | 4657.23 | 3313.8 | 474.33 | 0 | 0 | 122.98 | -250.5
KY | KY - WEST | 2621 | 25026405400 |  |  |  | 6720216M | 2514040 | U122858 |  | 557 | EX | EMER - INSTALL 2'-2" PMMP | 2621P | NEW CIRCLE | 547 W NEW CIRCLE RD | 067 | LEX | 2025-06-04 | U136251 | U122858 | 2025-04-21 | 2025-06-30 | 2025-07-01 | 2025-04-17 | KKINDER | 2025-05-30 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP4054 |  |  | 100 | 055732250264054 | 0.033333 | 2 | 3579.32 | 2374.73 | 23.97 | 272 | 153.92 | 0 | 10.14 | 744.56 | 2
KY | KY - CENTRAL | 2629 | 25026410800 |  |  |  | 7240216I | 2514918 | U128885 |  | 557 | CO | EMER - INSTALL 2'-2" PMMP | 2621P | INDIAN MOUND | 490 INDIAN MOUND DR | 173 | MT | 2025-06-17 |  | U128885 | 2025-06-06 | 2025-06-03 | 2025-06-04 |  | DENNING | 2025-06-04 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP4108 |  |  | 100 | 055732250264108 |  | 0 | 1873.09 | 789.55 | 0 | 460.11 | 118.4 | 0 | 98.89 | 406.14
KY | KY - EAST | 2631 | 24026341000 |  |  |  | 7348260P | 2405531 | U141016 |  | 559 | CO | INSTALL 300'OF 2" PMIP | 2621P | CRANCE | CRANCE CT | 019 | ASH | 2025-06-06 |  | U141016 | 2024-04-29 | 2025-04-24 | 2025-04-30 |  | MCOLLET | 2025-06-06 | 2025-03-23 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00559 | 3200559 |  |  | WP3410 |  |  | 100 | 055932240263410 | 142.9667 | 0 | 56621.85 | 10835.91 | 1231.72 | 5386.14 | 22329.12 | 0 | 957.46 | 15881.5
KY | KY - WEST | 2621 | 24026369000 |  |  |  | 6720212E | 2410261 | U122858 |  | 557 | EX | INSTALL 65'-8" PMLP | 2621P | LIMESTONE | 501 N LIMESTONE | 067 | LEX | 2025-06-20 | U132645 | U122858 | 2024-11-13 | 2025-07-18 | 2025-07-31 | 2025-04-03 | BDARNELL | 2025-06-06 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3690 | AMRCB |  | 100 | 055732240263690 | 0.98333 | 178 | 144966.81 | 31637.83 | 9002.36 | 8115.7 | 75991.58 | 0 | 517.71 | 19701.63 | 178
KY | KY - WEST | 2621 | 25026399300 |  |  |  |  | 2513258 | U132703 |  | 557 | CO | EMER - INSTALL 5'-2" PMMP | 2600B | 6870 ATHENS BOONESBORO | 6870 ATHENS BOONESBORO | 067 | LEX | 2025-06-06 |  | U132703 | 2025-03-19 | 2025-11-26 |  |  | BDARNELL | 2025-06-06 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3993 | AMRCB |  | 100 | 055732250263993 | 1.4333 | 0 | 2298.33 | 1275.32 | 33.81 | 242.08 | 0 | 0 | 45.97 | 701.15
KY | KY - WEST | 2621 | 25026406300 |  |  |  | 6720212N | 2514136 | U126783 |  | 557 | CO | INSTALL 15'-6" PMLP | 2621P | AURORA | 908 AURORA AV | 067 | LEX | 2025-06-06 |  | U126783 | 2025-04-24 | 2025-05-01 | 2025-07-31 |  | TROE | 2025-06-06 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP4063 | AMRCB |  | 100 | 055732250264063 | 0.1 | 0 | 10590.58 | 5611.78 | 0 | 582.16 | 2127.64 | 0 | 108.24 | 2160.76
KY | KY - WEST | 2621 | 24026368600 |  | 501372393 |  | 6712208N | 2409557 | U141016 |  | 555 | EX | INSTALL 640' OF 2" PMMP | 2600B | FOUNTAINBLUE | 3980 FOUNTAINBLUE LN LT4 | 067 | LEX | 2025-06-19 | U136251 | U141016 | 2024-11-11 | 2025-05-23 | 2025-06-01 | 2025-05-29 | EDWARD F GOINS | 2025-06-10 | 2025-05-20 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3686 |  |  | 100 | 055532240263686 | 55.0833 | 5456 | 50384.93 | 3760.94 | 2904.43 | 728.05 | 31726.33 | 0 | 206.36 | 11058.82 | 682
KY | KY - WEST | 2621 | 25026407800 |  |  |  | 6716208J | 2514497 | U122858 |  | 557 | CO | EMER - INSTALL 5'-2" PMMP | 2621P | NORMAN | 2350 NORMAN LN | 067 | LEX | 2025-06-10 |  | U122858 | 2025-05-14 | 2025-05-13 | 2025-05-13 |  | RSTRONG | 2025-06-10 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP4078 |  |  | 100 | 055732250264078 | 1.2833 | 0 | 1605.37 | 1062.64 | 23.97 | 120.58 | 65.12 | 0 | 12.71 | 320.35
KY | KY - WEST | 2621 | 25026410400 |  |  |  | 6720216O | 2514859 | U122858 |  | 557 | CO | EMER - INSTALL 10'-2" PMMP | 2621P | WHISPERING WOOD | 115 WHISPERING WOOD | 067 | LEX | 2025-06-16 |  | U122858 | 2025-06-04 | 2026-02-27 | 2025-07-31 |  | KKINDER | 2025-06-16 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP4104 |  |  | 100 | 055732250264104 | 0.85 | 0 | 2436.76 | 1561.32 | 0 | 91.52 | 116.92 | 0 | 129.83 | 537.17
KY | KY - WEST | 2623 | 25026410100 |  |  |  | 6684228B | 2514791 | U132703 |  | 557 | CO | EMER - INSTALL 200' - 2" | 2600E | KENTUCKY | 874 KENTUCKY AV | 073 | FRA | 2025-06-19 |  | U132703 | 2025-05-30 | 2026-08-27 | 2027-04-12 |  | D. COLLINS | 2025-06-19 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP4101 | AMRCB |  | 100 | 055732250264101 |  | 0 | 503.2 | 0 | 0 | 0 | 503.2 | 0 | 0 | 0

## SAP Pivot (hidden)
Basic finish date | (Multiple Items)
Row Labels | Sum of Total planned costs | Sum of Total actual costs
ANC32.0000.00002 | 0 | 675215.08
ANC32.0000.00027 | 0 | 1192.62
ANC32.0000.00029 | 0 | 824.94
ANC32.0000.00030 | 0 | 2260.97
ANC32.0000.00044 | 0 | 205.8
ANC32.0000.00046 | 0 | 7813.18
ANC32.0000.00051 | 0 | 4013.16
ANC32.0000.00053 | 0 | 52732.18
ANC32.0000.00055 | 0 | 6325.04
ANC32.0000.00060 | 0 | 4119.43
ANC32.0000.00061 | 0 | 4824.51
ANC32.0000.00062 | 0 | 847.97
ANC32.0000.00064 | 0 | 752.02
ANC32.0000.00065 | 0 | 5732.51
ANC32.0000.00066 | 0 | 4746.17
ANC32.0000.00067 | 0 | 4721.53
ANC32.0000.00069 | 0 | 523.95
ANC32.0000.00070 | 0 | 4126.3
ANC32.0000.00072 | 0 | 4739.55
ANC32.0000.00073 | 0 | 1654.69
ANC32.0000.00074 | 0 | 6187.75
ANC32.0000.00079 | 0 | 0
ANC32.0000.00080 | 0 | 1680.46
ANC32.0000.00082 | 0 | 109530.33
ANC32.0000.00087 | 0 | 2816.02
ANC32.0000.00088 | 0 | 2781.28
ANC32.0000.00089 | 0 | 15303.77
ANC32.0000.00090 | 0 | 2998.84
ANC32.0000.00092 | 0 | 3004.9
ANC32.0000.00094 | 0 | 21884.96
ANC32.0000.00101 | 0 | 80456.84
ANC32.0000.00107 | 0 | 5051.47
ANC32.0000.00109 | 0 | 1508.07
ANC32.0000.00110 | 0 | 6716.07
ANC32.0000.00111 | 0 | 2666.67
ANC32.0000.00112 | 0 | 5142.92
ANC32.0000.00113 | 0 | 456.5
ANC32.0000.00122 | 0 | 6792.46
ANC32.0000.00123 | 0 | 13157.5
ANC32.0000.00124 | 0 | 20617.11
ANC32.0000.00126 | 0 | 8521.83
ANC32.0000.00127 | 178.67 | 14941.24
ANC32.0000.00128 | 0 | 1799.98
ANC32.0000.00130 | 0 | 1980
ANC32.0000.00131 | 0 | 13743.6
ANC32.0000.00132 | 0 | 11803.01
ANC32.0000.00133 | 0 | 3380.13
ANC32.0000.00136 | 0 | 8156.02
ANC32.0000.00137 | 0 | 59384.05
ANC32.0000.00139 | 0 | 3648.09
ANC32.0000.00156 | 0 | 116.6
ANC32.0000.00158 | 0 | 16207.35
ANC32.0000.00162 | 0 | 279.67
ANC32.0000.00165 | 0 | 22236.34
ANC32.0000.00167 | 0 | 3563.82
ANC32.0000.00171 | 0 | 116.6
ANC32.0000.00174 | 0 | 571963.35
ANC32.0000.00176 | 0 | -329.95
ANC32.0000.00177 | 0 | 269020.5
ANC32.0000.00178 | 0 | 344971.35
ANC32.0000.00181 | 0 | 8107.65
ANC32.0000.00184 | 0 | 566005.26
ANC32.0000.00187 | 0 | 10225.45
ANC32.0000.00189 | 0 | 2706.98
ANC32.0000.00191 | 0 | 116.6
ANC32.0000.00192 | 0 | 400459.48
ANC32.0000.00193 | 0 | 80401.8
ANC32.0000.00195 | 1 | 1061.2
ANC32.0000.00196 | 0 | 10814.78
ANC32.0000.00197 | 0 | 1721.37
ANC32.0000.00202 | 1 | 475
ANC32.0000.00206 | 0 | 5517.82
ANC32.0000.00207 | 0 | 2223.65
ANC32.0000.00209 | 0 | 959.93
ANC32.0000.00222 | 0 | 16588.53
ANC32.0000.00226 | 0 | 3601.89
ANC32.0000.00229 | 0 | 4697.77
ANC32.0000.00230 | 0 | 2472.49
ANC32.0000.00231 | 0 | 328.02
ANC32.0000.00234 | 0 | -333.3
ANC32.0000.00235 | 0 | 3244.76
ANC32.0000.00237 | 0 | 8722.12
ANC32.0000.00238 | 0 | 709.8
ANC32.0000.00239 | 0 | 4574.65
ANC32.0000.00241 | 0 | 24.2
ANC32.0000.00244 | 0 | 3125.9
ANC32.0000.00247 | 0 | 1375.31
ANC32.0000.00248 | 0 | 1889.66
ANC32.0000.00249 | 0 | 288.18
ANC32.0000.00252 | 0 | 116711.13
ANC32.0000.00253 | 0 | 4349.7
ANC32.0000.00254 | 0 | 6108.51
ANC32.0000.00255 | 0 | 10345.19
ANC32.0000.00258 | 0 | 12980.95
ANC32.0000.00259 | 0 | 6659.91
ANC32.0000.00261 | 0 | 2600.01
ANC32.0000.00262 | 0 | 16451.01
ANC32.0000.00265 | 0 | 6723.58
ANC32.0000.00266 | 0 | 13085.86
ANC32.0000.00267 | 0 | 5556.87
ANC32.0000.00268 | 0 | 1853.11
ANC32.0000.00269 | 0 | 4364.41
ANC32.0000.00270 | 0 | 4799.74
ANC32.0000.00272 | 0 | 4697.3
ANC32.0000.00273 | 0 | 84155.23
ANC32.0000.00276 | 0 | 4566.56
ANC32.0000.00277 | 1 | 21232.26
ANC32.0000.00278 | 0 | 1676.06
ANC32.0000.00279 | 0 | 2389.03
ANC32.0000.00280 | 0 | 82366.97
ANC32.0000.00283 | 0 | 1175.54
ANC32.0000.00284 | 0 | 3536.68
ANC32.0000.00287 | 0 | 2315.97
ANC32.0000.00290 | 0 | 6231.53
ANC32.0000.00291 | 0 | 1812.91
ANC32.0000.00297 | 0 | 10224.57
ANC32.0000.00298 | 0 | 2811.87
ANC32.0000.00299 | 0 | 2822.66
ANC32.0000.00300 | 0 | 22578.79
ANC32.0000.00301 | 1 | 78916.1
ANC32.0000.00302 | 0 | 3653.42
ANC32.0000.00334 | 0 | 0
ANC32.0000.00364 | 11311.59 | 2524.7
ANC32.0000.00383 | 0 | 0
BET32.0000.00002 | 0 | 12009.44
BET32.0000.00011 | 0 | 2018.47
BET32.0000.00016 | 0 | 4736.69
BET32.0000.00017 | 0 | 1102.7
BET32.0000.00020 | 0 | 27623.39
BET32.0000.00021 | 0 | 102739.93
BET32.0000.00039 | 0 | 13871.41
BET32.0000.00040 | 0 | 7598.07
BET32.0000.00043 | 0 | 6280.76
BET32.0000.00048 | 0 | 577.39
BET32.0000.00063 | 0 | 0
GRT32.0000.00003 | 0 | 0
GRT32.0000.00004 | 0 | 0
GRT32.0000.00005 | 0 | 24550.76
GRT32.0000.00013 | 0 | 8507.52
GRT32.0000.00015 | 0 | 29995.76
GRT32.0000.00017 | 0 | 59974.8
GRT32.0000.00018 | 0 | 26876.53
GRT32.0000.00019 | 0 | 92698.16
GRT32.0000.00023 | 0 | 22820.46
GRT32.0000.00024 | 0 | 6607.39
GRT32.0000.00025 | 0 | 7578.53
GRT32.0000.00026 | 0 | 10703.61
GRT32.0000.00027 | 0 | 46770.14
GRT32.0000.00038 | 0 | 24207.76
GRT32.0000.00046 | 0 | 32023.98
GRT32.0000.00047 | 0 | 43855.25
GRT32.0000.00048 | 0 | 20413.05
GRT32.0000.00049 | 0 | 23934.84
GRT32.0000.00050 | 0 | 18665.67
GRT32.0000.00051 | 0 | 16053.74
GRT32.0000.00052 | 0 | 14353.53
GRT32.0000.00053 | 0 | 27451.39
GRT32.0000.00054 | 0 | 20415.57
GRT32.0000.00057 | 0 | 15229.56
GRT32.0000.00058 | 0 | 29842.78
GRT32.0000.00059 | 0 | 20757.3
GRT32.0000.00060 | 0 | 11652.49
GRT32.0000.00061 | 0 | 38937.28
GRT32.0000.00068 | 0 | 7990.65
GRT32.0000.00082 | 0 | 31681.55
GRT32.0000.00084 | 0 | 102021.49
GRT32.0000.00085 | 0 | 51672.95
GRT32.0000.00086 | 0 | 29483.1
GRT32.0000.00090 | 0 | 98246.22
GRT32.0000.00095 | 0 | 222206.91
GRT32.0000.00098 | 1 | 20000
GRT32.0000.00099 | 0 | 36755.9
GRT32.0000.00100 | 0 | 8024.52
GRT32.0000.00101 | 0 | 17818.52
GRT32.0000.00102 | 0 | 86676.99
GRT32.0000.00103 | 0 | 7979.42
GRT32.0002.00002 | 2.72 | 0
PIG32.0000.00009 | 0 | 79739.32
PIG32.0000.00010 | 0 | 21820.66
PIG32.0000.00012 | 0 | 47284.21
PIG32.0000.00017 | 0 | 1335.37
PIG32.0000.00022 | 0 | 2689.01
PIG32.0000.00023 | 0 | 2673.58
PIG32.0000.00026 | 0 | 567165.08
PIG32.0000.00027 | 0 | 23594.6
PIG32.0000.00031 | 0 | 34230.57
PIG32.0000.00032 | 0 | 19746.4
PIG32.0000.00033 | 0 | 36869.35
PIG32.0000.00035 | 1 | 702.42
PIG32.0000.00037 | 0 | 38247.65
PIG32.0000.00038 | 0 | 122100.73
PIG32.0000.00041 | 0 | 25600.79
PIG32.0000.00044 | 0 | 10100.83
PIG32.0000.00045 | 0 | 40201.17
PIG32.0000.00046 | 0 | 17111.71
PIG32.0000.00047 | 0 | 59178.63
PIG32.0000.00050 | 0 | 39248.49
PIG32.0000.00053 | 0 | 0
Grand Total | 11498.98 | 6929649.07

## SAP Data (hidden)
Location | City | Description | Order | WBS order header | System status | User Status | MaintActivityType | Total planned costs | Total actual costs | Basic start date | Basic finish date | Actual start date | Final Due Date | Entered By
2621 | LEXINGTON | FACILITY DAMAGE MAIN LINE 253320172 | 4000094590 | ANC32.0000.00001 | REL MANC PRC SETC | NEW ADJ FCMP NSFS RCFO REIM | MAI | 850.94 | 2600.23 | 2025-11-28 | 2025-11-29 |  |  | BTC_ALL
2629 | PARIS | Leak Repair | 4000096451 | ANC32.0000.00001 | CRTD MANC PRC | NEW NSFS RCFO | MAI | 633.18 | 0 | 2026-01-01 | 2026-01-22 |  | 2026-01-22 | BTC_ALL
2629 | PARIS | Leak Repair | 4000096519 | ANC32.0000.00001 | CRTD MANC PRC | NEW NSFS RCFO | MAI | 633.18 | 0 | 2026-01-01 | 2026-01-22 |  | 2026-01-22 | BTC_ALL
2629 | PARIS | Leak Repair | 4000096531 | ANC32.0000.00001 | CRTD MANC PRC | NEW NSFS RCFO | MAI | 633.18 | 0 | 2026-01-01 | 2026-01-22 |  | 2026-01-22 | BTC_ALL
2629 | PARIS | Leak Repair | 4000096657 | ANC32.0000.00001 | CRTD MANC PRC | NEW NSFS RCFO | MAI | 633.18 | 0 | 2026-01-01 | 2026-01-22 |  | 2026-01-22 | BTC_ALL
2629 | PARIS | Leak Repair | 4000096746 | ANC32.0000.00001 | CRTD MANC PRC | NEW NSFS RCFO | MAI | 633.18 | 0 | 2026-01-01 | 2026-01-22 |  | 2026-01-22 | BTC_ALL
2629 | PARIS | Leak Repair | 4000096859 | ANC32.0000.00001 | CRTD MANC PRC | NEW NSFS RCFO | MAI | 633.18 | 0 | 2026-01-01 | 2026-01-22 |  | 2026-01-22 | BTC_ALL
2629 | PARIS | Leak Repair | 4000096962 | ANC32.0000.00001 | CRTD MANC PRC | NEW NSFS RCFO | MAI | 633.18 | 0 | 2026-01-01 | 2026-01-22 |  | 2026-01-22 | BTC_ALL
2621 |  | FCLTY DMG MAIN LINE | 4000097062 | ANC32.0000.00001 | REL MANC NMAT PRC SETC | NEW FCMP MIFE NSFS RCFO REIM | MAI | 710.28 | 682.01 | 2026-01-23 | 2026-01-23 |  |  | BTC_ALL
2621 | LEXINGTON | Repair Distribution Main | 4000097116 | ANC32.0000.00001 | REL MANC NMAT PRC SETC | NEW FCMP MIFE NSFS RCFO | MAI | 847.8 | 110.81 | 2026-01-27 | 2026-01-28 |  | 2026-01-28 | BTC_ALL
2621 | LEXINGTON | Repair Distribution Main | 4000097292 | ANC32.0000.00001 | REL MANC NMAT PRC SETC | NEW FCMP MIFE NSFS RCFO | MAI | 847.8 | 93.47 | 2026-01-26 | 2026-01-27 |  | 2026-01-27 | BTC_ALL
2623 | GEORGETOWN | Repair Distribution Main | 4000097293 | ANC32.0000.00001 | REL MANC NMAT PRC SETC | NEW FCMP MIFE NSFS RCFO | MAI | 847.8 | 131.32 | 2026-01-28 | 2026-01-29 |  | 2026-01-29 | BTC_ALL
2621 |  | Leak Repair | 4000098701 | ANC32.0000.00001 | REL CSER MANC NMAT PRC SETC | NEW FCMP MIFE NSFS RCFO | MAI | 847.8 | 0 | 2025-07-08 | 2025-07-23 |  | 2025-07-23 | BTC_ALL
2623 | GEORGETOWN | REPAIR DIST MAIN - 1202 OLD OXFORD RD GE | 4000098702 | ANC32.0000.00001 | REL MANC NMAT PRC SETC | NEW FCMP MIFE NSFS RCFO | MAI | 2268.56 | 469.01 | 2025-10-01 | 2025-10-02 |  | 2025-10-02 | BTC_ALL
2621 |  | MAINTENANCE OF MAIN | 4000098900 | ANC32.0000.00001 | REL MANC NMAT PRC SETC | NEW FCMP MIFE NSFS RCFO | MAI | 1913.42 | 0 | 2025-10-23 | 2025-12-22 |  | 2026-01-21 | BTC_ALL
2631 | Ashland | Leak Repair/NO PRMT REQURIED | 4000098958 | ANC32.0000.00001 | CRTD MANC PRC | NEW NSFS RCFO | MAI | 251.46 | 0 | 2026-02-13 | 2026-03-06 |  | 2026-03-06 | BTC_ALL
2621 | LEXINGTON | Leak Repair/NO PRMT REQUIRED | 4000100375 | ANC32.0000.00001 | CRTD MANC PRC | NEW NSFS RCFO | MAI | 522.79 | 0 | 2026-02-09 | 2027-02-04 |  | 2027-05-05 | BTC_ALL
2631 | ASHLAND | FCLTY DMG MAIN LINE/PRMT RCVD | 4000100428 | ANC32.0000.00001 | REL CSER MANC NMAT PRC SETC | NEW FCMP MIFE NSFS RCFO REIM | MAI | 536.46 | 2352.46 | 2026-03-20 | 2026-03-20 |  |  | BTC_ALL
2629 | PARIS | Repair Distribution Main | 4000101419 | ANC32.0003.00911 | REL CSER MANC NMAT PRC SETC | NEW FCMP MIFE NSFS RCFO | MAI | 2497.44 | 8.13 | 2026-01-27 | 2026-02-17 |  | 2026-02-17 | BTC_ALL
2629 | PARIS | Repair Distribution Main | 4000101420 | ANC32.0003.00911 | REL CSER MANC NMAT PRC SETC | NEW FCMP MIFE NSFS RCFO | MAI | 932.32 | 4.65 | 2026-01-27 | 2027-01-22 |  | 2027-04-22 | BTC_ALL
2621 | LEXINGTON | Reset/Raise/Lower/Replace Vlv Box | 4000101841 | ANC32.0003.00911 | CRTD MANC NMAT PRC | NEW NSFS RCFO | MAI | 125.84 | 0 | 2026-02-27 | 2026-05-02 |  | 2026-05-02 | BTC_ALL
2623 | FRANKFORT | Leak Repair/NO PRMT REQUIRED | 4000102257 | ANC32.0003.00911 | CRTD MANC PRC | NEW NSFS RCFO | MAI | 283.72 | 0 | 2026-02-15 | 2027-01-11 |  | 2027-02-10 | BTC_ALL
2621 |  | REPAIR MAIN - 144 TURNER COMMONS WAY | 4000103401 | ANC32.0003.00911 | REL MANC NMAT PRC SETC | NEW FCMP MIFE NSFS RCFO | MAI | 22979.53 | 0 | 2025-11-18 | 2025-12-18 |  | 2025-12-18 | BTC_ALL
2621 |  | CNV-24026316800 RETIRE 9920' OF 4\\\"/6. | 4000073963 | ANC32.0000.00252 | REL MANC NMAT PRC SETC | NEW REV WENG | MAI | 0 | 0 | 2024-12-31 | 2024-12-31 |  | 2024-12-31 | C_U139391
2633 |  | CNV-24026317800 EMER - INSTALL 5'-2\\\. | 4000073964 | ANC32.0000.00253 | REL PCNF MANC NMAT PRC SETC | NEW REV | MAI | 0 | 4186.94 | 2024-12-31 | 2024-12-31 | 2025-07-31 | 2025-08-08 | C_U139391
2633 |  | CNV-24026317900 EMER - RETIRE 5'-2\" PIP | 4000073965 | ANC32.0000.00253 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 162.76 | 2024-12-31 | 2024-12-31 | 2025-07-31 | 2025-08-08 | C_U139391
2621 |  | CNV-24026348300 RETIRE ~30'-4\" PMMP | 4000073966 | BET32.0000.00002 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2834.93 | 2024-12-31 | 2024-12-31 | 2025-08-01 | 2025-02-28 | C_U139391
2621 |  | CNV-24026348800 EMER-LEAK RETIRE C14-37 | 4000073967 | ANC32.0000.00272 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 693.83 | 2024-12-31 | 2024-12-31 | 2025-08-01 | 2024-12-31 | C_U139391
2621 |  | CNV-24026365100 EMER-RETIRE 10' - 2\" PM | 4000073976 | ANC32.0000.00287 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 7.6 | 2024-12-31 | 2024-12-31 | 2025-08-01 | 2024-12-31 | C_U139391
2631 |  | CNV-24026371300 EMER - INSTALL 1'-2\" PM | 4000073977 | ANC32.0000.00087 | REL NMAT PRC SETC | NEW NSFS REV | MAI | 0 | 2816.02 | 2024-12-31 | 2024-12-31 |  | 2024-12-31 | C_U139391
2621 |  | CNV-24026371600 EMER - INSTALL 5' - 2\" | 4000073978 | ANC32.0000.00088 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2756.63 | 2024-12-31 | 2024-12-31 | 2025-08-03 | 2025-07-01 | C_U139391
2621 |  | CNV-24026371700 EMER - RETIRE 5' - 2\" P | 4000073979 | ANC32.0000.00088 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 24.65 | 2024-12-31 | 2024-12-31 |  | 2025-07-01 | C_U139391
2621 |  | CNV-24026310500 RETIRE VALVE & 5' OF 2\" | 4000073998 | BET32.0000.00040 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2024-12-31 | 2024-12-31 |  | 2024-12-31 | C_U139391
2629 |  | CNV-24026310700 ABANDON ~ 150'- 2\" CSIP | 4000073999 | BET32.0000.00048 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 577.39 | 2024-12-31 | 2024-12-31 | 2025-07-31 | 2024-12-31 | C_U139391
2631 |  | CNV-24026354400 INSTALL 20'-4\" PMLP | 4000074002 | ANC32.0000.00002 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1.86 | 2024-12-31 | 2024-12-31 |  | 2024-12-31 | C_U139391
2621 |  | CNV-24026330300 EMER - INSTALL 5'- 2\" P | 4000074003 | ANC32.0000.00259 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6479.76 | 2024-12-31 | 2024-12-31 | 2025-07-31 | 2025-08-24 | C_U139391
2621 |  | CNV-24026330400 EMER-RETIRE 5'-2\"PMMP | 4000074004 | ANC32.0000.00259 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 180.15 | 2024-12-31 | 2024-12-31 | 2025-07-31 | 2025-08-24 | C_U139391
2629 |  | CNV-17026724700 RETIRE 350' - 3\" PMLP | 4000074081 | BET32.0000.00014 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6408.49 | 2023-12-29 | 2023-12-31 | 2025-07-31 | 2023-12-31 | C_U139391
2631 |  | CNV-18026794000 RETIRE 4748'-2\"/3\"/4\" | 4000074109 | ANC32.0000.00156 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 116.6 | 2024-12-31 | 2024-12-31 |  | 2023-12-31 | C_U139391
2631 |  | CNV-19026913100 RETIRE 705'-2/3/4\" BS/P | 4000074117 | ANC32.0000.00001 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 116.6 | 2024-12-31 | 2024-12-31 |  | 2024-12-31 | C_U139391
2632 |  | CNV-21026127100 RETIRE 9400'-2\"&4\" BS& | 4000074120 | ANC32.0000.00168 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 2023-12-31 | C_U139391
2631 |  | CNV-21026130500 RETIRE 25,000' OF BSLP M | 4000074121 | ANC32.0000.00167 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1026.35 | 2023-12-29 | 2023-12-31 | 2025-07-31 | 2024-12-08 | C_U139391
2629 |  | CNV-21026140501 INSTALL 1,985'-6\" CSHP | 4000074122 | ANC32.0000.00189 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 2023-12-31 | C_U139391
2629 |  | CNV-21026140600 RETIRE 2,598'- 6\" BSHP | 4000074123 | ANC32.0000.00189 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 2023-12-31 | C_U139391
2631 |  | CNV-21026154800 RETIRE 35'-3\" CSMP | 4000074124 | ANC32.0000.00167 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 2023-12-31 | C_U139391
2621 |  | CNV-21026997900 RETIRE 6300' OF 4\"/6\"C | 4000074125 | ANC32.0000.00164 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 2024-08-31 | C_U139391
2631 |  | CNV-20026978200 RETIRE 8983' LP - 2520' | 4000074158 | ANC32.0000.00161 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 233.2 | 2023-12-29 | 2023-12-31 |  | 2023-12-31 | C_U139391
2631 |  | CNV-20026983400 RETIRE 5374'-4\" BSLP/CS | 4000074159 | ANC32.0000.00002 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 92.88 | 2023-12-29 | 2023-12-31 |  | 2024-12-31 | C_U139391
2631 |  | CNV-20026983600 ABANDON 1667'-2/3/4\" PM | 4000074160 | ANC32.0000.00162 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 290.24 | 2023-12-29 | 2023-12-31 | 2025-07-30 | 2023-12-31 | C_U139391
2629 |  | CNV-22026230500 RETIRE 1,368' - MP MAIN | 4000074332 | ANC32.0000.00190 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 2023-12-31 | C_U139391
2621 |  | CNV-22026231400 RETIRE 975' OF 8\"BSLP M | 4000074333 | ANC32.0000.00191 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 116.6 | 2024-12-31 | 2024-12-31 |  | 2024-12-31 | C_U139391
2623 |  | CNV-22026235400 RETIRE 2111'- 2\",4\",6\ | 4000074334 | ANC32.0000.00192 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 233.2 | 2024-12-31 | 2024-12-31 |  | 2024-12-31 | C_U139391
2629 |  | CNV-22026237900 RETIRE 5,265' IP MAIN | 4000074335 | ANC32.0000.00196 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2024-12-31 | 2024-12-31 |  | 2024-12-31 | C_U139391
2621 |  | CNV-22026241600 RETIRE 30'-2\" PMMP | 4000074336 | BET32.0000.00031 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 2023-12-31 | C_U139391
2621 |  | CNV-22026163300 RETIRE 800' OF 4\"BSLP M | 4000074354 | ANC32.0000.00173 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 2023-12-31 | C_U139391
2629 |  | CNV-22026164100 RETIRE 6,711'-BS/CS IP | 4000074355 | ANC32.0000.00174 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 663.38 | 2023-12-29 | 2023-12-31 | 2025-07-31 | 2024-12-31 | C_U139391
2629 |  | CNV-22026164300 RETIRE 3,574'-BSLP | 4000074356 | ANC32.0000.00175 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 136.8 | 2023-12-29 | 2023-12-31 |  | 2023-12-31 | C_U139391
2621 |  | CNV-22026165600 RETIRE 2715'-BSLP & 425' | 4000074357 | ANC32.0000.00176 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | -329.95 | 2024-12-31 | 2024-12-31 | 2025-08-01 | 2024-12-31 | C_U139391
2621 |  | CNV-22026224300 RETIRE 4500' OF 6\"/4\"B | 4000074373 | ANC32.0000.00187 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2313.44 | 2024-12-31 | 2024-12-31 |  | 2024-12-31 | C_U139391
2631 |  | CNV-22026172400 RETIRE 4792'-2/4/8\" PL/ | 4000074374 | ANC32.0000.00181 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 233.2 | 2023-12-29 | 2023-12-31 |  | 2024-12-31 | C_U139391
2621 |  | CNV-22026183200 RETIRE 3765' OF 2-4\" CS | 4000074375 | PIG32.0000.00027 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 2023-12-31 | C_U139391
2621 |  | CNV-22026183400 RETIRE 702' OF 6\" BSHP | 4000074376 | PIG32.0000.00027 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 233.2 | 2023-12-29 | 2023-12-31 |  | 2023-12-31 | C_U139391
2631 |  | CNV-22026207200 RETIRE 6009'-2\",3\", 4\ | 4000074377 | ANC32.0000.00184 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 872.75 | 2024-12-31 | 2024-12-31 | 2025-08-01 | 2025-08-15 | C_U139391
2621 |  | CNV-22026213000 RETIRE 2015'-8/4/2\" BSM | 4000074378 | ANC32.0000.00177 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 233.2 | 2023-12-29 | 2023-12-31 |  | 2023-12-31 | C_U139391
2621 |  | CNV-22026219500 RETIRE 380' OF 4\"BSMP M | 4000074379 | ANC32.0000.00186 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 91.2 | 2023-12-29 | 2023-12-31 |  | 2023-12-31 | C_U139391
2629 |  | CNV-23026248800 RETIRE 50' - 2\" CSMP | 4000074671 | BET32.0000.00033 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 2023-12-31 | C_U139391
2621 |  | CNV-23026264800 RETIRE 100' OF 3\"BSLP M | 4000074672 | ANC32.0000.00220 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 2024-08-11 | C_U139391
2623 |  | CNV-23026268600 PM-DE LINE ILI PH2 DENT | 4000074673 | BET32.0000.00032 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 798261.74 | 2023-12-29 | 2023-12-31 |  | 2023-12-31 | C_U139391
2629 |  | CNV-23026268700 PM-DE LINE PH 2 DENT 2/S | 4000074674 | BET32.0000.00032 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 92219 | 2023-12-29 | 2023-12-31 |  | 2023-12-31 | C_U139391
2623 |  | CNV-23026269200 PM-DE LINE ILI PH2 BEND | 4000074675 | BET32.0000.00032 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 130268.57 | 2023-12-29 | 2023-12-29 |  | 2023-12-31 | C_U139391
2623 |  | CNV-23026269300 PM-DE LINE ILI PH2 DENT | 4000074676 | BET32.0000.00032 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1444.19 | 2023-12-29 | 2023-12-29 | 2025-07-31 | 2023-12-31 | C_U139391
2629 |  | CNV-23026269400 PM-DE LINE ILI PH2 DENT2 | 4000074677 | BET32.0000.00032 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 26843.67 | 2023-12-29 | 2023-12-29 |  | 2023-12-31 | C_U139391
2631 |  | CNV-23026270300 EMER - INSTALL 2'-4\" PM | 4000074678 | BET32.0000.00035 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-29 |  | 2023-12-30 | C_U139391
2631 |  | CNV-23026270400 EMER - RETIRE 110'-4\" P | 4000074679 | BET32.0000.00035 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-29 |  | 2023-12-30 | C_U139391
2631 |  | CNV-23026271400 EMER - INSTALL ~5'-2\" P | 4000074680 | ANC32.0000.00224 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 2023-12-31 | C_U139391
2631 |  | CNV-23026271500 EMER - RETIRE ~5'-2\" PM | 4000074681 | ANC32.0000.00224 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 2023-12-31 | C_U139391
2631 |  | CNV-23026277700 RETIRE 2881'-12\" BSMP | 4000074682 | ANC32.0000.00230 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 440.15 | 2023-12-29 | 2023-12-31 | 2025-07-31 | 2023-12-31 | C_U139391
2631 |  | CNV-23026277800 RETIRE RECTIFIER | 4000074683 | ANC32.0000.00230 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2472.49 | 2024-12-31 | 2024-12-31 | 2025-07-31 | 2024-12-31 | C_U139391
2621 |  | CNV-23026280100 RETIRE 10' OF 10\"CSMP M | 4000074684 | ANC32.0000.00115 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 290.02 | 2023-12-29 | 2023-12-31 |  | 2023-12-31 | C_U139391
2631 |  | CNV-23026283600 INSTALL LP FITTINGS | 4000074685 | ANC32.0000.00184 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4179.66 | 2024-12-31 | 2024-12-31 | 2025-07-31 | 2024-12-31 | C_U139391
2621 |  | CNV-23026287700 RETIRE ~30'-4\" PMP | 4000074686 | BET32.0000.00038 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6450.91 | 2023-12-29 | 2023-12-31 |  | 2024-12-25 | C_U139391
2621 |  | CNV-23026294500 RETIRE 338' OF 4\"BSLP M | 4000074687 | BET32.0000.00015 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6590.43 | 2023-12-29 | 2023-12-31 | 2025-07-31 | 2023-12-31 | C_U139391
2623 |  | CNV-23026294600 ABANDON ~790'-2\" PMMP | 4000074688 | GRT32.0000.00001 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 2023-12-31 | C_U139391
2629 |  | CNV-23026297000 INSTALL PCF'S LP | 4000074689 | ANC32.0000.00003 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 2023-12-31 | C_U139391
2629 |  | CNV-23026301900 RETIRE RECTIFIER/GROUND | 4000074690 | ANC32.0000.00301 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 71.7 | 2024-12-31 | 2024-12-31 | 2025-07-31 | 2024-12-31 | C_U139391
2621 |  | CNV-23026304100 RETIRE 667' OF 2\"PMMP M | 4000074691 | PIG32.0000.00017 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4671.25 | 2023-12-29 | 2023-12-31 | 2025-07-31 | 2023-12-31 | C_U139391
2631 |  | CNV-23026305600 RETIRE RECTIFIER | 4000074692 | ANC32.0000.00167 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1383.22 | 2024-12-31 | 2024-12-31 | 2025-07-31 | 2024-12-31 | C_U139391
2631 |  | CNV-23026305700 RETIRE RECTIFIER | 4000074693 | ANC32.0000.00167 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2180.6 | 2024-12-31 | 2024-12-31 | 2025-07-31 | 2024-12-31 | C_U139391
2631 |  | CNV-25026404300 INSTALL 80' OF 2\" PMMP | 4000075685 | GRT32.0000.00074 | REL MANC PRC SETC | NPRG ADJ FCMP | MAI | 33570.17 | 6906.46 | 2025-08-12 | 2025-08-31 |  |  | C_U139391
2629 |  | CNV-25026406000 EMER - INSTALL 2'-2\" PM | 4000075687 | ANC32.0000.00151 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 2561.78 | 2025-04-11 | 2025-04-18 |  | 2025-04-18 | C_U139391
2629 |  | CNV-25026406100 EMER - RETIRE 2'-2\" PML | 4000075689 | ANC32.0000.00151 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 29.09 | 2025-04-17 | 2025-04-18 | 2025-08-03 | 2025-04-18 | C_U139391
2621 |  | WILSON ST SMRP - CNV-24026315000 | 4000075741 | ANC32.0000.00250 | REL PCNF GMPS MANC PRC SETC | COCO FCMP | MAI | 49600.16 | 135400.19 | 2025-10-21 | 2025-12-31 | 2025-08-03 | 2025-12-31 | C_U139391
2629 |  | ANC-SMRP Horseshoe Dr-Paris | 4000075743 | ANC32.0000.00251 | REL PCNF GMPS MANC PRC SETC | SCHD ADJ FCMP WGMA | MAI | 1377904 | 3912671.17 | 2025-07-24 | 2025-12-31 | 2026-03-16 | 2026-12-31 | C_U139391
2629 |  | CNV-25026409900 EMER - INSTALL 10'-2\" P | 4000075744 | SUP32.0002.00001 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 6262 | 2025-05-08 | 2025-05-08 |  | 2025-05-19 | C_U139391
2621 |  | FAYETTE PARK 2025 SMRP CNV-24026317600 | 4000075745 | ANC32.0000.00141 | REL PCNF GMPS MANC PRC SETC | NPRG ADJ | MAI | 51053.85 | 232457.82 | 2025-11-04 | 2025-12-31 | 2025-08-03 | 2025-12-31 | C_U139391
2623 |  | SMRP - MOCKINGBIRD | 4000075747 | ANC32.0000.00058 | REL PCNF GMPS MANC PRC SETC | NPRG ADJ MIFE | MAI | 1413114.51 | 1399970.23 | 2025-08-01 | 2025-08-01 | 2026-03-23 | 2026-05-01 | C_U139391
2621 |  | CNV-24026318600 EMER - INSTALL 11' OF 2\ | 4000075749 | ANC32.0000.00254 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 5951.21 | 2024-03-26 | 2024-03-31 | 2025-07-31 | 2024-03-31 | C_U139391
2621 |  | CNV-24026318700 EMER - RETIRE 11' OF 2\" | 4000075751 | ANC32.0000.00254 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 157.3 | 2024-03-28 | 2024-03-31 | 2025-07-31 | 2024-03-31 | C_U139391
2631 |  | ANC - SMRP FLOYD STREET - ASHLAND | 4000075753 | ANC32.0000.00256 | REL GMPS MANC PRC SETC | NPRG ADJ FCMP MEQD WGMA | MAI | 242958.47 | 3291186.21 | 2025-07-17 | 2025-12-31 |  | 2026-12-31 | C_U139391
2631 |  | ANC-BBQ HOLLOW HP SMRP-ASHLAND | 4000075755 | ANC32.0000.00267 | REL NMAT PRC SETC | NEW NSFS | MAI | 0 | 0 | 2025-01-23 | 2025-01-31 |  | 2026-12-31 | C_U139391
2621 |  | CNV-24026342000 EMER - INSTALL 2' OF 2\" | 4000075756 | ANC32.0000.00268 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1762.13 | 2024-05-31 | 2024-05-31 |  | 2024-05-31 | C_U139391
2621 |  | CNV-24026342100 EMER - RETIRE 2' OF 2\"P | 4000075758 | ANC32.0000.00268 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 90.98 | 2024-05-31 | 2024-05-31 | 2025-07-31 | 2024-05-31 | C_U139391
2621 |  | CNV-24026343300 INSTALL 4\" POLY VALVE | 4000075780 | BET32.0000.00043 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 5484.09 | 2024-10-31 | 2024-11-01 | 2025-07-31 | 2024-11-01 | C_U139391
2621 |  | CNV-24026343400 RETIRE 4\"POLY VALVE C19 | 4000075782 | BET32.0000.00043 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 796.67 | 2024-11-01 | 2024-11-01 | 2025-07-31 | 2024-11-01 | C_U139391
2629 |  | ANC-Wilson Ln Abandonment-Winchester | 4000075784 | ANC32.0000.00143 | REL MANC PRC SETC | NPRG ADJ FCMP MIFE WGMA | MAI | 30868.63 | 1973.6 | 2025-12-30 | 2025-12-31 |  | 2025-12-31 | C_U139391
2621 |  | CNV-24026345300 RETIRE 350' OF 4\"CSLP M | 4000075786 | BET32.0000.00016 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4736.69 | 2024-09-30 | 2024-10-01 | 2025-08-01 | 2024-10-01 | C_U139391
2621 |  | CNV-24026346300 EMER-INSTALL 3' OF 2\"PM | 4000075788 | ANC32.0000.00269 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4206.97 | 2024-09-30 | 2024-10-01 | 2025-08-01 | 2024-10-01 | C_U139391
2621 |  | CNV-24026346400 EMER-RETIRE 3' OF 2\"PMM | 4000075790 | ANC32.0000.00269 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 157.44 | 2024-10-01 | 2024-10-01 | 2025-08-01 | 2024-10-01 | C_U139391
2621 |  | CNV-24026346600 EMER-INSTALL 8' OF 4\"PM | 4000075792 | ANC32.0000.00270 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4789.73 | 2024-09-26 | 2024-09-26 | 2025-08-01 | 2024-09-28 | C_U139391
2621 |  | CNV-24026346700 EMER-RETIRE 8' OF 4\"PML | 4000075794 | ANC32.0000.00270 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 10.01 | 2024-08-30 | 2024-08-30 | 2025-08-01 | 2024-09-28 | C_U139391
2621 |  | CNV-24026348000 EMER-INSTALL 4' OF 3\"PM | 4000075796 | ANC32.0000.00073 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1654.69 | 2024-06-10 | 2024-06-10 | 2025-08-01 | 2024-09-28 | C_U139391
2621 |  | CNV-24026348200 INSTALL ~30'-4\" PMMP | 4000075798 | BET32.0000.00002 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 9174.51 | 2024-12-27 | 2024-12-31 | 2025-08-01 | 2025-02-28 | C_U139391
2621 |  | CNV-24026348700 EMER - INSTALL 5' OF 2\" | 4000075820 | ANC32.0000.00272 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4003.47 | 2024-12-30 | 2024-12-31 |  | 2024-12-31 | C_U139391
2621 |  | CNV-24026350500 EMER-INSTALL 2\"VALVE KY | 4000075823 | BET32.0000.00011 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2018.47 | 2024-09-30 | 2024-10-01 | 2025-08-01 | 2024-10-01 | C_U139391
2629 |  | ANC-SMRP Camelot Dr IP-Winchester | 4000075824 | ANC32.0000.00005 | REL GMPS MANC PRC SETC | NPRG ADJ | MAI | 40844.66 | 95096.44 | 2025-07-21 | 2025-12-31 |  | 2025-12-31 | C_U139391
2621 |  | CNV-24026351400 EMER - INSTALL 2'-2\" PM | 4000075826 | ANC32.0000.00275 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 1375.93 | 2025-03-31 | 2025-03-31 | 2025-08-01 | 2025-03-31 | C_U139391
2631 |  | CNV-20026952500 REPLACE VALVE C-16 | 4000075827 | BET32.0000.00028 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-12 | 2023-12-25 |  | 2023-12-25 | C_U139391
2621 |  | CNV-24026351500 EMER - RETIRE 2'-2\" PMP | 4000075828 | ANC32.0000.00275 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 14.2 | 2025-03-31 | 2025-03-31 | 2025-08-01 | 2025-03-31 | C_U139391
2631 |  | CNV-20026952600 RETIRE VALVE C-16 | 4000075829 | BET32.0000.00028 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-21 | 2023-12-25 |  | 2023-12-25 | C_U139391
2621 |  | CNV-24026351800 EMER-INSTALL 8' OF 3\" P | 4000075830 | ANC32.0000.00276 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4560.47 | 2024-08-29 | 2024-08-30 |  | 2024-08-30 | C_U139391
2631 |  | CNV-20026968700 EMER - INSTALL 5' - 2\" | 4000075831 | ANC32.0000.00159 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 241.92 | 2023-12-21 | 2023-12-21 | 2025-07-30 | 2023-12-25 | C_U139391
2621 |  | CNV-24026351900 EMER-RETIRE 8' OF 3\" PM | 4000075832 | ANC32.0000.00276 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6.09 | 2024-08-30 | 2024-08-30 | 2025-08-01 | 2024-08-30 | C_U139391
2621 |  | CNV-24026352600 EMER - INSTALL 2'-2\" PM | 4000075833 | ANC32.0000.00278 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1553.45 | 2024-08-14 | 2024-08-15 | 2025-08-01 | 2024-08-15 | C_U139391
2631 |  | CNV-20026968800 EMER - RETIRE 5'- 2\" PM | 4000075834 | ANC32.0000.00159 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 182.33 | 2023-12-21 | 2023-12-21 | 2025-07-30 | 2023-12-25 | C_U139391
2621 |  | CNV-24026352700 EMER - RETIRE 2'-2\" PMM | 4000075835 | ANC32.0000.00278 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 122.61 | 2024-08-15 | 2024-08-15 | 2025-08-01 | 2024-08-15 | C_U139391
2623 |  | CNV-20026974601 INSTALL 6,500'-4\"PMLP | 4000075836 | ANC32.0000.00160 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 11043.04 | 2023-02-08 | 2023-12-31 |  | 2049-12-31 | C_U139391
2623 |  | CNV-20026974700 RETIRE 6,900'-BSLP,CSLP, | 4000075838 | ANC32.0000.00160 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 233.2 | 2020-09-18 | 2049-12-31 |  | 2049-12-31 | C_U139391
2631 |  | CNV-20026978100 INSTALL 8620'- 2\" PMMP | 4000075860 | ANC32.0000.00161 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 442357.23 | 2023-05-30 | 2023-12-31 | 2025-07-30 | 2023-12-31 | C_U139391
2621 |  | CNV-24026365000 EMER-INSTALL 10' - 2\" P | 4000075863 | ANC32.0000.00287 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2308.37 | 2024-12-30 | 2024-12-31 | 2025-08-01 | 2024-12-31 | C_U139391
2621 |  | CNV-24026369000 INSTALL 65'-8\" PMLP | 4000075865 | ANC32.0000.00085 | REL NMAT PRC SETC | NEW FCMP NSFS WENG | MAI | 0 | 46796.4 | 2025-07-18 | 2025-07-31 |  | 2025-07-31 | C_U139391
2621 |  | CNV-24026371100 EMER-INSTALL 6' OF 8\"PM | 4000075867 | ANC32.0000.00086 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 3770.63 | 2025-07-01 | 2025-07-01 | 2025-08-03 | 2025-07-01 | C_U139391
2621 |  | CNV-24026371200 EMER-RETIRE 6' OF 8\"PMP | 4000075869 | ANC32.0000.00086 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 15.06 | 2025-04-28 | 2025-04-28 | 2025-08-03 | 2025-07-01 | C_U139391
2623 |  | ANC - Highland Parkway - Frankfort WR27 | 4000075870 | ANC32.0000.00165 | REL MANC PRC SETC | NEW ADJ NSFS WENG WENV WGMA WLND WPMT* | MAI | 235494.3 | 37820.61 | 2026-10-31 | 2027-12-31 |  |  | C_U139391
2621 |  | CNV-24026376700 EMER - INSTALL 3'-2\" PM | 4000075871 | ANC32.0000.00292 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 2391.9 | 2025-08-28 | 2025-08-31 | 2025-08-01 | 2025-08-31 | C_U139391
2623 |  | CNV-18026776800 RETIRE 3,439' - 8\" BS,C | 4000075872 | ANC32.0000.00165 | REL NMAT PRC SETC | NEW NSFS | MAI | 0 | 0 | 2025-11-21 | 2025-12-31 |  | 2026-12-31 | C_U139391
2621 |  | CNV-24026376800 EMER - RETIRE 3'-2\" PMP | 4000075873 | ANC32.0000.00292 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 6.11 | 2025-08-29 | 2025-08-31 |  | 2025-08-31 | C_U139391
2631 |  | CNV-18026793901 INSTALL 4,123' - 2\" PMM | 4000075875 | ANC32.0000.00156 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 20127.52 | 2023-08-01 | 2023-12-31 | 2025-07-31 | 2023-12-31 | C_U139391
2629 | CYNTHIANA | CNV-18026795501 INSTALL 14,600'-2,4,6,8. | 4000075877 | ANC32.0000.00158 | REL CSER MANC NMAT PRC SETC | NEW REV | MAI | 0 | 14815.83 | 2022-11-28 | 2024-03-31 |  | 2024-11-08 | C_U139391
2623 |  | CNV-18026845002 INSTALL THREE SSD UNITS | 4000075879 | ANC32.0000.00136 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 8156.02 | 2024-10-31 | 2024-12-01 |  | 2024-12-01 | C_U139391
2621 |  | CNV-24026310400 INSTALL VALVE & 5' OF 2\ | 4000075917 | BET32.0000.00040 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 7598.07 | 2024-12-30 | 2024-12-31 |  | 2024-12-31 | C_U139391
2629 |  | CNV-24026310600 INSTALL 2, 2\" STOPPLE F | 4000075919 | BET32.0000.00048 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 13907.28 | 2025-12-23 | 2025-12-31 | 2025-07-31 | 2025-12-31 | C_U139391
2633 |  | CNV-19026867802 INSTALL 376'-4\\\" PMIP. | 4000075940 | BET32.0000.00027 | REL MANC PRC SETC | NEW FCMP WENG | MAI | 11431.35 | 159288.9 | 2025-09-11 | 2025-09-30 |  | 2025-09-30 | C_U139391
2621 |  | CNV-24026311800 EMER-INSTALL 5' OF 2\"PM | 4000075941 | ANC32.0000.00248 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1865.23 | 2024-09-30 | 2024-09-30 | 2025-07-31 | 2024-09-30 | C_U139391
2633 |  | CNV-19026867900 RETIRE 396'-3\" P&CS | 4000075942 | BET32.0000.00027 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 33.42 | 2025-09-30 | 2025-09-30 |  | 2025-09-30 | C_U139391
2621 |  | CNV-24026311900 EMER-RETIRE 5' OF 2\"PAM | 4000075943 | ANC32.0000.00248 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 24.43 | 2024-09-30 | 2024-09-30 | 2025-07-31 | 2024-09-30 | C_U139391
2631 |  | CNV-19026913000 INSTALL 730'-2\\\PMMP.. | 4000075944 | ANC32.0000.00001 | REL PCNF MANC NMAT PRC SETC | NEW REV | MAI | 0 | 96680.57 | 2024-01-08 | 2024-12-31 | 2025-07-31 | 2024-12-31 | C_U139391
2621 |  | CNV-24026312700 RETIRE 310' OF 2\"PMMP M | 4000075945 | PIG32.0000.00017 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1335.37 | 2024-11-27 | 2024-12-01 | 2025-07-31 | 2024-12-01 | C_U139391
2621 |  | CNV-24026314000 EMER-INSTALL 5' OF 4\"PM | 4000075947 | ANC32.0000.00249 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 249.15 | 2024-09-30 | 2024-09-30 | 2025-07-31 | 2024-09-30 | C_U139391
2621 |  | CNV-24026314100 EMER-RETIRE 5' OF 4\"PAM | 4000075949 | ANC32.0000.00249 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 39.03 | 2024-09-30 | 2024-09-30 | 2025-07-31 | 2024-09-30 | C_U139391
2623 |  | CNV-21026115500 INSTALL 9560' OF 2\"PMMP | 4000075984 | ANC32.0000.00166 | REL PCNF GMPS NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 53259.86 | 2022-08-04 | 2023-02-21 | 2025-07-30 | 2023-12-31 | C_U139391
2623 |  | CNV-21026115600 RETIRE 9,590' OF BSLP & | 4000075986 | ANC32.0000.00166 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 182.4 | 2021-04-13 | 2049-12-31 |  | 2049-12-31 | C_U139391
2632 |  | CNV-21026127000 INSTALL 8021'-2\"&4\" PM | 4000075988 | ANC32.0000.00168 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 932.48 | 2023-08-29 | 2023-12-31 |  | 2023-12-31 | C_U139391
2631 |  | CNV-21026130200 EMER-INSTALL 5'-2\" PMIP | 4000075990 | ANC32.0000.00169 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2022-09-29 | 2022-09-30 |  | 2023-05-13 | C_U139391
2631 |  | CNV-21026130300 EMER-RETIRE 5'-2\" BSIP | 4000075992 | ANC32.0000.00169 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2022-09-30 | 2022-09-30 |  | 2023-05-13 | C_U139391
2631 |  | CNV-21026130400 INSTALL 25,111'-2\",4\" | 4000075994 | ANC32.0000.00167 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 194477.23 | 2022-08-04 | 2023-12-31 | 2025-07-30 | 2024-12-08 | C_U139391
2621 |  | CNV-24026355100 EMER - RETIRE 12'-2\" PM | 4000076038 | ANC32.0000.00113 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 456.5 | 2024-10-31 | 2024-10-31 | 2025-08-01 | 2024-10-31 | C_U139391
2621 |  | CNV-24026355400 EMER-INSTALL 2' OF 2\"PM | 4000076060 | ANC32.0000.00281 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 29.54 | 2025-10-31 | 2025-10-31 | 2025-08-01 | 2026-06-11 | C_U139391
2621 |  | CNV-24026355500 EMER-RETIRE 2' OF 2\"PAM | 4000076062 | ANC32.0000.00281 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 7.3 | 2025-10-31 | 2025-10-31 | 2025-08-01 | 2026-06-11 | C_U139391
2621 |  | CNV-24026356200 INSTALL NEW 4\" CRITICAL | 4000076064 | ANC32.0000.00283 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1175.54 | 2024-10-14 | 2024-10-15 | 2025-08-01 | 2026-04-16 | C_U139391
2621 |  | CNV-24026356300 RETIRE 4\" POLY VALVE C1 | 4000076066 | ANC32.0000.00283 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 5606.01 | 2025-08-29 | 2025-08-31 | 2025-08-01 | 2026-04-16 | C_U139391
2621 |  | CNV-24026328300 EMER - INSTALL 26'-6\" P | 4000076068 | ANC32.0000.00258 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 9947.87 | 2024-02-28 | 2024-03-07 | 2025-07-31 | 2024-03-10 | C_U139391
2621 |  | CNV-24026328400 EMER - RETIRE 26'-6\" BS | 4000076070 | ANC32.0000.00258 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3033.08 | 2024-02-28 | 2024-03-07 | 2025-07-31 | 2024-03-10 | C_U139391
2629 |  | ANC-SMRP Rowland Ave-Winchester | 4000076071 | ANC32.0000.00007 | REL CSER GMPS MANC PRC SETC | NEW ADJ | MAI | 193773.65 | 16615.18 | 2026-01-01 | 2026-12-31 |  | 2026-12-31 | C_U139391
2621 |  | CNV-24026331900 EMER - INSTALL 1' OF 2\" | 4000076072 | ANC32.0000.00261 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2305.11 | 2024-05-01 | 2024-05-01 | 2025-07-31 | 2024-05-01 | C_U139391
2631 |  | CNV-20026983300 INSTALL 6,600'-2\\\/4\. | 4000076073 | ANC32.0000.00002 | REL PCNF MANC NMAT PRC SETC | NEW REV | MAI | 0 | 675213.22 | 2024-03-01 | 2024-12-31 | 2025-07-31 | 2024-12-31 | C_U139391
2621 |  | CNV-24026332000 EMER - RETIRE 1' OF 2\"P | 4000076074 | ANC32.0000.00261 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 294.9 | 2024-05-01 | 2024-05-01 | 2025-07-31 | 2024-05-01 | C_U139391
2631 |  | CNV-20026983500 INSTALL 1670' - 2\" PMMP | 4000076075 | ANC32.0000.00162 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 81119.08 | 2023-11-08 | 2023-12-31 | 2025-07-30 | 2023-12-31 | C_U139391
2621 |  | CNV-24026332100 INSERT 50' OF 3\" PMLP | 4000076076 | ANC32.0000.00262 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 7319.46 | 2024-10-29 | 2024-10-31 |  | 2025-06-12 | C_U139391
2631 |  | CNV-20026991600 INSTALL RECTIFIER- JOHNS | 4000076077 | ANC32.0000.00138 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 716.73 | 2023-12-18 | 2023-12-20 | 2025-07-31 | 2023-12-20 | C_U139391
2621 |  | CNV-24026332200 RETIRE 52' - 4\" CSLP | 4000076078 | ANC32.0000.00262 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 9131.55 | 2024-10-31 | 2024-10-31 | 2025-07-31 | 2025-06-12 | C_U139391
2621 |  | CNV-24026333000 EMER-INSTALL 18'-4\"PMLP | 4000076100 | ANC32.0000.00064 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 752.02 | 2024-07-29 | 2024-07-31 |  | 2025-03-10 | C_U139391
2621 |  | CNV-24026334000 INSTALL 5' OF 2\" PMMP | 4000076102 | ANC32.0000.00265 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6723.58 | 2024-03-28 | 2024-03-30 | 2025-07-31 | 2026-02-08 | C_U139391
2621 |  | CNV-24026334200 RETIRE 5' OF 2\" PMP | 4000076104 | ANC32.0000.00265 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 47.46 | 2025-03-28 | 2025-03-30 | 2025-07-31 | 2026-02-08 | C_U139391
2621 |  | CNV-24026336800 EMER - INSTALL 5' OF 2\" | 4000076106 | ANC32.0000.00067 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4721.53 | 2024-07-31 | 2024-07-31 |  | 2024-08-31 | C_U139391
2621 |  | CNV-24026339400 RETIRE 322'-4\" CSLP | 4000076108 | PIG32.0000.00022 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2689.01 | 2024-09-30 | 2024-10-01 | 2025-07-31 | 2024-10-01 | C_U139391
2621 |  | CNV-24026339800 INSTALL 35' OF 6\"PMLP M | 4000076110 | ANC32.0000.00266 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 9350.15 | 2024-09-27 | 2024-10-01 | 2025-08-01 | 2024-10-01 | C_U139391
2621 |  | CNV-24026339900 RETIRE 25' OF 6\"BSLP MA | 4000076112 | ANC32.0000.00266 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3735.71 | 2024-10-01 | 2024-10-01 | 2025-08-01 | 2024-10-01 | C_U139391
2623 |  | CNV-24026356800 REPLACE 20'-6\" CSLP | 4000076114 | BET32.0000.00018 | REL PCNF NMAT PRC SETC | NEW NSFS | MAI | 0 | 1069.37 | 2025-12-30 | 2025-12-31 | 2025-08-01 | 2025-12-31 | C_U139391
2621 |  | CNV-24026357000 EMER-INSTALL 50' OF 4\"P | 4000076116 | ANC32.0000.00285 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 8511.32 | 2025-11-24 | 2025-11-30 | 2025-08-01 | 2026-07-13 | C_U139391
2621 |  | CNV-24026357100 EMER-RETIRE 50' OF 4\"BS | 4000076118 | ANC32.0000.00285 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 4851.43 | 2025-11-26 | 2025-11-30 | 2025-08-01 | 2026-07-13 | C_U139391
2629 | PARIS | CNV-23026264000 INSTALL NEW METER | 4000076139 | ANC32.0000.00124 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 20617.11 | 2024-12-30 | 2024-12-31 | 2025-07-31 | 2024-12-31 | C_U139391
2621 |  | CNV-24026357600 RETIRE 490' OF 2\"/4\"PM | 4000076140 | PIG32.0000.00023 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2673.58 | 2024-08-30 | 2024-09-01 | 2025-08-01 | 2024-09-01 | C_U139391
2621 |  | CNV-24026360500 INSTALL 18'-2\" PMMP | 4000076142 | PIG32.0000.00037 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 8026.04 | 2024-11-22 | 2024-11-30 | 2025-08-01 | 2024-11-30 | C_U139391
2621 |  | CNV-24026360600 RETIRE 10'-2\" PMMP | 4000076143 | PIG32.0000.00037 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3300.87 | 2024-11-27 | 2024-11-30 | 2025-08-01 | 2024-11-30 | C_U139391
2621 |  | CNV-24026361300 INSTALL 750'-2\\\ PMMP. | 4000076145 | PIG32.0000.00011 | REL PCNF GMPS MANC NMAT PRC SETC | NEW | MAI | 0 | 171116.42 | 2025-03-04 | 2025-03-30 | 2025-08-01 | 2025-03-30 | C_U139391
2623 |  | CNV-23026267900 PS&I HIGHLAND PARKWAY | 4000076161 | ANC32.0000.00165 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 22236.34 | 2024-12-30 | 2024-12-31 |  | 2024-12-31 | C_U139391
2623 |  | CNV-23026276700 RETIRE STATION R-1581 | 4000076163 | ANC32.0000.00197 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 1721.37 | 2024-12-31 | 2024-12-31 | 2025-08-01 | 2024-12-31 | C_U139391
2632 | MAYSVILLE | CNV-23026286900 HIGHLAND HEIGHTS BREAK M | 4000076165 | ANC32.0000.00126 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 8521.83 | 2024-12-30 | 2024-12-31 | 2025-08-01 | 2024-12-31 | C_U139391
2631 |  | CNV-23026308300 INVESTIGATE EASEMENTS AN | 4000076167 | PSI32.0000.00013 | TECO JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL REV | PSI | 0 | 5120.81 | 2024-12-31 | 2024-12-31 |  | 2024-12-31 | C_U139391
2621 |  | SMRP JESSELIN DR 2025 CNV 24-0263154-00 | 4000076403 | ANC32.0000.00054 | REL PCNF GMPS MANC PRC SETC | SCHD FCMP REV | MAI | 896582.69 | 6058159.51 | 2025-08-05 | 2025-12-31 | 2026-04-27 | 2026-05-01 | C_U139391
2621 |  | CNV-24026316701 INSTALL 11245' OF 2\\\". | 4000076405 | ANC32.0000.00252 | REL MANC NMAT PRC SETC | NEW REV WENG | MAI | 0 | 116711.13 | 2024-05-28 | 2024-12-31 |  | 2024-12-31 | C_U139391
2621 |  | CNV-24026321100 INSTALL 1400' OF 2\" PMM | 4000076407 | GRT32.0000.00099 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 36755.9 | 2024-05-17 | 2024-06-01 | 2025-07-31 | 2024-06-01 | C_U139391
2621 |  | WOLF RUN 2025 SMRP CNV-24026322000 | 4000076409 | ANC32.0000.00257 | REL GMPS MANC PRC SETC | COCO ADJ FCMP | MAI | 730195.39 | 681714.43 | 2025-07-31 | 2025-12-31 |  | 2025-12-31 | C_U139391
2621 |  | CNV-24026341900 INSTALL 4250' OF 2\"/4\" | 4000076411 | GRT32.0000.00102 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 86676.99 | 2024-08-26 | 2024-09-30 | 2025-08-01 | 2024-09-30 | C_U139391
2621 |  | CNV-24026342400 INSTALL ~585'-2\" PMMP | 4000076413 | PIG32.0000.00045 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 39880.08 | 2024-07-17 | 2024-07-30 | 2025-08-01 | 2024-07-30 | C_U139391
2621 |  | CNV-24026342500 RETIRE ~600'-2\" PMMP | 4000076414 | PIG32.0000.00045 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 321.09 | 2024-07-30 | 2024-07-30 | 2025-08-01 | 2024-07-30 | C_U139391
2621 |  | CNV-24026343500 INSTALL 25'-8\" PMLP | 4000076418 | PIG32.0000.00046 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 16995.11 | 2024-06-21 | 2024-06-30 | 2025-07-31 | 2024-06-30 | C_U139391
2621 |  | CNV-24026343600 RETIRE 15'-8\" CSLP | 4000076440 | PIG32.0000.00046 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 116.6 | 2024-06-28 | 2024-06-30 |  | 2024-06-30 | C_U139391
2621 |  | CNV-24026349300 INSTALL 4\"POLY VALVE KY | 4000076442 | BET32.0000.00044 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 10019.67 | 2025-05-28 | 2025-06-01 | 2025-08-01 | 2025-06-01 | C_U139391
2621 |  | CNV-24026349400 RETIRE 10' OF 3\"PMP MAI | 4000076444 | BET32.0000.00044 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 21.76 | 2025-05-30 | 2025-06-01 | 2025-08-01 | 2025-06-01 | C_U139391
2621 |  | CNV-24026351200 INSTALL 150' OF 2\"PMIP | 4000076446 | GRT32.0000.00103 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 7979.42 | 2024-09-26 | 2024-09-27 | 2025-08-01 | 2024-09-27 | C_U139391
2621 |  | CNV-24026363100 INSTALL 481'-8\" CSHP | 4000076459 | PIG32.0000.00013 | REL PCNF MANC PRC SETC | COCO ADJ FCMP RSHD | MAI | 195428.52 | 47018.3 | 2025-07-15 | 2025-07-30 | 2025-09-06 | 2025-07-30 | C_U139391
2621 |  | CNV-24026363600 INSTALL 620' OF 4\"PMMP | 4000076481 | ANC32.0000.00082 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 109530.33 | 2024-12-02 | 2024-12-31 | 2025-08-01 | 2024-12-31 | C_U139391
2621 |  | CNV-24026365700 INSTALL 320' OF 2\\\PM. | 4000076483 | GRT32.0000.00064 | REL MANC NMAT PRC SETC | NEW | MAI | 0 | 17437.01 | 2025-01-02 | 2025-01-10 |  | 2025-01-10 | C_U139391
2621 |  | ELM TREE 2025 SMRP CROSSBORE CNV-2402636 | 4000076485 | ANC32.0000.00289 | REL GMPS MANC PRC SETC | COCO ADJ FCMP | MAI | 55039.42 | 275901.46 | 2025-11-21 | 2025-12-31 |  | 2025-12-31 | C_U139391
2621 |  | ANC-CASSIDY AVE SMRP-LEXINGTON | 4000076487 | ANC32.0000.00084 | REL PCNF MANC PRC SETC | NEW ADJ | MAI | 645287.17 | 1471.17 | 2026-08-07 | 2026-12-31 | 2026-03-04 | 2026-12-31 | C_U139391
2621 |  | CNV-24026368600 INSTALL 640' OF 2\\\ P. | 4000076489 | GRT32.0000.00065 | REL PCNF MANC NMAT PRC SETC | NEW | MAI | 0 | 31021.74 | 2025-05-23 | 2025-06-01 | 2025-08-03 | 2025-06-01 | C_U139391
2621 |  | CNV-24026368800 INSTALL 5' OF 6\\\ PML. | 4000076491 | BET32.0000.00046 | REL PCNF MANC NMAT PRC SETC | NEW | MAI | 0 | 12900.04 | 2025-06-26 | 2025-06-30 | 2025-08-01 | 2025-06-30 | C_U139391
2621 |  | CNV-24026368900 RETIRE 5' OF 6\" BSLP | 4000076493 | BET32.0000.00046 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 820.05 | 2025-06-30 | 2025-06-30 | 2025-08-01 | 2025-06-30 | C_U139391
2621 |  | CNV-24026370200 INSTALL 1415'-2\" PMMP | 4000076495 | PIG32.0000.00030 | REL PCNF MANC PRC SETC | SCHD ADJ MIFE | MAI | 1.78 | 78682.95 | 2025-04-24 | 2025-05-30 | 2025-08-05 | 2025-05-30 | C_U139391
2621 |  | CNV-24026370300 RETIRE 679'-3\" CSMP | 4000076497 | PIG32.0000.00030 | REL PCNF NMAT PRC SETC | NEW NSFS | MAI | 0 | 643.86 | 2025-05-30 | 2025-05-30 | 2025-08-05 | 2025-05-30 | C_U139391
2621 |  | NICHOLASVILLE RD MP SMRP CNV-24026370900 | 4000076499 | ANC32.0000.00145 | REL GMPS MANC PRC SETC | COCO ADJ FCMP | MAI | 340620.69 | 1040845.26 | 2026-11-23 | 2026-12-31 |  | 2026-12-31 | C_U139391
2621 |  | CNV-24026376901 INSTALL 1218'-6\" PMMP | 4000076501 | PIG32.0000.00028 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 4735.83 | 2025-02-28 | 2025-04-30 |  | 2025-04-30 | C_U139391
2621 |  | CNV-24026377000 RETIRE 1140'-6\" PMP | 4000076503 | PIG32.0000.00028 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 571.78 | 2025-09-30 | 2025-09-30 |  | 2025-09-30 | C_U139391
2621 |  | SUMMERFIELD MLE CNV-25026385000 BALL HOM | 4000076538 | GRT32.0000.00067 | REL GMPS MANC PRC SETC | SCHD | MAI | 8618.47 | 168479.71 | 2025-09-29 | 2025-11-15 |  | 2026-03-10 | C_U139391
2621 |  | CNV-25026385100 EMER-INSTALL 4' OF 4\"PM | 4000076560 | ANC32.0000.00295 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 6298.29 | 2025-06-30 | 2025-06-30 | 2025-08-03 | 2025-07-01 | C_U139391
2623 |  | CNV-22026229200 INSTALL 80'-2\" PMMP | 4000076561 | GRT32.0000.00007 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-03-15 | 2023-03-17 |  | 2023-03-17 | C_U139391
2621 |  | CNV-25026385200 EMER-RETIRE 4' OF 4\"PMP | 4000076562 | ANC32.0000.00295 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 1275.57 | 2025-01-29 | 2025-01-29 |  | 2025-07-01 | C_U139391
2629 |  | CNV-22026230301 INSTALL 1,725'-2\" PMMP | 4000076563 | ANC32.0000.00190 | REL CSER NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 3483.73 | 2049-10-24 | 2049-10-24 |  | 2049-12-31 | C_U139391
2621 |  | CNV-25026399700 EMER - INSTALL 3'-2\" PM | 4000076564 | ANC32.0000.00098 | REL NMAT PRC SETC | NEW NSFS | MAI | 0 | 0 | 2025-11-26 | 2025-11-30 |  | 2025-11-30 | C_U139391
2633 |  | ANC-Caney Circle- Pippa Passes | 4000076565 | ANC32.0000.00140 | TECO MANC PRC SETC | NEW ADJ WENV | MAI | 60386.93 | 6712.5 | 2025-07-02 | 2025-12-31 |  | 2025-12-31 | C_U139391
2629 |  | CNV-22026230400 RETIRE 5,578' - IP MAIN | 4000076566 | ANC32.0000.00190 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2022-10-10 | 2049-12-31 |  | 2049-12-31 | C_U139391
2621 |  | CNV-25026400500 EMER - INSTALL 5'-2\" PM | 4000076567 | ANC32.0000.00099 | REL PRC SETC | NEW NSFS | MAI | 34.35 | 2436.44 | 2025-11-25 | 2025-11-30 |  | 2025-11-30 | C_U139391
2623 |  | CNV-22026230700 EMER-RETIRE 5' OF 3\"PAM | 4000076568 | ANC32.0000.00102 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-09-29 | 2023-09-30 |  | 2024-05-10 | C_U139391
2621 |  | CNV-25026400900 EMER - INSTALL 2'-4\" PM | 4000076569 | ANC32.0000.00100 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 4133.67 | 2025-11-25 | 2025-11-30 |  | 2025-11-30 | C_U139391
2623 |  | CNV-22026231200 INSTALL 1870'-2\"/4\" PM | 4000076570 | GRT32.0000.00001 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 130704.28 | 2023-09-11 | 2023-09-30 | 2025-07-30 | 2023-10-30 | C_U139391
2631 |  | CNV-25026404000 SMRP - INSTALL 650'-2\" | 4000076571 | ANC32.0000.00154 | REL GMPS MANC PRC SETC | NPRG ADJ | MAI | 31956.67 | 202446.55 | 2025-08-01 | 2025-08-29 |  | 2025-09-19 | C_U139391
2629 |  | CNV-22026234901 INSTALL 4,100'-2\" PMMP | 4000076572 | GRT32.0000.00085 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 23273.07 | 2023-10-23 | 2023-12-01 | 2025-07-31 | 2023-12-01 | C_U139391
2621 |  | CNV-25026405400 EMER - INSTALL 2'-2\" PM | 4000076573 | ANC32.0000.00150 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 2365.36 | 2025-06-30 | 2025-06-30 |  | 2025-07-01 | C_U139391
2623 |  | CNV-22026235100 INSTALL 2160'-2\"/4\" PM | 4000076574 | GRT32.0000.00084 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 102021.49 | 2023-06-09 | 2024-02-29 | 2025-07-31 | 2024-02-29 | C_U139391
2621 |  | CNV-25026405500 EMER - RETIRE 2'-2\" PMP | 4000076575 | ANC32.0000.00150 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 108.37 | 2025-07-01 | 2025-07-01 | 2025-08-03 | 2025-07-01 | C_U139391
2623 |  | CNV-22026235300 INST 1865'-8\" & 390'-2\ | 4000076576 | ANC32.0000.00192 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 400226.28 | 2024-10-17 | 2024-12-31 | 2025-07-31 | 2024-12-31 | C_U139391
2621 |  | CNV-25026406300 INSTALL 15'-6\" PMLP | 4000076577 | ANC32.0000.00152 | REL MANC PRC SETC | NEW ADJ FCMP MIFE NSFS WENG | MAI | 203.85 | 1732.64 | 2025-05-01 | 2025-05-04 |  | 2025-07-31 | C_U139391
2629 |  | CNV-22026236400 INSTALL 450'-4\" PMMP | 4000076579 | GRT32.0000.00009 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2693.93 | 2023-06-21 | 2023-07-15 | 2025-07-30 | 2023-07-15 | C_U139391
2623 |  | CNV-22026236901 INSTALL 11300'-2\" PMMP | 4000076601 | ANC32.0000.00193 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 80401.8 | 2024-01-15 | 2024-12-31 | 2025-08-01 | 2024-12-31 | C_U139391
2629 | WINCHESTER | CNV-22026237301 INSTALL 11,150'-8\\\"6\. | 4000076603 | ANC32.0000.00195 | REL CSER MANC NMAT PRC SETC | NEW REV | MAI | 0 | 143037.72 | 2024-12-18 | 2026-02-28 |  | 2026-10-21 | C_U139391
2629 |  | CNV-22026237400 RETIRE LP MAIN.. | 4000076605 | ANC32.0000.00195 | REL MANC NMAT PRC SETC | NEW | MAI | 0 | 252.59 | 2025-12-31 | 2025-12-31 |  | 2026-08-08 | C_U139391
2629 |  | CNV-22026237500 RETIRE MP MAIN | 4000076607 | ANC32.0000.00195 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 561.2 | 2024-01-31 | 2024-01-31 | 2025-07-31 | 2024-12-31 | C_U139391
2629 |  | CNV-22026237801 INSTALL 4,100'-2\" PMMP | 4000076609 | ANC32.0000.00196 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 7412.99 | 2024-08-09 | 2024-12-31 | 2025-07-31 | 2024-12-31 | C_U139391
2623 |  | CNV-22026238301 INSTALL 2505'-4\" PHHP | 4000076611 | GRT32.0000.00081 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 8013.44 | 2023-09-11 | 2023-12-30 | 2025-07-31 | 2024-01-31 | C_U139391
2623 |  | CNV-22026238401 INSTALL 5765'-2\" PMMP | 4000076613 | ANC32.0000.00197 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 709396.34 | 2023-11-28 | 2049-12-31 | 2025-07-31 | 2049-12-31 | C_U139391
2623 |  | ANC-SMRP HIGH STREET-FRANKFORT | 4000076615 | ANC32.0000.00018 | REL MANC PRC SETC | NEW ADJ NSFS WENG | MAI | 1441844.36 | 7149.16 | 2026-10-13 | 2026-12-31 |  | 2026-12-31 | C_U139391
2623 |  | CNV-22026241001 INSTALL 6375'-2\"/4\" PM | 4000076617 | GRT32.0000.00011 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 5088.06 | 2023-08-30 | 2023-12-31 | 2025-07-31 | 2023-12-31 | C_U139391
2623 |  | CNV-22026241701 INSTALL 1425' OF 2\"PMMP | 4000076619 | PIG32.0000.00033 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 36869.35 | 2024-01-15 | 2024-06-01 | 2025-07-31 | 2024-06-01 | C_U139391
2623 |  | CNV-22026241800 RETIRE 1175' OF 3\"/4\"B | 4000076641 | PIG32.0000.00033 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2024-05-31 | 2024-06-01 |  | 2024-06-01 | C_U139391
2633 |  | CNV-22026241900 INSTALL 249'-2\" PMIP | 4000076642 | PIG32.0000.00034 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-05-17 | 2023-05-31 |  | 2023-05-31 | C_U139391
2633 |  | CNV-22026242000 RETIRE 135'-3\" BSIP | 4000076644 | PIG32.0000.00034 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-05-31 | 2023-05-31 |  | 2023-05-31 | C_U139391
2629 |  | CNV-22026245300 EMER - INSTALL 5'-2\" PM | 4000076646 | ANC32.0000.00021 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-01-16 | 2023-01-16 |  | 2023-06-01 | C_U139391
2629 |  | ANC-SMRP Burns Ave Retirement-Winchester | 4000076659 | ANC32.0000.00170 | REL PCNF NMAT PRC SETC | NEW | MAI | 0 | 626.39 | 2025-11-26 | 2025-11-30 | 2025-11-06 | 2025-12-31 | C_U139391
2629 |  | CNV-22026161800 INSTALL 8\" PCF | 4000076681 | ANC32.0000.00158 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1391.52 | 2024-01-08 | 2024-01-08 | 2025-08-01 | 2024-12-31 | C_U139391
2629 |  | CNV-22026161900 RETIRE LP MAIN - LEAKAGE | 4000076683 | ANC32.0000.00158 | REL PCNF CSER NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 1465.95 | 2049-12-31 | 2049-12-31 | 2025-08-01 | 2024-12-31 | C_U139391
2629 |  | CNV-22026164000 INSTALL 5,100'-2\" PMMP | 4000076685 | ANC32.0000.00174 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 570375.53 | 2024-08-08 | 2024-12-31 | 2025-07-30 | 2024-12-31 | C_U139391
2629 |  | CNV-22026164201 INSTALL 2,300'-2\\\ PM. | 4000076687 | ANC32.0000.00175 | REL PCNF MANC NMAT PRC SETC | NEW REV | MAI | 0 | 20887.85 | 2023-10-03 | 2023-12-31 | 2025-07-30 | 2023-12-31 | C_U139391
2621 |  | CNV-25026406400 RETIRE ~15'-6\" BSLP | 4000076688 | ANC32.0000.00152 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS WENG | MAI | 0 | 303.26 | 2025-05-02 | 2025-05-04 | 2025-08-03 | 2025-07-31 | C_U139391
2621 |  | CNV-25026407500 INSTALL 2'-4\" PMMP | 4000076690 | ANC32.0000.00153 | REL CSER NMAT PRC SETC | SCHD NSFS | MAI | 0 | 15.32 | 2027-04-06 | 2027-04-10 |  | 2027-04-10 | C_U139391
2621 |  | CNV-25026407600 RETIRE 2'-4\" PMP | 4000076692 | ANC32.0000.00153 | REL CSER NMAT PRC SETC | SCHD NSFS | MAI | 0 | 867.16 | 2027-04-09 | 2027-04-10 |  | 2027-04-10 | C_U139391
2621 |  | CNV-25026407800 EMER - INSTALL 5'-2\" PM | 4000076694 | GRT32.0000.00075 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 1181.61 | 2025-05-13 | 2025-05-13 |  | 2025-05-13 | C_U139391
2621 |  | CNV-25026409400 INSTALL ANODE BED. | 4000076696 | PIG32.0000.00024 | REL MANC NMAT PRC SETC | NEW | MAI | 0 | 13182.42 | 2025-12-23 | 2025-12-23 |  | 2025-12-31 | C_U139391
2623 |  | CNV-22026225400 INSTALL APROX 180'-6\" P | 4000076805 | ANC32.0000.00188 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 93563.17 | 2023-09-18 | 2023-09-29 | 2025-07-30 | 2023-09-30 | C_U139391
2623 |  | CNV-22026225500 RETIRE 200' - 6\" BSLP | 4000076807 | ANC32.0000.00188 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 510.72 | 2023-03-31 | 2023-03-31 |  | 2023-09-30 | C_U139391
2629 |  | CNV-22026228201 INSTALL 4,225'-2\"/6\" P | 4000076809 | ANC32.0000.00189 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2706.98 | 2023-06-07 | 2024-01-31 |  | 2024-09-20 | C_U139391
2629 |  | CNV-22026228300 RETIRE 6,106'- LP MAIN | 4000076811 | ANC32.0000.00189 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2024-01-31 | 2024-01-31 |  | 2024-09-20 | C_U139391
2623 |  | CNV-22026168600 INSTALL 13,800'-2\"PMMP | 4000076813 | ANC32.0000.00012 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 105908.53 | 2023-03-31 | 2023-12-31 | 2025-07-30 | 2023-12-31 | C_U139391
2623 |  | CNV-22026169200 EMER-INSTALL 4' OF 2\"PM | 4000076815 | ANC32.0000.00013 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-09-01 | 2023-09-01 |  | 2024-12-31 | C_U139391
2629 |  | CNV-22026170600 INSTALL 7,200'-2\"/4\" P | 4000076817 | ANC32.0000.00003 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 153514.73 | 2023-04-06 | 2023-12-31 | 2025-07-30 | 2023-12-31 | C_U139391
2623 |  | CNV-22026170800 INSTALL 15,885'-2\"&4\"P | 4000076819 | ANC32.0000.00014 | REL CSER NMAT PRC SETC | NEW NSFS | MAI | 0 | 0 | 2026-05-20 | 2026-12-31 |  | 2026-12-31 | C_U139391
2623 |  | SMRP - MAIN ST (JIM BEAM) | 4000076831 | PSI32.0000.00025 | TECO JBFI NMAT PRC SETC | NEW CAN NSFS RECL | PSI | 0 | 74921.25 | 2026-12-31 | 2026-12-31 |  | 2026-12-31 | C_U139391
2623 |  | CNV-24026343100 PS&I HOLMES STREET RELO | 4000076833 | PSI32.0000.00037 | REL PCNF MANC NMAT PRC SETC | NEW | PSI | 46.68 | 2935.54 | 2026-12-31 | 2026-12-31 | 2026-03-04 | 2026-12-31 | C_U139391
2621 |  | CNV-24026311700 INSTALL 360' OF 2\"PMMP | 4000076851 | GRT32.0000.00049 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 23934.84 | 2024-04-09 | 2024-04-12 | 2025-07-31 | 2024-04-12 | C_U139391
2621 |  | CNV-24026314600 EMER-INSTALL 170' OF 2\" | 4000076854 | ANC32.0000.00053 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 52732.18 | 2024-02-05 | 2024-02-14 | 2025-07-31 | 2024-02-17 | C_U139391
2632 |  | ANC-Fernleaf Dr-Maysville | 4000076861 | ANC32.0000.00179 | REL PCNF GMPS MANC PRC SETC | NEW ADJ NSFS | MAI | 801667.68 | 1185363.99 | 2025-10-02 | 2026-10-30 | 2026-03-12 | 2026-12-31 | C_U139391
2632 |  | CNV-22026171800 INSTALL 3178'-2\" PMIP | 4000076864 | ANC32.0000.00015 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 19573.98 | 2023-11-02 | 2023-12-31 | 2025-07-30 | 2023-12-31 | C_U139391
2631 |  | CNV-22026172301 INSTALL 5000' OF 2\"PMMP | 4000076866 | ANC32.0000.00181 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 8107.65 | 2023-06-30 | 2024-12-31 | 2025-07-31 | 2024-12-31 | C_U139391
2633 |  | CNV-22026175100 INSTALL 3\" OUTLET VALVE | 4000076867 | BET32.0000.00029 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6469.02 | 2023-07-26 | 2023-08-01 |  | 2023-08-01 | C_U139391
2633 |  | CNV-22026175200 RETIRE ~10' - 3\" CSHP | 4000076869 | BET32.0000.00029 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-08-01 | 2023-08-01 |  | 2023-08-01 | C_U139391
2629 |  | CNV-22026182101 INSTALL 8,450' - 2\"/4\" | 4000076871 | GRT32.0000.00080 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 59520.36 | 2023-05-30 | 2023-12-01 | 2025-07-30 | 2023-12-01 | C_U139391
2623 |  | CNV-22026183001 INSTALL 4955'-2\" PMMP | 4000076873 | GRT32.0000.00004 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2024-11-26 | 2024-12-25 |  | 2024-12-25 | C_U139391
2623 |  | CNV-22026205401 INSTALL 1330'-4\" PMMP | 4000076875 | GRT32.0000.00005 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 24550.76 | 2024-03-08 | 2024-04-05 | 2025-07-31 | 2024-04-05 | C_U139391
2631 |  | CNV-22026207100 INSTALL 7870'-2\\\, 4\. | 4000076878 | ANC32.0000.00184 | REL PCNF GMPS MANC NMAT PRC SETC | NEW REV | MAI | 0 | 560952.85 | 2024-01-02 | 2024-12-31 | 2025-07-31 | 2025-08-15 | C_U139391
2621 |  | CNV-24026353800 INSTALL 180' OF 4\"PMMP | 4000076897 | ANC32.0000.00280 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 82257.59 | 2024-09-25 | 2024-10-01 | 2025-08-01 | 2025-04-19 | C_U139391
2629 |  | BET-Winchester Plaza-Winchester | 4000076900 | ANC32.0000.00185 | REL MANC NMAT PRC SETC | NEW NSFS | MAI | 0 | 0 | 2026-12-30 | 2030-12-31 |  | 2030-12-31 | C_U139391
2623 |  | CNV-22026210901 INSTALL 8OO' OF 2\\\PM. | 4000076902 | GRT32.0000.00082 | REL PCNF MANC NMAT PRC SETC | NEW REV | MAI | 0 | 31681.55 | 2024-02-26 | 2024-02-26 | 2025-07-31 | 2024-03-08 | C_U139391
2621 |  | CNV-24026353900 RETIRE 164' OF 4\"CSMP M | 4000076920 | ANC32.0000.00280 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 109.38 | 2024-10-01 | 2024-10-01 |  | 2025-04-19 | C_U139391
2621 |  | GRT-BALL HOMES PENINSULA DOCKSIDE-LEX | 4000076922 | GRT32.0000.00056 | REL PCNF GMPS MANC PRC SETC | NPRG ADJ | MAI | 14249.76 | 79755.73 | 2025-11-18 | 2025-12-31 | 2025-08-01 | 2025-12-31 | C_U139391
2631 | ASHLAND | CNV-24026309600 INSTALL METER | 4000076923 | ANC32.0000.00127 | REL PCNF MANC PRC SETC | NEW ADJ MIFE NSFS | STA | 178.67 | 14941.24 | 2024-12-09 | 2024-12-31 | 2025-08-02 | 2024-12-31 | C_U139391
2621 |  | CNV-24026354300 INSTALL 1750' OF 2\"PMMP | 4000076924 | GRT32.0000.00058 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 29842.78 | 2024-11-14 | 2024-12-31 | 2025-08-01 | 2024-12-31 | C_U139391
2633 | PIPPA PASSES | CNV-24026312800 INSTALL REGULATOR STATIO | 4000076925 | ANC32.0000.00129 | REL NMAT PRC SETC | NEW NSFS | STA | 0 | 0 | 2025-11-25 | 2025-12-31 |  | 2025-12-31 | C_U139391
2621 |  | CNV-24026355900 INSTALL 250' OF 2\"PMMP | 4000076926 | GRT32.0000.00061 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 38937.28 | 2024-11-18 | 2024-11-21 | 2025-08-01 | 2024-11-21 | C_U139391
2621 |  | CNV-24026356000 INSTALL 475' OF 2\\\PM. | 4000076928 | ANC32.0000.00282 | REL GMPS MANC NMAT PRC SETC | NEW | MAI | 0 | 111063.73 | 2025-10-31 | 2025-12-01 |  | 2025-12-01 | C_U139391
2621 |  | CNV-24026328800 NEWTOWN PIKE MP RELOCATI | 4000076930 | PIG32.0000.00043 | REL MANC PRC SETC | NEW ADJ NSFS | MAI | 136097.17 | 1897.5 | 2025-07-09 | 2025-08-30 |  | 2025-09-05 | C_U139391
2621 |  | CNV-24026329000 INSTALL 175' OF 4\" CSHP | 4000076932 | PIG32.0000.00043 | REL PCNF MANC PRC SETC | COCO ADJ FCMP | MAI | 188082.25 | 193324.54 | 2025-07-16 | 2025-09-01 | 2025-08-01 | 2025-09-01 | C_U139391
2621 |  | CNV-24026331500 INSTALL 300' OF 2\"PMMP | 4000076934 | GRT32.0000.00101 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 17818.52 | 2024-10-25 | 2024-10-31 | 2025-07-31 | 2024-10-31 | C_U139391
2621 |  | CNV-24026337000 INSTALL 675' OF 2\"PMMP | 4000076936 | GRT32.0000.00053 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 27451.39 | 2024-04-17 | 2024-04-30 | 2025-07-31 | 2024-06-30 | C_U139391
2621 |  | CNV-24026338000 INSTALL 65'-2\"&4\" PMMP | 4000076938 | PIG32.0000.00010 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 21820.66 | 2024-05-07 | 2024-05-17 | 2025-07-31 | 2024-05-30 | C_U139391
2621 |  | CNV-24026333900 INVESTIGATE ROAD R/W LIM | 4000076939 | PSI32.0000.00019 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 8026.24 | 2024-11-26 | 2024-12-01 |  | 2024-12-01 | C_U139391
2621 |  | CNV-24026338100 RETIRE 42'-2\"&4\" CSMP | 4000076960 | PIG32.0000.00010 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2024-05-17 | 2024-05-17 |  | 2024-05-17 | C_U139391
2631 | CATLETTSBURG | CNV-24026335800 EMER - INSTALL PF REGULA | 4000076961 | ANC32.0000.00132 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 11803.01 | 2024-09-25 | 2024-10-01 |  | 2024-10-01 | C_U139391
2621 |  | CNV-24026338500 INSTALL 585' OF 2\"PMMP | 4000076962 | GRT32.0000.00054 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 20415.57 | 2024-06-24 | 2024-06-28 | 2025-07-31 | 2024-06-28 | C_U139391
2623 |  | CNV-24026339700 OBTAIN HP EASEMENT | 4000076963 | GRT32.0000.00100 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 8024.52 | 2024-11-26 | 2024-12-01 |  | 2024-12-01 | C_U139391
2621 |  | CANCEL | 4000076964 | GRT32.0000.00097 | TECO JBFI MANC PRC SETC | NPRG CAN FCMP | MAI | 0 | -533931.53 | 2025-08-21 | 2025-12-01 |  | 2025-12-01 | C_U139391
2621 | LEXINGTON | CNV-24026340000 EMER-INSTALL NEW PF REGU | 4000076965 | ANC32.0000.00299 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 1735.02 | 2024-10-01 | 2024-10-01 | 2025-07-31 | 2024-10-01 | C_U139391
2621 | LEXINGTON | CNV-24026340200 INSTALL 600' OF 8\\\PM. | 4000076966 | GRT32.0000.00097 | REL MANC NMAT PRC SETC | NEW CAN | MAI | 0 | -170812.19 | 2025-01-08 | 2025-01-31 |  | 2025-01-31 | C_U139391
2621 | LEXINGTON | CNV-24026340100 EMER-RETIRE PF REGULATOR | 4000076967 | ANC32.0000.00299 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 1087.64 | 2024-10-01 | 2024-10-01 | 2025-07-31 | 2024-10-01 | C_U139391
2621 | LEXINGTON | CNV-24026358801 INSTALL 4200' OF 2\\\"/. | 4000076968 | PIG32.0000.00039 | REL CSER MANC NMAT PRC SETC | NEW REV | MAI | 0 | 50990.81 | 2024-09-19 | 2025-06-01 |  | 2025-06-01 | C_U139391
2631 |  | CNV-24026357900 INVESTIGATE LAND RIGHTS | 4000076969 | PSI32.0000.00028 | TECO JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL REV | PSI | 0 | 4975.16 | 2024-11-27 | 2024-12-01 |  | 2024-12-01 | C_U139391
2621 |  | GRT - THE GROVE MLE - NICHOLASVILLE | 4000076970 | GRT32.0000.00063 | REL GMPS MANC PRC SETC | NPRG FCMP | MAI | 399772.9 | 2627219.86 | 2025-09-02 | 2025-11-29 |  | 2026-03-16 | C_U139391
2621 |  | CNV-24026360700 INSTALL 230' OF 4\"PMLP | 4000076972 | PIG32.0000.00039 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 38.22 | 2025-05-30 | 2025-06-01 |  | 2025-06-01 | C_U139391
2621 |  | ANC-SMRP GEORGETOWN RD BSHP-LEXINGTON | 4000076975 | ANC32.0000.00081 | REL MANC PRC SETC | NEW ADJ NSFS REV WENV | MAI | 291270.15 | 2.52 | 2025-12-02 | 2025-12-31 |  | 2025-12-31 | C_U139391
2631 |  | CNV-18026794401 INSTALL 4400'-2\"/4\"PMM | 4000076985 | ANC32.0000.00157 | REL MANC PRC SETC | COCO FCMP NSFS | MAI | 52711.71 | 179108.98 | 2025-06-30 | 2025-12-31 |  | 2025-12-31 | C_U139391
2631 |  | CNV-18026794500 RETIRE 2450' - CS/BSMP | 4000076987 | ANC32.0000.00157 | REL PCNF MANC PRC SETC | COCO FCMP NSFS | MAI | 312.06 | 570.95 | 2025-12-31 | 2025-12-31 | 2025-08-03 | 2025-12-31 | C_U139391
2631 |  | CNV-21026135500 INSTALL 75'-4/6/12\" CSH | 4000077033 | BET32.0000.00003 | REL MANC PRC SETC | NPRG ADJ | MAI | 183004.72 | 28066.03 | 2025-07-25 | 2025-07-31 |  | 2025-12-31 | C_U139391
2631 |  | CNV-21026135600 RETIRE 10'-6/12\" CSHP & | 4000077035 | BET32.0000.00003 | REL PCNF NMAT PRC SETC | NEW NSFS | MAI | 0 | 306.69 | 2025-12-31 | 2025-12-31 | 2025-08-03 | 2025-12-31 | C_U139391
2629 |  |  | 4000077037 | ANC32.0000.00170 | REL PCNF GMPS MANC PRC SETC | NEW ADJ | MAI | 137535.3 | 1585256.47 | 2025-12-31 | 2025-12-31 | 2026-03-04 | 2025-12-31 | C_U139391
2621 |  | CNV-25026378600 INSTALL 42' OF 2\"/4\" P | 4000077139 | PIG32.0000.00015 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 13087.99 | 2025-02-26 | 2025-03-01 | 2025-08-01 | 2025-03-01 | C_U139391
2621 |  | CNV-25026395600 EMER-INSTALL 3' OF 3\"PM | 4000077161 | ANC32.0000.00296 | REL CSER NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 0 | 2026-06-30 | 2026-06-30 |  | 2027-02-18 | C_U139391
2621 |  | CNV-25026395700 EMER-RETIRE 3' OF 3\"PMP | 4000077163 | ANC32.0000.00296 | REL CSER NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 384.19 | 2026-06-30 | 2026-06-30 |  | 2027-02-18 | C_U139391
2621 |  | CNV-25026398000 INSTALL 1100'-8\" PMLP | 4000077166 | ANC32.0002.00002 | REL PCNF GMPS MANC PRC SETC | COCO ADJ FCMP | MAI | 241177.63 | 96648.21 | 2025-08-01 | 2025-08-08 | 2025-08-03 | 2025-08-08 | C_U139391
2621 |  | CNV-25026398800 INSTALL 3670' OF 2\"/4\" | 4000077168 | GRT32.0000.00108 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 67712.09 | 2025-05-02 | 2025-05-30 |  | 2025-05-30 | C_U139391
2621 |  | DYER COVE MLE CNV-25026398900 | 4000077170 | GRT32.0000.00078 | REL GMPS MANC PRC SETC | NPRG ADJ FCMP | MAI | 7741 | 83056.5 | 2025-08-25 | 2025-09-15 |  | 2025-09-15 | C_U139391
2621 |  | CNV-25026402200 INSTALL 270' OF 8"CSHP | 4000077173 | PIG32.0000.00016 | REL MANC PRC SETC | COCO ADJ FCMP MIFE | MAI | 34375.7 | 21065.27 | 2025-07-11 | 2025-07-31 |  | 2025-07-31 | C_U139391
2621 |  | UK PMMP RELOCATION-25026402500 INSTALL 3 | 4000077175 | PIG32.0000.00016 | REL PCNF MANC PRC SETC | NEW ADJ FCMP | MAI | 37503.8 | -58733.53 | 2025-07-16 | 2025-07-31 | 2025-08-03 | 2025-07-31 | C_U139391
2621 |  | CNV-25026409300 PAPER ONLY LP STOPPLE FI | 4000077274 | ANC32.0000.00252 | REL NMAT PRC SETC | NEW FCMP NSFS WENG | MAI | 0 | 0 | 2025-05-30 | 2025-06-01 |  | 2025-06-15 | C_U139391
2623 |  | CNV-25026393900 INVESTIGATE HP CONFLICTS | 4000077302 | PSI32.0000.00029 | REL NMAT PRC SETC | NEW NSFS | PSI | 0 | 4705.03 | 2025-07-01 | 2025-07-01 |  | 2025-07-01 | C_U139391
2621 |  | CNV-25026395100 INVESTIGATE AND MAP MAIN | 4000077304 | PSI32.0000.00040 | TECO JBFI MANC NMAT PRC SETC | NEW CAN FCMP NSFS RECL | PSI | 0.76 | 6658.73 | 2025-06-30 | 2025-06-30 |  | 2025-06-30 | C_U139391
2621 |  | CNV-25026403200 MAINS & SERVICES LOCATE/ | 4000077306 | PSI32.0000.00042 | TECO GMPS JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL | PSI | 0 | 9674.22 | 2025-06-30 | 2025-06-30 |  | 2025-07-01 | C_U139391
2623 | FRANKFORT | CNV-25026403300 INSTALL MONITOR REGULATO | 4000077308 | ANC32.0000.00149 | TECO NMAT PRC SETC | NEW FCMP NSFS | STA | 0 | 172.4 | 2025-05-29 | 2025-05-29 |  | 2025-06-01 | C_U139391
2623 | FRANKFORT | CNV-25026403400 RETIRE MONITORING REG | 4000077310 | ANC32.0000.00149 | TECO NMAT PRC SETC | NEW FCMP NSFS | STA | 0 | 0 | 2025-05-30 | 2025-05-30 |  | 2025-06-01 | C_U139391
2621 |  | CNV-21026145601 INSTALL 1885' - 4\" PMMP | 4000077552 | ANC32.0000.00171 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 13402.78 | 2023-07-05 | 2023-12-31 |  | 2024-12-31 | C_U139391
2621 |  | CNV-21026145700 RETIRE 1840' OF 4\" BSMP | 4000077554 | ANC32.0000.00171 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 116.6 | 2024-09-30 | 2024-09-30 |  | 2024-12-31 | C_U139391
2621 | LEXINGTON | CNV-21026152101 INSTALL 535' OF 8\\\"CS. | 4000077556 | ANC32.0000.00163 | REL MANC NMAT PRC SETC | NPRG | MAI | 788 | 116434.39 | 2025-12-02 | 2025-12-31 |  | 2025-12-31 | C_U139391
2621 |  | CNV-21026152200 RETIRE 457' OF 6 5/8\"BS | 4000077559 | ANC32.0000.00163 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 1873.19 | 2025-12-31 | 2025-12-31 | 2025-08-01 | 2025-12-31 | C_U139391
2621 |  | CNV-21026997801 INSTALL 4600' OF 2\"/6\" | 4000077581 | ANC32.0000.00164 | REL PCNF MANC PRC SETC | NEW ADJ FCMP NSFS | MAI | 29313.8 | 104311.15 | 2023-01-30 | 2023-12-31 | 2025-07-30 | 2023-12-31 | C_U139391
2621 |  | ANC - Rand Ave SMRP - Lexington | 4000077602 | ANC32.0000.00019 | REL PCNF GMPS MANC PRC SETC | NEW WGMA | MAI | 125669.49 | 546413.67 | 2025-07-16 | 2026-12-31 | 2026-03-04 | 2026-12-31 | C_U139391
2621 |  | RICHMOND ROAD PHASE 2 2025 SMRP CNV-2202 | 4000077604 | ANC32.0000.00020 | REL PCNF GMPS MANC PRC SETC | COCO ADJ FCMP | MAI | 130238.25 | 1492718.41 | 2025-09-25 | 2025-12-31 | 2025-08-03 | 2025-12-31 | C_U139391
2629 |  | ANC-SMRP Burns Av LP Install-Winchester | 4000077608 | ANC32.0000.00170 | REL GMPS MANC PRC SETC | NPRG ADJ MIFE | MAI | 3768.12 | 3427397.34 | 2025-05-05 | 2025-12-31 |  | 2026-12-31 | C_U139391
2621 |  | CNV-22026166900 INSTALL 2010' - 8\" & 6\ | 4000077661 | ANC32.0000.00177 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 269020.5 | 2024-04-23 | 2024-05-31 | 2025-07-30 | 2025-01-08 | C_U139391
2632 |  | CNV-22026171600 INSTALL 4371'-2\"&4\" PM | 4000077663 | ANC32.0000.00180 | REL GMPS MANC PRC SETC | NPRG ADJ | MAI | 192726.47 | 399600.77 | 2025-07-18 | 2025-12-31 |  | 2025-12-31 | C_U139391
2629 |  | BET-Red Lick Rd Reg IP-Irvine | 4000077665 | BET32.0000.00022 | REL MANC PRC SETC | NPRG | MAI | 1.17 | 11081.96 | 2025-12-30 | 2025-12-31 |  | 2025-12-31 | C_U139391
2631 |  | CNV-23026246800 INSTALL 800'-4\" PMMP | 4000077744 | PIG32.0000.00036 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-03-17 | 2023-03-17 |  | 2023-04-28 | C_U139391
2629 |  | CNV-23026248100 INSTALL GROUND BED | 4000077746 | ANC32.0000.00301 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 68163.34 | 2023-11-06 | 2024-12-31 | 2025-07-31 | 2024-12-31 | C_U139391
2631 |  | CNV-23026248600 RETIRE 3'-3\" PMLP | 4000077748 | ANC32.0000.00104 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-01-10 | 2023-01-10 |  | 2049-12-31 | C_U139391
2629 |  | CNV-23026248700 INSTALL 2\" SS | 4000077750 | BET32.0000.00033 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-28 | 2023-12-31 |  | 2023-12-31 | C_U139391
2631 |  | CNV-23026249100 INSTALL 100'-2\" PMMP | 4000077752 | GRT32.0000.00028 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 136.4 | 2023-01-26 | 2023-03-27 |  | 2023-03-27 | C_U139391
2623 |  | CNV-23026249500 INSTALL 870'-2\" PMMP | 4000077754 | GRT32.0000.00012 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-04-04 | 2023-04-15 |  | 2023-04-15 | C_U139391
2623 |  | CNV-23026249600 PM- DE ILI PH 2 JIM BEA. | 4000077756 | BET32.0000.00032 | REL MANC NMAT PRC SETC | NEW REV | MAI | 0 | -432898.53 | 2023-12-28 | 2023-12-31 |  | 2023-12-31 | C_U139391
2623 |  | CNV-23026249700 PM- DE ILI PH 2 JIM BEAM | 4000077758 | BET32.0000.00032 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-28 | 2023-12-31 |  | 2023-12-31 | C_U139391
2623 |  | CNV-23026251500 INSTALL 70'-2\" PMLP | 4000077780 | GRT32.0000.00029 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-05-03 | 2023-05-08 |  | 2023-05-08 | C_U139391
2623 |  | CNV-23026254300 TAP W/MAIN 23-0262543-00 | 4000077782 | GRT32.0000.00030 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-03-22 | 2023-03-24 |  | 2023-03-24 | C_U139391
2623 |  | CNV-23026256000 INSTALL 800'OF 2\"PMMP M | 4000077783 | ANC32.0000.00188 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 49280.99 | 2023-10-11 | 2023-10-31 | 2025-07-30 | 2023-10-31 | C_U139391
2633 |  | CNV-23026256300 INSTALL 130'-2\" PMIP | 4000077785 | GRT32.0000.00032 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 12275.65 | 2023-07-26 | 2023-07-31 | 2025-07-30 | 2023-07-31 | C_U139391
2623 |  | CNV-23026257100 INSTALL 300'-2\" PMMP | 4000077787 | GRT32.0000.00031 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 44932.26 | 2023-10-26 | 2023-11-01 | 2025-07-30 | 2023-11-01 | C_U139391
2631 |  | CNV-23026258600 EMER - INSTALL 5'-4\" PM | 4000077789 | ANC32.0000.00213 | REL CSER NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 23.1 | 2049-12-31 | 2049-12-31 |  | 2049-12-31 | C_U139391
2631 |  | CNV-23026258700 EMER- RETIRE 5'-4\" PMIP | 4000077791 | ANC32.0000.00213 | REL CSER NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 13716.55 | 2049-12-31 | 2049-12-31 |  | 2049-12-31 | C_U139391
2631 |  | CNV-23026262200 EMER - INSTALL 4'-2\" PM | 4000077793 | ANC32.0000.00215 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-03-03 | 2049-12-31 |  | 2049-12-31 | C_U139391
2631 |  | CNV-23026262300 EMER - RETIRE 4'-2\" PMM | 4000077795 | ANC32.0000.00215 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-03-03 | 2049-12-31 |  | 2049-12-31 | C_U139391
2623 |  | CNV-23026266100 INSTALL 880'-4\" PHHP | 4000077797 | GRT32.0000.00034 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 39603.07 | 2023-09-05 | 2023-09-15 | 2025-07-30 | 2023-09-15 | C_U139391
2623 |  | CNV-23026266200 INSTALL 1100'-4\" PHHP | 4000077820 | GRT32.0000.00035 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 50705.26 | 2023-09-21 | 2023-09-30 | 2025-07-30 | 2023-09-30 | C_U139391
2629 |  | CNV-23026267600 INSTALL 110'-4\"PMLP | 4000077822 | GRT32.0000.00036 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 21198.05 | 2023-09-01 | 2023-09-01 | 2025-07-30 | 2023-09-15 | C_U139391
2623 |  | CNV-23026268500 PM-DE LINE ILI PH 2 BEND | 4000077823 | BET32.0000.00032 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 371961.49 | 2023-12-28 | 2023-12-31 |  | 2023-12-31 | C_U139391
2623 |  | CNV-23026269000 EMER-INSTALL 4' OF 2\"PM | 4000077825 | ANC32.0000.00040 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-11-30 | 2023-11-30 |  | 2023-11-30 | C_U139391
2623 |  | CNV-23026271000 INSTALL 70'-2\" PMMP | 4000077827 | BET32.0000.00036 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 70.4 | 2023-04-26 | 2023-04-30 |  | 2023-04-30 | C_U139391
2623 |  | CNV-23026271100 ABANDON 60'-2\" PMMP | 4000077829 | BET32.0000.00036 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-04-28 | 2023-04-30 |  | 2023-04-30 | C_U139391
2629 |  | CNV-23026273200 EMER-RETIRE 741'-1\" PMP | 4000077831 | ANC32.0000.00106 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-04-27 | 2023-04-27 |  | 2023-04-29 | C_U139391
2623 |  | CNV-23026273500 EMER-INSTALL 65' OF 2\"P | 4000077833 | ANC32.0000.00225 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-04-18 | 2023-04-18 |  | 2023-04-19 | C_U139391
2623 |  | CNV-23026273600 EMER-RETIRE 55' OF 2\"PA | 4000077835 | ANC32.0000.00225 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 311.11 | 2023-04-19 | 2023-04-19 | 2025-07-30 | 2023-04-19 | C_U139391
2633 |  | CNV-23026274600 EMER - INSTALL 5'-2\" PM | 4000077837 | BET32.0000.00008 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-05-26 | 2023-05-30 |  | 2023-05-30 | C_U139391
2629 |  | CNV-23026274900 EMER - INSTALL 4'-2\" PM | 4000077839 | ANC32.0000.00227 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-04-05 | 2023-04-05 |  | 2023-05-09 | C_U139391
2629 |  | CNV-23026275000 EMER - RETIRE 4'-2\" PMM | 4000077881 | ANC32.0000.00227 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-05-16 | 2049-12-31 |  | 2049-12-31 | C_U139391
2629 |  | CNV-23026275100 RETIRE 276'-3\" BSLP | 4000077883 | PIG32.0000.00018 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-05-25 | 2023-05-26 |  | 2023-05-26 | C_U139391
2631 |  | CNV-23026275200 EMER - INSTALL 3'-2\" PM | 4000077885 | ANC32.0000.00228 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 24.2 | 2023-06-29 | 2023-06-30 |  | 2023-06-30 | C_U139391
2631 |  | CNV-23026275300 EMER - RETIRE 3'-2\" PIP | 4000077887 | ANC32.0000.00228 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-06-30 | 2023-06-30 |  | 2023-06-30 | C_U139391
2631 |  | CNV-23026276500 EMER - ABANDON 5'-4\"CSL | 4000077889 | BET32.0000.00047 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-06-09 | 2023-06-09 |  | 2023-12-30 | C_U139391
2631 |  | CNV-23026277600 INSTALL 595'-2\"PMMP | 4000077891 | ANC32.0000.00230 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 71122.9 | 2023-11-30 | 2023-12-31 | 2025-07-31 | 2023-12-31 | C_U139391
2629 |  | CNV-23026278500 EMER - INSTALL 3'-2\" PM | 4000077893 | ANC32.0000.00232 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 15.4 | 2023-06-01 | 2023-06-01 |  | 2023-06-06 | C_U139391
2629 |  | CNV-23026278600 EMER - RETIRE 3'-2\" PMM | 4000077895 | ANC32.0000.00232 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 8.22 | 2023-06-06 | 2023-06-06 | 2025-07-30 | 2023-06-06 | C_U139391
2631 |  | CNV-23026278700 INSTALL 105'-2\" PMMP | 4000077897 | GRT32.0000.00041 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 493.49 | 2023-06-14 | 2023-06-15 | 2025-07-30 | 2023-06-15 | C_U139391
2623 |  | CNV-23026278900 INSTALL 150'-2\" PMMP | 4000077899 | GRT32.0000.00042 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6557.82 | 2023-08-28 | 2023-08-31 | 2025-07-30 | 2023-08-31 | C_U139391
2631 |  | CNV-23026279500 INSTALL 339'-8\" PMLP | 4000077920 | PIG32.0000.00041 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 24140.5 | 2024-12-13 | 2024-12-30 | 2025-07-31 | 2024-12-30 | C_U139391
2631 |  | CNV-23026279600 RETIRE 339'-8\" BSLP | 4000077922 | PIG32.0000.00041 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1460.29 | 2024-05-10 | 2024-12-30 | 2025-07-31 | 2024-12-30 | C_U139391
2623 |  | CNV-23026279800 INSTALL 1800'-2\" PMMP | 4000077924 | GRT32.0000.00094 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 38792.39 | 2023-08-16 | 2023-08-31 | 2025-07-30 | 2023-08-31 | C_U139391
2631 |  | CNV-23026280200 RETIRE 18570'-2\"-16\" S | 4000077926 | ANC32.0000.00101 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 78531.65 | 2024-07-31 | 2024-07-31 | 2025-07-31 | 2025-03-16 | C_U139391
2631 |  | CNV-23026280300 RETIRE 1107'-2\"&8\" CS& | 4000077928 | ANC32.0000.00101 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 665.59 | 2023-06-26 | 2049-12-31 | 2025-07-31 | 2049-12-31 | C_U139391
2623 |  | CNV-23026281200 EMER-INSTALL 2' OF 2\"PM | 4000077930 | ANC32.0000.00045 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | -263.32 | 2023-06-26 | 2023-06-26 |  | 2023-06-26 | C_U139391
2623 |  | CNV-23026281400 INSTALL 1865'-2\"/4\" PM | 4000077932 | GRT32.0000.00043 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 49484.4 | 2023-10-17 | 2023-10-31 | 2025-07-31 | 2023-11-17 | C_U139391
2629 |  | CNV-23026281600 EMER-INSTALL 3'-3\" PMMP | 4000077934 | ANC32.0000.00234 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | -333.3 | 2024-09-25 | 2024-09-30 |  | 2025-05-27 | C_U139391
2629 |  | CNV-23026281700 EMER-RETIRE 3'-3\" PMAP | 4000077936 | ANC32.0000.00234 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2024-09-30 | 2024-09-30 |  | 2025-05-27 | C_U139391
2633 |  | CNV-23026282000 INSTALL 40'-4\" PMIP | 4000077938 | PIG32.0000.00042 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 31561.33 | 2023-07-24 | 2023-07-30 | 2025-07-30 | 2023-07-30 | C_U139391
2621 |  | CNV-22026228500 INSTALL 167'-2\" PMMP | 4000077957 | PIG32.0000.00031 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 34180.49 | 2024-06-14 | 2024-06-30 | 2025-07-31 | 2024-06-30 | C_U139391
2621 |  | CNV-22026228600 RETIRE 136'-2\" PMMP | 4000077959 | PIG32.0000.00031 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 50.08 | 2024-06-28 | 2024-06-30 | 2025-07-31 | 2024-06-30 | C_U139391
2633 |  | CNV-23026282100 RETIRE 36'-4\" BSIP | 4000077960 | PIG32.0000.00042 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 124.11 | 2023-07-28 | 2023-07-30 | 2025-07-30 | 2023-07-30 | C_U139391
2629 |  | CNV-23026282600 EMER - RETIRE 216'-2\" P | 4000077962 | ANC32.0000.00107 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 5051.47 | 2024-08-28 | 2024-08-31 |  | 2025-04-17 | C_U139391
2623 |  | CNV-23026282800 EMER - INSTALL 5'-2\" PM | 4000077964 | ANC32.0000.00046 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 7813.18 | 2024-03-21 | 2024-03-31 | 2025-07-31 | 2024-04-28 | C_U139391
2631 |  | CNV-23026283101 INSTALL 780'-2\" PMMP | 4000077966 | GRT32.0000.00044 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS WENG | MAI | 0 | 25623.87 | 2025-05-21 | 2025-05-30 | 2025-08-03 | 2025-05-30 | C_U139391
2623 |  | CNV-23026283801 INSTALL 5705'-2\"/4\" PM | 4000077968 | GRT32.0000.00095 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 222206.91 | 2024-01-22 | 2024-03-01 | 2025-07-31 | 2024-05-31 | C_U139391
2623 |  | CNV-23026284000 EMER-INSTALL 2' OF 3\"PM | 4000077970 | ANC32.0000.00047 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 11033.96 | 2023-11-30 | 2023-11-30 | 2025-07-30 | 2024-07-25 | C_U139391
2631 |  | CNV-23026284800 EMER - INSTALL 40'-4\" P | 4000077972 | ANC32.0000.00238 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 389.63 | 2024-03-27 | 2024-03-31 | 2025-07-30 | 2024-03-31 | C_U139391
2631 |  | CNV-23026284900 EMER - RETIRE 40'-4\" BS | 4000077974 | ANC32.0000.00238 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 320.17 | 2024-03-28 | 2024-03-31 | 2025-07-30 | 2024-03-31 | C_U139391
2623 |  | CNV-23026285800 EMER-INSTALL 3' OF 2\"PM | 4000077976 | ANC32.0000.00048 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3521.71 | 2023-07-24 | 2023-07-24 | 2025-07-30 | 2023-07-25 | C_U139391
2629 |  | CNV-23026286000 EMER - INSTALL 6'-2\" PM | 4000077978 | ANC32.0000.00239 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4064.86 | 2024-10-21 | 2024-10-31 |  | 2025-06-15 | C_U139391
2621 |  | CNV-22026231301 INSTALL 925' OF 2\"PMMP | 4000077981 | ANC32.0000.00191 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2024-11-11 | 2024-12-31 |  | 2024-12-31 | C_U139391
2621 |  | CNV-22026234001 INSTALL 500' OF 2\"/4\"P | 4000077983 | GRT32.0000.00008 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-03-21 | 2023-04-15 |  | 2023-04-15 | C_U139391
2621 | LEXINGTON |  | 4000077985 | ANC32.0000.00017 | REL MANC PRC SETC | COCO ADJ FCMP | MAI | 21327.92 | 73009.05 | 2025-07-17 | 2025-12-31 |  | 2025-12-31 | C_U139391
2621 |  | CNV-22026236700 INSTALL 134'-4\" PMLP | 4000077987 | PIG32.0000.00032 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 12290.93 | 2024-03-18 | 2024-03-20 | 2025-07-31 | 2024-03-20 | C_U139391
2621 |  | CNV-22026236800 RETIRE 130'-4\" PLP | 4000077989 | PIG32.0000.00032 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 7455.47 | 2024-03-20 | 2024-03-20 | 2025-07-31 | 2024-03-20 | C_U139391
2621 |  | SMRP LAFAYETTE HS | 4000077991 | ANC32.0000.00194 | REL PCNF GMPS MANC PRC SETC | COCO ADJ FCMP | MAI | 3481319.88 | 1322123.24 | 2025-08-05 | 2025-12-31 | 2025-08-01 | 2025-12-31 | C_U139391
2621 |  | CNV-22026238200 INSTALL 205' OF 2\"PMMP | 4000077994 | GRT32.0000.00010 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 237.6 | 2023-01-25 | 2023-01-31 |  | 2023-01-31 | C_U139391
2621 |  | MONTCLAIR/COOPER 2025 SMRP CNV-220262388 | 4000077996 | ANC32.0000.00198 | REL PCNF GMPS MANC PRC SETC | COCO ADJ FCMP | MAI | 197771.79 | 1074876.42 | 2025-08-01 | 2025-12-01 | 2025-08-01 | 2025-12-31 | C_U139391
2621 |  | CNV-22026239702 INSTALL 8650' - 2,4,6\" | 4000077998 | ANC32.0000.00199 | REL PCNF MANC PRC SETC | COCO FCMP NSFS REV WENG | MAI | 161307.39 | 159842.86 | 2024-06-20 | 2025-02-28 | 2025-08-01 | 2025-02-28 | C_U139391
2629 |  | CNV-23026286100 EMER - RETIRE 6'-2\" PMM | 4000078000 | ANC32.0000.00239 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 509.79 | 2024-10-31 | 2024-10-31 | 2025-07-30 | 2025-06-15 | C_U139391
2632 |  | CNV-23026287300 INSTALL 121'-4\" CSMP | 4000078002 | PIG32.0000.00009 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 79739.32 | 2024-03-08 | 2024-03-30 | 2025-08-01 | 2024-12-30 | C_U139391
2629 |  | CNV-23026287800 INSTALL 500'-4\" PMMP | 4000078004 | BET32.0000.00010 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 92799.54 | 2023-11-13 | 2023-11-30 | 2025-07-30 | 2023-11-30 | C_U139391
2629 |  | CNV-23026288600 EMER - RETIRE 3'-2\" PMP | 4000078006 | ANC32.0000.00241 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3766.85 | 2023-08-11 | 2049-12-31 |  | 2049-12-31 | C_U139391
2623 |  | CNV-23026288901 INSTALL 880'-4\" PMMP | 4000078007 | GRT32.0000.00040 | REL GMPS MANC PRC SETC | NPRG ADJ FCMP | MAI | 382159.46 | 31525.46 | 2025-07-31 | 2025-07-31 |  | 2025-07-31 | C_U139391
2623 |  | CNV-23026289700 INSTALL 70' OF 3\"PMLP M | 4000078009 | ANC32.0000.00242 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1556.55 | 2023-11-28 | 2023-11-30 |  | 2024-08-31 | C_U139391
2623 |  | CNV-23026289800 RETIRE 271' OF 2\"/3\"BS | 4000078011 | ANC32.0000.00242 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 15400.09 | 2023-11-30 | 2023-11-30 | 2025-07-31 | 2024-08-31 | C_U139391
2629 |  | CNV-23026289900 EMER-INSTALL 8'-3\" PMMP | 4000078013 | ANC32.0000.00243 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2245.29 | 2023-08-23 | 2023-09-03 |  | 2023-09-06 | C_U139391
2629 |  | CNV-23026290000 EMER-RETIRE 8'-3\" PAMP | 4000078016 | ANC32.0000.00243 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3557.52 | 2023-08-23 | 2023-09-03 | 2025-07-30 | 2023-09-06 | C_U139391
2633 |  | CNV-23026291200 EMER - INSTALL 8'-3\" PM | 4000078018 | ANC32.0000.00246 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 18113.32 | 2023-08-30 | 2023-08-31 |  | 2023-08-31 | C_U139391
2621 |  | CNV-22026241500 INSTALL 40'-2\" PMMP | 4000078020 | BET32.0000.00031 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-26 | 2023-12-31 |  | 2023-12-31 | C_U139391
2621 |  | CNV-22026242301 INSTALL 8\"POLY VALVE W/ | 4000078022 | ANC32.0000.00115 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 18738.58 | 2023-10-02 | 2023-10-15 |  | 2023-10-15 | C_U139391
2621 |  | CNV-22026242600 INSTALL 500' - 4\" PMMP | 4000078025 | ANC32.0000.00115 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-09-18 | 2023-10-01 |  | 2023-10-01 | C_U139391
2621 |  | CNV-22026242700 INSTALL 350' OF 8\"CSHP | 4000078027 | PIG32.0000.00004 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 312402.5 | 2023-07-10 | 2023-09-01 | 2025-07-30 | 2023-09-30 | C_U139391
2631 |  | CNV-20026949600 PSI FOR CWT HEATER INSTA | 4000078032 | GRT32.0000.00109 | REL NMAT PRC SETC | NEW NSFS | PSI | 0 | 0 | 2025-12-29 | 2025-12-29 |  | 2025-12-31 | C_U139391
2621 |  | CNV-22026158800 INSTALL 540' OF 4\"/8\"P | 4000078033 | ANC32.0000.00009 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-11-21 | 2023-12-31 |  | 2023-12-31 | C_U139391
2631 | SOUTH SHORE | CNV-20026971400 INSTALL CWT MODEL 140 HE | 4000078034 | GRT32.0000.00109 | REL NMAT PRC SETC | NEW NSFS | STA | 0 | 0 | 2025-12-23 | 2025-12-31 |  | 2025-12-31 | C_U139391
2621 |  | CV - LARKSPUR INSTALL 16'- 6" PMMP | 4000078036 | BET32.0000.00004 | REL MANC PRC SETC | NEW ADJ NSFS | MAI | 30134.34 | 10.04 | 2026-12-29 | 2026-12-31 |  | 2026-12-31 | C_U139391
2621 |  | CNV-22026162102 INSTALL 8150' OF 2\"/4\" | 4000078038 | ANC32.0000.00172 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 28375.28 | 2023-11-01 | 2023-12-31 | 2025-07-31 | 2023-11-01 | C_U139391
2633 |  | CNV-23026291300 EMER - RETIRE 7'3\" BS&P | 4000078040 | ANC32.0000.00246 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 392.92 | 2023-08-31 | 2023-08-31 | 2025-07-30 | 2023-08-31 | C_U139391
2623 |  | CNV-23026292201 INSTALL 360'-4\" PMMP | 4000078042 | GRT32.0000.00003 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2024-01-15 | 2024-02-29 |  | 2024-02-29 | C_U139391
2631 |  | CNV-23026292300 INSTALL 2\" SS | 4000078044 | BET32.0000.00039 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 772.22 | 2024-02-27 | 2024-02-28 | 2025-07-31 | 2024-02-28 | C_U139391
2631 |  | CNV-23026292400 RETIRE 154'-2\" CSIP | 4000078046 | BET32.0000.00039 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 13099.19 | 2024-02-28 | 2024-02-28 | 2025-07-31 | 2024-02-28 | C_U139391
2631 |  | RIVERSIDE 2025 SMPR -CNV-23026293500 | 4000078048 | ANC32.0000.00200 | REL PCNF GMPS MANC PRC SETC | COCO ADJ FCMP | MAI | 149415.74 | 397969.27 | 2025-07-29 | 2025-10-01 | 2025-07-31 | 2025-10-01 | C_U139391
2629 |  | CNV-23026293900 EMER-INSTALL 3' OF 2\"PM | 4000078050 | ANC32.0000.00022 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 5282 | 2023-09-05 | 2023-09-05 |  | 2023-09-07 | C_U139391
2631 |  | CNV-23026294700 INSTALL 70'-2\" PMIP | 4000078052 | GRT32.0000.00013 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 8507.52 | 2023-12-28 | 2024-01-02 | 2025-07-31 | 2024-01-02 | C_U139391
2623 |  | CNV-23026296400 INSTALL 110' OF 2\"PMMP | 4000078054 | ANC32.0000.00023 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 27214.96 | 2023-12-18 | 2023-12-31 | 2025-07-31 | 2024-01-10 | C_U139391
2631 |  | CNV-23026296700 INSTALL 165' OF 2\" PMIP | 4000078056 | GRT32.0000.00016 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3877.96 | 2023-11-27 | 2023-11-30 | 2025-07-31 | 2023-11-30 | C_U139391
2629 |  | ANC-SMRP Rio Vista-Paris | 4000078057 | ANC32.0000.00024 | REL PCNF MANC PRC SETC | NEW | MAI | 2471492.73 | 1939.39 | 2026-10-31 | 2027-12-31 | 2026-03-04 |  | C_U139391
2623 |  | CNV-23026298800 INSTALL 900'-2\" PMMP MA | 4000078059 | GRT32.0000.00017 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 59974.8 | 2024-04-04 | 2024-04-17 | 2025-07-31 | 2024-04-17 | C_U139391
2621 |  | CNV-22026162200 RETIRE 4600' OF 4\"/6\"B | 4000078060 | ANC32.0000.00172 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1449.39 | 2023-12-31 | 2023-12-31 | 2025-07-31 | 2024-08-11 | C_U139391
2621 |  | CNV-22026163200 INSTALL 775' OF 2\"PMMP | 4000078062 | ANC32.0000.00173 | REL GMPS NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2180.97 | 2023-12-05 | 2023-12-31 |  | 2023-12-31 | C_U139391
2621 |  | ANC-BOB O LINK SMRP-LEXINGTON PLANNED F | 4000078064 | ANC32.0000.00010 | REL PCNF GMPS MANC PRC SETC | SCHD ADJ | MAI | 1710160.13 | 1002334.59 | 2025-10-22 | 2026-12-31 | 2026-02-16 | 2026-12-31 | C_U139391
2621 |  | CNV-22026165501 INSTALL 3385' OF 2\" PMM | 4000078066 | ANC32.0000.00176 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2024-01-22 | 2024-12-31 |  | 2024-12-31 | C_U139391
2629 |  | ANC-SMRP Harrsion Ave-Mt Sterling | 4000078081 | ANC32.0000.00202 | REL PCNF GMPS MANC PRC SETC | NPRG | MAI | 3808532.52 | 846811.19 | 2026-01-01 | 2026-12-31 | 2026-03-12 | 2026-12-31 | C_U139391
2631 |  | CNV-23026300300 INSTALL 1810'-2\" PMMP | 4000078083 | GRT32.0000.00019 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 92698.16 | 2024-08-23 | 2024-09-20 | 2025-08-01 | 2024-09-20 | C_U139391
2629 |  | CNV-23026300401 INSTALL 1150' 4/2\" PMMP | 4000078085 | PIG32.0000.00035 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 202.42 | 2024-02-22 | 2024-03-15 |  | 2024-04-26 | C_U139391
2629 |  | CNV-23026300600 INSTALL 180'-4\" PMLP | 4000078087 | PIG32.0000.00006 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 49799.74 | 2023-12-18 | 2023-12-31 | 2025-07-31 | 2024-01-26 | C_U139391
2623 |  | CNV-23026301200 INSTALL 60' OF 6\"PMMP M | 4000078089 | PIG32.0000.00007 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | -18585.12 | 2025-03-26 | 2025-04-01 | 2025-08-02 | 2025-04-01 | C_U139391
2629 |  | GRT-Locust Hill Acres MLE-Winchester | 4000078091 | GRT32.0000.00020 | REL PCNF GMPS MANC PRC SETC | COCO ADJ FCMP | MAI | 59513.98 | 163090.85 | 2025-09-11 | 2025-10-31 | 2025-08-03 | 2025-10-31 | C_U139391
2629 |  | CNV-23026302800 EMER - INSTALL 2'-3\" PM | 4000078093 | ANC32.0000.00203 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2064.2 | 2023-10-18 | 2023-10-27 |  | 2023-10-30 | C_U139391
2629 |  | CNV-23026302900 EMER - RETIRE 2'-3\" PMP | 4000078095 | ANC32.0000.00203 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1224.64 | 2023-10-27 | 2023-10-27 |  | 2023-10-30 | C_U139391
2629 |  | CNV-23026303000 EMER - RETIRE 13'-3\" BS | 4000078097 | ANC32.0000.00103 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 18214.32 | 2023-10-26 | 2023-10-31 | 2025-08-01 | 2024-12-31 | C_U139391
2629 |  | CNV-23026303400 INSTALL 20'-2\" CSHP | 4000078099 | BET32.0000.00021 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 79958.27 | 2024-12-02 | 2024-12-02 | 2025-07-31 | 2024-12-15 | C_U139391
2623 |  | CNV-19026878100 INVESTIGATE LAND RIGHT/E | 4000078119 | PSI32.0000.00004 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 13171.38 | 2024-11-26 | 2024-11-26 |  | 2024-12-01 | C_U139391
2629 |  | GRT-Harrison Cty HS MLE-Cynthiana | 4000078121 | GRT32.0000.00021 | REL MANC NMAT PRC SETC | NEW NSFS | MAI | 0 | 0 | 2026-02-02 | 2026-10-25 |  | 2026-10-25 | C_U139391
2629 |  | CNV-23026306000 EMER-INSTALL 2'-3\" PMMP | 4000078123 | ANC32.0000.00028 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4274.2 | 2023-11-08 | 2023-11-08 |  | 2023-11-17 | C_U139391
2633 |  | CNV-23026307300 INSTALL ~100'-2\" PMIP | 4000078125 | GRT32.0000.00023 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 22820.46 | 2024-01-02 | 2024-01-15 | 2025-07-31 | 2024-01-31 | C_U139391
2623 |  | CNV-23026307400 EMER-INSTALL 3' OF 2\"PM | 4000078127 | ANC32.0000.00029 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 824.94 | 2024-03-01 | 2024-03-01 |  | 2024-03-01 | C_U139391
2623 |  | CNV-23026308601 INSTALL 675'-2\" PMMP | 4000078128 | GRT32.0000.00024 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6607.39 | 2024-04-24 | 2024-04-30 |  | 2024-05-30 | C_U139391
2623 |  | CNV-19026881800 ACQUIRE EASEMENT/LAND RI | 4000078141 | PSI32.0000.00004 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 0 | 2020-12-31 | 2020-12-31 |  | 2020-12-31 | C_U139391
2621 |  | CNV-19026907000 OBTAIN USABLE EASEMENT | 4000078143 | PSI32.0000.00003 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 0 | 2022-12-29 | 2022-12-31 |  | 2022-12-31 | C_U139391
2623 |  | CNV-19026907200 INVESTIGATE ENCROACHMENT | 4000078145 | PSI32.0000.00037 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 0 | 2020-12-31 | 2020-12-31 |  | 2020-12-31 | C_U139391
2629 |  | PSI-Colby Rd HP ROW-Winchester | 4000078189 | PSI32.0000.00007 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 6842.64 | 2021-12-30 | 2021-12-31 |  | 2021-12-31 | C_U139391
2629 |  | ANC-Levee Rd POD Valve-Mt Sterling | 4000078191 | ANC32.0000.00118 | REL NMAT PRC SETC | NEW NSFS REV | STA | 0 | 0 | 2023-12-28 | 2023-12-31 |  | 2023-12-31 | C_U139391
2623 |  | CNV-21026145400 INVESTIGATE &/OR ACQUIRE | 4000078193 | PSI32.0000.00008 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 0 | 2021-12-29 | 2021-12-31 |  | 2021-12-31 | C_U139391
2629 |  | CNV-21026149800 RETIRE R-1615 | 4000078195 | ANC32.0000.00189 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-12-21 | 2023-12-31 |  | 2023-12-31 | C_U139391
2629 |  | PSI-Wisemantown Rd-Irvine | 4000078197 | PSI32.0000.00037 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 10955.18 | 2022-12-29 | 2022-12-31 |  | 2022-12-31 | C_U139391
2621 |  | CNV-23026248200 EMER - INSTALL 2'-2\" PM | 4000078235 | ANC32.0000.00211 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-01-06 | 2023-01-06 |  | 2023-01-09 | C_U139391
2621 |  | CNV-23026248300 EMER - RETIRE ~2'-2\"PMP | 4000078237 | ANC32.0000.00211 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-01-09 | 2023-01-09 |  | 2023-01-09 | C_U139391
2621 |  | CNV-23026248400 EMER-INSTALL 3' OF 2\"PM | 4000078239 | ANC32.0000.00031 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-09-29 | 2023-09-30 |  | 2023-09-30 | C_U139391
2621 |  | CNV-22026166700 INSTALL 16'-2\"PMMP | 4000078245 | BET32.0000.00005 | REL CSER NMAT PRC SETC | NEW NSFS | MAI | 0 | 0 | 2026-12-29 | 2026-12-31 |  | 2026-12-31 | C_U139391
2621 |  | CNV-22026167200 INSTALL 720'- 4\" PMMP | 4000078247 | ANC32.0000.00011 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-11-14 | 2023-12-31 |  | 2023-12-31 | C_U139391
2621 |  | CNV-22026167800 INSTALL CRITICAL VALVE | 4000078249 | BET32.0000.00030 | REL CSER NMAT PRC SETC | NEW NSFS | MAI | 0 | 0 | 2026-12-29 | 2026-12-31 |  | 2026-12-31 | C_U139391
2621 |  | CNV-22026167900 RERTIRE APPROX 12'-4\" C | 4000078251 | BET32.0000.00030 | REL CSER NMAT PRC SETC | NEW NSFS | MAI | 0 | 0 | 2026-12-31 | 2026-12-31 |  | 2026-12-31 | C_U139391
2621 |  | CNV-22026171100 INSTALL 2715' OF 2\"/4\" | 4000078253 | ANC32.0000.00178 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 341540.67 | 2024-01-22 | 2024-08-19 | 2025-07-31 | 2024-08-19 | C_U139391
2621 |  | CNV-22026171200 RETIRE 2300' OF 3\"/6\"B | 4000078255 | ANC32.0000.00178 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 233.2 | 2024-08-19 | 2024-08-19 |  | 2024-08-19 | C_U139391
2621 |  | CNV-22026178900 INSTALL 620' OF 12\"CSHP | 4000078257 | ANC32.0000.00182 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 55631.6 | 2023-06-09 | 2023-07-31 | 2025-07-30 | 2024-03-31 | C_U139391
2621 |  | CNV-22026179100 RETIRE 520' OF 12\"MJBSH | 4000078259 | ANC32.0000.00182 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1186.35 | 2023-07-31 | 2023-07-31 | 2025-07-30 | 2024-03-31 | C_U139391
2621 |  | CNV-23026249300 EMER-INSTALL 5' OF 2\"PM | 4000078261 | ANC32.0000.00212 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-01-13 | 2023-01-13 |  | 2023-01-13 | C_U139391
2621 |  | CNV-23026249400 EMER-RETIRE 5' OF 2\"PMM | 4000078263 | ANC32.0000.00212 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-01-13 | 2023-01-13 |  | 2023-01-13 | C_U139391
2621 |  | CNV-23026251700 INSTALL 2060' OF 2\" PMM | 4000078265 | GRT32.0000.00087 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-03-29 | 2023-04-15 |  | 2023-04-15 | C_U139391
2621 |  | CNV-23026252000 EMER-INSTALL 3' OF 6\"PM | 4000078267 | ANC32.0000.00032 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-09-27 | 2023-09-30 |  | 2023-09-30 | C_U139391
2621 |  | CNV-23026252200 EMER-INSTALL 3' OF 4\"PM | 4000078269 | ANC32.0000.00033 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-09-28 | 2023-09-30 |  | 2023-09-30 | C_U139391
2621 |  | CNV-23026252600 INSTALL 3' OF 4\"PMLP MA | 4000078271 | ANC32.0000.00034 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-28 | 2023-12-31 |  | 2024-08-26 | C_U139391
2621 |  | CNV-23026256400 INSTALL 25' OF 2\"PMMP M | 4000078273 | GRT32.0000.00033 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6647.08 | 2023-07-28 | 2023-07-31 | 2025-07-30 | 2023-10-26 | C_U139391
2621 |  | CNV-23026259000 EMER-INST 85'-4\"PMMP MN | 4000078275 | ANC32.0000.00214 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 100.1 | 2023-02-15 | 2023-02-21 |  | 2023-02-24 | C_U139391
2621 |  | CNV-23026259100 EMER-RETIRE 85' OF 4\"PA | 4000078277 | ANC32.0000.00214 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-02-21 | 2023-02-21 |  | 2023-02-24 | C_U139391
2621 |  | CNV-23026262700 EMER-INSTALL 5' OF 2\"PM | 4000078279 | ANC32.0000.00216 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-03-07 | 2023-09-30 |  | 2024-05-19 | C_U139391
2621 |  | CNV-22026183100 INSTALL 3090' OF 2-4\" P | 4000078281 | PIG32.0000.00027 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 136292.1 | 2023-07-03 | 2023-08-30 | 2025-07-30 | 2023-10-30 | C_U139391
2621 |  | CNV-22026183301 SMRP INSTALL 1120' 8-12\ | 4000078283 | PIG32.0000.00027 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 23594.6 | 2023-11-29 | 2024-03-15 |  | 2024-03-15 | C_U139391
2621 |  | CNV-22026184800 INSTALL 3775'-2\" PMMP | 4000078285 | PIG32.0000.00029 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-03-15 | 2023-06-30 |  | 2023-06-30 | C_U139391
2621 |  | CNV-22026184900 RETIRE 3315'-2\"&4\"BSLP | 4000078287 | PIG32.0000.00029 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-06-30 | 2023-06-30 |  | 2023-06-30 | C_U139391
2621 |  | CNV-22026210301 INSTALL 850' OF 4\"PMMP | 4000078289 | GRT32.0000.00006 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 413.67 | 2022-12-06 | 2023-02-01 |  | 2023-02-01 | C_U139391
2621 |  | CNV-22026219400 INSTALL 380' OF 4\"PMMP | 4000078291 | ANC32.0000.00186 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 41.65 | 2023-12-07 | 2023-12-31 |  | 2023-12-31 | C_U139391
2621 |  | CNV-22026223600 INSTALL 3000' OF 2\"PMMP | 4000078293 | GRT32.0000.00083 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 51747.22 | 2023-07-03 | 2023-07-31 | 2025-07-30 | 2023-08-30 | C_U139391
2621 |  | CNV-22026223700 INSTALL 1296'-2\"&4\" PM | 4000078295 | PIG32.0000.00003 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | -695.88 | 2023-01-23 | 2023-03-30 |  | 2023-04-30 | C_U139391
2621 |  | CNV-22026223900 INSTALL 1067'-4\" PMMP | 4000078297 | PIG32.0000.00002 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 317.13 | 2023-03-17 | 2023-03-30 |  | 2023-03-30 | C_U139391
2621 |  | CNV-22026224201 INSTALL 2300' OF 2\"/4\" | 4000078299 | ANC32.0000.00187 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6065.09 | 2024-09-05 | 2024-12-31 | 2025-08-01 | 2024-12-31 | C_U139391
2621 |  | CNV-23026262800 EMER-RETIRE 5' OF 2\"PMP | 4000078301 | ANC32.0000.00216 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-03-07 | 2023-09-30 |  | 2024-05-19 | C_U139391
2621 |  | CNV-23026264700 INSTALL 100' OF 3\"PMLP | 4000078303 | ANC32.0000.00220 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 108.9 | 2023-12-21 | 2023-12-31 |  | 2024-08-11 | C_U139391
2621 |  | CNV-23026266300 EMER-INSTALL 3' OF 2\"PM | 4000078306 | ANC32.0000.00037 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-11-29 | 2023-11-30 |  | 2023-11-30 | C_U139391
2621 |  | CNV-23026267700 EMER-RETIRE 40' OF 6\"BS | 4000078308 | ANC32.0000.00105 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-12-28 | 2023-12-31 |  | 2023-12-31 | C_U139391
2621 |  | CNV-23026268200 INSERT 160' OF 3\"PMLP M | 4000078310 | ANC32.0000.00223 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 179.3 | 2023-12-27 | 2023-12-31 |  | 2024-08-10 | C_U139391
2621 |  | CNV-23026268300 RETIRE 160' OF 4\"BSLP M | 4000078312 | ANC32.0000.00223 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-04-04 | 2023-04-04 |  | 2024-08-10 | C_U139391
2621 |  | CNV-23026272300 EMER-INSTALL 3\" NC POLY | 4000078314 | BET32.0000.00037 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-09-29 | 2023-10-01 |  | 2023-10-01 | C_U139391
2621 |  | CNV-23026272400 EMER-RETIRE 3\"PV C16-87 | 4000078316 | BET32.0000.00037 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-09-29 | 2023-10-01 |  | 2023-10-01 | C_U139391
2621 |  | CNV-23026273000 INSTALL 20'-4\"PMMP W/NE | 4000078318 | BET32.0000.00007 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3025.27 | 2023-06-26 | 2023-10-01 |  | 2023-10-01 | C_U139391
2621 |  | CNV-23026273700 INSTALL 6' OF 2\"PMMP MA | 4000078341 | ANC32.0000.00226 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 59 | 2024-07-11 | 2024-07-12 | 2025-08-01 | 2025-05-03 | C_U139391
2621 |  | CNV-23026273800 RETIRE 2\" POLY VALVE C9 | 4000078343 | ANC32.0000.00226 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3542.89 | 2024-09-30 | 2024-09-30 | 2025-07-31 | 2025-05-03 | C_U139391
2621 |  | CNV-23026276300 EMER-INSTALL 2\"POLY VAL | 4000078345 | BET32.0000.00009 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 25.98 | 2023-09-28 | 2023-10-01 |  | 2023-10-01 | C_U139391
2621 |  | CNV-23026276900 RETIRE 250' OF 3\"BSLP M | 4000078347 | PIG32.0000.00019 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-09-01 | 2023-09-01 |  | 2023-09-01 | C_U139391
2621 |  | CNV-23026277000 EMER-INSTALL 15' OF 8\"P | 4000078349 | ANC32.0000.00229 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4392.43 | 2024-07-29 | 2024-07-31 | 2025-07-30 | 2025-03-13 | C_U139391
2621 |  | CNV-23026277100 EMER-RETIRE 15' OF 8\"BS | 4000078351 | ANC32.0000.00229 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 305.34 | 2024-07-31 | 2024-07-31 | 2025-07-30 | 2025-03-13 | C_U139391
2621 |  | CNV-23026277200 EMER-RETIRE 55' OF 6\"PM | 4000078353 | PIG32.0000.00020 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 91.2 | 2023-06-30 | 2023-07-01 |  | 2023-07-01 | C_U139391
2621 |  | CNV-23026277900 EMER - INSTALL 69'-6\" P | 4000078354 | ANC32.0000.00231 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 328.02 | 2024-08-31 | 2024-08-31 | 2025-07-30 | 2025-04-27 | C_U139391
2621 |  | CNV-23026278000 EMER - RETIRE 69'-6\" BS | 4000078357 | ANC32.0000.00231 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2024-08-31 | 2024-08-31 |  | 2025-04-27 | C_U139391
2621 |  | CNV-23026280800 EMER-INSTALL 62' OF 4\"P | 4000078359 | ANC32.0000.00233 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3419.1 | 2023-11-30 | 2023-12-01 | 2025-07-30 | 2023-12-01 | C_U139391
2621 |  | CNV-23026280900 EMER-RETIRE 62' OF 4\"BS | 4000078381 | ANC32.0000.00233 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2158.04 | 2023-12-01 | 2023-12-01 | 2025-07-30 | 2023-12-01 | C_U139391
2621 |  | CNV-23026282700 EMER-ABANDON 333' OF 2\" | 4000078383 | ANC32.0000.00108 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2814.68 | 2023-07-06 | 2023-07-06 | 2025-07-30 | 2023-12-01 | C_U139391
2621 |  | CNV-23026283400 EMER - INSTALL 5'-3\" PM | 4000078385 | ANC32.0000.00235 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3224.58 | 2024-09-30 | 2024-09-30 | 2025-07-30 | 2025-05-03 | C_U139391
2621 |  | CNV-23026283500 EMER - RETIRE 5'-3\" PMP | 4000078387 | ANC32.0000.00235 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 20.18 | 2024-09-30 | 2024-09-30 | 2025-07-30 | 2025-05-03 | C_U139391
2621 |  | CNV-23026284300 EMER-INSTALL 490' OF 2\" | 4000078389 | ANC32.0000.00236 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 34965.39 | 2023-09-25 | 2023-10-01 |  | 2023-10-01 | C_U139391
2621 |  | CNV-23026284400 EMER-RETIRE 520' OF 4\"B | 4000078391 | ANC32.0000.00236 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 223.87 | 2023-09-29 | 2023-10-01 | 2025-07-30 | 2023-10-01 | C_U139391
2621 |  | CNV-23026284500 INSTALL 80'4\" PMLP | 4000078393 | ANC32.0000.00237 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4827.81 | 2024-08-26 | 2024-08-31 | 2025-07-30 | 2025-04-25 | C_U139391
2621 |  | CNV-23026284600 RETIRE 80'-4\" BSLP | 4000078395 | ANC32.0000.00237 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3894.31 | 2024-08-30 | 2024-08-31 | 2025-07-30 | 2025-04-25 | C_U139391
2621 |  | CNV-23026285300 EMER - RETIRE 159'-3\"BS | 4000078397 | ANC32.0000.00291 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2373.67 | 2023-07-24 | 2023-07-24 | 2025-07-30 | 2023-07-24 | C_U139391
2621 |  | CNV-23026286300 RETIRE 306' OF 3\"BSLP M | 4000078399 | PIG32.0000.00021 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3360.3 | 2023-09-15 | 2023-09-15 | 2025-07-30 | 2023-09-15 | C_U139391
2629 |  | PSI-Danimer Phase 3 ROW-Winchester | 4000078402 | PSI32.0000.00006 | TECO MANC NMAT PRC SETC | NEW CAN NSFS REV | PSI | 0 | 0 | 2021-12-28 | 2021-12-31 |  | 2021-12-31 | C_U139391
2621 |  | CNV-23026286800 INSTALL 100' OF 2\"PMIP | 4000078441 | GRT32.0000.00045 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 12460.73 | 2023-11-16 | 2023-11-17 | 2025-07-31 | 2023-11-17 | C_U139391
2621 |  | CNV-23026287600 INSTALL 30'-4\" PMMP | 4000078443 | BET32.0000.00038 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 7282.62 | 2023-12-27 | 2023-12-31 | 2025-07-31 | 2024-12-25 | C_U139391
2621 |  | CNV-23026288000 EMER - INSTALL 5'-2\" PM | 4000078445 | ANC32.0000.00240 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 216.09 | 2023-08-10 | 2023-08-10 | 2025-07-30 | 2023-12-31 | C_U139391
2621 |  | CNV-23026288100 EMER - RETIRE 5'-2\" PMM | 4000078447 | ANC32.0000.00240 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1.31 | 2023-08-10 | 2023-08-10 |  | 2023-12-31 | C_U139391
2621 |  | CNV-23026290800 INSERT/INSTALL 160'-3\"P | 4000078450 | ANC32.0000.00245 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 17580.75 | 2023-10-16 | 2023-10-20 | 2025-07-30 | 2023-12-15 | C_U139391
2621 |  | CNV-23026290900 RETIRE 60' OF 3\"BSLP MA | 4000078452 | ANC32.0000.00245 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6100.78 | 2023-10-20 | 2023-10-20 | 2025-07-30 | 2023-12-15 | C_U139391
2629 |  | ANC-SMRP Sunset Dr-Paris | 4000078454 | ANC32.0000.00004 | REL PCNF MANC NMAT PRC SETC | SCHD | MAI | 46.68 | 2227.51 | 2025-07-16 | 2025-12-31 | 2025-09-02 | 2025-12-31 | C_U139391
2629 |  | ANC-SMRP Sunset Dr ABN-Paris | 4000078456 | ANC32.0000.00004 | REL PCNF NMAT PRC SETC | NEW | MAI | 0 | 572.15 | 2025-12-31 | 2025-12-31 | 2025-07-31 | 2025-12-31 | C_U139391
2629 |  | ANC-SMRP Camelot Dr MP-Winchester | 4000078458 | ANC32.0000.00005 | REL PCNF GMPS MANC PRC SETC | COCO ADJ FCMP | MAI | 1791702.55 | 569724.87 | 2025-08-20 | 2025-12-31 | 2025-08-03 | 2025-12-31 | C_U139391
2629 |  | ANC-SMRP Camelot Dr ABN-Winchester | 4000078481 | ANC32.0000.00005 | REL PCNF MANC PRC SETC | NEW ADJ | MAI | 175952.55 | 608.48 | 2025-08-20 | 2025-12-31 | 2025-08-05 | 2025-12-31 | C_U139391
2621 |  | CNV-23026300800 EMER-INSTALL 5' OF 3\"PM | 4000078483 | ANC32.0000.00025 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3055.81 | 2023-10-10 | 2023-10-10 | 2025-07-31 | 2023-10-10 | C_U139391
2621 |  | CNV-23026301000 EMER-INSTALL 2' OF 4\"PM | 4000078485 | ANC32.0000.00026 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1923.97 | 2023-12-01 | 2023-12-01 |  | 2023-12-01 | C_U139391
2621 |  | CNV-23026303700 EMER - INSTALL 5' OF 2\" | 4000078487 | ANC32.0000.00204 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 206.72 | 2023-11-03 | 2023-11-03 | 2025-07-31 | 2024-06-30 | C_U139391
2621 |  | CNV-23026303800 EMER - RETIRE 3' OF 2\" | 4000078489 | ANC32.0000.00204 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 114.38 | 2023-11-03 | 2023-11-03 | 2025-07-31 | 2024-06-30 | C_U139391
2621 |  | CNV-23026303900 EMER-INSTALL 3'-2\" PMMP | 4000078490 | ANC32.0000.00027 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1192.62 | 2024-06-28 | 2024-06-30 |  | 2024-06-30 | C_U139391
2621 |  | CNV-23026305300 EMER-INSTALL 11'-2\" PMM | 4000078492 | ANC32.0000.00205 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4025.96 | 2023-11-10 | 2023-11-10 | 2025-07-31 | 2023-11-13 | C_U139391
2621 |  | CNV-23026305400 EMER-RETIRE 11'-2\" PMMP | 4000078494 | ANC32.0000.00205 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 383.65 | 2023-11-13 | 2023-11-13 | 2025-07-31 | 2023-11-13 | C_U139391
2621 |  | CNV-23026307900 EMER-INSTALL 10'-4\"PMMP | 4000078497 | ANC32.0000.00206 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 5370.7 | 2024-08-29 | 2024-08-31 | 2025-07-31 | 2024-08-31 | C_U139391
2621 |  | CNV-23026308000 EMER-RETIRE 10'-4\"PMP/C | 4000078499 | ANC32.0000.00206 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 147.12 | 2024-08-30 | 2024-08-31 | 2025-07-31 | 2024-08-31 | C_U139391
2621 |  | CNV-23026308900 EMER INSTALL 4' OF 3\" P | 4000078521 | ANC32.0000.00207 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2047.52 | 2024-04-29 | 2024-04-30 | 2025-07-31 | 2024-04-30 | C_U139391
2621 |  | CNV-23026309000 EMER RETIRE 4' OF 3\" PM | 4000078523 | ANC32.0000.00207 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 176.13 | 2024-04-30 | 2024-04-30 | 2025-07-31 | 2024-04-30 | C_U139391
2621 |  | CNV-23026309100 EMER-INSTALL 4'OF 2\"PMM | 4000078525 | ANC32.0000.00208 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1804 | 2023-12-19 | 2023-12-19 | 2025-07-31 | 2023-12-19 | C_U139391
2621 |  | CNV-23026309200 EMER-RETIRE 4' OF 3\"PMP | 4000078527 | ANC32.0000.00208 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 269.86 | 2023-12-19 | 2023-12-19 | 2025-07-31 | 2023-12-19 | C_U139391
2621 |  | CNV-23026309300 EMER - INSTALL 5'-4\" PM | 4000078528 | ANC32.0000.00209 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 761.85 | 2024-10-30 | 2024-10-31 | 2025-07-31 | 2025-06-24 | C_U139391
2621 |  | CNV-23026309400 EMER - RETIRE 5'-4\" PMP | 4000078530 | ANC32.0000.00209 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 198.08 | 2024-10-31 | 2024-10-31 | 2025-07-31 | 2025-06-24 | C_U139391
2621 |  | CNV-22026240800 INVESTIGATE MAINS | 4000079035 | PSI32.0000.00012 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 7908.12 | 2023-06-29 | 2023-06-30 |  | 2023-06-30 | C_U139391
2621 | LEXINGTON | CNV-22026243500 RETIRE RECORDING GAUGE | 4000079037 | SUP32.0002.00001 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-12-01 | 2023-12-01 |  | 2023-12-01 | C_U139391
2621 |  | CNV-22026227500 PS&I BRANNON RD RELO | 4000079111 | PSI32.0000.00010 | TECO JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL REV | PSI | 0 | 8676.77 | 2023-12-28 | 2023-12-31 |  | 2023-12-31 | C_U139391
2621 |  | CNV-22026181300 RETIRE PIT REG STATION 1 | 4000079113 | ANC32.0000.00178 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 3197.48 | 2024-10-01 | 2024-10-01 | 2025-07-31 | 2024-10-01 | C_U139391
2629 |  | PSI-Winchester Plaza ROW-Winchester | 4000079115 | ANC32.0000.00185 | REL MANC NMAT PRC SETC | NEW NSFS | PSI | 0 | 0 | 2026-12-30 | 2028-12-31 |  | 2028-12-31 | C_U139391
2621 | LEXINGTON | CNV-22026212500 REPLACE VALVES AT R-1084 | 4000079119 | ANC32.0000.00115 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 5700.95 | 2023-09-27 | 2023-09-30 | 2025-07-30 | 2023-09-30 | C_U139391
2633 | HAROLD | CNV-22026218600 INSTALL NEW 1ST CUT REGU | 4000079145 | ANC32.0000.00291 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 2733.71 | 2023-12-01 | 2023-12-01 | 2025-07-31 | 2023-12-01 | C_U139391
2633 | HAROLD | CNV-22026218700 RETIRE 1ST CUT REGULATOR | 4000079147 | ANC32.0000.00291 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 1618.6 | 2023-12-01 | 2023-12-01 | 2025-07-31 | 2023-12-01 | C_U139391
2621 |  | CNV-23026246401 INSTALL 3100' OF 2\"PMMP | 4000079233 | BET32.0000.00001 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 665.82 | 2023-03-08 | 2023-06-01 |  | 2023-06-01 | C_U139391
2621 |  | CNV-23026248900 INSTALL 100' OF 2\"PMMP | 4000079235 | BET32.0000.00006 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-08-28 | 2023-09-01 |  | 2023-09-01 | C_U139391
2621 |  | CNV-23026251800 RETIRE 900' OF 2\"CSHP M | 4000079237 | GRT32.0000.00069 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 5320.14 | 2023-12-01 | 2023-12-01 | 2025-07-30 | 2023-12-01 | C_U139391
2621 |  | CNV-23026254400 INSTALL 420' OF 6\"PMMP | 4000079238 | PIG32.0000.00004 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-09-01 | 2023-09-01 |  | 2023-09-30 | C_U139391
2621 |  | CNV-23026254900 INSTALL 620' OF 8\"CSHP | 4000079260 | PIG32.0000.00038 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 121750.93 | 2024-07-23 | 2024-10-01 | 2025-07-31 | 2024-10-01 | C_U139391
2621 |  | CNV-23026255000 RETIRE 620' OF 8\"CSHP M | 4000079262 | PIG32.0000.00038 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 349.8 | 2024-10-01 | 2024-10-01 |  | 2024-10-01 | C_U139391
2621 |  | CNV-23026263000 INSTALL 5875' OF 2\"/4\" | 4000079264 | ANC32.0000.00035 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 223134.97 | 2023-06-02 | 2023-11-01 | 2025-07-30 | 2023-11-01 | C_U139391
2621 |  | CNV-23026263400 INSTALL 40'-4\" PMMP | 4000079266 | ANC32.0000.00217 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-10-25 | 2023-10-31 |  | 2023-10-31 | C_U139391
2621 |  | CNV-23026263500 RETIRE 20'-4\" PMMP | 4000079268 | ANC32.0000.00217 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-02-24 | 2049-12-31 |  | 2049-12-31 | C_U139391
2621 |  | CNV-23026265100 INSTALL 10'-3\"PMLP | 4000079270 | ANC32.0000.00221 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 140835.81 | 2023-11-22 | 2023-11-30 |  | 2023-11-30 | C_U139391
2621 |  | CNV-23026265200 RETIRE 10'-3\" BSLP | 4000079272 | ANC32.0000.00221 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-06-02 | 2023-06-02 |  | 2023-11-30 | C_U139391
2621 |  | CNV-23026267200 INSTALL 60'-4\" PMLP | 4000079274 | ANC32.0000.00222 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 16588.53 | 2024-02-12 | 2024-02-12 | 2025-07-31 | 2024-06-30 | C_U139391
2621 |  | CNV-23026267300 RETIRE ~60'-4\" BSLP | 4000079276 | ANC32.0000.00222 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 136.25 | 2023-11-30 | 2023-11-30 | 2025-07-31 | 2024-06-30 | C_U139391
2621 |  | CNV-23026267800 INSTALL 580' OF 2\"PMMP | 4000079278 | GRT32.0000.00037 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 859.74 | 2023-06-08 | 2023-06-19 |  | 2023-06-19 | C_U139391
2629 |  | CNV-24026316000 EMER - INSTALL 2'-3\" PM | 4000079294 | ANC32.0000.00055 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6325.04 | 2024-01-16 | 2024-01-16 |  | 2024-01-29 | C_U139391
2623 |  | CNV-24026316600 EMER - ABANDON ~15'-2\" | 4000079296 | ANC32.0000.00110 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6716.07 | 2024-09-30 | 2024-09-30 |  | 2025-05-18 | C_U139391
2623 |  | CNV-24026317300 INSTALL 270'-2\" PMMP | 4000079298 | GRT32.0000.00050 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 18665.67 | 2024-04-26 | 2024-04-30 | 2025-07-31 | 2024-04-30 | C_U139391
2621 |  | CNV-23026268400 INSTALL 2000' OF 2\"PMMP | 4000079300 | GRT32.0000.00088 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-05-04 | 2023-05-31 |  | 2023-05-31 | C_U139391
2621 |  | CNV-23026270600 INSTALL 550' OF 2\" PMMP | 4000079301 | GRT32.0000.00038 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 24207.76 | 2024-10-02 | 2024-10-11 | 2025-08-01 | 2024-10-11 | C_U139391
2621 |  | CNV-23026272200 INSTALL 200' OF 2\"PMMP | 4000079303 | GRT32.0000.00039 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 319.22 | 2023-06-06 | 2023-06-15 |  | 2023-06-27 | C_U139391
2621 |  | CNV-23026272600 INSTALL 875' OF 2\"PMMP | 4000079305 | GRT32.0000.00089 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-08-14 | 2023-08-18 |  | 2023-08-18 | C_U139391
2621 |  | CNV-23026272700 EMER - INSTALL 5'-2\" PM | 4000079307 | ANC32.0000.00042 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-04-25 | 2023-04-25 |  | 2023-04-25 | C_U139391
2621 |  | CNV-23026272901 INSTALL 2500' OF 2\"PMMP | 4000079309 | GRT32.0000.00090 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 98246.22 | 2024-02-01 | 2024-03-22 | 2025-07-31 | 2024-03-22 | C_U139391
2621 |  | CNV-23026273300 INSTALL 290' OF 4\" PMMP | 4000079311 | ANC32.0000.00043 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2614.92 | 2023-12-14 | 2023-12-31 |  | 2023-12-31 | C_U139391
2621 |  | CNV-23026274301 INSTALL 3400' OF 2\"PMMP | 4000079313 | GRT32.0000.00091 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 14303.12 | 2023-07-26 | 2023-08-11 | 2025-07-30 | 2023-10-27 | C_U139391
2621 |  | CNV-23026277300 INSTALL 265' OF 6\"PMMP | 4000079315 | PIG32.0000.00040 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 11880.36 | 2023-08-22 | 2023-09-01 | 2025-07-30 | 2023-09-01 | C_U139391
2621 |  | CNV-23026277400 RETIRE 285' OF 6\"PMMP M | 4000079317 | PIG32.0000.00040 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 439.64 | 2023-09-01 | 2023-09-01 | 2025-07-30 | 2023-09-01 | C_U139391
2621 |  | CNV-23026278200 EMER-INSTALL 185' OF 4\" | 4000079319 | ANC32.0000.00044 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 205.8 | 2024-01-29 | 2024-01-31 |  | 2024-09-06 | C_U139391
2631 |  | ANC-SMRP Algonquin Ave-Ashland | 4000079320 | ANC32.0000.00056 | REL GMPS MANC PRC SETC | NPRG ADJ FCMP | MAI | 157818.06 | 1550175.42 | 2026-07-10 | 2026-12-31 |  | 2026-12-31 | C_U139391
2629 |  | PSI-SMRP Broadway Av P2 ROW-Cynthiana | 4000079321 | PSI32.0000.00018 | REL NMAT PRC SETC | NEW FCMP | PSI | 0 | 41920.4 | 2025-12-30 | 2025-12-31 |  | 2025-12-31 | C_U139391
2623 |  | ANC - GANO AVE SMRP | 4000079322 | ANC32.0000.00057 | REL PCNF GMPS MANC PRC SETC | NEW ADJ | MAI | 52698.27 | 1729753.98 | 2026-05-14 | 2026-12-31 | 2026-02-13 | 2026-12-31 | C_U139391
2623 |  | ANC - SMRP - TURNER ST | 4000079323 | ANC32.0000.00059 | REL PCNF GMPS MANC PRC SETC | NEW | MAI | 34754.19 | 2677857.55 | 2026-04-28 | 2026-12-30 | 2026-03-04 | 2026-12-30 | C_U139391
2631 |  | CNV-24026320800 EMER - INSTALL 5'-3\" PM | 4000079325 | ANC32.0000.00255 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 10006.55 | 2024-03-28 | 2024-03-30 | 2025-07-31 | 2024-03-30 | C_U139391
2631 |  | CNV-24026320900 EMER RETIRE 5'-3\" PIP | 4000079327 | ANC32.0000.00255 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 338.64 | 2024-03-28 | 2024-03-30 | 2025-07-31 | 2024-03-30 | C_U139391
2623 |  | CNV-24026340300 INSTALL 2280' OF 4\"CSHP | 4000079329 | GRT32.0000.00100 | TECO MANC NMAT PRC SETC | NEW CAN NSFS | MAI | 0 | 108.36 | 2026-11-09 | 2026-12-31 |  | 2026-12-31 | C_U139391
2623 |  | CNV-24026340800 EMER - INSTALL 15'-2\" P | 4000079331 | ANC32.0000.00069 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 523.95 | 2024-04-29 | 2024-05-01 | 2025-08-01 | 2025-03-01 | C_U139391
2631 |  | CNV-24026341000 INSTALL 300'OF 2\" PMIP | 4000079333 | BET32.0000.00042 | REL PCNF MANC PRC SETC | NEW ADJ FCMP MIFE NSFS WENG | MAI | 1109.39 | 23226.43 | 2025-04-24 | 2025-04-30 | 2025-08-02 | 2025-04-30 | C_U139391
2629 |  | CNV-24026342300 EMER - RETIRE 267'-2\" P | 4000079335 | ANC32.0000.00111 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2666.67 | 2024-05-07 | 2024-05-09 |  | 2024-05-17 | C_U139391
2633 |  | CNV-24026342600 EMER ABANDON 200' OF 2\" | 4000079337 | ANC32.0000.00112 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 5142.92 | 2024-05-17 | 2024-05-20 |  | 2024-07-17 | C_U139391
2629 |  | CNV-24026343700 EMER - INSTALL 3'-3\" PM | 4000079339 | ANC32.0000.00070 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4126.3 | 2024-05-10 | 2024-05-17 |  | 2024-05-17 | C_U139391
2621 |  | CNV-23026278401 INSTALL 2300' OF 2\"/4\" | 4000079341 | GRT32.0000.00092 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 13917.31 | 2023-09-27 | 2023-10-31 | 2025-07-31 | 2023-12-01 | C_U139391
2621 |  | CNV-23026279100 INSTALL 300' OF 2\"PMIP | 4000079343 | GRT32.0000.00093 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 5117.78 | 2023-08-09 | 2023-08-11 | 2025-07-30 | 2023-08-11 | C_U139391
2621 |  | CNV-23026283200 INSTALL 480' OF 2\"PMMP | 4000079345 | PIG32.0000.00008 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 31110.85 | 2023-08-21 | 2023-09-01 | 2025-07-30 | 2023-09-01 | C_U139391
2621 |  | CNV-23026285400 RETIRE 300' OF 2\"PIP MA | 4000079347 | BET32.0000.00020 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 15489.39 | 2024-02-28 | 2024-03-01 | 2025-07-31 | 2024-03-01 | C_U139391
2621 |  | CNV-23026288401 INSTALL 5500' OF 4\"PMMP | 4000079349 | GRT32.0000.00046 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 32023.98 | 2024-02-12 | 2024-08-16 | 2025-08-01 | 2024-08-16 | C_U139391
2621 |  | LEX SUNSET DR 2025 SMRP CNV-23026290300 | 4000079351 | ANC32.0000.00049 | REL GMPS MANC PRC SETC | NPRG ADJ WGMA | MAI | 157274.21 | 1825203.45 | 2025-09-02 | 2025-12-31 |  | 2026-04-01 | C_U139391
2621 |  | BLUE RIDGE 2025 SMRP CNV-23026290600 | 4000079353 | ANC32.0000.00050 | REL GMPS MANC PRC SETC | NPRG ADJ FCMP RSHD | MAI | 163265.34 | 1060907.48 | 2025-07-07 | 2025-12-23 |  | 2025-12-23 | C_U139391
2621 |  | CNV-23026292000 INSTALL 2450' OF 2\"PMMP | 4000079355 | GRT32.0000.00047 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 43855.25 | 2024-02-12 | 2024-03-01 | 2025-07-31 | 2024-03-01 | C_U139391
2621 |  | CNV-23026292501 INSTALL 800' OF 2-4\" PM | 4000079357 | PIG32.0000.00027 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 8382.25 | 2023-10-18 | 2023-10-31 |  | 2024-11-30 | C_U139391
2621 |  | CNV-23026293700 INSTALL 74'-2\" PMMP | 4000079359 | PIG32.0000.00037 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 17676.74 | 2024-06-05 | 2024-06-30 | 2025-07-31 | 2024-06-30 | C_U139391
2621 |  | CNV-23026293800 RETIRE 88'-2\"&4\" PMMP | 4000079361 | PIG32.0000.00037 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 9244 | 2024-06-28 | 2024-06-30 | 2025-07-31 | 2024-06-30 | C_U139391
2621 |  | CNV-23026294800 INSTALL 225' OF 2\"PMMP | 4000079363 | GRT32.0000.00014 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 17369.41 | 2023-12-14 | 2023-12-18 | 2025-07-31 | 2023-12-18 | C_U139391
2621 |  | CNV-23026296000 INSTALL 220' OF 2\" PMMP | 4000079365 | GRT32.0000.00015 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 29995.76 | 2024-01-26 | 2024-02-01 | 2025-07-31 | 2024-02-01 | C_U139391
2621 |  | CNV-23026296200 INSTALL 1429'-6\" PMMP | 4000079367 | PIG32.0000.00026 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 566587.69 | 2024-01-15 | 2024-03-21 | 2025-07-31 | 2024-06-28 | C_U139391
2621 |  | CNV-23026296300 RETIRE 1479'-6\" CS&PMMP | 4000079369 | PIG32.0000.00026 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 577.39 | 2024-03-21 | 2024-03-21 | 2025-07-31 | 2024-04-26 | C_U139391
2621 |  | CNV-23026296800 EMER - INSTALL 40'-4\" P | 4000079371 | PIG32.0000.00005 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 20616.63 | 2023-12-21 | 2023-12-30 | 2025-08-12 | 2023-12-30 | C_U139391
2621 |  | CNV-23026297200 EMER - INSTALL 13'-2\" P | 4000079373 | ANC32.0000.00201 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 211.73 | 2023-10-06 | 2023-10-09 | 2025-07-31 | 2023-10-12 | C_U139391
2621 |  | CNV-23026297300 EMER - RETIRE 2'-2\" PMP | 4000079375 | ANC32.0000.00201 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 5935.69 | 2023-10-09 | 2023-10-09 | 2025-07-31 | 2023-10-12 | C_U139391
2621 |  | CNV-23026299700 INSTALL 325' OF 2\"PMMP | 4000079377 | GRT32.0000.00018 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 26876.53 | 2024-04-22 | 2024-04-26 | 2025-07-31 | 2024-04-26 | C_U139391
2621 |  | CNV-23026302701 INSTALL 2700' OF 2\"/4\" | 4000079379 | GRT32.0000.00086 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 29483.1 | 2024-05-13 | 2024-07-01 | 2025-07-31 | 2024-07-01 | C_U139391
2631 |  | CNV-24026344300 EMER-INSTALL 6' OF 4\" P | 4000079381 | ANC32.0000.00071 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 12417.86 | 2025-07-31 | 2025-07-31 |  | 2026-03-13 | C_U139391
2633 |  | CNV-24026345800 INSTALL 1400'-2\\\ PMI. | 4000079383 | PIG32.0000.00001 | REL PCNF MANC NMAT NTUP PRC SETC | NEW | MAI | 0 | 107970.38 | 2025-03-26 | 2025-04-15 | 2025-08-01 | 2025-04-15 | C_U139391
2633 |  | CNV-24026347600 EMER - INSTALL 7'-2\" PM | 4000079385 | ANC32.0000.00072 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4739.55 | 2024-06-10 | 2024-06-10 |  | 2024-06-10 | C_U139391
2631 |  | BET-ROBERTS DRIVE CASING-ASHLAND | 4000079387 | BET32.0000.00045 | REL PCNF MANC NMAT PRC SETC | NEW WENV WPMT | MAI | 365.12 | 204.22 | 2026-07-09 | 2026-07-18 | 2026-04-30 | 2026-07-18 | C_U139391
2631 |  | CNV-24026348600 RETIRE 360' OF 3\" CSIP | 4000079388 | BET32.0000.00045 | REL NMAT PRC SETC | NEW NSFS | MAI | 0 | 1779.35 | 2025-11-30 | 2025-11-30 |  | 2026-07-18 | C_U139391
2631 |  | CNV-24026348900 INSTALL 70'-8\" PMMP | 4000079390 | PIG32.0000.00047 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 59062.03 | 2024-10-10 | 2024-10-30 | 2025-08-01 | 2024-10-30 | C_U139391
2631 |  | CNV-24026349000 RETIRE 70' OF 10\"CSMP M | 4000079392 | PIG32.0000.00047 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 116.6 | 2024-10-30 | 2024-10-30 |  | 2024-10-30 | C_U139391
2631 |  | CNV-24026349500 INSTALL 40'-12\\\ CSMP. | 4000079394 | ANC32.0000.00273 | REL MANC NMAT PRC SETC | NEW REV | MAI | 0 | 83922.03 | 2024-08-31 | 2024-08-31 |  | 2025-04-20 | C_U139391
2631 |  | CNV-24026349600 RETIRE ~40'-12\" CSHP | 4000079396 | ANC32.0000.00273 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 233.2 | 2024-08-31 | 2024-08-31 |  | 2025-04-20 | C_U139391
2629 |  | CNV-24026349900 EMER - INSTALL 3'-2\" PM | 4000079398 | ANC32.0000.00074 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 6187.75 | 2024-12-23 | 2024-12-31 |  | 2024-12-31 | C_U139391
2621 |  | CNV-24026313700 INVESTIGATE HP EASEMENT/ | 4000079399 | PSI32.0000.00004 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 9480.15 | 2024-12-31 | 2024-12-31 |  | 2024-12-31 | C_U139391
2621 |  | CNV-23026304900 INSTALL 4450' OF 2-4\" P | 4000079401 | PIG32.0000.00043 | REL PCNF GMPS MANC PRC SETC | NPRG ADJ | MAI | 6357.31 | 1345562.37 | 2025-07-15 | 2025-10-03 | 2025-08-03 | 2025-10-03 | C_U139391
2632 |  | CNV-24026351600 EMER - INSTALL 2'-2\" PM | 4000079420 | ANC32.0000.00075 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 1335.05 | 2025-03-28 | 2025-03-31 |  | 2025-03-31 | C_U139391
2621 |  | CNV-24026313800 INVESTIGATE LAND RIGHTS | 4000079421 | ANC32.0000.00081 | TECO JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL | PSI | 0 | 54333.24 | 2025-12-30 | 2025-12-31 |  | 2025-12-31 | C_U139391
2629 |  | CNV-24026352000 INSTALL 700'-2\\\ PMMP. | 4000079422 | GRT32.0000.00055 | REL PCNF MANC NMAT NTUP PRC SETC | NEW | MAI | 0 | 30619.26 | 2025-01-24 | 2025-01-30 | 2025-08-01 | 2025-01-30 | C_U139391
2629 |  | ANC-SMRP Rogers Av-Mt Sterling | 4000079424 | ANC32.0000.00277 | REL NMAT PRC SETC | NEW NSFS REV | MAI | 0 | 478.34 | 2024-12-30 | 2024-12-31 |  | 2025-08-21 | C_U139391
2632 |  | CNV-24026352800 INSTALL SS FITTING | 4000079426 | ANC32.0000.00279 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1303.48 | 2024-08-01 | 2024-08-02 | 2025-08-01 | 2024-08-05 | C_U139391
2632 |  | CNV-24026352900 RETIRE 4'-3\"&4\"CSMP | 4000079428 | ANC32.0000.00279 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1085.55 | 2024-08-02 | 2024-08-02 | 2025-08-01 | 2024-08-05 | C_U139391
2631 |  | CNV-24026335700 INVESTIGATE EASEMENTS FO | 4000079435 | PSI32.0000.00021 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 7231.22 | 2024-12-31 | 2024-12-31 |  | 2024-12-31 | C_U139391
2623 |  | CNV-24026362000 EMER-INSTALL 3' OF 3\"PM | 4000079439 | ANC32.0000.00286 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 6505.22 | 2025-10-31 | 2025-10-31 |  | 2026-06-27 | C_U139391
2623 |  | CNV-24026362100 EMER-RETIRE 2' OF 3\"PMP | 4000079461 | ANC32.0000.00286 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 3316 | 2025-10-31 | 2025-10-31 |  | 2026-06-27 | C_U139391
2633 |  | CNV-24026364700 INSTALL 518'-4\" PMIP | 4000079463 | ANC32.0000.00083 | REL GMPS MANC PRC SETC | COCO ADJ FCMP | MAI | 35276.7 | 30580.52 | 2025-07-30 | 2025-08-08 |  | 2025-08-08 | C_U139391
2629 |  | CNV-24026364900 INSTALL 2,300'-4\" PMMP | 4000079465 | GRT32.0000.00096 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 93727.11 | 2025-01-08 | 2025-01-31 | 2025-08-01 | 2025-01-31 | C_U139391
2629 |  | GRT-Bourbon Oaks Phase 1 MLE-Paris | 4000079467 | GRT32.0000.00096 | REL PCNF MANC PRC SETC | SCHD ADJ FCMP | MAI | 9884.28 | 46175.8 | 2025-06-20 | 2025-06-30 | 2025-08-05 | 2025-06-30 | C_U139391
2631 |  | CNV-24026365300 EMER INSTALL 5\" OF 4\" | 4000079469 | ANC32.0000.00288 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 15339.42 | 2025-06-25 | 2025-06-30 | 2025-08-01 | 2025-06-30 | C_U139391
2631 |  | CNV-24026365400 EMER RETIRE 5\" OF 4\" P | 4000079471 | ANC32.0000.00288 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 410.02 | 2025-06-30 | 2025-06-30 | 2025-08-01 | 2025-06-30 | C_U139391
2632 |  | CNV-24026366400 INSTALL ~390'-2\" PMIP | 4000079473 | GRT32.0000.00106 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 17758.81 | 2025-02-06 | 2025-02-14 | 2025-08-01 | 2025-02-14 | C_U139391
2631 |  | CNV-24026367000 EMER INSTALL 5'-2\" PMMP | 4000079475 | ANC32.0000.00290 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 5780.2 | 2024-10-09 | 2024-10-09 | 2025-08-01 | 2024-10-10 | C_U139391
2631 |  | CNV-24026367100 EMER RETIRE 5'-2\" PMMP | 4000079478 | ANC32.0000.00290 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 451.33 | 2024-10-10 | 2024-10-10 | 2025-08-01 | 2024-10-10 | C_U139391
2631 |  | CNV-24026367500 INSTALL 1600'-2\" PMMP | 4000079479 | PIG32.0000.00049 | REL PCNF GMPS MANC PRC SETC | NEW ADJ FCMP NSFS WENG | MAI | 179.48 | 305253.06 | 2025-05-13 | 2025-07-01 | 2025-08-03 | 2025-07-01 | C_U139391
2623 |  | CNV-24026367900 INSTALL 1060' OF 2\"PMMP | 4000079502 | ANC32.0000.00144 | REL MANC PRC SETC | NPRG ADJ FCMP | MAI | 101110.57 | 3411.34 | 2025-08-06 | 2025-08-08 |  | 2025-08-08 | C_U139391
2629 |  | CNV-24026368000 EMER - INSTALL 5'-2\" PM | 4000079504 | ANC32.0000.00302 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3448.45 | 2024-11-01 | 2024-11-01 |  | 2024-11-01 | C_U139391
2629 |  | CNV-24026368100 EMER - RETIRE 5'-2\" PMM | 4000079506 | ANC32.0000.00302 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 204.97 | 2024-11-01 | 2024-11-01 | 2025-08-01 | 2024-11-01 | C_U139391
2629 |  | CNV-24026371800 EMER - INSTALL 3'-2\" PM | 4000079507 | ANC32.0000.00089 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 15303.77 | 2024-12-12 | 2024-12-31 |  | 2024-12-31 | C_U139391
2623 |  | CNV-24026372000 INSTALLING 500'-2\" PMMP | 4000079510 | GRT32.0000.00066 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 21681.94 | 2025-02-28 | 2025-03-14 | 2025-08-01 | 2025-03-14 | C_U139391
2629 |  | CNV-24026373800 EMER - INSTALL 3'-2\" PM | 4000079512 | ANC32.0000.00090 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2998.84 | 2024-12-27 | 2024-12-31 |  | 2024-12-31 | C_U139391
2629 |  | GRT-Adena Dr MLE-Mt Sterling | 4000079514 | ANC32.0000.00146 | REL GMPS MANC PRC SETC | NPRG ADJ FCMP | MAI | 71358.4 | 80873.14 | 2025-07-28 | 2025-08-09 |  | 2025-08-09 | C_U139391
2629 |  | CNV-24026376300 EMER - INSTALL 5'-2\" PM | 4000079516 | ANC32.0000.00092 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3004.9 | 2024-12-23 | 2024-12-31 |  | 2024-12-31 | C_U139391
2621 |  | RELOCATION - ARMSTRONG MILL RD | 4000079630 | PSI32.0000.00035 | TECO JBFI MANC NMAT NTUP PRC SETC | NEW CAN FCMP RECL | PSI | 0 | 10616.54 | 2025-12-30 | 2025-12-31 |  | 2025-12-31 | C_U139391
2621 |  | CNV-25026397600 INVESTIGATE CONFLICTS | 4000079632 | PSI32.0000.00041 | TECO JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL | PSI | 0 | 7735.95 | 2025-12-30 | 2025-12-31 |  | 2025-12-31 | C_U139391
2623 |  | CNV-24026309500 INSTALL 215'-2\" PMMP | 4000079638 | GRT32.0000.00026 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 10703.61 | 2024-05-22 | 2024-05-27 | 2025-07-31 | 2024-05-27 | C_U139391
2629 |  | CNV-24026309800 INSTALL 75' - 2\" PMMP | 4000079660 | GRT32.0000.00025 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 7578.53 | 2024-02-13 | 2024-02-15 | 2025-08-12 | 2024-02-15 | C_U139391
2623 |  | CNV-24026310000 EMER-INSTALL 4' OF 2\"PM | 4000079662 | ANC32.0000.00051 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4013.16 | 2024-11-26 | 2024-11-30 |  | 2025-07-28 | C_U139391
2629 |  | CNV-24026310800 INSTALL 1400' OF 2\" PMM | 4000079664 | GRT32.0000.00027 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 46770.14 | 2024-08-29 | 2024-09-10 | 2025-08-01 | 2024-09-10 | C_U139391
2623 |  | CNV-24026311500 EMER-RETIRE 350' OF 4\"P | 4000079666 | ANC32.0000.00109 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1508.07 | 2024-01-10 | 2024-01-10 |  | 2024-01-10 | C_U139391
2623 |  | CNV-24026312200 INSTALL 230'-2\" PMMP | 4000079669 | GRT32.0000.00048 | REL PCNF GMPS NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 20413.05 | 2024-06-12 | 2024-06-14 | 2025-07-31 | 2024-06-14 | C_U139391
2623 |  | CNV-24026313000 INSTALL 1570'-2\\\ PMM. | 4000079671 | ANC32.0000.00052 | REL PCNF MANC NMAT NTUP PRC SETC | NEW | MAI | 0 | 170437.9 | 2025-08-19 | 2025-09-30 | 2025-08-01 | 2025-09-30 | C_U139391
2629 |  | CNV-24026313400 REPLACE EXISTING RECTIFI | 4000079673 | ANC32.0000.00139 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3648.09 | 2024-02-28 | 2024-02-28 | 2025-07-31 | 2024-02-28 | C_U139391
2629 |  | CNV-24026314400 INSTALL 1,200'-4\\\ PM. | 4000079675 | GRT32.0000.00098 | REL PCNF GMPS MANC NMAT NTUP PRC SETC | NEW | MAI | 0 | 200725.69 | 2025-03-31 | 2025-04-11 | 2025-08-02 | 2025-04-11 | C_U139391
2629 |  | CNV-24026353200 EMER - INSTALL 3'-4\" PM | 4000079758 | ANC32.0000.00076 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 2039.58 | 2025-03-25 | 2025-03-31 |  | 2025-03-31 | C_U139391
2629 |  | CNV-24026354100 EMER - RETIRE 308'-2\" P | 4000079760 | BET32.0000.00017 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1102.7 | 2024-07-17 | 2024-07-18 |  | 2024-07-18 | C_U139391
2623 |  | CNV-24026355200 INSTALL 150'-4\" PMLP | 4000079762 | GRT32.0000.00059 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 20757.3 | 2024-12-16 | 2024-12-31 | 2025-08-01 | 2024-12-31 | C_U139391
2623 |  | CNV-24026355300 INSTALL 250'-2\" PMMP | 4000079764 | GRT32.0000.00060 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 11652.49 | 2024-09-23 | 2024-09-30 |  | 2024-09-30 | C_U139391
2631 |  | CNV-24026324100 INSTALL 670'-2' PMIP | 4000079766 | GRT32.0000.00051 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 16053.74 | 2024-08-15 | 2024-10-10 | 2025-08-01 | 2024-10-10 | C_U139391
2629 |  | CNV-24026329400 EMER - INSTALL 2'-3\" PM | 4000079768 | ANC32.0000.00060 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4119.43 | 2024-12-18 | 2024-12-31 |  | 2024-12-31 | C_U139391
2629 |  | CNV-24026329700 EMER - 2'-2\" PMMP | 4000079771 | ANC32.0000.00061 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4824.51 | 2024-12-17 | 2024-12-31 |  | 2024-12-31 | C_U139391
2623 |  | CNV-24026331100 EMER - INSTALL ~5'-2\" P | 4000079773 | ANC32.0000.00062 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 847.97 | 2024-12-27 | 2024-12-27 |  | 2024-12-29 | C_U139391
2623 |  | CNV-24026331601 INSTALL 475' OF 2\"PMMP | 4000079775 | ANC32.0000.00260 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 568.23 | 2025-04-15 | 2025-04-30 |  | 2025-12-05 | C_U139391
2623 |  | CNV-24026331700 REITRE 435' OF 2\"BSLP M | 4000079777 | ANC32.0000.00260 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 396.72 | 2025-04-30 | 2025-04-30 | 2025-07-31 | 2025-12-05 | C_U139391
2629 |  | CNV-24026332600 EMER INSTALL 10'-6\" PMM | 4000079779 | ANC32.0000.00063 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 20910.63 | 2025-03-20 | 2025-03-31 |  | 2025-11-20 | C_U139391
2623 |  | CNV-24026332800 EMER - INSTALL 5'-4\" PM | 4000079801 | ANC32.0000.00263 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 4699.68 | 2025-02-28 | 2025-02-28 | 2025-07-31 | 2025-10-10 | C_U139391
2623 |  | CNV-24026332900 EMER - ABANDON 5'-4\" PM | 4000079803 | ANC32.0000.00263 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 0 | 2025-02-27 | 2025-02-28 |  | 2025-10-10 | C_U139391
2631 |  | CNV-24026333201 EMER - INSTALL 478'-4\\. | 4000079805 | ANC32.0000.00264 | REL PCNF MANC NMAT NTUP PRC SETC | NEW | MAI | 0 | 81563.52 | 2025-02-17 | 2025-02-28 | 2025-08-01 | 2025-02-28 | C_U139391
2631 |  | CNV-24026333301 EMER - RETIRE 477'-4\" C | 4000079807 | ANC32.0000.00264 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 0 | 2025-02-28 | 2025-02-28 |  | 2025-02-28 | C_U139391
2633 |  | CNV-24026333600 INSTALL 75'-2\" PMIP | 4000079809 | GRT32.0000.00052 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 14353.53 | 2024-09-19 | 2024-09-20 | 2025-08-01 | 2024-09-20 | C_U139391
2629 |  | CNV-24026337600 INSTALL 30'-2\" PMMP | 4000079811 | PIG32.0000.00044 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 10081.09 | 2024-05-24 | 2024-05-31 | 2025-07-31 | 2024-05-31 | C_U139391
2629 |  | CNV-24026337700 RETIRE 20'-2\" PMMP | 4000079813 | PIG32.0000.00044 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 19.74 | 2024-05-31 | 2024-05-31 |  | 2024-05-31 | C_U139391
2631 |  | CNV-24026337800 INSTALL 8\" SS | 4000079815 | ANC32.0000.00001 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2024-04-30 | 2024-04-30 |  | 2024-04-30 | C_U139391
2629 |  | CNV-24026337900 INSTALL 2,550'-2\" PMMP | 4000079817 | GRT32.0000.00085 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 51672.95 | 2024-06-10 | 2024-06-30 | 2025-07-31 | 2024-06-30 | C_U139391
2623 |  | CNV-24026338200 EMER - INSTALL 5'-3\" PM | 4000079819 | ANC32.0000.00068 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 5210.66 | 2025-01-30 | 2025-01-31 |  | 2025-09-19 | C_U139391
2631 |  | CNV-24026356500 EMER - INSTALL 2'-2\" PM | 4000079841 | ANC32.0000.00284 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 3486.96 | 2024-08-29 | 2024-09-01 |  | 2024-09-01 | C_U139391
2631 |  | CNV-24026356600 EMER - RETIRE 2'-2\" PIP | 4000079843 | ANC32.0000.00284 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 49.72 | 2024-08-30 | 2024-09-01 | 2025-08-01 | 2024-09-01 | C_U139391
2623 |  | BALL HOMES ROSE RIDGE PH 2 NB | 4000079845 | GRT32.0000.00062 | REL PCNF GMPS MANC PRC SETC | SCHD ADJ FCMP | MAI | 23249.7 | 49509.72 | 2025-07-16 | 2025-08-01 | 2025-09-02 | 2025-08-01 | C_U139391
2632 |  | CNV-24026357400 INSTALL 275'-3\" CSMP | 4000079847 | PIG32.0000.00012 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 47284.21 | 2024-10-17 | 2024-10-30 | 2025-08-01 | 2024-10-30 | C_U139391
2623 |  | CNV-24026357700 EMER-INSTALL 2' OF 3\"PM | 4000079849 | ANC32.0000.00077 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 8659.42 | 2025-10-28 | 2025-10-31 | 2025-08-02 | 2026-06-27 | C_U139391
2629 |  | CNV-24026358600 INSTALL 175' - 4\\\ PM. | 4000079850 | PIG32.0000.00050 | REL PCNF MANC NMAT NTUP PRC SETC | NEW REV | MAI | 0 | 39248.49 | 2024-10-24 | 2024-12-31 | 2025-08-01 | 2024-12-31 | C_U139391
2631 |  | CNV-24026358700 INSTALL 100' OF 2\" PMMP | 4000079852 | GRT32.0000.00057 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 15229.56 | 2024-10-29 | 2024-10-31 | 2025-08-01 | 2024-10-31 | C_U139391
2631 |  | CNV-24026359401 INSTALL 200' OF 4\" PMIP | 4000079854 | GRT32.0000.00104 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 7249.07 | 2025-02-13 | 2025-02-19 | 2025-08-01 | 2025-02-19 | C_U139391
2629 |  | ANC-SMRP Basin Springs-Winchester | 4000079856 | ANC32.0000.00078 | REL PCNF GMPS MANC PRC SETC | SCHD ADJ | MAI | 942649.29 | 510290.27 | 2026-09-21 | 2026-12-01 | 2026-04-20 | 2026-12-31 | C_U139391
2623 |  | CNV-24026360200 EMER-INSTALL 3' OF 2\"PM | 4000079859 | ANC32.0000.00079 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2024-08-21 | 2024-08-21 |  | 2024-09-03 | C_U139391
2631 |  | CNV-24026361400 INSTALL 100' OF 2\\\ P. | 4000079861 | GRT32.0000.00105 | REL PCNF MANC NMAT NTUP PRC SETC | NEW | MAI | 0 | 14243.95 | 2025-02-12 | 2025-02-16 | 2025-08-05 | 2025-03-26 | C_U139391
2629 |  | CNV-24026361500 EMER - INSTALL 2'-3\" PM | 4000079862 | ANC32.0000.00080 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 1680.46 | 2024-09-27 | 2024-09-30 |  | 2024-09-30 | C_U139391
2621 | LEXINGTON | CNV-23026254000 RETIRE PRESSURE GAUGE | 4000079895 | ANC32.0000.00134 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-09-29 | 2023-10-01 |  | 2023-10-01 | C_U139391
2632 | MAYSVILLE | CNV-23026254100 RETIRE PRESSURE GAUGE | 4000079896 | ANC32.0000.00134 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-09-29 | 2023-10-01 |  | 2023-10-01 | C_U139391
2631 | GREENUP | CNV-23026254200 RETIRE RECORDING GAUGE | 4000079897 | ANC32.0000.00134 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-09-29 | 2023-10-01 |  | 2023-10-01 | C_U139391
2621 | LEXINGTON | CNV-23026254700 RETIRE PAPER GAUGE | 4000079898 | ANC32.0000.00134 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-12-01 | 2023-12-01 |  | 2023-12-01 | C_U139391
2621 | LEXINGTON | CNV-23026256201 INSTALL VRG CONTROLLERS | 4000079899 | GRT32.0000.00111 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 8134.45 | 2023-11-27 | 2023-12-01 |  | 2023-12-01 | C_U139391
2623 |  | CNV-21026101200 NEWTOWNNANNER FARM CHARG | 4000079909 | PSI32.0000.00011 | TECO JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL | PSI | 0 | 5557.13 | 2025-12-30 | 2025-12-31 |  | 2025-12-31 | C_U139391
2631 |  | CNV-21026122400 OBTAIN EASEMENT FOR MLE | 4000079911 | GRT32.0000.00109 | REL NMAT PRC SETC | NEW NSFS | PSI | 0 | 0 | 2025-12-30 | 2025-12-30 |  | 2025-12-31 | C_U139391
2623 |  | CNV-23026256600 RETIRE PAPER GAUGE | 4000079940 | ANC32.0000.00134 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-12-01 | 2023-12-01 |  | 2023-12-01 | C_U139391
2631 | GREENUP | CNV-23026256700 RETIRE PAPER GAUGE | 4000079941 | ANC32.0000.00134 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-12-01 | 2023-12-01 |  | 2023-12-01 | C_U139391
2632 | MAYSVILLE | CNV-23026256800 RETIRE PAPER GAUGE | 4000079942 | ANC32.0000.00134 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-12-01 | 2023-12-01 |  | 2023-12-01 | C_U139391
2631 | WORTHINGTON | CNV-23026257300 RETIRE CHART | 4000079943 | SUP32.0002.00001 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 385.91 | 2023-12-01 | 2023-12-01 | 2025-07-30 | 2023-12-01 | C_U139391
2631 | ASHLAND | CNV-23026257600 RETIRE PAPER CHAT | 4000079944 | SUP32.0002.00001 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 575.02 | 2023-12-01 | 2023-12-01 | 2025-07-30 | 2023-12-01 | C_U139391
2631 | LOUISA | CNV-23026257800 RETIRE PAPER CHART | 4000079945 | SUP32.0002.00001 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 1139.64 | 2023-12-01 | 2023-12-01 | 2025-07-30 | 2023-12-01 | C_U139391
2632 | MAYSVILLE | CNV-23026258000 RETIRE PAPER CHART | 4000079946 | SUP32.0002.00001 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 555.74 | 2023-12-01 | 2023-12-01 | 2025-07-30 | 2023-12-01 | C_U139391
2632 | MAYSVILLE | CNV-23026258300 INSTALL VRG CONTROLLER | 4000079947 | ANC32.0000.00297 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 9623.8 | 2024-12-23 | 2024-12-31 | 2025-07-31 | 2024-12-31 | C_U139391
2631 | LOUISA | CNV-23026259500 RETIRE PAPER CHART | 4000079948 | SUP32.0002.00001 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 347.03 | 2023-12-01 | 2023-12-01 | 2025-07-30 | 2023-12-01 | C_U139391
2623 | VERSAILLES | CNV-23026259700 RETIRE PAPER CHART | 4000079949 | SUP32.0002.00001 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-12-01 | 2023-12-01 |  | 2023-12-01 | C_U139391
2631 | LOUISA | CNV-23026259900 RETIRE PAPER CHART | 4000079950 | SUP32.0002.00001 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-12-01 | 2023-12-01 |  | 2023-12-01 | C_U139391
2631 | LOUISA | CNV-23026260100 RETIRE PAPER GAUGE | 4000079951 | SUP32.0002.00001 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-12-01 | 2023-12-01 |  | 2023-12-01 | C_U139391
2631 | WORTHINGTON | CNV-23026260300 RETIRE PAPER CHART | 4000079952 | SUP32.0002.00001 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-12-01 | 2023-12-01 |  | 2023-12-01 | C_U139391
2631 | GREENUP | CNV-23026260500 RETIRE PAPER CHART | 4000079953 | SUP32.0002.00001 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-12-01 | 2023-12-01 |  | 2023-12-01 | C_U139391
2621 | LEXINGTON | CNV-23026260800 RETIRE PAPER CHART | 4000079955 | SUP32.0002.00001 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-12-01 | 2023-12-01 |  | 2023-12-01 | C_U139391
2631 | GREENUP | CNV-23026261000 RETIRE PAPER CHART | 4000079956 | SUP32.0002.00001 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-12-01 | 2023-12-01 |  | 2023-12-01 | C_U139391
2633 | HAROLD | CNV-23026261600 RETIRE PAPER CHART | 4000079957 | SUP32.0002.00001 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 366.29 | 2023-12-01 | 2023-12-01 | 2025-07-30 | 2023-12-01 | C_U139391
2631 | CATLETTSBURG | CNV-23026261800 RETIRE PAPER CHART | 4000079958 | SUP32.0002.00001 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 642.64 | 2023-12-01 | 2023-12-01 | 2025-07-30 | 2023-12-01 | C_U139391
2633 | PIPPA PASSES | CNV-23026265300 INSTALL PILOT REGULATORS | 4000080000 | GRT32.0000.00068 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 7990.65 | 2024-09-30 | 2024-10-01 | 2025-07-31 | 2024-10-01 | C_U139391
2633 | HONAKER | CNV-23026276000 REPLACE ODORIZER R-1439 | 4000080002 | ANC32.0000.00121 | REL NMAT PRC SETC | NEW NSFS | STA | 0 | 0 | 2025-12-23 | 2025-12-31 |  | 2025-12-31 | C_U139391
2623 |  | CNV-23026287500 PS&I VANDALAY & WESTRIDG | 4000080003 | PSI32.0000.00014 | REL GMPS NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 24066.53 | 2023-12-28 | 2023-12-31 |  | 2023-12-31 | C_U139391
2629 | RICHMOND | CNV-23026303200 R-1647 REBUILD INSTALL | 4000080004 | BET32.0000.00021 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 22781.66 | 2024-12-16 | 2024-12-16 | 2025-07-31 | 2024-12-31 | C_U139391
2631 | GREENUP | CNV-23026306800 INSTALL METER RUN | 4000080005 | ANC32.0000.00122 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 6792.46 | 2024-11-26 | 2024-12-01 | 2025-08-01 | 2024-12-01 | C_U139391
2631 | GREENUP | CNV-23026308100 INSTALL NEW METER | 4000080006 | ANC32.0000.00128 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 1799.98 | 2024-12-23 | 2024-12-31 | 2025-08-01 | 2024-12-31 | C_U139391
2623 |  | CNV-25026377600 EMER-INSTALL 4' OF 2\"PM | 4000080036 | BET32.0000.00013 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 4751.4 | 2025-05-29 | 2025-06-01 |  | 2025-06-01 | C_U139391
2629 |  | CNV-25026378800 EMER - INSTALL 25'-2\\\. | 4000080039 | ANC32.0000.00094 | REL GMPS MANC NMAT NTUP PRC SETC | NEW FCMP REV | MAI | 0 | 21884.96 | 2024-11-13 | 2024-11-13 |  | 2025-01-07 | C_U139391
2629 |  | CNV-25026379000 EMER - INSTALL 9'-2\" PM | 4000080041 | ANC32.0000.00293 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 0 | 2025-01-02 | 2025-01-02 |  | 2025-01-13 | C_U139391
2629 |  | CNV-25026379101 EMER - RETIRE 9'-2\" PMP | 4000080043 | ANC32.0000.00293 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 2522.61 | 2025-01-02 | 2025-01-02 |  | 2025-01-13 | C_U139391
2623 |  | CNV-25026381300 EMER-INSTALL 180' OF 4\" | 4000080045 | ANC32.0000.00294 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 73.05 | 2025-01-28 | 2026-03-31 | 2025-08-01 | 2026-11-15 | C_U139391
2623 |  | CNV-25026381400 EMER-RETIRE 180' OF 6\"B | 4000080047 | ANC32.0000.00294 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 34.48 | 2025-01-28 | 2026-03-31 | 2025-08-03 | 2026-11-15 | C_U139391
2631 |  | CNV-25026381500 EMER - RETIRE ~870'-3\" | 4000080049 | ANC32.0000.00114 | REL PCNF MANC PRC SETC | COCO FCMP NSFS | MAI | 2276.13 | 4189.61 | 2025-01-27 | 2025-01-30 | 2025-08-03 | 2049-12-31 | C_U139391
2631 |  | CNV-25026381700 INSTALL 230' OF 2\\\ P. | 4000080051 | GRT32.0000.00002 | REL MANC NMAT PRC SETC | NEW | MAI | 0 | 31499.98 | 2025-02-04 | 2025-02-07 |  | 2025-04-14 | C_U139391
2629 |  | CNV-25026381800 INSTALL 250'-2\" PMMP | 4000080053 | GRT32.0000.00107 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 30046.4 | 2025-04-09 | 2025-04-11 | 2025-08-05 | 2025-04-11 | C_U139391
2631 |  | CNV-25026382100 INSTALL 110'-4\" PMLP | 4000080055 | BET32.0000.00025 | REL GMPS MANC PRC SETC | NPRG FCMP MIFE | MAI | 211351.06 | 348136.85 | 2025-10-17 | 2025-10-30 |  | 2025-10-30 | C_U139391
2623 |  | CNV-25026392000 INSTALL 140'-2\" PMMP | 4000080057 | GRT32.0000.00077 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 10453.86 | 2025-02-27 | 2025-05-28 | 2025-08-05 | 2025-05-28 | C_U139391
2631 |  | CNV-25026392800 RETIRE MP - PAPER ONLY | 4000080059 | ANC32.0000.00157 | REL MANC PRC SETC | COCO FCMP NSFS | MAI | 91.28 | 122.88 | 2026-12-31 | 2026-12-31 |  | 2026-12-31 | C_U139391
2629 |  | CNV-25026393800 INSTALL 2,100'-2\\\ PM. | 4000080081 | GRT32.0000.00022 | REL PCNF MANC NMAT PRC SETC | NEW | MAI | 0 | 72432.63 | 2025-05-13 | 2025-05-30 | 2025-08-03 | 2025-05-30 | C_U139391
2633 |  | CNV-25026394000 EMER INSERT 280'-1.2\\\. | 4000080083 | ANC32.0000.00006 | REL MANC NMAT PRC SETC | SCHD | MAI | 0 | 180.59 | 2025-10-28 | 2025-10-31 |  | 2025-10-31 | C_U139391
2633 |  | CNV-25026394100 EMER - RETIRE 284'-2\"BS | 4000080085 | ANC32.0000.00006 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 19.15 | 2025-10-31 | 2025-10-31 |  | 2025-10-31 | C_U139391
2629 |  | ANC-SMRP E Main St-Mt Sterling | 4000080087 | ANC32.0000.00147 | REL PCNF GMPS MANC PRC SETC | SCHD ADJ FCMP | MAI | 42430.62 | 218977.66 | 2025-06-26 | 2025-07-31 | 2025-08-03 | 2025-07-31 | C_U139391
2633 |  | CNV-25026396700 INSTALL RECTIFIER/BULLHO | 4000080089 | ANC32.0000.00006 | REL MANC PRC SETC | NPRG ADJ FCMP MIFE | MAI | 7471.7 | 1080.72 | 2025-08-28 | 2025-08-28 |  |  | C_U139391
2629 |  | ANC-Wisemantown Rd Rectifier-Irvine | 4000080091 | ANC32.0000.00006 | REL MANC PRC SETC | NPRG ADJ FCMP MIFE | MAI | 15373.08 | 4338.37 | 2025-08-28 | 2025-08-28 |  | 2025-08-31 | C_U139391
2623 |  | CNV-25026397000 UPGRADE RECTIFIER W/ RMU | 4000080093 | ANC32.0000.00148 | TECO MANC PRC SETC | NPRG ADJ FCMP MIFE | MAI | 16611.6 | 276.39 | 2025-08-28 | 2025-08-28 |  | 2025-08-31 | C_U139391
2623 |  | CNV-25026397400 EMER-INSTALL 3' OF 2\"PM | 4000080096 | ANC32.0000.00095 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 4664.52 | 2025-07-01 | 2025-07-01 | 2025-08-03 | 2025-07-01 | C_U139391
2629 |  | CNV-25026400200 INSTALL 550'-2\\\ PMMP. | 4000080098 | BET32.0000.00026 | REL PCNF MANC NMAT NTUP PRC SETC | NEW | MAI | 0 | 19463.81 | 2025-04-28 | 2025-05-01 | 2025-08-02 | 2025-05-01 | C_U139391
2629 |  | CNV-25026400700 RETIRE 100'-4\" PMMP | 4000080100 | BET32.0000.00023 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | -3146.07 | 2025-05-14 | 2025-05-15 | 2025-08-03 | 2025-05-15 | C_U139391
2629 |  | CNV-25026403100 EMER - RETIRE 2'-3\" PAM | 4000080102 | BET32.0000.00024 | REL PCNF MANC PRC SETC | COCO FCMP NSFS | MAI | 3218.22 | 11554.81 | 2025-04-07 | 2025-04-07 | 2025-08-03 | 2025-04-09 | C_U139391
2631 | CANNONSBURG | CNV-24026316400 EMER-INSTALL CATALYTIC H | 4000080256 | ANC32.0000.00291 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 1812.91 | 2024-07-01 | 2024-07-01 | 2025-07-31 | 2024-07-01 | C_U139391
2633 | SOUTH WILLIAMSON | CNV-24026320600 INSTALL ERX BATTERY | 4000080257 | ANC32.0000.00130 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 1980 | 2024-03-28 | 2024-03-30 |  | 2024-03-30 | C_U139391
2629 |  | CNV-24026345200 PM PARIS-CYNTHIANA POD R | 4000080259 | PSI32.0000.00023 | REL PCNF CSER NMAT PRC SETC | NEW NSFS WENG | PSI | 0 | 15497.83 | 2027-04-01 | 2027-10-01 | 2026-03-04 | 2027-10-30 | C_U139391
2623 |  | CNV-24026346800 LAND AND CONFLICT ASSESM | 4000080281 | PSI32.0000.00026 | TECO JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL REV | PSI | 0 | 29608.59 | 2024-07-29 | 2024-07-30 |  | 2024-07-30 | C_U139391
2633 |  | CNV-24026352100 INVESTIGATE MAINS | 4000080282 | PSI32.0000.00027 | TECO JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL REV | PSI | 0 | 39866.93 | 2024-09-30 | 2024-09-30 |  | 2024-09-30 | C_U139391
2629 |  | PSI-SMRP Rogers Av ROW-Mt Sterling | 4000080283 | ANC32.0000.00277 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 17954.07 | 2024-08-29 | 2024-08-31 |  | 2024-08-31 | C_U139391
2621 |  | CNV-24026369400 MAINS & SERVICES LOCATE/ | 4000080286 | PSI32.0000.00032 | REL NMAT PRC SETC | NEW NSFS | PSI | 0 | 15967.77 | 2025-01-30 | 2025-01-31 |  | 2025-01-31 | C_U139391
2633 |  | CNV-24026370800 ENVIROMENTAL CONSULTANT | 4000080287 | PSI32.0000.00031 | REL NMAT PRC SETC | NEW NSFS | PSI | 0 | 10970.06 | 2025-01-31 | 2025-01-31 |  | 2025-01-31 | C_U139391
2629 | IRVINE | ANC-Red Lick Rd Regulator Station-Irvine | 4000080301 | BET32.0000.00022 | REL PCNF GMPS MANC PRC SETC | NPRG FCMP | STA | 561.33 | 111062.47 | 2025-12-30 | 2025-12-31 | 2025-08-01 | 2025-12-31 | C_U139391
2629 |  | ANC-Levee Rd POD Valves-Mt Sterling | 4000080302 | ANC32.0000.00119 | REL NMAT PRC SETC | NEW NSFS | STA | 0 | 2052.03 | 2025-12-30 | 2025-12-31 |  | 2025-12-31 | C_U139391
2633 |  | CNV-22026221400 PS&I - INDUSTRIAL PARK | 4000080303 | PSI32.0000.00036 | TECO JBFI MANC NMAT PRC SETC | NEW CAN FCMP NSFS RECL | PSI | 0.76 | 0 | 2025-12-30 | 2025-12-31 |  | 2025-12-31 | C_U139391
2633 | PIPPA PASSES | CNV-24026311300 EMER - INSTALL 2\" 461S | 4000080322 | ANC32.0000.00298 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 2090.56 | 2024-03-26 | 2024-04-01 | 2025-07-31 | 2024-04-01 | C_U139391
2633 | PIPPA PASSES | CNV-24026311400 EMER - RETIRE 2\" MOONEY | 4000080323 | ANC32.0000.00298 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 721.31 | 2024-04-01 | 2024-04-01 | 2025-07-31 | 2024-04-01 | C_U139391
2631 |  | CNV-24026354700 INVESTIGATE REG STATION | 4000080335 | ANC32.0000.00267 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 5556.87 | 2024-08-29 | 2024-08-31 |  | 2024-08-31 | C_U139391
2631 | ASHLAND | CNV-24026325200 INSTALL BYPASS VALVE | 4000080336 | ANC32.0000.00131 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV WENG | STA | 0 | 13743.6 | 2024-05-24 | 2024-06-01 | 2025-07-31 | 2024-06-01 | C_U139391
2631 |  | CNV-24026334700 INVESTIGATE LAND RIGHTS | 4000080337 | PSI32.0000.00020 | TECO JBFI MANC NMAT PRC SETC | NEW CAN FCMP NSFS RECL | PSI | 0.76 | 30335.71 | 2025-01-30 | 2025-01-30 |  | 2025-01-30 | C_U139391
2632 |  | CNV-24026336300 INVESTIGATE EASEMENTS | 4000080338 | PSI32.0000.00022 | TECO GMPS JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL | PSI | 0 | 194084.06 | 2025-02-28 | 2025-03-01 |  | 2025-03-01 | C_U139391
2629 | IRVINE | CNV-24026359000 EMER - INSTALL NEW REGUL | 4000080339 | ANC32.0000.00300 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 20764.74 | 2024-09-23 | 2024-09-28 |  | 2024-09-28 | C_U139391
2629 | IRVINE | CNV-24026359100 EMER - RETIRE REGULATOR | 4000080360 | ANC32.0000.00300 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 1814.05 | 2024-09-30 | 2024-09-30 | 2025-08-02 | 2024-09-30 | C_U139391
2631 |  | CNV-25026381600 ENVIROMENTAL CONSULTANT | 4000080424 | BET32.0000.00045 | REL CSER NMAT PRC SETC | NEW NSFS | PSI | 0 | 1885.5 | 2026-07-16 | 2026-07-18 |  | 2026-07-18 | C_U139391
2629 |  | PSI-SMRP Regan Dr ROW-Winchester | 4000080425 | PSI32.0000.00033 | TECO JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL | PSI | 0 | 12437.99 | 2025-10-31 | 2025-10-31 |  | 2025-10-31 | C_U139391
2629 |  | PSI-SMRP W Lexington Av ROW-Winchester | 4000080426 | PSI32.0000.00030 | TECO JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL | PSI | 0 | 52843.54 | 2025-10-31 | 2025-10-31 |  | 2025-10-31 | C_U139391
2629 |  | PSI-SMRP Evergreen Dr ROW-Irvine | 4000080427 | PSI32.0000.00039 | TECO JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL | PSI | 0 | 22398.79 | 2025-10-31 | 2025-10-31 |  | 2025-10-31 | C_U139391
2621 |  | CNV-25026392200 DESIGN CONFLICT RELOCATI | 4000080428 | PSI32.0000.00034 | TECO JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL | PSI | 0 | 4554.68 | 2025-04-30 | 2025-04-30 |  | 2025-05-01 | C_U139391
2633 |  | CNV-25026399000 INVESTIGATE SITE | 4000080429 | ANC32.0000.00129 | REL NMAT PRC SETC | NEW NSFS | PSI | 0 | 21304.09 | 2025-08-01 | 2025-08-01 |  | 2025-08-01 | C_U139391
2621 |  | CNV-25026404400 LAND AND ENVIRONMENTAL | 4000080430 | ANC32.0000.00093 | REL GMPS NMAT PRC SETC | NEW NSFS | PSI | 0 | 150455.15 | 2025-10-01 | 2025-10-01 |  | 2025-10-01 | C_U139391
2621 |  | CNV-25026407000 INVESTIGATE EASEMENTS | 4000080464 | PSI32.0000.00043 | REL NMAT PRC SETC | NEW NSFS | PSI | 0 | 79956.78 | 2025-07-30 | 2025-07-30 |  | 2025-07-30 | C_U139391
2629 |  | PSI-Hollow Creek ROW-Mt Sterling | 4000080587 | PSI32.0000.00005 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 0 | 2020-12-29 | 2020-12-30 |  | 2020-12-30 | C_U139391
2621 |  | CNV-21026151000 MAP & INVESTIGATE CONFLI | 4000080624 | PSI32.0000.00002 | TECO GMPS JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL REV WENG WENV* | PSI | 0 | 15252.52 | 2022-06-30 | 2022-06-30 |  | 2022-06-30 | C_U139391
2621 | LEXINGTON | CNV-22026211900 INSTALL 1\" BYPASS VALVE | 4000080780 | ANC32.0000.00120 | REL NMAT PRC SETC | NEW NSFS | STA | 0 | 0 | 2025-09-25 | 2025-10-01 |  | 2025-10-01 | C_U139391
2621 | LEXINGTON | CNV-23026246100 RETIRE PAPER GAUGE | 4000080949 | ANC32.0000.00291 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-02-01 | 2023-02-01 |  | 2023-02-01 | C_U139391
2621 | LEXINGTON | CNV-23026271600 PAPER ONLY TO SET UP WMS | 4000080951 | BET32.0000.00001 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-06-30 | 2023-07-01 |  | 2023-07-01 | C_U139391
2621 | LEXINGTON | CNV-23026273900 INSTALL 441 REG (WEST RU | 4000080952 | ANC32.0000.00125 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 0 | 2023-11-01 | 2023-11-01 |  | 2023-11-01 | C_U139391
2633 |  | CNV-23026275400 INVESTIGATE MAINS | 4000080953 | PSI32.0000.00001 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 53321.38 | 2023-08-01 | 2023-08-01 |  | 2023-08-01 | C_U139391
2631 |  | CNV-23026280700 RETIRE STATIONS R-1375 | 4000080954 | ANC32.0000.00101 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 1925.19 | 2024-04-30 | 2024-04-30 | 2025-07-31 | 2024-04-30 | C_U139391
2621 |  | CNV-23026285500 RETIRE REG STATION #1129 | 4000080955 | BET32.0000.00020 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 12134 | 2024-03-01 | 2024-03-01 | 2025-08-12 | 2024-03-01 | C_U139391
2623 | VERSAILLES | CNV-23026288700 INSTALL NEW RELIEF VALVE | 4000080956 | ANC32.0000.00291 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 603.94 | 2023-11-01 | 2023-11-01 | 2025-07-30 | 2023-11-01 | C_U139391
2633 | GREEN MEADOW | CNV-23026302100 RETIRE PAPER GAUGE | 4000080957 | ANC32.0000.00133 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 306.23 | 2024-12-13 | 2024-12-15 |  | 2024-12-15 | C_U139391
2633 | HAROLD | CNV-23026302200 RETIRE PAPER GAUGE | 4000080958 | ANC32.0000.00133 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 1191.8 | 2024-12-13 | 2024-12-15 | 2025-07-31 | 2024-12-15 | C_U139391
2629 | WACO | CNV-23026302300 RETIRE PAPER GAUGE | 4000080959 | ANC32.0000.00133 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 835.24 | 2024-12-13 | 2024-12-15 | 2025-07-31 | 2024-12-15 | C_U139391
2632 | MAYSVILLE | CNV-23026302500 RETIRE PAPER GAUGE | 4000080980 | ANC32.0000.00133 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 994.07 | 2023-12-15 | 2023-12-15 | 2025-07-31 | 2023-12-15 | C_U139391
2633 | PIPPA PASSES | CNV-23026306500 INSTALL DRIP TANK | 4000080981 | ANC32.0000.00123 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 13157.5 | 2024-06-25 | 2024-07-01 | 2025-07-31 | 2024-07-01 | C_U139391
2632 | MAYSVILLE | CNV-23026258400 RETIRE BRISTOL CONTROL U | 4000081095 | ANC32.0000.00297 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 600.77 | 2024-12-31 | 2024-12-31 | 2025-08-01 | 2024-12-31 | C_U139391
2631 | CANNONSBURG | PSI-T-4 Transmission Derate-Ashland | 4000081096 | PSI32.0000.00015 | REL MANC NMAT PRC SETC | NEW NSFS WENG | PSI | 0 | 691279.34 | 2025-12-30 | 2026-12-30 |  | 2026-12-31 | C_U139391
2623 |  | CNV-24026344100 PS&I 329 ST CLAIR ST | 4000081374 | PSI32.0000.00024 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 3858.74 | 2024-12-30 | 2024-12-31 |  | 2024-12-31 | C_U139391
2621 |  | CNV-24026363000 NEW CIRCLE RD REVISION | 4000081389 | PIG32.0000.00027 | TECO JBFI MANC NMAT PRC SETC | NEW CAN FCMP NSFS RECL | PSI | 0.76 | 39676.23 | 2025-12-31 | 2025-12-31 |  | 2025-12-31 | C_U139391
2623 |  | CNV-24026310300 PS&I EAST WEST CONNECTOR | 4000081410 | PSI32.0000.00038 | TECO JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL REV | PSI | 0 | 2789.84 | 2024-12-30 | 2024-12-31 |  | 2024-12-31 | C_U139391
2623 |  | CNV-24026311000 PS&I 400 STEADMANTOWN LN | 4000081411 | PSI32.0000.00016 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 6769.63 | 2024-12-30 | 2024-12-31 |  | 2024-12-31 | C_U139391
2621 |  | CNV-24026313600 INVESTIGATE HP EASEMENT/ | 4000081412 | PSI32.0000.00004 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 9525.67 | 2024-12-30 | 2024-12-30 |  | 2024-12-31 | C_U139391
2621 |  | CNV-24026353500 ENCROACHMENT INV. & AGRE | 4000081417 | PSI32.0000.00037 | REL NMAT PRC SETC | NEW NSFS | PSI | 0 | 3637.5 | 2025-12-31 | 2025-12-31 |  | 2025-12-31 | C_U139391
2629 |  | CNV-24026331400 RETIRE R-1279 | 4000081418 | ANC32.0000.00174 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 1587.82 | 2024-12-31 | 2024-12-31 | 2025-07-31 | 2024-12-31 | C_U139391
2633 |  | CNV-24026332400 INVESTIGATE EASEMENTS AN | 4000081419 | PSI32.0000.00009 | TECO JBFI NMAT PRC SETC | NEW CAN FCMP NSFS RECL REV | PSI | 0 | 7297.56 | 2024-12-30 | 2024-12-30 |  | 2024-12-30 | C_U139391
2631 |  | CNV-24026335600 INVESTIGATE EASEMENTS FO | 4000081420 | PSI32.0000.00021 | REL NMAT PRC SETC | NEW NSFS REV | PSI | 0 | 4137.58 | 2024-12-30 | 2024-12-30 |  | 2024-12-31 | C_U139391
2629 |  | ANC-Levee Rd VRG Pilots-Mt Sterling | 4000081560 | ANC32.0000.00116 | REL NMAT PRC SETC | NEW NSFS REV | STA | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 2023-12-31 | C_U139391
2631 | ASHLAND | CNV-18026753500 INSTALL NEW REGULATORS | 4000081561 | ANC32.0000.00117 | REL NMAT PRC SETC | NEW NSFS REV | STA | 0 | 0 | 2023-12-29 | 2023-12-31 |  | 2023-12-31 | C_U139391
2631 |  | CNV-21026154600 RETIRE R-1354 | 4000081566 | ANC32.0000.00167 | TECO NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 8911.51 | 2023-12-29 | 2023-12-31 |  | 2023-12-31 | C_U139391
2629 | WINCHESTER | ANC-Mutual Ave Reg ABN-Winchester | 4000081704 | ANC32.0000.00195 | REL PCNF MANC NMAT PRC SETC | NEW | STA | 2240.64 | 2460.9 | 2025-12-31 | 2025-12-31 | 2025-08-01 | 2025-12-31 | C_U139391
2629 | CYNTHIANA | CNV-22026238100 RETIRE R-1230-A | 4000081705 | ANC32.0000.00196 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 3401.79 | 2024-12-31 | 2024-12-31 | 2025-07-31 | 2024-12-31 | C_U139391
2629 | IRVINE | ANC-Red Lick Rd Regulator ABN-Irvine | 4000081715 | BET32.0000.00022 | REL PCNF MANC PRC SETC | NPRG FCMP | STA | 94.53 | 19171.8 | 2025-12-31 | 2025-12-31 | 2025-08-01 | 2025-12-31 | C_U139391
2629 |  | CNV-22026205900 RETIRE R-1682 | 4000081716 | ANC32.0000.00003 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 603.94 | 2023-12-29 | 2023-12-31 | 2025-07-30 | 2023-12-31 | C_U139391
2621 | LEXINGTON | CNV-22026212600 RETIRE STATION VALVES R- | 4000081717 | ANC32.0000.00115 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 1269.95 | 2023-12-29 | 2023-12-31 | 2025-07-30 | 2023-12-31 | C_U139391
2633 |  | CNV-25026398400 EMER - INSTALL FITTINGS. | 4000081864 | ANC32.0000.00096 | REL MANC NMAT NTUP PRC SETC | NEW CAN | MAI | 0 | 4387.89 | 2025-11-25 | 2025-11-30 |  |  | C_U139391
2621 | LEXINGTON | CNV-25026408500 INSTALL ANODE BED FOR D. | 4000081875 | GRT32.0000.00076 | REL MANC NMAT PRC SETC | NEW | MAI | 0 | 12635.05 | 2025-12-31 | 2025-12-31 |  |  | C_U139391
2623 |  | CNV-22026178300 EMER-INSTALL 5'OF 2\"PMM | 4000081951 | ANC32.0000.00016 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2022-11-30 | 2022-11-30 |  |  | C_U139391
2631 |  | CNV-22026180700 EMER - INSTALL 3'-3\" PM | 4000081952 | ANC32.0000.00183 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 157.87 | 2022-09-12 | 2022-09-13 | 2025-07-30 |  | C_U139391
2631 |  | CNV-22026180800 EMER - RETIRE 3'-3\" PMI | 4000081953 | ANC32.0000.00183 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 61.32 | 2022-09-13 | 2022-09-13 | 2025-07-30 |  | C_U139391
2631 |  | CNV-23026247100 EMER - INSTALL 9'-4\" CS | 4000082025 | ANC32.0000.00210 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-09-25 | 2023-09-30 |  |  | C_U139391
2631 |  | CNV-23026247200 EMER - RETIRE 9'-4\" CSM | 4000082026 | ANC32.0000.00210 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-09-29 | 2023-09-30 |  |  | C_U139391
2621 |  | CNV-23026264300 EMER-INSTALL 5' OF 4\"PM | 4000082027 | ANC32.0000.00218 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-03-09 | 2023-03-10 |  |  | C_U139391
2621 |  | CNV-23026264400 EMER-RETIRE 520'- 4\"PAI | 4000082028 | ANC32.0000.00218 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-03-10 | 2023-03-10 |  |  | C_U139391
2631 |  | CNV-23026264500 EMER - INSTALL ~5'-4\" P | 4000082029 | ANC32.0000.00219 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 136.4 | 2023-11-30 | 2023-11-30 | 2025-07-30 |  | C_U139391
2631 |  | CNV-23026264600 EMER - RETIRE ~5'-4\" CS | 4000082030 | ANC32.0000.00219 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 207.26 | 2023-11-30 | 2023-11-30 | 2025-07-30 |  | C_U139391
2621 |  | CNV-23026265400 EMER - INSTALL 12' - 2\" | 4000082031 | BET32.0000.00034 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 840 | 2023-03-08 | 2023-03-08 |  |  | C_U139391
2621 |  | CNV-23026265500 EMER - RETIRE 12' - 2\" | 4000082032 | BET32.0000.00034 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-03-08 | 2023-03-08 |  |  | C_U139391
2631 |  | CNV-23026265600 EMER - INSTALL 4'-6\" PM | 4000082033 | ANC32.0000.00036 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 25.3 | 2023-11-27 | 2023-11-30 |  |  | C_U139391
2629 |  | CNV-23026266800 EMER - INSTALL 7'-2\" P | 4000082034 | ANC32.0000.00038 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-11-10 | 2023-11-30 |  |  | C_U139391
2629 |  | CNV-23026267000 EMER - INSTALL 2'-2\" PM | 4000082035 | ANC32.0000.00039 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 0 | 2023-11-29 | 2023-11-30 |  |  | C_U139391
2631 |  | CNV-23026269500 EMER - INSTALL 4'-2\" PI | 4000082036 | ANC32.0000.00041 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 20.9 | 2023-11-29 | 2023-11-30 |  |  | C_U139391
2629 |  | CNV-23026288500 EMER - INSTALL 3'-2\" PM | 4000082037 | ANC32.0000.00241 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 24.2 | 2024-04-10 | 2024-04-30 |  |  | C_U139391
2631 |  | CNV-23026289300 INSTALL 7'-2\"&6\" PMLP | 4000082038 | ANC32.0000.00162 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 279.67 | 2024-04-30 | 2024-04-30 |  |  | C_U139391
2631 |  | CNV-23026290100 EMER - 3'-3\" PMIP | 4000082039 | ANC32.0000.00244 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2933.74 | 2024-04-26 | 2024-04-30 | 2025-07-30 |  | C_U139391
2631 |  | CNV-23026290200 EMER-RETIRE 3'-PIP | 4000082060 | ANC32.0000.00244 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 192.16 | 2024-04-30 | 2024-04-30 | 2025-07-30 |  | C_U139391
2631 |  | CNV-23026291700 EMER - INSTALL 3'-4\" PM | 4000082061 | ANC32.0000.00247 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 801.39 | 2024-05-30 | 2024-05-31 | 2025-07-30 |  | C_U139391
2631 |  | CNV-23026291800 EMER - RETIRE 3'-4\" PIP | 4000082062 | ANC32.0000.00247 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 573.92 | 2024-05-31 | 2024-05-31 | 2025-07-30 |  | C_U139391
2621 |  | CNV-23026307700 EMER - INSTALL 5'-2\" PM | 4000082063 | ANC32.0000.00030 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 2260.97 | 2024-08-29 | 2024-08-31 |  |  | C_U139391
2631 |  | CNV-22026162900 INVESTIGATE/BUY-OUT CUST | 4000082435 | GRT32.0000.00109 | REL CSER NMAT PRC SETC | NEW NSFS | PSI | 0 | 0 | 2049-12-31 | 2049-12-31 |  |  | C_U139391
2621 |  | CNV-24026370600 INSTALL 32'-6\" PMLP | 4000082483 | PIG32.0000.00014 | REL PCNF MANC PRC SETC | NEW ADJ FCMP NSFS WENG | MAI | 790.12 | 4096.57 | 2025-05-23 | 2025-05-30 | 2025-08-02 |  | C_U139391
2621 |  | CNV-24026370700 RETIRE 20'-6\" BSLP | 4000082484 | PIG32.0000.00014 | REL PCNF MANC PRC SETC | COCO FCMP NSFS WENG | MAI | 44.58 | 6023.38 | 2025-05-30 | 2025-05-30 | 2025-08-03 |  | C_U139391
2621 |  | ANC-JONES CREEK HP-LEXINGTON | 4000082485 | ANC32.0000.00093 | REL MANC NMAT PRC SETC | NEW NSFS | MAI | 0 | 1197.37 | 2026-10-01 | 2027-12-31 |  |  | C_U139391
2621 |  | CNV-25026399300 EMER - INSTALL 5'-2\" PM | 4000082499 | ANC32.0000.00097 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 1473.33 | 2025-11-26 | 2025-11-30 |  |  | C_U139391
2621 |  | CNV-23026270100 RETIRE REG STATION# 1020 | 4000082569 | ANC32.0000.00187 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | STA | 0 | 1846.92 | 2024-12-13 | 2024-12-15 | 2025-07-31 |  | C_U139391
2629 | RICHMOND | ANC-Country Club Heights PG RET-Richmond | 4000082570 | ANC32.0000.00133 | REL PCNF NMAT PRC SETC | NEW NSFS REV | STA | 0 | 1046.86 | 2024-12-13 | 2024-12-15 | 2025-07-31 |  | C_U139391
2629 |  | CNV-24026365600 INSTALL SSD UNIT W/ZINC | 4000082652 | ANC32.0000.00137 | TECO PCNF NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 59384.05 | 2024-12-18 | 2024-12-31 | 2025-08-01 | 2024-12-31 | C_U139391
2631 |  | CNV-24026347300 EMER - INSTALL 12'-3\" P | 4000082667 | ANC32.0000.00271 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 15910.58 | 2025-02-24 | 2025-02-28 | 2025-07-31 |  | C_U139391
2631 |  | CNV-24026347400 EMER - RETIRE 12'-3\" PI | 4000082668 | ANC32.0000.00271 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 139.93 | 2025-02-28 | 2025-02-28 | 2025-07-31 |  | C_U139391
2631 |  | CNV-24026349700 EMER INSTALL 2' OF 2\" P | 4000082669 | ANC32.0000.00274 | REL PCNF NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 3768.7 | 2025-03-31 | 2025-03-31 | 2025-08-01 |  | C_U139391
2631 |  | CNV-24026349800 EMER ABANDON 2' OF 2\" P | 4000082670 | ANC32.0000.00274 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 267.85 | 2025-03-31 | 2025-03-31 |  |  | C_U139391
2621 |  | CNV-24026375200 EMER-INSTALL 6' OF 2\"PM | 4000082671 | ANC32.0000.00091 | REL NMAT PRC SETC | NEW FCMP NSFS | MAI | 0 | 4863.68 | 2025-08-29 | 2025-08-31 |  |  | C_U139391
2629 |  | CNV-24026335100 EMER - INSTALL 4'-3\" PM | 4000082716 | ANC32.0000.00065 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 5732.51 | 2024-11-11 | 2024-11-30 |  |  | C_U139391
2629 |  | CNV-24026335400 EMER - INSTALL 2'-2\" PM | 4000082717 | ANC32.0000.00066 | REL NMAT PRC SETC | NEW FCMP NSFS REV | MAI | 0 | 4746.17 | 2024-11-21 | 2024-11-30 |  |  | C_U139391
2632 |  | DO NOT EXECUTE | 4100449775 | GRT32.0002.00002 | REL CSER MANC NTUP PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2023-12-28 | 2023-12-31 |  | 2023-12-31 | C_U139391
2629 |  | DO NOT EXECUTE | 4100508576 | PIG32.0000.00035 | REL CSER MANC PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2024-03-27 | 2024-03-31 |  | 2025-06-24 | C_U139391
2629 |  | DO NOT EXECUTE | 4100509593 | GRT32.0002.00002 | REL MANC PRC SETC | NEW CAN NSFS | LND | 4.32 | 0 | 2025-12-30 | 2025-12-31 |  | 2025-12-31 | C_U139391
2629 |  | DO NOT EXECUTE | 4100509621 | ANC32.0000.00195 | REL CSER MANC PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2024-05-30 | 2024-05-30 |  | 2024-05-31 | C_U139391
2629 |  | DO NOT EXECUTE | 4100509632 | ANC32.0000.00005 | REL MACM PRC SETC | NEW CAN NSFS | LND | 2.52 | 0 | 2025-12-30 | 2025-12-31 |  | 2025-12-31 | C_U139391
2629 |  | DO NOT EXECUTE | 4100509673 | ANC32.0000.00202 | REL CSER MACM PRC SETC | NEW CAN | LND | 1 | 0 | 2024-12-31 | 2024-12-31 |  | 2024-12-31 | C_U139391
2629 |  | DO NOT EXECUTE | 4100509718 | ANC32.0000.00004 | REL MACM PRC SETC | NEW CAN | LND | 2.52 | 0 | 2025-12-30 | 2025-12-31 |  | 2025-12-31 | C_U139391
2629 |  | DO NOT EXECUTE | 4100509750 | ANC32.0000.00277 | REL CSER MACM PRC SETC | NEW CAN | LND | 1 | 0 | 2024-12-31 | 2024-12-31 |  | 2024-12-31 | C_U139391
2629 |  | DO NOT EXECUTE | 4100509755 | GRT32.0000.00098 | REL CSER MANC PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2024-12-31 | 2024-12-31 |  | 2024-12-31 | C_U139391
2621 |  | DO NOT EXECUTE | 4100547582 | ANC32.0002.00002 | REL MANC PRC SETC | NEW CAN NSFS | LND | 4.32 | 0 | 2025-04-29 | 2025-04-30 |  | 2025-04-30 | C_U139391
2621 |  | DO NOT EXECUTE | 4100547620 | ANC32.0000.00081 | REL MANC PRC SETC | NEW CAN | LND | 4.32 | 0 | 2025-05-15 | 2025-05-15 |  | 2025-05-17 | C_U139391
2623 |  | DO NOT EXECUTE | 4100553223 | ANC32.0000.00291 | REL CSER MANC PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2021-12-21 | 2021-12-21 |  | 2021-12-21 | C_U139391
2631 |  | DO NOT EXCUTE. | 4100555682 | SUP32.0002.00001 | REL CSER MANC PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2023-06-30 | 2023-06-30 |  | 2023-06-30 | C_U139391
2623 |  | DO NOT EXECUTE | 4100555721 | GRT32.0002.00002 | REL CSER MANC PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2023-09-28 | 2023-10-01 |  | 2023-10-01 | C_U139391
2623 |  | DO NOT EXECUTE | 4100555740 | ANC32.0000.00192 | REL CSER MACM PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2023-09-28 | 2023-09-28 |  | 2023-10-01 | C_U139391
2632 |  | DO NOT EXECUTE | 4100555746 | ANC32.0000.00179 | REL MACM PRC SETC | NEW CAN | LND | 2.52 | 0 | 2025-12-30 | 2025-12-31 |  | 2025-12-31 | C_U139391
2621 |  | DO NOT EXECUTE | 4100555789 | ANC32.0000.00187 | REL CSER MANC PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2023-09-29 | 2023-09-29 |  | 2023-10-01 | C_U139391
2629 |  | DO NOT EXECUTE | 4100555850 | ANC32.0000.00301 | REL CSER MANC PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2024-03-01 | 2024-03-01 |  | 2024-03-01 | C_U139391
2621 |  | DO NOT EXECUTE | 4100569108 | GRT32.0002.00002 | REL CSER MANC PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2023-12-28 | 2023-12-31 |  | 2023-12-31 | C_U139391
2629 |  | DO NOT EXECUTE | 4100577488 | GRT32.0002.00002 | REL MANC PRC SETC | SCHD CAN | LND | 2.72 | 0 | 2024-12-31 | 2024-12-31 |  | 2024-12-31 | C_U139391
2621 |  | CNV-22026211700 RETIRE LAND AND REG SITE | 4100577544 | GRT32.0002.00003 | CRTD MANC PRC | NEW FCMP NSFS REV | LND | 2.52 | 0 | 2023-12-01 | 2023-12-01 |  | 2023-12-01 | C_U139391
2629 |  | DO NOT EXECUTE | 4100577553 | ANC32.0000.00174 | REL CSER MACM PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2023-12-28 | 2023-12-31 |  | 2023-12-31 | C_U139391
2629 |  | DO NOT EXECUTE | 4100577557 | ANC32.0000.00158 | REL CSER MACM PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2023-12-28 | 2023-12-31 |  | 2023-12-31 | C_U139391
2621 |  | DO NOT EXECUTE | 4100577559 | PIG32.0000.00027 | REL CSER MANC PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2023-12-28 | 2023-12-31 |  | 2023-12-31 | C_U139391
2621 |  | DO NOT EXECUTE | 4100577602 | ANC32.0000.00182 | REL CSER MACM PRC SETC | NEW CAN NSFS | LND | 1 | 0 | 2023-06-01 | 2023-06-01 |  | 2023-06-01 | C_U139391
2621 |  | CNV-18026779401 ACQ 25X25 SITE FOR NEW R | 4000082857 | GRT32.0002.00002 | REL NMAT PRC SETC | NEW FCMP NSFS REV WENG | LND | 0 | 0 | 2023-12-28 | 2023-12-31 |  | 2023-12-31 | C_U141034
2632 |  | CNV-20026950500 ACQUIRE LAND FOR STATION | 4000082959 | GRT32.0002.00002 | REL NMAT PRC SETC | NEW FCMP NSFS REV | LND | 0 | 0 | 2023-12-28 | 2023-12-31 |  | 2023-12-31 | C_U141034
2623 |  | CNV-21026123000 INVESTIGATE/AQUIRE EASEM | 4000083108 | ANC32.0000.00291 | REL NMAT PRC SETC | NEW FCMP NSFS REV | LND | 0 | 2027.42 | 2021-12-21 | 2021-12-21 |  | 2021-12-21 | C_U141034
2629 |  | CNV-22026207901 PM- LAND MILLER DR POD | 4000083412 | GRT32.0002.00002 | REL NMAT PRC SETC | NEW NSFS REV | LND | 0 | 0 | 2024-12-31 | 2024-12-31 |  | 2024-12-31 | C_U141034
2629 |  | CNV-22026221100 ACQUIRE EASEMENT | 4000083416 | ANC32.0000.00174 | REL NMAT PRC SETC | NEW FCMP NSFS REV | LND | 0 | 0 | 2023-12-28 | 2023-12-31 |  | 2023-12-31 | C_U141034
2629 |  | CNV-22026224600 ACQUIRE LAND RIGHTS | 4000083417 | ANC32.0000.00158 | REL NMAT PRC SETC | NEW FCMP NSFS REV | LND | 0 | 500 | 2023-12-28 | 2023-12-31 |  | 2023-12-31 | C_U141034
2621 |  | CNV-22026235500 ACQUIRE EASEMENT | 4000083418 | PIG32.0000.00027 | REL NMAT PRC SETC | NEW FCMP NSFS REV | LND | 0 | 0 | 2023-12-28 | 2023-12-31 |  | 2023-12-31 | C_U141034
2621 |  | CNV-22026242400 OBTAIN NEW HP EASEMENT | 4000083419 | ANC32.0000.00182 | REL NMAT PRC SETC | NEW FCMP NSFS REV | LND | 0 | 0 | 2023-06-01 | 2023-06-01 |  | 2023-06-01 | C_U141034
2631 |  | CNV-23026266501 ACQUIRE EASEMENT | 4000084011 | SUP32.0002.00001 | REL NMAT PRC SETC | NEW FCMP NSFS REV | LND | 0 | 0 | 2023-06-30 | 2023-06-30 |  | 2023-06-30 | C_U141034
2623 |  | CNV-23026271300 OBTAIN ADDITIONAL LAND R | 4000084013 | GRT32.0002.00002 | REL NMAT PRC SETC | NEW FCMP NSFS REV | LND | 0 | 0 | 2023-09-28 | 2023-10-01 |  | 2023-10-01 | C_U141034
2623 |  | CNV-23026281000 OBTAIN NEW EASEMENT | 4000084015 | ANC32.0000.00192 | REL NMAT PRC SETC | NEW FCMP NSFS REV | LND | 0 | 4092.58 | 2023-09-28 | 2023-09-28 |  | 2023-10-01 | C_U141034
2632 |  | CNV-23026283900 ACQUIRE EASEMENTS | 4000084016 | ANC32.0000.00179 | REL NMAT PRC SETC | NEW NSFS | LND | 0 | 40497 | 2025-12-30 | 2025-12-31 |  | 2025-12-31 | C_U141034
2621 |  | CNV-23026292600 DOCUMENT 20'EASEMENT FRO | 4000084019 | ANC32.0000.00187 | REL NMAT PRC SETC | NEW FCMP NSFS REV | LND | 0 | 25257.44 | 2023-09-29 | 2023-09-29 |  | 2023-10-01 | C_U141034
2629 |  | CNV-23026302000 ACQUIRE LAND FOR GROUND | 4000084023 | ANC32.0000.00301 | TECO JBFI NMAT PRC SETC | NEW FCMP NSFS REV | LND | 0 | 10681.06 | 2024-03-01 | 2024-03-01 |  | 2024-03-01 | C_U141034
2629 |  | CNV-24026312500 ACQUIRE EASEMENT FOR REL | 4000084727 | PIG32.0000.00035 | TECO JBFI NMAT PRC SETC | NEW FCMP NSFS REV | LND | 0 | 500 | 2024-03-27 | 2024-03-31 |  |  | C_U141034
2629 |  | CNV-24026340500 ACQUIRE EASEMENT | 4000084793 | GRT32.0002.00002 | TECO JBFI NMAT PRC SETC | NEW FCMP NSFS | LND | 0 | 17825 | 2025-12-30 | 2025-12-31 |  | 2025-12-31 | C_U141034
2629 |  | CNV-24026341800 LAND PAYMENT FOR REG SIT | 4000084794 | ANC32.0000.00195 | REL NMAT PRC SETC | NEW FCMP NSFS REV | LND | 0 | 500 | 2024-05-30 | 2024-05-30 |  | 2024-05-31 | C_U141034
2629 |  | CNV-24026349200 ACQUIRE EASEMENT | 4000084795 | ANC32.0000.00005 | TECO JBFI NMAT PRC SETC | NEW FCMP NSFS | LND | 0 | 1800 | 2025-12-30 | 2025-12-31 |  | 2025-12-31 | C_U141034
2629 |  | ANC-SMRP Harrison Ave Land-Mt Sterling | 4000084798 | ANC32.0000.00202 | REL NMAT PRC SETC | NEW NSFS REV | LND | 0 | 475 | 2024-12-31 | 2024-12-31 |  | 2024-12-31 | C_U141034
2629 |  | ANC-SMRP Sunset Dr Land-Paris | 4000084799 | ANC32.0000.00004 | REL NMAT PRC SETC | NEW NSFS | LND | 0 | 19854.2 | 2025-12-30 | 2025-12-31 |  | 2025-12-31 | C_U141034
2629 |  | ANC-SMRP Rogers Av Land-Mt Sterling | 4000084801 | ANC32.0000.00277 | REL NMAT PRC SETC | NEW NSFS REV | LND | 0 | 2799.85 | 2024-12-31 | 2024-12-31 |  | 2024-12-31 | C_U141034
2629 |  | CNV-24026370500 ACQUIRE LAND RIGHTS | 4000084802 | GRT32.0000.00098 | REL NMAT PRC SETC | NEW FCMP NSFS REV | LND | 0 | 20000 | 2024-12-31 | 2024-12-31 |  | 2024-12-31 | C_U141034
2621 |  | CNV-25026399900 OBTAIN EASEMENTS | 4000085076 | ANC32.0002.00002 | TECO JBFI NMAT PRC SETC | NEW FCMP NSFS | LND | 0 | 7294.7 | 2025-04-29 | 2025-04-30 |  | 2025-04-30 | C_U141034
2621 |  | CNV-25026404500 EASEMENT PAYMENT 24-0263 | 4000085079 | ANC32.0000.00081 | REL NMAT PRC SETC | NEW NSFS | LND | 0 | 12827.47 | 2025-05-15 | 2025-05-15 |  | 2025-05-17 | C_U141034
2621 |  | Damage To Company Fac - Main | 4000087006 | ANC32.0002.00001 | REL MANC PRC SETC | NPRG ADJ FCMP MIFE NSFS RCFO REIM | MAI | 1243.06 | 1443.28 | 2025-07-30 | 2025-07-31 |  |  | SAP_WFRT
2623 |  | Damage To Company Fac - Main | 4000087304 | ANC32.0002.00001 | REL MANC PRC SETC | NEW ADJ FCMP MIFE NSFS RCFO REIM | MAI | 1781.13 | 406.59 | 2025-07-31 | 2025-08-01 |  |  | SAP_WFRT
2629 | IRVINE | Design for CU Tab | 4000090723 |  | CRTD MANC NMAT NTUP PRC | EST | MAI | 0 | 0 | 2025-09-21 | 2025-09-21 |  |  | SAP_WFRT
2621 | LEXINGTON | DAMAGED MAIN LINE TKT 253011846 | 4000092953 | ANC32.0002.00001 | REL MANC NMAT PRC SETC | NEW FCMP MIFE NSFS RCFO REIM | MAI | 710.28 | 3153.89 | 2025-10-28 | 2025-10-29 |  |  | SAP_WFRT
2621 |  | JOB CREATED TO CLEAR DPI FROM DAMAGE | 4000093937 | ANC32.0002.00001 | REL MANC NMAT PRC SETC | NEW ADJ FCMP NSFS RCFO | MAI | 847.8 | 350.58 | 2025-10-02 | 2025-10-03 |  | 2025-10-03 | SAP_WFRT
2621 | LEXINGTON | Leak Repair | 4000099530 | ANC32.0002.00001 | REL MANC NMAT PRC SETC | NEW FCMP MIFE NSFS RCFO | MAI | 1025.52 | 2489.56 | 2026-02-14 | 2026-03-07 |  | 2026-03-07 | SAP_WFRT
2633 |  | Install 518'-4" PMIP | 4000085428 | ANC32.0000.00303 | CRTD MANC NTUP PRC | EST REV WENV | MAI | 426369.71 | 0 | 2025-07-14 | 2025-08-08 |  |  | U122858
2623 |  | CNV-24026346800 LAND AND CONFLICT ASSESM | 4000086913 | PIG32.0000.00053 | CRTD MANC NMAT PRC | NEW CAN NSFS RCFO | MAI | 0 | 0 | 2024-07-29 | 2024-07-30 |  | 2024-07-30 | U122858
2623 |  | Finnely Development | 4000086944 | PIG32.0000.00053 | REL MANC PRC SETC | NEW ADJ CAN NSFS RCFO WENG | MAI | 68801.26 | 0 | 2025-08-04 | 2025-09-26 |  | 2025-09-26 | U122858
2623 |  | EMER - E Broadway St Crossbore FRANKFORT | 4000087431 | BET32.0000.00049 | REL ESTC MANC PRC SETC | NPRG ADJ FCMP | MAI | 157244.84 | 2978.58 | 2025-08-06 | 2025-08-29 |  | 2025-08-29 | U122858
2623 |  | Install 965'-4" PMMP | 4000087576 | PIG32.0000.00053 | REL ESTC GMPS MANC PRC SETC | NPRG ADJ FCMP REIM | MAI | 87286.17 | 271321.62 | 2025-08-08 | 2025-09-26 |  |  | U122858
2633 |  | Abandon ~279'-2" BSIP | 4000088050 | ANC32.0000.00316 | REL ESTC MANC PRC SETC | NPRG ADJ WARR WPWT | MAI | 2651.7 | 6303.25 | 2025-08-15 | 2025-11-28 |  |  | U122858
2621 |  | retire pipe | 4000088089 | PIG32.0000.00013 | CRTD MANC NTUP PRC | EST NSFS | MAI | 0 | 0 | 2025-08-15 | 2025-08-29 |  |  | U122858
2623 |  | Land Rights | 4000088138 | PIG32.0000.00053 | CRTD MANC PRC | EST NSFS | MAI | 1 | 0 | 2025-08-18 | 2025-08-18 |  |  | U122858
2621 |  | EMER - Retire 5'-2" PMMP | 4000088162 | GRT32.0000.00075 | CRTD MANC NTUP PRC | EST NSFS | MAI | 0 | 0 | 2025-08-18 | 2025-09-05 |  |  | U122858
2621 |  | EMER - Install 10'-2" PMMP | 4000088222 | BET32.0000.00053 | CRTD MANC NTUP PRC | EST NSFS | MAI | 455.12 | 0 | 2025-08-18 | 2025-09-05 |  |  | U122858
2621 |  | EMER - Retire 10'-2" PMMP | 4000088266 | BET32.0000.00053 | CRTD MANC NTUP PRC | EST NSFS | MAI | 0 | 0 | 2025-08-18 | 2025-08-18 |  |  | U122858
2621 |  | Install valve | 4000088271 | BET32.0000.00054 | REL PCNF ESTC MANC PRC SETC | NPRG ADJ | MAI | 7435.86 | 2214.33 | 2025-08-18 | 2025-10-31 | 2026-03-26 |  | U122858
2631 |  | PIG-S 5th Street-Greenup | 4000088972 | PIG32.0000.00057 | REL PCNF ESTC GMPS MANC PRC SETC | SCHD ADJ | MAI | 76248.19 | 87406.17 | 2025-08-28 | 2025-08-28 | 2026-03-04 | 2026-12-31 | U122858
2631 |  | EMER - Dixon St- Ashland | 4000090728 | PIG32.0000.00059 | REL ESTC GMPS MANC PRC SETC SKKP | NPRG ADJ FCMP | MAI | 49189.54 | 293936.73 | 2025-09-22 | 2025-09-22 |  |  | U122858
2621 |  | PIG-MNA Rosemary Ave-Lexington | 4000090770 | PIG32.0000.00060 | REL ESTC GMPS MANC PRC SETC SKKP | NPRG ADJ | MAI | 451435.3 | 1900152.14 | 2025-09-22 | 2025-09-22 |  |  | U122858
2631 |  | CREATE:NEED TO DEFINE EXISTING EASEMENTS | 4000091540 | ANC32.0000.00334 | CRTD MANC NMAT PRC | NEW NSFS RCFO | MAI | 0 | 0 | 2024-12-31 | 2024-12-31 |  | 2024-12-31 | U122858
2631 |  | ANC-Catletts Creek-Ashland | 4000091541 | ANC32.0000.00334 | REL GMPS MANC PRC SETC | NEW ADJ MIFE NSFS WENV WLND | MAI | 177986.08 | 77643.24 | 2025-11-04 | 2026-11-06 |  | 2026-11-06 | U122858
2632 |  | GRT-350 AA Hwy Grocery-Maysville | 4000093143 | GRT32.0000.00147 | CRTD ESTC MANC NTUP PRC SKKP | PLN ADJ | MAI | 135201.42 | 0 | 2026-04-21 | 2026-12-31 |  |  | U122858
2621 |  | Install Valve | 4000093791 | BET32.0000.00054 | CRTD ESTC CSER MANC NTUP PRC SKKP | NEW CAN | STA | 5126.44 | 0 | 2025-11-18 | 2025-12-05 |  |  | U122858
2621 |  | BET-Mitchell Ave-Lexington | 4000093901 | BET32.0000.00054 | REL ESTC MACM PRC SETC SKKP | NEW ADJ MIFE | STA | 7976.78 | 0 | 2025-11-19 | 2025-11-19 |  |  | U122858
2631 |  | ANC-Worthington-Ashland | 4000094681 | ANC32.0000.00341 | REL PCNF ESTC MANC PRC SETC | NEW ADJ WENG | MAI | 4241260.92 | 97.91 | 2026-10-31 | 2027-12-31 | 2026-05-14 |  | U122858
2631 |  | EMER-10th Street-Catlettsburg | 4000094732 | ANC32.0000.00339 | REL ESTC MANC PRC SETC | NEW ADJ FCMP | MAI | 1792.45 | 2.8 | 2025-12-04 | 2025-12-19 |  |  | U122858
2621 |  | PIG-Liberty Road-Lexington | 4000095180 | PIG32.0000.00064 | REL GMPS MANC PRC SETC | NPRG ADJ FCMP RCFO WENG | MAI | 120380.39 | 61401.74 | 2026-03-30 | 2026-12-31 |  | 2026-12-31 | U122858
2621 |  | ANC-Hunters Rest Ct-Lexington | 4000095706 | ANC32.0000.00342 | REL PCNF ESTC MACM PRC SETC | NEW ADJ | MAI | 11955.89 | 209.55 | 2026-01-05 | 2026-12-28 | 2026-03-04 | 2026-12-28 | U122858
2621 |  | PIG-N Limestone-Lexington | 4000095889 | PIG32.0000.00065 | REL PCNF ESTC GMPS MANC PRC SETC | NEW ADJ WENV WLND | MAI | 1244662.41 | 37496.41 | 2026-07-01 | 2026-12-31 | 2026-03-04 | 2026-12-31 | U122858
2631 |  | CNV-24026357900 INVESTIGATE LAND RIGHTS | 4000096631 | BET32.0000.00063 | REL NMAT PRC SETC | NEW NSFS RCFO | MAI | 0 | 0 | 2024-11-27 | 2024-12-01 |  | 2024-12-01 | U122858
2621 |  | PIG-Coleman Ct-Lexington | 4000096670 | PIG32.0000.00067 | REL ESTC MACM PRC SETC | NEW NSFS | MAI | 719.82 | 0 | 2026-01-20 | 2026-01-20 |  |  | U122858
2631 |  | ANC-11th Street-Catlettsburg | 4000096892 | ANC32.0000.00361 | REL ESTC MANC PRC SETC SKKP | NEW ADJ NSFS | MAI | 3187 | 0 | 2026-10-31 | 2027-12-31 |  |  | U122858
2631 | CATLETTSBURG | VCU | 4000096894 | ANC32.0000.00361 | CRTD MANC NMAT NTUP PRC | EST | STA | 0 | 0 | 2026-01-22 | 2027-12-30 |  |  | U122858
2633 |  | ANC-Main St-Hindman | 4000097076 | ANC32.0000.00364 | REL PCNF MANC PRC SETC | NEW ADJ RCFO WENV | MAI | 11311.59 | 2524.7 | 2024-12-30 | 2024-12-30 | 2026-04-30 | 2024-12-30 | U122858
2631 |  | ANC-Poplar St-Ashland | 4000098118 | ANC32.0000.00375 | REL ESTC MANC PRC SETC | NEW NSFS WLND | MAI | 55263.94 | 1272.06 | 2026-10-31 | 2027-12-31 |  |  | U122858
2631 |  | ANC-Oakview Rd-Ashland | 4000098209 | ANC32.0000.00376 | REL MANC PRC SETC | NEW NSFS | MAI | 0 | 0 | 2026-10-31 | 2027-12-31 |  |  | U122858
2631 |  | ANC-Hagen Ct-Ashland | 4000098266 | ANC32.0000.00377 | REL ESTC MANC PRC SETC | NEW NSFS | MAI | 13049.54 | 0 | 2026-10-31 | 2027-12-31 |  |  | U122858
2633 |  | ANC-SR 550-Hindman | 4000098280 | ANC32.0000.00378 | CRTD MANC NTUP PRC | NEW NSFS | MAI | 42805.94 | 0 | 2026-10-31 | 2028-12-31 |  |  | U122858
2633 |  | ANC-E Main St-Betsy Lane (2633) | 4000098292 | ANC32.0000.00379 | REL ESTC MANC PRC SETC | NEW NSFS WLND | MAI | 8.11 | 0 | 2026-10-31 | 2027-12-31 |  |  | U122858
2631 | WORTHINGTON | ANC-Retire R-1314-Worthington | 4000098339 | ANC32.0000.00341 | CRTD ESTC MANC NTUP PRC SKKP | NEW CAN NSFS | STA | 21065.6 | 0 | 2026-02-19 | 2027-12-31 |  |  | U122858
2631 | WORTHINGTON | ANC-Retire R-1314-Worthington. | 4000098360 | ANC32.0000.00341 | REL PCNF MANC PRC SETC SKKP | NPRG ADJ MIFE WENG | STA | 16286.5 | 264.06 | 2026-02-19 | 2027-12-31 | 2026-02-23 |  | U122858
2631 |  | ANC-34th St-Ashland | 4000098407 | ANC32.0000.00380 | REL MANC PRC SETC | NEW NSFS | MAI | 14068.32 | 0 | 2026-10-31 | 2027-12-31 |  |  | U122858
2631 |  | ANC-16th St-Ashland | 4000099141 | ANC32.0000.00384 | REL ESTC MACM PRC SETC | NEW NSFS | MAI | 31361 | 0 | 2026-03-04 | 2028-12-31 |  |  | U122858
2621 |  | PIG-Buchanan St-Lexington | 4000099164 | PIG32.0000.00073 | REL MANC PRC SETC | NEW ADJ NSFS RCFO | MAI | 251704.78 | 18.14 | 2026-03-12 | 2026-12-31 |  |  | U122858
2621 |  | PIG-Innovation Dr-Lexington | 4000099994 | PIG32.0000.00074 | REL ESTC GMPS MANC PRC SETC SKKP | NEW ADJ WENG | MAI | 91710.66 | 4721.58 | 2026-06-30 | 2026-08-30 |  |  | U122858
2631 | ASHLAND | STA-Hoods Creek M&R-Ashland | 4000100700 | BET32.0000.00063 | CRTD ESTC CSER MANC NTUP PRC | PLN ADJ | STA | 2216.72 | 0 | 2026-03-26 | 2026-03-26 |  |  | U122858
2631 |  | ANC-Pocahantas St-Louisa | 4000101894 | ANC32.0000.00389 | REL ESTC MACM PRC SETC | NEW NSFS | MAI | 4.42 | 0 | 2026-04-17 | 2028-12-31 |  |  | U122858
2621 |  | PIG-US 25-Lexington | 4000102123 | PIG32.0000.00076 | REL NMAT PRC SETC | NEW NSFS RCFO | MAI | 0 | 0 | 2025-12-30 | 2025-12-31 |  | 2025-12-31 | U122858
2631 |  | ANC-Hackworth St-Ashland | 4000102193 | ANC32.0000.00390 | REL ESTC MACM PRC SETC | NEW NSFS | MAI | 8150.69 | 0 | 2026-04-23 | 2026-04-23 |  |  | U122858
2621 | LEXINGTON | Fence for co prem 200874 | 4100791310 | BET32.0000.00050 | CRTD ESTC MANC NTUP PRC | PLN ADJ NSFS | STA | 12697.86 | 0 | 2025-08-15 | 2025-12-15 |  |  | U122858
2632 | MAYSVILLE | RMU REPLACEMENT | 4100801218 | ANC32.0002.00006 | TECO ESTC MANC PRC SETC | NPRG ADJ FCMP MIFE | MAI | 716.3 | 509.66 | 2025-09-19 | 2025-10-17 |  | 2025-10-31 | U122858
2632 | FOSTER | ANC-Heater Repl-Western Hills | 4100853558 | ANC32.0002.00007 | REL ESTC MACM PRC SETC SKKP | NEW | STA | 7268.1 | 29468.84 | 2026-03-06 | 2026-07-03 |  |  | U122858
2623 |  | 275 Heritage Dr MLE Versailles | 4000085536 | GRT32.0000.00119 | TECO PCNF ESTC GMPS JBFI MANC PRC SETC | NPRG ADJ FCMP MIFE | MAI | 15748.01 | 10194.51 | 2025-07-30 | 2025-08-14 | 2026-03-04 |  | U126783
2623 |  | GRT-Paddocks of Frankfort MLE | 4000086825 | GRT32.0000.00121 | REL PCNF ESTC GMPS MANC PRC SETC | SCHD REV | MAI | 596391.42 | 753323.74 | 2025-09-02 | 2025-12-31 | 2026-03-12 | 2026-05-01 | U126783
2623 |  | Fortune Dr Frankfort Tierney MLE | 4000087557 | GRT32.0000.00126 | REL ESTC GMPS MANC PRC SETC SKKP | NPRG ADJ | MAI | 85824.43 | 208369.03 | 2025-08-07 | 2025-08-07 |  |  | U126783
2623 |  | Ball Homes South Crossing P3 Georgetown | 4000087665 | GRT32.0000.00133 | REL ESTC GMPS MANC PRC SETC | NEW ADJ | MAI | 367711.37 | 281612.34 | 2025-09-02 | 2025-11-01 |  | 2025-11-01 | U126783
2623 |  | Vandalay Dr Frankfort Relo | 4000088075 | PIG32.0000.00056 | REL ESTC MANC PRC SETC | NPRG | MAI | 18975.45 | 4123.36 | 2025-08-15 | 2025-08-15 |  |  | U126783
2623 |  | ACE HARDWARE MIDWAY | 4000088987 | GRT32.0000.00134 | TECO ESTC GMPS JBFI MANC PRC SETC | NPRG ADJ FCMP WENG | MAI | 46804.6 | 382863.3 | 2025-09-02 | 2025-10-31 |  | 2025-10-31 | U126783
2623 |  | Ball Homes Payne Crossing P2 Versailles | 4000089773 | GRT32.0000.00135 | REL ESTC GMPS MANC PRC SETC | NPRG ADJ FCMP | MAI | 164510.5 | 250951.48 | 2025-09-04 | 2025-09-04 |  |  | U126783
2623 |  | GRT-Elkhorn Village Georgetown West | 4000089985 | GRT32.0000.00136 | CRTD MANC NTUP PRC | EST | MAI | 177.5 | 0 | 2026-04-16 | 2026-08-29 |  |  | U126783
2623 |  | Vandalay & Westridge Dr Relo Frankfort | 4000090198 | PIG32.0000.00058 | REL ESTC GMPS MANC PRC | NPRG ADJ FCMP | MAI | 285738.67 | 1527223.44 | 2025-09-11 | 2025-09-11 |  |  | U126783
2623 |  | STA-Industry Rd Station Upgrade-GEO | 4000090475 | BET32.0000.00059 | REL ESTC MACM PRC SETC SKKP | NEW ADJ WENG | STA | 48273.88 | 1100 | 2025-09-17 | 2025-09-17 |  | 2026-10-01 | U126783
2623 |  | 2623-VILLAGE AT LEMON MILL-GEORGETOWN | 4000090938 | GRT32.0000.00142 | REL PCNF ESTC GMPS MANC PRC SETC | NPRG ADJ FCMP | MAI | 107957.12 | 89467.15 | 2026-02-15 | 2026-03-31 | 2026-03-13 | 2026-03-31 | U126783
2623 | Nicholasville | 2621-50 & 52 LANTERN WAY-NICHOLASVILLE | 4000091838 | GRT32.0000.00143 | TECO ESTC GMPS JBFI MANC NTUP PRC SETC | NPRG FCMP REV | MAI | 22677.35 | 60519.1 | 2025-10-09 | 2025-10-09 |  |  | U126783
2623 | Georgetown | GRT-RUMPKE CNG MLE-GEORGETOWN | 4000092061 | GRT32.0000.00144 | REL PCNF ESTC GMPS MANC NTUP PRC SETC* | SCHD ADJ | MAI | 252594.58 | 94560.87 | 2026-05-04 | 2026-07-01 | 2026-05-12 | 2026-07-01 | U126783
2623 |  | 2623-SHOPS AT WOODFORD FARM-VERSAILLES | 4000093861 | GRT32.0000.00150 | CRTD ESTC MANC NTUP PRC SKKP | PLN ADJ WENG | MAI | 183861.61 | 0 | 2026-04-21 | 2026-12-19 |  |  | U126783
2621 |  | GRT-BALL HOMES PATCHEN WILKES-LEXINGTON | 4000098070 | GRT32.0000.00161 | REL PCNF ESTC CSER GMPS MANC PRC SETC | NPRG ADJ WENG | MAI | 539151.6 | 118963.06 | 2026-04-15 | 2026-06-05 | 2026-04-13 |  | U126783
2623 |  | PIG-BRANNON ROAD RELO-NICHOLASVILLE | 4000099103 | PIG32.0000.00071 | REL MANC NMAT PRC SETC | NEW NSFS RCFO | MAI | 0 | 506 | 2026-08-01 | 2026-12-31 |  |  | U126783
2623 |  | 2623-SMRP NEWTOWN ANNER-VERSAILLES | 4000100006 | ANC32.0000.00382 | REL NMAT PRC SETC | NEW NSFS RCFO | MAI | 0 | 1289.51 | 2025-12-30 | 2025-12-31 |  | 2025-12-31 | U126783
2621 |  | ANC-MONTGOMERY AVE SMRP-LEXINGTON | 4000100007 | ANC32.0000.00386 | CRTD MANC NTUP PRC | EST | MAI | 183.31 | 0 | 2026-03-16 | 2026-03-16 |  |  | U126783
2623 |  | 2623-EAST WEST CONNECTOR-FRANKFORT | 4000100142 | ANC32.0000.00383 | REL NMAT PRC SETC | NEW NSFS RCFO | MAI | 0 | 0 | 2024-12-30 | 2024-12-31 |  | 2024-12-31 | U126783
2623 |  | GRT-LIVESTOCK INNOVATION CENTER MLE-VER | 4000100528 | GRT32.0000.00165 | CRTD ESTC CSER MANC NTUP PRC SKKP | PLN WENG | MAI | 111669.28 | 0 | 2026-03-24 | 2026-03-24 |  |  | U126783
2623 |  | ANC-N COURT ST SMRP-GEORGETOWN | 4000101432 | ANC32.0000.00387 | CRTD MANC NTUP PRC | EST | MAI | 907.29 | 0 | 2026-04-09 | 2026-04-09 |  |  | U126783
2623 |  | GRT-GEORGETOWN COMMONS MLE-GEORGETOWN | 4000102522 | GRT32.0000.00171 | CRTD ESTC CSER MANC PRC SKKP | PLN ADJ | MAI | 556155.87 | 0 | 2026-04-29 | 2026-04-29 |  |  | U126783
2623 |  | GRT-Ball Homes Old Oxford P4-Georgetown | 4000103017 | GRT32.0000.00172 | CRTD ESTC MANC NTUP PRC SKKP | PLN ADJ | MAI | 489395.77 | 0 | 2026-05-08 | 2026-05-08 |  |  | U126783
2621 |  | ANC-ROSALIE HP SMRP-LEXINGTON | 4000085778 | ANC32.0000.00307 | REL ESTC MANC PRC SETC | NEW NSFS WENG | MAI | 2482476.25 | 5022.1 | 2026-10-31 | 2027-12-31 |  |  | U127466
2621 |  | ANC - NEWCIRCLELEAK - LEXINGTON | 4000087349 | ANC32.0000.00320 | REL PCNF ESTC GMPS MANC PRC SETC | NEW FCMP | MAI | 163562.32 | 486838.19 | 2025-08-06 | 2025-08-06 | 2026-03-04 | 2026-12-31 | U127466
2621 |  | 2621-TRAFTON SMRP-LEXINGTON | 4000088149 | ANC32.0000.00017 | CRTD MANC NTUP PRC | EST | MAI | 44.58 | 0 | 2025-08-18 | 2025-08-18 |  |  | U127466
2621 |  | 2621-ST THERESA ABN - EMER - LEXINGTON | 4000088152 | ANC32.0000.00252 | CRTD MANC NTUP PRC | EST | MAI | 44.58 | 0 | 2025-08-18 | 2025-08-18 |  |  | U127466
2621 |  | REG STATION 1073 OUTLET VALVE INSTALL - | 4000088155 | BET32.0000.00052 | REL ESTC GMPS MANC PRC SETC | NPRG ADJ FCMP | MAI | 38183.75 | 88181.36 | 2025-08-18 | 2025-08-18 |  |  | U127466
2621 |  | 2621 - STA 1073 VALVE REP - LEXINGTON | 4000088181 | BET32.0000.00052 | CRTD MANC PRC | EST | STA | 708.84 | 0 | 2025-08-18 | 2025-08-18 |  |  | U127466
2623 |  | 2623 - SOARDS RD ENCROACHMENT PSI GTOWN | 4000088324 | PSI32.0000.00048 | REL ESTC MACM PRC SETC | NEW | PSI | 1.2 | 8831 | 2025-08-19 | 2025-08-19 |  |  | U127466
2621 |  | ANC - JONES CREEK SMRP - LEXINGTON | 4000088361 | ANC32.0000.00336 | REL ESTC MANC PRC SETC | NEW NSFS WENG WENV | MAI | 399961.11 | 13773.58 | 2025-08-19 | 2025-08-19 |  |  | U127466
2621 |  | BET2621 - UK WEST BETTERMENT - LEXINGTON | 4000091870 | GRT32.0000.00097 | REL PCNF ESTC GMPS MANC PRC SETC SKKP | NPRG ADJ FCMP | MAI | 769.08 | 838100.89 | 2025-10-13 | 2025-10-13 | 2025-10-28 |  | U127466
2623 |  | ANC-CLEVELAND AVE. SMRP - VERSAILLES | 4000092292 | ANC32.0000.00330 | REL PCNF ESTC GMPS MANC PRC SETC | NPRG MIFE | MAI | 202788.23 | 2324364.56 | 2025-10-21 | 2025-10-21 | 2026-03-13 | 2026-12-31 | U127466
2621 |  | ANC-SAINT ANN SMRP 2026 - IDLE HOUR FINA | 4000092297 | ANC32.0000.00333 | REL PCNF ESTC GMPS MANC PRC SETC | NEW MIFE | MAI | 209584.94 | 529467.29 | 2025-10-21 | 2025-10-21 | 2026-03-04 | 2026-12-31 | U127466
2621 |  | ANC-DOVER ROAD SMRP-LEX | 4000095269 | ANC32.0000.00331 | REL ESTC MANC PRC SETC | NEW NSFS WENG | MAI | 10.34 | 10776.81 | 2026-10-31 | 2027-12-31 |  |  | U127466
2621 |  | ANC-SOUTHLAND DRIVE HP -LEXINGTON | 4000095936 | ANC32.0000.00343 | REL ESTC MANC PRC SETC | NEW NSFS | MAI | 1879 | 8788.26 | 2026-07-01 | 2026-12-31 |  |  | U127466
2621 |  | INSTALL 200' - 8" PMLP | 4000095938 | ANC32.0000.00344 | REL ESTC MANC PRC SETC | NEW NSFS | MAI | 26.65 | 10713.28 | 2026-10-31 | 2027-12-31 |  |  | U127466
2621 |  | 2621 - ANC - THIRD ST LEAK SMRP - LEX | 4000095939 | ANC32.0000.00344 | CRTD MANC NTUP PRC | EST | MAI | 2.41 | 0 | 2026-01-08 | 2026-01-08 |  |  | U127466
2623 |  | PIG - HOLMES ST RELOCATION - FRANKFORT | 4000095961 | PIG32.0000.00066 | REL ESTC MACM PRC SETC | SCHD NSFS WENG | MAI | 3.31 | 23116.8 | 2026-01-08 | 2026-01-08 |  | 2026-12-31 | U127466
2621 |  | ANC - LIBERTY HGTS SMRP - LEX | 4000095962 | ANC32.0000.00345 | CRTD MANC NTUP PRC | NEW ADJ NSFS | MAI | 4.71 | 0 | 2026-10-31 | 2027-12-31 |  |  | U127466
2621 |  | ANC - CULPEPPER SMRP - LEX | 4000095963 | ANC32.0000.00346 | REL MANC PRC SETC | NEW ADJ NSFS | MAI | 4.71 | 0 | 2026-10-31 | 2027-12-31 |  |  | U127466
2621 |  | ANC - SUBURBAN CT SMRP - LEX | 4000095964 | ANC32.0000.00347 | REL MANC PRC SETC | NEW NSFS | MAI | 4.71 | 5118.27 | 2026-10-31 | 2027-12-31 |  |  | U127466
2621 |  | ANC - LEGENDS LN SMRP - LEX | 4000095965 | ANC32.0000.00348 | REL MANC PRC SETC | NEW NSFS | MAI | 4.71 | 7753.86 | 2026-10-31 | 2027-12-31 |  |  | U127466
2621 |  | 2621 - ANC - MAXWELL DOWNTOWN SMRP - LEX | 4000095966 |  | CRTD MANC NTUP PRC | EST | MAI | 2.41 | 0 | 2026-01-08 | 2026-01-08 |  |  | U127466
2621 |  | ANC - BON AIR SMRP - LEX | 4000095967 | ANC32.0000.00350 | REL MANC PRC SETC | NEW NSFS | MAI | 4.71 | 4655.1 | 2026-10-31 | 2027-12-31 |  |  | U127466
2621 |  | ANC - ROBIN RD GLENDOVER SMRP - LEX | 4000095968 | ANC32.0000.00351 | REL MANC PRC SETC | NEW ADJ NSFS | MAI | 4.71 | 0 | 2026-10-31 | 2027-12-31 |  |  | U127466
2621 |  | ANC - DEERHAVEN HP SMRP - LEX | 4000095969 | ANC32.0000.00352 | REL ESTC MANC PRC SETC | NEW NSFS | MAI | 1.93 | 1697.73 | 2026-10-31 | 2027-12-31 |  |  | U127466
2621 |  | 2621 - ANC - LEXINGTON IBHP REP PH1 - LE | 4000095970 | ANC32.0000.00353 | REL ESTC MACM PRC SETC | NEW NSFS | MAI | 533.84 | 33713.41 | 2026-01-08 | 2026-01-08 |  |  | U127466
2621 |  | ANC - FAIRFIELD LEAK SMRP - LEX | 4000095971 | ANC32.0000.00354 | REL ESTC MANC PRC SETC | NEW NSFS | MAI | 4.71 | 6880.34 | 2026-10-31 | 2027-12-31 |  |  | U127466
2621 |  | ANC - PRICE RD TRLR PK SMRP - LEX | 4000095972 | ANC32.0000.00355 | REL MANC PRC SETC | NEW NSFS | MAI | 3.31 | 1018.5 | 2026-10-31 | 2027-12-31 |  |  | U127466
2621 |  | GRT - LUCILLE DR MLE - LEX | 4000097883 | GRT32.0000.00159 | REL PCNF ESTC GMPS MANC PRC SETC | NPRG ADFR FCMP | MAI | 235026.11 | 89202.77 | 2026-03-03 | 2026-03-25 | 2026-03-09 |  | U127466
2621 |  | PIG-UK PATIENT CARE HP/MP RELO-LEXINGTON | 4000101430 | PIG32.0000.00075 | REL MANC PRC SETC | NEW NSFS | MAI | 1518.69 | 0 | 2026-10-31 | 2027-05-01 |  |  | U127466
2629 |  | 2629-Patsy Way MLE-Mt Sterling | 4000085472 | GRT32.0000.00118 | REL ESTC GMPS MANC PRC SETC | NPRG ADJ | MAI | 26720.71 | 23675.7 | 2025-07-31 | 2025-10-30 |  | 2025-10-31 | U128885
2629 |  | 2629-S Highland Relocation-Winchester | 4000087344 | PIG32.0000.00055 | CRTD ESTC MANC NTUP PRC | PLN ADJ REIM | MAI | 34563.32 | 0 | 2025-08-06 | 2025-09-13 |  | 2025-09-15 | U128885
2629 | WINCHESTER | 2629-Deer Lawn MLE-Winchester | 4000087556 | GRT32.0000.00127 | CRTD ESTC MANC NTUP PRC | PLN ADJ WENG | MAI | 93130.66 | 0 | 2026-04-21 | 2026-08-31 |  |  | U128885
2629 |  | 2629-EMER 499 Indian mound-Mt Sterling | 4000088098 | ANC32.0000.00317 | REL ESTC MACM PRC SETC SKKP | NEW | MAI | 2723.68 | 0 | 2025-08-15 | 2025-12-31 |  |  | U128885
2621 |  | SMRP-Castlewood Dr-Lexington.. | 4000088170 | ANC32.0000.00199 | REL ESTC MACM PRC SETC SKKP | NEW | MAI | 336560.8 | 0 | 2025-08-18 | 2025-12-31 |  |  | U128885
2621 |  | 2621-Ball Homes Masterson Hills-Lex.. | 4000088260 | GRT32.0000.00122 | REL ESTC MACM PRC SETC | NEW | MAI | 35331.68 | 0 | 2025-08-18 | 2025-08-18 |  |  | U128885
2621 |  | 2621-Quintana Estates MLE-Lexington WMS. | 4000088317 | GRT32.0000.00130 | REL PCNF ESTC GMPS MANC PRC SETC SKKP | SCHD FCMP | MAI | 163229.55 | 119825.18 | 2025-09-17 | 2025-11-14 | 2025-10-06 | 2025-11-14 | U128885
2629 |  | GRT-Boones Crossing MLE-Winchester | 4000090868 | GRT32.0000.00141 | REL ESTC MANC PRC SETC SKKP | NEW NSFS WENG WLND WPMT WSTR | MAI | 377533.57 | 31474.64 | 2026-04-30 | 2026-07-31 |  | 2026-07-31 | U128885
2629 |  | ANC-SMRP Broadway Av P2-Cynthiana | 4000090920 | ANC32.0000.00327 | CRTD MANC NTUP PRC SKKP | NEW REV | MAI | 285883.65 | 0 | 2026-01-01 | 2026-12-31 |  | 2026-12-31 | U128885
2629 |  | ANC-SMRP W Lexington Av-Winchester | 4000090923 | ANC32.0000.00328 | REL MANC PRC SETC | NEW ADJ NSFS RCFO WLND WPMT | MAI | 4461116.06 | 27114.24 | 2026-05-06 | 2027-12-31 |  | 2027-12-31 | U128885
2629 |  | ANC-SMRP Evergreen Dr-Irvine | 4000090925 | ANC32.0000.00329 | REL PCNF GMPS MANC PRC SETC | SCHD | MAI | 2413451.55 | 1422468.38 | 2026-01-01 | 2026-12-31 | 2026-03-23 | 2027-12-31 | U128885
2629 |  | ANC-SMRP Regan Dr-Winchester | 4000092090 | ANC32.0000.00338 | REL PCNF GMPS MANC PRC SETC | NPRG ADJ | MAI | 507048.2 | 24071.55 | 2026-01-01 | 2026-12-31 | 2026-05-18 | 2026-12-31 | U128885
2629 | RICHMOND | BET-Boone Village Topworks-Richmond | 4000093519 | BET32.0000.00061 | CRTD MANC NMAT NTUP PRC | EST WENG | STA | 0 | 0 | 2025-11-13 | 2026-12-31 |  | 2026-12-31 | U128885
2629 | PARIS | 2629-Clintonville POD Meter-Paris | 4000095315 | BET32.0000.00062 | CRTD MANC NMAT NTUP PRC | EST WENG | STA | 0 | 0 | 2026-05-01 | 2026-05-29 |  |  | U128885
2629 |  | ANC-SMRP Broadway Av P2-Cynthiana | 4000095394 | ANC32.0000.00327 | REL PCNF ESTC GMPS MANC PRC SETC SKKP | NPRG ADJ MIFE | MAI | 2639748.16 | 2510760.62 | 2025-12-29 | 2026-10-02 | 2026-03-12 | 2026-10-02 | U128885
2629 |  | GRT-College Hill Estates MLE-Waco | 4000096101 | GRT32.0000.00155 | CRTD ESTC MANC NTUP PRC | PLN ADJ WENG | MAI | 288392.89 | 0 | 2026-04-21 | 2026-10-31 |  |  | U128885
2629 |  | ANC-SMRP Lola Dr-Cynthiana | 4000096900 | ANC32.0000.00374 | CRTD MANC PRC | EST CAN WLND | MAI | 54967.84 | 0 | 2027-01-01 | 2027-12-31 |  | 2028-12-31 | U128885
2629 |  | ANC-SMRP Franklin Ave-Winchester | 4000096978 | ANC32.0000.00363 | CRTD MANC NMAT NTUP PRC | EST CAN | MAI | 0 | 0 | 2026-10-31 | 2027-12-31 |  |  | U128885
2629 |  | GRT-Mt Sterling Rd Development-Wincheste | 4000097611 | GRT32.0000.00157 | CRTD ESTC CSER MANC PRC SKKP | PLN ADJ WENG | MAI | 1145544.29 | 0 | 2026-08-01 | 2026-12-31 |  |  | U128885
2629 |  | PIG-Stone Trace Dr Relo-Mt Sterling | 4000097800 | PIG32.0000.00068 | CRTD ESTC MANC NTUP PRC | PLN REIM | MAI | 61025.06 | 0 | 2026-02-10 | 2026-04-30 |  | 2026-04-30 | U128885
2629 |  | GRT-Harrison Cty HS & ATC MLE-Cynthiana | 4000098573 | GRT32.0000.00021 | CRTD MANC NTUP PRC SKKP | PLN ADJ WENG | MAI | 93492.19 | 0 | 2026-04-21 | 2026-10-31 |  |  | U128885
2629 |  | GRT-Colby Rd Development MLE-Winchester | 4000099022 | GRT32.0000.00162 | REL ESTC MACM PRC SETC SKKP | NEW ADJ NSFS | MAI | 123656.17 | 1032.61 | 2026-08-01 | 2026-08-31 |  | 2026-08-31 | U128885
2629 | Mount Sterling | GRT-Countryside Dr MLE-Mt Sterling | 4000099212 | GRT32.0000.00163 | CRTD ESTC MANC NTUP PRC | PLN CAN | MAI | 315961.06 | 0 | 2026-03-06 | 2026-03-13 |  |  | U128885
2629 |  | ANC-SMRP Lola Dr-Cynthiana | 4000100818 | ANC32.0000.00374 | REL ESTC MANC PRC SETC SKKP | NEW ADJ NSFS WENG WLND | MAI | 2724583.25 | 0 | 2026-10-31 | 2027-12-31 |  | 2027-12-31 | U128885
2629 |  | ANC-SMRP Franklin Ave-Winchester | 4000100876 | ANC32.0000.00363 | REL ESTC MANC PRC SETC SKKP | NEW ADJ NSFS WENV WLND | MAI | 2477250.83 | 257.9 | 2026-10-31 | 2027-12-31 |  |  | U128885
2629 |  | BET-Vojecaro POD Retirement-Winchester | 4000101069 | BET32.0000.00065 | CRTD ESTC CSER MANC PRC SKKP | PLN | MAI | 482621.43 | 0 | 2026-04-02 | 2028-12-31 |  | 2028-12-31 | U128885
2629 |  | Design for CU Tab | 4000101075 |  | CRTD MANC NMAT NTUP PRC | EST | PSI | 0 | 0 | 2026-04-02 | 2026-04-02 |  |  | U128885
2631 |  | ANC-SMRP Huckleberry St-Catlettsburg | 4000101746 | ANC32.0000.00388 | CRTD MANC NMAT NTUP PRC | EST | MAI | 42719.04 | 0 | 2026-10-31 | 2027-12-31 |  |  | U128885
|  | BET-Rolling Hills POD-Winchester | 4000102399 |  | CRTD MANC NMAT NTUP PRC | EST WENG | STA | 0 | 0 | 2026-04-28 | 2030-12-31 |  |  | U128885
2629 |  | GRT-Mcclure Rd Betterment-Winchester | 4000103310 | GRT32.0000.00141 | CRTD MANC PRC | EST | MAI | 120214.83 | 0 | 2026-05-14 | 2026-12-31 |  |  | U128885
2629 | WINCHESTER | ANC-Mutual Ave Land ABN-Winchester | 4100801141 | ANC32.0000.00326 | REL ESTC MACM PRC SETC | NEW | LND | 12527.5 | 10389.92 | 2025-09-19 | 2025-12-31 |  | 2025-12-31 | U128885
2629 |  | ANC-SMRP Broadway Av P2 Land-Cynthiana | 4100828092 | ANC32.0000.00327 | REL ESTC MACM PRC SETC | NEW | LND | 6263.7 | 750 | 2026-01-05 | 2026-12-31 |  | 2026-12-31 | U128885
2623 | GEORGETOWN | MOVE METER/4100776679 | 4100795172 | GRT32.0002.00001 | CRTD MANC NMAT NTUP PRC | EST | MAI | 0 | 0 | 2025-09-02 | 2026-07-29 |  | 2026-08-28 | U132386
2623 |  | ANC - Cardinal Ave SMRP | 4000085542 | ANC32.0000.00308 | REL PCNF ESTC MANC PRC SETC | NEW ADJ | MAI | 3326316 | 2904.09 | 2026-10-31 | 2027-12-31 | 2026-03-04 |  | U132703
2623 |  | ANC-CAPITOL AVE SMRP-FRANKFORT | 4000085545 | ANC32.0000.00305 | REL ESTC GMPS MANC PRC SETC SKKP | NEW ADJ | MAI | 871145.84 | 7694.5 | 2026-07-08 | 2026-12-31 |  | 2026-12-31 | U132703
2621 |  | Design for CU Tab | 4000086376 |  | CRTD MANC NMAT NTUP PRC | EST | PSI | 0 | 0 | 2025-07-23 | 2025-07-23 |  |  | U132703
2621 |  | RELOCATION - ARMSTRONG MILL RD | 4000086377 | ANC32.0000.00310 | CRTD MANC NMAT PRC | NEW CAN NSFS RCFO | MAI | 0 | 0 | 2025-12-30 | 2025-12-31 |  | 2025-12-31 | U132703
2621 |  | RELOCATION - ARMSTRONG MILL RD | 4000086378 | ANC32.0000.00310 | CRTD MANC NMAT PRC | NEW CAN NSFS RCFO | MAI | 0 | 0 | 2025-12-30 | 2025-12-31 |  | 2025-12-31 | U132703
2621 |  | RELOCATION - ARMSTRONG MILL RD | 4000086379 | ANC32.0000.00310 | CRTD MANC NMAT PRC | PLN CAN NSFS RCFO | MAI | 0 | 0 | 2025-12-30 | 2025-12-31 |  | 2025-12-31 | U132703
2621 |  | RELOCATION - ARMSTRONG MILL RD | 4000086387 | ANC32.0000.00310 | CRTD MANC NMAT PRC | NEW CAN NSFS RCFO | MAI | 0 | 0 | 2025-12-30 | 2025-12-31 |  | 2025-12-31 | U132703
2621 |  | RELOCATION - ARMSTRONG MILL RD | 4000086388 | ANC32.0000.00310 | CRTD MANC NMAT PRC | NEW CAN NSFS RCFO | MAI | 0 | 0 | 2025-12-30 | 2025-12-31 |  | 2025-12-31 | U132703
2621 |  | Design for CU Tab | 4000086389 |  | CRTD MANC NMAT NTUP PRC | EST | PSI | 0 | 0 | 2025-07-24 | 2025-07-24 |  |  | U132703
2621 |  | RELOCATION - ARMSTRONG MILL RD | 4000086390 | ANC32.0000.00310 | CRTD MANC NMAT PRC | NEW CAN NSFS RCFO | MAI | 0 | 0 | 2025-12-30 | 2025-12-31 |  | 2025-12-31 | U132703
2621 |  | RELOCATION - ARMSTRONG MILL RD | 4000086391 | ANC32.0000.00310 | CRTD MANC NMAT PRC | NEW CAN NSFS RCFO | MAI | 0 | 0 | 2025-12-30 | 2025-12-31 |  | 2025-12-31 | U132703
2621 |  | ARMSTRONG MILL RELO | 4000086395 | ANC32.0000.00319 | REL MANC PRC SETC | NEW RCFO | MAI | 59157.42 | 1212.65 | 2025-12-30 | 2025-12-31 |  | 2026-12-31 | U132703
2623 |  | CNV-24026341700 INVESTIGATE ROW/EASEMENT | 4000086426 | ANC32.0000.00310 | CRTD MANC NMAT PRC | NEW CAN NSFS RCFO | MAI | 0 | 0 | 2026-12-31 | 2026-12-31 |  | 2026-12-31 | U132703
2623 |  | Design for CU Tab | 4000086437 |  | CRTD MANC NMAT NTUP PRC | EST | PSI | 0 | 0 | 2025-07-24 | 2025-07-24 |  |  | U132703
2623 |  | ANC - MAIN ST HP - FRANKFORT (JIM BEAM) | 4000086454 | ANC32.0000.00310 | REL MANC NMAT PRC SETC | NEW CAN NSFS RCFO | MAI | 0 | 2379.02 | 2026-10-31 | 2027-12-31 |  |  | U132703
2623 |  | ANC - E College St SMRP | 4000086464 | ANC32.0000.00312 | REL PCNF ESTC MANC PRC SETC | NEW ADJ | MAI | 3222324.31 | 409.28 | 2026-10-31 | 2027-12-31 | 2026-03-06 |  | U132703
2623 |  | ps & i for capitol ave | 4000088340 | PSI32.0000.00045 | CRTD MANC NMAT NTUP PRC | EST CAN | PSI | 0 | 0 | 2025-08-19 | 2025-08-19 |  |  | U132703
2623 |  | CARDINAL AVE SMRP | 4000088395 | PSI32.0000.00047 | CRTD MANC NMAT NTUP PRC | EST CAN | PSI | 0 | 0 | 2025-08-19 | 2025-08-19 |  |  | U132703
2623 |  | E COLLEGE ST - SMRP | 4000088396 | PSI32.0000.00046 | CRTD MANC NMAT NTUP PRC | EST CAN | PSI | 0 | 0 | 2025-08-19 | 2025-08-19 |  |  | U132703
2623 |  | SMRP -PAUL SAWYIER DR | 4000090540 | ANC32.0000.00322 | REL ESTC GMPS MANC PRC SETC | SCHD ADJ | MAI | 452957.48 | 862363.9 | 2025-09-17 | 2025-09-17 |  | 2026-03-13 | U132703
2623 |  | ANC-GOVERNORS MANSION SMRP-FRANKFORT | 4000090547 | ANC32.0000.00323 | REL ESTC MANC PRC SETC SKKP | NEW ADJ | MAI | 279264.65 | 3332.41 | 2025-09-17 | 2025-09-17 |  | 2026-12-31 | U132703
2621 |  | PIG - ARMSTRONG MILL | 4000096152 | PIG32.0000.00061 | REL ESTC CSER MANC PRC SETC | NEW ADJ | MAI | 162362.04 | 10.42 | 2026-02-02 | 2026-02-02 |  | 2026-10-30 | U132703
2623 |  | ANC - E MAIN ST GEO SMRP | 4000097442 | ANC32.0000.00365 | REL ESTC MANC PRC SETC | NEW WLND | MAI | 294394.2 | 1269.21 | 2026-10-31 | 2027-12-31 |  |  | U132703
2623 |  | ANC - NE 4TH ST FRA SMRP | 4000097443 | ANC32.0000.00366 | REL ESTC MANC PRC SETC | NEW WLND | MAI | 1849.2 | 5693.21 | 2026-10-31 | 2027-12-31 |  |  | U132703
2623 |  | ANC - SE 4TH ST FRA SMRP | 4000097444 | ANC32.0000.00367 | REL ESTC MANC PRC SETC | NEW WLND | MAI | 2596.3 | 1896 | 2026-10-31 | 2027-12-31 |  |  | U132703
2623 |  | ANC - PINEHURST DR FRA SMRP | 4000097447 | ANC32.0000.00368 | CRTD ESTC MANC NTUP PRC | NEW WLND | MAI | 1291 | 0 | 2026-10-31 | 2027-12-31 |  |  | U132703
2623 |  | ANC - WINDING WAY DR FRA SMRP | 4000097448 | ANC32.0000.00369 | CRTD MANC NTUP PRC | NEW WLND | MAI | 1291 | 0 | 2026-10-31 | 2027-12-31 |  |  | U132703
2623 |  | ANC - CLIFTON RD FRA SMRP | 4000097450 | ANC32.0000.00370 | CRTD ESTC MANC NTUP PRC | NEW WLND | MAI | 2596.3 | 0 | 2026-10-31 | 2027-12-31 |  |  | U132703
2623 |  | ANC - ELM ST VER SMRP | 4000097453 | ANC32.0000.00371 | CRTD ESTC MANC NTUP PRC | NEW WLND | MAI | 2596.3 | 0 | 2026-10-31 | 2027-12-31 |  |  | U132703
2623 |  | ANC - PAYNES MILL RD VER SMRP | 4000097455 | ANC32.0000.00372 | REL ESTC MANC PRC SETC | NEW WLND | MAI | 1857.3 | 0 | 2026-10-31 | 2027-12-31 |  |  | U132703
2623 | FRANKFORT | STA - Station Upgrade | 4000100505 | ANC32.0000.00058 | REL ESTC CSER MANC PRC SETC | NEW ADJ | STA | 41296.74 | 5.21 | 2026-03-31 | 2026-03-31 |  |  | U132703
2621 |  | GRT-Rocky Mountain Cir MLE - Lex | 4000101699 | GRT32.0000.00174 | CRTD MANC NTUP PRC | EST WENG | MAI | 2.2 | 0 | 2026-04-14 | 2026-07-30 |  |  | U132703
2629 | MOUNT STERLING | Maintenance of Main / Check CP low read | 4100807913 | ANC32.0002.00006 | REL ESTC MANC NMAT PRC SETC | NPRG FCMP MIFE | MAI | 518.07 | 2086.74 | 2025-10-23 | 2026-10-18 |  | 2027-01-16 | U133262
2629 | CYNTHIANA | Remediate Test Point Issues | 4100809328 | ANC32.0002.00006 | REL MANC NMAT PRC SETC | NPRG FCMP | MAI | 518.07 | 2775.65 | 2025-10-29 | 2026-10-24 |  | 2027-01-22 | U133262
2629 | CYNTHIANA | Remediate Test Point Issues | 4100809572 | ANC32.0002.00006 | CRTD MANC NMAT NTUP PRC | NEW CAN | MAI | 0 | 0 | 2025-10-30 | 2026-10-25 |  | 2027-01-23 | U133262
2623 |  | Cutover Validation Overhead KY - RHARDEN | 4000082774 | ANC32.0000.00001 | CRTD ESTC MANC NTUP PRC SKKP | PLN CAN | MAI | 40840.9 | 0 | 2025-09-02 | 2025-11-29 |  | 2025-11-29 | U134232
2631 |  | Mavity Odorant Injection Point Replaceme | 4000085987 | ANC32.0000.00306 | REL ESTC MACM PRC SETC | NEW MIFE NSFS | MAI | 1.67 | 0 | 2025-07-16 | 2025-07-16 |  |  | U136909
2629 |  | S BURNS RS RETIREMENT, PREMISE 200449 | 4000091436 | ANC32.0000.00170 | CRTD MANC NTUP PRC | EST NSFS | STA | 185.09 | 0 | 2025-10-03 | 2025-10-03 |  |  | U137440
2621 |  | ANC-Narows Subsidence-Narrows | 4000091653 | ANC38.0000.00513 | REL PCNF ESTC GMPS MANC PRC SETC | SCHD ADJ | MAI | 91485.93 | 2637.75 | 2026-06-01 | 2026-09-01 | 2026-05-26 |  | U139606
2631 |  | Replace Coalton Rectifier - 25026408100 | 4000086412 | ANC32.0000.00311 | TECO ESTC MANC PRC SETC | NPRG ADJ FCMP MIFE | MAI | 5858.32 | 1714.45 | 2025-07-24 | 2025-10-24 |  |  | U141016
2629 |  | 2629 - 325 SANDE RIDGE LN - MT. STERLING | 4000086733 | PIG32.0000.00051 | REL ESTC GMPS MANC PRC SETC | COCO FCMP | MAI | 37169.36 | 28187.08 | 2025-07-28 | 2025-10-28 |  | 2025-10-28 | U141016
2631 | ASHLAND | GRT - 2804 PLEASANT AVE MLE - ASHLAND | 4000086902 | GRT32.0000.00120 | REL ESTC GMPS MANC PRC SETC | SCHD FCMP | MAI | 30420.98 | 217321.22 | 2025-10-01 | 2025-10-31 |  | 2025-10-31 | U141016
2621 |  | GRT - PALOMAR FOUNTAINS MLE - LEXINGTON | 4000087395 | GRT32.0000.00124 | REL PCNF ESTC GMPS MANC PRC SETC | NPRG ADJ | MAI | 102007.66 | 101406.76 | 2025-09-02 | 2025-12-31 | 2026-04-13 | 2026-05-01 | U141016
2621 |  | UK DORM WOODLAND | 4000087397 | GRT32.0000.00125 | TECO ESTC GMPS JBFI MANC PRC SETC | SCHD ADJ FCMP | MAI | 61809.85 | 35464.16 | 2025-08-06 | 2025-08-30 |  |  | U141016
2631 |  | ANC - SMRP RIDGEWAY DRIVE - ASHLAND | 4000087673 | ANC32.0000.00304 | REL PCNF ESTC GMPS MANC PPRT PRC SETC | SCHD | MAI | 612331.21 | 934464.53 | 2025-08-12 | 2026-12-31 | 2026-03-12 |  | U141016
2631 |  | ANC - SMRP RAILROAD STREET - RUSSELL | 4000087675 | ANC32.0000.00314 | REL ESTC MANC PRC SETC | NEW NSFS | MAI | 10240.24 | 10181.72 | 2025-08-12 | 2026-12-31 |  |  | U141016
2629 |  | SANDE RIDGE RELOCATION | 4000088349 | PSI32.0000.00049 | REL ESTC MACM PRC SETC | NEW CAN FCMP NSFS | PSI | 4694.82 | 0 | 2025-08-19 | 2025-11-30 |  |  | U141016
2621 |  | RE-CREATE UK DORM WOODLAND JO | 4000088355 | GRT32.0000.00125 | REL MACM PRC SETC | NEW NSFS | MAI | 65702.01 | 0 | 2025-08-19 | 2025-08-19 |  |  | U141016
2631 |  | BRUCE DRIVE WO RE-CREATE FOR ACCOUNTING | 4000088357 | ANC32.0000.00318 | CRTD MANC PRC | EST | MAI | 0.59 | 0 | 2025-08-19 | 2025-08-19 |  |  | U141016
2631 | Wurtland | 2631 - 206 Jacobs Ln - Wurtland | 4000088502 | GRT32.0000.00132 | CRTD ESTC MANC PRC | PLN ADJ CAN NSFS WENG | MAI | 36503.51 | 0 | 2025-08-20 | 2025-11-01 |  |  | U141016
2621 |  | GRT - CARRIAGE LN MLE - LEXINGTON | 4000088552 | GRT32.0000.00131 | REL ESTC GMPS MANC PRC SETC | COCO FCMP | MAI | 495629.82 | 357427.11 | 2025-10-01 | 2025-12-31 |  | 2025-12-31 | U141016
2621 |  | 2621-LAND RENEW LEASE AGREEMENT (200103) | 4000089074 | PSI32.0000.00050 | REL ESTC MACM PRC SETC | NEW NSFS | PSI | 30810.1 | 18091.32 | 2025-08-29 | 2025-12-31 |  |  | U141016
2629 |  | Design for CU Tab | 4000090027 |  | CRTD MANC NMAT NTUP PRC | EST | PSI | 0 | 0 | 2025-09-09 | 2025-09-09 |  |  | U141016
2629 |  | SANDE RIDGE RELOCATION | 4000090053 | PIG32.0000.00051 | CRTD MANC PRC | NEW NSFS RCFO | MAI | 4694.82 | 0 | 2025-08-19 | 2025-11-30 |  |  | U141016
2631 |  | GRT - 2029 FERN DR MLE - LOUISA | 4000090832 | GRT32.0000.00139 | REL ESTC GMPS JBFI MANC PRC SETC | NPRG FCMP | MAI | 31131.04 | 13372.78 | 2025-12-01 | 2025-12-10 |  | 2025-12-10 | U141016
2631 | Russell | GRT - 124 AUDOBON CT MLE - RUSSELL | 4000090908 | GRT32.0000.00140 | TECO PCNF ESTC GMPS MANC PRC SETC SKKP | SCHD FCMP | MAI | 46515.12 | 72150.8 | 2026-02-25 | 2026-03-09 | 2026-02-13 | 2026-03-09 | U141016
2621 | LEXINGTON | GRT-TURNER COMMONS MLE-LEXINGTON | 4000092674 | GRT32.0000.00145 | REL ESTC GMPS MANC PRC PRTB SETC SKKP | NPRG | MAI | 81269.6 | 133757.7 | 2025-10-28 | 2025-12-01 |  |  | U141016
2631 |  | GRT-206 JACOBS LN MLE-WURTLAND | 4000093040 | GRT32.0000.00132 | REL ESTC GMPS MANC PRC SETC | NPRG FCMP | MAI | 33358.89 | 31397.95 | 2026-01-12 | 2026-01-31 |  |  | U141016
2621 |  | GRT-LEGACY BUSINESS PARK MLE-LEXINGTON | 4000093541 | GRT32.0000.00148 | REL ESTC MACM PRC SETC SKKP | NEW WENG WLND | MAI | 922940.88 | 0 | 2026-04-21 | 2026-11-07 |  |  | U141016
2631 |  | ANC-ROBERTS DRIVE CASING-ASHLAND | 4000093713 | ANC32.0000.00340 | CRTD MANC NMAT NTUP PRC | EST | MAI | 0 | 0 | 2026-07-01 | 2026-07-18 |  | 2026-07-18 | U141016
2621 | LEXINGTON | GRT - SPRINGS AT POLO CLUB - LEXINGTON | 4000093774 | GRT32.0000.00149 | REL PCNF ESTC CSER GMPS MANC PRC SETC | COCO FCMP | MAI | 48540.19 | 73287.2 | 2026-03-23 | 2026-04-20 | 2026-03-25 | 2026-04-20 | U141016
2621 |  | CNV-25026392200 DESIGN CONFLICT RELOCATI | 4000093964 | GRT32.0000.00130 | REL NMAT PRC SETC | NEW NSFS RCFO | MAI | 0 | 0 | 2025-04-30 | 2025-04-30 |  | 2025-05-01 | U141016
2629 |  | SANDE RIDGE RELOCATION | 4000093966 | PIG32.0000.00051 | CRTD MANC PRC | NEW NSFS RCFO | MAI | 4694.82 | 0 | 2025-08-19 | 2025-11-30 |  |  | U141016
2631 |  | GRT-BOURBON STREET MLE-GREENUP | 4000095213 | GRT32.0000.00152 | CRTD ESTC MANC NTUP PRC | PLN NSFS | MAI | 658417.65 | 0 | 2026-12-31 | 2026-12-31 |  |  | U141016
2631 | ASHLAND | GRT-STARBUCKS CAMP LANDING-ASHLAND | 4000095261 | GRT32.0000.00153 | CRTD MANC PRC | EST | MAI | 4603.7 | 0 | 2026-01-24 | 2026-01-30 |  |  | U141016
2631 |  | GRT - 995 FERN DR MLE - LOUISA | 4000095304 | GRT32.0000.00154 | CRTD ESTC MANC NTUP PRC | PLN CAN WENG | MAI | 32209.98 | 0 | 2026-06-04 | 2026-06-11 |  |  | U141016
2631 |  | EMER-10th Street-Catlettsburg RECREATE | 4000095766 | ANC32.0000.00339 | REL ESTC MACM PRC SETC SKKP | NEW | MAI | 121797.85 | 0 | 2025-10-24 | 2025-10-25 |  |  | U141016
2631 |  | ANC - SMRP CHINN STREET - ASHLAND | 4000096262 | ANC32.0000.00358 | REL PCNF ESTC GMPS MANC PRC SETC SKKP | SCHD | MAI | 1005995.84 | 175352.31 | 2026-04-02 | 2027-12-31 | 2026-04-07 |  | U141016
2631 |  | ANC-SMRP BSHP SOUTHPOINT-ASHLAND | 4000096778 | ANC32.0000.00359 | CRTD ESTC MANC NTUP PRC | PLN NSFS | MAI | 14860.02 | 0 | 2026-10-31 | 2027-12-31 |  |  | U141016
2631 |  | ANC-BEVERLY BLVD SMRP-ASHLAND | 4000096838 | ANC32.0000.00360 | CRTD ESTC MANC NTUP PRC | PLN NSFS | MAI | 14860.02 | 0 | 2026-10-31 | 2027-12-31 |  |  | U141016
2631 | GREENUP | GRT - ALICE STREET MLE-GREENUP | 4000097588 | GRT32.0000.00156 | CRTD ESTC MANC NTUP PRC | PLN NSFS | MAI | 49442.4 | 0 | 2026-03-18 | 2026-03-25 |  |  | U141016
2631 |  | GRT - SPRINGHAVEN ST MLE - CATLETTSBURG | 4000097946 | GRT32.0000.00160 | REL PCNF ESTC CSER GMPS MANC PRC SETC* | COCO FCMP | MAI | 25818.31 | 21189.24 | 2026-05-07 | 2026-05-15 | 2026-04-22 |  | U141016
2623 | GEORGETOWN | Toyota Line-Blowdown Valve C206A&B | 4000098635 | ANC32.0000.00357 | CRTD MANC NMAT NTUP PRC | EST WENG | MAI | 0 | 0 | 2027-01-01 | 2027-12-31 |  |  | U141016
2623 |  | Toyota Line-Blowdown Valve C-205A&B | 4000098789 | ANC32.0000.00357 | CRTD MANC NMAT NTUP PRC | EST WENG | MAI | 0 | 0 | 2027-01-01 | 2027-12-31 |  |  | U141016
2623 |  | Toyota Line-Blowdown Valve C203A&B | 4000098790 | ANC32.0000.00357 | CRTD MANC NMAT NTUP PRC | EST CAN WENG | MAI | 0 | 0 | 2027-01-01 | 2027-12-31 |  |  | U141016
2631 |  | ANC-SMRP BRAMBLE DR-CATLETTSBURG | 4000098859 | ANC32.0000.00381 | CRTD MANC NMAT NTUP PRC | EST CAN | MAI | 0 | 0 | 2027-01-01 | 2027-12-31 |  |  | U141016
2621 |  | PIG-LAKEWOOD DRIVE RELOC-LEXINGTON | 4000099056 | PIG32.0000.00070 | REL PCNF GMPS MANC PRC SETC | NPRG RCFO | MAI | 9977 | 36786.48 | 2025-06-30 | 2025-06-30 | 2026-05-12 | 2025-07-01 | U141016
2631 |  | ANC-BRAMBLE DR SMRP-CATLETTSBURG | 4000099985 | ANC32.0000.00381 | CRTD MANC NMAT NTUP PRC | EST | MAI | 0 | 0 | 2026-10-31 | 2027-12-31 |  |  | U141016
2631 |  | GRT-SOUTH OHIO MED CENTER MLE-RACELAND | 4000100519 | GRT32.0000.00166 | REL ESTC CSER GMPS MACM PRC SETC SKKP | NEW | MAI | 47565.64 | 886.74 | 2026-06-15 | 2026-06-25 |  |  | U141016
2631 |  | ANC-SOUTH OHIO MED CENTER BET-RACELAND | 4000100580 | GRT32.0000.00166 | CRTD ESTC CSER MANC NTUP PRC | PLN | MAI | 122201.95 | 0 | 2026-06-01 | 2026-06-25 |  |  | U141016
2631 |  | GRT - 41 TOWN HILL RD MLE - LOUISA | 4000101837 | GRT32.0000.00169 | CRTD ESTC CSER MANC PRC SKKP | PLN ADJ WENG | MAI | 49724.33 | 0 | 2026-06-16 | 2026-06-26 |  |  | U141016
2621 |  | GRT-1336 TANFORAN DR MLE-LEXINGTON | 4000103899 | GRT32.0000.00173 | CRTD ESTC MANC NTUP PRC | PLN NSFS WENG | MAI | 11147.6 | 0 | 2026-06-22 | 2026-06-26 |  |  | U141016
2629 |  | 325 SANDE RIDGE LN RELOC. 25026409100 | 4100780082 | PIG32.0000.00051 | CRTD MANC NMAT NTUP PRC | EST CAN | MAI | 0 | 0 | 2025-07-28 | 2025-10-28 |  |  | U141016
2621 |  | PSI-ALUMNI DRIVE PATH RELO-LEXINGTON | 4100832925 | PSI32.0000.00053 | REL ESTC GMPS MANC PRC SETC SKKP | NEW NSFS | PSI | 13106.22 | 21817.42 | 2026-01-15 | 2026-03-02 |  |  | U141016
2621 |  | IDLE HOUR PARK RECTIFIER | 4000086939 | ANC32.0000.00313 | CRTD ESTC MANC NTUP PRC | NEW ADJ REV | MAI | 151555.84 | 0 | 2025-07-30 | 2026-07-30 |  |  | U145347
2621 |  | BALL HOMES - MASTERSON HILLS MLE | 4000087198 | GRT32.0000.00122 | REL ESTC GMPS MANC PRC SETC | COCO ADJ FCMP | MAI | 68908.83 | 136154.07 | 2025-09-03 | 2025-10-18 |  | 2025-10-18 | U145347
2621 |  | GRT-BALL HOMES SUMMERFIELD-LEXINGTON | 4000087365 | GRT32.0000.00123 | CRTD ESTC MANC NTUP PRC RELR | NEW ADJ WENG | MAI | 39021.25 | 0 | 2025-12-17 | 2026-02-14 |  | 2026-02-14 | U145347
2621 |  | Georgetown Street Anode Bed Install | 4000090524 | ANC32.0000.00324 | CRTD ESTC MANC NTUP PRC | NEW ADJ | MAI | 4755.23 | 0 | 2025-09-17 | 2025-09-17 |  |  | U145347
2621 |  | PIG-BOBWHITE TRAIL RELOCATION-LEXINGTON | 4000093818 | PIG32.0000.00063 | REL PCNF PRT GMPS MANC PRC SETC SKKP | NPRG ADJ FCMP REIM | MAI | 7782.24 | -12902.79 | 2025-11-19 | 2026-01-31 | 2026-02-04 |  | U145347
2621 |  | GRT-THE SANCUARY MLE-(CANCELED) | 4000094269 | GRT32.0000.00151 | CRTD MANC NTUP PRC | EST CAN | MAI | 10207.86 | 0 | 2025-11-25 | 2026-10-30 |  |  | U145347
2621 |  | Duke Rd. / Cooper Dr. Relocation | 4000094778 | BET32.0000.00060 | REL PCNF ESTC MANC PRC SETC | COCO ADJ FCMP | MAI | 11380.49 | 112.75 | 2025-12-05 | 2025-12-19 | 2026-02-13 | 2026-01-31 | U145347
2621 |  | GRT-THE SANCTUARY MLE-(CANCELED) | 4000097238 | GRT32.0000.00151 | CRTD ESTC CSER MANC NTUP PRC SKKP | PLN CAN | MAI | 209798.46 | 0 | 2026-01-29 | 2026-12-31 |  |  | U145347
2621 |  | GRT-HARTLAND PKWY MLE-LEXINGTON | 4000097613 | GRT32.0000.00158 | CRTD MANC NTUP PRC SKKP | NEW CAN NSFS REV WLND | MAI | 27177.48 | 0 | 2026-02-05 | 2026-04-30 |  |  | U145347
2621 |  | PIG-REDMILE RD. ABANDONMENT-LEXINGTON | 4000097968 | PIG32.0000.00069 | REL ESTC CSER GMPS MANC PRC SETC | NPRG FCMP | MAI | 8923.55 | 15435.22 | 2026-02-12 | 2026-04-16 |  |  | U145347
2621 |  | GRT-KROGER PATCHEN WILKES-LEXINGTON | 4000099571 | GRT32.0000.00164 | REL MANC PRC SETC SKKP | NEW ADJ NSFS WENV WLND | MAI | 263714.23 | 0 | 2026-05-06 | 2026-10-10 |  |  | U145347
|  | GRT-THE SANCTUARY MLE-LEXINGTON | 4000100569 |  | CRTD MANC NMAT NTUP PRC | EST | MAI | 0 | 0 | 2026-03-25 | 2026-12-31 |  |  | U145347
2621 |  | GRT-THE SANCTUARY MLE-LEXINGTON | 4000100570 | GRT32.0000.00151 | CRTD ESTC CSER MANC NTUP PRC | PLN WENG | MAI | 219626.52 | 0 | 2026-03-25 | 2026-12-31 |  |  | U145347
2621 |  | GRT-WILLOWS AT ANDOVER-LEXINGTON | 4000100966 | GRT32.0000.00168 | REL ESTC MANC PRC SETC | NEW WGMA WLND | MAI | 277736.39 | 0 | 2026-04-01 | 2026-10-31 |  |  | U145347
2621 |  | GRT-3258 AQUEDUCT DR. MLE-LEXINGTON | 4000102117 | GRT32.0000.00170 | CRTD ESTC MANC NTUP PRC | PLN WENG WLND | MAI | 43771.49 | 0 | 2026-04-22 | 2026-07-03 |  |  | U145347
2621 |  | Design for CU Tab | 4000103038 |  | CRTD MANC NMAT NTUP PRC | EST | MAI | 0 | 0 | 2026-05-08 | 2026-05-08 |  |  | U145347
2621 |  | GRT - SVU NEW BUILDING - BUENA VISTA | 4000094276 | GRT38.0000.00423 | CRTD ESTC MANC NTUP PRC | PLN ADJ NSFS | MAI | 454769.21 | 0 | 2025-11-25 | 2025-12-31 |  |  | U146250
2621 |  | ANC - SAVE GRANDVIEW DR - LEXINGTON | 4000094996 | ANC38.0000.00548 | REL MANC PRC SETC | NEW NSFS WLND | MAI | 90212.48 | 0 | 2025-12-10 | 2026-12-31 |  |  | U146250
2621 |  | ANC - SAVE KANAWHA - GLASGOW | 4000094999 | ANC38.0000.00550 | REL MANC PRC SETC | NEW NSFS WLND | MAI | 88031.7 | 0 | 2025-12-10 | 2026-12-31 |  |  | U146250
2621 |  | ANC - SAVE ROSS LN - LEXINGTON | 4000095000 | ANC38.0000.00551 | REL ESTC MANC PRC SETC | NEW NSFS WLND | MAI | 87204.7 | 0 | 2025-12-10 | 2026-12-31 |  |  | U146250
2633 |  | PIG-KY 292 Shallow Main-South Williamson | 4000088505 | PIG32.0000.00052 | REL PCNF GMPS MANC PRC SETC | NPRG ADJ MIFE RCFO | MAI | 1406753.85 | 280696.77 | 2026-01-19 | 2026-06-30 | 2026-04-13 | 2026-12-31 | U938437
2621 |  | ANC-Richmond Rd Phase III SMRP-Lexington | 4000090243 | ANC32.0000.00321 | REL ESTC CSER MANC PRC SETC | NEW | MAI | 167196.98 | 1083.28 | 2026-12-31 | 2026-12-31 |  |  | U938437
2632 |  | ANC- Maysville BSHP SMRP - Maysville | 4000090558 | ANC32.0000.00325 | REL PCNF GMPS MANC NMAT PRC SETC | NEW RCFO WENV | MAI | 365.12 | 49388.39 | 2026-06-20 | 2026-12-31 | 2026-02-19 | 2026-12-31 | U938437
2629 | PARIS | STA - Paris-Cynthiana POD Repl - Paris | 4000091562 | ANC32.0000.00335 | REL ESTC MACM PRC SETC | NEW MIFE NSFS WENG | STA | 402481.39 | 8041.64 | 2025-10-07 | 2025-10-07 |  |  | U938437
2621 |  | PIG -SR27-7-412 Relocation - Lexington | 4000093050 | PIG32.0000.00062 | REL ESTC MACM PRC SETC | NEW NSFS | MAI | 42600.9 | 7497.08 | 2025-11-05 | 2025-11-05 |  |  | U938437
2621 | LEXINGTON | STA-Richmond Rd Ph III-Lexington | 4000094767 | ANC32.0000.00321 | CRTD MANC NMAT NTUP PRC | EST | STA | 356.64 | 0 | 2025-12-04 | 2025-12-04 |  |  | U938437
2621 |  | ANC - DELMONT DR SMRP - LEX | 4000096753 | ANC32.0000.00356 | REL ESTC MANC PRC SETC | NEW MIFE NSFS WENG | MAI | 2.37 | 12283.27 | 2026-10-31 | 2027-12-31 |  |  | U938437
2621 |  | PIG - LIMA DR HP - LEXINGTON | 4000099136 | PIG32.0000.00072 | REL ESTC MANC PRC SETC | NEW MIFE NSFS WENG | MAI | 1.67 | 0 | 2026-10-31 | 2027-12-31 |  |  | U938437
2621 |  | ANC - St Martins Village SMRP -Lexington | 4000099200 | ANC32.0000.00385 | REL ESTC MANC PRC | NEW MIFE NSFS | MAI | 1.67 | 0 | 2026-10-31 | 2027-12-31 |  |  | U938437
2629 |  | STA- FISH 1301F REPL 200860-OWINGSVILLE | 4100836975 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW MIFE | STA | 4461.53 | 0 | 2026-02-01 | 2026-03-01 |  | 2026-12-31 | U938437
2623 | FRANKFORT | STA- FISH 1301F REPL 200162- | 4100836976 | ANC32.0003.00011 | REL ESTC CSER MANC PRC SETC | SCHD MIFE | STA | 2676.63 | 0 | 2026-02-01 | 2026-03-01 |  | 2026-12-31 | U938437
2631 | SOUTH SHORE | STA- FISH 1301F REPL 200311- | 4100836977 | ANC32.0003.00011 | REL ESTC CSER MANC PRC SETC | SCHD MIFE | STA | 4179.93 | 0 | 2026-02-01 | 2026-03-01 |  | 2026-12-31 | U938437
2621 | LEXINGTON | STA- FISH 1301F REPL 211853- | 4100836978 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | SCHD MIFE | STA | 4461.53 | 0 | 2026-02-01 | 2026-03-01 |  | 2026-12-31 | U938437
2621 | LEXINGTON | STA- FISH 1301F REPL 211762- | 4100837015 | ANC32.0003.00011 | REL ESTC CSER MANC PRC SETC | SCHD MIFE | STA | 4179.93 | 0 | 2026-03-01 | 2026-04-01 |  | 2026-12-31 | U938437
2623 | FRANKFORT | STA- FISH 1301F REPL 200653- | 4100837048 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW MIFE | STA | 4461.53 | 0 | 2026-03-01 | 2026-04-01 |  | 2026-12-31 | U938437
2623 | GEORGETOWN | STA- FISH 1301F REPL 213027- | 4100837060 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW | STA | 7468.13 | 0 | 2026-03-01 | 2026-04-01 |  | 2026-12-31 | U938437
2629 | PARIS | STA- FISH 1301F REPL 200933- | 4100837070 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW | STA | 4461.53 | 0 | 2026-03-01 | 2026-04-01 |  | 2026-12-31 | U938437
2632 | MAYSVILLE | STA- FISH 1301F REPL 208891- | 4100837080 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW MIFE | STA | 2958.23 | 0 | 2026-03-01 | 2026-04-01 |  | 2026-12-31 | U938437
2629 | CARLISLE | STA- FISH 1301F REPL 200958 | 4100837093 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | SCHD MIFE | STA | 23756.85 | 0 | 2026-03-01 | 2026-04-01 |  | 2026-12-31 | U938437
2631 | ASHLAND | STA- FISH 1301F REPL 210271- | 4100837104 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW | STA | 7468.13 | 0 | 2026-03-01 | 2026-04-01 |  | 2026-12-31 | U938437
2623 | MIDWAY | STA- FISH 1301F REPL 212294- | 4100837119 | ANC32.0003.00011 | REL ESTC MACM PRC SETC | NEW MIFE | STA | 4461.03 | 0 | 2026-04-01 | 2026-05-01 |  | 2026-12-31 | U938437
2623 | FRANKFORT | STA- FISH 1301F REPL 200170- | 4100837141 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW | STA | 4461.53 | 0 | 2026-04-01 | 2026-05-01 |  | 2026-12-31 | U938437
2623 | VERSAILLES | STA- FISH 1301F REPL 200246- | 4100837142 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW MIFE | STA | 2958.23 | 0 | 2026-05-01 | 2026-06-01 |  | 2026-12-31 | U938437
2629 |  | STA- FISH 1301F REPL 200709 | 4100837143 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW MIFE | STA | 7468.13 | 0 | 2026-05-01 | 2026-06-01 |  | 2026-12-31 | U938437
2629 | IRVINE | STA- FISH 1301F REPL 212043- | 4100837144 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW MIFE | STA | 4461.53 | 0 | 2026-05-01 | 2026-06-01 |  | 2026-12-31 | U938437
2623 | GEORGETOWN | STA- FISH 1301F REPL 210385 | 4100837146 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW MIFE | STA | 4461.53 | 0 | 2026-05-01 | 2026-06-01 |  | 2026-12-31 | U938437
2631 | CATLETTSBURG | STA- FISH 1301F REPL 209199- | 4100837147 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW | STA | 7468.13 | 0 | 2026-05-01 | 2026-06-01 |  | 2026-12-31 | U938437
2633 | GREEN MEADOW | STA- FISH 1301F REPL 210363- | 4100837148 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW MIFE | STA | 2958.23 | 0 | 2026-05-01 | 2026-06-01 |  | 2026-12-31 | U938437
2633 | PIPPA PASSES | STA- FISH 1301F REPL 200198- | 4100837149 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW MIFE | STA | 2958.23 | 0 | 2026-06-01 | 2026-07-01 |  | 2026-12-31 | U938437
2623 | FRANKFORT | STA- FISH 1301F REPL 211194- | 4100837150 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW MIFE | STA | 4461.53 | 0 | 2026-06-01 | 2026-07-07 |  | 2026-12-31 | U938437
2623 | GEORGETOWN | STA- FISH 1301F REPL 212339- | 4100837151 | ANC32.0003.00011 | REL ESTC MANC PRC SETC | NEW MIFE | STA | 7468.13 | 0 | 2026-07-01 | 2026-08-01 |  | 2026-12-31 | U938437

## Notes (hidden)
Assumed the following job types are "Construction Projects"
555
557
558
559
560
561
562
563
565
566
573
577
583
584
585
586
587
588
909
910
Reused data for 2021-23 that was filed in last rate case
Date actual start dates are estimated. This information wasn't entered into WMS, so my team and I looked through each job order and put down a best guess around approximate construction start time
SAP financial data seems off. All WMS-SAP conversion WO's financials were wrong. Went into WMS and maunally updated, but actuals are most likely inaccurate