## Schedule I1
KY PSC Case No. 2026-00099
Staff 1-27
Schedule I1
Columbia Gas of Kentucky Case No. 2026-00099 Attachment A Construction Projects For 5 years ended December 31, 2025
Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End | Job Order Comments
20026969700 | INSTALL 8500' OF 2"/4"PMMP MN |  |  |  |  | 0.3995% | 270941.08 | 301857.4038 | -30916.3238 | 2020-01-01 | 2020-12-31 | 2020-11-09 | 2021-01-08
21026993200 | EMER- INSTALL 5'-4" PMMP |  |  |  |  | 0.004807% | 3260.67 | 4003.4824 | -742.8124 | 2021-01-01 | 2021-12-31 | 2021-01-05 | 2021-01-08 | INSTALLED 4' OF 4" P. PRESSURE TESTED AT 90LBS FOR 1HR. SOAP TESTED (2) 4" EF COUPLINGS AT OPERATING PRESSURE (11PSIG).
21026993300 | EMER- RETIRE 5'-4" P-MP |  |  |  |  | 0.0002724% | 184.74 | 647.029 | -462.289 | 2021-01-01 | 2021-12-31 | 2021-01-05 | 2021-01-08 | REMOVED 4' OF DAMAGED 4" P
21026993600 | EMER INST 40'-4" PMLP |  |  |  |  | 0.00114% | 772.98 | 13260.7401 | -12487.7601 | 2021-01-01 | 2021-12-31 | 2021-01-07 | 2021-01-08 | INSTALLED 28' OF 4" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 10" WC
21026993700 | EMER RET 40'-4" BSLP/CSLP/P-LP |  |  |  |  | 0.0005487% | 372.17 | 1322.2973 | -950.1273 | 2021-01-01 | 2021-12-31 | 2021-01-07 | 2021-01-08 | RETIRED 28' OF 4" STEEL MAIN AND 3 WAY TEE
20026991200 | RETIRE BUILDING |  |  |  |  | 0% | 0 | 107.2796 | -107.2796 | 2021-01-01 | 2021-12-31 | 2021-01-07 | 2021-01-07 | THIS IS PAPER ONLY JOB BUILDING WAS TORN DOWN MANY YEARS AGO THIS JOB IS TO CORRECT CKY RECORDS ONLY FIELD VERIFIED BY CKY ENGINEERING
20026988100 | INSTALL 525' OF 2"PMMP MAIN |  |  |  |  | 0.01508% | 10228.67 | 17405.4965 | -7176.8265 | 2021-01-01 | 2021-12-31 | 2021-01-07 | 2021-01-11
21026994600 | EMER INSTALL 5'-4" PMMP |  |  |  |  | 0.006815% | 4622.23 | 5854.5805 | -1232.3505 | 2021-01-01 | 2021-12-31 | 2021-01-08 | 2021-01-11 | REPLACED 5 FT MAIN TEST 90 LB FOR 20 MIN TEST ALL TEES AT 5 MIN TEST BYPASS 90 LB FOR 1 HR TEST ALL END CAPS AT OP FOR 5 MIN BAR HOLE BANKS NO GAS FOUND MARKER BALL AT TEES AND CPLG
21026994400 | EMER- INSTALL 5'-2" PMIP |  |  |  |  | 0.007631% | 5176.12 | 7281.2724 | -2105.1524 | 2021-01-01 | 2021-12-31 | 2021-01-08 | 2021-01-13 | INSTALLED 6' NEW 020 MDPE ML. TESTED AT 90# 20 MINS. WELD-IN TRANSITIONS. S OAP TEST TIE IN. PURGED AT EOM. SWING TIES AND ELEC MARKERS. J HOWARD 1-13- 21
21026994700 | EMER - RETIRE 5'-4" PMP |  |  |  |  | 0.0001518% | 102.95 | 103.8156 | -0.86559 | 2021-01-01 | 2021-12-31 | 2021-01-08 | 2021-01-11 | CUT OUT CRACKED MAIN PUT ON BYPASS AND PUT IN 5 FT OF MAIN
21026994500 | EMER- RETIRE 5'-2" BSIP |  |  |  |  | 0.001725% | 1169.82 | 239.0145 | 930.8055 | 2021-01-01 | 2021-12-31 | 2021-01-08 | 2021-01-11 | INSTALLED 2 020 TDW SS. TAP AND STOP ML. NO UPSTREAM PRESSURE LOSS. REMOVED AND ABANDONED 6' SECTION OF 020 S ML FOR INSTALL OF 020 MDPE. J HOWARD 1-1 1-21
20026991100 | INSTALL 100' OF 4"PMLP S/L |  |  |  |  | 0.04978% | 33764.98 | 29024.9725 | 4740.0075 | 2021-01-01 | 2021-12-31 | 2021-01-07 | #N/A
21026996700 | EMER - INSTALL 10'-4" PMMP |  |  |  |  | 0.001939% | 1315.39 | 1997.1109 | -681.7209 | 2021-01-01 | 2021-12-31 | 2021-01-11 | 2021-01-11
21026996800 | EMER - RETIRE 10'-4" PMMP |  |  |  |  | 0% | 0 | 95.6296 | -95.6296 | 2021-01-01 | 2021-12-31 | 2021-01-11 | 2021-01-11
19026901000 | RETIRE STATION 1464 |  |  |  |  | 0.003914% | 2654.56 | 690.3419 | 1964.2181 | 2020-01-01 | 2020-12-31 | 2021-01-11 | 2021-01-11 | JOB CARRIED OVER UNTIL AFTER THE 1ST OF 2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/16/2021 GCCC TICKET NOT REQUIRED ON 2/16/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK 2/16/21 CFARIS
19026901100 | RETIRE STATION 1481 |  |  |  |  | 0.003662% | 2483.61 | 690.3419 | 1793.2681 | 2021-01-01 | 2021-12-31 | 2021-01-11 | 2021-01-11 | JOB ON HOLD UNTIL AFTER THE 1ST OF 2021
19026901200 | RETIRE STATION 1480 |  |  |  |  | 0.006583% | 4464.65 | 690.3419 | 3774.3081 | 2021-01-01 | 2021-12-31 | 2021-01-11 | 2021-01-11 | JOB WAS ON HOLD UNTIL AFTER THE 1ST OF 2021
20026945201 | INSTALL 5000' OF 2"PMMP MAIN |  |  |  |  | 0.3365% | 228201.9 | 223484.8945 | 4717.0055 | 2020-01-01 | 2020-12-31 | 2020-11-18 | 2021-02-16 | INSTALLED 4938"020 PMMP.
18026789001 | INSTALL 6900' - 4" PMMP |  |  |  |  | 1.164% | 789465.56 | 783479.7367 | 5985.8233 | 2020-01-01 | 2020-12-31 | 2020-10-20 | 2021-02-05
20026936600 | ABANDON ~10'-4" P-LP |  |  |  |  | 0.0002467% | 167.31 | 173.6495 | -6.3395 | 2021-01-01 | 2021-12-31 | 2021-01-12 | 2021-01-13
21026996400 | EMER - ABANDON 37'-2" PIP |  |  |  |  | 0.001269% | 860.91 | 2872.6664 | -2011.7564 | 2021-01-01 | 2021-12-31 | 2021-01-14 | 2021-01-25 | ABANDONED 37' OF 020 MAIN DUE TO FAC DAM. WORKED WITH TIE IN PLAN. INSTALLED LINE MARKER AT EOM. UPDATED MAPPING. SOAP TEST END CAP AT OP.TEST OK. BHB NGF.
20026930100 | UPGRADE ELECTRONICS |  |  |  |  | 0.005778% | 3919.3 | 3038 | 881.3 | 2021-01-01 | 2021-12-31 | 2021-01-14 | 2021-01-14 | NO TICKET NEEDED FOR THE WORK PERFORMED. 1/14/21 GCCC TICKET NOT REQUIRED PE ENGINEER CINDY SPARKS GAVE VERBAL APPROVAL ON SITE TO PROCEED WITH JOB. EFC REPLACEMENT ONLY GAS FLOW NOT INTERUPTED JOB DELAYED DUE TO COVID 19 AND COMPLIANCE WORK AND BY NOW HAVING TO BE REVIEWED BY PE ENGINEER
20026937300 | RETIRE ELECTRONICS |  |  |  |  | 0% | 0 | 73.3494 | -73.3494 | 2021-01-01 | 2021-12-31 | 2021-01-14 | 2021-01-14 | GCCC TICKET NOT REQUIRED VERBAL APPROVAL GIVEN ONSITE BY PE ENGINEER CINDY SPARKS TO WORK JOB GAS FLOW NOT INTERUPTED TO WORK JOB THIS WAS EFC REPLACEMENT ONLY JOB DELAYED DUE TO COVID 19 COMPLIANCE WORK AND WAITING REVIEW BY PE ENGINEER
20026989600 | INSTALL 40'-2" PMMP |  |  |  |  | 0.05443% | 36919.96 | 30326.4153 | 6593.5447 | 2021-01-01 | 2021-12-31 | 2021-01-13 | 2021-01-15
20026989700 | RETIRE 40'-2" CSMP |  |  |  |  | 0% | 0 | 107.2796 | -107.2796 | 2021-01-01 | 2021-12-31 | 2021-01-13 | 2021-01-15
19026895301 | INSTALL 6060' 2" PMMP |  |  |  |  | 1.203% | 815947.98 | 549218.5288 | 266729.4512 | 2020-01-01 | 2020-12-31 | 2020-09-29 | 2021-01-27 | JOB ORDER CODED COMPLETE IN ERROR. WILL BE CARRY OVER INTO 2021. SPENDLE OVERRUN EXPLANATION: ADDITIONAL PIPE WAS ADDED LATE INTO PROJECT AND ADDITI ONAL LABOR HOURS CAUSED INCREASE IN SEGA AS WELL AS LATE PAVING COSTS THAT HIT THE PROJECT SBRADY 6/18/21
20026990600 | PAPER ONLY FOR CLOSE OUT |  |  |  |  | 0% | 0 | 103.8156 | -103.8156 | 2021-01-01 | 2021-12-31 | 2021-01-21 | 2021-01-21
20026967900 | INSTALL 315' 2" PMIP |  |  |  |  | 0.1053% | 71403.61 | 31888.6353 | 39514.9747 | 2021-01-01 | 2021-12-31 | 2021-01-19 | 2021-01-29 | TWALKER/KY 02-23-21: ISSUED BACK ORDER CANCEL #48444 FOR JOB OVERRUN EXPLANATION: 150 SQUARE FEET OF 6&2 WAS ESTIMATED AND 990 SQ FEET W AS REQUIRED LEADING TO AN INCREASE IN CONTRACTOR COSTS AND OVERHEADS.
19026895200 | RETIRE 2104' 2" P/BSLP |  |  |  |  | 0.0001486% | 100.78 | 103.581 | -2.801 | 2021-01-01 | 2021-12-31 | 2021-01-15 | 2021-01-27
19026895400 | RETIRE 5072' 2-4" IP |  |  |  |  | 0% | 0 | 103.581 | -103.581 | 2021-01-01 | 2021-12-31 | 2021-01-15 | 2021-01-27
19026895600 | RETIRE 1516' 2" BS/P/WILP |  |  |  |  | 0.0001603% | 108.73 | 103.581 | 5.149 | 2021-01-01 | 2021-12-31 | 2021-01-15 | 2021-01-27
19026900900 | RETIRE MP TO IP RUN S-1455 |  |  |  |  | 0.0002246% | 152.33 | 690.3419 | -538.0119 | 2021-01-01 | 2021-12-31 | 2021-01-27 | 2021-10-25 | MP TO IP RUN RETIRE ON 1/27/21 BY RYAN VANDERPOOL PAPERWORK DID NOT GET TURNED IN FOR COMPLETION STATION RETIREMENT FIELD VERIFIED ALONG WITH RETIREMENT DATE FROM THE STATION INSPECTION RECORD BY WADE SHIMFESSEL AND JOSH MARTIN ON 10/18/2021 RETIREMENT PAPERWORK COMPLETED BY CYNTHIA FARIS ON 10/25/2021 GCCC TICKET NOT REQUIRED ON 10/25/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK. SETTING BYPASS VALVE AND INLET SETTING VALVE NOT RETIRED THEY ARE TURNED OFF AND BLIND FLANGED CFARIS
20026966800 | RETIRE 2800' OF 4"/6"BSLP MAIN |  |  |  |  | 0.001338% | 907.78 | 90.1729 | 817.6071 | 2021-01-01 | 2021-12-31 | 2021-02-03 | 2021-02-04
21026100900 | EMER INSTALL 5'-4" PMMP |  |  |  |  | 0.0733% | 49713.13 | 15398.8131 | 34314.3169 | 2021-01-01 | 2021-12-31 | 2021-02-03 | 2021-02-10 | RETIRED 4 FEET OF 4' PE MAIN LINE. REPLACED PEICE OF MAIN WITH NEW AND EF COUPLINGS. PRESSURE TESTED NEW PEICE OF MAIN FOR 1HR @ 90PSIG. TEST OK. SOAP TESTED FINALS CONNECTION @ OP. TEST, BHB, NGF. DMALONE 2/09/2021. OVERRUN EXPLANATION: UNEXPECTED CONTRACT COST OF $35,000 WAS NOT PLANNED, JO ORIGINALLY PLANNED FOR COMPANY CREW BUT WAS EXECUTED BY A CONTRACT CREW, COMPANY CREWS ALSO CHARGED 183 HOURS TO PROJECT
21026101000 | EMER RETIRE 5'-4" PMP D222468 |  |  |  |  | 1.614e-05% | 10.95 | 69.6296 | -58.6796 | 2021-01-01 | 2021-12-31 | 2021-02-03 | 2021-02-09 | RETIRED 4 FEET OF 4' PE MAIN LINE. REPLACED PEICE OF MAIN WITH NEW AND EF COUPLINGS. PRESSURE TESTED NEW PEICE OF MAIN FOR 1HR @ 90PSIG. TEST OK. SOAP TESTED FINAL CONNECTION @ OP. TEST OK. BHB. NGF. DMALONE 2/09/2021 OVERRUN EXPLANATION: THIS RETIREMENT JOB ORDER WAS ESTIMATED IN THE ORDINAR Y MANNER FOR JUST 1 HOUR; HOWEVER, THERE WERE NO PROPERTY UNITS INSTALLED S O THE JOB WAS WORKED AS AN ABANDONMENT WITH ALL THE LABOR AND CONTRACT COST S BEING APPLIED TO THE RETIREMENT. THE INSTALL JOB ORDER WAS EXECUTED WITH AN HOUR OF LABOR.
18026789100 | RETIRE 600' - 3" PMMP |  |  |  |  | 0.0001038% | 70.37 | 218.671 | -148.301 | 2021-01-01 | 2021-12-31 | 2021-02-04 | 2021-02-04
20026955400 | RETIRE STATION |  |  |  |  | 0.003485% | 2363.47 | 1910.2958 | 453.1742 | 2021-01-01 | 2021-12-31 | 2021-02-04 | 2021-02-04 | 8561 JOB WAS ON HOLD UNTIL AFTER BEGINNING OF THE YEAR
21026100300 | EMER INS ~15'-2"/3" PMIP/CSIP |  |  |  |  | 0.01937% | 13138.1 | 15461.5913 | -2323.4913 | 2020-01-01 | 2020-12-31 | 2020-10-20 | 2021-02-17 | 3" C.S. MAIN PULLED LOOSE FROM 4 BOLT COUPLING DUE TO STRESS ON MAIN FROM EXPOSURE DOWN STREAM. TAPPED & STOPPED 3" C.S. REPLACED LEAKING SECTION WITH 3" P 20' PRESSURE TEST 90 PSIG 1HR PURGED MAIN LINE, RESTORED SERVICE.
21026100400 | EMER RETIRE ~5'-3" CSIP |  |  |  |  | 0.002219% | 1505.21 | 1147.7777 | 357.4323 | 2021-01-01 | 2021-12-31 | 2021-02-05 | 2021-02-11 | 3" CS MAIN PULLED LOOSE FROM 4 BOLT COUPLING DUE TO STRESS ON MAIN FROM EXPOSURE DOWN STREAM. TAPPED & STOP 3" CS MAIN REPLACED LEAKING SECTION WITH 3" P 20' PRESSURE TEST 90PSIG FOR 1 HR. PURGED MAIN & RESTORED SERVICE
20026975000 | INSTALL 150'-2" PMIP |  |  |  |  | 0.01891% | 12825.26 | 12346.2686 | 478.9914 | 2021-01-01 | 2021-12-31 | 2021-01-27 | 2021-02-08
21026104900 | EMER INSTALL 5'-3" PMIP |  |  |  |  | 0.007015% | 4758.29 | 5995.5434 | -1237.2534 | 2021-01-01 | 2021-12-31 | 2021-02-22 | 2021-03-25 | SEE PAPER PACKET FOR INFO
21026105000 | EMER RETIRE 5'-3" P-IP |  |  |  |  | 0.005541% | 3758.23 | 750.8346 | 3007.3954 | 2021-01-01 | 2021-12-31 | 2021-02-22 | 2021-03-25 | SEE PAPER COPIES FOR TEST INFO SEE PAPER COPIES/ PIPE EXPOSURE FORM WILL NOT ACCEPT THE CORRECT MAIN NUMBER NOT LETTING ME COMPLETE THIS ORDER
21026131100 | EMER-RETIRE 10' OF 2"PAMP MAIN |  |  |  |  | 0% | 0 | 74.8797 | -74.8797 | 2021-01-01 | 2021-12-31 | 2021-06-22 | 2021-06-23
19026913900 | INSTALL 20' - 4" CSHP |  |  |  |  | 0.1218% | 82645.85 | 45390.8034 | 37255.0466 | 2021-01-01 | 2021-12-31 | 2021-02-08 | 2021-03-23 | COULD NOT REVISE DUE TO UNFULLFILLED PURCHASE ORDERS, NEEDED REVISION DUE TO EXTRA MATERIAL, INCREASE CONTRACT LABOR REQUIRED, EXTRA COMPANY LABOR, EXTRA TRUCK COSTS, AND EXTRA SEGA TTOY 3/18/2021
19026914000 | RETIRE 10' - 3" CSHP |  |  |  |  | 0.001025% | 695.55 | 114.5339 | 581.0161 | 2021-01-01 | 2021-12-31 | 2021-02-08 | 2021-03-23
20026941900 | RETIRE GAUGE |  |  |  |  | 0% | 0 | 91.4991 | -91.4991 | 2021-01-01 | 2021-12-31 | 2021-02-24 | 2021-07-16 | GAUGE RETIRE BY JOSH MULLINS ON 2/24/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/16/21 DELAY COMPLETING JOB ORDER DUE TO ISO SKETCH REVISION& PE APPROVAL GCCC TICKET NOT REQUIRED ON 7/16/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026942400 | RETIRE GAUGE |  |  |  |  | 0.001522% | 1032.4 | 91.4991 | 940.9009 | 2021-01-01 | 2021-12-31 | 2021-12-17 | 2021-12-17 | REPLACED MECHANICAL RECORDING GAUGE WITH ERX DELAY IN SENDING TO CLOSEOUT DUE TO WAITING ON INFORMATION, PE REVIEW/APPROVAL AND CORRECT ISO SKETCH CFARIS
20026941800 | INSTALL I&C EQUIPMENT |  |  |  |  | 0.0183% | 12411.86 | 16155.4774 | -3743.6174 | 2021-01-01 | 2021-12-31 | 2021-02-24 | 2021-07-16 | GCC 13064 EQUIPMENT INSTALLED BY JOSH MULLINS ON 2/24/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/16/21 DELAY IN JOB COMPLETION WAITING ON PE APPROVAL FOR 584 JOB ORDER AND ISO SKETCH UPDATE GCCC TICKET NOT REQUIRED ON 7/16/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026942300 | INSTALL I&C EQUIPMENT |  |  |  |  | 0.01717% | 11644.22 | 16155.4774 | -4511.2574 | 2021-01-01 | 2021-12-31 | 2021-12-17 | 2021-12-17 | INSTALLED ERX DELAY IN SENDING JOB TO CLOSE OUT WAITING ON INFORMATION PE REVIEW/APPROVAL AND ISO SKETCH CFARIS
21026105900 | EMER INSTALL 5' OF 4"PMMP MAIN |  |  |  |  | 0.01903% | 12908.51 | 24731.5705 | -11823.0605 | 2021-01-01 | 2021-12-31 | 2021-02-25 | 2021-03-18 | TWALKER/KY-04-20-21: I HAVE ADDED A SIGNED PRESSURE TEST TO APPROVE THE 20 MIN PRESSURE TEST TO WMS.DOCS WORKSPACE.
21026106500 | EMER - INSTALL 4' OF 2"PMMP |  |  |  |  | 0.01095% | 7429.12 | 7343.079 | 86.041 | 2021-01-01 | 2021-12-31 | 2021-02-25 | 2021-02-25
21026105700 | EMER INST 360'-2" PMIP D244304 |  |  |  |  | 0.1618% | 109722.07 | 25736.2708 | 83985.7992 | 2021-01-01 | 2021-12-31 | 2021-02-25 | 2021-03-09 | INSTALLED 345' OF 2" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7.5 P SIG OVERRUN EXPLANATION: THE SIGNIFICANT COST DIFFERENCE RESULTED FROM PAVING REQUIREMENTS. THE PROJECT WAS NOT ESTIMATED FOR CONTRACT RESTORATION. PAVE TICKETS WERE SUBMITTED TO REPAIR ROAD AND PARKING LOT AREA
21026106000 | EMER RETIRE 5' OF 4"PAMP MAIN |  |  |  |  | 0% | 0 | 82.208 | -82.208 | 2021-01-01 | 2021-12-31 | 2021-02-25 | 2021-03-18
21026106600 | EMER - RETIRE 4' OF 2"PMMP |  |  |  |  | 0% | 0 | 82.208 | -82.208 | 2021-01-01 | 2021-12-31 | 2021-02-25 | 2021-02-25
21026105800 | EMER RETIRE 350'-3"/2" CSIP |  |  |  |  | 0.03986% | 27035.38 | 1114.7918 | 25920.5882 | 2021-01-01 | 2021-12-31 | 2021-02-25 | 2021-03-09 | FOUND CRACKED MAIN RETIRED 345' OF 3" ST AND INSTALLED 345' OF NEW 2" PL TO STOP LEAKAGE TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7.5 PSIG
18026778900 | INSTALL ERX & RTU BUILDING |  |  |  |  | 0.1668% | 113154.12 | 156098.7133 | -42944.5933 | 2021-01-01 | 2021-12-31 | 2021-02-26 | 2021-12-16 | CC# 13231. 2/25/21 DSASH WORKED ON PAPERWORK OFF SITE. 2/26/21 DSASH EQUIPMENT INSTALLED ON 2/25/21 BY ACP AND DANNY ASH PAPERWORK COMPLETED ON 12/16/2021 BY CYNTHIA FARIS JOB CLOSEOUT DELAYED WAITING ON INFORMATION AND CORRECT ISO SKETCH UNDERRUN EXPLANATION: THE CONTRACT COSTS WERE SIGNIFICANT LESS THAT THE I&C TEAM HAD ORIGINALLY ESTIMATED.
21026998100 | INSTALL 180' OF 2"PMMP MAIN |  |  |  |  | 0.0542% | 36764.99 | 11159.7406 | 25605.2494 | 2021-01-01 | 2021-12-31 | 2021-02-08 | 2021-02-26
20026991300 | INSTALL 350'-2" PMMP |  |  |  |  | 0.02842% | 19273.52 | 31069.259 | -11795.739 | 2021-01-01 | 2021-12-31 | 2021-03-02 | 2021-03-03 | 337 FT 2 " MEDIUM PRESSURE MAIN INSTALLED BY STANLEY PIPELINE YELLOW MED IUM DENSITY.PIPE
20026980000 | INSTALL 675' - 2"/4" PMLP |  |  |  |  | 0.275% | 186497.16 | 148515.2952 | 37981.8648 | 2021-01-01 | 2021-12-31 | 2021-02-09 | 2021-03-04 | DUE TO WEATHER CONDITION ON STATE ROAD UNABLE TO MAKE COMMIT DATE OVERRUN EXPLANATION: ALL OPEN CUT WAS ESTIMATED, BUT 108 FEET OF DIRECTIONA L BORE WAS USED. ADDITIONALLY, APPROXIMATELY 4 TIMES AS MUCH FLAGGING WAS R EQUIRED THAN ESTIMATED. OVERHEADS INCREASED $10,500 DUE TO THESE OVERAGES.
21026107500 | EMER- INSTALL120'-2" PL |  |  |  |  | 0.003016% | 2045.88 | 13083 | -11037.12 | 2021-01-01 | 2021-12-31 | 2021-03-04 | 2021-06-10 | INSTALLED 155' OF 2" P-MP MAIN DUE TO LEAK, SEE CAPITAL PACKET JO# 21-0261075-00, CDESPAIN 3-4-21
21026107600 | RETIRE MAIN - LEAKAGE D304381 |  |  |  |  | 0.02162% | 14663.28 | 56.3197 | 14606.9603 | 2021-01-01 | 2021-12-31 | 2021-03-04 | 2021-06-10 | REPLACED 155' OF 2" P- MP MAIN, FOUND 2BOLT COUPLING PL-PL CORRODED AND LEAKING, SQUEEZED OFF, REPLACED MAIN, SEE JO PACKET 21-0261075-00 CDESPAIN 3-4-21
20026980100 | RETIRE 622' - 2" BSLP |  |  |  |  | 0.000955% | 647.77 | 103.8156 | 543.9544 | 2021-01-01 | 2021-12-31 | 2021-02-09 | 2021-03-04
18026807000 | INST. FN 115 EXTRA LP OPP |  |  |  |  | 0.04242% | 28771.63 | 24102.8722 | 4668.7578 | 2021-01-01 | 2021-12-31 | 2021-03-04 | 2021-05-12 | GCCC# 11422 CHARED TIME TO COLLECT MATERIAL. DID NOT VISIT SITE NO GCCC TICKET REQUIRED CMCOC 3/3/21 GCCC# 13985 CMCHOLAN 3-4-2021 CCC#13985 REGULATOR AND ER350 INSTALLED BY CHRIS COX ON 3/4/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026807100 | RET. FN 115 FOR EXTRA LP OPP |  |  |  |  | 0.00376% | 2550 | 54.9718 | 2495.0282 | 2021-01-01 | 2021-12-31 | 2021-03-04 | 2021-05-12 | REGULATOR REPLACED BY CHRIS COX ON 3/4/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026108600 | EMER-INSTAL 5'-2" PMMP |  |  |  |  | 0.0001711% | 116.02 | 5147.5997 | -5031.5797 | 2021-01-01 | 2021-12-31 | 2021-03-05 | 2021-03-08 | INSTALLED 5' OF TEST 2" PMMP, SOAP TEST TIE IN, NO LEAKS, BHB NGF TIE OVER 2 SERVICE LINES, ON 3-5-21 DMEDLEY 3-8-21
21026108700 | EMER - RETIRE 5'-2" PAMP |  |  |  |  | 0.007072% | 4796.8 | 85.3307 | 4711.4693 | 2021-01-01 | 2021-12-31 | 2021-03-05 | 2021-03-08 | INSTALLED GAUGE TEE, SQUEEZE OFF 2" PL MAIN, ABN 5' 2"PMP MAIN PER DLEMONS EMER DESIGN PLAN. WORKED ON 3-5-21, DMEDLEY 3-8-21
21026996200 | INSTALL 2150'-2" PMMP |  |  |  |  | 0.4962% | 336530.83 | 214604.887 | 121925.943 | 2021-01-01 | 2021-12-31 | 2021-01-22 | 2021-03-05 | JOB ORDER CODED COMPLETE AT TIME OF MAIN LINE COMPLETION, STILL WORKING ON SERVICES. SPENDLE 3/10/21 20APR21: SEVERAL ATTEMPTS WERE MADE TO REVISE THIS JOB ORDER TO CAPTURE OVERRUN, HOWEVER, OUTSTANDING INVOICES PREVENTED ENGINEERING FROM DOING SO. . 29APR21: OVERRUN EXPLANATION = FISHEL'S CONTRACT OVER $21K DUE TO INCREASED LABOR & MATERIALS TO PREP STAGING (STONE, FENCING, AND ENVIRONMENTAL BMPS) ALONG WITH A LOT MORE FLAGGING BY AWP FOR TRAFFIC CONTROL. BUCHANAN'S COST FOR SEWER INSPECTION & CAMERING WAS WAY UNDERESTIMATED CONTRIBUTING ANOTHER $33K TO THE OVERRUN. LASTLY, COMPANY LABOR OVERRAN BY $14K FROM WHAT WAS ORIGINALY ESTIMATED. THESE COSTS PLUS OH'S MAKE UP THE OVERRUN (BKSLONE).
21026109000 | EMER - INSTALL 10'-4" PMIP |  |  |  |  | 0.003464% | 2349.57 | 8970.0544 | -6620.4844 | 2021-01-01 | 2021-12-31 | 2021-03-16 | 2021-03-18 | INSTALLED 5' OF NEW 4" PL MAIN TO REPAIR CRACKED PIPE TESTED 90 PSIG 1 HR
21026109100 | EMER - RETIRE 10'-4" CSIP |  |  |  |  | 0.008736% | 5925.07 | 556.9397 | 5368.1303 | 2021-01-01 | 2021-12-31 | 2021-03-08 | 2021-03-18 | RETIRE 5' OF 4" CS MAIN DUE TO SPLIT MAIN SOAP TESTED OP 7.5 PSIG
20026987500 | INSTALL 300' OF 2"PMMP MAIN |  |  |  |  | 0.02681% | 18181.58 | 19258.6597 | -1077.0797 | 2021-01-01 | 2021-12-31 | 2021-03-08 | 2021-03-10
20026988800 | INSTALL 210'-2" PMLP |  |  |  |  | 0.03218% | 21827.5 | 42176.37 | -20348.87 | 2021-01-01 | 2021-12-31 | 2021-03-08 | 2021-03-10
20026984400 | INSTALL 949'-6" PMLP |  |  |  |  | 0.4169% | 282788.29 | 204292.6769 | 78495.6131 | 2021-01-01 | 2021-12-31 | 2021-01-20 | 2021-03-12 | 14JUN21: OVERRRUN EXPLANATION = 1) REQUIRED FLAGGING WAS WAY UNDERESTIMATED AS $30K ADDITIONAL DOLLARS FOR FLAGGING WAS REQUIRED, 2) AN ADDITIONAL $10K IN DUST & STONE WAS REQUIRED, 3) THE 6" ROCK BORE WAS PAID ALL IN HEAVY ROCK WHEREAS IT WAS ESTIMATED 1/2 HEAVY AND 1/2 LIGHT WHICH CONTRIBUTED ANOTHER $8K TO THE OVERRUN,4) ADDITIONAL VAC EXCAVATION WAS REQUIRED ADDING $3K TO THE OVERRUN. THESE PLUS ADDITIONAL OH'S MAKE UP THE MAJORITY OF THE $57K OVERRUN (BKSLONE)
21026997000 | INSTALL 1100'-2" PMP |  |  |  |  | 0.7856% | 532822.99 | 340896.6283 | 191926.3617 | 2021-01-01 | 2021-12-31 | 2021-02-23 | 2021-04-27 | 14JUN21: UNDERRUN EXPLANATION = 1) ASPHALT MILL & OVERLAY WAS MISCALCULATED RESULTING IN AN ADDITIONAL $120K AND 2) FLAGGING TIME WAS UNDERESTIMATED RESULTING IN AND ADDITIONAL $35K. THESE COSTS, ALONG WITH ASSOCIATED OH'S, MAKE UP THE MAJORITY IF THE $166K OVERRUN. THE ERROR IN PAVING COSTS WAS NOT NOTICED UNTIL AFTER THE ORIGINAL JOB ORDER WAS EXECUTED THEREBY PROHIBITING PROCESSING A REVISION (BKSLONE).
20026979600 | INSTALL 20' - 2"/6" PMMP |  |  |  |  | 0.1567% | 106288.64 | 65238.0736 | 41050.5664 | 2021-01-01 | 2021-12-31 | 2021-02-02 | 2021-03-19 | ATTEMPTED TO REVISE DUE TO EXTRA HOURLY COST, COULD NOT REVISE DUE TO UNFULLFILLED PURCHASE ORDER TTOY 3/18/2021 OVERRUN EXPLANATION: JO WAS ORIGINALLY PLANNED ON 2018 FISHEL CONTRACT, JO WAS EXECUTED USING 2020 STANLEY PIPELINE CONTRACT, EXTRA VAC EXCA, EXTRA WLD AND RIG, EXTRA TOP SOIL REQUIRED, EXTRA HOURLY CREW REQUIRED, ESTIMATED HOURLY TIME WAS 56 HOURS, ACTUAL HOURLY TIME WAS 398 HOURS, ESTIMATED CONTRACT COST WAS $35,000, ACTUAL CONTRACT COST WAS $51,000
20026990100 | INSTALL 6" SS |  |  |  |  | 0.0003621% | 245.63 | 1607.8146 | -1362.1846 | 2021-01-01 | 2021-12-31 | 2021-03-11 | 2021-03-19
20026979700 | RETIRE 15' - 2" BSLP |  |  |  |  | 0.0001052% | 71.35 | 92.1481 | -20.7981 | 2021-01-01 | 2021-12-31 | 2021-03-11 | 2021-03-19
20026992200 | INSTALL 100'-2" PMIP |  |  |  |  | 0.01259% | 8539.31 | 11276.4442 | -2737.1342 | 2021-01-01 | 2021-12-31 | 2021-03-11 | 2021-03-15
21026108400 | EMER - INSTALL 350' - 4" PMMP |  |  |  |  | 0.1281% | 86916.93 | 44073.8715 | 42843.0585 | 2021-01-01 | 2021-12-31 | 2021-03-10 | 2021-03-16 | OVERRUN EXPLANATION: HOURLY TIME EXTIMATED AT 48 HOURS, ACTUAL TIME WAS 97 HOURS, SEGA WAS DOUBLED, CONTRACT WAS ESTIMATED FOR $29,000, ACTUAL WAS $68,000, PROJECT WAS ESTIMATED TO DIRECTIONAL BORE 150', ACTUAL INSTALL WAS OPEN CUT 345', PROJECT REQUIRED EXTRA PAVING DUE TO OPEN CUT, PROJECT REQUIRED EXTRA PROCESSED AND STONE DUST DUE TO OPEN CUT, EXTRA VACUUM EXCAV ATING WAS REQUIRED, ESTIMATED FOR 4 MAN CREW CONTRACT, ACTUAL USED 3 MAN, 4 MAN, AND 5 MAN CREWS
21026115100 | INSTALL 1'-4" PMLP |  |  |  |  | 0% | 0 | 149.4587 | -149.4587 | 2021-01-01 | 2021-12-31 | 2021-04-02 | 2021-04-06
21026115800 | EMER - INSTALL 138'-4" PM/CSIP |  |  |  |  | 0.003795% | 2573.82 | 10752.5629 | -8178.7429 | 2021-01-01 | 2021-12-31 | 2021-03-15 | 2021-04-20 | INSTALLED 134' OF 4" PL IP TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7.5 PSIG
21026108500 | EMER - RETIRE 350' - 4" PMP |  |  |  |  | 0.006604% | 4479.43 | 85.3307 | 4394.0993 | 2021-01-01 | 2021-12-31 | 2021-03-16 | 2021-03-16
21026115900 | EMER - RETIRE 134'-4" CSIP |  |  |  |  | 0.01452% | 9847.31 | 1105.3087 | 8742.0013 | 2021-01-01 | 2021-12-31 | 2021-04-20 | 2021-04-20 | RETIRED 134' OF 4" CS DUE MAIN EXPOSED OUT OF GROUND AND DETERIORATION
20026936301 | INSTALL 1192'-4" PMMP |  |  |  |  | 0.4279% | 290217.29 | 375696.2322 | -85478.9422 | 2021-01-01 | 2021-12-31 | 2021-01-13 | 2021-04-06 | UNDERRUN EXPLANATION: SIGNIFICANTLY LESS HARD SURFACE REPAIRS AND BACKFILL REQUIRED THAN ESTIMATED. ALSO NOFLAGGING ON OVERTIME WAS REQUIRED. THE OVER HEAD EFFECT OF THESE REDUCTIONS ALSO CONTRIBUTED TO THE UNDERRUN.
20026982500 | INSTALL 120' - 4" PMLP |  |  |  |  | 0.05739% | 38925.35 | 30468.341 | 8457.009 | 2021-01-01 | 2021-12-31 | 2021-03-16 | 2021-03-26
20026951802 | INSTALL 3980' OF 2"PMMP MAIN |  |  |  |  | 0.6811% | 461944.16 | 383869.9188 | 78074.2412 | 2021-01-01 | 2021-12-31 | 2021-20-04 | 2021-05-07 | TWALKER/KY 09-21-21: JOB OVER RUN DUE TO ADDITIONAL STREET AND HARD SURFACE REPAIR ADDED $70,000 TO CONTRACT COST AND SEGA WAS $7000 HIGHER THAN ESTIMA TE.
21026113000 | EMER - INSTALL 60' OF 4"PMLP |  |  |  |  | 0.002981% | 2022.21 | 12530.1178 | -10507.9078 | 2021-01-01 | 2021-12-31 | 2021-03-26 | 2021-04-08 | INSTALLED 54' OF 040 PLASTIC DUE TO STEEL ATMOS CORR. BAGGED OFF MAIN, RETIRED 54' 040 STEEL.WORKED WITH TIE IN PLAN AND CAPITAL PACKET.INSTALLED TWO TEST STATIONS. BHB NGF. KKINDER
20026951900 | RETIRE 2100' OF 4"CI/PLP MAIN |  |  |  |  | 0% | 0 | 84.1799 | -84.1799 | 2021-01-01 | 2021-12-31 | 2021-04-28 | 2021-05-07
21026113100 | EMER - RETIRE 60' OF 4"BSLP |  |  |  |  | 0.001974% | 1338.57 | 57.8842 | 1280.6858 | 2021-01-01 | 2021-12-31 | 2021-03-26 | 2021-04-08 | ABADONED 54' OF S LP DUE TO ATMOS CORR. WORKED WITH 557. BAGGED OFF MAIN WORKED WITH TIE IN PLAN. KKINDER
21026106100 | INSTALL 1350' OF 2"/4"PMMP |  |  |  |  | 0.05848% | 39665.6 | 45765.0925 | -6099.4925 | 2021-01-01 | 2021-12-31 | 2021-03-22 | 2021-04-09 | STANLEY PIPELNE INSTALLED MAIN
20026930400 | UPGRADE ELECTRONICS |  |  |  |  | 0.009682% | 6567.19 | 3038 | 3529.19 | 2021-01-01 | 2021-12-31 | 2021-03-29 | 2021-03-31 | CCC TICKET NOT REQUIRED 3/29/21 CFARIS REPLACED EFC AND WORKED TP ORDER JOB ON HOLD FOR 2020 DUE TO COVID 19 GCCC TICKET NOT REQUIRED ON 3/31/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK ALSO THIS IS NON-SCADA MONITORED GMB CFARIS
20026937600 | RETIRE ELECTRONICS |  |  |  |  | 0% | 0 | 73.3494 | -73.3494 | 2021-01-01 | 2021-12-31 | 2021-03-31 | 2021-03-31 | REPLACED EFC JOB ON HOLD IN 2020 DUE TO COVID 19 GCCC TICKET NOT REQUIRED NOT AT STATION OFF SITE COMPLETING PAPERWORK ALSO THIS IS A NON-SCADA MONITORED GMB 3/31/21 CFARIS
21026997600 | INSTALL 20'-2" PMIP |  |  |  |  | 0.03758% | 25490.16 | 28869.525 | -3379.365 | 2021-01-01 | 2021-12-31 | 2021-03-29 | 2021-03-31
17026735700 | RETIRE 3510' MAIN - D243673 |  |  |  |  | 0.01229% | 8338.24 | 78.7024 | 8259.5376 | 2021-01-01 | 2021-12-31 | 2021-03-30 | 2021-03-30
21026997700 | RETIRE 15'-2" BSIP |  |  |  |  | 0.0001414% | 95.92 | 88.4533 | 7.4667 | 2021-01-01 | 2021-12-31 | 2021-03-30 | 2021-03-30
20026936400 | RETIRE 1228'-3"&4"BS/CS/P-LP |  |  |  |  | 0.001791% | 1214.98 | 400.0304 | 814.9496 | 2021-01-01 | 2021-12-31 | 2021-01-13 | 2021-04-06
21026998000 | CONVERT TO GMB ACCOUNT |  |  |  |  | 0.009454% | 6412.15 | 4845.4443 | 1566.7057 | 2021-01-01 | 2021-12-31 | 2021-04-05 | 2021-04-07 | CONVERTED FROM CAB TO GMB ACCOUNT CCC TICKET NOT REQUIRED THIS IS NON-SCADA MONITORED
21026114000 | EMER - RETIRE 145' OF 2"BSLP |  |  |  |  | 0.001849% | 1254.24 | 3325.023 | -2070.783 | 2021-01-01 | 2021-12-31 | 2021-04-07 | 2021-04-07 | RETIRED 146' OF 2" BSLP MAIN, SOAP TEST BOLTED DEAD END CAP AT OP, OK. SOAP TEST SADDLES AND PAC CLAMPS AT OP OK. BHB NGF. INSTALLED 9# ANODE. MAIN READ# -0.643. MAIN INSP OK. WHIMES 04/07/2021
21026109900 | RETIRE 2155'-4"/3" BS/PMLP |  |  |  |  | 0.00468% | 3173.92 | 343.31 | 2830.61 | 2021-01-01 | 2021-12-31 | 2021-04-07 | 2021-04-28
20026975201 | INSTALL 3000' OF 2"/4"PMMP |  |  |  |  | 0.9298% | 630664.21 | 552556.8312 | 78107.3788 | 2021-01-01 | 2021-12-31 | 2021-06-17 | 2021-06-11
21026106200 | INSTALL 6" PCF |  |  |  |  | 0.0198% | 13429.76 | 16594.9062 | -3165.1462 | 2021-01-01 | 2021-12-31 | 2021-04-07 | #N/A | INSTALLED 6"SST
21026106300 | RETIRE 575'-6" BSLP |  |  |  |  | 0.001576% | 1068.93 | 88.4533 | 980.4767 | 2021-01-01 | 2021-12-31 | 2021-04-07 | 2021-04-12 | ABANDONED 640'060 CSLP
21026107700 | INSTALL 20' OF 8"PMLP MAIN |  |  |  |  | 0.01251% | 8482.5 | 12704.2275 | -4221.7275 | 2021-01-01 | 2021-12-31 | 2021-04-12 | #N/A | REPLACED 36' OF S LP MAON W/ 8" P PER TIE-IN PLAN AND GAS STANDARDS. SOAP TEST TIE-IN COUPLINGS NO LEAKS. BHB NGF. MAIN PTOS READ -0.482 INST 2 9LB ANODES.
21026107800 | RETIRE 20' OF 8" BSLP |  |  |  |  | 0.01287% | 8727.02 | 56.3197 | 8670.7003 | 2021-01-01 | 2021-12-31 | 2021-04-12 | 2021-04-14 | ABN 36' OF 8" S LP MAIN AND REPLACE WITH 8" P PER GAS STANDARDS AND TIE-IN PLAN. WORKED W/ 557 JOB# 21026107700. MCRAIG 4/14/21
21026107900 | INSTALL 10' OF 3" PMLP |  |  |  |  | 0.01131% | 7671.47 | 13301.2275 | -5629.7575 | 2021-01-01 | 2021-12-31 | 2021-04-15 | #N/A | ABANDONED 23' OF 030 S MAIN.DUE TO ATMOS CORR INSTALLED 23' OF 030 PLASTIC WORKED WITH TIE IN PLAN AND GAS STANDARD. BHB NGF. INSTALLED TWO TEST STATIONS AND TWO ANODED.DESNO WRAPPED STEEL MAIN.
21026108000 | RETIRE 10' OF 3" BSLP |  |  |  |  | 0.01241% | 8414.88 | 79.3197 | 8335.5603 | 2021-01-01 | 2021-12-31 | 2021-04-15 | 2021-04-16 | ABANDONED 23' OF 030 S MAIN.DUE TO ATMOS CORR INSTALLED 23' OF 030 PLASTIC WORKED WITH TIE IN PLAN AND GAS STANDARD. BHB NGF. INSTALLED TWO TEST STATIONS AND TWO ANODED.DESNO WRAPPED STEEL MAIN.
20026979201 | INSTALL SERVICE TO GMB |  |  |  |  | 0.297% | 201470.53 | 135908.7766 | 65561.7534 | 2021-01-01 | 2021-12-31 | 2021-04-27 | #N/A | LEVEL 2 BUDGET VARIANCE LOADED INTO WMSSDOCS. D.LEMONS 9/22/21
20026979100 | RETIRE SERVICE |  |  |  |  | 0% | 0 | 83.3805 | -83.3805 | 2021-01-01 | 2021-12-31 | 2021-04-27 | 2021-04-21
21026113401 | INSTALL 100'-2" PMMP |  |  |  |  | 0.03157% | 21410.67 | 11198.5401 | 10212.1299 | 2021-01-01 | 2021-12-31 | 2021-04-12 | #N/A
20026929300 | UPGRADE ELECTRONICS |  |  |  |  | 0.00937% | 6355.62 | 3038 | 3317.62 | 2021-01-01 | 2021-12-31 | 2021-04-16 | #N/A | REPLACED EFC
20026929600 | UPGRADE ELECTRONICS |  |  |  |  | 0.005018% | 3403.36 | 3038 | 365.36 | 2021-01-01 | 2021-12-31 | 2021-04-16 | #N/A | REPLACED EFC
20026935000 | RETIRE ELECTRONICS |  |  |  |  | 0% | 0 | 73.3494 | -73.3494 | 2021-01-01 | 2021-12-31 | 2021-04-16 | 2021-04-16 | REPLACE EFC JOB ON HOLD 2020 BECAUSE OF COVID 19
21026114300 | RETIRE EFC |  |  |  |  | 0% | 0 | 111.0751 | -111.0751 | 2021-01-01 | 2021-12-31 | 2021-04-16 | #N/A
21026999500 | INSTALL 175' OF 2"PMMP |  |  |  |  | 0.02405% | 16309.78 | 9497.8185 | 6811.9615 | 2021-01-01 | 2021-12-31 | 2021-04-13 | 2021-05-03 | 174 '2"PLASTIC MED -DENSITY YELLOW PIPE INSTALLED BY BIRECTIONAL BOREBY STA NLEY PIPELINE.
21026117300 | EMER - RETIRE 2'-4" P-LP |  |  |  |  | 0.0002699% | 183.09 | 441.8134 | -258.7234 | 2021-01-01 | 2021-12-31 | 2021-04-19 | #N/A | RETIRE 2' OF 4" PL DUE TO DAMAGE
19026889001 | INSTALL 28'-8" PMLP |  |  |  |  | 0.04537% | 30769.7 | 17790.2899 | 12979.4101 | 2021-01-01 | 2021-12-31 | 2021-02-03 | #N/A
21026110200 | EMER - INSTALL 5'-3" PMIP |  |  |  |  | 0.001298% | 880.36 | 7868.6589 | -6988.2989 | 2021-01-01 | 2021-12-31 | 2021-04-20 | #N/A | INSTALLED 5' OF 3" PLASTIC. TESTED AT 90PSIG FOR 1HR.
21026110300 | EMER - RETIRE 5'-3" PIP |  |  |  |  | 0.01064% | 7215.11 | 441.8134 | 6773.2966 | 2021-01-01 | 2021-12-31 | 2021-04-20 | 2021-04-21 | RETIRED 5' OF 3" PLASTIC DUE TO PAC CLAMPS LEAKING.
18026762102 | INSTALL NEW GMB |  |  |  |  | 0.8138% | 551963 | 544123.4415 | 7839.5585 | 2021-01-01 | 2021-12-31 | 2021-04-27 | #N/A | GCCC TICKET NOT REQUIRED AT THIS TIME 1/11/21 CFARIS 1/13/21 GCCC TICKET NOT REQUIRED AT THIS TIME CFARIS 1/26/21 GCCC TICKET NOT REQUIRED FOR THIS JOB CFARIS DID NOT ENTER PREMISE CCC TICKET NOT REQUIRED 3/8/21 CFARIS 3/10/21 GCCC TICKET NOT REQUIRED CFARIS CCC TICKET NOT REQUIRED 3/16/21 CFARIS CCC TICKET NOT REQUIRED 3/18/21 CFARIS CMCHOLAN 4-13-2021 CCC TICKET NOT REQUIRED ON 9/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK. ERX PLACED IN SERVICE ON 9/13/2021 CFARIS
20026978900 | RETIRE GMB SETTING |  |  |  |  | 0% | 0 | 83.3805 | -83.3805 | 2021-01-01 | 2021-12-31 | 2021-09-20 | 2021-09-20 | JOB WAS ON HOLD UNTIL 2021 GCCC TICKET NOT REQUIRED ON 9/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026951300 | INSTALL 6200' OF 2"PMMP MAIN |  |  |  |  | 1.733% | 1175556.48 | 1180648.1173 | -5091.6373 | 2021-01-01 | 2021-12-31 | 2021-01-26 | 2021-05-17
20026979000 | RETIRE SERVICE |  |  |  |  | 0.003613% | 2450.84 | 83.3805 | 2367.4595 | 2021-01-01 | 2021-12-31 | 2021-04-22 | 2021-04-22 | THIS IS PAPER KILL ONLY
21026104600 | RETIRE PIT REG STATION 1016 |  |  |  |  | 0.2785% | 188917.56 | 138142.7376 | 50774.8224 | 2021-01-01 | 2021-12-31 | 2021-04-23 | 2021-05-14 | REMOVED MONITOR AND CONTROL REG. AND BLIND FLANGED, MONITORED 30 MIN. DUE TO NOT BEING ABLE TO BLIND FLANGE BYPASS, ADVISED CONSTRUCTION ABOUT BYPASS CCC 20355 CMCHOLAN RHAYES NGINTER BLONE 4-23-2021 REGULATORS REMOVED AND BLIND FLANGED ON 4/23/2021 PIPING AND VAULT ABANDONED AND REMOVED BY CONSTRUCTION ON 5/12/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/14/2021 GCCC TICKET NOT REQUIRED ON 5/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS TWALKER/KY 11-15-21: LEVEL 2 VARIANCE FORM ADDED TO WMS.DOCS. JOB OVER RUN DUE TO $41,500 FROM LP/OPP MATERIAL CHARGED TO THIS ORDER. ADDITIONAL $11,000 IN COMPANY HIGHER THAN PLANNED ESTIMATE.
21026120900 | INSTALL 5' - 3" PMLP |  |  |  |  | 0.001601% | 1085.98 | 1134.2677 | -48.2877 | 2021-01-01 | 2021-12-31 | 2021-04-26 | 2021-04-26
21026121000 | RETIRE 5' - 3" PMLP |  |  |  |  | 0% | 0 | 58.9085 | -58.9085 | 2021-01-01 | 2021-12-31 | 2021-04-26 | 2021-04-26
21026118700 | EMER-INSTALL 2' OF 2"PMMP MAIN |  |  |  |  | 0.003105% | 2106.1 | 4434.6174 | -2328.5174 | 2021-01-01 | 2021-12-31 | 2021-04-27 | 2021-04-29 | REFERENCE JOB# 21906644500 FOR COMMENTS AND JOB INFO DMARSTO 4/27/21
20026964102 | INSTALL 4000' OF 12"CSHP MAIN |  |  |  |  | 1.542% | 1045900.23 | 909258.0027 | 136642.2273 | 2021-01-01 | 2021-12-31 | 2021-01-06 | 2021-05-11 | TWALKER/KY 09-21-21: JOB OVER RUN DUE TO ADDITIONAL ENVIRONMENTAL AND SITE CLEANUP ON SITE DUE TO RAIN DURING CONSTRUCTION, THIS ADDED EXTRA $40,000 TO CONTRACT COST, PROJECT REQUIRED 2 COMPANY COORDINATORS BUT WAS PLANNED FOR 1 ADDED $35,000 IN LABOR COST AND SEGA INCREASED BY $33,000.
21026118800 | EMER-RETIRE 2' OF 2"PAMP MAIN |  |  |  |  | 0.001113% | 755.09 | 78.808 | 676.282 | 2021-01-01 | 2021-12-31 | 2021-04-27 | 2021-04-29 | REFERENCE JOB# 21906644500 FOR COMMENTS AND JOB INFO DMARSTO 4/27/21
20026964200 | RETIRE 1200' OF 12"BSHP MAIN |  |  |  |  | 0.005312% | 3603.11 | 84.1799 | 3518.9301 | 2021-01-01 | 2021-12-31 | 2021-01-06 | 2021-05-11
18026823200 | INST. FN 164 EXTRA LP OPP |  |  |  |  | 0.07917% | 53697.68 | 24062.1646 | 29635.5154 | 2021-01-01 | 2021-12-31 | 2021-04-27 | 2021-07-07 | TICKET CALLED IN BY JPASLEY NOT ON SITE ROUNDED UP PARTS. GCCC# 19363 CCC# 19363 CCC# 20802 NOT ON SITE CCC# 21442 P2P WITH GAS CONTROL REGULATOR AND ER350 INSTALLED BY WADE SHIMFESSEL ON 4/27/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/21 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026823300 | RET. FN 164 FOR EXTRA LP OPP |  |  |  |  | 0.0003362% | 228.05 | 53.6219 | 174.4281 | 2021-01-01 | 2021-12-31 | 2021-04-27 | 2021-07-07 | REGULATOR REPLACED BY WADE SHIMFESSEL ON 4/27/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/21 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026989800 | INSTALL 800'-2" PMMP |  |  |  |  | 0.04902% | 33245.15 | 25809.9211 | 7435.2289 | 2021-01-01 | 2021-12-31 | 2021-04-22 | 2021-05-10
21026121100 | INSTALL 5' - 4" PMMP |  |  |  |  | 0.003565% | 2417.89 | 2822.803 | -404.913 | 2021-01-01 | 2021-12-31 | 2021-04-28 | 2021-04-28
21026121200 | RETIRE 5' - 4" PMLP |  |  |  |  | 0% | 0 | 58.9085 | -58.9085 | 2021-01-01 | 2021-12-31 | 2021-04-28 | 2021-04-28
20026979300 | RETIRE 12'-8" CSHP |  |  |  |  | 0.00539% | 3655.53 | 134.3805 | 3521.1495 | 2021-01-01 | 2021-12-31 | 2021-04-13 | 2021-04-21
21026108100 | INSTALL 20' OF 3" PMMP |  |  |  |  | 0.1043% | 70757.52 | 21676.4521 | 49081.0679 | 2021-01-01 | 2021-12-31 | 2021-04-12 | 2021-05-06 | AWEBER/KY 09/21/2021: PROXIMITY OF LP MAIN TO MP MAIN RESULTED IN AN ACTUAL FOOTAGE INSTALL OF 320'-PMMP IN ORDER TO SEPERATE AND INSTALL FITTINGS AS NEEDED. UNABLE TO REVISE WMS JO DUE TO UNPAID MATERIAL INVOICES AND JO COMP LETION STATUS AT THE TIME.
21026108200 | RETIRE 20' OF 3" BSMP |  |  |  |  | 6.782e-06% | 4.6 | 56.3197 | -51.7197 | 2021-01-01 | 2021-12-31 | 2021-04-12 | #N/A
19026874200 | INSTALL 4600' OF 2"/4"/6"PMMP |  |  |  |  | 0.2183% | 148082.56 | 193673.3471 | -45590.7871 | 2021-01-01 | 2021-12-31 | 2021-03-17 | 2021-05-13 | TWALKER/KY 11-15-21: PROJECT UNDER RUN WAS DUE TO LESS ROCK ON SITE THAN PL ANNED AND NO STREET/HARD SURFACE REPAIRS REQUIRED THAT LOWER CONTRACT COST BY $25,000. LACK OF ROCK AND HARD SURFACE REPAIRS SPED UP CONSTRUCTION TIME AND LOWER COMPANY COST BY $XXXX AND SEGA WAS $4000 LOWER THAN ESTIMATE. COMPANY COST LOWER BY $3000 THAN ESTIMATE.
20026954500 | INSTALL 72' OF 4"CSHP MAIN |  |  |  |  | 0.07388% | 50107.73 | 48741.5249 | 1366.2051 | 2021-01-01 | 2021-12-31 | 2021-04-12 | #N/A
20026955701 | INSTALL 3,945'-4"/2" PMMP |  |  |  |  | 1.035% | 702217.99 | 724040.648 | -21822.658 | 2021-01-01 | 2021-12-31 | 2021-11-18 | #N/A
21026122500 | EMER-INSTALL 5' OF 4"PMLP MAIN |  |  |  |  | 0.01416% | 9606.89 | 6150.5343 | 3456.3557 | 2021-01-01 | 2021-12-31 | 2021-05-11 | 2021-05-11 | CONTRACTOR HIT 040 PLASTIC MAIN WITH EXCAVATOR. SQUEEZED OFF TO MAKE SAFE. REPLACED 5FT OF 040 P LP. TESTED MAIN FOR 20MINS AT 90LBS.TEST OK.SOAP TEST FINAL TIE INS AT OP. TEST OK.BHB NGF.WORKED WITH CAPITAL JO AND TIE IN PLAN TWALKER/KY 06-28-21: THIS PROJECT WAS GENERATED FROM 3RD PARTY DAMAGE FROM A CONTRACTOR REPLACING STORM/SEWER AT THE INTERSECTION OF MILLER AND 2ND ST. CONTRACTOR DAMAGE SMALL OF MAIN FIRST DAY AND THE VERY NEXT DAY HIT/DA MAGE THE REPAIR MAIN. THAT MAIN WAS NEVER BOOKED OR MAPPED IN WMS. ALL WORK AND COST CAPTURED ON THIS JOB ORDER. WE HAVE TWO TIE INS AND TEST.
21026122700 | EMEG-INSTALL 5' OF 4"PMMP MAIN |  |  |  |  | 0.005686% | 3856.8 | 5607.5343 | -1750.7343 | 2021-01-01 | 2021-12-31 | 2021-05-17 | 2021-05-18 | RESPONDED OT MAIN LINE DAMAGE. INSTALLED 2' OF 4" PE MAIN LINE. PRESSURE TESTED MAIN @ 90PSIG FOR 20MINS PER FOL APPROVAL. TEST OK. SOAP TESTED LAST CONNECTION @ OP. TEST OK. CONTENT VERIFIED. PRESSURE VERIFIED @ 52PSIG DMAL
21026122600 | EMER-RETIRE 5' OF 4"PMLP MAIN |  |  |  |  | 2.919e-05% | 19.8 | 78.808 | -59.008 | 2021-01-01 | 2021-12-31 | 2021-05-10 | 2021-05-11 | CONTRACTOR HIT 040 PLASTIC MAIN WITH EXCAVATOR. SQUEEZED OFF TO MAKE SAFE. REPLACED 5FT OF 040 P LP. TESTED MAIN FOR 20MINS AT 90LBS.TEST OK.SOAP TEST FINAL TIE INS AT OP. TEST OK.BHB NGF.WORKED WITH CAPITAL JO AND TIE IN PLAN
21026122800 | EMER-RETIRE 5' OF 4"PMMP MAIN |  |  |  |  | 0.00031% | 210.25 | 78.808 | 131.442 | 2021-01-01 | 2021-12-31 | 2021-05-17 | 2021-05-18 | RESPONDED TO MAIN LINE DAMAGE. INSTALLED 2' OF 4" PE MAIN LINE. PRESSURE TESTED MAIN @ 90PSIG. FOR 20MINS PER FOL APPROVAL. TEST OK. SOAP TESTED FINAL CONNECTION @ OP. TEST OK. CONTENT VERIFIED. VERIFIED PRESSURE @52PSIG
20026951400 | RETIRE 7600' OF 4"CI/BSLP MAIN |  |  |  |  | 0.0002104% | 142.7 | 165.7874 | -23.0874 | 2021-01-01 | 2021-12-31 | 2021-01-25 | #N/A
20026953701 | INSTALL 6100' OF 2"/4"PMMP |  |  |  |  | 2.427% | 1646234.22 | 1430757.5003 | 215476.7197 | 2021-01-01 | 2021-12-31 | 2021-10-14 | #N/A | TWALKER/KY 05-04-22: JOB OVER RUN DUE TO $65,000 SPEND ON OFF DUTY POLICE DUE TO HIGH CRIME/TRAFFIC AREA, STATE REQUIRED MILL/PAVING OF HOLME ST INCREASED CONTRACT COST BY $85,000. SEGA INCREASED BY $51,000 OVER EST.
21026104400 | INSTALL 2"SS TO RETIRE INLET |  |  |  |  | 0.03614% | 24511.65 | 37406.9466 | -12895.2966 | 2021-01-01 | 2021-12-31 | 2021-05-10 | 2021-05-13
21026123600 | REPLACE MAIN - LEAKAGE D253626 |  |  |  |  | 0.003998% | 2711.68 | 5432.0527 | -2720.3727 | 2021-01-01 | 2021-12-31 | 2021-05-12 | 2021-05-13
21026123700 | EMER 10'-2" PMLP |  |  |  |  | 0% | 0 | 85.0408 | -85.0408 | 2021-01-01 | 2021-12-31 | 2021-05-12 | 2021-05-13
21026118000 | INSTALL 4" SS |  |  |  |  | 0.02008% | 13617.82 | 29193.606 | -15575.786 | 2021-01-01 | 2021-12-31 | 2021-05-13 | 2021-05-14 | 4"SHORTSTOP INSTALLET BY RLA TESTED AND TAPPED BYCOMPANY 90 PSIG 15 MIN TEST NITROGN AS MEDIUM
21026104500 | RETIRE 7' OF 2"BSMP MAIN |  |  |  |  | 0.0001071% | 72.67 | 80.8842 | -8.2142 | 2021-01-01 | 2021-12-31 | 2021-05-10 | 2021-05-13
18026837600 | INST. FN 176 EXTRA LP OPP |  |  |  |  | 0.08815% | 59791.79 | 35378.1646 | 24413.6254 | 2021-01-01 | 2021-12-31 | 2021-05-13 | 2021-07-07 | CONTROL SHEET 008281 PAID ON 04/23/20 THURSDAY TO COVER 04/24/20 FRIDAY CONTROL SHEET008307 PAID ON 04/30/20 THURSDAY TO COVER 05/01/20 FRIDAY NOT ON SITE GETTING PARTS FOR JOB CCC# 23134 CCC# 23265 CCC# 23459 CCC# 25857 REGULATORS INSTALLED BY WADE SHIMFESSEL ON 5/13/2021 EC350 INSTALLED BY WADE SHIMFESSEL ON 5/14/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/2021 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS *EXISTING Y STRAINER STRAINER GASKET NOT INSTALLED
18026837700 | RET. FN 176 FOR EXTRA LP OPP |  |  |  |  | 0% | 0 | 53.9767 | -53.9767 | 2021-01-01 | 2021-12-31 | 2021-05-13 | 2021-07-07 | REGULATORS REPLACED BY WADE SHIMFESSEL ON 5/13/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/2021 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026124400 | EMER-INSTALL 2' OF 2"PMMP |  |  |  |  | 0.002168% | 1470.21 | 2935.5264 | -1465.3164 | 2021-01-01 | 2021-12-31 | 2021-06-30 | 2021-06-30
21026124500 | EMER-RETIRE 2' OF 2"PMMP |  |  |  |  | 0% | 0 | 85.0408 | -85.0408 | 2021-01-01 | 2021-12-31 | 2021-06-30 | 2021-06-30
21026117900 | INSTALL 575' OF 2"PMIP MAIN |  |  |  |  | 0.0231% | 15668.74 | 17428.325 | -1759.585 | 2021-01-01 | 2021-12-31 | 2021-06-09 | 2021-06-09 | TWALKER/KY 06-28-21: THIS 555 WAS COMPLETED IN THE FIELD BUT PAPERWORK NOT COMPLETED OR MAPPED WHEN A CONTRACTOR DAMAGED A SECTION OF THIS NEW GAS MAIN. ALL WORK AND COST INCLUDED IN THIS JOB ORDER AND THE REASON FOR TWO TIE IN PLANS AND TEST FORMS.
21026122200 | INSTALL 925' OF 2"PMMP MAIN |  |  |  |  | 0.06191% | 41992.33 | 32784.4942 | 9207.8358 | 2021-01-01 | 2021-12-31 | 2021-06-09 | 2021-06-09 | TWALKER/KY 06-28-21: THIS 555 PROJECT WAS COMPLETED IN FIELD BUT PAPERWORK NOT SUBMITTED TO CLOSE OR MAPPEND WHEN LEAK ON THE NEW MAIN WAS DETECTED. WE BELIEVE THE MAIN LINE WAS DAMAGED DURING BACK FIELD. LEAK WAS REPAIRED BY CONSTRUCTION THAT IS REASON FOR TWO TIE IN PLANS AND TEST FORMS.ALL COST AND WORK CAPTURED UNDER THIS JOB ORDER.
21026112700 | INSTALL 350' OF 2"PMIP MAIN |  |  |  |  | 0.05489% | 37226.93 | 19281.66 | 17945.27 | 2021-01-01 | 2021-12-31 | 2021-05-27 | 2021-06-11
21026121700 | INSTALL 10' OF 6"PHHP MAIN |  |  |  |  | 0.02129% | 14437.27 | 16348.9255 | -1911.6555 | 2021-01-01 | 2021-12-31 | 2021-06-03 | 2021-06-07
20026982200 | INSTALL 5'-4"PMMP & 4'-4"CS |  |  |  |  | 0.06039% | 40958.2 | 42642.7946 | -1684.5946 | 2021-01-01 | 2021-12-31 | 2021-05-25 | 2021-06-08
21026121800 | RETIRE 10' OF 6"PHHP MAIN |  |  |  |  | 0% | 0 | 80.3582 | -80.3582 | 2021-01-01 | 2021-12-31 | 2021-06-07 | 2021-06-07
20026982300 | ABANDON 5' - 4" CSMP |  |  |  |  | 1.589e-05% | 10.78 | 183.2963 | -172.5163 | 2021-01-01 | 2021-12-31 | 2021-06-07 | 2021-06-08
19026856900 | RETIRE 2166'- 2"-6" P/CS/BS |  |  |  |  | 0.0006914% | 468.94 | 94.7274 | 374.2126 | 2021-01-01 | 2021-12-31 | 2021-03-04 | 2021-07-01
20026945400 | RETIRE 1431'-2"-4" BSLP |  |  |  |  | 0.001572% | 1066.35 | 94.7274 | 971.6226 | 2021-01-01 | 2021-12-31 | 2021-03-03 | 2021-06-10 | ABANDONMENTS OF MAINLINE WERE DONE WITH JO# 20-0269755-00.
21026121600 | INSTALL 100'-2" PMIP |  |  |  |  | 0.02433% | 16499.56 | 13861.3812 | 2638.1788 | 2021-01-01 | 2021-12-31 | 2021-06-09 | 2021-06-14
20026975300 | RETIRE 1900' OF 6"BSLP MAIN |  |  |  |  | 0.002109% | 1430.35 | 64.0836 | 1366.2664 | 2021-01-01 | 2021-12-31 | 2021-01-08 | 2021-06-11
20026985200 | INSTALL 6" PCF |  |  |  |  | 0.01456% | 9877.17 | 16280.811 | -6403.641 | 2021-01-01 | 2021-12-31 | 2021-06-12 | 2021-06-12
20026985300 | RETIRE 300'-6" CSMP |  |  |  |  | 0.0001052% | 71.35 | 88.4533 | -17.1033 | 2021-01-01 | 2021-12-31 | 2021-06-02 | 2021-07-01
21026102900 | INSTALL 2400' OF 4"PMMP MAIN |  |  |  |  | 0.1537% | 104251.17 | 80646.5708 | 23604.5992 | 2021-01-01 | 2021-12-31 | 2021-05-20 | 2021-06-15
21026128500 | NSP - INSTALL 150'-2" PMLP |  |  |  |  | 0.01497% | 10156.16 | 16760.5972 | -6604.4372 | 2021-01-01 | 2021-12-31 | 2021-06-15 | 2021-06-15 | INSTALLED 150' 2"P. PRESSURE TESTED 90LBS 1HR. SOAP TESTED 2" EF COUPLING AT OP. PRESS. (11 IWC) 15MIN. PRESS. TEST 2X1 MONITORING TEE 90LBS 15MIN. SOAP TESTED MONITORING TEE END CAP OP. PRESS (11 IWC) 15MIN.
21026125400 | INSTALL 28' 4" PMMP |  |  |  |  | 0.0297% | 20147.11 | 10969.2814 | 9177.8286 | 2021-01-01 | 2021-12-31 | 2021-06-04 | 2021-06-15
21026125600 | INSTALL 28' 8" PMLP |  |  |  |  | 0.03432% | 23277.54 | 11805.2814 | 11472.2586 | 2021-01-01 | 2021-12-31 | 2021-06-04 | 2021-06-15
21026110600 | RETIRE 600'-2&3" PMLP |  |  |  |  | 0.001034% | 701.12 | 21928.4488 | -21227.3288 | 2021-01-01 | 2021-12-31 | 2021-07-08 | 2021-11-18
21026125500 | RETIRE 20' OF 4" PMMP |  |  |  |  | 0% | 0 | 91.2676 | -91.2676 | 2021-01-01 | 2021-12-31 | 2021-06-07 | 2021-06-15
21026125700 | RETIRE 20' 8" PMLP |  |  |  |  | 0.0001052% | 71.35 | 91.2676 | -19.9176 | 2021-01-01 | 2021-12-31 | 2021-06-15 | 2021-06-15
17026699800 | INSTALL ELEVATED BUS STOP ASSM |  |  |  |  | 0.0141% | 9561.04 | 61743.3758 | -52182.3358 | 2021-01-01 | 2021-12-31 | 2021-06-17 | 2021-08-17 | UNDERRUN EXPLANATION: THIS JOB ORDER WAS WORKED IN ONJUNCTION WITH ANOTHER JOB ORDER, 17-0269850-00, WHICH OVERRAN DUE TO THE CONTRACT LABOR BEING CHA RGED TO THAT JOB ORDER INSTEAD. THAT AMOUNT WAS APPROXIMATELY $40,000.
18026752700 | INSTALL VRG PILOT |  |  |  |  | 0.007908% | 5363.35 | 5404.3267 | -40.9767 | 2021-01-01 | 2021-12-31 | 2021-08-17 | 2021-08-17 | CCC #27769 CCC #28734
18026752800 | RETIRE |  |  |  |  | 0.001236% | 838.05 | 52.1634 | 785.8866 | 2021-01-01 | 2021-12-31 | 2021-08-17 | 2021-08-17
17026699900 | INSTALL NEW CH LINK FENCING |  |  |  |  | 0% | 0 | 20572.3069 | -20572.3069 | 2021-01-01 | 2021-12-31 | 2021-06-17 | 2021-08-17
17026698500 | INSTALL VRG PRESS CONT EQUIPMT |  |  |  |  | 0.3653% | 247791.39 | 128512.8191 | 119278.5709 | 2021-01-01 | 2021-12-31 | 2021-06-11 | 2021-08-17 | CC# 27659. 6/11/21 DSASH CCC #27659 CC# 27769. 6/14/21 DSASH CC# 27972. 6/16/21 DSASH CC# 28248. 6/17/21 DSASH CCC #28248 CCC #28445 CC# 28445. 6/18/21 DSASH CC# 28787. 6/23/21 DSASH CCC #28787 NOT AT STATION OFF SITE WORKING ON PAPERWORK FOR JOB 7/1/2021 GCCC TICKET NOT REQUIRED NOT AT STATION OFF SITE COMPLETING PAPERWORK 7/19/21 AND 8/17/21 CFARIS
17026698600 | RETIRE EXIST PRESS CONT EQUIPM |  |  |  |  | 0.0004414% | 299.36 | 131.3267 | 168.0333 | 2021-01-01 | 2021-12-31 | 2021-08-17 | 2021-08-17
19026856800 | INSTALL 3659'-2",4"&6" PMMP |  |  |  |  | 1.931% | 1309555.48 | 1978069.5146 | -668514.0346 | 2021-01-01 | 2021-12-31 | 2020-11-04 | 2021-06-28 | W. 2ND ST SEING TIES WILL NEED TO BE UPDATED ONCE ROAD CONSTRUCTION PROJECT IS COMPLETE. ALL POLES AND MANHOLES ARE BEING MOVED. OVERRUN EXPLANATION HAS BEEN COMPLETE AND LOADED INTO WMSDOCS WORKSPACE. D. LEMONS 12/23/2021
21026117400 | INSTALL 190' - 4" PMMP SL |  |  |  |  | 0.05912% | 40096.06 | 22441.9346 | 17654.1254 | 2021-01-01 | 2021-12-31 | 2021-06-14 | #N/A | INSTALLED 243'OF 4"PMP FOR SL TO FEED PSID 501307207-CAPPED AND BURRIED END OF SL FOR FUTURE TIE IN/INSTALLATION OF RISER AND SETTING ONCE FURTHER SITE CONSTRUCTION IS COMPLETED,PER CG ENGINEER J TOY AND CONSTRUCTION SITE GC- LINE MARKER WITH WIRE AT TAP,WIRE IN VALVE BOX,AND MARKER BALLS AT ALL CHANGES OF DIRECTIONAND END OF SL INSTALLED FOR LOCATABILITY
18026781701 | INSTALL MONITOR/CONTROL REGS |  |  |  |  | 0.2085% | 141447.12 | 99301.7623 | 42145.3577 | 2021-01-01 | 2021-12-31 | 2021-06-05 | 2021-06-22 | CCC TICKET 27187 CCC #27342 CCC #27472 CCC #27636 CCC #27973 CCC TICKET NOT REQUIRED NOT AT STATION 8/4/21
18026781800 | ABANDON REGULATORS |  |  |  |  | 0% | 0 | 56.3894 | -56.3894 | 2021-01-01 | 2021-12-31 | 2021-06-22 | 2021-06-22
19026860400 | INSTALLING I&C EQUIPMENT |  |  |  |  | 0.2575% | 174669.84 | 222748.2628 | -48078.4228 | 2021-01-01 | 2021-12-31 | 2021-06-09 | 2022-08-22 | CCC #27973 CCC #28142 CCC # 28275 CCC #28378 CCC #28665 CCC TICKET NOT REQUIRED NOT AT STATION 8/4/21
19026860500 | RETIRE I&C EQUIPMENT |  |  |  |  | 0.0007539% | 511.34 | 84.9756 | 426.3644 | 2021-01-01 | 2021-12-31 | 2022-08-22 | 2022-08-22 | CC# 78206
21026110100 | INSTALL 900' OF 2"PMMP MAIN |  |  |  |  | 0.03566% | 24183.42 | 26234.9875 | -2051.5675 | 2021-01-01 | 2021-12-31 | 2021-06-16 | 2021-06-23
21026131001 | EMER-INSTALL 10' OF 2"PMMP |  |  |  |  | 0.05108% | 34645.29 | 34334.8702 | 310.4198 | 2021-01-01 | 2021-12-31 | 2021-06-22 | 2021-06-23
20026930800 | UPGRADE ELECTRONICS |  |  |  |  | 0.006847% | 4644.07 | 3038 | 1606.07 | 2021-01-01 | 2021-12-31 | 2021-06-21 | 2021-07-06 | REPLACED EFC NON SCADA MONITORED GMB ACCOUNT GCCC TICKET NOT REQUIRED
21026131300 | RETIRE EFC UNIT |  |  |  |  | 0% | 0 | 74.8797 | -74.8797 | 2021-01-01 | 2021-12-31 | 2024-06-23 | 2021-07-06 | REPLACED EFC
21026122300 | INSTALL 100'-2" PMMP |  |  |  |  | 0.03973% | 26947.59 | 25260.7035 | 1686.8865 | 2021-01-01 | 2021-12-31 | 2021-06-16 | 2021-06-25
21026110500 | RETIRE 94'-12" CSMP |  |  |  |  | 0.0002104% | 142.7 | 85.5775 | 57.1225 | 2021-01-01 | 2021-12-31 | 2021-06-28 | 2021-06-30
21026117800 | RETIRE 117' - 4" PLP |  |  |  |  | 0.01711% | 11604.62 | 9954.0712 | 1650.5488 | 2021-01-01 | 2021-12-31 | 2021-06-28 | 2021-06-28 | ABN 102' OF 040 PL ML. TESTED 4' OF 040 W/ END CAPS FOR 1 HR @ 90# SOAP TESTED CONN PTS @ 11" WC. SOAP TESTED ALL TEE CAP AND END CAPS @ OP.
20026942700 | INSTALL I&C EQUIPMENT |  |  |  |  | 0.02302% | 15613 | 16155.4774 | -542.4774 | 2021-01-01 | 2021-12-31 | 2021-06-28 | 2021-12-10 | CCC # 28876 CC#29408. 6/28/21 DSASH CCC # 32222 INITIAL COMMISSIONING BY SHANE GIORDANO PAPERWORK COMPLETED BY CYNTHIA FARIS ON 12/10/21 PAPERWORK ON HOLD AWAITING ISO SKETCH
21026130200 | EMER-INSTALL 5'-2" PMIP/CSIP |  |  |  |  | 0.01114% | 7558.85 | 6178.4541 | 1380.3959 | 2021-01-01 | 2021-12-31 | 2023-03-24 | 2023-03-31
21026130300 | EMER-RETIRE 5'-2" BSIP |  |  |  |  | 0.0003402% | 230.72 | 410.7144 | -179.9944 | 2021-01-01 | 2021-12-31 | 2023-03-31 | 2023-03-31
21026110400 | INSTALL 100'-12" CSMP |  |  |  |  | 0.2782% | 188696.44 | 142453.0552 | 46243.3848 | 2021-01-01 | 2021-12-31 | 2021-06-03 | 2021-06-30 | OVERRUN EXPLANATION: PROJECT OVERRAN DUE TO FLAGGER TIME AND FLAGGER OVERTI ME. BUDGET VARIANCE EXPLANATION FORM LOADED INTO WMSDOCS WORKSPACE. D.LEMONS 12 /3/2021
20026942200 | RETIRE GAUGE |  |  |  |  | 0% | 0 | 91.4991 | -91.4991 | 2021-01-01 | 2021-12-31 | 2021-07-12 | 2021-07-12 | RETIRED PAPER RECORDING GAUGE AND INSTALLED ERX WORK COMPLETED ON 909 JOB ORDER WITH GCCC TICKET NUMBER 29962 GCCC TICKET NOT REQUIRED ON 7/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026942100 | INSTALL I&C EQUIPMENT |  |  |  |  | 0.02418% | 16401.86 | 16155.4774 | 246.3826 | 2021-01-01 | 2021-12-31 | 2021-06-29 | 2021-07-12 | CCC #29962 CCC #30339 INSTALLED ERX, RV50 MODEM, BATTERY AND SUPER SOLAR KIT GCCC TICKET NOT REQUIRED ON 7/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026941700 | RETIRE GAUGE |  |  |  |  | 0% | 0 | 91.4991 | -91.4991 | 2021-01-01 | 2021-12-31 | 2021-12-10 | 2021-12-10 | ERX INSTALLED AND PAPER RECORDING GAUGE RETIRED BY DANNY ASH AND JOSH MULLINS PAPERWORK COMPLETED BY CYNTHIA FARIS PAPERWORK ON HOLD AWAITING CORRECT ISO SKETCH
20026941600 | INSTALL I&C EQUIPMENT |  |  |  |  | 0.01657% | 11237.56 | 16155.4774 | -4917.9174 | 2021-01-01 | 2021-12-31 | 2021-06-30 | 2021-12-10 | CC# 30132. ERX INSTALLED BY DANNY ASH AND JOSH MULLINS PAPERWORK COMPLETED BY CYNTHIA FARIS PAPERWORK ON HOLD AWAITING CORRECT ISO SKETCH
21026116900 | INSTALL 200'-2" PMLP |  |  |  |  | 0.03655% | 24792.54 | 39229.3021 | -14436.7621 | 2021-01-01 | 2021-12-31 | 2021-06-28 | 2021-07-06
21026123100 | INSTALL 175'-4" PMMP |  |  |  |  | 0.07949% | 53913.76 | 39889.572 | 14024.188 | 2021-01-01 | 2021-12-31 | 2021-06-24 | 2021-07-07
21026123200 | RETIRE 200'-4" BSMP |  |  |  |  | 0% | 0 | 77.7619 | -77.7619 | 2021-01-01 | 2021-12-31 | 2021-07-07 | 2021-07-07
20026949900 | INSTALL 1100' - 2" PMMP |  |  |  |  | 0.3052% | 206985.91 | 207915.8181 | -929.9081 | 2021-01-01 | 2021-12-31 | 2021-05-25 | 2021-07-15
21026125200 | INSTALL 3" SS |  |  |  |  | 0.007388% | 5010.94 | 20373.572 | -15362.632 | 2021-01-01 | 2021-12-31 | 2021-07-08 | 2021-07-08
21026125100 | RETIRE 175' - 3" LP |  |  |  |  | 0% | 0 | 88.1542 | -88.1542 | 2021-01-01 | 2021-12-31 | 2021-07-08 | 2021-07-08
21026118600 | INSTALL 600' OF 2"PMMP MAIN |  |  |  |  | 0.09591% | 65051.29 | 37159.65 | 27891.64 | 2021-01-01 | 2021-12-31 | 2021-06-23 | 2021-07-13
19026856100 | RETIRE GAUGE |  |  |  |  | 0% | 0 | 73.6972 | -73.6972 | 2021-01-01 | 2021-12-31 | 2021-09-20 | 2021-09-20 | WAITING ON PE APPROVAL AND ISO SKETCH CCC TICKET NOT REQUIRED ON 9/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026110900 | INSTALL REPLACEMENT FENCE |  |  |  |  | 0.007329% | 4971.16 | 44982.9906 | -40011.8306 | 2021-01-01 | 2021-12-31 | 2021-06-28 | 2021-07-09 | CCC# 30433 MONITORED FENCE INSTALLATION CCC# 30433 CCC# 30596 CC# 30596 MONTOR STATION CCC# 30956 NEW FENCE INSTALLED WSHIMFESSEL 07-09-2021 UNDERRUN EXPLANATION: COST WAS SIGNIFICANTLY LESS THAT WHAT THE CONTRACTOR HAD ESTIMATED OVER THE PHONE.
20026942000 | INSTALL I&C EQUIPMENT |  |  |  |  | 0.02091% | 14182.01 | 16155.4774 | -1973.4674 | 2021-01-01 | 2021-12-31 | 2021-07-09 | 2021-09-20 | CCC# 30920 CCC TICKET NOT REQUIRED ON 9/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026977101 | INSTALL 11,500' OF 2"/4"PMMP |  |  |  |  | 1.686% | 1143604.07 | 926814.1047 | 216789.9653 | 2021-01-01 | 2021-12-31 | 2021-04-27 | 2021-12-15 | TWALKER/KY 03-02-22: PROJECT COST OVER RUN DUE TO ADDITIONAL CONSTRUCTION COORINATOR ON SITE DURING CONSTRUCTION ADDED $65,000 IN LABOR COST, SEWER VIDEO FOR MAIN/SL BY BUCHANAN WAS $86,000 HIGHER THAN ESTIMATE, ADDITIONAL FLAGGING AND HARD SURFACE REPAIRS ADDED $25,000 TO CONTRACT COST. FINALLY SEGA WAS $35,000 HIGHER THAT PLANNED COST.
21026109600 | INSTALL 351'-2" PMMP |  |  |  |  | 0.04216% | 28594.76 | 20339.7093 | 8255.0507 | 2021-01-01 | 2021-12-31 | 2021-07-12 | 2021-07-15
20026950000 | RETIRE 1430' OF 2"/3" BS-MP |  |  |  |  | 0.00369% | 2502.68 | 81.9085 | 2420.7715 | 2021-01-01 | 2021-12-31 | 2021-07-14 | 2021-07-15
20026942800 | RETIRE GAUGE |  |  |  |  | 0% | 0 | 91.4991 | -91.4991 | 2021-01-01 | 2021-12-31 | 2021-07-16 | 2021-12-10 | PAPERWORK COMPLETION ON HOLD AWAITING ISO SKETCH
21026127800 | INSTALL 500'-2" PMMP |  |  |  |  | 0.06943% | 47089.22 | 43810.3768 | 3278.8432 | 2021-01-01 | 2021-12-31 | 2021-07-14 | 2021-07-22
21026124600 | INSTALL 3" OUTLET VALVE |  |  |  |  | 0.04218% | 28606.82 | 34892.3468 | -6285.5268 | 2021-01-01 | 2021-12-31 | 2021-07-13 | 2021-07-19
21026124700 | RETIRE 4' OF 3"BSIP MAIN |  |  |  |  | 0% | 0 | 86.5975 | -86.5975 | 2021-01-01 | 2021-12-31 | 2021-07-19 | 2021-07-19
21026123300 | INSTALL 125'-2" PMMP |  |  |  |  | 0.05442% | 36910.92 | 28847.4767 | 8063.4433 | 2021-01-01 | 2021-12-31 | 2021-07-12 | 2021-07-20
21026123400 | RETIRE 160'-4" PMMP |  |  |  |  | 0% | 0 | 77.7619 | -77.7619 | 2021-01-01 | 2021-12-31 | 2021-07-16 | 2021-07-20
21026124800 | INSTALL INLET/OUTLET BLOCK VLV |  |  |  |  | 0.02999% | 20343.89 | 13873.2524 | 6470.6376 | 2021-01-01 | 2021-12-31 | 2021-07-08 | 2021-07-19 | CCC# 30839 CCC# 31113 CCC# 31169 IN PROGRESS CCC# 31169 CC# 31169 CC-31326 CC-31492 CCC# 31755 CC-31755 NOT ON SITE- OFFICE ISO UPDATE CAP WORK COMPLETED BY WADE SHIMFESSEL ON 7/19/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/21/20 GCCC TICKET NOT REQUIRED ON 7/21/20 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS 7/21/20
21026113600 | RETIRE INLET/OUTLET BLK VALVES |  |  |  |  | 0% | 0 | 88.1542 | -88.1542 | 2021-01-01 | 2021-12-31 | 2021-07-19 | 2021-07-19 | JOB COMPLETED BY WADE SHIMFESSEL ON 7/19/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/21/21 GCCC TICKET NOT REQUIRED ON 7/21/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026993100 | RETIRE 229' - PMMP |  |  |  |  | 0% | 0 | 103.8156 | -103.8156 | 2021-01-01 | 2021-12-31 | 2021-07-20 | 2021-11-12
20026971100 | INSTALL 3300' OF 2"/4"PMMP MN |  |  |  |  | 1.114% | 755817.87 | 877421.2279 | -121603.3579 | 2021-01-01 | 2021-12-31 | 2021-05-12 | 2022-03-18 | TWALKER/KY 05-04-22: JOB ORDER RUN DUE TO NO PAVING/HARD SURFACE REPAIRS HA VE BEEN STARTED AT THIS TIME. THIS IS JOINT PAVING RESTORATION WITH CITY OF LEXINGTON AND KY AMERICAN WATER. LOOK FOR COST TO BOOK LATE SUMMER 2022
21026137100 | RETIRE 4'-8" BSLP |  |  |  |  | 0% | 0 | 177.6312 | -177.6312 | 2021-01-01 | 2021-12-31 | 2021-07-23 | 2021-08-18
21026132100 | INSTALL 600'-4" PMMP |  |  |  |  | 0.1108% | 75178.06 | 159985.8979 | -84807.8379 | 2021-01-01 | 2021-12-31 | 2021-07-22 | 2021-10-01 | INSTALLED 573' OF 4" PL MP AND 9' OF 2" PL MP TESTED 90 PSIG 2 HRS SOAP TESTED FINAL CONN OP 44 PSIG UNDERRUN EXPLANATION: A SIGNIFICANT UNIT OF COST WAS THE PLANNED ROCK BORE BUT THE CREW WAS ABLE TO AVOID THE NEED FOR A ROCK BORE, THE JOB DURATION ESTIMATE TOOL ALSO PLANNED FOR 120 HOURS OF LABOR AND THE CREW COMPLETED THE JOB IN 60 HOURS AND SOME CREW MEMBERS WERE NOT NEEDED THE ENTIRE DURATION OF THE JOB.
21026132200 | RETIRE 450'-4" P-MP |  |  |  |  | 0.0003138% | 212.81 | 875.427 | -662.617 | 2021-01-01 | 2021-12-31 | 2021-08-19 | 2021-10-01 | RETIRED 487' OF 4" PL MP
18026808800 | INST. FN 259 EXTRA LP OPP |  |  |  |  | 0.3811% | 258499.79 | 23795.1646 | 234704.6254 | 2021-01-01 | 2021-12-31 | 2021-07-07 | 2021-08-02 | NOT ONSITE. NO GCCC TICKET REQUIRED. CMCOX 7/6/21 GCCC# 30701 CMCOX 7/7/21 NOT ONSITE. NO GCCC TICKET REQUIRED. CMCOX 7/8/21 CCC# 31111 GCCC# 31231 CMCOX 7/13/21 GCCC# 31380 GCCC# 31536 GCCC# 31616 DID NOT ENTER PIT. NO GCCC# REQUIRED. CMCOX 7/19//21 GCCC# 31756 CMCOX 7/20/21 CC# 32093 REGULATORS INSTALLED BY CHRIS COX 7/27/21 PAPERWORK COMPLETED BY CFARIS 7/29/21 CCC# NOT REQUIRED BY CFARIS ON 7/29 OR 8/2 NOT AT STATION
18026808900 | RET. FN 259 FOR EXTRA LP OPP |  |  |  |  | 0% | 0 | 53.9767 | -53.9767 | 2021-01-01 | 2021-12-31 | 2021-07-27 | 2021-07-29 | REGULATORS REPLACED BY CHRIS COX ON 7/27/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/29/2021 GCCC TICKET NOT REQUIRED ON 7/29/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026110700 | REPLACE FENCE |  |  |  |  | 0.0007091% | 480.98 | 14980.1771 | -14499.1971 | 2021-01-01 | 2021-12-31 | 2021-07-29 | 2021-12-17 | CCC# 33097 - BLONE - 07/29/21 FENCE REPLACED BY INTERSTATE FENCE COMPANY PAPERWORK COMPLETED BY CYNTHIA FARIS ON 12/17/2021
21026111101 | INSTALL FENCE |  |  |  |  | 0.008259% | 5601.7 | 40000.9906 | -34399.2906 | 2021-01-01 | 2021-12-31 | 2021-07-29 | 2021-12-16 | CCC# 31858 , 31996 , 32095 , 32237 , 32396 , 32702 ALL USED DURING PROJECT BLONE - 07/29/21 FENCE INSTALLED BY INTERSTATE FENCE COMPANY PAPERWORK COMPLETED BY CYNTHIA FARIS 12/16/21 UNDERRUN EXPLANATION: THE COST ESTIMATE THAT THE CONTRACTOR PROVIDED TURNED OUT TO BE SIGNIFICANTLY LESS THAN THEY HAD ESTIMATED. GES 3/2/22
21026110800 | RETIRE FENCE |  |  |  |  | 0% | 0 | 61.2976 | -61.2976 | 2021-01-01 | 2021-12-31 | 2021-12-17 | 2021-12-17 | FENCE REPLACED BY INTERSTATE FENCE COMPANY PAPERWORK COMPLETED BY CYNTHIA FARIS 12/17/2021
21026111200 | RETIRE FENCE |  |  |  |  | 0% | 0 | 61.2976 | -61.2976 | 2021-01-01 | 2021-12-31 | 2021-12-16 | 2021-12-16 | FENCE REPLACED BY INTERSTATE FENCE COMPANY PAPERWORK COMPLETED BY CYNTHIA FARIS 12/16/21
21026125800 | REPLACE C18-5 E |  |  |  |  | 0.1428% | 96855.51 | 77241.44 | 19614.07 | 2021-01-01 | 2021-12-31 | 2021-07-07 | 2021-07-30
21026125900 | RETIRE C18-5 |  |  |  |  | 5.687e-05% | 38.57 | 91.2676 | -52.6976 | 2021-01-01 | 2021-12-31 | 2021-08-10 | 2021-07-30
21026122900 | INSTALL 8" SS |  |  |  |  | 0.07193% | 48788.62 | 30904.4019 | 17884.2181 | 2021-01-01 | 2021-12-31 | 2021-07-28 | 2021-07-30
20026981601 | INSTALL 9,950' OF 2"/4"/6"PMMP |  |  |  |  | 5.127% | 3477462.23 | 3261487.9737 | 215974.2563 | 2021-01-01 | 2021-12-31 | 2022-05-23 | 2022-05-26
22026190700 | INSTALL 4" SS *PAPER ONLY*** |  |  |  |  | 0% | 0 | 84.2578 | -84.2578 | 2021-01-01 | 2021-12-31 | 2021-08-02 | 2021-08-02 | FACILITY CREATED ON JO 20-0269816-01. UNABLE TO EDIT. SS ALREADY ABANDONED ON JO 22-0261909-00 BEFORE THIS JO WAS CREATED.
21026123800 | INSTALL 160'-4" CSLP/PMLP |  |  |  |  | 0.1268% | 86016.2 | 161313.4069 | -75297.2069 | 2021-01-01 | 2021-12-31 | 2021-07-26 | 2021-08-09 | UNDERRUN EXPLANATION: SIGNIFICANTLY LESS HARD SURFACE RESTORATION AND BACKFILL REQUIRED THAN ESTIMATED KYTC REQUIRED RELOCATION AND TOLD US NOT TO WORRY ABOUT THE MILL & OVERLAY THAT THEY WOULD DO THAT WHEN THEY COMPLETED THEIR PART OF THE PROJECT, THIS RESULTED IN A SIGNIFICANT AMOUNT OF THE COST VARIATION
21026135400 | INSTALL 100'-4" PL SL |  |  |  |  | 0.01809% | 12266.69 | 10216.5972 | 2050.0928 | 2021-01-01 | 2021-12-31 | 2021-08-04 | 2021-08-06
21026135300 | ABANDON 120'-4" PL SL |  |  |  |  | 0% | 0 | 82.634 | -82.634 | 2021-01-01 | 2021-12-31 | 2021-08-04 | 2021-08-05
21026125300 | RETIRE 180'-4" BSLP |  |  |  |  | 0% | 0 | 282.1429 | -282.1429 | 2021-01-01 | 2021-12-31 | 2021-08-04 | 2021-08-07 | COMMITT DATE WAS PUSHED OUT TILL END OF AUG.2021
20026981200 | INSTALL 1550' OF 2"PMMP MAIN |  |  |  |  | 0.7073% | 479750.56 | 414073.7744 | 65676.7856 | 2021-01-01 | 2021-12-31 | 2021-08-10 | 2021-09-28 | TWALKER/KY 05-04-22: JOB OVER RUN CAUSED BY ADDTIONAL $46,000 FOR SEWER CAMERA WORK, PROJECT TOOK LONGER TO COMPLETE DUE TO TRAFFIC AND URBAN SETTING INCREASED COMPANY LABOR BY $5000, SEGA $17000 HIGHER THAN ESTIMATE.
21026136100 | EMER-INSTALL 10'-2" PMMP |  |  |  |  | 0.005402% | 3664.07 | 5241.7163 | -1577.6463 | 2021-01-01 | 2021-12-31 | 2021-08-10 | 2021-08-10
21026136200 | EMER-RETIRE 10'-2" PMP |  |  |  |  | 0.0003736% | 253.41 | 88.8156 | 164.5944 | 2021-01-01 | 2021-12-31 | 2021-08-10 | 2021-08-10 | RETIRED 2' OF DAMAGED 2" PMP MAIN
21026134400 | RETIRE 98' OF 2"PMMP MAIN |  |  |  |  | 0.00686% | 4653.06 | 3547.617 | 1105.443 | 2021-01-01 | 2021-12-31 | 2021-08-10 | 2021-08-10
21026132600 | INSTALL NEW TRANSMITTERS |  |  |  |  | 0.02122% | 14392.01 | 15506.2901 | -1114.2801 | 2021-01-01 | 2021-12-31 | 2021-08-11 | 2021-12-10 | CCC #34292 WAITING ON ISO
21026132700 | RETIRE DAMAGED TRANSMITTERS |  |  |  |  | 0% | 0 | 82.634 | -82.634 | 2021-01-01 | 2021-12-31 | 2021-08-11 | 2021-12-10 | WAITING ON ISO SKETCH REPLACED TRANSMITTERS AND RV50 DAMAGED BY LIGHTENING
21026121900 | INSTALL 100'-2" PMIP |  |  |  |  | 0.04535% | 30760.67 | 26223.5353 | 4537.1347 | 2021-01-01 | 2021-12-31 | 2021-08-09 | 2021-08-13
21026130600 | INSTALL 350' OF 2"PMMP MAIN |  |  |  |  | 0.06288% | 42649.02 | 31312.2411 | 11336.7789 | 2021-01-01 | 2021-12-31 | 2021-08-03 | 2021-08-17
21026136800 | EMER-INSTALL 5' OF 4"PMMP |  |  |  |  | 0.0005837% | 395.9 | 5949.1348 | -5553.2348 | 2021-01-01 | 2021-12-31 | 2021-08-17 | 2021-08-24 | INST 5' 4" P MP MAIN ACCORDING TO ENGINEERED TIE-IN PLAN AND GAS STANDARDS. WORKED ON 8/17/21. MCRAIG 8/24/21
21026136900 | EMER-RETIRE 5' OF 4"PAMP |  |  |  |  | 0.008019% | 5438.98 | 55.634 | 5383.346 | 2021-01-01 | 2021-12-31 | 2021-08-17 | 2021-08-24 | ABN 5' 4"P MP MAIN ACCORDING TO ENGINEERED TIE-IN PLAN. WORKED ON 8/17/21. MCRAIG 8/24/21
20026918001 | INSTALL ELECTRONICS |  |  |  |  | 0.3006% | 203885.41 | 78849.9064 | 125035.5036 | 2021-01-01 | 2021-12-31 | 2021-07-12 | 2021-08-17 | CC# 31091 CC# 34924 CC# 21685. 01-03-22 DSASH CC# 21685. 01-03-22 DSASH OVERRUN EXPLANATION: ASSUMED WE WOULD USE THE OLD BLOCK BUILDING BUT FOND T HAT IT WAS LEAKING SO HAD TO REPLACE WITH A NEW BUILDING.
22026160300 | RETIRED ELECTRONICS |  |  |  |  | 0.000623% | 422.53 | 75.9523 | 346.5777 | 2021-01-01 | 2021-12-31 | 2021-08-17 | 2021-08-17
21026136500 | RELOCATE 12' OF 4"PMLP MAIN |  |  |  |  | 0.03779% | 25628.84 | 10466.234 | 15162.606 | 2021-01-01 | 2021-12-31 | 2021-08-17 | 2021-08-18
21026136600 | RETIRE 6' OF 4"PMLP MAIN |  |  |  |  | 0% | 0 | 85.7248 | -85.7248 | 2021-01-01 | 2021-12-31 | 2021-08-07 | 2021-08-18
21026137400 | RETIRE 120'-1" PMP - D304537 |  |  |  |  | 0.0005897% | 399.97 | 3638.7915 | -3238.8215 | 2021-01-01 | 2021-12-31 | 2021-08-21 | 2021-08-21
20026977301 | INSTALL 12,100 OF 2"PMMP MAIN |  |  |  |  | 2.856% | 1937357.64 | 1697987.4343 | 239370.2057 | 2021-01-01 | 2021-12-31 | 2021-03-11 | 2021-11-01
21026121500 | INSTALL 160'-2" PMIP |  |  |  |  | 0.05561% | 37719.27 | 21640.9206 | 16078.3494 | 2021-01-01 | 2021-12-31 | 2021-08-19 | 2021-08-24
21026107300 | INSTALL 140' OF 4"PMMP S/L |  |  |  |  | 0.07842% | 53188.18 | 57302.0236 | -4113.8436 | 2021-01-01 | 2021-12-31 | 2021-08-16 | 2021-11-11
21026107200 | RETIRE 33' OF 4"PMMP S/L |  |  |  |  | 2.654e-06% | 1.8 | 76.3208 | -74.5208 | 2021-01-01 | 2021-12-31 | 2021-08-16 | 2021-11-17
21026129400 | RETIRE 135' OF 8"CSMP MAIN |  |  |  |  | 0.001684% | 1142.2 | 151.2005 | 990.9995 | 2021-01-01 | 2021-12-31 | 2021-08-22 | 2021-09-01 | ABN 135' ON CS MP MAIN.
21026138400 | EMER-INSTALL 2' OF 1"PMMP MAIN |  |  |  |  | 0.0003358% | 227.74 | 3122.8539 | -2895.1139 | 2021-01-01 | 2021-12-31 | 2021-08-25 | 2021-08-26
21026138500 | EMER-RETIRE 2'-1"PAMP MAIN |  |  |  |  | 0% | 0 | 82.634 | -82.634 | 2021-01-01 | 2021-12-31 | 2021-08-25 | 2021-08-26
21026129500 | RETIRE 109' OF 4"BSLP |  |  |  |  | 0.0001052% | 71.35 | 99.3208 | -27.9708 | 2021-01-01 | 2021-12-31 | 2021-06-23 | 2021-09-03 | ABN 4" BS LP MAIN PER GS
21026101501 | INSTALL 3800'-2",4"&6" PMMP |  |  |  |  | 1.242% | 842479.02 | 710294.4849 | 132184.5351 | 2021-01-01 | 2021-12-31 | 2021-12-03 | 2022-05-05 | OVERRUN EXPLANATION: ENCOUNTERED MORE ROCK EXCAVATION THAN ESTIMATED AS WEL L AS THE ASSOCATED SPECIAL BACKFILL. PROJECT ALSO REQUIRED MORE SEWER CAMER A WORK THAN ESTIMATED.
21026997101 | INSTALL 125' OF 4"PMMP MAIN |  |  |  |  | 0.1751% | 118779.98 | 111178.7891 | 7601.1909 | 2021-01-01 | 2021-12-31 | 2021-08-23 | 2021-08-30
21026139100 | EMER - INSTALL 5'-4" PMMP |  |  |  |  | 0.004129% | 2800.66 | 6493.0322 | -3692.3722 | 2021-01-01 | 2021-12-31 | 2021-09-28 | 2021-09-29 | INSTALLED MAIN ON TESTED 90 PSIG 1 HOUR SOAP TESTED FINAL CONN OP 44 PSIG
21026139200 | EMER - RETIRE 5'-4" P-MP |  |  |  |  | 0.008242% | 5590.11 | 743.2708 | 4846.8392 | 2021-01-01 | 2021-12-31 | 2021-09-28 | 2021-09-29
21026109300 | INSTALL 300' OF 2"PMMP MAIN |  |  |  |  | 0.03964% | 26886.16 | 25871.1277 | 1015.0323 | 2021-01-01 | 2021-12-31 | 2021-08-26 | 2021-09-02
21026133300 | INSTALL 200'-2" PMIP |  |  |  |  | 0.02912% | 19749.69 | 14590.9404 | 5158.7496 | 2021-01-01 | 2021-12-31 | 2021-08-27 | 2021-09-02
20026975400 | INSTALL 2250'-2" PMMP |  |  |  |  | 1.267% | 859560.09 | 623618.1819 | 235941.9081 | 2021-01-01 | 2021-12-31 | 2021-04-22 | 2021-11-16 | PROJECT COMPLETED ON 11-16-2021 D.LEMONS 3/2/2022: PROJECT OVERRUN WAS DUE TO ADDITIONAL TIME REQUIRED TO C OMPLETE PROJECT DUE TO MULTIPLE CONTRACTORS IN AREA DURING PROJECT. ESTIMA TED FOR 645 MAN HOURS, BUT REQUIRED 1018 MAN HOURS. ADDITIONAL $85K IN CONT RACT EXPENSES, $36K IN LABOR COSTS WHICH LEAD TO INCREASE OF $32K IN SEGA. THERE WAS A SLIGHT REDUCTION IN OTHER COST TO ACCOUNT FOR THE $147K OVERRUN .
21026118300 | INSTALL 210' OF 2"PMMP MAIN |  |  |  |  | 0.02637% | 17888.9 | 16739.4681 | 1149.4319 | 2021-01-01 | 2021-12-31 | 2021-09-07 | 2021-09-09
21026141000 | EMER - INSTALL 5'-4" PMMP |  |  |  |  | 0% | 0 | 427 | -427 | 2021-01-01 | 2021-12-31 | 2021-09-08 | 2021-09-09
21026141100 | EMER - RETIRE 5'-4" PMMP |  |  |  |  | 0% | 0 | 68.3073 | -68.3073 | 2021-01-01 | 2021-12-31 | 2021-09-08 | 2021-09-09
21026136300 | INSTALL 37'-2"/3" PMMP/CSMP |  |  |  |  | 0.02155% | 14615 | 33826.5433 | -19211.5433 | 2021-01-01 | 2021-12-31 | 2021-09-03 | 2021-09-20 | INSTALLED NEW 030 CS AND PE MAIN. TEST @ 90# FOR 1 HR, NO LEAKS. PURGED INT O SERVICE. STOP OFF AND REMOVED OLD MAIN. 3" WELD CAPS & 2" PE CAP SOAP TES T, NO LEAKS. WRAPPED MAIN. SWING TIES & EM BALLS. J HOWARD 9-20-21
21026136400 | RETIRE 29'-2"/3" CSMP/PMMP |  |  |  |  | 0.0001227% | 83.24 | 826.7837 | -743.5437 | 2021-01-01 | 2021-12-31 | 2021-09-03 | 2021-09-13 | LEAK ON END OF STEEL MECH COMP END CAP. INSTALLED NEW 030 & 020 ST AND PE M L, TESTED AT 90# FOR 1 HR. SOAP TEST 030 AND 020 CAPS, NO LEAKS. BAR BANKS, NGF. INSTALLED ANODE, WRAPPED MAIN. J HOWARD 9-13-21
21026141200 | EMER-INSTALL 3'OF 6"PMLP MAIN |  |  |  |  | 0.0087% | 5901.09 | 4022.0999 | 1878.9901 | 2021-01-01 | 2021-12-31 | 2021-09-12 | 2021-09-15
21026141300 | EMER-RETIRE 3' OF 6"PLP MAIN |  |  |  |  | 5.625e-05% | 38.15 | 69.8875 | -31.7375 | 2021-01-01 | 2021-12-31 | 2021-09-12 | 2021-09-13
21026142000 | EMER - INSTALL 5'-2" PMMP |  |  |  |  | 0.01635% | 11087.26 | 7513.9749 | 3573.2851 | 2021-01-01 | 2021-12-31 | 2021-09-14 | 2021-09-15
21026142100 | EMER - RETIRE 5'-3" PMMP |  |  |  |  | 0% | 0 | 69.8875 | -69.8875 | 2021-01-01 | 2021-12-31 | 2021-09-14 | 2021-09-15
21026115700 | INSTALL 300' OF 2"PMMP MAIN |  |  |  |  | 0.03176% | 21541.85 | 22097.6064 | -555.7564 | 2021-01-01 | 2021-12-31 | 2021-09-13 | 2021-09-28
21026129800 | INSTALL 200'-2" PMMP |  |  |  |  | 0.03769% | 25563.52 | 21853.3833 | 3710.1367 | 2021-01-01 | 2021-12-31 | 2021-09-13 | #N/A
21026142300 | EMER - INSTALL 5'-2" PMMP |  |  |  |  | 0.01628% | 11040.25 | 3984.9999 | 7055.2501 | 2021-01-01 | 2021-12-31 | 2021-09-15 | 2021-09-16
21026142400 | EMER - RETIRE 5'-2" PMP |  |  |  |  | 0.0001971% | 133.69 | 69.8875 | 63.8025 | 2021-01-01 | 2021-12-31 | 2021-09-15 | 2021-09-16
21026118900 | INSTALL REGULATORS |  |  |  |  | 0.006561% | 4450.3 | 6803.6557 | -2353.3557 | 2021-01-01 | 2021-12-31 | 2021-09-16 | 2021-09-21 | CCC# 38381 REPLACED REGULATORS ON 9/16/2021 GCCC TICKET NOT REQUIRED ON 9/21/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026119000 | RETIRE REGULATORS |  |  |  |  | 0.0008444% | 572.72 | 85.0089 | 487.7111 | 2021-01-01 | 2021-12-31 | 2021-09-16 | 2021-09-21 | REPLACED REGULATORS ON 9/16/21 CCC TICKET 38381 OBTAINED ON INSTALL JO CCC TICKET NOT REQUIRED ON 9/21/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026973700 | INSTALL 6150'-4" PMLP |  |  |  |  | 4.176% | 2832541.47 | 2202632.8927 | 629908.5773 | 2021-01-01 | 2021-12-31 | 2021-04-27 | 2022-05-05 | ODOR READS TOOK AT 128 E 3RD ST, MAYSVILLE,KY - WITH SN-16040105 12/17- .6@10:40 - 12/18 .5@16:30 - 12/19 .6@11:30 - 12/20 .5@ 16:29 - 12/21 .5@17:12 - 12/22 .5@16:45 - 12/23 .6@12:27 - TJETT 12/23/21 LEVEL 2 BUDGET VARIANCE COMPLETED AND FILED IN WMSDOCS. D.LEMONS 10/3/2022
21026142500 | EMER-INSTALL 5' OF 2"PMMP |  |  |  |  | 0.000615% | 417.14 | 3297.6583 | -2880.5183 | 2021-01-01 | 2021-12-31 | 2021-09-19 | 2021-09-20
21026142600 | EMER-RETIRE 5' OF 2"PMP MAIN |  |  |  |  | 0.0003882% | 263.29 | 69.8875 | 193.4025 | 2021-01-01 | 2021-12-31 | 2021-09-19 | 2021-09-20
21026113900 | INSTALL 1300' OF 2"/4"PMMP |  |  |  |  | 0.05099% | 34584.47 | 66451.1814 | -31866.7114 | 2021-01-01 | 2021-12-31 | 2021-09-07 | #N/A | MISSED COMMIT DATE DUE TO WEATHER UNDERRUN EXPLANATION: THE UNDERRUN VARIANCE IS DUE TO 50% ROCK EXCAVATION A ND 50% LESS DUST AND STONE. THE OVER HEAD EFFECT OF THESE REDUCTIONS ALSO PLAYED A FACTOR.
20026981300 | RETIRE 1600' OF 2"/3"BSLP MAIN |  |  |  |  | 0% | 0 | 84.1799 | -84.1799 | 2021-01-01 | 2021-12-31 | 2021-08-10 | 2021-09-28
21026112100 | INSTALL 1025'- 2"/4"PHHP MAIN |  |  |  |  | 0.2842% | 192775.66 | 194441.8822 | -1666.2222 | 2021-01-01 | 2021-12-31 | 2021-07-26 | 2021-09-29
21026112200 | RETIRE 980' OF 4"CSHP MAIN |  |  |  |  | 0.001067% | 723.52 | 74.8797 | 648.6403 | 2021-01-01 | 2021-12-31 | 2021-07-26 | 2021-09-29
20026928000 | UPGRADE ELECTRONICS |  |  |  |  | 0.01155% | 7833.1 | 3038 | 4795.1 | 2021-01-01 | 2021-12-31 | 2021-09-23 | #N/A | REPLACED EFC AND UPSIZED METER TO 16M ALSO WORKED TP AND MGRP WHILE ON SITE
21026143000 | RETIRE EME FACILITY |  |  |  |  | 0% | 0 | 63.4597 | -63.4597 | 2021-01-01 | 2021-12-31 | 2021-10-04 | 2021-10-04 | REPLACED EFC
20026955901 | INSTALL 215'-4" PMMP |  |  |  |  | 0.09361% | 63490.92 | 67929.8606 | -4438.9406 | 2021-01-01 | 2021-12-31 | 2021-06-29 | 2021-12-20
21026144300 | EMER - INSTALL 2' OF 2"PMIP |  |  |  |  | 0.0002022% | 137.16 | 2750.8249 | -2613.6649 | 2021-01-01 | 2021-12-31 | 2021-09-25 | 2021-09-26
21026144400 | EMER - RETIRE 2' OF 2"PAIP |  |  |  |  | 0% | 0 | 75.4968 | -75.4968 | 2021-01-01 | 2021-12-31 | 2021-09-25 | 2021-09-26
21026143400 | EMER-INSTALL 10'OF 4"PMIP MAIN |  |  |  |  | 0.01167% | 7913.03 | 7432.5408 | 480.4892 | 2021-01-01 | 2021-12-31 | 2021-09-26 | 2021-09-27
21026143900 | EMER-INSTALL 5'-2"PMMP |  |  |  |  | 0% | 0 | 6000.6188 | -6000.6188 | 2021-01-01 | 2021-12-31 | 2021-10-24 | 2021-10-25
21026143500 | EMER-RETIRE 10' OF 4"PAIP MAIN |  |  |  |  | 0% | 0 | 60.6987 | -60.6987 | 2021-01-01 | 2021-12-31 | 2021-09-26 | 2021-09-27
21026144000 | EMER-RETIRE 5'-2"PMMP |  |  |  |  | 0% | 0 | 49.6987 | -49.6987 | 2021-01-01 | 2021-12-31 | 2021-10-24 | 2021-10-25
21026143700 | INSTALL 4'-4" PMLP |  |  |  |  | 0.0007055% | 478.5 | 3297.2047 | -2818.7047 | 2021-01-01 | 2021-12-31 | 2021-12-18 | 2021-12-18 | INSTALLED 4' OF 4" PL LP MAIN LINE TESTED 90 PSIG 1 HOUR SOAP TESTED FINAL CONN OP 10" WC
21026143800 | RETIRE 4'-4" PMLP |  |  |  |  | 6.596e-05% | 44.74 | 295.4309 | -250.6909 | 2021-01-01 | 2021-12-31 | 2021-12-18 | 2021-12-18 | RETIRED MAIN DUE TO STEEL SADDLE TEE BIENG ON PL PIPE INSTALLED NEW SECTION OF PIPE
21026133100 | INSTAL 2" MOONEY REGS |  |  |  |  | 0.01712% | 11609.08 | 9907.1191 | 1701.9609 | 2021-01-01 | 2021-12-31 | 2021-09-28 | 2021-10-25 | REPLACED REGULATORS GCCC TICKET NOT REQUIRED
21026133200 | RETIRE FISHER 399 REGS |  |  |  |  | 0% | 0 | 90.361 | -90.361 | 2021-01-01 | 2021-12-31 | 2021-09-28 | 2021-10-25 | REPLACED REGULATORS GCCC TICKET NOT REQUIRED
21026112900 | INSTALL 150' - 2" PMMP |  |  |  |  | 0.02135% | 14483.58 | 15892.286 | -1408.706 | 2021-01-01 | 2021-12-31 | 2021-09-27 | 2021-09-29
21026139800 | INSTALL 100'-2" PMIP |  |  |  |  | 0.02939% | 19936.66 | 27338.1249 | -7401.4649 | 2021-01-01 | 2021-12-31 | 2021-09-27 | 2021-10-01
20026976301 | INSTALL 6300' OF 2"/4"PMMP |  |  |  |  | 3.103% | 2104702.57 | 2132943.4537 | -28240.8837 | 2021-01-01 | 2021-12-31 | 2021-09-16 | 2021-12-15
20026956000 | RETIRE 820'-2" PMMP |  |  |  |  | 0% | 0 | 85.0089 | -85.0089 | 2021-01-01 | 2021-12-31 | 2021-06-29 | 2021-12-20
18026761400 | INSTALL BULLHORN RMU |  |  |  |  | 0.00398% | 2699.78 | 3922.4303 | -1222.6503 | 2021-01-01 | 2021-12-31 | 2018-07-26 | #N/A | RMU WAS INSTALLED ON 09/30/2021 BY TIM SWARTS. SYSTEM SERIAL # IS 132395. -OSS
20026956101 | INSTALL 2475'-8"/6"/4" PMLP |  |  |  |  | 1.983% | 1344804.09 | 1170137.3307 | 174666.7593 | 2021-01-01 | 2021-12-31 | 2021-07-28 | 2021-12-20 | WIPE SAMPLE RESULTS WERE ENTERED ON THE INSTALL JOB INSTEAD OF THE RETIREMENT JOB. RETIREMENT RESULTS WERE ENTERED HERE.
21026132500 | INSTALL 450' OF 2"PMMP MAIN |  |  |  |  | 0.04606% | 31237.4 | 32348.6064 | -1111.2064 | 2021-01-01 | 2021-12-31 | 2021-09-21 | 2021-10-06
21026146300 | INSTALL 4'-4" PMLP |  |  |  |  | 0.0006257% | 424.36 | 2206.8953 | -1782.5353 | 2021-01-01 | 2021-12-31 | 2021-10-07 | 2021-10-12 | INSTALLED 4' OF 4" PLASTIC MAIN. PRESSURE TESTED 90LBS FOR 1HR.
21026146400 | RETIRE 4'-4" P-LP |  |  |  |  | 5.852e-05% | 39.69 | 197.4141 | -157.7241 | 2021-01-01 | 2021-12-31 | 2021-10-07 | 2021-10-12
21026128601 | INSTALL 700' OF 2"PMMP MAIN |  |  |  |  | 0.1116% | 75716.28 | 57445.0039 | 18271.2761 | 2021-01-01 | 2021-12-31 | 2021-09-20 | 2021-10-13
20026980601 | INSTALL 16,200'-2"/4" PMMP |  |  |  |  | 6.959% | 4720247.08 | 4665902.1359 | 54344.9441 | 2021-01-01 | 2021-12-31 | 2022-05-20 | 2022-09-29
21026147900 | EMER - INSTALL 5'-4" PMLP |  |  |  |  | 0.005442% | 3691.18 | 2422.8089 | 1268.3711 | 2021-01-01 | 2021-12-31 | 2021-11-16 | 2021-11-17 | INSTALLED 3FT OF 040 PLASTIC DUE TO 3 TEE'S BEING AN AOC. ALL TESTING INFO ON JO 21026147900 AND 21026148000 IN WMS DOCS.
21026148000 | EMER - RETIRE 5'-4" PLP |  |  |  |  | 6.458e-06% | 4.38 | 66.2207 | -61.8407 | 2021-01-01 | 2021-12-31 | 2021-11-16 | 2021-11-17 | INSTALLED 3FT OF 040 PLASTIC DUE TO 3 TEE'S BEING AN AOC. ALL TESTING INFO ON JO 21026147900 AND 21026148000 IN WMS DOCS.
21026994800 | RETIRE STATION 1502 |  |  |  |  | 0.01242% | 8422.17 | 4108.4893 | 4313.6807 | 2021-01-01 | 2021-12-31 | 2021-10-12 | 2021-11-02 | CCC# 37974 CCC#41227 CCC#41449 CCC# 41449 STATION ABANDONED ON 10/12/2021 PAPERWORK COMPLETED ON 11/2/2021 GCCC TICKET NOT REQUIRED ON 11/2/21 OFF SITE COMPLETING PAPERWORK CFARIS
21026107100 | INSTALL COMMUNICATIONS |  |  |  |  | 0.004976% | 3375.12 | 1691.2937 | 1683.8263 | 2021-01-01 | 2021-12-31 | 2021-10-11 | 2021-12-10 | CCC#41275 CCC#17228 INSTALLED SUPER SOLAR KIT AND BATTERY UPGRADED TO RV50 CELL MODEM CONVERTED TO FULL TIME MONITORING RTU TICKET NUMBER 4339
21026144200 | RETIRE 4280' OF 2"/3"PAMP MAIN |  |  |  |  | 0.06085% | 41269.58 | 14091.9275 | 27177.6525 | 2021-01-01 | 2021-12-31 | 2021-10-04 | 2021-11-17 | ABN 4280' P MP MAIN IN ACCORDNANCE WITH ENGINEERED TIE-IN PLAN AND GAS STANDARDS. SOAP TEST FINAL TIE-IN AT OP OK. BHB NGF. MCRAIG 10/13/21 TWALKER/KY 11-24-21: WMS WOULD NOT ALLOW FOR REVISION DUE TO UNPAID INVOICES, JOB ORDER OVER RUN DUE TO SCOPE OF WORK INCREASED AND WE RETIRED MORE UNLOCATED FIRST GENERATION PLASTIC MAIN THAN PLANNED AND SOME NEW EMPLOYEES WORKED WITH CREWS WITH INCREASED LABOR COST BY $14,000 OVER ESTIMATE
21026999700 | INSTALL 125' OF 2"PMMP MAIN |  |  |  |  | 0.03254% | 22070.53 | 28787.2695 | -6716.7395 | 2021-01-01 | 2021-12-31 | 2021-10-07 | 2021-10-13
21026999800 | RETIRE 115' OF 2"PMMP MAIN |  |  |  |  | 0% | 0 | 81.0887 | -81.0887 | 2021-01-01 | 2021-12-31 | 2021-10-07 | 2021-10-14
21026137500 | INSTALL SOLAR PANEL |  |  |  |  | 0.005306% | 3598.81 | 4862.234 | -1263.424 | 2021-01-01 | 2021-12-31 | 2021-10-13 | 2021-10-13 | CC# 41497 RHAYES 10-13-2021 RHAYES 10-13-2021 CHANGED ER350 FROM CRY IN TO FULL TIME MONITOR INSTALLED SUPER SOLAR KIT AN D RV 50 MODEM CCOX 10-13-2021
21026147100 | EMER-INSTALL 6' OF 4"PMMP |  |  |  |  | 0.0008908% | 604.21 | 1045.4141 | -441.2041 | 2021-01-01 | 2021-12-31 | 2021-10-24 | 2021-10-25
21026147200 | EMER-RETIRE 6' OF 4"PAMP MAIN |  |  |  |  | 5.69e-05% | 38.59 | 49.6987 | -11.1087 | 2021-01-01 | 2021-12-31 | 2021-10-24 | 2021-10-25
20026928700 | UPGRADE ELECTRONICS |  |  |  |  | 0.01186% | 8043.8 | 3038 | 5005.8 | 2021-01-01 | 2021-12-31 | 2021-10-18 | 2021-10-25 | REPLACED EFC
20026934400 | RETIRE ELECTRONICS |  |  |  |  | 0% | 0 | 73.3494 | -73.3494 | 2021-01-01 | 2021-12-31 | 2021-10-24 | 2021-10-25 | REPLACED EFC
21026146800 | RETIRE GMB #44535-AK STEEL |  |  |  |  | 0.005679% | 3852.12 | 2893.6188 | 958.5012 | 2021-01-01 | 2021-12-31 | 2021-10-11 | 2021-10-25 | ALL FACILITIES REMOVED FROM AK STEEL BY MATT RYAN AND SHANE GIORDANO MAINLINE/SERVICE LINE ABANDONED ON 10/18/2021 BY CONSTRUCTION SERVICES M&R PAPERWORK COMPLETED BY CYNTHIA FARIS ON 10/25/2021
21026146000 | INSTALL 404'-4"&6"PMMP |  |  |  |  | 0.1845% | 125105.39 | 224207.9887 | -99102.5987 | 2021-01-01 | 2021-12-31 | 2021-10-11 | 2021-12-16 | LEVEL 2 BUDGET VARIANCE EXPLANATION FORM HAS BEEN APPROVED AND LOADED INTO WMSDOCS WORKSPACE. D.LEMONS 3/3/2022
21026146100 | RETIRE 427'-4"BSLP |  |  |  |  | 0.002267% | 1537.36 | 63.4597 | 1473.9003 | 2021-01-01 | 2021-12-31 | 2021-10-11 | 2021-12-16
21026144600 | INSTALL 12" SS |  |  |  |  | 0.03776% | 25613.83 | 13660.0322 | 11953.7978 | 2021-01-01 | 2021-12-31 | 2021-10-18 | 2021-12-20 | INSTALLED 12" SS TO STOPPLE AND KILL 12" MAIN
21026144700 | RETIRE 1273'-6/12/16" CS/BSHP |  |  |  |  | 0.0002469% | 167.43 | 388.1295 | -220.6995 | 2021-01-01 | 2021-12-31 | 2021-12-18 | 2021-12-20 | RETIRE 1207' OF 12" BS HP TO AK STEEL SOAP TESTED OP 113 PSIG
21026147700 | EMER - INSTALL 5'-2" PMMP |  |  |  |  | 0.003732% | 2531.33 | 2686.3426 | -155.0126 | 2021-01-01 | 2021-12-31 | 2021-10-19 | 2021-10-20 | REPLACED 3' SECTION OF 2" PMP AFTER DIG IN. PRESSURE TESTED NEW MAIN AT 90 PSIG FOR 1 HOUR, SOAP TESTED FINAL TIE IN AT OP. OK 34 PSIG VERIFIED NRICHIE 10-20-21
21026147800 | EMER - RETIRE 5'-2" PMP |  |  |  |  | 0% | 0 | 61.5191 | -61.5191 | 2021-01-01 | 2021-12-31 | 2021-10-19 | 2021-10-20
20026977400 | RETIRE 10,510'OF 4"/6"BSLP |  |  |  |  | 0.001825% | 1237.75 | 90.4074 | 1147.3426 | 2021-01-01 | 2021-12-31 | 2021-10-21 | 2021-11-01
20026928100 | UPGRADE ELECTRONICS |  |  |  |  | 0.00894% | 6063.75 | 3038 | 3025.75 | 2021-01-01 | 2021-12-31 | 2021-10-20 | 2021-11-16 | REPLACED EFC
20026933800 | RETIRE ELECTRONICS |  |  |  |  | 0% | 0 | 73.3494 | -73.3494 | 2021-01-01 | 2021-12-31 | 2021-10-20 | 2021-11-16 | REPLACED EFC
21026134100 | INSTALL 850' OF 2"PMMP MAIN |  |  |  |  | 0.0417% | 28285.71 | 40949.6064 | -12663.8964 | 2021-01-01 | 2021-12-31 | 2021-10-15 | 2021-10-21
21026148100 | EMER-INSTALL 4' OF 2"HPHP MAIN |  |  |  |  | 0.002978% | 2019.57 | 7370.71 | -5351.14 | 2021-01-01 | 2021-12-31 | 2022-01-23 | 2022-01-24
21026148200 | EMER-RETIRE 4' OF 2"HDHP MAIN |  |  |  |  | 0% | 0 | 60.6987 | -60.6987 | 2021-01-01 | 2021-12-31 | 2022-01-23 | 2022-01-24
20026953800 | RETIRE 8800' OF 4"/6"BSLP MAIN |  |  |  |  | 0% | 0 | 240.2222 | -240.2222 | 2021-01-01 | 2021-12-31 | 2021-10-22 | 2021-10-29
20026990800 | RETIRE INLET PIPING R 1502 |  |  |  |  | 0% | 0 | 240.2222 | -240.2222 | 2021-01-01 | 2021-12-31 | 2021-10-22 | 2021-10-29
20026947301 | INSTALL 3,950' - 2" PMMP |  |  |  |  | 2.794% | 1895184.87 | 1562557.4499 | 332627.4201 | 2021-01-01 | 2021-12-31 | 2021-07-12 | 2021-11-11 | TTOY/KY 3/2/22: OVERRUN EXPLANATION: FLAGGER OT ESTIMATED FOR 543 HOURS BUT ACTUAL WAS 1033 HOURS, CONTRACTOR CREWS HOURLY TIME WAS OVER ESTIMATE AT 167 EXTRA HOURS, SEGA HAD EXTRA $60,000 IN COST, COMPANY LABOR HAD ADDITIONAL $27,000 COST OVER ESTIMATE
21026144100 | INSTALL 350' OF 2"PMIP MAIN |  |  |  |  | 0.02907% | 19720.01 | 20004.6217 | -284.6117 | 2021-01-01 | 2021-12-31 | 2021-10-14 | 2021-10-27
20026931100 | UPGRADE ELECTRONICS |  |  |  |  | 0.0003917% | 265.67 | 3038 | -2772.33 | 2021-01-01 | 2021-12-31 | 2021-10-27 | 2021-11-18 | REPLACED EFC
20026938100 | RETIRE ELECTRONICS |  |  |  |  | 0% | 0 | 73.3494 | -73.3494 | 2021-01-01 | 2021-12-31 | 2021-10-27 | 2021-11-18 | REPLACED EFC
20026947400 | RETIRE 5,000' - 4" CI/BS LP |  |  |  |  | 0.0001052% | 71.35 | 103.8156 | -32.4656 | 2021-01-01 | 2021-12-31 | 2021-10-29 | 2021-11-12
19026889700 | INSTALL METER AND SETTING |  |  |  |  | 0.08066% | 54709.93 | 55012.1889 | -302.2589 | 2021-01-01 | 2021-12-31 | 2022-05-10 | 2022-05-11 | CCC #30162 CCC # 42745 CCC # 42908 CCC # 43108 CLENANER INSTALLED ON 10-29-2022 ALONG WITH PAPERWORK CO BY JOSH MULLINS ON 5-10-22
19026889800 | RETIRE METER AND SETTING |  |  |  |  | 0.0009036% | 612.86 | 76.3408 | 536.5192 | 2021-01-01 | 2021-12-31 | 2021-06-30 | 2022-05-11
20026970100 | INSTALL 11400'-2"/4" PM/CSIP |  |  |  |  | 1.536% | 1042042.95 | 1176644.8813 | -134601.9313 | 2021-01-01 | 2021-12-31 | 2021-03-31 | 2021-11-12
20026918102 | INSTALL ELECTRONICS |  |  |  |  | 0.2556% | 173384.28 | 264607.6595 | -91223.3795 | 2021-01-01 | 2021-12-31 | 2021-11-01 | 2021-11-01 | NO CC NEEDED ONSITE MEETING DID NOT GO INSIDE BUILDING GES: UNDERRUN EXPLANATION: JOB UNDERRAN BECAUSE SCADA BUILDING WAS PLACED O N ANOTHER JOB ORDER THAT IS PLANNED FOR 2022 CONSTRUCTION. ADDITIONALLY, ASSUMED THERE WAS PRESSURE CONTROL WHEN ESTIMATED AND THERE W AS NOT.
21026142200 | INSTALL 575' OF 2"PMMP MAIN |  |  |  |  | 0.03752% | 25446.02 | 20915.4686 | 4530.5514 | 2021-01-01 | 2021-12-31 | 2021-10-25 | 2021-11-02
21026149000 | INSTALL 75'-2" PMIP |  |  |  |  | 0.001128% | 765.35 | 4287.763 | -3522.413 | 2021-01-01 | 2021-12-31 | 2021-11-01 | 2021-12-20 | INSTALLED 66' OF 2" PL TESTED 90 PSIG 0005 MIN SOAP TESTED CAP OP 8 PSIG
21026138201 | EMER-INSTALL 480' OF 6"PMLP |  |  |  |  | 0.2871% | 194700.21 | 240281.6735 | -45581.4635 | 2021-01-01 | 2021-12-31 | 2021-11-01 | 2021-11-02 | CCC# 43819 CCC# 43967 TWALKER/KY 05-04-22: JOB CURRENTLY UNDER RUNNING SINCE CITY OF FRANKFORT HAS NOT PAVED STREET AND BILLED CKY - PAVING ESTIMATE AT $35,000.
21026138300 | EMER-RETIRE 490' OF 6 5/8"BSLP |  |  |  |  | 0.0001052% | 71.35 | 82.634 | -11.284 | 2021-01-01 | 2021-12-31 | 2021-11-02 | 2021-11-02 | KBOTKINS ENTERED WIPE SAMPLE FOR OLIVER MAYNARD WHO IS ATTEMPTING TO COMPLETE THE JOB FOR CLOSE OUT. SAMPLE TAKEN 4/20/22 BUT SYSTEM WOULD NOT ACCEPT THAT DATE DUE TO THE CO DATE.
21026133900 | INSTALL VRG CONTROLER |  |  |  |  | 0% | 0 | 6187.1439 | -6187.1439 | 2021-01-01 | 2021-12-31 | 2022-11-01 | 2022-11-02
21026134000 | RETIRE DAMAGED CONTROLLER |  |  |  |  | 0% | 0 | 220.9908 | -220.9908 | 2021-01-01 | 2021-12-31 | 2022-11-01 | 2022-11-02
20026929400 | UPGRADE ELECTRONICS |  |  |  |  | 0.0004327% | 293.46 | 3038 | -2744.54 | 2021-01-01 | 2021-12-31 | 2021-11-02 | 2021-11-18 | REPLACED EFC
20026935100 | RETIRE ELECTRONICS |  |  |  |  | 0% | 0 | 73.3494 | -73.3494 | 2021-01-01 | 2021-12-31 | 2021-11-17 | 2021-11-18 | REPLACED EFC
21026145200 | EMER-INSTALL NEW BYPASS VALVES |  |  |  |  | 0.0009353% | 634.37 | 4285.9461 | -3651.5761 | 2021-01-01 | 2021-12-31 | 2021-11-03 | 2021-12-27 | CCC# 44725 BYPASS VALVES INSTALLED BY WADE SHIMFESSEL ALONG WITH CONTRACT CREW PAPERWORK COMPLETED BY CYNTHIA FARIS 12/27/21
21026120800 | RETIRE HP/MP RUN-1 OF R-1035 |  |  |  |  | 0.00122% | 827.14 | 21706.5276 | -20879.3876 | 2021-01-01 | 2021-12-31 | 2021-11-29 | 2021-11-29 | HP TO MP RUN 1 HAS BEEN RETIRED AND LP RUN 2 HAS BEEN PLACED BACK INTO SERVICE WORKED COMPLETED ON 11/3/2021 BY CHRIS COX PAPERWORK COMPLETED BY CYNTHIA FARIS ON 11/29/2021 GCCC TICKET NOT REQUIRED ON 11/29/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026145300 | EMER-RETIRE BYPASS VALVE |  |  |  |  | 0% | 0 | 60.6987 | -60.6987 | 2021-01-01 | 2021-12-31 | 2021-11-03 | 2022-01-11 | VALVE REPLACED BY WADE SHIMFESSEL AND CONTRACT CREW ON 11/3/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/11/2022
20026972201 | INSTALL 3300' OF 2"/4" PMMP |  |  |  |  | 0.1252% | 84926.85 | 89953.3001 | -5026.4501 | 2021-01-01 | 2021-12-31 | 2021-10-12 | 2021-11-04
21026124100 | INSTALL 300'-2" PMMP |  |  |  |  | 0.0619% | 41987.03 | 24076.2901 | 17910.7399 | 2021-01-01 | 2021-12-31 | 2021-11-01 | 2021-11-05
21026149500 | EMER-INSTALL 26'-3"/4"PMMP MN |  |  |  |  | 0.03504% | 23766.13 | 10953.3154 | 12812.8146 | 2021-01-01 | 2021-12-31 | 2021-11-16 | 2021-11-17 | SPLIT IN ALDYLA MAIN.INSTALLED BYPASS.REPLACED CRACKED MAIN AND INLINE TEE WHILE MAIN ON BYPASS.ALL TESTING INFO ON 21026149600 AND 21026149500 IN DOCS
21026149600 | EMER-RETIRE 26'- 4"PAMP MAIN |  |  |  |  | 0.000127% | 86.15 | 61.5191 | 24.6309 | 2021-01-01 | 2021-12-31 | 2021-11-16 | 2021-11-17 | SPLIT IN ALDYLA MAIN.INSTALLED BYPASS.REPLACED CRACKED MAIN AND INLINE TEE WHILE MAIN ON BYPASS.ALL TESTING INFO ON 21026149600 AND 21026149500 IN DOCS
20026929700 | UPGRADE ELECTRONICS |  |  |  |  | 0.005876% | 3985.53 | 3038 | 947.53 | 2021-01-01 | 2021-12-31 | 2021-10-18 | 2021-11-16 | REPLACED EFC
20026935400 | RETIRE ELECTRONICS |  |  |  |  | 0% | 0 | 73.3494 | -73.3494 | 2021-01-01 | 2021-12-31 | 2021-11-08 | 2021-11-16 | REPLACED EFC
21026131400 | INSTALL 300'-2" PMIP |  |  |  |  | 0.2337% | 158500.46 | 139158.4326 | 19342.0274 | 2021-01-01 | 2021-12-31 | 2021-10-25 | 2021-11-11
21026131500 | RETIRE 300'-2" PMIP |  |  |  |  | 5.8e-05% | 39.34 | 88.8156 | -49.4756 | 2021-01-01 | 2021-12-31 | 2021-11-09 | 2021-11-11
21026128700 | RETIRE HP/MP REG RUN |  |  |  |  | 0.005517% | 3741.83 | 4148.6042 | -406.7742 | 2021-01-01 | 2021-12-31 | 2021-11-09 | 2021-11-18 | HP/MP RUN RETIRED BY CHRIS COX ON 11/9/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 11/18/2021 GCCC TICKET NOT REQUIRED ON 11/18/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026970200 | RETIRE 10250'-2"/3"/4" BS/CSIP |  |  |  |  | 0.0004015% | 272.31 | 278.4699 | -6.1599 | 2021-01-01 | 2021-12-31 | 2021-10-14 | 2021-11-12
21026150000 | EMER - INSTALL 14'-4" PMLP |  |  |  |  | 0.1064% | 72137.82 | 3163.1338 | 68974.6862 | 2021-01-01 | 2021-12-31 | 2021-12-21 | 2021-12-22 | INSTALLED 16' OF 4" PL W/ 4 90'S TO GO ABOVE 24" CLAY TILE SEWER TESTED 90 PSIG 1 HR OVERRUN EXPLANATION: CROSSBORE FOUND- CAMERA CREW NEEDED AND ADDITIONAL HOURS NEEDED TO REMEDIATE THE CROSS-BORE ISSUE 2 MAINTENCE JOBS AND 1 PAVE JOB CHARGED BACK TO CAPITAL JOB AND WERE NOT ACCOUNTED FOR IN ORIGINAL PROPOSED COST, $26K IN FLAGGING AND RESTORATION CHARGED TO MAINTENCE JOBS AND $14K IN CAMERA WORK BY CONTRACTOR
21026150100 | EMER - RETIRE 6'-4" P-LP |  |  |  |  | 0.0009867% | 669.23 | 335.9749 | 333.2551 | 2021-01-01 | 2021-12-31 | 2021-12-21 | 2021-12-22 | REMOVED 4" PL FROM SEWER LINE CROSS BORE
21026101700 | INSTALL NEW GMB SETTING |  |  |  |  | 0.05908% | 40071.73 | 57815.8896 | -17744.1596 | 2021-01-01 | 2021-12-31 | 2021-07-27 | 2021-11-16 | INSTALLED NEW GMB SETTING
21026102400 | RETIRE WOODFORD GMB |  |  |  |  | 0% | 0 | 84.0131 | -84.0131 | 2021-01-01 | 2021-12-31 | 2021-11-10 | 2021-11-16 | RETIRED OLD GMB SETTING AFTER NEW SETTING PLACED IN SERVICE
21026999600 | INSTALL 90' OF 4"CS/PMMP MAIN |  |  |  |  | 0.06974% | 47302.77 | 68922.5327 | -21619.7627 | 2021-01-01 | 2021-12-31 | 2021-10-15 | 2021-11-11 | NEW MAIN GASED UP 11-11-21
21026150600 | EMER - INSTALL 5'-2" PMMP |  |  |  |  | 0.0005584% | 378.77 | 1696.2756 | -1317.5056 | 2021-01-01 | 2021-12-31 | 2021-11-16 | 2021-11-16
21026150700 | EMER - RETIRE 5'-2" PMP |  |  |  |  | 9.499e-05% | 64.43 | 335.9749 | -271.5449 | 2021-01-01 | 2021-12-31 | 2021-11-16 | 2021-11-17
21026129600 | INSTALL 100' OF 8"PMMP MAIN |  |  |  |  | 0.225% | 152586.55 | 99233.0142 | 53353.5358 | 2021-01-01 | 2021-12-31 | 2021-10-26 | 2021-11-19 | TWALKER/KY 01-24-23: JOB ORDER OVER RUN DUE TO ADDITIONAL FLAGGING ADDED $50,000 TO CONTRACT COST, SEGA INCREASED BY $6,000 AND CO LABOR COST HIGHER BY $14,000 LEVEL 2 VARIANCE ADDED TO WMS.DOCS.
21026129700 | RETIRE 20' OF 8"BSMP MAIN |  |  |  |  | 0.002891% | 1960.6 | 79.203 | 1881.397 | 2021-01-01 | 2021-12-31 | 2021-11-16 | 2021-11-19
20026975500 | RETIRE 3515'-2",3",4"& 6" |  |  |  |  | 0.0002104% | 142.7 | 107.2796 | 35.4204 | 2021-01-01 | 2021-12-31 | 2021-03-01 | 2021-11-16 | PROJECT COMPLETE ON 11162021
21026151500 | EMER-INSTALL 10' OF 4"PMMP |  |  |  |  | 0.0003106% | 210.64 | 5220.9567 | -5010.3167 | 2021-01-01 | 2021-12-31 | 2021-11-18 | 2021-11-24 | LEAK ON SF CPLG ON TEE OF SVC TO 3102 KIRKLEVINGTON DR. DPI D221947 CLEARED ON 2212. ABN/INST 3'- 4" P MAIN ACCORDING TO GAS STANDARDS AND ENGINEERED TIE-IN PLAN. WORKED 11/17/21 MCRAIG
20026973001 | INSTALL 10,000--2" PMMP |  |  |  |  | 4.27% | 2896168.82 | 2332285.9866 | 563882.8334 | 2021-01-01 | 2021-12-31 | 2021-08-27 | 2022-06-30 | COST OVERRUN OF $378K DUE TO PROJECT SHUT DOWN AND RESTART OVER WINTER. PR OJECT REQUIRED ADDITIONAL RESOURCES THAT WERE NOT ESTIMATED. COST OVERUN O F $345K IN MATERIALS (PAVING), $124K IN CONTRACT AND $21K IN LABOR. THERE W AS A SAVINGS OF $213K IN OTHER DUE TO ORIGINAL PAVING ESTIMATE BEING CAPTUR ED THERE. THESE ADDITIONAL COSTS CAUSED INCREASE IN SEGA OF $97K. D.LEMONS 10/26/2022
21026151600 | EMER-RETIRE 10' OF 4"PAMP |  |  |  |  | 3.6e-05% | 24.42 | 64.6591 | -40.2391 | 2021-01-01 | 2021-12-31 | 2024-11-17 | 2021-11-24 | LEAK ON SF COUPLING ON TEE TO SVC OF 3102 KIRKLEVINGTON DR. DPI D221947 CLEARED ON 2212. ABN/ INST 3'- 4" P MAIN ACCORDING TO GAS STANDARDS AND ENGINEERED TIE-IN PLAN. WORKED 11/17/24 MCRAIG
21026128200 | INSTALL 1,300 OF 2"/4"PMMP |  |  |  |  | 0.08334% | 56524.7 | 51810.9858 | 4713.7142 | 2021-01-01 | 2021-12-31 | 2021-11-08 | 2021-11-19
21026136700 | INSTALL 1,750'-2" PMMP |  |  |  |  | 0.06997% | 47459.5 | 49760.6579 | -2301.1579 | 2021-01-01 | 2021-12-31 | 2021-11-08 | 2021-11-23
20026954400 | INSTALL 12,500' OF 6"PMMP |  |  |  |  | 0.9897% | 671261.21 | 584465.9269 | 86795.2831 | 2021-01-01 | 2021-12-31 | 2021-08-26 | 2021-12-17 | GAS WAS ONLINE BEFORE COMMIT DATE. HAD TO FINISH UP RESTORATION AND PROJEC T INFO. STEVE CANOY 12/17/2021
20026955503 | INSTALL 2850'-8" CSHP |  |  |  |  | 1.864% | 1263938.35 | 1308080.823 | -44142.473 | 2021-01-01 | 2021-12-31 | 2021-11-18 | 2021-11-30
20026955600 | RETIRE 6100'-8"/3" BS/CSHP |  |  |  |  | 0.0002104% | 142.7 | 190.2592 | -47.5592 | 2021-01-01 | 2021-12-31 | 2021-11-30 | 2021-11-30
21026153400 | EMER - INSTALL 6'-4" PMIP |  |  |  |  | 0.01099% | 7455.58 | 4080.2324 | 3375.3476 | 2021-01-01 | 2021-12-31 | 2021-12-01 | 2021-12-22
21026153500 | EMER - RETIRE 6'-4" PMIP |  |  |  |  | 0.00015% | 101.71 | 518.618 | -416.908 | 2021-01-01 | 2021-12-31 | 2021-12-22 | 2021-12-22
21026135900 | INSTALL 140'-2" PMMP |  |  |  |  | 0.01229% | 8332.52 | 14039.3957 | -5706.8757 | 2021-01-01 | 2021-12-31 | 2021-11-23 | 2021-12-02
21026143200 | EMER - INSTALL 450'- 4" CSHP |  |  |  |  | 0.3801% | 257776.24 | 196595.4538 | 61180.7862 | 2021-01-01 | 2021-12-31 | 2021-12-02 | 2021-12-14 | PROJECT WAS CODED AMRCB BECAUSE THE PIPE UNDER THE BRIDGE HAD NO COATING. OVERRUN EXPLANATION: MAIN REASON FOR PROJECT COST OVERRUN IS DUE TO 2,000 UNITS OF ASPHALT PAVING WHEN ONLY 1,000 UNITS WERE PLANNED. THE STATE REQUIRED EXTRA PAVING DUE TO EXISTING ROAD CONDITION.THE PROJECT WAS PLANNED FOR 1 CONSTRUCTION COORDINATORBUT ENDED UP HAVING MULTIPLE AND DOUBLED THE COMPANY LABOR CHARGES. FLAGGING FOR THEPROJECT INCLUDED A 30% INCREASECOMPARED TO THE PLANNED AMOUNT. THE PROJECT INCLUDED AN ADDITIONAL 49 UNITS OF STEELMAINLINE INSTALLATION AND ROCK AND LEDGE EXCAVATIONWAS REQUIRED BUT NOT PLANNED. TTOY 12/2/22
21026143300 | EMER - RETIRE 100'-3" CSHP |  |  |  |  | 0.004474% | 3034.48 | 61.5191 | 2972.9609 | 2021-01-01 | 2021-12-31 | 2021-12-02 | 2021-12-14
21026156100 | EMER-INSTALL 6' OF 2"PMMP MAIN |  |  |  |  | 0.008274% | 5612.12 | 6138.1743 | -526.0543 | 2021-01-01 | 2021-12-31 | 2021-12-14 | 2021-12-14
20026976400 | RETIRE 6100' OF 3"/4"BSLP MN |  |  |  |  | 0.002645% | 1794.07 | 152.7248 | 1641.3452 | 2021-01-01 | 2021-12-31 | 2022-01-24 | 2021-12-15
20026977200 | RETIRE 6900' OF 4"/6"BSLP MAIN |  |  |  |  | 0.00125% | 848.1 | 76.6277 | 771.4723 | 2021-01-01 | 2021-12-31 | 2021-01-27 | 2021-12-15
21026156200 | EMR-RET 6'-2"PMP MAIN D222323 |  |  |  |  | 0.0001106% | 75.03 | 61.2976 | 13.7324 | 2021-01-01 | 2021-12-31 | 2021-12-14 | 2021-12-14
21026105401 | INSTALL 6520' OF 6"PMMP MAIN |  |  |  |  | 0.6217% | 421654.71 | 403346.5487 | 18308.1613 | 2021-01-01 | 2021-12-31 | 2021-07-22 | 2021-12-17
21026120700 | RETIRE REG STATION 1002 |  |  |  |  | 0.009557% | 6481.89 | 5235.8425 | 1246.0475 | 2021-01-01 | 2021-12-31 | 2021-12-15 | 2021-12-27 | CC# 48634 CMCOX 12/15/21 STATION RETIRED BY CHRIS COX AND CONSTRUCTION SERVICES PAPERWORK COMPLETED BY CYNTHIA FARIS ON 12/27/21
20026988300 | RETIRE 1853'-4"/3" BS/CSMP |  |  |  |  | 7.047e-05% | 47.8 | 5110.2031 | -5062.4031 | 2021-01-01 | 2021-12-31 | 2021-04-14 | 2021-12-16
21026113701 | INSTALL 4030' - 4"/2" PMMP |  |  |  |  | 1.271% | 862366.14 | 778460.4875 | 83905.6525 | 2021-01-01 | 2021-12-31 | 2021-04-14 | 2021-12-17
20026955800 | RETIRE 216'-2" PMMP |  |  |  |  | 0% | 0 | 85.5775 | -85.5775 | 2021-01-01 | 2021-12-31 | 2021-04-14 | 2021-12-17
21026106400 | RETIRE PAPER RECORD GAUGE |  |  |  |  | 0.0001362% | 92.38 | 341.3226 | -248.9426 | 2021-01-01 | 2021-12-31 | 2021-12-17 | 2021-12-17 | TICKET 13749
20026956200 | RETIRE 4775'-12">3"PM/BS/CSLP |  |  |  |  | 0.0002359% | 160 | 85.5775 | 74.4225 | 2021-01-01 | 2021-12-31 | 2021-04-14 | 2021-12-20
21026118500 | RETIRE 3,256' 10"-3" CS/BS/PLP |  |  |  |  | 6.325e-05% | 42.9 | 151.2005 | -108.3005 | 2021-01-01 | 2021-12-31 | 2021-04-14 | 2021-12-20
21026156500 | INSTALL 140'-2"/4" PMMP |  |  |  |  | 0.00309% | 2096.07 | 3669.7405 | -1573.6705 | 2021-01-01 | 2021-12-31 | 2021-12-20 | 2021-12-21
20026985600 | INSTALL 375' OF 2"CSHP MAIN |  |  |  |  | 0.133% | 90203.73 | 92169.2028 | -1965.4728 | 2021-01-01 | 2021-12-31 | 2021-12-12 | 2021-01-03
20026985700 | RETIRE 200' OF 2"CSHP MAIN |  |  |  |  | 9.281e-05% | 62.95 | 84.1794 | -21.2294 | 2021-01-01 | 2021-12-31 | 2021-12-12 | 2022-01-03
20026942600 | RETIRE GAUGE |  |  |  |  | 0% | 0 | 91.4991 | -91.4991 | 2021-01-01 | 2021-12-31 | 2021-12-21 | 2022-01-10 | GAUGE RETIRED AFTER ERX INSTALLED BY WADE SHIMFESSEL PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/10/2022
20026918301 | INSTALL ELECTRONICS |  |  |  |  | 0.241% | 163427.04 | 179105.9064 | -15678.8664 | 2021-01-01 | 2021-12-31 | 2021-12-21 | 2021-12-22 | GCC# 13951 CCC TICKET #14135 TICKET# 15597 CCC# 49425 REPLACED PUCK IN TRANSMITTER W/NOLL COMPLETED PAPERWORK 12-22-21 JMARTIN
20026942500 | INSTALL I&C EQUIPMENT |  |  |  |  | 0.0123% | 8341.61 | 16155.4774 | -7813.8674 | 2021-01-01 | 2021-12-31 | 2021-12-21 | 2022-01-10 | ERX INSTALLED BY ACP AND WADE SHIMFESSEL PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/10/22
22026205000 | RETIRE ERX |  |  |  |  | 0% | 0 | 78.4365 | -78.4365 | 2021-01-01 | 2021-12-31 | 2021-12-21 | 2021-12-22 | COMPLETED PAPERWORK 12-22-21 JMARTIN
21026157501 | EMER - INSTALL 5'-3" PMMP |  |  |  |  | 0.03609% | 24476.25 | 13441.7151 | 11034.5349 | 2021-01-01 | 2021-12-31 | 2021-12-26 | 2021-12-27
21026157600 | EMER - RETIRE 5'-3" PAMP |  |  |  |  | 0.0001572% | 106.63 | 72.8047 | 33.8253 | 2021-01-01 | 2021-12-31 | 2021-12-26 | 2021-12-27
21026141600 | INSTALL 320' OF 2"PMMP MAIN |  |  |  |  | 0.07578% | 51396.03 | 52296.0917 | -900.0617 | 2021-01-01 | 2021-12-31 | 2021-12-22 | 2021-12-28
21026141700 | RETIRE 315' OF 2"PMP MAIN |  |  |  |  | 6.789e-05% | 46.05 | 60.6987 | -14.6487 | 2021-01-01 | 2021-12-31 | 2021-12-22 | 2021-12-28
21026157800 | INSTALL 5'-4" PMLP |  |  |  |  | 0.004067% | 2758.28 | 4114.4273 | -1356.1473 | 2021-01-01 | 2021-12-31 | 2021-12-28 | 2022-01-03
21026157900 | RETIRE 5'-4" PMLP |  |  |  |  | 0.0007155% | 485.31 | 72.8047 | 412.5053 | 2021-01-01 | 2021-12-31 | 2021-12-28 | 2022-01-03
[7 empty] | 2021 Construction Project Budget | 67826000
20026943000 | RETIRE GAUGE |  |  |  |  | 0.002048% | 1496.7 | 91.4991 | 1405.2009 | 2022-01-01 | 2022-12-31 | 2022-01-06 | 2022-01-10 | CCC# 49347 COMMISION ERX CCC# 50118 ERX INSTALLED AND GAUGE RETIRED BY WADE SHIMFESSEL PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/10/22
20026942900 | INSTALL I&C EQUIPMENT |  |  |  |  | 0.01517% | 11090.78 | 16155.4774 | -5064.6974 | 2022-01-01 | 2022-12-31 | 2022-01-06 | 2022-01-10 | ERX INSTALLED BY ACP AND WADE SHIMFESSEL PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/10/22
22026159500 | EMER - INSTALL 5'-3" PMMP |  |  |  |  | 0.01609% | 11760.26 | 5999.0379 | 5761.2221 | 2022-01-01 | 2022-12-31 | 2022-01-10 | 2022-01-10
22026159600 | EMER - RETIRE 5' - 3" PMMP |  |  |  |  | 0% | 0 | 79.0999 | -79.0999 | 2022-01-01 | 2022-12-31 | 2022-01-10 | 2022-01-10
22026159700 | EMER - INSTALL 4'-4" PMLP |  |  |  |  | 0.00262% | 1914.95 | 4455.398 | -2540.448 | 2022-01-01 | 2022-12-31 | 2022-01-24 | 2022-01-24
22026159800 | EMER - RETIRE 4'-4" P-LP |  |  |  |  | 0.008803% | 6434.1 | 448.5353 | 5985.5647 | 2022-01-01 | 2022-12-31 | 2022-01-20 | 2022-01-20 | RETIRED 4' OF 4" PL LP TO REMOVED STEEL SADDLE FROM PLASTIC MAIN
22026160800 | EMER-INSTALL 5' OF 2"PMMP MAIN |  |  |  |  | 0.002886% | 2109.29 | 3947.9695 | -1838.6795 | 2022-01-01 | 2022-12-31 | 2022-01-12 | 2022-01-12
22026159900 | EMER - INSTALL 2'-2" PMLP |  |  |  |  | 0.003295% | 2408.32 | 2367.5988 | 40.7212 | 2022-01-01 | 2022-12-31 | 2022-02-03 | 2022-02-03
22026160900 | EMER-RETIRE 5' OF 2"PAMP MAIN |  |  |  |  | 0% | 0 | 69.6571 | -69.6571 | 2022-01-01 | 2022-12-31 | 2022-01-12 | 2022-01-12
22026160000 | EMER - RETIRE 2'2"P-LP D244381 |  |  |  |  | 0.0006666% | 487.19 | 506.8997 | -19.7097 | 2022-01-01 | 2022-12-31 | 2022-02-07 | 2022-02-07
21026134800 | INSTALL 20'-2" PMMP |  |  |  |  | 0.09217% | 67370.23 | 39141.4028 | 28228.8272 | 2022-01-01 | 2022-12-31 | 2022-01-03 | 2022-01-12
21026134900 | RETIRE 16'-2" CSMP |  |  |  |  | 0% | 0 | 88.8156 | -88.8156 | 2022-01-01 | 2022-12-31 | 2022-01-03 | 2022-01-12
20026926200 | INSTALL NETWORK UPGRADE |  |  |  |  | 0.001168% | 853.47 | 3150 | -2296.53 | 2022-01-01 | 2022-12-31 | 2022-01-12 | 2022-01-12 | SUPER SOLAR KIT AND RV50 INSTALLED BY NOLL DAVIS AND ACP PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/12/22
22026160400 | EMER - REPAIR LEAK |  |  |  |  | 0.01095% | 8003.12 | 3388.6445 | 4614.4755 | 2022-01-01 | 2022-12-31 | 2022-01-13 | 2022-01-13
22026160500 | EMER - REPAIR LEAK |  |  |  |  | 0% | 0 | 69.6571 | -69.6571 | 2022-01-01 | 2022-12-31 | 2022-01-13 | 2022-01-13
21026108801 | INSTALL 1000' OF 2"PMMP MAIN |  |  |  |  | 0.07059% | 51597.09 | 46147.0126 | 5450.0774 | 2022-01-01 | 2022-12-31 | 2022-01-06 | 2022-01-25
22026164900 | EMER-INSTALL 4' OF 3"PMMP MAIN |  |  |  |  | 0.02126% | 15536.92 | 14982.0392 | 554.8808 | 2022-01-01 | 2022-12-31 | 2022-01-31 | 2022-02-17 | INSTALLED 4' OF 030 P DUE TO EXC DMG TEST AT 90# FOR 20 MIN PER FOL APPROVA L, SOAP TEST TWO 030 EF CPLGS AT OP FOR 5 MIN OK. TEST FOR SEC DMG OK. WHIMES 02/17/2022
22026165000 | EMER-RETIRE 4' OF 3"PMP MAIN |  |  |  |  | 0.0001632% | 119.3 | 100.2728 | 19.0272 | 2022-01-01 | 2022-12-31 | 2022-02-17 | 2022-02-17 | COMPLETED W/ JO 22026164900
20026982700 | INSTALL 4500'-2"&4" PMMP |  |  |  |  | 1.212% | 885948.31 | 959444.7901 | -73496.4801 | 2022-01-01 | 2022-12-31 | 2021-10-18 | 2022-03-29
21026140000 | RETIRE 489'-4" PMP |  |  |  |  | 0.02778% | 20306.35 | 13697.8754 | 6608.4746 | 2022-01-01 | 2022-12-31 | 2022-02-01 | 2022-02-09
22026164400 | EMER - INSTALL 10'-2" PMMP |  |  |  |  | 0.01418% | 10363.46 | 13748.6188 | -3385.1588 | 2022-01-01 | 2022-12-31 | 2022-02-08 | 2022-02-08
22026164500 | EMER - RETIRE 10'-2" PMP |  |  |  |  | 0.0001525% | 111.44 | 109.7476 | 1.6924 | 2022-01-01 | 2022-12-31 | 2022-02-08 | 2022-02-08
21026155900 | INSTALL 2400' OF 2"PMMP MAIN |  |  |  |  | 0.09967% | 72846.65 | 61211.3642 | 11635.2858 | 2022-01-01 | 2022-12-31 | 2022-01-06 | 2022-02-10
22026167400 | EMER - INSTALL 5'-3" PMLP |  |  |  |  | 0% | 0 | 3781.5061 | -3781.5061 | 2022-01-01 | 2022-12-31 | 2022-02-09 | 2022-02-09
22026167500 | EMER - RETIRE 5'-3" PLP |  |  |  |  | 0% | 0 | 109.7476 | -109.7476 | 2022-01-01 | 2022-12-31 | 2022-02-09 | 2022-02-09
21026157100 | INSTALL 600'-2" PMMP |  |  |  |  | 0.04035% | 29494.94 | 21934.2504 | 7560.6896 | 2022-01-01 | 2022-12-31 | 2022-02-07 | 2022-02-16
22026162500 | INSTALL 8" STOPPLE FITTING |  |  |  |  | 0.03523% | 25751.7 | 14352.6857 | 11399.0143 | 2022-01-01 | 2022-12-31 | 2022-02-09 | 2022-02-10
22026162600 | RETIRE 44' OF 8"BSMP MAIN |  |  |  |  | 0% | 0 | 105.0102 | -105.0102 | 2022-01-01 | 2022-12-31 | 2022-02-09 | 2022-02-10
21026154000 | INSTALL 160'-2" PMMP |  |  |  |  | 0.03904% | 28534.77 | 33091.7151 | -4556.9451 | 2022-01-01 | 2022-12-31 | 2022-02-07 | 2022-02-14
21026141400 | INSTALL 130'-6" PMMP |  |  |  |  | 0.2449% | 179014.36 | 140177.264 | 38837.096 | 2022-01-01 | 2022-12-31 | 2022-01-11 | 2022-02-15 | PROJECT OVERRUN OF $38,555 (28%) DUE TO ADDITIONAL TIME AND RESOURCES BEING REQUIRED. LABOR HOURS ESTIMATED AT 176 HRS, BUT 319 HRS WERE REQUIRED ($11 ,052 DIFF. LABOR RATE ESTIMTES TOO LOW). NEW CONTRACT WILL ADDITIONAL UNITS WAS USED WHICH ADDED $57,948. BUT THERE WERE SAVINGS OF $30,000 IN THE OT HER CATAGORY, WHICH WERE COVERED WITH UNITS IN THE UPDATED CONTRACT. D.LEMO NS 7/8/2022
21026141500 | RETIRE 316'-6" PM&CS MP |  |  |  |  | 0.005642% | 4123.73 | 76.2083 | 4047.5217 | 2022-01-01 | 2022-12-31 | 2022-01-11 | 2022-02-15
22026160100 | PM-GREENSITE I75 ILI DE RELO |  |  |  |  | 0.008847% | 6466.13 | 0 | 6466.13 | 2022-01-01 | 2022-12-31 | 2022-07-11 | 2022-07-22
22026160200 | PM-GREENSITE I75 ILI DE ABAN |  |  |  |  | 0.0001444% | 105.53 | 0 | 105.53 | 2022-01-01 | 2022-12-31 | 2022-07-11 | 2022-07-22 | GIS HAD LESS FOOTAGE THAN WHAT WAS FIELD VERIFIED. NO FAC CREATED, DUE TO F ACT IT WAS BEING ABANDONED.
20026954900 | INSTALL SKID REG STATION #1574 |  |  |  |  | 0.1143% | 83537.33 | 91083.0917 | -7545.7617 | 2022-01-01 | 2022-12-31 | 2021-03-22 | #N/A | TUBE UP ONE RUN CCC #22458 CCC# 22583 CC# 23111 G.HALE 05-12-21 PLACED RUN 1 IN SERVICE ON 5/6/21 WITH TEMPORARY REGULATORS INSTALLED TO MEET COMMIT DATE WITH BUILDER RUN 2 OFF AND BLIND FLANGED PERMANENT EQUIPMENT ORDER WITH TENTATIVE DELIVERY DATE OF JUNE/JULY 2021 JOB CANNOT BE COMPLETED OR CLOSED OUT UNTIL PERMANENT EQUIPMENT IS INSTALLED CFARIS CCC# 43393 CCC# CALLED IN BY AL PARKS OR CONNER WIMPE CCC#55276 CWEMPE 2/15/22 GCCC# 56179 INSTALLED PERMANENT SLAMSHUT MOONEY'S COMMISSIONED STATION CWEMPE 2-16-22
21026103000 | INSTALL CHAIN LINK FENCE |  |  |  |  | 0.02804% | 20497.91 | 16434.2505 | 4063.6595 | 2022-01-01 | 2022-12-31 | 2021-03-22 | 2022-02-16 | RHAYES 08-24-2021 MONITORED FENCE INSTALLATION CCC 35764 CWEMPE PAPER WORK COMPLETION 2-16-22
22026164600 | EMER - INSTALL 220'-2" PMIP |  |  |  |  | 0.06715% | 49083.09 | 49188.5426 | -105.4526 | 2022-01-01 | 2022-12-31 | 2022-02-22 | 2022-02-22
22026164700 | EMER - RETIRE 20'-4" CSIP |  |  |  |  | 0.0001922% | 140.47 | 109.7476 | 30.7224 | 2022-01-01 | 2022-12-31 | 2022-02-22 | 2022-02-22
21026993800 | INSTALL 7200' OF 2"/6"PMMP |  |  |  |  | 4.114% | 3006825.55 | 2229015.8617 | 777809.6883 | 2022-01-01 | 2022-12-31 | 2022-01-27 | 2022-12-09
21026157200 | INSTALL 16' OF 3"PMMP MAIN |  |  |  |  | 0.07702% | 56295.03 | 11827.5319 | 44467.4981 | 2022-01-01 | 2022-12-31 | 2022-02-16 | 2022-02-23 | TWALKER/KY 02-24-22: WMS WOULD NOT ALLOW PROJECT TO BE REVISED DUE TO UNPAID INVOICES MESSAGE. JOB OVER RUN DUE TO UNKNOWN BOLTED COUPLINGS FOUND DURING CONSTUCTION AND SCOPE OF WORK WAS INCREASED TO REMOVE THOSE COUPLINGS IN THE PAVED STREET. TWALKER/KY 09-16-22: DURING CONSTRUCTION BOLTED COUPLING WERE FOUND ON MP GAS MAIN AND HAD TO BE REMOVED WMS WOULD NOT ALLOW REVISION. ADDITIONAL WORK INCREASED COMPANY LABOR BY $6000 SEGA INCREASED BY $4500 STREET CUT REPAIR REQUIRED AND ADDITIONAL CONTRACT RESOURCES INCREASED BY $27,000
21026157300 | RETIRE 14' OF 3"CSMP MAIN |  |  |  |  | 0% | 0 | 72.8047 | -72.8047 | 2022-01-01 | 2022-12-31 | 2022-02-16 | 2022-02-23
20026940100 | RETIRE PAPER GUAGE |  |  |  |  | 0.0002357% | 172.3 | 91.4991 | 80.8009 | 2022-01-01 | 2022-12-31 | 2022-02-24 | 2022-02-24 | RETIRED PAPER CHART INSTALLED HONEYWELL ERX CCOX 2-24-2022
20026940000 | INSTALL I&C EQUIPMENT |  |  |  |  | 0.01586% | 11589.34 | 16155.4774 | -4566.1374 | 2022-01-01 | 2022-12-31 | 2022-02-24 | 2022-02-24 | CCC# 43689 RETIRED PAPER CHART INSTALLED NEW ERX CCOX 02-24-2022
20026943200 | RETIRE GAUGE |  |  |  |  | 0.0003554% | 259.73 | 91.4991 | 168.2309 | 2022-01-01 | 2022-12-31 | 2022-02-25 | 2022-02-25 | INSTALLED NEW LEGACY ERX RETIRED PAPER CHART BLONE 2-25-2022
20026943100 | INSTALL I&C EQUIPMENT |  |  |  |  | 0.01921% | 14038.9 | 16155.4774 | -2116.5774 | 2022-01-01 | 2022-12-31 | 2022-02-25 | 2022-02-25 | CCC# 43654 INSTALLED ERX RETIRED PAPER CHART BLONE 2-25-2022
22026180900 | EMER-INSTALL 4' OF 2"PMMP |  |  |  |  | 0.005136% | 3753.68 | 3916.7503 | -163.0703 | 2022-01-01 | 2022-12-31 | 2022-02-28 | 2022-02-28
22026181000 | EMER-RETIRE 4' OF 2"PMMP |  |  |  |  | 0% | 0 | 75.4968 | -75.4968 | 2022-01-01 | 2022-12-31 | 2022-02-28 | 2022-02-28
20026928300 | UPGRADE FROM 3G NETWORK |  |  |  |  | 0.009324% | 6815.37 | 3038 | 3777.37 | 2022-01-01 | 2022-12-31 | 2022-02-28 | 2022-02-28 | RETIRED OLD EFC INSTALLED NEW EC350 CCOX 02-28-2022
20026934000 | RETIRE ELECTRONICS |  |  |  |  | 0.0008572% | 626.57 | 73.3494 | 553.2206 | 2022-01-01 | 2022-12-31 | 2022-02-28 | 2022-02-28 | RETIRED OLD EFC AND INSTALLED NEW EC350 CCOX 02-28-2022
21026156600 | INSTALL 230'-2" PMMP |  |  |  |  | 0.02414% | 17647.7 | 15538.521 | 2109.179 | 2022-01-01 | 2022-12-31 | 2022-02-28 | 2022-03-01
21026128000 | INSTALL 265' OF 4" PMLP |  |  |  |  | 0.1314% | 96077.32 | 71153.2979 | 24924.0221 | 2022-01-01 | 2022-12-31 | 2022-02-16 | 2022-03-10 | AWEBER - JO RAN OVER ESTIMATE DUE TO UNFORSEEN 8'X5' STORM BASIN @ 42" BELO W GRADE. EXCAVATION OF TOP OF BASIN OCCURRED TO PROVIDE REROUTE OF 4" PMMP INSTALL AT ACCEPTABLE DEPTH WITHOUT CROSSBORE.
21026128100 | RETIRE 230'-4" & 50'-6" PMLP |  |  |  |  | 9.762e-05% | 71.35 | 354.2624 | -282.9124 | 2022-01-01 | 2022-12-31 | 2022-02-16 | 2022-03-10
20026927900 | UPGRADE ELECTRONICS |  |  |  |  | 0.005009% | 3660.91 | 3038 | 622.91 | 2022-01-01 | 2022-12-31 | 2022-03-02 | 2022-03-02 | EFC REPLACED BY C. COX ON 3-1-22 PAPERWORK CO BY J MULLINS ON 3-2-22
20026933700 | RETIRE ELECTRONICS |  |  |  |  | 0.000619% | 452.45 | 73.3494 | 379.1006 | 2022-01-01 | 2022-12-31 | 2022-03-02 | 2022-03-02 | GAUGE RETIRED BY C. COX PAPPER WORK CO BY J. MULLINS 3-2-2022
22026172500 | INSTALL 5'-1" PMMP |  |  |  |  | 5.883e-06% | 4.3 | 1353.2384 | -1348.9384 | 2022-01-01 | 2022-12-31 | 2022-03-02 | 2022-03-02
22026172600 | RETIRE 5'-1" PAMP |  |  |  |  | 0.003008% | 2198.83 | 66.5954 | 2132.2346 | 2022-01-01 | 2022-12-31 | 2022-03-02 | 2022-03-02
20026928800 | UPGRADE ELECTRONICS |  |  |  |  | 0.009049% | 6614.01 | 3038 | 3576.01 | 2022-01-01 | 2022-12-31 | 2022-03-02 | 2022-03-02 | ASSIST SMCHOLAN 03-02-2022 RHAYES ASSIST SMCHOLAN 03-02-2022 RHAYES INSTALLED NEW EC350 SOAP TEST TUBING 5MIN OPP PRESSURE SMCHOLAN 3-2-22
20026934500 | RETIRE ELECTRONICS |  |  |  |  | 0% | 0 | 73.3494 | -73.3494 | 2022-01-01 | 2022-12-31 | 2022-03-02 | 2022-03-02 | RETIRED MINI-AT INSTALLED NEW EC350 SMCHOLAN 3-2-22
21026140400 | INSTALL 2800' OF 2"/4"PMMP |  |  |  |  | 0.1589% | 116146.05 | 86592.9986 | 29553.0514 | 2022-01-01 | 2022-12-31 | 2022-01-03 | 2022-03-04
16026666400 | INSTALL NEW CWT HEATER |  |  |  |  | 0.2576% | 188315.11 | 231341.3745 | -43026.2645 | 2022-01-01 | 2022-12-31 | 2022-01-26 | 2022-12-16 | CC# 53363. DRAINED WATERBATH HEATER. 01-26-22 DSASH CCC 55246 CCC 55359 CCC 55691 CCC 56098 CCC 57419 NO TICKET NEEDED NO TICKET NEEDED NO TICKET NEEDED CC# 70901. 6/20/22 DSASH RETIRED OLD WATER BATH INSTALLED NEW CWT HEATER DASH 3-3-22
16026666500 | RETIRE EXIST WB HEATER |  |  |  |  | 0.03989% | 29153.65 | 140.0254 | 29013.6246 | 2022-01-01 | 2022-12-31 | 2022-01-26 | 2022-03-03 | CCC # 53363 CCC 53705 CCC 54571 CCC # 54571 NO TICKET NEEDED CCC # 57419 NOT ON SITE NO CCC NEEDED NO CCC NOT ON SITE CHARGED TO LE TO GET VRG FOR REG REPLACE INSTALLED NEW CWT HEATER 3-3-22 DASH
20026930300 | UPGRADE ELECTRONICS |  |  |  |  | 0.01273% | 9306.71 | 3038 | 6268.71 | 2022-01-01 | 2022-12-31 | 2022-03-04 | 2022-03-04 | MET MOOSE ONSITE TO INSTALL SOLAR PANEL, CELL BOOSTER,BATTERY/BOX INSTALLED NEW EC350 WSHIMFESSEL JMULLINS COMPLETED PAPER WORK 06-13-2022
20026937500 | RETIRE ELECTRONICS |  |  |  |  | 0.0001776% | 129.79 | 73.3494 | 56.4406 | 2022-01-01 | 2022-12-31 | 2022-03-04 | 2022-03-04 | RETIRED MINI-AT INSTALLED NEW EC350 JMULLINS CO PAPER WORK 06132022
22026223100 | EMER-INSTALL 3' OF 2"PMMP MAIN |  |  |  |  | 0.005555% | 4059.84 | 4624.3747 | -564.5347 | 2022-01-01 | 2022-12-31 | 2022-10-10 | 2022-10-11 | COMPLETED PAPERWORK FOR JOB. R.CRAWFORD 10-11-22
22026223200 | EMER-RETIRE 3' OF 2"PMP MAIN |  |  |  |  | 0.0001713% | 125.23 | 89.0305 | 36.1995 | 2022-01-01 | 2022-12-31 | 2022-10-10 | 2022-10-17 | R.CRAWFORD
22026174700 | EMER- INSTALL 82'-4" PMIP/CSIP |  |  |  |  | 0.1173% | 85702.82 | 94519.5369 | -8816.7169 | 2022-01-01 | 2022-12-31 | 2022-03-08 | 2022-03-08 | REPAIRED LEAK ON MAIN BY REPLACING A SECTION OF BARE STEEL MAIN WITH 4" PLA STIC TESTED 105 PSIG FOR 1 HOUR WITH ELECTRONIC KUHLMAN GAUGE SERIAL NO 101 09154 3/8/22 REFER TO 2211 JOB ORDER# 22-9840666-00
22026174800 | EMER- RETIRE 76'-4" BSIP |  |  |  |  | 0% | 0 | 0 | 0 | 2022-01-01 | 2022-12-31 | 2022-03-08 | 2022-03-08
21026111902 | INSTALL 7,500' OF 2"/6"PMMP |  |  |  |  | 0.919% | 671698.12 | 670404.9715 | 1293.1485 | 2022-01-01 | 2022-12-31 | 2021-09-23 | 2022-03-11 | LOWES (#207438) - MATERIAL FOR ECP - $27.62 + 10% = $30.38 U461423 9/2 3/2021 SITE SUPPLY (#207438) - MULCH LOGS - #424.00 + 10% = 466.40 U461423 9/23/2021
22026158100 | INSTALL 70'-2" PMMP |  |  |  |  | 0.01459% | 10660.65 | 9277.6445 | 1383.0055 | 2022-01-01 | 2022-12-31 | 2022-03-07 | 2022-03-10 | INSTALED 57'OF 020PMMP.
20026982900 | RETIRE 3700'-2&4" BSLP |  |  |  |  | 0.0001952% | 142.7 | 88.8156 | 53.8844 | 2022-01-01 | 2022-12-31 | 2021-09-30 | 2022-04-01
22026179300 | RETIRE 82'-2"&4" PMMP |  |  |  |  | 0.0001133% | 82.8 | 73.9724 | 8.8276 | 2022-01-01 | 2022-12-31 | 2021-09-30 | 2022-04-02
22026175800 | EMER - INSTALL 120'-3" PMLP |  |  |  |  | 0.04395% | 32123.93 | 12124.3189 | 19999.6111 | 2022-01-01 | 2022-12-31 | 2022-03-11 | 2022-04-05 | INSTALLED 120' OF 3" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 10" W C
22026175900 | EMER - RETIRE 121'-3" P-LP |  |  |  |  | 0.001275% | 931.56 | 373.4562 | 558.1038 | 2022-01-01 | 2022-12-31 | 2022-03-11 | 2022-04-05 | RETIRE 121' OF 3" PL DUE TO WATER AND STEEL FITTINGS ON PL MAIN
22026158000 | INSTALL 200'-2" PMMP |  |  |  |  | 0.03262% | 23838.83 | 16273.357 | 7565.473 | 2022-01-01 | 2022-12-31 | 2022-03-14 | 2022-03-16
22026172900 | INSTALL 5' OF 4"PMLP S/L |  |  |  |  | 0.004259% | 3113 | 13312.2384 | -10199.2384 | 2022-01-01 | 2022-12-31 | 2022-03-15 | 2022-03-15
20026971200 | RETIRE 2100' OF 3"BSLP MAIN |  |  |  |  | 0.001937% | 1415.61 | 102.0836 | 1313.5264 | 2022-01-01 | 2022-12-31 | 2022-03-16 | 2022-03-18
22026172800 | RETIRE 5' OF 3"PLP S/L |  |  |  |  | 0% | 0 | 58.5954 | -58.5954 | 2022-01-01 | 2022-12-31 | 2022-03-16 | 2022-03-16 | ABANDONED CAPITAL SERVICE LINE WITH ABANDON JOB # 18-0268434-00. LSHARON
22026168800 | ST. JAMES HVAC UPGRADE |  |  |  |  | 0.03373% | 24656.22 | 37587.0767 | -12930.8567 | 2022-01-01 | 2022-12-31 | 2022-03-16 | 2022-08-05 | MONITOR WHILE ACP SWAPS RTU STATION SET TO LOCAL MODE GC ADVISED CC 58614 UPGRADE RTU ON 3-16-22 JOSH MULLINS
22026214700 | ST. JAMES RTU PANEL |  |  |  |  | 0% | 0 | 55.5311 | -55.5311 | 2022-01-01 | 2022-12-31 | 2022-03-16 | 2022-08-05 | UPGRADED RTU JOSH MULLINS
22026158400 | INSTALL 1200' OF 2"PMMP MAIN |  |  |  |  | 0.03986% | 29132.57 | 35742.3291 | -6609.7591 | 2022-01-01 | 2022-12-31 | 2022-03-14 | 2022-03-18
22026177000 | EMER - INSTALL 2'-4" PMIP |  |  |  |  | 0.003137% | 2292.91 | 4197.8249 | -1904.9149 | 2022-01-01 | 2022-12-31 | 2022-04-01 | 2022-04-01
22026177100 | EMER - RETIRE 2'-4" P-IP |  |  |  |  | 0.003266% | 2387.49 | 310.9595 | 2076.5305 | 2022-01-01 | 2022-12-31 | 2022-04-01 | 2022-04-01
22026244600 | INSTALL BUILDING AND FENCE |  |  |  |  | 0% | 0 | 28935.3221 | -28935.3221 | 2022-01-01 | 2022-12-31 | 2022-03-17 | 2022-03-17 | INSTALLED COMM BUILDING AND FENCE DASH 3-17-22
19026855301 | INSTALL RTU AND BUILDING |  |  |  |  | 0.2545% | 186001.86 | 182784.6097 | 3217.2503 | 2022-01-01 | 2022-12-31 | 2022-03-17 | 2022-03-17 | INSTALLED NEW RTU DASH 3-17-22
19026855400 | RETIRE OLD RTU EQUIPMENT |  |  |  |  | 0.007141% | 5219.78 | 69.4128 | 5150.3672 | 2022-01-01 | 2022-12-31 | 2022-03-17 | 2022-03-17 | INSTALLED NEW COMM BUILDING AND RTU DASH 3-17-22
22026159400 | RETIRE S/L |  |  |  |  | 0.002778% | 2030.55 | 3024.4273 | -993.8773 | 2022-01-01 | 2022-12-31 | 2022-03-21 | 2022-03-21
22026168900 | STEPSTONE POD HVAC UPGRADE |  |  |  |  | 0.02696% | 19703.94 | 15710.0767 | 3993.8633 | 2022-01-01 | 2022-12-31 | 2022-03-24 | 2022-08-05 | CCC# 59338 CCC# 55889 UPGRADED RTU JOSH MULLINS
22026214300 | STEPSTONE POD HVAC/RTU |  |  |  |  | 0% | 0 | 55.5311 | -55.5311 | 2022-01-01 | 2022-12-31 | 2022-03-24 | 2022-08-05 | UPGRADED RTU
21026130902 | INSTALL 5150' OF 2"/4" PMMP |  |  |  |  | 0.2636% | 192645.27 | 202239.5285 | -9594.2585 | 2022-01-01 | 2022-12-31 | 2022-01-26 | 2022-04-08
19026867100 | INSTALL VRG CONTROLLER |  |  |  |  | 0.02178% | 15917.94 | 15490.7518 | 427.1882 | 2022-01-01 | 2022-12-31 | 2022-03-29 | 2022-03-29 | CCC 59916 CCC # 59916 INSTALLED NEW VRG CONTROLLERS DASH 3-29-22
19026867200 | RETIRE CURRENT CONTROLLERS |  |  |  |  | 0.001421% | 1038.8 | 64.4897 | 974.3103 | 2022-01-01 | 2022-12-31 | 2022-03-29 | 2022-03-29 | CCC # INSTALLED NEW VRG'S RETIRED EXSISTING CONTROLLERS DASH 3-29-22
22026179500 | EMER - INSTALL 5'-2" PMIP |  |  |  |  | 0.00321% | 2346.49 | 5401.378 | -3054.888 | 2022-01-01 | 2022-12-31 | 2022-04-05 | 2022-04-05
22026179600 | EMER - RETIRE 5'-2" P-IP |  |  |  |  | 0% | 0 | 238.1994 | -238.1994 | 2022-01-01 | 2022-12-31 | 2022-04-05 | 2022-04-05
22026163700 | RETIRE 4"BSLP SERVICE LINE |  |  |  |  | 0.001816% | 1327.16 | 105.0102 | 1222.1498 | 2022-01-01 | 2022-12-31 | 2022-04-08 | 2022-04-08 | CAPITAL SERVICE LINE WAS ABANDONED WITH JOB NUMBER 18-0268433-01 TIE IN A1A2. LSHARON
22026180700 | EMER - INSTALL 3'-3" PMIP |  |  |  |  | 0.009168% | 6701.19 | 4036.7887 | 2664.4013 | 2022-01-01 | 2022-12-31 | 2023-08-25 | 2023-08-25
22026180800 | EMER - RETIRE 3'-3" PMIP |  |  |  |  | 8.4e-05% | 61.4 | 418.4749 | -357.0749 | 2022-01-01 | 2022-12-31 | 2023-08-25 | 2023-08-25
21026140901 | INSTALL 2750' OF 2"PMMP MAIN |  |  |  |  | 0.1424% | 104070.68 | 96941.3864 | 7129.2936 | 2022-01-01 | 2022-12-31 | 2022-03-14 | 2022-04-15
22026182800 | EMER-INSTALL 3' OF 2"PMMP |  |  |  |  | 0.006046% | 4419.13 | 4826.1382 | -407.0082 | 2022-01-01 | 2022-12-31 | 2022-04-20 | 2022-04-20 | INSTALLED 3' OF 2" PMMP DUE TO EXCAVATION DAMAGE, TESTED MAIN PIPE AT 90# F OR 20 MIN PER FOL APPROVAL OK, SOAP TEST 2 020 EF CPLGS AT OP FOR 5 MIN OK. INSTALLED MARKER BALLS ON CPLGS. MAP REVISED. WHIMES
22026182900 | EMER-RETIRE 3' OF 2"PMMP |  |  |  |  | 3.721e-06% | 2.72 | 74.2578 | -71.5378 | 2022-01-01 | 2022-12-31 | 2022-04-20 | 2022-04-20 | RETIRED 3' OF 020 PMMP DUE TO EXCAVATION DAMAGE. WHIMES 04/20/2022
21026157000 | RETIRE 10'-6" PMLP |  |  |  |  | 0% | 0 | 72.8047 | -72.8047 | 2022-01-01 | 2022-12-31 | 2022-04-08 | 2022-04-20
22026182300 | RETIRE PAPER RECORD GAUGE |  |  |  |  | 0.0001975% | 144.38 | 329.4627 | -185.0827 | 2022-01-01 | 2022-12-31 | 2022-04-20 | 2022-04-20
21026103400 | INSTALL 2,700' - 2"/4" PMMP |  |  |  |  | 0.2538% | 185537.75 | 115766.1902 | 69771.5598 | 2022-01-01 | 2022-12-31 | 2022-03-09 | 2022-04-22 | TTOY-9/20/22: LEVEL 2 VARIANCE OVERRUN EXPLANATION IN WMSDOCS
21026994200 | RETIRE 3" SERVICE |  |  |  |  | 0% | 0 | 98.6196 | -98.6196 | 2022-01-01 | 2022-12-31 | 2022-04-21 | 2022-04-21
20026992100 | RETIRE STATION |  |  |  |  | 0% | 0 | 3400.2343 | -3400.2343 | 2022-01-01 | 2022-12-31 | 2022-04-21 | 2022-04-21 | RETIRED REGULATOR STATION JMARTIN
21026107000 | INSTALL 250' - 2" PMMP |  |  |  |  | 0.09961% | 72807.39 | 25983.7669 | 46823.6231 | 2022-01-01 | 2022-12-31 | 2022-04-22 | 2022-04-22 | OVERRUN EXPLANATION: PROJECT WAS PLANNED FOR OPEN CUT, NEW MAIN WAS INSTALL ED BY HEAVY ROCK BORE, ADDITIONAL LAND SERVICES WAS REQUIRED FOR EASMENT, BORE CREW HOURLY WAS MORE THAN ESTIMATED 3 MAN CREW
20026973800 | RETIRE 6801'-4' CILP |  |  |  |  | 0.002054% | 1501.61 | 107.2796 | 1394.3304 | 2022-01-01 | 2022-12-31 | 2022-04-22 | 2022-05-05
20026974100 | RETIRE 385'- 3" & 4" |  |  |  |  | 0.003612% | 2639.76 | 8962.6172 | -6322.8572 | 2022-01-01 | 2022-12-31 | 2022-04-22 | 2022-05-05
21026101600 | RETIRE 1200'-2"&4" BSMP |  |  |  |  | 0.0004458% | 325.85 | 85.0089 | 240.8411 | 2022-01-01 | 2022-12-31 | 2022-03-10 | 2022-05-06
21026142800 | INSTALL 475'-4" PMLP |  |  |  |  | 0.1892% | 138313.25 | 59783.3635 | 78529.8865 | 2022-01-01 | 2022-12-31 | 2022-04-08 | 2022-04-29 | TTOY-9/20/22: OVERRUN LEVEL 2 VARIANCE EXPLANATION IN WMSDOCS
21026126700 | INSTALL 350' OF 2" PMMP |  |  |  |  | 0.136% | 99374.93 | 123612.3972 | -24237.4672 | 2022-01-01 | 2022-12-31 | 2022-04-15 | 2022-05-09
21026126102 | INSTALL 2000' OF 2"PMMP MAIN |  |  |  |  | 0.2316% | 169255.42 | 165212.1661 | 4043.2539 | 2022-01-01 | 2022-12-31 | 2022-04-27 | 2022-08-02
21026126200 | RETIRE 270' OF 1"BSHP MAIN |  |  |  |  | 0% | 0 | 63.0891 | -63.0891 | 2022-01-01 | 2022-12-31 | 2022-04-29 | 2022-08-02
22026216900 | PAPER ONLY EXECUTE |  |  |  |  | 0% | 0 | 84.9152 | -84.9152 | 2022-01-01 | 2022-12-31 | 2022-04-29 | 2022-04-29
21026126600 | RETIRE REG STATION #1181 |  |  |  |  | 0.001875% | 1370.38 | 4088.2989 | -2717.9189 | 2022-01-01 | 2022-12-31 | 2022-04-29 | 2022-04-29 | RWILLIAMS COMPLETED PAPER WORK, EBLANTON RETIRED STATION ON 04/29/2022
20026981800 | RETIRE 18,000 - MP MAIN |  |  |  |  | 0% | 0 | 82.4486 | -82.4486 | 2022-01-01 | 2022-12-31 | 2022-05-10 | 2022-05-26
21026134500 | INSTALL 1537'-2"PMIP |  |  |  |  | 0.4546% | 332303.55 | 208782.1462 | 123521.4038 | 2022-01-01 | 2022-12-31 | 2022-04-27 | 2022-08-26 | SEE PROJECT WORKSPACE 21-81540 FOR PROJECT OVERRUN EXPLANATION. D.LEMONS 10 /26/2022
21026117500 | INSTALL GMB SETTING |  |  |  |  | 0.1062% | 77589.89 | 58469.7613 | 19120.1287 | 2022-01-01 | 2022-12-31 | 2022-01-18 | 2022-05-03
22026166200 | INSTALL 20' OF 3"PMMP MAIN |  |  |  |  | 0.03179% | 23237.34 | 28323.8584 | -5086.5184 | 2022-01-01 | 2022-12-31 | 2022-05-02 | 2022-05-04
22026166300 | RETIRE 12' OF 3"PMP MAIN |  |  |  |  | 0.0001241% | 90.73 | 62.3079 | 28.4221 | 2022-01-01 | 2022-12-31 | 2022-05-05 | 2022-05-05
22026158200 | INSTALL 100'-2" PMMP |  |  |  |  | 0.03104% | 22688.28 | 26700.5988 | -4012.3188 | 2022-01-01 | 2022-12-31 | 2022-05-04 | 2022-05-06
21026134600 | RETIRE 1053'-2" CSIP |  |  |  |  | 0% | 0 | 109.7476 | -109.7476 | 2022-01-01 | 2022-12-31 | 2022-05-02 | 2022-08-26
22026174900 | INSTALL 50'-2" PMMP |  |  |  |  | 0.0505% | 36910.2 | 30717.8249 | 6192.3751 | 2022-01-01 | 2022-12-31 | 2022-05-09 | 2022-05-11
22026185100 | INSTALL 10'-2" PMMP |  |  |  |  | 0.008378% | 6123.2 | 3850.4525 | 2272.7475 | 2022-01-01 | 2022-12-31 | 2022-05-10 | 2022-05-10
22026185200 | RETIRE 10'-2" PMP |  |  |  |  | 0% | 0 | 74.2578 | -74.2578 | 2022-01-01 | 2022-12-31 | 2022-05-10 | 2022-05-10
21026111300 | RETIRE R-1654 |  |  |  |  | 0% | 0 | 3585.1779 | -3585.1779 | 2022-01-01 | 2022-12-31 | 2022-05-10 | 2022-05-10 | ENTIRE STATION RETIRED INCLUDING INLET AND OUTLET PIPING WSHIMFESSEL 5/10/2 022, RWILLIAMS COMPLETED JOB AND PAPERWORK
22026209500 | RETIRE CHAIN LINK FENCE |  |  |  |  | 0% | 0 | 65.0112 | -65.0112 | 2022-01-01 | 2022-12-31 | 2022-05-10 | 2022-05-10
22026178100 | INSTALL 20' OF 6"PMLP MAIN |  |  |  |  | 0.02023% | 14787.97 | 11448.7503 | 3339.2197 | 2022-01-01 | 2022-12-31 | 2022-05-04 | 2022-05-25
21026131200 | INSTALL 4875' OF 2"/4"PMMP |  |  |  |  | 0.1922% | 140463.01 | 141168.2553 | -705.2453 | 2022-01-01 | 2022-12-31 | 2022-03-21 | 2022-05-16
21026128802 | INSTALL 470' OF 4"PMMP MAIN |  |  |  |  | 0.1453% | 106230.58 | 96528.8129 | 9701.7671 | 2022-01-01 | 2022-12-31 | 2022-04-27 | 2022-05-25
21026114500 | RETIRE PIT REG STATION# 1024 |  |  |  |  | 0.2669% | 195061.46 | 149437.1771 | 45624.2829 | 2022-01-01 | 2022-12-31 | 2022-05-12 | 2022-05-12 | REMOVED 2 441 REGS AND BLIND FLANGED VALVES, STATION RETIRED, CMCHOLAN CCOX RHAYES 5-12-2022 RWILLIAMS COMPLETED PAPER WORK TWALKER/KY 11-30-22: JOB OVER RUN WAS DUE TO COST FOR 20-0269890-00 (2000) WITH LAND SERVICE AND CONTRACT ENG COST OF $65000, 19-0268950-00 (0001) MATERIAL FOR LPP MATERIAL OF $84000 AND 18-0268465-00 (2000) LAND SERVICES FOR LPP PROJECT APPROV $45000 FROM PROJECT MANAGEMENT AND GTMR GROUPS.
23026253500 | PM-GREENSITE IRONWORKS DE REPL |  |  |  |  | 0.02597% | 18978.29 | 1236355 | -1217376.71 | 2022-01-01 | 2022-12-31 | 2022-02-11 | 2022-05-13
22026179400 | RETIRE 100' OF 4"PMMP MAIN |  |  |  |  | 0% | 0 | 75.4968 | -75.4968 | 2022-01-01 | 2022-12-31 | 2022-05-13 | 2022-05-13
23026253600 | PM-GREENSITE IRONWORKS ABAN |  |  |  |  | 0% | 0 | 0 | 0 | 2022-01-01 | 2022-12-31 | 2022-05-13 | 2022-05-13
22026177700 | INSTALL 56'-6" PM-LP |  |  |  |  | 0.1379% | 100820.74 | 50137.1407 | 50683.5993 | 2022-01-01 | 2022-12-31 | 2022-04-25 | 2022-05-16 | OVERRUN EXPLANATION: PROJECT WAS INITIALLY PLANNED FOR 56 FEET OF INSTALL. HOWEVER, 171 FEET OF DIRECTIONAL ROCK BORE WERE REQUIRED INSTEAD WITHOUT A SCOPE CHANGE REQUEST. ADDITIONAL SAW CUT AND CUT AND REMOVE WERE REQUIRED A S WELL. STEEL PLATES WERE NOT ESTIMATED. $7000 OF SEWER CAMERA WERE NOT EST IMATED EITHER SINCE IT WAS INITALLY PLANNED DIFFERENTLY. ALL THIS ADDITIONA L WORK TOOK MORE TIME SO LABOR INCREASED BY $19,000 AND THE OVERHEAD EFFECT OF THESE CHANGES WAS $9000.
22026177800 | ABDN 20'-6" BS-LP |  |  |  |  | 0.0001952% | 142.7 | 73.9724 | 68.7276 | 2022-01-01 | 2022-12-31 | 2022-05-16 | 2022-05-16
22026187600 | REPLACE ELECTRONIC COMPONENTS |  |  |  |  | 0.04275% | 31245.53 | 5349.5438 | 25895.9862 | 2022-01-01 | 2022-12-31 | 2022-05-16 | 2022-05-16 | CCC# 67613 REPLACED ERX WITH NEW MIWI 350. P2P OK, JMARTIN CCC# 67613
22026187700 | RETIRE ELECTRONIC COMPONENTS |  |  |  |  | 5.399e-05% | 39.46 | 124.5156 | -85.0556 | 2022-01-01 | 2022-12-31 | 2022-05-16 | 2022-05-16 | CCC# 67613 RETIRE ERX JMARTIN
22026178200 | INSTALL 850'-2" PMIP |  |  |  |  | 0.0393% | 28727.79 | 33743.7503 | -5015.9603 | 2022-01-01 | 2022-12-31 | 2022-05-13 | 2022-05-17
22026185400 | EXCHANGE ELECTRONIC COMPONENTS |  |  |  |  | 0.001992% | 1456 | 5480.5156 | -4024.5156 | 2022-01-01 | 2022-12-31 | 2022-05-17 | 2022-05-17 | JMARTIN REMOVED OLD ERX AND INSTALLED NEW MIWI 350 5-17-2022
22026185500 | RETIRE COMPONENTS |  |  |  |  | 0.000979% | 715.54 | 124.5156 | 591.0244 | 2022-01-01 | 2022-12-31 | 2022-05-17 | 2022-05-17 | CCC# 67011 NOT ABLE TO COMP AT THIS TIME, HAS OLDER ERX AND NEED MORE PARTS. JMARTIN 5-16-22 CCC# 67183 REPLACE ERX WITH NEW MIWI 350. JMARTIN
22026165100 | INSTALL 300'-2" PMIP |  |  |  |  | 0.04666% | 34102.05 | 29167.1057 | 4934.9443 | 2022-01-01 | 2022-12-31 | 2022-05-15 | 2022-05-18
21026111400 | RETIRE R-1653-B LP |  |  |  |  | 0% | 0 | 3585.1779 | -3585.1779 | 2022-01-01 | 2022-12-31 | 2022-05-18 | 2022-05-18 | RETIRED LP RUN FROM R-1653 BLIND FLANGED INLET VALVE AND BYPASS VALVE WSHIM FESSEL, RWILLIAMS COMPLETED JOB AND PAPERWORK
22026187000 | EXCHANGE ELECTRONIC COMPONENTS |  |  |  |  | 0.001506% | 1100.73 | 4357.5409 | -3256.8109 | 2022-01-01 | 2022-12-31 | 2022-05-18 | 2022-05-18 | CCC# 67356 REPLACE ERX WITH NEW MIWI 350, P2P OK, JMARTIN CCC# 67669 WORKED TO FIX COMM ISSUE WITH MIWI. CCC# 67669
22026187100 | RETIRE ELECTRONIC COMPONENTS |  |  |  |  | 0% | 0 | 124.5156 | -124.5156 | 2022-01-01 | 2022-12-31 | 2022-05-18 | 2022-05-18 | RETIRED OLD ERX JMARTIN 5/18/2022
22026186600 | EXCHANGE ELECTRONIC COMPONENTS |  |  |  |  | 0.0008434% | 616.42 | 4216.5438 | -3600.1238 | 2022-01-01 | 2022-12-31 | 2022-05-19 | 2022-05-19 | INSTALLED MIWI 350 AND TUBING, CCC 67481 CMCHOLAN 5-19-2022 NOT ON SITE, TURNED IN PAPERWORK IN WINCHESTER, NO CCC TICKET, CMCHOLAN 5-20-2022
22026186700 | RETIRE ELECTRONIC COMPONENTS |  |  |  |  | 0.0006643% | 485.53 | 124.5156 | 361.0144 | 2022-01-01 | 2022-12-31 | 2022-05-19 | 2022-05-19 | REMOVED ERX, CCC 67481 CMCHOLAN 5-19-2022 RWILLIAMS EX CAPITAL JOB
22026187400 | EXCHANGE ELECTRONIC COMPONENTS |  |  |  |  | 0.001391% | 1016.56 | 4773.0565 | -3756.4965 | 2022-01-01 | 2022-12-31 | 2022-05-20 | 2022-05-20 | CCC# 67055 INSTALL NEW MIWI 350, P2P OK, JMARTIN CCC# 67183
22026187500 | RETIRE ELECTRONIC COMPONENTS |  |  |  |  | 0% | 0 | 124.5156 | -124.5156 | 2022-01-01 | 2022-12-31 | 2022-05-20 | 2022-05-20
22026197700 | INSTAL 3'-2" PMMP |  |  |  |  | 0.001795% | 1311.83 | 2387.9592 | -1076.1292 | 2022-01-01 | 2022-12-31 | 2022-05-21 | 2022-06-07 | HIT MAIN BY CONCRETE STAKE.MADE SAFE BY SQUEEZING OFF IN TWO BELL HOLES. REPLACED DAMAGED SECTION OF PIPE.TESTED 10FT OF 020 AND PURGE TEE FOR 1HR 90LBS.TEST OK.SOAP TEST END CAP AND 2EFC'S CPLGS AT OP.TEST OK BHB NGF
22026197800 | RETIRE 3'-2" PMMP |  |  |  |  | 0.001251% | 914.45 | 76.9137 | 837.5363 | 2022-01-01 | 2022-12-31 | 2022-05-21 | 2022-06-07 | HIT MAIN BY CONCRETE STAKE.MADE SAFE BY SQUEEZING OFF IN TWO BELL HOLES. REPLACED DAMAGED SECTION OF PIPE.TESTED 10FT OF 020 AND PURGE TEE FOR 1HR 90LBS.TEST OK.SOAP TEST END CAP AND 2EFC'S CPLGS AT OP.TEST OK BHB NGF
22026186200 | EXCHANGE ELECTRONIC COMPONENTS |  |  |  |  | 0% | 0 | 5480.5156 | -5480.5156 | 2022-01-01 | 2022-12-31 | 2022-05-23 | 2022-05-23 | INSTALLED NEW MIWI 350 05/23/2022 GHALE
22026186300 | RETIRE ELECTRONIC COMPONENTS |  |  |  |  | 0.0002604% | 190.3 | 124.5156 | 65.7844 | 2022-01-01 | 2022-12-31 | 2022-05-23 | 2022-05-23 | RETIRED OLD ERX 05/23/2022 GHALE
22026186400 | EXCHANGE ELECTRONIC COMPONENTS |  |  |  |  | 0.000751% | 548.88 | 5480.5156 | -4931.6356 | 2022-01-01 | 2022-12-31 | 2022-05-24 | 2022-05-24 | CCC# 68048 RETIRED ERX AND INSTALLED NEW MIWI350 JPASLEY
22026186500 | RETIRE ELECTRONIC COMPONENTS |  |  |  |  | 0% | 0 | 124.5156 | -124.5156 | 2022-01-01 | 2022-12-31 | 2022-05-24 | 2022-05-24 | RETIRED ERX AND INSTALLED NEW MIWI350 JPASLEY
21026128900 | RETIRE 440' OF 4"BSMP MAIN |  |  |  |  | 4.232e-05% | 30.93 | 67.1085 | -36.1785 | 2022-01-01 | 2022-12-31 | 2022-05-24 | 2022-06-30 | X
21026129000 | RETIRE 680'-4"BSLP MN -D247885 |  |  |  |  | 0% | 0 | 67.1085 | -67.1085 | 2022-01-01 | 2022-12-31 | 2022-05-25 | 2022-05-25
20026981700 | RETIRE 15,000' - LP MAIN |  |  |  |  | 0% | 0 | 82.4486 | -82.4486 | 2022-01-01 | 2022-12-31 | 2022-05-25 | 2022-05-26
21026140100 | INSTALL 52'-4"/6" PMIP/CSIP |  |  |  |  | 0.09214% | 67346.12 | 83495.319 | -16149.199 | 2022-01-01 | 2022-12-31 | 2022-05-16 | 2022-05-31
21026140200 | RETIRE 47'-4"/6" BSIP/CSIP |  |  |  |  | 0.0002836% | 207.25 | 500 | -292.75 | 2022-01-01 | 2022-12-31 | 2022-05-25 | 2022-05-31
22026187800 | INSTALL 10' OF 4"PMLP MAIN |  |  |  |  | 0.03978% | 29076.83 | 18153.0818 | 10923.7482 | 2022-01-01 | 2022-12-31 | 2022-05-23 | 2022-05-25
22026187900 | RETIRE 8' OF 4"PMLP MAIN |  |  |  |  | 0% | 0 | 74.2578 | -74.2578 | 2022-01-01 | 2022-12-31 | 2022-05-24 | 2022-05-25
20026984500 | REPLACE IP OUTLET BLOCK VALVE |  |  |  |  | 0.002026% | 1480.71 | 2174.0477 | -693.3377 | 2022-01-01 | 2022-12-31 | 2022-05-25 | 2022-05-25 | NOT ON SITE REPLACED INLET AND OUTLET IP RUN BLOCK VALVES SGIORDANO JMULLINS CO PAPERWORK 06132022
20026984600 | REPLACE IP OUTLET BLOCK VALVE |  |  |  |  | 0.003296% | 2409.31 | 50 | 2359.31 | 2022-01-01 | 2022-12-31 | 2021-07-21 | 2022-05-25 | CCC 68181 REPLACED INLET AND OUTLET IP BLOCK VALVS SGIORDANO JMULLINS CO PAPERWORK 06132022
22026185800 | EXCHANGE ELECTRONIC COMPONENTS |  |  |  |  | 0.00251% | 1834.52 | 5480.5156 | -3645.9956 | 2022-01-01 | 2022-12-31 | 2022-05-25 | 2022-05-25 | CCC# 68240 - REPLACED ERX WITH MIWI 350 - BLONE/CWEMPE - 05/25/22 INSTALLED NEW MIWI 350
22026185900 | RETIRE ELECTRONIC COMPONETS |  |  |  |  | 0.0006867% | 501.88 | 124.5156 | 377.3644 | 2022-01-01 | 2022-12-31 | 2022-05-25 | 2022-05-25 | CCC# 68240 - REPLACED ERX WITH MIWI 350 - BLONE/CWEMPE - 05/25/22 RETIRED OLD ERX
20026973500 | RETIRE STATION R-1458 |  |  |  |  | 0.001772% | 1295 | 1281.7771 | 13.2229 | 2022-01-01 | 2022-12-31 | 2022-05-26 | 2022-05-26
22026187200 | EXCHANGE ELECTRONIC COMPONENTS |  |  |  |  | 0.002506% | 1831.39 | 4745.0565 | -2913.6665 | 2022-01-01 | 2022-12-31 | 2022-05-26 | 2022-05-26 | CCC# 68726 INSTALLED NEW MIWI 350 AJPARKS
22026187300 | RETIRE ELECTRONIC COMPONENTS |  |  |  |  | 0.0002541% | 185.7 | 124.5156 | 61.1844 | 2022-01-01 | 2022-12-31 | 2022-05-26 | 2022-05-26 | CCC# 68726 RETIRED ERX 05/26/2022 APARKS
20026943400 | RETIRE GAUGE |  |  |  |  | 0.0007431% | 543.13 | 91.4991 | 451.6309 | 2022-01-01 | 2022-12-31 | 2022-05-27 | 2022-05-27 | REMOVED BOTH PAPER CHARTS INSTALLED ERX CC 62655 RHAYES SMCHOLAN CCOX EBLANTON 04-14-2022
20026943300 | INSTALL I&C EQUIPMENT |  |  |  |  | 0.01251% | 9146.19 | 16155.4774 | -7009.2874 | 2022-01-01 | 2022-12-31 | 2022-04-14 | 2022-05-27 | REMOVED BOTH PAPER CHARTS INSTALLED ERX FOR IP AND MP CMCHOLAN 4-14-2022 CC 65476 COMMISSIONED ERX RHAYES SMCHOLAN 05-03-2022 COMMITIONED ERX, PSP OK, CCC 65476 CMCHOLAN RHAYES 5-3-2022
22026186000 | EXCHANGE ELECTRONIC COMPONENTS |  |  |  |  | 0.00438% | 3201.06 | 5480.5156 | -2279.4556 | 2022-01-01 | 2022-12-31 | 2022-05-27 | 2022-05-27 | ACP REMOVED ERX REPLACED WITH MIWI CCOX RHAYES 05-27-2022
22026186100 | RETIRE ELECTRONIC COMPONENTS |  |  |  |  | 0.0002401% | 175.52 | 124.5156 | 51.0044 | 2022-01-01 | 2022-12-31 | 2022-05-27 | 2022-05-27 | ACP REPLACED ERX WITH MIWI RHAYES CCOX 05-27-2022 ACP REPLACED ERX WITH MIWI RHAYES CCOX 05-27-2022
21026112300 | INSTALL 180' OF 4"PMMP S/L |  |  |  |  | 0.03334% | 24370.71 | 28556.5857 | -4185.8757 | 2022-01-01 | 2022-12-31 | 2022-05-23 | #N/A
22026227000 | EMER-INSTALL 3' OF 2"PMMP MAIN |  |  |  |  | 0.007809% | 5707.92 | 5024.0582 | 683.8618 | 2022-01-01 | 2022-12-31 | 2022-06-02 | 2022-09-30 | INST 3" OF 2 P MP MAIN PER GAS STANDARDS. MCRAIG 9/30/22
22026196200 | EMER - INSTALL 1'-2" PMMP |  |  |  |  | 0.008907% | 6510.29 | 2866.3857 | 3643.9043 | 2022-01-01 | 2022-12-31 | 2022-06-02 | 2022-06-15 | INSTALLED 1' OF 2" PL DUE TO FACILTY DAMAGE TESTED 90 PSIG 0005 MIN SOAP TE STED FINAL CONN OP 42 PSIG REVISED EXECUTE COMMENTS: INSTALLED 1' OF 2" PL DUE TO FACILITY DAMAGE TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 42 PSIG/MCOLLETT 7/8/22
22026227100 | EMER-RETIRE 3' OF 2"PMP MAIN |  |  |  |  | 0.0004324% | 316.08 | 74.3089 | 241.7711 | 2022-01-01 | 2022-12-31 | 2022-06-02 | 2022-09-30 | ABN 3' OF 2" P MP MAIN DUE TO LEAK. PER GAS STANDARDS. MCRAIG 9/30/22
22026196300 | EMER - RETIRE 1'-2" P-MP |  |  |  |  | 0.001716% | 1254.11 | 497.9695 | 756.1405 | 2022-01-01 | 2022-12-31 | 2022-06-02 | 2022-06-15 | RETIRED 1' OF 2" PL MP DUE TO FACILITY DAMAGE SOAP TESTED OP TO VERIFY GAS SHUTOFF
22026188400 | EXCHANGE ELECTRONIC COMPONENTS |  |  |  |  | 0.001992% | 1456 | 6681.5691 | -5225.5691 | 2022-01-01 | 2022-12-31 | 2022-06-02 | 2022-06-02 | CCC# 69290 - BLONE - 06/02/22 INSTALLED MIWI SN:13450082 P1-0-PSI P2-0-60 IP:10.22.4.15MDN 859-221-6738
22026188500 | RETIRE ELECTRONICS |  |  |  |  | 0.0006478% | 473.46 | 74.2578 | 399.2022 | 2022-01-01 | 2022-12-31 | 2022-06-02 | 2022-06-02 | CCC# 69290 - BLONE - 06/02/22
22026186800 | EXCHANGE ELECTRONIC COMPONENTS |  |  |  |  | 0.001992% | 1456 | 4357.5409 | -2901.5409 | 2022-01-01 | 2022-12-31 | 2022-06-03 | 2022-06-03 | CCC-69443 INSTALLED NEW MIWI 350 SOAP TEST CONNECTIONS EBLANTON
22026186900 | RETIRE ELECTRONIC COMPONENTS |  |  |  |  | 0.0006896% | 504.03 | 124.5156 | 379.5144 | 2022-01-01 | 2022-12-31 | 2022-06-03 | 2022-06-03 | CCC-69443 RETIRED ERX EBLANTON
21026156700 | INSTALL 20'-3 PMMP |  |  |  |  | 0.01794% | 13109.07 | 12546.0469 | 563.0231 | 2022-01-01 | 2022-12-31 | 2022-06-03 | 2022-07-25
22026200300 | EMER - INSTALL 5'-2" PMIP |  |  |  |  | 0.01245% | 9101.9 | 2610.0199 | 6491.8801 | 2022-01-01 | 2022-12-31 | 2022-06-07 | 2022-06-07 | REPLACED 5' SECTION OF 2" PMMP. TESTED MAIN AT 90 PSIG FOR 1 HOUR AND TEST WAS GOOD. TESTED 2X1 EF TEES AT 90 PSIG FOR 5 MINS AND SOAP TESTED THE CAPS AND DEAD ENDS AT OP FOR 5 MINS. ALL TEST ARE GOOD.
21026156800 | ABDN CB 12'-3" PMP |  |  |  |  | 0% | 0 | 73.9724 | -73.9724 | 2022-01-01 | 2022-12-31 | 2022-06-07 | 2022-08-01
23026270200 | EMER - RETIRE 5'-2" PIP |  |  |  |  | 0% | 0 | 288.6068 | -288.6068 | 2022-01-01 | 2022-12-31 | 2022-06-07 | 2022-06-07 | REPLACED 5' SECTION OF 2" PMMP. TESTED MAIN AT 90 PSIG FOR 1 HOUR AND TEST WAS GOOD. TESTED 2X1 EF TEES AT 90 PSIG FOR 5 MINS AND SOAP TESTED THE CAPS AND DEAD ENDS AT OP FOR 5 MINS. ALL TEST ARE GOOD.
22026181600 | RELOCATE ~5"-2" PMMP |  |  |  |  | 0.01418% | 10366.16 | 6138.9503 | 4227.2097 | 2022-01-01 | 2022-12-31 | 2022-06-07 | 2022-06-14 | DURING AND AFTER REPLACEMENT PURGE NEW MAIN INTO SERVICE CO M.COLLINS/B.SEXTON RLA 6-7-2022 REPLACED 10' OF 2" P MP MAIN TEST 10' OF 2" PIPE ONSITE 90LBS FOR 1 HR NO LEAKS SOAP TEST TIE IN NO LEAKS BHB NGF SOAP TEST ALL TEE'S CAPS AND DEAD ENDS AT OP AFTER GUAGE REMOVAL NO LEAKS VERIFY DELIVERY PRESSURE BEFORE
22026181700 | RELOCATE ~5"-2" PMMP |  |  |  |  | 0% | 0 | 75.4968 | -75.4968 | 2022-01-01 | 2022-12-31 | 2022-06-07 | 2022-06-14
20026973400 | RETIRE STATION R-1452 |  |  |  |  | 0.0001562% | 114.18 | 1281.7771 | -1167.5971 | 2022-01-01 | 2022-12-31 | 2022-05-26 | 2022-06-08 | CCC# 68859 CCC# 68859 RETIRED REGSTATION PER AMRP PROJECT JMARTIN
22026169000 | MAVITY HVAC UPGRADE |  |  |  |  | 0.007769% | 5678.5 | 15264.0767 | -9585.5767 | 2022-01-01 | 2022-12-31 | 2022-06-08 | 2022-08-05
22026214400 | MAVITY HVAC/RTU |  |  |  |  | 0% | 0 | 55.5311 | -55.5311 | 2022-01-01 | 2022-12-31 | 2022-06-08 | 2022-08-05 | UPGRADED RTU
20026973100 | RETIRE 120'-4" BSMP |  |  |  |  | 0.002596% | 1897.5 | 80.6441 | 1816.8559 | 2022-01-01 | 2022-12-31 | 2022-06-09 | 2022-06-30
20026973200 | RETIRE 10875' BS/CI LP |  |  |  |  | 0.0001952% | 142.7 | 57.6441 | 85.0559 | 2022-01-01 | 2022-12-31 | 2022-06-09 | 2022-06-30
21026121300 | PM- SEWELL REPLACEMENT |  |  |  |  | 3.991% | 2916870.85 | 1087500 | 1829370.85 | 2022-01-01 | 2022-12-31 | 2022-06-02 | 2022-06-09
21026121400 | PM- SEWELL ABANDONMENT |  |  |  |  | 0.947% | 692157.41 | 62500 | 629657.41 | 2022-01-01 | 2022-12-31 | 2022-06-08 | 2022-06-09
19026861100 | INSTALL HEATER |  |  |  |  | 0.003245% | 2372.11 | 3045.0298 | -672.9198 | 2022-01-01 | 2022-12-31 | 2022-06-13 | #N/A | INSTALLED CAT HEATER
22026192300 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.0003856% | 281.87 | 4801.1928 | -4519.3228 | 2022-01-01 | 2022-12-31 | 2022-06-13 | 2022-06-13 | CHANGED ERX TO MIWI 350, P2P OK, CCC 70245 CMHOLAN 6-13-2022
22026192400 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.0006066% | 443.37 | 124.8731 | 318.4969 | 2022-01-01 | 2022-12-31 | 2022-06-13 | 2022-06-13 | REMOVED ERX TO INSTALL MIWI, CCC 70245 CMCHOLAN 6-13-2022 INSTALLED NEW MIWI350
20026977500 | INSTALL 4335'-4" & 6" PMLP |  |  |  |  | 1.388% | 1014309.73 | 818557.1832 | 195752.5468 | 2022-01-01 | 2022-12-31 | 2022-04-12 | 2022-09-06 | TWALKER/KY 01-24-23: PROJECT OVER RUN COST DUE TO ADDITIONAL PAVING/HARD SURFACE REPAIR RESULTED IN $100,000 HIGHER CONTRACT COST, MATERIAL COST WERE $46,000 HIGHER THAN EST. ADN SEGA $68,000 HIGHER THAN EST.
21026101900 | RETIRE 6"MP SERVICE LINE |  |  |  |  | 0.01332% | 9737.82 | 9764.3857 | -26.5657 | 2022-01-01 | 2022-12-31 | 2022-06-13 | 2022-06-14 | INSTALLED BOLTED DEAD END CAP AT END OF NC 216695 VALVE. JOSH PASLEY 6/14/22
22026189300 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.0006665% | 487.15 | 4745.0565 | -4257.9065 | 2022-01-01 | 2022-12-31 | 2022-06-14 | 2022-06-14 | CC# 70358 RETIRED BOTH ERX'S INSTALLED NEW MIWI350 MRYAN 6-14-2022
22026189400 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.0003329% | 243.32 | 124.5156 | 118.8044 | 2022-01-01 | 2022-12-31 | 2022-06-14 | 2022-06-14 | CC # 70358 RETIRED OLD ERX'S INSTALLED NEW MIWI350 MRYAN 6-14-2022
22026189500 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.0003999% | 292.29 | 4745.0565 | -4452.7665 | 2022-01-01 | 2022-12-31 | 2022-06-15 | 2022-06-15 | CC # 70566 RETIRED OLD ERX INSTALLED NEW HONEYWELL MIWI350 MRYAN 6-15-2022
22026189700 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.0001257% | 91.91 | 4745.0565 | -4653.1465 | 2022-01-01 | 2022-12-31 | 2022-06-15 | 2022-06-15 | CC # 70497 RETIRED OLD ERX INSTALLED NEW MIW350 MRYAN 06-15-2022
22026189600 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.0001256% | 91.82 | 124.5156 | -32.6956 | 2022-01-01 | 2022-12-31 | 2022-06-15 | 2022-06-15 | CC # 70566 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 06-15-2022
22026189800 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.0002915% | 213.04 | 124.5156 | 88.5244 | 2022-01-01 | 2022-12-31 | 2022-06-15 | 2022-06-15 | CC # 70497 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-15-2022
22026175600 | RETIRE R-1256 |  |  |  |  | 0.0002892% | 211.37 | 7307.4769 | -7096.1069 | 2022-01-01 | 2022-12-31 | 2022-06-15 | 2022-06-17 | STATION RETIRED AND ALL PIPING REMOVED WSHIMFESSEL 06-07-2022
22026185600 | EXCHANGE ELECTRONIC COMPONENTS |  |  |  |  | 0.0008814% | 644.24 | 6006.2549 | -5362.0149 | 2022-01-01 | 2022-12-31 | 2022-06-20 | 2022-06-20 | CCC# 70942 INSTALL NEW MIWI 350, P2P W/GAS CONTROL OK, JMARTIN 6-20-22
22026185700 | RETIRE ELECTRONIC COMPONENTS |  |  |  |  | 0.0001283% | 93.74 | 124.5156 | -30.7756 | 2022-01-01 | 2022-12-31 | 2022-06-20 | 2022-06-20 | CCC# 70942 RETIRE ERX AND REPLACE WITH MIWI 350, JMARTIN 6-20-22
22026191300 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.001148% | 839.28 | 4801.1928 | -3961.9128 | 2022-01-01 | 2022-12-31 | 2022-06-20 | 2022-06-21 | CCC# 71072
22026191400 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0% | 0 | 124.8731 | -124.8731 | 2022-01-01 | 2022-12-31 | 2022-06-21 | 2022-06-21
21026122000 | INSTALL 2150' OF 2"PMMP MAIN |  |  |  |  | 0.2441% | 178403.1 | 162365.3384 | 16037.7616 | 2022-01-01 | 2022-12-31 | 2022-05-10 | 2022-06-28
22026183600 | INSTALL 1700'-2" PMMP |  |  |  |  | 0.07049% | 51519.58 | 46580.9585 | 4938.6215 | 2022-01-01 | 2022-12-31 | 2022-06-06 | 2022-06-22
22026211400 | PAPER ONLY-RETIRE MP MAIN |  |  |  |  | 0% | 0 | 65.0112 | -65.0112 | 2022-01-01 | 2022-12-31 | 2022-06-23 | 2022-06-23
22026165400 | RETIRE REG STATION #1203 |  |  |  |  | 0.00778% | 5686.24 | 4576.607 | 1109.633 | 2022-01-01 | 2022-12-31 | 2022-06-22 | 2022-06-22 | STATION RETIRED ALL PIPEING REMOVED 06-22-2022 AJPARKS
22026192500 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.000548% | 400.52 | 4801.1928 | -4400.6728 | 2022-01-01 | 2022-12-31 | 2022-06-22 | 2022-06-22 | CCC# 71244
22026192600 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0% | 0 | 124.8731 | -124.8731 | 2022-01-01 | 2022-12-31 | 2022-06-22 | 2022-07-05
22026162000 | RETIRE 110' OF 2"CSHP MAIN |  |  |  |  | 0.0009809% | 716.93 | 105.0102 | 611.9198 | 2022-01-01 | 2022-12-31 | 2022-06-23 | 2022-06-28
22026190600 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.001118% | 817.09 | 4801.1928 | -3984.1028 | 2022-01-01 | 2022-12-31 | 2022-06-23 | 2022-06-23 | CCC 71454 RETIRED ERX AND INSTALLED NEW MIWI350
22026191900 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.001019% | 744.93 | 4801.1928 | -4056.2628 | 2022-01-01 | 2022-12-31 | 2022-06-23 | 2022-06-23 | CCC 71454
22026191000 | RETIRED ELECTRONICS EQUIPMENT |  |  |  |  | 0.0003578% | 261.55 | 124.8731 | 136.6769 | 2022-01-01 | 2022-12-31 | 2022-06-23 | 2022-06-23 | CCC 71454 RETIRE ERX AND INSTALLED NEW MIWI 350
22026192000 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.001262% | 922.45 | 124.8731 | 797.5769 | 2022-01-01 | 2022-12-31 | 2022-06-23 | 2022-06-23 | CCC 71454
22026208700 | EMER - RETIRE 2'-2" PMP |  |  |  |  | 0% | 0 | 63.5475 | -63.5475 | 2022-01-01 | 2022-12-31 | 2022-06-24 | 2022-07-05
22026208600 | EMER - INSTALL 2'-2" PMMP |  |  |  |  | 0.01039% | 7597.73 | 5654.5749 | 1943.1551 | 2022-01-01 | 2022-12-31 | 2022-06-24 | 2022-07-05
22026191100 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.001786% | 1305.26 | 4801.1928 | -3495.9328 | 2022-01-01 | 2022-12-31 | 2022-06-27 | 2022-06-27 | CC # 71822 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-27-2022
22026191200 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.0003141% | 229.57 | 124.8731 | 104.6969 | 2022-01-01 | 2022-12-31 | 2022-06-27 | 2022-06-27 | CC # 71822 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-27-2022
22026209400 | RETIRE CHAIN LINK FENCE |  |  |  |  | 0% | 0 | 65.0112 | -65.0112 | 2022-01-01 | 2022-12-31 | 2022-06-28 | 2022-06-28
22026192700 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.001067% | 780.12 | 4801.1928 | -4021.0728 | 2022-01-01 | 2022-12-31 | 2022-06-28 | 2022-06-28 | CC # 71922 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-28-2022
22026193200 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.000371% | 271.17 | 4801.1928 | -4530.0228 | 2022-01-01 | 2022-12-31 | 2022-06-28 | 2022-06-28 | CC # 71922 RETIRED OLD ERX INSTALLED NEW MIWI 350 MRYAN 6/28/2022
22026192800 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.0001131% | 82.66 | 124.8731 | -42.2131 | 2022-01-01 | 2022-12-31 | 2022-06-28 | 2022-06-28 | CC # 71984 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-28-2022
22026193300 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.0002136% | 156.09 | 124.8731 | 31.2169 | 2022-01-01 | 2022-12-31 | 2022-06-28 | 2022-06-28 | CC # 71922 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6/28/2022
22026188600 | INSTALL 165'-2" PMMP |  |  |  |  | 0.01634% | 11945.7 | 14323.3857 | -2377.6857 | 2022-01-01 | 2022-12-31 | 2022-06-17 | 2022-06-29
22026189100 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.003502% | 2559.49 | 4745.0565 | -2185.5665 | 2022-01-01 | 2022-12-31 | 2022-06-29 | 2022-06-29 | CC # 70264 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-29-2022
22026189200 | RETIRE ELECTRONIC EQUIPMENT |  |  |  |  | 0.0002915% | 213.04 | 124.5156 | 88.5244 | 2022-01-01 | 2022-12-31 | 2022-06-22 | 2022-06-29 | CC # 70264 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-29-2022
22026177900 | INSTALL 8' OF 6"PMMP MAIN |  |  |  |  | 0.05049% | 36900.11 | 29164.4 | 7735.71 | 2022-01-01 | 2022-12-31 | 2022-06-17 | 2022-07-11
22026178000 | RETIRE 4' OF 6"CSMP MAIN |  |  |  |  | 0.001199% | 876.45 | 75.4968 | 800.9532 | 2022-01-01 | 2022-12-31 | 2022-06-17 | 2022-07-11
21026120200 | PM-INS PIG REC/FILTER JIM BEAM |  |  |  |  | 3.479% | 2542524.27 | 2579017 | -36492.73 | 2022-01-01 | 2022-12-31 | 2021-06-13 | 2022-06-30
21026120300 | PM-ABA FOR EQUIP INST JIM BEAM |  |  |  |  | 1.143% | 835157.07 | 62500 | 772657.07 | 2022-01-01 | 2022-12-31 | 2021-06-13 | 2022-06-30
18026764800 | INSTALL COMM BUILDING |  |  |  |  | 0.1807% | 132078.26 | 156664.9991 | -24586.7391 | 2022-01-01 | 2022-12-31 | 2018-06-12 | 2022-06-30 | 72003 INSTALLED RTU BUILDING AND TRANSDUCERS
22026189900 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.0003773% | 275.74 | 4745.0565 | -4469.3165 | 2022-01-01 | 2022-12-31 | 2022-06-30 | 2022-06-30 | CC # 72215 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6/30/2022
22026194400 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.0004878% | 356.51 | 4801.1928 | -4444.6828 | 2022-01-01 | 2022-12-31 | 2022-06-30 | 2022-06-30 | CC # 72268 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-30-2022
22026190000 | RETIRED ELECTRONICS EQUIPMENT |  |  |  |  | 8.418e-05% | 61.53 | 124.5156 | -62.9856 | 2022-01-01 | 2022-12-31 | 2022-06-30 | 2022-06-30 | CC # 72215 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6/30/2022
22026194500 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 2.517e-06% | 1.84 | 124.8731 | -123.0331 | 2022-01-01 | 2022-12-31 | 2022-06-30 | 2022-06-30 | CC # 72268 RETIRED OLD ERX INSTALLED NEW MIWI 350 MRYAN 6-30-2022
22026206900 | EMER-INSTALL 16' OF 4"/6"PMLP |  |  |  |  | 0.01506% | 11009.07 | 8399.775 | 2609.295 | 2022-01-01 | 2022-12-31 | 2022-06-30 | 2022-07-15 | LEAKING POSI HOLD COUPLING.LEAKING OUT OF FITTING ON COUPLING. REPLACED 6'' TEE AND 19FT OF MAIN.TESTED MAIN FOR 1HR AT 90LBS.TEST OK. SOAP TEST FINAL TIE INS AT OP FOR 5MINS AT OP.TEST OK. BHB NGF.
22026207000 | EMER-RETIRE 14' OF 6"BSLP |  |  |  |  | 0.01536% | 11230.19 | 60.0112 | 11170.1788 | 2022-01-01 | 2022-12-31 | 2022-06-30 | 2022-07-15 | LEAKING POSI HOLD COUPLING.LEAKING OUT OF FITTING ON COUPLING. REPLACED 6'' TEE AND 19FT OF MAIN.TESTED MAIN FOR 1HR AT 90LBS.TEST OK. SOAP TEST FINAL TIE INS AT OP FOR 5MINS AT OP.TEST OK. BHB NGF.
22026210100 | EMER - INSTALL 6'-4" PMMP |  |  |  |  | 0.007545% | 5514.88 | 4810.9373 | 703.9427 | 2022-01-01 | 2022-12-31 | 2022-07-05 | 2022-07-26 | DAMAGED SECTION OF PIPE DUE TO EXCAVATOR ERROR.MADE SAFE BY SQUEEZING OFF IN BELLHOLES.OC 16FT NEW MAIN DUE TO EXCAVATION WHERE DAMAGE WAS TOO DEEP. TESTED MAIN 1HR AR 90LB.TEST OK.SOAP TEST EFC'SAT OP.TEST OK BHB NGF
22026210200 | EMER - RETIRE 6'-4" PMMP |  |  |  |  | 0.00013% | 95.05 | 63.5475 | 31.5025 | 2022-01-01 | 2022-12-31 | 2022-07-05 | 2022-07-26 | DAMAGED SECTION OF PIPE DUE TO EXCAVATOR ERROR.MADE SAFE BY SQUEEZING OFF IN BELLHOLES.OC 16FT NEW MAIN DUE TO EXCAVATION WHERE DAMAGE WAS TOO DEEP. TESTED MAIN 1HR AR 90LB.TEST OK.SOAP TEST EFC'SAT OP.TEST OK BHB NGF
22026211000 | EMER - INSTALL 3'-4" PMMP |  |  |  |  | 0.01169% | 8542 | 12351.4608 | -3809.4608 | 2022-01-01 | 2022-12-31 | 2022-07-05 | 2022-07-28 | CUT OUT 3' OF 4" PL MP AND REPLACED WITH NEW 3' OF 4" PL MP TESTED 90 PSIG 1 HOUR
22026211100 | EMER - RETIRE 3'-4" PMMP |  |  |  |  | 0.0006155% | 449.88 | 477.8601 | -27.9801 | 2022-01-01 | 2022-12-31 | 2022-07-05 | 2022-07-28 | RETIRED 3' OF 4" PL MP AND INSTALLED NEW 3' OF 4" PL TESTED 90 PSIG 1 HOUR SOAP TESTD FINAL CONN OP 40 PSIG
22026211200 | EMER-INSTALL 6' OF 4"PMIP MAIN |  |  |  |  | 0.01905% | 13924.65 | 10641.1495 | 3283.5005 | 2022-01-01 | 2022-12-31 | 2022-07-07 | 2022-07-07
22026211300 | EMER-RETIRE 6' OF 4"PAIP MAIN |  |  |  |  | 0% | 0 | 65.0112 | -65.0112 | 2022-01-01 | 2022-12-31 | 2022-07-07 | 2022-07-07
22026208900 | EMER - INSTALL ~10'-8" CSHP |  |  |  |  | 0.08181% | 59795.62 | 32930.2498 | 26865.3702 | 2022-01-01 | 2022-12-31 | 2022-07-07 | 2022-07-07
18026770100 | RETIRE CHART |  |  |  |  | 0% | 0 | 1613.3811 | -1613.3811 | 2022-01-01 | 2022-12-31 | 2022-07-07 | 2022-07-07 | RETIRED PAPER CHART MRYAN 07-07-2022
18026847000 | INSTALL CATALYTIC HEATER |  |  |  |  | 0.005171% | 3779.78 | 3926.2882 | -146.5082 | 2022-01-01 | 2022-12-31 | 2022-07-08 | 2022-07-08 | CC# 49296. 12/21/21 DSASH NO CC# NEEDED, DID NOT GO ON SITE. 12/22/21 DSASH GMB NO CC NEEDED RETIRED OLD CATALYTIC HEATER INSTALLED NEW CATALYTIC HEATER MRAYN 7-8-22
18026847200 | INSTALL CATALYTIC HEATER |  |  |  |  | 0.004255% | 3110.02 | 3926.2882 | -816.2682 | 2022-01-01 | 2022-12-31 | 2022-07-08 | 2022-07-08 | RETIRED OLD CATALYTIC HEATER AND INSTALLED NEW CATALYTIC HEATER MRYAN 7-8-2022
18026847100 | RETIRE CATALYTIC HEATER |  |  |  |  | 0.000583% | 426.13 | 77.1956 | 348.9344 | 2022-01-01 | 2022-12-31 | 2022-07-08 | 2022-07-08 | RETIRED OLD CATALYTIC HEATER INSTALLED NEW CATALYTIC HEATER MRYAN 7-8-2022
18026847300 | RETIRE CATALYTIC HEATER |  |  |  |  | 0.0004289% | 313.52 | 77.1956 | 236.3244 | 2022-01-01 | 2022-12-31 | 2022-07-08 | 2022-07-08 | RETIRED CATALYTIC HEATER INSTALLED NEW CATALYTIC HEATER MRYAN 7-8-2022
22026210600 | EMER-RETIRE 50' OF 3"BSLP MAIN |  |  |  |  | 0.003906% | 2854.75 | 5032.3621 | -2177.6121 | 2022-01-01 | 2022-12-31 | 2022-07-10 | 2022-09-12
22026215700 | EMER-INSTALL 2' OF 2"PMMP MAIN |  |  |  |  | 0.006719% | 4910.67 | 8681.8934 | -3771.2234 | 2022-01-01 | 2022-12-31 | 2022-07-11 | 2022-08-22 | REPLACED 2FT OF 020 DAMAGED MAIN.TESTED NEW MAIN FOR 20MINS AT 90LBS.TEST OK.SOAP TEST EFC'S AT OP FOR 5MINS.TEST OK. BHBNGF
22026211500 | EMER-INSTALL 5'-2" PMMP |  |  |  |  | 0.007739% | 5656.19 | 16105.0112 | -10448.8212 | 2022-01-01 | 2022-12-31 | 2022-07-11 | 2022-09-12
22026215800 | EMER-RETIRE 2' OF 2"PMP MAIN |  |  |  |  | 0.0003078% | 224.99 | 84.9152 | 140.0748 | 2022-01-01 | 2022-12-31 | 2022-07-11 | 2022-08-22 | REPLACED 2FT OF 020 DAMAGED MAIN.TESTED NEW MAIN FOR 20MINS AT 90LBS.TEST OK.SOAP TEST EFC'S AT OP FOR 5MINS.TEST OK. BHBNGF
22026211600 | EMER-RETIRE 5'-2" PMMP |  |  |  |  | 0.005315% | 3884.45 | 4031.2726 | -146.8226 | 2022-01-01 | 2022-12-31 | 2022-07-11 | 2022-09-12
22026184600 | INSTALL 64' OF 2"PMMP MAIN |  |  |  |  | 0.02295% | 16772.5 | 17899.1411 | -1126.6411 | 2022-01-01 | 2022-12-31 | 2022-06-27 | 2022-07-11
22026184700 | RETIRE 52' OF 2"PMMP MAIN |  |  |  |  | 0% | 0 | 74.2578 | -74.2578 | 2022-01-01 | 2022-12-31 | 2022-06-27 | 2022-07-11
20026929500 | UPGRADE ELECTRONICS |  |  |  |  | 0.007759% | 5670.86 | 3038 | 2632.86 | 2022-01-01 | 2022-12-31 | 2022-07-11 | 2022-07-11 | RETIRED OLD MINNI-AT INSTALLED NEW EC350 BLONE 07-11-2022
20026935200 | RETIRE ELECTRONICS |  |  |  |  | 0.001016% | 742.7 | 73.3494 | 669.3506 | 2022-01-01 | 2022-12-31 | 2022-07-11 | 2022-07-11 | RETIRED OLD MINI-AT INSTALLED NEW EC350 BLONE 07-11-2022
23026252900 | PM-GREENSITE RAILROAD CROSSING |  |  |  |  | 0.02448% | 17890.94 | 1236355 | -1218464.06 | 2022-01-01 | 2022-12-31 | 2022-04-10 | 2022-07-12
23026253000 | PM-GREENSITE RAILROAD ABANDON |  |  |  |  | 0.0004489% | 328.14 | 0 | 328.14 | 2022-01-01 | 2022-12-31 | 2022-04-10 | 2022-07-12
22026191500 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.001994% | 1457.43 | 4801.1928 | -3343.7628 | 2022-01-01 | 2022-12-31 | 2022-07-12 | 2022-08-16 | UPGRADED ERX TO MIWI
22026191600 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.0006122% | 447.49 | 124.8731 | 322.6169 | 2022-01-01 | 2022-12-31 | 2022-07-12 | 2022-08-16 | CC # 73221 UPGRADDED ERX TO MIWI
22026180500 | INSTALL 160'-2" PMIP |  |  |  |  | 0.03109% | 22724.8 | 36664.9938 | -13940.1938 | 2022-01-01 | 2022-12-31 | 2022-07-08 | 2022-07-13
22026215900 | EMER-INSTALL 3' OF 2"PMMP MAIN |  |  |  |  | 0.002537% | 1854.5 | 3722.1191 | -1867.6191 | 2022-01-01 | 2022-12-31 | 2022-07-13 | 2022-08-22 | REPLACED 3FT SECTION OF MAIN. TESTED NEW SECTION OF MAIN FOR 20MINS AT 90LBS.TEST OK SOAP TEST EFC'S AT OP FOR 5MINS.TEST OK. BHBNGF
22026216000 | EMER-RETIRE 3' OF 2"PAMP MAIN |  |  |  |  | 0.0001959% | 143.19 | 84.9152 | 58.2748 | 2022-01-01 | 2022-12-31 | 2022-07-13 | 2022-08-22 | REPLACED 3FT SECTION OF MAIN. TESTED NEW SECTION OF MAIN FOR 20MINS AT 90LBS.TEST OK SOAP TEST EFC'S AT OP FOR 5MINS.TEST OK. BHBNGF
22026194200 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.002447% | 1788.47 | 4801.1928 | -3012.7228 | 2022-01-01 | 2022-12-31 | 2022-07-13 | 2022-08-08 | CC # 73334
22026194300 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.0006444% | 470.99 | 124.8731 | 346.1169 | 2022-01-01 | 2022-12-31 | 2022-07-13 | 2022-08-08 | CC # 73334 UPDATTED ERX TO MIWI 07-13-22 J. MULLINS
22026202200 | INSTALL 125' OF 2" PMMP MAIN |  |  |  |  | 0.01568% | 11459.71 | 8841.6395 | 2618.0705 | 2022-01-01 | 2022-12-31 | 2022-07-14 | 2022-07-14
20026928200 | UPGRADE ELECTRONICS |  |  |  |  | 0.004735% | 3460.63 | 3038 | 422.63 | 2022-01-01 | 2022-12-31 | 2022-07-14 | 2022-07-14 | CMCHOLAN 7-14-2022 RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07-14-2022
20026928400 | UPGRADE FROM 3G NETWORK |  |  |  |  | 0.004347% | 3177.17 | 3038 | 139.17 | 2022-01-01 | 2022-12-31 | 2022-07-14 | 2022-07-14 | RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07-14-2022
20026928600 | UPGRADE ELECTRONICS |  |  |  |  | 0.004321% | 3158.07 | 5626 | -2467.93 | 2022-01-01 | 2022-12-31 | 2022-07-14 | 2022-07-14 | RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON
20026933900 | RETIRE ELECTRONICS |  |  |  |  | 0.001422% | 1039.15 | 73.3494 | 965.8006 | 2022-01-01 | 2022-12-31 | 2022-07-08 | 2022-07-14 | CMCHOLAN 7-14-2022 RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07142022
20026934100 | RETIRE ELECTRONICS |  |  |  |  | 0.000259% | 189.27 | 73.3494 | 115.9206 | 2022-01-01 | 2022-12-31 | 2022-07-14 | 2022-07-14 | RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07-14-2022
22026210000 | RETIRE ELECTRONICS |  |  |  |  | 0.0003409% | 249.16 | 65.0112 | 184.1488 | 2022-01-01 | 2022-12-31 | 2022-07-14 | 2022-07-14 | RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07-14-2022
22026193800 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.002159% | 1577.79 | 4801.1928 | -3223.4028 | 2022-01-01 | 2022-12-31 | 2022-07-14 | 2022-08-08 | CC # 73511
22026194000 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.002289% | 1673.13 | 4801.1928 | -3128.0628 | 2022-01-01 | 2022-12-31 | 2022-07-14 | 2022-08-08 | CC # 73511 UPGRADED FROM ERX TO MIWI JOSH MULLINS
22026193900 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.0003222% | 235.52 | 124.8731 | 110.6469 | 2022-01-01 | 2022-12-31 | 2022-07-14 | 2022-08-08 | CC # 73511 UPGRADED TO MIWI JOSH MULLINS
22026194100 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.0003154% | 230.5 | 124.8731 | 105.6269 | 2022-01-01 | 2022-12-31 | 2022-07-14 | 2022-08-08 | CC # 73511
21026118100 | INSTALL 5680'-2"/4" PMMP |  |  |  |  | 0.2136% | 156088.03 | 165876.9601 | -9788.9301 | 2022-01-01 | 2022-12-31 | 2022-05-10 | 2022-07-20
20026928500 | UPGRADE ELECTRONICS |  |  |  |  | 0.005017% | 3667.3 | 3038 | 629.3 | 2022-01-01 | 2022-12-31 | 2022-07-19 | 2022-07-19 | CWEMPE BLONE 7/19/22 RETIRED MINI-AT INSTALLED NEW EC350 CWEMPE 07-19-2022
20026934200 | RETIRE ELECTRONICS |  |  |  |  | 0.000688% | 502.89 | 73.3494 | 429.5406 | 2022-01-01 | 2022-12-31 | 2022-07-19 | 2022-07-19 | CWEMPE BLONE 7/19/22 RETIRED OLD MINI-AT INSTALLED NEW EC350
22026190800 | INSTALL 50'-4" PMLP |  |  |  |  | 0.06628% | 48441.53 | 45570.6341 | 2870.8959 | 2022-01-01 | 2022-12-31 | 2022-07-14 | 2022-07-21
22026190900 | RETIRE 41'-4" BSLP |  |  |  |  | 0.0001568% | 114.59 | 78.4365 | 36.1535 | 2022-01-01 | 2022-12-31 | 2022-07-20 | 2022-07-21
21026145800 | REPLACE VALVES ON HP-MP REG |  |  |  |  | 0.04591% | 33552.7 | 14136.4861 | 19416.2139 | 2022-01-01 | 2022-12-31 | 2022-07-12 | 2022-07-20 | CCC# 73837 CCC# 74028 CCC# 74317 REPLACED INLET, OUTLET, AND BOTH BYPASS VLVS ON STATION. JMARTIN 7/20/22
21026145900 | RETIRE 4 VALVES ON REG STATION |  |  |  |  | 0.001855% | 1355.49 | 600.4497 | 755.0403 | 2022-01-01 | 2022-12-31 | 2022-07-08 | 2022-07-20 | INSTALLED TEMPORARY REG SETTING REPLACED ALL FOUR SETTING VALVES JMARTIN 07 -20-2022
22026183800 | INSTALL 100'-2" PMIP |  |  |  |  | 0.02322% | 16969.45 | 18017.5748 | -1048.1248 | 2022-01-01 | 2022-12-31 | 2022-07-21 | 2022-07-21
22026215300 | EMER - INSTALL 20'-2" PMIP |  |  |  |  | 0.02075% | 15168.73 | 10433.2304 | 4735.4996 | 2022-01-01 | 2022-12-31 | 2022-07-20 | 2022-07-21
22026215500 | EMER - INSTALL 5'-2" PMMP |  |  |  |  | 0.009268% | 6774.27 | 4479.378 | 2294.892 | 2022-01-01 | 2022-12-31 | 2022-07-21 | 2022-07-21
22026215400 | EMER - RETIRE 5'-2" PMIP |  |  |  |  | 0% | 0 | 80.5311 | -80.5311 | 2022-01-01 | 2022-12-31 | 2022-07-20 | 2022-07-21
22026215600 | EMER - RETIRE 5'-2" PMMP |  |  |  |  | 0% | 0 | 84.9152 | -84.9152 | 2022-01-01 | 2022-12-31 | 2022-07-21 | 2022-07-21
21026156900 | INSTALL 10'-6" PMLP |  |  |  |  | 0.009551% | 6980.82 | 14786.2791 | -7805.4591 | 2022-01-01 | 2022-12-31 | 2022-07-21 | 2022-07-21 | INSTALLATION COMPLETE, HMCKUNE
22026191700 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.01451% | 10605.54 | 4801.1928 | 5804.3472 | 2022-01-01 | 2022-12-31 | 2022-07-25 | 2022-08-12 | UPGRADED ERX TO MIWI JOSH MULLINS
22026191800 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 2.742e-05% | 20.04 | 124.8731 | -104.8331 | 2022-01-01 | 2022-12-31 | 2022-07-25 | 2022-08-12
22026232000 | RETIRE PAPER GAUGE |  |  |  |  | 0% | 0 | 993 | -993 | 2022-01-01 | 2022-12-31 | 2022-07-26 | 2022-07-26 | RETIRED PAPER CHART 7-26-22 CCOX
22026192100 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.00317% | 2317.01 | 4801.1928 | -2484.1828 | 2022-01-01 | 2022-12-31 | 2022-07-26 | 2022-08-15 | CCC 75023
22026192200 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.00121% | 884.51 | 124.8731 | 759.6369 | 2022-01-01 | 2022-12-31 | 2022-07-26 | 2022-08-15 | CCC 75023 UPGRADED ERX TO MIWI J.MULLINS
22026214800 | EMER INSTALL 2' - PMMP |  |  |  |  | 0.01119% | 8176.85 | 2418.3858 | 5758.4642 | 2022-01-01 | 2022-12-31 | 2022-07-27 | 2022-07-27
22026214900 | EMER RETIRE 2'-PMP |  |  |  |  | 0% | 0 | 84.9152 | -84.9152 | 2022-01-01 | 2022-12-31 | 2022-07-27 | 2022-07-27
22026193400 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.002653% | 1938.82 | 4801.1928 | -2862.3728 | 2022-01-01 | 2022-12-31 | 2022-07-27 | 2022-08-17 | CC # 75237 NO CC NOT ONSITE PAPERWORK NO CC NEEDED UPGRADDED ERX TO MIWI JMULLINS
22026196000 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.008316% | 6078.6 | 4801.1928 | 1277.4072 | 2022-01-01 | 2022-12-31 | 2022-07-27 | 2022-07-27 | CC # 75237 RETIRED OLD ERX AND INSTALLED NEW HONEYWELL MIWI350 MRYAN 7-27-2022
22026193500 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 3.021e-05% | 22.08 | 124.8731 | -102.7931 | 2022-01-01 | 2022-12-31 | 2022-07-27 | 2022-08-17 | CC # 75237
22026196100 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.0003181% | 232.52 | 124.8731 | 107.6469 | 2022-01-01 | 2022-12-31 | 2022-07-27 | 2022-07-27 | CC # 75237 RETIRED OLD ERX INSTALLED NEW HONEY WELL MIWI350 MATT RYAN 7-27-2022
21026114200 | INSTALL 100'-2" PMMP |  |  |  |  | 0.02641% | 19306.24 | 12690.4563 | 6615.7837 | 2022-01-01 | 2022-12-31 | 2022-07-14 | 2022-07-28
22026215000 | EMER INSTALL 2'-4" PMLP |  |  |  |  | 0.01286% | 9400.14 | 3659.4376 | 5740.7024 | 2022-01-01 | 2022-12-31 | 2022-07-28 | 2022-07-28
22026215100 | EMER RETIRE 2'-4" PLP |  |  |  |  | 0% | 0 | 84.9152 | -84.9152 | 2022-01-01 | 2022-12-31 | 2022-07-28 | 2022-07-28
22026218200 | RETIRE PAPER GUAGE |  |  |  |  | 0% | 0 | 339.1994 | -339.1994 | 2022-01-01 | 2022-12-31 | 2022-07-28 | 2022-07-28 | RETIRE PAPER CHART DUE TO ERX INSTALL AT ANOTHER STATION SMCHOLAN
22026218300 | RETIRE PAPER GAUGE |  |  |  |  | 0% | 0 | 339.1994 | -339.1994 | 2022-01-01 | 2022-12-31 | 2022-07-28 | 2022-07-28 | RETIRED PAPER CHART DUE TO ERX INSTALL AT ANOTHER LOCATION
20026941400 | INSTALL I&C EQUIPMENT |  |  |  |  | 0.01645% | 12022.54 | 16155.4774 | -4132.9374 | 2022-01-01 | 2022-12-31 | 2020-06-08 | 2022-07-28 | INSTALLED TAP ON OUTLET LEG OF RUN 1 20# SYSTEM AND RAN SENSE LINES TO ERX FROM THE NEW TAP AND EXISTING HP SENSE LINE, AND COMMISSIONED ERX CCC 75328, CMCHOLAN CCOX 7-28-2022
22026213800 | EMER - RETIRE 150'-2" P-IP |  |  |  |  | 0.005659% | 4136.05 | 4412.2636 | -276.2136 | 2022-01-01 | 2022-12-31 | 2022-08-01 | 2022-09-06 | ABANDONED 150' OF 2" PLASTIC. SOAP TESTED ABANDONMENT AT OP. PRESS. 15MIN.
20026976501 | INSTALL 4270' OF 2"/4"PMMP MN |  |  |  |  | 2.651% | 1937333.59 | 1522347.7868 | 414985.8032 | 2022-01-01 | 2022-12-31 | 2022-02-21 | 2022-08-05 | WIPE SAMPLE RESULTS WERE ENTERED ON THE INSTALL JOB IN ERROR. WIPE RESULTS FOR THE RETIREMENT PIPE WERE ENTERED HERE. TWALKER/KY 01-24-23: JOB OVER RUN DUE TO ADDITIONAL STREET/HARD SURFACE REP AIRS REQUIRED BY CITY OF LEXINGTON. CONTRACT COST INCREASED BY $200,000 WITH PAVING/FLAGGING COST, SEGA WAS $73,000 HIGHER THAN PLANNED, ADDITIONAL $22,000 CHARGED FOR MATERIAL COST. TWALKER/KY 08-29-23: LEVEL 2 VARIANCE ADDED TO WMS.DOCS. JOB COST OVERRUN DUE TO ADDITIONAL STREET MILL/RE-PAVED COST REQUIRED BY CITY OF LEXINGTON.
20026976600 | RETIRE 4650' OF 3"/4"BSLP MN |  |  |  |  | 0.0004378% | 320 | 56.8875 | 263.1125 | 2022-01-01 | 2022-12-31 | 2022-02-21 | 2022-08-05
22026184500 | INSTALL 250'-4" PMLP/CSLP |  |  |  |  | 0.08753% | 63976.36 | 60316.4006 | 3659.9594 | 2022-01-01 | 2022-12-31 | 2022-07-13 | 2022-08-10
22026218400 | RETIRE 2'-4" BSLP |  |  |  |  | 0% | 0 | 84.9152 | -84.9152 | 2022-01-01 | 2022-12-31 | 2022-08-15 | 2022-08-15
22026216500 | EMER-INSTALL 2"/4" POLY VALVES |  |  |  |  | 0.593% | 433396.83 | 298130.9642 | 135265.8658 | 2022-01-01 | 2022-12-31 | 2022-02-01 | 2022-08-11 | COMPLETED OVERRUN EXPLANATION FORM LOADED INTO WMSDOCS JO WORKSPACE. D.LEMO NS 2/24/2023
22026222800 | EMER-INSTALL 2' OF 4"PMMP MAIN |  |  |  |  | 0.03008% | 21988.24 | 23837.8998 | -1849.6598 | 2022-01-01 | 2022-12-31 | 2022-08-11 | 2022-09-12
22026222900 | EMER-RETIRE 2' OF 4"PMMP MAIN |  |  |  |  | 0% | 0 | 89.0305 | -89.0305 | 2022-01-01 | 2022-12-31 | 2022-08-11 | 2022-09-12
22026216600 | EMER-RETIRE 7'-2"/4" PMIP/CSIP |  |  |  |  | 0% | 0 | 83.4538 | -83.4538 | 2022-01-01 | 2022-12-31 | 2022-08-11 | 2022-08-11
22026198200 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.00757% | 5532.75 | 4801.1928 | 731.5572 | 2022-01-01 | 2022-12-31 | 2022-08-11 | 2022-08-11 | CC 76915 UPGRADDED ERX TO MIWI 350
22026198300 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.0006393% | 467.24 | 124.8731 | 342.3669 | 2022-01-01 | 2022-12-31 | 2022-08-11 | 2022-08-11 | CC 76915 UPDATTED ERX TO MIWI 350
22026217500 | EMER-INSTALL 2' OF 3"PMMP MAIN |  |  |  |  | 0.008727% | 6378.4 | 5764.1191 | 614.2809 | 2022-01-01 | 2022-12-31 | 2022-08-11 | 2022-08-12
22026217600 | EMER-RETIRE 2' OF 3"PAMP MAIN |  |  |  |  | 0.005685% | 4155.42 | 1084.9152 | 3070.5048 | 2022-01-01 | 2022-12-31 | 2022-08-11 | 2022-08-12
21026126800 | INSTALL 11,170' OF 2"/6"PMMP |  |  |  |  | 2.289% | 1672773.41 | 1492284.9718 | 180488.4383 | 2022-01-01 | 2022-12-31 | 2022-01-03 | 2022-10-10
22026200600 | INSTALL 15' OF 3"/4"PMLP S/L |  |  |  |  | 0.0143% | 10449.59 | 11118.4162 | -668.8262 | 2022-01-01 | 2022-12-31 | 2022-06-17 | 2022-08-15
22026200500 | RETIRE 2' OF 3"PLP S/L |  |  |  |  | 0% | 0 | 62.4365 | -62.4365 | 2022-01-01 | 2022-12-31 | 2022-06-17 | 2022-09-12
21026131900 | INSTALL 3843' OF 2"/4"PMMP MN |  |  |  |  | 2.009% | 1468486.46 | 807937.3693 | 660549.0907 | 2022-01-01 | 2022-12-31 | 2022-03-03 | 2022-10-06 | PROJECT COST OVERRUN DUE TO ADDITIONAL TIME AND RESOURCES NEEDED. CONTRACT COSTS AND LABOR COSTS INCREASED DUE TO UNEXPECTED ROCK ENCOUNTERED DURING C ONSTRUCTION FOR BORE/OPEN CUT OF NEW MAIN. ADDITIONAL TIE-IN LOCATIONS WERE REQUIRED FOR INSTALL AND ABANDONMENT. INCREASED FLAGGING AND INCREASED RES TORATION COSTS ALSO CONTRIBUTED TO THE OVERRUN, AS WELL AS INCREASED SEGA C OSTS. MOLIVER 1/24/23
21026152700 | EMER - INSTALL ODORIZER |  |  |  |  | 0.2332% | 170463.75 | 303602.2828 | -133138.5328 | 2022-01-01 | 2022-12-31 | 2022-08-16 | 2022-08-16 | UNDERRUN EXPLANATION: PROJECT DID NOT REQUIRE AS MUCH CONTINGENCY, OR OUTSIDE LABOR COSTS FROM CONTRACTORS TTOY 3/2/23
21026152800 | EMER - RETIRE ODORIZER |  |  |  |  | 0.08552% | 62508.06 | 61.5191 | 62446.5409 | 2022-01-01 | 2022-12-31 | 2022-08-16 | 2022-08-16
22026245700 | INSTALL BUILDING R-1667 |  |  |  |  | 0.0008911% | 651.28 | 300.4844 | 350.7956 | 2022-01-01 | 2022-12-31 | 2023-01-16 | 2022-12-28
22026245800 | RETIRE MIS FACILITIES R-1639 |  |  |  |  | 0% | 0 | 131.2422 | -131.2422 | 2022-01-01 | 2022-12-31 | 2023-01-16 | 2022-12-28
22026217800 | EMER-INSTALL 3' OF 4"PMLP MAIN |  |  |  |  | 0.01683% | 12300.82 | 6173.2589 | 6127.5611 | 2022-01-01 | 2022-12-31 | 2022-06-17 | 2022-08-18 | LEAK CLEARED USING DPI D311930 PW
22026217900 | EMER-RETIRE 3' OF 4"BSLP MAIN |  |  |  |  | 0.006086% | 4448.33 | 170.8304 | 4277.4996 | 2022-01-01 | 2022-12-31 | 2022-06-17 | 2022-08-18
22026207500 | INSTALL NEW CONTROL REGULATOR |  |  |  |  | 0.001223% | 893.82 | 1471.7874 | -577.9674 | 2022-01-01 | 2022-12-31 | 2022-08-18 | 2022-08-18 | CCC#77790 INSTALLED NEW 461-57S CONTROL REGULATOR CWEMPE 8-18-22
22026207600 | REPLACE CONTROL REG |  |  |  |  | 0.0006676% | 487.94 | 65.0112 | 422.9288 | 2022-01-01 | 2022-12-31 | 2022-08-18 | 2022-08-18 | CCC#77790 REMOVED CONTROL REGULATOR CWEMPE 8-18-22
18026762800 | INSTALL NEW CHAIN LINK FENCE |  |  |  |  | 0.02304% | 16843.44 | 17042.1322 | -198.6922 | 2022-01-01 | 2022-12-31 | 2022-08-15 | 2022-08-18 | MONITORED NEW CHAINLINK FENCE INSTALL AMCCORMICK 8-18-22
18026762900 | REPLACE CHAIN LINK FENCE |  |  |  |  | 0.0005883% | 429.99 | 73.5943 | 356.3957 | 2022-01-01 | 2022-12-31 | 2022-08-15 | 2022-08-18 | MONITORED FENCE REMOVAL AND INSTALL AMCCORMICK 8-18-22
21026146701 | INSTALL 100'-2" PMIP |  |  |  |  | 0.008479% | 6197.36 | 40630.8922 | -34433.5322 | 2022-01-01 | 2022-12-31 | 2021-11-09 | 2022-08-30 | VAPIERCE (03/27/23); JOB OVER RUN DUE TO CONTRACT CHARGES ASSOCIATED TO EMERGENCY JOB ORDER 22-0262152-00 EMER-KY FLOODING 2022. $29,900 IN ESTIMATED CONTRACT COSTS AND $0 BOOKED TO THIS JOB ORDER, ALL CONTRACT COSTS WERE CHARGED TO EMER-KY FLOODING 2000 JO. MOST LABOR COSTS WERE ALSO BOOKED UNDER THE EMER JOB ORDER. CONSTRUCTION WAS UNAWARE THIS PLANNED PROJECT OVERLAPPED WITH EMER WORK.
22026178500 | INSTALL 44'-6" PMMP |  |  |  |  | 0.08921% | 65200.97 | 72684.0107 | -7483.0407 | 2022-01-01 | 2022-12-31 | 2022-06-06 | 2022-08-23
22026178600 | RETIRE 26'-6" CSMP |  |  |  |  | 0.002544% | 1859.72 | 73.9724 | 1785.7476 | 2022-01-01 | 2022-12-31 | 2022-06-06 | 2022-08-23
21026155700 | INSTALL FENCE - SCADA BUILDING |  |  |  |  | 0.01034% | 7557.57 | 15936.4497 | -8378.8797 | 2022-01-01 | 2022-12-31 | 2022-08-15 | 2022-08-22
21026112400 | INSTALL NEW GMB SETTING |  |  |  |  | 0.07536% | 55082.19 | 57016.3076 | -1934.1176 | 2022-01-01 | 2022-12-31 | 2022-03-02 | 2022-08-22 | INSTALLED NEW GMB SKID MOUNTED METER AND REGULATOR SETTING AJPARKS 8-22-202 2 PSID 501306155
20026960600 | INSTALL NEW TRANSMITTERS |  |  |  |  | 0.01321% | 9652.42 | 5450.0793 | 4202.3407 | 2022-01-01 | 2022-12-31 | 2020-07-21 | 2022-08-22 | INSTALLED NEW INLET AND OUTLET ROSEMONT 4088B TRANSMITTERS GHALE 8-22-2022
22026195400 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.0009332% | 682.09 | 4801.1928 | -4119.1028 | 2022-01-01 | 2022-12-31 | 2022-08-22 | 2022-08-22 | CCC# 78156 PAPERWORK ONLY - NO CCC NEEDED - BLONE - 11/8/22 INSTALLED NEW MIWI350 B LONE 8-22-2022
20026960700 | RETIRE DAMAGE TRANSMITTER |  |  |  |  | 0.0007426% | 542.77 | 80.9227 | 461.8473 | 2022-01-01 | 2022-12-31 | 2022-08-22 | 2022-08-22 | INSTALLED NEW INLET AND OUTLET TRANSMITTERS GHALE 8-22-2022
22026195500 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.0009259% | 676.72 | 124.8731 | 551.8469 | 2022-01-01 | 2022-12-31 | 2022-08-22 | 2022-08-22 | CCC# 78156 RETIRED OLD ERX INSTALLED NEW MIWI350 BLONE 8-22-22
21026119600 | PM- TURNER STATION REPLACEMENT |  |  |  |  | 4.531% | 3311444.82 | 1012500 | 2298944.82 | 2022-01-01 | 2022-12-31 | 2022-10-01 | 2022-08-23
21026119700 | PM- TURNER STATION ABANDONMENT |  |  |  |  | 0.5185% | 378972.89 | 62500 | 316472.89 | 2022-01-01 | 2022-12-31 | 2022-10-01 | 2022-08-23
22026231800 | RETIRE PAPER CHART |  |  |  |  | 0% | 0 | 1093 | -1093 | 2022-01-01 | 2022-12-31 | 2022-08-23 | 2022-08-23 | RETIRED PAPER CHART CCOX 8-23-22
20026926400 | INSTALL NETWORK UPGRADE |  |  |  |  | 0.009757% | 7131.29 | 3150 | 3981.29 | 2022-01-01 | 2022-12-31 | 2022-08-23 | 2022-09-09 | GMB NO CC NEEDED GMB NO CC NEEDED NO CC NEEDED--GMB NO CC NEEDED GMB INSTALLED SOAR,BATTERY,AND MODEM PAPERWORK DONE BY J.MULLINS
22026195600 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.007397% | 5406.36 | 4801.1928 | 605.1672 | 2022-01-01 | 2022-12-31 | 2022-08-22 | 2022-09-01 | CCC# 78341 - BLONE - 08/23/22 UPGRADED ERX TO MIME CO BY J.MULLINS
22026195700 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.0005223% | 381.79 | 124.8731 | 256.9169 | 2022-01-01 | 2022-12-31 | 2022-08-23 | 2022-09-01 | CCC# 78341 B. LONE UPDATTED ERX TO MIWI CO BY J. MULLINS
22026184000 | INSTALL 200'-6"/8" PMLP |  |  |  |  | 0.2879% | 210431.38 | 169438.8752 | 40992.5048 | 2022-01-01 | 2022-12-31 | 2022-07-11 | 2022-08-30 | OVERRUN EXPLANATION: PROJECT WAS PLANNED FOR 360 HOURS OF LABOR TIME BUT ENDED UP WITH 565 HOURS DUE TO MULTIPLE COORDINATORS AND WELDER CHARGING 125 HOURS, SEGA WAS ORIGINALLY $20,641 BUT ENDED UP AT $34,463, PROJECT REQUIRED 698 TONS OF STONE AND DUST BUT WAS ORIGINALLY PLANNED FOR 60 TONS, ADDITIONAL EXTRA DEPTH UNITS OF 134, PROJECT ALSO CHAR CHARGED ~$6,000 OF SEWER CAMERA EVEN THOUGH THE SEWER WAS ALREADY UNCOVERED WHICH IS WHY WE WERE INSTALLING THE RELOCATION. TTOY 2/3/23
22026184100 | RETIRE 100'-BSLP |  |  |  |  | 0.0005473% | 400 | 65.0112 | 334.9888 | 2022-01-01 | 2022-12-31 | 2022-08-24 | 2022-08-30
22026200700 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.007625% | 5573.15 | 4801.1928 | 771.9572 | 2022-01-01 | 2022-12-31 | 2022-08-24 | 2022-08-24 | CCC# 68204 - BLONE - 08/24/22 CCC#68204 TIME CHARGED FOR COMPLETING PAPERWORK. CWEMPE 8/30/22 RETIRED ERX INSTALLED NEW MIWI350 CWEMPE 8-24-2022
22026200800 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.0003902% | 285.19 | 124.8731 | 160.3169 | 2022-01-01 | 2022-12-31 | 2022-08-24 | 2022-08-24 | CCC# 68204 - BLONE - 08/24/22 CCC#68204 RETIRED OLD ERX INSTALLED NEW MIWI350 CWEMPE 8-24-2022
21026127200 | INSTALL 2200'-2"&4" PMMP |  |  |  |  | 0.781% | 570820.34 | 433097.159 | 137723.181 | 2022-01-01 | 2022-12-31 | 2022-02-11 | 2022-10-31 | COST OVERRUN DUE TO PAVING ESTIMATED IN CONTRACT, BUT CAPTURED IN MISC MATE RIALS WITH A DIFFERENCE OF $32,000. SOME ADDITIOANL MATERIALS WERE REQUIRE D THAT WERE NOT ESTIMATED FOR $6,000. SEGA ALSO INCREASED FOR ADDITIONAL $1 8,000. D.LEMONS 1/31/2023 ADDITIONAL $56,000 TRANSFERED FROM RETIREMENT JO THAT WAS ASSOCIATED WITH A DDITIONAL PAVING. D. LEMONS 2/23/2023
22026194800 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.008061% | 5891.93 | 4801.1928 | 1090.7372 | 2022-01-01 | 2022-12-31 | 2022-08-25 | 2022-08-25 | CCC# 78666 INSTALLED NEW MIWI350 JPASLEY 8-25-22
22026194900 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0% | 0 | 124.8731 | -124.8731 | 2022-01-01 | 2022-12-31 | 2022-08-25 | 2022-08-25 | RETIRED ERX INSTALLED NEW MIWI350 JPASLEY 8-25-22
22026175400 | RETIRE R-1258 |  |  |  |  | 0.0001561% | 114.11 | 7307.4769 | -7193.3669 | 2022-01-01 | 2022-12-31 | 2022-08-18 | 2022-08-26 | CCC# 77893 STATIONRETIRED PER AMRP PROJECT WSHIMFESSEL 8-26-2022 ALL FACILITIES REMOVE D
22026175500 | RETIRE R-1275 |  |  |  |  | 0.000887% | 648.29 | 7307.4769 | -6659.1869 | 2022-01-01 | 2022-12-31 | 2022-08-18 | 2022-08-26 | CCC# 77909 RETIRED REG STATION R-1275 ON AMRP PROJECT WSHIMFESSEL 8-26-2022 PREMISE IS RETIRED. GATHERED INFORMATION FOR CAPITOL CLOSEOUT.
22026196900 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.007104% | 5192.52 | 4801.1928 | 391.3272 | 2022-01-01 | 2022-12-31 | 2022-08-26 | 2022-08-26 | INSTALLED NEW MIWI350 JPASLEY 8-26-22
22026197000 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.000956% | 698.72 | 124.8731 | 573.8469 | 2022-01-01 | 2022-12-31 | 2022-08-26 | 2022-08-26 | RETIRED OLD ERX JPASLEY 8-26-22
22026222300 | EMER - INSTALL 7'-4" PMLP |  |  |  |  | 0.01898% | 13873.55 | 4005.634 | 9867.916 | 2022-01-01 | 2022-12-31 | 2022-08-29 | 2022-09-14
22026222400 | EMER - RETIRE 7'-4" PLP |  |  |  |  | 0% | 0 | 89.0305 | -89.0305 | 2022-01-01 | 2022-12-31 | 2022-08-29 | 2022-09-14
21026151200 | INSTALL 2065'-2"&6" PMMP |  |  |  |  | 0.6752% | 493527.08 | 333722.7132 | 159804.3668 | 2022-01-01 | 2022-12-31 | 2022-02-09 | 2022-10-17
22026220400 | ABANDON 550' OF 2"PMP MAIN |  |  |  |  | 0.0002527% | 184.67 | 3449.8998 | -3265.2298 | 2022-01-01 | 2022-12-31 | 2022-08-29 | 2022-08-29 | ABANDONED 020 MP PL ML. PREFORMED PER ABANDONMENT PLAN SOAP TEST DEAD END C AP OP 15 MINUTES. C HERNDON/S.BARKER PURGED ABANDONED SECTION OF LINE. CAPPED THE ENDS OF ABANDONED ML.
20026926600 | INSTALL NETWORK UPGRADE |  |  |  |  | 0.008975% | 6560.17 | 3150 | 3410.17 | 2022-01-01 | 2022-12-31 | 2022-08-29 | 2022-08-29 | NO CC NEEDED GMB INSTALLED NEW SUPER SOLAR KIT MRYAN 8-29-22
22026195000 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.007672% | 5607.88 | 4801.1928 | 806.6872 | 2022-01-01 | 2022-12-31 | 2022-08-29 | 2022-08-29 | SWAP COMP. PARKS 08-29-22 1545 CCC# 78985 RETIRED OLD ERX INSTALLED NEW MIWI350 AJPARKS 8-29-2022
22026195100 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.0003406% | 248.95 | 124.8731 | 124.0769 | 2022-01-01 | 2022-12-31 | 2022-08-29 | 2022-08-29 | REMOVAL COMP. APARKS 08-29-22 1044 CCC# 78985 RETIRED OLD ERX INSTALLED NEW MIWI350 AJPARKS 8-29-2022
22026180100 | INSTALL 805' OF 2"/4"PMMP MAIN |  |  |  |  | 0.1597% | 116760.6 | 54482.6036 | 62277.9964 | 2022-01-01 | 2022-12-31 | 2022-07-21 | 2022-09-07 | TWALKER/KY 09-08-22: PROJECT OVER RUN DUE TO ROCK ENCOUNTERED IN CONSTRUCTI ON REQUIRING ROCK BORE AND OPEN CUT ROCK WHICH INCREATED CONTRACT COST BY $30,000. WMS WOULD NOT ALLOW REVISION OF PROJECT DUE TO UNPAID INVOICES. COMPANY LABOR INCREASED BY OVER $16,000 DUE TO EXTRA TIME FOR CONSTRUCTION AND SEGA WAS $6000 THAN ESTIMATE TWALKER/KY 01-24-23: LEVEL 2 VARIANCE REPORT ADDED TO WMS.DOCS.
21026138900 | INSTALL 650'-6" PMMP |  |  |  |  | 0.1529% | 111751.03 | 35779.3166 | 75971.7134 | 2022-01-01 | 2022-12-31 | 2022-07-21 | 2022-09-01 | COST INCREASE FOR LABOR HOURS AND CONTRACT COSTS DUE TO INCREASED DIRECTION AL BORE FOOTAGE, GPS DATA COLLECTION, INCREASED RESTORATION COSTS, ADDITION AL TIE-IN LOCATIONS NEEDED, AND INCREASE IN SEGA COSTS. - MOLIVER
22026202900 | RETIRE 135' OF 2"PMP MAIN |  |  |  |  | 3.133e-06% | 2.29 | 78.4365 | -76.1465 | 2022-01-01 | 2022-12-31 | 2022-08-31 | 2022-09-07
21026147300 | INSTALL 400'-4" PMMP-SER |  |  |  |  | 0.04504% | 32919.84 | 22333.8994 | 10585.9406 | 2022-01-01 | 2022-12-31 | 2022-08-08 | #N/A | COMMIT DATE MISSED DUE TO WEATHER
22026195800 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.007635% | 5580.46 | 4801.1928 | 779.2672 | 2022-01-01 | 2022-12-31 | 2022-08-30 | 2022-08-30 | CCC# 79192 INSTALL NEW MIWI 350, P2P COMP. JMARTIN 8-30-22
22026195900 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 9.472e-05% | 69.23 | 124.8731 | -55.6431 | 2022-01-01 | 2022-12-31 | 2022-08-30 | 2022-08-30 | CCC# 79192 INSTALL NEW MIWI 350, P2P COMP. JMARTIN 8-30-22 RETIRED OLD ERX
22026221200 | EMER - INSTALL 8'-6"PMMP |  |  |  |  | 0.01606% | 11736.48 | 32929.6819 | -21193.2019 | 2022-01-01 | 2022-12-31 | 2022-08-31 | 2022-09-12 | TEST 6 IN MAIN AT 90 LB FOR 20 MIN SOAP TEST EFC AT OP FOR 5 MIN
22026219700 | EMER-INSTALL 8" STOPPLE FITS |  |  |  |  | 0.05336% | 39002.9 | 30183.131 | 8819.769 | 2022-01-01 | 2022-12-31 | 2022-08-29 | 2022-09-01
22026221300 | EMER - RETIRE 8'-6" PMP |  |  |  |  | 0.0008144% | 595.27 | 87.3224 | 507.9476 | 2022-01-01 | 2022-12-31 | 2022-08-31 | 2022-09-12 | REMOVED 2 FT OF 6 IN DAMAGE PIPE
22026219800 | EMER-RETIRE 1' OF 8"CSHP MAIN |  |  |  |  | 0.0002189% | 160 | 84.9152 | 75.0848 | 2022-01-01 | 2022-12-31 | 2022-08-31 | 2022-09-01
22026196700 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.007353% | 5374.37 | 4801.1928 | 573.1772 | 2022-01-01 | 2022-12-31 | 2022-08-31 | 2022-08-31 | CCC# 79339 INSTALLED NEW MIWI350. P2P W/GC OK 08/31/2022 WSHIMFE
22026196800 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0% | 0 | 124.8731 | -124.8731 | 2022-01-01 | 2022-12-31 | 2022-08-31 | 2022-08-31 | RETIRED OLD ERX INSTALLED NEW MIWI350 WSHIMFESSEL 8-31-2022
20026977600 | RETIRE 4766'-2"/3"/4"/6" BSLP |  |  |  |  | 0.01512% | 11052.89 | 476.2758 | 10576.6142 | 2022-01-01 | 2022-12-31 | 2022-09-01 | 2022-09-06
22026199300 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.007209% | 5269.21 | 4801.1928 | 468.0172 | 2022-01-01 | 2022-12-31 | 2022-09-01 | 2022-09-01 | CCC# 79486 RETIRED ERX INSTALLED NEW MIWI350 GHALE 9-1-2022
22026199400 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.0002323% | 169.77 | 124.8731 | 44.8969 | 2022-01-01 | 2022-12-31 | 2022-09-01 | 2022-09-01 | CCC# 79486 RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 9-1-2022
22026222500 | EMER - INSTALL 5'-6" PMMP |  |  |  |  | 0.007762% | 5673.45 | 5662.1316 | 11.3184 | 2022-01-01 | 2022-12-31 | 2022-09-22 | 2022-09-23
22026222600 | EMER - RETIRE 5'-6" PMMP |  |  |  |  | 0% | 0 | 74.3089 | -74.3089 | 2022-01-01 | 2022-12-31 | 2022-09-23 | 2022-09-23
22026199100 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.007665% | 5602.7 | 4801.1928 | 801.5072 | 2022-01-01 | 2022-12-31 | 2022-09-02 | 2022-09-02 | CCC 79615 RETIRED OLD ERX INSTALLED NEW MIWI350 EBLANTON 9-2-2022
22026199200 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.001205% | 880.44 | 124.8731 | 755.5669 | 2022-01-01 | 2022-12-31 | 2022-09-02 | 2022-09-02 | CCC 79615 RETIRED OLD ERX INSTALLED NEW MIWI350 EBLANTON 9-2-2022
22026221900 | EMER - RETIRE 20'-3" PMP |  |  |  |  | 0.00956% | 6987.81 | 3460.1765 | 3527.6335 | 2022-01-01 | 2022-12-31 | 2022-09-07 | 2022-10-04
20026980401 | INSTALL 13,025'-PMMP/CSHP |  |  |  |  | 3.091% | 2258910.28 | 1836238.4697 | 422671.8103 | 2022-01-01 | 2022-12-31 | 2022-09-06 | 2022-09-29 | OVERRUN EXPLANATION: PROJECT INCLUDED ADDITIONAL PAVING THAT WAS UNFORSEEN DUE TO CITY REQUIREMENTS, SEGA HAD AN INCREASE OF OVER $100,000 TTOY 3/2/2023
22026198900 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.007473% | 5462.44 | 4801.1928 | 661.2472 | 2022-01-01 | 2022-12-31 | 2022-09-06 | 2022-09-06 | CCC#79730 CWEMPE 9/6/22 UPGRADED ERX TO MIWI PAPERWORK DONE BY J.MULLINS
22026199000 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.0003458% | 252.74 | 124.8731 | 127.8669 | 2022-01-01 | 2022-12-31 | 2022-09-06 | 2022-09-06 | CCC#79730 CWEMPE 9/6/22
22026218500 | INSTALL 35'-2"/4 PMLP |  |  |  |  | 0.01178% | 8610.21 | 16435.9913 | -7825.7813 | 2022-01-01 | 2022-12-31 | 2022-09-07 | 2022-10-27 | INSTALLED 2' OF 4" PL AND 37' OF 2" PL LP TESTED 90 PSIG 1 HR
18026843301 | INSTALL 3000' OF 4/6/8"PMLP |  |  |  |  | 2.341% | 1711065.31 | 1495308.5734 | 215756.7366 | 2022-01-01 | 2022-12-31 | 2022-07-19 | 2022-09-09
18026843400 | RETIRE 2670' OF 3"/6"CILP MAIN |  |  |  |  | 0.0008185% | 598.25 | 81.035 | 517.215 | 2022-01-01 | 2022-12-31 | 2022-05-25 | 2022-09-12
21026998900 | RETIRE 3"PLP SERVICE LINE |  |  |  |  | 0.01243% | 9085.7 | 9329.0565 | -243.3565 | 2022-01-01 | 2022-12-31 | 2022-09-06 | 2022-09-20
22026197100 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.007352% | 5373.93 | 4801.1928 | 572.7372 | 2022-01-01 | 2022-12-31 | 2022-09-07 | 2022-09-07 | CCC 79940 RETIRED OLD ERX INSTALLED NEW MIWI350 9-7-2022
22026197200 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.0003435% | 251.1 | 124.8731 | 126.2269 | 2022-01-01 | 2022-12-31 | 2022-09-07 | 2022-09-07 | CCC 79940 RETIRED OLD ERX INSTALLED NEW MIWI350 EBLANTON 9-7-2022
22026217300 | RETIRE 3"PLP SERVICE LINE |  |  |  |  | 0% | 0 | 170.8304 | -170.8304 | 2022-01-01 | 2022-12-31 | 2022-09-08 | 2022-09-08
21026137900 | INSTALL OUTLET VLV R-1643 |  |  |  |  | 0.1097% | 80161.67 | 110321.1916 | -30159.5216 | 2022-01-01 | 2022-12-31 | 2022-08-31 | 2022-09-08 | CCC# 80227 MONITOR WHILE BACKFILLING INSTALLED ALL NEW STATION VALVES JPASLEY 9-8-22 UNDERRUN EXPLANATION: PROJECT INCLUDED $27,000 OF CONTINGENCY AND HAD AN UNDERRUN OF 30,492 TTOY 3/2/23
21026138000 | RETIRE OUTLET VLV R-1643 |  |  |  |  | 0% | 0 | 955.7874 | -955.7874 | 2022-01-01 | 2022-12-31 | 2022-09-08 | 2022-09-08 | RETIRED ALL STATION VALVES AND INSTALLED NEW VALVES JPASLEY 9-8-22
22026199500 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.007332% | 5358.86 | 4801.1928 | 557.6672 | 2022-01-01 | 2022-12-31 | 2022-09-08 | 2022-09-08 | CCC# 80149 P2P OK RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 9-8-2022
22026201100 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.00758% | 5540.17 | 4801.1928 | 738.9772 | 2022-01-01 | 2022-12-31 | 2022-09-08 | 2022-09-08 | CCC# 80069 P2P OK RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 9-8-2022
22026199600 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.0006964% | 509.01 | 124.8731 | 384.1369 | 2022-01-01 | 2022-12-31 | 2022-09-08 | 2022-09-08 | CCC# 80149 RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 09-08-2022
22026201200 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.0002154% | 157.47 | 124.8731 | 32.5969 | 2022-01-01 | 2022-12-31 | 2022-09-08 | #N/A | CCC# 80069 RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 9-8-2022
22026216200 | INSTALL 950' OF 2"/4"PMMP MAIN |  |  |  |  | 0.06482% | 47379.78 | 39269.0655 | 8110.7145 | 2022-01-01 | 2022-12-31 | 2022-08-24 | #N/A
22026198700 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.00861% | 6293.17 | 4801.1928 | 1491.9772 | 2022-01-01 | 2022-12-31 | 2022-09-13 | 2022-09-13 | CC 497 CC 497 REPLACED OLD ERX WITH NEW MIWI350 SGIORDANO 9-13-2022
22026198800 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.001388% | 1014.14 | 124.8731 | 889.2669 | 2022-01-01 | 2022-12-31 | 2022-09-13 | #N/A | CC 497 REPLACED ERX WITH NEW MIWI350 SGIORDANO 9-13-2022
20026980700 | RETIRE MAIN - LEAKAGE |  |  |  |  | 0.003483% | 2546.03 | 103.8156 | 2442.2144 | 2022-01-01 | 2022-12-31 | 2021-07-14 | #N/A
20026992600 | RETIRE MP MAIN |  |  |  |  | 0% | 0 | 103.8156 | -103.8156 | 2022-01-01 | 2022-12-31 | 2022-09-26 | #N/A
22026179200 | INSTALL 50' OF 6"PMLP S/L |  |  |  |  | 0.06279% | 45896.9 | 47001.2003 | -1104.3003 | 2022-01-01 | 2022-12-31 | 2022-09-08 | #N/A
22026200900 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.008397% | 6137.4 | 4801.1928 | 1336.2072 | 2022-01-01 | 2022-12-31 | 2022-09-14 | #N/A | CC 632 UPGRADED TO MIWI 350 PAPERWORK DONE BY J.MULLINS
22026201000 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.0006643% | 485.58 | 124.8731 | 360.7069 | 2022-01-01 | 2022-12-31 | 2022-09-14 | #N/A | CC 632 UPGRADED TO MIWI 350 PAPERWORK DONE BY J.MULLINS
22026181900 | LAB EQUIPMENT INSTALL |  |  |  |  | 0.007269% | 5312.84 | 15945.3111 | -10632.4711 | 2022-01-01 | 2022-12-31 | 2022-09-15 | #N/A
22026199900 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.008861% | 6476.38 | 4801.1928 | 1675.1872 | 2022-01-01 | 2022-12-31 | 2022-09-15 | #N/A | CC 118 INSTALLED NEW MIWI350 RETIRED OLD ERX SGIORDANO 9-15-22
22026200200 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.001917% | 1400.9 | 124.8731 | 1276.0269 | 2022-01-01 | 2022-12-31 | 2022-09-15 | #N/A | CC 118 INSTALLED NEW MIWI350 SGIORDANO 9-15-22 C 2820
21026993401 | INSTALL 10750'-2"/4"PMMP MAIN |  |  |  |  | 2.835% | 2072101.63 | 1880428.7756 | 191672.8544 | 2022-01-01 | 2022-12-31 | 2022-09-26 | #N/A
20026930900 | UPGRADE ELECTRONICS |  |  |  |  | 0.004555% | 3329.3 | 3038 | 291.3 | 2022-01-01 | 2022-12-31 | 2022-09-19 | #N/A | RETIRED MINI AT INSTALLED NEW EC350 ON CELL MODEM DASH 9-19-22
22026206400 | RETIRE ELECTRONIC |  |  |  |  | 0.00319% | 2331.95 | 65.0112 | 2266.9388 | 2022-01-01 | 2022-12-31 | 2022-09-19 | #N/A | RETIRED OLD MINIAT INSTALLED NEW EC350 DASH 9-19-2022
22026177500 | EMER - INSTALL 800'-6" CSHP |  |  |  |  | 1.41% | 1030814.44 | 663631.3961 | 367183.0439 | 2022-01-01 | 2022-12-31 | 2022-08-18 | #N/A | LEVEL 2 VARIANCE EXPLANATION IN WMSDOCS TTOY 2/3/23
20026980500 | RETIRE 12,520' - LP MAIN |  |  |  |  | 0.001108% | 809.88 | 52.2976 | 757.5824 | 2022-01-01 | 2022-12-31 | 2022-05-05 | #N/A
21026140700 | RETIRE 2,200' - CSMP |  |  |  |  | 0% | 0 | 61.2976 | -61.2976 | 2022-01-01 | 2022-12-31 | 2022-09-27 | #N/A
22026177600 | EMER-RETIRE 800'-4" CSHP |  |  |  |  | 0.001863% | 1361.76 | 84.9152 | 1276.8448 | 2022-01-01 | 2022-12-31 | 2022-08-18 | #N/A
22026199700 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.007731% | 5650.33 | 4801.1928 | 849.1372 | 2022-01-01 | 2022-12-31 | 2022-09-20 | #N/A | RETIRED OLD ERX INSTALLED NEW MIWI350 EBLANTON 9-20-22
22026199800 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.000811% | 592.76 | 124.8731 | 467.8869 | 2022-01-01 | 2022-12-31 | 2022-09-20 | 2022-09-20 | RETIRED OLD RX INSTALLED NEW MIWI350 EBLANTON 9-20-22
22026228000 | EMER-INSTALL 3' OF 2"PMMP MAIN |  |  |  |  | 0.002781% | 2032.93 | 4027.0582 | -1994.1282 | 2022-01-01 | 2022-12-31 | 2022-09-21 | #N/A | INSTALLED 3 FT OF 2 IN MAIN ON DAMAGE TEST FROM POINT A TO B 90 LB FOR 20 MIN TEST PURG TEE 90 LB FOR 5 MIN SOAP TEST 1 IN END CAP AT OP FOR 5 MIN SOAP TEST 2 EFC AT OP FOR 5 MIN BHB NO GAS FOUND
22026228100 | EMER-RETIRE 3' OF 2"PMMP MAIN |  |  |  |  | 0.0008077% | 590.32 | 74.3089 | 516.0111 | 2022-01-01 | 2022-12-31 | 2022-09-21 | 2022-10-04
22026198400 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.007577% | 5538.33 | 4801.1928 | 737.1372 | 2022-01-01 | 2022-12-31 | 2022-09-21 | 2022-09-21 | ASSIST WITH RUNNING STAINLESS 09-21-2022 RHAYES CCOX RETIRED OLD ERX INSTALL NEW MIWI350 CCOX 9-21-22
22026198500 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.0006158% | 450.09 | 124.8731 | 325.2169 | 2022-01-01 | 2022-12-31 | 2022-09-21 | #N/A
21026127400 | INSTALL 1900'-2"&4" PMIP |  |  |  |  | 0.6557% | 479284.77 | 236888.6644 | 242396.1056 | 2022-01-01 | 2022-12-31 | 2022-06-21 | #N/A | OVERRUN EXPLANATION LOADED INTO WMSDOCS. D.LEMONS 2/1/2023
21026127500 | RETIRE 1071'-3"&4" WIIP |  |  |  |  | 0% | 0 | 75.9523 | -75.9523 | 2022-01-01 | 2022-12-31 | 2022-06-21 | #N/A
21026120000 | PM-PARIS CYNTHIANA REPLACEMENT |  |  |  |  | 1.966% | 1437073.2 | 1087500 | 349573.2 | 2022-01-01 | 2022-12-31 | 2022-01-03 | #N/A
21026120100 | PM-PARIS CYNTHIANA ABANDONMENT |  |  |  |  | 0.4459% | 325920.13 | 62500 | 263420.13 | 2022-01-01 | 2022-12-31 | 2022-01-03 | 2022-09-22
22026173700 | 2022 SCADA VISIBILITY PROGRAM |  |  |  |  | 0.03884% | 28387.14 | 29658.8599 | -1271.7199 | 2022-01-01 | 2022-12-31 | 2022-05-13 | #N/A | CCC# 66803 CCC# 66803 MONITOR FOR NEW COMM INSTALL CCC# 80236 INSTALLED NEW MIWI350 EBLANTON 9-22-2022
23026247100 | EMER - INSTALL 9'-4" CSMP/PMP |  |  |  |  | 0.007283% | 5323.15 | 14951.5544 | -9628.4044 | 2022-01-01 | 2022-12-31 | 2022-09-26 | 2023-01-31 | LOWERED MAIN DUE TO LEAKAGE AND 14" WATER LINE TESTED 90 PSIG 0005 MIN SOAP TESTED FINAL CONN OP 40 PSIG
23026247200 | EMER - RETIRE 9'-4" CSMP |  |  |  |  | 0.001103% | 806.29 | 149.6969 | 656.5931 | 2022-01-01 | 2022-12-31 | 2022-09-26 | #N/A | RETIRED 9' OF 4" ST TO LOWER FOR 14" WATER MAIN SOAP TESTED OP TO VERIFY AD EQUATE SHUT DOWN 40 PSIG
23026253100 | PM- GREENSITE TRABU INSTALL |  |  |  |  | 0.04206% | 30739.67 | 1236355 | -1205615.33 | 2022-01-01 | 2022-12-31 | 2022-01-03 | 2022-09-26
23026253200 | PM- GREENSITE TRABU ABANDON |  |  |  |  | 0.0002362% | 172.67 | 0 | 172.67 | 2022-01-01 | 2022-12-31 | 2022-01-03 | 2022-09-26
18026772300 | CONVERT FROM GMB TO CAB ACCT |  |  |  |  | 0.0009926% | 725.53 | 2583.054 | -1857.524 | 2022-01-01 | 2022-12-31 | 2022-09-26 | #N/A | CONVERTED GMB TO CAB ACCOUNT INSTALLED NEW 800 METER ON 5# FPCC DASH 9-26-2 2
22026182000 | INSTALL 2185' OF 2" PMMP |  |  |  |  | 0.1941% | 141899.3 | 110360.5276 | 31538.7724 | 2022-01-01 | 2022-12-31 | 2022-09-12 | #N/A | AWEBER 01/24/2023 - PROJECT OVERRUN DUE PRIMARILY TO LAND OWNER ISSUES & EXPANSIVE SEWER LINE CAMERA WORK PERFORMED BY BUCHANON. EASEMENT FROM FIRST LAND OWNER FELL THROUGH DUE TO HOA VOTE, INCREASING INSTALLATION BY +200' & PRIVATE EASEMENT. PROJECT ENCOUNTERED ROCK BORE ADDING ~34 HOURS TO DURATIO N. OVERRUN BUCHANON COST $17K + LAND COST $11K & INCREASED SEGA RATE $6K LE D TO VARIANCE.
21026132000 | RETIRE 3700' OF 4"/6"BSLP MAIN |  |  |  |  | 0.004678% | 3419.35 | 52.2976 | 3367.0524 | 2022-01-01 | 2022-12-31 | 2022-09-27 | #N/A
23026253700 | PM-GREENSITE HWY 27 INSTALL |  |  |  |  | 0.02836% | 20730.94 | 1236355 | -1215624.06 | 2022-01-01 | 2022-12-31 | 2022-01-03 | 2022-09-27
23026253800 | PM-GREENSITE HWY 27 ABANDON |  |  |  |  | 0% | 0 | 0 | 0 | 2022-01-01 | 2022-12-31 | 2022-01-03 | #N/A
22026234100 | NEW RTU/COMM BUILDING |  |  |  |  | 0% | 0 | 136.2135 | -136.2135 | 2022-01-01 | 2022-12-31 | 2022-09-27 | 2022-09-27
22026204000 | RETIRE PAPER GAUGE |  |  |  |  | 0.0002162% | 157.99 | 78.4365 | 79.5535 | 2022-01-01 | 2022-12-31 | 2022-09-27 | 2022-09-27 | RETIRED PAPER CHART CHRIS COX 9-27-22
22026174600 | 2022 SCADA VISIBILITY PROGRAM |  |  |  |  | 0.05271% | 38527.05 | 29658.8599 | 8868.1901 | 2022-01-01 | 2022-12-31 | 2022-05-11 | 2022-09-27 | CC# 66475 CC#1503 INSTALLED NEW MIWI350 WITH SUPER SOLAR KIT 9-27-22 CCOX
20026918201 | INSTALL ELECTRONICS |  |  |  |  | 0.2726% | 199238.05 | 114999.9064 | 84238.1436 | 2022-01-01 | 2022-12-31 | 2021-03-25 | 2022-09-27 | CCC#17216 CCC# 19029 STATION RTU UP GRADE JPASLEY 9-27-22
21026104700 | REMOVE OBSOLETE ELECTRONICS |  |  |  |  | 0.0003233% | 236.27 | 135.8546 | 100.4154 | 2022-01-01 | 2022-12-31 | 2022-09-27 | 2022-09-27 | INSTALLED NEW RTU BUILDING AND TRANSMITTERS JPASLEY 9-27-2022
22026227600 | EMER - INSTALL 60'-4" PMLP |  |  |  |  | 0.02931% | 21421.89 | 30615.0582 | -9193.1682 | 2022-01-01 | 2022-12-31 | 2022-09-27 | 2022-09-28
22026227700 | EMER - RETIRE 60'-4" BSLP |  |  |  |  | 0.01111% | 8123.84 | 74.3089 | 8049.5311 | 2022-01-01 | 2022-12-31 | 2022-09-27 | 2022-09-28
21026999000 | RETIRE 4"PLP SERVICE LINE |  |  |  |  | 0.006425% | 4696.25 | 5007.8601 | -311.6101 | 2022-01-01 | 2022-12-31 | 2022-09-28 | 2022-09-28
22026173600 | 2022 SCADA VISIBILITY PROGRAM |  |  |  |  | 0.03457% | 25271.05 | 31941 | -6669.95 | 2022-01-01 | 2022-12-31 | 2022-09-28 | 2022-09-28 | INSTALLED NEW MIWI350 EBLANTON 9-28-2022
22026234500 | INSTALL NEW RTU/COMM BUILDING |  |  |  |  | 0% | 0 | 136.2135 | -136.2135 | 2022-01-01 | 2022-12-31 | 2022-09-29 | 2022-09-29 | JMULLINS COMPLETING PAPERWORK
22026173800 | 2022 SCADA VISIBILITY PROGRAM |  |  |  |  | 0.03417% | 24972.3 | 30164.6195 | -5192.3195 | 2022-01-01 | 2022-12-31 | 2022-05-10 | 2022-09-29 | WITH ACP CONTRACTOR WHILE THEY INSTALL POLE FOR COMM EQUIPMENT CC 66318 05-10-2022 RHAYES CC 1924 INSTALLED MIWI350 UNABLE TO PERFORM P2P NDAVIS WORKING ON TICKET MONITORED 30 MINUTES RHAYES 09-29-2022
18026766400 | I&C - INSTALL SCADA EQUIPMENT |  |  |  |  | 0.1968% | 143824.82 | 183526.0448 | -39701.2248 | 2022-01-01 | 2022-12-31 | 2022-09-29 | 2022-09-29 | JMULLINS COMPLETE PAPERWORK TWALKER/KY 01-24-23: JOB UNDER RUN DUE TO MATERIAL COST WAS $33,000 LESS THAN PLANNED, NO SEGA CHARGED TO JOB ORDER PROJECT WAS PLANNED FOR $23,000
22026228700 | RETIRE ELECTRONIC |  |  |  |  | 0% | 0 | 74.3089 | -74.3089 | 2022-01-01 | 2022-12-31 | 2022-09-29 | 2022-09-29
19026850400 | INSTALL ODORIZATION |  |  |  |  | 0.007172% | 5241.78 | 6839.1611 | -1597.3811 | 2022-01-01 | 2022-12-31 | 2022-09-30 | #N/A
19026875300 | INSTALL ODORIZER |  |  |  |  | 0.01267% | 9263.2 | 1300.1611 | 7963.0389 | 2022-01-01 | 2022-12-31 | 2022-09-30 | 2022-09-30 | INSTALLED ODORIZER BOTTLE JMULLINS 9-30-22
19026875400 | INSTALL ODORIZER |  |  |  |  | 0.0018% | 1315.89 | 1300.1611 | 15.7289 | 2022-01-01 | 2022-12-31 | 2022-09-30 | 2022-09-30 | INSTALLED FARM TAP ODORIZER BOTTLE JMULLINS 9-30-22
22026205600 | INSTALL 1200'-2" PMMP |  |  |  |  | 0.223% | 162971.11 | 61578.4138 | 101392.6962 | 2022-01-01 | 2022-12-31 | 2022-08-31 | 2022-10-04 | LEVEL 2 BUDGET VARIANCE EXPLANATION FORM WAS SUBMITTED FOR APPROVAL IN WMSDOCS PER VAPIERCE 5/25/23
22026204200 | RETIRED GAUGE |  |  |  |  | 0% | 0 | 76.9137 | -76.9137 | 2022-01-01 | 2022-12-31 | 2022-10-04 | 2022-10-04 | RETIRED PAPER CHARTS SMCHOLAN 10-04-2022
21026139300 | RETIRE STATION R-1455 |  |  |  |  | 0% | 0 | 1061.1136 | -1061.1136 | 2022-01-01 | 2022-12-31 | 2022-10-04 | 2022-10-04 | RETIRED REG STATION R1455 W 2ND ST MAYSVILLE JMARTIN 10-4-22
22026173000 | 2022 SCADA VISABILITY PROGRAM |  |  |  |  | 0.06471% | 47294.28 | 30164.6195 | 17129.6605 | 2022-01-01 | 2022-12-31 | 2022-05-12 | 2022-10-04 | CC# 66617 INSTALLED NEW MIWI350 SMCHOLAN 10-4-2022
22026205200 | INSTALL 115'-2" PMMP |  |  |  |  | 0.02911% | 21273.79 | 42423.5179 | -21149.7279 | 2022-01-01 | 2022-12-31 | 2022-10-03 | 2022-10-06 | CJ HUGHES CASEY PACK'S CREW INSTALLED 103' 2" STEEL/PLASTIC MAIN LINE EXTEN TION AND A NEW 1" PLASTIC SERVICE TO 1519 MAPLE ST 10/6/22 MBLANKE U123965
22026185001 | INSTALL 260' OF 2"PMMP MAIN |  |  |  |  | 0.04171% | 30483.21 | 27065.0582 | 3418.1518 | 2022-01-01 | 2022-12-31 | 2022-10-05 | 2022-10-07
22026203900 | RETIRE PAPER GAUGE |  |  |  |  | 0% | 0 | 78.4365 | -78.4365 | 2022-01-01 | 2022-12-31 | 2022-10-05 | 2022-10-05 | RETIRED PAPER CHART CCOX10-05-2022
22026174500 | 2022 SCADA VISIBILITY PROGRAM |  |  |  |  | 0.03972% | 29029.69 | 29658.8599 | -629.1699 | 2022-01-01 | 2022-12-31 | 2022-05-11 | 2022-10-05 | CC# 66436 CC# 79698 CC# 2587 CMCOX 10/5/22 INSTALLED NEW MIWI350 CCOX 10-05-2022
22026230100 | EMER-INSTALL 2' OF 2"PMMP |  |  |  |  | 0.003078% | 2249.75 | 3890.5291 | -1640.7791 | 2022-01-01 | 2022-12-31 | 2022-10-06 | 2022-10-06
22026231000 | EMER - INSTALL 1'-2" PMMP |  |  |  |  | 0.009393% | 6865.44 | 8585.1316 | -1719.6916 | 2022-01-01 | 2022-12-31 | 2022-10-06 | 2022-12-04
22026206200 | INSTALL 33'-2" PMIP |  |  |  |  | 0.05078% | 37112.14 | 82983.2827 | -45871.1427 | 2022-01-01 | 2022-12-31 | 2022-09-23 | 2022-10-25 | COST UNDERRUN DUE TO PROJECT BEING SIMPLIFIED AFTER START OF CONSTRUCTION. $2000 IN MATERIALS RETURNED AND NOT USED, $26000 IN CONTRACT ESTIMATED BUT NOT USED. ADDITIONAL SAVINGS IN OTHER AND SEGA CATAGORIA ASSOCIATED WITH LO WER COSTS. D. LEMONS 2/23/2023
22026230200 | EMER-RETIRE 2' OF 2"PMP MAIN |  |  |  |  | 0% | 0 | 74.3089 | -74.3089 | 2022-01-01 | 2022-12-31 | 2022-10-06 | 2022-10-06
22026231100 | EMER - RETIRE 1'-2" PMP |  |  |  |  | 0% | 0 | 60.3089 | -60.3089 | 2022-01-01 | 2022-12-31 | 2022-10-06 | 2022-12-04
22026230800 | EMER - RETIRE 3'-2" P-IP |  |  |  |  | 0.001916% | 1400.06 | 1985.3283 | -585.2683 | 2022-01-01 | 2022-12-31 | 2022-12-07 | 2022-12-15 | CONTRACTOR HIT MISS MARKED MAIN CUT OUT DAMAGED SECTION AND EF PURGE POINT ON END OF MAIN LINE SOAP TESTED OP 7 PSIG
21026127300 | RETIRE 2100'-2"&4" BSMP |  |  |  |  | 0% | 0 | 75.9523 | -75.9523 | 2022-01-01 | 2022-12-31 | 2022-10-04 | 2022-10-06
21026127600 | RETIRE 4700'-4" BSLP |  |  |  |  | 0% | 0 | 67.1085 | -67.1085 | 2022-01-01 | 2022-12-31 | 2022-10-06 | 2022-10-31
22026206300 | RETIRE 22'-4" WIIP |  |  |  |  | 0.00445% | 3252.3 | 83.4538 | 3168.8462 | 2022-01-01 | 2022-12-31 | 2022-09-30 | 2022-10-06
21026119400 | PM- INST FIL/SEP TOYOTA STA |  |  |  |  | 2.836% | 2073205.75 | 1687500 | 385705.75 | 2022-01-01 | 2022-12-31 | 2022-08-19 | 2022-10-06
21026119500 | PM-ABAN FOR FILTER INST TOYOTA |  |  |  |  | 0.7153% | 522788.31 | 62500 | 460288.31 | 2022-01-01 | 2022-12-31 | 2022-10-05 | 2022-10-06
22026217400 | RETIRE 6"PLP SERVICE LINE |  |  |  |  | 0.001132% | 827.26 | 144.8304 | 682.4296 | 2022-01-01 | 2022-12-31 | 2022-09-27 | 2022-10-06
22026218800 | INSTALL MI WIRELESS UNIT |  |  |  |  | 0.01404% | 10259.75 | 9310.2589 | 949.4911 | 2022-01-01 | 2022-12-31 | 2022-09-06 | 2022-10-06 | CC# 79803 CC# 2675 CC# 2675 CMCOX 10/6/22 INSTALLED NEW MIWI350 CCOX 10-06-2022
22026213400 | INSTALL NEW 1" REGULATORS |  |  |  |  | 0.003057% | 2234.49 | 1461.8601 | 772.6299 | 2022-01-01 | 2022-12-31 | 2022-10-07 | 2022-10-07 | REPLACED BOTH MONITOR AND CONTROL REGULATORS AND INLET AND OUTLET VALVES BL ONE 10-7-22
22026213500 | RETIRE REGULATORS |  |  |  |  | 0.001171% | 856.14 | 84.9152 | 771.2248 | 2022-01-01 | 2022-12-31 | 2022-09-29 | 2022-10-07 | REPLACED BOTH MONITOR AND CONTROL REGULATORS AND INLET AND OUTLET VALVES BL ONE 10-7-22
20026930000 | UPGRADE ELECTRONICS |  |  |  |  | 0.006146% | 4491.87 | 3038 | 1453.87 | 2022-01-01 | 2022-12-31 | 2022-07-13 | 2022-10-07 | INSTALLED NED EC350 JPASLEY 10-7-22
20026937200 | RETIRE ELECTRONICS |  |  |  |  | 0% | 0 | 73.3494 | -73.3494 | 2022-01-01 | 2022-12-31 | 2022-10-07 | 2022-10-07 | RETIRE OLD MIN-AT INSTALLED NED EC350 JPASLEY 10-7-22
22026235800 | EMER - INSTALL 3'-4" PMMP |  |  |  |  | 0.0097% | 7089.71 | 18999.7951 | -11910.0851 | 2022-01-01 | 2022-12-31 | 2022-10-10 | 2022-12-15 | FOUND CLAMPS ON 4" PL MAIN CUT OUT AND INSTALLED NEW MAIN TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 15 PSIG
21026126900 | RETIRE 9000' OF 4"/6"BSLP MAIN |  |  |  |  | 3.414e-05% | 24.95 | 62.0792 | -37.1292 | 2022-01-01 | 2022-12-31 | 2022-10-10 | 2022-10-10
22026235900 | EMER - RETIRE 3'-4" P-MP |  |  |  |  | 0.03099% | 22647.66 | 117.5985 | 22530.0615 | 2022-01-01 | 2022-12-31 | 2022-10-10 | 2022-12-15 | RETIRED 4" PL MAIN WITH CLAMPS ON IT TO INSTALL NEW
22026183700 | INSTALL 100' OF 2"PMMP MAIN |  |  |  |  | 0.02711% | 19814.52 | 12739.3747 | 7075.1453 | 2022-01-01 | 2022-12-31 | 2022-09-22 | 2022-10-11 | INSTALLED 199' OF 020 MAIN. TEST 199' OF MAIN FOR 1HR AT 90LBS. FOL APPROVED.SOAP TEST 2'' EFC AT OP OF FINAL TIE IN. SOAP TEST END CAP ON MONITORING GAUGE AT OP.TEST OK.
22026174400 | 2022 SCADA VISIBILITY PROGRAM |  |  |  |  | 0.03919% | 28643.37 | 29658.8599 | -1015.4899 | 2022-01-01 | 2022-12-31 | 2022-05-10 | 2022-10-11 | INSTALL POLES FOR COMM EQUIPMENT 05-10-2022 CC 66285 RHAYES
21026151300 | RETIRE 2111'-2"&6" CSMP |  |  |  |  | 0.0001095% | 80 | 109.7476 | -29.7476 | 2022-01-01 | 2022-12-31 | 2022-10-12 | 2022-10-17
22026194600 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.005507% | 4024.88 | 4801.1928 | -776.3128 | 2022-01-01 | 2022-12-31 | 2022-10-12 | 2022-10-12 | CCC# 3219 INSTALLED MIWI INSTALLED NEW MIWI350 WSHINFESSEL 10-12-22
22026194700 | RETIRED ELECTRONIC EXCHANGE |  |  |  |  | 0% | 0 | 124.8731 | -124.8731 | 2022-01-01 | 2022-12-31 | 2022-10-12 | 2022-10-12 | RETIRED OLD ERX WSHINFESSEL 10-12-22
21026119200 | PM- LAKE CARNICO REPLACEMENT |  |  |  |  | 4.161% | 3041283.83 | 3161436 | -120152.17 | 2022-01-01 | 2022-12-31 | 2022-10-13 | 2022-10-13
21026119300 | PM- LAKE CARNICO ABANDONMENT |  |  |  |  | 0.9975% | 729097.27 | 62500 | 666597.27 | 2022-01-01 | 2022-12-31 | 2022-10-13 | 2022-10-13
22026228900 | EMER - INSTALL 40'-2" PMIP |  |  |  |  | 0.0514% | 37570.14 | 32269.3764 | 5300.7636 | 2022-01-01 | 2022-12-31 | 2022-10-06 | 2022-10-13
22026229000 | EMER - RETIRE 40'-2" PIP |  |  |  |  | 0% | 0 | 132.427 | -132.427 | 2022-01-01 | 2022-12-31 | 2022-10-13 | 2022-10-13
21026111600 | INSTALL FENCE |  |  |  |  | 0.02904% | 21225.79 | 2231 | 18994.79 | 2022-01-01 | 2022-12-31 | 2022-09-02 | 2022-10-13 | CCC# 79626 MONITOR FOR FENCE INSTALL. JMARTIN 9-2-22 CCC# 79759 MONITOR FOR FENCE INSTALL
20026982100 | INSTALL 800'-2" PMIP |  |  |  |  | 0.09474% | 69244.93 | 47914.5682 | 21330.3618 | 2022-01-01 | 2022-12-31 | 2022-10-10 | 2022-10-17
22026231600 | EMER - INSTALL 2'-4" PMMP |  |  |  |  | 0.0002688% | 196.47 | 5460.0467 | -5263.5767 | 2022-01-01 | 2022-12-31 | 2022-11-11 | 2022-11-11 | INSTALLED 2' OF 4" PL MP TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 40 P SIG
22026231700 | EMER - RETIRE 2'-4" PMMP |  |  |  |  | 3.315e-05% | 24.23 | 263.239 | -239.009 | 2022-01-01 | 2022-12-31 | 2022-11-10 | 2022-11-11 | RETIRED 2' OF 4" PL MP DUE TO LEAKAGE SOAP TESTED TO VERFY SHUTDOWN
22026193600 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.002616% | 1911.78 | 4801.1928 | -2889.4128 | 2022-01-01 | 2022-12-31 | 2022-10-18 | 2022-10-18 | CC # 3865 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 10-18-22
22026193700 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.0002976% | 217.55 | 124.8731 | 92.6769 | 2022-01-01 | 2022-12-31 | 2022-10-18 | 2022-10-18 | CC # 3865 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 10-18-22
22026220800 | *PAPER ONLY* 2022 CAST IRON |  |  |  |  | 0% | 0 | 295.7645 | -295.7645 | 2022-01-01 | 2022-12-31 | 2022-10-19 | 2022-10-19
22026197300 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.009447% | 6904.6 | 4801.1928 | 2103.4072 | 2022-01-01 | 2022-12-31 | 2022-10-19 | 2022-10-19 | CC# 3980 CMCOX 10/19/22 INSTALLED NEW MIWI350 CCOX 10-19-22
22026197400 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 0.0004179% | 305.47 | 124.8731 | 180.5969 | 2022-01-01 | 2022-12-31 | 2022-10-19 | 2022-10-19 | CC# 3980 CMCOX 10/19/22 RETIRED OLD ERX CCOX 10-19-22
22026198601 | INSTALL 1900' OF 2"PMMP MAIN |  |  |  |  | 0.0979% | 71556.52 | 50146.9852 | 21409.5348 | 2022-01-01 | 2022-12-31 | 2022-09-29 | 2022-10-21
22026213900 | INSTALL 200'-2"PMMP |  |  |  |  | 0.04817% | 35208.99 | 22574.1191 | 12634.8709 | 2022-01-01 | 2022-12-31 | 2022-10-19 | 2022-10-24 | BORED IN 308' OF 020 PL ML. TESTED 90# FOR 1 HR. SOAP TESTED CONN PTS @ 39#
22026214100 | ABANDON 200'-2" PMMP |  |  |  |  | 0.00126% | 921.07 | 800.8601 | 120.2099 | 2022-01-01 | 2022-12-31 | 2022-10-21 | 2022-10-21
22026195200 | EXCHANGE ELECTRONIC EQUIPMENT |  |  |  |  | 0.00917% | 6702.65 | 4801.1928 | 1901.4572 | 2022-01-01 | 2022-12-31 | 2022-10-13 | 2022-10-21 | CCC# 4229 CCC# 4229 INSTALLED NEW MIWI350 JPASLEY
22026195300 | RETIRED ELECTRONIC EQUIPMENT |  |  |  |  | 4.691e-05% | 34.29 | 124.8731 | -90.5831 | 2022-01-01 | 2022-12-31 | 2022-10-21 | 2022-10-21 | CCC# 4229 RETIRED OLD ERX INSTALLED NEW MIWI350 JPASLEY
22026167600 | INSTALL 6' OF 3"PMLP MAIN |  |  |  |  | 0.01197% | 8748.35 | 16229.6788 | -7481.3288 | 2022-01-01 | 2022-12-31 | 2022-09-30 | 2022-10-27 | CUT OUT 4' SECTION OF 3" MAIN. TESTED DROP IN PIECE 90#5MINS, TG. ST LTI, TG. BHBNGF. 2 17LB ANODES INSTALLED. PRSSURE NEVER DROPPED ON GAUGES. PURGED ALL AIR OUT BEFORE GAS UP. R.CRAWFORD 10-27-22
22026167700 | RETIRE 6' OF 3"CSLP MAIN |  |  |  |  | 0.01324% | 9674.55 | 100.2728 | 9574.2772 | 2022-01-01 | 2022-12-31 | 2022-10-24 | 2022-10-27 | CUT OUT 4' SECTION OF LEAKING 3" MAIN, TESTED DROP IN PIECE 90#20MINS, TG. ST LTI. TG. BHBNGF. INST. 2 17LB ANODES. PRESSURE NEVER DROPPED ON GAUGES. PURGED ALL AIR OUT BEFORE GAS UP. R.CRAWFORD 10-27-22
21026998201 | INSTALL 1930'-2"/4" PMMP |  |  |  |  | 0.1562% | 114169.59 | 114050.6727 | 118.9173 | 2022-01-01 | 2022-12-31 | 2022-09-26 | 2022-11-01 | GAS ON MAIN 11/01/2022
22026230000 | ABANDON 470'-2"&3"PLP |  |  |  |  | 0.008071% | 5899.02 | 6027.5291 | -128.5091 | 2022-01-01 | 2022-12-31 | 2022-11-01 | 2022-11-01 | ABANDONED 334' OF 030 PL LP ML PER ENGINEERING AND TIE IN PLAN. SOAP TEST END CAP @ OP 15 MINS NO LEAKS BHB NGF. PURGED OUT ABANDONED SECTION OF ML G OOD M. COLLINS 11/1/2022
22026202500 | INSTALL 1120'-2"/4" PMMP |  |  |  |  | 0.06853% | 50092.05 | 49758.6341 | 333.4159 | 2022-01-01 | 2022-12-31 | 2022-10-19 | 2022-11-02
23026246200 | INSTALL VRG - MIS FACILITY |  |  |  |  | 0% | 0 | 449.3532 | -449.3532 | 2022-01-01 | 2022-12-31 | 2022-11-02 | 2022-12-16
23026246300 | INSTALL VRG - RETIRE MIS FAC |  |  |  |  | 0% | 0 | 132.4844 | -132.4844 | 2022-01-01 | 2022-12-31 | 2022-11-02 | 2022-12-16
20026922500 | INSTALL ELECTRONICS |  |  |  |  | 0.3269% | 238947.63 | 123804 | 115143.63 | 2022-01-01 | 2022-12-31 | 2022-11-02 | 2022-11-02 | CCC # 40652 NOT ON SITE CC# 47218. 12/01/21 DSASH CCC # 47218 CCC # 47356 CC# 47727. 12/07/21 DSASH
20026922600 | RETIRE ELECTRONICS |  |  |  |  | 0.0001973% | 144.18 | 115.4611 | 28.7189 | 2022-01-01 | 2022-12-31 | 2022-11-02 | 2022-11-02
18026757800 | RETIRE RECORDING GAUGE |  |  |  |  | 0% | 0 | 73.0037 | -73.0037 | 2022-01-01 | 2022-12-31 | 2022-11-07 | 2022-11-07 | RETIRED CHART INSTALLED HONEYWELL ERX JMULLINS 11-7-22
18026757700 | INSTALL MI WIRELESS EFC |  |  |  |  | 0.01942% | 14191.42 | 13926.0597 | 265.3603 | 2022-01-01 | 2022-12-31 | 2022-11-07 | 2022-11-07 | INSTALLED HONEYWELL ERX SUPER SOLAR KIT J MULLINS 11-7-22
22026216700 | EMER - INSTALL 456'-4" CS/PMIP |  |  |  |  | 0.1166% | 85192.39 | 50625 | 34567.39 | 2022-01-01 | 2022-12-31 | 2022-11-01 | 2022-11-09
22026216801 | EMER-RETIRE 130'-4" CS/BS/PIP |  |  |  |  | 0.0006006% | 439.01 | 132.427 | 306.583 | 2022-01-01 | 2022-12-31 | 2022-11-02 | 2022-11-09
21026132400 | INSTALL 225' OF 2"PMMP |  |  |  |  | 0.1169% | 85412.94 | 79492.8479 | 5920.0921 | 2022-01-01 | 2022-12-31 | 2022-10-25 | 2022-11-17 | TTALKER/KY 01-25-23: JOB IS SHOWING COST UNDER RUN AT THIS TIME BUT PAVING/ STREET REPAIRS NOT TAKE PLACE UNTIL SPRING/WARM WEATHER. TWALKER/KY 06-23-23: JOB ORDER CURRENTLY UNDER RUNNING $32000 BUT STREET PAVING HAS NOT BEEN COMPLETED AT THIS TIME DUE TO DOWNTOWN AREA AND CONSTRU CTION BY OTHERS IN AREA. TWALKER/KY 07-21-23: PAVING HAS BEEN COMPLETED AND COST APPLIED TO JOB ORDE R, NOT OVER OR UNDER BUDGET VARIANCE REQUIRED AT THIS TIME. PAVING WAS DELAYED TO COLD AND WET WEATHER PLUS THIS PROJECT IS LOCATED IN DOWNTOWN AREA SO PERMIT RESTRICTION APPLIED.
21026993500 | RETIRE 13650' OF 4"/6"BSLP |  |  |  |  | 0.0001095% | 80 | 86.5975 | -6.5975 | 2022-01-01 | 2022-12-31 | 2022-11-15 | 2022-11-17
22026212100 | INSTALL CHAIN LINK FENCE |  |  |  |  | 0.01262% | 9226.54 | 24086.2589 | -14859.7189 | 2022-01-01 | 2022-12-31 | 2022-11-08 | 2022-11-11 | INSTALLED CHAIN LINK FENCE JMULLINS 11-11-22
22026221000 | INSTALL 160'-4"PMMP |  |  |  |  | 0.04977% | 36375.08 | 20578.0582 | 15797.0218 | 2022-01-01 | 2022-12-31 | 2022-11-02 | 2022-11-14 | AWEBER 12/6/22 - JOB ENCOUNTERED HEAVY ROCK BORE, RESULTING IN DOUBLE TIME FROM ORIGINAL ESTIMATE. ATTEMPT TO REVISE, UNABLE DUE TO UNPAID INVOICES.
21026994000 | INSTALL 10930 - 2"/4"PMMP MAIN |  |  |  |  | 2.301% | 1681569.14 | 1953601.844 | -272032.704 | 2022-01-01 | 2022-12-31 | 2022-04-26 | 2022-11-16 | TWALKER/KY 05-22-23: PROJECT CURRENTLY UNDER RUNNING, WAITING ON FINAL RESTORATION/PAVING TO DETERMINE IF ADDITIONAL EXPLAINATION OR VARIANCE REQU IRED. TWALKER/KY 06-23-23: JOB UNDER RUNNING DUE TO PAVING/HARD SURFACES REPAIRS HAVE NOT BEEN FULLY COMPLETED. TWALKER/KY 07-24-23: PAVING/HARD SURFACE REPAIRS STILL IN PROGRESS TWALKER/KY 08-29-23: LEVEL 1 VARIANCE FORM ADDED IN WMS.DOCS NOT SURE IF ALL PAVING INVOICES HAVE BEEN PAID BUT COST UNDER RUN DRIVEN BY LESS PAVING COST BY PAVING CONTRACTOR INSTEAD OF PIPELINE CO.
21026994100 | RETIRE 14,600 - 4"CI/BSLP MAIN |  |  |  |  | 0.0003687% | 269.51 | 84.1794 | 185.3306 | 2022-01-01 | 2022-12-31 | 2022-11-16 | 2022-11-23
22026240900 | PAPER ONLY EXECUTE |  |  |  |  | 0% | 0 | 119.2135 | -119.2135 | 2022-01-01 | 2022-12-31 | 2022-11-30 | 2022-11-30
21026129900 | RETIRE PIT REG STATION W/AMRP |  |  |  |  | 0.004979% | 3639 | 4706.4362 | -1067.4362 | 2022-01-01 | 2022-12-31 | 2022-11-16 | 2022-11-16 | RETIRED 800 PRESS AVE 200340, CMCHOLAN 11-16-22
22026209800 | RETIRE VAULT STRUCTURE |  |  |  |  | 0% | 0 | 1027.5809 | -1027.5809 | 2022-01-01 | 2022-12-31 | 2022-11-16 | 2022-11-16 | PIT RETIRED AND FILLED IN
22026185301 | INSTALL 875' OF 2"PMMP MAIN |  |  |  |  | 0.09517% | 69561.33 | 74170.089 | -4608.759 | 2022-01-01 | 2022-12-31 | 2022-11-16 | 2022-11-18
22026240400 | PAPER ONLY - RETIRE BSIP MAIN |  |  |  |  | 0% | 0 | 119.2135 | -119.2135 | 2022-01-01 | 2022-12-31 | 2022-12-19 | 2022-12-19
22026245500 | INSTALL REG STATION BUILDING |  |  |  |  | 0.01681% | 12285 | 128388.6752 | -116103.6752 | 2022-01-01 | 2022-12-31 | 2022-11-18 | 2022-12-16
23026246000 | INSTALL M&R CRANE - MARATHON |  |  |  |  | 0.0194% | 14182.67 | 36312.6752 | -22130.0052 | 2022-01-01 | 2022-12-31 | 2022-11-18 | 2022-12-16
20026969900 | INSTALL FENCE & BOLLARDS |  |  |  |  | 0.01314% | 9603.34 | 36430.1489 | -26826.8089 | 2022-01-01 | 2022-12-31 | 2022-09-13 | 2022-11-19 | INSTALLED NEW FENCE 11-19-22 JMULLINS
20026970000 | RETIRE BUILDING |  |  |  |  | 0.03616% | 26427.16 | 88.8156 | 26338.3444 | 2022-01-01 | 2022-12-31 | 2022-09-13 | 2022-11-19 | CCC# 37831 CCC# 33819 CCC# 38966 TO BE COMP BY CFARRIS BUILDING REMOVED JMULLINS
22026234300 | RETIRE GMB SETTING |  |  |  |  | 0% | 0 | 725.239 | -725.239 | 2022-01-01 | 2022-12-31 | 2022-11-21 | 2022-11-21 | RETIRED GMB SETTING REMOVED METER BLIND PLATED SERVICE GAS NO LONGER NEEDED
22026234700 | INSTALL 3" STOPPLE FITTING |  |  |  |  | 0.01085% | 7929.81 | 13630.9028 | -5701.0928 | 2022-01-01 | 2022-12-31 | 2022-11-29 | 2022-11-30
22026234800 | RETIRE 75' OF 3"BSMP MAIN |  |  |  |  | 0.0001572% | 114.9 | 119.2135 | -4.3135 | 2022-01-01 | 2022-12-31 | 2022-11-29 | 2022-11-29
22026233800 | INSTALL 380' OF 4"PMLP SL |  |  |  |  | 0.04904% | 35845.97 | 36339.1396 | -493.1696 | 2022-01-01 | 2022-12-31 | 2022-11-15 | #N/A
22026240700 | INSTALL FENCE FOR NEW LAND |  |  |  |  | 0.08746% | 63926.63 | 26194.1417 | 37732.4883 | 2022-01-01 | 2022-12-31 | 2022-11-30 | 2022-11-30 | CCC# 12436 TICKET# 12436 CCC# 16515 GATHER INFO FOR CAPITAL PAPERWORK
22026232100 | RETIRE PAPER GAUGE |  |  |  |  | 0.0009839% | 719.12 | 993 | -273.88 | 2022-01-01 | 2022-12-31 | 2022-12-02 | 2022-12-14 | REMOVED CHART, CCC 2244, CMCHOLAN 12-1-22
22026240200 | EMER - INSTALL 100'-4" PMLP |  |  |  |  | 0.007035% | 5141.88 | 38890.2222 | -33748.3422 | 2022-01-01 | 2022-12-31 | 2022-12-02 | 2022-12-30 | INSTALLED 93' OF PL AND ST TESTED 90 PSIG 1 HR SOAP TESTED WELD CAPS AND SSTEE CAPS 10" WC
22026240300 | EMER - RETIRE 100'-4" BSLP |  |  |  |  | 0.0003903% | 285.28 | 129.6266 | 155.6534 | 2022-01-01 | 2022-12-31 | 2022-12-02 | 2022-12-30 | RETIRED 75' OF 4" BS DUE TO LEAKAGE
22026241300 | EMER - INSTALL 5'-4" PMMP |  |  |  |  | 0.001566% | 1144.39 | 10162.4624 | -9018.0724 | 2022-01-01 | 2022-12-31 | 2022-12-14 | 2022-12-15 | INSTALLED 3' OF 4" PL DUE TO LEAKAGE ON SERVICE TEE TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 11 PSIG
22026241400 | EMER - RETIRE 5'-4" PMP |  |  |  |  | 0.0001256% | 91.78 | 117.5985 | -25.8185 | 2022-01-01 | 2022-12-31 | 2022-12-14 | 2022-12-15 | RETIRE 4" MP TO DUE TO LEAKAGE ON SERVIEC TEE TO INSTALL NEW
22026234200 | INSTALL 100'-6"PMMP S/L |  |  |  |  | 0.08243% | 60246.05 | 78909.8457 | -18663.7957 | 2022-01-01 | 2022-12-31 | 2022-11-29 | 2022-12-06 | CJH JOE HADLEY REPLACED SL, TESTED SL AT 0106PSIG/0200HRS, OPEN CUT, SOAP TESTED FC/CAP AT OP, EXT CORR INSP, NO ANODE, WRAPPED EXPOSED MAIN, DS 12062022
22026222700 | INSTALL 86'-2" PMMP |  |  |  |  | 0.01849% | 13511.21 | 12304.5709 | 1206.6391 | 2022-01-01 | 2022-12-31 | 2022-12-05 | 2022-12-07 | THERE WAS A TYPO ON THE PRESSURE SYSTEM WHEN IT WAS CREATED. CORRECT SYSTEM NUMBER 32010047. SYSTEM NUMBER HAS BEEN CORRECTED IN DIS.
22026245100 | EMER-INSTALL 3' OF 2"PHHP MAIN |  |  |  |  | 0.003766% | 2752.76 | 4877.0569 | -2124.2969 | 2022-01-01 | 2022-12-31 | 2022-12-07 | 2022-12-07
22026240500 | INSTALL VRG |  |  |  |  | 0.01037% | 7577.2 | 14784.1417 | -7206.9417 | 2022-01-01 | 2022-12-31 | 2022-12-08 | 2022-12-08 | NOT ON SITE. GETTING MATERIAL FROM SHOP FOR JOB. CCC# 6417 CCC# 6417 CCC# 6417 CCC# 6417
22026240600 | RETIRE VRG |  |  |  |  | 0.001937% | 1416.09 | 1478.5709 | -62.4809 | 2022-01-01 | 2022-12-31 | 2022-12-08 | 2022-12-08
21026993900 | RETIRE 9500' OF 4"CI/6"BSLP MN |  |  |  |  | 0.00804% | 5876.52 | 80.3582 | 5796.1618 | 2022-01-01 | 2022-12-31 | 2022-01-25 | 2022-12-09 | ABANDONED ALL MAINS IN SCOPE OF PROJECT
22026245000 | PAPER ONLY EXECUTE |  |  |  |  | 0% | 0 | 131.2422 | -131.2422 | 2022-01-01 | 2022-12-31 | 2022-12-09 | 2022-12-09
22026242500 | EMER-RETIRE 385' OF 2"/3"PAIP |  |  |  |  | 0.007701% | 5628.45 | 5363.3319 | 265.1181 | 2022-01-01 | 2022-12-31 | 2022-12-12 | 2022-12-13
22026219600 | INSTALL 90'-2" PMIP |  |  |  |  | 0.06924% | 50608.23 | 21041.6638 | 29566.5662 | 2022-01-01 | 2022-12-31 | 2022-12-12 | 2022-12-19
22026235200 | INSTALL 200'-2" PMIP |  |  |  |  | 0.0164% | 11987.46 | 38455.6638 | -26468.2038 | 2022-01-01 | 2022-12-31 | 2022-12-15 | 2022-12-19
20026941000 | RETIRE GAUGE |  |  |  |  | 0.002165% | 1582.1 | 91.4991 | 1490.6009 | 2022-01-01 | 2022-12-31 | 2022-02-18 | 2022-12-15 | CCC TICKET# 55594 CCC# 55594 ERX ONLINE P2P W/GAS CONTROL OK REMOVED CHART BOX AND FILED LAST CHART ON CABINET TICKET# 11209 GATHERED INFORMATION FOR CLOSEOUT PAPERWORK 12-15-22 JBRADFORD
22026175300 | RETIRE R-1278 |  |  |  |  | 0.002588% | 1891.36 | 7307.4769 | -5416.1169 | 2022-01-01 | 2022-12-31 | 2022-12-15 | 2022-12-15 | PREMISE IS RETIRED. GATHERED INFORMATION FOR CLOSEOUT PAPERWORK. JBRADFORD 12-15-22 CCC# 20387 TICKET# 20387
21026120600 | RETIRE REG STATION WITH AMRP |  |  |  |  | 0.001448% | 1058.49 | 9924.8698 | -8866.3798 | 2022-01-01 | 2022-12-31 | 2022-11-09 | 2022-12-15 | CC# 6407 RETIRED REG STATION DASH 12-15-2022
22026210700 | RETIRE METAL BUILDING |  |  |  |  | 0% | 0 | 1009.5809 | -1009.5809 | 2022-01-01 | 2022-12-31 | 2022-12-15 | 2022-12-15 | REG STATION AND BUILDING RETIRED DASH 12-15-22
22026232200 | INSTALL SKID MOUNTED GMB |  |  |  |  | 0.05508% | 40259.26 | 56170.7039 | -15911.4439 | 2022-01-01 | 2022-12-31 | 2022-11-29 | 2022-12-15 | INSTALLED NEW SKID MOUNTED METER SETTING DASH 12-15-22
22026232300 | RETIRE GMB SETTING |  |  |  |  | 0.002714% | 1984.01 | 263.239 | 1720.771 | 2022-01-01 | 2022-12-31 | 2022-11-01 | 2022-12-15 | INSTALLED NEW SKID MOUNT METER SETTING AND RETIRED OLD METER AND REGULATORS DASH 12-15-22
18026848701 | STATION UPGRADES (SEP RELATED) |  |  |  |  | 0.2826% | 206545.63 | 151848.4602 | 54697.1698 | 2022-01-01 | 2022-12-31 | 2021-05-07 | 2022-12-15 | CCC 22581 CCC 23126 CCC 23442 CCC 24345 CCC 25855 CCC 26071
20026940900 | INSTALL I&C EQUIPMENT |  |  |  |  | 0.01758% | 12849.77 | 18740.1071 | -5890.3371 | 2022-01-01 | 2022-12-31 | 2022-12-15 | 2022-12-15 | CCC TICKET# 55594 CCC TICKET# 55594 PAPER WORK GATHER INFO 12-15-22 JBRADFORD
22026227200 | RETIRE ELECTRONICS |  |  |  |  | 0% | 0 | 74.3089 | -74.3089 | 2022-01-01 | 2022-12-31 | 2022-12-15 | 2022-12-15
22026232600 | INSTALL 200'-2" PMMP |  |  |  |  | 0.02743% | 20049.03 | 40586.0582 | -20537.0282 | 2022-01-01 | 2022-12-31 | 2022-12-13 | 2022-12-16
22026163000 | INSTALL ODORIZER |  |  |  |  | 0.5729% | 418702.35 | 596431.4654 | -177729.1154 | 2022-01-01 | 2022-12-31 | 2023-12-13 | #N/A
22026245300 | EMER - INSTALL 5'-2" PMMP |  |  |  |  | 0.00521% | 3807.72 | 10393.9744 | -6586.2544 | 2022-01-01 | 2022-12-31 | 2023-01-16 | 2023-01-19
22026245400 | EMER - RETIRE 5'-2" PMMP |  |  |  |  | 0% | 0 | 131.2422 | -131.2422 | 2022-01-01 | 2022-12-31 | 2023-01-16 | 2023-01-19
22026232700 | RETIRE GMB W/22-9790457-00 |  |  |  |  | 0% | 0 | 545.7645 | -545.7645 | 2022-01-01 | 2022-12-31 | 2022-12-20 | 2022-12-21
[7 empty] | 2022 Construction Project Budget | 73091000
23026246100 | RETIRE PAPER GAUGE |  |  |  |  | 0.0005638% | 389.08 | 131.2422 | 257.8378 | 2023-01-01 | 2023-12-31 | 2023-01-02 | 2023-01-02 | RETIRE PRESSURE CHART GUAGE CCOX 1-2-23
23026248200 | EMER - INSTALL 2'-2" PMMP |  |  |  |  | 0.0001966% | 135.67 | 13154.2985 | -13018.6285 | 2023-01-01 | 2023-12-31 | 2023-01-09 | 2023-01-11 | INSTALLED 2 ' OF 2'' PMP PIPE ( TESTED PIPE FOR 20MNS-GOOD PER FOL R. VANDERPOOL) J.OCHOA
23026248300 | EMER - RETIRE ~2'-2"PMP |  |  |  |  | 0.002388% | 1647.72 | 129.6266 | 1518.0934 | 2023-01-01 | 2023-12-31 | 2023-01-09 | 2023-01-11 | RETIRED 2' OF 2'' P MP MAIN DUE TO DAMAGE. J.OCHOA 01-11-2023
23026248600 | RETIRE 3'-3" PMLP |  |  |  |  | 0.004366% | 3012.93 | 1635.0284 | 1377.9016 | 2023-01-01 | 2023-12-31 | 2023-01-10 | 2023-01-25 | RETIRED 20' OF 3" PL MAIN DUE TO FACILITY DAMAGE SOAP TESTED OP 9.5" WC
22026211800 | RETIRE GMB SETTING |  |  |  |  | 0.002234% | 1541.41 | 1288.7874 | 252.6226 | 2023-01-01 | 2023-12-31 | 2023-01-10 | 2023-01-10 | GMB NO CC NEEDED
22026210301 | INSTALL 850' OF 4"PMMP MAIN |  |  |  |  | 0.2496% | 172217.52 | 192098.991 | -19881.471 | 2022-01-01 | 2022-12-31 | 2022-12-09 | 2023-01-23
22026238200 | INSTALL 205' OF 2"PMMP MAIN |  |  |  |  | 0.01971% | 13604.24 | 19394.2346 | -5789.9946 | 2023-01-01 | 2023-12-31 | 2023-01-12 | 2023-01-16 | TWALKER/KY 01-20-23: ISSUED BACK ORDER REQUEST #52196 FOR THIS JOB
23026249300 | EMER-INSTALL 5' OF 2"PMMP |  |  |  |  | 0.007264% | 5012.41 | 8253.2559 | -3240.8459 | 2023-01-01 | 2023-12-31 | 2023-01-13 | 2023-01-18 | REPLACED 3' OF DAMAGED 2" PLASTIC MAIN LINE WITH 2 EF COUPLINGS. PRESSURE TESTED THE THE NEW MAIN LINE AT 90PSIG FOR 1 HOUR. PRESSURE TEST OKAY. BHB, NGF. SOAP TESTED FINAL TIE IN AT OP. TEST OK. DMALONE
23026252000 | EMER-INSTALL 3' OF 6"PMMP MAIN |  |  |  |  | 0.01891% | 13052.34 | 12970.9861 | 81.3539 | 2023-01-01 | 2023-12-31 | 2023-01-17 | 2023-02-03
23026249400 | EMER-RETIRE 5' OF 2"PMMP MAIN |  |  |  |  | 0.0003179% | 219.4 | 131.2422 | 88.1578 | 2023-01-01 | 2023-12-31 | 2023-01-13 | 2023-01-17 | REPLACED 3' OF DAMAGES 2" PLASTIC MAIN LINE WITH 2 EF COUPLINGS. PRESSURE TESTED THE NEW MAIN LINE AT 90PSIG FOR 1 HOUR. PRSSURE TEST OK. BHB, NGF. SOAP TESTED FINAL TIE IN AT OP. TEST OK. DMALONE
23026252100 | RETIRE 3' OF 6"PMP MAIN |  |  |  |  | 0% | 0 | 138.8485 | -138.8485 | 2023-01-01 | 2023-12-31 | 2023-01-17 | 2023-02-03
23026249200 | GMB TO CAB CONVERSION |  |  |  |  | 0.001244% | 858.55 | 132.4844 | 726.0656 | 2023-01-01 | 2023-12-31 | 2023-01-17 | 2023-01-17 | CONVERTED FROM GMB TO CAB SGIORDANO
23026248400 | EMER-INSTALL 3' OF 2"PMMP MAIN |  |  |  |  | 0.003366% | 2322.97 | 5318.1948 | -2995.2248 | 2023-01-01 | 2023-12-31 | 2023-01-08 | 2023-01-18
23026248500 | EMER-RETIRE 3' OF 2"PMMP MAIN |  |  |  |  | 0% | 0 | 131.2422 | -131.2422 | 2023-01-01 | 2023-12-31 | 2023-01-08 | 2023-01-18
21026139400 | REMOVE BUILDING FOR R-1455 |  |  |  |  | 0.005782% | 3989.86 | 117.5985 | 3872.2615 | 2023-01-01 | 2023-12-31 | 2023-01-18 | 2023-01-18 | BUILDING REMOVED AND CLEANED UP BY PLANT. JMULLINS 1-18-23
23026252200 | EMER-INSTALL 3' OF 4"PMMP MAIN |  |  |  |  | 0.007738% | 5339.51 | 7839.2961 | -2499.7861 | 2023-01-01 | 2023-12-31 | 2023-01-18 | 2023-02-02
23026252300 | EMER-RETIRE 3' OF 4"PAMP MAIN |  |  |  |  | 0% | 0 | 138.8485 | -138.8485 | 2023-01-01 | 2023-12-31 | 2023-01-18 | 2023-02-02
22026167200 | INSTALL 720'- 4" PMMP |  |  |  |  | 0.425% | 293269.78 | 309266.4996 | -15996.7196 | 2023-01-01 | 2023-12-31 | 2023-01-10 | 2023-02-13 | ADETOMIWA FALADE 8/29/2023. JOB IS CURRENTLY SHOWING LEVEL 1 UNDER RUN BUT $35,000 IN PAVING WAS PROCESSED THIS WEEK. ONCE THIS PAYMENT IS APPLIED TO THIS JOB ORDER, NO VARIANCE PAPERWORK SHOULD BE REQUIRED. THE PAVING WAS PERFORMED BY PRIVATE CONTRACTOR INSTEAD OF PIPELINE CONTRACTOR WHICH SAVED THE COST OF PAVING.
23026251100 | INSTALL EC-350 UNIT |  |  |  |  | 0.002621% | 1808.88 | 3195.3221 | -1386.4421 | 2023-01-01 | 2023-12-31 | 2023-01-24 | 2023-01-24 | INSTALLED NEW EC350 DASH 1-24-23
23026251200 | RETIRE PAPER BILLING CHART |  |  |  |  | 0.001414% | 975.93 | 131.2422 | 844.6878 | 2023-01-01 | 2023-12-31 | 2023-01-24 | 2023-01-24 | RETIRED CHART INSTALLED NEW EC350 DASH 1-24-23
23026252600 | INSTALL 3' OF 4"PMLP MAIN |  |  |  |  | 0.02401% | 16571.37 | 9484.2961 | 7087.0739 | 2023-01-01 | 2023-12-31 | 2023-01-25 | 2023-01-25 | ABD 69 FT BS CUT OUT INLINE TEE AND INSTALLED 5 FT OF 4 IN PL TEST 90 LB FOR 1 HR OK SOAP TEST CPLG AND TEES AT OP FOR 5 MIN BAR HOLE BANKS NO GAS FOUND
23026252700 | RETIRE 69' OF 4"BSLP MAIN |  |  |  |  | 0% | 0 | 138.8485 | -138.8485 | 2023-01-01 | 2023-12-31 | 2023-01-24 | 2023-01-25 | ABDN 69 FT OF 6 IN BARE STEEL BLEW DOWN AND SEALED ENDS
23026249800 | INSTALL EC 350 UNIT |  |  |  |  | 0.007795% | 5379.35 | 7475.3221 | -2095.9721 | 2023-01-01 | 2023-12-31 | 2023-01-25 | 2023-01-25 | CHECK TO SEE IF CARD WAS READY CMCHOLAN 1-27-2023 INSTALLED NEW EC350 CMCHOLAN 1-25-23
23026249900 | RETIRE PAPER BILLING CHART |  |  |  |  | 0.000671% | 463.02 | 131.2422 | 331.7778 | 2023-01-01 | 2023-12-31 | 2023-01-25 | 2023-01-25 | REMOVED PAPER BILLING CHART, CMCHOLAN EBLANTON 1-25-23
22026229200 | INSTALL 80'-2" PMMP |  |  |  |  | 0.01562% | 10781.29 | 11104.5291 | -323.2391 | 2023-01-01 | 2023-12-31 | 2023-01-27 | 2023-01-27 | INSTALLED 160' 2'' MP-PL MAINLINE
23026249600 | PM- DE ILI PH 2 JIM BEAM INST |  |  |  |  | 1.4% | 965942.08 | 593000 | 372942.08 | 2023-01-01 | 2023-12-31 | 2023-01-27 | 2023-01-27
23026249700 | PM- DE ILI PH 2 JIM BEAM ABAN |  |  |  |  | 0.3393% | 234155.55 | 132000 | 102155.55 | 2023-01-01 | 2023-12-31 | 2023-01-27 | 2023-01-27
23026253900 | RETIRE PRESSURE GAUGE |  |  |  |  | 0% | 0 | 552.5683 | -552.5683 | 2023-01-01 | 2023-12-31 | 2023-01-27 | 2023-01-27
23026254000 | RETIRE PRESSURE GAUGE |  |  |  |  | 0.001114% | 768.43 | 552.5683 | 215.8617 | 2023-01-01 | 2023-12-31 | 2023-01-31 | 2023-01-31 | CC15136 CHART HAS BEEN REMOVED ISO UPDATED 1-31-23 CC15136 CHART HAS BEEN REMOVED ISO UPDATED 1-31-23
22026204100 | RETIRE BUILDING |  |  |  |  | 0% | 0 | 76.9137 | -76.9137 | 2023-01-01 | 2023-12-31 | 2023-01-31 | 2023-01-31 | BUILDING DEMOLISHED BY CONTRACTORS
22026204400 | RETIRE BUILDING |  |  |  |  | 0% | 0 | 76.9137 | -76.9137 | 2023-01-01 | 2023-12-31 | 2023-01-31 | 2023-01-31 | BUILDING DEMOLISHED BY CONTRACTOR
23026254700 | RETIRE PAPER GAUGE |  |  |  |  | 0.0003589% | 247.65 | 552.5683 | -304.9183 | 2023-01-01 | 2023-12-31 | 2023-02-10 | 2023-02-10 | REMOVED PAPER CHART, CCC 10587
23026248900 | INSTALL 100' OF 2"PMMP MAIN |  |  |  |  | 0.04186% | 28889.25 | 30720.7606 | -1831.5106 | 2023-01-01 | 2023-12-31 | 2023-02-02 | 2023-02-03
23026249000 | RETIRE 86' OF 2"CSMP MAIN |  |  |  |  | 0% | 0 | 131.2422 | -131.2422 | 2023-01-01 | 2023-12-31 | 2023-02-02 | 2023-02-09 | ABN 102' OF 2'' COATED STEELE MAIN PURGED AND END SEALED
23026254100 | RETIRE PRESSURE GAUGE |  |  |  |  | 0.000105% | 72.46 | 552.5683 | -480.1083 | 2023-01-01 | 2023-12-31 | 2023-02-03 | 2023-02-03 | CCC# 10600 RETIRED PRESSURE CHART. JMARTIN 2-3-23
20026952500 | REPLACE VALVE C-16 |  |  |  |  | 0.06895% | 47582.37 | 56236.611 | -8654.241 | 2023-01-01 | 2023-12-31 | 2023-02-02 | 2023-02-07
20026952600 | RETIRE VALVE C-16 |  |  |  |  | 0.00839% | 5789.59 | 952.0929 | 4837.4971 | 2023-01-01 | 2023-12-31 | 2023-02-02 | 2023-02-07
23026252400 | RETIRE GMB MS#804399 RUN |  |  |  |  | 0.03156% | 21780.96 | 2962.0987 | 18818.8613 | 2023-01-01 | 2023-12-31 | 2023-02-06 | 2023-02-06 | NOT ONSITE NOT ONSITE GATHERING PARTS CCC# 15748 TICKET# 15748 RETIRED GMB SETTING 2-6-23 BY J.BRADFORD
23026250900 | INSTALL EC 350 |  |  |  |  | 0.001095% | 755.31 | 2339.3221 | -1584.0121 | 2023-01-01 | 2023-12-31 | 2023-02-07 | 2023-02-07 | INSTALLED NEW EC 350 INSTALLED EC 350 J.BRADFORD 2-7-23
23026251000 | RETIRE PAPER BILLING CHART |  |  |  |  | 0.001165% | 803.89 | 131.2422 | 672.6478 | 2023-01-01 | 2023-12-31 | 2023-02-07 | 2023-02-07 | BILLING CHART REMOVED AND EC 350 INSTALLED
23026254300 | TAP W/MAIN 23-0262543-00 |  |  |  |  | 0.006463% | 4459.75 | 13015.0987 | -8555.3487 | 2023-01-01 | 2023-12-31 | 2023-02-08 | 2023-02-08
22026223900 | INSTALL 1067'-4" PMMP |  |  |  |  | 0.2173% | 149979.89 | 181608.1135 | -31628.2235 | 2023-01-01 | 2023-12-31 | 2023-01-24 | 2023-02-10
22026224000 | RETIRE 1150'-4" PMMP |  |  |  |  | 0% | 0 | 72.8379 | -72.8379 | 2023-01-01 | 2023-12-31 | 2023-01-24 | 2023-02-10
22026216300 | INSTALL VRG CONTROLLER |  |  |  |  | 0.04137% | 28545.09 | 10806.1191 | 17738.9709 | 2023-01-01 | 2023-12-31 | 2023-02-09 | 2023-02-09 | CC 15047 CC 15628 CC 15628 CC 15628 CC 15628 CC 16352 NOT ON SITE CAPITAL PAPERWORK/ISO SKETCH
22026216400 | RETIRE CONTROLLERS |  |  |  |  | 0.0008299% | 572.67 | 84.9152 | 487.7548 | 2023-01-01 | 2023-12-31 | 2023-02-09 | 2023-02-09 | RETIRED CONTROLLERS, INSTALLED NEW VRG'S
22026158800 | INSTALL 540' OF 4"/8"PMMP MAIN |  |  |  |  | 0.5491% | 378932.24 | 262444.8259 | 116487.4141 | 2023-01-01 | 2023-12-31 | 2023-01-17 | 2023-03-03 | TWALKER/KY 09-27-23: LEVEL 1 VARIANCE FORM ADDED TO WMS.DOCS JOB OVER RUN DUE TO ADDITIONAL PAVING/RESTORATION REQUIREMENT BY THE CITY INCREASED CONTRACT COST BY $30,000, ALSO SEGA $12,000 HIGHER THAN ESTIMATE. COMPANY LABOR INCREASED BY $25,000 DUE TO ADDITIONAL COMPANY LABOR REQUIRED. TWALKER/KY 10-27-23: LEVEL 2 VARIANCE REPORTED ADDED TO WMS.DOCS, JOB OVER DUE TO CITY PAVING AND RE-PAVING REQUIREMENT.
22026158900 | RETIRE 594' OF 8"BSMP MAIN |  |  |  |  | 0% | 0 | 72.8047 | -72.8047 | 2023-01-01 | 2023-12-31 | 2023-01-17 | 2023-03-03
22026167300 | RETIRE 720'-4" BS-LP |  |  |  |  | 0% | 0 | 62.2578 | -62.2578 | 2023-01-01 | 2023-12-31 | 2023-01-10 | 2023-02-13
23026248700 | INSTALL 2" SS |  |  |  |  | 0.00344% | 2373.93 | 18496.357 | -16122.427 | 2023-01-01 | 2023-12-31 | 2023-02-13 | 2023-03-22
23026248800 | RETIRE 50' - 2" CSMP |  |  |  |  | 0.009678% | 6678.36 | 138.8485 | 6539.5115 | 2023-01-01 | 2023-12-31 | 2023-02-13 | 2023-03-22
23026258600 | EMER - INSTALL 5'-4" PMIP |  |  |  |  | 0.04242% | 29274.5 | 23135.0467 | 6139.4533 | 2023-01-01 | 2023-12-31 | 2023-02-14 | 2023-06-14 | INSTALLED 3' OF 4" PL DUE TO BORE CREW BORING INTO MAIN TESTED 90 PSIG 1 HR
23026258700 | EMER- RETIRE 5'-4" PMIP |  |  |  |  | 0.002835% | 1956.38 | 137.555 | 1818.825 | 2023-01-01 | 2023-12-31 | 2023-02-14 | 2023-06-13 | RETIRED 3' OF 4" IP DUE TO BORE CREW HITTING MAIN SOAP TESTED OP 7 PSIG TO VERIFY SQUEEZE OFF
23026259000 | EMER-INST 85'-4"PMMP MND311494 |  |  |  |  | 0.03438% | 23726.73 | 25540.4028 | -1813.6728 | 2023-01-01 | 2023-12-31 | 2023-02-19 | 2023-02-20 | 4" MAIN/PINK PL LEAKING UNDER STAMPED CONCRETE ENTRANCE TO COUNTRY CLUB RETIRED 85' AND INSTALLED 85' OF NEW MAIN-BORING DONE BY STANLEY PIPELINE, MAIN TEST 1 HR @90IB OK, TIE IN COMPLETE 02/20/2023 HMCKUNE
23026259100 | EMER-RETIRE 85' OF 4"PAMP MAIN |  |  |  |  | 0.0003777% | 260.66 | 138.8485 | 121.8115 | 2023-01-01 | 2023-12-31 | 2023-02-19 | 2023-02-20 | 4" MAIN/PINK PL LEAKING UNDER STAMPED CONCRETE ENTRANCE TO COUNTRY CLUB RETIRED 85' AND INSTALLED 85' OF NEW MAIN-BORING DONE BY STANELY PIPELINE, MAIN TEST 1HR @90 IB OK, TIE IN COMPLETE, 02/20/2023 HMCKUNE
23026262200 | EMER - INSTALL 4'-2" PMMP |  |  |  |  | 0.02286% | 15777.13 | 2419.7892 | 13357.3408 | 2023-01-01 | 2023-12-31 | 2023-02-20 | 2023-03-03 | INSTALLED 4' OF 2" PLASTIC MAIN. PRESSURE TESTED AT 90LBS FOR 1 HR.
23026262300 | EMER - RETIRE 4'-2" PMMP |  |  |  |  | 0.0003519% | 242.84 | 260.4446 | -17.6046 | 2023-01-01 | 2023-12-31 | 2023-02-20 | 2023-03-03 | REMOVED 4' OF DAMAGED 2" PLASTIC
23026256700 | RETIRE PAPER GAUGE |  |  |  |  | 0.001096% | 756.49 | 138.8485 | 617.6415 | 2023-01-01 | 2023-12-31 | 2023-02-21 | 2023-02-21 | CC 17512 REMOVED PAPER PRESSURE GAUGE
23026266300 | EMER-INSTALL 3' OF 2"PMMP MAIN |  |  |  |  | 0.007053% | 4867.28 | 7671.8121 | -2804.5321 | 2023-01-01 | 2023-12-31 | 2023-02-22 | 2023-02-22
23026266400 | EMER-RETIRE 3' OF 2"PMP MAIN |  |  |  |  | 0% | 0 | 124.7348 | -124.7348 | 2023-01-01 | 2023-12-31 | 2023-02-22 | 2023-02-22
23026260300 | RETIRE PAPER CHART |  |  |  |  | 0.0008184% | 564.75 | 138.8485 | 425.9015 | 2023-01-01 | 2023-12-31 | 2023-02-22 | 2023-02-22 | CC 17668
23026260200 | INSTALL ERX W/SUPER SOLAR |  |  |  |  | 0.005962% | 4114.48 | 6314.9621 | -2200.4821 | 2023-01-01 | 2023-12-31 | 2023-02-22 | 2023-02-22 | CC 17668 NOT ON SITE CAPITAL PACKET PAPERWORK NOT ONSITE. ISO UPDATES CC 21100 ANNUAL GAUGE INSP AND P2P WITH GAS CONTROL COMPLETE.
23026262700 | EMER-INSTALL 5' OF 2"PMMP MAIN |  |  |  |  | 0.005191% | 3582.24 | 7460.3676 | -3878.1276 | 2023-01-01 | 2023-12-31 | 2023-02-22 | 2023-03-07 | WORKED WITH JO. 23026262700 INSTALLED 5FT OF 020 MAIN DUE TO LEAKING S/L TEE. TESTED 5FT OF 020, 010 TEE,010 COUPLING AND 020 PURGE END CAP FOR 1HR AT 90LBS.TEST OK. SOAP TEST 020 EFC AT OP. FOR 5MINS TEST OK. BHB NGF
23026262800 | EMER-RETIRE 5' OF 2"PMP MAIN |  |  |  |  | 0.001052% | 726.04 | 124.7348 | 601.3052 | 2023-01-01 | 2023-12-31 | 2023-02-22 | 2023-03-07 | FROM MAIN TO MTR FOR 5MINS AT 90LBS.TEST OK. SOAP TEST FINAL TIE IN AT OP.TEST OK. BHB NGF WORKED WITH JO. 23026262700 INSTALLED 5FT OF 020 MAIN DUE TO LEAKING S/L TEE. TESTED 5FT OF 020, 010 TEE,010 COUPLING AND 020 PURGE END CAP FOR 1HR AT 90LBS.TEST OK. SOAP TEST 020 EFC AT OP. FOR 5MINS TEST OK. BHB NGF -- 010 S/L ELECTROFUSION TEE LEAKING AT SADDLE CONNECTION TO MAIN.REPLACED 5FT OF MAIN WITH NEW S/L TEE AND 020 PURGE END CAP.TESTED FOR 1HR AT 90LBS. TEST OK. SOAP TEST EFC COULPING AT OP. FOR 5MINS.TEST OK.TEST S/L FOR 3905
23026260500 | RETIRE PAPER CHART |  |  |  |  | 0.0008777% | 605.66 | 138.8485 | 466.8115 | 2023-01-01 | 2023-12-31 | 2023-02-23 | 2023-02-23 | CC 17834
23026260400 | INSTALL ERX W/SUPER SOLAR |  |  |  |  | 0.004982% | 3437.82 | 6314.9621 | -2877.1421 | 2023-01-01 | 2023-12-31 | 2023-02-23 | 2023-02-23 | CC 17834 NOT ON SITE. CAPITAL PACKET PAPERWORK NOT ON SITE ISO UPDATES CC 21100 ANNUAL GAUGE INSP AND P2P WITH GAS CONTROL COMPLETE
22026230301 | INSTALL 1,725'-2" PMMP |  |  |  |  | 0.9804% | 676511.46 | 636475.4754 | 40035.9846 | 2023-01-01 | 2023-12-31 | 2023-01-03 | 2023-03-17
23026268100 | RETIRE MAIN - LEAKAGE |  |  |  |  | 0% | 0 | 117.7346 | -117.7346 | 2023-01-01 | 2023-12-31 | 2023-02-27 | 2023-04-12
23026249100 | INSTALL 100'-2" PMMP |  |  |  |  | 0.01972% | 13611.51 | 7008.1595 | 6603.3505 | 2023-01-01 | 2023-12-31 | 2023-02-28 | 2023-03-03 | INSTALLED NEW MAIN ON RICHLAND CT TESTED 90 PSIG 1 HR SOAP TESTED BRANCHING TEE CAP AND PURGE POINT CAP OP 14 PSIG
23026264300 | EMER-INSTALL 5' OF 4"PMMP MAIN |  |  |  |  | 0.0003882% | 267.86 | 7456.0229 | -7188.1629 | 2023-01-01 | 2023-12-31 | 2023-02-28 | 2023-03-10 | INSTALLED 3' OF 4" PL MAIN W/ EFC AND BF DE CAP- TEST 90# FOR 20MINS PER FOL DBANKS- SOAP TEST FINALTIEIN @ OP TEST OK- BHB NGF CONTENT VERIFIED DMARSTO 3/10/23
23026264400 | EMER-RETIRE 520'- 4"PAIP MAIN |  |  |  |  | 0.0004722% | 325.83 | 124.7348 | 201.0952 | 2023-01-01 | 2023-12-31 | 2023-02-28 | 2023-03-10 | ABN 520' SECTION OF 4" PL MAIN- PURGE ABN SECTION OF MAIN W/ AIR UNTIL 0% SUSTAINED- DMARSTO 3/10/23
22026184800 | INSTALL 3775'-2" PMMP |  |  |  |  | 0.9994% | 689655.43 | 567138.2381 | 122517.1919 | 2023-01-01 | 2023-12-31 | 2023-01-20 | 2023-04-12
23026260100 | RETIRE PAPER GAUGE |  |  |  |  | 0.0003736% | 257.79 | 138.8485 | 118.9415 | 2023-01-01 | 2023-12-31 | 2023-02-28 | 2023-02-28 | CC# 18341. 2/28/23 DSASH
20026952900 | REPLACE ROOF |  |  |  |  | 0.01775% | 12246.18 | 4729 | 7517.18 | 2023-01-01 | 2023-12-31 | 2023-02-28 | 2023-02-28
23026260000 | INSTALL ERX W/SUPER SOLAR |  |  |  |  | 0.004628% | 3193.7 | 5058.9621 | -1865.2621 | 2023-01-01 | 2023-12-31 | 2023-02-28 | 2023-02-28 | CC# 18341. 2/28/23 DSASH CC# 21913. P2P OK.
23026254200 | RETIRE RECORDING GAUGE |  |  |  |  | 0.0001552% | 107.1 | 552.5683 | -445.4683 | 2023-01-01 | 2023-12-31 | 2023-03-01 | 2023-03-01 | CC 10596 RETIRE PAPER CHART SHANE G. 03012023
23026256800 | RETIRE PAPER GAUGE |  |  |  |  | 6.272e-05% | 43.28 | 138.8485 | -95.5685 | 2023-01-01 | 2023-12-31 | 2023-03-01 | 2023-03-01 | CCC# 10600 RETIRE PRESSURE CHART, JMARTIN 3-1-23
23026250700 | INSTALL EC 350 |  |  |  |  | 0.008421% | 5810.87 | 5649.3221 | 161.5479 | 2023-01-01 | 2023-12-31 | 2023-03-01 | 2023-03-01 | RETIRED CHART INSTALLED NEW EC350
23026250800 | RETIRE PAPER BILLING CHART |  |  |  |  | 0.0007654% | 528.15 | 131.2422 | 396.9078 | 2023-01-01 | 2023-12-31 | 2023-03-01 | 2023-03-01 | RETIRED PAPER CHART CCOX
23026264500 | EMER - INSTALL ~5'-4" PM/CSMP |  |  |  |  | 0.001347% | 929.35 | 2069.4953 | -1140.1453 | 2023-01-01 | 2023-12-31 | 2023-03-02 | 2023-08-25
23026264600 | EMER - RETIRE ~5'-4" CSMP |  |  |  |  | 0.0003005% | 207.34 | 67.4953 | 139.8447 | 2023-01-01 | 2023-12-31 | 2023-03-02 | 2023-08-25
23026256600 | RETIRE PAPER GAUGE |  |  |  |  | 0.0006782% | 468 | 138.8485 | 329.1515 | 2023-01-01 | 2023-12-31 | 2023-03-02 | 2023-03-02 | CHART BOXES REMOVED. G.HALE A.PARKS 03-02-23 CHARTS REMOVED AND STORED AT LEX MOD APARKS 03-02-23
23026259900 | RETIRE PAPER CHART |  |  |  |  | 0.000402% | 277.39 | 138.8485 | 138.5415 | 2023-01-01 | 2023-12-31 | 2023-03-02 | 2023-03-02 | CC# 18720. 3/2/23 DSASH CC# 18720
23026259800 | INSTALL ERX W/SUPER SOLAR |  |  |  |  | 0.005022% | 3465.31 | 5058.9621 | -1593.6521 | 2023-01-01 | 2023-12-31 | 2023-03-02 | 2023-03-02 | CC# 18720. 3/2/23 DSASH
23026266800 | EMER - INSTALL 7'-2" PMMP |  |  |  |  | 0.000779% | 537.54 | 15964.0017 | -15426.4617 | 2023-01-01 | 2023-12-31 | 2023-03-02 | 2023-04-05
23026266900 | EMER - RETIRE 7'-2" PMAP |  |  |  |  | 0% | 0 | 64.7348 | -64.7348 | 2023-01-01 | 2023-12-31 | 2023-03-02 | 2023-04-05
23026260800 | RETIRE PAPER CHART |  |  |  |  | 0.0001139% | 78.59 | 138.8485 | -60.2585 | 2023-01-01 | 2023-12-31 | 2023-03-06 | 2023-03-06 | RETIRED PAPER CHART AND IS NOW CONNECTED ER350, CMCHOLAN CCC 19108
23026260700 | INSTALL ERX W/SUPER SOLAR |  |  |  |  | 0.005757% | 3972.47 | 5629.9621 | -1657.4921 | 2023-01-01 | 2023-12-31 | 2023-03-06 | 2023-03-06 | INSTALLED SUPER SOLAR AND MEDIUM PRESSURE RUN TO ER350, WILL BE FULL TIME MONITOR WHEN BUILT IN SCADA AND WILL DO P2P THEM CCC 19108, CMCHOLAN 3-6-23 FINISHED UP PAPERWORK AND SUMMITED ISO, CCC 19108 CMCHOLAN 3-6-23 0859 CCC-27261 DID P2P WITH GAS CONTROL ON MP, GAGE INSP OK, CCC 27123 CMCHOLAN EBLANTON 4-26-23 1600
23026267000 | EMER - INSTALL 2'-2" PMLP |  |  |  |  | 0.001791% | 1235.74 | 7754.9733 | -6519.2333 | 2023-01-01 | 2023-12-31 | 2023-03-07 | 2023-04-05
23026265600 | EMER - INSTALL 4'-6" PMIP |  |  |  |  | 0.02857% | 19713.32 | 12463.1003 | 7250.2197 | 2023-01-01 | 2023-12-31 | 2023-03-06 | 2023-08-26
23026267100 | EMER - RETIRE 2'-2" PLP |  |  |  |  | 0% | 0 | 64.7348 | -64.7348 | 2023-01-01 | 2023-12-31 | 2023-03-07 | 2023-04-05
23026265700 | EMER - RETIRE 4'-6" P-IP |  |  |  |  | 0% | 0 | 391.4196 | -391.4196 | 2023-01-01 | 2023-12-31 | 2023-03-06 | 2023-08-25
23026259700 | RETIRE PAPER CHART |  |  |  |  | 0.0003909% | 269.78 | 138.8485 | 130.9315 | 2023-01-01 | 2023-12-31 | 2023-03-07 | 2023-03-07
23026259600 | INSTALL ERX AND SUPER SOLAR |  |  |  |  | 0.005293% | 3652.44 | 5600.9621 | -1948.5221 | 2023-01-01 | 2023-12-31 | 2023-03-07 | 2023-03-07
22026163200 | INSTALL 775' OF 2"PMMP MAIN |  |  |  |  | 0.07211% | 49762.97 | 80533.8181 | -30770.8481 | 2023-01-01 | 2023-12-31 | 2023-03-06 | 2023-03-17 | TWALKER/KY- 09-27-23: LEVEL 1 VARIANCE ADDED TO WMS.DOCS JOB UNDER RUN WAS DUE TO NO FLAGGING OR STREET REPAIRS REQUIRED SINCE ALL MAIN WAS INSTALLED BY DIRECTIONAL BORE WHICH LOWER CONTRACT COST $23,000
23026251300 | INSTALL EC 350 UNIT |  |  |  |  | 0.0118% | 8141.46 | 7475.3221 | 666.1379 | 2023-01-01 | 2023-12-31 | 2023-03-13 | 2023-03-13 | INSTALLED NEW EC350 TO REPLACE PAPER BILLING CHART
23026251400 | RETIRE PAPER BILLING CHART |  |  |  |  | 0.001262% | 870.82 | 131.2422 | 739.5778 | 2023-01-01 | 2023-12-31 | 2023-03-13 | 2023-03-13 | RETIRE PAPER BILLING CHART
22026230400 | RETIRE 5,578' - IP MAIN |  |  |  |  | 0.001478% | 1019.8 | 475.239 | 544.561 | 2023-01-01 | 2023-12-31 | 2023-01-03 | 2023-03-17
22026230500 | RETIRE 1,368' - MP MAIN |  |  |  |  | 2.074e-05% | 14.31 | 475.239 | -460.929 | 2023-01-01 | 2023-12-31 | 2023-01-03 | 2023-03-17
22026241900 | INSTALL 249'-2" PMIP |  |  |  |  | 0.1466% | 101153.64 | 81974.2921 | 19179.3479 | 2023-01-01 | 2023-12-31 | 2023-02-28 | 2023-03-15
22026242000 | RETIRE 135'-3" BSIP |  |  |  |  | 0.0002024% | 139.7 | 117.5985 | 22.1015 | 2023-01-01 | 2023-12-31 | 2023-02-28 | 2023-03-15
23026250200 | INSTALL EC-350 |  |  |  |  | 0.01175% | 8105.28 | 6049.3221 | 2055.9579 | 2023-01-01 | 2023-12-31 | 2023-03-14 | 2023-03-14 | INSTALLED IN HONEYWELL EC3560 IN PLACE OF CHART EBLANTON 3-14-23
23026250300 | RETIRE PAPER BILLING CHART |  |  |  |  | 0.0002683% | 185.13 | 131.2422 | 53.8878 | 2023-01-01 | 2023-12-31 | 2023-03-14 | 2023-03-14 | RETIRE PAPER BILLING CHART EBLANTON 3-14-23
23026250500 | INSTALL EC 350 |  |  |  |  | 0.009643% | 6654.67 | 7589.3221 | -934.6521 | 2023-01-01 | 2023-12-31 | 2023-03-15 | 2023-03-15 | INSTALLED NEW HONEYWELL EC350 IN PLACE OF CHART EBLANTON 3-15-2023
23026250600 | RETIRE PAPER BILLING CHART |  |  |  |  | 0.000209% | 144.2 | 131.2422 | 12.9578 | 2023-01-01 | 2023-12-31 | 2023-03-15 | 2023-03-15 | RETIRED PAPER BILLING CHART EBLANTON 3-15-23
23026251700 | INSTALL 2060' OF 2" PMMP |  |  |  |  | 0.09547% | 65881.72 | 60788.4178 | 5093.3022 | 2023-01-01 | 2023-12-31 | 2023-02-28 | 2023-03-06
21026127000 | INSTALL 8021'-2"&4" PMIP |  |  |  |  | 3.306% | 2281682.81 | 1234240.1163 | 1047442.6937 | 2023-01-01 | 2023-12-31 | 2023-01-09 | 2023-06-07 | Variance caused due to substancial increase in paving/restoration & SEGA
22026163300 | RETIRE 800' OF 4"BSLP MAIN |  |  |  |  | 3.108e-05% | 21.45 | 105.0102 | -83.5602 | 2023-01-01 | 2023-12-31 | 2023-03-06 | 2023-03-17
23026267700 | EMER-RETIRE 40' OF 6"BSLP MAIN |  |  |  |  | 0.01189% | 8203.54 | 9430.1038 | -1226.5638 | 2023-01-01 | 2023-12-31 | 2023-03-16 | 2023-03-16
22026209201 | RETIRE BUILDING FOR R-1451 |  |  |  |  | 0.00496% | 3422.43 | 4594.5704 | -1172.1404 | 2023-01-01 | 2023-12-31 | 2023-03-16 | 2023-03-16
23026250000 | INSTALL EC 350 UNIT |  |  |  |  | 0.008925% | 6158.92 | 5649.3221 | 509.5979 | 2023-01-01 | 2023-12-31 | 2023-03-16 | 2023-03-16 | INSTALLED NEW HONEYWELL EC350 INPLACE OF CHART
23026250100 | RETIRE PAPER BILLING CHART |  |  |  |  | 0.0007608% | 525.01 | 131.2422 | 393.7678 | 2023-01-01 | 2023-12-31 | 2023-03-16 | 2023-03-16 | RETIRED PAPER CHART EBLANTON 3-16-23
23026269000 | EMER-INSTALL 4' OF 2"PMMP MAIN |  |  |  |  | 0.009208% | 6353.99 | 5499.7073 | 854.2827 | 2023-01-01 | 2023-12-31 | 2023-03-17 | 2023-03-29
23026269100 | EMER-RETIRE 4' OF 2"PAMP MAIN |  |  |  |  | 0% | 0 | 117.7346 | -117.7346 | 2023-01-01 | 2023-12-31 | 2023-03-17 | 2023-03-29
23026261000 | RETIRE PAPER CHART |  |  |  |  | 0.000253% | 174.56 | 138.8485 | 35.7115 | 2023-01-01 | 2023-12-31 | 2023-03-17 | 2023-03-17 | CC 20961
23026260900 | INSTALL ERX W/SUPER SOLAR |  |  |  |  | 0.002713% | 1872.11 | 5458.9621 | -3586.8521 | 2023-01-01 | 2023-12-31 | 2023-03-17 | 2023-03-17 | CC 20969 CC 24221 P2P OK WITH GC.
22026241500 | INSTALL 40'-2" PMMP |  |  |  |  | 0.02037% | 14054.24 | 23266.5784 | -9212.3384 | 2023-01-01 | 2023-12-31 | 2023-03-22 | 2023-03-23
22026241600 | RETIRE 30'-2" PMMP |  |  |  |  | 0.00028% | 193.2 | 124.7348 | 68.4652 | 2023-01-01 | 2023-12-31 | 2023-03-22 | 2023-03-21
23026269500 | EMER - INSTALL 4'-2" PIP |  |  |  |  | 0.003937% | 2717.09 | 7943.8116 | -5226.7216 | 2023-01-01 | 2023-12-31 | 2023-03-28 | 2023-08-26
23026269600 | EMER - RETIRE 5'-2" PIP |  |  |  |  | 0% | 0 | 134.4334 | -134.4334 | 2023-01-01 | 2023-12-31 | 2023-03-28 | 2023-08-25
22026243500 | RETIRE RECORDING GAUGE |  |  |  |  | 0.0003504% | 241.8 | 96.4823 | 145.3177 | 2023-01-01 | 2023-12-31 | 2023-03-29 | 2023-03-29 | CCC#22649
22026243400 | INSTALL NEW SCADA EQUIPMENT |  |  |  |  | 0.02298% | 15857.32 | 19008.8866 | -3151.5666 | 2023-01-01 | 2023-12-31 | 2023-03-29 | 2023-03-29 | CCC#22649
23026270300 | EMER - INSTALL 2'-4" PMMP |  |  |  |  | 0.000763% | 526.5 | 9141.6411 | -8615.1411 | 2023-01-01 | 2023-12-31 | 2023-04-01 | 2023-05-25
23026270400 | EMER - RETIRE 110'-4" P-MP |  |  |  |  | 0.0007785% | 537.22 | 137.555 | 399.665 | 2023-01-01 | 2023-12-31 | 2023-04-01 | 2023-05-25 | RETIRED 110' OF 4" PL MP DUE TO BUILDING COLLAPSING TESTED CAP 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 38 PSIG
23026271200 | INSTALL LEGACY ERX |  |  |  |  | 0.003573% | 2465.58 | 2907.8819 | -442.3019 | 2023-01-01 | 2023-12-31 | 2023-04-03 | 2023-04-03 | INSTALLED LEGACY ERX IN PLACE OF OLD RTU AND TRANSMITTER EBLANTON 4-3-23
22026168000 | HVAC AND RTU PANEL UPGRADE |  |  |  |  | 0.03316% | 22883.04 | 39849.6755 | -16966.6355 | 2023-01-01 | 2023-12-31 | 2023-04-03 | 2023-04-03 | PAPER JOB COMPLETION.
23026257000 | ST JOE - RETIRE RTU |  |  |  |  | 0.0004495% | 310.19 | 138.8485 | 171.3415 | 2023-01-01 | 2023-12-31 | 2023-04-03 | 2023-04-03 | RETIRED OLD RTU EBLANTON 4-3-23
22026214500 | JIM BEAN RTU PANEL |  |  |  |  | 0.00303% | 2091.18 | 55.5311 | 2035.6489 | 2023-01-01 | 2023-12-31 | 2023-04-03 | 2023-04-03 | CCC# 15710 CCC# 15710
23026249500 | INSTALL 870'-2" PMMP |  |  |  |  | 0.0759% | 52378.28 | 67614.2583 | -15235.9783 | 2023-01-01 | 2023-12-31 | 2023-03-21 | 2023-04-04
22026240100 | GMB TO CAB CONVERSION |  |  |  |  | 0.003096% | 2136.59 | 238.427 | 1898.163 | 2023-01-01 | 2023-12-31 | 2023-04-04 | 2023-04-04 | CONVERTED GMB TO CAB ACCOUNT, CMCHOLAN 4-4-23
23026260600 | GMB TO CAB CONVERSION |  |  |  |  | 0.002035% | 1404.11 | 138.8485 | 1265.2615 | 2023-01-01 | 2023-12-31 | 2023-04-04 | 2023-04-04 | GATHER PARTS FOR CONVERSION, MTR, FLANGES, GASKETS ETC. REGULATOR GMB TO CAB CONVERSION GAS ON BYPASS DURING REBUIL;D NO BYPASS GAS USED INST ALLED NEW ROMET 3M ON 2#
22026244400 | INSTALL NEW SCADA EQUIPMENT |  |  |  |  | 0.02519% | 17382.14 | 26337.6752 | -8955.5352 | 2023-01-01 | 2023-12-31 | 2023-04-04 | 2023-04-04 | CCC# 22134 WELDED NEW TAP ON INLET FOR MIWI INSTALL, JMARTIN DMARTIN 3-27-23 CCC# 23352 INSTALL NEW MIWI 350, UNIT IS WAITING FOR A TICKET # TO BE ABLE TO PUT ONLINE. JMARTIN 4-4-23 CCC# 23905 STILL NEED TO DO P2P WITH GAS CONTROL, MODEM NOT COMMUNICATING JMARTIN 4-6-23 CCC# 24126 TRIED TO FIX COMM ISSUE WITH MODEM CCC# 23905 P2P W/GAS CONTROL OK, JMARTIN 4-10-23 CCC# 26515 COMP ANOTHER P2P WITH GAS CONTROL. JMARTIN 4-21-23 NOT ONSITE, FIXED ISO AND SUBMITTED NEW CAP FOR DRAWING.
23026264700 | INSTALL 100' OF 3"PMLP MAIN |  |  |  |  | 0.03177% | 21922.36 | 29526.7351 | -7604.3751 | 2023-01-01 | 2023-12-31 | 2023-04-04 | 2023-04-19 | 100' OF BS MAIN RETIRED AND REPLACED W/3" PE PL MAIN DUE TO CORROSION
23026264800 | RETIRE 100' OF 3"BSLP MAIN |  |  |  |  | 0.009402% | 6487.75 | 124.7348 | 6363.0152 | 2023-01-01 | 2023-12-31 | 2023-04-04 | 2023-04-19 | 100' OF BS MAIN RETIRED AND REPLACED W/3" PE PL MAIN DUE TO CORROSION
23026265400 | EMER - INSTALL 12' - 2" PMMP |  |  |  |  | 0.01371% | 9462.49 | 5370.5784 | 4091.9116 | 2023-01-01 | 2023-12-31 | 2023-04-03 | 2023-04-06 | TEST 2 IN MAIN FROM POINT A TO B TEST 90 LB FOR 20 MIN SOAP TEST TIEINS AT OP BAR HOLE BANKS NO GAS FOUND
23026265500 | EMER - RETIRE 12' - 2" PMMP |  |  |  |  | 0.0002399% | 165.55 | 124.7348 | 40.8152 | 2023-01-01 | 2023-12-31 | 2023-04-03 | 2023-04-06
23026263400 | INSTALL 40'-4" PMMP |  |  |  |  | 0.03591% | 24778.88 | 25145.0229 | -366.1429 | 2023-01-01 | 2023-12-31 | 2023-04-10 | 2023-04-11
23026271400 | EMER - INSTALL ~5'-2" PMMP |  |  |  |  | 0.01122% | 7739.82 | 5664.5366 | 2075.2834 | 2023-01-01 | 2023-12-31 | 2023-04-10 | 2023-05-09 | INSTALLED 1' OF 2" PL MP DUE TO DAMAGE TESTED 90 PSIG 1 HR SOAP TESTED FINA L CONN OP 40 PSIG
23026263500 | RETIRE 20'-4" PMMP |  |  |  |  | 0.0001421% | 98.08 | 124.7348 | -26.6548 | 2023-01-01 | 2023-12-31 | 2023-04-10 | 2023-04-11
23026271500 | EMER - RETIRE ~5'-2" PMMP |  |  |  |  | 0.001029% | 709.93 | 114.3981 | 595.5319 | 2023-01-01 | 2023-12-31 | 2023-04-10 | 2023-05-09 | RETIRED 1" OF 2" PL MP DUE TO FACILITY DAMAGE SOAP TESTED TO VERIFY SQUEEZE OFF OP 40 PSIG
23026271000 | INSTALL 70'-2" PMMP |  |  |  |  | 0.0008788% | 606.43 | 9795.9371 | -9189.5071 | 2023-01-01 | 2023-12-31 | 2023-04-09 | 2023-04-10
23026271100 | ABANDON 60'-2" PMMP |  |  |  |  | 0.006102% | 4210.59 | 262.8722 | 3947.7178 | 2023-01-01 | 2023-12-31 | 2023-04-09 | 2023-04-10
22026244500 | INSTALL NEW SCADA EQUIPMENT |  |  |  |  | 0.02599% | 17938.12 | 19488.6752 | -1550.5552 | 2023-01-01 | 2023-12-31 | 2023-04-10 | 2023-04-10 | CCC# 22091 INSTALLED NEW INLET TAP FOR MIWI, JMARTIN DMARTIN 3-27-23 NOT ONSITE DELAY DUE TO RAIN NOT ONSITE ACP RESCHEDULED CCC# 24233 INSTALLED NEW MIWI 350 CCC# 26551 WORKED WITH GC TO GET SITE ONLINE. P2P COMP. JMARTIN 4-21-23 NOT ONSITE, UPDATED ISO AND SBMITTED REDLINED DRAWIN.
22026184900 | RETIRE 3315'-2"&4"BSLP |  |  |  |  | 3.41e-05% | 23.53 | 72.7393 | -49.2093 | 2023-01-01 | 2023-12-31 | 2023-01-20 | 2023-04-12
22026243200 | INSTALL NEW SCADA EQUIPMENT |  |  |  |  | 0.0299% | 20634.93 | 25283.8866 | -4648.9566 | 2023-01-01 | 2023-12-31 | 2023-03-30 | 2023-04-11 | CCC# 21042 CC 22745 WELD AND TEST STEEL TIE TAPS INLET 240# OUTLET 90# 5MINS RHAYES DMARTIN 03-30-2023 NOT ONSITE COLLECTING PARTS FOR JOB CCC#27524
22026223700 | INSTALL 1296'-2"&4" PMMP |  |  |  |  | 0.4149% | 286331.62 | 306884.1479 | -20552.5279 | 2023-01-01 | 2023-12-31 | 2023-02-14 | 2023-04-24
22026223800 | RETIRE 1212'-2",3"&4" CSMP |  |  |  |  | 0% | 0 | 117.5985 | -117.5985 | 2023-01-01 | 2023-12-31 | 2023-02-14 | 2023-04-24
22026243300 | INSTALL NEW SCADA EQUIPMENT |  |  |  |  | 0.03043% | 20996.21 | 20719.8866 | 276.3234 | 2023-01-01 | 2023-12-31 | 2023-04-12 | 2023-04-12 | CCC# 21042 CC#23191 CC#24679 CC# 27421 CMCOX 4/27/23 1600
23026268800 | RETIRE ER350 UNIT |  |  |  |  | 0.0001683% | 116.17 | 117.7346 | -1.5646 | 2023-01-01 | 2023-12-31 | 2023-04-12 | 2023-04-12
23026268200 | INSERT 160' OF 3"PMLP MAIN |  |  |  |  | 0.01824% | 12586.85 | 20952.5602 | -8365.7102 | 2023-01-01 | 2023-12-31 | 2023-04-13 | 2023-04-14
23026268300 | RETIRE 160' OF 4"BSLP MAIN |  |  |  |  | 0.01167% | 8055.67 | 117.7346 | 7937.9354 | 2023-01-01 | 2023-12-31 | 2023-04-13 | 2023-04-13
23026246401 | INSTALL 3100' OF 2"PMMP MAIN |  |  |  |  | 0.7466% | 515222.82 | 612252.3877 | -97029.5677 | 2023-01-01 | 2023-12-31 | 2023-03-16 | 2023-05-22
23026246800 | INSTALL 800'-4" PMMP |  |  |  |  | 0.3596% | 248116.67 | 369832.3416 | -121715.6716 | 2023-01-01 | 2023-12-31 | 2023-03-20 | 2023-04-19
23026246900 | RETIRE 1000'-4" P-MP |  |  |  |  | 0% | 0 | 123.4477 | -123.4477 | 2023-01-01 | 2023-12-31 | 2023-03-20 | 2023-04-19
21026105201 | INSTALL CHAIN LINK FENCE |  |  |  |  | 0.1222% | 84349.67 | 78948.1342 | 5401.5358 | 2023-01-01 | 2023-12-31 | 2023-04-14 | 2023-04-14 | FENCE INSTALL COMPLETE APARKS 04-19-23 1600 CCC#24962
22026243600 | INSTALL NEW SCADA EQUIPMENT |  |  |  |  | 0.02725% | 18807.4 | 27565.8866 | -8758.4866 | 2023-01-01 | 2023-12-31 | 2023-04-14 | 2023-04-14 | CCC 25146 INSTALLED NEW MIWI AND SOLAR KIT, NOT COMMIONSED YET CCC 25146 INSTALLED NEW SCADA EQUMENT NOT COMSSIONED YET BUT IS UP AND RUNNING CCC-30719PREFORMED POINT TO POINT FOR NEW WIMI
22026243700 | INSTALL NEW SCADA EQUIPMENT |  |  |  |  | 0.02601% | 17949.62 | 29277.8866 | -11328.2666 | 2023-01-01 | 2023-12-31 | 2023-03-29 | 2023-04-17 | CC 22683 CC 22535 WELDED INLET TAP TESTED INLET 375# 5 MINS RHAYES DMARTIN 03-29-2023 CCC# 24078 NOT ON SITE. CAPITAL PAPERWORK CCC#25522 CWEMPE 4/17/23 COMPLETED PAPERWORK OFFSITE. CWEMPE 4/20/23 DID NOT ENTER STATION. CHARGED TIME FOR PAPERWORK. CWEMPE 4/24/23
22026243800 | INSTALL NEW SCADA EQUIPMENT |  |  |  |  | 0.02488% | 17170.68 | 32044.6752 | -14873.9952 | 2023-01-01 | 2023-12-31 | 2023-03-29 | 2023-04-18 | CC 22535 WELDED TAPS TESTED INLET 375# OUTLET 45# MINS DMARTIN RHAYES 03-29-2023 CCC# 24067 CCC#25645 CWEMPE 4/18/23 COMPLETED PAPERWORK OFFSITE. CWEMPE 4/20/23 DID NOT ENTER STATION. CHARGED TIME FOR PAPERWORK. CWEMPE 4/24/23
22026244100 | INSTALL NEW SCADA EQUIPMENT |  |  |  |  | 0.0252% | 17388.43 | 32044.6752 | -14656.2452 | 2023-01-01 | 2023-12-31 | 2023-03-29 | 2023-04-19 | CC 22622 CC 22535 WELDED TAPS TESTED INLET 375# OUTLET 90# 5 MINS RHAYES DMARTIN 03-29-2023 CCC# 24075 CALLED FOR CLEARANCE TICKET AT END OF DAY AND CCC REFUSED TO CREATE TICKET. CWEMPE 4/19/23 COMPLETED PAPERWORK OFFSITE. CWEMPE 4/20/23
22026243000 | INSTALL NEW SCADA EQUIPMENT |  |  |  |  | 0.03023% | 20860 | 29336.8866 | -8476.8866 | 2023-01-01 | 2023-12-31 | 2023-04-20 | 2023-04-20 | CC# 23362 CCC# 24092 DID NOT ENTER STATION. CWEMPE 4/27/23
23026268400 | INSTALL 2000' OF 2"PMMP MAIN |  |  |  |  | 0.08149% | 56232.52 | 83632.6185 | -27400.0985 | 2023-01-01 | 2023-12-31 | 2023-04-04 | 2023-04-21
21026115500 | INSTALL 9560' OF 2"PMMP |  |  |  |  | 2.597% | 1791950.44 | 1674772.7999 | 117177.6401 | 2023-01-01 | 2023-12-31 | 2023-01-16 | 2023-06-30
23026273500 | EMER-INSTALL 65' OF 2"PMIP |  |  |  |  | 0.008671% | 5983.61 | 8772.0552 | -2788.4452 | 2023-01-01 | 2023-12-31 | 2023-04-20 | 2023-04-21
23026273600 | EMER-RETIRE 55' OF 2"PAIP |  |  |  |  | 0.001485% | 1024.42 | 117.7346 | 906.6854 | 2023-01-01 | 2023-12-31 | 2023-04-20 | 2023-04-21
22026244300 | INSTALL NEW SCADA EQUIPMENT |  |  |  |  | 0.03086% | 21295.01 | 29761.6752 | -8466.6652 | 2023-01-01 | 2023-12-31 | 2023-04-21 | 2023-04-21 | CC 22295 TAPS WELDED TESTED INLET 375# OUTLET90# 5MIN TESTED GOOD RHAYES CCC# 24050 CCC#26526 CWEMPE 4/21/23
22026234001 | INSTALL 500' OF 2"/4"PMMP MAIN |  |  |  |  | 0.1285% | 88694.69 | 89921.6185 | -1226.9285 | 2023-01-01 | 2023-12-31 | 2023-03-28 | 2023-04-25 | INSTALLED 422' 040-PMMP 185' 020-PMMP 607' TOTAL
23026272700 | EMER - INSTALL 5'-2" PMMP |  |  |  |  | 0.003431% | 2367.44 | 5551.3568 | -3183.9168 | 2023-01-01 | 2023-12-31 | 2023-04-25 | 2023-04-25
23026272800 | EMER - RETIRE 5'-2" PMMP |  |  |  |  | 0% | 0 | 112.7299 | -112.7299 | 2023-01-01 | 2023-12-31 | 2023-04-25 | 2023-04-25
22026244200 | INSTALL NEW SCADA EQUIPMENT |  |  |  |  | 0.03034% | 20934.82 | 33186.6752 | -12251.8552 | 2023-01-01 | 2023-12-31 | 2023-04-25 | 2023-04-25 | CCC# 24912 WELDED ON PUNCH TEES FOR SCADA VISIBILITY PROJECT. TESTED TAPPED, AND MT COMPLETE. LOCKED AND PLUGGED VALVE. CCC# 26916
23026272300 | EMER-INSTALL 3" NC POLY VALVE |  |  |  |  | 0.00987% | 6810.69 | 7421.5276 | -610.8376 | 2023-01-01 | 2023-12-31 | 2023-04-28 | 2023-04-28 | REPLACED BROKEN CRITICAL VLV WITH NEW 030 POLY VLV. TEST PIPE,VLV,&CPLGS 90#1HOUR, TG. ST LTI OK. BHBNGF. R.CRAWFORD 4-28-23
23026272400 | EMER-RETIRE 3"PV C16-87 |  |  |  |  | 0.0001246% | 85.95 | 117.7346 | -31.7846 | 2023-01-01 | 2023-12-31 | 2023-04-28 | 2023-04-28 | REFER TO JOB#-23026272300 FOR COMMENTS. R.CRAWFORD 4-28-23
22026243100 | INSTALL NEW SCADA EQUIPMENT |  |  |  |  | 0.02716% | 18742.99 | 21860.8866 | -3117.8966 | 2023-01-01 | 2023-12-31 | 2023-04-26 | 2023-04-26 | CC 22894 WELDED TAPS ON COULD NOT PRESSURE TEST DUE TO TIME CONSTRAINTS PER RTWAIT CCC# 24089
22026183100 | INSTALL 3090' OF 2-4" PMMP |  |  |  |  | 0.8835% | 609662.9 | 533028.4351 | 76634.4649 | 2023-01-01 | 2023-12-31 | 2023-04-28 | 2023-09-08 | PROJECT COMPLETE
23026273200 | EMER-RETIRE 741'-1" PMP |  |  |  |  | 0.001923% | 1327.21 | 1738.6263 | -411.4163 | 2023-01-01 | 2023-12-31 | 2023-04-29 | 2023-05-24
23026263200 | GMB TO CAB CONVERSION |  |  |  |  | 0.0011% | 758.88 | 124.7348 | 634.1452 | 2023-01-01 | 2023-12-31 | 2023-05-02 | 2023-05-02 | GATHER PARTS INFO 27 - 300,000 BTU HANGING UNIT HEATERS = 8,100,000 3 - 300,000 BTU ROOF TOP UNITS = 900,000 TOTAL BTU LOAD - 9,000,000 GMB TO CAB CONVERSION
21026140501 | INSTALL 1,985'-6" CSHP |  |  |  |  | 0.2032% | 140188.39 | 116515.0569 | 23673.3331 | 2023-01-01 | 2023-12-31 | 2023-02-01 | 2023-05-19
22026228201 | INSTALL 4,225'-2"/6" PMMP |  |  |  |  | 2.805% | 1935349.38 | 1875934.718 | 59414.662 | 2023-01-01 | 2023-12-31 | 2023-01-03 | 2023-05-22
21026140600 | RETIRE 2,598'- 6" BSHP |  |  |  |  | 0.0002643% | 182.4 | 61.5191 | 120.8809 | 2023-01-01 | 2023-12-31 | 2023-02-01 | 2023-05-19
22026228400 | RETIRE 1133'- MP MAIN |  |  |  |  | 0% | 0 | 952.0929 | -952.0929 | 2023-01-01 | 2023-12-31 | 2023-02-01 | 2023-05-04
22026243900 | INSTALL NEW SCADA EQUIPMENT |  |  |  |  | 0.0197% | 13592.24 | 14352.6752 | -760.4352 | 2023-01-01 | 2023-12-31 | 2023-03-28 | 2023-05-04 | CHANGE OF PLAN, SCADA IS NOT BUILT FOR THIS SIGHT AND NOT READY TO BE CHANGED OVER, CMCHOLAN 3-28-23 INSTALL NEW MIWI, P2P OK, GAGE INSP OK, REMOVED PAPER PRESSURE CHART, PRESSURE TEST OK, CMCHOLAN 5-4-23 1358
22026244000 | RETIRE ELECTRONICS |  |  |  |  | 9.474e-05% | 65.38 | 131.2422 | -65.8622 | 2023-01-01 | 2023-12-31 | 2023-05-04 | 2023-05-04 | REMOVED ERX TO INSTALL MIWI, CCC 22274, CMCHOLAN 3-28-23
23026251500 | INSTALL 70'-2" PMLP |  |  |  |  | 0.02369% | 16349.3 | 20790.0608 | -4440.7608 | 2023-01-01 | 2023-12-31 | 2023-05-04 | 2023-05-05
23026275200 | EMER - INSTALL 3'-2" PMIP |  |  |  |  | 0.008061% | 5562.78 | 9765.5645 | -4202.7845 | 2023-01-01 | 2023-12-31 | 2023-05-04 | 2023-06-14 | INSTALLED 3' OF 2" MAIN DUE TO DAMAGE BY BORE CREW TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 5.5 PSIG
23026275300 | EMER - RETIRE 3'-2" PIP |  |  |  |  | 0.0003416% | 235.76 | 134.4334 | 101.3266 | 2023-01-01 | 2023-12-31 | 2023-05-04 | 2023-06-14 | RETIRED 3' OF 2" PL DUE TO BORE CREW HITTING MAIN TIEING CONDUIT TOGHETHER
23026272600 | INSTALL 875' OF 2"PMMP MAIN |  |  |  |  | 0.04246% | 29299.51 | 32780.4095 | -3480.8995 | 2023-01-01 | 2023-12-31 | 2023-05-03 | 2023-05-09
21026149800 | RETIRE R-1615 |  |  |  |  | 0.0008008% | 552.62 | 16113.7857 | -15561.1657 | 2023-01-01 | 2023-12-31 | 2023-02-01 | 2023-05-09
23026274800 | RETIRE REG BUILDING |  |  |  |  | 0% | 0 | 117.7346 | -117.7346 | 2023-01-01 | 2023-12-31 | 2023-02-01 | 2023-05-15
22026228300 | RETIRE 6,106'- LP MAIN |  |  |  |  | 0.0002643% | 182.4 | 952.0929 | -769.6929 | 2023-01-01 | 2023-12-31 | 2023-02-01 | 2023-05-19
23026274600 | EMER - INSTALL 5'-2" PMIP |  |  |  |  | 0.004156% | 2867.86 | 11073.0623 | -8205.2023 | 2023-01-01 | 2023-12-31 | 2023-02-01 | 2023-05-11
23026274700 | EMER - INSTALL 5'-2" PM |  |  |  |  | 0% | 0 | 116.0664 | -116.0664 | 2023-01-01 | 2023-12-31 | 2023-05-11 | 2023-05-11
23026274900 | EMER - INSTALL 4'-2" PMMP |  |  |  |  | 0.02249% | 15519.62 | 31722.4446 | -16202.8246 | 2023-01-01 | 2023-12-31 | 2023-05-11 | 2023-05-24
23026275000 | EMER - RETIRE 4'-2" PMMP |  |  |  |  | 0.003378% | 2331.35 | 139.1159 | 2192.2341 | 2023-01-01 | 2023-12-31 | 2023-05-15 | 2023-05-24
23026275900 | RETIRE BATTERY FACILITY |  |  |  |  | 0% | 0 | 139.1159 | -139.1159 | 2023-01-01 | 2023-12-31 | 2023-05-17 | 2023-05-17
23026246500 | RETIRE 2400' OF 4"BS/CSLP MAIN |  |  |  |  | 0% | 0 | 138.8485 | -138.8485 | 2023-01-01 | 2023-12-31 | 2023-03-16 | 2023-05-22
23026268700 | PM-DE LINE PH 2 DENT 2/STPL 3 |  |  |  |  | 1.019% | 703157.62 | 1307000 | -603842.38 | 2023-01-01 | 2023-12-31 | 2023-03-27 | 2023-05-23
22026175100 | INSTALL 3" OUTLET VALVE |  |  |  |  | 0.05253% | 36249.58 | 40477.7168 | -4228.1368 | 2023-01-01 | 2023-12-31 | 2023-05-19 | 2023-05-24
22026175200 | RETIRE ~10' - 3" CSHP |  |  |  |  | 0.0003728% | 257.25 | 593 | -335.75 | 2023-01-01 | 2023-12-31 | 2023-05-19 | 2023-05-24
23026275100 | RETIRE 276'-3" BSLP |  |  |  |  | 0.008577% | 5918.41 | 12701.243 | -6782.833 | 2023-01-01 | 2023-12-31 | 2023-05-23 | 2023-05-23
23026275800 | INSTALL NEW BATTERY/EQUIPMENT |  |  |  |  | 0.000197% | 135.94 | 2819.6093 | -2683.6693 | 2023-01-01 | 2023-12-31 | 2023-05-23 | 2023-05-23
23026251600 | INSTALL RTU BUILDING |  |  |  |  | 0.002913% | 2010.08 | 170.6969 | 1839.3831 | 2023-01-01 | 2023-12-31 | 2023-05-05 | 2023-05-25 | CCC#28635 WORK DONE FOR WHAT THEY ARE DOING TODAY 5-5-23 JUSTIN HOBBS CCC# 31032 CREATED OTH FACID 861369 FOR HVAC. SM 12/1/23
22026169100 | RT. 89 POD RTU BUILDING |  |  |  |  | 0.321% | 221479.78 | 143652.6755 | 77827.1045 | 2023-01-01 | 2023-12-31 | 2023-05-25 | 2023-05-25 | CCC# 13947 MONITOR NOT ONSITE ACP NOT WORKING AT THAT SITE TODAY CCC# 13947 NOT ONSITE NOT ONSITE CCC#21297 CCC# 31371
22026242600 | INSTALL 500' - 4" PMMP |  |  |  |  | 0.1681% | 115979.71 | 97718.819 | 18260.891 | 2023-01-01 | 2023-12-31 | 2023-04-28 | 2023-05-26
23026301000 | EMER-INSTALL 2' OF 4"PMMP MAIN |  |  |  |  | 0.004738% | 3269.69 | 4675.4752 | -1405.7852 | 2023-01-01 | 2023-12-31 | 2023-05-31 | 2023-05-31
23026301100 | EMER-RETIRE 2' OF 4"PAMP MAIN |  |  |  |  | 0% | 0 | 122.9261 | -122.9261 | 2023-01-01 | 2023-12-31 | 2023-05-31 | 2023-05-31
23026269400 | PM-DE LINE ILI PH2 DENT2,STPL3 |  |  |  |  | 0.2883% | 198957.22 | 216349 | -17391.78 | 2023-01-01 | 2023-12-31 | 2023-03-27 | 2023-05-31
23026265100 | INSTALL 10'-3"PMLP |  |  |  |  | 0.02282% | 15746.7 | 37610.5067 | -21863.8067 | 2023-01-01 | 2023-12-31 | 2023-05-31 | 2023-06-02 | INSTALLED 10 FT OF PL TEST FROM POINT A TO B 90 LB FOR 20 MIN TEST OK SOAP TEST 2 CPLG AND ALL BAG HOLES AT OP BHBNGF MAIN READ -0.601 INSTALLED 2 ANODES
23026265200 | RETIRE 10'-3" BSLP |  |  |  |  | 0.0002763% | 190.67 | 120.2184 | 70.4516 | 2023-01-01 | 2023-12-31 | 2023-05-31 | 2023-06-02 | RETIRED 10 FT OF 3 IN BS PIPE PURGED OUT AND SEALED THE INLINE TEE SIDE
23026277200 | EMER-RETIRE 55' OF 6"PMLP MN |  |  |  |  | 0.008044% | 5550.64 | 4206.4374 | 1344.2026 | 2023-01-01 | 2023-12-31 | 2023-06-14 | 2023-06-14 | RETIRED 52' OF 6'-P-LP WITH E/F COUPLING AND DEAD END CAP. PURGED 52' OF ' MAIN OUT OF SERVICE. SOAP TESTED FINAL CONNECTION FOR 5 MINTES AT OP. TEST OKAY.
23026255400 | GMB TO CAB CONVERSION |  |  |  |  | 0.01377% | 9499.75 | 2712.0987 | 6787.6513 | 2023-01-01 | 2023-12-31 | 2023-06-01 | 2023-06-01 | REMOVED OLD GMB FACILITIES REBUILT METER SETTING INSTALLED NEW ROMET 16M ME TER AND CL838 REGS ON 15# DELIVERY BLONE 6-1-23
22026219400 | INSTALL 380' OF 4"PMMP MAIN |  |  |  |  | 0.2488% | 171665.76 | 176409.6078 | -4743.8478 | 2023-01-01 | 2023-12-31 | 2023-05-17 | 2023-06-08
23026268600 | PM-DE LINE ILI PH2 DENT 36 |  |  |  |  | 2.317% | 1598843.54 | 1150001 | 448842.54 | 2023-01-01 | 2023-12-31 | 2023-03-27 | 2023-06-03
23026269300 | PM-DE LINE ILI PH2 DENT 36 ABD |  |  |  |  | 0.4056% | 279860.8 | 192300 | 87560.8 | 2023-01-01 | 2023-12-31 | 2023-03-27 | 2023-06-05
23026278500 | EMER - INSTALL 3'-2" PMMP |  |  |  |  | 0.004471% | 3085.38 | 4078.3783 | -992.9983 | 2023-01-01 | 2023-12-31 | 2023-06-06 | 2023-07-06
23026278600 | EMER - RETIRE 3'-2" PMMP |  |  |  |  | 1.484e-05% | 10.24 | 139.1159 | -128.8759 | 2023-01-01 | 2023-12-31 | 2023-06-06 | 2023-07-06
23026278100 | RETIRE REG FAC |  |  |  |  | 0% | 0 | 67.1159 | -67.1159 | 2023-01-01 | 2023-12-31 | 2023-06-06 | 2023-06-06 | JOB TO EXECUTE PAPERWORK ONLY RWILLIAMS 6-6-2023
21026127100 | RETIRE 9400'-2"&4" BS&CS |  |  |  |  | 0.001934% | 1334.61 | 67.799 | 1266.811 | 2023-01-01 | 2023-12-31 | 2023-01-03 | 2023-06-07
23026267800 | INSTALL 580' OF 2"PMMP MAIN |  |  |  |  | 0.05181% | 35753.76 | 40516.7801 | -4763.0201 | 2023-01-01 | 2023-12-31 | 2023-05-30 | 2023-06-08
23026277900 | EMER - INSTALL 69'-6" PMLP |  |  |  |  | 0.04545% | 31362.92 | 35367.5186 | -4004.5986 | 2023-01-01 | 2023-12-31 | 2023-06-06 | 2023-06-08 | INSTALLED 40' 060 PMP TESTED FOR 1HR AT 90LBS.TEST OK. SOAP TEST TIE INS AT OP.TEST OK. BHB NGF WORKED WITH 558
22026219500 | RETIRE 380' OF 4"BSMP MAIN |  |  |  |  | 0.0001322% | 91.2 | 89.0305 | 2.1695 | 2023-01-01 | 2023-12-31 | 2023-05-17 | 2023-06-08
23026278000 | EMER - RETIRE 69'-6" BSLP |  |  |  |  | 0.0001808% | 124.77 | 139.1159 | -14.3459 | 2023-01-01 | 2023-12-31 | 2023-06-06 | 2023-06-08 | ABDN 40' OF 6'' STEEL WORKED WITH 557.
23026273900 | INSTALL 441 REG (WEST RUN) |  |  |  |  | 0.005985% | 4130.38 | 3436.7638 | 693.6162 | 2023-01-01 | 2023-12-31 | 2023-06-08 | 2023-06-08 | (NOT ON-SITE GETTING PARTS TO COMPLETE JOB) G.HALE NOT ONSITE COLLECTING REG AND PARTS APARKS 05-18-23 1551 SWAPPED 461 REGS FOR 441 REGS 57S 1 3/4 ORFICE BROWN SPRING IN BOTH CONTROL AND MONITOR MAJOR INSP. COMPLETED ON BOTH REGS INLET@90# MON@55# CON@47# CCC# 33177 NOT ONSITE PAPER WORK ONLY APARKS 06-19-23 1000
23026274000 | RETIRE 461 REGS (WEST RUN) |  |  |  |  | 0% | 0 | 117.7346 | -117.7346 | 2023-01-01 | 2023-12-31 | 2023-06-08 | 2023-06-08
23026299900 | PAPER ONLY SL REPLACEMENT |  |  |  |  | 0.001742% | 1201.76 | 145.9261 | 1055.8339 | 2023-01-01 | 2023-12-31 | 2023-10-10 | 2023-10-10 | paper only
23026299800 | PAPER ONLY SL RETIRE |  |  |  |  | 0% | 0 | 122.9261 | -122.9261 | 2023-01-01 | 2023-12-31 | 2023-06-12 | 2023-06-12 | paper only
22026171800 | INSTALL 3178'-2" PMIP |  |  |  |  | 1.168% | 806129.21 | 663052.9501 | 143076.2599 | 2023-01-01 | 2023-12-31 | 2023-04-17 | 2023-07-20
23026278200 | EMER-INSTALL 185' OF 4"PMLP |  |  |  |  | 0.06017% | 41523.49 | 28939.243 | 12584.247 | 2023-01-01 | 2023-12-31 | 2023-06-14 | 2023-06-16
23026278300 | EMER-RETIRE 181' OF 4"BSLP MN |  |  |  |  | 0% | 0 | 139.1159 | -139.1159 | 2023-01-01 | 2023-12-31 | 2023-06-14 | 2023-06-16
23026272200 | INSTALL 200' OF 2"PMMP MAIN |  |  |  |  | 0.03973% | 27418.37 | 23237.6457 | 4180.7243 | 2023-01-01 | 2023-12-31 | 2023-06-06 | 2023-06-16
23026268500 | PM-DE LINE ILI PH 2 BEND 260 |  |  |  |  | 1.039% | 717133.15 | 1150001 | -432867.85 | 2023-01-01 | 2023-12-31 | 2023-03-23 | 2023-06-16
22026170600 | INSTALL 7,200'-2"/4" PMMP |  |  |  |  | 2.212% | 1526718.34 | 1129128.3572 | 397589.9828 | 2023-01-01 | 2023-12-31 | 2023-03-20 | 2023-09-22
23026279900 | RETIRE 38'-3" PMP |  |  |  |  | 0% | 0 | 139.1159 | -139.1159 | 2023-01-01 | 2023-12-31 | 2023-06-12 | 2023-06-26
23026278700 | INSTALL 105'-2" PMMP |  |  |  |  | 0.01188% | 8200.66 | 17148.7846 | -8948.1246 | 2023-01-01 | 2023-12-31 | 2023-06-19 | 2023-06-26 | INSTALLED 116' OF 2" PL MP TESTED 90 PSIG 0005 MIN SOAP TESTED CAPS AND DEA D HEADS OP 17 PSG
22026164201 | INSTALL 2,300'-2" PMMP |  |  |  |  | 0.7066% | 487634.39 | 442002.9907 | 45631.3993 | 2023-01-01 | 2023-12-31 | 2023-08-02 | 2023-08-03
23026281600 | EMER-INSTALL 3'-3" PMMP |  |  |  |  | 0.007293% | 5032.43 | 5640.4544 | -608.0244 | 2023-01-01 | 2023-12-31 | 2023-06-22 | 2023-07-17
23026281700 | EMER-RETIRE 3'-3" PMAP |  |  |  |  | 0% | 0 | 67.1159 | -67.1159 | 2023-01-01 | 2023-12-31 | 2023-06-22 | 2023-07-17
21026117600 | RETIRE REG STATION 1522 |  |  |  |  | 0% | 0 | 3579.3015 | -3579.3015 | 2023-01-01 | 2023-12-31 | 2023-06-22 | 2023-06-22
23026269200 | PM-DE LINE ILI PH2 BEND 260 AB |  |  |  |  | 0.2827% | 195099.48 | 192300 | 2799.48 | 2023-01-01 | 2023-12-31 | 2023-03-23 | 2023-06-23
22026236400 | INSTALL 450'-4" PMMP |  |  |  |  | 0.07638% | 52709.69 | 61251.1595 | -8541.4695 | 2023-01-01 | 2023-12-31 | 2023-06-12 | 2023-06-27
23026281200 | EMER-INSTALL 2' OF 2"PMMP MAIN |  |  |  |  | 0.009017% | 6222.18 | 5082.4374 | 1139.7426 | 2023-01-01 | 2023-12-31 | 2023-06-26 | 2023-06-26
23026281300 | EMER-RETIRE 2' OF 2"PMMP MAIN |  |  |  |  | 0% | 0 | 139.1159 | -139.1159 | 2023-01-01 | 2023-12-31 | 2023-06-26 | 2023-06-26
23026273000 | INSTALL 20'-4"PMMP W/NEW VALVE |  |  |  |  | 0.03001% | 20711.38 | 13458.2914 | 7253.0886 | 2023-01-01 | 2023-12-31 | 2023-06-23 | 2023-06-26 | LOWERED 4" MP PE MAIN,REPLACED CRITICAL VLV,TEST MAIN@90IB 1HR,TIED IN W/2 EF CPLG'S, SOAP TEST TIE IN,MOVE CV TO SOFT SURFACE 06/26/2023 HMCKUNE
23026273100 | RETIRE 20'-4"PMMP W/C19-314 |  |  |  |  | 0% | 0 | 117.7346 | -117.7346 | 2023-01-01 | 2023-12-31 | 2023-06-23 | 2023-06-26
21026999201 | RETIRE 3"PIP SERVICE LINE |  |  |  |  | 0.02137% | 14749.54 | 6359.645 | 8389.895 | 2023-01-01 | 2023-12-31 | 2023-06-26 | 2023-06-26 | STEP 3 NEEDS INVESTIGATED STEP 3 NEEDS STATE PERMIT STEP 3 NEEDS STATE PERMIT THIS IS A PAPER ABN. THIS LINE IS AN ACTIVE LINE BUT THEY ARE NOT OUR CUSTOMER. THEY ARE USING NATURAL ENERGY. OUR ASSETS ARE NOT WITHIN THE PROPERTY. U131418 J. PARKS 4-24-23
21026115600 | RETIRE 9,590' OF BSLP & OTHER |  |  |  |  | 0.0002643% | 182.4 | 67.799 | 114.601 | 2023-01-01 | 2023-12-31 | 2023-01-03 | 2023-06-30
23026282600 | EMER - RETIRE 216'-2" PAMP |  |  |  |  | 0.00733% | 5057.99 | 2153.608 | 2904.382 | 2023-01-01 | 2023-12-31 | 2023-06-27 | 2023-07-14
23026276300 | EMER-INSTALL 2"POLY VALVE |  |  |  |  | 0.009929% | 6851.84 | 10283.4841 | -3431.6441 | 2023-01-01 | 2023-12-31 | 2023-06-22 | 2023-06-27 | INSTALLED NEW CRIT.VLV. TEST VLV FOR 1 HOUR, TG. TEST 2 BYPASS, TG. TEST ALL TEES, TG. ST LTI'S, TG. ALL TIME FOR JOB# 23186718700 TO BE CHARGED BACK TO THIS JOB, R.CRAWFORD 6-23-23 REFER TO JOB# 23026276400 FOR COMMENTS. R.CRAWFORD 6-27-23
23026276400 | EMER-RETIRE 2"VALVE C14-27 |  |  |  |  | 0% | 0 | 139.1159 | -139.1159 | 2023-01-01 | 2023-12-31 | 2023-06-22 | 2023-06-27 | REFERENCE COMMENTS FOR JOB # 23026276300. R.CRAWFORD 6-23-23 REPLACED BROKEN CV. TEST NEW CV AND PIPE WITH IT 90#1HR, TG. TEST ALL TEES 9#5MINS, TG. TEST BYPASS' 90#1HOUR, TG. ST ALL FINAL TI'S, TG. R.CRAWFORD 6-27-23
23026291400 | PAPER JOB - MP RETIREMENT |  |  |  |  | 0% | 0 | 119.4953 | -119.4953 | 2023-01-01 | 2023-12-31 | 2023-06-27 | 2023-06-27
23026276900 | RETIRE 250' OF 3"BSLP MAIN |  |  |  |  | 0.002487% | 1716.17 | 4585.4374 | -2869.2674 | 2023-01-01 | 2023-12-31 | 2023-06-27 | 2023-06-27 | ABDN 252 FT OF 3 IN BS MAIN SOAP TEST 4 PAC CLAMPS AT OP FOR 5 MIN SOAP TEST END CAP AT OP FOR 5 MIN BHBNGF INSTALLED 1ANODE PURGED OUT OLD MAIN AND SEALED MAIN LEFT 36 FT LINE MARKER AT END
23026273300 | INSTALL 290' OF 4" PMMP |  |  |  |  | 0.1173% | 80935.68 | 48321.0935 | 32614.5865 | 2023-01-01 | 2023-12-31 | 2023-06-19 | 2023-06-30
23026273400 | RETIRE 283' OF 3" BSMP |  |  |  |  | 0% | 0 | 67.1159 | -67.1159 | 2023-01-01 | 2023-12-31 | 2023-06-19 | 2023-06-30
22026178900 | INSTALL 620' OF 12"CSHP MAIN |  |  |  |  | 0.3887% | 268220 | 330116.9371 | -61896.9371 | 2023-01-01 | 2023-12-31 | 2023-04-01 | 2023-06-30
22026179100 | RETIRE 520' OF 12"MJBSHP |  |  |  |  | 0.004568% | 3152.18 | 131.2422 | 3020.9378 | 2023-01-01 | 2023-12-31 | 2023-04-01 | 2023-06-30
23026258000 | RETIRE PAPER CHART |  |  |  |  | 0.0008056% | 555.95 | 121.7239 | 434.2261 | 2023-01-01 | 2023-12-31 | 2023-07-05 | 2023-07-05 | CCC# 36022 RETIRED PAPER CHART. JMARTIN JHOBBS 7-5-23 CCC# 36022
23026257900 | INSTALL MIWI AND SUPER SOLAR |  |  |  |  | 0.001917% | 1323.01 | 22482.2854 | -21159.2754 | 2023-01-01 | 2023-12-31 | 2023-07-07 | 2023-07-07 | CCC# 36022 INSTALL NEW MIWI 350. JMARTIN JHOBBS 7-5-23 CCC#36022
23026282700 | EMER-ABANDON 333' OF 2"PAMP |  |  |  |  | 0.004255% | 2936.25 | 3839.4374 | -903.1874 | 2023-01-01 | 2023-12-31 | 2023-07-06 | 2023-07-06 | ABND CUL-DE-SAC AFTER HIT LINE BY OTHER CONTRACTOR PER ENGINEER/FOL AFTER VERIFICATION NO CUSTOMERS ON GAS FOR SECTION OF MAIN TO BE ABND
23026283400 | EMER - INSTALL 5'-3" PMMP |  |  |  |  | 0.006175% | 4261.01 | 10280.7214 | -6019.7114 | 2023-01-01 | 2023-12-31 | 2023-07-10 | 2023-07-24 | INST 5'- 3" NEW PL MAIN BY ENGINEERED PLAN. MCRAIG 7/10/23
23026283500 | EMER - RETIRE 5'-3" PMP |  |  |  |  | 5.273e-05% | 36.39 | 139.1159 | -102.7259 | 2023-01-01 | 2023-12-31 | 2023-07-10 | 2023-07-24 | RETIRE 5' OF 3" PL MAIN DUE TO LEAK PER ENGINEERED PLAN. MCRAIG 7/10/23
23026261400 | RETIRE PAPER CHART |  |  |  |  | 0% | 0 | 121.7239 | -121.7239 | 2023-01-01 | 2023-12-31 | 2023-07-10 | 2023-07-10
23026261300 | INSTALL MIWI AND SUPER SOLAR |  |  |  |  | 0.007069% | 4877.76 | 26706.2854 | -21828.5254 | 2023-01-01 | 2023-12-31 | 2023-07-10 | 2023-07-10 | CC # 36552 INSTALLD MIWI NO CC NOT ONSITE--PAPER WORK
23026261600 | RETIRE PAPER CHART |  |  |  |  | 0.0005634% | 388.77 | 121.7239 | 267.0461 | 2023-01-01 | 2023-12-31 | 2023-07-11 | 2023-07-11 | CC # 36725
23026261500 | INSTALL MIWI AND SUPER SOLAR |  |  |  |  | 0.005898% | 4069.95 | 26706.2854 | -22636.3354 | 2023-01-01 | 2023-12-31 | 2023-07-11 | 2023-07-11 | CC # 36725 NO CC NEEDED---GMB ACCOUNT NOT ON SITE NO CC NEEDED---PAPERWORK OFF SITE CC # 40724
23026280800 | EMER-INSTALL 62' OF 4"PMLP |  |  |  |  | 0.09225% | 63661.35 | 28754.8748 | 34906.4752 | 2023-01-01 | 2023-12-31 | 2023-07-11 | 2023-07-12 | INSTALLE 40 FT 4 IN MAIN TEST FROM POINT A TO POINT B 90 LB FOR 1 HR TEST ALL TEES AT 90 LB FOR 5 MIN SOAP TEST EFC AND BOLTD CPLG AT O OP FOR 5 MIN SOAP TEST 1 IN END CAP AT OP FOR 5 MIN INSTALL 1 ANODE
23026284000 | EMER-INSTALL 2' OF 3"PMMP MAIN |  |  |  |  | 0.02152% | 14848.12 | 4281.828 | 10566.292 | 2023-01-01 | 2023-12-31 | 2023-07-12 | 2023-07-26
23026286000 | EMER - INSTALL 6'-2" PMMP |  |  |  |  | 0.007907% | 5456.45 | 14279.5419 | -8823.0919 | 2023-01-01 | 2023-12-31 | 2023-07-12 | 2023-08-21
23026280900 | EMER-RETIRE 62' OF 4"BSLP |  |  |  |  | 0.003132% | 2161.53 | 139.1159 | 2022.4141 | 2023-01-01 | 2023-12-31 | 2023-07-12 | 2023-07-12 | RETIRED 36 FT OF BS AND 9 FT OF PL 4 IN LOW PRESSURE MAIN
23026284100 | EMER-RETIRE 2' OF 3"PAMP MAIN |  |  |  |  | 0% | 0 | 139.1159 | -139.1159 | 2023-01-01 | 2023-12-31 | 2023-07-12 | 2023-07-26
23026286100 | EMER - RETIRE 6'-2" PMMP |  |  |  |  | 0.007789% | 5375.26 | 67.1159 | 5308.1441 | 2023-01-01 | 2023-12-31 | 2023-07-12 | 2023-08-21
23026257600 | RETIRE PAPER CHAT |  |  |  |  | 0.0008333% | 575.02 | 121.7239 | 453.2961 | 2023-01-01 | 2023-12-31 | 2023-07-12 | 2023-07-12
23026257500 | INSTALL MIWI AND SUPER SOLAR |  |  |  |  | 0.005678% | 3917.88 | 23732.2854 | -19814.4054 | 2023-01-01 | 2023-12-31 | 2023-07-12 | 2023-07-12
23026258200 | RETIRE PAPER CHART |  |  |  |  | 0% | 0 | 121.7239 | -121.7239 | 2023-01-01 | 2023-12-31 | 2023-07-13 | 2023-07-13
23026258100 | INSTALL MIWI AND SUPER SOLAR |  |  |  |  | 0.006289% | 4339.86 | 20638.2854 | -16298.4254 | 2023-01-01 | 2023-12-31 | 2023-07-13 | 2023-07-13 | CC 41992
23026284300 | EMER-INSTALL 490' OF 2"PMMP |  |  |  |  | 0.1925% | 132813.07 | 184478.0101 | -51664.9401 | 2023-01-01 | 2023-12-31 | 2023-07-14 | 2023-08-10 | BARE STEEL LP MAIN LEAKING, CREW WAS UNABLE TO EXPOSE LEAK, ABANDONED BS MAIN AND BORED IN 490'OF 2"P- PRE AND POST CAMERA COMPLETED-PT NEW MAIN 90LBS FOR 1HR PER ENGINEERING-SOAP TESTED TIE IN AT OP
23026284400 | EMER-RETIRE 520' OF 4"BSMP MN |  |  |  |  | 0.0003245% | 223.9 | 139.1159 | 84.7841 | 2023-01-01 | 2023-12-31 | 2023-07-14 | 2023-08-10 | REPLACED 493' OF 4'' S MP WITH 2'' PMP DUE TO GRADE 1 LEAK.DPI D304338.
22026171900 | RETIRE ~3325'-2" BS,CS & P |  |  |  |  | 0% | 0 | 83.4538 | -83.4538 | 2023-01-01 | 2023-12-31 | 2023-04-17 | 2023-07-20
23026259300 | RETIRE PAPER CHART |  |  |  |  | 0% | 0 | 121.7239 | -121.7239 | 2023-01-01 | 2023-12-31 | 2023-07-14 | 2023-07-14
23026259200 | INSTALL MIWI AND SUPER SOLAR |  |  |  |  | 0.005973% | 4121.74 | 21353.2854 | -17231.5454 | 2023-01-01 | 2023-12-31 | 2023-07-14 | 2023-07-14 | CC 37280
23026282000 | INSTALL 40'-4" PMIP |  |  |  |  | 0.07138% | 49257.58 | 63454.1516 | -14196.5716 | 2023-01-01 | 2023-12-31 | 2023-07-06 | 2023-07-18
23026282100 | RETIRE 36'-4" BSIP |  |  |  |  | 0.0001808% | 124.74 | 139.1159 | -14.3759 | 2023-01-01 | 2023-12-31 | 2023-07-26 | 2023-07-18
23026261800 | RETIRE PAPER CHART |  |  |  |  | 0.0009313% | 642.64 | 121.7239 | 520.9161 | 2023-01-01 | 2023-12-31 | 2023-07-17 | 2023-07-17 | CC 37443
17026706600 | CONVERT FROM GMB TO CAB ACCT |  |  |  |  | 0.02104% | 14520.06 | 1078.4716 | 13441.5884 | 2023-01-01 | 2023-12-31 | 2023-07-17 | 2023-07-17 | CCC# 36905 CCC#36905
23026261700 | INSTALL MIWI AND SUPER SOLAR |  |  |  |  | 0.005464% | 3770.68 | 21353.2854 | -17582.6054 | 2023-01-01 | 2023-12-31 | 2023-07-17 | 2023-07-17
23026259500 | RETIRE PAPER CHART |  |  |  |  | 0.000503% | 347.11 | 121.7239 | 225.3861 | 2023-01-01 | 2023-12-31 | 2023-07-18 | 2023-07-18
23026259400 | INSTALL MIWI AND SUPER SOLAR |  |  |  |  | 0.005187% | 3579.71 | 20638.2854 | -17058.5754 | 2023-01-01 | 2023-12-31 | 2023-07-18 | 2023-07-18
23026256000 | INSTALL 800'OF 2"PMMP MAIN |  |  |  |  | 0.1342% | 92592.66 | 192451.7008 | -99859.0408 | 2023-01-01 | 2023-12-31 | 2023-07-13 | 2023-07-27
23026256300 | INSTALL 130'-2" PMIP |  |  |  |  | 0.02774% | 19141.35 | 38002.449 | -18861.099 | 2023-01-01 | 2023-12-31 | 2023-07-20 | 2023-07-21
23026284800 | EMER - INSTALL 40'-4" PMLP |  |  |  |  | 0.0009144% | 630.98 | 16339.4428 | -15708.4628 | 2023-01-01 | 2023-12-31 | 2023-07-21 | 2023-07-25 | INSTALLED 34' OF 4" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 10" WC
23026284900 | EMER - RETIRE 40'-4" BSLP |  |  |  |  | 0.0006541% | 451.35 | 139.1159 | 312.2341 | 2023-01-01 | 2023-12-31 | 2023-07-21 | 2023-07-25 | RETIRED 34' OF 4" BS MAIN DUE TO LEAKAGE SOAP TESTED OP TO VERIFY SHUTDOWN SOAP TESTED OP 10" WC
23026279800 | INSTALL 1800'-2" PMMP |  |  |  |  | 0.07721% | 53278.51 | 72065.7028 | -18787.1928 | 2023-01-01 | 2023-12-31 | 2023-07-17 | 2023-07-25
23026285300 | EMER - RETIRE 159'-3"BSLP |  |  |  |  | 0.007533% | 5197.96 | 10816.0505 | -5618.0905 | 2023-01-01 | 2023-12-31 | 2023-07-24 | 2023-07-27 | ABDN 159' OF 3'' BS LP.LEAK UNDER DRIVEWAY APPRON.MAIN NOT FEEDING ANY S/L.LEFT 15' OF 3'' ACTIVE. SOAP TEST END CAP AT OP FOR 5MINS TEST OK. BHB NGF. INSTALLED ANODE DENSO WRAPPED.
23026279100 | INSTALL 300' OF 2"PMIP MAIN |  |  |  |  | 0.01123% | 7749.44 | 17364.828 | -9615.388 | 2023-01-01 | 2023-12-31 | 2023-07-26 | 2023-07-28
23026284500 | INSTALL 80'4" PMLP |  |  |  |  | 0.03423% | 23619.02 | 47424.0373 | -23805.0173 | 2023-01-01 | 2023-12-31 | 2023-07-24 | 2023-07-27 | TEST FROM POINT A TO B TO C 90 LB FOR 1 HR TEST OK TEST FINAL TIE IN AT OP OK BHBNGF INSTALLED 3 ANODES MAIN READ -0.591 TEST PAAC CLAMPS AT OP OK
23026285800 | EMER-INSTALL 3' OF 2"PMMP MAIN |  |  |  |  | 0.01301% | 8976.29 | 6991.8345 | 1984.4555 | 2023-01-01 | 2023-12-31 | 2023-07-25 | 2023-07-25
23026284600 | RETIRE 80'-4" BSLP |  |  |  |  | 0.006788% | 4684.11 | 139.1159 | 4544.9941 | 2023-01-01 | 2023-12-31 | 2023-07-24 | 2023-07-27 | RETIRED 60 FT OF BS 4IN MAIN PURGED OUT AND REMOVED PIPE
23026285900 | EMER-RETIRE 3' OF 2"PMMP MAIN |  |  |  |  | 0% | 0 | 139.1159 | -139.1159 | 2023-01-01 | 2023-12-31 | 2023-07-25 | 2023-07-25
23026278900 | INSTALL 150'-2" PMMP |  |  |  |  | 0.01471% | 10151.75 | 13769.2187 | -3617.4687 | 2023-01-01 | 2023-12-31 | 2023-07-27 | 2023-07-28
20026983500 | INSTALL 1670' - 2" PMMP |  |  |  |  | 0.6176% | 426217.2 | 347784.1168 | 78433.0832 | 2023-01-01 | 2023-12-31 | 2023-05-25 | 2023-08-28
23026289300 | INSTALL 7'-2"&6" PMLP |  |  |  |  | 0.0006487% | 447.65 | 141.4953 | 306.1547 | 2023-01-01 | 2023-12-31 | 2023-06-23 | 2023-08-28
20026983600 | ABANDON 1667'-2/3/4" PMLP/BSLP |  |  |  |  | 0.0004206% | 290.24 | 360.3823 | -70.1423 | 2023-01-01 | 2023-12-31 | 2023-05-25 | 2023-08-28
22026164300 | RETIRE 3,574'-BSLP |  |  |  |  | 0.0001982% | 136.8 | 84.9152 | 51.8848 | 2023-01-01 | 2023-12-31 | 2023-08-02 | 2023-08-03
23026288500 | EMER - INSTALL 3'-2" PMMP |  |  |  |  | 4.815e-05% | 33.23 | 15193.894 | -15160.664 | 2023-01-01 | 2023-12-31 | 2023-07-31 | 2023-08-21
23026288600 | EMER - RETIRE 3'-2" PMP |  |  |  |  | 0.006141% | 4237.6 | 119.4953 | 4118.1047 | 2023-01-01 | 2023-12-31 | 2023-07-31 | 2023-08-21
23026247700 | INSTALL NEW GMB SETTING |  |  |  |  | 0.1398% | 96486.51 | 92317.8265 | 4168.6835 | 2023-01-01 | 2023-12-31 | 2023-07-27 | 2023-08-04 | TICKET# 39340 CCC#39340 CCC#39492 08-04-2023 RHAYES CCC#39795
21026997801 | INSTALL 4600' OF 2"/6"PMMP |  |  |  |  | 3.231% | 2229938.96 | 2229421.3209 | 517.6391 | 2023-01-01 | 2023-12-31 | 2022-09-14 | 2023-10-19
23026251800 | RETIRE 900' OF 2"CSHP MAIN |  |  |  |  | 0.01836% | 12666.75 | 4095.9621 | 8570.7879 | 2023-01-01 | 2023-12-31 | 2023-08-07 | 2023-08-07
23026256400 | INSTALL 25' OF 2"PMMP MAIN |  |  |  |  | 0.01333% | 9201.52 | 8978.2187 | 223.3013 | 2023-01-01 | 2023-12-31 | 2023-08-07 | 2023-08-08 | INSTALLED 18' OF NEW MAIN AND ONE SERVICE LINE TO 1600 VILLA MEDICI TWALKER/KY 10-19-23: ISSUED BACK ORDER CANCEL 53922 FOR THE 250' COIL OF 2"PIPE WHICH IS NO LONGER AVAILABLE
22026168600 | INSTALL 13,800'-2"PMMP |  |  |  |  | 2.22% | 1531903.82 | 1751471.355 | -219567.535 | 2023-01-01 | 2023-12-31 | 2023-01-03 | 2023-09-08
22026168700 | RETIRE 12,327'-BSLP,CSLP,PLP |  |  |  |  | 0% | 0 | 89.0305 | -89.0305 | 2023-01-01 | 2023-12-31 | 2023-01-03 | 2023-09-08
23026288000 | EMER - INSTALL 5'-2" PMMP |  |  |  |  | 0.0003879% | 267.7 | 3242.0133 | -2974.3133 | 2023-01-01 | 2023-12-31 | 2023-08-09 | 2023-08-10 | RELACED 5' OF 020 PMP DUE TO SOCKET ON TEE LEAKING. TESTED 5' OF 020 FOR 1HR AT 90LBS.TEST OK. SOAP TEST 2 2'' EFC AT OP. TEST OK. BHB NGF.
23026277000 | EMER-INSTALL 15' OF 8"PMLP MN |  |  |  |  | 0.02812% | 19403.77 | 23129.0935 | -3725.3235 | 2023-01-01 | 2023-12-31 | 2023-08-08 | 2023-08-10 | INSTALLED 8 IN PL MAIN TEST FROM POINT A TO POINT B SOAP TEST ALL PAC CLAMPS AND CPLG AT OP FOR 5 MIN BHBNGF INSTALLED 2 ANODE
23026277100 | EMER-RETIRE 15' OF 8"BSLP MN |  |  |  |  | 0.0004453% | 307.27 | 139.1159 | 168.1541 | 2023-01-01 | 2023-12-31 | 2023-08-09 | 2023-08-10 | ABDN 11 FT 8 IN BS MAIN INSTALLED 11 8 IN PL MAIN TEST 90 LB FOR 1 HHR SOAP TEST FINAL TIE IN AT OP FOR 5MIN BHBNGF
23026288100 | EMER - RETIRE 5'-2" PMMP |  |  |  |  | 2.014e-06% | 1.39 | 119.4953 | -118.1053 | 2023-01-01 | 2023-12-31 | 2023-08-09 | 2023-08-10 | RELACED 5' OF 020 PMP DUE TO SOCKET ON TEE LEAKING. TESTED 5' OF 020 FOR 1HR AT 90LBS.TEST OK. SOAP TEST 2 2'' EFC AT OP. TEST OK. BHB NGF.
23026283200 | INSTALL 480' OF 2"PMMP MAIN |  |  |  |  | 0.0688% | 47476.79 | 59017.0935 | -11540.3035 | 2023-01-01 | 2023-12-31 | 2023-08-07 | 2023-08-17 | TWALKER/KY 10-20-23: REQUESTED CUSTOMER REFUND FOR THE CUSTOMER PAID RELOCA TION PROJECT.
23026288700 | INSTALL NEW RELIEF VALVE |  |  |  |  | 0.00118% | 814.62 | 3278.6711 | -2464.0511 | 2023-01-01 | 2023-12-31 | 2023-08-11 | 2023-08-11
23026288800 | RETIRE RELIEF VALVE |  |  |  |  | 0% | 0 | 119.4953 | -119.4953 | 2023-01-01 | 2023-12-31 | 2023-08-11 | 2023-08-11
23026256201 | INSTALL VRG CONTROLLERS |  |  |  |  | 0.1144% | 78966.67 | 47185.8659 | 31780.8041 | 2023-01-01 | 2023-12-31 | 2023-06-14 | #N/A | DROPPING OF MATTERIAL 06-02-23 1324 CCC# 32360 CCC#32737 CC# 33503 CCC# 33503 CCC# 39939
21026130400 | INSTALL 25,111'-2",4" PMMP |  |  |  |  | 6.312% | 4355642.45 | 3707985.656 | 647656.794 | 2023-01-01 | 2023-12-31 | 2022-08-01 | 2023-12-05
23026290100 | EMER - 3'-3" PMIP |  |  |  |  | 0.008232% | 5680.32 | 2929.2518 | 2751.0682 | 2023-01-01 | 2023-12-31 | 2023-08-15 | 2023-09-20 | INSTALLED 3' OF 2" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 5 PSIG
23026290200 | EMER-RETIRE 3'-PIP |  |  |  |  | 0.0003666% | 253 | 119.4953 | 133.5047 | 2023-01-01 | 2023-12-31 | 2023-08-15 | 2023-09-20 | CUT OUT 3' OF 2" PL DUE TO HIT MAIN SOAP TESTED TO VERIFY SHUTDOWN AFTER SQUEEZE OP
23026257300 | RETIRE CHART |  |  |  |  | 0.0005595% | 386.09 | 124.7348 | 261.3552 | 2023-01-01 | 2023-12-31 | 2023-08-15 | 2023-08-15
23026257200 | INSTALL MIWI AND SUPER SOLAR |  |  |  |  | 0.004464% | 3080.61 | 12042.2854 | -8961.6754 | 2023-01-01 | 2023-12-31 | 2023-08-12 | 2023-08-12 | CC 41028
23026257800 | RETIRE PAPER CHART |  |  |  |  | 0.001655% | 1141.91 | 121.7239 | 1020.1861 | 2023-01-01 | 2023-12-31 | 2023-08-16 | 2023-08-16
23026257700 | INSTALL MIWI AND SUPER SOLAR |  |  |  |  | 0.005147% | 3552.01 | 22126.2854 | -18574.2754 | 2023-01-01 | 2023-12-31 | 2023-08-16 | 2023-08-16
22026225400 | INSTALL APROX 180'-6" PMLP |  |  |  |  | 0.232% | 160069.05 | 120007.3465 | 40061.7035 | 2023-01-01 | 2023-12-31 | 2023-07-06 | 2023-08-21 | GURU ADDED 2'-6"PLASTIC RISER PIPE TO TD 0735002. SM 11/7/23
23026289900 | EMER-INSTALL 8'-3" PMMP |  |  |  |  | 0.004319% | 2980.18 | 1914.647 | 1065.533 | 2023-01-01 | 2023-12-31 | 2023-08-17 | 2023-09-01
22026225500 | RETIRE 200' - 6" BSLP |  |  |  |  | 0.0007401% | 510.72 | 117.7346 | 392.9854 | 2023-01-01 | 2023-12-31 | 2023-07-06 | 2023-08-21
23026290000 | EMER-RETIRE 8'-3" PAMP |  |  |  |  | 0.01309% | 9034.26 | 7157.6376 | 1876.6224 | 2023-01-01 | 2023-12-31 | 2023-08-17 | 2023-09-01
23026283300 | RETIRE 400' OF 2"BSMP MAIN |  |  |  |  | 0% | 0 | 139.1159 | -139.1159 | 2023-01-01 | 2023-12-31 | 2023-08-17 | 2023-08-17
23026288200 | INSTALL VERIZON MODEM |  |  |  |  | 0.002698% | 1861.82 | 4954.3422 | -3092.5222 | 2023-01-01 | 2023-12-31 | 2023-08-17 | 2023-08-17
23026288300 | RETIRE SATELLITE COMM EQUIP |  |  |  |  | 0% | 0 | 119.4953 | -119.4953 | 2023-01-01 | 2023-12-31 | 2023-08-17 | 2023-08-17
23026266100 | INSTALL 880'-4" PHHP |  |  |  |  | 0.1018% | 70247.34 | 60596.7317 | 9650.6083 | 2023-01-01 | 2023-12-31 | 2023-08-01 | 2023-08-18
20026976900 | INSTALL RTU & INSTRUMENTATION |  |  |  |  | 0.5248% | 362179.42 | 302143.1164 | 60036.3036 | 2023-01-01 | 2023-12-31 | 2022-11-28 | 2023-08-22 | CCC# 2490 CCC# 2490 CCC# 2490 CCC# 5078 6417 CCC# 7314 CCC# 7314 CCC# 7314 CCC# 6417 CCC# 6417 CCC# 6417 CCC# 6417 CCC# 6417
20026977000 | RETIRE RTU & INSTRUMENTATION |  |  |  |  | 0.003765% | 2598.25 | 60.3089 | 2537.9411 | 2023-01-01 | 2023-12-31 | 2022-11-28 | 2023-08-22
22026223600 | INSTALL 3000' OF 2"PMMP MAIN |  |  |  |  | 0.1171% | 80798.26 | 81410.7619 | -612.5019 | 2023-01-01 | 2023-12-31 | 2023-07-31 | 2023-08-23
22026242700 | INSTALL 350' OF 8"CSHP MAIN |  |  |  |  | 0.5532% | 381751.32 | 370158.4472 | 11592.8728 | 2023-01-01 | 2023-12-31 | 2023-07-11 | 2023-08-31
22026242800 | RETIRE 326' OF 8"CSHP MAIN |  |  |  |  | 0% | 0 | 114.3981 | -114.3981 | 2023-01-01 | 2023-12-31 | 2023-07-11 | 2023-08-31
23026254400 | INSTALL 420' OF 6"PMMP MAIN |  |  |  |  | -0.0008091% | -558.31 | 9832.3981 | -10390.7081 | 2023-01-01 | 2023-12-31 | 2023-06-30 | 2023-08-31
23026254500 | RETIRE 356' OF 6"PMMP MAIN |  |  |  |  | 0% | 0 | 114.3981 | -114.3981 | 2023-01-01 | 2023-12-31 | 2023-06-30 | 2023-08-31
22026162102 | INSTALL 8150' OF 2"/4"PMMP |  |  |  |  | 1.095% | 755714.67 | 751182.165 | 4532.505 | 2023-01-01 | 2023-12-31 | 2023-01-20 | 2023-11-30
23026277300 | INSTALL 265' OF 6"PMMP MAIN |  |  |  |  | 0.04243% | 29277.24 | 71789.4841 | -42512.2441 | 2023-01-01 | 2023-12-31 | 2023-08-17 | 2023-08-31 | JOB COMPLETED. 08312023
23026277400 | RETIRE 285' OF 6"PMMP MAIN |  |  |  |  | 0.0006371% | 439.67 | 139.1159 | 300.5541 | 2023-01-01 | 2023-12-31 | 2023-08-17 | 2023-08-31 | JOB COMPLETED
23026267600 | INSTALL 110'-4"PMLP |  |  |  |  | 0.04713% | 32525.16 | 46300.0467 | -13774.8867 | 2023-01-01 | 2023-12-31 | 2023-09-07 | 2023-09-11
23026291700 | EMER - INSTALL 3'-4" PMIP |  |  |  |  | 0.003526% | 2433.5 | 9351.5219 | -6918.0219 | 2023-01-01 | 2023-12-31 | 2023-09-07 | 2023-09-08 | INSTALLED 3' OF 4" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7 PSIG
23026291800 | EMER - RETIRE 3'-4" PIP |  |  |  |  | 0.0009938% | 685.77 | 119.4953 | 566.2747 | 2023-01-01 | 2023-12-31 | 2023-09-01 | 2023-09-08 | RETIRED 3' OF 4" PL DUE TO LEAK ON 4" SF COUPLING SOAP TESTED OP 7 PSIG TO VERIFY ADEQUATE SHUTDOWN
23026291200 | EMER - INSTALL 8'-3" PMIP |  |  |  |  | 0.074% | 51065.27 | 32593.7477 | 18471.5223 | 2023-01-01 | 2023-12-31 | 2023-09-08 | 2023-09-08 | INSTALLED 3INCH PLASTIC MAIN SECTION TO REPLACE LEAKING 3 INCH BS MAIN JCK 9.8.23
23026291300 | EMER - RETIRE 7'3" BS&P |  |  |  |  | 0.0005694% | 392.93 | 119.4953 | 273.4347 | 2023-01-01 | 2023-12-31 | 2023-09-08 | 2023-09-08 | ABANDON LEAKING METAL MAIN. INSTALLED 3 INCH PLASTIC MAIN JCK 9.8.23
23026258900 | INSTALL MIWI AND SUPER SOLAR |  |  |  |  | 0.008481% | 5852.27 | 22126.2854 | -16274.0154 | 2023-01-01 | 2023-12-31 | 2023-08-29 | 2023-09-01
23026286800 | INSTALL 100' OF 2"PMIP MAIN |  |  |  |  | 0.01993% | 13755.57 | 8938.3422 | 4817.2278 | 2023-01-01 | 2023-12-31 | 2023-08-23 | 2023-09-05 | SPOTTED UTILITIES WITH VAC TRUCK. BORED IN 100' OF 020 P MAIN, PRESSURE TEST 1 HOUR AT 90#, TG. ST LTI, TG. R.CRAWFORD 9-5-23
23026263000 | INSTALL 5875' OF 2"/4"PMMP ENV |  |  |  |  | 1.106% | 763454.52 | 728668.2681 | 34786.2519 | 2023-01-01 | 2023-12-31 | 2023-03-09 | 2023-09-12
23026263100 | RETIRE 6090' OF 4"BSMP MAIN |  |  |  |  | 0% | 0 | 124.7348 | -124.7348 | 2023-01-01 | 2023-12-31 | 2023-03-09 | 2023-09-12
22026242301 | INSTALL 8"POLY VALVE W/10"SPH |  |  |  |  | 0.1223% | 84380.42 | 63212.0666 | 21168.3534 | 2023-01-01 | 2023-12-31 | 2023-08-21 | 2023-09-07
23026280100 | RETIRE 10' OF 10"CSMP MAIN |  |  |  |  | 0.0003965% | 273.6 | 139.1159 | 134.4841 | 2023-01-01 | 2023-12-31 | 2023-08-21 | 2023-09-07
23026286300 | RETIRE 306' OF 3"BSLP MAIN |  |  |  |  | 0.007061% | 4872.41 | 7586.4374 | -2714.0274 | 2023-01-01 | 2023-12-31 | 2023-08-15 | 2023-09-05 | ABN. 40' OF PLASTIC AND 306' OF STEEL MAIN. PURGE ALL GAS OUT. PLUGGED ENDS NGF AFTER PURGED. USED EF EC, ST AT OP, TG. R.CRAWFORD 9-5-23
22026212500 | REPLACE VALVES AT R-1084 |  |  |  |  | 0.01363% | 9402.89 | 14531.0267 | -5128.1367 | 2023-01-01 | 2023-12-31 | 2023-08-21 | 2023-09-06 | HELP CCOX WITH VALVE REPLACEMENT, CMCHOLAN 9-5-23 1600 CC# 43383 PAPERWORK ONLY. NO CC# REQUIRED. NOT ON SITE.
22026212600 | RETIRE STATION VALVES R-1084 |  |  |  |  | 0.00184% | 1269.98 | 119.4953 | 1150.4847 | 2023-01-01 | 2023-12-31 | 2023-08-21 | 2023-09-06
22026183200 | RETIRE 3765' OF 2-4" CS & PMMP |  |  |  |  | 0.0003957% | 273.03 | 138.8485 | 134.1815 | 2023-01-01 | 2023-12-31 | 2023-03-16 | 2023-09-08 | PROJECT COMPLETED
23026293900 | EMER-INSTALL 3' OF 2"PMMP MAIN |  |  |  |  | 0.01036% | 7147.03 | 14157.3554 | -7010.3254 | 2023-01-01 | 2023-12-31 | 2023-09-08 | 2023-09-18
23026294000 | EMER-RETIRE 3' OF 2"PMMP MAIN |  |  |  |  | 0% | 0 | 119.4953 | -119.4953 | 2023-01-01 | 2023-12-31 | 2023-09-08 | 2023-09-18
23026266200 | INSTALL 1100'-4" PHHP |  |  |  |  | 0.1822% | 125731.21 | 81743.7317 | 43987.4783 | 2023-01-01 | 2023-12-31 | 2023-08-04 | 2023-09-12
23026274301 | INSTALL 3400' OF 2"PMMP MAIN |  |  |  |  | 0.1202% | 82979.94 | 79169.604 | 3810.336 | 2023-01-01 | 2023-12-31 | 2023-07-21 | 2023-09-14
22026170700 | RETIRE BSLP |  |  |  |  | 0% | 0 | 89.0305 | -89.0305 | 2023-01-01 | 2023-12-31 | 2023-02-14 | 2023-09-22
23026297000 | INSTALL PCF'S LP |  |  |  |  | 0.004322% | 2982.68 | 145.9261 | 2836.7539 | 2023-01-01 | 2023-12-31 | 2023-09-14 | 2023-09-14
22026205900 | RETIRE R-1682 |  |  |  |  | 0.0008752% | 603.96 | 1417.3638 | -813.4038 | 2023-01-01 | 2023-12-31 | 2023-09-14 | 2023-09-14
23026295300 | RETIRE FENCE |  |  |  |  | 0% | 0 | 119.4953 | -119.4953 | 2023-01-01 | 2023-12-31 | 2023-09-19 | 2023-09-19
22026205800 | RETIRE 20'-2" PMP |  |  |  |  | 0% | 0 | 89.0305 | -89.0305 | 2023-01-01 | 2023-12-31 | 2023-02-14 | 2023-09-18
22026182101 | INSTALL 8,450' - 2"/4" PMMP |  |  |  |  | 1.362% | 940113.78 | 861854.0803 | 78259.6997 | 2023-01-01 | 2023-12-31 | 2023-03-13 | 2023-09-19
23026257100 | INSTALL 300'-2" PMMP |  |  |  |  | 0.09938% | 68581.44 | 32921.1974 | 35660.2426 | 2023-01-01 | 2023-12-31 | 2023-09-20 | 2023-09-28 | MAINLINE EXTENSION FOR ALDI'S INSTALLED BY STANLEY PIPELINE. JOSH PASLEY 9/28/23
22026231200 | INSTALL 1870'-2"/4" PMMP |  |  |  |  | 0.1292% | 89157.03 | 71796.5181 | 17360.5119 | 2023-01-01 | 2023-12-31 | 2023-07-21 | 2023-10-04
22026172301 | INSTALL 5000' OF 2"PMMP MAIN |  |  |  |  | 1.314% | 906953.7 | 1183513.1452 | -276559.4452 | 2023-01-01 | 2023-12-31 | 2023-11-14 | 2024-04-26
23026294600 | ABANDON ~790'-2" PMMP |  |  |  |  | 0.0005686% | 392.35 | 3905.6711 | -3513.3211 | 2023-01-01 | 2023-12-31 | 2023-09-21 | 2023-10-04
23026292501 | INSTALL 800' OF 2-4" PMMP |  |  |  |  | 0.3363% | 232050.11 | 229159.9279 | 2890.1821 | 2023-01-01 | 2023-12-31 | 2023-09-14 | 2023-10-06
23026300800 | EMER-INSTALL 5' OF 3"PMLP |  |  |  |  | 0.007755% | 5351.34 | 4600.4752 | 750.8648 | 2023-01-01 | 2023-12-31 | 2023-10-10 | 2023-10-10
18026793901 | INSTALL 4,123' - 2" PMMP |  |  |  |  | 0.8745% | 603491.8 | 506341.5777 | 97150.2223 | 2023-01-01 | 2023-12-31 | 2022-06-17 | 2023-12-07
20026978100 | INSTALL 8620'- 2" PMMP |  |  |  |  | 2.463% | 1699797.2 | 1435185.1923 | 264612.0077 | 2023-01-01 | 2023-12-31 | 2022-12-21 | 2023-11-27
23026300900 | EMER-RETIRE 5' OF 3"PLP MAIN |  |  |  |  | 0% | 0 | 122.9261 | -122.9261 | 2023-01-01 | 2023-12-31 | 2023-10-10 | 2023-10-10
23026300000 | INSTALL NEW EQUIPMENT |  |  |  |  | 0.0008268% | 570.56 | 3973.8688 | -3403.3088 | 2023-01-01 | 2023-12-31 | 2024-02-05 | 2023-10-10
23026287800 | INSTALL 500'-4" PMMP |  |  |  |  | 0.2546% | 175667.6 | 99252.0533 | 76415.5467 | 2023-01-01 | 2023-12-31 | 2023-09-07 | 2023-10-23
23026287900 | RETIRE 500'-3" PMP |  |  |  |  | 0% | 0 | 119.4953 | -119.4953 | 2023-01-01 | 2023-12-31 | 2023-09-07 | 2023-10-23
23026297200 | EMER - INSTALL 13'-2" PMMP |  |  |  |  | 0.007203% | 4970.8 | 9353.5801 | -4382.7801 | 2023-01-01 | 2023-12-31 | 2023-09-29 | 2023-10-12 | VALVE RETIRED.SOAP TEST END CAPS AT OP FOR 5MINS. TEST OK.BHB NGF LEAKING 020 P CRITICAL VALVE.LEAKING FROM STEM.RETIRED VALVE WITH 020 BYPASS.TESTED BYPASS AS MAIN FOR 1HR AT 90LBS.TEST OK INSTALLED TWO END CAPS AT VALVE TO ABDN VALVE.020 BYPASS MADE TO ACVTIVE MAIN AFTER
23026297300 | EMER - RETIRE 2'-2" PMP |  |  |  |  | 0.008613% | 5943.6 | 122.9261 | 5820.6739 | 2023-01-01 | 2023-12-31 | 2023-09-29 | 2023-10-12 | VALVE RETIRED.SOAP TEST END CAPS AT OP FOR 5MINS. TEST OK.BHB NGF LEAKING 020 P CRITICAL VALVE.LEAKING FROM STEM.RETIRED VALVE WITH 020 BYPASS.TESTED BYPASS AS MAIN FOR 1HR AT 90LBS.TEST OK INSTALLED TWO END CAPS AT VALVE TO ABDN VALVE.020 BYPASS MADE TO ACVTIVE MAIN AFTER
20026974601 | INSTALL 6,500'-4"PMLP |  |  |  |  | 3.768% | 2600268.43 | 2219393.0276 | 380875.4024 | 2023-01-01 | 2023-12-31 | 2023-08-11 | 2023-10-13
23026302100 | RETIRE PAPER GAUGE |  |  |  |  | 0.0004438% | 306.23 | 989.8688 | -683.6388 | 2023-01-01 | 2023-12-31 | 2023-10-13 | 2023-10-13
23026302800 | EMER - INSTALL 2'-3" PMP |  |  |  |  | 0.005787% | 3993.16 | 3855.2637 | 137.8963 | 2023-01-01 | 2023-12-31 | 2023-10-17 | 2023-10-30
23026302900 | EMER - RETIRE 2'-3" PMP |  |  |  |  | 0% | 0 | 122.9261 | -122.9261 | 2023-01-01 | 2023-12-31 | 2023-10-17 | 2023-10-30
21026997900 | RETIRE 6300' OF 4"/6"CILP MN |  |  |  |  | 0.001083% | 747.19 | 126.9534 | 620.2366 | 2023-01-01 | 2023-12-31 | 2022-10-14 | 2023-10-19
23026290800 | INSERT/INSTALL 160'-3"PMLP MN |  |  |  |  | 0.06601% | 45549.98 | 46254.1681 | -704.1881 | 2023-01-01 | 2023-12-31 | 2023-09-25 | 2023-10-20 | TEST FROM POINT A TTO B 90 LB FOR 1 HR TEST 2 IN HV TEE AND 2 IN MAIN FROM POINT A TO B 90 LB FOR 1 HR
23026290900 | RETIRE 60' OF 3"BSLP MAIN |  |  |  |  | 0.01155% | 7967.87 | 119.4953 | 7848.3747 | 2023-01-01 | 2023-12-31 | 2023-09-25 | 2023-10-20 | ABDN 82 FT OF 4" BS MAIN AND 143 FT OF 2 " BS MAIN PURGED OUT AND SEALED UP AND INSTALLED ALL NEW 3 "PL MAIN
23026296800 | EMER - INSTALL 40'-4" PMMP |  |  |  |  | 0.06857% | 47320.11 | 32230.3112 | 15089.7988 | 2023-01-01 | 2023-12-31 | 2023-10-23 | 2023-10-31
23026296900 | EMER - RETIRE 40'-4" CSMP |  |  |  |  | 0% | 0 | 122.9261 | -122.9261 | 2023-01-01 | 2023-12-31 | 2023-10-23 | 2023-10-31
23026265300 | INSTALL PILOT REGULATORS |  |  |  |  | 0.01362% | 9398.99 | 7328.1838 | 2070.8062 | 2023-01-01 | 2023-12-31 | 2023-11-08 | #N/A
23026303700 | EMER - INSTALL 5' OF 2" PMMP |  |  |  |  | 0.0008398% | 579.53 | 147.9261 | 431.6039 | 2023-01-01 | 2023-12-31 | 2023-10-27 | 2023-11-03
23026303800 | EMER - RETIRE 3' OF 2" PAMP |  |  |  |  | 0.0001661% | 114.6 | 124.9261 | -10.3261 | 2023-01-01 | 2023-12-31 | 2023-10-27 | 2023-11-03
23026289100 | INSTALL FENCE |  |  |  |  | 0.03364% | 23214.65 | 26355.734 | -3141.084 | 2023-01-01 | 2023-12-31 | 2023-10-18 | 2023-10-30 | NOT ON SITE, OFFICE PAPERWORK
23026281400 | INSTALL 1865'-2"/4" PMMP |  |  |  |  | 0.1306% | 90143.57 | 77027.7111 | 13115.8589 | 2023-01-01 | 2023-12-31 | 2023-10-03 | 2023-11-01
22026164000 | INSTALL 5,100'-2" PMMP |  |  |  |  | 1.646% | 1135773.48 | 1140024.6985 | -4251.2185 | 2023-01-01 | 2023-12-31 | 2023-10-03 | 2024-04-10
23026302300 | RETIRE PAPER GAUGE |  |  |  |  | 0.00121% | 835.24 | 989.8688 | -154.6288 | 2023-01-01 | 2023-12-31 | 2023-10-30 | 2023-11-01 | NOT ONSITE WORK POSTPONED TILL TOMMOROW CCC# 49846
23026277600 | INSTALL 595'-2"PMMP |  |  |  |  | 0.1987% | 137119.9 | 198539.3537 | -61419.4537 | 2023-01-01 | 2023-12-31 | 2023-10-17 | 2023-11-10
23026302500 | RETIRE PAPER GAUGE |  |  |  |  | 0.001441% | 994.29 | 989.8688 | 4.4212 | 2023-01-01 | 2023-12-31 | 2023-10-30 | 2023-11-02 | CCC# 50771 MONITOR FOR TC
22026218600 | INSTALL NEW 1ST CUT REGULATOR |  |  |  |  | 0.004838% | 3338.51 | 2521.2589 | 817.2511 | 2023-01-01 | 2023-12-31 | 2023-10-31 | 2023-11-06 | NOT ONSITE NO CC NEEDED GETTING MATERIAL/BUILDING REG PREPING FOR JOB MCR CC # 51243 INSTALLD NEW 1ST CUT REG DUE TO CORROSION MCR 11-6-23 1445 CC # 51776 ISTALLD TUBING ANF PAINTED SETTIN FIELD WORK COMPLETE
22026218700 | RETIRE 1ST CUT REGULATOR |  |  |  |  | 0.002384% | 1644.86 | 84.9152 | 1559.9448 | 2023-01-01 | 2023-12-31 | 2023-10-31 | 2023-11-06 | CC # 51243 REMOVED OLD FIRST CUT REG MCR 11-6-23 1030
23026301600 | INSTAL NEW MODEM |  |  |  |  | 0.0009452% | 652.23 | 2605.8688 | -1953.6388 | 2023-01-01 | 2023-12-31 | 2023-11-06 | 2023-11-06
23026301700 | RETIRE MODEM |  |  |  |  | 0.0005292% | 365.2 | 122.9261 | 242.2739 | 2023-01-01 | 2023-12-31 | 2023-11-06 | 2023-11-06
23026277700 | RETIRE 2881'-12" BSMP |  |  |  |  | 0.0006237% | 430.39 | 139.1159 | 291.2741 | 2023-01-01 | 2023-12-31 | 2023-10-17 | 2023-11-10
22026166900 | INSTALL 2010' - 8" & 6" PMMP |  |  |  |  | 0.7609% | 525084.39 | 400337.2549 | 124747.1351 | 2023-01-01 | 2023-12-31 | 2023-09-11 | 2023-12-19
22026234901 | INSTALL 4,100'-2" PMMP |  |  |  |  | 0.3153% | 217597.98 | 188453.1623 | 29144.8177 | 2023-01-01 | 2023-12-31 | 2023-09-21 | 2023-11-20
22026213000 | RETIRE 2015'-8/4/2" BSMP/CSMP |  |  |  |  | 0.0003188% | 220 | 89.0305 | 130.9695 | 2023-01-01 | 2023-12-31 | 2023-09-11 | 2023-12-19
23026305300 | EMER-INSTALL 11'-2" PMMP |  |  |  |  | 0.007287% | 5028.51 | 17054.8912 | -12026.3812 | 2023-01-01 | 2023-12-31 | 2023-11-13 | 2023-11-13 | INSTALLED 11' NEW 2"PL MAIN DURING DAMAGE/HIT LINE FROM BANK CAVE IN INSIDE UTILITY CONTRACTORS EXCAVATION-BHB,NGF-NGF UPON DEP
23026305400 | EMER-RETIRE 11'-2" PMMP |  |  |  |  | 0.000556% | 383.65 | 124.9261 | 258.7239 | 2023-01-01 | 2023-12-31 | 2023-11-13 | 2023-11-13 | ABND 11'SECTION OF MAIN FOR DAMAGE
23026278401 | INSTALL 2300' OF 2"/4"PMMP MN |  |  |  |  | 0.1693% | 116796.05 | 101330.2336 | 15465.8164 | 2023-01-01 | 2023-12-31 | 2023-09-18 | 2023-11-16
23026296700 | INSTALL 165' OF 2" PMIP |  |  |  |  | 0.0254% | 17527.84 | 23912.4752 | -6384.6352 | 2023-01-01 | 2023-12-31 | 2023-12-28 | 2023-12-29 | INSTALLED 157' OF 2" IP MAIN TESTED 90 PSIG 1 HR SOAP TESTED PURGE POINT CAP AND SST CAP OP 7.5 PSIG
20026978200 | RETIRE 8983' LP - 2520' BS |  |  |  |  | 0.0007434% | 513.02 | 476.2758 | 36.7442 | 2023-01-01 | 2023-12-31 | 2022-12-21 | 2023-11-27
21026130500 | RETIRE 25,000' OF BSLP MAINS |  |  |  |  | 0.002523% | 1741.22 | 485.0228 | 1256.1972 | 2023-01-01 | 2023-12-31 | 2022-01-04 | 2023-12-05
21026154800 | RETIRE 35'-3" CSMP |  |  |  |  | 3.942e-05% | 27.2 | 485.0228 | -457.8228 | 2023-01-01 | 2023-12-31 | 2022-01-04 | 2023-12-05
23026306000 | EMER-INSTALL 2'-3" PMMP |  |  |  |  | 0.009133% | 6302.19 | 6158.638 | 143.552 | 2023-01-01 | 2023-12-31 | 2023-12-03 | 2023-12-04
23026306100 | EMER-RETIRE 2'-3" PMMP |  |  |  |  | 0% | 0 | 124.9261 | -124.9261 | 2023-01-01 | 2023-12-31 | 2023-12-03 | 2023-12-04
23026298400 | INSTALL MODEM AND ANTENNA |  |  |  |  | 0% | 0 | 8303.7376 | -8303.7376 | 2023-01-01 | 2023-12-31 | 2023-11-19 | 2023-11-20 | CORRECTED PAPER WORK 11-20-23 JPASLEY
23026276600 | RETIRE RTU FACILITY |  |  |  |  | 0.003416% | 2357.33 | 139.1159 | 2218.2141 | 2023-01-01 | 2023-12-31 | 2023-06-14 | 2023-11-20 | CCC#33813 PICKED UP TRASH CPRRECTED PAPER WORK JPASLEY 11-20-23
21026154600 | RETIRE R-1354 |  |  |  |  | 0.01291% | 8911.51 | 163.2711 | 8748.2389 | 2023-01-01 | 2023-12-31 | 2023-11-25 | 2023-11-26
23026307000 | RETIRE METAL BLDG |  |  |  |  | 0% | 0 | 124.9261 | -124.9261 | 2023-01-01 | 2023-12-31 | 2023-11-25 | 2023-12-01 | TWALKER/KY 12-1-23: THIS BUILDING AND REG STATION RETIRED ON 21-0261546-00.
22026162200 | RETIRE 4600' OF 4"/6"BSLP MAIN |  |  |  |  | 0.002091% | 1442.96 | 105.0102 | 1337.9498 | 2023-01-01 | 2023-12-31 | 2023-11-27 | 2023-11-30
23026306200 | INSTALL BUILDINGS R-1667 |  |  |  |  | 0% | 0 | 147.9261 | -147.9261 | 2023-01-01 | 2023-12-31 | 2023-11-27 | 2023-11-28
22026241001 | INSTALL 6375'-2"/4" PMMP ENV |  |  |  |  | 1.156% | 797679.45 | 793212.5591 | 4466.8909 | 2023-01-01 | 2023-12-31 | 2023-04-24 | 2023-11-30
23026304100 | RETIRE 667' OF 2"PMMP MAIN |  |  |  |  | 0.007144% | 4930.16 | 5490.3441 | -560.1841 | 2023-01-01 | 2023-12-31 | 2023-11-17 | 2023-11-29 | ABND MAIN ON STATE ST
23026285500 | RETIRE REG STATION #1129 |  |  |  |  | 0.02774% | 19139.56 | 22153.7376 | -3014.1776 | 2023-01-01 | 2023-12-31 | 2023-11-29 | 2023-11-30 | CCC#54039
18026794000 | RETIRE 4748'-2"/3"/4"/6"P-BSLP |  |  |  |  | 0.0001594% | 110 | 61.2976 | 48.7024 | 2023-01-01 | 2023-12-31 | 2022-06-17 | 2023-12-07
23026302200 | RETIRE PAPER GAUGE |  |  |  |  | 0.00164% | 1131.38 | 989.8688 | 141.5112 | 2023-01-01 | 2023-12-31 | 2024-02-14 | 2023-12-04
23026294800 | INSTALL 225' OF 2"PMMP MAIN |  |  |  |  | 0.04148% | 28626.52 | 19109.6064 | 9516.9136 | 2023-01-01 | 2023-12-31 | 2023-11-27 | 2023-12-05
23026307900 | EMER-INSTALL 10'-4"PMMP/VALVE |  |  |  |  | 0.01166% | 8046.73 | 6246.9893 | 1799.7407 | 2023-01-01 | 2023-12-31 | 2023-12-17 | 2023-12-18 | LEAKING MAIN VALVE.LEAK FROM STEM.REPLACED WITH NEW VALVE. TESTED 10' OF 040 WITH VALVE FOR 1HR AT 90LBS.TEST OK. SOAP TEST 2 EFC AT OP FOR 5MINS.TEST OK. BHB NGF
23026307400 | EMER-INSTALL 3' OF 2"PMMP |  |  |  |  | 0.001965% | 1356.05 | 2930.7643 | -1574.7143 | 2023-01-01 | 2023-12-31 | 2023-12-04 | 2023-12-05
23026308000 | EMER-RETIRE 10'-4"PMP/C8-150 |  |  |  |  | 0.0002132% | 147.12 | 123.4493 | 23.6707 | 2023-01-01 | 2023-12-31 | 2023-12-17 | 2023-12-18 | LEAKING MAIN VALVE.LEAK FROM STEM.REPLACED WITH NEW VALVE. TESTED 10' OF 040 WITH VALVE FOR 1HR AT 90LBS.TEST OK. SOAP TEST 2 EFC AT OP FOR 5MINS.TEST OK. BHB NGF
23026307500 | EMER-RETIRE 3' OF 2"PMP MAIN |  |  |  |  | 0% | 0 | 123.4493 | -123.4493 | 2023-01-01 | 2023-12-31 | 2023-12-04 | 2023-12-05
22026213200 | INSTALL 30' OF 2-4" PMMP S/L |  |  |  |  | 0.04841% | 33409.7 | 27880.5873 | 5529.1127 | 2023-01-01 | 2023-12-31 | 2023-12-05 | 2023-12-06
22026213100 | RETIRE 3"BSMP SERVICE LINE |  |  |  |  | 0% | 0 | 63.4096 | -63.4096 | 2023-01-01 | 2023-12-31 | 2023-12-05 | 2023-12-06
23026307700 | EMER - INSTALL 5'-2" PMMP |  |  |  |  | 0.004893% | 3376.54 | 5646.8353 | -2270.2953 | 2023-01-01 | 2023-12-31 | 2023-12-07 | 2023-12-08
23026307800 | EMER - RETIRE 5'-2" PMP |  |  |  |  | 0% | 0 | 123.4493 | -123.4493 | 2023-01-01 | 2023-12-31 | 2023-12-07 | 2023-12-08
22026167000 | RETIRE 2260' OF 4-8" BSLP |  |  |  |  | 0% | 0 | 89.0305 | -89.0305 | 2023-01-01 | 2023-12-31 | 2023-09-11 | 2023-12-19
23026296400 | INSTALL 110' OF 2"PMMP MAIN |  |  |  |  | 0.08472% | 58459.83 | 46114.2728 | 12345.5572 | 2023-01-01 | 2023-12-31 | 2023-11-14 | 2023-12-21 | CAPITAL JOB COMPLETE BY STANLEY PIPELINE AND CLEARED ASSOCIATED DPI'S. JOSH PASLEY 12/21/23
23026296500 | RETIRE 88' OF 2"CSMP MAIN |  |  |  |  | 0% | 0 | 122.9261 | -122.9261 | 2023-01-01 | 2023-12-31 | 2023-11-14 | 2023-12-21 | CAPITAL JOB COMPLETED BY STANLEY PIPELINE. CLEARED ASSOCIATED DPI'S. JOSH PASLEY 12/21/23
23026294500 | RETIRE 338' OF 4"BSLP MAIN |  |  |  |  | 0.009815% | 6772.76 | 4190.6844 | 2582.0756 | 2023-01-01 | 2023-12-31 | 2023-12-13 | 2023-12-14
23026261200 | INSTALL ULTRASONIC METER |  |  |  |  | 0.05327% | 36758.54 | 47951.5304 | -11192.9904 | 2023-01-01 | 2023-12-31 | 2024-01-29 | 2023-12-14
20026974700 | RETIRE 6,900'-BSLP,CSLP,PLP |  |  |  |  | 0.0003188% | 220 | 66.2135 | 153.7865 | 2023-01-01 | 2023-12-31 | 2023-01-20 | 2023-12-21
23026309100 | EMER-INSTALL 4'OF 2"PMMP MAIN |  |  |  |  | 0.004223% | 2913.94 | 4579.9666 | -1666.0266 | 2023-01-01 | 2023-12-31 | 2024-01-23 | 2024-01-03 | INST 4'- 2" PL MAIN. TEST MAIN @ 90LB 5MIN OK. SOAP TEST TIE-IN @ OP OK. BHB NGF. CGI MAIN AND SVC OK. WRK 12/20/23. MCRAIG 1/3/24
23026309200 | EMER-RETIRE 4' OF 3"PMP MAIN |  |  |  |  | 0.0003754% | 259.03 | 123.4493 | 135.5807 | 2023-01-01 | 2023-12-31 | 2024-01-03 | #N/A | RETIRE 4'- 2" PL MAIN DUE TO LEAKING WELD. WRK 12/20/23. MCRAIG 1/3/24
23026308900 | EMER INSTALL 4' OF 3" PMMP |  |  |  |  | 0.004291% | 2961.2 | 3360.6855 | -399.4855 | 2023-01-01 | 2023-12-31 | 2023-12-21 | 2023-12-22 | INST 4'- 3" PL MAIN PER ENGINEERED PLAN AND GAS STANDARDS. TEST NEW MAIN @ 90LB 5MIN OK. SOAP TEST TIE-IN @ OP OK. WORKED ON 12/19/23. MCRAIG 12/22/23
23026309000 | EMER RETIRE 4' OF 3" PMP |  |  |  |  | 0.0003166% | 218.46 | 123.4493 | 95.0107 | 2023-01-01 | 2023-12-31 | 2023-12-21 | 2023-12-22 | RETIRE 4' OF 3" PL MAIN DUE TO LEAK IN ACCORDNANCE W/ ENGINEERING AND GAS STANDARDS. TEST NEW 4' PL @ 90LB 5MIN OK. SOAP TEST TIE-IN. WORKED 12/19/23. MCRAIG 12/22/23
23026262601 | INSTALL CHAIN LINK FENCE |  |  |  |  | 0.1053% | 72669.9 | 39848.4833 | 32821.4167 | 2023-01-01 | 2023-12-31 | 2023-11-07 | 2023-12-29 | CC 44278 NOT ON SITE CC 53373 CC 53373 CC 57440 CC 58157
[7 empty] | 2023 Construction Project Budget | 69007000
24026329700 | EMER - 2'-2" PMMP |  |  |  |  | 0.01407% | 8583.87 | 8686.5178 | -102.6478 | 2024-01-01 | 2024-12-31 | 2024-03-14 | 2024-03-14
24026331100 | EMER - INSTALL ~5'-2" PMMP |  |  |  |  | 0.0008587% | 523.81 | 3498.146 | -2974.336 | 2024-01-01 | 2024-12-31 | 2024-02-29 | 2024-02-29
24026331900 | EMER - INSTALL 1' OF 2"PMMP |  |  |  |  | 0.005692% | 3472.1 | 3799.146 | -327.046 | 2024-01-01 | 2024-12-31 | 2024-04-02 | 2024-04-02 | REPAIRED DAMAGES SECTION OF PIPE. TEST REPAIR PIECE 90#20MINS, TG. ST LTI, TG. TEST FOR SECONDARY DAMAGE OK. R.CRAWFORD 4-2-24
24026318600 | EMER - INSTALL 11' OF 2" PMMP |  |  |  |  | 0.06884% | 41990.31 | 30688.3135 | 11301.9965 | 2024-01-01 | 2024-12-31 | 2024-02-21 | 2024-02-21 | INST 8' AND 3' SECTION OF 2" P MP MAIN DUE TO LEAK PER ENGINEERED TIE-IN PLAN. TEST NEW MAIN @ 90LB 20MIN OK. SOAP TEST TIE-IN @ OP OK
24026347300 | EMER - INSTALL 12'-3" PMIP |  |  |  |  | 0.08648% | 52750.04 | 21463.3624 | 31286.6776 | 2024-01-01 | 2024-12-31 | 2024-06-17 | 2024-06-17 | FOUND 2-3X3 PAC CLALMPS LEAKING AND 2-3" BOLTED COUPLINGS ON MAIN CUT OUT A ND REPLACED 12' OF 3" PL MAIN TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7 PSIG
24026316500 | EMER - INSTALL 15'-2" PMMP |  |  |  |  | 0% | 0 | 4538.5784 | -4538.5784 | 2024-01-01 | 2024-12-31 | 2024-02-07 | 2024-02-07
24026342000 | EMER - INSTALL 2' OF 2"PMMP |  |  |  |  | 0.01083% | 6607.96 | 4292.2109 | 2315.7491 | 2024-01-01 | 2024-12-31 | 2024-05-14 | 2024-05-14 | INST 2'- 2" P MP MAIN DUE TO DAMAGE. INST PER ENGINEERED TIE-IN PLAN. WORKED 5/2/24. SOAP TEST TIE-IN OK. MCRAIG 5/14/24
24026356500 | EMER - INSTALL 2'-2" PMIP |  |  |  |  | 0.007977% | 4865.71 | 2544.1386 | 2321.5714 | 2024-01-01 | 2024-12-31 | 2024-09-04 | 2024-09-04 | INSTALLED 2' OF 2" P DUE TO FAC DAM. TESTED 90PSIG 1HR SOAP TESTED FC AT OP 7PSIG. CWHEELE
24026351400 | EMER - INSTALL 2'-2" PMMP |  |  |  |  | 0.003027% | 1846.55 | 5752.0111 | -3905.4611 | 2024-01-01 | 2024-12-31 | 2024-07-31 | 2024-07-31 | INST 2' OF 2" PLASTIC MAIN- TSTED FOR 90LBS FOR 20MIN PER FOL TST OK- SOAP TST POINT A AND POINT B FOR 5MIN @OP TST OK- BHB NGF TROE
24026352600 | EMER - INSTALL 2'-2" PMMP |  |  |  |  | 0.003179% | 1939.02 | 3613.4082 | -1674.3882 | 2024-01-01 | 2024-12-31 | 2024-08-06 | 2024-08-06 | CONTRACTOR HIT 020 PMP WHILE DIGGING OUT SEWER BOX.SQUEEZE OFF IN BELLHOL TO MAKE SAFE.INSTALLED 3FT MAIN.TEST MAIN FOR 20MINS AT 90LBS.TEST OK.TES TEE 5MINS AT 90LBS.TEST OK.SOAP TEST EFC AT OP FOR 5MINS.TEST OK.BHB NGF
24026346100 | EMER - INSTALL 2'-2" PMMP |  |  |  |  | 0% | 0 | 9472.4549 | -9472.4549 | 2024-01-01 | 2024-12-31 | 2024-06-05 | 2024-06-05
24026335400 | EMER - INSTALL 2'-2" PMMP |  |  |  |  | 0.01241% | 7568.56 | 5032.0911 | 2536.4689 | 2024-01-01 | 2024-12-31 | 2024-03-28 | 2024-03-28
24026351600 | EMER - INSTALL 2'-2" PMMP |  |  |  |  | 0.004819% | 2939.49 | 5505.7838 | -2566.2938 | 2024-01-01 | 2024-12-31 | 2024-07-30 | 2024-07-30
24026316000 | EMER - INSTALL 2'-3" PMLP |  |  |  |  | 0.01128% | 6877.79 | 9590.2924 | -2712.5024 | 2024-01-01 | 2024-12-31 | 2024-02-13 | 2024-02-13
24026329400 | EMER - INSTALL 2'-3" PMLP |  |  |  |  | 0.01047% | 6384.11 | 4221.248 | 2162.862 | 2024-01-01 | 2024-12-31 | 2024-03-01 | 2024-03-01
24026361500 | EMER - INSTALL 2'-3" PMLP |  |  |  |  | 0.008007% | 4884.17 | 3524.9349 | 1359.2351 | 2024-01-01 | 2024-12-31 | 2024-09-27 | 2024-09-27
24026328300 | EMER - INSTALL 26'-6" PMLP |  |  |  |  | 0.02328% | 14201.79 | 28720.319 | -14518.529 | 2024-01-01 | 2024-12-31 | 2024-02-27 | 2024-02-28 | REPLACED 26FT OF 060 S WITH 060 P DUE TO ATMOS CORR. TESTED PIPE FOR 1HR AT 90LBS.TEST OK. SOAP TEST BOTH COUPLINGS AT OP FOR 5MINS.TEST OK. BHB NGF. INSTALLED 2 ANODES. DENSO WRAP MAIN.
24026349900 | EMER - INSTALL 3'-2" PMMP |  |  |  |  | 0.01316% | 8029.62 | 7024.6066 | 1005.0134 | 2024-01-01 | 2024-12-31 | 2024-07-10 | 2024-07-10
24026371800 | EMER - INSTALL 3'-2" PMMP |  |  |  |  | 0.03157% | 19259.53 | 14865.4926 | 4394.0374 | 2024-01-01 | 2024-12-31 | 2024-12-22 | 2024-12-22
24026373800 | EMER - INSTALL 3'-2" PMMP |  |  |  |  | 0.00986% | 6014.6 | 4350.0713 | 1664.5287 | 2024-01-01 | 2024-12-31 | 2024-12-22 | 2024-12-22
24026343700 | EMER - INSTALL 3'-3" PMMP |  |  |  |  | 0.01669% | 10177.86 | 6477.801 | 3700.059 | 2024-01-01 | 2024-12-31 | 2024-05-31 | 2024-05-31
24026353200 | EMER - INSTALL 3'-4" PMMP |  |  |  |  | 0.005098% | 3109.71 | 7993.6359 | -4883.9259 | 2024-01-01 | 2024-12-31 | 2024-08-01 | 2024-08-01
24026335100 | EMER - INSTALL 4'-3" PMMP |  |  |  |  | 0.02049% | 12497.25 | 9960.0387 | 2537.2113 | 2024-01-01 | 2024-12-31 | 2024-03-27 | 2024-03-27
24026330300 | EMER - INSTALL 5'- 2" PMMP |  |  |  |  | 0.01788% | 10905.49 | 11353.2418 | -447.7518 | 2024-01-01 | 2024-12-31 | 2024-04-02 | 2024-04-02 | EXPOSED TWO ISOLATED STEEL COUPLINGS ON 020 PMP MAIN. REPLACED SECTION OF MAIN WHILE ON BYPASS.TESTED BYPASS FOR 20MINS AT 90LBS.TEST OK. TESTED MAIN FOR 1HR AT 90LBS.TEST OK. SOAP TEST COUPLINGS AT OP.TEST OK.
24026336800 | EMER - INSTALL 5' OF 2" PMMP |  |  |  |  | 0.008368% | 5104.57 | 3378.146 | 1726.424 | 2024-01-01 | 2024-12-31 | 2024-03-27 | 2024-03-27
24026348700 | EMER - INSTALL 5' OF 2" PMMP |  |  |  |  | 0.01437% | 8763.23 | 5410.4082 | 3352.8218 | 2024-01-01 | 2024-12-31 | 2024-06-26 | 2024-06-26
24026317800 | EMER - INSTALL 5'-2" PMIP |  |  |  |  | 0.0137% | 8355.27 | 6092.2548 | 2263.0152 | 2024-01-01 | 2024-12-31 | 2024-02-16 | 2024-02-16 | INSTALLED NEW 020 P ML. TESTED @ 90# 1 HOUR. SOAP TEST TIE IN COUPLING. MAR KER BALL AT EOM. J HOWARD 2-16-24
24026368000 | EMER - INSTALL 5'-2" PMMP |  |  |  |  | 0.007452% | 4545.67 | 12185.6111 | -7639.9411 | 2024-01-01 | 2024-12-31 | 2024-12-09 | 2024-12-09
24026320800 | EMER - INSTALL 5'-3" PMIP |  |  |  |  | 0.0412% | 25129.82 | 6546.5769 | 18583.2431 | 2024-01-01 | 2024-12-31 | 2024-02-22 | 2024-02-22 | INSTALLED 4' OF 3" PL IP MAIN TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7 PSIG
24026338200 | EMER - INSTALL 5'-3" PMMP |  |  |  |  | 0.01969% | 12009.27 | 3698.1293 | 8311.1407 | 2024-01-01 | 2024-12-31 | 2024-03-29 | 2024-03-29
24026332800 | EMER - INSTALL 5'-4" PMIP |  |  |  |  | 0.01375% | 8388.17 | 3664.146 | 4724.024 | 2024-01-01 | 2024-12-31 | 2024-03-16 | 2024-03-16
23026309300 | EMER - INSTALL 5'-4" PMMP |  |  |  |  | 0.006489% | 3958.19 | 8753.3832 | -4795.1932 | 2024-01-01 | 2024-12-31 | 2024-03-05 | 2024-03-06 | TEST 6 FT MAIN90LB FOR 20 MIN OK TEST 3 EF TEES 90 LB FOR 5 MIN SOAP TEST 2 EFC AT OP FOR 5 MINSOAP TEST 2 END 1 IN END CAPS AT OP OK BHBNGF
24026347600 | EMER - INSTALL 7'-2" PMIP |  |  |  |  | 0.01084% | 6613.86 | 6644.7043 | -30.8443 | 2024-01-01 | 2024-12-31 | 2024-06-10 | 2024-06-10
24026332600 | EMER INSTALL 10'-6" PMMP |  |  |  |  | 0.05317% | 32430.81 | 29701.1651 | 2729.6449 | 2024-01-01 | 2024-12-31 | 2024-03-15 | 2024-03-15
24026349700 | EMER INSTALL 2' OF 2" PMMP |  |  |  |  | 0.009925% | 6054.03 | 5242.4082 | 811.6218 | 2024-01-01 | 2024-12-31 | 2024-07-03 | 2024-07-03 | SOUTHERN OHIO TRENCHING HIT MISS MARKED 2" PL MP MAIN CUT OUT 2' OF MAIN AN D INSTALLED 2' TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 40 PSIG
24026367000 | EMER INSTALL 5'-2" PMMP |  |  |  |  | 0.01297% | 7909.41 | 7419.9991 | 489.4109 | 2024-01-01 | 2024-12-31 | 2024-10-11 | 2024-10-11
24026365000 | EMER-INSTALL 10' - 2" PMMP |  |  |  |  | 0.004985% | 3040.57 | 3276.1865 | -235.6165 | 2024-01-01 | 2024-12-31 | 2024-10-30 | 2024-10-30 | INST 10' OF 2" P MP MAIN PER ENGINEERED PLAN DUE TO FAC DAMAGE. MCRAIG 10/30/24
24026314600 | EMER-INSTALL 170' OF 2"/4"PMMP |  |  |  |  | 0.2321% | 141557.61 | 145005.519 | -3447.909 | 2024-01-01 | 2024-12-31 | 2024-02-02 | 2024-02-05
24026333000 | EMER-INSTALL 18'-4"PMLP MAIN |  |  |  |  | 0.03372% | 20568.01 | 29428.3233 | -8860.3133 | 2024-01-01 | 2024-12-31 | 2024-04-30 | 2024-04-30
24026355400 | EMER-INSTALL 2' OF 2"PMMP MAIN |  |  |  |  | 0.007625% | 4651.3 | 5647.5068 | -996.2068 | 2024-01-01 | 2024-12-31 | 2024-08-28 | 2024-08-28 | SERVICE TEE AND SERVICE FOR 5MIN @90LBS TST OK- TSTED GAUGE TEES @90LBS FOR 5MIN TST OK- SOAP TST DEAD END CAPS ON GAUGE TEES FOR 5MIN @OP TST OK INST 2' OF 2" PLASTIC MAIN- TST MAIN @90LBS FOR 1HOUR, TST OK- SOAP TST FINAL TIE IN POINT A AND POINT B @OP FOR 5MIN TST OK- BHB NGFTST 2 PURGE TEES 5MIN @90LBS TST OK- TEST 2X1"
24026357700 | EMER-INSTALL 2' OF 3"PMMP MAIN |  |  |  |  | 0.02263% | 13806.96 | 15212.4136 | -1405.4536 | 2024-01-01 | 2024-12-31 | 2024-08-23 | 2024-08-23
24026350500 | EMER-INSTALL 2"VALVE KY-C1586 |  |  |  |  | 0.005381% | 3282.54 | 5722.6534 | -2440.1134 | 2024-01-01 | 2024-12-31 | 2024-07-01 | 2024-07-01
24026346300 | EMER-INSTALL 3' OF 2"PMMP MAIN |  |  |  |  | 0.009902% | 6040.26 | 8304.9467 | -2264.6867 | 2024-01-01 | 2024-12-31 | 2024-07-05 | 2024-07-05 | INSTALLED 3' 2" PL MIAIN DUE TO DAMAGE PER ENG. TIE IN PLAN
24026360200 | EMER-INSTALL 3' OF 2"PMMP MAIN |  |  |  |  | 0.02097% | 12791.75 | 12190.8831 | 600.8669 | 2024-01-01 | 2024-12-31 | 2024-09-04 | 2024-09-04 | PAPERWORK ISSUES CFD
24026362000 | EMER-INSTALL 3' OF 3"PMMP MAIN |  |  |  |  | 0.02997% | 18283.02 | 5267.5068 | 13015.5132 | 2024-01-01 | 2024-12-31 | 2024-09-17 | 2024-09-17
24026310000 | EMER-INSTALL 4' OF 2"PMIP MAIN |  |  |  |  | 0.01927% | 11757.28 | 6172.4499 | 5584.8301 | 2024-01-01 | 2024-12-31 | 2024-01-04 | 2024-01-04
24026348000 | EMER-INSTALL 4' OF 3"PMMP MAIN |  |  |  |  | 0.003825% | 2333.5 | 6161.5865 | -3828.0865 | 2024-01-01 | 2024-12-31 | 2024-07-08 | 2024-07-08 | INST 4' OF 3" PLASTIC PIPE- TSTED PIPE FOR 20MIN @90LBS PER FOL - TST OK- SOAP TST FINSL TIE IN @OP FOR 5MIN TST OK- BHB NGF- TROE
23026309100 | EMER-INSTALL 4'OF 2"PMMP MAIN |  |  |  |  | 0.00484% | 2952.18 | 4579.9666 | -1627.7866 | 2024-01-01 | 2024-12-31 | 2024-01-02 | 2024-01-03 | INST 4'- 2" PL MAIN. TEST MAIN @ 90LB 5MIN OK. SOAP TEST TIE-IN @ OP OK. BHB NGF. CGI MAIN AND SVC OK. WRK 12/20/23. MCRAIG 1/3/24
24026311800 | EMER-INSTALL 5' OF 2"PMMP MAIN |  |  |  |  | 0.004823% | 2941.72 | 5455.4783 | -2513.7583 | 2024-01-01 | 2024-12-31 | 2024-02-20 | 2024-02-20 | REPLACED 5 FT OF MAIN TEST ALL MATERIAL TO ALL GAS STANDERDS TEST MAIN 90 FOR 20 MIN TEST ALL TEES 90 FOR 5 MIN SOAP TEST EFC AND SL END CAPS AT OP FOR 5 MIN BHBNGF
24026314000 | EMER-INSTALL 5' OF 4"PMMP MAIN |  |  |  |  | 0.0008516% | 519.5 | 1932.1928 | -1412.6928 | 2024-01-01 | 2024-12-31 | 2024-02-20 | 2024-02-20
24026357000 | EMER-INSTALL 50' OF 4"PMLP |  |  |  |  | 0.03208% | 19570.62 | 21585.4343 | -2014.8143 | 2024-01-01 | 2024-12-31 | 2024-09-10 | 2024-09-10 | INSTALLED NEW 040 P PIPE DUE TO CORROSION. TEST PIPE 90#1HOUR, TG. ST LTI, TG. MAIN READIN TAKEN AT "GOOD" SECTIONS OF PIPE FOR NEW INSTALL R.CRAWFORD 9-10-24
24026375200 | EMER-INSTALL 6' OF 2"PMMP MAIN |  |  |  |  | 0.01123% | 6850.53 | 7800.6918 | -950.1618 | 2024-01-01 | 2024-12-31 | 2024-12-11 | 2024-12-11
24026344300 | EMER-INSTALL 6' OF 4" PMIP |  |  |  |  | 0.03386% | 20651.9 | 14215.6055 | 6436.2945 | 2024-01-01 | 2024-12-31 | 2024-05-28 | 2024-05-28
24026351800 | EMER-INSTALL 8' OF 3" PMMP |  |  |  |  | 0.01029% | 6274.49 | 8361.8798 | -2087.3898 | 2024-01-01 | 2024-12-31 | 2024-07-26 | 2024-07-26 | INSTALLED 8' OF NEW 030 P PIPE AFTER REMOVING DAMAGED SECTION OF MAIN. TEST PIPE 90#20MINS, TG. PER R.VANDERPOOL. R.CRAWFORD 7-26-24
24026346600 | EMER-INSTALL 8' OF 4"PMLP |  |  |  |  | 0.01066% | 6502.78 | 11094.6001 | -4591.8201 | 2024-01-01 | 2024-12-31 | 2024-08-29 | 2024-08-29 | REPLACED TWO SECTIONS OF MAIN DUE TO DAMAGES. ALL WORK PREFORMED BY GAS STANDARDS AND TESTED BY GAS STANDARDS. ALL TESTING AND CLERICAL PAPERWORK ON CAPITAL PACKET.
24026332100 | INSERT 50' OF 3" PMLP |  |  |  |  | 0.04204% | 25644.18 | 34491.8294 | -8847.6494 | 2024-01-01 | 2024-12-31 | 2024-05-13 | 2024-05-29
22026235300 | INST 1865'-8" & 390'-2" PMMP |  |  |  |  | 1.838% | 1121157.31 | 895303.7297 | 225853.5803 | 2024-01-01 | 2024-12-31 | 2024-05-08 | 2024-06-11
23026307300 | INSTALL ~100'-2" PMIP |  |  |  |  | 0.06704% | 40892.69 | 23189 | 17703.69 | 2024-01-01 | 2024-12-31 | 2024-01-01 | 2024-02-01
24026342400 | INSTALL ~585'-2" PMMP |  |  |  |  | 0.1338% | 81606.34 | 85571.2987 | -3964.9587 | 2024-01-01 | 2024-12-31 | 2024-07-08 | 2024-07-30
22026237301 | INSTALL 11,150'-8"6"4"2" PMMP |  |  |  |  | 5.209% | 3177275.55 | 2580803.0362 | 596472.5138 | 2024-01-01 | 2024-12-31 | 2024-05-06 | 2024-12-17 | ADV JTOY FOL
24026316701 | INSTALL 11245' OF 2"PMMP MAIN |  |  |  |  | 1.779% | 1084887.24 | 1012154.1196 | 72733.1204 | 2024-01-01 | 2024-12-31 | 2024-08-05 | 2024-12-12
22026236901 | INSTALL 11300'-2" PMMP |  |  |  |  | 4.306% | 2626590.92 | 2204167.7449 | 422423.1751 | 2024-01-01 | 2024-12-31 | 2024-04-01 | 2024-10-21
23026300401 | INSTALL 1150' 4/2" PMMP |  |  |  |  | 0.4783% | 291755.2 | 220213.1673 | 71542.0327 | 2024-01-01 | 2024-12-31 | 2024-04-22 | 2024-05-16 | TTOY 5/6/24: ATTEMPTED TO REVISE DUE TO UNDERRUN, MATERIAL PO NOT FILLED,
23026287300 | INSTALL 121'-4" CSMP |  |  |  |  | 0.3087% | 188332.63 | 153650.3163 | 34682.3137 | 2024-01-01 | 2024-12-31 | 2024-09-06 | 2024-09-20
22026205401 | INSTALL 1330'-4" PMMP |  |  |  |  | 0.4729% | 288486.41 | 229795.8687 | 58690.5413 | 2024-01-01 | 2024-12-31 | 2024-02-15 | 2024-03-26
22026236700 | INSTALL 134'-4" PMLP |  |  |  |  | 0.04534% | 27660 | 32463.7981 | -4803.7981 | 2024-01-01 | 2024-12-31 | 2024-02-20 | 2024-02-27 | INST 160'- 4" P LP MAIN FOR SEWER PROJECT PER ENGINEERED TIE-IN PLAN. MCRAIG 2/27/24
18026795501 | INSTALL 14,600'-2,4,6,8" PMMP |  |  |  |  | 5.617% | 3426043.78 | 3061100.231 | 364943.549 | 2024-01-01 | 2024-12-31 | 2024-04-01 | 2024-11-15
24026310800 | INSTALL 1400' OF 2" PMMP |  |  |  |  | 0.1102% | 67204.19 | 90861.9332 | -23657.7432 | 2024-01-01 | 2024-12-31 | 2024-06-17 | 2024-07-10
24026321100 | INSTALL 1400' OF 2" PMMP MAIN |  |  |  |  | 0.1118% | 68220.66 | 53956.9279 | 14263.7321 | 2024-01-01 | 2024-12-31 | 2024-04-22 | 2024-05-14
22026241701 | INSTALL 1425' OF 2"PMMP MAIN |  |  |  |  | 1.145% | 698687.73 | 729573.6534 | -30885.9234 | 2024-01-01 | 2024-12-31 | 2024-04-10 | 2024-05-08
23026296200 | INSTALL 1429'-6" PMMP |  |  |  |  | 1.598% | 975067.42 | 234311.6314 | 740755.7886 | 2024-01-01 | 2024-12-31 | 2024-06-07 | 2024-06-28 | LEVEL 2 VARIANCE EXPLANATION APPROVED AND LOCATED IN JO WORKSPACE IN WMSDOC S. D.LEMONS 9/23/2024
24026351200 | INSTALL 150' OF 2"PMIP MAIN |  |  |  |  | 0.02377% | 14499.2 | 12159.6055 | 2339.5945 | 2024-01-01 | 2024-12-31 | 2024-09-02 | 2024-09-13
24026355200 | INSTALL 150'-4" PMLP |  |  |  |  | 0.09405% | 57369.63 | 34225.265 | 23144.365 | 2024-01-01 | 2024-12-31 | 2024-12-09 | 2024-12-18
24026313000 | INSTALL 1570'-2" PMMP |  |  |  |  | 0.824% | 502657.55 | 526295.3733 | -23637.8233 | 2024-01-01 | 2024-12-31 | 2024-11-18 | 2024-12-10
22026228500 | INSTALL 167'-2" PMMP |  |  |  |  | 0.1389% | 84729.46 | 82180.2832 | 2549.1768 | 2024-01-01 | 2024-12-31 | 2024-06-13 | 2024-06-20
24026358600 | INSTALL 175' - 4" PMMP |  |  |  |  | 0.1482% | 90409.34 | 72423.4515 | 17985.8885 | 2024-01-01 | 2024-12-31 | 2024-11-18 | 2024-12-02
24026354300 | INSTALL 1750' OF 2"PMMP MAIN |  |  |  |  | 0.08184% | 49920.61 | 59204.7838 | -9284.1738 | 2024-01-01 | 2024-12-31 | 2024-11-06 | 2024-12-19
24026353800 | INSTALL 180' OF 4"PMMP MAIN |  |  |  |  | 0.2747% | 167555.7 | 169246.7693 | -1691.0693 | 2024-01-01 | 2024-12-31 | 2024-08-16 | 2024-08-30
23026300600 | INSTALL 180'-4" PMLP |  |  |  |  | 0.1274% | 77710.69 | 62129.0817 | 15581.6083 | 2024-01-01 | 2024-12-31 | 2024-01-01 | 2024-01-12
23026300300 | INSTALL 1810'-2" PMMP |  |  |  |  | 0.3562% | 217275.5 | 171679.8061 | 45595.6939 | 2024-01-01 | 2024-12-31 | 2024-10-24 | 2024-11-14
24026360500 | INSTALL 18'-2" PMMP |  |  |  |  | 0.01742% | 10627.85 | 23343.2435 | -12715.3935 | 2024-01-01 | 2024-12-31 | 2024-10-05 | 2024-10-29 | INST 35' OF 2" P MP MAIN PER ENGINEERED PLAN TO OFFSET IN 2 INTERSECTIONS FOR SEWER PROJECT. MCRAIG 10/29/24
21026145601 | INSTALL 1885' - 4" PMMP MAIN |  |  |  |  | 1.339% | 816623.03 | 712573.3764 | 104049.6536 | 2024-01-01 | 2024-12-31 | 2024-02-01 | 2024-03-18 | JOB COMPLETE
24026362300 | INSTALL 2" SS |  |  |  |  | 0% | 0 | 159.2637 | -159.2637 | 2024-01-01 | 2024-12-31 | 2024-08-09 | 2024-08-12
23026292300 | INSTALL 2" SS |  |  |  |  | 0.002119% | 1292.35 | 15645.4681 | -14353.1181 | 2024-01-01 | 2024-12-31 | 2024-01-15 | 2024-01-16 | INSTALED AND TESTED SS FITTING AT 90PSIG FOR 15 MINS
24026310600 | INSTALL 2, 2" STOPPLE FITTINGS |  |  |  |  | 0.03585% | 21866.79 | 32187.8821 | -10321.0921 | 2024-01-01 | 2024-12-31 | 2024-06-16 | 2024-06-17
24026337900 | INSTALL 2,550'-2" PMMP |  |  |  |  | 0.1359% | 82903.24 | 91900.6833 | -8997.4433 | 2024-01-01 | 2024-12-31 | 2024-03-18 | 2024-05-09
23026303400 | INSTALL 20'-2" CSHP |  |  |  |  | 0.3489% | 212847.86 | 112306.0322 | 100541.8278 | 2024-01-01 | 2024-12-31 | 2024-08-05 | 2024-08-12
24026354400 | INSTALL 20'-4" PMLP |  |  |  |  | 0.0004712% | 287.45 | 159.2637 | 128.1863 | 2024-01-01 | 2024-12-31 | 2024-08-01 | 2024-08-07
24026309500 | INSTALL 215'-2" PMMP |  |  |  |  | 0.03195% | 19486.43 | 20568.4833 | -1082.0533 | 2024-01-01 | 2024-12-31 | 2024-05-08 | 2024-05-22
22026235100 | INSTALL 2160'-2"/4" PMMP |  |  |  |  | 0.2942% | 179472.03 | 82352.5181 | 97119.5119 | 2024-01-01 | 2024-12-31 | 2024-01-01 | 2024-02-09
23026296000 | INSTALL 220' OF 2" PMMP |  |  |  |  | 0.08327% | 50792.43 | 32123.3441 | 18669.0859 | 2024-01-01 | 2024-12-31 | 2024-01-07 | 2024-01-11
22026224201 | INSTALL 2300' OF 2"/4"PMMP |  |  |  |  | 0.9652% | 588766.29 | 524527.3047 | 64238.9853 | 2024-01-01 | 2024-12-31 | 2024-08-15 | 2024-09-16
24026312200 | INSTALL 230'-2" PMMP |  |  |  |  | 0.06107% | 37251.74 | 25802.5654 | 11449.1746 | 2024-01-01 | 2024-12-31 | 2024-05-28 | 2024-06-07
23026292000 | INSTALL 2450' OF 2"PMMP MAIN |  |  |  |  | 0.1539% | 93897.7 | 75092.497 | 18805.203 | 2024-01-01 | 2024-12-31 | 2024-02-06 | 2024-02-20
24026355900 | INSTALL 250' OF 2"PMMP MAIN |  |  |  |  | 0.09231% | 56306.29 | 23765.9793 | 32540.3107 | 2024-01-01 | 2024-12-31 | 2024-10-22 | 2024-10-31 | TWALKER/KY 11-01-24: WMS WOULD NOT ALLOW JOB ORDER REVISION DUE TO UNPAID INVOICE ERROR, PROJECT PLANNED DIRECT BORE BUT CREWS HIT ROCK REASON FOR JOB COST OVER RUN.
23026272901 | INSTALL 2500' OF 2"PMMP MAIN |  |  |  |  | 0.4126% | 251654.55 | 209814.7415 | 41839.8085 | 2024-01-01 | 2024-12-31 | 2024-02-01 | 2024-03-15
24026355300 | INSTALL 250'-2" PMMP |  |  |  |  | 0.04011% | 24464.47 | 25692.6504 | -1228.1804 | 2024-01-01 | 2024-12-31 | 2023-09-11 | 2024-09-18
22026238301 | INSTALL 2505'-4" PHHP |  |  |  |  | 0.4874% | 297291.9 | 265393.3206 | 31898.5794 | 2024-01-01 | 2024-12-31 | 2023-11-15 | 2024-01-08
24026343500 | INSTALL 25'-8" PMLP |  |  |  |  | 0.07945% | 48462.2 | 72915.1812 | -24452.9812 | 2024-01-01 | 2024-12-31 | 2024-06-03 | 2024-06-10
23026302701 | INSTALL 2700' OF 2"/4"PMMP |  |  |  |  | 0.4726% | 288308.66 | 294198.9734 | -5890.3134 | 2024-01-01 | 2024-12-31 | 2024-05-22 | 2024-06-12
24026317300 | INSTALL 270'-2" PMMP |  |  |  |  | 0.05378% | 32804.09 | 44548.0974 | -11744.0074 | 2024-01-01 | 2024-12-31 | 2024-03-25 | 2024-04-08
22026171100 | INSTALL 2715' OF 2"/4"PMMP |  |  |  |  | 1.204% | 734298.53 | 852559.9514 | -118261.4214 | 2024-01-01 | 2024-12-31 | 2024-04-20 | 2024-05-23 | TWALKER/KY 08-16-24: FINAL PAVING RESTORATION FOR THIS PROJECT WILL NOT HAPPEN UNTIL 2025 DUE TO PLANNED WATER COMPANY PROJECT ON SAME STREETS AND CITY OF LEXINGTON SHARED PAVING REQUIREMENTS
24026357400 | INSTALL 275'-3" CSMP |  |  |  |  | 0.1713% | 104472.75 | 87056.0137 | 17416.7363 | 2024-01-01 | 2024-12-31 | 2024-10-07 | 2024-10-24
24026331500 | INSTALL 300' OF 2"PMMP MAIN |  |  |  |  | 0.06584% | 40161.78 | 28768.72 | 11393.06 | 2024-01-01 | 2024-12-31 | 2024-04-10 | 2024-04-24
24026337600 | INSTALL 30'-2" PMMP |  |  |  |  | 0.0455% | 27755.6 | 27915.2109 | -159.6109 | 2024-01-01 | 2024-12-31 | 2024-05-17 | 2024-05-23
23026287600 | INSTALL 30'-4" PMMP |  |  |  |  | 0.03236% | 19740.37 | 14529.6064 | 5210.7636 | 2024-01-01 | 2024-12-31 | 2024-06-17 | 2024-06-20
24026365700 | INSTALL 320' OF 2"PMIP MAIN |  |  |  |  | 0.04878% | 29754.73 | 31921.5843 | -2166.8543 | 2024-01-01 | 2024-12-31 | 2024-12-02 | 2024-12-18
23026299700 | INSTALL 325' OF 2"PMMP MAIN |  |  |  |  | 0.08592% | 52412.36 | 30286.964 | 22125.396 | 2024-01-01 | 2024-12-31 | 2024-03-07 | 2024-03-14 | TWALKER/KY 03-22-24: JOB OVER RUN DUE TO UNKNOWN CROSS BORE DISCOVERED AT TIE IN POINT FOR THIS PROJECT, CREWS HAD TO CORRECT THAT ISSUE WHICH ADDED ADDITIONAL TIME/MONEY FOR CONTRACTOR AND CONS COORDINATOR
22026165501 | INSTALL 3385' OF 2" PMMP |  |  |  |  | 0.5704% | 347952.13 | 345650.6876 | 2301.4424 | 2024-01-01 | 2024-12-31 | 2024-08-15 | 2024-09-13
23026279500 | INSTALL 339'-8" PMLP |  |  |  |  | 0.1812% | 110539.26 | 126473.6122 | -15934.3522 | 2024-01-01 | 2024-12-31 | 2024-04-29 | 2024-05-10 | INSTALLED 218' OF 8" PLASTIC TESTED 105 PSIG 4 HOURS SOAP TESTED FINAL CONN OP 10" WC
24026339800 | INSTALL 35' OF 6"PMLP MAIN |  |  |  |  | 0.07167% | 43718.9 | 45030.1866 | -1311.2866 | 2024-01-01 | 2024-12-31 | 2024-07-29 | 2024-08-06 | REPLACED 56' OF 060 P LP DUE TO CROSS BORE IN SEWER. TESTED MAIN FOR 1HR AT 90LBS.TEST OK. TESTED TEMP BYPASS FOR 20MINS AT 90LBS.TESTS OK. SOAP TEST BOLTED COUPLINGS AT OP.TEST OK.SOAP TEST CLAPS AND SADDLES AT OP.TEST OK
24026311700 | INSTALL 360' OF 2"PMMP MAIN |  |  |  |  | 0.06281% | 38311.55 | 32438.7712 | 5872.7788 | 2024-01-01 | 2024-12-31 | 2024-03-01 | 2024-03-04
23026292201 | INSTALL 360'-4" PMMP |  |  |  |  | 0.2816% | 171750.99 | 171123.5748 | 627.4152 | 2024-01-01 | 2024-12-31 | 2024-04-10 | 2024-04-22
24026343300 | INSTALL 4" POLY VALVE |  |  |  |  | 0.01261% | 7689.14 | 18376.2056 | -10687.0656 | 2024-01-01 | 2024-12-31 | 2024-06-03 | 2024-06-06
24026349300 | INSTALL 4"POLY VALVE KY-C1556 |  |  |  |  | 0.03663% | 22343.49 | 32958.9947 | -10615.5047 | 2024-01-01 | 2024-12-31 | 2024-09-30 | 2024-10-02
22026237801 | INSTALL 4,100'-2" PMMP |  |  |  |  | 1.371% | 836183.38 | 765451.6207 | 70731.7593 | 2024-01-01 | 2024-12-31 | 2024-01-01 | 2024-02-27
24026341900 | INSTALL 4250' OF 2"/4"PMMP |  |  |  |  | 0.2625% | 160153.35 | 152744.147 | 7409.203 | 2024-01-01 | 2024-12-31 | 2024-07-01 | 2024-09-06
24026331601 | INSTALL 475' OF 2"PMMP MAIN |  |  |  |  | 0.2341% | 142820.44 | 110575.0083 | 32245.4317 | 2024-01-01 | 2024-12-31 | 2024-07-08 | 2024-07-22
22026183001 | INSTALL 4955'-2" PMMP |  |  |  |  | 0.2033% | 124010.5 | 134870.3496 | -10859.8496 | 2024-01-01 | 2024-12-31 | 2024-01-01 | 2024-05-24
24026334000 | INSTALL 5' OF 2" PMMP |  |  |  |  | 0.01862% | 11358.98 | 3841.146 | 7517.834 | 2024-01-01 | 2024-12-31 | 2024-04-01 | 2024-04-02 | FOUND COMPRESSION COUPLINGS LEAKING - SQEEZED OFFF MAIN WITH GAGE FOR PRESSURE VERIFICATION - PRESSURE REMAINED @ 53 - SOAP TEST LAST CONNECTIONS @ OP FOR 5 MIN TEST GOOD
22026164000 | INSTALL 5,100'-2" PMMP |  |  |  |  | 2.2% | 1341919.13 | 1140024.6985 | 201894.4315 | 2024-01-01 | 2024-12-31 | 2024-01-01 | 2024-04-10
22026172301 | INSTALL 5000' OF 2"PMMP MAIN |  |  |  |  | 2.009% | 1225170.53 | 1183513.1452 | 41657.3848 | 2024-01-01 | 2024-12-31 | 2024-01-01 | 2024-04-26
21026152101 | INSTALL 535' OF 8"CSHP MAIN |  |  |  |  | 0.7885% | 480960.85 | 444968.002 | 35992.848 | 2024-01-01 | 2024-12-31 | 2024-10-01 | 2024-10-31
23026270600 | INSTALL 550' OF 2" PMMP |  |  |  |  | 0.07106% | 43345.7 | 42706.9586 | 638.7414 | 2024-01-01 | 2024-12-31 | 2024-09-14 | 2024-09-26
23026288401 | INSTALL 5500' OF 4"PMMP MAIN |  |  |  |  | 0.483% | 294615.62 | 319863.8272 | -25248.2072 | 2024-01-01 | 2024-12-31 | 2024-06-23 | 2024-08-01
23026283801 | INSTALL 5705'-2"/4" PMMP |  |  |  |  | 0.6372% | 388707.97 | 361218.8401 | 27489.1299 | 2024-01-01 | 2024-12-31 | 2024-01-01 | 2024-04-11
22026238401 | INSTALL 5765'-2" PMMP |  |  |  |  | 2.331% | 1422160.57 | 1269865.7251 | 152294.8449 | 2024-01-01 | 2024-12-31 | 2024-09-16 | 2024-12-03
24026338500 | INSTALL 585' OF 2"PMMP MAIN |  |  |  |  | 0.05063% | 30882.37 | 37261.72 | -6379.35 | 2024-01-01 | 2024-12-31 | 2024-04-15 | 2024-05-03
23026273700 | INSTALL 6' OF 2"PMMP MAIN |  |  |  |  | 0.009592% | 5850.76 | 15141.0552 | -9290.2952 | 2024-01-01 | 2024-12-31 | 2024-07-10 | 2024-07-12 | LEAKING CV ON STEM.REMOVED CV AND INSTALLED 3' OF 020PMP.TESTED PURGE TEE AND 3FT OF MAIN FOR 1HR AT 90LBS.TEST OK.SOAP TEST EFC'S AT OP FOR 5MINS AT OP.TEST OK. BHB NGF. REMOVED CV C9-113.
20026983300 | INSTALL 6,600'-2"/4" PMMP |  |  |  |  | 3.304% | 2015230.05 | 1529743.322 | 485486.728 | 2024-01-01 | 2024-12-31 | 2024-09-09 | 2024-12-19
23026267200 | INSTALL 60'-4" PMLP |  |  |  |  | 0.0572% | 34888.84 | 41669.6267 | -6780.7867 | 2024-01-01 | 2024-12-31 | 2024-03-22 | 2024-03-28
24026363600 | INSTALL 620' OF 4"PMMP MAIN |  |  |  |  | 0.4511% | 275193.6 | 142827.5782 | 132366.0218 | 2024-01-01 | 2024-12-31 | 2024-11-04 | 2024-11-19 | TWALKER/KY 11-19-24: WMS WOULD NOT ALLOW JOB ORDER TO BE REVISED DUE TO UNPAID INVOICES. JOB WILL OVER RUN.
23026254900 | INSTALL 620' OF 8"CSHP MAIN |  |  |  |  | 0.3774% | 230200.58 | 398676.678 | -168476.098 | 2024-01-01 | 2024-12-31 | 2024-06-01 | 2024-07-19 | TWALKER/KY 01-20-25: LEVEL 1 VARIANCE ADDED TO WMS.DOCS: JOB UNDER RUN DUE TO THE UNIVERSITY OF KENTUCKY TAKING OWNERSHIP OF ALL THE STREETS IN PROJECT AREA - CKY DID NOT HAVE TO RESTORE/REPLACE ANY STREETS OR HARD SURFACE REPAIRS WHICH LOWERED CONTRACT COST BY $53,000, ALSO PROJECT WAS COMPLETED FASTER THAN ESTIMATE BECAUSE OF THE LACK OF STREET REPAIRS WHICH LOWERED LABOR COST BY $11,000. CKY WAS ABLE TO USED 8" STEEL PIPE LEFT OVER FROM LEESTOWN ROAD WIDENING PROJECT THAT SAVED $50,000 AND SEGA WAS $12,000 LOWER THAN ESTIMATE. FINALLY, THIS WAS A CUSTOMER PAID RELOCATION 100% REIMBURSEMENT PROJECT AND CUSTOMER WAS REFUNDED OVER PAYMENT IN 2024
24026338000 | INSTALL 65'-2"&4" PMMP |  |  |  |  | 0.09761% | 59541.79 | 74853.6852 | -15311.8952 | 2024-01-01 | 2024-12-31 | 2024-05-24 | 2024-05-30
24026324100 | INSTALL 670'-2' PMIP |  |  |  |  | 0.1495% | 91180.5 | 68828.4274 | 22352.0726 | 2024-01-01 | 2024-12-31 | 2024-10-28 | 2024-11-14 | INSTALLED 704' OF 2" PL IP AND 3' OF 2" ST TESTED 111 PSIG FOR 1 HR SOAP TE STED SST CAP AND PURGE POINT CAPS OP 7.5 PSIG
24026337000 | INSTALL 675' OF 2"PMMP MAIN |  |  |  |  | 0.07274% | 44370.55 | 60312.9634 | -15942.4134 | 2024-01-01 | 2024-12-31 | 2024-05-06 | 2024-05-21
23026308601 | INSTALL 675'-2" PMMP |  |  |  |  | 0.1492% | 91036.22 | 75877.1307 | 15159.0893 | 2024-01-01 | 2024-12-31 | 2024-05-27 | 2024-06-10 | JOB COMPLETED ON 5-14-24, ENGINEERING COMPLETED JOB ORDER REVISION ON 6-4-2 4 - RTINCHE 6-10-24
23026289700 | INSTALL 70' OF 3"PMLP MAIN |  |  |  |  | 0.0717% | 43735.5 | 32180.0533 | 11555.4467 | 2024-01-01 | 2024-12-31 | 2024-02-29 | 2024-03-05
23026294700 | INSTALL 70'-2" PMIP |  |  |  |  | 0.02028% | 12372.22 | 22819.9245 | -10447.7045 | 2024-01-01 | 2024-12-31 | 2024-01-01 | 2024-01-05 | INSTALLED 74' OF 2" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN AND PURGE POINT CAP OP 8 PSIG
24026348900 | INSTALL 70'-8" PMMP |  |  |  |  | 0.181% | 110389.69 | 134812.2257 | -24422.5357 | 2024-01-01 | 2024-12-31 | 2024-09-27 | 2024-10-07
19026913000 | INSTALL 730'-2"PMMP |  |  |  |  | 0.3983% | 242981.39 | 230850.9729 | 12130.4171 | 2024-01-01 | 2024-12-31 | 2024-03-12 | 2024-03-26
23026293700 | INSTALL 74'-2" PMMP |  |  |  |  | 0.08537% | 52073.55 | 102229.172 | -50155.622 | 2024-01-01 | 2024-12-31 | 2024-02-17 | 2024-02-21
24026309800 | INSTALL 75' - 2" PMMP |  |  |  |  | 0.03508% | 21399.98 | 15016.2249 | 6383.7551 | 2024-01-01 | 2024-12-31 | 2024-01-22 | 2024-01-29
24026333600 | INSTALL 75'-2" PMIP |  |  |  |  | 0.04654% | 28387.83 | 31694.159 | -3306.329 | 2024-01-01 | 2024-12-31 | 2024-09-02 | 2024-09-12
22026207100 | INSTALL 7870'-2", 4" PMMP |  |  |  |  | 2.54% | 1549123.72 | 1271473.5495 | 277650.1705 | 2024-01-01 | 2024-12-31 | 2024-08-05 | 2024-10-28
22026161800 | INSTALL 8" PCF |  |  |  |  | 0.04843% | 29544.9 | 147.7348 | 29397.1652 | 2024-01-01 | 2024-12-31 | 2024-11-11 | 2024-11-15
24026337800 | INSTALL 8" SS |  |  |  |  | 0.004346% | 2650.82 | 151.4465 | 2499.3735 | 2024-01-01 | 2024-12-31 | 2024-04-04 | 2024-04-08
24026354000 | INSTALL 850' OF 2"PMMP MAIN |  |  |  |  | 0.1002% | 61100.31 | 37954.6504 | 23145.6596 | 2024-01-01 | 2024-12-31 | 2024-08-05 | 2024-08-26 | COULD NOT INSTALL MAIN LINE ON DOCKSIDE PK. CT. BECAUSE ROAD WAS NOT INSTAL LED AT THIS TIME COMPLETED JOB PR ANDY ELLIOT DEVELLOPER WILL CALL WHEN REA DY, LSHARON 0/26/24
22026210901 | INSTALL 8OO' OF 2"PMMP MAIN |  |  |  |  | 0.08761% | 53441.52 | 49945.6881 | 3495.8319 | 2024-01-01 | 2024-12-31 | 2024-02-06 | 2024-02-20
23026298800 | INSTALL 900'-2" PMMP MAIN |  |  |  |  | 0.2529% | 154240.87 | 120091.9279 | 34148.9421 | 2024-01-01 | 2024-12-31 | 2024-03-20 | 2024-04-03
22026231301 | INSTALL 925' OF 2"PMMP MAIN |  |  |  |  | 0.6372% | 388671.62 | 399340.9217 | -10669.3017 | 2024-01-01 | 2024-12-31 | 2024-09-10 | 2024-09-20 | TWALKER/KY 10-25-24: JOB COST OVER RUN DUE TO CITY OF LEXINGTON REQUIRING MILL/PAVE FOR HIGH STREET WHICH ADDED $80,000 COPY INVOICE IN WMS.DOCS
25026377900 | INSTALL LP FITTING-PAPER ONLY |  |  |  |  | 0% | 0 | 139.0024 | -139.0024 | 2024-01-01 | 2024-12-31 | 2024-12-17 | 2024-12-17
23026283600 | INSTALL LP FITTINGS |  |  |  |  | 0.01583% | 9658.7 | 11183.6093 | -1524.9093 | 2024-01-01 | 2024-12-31 | 10/28/2024/ | 2024-10-28
24026340600 | INSTALL LP FITTINGS |  |  |  |  | 0% | 0 | 5899.0487 | -5899.0487 | 2024-01-01 | 2024-12-31 | 2024-04-25 | 2024-04-25
24026356200 | INSTALL NEW 4" CRITICAL VALVE |  |  |  |  | 0.01023% | 6237.92 | 9922.9586 | -3685.0386 | 2024-01-01 | 2024-12-31 | 2024-09-17 | 2024-09-20 | INST NEW 4" POLY CRITICAL VALVE C16-184 PER ENGINEERED TIE-IN AND GS. TEST NEW VALVE @ 90LB 1HR OK. SOAP TEST TIE-IN @ OP OK. BHB NGF. CO ON 9/19 MCRAIG 9/20/24
24026352800 | INSTALL SS FITTING |  |  |  |  | 0.009036% | 5512.14 | 24859.1129 | -19346.9729 | 2024-01-01 | 2024-12-31 | 2024-07-29 | 2024-08-01
24026310400 | INSTALL VALVE & 5' OF 2" PMMP |  |  |  |  | 0.01707% | 10413.42 | 11731.9279 | -1318.5079 | 2024-01-01 | 2024-12-31 | 2024-02-06 | 2024-02-07
22026183301 | SMRP INSTALL 1120' 8-12" CSHP |  |  |  |  | 2.705% | 1650295.52 | 1201596.3067 | 448699.2133 | 2024-01-01 | 2024-12-31 | 2024-01-01 | 2024-03-06
|  | - | - | - | - |  | 2024 Construction Project Budget | 60999242
ANC32.0000.00170 | ANC-SMRP Burns Ave |  |  |  |  | 2.26% | 1585256.47 | 1607553 | -22296.53 | 2025-01-01 | 2025-12-31 | 2025-05-05 | 2025-12-31
ANC32.0000.00256 | ANC - SMRP FLOYD STREET - ASHLAND |  |  |  |  | 4.691% | 3291186.21 | 3500000 | -208813.79 | 2025-01-01 | 2025-12-31 | 2025-07-17 | 2025-12-31 | More restoration than antipciated
ANC32.0000.00020 | RICHMOND ROAD PHASE 2 2025 SMRP |  |  |  |  | 2.128% | 1492718.41 | 1026516 | 466202.41 | 2025-01-01 | 2025-12-31 | 2025-09-25 | 2025-12-31 | Project was impacted by state road permit restricted work hours, additional flagging and hard surface restoration.
ANC32.0000.00049 | LEX SUNSET DR 2025 SMRP CNV-23026290300 |  |  |  |  | 1.929% | 1353303 | 924157 | 429146 | 2025-01-01 | 2025-12-31 | 2025-09-02 | 2025-12-31 | New main line was installed in roadway vs planned directional bore which increase restoration/hard surface repair cost.
22026239702 | INSTALL 8650' - 2,4,6" PMMP |  |  |  |  | 2.758% | 1934664.05 | 1422627.7319 | 512036.3181 | 2025-01-01 | 2025-12-31 | 2025-02-01 | 2025-05-02 | Higher project cost due to city paving/restoration cost - full road paving.
ANC32.0000.00050 | BLUE RIDGE 2025 SMRP CNV-23026290600 |  |  |  |  | 2.538% | 1780369 | 1314824 | 465545 | 2025-01-01 | 2025-12-31 | 2025-07-07 | 2025-12-23 | New main was installed by directional, older sewer and storm system required extensive camera work and locates.
GRT32.0000.00134 | ACE HARDWARE MIDWAY |  |  |  |  | 0.5458% | 382863.3 | 46804.6 | 336058.7 | 2025-01-01 | 2025-12-31 | 2025-09-02 | 2025-10-31 | City of Midway paved N Winter Street and could not issue city permit to cut new pavement. New Project route added 850' to overall project and increased cost.
ANC32.0000.00198 | MONTCLAIR/COOPER 2025 SMRP CNV-220262388 |  |  |  |  | 2.268% | 1590817 | 1271603 | 319214 | 2025-01-01 | 2025-12-31 | 2025-08-01 | 2025-12-01 | Miller Pipeline installed new main line by directional bore which required significant amount of sidewalk repair/replaced that increated project cost.
GRT32.0000.00098 | CNV-24026314400 INSTALL 1,200'-4\\\ PM. |  |  |  |  | 0.6298% | 441793 | 166742 | 275051 | 2025-01-01 | 2025-12-31 | 2025-03-31 | 2025-04-11 | Stanley Pipeline encountered significant rock and extra depth requirements for state road which increased over project costs.
ANC32.0000.00200 | RIVERSIDE 2025 SMPR -CNV-23026293500 |  |  |  |  | 0.5673% | 397969.27 | 149415.74 | 248553.53 | 2025-01-01 | 2025-12-31 | 2025-07-29 | 2025-10-01 | Project required change in route and CSX railroad permit/easement which added about 1000' of Main line.
PIG32.0000.00059 | EMER - Dixon St- Ashland |  |  |  |  | 0.419% | 293936.73 | 49189.54 | 244747.19 | 2025-01-01 | 2025-12-31 | 2025-09-22 | 2025-09-24 | Relocation project that design changed during construction phase and required us to re-work portions of the project.
ANC32.0000.00289 | ELM TREE 2025 SMRP CROSSBORE CNV-2402636 |  |  |  |  | 0.3933% | 275901.46 | 55039.42 | 220862.04 | 2025-01-01 | 2025-12-31 | 2025-11-21 | 2025-12-31 | Project was planned to correct cross bore issue but due to age/condition of LP main required installation of new PMMP main to resolve issue.
ANC32.0000.00180 | CNV-22026171600 INSTALL 4371'-2\"&4\" PM |  |  |  |  | 0.5696% | 399600.77 | 192726.47 | 206874.3 | 2025-01-01 | 2025-12-31 | 2025-07-18 | 2025-12-31 | Maple Road in Maysville required heavy rock bore that increased overall project cost.
22026236501 | INSTALL 1325' OF 4"/8"CSHP MN |  |  |  |  | 2.006% | 1407086.76 | 1205185.7862 | 201900.9738 | 2025-01-01 | 2025-12-31 | 2025-04-01 | 2025-05-29 | Trafton Street SMRP in Lexington project required railroad and state road rock bores that increase flagging cost and sewer camera.
GRT32.0000.00120 | GRT - 2804 PLEASANT AVE MLE - ASHLAND |  |  |  |  | 0.3098% | 217321.22 | 30420.98 | 186900.24 | 2025-01-01 | 2025-12-31 | 2025-10-01 | 2025-10-31 | Project size increased from 100' to 630' total footage due to customer request during construction.
ANC32.0000.00141 | FAYETTE PARK 2025 SMRP CNV-24026317600 |  |  |  |  | 0.3314% | 232457.82 | 51053.85 | 181403.97 | 2025-01-01 | 2025-12-31 | 2025-11-04 | 2025-12-31 | Project required additional sidewalk and road paving repairs that increased cost.
ANC32.0000.00147 | ANC-SMRP E Main St-Mt Sterling |  |  |  |  | 0.3121% | 218977.66 | 42430.62 | 176547.04 | 2025-01-01 | 2025-12-31 | 2025-06-26 | 2025-07-31 | Replacement project of BSLP main to accommodate city sidewalk and roadway improvements…scope of work was greater than expected.
ANC32.0000.00154 | CNV-25026404000 SMRP - INSTALL 650'-2\" |  |  |  |  | 0.2886% | 202446.55 | 31956.67 | 170489.88 | 2025-01-01 | 2025-12-31 | 2025-08-01 | 2025-08-29 | Project scope increased 150% in size due to age and condition of main encountered during construction.
ANC32.0000.00054 | SMRP JESSELIN DR 2025 CNV 24-0263154-00 |  |  |  |  | 1.285% | 901632 | 734748 | 166884 | 2025-01-01 | 2025-12-31 | 2025-08-05 | 2025-12-31 | New mains installed by directional bore that required additional sewer/storm camera work along with flagging cost.
GRT32.0000.00121 | GRT-Paddocks of Frankfort MLE |  |  |  |  | 1.074% | 753323.74 | 596391.42 | 156932.32 | 2025-01-01 | 2025-12-31 | 2025-09-02 | 2025-12-31 | Stanley Pipeline encountered significant rock and extra depth requirements for state road which increased over project costs.
BET32.0000.00027 | CNV-19026867802 INSTALL 376'-4\\\" PMIP. |  |  |  |  | 0.2271% | 159322.32 | 11431.35 | 147890.97 | 2025-01-01 | 2025-12-31 | 2025-09-11 | 2025-09-30
BET32.0000.00025 | CNV-25026382100 INSTALL 110'-4\" PMLP |  |  |  |  | 0.4963% | 348136.85 | 211351.06 | 136785.79 | 2025-01-01 | 2025-12-31 | 2025-10-17 | 2025-10-30
GRT32.0000.00096 | GRT-Bourbon Oaks Phase 1 MLE-Paris |  |  |  |  | 0.1994% | 139902.91 | 9884.28 | 130018.63 | 2025-01-01 | 2025-12-31 | 2025-06-20 | 2025-08-05
ANC32.0000.00157 | CNV-18026794401 INSTALL 4400'-2\"/4\"PMM |  |  |  |  | 0.2561% | 179679.93 | 53023.77 | 126656.16 | 2025-01-01 | 2025-12-31 | 2025-06-30 | 2025-12-31
GRT32.0000.00126 | Fortune Dr Frankfort Tierney MLE |  |  |  |  | 0.297% | 208369.03 | 85824.43 | 122544.6 | 2025-01-01 | 2025-12-31 | 2025-08-07 | 2025-12-31
ANC32.0000.00163 | CNV-21026152101 INSTALL 535' OF 8\\\"CS. |  |  |  |  | 0.6856% | 480961 | 444968 | 117519.58 | 2025-01-01 | 2025-12-31 | 2025-12-02 | 2025-12-31
PIG32.0000.00053 | Install 965'-4" PMMP |  |  |  |  | 0.3868% | 271321.62 | 156088.43 | 115233.19 | 2025-01-01 | 2025-12-31 | 2025-08-08 | 2025-09-26
GRT32.0000.00020 | GRT-Locust Hill Acres MLE-Winchester |  |  |  |  | 0.2325% | 163090.85 | 59513.98 | 103576.87 | 2025-01-01 | 2025-12-31 | 2025-09-11 | 2025-10-31
ANC32.0000.00264 | CNV-24026333201 EMER - INSTALL 478'-4\\. |  |  |  |  | 0.2929% | 205447 | 106609 | 98838 | 2025-01-01 | 2025-12-31 | 2025-02-17 | 2025-02-28
GRT32.0000.00097 | CNV-24026340200 INSTALL 600' OF 8\\\PM. |  |  |  |  | 0.5539% | 388585 | 296422 | 92163 | 2025-01-01 | 2025-12-31 | 2025-01-08 | 2025-01-31
GRT32.0000.00135 | Ball Homes Payne Crossing P2 Versailles |  |  |  |  | 0.3577% | 250951.48 | 164510.5 | 86440.98 | 2025-01-01 | 2025-12-31 | 2025-09-04 | 2025-09-04
ANC32.0000.00250 | WILSON ST SMRP - CNV-24026315000 |  |  |  |  | 0.193% | 135400.19 | 49600.16 | 85800.03 | 2025-01-01 | 2025-12-31 | 2025-10-21 | 2025-12-31
PIG32.0000.00028 | CNV-24026376901 INSTALL 1218'-6\" PMMP |  |  |  |  | 1.008% | 707095 | 626566 | 80529 | 2025-01-01 | 2025-12-31 | 2025-02-28 | 2025-04-30
GRT32.0000.00078 | DYER COVE MLE CNV-25026398900 |  |  |  |  | 0.1184% | 83056.5 | 7741 | 75315.5 | 2025-01-01 | 2025-12-31 | 2025-08-25 | 2025-09-15
GRT32.0000.00056 | GRT-BALL HOMES PENINSULA DOCKSIDE-LEX |  |  |  |  | 0.1137% | 79755.73 | 14249.76 | 65505.97 | 2025-01-01 | 2025-12-31 | 2025-11-18 | 2025-12-31
GRT32.0000.00002 | CNV-25026381700 INSTALL 230' OF 2\\\ P. |  |  |  |  | 0.1279% | 89700 | 29657 | 60043 | 2025-01-01 | 2025-12-31 | 2025-02-04 | 2025-02-07
GRT32.0000.00145 | GRT-TURNER COMMONS MLE-LEXINGTON |  |  |  |  | 0.1907% | 133757.7 | 81269.6 | 52488.1 | 2025-01-01 | 2025-12-31 | 2025-10-28 | 2025-12-01
ANC32.0000.00017 | 2621-TRAFTON SMRP-LEXINGTON |  |  |  |  | 0.1041% | 73009.05 | 21372.5 | 51636.55 | 2025-01-01 | 2025-12-31 | 2025-07-17 | 2025-08-18
BET32.0000.00052 | 2621 - STA 1073 VALVE REP - LEXINGTON |  |  |  |  | 0.1257% | 88181.36 | 38892.59 | 49288.77 | 2025-01-01 | 2025-12-31 | 2025-08-18 | 2025-09-25
PIG32.0000.00030 | CNV-24026370200 INSTALL 1415'-2\" PMMP |  |  |  |  | 0.2342% | 164287 | 125756 | 38531 | 2025-01-01 | 2025-12-31 | 2025-04-24 | 2025-05-30
GRT32.0000.00143 | 2621-50 & 52 LANTERN WAY-NICHOLASVILLE |  |  |  |  | 0.08627% | 60519.1 | 22677.35 | 37841.75 | 2025-01-01 | 2025-12-31 | 2025-10-09 | 2025-10-23
ANC32.0000.00085 | CNV-24026369000 INSTALL 65'-8\" PMLP |  |  |  |  | 0.2066% | 144967 | 108435 | 36532 | 2025-01-01 | 2025-12-31 | 2025-07-18 | 2025-07-31
ANC32.0000.00260 | CNV-24026331601 INSTALL 475' OF 2\"PMMP |  |  |  |  | 0.2036% | 142820 | 110575 | 32245 | 2025-01-01 | 2025-12-31 | 2025-04-15 | 2025-04-30
GRT32.0000.00122 | BALL HOMES - MASTERSON HILLS MLE |  |  |  |  | 0.1941% | 136154.07 | 104240.51 | 31913.56 | 2025-01-01 | 2025-12-31 | 2025-09-03 | 2025-10-18
ANC32.0000.00271 | CNV-24026347300 EMER - INSTALL 12'-3\" P |  |  |  |  | 0.07519% | 52750 | 21463 | 31287 | 2025-01-01 | 2025-12-31 | 2025-02-24 | 2025-02-28
BET32.0000.00046 | CNV-24026368800 INSTALL 5' OF 6\\\ PML. |  |  |  |  | 0.07687% | 53925 | 22845 | 31080 | 2025-01-01 | 2025-12-31 | 2025-06-26 | 2025-06-30
GRT32.0000.00062 | BALL HOMES ROSE RIDGE PH 2 NB |  |  |  |  | 0.07057% | 49509.72 | 23249.7 | 26260.02 | 2025-01-01 | 2025-12-31 | 2025-07-16 | 2025-09-02
PIG32.0000.00043 | CNV-24026328800 NEWTOWN PIKE MP RELOCATI |  |  |  |  | 2.196% | 1540784.41 | 1516637 | 24147.41 | 2025-01-01 | 2025-12-31 | 2025-07-09 | 2025-10-03
BET32.0000.00042 | CNV-24026341000 INSTALL 300'OF 2\" PMIP |  |  |  |  | 0.03311% | 23226.43 | 1109.39 | 22117.04 | 2025-01-01 | 2025-12-31 | 2025-04-24 | 2025-04-30
GRT32.0000.00076 | CNV-25026408500 INSTALL ANODE BED FOR D. |  |  |  |  | 0.03809% | 26719 | 6419 | 20300 | 2025-01-01 | 2025-12-31 | 2025-12-31 | 2025-12-31
GRT32.0000.00107 | CNV-25026381800 INSTALL 250'-2\" PMMP |  |  |  |  | 0.07463% | 52356 | 32186 | 20170 | 2025-01-01 | 2025-12-31 | 2025-04-09 | 2025-04-11
ANC32.0000.00282 | CNV-24026356000 INSTALL 475' OF 2\\\PM. |  |  |  |  | 0.1969% | 138118 | 124486 | 13632 | 2025-01-01 | 2025-12-31 | 2025-10-31 | 2025-12-01
ANC32.0000.00286 | CNV-24026362000 EMER-INSTALL 3' OF 3\"PM |  |  |  |  | 0.02606% | 18283 | 5267 | 13016 | 2025-01-01 | 2025-12-31 | 2025-11-26 | 2025-11-30
GRT32.0000.00104 | CNV-24026359401 INSTALL 200' OF 4\" PMIP |  |  |  |  | 0.08836% | 61986 | 49205 | 12781 | 2025-01-01 | 2025-12-31 | 2025-02-13 | 2025-02-19
ANC32.0000.00071 | CNV-24026344300 EMER-INSTALL 6' OF 4\" P |  |  |  |  | 0.0177% | 12417.86 | 0 | 12417.86 | 2025-01-01 | 2025-12-31 | 2025-07-31 | 2025-07-31
ANC32.0000.00146 | GRT-Adena Dr MLE-Mt Sterling |  |  |  |  | 0.1153% | 80873.14 | 71358.4 | 9514.74 | 2025-01-01 | 2025-12-31 | 2025-07-28 | 2025-08-09
ANC32.0000.00288 | CNV-24026365300 EMER INSTALL 5\" OF 4\" |  |  |  |  | 0.0374% | 26234 | 17482 | 8752 | 2025-01-01 | 2025-12-31 | 2025-06-25 | 2025-06-30
GRT32.0000.00077 | CNV-25026392000 INSTALL 140'-2\" PMMP |  |  |  |  | 0.03067% | 21515 | 12869 | 8646 | 2025-01-01 | 2025-12-31 | 2025-02-27 | 2025-05-28
BET32.0000.00024 | CNV-25026403100 EMER - RETIRE 2'-3\" PAM |  |  |  |  | 0.01647% | 11554.81 | 3218.22 | 8336.59 | 2025-01-01 | 2025-12-31 | 2025-04-07 | 2025-04-07
ANC32.0000.00263 | CNV-24026332800 EMER - INSTALL 5'-4\" PM |  |  |  |  | 0.01196% | 8388 | 3665 | 4723 | 2025-01-01 | 2025-12-31 | 2025-02-27 | 2025-02-28
GRT32.0000.00066 | CNV-24026372000 INSTALLING 500'-2\" PMMP |  |  |  |  | 0.06827% | 47890 | 43811 | 4079 | 2025-01-01 | 2025-12-31 | 2025-02-28 | 2025-03-14
GRT32.0000.00105 | CNV-24026361400 INSTALL 100' OF 2\\\ P. |  |  |  |  | 0.04004% | 28090 | 24014 | 4076 | 2025-01-01 | 2025-12-31 | 2025-02-12 | 2025-02-16
ANC32.0000.00316 | Abandon ~279'-2" BSIP |  |  |  |  | 0.008985% | 6303.25 | 2651.7 | 3651.55 | 2025-01-01 | 2025-12-31 | 2025-08-15 | 2025-11-28
ANC32.0000.00063 | CNV-24026332600 EMER INSTALL 10'-6\" PMM |  |  |  |  | 0.04623% | 32431 | 29701 | 2730 | 2025-01-01 | 2025-12-31 | 2025-03-20 | 2025-03-31
ANC32.0000.00114 | CNV-25026381500 EMER - RETIRE ~870'-3\" |  |  |  |  | 0.005972% | 4189.61 | 2276.13 | 1913.48 | 2025-01-01 | 2025-12-31 | 2025-01-27 | 2025-01-30
ANC32.0000.00152 | CNV-25026406300 INSTALL 15'-6\" PMLP |  |  |  |  | 0.002902% | 2035.9 | 203.85 | 1832.05 | 2025-01-01 | 2025-12-31 | 2025-05-01 | 2025-05-04
PIG32.0000.00015 | CNV-25026378600 INSTALL 42' OF 2\"/4\" P |  |  |  |  | 0.03708% | 26011 | 24410 | 1601 | 2025-01-01 | 2025-12-31 | 2025-02-26 | 2025-03-01
ANC32.0000.00068 | CNV-24026338200 EMER - INSTALL 5'-3\" PM |  |  |  |  | 0.007428% | 5210.66 | 3698 | 1512.66 | 2025-01-01 | 2025-12-31 | 2025-01-30 | 2025-01-31
GRT32.0000.00065 | CNV-24026368600 INSTALL 640' OF 2\\\ P. |  |  |  |  | 0.07182% | 50385 | 48982 | 1403 | 2025-01-01 | 2025-12-31 | 2025-05-23 | 2025-08-03
GRT32.0000.00040 | CNV-23026288901 INSTALL 880'-4\" PMMP |  |  |  |  | 0.3312% | 232364 | 231086 | 1278 | 2025-01-01 | 2025-12-31 | 2025-07-31 | 2025-09-16
ANC32.0000.00095 | CNV-25026397400 EMER-INSTALL 3' OF 2\"PM |  |  |  |  | 0.0113% | 7928 | 6833 | 1095 | 2025-01-01 | 2025-12-31 | 2025-07-01 | 2025-07-01
BET32.0000.00018 | CNV-24026356800 REPLACE 20'-6\" CSLP |  |  |  |  | 0.001524% | 1069.37 | 0 | 1069.37 | 2025-01-01 | 2025-12-31 | 2025-12-30 | 2025-12-31
PIG32.0000.00007 | CNV-23026301200 INSTALL 60' OF 6\"PMMP M |  |  |  |  | 0.06255% | 43879 | 42818 | 1061 | 2025-01-01 | 2025-12-31 | 2025-03-26 | 2025-04-01
ANC32.0000.00274 | CNV-24026349700 EMER INSTALL 2' OF 2\" P |  |  |  |  | 0.00863% | 6054 | 5243 | 811 | 2025-01-01 | 2025-12-31 | 2025-03-31 | 2025-03-31
ANC32.0000.00086 | CNV-24026371100 EMER-INSTALL 6' OF 8\"PM |  |  |  |  | 0.007608% | 5337 | 5614 | -277 | 2025-01-01 | 2025-12-31 | 2025-07-01 | 2025-07-01
BET32.0000.00053 | EMER - Install 10'-2" PMMP |  |  |  |  | 0% | 0 | 455.12 | -455.12 | 2025-01-01 | 2025-12-31 | 2025-08-18 | 2025-08-18
GRT32.0000.00108 | CNV-25026398800 INSTALL 3670' OF 2\"/4\" |  |  |  |  | 0.1858% | 130345 | 130832 | -487 | 2025-01-01 | 2025-12-31 | 2025-05-02 | 2025-05-30
ANC32.0000.00091 | CNV-24026375200 EMER-INSTALL 6' OF 2\"PM |  |  |  |  | 0.009766% | 6851 | 7800 | -949 | 2025-01-01 | 2025-12-31 | 2025-08-29 | 2025-08-31
ANC32.0000.00281 | CNV-24026355400 EMER-INSTALL 2' OF 2\"PM |  |  |  |  | 0.00663% | 4651 | 5647 | -996 | 2025-01-01 | 2025-12-31 | 2025-10-31 | 2025-10-31
ANC32.0000.00097 | CNV-25026399300 EMER - INSTALL 5'-2\" PM |  |  |  |  | 0.003276% | 2298 | 3695 | -1397 | 2025-01-01 | 2025-12-31 | 2025-11-26 | 2025-11-30
ANC32.0000.00077 | CNV-24026357700 EMER-INSTALL 2' OF 3\"PM |  |  |  |  | 0.01968% | 13807 | 15212 | -1405 | 2025-01-01 | 2025-12-31 | 2025-10-28 | 2025-10-31
ANC32.0000.00285 | CNV-24026357000 EMER-INSTALL 50' OF 4\"P |  |  |  |  | 0.0279% | 19571 | 21586 | -2015 | 2025-01-01 | 2025-12-31 | 2025-11-24 | 2025-11-30
GRT32.0000.00064 | CNV-24026365700 INSTALL 320' OF 2\\\PM. |  |  |  |  | 0.04241% | 29755 | 31922 | -2167 | 2025-01-01 | 2025-12-31 | 2025-01-02 | 2025-01-10
GRT32.0000.00075 | CNV-25026407800 EMER - INSTALL 5'-2\" PM |  |  |  |  | 0.002288% | 1605 | 4099 | -2494 | 2025-01-01 | 2025-12-31 | 2025-05-13 | 2025-05-13
ANC32.0000.00075 | CNV-24026351600 EMER - INSTALL 2'-2\" PM |  |  |  |  | 0.004189% | 2939 | 5506 | -2567 | 2025-01-01 | 2025-12-31 | 2025-03-28 | 2025-03-31
GRT32.0000.00055 | CNV-24026352000 INSTALL 700'-2\\\ PMMP. |  |  |  |  | 0.108% | 75787 | 78414 | -2627 | 2025-01-01 | 2025-12-31 | 2025-01-24 | 2025-01-30
ANC32.0000.00317 | 2629-EMER 499 Indian mound-Mt Sterling |  |  |  |  | 0% | 0 | 2723.68 | -2723.68 | 2025-01-01 | 2025-12-31 | 2025-08-15 | 2025-12-31
BET32.0000.00013 | CNV-25026377600 EMER-INSTALL 4' OF 2\"PM |  |  |  |  | 0.01283% | 8999 | 11901 | -2902 | 2025-01-01 | 2025-12-31 | 2025-05-29 | 2025-06-01
GRT32.0000.00118 | 2629-Patsy Way MLE-Mt Sterling |  |  |  |  | 0.03375% | 23675.7 | 26720.71 | -3045.01 | 2025-01-01 | 2025-12-31 | 2025-07-31 | 2025-10-30
ANC32.0000.00150 | CNV-25026405400 EMER - INSTALL 2'-2\" PM |  |  |  |  | 0.005102% | 3579 | 7065 | -3486 | 2025-01-01 | 2025-12-31 | 2025-06-30 | 2025-07-01
ANC32.0000.00099 | CNV-25026400500 EMER - INSTALL 5'-2\" PM |  |  |  |  | 0.006035% | 4234 | 7746 | -3512 | 2025-01-01 | 2025-12-31 | 2025-11-25 | 2025-11-30
PIG32.0000.00011 | CNV-24026361300 INSTALL 750'-2\\\ PMMP. |  |  |  |  | 0.2938% | 206115 | 209702 | -3587 | 2025-01-01 | 2025-12-31 | 2025-03-04 | 2025-03-30
ANC32.0000.00283 | CNV-24026356200 INSTALL NEW 4\" CRITICAL |  |  |  |  | 0.008892% | 6238 | 9923 | -3685 | 2025-01-01 | 2025-12-31 | 2025-10-31 | 2025-12-01
ANC32.0000.00275 | CNV-24026351400 EMER - INSTALL 2'-2\" PM |  |  |  |  | 0.002633% | 1847 | 5751 | -3904 | 2025-01-01 | 2025-12-31 | 2025-03-31 | 2025-03-31
ANC32.0000.00295 | CNV-25026385100 EMER-INSTALL 4' OF 4\"PM |  |  |  |  | 0.01504% | 10552 | 14597 | -4045 | 2025-01-01 | 2025-12-31 | 2025-06-30 | 2025-06-30
ANC32.0000.00311 | Replace Coalton Rectifier - 25026408100 |  |  |  |  | 0.002444% | 1714.45 | 5858.32 | -4143.87 | 2025-01-01 | 2025-12-31 | 2025-07-24 | 2025-10-24
ANC32.0000.00292 | CNV-24026376700 EMER - INSTALL 3'-2\" PM |  |  |  |  | 0.004479% | 3142 | 7334 | -4192 | 2025-01-01 | 2025-12-31 | 2025-08-28 | 2025-08-31
ANC32.0000.00151 | CNV-25026406000 EMER - INSTALL 2'-2\" PM |  |  |  |  | 0.005871% | 4119 | 8338 | -4219 | 2025-01-01 | 2025-12-31 | 2025-04-11 | 2025-04-18
ANC32.0000.00096 | CNV-25026398400 EMER - INSTALL FITTINGS. |  |  |  |  | 0.009779% | 6860 | 11221 | -4361 | 2025-01-01 | 2025-12-31 | 2025-11-25 | 2025-11-30
ANC32.0000.00083 | CNV-24026364700 INSTALL 518'-4\" PMIP |  |  |  |  | 0.04359% | 30580.52 | 35276.7 | -4696.18 | 2025-01-01 | 2025-12-31 | 2025-07-30 | 2025-08-08
ANC32.0000.00076 | CNV-24026353200 EMER - INSTALL 3'-4\" PM |  |  |  |  | 0.004433% | 3110 | 7994 | -4884 | 2025-01-01 | 2025-12-31 | 2025-03-25 | 2025-03-31
ANC32.0000.00149 | CNV-25026403300 INSTALL MONITOR REGULATO |  |  |  |  | 0.002415% | 1694.06 | 7028 | -5333.94 | 2025-01-01 | 2025-12-31 | 2025-05-29 | 2025-05-30
GRT32.0000.00119 | 275 Heritage Dr MLE Versailles |  |  |  |  | 0.01453% | 10194.51 | 15748.01 | -5553.5 | 2025-01-01 | 2025-12-31 | 2025-07-30 | 2025-08-14
ANC32.0000.00100 | CNV-25026400900 EMER - INSTALL 2'-4\" PM |  |  |  |  | 0.009023% | 6330 | 12462 | -6132 | 2025-01-01 | 2025-12-31 | 2025-11-25 | 2025-11-30
ANC32.0000.00098 | CNV-25026399700 EMER - INSTALL 3'-2\" PM |  |  |  |  | 0.0003564% | 250 | 6698 | -6448 | 2025-01-01 | 2025-12-31 | 2025-11-26 | 2025-11-30
ANC32.0000.00121 | CNV-23026276000 REPLACE ODORIZER R-1439 |  |  |  |  | 0.02483% | 17419 | 24767 | -7348 | 2025-01-01 | 2025-12-31 | 2025-12-23 | 2025-12-31
ANC32.0000.00293 | CNV-25026379000 EMER - INSTALL 9'-2\" PM |  |  |  |  | 0.003596% | 2522.61 | 11724 | -9201.39 | 2025-01-01 | 2025-12-31 | 2025-01-02 | 2025-01-02
BET32.0000.00026 | CNV-25026400200 INSTALL 550'-2\\\ PMMP. |  |  |  |  | 0.06772% | 47508 | 57766 | -10258 | 2025-01-01 | 2025-12-31 | 2025-04-28 | 2025-05-01
BET32.0000.00048 | CNV-24026310700 ABANDON ~ 150'- 2\" CSIP |  |  |  |  | 0.03117% | 21867 | 32187 | -10320 | 2025-01-01 | 2025-12-31 | 2025-12-23 | 2025-12-31
BET32.0000.00044 | CNV-24026349300 INSTALL 4\"POLY VALVE KY |  |  |  |  | 0.03185% | 22343 | 32959 | -10616 | 2025-01-01 | 2025-12-31 | 2025-05-28 | 2025-06-01
BET32.0000.00060 | Duke Rd. / Cooper Dr. Relocation |  |  |  |  | 0.0001607% | 112.75 | 11380.49 | -11267.74 | 2025-01-01 | 2025-12-31 | 2025-12-05 | 2025-12-19
ANC32.0000.00120 | CNV-22026211900 INSTALL 1\" BYPASS VALVE |  |  |  |  | 0.002399% | 1683 | 15921 | -14238 | 2025-01-01 | 2025-12-31 | 2025-09-25 | 2025-10-01
PIG32.0000.00056 | Vandalay Dr Frankfort Relo |  |  |  |  | 0.005878% | 4123.36 | 18975.45 | -14852.09 | 2025-01-01 | 2025-12-31 | 2025-08-01 | 2025-08-15
ANC32.0000.00148 | CNV-25026397000 UPGRADE RECTIFIER W/ RMU |  |  |  |  | 0.000394% | 276.39 | 16611.6 | -16335.21 | 2025-01-01 | 2025-12-31 | 2025-08-28 | 2025-08-28
ANC32.0000.00006 | ANC-Wisemantown Rd Rectifier-Irvine |  |  |  |  | 0.008009% | 5618.83 | 22844.78 | -17225.95 | 2025-01-01 | 2025-12-31 | 2025-08-28 | 2025-10-31
GRT32.0000.00139 | GRT - 2029 FERN DR MLE - LOUISA |  |  |  |  | 0.01906% | 13372.78 | 31131.04 | -17758.26 | 2025-01-01 | 2025-12-31 | 2025-12-01 | 2025-12-10
BET32.0000.00054 | BET-Mitchell Ave-Lexington |  |  |  |  | 0.003156% | 2214.33 | 20539.08 | -18324.75 | 2025-01-01 | 2025-12-31 | 2025-11-18 | 2025-12-05
PIG32.0000.00051 | 2629 - 325 SANDE RIDGE LN - MT. STERLING |  |  |  |  | 0.04018% | 28187.08 | 46559 | -18371.92 | 2025-01-01 | 2025-12-31 | 2025-08-19 | 2025-11-30
GRT32.0000.00106 | CNV-24026366400 INSTALL ~390'-2\" PMIP |  |  |  |  | 0.06401% | 44902 | 64433 | -19531 | 2025-01-01 | 2025-12-31 | 2025-02-06 | 2025-02-14
PIG32.0000.00014 | CNV-24026370600 INSTALL 32'-6\" PMLP |  |  |  |  | 0.01186% | 8318 | 29726 | -21408 | 2025-01-01 | 2025-12-31 | 2025-05-23 | 2025-05-30
ANC32.0000.00052 | CNV-24026313000 INSTALL 1570'-2\\\ PMM. |  |  |  |  | 0.7165% | 502658 | 526295 | -23637 | 2025-01-01 | 2025-12-31 | 2025-08-19 | 2025-09-30
GRT32.0000.00044 | CNV-23026283101 INSTALL 780'-2\" PMMP |  |  |  |  | 0.1023% | 71782 | 96019 | -24237 | 2025-01-01 | 2025-12-31 | 2025-05-21 | 2025-05-30
GRT32.0000.00074 | CNV-25026404300 INSTALL 80' OF 2\" PMMP |  |  |  |  | 0.009845% | 6906.46 | 33570.17 | -26663.71 | 2025-01-01 | 2025-12-31 | 2025-08-12 | 2025-08-31
ANC32.0000.00143 | ANC-Wilson Ln Abandonment-Winchester |  |  |  |  | 0.002813% | 1973.6 | 30868.63 | -28895.03 | 2025-01-01 | 2025-12-31 | 2025-12-30 | 2025-12-31
PIG32.0000.00024 | CNV-25026409400 INSTALL ANODE BED. |  |  |  |  | 0.03035% | 21291 | 52966 | -31675 | 2025-01-01 | 2025-12-31 | 2025-12-23 | 2025-12-23
PIG32.0000.00055 | 2629-S Highland Relocation-Winchester |  |  |  |  | 0% | 0 | 34563.32 | -34563.32 | 2025-01-01 | 2025-12-31 | 2025-08-06 | 2025-09-13
PIG32.0000.00001 | CNV-24026345800 INSTALL 1400'-2\\\ PMI. |  |  |  |  | 0.3757% | 263557 | 300749 | -37192 | 2025-01-01 | 2025-12-31 | 2025-03-26 | 2025-04-15
GRT32.0000.00130 | 2621-Quintana Estates MLE-Lexington WMS. |  |  |  |  | 0.1708% | 119825.18 | 163229.55 | -43404.37 | 2025-01-01 | 2025-12-31 | 2025-09-17 | 2025-11-14
ANC32.0000.00257 | WOLF RUN 2025 SMRP CNV-24026322000 |  |  |  |  | 0.9718% | 681714.43 | 730195.39 | -48480.96 | 2025-01-01 | 2025-12-31 | 2025-07-31 | 2025-12-31
ANC32.0000.00140 | ANC-Caney Circle- Pippa Passes |  |  |  |  | 0.009568% | 6712.5 | 60386.93 | -53674.43 | 2025-01-01 | 2025-12-31 | 2025-07-02 | 2025-12-31
GRT32.0000.00022 | CNV-25026393800 INSTALL 2,100'-2\\\ PM. |  |  |  |  | 0.1582% | 110997 | 177755 | -66758 | 2025-01-01 | 2025-12-31 | 2025-05-13 | 2025-05-30
GRT32.0000.00133 | Ball Homes South Crossing P3 Georgetown |  |  |  |  | 0.4014% | 281612.34 | 367711.37 | -86099.03 | 2025-01-01 | 2025-12-31 | 2025-09-02 | 2025-11-01
GRT32.0000.00125 | UK DORM WOODLAND |  |  |  |  | 0.05055% | 35464.16 | 127511.86 | -92047.7 | 2025-01-01 | 2025-12-31 | 2025-08-06 | 2025-08-30
ANC32.0000.00144 | CNV-24026367900 INSTALL 1060' OF 2\"PMMP |  |  |  |  | 0.004863% | 3411.34 | 101110.57 | -97699.23 | 2025-01-01 | 2025-12-31 | 2025-08-06 | 2025-08-08
PIG32.0000.00049 | CNV-24026367500 INSTALL 1600'-2\" PMMP |  |  |  |  | 0.5821% | 408326 | 509357 | -101031 | 2025-01-01 | 2025-12-31 | 2025-05-13 | 2025-07-01
PIG32.0000.00039 | CNV-24026358801 INSTALL 4200' OF 2\\\"/. |  |  |  |  | 1.115% | 782268 | 884926 | -102658 | 2025-01-01 | 2025-12-31 | 2024-09-19 | 2025-06-01
PIG32.0000.00016 | UK PMMP RELOCATION-25026402500 |  |  |  |  | 0.2267% | 159024 | 122594 | 36430 | 2025-01-01 | 2025-12-31 | 2025-07-16 | 2025-07-31
ANC32.0000.00339 | EMER-10th Street-Catlettsburg |  |  |  |  | 3.991e-06% | 2.8 | 1792.45 | -1789.65 | 2025-01-01 | 2025-12-31 | 2025-12-04 | 2025-12-19
GRT32.0000.00131 | GRT - CARRIAGE LN MLE - LEXINGTON |  |  |  |  | 0.5095% | 357427.11 | 495629.82 | -138202.71 | 2025-01-01 | 2025-12-31 | 2025-10-01 | 2025-12-31
PIG32.0000.00013 | CNV-24026363100 INSTALL 481'-8\" CSHP |  |  |  |  | 0.06702% | 47018.3 | 195428.52 | -148410.22 | 2025-01-01 | 2025-12-31 | 2025-07-15 | 2025-07-30
BET32.0000.00049 | EMER - E Broadway St Crossbore FRANKFORT |  |  |  |  | 0.004246% | 2978.58 | 157244.84 | -154266.26 | 2025-01-01 | 2025-12-31 | 2025-08-06 | 2025-08-29
BET32.0000.00003 | CNV-21026135500 INSTALL 75'-4/6/12\" CSH |  |  |  |  | 0.04044% | 28372.72 | 183004.72 | -154632 | 2025-01-01 | 2025-12-31 | 2025-07-25 | 2025-07-31
ANC32.0000.00199 | SMRP-Castlewood Dr-Lexington |  |  |  |  | 0.2278% | 159842.86 | 497868.19 | -338025.33 | 2025-01-01 | 2025-12-31 | 2025-08-18 | 2025-12-31
ANC32.0000.00005 | ANC-SMRP Camelot Dr - Winchester |  |  |  |  | 0.9511% | 667229.79 | 2008502.28 | -1341272.49 | 2025-01-01 | 2025-12-31 | 2025-07-21 | 2025-12-31 | Project was successfully bored instead of open as estimated which lowered overall cost.
ANC32.0000.00194 | SMRP LAFAYETTE HS |  |  |  |  | 1.885% | 1322123.24 | 1246000 | 76123.24 | 2025-01-01 | 2025-12-31 | 2025-08-05 | 2025-12-31
|  | - | - | - | - |  | 2025 Construction Project Budget | 70152936
Formulas:
Date Actual End = VLOOKUP([Project No.],'WMS JO Data'!$D20:BD27974,25,FALSE)

## 2021 (hidden)
Columbia Gas of Kentucky Case No. 2026-00099 Attachment A Construction Projects For 5 years ended December 31, 2025
Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End | Job Order Comments
20026969700 | INSTALL 8500' OF 2"/4"PMMP MN | [5 empty] | 270941.08 | 301857.4038 | -30916.3238 | 2020-01-01 | 2020-12-31 | 2020-11-09 | 2021-01-08
21026993200 | EMER- INSTALL 5'-4" PMMP | [5 empty] | 3260.67 | 4003.4824 | -742.8124 | 2021-01-01 | 2021-12-31 | 2021-01-05 | 2021-01-08 | INSTALLED 4' OF 4" P. PRESSURE TESTED AT 90LBS FOR 1HR. SOAP TESTED (2) 4" EF COUPLINGS AT OPERATING PRESSURE (11PSIG).
21026993300 | EMER- RETIRE 5'-4" P-MP | [5 empty] | 184.74 | 647.029 | -462.289 | 2021-01-01 | 2021-12-31 | 2021-01-05 | 2021-01-08 | REMOVED 4' OF DAMAGED 4" P
21026993600 | EMER INST 40'-4" PMLP | [5 empty] | 772.98 | 13260.7401 | -12487.7601 | 2021-01-01 | 2021-12-31 | 2021-01-07 | 2021-01-08 | INSTALLED 28' OF 4" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 10" WC
21026993700 | EMER RET 40'-4" BSLP/CSLP/P-LP | [5 empty] | 372.17 | 1322.2973 | -950.1273 | 2021-01-01 | 2021-12-31 | 2021-01-07 | 2021-01-08 | RETIRED 28' OF 4" STEEL MAIN AND 3 WAY TEE
20026991200 | RETIRE BUILDING | [5 empty] | 0 | 107.2796 | -107.2796 | 2021-01-01 | 2021-12-31 | 2021-01-07 | 2021-01-07 | THIS IS PAPER ONLY JOB BUILDING WAS TORN DOWN MANY YEARS AGO THIS JOB IS TO CORRECT CKY RECORDS ONLY FIELD VERIFIED BY CKY ENGINEERING
20026988100 | INSTALL 525' OF 2"PMMP MAIN | [5 empty] | 10228.67 | 17405.4965 | -7176.8265 | 2021-01-01 | 2021-12-31 | 2021-01-07 | 2021-01-11
21026994600 | EMER INSTALL 5'-4" PMMP | [5 empty] | 4622.23 | 5854.5805 | -1232.3505 | 2021-01-01 | 2021-12-31 | 2021-01-08 | 2021-01-11 | REPLACED 5 FT MAIN TEST 90 LB FOR 20 MIN TEST ALL TEES AT 5 MIN TEST BYPASS 90 LB FOR 1 HR TEST ALL END CAPS AT OP FOR 5 MIN BAR HOLE BANKS NO GAS FOUND MARKER BALL AT TEES AND CPLG
21026994400 | EMER- INSTALL 5'-2" PMIP | [5 empty] | 5176.12 | 7281.2724 | -2105.1524 | 2021-01-01 | 2021-12-31 | 2021-01-08 | 2021-01-13 | INSTALLED 6' NEW 020 MDPE ML. TESTED AT 90# 20 MINS. WELD-IN TRANSITIONS. S OAP TEST TIE IN. PURGED AT EOM. SWING TIES AND ELEC MARKERS. J HOWARD 1-13- 21
21026994700 | EMER - RETIRE 5'-4" PMP | [5 empty] | 102.95 | 103.8156 | -0.86559 | 2021-01-01 | 2021-12-31 | 2021-01-08 | 2021-01-11 | CUT OUT CRACKED MAIN PUT ON BYPASS AND PUT IN 5 FT OF MAIN
21026994500 | EMER- RETIRE 5'-2" BSIP | [5 empty] | 1169.82 | 239.0145 | 930.8055 | 2021-01-01 | 2021-12-31 | 2021-01-08 | 2021-01-11 | INSTALLED 2 020 TDW SS. TAP AND STOP ML. NO UPSTREAM PRESSURE LOSS. REMOVED AND ABANDONED 6' SECTION OF 020 S ML FOR INSTALL OF 020 MDPE. J HOWARD 1-1 1-21
20026991100 | INSTALL 100' OF 4"PMLP S/L | [5 empty] | 33764.98 | 29024.9725 | 4740.0075 | 2021-01-01 | 2021-12-31 | 2021-01-07 | #N/A
21026996700 | EMER - INSTALL 10'-4" PMMP | [5 empty] | 1315.39 | 1997.1109 | -681.7209 | 2021-01-01 | 2021-12-31 | 2021-01-11 | 2021-01-11
21026996800 | EMER - RETIRE 10'-4" PMMP | [5 empty] | 0 | 95.6296 | -95.6296 | 2021-01-01 | 2021-12-31 | 2021-01-11 | 2021-01-11
19026901000 | RETIRE STATION 1464 | [5 empty] | 2654.56 | 690.3419 | 1964.2181 | 2020-01-01 | 2020-12-31 | 2021-01-11 | 2021-01-11 | JOB CARRIED OVER UNTIL AFTER THE 1ST OF 2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/16/2021 GCCC TICKET NOT REQUIRED ON 2/16/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK 2/16/21 CFARIS
19026901100 | RETIRE STATION 1481 | [5 empty] | 2483.61 | 690.3419 | 1793.2681 | 2021-01-01 | 2021-12-31 | 2021-01-11 | 2021-01-11 | JOB ON HOLD UNTIL AFTER THE 1ST OF 2021
19026901200 | RETIRE STATION 1480 | [5 empty] | 4464.65 | 690.3419 | 3774.3081 | 2021-01-01 | 2021-12-31 | 2021-01-11 | 2021-01-11 | JOB WAS ON HOLD UNTIL AFTER THE 1ST OF 2021
20026945201 | INSTALL 5000' OF 2"PMMP MAIN | [5 empty] | 228201.9 | 223484.8945 | 4717.0055 | 2020-01-01 | 2020-12-31 | 2020-11-18 | 2021-02-16 | INSTALLED 4938"020 PMMP.
18026789001 | INSTALL 6900' - 4" PMMP | [5 empty] | 789465.56 | 783479.7367 | 5985.8233 | 2020-01-01 | 2020-12-31 | 2020-10-20 | 2021-02-05
20026936600 | ABANDON ~10'-4" P-LP | [5 empty] | 167.31 | 173.6495 | -6.3395 | 2021-01-01 | 2021-12-31 | 2021-01-12 | 2021-01-13
21026996400 | EMER - ABANDON 37'-2" PIP | [5 empty] | 860.91 | 2872.6664 | -2011.7564 | 2021-01-01 | 2021-12-31 | 2021-01-14 | 2021-01-25 | ABANDONED 37' OF 020 MAIN DUE TO FAC DAM. WORKED WITH TIE IN PLAN. INSTALLED LINE MARKER AT EOM. UPDATED MAPPING. SOAP TEST END CAP AT OP.TEST OK. BHB NGF.
20026930100 | UPGRADE ELECTRONICS | [5 empty] | 3919.3 | 3038 | 881.3 | 2021-01-01 | 2021-12-31 | 2021-01-14 | 2021-01-14 | NO TICKET NEEDED FOR THE WORK PERFORMED. 1/14/21 GCCC TICKET NOT REQUIRED PE ENGINEER CINDY SPARKS GAVE VERBAL APPROVAL ON SITE TO PROCEED WITH JOB. EFC REPLACEMENT ONLY GAS FLOW NOT INTERUPTED JOB DELAYED DUE TO COVID 19 AND COMPLIANCE WORK AND BY NOW HAVING TO BE REVIEWED BY PE ENGINEER
20026937300 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 | 2021-01-01 | 2021-12-31 | 2021-01-14 | 2021-01-14 | GCCC TICKET NOT REQUIRED VERBAL APPROVAL GIVEN ONSITE BY PE ENGINEER CINDY SPARKS TO WORK JOB GAS FLOW NOT INTERUPTED TO WORK JOB THIS WAS EFC REPLACEMENT ONLY JOB DELAYED DUE TO COVID 19 COMPLIANCE WORK AND WAITING REVIEW BY PE ENGINEER
20026989600 | INSTALL 40'-2" PMMP | [5 empty] | 36919.96 | 30326.4153 | 6593.5447 | 2021-01-01 | 2021-12-31 | 2021-01-13 | 2021-01-15
20026989700 | RETIRE 40'-2" CSMP | [5 empty] | 0 | 107.2796 | -107.2796 | 2021-01-01 | 2021-12-31 | 2021-01-13 | 2021-01-15
19026895301 | INSTALL 6060' 2" PMMP | [5 empty] | 815947.98 | 549218.5288 | 266729.4512 | 2020-01-01 | 2020-12-31 | 2020-09-29 | 2021-01-27 | JOB ORDER CODED COMPLETE IN ERROR. WILL BE CARRY OVER INTO 2021. SPENDLE OVERRUN EXPLANATION: ADDITIONAL PIPE WAS ADDED LATE INTO PROJECT AND ADDITI ONAL LABOR HOURS CAUSED INCREASE IN SEGA AS WELL AS LATE PAVING COSTS THAT HIT THE PROJECT SBRADY 6/18/21
20026990600 | PAPER ONLY FOR CLOSE OUT | [5 empty] | 0 | 103.8156 | -103.8156 | 2021-01-01 | 2021-12-31 | 2021-01-21 | 2021-01-21
20026967900 | INSTALL 315' 2" PMIP | [5 empty] | 71403.61 | 31888.6353 | 39514.9747 | 2021-01-01 | 2021-12-31 | 2021-01-19 | 2021-01-29 | TWALKER/KY 02-23-21: ISSUED BACK ORDER CANCEL #48444 FOR JOB OVERRUN EXPLANATION: 150 SQUARE FEET OF 6&2 WAS ESTIMATED AND 990 SQ FEET W AS REQUIRED LEADING TO AN INCREASE IN CONTRACTOR COSTS AND OVERHEADS.
19026895200 | RETIRE 2104' 2" P/BSLP | [5 empty] | 100.78 | 103.581 | -2.801 | 2021-01-01 | 2021-12-31 | 2021-01-15 | 2021-01-27
19026895400 | RETIRE 5072' 2-4" IP | [5 empty] | 0 | 103.581 | -103.581 | 2021-01-01 | 2021-12-31 | 2021-01-15 | 2021-01-27
19026895600 | RETIRE 1516' 2" BS/P/WILP | [5 empty] | 108.73 | 103.581 | 5.149 | 2021-01-01 | 2021-12-31 | 2021-01-15 | 2021-01-27
19026900900 | RETIRE MP TO IP RUN S-1455 | [5 empty] | 152.33 | 690.3419 | -538.0119 | 2021-01-01 | 2021-12-31 | 2021-01-27 | 2021-10-25 | MP TO IP RUN RETIRE ON 1/27/21 BY RYAN VANDERPOOL PAPERWORK DID NOT GET TURNED IN FOR COMPLETION STATION RETIREMENT FIELD VERIFIED ALONG WITH RETIREMENT DATE FROM THE STATION INSPECTION RECORD BY WADE SHIMFESSEL AND JOSH MARTIN ON 10/18/2021 RETIREMENT PAPERWORK COMPLETED BY CYNTHIA FARIS ON 10/25/2021 GCCC TICKET NOT REQUIRED ON 10/25/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK. SETTING BYPASS VALVE AND INLET SETTING VALVE NOT RETIRED THEY ARE TURNED OFF AND BLIND FLANGED CFARIS
20026966800 | RETIRE 2800' OF 4"/6"BSLP MAIN | [5 empty] | 907.78 | 90.1729 | 817.6071 | 2021-01-01 | 2021-12-31 | 2021-02-03 | 2021-02-04
21026100900 | EMER INSTALL 5'-4" PMMP | [5 empty] | 49713.13 | 15398.8131 | 34314.3169 | 2021-01-01 | 2021-12-31 | 2021-02-03 | 2021-02-10 | RETIRED 4 FEET OF 4' PE MAIN LINE. REPLACED PEICE OF MAIN WITH NEW AND EF COUPLINGS. PRESSURE TESTED NEW PEICE OF MAIN FOR 1HR @ 90PSIG. TEST OK. SOAP TESTED FINALS CONNECTION @ OP. TEST, BHB, NGF. DMALONE 2/09/2021. OVERRUN EXPLANATION: UNEXPECTED CONTRACT COST OF $35,000 WAS NOT PLANNED, JO ORIGINALLY PLANNED FOR COMPANY CREW BUT WAS EXECUTED BY A CONTRACT CREW, COMPANY CREWS ALSO CHARGED 183 HOURS TO PROJECT
21026101000 | EMER RETIRE 5'-4" PMP D222468 | [5 empty] | 10.95 | 69.6296 | -58.6796 | 2021-01-01 | 2021-12-31 | 2021-02-03 | 2021-02-09 | RETIRED 4 FEET OF 4' PE MAIN LINE. REPLACED PEICE OF MAIN WITH NEW AND EF COUPLINGS. PRESSURE TESTED NEW PEICE OF MAIN FOR 1HR @ 90PSIG. TEST OK. SOAP TESTED FINAL CONNECTION @ OP. TEST OK. BHB. NGF. DMALONE 2/09/2021 OVERRUN EXPLANATION: THIS RETIREMENT JOB ORDER WAS ESTIMATED IN THE ORDINAR Y MANNER FOR JUST 1 HOUR; HOWEVER, THERE WERE NO PROPERTY UNITS INSTALLED S O THE JOB WAS WORKED AS AN ABANDONMENT WITH ALL THE LABOR AND CONTRACT COST S BEING APPLIED TO THE RETIREMENT. THE INSTALL JOB ORDER WAS EXECUTED WITH AN HOUR OF LABOR.
18026789100 | RETIRE 600' - 3" PMMP | [5 empty] | 70.37 | 218.671 | -148.301 | 2021-01-01 | 2021-12-31 | 2021-02-04 | 2021-02-04
20026955400 | RETIRE STATION | [5 empty] | 2363.47 | 1910.2958 | 453.1742 | 2021-01-01 | 2021-12-31 | 2021-02-04 | 2021-02-04 | 8561 JOB WAS ON HOLD UNTIL AFTER BEGINNING OF THE YEAR
21026100300 | EMER INS ~15'-2"/3" PMIP/CSIP | [5 empty] | 13138.1 | 15461.5913 | -2323.4913 | 2020-01-01 | 2020-12-31 | 2020-10-20 | 2021-02-17 | 3" C.S. MAIN PULLED LOOSE FROM 4 BOLT COUPLING DUE TO STRESS ON MAIN FROM EXPOSURE DOWN STREAM. TAPPED & STOPPED 3" C.S. REPLACED LEAKING SECTION WITH 3" P 20' PRESSURE TEST 90 PSIG 1HR PURGED MAIN LINE, RESTORED SERVICE.
21026100400 | EMER RETIRE ~5'-3" CSIP | [5 empty] | 1505.21 | 1147.7777 | 357.4323 | 2021-01-01 | 2021-12-31 | 2021-02-05 | 2021-02-11 | 3" CS MAIN PULLED LOOSE FROM 4 BOLT COUPLING DUE TO STRESS ON MAIN FROM EXPOSURE DOWN STREAM. TAPPED & STOP 3" CS MAIN REPLACED LEAKING SECTION WITH 3" P 20' PRESSURE TEST 90PSIG FOR 1 HR. PURGED MAIN & RESTORED SERVICE
20026975000 | INSTALL 150'-2" PMIP | [5 empty] | 12825.26 | 12346.2686 | 478.9914 | 2021-01-01 | 2021-12-31 | 2021-01-27 | 2021-02-08
21026104900 | EMER INSTALL 5'-3" PMIP | [5 empty] | 4758.29 | 5995.5434 | -1237.2534 | 2021-01-01 | 2021-12-31 | 2021-02-22 | 2021-03-25 | SEE PAPER PACKET FOR INFO
21026105000 | EMER RETIRE 5'-3" P-IP | [5 empty] | 3758.23 | 750.8346 | 3007.3954 | 2021-01-01 | 2021-12-31 | 2021-02-22 | 2021-03-25 | SEE PAPER COPIES FOR TEST INFO SEE PAPER COPIES/ PIPE EXPOSURE FORM WILL NOT ACCEPT THE CORRECT MAIN NUMBER NOT LETTING ME COMPLETE THIS ORDER
21026131100 | EMER-RETIRE 10' OF 2"PAMP MAIN | [5 empty] | 0 | 74.8797 | -74.8797 | 2021-01-01 | 2021-12-31 | 2021-06-22 | 2021-06-23
19026913900 | INSTALL 20' - 4" CSHP | [5 empty] | 82645.85 | 45390.8034 | 37255.0466 | 2021-01-01 | 2021-12-31 | 2021-02-08 | 2021-03-23 | COULD NOT REVISE DUE TO UNFULLFILLED PURCHASE ORDERS, NEEDED REVISION DUE TO EXTRA MATERIAL, INCREASE CONTRACT LABOR REQUIRED, EXTRA COMPANY LABOR, EXTRA TRUCK COSTS, AND EXTRA SEGA TTOY 3/18/2021
19026914000 | RETIRE 10' - 3" CSHP | [5 empty] | 695.55 | 114.5339 | 581.0161 | 2021-01-01 | 2021-12-31 | 2021-02-08 | 2021-03-23
20026941900 | RETIRE GAUGE | [5 empty] | 0 | 91.4991 | -91.4991 | 2021-01-01 | 2021-12-31 | 2021-02-24 | 2021-07-16 | GAUGE RETIRE BY JOSH MULLINS ON 2/24/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/16/21 DELAY COMPLETING JOB ORDER DUE TO ISO SKETCH REVISION& PE APPROVAL GCCC TICKET NOT REQUIRED ON 7/16/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026942400 | RETIRE GAUGE | [5 empty] | 1032.4 | 91.4991 | 940.9009 | 2021-01-01 | 2021-12-31 | 2021-12-17 | 2021-12-17 | REPLACED MECHANICAL RECORDING GAUGE WITH ERX DELAY IN SENDING TO CLOSEOUT DUE TO WAITING ON INFORMATION, PE REVIEW/APPROVAL AND CORRECT ISO SKETCH CFARIS
20026941800 | INSTALL I&C EQUIPMENT | [5 empty] | 12411.86 | 16155.4774 | -3743.6174 | 2021-01-01 | 2021-12-31 | 2021-02-24 | 2021-07-16 | GCC 13064 EQUIPMENT INSTALLED BY JOSH MULLINS ON 2/24/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/16/21 DELAY IN JOB COMPLETION WAITING ON PE APPROVAL FOR 584 JOB ORDER AND ISO SKETCH UPDATE GCCC TICKET NOT REQUIRED ON 7/16/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026942300 | INSTALL I&C EQUIPMENT | [5 empty] | 11644.22 | 16155.4774 | -4511.2574 | 2021-01-01 | 2021-12-31 | 2021-12-17 | 2021-12-17 | INSTALLED ERX DELAY IN SENDING JOB TO CLOSE OUT WAITING ON INFORMATION PE REVIEW/APPROVAL AND ISO SKETCH CFARIS
21026105900 | EMER INSTALL 5' OF 4"PMMP MAIN | [5 empty] | 12908.51 | 24731.5705 | -11823.0605 | 2021-01-01 | 2021-12-31 | 2021-02-25 | 2021-03-18 | TWALKER/KY-04-20-21: I HAVE ADDED A SIGNED PRESSURE TEST TO APPROVE THE 20 MIN PRESSURE TEST TO WMS.DOCS WORKSPACE.
21026106500 | EMER - INSTALL 4' OF 2"PMMP | [5 empty] | 7429.12 | 7343.079 | 86.041 | 2021-01-01 | 2021-12-31 | 2021-02-25 | 2021-02-25
21026105700 | EMER INST 360'-2" PMIP D244304 | [5 empty] | 109722.07 | 25736.2708 | 83985.7992 | 2021-01-01 | 2021-12-31 | 2021-02-25 | 2021-03-09 | INSTALLED 345' OF 2" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7.5 P SIG OVERRUN EXPLANATION: THE SIGNIFICANT COST DIFFERENCE RESULTED FROM PAVING REQUIREMENTS. THE PROJECT WAS NOT ESTIMATED FOR CONTRACT RESTORATION. PAVE TICKETS WERE SUBMITTED TO REPAIR ROAD AND PARKING LOT AREA
21026106000 | EMER RETIRE 5' OF 4"PAMP MAIN | [5 empty] | 0 | 82.208 | -82.208 | 2021-01-01 | 2021-12-31 | 2021-02-25 | 2021-03-18
21026106600 | EMER - RETIRE 4' OF 2"PMMP | [5 empty] | 0 | 82.208 | -82.208 | 2021-01-01 | 2021-12-31 | 2021-02-25 | 2021-02-25
21026105800 | EMER RETIRE 350'-3"/2" CSIP | [5 empty] | 27035.38 | 1114.7918 | 25920.5882 | 2021-01-01 | 2021-12-31 | 2021-02-25 | 2021-03-09 | FOUND CRACKED MAIN RETIRED 345' OF 3" ST AND INSTALLED 345' OF NEW 2" PL TO STOP LEAKAGE TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7.5 PSIG
18026778900 | INSTALL ERX & RTU BUILDING | [5 empty] | 113154.12 | 156098.7133 | -42944.5933 | 2021-01-01 | 2021-12-31 | 2021-02-26 | 2021-12-16 | CC# 13231. 2/25/21 DSASH WORKED ON PAPERWORK OFF SITE. 2/26/21 DSASH EQUIPMENT INSTALLED ON 2/25/21 BY ACP AND DANNY ASH PAPERWORK COMPLETED ON 12/16/2021 BY CYNTHIA FARIS JOB CLOSEOUT DELAYED WAITING ON INFORMATION AND CORRECT ISO SKETCH UNDERRUN EXPLANATION: THE CONTRACT COSTS WERE SIGNIFICANT LESS THAT THE I&C TEAM HAD ORIGINALLY ESTIMATED.
21026998100 | INSTALL 180' OF 2"PMMP MAIN | [5 empty] | 36764.99 | 11159.7406 | 25605.2494 | 2021-01-01 | 2021-12-31 | 2021-02-08 | 2021-02-26
20026991300 | INSTALL 350'-2" PMMP | [5 empty] | 19273.52 | 31069.259 | -11795.739 | 2021-01-01 | 2021-12-31 | 2021-03-02 | 2021-03-03 | 337 FT 2 " MEDIUM PRESSURE MAIN INSTALLED BY STANLEY PIPELINE YELLOW MED IUM DENSITY.PIPE
20026980000 | INSTALL 675' - 2"/4" PMLP | [5 empty] | 186497.16 | 148515.2952 | 37981.8648 | 2021-01-01 | 2021-12-31 | 2021-02-09 | 2021-03-04 | DUE TO WEATHER CONDITION ON STATE ROAD UNABLE TO MAKE COMMIT DATE OVERRUN EXPLANATION: ALL OPEN CUT WAS ESTIMATED, BUT 108 FEET OF DIRECTIONA L BORE WAS USED. ADDITIONALLY, APPROXIMATELY 4 TIMES AS MUCH FLAGGING WAS R EQUIRED THAN ESTIMATED. OVERHEADS INCREASED $10,500 DUE TO THESE OVERAGES.
21026107500 | EMER- INSTALL120'-2" PL | [5 empty] | 2045.88 | 13083 | -11037.12 | 2021-01-01 | 2021-12-31 | 2021-03-04 | 2021-06-10 | INSTALLED 155' OF 2" P-MP MAIN DUE TO LEAK, SEE CAPITAL PACKET JO# 21-0261075-00, CDESPAIN 3-4-21
21026107600 | RETIRE MAIN - LEAKAGE D304381 | [5 empty] | 14663.28 | 56.3197 | 14606.9603 | 2021-01-01 | 2021-12-31 | 2021-03-04 | 2021-06-10 | REPLACED 155' OF 2" P- MP MAIN, FOUND 2BOLT COUPLING PL-PL CORRODED AND LEAKING, SQUEEZED OFF, REPLACED MAIN, SEE JO PACKET 21-0261075-00 CDESPAIN 3-4-21
20026980100 | RETIRE 622' - 2" BSLP | [5 empty] | 647.77 | 103.8156 | 543.9544 | 2021-01-01 | 2021-12-31 | 2021-02-09 | 2021-03-04
18026807000 | INST. FN 115 EXTRA LP OPP | [5 empty] | 28771.63 | 24102.8722 | 4668.7578 | 2021-01-01 | 2021-12-31 | 2021-03-04 | 2021-05-12 | GCCC# 11422 CHARED TIME TO COLLECT MATERIAL. DID NOT VISIT SITE NO GCCC TICKET REQUIRED CMCOC 3/3/21 GCCC# 13985 CMCHOLAN 3-4-2021 CCC#13985 REGULATOR AND ER350 INSTALLED BY CHRIS COX ON 3/4/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026807100 | RET. FN 115 FOR EXTRA LP OPP | [5 empty] | 2550 | 54.9718 | 2495.0282 | 2021-01-01 | 2021-12-31 | 2021-03-04 | 2021-05-12 | REGULATOR REPLACED BY CHRIS COX ON 3/4/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026108600 | EMER-INSTAL 5'-2" PMMP | [5 empty] | 116.02 | 5147.5997 | -5031.5797 | 2021-01-01 | 2021-12-31 | 2021-03-05 | 2021-03-08 | INSTALLED 5' OF TEST 2" PMMP, SOAP TEST TIE IN, NO LEAKS, BHB NGF TIE OVER 2 SERVICE LINES, ON 3-5-21 DMEDLEY 3-8-21
21026108700 | EMER - RETIRE 5'-2" PAMP | [5 empty] | 4796.8 | 85.3307 | 4711.4693 | 2021-01-01 | 2021-12-31 | 2021-03-05 | 2021-03-08 | INSTALLED GAUGE TEE, SQUEEZE OFF 2" PL MAIN, ABN 5' 2"PMP MAIN PER DLEMONS EMER DESIGN PLAN. WORKED ON 3-5-21, DMEDLEY 3-8-21
21026996200 | INSTALL 2150'-2" PMMP | [5 empty] | 336530.83 | 214604.887 | 121925.943 | 2021-01-01 | 2021-12-31 | 2021-01-22 | 2021-03-05 | JOB ORDER CODED COMPLETE AT TIME OF MAIN LINE COMPLETION, STILL WORKING ON SERVICES. SPENDLE 3/10/21 20APR21: SEVERAL ATTEMPTS WERE MADE TO REVISE THIS JOB ORDER TO CAPTURE OVERRUN, HOWEVER, OUTSTANDING INVOICES PREVENTED ENGINEERING FROM DOING SO. . 29APR21: OVERRUN EXPLANATION = FISHEL'S CONTRACT OVER $21K DUE TO INCREASED LABOR & MATERIALS TO PREP STAGING (STONE, FENCING, AND ENVIRONMENTAL BMPS) ALONG WITH A LOT MORE FLAGGING BY AWP FOR TRAFFIC CONTROL. BUCHANAN'S COST FOR SEWER INSPECTION & CAMERING WAS WAY UNDERESTIMATED CONTRIBUTING ANOTHER $33K TO THE OVERRUN. LASTLY, COMPANY LABOR OVERRAN BY $14K FROM WHAT WAS ORIGINALY ESTIMATED. THESE COSTS PLUS OH'S MAKE UP THE OVERRUN (BKSLONE).
21026109000 | EMER - INSTALL 10'-4" PMIP | [5 empty] | 2349.57 | 8970.0544 | -6620.4844 | 2021-01-01 | 2021-12-31 | 2021-03-16 | 2021-03-18 | INSTALLED 5' OF NEW 4" PL MAIN TO REPAIR CRACKED PIPE TESTED 90 PSIG 1 HR
21026109100 | EMER - RETIRE 10'-4" CSIP | [5 empty] | 5925.07 | 556.9397 | 5368.1303 | 2021-01-01 | 2021-12-31 | 2021-03-08 | 2021-03-18 | RETIRE 5' OF 4" CS MAIN DUE TO SPLIT MAIN SOAP TESTED OP 7.5 PSIG
20026987500 | INSTALL 300' OF 2"PMMP MAIN | [5 empty] | 18181.58 | 19258.6597 | -1077.0797 | 2021-01-01 | 2021-12-31 | 2021-03-08 | 2021-03-10
20026988800 | INSTALL 210'-2" PMLP | [5 empty] | 21827.5 | 42176.37 | -20348.87 | 2021-01-01 | 2021-12-31 | 2021-03-08 | 2021-03-10
20026984400 | INSTALL 949'-6" PMLP | [5 empty] | 282788.29 | 204292.6769 | 78495.6131 | 2021-01-01 | 2021-12-31 | 2021-01-20 | 2021-03-12 | 14JUN21: OVERRRUN EXPLANATION = 1) REQUIRED FLAGGING WAS WAY UNDERESTIMATED AS $30K ADDITIONAL DOLLARS FOR FLAGGING WAS REQUIRED, 2) AN ADDITIONAL $10K IN DUST & STONE WAS REQUIRED, 3) THE 6" ROCK BORE WAS PAID ALL IN HEAVY ROCK WHEREAS IT WAS ESTIMATED 1/2 HEAVY AND 1/2 LIGHT WHICH CONTRIBUTED ANOTHER $8K TO THE OVERRUN,4) ADDITIONAL VAC EXCAVATION WAS REQUIRED ADDING $3K TO THE OVERRUN. THESE PLUS ADDITIONAL OH'S MAKE UP THE MAJORITY OF THE $57K OVERRUN (BKSLONE)
21026997000 | INSTALL 1100'-2" PMP | [5 empty] | 532822.99 | 340896.6283 | 191926.3617 | 2021-01-01 | 2021-12-31 | 2021-02-23 | 2021-04-27 | 14JUN21: UNDERRUN EXPLANATION = 1) ASPHALT MILL & OVERLAY WAS MISCALCULATED RESULTING IN AN ADDITIONAL $120K AND 2) FLAGGING TIME WAS UNDERESTIMATED RESULTING IN AND ADDITIONAL $35K. THESE COSTS, ALONG WITH ASSOCIATED OH'S, MAKE UP THE MAJORITY IF THE $166K OVERRUN. THE ERROR IN PAVING COSTS WAS NOT NOTICED UNTIL AFTER THE ORIGINAL JOB ORDER WAS EXECUTED THEREBY PROHIBITING PROCESSING A REVISION (BKSLONE).
20026979600 | INSTALL 20' - 2"/6" PMMP | [5 empty] | 106288.64 | 65238.0736 | 41050.5664 | 2021-01-01 | 2021-12-31 | 2021-02-02 | 2021-03-19 | ATTEMPTED TO REVISE DUE TO EXTRA HOURLY COST, COULD NOT REVISE DUE TO UNFULLFILLED PURCHASE ORDER TTOY 3/18/2021 OVERRUN EXPLANATION: JO WAS ORIGINALLY PLANNED ON 2018 FISHEL CONTRACT, JO WAS EXECUTED USING 2020 STANLEY PIPELINE CONTRACT, EXTRA VAC EXCA, EXTRA WLD AND RIG, EXTRA TOP SOIL REQUIRED, EXTRA HOURLY CREW REQUIRED, ESTIMATED HOURLY TIME WAS 56 HOURS, ACTUAL HOURLY TIME WAS 398 HOURS, ESTIMATED CONTRACT COST WAS $35,000, ACTUAL CONTRACT COST WAS $51,000
20026990100 | INSTALL 6" SS | [5 empty] | 245.63 | 1607.8146 | -1362.1846 | 2021-01-01 | 2021-12-31 | 2021-03-11 | 2021-03-19
20026979700 | RETIRE 15' - 2" BSLP | [5 empty] | 71.35 | 92.1481 | -20.7981 | 2021-01-01 | 2021-12-31 | 2021-03-11 | 2021-03-19
20026992200 | INSTALL 100'-2" PMIP | [5 empty] | 8539.31 | 11276.4442 | -2737.1342 | 2021-01-01 | 2021-12-31 | 2021-03-11 | 2021-03-15
21026108400 | EMER - INSTALL 350' - 4" PMMP | [5 empty] | 86916.93 | 44073.8715 | 42843.0585 | 2021-01-01 | 2021-12-31 | 2021-03-10 | 2021-03-16 | OVERRUN EXPLANATION: HOURLY TIME EXTIMATED AT 48 HOURS, ACTUAL TIME WAS 97 HOURS, SEGA WAS DOUBLED, CONTRACT WAS ESTIMATED FOR $29,000, ACTUAL WAS $68,000, PROJECT WAS ESTIMATED TO DIRECTIONAL BORE 150', ACTUAL INSTALL WAS OPEN CUT 345', PROJECT REQUIRED EXTRA PAVING DUE TO OPEN CUT, PROJECT REQUIRED EXTRA PROCESSED AND STONE DUST DUE TO OPEN CUT, EXTRA VACUUM EXCAV ATING WAS REQUIRED, ESTIMATED FOR 4 MAN CREW CONTRACT, ACTUAL USED 3 MAN, 4 MAN, AND 5 MAN CREWS
21026115100 | INSTALL 1'-4" PMLP | [5 empty] | 0 | 149.4587 | -149.4587 | 2021-01-01 | 2021-12-31 | 2021-04-02 | 2021-04-06
21026115800 | EMER - INSTALL 138'-4" PM/CSIP | [5 empty] | 2573.82 | 10752.5629 | -8178.7429 | 2021-01-01 | 2021-12-31 | 2021-03-15 | 2021-04-20 | INSTALLED 134' OF 4" PL IP TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7.5 PSIG
21026108500 | EMER - RETIRE 350' - 4" PMP | [5 empty] | 4479.43 | 85.3307 | 4394.0993 | 2021-01-01 | 2021-12-31 | 2021-03-16 | 2021-03-16
21026115900 | EMER - RETIRE 134'-4" CSIP | [5 empty] | 9847.31 | 1105.3087 | 8742.0013 | 2021-01-01 | 2021-12-31 | 2021-04-20 | 2021-04-20 | RETIRED 134' OF 4" CS DUE MAIN EXPOSED OUT OF GROUND AND DETERIORATION
20026936301 | INSTALL 1192'-4" PMMP | [5 empty] | 290217.29 | 375696.2322 | -85478.9422 | 2021-01-01 | 2021-12-31 | 2021-01-13 | 2021-04-06 | UNDERRUN EXPLANATION: SIGNIFICANTLY LESS HARD SURFACE REPAIRS AND BACKFILL REQUIRED THAN ESTIMATED. ALSO NOFLAGGING ON OVERTIME WAS REQUIRED. THE OVER HEAD EFFECT OF THESE REDUCTIONS ALSO CONTRIBUTED TO THE UNDERRUN.
20026982500 | INSTALL 120' - 4" PMLP | [5 empty] | 38925.35 | 30468.341 | 8457.009 | 2021-01-01 | 2021-12-31 | 2021-03-16 | 2021-03-26
20026951802 | INSTALL 3980' OF 2"PMMP MAIN | [5 empty] | 461944.16 | 383869.9188 | 78074.2412 | 2021-01-01 | 2021-12-31 | 2021-20-04 | 2021-05-07 | TWALKER/KY 09-21-21: JOB OVER RUN DUE TO ADDITIONAL STREET AND HARD SURFACE REPAIR ADDED $70,000 TO CONTRACT COST AND SEGA WAS $7000 HIGHER THAN ESTIMA TE.
21026113000 | EMER - INSTALL 60' OF 4"PMLP | [5 empty] | 2022.21 | 12530.1178 | -10507.9078 | 2021-01-01 | 2021-12-31 | 2021-03-26 | 2021-04-08 | INSTALLED 54' OF 040 PLASTIC DUE TO STEEL ATMOS CORR. BAGGED OFF MAIN, RETIRED 54' 040 STEEL.WORKED WITH TIE IN PLAN AND CAPITAL PACKET.INSTALLED TWO TEST STATIONS. BHB NGF. KKINDER
20026951900 | RETIRE 2100' OF 4"CI/PLP MAIN | [5 empty] | 0 | 84.1799 | -84.1799 | 2021-01-01 | 2021-12-31 | 2021-04-28 | 2021-05-07
21026113100 | EMER - RETIRE 60' OF 4"BSLP | [5 empty] | 1338.57 | 57.8842 | 1280.6858 | 2021-01-01 | 2021-12-31 | 2021-03-26 | 2021-04-08 | ABADONED 54' OF S LP DUE TO ATMOS CORR. WORKED WITH 557. BAGGED OFF MAIN WORKED WITH TIE IN PLAN. KKINDER
21026106100 | INSTALL 1350' OF 2"/4"PMMP | [5 empty] | 39665.6 | 45765.0925 | -6099.4925 | 2021-01-01 | 2021-12-31 | 2021-03-22 | 2021-04-09 | STANLEY PIPELNE INSTALLED MAIN
20026930400 | UPGRADE ELECTRONICS | [5 empty] | 6567.19 | 3038 | 3529.19 | 2021-01-01 | 2021-12-31 | 2021-03-29 | 2021-03-31 | CCC TICKET NOT REQUIRED 3/29/21 CFARIS REPLACED EFC AND WORKED TP ORDER JOB ON HOLD FOR 2020 DUE TO COVID 19 GCCC TICKET NOT REQUIRED ON 3/31/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK ALSO THIS IS NON-SCADA MONITORED GMB CFARIS
20026937600 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 | 2021-01-01 | 2021-12-31 | 2021-03-31 | 2021-03-31 | REPLACED EFC JOB ON HOLD IN 2020 DUE TO COVID 19 GCCC TICKET NOT REQUIRED NOT AT STATION OFF SITE COMPLETING PAPERWORK ALSO THIS IS A NON-SCADA MONITORED GMB 3/31/21 CFARIS
21026997600 | INSTALL 20'-2" PMIP | [5 empty] | 25490.16 | 28869.525 | -3379.365 | 2021-01-01 | 2021-12-31 | 2021-03-29 | 2021-03-31
17026735700 | RETIRE 3510' MAIN - D243673 | [5 empty] | 8338.24 | 78.7024 | 8259.5376 | 2021-01-01 | 2021-12-31 | 2021-03-30 | 2021-03-30
21026997700 | RETIRE 15'-2" BSIP | [5 empty] | 95.92 | 88.4533 | 7.4667 | 2021-01-01 | 2021-12-31 | 2021-03-30 | 2021-03-30
20026936400 | RETIRE 1228'-3"&4"BS/CS/P-LP | [5 empty] | 1214.98 | 400.0304 | 814.9496 | 2021-01-01 | 2021-12-31 | 2021-01-13 | 2021-04-06
21026998000 | CONVERT TO GMB ACCOUNT | [5 empty] | 6412.15 | 4845.4443 | 1566.7057 | 2021-01-01 | 2021-12-31 | 2021-04-05 | 2021-04-07 | CONVERTED FROM CAB TO GMB ACCOUNT CCC TICKET NOT REQUIRED THIS IS NON-SCADA MONITORED
21026114000 | EMER - RETIRE 145' OF 2"BSLP | [5 empty] | 1254.24 | 3325.023 | -2070.783 | 2021-01-01 | 2021-12-31 | 2021-04-07 | 2021-04-07 | RETIRED 146' OF 2" BSLP MAIN, SOAP TEST BOLTED DEAD END CAP AT OP, OK. SOAP TEST SADDLES AND PAC CLAMPS AT OP OK. BHB NGF. INSTALLED 9# ANODE. MAIN READ# -0.643. MAIN INSP OK. WHIMES 04/07/2021
21026109900 | RETIRE 2155'-4"/3" BS/PMLP | [5 empty] | 3173.92 | 343.31 | 2830.61 | 2021-01-01 | 2021-12-31 | 2021-04-07 | 2021-04-28
20026975201 | INSTALL 3000' OF 2"/4"PMMP | [5 empty] | 630664.21 | 552556.8312 | 78107.3788 | 2021-01-01 | 2021-12-31 | 2021-06-17 | 2021-06-11
21026106200 | INSTALL 6" PCF | [5 empty] | 13429.76 | 16594.9062 | -3165.1462 | 2021-01-01 | 2021-12-31 | 2021-04-07 | #N/A | INSTALLED 6"SST
21026106300 | RETIRE 575'-6" BSLP | [5 empty] | 1068.93 | 88.4533 | 980.4767 | 2021-01-01 | 2021-12-31 | 2021-04-07 | 2021-04-12 | ABANDONED 640'060 CSLP
21026107700 | INSTALL 20' OF 8"PMLP MAIN | [5 empty] | 8482.5 | 12704.2275 | -4221.7275 | 2021-01-01 | 2021-12-31 | 2021-04-12 | #N/A | REPLACED 36' OF S LP MAON W/ 8" P PER TIE-IN PLAN AND GAS STANDARDS. SOAP TEST TIE-IN COUPLINGS NO LEAKS. BHB NGF. MAIN PTOS READ -0.482 INST 2 9LB ANODES.
21026107800 | RETIRE 20' OF 8" BSLP | [5 empty] | 8727.02 | 56.3197 | 8670.7003 | 2021-01-01 | 2021-12-31 | 2021-04-12 | 2021-04-14 | ABN 36' OF 8" S LP MAIN AND REPLACE WITH 8" P PER GAS STANDARDS AND TIE-IN PLAN. WORKED W/ 557 JOB# 21026107700. MCRAIG 4/14/21
21026107900 | INSTALL 10' OF 3" PMLP | [5 empty] | 7671.47 | 13301.2275 | -5629.7575 | 2021-01-01 | 2021-12-31 | 2021-04-15 | #N/A | ABANDONED 23' OF 030 S MAIN.DUE TO ATMOS CORR INSTALLED 23' OF 030 PLASTIC WORKED WITH TIE IN PLAN AND GAS STANDARD. BHB NGF. INSTALLED TWO TEST STATIONS AND TWO ANODED.DESNO WRAPPED STEEL MAIN.
21026108000 | RETIRE 10' OF 3" BSLP | [5 empty] | 8414.88 | 79.3197 | 8335.5603 | 2021-01-01 | 2021-12-31 | 2021-04-15 | 2021-04-16 | ABANDONED 23' OF 030 S MAIN.DUE TO ATMOS CORR INSTALLED 23' OF 030 PLASTIC WORKED WITH TIE IN PLAN AND GAS STANDARD. BHB NGF. INSTALLED TWO TEST STATIONS AND TWO ANODED.DESNO WRAPPED STEEL MAIN.
20026979201 | INSTALL SERVICE TO GMB | [5 empty] | 201470.53 | 135908.7766 | 65561.7534 | 2021-01-01 | 2021-12-31 | 2021-04-27 | #N/A | LEVEL 2 BUDGET VARIANCE LOADED INTO WMSSDOCS. D.LEMONS 9/22/21
20026979100 | RETIRE SERVICE | [5 empty] | 0 | 83.3805 | -83.3805 | 2021-01-01 | 2021-12-31 | 2021-04-27 | 2021-04-21
21026113401 | INSTALL 100'-2" PMMP | [5 empty] | 21410.67 | 11198.5401 | 10212.1299 | 2021-01-01 | 2021-12-31 | 2021-04-12 | #N/A
20026929300 | UPGRADE ELECTRONICS | [5 empty] | 6355.62 | 3038 | 3317.62 | 2021-01-01 | 2021-12-31 | 2021-04-16 | #N/A | REPLACED EFC
20026929600 | UPGRADE ELECTRONICS | [5 empty] | 3403.36 | 3038 | 365.36 | 2021-01-01 | 2021-12-31 | 2021-04-16 | #N/A | REPLACED EFC
20026935000 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 | 2021-01-01 | 2021-12-31 | 2021-04-16 | 2021-04-16 | REPLACE EFC JOB ON HOLD 2020 BECAUSE OF COVID 19
21026114300 | RETIRE EFC | [5 empty] | 0 | 111.0751 | -111.0751 | 2021-01-01 | 2021-12-31 | 2021-04-16 | #N/A
21026999500 | INSTALL 175' OF 2"PMMP | [5 empty] | 16309.78 | 9497.8185 | 6811.9615 | 2021-01-01 | 2021-12-31 | 2021-04-13 | 2021-05-03 | 174 '2"PLASTIC MED -DENSITY YELLOW PIPE INSTALLED BY BIRECTIONAL BOREBY STA NLEY PIPELINE.
21026117300 | EMER - RETIRE 2'-4" P-LP | [5 empty] | 183.09 | 441.8134 | -258.7234 | 2021-01-01 | 2021-12-31 | 2021-04-19 | #N/A | RETIRE 2' OF 4" PL DUE TO DAMAGE
19026889001 | INSTALL 28'-8" PMLP | [5 empty] | 30769.7 | 17790.2899 | 12979.4101 | 2021-01-01 | 2021-12-31 | 2021-02-03 | #N/A
21026110200 | EMER - INSTALL 5'-3" PMIP | [5 empty] | 880.36 | 7868.6589 | -6988.2989 | 2021-01-01 | 2021-12-31 | 2021-04-20 | #N/A | INSTALLED 5' OF 3" PLASTIC. TESTED AT 90PSIG FOR 1HR.
21026110300 | EMER - RETIRE 5'-3" PIP | [5 empty] | 7215.11 | 441.8134 | 6773.2966 | 2021-01-01 | 2021-12-31 | 2021-04-20 | 2021-04-21 | RETIRED 5' OF 3" PLASTIC DUE TO PAC CLAMPS LEAKING.
18026762102 | INSTALL NEW GMB | [5 empty] | 551963 | 544123.4415 | 7839.5585 | 2021-01-01 | 2021-12-31 | 2021-04-27 | #N/A | GCCC TICKET NOT REQUIRED AT THIS TIME 1/11/21 CFARIS 1/13/21 GCCC TICKET NOT REQUIRED AT THIS TIME CFARIS 1/26/21 GCCC TICKET NOT REQUIRED FOR THIS JOB CFARIS DID NOT ENTER PREMISE CCC TICKET NOT REQUIRED 3/8/21 CFARIS 3/10/21 GCCC TICKET NOT REQUIRED CFARIS CCC TICKET NOT REQUIRED 3/16/21 CFARIS CCC TICKET NOT REQUIRED 3/18/21 CFARIS CMCHOLAN 4-13-2021 CCC TICKET NOT REQUIRED ON 9/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK. ERX PLACED IN SERVICE ON 9/13/2021 CFARIS
20026978900 | RETIRE GMB SETTING | [5 empty] | 0 | 83.3805 | -83.3805 | 2021-01-01 | 2021-12-31 | 2021-09-20 | 2021-09-20 | JOB WAS ON HOLD UNTIL 2021 GCCC TICKET NOT REQUIRED ON 9/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026951300 | INSTALL 6200' OF 2"PMMP MAIN | [5 empty] | 1175556.48 | 1180648.1173 | -5091.6373 | 2021-01-01 | 2021-12-31 | 2021-01-26 | 2021-05-17
20026979000 | RETIRE SERVICE | [5 empty] | 2450.84 | 83.3805 | 2367.4595 | 2021-01-01 | 2021-12-31 | 2021-04-22 | 2021-04-22 | THIS IS PAPER KILL ONLY
21026104600 | RETIRE PIT REG STATION 1016 | [5 empty] | 188917.56 | 138142.7376 | 50774.8224 | 2021-01-01 | 2021-12-31 | 2021-04-23 | 2021-05-14 | REMOVED MONITOR AND CONTROL REG. AND BLIND FLANGED, MONITORED 30 MIN. DUE TO NOT BEING ABLE TO BLIND FLANGE BYPASS, ADVISED CONSTRUCTION ABOUT BYPASS CCC 20355 CMCHOLAN RHAYES NGINTER BLONE 4-23-2021 REGULATORS REMOVED AND BLIND FLANGED ON 4/23/2021 PIPING AND VAULT ABANDONED AND REMOVED BY CONSTRUCTION ON 5/12/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/14/2021 GCCC TICKET NOT REQUIRED ON 5/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS TWALKER/KY 11-15-21: LEVEL 2 VARIANCE FORM ADDED TO WMS.DOCS. JOB OVER RUN DUE TO $41,500 FROM LP/OPP MATERIAL CHARGED TO THIS ORDER. ADDITIONAL $11,000 IN COMPANY HIGHER THAN PLANNED ESTIMATE.
21026120900 | INSTALL 5' - 3" PMLP | [5 empty] | 1085.98 | 1134.2677 | -48.2877 | 2021-01-01 | 2021-12-31 | 2021-04-26 | 2021-04-26
21026121000 | RETIRE 5' - 3" PMLP | [5 empty] | 0 | 58.9085 | -58.9085 | 2021-01-01 | 2021-12-31 | 2021-04-26 | 2021-04-26
21026118700 | EMER-INSTALL 2' OF 2"PMMP MAIN | [5 empty] | 2106.1 | 4434.6174 | -2328.5174 | 2021-01-01 | 2021-12-31 | 2021-04-27 | 2021-04-29 | REFERENCE JOB# 21906644500 FOR COMMENTS AND JOB INFO DMARSTO 4/27/21
20026964102 | INSTALL 4000' OF 12"CSHP MAIN | [5 empty] | 1045900.23 | 909258.0027 | 136642.2273 | 2021-01-01 | 2021-12-31 | 2021-01-06 | 2021-05-11 | TWALKER/KY 09-21-21: JOB OVER RUN DUE TO ADDITIONAL ENVIRONMENTAL AND SITE CLEANUP ON SITE DUE TO RAIN DURING CONSTRUCTION, THIS ADDED EXTRA $40,000 TO CONTRACT COST, PROJECT REQUIRED 2 COMPANY COORDINATORS BUT WAS PLANNED FOR 1 ADDED $35,000 IN LABOR COST AND SEGA INCREASED BY $33,000.
21026118800 | EMER-RETIRE 2' OF 2"PAMP MAIN | [5 empty] | 755.09 | 78.808 | 676.282 | 2021-01-01 | 2021-12-31 | 2021-04-27 | 2021-04-29 | REFERENCE JOB# 21906644500 FOR COMMENTS AND JOB INFO DMARSTO 4/27/21
20026964200 | RETIRE 1200' OF 12"BSHP MAIN | [5 empty] | 3603.11 | 84.1799 | 3518.9301 | 2021-01-01 | 2021-12-31 | 2021-01-06 | 2021-05-11
18026823200 | INST. FN 164 EXTRA LP OPP | [5 empty] | 53697.68 | 24062.1646 | 29635.5154 | 2021-01-01 | 2021-12-31 | 2021-04-27 | 2021-07-07 | TICKET CALLED IN BY JPASLEY NOT ON SITE ROUNDED UP PARTS. GCCC# 19363 CCC# 19363 CCC# 20802 NOT ON SITE CCC# 21442 P2P WITH GAS CONTROL REGULATOR AND ER350 INSTALLED BY WADE SHIMFESSEL ON 4/27/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/21 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026823300 | RET. FN 164 FOR EXTRA LP OPP | [5 empty] | 228.05 | 53.6219 | 174.4281 | 2021-01-01 | 2021-12-31 | 2021-04-27 | 2021-07-07 | REGULATOR REPLACED BY WADE SHIMFESSEL ON 4/27/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/21 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026989800 | INSTALL 800'-2" PMMP | [5 empty] | 33245.15 | 25809.9211 | 7435.2289 | 2021-01-01 | 2021-12-31 | 2021-04-22 | 2021-05-10
21026121100 | INSTALL 5' - 4" PMMP | [5 empty] | 2417.89 | 2822.803 | -404.913 | 2021-01-01 | 2021-12-31 | 2021-04-28 | 2021-04-28
21026121200 | RETIRE 5' - 4" PMLP | [5 empty] | 0 | 58.9085 | -58.9085 | 2021-01-01 | 2021-12-31 | 2021-04-28 | 2021-04-28
20026979300 | RETIRE 12'-8" CSHP | [5 empty] | 3655.53 | 134.3805 | 3521.1495 | 2021-01-01 | 2021-12-31 | 2021-04-13 | 2021-04-21
21026108100 | INSTALL 20' OF 3" PMMP | [5 empty] | 70757.52 | 21676.4521 | 49081.0679 | 2021-01-01 | 2021-12-31 | 2021-04-12 | 2021-05-06 | AWEBER/KY 09/21/2021: PROXIMITY OF LP MAIN TO MP MAIN RESULTED IN AN ACTUAL FOOTAGE INSTALL OF 320'-PMMP IN ORDER TO SEPERATE AND INSTALL FITTINGS AS NEEDED. UNABLE TO REVISE WMS JO DUE TO UNPAID MATERIAL INVOICES AND JO COMP LETION STATUS AT THE TIME.
21026108200 | RETIRE 20' OF 3" BSMP | [5 empty] | 4.6 | 56.3197 | -51.7197 | 2021-01-01 | 2021-12-31 | 2021-04-12 | #N/A
19026874200 | INSTALL 4600' OF 2"/4"/6"PMMP | [5 empty] | 148082.56 | 193673.3471 | -45590.7871 | 2021-01-01 | 2021-12-31 | 2021-03-17 | 2021-05-13 | TWALKER/KY 11-15-21: PROJECT UNDER RUN WAS DUE TO LESS ROCK ON SITE THAN PL ANNED AND NO STREET/HARD SURFACE REPAIRS REQUIRED THAT LOWER CONTRACT COST BY $25,000. LACK OF ROCK AND HARD SURFACE REPAIRS SPED UP CONSTRUCTION TIME AND LOWER COMPANY COST BY $XXXX AND SEGA WAS $4000 LOWER THAN ESTIMATE. COMPANY COST LOWER BY $3000 THAN ESTIMATE.
20026954500 | INSTALL 72' OF 4"CSHP MAIN | [5 empty] | 50107.73 | 48741.5249 | 1366.2051 | 2021-01-01 | 2021-12-31 | 2021-04-12 | #N/A
20026955701 | INSTALL 3,945'-4"/2" PMMP | [5 empty] | 702217.99 | 724040.648 | -21822.658 | 2021-01-01 | 2021-12-31 | 2021-11-18 | #N/A
21026122500 | EMER-INSTALL 5' OF 4"PMLP MAIN | [5 empty] | 9606.89 | 6150.5343 | 3456.3557 | 2021-01-01 | 2021-12-31 | 2021-05-11 | 2021-05-11 | CONTRACTOR HIT 040 PLASTIC MAIN WITH EXCAVATOR. SQUEEZED OFF TO MAKE SAFE. REPLACED 5FT OF 040 P LP. TESTED MAIN FOR 20MINS AT 90LBS.TEST OK.SOAP TEST FINAL TIE INS AT OP. TEST OK.BHB NGF.WORKED WITH CAPITAL JO AND TIE IN PLAN TWALKER/KY 06-28-21: THIS PROJECT WAS GENERATED FROM 3RD PARTY DAMAGE FROM A CONTRACTOR REPLACING STORM/SEWER AT THE INTERSECTION OF MILLER AND 2ND ST. CONTRACTOR DAMAGE SMALL OF MAIN FIRST DAY AND THE VERY NEXT DAY HIT/DA MAGE THE REPAIR MAIN. THAT MAIN WAS NEVER BOOKED OR MAPPED IN WMS. ALL WORK AND COST CAPTURED ON THIS JOB ORDER. WE HAVE TWO TIE INS AND TEST.
21026122700 | EMEG-INSTALL 5' OF 4"PMMP MAIN | [5 empty] | 3856.8 | 5607.5343 | -1750.7343 | 2021-01-01 | 2021-12-31 | 2021-05-17 | 2021-05-18 | RESPONDED OT MAIN LINE DAMAGE. INSTALLED 2' OF 4" PE MAIN LINE. PRESSURE TESTED MAIN @ 90PSIG FOR 20MINS PER FOL APPROVAL. TEST OK. SOAP TESTED LAST CONNECTION @ OP. TEST OK. CONTENT VERIFIED. PRESSURE VERIFIED @ 52PSIG DMAL
21026122600 | EMER-RETIRE 5' OF 4"PMLP MAIN | [5 empty] | 19.8 | 78.808 | -59.008 | 2021-01-01 | 2021-12-31 | 2021-05-10 | 2021-05-11 | CONTRACTOR HIT 040 PLASTIC MAIN WITH EXCAVATOR. SQUEEZED OFF TO MAKE SAFE. REPLACED 5FT OF 040 P LP. TESTED MAIN FOR 20MINS AT 90LBS.TEST OK.SOAP TEST FINAL TIE INS AT OP. TEST OK.BHB NGF.WORKED WITH CAPITAL JO AND TIE IN PLAN
21026122800 | EMER-RETIRE 5' OF 4"PMMP MAIN | [5 empty] | 210.25 | 78.808 | 131.442 | 2021-01-01 | 2021-12-31 | 2021-05-17 | 2021-05-18 | RESPONDED TO MAIN LINE DAMAGE. INSTALLED 2' OF 4" PE MAIN LINE. PRESSURE TESTED MAIN @ 90PSIG. FOR 20MINS PER FOL APPROVAL. TEST OK. SOAP TESTED FINAL CONNECTION @ OP. TEST OK. CONTENT VERIFIED. VERIFIED PRESSURE @52PSIG
20026951400 | RETIRE 7600' OF 4"CI/BSLP MAIN | [5 empty] | 142.7 | 165.7874 | -23.0874 | 2021-01-01 | 2021-12-31 | 2021-01-25 | #N/A
20026953701 | INSTALL 6100' OF 2"/4"PMMP | [5 empty] | 1646234.22 | 1430757.5003 | 215476.7197 | 2021-01-01 | 2021-12-31 | 2021-10-14 | #N/A | TWALKER/KY 05-04-22: JOB OVER RUN DUE TO $65,000 SPEND ON OFF DUTY POLICE DUE TO HIGH CRIME/TRAFFIC AREA, STATE REQUIRED MILL/PAVING OF HOLME ST INCREASED CONTRACT COST BY $85,000. SEGA INCREASED BY $51,000 OVER EST.
21026104400 | INSTALL 2"SS TO RETIRE INLET | [5 empty] | 24511.65 | 37406.9466 | -12895.2966 | 2021-01-01 | 2021-12-31 | 2021-05-10 | 2021-05-13
21026123600 | REPLACE MAIN - LEAKAGE D253626 | [5 empty] | 2711.68 | 5432.0527 | -2720.3727 | 2021-01-01 | 2021-12-31 | 2021-05-12 | 2021-05-13
21026123700 | EMER 10'-2" PMLP | [5 empty] | 0 | 85.0408 | -85.0408 | 2021-01-01 | 2021-12-31 | 2021-05-12 | 2021-05-13
21026118000 | INSTALL 4" SS | [5 empty] | 13617.82 | 29193.606 | -15575.786 | 2021-01-01 | 2021-12-31 | 2021-05-13 | 2021-05-14 | 4"SHORTSTOP INSTALLET BY RLA TESTED AND TAPPED BYCOMPANY 90 PSIG 15 MIN TEST NITROGN AS MEDIUM
21026104500 | RETIRE 7' OF 2"BSMP MAIN | [5 empty] | 72.67 | 80.8842 | -8.2142 | 2021-01-01 | 2021-12-31 | 2021-05-10 | 2021-05-13
18026837600 | INST. FN 176 EXTRA LP OPP | [5 empty] | 59791.79 | 35378.1646 | 24413.6254 | 2021-01-01 | 2021-12-31 | 2021-05-13 | 2021-07-07 | CONTROL SHEET 008281 PAID ON 04/23/20 THURSDAY TO COVER 04/24/20 FRIDAY CONTROL SHEET008307 PAID ON 04/30/20 THURSDAY TO COVER 05/01/20 FRIDAY NOT ON SITE GETTING PARTS FOR JOB CCC# 23134 CCC# 23265 CCC# 23459 CCC# 25857 REGULATORS INSTALLED BY WADE SHIMFESSEL ON 5/13/2021 EC350 INSTALLED BY WADE SHIMFESSEL ON 5/14/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/2021 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS *EXISTING Y STRAINER STRAINER GASKET NOT INSTALLED
18026837700 | RET. FN 176 FOR EXTRA LP OPP | [5 empty] | 0 | 53.9767 | -53.9767 | 2021-01-01 | 2021-12-31 | 2021-05-13 | 2021-07-07 | REGULATORS REPLACED BY WADE SHIMFESSEL ON 5/13/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/2021 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026124400 | EMER-INSTALL 2' OF 2"PMMP | [5 empty] | 1470.21 | 2935.5264 | -1465.3164 | 2021-01-01 | 2021-12-31 | 2021-06-30 | 2021-06-30
21026124500 | EMER-RETIRE 2' OF 2"PMMP | [5 empty] | 0 | 85.0408 | -85.0408 | 2021-01-01 | 2021-12-31 | 2021-06-30 | 2021-06-30
21026117900 | INSTALL 575' OF 2"PMIP MAIN | [5 empty] | 15668.74 | 17428.325 | -1759.585 | 2021-01-01 | 2021-12-31 | 2021-06-09 | 2021-06-09 | TWALKER/KY 06-28-21: THIS 555 WAS COMPLETED IN THE FIELD BUT PAPERWORK NOT COMPLETED OR MAPPED WHEN A CONTRACTOR DAMAGED A SECTION OF THIS NEW GAS MAIN. ALL WORK AND COST INCLUDED IN THIS JOB ORDER AND THE REASON FOR TWO TIE IN PLANS AND TEST FORMS.
21026122200 | INSTALL 925' OF 2"PMMP MAIN | [5 empty] | 41992.33 | 32784.4942 | 9207.8358 | 2021-01-01 | 2021-12-31 | 2021-06-09 | 2021-06-09 | TWALKER/KY 06-28-21: THIS 555 PROJECT WAS COMPLETED IN FIELD BUT PAPERWORK NOT SUBMITTED TO CLOSE OR MAPPEND WHEN LEAK ON THE NEW MAIN WAS DETECTED. WE BELIEVE THE MAIN LINE WAS DAMAGED DURING BACK FIELD. LEAK WAS REPAIRED BY CONSTRUCTION THAT IS REASON FOR TWO TIE IN PLANS AND TEST FORMS.ALL COST AND WORK CAPTURED UNDER THIS JOB ORDER.
21026112700 | INSTALL 350' OF 2"PMIP MAIN | [5 empty] | 37226.93 | 19281.66 | 17945.27 | 2021-01-01 | 2021-12-31 | 2021-05-27 | 2021-06-11
21026121700 | INSTALL 10' OF 6"PHHP MAIN | [5 empty] | 14437.27 | 16348.9255 | -1911.6555 | 2021-01-01 | 2021-12-31 | 2021-06-03 | 2021-06-07
20026982200 | INSTALL 5'-4"PMMP & 4'-4"CS | [5 empty] | 40958.2 | 42642.7946 | -1684.5946 | 2021-01-01 | 2021-12-31 | 2021-05-25 | 2021-06-08
21026121800 | RETIRE 10' OF 6"PHHP MAIN | [5 empty] | 0 | 80.3582 | -80.3582 | 2021-01-01 | 2021-12-31 | 2021-06-07 | 2021-06-07
20026982300 | ABANDON 5' - 4" CSMP | [5 empty] | 10.78 | 183.2963 | -172.5163 | 2021-01-01 | 2021-12-31 | 2021-06-07 | 2021-06-08
19026856900 | RETIRE 2166'- 2"-6" P/CS/BS | [5 empty] | 468.94 | 94.7274 | 374.2126 | 2021-01-01 | 2021-12-31 | 2021-03-04 | 2021-07-01
20026945400 | RETIRE 1431'-2"-4" BSLP | [5 empty] | 1066.35 | 94.7274 | 971.6226 | 2021-01-01 | 2021-12-31 | 2021-03-03 | 2021-06-10 | ABANDONMENTS OF MAINLINE WERE DONE WITH JO# 20-0269755-00.
21026121600 | INSTALL 100'-2" PMIP | [5 empty] | 16499.56 | 13861.3812 | 2638.1788 | 2021-01-01 | 2021-12-31 | 2021-06-09 | 2021-06-14
20026975300 | RETIRE 1900' OF 6"BSLP MAIN | [5 empty] | 1430.35 | 64.0836 | 1366.2664 | 2021-01-01 | 2021-12-31 | 2021-01-08 | 2021-06-11
20026985200 | INSTALL 6" PCF | [5 empty] | 9877.17 | 16280.811 | -6403.641 | 2021-01-01 | 2021-12-31 | 2021-06-12 | 2021-06-12
20026985300 | RETIRE 300'-6" CSMP | [5 empty] | 71.35 | 88.4533 | -17.1033 | 2021-01-01 | 2021-12-31 | 2021-06-02 | 2021-07-01
21026102900 | INSTALL 2400' OF 4"PMMP MAIN | [5 empty] | 104251.17 | 80646.5708 | 23604.5992 | 2021-01-01 | 2021-12-31 | 2021-05-20 | 2021-06-15
21026128500 | NSP - INSTALL 150'-2" PMLP | [5 empty] | 10156.16 | 16760.5972 | -6604.4372 | 2021-01-01 | 2021-12-31 | 2021-06-15 | 2021-06-15 | INSTALLED 150' 2"P. PRESSURE TESTED 90LBS 1HR. SOAP TESTED 2" EF COUPLING AT OP. PRESS. (11 IWC) 15MIN. PRESS. TEST 2X1 MONITORING TEE 90LBS 15MIN. SOAP TESTED MONITORING TEE END CAP OP. PRESS (11 IWC) 15MIN.
21026125400 | INSTALL 28' 4" PMMP | [5 empty] | 20147.11 | 10969.2814 | 9177.8286 | 2021-01-01 | 2021-12-31 | 2021-06-04 | 2021-06-15
21026125600 | INSTALL 28' 8" PMLP | [5 empty] | 23277.54 | 11805.2814 | 11472.2586 | 2021-01-01 | 2021-12-31 | 2021-06-04 | 2021-06-15
21026110600 | RETIRE 600'-2&3" PMLP | [5 empty] | 701.12 | 21928.4488 | -21227.3288 | 2021-01-01 | 2021-12-31 | 2021-07-08 | 2021-11-18
21026125500 | RETIRE 20' OF 4" PMMP | [5 empty] | 0 | 91.2676 | -91.2676 | 2021-01-01 | 2021-12-31 | 2021-06-07 | 2021-06-15
21026125700 | RETIRE 20' 8" PMLP | [5 empty] | 71.35 | 91.2676 | -19.9176 | 2021-01-01 | 2021-12-31 | 2021-06-15 | 2021-06-15
17026699800 | INSTALL ELEVATED BUS STOP ASSM | [5 empty] | 9561.04 | 61743.3758 | -52182.3358 | 2021-01-01 | 2021-12-31 | 2021-06-17 | 2021-08-17 | UNDERRUN EXPLANATION: THIS JOB ORDER WAS WORKED IN ONJUNCTION WITH ANOTHER JOB ORDER, 17-0269850-00, WHICH OVERRAN DUE TO THE CONTRACT LABOR BEING CHA RGED TO THAT JOB ORDER INSTEAD. THAT AMOUNT WAS APPROXIMATELY $40,000.
18026752700 | INSTALL VRG PILOT | [5 empty] | 5363.35 | 5404.3267 | -40.9767 | 2021-01-01 | 2021-12-31 | 2021-08-17 | 2021-08-17 | CCC #27769 CCC #28734
18026752800 | RETIRE | [5 empty] | 838.05 | 52.1634 | 785.8866 | 2021-01-01 | 2021-12-31 | 2021-08-17 | 2021-08-17
17026699900 | INSTALL NEW CH LINK FENCING | [5 empty] | 0 | 20572.3069 | -20572.3069 | 2021-01-01 | 2021-12-31 | 2021-06-17 | 2021-08-17
17026698500 | INSTALL VRG PRESS CONT EQUIPMT | [5 empty] | 247791.39 | 128512.8191 | 119278.5709 | 2021-01-01 | 2021-12-31 | 2021-06-11 | 2021-08-17 | CC# 27659. 6/11/21 DSASH CCC #27659 CC# 27769. 6/14/21 DSASH CC# 27972. 6/16/21 DSASH CC# 28248. 6/17/21 DSASH CCC #28248 CCC #28445 CC# 28445. 6/18/21 DSASH CC# 28787. 6/23/21 DSASH CCC #28787 NOT AT STATION OFF SITE WORKING ON PAPERWORK FOR JOB 7/1/2021 GCCC TICKET NOT REQUIRED NOT AT STATION OFF SITE COMPLETING PAPERWORK 7/19/21 AND 8/17/21 CFARIS
17026698600 | RETIRE EXIST PRESS CONT EQUIPM | [5 empty] | 299.36 | 131.3267 | 168.0333 | 2021-01-01 | 2021-12-31 | 2021-08-17 | 2021-08-17
19026856800 | INSTALL 3659'-2",4"&6" PMMP | [5 empty] | 1309555.48 | 1978069.5146 | -668514.0346 | 2021-01-01 | 2021-12-31 | 2020-11-04 | 2021-06-28 | W. 2ND ST SEING TIES WILL NEED TO BE UPDATED ONCE ROAD CONSTRUCTION PROJECT IS COMPLETE. ALL POLES AND MANHOLES ARE BEING MOVED. OVERRUN EXPLANATION HAS BEEN COMPLETE AND LOADED INTO WMSDOCS WORKSPACE. D. LEMONS 12/23/2021
21026117400 | INSTALL 190' - 4" PMMP SL | [5 empty] | 40096.06 | 22441.9346 | 17654.1254 | 2021-01-01 | 2021-12-31 | 2021-06-14 | #N/A | INSTALLED 243'OF 4"PMP FOR SL TO FEED PSID 501307207-CAPPED AND BURRIED END OF SL FOR FUTURE TIE IN/INSTALLATION OF RISER AND SETTING ONCE FURTHER SITE CONSTRUCTION IS COMPLETED,PER CG ENGINEER J TOY AND CONSTRUCTION SITE GC- LINE MARKER WITH WIRE AT TAP,WIRE IN VALVE BOX,AND MARKER BALLS AT ALL CHANGES OF DIRECTIONAND END OF SL INSTALLED FOR LOCATABILITY
18026781701 | INSTALL MONITOR/CONTROL REGS | [5 empty] | 141447.12 | 99301.7623 | 42145.3577 | 2021-01-01 | 2021-12-31 | 2021-06-05 | 2021-06-22 | CCC TICKET 27187 CCC #27342 CCC #27472 CCC #27636 CCC #27973 CCC TICKET NOT REQUIRED NOT AT STATION 8/4/21
18026781800 | ABANDON REGULATORS | [5 empty] | 0 | 56.3894 | -56.3894 | 2021-01-01 | 2021-12-31 | 2021-06-22 | 2021-06-22
19026860400 | INSTALLING I&C EQUIPMENT | [5 empty] | 174669.84 | 222748.2628 | -48078.4228 | 2021-01-01 | 2021-12-31 | 2021-06-09 | 2022-08-22 | CCC #27973 CCC #28142 CCC # 28275 CCC #28378 CCC #28665 CCC TICKET NOT REQUIRED NOT AT STATION 8/4/21
19026860500 | RETIRE I&C EQUIPMENT | [5 empty] | 511.34 | 84.9756 | 426.3644 | 2021-01-01 | 2021-12-31 | 2022-08-22 | 2022-08-22 | CC# 78206
21026110100 | INSTALL 900' OF 2"PMMP MAIN | [5 empty] | 24183.42 | 26234.9875 | -2051.5675 | 2021-01-01 | 2021-12-31 | 2021-06-16 | 2021-06-23
21026131001 | EMER-INSTALL 10' OF 2"PMMP | [5 empty] | 34645.29 | 34334.8702 | 310.4198 | 2021-01-01 | 2021-12-31 | 2021-06-22 | 2021-06-23
20026930800 | UPGRADE ELECTRONICS | [5 empty] | 4644.07 | 3038 | 1606.07 | 2021-01-01 | 2021-12-31 | 2021-06-21 | 2021-07-06 | REPLACED EFC NON SCADA MONITORED GMB ACCOUNT GCCC TICKET NOT REQUIRED
21026131300 | RETIRE EFC UNIT | [5 empty] | 0 | 74.8797 | -74.8797 | 2021-01-01 | 2021-12-31 | 2024-06-23 | 2021-07-06 | REPLACED EFC
21026122300 | INSTALL 100'-2" PMMP | [5 empty] | 26947.59 | 25260.7035 | 1686.8865 | 2021-01-01 | 2021-12-31 | 2021-06-16 | 2021-06-25
21026110500 | RETIRE 94'-12" CSMP | [5 empty] | 142.7 | 85.5775 | 57.1225 | 2021-01-01 | 2021-12-31 | 2021-06-28 | 2021-06-30
21026117800 | RETIRE 117' - 4" PLP | [5 empty] | 11604.62 | 9954.0712 | 1650.5488 | 2021-01-01 | 2021-12-31 | 2021-06-28 | 2021-06-28 | ABN 102' OF 040 PL ML. TESTED 4' OF 040 W/ END CAPS FOR 1 HR @ 90# SOAP TESTED CONN PTS @ 11" WC. SOAP TESTED ALL TEE CAP AND END CAPS @ OP.
20026942700 | INSTALL I&C EQUIPMENT | [5 empty] | 15613 | 16155.4774 | -542.4774 | 2021-01-01 | 2021-12-31 | 2021-06-28 | 2021-12-10 | CCC # 28876 CC#29408. 6/28/21 DSASH CCC # 32222 INITIAL COMMISSIONING BY SHANE GIORDANO PAPERWORK COMPLETED BY CYNTHIA FARIS ON 12/10/21 PAPERWORK ON HOLD AWAITING ISO SKETCH
21026130200 | EMER-INSTALL 5'-2" PMIP/CSIP | [5 empty] | 7558.85 | 6178.4541 | 1380.3959 | 2021-01-01 | 2021-12-31 | 2023-03-24 | 2023-03-31
21026130300 | EMER-RETIRE 5'-2" BSIP | [5 empty] | 230.72 | 410.7144 | -179.9944 | 2021-01-01 | 2021-12-31 | 2023-03-31 | 2023-03-31
21026110400 | INSTALL 100'-12" CSMP | [5 empty] | 188696.44 | 142453.0552 | 46243.3848 | 2021-01-01 | 2021-12-31 | 2021-06-03 | 2021-06-30 | OVERRUN EXPLANATION: PROJECT OVERRAN DUE TO FLAGGER TIME AND FLAGGER OVERTI ME. BUDGET VARIANCE EXPLANATION FORM LOADED INTO WMSDOCS WORKSPACE. D.LEMONS 12 /3/2021
20026942200 | RETIRE GAUGE | [5 empty] | 0 | 91.4991 | -91.4991 | 2021-01-01 | 2021-12-31 | 2021-07-12 | 2021-07-12 | RETIRED PAPER RECORDING GAUGE AND INSTALLED ERX WORK COMPLETED ON 909 JOB ORDER WITH GCCC TICKET NUMBER 29962 GCCC TICKET NOT REQUIRED ON 7/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026942100 | INSTALL I&C EQUIPMENT | [5 empty] | 16401.86 | 16155.4774 | 246.3826 | 2021-01-01 | 2021-12-31 | 2021-06-29 | 2021-07-12 | CCC #29962 CCC #30339 INSTALLED ERX, RV50 MODEM, BATTERY AND SUPER SOLAR KIT GCCC TICKET NOT REQUIRED ON 7/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026941700 | RETIRE GAUGE | [5 empty] | 0 | 91.4991 | -91.4991 | 2021-01-01 | 2021-12-31 | 2021-12-10 | 2021-12-10 | ERX INSTALLED AND PAPER RECORDING GAUGE RETIRED BY DANNY ASH AND JOSH MULLINS PAPERWORK COMPLETED BY CYNTHIA FARIS PAPERWORK ON HOLD AWAITING CORRECT ISO SKETCH
20026941600 | INSTALL I&C EQUIPMENT | [5 empty] | 11237.56 | 16155.4774 | -4917.9174 | 2021-01-01 | 2021-12-31 | 2021-06-30 | 2021-12-10 | CC# 30132. ERX INSTALLED BY DANNY ASH AND JOSH MULLINS PAPERWORK COMPLETED BY CYNTHIA FARIS PAPERWORK ON HOLD AWAITING CORRECT ISO SKETCH
21026116900 | INSTALL 200'-2" PMLP | [5 empty] | 24792.54 | 39229.3021 | -14436.7621 | 2021-01-01 | 2021-12-31 | 2021-06-28 | 2021-07-06
21026123100 | INSTALL 175'-4" PMMP | [5 empty] | 53913.76 | 39889.572 | 14024.188 | 2021-01-01 | 2021-12-31 | 2021-06-24 | 2021-07-07
21026123200 | RETIRE 200'-4" BSMP | [5 empty] | 0 | 77.7619 | -77.7619 | 2021-01-01 | 2021-12-31 | 2021-07-07 | 2021-07-07
20026949900 | INSTALL 1100' - 2" PMMP | [5 empty] | 206985.91 | 207915.8181 | -929.9081 | 2021-01-01 | 2021-12-31 | 2021-05-25 | 2021-07-15
21026125200 | INSTALL 3" SS | [5 empty] | 5010.94 | 20373.572 | -15362.632 | 2021-01-01 | 2021-12-31 | 2021-07-08 | 2021-07-08
21026125100 | RETIRE 175' - 3" LP | [5 empty] | 0 | 88.1542 | -88.1542 | 2021-01-01 | 2021-12-31 | 2021-07-08 | 2021-07-08
21026118600 | INSTALL 600' OF 2"PMMP MAIN | [5 empty] | 65051.29 | 37159.65 | 27891.64 | 2021-01-01 | 2021-12-31 | 2021-06-23 | 2021-07-13
19026856100 | RETIRE GAUGE | [5 empty] | 0 | 73.6972 | -73.6972 | 2021-01-01 | 2021-12-31 | 2021-09-20 | 2021-09-20 | WAITING ON PE APPROVAL AND ISO SKETCH CCC TICKET NOT REQUIRED ON 9/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026110900 | INSTALL REPLACEMENT FENCE | [5 empty] | 4971.16 | 44982.9906 | -40011.8306 | 2021-01-01 | 2021-12-31 | 2021-06-28 | 2021-07-09 | CCC# 30433 MONITORED FENCE INSTALLATION CCC# 30433 CCC# 30596 CC# 30596 MONTOR STATION CCC# 30956 NEW FENCE INSTALLED WSHIMFESSEL 07-09-2021 UNDERRUN EXPLANATION: COST WAS SIGNIFICANTLY LESS THAT WHAT THE CONTRACTOR HAD ESTIMATED OVER THE PHONE.
20026942000 | INSTALL I&C EQUIPMENT | [5 empty] | 14182.01 | 16155.4774 | -1973.4674 | 2021-01-01 | 2021-12-31 | 2021-07-09 | 2021-09-20 | CCC# 30920 CCC TICKET NOT REQUIRED ON 9/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026977101 | INSTALL 11,500' OF 2"/4"PMMP | [5 empty] | 1143604.07 | 926814.1047 | 216789.9653 | 2021-01-01 | 2021-12-31 | 2021-04-27 | 2021-12-15 | TWALKER/KY 03-02-22: PROJECT COST OVER RUN DUE TO ADDITIONAL CONSTRUCTION COORINATOR ON SITE DURING CONSTRUCTION ADDED $65,000 IN LABOR COST, SEWER VIDEO FOR MAIN/SL BY BUCHANAN WAS $86,000 HIGHER THAN ESTIMATE, ADDITIONAL FLAGGING AND HARD SURFACE REPAIRS ADDED $25,000 TO CONTRACT COST. FINALLY SEGA WAS $35,000 HIGHER THAT PLANNED COST.
21026109600 | INSTALL 351'-2" PMMP | [5 empty] | 28594.76 | 20339.7093 | 8255.0507 | 2021-01-01 | 2021-12-31 | 2021-07-12 | 2021-07-15
20026950000 | RETIRE 1430' OF 2"/3" BS-MP | [5 empty] | 2502.68 | 81.9085 | 2420.7715 | 2021-01-01 | 2021-12-31 | 2021-07-14 | 2021-07-15
20026942800 | RETIRE GAUGE | [5 empty] | 0 | 91.4991 | -91.4991 | 2021-01-01 | 2021-12-31 | 2021-07-16 | 2021-12-10 | PAPERWORK COMPLETION ON HOLD AWAITING ISO SKETCH
21026127800 | INSTALL 500'-2" PMMP | [5 empty] | 47089.22 | 43810.3768 | 3278.8432 | 2021-01-01 | 2021-12-31 | 2021-07-14 | 2021-07-22
21026124600 | INSTALL 3" OUTLET VALVE | [5 empty] | 28606.82 | 34892.3468 | -6285.5268 | 2021-01-01 | 2021-12-31 | 2021-07-13 | 2021-07-19
21026124700 | RETIRE 4' OF 3"BSIP MAIN | [5 empty] | 0 | 86.5975 | -86.5975 | 2021-01-01 | 2021-12-31 | 2021-07-19 | 2021-07-19
21026123300 | INSTALL 125'-2" PMMP | [5 empty] | 36910.92 | 28847.4767 | 8063.4433 | 2021-01-01 | 2021-12-31 | 2021-07-12 | 2021-07-20
21026123400 | RETIRE 160'-4" PMMP | [5 empty] | 0 | 77.7619 | -77.7619 | 2021-01-01 | 2021-12-31 | 2021-07-16 | 2021-07-20
21026124800 | INSTALL INLET/OUTLET BLOCK VLV | [5 empty] | 20343.89 | 13873.2524 | 6470.6376 | 2021-01-01 | 2021-12-31 | 2021-07-08 | 2021-07-19 | CCC# 30839 CCC# 31113 CCC# 31169 IN PROGRESS CCC# 31169 CC# 31169 CC-31326 CC-31492 CCC# 31755 CC-31755 NOT ON SITE- OFFICE ISO UPDATE CAP WORK COMPLETED BY WADE SHIMFESSEL ON 7/19/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/21/20 GCCC TICKET NOT REQUIRED ON 7/21/20 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS 7/21/20
21026113600 | RETIRE INLET/OUTLET BLK VALVES | [5 empty] | 0 | 88.1542 | -88.1542 | 2021-01-01 | 2021-12-31 | 2021-07-19 | 2021-07-19 | JOB COMPLETED BY WADE SHIMFESSEL ON 7/19/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/21/21 GCCC TICKET NOT REQUIRED ON 7/21/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026993100 | RETIRE 229' - PMMP | [5 empty] | 0 | 103.8156 | -103.8156 | 2021-01-01 | 2021-12-31 | 2021-07-20 | 2021-11-12
20026971100 | INSTALL 3300' OF 2"/4"PMMP MN | [5 empty] | 755817.87 | 877421.2279 | -121603.3579 | 2021-01-01 | 2021-12-31 | 2021-05-12 | 2022-03-18 | TWALKER/KY 05-04-22: JOB ORDER RUN DUE TO NO PAVING/HARD SURFACE REPAIRS HA VE BEEN STARTED AT THIS TIME. THIS IS JOINT PAVING RESTORATION WITH CITY OF LEXINGTON AND KY AMERICAN WATER. LOOK FOR COST TO BOOK LATE SUMMER 2022
21026137100 | RETIRE 4'-8" BSLP | [5 empty] | 0 | 177.6312 | -177.6312 | 2021-01-01 | 2021-12-31 | 2021-07-23 | 2021-08-18
21026132100 | INSTALL 600'-4" PMMP | [5 empty] | 75178.06 | 159985.8979 | -84807.8379 | 2021-01-01 | 2021-12-31 | 2021-07-22 | 2021-10-01 | INSTALLED 573' OF 4" PL MP AND 9' OF 2" PL MP TESTED 90 PSIG 2 HRS SOAP TESTED FINAL CONN OP 44 PSIG UNDERRUN EXPLANATION: A SIGNIFICANT UNIT OF COST WAS THE PLANNED ROCK BORE BUT THE CREW WAS ABLE TO AVOID THE NEED FOR A ROCK BORE, THE JOB DURATION ESTIMATE TOOL ALSO PLANNED FOR 120 HOURS OF LABOR AND THE CREW COMPLETED THE JOB IN 60 HOURS AND SOME CREW MEMBERS WERE NOT NEEDED THE ENTIRE DURATION OF THE JOB.
21026132200 | RETIRE 450'-4" P-MP | [5 empty] | 212.81 | 875.427 | -662.617 | 2021-01-01 | 2021-12-31 | 2021-08-19 | 2021-10-01 | RETIRED 487' OF 4" PL MP
18026808800 | INST. FN 259 EXTRA LP OPP | [5 empty] | 258499.79 | 23795.1646 | 234704.6254 | 2021-01-01 | 2021-12-31 | 2021-07-07 | 2021-08-02 | NOT ONSITE. NO GCCC TICKET REQUIRED. CMCOX 7/6/21 GCCC# 30701 CMCOX 7/7/21 NOT ONSITE. NO GCCC TICKET REQUIRED. CMCOX 7/8/21 CCC# 31111 GCCC# 31231 CMCOX 7/13/21 GCCC# 31380 GCCC# 31536 GCCC# 31616 DID NOT ENTER PIT. NO GCCC# REQUIRED. CMCOX 7/19//21 GCCC# 31756 CMCOX 7/20/21 CC# 32093 REGULATORS INSTALLED BY CHRIS COX 7/27/21 PAPERWORK COMPLETED BY CFARIS 7/29/21 CCC# NOT REQUIRED BY CFARIS ON 7/29 OR 8/2 NOT AT STATION
18026808900 | RET. FN 259 FOR EXTRA LP OPP | [5 empty] | 0 | 53.9767 | -53.9767 | 2021-01-01 | 2021-12-31 | 2021-07-27 | 2021-07-29 | REGULATORS REPLACED BY CHRIS COX ON 7/27/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/29/2021 GCCC TICKET NOT REQUIRED ON 7/29/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026110700 | REPLACE FENCE | [5 empty] | 480.98 | 14980.1771 | -14499.1971 | 2021-01-01 | 2021-12-31 | 2021-07-29 | 2021-12-17 | CCC# 33097 - BLONE - 07/29/21 FENCE REPLACED BY INTERSTATE FENCE COMPANY PAPERWORK COMPLETED BY CYNTHIA FARIS ON 12/17/2021
21026111101 | INSTALL FENCE | [5 empty] | 5601.7 | 40000.9906 | -34399.2906 | 2021-01-01 | 2021-12-31 | 2021-07-29 | 2021-12-16 | CCC# 31858 , 31996 , 32095 , 32237 , 32396 , 32702 ALL USED DURING PROJECT BLONE - 07/29/21 FENCE INSTALLED BY INTERSTATE FENCE COMPANY PAPERWORK COMPLETED BY CYNTHIA FARIS 12/16/21 UNDERRUN EXPLANATION: THE COST ESTIMATE THAT THE CONTRACTOR PROVIDED TURNED OUT TO BE SIGNIFICANTLY LESS THAN THEY HAD ESTIMATED. GES 3/2/22
21026110800 | RETIRE FENCE | [5 empty] | 0 | 61.2976 | -61.2976 | 2021-01-01 | 2021-12-31 | 2021-12-17 | 2021-12-17 | FENCE REPLACED BY INTERSTATE FENCE COMPANY PAPERWORK COMPLETED BY CYNTHIA FARIS 12/17/2021
21026111200 | RETIRE FENCE | [5 empty] | 0 | 61.2976 | -61.2976 | 2021-01-01 | 2021-12-31 | 2021-12-16 | 2021-12-16 | FENCE REPLACED BY INTERSTATE FENCE COMPANY PAPERWORK COMPLETED BY CYNTHIA FARIS 12/16/21
21026125800 | REPLACE C18-5 E | [5 empty] | 96855.51 | 77241.44 | 19614.07 | 2021-01-01 | 2021-12-31 | 2021-07-07 | 2021-07-30
21026125900 | RETIRE C18-5 | [5 empty] | 38.57 | 91.2676 | -52.6976 | 2021-01-01 | 2021-12-31 | 2021-08-10 | 2021-07-30
21026122900 | INSTALL 8" SS | [5 empty] | 48788.62 | 30904.4019 | 17884.2181 | 2021-01-01 | 2021-12-31 | 2021-07-28 | 2021-07-30
20026981601 | INSTALL 9,950' OF 2"/4"/6"PMMP | [5 empty] | 3477462.23 | 3261487.9737 | 215974.2563 | 2021-01-01 | 2021-12-31 | 2022-05-23 | 2022-05-26
22026190700 | INSTALL 4" SS *PAPER ONLY*** | [5 empty] | 0 | 84.2578 | -84.2578 | 2021-01-01 | 2021-12-31 | 2021-08-02 | 2021-08-02 | FACILITY CREATED ON JO 20-0269816-01. UNABLE TO EDIT. SS ALREADY ABANDONED ON JO 22-0261909-00 BEFORE THIS JO WAS CREATED.
21026123800 | INSTALL 160'-4" CSLP/PMLP | [5 empty] | 86016.2 | 161313.4069 | -75297.2069 | 2021-01-01 | 2021-12-31 | 2021-07-26 | 2021-08-09 | UNDERRUN EXPLANATION: SIGNIFICANTLY LESS HARD SURFACE RESTORATION AND BACKFILL REQUIRED THAN ESTIMATED KYTC REQUIRED RELOCATION AND TOLD US NOT TO WORRY ABOUT THE MILL & OVERLAY THAT THEY WOULD DO THAT WHEN THEY COMPLETED THEIR PART OF THE PROJECT, THIS RESULTED IN A SIGNIFICANT AMOUNT OF THE COST VARIATION
21026135400 | INSTALL 100'-4" PL SL | [5 empty] | 12266.69 | 10216.5972 | 2050.0928 | 2021-01-01 | 2021-12-31 | 2021-08-04 | 2021-08-06
21026135300 | ABANDON 120'-4" PL SL | [5 empty] | 0 | 82.634 | -82.634 | 2021-01-01 | 2021-12-31 | 2021-08-04 | 2021-08-05
21026125300 | RETIRE 180'-4" BSLP | [5 empty] | 0 | 282.1429 | -282.1429 | 2021-01-01 | 2021-12-31 | 2021-08-04 | 2021-08-07 | COMMITT DATE WAS PUSHED OUT TILL END OF AUG.2021
20026981200 | INSTALL 1550' OF 2"PMMP MAIN | [5 empty] | 479750.56 | 414073.7744 | 65676.7856 | 2021-01-01 | 2021-12-31 | 2021-08-10 | 2021-09-28 | TWALKER/KY 05-04-22: JOB OVER RUN CAUSED BY ADDTIONAL $46,000 FOR SEWER CAMERA WORK, PROJECT TOOK LONGER TO COMPLETE DUE TO TRAFFIC AND URBAN SETTING INCREASED COMPANY LABOR BY $5000, SEGA $17000 HIGHER THAN ESTIMATE.
21026136100 | EMER-INSTALL 10'-2" PMMP | [5 empty] | 3664.07 | 5241.7163 | -1577.6463 | 2021-01-01 | 2021-12-31 | 2021-08-10 | 2021-08-10
21026136200 | EMER-RETIRE 10'-2" PMP | [5 empty] | 253.41 | 88.8156 | 164.5944 | 2021-01-01 | 2021-12-31 | 2021-08-10 | 2021-08-10 | RETIRED 2' OF DAMAGED 2" PMP MAIN
21026134400 | RETIRE 98' OF 2"PMMP MAIN | [5 empty] | 4653.06 | 3547.617 | 1105.443 | 2021-01-01 | 2021-12-31 | 2021-08-10 | 2021-08-10
21026132600 | INSTALL NEW TRANSMITTERS | [5 empty] | 14392.01 | 15506.2901 | -1114.2801 | 2021-01-01 | 2021-12-31 | 2021-08-11 | 2021-12-10 | CCC #34292 WAITING ON ISO
21026132700 | RETIRE DAMAGED TRANSMITTERS | [5 empty] | 0 | 82.634 | -82.634 | 2021-01-01 | 2021-12-31 | 2021-08-11 | 2021-12-10 | WAITING ON ISO SKETCH REPLACED TRANSMITTERS AND RV50 DAMAGED BY LIGHTENING
21026121900 | INSTALL 100'-2" PMIP | [5 empty] | 30760.67 | 26223.5353 | 4537.1347 | 2021-01-01 | 2021-12-31 | 2021-08-09 | 2021-08-13
21026130600 | INSTALL 350' OF 2"PMMP MAIN | [5 empty] | 42649.02 | 31312.2411 | 11336.7789 | 2021-01-01 | 2021-12-31 | 2021-08-03 | 2021-08-17
21026136800 | EMER-INSTALL 5' OF 4"PMMP | [5 empty] | 395.9 | 5949.1348 | -5553.2348 | 2021-01-01 | 2021-12-31 | 2021-08-17 | 2021-08-24 | INST 5' 4" P MP MAIN ACCORDING TO ENGINEERED TIE-IN PLAN AND GAS STANDARDS. WORKED ON 8/17/21. MCRAIG 8/24/21
21026136900 | EMER-RETIRE 5' OF 4"PAMP | [5 empty] | 5438.98 | 55.634 | 5383.346 | 2021-01-01 | 2021-12-31 | 2021-08-17 | 2021-08-24 | ABN 5' 4"P MP MAIN ACCORDING TO ENGINEERED TIE-IN PLAN. WORKED ON 8/17/21. MCRAIG 8/24/21
20026918001 | INSTALL ELECTRONICS | [5 empty] | 203885.41 | 78849.9064 | 125035.5036 | 2021-01-01 | 2021-12-31 | 2021-07-12 | 2021-08-17 | CC# 31091 CC# 34924 CC# 21685. 01-03-22 DSASH CC# 21685. 01-03-22 DSASH OVERRUN EXPLANATION: ASSUMED WE WOULD USE THE OLD BLOCK BUILDING BUT FOND T HAT IT WAS LEAKING SO HAD TO REPLACE WITH A NEW BUILDING.
22026160300 | RETIRED ELECTRONICS | [5 empty] | 422.53 | 75.9523 | 346.5777 | 2021-01-01 | 2021-12-31 | 2021-08-17 | 2021-08-17
21026136500 | RELOCATE 12' OF 4"PMLP MAIN | [5 empty] | 25628.84 | 10466.234 | 15162.606 | 2021-01-01 | 2021-12-31 | 2021-08-17 | 2021-08-18
21026136600 | RETIRE 6' OF 4"PMLP MAIN | [5 empty] | 0 | 85.7248 | -85.7248 | 2021-01-01 | 2021-12-31 | 2021-08-07 | 2021-08-18
21026137400 | RETIRE 120'-1" PMP - D304537 | [5 empty] | 399.97 | 3638.7915 | -3238.8215 | 2021-01-01 | 2021-12-31 | 2021-08-21 | 2021-08-21
20026977301 | INSTALL 12,100 OF 2"PMMP MAIN | [5 empty] | 1937357.64 | 1697987.4343 | 239370.2057 | 2021-01-01 | 2021-12-31 | 2021-03-11 | 2021-11-01
21026121500 | INSTALL 160'-2" PMIP | [5 empty] | 37719.27 | 21640.9206 | 16078.3494 | 2021-01-01 | 2021-12-31 | 2021-08-19 | 2021-08-24
21026107300 | INSTALL 140' OF 4"PMMP S/L | [5 empty] | 53188.18 | 57302.0236 | -4113.8436 | 2021-01-01 | 2021-12-31 | 2021-08-16 | 2021-11-11
21026107200 | RETIRE 33' OF 4"PMMP S/L | [5 empty] | 1.8 | 76.3208 | -74.5208 | 2021-01-01 | 2021-12-31 | 2021-08-16 | 2021-11-17
21026129400 | RETIRE 135' OF 8"CSMP MAIN | [5 empty] | 1142.2 | 151.2005 | 990.9995 | 2021-01-01 | 2021-12-31 | 2021-08-22 | 2021-09-01 | ABN 135' ON CS MP MAIN.
21026138400 | EMER-INSTALL 2' OF 1"PMMP MAIN | [5 empty] | 227.74 | 3122.8539 | -2895.1139 | 2021-01-01 | 2021-12-31 | 2021-08-25 | 2021-08-26
21026138500 | EMER-RETIRE 2'-1"PAMP MAIN | [5 empty] | 0 | 82.634 | -82.634 | 2021-01-01 | 2021-12-31 | 2021-08-25 | 2021-08-26
21026129500 | RETIRE 109' OF 4"BSLP | [5 empty] | 71.35 | 99.3208 | -27.9708 | 2021-01-01 | 2021-12-31 | 2021-06-23 | 2021-09-03 | ABN 4" BS LP MAIN PER GS
21026101501 | INSTALL 3800'-2",4"&6" PMMP | [5 empty] | 842479.02 | 710294.4849 | 132184.5351 | 2021-01-01 | 2021-12-31 | 2021-12-03 | 2022-05-05 | OVERRUN EXPLANATION: ENCOUNTERED MORE ROCK EXCAVATION THAN ESTIMATED AS WEL L AS THE ASSOCATED SPECIAL BACKFILL. PROJECT ALSO REQUIRED MORE SEWER CAMER A WORK THAN ESTIMATED.
21026997101 | INSTALL 125' OF 4"PMMP MAIN | [5 empty] | 118779.98 | 111178.7891 | 7601.1909 | 2021-01-01 | 2021-12-31 | 2021-08-23 | 2021-08-30
21026139100 | EMER - INSTALL 5'-4" PMMP | [5 empty] | 2800.66 | 6493.0322 | -3692.3722 | 2021-01-01 | 2021-12-31 | 2021-09-28 | 2021-09-29 | INSTALLED MAIN ON TESTED 90 PSIG 1 HOUR SOAP TESTED FINAL CONN OP 44 PSIG
21026139200 | EMER - RETIRE 5'-4" P-MP | [5 empty] | 5590.11 | 743.2708 | 4846.8392 | 2021-01-01 | 2021-12-31 | 2021-09-28 | 2021-09-29
21026109300 | INSTALL 300' OF 2"PMMP MAIN | [5 empty] | 26886.16 | 25871.1277 | 1015.0323 | 2021-01-01 | 2021-12-31 | 2021-08-26 | 2021-09-02
21026133300 | INSTALL 200'-2" PMIP | [5 empty] | 19749.69 | 14590.9404 | 5158.7496 | 2021-01-01 | 2021-12-31 | 2021-08-27 | 2021-09-02
20026975400 | INSTALL 2250'-2" PMMP | [5 empty] | 859560.09 | 623618.1819 | 235941.9081 | 2021-01-01 | 2021-12-31 | 2021-04-22 | 2021-11-16 | PROJECT COMPLETED ON 11-16-2021 D.LEMONS 3/2/2022: PROJECT OVERRUN WAS DUE TO ADDITIONAL TIME REQUIRED TO C OMPLETE PROJECT DUE TO MULTIPLE CONTRACTORS IN AREA DURING PROJECT. ESTIMA TED FOR 645 MAN HOURS, BUT REQUIRED 1018 MAN HOURS. ADDITIONAL $85K IN CONT RACT EXPENSES, $36K IN LABOR COSTS WHICH LEAD TO INCREASE OF $32K IN SEGA. THERE WAS A SLIGHT REDUCTION IN OTHER COST TO ACCOUNT FOR THE $147K OVERRUN .
21026118300 | INSTALL 210' OF 2"PMMP MAIN | [5 empty] | 17888.9 | 16739.4681 | 1149.4319 | 2021-01-01 | 2021-12-31 | 2021-09-07 | 2021-09-09
21026141000 | EMER - INSTALL 5'-4" PMMP | [5 empty] | 0 | 427 | -427 | 2021-01-01 | 2021-12-31 | 2021-09-08 | 2021-09-09
21026141100 | EMER - RETIRE 5'-4" PMMP | [5 empty] | 0 | 68.3073 | -68.3073 | 2021-01-01 | 2021-12-31 | 2021-09-08 | 2021-09-09
21026136300 | INSTALL 37'-2"/3" PMMP/CSMP | [5 empty] | 14615 | 33826.5433 | -19211.5433 | 2021-01-01 | 2021-12-31 | 2021-09-03 | 2021-09-20 | INSTALLED NEW 030 CS AND PE MAIN. TEST @ 90# FOR 1 HR, NO LEAKS. PURGED INT O SERVICE. STOP OFF AND REMOVED OLD MAIN. 3" WELD CAPS & 2" PE CAP SOAP TES T, NO LEAKS. WRAPPED MAIN. SWING TIES & EM BALLS. J HOWARD 9-20-21
21026136400 | RETIRE 29'-2"/3" CSMP/PMMP | [5 empty] | 83.24 | 826.7837 | -743.5437 | 2021-01-01 | 2021-12-31 | 2021-09-03 | 2021-09-13 | LEAK ON END OF STEEL MECH COMP END CAP. INSTALLED NEW 030 & 020 ST AND PE M L, TESTED AT 90# FOR 1 HR. SOAP TEST 030 AND 020 CAPS, NO LEAKS. BAR BANKS, NGF. INSTALLED ANODE, WRAPPED MAIN. J HOWARD 9-13-21
21026141200 | EMER-INSTALL 3'OF 6"PMLP MAIN | [5 empty] | 5901.09 | 4022.0999 | 1878.9901 | 2021-01-01 | 2021-12-31 | 2021-09-12 | 2021-09-15
21026141300 | EMER-RETIRE 3' OF 6"PLP MAIN | [5 empty] | 38.15 | 69.8875 | -31.7375 | 2021-01-01 | 2021-12-31 | 2021-09-12 | 2021-09-13
21026142000 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 11087.26 | 7513.9749 | 3573.2851 | 2021-01-01 | 2021-12-31 | 2021-09-14 | 2021-09-15
21026142100 | EMER - RETIRE 5'-3" PMMP | [5 empty] | 0 | 69.8875 | -69.8875 | 2021-01-01 | 2021-12-31 | 2021-09-14 | 2021-09-15
21026115700 | INSTALL 300' OF 2"PMMP MAIN | [5 empty] | 21541.85 | 22097.6064 | -555.7564 | 2021-01-01 | 2021-12-31 | 2021-09-13 | 2021-09-28
21026129800 | INSTALL 200'-2" PMMP | [5 empty] | 25563.52 | 21853.3833 | 3710.1367 | 2021-01-01 | 2021-12-31 | 2021-09-13 | #N/A
21026142300 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 11040.25 | 3984.9999 | 7055.2501 | 2021-01-01 | 2021-12-31 | 2021-09-15 | 2021-09-16
21026142400 | EMER - RETIRE 5'-2" PMP | [5 empty] | 133.69 | 69.8875 | 63.8025 | 2021-01-01 | 2021-12-31 | 2021-09-15 | 2021-09-16
21026118900 | INSTALL REGULATORS | [5 empty] | 4450.3 | 6803.6557 | -2353.3557 | 2021-01-01 | 2021-12-31 | 2021-09-16 | 2021-09-21 | CCC# 38381 REPLACED REGULATORS ON 9/16/2021 GCCC TICKET NOT REQUIRED ON 9/21/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026119000 | RETIRE REGULATORS | [5 empty] | 572.72 | 85.0089 | 487.7111 | 2021-01-01 | 2021-12-31 | 2021-09-16 | 2021-09-21 | REPLACED REGULATORS ON 9/16/21 CCC TICKET 38381 OBTAINED ON INSTALL JO CCC TICKET NOT REQUIRED ON 9/21/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026973700 | INSTALL 6150'-4" PMLP | [5 empty] | 2832541.47 | 2202632.8927 | 629908.5773 | 2021-01-01 | 2021-12-31 | 2021-04-27 | 2022-05-05 | ODOR READS TOOK AT 128 E 3RD ST, MAYSVILLE,KY - WITH SN-16040105 12/17- .6@10:40 - 12/18 .5@16:30 - 12/19 .6@11:30 - 12/20 .5@ 16:29 - 12/21 .5@17:12 - 12/22 .5@16:45 - 12/23 .6@12:27 - TJETT 12/23/21 LEVEL 2 BUDGET VARIANCE COMPLETED AND FILED IN WMSDOCS. D.LEMONS 10/3/2022
21026142500 | EMER-INSTALL 5' OF 2"PMMP | [5 empty] | 417.14 | 3297.6583 | -2880.5183 | 2021-01-01 | 2021-12-31 | 2021-09-19 | 2021-09-20
21026142600 | EMER-RETIRE 5' OF 2"PMP MAIN | [5 empty] | 263.29 | 69.8875 | 193.4025 | 2021-01-01 | 2021-12-31 | 2021-09-19 | 2021-09-20
21026113900 | INSTALL 1300' OF 2"/4"PMMP | [5 empty] | 34584.47 | 66451.1814 | -31866.7114 | 2021-01-01 | 2021-12-31 | 2021-09-07 | #N/A | MISSED COMMIT DATE DUE TO WEATHER UNDERRUN EXPLANATION: THE UNDERRUN VARIANCE IS DUE TO 50% ROCK EXCAVATION A ND 50% LESS DUST AND STONE. THE OVER HEAD EFFECT OF THESE REDUCTIONS ALSO PLAYED A FACTOR.
20026981300 | RETIRE 1600' OF 2"/3"BSLP MAIN | [5 empty] | 0 | 84.1799 | -84.1799 | 2021-01-01 | 2021-12-31 | 2021-08-10 | 2021-09-28
21026112100 | INSTALL 1025'- 2"/4"PHHP MAIN | [5 empty] | 192775.66 | 194441.8822 | -1666.2222 | 2021-01-01 | 2021-12-31 | 2021-07-26 | 2021-09-29
21026112200 | RETIRE 980' OF 4"CSHP MAIN | [5 empty] | 723.52 | 74.8797 | 648.6403 | 2021-01-01 | 2021-12-31 | 2021-07-26 | 2021-09-29
20026928000 | UPGRADE ELECTRONICS | [5 empty] | 7833.1 | 3038 | 4795.1 | 2021-01-01 | 2021-12-31 | 2021-09-23 | #N/A | REPLACED EFC AND UPSIZED METER TO 16M ALSO WORKED TP AND MGRP WHILE ON SITE
21026143000 | RETIRE EME FACILITY | [5 empty] | 0 | 63.4597 | -63.4597 | 2021-01-01 | 2021-12-31 | 2021-10-04 | 2021-10-04 | REPLACED EFC
20026955901 | INSTALL 215'-4" PMMP | [5 empty] | 63490.92 | 67929.8606 | -4438.9406 | 2021-01-01 | 2021-12-31 | 2021-06-29 | 2021-12-20
21026144300 | EMER - INSTALL 2' OF 2"PMIP | [5 empty] | 137.16 | 2750.8249 | -2613.6649 | 2021-01-01 | 2021-12-31 | 2021-09-25 | 2021-09-26
21026144400 | EMER - RETIRE 2' OF 2"PAIP | [5 empty] | 0 | 75.4968 | -75.4968 | 2021-01-01 | 2021-12-31 | 2021-09-25 | 2021-09-26
21026143400 | EMER-INSTALL 10'OF 4"PMIP MAIN | [5 empty] | 7913.03 | 7432.5408 | 480.4892 | 2021-01-01 | 2021-12-31 | 2021-09-26 | 2021-09-27
21026143900 | EMER-INSTALL 5'-2"PMMP | [5 empty] | 0 | 6000.6188 | -6000.6188 | 2021-01-01 | 2021-12-31 | 2021-10-24 | 2021-10-25
21026143500 | EMER-RETIRE 10' OF 4"PAIP MAIN | [5 empty] | 0 | 60.6987 | -60.6987 | 2021-01-01 | 2021-12-31 | 2021-09-26 | 2021-09-27
21026144000 | EMER-RETIRE 5'-2"PMMP | [5 empty] | 0 | 49.6987 | -49.6987 | 2021-01-01 | 2021-12-31 | 2021-10-24 | 2021-10-25
21026143700 | INSTALL 4'-4" PMLP | [5 empty] | 478.5 | 3297.2047 | -2818.7047 | 2021-01-01 | 2021-12-31 | 2021-12-18 | 2021-12-18 | INSTALLED 4' OF 4" PL LP MAIN LINE TESTED 90 PSIG 1 HOUR SOAP TESTED FINAL CONN OP 10" WC
21026143800 | RETIRE 4'-4" PMLP | [5 empty] | 44.74 | 295.4309 | -250.6909 | 2021-01-01 | 2021-12-31 | 2021-12-18 | 2021-12-18 | RETIRED MAIN DUE TO STEEL SADDLE TEE BIENG ON PL PIPE INSTALLED NEW SECTION OF PIPE
21026133100 | INSTAL 2" MOONEY REGS | [5 empty] | 11609.08 | 9907.1191 | 1701.9609 | 2021-01-01 | 2021-12-31 | 2021-09-28 | 2021-10-25 | REPLACED REGULATORS GCCC TICKET NOT REQUIRED
21026133200 | RETIRE FISHER 399 REGS | [5 empty] | 0 | 90.361 | -90.361 | 2021-01-01 | 2021-12-31 | 2021-09-28 | 2021-10-25 | REPLACED REGULATORS GCCC TICKET NOT REQUIRED
21026112900 | INSTALL 150' - 2" PMMP | [5 empty] | 14483.58 | 15892.286 | -1408.706 | 2021-01-01 | 2021-12-31 | 2021-09-27 | 2021-09-29
21026139800 | INSTALL 100'-2" PMIP | [5 empty] | 19936.66 | 27338.1249 | -7401.4649 | 2021-01-01 | 2021-12-31 | 2021-09-27 | 2021-10-01
20026976301 | INSTALL 6300' OF 2"/4"PMMP | [5 empty] | 2104702.57 | 2132943.4537 | -28240.8837 | 2021-01-01 | 2021-12-31 | 2021-09-16 | 2021-12-15
20026956000 | RETIRE 820'-2" PMMP | [5 empty] | 0 | 85.0089 | -85.0089 | 2021-01-01 | 2021-12-31 | 2021-06-29 | 2021-12-20
18026761400 | INSTALL BULLHORN RMU | [5 empty] | 2699.78 | 3922.4303 | -1222.6503 | 2021-01-01 | 2021-12-31 | 2018-07-26 | #N/A | RMU WAS INSTALLED ON 09/30/2021 BY TIM SWARTS. SYSTEM SERIAL # IS 132395. -OSS
20026956101 | INSTALL 2475'-8"/6"/4" PMLP | [5 empty] | 1344804.09 | 1170137.3307 | 174666.7593 | 2021-01-01 | 2021-12-31 | 2021-07-28 | 2021-12-20 | WIPE SAMPLE RESULTS WERE ENTERED ON THE INSTALL JOB INSTEAD OF THE RETIREMENT JOB. RETIREMENT RESULTS WERE ENTERED HERE.
21026132500 | INSTALL 450' OF 2"PMMP MAIN | [5 empty] | 31237.4 | 32348.6064 | -1111.2064 | 2021-01-01 | 2021-12-31 | 2021-09-21 | 2021-10-06
21026146300 | INSTALL 4'-4" PMLP | [5 empty] | 424.36 | 2206.8953 | -1782.5353 | 2021-01-01 | 2021-12-31 | 2021-10-07 | 2021-10-12 | INSTALLED 4' OF 4" PLASTIC MAIN. PRESSURE TESTED 90LBS FOR 1HR.
21026146400 | RETIRE 4'-4" P-LP | [5 empty] | 39.69 | 197.4141 | -157.7241 | 2021-01-01 | 2021-12-31 | 2021-10-07 | 2021-10-12
21026128601 | INSTALL 700' OF 2"PMMP MAIN | [5 empty] | 75716.28 | 57445.0039 | 18271.2761 | 2021-01-01 | 2021-12-31 | 2021-09-20 | 2021-10-13
20026980601 | INSTALL 16,200'-2"/4" PMMP | [5 empty] | 4720247.08 | 4665902.1359 | 54344.9441 | 2021-01-01 | 2021-12-31 | 2022-05-20 | 2022-09-29
21026147900 | EMER - INSTALL 5'-4" PMLP | [5 empty] | 3691.18 | 2422.8089 | 1268.3711 | 2021-01-01 | 2021-12-31 | 2021-11-16 | 2021-11-17 | INSTALLED 3FT OF 040 PLASTIC DUE TO 3 TEE'S BEING AN AOC. ALL TESTING INFO ON JO 21026147900 AND 21026148000 IN WMS DOCS.
21026148000 | EMER - RETIRE 5'-4" PLP | [5 empty] | 4.38 | 66.2207 | -61.8407 | 2021-01-01 | 2021-12-31 | 2021-11-16 | 2021-11-17 | INSTALLED 3FT OF 040 PLASTIC DUE TO 3 TEE'S BEING AN AOC. ALL TESTING INFO ON JO 21026147900 AND 21026148000 IN WMS DOCS.
21026994800 | RETIRE STATION 1502 | [5 empty] | 8422.17 | 4108.4893 | 4313.6807 | 2021-01-01 | 2021-12-31 | 2021-10-12 | 2021-11-02 | CCC# 37974 CCC#41227 CCC#41449 CCC# 41449 STATION ABANDONED ON 10/12/2021 PAPERWORK COMPLETED ON 11/2/2021 GCCC TICKET NOT REQUIRED ON 11/2/21 OFF SITE COMPLETING PAPERWORK CFARIS
21026107100 | INSTALL COMMUNICATIONS | [5 empty] | 3375.12 | 1691.2937 | 1683.8263 | 2021-01-01 | 2021-12-31 | 2021-10-11 | 2021-12-10 | CCC#41275 CCC#17228 INSTALLED SUPER SOLAR KIT AND BATTERY UPGRADED TO RV50 CELL MODEM CONVERTED TO FULL TIME MONITORING RTU TICKET NUMBER 4339
21026144200 | RETIRE 4280' OF 2"/3"PAMP MAIN | [5 empty] | 41269.58 | 14091.9275 | 27177.6525 | 2021-01-01 | 2021-12-31 | 2021-10-04 | 2021-11-17 | ABN 4280' P MP MAIN IN ACCORDNANCE WITH ENGINEERED TIE-IN PLAN AND GAS STANDARDS. SOAP TEST FINAL TIE-IN AT OP OK. BHB NGF. MCRAIG 10/13/21 TWALKER/KY 11-24-21: WMS WOULD NOT ALLOW FOR REVISION DUE TO UNPAID INVOICES, JOB ORDER OVER RUN DUE TO SCOPE OF WORK INCREASED AND WE RETIRED MORE UNLOCATED FIRST GENERATION PLASTIC MAIN THAN PLANNED AND SOME NEW EMPLOYEES WORKED WITH CREWS WITH INCREASED LABOR COST BY $14,000 OVER ESTIMATE
21026999700 | INSTALL 125' OF 2"PMMP MAIN | [5 empty] | 22070.53 | 28787.2695 | -6716.7395 | 2021-01-01 | 2021-12-31 | 2021-10-07 | 2021-10-13
21026999800 | RETIRE 115' OF 2"PMMP MAIN | [5 empty] | 0 | 81.0887 | -81.0887 | 2021-01-01 | 2021-12-31 | 2021-10-07 | 2021-10-14
21026137500 | INSTALL SOLAR PANEL | [5 empty] | 3598.81 | 4862.234 | -1263.424 | 2021-01-01 | 2021-12-31 | 2021-10-13 | 2021-10-13 | CC# 41497 RHAYES 10-13-2021 RHAYES 10-13-2021 CHANGED ER350 FROM CRY IN TO FULL TIME MONITOR INSTALLED SUPER SOLAR KIT AN D RV 50 MODEM CCOX 10-13-2021
21026147100 | EMER-INSTALL 6' OF 4"PMMP | [5 empty] | 604.21 | 1045.4141 | -441.2041 | 2021-01-01 | 2021-12-31 | 2021-10-24 | 2021-10-25
21026147200 | EMER-RETIRE 6' OF 4"PAMP MAIN | [5 empty] | 38.59 | 49.6987 | -11.1087 | 2021-01-01 | 2021-12-31 | 2021-10-24 | 2021-10-25
20026928700 | UPGRADE ELECTRONICS | [5 empty] | 8043.8 | 3038 | 5005.8 | 2021-01-01 | 2021-12-31 | 2021-10-18 | 2021-10-25 | REPLACED EFC
20026934400 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 | 2021-01-01 | 2021-12-31 | 2021-10-24 | 2021-10-25 | REPLACED EFC
21026146800 | RETIRE GMB #44535-AK STEEL | [5 empty] | 3852.12 | 2893.6188 | 958.5012 | 2021-01-01 | 2021-12-31 | 2021-10-11 | 2021-10-25 | ALL FACILITIES REMOVED FROM AK STEEL BY MATT RYAN AND SHANE GIORDANO MAINLINE/SERVICE LINE ABANDONED ON 10/18/2021 BY CONSTRUCTION SERVICES M&R PAPERWORK COMPLETED BY CYNTHIA FARIS ON 10/25/2021
21026146000 | INSTALL 404'-4"&6"PMMP | [5 empty] | 125105.39 | 224207.9887 | -99102.5987 | 2021-01-01 | 2021-12-31 | 2021-10-11 | 2021-12-16 | LEVEL 2 BUDGET VARIANCE EXPLANATION FORM HAS BEEN APPROVED AND LOADED INTO WMSDOCS WORKSPACE. D.LEMONS 3/3/2022
21026146100 | RETIRE 427'-4"BSLP | [5 empty] | 1537.36 | 63.4597 | 1473.9003 | 2021-01-01 | 2021-12-31 | 2021-10-11 | 2021-12-16
21026144600 | INSTALL 12" SS | [5 empty] | 25613.83 | 13660.0322 | 11953.7978 | 2021-01-01 | 2021-12-31 | 2021-10-18 | 2021-12-20 | INSTALLED 12" SS TO STOPPLE AND KILL 12" MAIN
21026144700 | RETIRE 1273'-6/12/16" CS/BSHP | [5 empty] | 167.43 | 388.1295 | -220.6995 | 2021-01-01 | 2021-12-31 | 2021-12-18 | 2021-12-20 | RETIRE 1207' OF 12" BS HP TO AK STEEL SOAP TESTED OP 113 PSIG
21026147700 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 2531.33 | 2686.3426 | -155.0126 | 2021-01-01 | 2021-12-31 | 2021-10-19 | 2021-10-20 | REPLACED 3' SECTION OF 2" PMP AFTER DIG IN. PRESSURE TESTED NEW MAIN AT 90 PSIG FOR 1 HOUR, SOAP TESTED FINAL TIE IN AT OP. OK 34 PSIG VERIFIED NRICHIE 10-20-21
21026147800 | EMER - RETIRE 5'-2" PMP | [5 empty] | 0 | 61.5191 | -61.5191 | 2021-01-01 | 2021-12-31 | 2021-10-19 | 2021-10-20
20026977400 | RETIRE 10,510'OF 4"/6"BSLP | [5 empty] | 1237.75 | 90.4074 | 1147.3426 | 2021-01-01 | 2021-12-31 | 2021-10-21 | 2021-11-01
20026928100 | UPGRADE ELECTRONICS | [5 empty] | 6063.75 | 3038 | 3025.75 | 2021-01-01 | 2021-12-31 | 2021-10-20 | 2021-11-16 | REPLACED EFC
20026933800 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 | 2021-01-01 | 2021-12-31 | 2021-10-20 | 2021-11-16 | REPLACED EFC
21026134100 | INSTALL 850' OF 2"PMMP MAIN | [5 empty] | 28285.71 | 40949.6064 | -12663.8964 | 2021-01-01 | 2021-12-31 | 2021-10-15 | 2021-10-21
21026148100 | EMER-INSTALL 4' OF 2"HPHP MAIN | [5 empty] | 2019.57 | 7370.71 | -5351.14 | 2021-01-01 | 2021-12-31 | 2022-01-23 | 2022-01-24
21026148200 | EMER-RETIRE 4' OF 2"HDHP MAIN | [5 empty] | 0 | 60.6987 | -60.6987 | 2021-01-01 | 2021-12-31 | 2022-01-23 | 2022-01-24
20026953800 | RETIRE 8800' OF 4"/6"BSLP MAIN | [5 empty] | 0 | 240.2222 | -240.2222 | 2021-01-01 | 2021-12-31 | 2021-10-22 | 2021-10-29
20026990800 | RETIRE INLET PIPING R 1502 | [5 empty] | 0 | 240.2222 | -240.2222 | 2021-01-01 | 2021-12-31 | 2021-10-22 | 2021-10-29
20026947301 | INSTALL 3,950' - 2" PMMP | [5 empty] | 1895184.87 | 1562557.4499 | 332627.4201 | 2021-01-01 | 2021-12-31 | 2021-07-12 | 2021-11-11 | TTOY/KY 3/2/22: OVERRUN EXPLANATION: FLAGGER OT ESTIMATED FOR 543 HOURS BUT ACTUAL WAS 1033 HOURS, CONTRACTOR CREWS HOURLY TIME WAS OVER ESTIMATE AT 167 EXTRA HOURS, SEGA HAD EXTRA $60,000 IN COST, COMPANY LABOR HAD ADDITIONAL $27,000 COST OVER ESTIMATE
21026144100 | INSTALL 350' OF 2"PMIP MAIN | [5 empty] | 19720.01 | 20004.6217 | -284.6117 | 2021-01-01 | 2021-12-31 | 2021-10-14 | 2021-10-27
20026931100 | UPGRADE ELECTRONICS | [5 empty] | 265.67 | 3038 | -2772.33 | 2021-01-01 | 2021-12-31 | 2021-10-27 | 2021-11-18 | REPLACED EFC
20026938100 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 | 2021-01-01 | 2021-12-31 | 2021-10-27 | 2021-11-18 | REPLACED EFC
20026947400 | RETIRE 5,000' - 4" CI/BS LP | [5 empty] | 71.35 | 103.8156 | -32.4656 | 2021-01-01 | 2021-12-31 | 2021-10-29 | 2021-11-12
19026889700 | INSTALL METER AND SETTING | [5 empty] | 54709.93 | 55012.1889 | -302.2589 | 2021-01-01 | 2021-12-31 | 2022-05-10 | 2022-05-11 | CCC #30162 CCC # 42745 CCC # 42908 CCC # 43108 CLENANER INSTALLED ON 10-29-2022 ALONG WITH PAPERWORK CO BY JOSH MULLINS ON 5-10-22
19026889800 | RETIRE METER AND SETTING | [5 empty] | 612.86 | 76.3408 | 536.5192 | 2021-01-01 | 2021-12-31 | 2021-06-30 | 2022-05-11
20026970100 | INSTALL 11400'-2"/4" PM/CSIP | [5 empty] | 1042042.95 | 1176644.8813 | -134601.9313 | 2021-01-01 | 2021-12-31 | 2021-03-31 | 2021-11-12
20026918102 | INSTALL ELECTRONICS | [5 empty] | 173384.28 | 264607.6595 | -91223.3795 | 2021-01-01 | 2021-12-31 | 2021-11-01 | 2021-11-01 | NO CC NEEDED ONSITE MEETING DID NOT GO INSIDE BUILDING GES: UNDERRUN EXPLANATION: JOB UNDERRAN BECAUSE SCADA BUILDING WAS PLACED O N ANOTHER JOB ORDER THAT IS PLANNED FOR 2022 CONSTRUCTION. ADDITIONALLY, ASSUMED THERE WAS PRESSURE CONTROL WHEN ESTIMATED AND THERE W AS NOT.
21026142200 | INSTALL 575' OF 2"PMMP MAIN | [5 empty] | 25446.02 | 20915.4686 | 4530.5514 | 2021-01-01 | 2021-12-31 | 2021-10-25 | 2021-11-02
21026149000 | INSTALL 75'-2" PMIP | [5 empty] | 765.35 | 4287.763 | -3522.413 | 2021-01-01 | 2021-12-31 | 2021-11-01 | 2021-12-20 | INSTALLED 66' OF 2" PL TESTED 90 PSIG 0005 MIN SOAP TESTED CAP OP 8 PSIG
21026138201 | EMER-INSTALL 480' OF 6"PMLP | [5 empty] | 194700.21 | 240281.6735 | -45581.4635 | 2021-01-01 | 2021-12-31 | 2021-11-01 | 2021-11-02 | CCC# 43819 CCC# 43967 TWALKER/KY 05-04-22: JOB CURRENTLY UNDER RUNNING SINCE CITY OF FRANKFORT HAS NOT PAVED STREET AND BILLED CKY - PAVING ESTIMATE AT $35,000.
21026138300 | EMER-RETIRE 490' OF 6 5/8"BSLP | [5 empty] | 71.35 | 82.634 | -11.284 | 2021-01-01 | 2021-12-31 | 2021-11-02 | 2021-11-02 | KBOTKINS ENTERED WIPE SAMPLE FOR OLIVER MAYNARD WHO IS ATTEMPTING TO COMPLETE THE JOB FOR CLOSE OUT. SAMPLE TAKEN 4/20/22 BUT SYSTEM WOULD NOT ACCEPT THAT DATE DUE TO THE CO DATE.
21026133900 | INSTALL VRG CONTROLER | [5 empty] | 0 | 6187.1439 | -6187.1439 | 2021-01-01 | 2021-12-31 | 2022-11-01 | 2022-11-02
21026134000 | RETIRE DAMAGED CONTROLLER | [5 empty] | 0 | 220.9908 | -220.9908 | 2021-01-01 | 2021-12-31 | 2022-11-01 | 2022-11-02
20026929400 | UPGRADE ELECTRONICS | [5 empty] | 293.46 | 3038 | -2744.54 | 2021-01-01 | 2021-12-31 | 2021-11-02 | 2021-11-18 | REPLACED EFC
20026935100 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 | 2021-01-01 | 2021-12-31 | 2021-11-17 | 2021-11-18 | REPLACED EFC
21026145200 | EMER-INSTALL NEW BYPASS VALVES | [5 empty] | 634.37 | 4285.9461 | -3651.5761 | 2021-01-01 | 2021-12-31 | 2021-11-03 | 2021-12-27 | CCC# 44725 BYPASS VALVES INSTALLED BY WADE SHIMFESSEL ALONG WITH CONTRACT CREW PAPERWORK COMPLETED BY CYNTHIA FARIS 12/27/21
21026120800 | RETIRE HP/MP RUN-1 OF R-1035 | [5 empty] | 827.14 | 21706.5276 | -20879.3876 | 2021-01-01 | 2021-12-31 | 2021-11-29 | 2021-11-29 | HP TO MP RUN 1 HAS BEEN RETIRED AND LP RUN 2 HAS BEEN PLACED BACK INTO SERVICE WORKED COMPLETED ON 11/3/2021 BY CHRIS COX PAPERWORK COMPLETED BY CYNTHIA FARIS ON 11/29/2021 GCCC TICKET NOT REQUIRED ON 11/29/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026145300 | EMER-RETIRE BYPASS VALVE | [5 empty] | 0 | 60.6987 | -60.6987 | 2021-01-01 | 2021-12-31 | 2021-11-03 | 2022-01-11 | VALVE REPLACED BY WADE SHIMFESSEL AND CONTRACT CREW ON 11/3/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/11/2022
20026972201 | INSTALL 3300' OF 2"/4" PMMP | [5 empty] | 84926.85 | 89953.3001 | -5026.4501 | 2021-01-01 | 2021-12-31 | 2021-10-12 | 2021-11-04
21026124100 | INSTALL 300'-2" PMMP | [5 empty] | 41987.03 | 24076.2901 | 17910.7399 | 2021-01-01 | 2021-12-31 | 2021-11-01 | 2021-11-05
21026149500 | EMER-INSTALL 26'-3"/4"PMMP MN | [5 empty] | 23766.13 | 10953.3154 | 12812.8146 | 2021-01-01 | 2021-12-31 | 2021-11-16 | 2021-11-17 | SPLIT IN ALDYLA MAIN.INSTALLED BYPASS.REPLACED CRACKED MAIN AND INLINE TEE WHILE MAIN ON BYPASS.ALL TESTING INFO ON 21026149600 AND 21026149500 IN DOCS
21026149600 | EMER-RETIRE 26'- 4"PAMP MAIN | [5 empty] | 86.15 | 61.5191 | 24.6309 | 2021-01-01 | 2021-12-31 | 2021-11-16 | 2021-11-17 | SPLIT IN ALDYLA MAIN.INSTALLED BYPASS.REPLACED CRACKED MAIN AND INLINE TEE WHILE MAIN ON BYPASS.ALL TESTING INFO ON 21026149600 AND 21026149500 IN DOCS
20026929700 | UPGRADE ELECTRONICS | [5 empty] | 3985.53 | 3038 | 947.53 | 2021-01-01 | 2021-12-31 | 2021-10-18 | 2021-11-16 | REPLACED EFC
20026935400 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 | 2021-01-01 | 2021-12-31 | 2021-11-08 | 2021-11-16 | REPLACED EFC
21026131400 | INSTALL 300'-2" PMIP | [5 empty] | 158500.46 | 139158.4326 | 19342.0274 | 2021-01-01 | 2021-12-31 | 2021-10-25 | 2021-11-11
21026131500 | RETIRE 300'-2" PMIP | [5 empty] | 39.34 | 88.8156 | -49.4756 | 2021-01-01 | 2021-12-31 | 2021-11-09 | 2021-11-11
21026128700 | RETIRE HP/MP REG RUN | [5 empty] | 3741.83 | 4148.6042 | -406.7742 | 2021-01-01 | 2021-12-31 | 2021-11-09 | 2021-11-18 | HP/MP RUN RETIRED BY CHRIS COX ON 11/9/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 11/18/2021 GCCC TICKET NOT REQUIRED ON 11/18/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026970200 | RETIRE 10250'-2"/3"/4" BS/CSIP | [5 empty] | 272.31 | 278.4699 | -6.1599 | 2021-01-01 | 2021-12-31 | 2021-10-14 | 2021-11-12
21026150000 | EMER - INSTALL 14'-4" PMLP | [5 empty] | 72137.82 | 3163.1338 | 68974.6862 | 2021-01-01 | 2021-12-31 | 2021-12-21 | 2021-12-22 | INSTALLED 16' OF 4" PL W/ 4 90'S TO GO ABOVE 24" CLAY TILE SEWER TESTED 90 PSIG 1 HR OVERRUN EXPLANATION: CROSSBORE FOUND- CAMERA CREW NEEDED AND ADDITIONAL HOURS NEEDED TO REMEDIATE THE CROSS-BORE ISSUE 2 MAINTENCE JOBS AND 1 PAVE JOB CHARGED BACK TO CAPITAL JOB AND WERE NOT ACCOUNTED FOR IN ORIGINAL PROPOSED COST, $26K IN FLAGGING AND RESTORATION CHARGED TO MAINTENCE JOBS AND $14K IN CAMERA WORK BY CONTRACTOR
21026150100 | EMER - RETIRE 6'-4" P-LP | [5 empty] | 669.23 | 335.9749 | 333.2551 | 2021-01-01 | 2021-12-31 | 2021-12-21 | 2021-12-22 | REMOVED 4" PL FROM SEWER LINE CROSS BORE
21026101700 | INSTALL NEW GMB SETTING | [5 empty] | 40071.73 | 57815.8896 | -17744.1596 | 2021-01-01 | 2021-12-31 | 2021-07-27 | 2021-11-16 | INSTALLED NEW GMB SETTING
21026102400 | RETIRE WOODFORD GMB | [5 empty] | 0 | 84.0131 | -84.0131 | 2021-01-01 | 2021-12-31 | 2021-11-10 | 2021-11-16 | RETIRED OLD GMB SETTING AFTER NEW SETTING PLACED IN SERVICE
21026999600 | INSTALL 90' OF 4"CS/PMMP MAIN | [5 empty] | 47302.77 | 68922.5327 | -21619.7627 | 2021-01-01 | 2021-12-31 | 2021-10-15 | 2021-11-11 | NEW MAIN GASED UP 11-11-21
21026150600 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 378.77 | 1696.2756 | -1317.5056 | 2021-01-01 | 2021-12-31 | 2021-11-16 | 2021-11-16
21026150700 | EMER - RETIRE 5'-2" PMP | [5 empty] | 64.43 | 335.9749 | -271.5449 | 2021-01-01 | 2021-12-31 | 2021-11-16 | 2021-11-17
21026129600 | INSTALL 100' OF 8"PMMP MAIN | [5 empty] | 152586.55 | 99233.0142 | 53353.5358 | 2021-01-01 | 2021-12-31 | 2021-10-26 | 2021-11-19 | TWALKER/KY 01-24-23: JOB ORDER OVER RUN DUE TO ADDITIONAL FLAGGING ADDED $50,000 TO CONTRACT COST, SEGA INCREASED BY $6,000 AND CO LABOR COST HIGHER BY $14,000 LEVEL 2 VARIANCE ADDED TO WMS.DOCS.
21026129700 | RETIRE 20' OF 8"BSMP MAIN | [5 empty] | 1960.6 | 79.203 | 1881.397 | 2021-01-01 | 2021-12-31 | 2021-11-16 | 2021-11-19
20026975500 | RETIRE 3515'-2",3",4"& 6" | [5 empty] | 142.7 | 107.2796 | 35.4204 | 2021-01-01 | 2021-12-31 | 2021-03-01 | 2021-11-16 | PROJECT COMPLETE ON 11162021
21026151500 | EMER-INSTALL 10' OF 4"PMMP | [5 empty] | 210.64 | 5220.9567 | -5010.3167 | 2021-01-01 | 2021-12-31 | 2021-11-18 | 2021-11-24 | LEAK ON SF CPLG ON TEE OF SVC TO 3102 KIRKLEVINGTON DR. DPI D221947 CLEARED ON 2212. ABN/INST 3'- 4" P MAIN ACCORDING TO GAS STANDARDS AND ENGINEERED TIE-IN PLAN. WORKED 11/17/21 MCRAIG
20026973001 | INSTALL 10,000--2" PMMP | [5 empty] | 2896168.82 | 2332285.9866 | 563882.8334 | 2021-01-01 | 2021-12-31 | 2021-08-27 | 2022-06-30 | COST OVERRUN OF $378K DUE TO PROJECT SHUT DOWN AND RESTART OVER WINTER. PR OJECT REQUIRED ADDITIONAL RESOURCES THAT WERE NOT ESTIMATED. COST OVERUN O F $345K IN MATERIALS (PAVING), $124K IN CONTRACT AND $21K IN LABOR. THERE W AS A SAVINGS OF $213K IN OTHER DUE TO ORIGINAL PAVING ESTIMATE BEING CAPTUR ED THERE. THESE ADDITIONAL COSTS CAUSED INCREASE IN SEGA OF $97K. D.LEMONS 10/26/2022
21026151600 | EMER-RETIRE 10' OF 4"PAMP | [5 empty] | 24.42 | 64.6591 | -40.2391 | 2021-01-01 | 2021-12-31 | 2024-11-17 | 2021-11-24 | LEAK ON SF COUPLING ON TEE TO SVC OF 3102 KIRKLEVINGTON DR. DPI D221947 CLEARED ON 2212. ABN/ INST 3'- 4" P MAIN ACCORDING TO GAS STANDARDS AND ENGINEERED TIE-IN PLAN. WORKED 11/17/24 MCRAIG
21026128200 | INSTALL 1,300 OF 2"/4"PMMP | [5 empty] | 56524.7 | 51810.9858 | 4713.7142 | 2021-01-01 | 2021-12-31 | 2021-11-08 | 2021-11-19
21026136700 | INSTALL 1,750'-2" PMMP | [5 empty] | 47459.5 | 49760.6579 | -2301.1579 | 2021-01-01 | 2021-12-31 | 2021-11-08 | 2021-11-23
20026954400 | INSTALL 12,500' OF 6"PMMP | [5 empty] | 671261.21 | 584465.9269 | 86795.2831 | 2021-01-01 | 2021-12-31 | 2021-08-26 | 2021-12-17 | GAS WAS ONLINE BEFORE COMMIT DATE. HAD TO FINISH UP RESTORATION AND PROJEC T INFO. STEVE CANOY 12/17/2021
20026955503 | INSTALL 2850'-8" CSHP | [5 empty] | 1263938.35 | 1308080.823 | -44142.473 | 2021-01-01 | 2021-12-31 | 2021-11-18 | 2021-11-30
20026955600 | RETIRE 6100'-8"/3" BS/CSHP | [5 empty] | 142.7 | 190.2592 | -47.5592 | 2021-01-01 | 2021-12-31 | 2021-11-30 | 2021-11-30
21026153400 | EMER - INSTALL 6'-4" PMIP | [5 empty] | 7455.58 | 4080.2324 | 3375.3476 | 2021-01-01 | 2021-12-31 | 2021-12-01 | 2021-12-22
21026153500 | EMER - RETIRE 6'-4" PMIP | [5 empty] | 101.71 | 518.618 | -416.908 | 2021-01-01 | 2021-12-31 | 2021-12-22 | 2021-12-22
21026135900 | INSTALL 140'-2" PMMP | [5 empty] | 8332.52 | 14039.3957 | -5706.8757 | 2021-01-01 | 2021-12-31 | 2021-11-23 | 2021-12-02
21026143200 | EMER - INSTALL 450'- 4" CSHP | [5 empty] | 257776.24 | 196595.4538 | 61180.7862 | 2021-01-01 | 2021-12-31 | 2021-12-02 | 2021-12-14 | PROJECT WAS CODED AMRCB BECAUSE THE PIPE UNDER THE BRIDGE HAD NO COATING. OVERRUN EXPLANATION: MAIN REASON FOR PROJECT COST OVERRUN IS DUE TO 2,000 UNITS OF ASPHALT PAVING WHEN ONLY 1,000 UNITS WERE PLANNED. THE STATE REQUIRED EXTRA PAVING DUE TO EXISTING ROAD CONDITION.THE PROJECT WAS PLANNED FOR 1 CONSTRUCTION COORDINATORBUT ENDED UP HAVING MULTIPLE AND DOUBLED THE COMPANY LABOR CHARGES. FLAGGING FOR THEPROJECT INCLUDED A 30% INCREASECOMPARED TO THE PLANNED AMOUNT. THE PROJECT INCLUDED AN ADDITIONAL 49 UNITS OF STEELMAINLINE INSTALLATION AND ROCK AND LEDGE EXCAVATIONWAS REQUIRED BUT NOT PLANNED. TTOY 12/2/22
21026143300 | EMER - RETIRE 100'-3" CSHP | [5 empty] | 3034.48 | 61.5191 | 2972.9609 | 2021-01-01 | 2021-12-31 | 2021-12-02 | 2021-12-14
21026156100 | EMER-INSTALL 6' OF 2"PMMP MAIN | [5 empty] | 5612.12 | 6138.1743 | -526.0543 | 2021-01-01 | 2021-12-31 | 2021-12-14 | 2021-12-14
20026976400 | RETIRE 6100' OF 3"/4"BSLP MN | [5 empty] | 1794.07 | 152.7248 | 1641.3452 | 2021-01-01 | 2021-12-31 | 2022-01-24 | 2021-12-15
20026977200 | RETIRE 6900' OF 4"/6"BSLP MAIN | [5 empty] | 848.1 | 76.6277 | 771.4723 | 2021-01-01 | 2021-12-31 | 2021-01-27 | 2021-12-15
21026156200 | EMR-RET 6'-2"PMP MAIN D222323 | [5 empty] | 75.03 | 61.2976 | 13.7324 | 2021-01-01 | 2021-12-31 | 2021-12-14 | 2021-12-14
21026105401 | INSTALL 6520' OF 6"PMMP MAIN | [5 empty] | 421654.71 | 403346.5487 | 18308.1613 | 2021-01-01 | 2021-12-31 | 2021-07-22 | 2021-12-17
21026120700 | RETIRE REG STATION 1002 | [5 empty] | 6481.89 | 5235.8425 | 1246.0475 | 2021-01-01 | 2021-12-31 | 2021-12-15 | 2021-12-27 | CC# 48634 CMCOX 12/15/21 STATION RETIRED BY CHRIS COX AND CONSTRUCTION SERVICES PAPERWORK COMPLETED BY CYNTHIA FARIS ON 12/27/21
20026988300 | RETIRE 1853'-4"/3" BS/CSMP | [5 empty] | 47.8 | 5110.2031 | -5062.4031 | 2021-01-01 | 2021-12-31 | 2021-04-14 | 2021-12-16
21026113701 | INSTALL 4030' - 4"/2" PMMP | [5 empty] | 862366.14 | 778460.4875 | 83905.6525 | 2021-01-01 | 2021-12-31 | 2021-04-14 | 2021-12-17
20026955800 | RETIRE 216'-2" PMMP | [5 empty] | 0 | 85.5775 | -85.5775 | 2021-01-01 | 2021-12-31 | 2021-04-14 | 2021-12-17
21026106400 | RETIRE PAPER RECORD GAUGE | [5 empty] | 92.38 | 341.3226 | -248.9426 | 2021-01-01 | 2021-12-31 | 2021-12-17 | 2021-12-17 | TICKET 13749
20026956200 | RETIRE 4775'-12">3"PM/BS/CSLP | [5 empty] | 160 | 85.5775 | 74.4225 | 2021-01-01 | 2021-12-31 | 2021-04-14 | 2021-12-20
21026118500 | RETIRE 3,256' 10"-3" CS/BS/PLP | [5 empty] | 42.9 | 151.2005 | -108.3005 | 2021-01-01 | 2021-12-31 | 2021-04-14 | 2021-12-20
21026156500 | INSTALL 140'-2"/4" PMMP | [5 empty] | 2096.07 | 3669.7405 | -1573.6705 | 2021-01-01 | 2021-12-31 | 2021-12-20 | 2021-12-21
20026985600 | INSTALL 375' OF 2"CSHP MAIN | [5 empty] | 90203.73 | 92169.2028 | -1965.4728 | 2021-01-01 | 2021-12-31 | 2021-12-12 | 2021-01-03
20026985700 | RETIRE 200' OF 2"CSHP MAIN | [5 empty] | 62.95 | 84.1794 | -21.2294 | 2021-01-01 | 2021-12-31 | 2021-12-12 | 2022-01-03
20026942600 | RETIRE GAUGE | [5 empty] | 0 | 91.4991 | -91.4991 | 2021-01-01 | 2021-12-31 | 2021-12-21 | 2022-01-10 | GAUGE RETIRED AFTER ERX INSTALLED BY WADE SHIMFESSEL PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/10/2022
20026918301 | INSTALL ELECTRONICS | [5 empty] | 163427.04 | 179105.9064 | -15678.8664 | 2021-01-01 | 2021-12-31 | 2021-12-21 | 2021-12-22 | GCC# 13951 CCC TICKET #14135 TICKET# 15597 CCC# 49425 REPLACED PUCK IN TRANSMITTER W/NOLL COMPLETED PAPERWORK 12-22-21 JMARTIN
20026942500 | INSTALL I&C EQUIPMENT | [5 empty] | 8341.61 | 16155.4774 | -7813.8674 | 2021-01-01 | 2021-12-31 | 2021-12-21 | 2022-01-10 | ERX INSTALLED BY ACP AND WADE SHIMFESSEL PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/10/22
22026205000 | RETIRE ERX | [5 empty] | 0 | 78.4365 | -78.4365 | 2021-01-01 | 2021-12-31 | 2021-12-21 | 2021-12-22 | COMPLETED PAPERWORK 12-22-21 JMARTIN
21026157501 | EMER - INSTALL 5'-3" PMMP | [5 empty] | 24476.25 | 13441.7151 | 11034.5349 | 2021-01-01 | 2021-12-31 | 2021-12-26 | 2021-12-27
21026157600 | EMER - RETIRE 5'-3" PAMP | [5 empty] | 106.63 | 72.8047 | 33.8253 | 2021-01-01 | 2021-12-31 | 2021-12-26 | 2021-12-27
21026141600 | INSTALL 320' OF 2"PMMP MAIN | [5 empty] | 51396.03 | 52296.0917 | -900.0617 | 2021-01-01 | 2021-12-31 | 2021-12-22 | 2021-12-28
21026141700 | RETIRE 315' OF 2"PMP MAIN | [5 empty] | 46.05 | 60.6987 | -14.6487 | 2021-01-01 | 2021-12-31 | 2021-12-22 | 2021-12-28
21026157800 | INSTALL 5'-4" PMLP | [5 empty] | 2758.28 | 4114.4273 | -1356.1473 | 2021-01-01 | 2021-12-31 | 2021-12-28 | 2022-01-03
21026157900 | RETIRE 5'-4" PMLP | [5 empty] | 485.31 | 72.8047 | 412.5053 | 2021-01-01 | 2021-12-31 | 2021-12-28 | 2022-01-03
Formulas:
Date Actual End = VLOOKUP([Project No.],'WMS JO Data'!$D20:BD27748,25,FALSE)

## 2022 (hidden)
Columbia Gas of Kentucky Case No. 2026-00099 Attachment A Construction Projects For 5 years ended December 31, 2025
Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End | Job Order Comments
20026943000 | RETIRE GAUGE | [5 empty] | 1496.7 | 91.4991 | 1405.2009 | 2022-01-01 | 2022-12-31 | 2022-01-06 | 2022-01-10 | CCC# 49347 COMMISION ERX CCC# 50118 ERX INSTALLED AND GAUGE RETIRED BY WADE SHIMFESSEL PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/10/22
20026942900 | INSTALL I&C EQUIPMENT | [5 empty] | 11090.78 | 16155.4774 | -5064.6974 | 2022-01-01 | 2022-12-31 | 2022-01-06 | 2022-01-10 | ERX INSTALLED BY ACP AND WADE SHIMFESSEL PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/10/22
22026159500 | EMER - INSTALL 5'-3" PMMP | [5 empty] | 11760.26 | 5999.0379 | 5761.2221 | 2022-01-01 | 2022-12-31 | 2022-01-10 | 2022-01-10
22026159600 | EMER - RETIRE 5' - 3" PMMP | [5 empty] | 0 | 79.0999 | -79.0999 | 2022-01-01 | 2022-12-31 | 2022-01-10 | 2022-01-10
22026159700 | EMER - INSTALL 4'-4" PMLP | [5 empty] | 1914.95 | 4455.398 | -2540.448 | 2022-01-01 | 2022-12-31 | 2022-01-24 | 2022-01-24
22026159800 | EMER - RETIRE 4'-4" P-LP | [5 empty] | 6434.1 | 448.5353 | 5985.5647 | 2022-01-01 | 2022-12-31 | 2022-01-20 | 2022-01-20 | RETIRED 4' OF 4" PL LP TO REMOVED STEEL SADDLE FROM PLASTIC MAIN
22026160800 | EMER-INSTALL 5' OF 2"PMMP MAIN | [5 empty] | 2109.29 | 3947.9695 | -1838.6795 | 2022-01-01 | 2022-12-31 | 2022-01-12 | 2022-01-12
22026159900 | EMER - INSTALL 2'-2" PMLP | [5 empty] | 2408.32 | 2367.5988 | 40.7212 | 2022-01-01 | 2022-12-31 | 2022-02-03 | 2022-02-03
22026160900 | EMER-RETIRE 5' OF 2"PAMP MAIN | [5 empty] | 0 | 69.6571 | -69.6571 | 2022-01-01 | 2022-12-31 | 2022-01-12 | 2022-01-12
22026160000 | EMER - RETIRE 2'2"P-LP D244381 | [5 empty] | 487.19 | 506.8997 | -19.7097 | 2022-01-01 | 2022-12-31 | 2022-02-07 | 2022-02-07
21026134800 | INSTALL 20'-2" PMMP | [5 empty] | 67370.23 | 39141.4028 | 28228.8272 | 2022-01-01 | 2022-12-31 | 2022-01-03 | 2022-01-12
21026134900 | RETIRE 16'-2" CSMP | [5 empty] | 0 | 88.8156 | -88.8156 | 2022-01-01 | 2022-12-31 | 2022-01-03 | 2022-01-12
20026926200 | INSTALL NETWORK UPGRADE | [5 empty] | 853.47 | 3150 | -2296.53 | 2022-01-01 | 2022-12-31 | 2022-01-12 | 2022-01-12 | SUPER SOLAR KIT AND RV50 INSTALLED BY NOLL DAVIS AND ACP PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/12/22
22026160400 | EMER - REPAIR LEAK | [5 empty] | 8003.12 | 3388.6445 | 4614.4755 | 2022-01-01 | 2022-12-31 | 2022-01-13 | 2022-01-13
22026160500 | EMER - REPAIR LEAK | [5 empty] | 0 | 69.6571 | -69.6571 | 2022-01-01 | 2022-12-31 | 2022-01-13 | 2022-01-13
21026108801 | INSTALL 1000' OF 2"PMMP MAIN | [5 empty] | 51597.09 | 46147.0126 | 5450.0774 | 2022-01-01 | 2022-12-31 | 2022-01-06 | 2022-01-25
22026164900 | EMER-INSTALL 4' OF 3"PMMP MAIN | [5 empty] | 15536.92 | 14982.0392 | 554.8808 | 2022-01-01 | 2022-12-31 | 2022-01-31 | 2022-02-17 | INSTALLED 4' OF 030 P DUE TO EXC DMG TEST AT 90# FOR 20 MIN PER FOL APPROVA L, SOAP TEST TWO 030 EF CPLGS AT OP FOR 5 MIN OK. TEST FOR SEC DMG OK. WHIMES 02/17/2022
22026165000 | EMER-RETIRE 4' OF 3"PMP MAIN | [5 empty] | 119.3 | 100.2728 | 19.0272 | 2022-01-01 | 2022-12-31 | 2022-02-17 | 2022-02-17 | COMPLETED W/ JO 22026164900
20026982700 | INSTALL 4500'-2"&4" PMMP | [5 empty] | 885948.31 | 959444.7901 | -73496.4801 | 2022-01-01 | 2022-12-31 | 2021-10-18 | 2022-03-29
21026140000 | RETIRE 489'-4" PMP | [5 empty] | 20306.35 | 13697.8754 | 6608.4746 | 2022-01-01 | 2022-12-31 | 2022-02-01 | 2022-02-09
22026164400 | EMER - INSTALL 10'-2" PMMP | [5 empty] | 10363.46 | 13748.6188 | -3385.1588 | 2022-01-01 | 2022-12-31 | 2022-02-08 | 2022-02-08
22026164500 | EMER - RETIRE 10'-2" PMP | [5 empty] | 111.44 | 109.7476 | 1.6924 | 2022-01-01 | 2022-12-31 | 2022-02-08 | 2022-02-08
21026155900 | INSTALL 2400' OF 2"PMMP MAIN | [5 empty] | 72846.65 | 61211.3642 | 11635.2858 | 2022-01-01 | 2022-12-31 | 2022-01-06 | 2022-02-10
22026167400 | EMER - INSTALL 5'-3" PMLP | [5 empty] | 0 | 3781.5061 | -3781.5061 | 2022-01-01 | 2022-12-31 | 2022-02-09 | 2022-02-09
22026167500 | EMER - RETIRE 5'-3" PLP | [5 empty] | 0 | 109.7476 | -109.7476 | 2022-01-01 | 2022-12-31 | 2022-02-09 | 2022-02-09
21026157100 | INSTALL 600'-2" PMMP | [5 empty] | 29494.94 | 21934.2504 | 7560.6896 | 2022-01-01 | 2022-12-31 | 2022-02-07 | 2022-02-16
22026162500 | INSTALL 8" STOPPLE FITTING | [5 empty] | 25751.7 | 14352.6857 | 11399.0143 | 2022-01-01 | 2022-12-31 | 2022-02-09 | 2022-02-10
22026162600 | RETIRE 44' OF 8"BSMP MAIN | [5 empty] | 0 | 105.0102 | -105.0102 | 2022-01-01 | 2022-12-31 | 2022-02-09 | 2022-02-10
21026154000 | INSTALL 160'-2" PMMP | [5 empty] | 28534.77 | 33091.7151 | -4556.9451 | 2022-01-01 | 2022-12-31 | 2022-02-07 | 2022-02-14
21026141400 | INSTALL 130'-6" PMMP | [5 empty] | 179014.36 | 140177.264 | 38837.096 | 2022-01-01 | 2022-12-31 | 2022-01-11 | 2022-02-15 | PROJECT OVERRUN OF $38,555 (28%) DUE TO ADDITIONAL TIME AND RESOURCES BEING REQUIRED. LABOR HOURS ESTIMATED AT 176 HRS, BUT 319 HRS WERE REQUIRED ($11 ,052 DIFF. LABOR RATE ESTIMTES TOO LOW). NEW CONTRACT WILL ADDITIONAL UNITS WAS USED WHICH ADDED $57,948. BUT THERE WERE SAVINGS OF $30,000 IN THE OT HER CATAGORY, WHICH WERE COVERED WITH UNITS IN THE UPDATED CONTRACT. D.LEMO NS 7/8/2022
21026141500 | RETIRE 316'-6" PM&CS MP | [5 empty] | 4123.73 | 76.2083 | 4047.5217 | 2022-01-01 | 2022-12-31 | 2022-01-11 | 2022-02-15
22026160100 | PM-GREENSITE I75 ILI DE RELO | [5 empty] | 6466.13 | 0 | 6466.13 | 2022-01-01 | 2022-12-31 | 2022-07-11 | 2022-07-22
22026160200 | PM-GREENSITE I75 ILI DE ABAN | [5 empty] | 105.53 | 0 | 105.53 | 2022-01-01 | 2022-12-31 | 2022-07-11 | 2022-07-22 | GIS HAD LESS FOOTAGE THAN WHAT WAS FIELD VERIFIED. NO FAC CREATED, DUE TO F ACT IT WAS BEING ABANDONED.
20026954900 | INSTALL SKID REG STATION #1574 | [5 empty] | 83537.33 | 91083.0917 | -7545.7617 | 2022-01-01 | 2022-12-31 | 2021-03-22 | #N/A | TUBE UP ONE RUN CCC #22458 CCC# 22583 CC# 23111 G.HALE 05-12-21 PLACED RUN 1 IN SERVICE ON 5/6/21 WITH TEMPORARY REGULATORS INSTALLED TO MEET COMMIT DATE WITH BUILDER RUN 2 OFF AND BLIND FLANGED PERMANENT EQUIPMENT ORDER WITH TENTATIVE DELIVERY DATE OF JUNE/JULY 2021 JOB CANNOT BE COMPLETED OR CLOSED OUT UNTIL PERMANENT EQUIPMENT IS INSTALLED CFARIS CCC# 43393 CCC# CALLED IN BY AL PARKS OR CONNER WIMPE CCC#55276 CWEMPE 2/15/22 GCCC# 56179 INSTALLED PERMANENT SLAMSHUT MOONEY'S COMMISSIONED STATION CWEMPE 2-16-22
21026103000 | INSTALL CHAIN LINK FENCE | [5 empty] | 20497.91 | 16434.2505 | 4063.6595 | 2022-01-01 | 2022-12-31 | 2021-03-22 | 2022-02-16 | RHAYES 08-24-2021 MONITORED FENCE INSTALLATION CCC 35764 CWEMPE PAPER WORK COMPLETION 2-16-22
22026164600 | EMER - INSTALL 220'-2" PMIP | [5 empty] | 49083.09 | 49188.5426 | -105.4526 | 2022-01-01 | 2022-12-31 | 2022-02-22 | 2022-02-22
22026164700 | EMER - RETIRE 20'-4" CSIP | [5 empty] | 140.47 | 109.7476 | 30.7224 | 2022-01-01 | 2022-12-31 | 2022-02-22 | 2022-02-22
21026993800 | INSTALL 7200' OF 2"/6"PMMP | [5 empty] | 3006825.55 | 2229015.8617 | 777809.6883 | 2022-01-01 | 2022-12-31 | 2022-01-27 | 2022-12-09
21026157200 | INSTALL 16' OF 3"PMMP MAIN | [5 empty] | 56295.03 | 11827.5319 | 44467.4981 | 2022-01-01 | 2022-12-31 | 2022-02-16 | 2022-02-23 | TWALKER/KY 02-24-22: WMS WOULD NOT ALLOW PROJECT TO BE REVISED DUE TO UNPAID INVOICES MESSAGE. JOB OVER RUN DUE TO UNKNOWN BOLTED COUPLINGS FOUND DURING CONSTUCTION AND SCOPE OF WORK WAS INCREASED TO REMOVE THOSE COUPLINGS IN THE PAVED STREET. TWALKER/KY 09-16-22: DURING CONSTRUCTION BOLTED COUPLING WERE FOUND ON MP GAS MAIN AND HAD TO BE REMOVED WMS WOULD NOT ALLOW REVISION. ADDITIONAL WORK INCREASED COMPANY LABOR BY $6000 SEGA INCREASED BY $4500 STREET CUT REPAIR REQUIRED AND ADDITIONAL CONTRACT RESOURCES INCREASED BY $27,000
21026157300 | RETIRE 14' OF 3"CSMP MAIN | [5 empty] | 0 | 72.8047 | -72.8047 | 2022-01-01 | 2022-12-31 | 2022-02-16 | 2022-02-23
20026940100 | RETIRE PAPER GUAGE | [5 empty] | 172.3 | 91.4991 | 80.8009 | 2022-01-01 | 2022-12-31 | 2022-02-24 | 2022-02-24 | RETIRED PAPER CHART INSTALLED HONEYWELL ERX CCOX 2-24-2022
20026940000 | INSTALL I&C EQUIPMENT | [5 empty] | 11589.34 | 16155.4774 | -4566.1374 | 2022-01-01 | 2022-12-31 | 2022-02-24 | 2022-02-24 | CCC# 43689 RETIRED PAPER CHART INSTALLED NEW ERX CCOX 02-24-2022
20026943200 | RETIRE GAUGE | [5 empty] | 259.73 | 91.4991 | 168.2309 | 2022-01-01 | 2022-12-31 | 2022-02-25 | 2022-02-25 | INSTALLED NEW LEGACY ERX RETIRED PAPER CHART BLONE 2-25-2022
20026943100 | INSTALL I&C EQUIPMENT | [5 empty] | 14038.9 | 16155.4774 | -2116.5774 | 2022-01-01 | 2022-12-31 | 2022-02-25 | 2022-02-25 | CCC# 43654 INSTALLED ERX RETIRED PAPER CHART BLONE 2-25-2022
22026180900 | EMER-INSTALL 4' OF 2"PMMP | [5 empty] | 3753.68 | 3916.7503 | -163.0703 | 2022-01-01 | 2022-12-31 | 2022-02-28 | 2022-02-28
22026181000 | EMER-RETIRE 4' OF 2"PMMP | [5 empty] | 0 | 75.4968 | -75.4968 | 2022-01-01 | 2022-12-31 | 2022-02-28 | 2022-02-28
20026928300 | UPGRADE FROM 3G NETWORK | [5 empty] | 6815.37 | 3038 | 3777.37 | 2022-01-01 | 2022-12-31 | 2022-02-28 | 2022-02-28 | RETIRED OLD EFC INSTALLED NEW EC350 CCOX 02-28-2022
20026934000 | RETIRE ELECTRONICS | [5 empty] | 626.57 | 73.3494 | 553.2206 | 2022-01-01 | 2022-12-31 | 2022-02-28 | 2022-02-28 | RETIRED OLD EFC AND INSTALLED NEW EC350 CCOX 02-28-2022
21026156600 | INSTALL 230'-2" PMMP | [5 empty] | 17647.7 | 15538.521 | 2109.179 | 2022-01-01 | 2022-12-31 | 2022-02-28 | 2022-03-01
21026128000 | INSTALL 265' OF 4" PMLP | [5 empty] | 96077.32 | 71153.2979 | 24924.0221 | 2022-01-01 | 2022-12-31 | 2022-02-16 | 2022-03-10 | AWEBER - JO RAN OVER ESTIMATE DUE TO UNFORSEEN 8'X5' STORM BASIN @ 42" BELO W GRADE. EXCAVATION OF TOP OF BASIN OCCURRED TO PROVIDE REROUTE OF 4" PMMP INSTALL AT ACCEPTABLE DEPTH WITHOUT CROSSBORE.
21026128100 | RETIRE 230'-4" & 50'-6" PMLP | [5 empty] | 71.35 | 354.2624 | -282.9124 | 2022-01-01 | 2022-12-31 | 2022-02-16 | 2022-03-10
20026927900 | UPGRADE ELECTRONICS | [5 empty] | 3660.91 | 3038 | 622.91 | 2022-01-01 | 2022-12-31 | 2022-03-02 | 2022-03-02 | EFC REPLACED BY C. COX ON 3-1-22 PAPERWORK CO BY J MULLINS ON 3-2-22
20026933700 | RETIRE ELECTRONICS | [5 empty] | 452.45 | 73.3494 | 379.1006 | 2022-01-01 | 2022-12-31 | 2022-03-02 | 2022-03-02 | GAUGE RETIRED BY C. COX PAPPER WORK CO BY J. MULLINS 3-2-2022
22026172500 | INSTALL 5'-1" PMMP | [5 empty] | 4.3 | 1353.2384 | -1348.9384 | 2022-01-01 | 2022-12-31 | 2022-03-02 | 2022-03-02
22026172600 | RETIRE 5'-1" PAMP | [5 empty] | 2198.83 | 66.5954 | 2132.2346 | 2022-01-01 | 2022-12-31 | 2022-03-02 | 2022-03-02
20026928800 | UPGRADE ELECTRONICS | [5 empty] | 6614.01 | 3038 | 3576.01 | 2022-01-01 | 2022-12-31 | 2022-03-02 | 2022-03-02 | ASSIST SMCHOLAN 03-02-2022 RHAYES ASSIST SMCHOLAN 03-02-2022 RHAYES INSTALLED NEW EC350 SOAP TEST TUBING 5MIN OPP PRESSURE SMCHOLAN 3-2-22
20026934500 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 | 2022-01-01 | 2022-12-31 | 2022-03-02 | 2022-03-02 | RETIRED MINI-AT INSTALLED NEW EC350 SMCHOLAN 3-2-22
21026140400 | INSTALL 2800' OF 2"/4"PMMP | [5 empty] | 116146.05 | 86592.9986 | 29553.0514 | 2022-01-01 | 2022-12-31 | 2022-01-03 | 2022-03-04
16026666400 | INSTALL NEW CWT HEATER | [5 empty] | 188315.11 | 231341.3745 | -43026.2645 | 2022-01-01 | 2022-12-31 | 2022-01-26 | 2022-12-16 | CC# 53363. DRAINED WATERBATH HEATER. 01-26-22 DSASH CCC 55246 CCC 55359 CCC 55691 CCC 56098 CCC 57419 NO TICKET NEEDED NO TICKET NEEDED NO TICKET NEEDED CC# 70901. 6/20/22 DSASH RETIRED OLD WATER BATH INSTALLED NEW CWT HEATER DASH 3-3-22
16026666500 | RETIRE EXIST WB HEATER | [5 empty] | 29153.65 | 140.0254 | 29013.6246 | 2022-01-01 | 2022-12-31 | 2022-01-26 | 2022-03-03 | CCC # 53363 CCC 53705 CCC 54571 CCC # 54571 NO TICKET NEEDED CCC # 57419 NOT ON SITE NO CCC NEEDED NO CCC NOT ON SITE CHARGED TO LE TO GET VRG FOR REG REPLACE INSTALLED NEW CWT HEATER 3-3-22 DASH
20026930300 | UPGRADE ELECTRONICS | [5 empty] | 9306.71 | 3038 | 6268.71 | 2022-01-01 | 2022-12-31 | 2022-03-04 | 2022-03-04 | MET MOOSE ONSITE TO INSTALL SOLAR PANEL, CELL BOOSTER,BATTERY/BOX INSTALLED NEW EC350 WSHIMFESSEL JMULLINS COMPLETED PAPER WORK 06-13-2022
20026937500 | RETIRE ELECTRONICS | [5 empty] | 129.79 | 73.3494 | 56.4406 | 2022-01-01 | 2022-12-31 | 2022-03-04 | 2022-03-04 | RETIRED MINI-AT INSTALLED NEW EC350 JMULLINS CO PAPER WORK 06132022
22026223100 | EMER-INSTALL 3' OF 2"PMMP MAIN | [5 empty] | 4059.84 | 4624.3747 | -564.5347 | 2022-01-01 | 2022-12-31 | 2022-10-10 | 2022-10-11 | COMPLETED PAPERWORK FOR JOB. R.CRAWFORD 10-11-22
22026223200 | EMER-RETIRE 3' OF 2"PMP MAIN | [5 empty] | 125.23 | 89.0305 | 36.1995 | 2022-01-01 | 2022-12-31 | 2022-10-10 | 2022-10-17 | R.CRAWFORD
22026174700 | EMER- INSTALL 82'-4" PMIP/CSIP | [5 empty] | 85702.82 | 94519.5369 | -8816.7169 | 2022-01-01 | 2022-12-31 | 2022-03-08 | 2022-03-08 | REPAIRED LEAK ON MAIN BY REPLACING A SECTION OF BARE STEEL MAIN WITH 4" PLA STIC TESTED 105 PSIG FOR 1 HOUR WITH ELECTRONIC KUHLMAN GAUGE SERIAL NO 101 09154 3/8/22 REFER TO 2211 JOB ORDER# 22-9840666-00
22026174800 | EMER- RETIRE 76'-4" BSIP | [5 empty] | 0 | 0 | 0 | 2022-01-01 | 2022-12-31 | 2022-03-08 | 2022-03-08
21026111902 | INSTALL 7,500' OF 2"/6"PMMP | [5 empty] | 671698.12 | 670404.9715 | 1293.1485 | 2022-01-01 | 2022-12-31 | 2021-09-23 | 2022-03-11 | LOWES (#207438) - MATERIAL FOR ECP - $27.62 + 10% = $30.38 U461423 9/2 3/2021 SITE SUPPLY (#207438) - MULCH LOGS - #424.00 + 10% = 466.40 U461423 9/23/2021
22026158100 | INSTALL 70'-2" PMMP | [5 empty] | 10660.65 | 9277.6445 | 1383.0055 | 2022-01-01 | 2022-12-31 | 2022-03-07 | 2022-03-10 | INSTALED 57'OF 020PMMP.
20026982900 | RETIRE 3700'-2&4" BSLP | [5 empty] | 142.7 | 88.8156 | 53.8844 | 2022-01-01 | 2022-12-31 | 2021-09-30 | 2022-04-01
22026179300 | RETIRE 82'-2"&4" PMMP | [5 empty] | 82.8 | 73.9724 | 8.8276 | 2022-01-01 | 2022-12-31 | 2021-09-30 | 2022-04-02
22026175800 | EMER - INSTALL 120'-3" PMLP | [5 empty] | 32123.93 | 12124.3189 | 19999.6111 | 2022-01-01 | 2022-12-31 | 2022-03-11 | 2022-04-05 | INSTALLED 120' OF 3" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 10" W C
22026175900 | EMER - RETIRE 121'-3" P-LP | [5 empty] | 931.56 | 373.4562 | 558.1038 | 2022-01-01 | 2022-12-31 | 2022-03-11 | 2022-04-05 | RETIRE 121' OF 3" PL DUE TO WATER AND STEEL FITTINGS ON PL MAIN
22026158000 | INSTALL 200'-2" PMMP | [5 empty] | 23838.83 | 16273.357 | 7565.473 | 2022-01-01 | 2022-12-31 | 2022-03-14 | 2022-03-16
22026172900 | INSTALL 5' OF 4"PMLP S/L | [5 empty] | 3113 | 13312.2384 | -10199.2384 | 2022-01-01 | 2022-12-31 | 2022-03-15 | 2022-03-15
20026971200 | RETIRE 2100' OF 3"BSLP MAIN | [5 empty] | 1415.61 | 102.0836 | 1313.5264 | 2022-01-01 | 2022-12-31 | 2022-03-16 | 2022-03-18
22026172800 | RETIRE 5' OF 3"PLP S/L | [5 empty] | 0 | 58.5954 | -58.5954 | 2022-01-01 | 2022-12-31 | 2022-03-16 | 2022-03-16 | ABANDONED CAPITAL SERVICE LINE WITH ABANDON JOB # 18-0268434-00. LSHARON
22026168800 | ST. JAMES HVAC UPGRADE | [5 empty] | 24656.22 | 37587.0767 | -12930.8567 | 2022-01-01 | 2022-12-31 | 2022-03-16 | 2022-08-05 | MONITOR WHILE ACP SWAPS RTU STATION SET TO LOCAL MODE GC ADVISED CC 58614 UPGRADE RTU ON 3-16-22 JOSH MULLINS
22026214700 | ST. JAMES RTU PANEL | [5 empty] | 0 | 55.5311 | -55.5311 | 2022-01-01 | 2022-12-31 | 2022-03-16 | 2022-08-05 | UPGRADED RTU JOSH MULLINS
22026158400 | INSTALL 1200' OF 2"PMMP MAIN | [5 empty] | 29132.57 | 35742.3291 | -6609.7591 | 2022-01-01 | 2022-12-31 | 2022-03-14 | 2022-03-18
22026177000 | EMER - INSTALL 2'-4" PMIP | [5 empty] | 2292.91 | 4197.8249 | -1904.9149 | 2022-01-01 | 2022-12-31 | 2022-04-01 | 2022-04-01
22026177100 | EMER - RETIRE 2'-4" P-IP | [5 empty] | 2387.49 | 310.9595 | 2076.5305 | 2022-01-01 | 2022-12-31 | 2022-04-01 | 2022-04-01
22026244600 | INSTALL BUILDING AND FENCE | [5 empty] | 0 | 28935.3221 | -28935.3221 | 2022-01-01 | 2022-12-31 | 2022-03-17 | 2022-03-17 | INSTALLED COMM BUILDING AND FENCE DASH 3-17-22
19026855301 | INSTALL RTU AND BUILDING | [5 empty] | 186001.86 | 182784.6097 | 3217.2503 | 2022-01-01 | 2022-12-31 | 2022-03-17 | 2022-03-17 | INSTALLED NEW RTU DASH 3-17-22
19026855400 | RETIRE OLD RTU EQUIPMENT | [5 empty] | 5219.78 | 69.4128 | 5150.3672 | 2022-01-01 | 2022-12-31 | 2022-03-17 | 2022-03-17 | INSTALLED NEW COMM BUILDING AND RTU DASH 3-17-22
22026159400 | RETIRE S/L | [5 empty] | 2030.55 | 3024.4273 | -993.8773 | 2022-01-01 | 2022-12-31 | 2022-03-21 | 2022-03-21
22026168900 | STEPSTONE POD HVAC UPGRADE | [5 empty] | 19703.94 | 15710.0767 | 3993.8633 | 2022-01-01 | 2022-12-31 | 2022-03-24 | 2022-08-05 | CCC# 59338 CCC# 55889 UPGRADED RTU JOSH MULLINS
22026214300 | STEPSTONE POD HVAC/RTU | [5 empty] | 0 | 55.5311 | -55.5311 | 2022-01-01 | 2022-12-31 | 2022-03-24 | 2022-08-05 | UPGRADED RTU
21026130902 | INSTALL 5150' OF 2"/4" PMMP | [5 empty] | 192645.27 | 202239.5285 | -9594.2585 | 2022-01-01 | 2022-12-31 | 2022-01-26 | 2022-04-08
19026867100 | INSTALL VRG CONTROLLER | [5 empty] | 15917.94 | 15490.7518 | 427.1882 | 2022-01-01 | 2022-12-31 | 2022-03-29 | 2022-03-29 | CCC 59916 CCC # 59916 INSTALLED NEW VRG CONTROLLERS DASH 3-29-22
19026867200 | RETIRE CURRENT CONTROLLERS | [5 empty] | 1038.8 | 64.4897 | 974.3103 | 2022-01-01 | 2022-12-31 | 2022-03-29 | 2022-03-29 | CCC # INSTALLED NEW VRG'S RETIRED EXSISTING CONTROLLERS DASH 3-29-22
22026179500 | EMER - INSTALL 5'-2" PMIP | [5 empty] | 2346.49 | 5401.378 | -3054.888 | 2022-01-01 | 2022-12-31 | 2022-04-05 | 2022-04-05
22026179600 | EMER - RETIRE 5'-2" P-IP | [5 empty] | 0 | 238.1994 | -238.1994 | 2022-01-01 | 2022-12-31 | 2022-04-05 | 2022-04-05
22026163700 | RETIRE 4"BSLP SERVICE LINE | [5 empty] | 1327.16 | 105.0102 | 1222.1498 | 2022-01-01 | 2022-12-31 | 2022-04-08 | 2022-04-08 | CAPITAL SERVICE LINE WAS ABANDONED WITH JOB NUMBER 18-0268433-01 TIE IN A1A2. LSHARON
22026180700 | EMER - INSTALL 3'-3" PMIP | [5 empty] | 6701.19 | 4036.7887 | 2664.4013 | 2022-01-01 | 2022-12-31 | 2023-08-25 | 2023-08-25
22026180800 | EMER - RETIRE 3'-3" PMIP | [5 empty] | 61.4 | 418.4749 | -357.0749 | 2022-01-01 | 2022-12-31 | 2023-08-25 | 2023-08-25
21026140901 | INSTALL 2750' OF 2"PMMP MAIN | [5 empty] | 104070.68 | 96941.3864 | 7129.2936 | 2022-01-01 | 2022-12-31 | 2022-03-14 | 2022-04-15
22026182800 | EMER-INSTALL 3' OF 2"PMMP | [5 empty] | 4419.13 | 4826.1382 | -407.0082 | 2022-01-01 | 2022-12-31 | 2022-04-20 | 2022-04-20 | INSTALLED 3' OF 2" PMMP DUE TO EXCAVATION DAMAGE, TESTED MAIN PIPE AT 90# F OR 20 MIN PER FOL APPROVAL OK, SOAP TEST 2 020 EF CPLGS AT OP FOR 5 MIN OK. INSTALLED MARKER BALLS ON CPLGS. MAP REVISED. WHIMES
22026182900 | EMER-RETIRE 3' OF 2"PMMP | [5 empty] | 2.72 | 74.2578 | -71.5378 | 2022-01-01 | 2022-12-31 | 2022-04-20 | 2022-04-20 | RETIRED 3' OF 020 PMMP DUE TO EXCAVATION DAMAGE. WHIMES 04/20/2022
21026157000 | RETIRE 10'-6" PMLP | [5 empty] | 0 | 72.8047 | -72.8047 | 2022-01-01 | 2022-12-31 | 2022-04-08 | 2022-04-20
22026182300 | RETIRE PAPER RECORD GAUGE | [5 empty] | 144.38 | 329.4627 | -185.0827 | 2022-01-01 | 2022-12-31 | 2022-04-20 | 2022-04-20
21026103400 | INSTALL 2,700' - 2"/4" PMMP | [5 empty] | 185537.75 | 115766.1902 | 69771.5598 | 2022-01-01 | 2022-12-31 | 2022-03-09 | 2022-04-22 | TTOY-9/20/22: LEVEL 2 VARIANCE OVERRUN EXPLANATION IN WMSDOCS
21026994200 | RETIRE 3" SERVICE | [5 empty] | 0 | 98.6196 | -98.6196 | 2022-01-01 | 2022-12-31 | 2022-04-21 | 2022-04-21
20026992100 | RETIRE STATION | [5 empty] | 0 | 3400.2343 | -3400.2343 | 2022-01-01 | 2022-12-31 | 2022-04-21 | 2022-04-21 | RETIRED REGULATOR STATION JMARTIN
21026107000 | INSTALL 250' - 2" PMMP | [5 empty] | 72807.39 | 25983.7669 | 46823.6231 | 2022-01-01 | 2022-12-31 | 2022-04-22 | 2022-04-22 | OVERRUN EXPLANATION: PROJECT WAS PLANNED FOR OPEN CUT, NEW MAIN WAS INSTALL ED BY HEAVY ROCK BORE, ADDITIONAL LAND SERVICES WAS REQUIRED FOR EASMENT, BORE CREW HOURLY WAS MORE THAN ESTIMATED 3 MAN CREW
20026973800 | RETIRE 6801'-4' CILP | [5 empty] | 1501.61 | 107.2796 | 1394.3304 | 2022-01-01 | 2022-12-31 | 2022-04-22 | 2022-05-05
20026974100 | RETIRE 385'- 3" & 4" | [5 empty] | 2639.76 | 8962.6172 | -6322.8572 | 2022-01-01 | 2022-12-31 | 2022-04-22 | 2022-05-05
21026101600 | RETIRE 1200'-2"&4" BSMP | [5 empty] | 325.85 | 85.0089 | 240.8411 | 2022-01-01 | 2022-12-31 | 2022-03-10 | 2022-05-06
21026142800 | INSTALL 475'-4" PMLP | [5 empty] | 138313.25 | 59783.3635 | 78529.8865 | 2022-01-01 | 2022-12-31 | 2022-04-08 | 2022-04-29 | TTOY-9/20/22: OVERRUN LEVEL 2 VARIANCE EXPLANATION IN WMSDOCS
21026126700 | INSTALL 350' OF 2" PMMP | [5 empty] | 99374.93 | 123612.3972 | -24237.4672 | 2022-01-01 | 2022-12-31 | 2022-04-15 | 2022-05-09
21026126102 | INSTALL 2000' OF 2"PMMP MAIN | [5 empty] | 169255.42 | 165212.1661 | 4043.2539 | 2022-01-01 | 2022-12-31 | 2022-04-27 | 2022-08-02
21026126200 | RETIRE 270' OF 1"BSHP MAIN | [5 empty] | 0 | 63.0891 | -63.0891 | 2022-01-01 | 2022-12-31 | 2022-04-29 | 2022-08-02
22026216900 | PAPER ONLY EXECUTE | [5 empty] | 0 | 84.9152 | -84.9152 | 2022-01-01 | 2022-12-31 | 2022-04-29 | 2022-04-29
21026126600 | RETIRE REG STATION #1181 | [5 empty] | 1370.38 | 4088.2989 | -2717.9189 | 2022-01-01 | 2022-12-31 | 2022-04-29 | 2022-04-29 | RWILLIAMS COMPLETED PAPER WORK, EBLANTON RETIRED STATION ON 04/29/2022
20026981800 | RETIRE 18,000 - MP MAIN | [5 empty] | 0 | 82.4486 | -82.4486 | 2022-01-01 | 2022-12-31 | 2022-05-10 | 2022-05-26
21026134500 | INSTALL 1537'-2"PMIP | [5 empty] | 332303.55 | 208782.1462 | 123521.4038 | 2022-01-01 | 2022-12-31 | 2022-04-27 | 2022-08-26 | SEE PROJECT WORKSPACE 21-81540 FOR PROJECT OVERRUN EXPLANATION. D.LEMONS 10 /26/2022
21026117500 | INSTALL GMB SETTING | [5 empty] | 77589.89 | 58469.7613 | 19120.1287 | 2022-01-01 | 2022-12-31 | 2022-01-18 | 2022-05-03
22026166200 | INSTALL 20' OF 3"PMMP MAIN | [5 empty] | 23237.34 | 28323.8584 | -5086.5184 | 2022-01-01 | 2022-12-31 | 2022-05-02 | 2022-05-04
22026166300 | RETIRE 12' OF 3"PMP MAIN | [5 empty] | 90.73 | 62.3079 | 28.4221 | 2022-01-01 | 2022-12-31 | 2022-05-05 | 2022-05-05
22026158200 | INSTALL 100'-2" PMMP | [5 empty] | 22688.28 | 26700.5988 | -4012.3188 | 2022-01-01 | 2022-12-31 | 2022-05-04 | 2022-05-06
21026134600 | RETIRE 1053'-2" CSIP | [5 empty] | 0 | 109.7476 | -109.7476 | 2022-01-01 | 2022-12-31 | 2022-05-02 | 2022-08-26
22026174900 | INSTALL 50'-2" PMMP | [5 empty] | 36910.2 | 30717.8249 | 6192.3751 | 2022-01-01 | 2022-12-31 | 2022-05-09 | 2022-05-11
22026185100 | INSTALL 10'-2" PMMP | [5 empty] | 6123.2 | 3850.4525 | 2272.7475 | 2022-01-01 | 2022-12-31 | 2022-05-10 | 2022-05-10
22026185200 | RETIRE 10'-2" PMP | [5 empty] | 0 | 74.2578 | -74.2578 | 2022-01-01 | 2022-12-31 | 2022-05-10 | 2022-05-10
21026111300 | RETIRE R-1654 | [5 empty] | 0 | 3585.1779 | -3585.1779 | 2022-01-01 | 2022-12-31 |  | 2022-05-10 | ENTIRE STATION RETIRED INCLUDING INLET AND OUTLET PIPING WSHIMFESSEL 5/10/2 022, RWILLIAMS COMPLETED JOB AND PAPERWORK
22026209500 | RETIRE CHAIN LINK FENCE | [5 empty] | 0 | 65.0112 | -65.0112 | 2022-01-01 | 2022-12-31 | 2022-05-10 | 2022-05-10
22026178100 | INSTALL 20' OF 6"PMLP MAIN | [5 empty] | 14787.97 | 11448.7503 | 3339.2197 | 2022-01-01 | 2022-12-31 | 2022-05-04 | 2022-05-25
21026131200 | INSTALL 4875' OF 2"/4"PMMP | [5 empty] | 140463.01 | 141168.2553 | -705.2453 | 2022-01-01 | 2022-12-31 | 2022-03-21 | 2022-05-16
21026128802 | INSTALL 470' OF 4"PMMP MAIN | [5 empty] | 106230.58 | 96528.8129 | 9701.7671 | 2022-01-01 | 2022-12-31 | 2022-04-27 | 2022-05-25
21026114500 | RETIRE PIT REG STATION# 1024 | [5 empty] | 195061.46 | 149437.1771 | 45624.2829 | 2022-01-01 | 2022-12-31 | 2022-05-12 | 2022-05-12 | REMOVED 2 441 REGS AND BLIND FLANGED VALVES, STATION RETIRED, CMCHOLAN CCOX RHAYES 5-12-2022 RWILLIAMS COMPLETED PAPER WORK TWALKER/KY 11-30-22: JOB OVER RUN WAS DUE TO COST FOR 20-0269890-00 (2000) WITH LAND SERVICE AND CONTRACT ENG COST OF $65000, 19-0268950-00 (0001) MATERIAL FOR LPP MATERIAL OF $84000 AND 18-0268465-00 (2000) LAND SERVICES FOR LPP PROJECT APPROV $45000 FROM PROJECT MANAGEMENT AND GTMR GROUPS.
23026253500 | PM-GREENSITE IRONWORKS DE REPL | [5 empty] | 18978.29 | 1236355 | -1217376.71 | 2022-01-01 | 2022-12-31 | 2022-02-11 | 2022-05-13
22026179400 | RETIRE 100' OF 4"PMMP MAIN | [5 empty] | 0 | 75.4968 | -75.4968 | 2022-01-01 | 2022-12-31 | 2022-05-13 | 2022-05-13
23026253600 | PM-GREENSITE IRONWORKS ABAN | [5 empty] | 0 | 0 | 0 | 2022-01-01 | 2022-12-31 | 2022-05-13 | 2022-05-13
22026177700 | INSTALL 56'-6" PM-LP | [5 empty] | 100820.74 | 50137.1407 | 50683.5993 | 2022-01-01 | 2022-12-31 | 2022-04-25 | 2022-05-16 | OVERRUN EXPLANATION: PROJECT WAS INITIALLY PLANNED FOR 56 FEET OF INSTALL. HOWEVER, 171 FEET OF DIRECTIONAL ROCK BORE WERE REQUIRED INSTEAD WITHOUT A SCOPE CHANGE REQUEST. ADDITIONAL SAW CUT AND CUT AND REMOVE WERE REQUIRED A S WELL. STEEL PLATES WERE NOT ESTIMATED. $7000 OF SEWER CAMERA WERE NOT EST IMATED EITHER SINCE IT WAS INITALLY PLANNED DIFFERENTLY. ALL THIS ADDITIONA L WORK TOOK MORE TIME SO LABOR INCREASED BY $19,000 AND THE OVERHEAD EFFECT OF THESE CHANGES WAS $9000.
22026177800 | ABDN 20'-6" BS-LP | [5 empty] | 142.7 | 73.9724 | 68.7276 | 2022-01-01 | 2022-12-31 | 2022-05-16 | 2022-05-16
22026187600 | REPLACE ELECTRONIC COMPONENTS | [5 empty] | 31245.53 | 5349.5438 | 25895.9862 | 2022-01-01 | 2022-12-31 | 2022-05-16 | 2022-05-16 | CCC# 67613 REPLACED ERX WITH NEW MIWI 350. P2P OK, JMARTIN CCC# 67613
22026187700 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 39.46 | 124.5156 | -85.0556 | 2022-01-01 | 2022-12-31 | 2022-05-16 | 2022-05-16 | CCC# 67613 RETIRE ERX JMARTIN
22026178200 | INSTALL 850'-2" PMIP | [5 empty] | 28727.79 | 33743.7503 | -5015.9603 | 2022-01-01 | 2022-12-31 | 2022-05-13 | 2022-05-17
22026185400 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 1456 | 5480.5156 | -4024.5156 | 2022-01-01 | 2022-12-31 | 2022-05-17 | 2022-05-17 | JMARTIN REMOVED OLD ERX AND INSTALLED NEW MIWI 350 5-17-2022
22026185500 | RETIRE COMPONENTS | [5 empty] | 715.54 | 124.5156 | 591.0244 | 2022-01-01 | 2022-12-31 | 2022-05-17 | 2022-05-17 | CCC# 67011 NOT ABLE TO COMP AT THIS TIME, HAS OLDER ERX AND NEED MORE PARTS. JMARTIN 5-16-22 CCC# 67183 REPLACE ERX WITH NEW MIWI 350. JMARTIN
22026165100 | INSTALL 300'-2" PMIP | [5 empty] | 34102.05 | 29167.1057 | 4934.9443 | 2022-01-01 | 2022-12-31 | 2022-05-15 | 2022-05-18
21026111400 | RETIRE R-1653-B LP | [5 empty] | 0 | 3585.1779 | -3585.1779 | 2022-01-01 | 2022-12-31 | 2022-05-18 | 2022-05-18 | RETIRED LP RUN FROM R-1653 BLIND FLANGED INLET VALVE AND BYPASS VALVE WSHIM FESSEL, RWILLIAMS COMPLETED JOB AND PAPERWORK
22026187000 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 1100.73 | 4357.5409 | -3256.8109 | 2022-01-01 | 2022-12-31 | 2022-05-18 | 2022-05-18 | CCC# 67356 REPLACE ERX WITH NEW MIWI 350, P2P OK, JMARTIN CCC# 67669 WORKED TO FIX COMM ISSUE WITH MIWI. CCC# 67669
22026187100 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 0 | 124.5156 | -124.5156 | 2022-01-01 | 2022-12-31 | 2022-05-18 | 2022-05-18 | RETIRED OLD ERX JMARTIN 5/18/2022
22026186600 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 616.42 | 4216.5438 | -3600.1238 | 2022-01-01 | 2022-12-31 | 2022-05-19 | 2022-05-19 | INSTALLED MIWI 350 AND TUBING, CCC 67481 CMCHOLAN 5-19-2022 NOT ON SITE, TURNED IN PAPERWORK IN WINCHESTER, NO CCC TICKET, CMCHOLAN 5-20-2022
22026186700 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 485.53 | 124.5156 | 361.0144 | 2022-01-01 | 2022-12-31 | 2022-05-19 | 2022-05-19 | REMOVED ERX, CCC 67481 CMCHOLAN 5-19-2022 RWILLIAMS EX CAPITAL JOB
22026187400 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 1016.56 | 4773.0565 | -3756.4965 | 2022-01-01 | 2022-12-31 | 2022-05-20 | 2022-05-20 | CCC# 67055 INSTALL NEW MIWI 350, P2P OK, JMARTIN CCC# 67183
22026187500 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 0 | 124.5156 | -124.5156 | 2022-01-01 | 2022-12-31 | 2022-05-20 | 2022-05-20
22026197700 | INSTAL 3'-2" PMMP | [5 empty] | 1311.83 | 2387.9592 | -1076.1292 | 2022-01-01 | 2022-12-31 | 2022-05-21 | 2022-06-07 | HIT MAIN BY CONCRETE STAKE.MADE SAFE BY SQUEEZING OFF IN TWO BELL HOLES. REPLACED DAMAGED SECTION OF PIPE.TESTED 10FT OF 020 AND PURGE TEE FOR 1HR 90LBS.TEST OK.SOAP TEST END CAP AND 2EFC'S CPLGS AT OP.TEST OK BHB NGF
22026197800 | RETIRE 3'-2" PMMP | [5 empty] | 914.45 | 76.9137 | 837.5363 | 2022-01-01 | 2022-12-31 | 2022-05-21 | 2022-06-07 | HIT MAIN BY CONCRETE STAKE.MADE SAFE BY SQUEEZING OFF IN TWO BELL HOLES. REPLACED DAMAGED SECTION OF PIPE.TESTED 10FT OF 020 AND PURGE TEE FOR 1HR 90LBS.TEST OK.SOAP TEST END CAP AND 2EFC'S CPLGS AT OP.TEST OK BHB NGF
22026186200 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 0 | 5480.5156 | -5480.5156 | 2022-01-01 | 2022-12-31 | 2022-05-23 | 2022-05-23 | INSTALLED NEW MIWI 350 05/23/2022 GHALE
22026186300 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 190.3 | 124.5156 | 65.7844 | 2022-01-01 | 2022-12-31 | 2022-05-23 | 2022-05-23 | RETIRED OLD ERX 05/23/2022 GHALE
22026186400 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 548.88 | 5480.5156 | -4931.6356 | 2022-01-01 | 2022-12-31 | 2022-05-24 | 2022-05-24 | CCC# 68048 RETIRED ERX AND INSTALLED NEW MIWI350 JPASLEY
22026186500 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 0 | 124.5156 | -124.5156 | 2022-01-01 | 2022-12-31 | 2022-05-24 | 2022-05-24 | RETIRED ERX AND INSTALLED NEW MIWI350 JPASLEY
21026128900 | RETIRE 440' OF 4"BSMP MAIN | [5 empty] | 30.93 | 67.1085 | -36.1785 | 2022-01-01 | 2022-12-31 | 2022-05-24 | 2022-06-30 | X
21026129000 | RETIRE 680'-4"BSLP MN -D247885 | [5 empty] | 0 | 67.1085 | -67.1085 | 2022-01-01 | 2022-12-31 | 2022-05-25 | 2022-05-25
20026981700 | RETIRE 15,000' - LP MAIN | [5 empty] | 0 | 82.4486 | -82.4486 | 2022-01-01 | 2022-12-31 | 2022-05-25 | 2022-05-26
21026140100 | INSTALL 52'-4"/6" PMIP/CSIP | [5 empty] | 67346.12 | 83495.319 | -16149.199 | 2022-01-01 | 2022-12-31 | 2022-05-16 | 2022-05-31
21026140200 | RETIRE 47'-4"/6" BSIP/CSIP | [5 empty] | 207.25 | 500 | -292.75 | 2022-01-01 | 2022-12-31 | 2022-05-25 | 2022-05-31
22026187800 | INSTALL 10' OF 4"PMLP MAIN | [5 empty] | 29076.83 | 18153.0818 | 10923.7482 | 2022-01-01 | 2022-12-31 | 2022-05-23 | 2022-05-25
22026187900 | RETIRE 8' OF 4"PMLP MAIN | [5 empty] | 0 | 74.2578 | -74.2578 | 2022-01-01 | 2022-12-31 | 2022-05-24 | 2022-05-25
20026984500 | REPLACE IP OUTLET BLOCK VALVE | [5 empty] | 1480.71 | 2174.0477 | -693.3377 | 2022-01-01 | 2022-12-31 | 2022-05-25 | 2022-05-25 | NOT ON SITE REPLACED INLET AND OUTLET IP RUN BLOCK VALVES SGIORDANO JMULLINS CO PAPERWORK 06132022
20026984600 | REPLACE IP OUTLET BLOCK VALVE | [5 empty] | 2409.31 | 50 | 2359.31 | 2022-01-01 | 2022-12-31 | 2021-07-21 | 2022-05-25 | CCC 68181 REPLACED INLET AND OUTLET IP BLOCK VALVS SGIORDANO JMULLINS CO PAPERWORK 06132022
22026185800 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 1834.52 | 5480.5156 | -3645.9956 | 2022-01-01 | 2022-12-31 | 2022-05-25 | 2022-05-25 | CCC# 68240 - REPLACED ERX WITH MIWI 350 - BLONE/CWEMPE - 05/25/22 INSTALLED NEW MIWI 350
22026185900 | RETIRE ELECTRONIC COMPONETS | [5 empty] | 501.88 | 124.5156 | 377.3644 | 2022-01-01 | 2022-12-31 | 2022-05-25 | 2022-05-25 | CCC# 68240 - REPLACED ERX WITH MIWI 350 - BLONE/CWEMPE - 05/25/22 RETIRED OLD ERX
20026973500 | RETIRE STATION R-1458 | [5 empty] | 1295 | 1281.7771 | 13.2229 | 2022-01-01 | 2022-12-31 | 2022-05-26 | 2022-05-26
22026187200 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 1831.39 | 4745.0565 | -2913.6665 | 2022-01-01 | 2022-12-31 | 2022-05-26 | 2022-05-26 | CCC# 68726 INSTALLED NEW MIWI 350 AJPARKS
22026187300 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 185.7 | 124.5156 | 61.1844 | 2022-01-01 | 2022-12-31 | 2022-05-26 | 2022-05-26 | CCC# 68726 RETIRED ERX 05/26/2022 APARKS
20026943400 | RETIRE GAUGE | [5 empty] | 543.13 | 91.4991 | 451.6309 | 2022-01-01 | 2022-12-31 | 2022-05-27 | 2022-05-27 | REMOVED BOTH PAPER CHARTS INSTALLED ERX CC 62655 RHAYES SMCHOLAN CCOX EBLANTON 04-14-2022
20026943300 | INSTALL I&C EQUIPMENT | [5 empty] | 9146.19 | 16155.4774 | -7009.2874 | 2022-01-01 | 2022-12-31 | 2022-04-14 | 2022-05-27 | REMOVED BOTH PAPER CHARTS INSTALLED ERX FOR IP AND MP CMCHOLAN 4-14-2022 CC 65476 COMMISSIONED ERX RHAYES SMCHOLAN 05-03-2022 COMMITIONED ERX, PSP OK, CCC 65476 CMCHOLAN RHAYES 5-3-2022
22026186000 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 3201.06 | 5480.5156 | -2279.4556 | 2022-01-01 | 2022-12-31 | 2022-05-27 | 2022-05-27 | ACP REMOVED ERX REPLACED WITH MIWI CCOX RHAYES 05-27-2022
22026186100 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 175.52 | 124.5156 | 51.0044 | 2022-01-01 | 2022-12-31 | 2022-05-27 | 2022-05-27 | ACP REPLACED ERX WITH MIWI RHAYES CCOX 05-27-2022 ACP REPLACED ERX WITH MIWI RHAYES CCOX 05-27-2022
21026112300 | INSTALL 180' OF 4"PMMP S/L | [5 empty] | 24370.71 | 28556.5857 | -4185.8757 | 2022-01-01 | 2022-12-31 | 2022-05-23 | #N/A
22026227000 | EMER-INSTALL 3' OF 2"PMMP MAIN | [5 empty] | 5707.92 | 5024.0582 | 683.8618 | 2022-01-01 | 2022-12-31 | 2022-06-02 | 2022-09-30 | INST 3" OF 2 P MP MAIN PER GAS STANDARDS. MCRAIG 9/30/22
22026196200 | EMER - INSTALL 1'-2" PMMP | [5 empty] | 6510.29 | 2866.3857 | 3643.9043 | 2022-01-01 | 2022-12-31 | 2022-06-02 | 2022-06-15 | INSTALLED 1' OF 2" PL DUE TO FACILTY DAMAGE TESTED 90 PSIG 0005 MIN SOAP TE STED FINAL CONN OP 42 PSIG REVISED EXECUTE COMMENTS: INSTALLED 1' OF 2" PL DUE TO FACILITY DAMAGE TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 42 PSIG/MCOLLETT 7/8/22
22026227100 | EMER-RETIRE 3' OF 2"PMP MAIN | [5 empty] | 316.08 | 74.3089 | 241.7711 | 2022-01-01 | 2022-12-31 | 2022-06-02 | 2022-09-30 | ABN 3' OF 2" P MP MAIN DUE TO LEAK. PER GAS STANDARDS. MCRAIG 9/30/22
22026196300 | EMER - RETIRE 1'-2" P-MP | [5 empty] | 1254.11 | 497.9695 | 756.1405 | 2022-01-01 | 2022-12-31 | 2022-06-02 | 2022-06-15 | RETIRED 1' OF 2" PL MP DUE TO FACILITY DAMAGE SOAP TESTED OP TO VERIFY GAS SHUTOFF
22026188400 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 1456 | 6681.5691 | -5225.5691 | 2022-01-01 | 2022-12-31 | 2022-06-02 | 2022-06-02 | CCC# 69290 - BLONE - 06/02/22 INSTALLED MIWI SN:13450082 P1-0-PSI P2-0-60 IP:10.22.4.15MDN 859-221-6738
22026188500 | RETIRE ELECTRONICS | [5 empty] | 473.46 | 74.2578 | 399.2022 | 2022-01-01 | 2022-12-31 | 2022-06-02 | 2022-06-02 | CCC# 69290 - BLONE - 06/02/22
22026186800 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 1456 | 4357.5409 | -2901.5409 | 2022-01-01 | 2022-12-31 | 2022-06-03 | 2022-06-03 | CCC-69443 INSTALLED NEW MIWI 350 SOAP TEST CONNECTIONS EBLANTON
22026186900 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 504.03 | 124.5156 | 379.5144 | 2022-01-01 | 2022-12-31 | 2022-06-03 | 2022-06-03 | CCC-69443 RETIRED ERX EBLANTON
21026156700 | INSTALL 20'-3 PMMP | [5 empty] | 13109.07 | 12546.0469 | 563.0231 | 2022-01-01 | 2022-12-31 | 2022-06-03 | 2022-07-25
22026200300 | EMER - INSTALL 5'-2" PMIP | [5 empty] | 9101.9 | 2610.0199 | 6491.8801 | 2022-01-01 | 2022-12-31 | 2022-06-07 | 2022-06-07 | REPLACED 5' SECTION OF 2" PMMP. TESTED MAIN AT 90 PSIG FOR 1 HOUR AND TEST WAS GOOD. TESTED 2X1 EF TEES AT 90 PSIG FOR 5 MINS AND SOAP TESTED THE CAPS AND DEAD ENDS AT OP FOR 5 MINS. ALL TEST ARE GOOD.
21026156800 | ABDN CB 12'-3" PMP | [5 empty] | 0 | 73.9724 | -73.9724 | 2022-01-01 | 2022-12-31 | 2022-06-07 | 2022-08-01
23026270200 | EMER - RETIRE 5'-2" PIP | [5 empty] | 0 | 288.6068 | -288.6068 | 2022-01-01 | 2022-12-31 | 2022-06-07 | 2022-06-07 | REPLACED 5' SECTION OF 2" PMMP. TESTED MAIN AT 90 PSIG FOR 1 HOUR AND TEST WAS GOOD. TESTED 2X1 EF TEES AT 90 PSIG FOR 5 MINS AND SOAP TESTED THE CAPS AND DEAD ENDS AT OP FOR 5 MINS. ALL TEST ARE GOOD.
22026181600 | RELOCATE ~5"-2" PMMP | [5 empty] | 10366.16 | 6138.9503 | 4227.2097 | 2022-01-01 | 2022-12-31 | 2022-06-07 | 2022-06-14 | DURING AND AFTER REPLACEMENT PURGE NEW MAIN INTO SERVICE CO M.COLLINS/B.SEXTON RLA 6-7-2022 REPLACED 10' OF 2" P MP MAIN TEST 10' OF 2" PIPE ONSITE 90LBS FOR 1 HR NO LEAKS SOAP TEST TIE IN NO LEAKS BHB NGF SOAP TEST ALL TEE'S CAPS AND DEAD ENDS AT OP AFTER GUAGE REMOVAL NO LEAKS VERIFY DELIVERY PRESSURE BEFORE
22026181700 | RELOCATE ~5"-2" PMMP | [5 empty] | 0 | 75.4968 | -75.4968 | 2022-01-01 | 2022-12-31 | 2022-06-07 | 2022-06-14
20026973400 | RETIRE STATION R-1452 | [5 empty] | 114.18 | 1281.7771 | -1167.5971 | 2022-01-01 | 2022-12-31 | 2022-05-26 | 2022-06-08 | CCC# 68859 CCC# 68859 RETIRED REGSTATION PER AMRP PROJECT JMARTIN
22026169000 | MAVITY HVAC UPGRADE | [5 empty] | 5678.5 | 15264.0767 | -9585.5767 | 2022-01-01 | 2022-12-31 | 2022-06-08 | 2022-08-05
22026214400 | MAVITY HVAC/RTU | [5 empty] | 0 | 55.5311 | -55.5311 | 2022-01-01 | 2022-12-31 | 2022-06-08 | 2022-08-05 | UPGRADED RTU
20026973100 | RETIRE 120'-4" BSMP | [5 empty] | 1897.5 | 80.6441 | 1816.8559 | 2022-01-01 | 2022-12-31 | 2022-06-09 | 2022-06-30
20026973200 | RETIRE 10875' BS/CI LP | [5 empty] | 142.7 | 57.6441 | 85.0559 | 2022-01-01 | 2022-12-31 | 2022-06-09 | 2022-06-30
21026121300 | PM- SEWELL REPLACEMENT | [5 empty] | 2916870.85 | 1087500 | 1829370.85 | 2022-01-01 | 2022-12-31 | 2022-06-02 | 2022-06-09
21026121400 | PM- SEWELL ABANDONMENT | [5 empty] | 692157.41 | 62500 | 629657.41 | 2022-01-01 | 2022-12-31 | 2022-06-08 | 2022-06-09
19026861100 | INSTALL HEATER | [5 empty] | 2372.11 | 3045.0298 | -672.9198 | 2022-01-01 | 2022-12-31 | 2022-06-13 | #N/A | INSTALLED CAT HEATER
22026192300 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 281.87 | 4801.1928 | -4519.3228 | 2022-01-01 | 2022-12-31 | 2022-06-13 | 2022-06-13 | CHANGED ERX TO MIWI 350, P2P OK, CCC 70245 CMHOLAN 6-13-2022
22026192400 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 443.37 | 124.8731 | 318.4969 | 2022-01-01 | 2022-12-31 | 2022-06-13 | 2022-06-13 | REMOVED ERX TO INSTALL MIWI, CCC 70245 CMCHOLAN 6-13-2022 INSTALLED NEW MIWI350
20026977500 | INSTALL 4335'-4" & 6" PMLP | [5 empty] | 1014309.73 | 818557.1832 | 195752.5468 | 2022-01-01 | 2022-12-31 | 2022-04-12 | 2022-09-06 | TWALKER/KY 01-24-23: PROJECT OVER RUN COST DUE TO ADDITIONAL PAVING/HARD SURFACE REPAIR RESULTED IN $100,000 HIGHER CONTRACT COST, MATERIAL COST WERE $46,000 HIGHER THAN EST. ADN SEGA $68,000 HIGHER THAN EST.
21026101900 | RETIRE 6"MP SERVICE LINE | [5 empty] | 9737.82 | 9764.3857 | -26.5657 | 2022-01-01 | 2022-12-31 | 2022-06-13 | 2022-06-14 | INSTALLED BOLTED DEAD END CAP AT END OF NC 216695 VALVE. JOSH PASLEY 6/14/22
22026189300 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 487.15 | 4745.0565 | -4257.9065 | 2022-01-01 | 2022-12-31 | 2022-06-14 | 2022-06-14 | CC# 70358 RETIRED BOTH ERX'S INSTALLED NEW MIWI350 MRYAN 6-14-2022
22026189400 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 243.32 | 124.5156 | 118.8044 | 2022-01-01 | 2022-12-31 | 2022-06-14 | 2022-06-14 | CC # 70358 RETIRED OLD ERX'S INSTALLED NEW MIWI350 MRYAN 6-14-2022
22026189500 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 292.29 | 4745.0565 | -4452.7665 | 2022-01-01 | 2022-12-31 | 2022-06-15 | 2022-06-15 | CC # 70566 RETIRED OLD ERX INSTALLED NEW HONEYWELL MIWI350 MRYAN 6-15-2022
22026189700 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 91.91 | 4745.0565 | -4653.1465 | 2022-01-01 | 2022-12-31 | 2022-06-15 | 2022-06-15 | CC # 70497 RETIRED OLD ERX INSTALLED NEW MIW350 MRYAN 06-15-2022
22026189600 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 91.82 | 124.5156 | -32.6956 | 2022-01-01 | 2022-12-31 | 2022-06-15 | 2022-06-15 | CC # 70566 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 06-15-2022
22026189800 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 213.04 | 124.5156 | 88.5244 | 2022-01-01 | 2022-12-31 | 2022-06-15 | 2022-06-15 | CC # 70497 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-15-2022
22026175600 | RETIRE R-1256 | [5 empty] | 211.37 | 7307.4769 | -7096.1069 | 2022-01-01 | 2022-12-31 | 2022-06-15 | 2022-06-17 | STATION RETIRED AND ALL PIPING REMOVED WSHIMFESSEL 06-07-2022
22026185600 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 644.24 | 6006.2549 | -5362.0149 | 2022-01-01 | 2022-12-31 | 2022-06-20 | 2022-06-20 | CCC# 70942 INSTALL NEW MIWI 350, P2P W/GAS CONTROL OK, JMARTIN 6-20-22
22026185700 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 93.74 | 124.5156 | -30.7756 | 2022-01-01 | 2022-12-31 | 2022-06-20 | 2022-06-20 | CCC# 70942 RETIRE ERX AND REPLACE WITH MIWI 350, JMARTIN 6-20-22
22026191300 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 839.28 | 4801.1928 | -3961.9128 | 2022-01-01 | 2022-12-31 | 2022-06-20 | 2022-06-21 | CCC# 71072
22026191400 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 0 | 124.8731 | -124.8731 | 2022-01-01 | 2022-12-31 | 2022-06-21 | 2022-06-21
21026122000 | INSTALL 2150' OF 2"PMMP MAIN | [5 empty] | 178403.1 | 162365.3384 | 16037.7616 | 2022-01-01 | 2022-12-31 | 2022-05-10 | 2022-06-28
22026183600 | INSTALL 1700'-2" PMMP | [5 empty] | 51519.58 | 46580.9585 | 4938.6215 | 2022-01-01 | 2022-12-31 | 2022-06-06 | 2022-06-22
22026211400 | PAPER ONLY-RETIRE MP MAIN | [5 empty] | 0 | 65.0112 | -65.0112 | 2022-01-01 | 2022-12-31 | 2022-06-23 | 2022-06-23
22026165400 | RETIRE REG STATION #1203 | [5 empty] | 5686.24 | 4576.607 | 1109.633 | 2022-01-01 | 2022-12-31 | 2022-06-22 | 2022-06-22 | STATION RETIRED ALL PIPEING REMOVED 06-22-2022 AJPARKS
22026192500 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 400.52 | 4801.1928 | -4400.6728 | 2022-01-01 | 2022-12-31 | 2022-06-22 | 2022-06-22 | CCC# 71244
22026192600 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 0 | 124.8731 | -124.8731 | 2022-01-01 | 2022-12-31 | 2022-06-22 | 2022-07-05
22026162000 | RETIRE 110' OF 2"CSHP MAIN | [5 empty] | 716.93 | 105.0102 | 611.9198 | 2022-01-01 | 2022-12-31 | 2022-06-23 | 2022-06-28
22026190600 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 817.09 | 4801.1928 | -3984.1028 | 2022-01-01 | 2022-12-31 | 2022-06-23 | 2022-06-23 | CCC 71454 RETIRED ERX AND INSTALLED NEW MIWI350
22026191900 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 744.93 | 4801.1928 | -4056.2628 | 2022-01-01 | 2022-12-31 | 2022-06-23 | 2022-06-23 | CCC 71454
22026191000 | RETIRED ELECTRONICS EQUIPMENT | [5 empty] | 261.55 | 124.8731 | 136.6769 | 2022-01-01 | 2022-12-31 | 2022-06-23 | 2022-06-23 | CCC 71454 RETIRE ERX AND INSTALLED NEW MIWI 350
22026192000 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 922.45 | 124.8731 | 797.5769 | 2022-01-01 | 2022-12-31 | 2022-06-23 | 2022-06-23 | CCC 71454
22026208700 | EMER - RETIRE 2'-2" PMP | [5 empty] | 0 | 63.5475 | -63.5475 | 2022-01-01 | 2022-12-31 | 2022-06-24 | 2022-07-05
22026208600 | EMER - INSTALL 2'-2" PMMP | [5 empty] | 7597.73 | 5654.5749 | 1943.1551 | 2022-01-01 | 2022-12-31 | 2022-06-24 | 2022-07-05
22026191100 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 1305.26 | 4801.1928 | -3495.9328 | 2022-01-01 | 2022-12-31 | 2022-06-27 | 2022-06-27 | CC # 71822 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-27-2022
22026191200 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 229.57 | 124.8731 | 104.6969 | 2022-01-01 | 2022-12-31 | 2022-06-27 | 2022-06-27 | CC # 71822 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-27-2022
22026209400 | RETIRE CHAIN LINK FENCE | [5 empty] | 0 | 65.0112 | -65.0112 | 2022-01-01 | 2022-12-31 | 2022-06-28 | 2022-06-28
22026192700 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 780.12 | 4801.1928 | -4021.0728 | 2022-01-01 | 2022-12-31 | 2022-06-28 | 2022-06-28 | CC # 71922 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-28-2022
22026193200 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 271.17 | 4801.1928 | -4530.0228 | 2022-01-01 | 2022-12-31 | 2022-06-28 | 2022-06-28 | CC # 71922 RETIRED OLD ERX INSTALLED NEW MIWI 350 MRYAN 6/28/2022
22026192800 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 82.66 | 124.8731 | -42.2131 | 2022-01-01 | 2022-12-31 | 2022-06-28 | 2022-06-28 | CC # 71984 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-28-2022
22026193300 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 156.09 | 124.8731 | 31.2169 | 2022-01-01 | 2022-12-31 | 2022-06-28 | 2022-06-28 | CC # 71922 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6/28/2022
22026188600 | INSTALL 165'-2" PMMP | [5 empty] | 11945.7 | 14323.3857 | -2377.6857 | 2022-01-01 | 2022-12-31 | 2022-06-17 | 2022-06-29
22026189100 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 2559.49 | 4745.0565 | -2185.5665 | 2022-01-01 | 2022-12-31 | 2022-06-29 | 2022-06-29 | CC # 70264 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-29-2022
22026189200 | RETIRE ELECTRONIC EQUIPMENT | [5 empty] | 213.04 | 124.5156 | 88.5244 | 2022-01-01 | 2022-12-31 | 2022-06-22 | 2022-06-29 | CC # 70264 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-29-2022
22026177900 | INSTALL 8' OF 6"PMMP MAIN | [5 empty] | 36900.11 | 29164.4 | 7735.71 | 2022-01-01 | 2022-12-31 | 2022-06-17 | 2022-07-11
22026178000 | RETIRE 4' OF 6"CSMP MAIN | [5 empty] | 876.45 | 75.4968 | 800.9532 | 2022-01-01 | 2022-12-31 | 2022-06-17 | 2022-07-11
21026120200 | PM-INS PIG REC/FILTER JIM BEAM | [5 empty] | 2542524.27 | 2579017 | -36492.73 | 2022-01-01 | 2022-12-31 | 2021-06-13 | 2022-06-30
21026120300 | PM-ABA FOR EQUIP INST JIM BEAM | [5 empty] | 835157.07 | 62500 | 772657.07 | 2022-01-01 | 2022-12-31 | 2021-06-13 | 2022-06-30
18026764800 | INSTALL COMM BUILDING | [5 empty] | 132078.26 | 156664.9991 | -24586.7391 | 2022-01-01 | 2022-12-31 | 2018-06-12 | 2022-06-30 | 72003 INSTALLED RTU BUILDING AND TRANSDUCERS
22026189900 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 275.74 | 4745.0565 | -4469.3165 | 2022-01-01 | 2022-12-31 | 2022-06-30 | 2022-06-30 | CC # 72215 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6/30/2022
22026194400 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 356.51 | 4801.1928 | -4444.6828 | 2022-01-01 | 2022-12-31 | 2022-06-30 | 2022-06-30 | CC # 72268 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-30-2022
22026190000 | RETIRED ELECTRONICS EQUIPMENT | [5 empty] | 61.53 | 124.5156 | -62.9856 | 2022-01-01 | 2022-12-31 | 2022-06-30 | 2022-06-30 | CC # 72215 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6/30/2022
22026194500 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 1.84 | 124.8731 | -123.0331 | 2022-01-01 | 2022-12-31 | 2022-06-30 | 2022-06-30 | CC # 72268 RETIRED OLD ERX INSTALLED NEW MIWI 350 MRYAN 6-30-2022
22026206900 | EMER-INSTALL 16' OF 4"/6"PMLP | [5 empty] | 11009.07 | 8399.775 | 2609.295 | 2022-01-01 | 2022-12-31 | 2022-06-30 | 2022-07-15 | LEAKING POSI HOLD COUPLING.LEAKING OUT OF FITTING ON COUPLING. REPLACED 6'' TEE AND 19FT OF MAIN.TESTED MAIN FOR 1HR AT 90LBS.TEST OK. SOAP TEST FINAL TIE INS AT OP FOR 5MINS AT OP.TEST OK. BHB NGF.
22026207000 | EMER-RETIRE 14' OF 6"BSLP | [5 empty] | 11230.19 | 60.0112 | 11170.1788 | 2022-01-01 | 2022-12-31 | 2022-06-30 | 2022-07-15 | LEAKING POSI HOLD COUPLING.LEAKING OUT OF FITTING ON COUPLING. REPLACED 6'' TEE AND 19FT OF MAIN.TESTED MAIN FOR 1HR AT 90LBS.TEST OK. SOAP TEST FINAL TIE INS AT OP FOR 5MINS AT OP.TEST OK. BHB NGF.
22026210100 | EMER - INSTALL 6'-4" PMMP | [5 empty] | 5514.88 | 4810.9373 | 703.9427 | 2022-01-01 | 2022-12-31 | 2022-07-05 | 2022-07-26 | DAMAGED SECTION OF PIPE DUE TO EXCAVATOR ERROR.MADE SAFE BY SQUEEZING OFF IN BELLHOLES.OC 16FT NEW MAIN DUE TO EXCAVATION WHERE DAMAGE WAS TOO DEEP. TESTED MAIN 1HR AR 90LB.TEST OK.SOAP TEST EFC'SAT OP.TEST OK BHB NGF
22026210200 | EMER - RETIRE 6'-4" PMMP | [5 empty] | 95.05 | 63.5475 | 31.5025 | 2022-01-01 | 2022-12-31 | 2022-07-05 | 2022-07-26 | DAMAGED SECTION OF PIPE DUE TO EXCAVATOR ERROR.MADE SAFE BY SQUEEZING OFF IN BELLHOLES.OC 16FT NEW MAIN DUE TO EXCAVATION WHERE DAMAGE WAS TOO DEEP. TESTED MAIN 1HR AR 90LB.TEST OK.SOAP TEST EFC'SAT OP.TEST OK BHB NGF
22026211000 | EMER - INSTALL 3'-4" PMMP | [5 empty] | 8542 | 12351.4608 | -3809.4608 | 2022-01-01 | 2022-12-31 | 2022-07-05 | 2022-07-28 | CUT OUT 3' OF 4" PL MP AND REPLACED WITH NEW 3' OF 4" PL MP TESTED 90 PSIG 1 HOUR
22026211100 | EMER - RETIRE 3'-4" PMMP | [5 empty] | 449.88 | 477.8601 | -27.9801 | 2022-01-01 | 2022-12-31 | 2022-07-05 | 2022-07-28 | RETIRED 3' OF 4" PL MP AND INSTALLED NEW 3' OF 4" PL TESTED 90 PSIG 1 HOUR SOAP TESTD FINAL CONN OP 40 PSIG
22026211200 | EMER-INSTALL 6' OF 4"PMIP MAIN | [5 empty] | 13924.65 | 10641.1495 | 3283.5005 | 2022-01-01 | 2022-12-31 | 2022-07-07 | 2022-07-07
22026211300 | EMER-RETIRE 6' OF 4"PAIP MAIN | [5 empty] | 0 | 65.0112 | -65.0112 | 2022-01-01 | 2022-12-31 | 2022-07-07 | 2022-07-07
22026208900 | EMER - INSTALL ~10'-8" CSHP | [5 empty] | 59795.62 | 32930.2498 | 26865.3702 | 2022-01-01 | 2022-12-31 | 2022-07-07 | 2022-07-07
18026770100 | RETIRE CHART | [5 empty] | 0 | 1613.3811 | -1613.3811 | 2022-01-01 | 2022-12-31 | 2022-07-07 | 2022-07-07 | RETIRED PAPER CHART MRYAN 07-07-2022
18026847000 | INSTALL CATALYTIC HEATER | [5 empty] | 3779.78 | 3926.2882 | -146.5082 | 2022-01-01 | 2022-12-31 | 2022-07-08 | 2022-07-08 | CC# 49296. 12/21/21 DSASH NO CC# NEEDED, DID NOT GO ON SITE. 12/22/21 DSASH GMB NO CC NEEDED RETIRED OLD CATALYTIC HEATER INSTALLED NEW CATALYTIC HEATER MRAYN 7-8-22
18026847200 | INSTALL CATALYTIC HEATER | [5 empty] | 3110.02 | 3926.2882 | -816.2682 | 2022-01-01 | 2022-12-31 | 2022-07-08 | 2022-07-08 | RETIRED OLD CATALYTIC HEATER AND INSTALLED NEW CATALYTIC HEATER MRYAN 7-8-2022
18026847100 | RETIRE CATALYTIC HEATER | [5 empty] | 426.13 | 77.1956 | 348.9344 | 2022-01-01 | 2022-12-31 | 2022-07-08 | 2022-07-08 | RETIRED OLD CATALYTIC HEATER INSTALLED NEW CATALYTIC HEATER MRYAN 7-8-2022
18026847300 | RETIRE CATALYTIC HEATER | [5 empty] | 313.52 | 77.1956 | 236.3244 | 2022-01-01 | 2022-12-31 | 2022-07-08 | 2022-07-08 | RETIRED CATALYTIC HEATER INSTALLED NEW CATALYTIC HEATER MRYAN 7-8-2022
22026210600 | EMER-RETIRE 50' OF 3"BSLP MAIN | [5 empty] | 2854.75 | 5032.3621 | -2177.6121 | 2022-01-01 | 2022-12-31 | 2022-07-10 | 2022-09-12
22026215700 | EMER-INSTALL 2' OF 2"PMMP MAIN | [5 empty] | 4910.67 | 8681.8934 | -3771.2234 | 2022-01-01 | 2022-12-31 | 2022-07-11 | 2022-08-22 | REPLACED 2FT OF 020 DAMAGED MAIN.TESTED NEW MAIN FOR 20MINS AT 90LBS.TEST OK.SOAP TEST EFC'S AT OP FOR 5MINS.TEST OK. BHBNGF
22026211500 | EMER-INSTALL 5'-2" PMMP | [5 empty] | 5656.19 | 16105.0112 | -10448.8212 | 2022-01-01 | 2022-12-31 | 2022-07-11 | 2022-09-12
22026215800 | EMER-RETIRE 2' OF 2"PMP MAIN | [5 empty] | 224.99 | 84.9152 | 140.0748 | 2022-01-01 | 2022-12-31 | 2022-07-11 | 2022-08-22 | REPLACED 2FT OF 020 DAMAGED MAIN.TESTED NEW MAIN FOR 20MINS AT 90LBS.TEST OK.SOAP TEST EFC'S AT OP FOR 5MINS.TEST OK. BHBNGF
22026211600 | EMER-RETIRE 5'-2" PMMP | [5 empty] | 3884.45 | 4031.2726 | -146.8226 | 2022-01-01 | 2022-12-31 | 2022-07-11 | 2022-09-12
22026184600 | INSTALL 64' OF 2"PMMP MAIN | [5 empty] | 16772.5 | 17899.1411 | -1126.6411 | 2022-01-01 | 2022-12-31 | 2022-06-27 | 2022-07-11
22026184700 | RETIRE 52' OF 2"PMMP MAIN | [5 empty] | 0 | 74.2578 | -74.2578 | 2022-01-01 | 2022-12-31 | 2022-06-27 | 2022-07-11
20026929500 | UPGRADE ELECTRONICS | [5 empty] | 5670.86 | 3038 | 2632.86 | 2022-01-01 | 2022-12-31 | 2022-07-11 | 2022-07-11 | RETIRED OLD MINNI-AT INSTALLED NEW EC350 BLONE 07-11-2022
20026935200 | RETIRE ELECTRONICS | [5 empty] | 742.7 | 73.3494 | 669.3506 | 2022-01-01 | 2022-12-31 | 2022-07-11 | 2022-07-11 | RETIRED OLD MINI-AT INSTALLED NEW EC350 BLONE 07-11-2022
23026252900 | PM-GREENSITE RAILROAD CROSSING | [5 empty] | 17890.94 | 1236355 | -1218464.06 | 2022-01-01 | 2022-12-31 | 2022-04-10 | 2022-07-12
23026253000 | PM-GREENSITE RAILROAD ABANDON | [5 empty] | 328.14 | 0 | 328.14 | 2022-01-01 | 2022-12-31 | 2022-04-10 | 2022-07-12
22026191500 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 1457.43 | 4801.1928 | -3343.7628 | 2022-01-01 | 2022-12-31 | 2022-07-12 | 2022-08-16 | UPGRADED ERX TO MIWI
22026191600 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 447.49 | 124.8731 | 322.6169 | 2022-01-01 | 2022-12-31 | 2022-07-12 | 2022-08-16 | CC # 73221 UPGRADDED ERX TO MIWI
22026180500 | INSTALL 160'-2" PMIP | [5 empty] | 22724.8 | 36664.9938 | -13940.1938 | 2022-01-01 | 2022-12-31 | 2022-07-08 | 2022-07-13
22026215900 | EMER-INSTALL 3' OF 2"PMMP MAIN | [5 empty] | 1854.5 | 3722.1191 | -1867.6191 | 2022-01-01 | 2022-12-31 | 2022-07-13 | 2022-08-22 | REPLACED 3FT SECTION OF MAIN. TESTED NEW SECTION OF MAIN FOR 20MINS AT 90LBS.TEST OK SOAP TEST EFC'S AT OP FOR 5MINS.TEST OK. BHBNGF
22026216000 | EMER-RETIRE 3' OF 2"PAMP MAIN | [5 empty] | 143.19 | 84.9152 | 58.2748 | 2022-01-01 | 2022-12-31 | 2022-07-13 | 2022-08-22 | REPLACED 3FT SECTION OF MAIN. TESTED NEW SECTION OF MAIN FOR 20MINS AT 90LBS.TEST OK SOAP TEST EFC'S AT OP FOR 5MINS.TEST OK. BHBNGF
22026194200 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 1788.47 | 4801.1928 | -3012.7228 | 2022-01-01 | 2022-12-31 | 2022-07-13 | 2022-08-08 | CC # 73334
22026194300 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 470.99 | 124.8731 | 346.1169 | 2022-01-01 | 2022-12-31 | 2022-07-13 | 2022-08-08 | CC # 73334 UPDATTED ERX TO MIWI 07-13-22 J. MULLINS
22026202200 | INSTALL 125' OF 2" PMMP MAIN | [5 empty] | 11459.71 | 8841.6395 | 2618.0705 | 2022-01-01 | 2022-12-31 | 2022-07-14 | 2022-07-14
20026928200 | UPGRADE ELECTRONICS | [5 empty] | 3460.63 | 3038 | 422.63 | 2022-01-01 | 2022-12-31 | 2022-07-14 | 2022-07-14 | CMCHOLAN 7-14-2022 RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07-14-2022
20026928400 | UPGRADE FROM 3G NETWORK | [5 empty] | 3177.17 | 3038 | 139.17 | 2022-01-01 | 2022-12-31 | 2022-07-14 | 2022-07-14 | RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07-14-2022
20026928600 | UPGRADE ELECTRONICS | [5 empty] | 3158.07 | 5626 | -2467.93 | 2022-01-01 | 2022-12-31 | 2022-07-14 | 2022-07-14 | RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON
20026933900 | RETIRE ELECTRONICS | [5 empty] | 1039.15 | 73.3494 | 965.8006 | 2022-01-01 | 2022-12-31 | 2022-07-08 | 2022-07-14 | CMCHOLAN 7-14-2022 RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07142022
20026934100 | RETIRE ELECTRONICS | [5 empty] | 189.27 | 73.3494 | 115.9206 | 2022-01-01 | 2022-12-31 | 2022-07-14 | 2022-07-14 | RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07-14-2022
22026210000 | RETIRE ELECTRONICS | [5 empty] | 249.16 | 65.0112 | 184.1488 | 2022-01-01 | 2022-12-31 | 2022-07-14 | 2022-07-14 | RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07-14-2022
22026193800 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 1577.79 | 4801.1928 | -3223.4028 | 2022-01-01 | 2022-12-31 | 2022-07-14 | 2022-08-08 | CC # 73511
22026194000 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 1673.13 | 4801.1928 | -3128.0628 | 2022-01-01 | 2022-12-31 | 2022-07-14 | 2022-08-08 | CC # 73511 UPGRADED FROM ERX TO MIWI JOSH MULLINS
22026193900 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 235.52 | 124.8731 | 110.6469 | 2022-01-01 | 2022-12-31 | 2022-07-14 | 2022-08-08 | CC # 73511 UPGRADED TO MIWI JOSH MULLINS
22026194100 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 230.5 | 124.8731 | 105.6269 | 2022-01-01 | 2022-12-31 | 2022-07-14 | 2022-08-08 | CC # 73511
21026118100 | INSTALL 5680'-2"/4" PMMP | [5 empty] | 156088.03 | 165876.9601 | -9788.9301 | 2022-01-01 | 2022-12-31 | 2022-05-10 | 2022-07-20
20026928500 | UPGRADE ELECTRONICS | [5 empty] | 3667.3 | 3038 | 629.3 | 2022-01-01 | 2022-12-31 | 2022-07-19 | 2022-07-19 | CWEMPE BLONE 7/19/22 RETIRED MINI-AT INSTALLED NEW EC350 CWEMPE 07-19-2022
20026934200 | RETIRE ELECTRONICS | [5 empty] | 502.89 | 73.3494 | 429.5406 | 2022-01-01 | 2022-12-31 | 2022-07-19 | 2022-07-19 | CWEMPE BLONE 7/19/22 RETIRED OLD MINI-AT INSTALLED NEW EC350
22026190800 | INSTALL 50'-4" PMLP | [5 empty] | 48441.53 | 45570.6341 | 2870.8959 | 2022-01-01 | 2022-12-31 | 2022-07-14 | 2022-07-21
22026190900 | RETIRE 41'-4" BSLP | [5 empty] | 114.59 | 78.4365 | 36.1535 | 2022-01-01 | 2022-12-31 | 2022-07-20 | 2022-07-21
21026145800 | REPLACE VALVES ON HP-MP REG | [5 empty] | 33552.7 | 14136.4861 | 19416.2139 | 2022-01-01 | 2022-12-31 | 2022-07-12 | 2022-07-20 | CCC# 73837 CCC# 74028 CCC# 74317 REPLACED INLET, OUTLET, AND BOTH BYPASS VLVS ON STATION. JMARTIN 7/20/22
21026145900 | RETIRE 4 VALVES ON REG STATION | [5 empty] | 1355.49 | 600.4497 | 755.0403 | 2022-01-01 | 2022-12-31 | 2022-07-08 | 2022-07-20 | INSTALLED TEMPORARY REG SETTING REPLACED ALL FOUR SETTING VALVES JMARTIN 07 -20-2022
22026183800 | INSTALL 100'-2" PMIP | [5 empty] | 16969.45 | 18017.5748 | -1048.1248 | 2022-01-01 | 2022-12-31 | 2022-07-21 | 2022-07-21
22026215300 | EMER - INSTALL 20'-2" PMIP | [5 empty] | 15168.73 | 10433.2304 | 4735.4996 | 2022-01-01 | 2022-12-31 | 2022-07-20 | 2022-07-21
22026215500 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 6774.27 | 4479.378 | 2294.892 | 2022-01-01 | 2022-12-31 | 2022-07-21 | 2022-07-21
22026215400 | EMER - RETIRE 5'-2" PMIP | [5 empty] | 0 | 80.5311 | -80.5311 | 2022-01-01 | 2022-12-31 | 2022-07-20 | 2022-07-21
22026215600 | EMER - RETIRE 5'-2" PMMP | [5 empty] | 0 | 84.9152 | -84.9152 | 2022-01-01 | 2022-12-31 | 2022-07-21 | 2022-07-21
21026156900 | INSTALL 10'-6" PMLP | [5 empty] | 6980.82 | 14786.2791 | -7805.4591 | 2022-01-01 | 2022-12-31 | 2022-07-21 | 2022-07-21 | INSTALLATION COMPLETE, HMCKUNE
22026191700 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 10605.54 | 4801.1928 | 5804.3472 | 2022-01-01 | 2022-12-31 | 2022-07-25 | 2022-08-12 | UPGRADED ERX TO MIWI JOSH MULLINS
22026191800 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 20.04 | 124.8731 | -104.8331 | 2022-01-01 | 2022-12-31 | 2022-07-25 | 2022-08-12
22026232000 | RETIRE PAPER GAUGE | [5 empty] | 0 | 993 | -993 | 2022-01-01 | 2022-12-31 | 2022-07-26 | 2022-07-26 | RETIRED PAPER CHART 7-26-22 CCOX
22026192100 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 2317.01 | 4801.1928 | -2484.1828 | 2022-01-01 | 2022-12-31 | 2022-07-26 | 2022-08-15 | CCC 75023
22026192200 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 884.51 | 124.8731 | 759.6369 | 2022-01-01 | 2022-12-31 | 2022-07-26 | 2022-08-15 | CCC 75023 UPGRADED ERX TO MIWI J.MULLINS
22026214800 | EMER INSTALL 2' - PMMP | [5 empty] | 8176.85 | 2418.3858 | 5758.4642 | 2022-01-01 | 2022-12-31 | 2022-07-27 | 2022-07-27
22026214900 | EMER RETIRE 2'-PMP | [5 empty] | 0 | 84.9152 | -84.9152 | 2022-01-01 | 2022-12-31 | 2022-07-27 | 2022-07-27
22026193400 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 1938.82 | 4801.1928 | -2862.3728 | 2022-01-01 | 2022-12-31 | 2022-07-27 | 2022-08-17 | CC # 75237 NO CC NOT ONSITE PAPERWORK NO CC NEEDED UPGRADDED ERX TO MIWI JMULLINS
22026196000 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 6078.6 | 4801.1928 | 1277.4072 | 2022-01-01 | 2022-12-31 | 2022-07-27 | 2022-07-27 | CC # 75237 RETIRED OLD ERX AND INSTALLED NEW HONEYWELL MIWI350 MRYAN 7-27-2022
22026193500 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 22.08 | 124.8731 | -102.7931 | 2022-01-01 | 2022-12-31 | 2022-07-27 | 2022-08-17 | CC # 75237
22026196100 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 232.52 | 124.8731 | 107.6469 | 2022-01-01 | 2022-12-31 | 2022-07-27 | 2022-07-27 | CC # 75237 RETIRED OLD ERX INSTALLED NEW HONEY WELL MIWI350 MATT RYAN 7-27-2022
21026114200 | INSTALL 100'-2" PMMP | [5 empty] | 19306.24 | 12690.4563 | 6615.7837 | 2022-01-01 | 2022-12-31 | 2022-07-14 | 2022-07-28
22026215000 | EMER INSTALL 2'-4" PMLP | [5 empty] | 9400.14 | 3659.4376 | 5740.7024 | 2022-01-01 | 2022-12-31 | 2022-07-28 | 2022-07-28
22026215100 | EMER RETIRE 2'-4" PLP | [5 empty] | 0 | 84.9152 | -84.9152 | 2022-01-01 | 2022-12-31 | 2022-07-28 | 2022-07-28
22026218200 | RETIRE PAPER GUAGE | [5 empty] | 0 | 339.1994 | -339.1994 | 2022-01-01 | 2022-12-31 | 2022-07-28 | 2022-07-28 | RETIRE PAPER CHART DUE TO ERX INSTALL AT ANOTHER STATION SMCHOLAN
22026218300 | RETIRE PAPER GAUGE | [5 empty] | 0 | 339.1994 | -339.1994 | 2022-01-01 | 2022-12-31 | 2022-07-28 | 2022-07-28 | RETIRED PAPER CHART DUE TO ERX INSTALL AT ANOTHER LOCATION
20026941400 | INSTALL I&C EQUIPMENT | [5 empty] | 12022.54 | 16155.4774 | -4132.9374 | 2022-01-01 | 2022-12-31 | 2020-06-08 | 2022-07-28 | INSTALLED TAP ON OUTLET LEG OF RUN 1 20# SYSTEM AND RAN SENSE LINES TO ERX FROM THE NEW TAP AND EXISTING HP SENSE LINE, AND COMMISSIONED ERX CCC 75328, CMCHOLAN CCOX 7-28-2022
22026213800 | EMER - RETIRE 150'-2" P-IP | [5 empty] | 4136.05 | 4412.2636 | -276.2136 | 2022-01-01 | 2022-12-31 | 2022-08-01 | 2022-09-06 | ABANDONED 150' OF 2" PLASTIC. SOAP TESTED ABANDONMENT AT OP. PRESS. 15MIN.
20026976501 | INSTALL 4270' OF 2"/4"PMMP MN | [5 empty] | 1937333.59 | 1522347.7868 | 414985.8032 | 2022-01-01 | 2022-12-31 | 2022-02-21 | 2022-08-05 | WIPE SAMPLE RESULTS WERE ENTERED ON THE INSTALL JOB IN ERROR. WIPE RESULTS FOR THE RETIREMENT PIPE WERE ENTERED HERE. TWALKER/KY 01-24-23: JOB OVER RUN DUE TO ADDITIONAL STREET/HARD SURFACE REP AIRS REQUIRED BY CITY OF LEXINGTON. CONTRACT COST INCREASED BY $200,000 WITH PAVING/FLAGGING COST, SEGA WAS $73,000 HIGHER THAN PLANNED, ADDITIONAL $22,000 CHARGED FOR MATERIAL COST. TWALKER/KY 08-29-23: LEVEL 2 VARIANCE ADDED TO WMS.DOCS. JOB COST OVERRUN DUE TO ADDITIONAL STREET MILL/RE-PAVED COST REQUIRED BY CITY OF LEXINGTON.
20026976600 | RETIRE 4650' OF 3"/4"BSLP MN | [5 empty] | 320 | 56.8875 | 263.1125 | 2022-01-01 | 2022-12-31 | 2022-02-21 | 2022-08-05
22026184500 | INSTALL 250'-4" PMLP/CSLP | [5 empty] | 63976.36 | 60316.4006 | 3659.9594 | 2022-01-01 | 2022-12-31 | 2022-07-13 | 2022-08-10
22026218400 | RETIRE 2'-4" BSLP | [5 empty] | 0 | 84.9152 | -84.9152 | 2022-01-01 | 2022-12-31 | 2022-08-15 | 2022-08-15
22026216500 | EMER-INSTALL 2"/4" POLY VALVES | [5 empty] | 433396.83 | 298130.9642 | 135265.8658 | 2022-01-01 | 2022-12-31 | 2022-02-01 | 2022-08-11 | COMPLETED OVERRUN EXPLANATION FORM LOADED INTO WMSDOCS JO WORKSPACE. D.LEMO NS 2/24/2023
22026222800 | EMER-INSTALL 2' OF 4"PMMP MAIN | [5 empty] | 21988.24 | 23837.8998 | -1849.6598 | 2022-01-01 | 2022-12-31 | 2022-08-11 | 2022-09-12
22026222900 | EMER-RETIRE 2' OF 4"PMMP MAIN | [5 empty] | 0 | 89.0305 | -89.0305 | 2022-01-01 | 2022-12-31 | 2022-08-11 | 2022-09-12
22026216600 | EMER-RETIRE 7'-2"/4" PMIP/CSIP | [5 empty] | 0 | 83.4538 | -83.4538 | 2022-01-01 | 2022-12-31 | 2022-08-11 | 2022-08-11
22026198200 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5532.75 | 4801.1928 | 731.5572 | 2022-01-01 | 2022-12-31 | 2022-08-11 | 2022-08-11 | CC 76915 UPGRADDED ERX TO MIWI 350
22026198300 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 467.24 | 124.8731 | 342.3669 | 2022-01-01 | 2022-12-31 | 2022-08-11 | 2022-08-11 | CC 76915 UPDATTED ERX TO MIWI 350
22026217500 | EMER-INSTALL 2' OF 3"PMMP MAIN | [5 empty] | 6378.4 | 5764.1191 | 614.2809 | 2022-01-01 | 2022-12-31 | 2022-08-11 | 2022-08-12
22026217600 | EMER-RETIRE 2' OF 3"PAMP MAIN | [5 empty] | 4155.42 | 1084.9152 | 3070.5048 | 2022-01-01 | 2022-12-31 | 2022-08-11 | 2022-08-12
21026126800 | INSTALL 11,170' OF 2"/6"PMMP | [5 empty] | 1672773.41 | 1492284.9718 | 180488.4383 | 2022-01-01 | 2022-12-31 | 2022-01-03 | 2022-10-10
22026200600 | INSTALL 15' OF 3"/4"PMLP S/L | [5 empty] | 10449.59 | 11118.4162 | -668.8262 | 2022-01-01 | 2022-12-31 | 2022-06-17 | 2022-08-15
22026200500 | RETIRE 2' OF 3"PLP S/L | [5 empty] | 0 | 62.4365 | -62.4365 | 2022-01-01 | 2022-12-31 | 2022-06-17 | 2022-09-12
21026131900 | INSTALL 3843' OF 2"/4"PMMP MN | [5 empty] | 1468486.46 | 807937.3693 | 660549.0907 | 2022-01-01 | 2022-12-31 | 2022-03-03 | 2022-10-06 | PROJECT COST OVERRUN DUE TO ADDITIONAL TIME AND RESOURCES NEEDED. CONTRACT COSTS AND LABOR COSTS INCREASED DUE TO UNEXPECTED ROCK ENCOUNTERED DURING C ONSTRUCTION FOR BORE/OPEN CUT OF NEW MAIN. ADDITIONAL TIE-IN LOCATIONS WERE REQUIRED FOR INSTALL AND ABANDONMENT. INCREASED FLAGGING AND INCREASED RES TORATION COSTS ALSO CONTRIBUTED TO THE OVERRUN, AS WELL AS INCREASED SEGA C OSTS. MOLIVER 1/24/23
21026152700 | EMER - INSTALL ODORIZER | [5 empty] | 170463.75 | 303602.2828 | -133138.5328 | 2022-01-01 | 2022-12-31 | 2022-08-16 | 2022-08-16 | UNDERRUN EXPLANATION: PROJECT DID NOT REQUIRE AS MUCH CONTINGENCY, OR OUTSIDE LABOR COSTS FROM CONTRACTORS TTOY 3/2/23
21026152800 | EMER - RETIRE ODORIZER | [5 empty] | 62508.06 | 61.5191 | 62446.5409 | 2022-01-01 | 2022-12-31 | 2022-08-16 | 2022-08-16
22026245700 | INSTALL BUILDING R-1667 | [5 empty] | 651.28 | 300.4844 | 350.7956 | 2022-01-01 | 2022-12-31 | 2023-01-16 | 2022-12-28
22026245800 | RETIRE MIS FACILITIES R-1639 | [5 empty] | 0 | 131.2422 | -131.2422 | 2022-01-01 | 2022-12-31 | 2023-01-16 | 2022-12-28
22026217800 | EMER-INSTALL 3' OF 4"PMLP MAIN | [5 empty] | 12300.82 | 6173.2589 | 6127.5611 | 2022-01-01 | 2022-12-31 | 2022-06-17 | 2022-08-18 | LEAK CLEARED USING DPI D311930 PW
22026217900 | EMER-RETIRE 3' OF 4"BSLP MAIN | [5 empty] | 4448.33 | 170.8304 | 4277.4996 | 2022-01-01 | 2022-12-31 | 2022-06-17 | 2022-08-18
22026207500 | INSTALL NEW CONTROL REGULATOR | [5 empty] | 893.82 | 1471.7874 | -577.9674 | 2022-01-01 | 2022-12-31 | 2022-08-18 | 2022-08-18 | CCC#77790 INSTALLED NEW 461-57S CONTROL REGULATOR CWEMPE 8-18-22
22026207600 | REPLACE CONTROL REG | [5 empty] | 487.94 | 65.0112 | 422.9288 | 2022-01-01 | 2022-12-31 | 2022-08-18 | 2022-08-18 | CCC#77790 REMOVED CONTROL REGULATOR CWEMPE 8-18-22
18026762800 | INSTALL NEW CHAIN LINK FENCE | [5 empty] | 16843.44 | 17042.1322 | -198.6922 | 2022-01-01 | 2022-12-31 | 2022-08-15 | 2022-08-18 | MONITORED NEW CHAINLINK FENCE INSTALL AMCCORMICK 8-18-22
18026762900 | REPLACE CHAIN LINK FENCE | [5 empty] | 429.99 | 73.5943 | 356.3957 | 2022-01-01 | 2022-12-31 | 2022-08-15 | 2022-08-18 | MONITORED FENCE REMOVAL AND INSTALL AMCCORMICK 8-18-22
21026146701 | INSTALL 100'-2" PMIP | [5 empty] | 6197.36 | 40630.8922 | -34433.5322 | 2022-01-01 | 2022-12-31 | 2021-11-09 | 2022-08-30 | VAPIERCE (03/27/23); JOB OVER RUN DUE TO CONTRACT CHARGES ASSOCIATED TO EMERGENCY JOB ORDER 22-0262152-00 EMER-KY FLOODING 2022. $29,900 IN ESTIMATED CONTRACT COSTS AND $0 BOOKED TO THIS JOB ORDER, ALL CONTRACT COSTS WERE CHARGED TO EMER-KY FLOODING 2000 JO. MOST LABOR COSTS WERE ALSO BOOKED UNDER THE EMER JOB ORDER. CONSTRUCTION WAS UNAWARE THIS PLANNED PROJECT OVERLAPPED WITH EMER WORK.
22026178500 | INSTALL 44'-6" PMMP | [5 empty] | 65200.97 | 72684.0107 | -7483.0407 | 2022-01-01 | 2022-12-31 | 2022-06-06 | 2022-08-23
22026178600 | RETIRE 26'-6" CSMP | [5 empty] | 1859.72 | 73.9724 | 1785.7476 | 2022-01-01 | 2022-12-31 | 2022-06-06 | 2022-08-23
21026155700 | INSTALL FENCE - SCADA BUILDING | [5 empty] | 7557.57 | 15936.4497 | -8378.8797 | 2022-01-01 | 2022-12-31 | 2022-08-15 | 2022-08-22
21026112400 | INSTALL NEW GMB SETTING | [5 empty] | 55082.19 | 57016.3076 | -1934.1176 | 2022-01-01 | 2022-12-31 | 2022-03-02 | 2022-08-22 | INSTALLED NEW GMB SKID MOUNTED METER AND REGULATOR SETTING AJPARKS 8-22-202 2 PSID 501306155
20026960600 | INSTALL NEW TRANSMITTERS | [5 empty] | 9652.42 | 5450.0793 | 4202.3407 | 2022-01-01 | 2022-12-31 | 2020-07-21 | 2022-08-22 | INSTALLED NEW INLET AND OUTLET ROSEMONT 4088B TRANSMITTERS GHALE 8-22-2022
22026195400 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 682.09 | 4801.1928 | -4119.1028 | 2022-01-01 | 2022-12-31 | 2022-08-22 | 2022-08-22 | CCC# 78156 PAPERWORK ONLY - NO CCC NEEDED - BLONE - 11/8/22 INSTALLED NEW MIWI350 B LONE 8-22-2022
20026960700 | RETIRE DAMAGE TRANSMITTER | [5 empty] | 542.77 | 80.9227 | 461.8473 | 2022-01-01 | 2022-12-31 | 2022-08-22 | 2022-08-22 | INSTALLED NEW INLET AND OUTLET TRANSMITTERS GHALE 8-22-2022
22026195500 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 676.72 | 124.8731 | 551.8469 | 2022-01-01 | 2022-12-31 | 2022-08-22 | 2022-08-22 | CCC# 78156 RETIRED OLD ERX INSTALLED NEW MIWI350 BLONE 8-22-22
21026119600 | PM- TURNER STATION REPLACEMENT | [5 empty] | 3311444.82 | 1012500 | 2298944.82 | 2022-01-01 | 2022-12-31 | 2022-10-01 | 2022-08-23
21026119700 | PM- TURNER STATION ABANDONMENT | [5 empty] | 378972.89 | 62500 | 316472.89 | 2022-01-01 | 2022-12-31 | 2022-10-01 | 2022-08-23
22026231800 | RETIRE PAPER CHART | [5 empty] | 0 | 1093 | -1093 | 2022-01-01 | 2022-12-31 | 2022-08-23 | 2022-08-23 | RETIRED PAPER CHART CCOX 8-23-22
20026926400 | INSTALL NETWORK UPGRADE | [5 empty] | 7131.29 | 3150 | 3981.29 | 2022-01-01 | 2022-12-31 | 2022-08-23 | 2022-09-09 | GMB NO CC NEEDED GMB NO CC NEEDED NO CC NEEDED--GMB NO CC NEEDED GMB INSTALLED SOAR,BATTERY,AND MODEM PAPERWORK DONE BY J.MULLINS
22026195600 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5406.36 | 4801.1928 | 605.1672 | 2022-01-01 | 2022-12-31 | 2022-08-22 | 2022-09-01 | CCC# 78341 - BLONE - 08/23/22 UPGRADED ERX TO MIME CO BY J.MULLINS
22026195700 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 381.79 | 124.8731 | 256.9169 | 2022-01-01 | 2022-12-31 | 2022-08-23 | 2022-09-01 | CCC# 78341 B. LONE UPDATTED ERX TO MIWI CO BY J. MULLINS
22026184000 | INSTALL 200'-6"/8" PMLP | [5 empty] | 210431.38 | 169438.8752 | 40992.5048 | 2022-01-01 | 2022-12-31 | 2022-07-11 | 2022-08-30 | OVERRUN EXPLANATION: PROJECT WAS PLANNED FOR 360 HOURS OF LABOR TIME BUT ENDED UP WITH 565 HOURS DUE TO MULTIPLE COORDINATORS AND WELDER CHARGING 125 HOURS, SEGA WAS ORIGINALLY $20,641 BUT ENDED UP AT $34,463, PROJECT REQUIRED 698 TONS OF STONE AND DUST BUT WAS ORIGINALLY PLANNED FOR 60 TONS, ADDITIONAL EXTRA DEPTH UNITS OF 134, PROJECT ALSO CHAR CHARGED ~$6,000 OF SEWER CAMERA EVEN THOUGH THE SEWER WAS ALREADY UNCOVERED WHICH IS WHY WE WERE INSTALLING THE RELOCATION. TTOY 2/3/23
22026184100 | RETIRE 100'-BSLP | [5 empty] | 400 | 65.0112 | 334.9888 | 2022-01-01 | 2022-12-31 | 2022-08-24 | 2022-08-30
22026200700 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5573.15 | 4801.1928 | 771.9572 | 2022-01-01 | 2022-12-31 | 2022-08-24 | 2022-08-24 | CCC# 68204 - BLONE - 08/24/22 CCC#68204 TIME CHARGED FOR COMPLETING PAPERWORK. CWEMPE 8/30/22 RETIRED ERX INSTALLED NEW MIWI350 CWEMPE 8-24-2022
22026200800 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 285.19 | 124.8731 | 160.3169 | 2022-01-01 | 2022-12-31 | 2022-08-24 | 2022-08-24 | CCC# 68204 - BLONE - 08/24/22 CCC#68204 RETIRED OLD ERX INSTALLED NEW MIWI350 CWEMPE 8-24-2022
21026127200 | INSTALL 2200'-2"&4" PMMP | [5 empty] | 570820.34 | 433097.159 | 137723.181 | 2022-01-01 | 2022-12-31 | 2022-02-11 | 2022-10-31 | COST OVERRUN DUE TO PAVING ESTIMATED IN CONTRACT, BUT CAPTURED IN MISC MATE RIALS WITH A DIFFERENCE OF $32,000. SOME ADDITIOANL MATERIALS WERE REQUIRE D THAT WERE NOT ESTIMATED FOR $6,000. SEGA ALSO INCREASED FOR ADDITIONAL $1 8,000. D.LEMONS 1/31/2023 ADDITIONAL $56,000 TRANSFERED FROM RETIREMENT JO THAT WAS ASSOCIATED WITH A DDITIONAL PAVING. D. LEMONS 2/23/2023
22026194800 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5891.93 | 4801.1928 | 1090.7372 | 2022-01-01 | 2022-12-31 | 2022-08-25 | 2022-08-25 | CCC# 78666 INSTALLED NEW MIWI350 JPASLEY 8-25-22
22026194900 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 0 | 124.8731 | -124.8731 | 2022-01-01 | 2022-12-31 | 2022-08-25 | 2022-08-25 | RETIRED ERX INSTALLED NEW MIWI350 JPASLEY 8-25-22
22026175400 | RETIRE R-1258 | [5 empty] | 114.11 | 7307.4769 | -7193.3669 | 2022-01-01 | 2022-12-31 | 2022-08-18 | 2022-08-26 | CCC# 77893 STATIONRETIRED PER AMRP PROJECT WSHIMFESSEL 8-26-2022 ALL FACILITIES REMOVE D
22026175500 | RETIRE R-1275 | [5 empty] | 648.29 | 7307.4769 | -6659.1869 | 2022-01-01 | 2022-12-31 | 2022-08-18 | 2022-08-26 | CCC# 77909 RETIRED REG STATION R-1275 ON AMRP PROJECT WSHIMFESSEL 8-26-2022 PREMISE IS RETIRED. GATHERED INFORMATION FOR CAPITOL CLOSEOUT.
22026196900 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5192.52 | 4801.1928 | 391.3272 | 2022-01-01 | 2022-12-31 | 2022-08-26 | 2022-08-26 | INSTALLED NEW MIWI350 JPASLEY 8-26-22
22026197000 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 698.72 | 124.8731 | 573.8469 | 2022-01-01 | 2022-12-31 | 2022-08-26 | 2022-08-26 | RETIRED OLD ERX JPASLEY 8-26-22
22026222300 | EMER - INSTALL 7'-4" PMLP | [5 empty] | 13873.55 | 4005.634 | 9867.916 | 2022-01-01 | 2022-12-31 | 2022-08-29 | 2022-09-14
22026222400 | EMER - RETIRE 7'-4" PLP | [5 empty] | 0 | 89.0305 | -89.0305 | 2022-01-01 | 2022-12-31 | 2022-08-29 | 2022-09-14
21026151200 | INSTALL 2065'-2"&6" PMMP | [5 empty] | 493527.08 | 333722.7132 | 159804.3668 | 2022-01-01 | 2022-12-31 | 2022-02-09 | 2022-10-17
22026220400 | ABANDON 550' OF 2"PMP MAIN | [5 empty] | 184.67 | 3449.8998 | -3265.2298 | 2022-01-01 | 2022-12-31 | 2022-08-29 | 2022-08-29 | ABANDONED 020 MP PL ML. PREFORMED PER ABANDONMENT PLAN SOAP TEST DEAD END C AP OP 15 MINUTES. C HERNDON/S.BARKER PURGED ABANDONED SECTION OF LINE. CAPPED THE ENDS OF ABANDONED ML.
20026926600 | INSTALL NETWORK UPGRADE | [5 empty] | 6560.17 | 3150 | 3410.17 | 2022-01-01 | 2022-12-31 | 2022-08-29 | 2022-08-29 | NO CC NEEDED GMB INSTALLED NEW SUPER SOLAR KIT MRYAN 8-29-22
22026195000 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5607.88 | 4801.1928 | 806.6872 | 2022-01-01 | 2022-12-31 | 2022-08-29 | 2022-08-29 | SWAP COMP. PARKS 08-29-22 1545 CCC# 78985 RETIRED OLD ERX INSTALLED NEW MIWI350 AJPARKS 8-29-2022
22026195100 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 248.95 | 124.8731 | 124.0769 | 2022-01-01 | 2022-12-31 | 2022-08-29 | 2022-08-29 | REMOVAL COMP. APARKS 08-29-22 1044 CCC# 78985 RETIRED OLD ERX INSTALLED NEW MIWI350 AJPARKS 8-29-2022
22026180100 | INSTALL 805' OF 2"/4"PMMP MAIN | [5 empty] | 116760.6 | 54482.6036 | 62277.9964 | 2022-01-01 | 2022-12-31 | 2022-07-21 | 2022-09-07 | TWALKER/KY 09-08-22: PROJECT OVER RUN DUE TO ROCK ENCOUNTERED IN CONSTRUCTI ON REQUIRING ROCK BORE AND OPEN CUT ROCK WHICH INCREATED CONTRACT COST BY $30,000. WMS WOULD NOT ALLOW REVISION OF PROJECT DUE TO UNPAID INVOICES. COMPANY LABOR INCREASED BY OVER $16,000 DUE TO EXTRA TIME FOR CONSTRUCTION AND SEGA WAS $6000 THAN ESTIMATE TWALKER/KY 01-24-23: LEVEL 2 VARIANCE REPORT ADDED TO WMS.DOCS.
21026138900 | INSTALL 650'-6" PMMP | [5 empty] | 111751.03 | 35779.3166 | 75971.7134 | 2022-01-01 | 2022-12-31 | 2022-07-21 | 2022-09-01 | COST INCREASE FOR LABOR HOURS AND CONTRACT COSTS DUE TO INCREASED DIRECTION AL BORE FOOTAGE, GPS DATA COLLECTION, INCREASED RESTORATION COSTS, ADDITION AL TIE-IN LOCATIONS NEEDED, AND INCREASE IN SEGA COSTS. - MOLIVER
22026202900 | RETIRE 135' OF 2"PMP MAIN | [5 empty] | 2.29 | 78.4365 | -76.1465 | 2022-01-01 | 2022-12-31 | 2022-08-31 | 2022-09-07
21026147300 | INSTALL 400'-4" PMMP-SER | [5 empty] | 32919.84 | 22333.8994 | 10585.9406 | 2022-01-01 | 2022-12-31 | 2022-08-08 | #N/A | COMMIT DATE MISSED DUE TO WEATHER
22026195800 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5580.46 | 4801.1928 | 779.2672 | 2022-01-01 | 2022-12-31 | 2022-08-30 | 2022-08-30 | CCC# 79192 INSTALL NEW MIWI 350, P2P COMP. JMARTIN 8-30-22
22026195900 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 69.23 | 124.8731 | -55.6431 | 2022-01-01 | 2022-12-31 | 2022-08-30 | 2022-08-30 | CCC# 79192 INSTALL NEW MIWI 350, P2P COMP. JMARTIN 8-30-22 RETIRED OLD ERX
22026221200 | EMER - INSTALL 8'-6"PMMP | [5 empty] | 11736.48 | 32929.6819 | -21193.2019 | 2022-01-01 | 2022-12-31 | 2022-08-31 | 2022-09-12 | TEST 6 IN MAIN AT 90 LB FOR 20 MIN SOAP TEST EFC AT OP FOR 5 MIN
22026219700 | EMER-INSTALL 8" STOPPLE FITS | [5 empty] | 39002.9 | 30183.131 | 8819.769 | 2022-01-01 | 2022-12-31 | 2022-08-29 | 2022-09-01
22026221300 | EMER - RETIRE 8'-6" PMP | [5 empty] | 595.27 | 87.3224 | 507.9476 | 2022-01-01 | 2022-12-31 | 2022-08-31 | 2022-09-12 | REMOVED 2 FT OF 6 IN DAMAGE PIPE
22026219800 | EMER-RETIRE 1' OF 8"CSHP MAIN | [5 empty] | 160 | 84.9152 | 75.0848 | 2022-01-01 | 2022-12-31 | 2022-08-31 | 2022-09-01
22026196700 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5374.37 | 4801.1928 | 573.1772 | 2022-01-01 | 2022-12-31 | 2022-08-31 | 2022-08-31 | CCC# 79339 INSTALLED NEW MIWI350. P2P W/GC OK 08/31/2022 WSHIMFE
22026196800 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 0 | 124.8731 | -124.8731 | 2022-01-01 | 2022-12-31 | 2022-08-31 | 2022-08-31 | RETIRED OLD ERX INSTALLED NEW MIWI350 WSHIMFESSEL 8-31-2022
20026977600 | RETIRE 4766'-2"/3"/4"/6" BSLP | [5 empty] | 11052.89 | 476.2758 | 10576.6142 | 2022-01-01 | 2022-12-31 | 2022-09-01 | 2022-09-06
22026199300 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5269.21 | 4801.1928 | 468.0172 | 2022-01-01 | 2022-12-31 | 2022-09-01 | 2022-09-01 | CCC# 79486 RETIRED ERX INSTALLED NEW MIWI350 GHALE 9-1-2022
22026199400 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 169.77 | 124.8731 | 44.8969 | 2022-01-01 | 2022-12-31 | 2022-09-01 | 2022-09-01 | CCC# 79486 RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 9-1-2022
22026222500 | EMER - INSTALL 5'-6" PMMP | [5 empty] | 5673.45 | 5662.1316 | 11.3184 | 2022-01-01 | 2022-12-31 | 2022-09-22 | 2022-09-23
22026222600 | EMER - RETIRE 5'-6" PMMP | [5 empty] | 0 | 74.3089 | -74.3089 | 2022-01-01 | 2022-12-31 | 2022-09-23 | 2022-09-23
22026199100 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5602.7 | 4801.1928 | 801.5072 | 2022-01-01 | 2022-12-31 | 2022-09-02 | 2022-09-02 | CCC 79615 RETIRED OLD ERX INSTALLED NEW MIWI350 EBLANTON 9-2-2022
22026199200 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 880.44 | 124.8731 | 755.5669 | 2022-01-01 | 2022-12-31 | 2022-09-02 | 2022-09-02 | CCC 79615 RETIRED OLD ERX INSTALLED NEW MIWI350 EBLANTON 9-2-2022
22026221900 | EMER - RETIRE 20'-3" PMP | [5 empty] | 6987.81 | 3460.1765 | 3527.6335 | 2022-01-01 | 2022-12-31 | 2022-09-07 | 2022-10-04
20026980401 | INSTALL 13,025'-PMMP/CSHP | [5 empty] | 2258910.28 | 1836238.4697 | 422671.8103 | 2022-01-01 | 2022-12-31 | 2022-09-06 | 2022-09-29 | OVERRUN EXPLANATION: PROJECT INCLUDED ADDITIONAL PAVING THAT WAS UNFORSEEN DUE TO CITY REQUIREMENTS, SEGA HAD AN INCREASE OF OVER $100,000 TTOY 3/2/2023
22026198900 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5462.44 | 4801.1928 | 661.2472 | 2022-01-01 | 2022-12-31 | 2022-09-06 | 2022-09-06 | CCC#79730 CWEMPE 9/6/22 UPGRADED ERX TO MIWI PAPERWORK DONE BY J.MULLINS
22026199000 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 252.74 | 124.8731 | 127.8669 | 2022-01-01 | 2022-12-31 | 2022-09-06 | 2022-09-06 | CCC#79730 CWEMPE 9/6/22
22026218500 | INSTALL 35'-2"/4 PMLP | [5 empty] | 8610.21 | 16435.9913 | -7825.7813 | 2022-01-01 | 2022-12-31 | 2022-09-07 | 2022-10-27 | INSTALLED 2' OF 4" PL AND 37' OF 2" PL LP TESTED 90 PSIG 1 HR
18026843301 | INSTALL 3000' OF 4/6/8"PMLP | [5 empty] | 1711065.31 | 1495308.5734 | 215756.7366 | 2022-01-01 | 2022-12-31 | 2022-07-19 | 2022-09-09
18026843400 | RETIRE 2670' OF 3"/6"CILP MAIN | [5 empty] | 598.25 | 81.035 | 517.215 | 2022-01-01 | 2022-12-31 | 2022-05-25 | 2022-09-12
21026998900 | RETIRE 3"PLP SERVICE LINE | [5 empty] | 9085.7 | 9329.0565 | -243.3565 | 2022-01-01 | 2022-12-31 | 2022-09-06 | 2022-09-20
22026197100 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5373.93 | 4801.1928 | 572.7372 | 2022-01-01 | 2022-12-31 | 2022-09-07 | 2022-09-07 | CCC 79940 RETIRED OLD ERX INSTALLED NEW MIWI350 9-7-2022
22026197200 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 251.1 | 124.8731 | 126.2269 | 2022-01-01 | 2022-12-31 | 2022-09-07 | 2022-09-07 | CCC 79940 RETIRED OLD ERX INSTALLED NEW MIWI350 EBLANTON 9-7-2022
22026217300 | RETIRE 3"PLP SERVICE LINE | [5 empty] | 0 | 170.8304 | -170.8304 | 2022-01-01 | 2022-12-31 | 2022-09-08 | 2022-09-08
21026137900 | INSTALL OUTLET VLV R-1643 | [5 empty] | 80161.67 | 110321.1916 | -30159.5216 | 2022-01-01 | 2022-12-31 | 2022-08-31 | 2022-09-08 | CCC# 80227 MONITOR WHILE BACKFILLING INSTALLED ALL NEW STATION VALVES JPASLEY 9-8-22 UNDERRUN EXPLANATION: PROJECT INCLUDED $27,000 OF CONTINGENCY AND HAD AN UNDERRUN OF 30,492 TTOY 3/2/23
21026138000 | RETIRE OUTLET VLV R-1643 | [5 empty] | 0 | 955.7874 | -955.7874 | 2022-01-01 | 2022-12-31 | 2022-09-08 | 2022-09-08 | RETIRED ALL STATION VALVES AND INSTALLED NEW VALVES JPASLEY 9-8-22
22026199500 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5358.86 | 4801.1928 | 557.6672 | 2022-01-01 | 2022-12-31 | 2022-09-08 | 2022-09-08 | CCC# 80149 P2P OK RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 9-8-2022
22026201100 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5540.17 | 4801.1928 | 738.9772 | 2022-01-01 | 2022-12-31 | 2022-09-08 | 2022-09-08 | CCC# 80069 P2P OK RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 9-8-2022
22026199600 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 509.01 | 124.8731 | 384.1369 | 2022-01-01 | 2022-12-31 | 2022-09-08 | 2022-09-08 | CCC# 80149 RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 09-08-2022
22026201200 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 157.47 | 124.8731 | 32.5969 | 2022-01-01 | 2022-12-31 | 2022-09-08 | #N/A | CCC# 80069 RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 9-8-2022
22026216200 | INSTALL 950' OF 2"/4"PMMP MAIN | [5 empty] | 47379.78 | 39269.0655 | 8110.7145 | 2022-01-01 | 2022-12-31 | 2022-08-24 | #N/A
22026198700 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 6293.17 | 4801.1928 | 1491.9772 | 2022-01-01 | 2022-12-31 | 2022-09-13 | 2022-09-13 | CC 497 CC 497 REPLACED OLD ERX WITH NEW MIWI350 SGIORDANO 9-13-2022
22026198800 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 1014.14 | 124.8731 | 889.2669 | 2022-01-01 | 2022-12-31 | 2022-09-13 | #N/A | CC 497 REPLACED ERX WITH NEW MIWI350 SGIORDANO 9-13-2022
20026980700 | RETIRE MAIN - LEAKAGE | [5 empty] | 2546.03 | 103.8156 | 2442.2144 | 2022-01-01 | 2022-12-31 | 2021-07-14 | #N/A
20026992600 | RETIRE MP MAIN | [5 empty] | 0 | 103.8156 | -103.8156 | 2022-01-01 | 2022-12-31 | 2022-09-26 | #N/A
22026179200 | INSTALL 50' OF 6"PMLP S/L | [5 empty] | 45896.9 | 47001.2003 | -1104.3003 | 2022-01-01 | 2022-12-31 | 2022-09-08 | #N/A
22026200900 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 6137.4 | 4801.1928 | 1336.2072 | 2022-01-01 | 2022-12-31 | 2022-09-14 | #N/A | CC 632 UPGRADED TO MIWI 350 PAPERWORK DONE BY J.MULLINS
22026201000 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 485.58 | 124.8731 | 360.7069 | 2022-01-01 | 2022-12-31 | 2022-09-14 | #N/A | CC 632 UPGRADED TO MIWI 350 PAPERWORK DONE BY J.MULLINS
22026181900 | LAB EQUIPMENT INSTALL | [5 empty] | 5312.84 | 15945.3111 | -10632.4711 | 2022-01-01 | 2022-12-31 | 2022-09-15 | #N/A
22026199900 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 6476.38 | 4801.1928 | 1675.1872 | 2022-01-01 | 2022-12-31 | 2022-09-15 | #N/A | CC 118 INSTALLED NEW MIWI350 RETIRED OLD ERX SGIORDANO 9-15-22
22026200200 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 1400.9 | 124.8731 | 1276.0269 | 2022-01-01 | 2022-12-31 | 2022-09-15 | #N/A | CC 118 INSTALLED NEW MIWI350 SGIORDANO 9-15-22 C 2820
21026993401 | INSTALL 10750'-2"/4"PMMP MAIN | [5 empty] | 2072101.63 | 1880428.7756 | 191672.8544 | 2022-01-01 | 2022-12-31 | 2022-09-26 | #N/A
20026930900 | UPGRADE ELECTRONICS | [5 empty] | 3329.3 | 3038 | 291.3 | 2022-01-01 | 2022-12-31 | 2022-09-19 | #N/A | RETIRED MINI AT INSTALLED NEW EC350 ON CELL MODEM DASH 9-19-22
22026206400 | RETIRE ELECTRONIC | [5 empty] | 2331.95 | 65.0112 | 2266.9388 | 2022-01-01 | 2022-12-31 | 2022-09-19 | #N/A | RETIRED OLD MINIAT INSTALLED NEW EC350 DASH 9-19-2022
22026177500 | EMER - INSTALL 800'-6" CSHP | [5 empty] | 1030814.44 | 663631.3961 | 367183.0439 | 2022-01-01 | 2022-12-31 | 2022-08-18 | #N/A | LEVEL 2 VARIANCE EXPLANATION IN WMSDOCS TTOY 2/3/23
20026980500 | RETIRE 12,520' - LP MAIN | [5 empty] | 809.88 | 52.2976 | 757.5824 | 2022-01-01 | 2022-12-31 | 2022-05-05 | #N/A
21026140700 | RETIRE 2,200' - CSMP | [5 empty] | 0 | 61.2976 | -61.2976 | 2022-01-01 | 2022-12-31 | 2022-09-27 | #N/A
22026177600 | EMER-RETIRE 800'-4" CSHP | [5 empty] | 1361.76 | 84.9152 | 1276.8448 | 2022-01-01 | 2022-12-31 | 2022-08-18 | #N/A
22026199700 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5650.33 | 4801.1928 | 849.1372 | 2022-01-01 | 2022-12-31 | 2022-09-20 | #N/A | RETIRED OLD ERX INSTALLED NEW MIWI350 EBLANTON 9-20-22
22026199800 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 592.76 | 124.8731 | 467.8869 | 2022-01-01 | 2022-12-31 | 2022-09-20 | 2022-09-20 | RETIRED OLD RX INSTALLED NEW MIWI350 EBLANTON 9-20-22
22026228000 | EMER-INSTALL 3' OF 2"PMMP MAIN | [5 empty] | 2032.93 | 4027.0582 | -1994.1282 | 2022-01-01 | 2022-12-31 | 2022-09-21 | #N/A | INSTALLED 3 FT OF 2 IN MAIN ON DAMAGE TEST FROM POINT A TO B 90 LB FOR 20 MIN TEST PURG TEE 90 LB FOR 5 MIN SOAP TEST 1 IN END CAP AT OP FOR 5 MIN SOAP TEST 2 EFC AT OP FOR 5 MIN BHB NO GAS FOUND
22026228100 | EMER-RETIRE 3' OF 2"PMMP MAIN | [5 empty] | 590.32 | 74.3089 | 516.0111 | 2022-01-01 | 2022-12-31 | 2022-09-21 | 2022-10-04
22026198400 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5538.33 | 4801.1928 | 737.1372 | 2022-01-01 | 2022-12-31 | 2022-09-21 | 2022-09-21 | ASSIST WITH RUNNING STAINLESS 09-21-2022 RHAYES CCOX RETIRED OLD ERX INSTALL NEW MIWI350 CCOX 9-21-22
22026198500 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 450.09 | 124.8731 | 325.2169 | 2022-01-01 | 2022-12-31 | 2022-09-21 | #N/A
21026127400 | INSTALL 1900'-2"&4" PMIP | [5 empty] | 479284.77 | 236888.6644 | 242396.1056 | 2022-01-01 | 2022-12-31 | 2022-06-21 | #N/A | OVERRUN EXPLANATION LOADED INTO WMSDOCS. D.LEMONS 2/1/2023
21026127500 | RETIRE 1071'-3"&4" WIIP | [5 empty] | 0 | 75.9523 | -75.9523 | 2022-01-01 | 2022-12-31 | 2022-06-21 | #N/A
21026120000 | PM-PARIS CYNTHIANA REPLACEMENT | [5 empty] | 1437073.2 | 1087500 | 349573.2 | 2022-01-01 | 2022-12-31 | 2022-01-03 | #N/A
21026120100 | PM-PARIS CYNTHIANA ABANDONMENT | [5 empty] | 325920.13 | 62500 | 263420.13 | 2022-01-01 | 2022-12-31 | 2022-01-03 | 2022-09-22
22026173700 | 2022 SCADA VISIBILITY PROGRAM | [5 empty] | 28387.14 | 29658.8599 | -1271.7199 | 2022-01-01 | 2022-12-31 | 2022-05-13 | #N/A | CCC# 66803 CCC# 66803 MONITOR FOR NEW COMM INSTALL CCC# 80236 INSTALLED NEW MIWI350 EBLANTON 9-22-2022
23026247100 | EMER - INSTALL 9'-4" CSMP/PMP | [5 empty] | 5323.15 | 14951.5544 | -9628.4044 | 2022-01-01 | 2022-12-31 | 2022-09-26 | 2023-01-31 | LOWERED MAIN DUE TO LEAKAGE AND 14" WATER LINE TESTED 90 PSIG 0005 MIN SOAP TESTED FINAL CONN OP 40 PSIG
23026247200 | EMER - RETIRE 9'-4" CSMP | [5 empty] | 806.29 | 149.6969 | 656.5931 | 2022-01-01 | 2022-12-31 | 2022-09-26 | #N/A | RETIRED 9' OF 4" ST TO LOWER FOR 14" WATER MAIN SOAP TESTED OP TO VERIFY AD EQUATE SHUT DOWN 40 PSIG
23026253100 | PM- GREENSITE TRABU INSTALL | [5 empty] | 30739.67 | 1236355 | -1205615.33 | 2022-01-01 | 2022-12-31 | 2022-01-03 | 2022-09-26
23026253200 | PM- GREENSITE TRABU ABANDON | [5 empty] | 172.67 | 0 | 172.67 | 2022-01-01 | 2022-12-31 | 2022-01-03 | 2022-09-26
18026772300 | CONVERT FROM GMB TO CAB ACCT | [5 empty] | 725.53 | 2583.054 | -1857.524 | 2022-01-01 | 2022-12-31 | 2022-09-26 | #N/A | CONVERTED GMB TO CAB ACCOUNT INSTALLED NEW 800 METER ON 5# FPCC DASH 9-26-2 2
22026182000 | INSTALL 2185' OF 2" PMMP | [5 empty] | 141899.3 | 110360.5276 | 31538.7724 | 2022-01-01 | 2022-12-31 | 2022-09-12 | #N/A | AWEBER 01/24/2023 - PROJECT OVERRUN DUE PRIMARILY TO LAND OWNER ISSUES & EXPANSIVE SEWER LINE CAMERA WORK PERFORMED BY BUCHANON. EASEMENT FROM FIRST LAND OWNER FELL THROUGH DUE TO HOA VOTE, INCREASING INSTALLATION BY +200' & PRIVATE EASEMENT. PROJECT ENCOUNTERED ROCK BORE ADDING ~34 HOURS TO DURATIO N. OVERRUN BUCHANON COST $17K + LAND COST $11K & INCREASED SEGA RATE $6K LE D TO VARIANCE.
21026132000 | RETIRE 3700' OF 4"/6"BSLP MAIN | [5 empty] | 3419.35 | 52.2976 | 3367.0524 | 2022-01-01 | 2022-12-31 | 2022-09-27 | #N/A
23026253700 | PM-GREENSITE HWY 27 INSTALL | [5 empty] | 20730.94 | 1236355 | -1215624.06 | 2022-01-01 | 2022-12-31 | 2022-01-03 | 2022-09-27
23026253800 | PM-GREENSITE HWY 27 ABANDON | [5 empty] | 0 | 0 | 0 | 2022-01-01 | 2022-12-31 | 2022-01-03 | #N/A
22026234100 | NEW RTU/COMM BUILDING | [5 empty] | 0 | 136.2135 | -136.2135 | 2022-01-01 | 2022-12-31 | 2022-09-27 | 2022-09-27
22026204000 | RETIRE PAPER GAUGE | [5 empty] | 157.99 | 78.4365 | 79.5535 | 2022-01-01 | 2022-12-31 | 2022-09-27 | 2022-09-27 | RETIRED PAPER CHART CHRIS COX 9-27-22
22026174600 | 2022 SCADA VISIBILITY PROGRAM | [5 empty] | 38527.05 | 29658.8599 | 8868.1901 | 2022-01-01 | 2022-12-31 | 2022-05-11 | 2022-09-27 | CC# 66475 CC#1503 INSTALLED NEW MIWI350 WITH SUPER SOLAR KIT 9-27-22 CCOX
20026918201 | INSTALL ELECTRONICS | [5 empty] | 199238.05 | 114999.9064 | 84238.1436 | 2022-01-01 | 2022-12-31 | 2021-03-25 | 2022-09-27 | CCC#17216 CCC# 19029 STATION RTU UP GRADE JPASLEY 9-27-22
21026104700 | REMOVE OBSOLETE ELECTRONICS | [5 empty] | 236.27 | 135.8546 | 100.4154 | 2022-01-01 | 2022-12-31 | 2022-09-27 | 2022-09-27 | INSTALLED NEW RTU BUILDING AND TRANSMITTERS JPASLEY 9-27-2022
22026227600 | EMER - INSTALL 60'-4" PMLP | [5 empty] | 21421.89 | 30615.0582 | -9193.1682 | 2022-01-01 | 2022-12-31 | 2022-09-27 | 2022-09-28
22026227700 | EMER - RETIRE 60'-4" BSLP | [5 empty] | 8123.84 | 74.3089 | 8049.5311 | 2022-01-01 | 2022-12-31 | 2022-09-27 | 2022-09-28
21026999000 | RETIRE 4"PLP SERVICE LINE | [5 empty] | 4696.25 | 5007.8601 | -311.6101 | 2022-01-01 | 2022-12-31 | 2022-09-28 | 2022-09-28
22026173600 | 2022 SCADA VISIBILITY PROGRAM | [5 empty] | 25271.05 | 31941 | -6669.95 | 2022-01-01 | 2022-12-31 | 2022-09-28 | 2022-09-28 | INSTALLED NEW MIWI350 EBLANTON 9-28-2022
22026234500 | INSTALL NEW RTU/COMM BUILDING | [5 empty] | 0 | 136.2135 | -136.2135 | 2022-01-01 | 2022-12-31 | 2022-09-29 | 2022-09-29 | JMULLINS COMPLETING PAPERWORK
22026173800 | 2022 SCADA VISIBILITY PROGRAM | [5 empty] | 24972.3 | 30164.6195 | -5192.3195 | 2022-01-01 | 2022-12-31 | 2022-05-10 | 2022-09-29 | WITH ACP CONTRACTOR WHILE THEY INSTALL POLE FOR COMM EQUIPMENT CC 66318 05-10-2022 RHAYES CC 1924 INSTALLED MIWI350 UNABLE TO PERFORM P2P NDAVIS WORKING ON TICKET MONITORED 30 MINUTES RHAYES 09-29-2022
18026766400 | I&C - INSTALL SCADA EQUIPMENT | [5 empty] | 143824.82 | 183526.0448 | -39701.2248 | 2022-01-01 | 2022-12-31 | 2022-09-29 | 2022-09-29 | JMULLINS COMPLETE PAPERWORK TWALKER/KY 01-24-23: JOB UNDER RUN DUE TO MATERIAL COST WAS $33,000 LESS THAN PLANNED, NO SEGA CHARGED TO JOB ORDER PROJECT WAS PLANNED FOR $23,000
22026228700 | RETIRE ELECTRONIC | [5 empty] | 0 | 74.3089 | -74.3089 | 2022-01-01 | 2022-12-31 | 2022-09-29 | 2022-09-29
19026850400 | INSTALL ODORIZATION | [5 empty] | 5241.78 | 6839.1611 | -1597.3811 | 2022-01-01 | 2022-12-31 | 2022-09-30 | #N/A
19026875300 | INSTALL ODORIZER | [5 empty] | 9263.2 | 1300.1611 | 7963.0389 | 2022-01-01 | 2022-12-31 | 2022-09-30 | 2022-09-30 | INSTALLED ODORIZER BOTTLE JMULLINS 9-30-22
19026875400 | INSTALL ODORIZER | [5 empty] | 1315.89 | 1300.1611 | 15.7289 | 2022-01-01 | 2022-12-31 | 2022-09-30 | 2022-09-30 | INSTALLED FARM TAP ODORIZER BOTTLE JMULLINS 9-30-22
22026205600 | INSTALL 1200'-2" PMMP | [5 empty] | 162971.11 | 61578.4138 | 101392.6962 | 2022-01-01 | 2022-12-31 | 2022-08-31 | 2022-10-04 | LEVEL 2 BUDGET VARIANCE EXPLANATION FORM WAS SUBMITTED FOR APPROVAL IN WMSDOCS PER VAPIERCE 5/25/23
22026204200 | RETIRED GAUGE | [5 empty] | 0 | 76.9137 | -76.9137 | 2022-01-01 | 2022-12-31 | 2022-10-04 | 2022-10-04 | RETIRED PAPER CHARTS SMCHOLAN 10-04-2022
21026139300 | RETIRE STATION R-1455 | [5 empty] | 0 | 1061.1136 | -1061.1136 | 2022-01-01 | 2022-12-31 | 2022-10-04 | 2022-10-04 | RETIRED REG STATION R1455 W 2ND ST MAYSVILLE JMARTIN 10-4-22
22026173000 | 2022 SCADA VISABILITY PROGRAM | [5 empty] | 47294.28 | 30164.6195 | 17129.6605 | 2022-01-01 | 2022-12-31 | 2022-05-12 | 2022-10-04 | CC# 66617 INSTALLED NEW MIWI350 SMCHOLAN 10-4-2022
22026205200 | INSTALL 115'-2" PMMP | [5 empty] | 21273.79 | 42423.5179 | -21149.7279 | 2022-01-01 | 2022-12-31 | 2022-10-03 | 2022-10-06 | CJ HUGHES CASEY PACK'S CREW INSTALLED 103' 2" STEEL/PLASTIC MAIN LINE EXTEN TION AND A NEW 1" PLASTIC SERVICE TO 1519 MAPLE ST 10/6/22 MBLANKE U123965
22026185001 | INSTALL 260' OF 2"PMMP MAIN | [5 empty] | 30483.21 | 27065.0582 | 3418.1518 | 2022-01-01 | 2022-12-31 | 2022-10-05 | 2022-10-07
22026203900 | RETIRE PAPER GAUGE | [5 empty] | 0 | 78.4365 | -78.4365 | 2022-01-01 | 2022-12-31 | 2022-10-05 | 2022-10-05 | RETIRED PAPER CHART CCOX10-05-2022
22026174500 | 2022 SCADA VISIBILITY PROGRAM | [5 empty] | 29029.69 | 29658.8599 | -629.1699 | 2022-01-01 | 2022-12-31 | 2022-05-11 | 2022-10-05 | CC# 66436 CC# 79698 CC# 2587 CMCOX 10/5/22 INSTALLED NEW MIWI350 CCOX 10-05-2022
22026230100 | EMER-INSTALL 2' OF 2"PMMP | [5 empty] | 2249.75 | 3890.5291 | -1640.7791 | 2022-01-01 | 2022-12-31 | 2022-10-06 | 2022-10-06
22026231000 | EMER - INSTALL 1'-2" PMMP | [5 empty] | 6865.44 | 8585.1316 | -1719.6916 | 2022-01-01 | 2022-12-31 | 2022-10-06 | 2022-12-04
22026206200 | INSTALL 33'-2" PMIP | [5 empty] | 37112.14 | 82983.2827 | -45871.1427 | 2022-01-01 | 2022-12-31 | 2022-09-23 | 2022-10-25 | COST UNDERRUN DUE TO PROJECT BEING SIMPLIFIED AFTER START OF CONSTRUCTION. $2000 IN MATERIALS RETURNED AND NOT USED, $26000 IN CONTRACT ESTIMATED BUT NOT USED. ADDITIONAL SAVINGS IN OTHER AND SEGA CATAGORIA ASSOCIATED WITH LO WER COSTS. D. LEMONS 2/23/2023
22026230200 | EMER-RETIRE 2' OF 2"PMP MAIN | [5 empty] | 0 | 74.3089 | -74.3089 | 2022-01-01 | 2022-12-31 | 2022-10-06 | 2022-10-06
22026231100 | EMER - RETIRE 1'-2" PMP | [5 empty] | 0 | 60.3089 | -60.3089 | 2022-01-01 | 2022-12-31 | 2022-10-06 | 2022-12-04
22026230800 | EMER - RETIRE 3'-2" P-IP | [5 empty] | 1400.06 | 1985.3283 | -585.2683 | 2022-01-01 | 2022-12-31 | 2022-12-07 | 2022-12-15 | CONTRACTOR HIT MISS MARKED MAIN CUT OUT DAMAGED SECTION AND EF PURGE POINT ON END OF MAIN LINE SOAP TESTED OP 7 PSIG
21026127300 | RETIRE 2100'-2"&4" BSMP | [5 empty] | 0 | 75.9523 | -75.9523 | 2022-01-01 | 2022-12-31 | 2022-10-04 | 2022-10-06
21026127600 | RETIRE 4700'-4" BSLP | [5 empty] | 0 | 67.1085 | -67.1085 | 2022-01-01 | 2022-12-31 | 2022-10-06 | 2022-10-31
22026206300 | RETIRE 22'-4" WIIP | [5 empty] | 3252.3 | 83.4538 | 3168.8462 | 2022-01-01 | 2022-12-31 | 2022-09-30 | 2022-10-06
21026119400 | PM- INST FIL/SEP TOYOTA STA | [5 empty] | 2073205.75 | 1687500 | 385705.75 | 2022-01-01 | 2022-12-31 | 2022-08-19 | 2022-10-06
21026119500 | PM-ABAN FOR FILTER INST TOYOTA | [5 empty] | 522788.31 | 62500 | 460288.31 | 2022-01-01 | 2022-12-31 | 2022-10-05 | 2022-10-06
22026217400 | RETIRE 6"PLP SERVICE LINE | [5 empty] | 827.26 | 144.8304 | 682.4296 | 2022-01-01 | 2022-12-31 | 2022-09-27 | 2022-10-06
22026218800 | INSTALL MI WIRELESS UNIT | [5 empty] | 10259.75 | 9310.2589 | 949.4911 | 2022-01-01 | 2022-12-31 | 2022-09-06 | 2022-10-06 | CC# 79803 CC# 2675 CC# 2675 CMCOX 10/6/22 INSTALLED NEW MIWI350 CCOX 10-06-2022
22026213400 | INSTALL NEW 1" REGULATORS | [5 empty] | 2234.49 | 1461.8601 | 772.6299 | 2022-01-01 | 2022-12-31 | 2022-10-07 | 2022-10-07 | REPLACED BOTH MONITOR AND CONTROL REGULATORS AND INLET AND OUTLET VALVES BL ONE 10-7-22
22026213500 | RETIRE REGULATORS | [5 empty] | 856.14 | 84.9152 | 771.2248 | 2022-01-01 | 2022-12-31 | 2022-09-29 | 2022-10-07 | REPLACED BOTH MONITOR AND CONTROL REGULATORS AND INLET AND OUTLET VALVES BL ONE 10-7-22
20026930000 | UPGRADE ELECTRONICS | [5 empty] | 4491.87 | 3038 | 1453.87 | 2022-01-01 | 2022-12-31 | 2022-07-13 | 2022-10-07 | INSTALLED NED EC350 JPASLEY 10-7-22
20026937200 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 | 2022-01-01 | 2022-12-31 | 2022-10-07 | 2022-10-07 | RETIRE OLD MIN-AT INSTALLED NED EC350 JPASLEY 10-7-22
22026235800 | EMER - INSTALL 3'-4" PMMP | [5 empty] | 7089.71 | 18999.7951 | -11910.0851 | 2022-01-01 | 2022-12-31 | 2022-10-10 | 2022-12-15 | FOUND CLAMPS ON 4" PL MAIN CUT OUT AND INSTALLED NEW MAIN TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 15 PSIG
21026126900 | RETIRE 9000' OF 4"/6"BSLP MAIN | [5 empty] | 24.95 | 62.0792 | -37.1292 | 2022-01-01 | 2022-12-31 | 2022-10-10 | 2022-10-10
22026235900 | EMER - RETIRE 3'-4" P-MP | [5 empty] | 22647.66 | 117.5985 | 22530.0615 | 2022-01-01 | 2022-12-31 | 2022-10-10 | 2022-12-15 | RETIRED 4" PL MAIN WITH CLAMPS ON IT TO INSTALL NEW
22026183700 | INSTALL 100' OF 2"PMMP MAIN | [5 empty] | 19814.52 | 12739.3747 | 7075.1453 | 2022-01-01 | 2022-12-31 | 2022-09-22 | 2022-10-11 | INSTALLED 199' OF 020 MAIN. TEST 199' OF MAIN FOR 1HR AT 90LBS. FOL APPROVED.SOAP TEST 2'' EFC AT OP OF FINAL TIE IN. SOAP TEST END CAP ON MONITORING GAUGE AT OP.TEST OK.
22026174400 | 2022 SCADA VISIBILITY PROGRAM | [5 empty] | 28643.37 | 29658.8599 | -1015.4899 | 2022-01-01 | 2022-12-31 | 2022-05-10 | 2022-10-11 | INSTALL POLES FOR COMM EQUIPMENT 05-10-2022 CC 66285 RHAYES
21026151300 | RETIRE 2111'-2"&6" CSMP | [5 empty] | 80 | 109.7476 | -29.7476 | 2022-01-01 | 2022-12-31 | 2022-10-12 | 2022-10-17
22026194600 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 4024.88 | 4801.1928 | -776.3128 | 2022-01-01 | 2022-12-31 | 2022-10-12 | 2022-10-12 | CCC# 3219 INSTALLED MIWI INSTALLED NEW MIWI350 WSHINFESSEL 10-12-22
22026194700 | RETIRED ELECTRONIC EXCHANGE | [5 empty] | 0 | 124.8731 | -124.8731 | 2022-01-01 | 2022-12-31 | 2022-10-12 | 2022-10-12 | RETIRED OLD ERX WSHINFESSEL 10-12-22
21026119200 | PM- LAKE CARNICO REPLACEMENT | [5 empty] | 3041283.83 | 3161436 | -120152.17 | 2022-01-01 | 2022-12-31 | 2022-10-13 | 2022-10-13
21026119300 | PM- LAKE CARNICO ABANDONMENT | [5 empty] | 729097.27 | 62500 | 666597.27 | 2022-01-01 | 2022-12-31 | 2022-10-13 | 2022-10-13
22026228900 | EMER - INSTALL 40'-2" PMIP | [5 empty] | 37570.14 | 32269.3764 | 5300.7636 | 2022-01-01 | 2022-12-31 | 2022-10-06 | 2022-10-13
22026229000 | EMER - RETIRE 40'-2" PIP | [5 empty] | 0 | 132.427 | -132.427 | 2022-01-01 | 2022-12-31 | 2022-10-13 | 2022-10-13
21026111600 | INSTALL FENCE | [5 empty] | 21225.79 | 2231 | 18994.79 | 2022-01-01 | 2022-12-31 | 2022-09-02 | 2022-10-13 | CCC# 79626 MONITOR FOR FENCE INSTALL. JMARTIN 9-2-22 CCC# 79759 MONITOR FOR FENCE INSTALL
20026982100 | INSTALL 800'-2" PMIP | [5 empty] | 69244.93 | 47914.5682 | 21330.3618 | 2022-01-01 | 2022-12-31 | 2022-10-10 | 2022-10-17
22026231600 | EMER - INSTALL 2'-4" PMMP | [5 empty] | 196.47 | 5460.0467 | -5263.5767 | 2022-01-01 | 2022-12-31 | 2022-11-11 | 2022-11-11 | INSTALLED 2' OF 4" PL MP TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 40 P SIG
22026231700 | EMER - RETIRE 2'-4" PMMP | [5 empty] | 24.23 | 263.239 | -239.009 | 2022-01-01 | 2022-12-31 | 2022-11-10 | 2022-11-11 | RETIRED 2' OF 4" PL MP DUE TO LEAKAGE SOAP TESTED TO VERFY SHUTDOWN
22026193600 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 1911.78 | 4801.1928 | -2889.4128 | 2022-01-01 | 2022-12-31 | 2022-10-18 | 2022-10-18 | CC # 3865 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 10-18-22
22026193700 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 217.55 | 124.8731 | 92.6769 | 2022-01-01 | 2022-12-31 | 2022-10-18 | 2022-10-18 | CC # 3865 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 10-18-22
22026220800 | *PAPER ONLY* 2022 CAST IRON | [5 empty] | 0 | 295.7645 | -295.7645 | 2022-01-01 | 2022-12-31 | 2022-10-19 | 2022-10-19
22026197300 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 6904.6 | 4801.1928 | 2103.4072 | 2022-01-01 | 2022-12-31 | 2022-10-19 | 2022-10-19 | CC# 3980 CMCOX 10/19/22 INSTALLED NEW MIWI350 CCOX 10-19-22
22026197400 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 305.47 | 124.8731 | 180.5969 | 2022-01-01 | 2022-12-31 | 2022-10-19 | 2022-10-19 | CC# 3980 CMCOX 10/19/22 RETIRED OLD ERX CCOX 10-19-22
22026198601 | INSTALL 1900' OF 2"PMMP MAIN | [5 empty] | 71556.52 | 50146.9852 | 21409.5348 | 2022-01-01 | 2022-12-31 | 2022-09-29 | 2022-10-21
22026213900 | INSTALL 200'-2"PMMP | [5 empty] | 35208.99 | 22574.1191 | 12634.8709 | 2022-01-01 | 2022-12-31 | 2022-10-19 | 2022-10-24 | BORED IN 308' OF 020 PL ML. TESTED 90# FOR 1 HR. SOAP TESTED CONN PTS @ 39#
22026214100 | ABANDON 200'-2" PMMP | [5 empty] | 921.07 | 800.8601 | 120.2099 | 2022-01-01 | 2022-12-31 | 2022-10-21 | 2022-10-21
22026195200 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 6702.65 | 4801.1928 | 1901.4572 | 2022-01-01 | 2022-12-31 | 2022-10-13 | 2022-10-21 | CCC# 4229 CCC# 4229 INSTALLED NEW MIWI350 JPASLEY
22026195300 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 34.29 | 124.8731 | -90.5831 | 2022-01-01 | 2022-12-31 | 2022-10-21 | 2022-10-21 | CCC# 4229 RETIRED OLD ERX INSTALLED NEW MIWI350 JPASLEY
22026167600 | INSTALL 6' OF 3"PMLP MAIN | [5 empty] | 8748.35 | 16229.6788 | -7481.3288 | 2022-01-01 | 2022-12-31 | 2022-09-30 | 2022-10-27 | CUT OUT 4' SECTION OF 3" MAIN. TESTED DROP IN PIECE 90#5MINS, TG. ST LTI, TG. BHBNGF. 2 17LB ANODES INSTALLED. PRSSURE NEVER DROPPED ON GAUGES. PURGED ALL AIR OUT BEFORE GAS UP. R.CRAWFORD 10-27-22
22026167700 | RETIRE 6' OF 3"CSLP MAIN | [5 empty] | 9674.55 | 100.2728 | 9574.2772 | 2022-01-01 | 2022-12-31 | 2022-10-24 | 2022-10-27 | CUT OUT 4' SECTION OF LEAKING 3" MAIN, TESTED DROP IN PIECE 90#20MINS, TG. ST LTI. TG. BHBNGF. INST. 2 17LB ANODES. PRESSURE NEVER DROPPED ON GAUGES. PURGED ALL AIR OUT BEFORE GAS UP. R.CRAWFORD 10-27-22
21026998201 | INSTALL 1930'-2"/4" PMMP | [5 empty] | 114169.59 | 114050.6727 | 118.9173 | 2022-01-01 | 2022-12-31 | 2022-09-26 | 2022-11-01 | GAS ON MAIN 11/01/2022
22026230000 | ABANDON 470'-2"&3"PLP | [5 empty] | 5899.02 | 6027.5291 | -128.5091 | 2022-01-01 | 2022-12-31 | 2022-11-01 | 2022-11-01 | ABANDONED 334' OF 030 PL LP ML PER ENGINEERING AND TIE IN PLAN. SOAP TEST END CAP @ OP 15 MINS NO LEAKS BHB NGF. PURGED OUT ABANDONED SECTION OF ML G OOD M. COLLINS 11/1/2022
22026202500 | INSTALL 1120'-2"/4" PMMP | [5 empty] | 50092.05 | 49758.6341 | 333.4159 | 2022-01-01 | 2022-12-31 | 2022-10-19 | 2022-11-02
23026246200 | INSTALL VRG - MIS FACILITY | [5 empty] | 0 | 449.3532 | -449.3532 | 2022-01-01 | 2022-12-31 | 2022-11-02 | 2022-12-16
23026246300 | INSTALL VRG - RETIRE MIS FAC | [5 empty] | 0 | 132.4844 | -132.4844 | 2022-01-01 | 2022-12-31 | 2022-11-02 | 2022-12-16
20026922500 | INSTALL ELECTRONICS | [5 empty] | 238947.63 | 123804 | 115143.63 | 2022-01-01 | 2022-12-31 | 2022-11-02 | 2022-11-02 | CCC # 40652 NOT ON SITE CC# 47218. 12/01/21 DSASH CCC # 47218 CCC # 47356 CC# 47727. 12/07/21 DSASH
20026922600 | RETIRE ELECTRONICS | [5 empty] | 144.18 | 115.4611 | 28.7189 | 2022-01-01 | 2022-12-31 | 2022-11-02 | 2022-11-02
18026757800 | RETIRE RECORDING GAUGE | [5 empty] | 0 | 73.0037 | -73.0037 | 2022-01-01 | 2022-12-31 | 2022-11-07 | 2022-11-07 | RETIRED CHART INSTALLED HONEYWELL ERX JMULLINS 11-7-22
18026757700 | INSTALL MI WIRELESS EFC | [5 empty] | 14191.42 | 13926.0597 | 265.3603 | 2022-01-01 | 2022-12-31 | 2022-11-07 | 2022-11-07 | INSTALLED HONEYWELL ERX SUPER SOLAR KIT J MULLINS 11-7-22
22026216700 | EMER - INSTALL 456'-4" CS/PMIP | [5 empty] | 85192.39 | 50625 | 34567.39 | 2022-01-01 | 2022-12-31 | 2022-11-01 | 2022-11-09
22026216801 | EMER-RETIRE 130'-4" CS/BS/PIP | [5 empty] | 439.01 | 132.427 | 306.583 | 2022-01-01 | 2022-12-31 | 2022-11-02 | 2022-11-09
21026132400 | INSTALL 225' OF 2"PMMP | [5 empty] | 85412.94 | 79492.8479 | 5920.0921 | 2022-01-01 | 2022-12-31 | 2022-10-25 | 2022-11-17 | TTALKER/KY 01-25-23: JOB IS SHOWING COST UNDER RUN AT THIS TIME BUT PAVING/ STREET REPAIRS NOT TAKE PLACE UNTIL SPRING/WARM WEATHER. TWALKER/KY 06-23-23: JOB ORDER CURRENTLY UNDER RUNNING $32000 BUT STREET PAVING HAS NOT BEEN COMPLETED AT THIS TIME DUE TO DOWNTOWN AREA AND CONSTRU CTION BY OTHERS IN AREA. TWALKER/KY 07-21-23: PAVING HAS BEEN COMPLETED AND COST APPLIED TO JOB ORDE R, NOT OVER OR UNDER BUDGET VARIANCE REQUIRED AT THIS TIME. PAVING WAS DELAYED TO COLD AND WET WEATHER PLUS THIS PROJECT IS LOCATED IN DOWNTOWN AREA SO PERMIT RESTRICTION APPLIED.
21026993500 | RETIRE 13650' OF 4"/6"BSLP | [5 empty] | 80 | 86.5975 | -6.5975 | 2022-01-01 | 2022-12-31 | 2022-11-15 | 2022-11-17
22026212100 | INSTALL CHAIN LINK FENCE | [5 empty] | 9226.54 | 24086.2589 | -14859.7189 | 2022-01-01 | 2022-12-31 | 2022-11-08 | 2022-11-11 | INSTALLED CHAIN LINK FENCE JMULLINS 11-11-22
22026221000 | INSTALL 160'-4"PMMP | [5 empty] | 36375.08 | 20578.0582 | 15797.0218 | 2022-01-01 | 2022-12-31 | 2022-11-02 | 2022-11-14 | AWEBER 12/6/22 - JOB ENCOUNTERED HEAVY ROCK BORE, RESULTING IN DOUBLE TIME FROM ORIGINAL ESTIMATE. ATTEMPT TO REVISE, UNABLE DUE TO UNPAID INVOICES.
21026994000 | INSTALL 10930 - 2"/4"PMMP MAIN | [5 empty] | 1681569.14 | 1953601.844 | -272032.704 | 2022-01-01 | 2022-12-31 | 2022-04-26 | 2022-11-16 | TWALKER/KY 05-22-23: PROJECT CURRENTLY UNDER RUNNING, WAITING ON FINAL RESTORATION/PAVING TO DETERMINE IF ADDITIONAL EXPLAINATION OR VARIANCE REQU IRED. TWALKER/KY 06-23-23: JOB UNDER RUNNING DUE TO PAVING/HARD SURFACES REPAIRS HAVE NOT BEEN FULLY COMPLETED. TWALKER/KY 07-24-23: PAVING/HARD SURFACE REPAIRS STILL IN PROGRESS TWALKER/KY 08-29-23: LEVEL 1 VARIANCE FORM ADDED IN WMS.DOCS NOT SURE IF ALL PAVING INVOICES HAVE BEEN PAID BUT COST UNDER RUN DRIVEN BY LESS PAVING COST BY PAVING CONTRACTOR INSTEAD OF PIPELINE CO.
21026994100 | RETIRE 14,600 - 4"CI/BSLP MAIN | [5 empty] | 269.51 | 84.1794 | 185.3306 | 2022-01-01 | 2022-12-31 | 2022-11-16 | 2022-11-23
22026240900 | PAPER ONLY EXECUTE | [5 empty] | 0 | 119.2135 | -119.2135 | 2022-01-01 | 2022-12-31 | 2022-11-30 | 2022-11-30
21026129900 | RETIRE PIT REG STATION W/AMRP | [5 empty] | 3639 | 4706.4362 | -1067.4362 | 2022-01-01 | 2022-12-31 | 2022-11-16 | 2022-11-16 | RETIRED 800 PRESS AVE 200340, CMCHOLAN 11-16-22
22026209800 | RETIRE VAULT STRUCTURE | [5 empty] | 0 | 1027.5809 | -1027.5809 | 2022-01-01 | 2022-12-31 | 2022-11-16 | 2022-11-16 | PIT RETIRED AND FILLED IN
22026185301 | INSTALL 875' OF 2"PMMP MAIN | [5 empty] | 69561.33 | 74170.089 | -4608.759 | 2022-01-01 | 2022-12-31 | 2022-11-16 | 2022-11-18
22026240400 | PAPER ONLY - RETIRE BSIP MAIN | [5 empty] | 0 | 119.2135 | -119.2135 | 2022-01-01 | 2022-12-31 | 2022-12-19 | 2022-12-19
22026245500 | INSTALL REG STATION BUILDING | [5 empty] | 12285 | 128388.6752 | -116103.6752 | 2022-01-01 | 2022-12-31 | 2022-11-18 | 2022-12-16
23026246000 | INSTALL M&R CRANE - MARATHON | [5 empty] | 14182.67 | 36312.6752 | -22130.0052 | 2022-01-01 | 2022-12-31 | 2022-11-18 | 2022-12-16
20026969900 | INSTALL FENCE & BOLLARDS | [5 empty] | 9603.34 | 36430.1489 | -26826.8089 | 2022-01-01 | 2022-12-31 | 2022-09-13 | 2022-11-19 | INSTALLED NEW FENCE 11-19-22 JMULLINS
20026970000 | RETIRE BUILDING | [5 empty] | 26427.16 | 88.8156 | 26338.3444 | 2022-01-01 | 2022-12-31 | 2022-09-13 | 2022-11-19 | CCC# 37831 CCC# 33819 CCC# 38966 TO BE COMP BY CFARRIS BUILDING REMOVED JMULLINS
22026234300 | RETIRE GMB SETTING | [5 empty] | 0 | 725.239 | -725.239 | 2022-01-01 | 2022-12-31 | 2022-11-21 | 2022-11-21 | RETIRED GMB SETTING REMOVED METER BLIND PLATED SERVICE GAS NO LONGER NEEDED
22026234700 | INSTALL 3" STOPPLE FITTING | [5 empty] | 7929.81 | 13630.9028 | -5701.0928 | 2022-01-01 | 2022-12-31 | 2022-11-29 | 2022-11-30
22026234800 | RETIRE 75' OF 3"BSMP MAIN | [5 empty] | 114.9 | 119.2135 | -4.3135 | 2022-01-01 | 2022-12-31 | 2022-11-29 | 2022-11-29
22026233800 | INSTALL 380' OF 4"PMLP SL | [5 empty] | 35845.97 | 36339.1396 | -493.1696 | 2022-01-01 | 2022-12-31 | 2022-11-15 | #N/A
22026240700 | INSTALL FENCE FOR NEW LAND | [5 empty] | 63926.63 | 26194.1417 | 37732.4883 | 2022-01-01 | 2022-12-31 | 2022-11-30 | 2022-11-30 | CCC# 12436 TICKET# 12436 CCC# 16515 GATHER INFO FOR CAPITAL PAPERWORK
22026232100 | RETIRE PAPER GAUGE | [5 empty] | 719.12 | 993 | -273.88 | 2022-01-01 | 2022-12-31 | 2022-12-02 | 2022-12-14 | REMOVED CHART, CCC 2244, CMCHOLAN 12-1-22
22026240200 | EMER - INSTALL 100'-4" PMLP | [5 empty] | 5141.88 | 38890.2222 | -33748.3422 | 2022-01-01 | 2022-12-31 | 2022-12-02 | 2022-12-30 | INSTALLED 93' OF PL AND ST TESTED 90 PSIG 1 HR SOAP TESTED WELD CAPS AND SSTEE CAPS 10" WC
22026240300 | EMER - RETIRE 100'-4" BSLP | [5 empty] | 285.28 | 129.6266 | 155.6534 | 2022-01-01 | 2022-12-31 | 2022-12-02 | 2022-12-30 | RETIRED 75' OF 4" BS DUE TO LEAKAGE
22026241300 | EMER - INSTALL 5'-4" PMMP | [5 empty] | 1144.39 | 10162.4624 | -9018.0724 | 2022-01-01 | 2022-12-31 | 2022-12-14 | 2022-12-15 | INSTALLED 3' OF 4" PL DUE TO LEAKAGE ON SERVICE TEE TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 11 PSIG
22026241400 | EMER - RETIRE 5'-4" PMP | [5 empty] | 91.78 | 117.5985 | -25.8185 | 2022-01-01 | 2022-12-31 | 2022-12-14 | 2022-12-15 | RETIRE 4" MP TO DUE TO LEAKAGE ON SERVIEC TEE TO INSTALL NEW
22026234200 | INSTALL 100'-6"PMMP S/L | [5 empty] | 60246.05 | 78909.8457 | -18663.7957 | 2022-01-01 | 2022-12-31 | 2022-11-29 | 2022-12-06 | CJH JOE HADLEY REPLACED SL, TESTED SL AT 0106PSIG/0200HRS, OPEN CUT, SOAP TESTED FC/CAP AT OP, EXT CORR INSP, NO ANODE, WRAPPED EXPOSED MAIN, DS 12062022
22026222700 | INSTALL 86'-2" PMMP | [5 empty] | 13511.21 | 12304.5709 | 1206.6391 | 2022-01-01 | 2022-12-31 | 2022-12-05 | 2022-12-07 | THERE WAS A TYPO ON THE PRESSURE SYSTEM WHEN IT WAS CREATED. CORRECT SYSTEM NUMBER 32010047. SYSTEM NUMBER HAS BEEN CORRECTED IN DIS.
22026245100 | EMER-INSTALL 3' OF 2"PHHP MAIN | [5 empty] | 2752.76 | 4877.0569 | -2124.2969 | 2022-01-01 | 2022-12-31 | 2022-12-07 | 2022-12-07
22026240500 | INSTALL VRG | [5 empty] | 7577.2 | 14784.1417 | -7206.9417 | 2022-01-01 | 2022-12-31 | 2022-12-08 | 2022-12-08 | NOT ON SITE. GETTING MATERIAL FROM SHOP FOR JOB. CCC# 6417 CCC# 6417 CCC# 6417 CCC# 6417
22026240600 | RETIRE VRG | [5 empty] | 1416.09 | 1478.5709 | -62.4809 | 2022-01-01 | 2022-12-31 | 2022-12-08 | 2022-12-08
21026993900 | RETIRE 9500' OF 4"CI/6"BSLP MN | [5 empty] | 5876.52 | 80.3582 | 5796.1618 | 2022-01-01 | 2022-12-31 | 2022-01-25 | 2022-12-09 | ABANDONED ALL MAINS IN SCOPE OF PROJECT
22026245000 | PAPER ONLY EXECUTE | [5 empty] | 0 | 131.2422 | -131.2422 | 2022-01-01 | 2022-12-31 | 2022-12-09 | 2022-12-09
22026242500 | EMER-RETIRE 385' OF 2"/3"PAIP | [5 empty] | 5628.45 | 5363.3319 | 265.1181 | 2022-01-01 | 2022-12-31 | 2022-12-12 | 2022-12-13
22026219600 | INSTALL 90'-2" PMIP | [5 empty] | 50608.23 | 21041.6638 | 29566.5662 | 2022-01-01 | 2022-12-31 | 2022-12-12 | 2022-12-19
22026235200 | INSTALL 200'-2" PMIP | [5 empty] | 11987.46 | 38455.6638 | -26468.2038 | 2022-01-01 | 2022-12-31 | 2022-12-15 | 2022-12-19
20026941000 | RETIRE GAUGE | [5 empty] | 1582.1 | 91.4991 | 1490.6009 | 2022-01-01 | 2022-12-31 | 2022-02-18 | 2022-12-15 | CCC TICKET# 55594 CCC# 55594 ERX ONLINE P2P W/GAS CONTROL OK REMOVED CHART BOX AND FILED LAST CHART ON CABINET TICKET# 11209 GATHERED INFORMATION FOR CLOSEOUT PAPERWORK 12-15-22 JBRADFORD
22026175300 | RETIRE R-1278 | [5 empty] | 1891.36 | 7307.4769 | -5416.1169 | 2022-01-01 | 2022-12-31 | 2022-12-15 | 2022-12-15 | PREMISE IS RETIRED. GATHERED INFORMATION FOR CLOSEOUT PAPERWORK. JBRADFORD 12-15-22 CCC# 20387 TICKET# 20387
21026120600 | RETIRE REG STATION WITH AMRP | [5 empty] | 1058.49 | 9924.8698 | -8866.3798 | 2022-01-01 | 2022-12-31 | 2022-11-09 | 2022-12-15 | CC# 6407 RETIRED REG STATION DASH 12-15-2022
22026210700 | RETIRE METAL BUILDING | [5 empty] | 0 | 1009.5809 | -1009.5809 | 2022-01-01 | 2022-12-31 | 2022-12-15 | 2022-12-15 | REG STATION AND BUILDING RETIRED DASH 12-15-22
22026232200 | INSTALL SKID MOUNTED GMB | [5 empty] | 40259.26 | 56170.7039 | -15911.4439 | 2022-01-01 | 2022-12-31 | 2022-11-29 | 2022-12-15 | INSTALLED NEW SKID MOUNTED METER SETTING DASH 12-15-22
22026232300 | RETIRE GMB SETTING | [5 empty] | 1984.01 | 263.239 | 1720.771 | 2022-01-01 | 2022-12-31 | 2022-11-01 | 2022-12-15 | INSTALLED NEW SKID MOUNT METER SETTING AND RETIRED OLD METER AND REGULATORS DASH 12-15-22
18026848701 | STATION UPGRADES (SEP RELATED) | [5 empty] | 206545.63 | 151848.4602 | 54697.1698 | 2022-01-01 | 2022-12-31 | 2021-05-07 | 2022-12-15 | CCC 22581 CCC 23126 CCC 23442 CCC 24345 CCC 25855 CCC 26071
20026940900 | INSTALL I&C EQUIPMENT | [5 empty] | 12849.77 | 18740.1071 | -5890.3371 | 2022-01-01 | 2022-12-31 | 2022-12-15 | 2022-12-15 | CCC TICKET# 55594 CCC TICKET# 55594 PAPER WORK GATHER INFO 12-15-22 JBRADFORD
22026227200 | RETIRE ELECTRONICS | [5 empty] | 0 | 74.3089 | -74.3089 | 2022-01-01 | 2022-12-31 | 2022-12-15 | 2022-12-15
22026232600 | INSTALL 200'-2" PMMP | [5 empty] | 20049.03 | 40586.0582 | -20537.0282 | 2022-01-01 | 2022-12-31 | 2022-12-13 | 2022-12-16
22026163000 | INSTALL ODORIZER | [5 empty] | 418702.35 | 596431.4654 | -177729.1154 | 2022-01-01 | 2022-12-31 | 2023-12-13 | #N/A
22026245300 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 3807.72 | 10393.9744 | -6586.2544 | 2022-01-01 | 2022-12-31 | 2023-01-16 | 2023-01-19
22026245400 | EMER - RETIRE 5'-2" PMMP | [5 empty] | 0 | 131.2422 | -131.2422 | 2022-01-01 | 2022-12-31 | 2023-01-16 | 2023-01-19
22026232700 | RETIRE GMB W/22-9790457-00 | [5 empty] | 0 | 545.7645 | -545.7645 | 2022-01-01 | 2022-12-31 | 2022-12-20 | 2022-12-21
23026271600 | PAPER ONLY TO SET UP WMS FAC | [5 empty] | -1146.13 | 139.7346 | -1285.8646 | 2022-01-01 | 2022-12-31 | N/A | #N/A | THIS JOB IS TO CREATE FUNCTIONS AND FACILITIES FOR THE TEMPORARY SKID REGUL ATOR SETTING RWILLIAMS PUT TEMP STATION BACK TOGETHER, CMCHOLAN 6-26-2023
Formulas:
Date Actual End = VLOOKUP([Project No.],'WMS JO Data'!$D20:BD27974,25,FALSE)

## 2023 (hidden)
Columbia Gas of Kentucky Case No. 2026-00099 Attachment A Construction Projects For 5 years ended December 31, 2025
Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End | Job Order Comments
23026246100 | RETIRE PAPER GAUGE | [5 empty] | 389.08 | 131.2422 | 257.8378 | 2023-01-01 | 2023-12-31 | 2023-01-02 | 2023-01-02 | RETIRE PRESSURE CHART GUAGE CCOX 1-2-23
23026248200 | EMER - INSTALL 2'-2" PMMP | [5 empty] | 135.67 | 13154.2985 | -13018.6285 | 2023-01-01 | 2023-12-31 | 2023-01-09 | 2023-01-11 | INSTALLED 2 ' OF 2'' PMP PIPE ( TESTED PIPE FOR 20MNS-GOOD PER FOL R. VANDERPOOL) J.OCHOA
23026248300 | EMER - RETIRE ~2'-2"PMP | [5 empty] | 1647.72 | 129.6266 | 1518.0934 | 2023-01-01 | 2023-12-31 | 2023-01-09 | 2023-01-11 | RETIRED 2' OF 2'' P MP MAIN DUE TO DAMAGE. J.OCHOA 01-11-2023
23026248600 | RETIRE 3'-3" PMLP | [5 empty] | 3012.93 | 1635.0284 | 1377.9016 | 2023-01-01 | 2023-12-31 | 2023-01-10 | 2023-01-25 | RETIRED 20' OF 3" PL MAIN DUE TO FACILITY DAMAGE SOAP TESTED OP 9.5" WC
22026211800 | RETIRE GMB SETTING | [5 empty] | 1541.41 | 1288.7874 | 252.6226 | 2023-01-01 | 2023-12-31 | 2023-01-10 | 2023-01-10 | GMB NO CC NEEDED
22026210301 | INSTALL 850' OF 4"PMMP MAIN | [5 empty] | 172217.52 | 192098.991 | -19881.471 | 2022-01-01 | 2022-12-31 | 2022-12-09 | 2023-01-23
22026238200 | INSTALL 205' OF 2"PMMP MAIN | [5 empty] | 13604.24 | 19394.2346 | -5789.9946 | 2023-01-01 | 2023-12-31 | 2023-01-12 | 2023-01-16 | TWALKER/KY 01-20-23: ISSUED BACK ORDER REQUEST #52196 FOR THIS JOB
23026249300 | EMER-INSTALL 5' OF 2"PMMP | [5 empty] | 5012.41 | 8253.2559 | -3240.8459 | 2023-01-01 | 2023-12-31 | 2023-01-13 | 2023-01-18 | REPLACED 3' OF DAMAGED 2" PLASTIC MAIN LINE WITH 2 EF COUPLINGS. PRESSURE TESTED THE THE NEW MAIN LINE AT 90PSIG FOR 1 HOUR. PRESSURE TEST OKAY. BHB, NGF. SOAP TESTED FINAL TIE IN AT OP. TEST OK. DMALONE
23026252000 | EMER-INSTALL 3' OF 6"PMMP MAIN | [5 empty] | 13052.34 | 12970.9861 | 81.3539 | 2023-01-01 | 2023-12-31 | 2023-01-17 | 2023-02-03
23026249400 | EMER-RETIRE 5' OF 2"PMMP MAIN | [5 empty] | 219.4 | 131.2422 | 88.1578 | 2023-01-01 | 2023-12-31 | 2023-01-13 | 2023-01-17 | REPLACED 3' OF DAMAGES 2" PLASTIC MAIN LINE WITH 2 EF COUPLINGS. PRESSURE TESTED THE NEW MAIN LINE AT 90PSIG FOR 1 HOUR. PRSSURE TEST OK. BHB, NGF. SOAP TESTED FINAL TIE IN AT OP. TEST OK. DMALONE
23026252100 | RETIRE 3' OF 6"PMP MAIN | [5 empty] | 0 | 138.8485 | -138.8485 | 2023-01-01 | 2023-12-31 | 2023-01-17 | 2023-02-03
23026249200 | GMB TO CAB CONVERSION | [5 empty] | 858.55 | 132.4844 | 726.0656 | 2023-01-01 | 2023-12-31 | 2023-01-17 | 2023-01-17 | CONVERTED FROM GMB TO CAB SGIORDANO
23026248400 | EMER-INSTALL 3' OF 2"PMMP MAIN | [5 empty] | 2322.97 | 5318.1948 | -2995.2248 | 2023-01-01 | 2023-12-31 | 2023-01-08 | 2023-01-18
23026248500 | EMER-RETIRE 3' OF 2"PMMP MAIN | [5 empty] | 0 | 131.2422 | -131.2422 | 2023-01-01 | 2023-12-31 | 2023-01-08 | 2023-01-18
21026139400 | REMOVE BUILDING FOR R-1455 | [5 empty] | 3989.86 | 117.5985 | 3872.2615 | 2023-01-01 | 2023-12-31 | 2023-01-18 | 2023-01-18 | BUILDING REMOVED AND CLEANED UP BY PLANT. JMULLINS 1-18-23
23026252200 | EMER-INSTALL 3' OF 4"PMMP MAIN | [5 empty] | 5339.51 | 7839.2961 | -2499.7861 | 2023-01-01 | 2023-12-31 | 2023-01-18 | 2023-02-02
23026252300 | EMER-RETIRE 3' OF 4"PAMP MAIN | [5 empty] | 0 | 138.8485 | -138.8485 | 2023-01-01 | 2023-12-31 | 2023-01-18 | 2023-02-02
22026167200 | INSTALL 720'- 4" PMMP | [5 empty] | 293269.78 | 309266.4996 | -15996.7196 | 2023-01-01 | 2023-12-31 | 2023-01-10 | 2023-02-13 | ADETOMIWA FALADE 8/29/2023. JOB IS CURRENTLY SHOWING LEVEL 1 UNDER RUN BUT $35,000 IN PAVING WAS PROCESSED THIS WEEK. ONCE THIS PAYMENT IS APPLIED TO THIS JOB ORDER, NO VARIANCE PAPERWORK SHOULD BE REQUIRED. THE PAVING WAS PERFORMED BY PRIVATE CONTRACTOR INSTEAD OF PIPELINE CONTRACTOR WHICH SAVED THE COST OF PAVING.
23026251100 | INSTALL EC-350 UNIT | [5 empty] | 1808.88 | 3195.3221 | -1386.4421 | 2023-01-01 | 2023-12-31 | 2023-01-24 | 2023-01-24 | INSTALLED NEW EC350 DASH 1-24-23
23026251200 | RETIRE PAPER BILLING CHART | [5 empty] | 975.93 | 131.2422 | 844.6878 | 2023-01-01 | 2023-12-31 | 2023-01-24 | 2023-01-24 | RETIRED CHART INSTALLED NEW EC350 DASH 1-24-23
23026252600 | INSTALL 3' OF 4"PMLP MAIN | [5 empty] | 16571.37 | 9484.2961 | 7087.0739 | 2023-01-01 | 2023-12-31 |  | 2023-01-25 | ABD 69 FT BS CUT OUT INLINE TEE AND INSTALLED 5 FT OF 4 IN PL TEST 90 LB FOR 1 HR OK SOAP TEST CPLG AND TEES AT OP FOR 5 MIN BAR HOLE BANKS NO GAS FOUND
23026252700 | RETIRE 69' OF 4"BSLP MAIN | [5 empty] | 0 | 138.8485 | -138.8485 | 2023-01-01 | 2023-12-31 | 2023-01-24 | 2023-01-25 | ABDN 69 FT OF 6 IN BARE STEEL BLEW DOWN AND SEALED ENDS
23026249800 | INSTALL EC 350 UNIT | [5 empty] | 5379.35 | 7475.3221 | -2095.9721 | 2023-01-01 | 2023-12-31 | 2023-01-25 | 2023-01-25 | CHECK TO SEE IF CARD WAS READY CMCHOLAN 1-27-2023 INSTALLED NEW EC350 CMCHOLAN 1-25-23
23026249900 | RETIRE PAPER BILLING CHART | [5 empty] | 463.02 | 131.2422 | 331.7778 | 2023-01-01 | 2023-12-31 | 2023-01-25 | 2023-01-25 | REMOVED PAPER BILLING CHART, CMCHOLAN EBLANTON 1-25-23
22026229200 | INSTALL 80'-2" PMMP | [5 empty] | 10781.29 | 11104.5291 | -323.2391 | 2023-01-01 | 2023-12-31 | 2023-01-27 | 2023-01-27 | INSTALLED 160' 2'' MP-PL MAINLINE
23026249600 | PM- DE ILI PH 2 JIM BEAM INST | [5 empty] | 965942.08 | 593000 | 372942.08 | 2023-01-01 | 2023-12-31 | 2023-01-27 | 2023-01-27
23026249700 | PM- DE ILI PH 2 JIM BEAM ABAN | [5 empty] | 234155.55 | 132000 | 102155.55 | 2023-01-01 | 2023-12-31 | 2023-01-27 | 2023-01-27
23026253900 | RETIRE PRESSURE GAUGE | [5 empty] | 0 | 552.5683 | -552.5683 | 2023-01-01 | 2023-12-31 | 2023-01-27 | 2023-01-27
23026254000 | RETIRE PRESSURE GAUGE | [5 empty] | 768.43 | 552.5683 | 215.8617 | 2023-01-01 | 2023-12-31 | 2023-01-31 | 2023-01-31 | CC15136 CHART HAS BEEN REMOVED ISO UPDATED 1-31-23 CC15136 CHART HAS BEEN REMOVED ISO UPDATED 1-31-23
22026204100 | RETIRE BUILDING | [5 empty] | 0 | 76.9137 | -76.9137 | 2023-01-01 | 2023-12-31 | 2023-01-31 | 2023-01-31 | BUILDING DEMOLISHED BY CONTRACTORS
22026204400 | RETIRE BUILDING | [5 empty] | 0 | 76.9137 | -76.9137 | 2023-01-01 | 2023-12-31 | 2023-01-31 | 2023-01-31 | BUILDING DEMOLISHED BY CONTRACTOR
23026254700 | RETIRE PAPER GAUGE | [5 empty] | 247.65 | 552.5683 | -304.9183 | 2023-01-01 | 2023-12-31 | 2023-02-10 | 2023-02-10 | REMOVED PAPER CHART, CCC 10587
23026248900 | INSTALL 100' OF 2"PMMP MAIN | [5 empty] | 28889.25 | 30720.7606 | -1831.5106 | 2023-01-01 | 2023-12-31 | 2023-02-02 | 2023-02-03
23026249000 | RETIRE 86' OF 2"CSMP MAIN | [5 empty] | 0 | 131.2422 | -131.2422 | 2023-01-01 | 2023-12-31 | 2023-02-02 | 2023-02-09 | ABN 102' OF 2'' COATED STEELE MAIN PURGED AND END SEALED
23026254100 | RETIRE PRESSURE GAUGE | [5 empty] | 72.46 | 552.5683 | -480.1083 | 2023-01-01 | 2023-12-31 | 2023-02-03 | 2023-02-03 | CCC# 10600 RETIRED PRESSURE CHART. JMARTIN 2-3-23
20026952500 | REPLACE VALVE C-16 | [5 empty] | 47582.37 | 56236.611 | -8654.241 | 2023-01-01 | 2023-12-31 | 2023-02-02 | 2023-02-07
20026952600 | RETIRE VALVE C-16 | [5 empty] | 5789.59 | 952.0929 | 4837.4971 | 2023-01-01 | 2023-12-31 | 2023-02-02 | 2023-02-07
23026252400 | RETIRE GMB MS#804399 RUN | [5 empty] | 21780.96 | 2962.0987 | 18818.8613 | 2023-01-01 | 2023-12-31 | 2023-02-06 | 2023-02-06 | NOT ONSITE NOT ONSITE GATHERING PARTS CCC# 15748 TICKET# 15748 RETIRED GMB SETTING 2-6-23 BY J.BRADFORD
23026250900 | INSTALL EC 350 | [5 empty] | 755.31 | 2339.3221 | -1584.0121 | 2023-01-01 | 2023-12-31 | 2023-02-07 | 2023-02-07 | INSTALLED NEW EC 350 INSTALLED EC 350 J.BRADFORD 2-7-23
23026251000 | RETIRE PAPER BILLING CHART | [5 empty] | 803.89 | 131.2422 | 672.6478 | 2023-01-01 | 2023-12-31 | 2023-02-07 | 2023-02-07 | BILLING CHART REMOVED AND EC 350 INSTALLED
23026254300 | TAP W/MAIN 23-0262543-00 | [5 empty] | 4459.75 | 13015.0987 | -8555.3487 | 2023-01-01 | 2023-12-31 | 2023-02-08 | 2023-02-08
22026223900 | INSTALL 1067'-4" PMMP | [5 empty] | 149979.89 | 181608.1135 | -31628.2235 | 2023-01-01 | 2023-12-31 | 2023-01-24 | 2023-02-10
22026224000 | RETIRE 1150'-4" PMMP | [5 empty] | 0 | 72.8379 | -72.8379 | 2023-01-01 | 2023-12-31 | 2023-01-24 | 2023-02-10
22026216300 | INSTALL VRG CONTROLLER | [5 empty] | 28545.09 | 10806.1191 | 17738.9709 | 2023-01-01 | 2023-12-31 | 2023-02-09 | 2023-02-09 | CC 15047 CC 15628 CC 15628 CC 15628 CC 15628 CC 16352 NOT ON SITE CAPITAL PAPERWORK/ISO SKETCH
22026216400 | RETIRE CONTROLLERS | [5 empty] | 572.67 | 84.9152 | 487.7548 | 2023-01-01 | 2023-12-31 | 2023-02-09 | 2023-02-09 | RETIRED CONTROLLERS, INSTALLED NEW VRG'S
22026158800 | INSTALL 540' OF 4"/8"PMMP MAIN | [5 empty] | 378932.24 | 262444.8259 | 116487.4141 | 2023-01-01 | 2023-12-31 | 2023-01-17 | 2023-03-03 | TWALKER/KY 09-27-23: LEVEL 1 VARIANCE FORM ADDED TO WMS.DOCS JOB OVER RUN DUE TO ADDITIONAL PAVING/RESTORATION REQUIREMENT BY THE CITY INCREASED CONTRACT COST BY $30,000, ALSO SEGA $12,000 HIGHER THAN ESTIMATE. COMPANY LABOR INCREASED BY $25,000 DUE TO ADDITIONAL COMPANY LABOR REQUIRED. TWALKER/KY 10-27-23: LEVEL 2 VARIANCE REPORTED ADDED TO WMS.DOCS, JOB OVER DUE TO CITY PAVING AND RE-PAVING REQUIREMENT.
22026158900 | RETIRE 594' OF 8"BSMP MAIN | [5 empty] | 0 | 72.8047 | -72.8047 | 2023-01-01 | 2023-12-31 | 2023-01-17 | 2023-03-03
22026167300 | RETIRE 720'-4" BS-LP | [5 empty] | 0 | 62.2578 | -62.2578 | 2023-01-01 | 2023-12-31 | 2023-01-10 | 2023-02-13
23026248700 | INSTALL 2" SS | [5 empty] | 2373.93 | 18496.357 | -16122.427 | 2023-01-01 | 2023-12-31 | 2023-02-13 | 2023-03-22
23026248800 | RETIRE 50' - 2" CSMP | [5 empty] | 6678.36 | 138.8485 | 6539.5115 | 2023-01-01 | 2023-12-31 | 2023-02-13 | 2023-03-22
23026258600 | EMER - INSTALL 5'-4" PMIP | [5 empty] | 29274.5 | 23135.0467 | 6139.4533 | 2023-01-01 | 2023-12-31 | 2023-02-14 | 2023-06-14 | INSTALLED 3' OF 4" PL DUE TO BORE CREW BORING INTO MAIN TESTED 90 PSIG 1 HR
23026258700 | EMER- RETIRE 5'-4" PMIP | [5 empty] | 1956.38 | 137.555 | 1818.825 | 2023-01-01 | 2023-12-31 | 2023-02-14 | 2023-06-13 | RETIRED 3' OF 4" IP DUE TO BORE CREW HITTING MAIN SOAP TESTED OP 7 PSIG TO VERIFY SQUEEZE OFF
23026259000 | EMER-INST 85'-4"PMMP MND311494 | [5 empty] | 23726.73 | 25540.4028 | -1813.6728 | 2023-01-01 | 2023-12-31 | 2023-02-19 | 2023-02-20 | 4" MAIN/PINK PL LEAKING UNDER STAMPED CONCRETE ENTRANCE TO COUNTRY CLUB RETIRED 85' AND INSTALLED 85' OF NEW MAIN-BORING DONE BY STANLEY PIPELINE, MAIN TEST 1 HR @90IB OK, TIE IN COMPLETE 02/20/2023 HMCKUNE
23026259100 | EMER-RETIRE 85' OF 4"PAMP MAIN | [5 empty] | 260.66 | 138.8485 | 121.8115 | 2023-01-01 | 2023-12-31 | 2023-02-19 | 2023-02-20 | 4" MAIN/PINK PL LEAKING UNDER STAMPED CONCRETE ENTRANCE TO COUNTRY CLUB RETIRED 85' AND INSTALLED 85' OF NEW MAIN-BORING DONE BY STANELY PIPELINE, MAIN TEST 1HR @90 IB OK, TIE IN COMPLETE, 02/20/2023 HMCKUNE
23026262200 | EMER - INSTALL 4'-2" PMMP | [5 empty] | 15777.13 | 2419.7892 | 13357.3408 | 2023-01-01 | 2023-12-31 | 2023-02-20 | 2023-03-03 | INSTALLED 4' OF 2" PLASTIC MAIN. PRESSURE TESTED AT 90LBS FOR 1 HR.
23026262300 | EMER - RETIRE 4'-2" PMMP | [5 empty] | 242.84 | 260.4446 | -17.6046 | 2023-01-01 | 2023-12-31 | 2023-02-20 | 2023-03-03 | REMOVED 4' OF DAMAGED 2" PLASTIC
23026256700 | RETIRE PAPER GAUGE | [5 empty] | 756.49 | 138.8485 | 617.6415 | 2023-01-01 | 2023-12-31 | 2023-02-21 | 2023-02-21 | CC 17512 REMOVED PAPER PRESSURE GAUGE
23026266300 | EMER-INSTALL 3' OF 2"PMMP MAIN | [5 empty] | 4867.28 | 7671.8121 | -2804.5321 | 2023-01-01 | 2023-12-31 | 2023-02-22 | 2023-02-22
23026266400 | EMER-RETIRE 3' OF 2"PMP MAIN | [5 empty] | 0 | 124.7348 | -124.7348 | 2023-01-01 | 2023-12-31 | 2023-02-22 | 2023-02-22
23026260300 | RETIRE PAPER CHART | [5 empty] | 564.75 | 138.8485 | 425.9015 | 2023-01-01 | 2023-12-31 | 2023-02-22 | 2023-02-22 | CC 17668
23026260200 | INSTALL ERX W/SUPER SOLAR | [5 empty] | 4114.48 | 6314.9621 | -2200.4821 | 2023-01-01 | 2023-12-31 | 2023-02-22 | 2023-02-22 | CC 17668 NOT ON SITE CAPITAL PACKET PAPERWORK NOT ONSITE. ISO UPDATES CC 21100 ANNUAL GAUGE INSP AND P2P WITH GAS CONTROL COMPLETE.
23026262700 | EMER-INSTALL 5' OF 2"PMMP MAIN | [5 empty] | 3582.24 | 7460.3676 | -3878.1276 | 2023-01-01 | 2023-12-31 | 2023-02-22 | 2023-03-07 | WORKED WITH JO. 23026262700 INSTALLED 5FT OF 020 MAIN DUE TO LEAKING S/L TEE. TESTED 5FT OF 020, 010 TEE,010 COUPLING AND 020 PURGE END CAP FOR 1HR AT 90LBS.TEST OK. SOAP TEST 020 EFC AT OP. FOR 5MINS TEST OK. BHB NGF
23026262800 | EMER-RETIRE 5' OF 2"PMP MAIN | [5 empty] | 726.04 | 124.7348 | 601.3052 | 2023-01-01 | 2023-12-31 | 2023-02-22 | 2023-03-07 | FROM MAIN TO MTR FOR 5MINS AT 90LBS.TEST OK. SOAP TEST FINAL TIE IN AT OP.TEST OK. BHB NGF WORKED WITH JO. 23026262700 INSTALLED 5FT OF 020 MAIN DUE TO LEAKING S/L TEE. TESTED 5FT OF 020, 010 TEE,010 COUPLING AND 020 PURGE END CAP FOR 1HR AT 90LBS.TEST OK. SOAP TEST 020 EFC AT OP. FOR 5MINS TEST OK. BHB NGF -- 010 S/L ELECTROFUSION TEE LEAKING AT SADDLE CONNECTION TO MAIN.REPLACED 5FT OF MAIN WITH NEW S/L TEE AND 020 PURGE END CAP.TESTED FOR 1HR AT 90LBS. TEST OK. SOAP TEST EFC COULPING AT OP. FOR 5MINS.TEST OK.TEST S/L FOR 3905
23026260500 | RETIRE PAPER CHART | [5 empty] | 605.66 | 138.8485 | 466.8115 | 2023-01-01 | 2023-12-31 | 2023-02-23 | 2023-02-23 | CC 17834
23026260400 | INSTALL ERX W/SUPER SOLAR | [5 empty] | 3437.82 | 6314.9621 | -2877.1421 | 2023-01-01 | 2023-12-31 | 2023-02-23 | 2023-02-23 | CC 17834 NOT ON SITE. CAPITAL PACKET PAPERWORK NOT ON SITE ISO UPDATES CC 21100 ANNUAL GAUGE INSP AND P2P WITH GAS CONTROL COMPLETE
22026230301 | INSTALL 1,725'-2" PMMP | [5 empty] | 676511.46 | 636475.4754 | 40035.9846 | 2023-01-01 | 2023-12-31 | 2023-01-03 | 2023-03-17
23026268100 | RETIRE MAIN - LEAKAGE | [5 empty] | 0 | 117.7346 | -117.7346 | 2023-01-01 | 2023-12-31 | 2023-02-27 | 2023-04-12
23026249100 | INSTALL 100'-2" PMMP | [5 empty] | 13611.51 | 7008.1595 | 6603.3505 | 2023-01-01 | 2023-12-31 | 2023-02-28 | 2023-03-03 | INSTALLED NEW MAIN ON RICHLAND CT TESTED 90 PSIG 1 HR SOAP TESTED BRANCHING TEE CAP AND PURGE POINT CAP OP 14 PSIG
23026264300 | EMER-INSTALL 5' OF 4"PMMP MAIN | [5 empty] | 267.86 | 7456.0229 | -7188.1629 | 2023-01-01 | 2023-12-31 | 2023-02-28 | 2023-03-10 | INSTALLED 3' OF 4" PL MAIN W/ EFC AND BF DE CAP- TEST 90# FOR 20MINS PER FOL DBANKS- SOAP TEST FINALTIEIN @ OP TEST OK- BHB NGF CONTENT VERIFIED DMARSTO 3/10/23
23026264400 | EMER-RETIRE 520'- 4"PAIP MAIN | [5 empty] | 325.83 | 124.7348 | 201.0952 | 2023-01-01 | 2023-12-31 | 2023-02-28 | 2023-03-10 | ABN 520' SECTION OF 4" PL MAIN- PURGE ABN SECTION OF MAIN W/ AIR UNTIL 0% SUSTAINED- DMARSTO 3/10/23
22026184800 | INSTALL 3775'-2" PMMP | [5 empty] | 689655.43 | 567138.2381 | 122517.1919 | 2023-01-01 | 2023-12-31 | 2023-01-20 | 2023-04-12
23026260100 | RETIRE PAPER GAUGE | [5 empty] | 257.79 | 138.8485 | 118.9415 | 2023-01-01 | 2023-12-31 | 2023-02-28 | 2023-02-28 | CC# 18341. 2/28/23 DSASH
20026952900 | REPLACE ROOF | [5 empty] | 12246.18 | 4729 | 7517.18 | 2023-01-01 | 2023-12-31 | 2023-02-28 | 2023-02-28
23026260000 | INSTALL ERX W/SUPER SOLAR | [5 empty] | 3193.7 | 5058.9621 | -1865.2621 | 2023-01-01 | 2023-12-31 | 2023-02-28 | 2023-02-28 | CC# 18341. 2/28/23 DSASH CC# 21913. P2P OK.
23026254200 | RETIRE RECORDING GAUGE | [5 empty] | 107.1 | 552.5683 | -445.4683 | 2023-01-01 | 2023-12-31 | 2023-03-01 | 2023-03-01 | CC 10596 RETIRE PAPER CHART SHANE G. 03012023
23026256800 | RETIRE PAPER GAUGE | [5 empty] | 43.28 | 138.8485 | -95.5685 | 2023-01-01 | 2023-12-31 | 2023-03-01 | 2023-03-01 | CCC# 10600 RETIRE PRESSURE CHART, JMARTIN 3-1-23
23026250700 | INSTALL EC 350 | [5 empty] | 5810.87 | 5649.3221 | 161.5479 | 2023-01-01 | 2023-12-31 | 2023-03-01 | 2023-03-01 | RETIRED CHART INSTALLED NEW EC350
23026250800 | RETIRE PAPER BILLING CHART | [5 empty] | 528.15 | 131.2422 | 396.9078 | 2023-01-01 | 2023-12-31 | 2023-03-01 | 2023-03-01 | RETIRED PAPER CHART CCOX
23026264500 | EMER - INSTALL ~5'-4" PM/CSMP | [5 empty] | 929.35 | 2069.4953 | -1140.1453 | 2023-01-01 | 2023-12-31 | 2023-03-02 | 2023-08-25
23026264600 | EMER - RETIRE ~5'-4" CSMP | [5 empty] | 207.34 | 67.4953 | 139.8447 | 2023-01-01 | 2023-12-31 | 2023-03-02 | 2023-08-25
23026256600 | RETIRE PAPER GAUGE | [5 empty] | 468 | 138.8485 | 329.1515 | 2023-01-01 | 2023-12-31 | 2023-03-02 | 2023-03-02 | CHART BOXES REMOVED. G.HALE A.PARKS 03-02-23 CHARTS REMOVED AND STORED AT LEX MOD APARKS 03-02-23
23026259900 | RETIRE PAPER CHART | [5 empty] | 277.39 | 138.8485 | 138.5415 | 2023-01-01 | 2023-12-31 | 2023-03-02 | 2023-03-02 | CC# 18720. 3/2/23 DSASH CC# 18720
23026259800 | INSTALL ERX W/SUPER SOLAR | [5 empty] | 3465.31 | 5058.9621 | -1593.6521 | 2023-01-01 | 2023-12-31 | 2023-03-02 | 2023-03-02 | CC# 18720. 3/2/23 DSASH
23026266800 | EMER - INSTALL 7'-2" PMMP | [5 empty] | 537.54 | 15964.0017 | -15426.4617 | 2023-01-01 | 2023-12-31 | 2023-03-02 | 2023-04-05
23026266900 | EMER - RETIRE 7'-2" PMAP | [5 empty] | 0 | 64.7348 | -64.7348 | 2023-01-01 | 2023-12-31 | 2023-03-02 | 2023-04-05
23026260800 | RETIRE PAPER CHART | [5 empty] | 78.59 | 138.8485 | -60.2585 | 2023-01-01 | 2023-12-31 | 2023-03-06 | 2023-03-06 | RETIRED PAPER CHART AND IS NOW CONNECTED ER350, CMCHOLAN CCC 19108
23026260700 | INSTALL ERX W/SUPER SOLAR | [5 empty] | 3972.47 | 5629.9621 | -1657.4921 | 2023-01-01 | 2023-12-31 | 2023-03-06 | 2023-03-06 | INSTALLED SUPER SOLAR AND MEDIUM PRESSURE RUN TO ER350, WILL BE FULL TIME MONITOR WHEN BUILT IN SCADA AND WILL DO P2P THEM CCC 19108, CMCHOLAN 3-6-23 FINISHED UP PAPERWORK AND SUMMITED ISO, CCC 19108 CMCHOLAN 3-6-23 0859 CCC-27261 DID P2P WITH GAS CONTROL ON MP, GAGE INSP OK, CCC 27123 CMCHOLAN EBLANTON 4-26-23 1600
23026267000 | EMER - INSTALL 2'-2" PMLP | [5 empty] | 1235.74 | 7754.9733 | -6519.2333 | 2023-01-01 | 2023-12-31 | 2023-03-07 | 2023-04-05
23026265600 | EMER - INSTALL 4'-6" PMIP | [5 empty] | 19713.32 | 12463.1003 | 7250.2197 | 2023-01-01 | 2023-12-31 | 2023-03-06 | 2023-08-26
23026267100 | EMER - RETIRE 2'-2" PLP | [5 empty] | 0 | 64.7348 | -64.7348 | 2023-01-01 | 2023-12-31 | 2023-03-07 | 2023-04-05
23026265700 | EMER - RETIRE 4'-6" P-IP | [5 empty] | 0 | 391.4196 | -391.4196 | 2023-01-01 | 2023-12-31 | 2023-03-06 | 2023-08-25
23026259700 | RETIRE PAPER CHART | [5 empty] | 269.78 | 138.8485 | 130.9315 | 2023-01-01 | 2023-12-31 | 2023-03-07 | 2023-03-07
23026259600 | INSTALL ERX AND SUPER SOLAR | [5 empty] | 3652.44 | 5600.9621 | -1948.5221 | 2023-01-01 | 2023-12-31 | 2023-03-07 | 2023-03-07
22026163200 | INSTALL 775' OF 2"PMMP MAIN | [5 empty] | 49762.97 | 80533.8181 | -30770.8481 | 2023-01-01 | 2023-12-31 | 2023-03-06 | 2023-03-17 | TWALKER/KY- 09-27-23: LEVEL 1 VARIANCE ADDED TO WMS.DOCS JOB UNDER RUN WAS DUE TO NO FLAGGING OR STREET REPAIRS REQUIRED SINCE ALL MAIN WAS INSTALLED BY DIRECTIONAL BORE WHICH LOWER CONTRACT COST $23,000
23026251300 | INSTALL EC 350 UNIT | [5 empty] | 8141.46 | 7475.3221 | 666.1379 | 2023-01-01 | 2023-12-31 | 2023-03-13 | 2023-03-13 | INSTALLED NEW EC350 TO REPLACE PAPER BILLING CHART
23026251400 | RETIRE PAPER BILLING CHART | [5 empty] | 870.82 | 131.2422 | 739.5778 | 2023-01-01 | 2023-12-31 | 2023-03-13 | 2023-03-13 | RETIRE PAPER BILLING CHART
22026230400 | RETIRE 5,578' - IP MAIN | [5 empty] | 1019.8 | 475.239 | 544.561 | 2023-01-01 | 2023-12-31 | 2023-01-03 | 2023-03-17
22026230500 | RETIRE 1,368' - MP MAIN | [5 empty] | 14.31 | 475.239 | -460.929 | 2023-01-01 | 2023-12-31 | 2023-01-03 | 2023-03-17
22026241900 | INSTALL 249'-2" PMIP | [5 empty] | 101153.64 | 81974.2921 | 19179.3479 | 2023-01-01 | 2023-12-31 | 2023-02-28 | 2023-03-15
22026242000 | RETIRE 135'-3" BSIP | [5 empty] | 139.7 | 117.5985 | 22.1015 | 2023-01-01 | 2023-12-31 | 2023-02-28 | 2023-03-15
23026250200 | INSTALL EC-350 | [5 empty] | 8105.28 | 6049.3221 | 2055.9579 | 2023-01-01 | 2023-12-31 | 2023-03-14 | 2023-03-14 | INSTALLED IN HONEYWELL EC3560 IN PLACE OF CHART EBLANTON 3-14-23
23026250300 | RETIRE PAPER BILLING CHART | [5 empty] | 185.13 | 131.2422 | 53.8878 | 2023-01-01 | 2023-12-31 | 2023-03-14 | 2023-03-14 | RETIRE PAPER BILLING CHART EBLANTON 3-14-23
23026250500 | INSTALL EC 350 | [5 empty] | 6654.67 | 7589.3221 | -934.6521 | 2023-01-01 | 2023-12-31 | 2023-03-15 | 2023-03-15 | INSTALLED NEW HONEYWELL EC350 IN PLACE OF CHART EBLANTON 3-15-2023
23026250600 | RETIRE PAPER BILLING CHART | [5 empty] | 144.2 | 131.2422 | 12.9578 | 2023-01-01 | 2023-12-31 | 2023-03-15 | 2023-03-15 | RETIRED PAPER BILLING CHART EBLANTON 3-15-23
23026251700 | INSTALL 2060' OF 2" PMMP | [5 empty] | 65881.72 | 60788.4178 | 5093.3022 | 2023-01-01 | 2023-12-31 | 2023-02-28 | 2023-03-06
21026127000 | INSTALL 8021'-2"&4" PMIP | [5 empty] | 2281682.81 | 1234240.1163 | 1047442.6937 | 2023-01-01 | 2023-12-31 | 2023-01-09 | 2023-06-07 | Variance caused due to substancial increase in paving/restoration & SEGA
22026163300 | RETIRE 800' OF 4"BSLP MAIN | [5 empty] | 21.45 | 105.0102 | -83.5602 | 2023-01-01 | 2023-12-31 | 2023-03-06 | 2023-03-17
23026267700 | EMER-RETIRE 40' OF 6"BSLP MAIN | [5 empty] | 8203.54 | 9430.1038 | -1226.5638 | 2023-01-01 | 2023-12-31 | 2023-03-16 | 2023-03-16
22026209201 | RETIRE BUILDING FOR R-1451 | [5 empty] | 3422.43 | 4594.5704 | -1172.1404 | 2023-01-01 | 2023-12-31 | 2023-03-16 | 2023-03-16
23026250000 | INSTALL EC 350 UNIT | [5 empty] | 6158.92 | 5649.3221 | 509.5979 | 2023-01-01 | 2023-12-31 | 2023-03-16 | 2023-03-16 | INSTALLED NEW HONEYWELL EC350 INPLACE OF CHART
23026250100 | RETIRE PAPER BILLING CHART | [5 empty] | 525.01 | 131.2422 | 393.7678 | 2023-01-01 | 2023-12-31 | 2023-03-16 | 2023-03-16 | RETIRED PAPER CHART EBLANTON 3-16-23
23026269000 | EMER-INSTALL 4' OF 2"PMMP MAIN | [5 empty] | 6353.99 | 5499.7073 | 854.2827 | 2023-01-01 | 2023-12-31 | 2023-03-17 | 2023-03-29
23026269100 | EMER-RETIRE 4' OF 2"PAMP MAIN | [5 empty] | 0 | 117.7346 | -117.7346 | 2023-01-01 | 2023-12-31 | 2023-03-17 | 2023-03-29
23026261000 | RETIRE PAPER CHART | [5 empty] | 174.56 | 138.8485 | 35.7115 | 2023-01-01 | 2023-12-31 | 2023-03-17 | 2023-03-17 | CC 20961
23026260900 | INSTALL ERX W/SUPER SOLAR | [5 empty] | 1872.11 | 5458.9621 | -3586.8521 | 2023-01-01 | 2023-12-31 | 2023-03-17 | 2023-03-17 | CC 20969 CC 24221 P2P OK WITH GC.
22026241500 | INSTALL 40'-2" PMMP | [5 empty] | 14054.24 | 23266.5784 | -9212.3384 | 2023-01-01 | 2023-12-31 | 2023-03-22 | 2023-03-23
22026241600 | RETIRE 30'-2" PMMP | [5 empty] | 193.2 | 124.7348 | 68.4652 | 2023-01-01 | 2023-12-31 | 2023-03-22 | 2023-03-21
23026269500 | EMER - INSTALL 4'-2" PIP | [5 empty] | 2717.09 | 7943.8116 | -5226.7216 | 2023-01-01 | 2023-12-31 | 2023-03-28 | 2023-08-26
23026269600 | EMER - RETIRE 5'-2" PIP | [5 empty] | 0 | 134.4334 | -134.4334 | 2023-01-01 | 2023-12-31 | 2023-03-28 | 2023-08-25
22026243500 | RETIRE RECORDING GAUGE | [5 empty] | 241.8 | 96.4823 | 145.3177 | 2023-01-01 | 2023-12-31 | 2023-03-29 | 2023-03-29 | CCC#22649
22026243400 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 15857.32 | 19008.8866 | -3151.5666 | 2023-01-01 | 2023-12-31 | 2023-03-29 | 2023-03-29 | CCC#22649
23026270300 | EMER - INSTALL 2'-4" PMMP | [5 empty] | 526.5 | 9141.6411 | -8615.1411 | 2023-01-01 | 2023-12-31 | 2023-04-01 | 2023-05-25
23026270400 | EMER - RETIRE 110'-4" P-MP | [5 empty] | 537.22 | 137.555 | 399.665 | 2023-01-01 | 2023-12-31 | 2023-04-01 | 2023-05-25 | RETIRED 110' OF 4" PL MP DUE TO BUILDING COLLAPSING TESTED CAP 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 38 PSIG
23026271200 | INSTALL LEGACY ERX | [5 empty] | 2465.58 | 2907.8819 | -442.3019 | 2023-01-01 | 2023-12-31 | 2023-04-03 | 2023-04-03 | INSTALLED LEGACY ERX IN PLACE OF OLD RTU AND TRANSMITTER EBLANTON 4-3-23
22026168000 | HVAC AND RTU PANEL UPGRADE | [5 empty] | 22883.04 | 39849.6755 | -16966.6355 | 2023-01-01 | 2023-12-31 | 2023-04-03 | 2023-04-03 | PAPER JOB COMPLETION.
23026257000 | ST JOE - RETIRE RTU | [5 empty] | 310.19 | 138.8485 | 171.3415 | 2023-01-01 | 2023-12-31 | 2023-04-03 | 2023-04-03 | RETIRED OLD RTU EBLANTON 4-3-23
22026214500 | JIM BEAN RTU PANEL | [5 empty] | 2091.18 | 55.5311 | 2035.6489 | 2023-01-01 | 2023-12-31 | 2023-04-03 | 2023-04-03 | CCC# 15710 CCC# 15710
23026249500 | INSTALL 870'-2" PMMP | [5 empty] | 52378.28 | 67614.2583 | -15235.9783 | 2023-01-01 | 2023-12-31 | 2023-03-21 | 2023-04-04
22026240100 | GMB TO CAB CONVERSION | [5 empty] | 2136.59 | 238.427 | 1898.163 | 2023-01-01 | 2023-12-31 | 2023-04-04 | 2023-04-04 | CONVERTED GMB TO CAB ACCOUNT, CMCHOLAN 4-4-23
23026260600 | GMB TO CAB CONVERSION | [5 empty] | 1404.11 | 138.8485 | 1265.2615 | 2023-01-01 | 2023-12-31 | 2023-04-04 | 2023-04-04 | GATHER PARTS FOR CONVERSION, MTR, FLANGES, GASKETS ETC. REGULATOR GMB TO CAB CONVERSION GAS ON BYPASS DURING REBUIL;D NO BYPASS GAS USED INST ALLED NEW ROMET 3M ON 2#
22026244400 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 17382.14 | 26337.6752 | -8955.5352 | 2023-01-01 | 2023-12-31 | 2023-04-04 | 2023-04-04 | CCC# 22134 WELDED NEW TAP ON INLET FOR MIWI INSTALL, JMARTIN DMARTIN 3-27-23 CCC# 23352 INSTALL NEW MIWI 350, UNIT IS WAITING FOR A TICKET # TO BE ABLE TO PUT ONLINE. JMARTIN 4-4-23 CCC# 23905 STILL NEED TO DO P2P WITH GAS CONTROL, MODEM NOT COMMUNICATING JMARTIN 4-6-23 CCC# 24126 TRIED TO FIX COMM ISSUE WITH MODEM CCC# 23905 P2P W/GAS CONTROL OK, JMARTIN 4-10-23 CCC# 26515 COMP ANOTHER P2P WITH GAS CONTROL. JMARTIN 4-21-23 NOT ONSITE, FIXED ISO AND SUBMITTED NEW CAP FOR DRAWING.
23026264700 | INSTALL 100' OF 3"PMLP MAIN | [5 empty] | 21922.36 | 29526.7351 | -7604.3751 | 2023-01-01 | 2023-12-31 | 2023-04-04 | 2023-04-19 | 100' OF BS MAIN RETIRED AND REPLACED W/3" PE PL MAIN DUE TO CORROSION
23026264800 | RETIRE 100' OF 3"BSLP MAIN | [5 empty] | 6487.75 | 124.7348 | 6363.0152 | 2023-01-01 | 2023-12-31 | 2023-04-04 | 2023-04-19 | 100' OF BS MAIN RETIRED AND REPLACED W/3" PE PL MAIN DUE TO CORROSION
23026265400 | EMER - INSTALL 12' - 2" PMMP | [5 empty] | 9462.49 | 5370.5784 | 4091.9116 | 2023-01-01 | 2023-12-31 | 2023-04-03 | 2023-04-06 | TEST 2 IN MAIN FROM POINT A TO B TEST 90 LB FOR 20 MIN SOAP TEST TIEINS AT OP BAR HOLE BANKS NO GAS FOUND
23026265500 | EMER - RETIRE 12' - 2" PMMP | [5 empty] | 165.55 | 124.7348 | 40.8152 | 2023-01-01 | 2023-12-31 | 2023-04-03 | 2023-04-06
23026263400 | INSTALL 40'-4" PMMP | [5 empty] | 24778.88 | 25145.0229 | -366.1429 | 2023-01-01 | 2023-12-31 | 2023-04-10 | 2023-04-11
23026271400 | EMER - INSTALL ~5'-2" PMMP | [5 empty] | 7739.82 | 5664.5366 | 2075.2834 | 2023-01-01 | 2023-12-31 | 2023-04-10 | 2023-05-09 | INSTALLED 1' OF 2" PL MP DUE TO DAMAGE TESTED 90 PSIG 1 HR SOAP TESTED FINA L CONN OP 40 PSIG
23026263500 | RETIRE 20'-4" PMMP | [5 empty] | 98.08 | 124.7348 | -26.6548 | 2023-01-01 | 2023-12-31 | 2023-04-10 | 2023-04-11
23026271500 | EMER - RETIRE ~5'-2" PMMP | [5 empty] | 709.93 | 114.3981 | 595.5319 | 2023-01-01 | 2023-12-31 | 2023-04-10 | 2023-05-09 | RETIRED 1" OF 2" PL MP DUE TO FACILITY DAMAGE SOAP TESTED TO VERIFY SQUEEZE OFF OP 40 PSIG
23026271000 | INSTALL 70'-2" PMMP | [5 empty] | 606.43 | 9795.9371 | -9189.5071 | 2023-01-01 | 2023-12-31 | 2023-04-09 | 2023-04-10
23026271100 | ABANDON 60'-2" PMMP | [5 empty] | 4210.59 | 262.8722 | 3947.7178 | 2023-01-01 | 2023-12-31 | 2023-04-09 | 2023-04-10
22026244500 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 17938.12 | 19488.6752 | -1550.5552 | 2023-01-01 | 2023-12-31 | 2023-04-10 | 2023-04-10 | CCC# 22091 INSTALLED NEW INLET TAP FOR MIWI, JMARTIN DMARTIN 3-27-23 NOT ONSITE DELAY DUE TO RAIN NOT ONSITE ACP RESCHEDULED CCC# 24233 INSTALLED NEW MIWI 350 CCC# 26551 WORKED WITH GC TO GET SITE ONLINE. P2P COMP. JMARTIN 4-21-23 NOT ONSITE, UPDATED ISO AND SBMITTED REDLINED DRAWIN.
22026184900 | RETIRE 3315'-2"&4"BSLP | [5 empty] | 23.53 | 72.7393 | -49.2093 | 2023-01-01 | 2023-12-31 | 2023-01-20 | 2023-04-12
22026243200 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 20634.93 | 25283.8866 | -4648.9566 | 2023-01-01 | 2023-12-31 | 2023-03-30 | 2023-04-11 | CCC# 21042 CC 22745 WELD AND TEST STEEL TIE TAPS INLET 240# OUTLET 90# 5MINS RHAYES DMARTIN 03-30-2023 NOT ONSITE COLLECTING PARTS FOR JOB CCC#27524
22026223700 | INSTALL 1296'-2"&4" PMMP | [5 empty] | 286331.62 | 306884.1479 | -20552.5279 | 2023-01-01 | 2023-12-31 | 2023-02-14 | 2023-04-24
22026223800 | RETIRE 1212'-2",3"&4" CSMP | [5 empty] | 0 | 117.5985 | -117.5985 | 2023-01-01 | 2023-12-31 | 2023-02-14 | 2023-04-24
22026243300 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 20996.21 | 20719.8866 | 276.3234 | 2023-01-01 | 2023-12-31 | 2023-04-12 | 2023-04-12 | CCC# 21042 CC#23191 CC#24679 CC# 27421 CMCOX 4/27/23 1600
23026268800 | RETIRE ER350 UNIT | [5 empty] | 116.17 | 117.7346 | -1.5646 | 2023-01-01 | 2023-12-31 | 2023-04-12 | 2023-04-12
23026268200 | INSERT 160' OF 3"PMLP MAIN | [5 empty] | 12586.85 | 20952.5602 | -8365.7102 | 2023-01-01 | 2023-12-31 | 2023-04-13 | 2023-04-14
23026268300 | RETIRE 160' OF 4"BSLP MAIN | [5 empty] | 8055.67 | 117.7346 | 7937.9354 | 2023-01-01 | 2023-12-31 | 2023-04-13 | 2023-04-13
23026246401 | INSTALL 3100' OF 2"PMMP MAIN | [5 empty] | 515222.82 | 612252.3877 | -97029.5677 | 2023-01-01 | 2023-12-31 | 2023-03-16 | 2023-05-22
23026246800 | INSTALL 800'-4" PMMP | [5 empty] | 248116.67 | 369832.3416 | -121715.6716 | 2023-01-01 | 2023-12-31 | 2023-03-20 | 2023-04-19
23026246900 | RETIRE 1000'-4" P-MP | [5 empty] | 0 | 123.4477 | -123.4477 | 2023-01-01 | 2023-12-31 | 2023-03-20 | 2023-04-19
21026105201 | INSTALL CHAIN LINK FENCE | [5 empty] | 84349.67 | 78948.1342 | 5401.5358 | 2023-01-01 | 2023-12-31 | 2023-04-14 | 2023-04-14 | FENCE INSTALL COMPLETE APARKS 04-19-23 1600 CCC#24962
22026243600 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 18807.4 | 27565.8866 | -8758.4866 | 2023-01-01 | 2023-12-31 | 2023-04-14 | 2023-04-14 | CCC 25146 INSTALLED NEW MIWI AND SOLAR KIT, NOT COMMIONSED YET CCC 25146 INSTALLED NEW SCADA EQUMENT NOT COMSSIONED YET BUT IS UP AND RUNNING CCC-30719PREFORMED POINT TO POINT FOR NEW WIMI
22026243700 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 17949.62 | 29277.8866 | -11328.2666 | 2023-01-01 | 2023-12-31 | 2023-03-29 | 2023-04-17 | CC 22683 CC 22535 WELDED INLET TAP TESTED INLET 375# 5 MINS RHAYES DMARTIN 03-29-2023 CCC# 24078 NOT ON SITE. CAPITAL PAPERWORK CCC#25522 CWEMPE 4/17/23 COMPLETED PAPERWORK OFFSITE. CWEMPE 4/20/23 DID NOT ENTER STATION. CHARGED TIME FOR PAPERWORK. CWEMPE 4/24/23
22026243800 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 17170.68 | 32044.6752 | -14873.9952 | 2023-01-01 | 2023-12-31 | 2023-03-29 | 2023-04-18 | CC 22535 WELDED TAPS TESTED INLET 375# OUTLET 45# MINS DMARTIN RHAYES 03-29-2023 CCC# 24067 CCC#25645 CWEMPE 4/18/23 COMPLETED PAPERWORK OFFSITE. CWEMPE 4/20/23 DID NOT ENTER STATION. CHARGED TIME FOR PAPERWORK. CWEMPE 4/24/23
22026244100 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 17388.43 | 32044.6752 | -14656.2452 | 2023-01-01 | 2023-12-31 | 2023-03-29 | 2023-04-19 | CC 22622 CC 22535 WELDED TAPS TESTED INLET 375# OUTLET 90# 5 MINS RHAYES DMARTIN 03-29-2023 CCC# 24075 CALLED FOR CLEARANCE TICKET AT END OF DAY AND CCC REFUSED TO CREATE TICKET. CWEMPE 4/19/23 COMPLETED PAPERWORK OFFSITE. CWEMPE 4/20/23
22026243000 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 20860 | 29336.8866 | -8476.8866 | 2023-01-01 | 2023-12-31 | 2023-04-20 | 2023-04-20 | CC# 23362 CCC# 24092 DID NOT ENTER STATION. CWEMPE 4/27/23
23026268400 | INSTALL 2000' OF 2"PMMP MAIN | [5 empty] | 56232.52 | 83632.6185 | -27400.0985 | 2023-01-01 | 2023-12-31 | 2023-04-04 | 2023-04-21
21026115500 | INSTALL 9560' OF 2"PMMP | [5 empty] | 1791950.44 | 1674772.7999 | 117177.6401 | 2023-01-01 | 2023-12-31 | 2023-01-16 | 2023-06-30
23026273500 | EMER-INSTALL 65' OF 2"PMIP | [5 empty] | 5983.61 | 8772.0552 | -2788.4452 | 2023-01-01 | 2023-12-31 | 2023-04-20 | 2023-04-21
23026273600 | EMER-RETIRE 55' OF 2"PAIP | [5 empty] | 1024.42 | 117.7346 | 906.6854 | 2023-01-01 | 2023-12-31 | 2023-04-20 | 2023-04-21
22026244300 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 21295.01 | 29761.6752 | -8466.6652 | 2023-01-01 | 2023-12-31 | 2023-04-21 | 2023-04-21 | CC 22295 TAPS WELDED TESTED INLET 375# OUTLET90# 5MIN TESTED GOOD RHAYES CCC# 24050 CCC#26526 CWEMPE 4/21/23
22026234001 | INSTALL 500' OF 2"/4"PMMP MAIN | [5 empty] | 88694.69 | 89921.6185 | -1226.9285 | 2023-01-01 | 2023-12-31 | 2023-03-28 | 2023-04-25 | INSTALLED 422' 040-PMMP 185' 020-PMMP 607' TOTAL
23026272700 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 2367.44 | 5551.3568 | -3183.9168 | 2023-01-01 | 2023-12-31 | 2023-04-25 | 2023-04-25
23026272800 | EMER - RETIRE 5'-2" PMMP | [5 empty] | 0 | 112.7299 | -112.7299 | 2023-01-01 | 2023-12-31 | 2023-04-25 | 2023-04-25
22026244200 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 20934.82 | 33186.6752 | -12251.8552 | 2023-01-01 | 2023-12-31 | 2023-04-25 | 2023-04-25 | CCC# 24912 WELDED ON PUNCH TEES FOR SCADA VISIBILITY PROJECT. TESTED TAPPED, AND MT COMPLETE. LOCKED AND PLUGGED VALVE. CCC# 26916
23026272300 | EMER-INSTALL 3" NC POLY VALVE | [5 empty] | 6810.69 | 7421.5276 | -610.8376 | 2023-01-01 | 2023-12-31 | 2023-04-28 | 2023-04-28 | REPLACED BROKEN CRITICAL VLV WITH NEW 030 POLY VLV. TEST PIPE,VLV,&CPLGS 90#1HOUR, TG. ST LTI OK. BHBNGF. R.CRAWFORD 4-28-23
23026272400 | EMER-RETIRE 3"PV C16-87 | [5 empty] | 85.95 | 117.7346 | -31.7846 | 2023-01-01 | 2023-12-31 | 2023-04-28 | 2023-04-28 | REFER TO JOB#-23026272300 FOR COMMENTS. R.CRAWFORD 4-28-23
22026243100 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 18742.99 | 21860.8866 | -3117.8966 | 2023-01-01 | 2023-12-31 | 2023-04-26 | 2023-04-26 | CC 22894 WELDED TAPS ON COULD NOT PRESSURE TEST DUE TO TIME CONSTRAINTS PER RTWAIT CCC# 24089
22026183100 | INSTALL 3090' OF 2-4" PMMP | [5 empty] | 609662.9 | 533028.4351 | 76634.4649 | 2023-01-01 | 2023-12-31 | 2023-04-28 | 2023-09-08 | PROJECT COMPLETE
23026273200 | EMER-RETIRE 741'-1" PMP | [5 empty] | 1327.21 | 1738.6263 | -411.4163 | 2023-01-01 | 2023-12-31 | 2023-04-29 | 2023-05-24
23026263200 | GMB TO CAB CONVERSION | [5 empty] | 758.88 | 124.7348 | 634.1452 | 2023-01-01 | 2023-12-31 | 2023-05-02 | 2023-05-02 | GATHER PARTS INFO 27 - 300,000 BTU HANGING UNIT HEATERS = 8,100,000 3 - 300,000 BTU ROOF TOP UNITS = 900,000 TOTAL BTU LOAD - 9,000,000 GMB TO CAB CONVERSION
21026140501 | INSTALL 1,985'-6" CSHP | [5 empty] | 140188.39 | 116515.0569 | 23673.3331 | 2023-01-01 | 2023-12-31 | 2023-02-01 | 2023-05-19
22026228201 | INSTALL 4,225'-2"/6" PMMP | [5 empty] | 1935349.38 | 1875934.718 | 59414.662 | 2023-01-01 | 2023-12-31 | 2023-01-03 | 2023-05-22
21026140600 | RETIRE 2,598'- 6" BSHP | [5 empty] | 182.4 | 61.5191 | 120.8809 | 2023-01-01 | 2023-12-31 | 2023-02-01 | 2023-05-19
22026228400 | RETIRE 1133'- MP MAIN | [5 empty] | 0 | 952.0929 | -952.0929 | 2023-01-01 | 2023-12-31 | 2023-02-01 | 2023-05-04
22026243900 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 13592.24 | 14352.6752 | -760.4352 | 2023-01-01 | 2023-12-31 | 2023-03-28 | 2023-05-04 | CHANGE OF PLAN, SCADA IS NOT BUILT FOR THIS SIGHT AND NOT READY TO BE CHANGED OVER, CMCHOLAN 3-28-23 INSTALL NEW MIWI, P2P OK, GAGE INSP OK, REMOVED PAPER PRESSURE CHART, PRESSURE TEST OK, CMCHOLAN 5-4-23 1358
22026244000 | RETIRE ELECTRONICS | [5 empty] | 65.38 | 131.2422 | -65.8622 | 2023-01-01 | 2023-12-31 | 2023-05-04 | 2023-05-04 | REMOVED ERX TO INSTALL MIWI, CCC 22274, CMCHOLAN 3-28-23
23026251500 | INSTALL 70'-2" PMLP | [5 empty] | 16349.3 | 20790.0608 | -4440.7608 | 2023-01-01 | 2023-12-31 | 2023-05-04 | 2023-05-05
23026275200 | EMER - INSTALL 3'-2" PMIP | [5 empty] | 5562.78 | 9765.5645 | -4202.7845 | 2023-01-01 | 2023-12-31 | 2023-05-04 | 2023-06-14 | INSTALLED 3' OF 2" MAIN DUE TO DAMAGE BY BORE CREW TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 5.5 PSIG
23026275300 | EMER - RETIRE 3'-2" PIP | [5 empty] | 235.76 | 134.4334 | 101.3266 | 2023-01-01 | 2023-12-31 | 2023-05-04 | 2023-06-14 | RETIRED 3' OF 2" PL DUE TO BORE CREW HITTING MAIN TIEING CONDUIT TOGHETHER
23026272600 | INSTALL 875' OF 2"PMMP MAIN | [5 empty] | 29299.51 | 32780.4095 | -3480.8995 | 2023-01-01 | 2023-12-31 | 2023-05-03 | 2023-05-09
21026149800 | RETIRE R-1615 | [5 empty] | 552.62 | 16113.7857 | -15561.1657 | 2023-01-01 | 2023-12-31 | 2023-02-01 | 2023-05-09
23026274800 | RETIRE REG BUILDING | [5 empty] | 0 | 117.7346 | -117.7346 | 2023-01-01 | 2023-12-31 | 2023-02-01 | 2023-05-15
22026228300 | RETIRE 6,106'- LP MAIN | [5 empty] | 182.4 | 952.0929 | -769.6929 | 2023-01-01 | 2023-12-31 | 2023-02-01 | 2023-05-19
23026274600 | EMER - INSTALL 5'-2" PMIP | [5 empty] | 2867.86 | 11073.0623 | -8205.2023 | 2023-01-01 | 2023-12-31 | 2023-02-01 | 2023-05-11
23026274700 | EMER - INSTALL 5'-2" PM | [5 empty] | 0 | 116.0664 | -116.0664 | 2023-01-01 | 2023-12-31 | 2023-05-11 | 2023-05-11
23026274900 | EMER - INSTALL 4'-2" PMMP | [5 empty] | 15519.62 | 31722.4446 | -16202.8246 | 2023-01-01 | 2023-12-31 | 2023-05-11 | 2023-05-24
23026275000 | EMER - RETIRE 4'-2" PMMP | [5 empty] | 2331.35 | 139.1159 | 2192.2341 | 2023-01-01 | 2023-12-31 | 2023-05-15 | 2023-05-24
23026275900 | RETIRE BATTERY FACILITY | [5 empty] | 0 | 139.1159 | -139.1159 | 2023-01-01 | 2023-12-31 | 2023-05-17 | 2023-05-17
23026246500 | RETIRE 2400' OF 4"BS/CSLP MAIN | [5 empty] | 0 | 138.8485 | -138.8485 | 2023-01-01 | 2023-12-31 | 2023-03-16 | 2023-05-22
23026268700 | PM-DE LINE PH 2 DENT 2/STPL 3 | [5 empty] | 703157.62 | 1307000 | -603842.38 | 2023-01-01 | 2023-12-31 | 2023-03-27 | 2023-05-23
22026175100 | INSTALL 3" OUTLET VALVE | [5 empty] | 36249.58 | 40477.7168 | -4228.1368 | 2023-01-01 | 2023-12-31 | 2023-05-19 | 2023-05-24
22026175200 | RETIRE ~10' - 3" CSHP | [5 empty] | 257.25 | 593 | -335.75 | 2023-01-01 | 2023-12-31 | 2023-05-19 | 2023-05-24
23026275100 | RETIRE 276'-3" BSLP | [5 empty] | 5918.41 | 12701.243 | -6782.833 | 2023-01-01 | 2023-12-31 | 2023-05-23 | 2023-05-23
23026275800 | INSTALL NEW BATTERY/EQUIPMENT | [5 empty] | 135.94 | 2819.6093 | -2683.6693 | 2023-01-01 | 2023-12-31 | 2023-05-23 | 2023-05-23
23026251600 | INSTALL RTU BUILDING | [5 empty] | 2010.08 | 170.6969 | 1839.3831 | 2023-01-01 | 2023-12-31 | 2023-05-05 | 2023-05-25 | CCC#28635 WORK DONE FOR WHAT THEY ARE DOING TODAY 5-5-23 JUSTIN HOBBS CCC# 31032 CREATED OTH FACID 861369 FOR HVAC. SM 12/1/23
22026169100 | RT. 89 POD RTU BUILDING | [5 empty] | 221479.78 | 143652.6755 | 77827.1045 | 2023-01-01 | 2023-12-31 | 2023-05-25 | 2023-05-25 | CCC# 13947 MONITOR NOT ONSITE ACP NOT WORKING AT THAT SITE TODAY CCC# 13947 NOT ONSITE NOT ONSITE CCC#21297 CCC# 31371
22026242600 | INSTALL 500' - 4" PMMP | [5 empty] | 115979.71 | 97718.819 | 18260.891 | 2023-01-01 | 2023-12-31 | 2023-04-28 | 2023-05-26
23026301000 | EMER-INSTALL 2' OF 4"PMMP MAIN | [5 empty] | 3269.69 | 4675.4752 | -1405.7852 | 2023-01-01 | 2023-12-31 | 2023-05-31 | 2023-05-31
23026301100 | EMER-RETIRE 2' OF 4"PAMP MAIN | [5 empty] | 0 | 122.9261 | -122.9261 | 2023-01-01 | 2023-12-31 | 2023-05-31 | 2023-05-31
23026269400 | PM-DE LINE ILI PH2 DENT2,STPL3 | [5 empty] | 198957.22 | 216349 | -17391.78 | 2023-01-01 | 2023-12-31 | 2023-03-27 | 2023-05-31
23026265100 | INSTALL 10'-3"PMLP | [5 empty] | 15746.7 | 37610.5067 | -21863.8067 | 2023-01-01 | 2023-12-31 | 2023-05-31 | 2023-06-02 | INSTALLED 10 FT OF PL TEST FROM POINT A TO B 90 LB FOR 20 MIN TEST OK SOAP TEST 2 CPLG AND ALL BAG HOLES AT OP BHBNGF MAIN READ -0.601 INSTALLED 2 ANODES
23026265200 | RETIRE 10'-3" BSLP | [5 empty] | 190.67 | 120.2184 | 70.4516 | 2023-01-01 | 2023-12-31 | 2023-05-31 | 2023-06-02 | RETIRED 10 FT OF 3 IN BS PIPE PURGED OUT AND SEALED THE INLINE TEE SIDE
23026277200 | EMER-RETIRE 55' OF 6"PMLP MN | [5 empty] | 5550.64 | 4206.4374 | 1344.2026 | 2023-01-01 | 2023-12-31 | 2023-06-14 | 2023-06-14 | RETIRED 52' OF 6'-P-LP WITH E/F COUPLING AND DEAD END CAP. PURGED 52' OF ' MAIN OUT OF SERVICE. SOAP TESTED FINAL CONNECTION FOR 5 MINTES AT OP. TEST OKAY.
23026255400 | GMB TO CAB CONVERSION | [5 empty] | 9499.75 | 2712.0987 | 6787.6513 | 2023-01-01 | 2023-12-31 | 2023-06-01 | 2023-06-01 | REMOVED OLD GMB FACILITIES REBUILT METER SETTING INSTALLED NEW ROMET 16M ME TER AND CL838 REGS ON 15# DELIVERY BLONE 6-1-23
22026219400 | INSTALL 380' OF 4"PMMP MAIN | [5 empty] | 171665.76 | 176409.6078 | -4743.8478 | 2023-01-01 | 2023-12-31 | 2023-05-17 | 2023-06-08
23026268600 | PM-DE LINE ILI PH2 DENT 36 | [5 empty] | 1598843.54 | 1150001 | 448842.54 | 2023-01-01 | 2023-12-31 | 2023-03-27 | 2023-06-03
23026269300 | PM-DE LINE ILI PH2 DENT 36 ABD | [5 empty] | 279860.8 | 192300 | 87560.8 | 2023-01-01 | 2023-12-31 | 2023-03-27 | 2023-06-05
23026278500 | EMER - INSTALL 3'-2" PMMP | [5 empty] | 3085.38 | 4078.3783 | -992.9983 | 2023-01-01 | 2023-12-31 | 2023-06-06 | 2023-07-06
23026278600 | EMER - RETIRE 3'-2" PMMP | [5 empty] | 10.24 | 139.1159 | -128.8759 | 2023-01-01 | 2023-12-31 | 2023-06-06 | 2023-07-06
23026278100 | RETIRE REG FAC | [5 empty] | 0 | 67.1159 | -67.1159 | 2023-01-01 | 2023-12-31 | 2023-06-06 | 2023-06-06 | JOB TO EXECUTE PAPERWORK ONLY RWILLIAMS 6-6-2023
21026127100 | RETIRE 9400'-2"&4" BS&CS | [5 empty] | 1334.61 | 67.799 | 1266.811 | 2023-01-01 | 2023-12-31 | 2023-01-03 | 2023-06-07
23026267800 | INSTALL 580' OF 2"PMMP MAIN | [5 empty] | 35753.76 | 40516.7801 | -4763.0201 | 2023-01-01 | 2023-12-31 | 2023-05-30 | 2023-06-08
23026277900 | EMER - INSTALL 69'-6" PMLP | [5 empty] | 31362.92 | 35367.5186 | -4004.5986 | 2023-01-01 | 2023-12-31 | 2023-06-06 | 2023-06-08 | INSTALLED 40' 060 PMP TESTED FOR 1HR AT 90LBS.TEST OK. SOAP TEST TIE INS AT OP.TEST OK. BHB NGF WORKED WITH 558
22026219500 | RETIRE 380' OF 4"BSMP MAIN | [5 empty] | 91.2 | 89.0305 | 2.1695 | 2023-01-01 | 2023-12-31 | 2023-05-17 | 2023-06-08
23026278000 | EMER - RETIRE 69'-6" BSLP | [5 empty] | 124.77 | 139.1159 | -14.3459 | 2023-01-01 | 2023-12-31 | 2023-06-06 | 2023-06-08 | ABDN 40' OF 6'' STEEL WORKED WITH 557.
23026273900 | INSTALL 441 REG (WEST RUN) | [5 empty] | 4130.38 | 3436.7638 | 693.6162 | 2023-01-01 | 2023-12-31 | 2023-06-08 | 2023-06-08 | (NOT ON-SITE GETTING PARTS TO COMPLETE JOB) G.HALE NOT ONSITE COLLECTING REG AND PARTS APARKS 05-18-23 1551 SWAPPED 461 REGS FOR 441 REGS 57S 1 3/4 ORFICE BROWN SPRING IN BOTH CONTROL AND MONITOR MAJOR INSP. COMPLETED ON BOTH REGS INLET@90# MON@55# CON@47# CCC# 33177 NOT ONSITE PAPER WORK ONLY APARKS 06-19-23 1000
23026274000 | RETIRE 461 REGS (WEST RUN) | [5 empty] | 0 | 117.7346 | -117.7346 | 2023-01-01 | 2023-12-31 | 2023-06-08 | 2023-06-08
23026299900 | PAPER ONLY SL REPLACEMENT | [5 empty] | 1201.76 | 145.9261 | 1055.8339 | 2023-01-01 | 2023-12-31 | 2023-10-10 | 2023-10-10 | paper only
23026299800 | PAPER ONLY SL RETIRE | [5 empty] | 0 | 122.9261 | -122.9261 | 2023-01-01 | 2023-12-31 | 2023-06-12 | 2023-06-12 | paper only
22026171800 | INSTALL 3178'-2" PMIP | [5 empty] | 806129.21 | 663052.9501 | 143076.2599 | 2023-01-01 | 2023-12-31 | 2023-04-17 | 2023-07-20
23026278200 | EMER-INSTALL 185' OF 4"PMLP | [5 empty] | 41523.49 | 28939.243 | 12584.247 | 2023-01-01 | 2023-12-31 | 2023-06-14 | 2023-06-16
23026278300 | EMER-RETIRE 181' OF 4"BSLP MN | [5 empty] | 0 | 139.1159 | -139.1159 | 2023-01-01 | 2023-12-31 | 2023-06-14 | 2023-06-16
23026272200 | INSTALL 200' OF 2"PMMP MAIN | [5 empty] | 27418.37 | 23237.6457 | 4180.7243 | 2023-01-01 | 2023-12-31 | 2023-06-06 | 2023-06-16
23026268500 | PM-DE LINE ILI PH 2 BEND 260 | [5 empty] | 717133.15 | 1150001 | -432867.85 | 2023-01-01 | 2023-12-31 | 2023-03-23 | 2023-06-16
22026170600 | INSTALL 7,200'-2"/4" PMMP | [5 empty] | 1526718.34 | 1129128.3572 | 397589.9828 | 2023-01-01 | 2023-12-31 | 2023-03-20 | 2023-09-22
23026279900 | RETIRE 38'-3" PMP | [5 empty] | 0 | 139.1159 | -139.1159 | 2023-01-01 | 2023-12-31 | 2023-06-12 | 2023-06-26
23026278700 | INSTALL 105'-2" PMMP | [5 empty] | 8200.66 | 17148.7846 | -8948.1246 | 2023-01-01 | 2023-12-31 | 2023-06-19 | 2023-06-26 | INSTALLED 116' OF 2" PL MP TESTED 90 PSIG 0005 MIN SOAP TESTED CAPS AND DEA D HEADS OP 17 PSG
22026164201 | INSTALL 2,300'-2" PMMP | [5 empty] | 487634.39 | 442002.9907 | 45631.3993 | 2023-01-01 | 2023-12-31 | 2023-08-02 | 2023-08-03
23026281600 | EMER-INSTALL 3'-3" PMMP | [5 empty] | 5032.43 | 5640.4544 | -608.0244 | 2023-01-01 | 2023-12-31 | 2023-06-22 | 2023-07-17
23026281700 | EMER-RETIRE 3'-3" PMAP | [5 empty] | 0 | 67.1159 | -67.1159 | 2023-01-01 | 2023-12-31 | 2023-06-22 | 2023-07-17
21026117600 | RETIRE REG STATION 1522 | [5 empty] | 0 | 3579.3015 | -3579.3015 | 2023-01-01 | 2023-12-31 | 2023-06-22 | 2023-06-22
23026269200 | PM-DE LINE ILI PH2 BEND 260 AB | [5 empty] | 195099.48 | 192300 | 2799.48 | 2023-01-01 | 2023-12-31 | 2023-03-23 | 2023-06-23
22026236400 | INSTALL 450'-4" PMMP | [5 empty] | 52709.69 | 61251.1595 | -8541.4695 | 2023-01-01 | 2023-12-31 | 2023-06-12 | 2023-06-27
23026281200 | EMER-INSTALL 2' OF 2"PMMP MAIN | [5 empty] | 6222.18 | 5082.4374 | 1139.7426 | 2023-01-01 | 2023-12-31 | 2023-06-26 | 2023-06-26
23026281300 | EMER-RETIRE 2' OF 2"PMMP MAIN | [5 empty] | 0 | 139.1159 | -139.1159 | 2023-01-01 | 2023-12-31 | 2023-06-26 | 2023-06-26
23026273000 | INSTALL 20'-4"PMMP W/NEW VALVE | [5 empty] | 20711.38 | 13458.2914 | 7253.0886 | 2023-01-01 | 2023-12-31 | 2023-06-23 | 2023-06-26 | LOWERED 4" MP PE MAIN,REPLACED CRITICAL VLV,TEST MAIN@90IB 1HR,TIED IN W/2 EF CPLG'S, SOAP TEST TIE IN,MOVE CV TO SOFT SURFACE 06/26/2023 HMCKUNE
23026273100 | RETIRE 20'-4"PMMP W/C19-314 | [5 empty] | 0 | 117.7346 | -117.7346 | 2023-01-01 | 2023-12-31 | 2023-06-23 | 2023-06-26
21026999201 | RETIRE 3"PIP SERVICE LINE | [5 empty] | 14749.54 | 6359.645 | 8389.895 | 2023-01-01 | 2023-12-31 | 2023-06-26 | 2023-06-26 | STEP 3 NEEDS INVESTIGATED STEP 3 NEEDS STATE PERMIT STEP 3 NEEDS STATE PERMIT THIS IS A PAPER ABN. THIS LINE IS AN ACTIVE LINE BUT THEY ARE NOT OUR CUSTOMER. THEY ARE USING NATURAL ENERGY. OUR ASSETS ARE NOT WITHIN THE PROPERTY. U131418 J. PARKS 4-24-23
21026115600 | RETIRE 9,590' OF BSLP & OTHER | [5 empty] | 182.4 | 67.799 | 114.601 | 2023-01-01 | 2023-12-31 | 2023-01-03 | 2023-06-30
23026282600 | EMER - RETIRE 216'-2" PAMP | [5 empty] | 5057.99 | 2153.608 | 2904.382 | 2023-01-01 | 2023-12-31 | 2023-06-27 | 2023-07-14
23026276300 | EMER-INSTALL 2"POLY VALVE | [5 empty] | 6851.84 | 10283.4841 | -3431.6441 | 2023-01-01 | 2023-12-31 | 2023-06-22 | 2023-06-27 | INSTALLED NEW CRIT.VLV. TEST VLV FOR 1 HOUR, TG. TEST 2 BYPASS, TG. TEST ALL TEES, TG. ST LTI'S, TG. ALL TIME FOR JOB# 23186718700 TO BE CHARGED BACK TO THIS JOB, R.CRAWFORD 6-23-23 REFER TO JOB# 23026276400 FOR COMMENTS. R.CRAWFORD 6-27-23
23026276400 | EMER-RETIRE 2"VALVE C14-27 | [5 empty] | 0 | 139.1159 | -139.1159 | 2023-01-01 | 2023-12-31 | 2023-06-22 | 2023-06-27 | REFERENCE COMMENTS FOR JOB # 23026276300. R.CRAWFORD 6-23-23 REPLACED BROKEN CV. TEST NEW CV AND PIPE WITH IT 90#1HR, TG. TEST ALL TEES 9#5MINS, TG. TEST BYPASS' 90#1HOUR, TG. ST ALL FINAL TI'S, TG. R.CRAWFORD 6-27-23
23026291400 | PAPER JOB - MP RETIREMENT | [5 empty] | 0 | 119.4953 | -119.4953 | 2023-01-01 | 2023-12-31 | 2023-06-27 | 2023-06-27
23026276900 | RETIRE 250' OF 3"BSLP MAIN | [5 empty] | 1716.17 | 4585.4374 | -2869.2674 | 2023-01-01 | 2023-12-31 | 2023-06-27 | 2023-06-27 | ABDN 252 FT OF 3 IN BS MAIN SOAP TEST 4 PAC CLAMPS AT OP FOR 5 MIN SOAP TEST END CAP AT OP FOR 5 MIN BHBNGF INSTALLED 1ANODE PURGED OUT OLD MAIN AND SEALED MAIN LEFT 36 FT LINE MARKER AT END
23026273300 | INSTALL 290' OF 4" PMMP | [5 empty] | 80935.68 | 48321.0935 | 32614.5865 | 2023-01-01 | 2023-12-31 | 2023-06-19 | 2023-06-30
23026273400 | RETIRE 283' OF 3" BSMP | [5 empty] | 0 | 67.1159 | -67.1159 | 2023-01-01 | 2023-12-31 | 2023-06-19 | 2023-06-30
22026178900 | INSTALL 620' OF 12"CSHP MAIN | [5 empty] | 268220 | 330116.9371 | -61896.9371 | 2023-01-01 | 2023-12-31 | 2023-04-01 | 2023-06-30
22026179100 | RETIRE 520' OF 12"MJBSHP | [5 empty] | 3152.18 | 131.2422 | 3020.9378 | 2023-01-01 | 2023-12-31 | 2023-04-01 | 2023-06-30
23026258000 | RETIRE PAPER CHART | [5 empty] | 555.95 | 121.7239 | 434.2261 | 2023-01-01 | 2023-12-31 | 2023-07-05 | 2023-07-05 | CCC# 36022 RETIRED PAPER CHART. JMARTIN JHOBBS 7-5-23 CCC# 36022
23026257900 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 1323.01 | 22482.2854 | -21159.2754 | 2023-01-01 | 2023-12-31 | 2023-07-07 | 2023-07-07 | CCC# 36022 INSTALL NEW MIWI 350. JMARTIN JHOBBS 7-5-23 CCC#36022
23026282700 | EMER-ABANDON 333' OF 2"PAMP | [5 empty] | 2936.25 | 3839.4374 | -903.1874 | 2023-01-01 | 2023-12-31 | 2023-07-06 | 2023-07-06 | ABND CUL-DE-SAC AFTER HIT LINE BY OTHER CONTRACTOR PER ENGINEER/FOL AFTER VERIFICATION NO CUSTOMERS ON GAS FOR SECTION OF MAIN TO BE ABND
23026283400 | EMER - INSTALL 5'-3" PMMP | [5 empty] | 4261.01 | 10280.7214 | -6019.7114 | 2023-01-01 | 2023-12-31 | 2023-07-10 | 2023-07-24 | INST 5'- 3" NEW PL MAIN BY ENGINEERED PLAN. MCRAIG 7/10/23
23026283500 | EMER - RETIRE 5'-3" PMP | [5 empty] | 36.39 | 139.1159 | -102.7259 | 2023-01-01 | 2023-12-31 | 2023-07-10 | 2023-07-24 | RETIRE 5' OF 3" PL MAIN DUE TO LEAK PER ENGINEERED PLAN. MCRAIG 7/10/23
23026261400 | RETIRE PAPER CHART | [5 empty] | 0 | 121.7239 | -121.7239 | 2023-01-01 | 2023-12-31 | 2023-07-10 | 2023-07-10
23026261300 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 4877.76 | 26706.2854 | -21828.5254 | 2023-01-01 | 2023-12-31 | 2023-07-10 | 2023-07-10 | CC # 36552 INSTALLD MIWI NO CC NOT ONSITE--PAPER WORK
23026261600 | RETIRE PAPER CHART | [5 empty] | 388.77 | 121.7239 | 267.0461 | 2023-01-01 | 2023-12-31 | 2023-07-11 | 2023-07-11 | CC # 36725
23026261500 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 4069.95 | 26706.2854 | -22636.3354 | 2023-01-01 | 2023-12-31 | 2023-07-11 | 2023-07-11 | CC # 36725 NO CC NEEDED---GMB ACCOUNT NOT ON SITE NO CC NEEDED---PAPERWORK OFF SITE CC # 40724
23026280800 | EMER-INSTALL 62' OF 4"PMLP | [5 empty] | 63661.35 | 28754.8748 | 34906.4752 | 2023-01-01 | 2023-12-31 | 2023-07-11 | 2023-07-12 | INSTALLE 40 FT 4 IN MAIN TEST FROM POINT A TO POINT B 90 LB FOR 1 HR TEST ALL TEES AT 90 LB FOR 5 MIN SOAP TEST EFC AND BOLTD CPLG AT O OP FOR 5 MIN SOAP TEST 1 IN END CAP AT OP FOR 5 MIN INSTALL 1 ANODE
23026284000 | EMER-INSTALL 2' OF 3"PMMP MAIN | [5 empty] | 14848.12 | 4281.828 | 10566.292 | 2023-01-01 | 2023-12-31 | 2023-07-12 | 2023-07-26
23026286000 | EMER - INSTALL 6'-2" PMMP | [5 empty] | 5456.45 | 14279.5419 | -8823.0919 | 2023-01-01 | 2023-12-31 | 2023-07-12 | 2023-08-21
23026280900 | EMER-RETIRE 62' OF 4"BSLP | [5 empty] | 2161.53 | 139.1159 | 2022.4141 | 2023-01-01 | 2023-12-31 | 2023-07-12 | 2023-07-12 | RETIRED 36 FT OF BS AND 9 FT OF PL 4 IN LOW PRESSURE MAIN
23026284100 | EMER-RETIRE 2' OF 3"PAMP MAIN | [5 empty] | 0 | 139.1159 | -139.1159 | 2023-01-01 | 2023-12-31 | 2023-07-12 | 2023-07-26
23026286100 | EMER - RETIRE 6'-2" PMMP | [5 empty] | 5375.26 | 67.1159 | 5308.1441 | 2023-01-01 | 2023-12-31 | 2023-07-12 | 2023-08-21
23026257600 | RETIRE PAPER CHAT | [5 empty] | 575.02 | 121.7239 | 453.2961 | 2023-01-01 | 2023-12-31 | 2023-07-12 | 2023-07-12
23026257500 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 3917.88 | 23732.2854 | -19814.4054 | 2023-01-01 | 2023-12-31 | 2023-07-12 | 2023-07-12
23026258200 | RETIRE PAPER CHART | [5 empty] | 0 | 121.7239 | -121.7239 | 2023-01-01 | 2023-12-31 | 2023-07-13 | 2023-07-13
23026258100 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 4339.86 | 20638.2854 | -16298.4254 | 2023-01-01 | 2023-12-31 | 2023-07-13 | 2023-07-13 | CC 41992
23026284300 | EMER-INSTALL 490' OF 2"PMMP | [5 empty] | 132813.07 | 184478.0101 | -51664.9401 | 2023-01-01 | 2023-12-31 | 2023-07-14 | 2023-08-10 | BARE STEEL LP MAIN LEAKING, CREW WAS UNABLE TO EXPOSE LEAK, ABANDONED BS MAIN AND BORED IN 490'OF 2"P- PRE AND POST CAMERA COMPLETED-PT NEW MAIN 90LBS FOR 1HR PER ENGINEERING-SOAP TESTED TIE IN AT OP
23026284400 | EMER-RETIRE 520' OF 4"BSMP MN | [5 empty] | 223.9 | 139.1159 | 84.7841 | 2023-01-01 | 2023-12-31 | 2023-07-14 | 2023-08-10 | REPLACED 493' OF 4'' S MP WITH 2'' PMP DUE TO GRADE 1 LEAK.DPI D304338.
22026171900 | RETIRE ~3325'-2" BS,CS & P | [5 empty] | 0 | 83.4538 | -83.4538 | 2023-01-01 | 2023-12-31 | 2023-04-17 | 2023-07-20
23026259300 | RETIRE PAPER CHART | [5 empty] | 0 | 121.7239 | -121.7239 | 2023-01-01 | 2023-12-31 | 2023-07-14 | 2023-07-14
23026259200 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 4121.74 | 21353.2854 | -17231.5454 | 2023-01-01 | 2023-12-31 | 2023-07-14 | 2023-07-14 | CC 37280
23026282000 | INSTALL 40'-4" PMIP | [5 empty] | 49257.58 | 63454.1516 | -14196.5716 | 2023-01-01 | 2023-12-31 | 2023-07-06 | 2023-07-18
23026282100 | RETIRE 36'-4" BSIP | [5 empty] | 124.74 | 139.1159 | -14.3759 | 2023-01-01 | 2023-12-31 | 2023-07-26 | 2023-07-18
23026261800 | RETIRE PAPER CHART | [5 empty] | 642.64 | 121.7239 | 520.9161 | 2023-01-01 | 2023-12-31 | 2023-07-17 | 2023-07-17 | CC 37443
17026706600 | CONVERT FROM GMB TO CAB ACCT | [5 empty] | 14520.06 | 1078.4716 | 13441.5884 | 2023-01-01 | 2023-12-31 | 2023-07-17 | 2023-07-17 | CCC# 36905 CCC#36905
23026261700 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 3770.68 | 21353.2854 | -17582.6054 | 2023-01-01 | 2023-12-31 | 2023-07-17 | 2023-07-17
23026259500 | RETIRE PAPER CHART | [5 empty] | 347.11 | 121.7239 | 225.3861 | 2023-01-01 | 2023-12-31 | 2023-07-18 | 2023-07-18
23026259400 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 3579.71 | 20638.2854 | -17058.5754 | 2023-01-01 | 2023-12-31 | 2023-07-18 | 2023-07-18
23026256000 | INSTALL 800'OF 2"PMMP MAIN | [5 empty] | 92592.66 | 192451.7008 | -99859.0408 | 2023-01-01 | 2023-12-31 | 2023-07-13 | 2023-07-27
23026256300 | INSTALL 130'-2" PMIP | [5 empty] | 19141.35 | 38002.449 | -18861.099 | 2023-01-01 | 2023-12-31 | 2023-07-20 | 2023-07-21
23026284800 | EMER - INSTALL 40'-4" PMLP | [5 empty] | 630.98 | 16339.4428 | -15708.4628 | 2023-01-01 | 2023-12-31 | 2023-07-21 | 2023-07-25 | INSTALLED 34' OF 4" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 10" WC
23026284900 | EMER - RETIRE 40'-4" BSLP | [5 empty] | 451.35 | 139.1159 | 312.2341 | 2023-01-01 | 2023-12-31 | 2023-07-21 | 2023-07-25 | RETIRED 34' OF 4" BS MAIN DUE TO LEAKAGE SOAP TESTED OP TO VERIFY SHUTDOWN SOAP TESTED OP 10" WC
23026279800 | INSTALL 1800'-2" PMMP | [5 empty] | 53278.51 | 72065.7028 | -18787.1928 | 2023-01-01 | 2023-12-31 | 2023-07-17 | 2023-07-25
23026285300 | EMER - RETIRE 159'-3"BSLP | [5 empty] | 5197.96 | 10816.0505 | -5618.0905 | 2023-01-01 | 2023-12-31 | 2023-07-24 | 2023-07-27 | ABDN 159' OF 3'' BS LP.LEAK UNDER DRIVEWAY APPRON.MAIN NOT FEEDING ANY S/L.LEFT 15' OF 3'' ACTIVE. SOAP TEST END CAP AT OP FOR 5MINS TEST OK. BHB NGF. INSTALLED ANODE DENSO WRAPPED.
23026279100 | INSTALL 300' OF 2"PMIP MAIN | [5 empty] | 7749.44 | 17364.828 | -9615.388 | 2023-01-01 | 2023-12-31 | 2023-07-26 | 2023-07-28
23026284500 | INSTALL 80'4" PMLP | [5 empty] | 23619.02 | 47424.0373 | -23805.0173 | 2023-01-01 | 2023-12-31 | 2023-07-24 | 2023-07-27 | TEST FROM POINT A TO B TO C 90 LB FOR 1 HR TEST OK TEST FINAL TIE IN AT OP OK BHBNGF INSTALLED 3 ANODES MAIN READ -0.591 TEST PAAC CLAMPS AT OP OK
23026285800 | EMER-INSTALL 3' OF 2"PMMP MAIN | [5 empty] | 8976.29 | 6991.8345 | 1984.4555 | 2023-01-01 | 2023-12-31 | 2023-07-25 | 2023-07-25
23026284600 | RETIRE 80'-4" BSLP | [5 empty] | 4684.11 | 139.1159 | 4544.9941 | 2023-01-01 | 2023-12-31 | 2023-07-24 | 2023-07-27 | RETIRED 60 FT OF BS 4IN MAIN PURGED OUT AND REMOVED PIPE
23026285900 | EMER-RETIRE 3' OF 2"PMMP MAIN | [5 empty] | 0 | 139.1159 | -139.1159 | 2023-01-01 | 2023-12-31 | 2023-07-25 | 2023-07-25
23026278900 | INSTALL 150'-2" PMMP | [5 empty] | 10151.75 | 13769.2187 | -3617.4687 | 2023-01-01 | 2023-12-31 | 2023-07-27 | 2023-07-28
20026983500 | INSTALL 1670' - 2" PMMP | [5 empty] | 426217.2 | 347784.1168 | 78433.0832 | 2023-01-01 | 2023-12-31 | 2023-05-25 | 2023-08-28
23026289300 | INSTALL 7'-2"&6" PMLP | [5 empty] | 447.65 | 141.4953 | 306.1547 | 2023-01-01 | 2023-12-31 | 2023-06-23 | 2023-08-28
20026983600 | ABANDON 1667'-2/3/4" PMLP/BSLP | [5 empty] | 290.24 | 360.3823 | -70.1423 | 2023-01-01 | 2023-12-31 | 2023-05-25 | 2023-08-28
22026164300 | RETIRE 3,574'-BSLP | [5 empty] | 136.8 | 84.9152 | 51.8848 | 2023-01-01 | 2023-12-31 | 2023-08-02 | 2023-08-03
23026288500 | EMER - INSTALL 3'-2" PMMP | [5 empty] | 33.23 | 15193.894 | -15160.664 | 2023-01-01 | 2023-12-31 | 2023-07-31 | 2023-08-21
23026288600 | EMER - RETIRE 3'-2" PMP | [5 empty] | 4237.6 | 119.4953 | 4118.1047 | 2023-01-01 | 2023-12-31 | 2023-07-31 | 2023-08-21
23026247700 | INSTALL NEW GMB SETTING | [5 empty] | 96486.51 | 92317.8265 | 4168.6835 | 2023-01-01 | 2023-12-31 | 2023-07-27 | 2023-08-04 | TICKET# 39340 CCC#39340 CCC#39492 08-04-2023 RHAYES CCC#39795
21026997801 | INSTALL 4600' OF 2"/6"PMMP | [5 empty] | 2229938.96 | 2229421.3209 | 517.6391 | 2023-01-01 | 2023-12-31 | 2022-09-14 | 2023-10-19
23026251800 | RETIRE 900' OF 2"CSHP MAIN | [5 empty] | 12666.75 | 4095.9621 | 8570.7879 | 2023-01-01 | 2023-12-31 | 2023-08-07 | 2023-08-07
23026256400 | INSTALL 25' OF 2"PMMP MAIN | [5 empty] | 9201.52 | 8978.2187 | 223.3013 | 2023-01-01 | 2023-12-31 | 2023-08-07 | 2023-08-08 | INSTALLED 18' OF NEW MAIN AND ONE SERVICE LINE TO 1600 VILLA MEDICI TWALKER/KY 10-19-23: ISSUED BACK ORDER CANCEL 53922 FOR THE 250' COIL OF 2"PIPE WHICH IS NO LONGER AVAILABLE
22026168600 | INSTALL 13,800'-2"PMMP | [5 empty] | 1531903.82 | 1751471.355 | -219567.535 | 2023-01-01 | 2023-12-31 | 2023-01-03 | 2023-09-08
22026168700 | RETIRE 12,327'-BSLP,CSLP,PLP | [5 empty] | 0 | 89.0305 | -89.0305 | 2023-01-01 | 2023-12-31 | 2023-01-03 | 2023-09-08
23026288000 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 267.7 | 3242.0133 | -2974.3133 | 2023-01-01 | 2023-12-31 | 2023-08-09 | 2023-08-10 | RELACED 5' OF 020 PMP DUE TO SOCKET ON TEE LEAKING. TESTED 5' OF 020 FOR 1HR AT 90LBS.TEST OK. SOAP TEST 2 2'' EFC AT OP. TEST OK. BHB NGF.
23026277000 | EMER-INSTALL 15' OF 8"PMLP MN | [5 empty] | 19403.77 | 23129.0935 | -3725.3235 | 2023-01-01 | 2023-12-31 | 2023-08-08 | 2023-08-10 | INSTALLED 8 IN PL MAIN TEST FROM POINT A TO POINT B SOAP TEST ALL PAC CLAMPS AND CPLG AT OP FOR 5 MIN BHBNGF INSTALLED 2 ANODE
23026277100 | EMER-RETIRE 15' OF 8"BSLP MN | [5 empty] | 307.27 | 139.1159 | 168.1541 | 2023-01-01 | 2023-12-31 | 2023-08-09 | 2023-08-10 | ABDN 11 FT 8 IN BS MAIN INSTALLED 11 8 IN PL MAIN TEST 90 LB FOR 1 HHR SOAP TEST FINAL TIE IN AT OP FOR 5MIN BHBNGF
23026288100 | EMER - RETIRE 5'-2" PMMP | [5 empty] | 1.39 | 119.4953 | -118.1053 | 2023-01-01 | 2023-12-31 | 2023-08-09 | 2023-08-10 | RELACED 5' OF 020 PMP DUE TO SOCKET ON TEE LEAKING. TESTED 5' OF 020 FOR 1HR AT 90LBS.TEST OK. SOAP TEST 2 2'' EFC AT OP. TEST OK. BHB NGF.
23026283200 | INSTALL 480' OF 2"PMMP MAIN | [5 empty] | 47476.79 | 59017.0935 | -11540.3035 | 2023-01-01 | 2023-12-31 | 2023-08-07 | 2023-08-17 | TWALKER/KY 10-20-23: REQUESTED CUSTOMER REFUND FOR THE CUSTOMER PAID RELOCA TION PROJECT.
23026288700 | INSTALL NEW RELIEF VALVE | [5 empty] | 814.62 | 3278.6711 | -2464.0511 | 2023-01-01 | 2023-12-31 | 2023-08-11 | 2023-08-11
23026288800 | RETIRE RELIEF VALVE | [5 empty] | 0 | 119.4953 | -119.4953 | 2023-01-01 | 2023-12-31 | 2023-08-11 | 2023-08-11
23026256201 | INSTALL VRG CONTROLLERS | [5 empty] | 78966.67 | 47185.8659 | 31780.8041 | 2023-01-01 | 2023-12-31 | 2023-06-14 | #N/A | DROPPING OF MATTERIAL 06-02-23 1324 CCC# 32360 CCC#32737 CC# 33503 CCC# 33503 CCC# 39939
21026130400 | INSTALL 25,111'-2",4" PMMP | [5 empty] | 4355642.45 | 3707985.656 | 647656.794 | 2023-01-01 | 2023-12-31 | 2022-08-01 | 2023-12-05
23026290100 | EMER - 3'-3" PMIP | [5 empty] | 5680.32 | 2929.2518 | 2751.0682 | 2023-01-01 | 2023-12-31 | 2023-08-15 | 2023-09-20 | INSTALLED 3' OF 2" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 5 PSIG
23026290200 | EMER-RETIRE 3'-PIP | [5 empty] | 253 | 119.4953 | 133.5047 | 2023-01-01 | 2023-12-31 | 2023-08-15 | 2023-09-20 | CUT OUT 3' OF 2" PL DUE TO HIT MAIN SOAP TESTED TO VERIFY SHUTDOWN AFTER SQUEEZE OP
23026257300 | RETIRE CHART | [5 empty] | 386.09 | 124.7348 | 261.3552 | 2023-01-01 | 2023-12-31 | 2023-08-15 | 2023-08-15
23026257200 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 3080.61 | 12042.2854 | -8961.6754 | 2023-01-01 | 2023-12-31 | 2023-08-12 | 2023-08-12 | CC 41028
23026257800 | RETIRE PAPER CHART | [5 empty] | 1141.91 | 121.7239 | 1020.1861 | 2023-01-01 | 2023-12-31 | 2023-08-16 | 2023-08-16
23026257700 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 3552.01 | 22126.2854 | -18574.2754 | 2023-01-01 | 2023-12-31 | 2023-08-16 | 2023-08-16
22026225400 | INSTALL APROX 180'-6" PMLP | [5 empty] | 160069.05 | 120007.3465 | 40061.7035 | 2023-01-01 | 2023-12-31 | 2023-07-06 | 2023-08-21 | GURU ADDED 2'-6"PLASTIC RISER PIPE TO TD 0735002. SM 11/7/23
23026289900 | EMER-INSTALL 8'-3" PMMP | [5 empty] | 2980.18 | 1914.647 | 1065.533 | 2023-01-01 | 2023-12-31 | 2023-08-17 | 2023-09-01
22026225500 | RETIRE 200' - 6" BSLP | [5 empty] | 510.72 | 117.7346 | 392.9854 | 2023-01-01 | 2023-12-31 | 2023-07-06 | 2023-08-21
23026290000 | EMER-RETIRE 8'-3" PAMP | [5 empty] | 9034.26 | 7157.6376 | 1876.6224 | 2023-01-01 | 2023-12-31 | 2023-08-17 | 2023-09-01
23026283300 | RETIRE 400' OF 2"BSMP MAIN | [5 empty] | 0 | 139.1159 | -139.1159 | 2023-01-01 | 2023-12-31 | 2023-08-17 | 2023-08-17
23026288200 | INSTALL VERIZON MODEM | [5 empty] | 1861.82 | 4954.3422 | -3092.5222 | 2023-01-01 | 2023-12-31 | 2023-08-17 | 2023-08-17
23026288300 | RETIRE SATELLITE COMM EQUIP | [5 empty] | 0 | 119.4953 | -119.4953 | 2023-01-01 | 2023-12-31 | 2023-08-17 | 2023-08-17
23026266100 | INSTALL 880'-4" PHHP | [5 empty] | 70247.34 | 60596.7317 | 9650.6083 | 2023-01-01 | 2023-12-31 | 2023-08-01 | 2023-08-18
20026976900 | INSTALL RTU & INSTRUMENTATION | [5 empty] | 362179.42 | 302143.1164 | 60036.3036 | 2023-01-01 | 2023-12-31 | 2022-11-28 | 2023-08-22 | CCC# 2490 CCC# 2490 CCC# 2490 CCC# 5078 6417 CCC# 7314 CCC# 7314 CCC# 7314 CCC# 6417 CCC# 6417 CCC# 6417 CCC# 6417 CCC# 6417
20026977000 | RETIRE RTU & INSTRUMENTATION | [5 empty] | 2598.25 | 60.3089 | 2537.9411 | 2023-01-01 | 2023-12-31 | 2022-11-28 | 2023-08-22
22026223600 | INSTALL 3000' OF 2"PMMP MAIN | [5 empty] | 80798.26 | 81410.7619 | -612.5019 | 2023-01-01 | 2023-12-31 | 2023-07-31 | 2023-08-23
22026242700 | INSTALL 350' OF 8"CSHP MAIN | [5 empty] | 381751.32 | 370158.4472 | 11592.8728 | 2023-01-01 | 2023-12-31 | 2023-07-11 | 2023-08-31
22026242800 | RETIRE 326' OF 8"CSHP MAIN | [5 empty] | 0 | 114.3981 | -114.3981 | 2023-01-01 | 2023-12-31 | 2023-07-11 | 2023-08-31
23026254400 | INSTALL 420' OF 6"PMMP MAIN | [5 empty] | -558.31 | 9832.3981 | -10390.7081 | 2023-01-01 | 2023-12-31 | 2023-06-30 | 2023-08-31
23026254500 | RETIRE 356' OF 6"PMMP MAIN | [5 empty] | 0 | 114.3981 | -114.3981 | 2023-01-01 | 2023-12-31 | 2023-06-30 | 2023-08-31
22026162102 | INSTALL 8150' OF 2"/4"PMMP | [5 empty] | 755714.67 | 751182.165 | 4532.505 | 2023-01-01 | 2023-12-31 | 2023-01-20 | 2023-11-30
23026277300 | INSTALL 265' OF 6"PMMP MAIN | [5 empty] | 29277.24 | 71789.4841 | -42512.2441 | 2023-01-01 | 2023-12-31 | 2023-08-17 | 2023-08-31 | JOB COMPLETED. 08312023
23026277400 | RETIRE 285' OF 6"PMMP MAIN | [5 empty] | 439.67 | 139.1159 | 300.5541 | 2023-01-01 | 2023-12-31 | 2023-08-17 | 2023-08-31 | JOB COMPLETED
23026267600 | INSTALL 110'-4"PMLP | [5 empty] | 32525.16 | 46300.0467 | -13774.8867 | 2023-01-01 | 2023-12-31 | 2023-09-07 | 2023-09-11
23026291700 | EMER - INSTALL 3'-4" PMIP | [5 empty] | 2433.5 | 9351.5219 | -6918.0219 | 2023-01-01 | 2023-12-31 | 2023-09-07 | 2023-09-08 | INSTALLED 3' OF 4" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7 PSIG
23026291800 | EMER - RETIRE 3'-4" PIP | [5 empty] | 685.77 | 119.4953 | 566.2747 | 2023-01-01 | 2023-12-31 | 2023-09-01 | 2023-09-08 | RETIRED 3' OF 4" PL DUE TO LEAK ON 4" SF COUPLING SOAP TESTED OP 7 PSIG TO VERIFY ADEQUATE SHUTDOWN
23026291200 | EMER - INSTALL 8'-3" PMIP | [5 empty] | 51065.27 | 32593.7477 | 18471.5223 | 2023-01-01 | 2023-12-31 | 2023-09-08 | 2023-09-08 | INSTALLED 3INCH PLASTIC MAIN SECTION TO REPLACE LEAKING 3 INCH BS MAIN JCK 9.8.23
23026291300 | EMER - RETIRE 7'3" BS&P | [5 empty] | 392.93 | 119.4953 | 273.4347 | 2023-01-01 | 2023-12-31 | 2023-09-08 | 2023-09-08 | ABANDON LEAKING METAL MAIN. INSTALLED 3 INCH PLASTIC MAIN JCK 9.8.23
23026258900 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 5852.27 | 22126.2854 | -16274.0154 | 2023-01-01 | 2023-12-31 | 2023-08-29 | 2023-09-01
23026286800 | INSTALL 100' OF 2"PMIP MAIN | [5 empty] | 13755.57 | 8938.3422 | 4817.2278 | 2023-01-01 | 2023-12-31 | 2023-08-23 | 2023-09-05 | SPOTTED UTILITIES WITH VAC TRUCK. BORED IN 100' OF 020 P MAIN, PRESSURE TEST 1 HOUR AT 90#, TG. ST LTI, TG. R.CRAWFORD 9-5-23
23026263000 | INSTALL 5875' OF 2"/4"PMMP ENV | [5 empty] | 763454.52 | 728668.2681 | 34786.2519 | 2023-01-01 | 2023-12-31 | 2023-03-09 | 2023-09-12
23026263100 | RETIRE 6090' OF 4"BSMP MAIN | [5 empty] | 0 | 124.7348 | -124.7348 | 2023-01-01 | 2023-12-31 | 2023-03-09 | 2023-09-12
22026242301 | INSTALL 8"POLY VALVE W/10"SPH | [5 empty] | 84380.42 | 63212.0666 | 21168.3534 | 2023-01-01 | 2023-12-31 | 2023-08-21 | 2023-09-07
23026280100 | RETIRE 10' OF 10"CSMP MAIN | [5 empty] | 273.6 | 139.1159 | 134.4841 | 2023-01-01 | 2023-12-31 | 2023-08-21 | 2023-09-07
23026286300 | RETIRE 306' OF 3"BSLP MAIN | [5 empty] | 4872.41 | 7586.4374 | -2714.0274 | 2023-01-01 | 2023-12-31 | 2023-08-15 | 2023-09-05 | ABN. 40' OF PLASTIC AND 306' OF STEEL MAIN. PURGE ALL GAS OUT. PLUGGED ENDS NGF AFTER PURGED. USED EF EC, ST AT OP, TG. R.CRAWFORD 9-5-23
22026212500 | REPLACE VALVES AT R-1084 | [5 empty] | 9402.89 | 14531.0267 | -5128.1367 | 2023-01-01 | 2023-12-31 | 2023-08-21 | 2023-09-06 | HELP CCOX WITH VALVE REPLACEMENT, CMCHOLAN 9-5-23 1600 CC# 43383 PAPERWORK ONLY. NO CC# REQUIRED. NOT ON SITE.
22026212600 | RETIRE STATION VALVES R-1084 | [5 empty] | 1269.98 | 119.4953 | 1150.4847 | 2023-01-01 | 2023-12-31 | 2023-08-21 | 2023-09-06
22026183200 | RETIRE 3765' OF 2-4" CS & PMMP | [5 empty] | 273.03 | 138.8485 | 134.1815 | 2023-01-01 | 2023-12-31 | 2023-03-16 | 2023-09-08 | PROJECT COMPLETED
23026293900 | EMER-INSTALL 3' OF 2"PMMP MAIN | [5 empty] | 7147.03 | 14157.3554 | -7010.3254 | 2023-01-01 | 2023-12-31 | 2023-09-08 | 2023-09-18
23026294000 | EMER-RETIRE 3' OF 2"PMMP MAIN | [5 empty] | 0 | 119.4953 | -119.4953 | 2023-01-01 | 2023-12-31 | 2023-09-08 | 2023-09-18
23026266200 | INSTALL 1100'-4" PHHP | [5 empty] | 125731.21 | 81743.7317 | 43987.4783 | 2023-01-01 | 2023-12-31 | 2023-08-04 | 2023-09-12
23026274301 | INSTALL 3400' OF 2"PMMP MAIN | [5 empty] | 82979.94 | 79169.604 | 3810.336 | 2023-01-01 | 2023-12-31 | 2023-07-21 | 2023-09-14
22026170700 | RETIRE BSLP | [5 empty] | 0 | 89.0305 | -89.0305 | 2023-01-01 | 2023-12-31 | 2023-02-14 | 2023-09-22
23026297000 | INSTALL PCF'S LP | [5 empty] | 2982.68 | 145.9261 | 2836.7539 | 2023-01-01 | 2023-12-31 | 2023-09-14 | 2023-09-14
22026205900 | RETIRE R-1682 | [5 empty] | 603.96 | 1417.3638 | -813.4038 | 2023-01-01 | 2023-12-31 | 2023-09-14 | 2023-09-14
23026295300 | RETIRE FENCE | [5 empty] | 0 | 119.4953 | -119.4953 | 2023-01-01 | 2023-12-31 | 2023-09-19 | 2023-09-19
22026205800 | RETIRE 20'-2" PMP | [5 empty] | 0 | 89.0305 | -89.0305 | 2023-01-01 | 2023-12-31 | 2023-02-14 | 2023-09-18
22026182101 | INSTALL 8,450' - 2"/4" PMMP | [5 empty] | 940113.78 | 861854.0803 | 78259.6997 | 2023-01-01 | 2023-12-31 | 2023-03-13 | 2023-09-19
23026257100 | INSTALL 300'-2" PMMP | [5 empty] | 68581.44 | 32921.1974 | 35660.2426 | 2023-01-01 | 2023-12-31 | 2023-09-20 | 2023-09-28 | MAINLINE EXTENSION FOR ALDI'S INSTALLED BY STANLEY PIPELINE. JOSH PASLEY 9/28/23
22026231200 | INSTALL 1870'-2"/4" PMMP | [5 empty] | 89157.03 | 71796.5181 | 17360.5119 | 2023-01-01 | 2023-12-31 | 2023-07-21 | 2023-10-04
22026172301 | INSTALL 5000' OF 2"PMMP MAIN | [5 empty] | 906953.7 | 1183513.1452 | -276559.4452 | 2023-01-01 | 2023-12-31 | 2023-11-14 | 2024-04-26
23026294600 | ABANDON ~790'-2" PMMP | [5 empty] | 392.35 | 3905.6711 | -3513.3211 | 2023-01-01 | 2023-12-31 | 2023-09-21 | 2023-10-04
23026292501 | INSTALL 800' OF 2-4" PMMP | [5 empty] | 232050.11 | 229159.9279 | 2890.1821 | 2023-01-01 | 2023-12-31 | 2023-09-14 | 2023-10-06
23026300800 | EMER-INSTALL 5' OF 3"PMLP | [5 empty] | 5351.34 | 4600.4752 | 750.8648 | 2023-01-01 | 2023-12-31 | 2023-10-10 | 2023-10-10
18026793901 | INSTALL 4,123' - 2" PMMP | [5 empty] | 603491.8 | 506341.5777 | 97150.2223 | 2023-01-01 | 2023-12-31 | 2022-06-17 | 2023-12-07
20026978100 | INSTALL 8620'- 2" PMMP | [5 empty] | 1699797.2 | 1435185.1923 | 264612.0077 | 2023-01-01 | 2023-12-31 | 2022-12-21 | 2023-11-27
23026300900 | EMER-RETIRE 5' OF 3"PLP MAIN | [5 empty] | 0 | 122.9261 | -122.9261 | 2023-01-01 | 2023-12-31 | 2023-10-10 | 2023-10-10
23026300000 | INSTALL NEW EQUIPMENT | [5 empty] | 570.56 | 3973.8688 | -3403.3088 | 2023-01-01 | 2023-12-31 | 2024-02-05 | 2023-10-10
23026287800 | INSTALL 500'-4" PMMP | [5 empty] | 175667.6 | 99252.0533 | 76415.5467 | 2023-01-01 | 2023-12-31 | 2023-09-07 | 2023-10-23
23026287900 | RETIRE 500'-3" PMP | [5 empty] | 0 | 119.4953 | -119.4953 | 2023-01-01 | 2023-12-31 | 2023-09-07 | 2023-10-23
23026297200 | EMER - INSTALL 13'-2" PMMP | [5 empty] | 4970.8 | 9353.5801 | -4382.7801 | 2023-01-01 | 2023-12-31 | 2023-09-29 | 2023-10-12 | VALVE RETIRED.SOAP TEST END CAPS AT OP FOR 5MINS. TEST OK.BHB NGF LEAKING 020 P CRITICAL VALVE.LEAKING FROM STEM.RETIRED VALVE WITH 020 BYPASS.TESTED BYPASS AS MAIN FOR 1HR AT 90LBS.TEST OK INSTALLED TWO END CAPS AT VALVE TO ABDN VALVE.020 BYPASS MADE TO ACVTIVE MAIN AFTER
23026297300 | EMER - RETIRE 2'-2" PMP | [5 empty] | 5943.6 | 122.9261 | 5820.6739 | 2023-01-01 | 2023-12-31 | 2023-09-29 | 2023-10-12 | VALVE RETIRED.SOAP TEST END CAPS AT OP FOR 5MINS. TEST OK.BHB NGF LEAKING 020 P CRITICAL VALVE.LEAKING FROM STEM.RETIRED VALVE WITH 020 BYPASS.TESTED BYPASS AS MAIN FOR 1HR AT 90LBS.TEST OK INSTALLED TWO END CAPS AT VALVE TO ABDN VALVE.020 BYPASS MADE TO ACVTIVE MAIN AFTER
20026974601 | INSTALL 6,500'-4"PMLP | [5 empty] | 2600268.43 | 2219393.0276 | 380875.4024 | 2023-01-01 | 2023-12-31 | 2023-08-11 | 2023-10-13
23026302100 | RETIRE PAPER GAUGE | [5 empty] | 306.23 | 989.8688 | -683.6388 | 2023-01-01 | 2023-12-31 | 2023-10-13 | 2023-10-13
23026302800 | EMER - INSTALL 2'-3" PMP | [5 empty] | 3993.16 | 3855.2637 | 137.8963 | 2023-01-01 | 2023-12-31 | 2023-10-17 | 2023-10-30
23026302900 | EMER - RETIRE 2'-3" PMP | [5 empty] | 0 | 122.9261 | -122.9261 | 2023-01-01 | 2023-12-31 | 2023-10-17 | 2023-10-30
21026997900 | RETIRE 6300' OF 4"/6"CILP MN | [5 empty] | 747.19 | 126.9534 | 620.2366 | 2023-01-01 | 2023-12-31 | 2022-10-14 | 2023-10-19
23026290800 | INSERT/INSTALL 160'-3"PMLP MN | [5 empty] | 45549.98 | 46254.1681 | -704.1881 | 2023-01-01 | 2023-12-31 | 2023-09-25 | 2023-10-20 | TEST FROM POINT A TTO B 90 LB FOR 1 HR TEST 2 IN HV TEE AND 2 IN MAIN FROM POINT A TO B 90 LB FOR 1 HR
23026290900 | RETIRE 60' OF 3"BSLP MAIN | [5 empty] | 7967.87 | 119.4953 | 7848.3747 | 2023-01-01 | 2023-12-31 | 2023-09-25 | 2023-10-20 | ABDN 82 FT OF 4" BS MAIN AND 143 FT OF 2 " BS MAIN PURGED OUT AND SEALED UP AND INSTALLED ALL NEW 3 "PL MAIN
23026296800 | EMER - INSTALL 40'-4" PMMP | [5 empty] | 47320.11 | 32230.3112 | 15089.7988 | 2023-01-01 | 2023-12-31 | 2023-10-23 | 2023-10-31
23026296900 | EMER - RETIRE 40'-4" CSMP | [5 empty] | 0 | 122.9261 | -122.9261 | 2023-01-01 | 2023-12-31 | 2023-10-23 | 2023-10-31
23026265300 | INSTALL PILOT REGULATORS | [5 empty] | 9398.99 | 7328.1838 | 2070.8062 | 2023-01-01 | 2023-12-31 | 2023-11-08 | #N/A
23026303700 | EMER - INSTALL 5' OF 2" PMMP | [5 empty] | 579.53 | 147.9261 | 431.6039 | 2023-01-01 | 2023-12-31 | 2023-10-27 | 2023-11-03
23026303800 | EMER - RETIRE 3' OF 2" PAMP | [5 empty] | 114.6 | 124.9261 | -10.3261 | 2023-01-01 | 2023-12-31 | 2023-10-27 | 2023-11-03
23026289100 | INSTALL FENCE | [5 empty] | 23214.65 | 26355.734 | -3141.084 | 2023-01-01 | 2023-12-31 | 2023-10-18 | 2023-10-30 | NOT ON SITE, OFFICE PAPERWORK
23026281400 | INSTALL 1865'-2"/4" PMMP | [5 empty] | 90143.57 | 77027.7111 | 13115.8589 | 2023-01-01 | 2023-12-31 | 2023-10-03 | 2023-11-01
22026164000 | INSTALL 5,100'-2" PMMP | [5 empty] | 1135773.48 | 1140024.6985 | -4251.2185 | 2023-01-01 | 2023-12-31 | 2023-10-03 | 2024-04-10
23026302300 | RETIRE PAPER GAUGE | [5 empty] | 835.24 | 989.8688 | -154.6288 | 2023-01-01 | 2023-12-31 | 2023-10-30 | 2023-11-01 | NOT ONSITE WORK POSTPONED TILL TOMMOROW CCC# 49846
23026277600 | INSTALL 595'-2"PMMP | [5 empty] | 137119.9 | 198539.3537 | -61419.4537 | 2023-01-01 | 2023-12-31 | 2023-10-17 | 2023-11-10
23026302500 | RETIRE PAPER GAUGE | [5 empty] | 994.29 | 989.8688 | 4.4212 | 2023-01-01 | 2023-12-31 | 2023-10-30 | 2023-11-02 | CCC# 50771 MONITOR FOR TC
22026218600 | INSTALL NEW 1ST CUT REGULATOR | [5 empty] | 3338.51 | 2521.2589 | 817.2511 | 2023-01-01 | 2023-12-31 | 2023-10-31 | 2023-11-06 | NOT ONSITE NO CC NEEDED GETTING MATERIAL/BUILDING REG PREPING FOR JOB MCR CC # 51243 INSTALLD NEW 1ST CUT REG DUE TO CORROSION MCR 11-6-23 1445 CC # 51776 ISTALLD TUBING ANF PAINTED SETTIN FIELD WORK COMPLETE
22026218700 | RETIRE 1ST CUT REGULATOR | [5 empty] | 1644.86 | 84.9152 | 1559.9448 | 2023-01-01 | 2023-12-31 | 2023-10-31 | 2023-11-06 | CC # 51243 REMOVED OLD FIRST CUT REG MCR 11-6-23 1030
23026301600 | INSTAL NEW MODEM | [5 empty] | 652.23 | 2605.8688 | -1953.6388 | 2023-01-01 | 2023-12-31 | 2023-11-06 | 2023-11-06
23026301700 | RETIRE MODEM | [5 empty] | 365.2 | 122.9261 | 242.2739 | 2023-01-01 | 2023-12-31 | 2023-11-06 | 2023-11-06
23026277700 | RETIRE 2881'-12" BSMP | [5 empty] | 430.39 | 139.1159 | 291.2741 | 2023-01-01 | 2023-12-31 | 2023-10-17 | 2023-11-10
22026166900 | INSTALL 2010' - 8" & 6" PMMP | [5 empty] | 525084.39 | 400337.2549 | 124747.1351 | 2023-01-01 | 2023-12-31 | 2023-09-11 | 2023-12-19
22026234901 | INSTALL 4,100'-2" PMMP | [5 empty] | 217597.98 | 188453.1623 | 29144.8177 | 2023-01-01 | 2023-12-31 | 2023-09-21 | 2023-11-20
22026213000 | RETIRE 2015'-8/4/2" BSMP/CSMP | [5 empty] | 220 | 89.0305 | 130.9695 | 2023-01-01 | 2023-12-31 | 2023-09-11 | 2023-12-19
23026305300 | EMER-INSTALL 11'-2" PMMP | [5 empty] | 5028.51 | 17054.8912 | -12026.3812 | 2023-01-01 | 2023-12-31 | 2023-11-13 | 2023-11-13 | INSTALLED 11' NEW 2"PL MAIN DURING DAMAGE/HIT LINE FROM BANK CAVE IN INSIDE UTILITY CONTRACTORS EXCAVATION-BHB,NGF-NGF UPON DEP
23026305400 | EMER-RETIRE 11'-2" PMMP | [5 empty] | 383.65 | 124.9261 | 258.7239 | 2023-01-01 | 2023-12-31 | 2023-11-13 | 2023-11-13 | ABND 11'SECTION OF MAIN FOR DAMAGE
23026278401 | INSTALL 2300' OF 2"/4"PMMP MN | [5 empty] | 116796.05 | 101330.2336 | 15465.8164 | 2023-01-01 | 2023-12-31 | 2023-09-18 | 2023-11-16
23026296700 | INSTALL 165' OF 2" PMIP | [5 empty] | 17527.84 | 23912.4752 | -6384.6352 | 2023-01-01 | 2023-12-31 | 2023-12-28 | 2023-12-29 | INSTALLED 157' OF 2" IP MAIN TESTED 90 PSIG 1 HR SOAP TESTED PURGE POINT CAP AND SST CAP OP 7.5 PSIG
20026978200 | RETIRE 8983' LP - 2520' BS | [5 empty] | 513.02 | 476.2758 | 36.7442 | 2023-01-01 | 2023-12-31 | 2022-12-21 | 2023-11-27
21026130500 | RETIRE 25,000' OF BSLP MAINS | [5 empty] | 1741.22 | 485.0228 | 1256.1972 | 2023-01-01 | 2023-12-31 | 2022-01-04 | 2023-12-05
21026154800 | RETIRE 35'-3" CSMP | [5 empty] | 27.2 | 485.0228 | -457.8228 | 2023-01-01 | 2023-12-31 | 2022-01-04 | 2023-12-05
23026306000 | EMER-INSTALL 2'-3" PMMP | [5 empty] | 6302.19 | 6158.638 | 143.552 | 2023-01-01 | 2023-12-31 | 2023-12-03 | 2023-12-04
23026306100 | EMER-RETIRE 2'-3" PMMP | [5 empty] | 0 | 124.9261 | -124.9261 | 2023-01-01 | 2023-12-31 | 2023-12-03 | 2023-12-04
23026298400 | INSTALL MODEM AND ANTENNA | [5 empty] | 0 | 8303.7376 | -8303.7376 | 2023-01-01 | 2023-12-31 | 2023-11-19 | 2023-11-20 | CORRECTED PAPER WORK 11-20-23 JPASLEY
23026276600 | RETIRE RTU FACILITY | [5 empty] | 2357.33 | 139.1159 | 2218.2141 | 2023-01-01 | 2023-12-31 | 2023-06-14 | 2023-11-20 | CCC#33813 PICKED UP TRASH CPRRECTED PAPER WORK JPASLEY 11-20-23
21026154600 | RETIRE R-1354 | [5 empty] | 8911.51 | 163.2711 | 8748.2389 | 2023-01-01 | 2023-12-31 | 2023-11-25 | 2023-11-26
23026307000 | RETIRE METAL BLDG | [5 empty] | 0 | 124.9261 | -124.9261 | 2023-01-01 | 2023-12-31 | 2023-11-25 | 2023-12-01 | TWALKER/KY 12-1-23: THIS BUILDING AND REG STATION RETIRED ON 21-0261546-00.
22026162200 | RETIRE 4600' OF 4"/6"BSLP MAIN | [5 empty] | 1442.96 | 105.0102 | 1337.9498 | 2023-01-01 | 2023-12-31 | 2023-11-27 | 2023-11-30
23026306200 | INSTALL BUILDINGS R-1667 | [5 empty] | 0 | 147.9261 | -147.9261 | 2023-01-01 | 2023-12-31 | 2023-11-27 | 2023-11-28
22026241001 | INSTALL 6375'-2"/4" PMMP ENV | [5 empty] | 797679.45 | 793212.5591 | 4466.8909 | 2023-01-01 | 2023-12-31 | 2023-04-24 | 2023-11-30
23026304100 | RETIRE 667' OF 2"PMMP MAIN | [5 empty] | 4930.16 | 5490.3441 | -560.1841 | 2023-01-01 | 2023-12-31 | 2023-11-17 | 2023-11-29 | ABND MAIN ON STATE ST
23026285500 | RETIRE REG STATION #1129 | [5 empty] | 19139.56 | 22153.7376 | -3014.1776 | 2023-01-01 | 2023-12-31 | 2023-11-29 | 2023-11-30 | CCC#54039
18026794000 | RETIRE 4748'-2"/3"/4"/6"P-BSLP | [5 empty] | 110 | 61.2976 | 48.7024 | 2023-01-01 | 2023-12-31 | 2022-06-17 | 2023-12-07
23026302200 | RETIRE PAPER GAUGE | [5 empty] | 1131.38 | 989.8688 | 141.5112 | 2023-01-01 | 2023-12-31 | 2024-02-14 | 2023-12-04
23026294800 | INSTALL 225' OF 2"PMMP MAIN | [5 empty] | 28626.52 | 19109.6064 | 9516.9136 | 2023-01-01 | 2023-12-31 | 2023-11-27 | 2023-12-05
23026307900 | EMER-INSTALL 10'-4"PMMP/VALVE | [5 empty] | 8046.73 | 6246.9893 | 1799.7407 | 2023-01-01 | 2023-12-31 | 2023-12-17 | 2023-12-18 | LEAKING MAIN VALVE.LEAK FROM STEM.REPLACED WITH NEW VALVE. TESTED 10' OF 040 WITH VALVE FOR 1HR AT 90LBS.TEST OK. SOAP TEST 2 EFC AT OP FOR 5MINS.TEST OK. BHB NGF
23026307400 | EMER-INSTALL 3' OF 2"PMMP | [5 empty] | 1356.05 | 2930.7643 | -1574.7143 | 2023-01-01 | 2023-12-31 | 2023-12-04 | 2023-12-05
23026308000 | EMER-RETIRE 10'-4"PMP/C8-150 | [5 empty] | 147.12 | 123.4493 | 23.6707 | 2023-01-01 | 2023-12-31 | 2023-12-17 | 2023-12-18 | LEAKING MAIN VALVE.LEAK FROM STEM.REPLACED WITH NEW VALVE. TESTED 10' OF 040 WITH VALVE FOR 1HR AT 90LBS.TEST OK. SOAP TEST 2 EFC AT OP FOR 5MINS.TEST OK. BHB NGF
23026307500 | EMER-RETIRE 3' OF 2"PMP MAIN | [5 empty] | 0 | 123.4493 | -123.4493 | 2023-01-01 | 2023-12-31 | 2023-12-04 | 2023-12-05
22026213200 | INSTALL 30' OF 2-4" PMMP S/L | [5 empty] | 33409.7 | 27880.5873 | 5529.1127 | 2023-01-01 | 2023-12-31 | 2023-12-05 | 2023-12-06
22026213100 | RETIRE 3"BSMP SERVICE LINE | [5 empty] | 0 | 63.4096 | -63.4096 | 2023-01-01 | 2023-12-31 | 2023-12-05 | 2023-12-06
23026307700 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 3376.54 | 5646.8353 | -2270.2953 | 2023-01-01 | 2023-12-31 | 2023-12-07 | 2023-12-08
23026307800 | EMER - RETIRE 5'-2" PMP | [5 empty] | 0 | 123.4493 | -123.4493 | 2023-01-01 | 2023-12-31 | 2023-12-07 | 2023-12-08
22026167000 | RETIRE 2260' OF 4-8" BSLP | [5 empty] | 0 | 89.0305 | -89.0305 | 2023-01-01 | 2023-12-31 | 2023-09-11 | 2023-12-19
23026296400 | INSTALL 110' OF 2"PMMP MAIN | [5 empty] | 58459.83 | 46114.2728 | 12345.5572 | 2023-01-01 | 2023-12-31 | 2023-11-14 | 2023-12-21 | CAPITAL JOB COMPLETE BY STANLEY PIPELINE AND CLEARED ASSOCIATED DPI'S. JOSH PASLEY 12/21/23
23026296500 | RETIRE 88' OF 2"CSMP MAIN | [5 empty] | 0 | 122.9261 | -122.9261 | 2023-01-01 | 2023-12-31 | 2023-11-14 | 2023-12-21 | CAPITAL JOB COMPLETED BY STANLEY PIPELINE. CLEARED ASSOCIATED DPI'S. JOSH PASLEY 12/21/23
23026294500 | RETIRE 338' OF 4"BSLP MAIN | [5 empty] | 6772.76 | 4190.6844 | 2582.0756 | 2023-01-01 | 2023-12-31 | 2023-12-13 | 2023-12-14
23026261200 | INSTALL ULTRASONIC METER | [5 empty] | 36758.54 | 47951.5304 | -11192.9904 | 2023-01-01 | 2023-12-31 | 2024-01-29 | 2023-12-14
20026974700 | RETIRE 6,900'-BSLP,CSLP,PLP | [5 empty] | 220 | 66.2135 | 153.7865 | 2023-01-01 | 2023-12-31 | 2023-01-20 | 2023-12-21
23026309100 | EMER-INSTALL 4'OF 2"PMMP MAIN | [5 empty] | 2913.94 | 4579.9666 | -1666.0266 | 2023-01-01 | 2023-12-31 | 2024-01-23 | 2024-01-03 | INST 4'- 2" PL MAIN. TEST MAIN @ 90LB 5MIN OK. SOAP TEST TIE-IN @ OP OK. BHB NGF. CGI MAIN AND SVC OK. WRK 12/20/23. MCRAIG 1/3/24
23026309200 | EMER-RETIRE 4' OF 3"PMP MAIN | [5 empty] | 259.03 | 123.4493 | 135.5807 | 2023-01-01 | 2023-12-31 | 2024-01-03 | #N/A | RETIRE 4'- 2" PL MAIN DUE TO LEAKING WELD. WRK 12/20/23. MCRAIG 1/3/24
23026308900 | EMER INSTALL 4' OF 3" PMMP | [5 empty] | 2961.2 | 3360.6855 | -399.4855 | 2023-01-01 | 2023-12-31 | 2023-12-21 | 2023-12-22 | INST 4'- 3" PL MAIN PER ENGINEERED PLAN AND GAS STANDARDS. TEST NEW MAIN @ 90LB 5MIN OK. SOAP TEST TIE-IN @ OP OK. WORKED ON 12/19/23. MCRAIG 12/22/23
23026309000 | EMER RETIRE 4' OF 3" PMP | [5 empty] | 218.46 | 123.4493 | 95.0107 | 2023-01-01 | 2023-12-31 | 2023-12-21 | 2023-12-22 | RETIRE 4' OF 3" PL MAIN DUE TO LEAK IN ACCORDNANCE W/ ENGINEERING AND GAS STANDARDS. TEST NEW 4' PL @ 90LB 5MIN OK. SOAP TEST TIE-IN. WORKED 12/19/23. MCRAIG 12/22/23
23026262601 | INSTALL CHAIN LINK FENCE | [5 empty] | 72669.9 | 39848.4833 | 32821.4167 | 2023-01-01 | 2023-12-31 | 2023-11-07 | 2023-12-29 | CC 44278 NOT ON SITE CC 53373 CC 53373 CC 57440 CC 58157
Formulas:
Date Actual End = VLOOKUP([Project No.],'WMS JO Data'!$D20:BD27974,25,FALSE)

## 2024 (hidden)
Columbia Gas of Kentucky Case No. 2026-00099 Attachment A Construction Projects For 5 years ended December 31, 2025
Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End | Job Order Comments
18026757700 | INSTALL MI WIRELESS EFC | [5 empty] | 14191.42 | 13926.0597 | 265.3603 |  |  |  | 2022-11-07 | INSTALLED HONEYWELL ERX SUPER SOLAR KIT J MULLINS 11-7-22
18026757800 | RETIRE RECORDING GAUGE | [5 empty] | 0 | 73.0037 | -73.0037 |  |  |  | 2022-11-07 | RETIRED CHART INSTALLED HONEYWELL ERX JMULLINS 11-7-22
18026807000 | INST. FN 115 EXTRA LP OPP | [5 empty] | 28771.63 | 24102.8722 | 4668.7578 |  |  |  | 2021-05-12 | GCCC# 11422 CHARED TIME TO COLLECT MATERIAL. DID NOT VISIT SITE NO GCCC TICKET REQUIRED CMCOC 3/3/21 GCCC# 13985 CMCHOLAN 3-4-2021 CCC#13985 REGULATOR AND ER350 INSTALLED BY CHRIS COX ON 3/4/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026807100 | RET. FN 115 FOR EXTRA LP OPP | [5 empty] | 2550 | 54.9718 | 2495.0282 |  |  |  | 2021-05-12 | REGULATOR REPLACED BY CHRIS COX ON 3/4/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026808800 | INST. FN 259 EXTRA LP OPP | [5 empty] | 258499.79 | 23795.1646 | 234704.6254 |  |  |  | 2021-08-02 | NOT ONSITE. NO GCCC TICKET REQUIRED. CMCOX 7/6/21 GCCC# 30701 CMCOX 7/7/21 NOT ONSITE. NO GCCC TICKET REQUIRED. CMCOX 7/8/21 CCC# 31111 GCCC# 31231 CMCOX 7/13/21 GCCC# 31380 GCCC# 31536 GCCC# 31616 DID NOT ENTER PIT. NO GCCC# REQUIRED. CMCOX 7/19//21 GCCC# 31756 CMCOX 7/20/21 CC# 32093 REGULATORS INSTALLED BY CHRIS COX 7/27/21 PAPERWORK COMPLETED BY CFARIS 7/29/21 CCC# NOT REQUIRED BY CFARIS ON 7/29 OR 8/2 NOT AT STATION
18026808900 | RET. FN 259 FOR EXTRA LP OPP | [5 empty] | 0 | 53.9767 | -53.9767 |  |  |  | 2021-07-29 | REGULATORS REPLACED BY CHRIS COX ON 7/27/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/29/2021 GCCC TICKET NOT REQUIRED ON 7/29/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026843301 | INSTALL 3000' OF 4/6/8"PMLP | [5 empty] | 1711065.31 | 1495308.5734 | 215756.7366 |  |  |  | 2022-09-09
18026843400 | RETIRE 2670' OF 3"/6"CILP MAIN | [5 empty] | 598.25 | 81.035 | 517.215 |  |  |  | 2022-09-12
18026848701 | STATION UPGRADES (SEP RELATED) | [5 empty] | 206545.63 | 151848.4602 | 54697.1698 |  |  |  | 2022-12-15 | CCC 22581 CCC 23126 CCC 23442 CCC 24345 CCC 25855 CCC 26071
19026889001 | INSTALL 28'-8" PMLP | [5 empty] | 30769.7 | 17790.2899 | 12979.4101 |  |  |  | 2021-04-19
20026927900 | UPGRADE ELECTRONICS | [5 empty] | 3660.91 | 3038 | 622.91 |  |  |  | 2022-03-02 | EFC REPLACED BY C. COX ON 3-1-22 PAPERWORK CO BY J MULLINS ON 3-2-22
20026928000 | UPGRADE ELECTRONICS | [5 empty] | 7833.1 | 3038 | 4795.1 |  |  |  | 2021-10-04 | REPLACED EFC AND UPSIZED METER TO 16M ALSO WORKED TP AND MGRP WHILE ON SITE
20026928100 | UPGRADE ELECTRONICS | [5 empty] | 6063.75 | 3038 | 3025.75 |  |  |  | 2021-11-16 | REPLACED EFC
20026928200 | UPGRADE ELECTRONICS | [5 empty] | 3460.63 | 3038 | 422.63 |  |  |  | 2022-07-14 | CMCHOLAN 7-14-2022 RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07-14-2022
20026928300 | UPGRADE FROM 3G NETWORK | [5 empty] | 6815.37 | 3038 | 3777.37 |  |  |  | 2022-02-28 | RETIRED OLD EFC INSTALLED NEW EC350 CCOX 02-28-2022
20026928400 | UPGRADE FROM 3G NETWORK | [5 empty] | 3177.17 | 3038 | 139.17 |  |  |  | 2022-07-14 | RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07-14-2022
20026928500 | UPGRADE ELECTRONICS | [5 empty] | 3667.3 | 3038 | 629.3 |  |  |  | 2022-07-19 | CWEMPE BLONE 7/19/22 RETIRED MINI-AT INSTALLED NEW EC350 CWEMPE 07-19-2022
20026928600 | UPGRADE ELECTRONICS | [5 empty] | 3158.07 | 5626 | -2467.93 |  |  |  | 2022-07-14 | RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON
20026928700 | UPGRADE ELECTRONICS | [5 empty] | 8043.8 | 3038 | 5005.8 |  |  |  | 2021-10-25 | REPLACED EFC
20026928800 | UPGRADE ELECTRONICS | [5 empty] | 6614.01 | 3038 | 3576.01 |  |  |  | 2022-03-02 | ASSIST SMCHOLAN 03-02-2022 RHAYES ASSIST SMCHOLAN 03-02-2022 RHAYES INSTALLED NEW EC350 SOAP TEST TUBING 5MIN OPP PRESSURE SMCHOLAN 3-2-22
20026933700 | RETIRE ELECTRONICS | [5 empty] | 452.45 | 73.3494 | 379.1006 |  |  |  | 2022-03-02 | GAUGE RETIRED BY C. COX PAPPER WORK CO BY J. MULLINS 3-2-2022
20026933800 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 |  |  |  | 2021-11-16 | REPLACED EFC
20026933900 | RETIRE ELECTRONICS | [5 empty] | 1039.15 | 73.3494 | 965.8006 |  |  |  | 2022-07-14 | CMCHOLAN 7-14-2022 RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07142022
20026934000 | RETIRE ELECTRONICS | [5 empty] | 626.57 | 73.3494 | 553.2206 |  |  |  | 2022-02-28 | RETIRED OLD EFC AND INSTALLED NEW EC350 CCOX 02-28-2022
20026934100 | RETIRE ELECTRONICS | [5 empty] | 189.27 | 73.3494 | 115.9206 |  |  |  | 2022-07-14 | RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07-14-2022
20026934200 | RETIRE ELECTRONICS | [5 empty] | 502.89 | 73.3494 | 429.5406 |  |  |  | 2022-07-19 | CWEMPE BLONE 7/19/22 RETIRED OLD MINI-AT INSTALLED NEW EC350
20026934400 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 |  |  |  | 2021-10-25 | REPLACED EFC
20026934500 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 |  |  |  | 2022-03-02 | RETIRED MINI-AT INSTALLED NEW EC350 SMCHOLAN 3-2-22
20026940000 | INSTALL I&C EQUIPMENT | [5 empty] | 11589.34 | 16155.4774 | -4566.1374 |  |  |  | 2022-02-24 | CCC# 43689 RETIRED PAPER CHART INSTALLED NEW ERX CCOX 02-24-2022
20026940100 | RETIRE PAPER GUAGE | [5 empty] | 172.3 | 91.4991 | 80.8009 |  |  |  | 2022-02-24 | RETIRED PAPER CHART INSTALLED HONEYWELL ERX CCOX 2-24-2022
20026941400 | INSTALL I&C EQUIPMENT | [5 empty] | 12022.54 | 16155.4774 | -4132.9374 |  |  |  | 2022-07-28 | INSTALLED TAP ON OUTLET LEG OF RUN 1 20# SYSTEM AND RAN SENSE LINES TO ERX FROM THE NEW TAP AND EXISTING HP SENSE LINE, AND COMMISSIONED ERX CCC 75328, CMCHOLAN CCOX 7-28-2022
20026943300 | INSTALL I&C EQUIPMENT | [5 empty] | 9146.19 | 16155.4774 | -7009.2874 |  |  |  | 2022-05-27 | REMOVED BOTH PAPER CHARTS INSTALLED ERX FOR IP AND MP CMCHOLAN 4-14-2022 CC 65476 COMMISSIONED ERX RHAYES SMCHOLAN 05-03-2022 COMMITIONED ERX, PSP OK, CCC 65476 CMCHOLAN RHAYES 5-3-2022
20026943400 | RETIRE GAUGE | [5 empty] | 543.13 | 91.4991 | 451.6309 |  |  |  | 2022-05-27 | REMOVED BOTH PAPER CHARTS INSTALLED ERX CC 62655 RHAYES SMCHOLAN CCOX EBLANTON 04-14-2022
20026945201 | INSTALL 5000' OF 2"PMMP MAIN | [5 empty] | 228201.9 | 223484.8945 | 4717.0055 |  |  |  | 2021-02-16 | INSTALLED 4938"020 PMMP.
20026951300 | INSTALL 6200' OF 2"PMMP MAIN | [5 empty] | 1175556.48 | 1180648.1173 | -5091.6373 |  |  |  | 2021-05-17
20026951400 | RETIRE 7600' OF 4"CI/BSLP MAIN | [5 empty] | 142.7 | 165.7874 | -23.0874 |  |  |  | 2021-05-17
20026951802 | INSTALL 3980' OF 2"PMMP MAIN | [5 empty] | 461944.16 | 383869.9188 | 78074.2412 |  |  |  | 2021-05-07 | TWALKER/KY 09-21-21: JOB OVER RUN DUE TO ADDITIONAL STREET AND HARD SURFACE REPAIR ADDED $70,000 TO CONTRACT COST AND SEGA WAS $7000 HIGHER THAN ESTIMA TE.
20026951900 | RETIRE 2100' OF 4"CI/PLP MAIN | [5 empty] | 0 | 84.1799 | -84.1799 |  |  |  | 2021-05-07
20026955503 | INSTALL 2850'-8" CSHP | [5 empty] | 1263938.35 | 1308080.823 | -44142.473 |  |  |  | 2021-11-30
20026955600 | RETIRE 6100'-8"/3" BS/CSHP | [5 empty] | 142.7 | 190.2592 | -47.5592 |  |  |  | 2021-11-30
20026955701 | INSTALL 3,945'-4"/2" PMMP | [5 empty] | 702217.99 | 724040.648 | -21822.658 |  |  |  | 2021-12-20
20026955800 | RETIRE 216'-2" PMMP | [5 empty] | 0 | 85.5775 | -85.5775 |  |  |  | 2021-12-17
20026955901 | INSTALL 215'-4" PMMP | [5 empty] | 63490.92 | 67929.8606 | -4438.9406 |  |  |  | 2021-12-20
20026956000 | RETIRE 820'-2" PMMP | [5 empty] | 0 | 85.0089 | -85.0089 |  |  |  | 2021-12-20
20026956101 | INSTALL 2475'-8"/6"/4" PMLP | [5 empty] | 1344804.09 | 1170137.3307 | 174666.7593 |  |  |  | 2021-12-20 | WIPE SAMPLE RESULTS WERE ENTERED ON THE INSTALL JOB INSTEAD OF THE RETIREMENT JOB. RETIREMENT RESULTS WERE ENTERED HERE.
20026956200 | RETIRE 4775'-12">3"PM/BS/CSLP | [5 empty] | 160 | 85.5775 | 74.4225 |  |  |  | 2021-12-20
20026966800 | RETIRE 2800' OF 4"/6"BSLP MAIN | [5 empty] | 907.78 | 90.1729 | 817.6071 |  |  |  | 2021-02-04
20026969700 | INSTALL 8500' OF 2"/4"PMMP MN | [5 empty] | 270941.08 | 301857.4038 | -30916.3238 |  |  |  | 2021-01-08
20026971100 | INSTALL 3300' OF 2"/4"PMMP MN | [5 empty] | 755817.87 | 877421.2279 | -121603.3579 |  |  |  | 2022-03-18 | TWALKER/KY 05-04-22: JOB ORDER RUN DUE TO NO PAVING/HARD SURFACE REPAIRS HA VE BEEN STARTED AT THIS TIME. THIS IS JOINT PAVING RESTORATION WITH CITY OF LEXINGTON AND KY AMERICAN WATER. LOOK FOR COST TO BOOK LATE SUMMER 2022
20026971200 | RETIRE 2100' OF 3"BSLP MAIN | [5 empty] | 1415.61 | 102.0836 | 1313.5264 |  |  |  | 2022-03-18
20026972201 | INSTALL 3300' OF 2"/4" PMMP | [5 empty] | 84926.85 | 89953.3001 | -5026.4501 |  |  |  | 2021-11-04
20026975201 | INSTALL 3000' OF 2"/4"PMMP | [5 empty] | 630664.21 | 552556.8312 | 78107.3788 |  |  |  | 2021-06-11
20026975300 | RETIRE 1900' OF 6"BSLP MAIN | [5 empty] | 1430.35 | 64.0836 | 1366.2664 |  |  |  | 2021-06-11
20026976301 | INSTALL 6300' OF 2"/4"PMMP | [5 empty] | 2104702.57 | 2132943.4537 | -28240.8837 |  |  |  | 2021-12-15
20026976400 | RETIRE 6100' OF 3"/4"BSLP MN | [5 empty] | 1794.07 | 152.7248 | 1641.3452 |  |  |  | 2021-12-15
20026976501 | INSTALL 4270' OF 2"/4"PMMP MN | [5 empty] | 1937333.59 | 1522347.7868 | 414985.8032 |  |  |  | 2022-08-05 | WIPE SAMPLE RESULTS WERE ENTERED ON THE INSTALL JOB IN ERROR. WIPE RESULTS FOR THE RETIREMENT PIPE WERE ENTERED HERE. TWALKER/KY 01-24-23: JOB OVER RUN DUE TO ADDITIONAL STREET/HARD SURFACE REP AIRS REQUIRED BY CITY OF LEXINGTON. CONTRACT COST INCREASED BY $200,000 WITH PAVING/FLAGGING COST, SEGA WAS $73,000 HIGHER THAN PLANNED, ADDITIONAL $22,000 CHARGED FOR MATERIAL COST. TWALKER/KY 08-29-23: LEVEL 2 VARIANCE ADDED TO WMS.DOCS. JOB COST OVERRUN DUE TO ADDITIONAL STREET MILL/RE-PAVED COST REQUIRED BY CITY OF LEXINGTON.
20026976600 | RETIRE 4650' OF 3"/4"BSLP MN | [5 empty] | 320 | 56.8875 | 263.1125 |  |  |  | 2022-08-05
20026977101 | INSTALL 11,500' OF 2"/4"PMMP | [5 empty] | 1143604.07 | 926814.1047 | 216789.9653 |  |  |  | 2021-12-15 | TWALKER/KY 03-02-22: PROJECT COST OVER RUN DUE TO ADDITIONAL CONSTRUCTION COORINATOR ON SITE DURING CONSTRUCTION ADDED $65,000 IN LABOR COST, SEWER VIDEO FOR MAIN/SL BY BUCHANAN WAS $86,000 HIGHER THAN ESTIMATE, ADDITIONAL FLAGGING AND HARD SURFACE REPAIRS ADDED $25,000 TO CONTRACT COST. FINALLY SEGA WAS $35,000 HIGHER THAT PLANNED COST.
20026977200 | RETIRE 6900' OF 4"/6"BSLP MAIN | [5 empty] | 848.1 | 76.6277 | 771.4723 |  |  |  | 2021-12-15
20026981200 | INSTALL 1550' OF 2"PMMP MAIN | [5 empty] | 479750.56 | 414073.7744 | 65676.7856 |  |  |  | 2021-09-28 | TWALKER/KY 05-04-22: JOB OVER RUN CAUSED BY ADDTIONAL $46,000 FOR SEWER CAMERA WORK, PROJECT TOOK LONGER TO COMPLETE DUE TO TRAFFIC AND URBAN SETTING INCREASED COMPANY LABOR BY $5000, SEGA $17000 HIGHER THAN ESTIMATE.
20026981300 | RETIRE 1600' OF 2"/3"BSLP MAIN | [5 empty] | 0 | 84.1799 | -84.1799 |  |  |  | 2021-09-28
20026982700 | INSTALL 4500'-2"&4" PMMP | [5 empty] | 885948.31 | 959444.7901 | -73496.4801 |  |  |  | 2022-03-29
20026982900 | RETIRE 3700'-2&4" BSLP | [5 empty] | 142.7 | 88.8156 | 53.8844 |  |  |  | 2022-04-01
20026984400 | INSTALL 949'-6" PMLP | [5 empty] | 282788.29 | 204292.6769 | 78495.6131 |  |  |  | 2021-03-12 | 14JUN21: OVERRRUN EXPLANATION = 1) REQUIRED FLAGGING WAS WAY UNDERESTIMATED AS $30K ADDITIONAL DOLLARS FOR FLAGGING WAS REQUIRED, 2) AN ADDITIONAL $10K IN DUST & STONE WAS REQUIRED, 3) THE 6" ROCK BORE WAS PAID ALL IN HEAVY ROCK WHEREAS IT WAS ESTIMATED 1/2 HEAVY AND 1/2 LIGHT WHICH CONTRIBUTED ANOTHER $8K TO THE OVERRUN,4) ADDITIONAL VAC EXCAVATION WAS REQUIRED ADDING $3K TO THE OVERRUN. THESE PLUS ADDITIONAL OH'S MAKE UP THE MAJORITY OF THE $57K OVERRUN (BKSLONE)
20026985200 | INSTALL 6" PCF | [5 empty] | 9877.17 | 16280.811 | -6403.641 |  |  |  | 2021-06-12
20026985300 | RETIRE 300'-6" CSMP | [5 empty] | 71.35 | 88.4533 | -17.1033 |  |  |  | 2021-07-01
20026985600 | INSTALL 375' OF 2"CSHP MAIN | [5 empty] | 90203.73 | 92169.2028 | -1965.4728 |  |  |  | 2021-01-03
20026985700 | RETIRE 200' OF 2"CSHP MAIN | [5 empty] | 62.95 | 84.1794 | -21.2294 |  |  |  | 2022-01-03
20026987500 | INSTALL 300' OF 2"PMMP MAIN | [5 empty] | 18181.58 | 19258.6597 | -1077.0797 |  |  |  | 2021-03-10
20026988100 | INSTALL 525' OF 2"PMMP MAIN | [5 empty] | 10228.67 | 17405.4965 | -7176.8265 |  |  |  | 2021-01-11
20026988300 | RETIRE 1853'-4"/3" BS/CSMP | [5 empty] | 47.8 | 5110.2031 | -5062.4031 |  |  |  | 2021-12-16
20026989600 | INSTALL 40'-2" PMMP | [5 empty] | 36919.96 | 30326.4153 | 6593.5447 |  |  |  | 2021-01-15
20026989700 | RETIRE 40'-2" CSMP | [5 empty] | 0 | 107.2796 | -107.2796 |  |  |  | 2021-01-15
20026990600 | PAPER ONLY FOR CLOSE OUT | [5 empty] | 0 | 103.8156 | -103.8156 |  |  |  | 2021-01-21
20026991100 | INSTALL 100' OF 4"PMLP S/L | [5 empty] | 33764.98 | 29024.9725 | 4740.0075 |  |  |  | #N/A
21026100900 | EMER INSTALL 5'-4" PMMP | [5 empty] | 49713.13 | 15398.8131 | 34314.3169 |  |  |  | 2021-02-10 | RETIRED 4 FEET OF 4' PE MAIN LINE. REPLACED PEICE OF MAIN WITH NEW AND EF COUPLINGS. PRESSURE TESTED NEW PEICE OF MAIN FOR 1HR @ 90PSIG. TEST OK. SOAP TESTED FINALS CONNECTION @ OP. TEST, BHB, NGF. DMALONE 2/09/2021. OVERRUN EXPLANATION: UNEXPECTED CONTRACT COST OF $35,000 WAS NOT PLANNED, JO ORIGINALLY PLANNED FOR COMPANY CREW BUT WAS EXECUTED BY A CONTRACT CREW, COMPANY CREWS ALSO CHARGED 183 HOURS TO PROJECT
21026101000 | EMER RETIRE 5'-4" PMP D222468 | [5 empty] | 10.95 | 69.6296 | -58.6796 |  |  |  | 2021-02-09 | RETIRED 4 FEET OF 4' PE MAIN LINE. REPLACED PEICE OF MAIN WITH NEW AND EF COUPLINGS. PRESSURE TESTED NEW PEICE OF MAIN FOR 1HR @ 90PSIG. TEST OK. SOAP TESTED FINAL CONNECTION @ OP. TEST OK. BHB. NGF. DMALONE 2/09/2021 OVERRUN EXPLANATION: THIS RETIREMENT JOB ORDER WAS ESTIMATED IN THE ORDINAR Y MANNER FOR JUST 1 HOUR; HOWEVER, THERE WERE NO PROPERTY UNITS INSTALLED S O THE JOB WAS WORKED AS AN ABANDONMENT WITH ALL THE LABOR AND CONTRACT COST S BEING APPLIED TO THE RETIREMENT. THE INSTALL JOB ORDER WAS EXECUTED WITH AN HOUR OF LABOR.
21026101501 | INSTALL 3800'-2",4"&6" PMMP | [5 empty] | 842479.02 | 710294.4849 | 132184.5351 |  |  |  | 2022-05-05 | OVERRUN EXPLANATION: ENCOUNTERED MORE ROCK EXCAVATION THAN ESTIMATED AS WEL L AS THE ASSOCATED SPECIAL BACKFILL. PROJECT ALSO REQUIRED MORE SEWER CAMER A WORK THAN ESTIMATED.
21026101600 | RETIRE 1200'-2"&4" BSMP | [5 empty] | 325.85 | 85.0089 | 240.8411 |  |  |  | 2022-05-06
21026102900 | INSTALL 2400' OF 4"PMMP MAIN | [5 empty] | 104251.17 | 80646.5708 | 23604.5992 |  |  |  | 2021-06-15
21026104400 | INSTALL 2"SS TO RETIRE INLET | [5 empty] | 24511.65 | 37406.9466 | -12895.2966 |  |  |  | 2021-05-13
21026104500 | RETIRE 7' OF 2"BSMP MAIN | [5 empty] | 72.67 | 80.8842 | -8.2142 |  |  |  | 2021-05-13
21026104600 | RETIRE PIT REG STATION 1016 | [5 empty] | 188917.56 | 138142.7376 | 50774.8224 |  |  |  | 2021-05-14 | REMOVED MONITOR AND CONTROL REG. AND BLIND FLANGED, MONITORED 30 MIN. DUE TO NOT BEING ABLE TO BLIND FLANGE BYPASS, ADVISED CONSTRUCTION ABOUT BYPASS CCC 20355 CMCHOLAN RHAYES NGINTER BLONE 4-23-2021 REGULATORS REMOVED AND BLIND FLANGED ON 4/23/2021 PIPING AND VAULT ABANDONED AND REMOVED BY CONSTRUCTION ON 5/12/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/14/2021 GCCC TICKET NOT REQUIRED ON 5/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS TWALKER/KY 11-15-21: LEVEL 2 VARIANCE FORM ADDED TO WMS.DOCS. JOB OVER RUN DUE TO $41,500 FROM LP/OPP MATERIAL CHARGED TO THIS ORDER. ADDITIONAL $11,000 IN COMPANY HIGHER THAN PLANNED ESTIMATE.
21026105201 | INSTALL CHAIN LINK FENCE | [5 empty] | 84349.67 | 78948.1342 | 5401.5358 |  |  |  | 2023-04-14 | FENCE INSTALL COMPLETE APARKS 04-19-23 1600 CCC#24962
21026105401 | INSTALL 6520' OF 6"PMMP MAIN | [5 empty] | 427430.93 | 403346.5487 | 24084.3813 |  |  |  | 2021-12-17
21026105900 | EMER INSTALL 5' OF 4"PMMP MAIN | [5 empty] | 12908.51 | 24731.5705 | -11823.0605 |  |  |  | 2021-03-18 | TWALKER/KY-04-20-21: I HAVE ADDED A SIGNED PRESSURE TEST TO APPROVE THE 20 MIN PRESSURE TEST TO WMS.DOCS WORKSPACE.
21026106000 | EMER RETIRE 5' OF 4"PAMP MAIN | [5 empty] | 0 | 82.208 | -82.208 |  |  |  | 2021-03-18
21026106100 | INSTALL 1350' OF 2"/4"PMMP | [5 empty] | 39665.6 | 45765.0925 | -6099.4925 |  |  |  | 2021-04-09 | STANLEY PIPELNE INSTALLED MAIN
21026106200 | INSTALL 6" PCF | [5 empty] | 13429.76 | 16594.9062 | -3165.1462 |  |  |  | 2021-04-12 | INSTALLED 6"SST
21026106300 | RETIRE 575'-6" BSLP | [5 empty] | 1068.93 | 88.4533 | 980.4767 |  |  |  | 2021-04-12 | ABANDONED 640'060 CSLP
21026107700 | INSTALL 20' OF 8"PMLP MAIN | [5 empty] | 8482.5 | 12704.2275 | -4221.7275 |  |  |  | 2021-04-14 | REPLACED 36' OF S LP MAON W/ 8" P PER TIE-IN PLAN AND GAS STANDARDS. SOAP TEST TIE-IN COUPLINGS NO LEAKS. BHB NGF. MAIN PTOS READ -0.482 INST 2 9LB ANODES.
21026107800 | RETIRE 20' OF 8" BSLP | [5 empty] | 8727.02 | 56.3197 | 8670.7003 |  |  |  | 2021-04-14 | ABN 36' OF 8" S LP MAIN AND REPLACE WITH 8" P PER GAS STANDARDS AND TIE-IN PLAN. WORKED W/ 557 JOB# 21026107700. MCRAIG 4/14/21
21026107900 | INSTALL 10' OF 3" PMLP | [5 empty] | 7671.47 | 13301.2275 | -5629.7575 |  |  |  | 2021-04-16 | ABANDONED 23' OF 030 S MAIN.DUE TO ATMOS CORR INSTALLED 23' OF 030 PLASTIC WORKED WITH TIE IN PLAN AND GAS STANDARD. BHB NGF. INSTALLED TWO TEST STATIONS AND TWO ANODED.DESNO WRAPPED STEEL MAIN.
21026108000 | RETIRE 10' OF 3" BSLP | [5 empty] | 8414.88 | 79.3197 | 8335.5603 |  |  |  | 2021-04-16 | ABANDONED 23' OF 030 S MAIN.DUE TO ATMOS CORR INSTALLED 23' OF 030 PLASTIC WORKED WITH TIE IN PLAN AND GAS STANDARD. BHB NGF. INSTALLED TWO TEST STATIONS AND TWO ANODED.DESNO WRAPPED STEEL MAIN.
21026108100 | INSTALL 20' OF 3" PMMP | [5 empty] | 70757.52 | 21676.4521 | 49081.0679 |  |  |  | 2021-05-06 | AWEBER/KY 09/21/2021: PROXIMITY OF LP MAIN TO MP MAIN RESULTED IN AN ACTUAL FOOTAGE INSTALL OF 320'-PMMP IN ORDER TO SEPERATE AND INSTALL FITTINGS AS NEEDED. UNABLE TO REVISE WMS JO DUE TO UNPAID MATERIAL INVOICES AND JO COMP LETION STATUS AT THE TIME.
21026108200 | RETIRE 20' OF 3" BSMP | [5 empty] | 4.6 | 56.3197 | -51.7197 |  |  |  | 2021-05-05
21026108600 | EMER-INSTAL 5'-2" PMMP | [5 empty] | 116.02 | 5147.5997 | -5031.5797 |  |  |  | 2021-03-08 | INSTALLED 5' OF TEST 2" PMMP, SOAP TEST TIE IN, NO LEAKS, BHB NGF TIE OVER 2 SERVICE LINES, ON 3-5-21 DMEDLEY 3-8-21
21026108700 | EMER - RETIRE 5'-2" PAMP | [5 empty] | 4796.8 | 85.3307 | 4711.4693 |  |  |  | 2021-03-08 | INSTALLED GAUGE TEE, SQUEEZE OFF 2" PL MAIN, ABN 5' 2"PMP MAIN PER DLEMONS EMER DESIGN PLAN. WORKED ON 3-5-21, DMEDLEY 3-8-21
21026108801 | INSTALL 1000' OF 2"PMMP MAIN | [5 empty] | 51597.09 | 46147.0126 | 5450.0774 |  |  |  | 2022-01-25
21026109300 | INSTALL 300' OF 2"PMMP MAIN | [5 empty] | 26886.16 | 25871.1277 | 1015.0323 |  |  |  | 2021-09-02
21026109900 | RETIRE 2155'-4"/3" BS/PMLP | [5 empty] | 3173.92 | 343.31 | 2830.61 |  |  |  | 2021-04-28
21026110100 | INSTALL 900' OF 2"PMMP MAIN | [5 empty] | 24183.42 | 26234.9875 | -2051.5675 |  |  |  | 2021-06-23
21026110400 | INSTALL 100'-12" CSMP | [5 empty] | 188696.44 | 142453.0552 | 46243.3848 |  |  |  | 2021-06-30 | OVERRUN EXPLANATION: PROJECT OVERRAN DUE TO FLAGGER TIME AND FLAGGER OVERTI ME. BUDGET VARIANCE EXPLANATION FORM LOADED INTO WMSDOCS WORKSPACE. D.LEMONS 12 /3/2021
21026110500 | RETIRE 94'-12" CSMP | [5 empty] | 142.7 | 85.5775 | 57.1225 |  |  |  | 2021-06-30
21026110600 | RETIRE 600'-2&3" PMLP | [5 empty] | 701.12 | 21928.4488 | -21227.3288 |  |  |  | 2021-11-18
21026110700 | REPLACE FENCE | [5 empty] | 480.98 | 14980.1771 | -14499.1971 |  |  |  | 2021-12-17 | CCC# 33097 - BLONE - 07/29/21 FENCE REPLACED BY INTERSTATE FENCE COMPANY PAPERWORK COMPLETED BY CYNTHIA FARIS ON 12/17/2021
21026110800 | RETIRE FENCE | [5 empty] | 0 | 61.2976 | -61.2976 |  |  |  | 2021-12-17 | FENCE REPLACED BY INTERSTATE FENCE COMPANY PAPERWORK COMPLETED BY CYNTHIA FARIS 12/17/2021
21026111101 | INSTALL FENCE | [5 empty] | 5601.7 | 40000.9906 | -34399.2906 |  |  |  | 2021-12-16 | CCC# 31858 , 31996 , 32095 , 32237 , 32396 , 32702 ALL USED DURING PROJECT BLONE - 07/29/21 FENCE INSTALLED BY INTERSTATE FENCE COMPANY PAPERWORK COMPLETED BY CYNTHIA FARIS 12/16/21 UNDERRUN EXPLANATION: THE COST ESTIMATE THAT THE CONTRACTOR PROVIDED TURNED OUT TO BE SIGNIFICANTLY LESS THAN THEY HAD ESTIMATED. GES 3/2/22
21026111200 | RETIRE FENCE | [5 empty] | 0 | 61.2976 | -61.2976 |  |  |  | 2021-12-16 | FENCE REPLACED BY INTERSTATE FENCE COMPANY PAPERWORK COMPLETED BY CYNTHIA FARIS 12/16/21
21026112100 | INSTALL 1025'- 2"/4"PHHP MAIN | [5 empty] | 192775.66 | 194441.8822 | -1666.2222 |  |  |  | 2021-09-29
21026112200 | RETIRE 980' OF 4"CSHP MAIN | [5 empty] | 723.52 | 74.8797 | 648.6403 |  |  |  | 2021-09-29
21026112300 | INSTALL 180' OF 4"PMMP S/L | [5 empty] | 24370.71 | 28556.5857 | -4185.8757 |  |  |  | #N/A
21026112400 | INSTALL NEW GMB SETTING | [5 empty] | 55082.19 | 57016.3076 | -1934.1176 |  |  |  | 2022-08-22 | INSTALLED NEW GMB SKID MOUNTED METER AND REGULATOR SETTING AJPARKS 8-22-202 2 PSID 501306155
21026112700 | INSTALL 350' OF 2"PMIP MAIN | [5 empty] | 37226.93 | 19281.66 | 17945.27 |  |  |  | 2021-06-11
21026113000 | EMER - INSTALL 60' OF 4"PMLP | [5 empty] | 2022.21 | 12530.1178 | -10507.9078 |  |  |  | 2021-04-08 | INSTALLED 54' OF 040 PLASTIC DUE TO STEEL ATMOS CORR. BAGGED OFF MAIN, RETIRED 54' 040 STEEL.WORKED WITH TIE IN PLAN AND CAPITAL PACKET.INSTALLED TWO TEST STATIONS. BHB NGF. KKINDER
21026113100 | EMER - RETIRE 60' OF 4"BSLP | [5 empty] | 1338.57 | 57.8842 | 1280.6858 |  |  |  | 2021-04-08 | ABADONED 54' OF S LP DUE TO ATMOS CORR. WORKED WITH 557. BAGGED OFF MAIN WORKED WITH TIE IN PLAN. KKINDER
21026113600 | RETIRE INLET/OUTLET BLK VALVES | [5 empty] | 0 | 88.1542 | -88.1542 |  |  |  | 2021-07-19 | JOB COMPLETED BY WADE SHIMFESSEL ON 7/19/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/21/21 GCCC TICKET NOT REQUIRED ON 7/21/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026113701 | INSTALL 4030' - 4"/2" PMMP | [5 empty] | 862366.14 | 778460.4875 | 83905.6525 |  |  |  | 2021-12-17
21026114500 | RETIRE PIT REG STATION# 1024 | [5 empty] | 195061.46 | 149437.1771 | 45624.2829 |  |  |  | 2022-05-12 | REMOVED 2 441 REGS AND BLIND FLANGED VALVES, STATION RETIRED, CMCHOLAN CCOX RHAYES 5-12-2022 RWILLIAMS COMPLETED PAPER WORK TWALKER/KY 11-30-22: JOB OVER RUN WAS DUE TO COST FOR 20-0269890-00 (2000) WITH LAND SERVICE AND CONTRACT ENG COST OF $65000, 19-0268950-00 (0001) MATERIAL FOR LPP MATERIAL OF $84000 AND 18-0268465-00 (2000) LAND SERVICES FOR LPP PROJECT APPROV $45000 FROM PROJECT MANAGEMENT AND GTMR GROUPS.
21026115700 | INSTALL 300' OF 2"PMMP MAIN | [5 empty] | 21541.85 | 22097.6064 | -555.7564 |  |  |  | 2021-09-28
21026117800 | RETIRE 117' - 4" PLP | [5 empty] | 11604.62 | 9954.0712 | 1650.5488 |  |  |  | 2021-06-28 | ABN 102' OF 040 PL ML. TESTED 4' OF 040 W/ END CAPS FOR 1 HR @ 90# SOAP TESTED CONN PTS @ 11" WC. SOAP TESTED ALL TEE CAP AND END CAPS @ OP.
21026117900 | INSTALL 575' OF 2"PMIP MAIN | [5 empty] | 15668.74 | 17428.325 | -1759.585 |  |  |  | 2021-06-09 | TWALKER/KY 06-28-21: THIS 555 WAS COMPLETED IN THE FIELD BUT PAPERWORK NOT COMPLETED OR MAPPED WHEN A CONTRACTOR DAMAGED A SECTION OF THIS NEW GAS MAIN. ALL WORK AND COST INCLUDED IN THIS JOB ORDER AND THE REASON FOR TWO TIE IN PLANS AND TEST FORMS.
21026118300 | INSTALL 210' OF 2"PMMP MAIN | [5 empty] | 17888.9 | 16739.4681 | 1149.4319 |  |  |  | 2021-09-09
21026118500 | RETIRE 3,256' 10"-3" CS/BS/PLP | [5 empty] | 42.9 | 151.2005 | -108.3005 |  |  |  | 2021-12-20
21026118600 | INSTALL 600' OF 2"PMMP MAIN | [5 empty] | 65051.29 | 37159.65 | 27891.64 |  |  |  | 2021-07-13
21026118700 | EMER-INSTALL 2' OF 2"PMMP MAIN | [5 empty] | 2106.1 | 4434.6174 | -2328.5174 |  |  |  | 2021-04-29 | REFERENCE JOB# 21906644500 FOR COMMENTS AND JOB INFO DMARSTO 4/27/21
21026118800 | EMER-RETIRE 2' OF 2"PAMP MAIN | [5 empty] | 755.09 | 78.808 | 676.282 |  |  |  | 2021-04-29 | REFERENCE JOB# 21906644500 FOR COMMENTS AND JOB INFO DMARSTO 4/27/21
21026120700 | RETIRE REG STATION 1002 | [5 empty] | 6481.89 | 5235.8425 | 1246.0475 |  |  |  | 2021-12-27 | CC# 48634 CMCOX 12/15/21 STATION RETIRED BY CHRIS COX AND CONSTRUCTION SERVICES PAPERWORK COMPLETED BY CYNTHIA FARIS ON 12/27/21
21026120800 | RETIRE HP/MP RUN-1 OF R-1035 | [5 empty] | 827.14 | 21706.5276 | -20879.3876 |  |  |  | 2021-11-29 | HP TO MP RUN 1 HAS BEEN RETIRED AND LP RUN 2 HAS BEEN PLACED BACK INTO SERVICE WORKED COMPLETED ON 11/3/2021 BY CHRIS COX PAPERWORK COMPLETED BY CYNTHIA FARIS ON 11/29/2021 GCCC TICKET NOT REQUIRED ON 11/29/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026122000 | INSTALL 2150' OF 2"PMMP MAIN | [5 empty] | 178403.1 | 162365.3384 | 16037.7616 |  |  |  | 2022-06-28
21026122200 | INSTALL 925' OF 2"PMMP MAIN | [5 empty] | 41992.33 | 32784.4942 | 9207.8358 |  |  |  | 2021-06-09 | TWALKER/KY 06-28-21: THIS 555 PROJECT WAS COMPLETED IN FIELD BUT PAPERWORK NOT SUBMITTED TO CLOSE OR MAPPEND WHEN LEAK ON THE NEW MAIN WAS DETECTED. WE BELIEVE THE MAIN LINE WAS DAMAGED DURING BACK FIELD. LEAK WAS REPAIRED BY CONSTRUCTION THAT IS REASON FOR TWO TIE IN PLANS AND TEST FORMS.ALL COST AND WORK CAPTURED UNDER THIS JOB ORDER.
21026122500 | EMER-INSTALL 5' OF 4"PMLP MAIN | [5 empty] | 9606.89 | 6150.5343 | 3456.3557 |  |  |  | 2021-05-11 | CONTRACTOR HIT 040 PLASTIC MAIN WITH EXCAVATOR. SQUEEZED OFF TO MAKE SAFE. REPLACED 5FT OF 040 P LP. TESTED MAIN FOR 20MINS AT 90LBS.TEST OK.SOAP TEST FINAL TIE INS AT OP. TEST OK.BHB NGF.WORKED WITH CAPITAL JO AND TIE IN PLAN TWALKER/KY 06-28-21: THIS PROJECT WAS GENERATED FROM 3RD PARTY DAMAGE FROM A CONTRACTOR REPLACING STORM/SEWER AT THE INTERSECTION OF MILLER AND 2ND ST. CONTRACTOR DAMAGE SMALL OF MAIN FIRST DAY AND THE VERY NEXT DAY HIT/DA MAGE THE REPAIR MAIN. THAT MAIN WAS NEVER BOOKED OR MAPPED IN WMS. ALL WORK AND COST CAPTURED ON THIS JOB ORDER. WE HAVE TWO TIE INS AND TEST.
21026122600 | EMER-RETIRE 5' OF 4"PMLP MAIN | [5 empty] | 19.8 | 78.808 | -59.008 |  |  |  | 2021-05-11 | CONTRACTOR HIT 040 PLASTIC MAIN WITH EXCAVATOR. SQUEEZED OFF TO MAKE SAFE. REPLACED 5FT OF 040 P LP. TESTED MAIN FOR 20MINS AT 90LBS.TEST OK.SOAP TEST FINAL TIE INS AT OP. TEST OK.BHB NGF.WORKED WITH CAPITAL JO AND TIE IN PLAN
21026122700 | EMEG-INSTALL 5' OF 4"PMMP MAIN | [5 empty] | 3856.8 | 5607.5343 | -1750.7343 |  |  |  | 2021-05-18 | RESPONDED OT MAIN LINE DAMAGE. INSTALLED 2' OF 4" PE MAIN LINE. PRESSURE TESTED MAIN @ 90PSIG FOR 20MINS PER FOL APPROVAL. TEST OK. SOAP TESTED LAST CONNECTION @ OP. TEST OK. CONTENT VERIFIED. PRESSURE VERIFIED @ 52PSIG DMAL
21026122800 | EMER-RETIRE 5' OF 4"PMMP MAIN | [5 empty] | 210.25 | 78.808 | 131.442 |  |  |  | 2021-05-18 | RESPONDED TO MAIN LINE DAMAGE. INSTALLED 2' OF 4" PE MAIN LINE. PRESSURE TESTED MAIN @ 90PSIG. FOR 20MINS PER FOL APPROVAL. TEST OK. SOAP TESTED FINAL CONNECTION @ OP. TEST OK. CONTENT VERIFIED. VERIFIED PRESSURE @52PSIG
21026122900 | INSTALL 8" SS | [5 empty] | 48788.62 | 30904.4019 | 17884.2181 |  |  |  | 2021-07-30
21026124400 | EMER-INSTALL 2' OF 2"PMMP | [5 empty] | 1470.21 | 2935.5264 | -1465.3164 |  |  |  | 2021-06-30
21026124500 | EMER-RETIRE 2' OF 2"PMMP | [5 empty] | 0 | 85.0408 | -85.0408 |  |  |  | 2021-06-30
21026124600 | INSTALL 3" OUTLET VALVE | [5 empty] | 28606.82 | 34892.3468 | -6285.5268 |  |  |  | 2021-07-19
21026124700 | RETIRE 4' OF 3"BSIP MAIN | [5 empty] | 0 | 86.5975 | -86.5975 |  |  |  | 2021-07-19
21026124800 | INSTALL INLET/OUTLET BLOCK VLV | [5 empty] | 20343.89 | 13873.2524 | 6470.6376 |  |  |  | 2021-07-19 | CCC# 30839 CCC# 31113 CCC# 31169 IN PROGRESS CCC# 31169 CC# 31169 CC-31326 CC-31492 CCC# 31755 CC-31755 NOT ON SITE- OFFICE ISO UPDATE CAP WORK COMPLETED BY WADE SHIMFESSEL ON 7/19/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/21/20 GCCC TICKET NOT REQUIRED ON 7/21/20 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS 7/21/20
21026125400 | INSTALL 28' 4" PMMP | [5 empty] | 20147.11 | 10969.2814 | 9177.8286 |  |  |  | 2021-06-15
21026125500 | RETIRE 20' OF 4" PMMP | [5 empty] | 0 | 91.2676 | -91.2676 |  |  |  | 2021-06-15
21026125600 | INSTALL 28' 8" PMLP | [5 empty] | 23277.54 | 11805.2814 | 11472.2586 |  |  |  | 2021-06-15
21026125700 | RETIRE 20' 8" PMLP | [5 empty] | 71.35 | 91.2676 | -19.9176 |  |  |  | 2021-06-15
21026125800 | REPLACE C18-5 E | [5 empty] | 96855.51 | 77241.44 | 19614.07 |  |  |  | 2021-07-30
21026125900 | RETIRE C18-5 | [5 empty] | 38.57 | 91.2676 | -52.6976 |  |  |  | 2021-07-30
21026126102 | INSTALL 2000' OF 2"PMMP MAIN | [5 empty] | 169255.42 | 165212.1661 | 4043.2539 |  |  |  | 2022-08-02
21026126200 | RETIRE 270' OF 1"BSHP MAIN | [5 empty] | 0 | 63.0891 | -63.0891 |  |  |  | 2022-08-02
21026126600 | RETIRE REG STATION #1181 | [5 empty] | 1370.38 | 4088.2989 | -2717.9189 |  |  |  | 2022-04-29 | RWILLIAMS COMPLETED PAPER WORK, EBLANTON RETIRED STATION ON 04/29/2022
21026126700 | INSTALL 350' OF 2" PMMP | [5 empty] | 99374.93 | 123612.3972 | -24237.4672 |  |  |  | 2022-05-09
21026126800 | INSTALL 11,170' OF 2"/6"PMMP | [5 empty] | 1675598.92 | 1492284.9718 | 183313.9482 |  |  |  | 2022-10-10
21026126900 | RETIRE 9000' OF 4"/6"BSLP MAIN | [5 empty] | 24.95 | 62.0792 | -37.1292 |  |  |  | 2022-10-10
21026128000 | INSTALL 265' OF 4" PMLP | [5 empty] | 96077.32 | 71153.2979 | 24924.0221 |  |  |  | 2022-03-10 | AWEBER - JO RAN OVER ESTIMATE DUE TO UNFORSEEN 8'X5' STORM BASIN @ 42" BELO W GRADE. EXCAVATION OF TOP OF BASIN OCCURRED TO PROVIDE REROUTE OF 4" PMMP INSTALL AT ACCEPTABLE DEPTH WITHOUT CROSSBORE.
21026128100 | RETIRE 230'-4" & 50'-6" PMLP | [5 empty] | 71.35 | 354.2624 | -282.9124 |  |  |  | 2022-03-10
21026128601 | INSTALL 700' OF 2"PMMP MAIN | [5 empty] | 75716.28 | 57445.0039 | 18271.2761 |  |  |  | 2021-10-13
21026128700 | RETIRE HP/MP REG RUN | [5 empty] | 3741.83 | 4148.6042 | -406.7742 |  |  |  | 2021-11-18 | HP/MP RUN RETIRED BY CHRIS COX ON 11/9/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 11/18/2021 GCCC TICKET NOT REQUIRED ON 11/18/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026128802 | INSTALL 470' OF 4"PMMP MAIN | [5 empty] | 106230.58 | 96528.8129 | 9701.7671 |  |  |  | 2022-05-25
21026128900 | RETIRE 440' OF 4"BSMP MAIN | [5 empty] | 30.93 | 67.1085 | -36.1785 |  |  |  | 2022-06-30 | X
21026129000 | RETIRE 680'-4"BSLP MN -D247885 | [5 empty] | 0 | 67.1085 | -67.1085 |  |  |  | 2022-05-25
21026129400 | RETIRE 135' OF 8"CSMP MAIN | [5 empty] | 1142.2 | 151.2005 | 990.9995 |  |  |  | 2021-09-01 | ABN 135' ON CS MP MAIN.
21026129500 | RETIRE 109' OF 4"BSLP | [5 empty] | 71.35 | 99.3208 | -27.9708 |  |  |  | 2021-09-03 | ABN 4" BS LP MAIN PER GS
21026129600 | INSTALL 100' OF 8"PMMP MAIN | [5 empty] | 152586.55 | 99233.0142 | 53353.5358 |  |  |  | 2021-11-19 | TWALKER/KY 01-24-23: JOB ORDER OVER RUN DUE TO ADDITIONAL FLAGGING ADDED $50,000 TO CONTRACT COST, SEGA INCREASED BY $6,000 AND CO LABOR COST HIGHER BY $14,000 LEVEL 2 VARIANCE ADDED TO WMS.DOCS.
21026129700 | RETIRE 20' OF 8"BSMP MAIN | [5 empty] | 1960.6 | 79.203 | 1881.397 |  |  |  | 2021-11-19
21026129900 | RETIRE PIT REG STATION W/AMRP | [5 empty] | 3639 | 4706.4362 | -1067.4362 |  |  |  | 2022-11-16 | RETIRED 800 PRESS AVE 200340, CMCHOLAN 11-16-22
21026130600 | INSTALL 350' OF 2"PMMP MAIN | [5 empty] | 42649.02 | 31312.2411 | 11336.7789 |  |  |  | 2021-08-17
21026130902 | INSTALL 5150' OF 2"/4" PMMP | [5 empty] | 192645.27 | 202239.5285 | -9594.2585 |  |  |  | 2022-04-08
21026132400 | INSTALL 225' OF 2"PMMP | [5 empty] | 85412.94 | 79492.8479 | 5920.0921 |  |  |  | 2022-11-17 | TTALKER/KY 01-25-23: JOB IS SHOWING COST UNDER RUN AT THIS TIME BUT PAVING/ STREET REPAIRS NOT TAKE PLACE UNTIL SPRING/WARM WEATHER. TWALKER/KY 06-23-23: JOB ORDER CURRENTLY UNDER RUNNING $32000 BUT STREET PAVING HAS NOT BEEN COMPLETED AT THIS TIME DUE TO DOWNTOWN AREA AND CONSTRU CTION BY OTHERS IN AREA. TWALKER/KY 07-21-23: PAVING HAS BEEN COMPLETED AND COST APPLIED TO JOB ORDE R, NOT OVER OR UNDER BUDGET VARIANCE REQUIRED AT THIS TIME. PAVING WAS DELAYED TO COLD AND WET WEATHER PLUS THIS PROJECT IS LOCATED IN DOWNTOWN AREA SO PERMIT RESTRICTION APPLIED.
21026132500 | INSTALL 450' OF 2"PMMP MAIN | [5 empty] | 31237.4 | 32348.6064 | -1111.2064 |  |  |  | 2021-10-06
21026134100 | INSTALL 850' OF 2"PMMP MAIN | [5 empty] | 28285.71 | 40949.6064 | -12663.8964 |  |  |  | 2021-10-21
21026134800 | INSTALL 20'-2" PMMP | [5 empty] | 67370.23 | 39141.4028 | 28228.8272 |  |  |  | 2022-01-12
21026134900 | RETIRE 16'-2" CSMP | [5 empty] | 0 | 88.8156 | -88.8156 |  |  |  | 2022-01-12
21026136100 | EMER-INSTALL 10'-2" PMMP | [5 empty] | 3664.07 | 5241.7163 | -1577.6463 |  |  |  | 2021-08-10
21026136200 | EMER-RETIRE 10'-2" PMP | [5 empty] | 253.41 | 88.8156 | 164.5944 |  |  |  | 2021-08-10 | RETIRED 2' OF DAMAGED 2" PMP MAIN
21026136500 | RELOCATE 12' OF 4"PMLP MAIN | [5 empty] | 25628.84 | 10466.234 | 15162.606 |  |  |  | 2021-08-18
21026136600 | RETIRE 6' OF 4"PMLP MAIN | [5 empty] | 0 | 85.7248 | -85.7248 |  |  |  | 2021-08-18
21026136800 | EMER-INSTALL 5' OF 4"PMMP | [5 empty] | 395.9 | 5949.1348 | -5553.2348 |  |  |  | 2021-08-24 | INST 5' 4" P MP MAIN ACCORDING TO ENGINEERED TIE-IN PLAN AND GAS STANDARDS. WORKED ON 8/17/21. MCRAIG 8/24/21
21026136900 | EMER-RETIRE 5' OF 4"PAMP | [5 empty] | 5438.98 | 55.634 | 5383.346 |  |  |  | 2021-08-24 | ABN 5' 4"P MP MAIN ACCORDING TO ENGINEERED TIE-IN PLAN. WORKED ON 8/17/21. MCRAIG 8/24/21
21026137100 | RETIRE 4'-8" BSLP | [5 empty] | 0 | 177.6312 | -177.6312 |  |  |  | 2021-08-18
21026137500 | INSTALL SOLAR PANEL | [5 empty] | 3598.81 | 4862.234 | -1263.424 |  |  |  | 2021-10-13 | CC# 41497 RHAYES 10-13-2021 RHAYES 10-13-2021 CHANGED ER350 FROM CRY IN TO FULL TIME MONITOR INSTALLED SUPER SOLAR KIT AN D RV 50 MODEM CCOX 10-13-2021
21026140400 | INSTALL 2800' OF 2"/4"PMMP | [5 empty] | 116146.05 | 86592.9986 | 29553.0514 |  |  |  | 2022-03-04
21026140901 | INSTALL 2750' OF 2"PMMP MAIN | [5 empty] | 104070.68 | 96941.3864 | 7129.2936 |  |  |  | 2022-04-15
21026141200 | EMER-INSTALL 3'OF 6"PMLP MAIN | [5 empty] | 5901.09 | 4022.0999 | 1878.9901 |  |  |  | 2021-09-15
21026141300 | EMER-RETIRE 3' OF 6"PLP MAIN | [5 empty] | 38.15 | 69.8875 | -31.7375 |  |  |  | 2021-09-13
21026141400 | INSTALL 130'-6" PMMP | [5 empty] | 179014.36 | 140177.264 | 38837.096 |  |  |  | 2022-02-15 | PROJECT OVERRUN OF $38,555 (28%) DUE TO ADDITIONAL TIME AND RESOURCES BEING REQUIRED. LABOR HOURS ESTIMATED AT 176 HRS, BUT 319 HRS WERE REQUIRED ($11 ,052 DIFF. LABOR RATE ESTIMTES TOO LOW). NEW CONTRACT WILL ADDITIONAL UNITS WAS USED WHICH ADDED $57,948. BUT THERE WERE SAVINGS OF $30,000 IN THE OT HER CATAGORY, WHICH WERE COVERED WITH UNITS IN THE UPDATED CONTRACT. D.LEMO NS 7/8/2022
21026141500 | RETIRE 316'-6" PM&CS MP | [5 empty] | 4123.73 | 76.2083 | 4047.5217 |  |  |  | 2022-02-15
21026141600 | INSTALL 320' OF 2"PMMP MAIN | [5 empty] | 51396.03 | 52296.0917 | -900.0617 |  |  |  | 2021-12-28
21026141700 | RETIRE 315' OF 2"PMP MAIN | [5 empty] | 46.05 | 60.6987 | -14.6487 |  |  |  | 2021-12-28
21026142200 | INSTALL 575' OF 2"PMMP MAIN | [5 empty] | 25446.02 | 20915.4686 | 4530.5514 |  |  |  | 2021-11-02
21026142500 | EMER-INSTALL 5' OF 2"PMMP | [5 empty] | 417.14 | 3297.6583 | -2880.5183 |  |  |  | 2021-09-20
21026142600 | EMER-RETIRE 5' OF 2"PMP MAIN | [5 empty] | 263.29 | 69.8875 | 193.4025 |  |  |  | 2021-09-20
21026143000 | RETIRE EME FACILITY | [5 empty] | 0 | 63.4597 | -63.4597 |  |  |  | 2021-10-04 | REPLACED EFC
21026143400 | EMER-INSTALL 10'OF 4"PMIP MAIN | [5 empty] | 7913.03 | 7432.5408 | 480.4892 |  |  |  | 2021-09-27
21026143500 | EMER-RETIRE 10' OF 4"PAIP MAIN | [5 empty] | 0 | 60.6987 | -60.6987 |  |  |  | 2021-09-27
21026143900 | EMER-INSTALL 5'-2"PMMP | [5 empty] | 0 | 6000.6188 | -6000.6188 |  |  |  | 2021-10-25
21026144000 | EMER-RETIRE 5'-2"PMMP | [5 empty] | 0 | 49.6987 | -49.6987 |  |  |  | 2021-10-25
21026144100 | INSTALL 350' OF 2"PMIP MAIN | [5 empty] | 19720.01 | 20004.6217 | -284.6117 |  |  |  | 2021-10-27
21026144200 | RETIRE 4280' OF 2"/3"PAMP MAIN | [5 empty] | 41269.58 | 14091.9275 | 27177.6525 |  |  |  | 2021-11-17 | ABN 4280' P MP MAIN IN ACCORDNANCE WITH ENGINEERED TIE-IN PLAN AND GAS STANDARDS. SOAP TEST FINAL TIE-IN AT OP OK. BHB NGF. MCRAIG 10/13/21 TWALKER/KY 11-24-21: WMS WOULD NOT ALLOW FOR REVISION DUE TO UNPAID INVOICES, JOB ORDER OVER RUN DUE TO SCOPE OF WORK INCREASED AND WE RETIRED MORE UNLOCATED FIRST GENERATION PLASTIC MAIN THAN PLANNED AND SOME NEW EMPLOYEES WORKED WITH CREWS WITH INCREASED LABOR COST BY $14,000 OVER ESTIMATE
24026329700 | EMER - 2'-2" PMMP | [5 empty] | 8583.87 | 8686.5178 | -102.6478 | 2024-01-01 | 2024-12-31 | 2024-03-14 | 2024-03-14
21026145700 | RETIRE 1840' OF 4" BSMP | [5 empty] | 110 | 100.2728 | 9.7272 |  |  |  | #N/A | JOB COMPLETE
21026146000 | INSTALL 404'-4"&6"PMMP | [5 empty] | 125105.39 | 224207.9887 | -99102.5987 |  |  |  | 2021-12-16 | LEVEL 2 BUDGET VARIANCE EXPLANATION FORM HAS BEEN APPROVED AND LOADED INTO WMSDOCS WORKSPACE. D.LEMONS 3/3/2022
21026146100 | RETIRE 427'-4"BSLP | [5 empty] | 1537.36 | 63.4597 | 1473.9003 |  |  |  | 2021-12-16
21026147100 | EMER-INSTALL 6' OF 4"PMMP | [5 empty] | 604.21 | 1045.4141 | -441.2041 |  |  |  | 2021-10-25
21026147200 | EMER-RETIRE 6' OF 4"PAMP MAIN | [5 empty] | 38.59 | 49.6987 | -11.1087 |  |  |  | 2021-10-25
21026147900 | EMER - INSTALL 5'-4" PMLP | [5 empty] | 3691.18 | 2422.8089 | 1268.3711 |  |  |  | 2021-11-17 | INSTALLED 3FT OF 040 PLASTIC DUE TO 3 TEE'S BEING AN AOC. ALL TESTING INFO ON JO 21026147900 AND 21026148000 IN WMS DOCS.
21026148000 | EMER - RETIRE 5'-4" PLP | [5 empty] | 4.38 | 66.2207 | -61.8407 |  |  |  | 2021-11-17 | INSTALLED 3FT OF 040 PLASTIC DUE TO 3 TEE'S BEING AN AOC. ALL TESTING INFO ON JO 21026147900 AND 21026148000 IN WMS DOCS.
21026148100 | EMER-INSTALL 4' OF 2"HPHP MAIN | [5 empty] | 2019.57 | 7370.71 | -5351.14 |  |  |  | 2022-01-24
21026148200 | EMER-RETIRE 4' OF 2"HDHP MAIN | [5 empty] | 0 | 60.6987 | -60.6987 |  |  |  | 2022-01-24
21026151200 | INSTALL 2065'-2"&6" PMMP | [5 empty] | 493527.08 | 333722.7132 | 159804.3668 |  |  |  | 2022-10-17
21026151300 | RETIRE 2111'-2"&6" CSMP | [5 empty] | 80 | 109.7476 | -29.7476 |  |  |  | 2022-10-17
21026151500 | EMER-INSTALL 10' OF 4"PMMP | [5 empty] | 210.64 | 5220.9567 | -5010.3167 |  |  |  | 2021-11-24 | LEAK ON SF CPLG ON TEE OF SVC TO 3102 KIRKLEVINGTON DR. DPI D221947 CLEARED ON 2212. ABN/INST 3'- 4" P MAIN ACCORDING TO GAS STANDARDS AND ENGINEERED TIE-IN PLAN. WORKED 11/17/21 MCRAIG
21026151600 | EMER-RETIRE 10' OF 4"PAMP | [5 empty] | 24.42 | 64.6591 | -40.2391 |  |  |  | 2021-11-24 | LEAK ON SF COUPLING ON TEE TO SVC OF 3102 KIRKLEVINGTON DR. DPI D221947 CLEARED ON 2212. ABN/ INST 3'- 4" P MAIN ACCORDING TO GAS STANDARDS AND ENGINEERED TIE-IN PLAN. WORKED 11/17/24 MCRAIG
24026331100 | EMER - INSTALL ~5'-2" PMMP | [5 empty] | 523.81 | 3498.146 | -2974.336 | 2024-01-01 | 2024-12-31 | 2024-02-29 | 2024-02-29
21026152200 | RETIRE 457' OF 6 5/8"BSHP MAIN | [5 empty] | 1859.99 | 74.2578 | 1785.7322 |  |  |  | #N/A
21026155900 | INSTALL 2400' OF 2"PMMP MAIN | [5 empty] | 72846.65 | 61211.3642 | 11635.2858 |  |  |  | 2022-02-10
21026156700 | INSTALL 20'-3 PMMP | [5 empty] | 13109.07 | 12546.0469 | 563.0231 |  |  |  | 2022-07-25
21026156800 | ABDN CB 12'-3" PMP | [5 empty] | 0 | 73.9724 | -73.9724 |  |  |  | 2022-08-01
21026156900 | INSTALL 10'-6" PMLP | [5 empty] | 6980.82 | 14786.2791 | -7805.4591 |  |  |  | 2022-07-21 | INSTALLATION COMPLETE, HMCKUNE
21026157000 | RETIRE 10'-6" PMLP | [5 empty] | 0 | 72.8047 | -72.8047 |  |  |  | 2022-04-20
21026993800 | INSTALL 7200' OF 2"/6"PMMP | [5 empty] | 3013391.75 | 2229015.8617 | 784375.8883 |  |  |  | 2022-12-09
21026993900 | RETIRE 9500' OF 4"CI/6"BSLP MN | [5 empty] | 5876.52 | 80.3582 | 5796.1618 |  |  |  | 2022-12-09 | ABANDONED ALL MAINS IN SCOPE OF PROJECT
21026994000 | INSTALL 10930 - 2"/4"PMMP MAIN | [5 empty] | 1681569.14 | 1953601.844 | -272032.704 |  |  |  | 2022-11-16 | TWALKER/KY 05-22-23: PROJECT CURRENTLY UNDER RUNNING, WAITING ON FINAL RESTORATION/PAVING TO DETERMINE IF ADDITIONAL EXPLAINATION OR VARIANCE REQU IRED. TWALKER/KY 06-23-23: JOB UNDER RUNNING DUE TO PAVING/HARD SURFACES REPAIRS HAVE NOT BEEN FULLY COMPLETED. TWALKER/KY 07-24-23: PAVING/HARD SURFACE REPAIRS STILL IN PROGRESS TWALKER/KY 08-29-23: LEVEL 1 VARIANCE FORM ADDED IN WMS.DOCS NOT SURE IF ALL PAVING INVOICES HAVE BEEN PAID BUT COST UNDER RUN DRIVEN BY LESS PAVING COST BY PAVING CONTRACTOR INSTEAD OF PIPELINE CO.
21026994100 | RETIRE 14,600 - 4"CI/BSLP MAIN | [5 empty] | 269.51 | 84.1794 | 185.3306 |  |  |  | 2022-11-23
21026994600 | EMER INSTALL 5'-4" PMMP | [5 empty] | 4622.23 | 5854.5805 | -1232.3505 |  |  |  | 2021-01-11 | REPLACED 5 FT MAIN TEST 90 LB FOR 20 MIN TEST ALL TEES AT 5 MIN TEST BYPASS 90 LB FOR 1 HR TEST ALL END CAPS AT OP FOR 5 MIN BAR HOLE BANKS NO GAS FOUND MARKER BALL AT TEES AND CPLG
21026994700 | EMER - RETIRE 5'-4" PMP | [5 empty] | 102.95 | 103.8156 | -0.86559 |  |  |  | 2021-01-11 | CUT OUT CRACKED MAIN PUT ON BYPASS AND PUT IN 5 FT OF MAIN
21026996200 | INSTALL 2150'-2" PMMP | [5 empty] | 336530.83 | 214604.887 | 121925.943 |  |  |  | 2021-03-05 | JOB ORDER CODED COMPLETE AT TIME OF MAIN LINE COMPLETION, STILL WORKING ON SERVICES. SPENDLE 3/10/21 20APR21: SEVERAL ATTEMPTS WERE MADE TO REVISE THIS JOB ORDER TO CAPTURE OVERRUN, HOWEVER, OUTSTANDING INVOICES PREVENTED ENGINEERING FROM DOING SO. . 29APR21: OVERRUN EXPLANATION = FISHEL'S CONTRACT OVER $21K DUE TO INCREASED LABOR & MATERIALS TO PREP STAGING (STONE, FENCING, AND ENVIRONMENTAL BMPS) ALONG WITH A LOT MORE FLAGGING BY AWP FOR TRAFFIC CONTROL. BUCHANAN'S COST FOR SEWER INSPECTION & CAMERING WAS WAY UNDERESTIMATED CONTRIBUTING ANOTHER $33K TO THE OVERRUN. LASTLY, COMPANY LABOR OVERRAN BY $14K FROM WHAT WAS ORIGINALY ESTIMATED. THESE COSTS PLUS OH'S MAKE UP THE OVERRUN (BKSLONE).
21026996400 | EMER - ABANDON 37'-2" PIP | [5 empty] | 860.91 | 2872.6664 | -2011.7564 |  |  |  | 2021-01-25 | ABANDONED 37' OF 020 MAIN DUE TO FAC DAM. WORKED WITH TIE IN PLAN. INSTALLED LINE MARKER AT EOM. UPDATED MAPPING. SOAP TEST END CAP AT OP.TEST OK. BHB NGF.
21026997000 | INSTALL 1100'-2" PMP | [5 empty] | 532822.99 | 340896.6283 | 191926.3617 |  |  |  | 2021-04-27 | 14JUN21: UNDERRUN EXPLANATION = 1) ASPHALT MILL & OVERLAY WAS MISCALCULATED RESULTING IN AN ADDITIONAL $120K AND 2) FLAGGING TIME WAS UNDERESTIMATED RESULTING IN AND ADDITIONAL $35K. THESE COSTS, ALONG WITH ASSOCIATED OH'S, MAKE UP THE MAJORITY IF THE $166K OVERRUN. THE ERROR IN PAVING COSTS WAS NOT NOTICED UNTIL AFTER THE ORIGINAL JOB ORDER WAS EXECUTED THEREBY PROHIBITING PROCESSING A REVISION (BKSLONE).
21026997101 | INSTALL 125' OF 4"PMMP MAIN | [5 empty] | 118779.98 | 111178.7891 | 7601.1909 |  |  |  | 2021-08-30
21026997801 | INSTALL 4600' OF 2"/6"PMMP | [5 empty] | 2405348.07 | 2229421.3209 | 175926.7491 |  |  |  | 2023-10-19
21026997900 | RETIRE 6300' OF 4"/6"CILP MN | [5 empty] | 747.19 | 126.9534 | 620.2366 |  |  |  | 2023-10-19
21026998000 | CONVERT TO GMB ACCOUNT | [5 empty] | 6412.15 | 4845.4443 | 1566.7057 |  |  |  | 2021-04-07 | CONVERTED FROM CAB TO GMB ACCOUNT CCC TICKET NOT REQUIRED THIS IS NON-SCADA MONITORED
21026998100 | INSTALL 180' OF 2"PMMP MAIN | [5 empty] | 36764.99 | 11159.7406 | 25605.2494 |  |  |  | 2021-02-26
21026998900 | RETIRE 3"PLP SERVICE LINE | [5 empty] | 9085.7 | 9329.0565 | -243.3565 |  |  |  | 2022-09-20
21026999500 | INSTALL 175' OF 2"PMMP | [5 empty] | 16309.78 | 9497.8185 | 6811.9615 |  |  |  | 2021-05-03 | 174 '2"PLASTIC MED -DENSITY YELLOW PIPE INSTALLED BY BIRECTIONAL BOREBY STA NLEY PIPELINE.
21026999600 | INSTALL 90' OF 4"CS/PMMP MAIN | [5 empty] | 47302.77 | 68922.5327 | -21619.7627 |  |  |  | 2021-11-11 | NEW MAIN GASED UP 11-11-21
22026158400 | INSTALL 1200' OF 2"PMMP MAIN | [5 empty] | 29132.57 | 35742.3291 | -6609.7591 |  |  |  | 2022-03-18
22026158800 | INSTALL 540' OF 4"/8"PMMP MAIN | [5 empty] | 378932.24 | 262444.8259 | 116487.4141 |  |  |  | 2023-03-03 | TWALKER/KY 09-27-23: LEVEL 1 VARIANCE FORM ADDED TO WMS.DOCS JOB OVER RUN DUE TO ADDITIONAL PAVING/RESTORATION REQUIREMENT BY THE CITY INCREASED CONTRACT COST BY $30,000, ALSO SEGA $12,000 HIGHER THAN ESTIMATE. COMPANY LABOR INCREASED BY $25,000 DUE TO ADDITIONAL COMPANY LABOR REQUIRED. TWALKER/KY 10-27-23: LEVEL 2 VARIANCE REPORTED ADDED TO WMS.DOCS, JOB OVER DUE TO CITY PAVING AND RE-PAVING REQUIREMENT.
22026158900 | RETIRE 594' OF 8"BSMP MAIN | [5 empty] | 0 | 72.8047 | -72.8047 |  |  |  | 2023-03-03
22026160800 | EMER-INSTALL 5' OF 2"PMMP MAIN | [5 empty] | 2109.29 | 3947.9695 | -1838.6795 |  |  |  | 2022-01-12
22026160900 | EMER-RETIRE 5' OF 2"PAMP MAIN | [5 empty] | 0 | 69.6571 | -69.6571 |  |  |  | 2022-01-12
22026162000 | RETIRE 110' OF 2"CSHP MAIN | [5 empty] | 716.93 | 105.0102 | 611.9198 |  |  |  | 2022-06-28
22026162102 | INSTALL 8150' OF 2"/4"PMMP | [5 empty] | 756346.06 | 751182.165 | 5163.895 |  |  |  | 2023-11-30
22026162200 | RETIRE 4600' OF 4"/6"BSLP MAIN | [5 empty] | 1442.96 | 105.0102 | 1337.9498 |  |  |  | 2023-11-30
22026162500 | INSTALL 8" STOPPLE FITTING | [5 empty] | 25751.7 | 14352.6857 | 11399.0143 |  |  |  | 2022-02-10
22026162600 | RETIRE 44' OF 8"BSMP MAIN | [5 empty] | 0 | 105.0102 | -105.0102 |  |  |  | 2022-02-10
22026163200 | INSTALL 775' OF 2"PMMP MAIN | [5 empty] | 49762.97 | 80533.8181 | -30770.8481 |  |  |  | 2023-03-17 | TWALKER/KY- 09-27-23: LEVEL 1 VARIANCE ADDED TO WMS.DOCS JOB UNDER RUN WAS DUE TO NO FLAGGING OR STREET REPAIRS REQUIRED SINCE ALL MAIN WAS INSTALLED BY DIRECTIONAL BORE WHICH LOWER CONTRACT COST $23,000
22026163300 | RETIRE 800' OF 4"BSLP MAIN | [5 empty] | 21.45 | 105.0102 | -83.5602 |  |  |  | 2023-03-17
22026163700 | RETIRE 4"BSLP SERVICE LINE | [5 empty] | 1327.16 | 105.0102 | 1222.1498 |  |  |  | 2022-04-08 | CAPITAL SERVICE LINE WAS ABANDONED WITH JOB NUMBER 18-0268433-01 TIE IN A1A2. LSHARON
22026164400 | EMER - INSTALL 10'-2" PMMP | [5 empty] | 10363.46 | 13748.6188 | -3385.1588 |  |  |  | 2022-02-08
22026164500 | EMER - RETIRE 10'-2" PMP | [5 empty] | 111.44 | 109.7476 | 1.6924 |  |  |  | 2022-02-08
22026164900 | EMER-INSTALL 4' OF 3"PMMP MAIN | [5 empty] | 15536.92 | 14982.0392 | 554.8808 |  |  |  | 2022-02-17 | INSTALLED 4' OF 030 P DUE TO EXC DMG TEST AT 90# FOR 20 MIN PER FOL APPROVA L, SOAP TEST TWO 030 EF CPLGS AT OP FOR 5 MIN OK. TEST FOR SEC DMG OK. WHIMES 02/17/2022
22026165000 | EMER-RETIRE 4' OF 3"PMP MAIN | [5 empty] | 119.3 | 100.2728 | 19.0272 |  |  |  | 2022-02-17 | COMPLETED W/ JO 22026164900
22026165400 | RETIRE REG STATION #1203 | [5 empty] | 5686.24 | 4576.607 | 1109.633 |  |  |  | 2022-06-22 | STATION RETIRED ALL PIPEING REMOVED 06-22-2022 AJPARKS
24026331900 | EMER - INSTALL 1' OF 2"PMMP | [5 empty] | 3472.1 | 3799.146 | -327.046 | 2024-01-01 | 2024-12-31 | 2024-04-02 | 2024-04-02 | REPAIRED DAMAGES SECTION OF PIPE. TEST REPAIR PIECE 90#20MINS, TG. ST LTI, TG. TEST FOR SECONDARY DAMAGE OK. R.CRAWFORD 4-2-24
22026165600 | RETIRE 2715'-BSLP & 425'-PLP | [5 empty] | 1766 | 75.4968 | 1690.5032 |  |  |  | #N/A
22026166200 | INSTALL 20' OF 3"PMMP MAIN | [5 empty] | 23237.34 | 28323.8584 | -5086.5184 |  |  |  | 2022-05-04
22026166300 | RETIRE 12' OF 3"PMP MAIN | [5 empty] | 90.73 | 62.3079 | 28.4221 |  |  |  | 2022-05-05
22026166900 | INSTALL 2010' - 8" & 6" PMMP | [5 empty] | 525084.39 | 400337.2549 | 124747.1351 |  |  |  | 2023-12-19
22026167000 | RETIRE 2260' OF 4-8" BSLP | [5 empty] | 0 | 89.0305 | -89.0305 |  |  |  | 2023-12-19
22026167200 | INSTALL 720'- 4" PMMP | [5 empty] | 293269.78 | 309266.4996 | -15996.7196 |  |  |  | 2023-02-13 | ADETOMIWA FALADE 8/29/2023. JOB IS CURRENTLY SHOWING LEVEL 1 UNDER RUN BUT $35,000 IN PAVING WAS PROCESSED THIS WEEK. ONCE THIS PAYMENT IS APPLIED TO THIS JOB ORDER, NO VARIANCE PAPERWORK SHOULD BE REQUIRED. THE PAVING WAS PERFORMED BY PRIVATE CONTRACTOR INSTEAD OF PIPELINE CONTRACTOR WHICH SAVED THE COST OF PAVING.
22026167300 | RETIRE 720'-4" BS-LP | [5 empty] | 0 | 62.2578 | -62.2578 |  |  |  | 2023-02-13
22026167400 | EMER - INSTALL 5'-3" PMLP | [5 empty] | 0 | 3781.5061 | -3781.5061 |  |  |  | 2022-02-09
22026167500 | EMER - RETIRE 5'-3" PLP | [5 empty] | 0 | 109.7476 | -109.7476 |  |  |  | 2022-02-09
22026167600 | INSTALL 6' OF 3"PMLP MAIN | [5 empty] | 8748.35 | 16229.6788 | -7481.3288 |  |  |  | 2022-10-27 | CUT OUT 4' SECTION OF 3" MAIN. TESTED DROP IN PIECE 90#5MINS, TG. ST LTI, TG. BHBNGF. 2 17LB ANODES INSTALLED. PRSSURE NEVER DROPPED ON GAUGES. PURGED ALL AIR OUT BEFORE GAS UP. R.CRAWFORD 10-27-22
22026167700 | RETIRE 6' OF 3"CSLP MAIN | [5 empty] | 9674.55 | 100.2728 | 9574.2772 |  |  |  | 2022-10-27 | CUT OUT 4' SECTION OF LEAKING 3" MAIN, TESTED DROP IN PIECE 90#20MINS, TG. ST LTI. TG. BHBNGF. INST. 2 17LB ANODES. PRESSURE NEVER DROPPED ON GAUGES. PURGED ALL AIR OUT BEFORE GAS UP. R.CRAWFORD 10-27-22
22026168800 | ST. JAMES HVAC UPGRADE | [5 empty] | 24656.22 | 37587.0767 | -12930.8567 |  |  |  | 2022-08-05 | MONITOR WHILE ACP SWAPS RTU STATION SET TO LOCAL MODE GC ADVISED CC 58614 UPGRADE RTU ON 3-16-22 JOSH MULLINS
24026318600 | EMER - INSTALL 11' OF 2" PMMP | [5 empty] | 41990.31 | 30688.3135 | 11301.9965 | 2024-01-01 | 2024-12-31 | 2024-02-21 | 2024-02-21 | INST 8' AND 3' SECTION OF 2" P MP MAIN DUE TO LEAK PER ENGINEERED TIE-IN PLAN. TEST NEW MAIN @ 90LB 20MIN OK. SOAP TEST TIE-IN @ OP OK
22026171200 | RETIRE 2300' OF 3"/6"BSLP | [5 empty] | 220 | 75.4968 | 144.5032 |  |  |  | #N/A
22026172800 | RETIRE 5' OF 3"PLP S/L | [5 empty] | 0 | 58.5954 | -58.5954 |  |  |  | 2022-03-16 | ABANDONED CAPITAL SERVICE LINE WITH ABANDON JOB # 18-0268434-00. LSHARON
22026172900 | INSTALL 5' OF 4"PMLP S/L | [5 empty] | 3113 | 13312.2384 | -10199.2384 |  |  |  | 2022-03-15
22026173000 | 2022 SCADA VISABILITY PROGRAM | [5 empty] | 47294.28 | 30164.6195 | 17129.6605 |  |  |  | 2022-10-04 | CC# 66617 INSTALLED NEW MIWI350 SMCHOLAN 10-4-2022
22026173600 | 2022 SCADA VISIBILITY PROGRAM | [5 empty] | 25271.05 | 31941 | -6669.95 |  |  |  | 2022-09-28 | INSTALLED NEW MIWI350 EBLANTON 9-28-2022
22026173800 | 2022 SCADA VISIBILITY PROGRAM | [5 empty] | 24972.3 | 30164.6195 | -5192.3195 |  |  |  | 2022-09-29 | WITH ACP CONTRACTOR WHILE THEY INSTALL POLE FOR COMM EQUIPMENT CC 66318 05-10-2022 RHAYES CC 1924 INSTALLED MIWI350 UNABLE TO PERFORM P2P NDAVIS WORKING ON TICKET MONITORED 30 MINUTES RHAYES 09-29-2022
22026174400 | 2022 SCADA VISIBILITY PROGRAM | [5 empty] | 28643.37 | 29658.8599 | -1015.4899 |  |  |  | 2022-10-11 | INSTALL POLES FOR COMM EQUIPMENT 05-10-2022 CC 66285 RHAYES
22026174500 | 2022 SCADA VISIBILITY PROGRAM | [5 empty] | 29029.69 | 29658.8599 | -629.1699 |  |  |  | 2022-10-05 | CC# 66436 CC# 79698 CC# 2587 CMCOX 10/5/22 INSTALLED NEW MIWI350 CCOX 10-05-2022
22026174600 | 2022 SCADA VISIBILITY PROGRAM | [5 empty] | 38527.05 | 29658.8599 | 8868.1901 |  |  |  | 2022-09-27 | CC# 66475 CC#1503 INSTALLED NEW MIWI350 WITH SUPER SOLAR KIT 9-27-22 CCOX
22026177900 | INSTALL 8' OF 6"PMMP MAIN | [5 empty] | 36900.11 | 29164.4 | 7735.71 |  |  |  | 2022-07-11
22026178000 | RETIRE 4' OF 6"CSMP MAIN | [5 empty] | 876.45 | 75.4968 | 800.9532 |  |  |  | 2022-07-11
22026178100 | INSTALL 20' OF 6"PMLP MAIN | [5 empty] | 14787.97 | 11448.7503 | 3339.2197 |  |  |  | 2022-05-25
22026178500 | INSTALL 44'-6" PMMP | [5 empty] | 77349.62 | 72684.0107 | 4665.6093 |  |  |  | 2022-08-23
22026178600 | RETIRE 26'-6" CSMP | [5 empty] | 1859.72 | 73.9724 | 1785.7476 |  |  |  | 2022-08-23
22026178900 | INSTALL 620' OF 12"CSHP MAIN | [5 empty] | 268220 | 330116.9371 | -61896.9371 |  |  |  | 2023-06-30
22026179100 | RETIRE 520' OF 12"MJBSHP | [5 empty] | 3152.18 | 131.2422 | 3020.9378 |  |  |  | 2023-06-30
22026179200 | INSTALL 50' OF 6"PMLP S/L | [5 empty] | 45896.9 | 47001.2003 | -1104.3003 |  |  |  | #N/A
22026179300 | RETIRE 82'-2"&4" PMMP | [5 empty] | 82.8 | 73.9724 | 8.8276 |  |  |  | 2022-04-02
22026180100 | INSTALL 805' OF 2"/4"PMMP MAIN | [5 empty] | 116760.6 | 54482.6036 | 62277.9964 |  |  |  | 2022-09-07 | TWALKER/KY 09-08-22: PROJECT OVER RUN DUE TO ROCK ENCOUNTERED IN CONSTRUCTI ON REQUIRING ROCK BORE AND OPEN CUT ROCK WHICH INCREATED CONTRACT COST BY $30,000. WMS WOULD NOT ALLOW REVISION OF PROJECT DUE TO UNPAID INVOICES. COMPANY LABOR INCREASED BY OVER $16,000 DUE TO EXTRA TIME FOR CONSTRUCTION AND SEGA WAS $6000 THAN ESTIMATE TWALKER/KY 01-24-23: LEVEL 2 VARIANCE REPORT ADDED TO WMS.DOCS.
22026180900 | EMER-INSTALL 4' OF 2"PMMP | [5 empty] | 3753.68 | 3916.7503 | -163.0703 |  |  |  | 2022-02-28
22026181000 | EMER-RETIRE 4' OF 2"PMMP | [5 empty] | 0 | 75.4968 | -75.4968 |  |  |  | 2022-02-28
22026181300 | RETIRE PIT REG STATION 1124 | [5 empty] | 4926.17 | 5746.3751 | -820.2051 |  |  |  | #N/A | CCC# 72702 RETIRED REG STATION, REMOVED REGS AND BLIND PLATED VAVLES, REMOVED OIL FROM PRV AND PLUGGED INSIDE PIT, PREFORMED LEAK TEST ON ALL ON CONNECTIONS, CCC 73281 CMCHOLAN 5-17-24 1600
22026181900 | LAB EQUIPMENT INSTALL | [5 empty] | 5312.84 | 15945.3111 | -10632.4711 |  |  |  | 2022-09-15
22026182000 | INSTALL 2185' OF 2" PMMP | [5 empty] | 141899.3 | 110360.5276 | 31538.7724 |  |  |  | 2022-09-27 | AWEBER 01/24/2023 - PROJECT OVERRUN DUE PRIMARILY TO LAND OWNER ISSUES & EXPANSIVE SEWER LINE CAMERA WORK PERFORMED BY BUCHANON. EASEMENT FROM FIRST LAND OWNER FELL THROUGH DUE TO HOA VOTE, INCREASING INSTALLATION BY +200' & PRIVATE EASEMENT. PROJECT ENCOUNTERED ROCK BORE ADDING ~34 HOURS TO DURATIO N. OVERRUN BUCHANON COST $17K + LAND COST $11K & INCREASED SEGA RATE $6K LE D TO VARIANCE.
22026182800 | EMER-INSTALL 3' OF 2"PMMP | [5 empty] | 4419.13 | 4826.1382 | -407.0082 |  |  |  | 2022-04-20 | INSTALLED 3' OF 2" PMMP DUE TO EXCAVATION DAMAGE, TESTED MAIN PIPE AT 90# F OR 20 MIN PER FOL APPROVAL OK, SOAP TEST 2 020 EF CPLGS AT OP FOR 5 MIN OK. INSTALLED MARKER BALLS ON CPLGS. MAP REVISED. WHIMES
22026182900 | EMER-RETIRE 3' OF 2"PMMP | [5 empty] | 2.72 | 74.2578 | -71.5378 |  |  |  | 2022-04-20 | RETIRED 3' OF 020 PMMP DUE TO EXCAVATION DAMAGE. WHIMES 04/20/2022
22026183100 | INSTALL 3090' OF 2-4" PMMP | [5 empty] | 610263.34 | 533028.4351 | 77234.9049 |  |  |  | 2023-09-08 | PROJECT COMPLETE
22026183200 | RETIRE 3765' OF 2-4" CS & PMMP | [5 empty] | 273.03 | 138.8485 | 134.1815 |  |  |  | 2023-09-08 | PROJECT COMPLETED
24026347300 | EMER - INSTALL 12'-3" PMIP | [5 empty] | 52750.04 | 21463.3624 | 31286.6776 | 2024-01-01 | 2024-12-31 | 2024-06-17 | 2024-06-17 | FOUND 2-3X3 PAC CLALMPS LEAKING AND 2-3" BOLTED COUPLINGS ON MAIN CUT OUT A ND REPLACED 12' OF 3" PL MAIN TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7 PSIG
22026183400 | RETIRE 702' OF 6" BSHP | [5 empty] | 220 | 121.7239 | 98.2761 |  |  |  | #N/A
22026183600 | INSTALL 1700'-2" PMMP | [5 empty] | 51519.58 | 46580.9585 | 4938.6215 |  |  |  | 2022-06-22
22026183700 | INSTALL 100' OF 2"PMMP MAIN | [5 empty] | 19814.52 | 12739.3747 | 7075.1453 |  |  |  | 2022-10-11 | INSTALLED 199' OF 020 MAIN. TEST 199' OF MAIN FOR 1HR AT 90LBS. FOL APPROVED.SOAP TEST 2'' EFC AT OP OF FINAL TIE IN. SOAP TEST END CAP ON MONITORING GAUGE AT OP.TEST OK.
22026184600 | INSTALL 64' OF 2"PMMP MAIN | [5 empty] | 16772.5 | 17899.1411 | -1126.6411 |  |  |  | 2022-07-11
22026184700 | RETIRE 52' OF 2"PMMP MAIN | [5 empty] | 0 | 74.2578 | -74.2578 |  |  |  | 2022-07-11
22026184800 | INSTALL 3775'-2" PMMP | [5 empty] | 689655.43 | 567138.2381 | 122517.1919 |  |  |  | 2023-04-12
22026184900 | RETIRE 3315'-2"&4"BSLP | [5 empty] | 23.53 | 72.7393 | -49.2093 |  |  |  | 2023-04-12
22026185001 | INSTALL 260' OF 2"PMMP MAIN | [5 empty] | 30483.21 | 27065.0582 | 3418.1518 |  |  |  | 2022-10-07
22026185301 | INSTALL 875' OF 2"PMMP MAIN | [5 empty] | 69561.33 | 74170.089 | -4608.759 |  |  |  | 2022-11-18
22026186000 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 3201.06 | 5480.5156 | -2279.4556 |  |  |  | 2022-05-27 | ACP REMOVED ERX REPLACED WITH MIWI CCOX RHAYES 05-27-2022
22026186100 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 175.52 | 124.5156 | 51.0044 |  |  |  | 2022-05-27 | ACP REPLACED ERX WITH MIWI RHAYES CCOX 05-27-2022 ACP REPLACED ERX WITH MIWI RHAYES CCOX 05-27-2022
22026186600 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 616.42 | 4216.5438 | -3600.1238 |  |  |  | 2022-05-19 | INSTALLED MIWI 350 AND TUBING, CCC 67481 CMCHOLAN 5-19-2022 NOT ON SITE, TURNED IN PAPERWORK IN WINCHESTER, NO CCC TICKET, CMCHOLAN 5-20-2022
22026186700 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 485.53 | 124.5156 | 361.0144 |  |  |  | 2022-05-19 | REMOVED ERX, CCC 67481 CMCHOLAN 5-19-2022 RWILLIAMS EX CAPITAL JOB
22026187200 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 1831.39 | 4745.0565 | -2913.6665 |  |  |  | 2022-05-26 | CCC# 68726 INSTALLED NEW MIWI 350 AJPARKS
22026187300 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 185.7 | 124.5156 | 61.1844 |  |  |  | 2022-05-26 | CCC# 68726 RETIRED ERX 05/26/2022 APARKS
22026187800 | INSTALL 10' OF 4"PMLP MAIN | [5 empty] | 29076.83 | 18153.0818 | 10923.7482 |  |  |  | 2022-05-25
22026187900 | RETIRE 8' OF 4"PMLP MAIN | [5 empty] | 0 | 74.2578 | -74.2578 |  |  |  | 2022-05-25
22026192300 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 281.87 | 4801.1928 | -4519.3228 |  |  |  | 2022-06-13 | CHANGED ERX TO MIWI 350, P2P OK, CCC 70245 CMHOLAN 6-13-2022
22026192400 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 443.37 | 124.8731 | 318.4969 |  |  |  | 2022-06-13 | REMOVED ERX TO INSTALL MIWI, CCC 70245 CMCHOLAN 6-13-2022 INSTALLED NEW MIWI350
22026195000 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5607.88 | 4801.1928 | 806.6872 |  |  |  | 2022-08-29 | SWAP COMP. PARKS 08-29-22 1545 CCC# 78985 RETIRED OLD ERX INSTALLED NEW MIWI350 AJPARKS 8-29-2022
22026195100 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 248.95 | 124.8731 | 124.0769 |  |  |  | 2022-08-29 | REMOVAL COMP. APARKS 08-29-22 1044 CCC# 78985 RETIRED OLD ERX INSTALLED NEW MIWI350 AJPARKS 8-29-2022
22026197100 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5373.93 | 4801.1928 | 572.7372 |  |  |  | 2022-09-07 | CCC 79940 RETIRED OLD ERX INSTALLED NEW MIWI350 9-7-2022
22026197200 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 251.1 | 124.8731 | 126.2269 |  |  |  | 2022-09-07 | CCC 79940 RETIRED OLD ERX INSTALLED NEW MIWI350 EBLANTON 9-7-2022
22026197300 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 6904.6 | 4801.1928 | 2103.4072 |  |  |  | 2022-10-19 | CC# 3980 CMCOX 10/19/22 INSTALLED NEW MIWI350 CCOX 10-19-22
22026197400 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 305.47 | 124.8731 | 180.5969 |  |  |  | 2022-10-19 | CC# 3980 CMCOX 10/19/22 RETIRED OLD ERX CCOX 10-19-22
22026197700 | INSTAL 3'-2" PMMP | [5 empty] | 1311.83 | 2387.9592 | -1076.1292 |  |  |  | 2022-06-07 | HIT MAIN BY CONCRETE STAKE.MADE SAFE BY SQUEEZING OFF IN TWO BELL HOLES. REPLACED DAMAGED SECTION OF PIPE.TESTED 10FT OF 020 AND PURGE TEE FOR 1HR 90LBS.TEST OK.SOAP TEST END CAP AND 2EFC'S CPLGS AT OP.TEST OK BHB NGF
22026197800 | RETIRE 3'-2" PMMP | [5 empty] | 914.45 | 76.9137 | 837.5363 |  |  |  | 2022-06-07 | HIT MAIN BY CONCRETE STAKE.MADE SAFE BY SQUEEZING OFF IN TWO BELL HOLES. REPLACED DAMAGED SECTION OF PIPE.TESTED 10FT OF 020 AND PURGE TEE FOR 1HR 90LBS.TEST OK.SOAP TEST END CAP AND 2EFC'S CPLGS AT OP.TEST OK BHB NGF
22026198601 | INSTALL 1900' OF 2"PMMP MAIN | [5 empty] | 71556.52 | 50146.9852 | 21409.5348 |  |  |  | 2022-10-21
22026199100 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5602.7 | 4801.1928 | 801.5072 |  |  |  | 2022-09-02 | CCC 79615 RETIRED OLD ERX INSTALLED NEW MIWI350 EBLANTON 9-2-2022
22026199200 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 880.44 | 124.8731 | 755.5669 |  |  |  | 2022-09-02 | CCC 79615 RETIRED OLD ERX INSTALLED NEW MIWI350 EBLANTON 9-2-2022
22026200500 | RETIRE 2' OF 3"PLP S/L | [5 empty] | 0 | 62.4365 | -62.4365 |  |  |  | 2022-09-12
22026200600 | INSTALL 15' OF 3"/4"PMLP S/L | [5 empty] | 10449.59 | 11118.4162 | -668.8262 |  |  |  | 2022-08-15
22026202200 | INSTALL 125' OF 2" PMMP MAIN | [5 empty] | 11459.71 | 8841.6395 | 2618.0705 |  |  |  | 2022-07-14
22026202900 | RETIRE 135' OF 2"PMP MAIN | [5 empty] | 2.29 | 78.4365 | -76.1465 |  |  |  | 2022-09-07
22026203900 | RETIRE PAPER GAUGE | [5 empty] | 0 | 78.4365 | -78.4365 |  |  |  | 2022-10-05 | RETIRED PAPER CHART CCOX10-05-2022
22026204000 | RETIRE PAPER GAUGE | [5 empty] | 157.99 | 78.4365 | 79.5535 |  |  |  | 2022-09-27 | RETIRED PAPER CHART CHRIS COX 9-27-22
22026204200 | RETIRED GAUGE | [5 empty] | 0 | 76.9137 | -76.9137 |  |  |  | 2022-10-04 | RETIRED PAPER CHARTS SMCHOLAN 10-04-2022
22026206900 | EMER-INSTALL 16' OF 4"/6"PMLP | [5 empty] | 11009.07 | 8399.775 | 2609.295 |  |  |  | 2022-07-15 | LEAKING POSI HOLD COUPLING.LEAKING OUT OF FITTING ON COUPLING. REPLACED 6'' TEE AND 19FT OF MAIN.TESTED MAIN FOR 1HR AT 90LBS.TEST OK. SOAP TEST FINAL TIE INS AT OP FOR 5MINS AT OP.TEST OK. BHB NGF.
22026207000 | EMER-RETIRE 14' OF 6"BSLP | [5 empty] | 11230.19 | 60.0112 | 11170.1788 |  |  |  | 2022-07-15 | LEAKING POSI HOLD COUPLING.LEAKING OUT OF FITTING ON COUPLING. REPLACED 6'' TEE AND 19FT OF MAIN.TESTED MAIN FOR 1HR AT 90LBS.TEST OK. SOAP TEST FINAL TIE INS AT OP FOR 5MINS AT OP.TEST OK. BHB NGF.
22026208900 | EMER - INSTALL ~10'-8" CSHP | [5 empty] | 59795.62 | 32930.2498 | 26865.3702 |  |  |  | 2022-07-07
22026209400 | RETIRE CHAIN LINK FENCE | [5 empty] | 0 | 65.0112 | -65.0112 |  |  |  | 2022-06-28
22026209500 | RETIRE CHAIN LINK FENCE | [5 empty] | 0 | 65.0112 | -65.0112 |  |  |  | 2022-05-10
22026209800 | RETIRE VAULT STRUCTURE | [5 empty] | 0 | 1027.5809 | -1027.5809 |  |  |  | 2022-11-16 | PIT RETIRED AND FILLED IN
22026209900 | RETIRE VAULT STRUCTURE | [5 empty] | 2265.12 | 859.5809 | 1405.5391 |  |  |  | #N/A
22026210000 | RETIRE ELECTRONICS | [5 empty] | 249.16 | 65.0112 | 184.1488 |  |  |  | 2022-07-14 | RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07-14-2022
22026210100 | EMER - INSTALL 6'-4" PMMP | [5 empty] | 5514.88 | 4810.9373 | 703.9427 |  |  |  | 2022-07-26 | DAMAGED SECTION OF PIPE DUE TO EXCAVATOR ERROR.MADE SAFE BY SQUEEZING OFF IN BELLHOLES.OC 16FT NEW MAIN DUE TO EXCAVATION WHERE DAMAGE WAS TOO DEEP. TESTED MAIN 1HR AR 90LB.TEST OK.SOAP TEST EFC'SAT OP.TEST OK BHB NGF
22026210200 | EMER - RETIRE 6'-4" PMMP | [5 empty] | 95.05 | 63.5475 | 31.5025 |  |  |  | 2022-07-26 | DAMAGED SECTION OF PIPE DUE TO EXCAVATOR ERROR.MADE SAFE BY SQUEEZING OFF IN BELLHOLES.OC 16FT NEW MAIN DUE TO EXCAVATION WHERE DAMAGE WAS TOO DEEP. TESTED MAIN 1HR AR 90LB.TEST OK.SOAP TEST EFC'SAT OP.TEST OK BHB NGF
22026210301 | INSTALL 850' OF 4"PMMP MAIN | [5 empty] | 173794.47 | 192098.991 | -18304.521 |  |  |  | 2023-01-23
22026210600 | EMER-RETIRE 50' OF 3"BSLP MAIN | [5 empty] | 2854.75 | 5032.3621 | -2177.6121 |  |  |  | 2022-09-12
22026211400 | PAPER ONLY-RETIRE MP MAIN | [5 empty] | 0 | 65.0112 | -65.0112 |  |  |  | 2022-06-23
22026212500 | REPLACE VALVES AT R-1084 | [5 empty] | 9402.89 | 14531.0267 | -5128.1367 |  |  |  | 2023-09-06 | HELP CCOX WITH VALVE REPLACEMENT, CMCHOLAN 9-5-23 1600 CC# 43383 PAPERWORK ONLY. NO CC# REQUIRED. NOT ON SITE.
22026212600 | RETIRE STATION VALVES R-1084 | [5 empty] | 1269.98 | 119.4953 | 1150.4847 |  |  |  | 2023-09-06
22026213000 | RETIRE 2015'-8/4/2" BSMP/CSMP | [5 empty] | 220 | 89.0305 | 130.9695 |  |  |  | 2023-12-19
22026213100 | RETIRE 3"BSMP SERVICE LINE | [5 empty] | 0 | 63.4096 | -63.4096 |  |  |  | 2023-12-06
22026213200 | INSTALL 30' OF 2-4" PMMP S/L | [5 empty] | 33540.05 | 27880.5873 | 5659.4627 |  |  |  | 2023-12-06
22026214700 | ST. JAMES RTU PANEL | [5 empty] | 0 | 55.5311 | -55.5311 |  |  |  | 2022-08-05 | UPGRADED RTU JOSH MULLINS
22026214800 | EMER INSTALL 2' - PMMP | [5 empty] | 8176.85 | 2418.3858 | 5758.4642 |  |  |  | 2022-07-27
22026214900 | EMER RETIRE 2'-PMP | [5 empty] | 0 | 84.9152 | -84.9152 |  |  |  | 2022-07-27
22026215000 | EMER INSTALL 2'-4" PMLP | [5 empty] | 9400.14 | 3659.4376 | 5740.7024 |  |  |  | 2022-07-28
22026215100 | EMER RETIRE 2'-4" PLP | [5 empty] | 0 | 84.9152 | -84.9152 |  |  |  | 2022-07-28
22026215300 | EMER - INSTALL 20'-2" PMIP | [5 empty] | 15168.73 | 10433.2304 | 4735.4996 |  |  |  | 2022-07-21
22026215400 | EMER - RETIRE 5'-2" PMIP | [5 empty] | 0 | 80.5311 | -80.5311 |  |  |  | 2022-07-21
22026215500 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 6774.27 | 4479.378 | 2294.892 |  |  |  | 2022-07-21
22026215600 | EMER - RETIRE 5'-2" PMMP | [5 empty] | 0 | 84.9152 | -84.9152 |  |  |  | 2022-07-21
22026215900 | EMER-INSTALL 3' OF 2"PMMP MAIN | [5 empty] | 1854.5 | 3722.1191 | -1867.6191 |  |  |  | 2022-08-22 | REPLACED 3FT SECTION OF MAIN. TESTED NEW SECTION OF MAIN FOR 20MINS AT 90LBS.TEST OK SOAP TEST EFC'S AT OP FOR 5MINS.TEST OK. BHBNGF
22026216000 | EMER-RETIRE 3' OF 2"PAMP MAIN | [5 empty] | 143.19 | 84.9152 | 58.2748 |  |  |  | 2022-08-22 | REPLACED 3FT SECTION OF MAIN. TESTED NEW SECTION OF MAIN FOR 20MINS AT 90LBS.TEST OK SOAP TEST EFC'S AT OP FOR 5MINS.TEST OK. BHBNGF
22026216200 | INSTALL 950' OF 2"/4"PMMP MAIN | [5 empty] | 47379.78 | 39269.0655 | 8110.7145 |  |  |  | 2022-09-09
22026216900 | PAPER ONLY EXECUTE | [5 empty] | 0 | 84.9152 | -84.9152 |  |  |  | 2022-04-29
22026217300 | RETIRE 3"PLP SERVICE LINE | [5 empty] | 0 | 170.8304 | -170.8304 |  |  |  | 2022-09-08
22026217400 | RETIRE 6"PLP SERVICE LINE | [5 empty] | 827.26 | 144.8304 | 682.4296 |  |  |  | 2022-10-06
22026217800 | EMER-INSTALL 3' OF 4"PMLP MAIN | [5 empty] | 12300.82 | 6173.2589 | 6127.5611 |  |  |  | 2022-08-18 | LEAK CLEARED USING DPI D311930 PW
22026217900 | EMER-RETIRE 3' OF 4"BSLP MAIN | [5 empty] | 4448.33 | 170.8304 | 4277.4996 |  |  |  | 2022-08-18
22026218200 | RETIRE PAPER GUAGE | [5 empty] | 0 | 339.1994 | -339.1994 |  |  |  | 2022-07-28 | RETIRE PAPER CHART DUE TO ERX INSTALL AT ANOTHER STATION SMCHOLAN
22026218300 | RETIRE PAPER GAUGE | [5 empty] | 0 | 339.1994 | -339.1994 |  |  |  | 2022-07-28 | RETIRED PAPER CHART DUE TO ERX INSTALL AT ANOTHER LOCATION
22026218800 | INSTALL MI WIRELESS UNIT | [5 empty] | 10259.75 | 9310.2589 | 949.4911 |  |  |  | 2022-10-06 | CC# 79803 CC# 2675 CC# 2675 CMCOX 10/6/22 INSTALLED NEW MIWI350 CCOX 10-06-2022
22026219400 | INSTALL 380' OF 4"PMMP MAIN | [5 empty] | 172779.97 | 176409.6078 | -3629.6378 |  |  |  | 2023-06-08
22026219500 | RETIRE 380' OF 4"BSMP MAIN | [5 empty] | 91.2 | 89.0305 | 2.1695 |  |  |  | 2023-06-08
22026220800 | *PAPER ONLY* 2022 CAST IRON | [5 empty] | 0 | 295.7645 | -295.7645 |  |  |  | 2022-10-19
22026221200 | EMER - INSTALL 8'-6"PMMP | [5 empty] | 11736.48 | 32929.6819 | -21193.2019 |  |  |  | 2022-09-12 | TEST 6 IN MAIN AT 90 LB FOR 20 MIN SOAP TEST EFC AT OP FOR 5 MIN
22026221300 | EMER - RETIRE 8'-6" PMP | [5 empty] | 595.27 | 87.3224 | 507.9476 |  |  |  | 2022-09-12 | REMOVED 2 FT OF 6 IN DAMAGE PIPE
22026222800 | EMER-INSTALL 2' OF 4"PMMP MAIN | [5 empty] | 21988.24 | 23837.8998 | -1849.6598 |  |  |  | 2022-09-12
22026222900 | EMER-RETIRE 2' OF 4"PMMP MAIN | [5 empty] | 0 | 89.0305 | -89.0305 |  |  |  | 2022-09-12
22026223100 | EMER-INSTALL 3' OF 2"PMMP MAIN | [5 empty] | 4059.84 | 4624.3747 | -564.5347 |  |  |  | 2022-10-11 | COMPLETED PAPERWORK FOR JOB. R.CRAWFORD 10-11-22
22026223200 | EMER-RETIRE 3' OF 2"PMP MAIN | [5 empty] | 125.23 | 89.0305 | 36.1995 |  |  |  | 2022-10-17 | R.CRAWFORD
22026223600 | INSTALL 3000' OF 2"PMMP MAIN | [5 empty] | 80798.26 | 81410.7619 | -612.5019 |  |  |  | 2023-08-23
22026223700 | INSTALL 1296'-2"&4" PMMP | [5 empty] | 286331.62 | 306884.1479 | -20552.5279 |  |  |  | 2023-04-24
22026223800 | RETIRE 1212'-2",3"&4" CSMP | [5 empty] | 0 | 117.5985 | -117.5985 |  |  |  | 2023-04-24
22026223900 | INSTALL 1067'-4" PMMP | [5 empty] | 149979.89 | 181608.1135 | -31628.2235 |  |  |  | 2023-02-10
22026224000 | RETIRE 1150'-4" PMMP | [5 empty] | 0 | 72.8379 | -72.8379 |  |  |  | 2023-02-10
24026316500 | EMER - INSTALL 15'-2" PMMP | [5 empty] | 0 | 4538.5784 | -4538.5784 | 2024-01-01 | 2024-12-31 | 2024-02-07 | 2024-02-07
22026224300 | RETIRE 4500' OF 6"/4"BSLP MAIN | [5 empty] | 2115.84 | 114.3981 | 2001.4419 |  |  |  | #N/A
22026227000 | EMER-INSTALL 3' OF 2"PMMP MAIN | [5 empty] | 5707.92 | 5024.0582 | 683.8618 |  |  |  | 2022-09-30 | INST 3" OF 2 P MP MAIN PER GAS STANDARDS. MCRAIG 9/30/22
22026227100 | EMER-RETIRE 3' OF 2"PMP MAIN | [5 empty] | 316.08 | 74.3089 | 241.7711 |  |  |  | 2022-09-30 | ABN 3' OF 2" P MP MAIN DUE TO LEAK. PER GAS STANDARDS. MCRAIG 9/30/22
22026227200 | RETIRE ELECTRONICS | [5 empty] | 0 | 74.3089 | -74.3089 |  |  |  | 2022-12-15
22026228000 | EMER-INSTALL 3' OF 2"PMMP MAIN | [5 empty] | 2032.93 | 4027.0582 | -1994.1282 |  |  |  | 2022-10-06 | INSTALLED 3 FT OF 2 IN MAIN ON DAMAGE TEST FROM POINT A TO B 90 LB FOR 20 MIN TEST PURG TEE 90 LB FOR 5 MIN SOAP TEST 1 IN END CAP AT OP FOR 5 MIN SOAP TEST 2 EFC AT OP FOR 5 MIN BHB NO GAS FOUND
22026228100 | EMER-RETIRE 3' OF 2"PMMP MAIN | [5 empty] | 590.32 | 74.3089 | 516.0111 |  |  |  | 2022-10-04
24026342000 | EMER - INSTALL 2' OF 2"PMMP | [5 empty] | 6607.96 | 4292.2109 | 2315.7491 | 2024-01-01 | 2024-12-31 | 2024-05-14 | 2024-05-14 | INST 2'- 2" P MP MAIN DUE TO DAMAGE. INST PER ENGINEERED TIE-IN PLAN. WORKED 5/2/24. SOAP TEST TIE-IN OK. MCRAIG 5/14/24
22026228600 | RETIRE 136'-2" PMMP | [5 empty] | 50.09 | 72.8379 | -22.7479 |  |  |  | #N/A
22026230100 | EMER-INSTALL 2' OF 2"PMMP | [5 empty] | 2249.75 | 3890.5291 | -1640.7791 |  |  |  | 2022-10-06
22026230200 | EMER-RETIRE 2' OF 2"PMP MAIN | [5 empty] | 0 | 74.3089 | -74.3089 |  |  |  | 2022-10-06
24026356500 | EMER - INSTALL 2'-2" PMIP | [5 empty] | 4865.71 | 2544.1386 | 2321.5714 | 2024-01-01 | 2024-12-31 | 2024-09-04 | 2024-09-04 | INSTALLED 2' OF 2" P DUE TO FAC DAM. TESTED 90PSIG 1HR SOAP TESTED FC AT OP 7PSIG. CWHEELE
22026231400 | RETIRE 975' OF 8"BSLP MAIN | [5 empty] | 110 | 121.7239 | -11.7239 |  |  |  | #N/A
22026231800 | RETIRE PAPER CHART | [5 empty] | 0 | 1093 | -1093 |  |  |  | 2022-08-23 | RETIRED PAPER CHART CCOX 8-23-22
22026232000 | RETIRE PAPER GAUGE | [5 empty] | 0 | 993 | -993 |  |  |  | 2022-07-26 | RETIRED PAPER CHART 7-26-22 CCOX
22026232100 | RETIRE PAPER GAUGE | [5 empty] | 719.12 | 993 | -273.88 |  |  |  | 2022-12-14 | REMOVED CHART, CCC 2244, CMCHOLAN 12-1-22
22026233800 | INSTALL 380' OF 4"PMLP SL | [5 empty] | 35845.97 | 36339.1396 | -493.1696 |  |  |  | #N/A
22026234001 | INSTALL 500' OF 2"/4"PMMP MAIN | [5 empty] | 95523.45 | 89921.6185 | 5601.8315 |  |  |  | 2023-04-25 | INSTALLED 422' 040-PMMP 185' 020-PMMP 607' TOTAL
22026236501 | INSTALL 1325' OF 4"/8"CSHP MN | [5 empty] | 1407086.76 | 1205185.7862 | 201900.9738 |  |  |  | 2025-05-29
22026236600 | RETIRE 1300'- 6 5/8"BSHP MAIN | [5 empty] | 484.04 | 119.4953 | 364.5447 |  |  |  | #N/A
24026351400 | EMER - INSTALL 2'-2" PMMP | [5 empty] | 1846.55 | 5752.0111 | -3905.4611 | 2024-01-01 | 2024-12-31 | 2024-07-31 | 2024-07-31 | INST 2' OF 2" PLASTIC MAIN- TSTED FOR 90LBS FOR 20MIN PER FOL TST OK- SOAP TST POINT A AND POINT B FOR 5MIN @OP TST OK- BHB NGF TROE
22026236800 | RETIRE 130'-4" PLP | [5 empty] | 10308.08 | 160.3697 | 10147.7103 |  |  |  | #N/A | RETIRE 148'- 4" P LP MAIN TO RELOCATE PER ENGINEERED PLAN. MCRAIG 2/27/24
22026238200 | INSTALL 205' OF 2"PMMP MAIN | [5 empty] | 13604.24 | 19394.2346 | -5789.9946 |  |  |  | 2023-01-16 | TWALKER/KY 01-20-23: ISSUED BACK ORDER REQUEST #52196 FOR THIS JOB
22026239702 | INSTALL 8650' - 2,4,6" PMMP | [5 empty] | 1934664.05 | 1422627.7319 | 512036.3181 |  |  |  | 2025-05-02
22026239800 | RETIRE 6065' - 4/6" BS/CS/PLP | [5 empty] | 149.74 | 139.1159 | 10.6241 |  |  |  | #N/A
22026240100 | GMB TO CAB CONVERSION | [5 empty] | 2136.59 | 238.427 | 1898.163 |  |  |  | 2023-04-04 | CONVERTED GMB TO CAB ACCOUNT, CMCHOLAN 4-4-23
22026240900 | PAPER ONLY EXECUTE | [5 empty] | 0 | 119.2135 | -119.2135 |  |  |  | 2022-11-30
22026241500 | INSTALL 40'-2" PMMP | [5 empty] | 14054.24 | 23266.5784 | -9212.3384 |  |  |  | 2023-03-23
22026241600 | RETIRE 30'-2" PMMP | [5 empty] | 193.2 | 124.7348 | 68.4652 |  |  |  | 2023-03-21
22026242301 | INSTALL 8"POLY VALVE W/10"SPH | [5 empty] | 84736.28 | 63212.0666 | 21524.2134 |  |  |  | 2023-09-07
22026242500 | EMER-RETIRE 385' OF 2"/3"PAIP | [5 empty] | 5628.45 | 5363.3319 | 265.1181 |  |  |  | 2022-12-13
22026242600 | INSTALL 500' - 4" PMMP | [5 empty] | 115979.71 | 97718.819 | 18260.891 |  |  |  | 2023-05-26
22026242700 | INSTALL 350' OF 8"CSHP MAIN | [5 empty] | 383081.64 | 370158.4472 | 12923.1928 |  |  |  | 2023-08-31
22026242800 | RETIRE 326' OF 8"CSHP MAIN | [5 empty] | 0 | 114.3981 | -114.3981 |  |  |  | 2023-08-31
22026243000 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 20860 | 29336.8866 | -8476.8866 |  |  |  | 2023-04-20 | CC# 23362 CCC# 24092 DID NOT ENTER STATION. CWEMPE 4/27/23
22026243100 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 18742.99 | 21860.8866 | -3117.8966 |  |  |  | 2023-04-26 | CC 22894 WELDED TAPS ON COULD NOT PRESSURE TEST DUE TO TIME CONSTRAINTS PER RTWAIT CCC# 24089
22026243200 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 20634.93 | 25283.8866 | -4648.9566 |  |  |  | 2023-04-11 | CCC# 21042 CC 22745 WELD AND TEST STEEL TIE TAPS INLET 240# OUTLET 90# 5MINS RHAYES DMARTIN 03-30-2023 NOT ONSITE COLLECTING PARTS FOR JOB CCC#27524
22026243300 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 20996.21 | 20719.8866 | 276.3234 |  |  |  | 2023-04-12 | CCC# 21042 CC#23191 CC#24679 CC# 27421 CMCOX 4/27/23 1600
22026243400 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 15857.32 | 19008.8866 | -3151.5666 |  |  |  | 2023-03-29 | CCC#22649
22026243500 | RETIRE RECORDING GAUGE | [5 empty] | 241.8 | 96.4823 | 145.3177 |  |  |  | 2023-03-29 | CCC#22649
22026243600 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 18807.4 | 27565.8866 | -8758.4866 |  |  |  | 2023-04-14 | CCC 25146 INSTALLED NEW MIWI AND SOLAR KIT, NOT COMMIONSED YET CCC 25146 INSTALLED NEW SCADA EQUMENT NOT COMSSIONED YET BUT IS UP AND RUNNING CCC-30719PREFORMED POINT TO POINT FOR NEW WIMI
22026243900 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 13592.24 | 14352.6752 | -760.4352 |  |  |  | 2023-05-04 | CHANGE OF PLAN, SCADA IS NOT BUILT FOR THIS SIGHT AND NOT READY TO BE CHANGED OVER, CMCHOLAN 3-28-23 INSTALL NEW MIWI, P2P OK, GAGE INSP OK, REMOVED PAPER PRESSURE CHART, PRESSURE TEST OK, CMCHOLAN 5-4-23 1358
22026244000 | RETIRE ELECTRONICS | [5 empty] | 65.38 | 131.2422 | -65.8622 |  |  |  | 2023-05-04 | REMOVED ERX TO INSTALL MIWI, CCC 22274, CMCHOLAN 3-28-23
22026245000 | PAPER ONLY EXECUTE | [5 empty] | 0 | 131.2422 | -131.2422 |  |  |  | 2022-12-09
23026246100 | RETIRE PAPER GAUGE | [5 empty] | 389.08 | 131.2422 | 257.8378 |  |  |  | 2023-01-02 | RETIRE PRESSURE CHART GUAGE CCOX 1-2-23
23026246401 | INSTALL 3100' OF 2"PMMP MAIN | [5 empty] | 515222.82 | 612252.3877 | -97029.5677 |  |  |  | 2023-05-22
23026246500 | RETIRE 2400' OF 4"BS/CSLP MAIN | [5 empty] | 0 | 138.8485 | -138.8485 |  |  |  | 2023-05-22
23026247700 | INSTALL NEW GMB SETTING | [5 empty] | 96486.51 | 92317.8265 | 4168.6835 |  |  |  | 2023-08-04 | TICKET# 39340 CCC#39340 CCC#39492 08-04-2023 RHAYES CCC#39795
23026248200 | EMER - INSTALL 2'-2" PMMP | [5 empty] | 135.67 | 13154.2985 | -13018.6285 |  |  |  | 2023-01-11 | INSTALLED 2 ' OF 2'' PMP PIPE ( TESTED PIPE FOR 20MNS-GOOD PER FOL R. VANDERPOOL) J.OCHOA
23026248300 | EMER - RETIRE ~2'-2"PMP | [5 empty] | 1647.72 | 129.6266 | 1518.0934 |  |  |  | 2023-01-11 | RETIRED 2' OF 2'' P MP MAIN DUE TO DAMAGE. J.OCHOA 01-11-2023
23026248400 | EMER-INSTALL 3' OF 2"PMMP MAIN | [5 empty] | 2322.97 | 5318.1948 | -2995.2248 |  |  |  | 2023-01-18
23026248500 | EMER-RETIRE 3' OF 2"PMMP MAIN | [5 empty] | 0 | 131.2422 | -131.2422 |  |  |  | 2023-01-18
23026248900 | INSTALL 100' OF 2"PMMP MAIN | [5 empty] | 28889.25 | 30720.7606 | -1831.5106 |  |  |  | 2023-02-03
23026249000 | RETIRE 86' OF 2"CSMP MAIN | [5 empty] | 0 | 131.2422 | -131.2422 |  |  |  | 2023-02-09 | ABN 102' OF 2'' COATED STEELE MAIN PURGED AND END SEALED
23026249300 | EMER-INSTALL 5' OF 2"PMMP | [5 empty] | 5012.41 | 8253.2559 | -3240.8459 |  |  |  | 2023-01-18 | REPLACED 3' OF DAMAGED 2" PLASTIC MAIN LINE WITH 2 EF COUPLINGS. PRESSURE TESTED THE THE NEW MAIN LINE AT 90PSIG FOR 1 HOUR. PRESSURE TEST OKAY. BHB, NGF. SOAP TESTED FINAL TIE IN AT OP. TEST OK. DMALONE
23026249400 | EMER-RETIRE 5' OF 2"PMMP MAIN | [5 empty] | 219.4 | 131.2422 | 88.1578 |  |  |  | 2023-01-17 | REPLACED 3' OF DAMAGES 2" PLASTIC MAIN LINE WITH 2 EF COUPLINGS. PRESSURE TESTED THE NEW MAIN LINE AT 90PSIG FOR 1 HOUR. PRSSURE TEST OK. BHB, NGF. SOAP TESTED FINAL TIE IN AT OP. TEST OK. DMALONE
23026249800 | INSTALL EC 350 UNIT | [5 empty] | 5379.35 | 7475.3221 | -2095.9721 |  |  |  | 2023-01-25 | CHECK TO SEE IF CARD WAS READY CMCHOLAN 1-27-2023 INSTALLED NEW EC350 CMCHOLAN 1-25-23
23026249900 | RETIRE PAPER BILLING CHART | [5 empty] | 463.02 | 131.2422 | 331.7778 |  |  |  | 2023-01-25 | REMOVED PAPER BILLING CHART, CMCHOLAN EBLANTON 1-25-23
23026250000 | INSTALL EC 350 UNIT | [5 empty] | 6158.92 | 5649.3221 | 509.5979 |  |  |  | 2023-03-16 | INSTALLED NEW HONEYWELL EC350 INPLACE OF CHART
23026250100 | RETIRE PAPER BILLING CHART | [5 empty] | 525.01 | 131.2422 | 393.7678 |  |  |  | 2023-03-16 | RETIRED PAPER CHART EBLANTON 3-16-23
23026250200 | INSTALL EC-350 | [5 empty] | 8105.28 | 6049.3221 | 2055.9579 |  |  |  | 2023-03-14 | INSTALLED IN HONEYWELL EC3560 IN PLACE OF CHART EBLANTON 3-14-23
23026250300 | RETIRE PAPER BILLING CHART | [5 empty] | 185.13 | 131.2422 | 53.8878 |  |  |  | 2023-03-14 | RETIRE PAPER BILLING CHART EBLANTON 3-14-23
23026250500 | INSTALL EC 350 | [5 empty] | 6654.67 | 7589.3221 | -934.6521 |  |  |  | 2023-03-15 | INSTALLED NEW HONEYWELL EC350 IN PLACE OF CHART EBLANTON 3-15-2023
23026250600 | RETIRE PAPER BILLING CHART | [5 empty] | 144.2 | 131.2422 | 12.9578 |  |  |  | 2023-03-15 | RETIRED PAPER BILLING CHART EBLANTON 3-15-23
23026250700 | INSTALL EC 350 | [5 empty] | 5810.87 | 5649.3221 | 161.5479 |  |  |  | 2023-03-01 | RETIRED CHART INSTALLED NEW EC350
23026250800 | RETIRE PAPER BILLING CHART | [5 empty] | 528.15 | 131.2422 | 396.9078 |  |  |  | 2023-03-01 | RETIRED PAPER CHART CCOX
23026251700 | INSTALL 2060' OF 2" PMMP | [5 empty] | 65881.72 | 60788.4178 | 5093.3022 |  |  |  | 2023-03-06
23026251800 | RETIRE 900' OF 2"CSHP MAIN | [5 empty] | 12666.75 | 4095.9621 | 8570.7879 |  |  |  | 2023-08-07
23026252000 | EMER-INSTALL 3' OF 6"PMMP MAIN | [5 empty] | 13052.34 | 12970.9861 | 81.3539 |  |  |  | 2023-02-03
23026252100 | RETIRE 3' OF 6"PMP MAIN | [5 empty] | 0 | 138.8485 | -138.8485 |  |  |  | 2023-02-03
23026252200 | EMER-INSTALL 3' OF 4"PMMP MAIN | [5 empty] | 5339.51 | 7839.2961 | -2499.7861 |  |  |  | 2023-02-02
23026252300 | EMER-RETIRE 3' OF 4"PAMP MAIN | [5 empty] | 0 | 138.8485 | -138.8485 |  |  |  | 2023-02-02
23026252600 | INSTALL 3' OF 4"PMLP MAIN | [5 empty] | 16571.37 | 9484.2961 | 7087.0739 |  |  |  | 2023-01-25 | ABD 69 FT BS CUT OUT INLINE TEE AND INSTALLED 5 FT OF 4 IN PL TEST 90 LB FOR 1 HR OK SOAP TEST CPLG AND TEES AT OP FOR 5 MIN BAR HOLE BANKS NO GAS FOUND
23026252700 | RETIRE 69' OF 4"BSLP MAIN | [5 empty] | 0 | 138.8485 | -138.8485 |  |  |  | 2023-01-25 | ABDN 69 FT OF 6 IN BARE STEEL BLEW DOWN AND SEALED ENDS
23026253900 | RETIRE PRESSURE GAUGE | [5 empty] | 0 | 552.5683 | -552.5683 |  |  |  | 2023-01-27
23026254000 | RETIRE PRESSURE GAUGE | [5 empty] | 768.43 | 552.5683 | 215.8617 |  |  |  | 2023-01-31 | CC15136 CHART HAS BEEN REMOVED ISO UPDATED 1-31-23 CC15136 CHART HAS BEEN REMOVED ISO UPDATED 1-31-23
23026254400 | INSTALL 420' OF 6"PMMP MAIN | [5 empty] | -558.31 | 9832.3981 | -10390.7081 |  |  |  | 2023-08-31
23026254500 | RETIRE 356' OF 6"PMMP MAIN | [5 empty] | 0 | 114.3981 | -114.3981 |  |  |  | 2023-08-31
23026254700 | RETIRE PAPER GAUGE | [5 empty] | 247.65 | 552.5683 | -304.9183 |  |  |  | 2023-02-10 | REMOVED PAPER CHART, CCC 10587
24026352600 | EMER - INSTALL 2'-2" PMMP | [5 empty] | 1939.02 | 3613.4082 | -1674.3882 | 2024-01-01 | 2024-12-31 | 2024-08-06 | 2024-08-06 | CONTRACTOR HIT 020 PMP WHILE DIGGING OUT SEWER BOX.SQUEEZE OFF IN BELLHOL TO MAKE SAFE.INSTALLED 3FT MAIN.TEST MAIN FOR 20MINS AT 90LBS.TEST OK.TES TEE 5MINS AT 90LBS.TEST OK.SOAP TEST EFC AT OP FOR 5MINS.TEST OK.BHB NGF
23026255000 | RETIRE 620' OF 8"CSHP MAIN | [5 empty] | 330 | 116.356 | 213.644 |  |  |  | #N/A
23026256201 | INSTALL VRG CONTROLLERS | [5 empty] | 79546.52 | 47185.8659 | 32360.6541 |  |  |  | #N/A | DROPPING OF MATTERIAL 06-02-23 1324 CCC# 32360 CCC#32737 CC# 33503 CCC# 33503 CCC# 39939
23026256400 | INSTALL 25' OF 2"PMMP MAIN | [5 empty] | 9201.52 | 8978.2187 | 223.3013 |  |  |  | 2023-08-08 | INSTALLED 18' OF NEW MAIN AND ONE SERVICE LINE TO 1600 VILLA MEDICI TWALKER/KY 10-19-23: ISSUED BACK ORDER CANCEL 53922 FOR THE 250' COIL OF 2"PIPE WHICH IS NO LONGER AVAILABLE
23026257000 | ST JOE - RETIRE RTU | [5 empty] | 310.19 | 138.8485 | 171.3415 |  |  |  | 2023-04-03 | RETIRED OLD RTU EBLANTON 4-3-23
23026259000 | EMER-INST 85'-4"PMMP MND311494 | [5 empty] | 23726.73 | 25540.4028 | -1813.6728 |  |  |  | 2023-02-20 | 4" MAIN/PINK PL LEAKING UNDER STAMPED CONCRETE ENTRANCE TO COUNTRY CLUB RETIRED 85' AND INSTALLED 85' OF NEW MAIN-BORING DONE BY STANLEY PIPELINE, MAIN TEST 1 HR @90IB OK, TIE IN COMPLETE 02/20/2023 HMCKUNE
23026259100 | EMER-RETIRE 85' OF 4"PAMP MAIN | [5 empty] | 260.66 | 138.8485 | 121.8115 |  |  |  | 2023-02-20 | 4" MAIN/PINK PL LEAKING UNDER STAMPED CONCRETE ENTRANCE TO COUNTRY CLUB RETIRED 85' AND INSTALLED 85' OF NEW MAIN-BORING DONE BY STANELY PIPELINE, MAIN TEST 1HR @90 IB OK, TIE IN COMPLETE, 02/20/2023 HMCKUNE
23026260700 | INSTALL ERX W/SUPER SOLAR | [5 empty] | 3972.47 | 5629.9621 | -1657.4921 |  |  |  | 2023-03-06 | INSTALLED SUPER SOLAR AND MEDIUM PRESSURE RUN TO ER350, WILL BE FULL TIME MONITOR WHEN BUILT IN SCADA AND WILL DO P2P THEM CCC 19108, CMCHOLAN 3-6-23 FINISHED UP PAPERWORK AND SUMMITED ISO, CCC 19108 CMCHOLAN 3-6-23 0859 CCC-27261 DID P2P WITH GAS CONTROL ON MP, GAGE INSP OK, CCC 27123 CMCHOLAN EBLANTON 4-26-23 1600
23026260800 | RETIRE PAPER CHART | [5 empty] | 78.59 | 138.8485 | -60.2585 |  |  |  | 2023-03-06 | RETIRED PAPER CHART AND IS NOW CONNECTED ER350, CMCHOLAN CCC 19108
23026262700 | EMER-INSTALL 5' OF 2"PMMP MAIN | [5 empty] | 3582.24 | 7460.3676 | -3878.1276 |  |  |  | 2023-03-07 | WORKED WITH JO. 23026262700 INSTALLED 5FT OF 020 MAIN DUE TO LEAKING S/L TEE. TESTED 5FT OF 020, 010 TEE,010 COUPLING AND 020 PURGE END CAP FOR 1HR AT 90LBS.TEST OK. SOAP TEST 020 EFC AT OP. FOR 5MINS TEST OK. BHB NGF
23026262800 | EMER-RETIRE 5' OF 2"PMP MAIN | [5 empty] | 726.04 | 124.7348 | 601.3052 |  |  |  | 2023-03-07 | FROM MAIN TO MTR FOR 5MINS AT 90LBS.TEST OK. SOAP TEST FINAL TIE IN AT OP.TEST OK. BHB NGF WORKED WITH JO. 23026262700 INSTALLED 5FT OF 020 MAIN DUE TO LEAKING S/L TEE. TESTED 5FT OF 020, 010 TEE,010 COUPLING AND 020 PURGE END CAP FOR 1HR AT 90LBS.TEST OK. SOAP TEST 020 EFC AT OP. FOR 5MINS TEST OK. BHB NGF -- 010 S/L ELECTROFUSION TEE LEAKING AT SADDLE CONNECTION TO MAIN.REPLACED 5FT OF MAIN WITH NEW S/L TEE AND 020 PURGE END CAP.TESTED FOR 1HR AT 90LBS. TEST OK. SOAP TEST EFC COULPING AT OP. FOR 5MINS.TEST OK.TEST S/L FOR 3905
23026263000 | INSTALL 5875' OF 2"/4"PMMP ENV | [5 empty] | 763454.52 | 728668.2681 | 34786.2519 |  |  |  | 2023-09-12
23026263100 | RETIRE 6090' OF 4"BSMP MAIN | [5 empty] | 0 | 124.7348 | -124.7348 |  |  |  | 2023-09-12
23026263400 | INSTALL 40'-4" PMMP | [5 empty] | 24778.88 | 25145.0229 | -366.1429 |  |  |  | 2023-04-11
23026263500 | RETIRE 20'-4" PMMP | [5 empty] | 98.08 | 124.7348 | -26.6548 |  |  |  | 2023-04-11
23026264300 | EMER-INSTALL 5' OF 4"PMMP MAIN | [5 empty] | 267.86 | 7456.0229 | -7188.1629 |  |  |  | 2023-03-10 | INSTALLED 3' OF 4" PL MAIN W/ EFC AND BF DE CAP- TEST 90# FOR 20MINS PER FOL DBANKS- SOAP TEST FINALTIEIN @ OP TEST OK- BHB NGF CONTENT VERIFIED DMARSTO 3/10/23
23026264400 | EMER-RETIRE 520'- 4"PAIP MAIN | [5 empty] | 325.83 | 124.7348 | 201.0952 |  |  |  | 2023-03-10 | ABN 520' SECTION OF 4" PL MAIN- PURGE ABN SECTION OF MAIN W/ AIR UNTIL 0% SUSTAINED- DMARSTO 3/10/23
23026264700 | INSTALL 100' OF 3"PMLP MAIN | [5 empty] | 21922.36 | 29526.7351 | -7604.3751 |  |  |  | 2023-04-19 | 100' OF BS MAIN RETIRED AND REPLACED W/3" PE PL MAIN DUE TO CORROSION
23026264800 | RETIRE 100' OF 3"BSLP MAIN | [5 empty] | 6487.75 | 124.7348 | 6363.0152 |  |  |  | 2023-04-19 | 100' OF BS MAIN RETIRED AND REPLACED W/3" PE PL MAIN DUE TO CORROSION
23026265100 | INSTALL 10'-3"PMLP | [5 empty] | 203249.18 | 37610.5067 | 165638.6733 |  |  |  | 2023-06-02 | INSTALLED 10 FT OF PL TEST FROM POINT A TO B 90 LB FOR 20 MIN TEST OK SOAP TEST 2 CPLG AND ALL BAG HOLES AT OP BHBNGF MAIN READ -0.601 INSTALLED 2 ANODES
23026265200 | RETIRE 10'-3" BSLP | [5 empty] | 190.67 | 120.2184 | 70.4516 |  |  |  | 2023-06-02 | RETIRED 10 FT OF 3 IN BS PIPE PURGED OUT AND SEALED THE INLINE TEE SIDE
23026265400 | EMER - INSTALL 12' - 2" PMMP | [5 empty] | 9462.49 | 5370.5784 | 4091.9116 |  |  |  | 2023-04-06 | TEST 2 IN MAIN FROM POINT A TO B TEST 90 LB FOR 20 MIN SOAP TEST TIEINS AT OP BAR HOLE BANKS NO GAS FOUND
23026265500 | EMER - RETIRE 12' - 2" PMMP | [5 empty] | 165.55 | 124.7348 | 40.8152 |  |  |  | 2023-04-06
23026266300 | EMER-INSTALL 3' OF 2"PMMP MAIN | [5 empty] | 4867.28 | 7671.8121 | -2804.5321 |  |  |  | 2023-02-22
23026266400 | EMER-RETIRE 3' OF 2"PMP MAIN | [5 empty] | 0 | 124.7348 | -124.7348 |  |  |  | 2023-02-22
24026346100 | EMER - INSTALL 2'-2" PMMP | [5 empty] | 0 | 9472.4549 | -9472.4549 | 2024-01-01 | 2024-12-31 | 2024-06-05 | 2024-06-05
23026267300 | RETIRE ~60'-4" BSLP | [5 empty] | 136.28 | 120.2184 | 16.0616 |  |  |  | #N/A
23026267700 | EMER-RETIRE 40' OF 6"BSLP MAIN | [5 empty] | 8203.54 | 9430.1038 | -1226.5638 |  |  |  | 2023-03-16
23026267800 | INSTALL 580' OF 2"PMMP MAIN | [5 empty] | 35753.76 | 40516.7801 | -4763.0201 |  |  |  | 2023-06-08
23026268200 | INSERT 160' OF 3"PMLP MAIN | [5 empty] | 15778.59 | 20952.5602 | -5173.9702 |  |  |  | 2023-04-14
23026268300 | RETIRE 160' OF 4"BSLP MAIN | [5 empty] | 8055.67 | 117.7346 | 7937.9354 |  |  |  | 2023-04-13
23026268400 | INSTALL 2000' OF 2"PMMP MAIN | [5 empty] | 56232.52 | 83632.6185 | -27400.0985 |  |  |  | 2023-04-21
23026268800 | RETIRE ER350 UNIT | [5 empty] | 116.17 | 117.7346 | -1.5646 |  |  |  | 2023-04-12
23026270100 | RETIRE REG STATION# 1020 | [5 empty] | 1847.24 | 10605.8819 | -8758.6419 |  |  |  | #N/A | RETIRED STATION AND REMOVED REGS, MONITORED PRESSURE FOR 30 MIN AFTER RETIREMENT, SOAPED BLING FLANGES AND PLUGS, CCC 77786, CMCHOLAN 6-20-24 1500
24026335400 | EMER - INSTALL 2'-2" PMMP | [5 empty] | 7568.56 | 5032.0911 | 2536.4689 | 2024-01-01 | 2024-12-31 | 2024-03-28 | 2024-03-28
23026271200 | INSTALL LEGACY ERX | [5 empty] | 2465.58 | 2907.8819 | -442.3019 |  |  |  | 2023-04-03 | INSTALLED LEGACY ERX IN PLACE OF OLD RTU AND TRANSMITTER EBLANTON 4-3-23
23026271600 | PAPER ONLY TO SET UP WMS FAC | [5 empty] | 14353.75 | 139.7346 | 14214.0154 |  |  |  | #N/A | THIS JOB IS TO CREATE FUNCTIONS AND FACILITIES FOR THE TEMPORARY SKID REGUL ATOR SETTING RWILLIAMS PUT TEMP STATION BACK TOGETHER, CMCHOLAN 6-26-2023
23026272200 | INSTALL 200' OF 2"PMMP MAIN | [5 empty] | 27418.37 | 23237.6457 | 4180.7243 |  |  |  | 2023-06-16
23026272300 | EMER-INSTALL 3" NC POLY VALVE | [5 empty] | 6810.69 | 7421.5276 | -610.8376 |  |  |  | 2023-04-28 | REPLACED BROKEN CRITICAL VLV WITH NEW 030 POLY VLV. TEST PIPE,VLV,&CPLGS 90#1HOUR, TG. ST LTI OK. BHBNGF. R.CRAWFORD 4-28-23
23026272400 | EMER-RETIRE 3"PV C16-87 | [5 empty] | 85.95 | 117.7346 | -31.7846 |  |  |  | 2023-04-28 | REFER TO JOB#-23026272300 FOR COMMENTS. R.CRAWFORD 4-28-23
23026272600 | INSTALL 875' OF 2"PMMP MAIN | [5 empty] | 29299.51 | 32780.4095 | -3480.8995 |  |  |  | 2023-05-09
23026272700 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 2367.44 | 5551.3568 | -3183.9168 |  |  |  | 2023-04-25
23026272800 | EMER - RETIRE 5'-2" PMMP | [5 empty] | 0 | 112.7299 | -112.7299 |  |  |  | 2023-04-25
24026351600 | EMER - INSTALL 2'-2" PMMP | [5 empty] | 2939.49 | 5505.7838 | -2566.2938 | 2024-01-01 | 2024-12-31 | 2024-07-30 | 2024-07-30
23026273000 | INSTALL 20'-4"PMMP W/NEW VALVE | [5 empty] | 20711.38 | 13458.2914 | 7253.0886 |  |  |  | 2023-06-26 | LOWERED 4" MP PE MAIN,REPLACED CRITICAL VLV,TEST MAIN@90IB 1HR,TIED IN W/2 EF CPLG'S, SOAP TEST TIE IN,MOVE CV TO SOFT SURFACE 06/26/2023 HMCKUNE
23026273100 | RETIRE 20'-4"PMMP W/C19-314 | [5 empty] | 0 | 117.7346 | -117.7346 |  |  |  | 2023-06-26
23026273300 | INSTALL 290' OF 4" PMMP | [5 empty] | 80935.68 | 48321.0935 | 32614.5865 |  |  |  | 2023-06-30
23026273400 | RETIRE 283' OF 3" BSMP | [5 empty] | 0 | 67.1159 | -67.1159 |  |  |  | 2023-06-30
24026316000 | EMER - INSTALL 2'-3" PMLP | [5 empty] | 6877.79 | 9590.2924 | -2712.5024 | 2024-01-01 | 2024-12-31 | 2024-02-13 | 2024-02-13
23026273800 | RETIRE 2" POLY VALVE C9-113 | [5 empty] | 3847.88 | 117.7346 | 3730.1454 |  |  |  | #N/A | LEAKING CV ON STEM.REMOVED CV AND INSTALLED 3' OF 020PMP.TESTED PURGE TEE AND 3FT OF MAIN FOR 1HR AT 90LBS.TEST OK.SOAP TEST EFC'S AT OP FOR 5MINS AT OP.TEST OK. BHB NGF. REMOVED CV C9-113.
23026273900 | INSTALL 441 REG (WEST RUN) | [5 empty] | 4130.38 | 3436.7638 | 693.6162 |  |  |  | 2023-06-08 | (NOT ON-SITE GETTING PARTS TO COMPLETE JOB) G.HALE NOT ONSITE COLLECTING REG AND PARTS APARKS 05-18-23 1551 SWAPPED 461 REGS FOR 441 REGS 57S 1 3/4 ORFICE BROWN SPRING IN BOTH CONTROL AND MONITOR MAJOR INSP. COMPLETED ON BOTH REGS INLET@90# MON@55# CON@47# CCC# 33177 NOT ONSITE PAPER WORK ONLY APARKS 06-19-23 1000
23026274000 | RETIRE 461 REGS (WEST RUN) | [5 empty] | 0 | 117.7346 | -117.7346 |  |  |  | 2023-06-08
23026274301 | INSTALL 3400' OF 2"PMMP MAIN | [5 empty] | 82979.94 | 79169.604 | 3810.336 |  |  |  | 2023-09-14
23026276300 | EMER-INSTALL 2"POLY VALVE | [5 empty] | 6885.74 | 10283.4841 | -3397.7441 |  |  |  | 2023-06-27 | INSTALLED NEW CRIT.VLV. TEST VLV FOR 1 HOUR, TG. TEST 2 BYPASS, TG. TEST ALL TEES, TG. ST LTI'S, TG. ALL TIME FOR JOB# 23186718700 TO BE CHARGED BACK TO THIS JOB, R.CRAWFORD 6-23-23 REFER TO JOB# 23026276400 FOR COMMENTS. R.CRAWFORD 6-27-23
23026276400 | EMER-RETIRE 2"VALVE C14-27 | [5 empty] | 0 | 139.1159 | -139.1159 |  |  |  | 2023-06-27 | REFERENCE COMMENTS FOR JOB # 23026276300. R.CRAWFORD 6-23-23 REPLACED BROKEN CV. TEST NEW CV AND PIPE WITH IT 90#1HR, TG. TEST ALL TEES 9#5MINS, TG. TEST BYPASS' 90#1HOUR, TG. ST ALL FINAL TI'S, TG. R.CRAWFORD 6-27-23
23026276900 | RETIRE 250' OF 3"BSLP MAIN | [5 empty] | 1716.17 | 4585.4374 | -2869.2674 |  |  |  | 2023-06-27 | ABDN 252 FT OF 3 IN BS MAIN SOAP TEST 4 PAC CLAMPS AT OP FOR 5 MIN SOAP TEST END CAP AT OP FOR 5 MIN BHBNGF INSTALLED 1ANODE PURGED OUT OLD MAIN AND SEALED MAIN LEFT 36 FT LINE MARKER AT END
23026277000 | EMER-INSTALL 15' OF 8"PMLP MN | [5 empty] | 19444.34 | 23129.0935 | -3684.7535 |  |  |  | 2023-08-10 | INSTALLED 8 IN PL MAIN TEST FROM POINT A TO POINT B SOAP TEST ALL PAC CLAMPS AND CPLG AT OP FOR 5 MIN BHBNGF INSTALLED 2 ANODE
23026277100 | EMER-RETIRE 15' OF 8"BSLP MN | [5 empty] | 307.27 | 139.1159 | 168.1541 |  |  |  | 2023-08-10 | ABDN 11 FT 8 IN BS MAIN INSTALLED 11 8 IN PL MAIN TEST 90 LB FOR 1 HHR SOAP TEST FINAL TIE IN AT OP FOR 5MIN BHBNGF
23026277200 | EMER-RETIRE 55' OF 6"PMLP MN | [5 empty] | 5550.64 | 4206.4374 | 1344.2026 |  |  |  | 2023-06-14 | RETIRED 52' OF 6'-P-LP WITH E/F COUPLING AND DEAD END CAP. PURGED 52' OF ' MAIN OUT OF SERVICE. SOAP TESTED FINAL CONNECTION FOR 5 MINTES AT OP. TEST OKAY.
23026277300 | INSTALL 265' OF 6"PMMP MAIN | [5 empty] | 29277.24 | 71789.4841 | -42512.2441 |  |  |  | 2023-08-31 | JOB COMPLETED. 08312023
23026277400 | RETIRE 285' OF 6"PMMP MAIN | [5 empty] | 439.67 | 139.1159 | 300.5541 |  |  |  | 2023-08-31 | JOB COMPLETED
23026277900 | EMER - INSTALL 69'-6" PMLP | [5 empty] | 31362.92 | 35367.5186 | -4004.5986 |  |  |  | 2023-06-08 | INSTALLED 40' 060 PMP TESTED FOR 1HR AT 90LBS.TEST OK. SOAP TEST TIE INS AT OP.TEST OK. BHB NGF WORKED WITH 558
23026278000 | EMER - RETIRE 69'-6" BSLP | [5 empty] | 124.77 | 139.1159 | -14.3459 |  |  |  | 2023-06-08 | ABDN 40' OF 6'' STEEL WORKED WITH 557.
23026278200 | EMER-INSTALL 185' OF 4"PMLP | [5 empty] | 41688.69 | 28939.243 | 12749.447 |  |  |  | 2023-06-16
23026278300 | EMER-RETIRE 181' OF 4"BSLP MN | [5 empty] | 0 | 139.1159 | -139.1159 |  |  |  | 2023-06-16
23026278401 | INSTALL 2300' OF 2"/4"PMMP MN | [5 empty] | 116796.05 | 101330.2336 | 15465.8164 |  |  |  | 2023-11-16
23026279100 | INSTALL 300' OF 2"PMIP MAIN | [5 empty] | 7749.44 | 17364.828 | -9615.388 |  |  |  | 2023-07-28
23026280100 | RETIRE 10' OF 10"CSMP MAIN | [5 empty] | 273.6 | 139.1159 | 134.4841 |  |  |  | 2023-09-07
23026280800 | EMER-INSTALL 62' OF 4"PMLP | [5 empty] | 63661.35 | 28754.8748 | 34906.4752 |  |  |  | 2023-07-12 | INSTALLE 40 FT 4 IN MAIN TEST FROM POINT A TO POINT B 90 LB FOR 1 HR TEST ALL TEES AT 90 LB FOR 5 MIN SOAP TEST EFC AND BOLTD CPLG AT O OP FOR 5 MIN SOAP TEST 1 IN END CAP AT OP FOR 5 MIN INSTALL 1 ANODE
23026280900 | EMER-RETIRE 62' OF 4"BSLP | [5 empty] | 2161.53 | 139.1159 | 2022.4141 |  |  |  | 2023-07-12 | RETIRED 36 FT OF BS AND 9 FT OF PL 4 IN LOW PRESSURE MAIN
23026282700 | EMER-ABANDON 333' OF 2"PAMP | [5 empty] | 2936.25 | 3839.4374 | -903.1874 |  |  |  | 2023-07-06 | ABND CUL-DE-SAC AFTER HIT LINE BY OTHER CONTRACTOR PER ENGINEER/FOL AFTER VERIFICATION NO CUSTOMERS ON GAS FOR SECTION OF MAIN TO BE ABND
23026283200 | INSTALL 480' OF 2"PMMP MAIN | [5 empty] | 47476.79 | 59017.0935 | -11540.3035 |  |  |  | 2023-08-17 | TWALKER/KY 10-20-23: REQUESTED CUSTOMER REFUND FOR THE CUSTOMER PAID RELOCA TION PROJECT.
23026283300 | RETIRE 400' OF 2"BSMP MAIN | [5 empty] | 0 | 139.1159 | -139.1159 |  |  |  | 2023-08-17
23026283400 | EMER - INSTALL 5'-3" PMMP | [5 empty] | 4304.94 | 10280.7214 | -5975.7814 |  |  |  | 2023-07-24 | INST 5'- 3" NEW PL MAIN BY ENGINEERED PLAN. MCRAIG 7/10/23
23026283500 | EMER - RETIRE 5'-3" PMP | [5 empty] | 36.39 | 139.1159 | -102.7259 |  |  |  | 2023-07-24 | RETIRE 5' OF 3" PL MAIN DUE TO LEAK PER ENGINEERED PLAN. MCRAIG 7/10/23
23026284300 | EMER-INSTALL 490' OF 2"PMMP | [5 empty] | 133294.53 | 184478.0101 | -51183.4801 |  |  |  | 2023-08-10 | BARE STEEL LP MAIN LEAKING, CREW WAS UNABLE TO EXPOSE LEAK, ABANDONED BS MAIN AND BORED IN 490'OF 2"P- PRE AND POST CAMERA COMPLETED-PT NEW MAIN 90LBS FOR 1HR PER ENGINEERING-SOAP TESTED TIE IN AT OP
23026284400 | EMER-RETIRE 520' OF 4"BSMP MN | [5 empty] | 223.9 | 139.1159 | 84.7841 |  |  |  | 2023-08-10 | REPLACED 493' OF 4'' S MP WITH 2'' PMP DUE TO GRADE 1 LEAK.DPI D304338.
23026284500 | INSTALL 80'4" PMLP | [5 empty] | 23619.02 | 47424.0373 | -23805.0173 |  |  |  | 2023-07-27 | TEST FROM POINT A TO B TO C 90 LB FOR 1 HR TEST OK TEST FINAL TIE IN AT OP OK BHBNGF INSTALLED 3 ANODES MAIN READ -0.591 TEST PAAC CLAMPS AT OP OK
23026284600 | RETIRE 80'-4" BSLP | [5 empty] | 4684.11 | 139.1159 | 4544.9941 |  |  |  | 2023-07-27 | RETIRED 60 FT OF BS 4IN MAIN PURGED OUT AND REMOVED PIPE
23026285300 | EMER - RETIRE 159'-3"BSLP | [5 empty] | 5197.96 | 10816.0505 | -5618.0905 |  |  |  | 2023-07-27 | ABDN 159' OF 3'' BS LP.LEAK UNDER DRIVEWAY APPRON.MAIN NOT FEEDING ANY S/L.LEFT 15' OF 3'' ACTIVE. SOAP TEST END CAP AT OP FOR 5MINS TEST OK. BHB NGF. INSTALLED ANODE DENSO WRAPPED.
23026285400 | RETIRE 300' OF 2"PIP MAIN | [5 empty] | 17543.67 | 16251.9287 | 1291.7413 |  |  |  | #N/A | CAPPED OFF HP INLET TO ABANDONED STATION AND REMOVED STATION AND FENCE. CONTRACTORS REMOVED ALL VISIBLE LINE MARKERS AND RISERS IN TRAILER PARK. JOSH PASLEY 2/5/24
23026285500 | RETIRE REG STATION #1129 | [5 empty] | 19139.56 | 22153.7376 | -3014.1776 |  |  |  | 2023-11-30 | CCC#54039
23026286300 | RETIRE 306' OF 3"BSLP MAIN | [5 empty] | 10623.01 | 7586.4374 | 3036.5726 |  |  |  | 2023-09-05 | ABN. 40' OF PLASTIC AND 306' OF STEEL MAIN. PURGE ALL GAS OUT. PLUGGED ENDS NGF AFTER PURGED. USED EF EC, ST AT OP, TG. R.CRAWFORD 9-5-23
23026286800 | INSTALL 100' OF 2"PMIP MAIN | [5 empty] | 17844.41 | 8938.3422 | 8906.0678 |  |  |  | 2023-09-05 | SPOTTED UTILITIES WITH VAC TRUCK. BORED IN 100' OF 020 P MAIN, PRESSURE TEST 1 HOUR AT 90#, TG. ST LTI, TG. R.CRAWFORD 9-5-23
24026329400 | EMER - INSTALL 2'-3" PMLP | [5 empty] | 6384.11 | 4221.248 | 2162.862 | 2024-01-01 | 2024-12-31 | 2024-03-01 | 2024-03-01
23026287700 | RETIRE ~30'-4" PMP | [5 empty] | 6450.91 | 124.9261 | 6325.9839 |  |  |  | #N/A
23026288000 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 267.7 | 3242.0133 | -2974.3133 |  |  |  | 2023-08-10 | RELACED 5' OF 020 PMP DUE TO SOCKET ON TEE LEAKING. TESTED 5' OF 020 FOR 1HR AT 90LBS.TEST OK. SOAP TEST 2 2'' EFC AT OP. TEST OK. BHB NGF.
23026288100 | EMER - RETIRE 5'-2" PMMP | [5 empty] | 1.39 | 119.4953 | -118.1053 |  |  |  | 2023-08-10 | RELACED 5' OF 020 PMP DUE TO SOCKET ON TEE LEAKING. TESTED 5' OF 020 FOR 1HR AT 90LBS.TEST OK. SOAP TEST 2 2'' EFC AT OP. TEST OK. BHB NGF.
23026288200 | INSTALL VERIZON MODEM | [5 empty] | 1861.82 | 4954.3422 | -3092.5222 |  |  |  | 2023-08-17
23026288300 | RETIRE SATELLITE COMM EQUIP | [5 empty] | 0 | 119.4953 | -119.4953 |  |  |  | 2023-08-17
24026361500 | EMER - INSTALL 2'-3" PMLP | [5 empty] | 4884.17 | 3524.9349 | 1359.2351 | 2024-01-01 | 2024-12-31 | 2024-09-27 | 2024-09-27
23026289100 | INSTALL FENCE | [5 empty] | 23214.65 | 26355.734 | -3141.084 |  |  |  | 2023-10-30 | NOT ON SITE, OFFICE PAPERWORK
23026290800 | INSERT/INSTALL 160'-3"PMLP MN | [5 empty] | 45855.9 | 46254.1681 | -398.2681 |  |  |  | 2023-10-20 | TEST FROM POINT A TTO B 90 LB FOR 1 HR TEST 2 IN HV TEE AND 2 IN MAIN FROM POINT A TO B 90 LB FOR 1 HR
23026290900 | RETIRE 60' OF 3"BSLP MAIN | [5 empty] | 7967.87 | 119.4953 | 7848.3747 |  |  |  | 2023-10-20 | ABDN 82 FT OF 4" BS MAIN AND 143 FT OF 2 " BS MAIN PURGED OUT AND SEALED UP AND INSTALLED ALL NEW 3 "PL MAIN
24026328300 | EMER - INSTALL 26'-6" PMLP | [5 empty] | 14201.79 | 28720.319 | -14518.529 | 2024-01-01 | 2024-12-31 | 2024-02-27 | 2024-02-28 | REPLACED 26FT OF 060 S WITH 060 P DUE TO ATMOS CORR. TESTED PIPE FOR 1HR AT 90LBS.TEST OK. SOAP TEST BOTH COUPLINGS AT OP FOR 5MINS.TEST OK. BHB NGF. INSTALLED 2 ANODES. DENSO WRAP MAIN.
23026292501 | INSTALL 800' OF 2-4" PMMP | [5 empty] | 232050.11 | 229159.9279 | 2890.1821 |  |  |  | 2023-10-06
24026349900 | EMER - INSTALL 3'-2" PMMP | [5 empty] | 8029.62 | 7024.6066 | 1005.0134 | 2024-01-01 | 2024-12-31 | 2024-07-10 | 2024-07-10
23026293800 | RETIRE 88'-2"&4" PMMP | [5 empty] | 12669.1 | 119.4953 | 12549.6047 |  |  |  | #N/A
23026294500 | RETIRE 338' OF 4"BSLP MAIN | [5 empty] | 13645.62 | 4190.6844 | 9454.9356 |  |  |  | 2023-12-14
23026294800 | INSTALL 225' OF 2"PMMP MAIN | [5 empty] | 29004.09 | 19109.6064 | 9894.4836 |  |  |  | 2023-12-05
24026371800 | EMER - INSTALL 3'-2" PMMP | [5 empty] | 19259.53 | 14865.4926 | 4394.0374 | 2024-01-01 | 2024-12-31 | 2024-12-22 | 2024-12-22
24026373800 | EMER - INSTALL 3'-2" PMMP | [5 empty] | 6014.6 | 4350.0713 | 1664.5287 | 2024-01-01 | 2024-12-31 | 2024-12-22 | 2024-12-22
23026296300 | RETIRE 1479'-6" CS&PMMP | [5 empty] | 577.39 | 122.9261 | 454.4639 |  |  |  | #N/A
23026296800 | EMER - INSTALL 40'-4" PMMP | [5 empty] | 48671.57 | 32230.3112 | 16441.2588 |  |  |  | 2023-10-31
23026296900 | EMER - RETIRE 40'-4" CSMP | [5 empty] | 0 | 122.9261 | -122.9261 |  |  |  | 2023-10-31
23026297200 | EMER - INSTALL 13'-2" PMMP | [5 empty] | 5013.23 | 9353.5801 | -4340.3501 |  |  |  | 2023-10-12 | VALVE RETIRED.SOAP TEST END CAPS AT OP FOR 5MINS. TEST OK.BHB NGF LEAKING 020 P CRITICAL VALVE.LEAKING FROM STEM.RETIRED VALVE WITH 020 BYPASS.TESTED BYPASS AS MAIN FOR 1HR AT 90LBS.TEST OK INSTALLED TWO END CAPS AT VALVE TO ABDN VALVE.020 BYPASS MADE TO ACVTIVE MAIN AFTER
23026297300 | EMER - RETIRE 2'-2" PMP | [5 empty] | 5943.6 | 122.9261 | 5820.6739 |  |  |  | 2023-10-12 | VALVE RETIRED.SOAP TEST END CAPS AT OP FOR 5MINS. TEST OK.BHB NGF LEAKING 020 P CRITICAL VALVE.LEAKING FROM STEM.RETIRED VALVE WITH 020 BYPASS.TESTED BYPASS AS MAIN FOR 1HR AT 90LBS.TEST OK INSTALLED TWO END CAPS AT VALVE TO ABDN VALVE.020 BYPASS MADE TO ACVTIVE MAIN AFTER
24026343700 | EMER - INSTALL 3'-3" PMMP | [5 empty] | 10177.86 | 6477.801 | 3700.059 | 2024-01-01 | 2024-12-31 | 2024-05-31 | 2024-05-31
23026300800 | EMER-INSTALL 5' OF 3"PMLP | [5 empty] | 5389.28 | 4600.4752 | 788.8048 |  |  |  | 2023-10-10
23026300900 | EMER-RETIRE 5' OF 3"PLP MAIN | [5 empty] | 0 | 122.9261 | -122.9261 |  |  |  | 2023-10-10
23026301000 | EMER-INSTALL 2' OF 4"PMMP MAIN | [5 empty] | 3269.69 | 4675.4752 | -1405.7852 |  |  |  | 2023-05-31
23026301100 | EMER-RETIRE 2' OF 4"PAMP MAIN | [5 empty] | 0 | 122.9261 | -122.9261 |  |  |  | 2023-05-31
24026353200 | EMER - INSTALL 3'-4" PMMP | [5 empty] | 3109.71 | 7993.6359 | -4883.9259 | 2024-01-01 | 2024-12-31 | 2024-08-01 | 2024-08-01
23026303700 | EMER - INSTALL 5' OF 2" PMMP | [5 empty] | 617.17 | 147.9261 | 469.2439 |  |  |  | 2023-11-03
23026303800 | EMER - RETIRE 3' OF 2" PAMP | [5 empty] | 114.6 | 124.9261 | -10.3261 |  |  |  | 2023-11-03
23026303900 | EMER-INSTALL 3'-2" PMMP MAIN | [5 empty] | 2236.53 | 5599.8489 | -3363.3189 |  |  |  | #N/A
23026304000 | EMER-RETIRE 3'-2"PAMP MAIN | [5 empty] | 0 | 124.9261 | -124.9261 |  |  |  | #N/A
23026304100 | RETIRE 667' OF 2"PMMP MAIN | [5 empty] | 4930.16 | 5490.3441 | -560.1841 |  |  |  | 2023-11-29 | ABND MAIN ON STATE ST
23026305300 | EMER-INSTALL 11'-2" PMMP | [5 empty] | 5063.47 | 17054.8912 | -11991.4212 |  |  |  | 2023-11-13 | INSTALLED 11' NEW 2"PL MAIN DURING DAMAGE/HIT LINE FROM BANK CAVE IN INSIDE UTILITY CONTRACTORS EXCAVATION-BHB,NGF-NGF UPON DEP
23026305400 | EMER-RETIRE 11'-2" PMMP | [5 empty] | 383.65 | 124.9261 | 258.7239 |  |  |  | 2023-11-13 | ABND 11'SECTION OF MAIN FOR DAMAGE
23026305800 | RETIRE CHAIN LINK FENCE | [5 empty] | 0 | 502.1911 | -502.1911 |  |  |  | #N/A
23026307700 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 3856.33 | 5646.8353 | -1790.5053 |  |  |  | 2023-12-08
23026307800 | EMER - RETIRE 5'-2" PMP | [5 empty] | 0 | 123.4493 | -123.4493 |  |  |  | 2023-12-08
23026307900 | EMER-INSTALL 10'-4"PMMP/VALVE | [5 empty] | 8083.2 | 6246.9893 | 1836.2107 |  |  |  | 2023-12-18 | LEAKING MAIN VALVE.LEAK FROM STEM.REPLACED WITH NEW VALVE. TESTED 10' OF 040 WITH VALVE FOR 1HR AT 90LBS.TEST OK. SOAP TEST 2 EFC AT OP FOR 5MINS.TEST OK. BHB NGF
23026308000 | EMER-RETIRE 10'-4"PMP/C8-150 | [5 empty] | 147.12 | 123.4493 | 23.6707 |  |  |  | 2023-12-18 | LEAKING MAIN VALVE.LEAK FROM STEM.REPLACED WITH NEW VALVE. TESTED 10' OF 040 WITH VALVE FOR 1HR AT 90LBS.TEST OK. SOAP TEST 2 EFC AT OP FOR 5MINS.TEST OK. BHB NGF
23026308900 | EMER INSTALL 4' OF 3" PMMP | [5 empty] | 2998.44 | 3360.6855 | -362.2455 |  |  |  | 2023-12-22 | INST 4'- 3" PL MAIN PER ENGINEERED PLAN AND GAS STANDARDS. TEST NEW MAIN @ 90LB 5MIN OK. SOAP TEST TIE-IN @ OP OK. WORKED ON 12/19/23. MCRAIG 12/22/23
23026309000 | EMER RETIRE 4' OF 3" PMP | [5 empty] | 218.46 | 123.4493 | 95.0107 |  |  |  | 2023-12-22 | RETIRE 4' OF 3" PL MAIN DUE TO LEAK IN ACCORDNANCE W/ ENGINEERING AND GAS STANDARDS. TEST NEW 4' PL @ 90LB 5MIN OK. SOAP TEST TIE-IN. WORKED 12/19/23. MCRAIG 12/22/23
24026335100 | EMER - INSTALL 4'-3" PMMP | [5 empty] | 12497.25 | 9960.0387 | 2537.2113 | 2024-01-01 | 2024-12-31 | 2024-03-27 | 2024-03-27
23026309200 | EMER-RETIRE 4' OF 3"PMP MAIN | [5 empty] | 259.03 | 123.4493 | 135.5807 |  |  |  | #N/A | RETIRE 4'- 2" PL MAIN DUE TO LEAKING WELD. WRK 12/20/23. MCRAIG 1/3/24
24026330300 | EMER - INSTALL 5'- 2" PMMP | [5 empty] | 10905.49 | 11353.2418 | -447.7518 | 2024-01-01 | 2024-12-31 | 2024-04-02 | 2024-04-02 | EXPOSED TWO ISOLATED STEEL COUPLINGS ON 020 PMP MAIN. REPLACED SECTION OF MAIN WHILE ON BYPASS.TESTED BYPASS FOR 20MINS AT 90LBS.TEST OK. TESTED MAIN FOR 1HR AT 90LBS.TEST OK. SOAP TEST COUPLINGS AT OP.TEST OK.
23026309400 | EMER - RETIRE 5'-4" PMP | [5 empty] | 158.95 | 123.4493 | 35.5007 |  |  |  | #N/A | CPLNG ON TEE LEAKING REPLACED 6 FT OF MAIN TEST NEW MAIN 90 LB FOR 20 MIN SOAP TEST FINAL TIE IN AT OP BHBNGF
24026336800 | EMER - INSTALL 5' OF 2" PMMP | [5 empty] | 5104.57 | 3378.146 | 1726.424 | 2024-01-01 | 2024-12-31 | 2024-03-27 | 2024-03-27
24026310500 | RETIRE VALVE & 5' OF 2" PMP | [5 empty] | 3446.12 | 160.3697 | 3285.7503 |  |  |  | #N/A
24026348700 | EMER - INSTALL 5' OF 2" PMMP | [5 empty] | 8763.23 | 5410.4082 | 3352.8218 | 2024-01-01 | 2024-12-31 | 2024-06-26 | 2024-06-26
24026317800 | EMER - INSTALL 5'-2" PMIP | [5 empty] | 8355.27 | 6092.2548 | 2263.0152 | 2024-01-01 | 2024-12-31 | 2024-02-16 | 2024-02-16 | INSTALLED NEW 020 P ML. TESTED @ 90# 1 HOUR. SOAP TEST TIE IN COUPLING. MAR KER BALL AT EOM. J HOWARD 2-16-24
24026311900 | EMER-RETIRE 5' OF 2"PAMP MAIN | [5 empty] | 22.89 | 123.4493 | -100.5593 |  |  |  | #N/A | FOUND LEAK ON MAIN INSTALLED 5 FT OF MAIN TEST 90 LB FOR 20 MIN ABDN 5 FT OF MAIN
24026312700 | RETIRE 310' OF 2"PMMP MAIN | [5 empty] | 1540.57 | 4362.2109 | -2821.6409 |  |  |  | #N/A | ABN MAIN DUE TO DEMO OF HOUSES - ABN 2" PLASTIC MAIN WITH 2" EF DEAD END CAP - SOAP TEST @ OP FOR 5 MIN TEST GOOD
24026368000 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 4545.67 | 12185.6111 | -7639.9411 | 2024-01-01 | 2024-12-31 | 2024-12-09 | 2024-12-09
24026314100 | EMER-RETIRE 5' OF 4"PAMP MAIN | [5 empty] | 29.31 | 160.3697 | -131.0597 |  |  |  | #N/A
24026320800 | EMER - INSTALL 5'-3" PMIP | [5 empty] | 25129.82 | 6546.5769 | 18583.2431 | 2024-01-01 | 2024-12-31 | 2024-02-22 | 2024-02-22 | INSTALLED 4' OF 3" PL IP MAIN TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7 PSIG
24026314700 | EMER-RETIRE 120'- 8"BSMP MAIN | [5 empty] | 0 | 160.3697 | -160.3697 |  |  |  | #N/A
24026338200 | EMER - INSTALL 5'-3" PMMP | [5 empty] | 12009.27 | 3698.1293 | 8311.1407 | 2024-01-01 | 2024-12-31 | 2024-03-29 | 2024-03-29
24026316800 | RETIRE 9920' OF 4"/6"BSLP MAIN | [5 empty] | 717.72 | 118.4933 | 599.2267 |  |  |  | #N/A | GURU RETIRED 1-4"DRIP. SM 6/11.25
24026332800 | EMER - INSTALL 5'-4" PMIP | [5 empty] | 8388.17 | 3664.146 | 4724.024 | 2024-01-01 | 2024-12-31 | 2024-03-16 | 2024-03-16
24026318700 | EMER - RETIRE 11' OF 2" PMP | [5 empty] | 180.42 | 160.3697 | 20.0503 |  |  |  | #N/A | RETIRE 11' OF 2" P MP MAIN DUE TO LEAK PER ENGINEERED TIE-IN PLAN. WORKED ON 2/7. MCRAIG 2/21/24
24026319600 | INSTALL SOLAR BACK UP UNIT | [5 empty] | 6617.58 | 10754.1928 | -4136.6128 |  |  |  | #N/A
24026321000 | PAPER-RETIRE ~250-3" PLP | [5 empty] | 0 | 160.3697 | -160.3697 |  |  |  | #N/A | JOB COMPLETED
23026309300 | EMER - INSTALL 5'-4" PMMP | [5 empty] | 3958.19 | 8753.3832 | -4795.1932 | 2024-01-01 | 2024-12-31 | 2024-03-05 | 2024-03-06 | TEST 6 FT MAIN90LB FOR 20 MIN OK TEST 3 EF TEES 90 LB FOR 5 MIN SOAP TEST 2 EFC AT OP FOR 5 MINSOAP TEST 2 END 1 IN END CAPS AT OP OK BHBNGF
24026321200 | INSTALL EQUIPMENT & BUILDING | [5 empty] | 177086.72 | 181907.9279 | -4821.2079 |  |  |  | #N/A | CCC 86957 CCC 89138
24026321300 | RETIRE EQUIPMENT | [5 empty] | 0 | 160.3697 | -160.3697 |  |  |  | #N/A
24026322700 | INSTALL MIWI W/ SOLAR | [5 empty] | 18428.99 | 25805.1928 | -7376.2028 |  |  |  | #N/A
24026322800 | RETIRE FACILITIES | [5 empty] | 339.76 | 160.3697 | 179.3903 |  |  |  | #N/A | CCC 95201
24026323900 | UPGRADE TO FULL TIME | [5 empty] | 15170.64 | 10457.1928 | 4713.4472 |  |  |  | #N/A | CONVERTER ER350 TO FULL TIME MONITOR WITH ACP, CCC 82460, CMCHOLAN 7-29-24 FILLED OUT PAPERWORK FOR SOLAR PANEL INSTALL, CCC 86978, CMCHOLAN 9-3-24 1050
24026324000 | UPGRADE TO FULL TIME | [5 empty] | 90.3 | 160.3697 | -70.0697 |  |  |  | #N/A | UPGRADED TO FULL TIME MONITORED WITH ACP, CCC 82460, CMCHOLAN 1343
24026324400 | UPGRADE TO FULL TIME | [5 empty] | 1964.52 | 10901.0487 | -8936.5287 |  |  |  | #N/A
24026324500 | UPGRADE TO FULL TIME | [5 empty] | 709.33 | 121.4465 | 587.8835 |  |  |  | #N/A
24026324600 | UPGRADE TO FULL TIME | [5 empty] | 8507.07 | 10901.0487 | -2393.9787 |  |  |  | #N/A | CCC 82823 SUPER SOLAR INSTALL FORM COMPLETE, CCC 86978, CMCHOLAN 9-3-24 1200
24026324700 | UPGRADE TO FULL TIME | [5 empty] | 568.65 | 121.4465 | 447.2035 |  |  |  | #N/A | CCC 82823
24026324800 | MIWI WITH SOLAR | [5 empty] | 10379.92 | 13977.0487 | -3597.1287 |  |  |  | #N/A
24026324900 | RETIRE | [5 empty] | 532.44 | 121.4465 | 410.9935 |  |  |  | #N/A
24026325700 | UPGRADE SCADA SYSTEM | [5 empty] | 9180.49 | 10627.0487 | -1446.5587 |  |  |  | #N/A
24026325900 | UPGRADE SCADA SYSTEM | [5 empty] | 362.79 | 121.4465 | 241.3435 |  |  |  | #N/A
24026326200 | UPGRADE SCADA SYSTEM | [5 empty] | 8523.81 | 10627.0487 | -2103.2387 |  |  |  | #N/A | CCC 82629 CMCOX 7/30/24
24026326300 | UPGRADE SCADA SYSTEM | [5 empty] | 462.23 | 121.4465 | 340.7835 |  |  |  | #N/A | CCC 82629 CMCOX 7/30/24
24026326400 | UPGRADE SCADA SYSTEM | [5 empty] | 2879.61 | 10627.0487 | -7747.4387 |  |  |  | #N/A | CCC-82971 CCC 87260, DID SOLAR PANEL PAPERWORK, CMCHOLAN 9-4-24 1600
24026326500 | UPGRADE SCADA SYSTEM | [5 empty] | 499.97 | 121.4465 | 378.5235 |  |  |  | #N/A | CCC-82971
24026347600 | EMER - INSTALL 7'-2" PMIP | [5 empty] | 6613.86 | 6644.7043 | -30.8443 | 2024-01-01 | 2024-12-31 | 2024-06-10 | 2024-06-10
24026328400 | EMER - RETIRE 26'-6" BSLP | [5 empty] | 2990.24 | 115.5402 | 2874.6998 |  |  |  | #N/A | REPLACED 26FT OF 060 S WITH 060 P DUE TO ATMOS CORR. TESTED PIPE FOR 1HR AT 90LBS.TEST OK. SOAP TEST BOTH COUPLINGS AT OP FOR 5MINS.TEST OK. BHB NGF. INSTALLED 2 ANODES. DENSO WRAP MAIN.
24026330000 | ABANDON S/L - DEMO/ CITY RQD | [5 empty] | 7688.07 | 6179.2921 | 1508.7779 |  |  |  | #N/A | SL ABN DUE TO DEMO OF BLDG. TAP CREW AND WELDER CAPPED SL AT TAP BHB NGF, MRK BALL AT TAP, SOAP TEST AT OP OK, PLUGGED EXSISTING LINE JOB EXECUTE W/CAPITAL PACKET
24026332600 | EMER INSTALL 10'-6" PMMP | [5 empty] | 32430.81 | 29701.1651 | 2729.6449 | 2024-01-01 | 2024-12-31 | 2024-03-15 | 2024-03-15
24026330400 | EMER-RETIRE 5'-2"PMMP | [5 empty] | 180.38 | 118.4933 | 61.8867 |  |  |  | #N/A | EXPOSED TWO ISOLATED STEEL COUPLINGS ON 020 PMP MAIN. REPLACED SECTION OF MAIN WHILE ON BYPASS.TESTED BYPASS FOR 20MINS AT 90LBS.TEST OK. TESTED MAIN FOR 1HR AT 90LBS.TEST OK. SOAP TEST COUPLINGS AT OP.TEST OK.
24026331300 | RETIRE 3"PLP S/L & C18-82 VALV | [5 empty] | 0 | 132.893 | -132.893 |  |  |  | #N/A
24026349700 | EMER INSTALL 2' OF 2" PMMP | [5 empty] | 6054.03 | 5242.4082 | 811.6218 | 2024-01-01 | 2024-12-31 | 2024-07-03 | 2024-07-03 | SOUTHERN OHIO TRENCHING HIT MISS MARKED 2" PL MP MAIN CUT OUT 2' OF MAIN AN D INSTALLED 2' TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 40 PSIG
24026331800 | RETIRE 3"BSLP S/L & C14-35 VLV | [5 empty] | 0 | 66.4465 | -66.4465 |  |  |  | #N/A
24026367000 | EMER INSTALL 5'-2" PMMP | [5 empty] | 7909.41 | 7419.9991 | 489.4109 | 2024-01-01 | 2024-12-31 | 2024-10-11 | 2024-10-11
24026332000 | EMER - RETIRE 1' OF 2"PAMP | [5 empty] | 295.06 | 121.4465 | 173.6135 |  |  |  | #N/A | REPAIRED DAMAGED SECTION OF PIPE. TEST REPAIR PIECE 90#20MINS, TG. ST LTI. TEST FOR SECONDARY DAMAGE OK. R.CRAWFORD 4-2-24
24026365000 | EMER-INSTALL 10' - 2" PMMP | [5 empty] | 3040.57 | 3276.1865 | -235.6165 | 2024-01-01 | 2024-12-31 | 2024-10-30 | 2024-10-30 | INST 10' OF 2" P MP MAIN PER ENGINEERED PLAN DUE TO FAC DAMAGE. MCRAIG 10/30/24
24026332200 | RETIRE 52' - 4" CSLP | [5 empty] | 12630.36 | 121.4465 | 12508.9135 |  |  |  | #N/A | PART OF CAPITAL JOB
24026314600 | EMER-INSTALL 170' OF 2"/4"PMMP | [5 empty] | 141557.61 | 145005.519 | -3447.909 | 2024-01-01 | 2024-12-31 | 2024-02-02 | 2024-02-05
24026333100 | EMER-RETIRE 18'-4"BSLP MAIN | [5 empty] | 0 | 121.4465 | -121.4465 |  |  |  | #N/A
24026333000 | EMER-INSTALL 18'-4"PMLP MAIN | [5 empty] | 20568.01 | 29428.3233 | -8860.3133 | 2024-01-01 | 2024-12-31 | 2024-04-30 | 2024-04-30
24026334200 | RETIRE 5' OF 2" PMP | [5 empty] | 47.65 | 121.4465 | -73.7965 |  |  |  | #N/A | FOUND COMPRESSION COUPLINGS LEAKING - SQUEEZED OFF MAIN WITH GAGE FOR PRESSURE VERIFICATION- PRESSURE REMAINED @ 53 PSIG TEST NEW PIPE @ 90 FOR 1 HR TEST GOOD - INSTALLED 5 FT
24026336400 | RETIRE ~71-4" PMMP S/L | [5 empty] | 2817.23 | 124.2298 | 2693.0002 |  |  |  | #N/A
24026336500 | INSTALL ~75'-4" PMMP S/L | [5 empty] | 26538.42 | 35134.784 | -8596.364 |  |  |  | #N/A | REPL SL WITH NEW 4" PLASTIC- TST SL AND MAIN IN ONE FOR 90LBS FOR 1HOUR TST OK- SOAP TST FINAL TIE IN @OP FOR 5MIN TST OK- BHB NGF- TROE
24026336600 | INSTALL GMB SETTING | [5 empty] | 23056.34 | 48285.9326 | -25229.5926 |  |  |  | #N/A
24026336700 | RETIRE GMB SETTING | [5 empty] | 0 | 65.2298 | -65.2298 |  |  |  | #N/A
24026355400 | EMER-INSTALL 2' OF 2"PMMP MAIN | [5 empty] | 4651.3 | 5647.5068 | -996.2068 | 2024-01-01 | 2024-12-31 | 2024-08-28 | 2024-08-28 | SERVICE TEE AND SERVICE FOR 5MIN @90LBS TST OK- TSTED GAUGE TEES @90LBS FOR 5MIN TST OK- SOAP TST DEAD END CAPS ON GAUGE TEES FOR 5MIN @OP TST OK INST 2' OF 2" PLASTIC MAIN- TST MAIN @90LBS FOR 1HOUR, TST OK- SOAP TST FINAL TIE IN POINT A AND POINT B @OP FOR 5MIN TST OK- BHB NGFTST 2 PURGE TEES 5MIN @90LBS TST OK- TEST 2X1"
24026336900 | EMER - RETIRE 5' - 2" PMMP | [5 empty] | 0 | 121.4465 | -121.4465 |  |  |  | #N/A
24026357700 | EMER-INSTALL 2' OF 3"PMMP MAIN | [5 empty] | 13806.96 | 15212.4136 | -1405.4536 | 2024-01-01 | 2024-12-31 | 2024-08-23 | 2024-08-23
24026350500 | EMER-INSTALL 2"VALVE KY-C1586 | [5 empty] | 3282.54 | 5722.6534 | -2440.1134 | 2024-01-01 | 2024-12-31 | 2024-07-01 | 2024-07-01
24026338100 | RETIRE 42'-2"&4" CSMP | [5 empty] | 96.62 | 118.4933 | -21.8733 |  |  |  | #N/A | START DATE OF INSTALL JOB WAS 5/20/24 - COMMIT DATE FOR INSTALL 5/30, COMMIT DATE FOR ABANDONMENT 5/17 - START DATE WAS AFTER COMMMIT DATE - RTINCHER 6-21-24
24026346300 | EMER-INSTALL 3' OF 2"PMMP MAIN | [5 empty] | 6040.26 | 8304.9467 | -2264.6867 | 2024-01-01 | 2024-12-31 | 2024-07-05 | 2024-07-05 | INSTALLED 3' 2" PL MIAIN DUE TO DAMAGE PER ENG. TIE IN PLAN
24026339000 | INSTALL OT NETWORK HARDWARE | [5 empty] | 5456.41 | 3063.0974 | 2393.3126 |  |  |  | #N/A | CCC#68493
24026339100 | RETIRE MODEM WITH IT UPGRADES | [5 empty] | 563.82 | 121.4465 | 442.3735 |  |  |  | #N/A
24026339400 | RETIRE 322'-4" CSLP | [5 empty] | 6251.56 | 8828.6617 | -2577.1017 |  |  |  | #N/A | ABD 322 FT OF CS MAIN TEST TEE 90 LB FOR 5 MIN SOAP TEST END CAP AT OP SOAP TEST 1 IN CAP AT OP BHBNGF ABDN 322 FT CS 4 IN MAIN SOAP TEST END CAP AT OP BLEW OUT ABDN MAIN AND SEALED THE END UP ON IT MARKER BALL AT DEAD END CAP
24026360200 | EMER-INSTALL 3' OF 2"PMMP MAIN | [5 empty] | 12791.75 | 12190.8831 | 600.8669 | 2024-01-01 | 2024-12-31 | 2024-09-04 | 2024-09-04 | PAPERWORK ISSUES CFD
24026339900 | RETIRE 25' OF 6"BSLP MAIN | [5 empty] | 4843.71 | 139.7787 | 4703.9313 |  |  |  | #N/A | REPLACED 56' OF 060 P LP DUE TO CROSS BORE IN SEWER. TESTED MAIN FOR 1HR AT 90LBS.TEST OK. TESTED TEMP BYPASS FOR 20MINS AT 90LBS.TESTS OK. SOAP TEST BOLTED COUPLINGS AT OP.TEST OK.SOAP TEST CLAPS AND SADDLES AT OP.TEST OK
24026340000 | EMER-INSTALL NEW PF REGULATOR | [5 empty] | 2398.18 | 5188.1947 | -2790.0147 |  |  |  | #N/A | CC 69018 NEW REG INSTALLED 04-17-2024 APARKS GHALE RHAYES CC 69018 INSTALLED PF REG SN 201920474068 AND ASV SN 201920474092 APARKS GHALE RHAYES 04-18-2024
24026340100 | EMER-RETIRE PF REGULATOR | [5 empty] | 1088.91 | 66.4465 | 1022.4635 |  |  |  | #N/A | CC 69018 REMOVED PF REG AND SLAMSHUT INSTALLED NEW PF AND SLAMSHUT ALPARKS GHALE RHAYES
24026340200 | INSTALL 600' OF 8"PMMP MAIN | [5 empty] | 388585.22 | 296422.5677 | 92162.6523 |  |  |  | 2025-02-25
24026362000 | EMER-INSTALL 3' OF 3"PMMP MAIN | [5 empty] | 18283.02 | 5267.5068 | 13015.5132 | 2024-01-01 | 2024-12-31 | 2024-09-17 | 2024-09-17
24026310000 | EMER-INSTALL 4' OF 2"PMIP MAIN | [5 empty] | 11757.28 | 6172.4499 | 5584.8301 | 2024-01-01 | 2024-12-31 | 2024-01-04 | 2024-01-04
24026342100 | EMER - RETIRE 2' OF 2"PMP MAIN | [5 empty] | 109.14 | 139.7787 | -30.6387 |  |  |  | #N/A | ABN 2' OF 2" P MP MAIN DUE TO DAMGE. PER ENGINEERED TIE-IN PLAN WORKED 5/2/24. MCRAIG 5/14/24
24026348000 | EMER-INSTALL 4' OF 3"PMMP MAIN | [5 empty] | 2333.5 | 6161.5865 | -3828.0865 | 2024-01-01 | 2024-12-31 | 2024-07-08 | 2024-07-08 | INST 4' OF 3" PLASTIC PIPE- TSTED PIPE FOR 20MIN @90LBS PER FOL - TST OK- SOAP TST FINSL TIE IN @OP FOR 5MIN TST OK- BHB NGF- TROE
24026342500 | RETIRE ~600'-2" PMMP | [5 empty] | 324.53 | 139.7787 | 184.7513 |  |  |  | #N/A
24026343200 | DEMO BLOCK BUILDING | [5 empty] | 0 | 279.5575 | -279.5575 |  |  |  | #N/A
23026309100 | EMER-INSTALL 4'OF 2"PMMP MAIN | [5 empty] | 2952.18 | 4579.9666 | -1627.7866 | 2024-01-01 | 2024-12-31 | 2024-01-02 | 2024-01-03 | INST 4'- 2" PL MAIN. TEST MAIN @ 90LB 5MIN OK. SOAP TEST TIE-IN @ OP OK. BHB NGF. CGI MAIN AND SVC OK. WRK 12/20/23. MCRAIG 1/3/24
24026343400 | RETIRE 4"POLY VALVE C19-270 | [5 empty] | 796.71 | 139.7787 | 656.9313 |  |  |  | #N/A | REPLACED VALVE C19-270 NEW VALVE NUMBER KY-C1414 REFER TO JOB#24-0263433-00 A WILLIAMSON 6-6-2024
24026311800 | EMER-INSTALL 5' OF 2"PMMP MAIN | [5 empty] | 2941.72 | 5455.4783 | -2513.7583 | 2024-01-01 | 2024-12-31 | 2024-02-20 | 2024-02-20 | REPLACED 5 FT OF MAIN TEST ALL MATERIAL TO ALL GAS STANDERDS TEST MAIN 90 FOR 20 MIN TEST ALL TEES 90 FOR 5 MIN SOAP TEST EFC AND SL END CAPS AT OP FOR 5 MIN BHBNGF
24026343600 | RETIRE 15'-8" CSLP | [5 empty] | 110 | 136.633 | -26.633 |  |  |  | #N/A
24026345300 | RETIRE 350' OF 4"CSLP MAIN | [5 empty] | 10006.29 | 10488.3069 | -482.0169 |  |  |  | #N/A | RETIRED 4" CS MAIN DUE TO CORROSION- PURGED ABN MAIN OUT- CAPPED ABN MAIN- SOAP TST DEAD END CAP OF MAIN FOR 5MIN @OP TST OK- BHB NGF- INST 17LB ANODE INST TESTS STATION @ END OF MAIN- TROE GURU ADDED A TEST STATION FACILITY. SM 3/28/25
24026314000 | EMER-INSTALL 5' OF 4"PMMP MAIN | [5 empty] | 519.5 | 1932.1928 | -1412.6928 | 2024-01-01 | 2024-12-31 | 2024-02-20 | 2024-02-20
24026346400 | EMER-RETIRE 3' OF 2"PMMP MAIN | [5 empty] | 157.44 | 139.7787 | 17.6613 |  |  |  | #N/A | ABN 3' 2" PL MAIN PER ENG. TIE IN PLAN ABDN 322 FT CS 4 IN MAIN SOAP TEST END CAP AT OP BLEW OUT ABDN MAIN AND SEALED THE END UP ON IT MARKER BALL AT DEAD END CAP
24026357000 | EMER-INSTALL 50' OF 4"PMLP | [5 empty] | 19570.62 | 21585.4343 | -2014.8143 | 2024-01-01 | 2024-12-31 | 2024-09-10 | 2024-09-10 | INSTALLED NEW 040 P PIPE DUE TO CORROSION. TEST PIPE 90#1HOUR, TG. ST LTI, TG. MAIN READIN TAKEN AT "GOOD" SECTIONS OF PIPE FOR NEW INSTALL R.CRAWFORD 9-10-24
24026346700 | EMER-RETIRE 8' OF 4"PMLP | [5 empty] | 10.1 | 139.7787 | -129.6787 |  |  |  | #N/A | REPLACED TWO SECTIONS OF MAIN DUE TO DAMAGES. ALL WORK PREFORMED BY GAS STANDARDS AND TESTED BY GAS STANDARDS. ALL TESTING AND CLERICAL PAPERWORK ON CAPITAL PACKET.
24026375200 | EMER-INSTALL 6' OF 2"PMMP MAIN | [5 empty] | 6850.53 | 7800.6918 | -950.1618 | 2024-01-01 | 2024-12-31 | 2024-12-11 | 2024-12-11
24026348100 | EMER-RETIRE 4' OF 3"PMMP MAIN | [5 empty] | 0 | 139.7787 | -139.7787 |  |  |  | #N/A
24026348200 | INSTALL ~30'-4" PMMP | [5 empty] | 16880.63 | 17592.9326 | -712.3026 |  |  |  | 2025-01-16 | INST 34' OF 4" PLASTIC MAIN AND 13' OF 2" PLASTIC MAIN- AND 58' OF 4" SL- TSTED ALL NEW MAIN FOR 90LBS FOR 1 HOUR- TST OK- SOAP TST FINAL TIE IN @OP FOR 5MIN TST OK- BHB NGF- TROE
24026348300 | RETIRE ~30'-4" PMMP | [5 empty] | 3460.68 | 124.2298 | 3336.4502 |  |  |  | #N/A | ABN 25' OF 4" PLASTIC MAIN DUE TO CONFLICT WITH WATER BOX- SOAP TST DEAD END CAP ON 4" FOR 5MIN @OP TST OK- SOAP TST DEAD END CAP FOR 2" MAIN @OP FOR 5MIN TST OK- TROE
24026344300 | EMER-INSTALL 6' OF 4" PMIP | [5 empty] | 20651.9 | 14215.6055 | 6436.2945 | 2024-01-01 | 2024-12-31 | 2024-05-28 | 2024-05-28
24026348800 | EMER-LEAK RETIRE C14-37 | [5 empty] | 693.84 | 139.7787 | 554.0613 |  |  |  | #N/A
24026351800 | EMER-INSTALL 8' OF 3" PMMP | [5 empty] | 6274.49 | 8361.8798 | -2087.3898 | 2024-01-01 | 2024-12-31 | 2024-07-26 | 2024-07-26 | INSTALLED 8' OF NEW 030 P PIPE AFTER REMOVING DAMAGED SECTION OF MAIN. TEST PIPE 90#20MINS, TG. PER R.VANDERPOOL. R.CRAWFORD 7-26-24
24026349400 | RETIRE 10' OF 3"PMP MAIN | [5 empty] | 21.79 | 139.7787 | -117.9887 |  |  |  | #N/A
24026346600 | EMER-INSTALL 8' OF 4"PMLP | [5 empty] | 6502.78 | 11094.6001 | -4591.8201 | 2024-01-01 | 2024-12-31 | 2024-08-29 | 2024-08-29 | REPLACED TWO SECTIONS OF MAIN DUE TO DAMAGES. ALL WORK PREFORMED BY GAS STANDARDS AND TESTED BY GAS STANDARDS. ALL TESTING AND CLERICAL PAPERWORK ON CAPITAL PACKET.
24026350600 | EMER-RETIRE C15-66 POLY VALVE | [5 empty] | 0 | 139.7787 | -139.7787 |  |  |  | #N/A
24026350800 | PAPER ONLY MP RETIREMENT | [5 empty] | 0 | 139.7787 | -139.7787 |  |  |  | #N/A
24026332100 | INSERT 50' OF 3" PMLP | [5 empty] | 25644.18 | 34491.8294 | -8847.6494 | 2024-01-01 | 2024-12-31 | 2024-05-13 | 2024-05-29
22026235300 | INST 1865'-8" & 390'-2" PMMP | [5 empty] | 1121157.31 | 895303.7297 | 225853.5803 | 2024-01-01 | 2024-12-31 | 2024-05-08 | 2024-06-11
24026351500 | EMER - RETIRE 2'-2" PMP | [5 empty] | 14.54 | 136.633 | -122.093 |  |  |  | #N/A | REMVED 2' OF 2" DAMAGED PLASTIC PIPE DUE TO HIT LINE- REPLACED WIT NEW 2" PLASTIC PIPE TSTED FOR 90LBS FOR 20MIN PER FOL SOAP TST POINT A AND POINT B @OP FOR 5MIN TST OK- TROE
23026307300 | INSTALL ~100'-2" PMIP | [5 empty] | 40892.69 | 23189 | 17703.69 | 2024-01-01 | 2024-12-31 | 2024-01-01 | 2024-02-01
24026351900 | EMER-RETIRE 8' OF 3" PMP | [5 empty] | 6.23 | 139.7787 | -133.5487 |  |  |  | #N/A | TOOK OUT 8' OF 030 P PIPE. REPLACED W/ 8' OF NEW 030 P PIPE. R.CRAWFORD 7-26-24
24026342400 | INSTALL ~585'-2" PMMP | [5 empty] | 81606.34 | 85571.2987 | -3964.9587 | 2024-01-01 | 2024-12-31 | 2024-07-08 | 2024-07-30
24026352700 | EMER - RETIRE 2'-2" PMMP | [5 empty] | 122.63 | 139.7787 | -17.1487 |  |  |  | #N/A | JO COMMENTS ON 557 AND 2412
22026237301 | INSTALL 11,150'-8"6"4"2" PMMP | [5 empty] | 3177275.55 | 2580803.0362 | 596472.5138 | 2024-01-01 | 2024-12-31 | 2024-05-06 | 2024-12-17 | ADV JTOY FOL
24026353900 | RETIRE 164' OF 4"CSMP MAIN | [5 empty] | 419.02 | 68.2637 | 350.7563 |  |  |  | #N/A
24026316701 | INSTALL 11245' OF 2"PMMP MAIN | [5 empty] | 1084887.24 | 1012154.1196 | 72733.1204 | 2024-01-01 | 2024-12-31 | 2024-08-05 | 2024-12-12
22026236901 | INSTALL 11300'-2" PMMP | [5 empty] | 2626590.92 | 2204167.7449 | 422423.1751 | 2024-01-01 | 2024-12-31 | 2024-04-01 | 2024-10-21
23026300401 | INSTALL 1150' 4/2" PMMP | [5 empty] | 291755.2 | 220213.1673 | 71542.0327 | 2024-01-01 | 2024-12-31 | 2024-04-22 | 2024-05-16 | TTOY 5/6/24: ATTEMPTED TO REVISE DUE TO UNDERRUN, MATERIAL PO NOT FILLED,
24026355100 | EMER - RETIRE 12'-2" PMMP | [5 empty] | 482.5 | 1059.1985 | -576.6985 |  |  |  | #N/A | CONTRACTOR HIT 020 PMP MAIN DIGGING FOOTER FOR BUILDING.SQUEEZED OFF TO MAKE SAFE. END CAP INSTALLED BEFORE DITCH OF FOOTER. SOAP TEST END CAP AT OP.TEST OK. BHB NGF. ADV FOL OF ENCROACHMENT. ABDN 12FT OF MAIN.
23026287300 | INSTALL 121'-4" CSMP | [5 empty] | 188332.63 | 153650.3163 | 34682.3137 | 2024-01-01 | 2024-12-31 | 2024-09-06 | 2024-09-20
24026355500 | EMER-RETIRE 2' OF 2"PAMP MAIN | [5 empty] | 7.56 | 127.2637 | -119.7037 |  |  |  | #N/A | REMOVED 2' OF 2" PLASTIC MAIN- INDTALLED 2" OF 2" PLASTIC MAIN- TST FOR 1HR @90LBS TST OK- SOAP TSTT FINAL TIE IN @OP FOR 5MIN TST OK- TROE
22026205401 | INSTALL 1330'-4" PMMP | [5 empty] | 288486.41 | 229795.8687 | 58690.5413 | 2024-01-01 | 2024-12-31 | 2024-02-15 | 2024-03-26
24026356000 | INSTALL 475' OF 2"PMMP MAIN | [5 empty] | 138117.86 | 124485.9173 | 13631.9427 |  |  |  | 2025-05-29
24026356100 | RETIRE 420' OF 2"BSLP MAIN | [5 empty] | 0 | 127.2637 | -127.2637 |  |  |  | #N/A
22026236700 | INSTALL 134'-4" PMLP | [5 empty] | 27660 | 32463.7981 | -4803.7981 | 2024-01-01 | 2024-12-31 | 2024-02-20 | 2024-02-27 | INST 160'- 4" P LP MAIN FOR SEWER PROJECT PER ENGINEERED TIE-IN PLAN. MCRAIG 2/27/24
24026356300 | RETIRE 4" POLY VALVE C16-184 | [5 empty] | 6591.98 | 127.2637 | 6464.7163 |  |  |  | #N/A | CUT OUT CRITICAL VALVE C16-184 PER ENGINEERED TIE-IN AND GS. MCRAIG 9/20/24
24026356400 | RETIRE 4"PLP SERVICE LINE | [5 empty] | 2580.83 | 127.2637 | 2453.5663 |  |  |  | #N/A | ABANDONED 4" SERVICE LINE USING EXISTING 4" CURB VALVE. THE REMAINING SERVICE LINE IS TO BE ABANDONED ON CAPITAL ABANDONMENT ORDER 24-0263168-00. JOSH PASLEY 8/13/24
18026795501 | INSTALL 14,600'-2,4,6,8" PMMP | [5 empty] | 3426043.78 | 3061100.231 | 364943.549 | 2024-01-01 | 2024-12-31 | 2024-04-01 | 2024-11-15
24026357100 | EMER-RETIRE 50' OF 4"BSLP MAIN | [5 empty] | 8645.9 | 127.2637 | 8518.6363 |  |  |  | #N/A | RETIRED PIPE DUE TO CORROSION FOR INSTALL OF NEW 040 P PIPE. MAIN READING TAKEN AT "GOOD" SECTIONS OF PIPE FOR INSTALL OF NEW PIPE. R.CRAWFORD 9-10-24
24026357600 | RETIRE 490' OF 2"/4"PMP MAIN | [5 empty] | 3022.51 | 4637.6504 | -1615.1404 |  |  |  | #N/A | ABN PARTIAL MAIN - SOAP TEST DEAD END CAP @ OP FOR 5 MIN TEST GOOD -
24026358801 | INSTALL 4200' OF 2"/4"PMMP | [5 empty] | 782267.64 | 884925.4499 | -102657.8099 |  |  |  | 2025-05-21
24026358900 | RETIRE 914' OF 4"BSMP MAIN | [5 empty] | 0 | 135.7529 | -135.7529 |  |  |  | #N/A
24026310800 | INSTALL 1400' OF 2" PMMP | [5 empty] | 67204.19 | 90861.9332 | -23657.7432 | 2024-01-01 | 2024-12-31 | 2024-06-17 | 2024-07-10
24026360600 | RETIRE 10'-2" PMMP | [5 empty] | 2874.37 | 127.2637 | 2747.1063 |  |  |  | #N/A | RETIRE 10' OF 2" P MP MAIN PER ENGINEERED PLAN AND GS TO OFFSET MAIN FOR SEWER PROJECT. MCRAIG 10/29/24
24026360700 | INSTALL 230' OF 4"PMLP MAIN | [5 empty] | 19505.93 | 12568.7288 | 6937.2012 |  |  |  | 2025-05-21
24026360800 | RETIRE 620' OF 4"BSLP MAIN | [5 empty] | 110 | 135.7529 | -25.7529 |  |  |  | #N/A
24026361300 | INSTALL 750'-2" PMMP | [5 empty] | 206114.64 | 209702.6457 | -3588.0057 |  |  |  | 2025-03-19
24026363400 | PAPER ONLY MP RETIREMENT | [5 empty] | 0 | 127.2637 | -127.2637 |  |  |  | #N/A
24026321100 | INSTALL 1400' OF 2" PMMP MAIN | [5 empty] | 68220.66 | 53956.9279 | 14263.7321 | 2024-01-01 | 2024-12-31 | 2024-04-22 | 2024-05-14
24026363700 | RETIRE 580' OF 4"BSMP MAIN | [5 empty] | 0 | 135.7529 | -135.7529 |  |  |  | #N/A
22026241701 | INSTALL 1425' OF 2"PMMP MAIN | [5 empty] | 698687.73 | 729573.6534 | -30885.9234 | 2024-01-01 | 2024-12-31 | 2024-04-10 | 2024-05-08
24026365100 | EMER-RETIRE 10' - 2" PMMP | [5 empty] | 2.82 | 135.7529 | -132.9329 |  |  |  | #N/A | CUT OUT 10' OF 2" P MP MAIN FROM DAMAGE. MCRAIG 10/30/24
23026296200 | INSTALL 1429'-6" PMMP | [5 empty] | 975067.42 | 234311.6314 | 740755.7886 | 2024-01-01 | 2024-12-31 | 2024-06-07 | 2024-06-28 | LEVEL 2 VARIANCE EXPLANATION APPROVED AND LOCATED IN JO WORKSPACE IN WMSDOC S. D.LEMONS 9/23/2024
24026368600 | INSTALL 640' OF 2" PMMP | [5 empty] | 50384.93 | 48981.3497 | 1403.5803 |  |  |  | 2025-06-10
24026368800 | INSTALL 5' OF 6" PMLP (PIF) | [5 empty] | 53924.5 | 22844.1865 | 31080.3135 |  |  |  | 2025-02-03
24026368900 | RETIRE 5' OF 6" BSLP | [5 empty] | 806.6 | 135.7529 | 670.8471 |  |  |  | #N/A
24026369000 | INSTALL 65'-8" PMLP | [5 empty] | 144966.81 | 108434.8433 | 36531.9667 |  |  |  | 2025-06-06 | INSTALLED NEW 8" PLASTIC MAIN, TESTED NEW MAIN AT 90PSI FOR 1 HR, TEST OKAY SOAP TEST FINAL TIE IN AT OP 5 MINS, TEST OKAY, BHBNGF
24026369100 | RETIRE 70'-12'&6" BSLP | [5 empty] | 6.18 | 108.1134 | -101.9334 |  |  |  | #N/A | INSTALLED NEW 8" PLASTIC MAIN,TESTED NEW MAIN AT 90PSI FOR 1HR, TEST OKAY SOAP TEST FINAL TIE IN AT OP 5MINS, TEST OKAY, BHBNGF
24026370400 | INSTALL RTU BUILDING | [5 empty] | 0 | 170.7529 | -170.7529 |  |  |  | #N/A
24026370600 | INSTALL 32'-6" PMLP | [5 empty] | 8317.84 | 29726.9608 | -21409.1208 |  |  |  | 2025-05-30
24026370700 | RETIRE 20'-6" BSLP | [5 empty] | 8109.18 | 112.4469 | 7996.7331 |  |  |  | #N/A
24026371100 | EMER-INSTALL 6' OF 8"PMMP | [5 empty] | 5742.34 | 5613.764 | 128.576 |  |  |  | 2025-05-09 | INSTALLED 6' OF 8" PLASTIC TO REPAIR DAMAGE, TEST 90# FOR 1.0 HR TEST OK SOAP TEST FINAL TIE IN AT OP 5 MINS, TEST OK
24026371200 | EMER-RETIRE 6' OF 8"PMP MAIN | [5 empty] | 397.39 | 111.0024 | 286.3876 |  |  |  | #N/A | ABANDONED 6' OF 8"PMP AND REPLACED WITH 6' OF 8" PMP. TEST 90# 1.0 HR TEST OK. SOAP TEST FINAL TIE IN AT OP 5 MINS TEST OK
24026371600 | EMER - INSTALL 5' - 2" PMMP | [5 empty] | 6372.3 | 4001.8556 | 2370.4444 |  |  |  | 2025-05-09 | CUST . CUT A 2' MAIN IN HALF WITH A DITCH WITCH - PRESSURE TEST @ 90 FOR 1 HOUR - SOAP TEST LAST CONNECTION @ OP FOR 5 MIN TEST GOOD
24026371700 | EMER - RETIRE 5' - 2" PMMP | [5 empty] | 45.7 | 111.0024 | -65.3024 |  |  |  | #N/A | CUST. CUT 2' MAIN IN HALF WITH A DITCH WITCH - REPLACED DAMAGED PIPED - PRESSURE TEST @ 90 FOR 1 HOUR TEST GOOD -
24026372500 | REPLACE VSAT WITH AT&T MODEM | [5 empty] | 6289.92 | 7998.4639 | -1708.5439 |  |  |  | #N/A | CCC 119698 SWITCHED PRIMARY COMMS FROM SAT TO CELL POINT 2 POINT VERIFIED WITH GAS CONTROL
24026372600 | REPLACE VSAT | [5 empty] | 0 | 111.0024 | -111.0024 |  |  |  | #N/A
24026372700 | INSTALL SOLAR BACKUP | [5 empty] | 7232.8 | 9877.4639 | -2644.6639 |  |  |  | #N/A
24026373100 | INSTALL SOLAR BACKUP | [5 empty] | 7699.73 | 9877.4639 | -2177.7339 |  |  |  | #N/A | INSTALL COMPLETE APARKS 02-12-25 1318 CCC 106887
24026351200 | INSTALL 150' OF 2"PMIP MAIN | [5 empty] | 14499.2 | 12159.6055 | 2339.5945 | 2024-01-01 | 2024-12-31 | 2024-09-02 | 2024-09-13
24026375300 | EMER-RETIRE 6' OF 2"PMMP MAIN | [5 empty] | 0 | 111.0024 | -111.0024 |  |  |  | #N/A
24026376700 | EMER - INSTALL 3'-2" PMMP | [5 empty] | 3141.8 | 7334.5817 | -4192.7817 |  |  |  | 2025-01-10 | JOB COMPLETE WITH CAPITAL PACKET
24026376800 | EMER - RETIRE 3'-2" PMP | [5 empty] | 6.4 | 112.4469 | -106.0469 |  |  |  | #N/A | COMPLETE WITH CAPITAL PACKET
24026376901 | INSTALL 1218'-6" PMMP | [5 empty] | 707094.52 | 626565.8286 | 80528.6914 |  |  |  | 2025-04-30
24026377000 | RETIRE 1140'-6" PMP | [5 empty] | 571.78 | 112.4469 | 459.3331 |  |  |  | #N/A
25026378600 | INSTALL 42' OF 2"/4" PMMP MAIN | [5 empty] | 26011.02 | 24410.382 | 1600.638 |  |  |  | 2025-02-26
25026378700 | RETIRE 30' OF 2"/4"PMMP MAIN | [5 empty] | 0 | 65.0024 | -65.0024 |  |  |  | #N/A
25026380600 | INSTALL SCADA VISIBILITY | [5 empty] | 10718.92 | 10377.5378 | 341.3822 |  |  |  | #N/A | CCC 113973 CCC-117909 CCC-122674 INSTALL ER350 AND SOLAR PANEL, CMCHOLAN 5-29-25
25026380800 | INSTALL SCADA VISIBILITY | [5 empty] | 9824.48 | 10377.5378 | -553.0578 |  |  |  | #N/A | CCC# 125214
25026395600 | EMER-INSTALL 3' OF 3"PMMP MAIN | [5 empty] | 330.23 | 1646.6381 | -1316.4081 |  |  |  | 2025-03-13
25026395700 | EMER-RETIRE 3' OF 3"PMP MAIN | [5 empty] | 435.29 | 160.2249 | 275.0651 |  |  |  | #N/A
25026398800 | INSTALL 3670' OF 2"/4"PMMP MN | [5 empty] | 130345.4 | 130832.2322 | -486.8322 |  |  |  | 2025-05-05
25026400900 | EMER - INSTALL 2'-4" PMMP | [5 empty] | 6330.01 | 12461.1986 | -6131.1886 |  |  |  | 2025-03-24
25026401000 | EMER - RETIRE 2'-4" PMP | [5 empty] | 0 | 137.1267 | -137.1267 |  |  |  | #N/A
25026405400 | EMER - INSTALL 2'-2" PMMP | [5 empty] | 3579.32 | 7065.0993 | -3485.7793 |  |  |  | 2025-05-30
25026405500 | EMER - RETIRE 2'-2" PMP | [5 empty] | 108.37 | 137.1267 | -28.7567 |  |  |  | #N/A
24026355200 | INSTALL 150'-4" PMLP | [5 empty] | 57369.63 | 34225.265 | 23144.365 | 2024-01-01 | 2024-12-31 | 2024-12-09 | 2024-12-18
25026410600 | EMER-INSTALL 3'-2"PMMP MAIN | [5 empty] | 59.2 | 178.4144 | -119.2144 |  |  |  | 2025-02-10 | REPL SECTION OF MAIN DUE TO FAILURE
25026410700 | EMER-RETIRE 3' OF 2"PMMP MAIN | [5 empty] | 59.14 | 138.4144 | -79.2744 |  |  |  | #N/A
18026762102 | INSTALL NEW GMB | [5 empty] | 551963 | 544123.4415 | 7839.5585 |  |  |  | 2021-09-20 | GCCC TICKET NOT REQUIRED AT THIS TIME 1/11/21 CFARIS 1/13/21 GCCC TICKET NOT REQUIRED AT THIS TIME CFARIS 1/26/21 GCCC TICKET NOT REQUIRED FOR THIS JOB CFARIS DID NOT ENTER PREMISE CCC TICKET NOT REQUIRED 3/8/21 CFARIS 3/10/21 GCCC TICKET NOT REQUIRED CFARIS CCC TICKET NOT REQUIRED 3/16/21 CFARIS CCC TICKET NOT REQUIRED 3/18/21 CFARIS CMCHOLAN 4-13-2021 CCC TICKET NOT REQUIRED ON 9/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK. ERX PLACED IN SERVICE ON 9/13/2021 CFARIS
18026845002 | INSTALL THREE SSD UNITS | [5 empty] | 151615.63 | 142836.3088 | 8779.3212 |  |  |  | #N/A | INSTALLED TRITON COUPON TS CSE AND DAIRYLAND SOLID-STATE DECOUPLER (SSD) - DAIRYLAND SSD-2/2-5.0-100R (50-60) WITH EXTERNAL OR INTERNAL ISOLATION SWITCHWITH SWX-100 ENCLOSURE. TS FAC 408323 AT CARDOME, TS FAC 409481 AT BEVINS FARM REAR AND NEW TS FAC 865373 ON BEVINS FARM FIELD 2/3 ALL HAVE 1/2" ZINC RIBBON FOR AC MITIGATION AND COUPON TS WITH SSD INSTALLED. TS FAC 408320 IS NOW FLUSH MOUNT READ ONLY TS / REUSED APX 600' OF ZINC RIBBON AND ZINC MAT AT TS 408323 / REUSED 585' AND INSTALLED 565' OF ZINC RIBBON AND NEW ZINC MAT AT NEW TS 865373 / REUSED APX 1000' OF ZINC AND ZINC MAT AT TS 409481 / JMM
19026856100 | RETIRE GAUGE | [5 empty] | 0 | 73.6972 | -73.6972 |  |  |  | 2021-09-20 | WAITING ON PE APPROVAL AND ISO SKETCH CCC TICKET NOT REQUIRED ON 9/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026856800 | INSTALL 3659'-2",4"&6" PMMP | [5 empty] | 1309555.48 | 1978069.5146 | -668514.0346 |  |  |  | 2021-06-28 | W. 2ND ST SEING TIES WILL NEED TO BE UPDATED ONCE ROAD CONSTRUCTION PROJECT IS COMPLETE. ALL POLES AND MANHOLES ARE BEING MOVED. OVERRUN EXPLANATION HAS BEEN COMPLETE AND LOADED INTO WMSDOCS WORKSPACE. D. LEMONS 12/23/2021
19026856900 | RETIRE 2166'- 2"-6" P/CS/BS | [5 empty] | 468.94 | 94.7274 | 374.2126 |  |  |  | 2021-07-01
19026874200 | INSTALL 4600' OF 2"/4"/6"PMMP | [5 empty] | 148082.56 | 193673.3471 | -45590.7871 |  |  |  | 2021-05-13 | TWALKER/KY 11-15-21: PROJECT UNDER RUN WAS DUE TO LESS ROCK ON SITE THAN PL ANNED AND NO STREET/HARD SURFACE REPAIRS REQUIRED THAT LOWER CONTRACT COST BY $25,000. LACK OF ROCK AND HARD SURFACE REPAIRS SPED UP CONSTRUCTION TIME AND LOWER COMPANY COST BY $XXXX AND SEGA WAS $4000 LOWER THAN ESTIMATE. COMPANY COST LOWER BY $3000 THAN ESTIMATE.
20026929300 | UPGRADE ELECTRONICS | [5 empty] | 6355.62 | 3038 | 3317.62 |  |  |  | 2021-04-26 | REPLACED EFC
20026929400 | UPGRADE ELECTRONICS | [5 empty] | 293.46 | 3038 | -2744.54 |  |  |  | 2021-11-18 | REPLACED EFC
20026929500 | UPGRADE ELECTRONICS | [5 empty] | 5670.86 | 3038 | 2632.86 |  |  |  | 2022-07-11 | RETIRED OLD MINNI-AT INSTALLED NEW EC350 BLONE 07-11-2022
20026929600 | UPGRADE ELECTRONICS | [5 empty] | 3403.36 | 3038 | 365.36 |  |  |  | 2021-04-26 | REPLACED EFC
20026929700 | UPGRADE ELECTRONICS | [5 empty] | 3985.53 | 3038 | 947.53 |  |  |  | 2021-11-16 | REPLACED EFC
20026935000 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 |  |  |  | 2021-04-16 | REPLACE EFC JOB ON HOLD 2020 BECAUSE OF COVID 19
20026935100 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 |  |  |  | 2021-11-18 | REPLACED EFC
20026935200 | RETIRE ELECTRONICS | [5 empty] | 742.7 | 73.3494 | 669.3506 |  |  |  | 2022-07-11 | RETIRED OLD MINI-AT INSTALLED NEW EC350 BLONE 07-11-2022
20026935400 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 |  |  |  | 2021-11-16 | REPLACED EFC
20026942000 | INSTALL I&C EQUIPMENT | [5 empty] | 14182.01 | 16155.4774 | -1973.4674 |  |  |  | 2021-09-20 | CCC# 30920 CCC TICKET NOT REQUIRED ON 9/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026943100 | INSTALL I&C EQUIPMENT | [5 empty] | 14038.9 | 16155.4774 | -2116.5774 |  |  |  | 2022-02-25 | CCC# 43654 INSTALLED ERX RETIRED PAPER CHART BLONE 2-25-2022
20026943200 | RETIRE GAUGE | [5 empty] | 259.73 | 91.4991 | 168.2309 |  |  |  | 2022-02-25 | INSTALLED NEW LEGACY ERX RETIRED PAPER CHART BLONE 2-25-2022
20026945400 | RETIRE 1431'-2"-4" BSLP | [5 empty] | 1066.35 | 94.7274 | 971.6226 |  |  |  | 2021-06-10 | ABANDONMENTS OF MAINLINE WERE DONE WITH JO# 20-0269755-00.
20026952900 | REPLACE ROOF | [5 empty] | 12246.18 | 4729 | 7517.18 |  |  |  | 2023-02-28
20026953701 | INSTALL 6100' OF 2"/4"PMMP | [5 empty] | 1646234.22 | 1430757.5003 | 215476.7197 |  |  |  | 2021-10-29 | TWALKER/KY 05-04-22: JOB OVER RUN DUE TO $65,000 SPEND ON OFF DUTY POLICE DUE TO HIGH CRIME/TRAFFIC AREA, STATE REQUIRED MILL/PAVING OF HOLME ST INCREASED CONTRACT COST BY $85,000. SEGA INCREASED BY $51,000 OVER EST.
20026953800 | RETIRE 8800' OF 4"/6"BSLP MAIN | [5 empty] | 0 | 240.2222 | -240.2222 |  |  |  | 2021-10-29
20026954400 | INSTALL 12,500' OF 6"PMMP | [5 empty] | 671261.21 | 584465.9269 | 86795.2831 |  |  |  | 2021-12-17 | GAS WAS ONLINE BEFORE COMMIT DATE. HAD TO FINISH UP RESTORATION AND PROJEC T INFO. STEVE CANOY 12/17/2021
20026954500 | INSTALL 72' OF 4"CSHP MAIN | [5 empty] | 50107.73 | 48741.5249 | 1366.2051 |  |  |  | 2021-05-13
20026954900 | INSTALL SKID REG STATION #1574 | [5 empty] | 83537.33 | 91083.0917 | -7545.7617 |  |  |  | #N/A | TUBE UP ONE RUN CCC #22458 CCC# 22583 CC# 23111 G.HALE 05-12-21 PLACED RUN 1 IN SERVICE ON 5/6/21 WITH TEMPORARY REGULATORS INSTALLED TO MEET COMMIT DATE WITH BUILDER RUN 2 OFF AND BLIND FLANGED PERMANENT EQUIPMENT ORDER WITH TENTATIVE DELIVERY DATE OF JUNE/JULY 2021 JOB CANNOT BE COMPLETED OR CLOSED OUT UNTIL PERMANENT EQUIPMENT IS INSTALLED CFARIS CCC# 43393 CCC# CALLED IN BY AL PARKS OR CONNER WIMPE CCC#55276 CWEMPE 2/15/22 GCCC# 56179 INSTALLED PERMANENT SLAMSHUT MOONEY'S COMMISSIONED STATION CWEMPE 2-16-22
20026960600 | INSTALL NEW TRANSMITTERS | [5 empty] | 9652.42 | 5450.0793 | 4202.3407 |  |  |  | 2022-08-22 | INSTALLED NEW INLET AND OUTLET ROSEMONT 4088B TRANSMITTERS GHALE 8-22-2022
20026960700 | RETIRE DAMAGE TRANSMITTER | [5 empty] | 542.77 | 80.9227 | 461.8473 |  |  |  | 2022-08-22 | INSTALLED NEW INLET AND OUTLET TRANSMITTERS GHALE 8-22-2022
20026974601 | INSTALL 6,500'-4"PMLP | [5 empty] | 2992726.14 | 2219393.0276 | 773333.1124 |  |  |  | 2023-10-13
20026974700 | RETIRE 6,900'-BSLP,CSLP,PLP | [5 empty] | 220 | 66.2135 | 153.7865 |  |  |  | 2023-12-21
20026975400 | INSTALL 2250'-2" PMMP | [5 empty] | 859560.09 | 623618.1819 | 235941.9081 |  |  |  | 2021-11-16 | PROJECT COMPLETED ON 11-16-2021 D.LEMONS 3/2/2022: PROJECT OVERRUN WAS DUE TO ADDITIONAL TIME REQUIRED TO C OMPLETE PROJECT DUE TO MULTIPLE CONTRACTORS IN AREA DURING PROJECT. ESTIMA TED FOR 645 MAN HOURS, BUT REQUIRED 1018 MAN HOURS. ADDITIONAL $85K IN CONT RACT EXPENSES, $36K IN LABOR COSTS WHICH LEAD TO INCREASE OF $32K IN SEGA. THERE WAS A SLIGHT REDUCTION IN OTHER COST TO ACCOUNT FOR THE $147K OVERRUN .
20026975500 | RETIRE 3515'-2",3",4"& 6" | [5 empty] | 142.7 | 107.2796 | 35.4204 |  |  |  | 2021-11-16 | PROJECT COMPLETE ON 11162021
20026978900 | RETIRE GMB SETTING | [5 empty] | 0 | 83.3805 | -83.3805 |  |  |  | 2021-09-20 | JOB WAS ON HOLD UNTIL 2021 GCCC TICKET NOT REQUIRED ON 9/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026979000 | RETIRE SERVICE | [5 empty] | 2450.84 | 83.3805 | 2367.4595 |  |  |  | 2021-04-22 | THIS IS PAPER KILL ONLY
20026979100 | RETIRE SERVICE | [5 empty] | 0 | 83.3805 | -83.3805 |  |  |  | 2021-04-21
20026979201 | INSTALL SERVICE TO GMB | [5 empty] | 201470.53 | 135908.7766 | 65561.7534 |  |  |  | 2021-04-29 | LEVEL 2 BUDGET VARIANCE LOADED INTO WMSSDOCS. D.LEMONS 9/22/21
20026979300 | RETIRE 12'-8" CSHP | [5 empty] | 3655.53 | 134.3805 | 3521.1495 |  |  |  | 2021-04-21
20026989800 | INSTALL 800'-2" PMMP | [5 empty] | 33245.15 | 25809.9211 | 7435.2289 |  |  |  | 2021-05-10
20026990800 | RETIRE INLET PIPING R 1502 | [5 empty] | 0 | 240.2222 | -240.2222 |  |  |  | 2021-10-29
20026991300 | INSTALL 350'-2" PMMP | [5 empty] | 19273.52 | 31069.259 | -11795.739 |  |  |  | 2021-03-03 | 337 FT 2 " MEDIUM PRESSURE MAIN INSTALLED BY STANLEY PIPELINE YELLOW MED IUM DENSITY.PIPE
21026101700 | INSTALL NEW GMB SETTING | [5 empty] | 40071.73 | 57815.8896 | -17744.1596 |  |  |  | 2021-11-16 | INSTALLED NEW GMB SETTING
21026102400 | RETIRE WOODFORD GMB | [5 empty] | 0 | 84.0131 | -84.0131 |  |  |  | 2021-11-16 | RETIRED OLD GMB SETTING AFTER NEW SETTING PLACED IN SERVICE
21026103000 | INSTALL CHAIN LINK FENCE | [5 empty] | 20497.91 | 16434.2505 | 4063.6595 |  |  |  | 2022-02-16 | RHAYES 08-24-2021 MONITORED FENCE INSTALLATION CCC 35764 CWEMPE PAPER WORK COMPLETION 2-16-22
21026106500 | EMER - INSTALL 4' OF 2"PMMP | [5 empty] | 7429.12 | 7343.079 | 86.041 |  |  |  | 2021-02-25
21026106600 | EMER - RETIRE 4' OF 2"PMMP | [5 empty] | 0 | 82.208 | -82.208 |  |  |  | 2021-02-25
21026107100 | INSTALL COMMUNICATIONS | [5 empty] | 3375.12 | 1691.2937 | 1683.8263 |  |  |  | 2021-12-10 | CCC#41275 CCC#17228 INSTALLED SUPER SOLAR KIT AND BATTERY UPGRADED TO RV50 CELL MODEM CONVERTED TO FULL TIME MONITORING RTU TICKET NUMBER 4339
21026107200 | RETIRE 33' OF 4"PMMP S/L | [5 empty] | 1.8 | 76.3208 | -74.5208 |  |  |  | 2021-11-17
21026107300 | INSTALL 140' OF 4"PMMP S/L | [5 empty] | 53188.18 | 57302.0236 | -4113.8436 |  |  |  | 2021-11-11
21026107500 | EMER- INSTALL120'-2" PL | [5 empty] | 2045.88 | 13083 | -11037.12 |  |  |  | 2021-06-10 | INSTALLED 155' OF 2" P-MP MAIN DUE TO LEAK, SEE CAPITAL PACKET JO# 21-0261075-00, CDESPAIN 3-4-21
21026107600 | RETIRE MAIN - LEAKAGE D304381 | [5 empty] | 14663.28 | 56.3197 | 14606.9603 |  |  |  | 2021-06-10 | REPLACED 155' OF 2" P- MP MAIN, FOUND 2BOLT COUPLING PL-PL CORRODED AND LEAKING, SQUEEZED OFF, REPLACED MAIN, SEE JO PACKET 21-0261075-00 CDESPAIN 3-4-21
21026109600 | INSTALL 351'-2" PMMP | [5 empty] | 28594.76 | 20339.7093 | 8255.0507 |  |  |  | 2021-07-15
21026111902 | INSTALL 7,500' OF 2"/6"PMMP | [5 empty] | 671698.12 | 670404.9715 | 1293.1485 |  |  |  | 2022-03-11 | LOWES (#207438) - MATERIAL FOR ECP - $27.62 + 10% = $30.38 U461423 9/2 3/2021 SITE SUPPLY (#207438) - MULCH LOGS - #424.00 + 10% = 466.40 U461423 9/23/2021
21026113900 | INSTALL 1300' OF 2"/4"PMMP | [5 empty] | 34584.47 | 66451.1814 | -31866.7114 |  |  |  | 2021-09-22 | MISSED COMMIT DATE DUE TO WEATHER UNDERRUN EXPLANATION: THE UNDERRUN VARIANCE IS DUE TO 50% ROCK EXCAVATION A ND 50% LESS DUST AND STONE. THE OVER HEAD EFFECT OF THESE REDUCTIONS ALSO PLAYED A FACTOR.
21026114000 | EMER - RETIRE 145' OF 2"BSLP | [5 empty] | 1254.24 | 3325.023 | -2070.783 |  |  |  | 2021-04-07 | RETIRED 146' OF 2" BSLP MAIN, SOAP TEST BOLTED DEAD END CAP AT OP, OK. SOAP TEST SADDLES AND PAC CLAMPS AT OP OK. BHB NGF. INSTALLED 9# ANODE. MAIN READ# -0.643. MAIN INSP OK. WHIMES 04/07/2021
21026114200 | INSTALL 100'-2" PMMP | [5 empty] | 19306.24 | 12690.4563 | 6615.7837 |  |  |  | 2022-07-28
21026114300 | RETIRE EFC | [5 empty] | 0 | 111.0751 | -111.0751 |  |  |  | 2021-04-21
21026115500 | INSTALL 9560' OF 2"PMMP | [5 empty] | 2294747.45 | 1674772.7999 | 619974.6501 |  |  |  | 2023-06-30
21026115600 | RETIRE 9,590' OF BSLP & OTHER | [5 empty] | 182.4 | 67.799 | 114.601 |  |  |  | 2023-06-30
21026117600 | RETIRE REG STATION 1522 | [5 empty] | 0 | 3579.3015 | -3579.3015 |  |  |  | 2023-06-22
21026118100 | INSTALL 5680'-2"/4" PMMP | [5 empty] | 156088.03 | 165876.9601 | -9788.9301 |  |  |  | 2022-07-20
21026118900 | INSTALL REGULATORS | [5 empty] | 4450.3 | 6803.6557 | -2353.3557 |  |  |  | 2021-09-21 | CCC# 38381 REPLACED REGULATORS ON 9/16/2021 GCCC TICKET NOT REQUIRED ON 9/21/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026119000 | RETIRE REGULATORS | [5 empty] | 572.72 | 85.0089 | 487.7111 |  |  |  | 2021-09-21 | REPLACED REGULATORS ON 9/16/21 CCC TICKET 38381 OBTAINED ON INSTALL JO CCC TICKET NOT REQUIRED ON 9/21/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026119400 | PM- INST FIL/SEP TOYOTA STA | [5 empty] | 3658431.91 | 1687500 | 1970931.91 |  |  |  | 2022-10-06
21026119500 | PM-ABAN FOR FILTER INST TOYOTA | [5 empty] | 522788.31 | 62500 | 460288.31 |  |  |  | 2022-10-06
21026119600 | PM- TURNER STATION REPLACEMENT | [5 empty] | 4896097.44 | 1012500 | 3883597.44 |  |  |  | 2022-08-23
21026119700 | PM- TURNER STATION ABANDONMENT | [5 empty] | 379030.64 | 62500 | 316530.64 |  |  |  | 2022-08-23
21026120200 | PM-INS PIG REC/FILTER JIM BEAM | [5 empty] | 4126203.26 | 2579017 | 1547186.26 |  |  |  | 2022-06-30
21026120300 | PM-ABA FOR EQUIP INST JIM BEAM | [5 empty] | 835157.07 | 62500 | 772657.07 |  |  |  | 2022-06-30
21026121300 | PM- SEWELL REPLACEMENT | [5 empty] | 4500640.76 | 1087500 | 3413140.76 |  |  |  | 2022-06-09
21026121400 | PM- SEWELL ABANDONMENT | [5 empty] | 692165.24 | 62500 | 629665.24 |  |  |  | 2022-06-09
21026121700 | INSTALL 10' OF 6"PHHP MAIN | [5 empty] | 14437.27 | 16348.9255 | -1911.6555 |  |  |  | 2021-06-07
21026121800 | RETIRE 10' OF 6"PHHP MAIN | [5 empty] | 0 | 80.3582 | -80.3582 |  |  |  | 2021-06-07
21026123600 | REPLACE MAIN - LEAKAGE D253626 | [5 empty] | 2711.68 | 5432.0527 | -2720.3727 |  |  |  | 2021-05-13
21026123700 | EMER 10'-2" PMLP | [5 empty] | 0 | 85.0408 | -85.0408 |  |  |  | 2021-05-13
21026124100 | INSTALL 300'-2" PMMP | [5 empty] | 41987.03 | 24076.2901 | 17910.7399 |  |  |  | 2021-11-05
21026131001 | EMER-INSTALL 10' OF 2"PMMP | [5 empty] | 34645.29 | 34334.8702 | 310.4198 |  |  |  | 2021-06-23
21026131100 | EMER-RETIRE 10' OF 2"PAMP MAIN | [5 empty] | 0 | 74.8797 | -74.8797 |  |  |  | 2021-06-23
21026131200 | INSTALL 4875' OF 2"/4"PMMP | [5 empty] | 140463.01 | 141168.2553 | -705.2453 |  |  |  | 2022-05-16
21026131900 | INSTALL 3843' OF 2"/4"PMMP MN | [5 empty] | 1468486.46 | 807937.3693 | 660549.0907 |  |  |  | 2022-10-06 | PROJECT COST OVERRUN DUE TO ADDITIONAL TIME AND RESOURCES NEEDED. CONTRACT COSTS AND LABOR COSTS INCREASED DUE TO UNEXPECTED ROCK ENCOUNTERED DURING C ONSTRUCTION FOR BORE/OPEN CUT OF NEW MAIN. ADDITIONAL TIE-IN LOCATIONS WERE REQUIRED FOR INSTALL AND ABANDONMENT. INCREASED FLAGGING AND INCREASED RES TORATION COSTS ALSO CONTRIBUTED TO THE OVERRUN, AS WELL AS INCREASED SEGA C OSTS. MOLIVER 1/24/23
21026132000 | RETIRE 3700' OF 4"/6"BSLP MAIN | [5 empty] | 3419.35 | 52.2976 | 3367.0524 |  |  |  | 2022-10-06
21026132600 | INSTALL NEW TRANSMITTERS | [5 empty] | 14392.01 | 15506.2901 | -1114.2801 |  |  |  | 2021-12-10 | CCC #34292 WAITING ON ISO
21026132700 | RETIRE DAMAGED TRANSMITTERS | [5 empty] | 0 | 82.634 | -82.634 |  |  |  | 2021-12-10 | WAITING ON ISO SKETCH REPLACED TRANSMITTERS AND RV50 DAMAGED BY LIGHTENING
21026133100 | INSTAL 2" MOONEY REGS | [5 empty] | 11609.08 | 9907.1191 | 1701.9609 |  |  |  | 2021-10-25 | REPLACED REGULATORS GCCC TICKET NOT REQUIRED
21026133200 | RETIRE FISHER 399 REGS | [5 empty] | 0 | 90.361 | -90.361 |  |  |  | 2021-10-25 | REPLACED REGULATORS GCCC TICKET NOT REQUIRED
21026134400 | RETIRE 98' OF 2"PMMP MAIN | [5 empty] | 4653.06 | 3547.617 | 1105.443 |  |  |  | 2021-08-10
21026138201 | EMER-INSTALL 480' OF 6"PMLP | [5 empty] | 194700.21 | 240281.6735 | -45581.4635 |  |  |  | 2021-11-02 | CCC# 43819 CCC# 43967 TWALKER/KY 05-04-22: JOB CURRENTLY UNDER RUNNING SINCE CITY OF FRANKFORT HAS NOT PAVED STREET AND BILLED CKY - PAVING ESTIMATE AT $35,000.
21026138300 | EMER-RETIRE 490' OF 6 5/8"BSLP | [5 empty] | 71.35 | 82.634 | -11.284 |  |  |  | 2021-11-02 | KBOTKINS ENTERED WIPE SAMPLE FOR OLIVER MAYNARD WHO IS ATTEMPTING TO COMPLETE THE JOB FOR CLOSE OUT. SAMPLE TAKEN 4/20/22 BUT SYSTEM WOULD NOT ACCEPT THAT DATE DUE TO THE CO DATE.
21026138900 | INSTALL 650'-6" PMMP | [5 empty] | 111751.03 | 35779.3166 | 75971.7134 |  |  |  | 2022-09-01 | COST INCREASE FOR LABOR HOURS AND CONTRACT COSTS DUE TO INCREASED DIRECTION AL BORE FOOTAGE, GPS DATA COLLECTION, INCREASED RESTORATION COSTS, ADDITION AL TIE-IN LOCATIONS NEEDED, AND INCREASE IN SEGA COSTS. - MOLIVER
21026141000 | EMER - INSTALL 5'-4" PMMP | [5 empty] | 0 | 427 | -427 |  |  |  | 2021-09-09
21026141100 | EMER - RETIRE 5'-4" PMMP | [5 empty] | 0 | 68.3073 | -68.3073 |  |  |  | 2021-09-09
21026144300 | EMER - INSTALL 2' OF 2"PMIP | [5 empty] | 137.16 | 2750.8249 | -2613.6649 |  |  |  | 2021-09-26
21026144400 | EMER - RETIRE 2' OF 2"PAIP | [5 empty] | 0 | 75.4968 | -75.4968 |  |  |  | 2021-09-26
21026145200 | EMER-INSTALL NEW BYPASS VALVES | [5 empty] | 634.37 | 4285.9461 | -3651.5761 |  |  |  | 2021-12-27 | CCC# 44725 BYPASS VALVES INSTALLED BY WADE SHIMFESSEL ALONG WITH CONTRACT CREW PAPERWORK COMPLETED BY CYNTHIA FARIS 12/27/21
21026145300 | EMER-RETIRE BYPASS VALVE | [5 empty] | 0 | 60.6987 | -60.6987 |  |  |  | 2022-01-11 | VALVE REPLACED BY WADE SHIMFESSEL AND CONTRACT CREW ON 11/3/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/11/2022
21026147300 | INSTALL 400'-4" PMMP-SER | [5 empty] | 32919.84 | 22333.8994 | 10585.9406 |  |  |  | #N/A | COMMIT DATE MISSED DUE TO WEATHER
21026149500 | EMER-INSTALL 26'-3"/4"PMMP MN | [5 empty] | 23766.13 | 10953.3154 | 12812.8146 |  |  |  | 2021-11-17 | SPLIT IN ALDYLA MAIN.INSTALLED BYPASS.REPLACED CRACKED MAIN AND INLINE TEE WHILE MAIN ON BYPASS.ALL TESTING INFO ON 21026149600 AND 21026149500 IN DOCS
21026149600 | EMER-RETIRE 26'- 4"PAMP MAIN | [5 empty] | 86.15 | 61.5191 | 24.6309 |  |  |  | 2021-11-17 | SPLIT IN ALDYLA MAIN.INSTALLED BYPASS.REPLACED CRACKED MAIN AND INLINE TEE WHILE MAIN ON BYPASS.ALL TESTING INFO ON 21026149600 AND 21026149500 IN DOCS
21026156600 | INSTALL 230'-2" PMMP | [5 empty] | 17647.7 | 15538.521 | 2109.179 |  |  |  | 2022-03-01
21026157100 | INSTALL 600'-2" PMMP | [5 empty] | 29494.94 | 21934.2504 | 7560.6896 |  |  |  | 2022-02-16
21026157200 | INSTALL 16' OF 3"PMMP MAIN | [5 empty] | 56295.03 | 11827.5319 | 44467.4981 |  |  |  | 2022-02-23 | TWALKER/KY 02-24-22: WMS WOULD NOT ALLOW PROJECT TO BE REVISED DUE TO UNPAID INVOICES MESSAGE. JOB OVER RUN DUE TO UNKNOWN BOLTED COUPLINGS FOUND DURING CONSTUCTION AND SCOPE OF WORK WAS INCREASED TO REMOVE THOSE COUPLINGS IN THE PAVED STREET. TWALKER/KY 09-16-22: DURING CONSTRUCTION BOLTED COUPLING WERE FOUND ON MP GAS MAIN AND HAD TO BE REMOVED WMS WOULD NOT ALLOW REVISION. ADDITIONAL WORK INCREASED COMPANY LABOR BY $6000 SEGA INCREASED BY $4500 STREET CUT REPAIR REQUIRED AND ADDITIONAL CONTRACT RESOURCES INCREASED BY $27,000
21026157300 | RETIRE 14' OF 3"CSMP MAIN | [5 empty] | 0 | 72.8047 | -72.8047 |  |  |  | 2022-02-23
21026994800 | RETIRE STATION 1502 | [5 empty] | 8422.17 | 4108.4893 | 4313.6807 |  |  |  | 2021-11-02 | CCC# 37974 CCC#41227 CCC#41449 CCC# 41449 STATION ABANDONED ON 10/12/2021 PAPERWORK COMPLETED ON 11/2/2021 GCCC TICKET NOT REQUIRED ON 11/2/21 OFF SITE COMPLETING PAPERWORK CFARIS
21026998201 | INSTALL 1930'-2"/4" PMMP | [5 empty] | 114169.59 | 114050.6727 | 118.9173 |  |  |  | 2022-11-01 | GAS ON MAIN 11/01/2022
21026999700 | INSTALL 125' OF 2"PMMP MAIN | [5 empty] | 22070.53 | 28787.2695 | -6716.7395 |  |  |  | 2021-10-13
21026999800 | RETIRE 115' OF 2"PMMP MAIN | [5 empty] | 0 | 81.0887 | -81.0887 |  |  |  | 2021-10-14
22026158100 | INSTALL 70'-2" PMMP | [5 empty] | 10660.65 | 9277.6445 | 1383.0055 |  |  |  | 2022-03-10 | INSTALED 57'OF 020PMMP.
22026160100 | PM-GREENSITE I75 ILI DE RELO | [5 empty] | 9503.69 | 0 | 9503.69 |  |  |  | 2022-07-22
22026160200 | PM-GREENSITE I75 ILI DE ABAN | [5 empty] | 105.53 | 0 | 105.53 |  |  |  | 2022-07-22 | GIS HAD LESS FOOTAGE THAN WHAT WAS FIELD VERIFIED. NO FAC CREATED, DUE TO F ACT IT WAS BEING ABANDONED.
22026160400 | EMER - REPAIR LEAK | [5 empty] | 8003.12 | 3388.6445 | 4614.4755 |  |  |  | 2022-01-13
22026160500 | EMER - REPAIR LEAK | [5 empty] | 0 | 69.6571 | -69.6571 |  |  |  | 2022-01-13
22026168000 | HVAC AND RTU PANEL UPGRADE | [5 empty] | 22883.04 | 39849.6755 | -16966.6355 |  |  |  | 2023-04-03 | PAPER JOB COMPLETION.
22026168600 | INSTALL 13,800'-2"PMMP | [5 empty] | 1532684.69 | 1751471.355 | -218786.665 |  |  |  | 2023-09-08
22026168700 | RETIRE 12,327'-BSLP,CSLP,PLP | [5 empty] | 0 | 89.0305 | -89.0305 |  |  |  | 2023-09-08
22026169200 | EMER-INSTALL 4' OF 2"PMMP MAIN | [5 empty] | 4368.24 | 5880.7828 | -1512.5428 |  |  |  | 2022-02-15
22026169300 | EMER-RETIRE 4' OF 2"PMMP MAIN | [5 empty] | 0 | 107.3789 | -107.3789 |  |  |  | 2022-02-15
22026179400 | RETIRE 100' OF 4"PMMP MAIN | [5 empty] | 0 | 75.4968 | -75.4968 |  |  |  | 2022-05-13
22026181600 | RELOCATE ~5"-2" PMMP | [5 empty] | 10366.16 | 6138.9503 | 4227.2097 |  |  |  | 2022-06-14 | DURING AND AFTER REPLACEMENT PURGE NEW MAIN INTO SERVICE CO M.COLLINS/B.SEXTON RLA 6-7-2022 REPLACED 10' OF 2" P MP MAIN TEST 10' OF 2" PIPE ONSITE 90LBS FOR 1 HR NO LEAKS SOAP TEST TIE IN NO LEAKS BHB NGF SOAP TEST ALL TEE'S CAPS AND DEAD ENDS AT OP AFTER GUAGE REMOVAL NO LEAKS VERIFY DELIVERY PRESSURE BEFORE
22026181700 | RELOCATE ~5"-2" PMMP | [5 empty] | 0 | 75.4968 | -75.4968 |  |  |  | 2022-06-14
24026313000 | INSTALL 1570'-2" PMMP | [5 empty] | 502657.55 | 526295.3733 | -23637.8233 | 2024-01-01 | 2024-12-31 | 2024-11-18 | 2024-12-10
22026185800 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 1834.52 | 5480.5156 | -3645.9956 |  |  |  | 2022-05-25 | CCC# 68240 - REPLACED ERX WITH MIWI 350 - BLONE/CWEMPE - 05/25/22 INSTALLED NEW MIWI 350
22026185900 | RETIRE ELECTRONIC COMPONETS | [5 empty] | 501.88 | 124.5156 | 377.3644 |  |  |  | 2022-05-25 | CCC# 68240 - REPLACED ERX WITH MIWI 350 - BLONE/CWEMPE - 05/25/22 RETIRED OLD ERX
22026186200 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 0 | 5480.5156 | -5480.5156 |  |  |  | 2022-05-23 | INSTALLED NEW MIWI 350 05/23/2022 GHALE
22026186300 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 190.3 | 124.5156 | 65.7844 |  |  |  | 2022-05-23 | RETIRED OLD ERX 05/23/2022 GHALE
22026186400 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 548.88 | 5480.5156 | -4931.6356 |  |  |  | 2022-05-24 | CCC# 68048 RETIRED ERX AND INSTALLED NEW MIWI350 JPASLEY
22026186500 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 0 | 124.5156 | -124.5156 |  |  |  | 2022-05-24 | RETIRED ERX AND INSTALLED NEW MIWI350 JPASLEY
22026186800 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 1456 | 4357.5409 | -2901.5409 |  |  |  | 2022-06-03 | CCC-69443 INSTALLED NEW MIWI 350 SOAP TEST CONNECTIONS EBLANTON
22026186900 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 504.03 | 124.5156 | 379.5144 |  |  |  | 2022-06-03 | CCC-69443 RETIRED ERX EBLANTON
22026188400 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 1456 | 6681.5691 | -5225.5691 |  |  |  | 2022-06-02 | CCC# 69290 - BLONE - 06/02/22 INSTALLED MIWI SN:13450082 P1-0-PSI P2-0-60 IP:10.22.4.15MDN 859-221-6738
22026188500 | RETIRE ELECTRONICS | [5 empty] | 473.46 | 74.2578 | 399.2022 |  |  |  | 2022-06-02 | CCC# 69290 - BLONE - 06/02/22
22026188600 | INSTALL 165'-2" PMMP | [5 empty] | 11945.7 | 14323.3857 | -2377.6857 |  |  |  | 2022-06-29
22026195400 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 682.09 | 4801.1928 | -4119.1028 |  |  |  | 2022-08-22 | CCC# 78156 PAPERWORK ONLY - NO CCC NEEDED - BLONE - 11/8/22 INSTALLED NEW MIWI350 B LONE 8-22-2022
22026195500 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 676.72 | 124.8731 | 551.8469 |  |  |  | 2022-08-22 | CCC# 78156 RETIRED OLD ERX INSTALLED NEW MIWI350 BLONE 8-22-22
22026195600 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5406.36 | 4801.1928 | 605.1672 |  |  |  | 2022-09-01 | CCC# 78341 - BLONE - 08/23/22 UPGRADED ERX TO MIME CO BY J.MULLINS
22026195700 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 381.79 | 124.8731 | 256.9169 |  |  |  | 2022-09-01 | CCC# 78341 B. LONE UPDATTED ERX TO MIWI CO BY J. MULLINS
22026198900 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5462.44 | 4801.1928 | 661.2472 |  |  |  | 2022-09-06 | CCC#79730 CWEMPE 9/6/22 UPGRADED ERX TO MIWI PAPERWORK DONE BY J.MULLINS
22026199000 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 252.74 | 124.8731 | 127.8669 |  |  |  | 2022-09-06 | CCC#79730 CWEMPE 9/6/22
22026199300 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5269.21 | 4801.1928 | 468.0172 |  |  |  | 2022-09-01 | CCC# 79486 RETIRED ERX INSTALLED NEW MIWI350 GHALE 9-1-2022
22026199400 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 169.77 | 124.8731 | 44.8969 |  |  |  | 2022-09-01 | CCC# 79486 RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 9-1-2022
22026199500 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5358.86 | 4801.1928 | 557.6672 |  |  |  | 2022-09-08 | CCC# 80149 P2P OK RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 9-8-2022
22026199600 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 509.01 | 124.8731 | 384.1369 |  |  |  | 2022-09-08 | CCC# 80149 RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 09-08-2022
22026200700 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5573.15 | 4801.1928 | 771.9572 |  |  |  | 2022-08-24 | CCC# 68204 - BLONE - 08/24/22 CCC#68204 TIME CHARGED FOR COMPLETING PAPERWORK. CWEMPE 8/30/22 RETIRED ERX INSTALLED NEW MIWI350 CWEMPE 8-24-2022
22026200800 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 285.19 | 124.8731 | 160.3169 |  |  |  | 2022-08-24 | CCC# 68204 - BLONE - 08/24/22 CCC#68204 RETIRED OLD ERX INSTALLED NEW MIWI350 CWEMPE 8-24-2022
22026201100 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5540.17 | 4801.1928 | 738.9772 |  |  |  | 2022-09-08 | CCC# 80069 P2P OK RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 9-8-2022
22026201200 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 157.47 | 124.8731 | 32.5969 |  |  |  | 2022-09-08 | CCC# 80069 RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 9-8-2022
22026202500 | INSTALL 1120'-2"/4" PMMP | [5 empty] | 50092.05 | 49758.6341 | 333.4159 |  |  |  | 2022-11-02
22026228500 | INSTALL 167'-2" PMMP | [5 empty] | 84729.46 | 82180.2832 | 2549.1768 | 2024-01-01 | 2024-12-31 | 2024-06-13 | 2024-06-20
22026207500 | INSTALL NEW CONTROL REGULATOR | [5 empty] | 893.82 | 1471.7874 | -577.9674 |  |  |  | 2022-08-18 | CCC#77790 INSTALLED NEW 461-57S CONTROL REGULATOR CWEMPE 8-18-22
22026207600 | REPLACE CONTROL REG | [5 empty] | 487.94 | 65.0112 | 422.9288 |  |  |  | 2022-08-18 | CCC#77790 REMOVED CONTROL REGULATOR CWEMPE 8-18-22
22026208600 | EMER - INSTALL 2'-2" PMMP | [5 empty] | 7597.73 | 5654.5749 | 1943.1551 |  |  |  | 2022-07-05
22026208700 | EMER - RETIRE 2'-2" PMP | [5 empty] | 0 | 63.5475 | -63.5475 |  |  |  | 2022-07-05
24026358600 | INSTALL 175' - 4" PMMP | [5 empty] | 90409.34 | 72423.4515 | 17985.8885 | 2024-01-01 | 2024-12-31 | 2024-11-18 | 2024-12-02
22026211200 | EMER-INSTALL 6' OF 4"PMIP MAIN | [5 empty] | 13924.65 | 10641.1495 | 3283.5005 |  |  |  | 2022-07-07
22026211300 | EMER-RETIRE 6' OF 4"PAIP MAIN | [5 empty] | 0 | 65.0112 | -65.0112 |  |  |  | 2022-07-07
22026213400 | INSTALL NEW 1" REGULATORS | [5 empty] | 2234.49 | 1461.8601 | 772.6299 |  |  |  | 2022-10-07 | REPLACED BOTH MONITOR AND CONTROL REGULATORS AND INLET AND OUTLET VALVES BL ONE 10-7-22
22026213500 | RETIRE REGULATORS | [5 empty] | 856.14 | 84.9152 | 771.2248 |  |  |  | 2022-10-07 | REPLACED BOTH MONITOR AND CONTROL REGULATORS AND INLET AND OUTLET VALVES BL ONE 10-7-22
22026213900 | INSTALL 200'-2"PMMP | [5 empty] | 35208.99 | 22574.1191 | 12634.8709 |  |  |  | 2022-10-24 | BORED IN 308' OF 020 PL ML. TESTED 90# FOR 1 HR. SOAP TESTED CONN PTS @ 39#
22026214100 | ABANDON 200'-2" PMMP | [5 empty] | 921.07 | 800.8601 | 120.2099 |  |  |  | 2022-10-21
22026214500 | JIM BEAN RTU PANEL | [5 empty] | 2091.18 | 55.5311 | 2035.6489 |  |  |  | 2023-04-03 | CCC# 15710 CCC# 15710
22026215700 | EMER-INSTALL 2' OF 2"PMMP MAIN | [5 empty] | 4910.67 | 8681.8934 | -3771.2234 |  |  |  | 2022-08-22 | REPLACED 2FT OF 020 DAMAGED MAIN.TESTED NEW MAIN FOR 20MINS AT 90LBS.TEST OK.SOAP TEST EFC'S AT OP FOR 5MINS.TEST OK. BHBNGF
22026215800 | EMER-RETIRE 2' OF 2"PMP MAIN | [5 empty] | 224.99 | 84.9152 | 140.0748 |  |  |  | 2022-08-22 | REPLACED 2FT OF 020 DAMAGED MAIN.TESTED NEW MAIN FOR 20MINS AT 90LBS.TEST OK.SOAP TEST EFC'S AT OP FOR 5MINS.TEST OK. BHBNGF
22026220400 | ABANDON 550' OF 2"PMP MAIN | [5 empty] | 184.67 | 3449.8998 | -3265.2298 |  |  |  | 2022-08-29 | ABANDONED 020 MP PL ML. PREFORMED PER ABANDONMENT PLAN SOAP TEST DEAD END C AP OP 15 MINUTES. C HERNDON/S.BARKER PURGED ABANDONED SECTION OF LINE. CAPPED THE ENDS OF ABANDONED ML.
22026221000 | INSTALL 160'-4"PMMP | [5 empty] | 36375.08 | 20578.0582 | 15797.0218 |  |  |  | 2022-11-14 | AWEBER 12/6/22 - JOB ENCOUNTERED HEAVY ROCK BORE, RESULTING IN DOUBLE TIME FROM ORIGINAL ESTIMATE. ATTEMPT TO REVISE, UNABLE DUE TO UNPAID INVOICES.
22026222700 | INSTALL 86'-2" PMMP | [5 empty] | 13511.21 | 12304.5709 | 1206.6391 |  |  |  | 2022-12-07 | THERE WAS A TYPO ON THE PRESSURE SYSTEM WHEN IT WAS CREATED. CORRECT SYSTEM NUMBER 32010047. SYSTEM NUMBER HAS BEEN CORRECTED IN DIS.
22026225400 | INSTALL APROX 180'-6" PMLP | [5 empty] | 161513.7 | 120007.3465 | 41506.3535 |  |  |  | 2023-08-21 | GURU ADDED 2'-6"PLASTIC RISER PIPE TO TD 0735002. SM 11/7/23
22026225500 | RETIRE 200' - 6" BSLP | [5 empty] | 510.72 | 117.7346 | 392.9854 |  |  |  | 2023-08-21
22026229200 | INSTALL 80'-2" PMMP | [5 empty] | 10781.29 | 11104.5291 | -323.2391 |  |  |  | 2023-01-27 | INSTALLED 160' 2'' MP-PL MAINLINE
22026230000 | ABANDON 470'-2"&3"PLP | [5 empty] | 5899.02 | 6027.5291 | -128.5091 |  |  |  | 2022-11-01 | ABANDONED 334' OF 030 PL LP ML PER ENGINEERING AND TIE IN PLAN. SOAP TEST END CAP @ OP 15 MINS NO LEAKS BHB NGF. PURGED OUT ABANDONED SECTION OF ML G OOD M. COLLINS 11/1/2022
22026230600 | EMER-INSTALL 5' OF 3"PMMP MAIN | [5 empty] | 0 | 828.6177 | -828.6177 |  |  |  | 2022-10-06
22026230700 | EMER-RETIRE 5' OF 3"PAMP MAIN | [5 empty] | 12302.62 | 4289.0582 | 8013.5618 |  |  |  | 2022-10-06
22026231200 | INSTALL 1870'-2"/4" PMMP | [5 empty] | 213474.97 | 71796.5181 | 141678.4519 |  |  |  | 2023-10-04
24026354300 | INSTALL 1750' OF 2"PMMP MAIN | [5 empty] | 49920.61 | 59204.7838 | -9284.1738 | 2024-01-01 | 2024-12-31 | 2024-11-06 | 2024-12-19
24026353800 | INSTALL 180' OF 4"PMMP MAIN | [5 empty] | 167555.7 | 169246.7693 | -1691.0693 | 2024-01-01 | 2024-12-31 | 2024-08-16 | 2024-08-30
22026235400 | RETIRE 2111'- 2",4",6",8" BSMP | [5 empty] | 220 | 139.1159 | 80.8841 |  |  |  | #N/A
23026300600 | INSTALL 180'-4" PMLP | [5 empty] | 77710.69 | 62129.0817 | 15581.6083 | 2024-01-01 | 2024-12-31 | 2024-01-01 | 2024-01-12
22026237000 | ABDN~8924'-2",3",4" BS,CS,P LP | [5 empty] | 0 | 124.9261 | -124.9261 |  |  |  | #N/A
23026300300 | INSTALL 1810'-2" PMMP | [5 empty] | 217275.5 | 171679.8061 | 45595.6939 | 2024-01-01 | 2024-12-31 | 2024-10-24 | 2024-11-14
24026360500 | INSTALL 18'-2" PMMP | [5 empty] | 10627.85 | 23343.2435 | -12715.3935 | 2024-01-01 | 2024-12-31 | 2024-10-05 | 2024-10-29 | INST 35' OF 2" P MP MAIN PER ENGINEERED PLAN TO OFFSET IN 2 INTERSECTIONS FOR SEWER PROJECT. MCRAIG 10/29/24
22026238500 | RETIRE 7260'-2"-6" BS,CS & P | [5 empty] | 0 | 139.1159 | -139.1159 |  |  |  | #N/A
22026238600 | RETIRE 116'-2"&3" CS&PMP | [5 empty] | 0 | 139.1159 | -139.1159 |  |  |  | #N/A
22026241001 | INSTALL 6375'-2"/4" PMMP ENV | [5 empty] | 797679.45 | 793212.5591 | 4466.8909 |  |  |  | 2023-11-30
21026145601 | INSTALL 1885' - 4" PMMP MAIN | [5 empty] | 816623.03 | 712573.3764 | 104049.6536 | 2024-01-01 | 2024-12-31 | 2024-02-01 | 2024-03-18 | JOB COMPLETE
22026241800 | RETIRE 1175' OF 3"/4"BSLP MAIN | [5 empty] | 10.85 | 119.4953 | -108.6453 |  |  |  | #N/A
22026243700 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 17949.62 | 29277.8866 | -11328.2666 |  |  |  | 2023-04-17 | CC 22683 CC 22535 WELDED INLET TAP TESTED INLET 375# 5 MINS RHAYES DMARTIN 03-29-2023 CCC# 24078 NOT ON SITE. CAPITAL PAPERWORK CCC#25522 CWEMPE 4/17/23 COMPLETED PAPERWORK OFFSITE. CWEMPE 4/20/23 DID NOT ENTER STATION. CHARGED TIME FOR PAPERWORK. CWEMPE 4/24/23
22026243800 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 17170.68 | 32044.6752 | -14873.9952 |  |  |  | 2023-04-18 | CC 22535 WELDED TAPS TESTED INLET 375# OUTLET 45# MINS DMARTIN RHAYES 03-29-2023 CCC# 24067 CCC#25645 CWEMPE 4/18/23 COMPLETED PAPERWORK OFFSITE. CWEMPE 4/20/23 DID NOT ENTER STATION. CHARGED TIME FOR PAPERWORK. CWEMPE 4/24/23
22026244100 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 17388.43 | 32044.6752 | -14656.2452 |  |  |  | 2023-04-19 | CC 22622 CC 22535 WELDED TAPS TESTED INLET 375# OUTLET 90# 5 MINS RHAYES DMARTIN 03-29-2023 CCC# 24075 CALLED FOR CLEARANCE TICKET AT END OF DAY AND CCC REFUSED TO CREATE TICKET. CWEMPE 4/19/23 COMPLETED PAPERWORK OFFSITE. CWEMPE 4/20/23
22026244200 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 20934.82 | 33186.6752 | -12251.8552 |  |  |  | 2023-04-25 | CCC# 24912 WELDED ON PUNCH TEES FOR SCADA VISIBILITY PROJECT. TESTED TAPPED, AND MT COMPLETE. LOCKED AND PLUGGED VALVE. CCC# 26916
22026244300 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 21295.01 | 29761.6752 | -8466.6652 |  |  |  | 2023-04-21 | CC 22295 TAPS WELDED TESTED INLET 375# OUTLET90# 5MIN TESTED GOOD RHAYES CCC# 24050 CCC#26526 CWEMPE 4/21/23
22026245100 | EMER-INSTALL 3' OF 2"PHHP MAIN | [5 empty] | 2741.28 | 4877.0569 | -2135.7769 |  |  |  | 2022-12-07
22026245200 | EMER-RETIRE 3' OF 2"PHHP MAIN | [5 empty] | 0 | 131.2422 | -131.2422 |  |  |  | #N/A
23026249500 | INSTALL 870'-2" PMMP | [5 empty] | 52378.28 | 67614.2583 | -15235.9783 |  |  |  | 2023-04-04
23026249600 | PM- DE ILI PH 2 JIM BEAM INST | [5 empty] | 966229.4 | 593000 | 373229.4 |  |  |  | 2023-01-27
23026249700 | PM- DE ILI PH 2 JIM BEAM ABAN | [5 empty] | 234155.55 | 132000 | 102155.55 |  |  |  | 2023-01-27
23026251500 | INSTALL 70'-2" PMLP | [5 empty] | 16349.3 | 20790.0608 | -4440.7608 |  |  |  | 2023-05-05
23026252900 | PM-GREENSITE RAILROAD CROSSING | [5 empty] | 17890.94 | 1236355 | -1218464.06 |  |  |  | 2022-07-12
23026253000 | PM-GREENSITE RAILROAD ABANDON | [5 empty] | 328.14 | 0 | 328.14 |  |  |  | 2022-07-12
23026253500 | PM-GREENSITE IRONWORKS DE REPL | [5 empty] | 18995.31 | 1236355 | -1217359.69 |  |  |  | 2022-05-13
23026253600 | PM-GREENSITE IRONWORKS ABAN | [5 empty] | 6.23 | 0 | 6.23 |  |  |  | 2022-05-13
23026254300 | TAP W/MAIN 23-0262543-00 | [5 empty] | 4459.75 | 13015.0987 | -8555.3487 |  |  |  | 2023-02-08
23026255400 | GMB TO CAB CONVERSION | [5 empty] | 9499.75 | 2712.0987 | 6787.6513 |  |  |  | 2023-06-01 | REMOVED OLD GMB FACILITIES REBUILT METER SETTING INSTALLED NEW ROMET 16M ME TER AND CL838 REGS ON 15# DELIVERY BLONE 6-1-23
23026256000 | INSTALL 800'OF 2"PMMP MAIN | [5 empty] | 92657.71 | 192451.7008 | -99793.9908 |  |  |  | 2023-07-27
23026256600 | RETIRE PAPER GAUGE | [5 empty] | 468 | 138.8485 | 329.1515 |  |  |  | 2023-03-02 | CHART BOXES REMOVED. G.HALE A.PARKS 03-02-23 CHARTS REMOVED AND STORED AT LEX MOD APARKS 03-02-23
23026257100 | INSTALL 300'-2" PMMP | [5 empty] | 68581.44 | 32921.1974 | 35660.2426 |  |  |  | 2023-09-28 | MAINLINE EXTENSION FOR ALDI'S INSTALLED BY STANLEY PIPELINE. JOSH PASLEY 9/28/23
23026259600 | INSTALL ERX AND SUPER SOLAR | [5 empty] | 4884.63 | 5600.9621 | -716.3321 |  |  |  | 2023-03-07
23026259700 | RETIRE PAPER CHART | [5 empty] | 269.78 | 138.8485 | 130.9315 |  |  |  | 2023-03-07
23026260600 | GMB TO CAB CONVERSION | [5 empty] | 1404.11 | 138.8485 | 1265.2615 |  |  |  | 2023-04-04 | GATHER PARTS FOR CONVERSION, MTR, FLANGES, GASKETS ETC. REGULATOR GMB TO CAB CONVERSION GAS ON BYPASS DURING REBUIL;D NO BYPASS GAS USED INST ALLED NEW ROMET 3M ON 2#
23026266100 | INSTALL 880'-4" PHHP | [5 empty] | 70247.34 | 60596.7317 | 9650.6083 |  |  |  | 2023-08-18
23026266200 | INSTALL 1100'-4" PHHP | [5 empty] | 127648.14 | 81743.7317 | 45904.4083 |  |  |  | 2023-09-12
23026268100 | RETIRE MAIN - LEAKAGE | [5 empty] | 0 | 117.7346 | -117.7346 |  |  |  | 2023-04-12
23026268500 | PM-DE LINE ILI PH 2 BEND 260 | [5 empty] | 770197.91 | 1150001 | -379803.09 |  |  |  | 2023-06-16
23026268600 | PM-DE LINE ILI PH2 DENT 36 | [5 empty] | 1598859.3 | 1150001 | 448858.3 |  |  |  | 2023-06-03
23026269000 | EMER-INSTALL 4' OF 2"PMMP MAIN | [5 empty] | 6353.99 | 5499.7073 | 854.2827 |  |  |  | 2023-03-29
23026269100 | EMER-RETIRE 4' OF 2"PAMP MAIN | [5 empty] | 0 | 117.7346 | -117.7346 |  |  |  | 2023-03-29
23026269200 | PM-DE LINE ILI PH2 BEND 260 AB | [5 empty] | 195099.48 | 192300 | 2799.48 |  |  |  | 2023-06-23
23026269300 | PM-DE LINE ILI PH2 DENT 36 ABD | [5 empty] | 282014.56 | 192300 | 89714.56 |  |  |  | 2023-06-05
23026271000 | INSTALL 70'-2" PMMP | [5 empty] | 606.43 | 9795.9371 | -9189.5071 |  |  |  | 2023-04-10
23026271100 | ABANDON 60'-2" PMMP | [5 empty] | 4210.59 | 262.8722 | 3947.7178 |  |  |  | 2023-04-10
23026273500 | EMER-INSTALL 65' OF 2"PMIP | [5 empty] | 5983.61 | 8772.0552 | -2788.4452 |  |  |  | 2023-04-21
23026273600 | EMER-RETIRE 55' OF 2"PAIP | [5 empty] | 1024.42 | 117.7346 | 906.6854 |  |  |  | 2023-04-21
23026276700 | RETIRE STATION R-1581 | [5 empty] | 1722.38 | 541.8551 | 1180.5249 |  |  |  | #N/A | NO CCC NEEDED -RETIRED STATION - CHECKED TO SEE RETIRED STATUS AND STATUS OF INLET VALVE - BLONE - 05/02/25
23026276800 | RETIRE FENCE | [5 empty] | 0 | 139.1159 | -139.1159 |  |  |  | #N/A
23026278900 | INSTALL 150'-2" PMMP | [5 empty] | 10151.75 | 13769.2187 | -3617.4687 |  |  |  | 2023-07-28
23026279800 | INSTALL 1800'-2" PMMP | [5 empty] | 53278.51 | 72065.7028 | -18787.1928 |  |  |  | 2023-07-25
23026281200 | EMER-INSTALL 2' OF 2"PMMP MAIN | [5 empty] | 6222.18 | 5082.4374 | 1139.7426 |  |  |  | 2023-06-26
23026281300 | EMER-RETIRE 2' OF 2"PMMP MAIN | [5 empty] | 0 | 139.1159 | -139.1159 |  |  |  | 2023-06-26
23026281400 | INSTALL 1865'-2"/4" PMMP | [5 empty] | 90143.57 | 77027.7111 | 13115.8589 |  |  |  | 2023-11-01
23026282800 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 8915.85 | 5465.9794 | 3449.8706 |  |  |  | 2023-07-05
23026282900 | EMER - ABANDON 5'-2" PMMP | [5 empty] | 0 | 67.1159 | -67.1159 |  |  |  | 2023-07-05
24026362300 | INSTALL 2" SS | [5 empty] | 0 | 159.2637 | -159.2637 | 2024-01-01 | 2024-12-31 | 2024-08-09 | 2024-08-12
23026284000 | EMER-INSTALL 2' OF 3"PMMP MAIN | [5 empty] | 14848.12 | 4281.828 | 10566.292 |  |  |  | 2023-07-26
23026284100 | EMER-RETIRE 2' OF 3"PAMP MAIN | [5 empty] | 0 | 139.1159 | -139.1159 |  |  |  | 2023-07-26
23026285800 | EMER-INSTALL 3' OF 2"PMMP MAIN | [5 empty] | 8976.29 | 6991.8345 | 1984.4555 |  |  |  | 2023-07-25
23026285900 | EMER-RETIRE 3' OF 2"PMMP MAIN | [5 empty] | 0 | 139.1159 | -139.1159 |  |  |  | 2023-07-25
23026288700 | INSTALL NEW RELIEF VALVE | [5 empty] | 814.62 | 3278.6711 | -2464.0511 |  |  |  | 2023-08-11
23026288800 | RETIRE RELIEF VALVE | [5 empty] | 0 | 119.4953 | -119.4953 |  |  |  | 2023-08-11
23026292300 | INSTALL 2" SS | [5 empty] | 1292.35 | 15645.4681 | -14353.1181 | 2024-01-01 | 2024-12-31 | 2024-01-15 | 2024-01-16 | INSTALED AND TESTED SS FITTING AT 90PSIG FOR 15 MINS
23026289800 | RETIRE 271' OF 2"/3"BSLP MAIN | [5 empty] | 9.9 | 119.4953 | -109.5953 |  |  |  | #N/A
23026291400 | PAPER JOB - MP RETIREMENT | [5 empty] | 0 | 119.4953 | -119.4953 |  |  |  | 2023-06-27
24026310600 | INSTALL 2, 2" STOPPLE FITTINGS | [5 empty] | 21866.79 | 32187.8821 | -10321.0921 | 2024-01-01 | 2024-12-31 | 2024-06-16 | 2024-06-17
23026294600 | ABANDON ~790'-2" PMMP | [5 empty] | 392.35 | 3905.6711 | -3513.3211 |  |  |  | 2023-10-04
23026296400 | INSTALL 110' OF 2"PMMP MAIN | [5 empty] | 58459.83 | 46114.2728 | 12345.5572 |  |  |  | 2023-12-21 | CAPITAL JOB COMPLETE BY STANLEY PIPELINE AND CLEARED ASSOCIATED DPI'S. JOSH PASLEY 12/21/23
23026296500 | RETIRE 88' OF 2"CSMP MAIN | [5 empty] | 0 | 122.9261 | -122.9261 |  |  |  | 2023-12-21 | CAPITAL JOB COMPLETED BY STANLEY PIPELINE. CLEARED ASSOCIATED DPI'S. JOSH PASLEY 12/21/23
24026337900 | INSTALL 2,550'-2" PMMP | [5 empty] | 82903.24 | 91900.6833 | -8997.4433 | 2024-01-01 | 2024-12-31 | 2024-03-18 | 2024-05-09
23026301200 | INSTALL 60' OF 6"PMMP MAIN | [5 empty] | 43879.22 | 42818.4272 | 1060.7928 |  |  |  | 2025-03-06
23026301300 | RETIRE 54' OF 6"PMP MAIN | [5 empty] | 0 | 156.7483 | -156.7483 |  |  |  | #N/A
23026301600 | INSTAL NEW MODEM | [5 empty] | 652.23 | 2605.8688 | -1953.6388 |  |  |  | 2023-11-06
23026301700 | RETIRE MODEM | [5 empty] | 365.2 | 122.9261 | 242.2739 |  |  |  | 2023-11-06
23026307400 | EMER-INSTALL 3' OF 2"PMMP | [5 empty] | 1388.66 | 2930.7643 | -1542.1043 |  |  |  | 2023-12-05
23026307500 | EMER-RETIRE 3' OF 2"PMP MAIN | [5 empty] | 0 | 123.4493 | -123.4493 |  |  |  | 2023-12-05
23026303400 | INSTALL 20'-2" CSHP | [5 empty] | 212847.86 | 112306.0322 | 100541.8278 | 2024-01-01 | 2024-12-31 | 2024-08-05 | 2024-08-12
24026354400 | INSTALL 20'-4" PMLP | [5 empty] | 287.45 | 159.2637 | 128.1863 | 2024-01-01 | 2024-12-31 | 2024-08-01 | 2024-08-07
24026309500 | INSTALL 215'-2" PMMP | [5 empty] | 19486.43 | 20568.4833 | -1082.0533 | 2024-01-01 | 2024-12-31 | 2024-05-08 | 2024-05-22
24026310100 | EMER-RETIRE 4' OF 2"PAIP MAIN | [5 empty] | 0 | 123.4493 | -123.4493 |  |  |  | #N/A
24026311500 | EMER-RETIRE 350' OF 4"PMP MAIN | [5 empty] | 1832.02 | 3055.4946 | -1223.4746 |  |  |  | #N/A
24026312100 | REMOVE SATELLITE UNIT | [5 empty] | 1333.97 | 4076.4833 | -2742.5133 |  |  |  | #N/A | CCC# 58738
22026235100 | INSTALL 2160'-2"/4" PMMP | [5 empty] | 179472.03 | 82352.5181 | 97119.5119 | 2024-01-01 | 2024-12-31 | 2024-01-01 | 2024-02-09
24026312301 | INSTALL NEW GMB SETTING | [5 empty] | 230544.69 | 234758.3952 | -4213.7052 |  |  |  | #N/A
24026312400 | INSTALL 50'-4" PHHP-SERV | [5 empty] | 23459.51 | 13239.0974 | 10220.4126 |  |  |  | #N/A
23026296000 | INSTALL 220' OF 2" PMMP | [5 empty] | 50792.43 | 32123.3441 | 18669.0859 | 2024-01-01 | 2024-12-31 | 2024-01-07 | 2024-01-11
24026313100 | RETIRE~1346 OF BSLP/PLP MAIN | [5 empty] | 0 | 139.7787 | -139.7787 |  |  |  | #N/A
24026314800 | INSTALL MINI AT W/EC350 | [5 empty] | 5915.68 | 3917.1928 | 1998.4872 |  |  |  | #N/A | INSTALLED NEW EC350 WITH HONEYWELL MODEM
24026314900 | RETIRE ELECTRONICS | [5 empty] | 1358.47 | 160.3697 | 1198.1003 |  |  |  | #N/A | RETIRED OLD MINI AT
22026224201 | INSTALL 2300' OF 2"/4"PMMP | [5 empty] | 588766.29 | 524527.3047 | 64238.9853 | 2024-01-01 | 2024-12-31 | 2024-08-15 | 2024-09-16
24026316600 | EMER - ABANDON ~15'-2" PMMP | [5 empty] | 7172.61 | 160.3697 | 7012.2403 |  |  |  | #N/A
24026312200 | INSTALL 230'-2" PMMP | [5 empty] | 37251.74 | 25802.5654 | 11449.1746 | 2024-01-01 | 2024-12-31 | 2024-05-28 | 2024-06-07
24026322900 | INSTALL MIWI W/ SOLAR | [5 empty] | 16866.28 | 22593.1928 | -5726.9128 |  |  |  | #N/A | CCC# 96304 CCC# 96304 X-RAY WELD AND DROP OFF PAPERWORK. G.HALE 11-18-2024
24026323000 | RETIRE FACILITIES | [5 empty] | 890.43 | 160.3697 | 730.0603 |  |  |  | #N/A | CCC# 96304
23026292000 | INSTALL 2450' OF 2"PMMP MAIN | [5 empty] | 93897.7 | 75092.497 | 18805.203 | 2024-01-01 | 2024-12-31 | 2024-02-06 | 2024-02-20
24026331200 | EMER-ABANDON ~5'-2" PMMP | [5 empty] | 0 | 118.4933 | -118.4933 |  |  |  | #N/A
24026355900 | INSTALL 250' OF 2"PMMP MAIN | [5 empty] | 56306.29 | 23765.9793 | 32540.3107 | 2024-01-01 | 2024-12-31 | 2024-10-22 | 2024-10-31 | TWALKER/KY 11-01-24: WMS WOULD NOT ALLOW JOB ORDER REVISION DUE TO UNPAID INVOICE ERROR, PROJECT PLANNED DIRECT BORE BUT CREWS HIT ROCK REASON FOR JOB COST OVER RUN.
24026331700 | REITRE 435' OF 2"BSLP MAIN | [5 empty] | 489.56 | 121.4465 | 368.1135 |  |  |  | #N/A
23026272901 | INSTALL 2500' OF 2"PMMP MAIN | [5 empty] | 251654.55 | 209814.7415 | 41839.8085 | 2024-01-01 | 2024-12-31 | 2024-02-01 | 2024-03-15
24026332900 | EMER - ABANDON 5'-4" PMIP | [5 empty] | 19.55 | 118.4933 | -98.9433 |  |  |  | #N/A
24026355300 | INSTALL 250'-2" PMMP | [5 empty] | 24464.47 | 25692.6504 | -1228.1804 | 2024-01-01 | 2024-12-31 | 2023-09-11 | 2024-09-18
24026338300 | EMER - ABANDON 5'-3" PMMP | [5 empty] | 0 | 118.4933 | -118.4933 |  |  |  | #N/A
24026344900 | ABANDON ~30'-2" PMP | [5 empty] | 0 | 139.7787 | -139.7787 |  |  |  | #N/A
22026238301 | INSTALL 2505'-4" PHHP | [5 empty] | 297291.9 | 265393.3206 | 31898.5794 | 2024-01-01 | 2024-12-31 | 2023-11-15 | 2024-01-08
24026346200 | EMER - ABANDON 2'-2" PMP | [5 empty] | 0 | 139.7787 | -139.7787 |  |  |  | #N/A
24026346900 | INSTALL 2"BYPASS REGULATOR | [5 empty] | 30803.34 | 18438.8164 | 12364.5236 |  |  |  | #N/A | INSTALL BYPASS REGS, CMCHOLAN 8-28-24 0815
24026347000 | RETIRE 4" BYASS REGULATORS | [5 empty] | 1210.3 | 139.7787 | 1070.5213 |  |  |  | #N/A
24026350100 | INSTALL RMU UNIT AT RECTIFER | [5 empty] | 6.49 | 5471.8027 | -5465.3127 |  |  |  | #N/A | RM5 I/04 DOME:510102550 MODEM:501004142 INSTALLED (TE866717) AT GLENNS CREEK REC / 07-10-24 JMM
24026350200 | RETIRE RMU UNIT AT RECTIFIER | [5 empty] | 0 | 139.7787 | -139.7787 |  |  |  | #N/A | OLD RMU RM4014 TE 673502 RETIRED / INSTALLED NEW RMU RM5 TE 866717 / JMM 673502 RETIRED VIA UFA IN ERROR. PU NUMBER RETIRED VIA 999
24026350300 | INSTALL RMU AT RECTIFIER | [5 empty] | 5998.89 | 6097.8027 | -98.9127 |  |  |  | #N/A | RM5 I/04 DOME:510102969 MODEM:501003622 INSTALLED (TE867224) AT AUSTIN REC 08-07-24 JMM
24026350400 | RETIRE RMU UNIT | [5 empty] | 0 | 139.7787 | -139.7787 |  |  |  | #N/A | OLD RMU RM4010 TE 655082 RETIRED / INSTALLED NEW RMU RM5 TE 867224 / JMM
24026354500 | RETIRE 4" BS-MP SERVICE LINE | [5 empty] | 0 | 127.2637 | -127.2637 |  |  |  | #N/A
24026354600 | INSTALL 790'-4" PMMP S/L | [5 empty] | 73956.17 | 108203.2906 | -34247.1206 |  |  |  | #N/A
24026343500 | INSTALL 25'-8" PMLP | [5 empty] | 48462.2 | 72915.1812 | -24452.9812 | 2024-01-01 | 2024-12-31 | 2024-06-03 | 2024-06-10
23026302701 | INSTALL 2700' OF 2"/4"PMMP | [5 empty] | 288308.66 | 294198.9734 | -5890.3134 | 2024-01-01 | 2024-12-31 | 2024-05-22 | 2024-06-12
24026317300 | INSTALL 270'-2" PMMP | [5 empty] | 32804.09 | 44548.0974 | -11744.0074 | 2024-01-01 | 2024-12-31 | 2024-03-25 | 2024-04-08
24026357800 | EMER-RETIRE 3" POLY VLV C-145 | [5 empty] | 0 | 127.2637 | -127.2637 |  |  |  | #N/A
22026171100 | INSTALL 2715' OF 2"/4"PMMP | [5 empty] | 734298.53 | 852559.9514 | -118261.4214 | 2024-01-01 | 2024-12-31 | 2024-04-20 | 2024-05-23 | TWALKER/KY 08-16-24: FINAL PAVING RESTORATION FOR THIS PROJECT WILL NOT HAPPEN UNTIL 2025 DUE TO PLANNED WATER COMPANY PROJECT ON SAME STREETS AND CITY OF LEXINGTON SHARED PAVING REQUIREMENTS
24026360300 | EMER-RETIRE 3' OF 2"PAMP MAIN | [5 empty] | 0 | 127.2637 | -127.2637 |  |  |  | #N/A | PAPERWORK ISSUES CFD
24026357400 | INSTALL 275'-3" CSMP | [5 empty] | 104472.75 | 87056.0137 | 17416.7363 | 2024-01-01 | 2024-12-31 | 2024-10-07 | 2024-10-24
24026362100 | EMER-RETIRE 2' OF 3"PMP/VALVE | [5 empty] | 12763.63 | 127.2637 | 12636.3663 |  |  |  | #N/A
24026363800 | INSTALL EC-350 UNIT | [5 empty] | 5892.2 | 4869.446 | 1022.754 |  |  |  | #N/A
24026363900 | RETIRE EFC UNIT | [5 empty] | 0 | 135.7529 | -135.7529 |  |  |  | #N/A
24026372000 | INSTALLING 500'-2" PMMP | [5 empty] | 47889.55 | 43811.0834 | 4078.4666 |  |  |  | 2025-02-21
24026372200 | PM- SEWELL RPL OUTLET SYS ABAN | [5 empty] | 0 | 0 | 0 |  |  |  | #N/A
24026372300 | PM- SEWELL REPL OUTLET SYS# | [5 empty] | 0 | 0 | 0 |  |  |  | #N/A
25026377600 | EMER-INSTALL 4' OF 2"PMMP MAIN | [5 empty] | 8999.48 | 11901.0834 | -2901.6034 |  |  |  | 2025-01-02
25026377700 | EMER-RETIRE 4' OF 2"PMP MAIN | [5 empty] | 0 | 111.0024 | -111.0024 |  |  |  | #N/A
25026381100 | INSTALL SCADA VISIBILITY | [5 empty] | 8624.74 | 10377.5378 | -1752.7978 |  |  |  | #N/A | CCC 114389 WELD TAPS ON PRESSURE TEST 375# INLET CCC 124465 INSTALLED ER350 AND SUPER SOLAR KIT. COMMISSIONED WITH GC. 6/10/25 DSASH
25026392000 | INSTALL 140'-2" PMMP | [5 empty] | 21515.47 | 12869.0756 | 8646.3944 |  |  |  | 2025-05-12
25026403300 | INSTALL MONITOR REGULATOR | [5 empty] | 1909.6 | 7027.7205 | -5118.1205 |  |  |  | #N/A
25026403400 | RETIRE MONITORING REG | [5 empty] | 1316.2 | 79.8251 | 1236.3749 |  |  |  | #N/A
17026706600 | CONVERT FROM GMB TO CAB ACCT | [5 empty] | 14520.06 | 1078.4716 | 13441.5884 |  |  |  | 2023-07-17 | CCC# 36905 CCC#36905
17026724700 | RETIRE 350' - 3" PMLP | [5 empty] | 6306.19 | 2349.008 | 3957.182 |  |  |  | #N/A | PREP FOR JOB/GATHERED MATERIAL WILL DO PAPERWORK TOMORROW ABANDONED MAIN DOWNSTREAM OF METER AT 102 BLUEBERRY LN PER FOL - SOAP TEST DEAD END CAP FOR 5 MIN AT OP OK - BHB OK - 10.5 IWC VERIFIED - NRICHIE 2-20-24. IP OFF SITE.
18026766400 | I&C - INSTALL SCADA EQUIPMENT | [5 empty] | 143824.82 | 183526.0448 | -39701.2248 |  |  |  | 2022-09-29 | JMULLINS COMPLETE PAPERWORK TWALKER/KY 01-24-23: JOB UNDER RUN DUE TO MATERIAL COST WAS $33,000 LESS THAN PLANNED, NO SEGA CHARGED TO JOB ORDER PROJECT WAS PLANNED FOR $23,000
18026789001 | INSTALL 6900' - 4" PMMP | [5 empty] | 789465.56 | 783479.7367 | 5985.8233 |  |  |  | 2021-02-05
18026789100 | RETIRE 600' - 3" PMMP | [5 empty] | 70.37 | 218.671 | -148.301 |  |  |  | 2021-02-04
24026331500 | INSTALL 300' OF 2"PMMP MAIN | [5 empty] | 40161.78 | 28768.72 | 11393.06 | 2024-01-01 | 2024-12-31 | 2024-04-10 | 2024-04-24
18026795600 | RETIRE 714' - 6" BSMP | [5 empty] | 0 | 124.7348 | -124.7348 |  |  |  | #N/A
18026823200 | INST. FN 164 EXTRA LP OPP | [5 empty] | 53697.68 | 24062.1646 | 29635.5154 |  |  |  | 2021-07-07 | TICKET CALLED IN BY JPASLEY NOT ON SITE ROUNDED UP PARTS. GCCC# 19363 CCC# 19363 CCC# 20802 NOT ON SITE CCC# 21442 P2P WITH GAS CONTROL REGULATOR AND ER350 INSTALLED BY WADE SHIMFESSEL ON 4/27/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/21 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026823300 | RET. FN 164 FOR EXTRA LP OPP | [5 empty] | 228.05 | 53.6219 | 174.4281 |  |  |  | 2021-07-07 | REGULATOR REPLACED BY WADE SHIMFESSEL ON 4/27/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/21 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026861100 | INSTALL HEATER | [5 empty] | 2372.11 | 3045.0298 | -672.9198 |  |  |  | #N/A | INSTALLED CAT HEATER
19026913900 | INSTALL 20' - 4" CSHP | [5 empty] | 82645.85 | 45390.8034 | 37255.0466 |  |  |  | 2021-03-23 | COULD NOT REVISE DUE TO UNFULLFILLED PURCHASE ORDERS, NEEDED REVISION DUE TO EXTRA MATERIAL, INCREASE CONTRACT LABOR REQUIRED, EXTRA COMPANY LABOR, EXTRA TRUCK COSTS, AND EXTRA SEGA TTOY 3/18/2021
19026914000 | RETIRE 10' - 3" CSHP | [5 empty] | 695.55 | 114.5339 | 581.0161 |  |  |  | 2021-03-23
20026918201 | INSTALL ELECTRONICS | [5 empty] | 199238.05 | 114999.9064 | 84238.1436 |  |  |  | 2022-09-27 | CCC#17216 CCC# 19029 STATION RTU UP GRADE JPASLEY 9-27-22
20026930000 | UPGRADE ELECTRONICS | [5 empty] | 4491.87 | 3038 | 1453.87 |  |  |  | 2022-10-07 | INSTALLED NED EC350 JPASLEY 10-7-22
20026930100 | UPGRADE ELECTRONICS | [5 empty] | 3919.3 | 3038 | 881.3 |  |  |  | 2021-01-14 | NO TICKET NEEDED FOR THE WORK PERFORMED. 1/14/21 GCCC TICKET NOT REQUIRED PE ENGINEER CINDY SPARKS GAVE VERBAL APPROVAL ON SITE TO PROCEED WITH JOB. EFC REPLACEMENT ONLY GAS FLOW NOT INTERUPTED JOB DELAYED DUE TO COVID 19 AND COMPLIANCE WORK AND BY NOW HAVING TO BE REVIEWED BY PE ENGINEER
20026930300 | UPGRADE ELECTRONICS | [5 empty] | 9306.71 | 3038 | 6268.71 |  |  |  | 2022-03-04 | MET MOOSE ONSITE TO INSTALL SOLAR PANEL, CELL BOOSTER,BATTERY/BOX INSTALLED NEW EC350 WSHIMFESSEL JMULLINS COMPLETED PAPER WORK 06-13-2022
20026930400 | UPGRADE ELECTRONICS | [5 empty] | 6567.19 | 3038 | 3529.19 |  |  |  | 2021-03-31 | CCC TICKET NOT REQUIRED 3/29/21 CFARIS REPLACED EFC AND WORKED TP ORDER JOB ON HOLD FOR 2020 DUE TO COVID 19 GCCC TICKET NOT REQUIRED ON 3/31/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK ALSO THIS IS NON-SCADA MONITORED GMB CFARIS
20026937200 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 |  |  |  | 2022-10-07 | RETIRE OLD MIN-AT INSTALLED NED EC350 JPASLEY 10-7-22
20026937300 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 |  |  |  | 2021-01-14 | GCCC TICKET NOT REQUIRED VERBAL APPROVAL GIVEN ONSITE BY PE ENGINEER CINDY SPARKS TO WORK JOB GAS FLOW NOT INTERUPTED TO WORK JOB THIS WAS EFC REPLACEMENT ONLY JOB DELAYED DUE TO COVID 19 COMPLIANCE WORK AND WAITING REVIEW BY PE ENGINEER
20026937500 | RETIRE ELECTRONICS | [5 empty] | 129.79 | 73.3494 | 56.4406 |  |  |  | 2022-03-04 | RETIRED MINI-AT INSTALLED NEW EC350 JMULLINS CO PAPER WORK 06132022
20026937600 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 |  |  |  | 2021-03-31 | REPLACED EFC JOB ON HOLD IN 2020 DUE TO COVID 19 GCCC TICKET NOT REQUIRED NOT AT STATION OFF SITE COMPLETING PAPERWORK ALSO THIS IS A NON-SCADA MONITORED GMB 3/31/21 CFARIS
20026940900 | INSTALL I&C EQUIPMENT | [5 empty] | 12849.77 | 18740.1071 | -5890.3371 |  |  |  | 2022-12-15 | CCC TICKET# 55594 CCC TICKET# 55594 PAPER WORK GATHER INFO 12-15-22 JBRADFORD
20026941000 | RETIRE GAUGE | [5 empty] | 1582.1 | 91.4991 | 1490.6009 |  |  |  | 2022-12-15 | CCC TICKET# 55594 CCC# 55594 ERX ONLINE P2P W/GAS CONTROL OK REMOVED CHART BOX AND FILED LAST CHART ON CABINET TICKET# 11209 GATHERED INFORMATION FOR CLOSEOUT PAPERWORK 12-15-22 JBRADFORD
20026947301 | INSTALL 3,950' - 2" PMMP | [5 empty] | 1895184.87 | 1562557.4499 | 332627.4201 |  |  |  | 2021-11-11 | TTOY/KY 3/2/22: OVERRUN EXPLANATION: FLAGGER OT ESTIMATED FOR 543 HOURS BUT ACTUAL WAS 1033 HOURS, CONTRACTOR CREWS HOURLY TIME WAS OVER ESTIMATE AT 167 EXTRA HOURS, SEGA HAD EXTRA $60,000 IN COST, COMPANY LABOR HAD ADDITIONAL $27,000 COST OVER ESTIMATE
20026947400 | RETIRE 5,000' - 4" CI/BS LP | [5 empty] | 71.35 | 103.8156 | -32.4656 |  |  |  | 2021-11-12
20026949900 | INSTALL 1100' - 2" PMMP | [5 empty] | 207663.91 | 207915.8181 | -251.9081 |  |  |  | 2021-07-15
20026950000 | RETIRE 1430' OF 2"/3" BS-MP | [5 empty] | 2502.68 | 81.9085 | 2420.7715 |  |  |  | 2021-07-15
20026955400 | RETIRE STATION | [5 empty] | 2363.47 | 1910.2958 | 453.1742 |  |  |  | 2021-02-04 | 8561 JOB WAS ON HOLD UNTIL AFTER BEGINNING OF THE YEAR
20026964102 | INSTALL 4000' OF 12"CSHP MAIN | [5 empty] | 1045900.23 | 909258.0027 | 136642.2273 |  |  |  | 2021-05-11 | TWALKER/KY 09-21-21: JOB OVER RUN DUE TO ADDITIONAL ENVIRONMENTAL AND SITE CLEANUP ON SITE DUE TO RAIN DURING CONSTRUCTION, THIS ADDED EXTRA $40,000 TO CONTRACT COST, PROJECT REQUIRED 2 COMPANY COORDINATORS BUT WAS PLANNED FOR 1 ADDED $35,000 IN LABOR COST AND SEGA INCREASED BY $33,000.
20026964200 | RETIRE 1200' OF 12"BSHP MAIN | [5 empty] | 3603.11 | 84.1799 | 3518.9301 |  |  |  | 2021-05-11
20026969900 | INSTALL FENCE & BOLLARDS | [5 empty] | 9603.34 | 36430.1489 | -26826.8089 |  |  |  | 2022-11-19 | INSTALLED NEW FENCE 11-19-22 JMULLINS
20026970000 | RETIRE BUILDING | [5 empty] | 26427.16 | 88.8156 | 26338.3444 |  |  |  | 2022-11-19 | CCC# 37831 CCC# 33819 CCC# 38966 TO BE COMP BY CFARRIS BUILDING REMOVED JMULLINS
20026976900 | INSTALL RTU & INSTRUMENTATION | [5 empty] | 362179.42 | 302143.1164 | 60036.3036 |  |  |  | 2023-08-22 | CCC# 2490 CCC# 2490 CCC# 2490 CCC# 5078 6417 CCC# 7314 CCC# 7314 CCC# 7314 CCC# 6417 CCC# 6417 CCC# 6417 CCC# 6417 CCC# 6417
20026977000 | RETIRE RTU & INSTRUMENTATION | [5 empty] | 2598.25 | 60.3089 | 2537.9411 |  |  |  | 2023-08-22
20026979600 | INSTALL 20' - 2"/6" PMMP | [5 empty] | 106288.64 | 65238.0736 | 41050.5664 |  |  |  | 2021-03-19 | ATTEMPTED TO REVISE DUE TO EXTRA HOURLY COST, COULD NOT REVISE DUE TO UNFULLFILLED PURCHASE ORDER TTOY 3/18/2021 OVERRUN EXPLANATION: JO WAS ORIGINALLY PLANNED ON 2018 FISHEL CONTRACT, JO WAS EXECUTED USING 2020 STANLEY PIPELINE CONTRACT, EXTRA VAC EXCA, EXTRA WLD AND RIG, EXTRA TOP SOIL REQUIRED, EXTRA HOURLY CREW REQUIRED, ESTIMATED HOURLY TIME WAS 56 HOURS, ACTUAL HOURLY TIME WAS 398 HOURS, ESTIMATED CONTRACT COST WAS $35,000, ACTUAL CONTRACT COST WAS $51,000
20026979700 | RETIRE 15' - 2" BSLP | [5 empty] | 71.35 | 92.1481 | -20.7981 |  |  |  | 2021-03-19
20026980401 | INSTALL 13,025'-PMMP/CSHP | [5 empty] | 2259933.17 | 1836238.4697 | 423694.7003 |  |  |  | 2022-09-29 | OVERRUN EXPLANATION: PROJECT INCLUDED ADDITIONAL PAVING THAT WAS UNFORSEEN DUE TO CITY REQUIREMENTS, SEGA HAD AN INCREASE OF OVER $100,000 TTOY 3/2/2023
20026980500 | RETIRE 12,520' - LP MAIN | [5 empty] | 809.88 | 52.2976 | 757.5824 |  |  |  | 2022-09-29
20026980601 | INSTALL 16,200'-2"/4" PMMP | [5 empty] | 4720247.08 | 4665902.1359 | 54344.9441 |  |  |  | 2022-09-29
20026980700 | RETIRE MAIN - LEAKAGE | [5 empty] | 2546.03 | 103.8156 | 2442.2144 |  |  |  | 2022-09-29
20026981601 | INSTALL 9,950' OF 2"/4"/6"PMMP | [5 empty] | 3477462.23 | 3261487.9737 | 215974.2563 |  |  |  | 2022-05-26
20026981700 | RETIRE 15,000' - LP MAIN | [5 empty] | 0 | 82.4486 | -82.4486 |  |  |  | 2022-05-26
20026981800 | RETIRE 18,000 - MP MAIN | [5 empty] | 0 | 82.4486 | -82.4486 |  |  |  | 2022-05-26
20026990100 | INSTALL 6" SS | [5 empty] | 245.63 | 1607.8146 | -1362.1846 |  |  |  | 2021-03-19
20026992600 | RETIRE MP MAIN | [5 empty] | 0 | 103.8156 | -103.8156 |  |  |  | 2022-10-11
21026101900 | RETIRE 6"MP SERVICE LINE | [5 empty] | 9737.82 | 9764.3857 | -26.5657 |  |  |  | 2022-06-14 | INSTALLED BOLTED DEAD END CAP AT END OF NC 216695 VALVE. JOSH PASLEY 6/14/22
21026103400 | INSTALL 2,700' - 2"/4" PMMP | [5 empty] | 185537.75 | 115766.1902 | 69771.5598 |  |  |  | 2022-04-22 | TTOY-9/20/22: LEVEL 2 VARIANCE OVERRUN EXPLANATION IN WMSDOCS
21026104700 | REMOVE OBSOLETE ELECTRONICS | [5 empty] | 236.27 | 135.8546 | 100.4154 |  |  |  | 2022-09-27 | INSTALLED NEW RTU BUILDING AND TRANSMITTERS JPASLEY 9-27-2022
21026107000 | INSTALL 250' - 2" PMMP | [5 empty] | 72807.39 | 25983.7669 | 46823.6231 |  |  |  | 2022-04-22 | OVERRUN EXPLANATION: PROJECT WAS PLANNED FOR OPEN CUT, NEW MAIN WAS INSTALL ED BY HEAVY ROCK BORE, ADDITIONAL LAND SERVICES WAS REQUIRED FOR EASMENT, BORE CREW HOURLY WAS MORE THAN ESTIMATED 3 MAN CREW
21026108400 | EMER - INSTALL 350' - 4" PMMP | [5 empty] | 86916.93 | 44073.8715 | 42843.0585 |  |  |  | 2021-03-16 | OVERRUN EXPLANATION: HOURLY TIME EXTIMATED AT 48 HOURS, ACTUAL TIME WAS 97 HOURS, SEGA WAS DOUBLED, CONTRACT WAS ESTIMATED FOR $29,000, ACTUAL WAS $68,000, PROJECT WAS ESTIMATED TO DIRECTIONAL BORE 150', ACTUAL INSTALL WAS OPEN CUT 345', PROJECT REQUIRED EXTRA PAVING DUE TO OPEN CUT, PROJECT REQUIRED EXTRA PROCESSED AND STONE DUST DUE TO OPEN CUT, EXTRA VACUUM EXCAV ATING WAS REQUIRED, ESTIMATED FOR 4 MAN CREW CONTRACT, ACTUAL USED 3 MAN, 4 MAN, AND 5 MAN CREWS
21026108500 | EMER - RETIRE 350' - 4" PMP | [5 empty] | 4479.43 | 85.3307 | 4394.0993 |  |  |  | 2021-03-16
21026110900 | INSTALL REPLACEMENT FENCE | [5 empty] | 4971.16 | 44982.9906 | -40011.8306 |  |  |  | 2021-07-09 | CCC# 30433 MONITORED FENCE INSTALLATION CCC# 30433 CCC# 30596 CC# 30596 MONTOR STATION CCC# 30956 NEW FENCE INSTALLED WSHIMFESSEL 07-09-2021 UNDERRUN EXPLANATION: COST WAS SIGNIFICANTLY LESS THAT WHAT THE CONTRACTOR HAD ESTIMATED OVER THE PHONE.
21026111300 | RETIRE R-1654 | [5 empty] | 0 | 3585.1779 | -3585.1779 |  |  |  | 2022-05-10 | ENTIRE STATION RETIRED INCLUDING INLET AND OUTLET PIPING WSHIMFESSEL 5/10/2 022, RWILLIAMS COMPLETED JOB AND PAPERWORK
21026111400 | RETIRE R-1653-B LP | [5 empty] | 0 | 3585.1779 | -3585.1779 |  |  |  | 2022-05-18 | RETIRED LP RUN FROM R-1653 BLIND FLANGED INLET VALVE AND BYPASS VALVE WSHIM FESSEL, RWILLIAMS COMPLETED JOB AND PAPERWORK
21026112900 | INSTALL 150' - 2" PMMP | [5 empty] | 14483.58 | 15892.286 | -1408.706 |  |  |  | 2021-09-29
21026117400 | INSTALL 190' - 4" PMMP SL | [5 empty] | 40096.06 | 22441.9346 | 17654.1254 |  |  |  | #N/A | INSTALLED 243'OF 4"PMP FOR SL TO FEED PSID 501307207-CAPPED AND BURRIED END OF SL FOR FUTURE TIE IN/INSTALLATION OF RISER AND SETTING ONCE FURTHER SITE CONSTRUCTION IS COMPLETED,PER CG ENGINEER J TOY AND CONSTRUCTION SITE GC- LINE MARKER WITH WIRE AT TAP,WIRE IN VALVE BOX,AND MARKER BALLS AT ALL CHANGES OF DIRECTIONAND END OF SL INSTALLED FOR LOCATABILITY
21026117500 | INSTALL GMB SETTING | [5 empty] | 77589.89 | 58469.7613 | 19120.1287 |  |  |  | 2022-05-03
21026119200 | PM- LAKE CARNICO REPLACEMENT | [5 empty] | 3041365.07 | 3161436 | -120070.93 |  |  |  | 2022-10-13
21026119300 | PM- LAKE CARNICO ABANDONMENT | [5 empty] | 739279.78 | 62500 | 676779.78 |  |  |  | 2022-10-13
21026120000 | PM-PARIS CYNTHIANA REPLACEMENT | [5 empty] | 3020752.24 | 1087500 | 1933252.24 |  |  |  | 2022-09-22
21026120100 | PM-PARIS CYNTHIANA ABANDONMENT | [5 empty] | 325920.13 | 62500 | 263420.13 |  |  |  | 2022-09-22
21026120900 | INSTALL 5' - 3" PMLP | [5 empty] | 1085.98 | 1134.2677 | -48.2877 |  |  |  | 2021-04-26
21026121000 | RETIRE 5' - 3" PMLP | [5 empty] | 0 | 58.9085 | -58.9085 |  |  |  | 2021-04-26
21026121100 | INSTALL 5' - 4" PMMP | [5 empty] | 2417.89 | 2822.803 | -404.913 |  |  |  | 2021-04-28
21026121200 | RETIRE 5' - 4" PMLP | [5 empty] | 0 | 58.9085 | -58.9085 |  |  |  | 2021-04-28
21026123100 | INSTALL 175'-4" PMMP | [5 empty] | 53913.76 | 39889.572 | 14024.188 |  |  |  | 2021-07-07
21026123200 | RETIRE 200'-4" BSMP | [5 empty] | 0 | 77.7619 | -77.7619 |  |  |  | 2021-07-07
21026123300 | INSTALL 125'-2" PMMP | [5 empty] | 36910.92 | 28847.4767 | 8063.4433 |  |  |  | 2021-07-20
21026123400 | RETIRE 160'-4" PMMP | [5 empty] | 0 | 77.7619 | -77.7619 |  |  |  | 2021-07-20
21026125100 | RETIRE 175' - 3" LP | [5 empty] | 0 | 88.1542 | -88.1542 |  |  |  | 2021-07-08
21026125200 | INSTALL 3" SS | [5 empty] | 5010.94 | 20373.572 | -15362.632 |  |  |  | 2021-07-08
21026128200 | INSTALL 1,300 OF 2"/4"PMMP | [5 empty] | 56524.7 | 51810.9858 | 4713.7142 |  |  |  | 2021-11-19
21026135300 | ABANDON 120'-4" PL SL | [5 empty] | 0 | 82.634 | -82.634 |  |  |  | 2021-08-05
21026135400 | INSTALL 100'-4" PL SL | [5 empty] | 12266.69 | 10216.5972 | 2050.0928 |  |  |  | 2021-08-06
21026135900 | INSTALL 140'-2" PMMP | [5 empty] | 8332.52 | 14039.3957 | -5706.8757 |  |  |  | 2021-12-02
21026136700 | INSTALL 1,750'-2" PMMP | [5 empty] | 47459.5 | 49760.6579 | -2301.1579 |  |  |  | 2021-11-23
21026137400 | RETIRE 120'-1" PMP - D304537 | [5 empty] | 399.97 | 3638.7915 | -3238.8215 |  |  |  | 2021-08-21
21026137900 | INSTALL OUTLET VLV R-1643 | [5 empty] | 80161.67 | 110321.1916 | -30159.5216 |  |  |  | 2022-09-08 | CCC# 80227 MONITOR WHILE BACKFILLING INSTALLED ALL NEW STATION VALVES JPASLEY 9-8-22 UNDERRUN EXPLANATION: PROJECT INCLUDED $27,000 OF CONTINGENCY AND HAD AN UNDERRUN OF 30,492 TTOY 3/2/23
21026138000 | RETIRE OUTLET VLV R-1643 | [5 empty] | 0 | 955.7874 | -955.7874 |  |  |  | 2022-09-08 | RETIRED ALL STATION VALVES AND INSTALLED NEW VALVES JPASLEY 9-8-22
21026138400 | EMER-INSTALL 2' OF 1"PMMP MAIN | [5 empty] | 227.74 | 3122.8539 | -2895.1139 |  |  |  | 2021-08-26
21026138500 | EMER-RETIRE 2'-1"PAMP MAIN | [5 empty] | 0 | 82.634 | -82.634 |  |  |  | 2021-08-26
21026140000 | RETIRE 489'-4" PMP | [5 empty] | 20306.35 | 13697.8754 | 6608.4746 |  |  |  | 2022-02-09
21026140501 | INSTALL 1,985'-6" CSHP | [5 empty] | 143065.13 | 116515.0569 | 26550.0731 |  |  |  | 2023-05-19
21026140600 | RETIRE 2,598'- 6" BSHP | [5 empty] | 182.4 | 61.5191 | 120.8809 |  |  |  | 2023-05-19
21026140700 | RETIRE 2,200' - CSMP | [5 empty] | 0 | 61.2976 | -61.2976 |  |  |  | 2022-10-11
21026142000 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 11087.26 | 7513.9749 | 3573.2851 |  |  |  | 2021-09-15
21026142100 | EMER - RETIRE 5'-3" PMMP | [5 empty] | 0 | 69.8875 | -69.8875 |  |  |  | 2021-09-15
21026142300 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 11040.25 | 3984.9999 | 7055.2501 |  |  |  | 2021-09-16
21026142400 | EMER - RETIRE 5'-2" PMP | [5 empty] | 133.69 | 69.8875 | 63.8025 |  |  |  | 2021-09-16
21026143200 | EMER - INSTALL 450'- 4" CSHP | [5 empty] | 257776.24 | 196595.4538 | 61180.7862 |  |  |  | 2021-12-14 | PROJECT WAS CODED AMRCB BECAUSE THE PIPE UNDER THE BRIDGE HAD NO COATING. OVERRUN EXPLANATION: MAIN REASON FOR PROJECT COST OVERRUN IS DUE TO 2,000 UNITS OF ASPHALT PAVING WHEN ONLY 1,000 UNITS WERE PLANNED. THE STATE REQUIRED EXTRA PAVING DUE TO EXISTING ROAD CONDITION.THE PROJECT WAS PLANNED FOR 1 CONSTRUCTION COORDINATORBUT ENDED UP HAVING MULTIPLE AND DOUBLED THE COMPANY LABOR CHARGES. FLAGGING FOR THEPROJECT INCLUDED A 30% INCREASECOMPARED TO THE PLANNED AMOUNT. THE PROJECT INCLUDED AN ADDITIONAL 49 UNITS OF STEELMAINLINE INSTALLATION AND ROCK AND LEDGE EXCAVATIONWAS REQUIRED BUT NOT PLANNED. TTOY 12/2/22
21026143300 | EMER - RETIRE 100'-3" CSHP | [5 empty] | 3034.48 | 61.5191 | 2972.9609 |  |  |  | 2021-12-14
21026147700 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 2531.33 | 2686.3426 | -155.0126 |  |  |  | 2021-10-20 | REPLACED 3' SECTION OF 2" PMP AFTER DIG IN. PRESSURE TESTED NEW MAIN AT 90 PSIG FOR 1 HOUR, SOAP TESTED FINAL TIE IN AT OP. OK 34 PSIG VERIFIED NRICHIE 10-20-21
21026147800 | EMER - RETIRE 5'-2" PMP | [5 empty] | 0 | 61.5191 | -61.5191 |  |  |  | 2021-10-20
21026149800 | RETIRE R-1615 | [5 empty] | 552.62 | 16113.7857 | -15561.1657 |  |  |  | 2023-05-09
21026152700 | EMER - INSTALL ODORIZER | [5 empty] | 170463.75 | 303602.2828 | -133138.5328 |  |  |  | 2022-08-16 | UNDERRUN EXPLANATION: PROJECT DID NOT REQUIRE AS MUCH CONTINGENCY, OR OUTSIDE LABOR COSTS FROM CONTRACTORS TTOY 3/2/23
21026152800 | EMER - RETIRE ODORIZER | [5 empty] | 62508.06 | 61.5191 | 62446.5409 |  |  |  | 2022-08-16
21026156100 | EMER-INSTALL 6' OF 2"PMMP MAIN | [5 empty] | 5612.12 | 6138.1743 | -526.0543 |  |  |  | 2021-12-14
21026156200 | EMR-RET 6'-2"PMP MAIN D222323 | [5 empty] | 75.03 | 61.2976 | 13.7324 |  |  |  | 2021-12-14
21026157501 | EMER - INSTALL 5'-3" PMMP | [5 empty] | 24476.25 | 13441.7151 | 11034.5349 |  |  |  | 2021-12-27
21026157600 | EMER - RETIRE 5'-3" PAMP | [5 empty] | 106.63 | 72.8047 | 33.8253 |  |  |  | 2021-12-27
21026993100 | RETIRE 229' - PMMP | [5 empty] | 0 | 103.8156 | -103.8156 |  |  |  | 2021-11-12
21026996700 | EMER - INSTALL 10'-4" PMMP | [5 empty] | 1315.39 | 1997.1109 | -681.7209 |  |  |  | 2021-01-11
21026996800 | EMER - RETIRE 10'-4" PMMP | [5 empty] | 0 | 95.6296 | -95.6296 |  |  |  | 2021-01-11
21026999000 | RETIRE 4"PLP SERVICE LINE | [5 empty] | 4696.25 | 5007.8601 | -311.6101 |  |  |  | 2022-09-28
22026158000 | INSTALL 200'-2" PMMP | [5 empty] | 23838.83 | 16273.357 | 7565.473 |  |  |  | 2022-03-16
22026159500 | EMER - INSTALL 5'-3" PMMP | [5 empty] | 11760.26 | 5999.0379 | 5761.2221 |  |  |  | 2022-01-10
22026159600 | EMER - RETIRE 5' - 3" PMMP | [5 empty] | 0 | 79.0999 | -79.0999 |  |  |  | 2022-01-10
24026337600 | INSTALL 30'-2" PMMP | [5 empty] | 27755.6 | 27915.2109 | -159.6109 | 2024-01-01 | 2024-12-31 | 2024-05-17 | 2024-05-23
22026161900 | RETIRE LP MAIN - LEAKAGE | [5 empty] | 1465.95 | 124.7348 | 1341.2152 |  |  |  | #N/A
22026163000 | INSTALL ODORIZER | [5 empty] | 421358.34 | 596431.4654 | -175073.1254 |  |  |  | #N/A
23026287600 | INSTALL 30'-4" PMMP | [5 empty] | 19740.37 | 14529.6064 | 5210.7636 | 2024-01-01 | 2024-12-31 | 2024-06-17 | 2024-06-20
22026164100 | RETIRE 6,711'-BS/CS IP | [5 empty] | 663.39 | 74.3089 | 589.0811 |  |  |  | #N/A
22026164201 | INSTALL 2,300'-2" PMMP | [5 empty] | 487634.39 | 442002.9907 | 45631.3993 |  |  |  | 2023-08-03
22026164300 | RETIRE 3,574'-BSLP | [5 empty] | 136.8 | 84.9152 | 51.8848 |  |  |  | 2023-08-03
22026168900 | STEPSTONE POD HVAC UPGRADE | [5 empty] | 19703.94 | 15710.0767 | 3993.8633 |  |  |  | 2022-08-05 | CCC# 59338 CCC# 55889 UPGRADED RTU JOSH MULLINS
22026169100 | RT. 89 POD RTU BUILDING | [5 empty] | 221479.78 | 143652.6755 | 77827.1045 |  |  |  | 2023-05-25 | CCC# 13947 MONITOR NOT ONSITE ACP NOT WORKING AT THAT SITE TODAY CCC# 13947 NOT ONSITE NOT ONSITE CCC#21297 CCC# 31371
22026170600 | INSTALL 7,200'-2"/4" PMMP | [5 empty] | 1527638.88 | 1129128.3572 | 398510.5228 |  |  |  | 2023-09-22
22026170700 | RETIRE BSLP | [5 empty] | 0 | 89.0305 | -89.0305 |  |  |  | 2023-09-22
22026172500 | INSTALL 5'-1" PMMP | [5 empty] | 4.3 | 1353.2384 | -1348.9384 |  |  |  | 2022-03-02
22026172600 | RETIRE 5'-1" PAMP | [5 empty] | 2198.83 | 66.5954 | 2132.2346 |  |  |  | 2022-03-02
22026173700 | 2022 SCADA VISIBILITY PROGRAM | [5 empty] | 28387.14 | 29658.8599 | -1271.7199 |  |  |  | 2022-09-22 | CCC# 66803 CCC# 66803 MONITOR FOR NEW COMM INSTALL CCC# 80236 INSTALLED NEW MIWI350 EBLANTON 9-22-2022
22026175300 | RETIRE R-1278 | [5 empty] | 1891.36 | 7307.4769 | -5416.1169 |  |  |  | 2022-12-15 | PREMISE IS RETIRED. GATHERED INFORMATION FOR CLOSEOUT PAPERWORK. JBRADFORD 12-15-22 CCC# 20387 TICKET# 20387
22026175400 | RETIRE R-1258 | [5 empty] | 114.11 | 7307.4769 | -7193.3669 |  |  |  | 2022-08-26 | CCC# 77893 STATIONRETIRED PER AMRP PROJECT WSHIMFESSEL 8-26-2022 ALL FACILITIES REMOVE D
22026175500 | RETIRE R-1275 | [5 empty] | 648.29 | 7307.4769 | -6659.1869 |  |  |  | 2022-08-26 | CCC# 77909 RETIRED REG STATION R-1275 ON AMRP PROJECT WSHIMFESSEL 8-26-2022 PREMISE IS RETIRED. GATHERED INFORMATION FOR CAPITOL CLOSEOUT.
22026175600 | RETIRE R-1256 | [5 empty] | 211.37 | 7307.4769 | -7096.1069 |  |  |  | 2022-06-17 | STATION RETIRED AND ALL PIPING REMOVED WSHIMFESSEL 06-07-2022
22026177500 | EMER - INSTALL 800'-6" CSHP | [5 empty] | 1030814.44 | 663631.3961 | 367183.0439 |  |  |  | 2022-09-28 | LEVEL 2 VARIANCE EXPLANATION IN WMSDOCS TTOY 2/3/23
22026177600 | EMER-RETIRE 800'-4" CSHP | [5 empty] | 1361.76 | 84.9152 | 1276.8448 |  |  |  | 2022-09-28
22026177700 | INSTALL 56'-6" PM-LP | [5 empty] | 107530.2 | 50137.1407 | 57393.0593 |  |  |  | 2022-05-16 | OVERRUN EXPLANATION: PROJECT WAS INITIALLY PLANNED FOR 56 FEET OF INSTALL. HOWEVER, 171 FEET OF DIRECTIONAL ROCK BORE WERE REQUIRED INSTEAD WITHOUT A SCOPE CHANGE REQUEST. ADDITIONAL SAW CUT AND CUT AND REMOVE WERE REQUIRED A S WELL. STEEL PLATES WERE NOT ESTIMATED. $7000 OF SEWER CAMERA WERE NOT EST IMATED EITHER SINCE IT WAS INITALLY PLANNED DIFFERENTLY. ALL THIS ADDITIONA L WORK TOOK MORE TIME SO LABOR INCREASED BY $19,000 AND THE OVERHEAD EFFECT OF THESE CHANGES WAS $9000.
22026177800 | ABDN 20'-6" BS-LP | [5 empty] | 142.7 | 73.9724 | 68.7276 |  |  |  | 2022-05-16
22026178200 | INSTALL 850'-2" PMIP | [5 empty] | 28727.79 | 33743.7503 | -5015.9603 |  |  |  | 2022-05-17
22026182101 | INSTALL 8,450' - 2"/4" PMMP | [5 empty] | 940113.78 | 861854.0803 | 78259.6997 |  |  |  | 2023-09-19
22026183800 | INSTALL 100'-2" PMIP | [5 empty] | 16969.45 | 18017.5748 | -1048.1248 |  |  |  | 2022-07-21
22026184000 | INSTALL 200'-6"/8" PMLP | [5 empty] | 210431.38 | 169438.8752 | 40992.5048 |  |  |  | 2022-08-30 | OVERRUN EXPLANATION: PROJECT WAS PLANNED FOR 360 HOURS OF LABOR TIME BUT ENDED UP WITH 565 HOURS DUE TO MULTIPLE COORDINATORS AND WELDER CHARGING 125 HOURS, SEGA WAS ORIGINALLY $20,641 BUT ENDED UP AT $34,463, PROJECT REQUIRED 698 TONS OF STONE AND DUST BUT WAS ORIGINALLY PLANNED FOR 60 TONS, ADDITIONAL EXTRA DEPTH UNITS OF 134, PROJECT ALSO CHAR CHARGED ~$6,000 OF SEWER CAMERA EVEN THOUGH THE SEWER WAS ALREADY UNCOVERED WHICH IS WHY WE WERE INSTALLING THE RELOCATION. TTOY 2/3/23
22026184100 | RETIRE 100'-BSLP | [5 empty] | 400 | 65.0112 | 334.9888 |  |  |  | 2022-08-30
22026185100 | INSTALL 10'-2" PMMP | [5 empty] | 6123.2 | 3850.4525 | 2272.7475 |  |  |  | 2022-05-10
22026185200 | RETIRE 10'-2" PMP | [5 empty] | 0 | 74.2578 | -74.2578 |  |  |  | 2022-05-10
22026190700 | INSTALL 4" SS *PAPER ONLY*** | [5 empty] | 0 | 84.2578 | -84.2578 |  |  |  | 2021-08-02 | FACILITY CREATED ON JO 20-0269816-01. UNABLE TO EDIT. SS ALREADY ABANDONED ON JO 22-0261909-00 BEFORE THIS JO WAS CREATED.
22026190800 | INSTALL 50'-4" PMLP | [5 empty] | 48441.53 | 45570.6341 | 2870.8959 |  |  |  | 2022-07-21
22026190900 | RETIRE 41'-4" BSLP | [5 empty] | 114.59 | 78.4365 | 36.1535 |  |  |  | 2022-07-21
22026191300 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 839.28 | 4801.1928 | -3961.9128 |  |  |  | 2022-06-21 | CCC# 71072
22026191400 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 0 | 124.8731 | -124.8731 |  |  |  | 2022-06-21
22026192500 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 400.52 | 4801.1928 | -4400.6728 |  |  |  | 2022-06-22 | CCC# 71244
22026192600 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 0 | 124.8731 | -124.8731 |  |  |  | 2022-07-05
22026194600 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 4024.88 | 4801.1928 | -776.3128 |  |  |  | 2022-10-12 | CCC# 3219 INSTALLED MIWI INSTALLED NEW MIWI350 WSHINFESSEL 10-12-22
22026194700 | RETIRED ELECTRONIC EXCHANGE | [5 empty] | 0 | 124.8731 | -124.8731 |  |  |  | 2022-10-12 | RETIRED OLD ERX WSHINFESSEL 10-12-22
22026194800 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5891.93 | 4801.1928 | 1090.7372 |  |  |  | 2022-08-25 | CCC# 78666 INSTALLED NEW MIWI350 JPASLEY 8-25-22
22026194900 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 0 | 124.8731 | -124.8731 |  |  |  | 2022-08-25 | RETIRED ERX INSTALLED NEW MIWI350 JPASLEY 8-25-22
22026195200 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 6702.65 | 4801.1928 | 1901.4572 |  |  |  | 2022-10-21 | CCC# 4229 CCC# 4229 INSTALLED NEW MIWI350 JPASLEY
22026195300 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 34.29 | 124.8731 | -90.5831 |  |  |  | 2022-10-21 | CCC# 4229 RETIRED OLD ERX INSTALLED NEW MIWI350 JPASLEY
22026196700 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5374.37 | 4801.1928 | 573.1772 |  |  |  | 2022-08-31 | CCC# 79339 INSTALLED NEW MIWI350. P2P W/GC OK 08/31/2022 WSHIMFE
22026196800 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 0 | 124.8731 | -124.8731 |  |  |  | 2022-08-31 | RETIRED OLD ERX INSTALLED NEW MIWI350 WSHIMFESSEL 8-31-2022
22026196900 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5192.52 | 4801.1928 | 391.3272 |  |  |  | 2022-08-26 | INSTALLED NEW MIWI350 JPASLEY 8-26-22
22026197000 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 698.72 | 124.8731 | 573.8469 |  |  |  | 2022-08-26 | RETIRED OLD ERX JPASLEY 8-26-22
22026198400 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5538.33 | 4801.1928 | 737.1372 |  |  |  | 2022-09-21 | ASSIST WITH RUNNING STAINLESS 09-21-2022 RHAYES CCOX RETIRED OLD ERX INSTALL NEW MIWI350 CCOX 9-21-22
22026198500 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 450.09 | 124.8731 | 325.2169 |  |  |  | 2022-09-21
22026199700 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5650.33 | 4801.1928 | 849.1372 |  |  |  | 2022-09-20 | RETIRED OLD ERX INSTALLED NEW MIWI350 EBLANTON 9-20-22
22026199800 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 592.76 | 124.8731 | 467.8869 |  |  |  | 2022-09-20 | RETIRED OLD RX INSTALLED NEW MIWI350 EBLANTON 9-20-22
22026205800 | RETIRE 20'-2" PMP | [5 empty] | 0 | 89.0305 | -89.0305 |  |  |  | 2023-09-18
22026205900 | RETIRE R-1682 | [5 empty] | 603.96 | 1417.3638 | -813.4038 |  |  |  | 2023-09-14
22026211500 | EMER-INSTALL 5'-2" PMMP | [5 empty] | 5656.19 | 16105.0112 | -10448.8212 |  |  |  | 2022-09-12
22026211600 | EMER-RETIRE 5'-2" PMMP | [5 empty] | 3884.45 | 4031.2726 | -146.8226 |  |  |  | 2022-09-12
22026212100 | INSTALL CHAIN LINK FENCE | [5 empty] | 9226.54 | 24086.2589 | -14859.7189 |  |  |  | 2022-11-11 | INSTALLED CHAIN LINK FENCE JMULLINS 11-11-22
22026214300 | STEPSTONE POD HVAC/RTU | [5 empty] | 0 | 55.5311 | -55.5311 |  |  |  | 2022-08-05 | UPGRADED RTU
22026217500 | EMER-INSTALL 2' OF 3"PMMP MAIN | [5 empty] | 6378.4 | 5764.1191 | 614.2809 |  |  |  | 2022-08-12
22026217600 | EMER-RETIRE 2' OF 3"PAMP MAIN | [5 empty] | 4155.42 | 1084.9152 | 3070.5048 |  |  |  | 2022-08-12
22026219700 | EMER-INSTALL 8" STOPPLE FITS | [5 empty] | 39002.9 | 30183.131 | 8819.769 |  |  |  | 2022-09-01
22026219800 | EMER-RETIRE 1' OF 8"CSHP MAIN | [5 empty] | 160 | 84.9152 | 75.0848 |  |  |  | 2022-09-01
22026221900 | EMER - RETIRE 20'-3" PMP | [5 empty] | 6987.81 | 3460.1765 | 3527.6335 |  |  |  | 2022-10-04
22026222300 | EMER - INSTALL 7'-4" PMLP | [5 empty] | 13873.55 | 4005.634 | 9867.916 |  |  |  | 2022-09-14
22026222400 | EMER - RETIRE 7'-4" PLP | [5 empty] | 0 | 89.0305 | -89.0305 |  |  |  | 2022-09-14
22026227600 | EMER - INSTALL 60'-4" PMLP | [5 empty] | 21421.89 | 30615.0582 | -9193.1682 |  |  |  | 2022-09-28
22026227700 | EMER - RETIRE 60'-4" BSLP | [5 empty] | 8123.84 | 74.3089 | 8049.5311 |  |  |  | 2022-09-28
22026228201 | INSTALL 4,225'-2"/6" PMMP | [5 empty] | 1935349.38 | 1875934.718 | 59414.662 |  |  |  | 2023-05-22
22026228300 | RETIRE 6,106'- LP MAIN | [5 empty] | 182.4 | 952.0929 | -769.6929 |  |  |  | 2023-05-19
22026228400 | RETIRE 1133'- MP MAIN | [5 empty] | 0 | 952.0929 | -952.0929 |  |  |  | 2023-05-04
22026228700 | RETIRE ELECTRONIC | [5 empty] | 0 | 74.3089 | -74.3089 |  |  |  | 2022-09-29
22026230301 | INSTALL 1,725'-2" PMMP | [5 empty] | 676511.46 | 636475.4754 | 40035.9846 |  |  |  | 2023-03-17
22026230400 | RETIRE 5,578' - IP MAIN | [5 empty] | 1019.8 | 475.239 | 544.561 |  |  |  | 2023-03-17
22026230500 | RETIRE 1,368' - MP MAIN | [5 empty] | 14.31 | 475.239 | -460.929 |  |  |  | 2023-03-17
22026231000 | EMER - INSTALL 1'-2" PMMP | [5 empty] | 6865.44 | 8585.1316 | -1719.6916 |  |  |  | 2022-12-04
22026231100 | EMER - RETIRE 1'-2" PMP | [5 empty] | 0 | 60.3089 | -60.3089 |  |  |  | 2022-12-04
22026232600 | INSTALL 200'-2" PMMP | [5 empty] | 20049.03 | 40586.0582 | -20537.0282 |  |  |  | 2022-12-16
22026234100 | NEW RTU/COMM BUILDING | [5 empty] | 0 | 136.2135 | -136.2135 |  |  |  | 2022-09-27
22026234500 | INSTALL NEW RTU/COMM BUILDING | [5 empty] | 0 | 136.2135 | -136.2135 |  |  |  | 2022-09-29 | JMULLINS COMPLETING PAPERWORK
22026234700 | INSTALL 3" STOPPLE FITTING | [5 empty] | 7929.81 | 13630.9028 | -5701.0928 |  |  |  | 2022-11-30
22026234800 | RETIRE 75' OF 3"BSMP MAIN | [5 empty] | 114.9 | 119.2135 | -4.3135 |  |  |  | 2022-11-29
22026234901 | INSTALL 4,100'-2" PMMP | [5 empty] | 217597.98 | 188453.1623 | 29144.8177 |  |  |  | 2023-11-20
22026236400 | INSTALL 450'-4" PMMP | [5 empty] | 52709.69 | 61251.1595 | -8541.4695 |  |  |  | 2023-06-27
24026365700 | INSTALL 320' OF 2"PMIP MAIN | [5 empty] | 29754.73 | 31921.5843 | -2166.8543 | 2024-01-01 | 2024-12-31 | 2024-12-02 | 2024-12-18
22026237400 | RETIRE LP MAIN | [5 empty] | 886.14 | 139.1159 | 747.0241 |  |  |  | #N/A
22026237500 | RETIRE MP MAIN | [5 empty] | 554.6 | 139.1159 | 415.4841 |  |  |  | #N/A
23026299700 | INSTALL 325' OF 2"PMMP MAIN | [5 empty] | 52412.36 | 30286.964 | 22125.396 | 2024-01-01 | 2024-12-31 | 2024-03-07 | 2024-03-14 | TWALKER/KY 03-22-24: JOB OVER RUN DUE TO UNKNOWN CROSS BORE DISCOVERED AT TIE IN POINT FOR THIS PROJECT, CREWS HAD TO CORRECT THAT ISSUE WHICH ADDED ADDITIONAL TIME/MONEY FOR CONTRACTOR AND CONS COORDINATOR
22026237900 | RETIRE 5,265' IP MAIN | [5 empty] | 217.02 | 135.9942 | 81.0258 |  |  |  | #N/A
22026238100 | RETIRE R-1230-A | [5 empty] | 2779.72 | 1996.3422 | 783.3778 |  |  |  | #N/A | CCC#62228
22026240500 | INSTALL VRG | [5 empty] | 7577.2 | 14784.1417 | -7206.9417 |  |  |  | 2022-12-08 | NOT ON SITE. GETTING MATERIAL FROM SHOP FOR JOB. CCC# 6417 CCC# 6417 CCC# 6417 CCC# 6417
22026240600 | RETIRE VRG | [5 empty] | 1416.09 | 1478.5709 | -62.4809 |  |  |  | 2022-12-08
22026240700 | INSTALL FENCE FOR NEW LAND | [5 empty] | 63926.63 | 26194.1417 | 37732.4883 |  |  |  | 2022-11-30 | CCC# 12436 TICKET# 12436 CCC# 16515 GATHER INFO FOR CAPITAL PAPERWORK
22026244400 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 17382.14 | 26337.6752 | -8955.5352 |  |  |  | 2023-04-04 | CCC# 22134 WELDED NEW TAP ON INLET FOR MIWI INSTALL, JMARTIN DMARTIN 3-27-23 CCC# 23352 INSTALL NEW MIWI 350, UNIT IS WAITING FOR A TICKET # TO BE ABLE TO PUT ONLINE. JMARTIN 4-4-23 CCC# 23905 STILL NEED TO DO P2P WITH GAS CONTROL, MODEM NOT COMMUNICATING JMARTIN 4-6-23 CCC# 24126 TRIED TO FIX COMM ISSUE WITH MODEM CCC# 23905 P2P W/GAS CONTROL OK, JMARTIN 4-10-23 CCC# 26515 COMP ANOTHER P2P WITH GAS CONTROL. JMARTIN 4-21-23 NOT ONSITE, FIXED ISO AND SUBMITTED NEW CAP FOR DRAWING.
22026244500 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 17938.12 | 19488.6752 | -1550.5552 |  |  |  | 2023-04-10 | CCC# 22091 INSTALLED NEW INLET TAP FOR MIWI, JMARTIN DMARTIN 3-27-23 NOT ONSITE DELAY DUE TO RAIN NOT ONSITE ACP RESCHEDULED CCC# 24233 INSTALLED NEW MIWI 350 CCC# 26551 WORKED WITH GC TO GET SITE ONLINE. P2P COMP. JMARTIN 4-21-23 NOT ONSITE, UPDATED ISO AND SBMITTED REDLINED DRAWIN.
22026245300 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 3807.72 | 10393.9744 | -6586.2544 |  |  |  | 2023-01-19
22026245400 | EMER - RETIRE 5'-2" PMMP | [5 empty] | 0 | 131.2422 | -131.2422 |  |  |  | 2023-01-19
22026245700 | INSTALL BUILDING R-1667 | [5 empty] | 651.28 | 300.4844 | 350.7956 |  |  |  | 2022-12-28
22026245800 | RETIRE MIS FACILITIES R-1639 | [5 empty] | 0 | 131.2422 | -131.2422 |  |  |  | 2022-12-28
23026248700 | INSTALL 2" SS | [5 empty] | 2373.93 | 18496.357 | -16122.427 |  |  |  | 2023-03-22
23026248800 | RETIRE 50' - 2" CSMP | [5 empty] | 6678.36 | 138.8485 | 6539.5115 |  |  |  | 2023-03-22
23026250900 | INSTALL EC 350 | [5 empty] | 755.31 | 2339.3221 | -1584.0121 |  |  |  | 2023-02-07 | INSTALLED NEW EC 350 INSTALLED EC 350 J.BRADFORD 2-7-23
23026251000 | RETIRE PAPER BILLING CHART | [5 empty] | 803.89 | 131.2422 | 672.6478 |  |  |  | 2023-02-07 | BILLING CHART REMOVED AND EC 350 INSTALLED
23026251600 | INSTALL RTU BUILDING | [5 empty] | 2010.08 | 170.6969 | 1839.3831 |  |  |  | 2023-05-25 | CCC#28635 WORK DONE FOR WHAT THEY ARE DOING TODAY 5-5-23 JUSTIN HOBBS CCC# 31032 CREATED OTH FACID 861369 FOR HVAC. SM 12/1/23
23026252400 | RETIRE GMB MS#804399 RUN | [5 empty] | 21780.96 | 2962.0987 | 18818.8613 |  |  |  | 2023-02-06 | NOT ONSITE NOT ONSITE GATHERING PARTS CCC# 15748 TICKET# 15748 RETIRED GMB SETTING 2-6-23 BY J.BRADFORD
23026253100 | PM- GREENSITE TRABU INSTALL | [5 empty] | 30780.16 | 1236355 | -1205574.84 |  |  |  | 2022-09-26
23026253200 | PM- GREENSITE TRABU ABANDON | [5 empty] | 235.97 | 0 | 235.97 |  |  |  | 2022-09-26
23026253700 | PM-GREENSITE HWY 27 INSTALL | [5 empty] | 20755.46 | 1236355 | -1215599.54 |  |  |  | 2022-09-27
23026253800 | PM-GREENSITE HWY 27 ABANDON | [5 empty] | 137.28 | 0 | 137.28 |  |  |  | 2022-09-27
23026261100 | INSTALL ULTRASONIC METER | [5 empty] | 52334.12 | 48123.5304 | 4210.5896 |  |  |  | #N/A | TICKET# 41313 CCC# 60438 TICKET# 60438 CCC# 60946 P2P W/ GC
23026263200 | GMB TO CAB CONVERSION | [5 empty] | 758.88 | 124.7348 | 634.1452 |  |  |  | 2023-05-02 | GATHER PARTS INFO 27 - 300,000 BTU HANGING UNIT HEATERS = 8,100,000 3 - 300,000 BTU ROOF TOP UNITS = 900,000 TOTAL BTU LOAD - 9,000,000 GMB TO CAB CONVERSION
23026264000 | INSTALL NEW METER | [5 empty] | 29289.91 | 31875.3689 | -2585.4589 |  |  |  | #N/A | CCC 71591 INSTALLED NEW METER CCC 71591
23026266800 | EMER - INSTALL 7'-2" PMMP | [5 empty] | 537.54 | 15964.0017 | -15426.4617 |  |  |  | 2023-04-05
23026266900 | EMER - RETIRE 7'-2" PMAP | [5 empty] | 0 | 64.7348 | -64.7348 |  |  |  | 2023-04-05
23026267000 | EMER - INSTALL 2'-2" PMLP | [5 empty] | 1235.74 | 7754.9733 | -6519.2333 |  |  |  | 2023-04-05
23026267100 | EMER - RETIRE 2'-2" PLP | [5 empty] | 0 | 64.7348 | -64.7348 |  |  |  | 2023-04-05
23026267600 | INSTALL 110'-4"PMLP | [5 empty] | 32525.16 | 46300.0467 | -13774.8867 |  |  |  | 2023-09-11
23026268700 | PM-DE LINE PH 2 DENT 2/STPL 3 | [5 empty] | 705427.76 | 1307000 | -601572.24 |  |  |  | 2023-05-23
23026269400 | PM-DE LINE ILI PH2 DENT2,STPL3 | [5 empty] | 198957.22 | 216349 | -17391.78 |  |  |  | 2023-05-31
23026273200 | EMER-RETIRE 741'-1" PMP | [5 empty] | 1327.21 | 1738.6263 | -411.4163 |  |  |  | 2023-05-24
23026274800 | RETIRE REG BUILDING | [5 empty] | 0 | 117.7346 | -117.7346 |  |  |  | 2023-05-15
23026274900 | EMER - INSTALL 4'-2" PMMP | [5 empty] | 15519.62 | 31722.4446 | -16202.8246 |  |  |  | 2023-05-24
23026275000 | EMER - RETIRE 4'-2" PMMP | [5 empty] | 2331.35 | 139.1159 | 2192.2341 |  |  |  | 2023-05-24
23026275100 | RETIRE 276'-3" BSLP | [5 empty] | 5918.41 | 12701.243 | -6782.833 |  |  |  | 2023-05-23
23026276600 | RETIRE RTU FACILITY | [5 empty] | 2357.33 | 139.1159 | 2218.2141 |  |  |  | 2023-11-20 | CCC#33813 PICKED UP TRASH CPRRECTED PAPER WORK JPASLEY 11-20-23
23026278500 | EMER - INSTALL 3'-2" PMMP | [5 empty] | 3085.38 | 4078.3783 | -992.9983 |  |  |  | 2023-07-06
23026278600 | EMER - RETIRE 3'-2" PMMP | [5 empty] | 10.24 | 139.1159 | -128.8759 |  |  |  | 2023-07-06
23026279900 | RETIRE 38'-3" PMP | [5 empty] | 0 | 139.1159 | -139.1159 |  |  |  | 2023-06-26
23026281600 | EMER-INSTALL 3'-3" PMMP | [5 empty] | 5032.43 | 5640.4544 | -608.0244 |  |  |  | 2023-07-17
23026281700 | EMER-RETIRE 3'-3" PMAP | [5 empty] | 1946 | 67.1159 | 1878.8841 |  |  |  | 2023-07-17
23026282600 | EMER - RETIRE 216'-2" PAMP | [5 empty] | 5057.99 | 2153.608 | 2904.382 |  |  |  | 2023-07-14
23026286000 | EMER - INSTALL 6'-2" PMMP | [5 empty] | 5456.45 | 14279.5419 | -8823.0919 |  |  |  | 2023-08-21
23026286100 | EMER - RETIRE 6'-2" PMMP | [5 empty] | 5375.26 | 67.1159 | 5308.1441 |  |  |  | 2023-08-21
23026287800 | INSTALL 500'-4" PMMP | [5 empty] | 175667.6 | 99252.0533 | 76415.5467 |  |  |  | 2023-10-23
23026287900 | RETIRE 500'-3" PMP | [5 empty] | 0 | 119.4953 | -119.4953 |  |  |  | 2023-10-23
23026288500 | EMER - INSTALL 3'-2" PMMP | [5 empty] | 33.23 | 15193.894 | -15160.664 |  |  |  | 2023-08-21
23026288600 | EMER - RETIRE 3'-2" PMP | [5 empty] | 4237.6 | 119.4953 | 4118.1047 |  |  |  | 2023-08-21
23026289900 | EMER-INSTALL 8'-3" PMMP | [5 empty] | 3026.88 | 1914.647 | 1112.233 |  |  |  | 2023-09-01
23026290000 | EMER-RETIRE 8'-3" PAMP | [5 empty] | 9034.26 | 7157.6376 | 1876.6224 |  |  |  | 2023-09-01
23026293900 | EMER-INSTALL 3' OF 2"PMMP MAIN | [5 empty] | 7202.89 | 14157.3554 | -6954.4654 |  |  |  | 2023-09-18
23026294000 | EMER-RETIRE 3' OF 2"PMMP MAIN | [5 empty] | 0 | 119.4953 | -119.4953 |  |  |  | 2023-09-18
23026295300 | RETIRE FENCE | [5 empty] | 0 | 119.4953 | -119.4953 |  |  |  | 2023-09-19
23026297000 | INSTALL PCF'S LP | [5 empty] | 2982.68 | 145.9261 | 2836.7539 |  |  |  | 2023-09-14
23026298400 | INSTALL MODEM AND ANTENNA | [5 empty] | 0 | 8303.7376 | -8303.7376 |  |  |  | 2023-11-20 | CORRECTED PAPER WORK 11-20-23 JPASLEY
22026165501 | INSTALL 3385' OF 2" PMMP | [5 empty] | 347952.13 | 345650.6876 | 2301.4424 | 2024-01-01 | 2024-12-31 | 2024-08-15 | 2024-09-13
23026300500 | RETIRE 3896' 4/3/2" PAMP | [5 empty] | 0 | 160.3697 | -160.3697 |  |  |  | #N/A
23026279500 | INSTALL 339'-8" PMLP | [5 empty] | 110539.26 | 126473.6122 | -15934.3522 | 2024-01-01 | 2024-12-31 | 2024-04-29 | 2024-05-10 | INSTALLED 218' OF 8" PLASTIC TESTED 105 PSIG 4 HOURS SOAP TESTED FINAL CONN OP 10" WC
23026300700 | RETIRE 150'-4" PMLP | [5 empty] | 0 | 124.9261 | -124.9261 |  |  |  | #N/A
23026302300 | RETIRE PAPER GAUGE | [5 empty] | 835.24 | 989.8688 | -154.6288 |  |  |  | 2023-11-01 | NOT ONSITE WORK POSTPONED TILL TOMMOROW CCC# 49846
23026302800 | EMER - INSTALL 2'-3" PMP | [5 empty] | 4049.34 | 3855.2637 | 194.0763 |  |  |  | 2023-10-30
23026302900 | EMER - RETIRE 2'-3" PMP | [5 empty] | 1224.64 | 122.9261 | 1101.7139 |  |  |  | 2023-10-30
23026303000 | EMER - RETIRE 13'-3" BSLP | [5 empty] | 19694.3 | 23992.5325 | -4298.2325 |  |  |  | #N/A
23026303200 | R-1647 REBUILD INSTALL | [5 empty] | 123864.29 | 69868.5777 | 53995.7123 |  |  |  | #N/A | BYPASS HOSE PICK UP/OHIO NOT ONSITE NOT ONSITE BUILD AND TEST TEMP STATION CCC# 56331 CCC# 56478 INSTALLING TEMP STATION CCC# 56478 PUT TEMP STATION ONLINE. NOT ONSITE. DOING EXPENSE REPORT FOR PURCHASE FOR JOB. CCC# 56815 MONITOR FOR VAC TRUCK. JMARTIN 12/26/23 CCC# 57050 CCC# 57112 CCC# 57112 CCC# 57112 CCC# 57190
23026303300 | R-1647 PARTIAL RETIRE | [5 empty] | 0 | 124.9261 | -124.9261 |  |  |  | #N/A
24026339800 | INSTALL 35' OF 6"PMLP MAIN | [5 empty] | 43718.9 | 45030.1866 | -1311.2866 | 2024-01-01 | 2024-12-31 | 2024-07-29 | 2024-08-06 | REPLACED 56' OF 060 P LP DUE TO CROSS BORE IN SEWER. TESTED MAIN FOR 1HR AT 90LBS.TEST OK. TESTED TEMP BYPASS FOR 20MINS AT 90LBS.TESTS OK. SOAP TEST BOLTED COUPLINGS AT OP.TEST OK.SOAP TEST CLAPS AND SADDLES AT OP.TEST OK
23026306000 | EMER-INSTALL 2'-3" PMMP | [5 empty] | 6338.35 | 6158.638 | 179.712 |  |  |  | 2023-12-04
23026306100 | EMER-RETIRE 2'-3" PMMP | [5 empty] | 0 | 124.9261 | -124.9261 |  |  |  | 2023-12-04
23026306200 | INSTALL BUILDINGS R-1667 | [5 empty] | 0 | 147.9261 | -147.9261 |  |  |  | 2023-11-28
24026311700 | INSTALL 360' OF 2"PMMP MAIN | [5 empty] | 38311.55 | 32438.7712 | 5872.7788 | 2024-01-01 | 2024-12-31 | 2024-03-01 | 2024-03-04
23026292201 | INSTALL 360'-4" PMMP | [5 empty] | 171750.99 | 171123.5748 | 627.4152 | 2024-01-01 | 2024-12-31 | 2024-04-10 | 2024-04-22
24026310700 | ABANDON ~ 150'- 2" CSIP | [5 empty] | 577.39 | 118.4933 | 458.8967 |  |  |  | #N/A
24026343300 | INSTALL 4" POLY VALVE | [5 empty] | 7689.14 | 18376.2056 | -10687.0656 | 2024-01-01 | 2024-12-31 | 2024-06-03 | 2024-06-06
24026314400 | INSTALL 1,200'-4" PMMP | [5 empty] | 441793.04 | 166742.0112 | 275051.0288 |  |  |  | 2025-04-15 | PAST COMMIT DATE DUE TO WEATHER AND ROUGH DIFFULCT OF JOB AND BORE
24026315200 | INSTALL NEW EC 350 | [5 empty] | 8919.7 | 5524.5572 | 3395.1428 |  |  |  | #N/A | INSTALLED NEW EC350
24026315300 | RETIRE EC350 | [5 empty] | 273.05 | 160.3697 | 112.6803 |  |  |  | #N/A | RETIRED MINI AT
24026349300 | INSTALL 4"POLY VALVE KY-C1556 | [5 empty] | 22343.49 | 32958.9947 | -10615.5047 | 2024-01-01 | 2024-12-31 | 2024-09-30 | 2024-10-02
24026316100 | EMER - RETIRE 2'-3" PALP | [5 empty] | 0 | 160.3697 | -160.3697 |  |  |  | #N/A
24026319000 | ADD SOLAR BACKUP | [5 empty] | 6634.21 | 15005.0106 | -8370.8006 |  |  |  | #N/A
24026320400 | INSTALL MIWI W/FLOW SWITCH | [5 empty] | 17939.6 | 21508.3856 | -3568.7856 |  |  |  | #N/A | CCC# 93710 CCC# 94300 INSTALLED NEW TAPS FOR MIWI
24026325000 | MIWI WITH SOLAR | [5 empty] | 17266.04 | 19446.0487 | -2180.0087 |  |  |  | #N/A | CCC# 88776 INSTALL NEW TAPS FOR MIWI.
24026325100 | MIWI WITH SOLAR | [5 empty] | 0 | 121.4465 | -121.4465 |  |  |  | #N/A
24026326000 | UPGRADE SCADA SYSTEM | [5 empty] | 9009.11 | 10627.0487 | -1617.9387 |  |  |  | #N/A | CCC 92291 CCC 92291
24026326100 | UPGRADE SCADA SYSTEM | [5 empty] | 494.05 | 121.4465 | 372.6035 |  |  |  | #N/A | CCC 92291
24026327000 | INSTALL ELECTRONICS | [5 empty] | 8645.98 | 15644.0403 | -6998.0603 |  |  |  | #N/A | CCC# 84533
24026327100 | RETIRE ELECTRONICS | [5 empty] | 0 | 118.4933 | -118.4933 |  |  |  | #N/A
24026327200 | INSTALL ELECTRIONICS | [5 empty] | 7576.45 | 15644.0403 | -8067.5903 |  |  |  | #N/A | CCC# 84650
24026327300 | RETIRE ELECTRONICS | [5 empty] | 0 | 118.4933 | -118.4933 |  |  |  | #N/A
24026327800 | INSTALL ELECTRONICS | [5 empty] | 9991.66 | 15644.0403 | -5652.3803 |  |  |  | #N/A | CCC# 84481
24026327900 | RETIRE ELECTRONICS | [5 empty] | 9.73 | 118.4933 | -108.7633 |  |  |  | #N/A | CCC# 84481
22026237801 | INSTALL 4,100'-2" PMMP | [5 empty] | 836183.38 | 765451.6207 | 70731.7593 | 2024-01-01 | 2024-12-31 | 2024-01-01 | 2024-02-27
24026329500 | EMER - RETIRE 2'-3" PALP | [5 empty] | 0 | 121.4465 | -121.4465 |  |  |  | #N/A
24026341900 | INSTALL 4250' OF 2"/4"PMMP | [5 empty] | 160153.35 | 152744.147 | 7409.203 | 2024-01-01 | 2024-12-31 | 2024-07-01 | 2024-09-06
24026329800 | EMER - RETIRE 2'-2" PMP | [5 empty] | 0 | 121.4465 | -121.4465 |  |  |  | #N/A
24026331400 | RETIRE R-1279 | [5 empty] | 1587.88 | 973.0487 | 614.8313 |  |  |  | #N/A | CCC 63860 RETIRED STATION R-1279
24026331601 | INSTALL 475' OF 2"PMMP MAIN | [5 empty] | 142820.44 | 110575.0083 | 32245.4317 | 2024-01-01 | 2024-12-31 | 2024-07-08 | 2024-07-22
24026332700 | EMER - RETIRE 15'- PMMP | [5 empty] | 0 | 139.7787 | -139.7787 |  |  |  | #N/A
22026183001 | INSTALL 4955'-2" PMMP | [5 empty] | 124010.5 | 134870.3496 | -10859.8496 | 2024-01-01 | 2024-12-31 | 2024-01-01 | 2024-05-24
24026335200 | EMER - 4' - 3" PMMP | [5 empty] | 0 | 121.4465 | -121.4465 |  |  |  | #N/A
24026334000 | INSTALL 5' OF 2" PMMP | [5 empty] | 11358.98 | 3841.146 | 7517.834 | 2024-01-01 | 2024-12-31 | 2024-04-01 | 2024-04-02 | FOUND COMPRESSION COUPLINGS LEAKING - SQEEZED OFFF MAIN WITH GAGE FOR PRESSURE VERIFICATION - PRESSURE REMAINED @ 53 - SOAP TEST LAST CONNECTIONS @ OP FOR 5 MIN TEST GOOD
24026335500 | EMER - RETIRE - 2'-2" PMMP | [5 empty] | 0 | 121.4465 | -121.4465 |  |  |  | #N/A
22026164000 | INSTALL 5,100'-2" PMMP | [5 empty] | 1341919.13 | 1140024.6985 | 201894.4315 | 2024-01-01 | 2024-12-31 | 2024-01-01 | 2024-04-10
24026337700 | RETIRE 20'-2" PMMP | [5 empty] | 19.74 | 139.7787 | -120.0387 |  |  |  | #N/A
22026172301 | INSTALL 5000' OF 2"PMMP MAIN | [5 empty] | 1225170.53 | 1183513.1452 | 41657.3848 | 2024-01-01 | 2024-12-31 | 2024-01-01 | 2024-04-26
24026342300 | EMER - RETIRE 267'-2" PMP | [5 empty] | 2861.12 | 2962.6295 | -101.5095 |  |  |  | #N/A
21026152101 | INSTALL 535' OF 8"CSHP MAIN | [5 empty] | 480960.85 | 444968.002 | 35992.848 | 2024-01-01 | 2024-12-31 | 2024-10-01 | 2024-10-31
24026343800 | EMER - RETIRE 3'-3" PMP | [5 empty] | 0 | 139.7787 | -139.7787 |  |  |  | #N/A
24026345000 | INSTALL NEW EC 350 UNIT | [5 empty] | 548.93 | 2029.8027 | -1480.8727 |  |  |  | #N/A | INSTALLED NEW EC350 S/N 232590014 0-300#PSIA
24026345100 | RETIRE EC 350 UNIT | [5 empty] | 123.53 | 70.7787 | 52.7513 |  |  |  | #N/A | RETIRED OLD EC350 INSTALLED NEW EC350
23026270600 | INSTALL 550' OF 2" PMMP | [5 empty] | 43345.7 | 42706.9586 | 638.7414 | 2024-01-01 | 2024-12-31 | 2024-09-14 | 2024-09-26
24026350000 | EMER - RETIRE 3'-2" PMP | [5 empty] | 0 | 139.7787 | -139.7787 |  |  |  | #N/A
24026350900 | RETIRE 38'-2" CSMP | [5 empty] | 0 | 139.7787 | -139.7787 |  |  |  | #N/A
24026352000 | INSTALL 700'-2" PMMP | [5 empty] | 75786.62 | 78413.3497 | -2626.7297 |  |  |  | 2025-02-10
23026288401 | INSTALL 5500' OF 4"PMMP MAIN | [5 empty] | 294615.62 | 319863.8272 | -25248.2072 | 2024-01-01 | 2024-12-31 | 2024-06-23 | 2024-08-01
24026353300 | EMER - RETIRE 3'-4" PAMP | [5 empty] | 0 | 139.7787 | -139.7787 |  |  |  | #N/A
24026354100 | EMER - RETIRE 308'-2" PLP | [5 empty] | 3269.44 | 2331.6111 | 937.8289 |  |  |  | #N/A
23026283801 | INSTALL 5705'-2"/4" PMMP | [5 empty] | 388707.97 | 361218.8401 | 27489.1299 | 2024-01-01 | 2024-12-31 | 2024-01-01 | 2024-04-11
24026359000 | EMER - INSTALL NEW REGULATOR | [5 empty] | 32098.29 | 163089.7838 | -130991.4938 |  |  |  | #N/A
24026359100 | EMER - RETIRE REGULATOR | [5 empty] | 3027.28 | 124.2298 | 2903.0502 |  |  |  | #N/A
22026238401 | INSTALL 5765'-2" PMMP | [5 empty] | 1422160.57 | 1269865.7251 | 152294.8449 | 2024-01-01 | 2024-12-31 | 2024-09-16 | 2024-12-03
24026361600 | EMER - RETIRE 2'-3" PALP | [5 empty] | 0 | 127.2637 | -127.2637 |  |  |  | #N/A
24026338500 | INSTALL 585' OF 2"PMMP MAIN | [5 empty] | 30882.37 | 37261.72 | -6379.35 | 2024-01-01 | 2024-12-31 | 2024-04-15 | 2024-05-03
24026364900 | INSTALL 2,300'-4" PMMP | [5 empty] | 215200.02 | 164697.53 | 50502.49 |  |  |  | 2025-03-24
24026365600 | INSTALL SSD UNIT W/ZINC RIBBON | [5 empty] | 95863.74 | 55300.1794 | 40563.5606 |  |  |  | #N/A | INSTALLED DUAL RUNS OF 420' ZINC ON THE NORTH & SOUTH SIDE OF 12"CSHP MAIN 5' OFF FROM MAIN & BELOW THE PIPE / INSTALLED DAIRYLAND SOLID-STATE DECOUPLER (SSD-2/2-5.0-100R) SERIAL #64954 WITH ENCLOSURE / ZINC MAT INSTALLED WITH #6 WHITE WIRE AND GREEN TAPE / TS FAC 885476 INSTALLED ON THE EAST END OF PROJECT & TS FAC 885477 INSTALLED ON THE WEST END OF PROJECT WITH #6 WHITE WIRE RUN UP FROM ZINC
23026273700 | INSTALL 6' OF 2"PMMP MAIN | [5 empty] | 5850.76 | 15141.0552 | -9290.2952 | 2024-01-01 | 2024-12-31 | 2024-07-10 | 2024-07-12 | LEAKING CV ON STEM.REMOVED CV AND INSTALLED 3' OF 020PMP.TESTED PURGE TEE AND 3FT OF MAIN FOR 1HR AT 90LBS.TEST OK.SOAP TEST EFC'S AT OP FOR 5MINS AT OP.TEST OK. BHB NGF. REMOVED CV C9-113.
24026368100 | EMER - RETIRE 5'-2" PMMP | [5 empty] | 295.06 | 137.4585 | 157.6015 |  |  |  | #N/A | WORKED ORDER
20026983300 | INSTALL 6,600'-2"/4" PMMP | [5 empty] | 2015230.05 | 1529743.322 | 485486.728 | 2024-01-01 | 2024-12-31 | 2024-09-09 | 2024-12-19
24026371900 | EMER - RETIRE 3'-2" PMP | [5 empty] | 0 | 111.0024 | -111.0024 |  |  |  | #N/A
24026373200 | INSTALL SOLAR BACKUP UNIT | [5 empty] | 7104.24 | 9877.4639 | -2773.2239 |  |  |  | #N/A | CCC# 108028
24026373700 | INSTALL SOLAR BACKUP UNIT | [5 empty] | 8114.69 | 9877.4639 | -1762.7739 |  |  |  | #N/A | CCC 107505 CCC#107505 WORK IS COMPLETE ON 2-18-2025 1550 J HOBBS
23026267200 | INSTALL 60'-4" PMLP | [5 empty] | 34888.84 | 41669.6267 | -6780.7867 | 2024-01-01 | 2024-12-31 | 2024-03-22 | 2024-03-28
24026373900 | EMER - RETIRE 3'-2" PAMP | [5 empty] | 0 | 111.0024 | -111.0024 |  |  |  | #N/A
24026376300 | EMER - INSTALL 5'-2" PMIP | [5 empty] | 6514.7 | 6864.5633 | -349.8633 |  |  |  | 2025-01-24
24026376400 | EMER - RETIRE 5'-2" PAIP | [5 empty] | 0 | 111.0024 | -111.0024 |  |  |  | #N/A
24026363600 | INSTALL 620' OF 4"PMMP MAIN | [5 empty] | 275193.6 | 142827.5782 | 132366.0218 | 2024-01-01 | 2024-12-31 | 2024-11-04 | 2024-11-19 | TWALKER/KY 11-19-24: WMS WOULD NOT ALLOW JOB ORDER TO BE REVISED DUE TO UNPAID INVOICES. JOB WILL OVER RUN.
25026378800 | EMER - INSTALL 25'-2" PMMP | [5 empty] | 81247.31 | 46887.3793 | 34359.9307 |  |  |  | 2025-01-24
25026378900 | EMER - RETIRE 25'-3" PAMP | [5 empty] | 0 | 111.0024 | -111.0024 |  |  |  | #N/A
25026379000 | EMER - INSTALL 9'-2" PMMP | [5 empty] | 1184.26 | 11723.1799 | -10538.9199 |  |  |  | 2025-01-28
25026379101 | EMER - RETIRE 9'-2" PMP | [5 empty] | 9245.89 | 6663.1804 | 2582.7096 |  |  |  | #N/A
25026379500 | INSTALL SCADA VISIBILITY | [5 empty] | 13338.87 | 16667 | -3328.13 |  |  |  | #N/A | NOT ONSITE ORDER NOT NEEDED CCC# 119324 NOT ONSITE WENT ENROUTE TO THE WRONG JOB CCC# 121903 INSTALL POLES, BATTERY BOX, AND ER350.
25026379700 | INSTALL SCADA VISIBILITY | [5 empty] | 11378.96 | 16667 | -5288.04 |  |  |  | #N/A | CCC 109193 INSTALLED 1'' TEE AND 1/4'' BALL VALVE FOR FUTURE SCADA VISIBILITY CCC 123850 CCC#123850
25026381800 | INSTALL 250'-2" PMMP | [5 empty] | 52355.75 | 32185.6133 | 20170.1367 |  |  |  | 2025-03-28
25026393800 | INSTALL 2,100'-2" PMMP | [5 empty] | 110997.26 | 177755.4678 | -66758.2078 |  |  |  | 2025-05-20
25026400200 | INSTALL 550'-2" PMMP | [5 empty] | 47508 | 57765.7205 | -10257.7205 |  |  |  | 2025-04-25
25026400700 | RETIRE 100'-4" PMMP | [5 empty] | 2247.29 | 5393.6654 | -3146.3754 |  |  |  | #N/A | ABANDONED 135' OF 4" PLASTIC TO ALLOW FOR DRIVEWAY ENTRANCE, STUB LEFT FOR FUTURE SERVICE TO PROPERTY- PAPERWORK CO OFF SITE
25026403000 | EMER - INSTALL 2'-3" PMMP | [5 empty] | 230.88 | 13653.342 | -13422.462 |  |  |  | 2025-03-27
25026403100 | EMER - RETIRE 2'-3" PAMP | [5 empty] | 15086.34 | 138.8251 | 14947.5149 |  |  |  | #N/A | ABANDONED SECTION OF LEAKING CRACKED PLASTIC PIPE AND REPLACED WITH NEW PIP E
16026666400 | INSTALL NEW CWT HEATER | [5 empty] | 188315.11 | 231341.3745 | -43026.2645 |  |  |  | 2022-12-16 | CC# 53363. DRAINED WATERBATH HEATER. 01-26-22 DSASH CCC 55246 CCC 55359 CCC 55691 CCC 56098 CCC 57419 NO TICKET NEEDED NO TICKET NEEDED NO TICKET NEEDED CC# 70901. 6/20/22 DSASH RETIRED OLD WATER BATH INSTALLED NEW CWT HEATER DASH 3-3-22
16026666500 | RETIRE EXIST WB HEATER | [5 empty] | 29153.65 | 140.0254 | 29013.6246 |  |  |  | 2022-03-03 | CCC # 53363 CCC 53705 CCC 54571 CCC # 54571 NO TICKET NEEDED CCC # 57419 NOT ON SITE NO CCC NEEDED NO CCC NOT ON SITE CHARGED TO LE TO GET VRG FOR REG REPLACE INSTALLED NEW CWT HEATER 3-3-22 DASH
17026698500 | INSTALL VRG PRESS CONT EQUIPMT | [5 empty] | 247791.39 | 128512.8191 | 119278.5709 |  |  |  | 2021-08-17 | CC# 27659. 6/11/21 DSASH CCC #27659 CC# 27769. 6/14/21 DSASH CC# 27972. 6/16/21 DSASH CC# 28248. 6/17/21 DSASH CCC #28248 CCC #28445 CC# 28445. 6/18/21 DSASH CC# 28787. 6/23/21 DSASH CCC #28787 NOT AT STATION OFF SITE WORKING ON PAPERWORK FOR JOB 7/1/2021 GCCC TICKET NOT REQUIRED NOT AT STATION OFF SITE COMPLETING PAPERWORK 7/19/21 AND 8/17/21 CFARIS
17026698600 | RETIRE EXIST PRESS CONT EQUIPM | [5 empty] | 299.36 | 131.3267 | 168.0333 |  |  |  | 2021-08-17
17026699800 | INSTALL ELEVATED BUS STOP ASSM | [5 empty] | 9561.04 | 61743.3758 | -52182.3358 |  |  |  | 2021-08-17 | UNDERRUN EXPLANATION: THIS JOB ORDER WAS WORKED IN ONJUNCTION WITH ANOTHER JOB ORDER, 17-0269850-00, WHICH OVERRAN DUE TO THE CONTRACT LABOR BEING CHA RGED TO THAT JOB ORDER INSTEAD. THAT AMOUNT WAS APPROXIMATELY $40,000.
17026699900 | INSTALL NEW CH LINK FENCING | [5 empty] | 0 | 20572.3069 | -20572.3069 |  |  |  | 2021-08-17
17026735700 | RETIRE 3510' MAIN - D243673 | [5 empty] | 8338.24 | 78.7024 | 8259.5376 |  |  |  | 2021-03-30
18026752700 | INSTALL VRG PILOT | [5 empty] | 5363.35 | 5404.3267 | -40.9767 |  |  |  | 2021-08-17 | CCC #27769 CCC #28734
18026752800 | RETIRE | [5 empty] | 838.05 | 52.1634 | 785.8866 |  |  |  | 2021-08-17
18026762800 | INSTALL NEW CHAIN LINK FENCE | [5 empty] | 16843.44 | 17042.1322 | -198.6922 |  |  |  | 2022-08-18 | MONITORED NEW CHAINLINK FENCE INSTALL AMCCORMICK 8-18-22
18026762900 | REPLACE CHAIN LINK FENCE | [5 empty] | 429.99 | 73.5943 | 356.3957 |  |  |  | 2022-08-18 | MONITORED FENCE REMOVAL AND INSTALL AMCCORMICK 8-18-22
18026764800 | INSTALL COMM BUILDING | [5 empty] | 132078.26 | 156664.9991 | -24586.7391 |  |  |  | 2022-06-30 | 72003 INSTALLED RTU BUILDING AND TRANSDUCERS
18026772300 | CONVERT FROM GMB TO CAB ACCT | [5 empty] | 725.53 | 2583.054 | -1857.524 |  |  |  | 2022-09-26 | CONVERTED GMB TO CAB ACCOUNT INSTALLED NEW 800 METER ON 5# FPCC DASH 9-26-2 2
18026778900 | INSTALL ERX & RTU BUILDING | [5 empty] | 113154.12 | 156098.7133 | -42944.5933 |  |  |  | 2021-12-16 | CC# 13231. 2/25/21 DSASH WORKED ON PAPERWORK OFF SITE. 2/26/21 DSASH EQUIPMENT INSTALLED ON 2/25/21 BY ACP AND DANNY ASH PAPERWORK COMPLETED ON 12/16/2021 BY CYNTHIA FARIS JOB CLOSEOUT DELAYED WAITING ON INFORMATION AND CORRECT ISO SKETCH UNDERRUN EXPLANATION: THE CONTRACT COSTS WERE SIGNIFICANT LESS THAT THE I&C TEAM HAD ORIGINALLY ESTIMATED.
18026781701 | INSTALL MONITOR/CONTROL REGS | [5 empty] | 141447.12 | 99301.7623 | 42145.3577 |  |  |  | 2021-06-22 | CCC TICKET 27187 CCC #27342 CCC #27472 CCC #27636 CCC #27973 CCC TICKET NOT REQUIRED NOT AT STATION 8/4/21
18026781800 | ABANDON REGULATORS | [5 empty] | 0 | 56.3894 | -56.3894 |  |  |  | 2021-06-22
18026793901 | INSTALL 4,123' - 2" PMMP | [5 empty] | 649583.26 | 506341.5777 | 143241.6823 |  |  |  | 2023-12-07
18026794000 | RETIRE 4748'-2"/3"/4"/6"P-BSLP | [5 empty] | 110 | 61.2976 | 48.7024 |  |  |  | 2023-12-07
18026794401 | INSTALL 4400'-2"/4"PMMP MAIN | [5 empty] | 1250897.35 | 1022806.1278 | 228091.2222 |  |  |  | 2025-05-27
18026794500 | RETIRE 2450' - CS/BSMP | [5 empty] | 589.7 | 118.4933 | 471.2067 |  |  |  | #N/A
19026855301 | INSTALL RTU AND BUILDING | [5 empty] | 186001.86 | 182784.6097 | 3217.2503 |  |  |  | 2022-03-17 | INSTALLED NEW RTU DASH 3-17-22
19026855400 | RETIRE OLD RTU EQUIPMENT | [5 empty] | 5219.78 | 69.4128 | 5150.3672 |  |  |  | 2022-03-17 | INSTALLED NEW COMM BUILDING AND RTU DASH 3-17-22
19026860400 | INSTALLING I&C EQUIPMENT | [5 empty] | 174669.84 | 222748.2628 | -48078.4228 |  |  |  | 2022-08-22 | CCC #27973 CCC #28142 CCC # 28275 CCC #28378 CCC #28665 CCC TICKET NOT REQUIRED NOT AT STATION 8/4/21
19026860500 | RETIRE I&C EQUIPMENT | [5 empty] | 511.34 | 84.9756 | 426.3644 |  |  |  | 2022-08-22 | CC# 78206
19026867100 | INSTALL VRG CONTROLLER | [5 empty] | 15917.94 | 15490.7518 | 427.1882 |  |  |  | 2022-03-29 | CCC 59916 CCC # 59916 INSTALLED NEW VRG CONTROLLERS DASH 3-29-22
19026867200 | RETIRE CURRENT CONTROLLERS | [5 empty] | 1038.8 | 64.4897 | 974.3103 |  |  |  | 2022-03-29 | CCC # INSTALLED NEW VRG'S RETIRED EXSISTING CONTROLLERS DASH 3-29-22
19026889700 | INSTALL METER AND SETTING | [5 empty] | 54709.93 | 55012.1889 | -302.2589 |  |  |  | 2022-05-11 | CCC #30162 CCC # 42745 CCC # 42908 CCC # 43108 CLENANER INSTALLED ON 10-29-2022 ALONG WITH PAPERWORK CO BY JOSH MULLINS ON 5-10-22
19026889800 | RETIRE METER AND SETTING | [5 empty] | 612.86 | 76.3408 | 536.5192 |  |  |  | 2022-05-11
23026254900 | INSTALL 620' OF 8"CSHP MAIN | [5 empty] | 230200.58 | 398676.678 | -168476.098 | 2024-01-01 | 2024-12-31 | 2024-06-01 | 2024-07-19 | TWALKER/KY 01-20-25: LEVEL 1 VARIANCE ADDED TO WMS.DOCS: JOB UNDER RUN DUE TO THE UNIVERSITY OF KENTUCKY TAKING OWNERSHIP OF ALL THE STREETS IN PROJECT AREA - CKY DID NOT HAVE TO RESTORE/REPLACE ANY STREETS OR HARD SURFACE REPAIRS WHICH LOWERED CONTRACT COST BY $53,000, ALSO PROJECT WAS COMPLETED FASTER THAN ESTIMATE BECAUSE OF THE LACK OF STREET REPAIRS WHICH LOWERED LABOR COST BY $11,000. CKY WAS ABLE TO USED 8" STEEL PIPE LEFT OVER FROM LEESTOWN ROAD WIDENING PROJECT THAT SAVED $50,000 AND SEGA WAS $12,000 LOWER THAN ESTIMATE. FINALLY, THIS WAS A CUSTOMER PAID RELOCATION 100% REIMBURSEMENT PROJECT AND CUSTOMER WAS REFUNDED OVER PAYMENT IN 2024
19026913100 | RETIRE 705'-2/3/4" BS/PL/CSLP | [5 empty] | 354.92 | 239.7645 | 115.1555 |  |  |  | #N/A
20026918001 | INSTALL ELECTRONICS | [5 empty] | 203885.41 | 78849.9064 | 125035.5036 |  |  |  | 2021-08-17 | CC# 31091 CC# 34924 CC# 21685. 01-03-22 DSASH CC# 21685. 01-03-22 DSASH OVERRUN EXPLANATION: ASSUMED WE WOULD USE THE OLD BLOCK BUILDING BUT FOND T HAT IT WAS LEAKING SO HAD TO REPLACE WITH A NEW BUILDING.
20026918102 | INSTALL ELECTRONICS | [5 empty] | 173384.28 | 264607.6595 | -91223.3795 |  |  |  | 2021-11-01 | NO CC NEEDED ONSITE MEETING DID NOT GO INSIDE BUILDING GES: UNDERRUN EXPLANATION: JOB UNDERRAN BECAUSE SCADA BUILDING WAS PLACED O N ANOTHER JOB ORDER THAT IS PLANNED FOR 2022 CONSTRUCTION. ADDITIONALLY, ASSUMED THERE WAS PRESSURE CONTROL WHEN ESTIMATED AND THERE W AS NOT.
20026922500 | INSTALL ELECTRONICS | [5 empty] | 238947.63 | 123804 | 115143.63 |  |  |  | 2022-11-02 | CCC # 40652 NOT ON SITE CC# 47218. 12/01/21 DSASH CCC # 47218 CCC # 47356 CC# 47727. 12/07/21 DSASH
20026922600 | RETIRE ELECTRONICS | [5 empty] | 144.18 | 115.4611 | 28.7189 |  |  |  | 2022-11-02
20026930800 | UPGRADE ELECTRONICS | [5 empty] | 4644.07 | 3038 | 1606.07 |  |  |  | 2021-07-06 | REPLACED EFC NON SCADA MONITORED GMB ACCOUNT GCCC TICKET NOT REQUIRED
20026930900 | UPGRADE ELECTRONICS | [5 empty] | 3329.3 | 3038 | 291.3 |  |  |  | 2022-09-19 | RETIRED MINI AT INSTALLED NEW EC350 ON CELL MODEM DASH 9-19-22
20026936301 | INSTALL 1192'-4" PMMP | [5 empty] | 290217.29 | 375696.2322 | -85478.9422 |  |  |  | 2021-04-06 | UNDERRUN EXPLANATION: SIGNIFICANTLY LESS HARD SURFACE REPAIRS AND BACKFILL REQUIRED THAN ESTIMATED. ALSO NOFLAGGING ON OVERTIME WAS REQUIRED. THE OVER HEAD EFFECT OF THESE REDUCTIONS ALSO CONTRIBUTED TO THE UNDERRUN.
20026936400 | RETIRE 1228'-3"&4"BS/CS/P-LP | [5 empty] | 1214.98 | 400.0304 | 814.9496 |  |  |  | 2021-04-06
20026936600 | ABANDON ~10'-4" P-LP | [5 empty] | 167.31 | 173.6495 | -6.3395 |  |  |  | 2021-01-13
20026941600 | INSTALL I&C EQUIPMENT | [5 empty] | 11237.56 | 16155.4774 | -4917.9174 |  |  |  | 2021-12-10 | CC# 30132. ERX INSTALLED BY DANNY ASH AND JOSH MULLINS PAPERWORK COMPLETED BY CYNTHIA FARIS PAPERWORK ON HOLD AWAITING CORRECT ISO SKETCH
20026941700 | RETIRE GAUGE | [5 empty] | 0 | 91.4991 | -91.4991 |  |  |  | 2021-12-10 | ERX INSTALLED AND PAPER RECORDING GAUGE RETIRED BY DANNY ASH AND JOSH MULLINS PAPERWORK COMPLETED BY CYNTHIA FARIS PAPERWORK ON HOLD AWAITING CORRECT ISO SKETCH
20026941800 | INSTALL I&C EQUIPMENT | [5 empty] | 12411.86 | 16155.4774 | -3743.6174 |  |  |  | 2021-07-16 | GCC 13064 EQUIPMENT INSTALLED BY JOSH MULLINS ON 2/24/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/16/21 DELAY IN JOB COMPLETION WAITING ON PE APPROVAL FOR 584 JOB ORDER AND ISO SKETCH UPDATE GCCC TICKET NOT REQUIRED ON 7/16/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026941900 | RETIRE GAUGE | [5 empty] | 0 | 91.4991 | -91.4991 |  |  |  | 2021-07-16 | GAUGE RETIRE BY JOSH MULLINS ON 2/24/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/16/21 DELAY COMPLETING JOB ORDER DUE TO ISO SKETCH REVISION& PE APPROVAL GCCC TICKET NOT REQUIRED ON 7/16/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026942100 | INSTALL I&C EQUIPMENT | [5 empty] | 16401.86 | 16155.4774 | 246.3826 |  |  |  | 2021-07-12 | CCC #29962 CCC #30339 INSTALLED ERX, RV50 MODEM, BATTERY AND SUPER SOLAR KIT GCCC TICKET NOT REQUIRED ON 7/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026942200 | RETIRE GAUGE | [5 empty] | 0 | 91.4991 | -91.4991 |  |  |  | 2021-07-12 | RETIRED PAPER RECORDING GAUGE AND INSTALLED ERX WORK COMPLETED ON 909 JOB ORDER WITH GCCC TICKET NUMBER 29962 GCCC TICKET NOT REQUIRED ON 7/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026942300 | INSTALL I&C EQUIPMENT | [5 empty] | 11644.22 | 16155.4774 | -4511.2574 |  |  |  | 2021-12-17 | INSTALLED ERX DELAY IN SENDING JOB TO CLOSE OUT WAITING ON INFORMATION PE REVIEW/APPROVAL AND ISO SKETCH CFARIS
20026942400 | RETIRE GAUGE | [5 empty] | 1032.4 | 91.4991 | 940.9009 |  |  |  | 2021-12-17 | REPLACED MECHANICAL RECORDING GAUGE WITH ERX DELAY IN SENDING TO CLOSEOUT DUE TO WAITING ON INFORMATION, PE REVIEW/APPROVAL AND CORRECT ISO SKETCH CFARIS
20026942700 | INSTALL I&C EQUIPMENT | [5 empty] | 15613 | 16155.4774 | -542.4774 |  |  |  | 2021-12-10 | CCC # 28876 CC#29408. 6/28/21 DSASH CCC # 32222 INITIAL COMMISSIONING BY SHANE GIORDANO PAPERWORK COMPLETED BY CYNTHIA FARIS ON 12/10/21 PAPERWORK ON HOLD AWAITING ISO SKETCH
20026942800 | RETIRE GAUGE | [5 empty] | 0 | 91.4991 | -91.4991 |  |  |  | 2021-12-10 | PAPERWORK COMPLETION ON HOLD AWAITING ISO SKETCH
20026952500 | REPLACE VALVE C-16 | [5 empty] | 47582.37 | 56236.611 | -8654.241 |  |  |  | 2023-02-07
20026952600 | RETIRE VALVE C-16 | [5 empty] | 5789.59 | 952.0929 | 4837.4971 |  |  |  | 2023-02-07
20026967900 | INSTALL 315' 2" PMIP | [5 empty] | 71403.61 | 31888.6353 | 39514.9747 |  |  |  | 2021-01-29 | TWALKER/KY 02-23-21: ISSUED BACK ORDER CANCEL #48444 FOR JOB OVERRUN EXPLANATION: 150 SQUARE FEET OF 6&2 WAS ESTIMATED AND 990 SQ FEET W AS REQUIRED LEADING TO AN INCREASE IN CONTRACTOR COSTS AND OVERHEADS.
20026970100 | INSTALL 11400'-2"/4" PM/CSIP | [5 empty] | 1042042.95 | 1176644.8813 | -134601.9313 |  |  |  | 2021-11-12
20026970200 | RETIRE 10250'-2"/3"/4" BS/CSIP | [5 empty] | 272.31 | 278.4699 | -6.1599 |  |  |  | 2021-11-12
20026977301 | INSTALL 12,100 OF 2"PMMP MAIN | [5 empty] | 1937357.64 | 1697987.4343 | 239370.2057 |  |  |  | 2021-11-01
20026977400 | RETIRE 10,510'OF 4"/6"BSLP | [5 empty] | 1237.75 | 90.4074 | 1147.3426 |  |  |  | 2021-11-01
20026977500 | INSTALL 4335'-4" & 6" PMLP | [5 empty] | 1014309.73 | 818557.1832 | 195752.5468 |  |  |  | 2022-09-06 | TWALKER/KY 01-24-23: PROJECT OVER RUN COST DUE TO ADDITIONAL PAVING/HARD SURFACE REPAIR RESULTED IN $100,000 HIGHER CONTRACT COST, MATERIAL COST WERE $46,000 HIGHER THAN EST. ADN SEGA $68,000 HIGHER THAN EST.
20026977600 | RETIRE 4766'-2"/3"/4"/6" BSLP | [5 empty] | 11052.89 | 476.2758 | 10576.6142 |  |  |  | 2022-09-06
20026978100 | INSTALL 8620'- 2" PMMP | [5 empty] | 2117372.66 | 1435185.1923 | 682187.4677 |  |  |  | 2023-11-27
20026978200 | RETIRE 8983' LP - 2520' BS | [5 empty] | 513.02 | 476.2758 | 36.7442 |  |  |  | 2023-11-27
20026982200 | INSTALL 5'-4"PMMP & 4'-4"CS | [5 empty] | 40958.2 | 42642.7946 | -1684.5946 |  |  |  | 2021-06-08
20026982300 | ABANDON 5' - 4" CSMP | [5 empty] | 10.78 | 183.2963 | -172.5163 |  |  |  | 2021-06-08
20026982500 | INSTALL 120' - 4" PMLP | [5 empty] | 38925.35 | 30468.341 | 8457.009 |  |  |  | 2021-03-26
24026338000 | INSTALL 65'-2"&4" PMMP | [5 empty] | 59541.79 | 74853.6852 | -15311.8952 | 2024-01-01 | 2024-12-31 | 2024-05-24 | 2024-05-30
20026983400 | RETIRE 5374'-4" BSLP/CSLP | [5 empty] | 92.88 | 119.4953 | -26.6153 |  |  |  | #N/A
20026983500 | INSTALL 1670' - 2" PMMP | [5 empty] | 426217.2 | 347784.1168 | 78433.0832 |  |  |  | 2023-08-28
20026983600 | ABANDON 1667'-2/3/4" PMLP/BSLP | [5 empty] | 290.24 | 360.3823 | -70.1423 |  |  |  | 2023-08-28
20026984500 | REPLACE IP OUTLET BLOCK VALVE | [5 empty] | 1480.71 | 2174.0477 | -693.3377 |  |  |  | 2022-05-25 | NOT ON SITE REPLACED INLET AND OUTLET IP RUN BLOCK VALVES SGIORDANO JMULLINS CO PAPERWORK 06132022
20026984600 | REPLACE IP OUTLET BLOCK VALVE | [5 empty] | 2409.31 | 50 | 2359.31 |  |  |  | 2022-05-25 | CCC 68181 REPLACED INLET AND OUTLET IP BLOCK VALVS SGIORDANO JMULLINS CO PAPERWORK 06132022
20026988800 | INSTALL 210'-2" PMLP | [5 empty] | 21827.5 | 42176.37 | -20348.87 |  |  |  | 2021-03-10
20026992200 | INSTALL 100'-2" PMIP | [5 empty] | 8539.31 | 11276.4442 | -2737.1342 |  |  |  | 2021-03-15
21026104900 | EMER INSTALL 5'-3" PMIP | [5 empty] | 4758.29 | 5995.5434 | -1237.2534 |  |  |  | 2021-03-25 | SEE PAPER PACKET FOR INFO
21026105000 | EMER RETIRE 5'-3" P-IP | [5 empty] | 3758.23 | 750.8346 | 3007.3954 |  |  |  | 2021-03-25 | SEE PAPER COPIES FOR TEST INFO SEE PAPER COPIES/ PIPE EXPOSURE FORM WILL NOT ACCEPT THE CORRECT MAIN NUMBER NOT LETTING ME COMPLETE THIS ORDER
21026105700 | EMER INST 360'-2" PMIP D244304 | [5 empty] | 109722.07 | 25736.2708 | 83985.7992 |  |  |  | 2021-03-09 | INSTALLED 345' OF 2" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7.5 P SIG OVERRUN EXPLANATION: THE SIGNIFICANT COST DIFFERENCE RESULTED FROM PAVING REQUIREMENTS. THE PROJECT WAS NOT ESTIMATED FOR CONTRACT RESTORATION. PAVE TICKETS WERE SUBMITTED TO REPAIR ROAD AND PARKING LOT AREA
21026105800 | EMER RETIRE 350'-3"/2" CSIP | [5 empty] | 27035.38 | 1114.7918 | 25920.5882 |  |  |  | 2021-03-09 | FOUND CRACKED MAIN RETIRED 345' OF 3" ST AND INSTALLED 345' OF NEW 2" PL TO STOP LEAKAGE TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7.5 PSIG
21026106400 | RETIRE PAPER RECORD GAUGE | [5 empty] | 92.38 | 341.3226 | -248.9426 |  |  |  | 2021-12-17 | TICKET 13749
21026109000 | EMER - INSTALL 10'-4" PMIP | [5 empty] | 2349.57 | 8970.0544 | -6620.4844 |  |  |  | 2021-03-18 | INSTALLED 5' OF NEW 4" PL MAIN TO REPAIR CRACKED PIPE TESTED 90 PSIG 1 HR
21026109100 | EMER - RETIRE 10'-4" CSIP | [5 empty] | 5925.07 | 556.9397 | 5368.1303 |  |  |  | 2021-03-18 | RETIRE 5' OF 4" CS MAIN DUE TO SPLIT MAIN SOAP TESTED OP 7.5 PSIG
21026110200 | EMER - INSTALL 5'-3" PMIP | [5 empty] | 880.36 | 7868.6589 | -6988.2989 |  |  |  | 2021-04-21 | INSTALLED 5' OF 3" PLASTIC. TESTED AT 90PSIG FOR 1HR.
21026110300 | EMER - RETIRE 5'-3" PIP | [5 empty] | 7215.11 | 441.8134 | 6773.2966 |  |  |  | 2021-04-21 | RETIRED 5' OF 3" PLASTIC DUE TO PAC CLAMPS LEAKING.
21026113401 | INSTALL 100'-2" PMMP | [5 empty] | 21410.67 | 11198.5401 | 10212.1299 |  |  |  | 2021-04-19
21026115100 | INSTALL 1'-4" PMLP | [5 empty] | 0 | 149.4587 | -149.4587 |  |  |  | 2021-04-06
21026115800 | EMER - INSTALL 138'-4" PM/CSIP | [5 empty] | 2573.82 | 10752.5629 | -8178.7429 |  |  |  | 2021-04-20 | INSTALLED 134' OF 4" PL IP TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7.5 PSIG
21026115900 | EMER - RETIRE 134'-4" CSIP | [5 empty] | 9847.31 | 1105.3087 | 8742.0013 |  |  |  | 2021-04-20 | RETIRED 134' OF 4" CS DUE MAIN EXPOSED OUT OF GROUND AND DETERIORATION
21026116900 | INSTALL 200'-2" PMLP | [5 empty] | 24792.54 | 39229.3021 | -14436.7621 |  |  |  | 2021-07-06
21026117300 | EMER - RETIRE 2'-4" P-LP | [5 empty] | 183.09 | 441.8134 | -258.7234 |  |  |  | 2021-04-21 | RETIRE 2' OF 4" PL DUE TO DAMAGE
21026120600 | RETIRE REG STATION WITH AMRP | [5 empty] | 1058.49 | 9924.8698 | -8866.3798 |  |  |  | 2022-12-15 | CC# 6407 RETIRED REG STATION DASH 12-15-2022
21026121500 | INSTALL 160'-2" PMIP | [5 empty] | 37719.27 | 21640.9206 | 16078.3494 |  |  |  | 2021-08-24
21026121600 | INSTALL 100'-2" PMIP | [5 empty] | 16499.56 | 13861.3812 | 2638.1788 |  |  |  | 2021-06-14
21026122300 | INSTALL 100'-2" PMMP | [5 empty] | 26947.59 | 25260.7035 | 1686.8865 |  |  |  | 2021-06-25
21026123800 | INSTALL 160'-4" CSLP/PMLP | [5 empty] | 86016.2 | 161313.4069 | -75297.2069 |  |  |  | 2021-08-09 | UNDERRUN EXPLANATION: SIGNIFICANTLY LESS HARD SURFACE RESTORATION AND BACKFILL REQUIRED THAN ESTIMATED KYTC REQUIRED RELOCATION AND TOLD US NOT TO WORRY ABOUT THE MILL & OVERLAY THAT THEY WOULD DO THAT WHEN THEY COMPLETED THEIR PART OF THE PROJECT, THIS RESULTED IN A SIGNIFICANT AMOUNT OF THE COST VARIATION
21026125300 | RETIRE 180'-4" BSLP | [5 empty] | 0 | 282.1429 | -282.1429 |  |  |  | 2021-08-07 | COMMITT DATE WAS PUSHED OUT TILL END OF AUG.2021
21026127800 | INSTALL 500'-2" PMMP | [5 empty] | 47089.22 | 43810.3768 | 3278.8432 |  |  |  | 2021-07-22
21026128500 | NSP - INSTALL 150'-2" PMLP | [5 empty] | 10156.16 | 16760.5972 | -6604.4372 |  |  |  | 2021-06-15 | INSTALLED 150' 2"P. PRESSURE TESTED 90LBS 1HR. SOAP TESTED 2" EF COUPLING AT OP. PRESS. (11 IWC) 15MIN. PRESS. TEST 2X1 MONITORING TEE 90LBS 15MIN. SOAP TESTED MONITORING TEE END CAP OP. PRESS (11 IWC) 15MIN.
21026129800 | INSTALL 200'-2" PMMP | [5 empty] | 25563.52 | 21853.3833 | 3710.1367 |  |  |  | 2021-09-16
21026130200 | EMER-INSTALL 5'-2" PMIP/CSIP | [5 empty] | 7558.85 | 6178.4541 | 1380.3959 |  |  |  | 2023-03-31
21026130300 | EMER-RETIRE 5'-2" BSIP | [5 empty] | 230.72 | 410.7144 | -179.9944 |  |  |  | 2023-03-31
21026130400 | INSTALL 25,111'-2",4" PMMP | [5 empty] | 4360387.57 | 3707985.656 | 652401.914 |  |  |  | 2023-12-05
21026130500 | RETIRE 25,000' OF BSLP MAINS | [5 empty] | 1741.22 | 485.0228 | 1256.1972 |  |  |  | 2023-12-05
21026131300 | RETIRE EFC UNIT | [5 empty] | 0 | 74.8797 | -74.8797 |  |  |  | 2021-07-06 | REPLACED EFC
21026132100 | INSTALL 600'-4" PMMP | [5 empty] | 75178.06 | 159985.8979 | -84807.8379 |  |  |  | 2021-10-01 | INSTALLED 573' OF 4" PL MP AND 9' OF 2" PL MP TESTED 90 PSIG 2 HRS SOAP TESTED FINAL CONN OP 44 PSIG UNDERRUN EXPLANATION: A SIGNIFICANT UNIT OF COST WAS THE PLANNED ROCK BORE BUT THE CREW WAS ABLE TO AVOID THE NEED FOR A ROCK BORE, THE JOB DURATION ESTIMATE TOOL ALSO PLANNED FOR 120 HOURS OF LABOR AND THE CREW COMPLETED THE JOB IN 60 HOURS AND SOME CREW MEMBERS WERE NOT NEEDED THE ENTIRE DURATION OF THE JOB.
21026132200 | RETIRE 450'-4" P-MP | [5 empty] | 212.81 | 875.427 | -662.617 |  |  |  | 2021-10-01 | RETIRED 487' OF 4" PL MP
21026133300 | INSTALL 200'-2" PMIP | [5 empty] | 19749.69 | 14590.9404 | 5158.7496 |  |  |  | 2021-09-02
21026133900 | INSTALL VRG CONTROLER | [5 empty] | 0 | 6187.1439 | -6187.1439 |  |  |  | 2022-11-02
21026134000 | RETIRE DAMAGED CONTROLLER | [5 empty] | 0 | 220.9908 | -220.9908 |  |  |  | 2022-11-02
21026139100 | EMER - INSTALL 5'-4" PMMP | [5 empty] | 2800.66 | 6493.0322 | -3692.3722 |  |  |  | 2021-09-29 | INSTALLED MAIN ON TESTED 90 PSIG 1 HOUR SOAP TESTED FINAL CONN OP 44 PSIG
21026139200 | EMER - RETIRE 5'-4" P-MP | [5 empty] | 5590.11 | 743.2708 | 4846.8392 |  |  |  | 2021-09-29
21026139800 | INSTALL 100'-2" PMIP | [5 empty] | 19936.66 | 27338.1249 | -7401.4649 |  |  |  | 2021-10-01
21026140100 | INSTALL 52'-4"/6" PMIP/CSIP | [5 empty] | 67346.12 | 83495.319 | -16149.199 |  |  |  | 2022-05-31
21026140200 | RETIRE 47'-4"/6" BSIP/CSIP | [5 empty] | 207.25 | 500 | -292.75 |  |  |  | 2022-05-31
21026143700 | INSTALL 4'-4" PMLP | [5 empty] | 478.5 | 3297.2047 | -2818.7047 |  |  |  | 2021-12-18 | INSTALLED 4' OF 4" PL LP MAIN LINE TESTED 90 PSIG 1 HOUR SOAP TESTED FINAL CONN OP 10" WC
21026143800 | RETIRE 4'-4" PMLP | [5 empty] | 44.74 | 295.4309 | -250.6909 |  |  |  | 2021-12-18 | RETIRED MAIN DUE TO STEEL SADDLE TEE BIENG ON PL PIPE INSTALLED NEW SECTION OF PIPE
21026144600 | INSTALL 12" SS | [5 empty] | 25613.83 | 13660.0322 | 11953.7978 |  |  |  | 2021-12-20 | INSTALLED 12" SS TO STOPPLE AND KILL 12" MAIN
21026144700 | RETIRE 1273'-6/12/16" CS/BSHP | [5 empty] | 167.43 | 388.1295 | -220.6995 |  |  |  | 2021-12-20 | RETIRE 1207' OF 12" BS HP TO AK STEEL SOAP TESTED OP 113 PSIG
21026146300 | INSTALL 4'-4" PMLP | [5 empty] | 424.36 | 2206.8953 | -1782.5353 |  |  |  | 2021-10-12 | INSTALLED 4' OF 4" PLASTIC MAIN. PRESSURE TESTED 90LBS FOR 1HR.
21026146400 | RETIRE 4'-4" P-LP | [5 empty] | 39.69 | 197.4141 | -157.7241 |  |  |  | 2021-10-12
21026146800 | RETIRE GMB #44535-AK STEEL | [5 empty] | 3852.12 | 2893.6188 | 958.5012 |  |  |  | 2021-10-25 | ALL FACILITIES REMOVED FROM AK STEEL BY MATT RYAN AND SHANE GIORDANO MAINLINE/SERVICE LINE ABANDONED ON 10/18/2021 BY CONSTRUCTION SERVICES M&R PAPERWORK COMPLETED BY CYNTHIA FARIS ON 10/25/2021
21026149000 | INSTALL 75'-2" PMIP | [5 empty] | 765.35 | 4287.763 | -3522.413 |  |  |  | 2021-12-20 | INSTALLED 66' OF 2" PL TESTED 90 PSIG 0005 MIN SOAP TESTED CAP OP 8 PSIG
21026150000 | EMER - INSTALL 14'-4" PMLP | [5 empty] | 72137.82 | 3163.1338 | 68974.6862 |  |  |  | 2021-12-22 | INSTALLED 16' OF 4" PL W/ 4 90'S TO GO ABOVE 24" CLAY TILE SEWER TESTED 90 PSIG 1 HR OVERRUN EXPLANATION: CROSSBORE FOUND- CAMERA CREW NEEDED AND ADDITIONAL HOURS NEEDED TO REMEDIATE THE CROSS-BORE ISSUE 2 MAINTENCE JOBS AND 1 PAVE JOB CHARGED BACK TO CAPITAL JOB AND WERE NOT ACCOUNTED FOR IN ORIGINAL PROPOSED COST, $26K IN FLAGGING AND RESTORATION CHARGED TO MAINTENCE JOBS AND $14K IN CAMERA WORK BY CONTRACTOR
21026150100 | EMER - RETIRE 6'-4" P-LP | [5 empty] | 669.23 | 335.9749 | 333.2551 |  |  |  | 2021-12-22 | REMOVED 4" PL FROM SEWER LINE CROSS BORE
21026150600 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 378.77 | 1696.2756 | -1317.5056 |  |  |  | 2021-11-16
21026150700 | EMER - RETIRE 5'-2" PMP | [5 empty] | 64.43 | 335.9749 | -271.5449 |  |  |  | 2021-11-17
21026153400 | EMER - INSTALL 6'-4" PMIP | [5 empty] | 7455.58 | 4080.2324 | 3375.3476 |  |  |  | 2021-12-22
21026153500 | EMER - RETIRE 6'-4" PMIP | [5 empty] | 101.71 | 518.618 | -416.908 |  |  |  | 2021-12-22
21026154000 | INSTALL 160'-2" PMMP | [5 empty] | 28534.77 | 33091.7151 | -4556.9451 |  |  |  | 2022-02-14
21026154600 | RETIRE R-1354 | [5 empty] | 8911.51 | 163.2711 | 8748.2389 |  |  |  | 2023-11-26
21026154800 | RETIRE 35'-3" CSMP | [5 empty] | 27.2 | 485.0228 | -457.8228 |  |  |  | 2023-12-05
21026155700 | INSTALL FENCE - SCADA BUILDING | [5 empty] | 7557.57 | 15936.4497 | -8378.8797 |  |  |  | 2022-08-22
21026156500 | INSTALL 140'-2"/4" PMMP | [5 empty] | 2096.07 | 3669.7405 | -1573.6705 |  |  |  | 2021-12-21
21026157800 | INSTALL 5'-4" PMLP | [5 empty] | 2758.28 | 4114.4273 | -1356.1473 |  |  |  | 2022-01-03
21026157900 | RETIRE 5'-4" PMLP | [5 empty] | 485.31 | 72.8047 | 412.5053 |  |  |  | 2022-01-03
21026993200 | EMER- INSTALL 5'-4" PMMP | [5 empty] | 3260.67 | 4003.4824 | -742.8124 |  |  |  | 2021-01-08 | INSTALLED 4' OF 4" P. PRESSURE TESTED AT 90LBS FOR 1HR. SOAP TESTED (2) 4" EF COUPLINGS AT OPERATING PRESSURE (11PSIG).
21026993300 | EMER- RETIRE 5'-4" P-MP | [5 empty] | 184.74 | 647.029 | -462.289 |  |  |  | 2021-01-08 | REMOVED 4' OF DAMAGED 4" P
21026993401 | INSTALL 10750'-2"/4"PMMP MAIN | [5 empty] | 2072101.63 | 1880428.7756 | 191672.8544 |  |  |  | 2022-11-17
21026993500 | RETIRE 13650' OF 4"/6"BSLP | [5 empty] | 80 | 86.5975 | -6.5975 |  |  |  | 2022-11-17
21026993600 | EMER INST 40'-4" PMLP | [5 empty] | 772.98 | 13260.7401 | -12487.7601 |  |  |  | 2021-01-08 | INSTALLED 28' OF 4" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 10" WC
21026993700 | EMER RET 40'-4" BSLP/CSLP/P-LP | [5 empty] | 372.17 | 1322.2973 | -950.1273 |  |  |  | 2021-01-08 | RETIRED 28' OF 4" STEEL MAIN AND 3 WAY TEE
21026999201 | RETIRE 3"PIP SERVICE LINE | [5 empty] | 14749.54 | 6359.645 | 8389.895 |  |  |  | 2023-06-26 | STEP 3 NEEDS INVESTIGATED STEP 3 NEEDS STATE PERMIT STEP 3 NEEDS STATE PERMIT THIS IS A PAPER ABN. THIS LINE IS AN ACTIVE LINE BUT THEY ARE NOT OUR CUSTOMER. THEY ARE USING NATURAL ENERGY. OUR ASSETS ARE NOT WITHIN THE PROPERTY. U131418 J. PARKS 4-24-23
22026159700 | EMER - INSTALL 4'-4" PMLP | [5 empty] | 1914.95 | 4455.398 | -2540.448 |  |  |  | 2022-01-24
22026159800 | EMER - RETIRE 4'-4" P-LP | [5 empty] | 6434.1 | 448.5353 | 5985.5647 |  |  |  | 2022-01-20 | RETIRED 4' OF 4" PL LP TO REMOVED STEEL SADDLE FROM PLASTIC MAIN
22026159900 | EMER - INSTALL 2'-2" PMLP | [5 empty] | 2408.32 | 2367.5988 | 40.7212 |  |  |  | 2022-02-03
22026160000 | EMER - RETIRE 2'2"P-LP D244381 | [5 empty] | 487.19 | 506.8997 | -19.7097 |  |  |  | 2022-02-07
22026160300 | RETIRED ELECTRONICS | [5 empty] | 422.53 | 75.9523 | 346.5777 |  |  |  | 2021-08-17
22026169000 | MAVITY HVAC UPGRADE | [5 empty] | 5678.5 | 15264.0767 | -9585.5767 |  |  |  | 2022-08-05
24026324100 | INSTALL 670'-2' PMIP | [5 empty] | 91180.5 | 68828.4274 | 22352.0726 | 2024-01-01 | 2024-12-31 | 2024-10-28 | 2024-11-14 | INSTALLED 704' OF 2" PL IP AND 3' OF 2" ST TESTED 111 PSIG FOR 1 HR SOAP TE STED SST CAP AND PURGE POINT CAPS OP 7.5 PSIG
22026172400 | RETIRE 4792'-2/4/8" PL/CS/BSLP | [5 empty] | 220 | 709.5359 | -489.5359 |  |  |  | #N/A
22026174900 | INSTALL 50'-2" PMMP | [5 empty] | 36910.2 | 30717.8249 | 6192.3751 |  |  |  | 2022-05-11
22026175800 | EMER - INSTALL 120'-3" PMLP | [5 empty] | 32123.93 | 12124.3189 | 19999.6111 |  |  |  | 2022-04-05 | INSTALLED 120' OF 3" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 10" W C
22026175900 | EMER - RETIRE 121'-3" P-LP | [5 empty] | 931.56 | 373.4562 | 558.1038 |  |  |  | 2022-04-05 | RETIRE 121' OF 3" PL DUE TO WATER AND STEEL FITTINGS ON PL MAIN
22026177000 | EMER - INSTALL 2'-4" PMIP | [5 empty] | 2292.91 | 4197.8249 | -1904.9149 |  |  |  | 2022-04-01
22026177100 | EMER - RETIRE 2'-4" P-IP | [5 empty] | 2387.49 | 310.9595 | 2076.5305 |  |  |  | 2022-04-01
22026180500 | INSTALL 160'-2" PMIP | [5 empty] | 22724.8 | 36664.9938 | -13940.1938 |  |  |  | 2022-07-13
22026180700 | EMER - INSTALL 3'-3" PMIP | [5 empty] | 6701.19 | 4036.7887 | 2664.4013 |  |  |  | 2023-08-25
22026180800 | EMER - RETIRE 3'-3" PMIP | [5 empty] | 61.4 | 418.4749 | -357.0749 |  |  |  | 2023-08-25
22026182300 | RETIRE PAPER RECORD GAUGE | [5 empty] | 144.38 | 329.4627 | -185.0827 |  |  |  | 2022-04-20
22026184500 | INSTALL 250'-4" PMLP/CSLP | [5 empty] | 63976.36 | 60316.4006 | 3659.9594 |  |  |  | 2022-08-10
22026190600 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 817.09 | 4801.1928 | -3984.1028 |  |  |  | 2022-06-23 | CCC 71454 RETIRED ERX AND INSTALLED NEW MIWI350
22026191000 | RETIRED ELECTRONICS EQUIPMENT | [5 empty] | 261.55 | 124.8731 | 136.6769 |  |  |  | 2022-06-23 | CCC 71454 RETIRE ERX AND INSTALLED NEW MIWI 350
22026191700 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 10605.54 | 4801.1928 | 5804.3472 |  |  |  | 2022-08-12 | UPGRADED ERX TO MIWI JOSH MULLINS
22026191800 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 20.04 | 124.8731 | -104.8331 |  |  |  | 2022-08-12
22026191900 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 744.93 | 4801.1928 | -4056.2628 |  |  |  | 2022-06-23 | CCC 71454
22026192000 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 922.45 | 124.8731 | 797.5769 |  |  |  | 2022-06-23 | CCC 71454
22026192100 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 2317.01 | 4801.1928 | -2484.1828 |  |  |  | 2022-08-15 | CCC 75023
22026192200 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 884.51 | 124.8731 | 759.6369 |  |  |  | 2022-08-15 | CCC 75023 UPGRADED ERX TO MIWI J.MULLINS
22026196200 | EMER - INSTALL 1'-2" PMMP | [5 empty] | 6510.29 | 2866.3857 | 3643.9043 |  |  |  | 2022-06-15 | INSTALLED 1' OF 2" PL DUE TO FACILTY DAMAGE TESTED 90 PSIG 0005 MIN SOAP TE STED FINAL CONN OP 42 PSIG REVISED EXECUTE COMMENTS: INSTALLED 1' OF 2" PL DUE TO FACILITY DAMAGE TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 42 PSIG/MCOLLETT 7/8/22
22026196300 | EMER - RETIRE 1'-2" P-MP | [5 empty] | 1254.11 | 497.9695 | 756.1405 |  |  |  | 2022-06-15 | RETIRED 1' OF 2" PL MP DUE TO FACILITY DAMAGE SOAP TESTED OP TO VERIFY GAS SHUTOFF
22026198200 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5532.75 | 4801.1928 | 731.5572 |  |  |  | 2022-08-11 | CC 76915 UPGRADDED ERX TO MIWI 350
22026198300 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 467.24 | 124.8731 | 342.3669 |  |  |  | 2022-08-11 | CC 76915 UPDATTED ERX TO MIWI 350
22026198700 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 6293.17 | 4801.1928 | 1491.9772 |  |  |  | 2022-09-13 | CC 497 CC 497 REPLACED OLD ERX WITH NEW MIWI350 SGIORDANO 9-13-2022
22026198800 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 1014.14 | 124.8731 | 889.2669 |  |  |  | 2022-09-13 | CC 497 REPLACED ERX WITH NEW MIWI350 SGIORDANO 9-13-2022
22026199900 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 6476.38 | 4801.1928 | 1675.1872 |  |  |  | 2022-09-15 | CC 118 INSTALLED NEW MIWI350 RETIRED OLD ERX SGIORDANO 9-15-22
22026200200 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 1400.9 | 124.8731 | 1276.0269 |  |  |  | 2022-09-15 | CC 118 INSTALLED NEW MIWI350 SGIORDANO 9-15-22 C 2820
22026200300 | EMER - INSTALL 5'-2" PMIP | [5 empty] | 9101.9 | 2610.0199 | 6491.8801 |  |  |  | 2022-06-07 | REPLACED 5' SECTION OF 2" PMMP. TESTED MAIN AT 90 PSIG FOR 1 HOUR AND TEST WAS GOOD. TESTED 2X1 EF TEES AT 90 PSIG FOR 5 MINS AND SOAP TESTED THE CAPS AND DEAD ENDS AT OP FOR 5 MINS. ALL TEST ARE GOOD.
22026200900 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 6137.4 | 4801.1928 | 1336.2072 |  |  |  | 2022-09-14 | CC 632 UPGRADED TO MIWI 350 PAPERWORK DONE BY J.MULLINS
22026201000 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 485.58 | 124.8731 | 360.7069 |  |  |  | 2022-09-14 | CC 632 UPGRADED TO MIWI 350 PAPERWORK DONE BY J.MULLINS
22026205200 | INSTALL 115'-2" PMMP | [5 empty] | 21273.79 | 42423.5179 | -21149.7279 |  |  |  | 2022-10-06 | CJ HUGHES CASEY PACK'S CREW INSTALLED 103' 2" STEEL/PLASTIC MAIN LINE EXTEN TION AND A NEW 1" PLASTIC SERVICE TO 1519 MAPLE ST 10/6/22 MBLANKE U123965
22026205600 | INSTALL 1200'-2" PMMP | [5 empty] | 162971.11 | 61578.4138 | 101392.6962 |  |  |  | 2022-10-04 | LEVEL 2 BUDGET VARIANCE EXPLANATION FORM WAS SUBMITTED FOR APPROVAL IN WMSDOCS PER VAPIERCE 5/25/23
22026206400 | RETIRE ELECTRONIC | [5 empty] | 2331.95 | 65.0112 | 2266.9388 |  |  |  | 2022-09-19 | RETIRED OLD MINIAT INSTALLED NEW EC350 DASH 9-19-2022
24026337000 | INSTALL 675' OF 2"PMMP MAIN | [5 empty] | 44370.55 | 60312.9634 | -15942.4134 | 2024-01-01 | 2024-12-31 | 2024-05-06 | 2024-05-21
22026207200 | RETIRE 6009'-2",3", 4" LP | [5 empty] | 873.05 | 1120.6093 | -247.5593 |  |  |  | #N/A
22026210700 | RETIRE METAL BUILDING | [5 empty] | 0 | 1009.5809 | -1009.5809 |  |  |  | 2022-12-15 | REG STATION AND BUILDING RETIRED DASH 12-15-22
22026211000 | EMER - INSTALL 3'-4" PMMP | [5 empty] | 8542 | 12351.4608 | -3809.4608 |  |  |  | 2022-07-28 | CUT OUT 3' OF 4" PL MP AND REPLACED WITH NEW 3' OF 4" PL MP TESTED 90 PSIG 1 HOUR
22026211100 | EMER - RETIRE 3'-4" PMMP | [5 empty] | 449.88 | 477.8601 | -27.9801 |  |  |  | 2022-07-28 | RETIRED 3' OF 4" PL MP AND INSTALLED NEW 3' OF 4" PL TESTED 90 PSIG 1 HOUR SOAP TESTD FINAL CONN OP 40 PSIG
22026211800 | RETIRE GMB SETTING | [5 empty] | 1541.41 | 1288.7874 | 252.6226 |  |  |  | 2023-01-10 | GMB NO CC NEEDED
22026213800 | EMER - RETIRE 150'-2" P-IP | [5 empty] | 4136.05 | 4412.2636 | -276.2136 |  |  |  | 2022-09-06 | ABANDONED 150' OF 2" PLASTIC. SOAP TESTED ABANDONMENT AT OP. PRESS. 15MIN.
22026214400 | MAVITY HVAC/RTU | [5 empty] | 0 | 55.5311 | -55.5311 |  |  |  | 2022-08-05 | UPGRADED RTU
22026216300 | INSTALL VRG CONTROLLER | [5 empty] | 28545.09 | 10806.1191 | 17738.9709 |  |  |  | 2023-02-09 | CC 15047 CC 15628 CC 15628 CC 15628 CC 15628 CC 16352 NOT ON SITE CAPITAL PAPERWORK/ISO SKETCH
22026216400 | RETIRE CONTROLLERS | [5 empty] | 572.67 | 84.9152 | 487.7548 |  |  |  | 2023-02-09 | RETIRED CONTROLLERS, INSTALLED NEW VRG'S
22026218400 | RETIRE 2'-4" BSLP | [5 empty] | 0 | 84.9152 | -84.9152 |  |  |  | 2022-08-15
22026218500 | INSTALL 35'-2"/4 PMLP | [5 empty] | 8610.21 | 16435.9913 | -7825.7813 |  |  |  | 2022-10-27 | INSTALLED 2' OF 4" PL AND 37' OF 2" PL LP TESTED 90 PSIG 1 HR
22026219600 | INSTALL 90'-2" PMIP | [5 empty] | 50608.23 | 21041.6638 | 29566.5662 |  |  |  | 2022-12-19
22026228900 | EMER - INSTALL 40'-2" PMIP | [5 empty] | 37570.14 | 32269.3764 | 5300.7636 |  |  |  | 2022-10-13
22026229000 | EMER - RETIRE 40'-2" PIP | [5 empty] | 0 | 132.427 | -132.427 |  |  |  | 2022-10-13
22026230800 | EMER - RETIRE 3'-2" P-IP | [5 empty] | 1400.06 | 1985.3283 | -585.2683 |  |  |  | 2022-12-15 | CONTRACTOR HIT MISS MARKED MAIN CUT OUT DAMAGED SECTION AND EF PURGE POINT ON END OF MAIN LINE SOAP TESTED OP 7 PSIG
22026231600 | EMER - INSTALL 2'-4" PMMP | [5 empty] | 196.47 | 5460.0467 | -5263.5767 |  |  |  | 2022-11-11 | INSTALLED 2' OF 4" PL MP TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 40 P SIG
22026231700 | EMER - RETIRE 2'-4" PMMP | [5 empty] | 24.23 | 263.239 | -239.009 |  |  |  | 2022-11-11 | RETIRED 2' OF 4" PL MP DUE TO LEAKAGE SOAP TESTED TO VERFY SHUTDOWN
22026232200 | INSTALL SKID MOUNTED GMB | [5 empty] | 40259.26 | 56170.7039 | -15911.4439 |  |  |  | 2022-12-15 | INSTALLED NEW SKID MOUNTED METER SETTING DASH 12-15-22
22026232300 | RETIRE GMB SETTING | [5 empty] | 1984.01 | 263.239 | 1720.771 |  |  |  | 2022-12-15 | INSTALLED NEW SKID MOUNT METER SETTING AND RETIRED OLD METER AND REGULATORS DASH 12-15-22
22026232700 | RETIRE GMB W/22-9790457-00 | [5 empty] | 0 | 545.7645 | -545.7645 |  |  |  | 2022-12-21
22026234200 | INSTALL 100'-6"PMMP S/L | [5 empty] | 60246.05 | 78909.8457 | -18663.7957 |  |  |  | 2022-12-06 | CJH JOE HADLEY REPLACED SL, TESTED SL AT 0106PSIG/0200HRS, OPEN CUT, SOAP TESTED FC/CAP AT OP, EXT CORR INSP, NO ANODE, WRAPPED EXPOSED MAIN, DS 12062022
22026234300 | RETIRE GMB SETTING | [5 empty] | 0 | 725.239 | -725.239 |  |  |  | 2022-11-21 | RETIRED GMB SETTING REMOVED METER BLIND PLATED SERVICE GAS NO LONGER NEEDED
22026235200 | INSTALL 200'-2" PMIP | [5 empty] | 11987.46 | 38455.6638 | -26468.2038 |  |  |  | 2022-12-19
22026235800 | EMER - INSTALL 3'-4" PMMP | [5 empty] | 7089.71 | 18999.7951 | -11910.0851 |  |  |  | 2022-12-15 | FOUND CLAMPS ON 4" PL MAIN CUT OUT AND INSTALLED NEW MAIN TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 15 PSIG
22026235900 | EMER - RETIRE 3'-4" P-MP | [5 empty] | 22647.66 | 117.5985 | 22530.0615 |  |  |  | 2022-12-15 | RETIRED 4" PL MAIN WITH CLAMPS ON IT TO INSTALL NEW
22026240200 | EMER - INSTALL 100'-4" PMLP | [5 empty] | 5141.88 | 38890.2222 | -33748.3422 |  |  |  | 2022-12-30 | INSTALLED 93' OF PL AND ST TESTED 90 PSIG 1 HR SOAP TESTED WELD CAPS AND SSTEE CAPS 10" WC
22026240300 | EMER - RETIRE 100'-4" BSLP | [5 empty] | 285.28 | 129.6266 | 155.6534 |  |  |  | 2022-12-30 | RETIRED 75' OF 4" BS DUE TO LEAKAGE
22026240400 | PAPER ONLY - RETIRE BSIP MAIN | [5 empty] | 0 | 119.2135 | -119.2135 |  |  |  | 2022-12-19
22026241300 | EMER - INSTALL 5'-4" PMMP | [5 empty] | 1144.39 | 10162.4624 | -9018.0724 |  |  |  | 2022-12-15 | INSTALLED 3' OF 4" PL DUE TO LEAKAGE ON SERVICE TEE TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 11 PSIG
22026241400 | EMER - RETIRE 5'-4" PMP | [5 empty] | 91.78 | 117.5985 | -25.8185 |  |  |  | 2022-12-15 | RETIRE 4" MP TO DUE TO LEAKAGE ON SERVIEC TEE TO INSTALL NEW
22026244600 | INSTALL BUILDING AND FENCE | [5 empty] | 0 | 28935.3221 | -28935.3221 |  |  |  | 2022-03-17 | INSTALLED COMM BUILDING AND FENCE DASH 3-17-22
22026245500 | INSTALL REG STATION BUILDING | [5 empty] | 12285 | 128388.6752 | -116103.6752 |  |  |  | 2022-12-16
23026246000 | INSTALL M&R CRANE - MARATHON | [5 empty] | 14182.67 | 36312.6752 | -22130.0052 |  |  |  | 2022-12-16
23026246200 | INSTALL VRG - MIS FACILITY | [5 empty] | 0 | 449.3532 | -449.3532 |  |  |  | 2022-12-16
23026246300 | INSTALL VRG - RETIRE MIS FAC | [5 empty] | 0 | 132.4844 | -132.4844 |  |  |  | 2022-12-16
23026246800 | INSTALL 800'-4" PMMP | [5 empty] | 287158.53 | 369832.3416 | -82673.8116 |  |  |  | 2023-04-19
23026246900 | RETIRE 1000'-4" P-MP | [5 empty] | 0 | 123.4477 | -123.4477 |  |  |  | 2023-04-19
23026247100 | EMER - INSTALL 9'-4" CSMP/PMP | [5 empty] | 5323.15 | 14951.5544 | -9628.4044 |  |  |  | 2023-01-31 | LOWERED MAIN DUE TO LEAKAGE AND 14" WATER LINE TESTED 90 PSIG 0005 MIN SOAP TESTED FINAL CONN OP 40 PSIG
23026247200 | EMER - RETIRE 9'-4" CSMP | [5 empty] | 806.29 | 149.6969 | 656.5931 |  |  |  | 2023-01-31 | RETIRED 9' OF 4" ST TO LOWER FOR 14" WATER MAIN SOAP TESTED OP TO VERIFY AD EQUATE SHUT DOWN 40 PSIG
23026248600 | RETIRE 3'-3" PMLP | [5 empty] | 3012.93 | 1635.0284 | 1377.9016 |  |  |  | 2023-01-25 | RETIRED 20' OF 3" PL MAIN DUE TO FACILITY DAMAGE SOAP TESTED OP 9.5" WC
23026249100 | INSTALL 100'-2" PMMP | [5 empty] | 13611.51 | 7008.1595 | 6603.3505 |  |  |  | 2023-03-03 | INSTALLED NEW MAIN ON RICHLAND CT TESTED 90 PSIG 1 HR SOAP TESTED BRANCHING TEE CAP AND PURGE POINT CAP OP 14 PSIG
23026249200 | GMB TO CAB CONVERSION | [5 empty] | 858.55 | 132.4844 | 726.0656 |  |  |  | 2023-01-17 | CONVERTED FROM GMB TO CAB SGIORDANO
23026251100 | INSTALL EC-350 UNIT | [5 empty] | 1808.88 | 3195.3221 | -1386.4421 |  |  |  | 2023-01-24 | INSTALLED NEW EC350 DASH 1-24-23
23026251200 | RETIRE PAPER BILLING CHART | [5 empty] | 975.93 | 131.2422 | 844.6878 |  |  |  | 2023-01-24 | RETIRED CHART INSTALLED NEW EC350 DASH 1-24-23
23026251300 | INSTALL EC 350 UNIT | [5 empty] | 8141.46 | 7475.3221 | 666.1379 |  |  |  | 2023-03-13 | INSTALLED NEW EC350 TO REPLACE PAPER BILLING CHART
23026251400 | RETIRE PAPER BILLING CHART | [5 empty] | 870.82 | 131.2422 | 739.5778 |  |  |  | 2023-03-13 | RETIRE PAPER BILLING CHART
23026254200 | RETIRE RECORDING GAUGE | [5 empty] | 107.1 | 552.5683 | -445.4683 |  |  |  | 2023-03-01 | CC 10596 RETIRE PAPER CHART SHANE G. 03012023
23026256700 | RETIRE PAPER GAUGE | [5 empty] | 756.49 | 138.8485 | 617.6415 |  |  |  | 2023-02-21 | CC 17512 REMOVED PAPER PRESSURE GAUGE
23026257200 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 3080.61 | 12042.2854 | -8961.6754 |  |  |  | 2023-08-12 | CC 41028
23026257300 | RETIRE CHART | [5 empty] | 386.09 | 124.7348 | 261.3552 |  |  |  | 2023-08-15
23026257500 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 3917.88 | 23732.2854 | -19814.4054 |  |  |  | 2023-07-12
23026257600 | RETIRE PAPER CHAT | [5 empty] | 575.02 | 121.7239 | 453.2961 |  |  |  | 2023-07-12
23026257700 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 3552.01 | 22126.2854 | -18574.2754 |  |  |  | 2023-08-16
23026257800 | RETIRE PAPER CHART | [5 empty] | 1141.91 | 121.7239 | 1020.1861 |  |  |  | 2023-08-16
23026258100 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 4339.86 | 20638.2854 | -16298.4254 |  |  |  | 2023-07-13 | CC 41992
23026258200 | RETIRE PAPER CHART | [5 empty] | 0 | 121.7239 | -121.7239 |  |  |  | 2023-07-13
23026258500 | INSTALL ULTRASONIC METER | [5 empty] | 51660.67 | 47491.9621 | 4168.7079 |  |  |  | #N/A | CC# 47829
23026258600 | EMER - INSTALL 5'-4" PMIP | [5 empty] | 29274.5 | 23135.0467 | 6139.4533 |  |  |  | 2023-06-14 | INSTALLED 3' OF 4" PL DUE TO BORE CREW BORING INTO MAIN TESTED 90 PSIG 1 HR
23026258700 | EMER- RETIRE 5'-4" PMIP | [5 empty] | 21718.99 | 137.555 | 21581.435 |  |  |  | 2023-06-13 | RETIRED 3' OF 4" IP DUE TO BORE CREW HITTING MAIN SOAP TESTED OP 7 PSIG TO VERIFY SQUEEZE OFF
23026258900 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 5852.27 | 22126.2854 | -16274.0154 |  |  |  | 2023-09-01
23026259200 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 4121.74 | 21353.2854 | -17231.5454 |  |  |  | 2023-07-14 | CC 37280
23026259300 | RETIRE PAPER CHART | [5 empty] | 0 | 121.7239 | -121.7239 |  |  |  | 2023-07-14
23026259400 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 3579.71 | 20638.2854 | -17058.5754 |  |  |  | 2023-07-18
23026259500 | RETIRE PAPER CHART | [5 empty] | 347.11 | 121.7239 | 225.3861 |  |  |  | 2023-07-18
23026259800 | INSTALL ERX W/SUPER SOLAR | [5 empty] | 3465.31 | 5058.9621 | -1593.6521 |  |  |  | 2023-03-02 | CC# 18720. 3/2/23 DSASH
23026259900 | RETIRE PAPER CHART | [5 empty] | 277.39 | 138.8485 | 138.5415 |  |  |  | 2023-03-02 | CC# 18720. 3/2/23 DSASH CC# 18720
23026260000 | INSTALL ERX W/SUPER SOLAR | [5 empty] | 3193.7 | 5058.9621 | -1865.2621 |  |  |  | 2023-02-28 | CC# 18341. 2/28/23 DSASH CC# 21913. P2P OK.
23026260100 | RETIRE PAPER GAUGE | [5 empty] | 257.79 | 138.8485 | 118.9415 |  |  |  | 2023-02-28 | CC# 18341. 2/28/23 DSASH
23026260200 | INSTALL ERX W/SUPER SOLAR | [5 empty] | 4114.48 | 6314.9621 | -2200.4821 |  |  |  | 2023-02-22 | CC 17668 NOT ON SITE CAPITAL PACKET PAPERWORK NOT ONSITE. ISO UPDATES CC 21100 ANNUAL GAUGE INSP AND P2P WITH GAS CONTROL COMPLETE.
23026260300 | RETIRE PAPER CHART | [5 empty] | 564.75 | 138.8485 | 425.9015 |  |  |  | 2023-02-22 | CC 17668
23026260400 | INSTALL ERX W/SUPER SOLAR | [5 empty] | 3437.82 | 6314.9621 | -2877.1421 |  |  |  | 2023-02-23 | CC 17834 NOT ON SITE. CAPITAL PACKET PAPERWORK NOT ON SITE ISO UPDATES CC 21100 ANNUAL GAUGE INSP AND P2P WITH GAS CONTROL COMPLETE
23026260500 | RETIRE PAPER CHART | [5 empty] | 605.66 | 138.8485 | 466.8115 |  |  |  | 2023-02-23 | CC 17834
23026260900 | INSTALL ERX W/SUPER SOLAR | [5 empty] | 1872.11 | 5458.9621 | -3586.8521 |  |  |  | 2023-03-17 | CC 20969 CC 24221 P2P OK WITH GC.
23026261000 | RETIRE PAPER CHART | [5 empty] | 174.56 | 138.8485 | 35.7115 |  |  |  | 2023-03-17 | CC 20961
23026261200 | INSTALL ULTRASONIC METER | [5 empty] | 57893.54 | 47951.5304 | 9942.0096 |  |  |  | 2023-12-14
23026261700 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 3770.68 | 21353.2854 | -17582.6054 |  |  |  | 2023-07-17
23026261800 | RETIRE PAPER CHART | [5 empty] | 642.64 | 121.7239 | 520.9161 |  |  |  | 2023-07-17 | CC 37443
23026262200 | EMER - INSTALL 4'-2" PMMP | [5 empty] | 15777.13 | 2419.7892 | 13357.3408 |  |  |  | 2023-03-03 | INSTALLED 4' OF 2" PLASTIC MAIN. PRESSURE TESTED AT 90LBS FOR 1 HR.
23026262300 | EMER - RETIRE 4'-2" PMMP | [5 empty] | 242.84 | 260.4446 | -17.6046 |  |  |  | 2023-03-03 | REMOVED 4' OF DAMAGED 2" PLASTIC
23026262400 | INSTALL RTU & INSTRUMENTATION | [5 empty] | 279231.64 | 257150.5602 | 22081.0798 |  |  |  | #N/A | CC 27892 NOT ON SITE CONTRACTOR RESCHEDULED CC 44847 CC 45180 CC 51942 CC 52129 CC# 52432 NO CC NEEDED CC 53623 CC 53623 CC 53373 CC 53373
23026262500 | RETIRE RTU & INSTRUMENTATION | [5 empty] | 0 | 117.7346 | -117.7346 |  |  |  | #N/A
23026262601 | INSTALL CHAIN LINK FENCE | [5 empty] | 72669.9 | 39848.4833 | 32821.4167 |  |  |  | 2023-12-29 | CC 44278 NOT ON SITE CC 53373 CC 53373 CC 57440 CC 58157
23026264500 | EMER - INSTALL ~5'-4" PM/CSMP | [5 empty] | 929.35 | 2069.4953 | -1140.1453 |  |  |  | 2023-08-25
23026264600 | EMER - RETIRE ~5'-4" CSMP | [5 empty] | 207.34 | 67.4953 | 139.8447 |  |  |  | 2023-08-25
23026265600 | EMER - INSTALL 4'-6" PMIP | [5 empty] | 19713.32 | 12463.1003 | 7250.2197 |  |  |  | 2023-08-26
23026265700 | EMER - RETIRE 4'-6" P-IP | [5 empty] | 0 | 391.4196 | -391.4196 |  |  |  | 2023-08-25
23026269500 | EMER - INSTALL 4'-2" PIP | [5 empty] | 2717.09 | 7943.8116 | -5226.7216 |  |  |  | 2023-08-26
23026269600 | EMER - RETIRE 5'-2" PIP | [5 empty] | 0 | 134.4334 | -134.4334 |  |  |  | 2023-08-25
23026270200 | EMER - RETIRE 5'-2" PIP | [5 empty] | 0 | 288.6068 | -288.6068 |  |  |  | 2022-06-07 | REPLACED 5' SECTION OF 2" PMMP. TESTED MAIN AT 90 PSIG FOR 1 HOUR AND TEST WAS GOOD. TESTED 2X1 EF TEES AT 90 PSIG FOR 5 MINS AND SOAP TESTED THE CAPS AND DEAD ENDS AT OP FOR 5 MINS. ALL TEST ARE GOOD.
23026270300 | EMER - INSTALL 2'-4" PMMP | [5 empty] | 526.5 | 9141.6411 | -8615.1411 |  |  |  | 2023-05-25
23026270400 | EMER - RETIRE 110'-4" P-MP | [5 empty] | 537.22 | 137.555 | 399.665 |  |  |  | 2023-05-25 | RETIRED 110' OF 4" PL MP DUE TO BUILDING COLLAPSING TESTED CAP 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 38 PSIG
23026271400 | EMER - INSTALL ~5'-2" PMMP | [5 empty] | 7739.82 | 5664.5366 | 2075.2834 |  |  |  | 2023-05-09 | INSTALLED 1' OF 2" PL MP DUE TO DAMAGE TESTED 90 PSIG 1 HR SOAP TESTED FINA L CONN OP 40 PSIG
23026271500 | EMER - RETIRE ~5'-2" PMMP | [5 empty] | 709.93 | 114.3981 | 595.5319 |  |  |  | 2023-05-09 | RETIRED 1" OF 2" PL MP DUE TO FACILITY DAMAGE SOAP TESTED TO VERIFY SQUEEZE OFF OP 40 PSIG
23026275200 | EMER - INSTALL 3'-2" PMIP | [5 empty] | 5562.78 | 9765.5645 | -4202.7845 |  |  |  | 2023-06-14 | INSTALLED 3' OF 2" MAIN DUE TO DAMAGE BY BORE CREW TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 5.5 PSIG
23026275300 | EMER - RETIRE 3'-2" PIP | [5 empty] | 235.76 | 134.4334 | 101.3266 |  |  |  | 2023-06-14 | RETIRED 3' OF 2" PL DUE TO BORE CREW HITTING MAIN TIEING CONDUIT TOGHETHER
23026277600 | INSTALL 595'-2"PMMP | [5 empty] | 137119.9 | 198539.3537 | -61419.4537 |  |  |  | 2023-11-10
23026277700 | RETIRE 2881'-12" BSMP | [5 empty] | 430.39 | 139.1159 | 291.2741 |  |  |  | 2023-11-10
23026278100 | RETIRE REG FAC | [5 empty] | 0 | 67.1159 | -67.1159 |  |  |  | 2023-06-06 | JOB TO EXECUTE PAPERWORK ONLY RWILLIAMS 6-6-2023
23026278700 | INSTALL 105'-2" PMMP | [5 empty] | 9899.17 | 17148.7846 | -7249.6146 |  |  |  | 2023-06-26 | INSTALLED 116' OF 2" PL MP TESTED 90 PSIG 0005 MIN SOAP TESTED CAPS AND DEA D HEADS OP 17 PSG
23026308601 | INSTALL 675'-2" PMMP | [5 empty] | 91036.22 | 75877.1307 | 15159.0893 | 2024-01-01 | 2024-12-31 | 2024-05-27 | 2024-06-10 | JOB COMPLETED ON 5-14-24, ENGINEERING COMPLETED JOB ORDER REVISION ON 6-4-2 4 - RTINCHE 6-10-24
23026279600 | RETIRE 339'-8" BSLP | [5 empty] | 1599.81 | 119.4953 | 1480.3147 |  |  |  | #N/A | RETIRED MAIN LINES PURGED AND SEALED SOAP TESTED 10" WC TO VERIFY SHUTDOWN
23026280200 | RETIRE 18570'-2"-16" S&PMP | [5 empty] | 111917.81 | 113891.7734 | -1973.9634 |  |  |  | #N/A | IP 23175576300 2211 - REPAIR LEAK ON MAIN D200007
23026280300 | RETIRE 1107'-2"&8" CS&PHHP | [5 empty] | 2514.99 | 14918.7734 | -12403.7834 |  |  |  | #N/A
23026280600 | RETIRE FENCE | [5 empty] | 0 | 5554.3418 | -5554.3418 |  |  |  | #N/A
23026280700 | RETIRE STATIONS R-1375 | [5 empty] | 1935.34 | 4462.367 | -2527.027 |  |  |  | #N/A
23026283101 | INSTALL 780'-2" PMMP | [5 empty] | 71782.2 | 96018.7749 | -24236.5749 |  |  |  | 2025-05-28
23026289700 | INSTALL 70' OF 3"PMLP MAIN | [5 empty] | 43735.5 | 32180.0533 | 11555.4467 | 2024-01-01 | 2024-12-31 | 2024-02-29 | 2024-03-05
23026284800 | EMER - INSTALL 40'-4" PMLP | [5 empty] | 630.98 | 16339.4428 | -15708.4628 |  |  |  | 2023-07-25 | INSTALLED 34' OF 4" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 10" WC
23026284900 | EMER - RETIRE 40'-4" BSLP | [5 empty] | 451.35 | 139.1159 | 312.2341 |  |  |  | 2023-07-25 | RETIRED 34' OF 4" BS MAIN DUE TO LEAKAGE SOAP TESTED OP TO VERIFY SHUTDOWN SOAP TESTED OP 10" WC
23026289300 | INSTALL 7'-2"&6" PMLP | [5 empty] | 447.65 | 141.4953 | 306.1547 |  |  |  | 2023-08-28
23026290100 | EMER - 3'-3" PMIP | [5 empty] | 5711.96 | 2929.2518 | 2782.7082 |  |  |  | 2023-09-20 | INSTALLED 3' OF 2" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 5 PSIG
23026290200 | EMER-RETIRE 3'-PIP | [5 empty] | 253 | 119.4953 | 133.5047 |  |  |  | 2023-09-20 | CUT OUT 3' OF 2" PL DUE TO HIT MAIN SOAP TESTED TO VERIFY SHUTDOWN AFTER SQUEEZE OP
23026291700 | EMER - INSTALL 3'-4" PMIP | [5 empty] | 2485.01 | 9351.5219 | -6866.5119 |  |  |  | 2023-09-08 | INSTALLED 3' OF 4" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7 PSIG
23026291800 | EMER - RETIRE 3'-4" PIP | [5 empty] | 685.77 | 119.4953 | 566.2747 |  |  |  | 2023-09-08 | RETIRED 3' OF 4" PL DUE TO LEAK ON 4" SF COUPLING SOAP TESTED OP 7 PSIG TO VERIFY ADEQUATE SHUTDOWN
23026294700 | INSTALL 70'-2" PMIP | [5 empty] | 12372.22 | 22819.9245 | -10447.7045 | 2024-01-01 | 2024-12-31 | 2024-01-01 | 2024-01-05 | INSTALLED 74' OF 2" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN AND PURGE POINT CAP OP 8 PSIG
23026292400 | RETIRE 154'-2" CSIP | [5 empty] | 13487.05 | 119.4953 | 13367.5547 |  |  |  | #N/A | INSTALLED WELD CAP TO MAIN SOAP TESTED END CAP AT OP FOR 15 MINS
24026348900 | INSTALL 70'-8" PMMP | [5 empty] | 110389.69 | 134812.2257 | -24422.5357 | 2024-01-01 | 2024-12-31 | 2024-09-27 | 2024-10-07
23026296700 | INSTALL 165' OF 2" PMIP | [5 empty] | 15685.08 | 23912.4752 | -8227.3952 |  |  |  | 2023-12-29 | INSTALLED 157' OF 2" IP MAIN TESTED 90 PSIG 1 HR SOAP TESTED PURGE POINT CAP AND SST CAP OP 7.5 PSIG
23026299800 | PAPER ONLY SL RETIRE | [5 empty] | 0 | 122.9261 | -122.9261 |  |  |  | 2023-06-12
23026299900 | PAPER ONLY SL REPLACEMENT | [5 empty] | 1201.76 | 145.9261 | 1055.8339 |  |  |  | 2023-10-10
23026300000 | INSTALL NEW EQUIPMENT | [5 empty] | 570.56 | 3973.8688 | -3403.3088 |  |  |  | 2023-10-10
19026913000 | INSTALL 730'-2"PMMP | [5 empty] | 242981.39 | 230850.9729 | 12130.4171 | 2024-01-01 | 2024-12-31 | 2024-03-12 | 2024-03-26
23026306800 | INSTALL METER RUN | [5 empty] | 47050.46 | 89187.262 | -42136.802 |  |  |  | #N/A | CCC 94516 CCC 95365 SG 11/4/24 X 1109A
23026307000 | RETIRE METAL BLDG | [5 empty] | 0 | 124.9261 | -124.9261 |  |  |  | 2023-12-01 | TWALKER/KY 12-1-23: THIS BUILDING AND REG STATION RETIRED ON 21-0261546-00.
23026308100 | INSTALL NEW METER | [5 empty] | 7400.08 | 41682.6833 | -34282.6033 |  |  |  | #N/A | CCC 92257 NO CCC NEEDED. COMPLETING CAPITAL PAPERWORK. SG 10/30/24 1235P PER D.ASH NPRV NOT NEEDED SO IT WAS NOT ORDERED OR INSTALLED
24026316400 | EMER-INSTALL CATALYTIC HEATER | [5 empty] | 2159.35 | 3661.3856 | -1502.0356 |  |  |  | #N/A | TWALKER/KY 02-27-24: CORRECTED JOB TO EMER STATUS, MP SYSTEM 32051028 IS SUPPLIED BY REG #1381 AND #1374...REG#1381 HAD TO BE SHUT IN FOR M&R WORK, WITH ONLY ONE REG STATION SUPPLIED MP SYSTEM REQUIRED A CAT HEATER DUE TO FREEZING ISSUE.
24026318800 | ADD SOLAR BACKUP | [5 empty] | 9847.7 | 11051.1928 | -1203.4928 |  |  |  | #N/A | CCC 88756 CCC 90158
24026318900 | RETIRE COMPONENTS | [5 empty] | 0 | 160.3697 | -160.3697 |  |  |  | #N/A
24026319200 | UPGRADE SCADA SYSTEM | [5 empty] | 9821.8 | 11051.1928 | -1229.3928 |  |  |  | #N/A | CCC# 88928
24026319300 | RETIRE SCADA COMPONENTS | [5 empty] | 0 | 160.3697 | -160.3697 |  |  |  | #N/A
24026319400 | UPGRADE SCADA SYSTEM | [5 empty] | 11260.82 | 11051.1928 | 209.6272 |  |  |  | #N/A | CCC# 89146
24026319500 | RETIRE SCADA COMPONENTS | [5 empty] | 23092 | 160.3697 | 22931.6303 |  |  |  | #N/A
24026319800 | UPGRADE SCADA SYSTEM | [5 empty] | 7392.38 | 11051.1928 | -3658.8128 |  |  |  | #N/A | CCC# 89306
24026319900 | RETIRE SCADA COMPONENTS | [5 empty] | 0 | 160.3697 | -160.3697 |  |  |  | #N/A
24026320000 | INSTALL SOLAR BACK UP UNIT | [5 empty] | 6749.45 | 11051.1928 | -4301.7428 |  |  |  | #N/A
24026320200 | UPGRADE SCADA SYSTEM | [5 empty] | 9127.38 | 11051.1928 | -1923.8128 |  |  |  | #N/A
24026320300 | RETIRE SCADA COMPONENTS | [5 empty] | 1185.97 | 160.3697 | 1025.6003 |  |  |  | #N/A
24026320500 | INSTALL ULTRA SONIC METER | [5 empty] | 36964.47 | 47090.3856 | -10125.9156 |  |  |  | #N/A
23026293700 | INSTALL 74'-2" PMMP | [5 empty] | 52073.55 | 102229.172 | -50155.622 | 2024-01-01 | 2024-12-31 | 2024-02-17 | 2024-02-21
24026320900 | EMER RETIRE 5'-3" PIP | [5 empty] | 403.88 | 160.3697 | 243.5103 |  |  |  | #N/A | RETIRED 4' OF 3" PL DUE TO FAILED 3X1 EF ON MAIN SOAP TESED TO VERIFY SHUT DOWN OP 7 PSIG
24026322500 | INSTALL MIWI W/ SOLAR | [5 empty] | 18888.98 | 29494.1928 | -10605.2128 |  |  |  | #N/A | CCC 88309 SG 9/11/24 250P CCC 93309 CCC 93309 CCC 93309 SG 11/1/24 250P CCC 93309 P2P COMPLETED. SG 11/4/24 240P
24026322600 | REITRE FACILITIES | [5 empty] | 0 | 160.3697 | -160.3697 |  |  |  | #N/A
24026323100 | UPGRADE TO FULL TIME | [5 empty] | 7625.67 | 14026.1928 | -6400.5228 |  |  |  | #N/A
24026323200 | RETIRE FACILITIES | [5 empty] | 501.62 | 160.3697 | 341.2503 |  |  |  | #N/A
24026323300 | UPGRADE TO FULL TIME | [5 empty] | 7465.2 | 14026.1928 | -6560.9928 |  |  |  | #N/A
24026323400 | RETIRE FACILITIES | [5 empty] | 722.69 | 160.3697 | 562.3203 |  |  |  | #N/A
24026323500 | UPGRADE TO FULL TIME | [5 empty] | 7331.42 | 14026.1928 | -6694.7728 |  |  |  | #N/A
24026323600 | RETIRE FACILITIES | [5 empty] | 717.61 | 160.3697 | 557.2403 |  |  |  | #N/A
24026323700 | UPGRADE TO FULL TIME | [5 empty] | 7820.77 | 14026.1928 | -6205.4228 |  |  |  | #N/A
24026323800 | RETIRE FACILITIES | [5 empty] | 748.22 | 160.3697 | 587.8503 |  |  |  | #N/A
24026309800 | INSTALL 75' - 2" PMMP | [5 empty] | 21399.98 | 15016.2249 | 6383.7551 | 2024-01-01 | 2024-12-31 | 2024-01-22 | 2024-01-29
24026325200 | INSTALL BYPASS VALVE | [5 empty] | 23298.82 | 30940.8061 | -7641.9861 |  |  |  | #N/A | CCC 73047 NO CCC NEEDED. NO CCC NEEDED. WORK BEING DONE AT GMB LOCATION.
24026325300 | UPGRADE SCADA SYSTEM | [5 empty] | 9037.36 | 10627.0487 | -1589.6887 |  |  |  | #N/A | CCC# 89894
24026325400 | UPGRADE SCADA SYSTEM | [5 empty] | 0 | 121.4465 | -121.4465 |  |  |  | #N/A
24026325500 | UPGRADE SCADA SYSTEM | [5 empty] | 7316.43 | 10627.0487 | -3310.6187 |  |  |  | #N/A
24026325600 | UPGRADE SCADA SYSTEM | [5 empty] | 563.53 | 121.4465 | 442.0835 |  |  |  | #N/A
24026326800 | INSTALL ELECTRINICS | [5 empty] | 8703.66 | 15644.0403 | -6940.3803 |  |  |  | #N/A | CCC 92181
24026326900 | RETIRE ELECTRONICS | [5 empty] | 0 | 118.4933 | -118.4933 |  |  |  | #N/A
24026327400 | INSTALL ELECTRONICS | [5 empty] | 9042.76 | 15644.0403 | -6601.2803 |  |  |  | #N/A | CCC 90038
24026327500 | RETIRE ELECTRONICS | [5 empty] | 0 | 118.4933 | -118.4933 |  |  |  | #N/A
24026327600 | INSTALL ELECTRONICS | [5 empty] | 8257.47 | 15644.0403 | -7386.5703 |  |  |  | #N/A
24026327700 | RETIRE ELECTRONICS | [5 empty] | 1025.99 | 118.4933 | 907.4967 |  |  |  | #N/A
24026328000 | INSTALL ELECTRONICS | [5 empty] | 7483.34 | 15644.0403 | -8160.7003 |  |  |  | #N/A
24026328100 | RETIRE ELECTRONICS | [5 empty] | 431.14 | 118.4933 | 312.6467 |  |  |  | #N/A
24026333201 | EMER - INSTALL 478'-4" PMLP | [5 empty] | 205447.29 | 106609.2647 | 98838.0253 |  |  |  | 2025-02-06
24026333301 | EMER - RETIRE 477'-4" CSLP | [5 empty] | 226.51 | 112.4469 | 114.0631 |  |  |  | #N/A
24026335800 | EMER - INSTALL PF REGULATOR | [5 empty] | 111967.23 | 48662.72 | 63304.51 |  |  |  | #N/A | TWALKER 08-29-24: JOB ORDER OVER RUN DUE TO LP OUTAGE AND LABOR TO RESTORE SERVICE ADDED $40,000 TO COST AND SEGA WAS $20,000 HIGHER THAN EST.
24026335900 | EMER - RETIRE PF REGULATOR | [5 empty] | 0 | 121.4465 | -121.4465 |  |  |  | #N/A
24026333600 | INSTALL 75'-2" PMIP | [5 empty] | 28387.83 | 31694.159 | -3306.329 | 2024-01-01 | 2024-12-31 | 2024-09-02 | 2024-09-12
22026207100 | INSTALL 7870'-2", 4" PMMP | [5 empty] | 1549123.72 | 1271473.5495 | 277650.1705 | 2024-01-01 | 2024-12-31 | 2024-08-05 | 2024-10-28
22026161800 | INSTALL 8" PCF | [5 empty] | 29544.9 | 147.7348 | 29397.1652 | 2024-01-01 | 2024-12-31 | 2024-11-11 | 2024-11-15
24026344400 | EMER-RETIRE 6' OF 4" PAIP | [5 empty] | 0 | 139.7787 | -139.7787 |  |  |  | #N/A
24026337800 | INSTALL 8" SS | [5 empty] | 2650.82 | 151.4465 | 2499.3735 | 2024-01-01 | 2024-12-31 | 2024-04-04 | 2024-04-08
24026347400 | EMER - RETIRE 12'-3" PIP | [5 empty] | 167.95 | 136.633 | 31.317 |  |  |  | #N/A | CUT OUT 2 LEAKING 3X3 CLAMPS AND 2 3" BOLTED COUPLINGS SOAP TESTED TO VERIF Y SHUTDOWN ASFTER SQUEEZE
24026354000 | INSTALL 850' OF 2"PMMP MAIN | [5 empty] | 61100.31 | 37954.6504 | 23145.6596 | 2024-01-01 | 2024-12-31 | 2024-08-05 | 2024-08-26 | COULD NOT INSTALL MAIN LINE ON DOCKSIDE PK. CT. BECAUSE ROAD WAS NOT INSTAL LED AT THIS TIME COMPLETED JOB PR ANDY ELLIOT DEVELLOPER WILL CALL WHEN REA DY, LSHARON 0/26/24
24026349000 | RETIRE 70' OF 10"CSMP MAIN | [5 empty] | 110 | 136.633 | -26.633 |  |  |  | #N/A
24026349500 | INSTALL 40'-12" CSMP | [5 empty] | 237894.26 | 141636.0949 | 96258.1651 |  |  |  | 2025-03-14
24026349600 | RETIRE ~40'-12" CSHP | [5 empty] | 220 | 136.633 | 83.367 |  |  |  | #N/A
22026210901 | INSTALL 8OO' OF 2"PMMP MAIN | [5 empty] | 53441.52 | 49945.6881 | 3495.8319 | 2024-01-01 | 2024-12-31 | 2024-02-06 | 2024-02-20
24026349800 | EMER ABANDON 2' OF 2" PAMP | [5 empty] | 315.69 | 139.7787 | 175.9113 |  |  |  | #N/A | RETIRED 2'' OF 2" PL MP SOAP TESTED 40 PSIG TO VERFIY SQUEEZE OFF SHUTDOWN
23026298800 | INSTALL 900'-2" PMMP MAIN | [5 empty] | 154240.87 | 120091.9279 | 34148.9421 | 2024-01-01 | 2024-12-31 | 2024-03-20 | 2024-04-03
22026231301 | INSTALL 925' OF 2"PMMP MAIN | [5 empty] | 388671.62 | 399340.9217 | -10669.3017 | 2024-01-01 | 2024-12-31 | 2024-09-10 | 2024-09-20 | TWALKER/KY 10-25-24: JOB COST OVER RUN DUE TO CITY OF LEXINGTON REQUIRING MILL/PAVE FOR HIGH STREET WHICH ADDED $80,000 COPY INVOICE IN WMS.DOCS
24026356600 | EMER - RETIRE 2'-2" PIP | [5 empty] | 49.73 | 124.2298 | -74.4998 |  |  |  | #N/A | REITRED 2' OF 2" P MAIN DUE TO FAC DAM SOAP TESTED OP TO VERIFY ADEQUATE SQUEEZE. CWHEELE 9-4-2024
24026358700 | INSTALL 100' OF 2" PMMP MLE | [5 empty] | 24604.17 | 21795.7838 | 2808.3862 |  |  |  | 2025-03-14
24026359401 | INSTALL 200' OF 4" PMIP | [5 empty] | 61986.14 | 49205.4272 | 12780.7128 |  |  |  | 2025-02-27
24026361400 | INSTALL 100' OF 2" PMIP | [5 empty] | 28089.92 | 24014.3917 | 4075.5283 |  |  |  | 2025-03-31
24026362600 | DOCUMENT RTU BUILDING | [5 empty] | 0 | 159.2637 | -159.2637 |  |  |  | #N/A
24026365300 | EMER INSTALL 5" OF 4" PMLP | [5 empty] | 26234.06 | 17482.6388 | 8751.4212 |  |  |  | 2025-01-17 | INSTALLED NEW PL 4" DUE TO CRACKED SF JOINT ON MAIN TESTED 2' OF 4" PL 90 PSIG 0005 MIN SOAP TESTED FINAL CONN OP 10.5" WC
24026365400 | EMER RETIRE 5" OF 4" PALP | [5 empty] | 612.15 | 76.7529 | 535.3971 |  |  |  | #N/A | RETIRED 2' OF 4" PL ALDYL-A DUE TO CRACKED SF COUPLING ON MAIN SOAP TESTED OP 10.5" WC TO VERIFY SHUTDOWN
25026377900 | INSTALL LP FITTING-PAPER ONLY | [5 empty] | 0 | 139.0024 | -139.0024 | 2024-01-01 | 2024-12-31 | 2024-12-17 | 2024-12-17
24026367100 | EMER RETIRE 5'-2" PMMP | [5 empty] | 451.33 | 137.4585 | 313.8715 |  |  |  | #N/A
24026372800 | INSTALL SOLAR BACKUP | [5 empty] | 8466.91 | 9877.4639 | -1410.5539 |  |  |  | #N/A | CCC 107099 AJM 2/13/2025
24026373300 | INSTALL SOLAR BACKUP UNIT | [5 empty] | 7710.91 | 9877.4639 | -2166.5539 |  |  |  | #N/A | INSTALLED SOLAR BACKUP, CCC#108529, DS 02272025
24026373500 | INSTALL SOLAR BACKUP UNIT | [5 empty] | 7634.88 | 9877.4639 | -2242.5839 |  |  |  | #N/A | CCC 107260 AJM 2/14/2025 12:46 PM
24026374100 | INSTALL SOLAR BACKUP UNIT | [5 empty] | 7964.76 | 9877.4639 | -1912.7039 |  |  |  | #N/A | CC 107886 SG 2/21/25 130P
25026381500 | EMER - RETIRE ~870'-3" PIP | [5 empty] | 8256.1 | 3411.7402 | 4844.3598 |  |  |  | #N/A | RETIRED 800' OF MAIN - SOAP TEST END CAP @ OP OK- BHB OK-ABHATFIE 3/14/25
25026381700 | INSTALL 230' OF 2" PMIP | [5 empty] | 89700.18 | 29656.6889 | 60043.4911 |  |  |  | 2025-03-24
25026382400 | INSTALL SCADA EQUIPMENT | [5 empty] | 11519.85 | 20669 | -9149.15 |  |  |  | #N/A
25026392800 | RETIRE MP - PAPER ONLY | [5 empty] | 251.75 | 160.2249 | 91.5251 |  |  |  | #N/A
25026411700 | INSTALL SHORTSTOP TEE | [5 empty] | 0 | 2670.4144 | -2670.4144 |  |  |  | 2025-05-27
18026837600 | INST. FN 176 EXTRA LP OPP | [5 empty] | 59791.79 | 35378.1646 | 24413.6254 |  |  |  | 2021-07-07 | CONTROL SHEET 008281 PAID ON 04/23/20 THURSDAY TO COVER 04/24/20 FRIDAY CONTROL SHEET008307 PAID ON 04/30/20 THURSDAY TO COVER 05/01/20 FRIDAY NOT ON SITE GETTING PARTS FOR JOB CCC# 23134 CCC# 23265 CCC# 23459 CCC# 25857 REGULATORS INSTALLED BY WADE SHIMFESSEL ON 5/13/2021 EC350 INSTALLED BY WADE SHIMFESSEL ON 5/14/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/2021 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS *EXISTING Y STRAINER STRAINER GASKET NOT INSTALLED
18026837700 | RET. FN 176 FOR EXTRA LP OPP | [5 empty] | 0 | 53.9767 | -53.9767 |  |  |  | 2021-07-07 | REGULATORS REPLACED BY WADE SHIMFESSEL ON 5/13/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/2021 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026895200 | RETIRE 2104' 2" P/BSLP | [5 empty] | 100.78 | 103.581 | -2.801 |  |  |  | 2021-01-27
19026895301 | INSTALL 6060' 2" PMMP | [5 empty] | 815947.98 | 549218.5288 | 266729.4512 |  |  |  | 2021-01-27 | JOB ORDER CODED COMPLETE IN ERROR. WILL BE CARRY OVER INTO 2021. SPENDLE OVERRUN EXPLANATION: ADDITIONAL PIPE WAS ADDED LATE INTO PROJECT AND ADDITI ONAL LABOR HOURS CAUSED INCREASE IN SEGA AS WELL AS LATE PAVING COSTS THAT HIT THE PROJECT SBRADY 6/18/21
19026895400 | RETIRE 5072' 2-4" IP | [5 empty] | 0 | 103.581 | -103.581 |  |  |  | 2021-01-27
19026895600 | RETIRE 1516' 2" BS/P/WILP | [5 empty] | 108.73 | 103.581 | 5.149 |  |  |  | 2021-01-27
19026900900 | RETIRE MP TO IP RUN S-1455 | [5 empty] | 152.33 | 690.3419 | -538.0119 |  |  |  | 2021-10-25 | MP TO IP RUN RETIRE ON 1/27/21 BY RYAN VANDERPOOL PAPERWORK DID NOT GET TURNED IN FOR COMPLETION STATION RETIREMENT FIELD VERIFIED ALONG WITH RETIREMENT DATE FROM THE STATION INSPECTION RECORD BY WADE SHIMFESSEL AND JOSH MARTIN ON 10/18/2021 RETIREMENT PAPERWORK COMPLETED BY CYNTHIA FARIS ON 10/25/2021 GCCC TICKET NOT REQUIRED ON 10/25/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK. SETTING BYPASS VALVE AND INLET SETTING VALVE NOT RETIRED THEY ARE TURNED OFF AND BLIND FLANGED CFARIS
19026901000 | RETIRE STATION 1464 | [5 empty] | 2654.56 | 690.3419 | 1964.2181 |  |  |  | 2021-01-11 | JOB CARRIED OVER UNTIL AFTER THE 1ST OF 2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/16/2021 GCCC TICKET NOT REQUIRED ON 2/16/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK 2/16/21 CFARIS
19026901100 | RETIRE STATION 1481 | [5 empty] | 2483.61 | 690.3419 | 1793.2681 |  |  |  | 2021-01-11 | JOB ON HOLD UNTIL AFTER THE 1ST OF 2021
19026901200 | RETIRE STATION 1480 | [5 empty] | 4464.65 | 690.3419 | 3774.3081 |  |  |  | 2021-01-11 | JOB WAS ON HOLD UNTIL AFTER THE 1ST OF 2021
20026918301 | INSTALL ELECTRONICS | [5 empty] | 163427.04 | 179105.9064 | -15678.8664 |  |  |  | 2021-12-22 | GCC# 13951 CCC TICKET #14135 TICKET# 15597 CCC# 49425 REPLACED PUCK IN TRANSMITTER W/NOLL COMPLETED PAPERWORK 12-22-21 JMARTIN
20026931100 | UPGRADE ELECTRONICS | [5 empty] | 265.67 | 3038 | -2772.33 |  |  |  | 2021-11-18 | REPLACED EFC
20026938100 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 |  |  |  | 2021-11-18 | REPLACED EFC
20026942500 | INSTALL I&C EQUIPMENT | [5 empty] | 8341.61 | 16155.4774 | -7813.8674 |  |  |  | 2022-01-10 | ERX INSTALLED BY ACP AND WADE SHIMFESSEL PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/10/22
20026942600 | RETIRE GAUGE | [5 empty] | 0 | 91.4991 | -91.4991 |  |  |  | 2022-01-10 | GAUGE RETIRED AFTER ERX INSTALLED BY WADE SHIMFESSEL PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/10/2022
20026942900 | INSTALL I&C EQUIPMENT | [5 empty] | 11090.78 | 16155.4774 | -5064.6974 |  |  |  | 2022-01-10 | ERX INSTALLED BY ACP AND WADE SHIMFESSEL PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/10/22
20026943000 | RETIRE GAUGE | [5 empty] | 1496.7 | 91.4991 | 1405.2009 |  |  |  | 2022-01-10 | CCC# 49347 COMMISION ERX CCC# 50118 ERX INSTALLED AND GAUGE RETIRED BY WADE SHIMFESSEL PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/10/22
20026973001 | INSTALL 10,000--2" PMMP | [5 empty] | 2896168.82 | 2332285.9866 | 563882.8334 |  |  |  | 2022-06-30 | COST OVERRUN OF $378K DUE TO PROJECT SHUT DOWN AND RESTART OVER WINTER. PR OJECT REQUIRED ADDITIONAL RESOURCES THAT WERE NOT ESTIMATED. COST OVERUN O F $345K IN MATERIALS (PAVING), $124K IN CONTRACT AND $21K IN LABOR. THERE W AS A SAVINGS OF $213K IN OTHER DUE TO ORIGINAL PAVING ESTIMATE BEING CAPTUR ED THERE. THESE ADDITIONAL COSTS CAUSED INCREASE IN SEGA OF $97K. D.LEMONS 10/26/2022
20026973100 | RETIRE 120'-4" BSMP | [5 empty] | 1897.5 | 80.6441 | 1816.8559 |  |  |  | 2022-06-30
20026973200 | RETIRE 10875' BS/CI LP | [5 empty] | 142.7 | 57.6441 | 85.0559 |  |  |  | 2022-06-30
20026973400 | RETIRE STATION R-1452 | [5 empty] | 114.18 | 1281.7771 | -1167.5971 |  |  |  | 2022-06-08 | CCC# 68859 CCC# 68859 RETIRED REGSTATION PER AMRP PROJECT JMARTIN
20026973500 | RETIRE STATION R-1458 | [5 empty] | 1295 | 1281.7771 | 13.2229 |  |  |  | 2022-05-26
20026973700 | INSTALL 6150'-4" PMLP | [5 empty] | 2832541.47 | 2202632.8927 | 629908.5773 |  |  |  | 2022-05-05 | ODOR READS TOOK AT 128 E 3RD ST, MAYSVILLE,KY - WITH SN-16040105 12/17- .6@10:40 - 12/18 .5@16:30 - 12/19 .6@11:30 - 12/20 .5@ 16:29 - 12/21 .5@17:12 - 12/22 .5@16:45 - 12/23 .6@12:27 - TJETT 12/23/21 LEVEL 2 BUDGET VARIANCE COMPLETED AND FILED IN WMSDOCS. D.LEMONS 10/3/2022
20026973800 | RETIRE 6801'-4' CILP | [5 empty] | 1501.61 | 107.2796 | 1394.3304 |  |  |  | 2022-05-05
20026974100 | RETIRE 385'- 3" & 4" | [5 empty] | 2639.76 | 8962.6172 | -6322.8572 |  |  |  | 2022-05-05
20026975000 | INSTALL 150'-2" PMIP | [5 empty] | 12825.26 | 12346.2686 | 478.9914 |  |  |  | 2021-02-08
20026982100 | INSTALL 800'-2" PMIP | [5 empty] | 69244.93 | 47914.5682 | 21330.3618 |  |  |  | 2022-10-17
20026992100 | RETIRE STATION | [5 empty] | 0 | 3400.2343 | -3400.2343 |  |  |  | 2022-04-21 | RETIRED REGULATOR STATION JMARTIN
21026111600 | INSTALL FENCE | [5 empty] | 21225.79 | 2231 | 18994.79 |  |  |  | 2022-10-13 | CCC# 79626 MONITOR FOR FENCE INSTALL. JMARTIN 9-2-22 CCC# 79759 MONITOR FOR FENCE INSTALL
21026118000 | INSTALL 4" SS | [5 empty] | 13617.82 | 29193.606 | -15575.786 |  |  |  | 2021-05-14 | 4"SHORTSTOP INSTALLET BY RLA TESTED AND TAPPED BYCOMPANY 90 PSIG 15 MIN TEST NITROGN AS MEDIUM
21026127000 | INSTALL 8021'-2"&4" PMIP | [5 empty] | 2281682.81 | 1234240.1163 | 1047442.6937 |  |  |  | 2023-06-07
21026127100 | RETIRE 9400'-2"&4" BS&CS | [5 empty] | 1334.61 | 67.799 | 1266.811 |  |  |  | 2023-06-07
21026127200 | INSTALL 2200'-2"&4" PMMP | [5 empty] | 570820.34 | 433097.159 | 137723.181 |  |  |  | 2022-10-31 | COST OVERRUN DUE TO PAVING ESTIMATED IN CONTRACT, BUT CAPTURED IN MISC MATE RIALS WITH A DIFFERENCE OF $32,000. SOME ADDITIOANL MATERIALS WERE REQUIRE D THAT WERE NOT ESTIMATED FOR $6,000. SEGA ALSO INCREASED FOR ADDITIONAL $1 8,000. D.LEMONS 1/31/2023 ADDITIONAL $56,000 TRANSFERED FROM RETIREMENT JO THAT WAS ASSOCIATED WITH A DDITIONAL PAVING. D. LEMONS 2/23/2023
21026127300 | RETIRE 2100'-2"&4" BSMP | [5 empty] | 0 | 75.9523 | -75.9523 |  |  |  | 2022-10-06
21026127400 | INSTALL 1900'-2"&4" PMIP | [5 empty] | 479284.77 | 236888.6644 | 242396.1056 |  |  |  | 2022-11-03 | OVERRUN EXPLANATION LOADED INTO WMSDOCS. D.LEMONS 2/1/2023
21026127500 | RETIRE 1071'-3"&4" WIIP | [5 empty] | 0 | 75.9523 | -75.9523 |  |  |  | 2022-11-03
21026127600 | RETIRE 4700'-4" BSLP | [5 empty] | 0 | 67.1085 | -67.1085 |  |  |  | 2022-10-31
21026134500 | INSTALL 1537'-2"PMIP | [5 empty] | 332303.55 | 208782.1462 | 123521.4038 |  |  |  | 2022-08-26 | SEE PROJECT WORKSPACE 21-81540 FOR PROJECT OVERRUN EXPLANATION. D.LEMONS 10 /26/2022
21026134600 | RETIRE 1053'-2" CSIP | [5 empty] | 0 | 109.7476 | -109.7476 |  |  |  | 2022-08-26
21026139300 | RETIRE STATION R-1455 | [5 empty] | 0 | 1061.1136 | -1061.1136 |  |  |  | 2022-10-04 | RETIRED REG STATION R1455 W 2ND ST MAYSVILLE JMARTIN 10-4-22
21026139400 | REMOVE BUILDING FOR R-1455 | [5 empty] | 3989.86 | 117.5985 | 3872.2615 |  |  |  | 2023-01-18 | BUILDING REMOVED AND CLEANED UP BY PLANT. JMULLINS 1-18-23
21026145800 | REPLACE VALVES ON HP-MP REG | [5 empty] | 33552.7 | 14136.4861 | 19416.2139 |  |  |  | 2022-07-20 | CCC# 73837 CCC# 74028 CCC# 74317 REPLACED INLET, OUTLET, AND BOTH BYPASS VLVS ON STATION. JMARTIN 7/20/22
21026145900 | RETIRE 4 VALVES ON REG STATION | [5 empty] | 1355.49 | 600.4497 | 755.0403 |  |  |  | 2022-07-20 | INSTALLED TEMPORARY REG SETTING REPLACED ALL FOUR SETTING VALVES JMARTIN 07 -20-2022
21026994200 | RETIRE 3" SERVICE | [5 empty] | 0 | 98.6196 | -98.6196 |  |  |  | 2022-04-21
22026159400 | RETIRE S/L | [5 empty] | 2030.55 | 3024.4273 | -993.8773 |  |  |  | 2022-03-21
22026165100 | INSTALL 300'-2" PMIP | [5 empty] | 34102.05 | 29167.1057 | 4934.9443 |  |  |  | 2022-05-18
22026171800 | INSTALL 3178'-2" PMIP | [5 empty] | 830935.96 | 663052.9501 | 167883.0099 |  |  |  | 2023-07-20
22026171900 | RETIRE ~3325'-2" BS,CS & P | [5 empty] | 0 | 83.4538 | -83.4538 |  |  |  | 2023-07-20
22026185400 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 1456 | 5480.5156 | -4024.5156 |  |  |  | 2022-05-17 | JMARTIN REMOVED OLD ERX AND INSTALLED NEW MIWI 350 5-17-2022
22026185500 | RETIRE COMPONENTS | [5 empty] | 715.54 | 124.5156 | 591.0244 |  |  |  | 2022-05-17 | CCC# 67011 NOT ABLE TO COMP AT THIS TIME, HAS OLDER ERX AND NEED MORE PARTS. JMARTIN 5-16-22 CCC# 67183 REPLACE ERX WITH NEW MIWI 350. JMARTIN
22026185600 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 644.24 | 6006.2549 | -5362.0149 |  |  |  | 2022-06-20 | CCC# 70942 INSTALL NEW MIWI 350, P2P W/GAS CONTROL OK, JMARTIN 6-20-22
22026185700 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 93.74 | 124.5156 | -30.7756 |  |  |  | 2022-06-20 | CCC# 70942 RETIRE ERX AND REPLACE WITH MIWI 350, JMARTIN 6-20-22
22026187000 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 1100.73 | 4357.5409 | -3256.8109 |  |  |  | 2022-05-18 | CCC# 67356 REPLACE ERX WITH NEW MIWI 350, P2P OK, JMARTIN CCC# 67669 WORKED TO FIX COMM ISSUE WITH MIWI. CCC# 67669
22026187100 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 0 | 124.5156 | -124.5156 |  |  |  | 2022-05-18 | RETIRED OLD ERX JMARTIN 5/18/2022
22026187400 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 1016.56 | 4773.0565 | -3756.4965 |  |  |  | 2022-05-20 | CCC# 67055 INSTALL NEW MIWI 350, P2P OK, JMARTIN CCC# 67183
22026187500 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 0 | 124.5156 | -124.5156 |  |  |  | 2022-05-20
22026187600 | REPLACE ELECTRONIC COMPONENTS | [5 empty] | 31865.96 | 5349.5438 | 26516.4162 |  |  |  | 2022-05-16 | CCC# 67613 REPLACED ERX WITH NEW MIWI 350. P2P OK, JMARTIN CCC# 67613
22026187700 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 39.46 | 124.5156 | -85.0556 |  |  |  | 2022-05-16 | CCC# 67613 RETIRE ERX JMARTIN
22026195800 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5580.46 | 4801.1928 | 779.2672 |  |  |  | 2022-08-30 | CCC# 79192 INSTALL NEW MIWI 350, P2P COMP. JMARTIN 8-30-22
22026195900 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 69.23 | 124.8731 | -55.6431 |  |  |  | 2022-08-30 | CCC# 79192 INSTALL NEW MIWI 350, P2P COMP. JMARTIN 8-30-22 RETIRED OLD ERX
22026204100 | RETIRE BUILDING | [5 empty] | 0 | 76.9137 | -76.9137 |  |  |  | 2023-01-31 | BUILDING DEMOLISHED BY CONTRACTORS
22026204400 | RETIRE BUILDING | [5 empty] | 0 | 76.9137 | -76.9137 |  |  |  | 2023-01-31 | BUILDING DEMOLISHED BY CONTRACTOR
22026205000 | RETIRE ERX | [5 empty] | 0 | 78.4365 | -78.4365 |  |  |  | 2021-12-22 | COMPLETED PAPERWORK 12-22-21 JMARTIN
22026206200 | INSTALL 33'-2" PMIP | [5 empty] | 37112.14 | 82983.2827 | -45871.1427 |  |  |  | 2022-10-25 | COST UNDERRUN DUE TO PROJECT BEING SIMPLIFIED AFTER START OF CONSTRUCTION. $2000 IN MATERIALS RETURNED AND NOT USED, $26000 IN CONTRACT ESTIMATED BUT NOT USED. ADDITIONAL SAVINGS IN OTHER AND SEGA CATAGORIA ASSOCIATED WITH LO WER COSTS. D. LEMONS 2/23/2023
22026206300 | RETIRE 22'-4" WIIP | [5 empty] | 3252.3 | 83.4538 | 3168.8462 |  |  |  | 2022-10-06
22026209201 | RETIRE BUILDING FOR R-1451 | [5 empty] | 3422.43 | 4594.5704 | -1172.1404 |  |  |  | 2023-03-16
22026222500 | EMER - INSTALL 5'-6" PMMP | [5 empty] | 5673.45 | 5662.1316 | 11.3184 |  |  |  | 2022-09-23
22026222600 | EMER - RETIRE 5'-6" PMMP | [5 empty] | 0 | 74.3089 | -74.3089 |  |  |  | 2022-09-23
23026254100 | RETIRE PRESSURE GAUGE | [5 empty] | 72.46 | 552.5683 | -480.1083 |  |  |  | 2023-02-03 | CCC# 10600 RETIRED PRESSURE CHART. JMARTIN 2-3-23
23026256800 | RETIRE PAPER GAUGE | [5 empty] | 43.28 | 138.8485 | -95.5685 |  |  |  | 2023-03-01 | CCC# 10600 RETIRE PRESSURE CHART, JMARTIN 3-1-23
23026257900 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 1494.37 | 22482.2854 | -20987.9154 |  |  |  | 2023-07-07 | CCC# 36022 INSTALL NEW MIWI 350. JMARTIN JHOBBS 7-5-23 CCC#36022
23026258000 | RETIRE PAPER CHART | [5 empty] | 555.95 | 121.7239 | 434.2261 |  |  |  | 2023-07-05 | CCC# 36022 RETIRED PAPER CHART. JMARTIN JHOBBS 7-5-23 CCC# 36022
23026258300 | INSTALL VRG CONTROLLER | [5 empty] | 41605.07 | 16195.69 | 25409.38 |  |  |  | #N/A | CCC#94028 VAC TRUCK WAS A NO SHOW CCC# 94512 W/VAC TRUCK CCC#94691 WELDED UP THE TAPS CCC#94691 WELDED TAP TEES ON FOR VRGS NOT ONSITE ORDER IS NOT MINE NOT NEEDED CCC#97247 TOOK OUT OLD CONTROLERS AND INSTALLED NEW VRG CONTROLER J HOBBS J BRADFORD 1700 11-18 24 CCC#97247 FINISH UP BACK FILLING 11-19-24 J HOBBS 1150
23026258400 | RETIRE BRISTOL CONTROL UNIT | [5 empty] | 600.77 | 138.8485 | 461.9215 |  |  |  | #N/A | NO TICKET NEEDED HAD TO FIND PARTS 11-15-2023 J HOBBS 1559
23026286900 | HIGHLAND HEIGHTS BREAK METER | [5 empty] | 40214.72 | 103097.3193 | -62882.5993 |  |  |  | #N/A | CCC 88243 NO TICKET NEED. HAD TO TURN IN PAPER WORK OFF SIGHT 9-20-24
23026283600 | INSTALL LP FITTINGS | [5 empty] | 9658.7 | 11183.6093 | -1524.9093 | 2024-01-01 | 2024-12-31 | 10/28/2024/ | 2024-10-28
23026287400 | RETIRE 98'-4" CSMP | [5 empty] | 0 | 136.633 | -136.633 |  |  |  | #N/A
23026302500 | RETIRE PAPER GAUGE | [5 empty] | 994.29 | 989.8688 | 4.4212 |  |  |  | 2023-11-02 | CCC# 50771 MONITOR FOR TC
24026324200 | UPGRADE TO FULL TIME | [5 empty] | 8739.85 | 10901.0487 | -2161.1987 |  |  |  | #N/A | CCC#83588 CCC# 83763 INSTALL SOLAR PANEL AND SWITCH TO CONTINUOUS POLL. JMARTIN 8-7-24
24026324300 | UPGRADE TO FULL TIME | [5 empty] | 92.55 | 121.4465 | -28.8965 |  |  |  | #N/A | CCC# 83763 INSTALLING SOLAR TO MAKE CONTINUOUS POLL, JMARTIN 8-7-24
24026326600 | UPGRADE TO FULL TIME | [5 empty] | 16219.76 | 10901.0487 | 5318.7113 |  |  |  | #N/A | CCC#83806 CCC 83806 CCC# 83806 INSTALL SOLAR FOR CONTINUOUS POLL, JMARTIN 8-7-24
24026326700 | UPGRADE TO FULL TIME | [5 empty] | 142.43 | 121.4465 | 20.9835 |  |  |  | #N/A | CCC# 83806 INSTALL SOLAR FOR CONTINUOUS POLL, JMARTIN 8-7-24
24026340600 | INSTALL LP FITTINGS | [5 empty] | 0 | 5899.0487 | -5899.0487 | 2024-01-01 | 2024-12-31 | 2024-04-25 | 2024-04-25
24026351700 | EMER - RETIRE 2'-2" PMP | [5 empty] | 0 | 136.633 | -136.633 |  |  |  | #N/A
24026356200 | INSTALL NEW 4" CRITICAL VALVE | [5 empty] | 6237.92 | 9922.9586 | -3685.0386 | 2024-01-01 | 2024-12-31 | 2024-09-17 | 2024-09-20 | INST NEW 4" POLY CRITICAL VALVE C16-184 PER ENGINEERED TIE-IN AND GS. TEST NEW VALVE @ 90LB 1HR OK. SOAP TEST TIE-IN @ OP OK. BHB NGF. CO ON 9/19 MCRAIG 9/20/24
24026352900 | RETIRE 4'-3"&4"CSMP | [5 empty] | 2114.27 | 136.633 | 1977.637 |  |  |  | #N/A
24026352800 | INSTALL SS FITTING | [5 empty] | 5512.14 | 24859.1129 | -19346.9729 | 2024-01-01 | 2024-12-31 | 2024-07-29 | 2024-08-01
24026357500 | RETIRE 265'-3" CSMP | [5 empty] | 0 | 124.2298 | -124.2298 |  |  |  | #N/A
24026366400 | INSTALL ~390'-2" PMIP | [5 empty] | 44902.44 | 64432.6111 | -19530.1711 |  |  |  | 2025-03-31
24026373600 | INSTALL SOLAR BACKUP UNIT | [5 empty] | 7104.24 | 9877.4639 | -2773.2239 |  |  |  | #N/A | CCC# 107389. DSASH 2/17/25 1330
18026761400 | INSTALL BULLHORN RMU | [5 empty] | 2699.78 | 3922.4303 | -1222.6503 |  |  |  | 2021-09-30 | RMU WAS INSTALLED ON 09/30/2021 BY TIM SWARTS. SYSTEM SERIAL # IS 132395. -OSS
18026770000 | RETIRE CHART | [5 empty] | 3621.11 | 1613.3811 | 2007.7289 |  |  |  | #N/A | RETIRED MANUAL CHART INSTALLED NEW EC350
18026770100 | RETIRE CHART | [5 empty] | 0 | 1613.3811 | -1613.3811 |  |  |  | 2022-07-07 | RETIRED PAPER CHART MRYAN 07-07-2022
18026847000 | INSTALL CATALYTIC HEATER | [5 empty] | 3779.78 | 3926.2882 | -146.5082 |  |  |  | 2022-07-08 | CC# 49296. 12/21/21 DSASH NO CC# NEEDED, DID NOT GO ON SITE. 12/22/21 DSASH GMB NO CC NEEDED RETIRED OLD CATALYTIC HEATER INSTALLED NEW CATALYTIC HEATER MRAYN 7-8-22
18026847100 | RETIRE CATALYTIC HEATER | [5 empty] | 426.13 | 77.1956 | 348.9344 |  |  |  | 2022-07-08 | RETIRED OLD CATALYTIC HEATER INSTALLED NEW CATALYTIC HEATER MRYAN 7-8-2022
18026847200 | INSTALL CATALYTIC HEATER | [5 empty] | 3110.02 | 3926.2882 | -816.2682 |  |  |  | 2022-07-08 | RETIRED OLD CATALYTIC HEATER AND INSTALLED NEW CATALYTIC HEATER MRYAN 7-8-2022
18026847300 | RETIRE CATALYTIC HEATER | [5 empty] | 313.52 | 77.1956 | 236.3244 |  |  |  | 2022-07-08 | RETIRED CATALYTIC HEATER INSTALLED NEW CATALYTIC HEATER MRYAN 7-8-2022
19026850400 | INSTALL ODORIZATION | [5 empty] | 5241.78 | 6839.1611 | -1597.3811 |  |  |  | #N/A
19026867802 | INSTALL 376'-4" PMIP | [5 empty] | 262651.39 | 112969.7187 | 149681.6713 |  |  |  | 2025-05-16
19026867900 | RETIRE 396'-3" P&CS | [5 empty] | 48.51 | 79.9756 | -31.4656 |  |  |  | #N/A
19026875300 | INSTALL ODORIZER | [5 empty] | 9263.2 | 1300.1611 | 7963.0389 |  |  |  | 2022-09-30 | INSTALLED ODORIZER BOTTLE JMULLINS 9-30-22
19026875400 | INSTALL ODORIZER | [5 empty] | 1315.89 | 1300.1611 | 15.7289 |  |  |  | 2022-09-30 | INSTALLED FARM TAP ODORIZER BOTTLE JMULLINS 9-30-22
20026926200 | INSTALL NETWORK UPGRADE | [5 empty] | 853.47 | 3150 | -2296.53 |  |  |  | 2022-01-12 | SUPER SOLAR KIT AND RV50 INSTALLED BY NOLL DAVIS AND ACP PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/12/22
20026926400 | INSTALL NETWORK UPGRADE | [5 empty] | 7131.29 | 3150 | 3981.29 |  |  |  | 2022-09-09 | GMB NO CC NEEDED GMB NO CC NEEDED NO CC NEEDED--GMB NO CC NEEDED GMB INSTALLED SOAR,BATTERY,AND MODEM PAPERWORK DONE BY J.MULLINS
20026926600 | INSTALL NETWORK UPGRADE | [5 empty] | 6560.17 | 3150 | 3410.17 |  |  |  | 2022-08-29 | NO CC NEEDED GMB INSTALLED NEW SUPER SOLAR KIT MRYAN 8-29-22
20026980000 | INSTALL 675' - 2"/4" PMLP | [5 empty] | 186497.16 | 148515.2952 | 37981.8648 |  |  |  | 2021-03-04 | DUE TO WEATHER CONDITION ON STATE ROAD UNABLE TO MAKE COMMIT DATE OVERRUN EXPLANATION: ALL OPEN CUT WAS ESTIMATED, BUT 108 FEET OF DIRECTIONA L BORE WAS USED. ADDITIONALLY, APPROXIMATELY 4 TIMES AS MUCH FLAGGING WAS R EQUIRED THAN ESTIMATED. OVERHEADS INCREASED $10,500 DUE TO THESE OVERAGES.
20026980100 | RETIRE 622' - 2" BSLP | [5 empty] | 647.77 | 103.8156 | 543.9544 |  |  |  | 2021-03-04
20026991200 | RETIRE BUILDING | [5 empty] | 0 | 107.2796 | -107.2796 |  |  |  | 2021-01-07 | THIS IS PAPER ONLY JOB BUILDING WAS TORN DOWN MANY YEARS AGO THIS JOB IS TO CORRECT CKY RECORDS ONLY FIELD VERIFIED BY CKY ENGINEERING
21026100300 | EMER INS ~15'-2"/3" PMIP/CSIP | [5 empty] | 13138.1 | 15461.5913 | -2323.4913 |  |  |  | 2021-02-17 | 3" C.S. MAIN PULLED LOOSE FROM 4 BOLT COUPLING DUE TO STRESS ON MAIN FROM EXPOSURE DOWN STREAM. TAPPED & STOPPED 3" C.S. REPLACED LEAKING SECTION WITH 3" P 20' PRESSURE TEST 90 PSIG 1HR PURGED MAIN LINE, RESTORED SERVICE.
21026100400 | EMER RETIRE ~5'-3" CSIP | [5 empty] | 1505.21 | 1147.7777 | 357.4323 |  |  |  | 2021-02-11 | 3" CS MAIN PULLED LOOSE FROM 4 BOLT COUPLING DUE TO STRESS ON MAIN FROM EXPOSURE DOWN STREAM. TAPPED & STOP 3" CS MAIN REPLACED LEAKING SECTION WITH 3" P 20' PRESSURE TEST 90PSIG FOR 1 HR. PURGED MAIN & RESTORED SERVICE
21026121900 | INSTALL 100'-2" PMIP | [5 empty] | 30760.67 | 26223.5353 | 4537.1347 |  |  |  | 2021-08-13
21026131400 | INSTALL 300'-2" PMIP | [5 empty] | 158500.46 | 139158.4326 | 19342.0274 |  |  |  | 2021-11-11
21026131500 | RETIRE 300'-2" PMIP | [5 empty] | 39.34 | 88.8156 | -49.4756 |  |  |  | 2021-11-11
21026136300 | INSTALL 37'-2"/3" PMMP/CSMP | [5 empty] | 14615 | 33826.5433 | -19211.5433 |  |  |  | 2021-09-20 | INSTALLED NEW 030 CS AND PE MAIN. TEST @ 90# FOR 1 HR, NO LEAKS. PURGED INT O SERVICE. STOP OFF AND REMOVED OLD MAIN. 3" WELD CAPS & 2" PE CAP SOAP TES T, NO LEAKS. WRAPPED MAIN. SWING TIES & EM BALLS. J HOWARD 9-20-21
21026136400 | RETIRE 29'-2"/3" CSMP/PMMP | [5 empty] | 83.24 | 826.7837 | -743.5437 |  |  |  | 2021-09-13 | LEAK ON END OF STEEL MECH COMP END CAP. INSTALLED NEW 030 & 020 ST AND PE M L, TESTED AT 90# FOR 1 HR. SOAP TEST 030 AND 020 CAPS, NO LEAKS. BAR BANKS, NGF. INSTALLED ANODE, WRAPPED MAIN. J HOWARD 9-13-21
21026142800 | INSTALL 475'-4" PMLP | [5 empty] | 138313.25 | 59783.3635 | 78529.8865 |  |  |  | 2022-04-29 | TTOY-9/20/22: OVERRUN LEVEL 2 VARIANCE EXPLANATION IN WMSDOCS
21026146701 | INSTALL 100'-2" PMIP | [5 empty] | 6197.36 | 40630.8922 | -34433.5322 |  |  |  | 2022-08-30 | VAPIERCE (03/27/23); JOB OVER RUN DUE TO CONTRACT CHARGES ASSOCIATED TO EMERGENCY JOB ORDER 22-0262152-00 EMER-KY FLOODING 2022. $29,900 IN ESTIMATED CONTRACT COSTS AND $0 BOOKED TO THIS JOB ORDER, ALL CONTRACT COSTS WERE CHARGED TO EMER-KY FLOODING 2000 JO. MOST LABOR COSTS WERE ALSO BOOKED UNDER THE EMER JOB ORDER. CONSTRUCTION WAS UNAWARE THIS PLANNED PROJECT OVERLAPPED WITH EMER WORK.
21026994400 | EMER- INSTALL 5'-2" PMIP | [5 empty] | 5176.12 | 7281.2724 | -2105.1524 |  |  |  | 2021-01-13 | INSTALLED 6' NEW 020 MDPE ML. TESTED AT 90# 20 MINS. WELD-IN TRANSITIONS. S OAP TEST TIE IN. PURGED AT EOM. SWING TIES AND ELEC MARKERS. J HOWARD 1-13- 21
21026994500 | EMER- RETIRE 5'-2" BSIP | [5 empty] | 1169.82 | 239.0145 | 930.8055 |  |  |  | 2021-01-11 | INSTALLED 2 020 TDW SS. TAP AND STOP ML. NO UPSTREAM PRESSURE LOSS. REMOVED AND ABANDONED 6' SECTION OF 020 S ML FOR INSTALL OF 020 MDPE. J HOWARD 1-1 1-21
21026997600 | INSTALL 20'-2" PMIP | [5 empty] | 25490.16 | 28869.525 | -3379.365 |  |  |  | 2021-03-31
21026997700 | RETIRE 15'-2" BSIP | [5 empty] | 95.92 | 88.4533 | 7.4667 |  |  |  | 2021-03-30
22026158200 | INSTALL 100'-2" PMMP | [5 empty] | 22688.28 | 26700.5988 | -4012.3188 |  |  |  | 2022-05-06
22026164600 | EMER - INSTALL 220'-2" PMIP | [5 empty] | 49083.09 | 49188.5426 | -105.4526 |  |  |  | 2022-02-22
22026164700 | EMER - RETIRE 20'-4" CSIP | [5 empty] | 140.47 | 109.7476 | 30.7224 |  |  |  | 2022-02-22
22026174700 | EMER- INSTALL 82'-4" PMIP/CSIP | [5 empty] | 85702.82 | 94519.5369 | -8816.7169 |  |  |  | 2022-03-08 | REPAIRED LEAK ON MAIN BY REPLACING A SECTION OF BARE STEEL MAIN WITH 4" PLA STIC TESTED 105 PSIG FOR 1 HOUR WITH ELECTRONIC KUHLMAN GAUGE SERIAL NO 101 09154 3/8/22 REFER TO 2211 JOB ORDER# 22-9840666-00
22026174800 | EMER- RETIRE 76'-4" BSIP | [5 empty] | 0 | 0 | 0 |  |  |  | 2022-03-08
22026175100 | INSTALL 3" OUTLET VALVE | [5 empty] | 44613.77 | 40477.7168 | 4136.0532 |  |  |  | 2023-05-24
22026175200 | RETIRE ~10' - 3" CSHP | [5 empty] | 257.25 | 593 | -335.75 |  |  |  | 2023-05-24
22026179500 | EMER - INSTALL 5'-2" PMIP | [5 empty] | 2346.49 | 5401.378 | -3054.888 |  |  |  | 2022-04-05
22026179600 | EMER - RETIRE 5'-2" P-IP | [5 empty] | 0 | 238.1994 | -238.1994 |  |  |  | 2022-04-05
22026189100 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 2559.49 | 4745.0565 | -2185.5665 |  |  |  | 2022-06-29 | CC # 70264 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-29-2022
22026189200 | RETIRE ELECTRONIC EQUIPMENT | [5 empty] | 213.04 | 124.5156 | 88.5244 |  |  |  | 2022-06-29 | CC # 70264 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-29-2022
22026189300 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 487.15 | 4745.0565 | -4257.9065 |  |  |  | 2022-06-14 | CC# 70358 RETIRED BOTH ERX'S INSTALLED NEW MIWI350 MRYAN 6-14-2022
22026189400 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 243.32 | 124.5156 | 118.8044 |  |  |  | 2022-06-14 | CC # 70358 RETIRED OLD ERX'S INSTALLED NEW MIWI350 MRYAN 6-14-2022
22026189500 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 292.29 | 4745.0565 | -4452.7665 |  |  |  | 2022-06-15 | CC # 70566 RETIRED OLD ERX INSTALLED NEW HONEYWELL MIWI350 MRYAN 6-15-2022
22026189600 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 91.82 | 124.5156 | -32.6956 |  |  |  | 2022-06-15 | CC # 70566 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 06-15-2022
22026189700 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 91.91 | 4745.0565 | -4653.1465 |  |  |  | 2022-06-15 | CC # 70497 RETIRED OLD ERX INSTALLED NEW MIW350 MRYAN 06-15-2022
22026189800 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 213.04 | 124.5156 | 88.5244 |  |  |  | 2022-06-15 | CC # 70497 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-15-2022
22026189900 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 275.74 | 4745.0565 | -4469.3165 |  |  |  | 2022-06-30 | CC # 72215 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6/30/2022
22026190000 | RETIRED ELECTRONICS EQUIPMENT | [5 empty] | 61.53 | 124.5156 | -62.9856 |  |  |  | 2022-06-30 | CC # 72215 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6/30/2022
22026191100 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 1925.69 | 4801.1928 | -2875.5028 |  |  |  | 2022-06-27 | CC # 71822 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-27-2022
22026191200 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 229.57 | 124.8731 | 104.6969 |  |  |  | 2022-06-27 | CC # 71822 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-27-2022
22026191500 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 1457.43 | 4801.1928 | -3343.7628 |  |  |  | 2022-08-16 | UPGRADED ERX TO MIWI
22026191600 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 447.49 | 124.8731 | 322.6169 |  |  |  | 2022-08-16 | CC # 73221 UPGRADDED ERX TO MIWI
22026192700 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 780.12 | 4801.1928 | -4021.0728 |  |  |  | 2022-06-28 | CC # 71922 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-28-2022
22026192800 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 82.66 | 124.8731 | -42.2131 |  |  |  | 2022-06-28 | CC # 71984 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-28-2022
22026193200 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 271.17 | 4801.1928 | -4530.0228 |  |  |  | 2022-06-28 | CC # 71922 RETIRED OLD ERX INSTALLED NEW MIWI 350 MRYAN 6/28/2022
22026193300 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 156.09 | 124.8731 | 31.2169 |  |  |  | 2022-06-28 | CC # 71922 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6/28/2022
22026193400 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 1938.82 | 4801.1928 | -2862.3728 |  |  |  | 2022-08-17 | CC # 75237 NO CC NOT ONSITE PAPERWORK NO CC NEEDED UPGRADDED ERX TO MIWI JMULLINS
22026193500 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 22.08 | 124.8731 | -102.7931 |  |  |  | 2022-08-17 | CC # 75237
22026193600 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 1911.78 | 4801.1928 | -2889.4128 |  |  |  | 2022-10-18 | CC # 3865 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 10-18-22
22026193700 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 217.55 | 124.8731 | 92.6769 |  |  |  | 2022-10-18 | CC # 3865 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 10-18-22
22026193800 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 1577.79 | 4801.1928 | -3223.4028 |  |  |  | 2022-08-08 | CC # 73511
22026193900 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 235.52 | 124.8731 | 110.6469 |  |  |  | 2022-08-08 | CC # 73511 UPGRADED TO MIWI JOSH MULLINS
22026194000 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 1673.13 | 4801.1928 | -3128.0628 |  |  |  | 2022-08-08 | CC # 73511 UPGRADED FROM ERX TO MIWI JOSH MULLINS
22026194100 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 230.5 | 124.8731 | 105.6269 |  |  |  | 2022-08-08 | CC # 73511
22026194200 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 1788.47 | 4801.1928 | -3012.7228 |  |  |  | 2022-08-08 | CC # 73334
22026194300 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 470.99 | 124.8731 | 346.1169 |  |  |  | 2022-08-08 | CC # 73334 UPDATTED ERX TO MIWI 07-13-22 J. MULLINS
22026194400 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 356.51 | 4801.1928 | -4444.6828 |  |  |  | 2022-06-30 | CC # 72268 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-30-2022
22026194500 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 1.84 | 124.8731 | -123.0331 |  |  |  | 2022-06-30 | CC # 72268 RETIRED OLD ERX INSTALLED NEW MIWI 350 MRYAN 6-30-2022
22026196000 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 6078.6 | 4801.1928 | 1277.4072 |  |  |  | 2022-07-27 | CC # 75237 RETIRED OLD ERX AND INSTALLED NEW HONEYWELL MIWI350 MRYAN 7-27-2022
22026196100 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 232.52 | 124.8731 | 107.6469 |  |  |  | 2022-07-27 | CC # 75237 RETIRED OLD ERX INSTALLED NEW HONEY WELL MIWI350 MATT RYAN 7-27-2022
22026209100 | RETIRE METER | [5 empty] | 1187.88 | 136.5602 | 1051.3198 |  |  |  | #N/A | NO CC NEEDED---GMB ACCOUNT MCR 10-6-23 1600 METER READY TO BE REMOVED INLET OUTLET BLIND FLNGD
22026216500 | EMER-INSTALL 2"/4" POLY VALVES | [5 empty] | 433396.83 | 298130.9642 | 135265.8658 |  |  |  | 2022-08-11 | COMPLETED OVERRUN EXPLANATION FORM LOADED INTO WMSDOCS JO WORKSPACE. D.LEMO NS 2/24/2023
22026216600 | EMER-RETIRE 7'-2"/4" PMIP/CSIP | [5 empty] | 0 | 83.4538 | -83.4538 |  |  |  | 2022-08-11
22026216700 | EMER - INSTALL 456'-4" CS/PMIP | [5 empty] | 85192.39 | 50625 | 34567.39 |  |  |  | 2022-11-09
22026216801 | EMER-RETIRE 130'-4" CS/BS/PIP | [5 empty] | 439.01 | 132.427 | 306.583 |  |  |  | 2022-11-09
22026218600 | INSTALL NEW 1ST CUT REGULATOR | [5 empty] | 3338.51 | 2521.2589 | 817.2511 |  |  |  | 2023-11-06 | NOT ONSITE NO CC NEEDED GETTING MATERIAL/BUILDING REG PREPING FOR JOB MCR CC # 51243 INSTALLD NEW 1ST CUT REG DUE TO CORROSION MCR 11-6-23 1445 CC # 51776 ISTALLD TUBING ANF PAINTED SETTIN FIELD WORK COMPLETE
22026218700 | RETIRE 1ST CUT REGULATOR | [5 empty] | 1644.86 | 84.9152 | 1559.9448 |  |  |  | 2023-11-06 | CC # 51243 REMOVED OLD FIRST CUT REG MCR 11-6-23 1030
22026218900 | INSTALL NEW METER | [5 empty] | 17499.51 | 6441.3422 | 11058.1678 |  |  |  | #N/A | CCC NOT NEEDED--GMB MCR 6-18-24 1500
22026241900 | INSTALL 249'-2" PMIP | [5 empty] | 101153.64 | 81974.2921 | 19179.3479 |  |  |  | 2023-03-15
22026242000 | RETIRE 135'-3" BSIP | [5 empty] | 139.7 | 117.5985 | 22.1015 |  |  |  | 2023-03-15
23026256300 | INSTALL 130'-2" PMIP | [5 empty] | 19141.35 | 38002.449 | -18861.099 |  |  |  | 2023-07-21
23026261300 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 4877.76 | 26706.2854 | -21828.5254 |  |  |  | 2023-07-10 | CC # 36552 INSTALLD MIWI NO CC NOT ONSITE--PAPER WORK
23026261400 | RETIRE PAPER CHART | [5 empty] | 0 | 121.7239 | -121.7239 |  |  |  | 2023-07-10
23026261500 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 4069.95 | 26706.2854 | -22636.3354 |  |  |  | 2023-07-11 | CC # 36725 NO CC NEEDED---GMB ACCOUNT NOT ON SITE NO CC NEEDED---PAPERWORK OFF SITE CC # 40724
23026261600 | RETIRE PAPER CHART | [5 empty] | 388.77 | 121.7239 | 267.0461 |  |  |  | 2023-07-11 | CC # 36725
23026265300 | INSTALL PILOT REGULATORS | [5 empty] | 9398.99 | 7328.1838 | 2070.8062 |  |  |  | #N/A
23026274600 | EMER - INSTALL 5'-2" PMIP | [5 empty] | 2867.86 | 11073.0623 | -8205.2023 |  |  |  | 2023-05-11
23026274700 | EMER - INSTALL 5'-2" PM | [5 empty] | 0 | 116.0664 | -116.0664 |  |  |  | 2023-05-11
23026275800 | INSTALL NEW BATTERY/EQUIPMENT | [5 empty] | 135.94 | 2819.6093 | -2683.6693 |  |  |  | 2023-05-23
23026275900 | RETIRE BATTERY FACILITY | [5 empty] | 0 | 139.1159 | -139.1159 |  |  |  | 2023-05-17
23026282000 | INSTALL 40'-4" PMIP | [5 empty] | 49257.58 | 63454.1516 | -14196.5716 |  |  |  | 2023-07-18
23026282100 | RETIRE 36'-4" BSIP | [5 empty] | 124.74 | 139.1159 | -14.3759 |  |  |  | 2023-07-18
23026291200 | EMER - INSTALL 8'-3" PMIP | [5 empty] | 51206.39 | 32593.7477 | 18612.6423 |  |  |  | 2023-09-08 | INSTALLED 3INCH PLASTIC MAIN SECTION TO REPLACE LEAKING 3 INCH BS MAIN JCK 9.8.23
23026291300 | EMER - RETIRE 7'3" BS&P | [5 empty] | 392.93 | 119.4953 | 273.4347 |  |  |  | 2023-09-08 | ABANDON LEAKING METAL MAIN. INSTALLED 3 INCH PLASTIC MAIN JCK 9.8.23
23026302100 | RETIRE PAPER GAUGE | [5 empty] | 306.23 | 989.8688 | -683.6388 |  |  |  | 2023-10-13
23026302200 | RETIRE PAPER GAUGE | [5 empty] | 1131.38 | 989.8688 | 141.5112 |  |  |  | 2023-12-04
23026306500 | INSTALL DRIP TANK | [5 empty] | 22554.83 | 21571.6224 | 983.2076 |  |  |  | #N/A | NO CC NEEDED NOT ONSITE-- GATHERIN MATERIAL TO INSTALL MCR 2-5-24 1600 NO CC NEEDED CC # 57053 MCR 2-6-24 1600 CC # 57053 CC 57053 NO CC NEEDED. MATERIAL PICKUP. CC # 57053 DRIP INSTALLED MCR 2-15-2024 1500 CC # 50753
24026310400 | INSTALL VALVE & 5' OF 2" PMMP | [5 empty] | 10413.42 | 11731.9279 | -1318.5079 | 2024-01-01 | 2024-12-31 | 2024-02-06 | 2024-02-07
24026311300 | EMER - INSTALL 2" 461S | [5 empty] | 2699.35 | 2282.9666 | 416.3834 |  |  |  | #N/A | CC # 57053 INSTLLD REGS MCR 1-22-24 1330 CC 57053 NO CC NEEDED NOT ONSITE-- CO PAPERWORK TO SEND TO WADE MCR 1-26-24 1000 NO CC NEEDED NOT ONSITE PAPAER WORK OFF SITE MCR 2-5-24 1205
24026311400 | EMER - RETIRE 2" MOONEYS | [5 empty] | 721.94 | 59.4493 | 662.4907 |  |  |  | #N/A | CC # 57053 REMOVED MOONEYS MCR 1-22-24 1030 CC 57053
24026317900 | EMER - RETIRE 5'-2" PIP | [5 empty] | 162.78 | 160.3697 | 2.4103 |  |  |  | #N/A
24026320600 | INSTALL ERX BATTERY | [5 empty] | 2726.43 | 3894.6442 | -1168.2142 |  |  |  | #N/A
24026320700 | RETIRE ERX BATTERY | [5 empty] | 0 | 160.3697 | -160.3697 |  |  |  | #N/A
24026342600 | EMER ABANDON 200' OF 2" BSIP | [5 empty] | 5344.92 | 7907.5865 | -2562.6665 |  |  |  | #N/A
24026345800 | INSTALL 1400'-2" PMIP | [5 empty] | 263557.02 | 300748.5042 | -37191.4842 |  |  |  | 2025-04-02
24026345900 | RETIRE 1200'-2"/4" PA/BS/CS IP | [5 empty] | 0 | 76.7529 | -76.7529 |  |  |  | #N/A
22026183301 | SMRP INSTALL 1120' 8-12" CSHP | [5 empty] | 1650295.52 | 1201596.3067 | 448699.2133 | 2024-01-01 | 2024-12-31 | 2024-01-01 | 2024-03-06
24026347700 | EMER -RETIRE 7'-2" PMIP | [5 empty] | 0 | 136.633 | -136.633 |  |  |  | #N/A
24026362700 | INSTALL EC-350 FOR GMB | [5 empty] | 0 | 159.2637 | -159.2637 |  |  |  | #N/A | INSTALLED EC350 REPLACE MANUAL CHART
24026367700 | INSTALL NEW EC-350 UNIT | [5 empty] | 706.81 | 6063.7288 | -5356.9188 |  |  |  | #N/A | CCC NOT NEEDED GMB ACCNT MCR 11-8-24 1530 INSTALLED NEW EC350
24026367800 | RETIRE EME UNIT | [5 empty] | 379.26 | 135.7529 | 243.5071 |  |  |  | #N/A | CCC NOT NEEDED GMB ACCNT MCR 11-8-24 1100 RETIRED MINI AT INSTALLED NEW EC350
24026375700 | INSTALL FLOAT SWITCH | [5 empty] | 1897.47 | 2988.4639 | -1090.9939 |  |  |  | #N/A | CCC 108219 INSTALLED FLOAT SWITCH WITH ACP 2-25-25 1300 TAX DISTRICT IS INCORRECT IN WMS, MAPPED CORRECTLY IN GIS. PER SYLVIA MORRISON LEAVE AS IS FOR NOW, FCA WILL BE NEEDED IN FUTURE CORRECT TAXING DISTRICT IS 1957702
24026375800 | INSTALL FLOAT SWITCH | [5 empty] | 2733.24 | 2988.4639 | -255.2239 |  |  |  | #N/A | CCC 108219 INSTLLD FLOAT SWITCH WITH ACP MCR 2-2-5-25 1200
24026375900 | INSTALL FLOAT SWITCH | [5 empty] | 2210.8 | 2988.4639 | -777.6639 |  |  |  | #N/A | CCC 108219 INSTLLD FLOAT SWITCHES WITH ACP MCR 2-25-25 1530
25026394000 | EMER INSERT 280'-1.2" PMIP | [5 empty] | 2217.44 | 34665.9445 | -32448.5045 |  |  |  | 2025-03-10 | INSERTED 280' 1.25" PMIP INTO 2" CASING. TOTAL INSTALL 287'. TESTED AT 90 P SIG FOR 20 MINS W/ FOL APPROVAL. EM BALLS AND TWS INSTALLED. OTHER JOB ORDE R FOR RETIRE 25026394100. J HOWARD 3-10-25
25026394100 | EMER - RETIRE 284'-2"BSIP | [5 empty] | 19.19 | 181.0849 | -161.8949 |  |  |  | #N/A | ABND 284FT OF 020 S. 268FT USED FOR CASING OF 280FT OF 0125 CARRIER PIPE. I NSTALL JOB ORDER 25026394000. J HOWARD 3-10-25
25026396000 | INSTALL CAT HEATER | [5 empty] | 0 | 8040.0756 | -8040.0756 |  |  |  | #N/A | CCC# 107424 2/17/25 JAMES PASLEY
25026396100 | RETIRE CAT HEATER | [5 empty] | 0 | 160.2249 | -160.2249 |  |  |  | #N/A
25026398400 | EMER - INSTALL FITTINGS | [5 empty] | 6860.25 | 11221.5028 | -4361.2528 |  |  |  | 2025-03-24
25026398500 | EMER - RETIRE 50'-4" CSIP | [5 empty] | 0 | 160.2249 | -160.2249 |  |  |  | #N/A
Formulas:
Date Actual End = VLOOKUP([Project No.],'WMS JO Data'!$D20:BD27974,25,FALSE)

## 2025 (hidden)
Columbia Gas of Kentucky Case No. 2026-00099 Attachment A Construction Projects For 5 years ended December 31, 2025
Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End | Job Order Comments
18026757700 | INSTALL MI WIRELESS EFC | [5 empty] | 14191.42 | 13926.0597 | 265.3603 |  |  |  | 2022-11-07 | INSTALLED HONEYWELL ERX SUPER SOLAR KIT J MULLINS 11-7-22
18026757800 | RETIRE RECORDING GAUGE | [5 empty] | 0 | 73.0037 | -73.0037 |  |  |  | 2022-11-07 | RETIRED CHART INSTALLED HONEYWELL ERX JMULLINS 11-7-22
18026807000 | INST. FN 115 EXTRA LP OPP | [5 empty] | 28771.63 | 24102.8722 | 4668.7578 |  |  |  | 2021-05-12 | GCCC# 11422 CHARED TIME TO COLLECT MATERIAL. DID NOT VISIT SITE NO GCCC TICKET REQUIRED CMCOC 3/3/21 GCCC# 13985 CMCHOLAN 3-4-2021 CCC#13985 REGULATOR AND ER350 INSTALLED BY CHRIS COX ON 3/4/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026807100 | RET. FN 115 FOR EXTRA LP OPP | [5 empty] | 2550 | 54.9718 | 2495.0282 |  |  |  | 2021-05-12 | REGULATOR REPLACED BY CHRIS COX ON 3/4/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026808800 | INST. FN 259 EXTRA LP OPP | [5 empty] | 258499.79 | 23795.1646 | 234704.6254 |  |  |  | 2021-08-02 | NOT ONSITE. NO GCCC TICKET REQUIRED. CMCOX 7/6/21 GCCC# 30701 CMCOX 7/7/21 NOT ONSITE. NO GCCC TICKET REQUIRED. CMCOX 7/8/21 CCC# 31111 GCCC# 31231 CMCOX 7/13/21 GCCC# 31380 GCCC# 31536 GCCC# 31616 DID NOT ENTER PIT. NO GCCC# REQUIRED. CMCOX 7/19//21 GCCC# 31756 CMCOX 7/20/21 CC# 32093 REGULATORS INSTALLED BY CHRIS COX 7/27/21 PAPERWORK COMPLETED BY CFARIS 7/29/21 CCC# NOT REQUIRED BY CFARIS ON 7/29 OR 8/2 NOT AT STATION
18026808900 | RET. FN 259 FOR EXTRA LP OPP | [5 empty] | 0 | 53.9767 | -53.9767 |  |  |  | 2021-07-29 | REGULATORS REPLACED BY CHRIS COX ON 7/27/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/29/2021 GCCC TICKET NOT REQUIRED ON 7/29/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026843301 | INSTALL 3000' OF 4/6/8"PMLP | [5 empty] | 1711065.31 | 1495308.5734 | 215756.7366 |  |  |  | 2022-09-09
18026843400 | RETIRE 2670' OF 3"/6"CILP MAIN | [5 empty] | 598.25 | 81.035 | 517.215 |  |  |  | 2022-09-12
18026848701 | STATION UPGRADES (SEP RELATED) | [5 empty] | 206545.63 | 151848.4602 | 54697.1698 |  |  |  | 2022-12-15 | CCC 22581 CCC 23126 CCC 23442 CCC 24345 CCC 25855 CCC 26071
19026889001 | INSTALL 28'-8" PMLP | [5 empty] | 30769.7 | 17790.2899 | 12979.4101 |  |  |  | 2021-04-19
20026927900 | UPGRADE ELECTRONICS | [5 empty] | 3660.91 | 3038 | 622.91 |  |  |  | 2022-03-02 | EFC REPLACED BY C. COX ON 3-1-22 PAPERWORK CO BY J MULLINS ON 3-2-22
20026928000 | UPGRADE ELECTRONICS | [5 empty] | 7833.1 | 3038 | 4795.1 |  |  |  | 2021-10-04 | REPLACED EFC AND UPSIZED METER TO 16M ALSO WORKED TP AND MGRP WHILE ON SITE
20026928100 | UPGRADE ELECTRONICS | [5 empty] | 6063.75 | 3038 | 3025.75 |  |  |  | 2021-11-16 | REPLACED EFC
20026928200 | UPGRADE ELECTRONICS | [5 empty] | 3460.63 | 3038 | 422.63 |  |  |  | 2022-07-14 | CMCHOLAN 7-14-2022 RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07-14-2022
20026928300 | UPGRADE FROM 3G NETWORK | [5 empty] | 6815.37 | 3038 | 3777.37 |  |  |  | 2022-02-28 | RETIRED OLD EFC INSTALLED NEW EC350 CCOX 02-28-2022
20026928400 | UPGRADE FROM 3G NETWORK | [5 empty] | 3177.17 | 3038 | 139.17 |  |  |  | 2022-07-14 | RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07-14-2022
20026928500 | UPGRADE ELECTRONICS | [5 empty] | 3667.3 | 3038 | 629.3 |  |  |  | 2022-07-19 | CWEMPE BLONE 7/19/22 RETIRED MINI-AT INSTALLED NEW EC350 CWEMPE 07-19-2022
20026928600 | UPGRADE ELECTRONICS | [5 empty] | 3158.07 | 5626 | -2467.93 |  |  |  | 2022-07-14 | RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON
20026928700 | UPGRADE ELECTRONICS | [5 empty] | 8043.8 | 3038 | 5005.8 |  |  |  | 2021-10-25 | REPLACED EFC
20026928800 | UPGRADE ELECTRONICS | [5 empty] | 6614.01 | 3038 | 3576.01 |  |  |  | 2022-03-02 | ASSIST SMCHOLAN 03-02-2022 RHAYES ASSIST SMCHOLAN 03-02-2022 RHAYES INSTALLED NEW EC350 SOAP TEST TUBING 5MIN OPP PRESSURE SMCHOLAN 3-2-22
20026933700 | RETIRE ELECTRONICS | [5 empty] | 452.45 | 73.3494 | 379.1006 |  |  |  | 2022-03-02 | GAUGE RETIRED BY C. COX PAPPER WORK CO BY J. MULLINS 3-2-2022
20026933800 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 |  |  |  | 2021-11-16 | REPLACED EFC
20026933900 | RETIRE ELECTRONICS | [5 empty] | 1039.15 | 73.3494 | 965.8006 |  |  |  | 2022-07-14 | CMCHOLAN 7-14-2022 RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07142022
20026934000 | RETIRE ELECTRONICS | [5 empty] | 626.57 | 73.3494 | 553.2206 |  |  |  | 2022-02-28 | RETIRED OLD EFC AND INSTALLED NEW EC350 CCOX 02-28-2022
20026934100 | RETIRE ELECTRONICS | [5 empty] | 189.27 | 73.3494 | 115.9206 |  |  |  | 2022-07-14 | RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07-14-2022
20026934200 | RETIRE ELECTRONICS | [5 empty] | 502.89 | 73.3494 | 429.5406 |  |  |  | 2022-07-19 | CWEMPE BLONE 7/19/22 RETIRED OLD MINI-AT INSTALLED NEW EC350
20026934400 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 |  |  |  | 2021-10-25 | REPLACED EFC
20026934500 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 |  |  |  | 2022-03-02 | RETIRED MINI-AT INSTALLED NEW EC350 SMCHOLAN 3-2-22
20026940000 | INSTALL I&C EQUIPMENT | [5 empty] | 11589.34 | 16155.4774 | -4566.1374 |  |  |  | 2022-02-24 | CCC# 43689 RETIRED PAPER CHART INSTALLED NEW ERX CCOX 02-24-2022
20026940100 | RETIRE PAPER GUAGE | [5 empty] | 172.3 | 91.4991 | 80.8009 |  |  |  | 2022-02-24 | RETIRED PAPER CHART INSTALLED HONEYWELL ERX CCOX 2-24-2022
20026941400 | INSTALL I&C EQUIPMENT | [5 empty] | 12022.54 | 16155.4774 | -4132.9374 |  |  |  | 2022-07-28 | INSTALLED TAP ON OUTLET LEG OF RUN 1 20# SYSTEM AND RAN SENSE LINES TO ERX FROM THE NEW TAP AND EXISTING HP SENSE LINE, AND COMMISSIONED ERX CCC 75328, CMCHOLAN CCOX 7-28-2022
20026943300 | INSTALL I&C EQUIPMENT | [5 empty] | 9146.19 | 16155.4774 | -7009.2874 |  |  |  | 2022-05-27 | REMOVED BOTH PAPER CHARTS INSTALLED ERX FOR IP AND MP CMCHOLAN 4-14-2022 CC 65476 COMMISSIONED ERX RHAYES SMCHOLAN 05-03-2022 COMMITIONED ERX, PSP OK, CCC 65476 CMCHOLAN RHAYES 5-3-2022
20026943400 | RETIRE GAUGE | [5 empty] | 543.13 | 91.4991 | 451.6309 |  |  |  | 2022-05-27 | REMOVED BOTH PAPER CHARTS INSTALLED ERX CC 62655 RHAYES SMCHOLAN CCOX EBLANTON 04-14-2022
20026945201 | INSTALL 5000' OF 2"PMMP MAIN | [5 empty] | 228201.9 | 223484.8945 | 4717.0055 |  |  |  | 2021-02-16 | INSTALLED 4938"020 PMMP.
20026951300 | INSTALL 6200' OF 2"PMMP MAIN | [5 empty] | 1175556.48 | 1180648.1173 | -5091.6373 |  |  |  | 2021-05-17
20026951400 | RETIRE 7600' OF 4"CI/BSLP MAIN | [5 empty] | 142.7 | 165.7874 | -23.0874 |  |  |  | 2021-05-17
20026951802 | INSTALL 3980' OF 2"PMMP MAIN | [5 empty] | 461944.16 | 383869.9188 | 78074.2412 |  |  |  | 2021-05-07 | TWALKER/KY 09-21-21: JOB OVER RUN DUE TO ADDITIONAL STREET AND HARD SURFACE REPAIR ADDED $70,000 TO CONTRACT COST AND SEGA WAS $7000 HIGHER THAN ESTIMA TE.
20026951900 | RETIRE 2100' OF 4"CI/PLP MAIN | [5 empty] | 0 | 84.1799 | -84.1799 |  |  |  | 2021-05-07
20026955503 | INSTALL 2850'-8" CSHP | [5 empty] | 1263938.35 | 1308080.823 | -44142.473 |  |  |  | 2021-11-30
20026955600 | RETIRE 6100'-8"/3" BS/CSHP | [5 empty] | 142.7 | 190.2592 | -47.5592 |  |  |  | 2021-11-30
20026955701 | INSTALL 3,945'-4"/2" PMMP | [5 empty] | 702217.99 | 724040.648 | -21822.658 |  |  |  | 2021-12-20
20026955800 | RETIRE 216'-2" PMMP | [5 empty] | 0 | 85.5775 | -85.5775 |  |  |  | 2021-12-17
20026955901 | INSTALL 215'-4" PMMP | [5 empty] | 63490.92 | 67929.8606 | -4438.9406 |  |  |  | 2021-12-20
20026956000 | RETIRE 820'-2" PMMP | [5 empty] | 0 | 85.0089 | -85.0089 |  |  |  | 2021-12-20
20026956101 | INSTALL 2475'-8"/6"/4" PMLP | [5 empty] | 1344804.09 | 1170137.3307 | 174666.7593 |  |  |  | 2021-12-20 | WIPE SAMPLE RESULTS WERE ENTERED ON THE INSTALL JOB INSTEAD OF THE RETIREMENT JOB. RETIREMENT RESULTS WERE ENTERED HERE.
20026956200 | RETIRE 4775'-12">3"PM/BS/CSLP | [5 empty] | 160 | 85.5775 | 74.4225 |  |  |  | 2021-12-20
20026966800 | RETIRE 2800' OF 4"/6"BSLP MAIN | [5 empty] | 907.78 | 90.1729 | 817.6071 |  |  |  | 2021-02-04
20026969700 | INSTALL 8500' OF 2"/4"PMMP MN | [5 empty] | 270941.08 | 301857.4038 | -30916.3238 |  |  |  | 2021-01-08
20026971100 | INSTALL 3300' OF 2"/4"PMMP MN | [5 empty] | 755817.87 | 877421.2279 | -121603.3579 |  |  |  | 2022-03-18 | TWALKER/KY 05-04-22: JOB ORDER RUN DUE TO NO PAVING/HARD SURFACE REPAIRS HA VE BEEN STARTED AT THIS TIME. THIS IS JOINT PAVING RESTORATION WITH CITY OF LEXINGTON AND KY AMERICAN WATER. LOOK FOR COST TO BOOK LATE SUMMER 2022
20026971200 | RETIRE 2100' OF 3"BSLP MAIN | [5 empty] | 1415.61 | 102.0836 | 1313.5264 |  |  |  | 2022-03-18
20026972201 | INSTALL 3300' OF 2"/4" PMMP | [5 empty] | 84926.85 | 89953.3001 | -5026.4501 |  |  |  | 2021-11-04
20026975201 | INSTALL 3000' OF 2"/4"PMMP | [5 empty] | 630664.21 | 552556.8312 | 78107.3788 |  |  |  | 2021-06-11
20026975300 | RETIRE 1900' OF 6"BSLP MAIN | [5 empty] | 1430.35 | 64.0836 | 1366.2664 |  |  |  | 2021-06-11
20026976301 | INSTALL 6300' OF 2"/4"PMMP | [5 empty] | 2104702.57 | 2132943.4537 | -28240.8837 |  |  |  | 2021-12-15
20026976400 | RETIRE 6100' OF 3"/4"BSLP MN | [5 empty] | 1794.07 | 152.7248 | 1641.3452 |  |  |  | 2021-12-15
20026976501 | INSTALL 4270' OF 2"/4"PMMP MN | [5 empty] | 1937333.59 | 1522347.7868 | 414985.8032 |  |  |  | 2022-08-05 | WIPE SAMPLE RESULTS WERE ENTERED ON THE INSTALL JOB IN ERROR. WIPE RESULTS FOR THE RETIREMENT PIPE WERE ENTERED HERE. TWALKER/KY 01-24-23: JOB OVER RUN DUE TO ADDITIONAL STREET/HARD SURFACE REP AIRS REQUIRED BY CITY OF LEXINGTON. CONTRACT COST INCREASED BY $200,000 WITH PAVING/FLAGGING COST, SEGA WAS $73,000 HIGHER THAN PLANNED, ADDITIONAL $22,000 CHARGED FOR MATERIAL COST. TWALKER/KY 08-29-23: LEVEL 2 VARIANCE ADDED TO WMS.DOCS. JOB COST OVERRUN DUE TO ADDITIONAL STREET MILL/RE-PAVED COST REQUIRED BY CITY OF LEXINGTON.
20026976600 | RETIRE 4650' OF 3"/4"BSLP MN | [5 empty] | 320 | 56.8875 | 263.1125 |  |  |  | 2022-08-05
20026977101 | INSTALL 11,500' OF 2"/4"PMMP | [5 empty] | 1143604.07 | 926814.1047 | 216789.9653 |  |  |  | 2021-12-15 | TWALKER/KY 03-02-22: PROJECT COST OVER RUN DUE TO ADDITIONAL CONSTRUCTION COORINATOR ON SITE DURING CONSTRUCTION ADDED $65,000 IN LABOR COST, SEWER VIDEO FOR MAIN/SL BY BUCHANAN WAS $86,000 HIGHER THAN ESTIMATE, ADDITIONAL FLAGGING AND HARD SURFACE REPAIRS ADDED $25,000 TO CONTRACT COST. FINALLY SEGA WAS $35,000 HIGHER THAT PLANNED COST.
20026977200 | RETIRE 6900' OF 4"/6"BSLP MAIN | [5 empty] | 848.1 | 76.6277 | 771.4723 |  |  |  | 2021-12-15
20026981200 | INSTALL 1550' OF 2"PMMP MAIN | [5 empty] | 479750.56 | 414073.7744 | 65676.7856 |  |  |  | 2021-09-28 | TWALKER/KY 05-04-22: JOB OVER RUN CAUSED BY ADDTIONAL $46,000 FOR SEWER CAMERA WORK, PROJECT TOOK LONGER TO COMPLETE DUE TO TRAFFIC AND URBAN SETTING INCREASED COMPANY LABOR BY $5000, SEGA $17000 HIGHER THAN ESTIMATE.
20026981300 | RETIRE 1600' OF 2"/3"BSLP MAIN | [5 empty] | 0 | 84.1799 | -84.1799 |  |  |  | 2021-09-28
20026982700 | INSTALL 4500'-2"&4" PMMP | [5 empty] | 885948.31 | 959444.7901 | -73496.4801 |  |  |  | 2022-03-29
20026982900 | RETIRE 3700'-2&4" BSLP | [5 empty] | 142.7 | 88.8156 | 53.8844 |  |  |  | 2022-04-01
20026984400 | INSTALL 949'-6" PMLP | [5 empty] | 282788.29 | 204292.6769 | 78495.6131 |  |  |  | 2021-03-12 | 14JUN21: OVERRRUN EXPLANATION = 1) REQUIRED FLAGGING WAS WAY UNDERESTIMATED AS $30K ADDITIONAL DOLLARS FOR FLAGGING WAS REQUIRED, 2) AN ADDITIONAL $10K IN DUST & STONE WAS REQUIRED, 3) THE 6" ROCK BORE WAS PAID ALL IN HEAVY ROCK WHEREAS IT WAS ESTIMATED 1/2 HEAVY AND 1/2 LIGHT WHICH CONTRIBUTED ANOTHER $8K TO THE OVERRUN,4) ADDITIONAL VAC EXCAVATION WAS REQUIRED ADDING $3K TO THE OVERRUN. THESE PLUS ADDITIONAL OH'S MAKE UP THE MAJORITY OF THE $57K OVERRUN (BKSLONE)
20026985200 | INSTALL 6" PCF | [5 empty] | 9877.17 | 16280.811 | -6403.641 |  |  |  | 2021-06-12
20026985300 | RETIRE 300'-6" CSMP | [5 empty] | 71.35 | 88.4533 | -17.1033 |  |  |  | 2021-07-01
20026985600 | INSTALL 375' OF 2"CSHP MAIN | [5 empty] | 90203.73 | 92169.2028 | -1965.4728 |  |  |  | 2021-01-03
20026985700 | RETIRE 200' OF 2"CSHP MAIN | [5 empty] | 62.95 | 84.1794 | -21.2294 |  |  |  | 2022-01-03
20026987500 | INSTALL 300' OF 2"PMMP MAIN | [5 empty] | 18181.58 | 19258.6597 | -1077.0797 |  |  |  | 2021-03-10
20026988100 | INSTALL 525' OF 2"PMMP MAIN | [5 empty] | 10228.67 | 17405.4965 | -7176.8265 |  |  |  | 2021-01-11
20026988300 | RETIRE 1853'-4"/3" BS/CSMP | [5 empty] | 47.8 | 5110.2031 | -5062.4031 |  |  |  | 2021-12-16
20026989600 | INSTALL 40'-2" PMMP | [5 empty] | 36919.96 | 30326.4153 | 6593.5447 |  |  |  | 2021-01-15
20026989700 | RETIRE 40'-2" CSMP | [5 empty] | 0 | 107.2796 | -107.2796 |  |  |  | 2021-01-15
20026990600 | PAPER ONLY FOR CLOSE OUT | [5 empty] | 0 | 103.8156 | -103.8156 |  |  |  | 2021-01-21
20026991100 | INSTALL 100' OF 4"PMLP S/L | [5 empty] | 33764.98 | 29024.9725 | 4740.0075 |  |  |  | #N/A
21026100900 | EMER INSTALL 5'-4" PMMP | [5 empty] | 49713.13 | 15398.8131 | 34314.3169 |  |  |  | 2021-02-10 | RETIRED 4 FEET OF 4' PE MAIN LINE. REPLACED PEICE OF MAIN WITH NEW AND EF COUPLINGS. PRESSURE TESTED NEW PEICE OF MAIN FOR 1HR @ 90PSIG. TEST OK. SOAP TESTED FINALS CONNECTION @ OP. TEST, BHB, NGF. DMALONE 2/09/2021. OVERRUN EXPLANATION: UNEXPECTED CONTRACT COST OF $35,000 WAS NOT PLANNED, JO ORIGINALLY PLANNED FOR COMPANY CREW BUT WAS EXECUTED BY A CONTRACT CREW, COMPANY CREWS ALSO CHARGED 183 HOURS TO PROJECT
21026101000 | EMER RETIRE 5'-4" PMP D222468 | [5 empty] | 10.95 | 69.6296 | -58.6796 |  |  |  | 2021-02-09 | RETIRED 4 FEET OF 4' PE MAIN LINE. REPLACED PEICE OF MAIN WITH NEW AND EF COUPLINGS. PRESSURE TESTED NEW PEICE OF MAIN FOR 1HR @ 90PSIG. TEST OK. SOAP TESTED FINAL CONNECTION @ OP. TEST OK. BHB. NGF. DMALONE 2/09/2021 OVERRUN EXPLANATION: THIS RETIREMENT JOB ORDER WAS ESTIMATED IN THE ORDINAR Y MANNER FOR JUST 1 HOUR; HOWEVER, THERE WERE NO PROPERTY UNITS INSTALLED S O THE JOB WAS WORKED AS AN ABANDONMENT WITH ALL THE LABOR AND CONTRACT COST S BEING APPLIED TO THE RETIREMENT. THE INSTALL JOB ORDER WAS EXECUTED WITH AN HOUR OF LABOR.
21026101501 | INSTALL 3800'-2",4"&6" PMMP | [5 empty] | 842479.02 | 710294.4849 | 132184.5351 |  |  |  | 2022-05-05 | OVERRUN EXPLANATION: ENCOUNTERED MORE ROCK EXCAVATION THAN ESTIMATED AS WEL L AS THE ASSOCATED SPECIAL BACKFILL. PROJECT ALSO REQUIRED MORE SEWER CAMER A WORK THAN ESTIMATED.
21026101600 | RETIRE 1200'-2"&4" BSMP | [5 empty] | 325.85 | 85.0089 | 240.8411 |  |  |  | 2022-05-06
21026102900 | INSTALL 2400' OF 4"PMMP MAIN | [5 empty] | 104251.17 | 80646.5708 | 23604.5992 |  |  |  | 2021-06-15
21026104400 | INSTALL 2"SS TO RETIRE INLET | [5 empty] | 24511.65 | 37406.9466 | -12895.2966 |  |  |  | 2021-05-13
21026104500 | RETIRE 7' OF 2"BSMP MAIN | [5 empty] | 72.67 | 80.8842 | -8.2142 |  |  |  | 2021-05-13
21026104600 | RETIRE PIT REG STATION 1016 | [5 empty] | 188917.56 | 138142.7376 | 50774.8224 |  |  |  | 2021-05-14 | REMOVED MONITOR AND CONTROL REG. AND BLIND FLANGED, MONITORED 30 MIN. DUE TO NOT BEING ABLE TO BLIND FLANGE BYPASS, ADVISED CONSTRUCTION ABOUT BYPASS CCC 20355 CMCHOLAN RHAYES NGINTER BLONE 4-23-2021 REGULATORS REMOVED AND BLIND FLANGED ON 4/23/2021 PIPING AND VAULT ABANDONED AND REMOVED BY CONSTRUCTION ON 5/12/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/14/2021 GCCC TICKET NOT REQUIRED ON 5/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS TWALKER/KY 11-15-21: LEVEL 2 VARIANCE FORM ADDED TO WMS.DOCS. JOB OVER RUN DUE TO $41,500 FROM LP/OPP MATERIAL CHARGED TO THIS ORDER. ADDITIONAL $11,000 IN COMPANY HIGHER THAN PLANNED ESTIMATE.
21026105201 | INSTALL CHAIN LINK FENCE | [5 empty] | 84349.67 | 78948.1342 | 5401.5358 |  |  |  | 2023-04-14 | FENCE INSTALL COMPLETE APARKS 04-19-23 1600 CCC#24962
21026105401 | INSTALL 6520' OF 6"PMMP MAIN | [5 empty] | 427430.93 | 403346.5487 | 24084.3813 |  |  |  | 2021-12-17
21026105900 | EMER INSTALL 5' OF 4"PMMP MAIN | [5 empty] | 12908.51 | 24731.5705 | -11823.0605 |  |  |  | 2021-03-18 | TWALKER/KY-04-20-21: I HAVE ADDED A SIGNED PRESSURE TEST TO APPROVE THE 20 MIN PRESSURE TEST TO WMS.DOCS WORKSPACE.
21026106000 | EMER RETIRE 5' OF 4"PAMP MAIN | [5 empty] | 0 | 82.208 | -82.208 |  |  |  | 2021-03-18
21026106100 | INSTALL 1350' OF 2"/4"PMMP | [5 empty] | 39665.6 | 45765.0925 | -6099.4925 |  |  |  | 2021-04-09 | STANLEY PIPELNE INSTALLED MAIN
21026106200 | INSTALL 6" PCF | [5 empty] | 13429.76 | 16594.9062 | -3165.1462 |  |  |  | 2021-04-12 | INSTALLED 6"SST
21026106300 | RETIRE 575'-6" BSLP | [5 empty] | 1068.93 | 88.4533 | 980.4767 |  |  |  | 2021-04-12 | ABANDONED 640'060 CSLP
21026107700 | INSTALL 20' OF 8"PMLP MAIN | [5 empty] | 8482.5 | 12704.2275 | -4221.7275 |  |  |  | 2021-04-14 | REPLACED 36' OF S LP MAON W/ 8" P PER TIE-IN PLAN AND GAS STANDARDS. SOAP TEST TIE-IN COUPLINGS NO LEAKS. BHB NGF. MAIN PTOS READ -0.482 INST 2 9LB ANODES.
21026107800 | RETIRE 20' OF 8" BSLP | [5 empty] | 8727.02 | 56.3197 | 8670.7003 |  |  |  | 2021-04-14 | ABN 36' OF 8" S LP MAIN AND REPLACE WITH 8" P PER GAS STANDARDS AND TIE-IN PLAN. WORKED W/ 557 JOB# 21026107700. MCRAIG 4/14/21
21026107900 | INSTALL 10' OF 3" PMLP | [5 empty] | 7671.47 | 13301.2275 | -5629.7575 |  |  |  | 2021-04-16 | ABANDONED 23' OF 030 S MAIN.DUE TO ATMOS CORR INSTALLED 23' OF 030 PLASTIC WORKED WITH TIE IN PLAN AND GAS STANDARD. BHB NGF. INSTALLED TWO TEST STATIONS AND TWO ANODED.DESNO WRAPPED STEEL MAIN.
21026108000 | RETIRE 10' OF 3" BSLP | [5 empty] | 8414.88 | 79.3197 | 8335.5603 |  |  |  | 2021-04-16 | ABANDONED 23' OF 030 S MAIN.DUE TO ATMOS CORR INSTALLED 23' OF 030 PLASTIC WORKED WITH TIE IN PLAN AND GAS STANDARD. BHB NGF. INSTALLED TWO TEST STATIONS AND TWO ANODED.DESNO WRAPPED STEEL MAIN.
21026108100 | INSTALL 20' OF 3" PMMP | [5 empty] | 70757.52 | 21676.4521 | 49081.0679 |  |  |  | 2021-05-06 | AWEBER/KY 09/21/2021: PROXIMITY OF LP MAIN TO MP MAIN RESULTED IN AN ACTUAL FOOTAGE INSTALL OF 320'-PMMP IN ORDER TO SEPERATE AND INSTALL FITTINGS AS NEEDED. UNABLE TO REVISE WMS JO DUE TO UNPAID MATERIAL INVOICES AND JO COMP LETION STATUS AT THE TIME.
21026108200 | RETIRE 20' OF 3" BSMP | [5 empty] | 4.6 | 56.3197 | -51.7197 |  |  |  | 2021-05-05
21026108600 | EMER-INSTAL 5'-2" PMMP | [5 empty] | 116.02 | 5147.5997 | -5031.5797 |  |  |  | 2021-03-08 | INSTALLED 5' OF TEST 2" PMMP, SOAP TEST TIE IN, NO LEAKS, BHB NGF TIE OVER 2 SERVICE LINES, ON 3-5-21 DMEDLEY 3-8-21
21026108700 | EMER - RETIRE 5'-2" PAMP | [5 empty] | 4796.8 | 85.3307 | 4711.4693 |  |  |  | 2021-03-08 | INSTALLED GAUGE TEE, SQUEEZE OFF 2" PL MAIN, ABN 5' 2"PMP MAIN PER DLEMONS EMER DESIGN PLAN. WORKED ON 3-5-21, DMEDLEY 3-8-21
21026108801 | INSTALL 1000' OF 2"PMMP MAIN | [5 empty] | 51597.09 | 46147.0126 | 5450.0774 |  |  |  | 2022-01-25
21026109300 | INSTALL 300' OF 2"PMMP MAIN | [5 empty] | 26886.16 | 25871.1277 | 1015.0323 |  |  |  | 2021-09-02
21026109900 | RETIRE 2155'-4"/3" BS/PMLP | [5 empty] | 3173.92 | 343.31 | 2830.61 |  |  |  | 2021-04-28
21026110100 | INSTALL 900' OF 2"PMMP MAIN | [5 empty] | 24183.42 | 26234.9875 | -2051.5675 |  |  |  | 2021-06-23
21026110400 | INSTALL 100'-12" CSMP | [5 empty] | 188696.44 | 142453.0552 | 46243.3848 |  |  |  | 2021-06-30 | OVERRUN EXPLANATION: PROJECT OVERRAN DUE TO FLAGGER TIME AND FLAGGER OVERTI ME. BUDGET VARIANCE EXPLANATION FORM LOADED INTO WMSDOCS WORKSPACE. D.LEMONS 12 /3/2021
21026110500 | RETIRE 94'-12" CSMP | [5 empty] | 142.7 | 85.5775 | 57.1225 |  |  |  | 2021-06-30
21026110600 | RETIRE 600'-2&3" PMLP | [5 empty] | 701.12 | 21928.4488 | -21227.3288 |  |  |  | 2021-11-18
21026110700 | REPLACE FENCE | [5 empty] | 480.98 | 14980.1771 | -14499.1971 |  |  |  | 2021-12-17 | CCC# 33097 - BLONE - 07/29/21 FENCE REPLACED BY INTERSTATE FENCE COMPANY PAPERWORK COMPLETED BY CYNTHIA FARIS ON 12/17/2021
21026110800 | RETIRE FENCE | [5 empty] | 0 | 61.2976 | -61.2976 |  |  |  | 2021-12-17 | FENCE REPLACED BY INTERSTATE FENCE COMPANY PAPERWORK COMPLETED BY CYNTHIA FARIS 12/17/2021
21026111101 | INSTALL FENCE | [5 empty] | 5601.7 | 40000.9906 | -34399.2906 |  |  |  | 2021-12-16 | CCC# 31858 , 31996 , 32095 , 32237 , 32396 , 32702 ALL USED DURING PROJECT BLONE - 07/29/21 FENCE INSTALLED BY INTERSTATE FENCE COMPANY PAPERWORK COMPLETED BY CYNTHIA FARIS 12/16/21 UNDERRUN EXPLANATION: THE COST ESTIMATE THAT THE CONTRACTOR PROVIDED TURNED OUT TO BE SIGNIFICANTLY LESS THAN THEY HAD ESTIMATED. GES 3/2/22
21026111200 | RETIRE FENCE | [5 empty] | 0 | 61.2976 | -61.2976 |  |  |  | 2021-12-16 | FENCE REPLACED BY INTERSTATE FENCE COMPANY PAPERWORK COMPLETED BY CYNTHIA FARIS 12/16/21
21026112100 | INSTALL 1025'- 2"/4"PHHP MAIN | [5 empty] | 192775.66 | 194441.8822 | -1666.2222 |  |  |  | 2021-09-29
21026112200 | RETIRE 980' OF 4"CSHP MAIN | [5 empty] | 723.52 | 74.8797 | 648.6403 |  |  |  | 2021-09-29
21026112300 | INSTALL 180' OF 4"PMMP S/L | [5 empty] | 24370.71 | 28556.5857 | -4185.8757 |  |  |  | #N/A
21026112400 | INSTALL NEW GMB SETTING | [5 empty] | 55082.19 | 57016.3076 | -1934.1176 |  |  |  | 2022-08-22 | INSTALLED NEW GMB SKID MOUNTED METER AND REGULATOR SETTING AJPARKS 8-22-202 2 PSID 501306155
21026112700 | INSTALL 350' OF 2"PMIP MAIN | [5 empty] | 37226.93 | 19281.66 | 17945.27 |  |  |  | 2021-06-11
21026113000 | EMER - INSTALL 60' OF 4"PMLP | [5 empty] | 2022.21 | 12530.1178 | -10507.9078 |  |  |  | 2021-04-08 | INSTALLED 54' OF 040 PLASTIC DUE TO STEEL ATMOS CORR. BAGGED OFF MAIN, RETIRED 54' 040 STEEL.WORKED WITH TIE IN PLAN AND CAPITAL PACKET.INSTALLED TWO TEST STATIONS. BHB NGF. KKINDER
21026113100 | EMER - RETIRE 60' OF 4"BSLP | [5 empty] | 1338.57 | 57.8842 | 1280.6858 |  |  |  | 2021-04-08 | ABADONED 54' OF S LP DUE TO ATMOS CORR. WORKED WITH 557. BAGGED OFF MAIN WORKED WITH TIE IN PLAN. KKINDER
21026113600 | RETIRE INLET/OUTLET BLK VALVES | [5 empty] | 0 | 88.1542 | -88.1542 |  |  |  | 2021-07-19 | JOB COMPLETED BY WADE SHIMFESSEL ON 7/19/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/21/21 GCCC TICKET NOT REQUIRED ON 7/21/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026113701 | INSTALL 4030' - 4"/2" PMMP | [5 empty] | 862366.14 | 778460.4875 | 83905.6525 |  |  |  | 2021-12-17
21026114500 | RETIRE PIT REG STATION# 1024 | [5 empty] | 195061.46 | 149437.1771 | 45624.2829 |  |  |  | 2022-05-12 | REMOVED 2 441 REGS AND BLIND FLANGED VALVES, STATION RETIRED, CMCHOLAN CCOX RHAYES 5-12-2022 RWILLIAMS COMPLETED PAPER WORK TWALKER/KY 11-30-22: JOB OVER RUN WAS DUE TO COST FOR 20-0269890-00 (2000) WITH LAND SERVICE AND CONTRACT ENG COST OF $65000, 19-0268950-00 (0001) MATERIAL FOR LPP MATERIAL OF $84000 AND 18-0268465-00 (2000) LAND SERVICES FOR LPP PROJECT APPROV $45000 FROM PROJECT MANAGEMENT AND GTMR GROUPS.
21026115700 | INSTALL 300' OF 2"PMMP MAIN | [5 empty] | 21541.85 | 22097.6064 | -555.7564 |  |  |  | 2021-09-28
21026117800 | RETIRE 117' - 4" PLP | [5 empty] | 11604.62 | 9954.0712 | 1650.5488 |  |  |  | 2021-06-28 | ABN 102' OF 040 PL ML. TESTED 4' OF 040 W/ END CAPS FOR 1 HR @ 90# SOAP TESTED CONN PTS @ 11" WC. SOAP TESTED ALL TEE CAP AND END CAPS @ OP.
21026117900 | INSTALL 575' OF 2"PMIP MAIN | [5 empty] | 15668.74 | 17428.325 | -1759.585 |  |  |  | 2021-06-09 | TWALKER/KY 06-28-21: THIS 555 WAS COMPLETED IN THE FIELD BUT PAPERWORK NOT COMPLETED OR MAPPED WHEN A CONTRACTOR DAMAGED A SECTION OF THIS NEW GAS MAIN. ALL WORK AND COST INCLUDED IN THIS JOB ORDER AND THE REASON FOR TWO TIE IN PLANS AND TEST FORMS.
21026118300 | INSTALL 210' OF 2"PMMP MAIN | [5 empty] | 17888.9 | 16739.4681 | 1149.4319 |  |  |  | 2021-09-09
21026118500 | RETIRE 3,256' 10"-3" CS/BS/PLP | [5 empty] | 42.9 | 151.2005 | -108.3005 |  |  |  | 2021-12-20
21026118600 | INSTALL 600' OF 2"PMMP MAIN | [5 empty] | 65051.29 | 37159.65 | 27891.64 |  |  |  | 2021-07-13
21026118700 | EMER-INSTALL 2' OF 2"PMMP MAIN | [5 empty] | 2106.1 | 4434.6174 | -2328.5174 |  |  |  | 2021-04-29 | REFERENCE JOB# 21906644500 FOR COMMENTS AND JOB INFO DMARSTO 4/27/21
21026118800 | EMER-RETIRE 2' OF 2"PAMP MAIN | [5 empty] | 755.09 | 78.808 | 676.282 |  |  |  | 2021-04-29 | REFERENCE JOB# 21906644500 FOR COMMENTS AND JOB INFO DMARSTO 4/27/21
21026120700 | RETIRE REG STATION 1002 | [5 empty] | 6481.89 | 5235.8425 | 1246.0475 |  |  |  | 2021-12-27 | CC# 48634 CMCOX 12/15/21 STATION RETIRED BY CHRIS COX AND CONSTRUCTION SERVICES PAPERWORK COMPLETED BY CYNTHIA FARIS ON 12/27/21
21026120800 | RETIRE HP/MP RUN-1 OF R-1035 | [5 empty] | 827.14 | 21706.5276 | -20879.3876 |  |  |  | 2021-11-29 | HP TO MP RUN 1 HAS BEEN RETIRED AND LP RUN 2 HAS BEEN PLACED BACK INTO SERVICE WORKED COMPLETED ON 11/3/2021 BY CHRIS COX PAPERWORK COMPLETED BY CYNTHIA FARIS ON 11/29/2021 GCCC TICKET NOT REQUIRED ON 11/29/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026122000 | INSTALL 2150' OF 2"PMMP MAIN | [5 empty] | 178403.1 | 162365.3384 | 16037.7616 |  |  |  | 2022-06-28
21026122200 | INSTALL 925' OF 2"PMMP MAIN | [5 empty] | 41992.33 | 32784.4942 | 9207.8358 |  |  |  | 2021-06-09 | TWALKER/KY 06-28-21: THIS 555 PROJECT WAS COMPLETED IN FIELD BUT PAPERWORK NOT SUBMITTED TO CLOSE OR MAPPEND WHEN LEAK ON THE NEW MAIN WAS DETECTED. WE BELIEVE THE MAIN LINE WAS DAMAGED DURING BACK FIELD. LEAK WAS REPAIRED BY CONSTRUCTION THAT IS REASON FOR TWO TIE IN PLANS AND TEST FORMS.ALL COST AND WORK CAPTURED UNDER THIS JOB ORDER.
21026122500 | EMER-INSTALL 5' OF 4"PMLP MAIN | [5 empty] | 9606.89 | 6150.5343 | 3456.3557 |  |  |  | 2021-05-11 | CONTRACTOR HIT 040 PLASTIC MAIN WITH EXCAVATOR. SQUEEZED OFF TO MAKE SAFE. REPLACED 5FT OF 040 P LP. TESTED MAIN FOR 20MINS AT 90LBS.TEST OK.SOAP TEST FINAL TIE INS AT OP. TEST OK.BHB NGF.WORKED WITH CAPITAL JO AND TIE IN PLAN TWALKER/KY 06-28-21: THIS PROJECT WAS GENERATED FROM 3RD PARTY DAMAGE FROM A CONTRACTOR REPLACING STORM/SEWER AT THE INTERSECTION OF MILLER AND 2ND ST. CONTRACTOR DAMAGE SMALL OF MAIN FIRST DAY AND THE VERY NEXT DAY HIT/DA MAGE THE REPAIR MAIN. THAT MAIN WAS NEVER BOOKED OR MAPPED IN WMS. ALL WORK AND COST CAPTURED ON THIS JOB ORDER. WE HAVE TWO TIE INS AND TEST.
21026122600 | EMER-RETIRE 5' OF 4"PMLP MAIN | [5 empty] | 19.8 | 78.808 | -59.008 |  |  |  | 2021-05-11 | CONTRACTOR HIT 040 PLASTIC MAIN WITH EXCAVATOR. SQUEEZED OFF TO MAKE SAFE. REPLACED 5FT OF 040 P LP. TESTED MAIN FOR 20MINS AT 90LBS.TEST OK.SOAP TEST FINAL TIE INS AT OP. TEST OK.BHB NGF.WORKED WITH CAPITAL JO AND TIE IN PLAN
21026122700 | EMEG-INSTALL 5' OF 4"PMMP MAIN | [5 empty] | 3856.8 | 5607.5343 | -1750.7343 |  |  |  | 2021-05-18 | RESPONDED OT MAIN LINE DAMAGE. INSTALLED 2' OF 4" PE MAIN LINE. PRESSURE TESTED MAIN @ 90PSIG FOR 20MINS PER FOL APPROVAL. TEST OK. SOAP TESTED LAST CONNECTION @ OP. TEST OK. CONTENT VERIFIED. PRESSURE VERIFIED @ 52PSIG DMAL
21026122800 | EMER-RETIRE 5' OF 4"PMMP MAIN | [5 empty] | 210.25 | 78.808 | 131.442 |  |  |  | 2021-05-18 | RESPONDED TO MAIN LINE DAMAGE. INSTALLED 2' OF 4" PE MAIN LINE. PRESSURE TESTED MAIN @ 90PSIG. FOR 20MINS PER FOL APPROVAL. TEST OK. SOAP TESTED FINAL CONNECTION @ OP. TEST OK. CONTENT VERIFIED. VERIFIED PRESSURE @52PSIG
21026122900 | INSTALL 8" SS | [5 empty] | 48788.62 | 30904.4019 | 17884.2181 |  |  |  | 2021-07-30
21026124400 | EMER-INSTALL 2' OF 2"PMMP | [5 empty] | 1470.21 | 2935.5264 | -1465.3164 |  |  |  | 2021-06-30
21026124500 | EMER-RETIRE 2' OF 2"PMMP | [5 empty] | 0 | 85.0408 | -85.0408 |  |  |  | 2021-06-30
21026124600 | INSTALL 3" OUTLET VALVE | [5 empty] | 28606.82 | 34892.3468 | -6285.5268 |  |  |  | 2021-07-19
21026124700 | RETIRE 4' OF 3"BSIP MAIN | [5 empty] | 0 | 86.5975 | -86.5975 |  |  |  | 2021-07-19
21026124800 | INSTALL INLET/OUTLET BLOCK VLV | [5 empty] | 20343.89 | 13873.2524 | 6470.6376 |  |  |  | 2021-07-19 | CCC# 30839 CCC# 31113 CCC# 31169 IN PROGRESS CCC# 31169 CC# 31169 CC-31326 CC-31492 CCC# 31755 CC-31755 NOT ON SITE- OFFICE ISO UPDATE CAP WORK COMPLETED BY WADE SHIMFESSEL ON 7/19/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/21/20 GCCC TICKET NOT REQUIRED ON 7/21/20 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS 7/21/20
21026125400 | INSTALL 28' 4" PMMP | [5 empty] | 20147.11 | 10969.2814 | 9177.8286 |  |  |  | 2021-06-15
21026125500 | RETIRE 20' OF 4" PMMP | [5 empty] | 0 | 91.2676 | -91.2676 |  |  |  | 2021-06-15
21026125600 | INSTALL 28' 8" PMLP | [5 empty] | 23277.54 | 11805.2814 | 11472.2586 |  |  |  | 2021-06-15
21026125700 | RETIRE 20' 8" PMLP | [5 empty] | 71.35 | 91.2676 | -19.9176 |  |  |  | 2021-06-15
21026125800 | REPLACE C18-5 E | [5 empty] | 96855.51 | 77241.44 | 19614.07 |  |  |  | 2021-07-30
21026125900 | RETIRE C18-5 | [5 empty] | 38.57 | 91.2676 | -52.6976 |  |  |  | 2021-07-30
21026126102 | INSTALL 2000' OF 2"PMMP MAIN | [5 empty] | 169255.42 | 165212.1661 | 4043.2539 |  |  |  | 2022-08-02
21026126200 | RETIRE 270' OF 1"BSHP MAIN | [5 empty] | 0 | 63.0891 | -63.0891 |  |  |  | 2022-08-02
21026126600 | RETIRE REG STATION #1181 | [5 empty] | 1370.38 | 4088.2989 | -2717.9189 |  |  |  | 2022-04-29 | RWILLIAMS COMPLETED PAPER WORK, EBLANTON RETIRED STATION ON 04/29/2022
21026126700 | INSTALL 350' OF 2" PMMP | [5 empty] | 99374.93 | 123612.3972 | -24237.4672 |  |  |  | 2022-05-09
21026126800 | INSTALL 11,170' OF 2"/6"PMMP | [5 empty] | 1675598.92 | 1492284.9718 | 183313.9482 |  |  |  | 2022-10-10
21026126900 | RETIRE 9000' OF 4"/6"BSLP MAIN | [5 empty] | 24.95 | 62.0792 | -37.1292 |  |  |  | 2022-10-10
21026128000 | INSTALL 265' OF 4" PMLP | [5 empty] | 96077.32 | 71153.2979 | 24924.0221 |  |  |  | 2022-03-10 | AWEBER - JO RAN OVER ESTIMATE DUE TO UNFORSEEN 8'X5' STORM BASIN @ 42" BELO W GRADE. EXCAVATION OF TOP OF BASIN OCCURRED TO PROVIDE REROUTE OF 4" PMMP INSTALL AT ACCEPTABLE DEPTH WITHOUT CROSSBORE.
21026128100 | RETIRE 230'-4" & 50'-6" PMLP | [5 empty] | 71.35 | 354.2624 | -282.9124 |  |  |  | 2022-03-10
21026128601 | INSTALL 700' OF 2"PMMP MAIN | [5 empty] | 75716.28 | 57445.0039 | 18271.2761 |  |  |  | 2021-10-13
21026128700 | RETIRE HP/MP REG RUN | [5 empty] | 3741.83 | 4148.6042 | -406.7742 |  |  |  | 2021-11-18 | HP/MP RUN RETIRED BY CHRIS COX ON 11/9/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 11/18/2021 GCCC TICKET NOT REQUIRED ON 11/18/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026128802 | INSTALL 470' OF 4"PMMP MAIN | [5 empty] | 106230.58 | 96528.8129 | 9701.7671 |  |  |  | 2022-05-25
21026128900 | RETIRE 440' OF 4"BSMP MAIN | [5 empty] | 30.93 | 67.1085 | -36.1785 |  |  |  | 2022-06-30 | X
21026129000 | RETIRE 680'-4"BSLP MN -D247885 | [5 empty] | 0 | 67.1085 | -67.1085 |  |  |  | 2022-05-25
21026129400 | RETIRE 135' OF 8"CSMP MAIN | [5 empty] | 1142.2 | 151.2005 | 990.9995 |  |  |  | 2021-09-01 | ABN 135' ON CS MP MAIN.
21026129500 | RETIRE 109' OF 4"BSLP | [5 empty] | 71.35 | 99.3208 | -27.9708 |  |  |  | 2021-09-03 | ABN 4" BS LP MAIN PER GS
21026129600 | INSTALL 100' OF 8"PMMP MAIN | [5 empty] | 152586.55 | 99233.0142 | 53353.5358 |  |  |  | 2021-11-19 | TWALKER/KY 01-24-23: JOB ORDER OVER RUN DUE TO ADDITIONAL FLAGGING ADDED $50,000 TO CONTRACT COST, SEGA INCREASED BY $6,000 AND CO LABOR COST HIGHER BY $14,000 LEVEL 2 VARIANCE ADDED TO WMS.DOCS.
21026129700 | RETIRE 20' OF 8"BSMP MAIN | [5 empty] | 1960.6 | 79.203 | 1881.397 |  |  |  | 2021-11-19
21026129900 | RETIRE PIT REG STATION W/AMRP | [5 empty] | 3639 | 4706.4362 | -1067.4362 |  |  |  | 2022-11-16 | RETIRED 800 PRESS AVE 200340, CMCHOLAN 11-16-22
21026130600 | INSTALL 350' OF 2"PMMP MAIN | [5 empty] | 42649.02 | 31312.2411 | 11336.7789 |  |  |  | 2021-08-17
21026130902 | INSTALL 5150' OF 2"/4" PMMP | [5 empty] | 192645.27 | 202239.5285 | -9594.2585 |  |  |  | 2022-04-08
21026132400 | INSTALL 225' OF 2"PMMP | [5 empty] | 85412.94 | 79492.8479 | 5920.0921 |  |  |  | 2022-11-17 | TTALKER/KY 01-25-23: JOB IS SHOWING COST UNDER RUN AT THIS TIME BUT PAVING/ STREET REPAIRS NOT TAKE PLACE UNTIL SPRING/WARM WEATHER. TWALKER/KY 06-23-23: JOB ORDER CURRENTLY UNDER RUNNING $32000 BUT STREET PAVING HAS NOT BEEN COMPLETED AT THIS TIME DUE TO DOWNTOWN AREA AND CONSTRU CTION BY OTHERS IN AREA. TWALKER/KY 07-21-23: PAVING HAS BEEN COMPLETED AND COST APPLIED TO JOB ORDE R, NOT OVER OR UNDER BUDGET VARIANCE REQUIRED AT THIS TIME. PAVING WAS DELAYED TO COLD AND WET WEATHER PLUS THIS PROJECT IS LOCATED IN DOWNTOWN AREA SO PERMIT RESTRICTION APPLIED.
21026132500 | INSTALL 450' OF 2"PMMP MAIN | [5 empty] | 31237.4 | 32348.6064 | -1111.2064 |  |  |  | 2021-10-06
21026134100 | INSTALL 850' OF 2"PMMP MAIN | [5 empty] | 28285.71 | 40949.6064 | -12663.8964 |  |  |  | 2021-10-21
21026134800 | INSTALL 20'-2" PMMP | [5 empty] | 67370.23 | 39141.4028 | 28228.8272 |  |  |  | 2022-01-12
21026134900 | RETIRE 16'-2" CSMP | [5 empty] | 0 | 88.8156 | -88.8156 |  |  |  | 2022-01-12
21026136100 | EMER-INSTALL 10'-2" PMMP | [5 empty] | 3664.07 | 5241.7163 | -1577.6463 |  |  |  | 2021-08-10
21026136200 | EMER-RETIRE 10'-2" PMP | [5 empty] | 253.41 | 88.8156 | 164.5944 |  |  |  | 2021-08-10 | RETIRED 2' OF DAMAGED 2" PMP MAIN
21026136500 | RELOCATE 12' OF 4"PMLP MAIN | [5 empty] | 25628.84 | 10466.234 | 15162.606 |  |  |  | 2021-08-18
21026136600 | RETIRE 6' OF 4"PMLP MAIN | [5 empty] | 0 | 85.7248 | -85.7248 |  |  |  | 2021-08-18
21026136800 | EMER-INSTALL 5' OF 4"PMMP | [5 empty] | 395.9 | 5949.1348 | -5553.2348 |  |  |  | 2021-08-24 | INST 5' 4" P MP MAIN ACCORDING TO ENGINEERED TIE-IN PLAN AND GAS STANDARDS. WORKED ON 8/17/21. MCRAIG 8/24/21
21026136900 | EMER-RETIRE 5' OF 4"PAMP | [5 empty] | 5438.98 | 55.634 | 5383.346 |  |  |  | 2021-08-24 | ABN 5' 4"P MP MAIN ACCORDING TO ENGINEERED TIE-IN PLAN. WORKED ON 8/17/21. MCRAIG 8/24/21
21026137100 | RETIRE 4'-8" BSLP | [5 empty] | 0 | 177.6312 | -177.6312 |  |  |  | 2021-08-18
21026137500 | INSTALL SOLAR PANEL | [5 empty] | 3598.81 | 4862.234 | -1263.424 |  |  |  | 2021-10-13 | CC# 41497 RHAYES 10-13-2021 RHAYES 10-13-2021 CHANGED ER350 FROM CRY IN TO FULL TIME MONITOR INSTALLED SUPER SOLAR KIT AN D RV 50 MODEM CCOX 10-13-2021
21026140400 | INSTALL 2800' OF 2"/4"PMMP | [5 empty] | 116146.05 | 86592.9986 | 29553.0514 |  |  |  | 2022-03-04
21026140901 | INSTALL 2750' OF 2"PMMP MAIN | [5 empty] | 104070.68 | 96941.3864 | 7129.2936 |  |  |  | 2022-04-15
21026141200 | EMER-INSTALL 3'OF 6"PMLP MAIN | [5 empty] | 5901.09 | 4022.0999 | 1878.9901 |  |  |  | 2021-09-15
21026141300 | EMER-RETIRE 3' OF 6"PLP MAIN | [5 empty] | 38.15 | 69.8875 | -31.7375 |  |  |  | 2021-09-13
21026141400 | INSTALL 130'-6" PMMP | [5 empty] | 179014.36 | 140177.264 | 38837.096 |  |  |  | 2022-02-15 | PROJECT OVERRUN OF $38,555 (28%) DUE TO ADDITIONAL TIME AND RESOURCES BEING REQUIRED. LABOR HOURS ESTIMATED AT 176 HRS, BUT 319 HRS WERE REQUIRED ($11 ,052 DIFF. LABOR RATE ESTIMTES TOO LOW). NEW CONTRACT WILL ADDITIONAL UNITS WAS USED WHICH ADDED $57,948. BUT THERE WERE SAVINGS OF $30,000 IN THE OT HER CATAGORY, WHICH WERE COVERED WITH UNITS IN THE UPDATED CONTRACT. D.LEMO NS 7/8/2022
21026141500 | RETIRE 316'-6" PM&CS MP | [5 empty] | 4123.73 | 76.2083 | 4047.5217 |  |  |  | 2022-02-15
21026141600 | INSTALL 320' OF 2"PMMP MAIN | [5 empty] | 51396.03 | 52296.0917 | -900.0617 |  |  |  | 2021-12-28
21026141700 | RETIRE 315' OF 2"PMP MAIN | [5 empty] | 46.05 | 60.6987 | -14.6487 |  |  |  | 2021-12-28
21026142200 | INSTALL 575' OF 2"PMMP MAIN | [5 empty] | 25446.02 | 20915.4686 | 4530.5514 |  |  |  | 2021-11-02
21026142500 | EMER-INSTALL 5' OF 2"PMMP | [5 empty] | 417.14 | 3297.6583 | -2880.5183 |  |  |  | 2021-09-20
21026142600 | EMER-RETIRE 5' OF 2"PMP MAIN | [5 empty] | 263.29 | 69.8875 | 193.4025 |  |  |  | 2021-09-20
21026143000 | RETIRE EME FACILITY | [5 empty] | 0 | 63.4597 | -63.4597 |  |  |  | 2021-10-04 | REPLACED EFC
21026143400 | EMER-INSTALL 10'OF 4"PMIP MAIN | [5 empty] | 7913.03 | 7432.5408 | 480.4892 |  |  |  | 2021-09-27
21026143500 | EMER-RETIRE 10' OF 4"PAIP MAIN | [5 empty] | 0 | 60.6987 | -60.6987 |  |  |  | 2021-09-27
21026143900 | EMER-INSTALL 5'-2"PMMP | [5 empty] | 0 | 6000.6188 | -6000.6188 |  |  |  | 2021-10-25
21026144000 | EMER-RETIRE 5'-2"PMMP | [5 empty] | 0 | 49.6987 | -49.6987 |  |  |  | 2021-10-25
21026144100 | INSTALL 350' OF 2"PMIP MAIN | [5 empty] | 19720.01 | 20004.6217 | -284.6117 |  |  |  | 2021-10-27
21026144200 | RETIRE 4280' OF 2"/3"PAMP MAIN | [5 empty] | 41269.58 | 14091.9275 | 27177.6525 |  |  |  | 2021-11-17 | ABN 4280' P MP MAIN IN ACCORDNANCE WITH ENGINEERED TIE-IN PLAN AND GAS STANDARDS. SOAP TEST FINAL TIE-IN AT OP OK. BHB NGF. MCRAIG 10/13/21 TWALKER/KY 11-24-21: WMS WOULD NOT ALLOW FOR REVISION DUE TO UNPAID INVOICES, JOB ORDER OVER RUN DUE TO SCOPE OF WORK INCREASED AND WE RETIRED MORE UNLOCATED FIRST GENERATION PLASTIC MAIN THAN PLANNED AND SOME NEW EMPLOYEES WORKED WITH CREWS WITH INCREASED LABOR COST BY $14,000 OVER ESTIMATE
21026145601 | INSTALL 1885' - 4" PMMP MAIN | [5 empty] | 816623.03 | 712573.3764 | 104049.6536 |  |  |  | 2024-03-18 | JOB COMPLETE
21026145700 | RETIRE 1840' OF 4" BSMP | [5 empty] | 110 | 100.2728 | 9.7272 |  |  |  | #N/A | JOB COMPLETE
21026146000 | INSTALL 404'-4"&6"PMMP | [5 empty] | 125105.39 | 224207.9887 | -99102.5987 |  |  |  | 2021-12-16 | LEVEL 2 BUDGET VARIANCE EXPLANATION FORM HAS BEEN APPROVED AND LOADED INTO WMSDOCS WORKSPACE. D.LEMONS 3/3/2022
21026146100 | RETIRE 427'-4"BSLP | [5 empty] | 1537.36 | 63.4597 | 1473.9003 |  |  |  | 2021-12-16
21026147100 | EMER-INSTALL 6' OF 4"PMMP | [5 empty] | 604.21 | 1045.4141 | -441.2041 |  |  |  | 2021-10-25
21026147200 | EMER-RETIRE 6' OF 4"PAMP MAIN | [5 empty] | 38.59 | 49.6987 | -11.1087 |  |  |  | 2021-10-25
21026147900 | EMER - INSTALL 5'-4" PMLP | [5 empty] | 3691.18 | 2422.8089 | 1268.3711 |  |  |  | 2021-11-17 | INSTALLED 3FT OF 040 PLASTIC DUE TO 3 TEE'S BEING AN AOC. ALL TESTING INFO ON JO 21026147900 AND 21026148000 IN WMS DOCS.
21026148000 | EMER - RETIRE 5'-4" PLP | [5 empty] | 4.38 | 66.2207 | -61.8407 |  |  |  | 2021-11-17 | INSTALLED 3FT OF 040 PLASTIC DUE TO 3 TEE'S BEING AN AOC. ALL TESTING INFO ON JO 21026147900 AND 21026148000 IN WMS DOCS.
21026148100 | EMER-INSTALL 4' OF 2"HPHP MAIN | [5 empty] | 2019.57 | 7370.71 | -5351.14 |  |  |  | 2022-01-24
21026148200 | EMER-RETIRE 4' OF 2"HDHP MAIN | [5 empty] | 0 | 60.6987 | -60.6987 |  |  |  | 2022-01-24
21026151200 | INSTALL 2065'-2"&6" PMMP | [5 empty] | 493527.08 | 333722.7132 | 159804.3668 |  |  |  | 2022-10-17
21026151300 | RETIRE 2111'-2"&6" CSMP | [5 empty] | 80 | 109.7476 | -29.7476 |  |  |  | 2022-10-17
21026151500 | EMER-INSTALL 10' OF 4"PMMP | [5 empty] | 210.64 | 5220.9567 | -5010.3167 |  |  |  | 2021-11-24 | LEAK ON SF CPLG ON TEE OF SVC TO 3102 KIRKLEVINGTON DR. DPI D221947 CLEARED ON 2212. ABN/INST 3'- 4" P MAIN ACCORDING TO GAS STANDARDS AND ENGINEERED TIE-IN PLAN. WORKED 11/17/21 MCRAIG
21026151600 | EMER-RETIRE 10' OF 4"PAMP | [5 empty] | 24.42 | 64.6591 | -40.2391 |  |  |  | 2021-11-24 | LEAK ON SF COUPLING ON TEE TO SVC OF 3102 KIRKLEVINGTON DR. DPI D221947 CLEARED ON 2212. ABN/ INST 3'- 4" P MAIN ACCORDING TO GAS STANDARDS AND ENGINEERED TIE-IN PLAN. WORKED 11/17/24 MCRAIG
21026152101 | INSTALL 535' OF 8"CSHP MAIN | [5 empty] | 480960.85 | 444968.002 | 35992.848 |  |  |  | 2024-10-31
21026152200 | RETIRE 457' OF 6 5/8"BSHP MAIN | [5 empty] | 1859.99 | 74.2578 | 1785.7322 |  |  |  | #N/A
21026155900 | INSTALL 2400' OF 2"PMMP MAIN | [5 empty] | 72846.65 | 61211.3642 | 11635.2858 |  |  |  | 2022-02-10
21026156700 | INSTALL 20'-3 PMMP | [5 empty] | 13109.07 | 12546.0469 | 563.0231 |  |  |  | 2022-07-25
21026156800 | ABDN CB 12'-3" PMP | [5 empty] | 0 | 73.9724 | -73.9724 |  |  |  | 2022-08-01
21026156900 | INSTALL 10'-6" PMLP | [5 empty] | 6980.82 | 14786.2791 | -7805.4591 |  |  |  | 2022-07-21 | INSTALLATION COMPLETE, HMCKUNE
21026157000 | RETIRE 10'-6" PMLP | [5 empty] | 0 | 72.8047 | -72.8047 |  |  |  | 2022-04-20
21026993800 | INSTALL 7200' OF 2"/6"PMMP | [5 empty] | 3013391.75 | 2229015.8617 | 784375.8883 |  |  |  | 2022-12-09
21026993900 | RETIRE 9500' OF 4"CI/6"BSLP MN | [5 empty] | 5876.52 | 80.3582 | 5796.1618 |  |  |  | 2022-12-09 | ABANDONED ALL MAINS IN SCOPE OF PROJECT
21026994000 | INSTALL 10930 - 2"/4"PMMP MAIN | [5 empty] | 1681569.14 | 1953601.844 | -272032.704 |  |  |  | 2022-11-16 | TWALKER/KY 05-22-23: PROJECT CURRENTLY UNDER RUNNING, WAITING ON FINAL RESTORATION/PAVING TO DETERMINE IF ADDITIONAL EXPLAINATION OR VARIANCE REQU IRED. TWALKER/KY 06-23-23: JOB UNDER RUNNING DUE TO PAVING/HARD SURFACES REPAIRS HAVE NOT BEEN FULLY COMPLETED. TWALKER/KY 07-24-23: PAVING/HARD SURFACE REPAIRS STILL IN PROGRESS TWALKER/KY 08-29-23: LEVEL 1 VARIANCE FORM ADDED IN WMS.DOCS NOT SURE IF ALL PAVING INVOICES HAVE BEEN PAID BUT COST UNDER RUN DRIVEN BY LESS PAVING COST BY PAVING CONTRACTOR INSTEAD OF PIPELINE CO.
21026994100 | RETIRE 14,600 - 4"CI/BSLP MAIN | [5 empty] | 269.51 | 84.1794 | 185.3306 |  |  |  | 2022-11-23
21026994600 | EMER INSTALL 5'-4" PMMP | [5 empty] | 4622.23 | 5854.5805 | -1232.3505 |  |  |  | 2021-01-11 | REPLACED 5 FT MAIN TEST 90 LB FOR 20 MIN TEST ALL TEES AT 5 MIN TEST BYPASS 90 LB FOR 1 HR TEST ALL END CAPS AT OP FOR 5 MIN BAR HOLE BANKS NO GAS FOUND MARKER BALL AT TEES AND CPLG
21026994700 | EMER - RETIRE 5'-4" PMP | [5 empty] | 102.95 | 103.8156 | -0.86559 |  |  |  | 2021-01-11 | CUT OUT CRACKED MAIN PUT ON BYPASS AND PUT IN 5 FT OF MAIN
21026996200 | INSTALL 2150'-2" PMMP | [5 empty] | 336530.83 | 214604.887 | 121925.943 |  |  |  | 2021-03-05 | JOB ORDER CODED COMPLETE AT TIME OF MAIN LINE COMPLETION, STILL WORKING ON SERVICES. SPENDLE 3/10/21 20APR21: SEVERAL ATTEMPTS WERE MADE TO REVISE THIS JOB ORDER TO CAPTURE OVERRUN, HOWEVER, OUTSTANDING INVOICES PREVENTED ENGINEERING FROM DOING SO. . 29APR21: OVERRUN EXPLANATION = FISHEL'S CONTRACT OVER $21K DUE TO INCREASED LABOR & MATERIALS TO PREP STAGING (STONE, FENCING, AND ENVIRONMENTAL BMPS) ALONG WITH A LOT MORE FLAGGING BY AWP FOR TRAFFIC CONTROL. BUCHANAN'S COST FOR SEWER INSPECTION & CAMERING WAS WAY UNDERESTIMATED CONTRIBUTING ANOTHER $33K TO THE OVERRUN. LASTLY, COMPANY LABOR OVERRAN BY $14K FROM WHAT WAS ORIGINALY ESTIMATED. THESE COSTS PLUS OH'S MAKE UP THE OVERRUN (BKSLONE).
21026996400 | EMER - ABANDON 37'-2" PIP | [5 empty] | 860.91 | 2872.6664 | -2011.7564 |  |  |  | 2021-01-25 | ABANDONED 37' OF 020 MAIN DUE TO FAC DAM. WORKED WITH TIE IN PLAN. INSTALLED LINE MARKER AT EOM. UPDATED MAPPING. SOAP TEST END CAP AT OP.TEST OK. BHB NGF.
21026997000 | INSTALL 1100'-2" PMP | [5 empty] | 532822.99 | 340896.6283 | 191926.3617 |  |  |  | 2021-04-27 | 14JUN21: UNDERRUN EXPLANATION = 1) ASPHALT MILL & OVERLAY WAS MISCALCULATED RESULTING IN AN ADDITIONAL $120K AND 2) FLAGGING TIME WAS UNDERESTIMATED RESULTING IN AND ADDITIONAL $35K. THESE COSTS, ALONG WITH ASSOCIATED OH'S, MAKE UP THE MAJORITY IF THE $166K OVERRUN. THE ERROR IN PAVING COSTS WAS NOT NOTICED UNTIL AFTER THE ORIGINAL JOB ORDER WAS EXECUTED THEREBY PROHIBITING PROCESSING A REVISION (BKSLONE).
21026997101 | INSTALL 125' OF 4"PMMP MAIN | [5 empty] | 118779.98 | 111178.7891 | 7601.1909 |  |  |  | 2021-08-30
21026997801 | INSTALL 4600' OF 2"/6"PMMP | [5 empty] | 2405348.07 | 2229421.3209 | 175926.7491 |  |  |  | 2023-10-19
21026997900 | RETIRE 6300' OF 4"/6"CILP MN | [5 empty] | 747.19 | 126.9534 | 620.2366 |  |  |  | 2023-10-19
21026998000 | CONVERT TO GMB ACCOUNT | [5 empty] | 6412.15 | 4845.4443 | 1566.7057 |  |  |  | 2021-04-07 | CONVERTED FROM CAB TO GMB ACCOUNT CCC TICKET NOT REQUIRED THIS IS NON-SCADA MONITORED
21026998100 | INSTALL 180' OF 2"PMMP MAIN | [5 empty] | 36764.99 | 11159.7406 | 25605.2494 |  |  |  | 2021-02-26
21026998900 | RETIRE 3"PLP SERVICE LINE | [5 empty] | 9085.7 | 9329.0565 | -243.3565 |  |  |  | 2022-09-20
21026999500 | INSTALL 175' OF 2"PMMP | [5 empty] | 16309.78 | 9497.8185 | 6811.9615 |  |  |  | 2021-05-03 | 174 '2"PLASTIC MED -DENSITY YELLOW PIPE INSTALLED BY BIRECTIONAL BOREBY STA NLEY PIPELINE.
21026999600 | INSTALL 90' OF 4"CS/PMMP MAIN | [5 empty] | 47302.77 | 68922.5327 | -21619.7627 |  |  |  | 2021-11-11 | NEW MAIN GASED UP 11-11-21
22026158400 | INSTALL 1200' OF 2"PMMP MAIN | [5 empty] | 29132.57 | 35742.3291 | -6609.7591 |  |  |  | 2022-03-18
22026158800 | INSTALL 540' OF 4"/8"PMMP MAIN | [5 empty] | 378932.24 | 262444.8259 | 116487.4141 |  |  |  | 2023-03-03 | TWALKER/KY 09-27-23: LEVEL 1 VARIANCE FORM ADDED TO WMS.DOCS JOB OVER RUN DUE TO ADDITIONAL PAVING/RESTORATION REQUIREMENT BY THE CITY INCREASED CONTRACT COST BY $30,000, ALSO SEGA $12,000 HIGHER THAN ESTIMATE. COMPANY LABOR INCREASED BY $25,000 DUE TO ADDITIONAL COMPANY LABOR REQUIRED. TWALKER/KY 10-27-23: LEVEL 2 VARIANCE REPORTED ADDED TO WMS.DOCS, JOB OVER DUE TO CITY PAVING AND RE-PAVING REQUIREMENT.
22026158900 | RETIRE 594' OF 8"BSMP MAIN | [5 empty] | 0 | 72.8047 | -72.8047 |  |  |  | 2023-03-03
22026160800 | EMER-INSTALL 5' OF 2"PMMP MAIN | [5 empty] | 2109.29 | 3947.9695 | -1838.6795 |  |  |  | 2022-01-12
22026160900 | EMER-RETIRE 5' OF 2"PAMP MAIN | [5 empty] | 0 | 69.6571 | -69.6571 |  |  |  | 2022-01-12
22026162000 | RETIRE 110' OF 2"CSHP MAIN | [5 empty] | 716.93 | 105.0102 | 611.9198 |  |  |  | 2022-06-28
22026162102 | INSTALL 8150' OF 2"/4"PMMP | [5 empty] | 756346.06 | 751182.165 | 5163.895 |  |  |  | 2023-11-30
22026162200 | RETIRE 4600' OF 4"/6"BSLP MAIN | [5 empty] | 1442.96 | 105.0102 | 1337.9498 |  |  |  | 2023-11-30
22026162500 | INSTALL 8" STOPPLE FITTING | [5 empty] | 25751.7 | 14352.6857 | 11399.0143 |  |  |  | 2022-02-10
22026162600 | RETIRE 44' OF 8"BSMP MAIN | [5 empty] | 0 | 105.0102 | -105.0102 |  |  |  | 2022-02-10
22026163200 | INSTALL 775' OF 2"PMMP MAIN | [5 empty] | 49762.97 | 80533.8181 | -30770.8481 |  |  |  | 2023-03-17 | TWALKER/KY- 09-27-23: LEVEL 1 VARIANCE ADDED TO WMS.DOCS JOB UNDER RUN WAS DUE TO NO FLAGGING OR STREET REPAIRS REQUIRED SINCE ALL MAIN WAS INSTALLED BY DIRECTIONAL BORE WHICH LOWER CONTRACT COST $23,000
22026163300 | RETIRE 800' OF 4"BSLP MAIN | [5 empty] | 21.45 | 105.0102 | -83.5602 |  |  |  | 2023-03-17
22026163700 | RETIRE 4"BSLP SERVICE LINE | [5 empty] | 1327.16 | 105.0102 | 1222.1498 |  |  |  | 2022-04-08 | CAPITAL SERVICE LINE WAS ABANDONED WITH JOB NUMBER 18-0268433-01 TIE IN A1A2. LSHARON
22026164400 | EMER - INSTALL 10'-2" PMMP | [5 empty] | 10363.46 | 13748.6188 | -3385.1588 |  |  |  | 2022-02-08
22026164500 | EMER - RETIRE 10'-2" PMP | [5 empty] | 111.44 | 109.7476 | 1.6924 |  |  |  | 2022-02-08
22026164900 | EMER-INSTALL 4' OF 3"PMMP MAIN | [5 empty] | 15536.92 | 14982.0392 | 554.8808 |  |  |  | 2022-02-17 | INSTALLED 4' OF 030 P DUE TO EXC DMG TEST AT 90# FOR 20 MIN PER FOL APPROVA L, SOAP TEST TWO 030 EF CPLGS AT OP FOR 5 MIN OK. TEST FOR SEC DMG OK. WHIMES 02/17/2022
22026165000 | EMER-RETIRE 4' OF 3"PMP MAIN | [5 empty] | 119.3 | 100.2728 | 19.0272 |  |  |  | 2022-02-17 | COMPLETED W/ JO 22026164900
22026165400 | RETIRE REG STATION #1203 | [5 empty] | 5686.24 | 4576.607 | 1109.633 |  |  |  | 2022-06-22 | STATION RETIRED ALL PIPEING REMOVED 06-22-2022 AJPARKS
22026165501 | INSTALL 3385' OF 2" PMMP | [5 empty] | 347952.13 | 345650.6876 | 2301.4424 |  |  |  | 2024-09-13
22026165600 | RETIRE 2715'-BSLP & 425'-PLP | [5 empty] | 1766 | 75.4968 | 1690.5032 |  |  |  | #N/A
22026166200 | INSTALL 20' OF 3"PMMP MAIN | [5 empty] | 23237.34 | 28323.8584 | -5086.5184 |  |  |  | 2022-05-04
22026166300 | RETIRE 12' OF 3"PMP MAIN | [5 empty] | 90.73 | 62.3079 | 28.4221 |  |  |  | 2022-05-05
22026166900 | INSTALL 2010' - 8" & 6" PMMP | [5 empty] | 525084.39 | 400337.2549 | 124747.1351 |  |  |  | 2023-12-19
22026167000 | RETIRE 2260' OF 4-8" BSLP | [5 empty] | 0 | 89.0305 | -89.0305 |  |  |  | 2023-12-19
22026167200 | INSTALL 720'- 4" PMMP | [5 empty] | 293269.78 | 309266.4996 | -15996.7196 |  |  |  | 2023-02-13 | ADETOMIWA FALADE 8/29/2023. JOB IS CURRENTLY SHOWING LEVEL 1 UNDER RUN BUT $35,000 IN PAVING WAS PROCESSED THIS WEEK. ONCE THIS PAYMENT IS APPLIED TO THIS JOB ORDER, NO VARIANCE PAPERWORK SHOULD BE REQUIRED. THE PAVING WAS PERFORMED BY PRIVATE CONTRACTOR INSTEAD OF PIPELINE CONTRACTOR WHICH SAVED THE COST OF PAVING.
22026167300 | RETIRE 720'-4" BS-LP | [5 empty] | 0 | 62.2578 | -62.2578 |  |  |  | 2023-02-13
22026167400 | EMER - INSTALL 5'-3" PMLP | [5 empty] | 0 | 3781.5061 | -3781.5061 |  |  |  | 2022-02-09
22026167500 | EMER - RETIRE 5'-3" PLP | [5 empty] | 0 | 109.7476 | -109.7476 |  |  |  | 2022-02-09
22026167600 | INSTALL 6' OF 3"PMLP MAIN | [5 empty] | 8748.35 | 16229.6788 | -7481.3288 |  |  |  | 2022-10-27 | CUT OUT 4' SECTION OF 3" MAIN. TESTED DROP IN PIECE 90#5MINS, TG. ST LTI, TG. BHBNGF. 2 17LB ANODES INSTALLED. PRSSURE NEVER DROPPED ON GAUGES. PURGED ALL AIR OUT BEFORE GAS UP. R.CRAWFORD 10-27-22
22026167700 | RETIRE 6' OF 3"CSLP MAIN | [5 empty] | 9674.55 | 100.2728 | 9574.2772 |  |  |  | 2022-10-27 | CUT OUT 4' SECTION OF LEAKING 3" MAIN, TESTED DROP IN PIECE 90#20MINS, TG. ST LTI. TG. BHBNGF. INST. 2 17LB ANODES. PRESSURE NEVER DROPPED ON GAUGES. PURGED ALL AIR OUT BEFORE GAS UP. R.CRAWFORD 10-27-22
22026168800 | ST. JAMES HVAC UPGRADE | [5 empty] | 24656.22 | 37587.0767 | -12930.8567 |  |  |  | 2022-08-05 | MONITOR WHILE ACP SWAPS RTU STATION SET TO LOCAL MODE GC ADVISED CC 58614 UPGRADE RTU ON 3-16-22 JOSH MULLINS
22026171100 | INSTALL 2715' OF 2"/4"PMMP | [5 empty] | 734298.53 | 852559.9514 | -118261.4214 |  |  |  | 2024-05-23 | TWALKER/KY 08-16-24: FINAL PAVING RESTORATION FOR THIS PROJECT WILL NOT HAPPEN UNTIL 2025 DUE TO PLANNED WATER COMPANY PROJECT ON SAME STREETS AND CITY OF LEXINGTON SHARED PAVING REQUIREMENTS
22026171200 | RETIRE 2300' OF 3"/6"BSLP | [5 empty] | 220 | 75.4968 | 144.5032 |  |  |  | #N/A
22026172800 | RETIRE 5' OF 3"PLP S/L | [5 empty] | 0 | 58.5954 | -58.5954 |  |  |  | 2022-03-16 | ABANDONED CAPITAL SERVICE LINE WITH ABANDON JOB # 18-0268434-00. LSHARON
22026172900 | INSTALL 5' OF 4"PMLP S/L | [5 empty] | 3113 | 13312.2384 | -10199.2384 |  |  |  | 2022-03-15
22026173000 | 2022 SCADA VISABILITY PROGRAM | [5 empty] | 47294.28 | 30164.6195 | 17129.6605 |  |  |  | 2022-10-04 | CC# 66617 INSTALLED NEW MIWI350 SMCHOLAN 10-4-2022
22026173600 | 2022 SCADA VISIBILITY PROGRAM | [5 empty] | 25271.05 | 31941 | -6669.95 |  |  |  | 2022-09-28 | INSTALLED NEW MIWI350 EBLANTON 9-28-2022
22026173800 | 2022 SCADA VISIBILITY PROGRAM | [5 empty] | 24972.3 | 30164.6195 | -5192.3195 |  |  |  | 2022-09-29 | WITH ACP CONTRACTOR WHILE THEY INSTALL POLE FOR COMM EQUIPMENT CC 66318 05-10-2022 RHAYES CC 1924 INSTALLED MIWI350 UNABLE TO PERFORM P2P NDAVIS WORKING ON TICKET MONITORED 30 MINUTES RHAYES 09-29-2022
22026174400 | 2022 SCADA VISIBILITY PROGRAM | [5 empty] | 28643.37 | 29658.8599 | -1015.4899 |  |  |  | 2022-10-11 | INSTALL POLES FOR COMM EQUIPMENT 05-10-2022 CC 66285 RHAYES
22026174500 | 2022 SCADA VISIBILITY PROGRAM | [5 empty] | 29029.69 | 29658.8599 | -629.1699 |  |  |  | 2022-10-05 | CC# 66436 CC# 79698 CC# 2587 CMCOX 10/5/22 INSTALLED NEW MIWI350 CCOX 10-05-2022
22026174600 | 2022 SCADA VISIBILITY PROGRAM | [5 empty] | 38527.05 | 29658.8599 | 8868.1901 |  |  |  | 2022-09-27 | CC# 66475 CC#1503 INSTALLED NEW MIWI350 WITH SUPER SOLAR KIT 9-27-22 CCOX
22026177900 | INSTALL 8' OF 6"PMMP MAIN | [5 empty] | 36900.11 | 29164.4 | 7735.71 |  |  |  | 2022-07-11
22026178000 | RETIRE 4' OF 6"CSMP MAIN | [5 empty] | 876.45 | 75.4968 | 800.9532 |  |  |  | 2022-07-11
22026178100 | INSTALL 20' OF 6"PMLP MAIN | [5 empty] | 14787.97 | 11448.7503 | 3339.2197 |  |  |  | 2022-05-25
22026178500 | INSTALL 44'-6" PMMP | [5 empty] | 77349.62 | 72684.0107 | 4665.6093 |  |  |  | 2022-08-23
22026178600 | RETIRE 26'-6" CSMP | [5 empty] | 1859.72 | 73.9724 | 1785.7476 |  |  |  | 2022-08-23
22026178900 | INSTALL 620' OF 12"CSHP MAIN | [5 empty] | 268220 | 330116.9371 | -61896.9371 |  |  |  | 2023-06-30
22026179100 | RETIRE 520' OF 12"MJBSHP | [5 empty] | 3152.18 | 131.2422 | 3020.9378 |  |  |  | 2023-06-30
22026179200 | INSTALL 50' OF 6"PMLP S/L | [5 empty] | 45896.9 | 47001.2003 | -1104.3003 |  |  |  | #N/A
22026179300 | RETIRE 82'-2"&4" PMMP | [5 empty] | 82.8 | 73.9724 | 8.8276 |  |  |  | 2022-04-02
22026180100 | INSTALL 805' OF 2"/4"PMMP MAIN | [5 empty] | 116760.6 | 54482.6036 | 62277.9964 |  |  |  | 2022-09-07 | TWALKER/KY 09-08-22: PROJECT OVER RUN DUE TO ROCK ENCOUNTERED IN CONSTRUCTI ON REQUIRING ROCK BORE AND OPEN CUT ROCK WHICH INCREATED CONTRACT COST BY $30,000. WMS WOULD NOT ALLOW REVISION OF PROJECT DUE TO UNPAID INVOICES. COMPANY LABOR INCREASED BY OVER $16,000 DUE TO EXTRA TIME FOR CONSTRUCTION AND SEGA WAS $6000 THAN ESTIMATE TWALKER/KY 01-24-23: LEVEL 2 VARIANCE REPORT ADDED TO WMS.DOCS.
22026180900 | EMER-INSTALL 4' OF 2"PMMP | [5 empty] | 3753.68 | 3916.7503 | -163.0703 |  |  |  | 2022-02-28
22026181000 | EMER-RETIRE 4' OF 2"PMMP | [5 empty] | 0 | 75.4968 | -75.4968 |  |  |  | 2022-02-28
22026181300 | RETIRE PIT REG STATION 1124 | [5 empty] | 4926.17 | 5746.3751 | -820.2051 |  |  |  | #N/A | CCC# 72702 RETIRED REG STATION, REMOVED REGS AND BLIND PLATED VAVLES, REMOVED OIL FROM PRV AND PLUGGED INSIDE PIT, PREFORMED LEAK TEST ON ALL ON CONNECTIONS, CCC 73281 CMCHOLAN 5-17-24 1600
22026181900 | LAB EQUIPMENT INSTALL | [5 empty] | 5312.84 | 15945.3111 | -10632.4711 |  |  |  | 2022-09-15
22026182000 | INSTALL 2185' OF 2" PMMP | [5 empty] | 141899.3 | 110360.5276 | 31538.7724 |  |  |  | 2022-09-27 | AWEBER 01/24/2023 - PROJECT OVERRUN DUE PRIMARILY TO LAND OWNER ISSUES & EXPANSIVE SEWER LINE CAMERA WORK PERFORMED BY BUCHANON. EASEMENT FROM FIRST LAND OWNER FELL THROUGH DUE TO HOA VOTE, INCREASING INSTALLATION BY +200' & PRIVATE EASEMENT. PROJECT ENCOUNTERED ROCK BORE ADDING ~34 HOURS TO DURATIO N. OVERRUN BUCHANON COST $17K + LAND COST $11K & INCREASED SEGA RATE $6K LE D TO VARIANCE.
22026182800 | EMER-INSTALL 3' OF 2"PMMP | [5 empty] | 4419.13 | 4826.1382 | -407.0082 |  |  |  | 2022-04-20 | INSTALLED 3' OF 2" PMMP DUE TO EXCAVATION DAMAGE, TESTED MAIN PIPE AT 90# F OR 20 MIN PER FOL APPROVAL OK, SOAP TEST 2 020 EF CPLGS AT OP FOR 5 MIN OK. INSTALLED MARKER BALLS ON CPLGS. MAP REVISED. WHIMES
22026182900 | EMER-RETIRE 3' OF 2"PMMP | [5 empty] | 2.72 | 74.2578 | -71.5378 |  |  |  | 2022-04-20 | RETIRED 3' OF 020 PMMP DUE TO EXCAVATION DAMAGE. WHIMES 04/20/2022
22026183100 | INSTALL 3090' OF 2-4" PMMP | [5 empty] | 610263.34 | 533028.4351 | 77234.9049 |  |  |  | 2023-09-08 | PROJECT COMPLETE
22026183200 | RETIRE 3765' OF 2-4" CS & PMMP | [5 empty] | 273.03 | 138.8485 | 134.1815 |  |  |  | 2023-09-08 | PROJECT COMPLETED
22026183301 | SMRP INSTALL 1120' 8-12" CSHP | [5 empty] | 1650295.52 | 1201596.3067 | 448699.2133 |  |  |  | 2024-03-06
22026183400 | RETIRE 702' OF 6" BSHP | [5 empty] | 220 | 121.7239 | 98.2761 |  |  |  | #N/A
22026183600 | INSTALL 1700'-2" PMMP | [5 empty] | 51519.58 | 46580.9585 | 4938.6215 |  |  |  | 2022-06-22
22026183700 | INSTALL 100' OF 2"PMMP MAIN | [5 empty] | 19814.52 | 12739.3747 | 7075.1453 |  |  |  | 2022-10-11 | INSTALLED 199' OF 020 MAIN. TEST 199' OF MAIN FOR 1HR AT 90LBS. FOL APPROVED.SOAP TEST 2'' EFC AT OP OF FINAL TIE IN. SOAP TEST END CAP ON MONITORING GAUGE AT OP.TEST OK.
22026184600 | INSTALL 64' OF 2"PMMP MAIN | [5 empty] | 16772.5 | 17899.1411 | -1126.6411 |  |  |  | 2022-07-11
22026184700 | RETIRE 52' OF 2"PMMP MAIN | [5 empty] | 0 | 74.2578 | -74.2578 |  |  |  | 2022-07-11
22026184800 | INSTALL 3775'-2" PMMP | [5 empty] | 689655.43 | 567138.2381 | 122517.1919 |  |  |  | 2023-04-12
22026184900 | RETIRE 3315'-2"&4"BSLP | [5 empty] | 23.53 | 72.7393 | -49.2093 |  |  |  | 2023-04-12
22026185001 | INSTALL 260' OF 2"PMMP MAIN | [5 empty] | 30483.21 | 27065.0582 | 3418.1518 |  |  |  | 2022-10-07
22026185301 | INSTALL 875' OF 2"PMMP MAIN | [5 empty] | 69561.33 | 74170.089 | -4608.759 |  |  |  | 2022-11-18
22026186000 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 3201.06 | 5480.5156 | -2279.4556 |  |  |  | 2022-05-27 | ACP REMOVED ERX REPLACED WITH MIWI CCOX RHAYES 05-27-2022
22026186100 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 175.52 | 124.5156 | 51.0044 |  |  |  | 2022-05-27 | ACP REPLACED ERX WITH MIWI RHAYES CCOX 05-27-2022 ACP REPLACED ERX WITH MIWI RHAYES CCOX 05-27-2022
22026186600 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 616.42 | 4216.5438 | -3600.1238 |  |  |  | 2022-05-19 | INSTALLED MIWI 350 AND TUBING, CCC 67481 CMCHOLAN 5-19-2022 NOT ON SITE, TURNED IN PAPERWORK IN WINCHESTER, NO CCC TICKET, CMCHOLAN 5-20-2022
22026186700 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 485.53 | 124.5156 | 361.0144 |  |  |  | 2022-05-19 | REMOVED ERX, CCC 67481 CMCHOLAN 5-19-2022 RWILLIAMS EX CAPITAL JOB
22026187200 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 1831.39 | 4745.0565 | -2913.6665 |  |  |  | 2022-05-26 | CCC# 68726 INSTALLED NEW MIWI 350 AJPARKS
22026187300 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 185.7 | 124.5156 | 61.1844 |  |  |  | 2022-05-26 | CCC# 68726 RETIRED ERX 05/26/2022 APARKS
22026187800 | INSTALL 10' OF 4"PMLP MAIN | [5 empty] | 29076.83 | 18153.0818 | 10923.7482 |  |  |  | 2022-05-25
22026187900 | RETIRE 8' OF 4"PMLP MAIN | [5 empty] | 0 | 74.2578 | -74.2578 |  |  |  | 2022-05-25
22026192300 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 281.87 | 4801.1928 | -4519.3228 |  |  |  | 2022-06-13 | CHANGED ERX TO MIWI 350, P2P OK, CCC 70245 CMHOLAN 6-13-2022
22026192400 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 443.37 | 124.8731 | 318.4969 |  |  |  | 2022-06-13 | REMOVED ERX TO INSTALL MIWI, CCC 70245 CMCHOLAN 6-13-2022 INSTALLED NEW MIWI350
22026195000 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5607.88 | 4801.1928 | 806.6872 |  |  |  | 2022-08-29 | SWAP COMP. PARKS 08-29-22 1545 CCC# 78985 RETIRED OLD ERX INSTALLED NEW MIWI350 AJPARKS 8-29-2022
22026195100 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 248.95 | 124.8731 | 124.0769 |  |  |  | 2022-08-29 | REMOVAL COMP. APARKS 08-29-22 1044 CCC# 78985 RETIRED OLD ERX INSTALLED NEW MIWI350 AJPARKS 8-29-2022
22026197100 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5373.93 | 4801.1928 | 572.7372 |  |  |  | 2022-09-07 | CCC 79940 RETIRED OLD ERX INSTALLED NEW MIWI350 9-7-2022
22026197200 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 251.1 | 124.8731 | 126.2269 |  |  |  | 2022-09-07 | CCC 79940 RETIRED OLD ERX INSTALLED NEW MIWI350 EBLANTON 9-7-2022
22026197300 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 6904.6 | 4801.1928 | 2103.4072 |  |  |  | 2022-10-19 | CC# 3980 CMCOX 10/19/22 INSTALLED NEW MIWI350 CCOX 10-19-22
22026197400 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 305.47 | 124.8731 | 180.5969 |  |  |  | 2022-10-19 | CC# 3980 CMCOX 10/19/22 RETIRED OLD ERX CCOX 10-19-22
22026197700 | INSTAL 3'-2" PMMP | [5 empty] | 1311.83 | 2387.9592 | -1076.1292 |  |  |  | 2022-06-07 | HIT MAIN BY CONCRETE STAKE.MADE SAFE BY SQUEEZING OFF IN TWO BELL HOLES. REPLACED DAMAGED SECTION OF PIPE.TESTED 10FT OF 020 AND PURGE TEE FOR 1HR 90LBS.TEST OK.SOAP TEST END CAP AND 2EFC'S CPLGS AT OP.TEST OK BHB NGF
22026197800 | RETIRE 3'-2" PMMP | [5 empty] | 914.45 | 76.9137 | 837.5363 |  |  |  | 2022-06-07 | HIT MAIN BY CONCRETE STAKE.MADE SAFE BY SQUEEZING OFF IN TWO BELL HOLES. REPLACED DAMAGED SECTION OF PIPE.TESTED 10FT OF 020 AND PURGE TEE FOR 1HR 90LBS.TEST OK.SOAP TEST END CAP AND 2EFC'S CPLGS AT OP.TEST OK BHB NGF
22026198601 | INSTALL 1900' OF 2"PMMP MAIN | [5 empty] | 71556.52 | 50146.9852 | 21409.5348 |  |  |  | 2022-10-21
22026199100 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5602.7 | 4801.1928 | 801.5072 |  |  |  | 2022-09-02 | CCC 79615 RETIRED OLD ERX INSTALLED NEW MIWI350 EBLANTON 9-2-2022
22026199200 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 880.44 | 124.8731 | 755.5669 |  |  |  | 2022-09-02 | CCC 79615 RETIRED OLD ERX INSTALLED NEW MIWI350 EBLANTON 9-2-2022
22026200500 | RETIRE 2' OF 3"PLP S/L | [5 empty] | 0 | 62.4365 | -62.4365 |  |  |  | 2022-09-12
22026200600 | INSTALL 15' OF 3"/4"PMLP S/L | [5 empty] | 10449.59 | 11118.4162 | -668.8262 |  |  |  | 2022-08-15
22026202200 | INSTALL 125' OF 2" PMMP MAIN | [5 empty] | 11459.71 | 8841.6395 | 2618.0705 |  |  |  | 2022-07-14
22026202900 | RETIRE 135' OF 2"PMP MAIN | [5 empty] | 2.29 | 78.4365 | -76.1465 |  |  |  | 2022-09-07
22026203900 | RETIRE PAPER GAUGE | [5 empty] | 0 | 78.4365 | -78.4365 |  |  |  | 2022-10-05 | RETIRED PAPER CHART CCOX10-05-2022
22026204000 | RETIRE PAPER GAUGE | [5 empty] | 157.99 | 78.4365 | 79.5535 |  |  |  | 2022-09-27 | RETIRED PAPER CHART CHRIS COX 9-27-22
22026204200 | RETIRED GAUGE | [5 empty] | 0 | 76.9137 | -76.9137 |  |  |  | 2022-10-04 | RETIRED PAPER CHARTS SMCHOLAN 10-04-2022
22026206900 | EMER-INSTALL 16' OF 4"/6"PMLP | [5 empty] | 11009.07 | 8399.775 | 2609.295 |  |  |  | 2022-07-15 | LEAKING POSI HOLD COUPLING.LEAKING OUT OF FITTING ON COUPLING. REPLACED 6'' TEE AND 19FT OF MAIN.TESTED MAIN FOR 1HR AT 90LBS.TEST OK. SOAP TEST FINAL TIE INS AT OP FOR 5MINS AT OP.TEST OK. BHB NGF.
22026207000 | EMER-RETIRE 14' OF 6"BSLP | [5 empty] | 11230.19 | 60.0112 | 11170.1788 |  |  |  | 2022-07-15 | LEAKING POSI HOLD COUPLING.LEAKING OUT OF FITTING ON COUPLING. REPLACED 6'' TEE AND 19FT OF MAIN.TESTED MAIN FOR 1HR AT 90LBS.TEST OK. SOAP TEST FINAL TIE INS AT OP FOR 5MINS AT OP.TEST OK. BHB NGF.
22026208900 | EMER - INSTALL ~10'-8" CSHP | [5 empty] | 59795.62 | 32930.2498 | 26865.3702 |  |  |  | 2022-07-07
22026209400 | RETIRE CHAIN LINK FENCE | [5 empty] | 0 | 65.0112 | -65.0112 |  |  |  | 2022-06-28
22026209500 | RETIRE CHAIN LINK FENCE | [5 empty] | 0 | 65.0112 | -65.0112 |  |  |  | 2022-05-10
22026209800 | RETIRE VAULT STRUCTURE | [5 empty] | 0 | 1027.5809 | -1027.5809 |  |  |  | 2022-11-16 | PIT RETIRED AND FILLED IN
22026209900 | RETIRE VAULT STRUCTURE | [5 empty] | 2265.12 | 859.5809 | 1405.5391 |  |  |  | #N/A
22026210000 | RETIRE ELECTRONICS | [5 empty] | 249.16 | 65.0112 | 184.1488 |  |  |  | 2022-07-14 | RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07-14-2022
22026210100 | EMER - INSTALL 6'-4" PMMP | [5 empty] | 5514.88 | 4810.9373 | 703.9427 |  |  |  | 2022-07-26 | DAMAGED SECTION OF PIPE DUE TO EXCAVATOR ERROR.MADE SAFE BY SQUEEZING OFF IN BELLHOLES.OC 16FT NEW MAIN DUE TO EXCAVATION WHERE DAMAGE WAS TOO DEEP. TESTED MAIN 1HR AR 90LB.TEST OK.SOAP TEST EFC'SAT OP.TEST OK BHB NGF
22026210200 | EMER - RETIRE 6'-4" PMMP | [5 empty] | 95.05 | 63.5475 | 31.5025 |  |  |  | 2022-07-26 | DAMAGED SECTION OF PIPE DUE TO EXCAVATOR ERROR.MADE SAFE BY SQUEEZING OFF IN BELLHOLES.OC 16FT NEW MAIN DUE TO EXCAVATION WHERE DAMAGE WAS TOO DEEP. TESTED MAIN 1HR AR 90LB.TEST OK.SOAP TEST EFC'SAT OP.TEST OK BHB NGF
22026210301 | INSTALL 850' OF 4"PMMP MAIN | [5 empty] | 173794.47 | 192098.991 | -18304.521 |  |  |  | 2023-01-23
22026210600 | EMER-RETIRE 50' OF 3"BSLP MAIN | [5 empty] | 2854.75 | 5032.3621 | -2177.6121 |  |  |  | 2022-09-12
22026211400 | PAPER ONLY-RETIRE MP MAIN | [5 empty] | 0 | 65.0112 | -65.0112 |  |  |  | 2022-06-23
22026212500 | REPLACE VALVES AT R-1084 | [5 empty] | 9402.89 | 14531.0267 | -5128.1367 |  |  |  | 2023-09-06 | HELP CCOX WITH VALVE REPLACEMENT, CMCHOLAN 9-5-23 1600 CC# 43383 PAPERWORK ONLY. NO CC# REQUIRED. NOT ON SITE.
22026212600 | RETIRE STATION VALVES R-1084 | [5 empty] | 1269.98 | 119.4953 | 1150.4847 |  |  |  | 2023-09-06
22026213000 | RETIRE 2015'-8/4/2" BSMP/CSMP | [5 empty] | 220 | 89.0305 | 130.9695 |  |  |  | 2023-12-19
22026213100 | RETIRE 3"BSMP SERVICE LINE | [5 empty] | 0 | 63.4096 | -63.4096 |  |  |  | 2023-12-06
22026213200 | INSTALL 30' OF 2-4" PMMP S/L | [5 empty] | 33540.05 | 27880.5873 | 5659.4627 |  |  |  | 2023-12-06
22026214700 | ST. JAMES RTU PANEL | [5 empty] | 0 | 55.5311 | -55.5311 |  |  |  | 2022-08-05 | UPGRADED RTU JOSH MULLINS
22026214800 | EMER INSTALL 2' - PMMP | [5 empty] | 8176.85 | 2418.3858 | 5758.4642 |  |  |  | 2022-07-27
22026214900 | EMER RETIRE 2'-PMP | [5 empty] | 0 | 84.9152 | -84.9152 |  |  |  | 2022-07-27
22026215000 | EMER INSTALL 2'-4" PMLP | [5 empty] | 9400.14 | 3659.4376 | 5740.7024 |  |  |  | 2022-07-28
22026215100 | EMER RETIRE 2'-4" PLP | [5 empty] | 0 | 84.9152 | -84.9152 |  |  |  | 2022-07-28
22026215300 | EMER - INSTALL 20'-2" PMIP | [5 empty] | 15168.73 | 10433.2304 | 4735.4996 |  |  |  | 2022-07-21
22026215400 | EMER - RETIRE 5'-2" PMIP | [5 empty] | 0 | 80.5311 | -80.5311 |  |  |  | 2022-07-21
22026215500 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 6774.27 | 4479.378 | 2294.892 |  |  |  | 2022-07-21
22026215600 | EMER - RETIRE 5'-2" PMMP | [5 empty] | 0 | 84.9152 | -84.9152 |  |  |  | 2022-07-21
22026215900 | EMER-INSTALL 3' OF 2"PMMP MAIN | [5 empty] | 1854.5 | 3722.1191 | -1867.6191 |  |  |  | 2022-08-22 | REPLACED 3FT SECTION OF MAIN. TESTED NEW SECTION OF MAIN FOR 20MINS AT 90LBS.TEST OK SOAP TEST EFC'S AT OP FOR 5MINS.TEST OK. BHBNGF
22026216000 | EMER-RETIRE 3' OF 2"PAMP MAIN | [5 empty] | 143.19 | 84.9152 | 58.2748 |  |  |  | 2022-08-22 | REPLACED 3FT SECTION OF MAIN. TESTED NEW SECTION OF MAIN FOR 20MINS AT 90LBS.TEST OK SOAP TEST EFC'S AT OP FOR 5MINS.TEST OK. BHBNGF
22026216200 | INSTALL 950' OF 2"/4"PMMP MAIN | [5 empty] | 47379.78 | 39269.0655 | 8110.7145 |  |  |  | 2022-09-09
22026216900 | PAPER ONLY EXECUTE | [5 empty] | 0 | 84.9152 | -84.9152 |  |  |  | 2022-04-29
22026217300 | RETIRE 3"PLP SERVICE LINE | [5 empty] | 0 | 170.8304 | -170.8304 |  |  |  | 2022-09-08
22026217400 | RETIRE 6"PLP SERVICE LINE | [5 empty] | 827.26 | 144.8304 | 682.4296 |  |  |  | 2022-10-06
22026217800 | EMER-INSTALL 3' OF 4"PMLP MAIN | [5 empty] | 12300.82 | 6173.2589 | 6127.5611 |  |  |  | 2022-08-18 | LEAK CLEARED USING DPI D311930 PW
22026217900 | EMER-RETIRE 3' OF 4"BSLP MAIN | [5 empty] | 4448.33 | 170.8304 | 4277.4996 |  |  |  | 2022-08-18
22026218200 | RETIRE PAPER GUAGE | [5 empty] | 0 | 339.1994 | -339.1994 |  |  |  | 2022-07-28 | RETIRE PAPER CHART DUE TO ERX INSTALL AT ANOTHER STATION SMCHOLAN
22026218300 | RETIRE PAPER GAUGE | [5 empty] | 0 | 339.1994 | -339.1994 |  |  |  | 2022-07-28 | RETIRED PAPER CHART DUE TO ERX INSTALL AT ANOTHER LOCATION
22026218800 | INSTALL MI WIRELESS UNIT | [5 empty] | 10259.75 | 9310.2589 | 949.4911 |  |  |  | 2022-10-06 | CC# 79803 CC# 2675 CC# 2675 CMCOX 10/6/22 INSTALLED NEW MIWI350 CCOX 10-06-2022
22026219400 | INSTALL 380' OF 4"PMMP MAIN | [5 empty] | 172779.97 | 176409.6078 | -3629.6378 |  |  |  | 2023-06-08
22026219500 | RETIRE 380' OF 4"BSMP MAIN | [5 empty] | 91.2 | 89.0305 | 2.1695 |  |  |  | 2023-06-08
22026220800 | *PAPER ONLY* 2022 CAST IRON | [5 empty] | 0 | 295.7645 | -295.7645 |  |  |  | 2022-10-19
22026221200 | EMER - INSTALL 8'-6"PMMP | [5 empty] | 11736.48 | 32929.6819 | -21193.2019 |  |  |  | 2022-09-12 | TEST 6 IN MAIN AT 90 LB FOR 20 MIN SOAP TEST EFC AT OP FOR 5 MIN
22026221300 | EMER - RETIRE 8'-6" PMP | [5 empty] | 595.27 | 87.3224 | 507.9476 |  |  |  | 2022-09-12 | REMOVED 2 FT OF 6 IN DAMAGE PIPE
22026222800 | EMER-INSTALL 2' OF 4"PMMP MAIN | [5 empty] | 21988.24 | 23837.8998 | -1849.6598 |  |  |  | 2022-09-12
22026222900 | EMER-RETIRE 2' OF 4"PMMP MAIN | [5 empty] | 0 | 89.0305 | -89.0305 |  |  |  | 2022-09-12
22026223100 | EMER-INSTALL 3' OF 2"PMMP MAIN | [5 empty] | 4059.84 | 4624.3747 | -564.5347 |  |  |  | 2022-10-11 | COMPLETED PAPERWORK FOR JOB. R.CRAWFORD 10-11-22
22026223200 | EMER-RETIRE 3' OF 2"PMP MAIN | [5 empty] | 125.23 | 89.0305 | 36.1995 |  |  |  | 2022-10-17 | R.CRAWFORD
22026223600 | INSTALL 3000' OF 2"PMMP MAIN | [5 empty] | 80798.26 | 81410.7619 | -612.5019 |  |  |  | 2023-08-23
22026223700 | INSTALL 1296'-2"&4" PMMP | [5 empty] | 286331.62 | 306884.1479 | -20552.5279 |  |  |  | 2023-04-24
22026223800 | RETIRE 1212'-2",3"&4" CSMP | [5 empty] | 0 | 117.5985 | -117.5985 |  |  |  | 2023-04-24
22026223900 | INSTALL 1067'-4" PMMP | [5 empty] | 149979.89 | 181608.1135 | -31628.2235 |  |  |  | 2023-02-10
22026224000 | RETIRE 1150'-4" PMMP | [5 empty] | 0 | 72.8379 | -72.8379 |  |  |  | 2023-02-10
22026224201 | INSTALL 2300' OF 2"/4"PMMP | [5 empty] | 588766.29 | 524527.3047 | 64238.9853 |  |  |  | 2024-09-16
22026224300 | RETIRE 4500' OF 6"/4"BSLP MAIN | [5 empty] | 2115.84 | 114.3981 | 2001.4419 |  |  |  | #N/A
22026227000 | EMER-INSTALL 3' OF 2"PMMP MAIN | [5 empty] | 5707.92 | 5024.0582 | 683.8618 |  |  |  | 2022-09-30 | INST 3" OF 2 P MP MAIN PER GAS STANDARDS. MCRAIG 9/30/22
22026227100 | EMER-RETIRE 3' OF 2"PMP MAIN | [5 empty] | 316.08 | 74.3089 | 241.7711 |  |  |  | 2022-09-30 | ABN 3' OF 2" P MP MAIN DUE TO LEAK. PER GAS STANDARDS. MCRAIG 9/30/22
22026227200 | RETIRE ELECTRONICS | [5 empty] | 0 | 74.3089 | -74.3089 |  |  |  | 2022-12-15
22026228000 | EMER-INSTALL 3' OF 2"PMMP MAIN | [5 empty] | 2032.93 | 4027.0582 | -1994.1282 |  |  |  | 2022-10-06 | INSTALLED 3 FT OF 2 IN MAIN ON DAMAGE TEST FROM POINT A TO B 90 LB FOR 20 MIN TEST PURG TEE 90 LB FOR 5 MIN SOAP TEST 1 IN END CAP AT OP FOR 5 MIN SOAP TEST 2 EFC AT OP FOR 5 MIN BHB NO GAS FOUND
22026228100 | EMER-RETIRE 3' OF 2"PMMP MAIN | [5 empty] | 590.32 | 74.3089 | 516.0111 |  |  |  | 2022-10-04
22026228500 | INSTALL 167'-2" PMMP | [5 empty] | 84729.46 | 82180.2832 | 2549.1768 |  |  |  | 2024-06-20
22026228600 | RETIRE 136'-2" PMMP | [5 empty] | 50.09 | 72.8379 | -22.7479 |  |  |  | #N/A
22026230100 | EMER-INSTALL 2' OF 2"PMMP | [5 empty] | 2249.75 | 3890.5291 | -1640.7791 |  |  |  | 2022-10-06
22026230200 | EMER-RETIRE 2' OF 2"PMP MAIN | [5 empty] | 0 | 74.3089 | -74.3089 |  |  |  | 2022-10-06
22026231301 | INSTALL 925' OF 2"PMMP MAIN | [5 empty] | 388671.62 | 399340.9217 | -10669.3017 |  |  |  | 2024-09-20 | TWALKER/KY 10-25-24: JOB COST OVER RUN DUE TO CITY OF LEXINGTON REQUIRING MILL/PAVE FOR HIGH STREET WHICH ADDED $80,000 COPY INVOICE IN WMS.DOCS
22026231400 | RETIRE 975' OF 8"BSLP MAIN | [5 empty] | 110 | 121.7239 | -11.7239 |  |  |  | #N/A
22026231800 | RETIRE PAPER CHART | [5 empty] | 0 | 1093 | -1093 |  |  |  | 2022-08-23 | RETIRED PAPER CHART CCOX 8-23-22
22026232000 | RETIRE PAPER GAUGE | [5 empty] | 0 | 993 | -993 |  |  |  | 2022-07-26 | RETIRED PAPER CHART 7-26-22 CCOX
22026232100 | RETIRE PAPER GAUGE | [5 empty] | 719.12 | 993 | -273.88 |  |  |  | 2022-12-14 | REMOVED CHART, CCC 2244, CMCHOLAN 12-1-22
22026233800 | INSTALL 380' OF 4"PMLP SL | [5 empty] | 35845.97 | 36339.1396 | -493.1696 |  |  |  | #N/A
22026234001 | INSTALL 500' OF 2"/4"PMMP MAIN | [5 empty] | 95523.45 | 89921.6185 | 5601.8315 |  |  |  | 2023-04-25 | INSTALLED 422' 040-PMMP 185' 020-PMMP 607' TOTAL
22026239702 | INSTALL 8650' - 2,4,6" PMMP | [5 empty] | 1934664.05 | 1422627.7319 | 512036.3181 | 2025-01-01 | 2025-12-31 | 2025-02-01 | 2025-05-02
22026236600 | RETIRE 1300'- 6 5/8"BSHP MAIN | [5 empty] | 484.04 | 119.4953 | 364.5447 |  |  |  | #N/A
22026236700 | INSTALL 134'-4" PMLP | [5 empty] | 27660 | 32463.7981 | -4803.7981 |  |  |  | 2024-02-27 | INST 160'- 4" P LP MAIN FOR SEWER PROJECT PER ENGINEERED TIE-IN PLAN. MCRAIG 2/27/24
22026236800 | RETIRE 130'-4" PLP | [5 empty] | 10308.08 | 160.3697 | 10147.7103 |  |  |  | #N/A | RETIRE 148'- 4" P LP MAIN TO RELOCATE PER ENGINEERED PLAN. MCRAIG 2/27/24
22026238200 | INSTALL 205' OF 2"PMMP MAIN | [5 empty] | 13604.24 | 19394.2346 | -5789.9946 |  |  |  | 2023-01-16 | TWALKER/KY 01-20-23: ISSUED BACK ORDER REQUEST #52196 FOR THIS JOB
ANC32.0000.00020 | RICHMOND ROAD PHASE 2 2025 SMRP | [5 empty] | 1492718.41 | 1026516 | 466202.41 | 2025-01-01 | 2025-12-31 | 2025-09-25 | 2025-12-31
22026239800 | RETIRE 6065' - 4/6" BS/CS/PLP | [5 empty] | 149.74 | 139.1159 | 10.6241 |  |  |  | #N/A
22026240100 | GMB TO CAB CONVERSION | [5 empty] | 2136.59 | 238.427 | 1898.163 |  |  |  | 2023-04-04 | CONVERTED GMB TO CAB ACCOUNT, CMCHOLAN 4-4-23
22026240900 | PAPER ONLY EXECUTE | [5 empty] | 0 | 119.2135 | -119.2135 |  |  |  | 2022-11-30
22026241500 | INSTALL 40'-2" PMMP | [5 empty] | 14054.24 | 23266.5784 | -9212.3384 |  |  |  | 2023-03-23
22026241600 | RETIRE 30'-2" PMMP | [5 empty] | 193.2 | 124.7348 | 68.4652 |  |  |  | 2023-03-21
22026242301 | INSTALL 8"POLY VALVE W/10"SPH | [5 empty] | 84736.28 | 63212.0666 | 21524.2134 |  |  |  | 2023-09-07
22026242500 | EMER-RETIRE 385' OF 2"/3"PAIP | [5 empty] | 5628.45 | 5363.3319 | 265.1181 |  |  |  | 2022-12-13
22026242600 | INSTALL 500' - 4" PMMP | [5 empty] | 115979.71 | 97718.819 | 18260.891 |  |  |  | 2023-05-26
22026242700 | INSTALL 350' OF 8"CSHP MAIN | [5 empty] | 383081.64 | 370158.4472 | 12923.1928 |  |  |  | 2023-08-31
22026242800 | RETIRE 326' OF 8"CSHP MAIN | [5 empty] | 0 | 114.3981 | -114.3981 |  |  |  | 2023-08-31
22026243000 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 20860 | 29336.8866 | -8476.8866 |  |  |  | 2023-04-20 | CC# 23362 CCC# 24092 DID NOT ENTER STATION. CWEMPE 4/27/23
22026243100 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 18742.99 | 21860.8866 | -3117.8966 |  |  |  | 2023-04-26 | CC 22894 WELDED TAPS ON COULD NOT PRESSURE TEST DUE TO TIME CONSTRAINTS PER RTWAIT CCC# 24089
22026243200 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 20634.93 | 25283.8866 | -4648.9566 |  |  |  | 2023-04-11 | CCC# 21042 CC 22745 WELD AND TEST STEEL TIE TAPS INLET 240# OUTLET 90# 5MINS RHAYES DMARTIN 03-30-2023 NOT ONSITE COLLECTING PARTS FOR JOB CCC#27524
22026243300 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 20996.21 | 20719.8866 | 276.3234 |  |  |  | 2023-04-12 | CCC# 21042 CC#23191 CC#24679 CC# 27421 CMCOX 4/27/23 1600
22026243400 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 15857.32 | 19008.8866 | -3151.5666 |  |  |  | 2023-03-29 | CCC#22649
22026243500 | RETIRE RECORDING GAUGE | [5 empty] | 241.8 | 96.4823 | 145.3177 |  |  |  | 2023-03-29 | CCC#22649
22026243600 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 18807.4 | 27565.8866 | -8758.4866 |  |  |  | 2023-04-14 | CCC 25146 INSTALLED NEW MIWI AND SOLAR KIT, NOT COMMIONSED YET CCC 25146 INSTALLED NEW SCADA EQUMENT NOT COMSSIONED YET BUT IS UP AND RUNNING CCC-30719PREFORMED POINT TO POINT FOR NEW WIMI
22026243900 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 13592.24 | 14352.6752 | -760.4352 |  |  |  | 2023-05-04 | CHANGE OF PLAN, SCADA IS NOT BUILT FOR THIS SIGHT AND NOT READY TO BE CHANGED OVER, CMCHOLAN 3-28-23 INSTALL NEW MIWI, P2P OK, GAGE INSP OK, REMOVED PAPER PRESSURE CHART, PRESSURE TEST OK, CMCHOLAN 5-4-23 1358
22026244000 | RETIRE ELECTRONICS | [5 empty] | 65.38 | 131.2422 | -65.8622 |  |  |  | 2023-05-04 | REMOVED ERX TO INSTALL MIWI, CCC 22274, CMCHOLAN 3-28-23
22026245000 | PAPER ONLY EXECUTE | [5 empty] | 0 | 131.2422 | -131.2422 |  |  |  | 2022-12-09
23026246100 | RETIRE PAPER GAUGE | [5 empty] | 389.08 | 131.2422 | 257.8378 |  |  |  | 2023-01-02 | RETIRE PRESSURE CHART GUAGE CCOX 1-2-23
23026246401 | INSTALL 3100' OF 2"PMMP MAIN | [5 empty] | 515222.82 | 612252.3877 | -97029.5677 |  |  |  | 2023-05-22
23026246500 | RETIRE 2400' OF 4"BS/CSLP MAIN | [5 empty] | 0 | 138.8485 | -138.8485 |  |  |  | 2023-05-22
23026247700 | INSTALL NEW GMB SETTING | [5 empty] | 96486.51 | 92317.8265 | 4168.6835 |  |  |  | 2023-08-04 | TICKET# 39340 CCC#39340 CCC#39492 08-04-2023 RHAYES CCC#39795
23026248200 | EMER - INSTALL 2'-2" PMMP | [5 empty] | 135.67 | 13154.2985 | -13018.6285 |  |  |  | 2023-01-11 | INSTALLED 2 ' OF 2'' PMP PIPE ( TESTED PIPE FOR 20MNS-GOOD PER FOL R. VANDERPOOL) J.OCHOA
23026248300 | EMER - RETIRE ~2'-2"PMP | [5 empty] | 1647.72 | 129.6266 | 1518.0934 |  |  |  | 2023-01-11 | RETIRED 2' OF 2'' P MP MAIN DUE TO DAMAGE. J.OCHOA 01-11-2023
23026248400 | EMER-INSTALL 3' OF 2"PMMP MAIN | [5 empty] | 2322.97 | 5318.1948 | -2995.2248 |  |  |  | 2023-01-18
23026248500 | EMER-RETIRE 3' OF 2"PMMP MAIN | [5 empty] | 0 | 131.2422 | -131.2422 |  |  |  | 2023-01-18
23026248900 | INSTALL 100' OF 2"PMMP MAIN | [5 empty] | 28889.25 | 30720.7606 | -1831.5106 |  |  |  | 2023-02-03
23026249000 | RETIRE 86' OF 2"CSMP MAIN | [5 empty] | 0 | 131.2422 | -131.2422 |  |  |  | 2023-02-09 | ABN 102' OF 2'' COATED STEELE MAIN PURGED AND END SEALED
23026249300 | EMER-INSTALL 5' OF 2"PMMP | [5 empty] | 5012.41 | 8253.2559 | -3240.8459 |  |  |  | 2023-01-18 | REPLACED 3' OF DAMAGED 2" PLASTIC MAIN LINE WITH 2 EF COUPLINGS. PRESSURE TESTED THE THE NEW MAIN LINE AT 90PSIG FOR 1 HOUR. PRESSURE TEST OKAY. BHB, NGF. SOAP TESTED FINAL TIE IN AT OP. TEST OK. DMALONE
23026249400 | EMER-RETIRE 5' OF 2"PMMP MAIN | [5 empty] | 219.4 | 131.2422 | 88.1578 |  |  |  | 2023-01-17 | REPLACED 3' OF DAMAGES 2" PLASTIC MAIN LINE WITH 2 EF COUPLINGS. PRESSURE TESTED THE NEW MAIN LINE AT 90PSIG FOR 1 HOUR. PRSSURE TEST OK. BHB, NGF. SOAP TESTED FINAL TIE IN AT OP. TEST OK. DMALONE
23026249800 | INSTALL EC 350 UNIT | [5 empty] | 5379.35 | 7475.3221 | -2095.9721 |  |  |  | 2023-01-25 | CHECK TO SEE IF CARD WAS READY CMCHOLAN 1-27-2023 INSTALLED NEW EC350 CMCHOLAN 1-25-23
23026249900 | RETIRE PAPER BILLING CHART | [5 empty] | 463.02 | 131.2422 | 331.7778 |  |  |  | 2023-01-25 | REMOVED PAPER BILLING CHART, CMCHOLAN EBLANTON 1-25-23
23026250000 | INSTALL EC 350 UNIT | [5 empty] | 6158.92 | 5649.3221 | 509.5979 |  |  |  | 2023-03-16 | INSTALLED NEW HONEYWELL EC350 INPLACE OF CHART
23026250100 | RETIRE PAPER BILLING CHART | [5 empty] | 525.01 | 131.2422 | 393.7678 |  |  |  | 2023-03-16 | RETIRED PAPER CHART EBLANTON 3-16-23
23026250200 | INSTALL EC-350 | [5 empty] | 8105.28 | 6049.3221 | 2055.9579 |  |  |  | 2023-03-14 | INSTALLED IN HONEYWELL EC3560 IN PLACE OF CHART EBLANTON 3-14-23
23026250300 | RETIRE PAPER BILLING CHART | [5 empty] | 185.13 | 131.2422 | 53.8878 |  |  |  | 2023-03-14 | RETIRE PAPER BILLING CHART EBLANTON 3-14-23
23026250500 | INSTALL EC 350 | [5 empty] | 6654.67 | 7589.3221 | -934.6521 |  |  |  | 2023-03-15 | INSTALLED NEW HONEYWELL EC350 IN PLACE OF CHART EBLANTON 3-15-2023
23026250600 | RETIRE PAPER BILLING CHART | [5 empty] | 144.2 | 131.2422 | 12.9578 |  |  |  | 2023-03-15 | RETIRED PAPER BILLING CHART EBLANTON 3-15-23
23026250700 | INSTALL EC 350 | [5 empty] | 5810.87 | 5649.3221 | 161.5479 |  |  |  | 2023-03-01 | RETIRED CHART INSTALLED NEW EC350
23026250800 | RETIRE PAPER BILLING CHART | [5 empty] | 528.15 | 131.2422 | 396.9078 |  |  |  | 2023-03-01 | RETIRED PAPER CHART CCOX
23026251700 | INSTALL 2060' OF 2" PMMP | [5 empty] | 65881.72 | 60788.4178 | 5093.3022 |  |  |  | 2023-03-06
23026251800 | RETIRE 900' OF 2"CSHP MAIN | [5 empty] | 12666.75 | 4095.9621 | 8570.7879 |  |  |  | 2023-08-07
23026252000 | EMER-INSTALL 3' OF 6"PMMP MAIN | [5 empty] | 13052.34 | 12970.9861 | 81.3539 |  |  |  | 2023-02-03
23026252100 | RETIRE 3' OF 6"PMP MAIN | [5 empty] | 0 | 138.8485 | -138.8485 |  |  |  | 2023-02-03
23026252200 | EMER-INSTALL 3' OF 4"PMMP MAIN | [5 empty] | 5339.51 | 7839.2961 | -2499.7861 |  |  |  | 2023-02-02
23026252300 | EMER-RETIRE 3' OF 4"PAMP MAIN | [5 empty] | 0 | 138.8485 | -138.8485 |  |  |  | 2023-02-02
23026252600 | INSTALL 3' OF 4"PMLP MAIN | [5 empty] | 16571.37 | 9484.2961 | 7087.0739 |  |  |  | 2023-01-25 | ABD 69 FT BS CUT OUT INLINE TEE AND INSTALLED 5 FT OF 4 IN PL TEST 90 LB FOR 1 HR OK SOAP TEST CPLG AND TEES AT OP FOR 5 MIN BAR HOLE BANKS NO GAS FOUND
23026252700 | RETIRE 69' OF 4"BSLP MAIN | [5 empty] | 0 | 138.8485 | -138.8485 |  |  |  | 2023-01-25 | ABDN 69 FT OF 6 IN BARE STEEL BLEW DOWN AND SEALED ENDS
23026253900 | RETIRE PRESSURE GAUGE | [5 empty] | 0 | 552.5683 | -552.5683 |  |  |  | 2023-01-27
23026254000 | RETIRE PRESSURE GAUGE | [5 empty] | 768.43 | 552.5683 | 215.8617 |  |  |  | 2023-01-31 | CC15136 CHART HAS BEEN REMOVED ISO UPDATED 1-31-23 CC15136 CHART HAS BEEN REMOVED ISO UPDATED 1-31-23
23026254400 | INSTALL 420' OF 6"PMMP MAIN | [5 empty] | -558.31 | 9832.3981 | -10390.7081 |  |  |  | 2023-08-31
23026254500 | RETIRE 356' OF 6"PMMP MAIN | [5 empty] | 0 | 114.3981 | -114.3981 |  |  |  | 2023-08-31
23026254700 | RETIRE PAPER GAUGE | [5 empty] | 247.65 | 552.5683 | -304.9183 |  |  |  | 2023-02-10 | REMOVED PAPER CHART, CCC 10587
23026254900 | INSTALL 620' OF 8"CSHP MAIN | [5 empty] | 230200.58 | 398676.678 | -168476.098 |  |  |  | 2024-07-19 | TWALKER/KY 01-20-25: LEVEL 1 VARIANCE ADDED TO WMS.DOCS: JOB UNDER RUN DUE TO THE UNIVERSITY OF KENTUCKY TAKING OWNERSHIP OF ALL THE STREETS IN PROJECT AREA - CKY DID NOT HAVE TO RESTORE/REPLACE ANY STREETS OR HARD SURFACE REPAIRS WHICH LOWERED CONTRACT COST BY $53,000, ALSO PROJECT WAS COMPLETED FASTER THAN ESTIMATE BECAUSE OF THE LACK OF STREET REPAIRS WHICH LOWERED LABOR COST BY $11,000. CKY WAS ABLE TO USED 8" STEEL PIPE LEFT OVER FROM LEESTOWN ROAD WIDENING PROJECT THAT SAVED $50,000 AND SEGA WAS $12,000 LOWER THAN ESTIMATE. FINALLY, THIS WAS A CUSTOMER PAID RELOCATION 100% REIMBURSEMENT PROJECT AND CUSTOMER WAS REFUNDED OVER PAYMENT IN 2024
23026255000 | RETIRE 620' OF 8"CSHP MAIN | [5 empty] | 330 | 116.356 | 213.644 |  |  |  | #N/A
23026256201 | INSTALL VRG CONTROLLERS | [5 empty] | 79546.52 | 47185.8659 | 32360.6541 |  |  |  | #N/A | DROPPING OF MATTERIAL 06-02-23 1324 CCC# 32360 CCC#32737 CC# 33503 CCC# 33503 CCC# 39939
23026256400 | INSTALL 25' OF 2"PMMP MAIN | [5 empty] | 9201.52 | 8978.2187 | 223.3013 |  |  |  | 2023-08-08 | INSTALLED 18' OF NEW MAIN AND ONE SERVICE LINE TO 1600 VILLA MEDICI TWALKER/KY 10-19-23: ISSUED BACK ORDER CANCEL 53922 FOR THE 250' COIL OF 2"PIPE WHICH IS NO LONGER AVAILABLE
23026257000 | ST JOE - RETIRE RTU | [5 empty] | 310.19 | 138.8485 | 171.3415 |  |  |  | 2023-04-03 | RETIRED OLD RTU EBLANTON 4-3-23
23026259000 | EMER-INST 85'-4"PMMP MND311494 | [5 empty] | 23726.73 | 25540.4028 | -1813.6728 |  |  |  | 2023-02-20 | 4" MAIN/PINK PL LEAKING UNDER STAMPED CONCRETE ENTRANCE TO COUNTRY CLUB RETIRED 85' AND INSTALLED 85' OF NEW MAIN-BORING DONE BY STANLEY PIPELINE, MAIN TEST 1 HR @90IB OK, TIE IN COMPLETE 02/20/2023 HMCKUNE
23026259100 | EMER-RETIRE 85' OF 4"PAMP MAIN | [5 empty] | 260.66 | 138.8485 | 121.8115 |  |  |  | 2023-02-20 | 4" MAIN/PINK PL LEAKING UNDER STAMPED CONCRETE ENTRANCE TO COUNTRY CLUB RETIRED 85' AND INSTALLED 85' OF NEW MAIN-BORING DONE BY STANELY PIPELINE, MAIN TEST 1HR @90 IB OK, TIE IN COMPLETE, 02/20/2023 HMCKUNE
23026260700 | INSTALL ERX W/SUPER SOLAR | [5 empty] | 3972.47 | 5629.9621 | -1657.4921 |  |  |  | 2023-03-06 | INSTALLED SUPER SOLAR AND MEDIUM PRESSURE RUN TO ER350, WILL BE FULL TIME MONITOR WHEN BUILT IN SCADA AND WILL DO P2P THEM CCC 19108, CMCHOLAN 3-6-23 FINISHED UP PAPERWORK AND SUMMITED ISO, CCC 19108 CMCHOLAN 3-6-23 0859 CCC-27261 DID P2P WITH GAS CONTROL ON MP, GAGE INSP OK, CCC 27123 CMCHOLAN EBLANTON 4-26-23 1600
23026260800 | RETIRE PAPER CHART | [5 empty] | 78.59 | 138.8485 | -60.2585 |  |  |  | 2023-03-06 | RETIRED PAPER CHART AND IS NOW CONNECTED ER350, CMCHOLAN CCC 19108
23026262700 | EMER-INSTALL 5' OF 2"PMMP MAIN | [5 empty] | 3582.24 | 7460.3676 | -3878.1276 |  |  |  | 2023-03-07 | WORKED WITH JO. 23026262700 INSTALLED 5FT OF 020 MAIN DUE TO LEAKING S/L TEE. TESTED 5FT OF 020, 010 TEE,010 COUPLING AND 020 PURGE END CAP FOR 1HR AT 90LBS.TEST OK. SOAP TEST 020 EFC AT OP. FOR 5MINS TEST OK. BHB NGF
23026262800 | EMER-RETIRE 5' OF 2"PMP MAIN | [5 empty] | 726.04 | 124.7348 | 601.3052 |  |  |  | 2023-03-07 | FROM MAIN TO MTR FOR 5MINS AT 90LBS.TEST OK. SOAP TEST FINAL TIE IN AT OP.TEST OK. BHB NGF WORKED WITH JO. 23026262700 INSTALLED 5FT OF 020 MAIN DUE TO LEAKING S/L TEE. TESTED 5FT OF 020, 010 TEE,010 COUPLING AND 020 PURGE END CAP FOR 1HR AT 90LBS.TEST OK. SOAP TEST 020 EFC AT OP. FOR 5MINS TEST OK. BHB NGF -- 010 S/L ELECTROFUSION TEE LEAKING AT SADDLE CONNECTION TO MAIN.REPLACED 5FT OF MAIN WITH NEW S/L TEE AND 020 PURGE END CAP.TESTED FOR 1HR AT 90LBS. TEST OK. SOAP TEST EFC COULPING AT OP. FOR 5MINS.TEST OK.TEST S/L FOR 3905
23026263000 | INSTALL 5875' OF 2"/4"PMMP ENV | [5 empty] | 763454.52 | 728668.2681 | 34786.2519 |  |  |  | 2023-09-12
23026263100 | RETIRE 6090' OF 4"BSMP MAIN | [5 empty] | 0 | 124.7348 | -124.7348 |  |  |  | 2023-09-12
23026263400 | INSTALL 40'-4" PMMP | [5 empty] | 24778.88 | 25145.0229 | -366.1429 |  |  |  | 2023-04-11
23026263500 | RETIRE 20'-4" PMMP | [5 empty] | 98.08 | 124.7348 | -26.6548 |  |  |  | 2023-04-11
23026264300 | EMER-INSTALL 5' OF 4"PMMP MAIN | [5 empty] | 267.86 | 7456.0229 | -7188.1629 |  |  |  | 2023-03-10 | INSTALLED 3' OF 4" PL MAIN W/ EFC AND BF DE CAP- TEST 90# FOR 20MINS PER FOL DBANKS- SOAP TEST FINALTIEIN @ OP TEST OK- BHB NGF CONTENT VERIFIED DMARSTO 3/10/23
23026264400 | EMER-RETIRE 520'- 4"PAIP MAIN | [5 empty] | 325.83 | 124.7348 | 201.0952 |  |  |  | 2023-03-10 | ABN 520' SECTION OF 4" PL MAIN- PURGE ABN SECTION OF MAIN W/ AIR UNTIL 0% SUSTAINED- DMARSTO 3/10/23
23026264700 | INSTALL 100' OF 3"PMLP MAIN | [5 empty] | 21922.36 | 29526.7351 | -7604.3751 |  |  |  | 2023-04-19 | 100' OF BS MAIN RETIRED AND REPLACED W/3" PE PL MAIN DUE TO CORROSION
23026264800 | RETIRE 100' OF 3"BSLP MAIN | [5 empty] | 6487.75 | 124.7348 | 6363.0152 |  |  |  | 2023-04-19 | 100' OF BS MAIN RETIRED AND REPLACED W/3" PE PL MAIN DUE TO CORROSION
23026265100 | INSTALL 10'-3"PMLP | [5 empty] | 203249.18 | 37610.5067 | 165638.6733 |  |  |  | 2023-06-02 | INSTALLED 10 FT OF PL TEST FROM POINT A TO B 90 LB FOR 20 MIN TEST OK SOAP TEST 2 CPLG AND ALL BAG HOLES AT OP BHBNGF MAIN READ -0.601 INSTALLED 2 ANODES
23026265200 | RETIRE 10'-3" BSLP | [5 empty] | 190.67 | 120.2184 | 70.4516 |  |  |  | 2023-06-02 | RETIRED 10 FT OF 3 IN BS PIPE PURGED OUT AND SEALED THE INLINE TEE SIDE
23026265400 | EMER - INSTALL 12' - 2" PMMP | [5 empty] | 9462.49 | 5370.5784 | 4091.9116 |  |  |  | 2023-04-06 | TEST 2 IN MAIN FROM POINT A TO B TEST 90 LB FOR 20 MIN SOAP TEST TIEINS AT OP BAR HOLE BANKS NO GAS FOUND
23026265500 | EMER - RETIRE 12' - 2" PMMP | [5 empty] | 165.55 | 124.7348 | 40.8152 |  |  |  | 2023-04-06
23026266300 | EMER-INSTALL 3' OF 2"PMMP MAIN | [5 empty] | 4867.28 | 7671.8121 | -2804.5321 |  |  |  | 2023-02-22
23026266400 | EMER-RETIRE 3' OF 2"PMP MAIN | [5 empty] | 0 | 124.7348 | -124.7348 |  |  |  | 2023-02-22
23026267200 | INSTALL 60'-4" PMLP | [5 empty] | 34888.84 | 41669.6267 | -6780.7867 |  |  |  | 2024-03-28
23026267300 | RETIRE ~60'-4" BSLP | [5 empty] | 136.28 | 120.2184 | 16.0616 |  |  |  | #N/A
23026267700 | EMER-RETIRE 40' OF 6"BSLP MAIN | [5 empty] | 8203.54 | 9430.1038 | -1226.5638 |  |  |  | 2023-03-16
23026267800 | INSTALL 580' OF 2"PMMP MAIN | [5 empty] | 35753.76 | 40516.7801 | -4763.0201 |  |  |  | 2023-06-08
23026268200 | INSERT 160' OF 3"PMLP MAIN | [5 empty] | 15778.59 | 20952.5602 | -5173.9702 |  |  |  | 2023-04-14
23026268300 | RETIRE 160' OF 4"BSLP MAIN | [5 empty] | 8055.67 | 117.7346 | 7937.9354 |  |  |  | 2023-04-13
23026268400 | INSTALL 2000' OF 2"PMMP MAIN | [5 empty] | 56232.52 | 83632.6185 | -27400.0985 |  |  |  | 2023-04-21
23026268800 | RETIRE ER350 UNIT | [5 empty] | 116.17 | 117.7346 | -1.5646 |  |  |  | 2023-04-12
23026270100 | RETIRE REG STATION# 1020 | [5 empty] | 1847.24 | 10605.8819 | -8758.6419 |  |  |  | #N/A | RETIRED STATION AND REMOVED REGS, MONITORED PRESSURE FOR 30 MIN AFTER RETIREMENT, SOAPED BLING FLANGES AND PLUGS, CCC 77786, CMCHOLAN 6-20-24 1500
23026270600 | INSTALL 550' OF 2" PMMP | [5 empty] | 43345.7 | 42706.9586 | 638.7414 |  |  |  | 2024-09-26
23026271200 | INSTALL LEGACY ERX | [5 empty] | 2465.58 | 2907.8819 | -442.3019 |  |  |  | 2023-04-03 | INSTALLED LEGACY ERX IN PLACE OF OLD RTU AND TRANSMITTER EBLANTON 4-3-23
23026271600 | PAPER ONLY TO SET UP WMS FAC | [5 empty] | 14353.75 | 139.7346 | 14214.0154 |  |  |  | #N/A | THIS JOB IS TO CREATE FUNCTIONS AND FACILITIES FOR THE TEMPORARY SKID REGUL ATOR SETTING RWILLIAMS PUT TEMP STATION BACK TOGETHER, CMCHOLAN 6-26-2023
23026272200 | INSTALL 200' OF 2"PMMP MAIN | [5 empty] | 27418.37 | 23237.6457 | 4180.7243 |  |  |  | 2023-06-16
23026272300 | EMER-INSTALL 3" NC POLY VALVE | [5 empty] | 6810.69 | 7421.5276 | -610.8376 |  |  |  | 2023-04-28 | REPLACED BROKEN CRITICAL VLV WITH NEW 030 POLY VLV. TEST PIPE,VLV,&CPLGS 90#1HOUR, TG. ST LTI OK. BHBNGF. R.CRAWFORD 4-28-23
23026272400 | EMER-RETIRE 3"PV C16-87 | [5 empty] | 85.95 | 117.7346 | -31.7846 |  |  |  | 2023-04-28 | REFER TO JOB#-23026272300 FOR COMMENTS. R.CRAWFORD 4-28-23
23026272600 | INSTALL 875' OF 2"PMMP MAIN | [5 empty] | 29299.51 | 32780.4095 | -3480.8995 |  |  |  | 2023-05-09
23026272700 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 2367.44 | 5551.3568 | -3183.9168 |  |  |  | 2023-04-25
23026272800 | EMER - RETIRE 5'-2" PMMP | [5 empty] | 0 | 112.7299 | -112.7299 |  |  |  | 2023-04-25
23026272901 | INSTALL 2500' OF 2"PMMP MAIN | [5 empty] | 251654.55 | 209814.7415 | 41839.8085 |  |  |  | 2024-03-15
23026273000 | INSTALL 20'-4"PMMP W/NEW VALVE | [5 empty] | 20711.38 | 13458.2914 | 7253.0886 |  |  |  | 2023-06-26 | LOWERED 4" MP PE MAIN,REPLACED CRITICAL VLV,TEST MAIN@90IB 1HR,TIED IN W/2 EF CPLG'S, SOAP TEST TIE IN,MOVE CV TO SOFT SURFACE 06/26/2023 HMCKUNE
23026273100 | RETIRE 20'-4"PMMP W/C19-314 | [5 empty] | 0 | 117.7346 | -117.7346 |  |  |  | 2023-06-26
23026273300 | INSTALL 290' OF 4" PMMP | [5 empty] | 80935.68 | 48321.0935 | 32614.5865 |  |  |  | 2023-06-30
23026273400 | RETIRE 283' OF 3" BSMP | [5 empty] | 0 | 67.1159 | -67.1159 |  |  |  | 2023-06-30
23026273700 | INSTALL 6' OF 2"PMMP MAIN | [5 empty] | 5850.76 | 15141.0552 | -9290.2952 |  |  |  | 2024-07-12 | LEAKING CV ON STEM.REMOVED CV AND INSTALLED 3' OF 020PMP.TESTED PURGE TEE AND 3FT OF MAIN FOR 1HR AT 90LBS.TEST OK.SOAP TEST EFC'S AT OP FOR 5MINS AT OP.TEST OK. BHB NGF. REMOVED CV C9-113.
23026273800 | RETIRE 2" POLY VALVE C9-113 | [5 empty] | 3847.88 | 117.7346 | 3730.1454 |  |  |  | #N/A | LEAKING CV ON STEM.REMOVED CV AND INSTALLED 3' OF 020PMP.TESTED PURGE TEE AND 3FT OF MAIN FOR 1HR AT 90LBS.TEST OK.SOAP TEST EFC'S AT OP FOR 5MINS AT OP.TEST OK. BHB NGF. REMOVED CV C9-113.
23026273900 | INSTALL 441 REG (WEST RUN) | [5 empty] | 4130.38 | 3436.7638 | 693.6162 |  |  |  | 2023-06-08 | (NOT ON-SITE GETTING PARTS TO COMPLETE JOB) G.HALE NOT ONSITE COLLECTING REG AND PARTS APARKS 05-18-23 1551 SWAPPED 461 REGS FOR 441 REGS 57S 1 3/4 ORFICE BROWN SPRING IN BOTH CONTROL AND MONITOR MAJOR INSP. COMPLETED ON BOTH REGS INLET@90# MON@55# CON@47# CCC# 33177 NOT ONSITE PAPER WORK ONLY APARKS 06-19-23 1000
23026274000 | RETIRE 461 REGS (WEST RUN) | [5 empty] | 0 | 117.7346 | -117.7346 |  |  |  | 2023-06-08
23026274301 | INSTALL 3400' OF 2"PMMP MAIN | [5 empty] | 82979.94 | 79169.604 | 3810.336 |  |  |  | 2023-09-14
23026276300 | EMER-INSTALL 2"POLY VALVE | [5 empty] | 6885.74 | 10283.4841 | -3397.7441 |  |  |  | 2023-06-27 | INSTALLED NEW CRIT.VLV. TEST VLV FOR 1 HOUR, TG. TEST 2 BYPASS, TG. TEST ALL TEES, TG. ST LTI'S, TG. ALL TIME FOR JOB# 23186718700 TO BE CHARGED BACK TO THIS JOB, R.CRAWFORD 6-23-23 REFER TO JOB# 23026276400 FOR COMMENTS. R.CRAWFORD 6-27-23
23026276400 | EMER-RETIRE 2"VALVE C14-27 | [5 empty] | 0 | 139.1159 | -139.1159 |  |  |  | 2023-06-27 | REFERENCE COMMENTS FOR JOB # 23026276300. R.CRAWFORD 6-23-23 REPLACED BROKEN CV. TEST NEW CV AND PIPE WITH IT 90#1HR, TG. TEST ALL TEES 9#5MINS, TG. TEST BYPASS' 90#1HOUR, TG. ST ALL FINAL TI'S, TG. R.CRAWFORD 6-27-23
23026276900 | RETIRE 250' OF 3"BSLP MAIN | [5 empty] | 1716.17 | 4585.4374 | -2869.2674 |  |  |  | 2023-06-27 | ABDN 252 FT OF 3 IN BS MAIN SOAP TEST 4 PAC CLAMPS AT OP FOR 5 MIN SOAP TEST END CAP AT OP FOR 5 MIN BHBNGF INSTALLED 1ANODE PURGED OUT OLD MAIN AND SEALED MAIN LEFT 36 FT LINE MARKER AT END
23026277000 | EMER-INSTALL 15' OF 8"PMLP MN | [5 empty] | 19444.34 | 23129.0935 | -3684.7535 |  |  |  | 2023-08-10 | INSTALLED 8 IN PL MAIN TEST FROM POINT A TO POINT B SOAP TEST ALL PAC CLAMPS AND CPLG AT OP FOR 5 MIN BHBNGF INSTALLED 2 ANODE
23026277100 | EMER-RETIRE 15' OF 8"BSLP MN | [5 empty] | 307.27 | 139.1159 | 168.1541 |  |  |  | 2023-08-10 | ABDN 11 FT 8 IN BS MAIN INSTALLED 11 8 IN PL MAIN TEST 90 LB FOR 1 HHR SOAP TEST FINAL TIE IN AT OP FOR 5MIN BHBNGF
23026277200 | EMER-RETIRE 55' OF 6"PMLP MN | [5 empty] | 5550.64 | 4206.4374 | 1344.2026 |  |  |  | 2023-06-14 | RETIRED 52' OF 6'-P-LP WITH E/F COUPLING AND DEAD END CAP. PURGED 52' OF ' MAIN OUT OF SERVICE. SOAP TESTED FINAL CONNECTION FOR 5 MINTES AT OP. TEST OKAY.
23026277300 | INSTALL 265' OF 6"PMMP MAIN | [5 empty] | 29277.24 | 71789.4841 | -42512.2441 |  |  |  | 2023-08-31 | JOB COMPLETED. 08312023
23026277400 | RETIRE 285' OF 6"PMMP MAIN | [5 empty] | 439.67 | 139.1159 | 300.5541 |  |  |  | 2023-08-31 | JOB COMPLETED
23026277900 | EMER - INSTALL 69'-6" PMLP | [5 empty] | 31362.92 | 35367.5186 | -4004.5986 |  |  |  | 2023-06-08 | INSTALLED 40' 060 PMP TESTED FOR 1HR AT 90LBS.TEST OK. SOAP TEST TIE INS AT OP.TEST OK. BHB NGF WORKED WITH 558
23026278000 | EMER - RETIRE 69'-6" BSLP | [5 empty] | 124.77 | 139.1159 | -14.3459 |  |  |  | 2023-06-08 | ABDN 40' OF 6'' STEEL WORKED WITH 557.
23026278200 | EMER-INSTALL 185' OF 4"PMLP | [5 empty] | 41688.69 | 28939.243 | 12749.447 |  |  |  | 2023-06-16
23026278300 | EMER-RETIRE 181' OF 4"BSLP MN | [5 empty] | 0 | 139.1159 | -139.1159 |  |  |  | 2023-06-16
23026278401 | INSTALL 2300' OF 2"/4"PMMP MN | [5 empty] | 116796.05 | 101330.2336 | 15465.8164 |  |  |  | 2023-11-16
23026279100 | INSTALL 300' OF 2"PMIP MAIN | [5 empty] | 7749.44 | 17364.828 | -9615.388 |  |  |  | 2023-07-28
23026280100 | RETIRE 10' OF 10"CSMP MAIN | [5 empty] | 273.6 | 139.1159 | 134.4841 |  |  |  | 2023-09-07
23026280800 | EMER-INSTALL 62' OF 4"PMLP | [5 empty] | 63661.35 | 28754.8748 | 34906.4752 |  |  |  | 2023-07-12 | INSTALLE 40 FT 4 IN MAIN TEST FROM POINT A TO POINT B 90 LB FOR 1 HR TEST ALL TEES AT 90 LB FOR 5 MIN SOAP TEST EFC AND BOLTD CPLG AT O OP FOR 5 MIN SOAP TEST 1 IN END CAP AT OP FOR 5 MIN INSTALL 1 ANODE
23026280900 | EMER-RETIRE 62' OF 4"BSLP | [5 empty] | 2161.53 | 139.1159 | 2022.4141 |  |  |  | 2023-07-12 | RETIRED 36 FT OF BS AND 9 FT OF PL 4 IN LOW PRESSURE MAIN
23026282700 | EMER-ABANDON 333' OF 2"PAMP | [5 empty] | 2936.25 | 3839.4374 | -903.1874 |  |  |  | 2023-07-06 | ABND CUL-DE-SAC AFTER HIT LINE BY OTHER CONTRACTOR PER ENGINEER/FOL AFTER VERIFICATION NO CUSTOMERS ON GAS FOR SECTION OF MAIN TO BE ABND
23026283200 | INSTALL 480' OF 2"PMMP MAIN | [5 empty] | 47476.79 | 59017.0935 | -11540.3035 |  |  |  | 2023-08-17 | TWALKER/KY 10-20-23: REQUESTED CUSTOMER REFUND FOR THE CUSTOMER PAID RELOCA TION PROJECT.
23026283300 | RETIRE 400' OF 2"BSMP MAIN | [5 empty] | 0 | 139.1159 | -139.1159 |  |  |  | 2023-08-17
23026283400 | EMER - INSTALL 5'-3" PMMP | [5 empty] | 4304.94 | 10280.7214 | -5975.7814 |  |  |  | 2023-07-24 | INST 5'- 3" NEW PL MAIN BY ENGINEERED PLAN. MCRAIG 7/10/23
23026283500 | EMER - RETIRE 5'-3" PMP | [5 empty] | 36.39 | 139.1159 | -102.7259 |  |  |  | 2023-07-24 | RETIRE 5' OF 3" PL MAIN DUE TO LEAK PER ENGINEERED PLAN. MCRAIG 7/10/23
23026284300 | EMER-INSTALL 490' OF 2"PMMP | [5 empty] | 133294.53 | 184478.0101 | -51183.4801 |  |  |  | 2023-08-10 | BARE STEEL LP MAIN LEAKING, CREW WAS UNABLE TO EXPOSE LEAK, ABANDONED BS MAIN AND BORED IN 490'OF 2"P- PRE AND POST CAMERA COMPLETED-PT NEW MAIN 90LBS FOR 1HR PER ENGINEERING-SOAP TESTED TIE IN AT OP
23026284400 | EMER-RETIRE 520' OF 4"BSMP MN | [5 empty] | 223.9 | 139.1159 | 84.7841 |  |  |  | 2023-08-10 | REPLACED 493' OF 4'' S MP WITH 2'' PMP DUE TO GRADE 1 LEAK.DPI D304338.
23026284500 | INSTALL 80'4" PMLP | [5 empty] | 23619.02 | 47424.0373 | -23805.0173 |  |  |  | 2023-07-27 | TEST FROM POINT A TO B TO C 90 LB FOR 1 HR TEST OK TEST FINAL TIE IN AT OP OK BHBNGF INSTALLED 3 ANODES MAIN READ -0.591 TEST PAAC CLAMPS AT OP OK
23026284600 | RETIRE 80'-4" BSLP | [5 empty] | 4684.11 | 139.1159 | 4544.9941 |  |  |  | 2023-07-27 | RETIRED 60 FT OF BS 4IN MAIN PURGED OUT AND REMOVED PIPE
23026285300 | EMER - RETIRE 159'-3"BSLP | [5 empty] | 5197.96 | 10816.0505 | -5618.0905 |  |  |  | 2023-07-27 | ABDN 159' OF 3'' BS LP.LEAK UNDER DRIVEWAY APPRON.MAIN NOT FEEDING ANY S/L.LEFT 15' OF 3'' ACTIVE. SOAP TEST END CAP AT OP FOR 5MINS TEST OK. BHB NGF. INSTALLED ANODE DENSO WRAPPED.
23026285400 | RETIRE 300' OF 2"PIP MAIN | [5 empty] | 17543.67 | 16251.9287 | 1291.7413 |  |  |  | #N/A | CAPPED OFF HP INLET TO ABANDONED STATION AND REMOVED STATION AND FENCE. CONTRACTORS REMOVED ALL VISIBLE LINE MARKERS AND RISERS IN TRAILER PARK. JOSH PASLEY 2/5/24
23026285500 | RETIRE REG STATION #1129 | [5 empty] | 19139.56 | 22153.7376 | -3014.1776 |  |  |  | 2023-11-30 | CCC#54039
23026286300 | RETIRE 306' OF 3"BSLP MAIN | [5 empty] | 10623.01 | 7586.4374 | 3036.5726 |  |  |  | 2023-09-05 | ABN. 40' OF PLASTIC AND 306' OF STEEL MAIN. PURGE ALL GAS OUT. PLUGGED ENDS NGF AFTER PURGED. USED EF EC, ST AT OP, TG. R.CRAWFORD 9-5-23
23026286800 | INSTALL 100' OF 2"PMIP MAIN | [5 empty] | 17844.41 | 8938.3422 | 8906.0678 |  |  |  | 2023-09-05 | SPOTTED UTILITIES WITH VAC TRUCK. BORED IN 100' OF 020 P MAIN, PRESSURE TEST 1 HOUR AT 90#, TG. ST LTI, TG. R.CRAWFORD 9-5-23
23026287600 | INSTALL 30'-4" PMMP | [5 empty] | 19740.37 | 14529.6064 | 5210.7636 |  |  |  | 2024-06-20
23026287700 | RETIRE ~30'-4" PMP | [5 empty] | 6450.91 | 124.9261 | 6325.9839 |  |  |  | #N/A
23026288000 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 267.7 | 3242.0133 | -2974.3133 |  |  |  | 2023-08-10 | RELACED 5' OF 020 PMP DUE TO SOCKET ON TEE LEAKING. TESTED 5' OF 020 FOR 1HR AT 90LBS.TEST OK. SOAP TEST 2 2'' EFC AT OP. TEST OK. BHB NGF.
23026288100 | EMER - RETIRE 5'-2" PMMP | [5 empty] | 1.39 | 119.4953 | -118.1053 |  |  |  | 2023-08-10 | RELACED 5' OF 020 PMP DUE TO SOCKET ON TEE LEAKING. TESTED 5' OF 020 FOR 1HR AT 90LBS.TEST OK. SOAP TEST 2 2'' EFC AT OP. TEST OK. BHB NGF.
23026288200 | INSTALL VERIZON MODEM | [5 empty] | 1861.82 | 4954.3422 | -3092.5222 |  |  |  | 2023-08-17
23026288300 | RETIRE SATELLITE COMM EQUIP | [5 empty] | 0 | 119.4953 | -119.4953 |  |  |  | 2023-08-17
23026288401 | INSTALL 5500' OF 4"PMMP MAIN | [5 empty] | 294615.62 | 319863.8272 | -25248.2072 |  |  |  | 2024-08-01
23026289100 | INSTALL FENCE | [5 empty] | 23214.65 | 26355.734 | -3141.084 |  |  |  | 2023-10-30 | NOT ON SITE, OFFICE PAPERWORK
23026290800 | INSERT/INSTALL 160'-3"PMLP MN | [5 empty] | 45855.9 | 46254.1681 | -398.2681 |  |  |  | 2023-10-20 | TEST FROM POINT A TTO B 90 LB FOR 1 HR TEST 2 IN HV TEE AND 2 IN MAIN FROM POINT A TO B 90 LB FOR 1 HR
23026290900 | RETIRE 60' OF 3"BSLP MAIN | [5 empty] | 7967.87 | 119.4953 | 7848.3747 |  |  |  | 2023-10-20 | ABDN 82 FT OF 4" BS MAIN AND 143 FT OF 2 " BS MAIN PURGED OUT AND SEALED UP AND INSTALLED ALL NEW 3 "PL MAIN
23026292000 | INSTALL 2450' OF 2"PMMP MAIN | [5 empty] | 93897.7 | 75092.497 | 18805.203 |  |  |  | 2024-02-20
23026292501 | INSTALL 800' OF 2-4" PMMP | [5 empty] | 232050.11 | 229159.9279 | 2890.1821 |  |  |  | 2023-10-06
23026293700 | INSTALL 74'-2" PMMP | [5 empty] | 52073.55 | 102229.172 | -50155.622 |  |  |  | 2024-02-21
23026293800 | RETIRE 88'-2"&4" PMMP | [5 empty] | 12669.1 | 119.4953 | 12549.6047 |  |  |  | #N/A
23026294500 | RETIRE 338' OF 4"BSLP MAIN | [5 empty] | 13645.62 | 4190.6844 | 9454.9356 |  |  |  | 2023-12-14
23026294800 | INSTALL 225' OF 2"PMMP MAIN | [5 empty] | 29004.09 | 19109.6064 | 9894.4836 |  |  |  | 2023-12-05
23026296000 | INSTALL 220' OF 2" PMMP | [5 empty] | 50792.43 | 32123.3441 | 18669.0859 |  |  |  | 2024-01-11
23026296200 | INSTALL 1429'-6" PMMP | [5 empty] | 975067.42 | 234311.6314 | 740755.7886 |  |  |  | 2024-06-28 | LEVEL 2 VARIANCE EXPLANATION APPROVED AND LOCATED IN JO WORKSPACE IN WMSDOC S. D.LEMONS 9/23/2024
23026296300 | RETIRE 1479'-6" CS&PMMP | [5 empty] | 577.39 | 122.9261 | 454.4639 |  |  |  | #N/A
23026296800 | EMER - INSTALL 40'-4" PMMP | [5 empty] | 48671.57 | 32230.3112 | 16441.2588 |  |  |  | 2023-10-31
23026296900 | EMER - RETIRE 40'-4" CSMP | [5 empty] | 0 | 122.9261 | -122.9261 |  |  |  | 2023-10-31
23026297200 | EMER - INSTALL 13'-2" PMMP | [5 empty] | 5013.23 | 9353.5801 | -4340.3501 |  |  |  | 2023-10-12 | VALVE RETIRED.SOAP TEST END CAPS AT OP FOR 5MINS. TEST OK.BHB NGF LEAKING 020 P CRITICAL VALVE.LEAKING FROM STEM.RETIRED VALVE WITH 020 BYPASS.TESTED BYPASS AS MAIN FOR 1HR AT 90LBS.TEST OK INSTALLED TWO END CAPS AT VALVE TO ABDN VALVE.020 BYPASS MADE TO ACVTIVE MAIN AFTER
23026297300 | EMER - RETIRE 2'-2" PMP | [5 empty] | 5943.6 | 122.9261 | 5820.6739 |  |  |  | 2023-10-12 | VALVE RETIRED.SOAP TEST END CAPS AT OP FOR 5MINS. TEST OK.BHB NGF LEAKING 020 P CRITICAL VALVE.LEAKING FROM STEM.RETIRED VALVE WITH 020 BYPASS.TESTED BYPASS AS MAIN FOR 1HR AT 90LBS.TEST OK INSTALLED TWO END CAPS AT VALVE TO ABDN VALVE.020 BYPASS MADE TO ACVTIVE MAIN AFTER
23026299700 | INSTALL 325' OF 2"PMMP MAIN | [5 empty] | 52412.36 | 30286.964 | 22125.396 |  |  |  | 2024-03-14 | TWALKER/KY 03-22-24: JOB OVER RUN DUE TO UNKNOWN CROSS BORE DISCOVERED AT TIE IN POINT FOR THIS PROJECT, CREWS HAD TO CORRECT THAT ISSUE WHICH ADDED ADDITIONAL TIME/MONEY FOR CONTRACTOR AND CONS COORDINATOR
23026300800 | EMER-INSTALL 5' OF 3"PMLP | [5 empty] | 5389.28 | 4600.4752 | 788.8048 |  |  |  | 2023-10-10
23026300900 | EMER-RETIRE 5' OF 3"PLP MAIN | [5 empty] | 0 | 122.9261 | -122.9261 |  |  |  | 2023-10-10
23026301000 | EMER-INSTALL 2' OF 4"PMMP MAIN | [5 empty] | 3269.69 | 4675.4752 | -1405.7852 |  |  |  | 2023-05-31
23026301100 | EMER-RETIRE 2' OF 4"PAMP MAIN | [5 empty] | 0 | 122.9261 | -122.9261 |  |  |  | 2023-05-31
23026302701 | INSTALL 2700' OF 2"/4"PMMP | [5 empty] | 288308.66 | 294198.9734 | -5890.3134 |  |  |  | 2024-06-12
23026303700 | EMER - INSTALL 5' OF 2" PMMP | [5 empty] | 617.17 | 147.9261 | 469.2439 |  |  |  | 2023-11-03
23026303800 | EMER - RETIRE 3' OF 2" PAMP | [5 empty] | 114.6 | 124.9261 | -10.3261 |  |  |  | 2023-11-03
23026303900 | EMER-INSTALL 3'-2" PMMP MAIN | [5 empty] | 2236.53 | 5599.8489 | -3363.3189 |  |  |  | #N/A
23026304000 | EMER-RETIRE 3'-2"PAMP MAIN | [5 empty] | 0 | 124.9261 | -124.9261 |  |  |  | #N/A
23026304100 | RETIRE 667' OF 2"PMMP MAIN | [5 empty] | 4930.16 | 5490.3441 | -560.1841 |  |  |  | 2023-11-29 | ABND MAIN ON STATE ST
23026305300 | EMER-INSTALL 11'-2" PMMP | [5 empty] | 5063.47 | 17054.8912 | -11991.4212 |  |  |  | 2023-11-13 | INSTALLED 11' NEW 2"PL MAIN DURING DAMAGE/HIT LINE FROM BANK CAVE IN INSIDE UTILITY CONTRACTORS EXCAVATION-BHB,NGF-NGF UPON DEP
23026305400 | EMER-RETIRE 11'-2" PMMP | [5 empty] | 383.65 | 124.9261 | 258.7239 |  |  |  | 2023-11-13 | ABND 11'SECTION OF MAIN FOR DAMAGE
23026305800 | RETIRE CHAIN LINK FENCE | [5 empty] | 0 | 502.1911 | -502.1911 |  |  |  | #N/A
23026307700 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 3856.33 | 5646.8353 | -1790.5053 |  |  |  | 2023-12-08
23026307800 | EMER - RETIRE 5'-2" PMP | [5 empty] | 0 | 123.4493 | -123.4493 |  |  |  | 2023-12-08
23026307900 | EMER-INSTALL 10'-4"PMMP/VALVE | [5 empty] | 8083.2 | 6246.9893 | 1836.2107 |  |  |  | 2023-12-18 | LEAKING MAIN VALVE.LEAK FROM STEM.REPLACED WITH NEW VALVE. TESTED 10' OF 040 WITH VALVE FOR 1HR AT 90LBS.TEST OK. SOAP TEST 2 EFC AT OP FOR 5MINS.TEST OK. BHB NGF
23026308000 | EMER-RETIRE 10'-4"PMP/C8-150 | [5 empty] | 147.12 | 123.4493 | 23.6707 |  |  |  | 2023-12-18 | LEAKING MAIN VALVE.LEAK FROM STEM.REPLACED WITH NEW VALVE. TESTED 10' OF 040 WITH VALVE FOR 1HR AT 90LBS.TEST OK. SOAP TEST 2 EFC AT OP FOR 5MINS.TEST OK. BHB NGF
23026308900 | EMER INSTALL 4' OF 3" PMMP | [5 empty] | 2998.44 | 3360.6855 | -362.2455 |  |  |  | 2023-12-22 | INST 4'- 3" PL MAIN PER ENGINEERED PLAN AND GAS STANDARDS. TEST NEW MAIN @ 90LB 5MIN OK. SOAP TEST TIE-IN @ OP OK. WORKED ON 12/19/23. MCRAIG 12/22/23
23026309000 | EMER RETIRE 4' OF 3" PMP | [5 empty] | 218.46 | 123.4493 | 95.0107 |  |  |  | 2023-12-22 | RETIRE 4' OF 3" PL MAIN DUE TO LEAK IN ACCORDNANCE W/ ENGINEERING AND GAS STANDARDS. TEST NEW 4' PL @ 90LB 5MIN OK. SOAP TEST TIE-IN. WORKED 12/19/23. MCRAIG 12/22/23
23026309100 | EMER-INSTALL 4'OF 2"PMMP MAIN | [5 empty] | 2952.18 | 4579.9666 | -1627.7866 |  |  |  | 2024-01-03 | INST 4'- 2" PL MAIN. TEST MAIN @ 90LB 5MIN OK. SOAP TEST TIE-IN @ OP OK. BHB NGF. CGI MAIN AND SVC OK. WRK 12/20/23. MCRAIG 1/3/24
23026309200 | EMER-RETIRE 4' OF 3"PMP MAIN | [5 empty] | 259.03 | 123.4493 | 135.5807 |  |  |  | #N/A | RETIRE 4'- 2" PL MAIN DUE TO LEAKING WELD. WRK 12/20/23. MCRAIG 1/3/24
23026309300 | EMER - INSTALL 5'-4" PMMP | [5 empty] | 3958.19 | 8753.3832 | -4795.1932 |  |  |  | 2024-03-06 | TEST 6 FT MAIN90LB FOR 20 MIN OK TEST 3 EF TEES 90 LB FOR 5 MIN SOAP TEST 2 EFC AT OP FOR 5 MINSOAP TEST 2 END 1 IN END CAPS AT OP OK BHBNGF
23026309400 | EMER - RETIRE 5'-4" PMP | [5 empty] | 158.95 | 123.4493 | 35.5007 |  |  |  | #N/A | CPLNG ON TEE LEAKING REPLACED 6 FT OF MAIN TEST NEW MAIN 90 LB FOR 20 MIN SOAP TEST FINAL TIE IN AT OP BHBNGF
24026310400 | INSTALL VALVE & 5' OF 2" PMMP | [5 empty] | 10413.42 | 11731.9279 | -1318.5079 |  |  |  | 2024-02-07
24026310500 | RETIRE VALVE & 5' OF 2" PMP | [5 empty] | 3446.12 | 160.3697 | 3285.7503 |  |  |  | #N/A
24026311700 | INSTALL 360' OF 2"PMMP MAIN | [5 empty] | 38311.55 | 32438.7712 | 5872.7788 |  |  |  | 2024-03-04
24026311800 | EMER-INSTALL 5' OF 2"PMMP MAIN | [5 empty] | 2941.72 | 5455.4783 | -2513.7583 |  |  |  | 2024-02-20 | REPLACED 5 FT OF MAIN TEST ALL MATERIAL TO ALL GAS STANDERDS TEST MAIN 90 FOR 20 MIN TEST ALL TEES 90 FOR 5 MIN SOAP TEST EFC AND SL END CAPS AT OP FOR 5 MIN BHBNGF
24026311900 | EMER-RETIRE 5' OF 2"PAMP MAIN | [5 empty] | 22.89 | 123.4493 | -100.5593 |  |  |  | #N/A | FOUND LEAK ON MAIN INSTALLED 5 FT OF MAIN TEST 90 LB FOR 20 MIN ABDN 5 FT OF MAIN
24026312700 | RETIRE 310' OF 2"PMMP MAIN | [5 empty] | 1540.57 | 4362.2109 | -2821.6409 |  |  |  | #N/A | ABN MAIN DUE TO DEMO OF HOUSES - ABN 2" PLASTIC MAIN WITH 2" EF DEAD END CAP - SOAP TEST @ OP FOR 5 MIN TEST GOOD
24026314000 | EMER-INSTALL 5' OF 4"PMMP MAIN | [5 empty] | 519.5 | 1932.1928 | -1412.6928 |  |  |  | 2024-02-20
24026314100 | EMER-RETIRE 5' OF 4"PAMP MAIN | [5 empty] | 29.31 | 160.3697 | -131.0597 |  |  |  | #N/A
24026314600 | EMER-INSTALL 170' OF 2"/4"PMMP | [5 empty] | 141557.61 | 145005.519 | -3447.909 |  |  |  | 2024-02-05
24026314700 | EMER-RETIRE 120'- 8"BSMP MAIN | [5 empty] | 0 | 160.3697 | -160.3697 |  |  |  | #N/A
24026316701 | INSTALL 11245' OF 2"PMMP MAIN | [5 empty] | 1084887.24 | 1012154.1196 | 72733.1204 |  |  |  | 2024-12-12
24026316800 | RETIRE 9920' OF 4"/6"BSLP MAIN | [5 empty] | 717.72 | 118.4933 | 599.2267 |  |  |  | #N/A | GURU RETIRED 1-4"DRIP. SM 6/11.25
24026318600 | EMER - INSTALL 11' OF 2" PMMP | [5 empty] | 41990.31 | 30688.3135 | 11301.9965 |  |  |  | 2024-02-21 | INST 8' AND 3' SECTION OF 2" P MP MAIN DUE TO LEAK PER ENGINEERED TIE-IN PLAN. TEST NEW MAIN @ 90LB 20MIN OK. SOAP TEST TIE-IN @ OP OK
24026318700 | EMER - RETIRE 11' OF 2" PMP | [5 empty] | 180.42 | 160.3697 | 20.0503 |  |  |  | #N/A | RETIRE 11' OF 2" P MP MAIN DUE TO LEAK PER ENGINEERED TIE-IN PLAN. WORKED ON 2/7. MCRAIG 2/21/24
24026319600 | INSTALL SOLAR BACK UP UNIT | [5 empty] | 6617.58 | 10754.1928 | -4136.6128 |  |  |  | #N/A
24026321000 | PAPER-RETIRE ~250-3" PLP | [5 empty] | 0 | 160.3697 | -160.3697 |  |  |  | #N/A | JOB COMPLETED
24026321100 | INSTALL 1400' OF 2" PMMP MAIN | [5 empty] | 68220.66 | 53956.9279 | 14263.7321 |  |  |  | 2024-05-14
24026321200 | INSTALL EQUIPMENT & BUILDING | [5 empty] | 177086.72 | 181907.9279 | -4821.2079 |  |  |  | #N/A | CCC 86957 CCC 89138
24026321300 | RETIRE EQUIPMENT | [5 empty] | 0 | 160.3697 | -160.3697 |  |  |  | #N/A
24026322700 | INSTALL MIWI W/ SOLAR | [5 empty] | 18428.99 | 25805.1928 | -7376.2028 |  |  |  | #N/A
24026322800 | RETIRE FACILITIES | [5 empty] | 339.76 | 160.3697 | 179.3903 |  |  |  | #N/A | CCC 95201
24026323900 | UPGRADE TO FULL TIME | [5 empty] | 15170.64 | 10457.1928 | 4713.4472 |  |  |  | #N/A | CONVERTER ER350 TO FULL TIME MONITOR WITH ACP, CCC 82460, CMCHOLAN 7-29-24 FILLED OUT PAPERWORK FOR SOLAR PANEL INSTALL, CCC 86978, CMCHOLAN 9-3-24 1050
24026324000 | UPGRADE TO FULL TIME | [5 empty] | 90.3 | 160.3697 | -70.0697 |  |  |  | #N/A | UPGRADED TO FULL TIME MONITORED WITH ACP, CCC 82460, CMCHOLAN 1343
24026324400 | UPGRADE TO FULL TIME | [5 empty] | 1964.52 | 10901.0487 | -8936.5287 |  |  |  | #N/A
24026324500 | UPGRADE TO FULL TIME | [5 empty] | 709.33 | 121.4465 | 587.8835 |  |  |  | #N/A
24026324600 | UPGRADE TO FULL TIME | [5 empty] | 8507.07 | 10901.0487 | -2393.9787 |  |  |  | #N/A | CCC 82823 SUPER SOLAR INSTALL FORM COMPLETE, CCC 86978, CMCHOLAN 9-3-24 1200
24026324700 | UPGRADE TO FULL TIME | [5 empty] | 568.65 | 121.4465 | 447.2035 |  |  |  | #N/A | CCC 82823
24026324800 | MIWI WITH SOLAR | [5 empty] | 10379.92 | 13977.0487 | -3597.1287 |  |  |  | #N/A
24026324900 | RETIRE | [5 empty] | 532.44 | 121.4465 | 410.9935 |  |  |  | #N/A
24026325700 | UPGRADE SCADA SYSTEM | [5 empty] | 9180.49 | 10627.0487 | -1446.5587 |  |  |  | #N/A
24026325900 | UPGRADE SCADA SYSTEM | [5 empty] | 362.79 | 121.4465 | 241.3435 |  |  |  | #N/A
24026326200 | UPGRADE SCADA SYSTEM | [5 empty] | 8523.81 | 10627.0487 | -2103.2387 |  |  |  | #N/A | CCC 82629 CMCOX 7/30/24
24026326300 | UPGRADE SCADA SYSTEM | [5 empty] | 462.23 | 121.4465 | 340.7835 |  |  |  | #N/A | CCC 82629 CMCOX 7/30/24
24026326400 | UPGRADE SCADA SYSTEM | [5 empty] | 2879.61 | 10627.0487 | -7747.4387 |  |  |  | #N/A | CCC-82971 CCC 87260, DID SOLAR PANEL PAPERWORK, CMCHOLAN 9-4-24 1600
24026326500 | UPGRADE SCADA SYSTEM | [5 empty] | 499.97 | 121.4465 | 378.5235 |  |  |  | #N/A | CCC-82971
24026328300 | EMER - INSTALL 26'-6" PMLP | [5 empty] | 14201.79 | 28720.319 | -14518.529 |  |  |  | 45350 | REPLACED 26FT OF 060 S WITH 060 P DUE TO ATMOS CORR. TESTED PIPE FOR 1HR AT 90LBS.TEST OK. SOAP TEST BOTH COUPLINGS AT OP FOR 5MINS.TEST OK. BHB NGF. INSTALLED 2 ANODES. DENSO WRAP MAIN.
24026328400 | EMER - RETIRE 26'-6" BSLP | [5 empty] | 2990.24 | 115.5402 | 2874.6998 |  |  |  | #N/A | REPLACED 26FT OF 060 S WITH 060 P DUE TO ATMOS CORR. TESTED PIPE FOR 1HR AT 90LBS.TEST OK. SOAP TEST BOTH COUPLINGS AT OP FOR 5MINS.TEST OK. BHB NGF. INSTALLED 2 ANODES. DENSO WRAP MAIN.
24026330000 | ABANDON S/L - DEMO/ CITY RQD | [5 empty] | 7688.07 | 6179.2921 | 1508.7779 |  |  |  | #N/A | SL ABN DUE TO DEMO OF BLDG. TAP CREW AND WELDER CAPPED SL AT TAP BHB NGF, MRK BALL AT TAP, SOAP TEST AT OP OK, PLUGGED EXSISTING LINE JOB EXECUTE W/CAPITAL PACKET
24026330300 | EMER - INSTALL 5'- 2" PMMP | [5 empty] | 10905.49 | 11353.2418 | -447.7518 |  |  |  | 45384 | EXPOSED TWO ISOLATED STEEL COUPLINGS ON 020 PMP MAIN. REPLACED SECTION OF MAIN WHILE ON BYPASS.TESTED BYPASS FOR 20MINS AT 90LBS.TEST OK. TESTED MAIN FOR 1HR AT 90LBS.TEST OK. SOAP TEST COUPLINGS AT OP.TEST OK.
24026330400 | EMER-RETIRE 5'-2"PMMP | [5 empty] | 180.38 | 118.4933 | 61.8867 |  |  |  | #N/A | EXPOSED TWO ISOLATED STEEL COUPLINGS ON 020 PMP MAIN. REPLACED SECTION OF MAIN WHILE ON BYPASS.TESTED BYPASS FOR 20MINS AT 90LBS.TEST OK. TESTED MAIN FOR 1HR AT 90LBS.TEST OK. SOAP TEST COUPLINGS AT OP.TEST OK.
24026331300 | RETIRE 3"PLP S/L & C18-82 VALV | [5 empty] | 0 | 132.893 | -132.893 |  |  |  | #N/A
24026331500 | INSTALL 300' OF 2"PMMP MAIN | [5 empty] | 40161.78 | 28768.72 | 11393.06 |  |  |  | 45406
24026331800 | RETIRE 3"BSLP S/L & C14-35 VLV | [5 empty] | 0 | 66.4465 | -66.4465 |  |  |  | #N/A
24026331900 | EMER - INSTALL 1' OF 2"PMMP | [5 empty] | 3472.1 | 3799.146 | -327.046 |  |  |  | 45384 | REPAIRED DAMAGES SECTION OF PIPE. TEST REPAIR PIECE 90#20MINS, TG. ST LTI, TG. TEST FOR SECONDARY DAMAGE OK. R.CRAWFORD 4-2-24
24026332000 | EMER - RETIRE 1' OF 2"PAMP | [5 empty] | 295.06 | 121.4465 | 173.6135 |  |  |  | #N/A | REPAIRED DAMAGED SECTION OF PIPE. TEST REPAIR PIECE 90#20MINS, TG. ST LTI. TEST FOR SECONDARY DAMAGE OK. R.CRAWFORD 4-2-24
24026332100 | INSERT 50' OF 3" PMLP | [5 empty] | 25644.18 | 34491.8294 | -8847.6494 |  |  |  | 45441
24026332200 | RETIRE 52' - 4" CSLP | [5 empty] | 12630.36 | 121.4465 | 12508.9135 |  |  |  | #N/A | PART OF CAPITAL JOB
24026333000 | EMER-INSTALL 18'-4"PMLP MAIN | [5 empty] | 20568.01 | 29428.3233 | -8860.3133 |  |  |  | 45412
24026333100 | EMER-RETIRE 18'-4"BSLP MAIN | [5 empty] | 0 | 121.4465 | -121.4465 |  |  |  | #N/A
24026334000 | INSTALL 5' OF 2" PMMP | [5 empty] | 11358.98 | 3841.146 | 7517.834 |  |  |  | 45384 | FOUND COMPRESSION COUPLINGS LEAKING - SQEEZED OFFF MAIN WITH GAGE FOR PRESSURE VERIFICATION - PRESSURE REMAINED @ 53 - SOAP TEST LAST CONNECTIONS @ OP FOR 5 MIN TEST GOOD
24026334200 | RETIRE 5' OF 2" PMP | [5 empty] | 47.65 | 121.4465 | -73.7965 |  |  |  | #N/A | FOUND COMPRESSION COUPLINGS LEAKING - SQUEEZED OFF MAIN WITH GAGE FOR PRESSURE VERIFICATION- PRESSURE REMAINED @ 53 PSIG TEST NEW PIPE @ 90 FOR 1 HR TEST GOOD - INSTALLED 5 FT
24026336400 | RETIRE ~71-4" PMMP S/L | [5 empty] | 2817.23 | 124.2298 | 2693.0002 |  |  |  | #N/A
24026336500 | INSTALL ~75'-4" PMMP S/L | [5 empty] | 26538.42 | 35134.784 | -8596.364 |  |  |  | #N/A | REPL SL WITH NEW 4" PLASTIC- TST SL AND MAIN IN ONE FOR 90LBS FOR 1HOUR TST OK- SOAP TST FINAL TIE IN @OP FOR 5MIN TST OK- BHB NGF- TROE
24026336600 | INSTALL GMB SETTING | [5 empty] | 23056.34 | 48285.9326 | -25229.5926 |  |  |  | #N/A
24026336700 | RETIRE GMB SETTING | [5 empty] | 0 | 65.2298 | -65.2298 |  |  |  | #N/A
24026336800 | EMER - INSTALL 5' OF 2" PMMP | [5 empty] | 5104.57 | 3378.146 | 1726.424 |  |  |  | 45378
24026336900 | EMER - RETIRE 5' - 2" PMMP | [5 empty] | 0 | 121.4465 | -121.4465 |  |  |  | #N/A
24026337000 | INSTALL 675' OF 2"PMMP MAIN | [5 empty] | 44370.55 | 60312.9634 | -15942.4134 |  |  |  | 45433
24026338000 | INSTALL 65'-2"&4" PMMP | [5 empty] | 59541.79 | 74853.6852 | -15311.8952 |  |  |  | 45442
24026338100 | RETIRE 42'-2"&4" CSMP | [5 empty] | 96.62 | 118.4933 | -21.8733 |  |  |  | #N/A | START DATE OF INSTALL JOB WAS 5/20/24 - COMMIT DATE FOR INSTALL 5/30, COMMIT DATE FOR ABANDONMENT 5/17 - START DATE WAS AFTER COMMMIT DATE - RTINCHER 6-21-24
24026338500 | INSTALL 585' OF 2"PMMP MAIN | [5 empty] | 30882.37 | 37261.72 | -6379.35 |  |  |  | 45415
24026339000 | INSTALL OT NETWORK HARDWARE | [5 empty] | 5456.41 | 3063.0974 | 2393.3126 |  |  |  | #N/A | CCC#68493
24026339100 | RETIRE MODEM WITH IT UPGRADES | [5 empty] | 563.82 | 121.4465 | 442.3735 |  |  |  | #N/A
24026339400 | RETIRE 322'-4" CSLP | [5 empty] | 6251.56 | 8828.6617 | -2577.1017 |  |  |  | #N/A | ABD 322 FT OF CS MAIN TEST TEE 90 LB FOR 5 MIN SOAP TEST END CAP AT OP SOAP TEST 1 IN CAP AT OP BHBNGF ABDN 322 FT CS 4 IN MAIN SOAP TEST END CAP AT OP BLEW OUT ABDN MAIN AND SEALED THE END UP ON IT MARKER BALL AT DEAD END CAP
24026339800 | INSTALL 35' OF 6"PMLP MAIN | [5 empty] | 43718.9 | 45030.1866 | -1311.2866 |  |  |  | 45510 | REPLACED 56' OF 060 P LP DUE TO CROSS BORE IN SEWER. TESTED MAIN FOR 1HR AT 90LBS.TEST OK. TESTED TEMP BYPASS FOR 20MINS AT 90LBS.TESTS OK. SOAP TEST BOLTED COUPLINGS AT OP.TEST OK.SOAP TEST CLAPS AND SADDLES AT OP.TEST OK
24026339900 | RETIRE 25' OF 6"BSLP MAIN | [5 empty] | 4843.71 | 139.7787 | 4703.9313 |  |  |  | #N/A | REPLACED 56' OF 060 P LP DUE TO CROSS BORE IN SEWER. TESTED MAIN FOR 1HR AT 90LBS.TEST OK. TESTED TEMP BYPASS FOR 20MINS AT 90LBS.TESTS OK. SOAP TEST BOLTED COUPLINGS AT OP.TEST OK.SOAP TEST CLAPS AND SADDLES AT OP.TEST OK
24026340000 | EMER-INSTALL NEW PF REGULATOR | [5 empty] | 2398.18 | 5188.1947 | -2790.0147 |  |  |  | #N/A | CC 69018 NEW REG INSTALLED 04-17-2024 APARKS GHALE RHAYES CC 69018 INSTALLED PF REG SN 201920474068 AND ASV SN 201920474092 APARKS GHALE RHAYES 04-18-2024
24026340100 | EMER-RETIRE PF REGULATOR | [5 empty] | 1088.91 | 66.4465 | 1022.4635 |  |  |  | #N/A | CC 69018 REMOVED PF REG AND SLAMSHUT INSTALLED NEW PF AND SLAMSHUT ALPARKS GHALE RHAYES
24026340200 | INSTALL 600' OF 8"PMMP MAIN | [5 empty] | 388585.22 | 296422.5677 | 92162.6523 |  |  |  | 45713
24026341900 | INSTALL 4250' OF 2"/4"PMMP | [5 empty] | 160153.35 | 152744.147 | 7409.203 |  |  |  | 45541
24026342000 | EMER - INSTALL 2' OF 2"PMMP | [5 empty] | 6607.96 | 4292.2109 | 2315.7491 |  |  |  | 45426 | INST 2'- 2" P MP MAIN DUE TO DAMAGE. INST PER ENGINEERED TIE-IN PLAN. WORKED 5/2/24. SOAP TEST TIE-IN OK. MCRAIG 5/14/24
24026342100 | EMER - RETIRE 2' OF 2"PMP MAIN | [5 empty] | 109.14 | 139.7787 | -30.6387 |  |  |  | #N/A | ABN 2' OF 2" P MP MAIN DUE TO DAMGE. PER ENGINEERED TIE-IN PLAN WORKED 5/2/24. MCRAIG 5/14/24
24026342400 | INSTALL ~585'-2" PMMP | [5 empty] | 81606.34 | 85571.2987 | -3964.9587 |  |  |  | 45503
24026342500 | RETIRE ~600'-2" PMMP | [5 empty] | 324.53 | 139.7787 | 184.7513 |  |  |  | #N/A
24026343200 | DEMO BLOCK BUILDING | [5 empty] | 0 | 279.5575 | -279.5575 |  |  |  | #N/A
24026343300 | INSTALL 4" POLY VALVE | [5 empty] | 7689.14 | 18376.2056 | -10687.0656 |  |  |  | 45449
24026343400 | RETIRE 4"POLY VALVE C19-270 | [5 empty] | 796.71 | 139.7787 | 656.9313 |  |  |  | #N/A | REPLACED VALVE C19-270 NEW VALVE NUMBER KY-C1414 REFER TO JOB#24-0263433-00 A WILLIAMSON 6-6-2024
24026343500 | INSTALL 25'-8" PMLP | [5 empty] | 48462.2 | 72915.1812 | -24452.9812 |  |  |  | 45453
24026343600 | RETIRE 15'-8" CSLP | [5 empty] | 110 | 136.633 | -26.633 |  |  |  | #N/A
24026345300 | RETIRE 350' OF 4"CSLP MAIN | [5 empty] | 10006.29 | 10488.3069 | -482.0169 |  |  |  | #N/A | RETIRED 4" CS MAIN DUE TO CORROSION- PURGED ABN MAIN OUT- CAPPED ABN MAIN- SOAP TST DEAD END CAP OF MAIN FOR 5MIN @OP TST OK- BHB NGF- INST 17LB ANODE INST TESTS STATION @ END OF MAIN- TROE GURU ADDED A TEST STATION FACILITY. SM 3/28/25
24026346300 | EMER-INSTALL 3' OF 2"PMMP MAIN | [5 empty] | 6040.26 | 8304.9467 | -2264.6867 |  |  |  | 45478 | INSTALLED 3' 2" PL MIAIN DUE TO DAMAGE PER ENG. TIE IN PLAN
24026346400 | EMER-RETIRE 3' OF 2"PMMP MAIN | [5 empty] | 157.44 | 139.7787 | 17.6613 |  |  |  | #N/A | ABN 3' 2" PL MAIN PER ENG. TIE IN PLAN ABDN 322 FT CS 4 IN MAIN SOAP TEST END CAP AT OP BLEW OUT ABDN MAIN AND SEALED THE END UP ON IT MARKER BALL AT DEAD END CAP
24026346600 | EMER-INSTALL 8' OF 4"PMLP | [5 empty] | 6502.78 | 11094.6001 | -4591.8201 |  |  |  | 45533 | REPLACED TWO SECTIONS OF MAIN DUE TO DAMAGES. ALL WORK PREFORMED BY GAS STANDARDS AND TESTED BY GAS STANDARDS. ALL TESTING AND CLERICAL PAPERWORK ON CAPITAL PACKET.
24026346700 | EMER-RETIRE 8' OF 4"PMLP | [5 empty] | 10.1 | 139.7787 | -129.6787 |  |  |  | #N/A | REPLACED TWO SECTIONS OF MAIN DUE TO DAMAGES. ALL WORK PREFORMED BY GAS STANDARDS AND TESTED BY GAS STANDARDS. ALL TESTING AND CLERICAL PAPERWORK ON CAPITAL PACKET.
24026348000 | EMER-INSTALL 4' OF 3"PMMP MAIN | [5 empty] | 2333.5 | 6161.5865 | -3828.0865 |  |  |  | 45481 | INST 4' OF 3" PLASTIC PIPE- TSTED PIPE FOR 20MIN @90LBS PER FOL - TST OK- SOAP TST FINSL TIE IN @OP FOR 5MIN TST OK- BHB NGF- TROE
24026348100 | EMER-RETIRE 4' OF 3"PMMP MAIN | [5 empty] | 0 | 139.7787 | -139.7787 |  |  |  | #N/A
24026348200 | INSTALL ~30'-4" PMMP | [5 empty] | 16880.63 | 17592.9326 | -712.3026 |  |  |  | 45673 | INST 34' OF 4" PLASTIC MAIN AND 13' OF 2" PLASTIC MAIN- AND 58' OF 4" SL- TSTED ALL NEW MAIN FOR 90LBS FOR 1 HOUR- TST OK- SOAP TST FINAL TIE IN @OP FOR 5MIN TST OK- BHB NGF- TROE
24026348300 | RETIRE ~30'-4" PMMP | [5 empty] | 3460.68 | 124.2298 | 3336.4502 |  |  |  | #N/A | ABN 25' OF 4" PLASTIC MAIN DUE TO CONFLICT WITH WATER BOX- SOAP TST DEAD END CAP ON 4" FOR 5MIN @OP TST OK- SOAP TST DEAD END CAP FOR 2" MAIN @OP FOR 5MIN TST OK- TROE
24026348700 | EMER - INSTALL 5' OF 2" PMMP | [5 empty] | 8763.23 | 5410.4082 | 3352.8218 |  |  |  | 45469
24026348800 | EMER-LEAK RETIRE C14-37 | [5 empty] | 693.84 | 139.7787 | 554.0613 |  |  |  | #N/A
24026349300 | INSTALL 4"POLY VALVE KY-C1556 | [5 empty] | 22343.49 | 32958.9947 | -10615.5047 |  |  |  | 45567
24026349400 | RETIRE 10' OF 3"PMP MAIN | [5 empty] | 21.79 | 139.7787 | -117.9887 |  |  |  | #N/A
24026350500 | EMER-INSTALL 2"VALVE KY-C1586 | [5 empty] | 3282.54 | 5722.6534 | -2440.1134 |  |  |  | 45474
24026350600 | EMER-RETIRE C15-66 POLY VALVE | [5 empty] | 0 | 139.7787 | -139.7787 |  |  |  | #N/A
24026350800 | PAPER ONLY MP RETIREMENT | [5 empty] | 0 | 139.7787 | -139.7787 |  |  |  | #N/A
24026351200 | INSTALL 150' OF 2"PMIP MAIN | [5 empty] | 14499.2 | 12159.6055 | 2339.5945 |  |  |  | 45548
24026351400 | EMER - INSTALL 2'-2" PMMP | [5 empty] | 1846.55 | 5752.0111 | -3905.4611 |  |  |  | 45504 | INST 2' OF 2" PLASTIC MAIN- TSTED FOR 90LBS FOR 20MIN PER FOL TST OK- SOAP TST POINT A AND POINT B FOR 5MIN @OP TST OK- BHB NGF TROE
24026351500 | EMER - RETIRE 2'-2" PMP | [5 empty] | 14.54 | 136.633 | -122.093 |  |  |  | #N/A | REMVED 2' OF 2" DAMAGED PLASTIC PIPE DUE TO HIT LINE- REPLACED WIT NEW 2" PLASTIC PIPE TSTED FOR 90LBS FOR 20MIN PER FOL SOAP TST POINT A AND POINT B @OP FOR 5MIN TST OK- TROE
24026351800 | EMER-INSTALL 8' OF 3" PMMP | [5 empty] | 6274.49 | 8361.8798 | -2087.3898 |  |  |  | 45499 | INSTALLED 8' OF NEW 030 P PIPE AFTER REMOVING DAMAGED SECTION OF MAIN. TEST PIPE 90#20MINS, TG. PER R.VANDERPOOL. R.CRAWFORD 7-26-24
24026351900 | EMER-RETIRE 8' OF 3" PMP | [5 empty] | 6.23 | 139.7787 | -133.5487 |  |  |  | #N/A | TOOK OUT 8' OF 030 P PIPE. REPLACED W/ 8' OF NEW 030 P PIPE. R.CRAWFORD 7-26-24
24026352600 | EMER - INSTALL 2'-2" PMMP | [5 empty] | 1939.02 | 3613.4082 | -1674.3882 |  |  |  | 45510 | CONTRACTOR HIT 020 PMP WHILE DIGGING OUT SEWER BOX.SQUEEZE OFF IN BELLHOL TO MAKE SAFE.INSTALLED 3FT MAIN.TEST MAIN FOR 20MINS AT 90LBS.TEST OK.TES TEE 5MINS AT 90LBS.TEST OK.SOAP TEST EFC AT OP FOR 5MINS.TEST OK.BHB NGF
24026352700 | EMER - RETIRE 2'-2" PMMP | [5 empty] | 122.63 | 139.7787 | -17.1487 |  |  |  | #N/A | JO COMMENTS ON 557 AND 2412
24026353800 | INSTALL 180' OF 4"PMMP MAIN | [5 empty] | 167555.7 | 169246.7693 | -1691.0693 |  |  |  | 45534
24026353900 | RETIRE 164' OF 4"CSMP MAIN | [5 empty] | 419.02 | 68.2637 | 350.7563 |  |  |  | #N/A
24026354000 | INSTALL 850' OF 2"PMMP MAIN | [5 empty] | 61100.31 | 37954.6504 | 23145.6596 |  |  |  | 45530 | COULD NOT INSTALL MAIN LINE ON DOCKSIDE PK. CT. BECAUSE ROAD WAS NOT INSTAL LED AT THIS TIME COMPLETED JOB PR ANDY ELLIOT DEVELLOPER WILL CALL WHEN REA DY, LSHARON 0/26/24
24026354300 | INSTALL 1750' OF 2"PMMP MAIN | [5 empty] | 49920.61 | 59204.7838 | -9284.1738 |  |  |  | 45645
24026354900 | PAPER ONLY-LP STOPPLE FITTINGS | [5 empty] | 0 | 159.2637 | -159.2637 |  |  |  | 45506
24026355100 | EMER - RETIRE 12'-2" PMMP | [5 empty] | 482.5 | 1059.1985 | -576.6985 |  |  |  | #N/A | CONTRACTOR HIT 020 PMP MAIN DIGGING FOOTER FOR BUILDING.SQUEEZED OFF TO MAKE SAFE. END CAP INSTALLED BEFORE DITCH OF FOOTER. SOAP TEST END CAP AT OP.TEST OK. BHB NGF. ADV FOL OF ENCROACHMENT. ABDN 12FT OF MAIN.
24026355400 | EMER-INSTALL 2' OF 2"PMMP MAIN | [5 empty] | 4651.3 | 5647.5068 | -996.2068 |  |  |  | 45532 | SERVICE TEE AND SERVICE FOR 5MIN @90LBS TST OK- TSTED GAUGE TEES @90LBS FOR 5MIN TST OK- SOAP TST DEAD END CAPS ON GAUGE TEES FOR 5MIN @OP TST OK INST 2' OF 2" PLASTIC MAIN- TST MAIN @90LBS FOR 1HOUR, TST OK- SOAP TST FINAL TIE IN POINT A AND POINT B @OP FOR 5MIN TST OK- BHB NGFTST 2 PURGE TEES 5MIN @90LBS TST OK- TEST 2X1"
24026355500 | EMER-RETIRE 2' OF 2"PAMP MAIN | [5 empty] | 7.56 | 127.2637 | -119.7037 |  |  |  | #N/A | REMOVED 2' OF 2" PLASTIC MAIN- INDTALLED 2" OF 2" PLASTIC MAIN- TST FOR 1HR @90LBS TST OK- SOAP TSTT FINAL TIE IN @OP FOR 5MIN TST OK- TROE
24026355900 | INSTALL 250' OF 2"PMMP MAIN | [5 empty] | 56306.29 | 23765.9793 | 32540.3107 |  |  |  | 45596 | TWALKER/KY 11-01-24: WMS WOULD NOT ALLOW JOB ORDER REVISION DUE TO UNPAID INVOICE ERROR, PROJECT PLANNED DIRECT BORE BUT CREWS HIT ROCK REASON FOR JOB COST OVER RUN.
24026356000 | INSTALL 475' OF 2"PMMP MAIN | [5 empty] | 138117.86 | 124485.9173 | 13631.9427 |  |  |  | 45806
24026356100 | RETIRE 420' OF 2"BSLP MAIN | [5 empty] | 0 | 127.2637 | -127.2637 |  |  |  | #N/A
24026356200 | INSTALL NEW 4" CRITICAL VALVE | [5 empty] | 6237.92 | 9922.9586 | -3685.0386 |  |  |  | 45555 | INST NEW 4" POLY CRITICAL VALVE C16-184 PER ENGINEERED TIE-IN AND GS. TEST NEW VALVE @ 90LB 1HR OK. SOAP TEST TIE-IN @ OP OK. BHB NGF. CO ON 9/19 MCRAIG 9/20/24
24026356300 | RETIRE 4" POLY VALVE C16-184 | [5 empty] | 6591.98 | 127.2637 | 6464.7163 |  |  |  | #N/A | CUT OUT CRITICAL VALVE C16-184 PER ENGINEERED TIE-IN AND GS. MCRAIG 9/20/24
24026356400 | RETIRE 4"PLP SERVICE LINE | [5 empty] | 2580.83 | 127.2637 | 2453.5663 |  |  |  | #N/A | ABANDONED 4" SERVICE LINE USING EXISTING 4" CURB VALVE. THE REMAINING SERVICE LINE IS TO BE ABANDONED ON CAPITAL ABANDONMENT ORDER 24-0263168-00. JOSH PASLEY 8/13/24
24026357000 | EMER-INSTALL 50' OF 4"PMLP | [5 empty] | 19570.62 | 21585.4343 | -2014.8143 |  |  |  | 45545 | INSTALLED NEW 040 P PIPE DUE TO CORROSION. TEST PIPE 90#1HOUR, TG. ST LTI, TG. MAIN READIN TAKEN AT "GOOD" SECTIONS OF PIPE FOR NEW INSTALL R.CRAWFORD 9-10-24
24026357100 | EMER-RETIRE 50' OF 4"BSLP MAIN | [5 empty] | 8645.9 | 127.2637 | 8518.6363 |  |  |  | #N/A | RETIRED PIPE DUE TO CORROSION FOR INSTALL OF NEW 040 P PIPE. MAIN READING TAKEN AT "GOOD" SECTIONS OF PIPE FOR INSTALL OF NEW PIPE. R.CRAWFORD 9-10-24
24026357600 | RETIRE 490' OF 2"/4"PMP MAIN | [5 empty] | 3022.51 | 4637.6504 | -1615.1404 |  |  |  | #N/A | ABN PARTIAL MAIN - SOAP TEST DEAD END CAP @ OP FOR 5 MIN TEST GOOD -
24026358801 | INSTALL 4200' OF 2"/4"PMMP | [5 empty] | 782267.64 | 884925.4499 | -102657.8099 |  |  |  | 45798
24026358900 | RETIRE 914' OF 4"BSMP MAIN | [5 empty] | 0 | 135.7529 | -135.7529 |  |  |  | #N/A
24026360500 | INSTALL 18'-2" PMMP | [5 empty] | 10627.85 | 23343.2435 | -12715.3935 |  |  |  | 45594 | INST 35' OF 2" P MP MAIN PER ENGINEERED PLAN TO OFFSET IN 2 INTERSECTIONS FOR SEWER PROJECT. MCRAIG 10/29/24
24026360600 | RETIRE 10'-2" PMMP | [5 empty] | 2874.37 | 127.2637 | 2747.1063 |  |  |  | #N/A | RETIRE 10' OF 2" P MP MAIN PER ENGINEERED PLAN AND GS TO OFFSET MAIN FOR SEWER PROJECT. MCRAIG 10/29/24
24026360700 | INSTALL 230' OF 4"PMLP MAIN | [5 empty] | 19505.93 | 12568.7288 | 6937.2012 |  |  |  | 45798
24026360800 | RETIRE 620' OF 4"BSLP MAIN | [5 empty] | 110 | 135.7529 | -25.7529 |  |  |  | #N/A
24026361300 | INSTALL 750'-2" PMMP | [5 empty] | 206114.64 | 209702.6457 | -3588.0057 |  |  |  | 45735
24026363400 | PAPER ONLY MP RETIREMENT | [5 empty] | 0 | 127.2637 | -127.2637 |  |  |  | #N/A
24026363600 | INSTALL 620' OF 4"PMMP MAIN | [5 empty] | 275193.6 | 142827.5782 | 132366.0218 |  |  |  | 45615 | TWALKER/KY 11-19-24: WMS WOULD NOT ALLOW JOB ORDER TO BE REVISED DUE TO UNPAID INVOICES. JOB WILL OVER RUN.
24026363700 | RETIRE 580' OF 4"BSMP MAIN | [5 empty] | 0 | 135.7529 | -135.7529 |  |  |  | #N/A
24026365000 | EMER-INSTALL 10' - 2" PMMP | [5 empty] | 3040.57 | 3276.1865 | -235.6165 |  |  |  | 45595 | INST 10' OF 2" P MP MAIN PER ENGINEERED PLAN DUE TO FAC DAMAGE. MCRAIG 10/30/24
24026365100 | EMER-RETIRE 10' - 2" PMMP | [5 empty] | 2.82 | 135.7529 | -132.9329 |  |  |  | #N/A | CUT OUT 10' OF 2" P MP MAIN FROM DAMAGE. MCRAIG 10/30/24
24026365700 | INSTALL 320' OF 2"PMIP MAIN | [5 empty] | 29754.73 | 31921.5843 | -2166.8543 |  |  |  | 45644
24026368600 | INSTALL 640' OF 2" PMMP | [5 empty] | 50384.93 | 48981.3497 | 1403.5803 |  |  |  | 45818
24026368800 | INSTALL 5' OF 6" PMLP (PIF) | [5 empty] | 53924.5 | 22844.1865 | 31080.3135 |  |  |  | 45691
24026368900 | RETIRE 5' OF 6" BSLP | [5 empty] | 806.6 | 135.7529 | 670.8471 |  |  |  | #N/A
24026369000 | INSTALL 65'-8" PMLP | [5 empty] | 144966.81 | 108434.8433 | 36531.9667 |  |  |  | 45814 | INSTALLED NEW 8" PLASTIC MAIN, TESTED NEW MAIN AT 90PSI FOR 1 HR, TEST OKAY SOAP TEST FINAL TIE IN AT OP 5 MINS, TEST OKAY, BHBNGF
24026369100 | RETIRE 70'-12'&6" BSLP | [5 empty] | 6.18 | 108.1134 | -101.9334 |  |  |  | #N/A | INSTALLED NEW 8" PLASTIC MAIN,TESTED NEW MAIN AT 90PSI FOR 1HR, TEST OKAY SOAP TEST FINAL TIE IN AT OP 5MINS, TEST OKAY, BHBNGF
24026370400 | INSTALL RTU BUILDING | [5 empty] | 0 | 170.7529 | -170.7529 |  |  |  | #N/A
24026370600 | INSTALL 32'-6" PMLP | [5 empty] | 8317.84 | 29726.9608 | -21409.1208 |  |  |  | 45807
24026370700 | RETIRE 20'-6" BSLP | [5 empty] | 8109.18 | 112.4469 | 7996.7331 |  |  |  | #N/A
24026371100 | EMER-INSTALL 6' OF 8"PMMP | [5 empty] | 5742.34 | 5613.764 | 128.576 |  |  |  | 45786 | INSTALLED 6' OF 8" PLASTIC TO REPAIR DAMAGE, TEST 90# FOR 1.0 HR TEST OK SOAP TEST FINAL TIE IN AT OP 5 MINS, TEST OK
24026371200 | EMER-RETIRE 6' OF 8"PMP MAIN | [5 empty] | 397.39 | 111.0024 | 286.3876 |  |  |  | #N/A | ABANDONED 6' OF 8"PMP AND REPLACED WITH 6' OF 8" PMP. TEST 90# 1.0 HR TEST OK. SOAP TEST FINAL TIE IN AT OP 5 MINS TEST OK
24026371600 | EMER - INSTALL 5' - 2" PMMP | [5 empty] | 6372.3 | 4001.8556 | 2370.4444 |  |  |  | 45786 | CUST . CUT A 2' MAIN IN HALF WITH A DITCH WITCH - PRESSURE TEST @ 90 FOR 1 HOUR - SOAP TEST LAST CONNECTION @ OP FOR 5 MIN TEST GOOD
24026371700 | EMER - RETIRE 5' - 2" PMMP | [5 empty] | 45.7 | 111.0024 | -65.3024 |  |  |  | #N/A | CUST. CUT 2' MAIN IN HALF WITH A DITCH WITCH - REPLACED DAMAGED PIPED - PRESSURE TEST @ 90 FOR 1 HOUR TEST GOOD -
24026372500 | REPLACE VSAT WITH AT&T MODEM | [5 empty] | 6289.92 | 7998.4639 | -1708.5439 |  |  |  | #N/A | CCC 119698 SWITCHED PRIMARY COMMS FROM SAT TO CELL POINT 2 POINT VERIFIED WITH GAS CONTROL
24026372600 | REPLACE VSAT | [5 empty] | 0 | 111.0024 | -111.0024 |  |  |  | #N/A
24026372700 | INSTALL SOLAR BACKUP | [5 empty] | 7232.8 | 9877.4639 | -2644.6639 |  |  |  | #N/A
24026373100 | INSTALL SOLAR BACKUP | [5 empty] | 7699.73 | 9877.4639 | -2177.7339 |  |  |  | #N/A | INSTALL COMPLETE APARKS 02-12-25 1318 CCC 106887
24026375200 | EMER-INSTALL 6' OF 2"PMMP MAIN | [5 empty] | 6850.53 | 7800.6918 | -950.1618 |  |  |  | 45637
24026375300 | EMER-RETIRE 6' OF 2"PMMP MAIN | [5 empty] | 0 | 111.0024 | -111.0024 |  |  |  | #N/A
24026376700 | EMER - INSTALL 3'-2" PMMP | [5 empty] | 3141.8 | 7334.5817 | -4192.7817 |  |  |  | 45667 | JOB COMPLETE WITH CAPITAL PACKET
24026376800 | EMER - RETIRE 3'-2" PMP | [5 empty] | 6.4 | 112.4469 | -106.0469 |  |  |  | #N/A | COMPLETE WITH CAPITAL PACKET
24026376901 | INSTALL 1218'-6" PMMP | [5 empty] | 707094.52 | 626565.8286 | 80528.6914 |  |  |  | 45777
24026377000 | RETIRE 1140'-6" PMP | [5 empty] | 571.78 | 112.4469 | 459.3331 |  |  |  | #N/A
25026378600 | INSTALL 42' OF 2"/4" PMMP MAIN | [5 empty] | 26011.02 | 24410.382 | 1600.638 |  |  |  | 45714
25026378700 | RETIRE 30' OF 2"/4"PMMP MAIN | [5 empty] | 0 | 65.0024 | -65.0024 |  |  |  | #N/A
25026380600 | INSTALL SCADA VISIBILITY | [5 empty] | 10718.92 | 10377.5378 | 341.3822 |  |  |  | #N/A | CCC 113973 CCC-117909 CCC-122674 INSTALL ER350 AND SOLAR PANEL, CMCHOLAN 5-29-25
25026380800 | INSTALL SCADA VISIBILITY | [5 empty] | 9824.48 | 10377.5378 | -553.0578 |  |  |  | #N/A | CCC# 125214
25026395600 | EMER-INSTALL 3' OF 3"PMMP MAIN | [5 empty] | 330.23 | 1646.6381 | -1316.4081 |  |  |  | 45729
25026395700 | EMER-RETIRE 3' OF 3"PMP MAIN | [5 empty] | 435.29 | 160.2249 | 275.0651 |  |  |  | #N/A
25026398800 | INSTALL 3670' OF 2"/4"PMMP MN | [5 empty] | 130345.4 | 130832.2322 | -486.8322 |  |  |  | 45782
25026400900 | EMER - INSTALL 2'-4" PMMP | [5 empty] | 6330.01 | 12461.1986 | -6131.1886 |  |  |  | 45740
25026401000 | EMER - RETIRE 2'-4" PMP | [5 empty] | 0 | 137.1267 | -137.1267 |  |  |  | #N/A
25026405400 | EMER - INSTALL 2'-2" PMMP | [5 empty] | 3579.32 | 7065.0993 | -3485.7793 |  |  |  | 45807
25026405500 | EMER - RETIRE 2'-2" PMP | [5 empty] | 108.37 | 137.1267 | -28.7567 |  |  |  | #N/A
25026409300 | PAPER ONLY LP STOPPLE FITTINGS | [5 empty] | 6269.9 | 96.4144 | 6173.4856 |  |  |  | 45638
25026410600 | EMER-INSTALL 3'-2"PMMP MAIN | [5 empty] | 59.2 | 178.4144 | -119.2144 |  |  |  | 45698 | REPL SECTION OF MAIN DUE TO FAILURE
25026410700 | EMER-RETIRE 3' OF 2"PMMP MAIN | [5 empty] | 59.14 | 138.4144 | -79.2744 |  |  |  | #N/A
18026762102 | INSTALL NEW GMB | [5 empty] | 551963 | 544123.4415 | 7839.5585 |  |  |  | 44459 | GCCC TICKET NOT REQUIRED AT THIS TIME 1/11/21 CFARIS 1/13/21 GCCC TICKET NOT REQUIRED AT THIS TIME CFARIS 1/26/21 GCCC TICKET NOT REQUIRED FOR THIS JOB CFARIS DID NOT ENTER PREMISE CCC TICKET NOT REQUIRED 3/8/21 CFARIS 3/10/21 GCCC TICKET NOT REQUIRED CFARIS CCC TICKET NOT REQUIRED 3/16/21 CFARIS CCC TICKET NOT REQUIRED 3/18/21 CFARIS CMCHOLAN 4-13-2021 CCC TICKET NOT REQUIRED ON 9/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK. ERX PLACED IN SERVICE ON 9/13/2021 CFARIS
18026845002 | INSTALL THREE SSD UNITS | [5 empty] | 151615.63 | 142836.3088 | 8779.3212 |  |  |  | #N/A | INSTALLED TRITON COUPON TS CSE AND DAIRYLAND SOLID-STATE DECOUPLER (SSD) - DAIRYLAND SSD-2/2-5.0-100R (50-60) WITH EXTERNAL OR INTERNAL ISOLATION SWITCHWITH SWX-100 ENCLOSURE. TS FAC 408323 AT CARDOME, TS FAC 409481 AT BEVINS FARM REAR AND NEW TS FAC 865373 ON BEVINS FARM FIELD 2/3 ALL HAVE 1/2" ZINC RIBBON FOR AC MITIGATION AND COUPON TS WITH SSD INSTALLED. TS FAC 408320 IS NOW FLUSH MOUNT READ ONLY TS / REUSED APX 600' OF ZINC RIBBON AND ZINC MAT AT TS 408323 / REUSED 585' AND INSTALLED 565' OF ZINC RIBBON AND NEW ZINC MAT AT NEW TS 865373 / REUSED APX 1000' OF ZINC AND ZINC MAT AT TS 409481 / JMM
19026856100 | RETIRE GAUGE | [5 empty] | 0 | 73.6972 | -73.6972 |  |  |  | 44459 | WAITING ON PE APPROVAL AND ISO SKETCH CCC TICKET NOT REQUIRED ON 9/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026856800 | INSTALL 3659'-2",4"&6" PMMP | [5 empty] | 1309555.48 | 1978069.5146 | -668514.0346 |  |  |  | 44375 | W. 2ND ST SEING TIES WILL NEED TO BE UPDATED ONCE ROAD CONSTRUCTION PROJECT IS COMPLETE. ALL POLES AND MANHOLES ARE BEING MOVED. OVERRUN EXPLANATION HAS BEEN COMPLETE AND LOADED INTO WMSDOCS WORKSPACE. D. LEMONS 12/23/2021
19026856900 | RETIRE 2166'- 2"-6" P/CS/BS | [5 empty] | 468.94 | 94.7274 | 374.2126 |  |  |  | 44378
19026874200 | INSTALL 4600' OF 2"/4"/6"PMMP | [5 empty] | 148082.56 | 193673.3471 | -45590.7871 |  |  |  | 44329 | TWALKER/KY 11-15-21: PROJECT UNDER RUN WAS DUE TO LESS ROCK ON SITE THAN PL ANNED AND NO STREET/HARD SURFACE REPAIRS REQUIRED THAT LOWER CONTRACT COST BY $25,000. LACK OF ROCK AND HARD SURFACE REPAIRS SPED UP CONSTRUCTION TIME AND LOWER COMPANY COST BY $XXXX AND SEGA WAS $4000 LOWER THAN ESTIMATE. COMPANY COST LOWER BY $3000 THAN ESTIMATE.
20026929300 | UPGRADE ELECTRONICS | [5 empty] | 6355.62 | 3038 | 3317.62 |  |  |  | 44312 | REPLACED EFC
20026929400 | UPGRADE ELECTRONICS | [5 empty] | 293.46 | 3038 | -2744.54 |  |  |  | 44518 | REPLACED EFC
20026929500 | UPGRADE ELECTRONICS | [5 empty] | 5670.86 | 3038 | 2632.86 |  |  |  | 44753 | RETIRED OLD MINNI-AT INSTALLED NEW EC350 BLONE 07-11-2022
20026929600 | UPGRADE ELECTRONICS | [5 empty] | 3403.36 | 3038 | 365.36 |  |  |  | 44312 | REPLACED EFC
20026929700 | UPGRADE ELECTRONICS | [5 empty] | 3985.53 | 3038 | 947.53 |  |  |  | 44516 | REPLACED EFC
20026935000 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 |  |  |  | 44302 | REPLACE EFC JOB ON HOLD 2020 BECAUSE OF COVID 19
20026935100 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 |  |  |  | 44518 | REPLACED EFC
20026935200 | RETIRE ELECTRONICS | [5 empty] | 742.7 | 73.3494 | 669.3506 |  |  |  | 44753 | RETIRED OLD MINI-AT INSTALLED NEW EC350 BLONE 07-11-2022
20026935400 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 |  |  |  | 44516 | REPLACED EFC
20026942000 | INSTALL I&C EQUIPMENT | [5 empty] | 14182.01 | 16155.4774 | -1973.4674 |  |  |  | 44459 | CCC# 30920 CCC TICKET NOT REQUIRED ON 9/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026943100 | INSTALL I&C EQUIPMENT | [5 empty] | 14038.9 | 16155.4774 | -2116.5774 |  |  |  | 44617 | CCC# 43654 INSTALLED ERX RETIRED PAPER CHART BLONE 2-25-2022
20026943200 | RETIRE GAUGE | [5 empty] | 259.73 | 91.4991 | 168.2309 |  |  |  | 44617 | INSTALLED NEW LEGACY ERX RETIRED PAPER CHART BLONE 2-25-2022
20026945400 | RETIRE 1431'-2"-4" BSLP | [5 empty] | 1066.35 | 94.7274 | 971.6226 |  |  |  | 44357 | ABANDONMENTS OF MAINLINE WERE DONE WITH JO# 20-0269755-00.
20026952900 | REPLACE ROOF | [5 empty] | 12246.18 | 4729 | 7517.18 |  |  |  | 44985
20026953701 | INSTALL 6100' OF 2"/4"PMMP | [5 empty] | 1646234.22 | 1430757.5003 | 215476.7197 |  |  |  | 44498 | TWALKER/KY 05-04-22: JOB OVER RUN DUE TO $65,000 SPEND ON OFF DUTY POLICE DUE TO HIGH CRIME/TRAFFIC AREA, STATE REQUIRED MILL/PAVING OF HOLME ST INCREASED CONTRACT COST BY $85,000. SEGA INCREASED BY $51,000 OVER EST.
20026953800 | RETIRE 8800' OF 4"/6"BSLP MAIN | [5 empty] | 0 | 240.2222 | -240.2222 |  |  |  | 44498
20026954400 | INSTALL 12,500' OF 6"PMMP | [5 empty] | 671261.21 | 584465.9269 | 86795.2831 |  |  |  | 44547 | GAS WAS ONLINE BEFORE COMMIT DATE. HAD TO FINISH UP RESTORATION AND PROJEC T INFO. STEVE CANOY 12/17/2021
20026954500 | INSTALL 72' OF 4"CSHP MAIN | [5 empty] | 50107.73 | 48741.5249 | 1366.2051 |  |  |  | 44329
20026954900 | INSTALL SKID REG STATION #1574 | [5 empty] | 83537.33 | 91083.0917 | -7545.7617 |  |  |  | #N/A | TUBE UP ONE RUN CCC #22458 CCC# 22583 CC# 23111 G.HALE 05-12-21 PLACED RUN 1 IN SERVICE ON 5/6/21 WITH TEMPORARY REGULATORS INSTALLED TO MEET COMMIT DATE WITH BUILDER RUN 2 OFF AND BLIND FLANGED PERMANENT EQUIPMENT ORDER WITH TENTATIVE DELIVERY DATE OF JUNE/JULY 2021 JOB CANNOT BE COMPLETED OR CLOSED OUT UNTIL PERMANENT EQUIPMENT IS INSTALLED CFARIS CCC# 43393 CCC# CALLED IN BY AL PARKS OR CONNER WIMPE CCC#55276 CWEMPE 2/15/22 GCCC# 56179 INSTALLED PERMANENT SLAMSHUT MOONEY'S COMMISSIONED STATION CWEMPE 2-16-22
20026960600 | INSTALL NEW TRANSMITTERS | [5 empty] | 9652.42 | 5450.0793 | 4202.3407 |  |  |  | 44795 | INSTALLED NEW INLET AND OUTLET ROSEMONT 4088B TRANSMITTERS GHALE 8-22-2022
20026960700 | RETIRE DAMAGE TRANSMITTER | [5 empty] | 542.77 | 80.9227 | 461.8473 |  |  |  | 44795 | INSTALLED NEW INLET AND OUTLET TRANSMITTERS GHALE 8-22-2022
20026974601 | INSTALL 6,500'-4"PMLP | [5 empty] | 2992726.14 | 2219393.0276 | 773333.1124 |  |  |  | 45212
20026974700 | RETIRE 6,900'-BSLP,CSLP,PLP | [5 empty] | 220 | 66.2135 | 153.7865 |  |  |  | 45281
20026975400 | INSTALL 2250'-2" PMMP | [5 empty] | 859560.09 | 623618.1819 | 235941.9081 |  |  |  | 44516 | PROJECT COMPLETED ON 11-16-2021 D.LEMONS 3/2/2022: PROJECT OVERRUN WAS DUE TO ADDITIONAL TIME REQUIRED TO C OMPLETE PROJECT DUE TO MULTIPLE CONTRACTORS IN AREA DURING PROJECT. ESTIMA TED FOR 645 MAN HOURS, BUT REQUIRED 1018 MAN HOURS. ADDITIONAL $85K IN CONT RACT EXPENSES, $36K IN LABOR COSTS WHICH LEAD TO INCREASE OF $32K IN SEGA. THERE WAS A SLIGHT REDUCTION IN OTHER COST TO ACCOUNT FOR THE $147K OVERRUN .
20026975500 | RETIRE 3515'-2",3",4"& 6" | [5 empty] | 142.7 | 107.2796 | 35.4204 |  |  |  | 44516 | PROJECT COMPLETE ON 11162021
20026978900 | RETIRE GMB SETTING | [5 empty] | 0 | 83.3805 | -83.3805 |  |  |  | 44459 | JOB WAS ON HOLD UNTIL 2021 GCCC TICKET NOT REQUIRED ON 9/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026979000 | RETIRE SERVICE | [5 empty] | 2450.84 | 83.3805 | 2367.4595 |  |  |  | 44308 | THIS IS PAPER KILL ONLY
20026979100 | RETIRE SERVICE | [5 empty] | 0 | 83.3805 | -83.3805 |  |  |  | 44307
20026979201 | INSTALL SERVICE TO GMB | [5 empty] | 201470.53 | 135908.7766 | 65561.7534 |  |  |  | 44315 | LEVEL 2 BUDGET VARIANCE LOADED INTO WMSSDOCS. D.LEMONS 9/22/21
20026979300 | RETIRE 12'-8" CSHP | [5 empty] | 3655.53 | 134.3805 | 3521.1495 |  |  |  | 44307
20026989800 | INSTALL 800'-2" PMMP | [5 empty] | 33245.15 | 25809.9211 | 7435.2289 |  |  |  | 44326
20026990800 | RETIRE INLET PIPING R 1502 | [5 empty] | 0 | 240.2222 | -240.2222 |  |  |  | 44498
20026991300 | INSTALL 350'-2" PMMP | [5 empty] | 19273.52 | 31069.259 | -11795.739 |  |  |  | 44258 | 337 FT 2 " MEDIUM PRESSURE MAIN INSTALLED BY STANLEY PIPELINE YELLOW MED IUM DENSITY.PIPE
21026101700 | INSTALL NEW GMB SETTING | [5 empty] | 40071.73 | 57815.8896 | -17744.1596 |  |  |  | 44516 | INSTALLED NEW GMB SETTING
21026102400 | RETIRE WOODFORD GMB | [5 empty] | 0 | 84.0131 | -84.0131 |  |  |  | 44516 | RETIRED OLD GMB SETTING AFTER NEW SETTING PLACED IN SERVICE
21026103000 | INSTALL CHAIN LINK FENCE | [5 empty] | 20497.91 | 16434.2505 | 4063.6595 |  |  |  | 44608 | RHAYES 08-24-2021 MONITORED FENCE INSTALLATION CCC 35764 CWEMPE PAPER WORK COMPLETION 2-16-22
21026106500 | EMER - INSTALL 4' OF 2"PMMP | [5 empty] | 7429.12 | 7343.079 | 86.041 |  |  |  | 44252
21026106600 | EMER - RETIRE 4' OF 2"PMMP | [5 empty] | 0 | 82.208 | -82.208 |  |  |  | 44252
21026107100 | INSTALL COMMUNICATIONS | [5 empty] | 3375.12 | 1691.2937 | 1683.8263 |  |  |  | 44540 | CCC#41275 CCC#17228 INSTALLED SUPER SOLAR KIT AND BATTERY UPGRADED TO RV50 CELL MODEM CONVERTED TO FULL TIME MONITORING RTU TICKET NUMBER 4339
21026107200 | RETIRE 33' OF 4"PMMP S/L | [5 empty] | 1.8 | 76.3208 | -74.5208 |  |  |  | 44517
21026107300 | INSTALL 140' OF 4"PMMP S/L | [5 empty] | 53188.18 | 57302.0236 | -4113.8436 |  |  |  | 44511
21026107500 | EMER- INSTALL120'-2" PL | [5 empty] | 2045.88 | 13083 | -11037.12 |  |  |  | 44357 | INSTALLED 155' OF 2" P-MP MAIN DUE TO LEAK, SEE CAPITAL PACKET JO# 21-0261075-00, CDESPAIN 3-4-21
21026107600 | RETIRE MAIN - LEAKAGE D304381 | [5 empty] | 14663.28 | 56.3197 | 14606.9603 |  |  |  | 44357 | REPLACED 155' OF 2" P- MP MAIN, FOUND 2BOLT COUPLING PL-PL CORRODED AND LEAKING, SQUEEZED OFF, REPLACED MAIN, SEE JO PACKET 21-0261075-00 CDESPAIN 3-4-21
21026109600 | INSTALL 351'-2" PMMP | [5 empty] | 28594.76 | 20339.7093 | 8255.0507 |  |  |  | 44392
21026111902 | INSTALL 7,500' OF 2"/6"PMMP | [5 empty] | 671698.12 | 670404.9715 | 1293.1485 |  |  |  | 44631 | LOWES (#207438) - MATERIAL FOR ECP - $27.62 + 10% = $30.38 U461423 9/2 3/2021 SITE SUPPLY (#207438) - MULCH LOGS - #424.00 + 10% = 466.40 U461423 9/23/2021
21026113900 | INSTALL 1300' OF 2"/4"PMMP | [5 empty] | 34584.47 | 66451.1814 | -31866.7114 |  |  |  | 44461 | MISSED COMMIT DATE DUE TO WEATHER UNDERRUN EXPLANATION: THE UNDERRUN VARIANCE IS DUE TO 50% ROCK EXCAVATION A ND 50% LESS DUST AND STONE. THE OVER HEAD EFFECT OF THESE REDUCTIONS ALSO PLAYED A FACTOR.
21026114000 | EMER - RETIRE 145' OF 2"BSLP | [5 empty] | 1254.24 | 3325.023 | -2070.783 |  |  |  | 44293 | RETIRED 146' OF 2" BSLP MAIN, SOAP TEST BOLTED DEAD END CAP AT OP, OK. SOAP TEST SADDLES AND PAC CLAMPS AT OP OK. BHB NGF. INSTALLED 9# ANODE. MAIN READ# -0.643. MAIN INSP OK. WHIMES 04/07/2021
21026114200 | INSTALL 100'-2" PMMP | [5 empty] | 19306.24 | 12690.4563 | 6615.7837 |  |  |  | 44770
21026114300 | RETIRE EFC | [5 empty] | 0 | 111.0751 | -111.0751 |  |  |  | 44307
21026115500 | INSTALL 9560' OF 2"PMMP | [5 empty] | 2294747.45 | 1674772.7999 | 619974.6501 |  |  |  | 45107
21026115600 | RETIRE 9,590' OF BSLP & OTHER | [5 empty] | 182.4 | 67.799 | 114.601 |  |  |  | 45107
21026117600 | RETIRE REG STATION 1522 | [5 empty] | 0 | 3579.3015 | -3579.3015 |  |  |  | 45099
21026118100 | INSTALL 5680'-2"/4" PMMP | [5 empty] | 156088.03 | 165876.9601 | -9788.9301 |  |  |  | 44762
21026118900 | INSTALL REGULATORS | [5 empty] | 4450.3 | 6803.6557 | -2353.3557 |  |  |  | 44460 | CCC# 38381 REPLACED REGULATORS ON 9/16/2021 GCCC TICKET NOT REQUIRED ON 9/21/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026119000 | RETIRE REGULATORS | [5 empty] | 572.72 | 85.0089 | 487.7111 |  |  |  | 44460 | REPLACED REGULATORS ON 9/16/21 CCC TICKET 38381 OBTAINED ON INSTALL JO CCC TICKET NOT REQUIRED ON 9/21/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026119400 | PM- INST FIL/SEP TOYOTA STA | [5 empty] | 3658431.91 | 1687500 | 1970931.91 |  |  |  | 44840
21026119500 | PM-ABAN FOR FILTER INST TOYOTA | [5 empty] | 522788.31 | 62500 | 460288.31 |  |  |  | 44840
21026119600 | PM- TURNER STATION REPLACEMENT | [5 empty] | 4896097.44 | 1012500 | 3883597.44 |  |  |  | 44796
21026119700 | PM- TURNER STATION ABANDONMENT | [5 empty] | 379030.64 | 62500 | 316530.64 |  |  |  | 44796
21026120200 | PM-INS PIG REC/FILTER JIM BEAM | [5 empty] | 4126203.26 | 2579017 | 1547186.26 |  |  |  | 44742
21026120300 | PM-ABA FOR EQUIP INST JIM BEAM | [5 empty] | 835157.07 | 62500 | 772657.07 |  |  |  | 44742
21026121300 | PM- SEWELL REPLACEMENT | [5 empty] | 4500640.76 | 1087500 | 3413140.76 |  |  |  | 44721
21026121400 | PM- SEWELL ABANDONMENT | [5 empty] | 692165.24 | 62500 | 629665.24 |  |  |  | 44721
21026121700 | INSTALL 10' OF 6"PHHP MAIN | [5 empty] | 14437.27 | 16348.9255 | -1911.6555 |  |  |  | 44354
21026121800 | RETIRE 10' OF 6"PHHP MAIN | [5 empty] | 0 | 80.3582 | -80.3582 |  |  |  | 44354
21026123600 | REPLACE MAIN - LEAKAGE D253626 | [5 empty] | 2711.68 | 5432.0527 | -2720.3727 |  |  |  | 44329
21026123700 | EMER 10'-2" PMLP | [5 empty] | 0 | 85.0408 | -85.0408 |  |  |  | 44329
21026124100 | INSTALL 300'-2" PMMP | [5 empty] | 41987.03 | 24076.2901 | 17910.7399 |  |  |  | 44505
21026131001 | EMER-INSTALL 10' OF 2"PMMP | [5 empty] | 34645.29 | 34334.8702 | 310.4198 |  |  |  | 44370
21026131100 | EMER-RETIRE 10' OF 2"PAMP MAIN | [5 empty] | 0 | 74.8797 | -74.8797 |  |  |  | 44370
21026131200 | INSTALL 4875' OF 2"/4"PMMP | [5 empty] | 140463.01 | 141168.2553 | -705.2453 |  |  |  | 44697
21026131900 | INSTALL 3843' OF 2"/4"PMMP MN | [5 empty] | 1468486.46 | 807937.3693 | 660549.0907 |  |  |  | 44840 | PROJECT COST OVERRUN DUE TO ADDITIONAL TIME AND RESOURCES NEEDED. CONTRACT COSTS AND LABOR COSTS INCREASED DUE TO UNEXPECTED ROCK ENCOUNTERED DURING C ONSTRUCTION FOR BORE/OPEN CUT OF NEW MAIN. ADDITIONAL TIE-IN LOCATIONS WERE REQUIRED FOR INSTALL AND ABANDONMENT. INCREASED FLAGGING AND INCREASED RES TORATION COSTS ALSO CONTRIBUTED TO THE OVERRUN, AS WELL AS INCREASED SEGA C OSTS. MOLIVER 1/24/23
21026132000 | RETIRE 3700' OF 4"/6"BSLP MAIN | [5 empty] | 3419.35 | 52.2976 | 3367.0524 |  |  |  | 44840
21026132600 | INSTALL NEW TRANSMITTERS | [5 empty] | 14392.01 | 15506.2901 | -1114.2801 |  |  |  | 44540 | CCC #34292 WAITING ON ISO
21026132700 | RETIRE DAMAGED TRANSMITTERS | [5 empty] | 0 | 82.634 | -82.634 |  |  |  | 44540 | WAITING ON ISO SKETCH REPLACED TRANSMITTERS AND RV50 DAMAGED BY LIGHTENING
21026133100 | INSTAL 2" MOONEY REGS | [5 empty] | 11609.08 | 9907.1191 | 1701.9609 |  |  |  | 44494 | REPLACED REGULATORS GCCC TICKET NOT REQUIRED
21026133200 | RETIRE FISHER 399 REGS | [5 empty] | 0 | 90.361 | -90.361 |  |  |  | 44494 | REPLACED REGULATORS GCCC TICKET NOT REQUIRED
21026134400 | RETIRE 98' OF 2"PMMP MAIN | [5 empty] | 4653.06 | 3547.617 | 1105.443 |  |  |  | 44418
21026138201 | EMER-INSTALL 480' OF 6"PMLP | [5 empty] | 194700.21 | 240281.6735 | -45581.4635 |  |  |  | 44502 | CCC# 43819 CCC# 43967 TWALKER/KY 05-04-22: JOB CURRENTLY UNDER RUNNING SINCE CITY OF FRANKFORT HAS NOT PAVED STREET AND BILLED CKY - PAVING ESTIMATE AT $35,000.
21026138300 | EMER-RETIRE 490' OF 6 5/8"BSLP | [5 empty] | 71.35 | 82.634 | -11.284 |  |  |  | 44502 | KBOTKINS ENTERED WIPE SAMPLE FOR OLIVER MAYNARD WHO IS ATTEMPTING TO COMPLETE THE JOB FOR CLOSE OUT. SAMPLE TAKEN 4/20/22 BUT SYSTEM WOULD NOT ACCEPT THAT DATE DUE TO THE CO DATE.
21026138900 | INSTALL 650'-6" PMMP | [5 empty] | 111751.03 | 35779.3166 | 75971.7134 |  |  |  | 44805 | COST INCREASE FOR LABOR HOURS AND CONTRACT COSTS DUE TO INCREASED DIRECTION AL BORE FOOTAGE, GPS DATA COLLECTION, INCREASED RESTORATION COSTS, ADDITION AL TIE-IN LOCATIONS NEEDED, AND INCREASE IN SEGA COSTS. - MOLIVER
21026141000 | EMER - INSTALL 5'-4" PMMP | [5 empty] | 0 | 427 | -427 |  |  |  | 44448
21026141100 | EMER - RETIRE 5'-4" PMMP | [5 empty] | 0 | 68.3073 | -68.3073 |  |  |  | 44448
21026144300 | EMER - INSTALL 2' OF 2"PMIP | [5 empty] | 137.16 | 2750.8249 | -2613.6649 |  |  |  | 44465
21026144400 | EMER - RETIRE 2' OF 2"PAIP | [5 empty] | 0 | 75.4968 | -75.4968 |  |  |  | 44465
21026145200 | EMER-INSTALL NEW BYPASS VALVES | [5 empty] | 634.37 | 4285.9461 | -3651.5761 |  |  |  | 44557 | CCC# 44725 BYPASS VALVES INSTALLED BY WADE SHIMFESSEL ALONG WITH CONTRACT CREW PAPERWORK COMPLETED BY CYNTHIA FARIS 12/27/21
21026145300 | EMER-RETIRE BYPASS VALVE | [5 empty] | 0 | 60.6987 | -60.6987 |  |  |  | 44572 | VALVE REPLACED BY WADE SHIMFESSEL AND CONTRACT CREW ON 11/3/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/11/2022
21026147300 | INSTALL 400'-4" PMMP-SER | [5 empty] | 32919.84 | 22333.8994 | 10585.9406 |  |  |  | #N/A | COMMIT DATE MISSED DUE TO WEATHER
21026149500 | EMER-INSTALL 26'-3"/4"PMMP MN | [5 empty] | 23766.13 | 10953.3154 | 12812.8146 |  |  |  | 44517 | SPLIT IN ALDYLA MAIN.INSTALLED BYPASS.REPLACED CRACKED MAIN AND INLINE TEE WHILE MAIN ON BYPASS.ALL TESTING INFO ON 21026149600 AND 21026149500 IN DOCS
21026149600 | EMER-RETIRE 26'- 4"PAMP MAIN | [5 empty] | 86.15 | 61.5191 | 24.6309 |  |  |  | 44517 | SPLIT IN ALDYLA MAIN.INSTALLED BYPASS.REPLACED CRACKED MAIN AND INLINE TEE WHILE MAIN ON BYPASS.ALL TESTING INFO ON 21026149600 AND 21026149500 IN DOCS
21026156600 | INSTALL 230'-2" PMMP | [5 empty] | 17647.7 | 15538.521 | 2109.179 |  |  |  | 44621
21026157100 | INSTALL 600'-2" PMMP | [5 empty] | 29494.94 | 21934.2504 | 7560.6896 |  |  |  | 44608
21026157200 | INSTALL 16' OF 3"PMMP MAIN | [5 empty] | 56295.03 | 11827.5319 | 44467.4981 |  |  |  | 44615 | TWALKER/KY 02-24-22: WMS WOULD NOT ALLOW PROJECT TO BE REVISED DUE TO UNPAID INVOICES MESSAGE. JOB OVER RUN DUE TO UNKNOWN BOLTED COUPLINGS FOUND DURING CONSTUCTION AND SCOPE OF WORK WAS INCREASED TO REMOVE THOSE COUPLINGS IN THE PAVED STREET. TWALKER/KY 09-16-22: DURING CONSTRUCTION BOLTED COUPLING WERE FOUND ON MP GAS MAIN AND HAD TO BE REMOVED WMS WOULD NOT ALLOW REVISION. ADDITIONAL WORK INCREASED COMPANY LABOR BY $6000 SEGA INCREASED BY $4500 STREET CUT REPAIR REQUIRED AND ADDITIONAL CONTRACT RESOURCES INCREASED BY $27,000
21026157300 | RETIRE 14' OF 3"CSMP MAIN | [5 empty] | 0 | 72.8047 | -72.8047 |  |  |  | 44615
21026994800 | RETIRE STATION 1502 | [5 empty] | 8422.17 | 4108.4893 | 4313.6807 |  |  |  | 44502 | CCC# 37974 CCC#41227 CCC#41449 CCC# 41449 STATION ABANDONED ON 10/12/2021 PAPERWORK COMPLETED ON 11/2/2021 GCCC TICKET NOT REQUIRED ON 11/2/21 OFF SITE COMPLETING PAPERWORK CFARIS
21026998201 | INSTALL 1930'-2"/4" PMMP | [5 empty] | 114169.59 | 114050.6727 | 118.9173 |  |  |  | 44866 | GAS ON MAIN 11/01/2022
21026999700 | INSTALL 125' OF 2"PMMP MAIN | [5 empty] | 22070.53 | 28787.2695 | -6716.7395 |  |  |  | 44482
21026999800 | RETIRE 115' OF 2"PMMP MAIN | [5 empty] | 0 | 81.0887 | -81.0887 |  |  |  | 44483
22026158100 | INSTALL 70'-2" PMMP | [5 empty] | 10660.65 | 9277.6445 | 1383.0055 |  |  |  | 44630 | INSTALED 57'OF 020PMMP.
22026160100 | PM-GREENSITE I75 ILI DE RELO | [5 empty] | 9503.69 | 0 | 9503.69 |  |  |  | 44764
22026160200 | PM-GREENSITE I75 ILI DE ABAN | [5 empty] | 105.53 | 0 | 105.53 |  |  |  | 44764 | GIS HAD LESS FOOTAGE THAN WHAT WAS FIELD VERIFIED. NO FAC CREATED, DUE TO F ACT IT WAS BEING ABANDONED.
22026160400 | EMER - REPAIR LEAK | [5 empty] | 8003.12 | 3388.6445 | 4614.4755 |  |  |  | 44574
22026160500 | EMER - REPAIR LEAK | [5 empty] | 0 | 69.6571 | -69.6571 |  |  |  | 44574
22026168000 | HVAC AND RTU PANEL UPGRADE | [5 empty] | 22883.04 | 39849.6755 | -16966.6355 |  |  |  | 45019 | PAPER JOB COMPLETION.
22026168600 | INSTALL 13,800'-2"PMMP | [5 empty] | 1532684.69 | 1751471.355 | -218786.665 |  |  |  | 45177
22026168700 | RETIRE 12,327'-BSLP,CSLP,PLP | [5 empty] | 0 | 89.0305 | -89.0305 |  |  |  | 45177
22026169200 | EMER-INSTALL 4' OF 2"PMMP MAIN | [5 empty] | 4368.24 | 5880.7828 | -1512.5428 |  |  |  | 44607
22026169300 | EMER-RETIRE 4' OF 2"PMMP MAIN | [5 empty] | 0 | 107.3789 | -107.3789 |  |  |  | 44607
22026179400 | RETIRE 100' OF 4"PMMP MAIN | [5 empty] | 0 | 75.4968 | -75.4968 |  |  |  | 44694
22026181600 | RELOCATE ~5"-2" PMMP | [5 empty] | 10366.16 | 6138.9503 | 4227.2097 |  |  |  | 44726 | DURING AND AFTER REPLACEMENT PURGE NEW MAIN INTO SERVICE CO M.COLLINS/B.SEXTON RLA 6-7-2022 REPLACED 10' OF 2" P MP MAIN TEST 10' OF 2" PIPE ONSITE 90LBS FOR 1 HR NO LEAKS SOAP TEST TIE IN NO LEAKS BHB NGF SOAP TEST ALL TEE'S CAPS AND DEAD ENDS AT OP AFTER GUAGE REMOVAL NO LEAKS VERIFY DELIVERY PRESSURE BEFORE
22026181700 | RELOCATE ~5"-2" PMMP | [5 empty] | 0 | 75.4968 | -75.4968 |  |  |  | 44726
22026183001 | INSTALL 4955'-2" PMMP | [5 empty] | 124010.5 | 134870.3496 | -10859.8496 |  |  |  | 45436
22026185800 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 1834.52 | 5480.5156 | -3645.9956 |  |  |  | 44706 | CCC# 68240 - REPLACED ERX WITH MIWI 350 - BLONE/CWEMPE - 05/25/22 INSTALLED NEW MIWI 350
22026185900 | RETIRE ELECTRONIC COMPONETS | [5 empty] | 501.88 | 124.5156 | 377.3644 |  |  |  | 44706 | CCC# 68240 - REPLACED ERX WITH MIWI 350 - BLONE/CWEMPE - 05/25/22 RETIRED OLD ERX
22026186200 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 0 | 5480.5156 | -5480.5156 |  |  |  | 44704 | INSTALLED NEW MIWI 350 05/23/2022 GHALE
22026186300 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 190.3 | 124.5156 | 65.7844 |  |  |  | 44704 | RETIRED OLD ERX 05/23/2022 GHALE
22026186400 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 548.88 | 5480.5156 | -4931.6356 |  |  |  | 44705 | CCC# 68048 RETIRED ERX AND INSTALLED NEW MIWI350 JPASLEY
22026186500 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 0 | 124.5156 | -124.5156 |  |  |  | 44705 | RETIRED ERX AND INSTALLED NEW MIWI350 JPASLEY
22026186800 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 1456 | 4357.5409 | -2901.5409 |  |  |  | 44715 | CCC-69443 INSTALLED NEW MIWI 350 SOAP TEST CONNECTIONS EBLANTON
22026186900 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 504.03 | 124.5156 | 379.5144 |  |  |  | 44715 | CCC-69443 RETIRED ERX EBLANTON
22026188400 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 1456 | 6681.5691 | -5225.5691 |  |  |  | 44714 | CCC# 69290 - BLONE - 06/02/22 INSTALLED MIWI SN:13450082 P1-0-PSI P2-0-60 IP:10.22.4.15MDN 859-221-6738
22026188500 | RETIRE ELECTRONICS | [5 empty] | 473.46 | 74.2578 | 399.2022 |  |  |  | 44714 | CCC# 69290 - BLONE - 06/02/22
22026188600 | INSTALL 165'-2" PMMP | [5 empty] | 11945.7 | 14323.3857 | -2377.6857 |  |  |  | 44741
22026195400 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 682.09 | 4801.1928 | -4119.1028 |  |  |  | 44795 | CCC# 78156 PAPERWORK ONLY - NO CCC NEEDED - BLONE - 11/8/22 INSTALLED NEW MIWI350 B LONE 8-22-2022
22026195500 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 676.72 | 124.8731 | 551.8469 |  |  |  | 44795 | CCC# 78156 RETIRED OLD ERX INSTALLED NEW MIWI350 BLONE 8-22-22
22026195600 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5406.36 | 4801.1928 | 605.1672 |  |  |  | 44805 | CCC# 78341 - BLONE - 08/23/22 UPGRADED ERX TO MIME CO BY J.MULLINS
22026195700 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 381.79 | 124.8731 | 256.9169 |  |  |  | 44805 | CCC# 78341 B. LONE UPDATTED ERX TO MIWI CO BY J. MULLINS
22026198900 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5462.44 | 4801.1928 | 661.2472 |  |  |  | 44810 | CCC#79730 CWEMPE 9/6/22 UPGRADED ERX TO MIWI PAPERWORK DONE BY J.MULLINS
22026199000 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 252.74 | 124.8731 | 127.8669 |  |  |  | 44810 | CCC#79730 CWEMPE 9/6/22
22026199300 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5269.21 | 4801.1928 | 468.0172 |  |  |  | 44805 | CCC# 79486 RETIRED ERX INSTALLED NEW MIWI350 GHALE 9-1-2022
22026199400 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 169.77 | 124.8731 | 44.8969 |  |  |  | 44805 | CCC# 79486 RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 9-1-2022
22026199500 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5358.86 | 4801.1928 | 557.6672 |  |  |  | 44812 | CCC# 80149 P2P OK RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 9-8-2022
22026199600 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 509.01 | 124.8731 | 384.1369 |  |  |  | 44812 | CCC# 80149 RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 09-08-2022
22026200700 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5573.15 | 4801.1928 | 771.9572 |  |  |  | 44797 | CCC# 68204 - BLONE - 08/24/22 CCC#68204 TIME CHARGED FOR COMPLETING PAPERWORK. CWEMPE 8/30/22 RETIRED ERX INSTALLED NEW MIWI350 CWEMPE 8-24-2022
22026200800 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 285.19 | 124.8731 | 160.3169 |  |  |  | 44797 | CCC# 68204 - BLONE - 08/24/22 CCC#68204 RETIRED OLD ERX INSTALLED NEW MIWI350 CWEMPE 8-24-2022
22026201100 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5540.17 | 4801.1928 | 738.9772 |  |  |  | 44812 | CCC# 80069 P2P OK RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 9-8-2022
22026201200 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 157.47 | 124.8731 | 32.5969 |  |  |  | 44812 | CCC# 80069 RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 9-8-2022
22026202500 | INSTALL 1120'-2"/4" PMMP | [5 empty] | 50092.05 | 49758.6341 | 333.4159 |  |  |  | 44867
22026205401 | INSTALL 1330'-4" PMMP | [5 empty] | 288486.41 | 229795.8687 | 58690.5413 |  |  |  | 45377
22026207500 | INSTALL NEW CONTROL REGULATOR | [5 empty] | 893.82 | 1471.7874 | -577.9674 |  |  |  | 44791 | CCC#77790 INSTALLED NEW 461-57S CONTROL REGULATOR CWEMPE 8-18-22
22026207600 | REPLACE CONTROL REG | [5 empty] | 487.94 | 65.0112 | 422.9288 |  |  |  | 44791 | CCC#77790 REMOVED CONTROL REGULATOR CWEMPE 8-18-22
22026208600 | EMER - INSTALL 2'-2" PMMP | [5 empty] | 7597.73 | 5654.5749 | 1943.1551 |  |  |  | 44747
22026208700 | EMER - RETIRE 2'-2" PMP | [5 empty] | 0 | 63.5475 | -63.5475 |  |  |  | 44747
22026210901 | INSTALL 8OO' OF 2"PMMP MAIN | [5 empty] | 53441.52 | 49945.6881 | 3495.8319 |  |  |  | 45342
22026211200 | EMER-INSTALL 6' OF 4"PMIP MAIN | [5 empty] | 13924.65 | 10641.1495 | 3283.5005 |  |  |  | 44749
22026211300 | EMER-RETIRE 6' OF 4"PAIP MAIN | [5 empty] | 0 | 65.0112 | -65.0112 |  |  |  | 44749
22026213400 | INSTALL NEW 1" REGULATORS | [5 empty] | 2234.49 | 1461.8601 | 772.6299 |  |  |  | 44841 | REPLACED BOTH MONITOR AND CONTROL REGULATORS AND INLET AND OUTLET VALVES BL ONE 10-7-22
22026213500 | RETIRE REGULATORS | [5 empty] | 856.14 | 84.9152 | 771.2248 |  |  |  | 44841 | REPLACED BOTH MONITOR AND CONTROL REGULATORS AND INLET AND OUTLET VALVES BL ONE 10-7-22
22026213900 | INSTALL 200'-2"PMMP | [5 empty] | 35208.99 | 22574.1191 | 12634.8709 |  |  |  | 44858 | BORED IN 308' OF 020 PL ML. TESTED 90# FOR 1 HR. SOAP TESTED CONN PTS @ 39#
22026214100 | ABANDON 200'-2" PMMP | [5 empty] | 921.07 | 800.8601 | 120.2099 |  |  |  | 44855
22026214500 | JIM BEAN RTU PANEL | [5 empty] | 2091.18 | 55.5311 | 2035.6489 |  |  |  | 45019 | CCC# 15710 CCC# 15710
22026215700 | EMER-INSTALL 2' OF 2"PMMP MAIN | [5 empty] | 4910.67 | 8681.8934 | -3771.2234 |  |  |  | 44795 | REPLACED 2FT OF 020 DAMAGED MAIN.TESTED NEW MAIN FOR 20MINS AT 90LBS.TEST OK.SOAP TEST EFC'S AT OP FOR 5MINS.TEST OK. BHBNGF
22026215800 | EMER-RETIRE 2' OF 2"PMP MAIN | [5 empty] | 224.99 | 84.9152 | 140.0748 |  |  |  | 44795 | REPLACED 2FT OF 020 DAMAGED MAIN.TESTED NEW MAIN FOR 20MINS AT 90LBS.TEST OK.SOAP TEST EFC'S AT OP FOR 5MINS.TEST OK. BHBNGF
22026220400 | ABANDON 550' OF 2"PMP MAIN | [5 empty] | 184.67 | 3449.8998 | -3265.2298 |  |  |  | 44802 | ABANDONED 020 MP PL ML. PREFORMED PER ABANDONMENT PLAN SOAP TEST DEAD END C AP OP 15 MINUTES. C HERNDON/S.BARKER PURGED ABANDONED SECTION OF LINE. CAPPED THE ENDS OF ABANDONED ML.
22026221000 | INSTALL 160'-4"PMMP | [5 empty] | 36375.08 | 20578.0582 | 15797.0218 |  |  |  | 44879 | AWEBER 12/6/22 - JOB ENCOUNTERED HEAVY ROCK BORE, RESULTING IN DOUBLE TIME FROM ORIGINAL ESTIMATE. ATTEMPT TO REVISE, UNABLE DUE TO UNPAID INVOICES.
22026222700 | INSTALL 86'-2" PMMP | [5 empty] | 13511.21 | 12304.5709 | 1206.6391 |  |  |  | 44902 | THERE WAS A TYPO ON THE PRESSURE SYSTEM WHEN IT WAS CREATED. CORRECT SYSTEM NUMBER 32010047. SYSTEM NUMBER HAS BEEN CORRECTED IN DIS.
22026225400 | INSTALL APROX 180'-6" PMLP | [5 empty] | 161513.7 | 120007.3465 | 41506.3535 |  |  |  | 45159 | GURU ADDED 2'-6"PLASTIC RISER PIPE TO TD 0735002. SM 11/7/23
22026225500 | RETIRE 200' - 6" BSLP | [5 empty] | 510.72 | 117.7346 | 392.9854 |  |  |  | 45159
22026229200 | INSTALL 80'-2" PMMP | [5 empty] | 10781.29 | 11104.5291 | -323.2391 |  |  |  | 44953 | INSTALLED 160' 2'' MP-PL MAINLINE
22026230000 | ABANDON 470'-2"&3"PLP | [5 empty] | 5899.02 | 6027.5291 | -128.5091 |  |  |  | 44866 | ABANDONED 334' OF 030 PL LP ML PER ENGINEERING AND TIE IN PLAN. SOAP TEST END CAP @ OP 15 MINS NO LEAKS BHB NGF. PURGED OUT ABANDONED SECTION OF ML G OOD M. COLLINS 11/1/2022
22026230600 | EMER-INSTALL 5' OF 3"PMMP MAIN | [5 empty] | 0 | 828.6177 | -828.6177 |  |  |  | 44840
22026230700 | EMER-RETIRE 5' OF 3"PAMP MAIN | [5 empty] | 12302.62 | 4289.0582 | 8013.5618 |  |  |  | 44840
22026231200 | INSTALL 1870'-2"/4" PMMP | [5 empty] | 213474.97 | 71796.5181 | 141678.4519 |  |  |  | 45203
22026235100 | INSTALL 2160'-2"/4" PMMP | [5 empty] | 179472.03 | 82352.5181 | 97119.5119 |  |  |  | 45331
22026235300 | INST 1865'-8" & 390'-2" PMMP | [5 empty] | 1121157.31 | 895303.7297 | 225853.5803 |  |  |  | 45454
22026235400 | RETIRE 2111'- 2",4",6",8" BSMP | [5 empty] | 220 | 139.1159 | 80.8841 |  |  |  | #N/A
22026236901 | INSTALL 11300'-2" PMMP | [5 empty] | 2626590.92 | 2204167.7449 | 422423.1751 |  |  |  | 45586
22026237000 | ABDN~8924'-2",3",4" BS,CS,P LP | [5 empty] | 0 | 124.9261 | -124.9261 |  |  |  | #N/A
22026238301 | INSTALL 2505'-4" PHHP | [5 empty] | 297291.9 | 265393.3206 | 31898.5794 |  |  |  | 45299
22026238401 | INSTALL 5765'-2" PMMP | [5 empty] | 1422160.57 | 1269865.7251 | 152294.8449 |  |  |  | 45629
22026238500 | RETIRE 7260'-2"-6" BS,CS & P | [5 empty] | 0 | 139.1159 | -139.1159 |  |  |  | #N/A
22026238600 | RETIRE 116'-2"&3" CS&PMP | [5 empty] | 0 | 139.1159 | -139.1159 |  |  |  | #N/A
22026241001 | INSTALL 6375'-2"/4" PMMP ENV | [5 empty] | 797679.45 | 793212.5591 | 4466.8909 |  |  |  | 45260
22026241701 | INSTALL 1425' OF 2"PMMP MAIN | [5 empty] | 698687.73 | 729573.6534 | -30885.9234 |  |  |  | 45420
22026241800 | RETIRE 1175' OF 3"/4"BSLP MAIN | [5 empty] | 10.85 | 119.4953 | -108.6453 |  |  |  | #N/A
22026243700 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 17949.62 | 29277.8866 | -11328.2666 |  |  |  | 45033 | CC 22683 CC 22535 WELDED INLET TAP TESTED INLET 375# 5 MINS RHAYES DMARTIN 03-29-2023 CCC# 24078 NOT ON SITE. CAPITAL PAPERWORK CCC#25522 CWEMPE 4/17/23 COMPLETED PAPERWORK OFFSITE. CWEMPE 4/20/23 DID NOT ENTER STATION. CHARGED TIME FOR PAPERWORK. CWEMPE 4/24/23
22026243800 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 17170.68 | 32044.6752 | -14873.9952 |  |  |  | 45034 | CC 22535 WELDED TAPS TESTED INLET 375# OUTLET 45# MINS DMARTIN RHAYES 03-29-2023 CCC# 24067 CCC#25645 CWEMPE 4/18/23 COMPLETED PAPERWORK OFFSITE. CWEMPE 4/20/23 DID NOT ENTER STATION. CHARGED TIME FOR PAPERWORK. CWEMPE 4/24/23
22026244100 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 17388.43 | 32044.6752 | -14656.2452 |  |  |  | 45035 | CC 22622 CC 22535 WELDED TAPS TESTED INLET 375# OUTLET 90# 5 MINS RHAYES DMARTIN 03-29-2023 CCC# 24075 CALLED FOR CLEARANCE TICKET AT END OF DAY AND CCC REFUSED TO CREATE TICKET. CWEMPE 4/19/23 COMPLETED PAPERWORK OFFSITE. CWEMPE 4/20/23
22026244200 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 20934.82 | 33186.6752 | -12251.8552 |  |  |  | 45041 | CCC# 24912 WELDED ON PUNCH TEES FOR SCADA VISIBILITY PROJECT. TESTED TAPPED, AND MT COMPLETE. LOCKED AND PLUGGED VALVE. CCC# 26916
22026244300 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 21295.01 | 29761.6752 | -8466.6652 |  |  |  | 45037 | CC 22295 TAPS WELDED TESTED INLET 375# OUTLET90# 5MIN TESTED GOOD RHAYES CCC# 24050 CCC#26526 CWEMPE 4/21/23
22026245100 | EMER-INSTALL 3' OF 2"PHHP MAIN | [5 empty] | 2741.28 | 4877.0569 | -2135.7769 |  |  |  | 44902
22026245200 | EMER-RETIRE 3' OF 2"PHHP MAIN | [5 empty] | 0 | 131.2422 | -131.2422 |  |  |  | #N/A
23026249500 | INSTALL 870'-2" PMMP | [5 empty] | 52378.28 | 67614.2583 | -15235.9783 |  |  |  | 45020
23026249600 | PM- DE ILI PH 2 JIM BEAM INST | [5 empty] | 966229.4 | 593000 | 373229.4 |  |  |  | 44953
23026249700 | PM- DE ILI PH 2 JIM BEAM ABAN | [5 empty] | 234155.55 | 132000 | 102155.55 |  |  |  | 44953
23026251500 | INSTALL 70'-2" PMLP | [5 empty] | 16349.3 | 20790.0608 | -4440.7608 |  |  |  | 45051
23026252900 | PM-GREENSITE RAILROAD CROSSING | [5 empty] | 17890.94 | 1236355 | -1218464.06 |  |  |  | 44754
23026253000 | PM-GREENSITE RAILROAD ABANDON | [5 empty] | 328.14 | 0 | 328.14 |  |  |  | 44754
23026253500 | PM-GREENSITE IRONWORKS DE REPL | [5 empty] | 18995.31 | 1236355 | -1217359.69 |  |  |  | 44694
23026253600 | PM-GREENSITE IRONWORKS ABAN | [5 empty] | 6.23 | 0 | 6.23 |  |  |  | 44694
23026254300 | TAP W/MAIN 23-0262543-00 | [5 empty] | 4459.75 | 13015.0987 | -8555.3487 |  |  |  | 44965
23026255400 | GMB TO CAB CONVERSION | [5 empty] | 9499.75 | 2712.0987 | 6787.6513 |  |  |  | 45078 | REMOVED OLD GMB FACILITIES REBUILT METER SETTING INSTALLED NEW ROMET 16M ME TER AND CL838 REGS ON 15# DELIVERY BLONE 6-1-23
23026256000 | INSTALL 800'OF 2"PMMP MAIN | [5 empty] | 92657.71 | 192451.7008 | -99793.9908 |  |  |  | 45134
23026256600 | RETIRE PAPER GAUGE | [5 empty] | 468 | 138.8485 | 329.1515 |  |  |  | 44987 | CHART BOXES REMOVED. G.HALE A.PARKS 03-02-23 CHARTS REMOVED AND STORED AT LEX MOD APARKS 03-02-23
23026257100 | INSTALL 300'-2" PMMP | [5 empty] | 68581.44 | 32921.1974 | 35660.2426 |  |  |  | 45197 | MAINLINE EXTENSION FOR ALDI'S INSTALLED BY STANLEY PIPELINE. JOSH PASLEY 9/28/23
23026259600 | INSTALL ERX AND SUPER SOLAR | [5 empty] | 4884.63 | 5600.9621 | -716.3321 |  |  |  | 44992
23026259700 | RETIRE PAPER CHART | [5 empty] | 269.78 | 138.8485 | 130.9315 |  |  |  | 44992
23026260600 | GMB TO CAB CONVERSION | [5 empty] | 1404.11 | 138.8485 | 1265.2615 |  |  |  | 45020 | GATHER PARTS FOR CONVERSION, MTR, FLANGES, GASKETS ETC. REGULATOR GMB TO CAB CONVERSION GAS ON BYPASS DURING REBUIL;D NO BYPASS GAS USED INST ALLED NEW ROMET 3M ON 2#
23026266100 | INSTALL 880'-4" PHHP | [5 empty] | 70247.34 | 60596.7317 | 9650.6083 |  |  |  | 45156
23026266200 | INSTALL 1100'-4" PHHP | [5 empty] | 127648.14 | 81743.7317 | 45904.4083 |  |  |  | 45181
23026268100 | RETIRE MAIN - LEAKAGE | [5 empty] | 0 | 117.7346 | -117.7346 |  |  |  | 45028
23026268500 | PM-DE LINE ILI PH 2 BEND 260 | [5 empty] | 770197.91 | 1150001 | -379803.09 |  |  |  | 45093
23026268600 | PM-DE LINE ILI PH2 DENT 36 | [5 empty] | 1598859.3 | 1150001 | 448858.3 |  |  |  | 45080
23026269000 | EMER-INSTALL 4' OF 2"PMMP MAIN | [5 empty] | 6353.99 | 5499.7073 | 854.2827 |  |  |  | 45014
23026269100 | EMER-RETIRE 4' OF 2"PAMP MAIN | [5 empty] | 0 | 117.7346 | -117.7346 |  |  |  | 45014
23026269200 | PM-DE LINE ILI PH2 BEND 260 AB | [5 empty] | 195099.48 | 192300 | 2799.48 |  |  |  | 45100
23026269300 | PM-DE LINE ILI PH2 DENT 36 ABD | [5 empty] | 282014.56 | 192300 | 89714.56 |  |  |  | 45082
23026271000 | INSTALL 70'-2" PMMP | [5 empty] | 606.43 | 9795.9371 | -9189.5071 |  |  |  | 45026
23026271100 | ABANDON 60'-2" PMMP | [5 empty] | 4210.59 | 262.8722 | 3947.7178 |  |  |  | 45026
23026273500 | EMER-INSTALL 65' OF 2"PMIP | [5 empty] | 5983.61 | 8772.0552 | -2788.4452 |  |  |  | 45037
23026273600 | EMER-RETIRE 55' OF 2"PAIP | [5 empty] | 1024.42 | 117.7346 | 906.6854 |  |  |  | 45037
23026276700 | RETIRE STATION R-1581 | [5 empty] | 1722.38 | 541.8551 | 1180.5249 |  |  |  | #N/A | NO CCC NEEDED -RETIRED STATION - CHECKED TO SEE RETIRED STATUS AND STATUS OF INLET VALVE - BLONE - 05/02/25
23026276800 | RETIRE FENCE | [5 empty] | 0 | 139.1159 | -139.1159 |  |  |  | #N/A
23026278900 | INSTALL 150'-2" PMMP | [5 empty] | 10151.75 | 13769.2187 | -3617.4687 |  |  |  | 45135
23026279800 | INSTALL 1800'-2" PMMP | [5 empty] | 53278.51 | 72065.7028 | -18787.1928 |  |  |  | 45132
23026281200 | EMER-INSTALL 2' OF 2"PMMP MAIN | [5 empty] | 6222.18 | 5082.4374 | 1139.7426 |  |  |  | 45103
23026281300 | EMER-RETIRE 2' OF 2"PMMP MAIN | [5 empty] | 0 | 139.1159 | -139.1159 |  |  |  | 45103
23026281400 | INSTALL 1865'-2"/4" PMMP | [5 empty] | 90143.57 | 77027.7111 | 13115.8589 |  |  |  | 45231
23026282800 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 8915.85 | 5465.9794 | 3449.8706 |  |  |  | 45112
23026282900 | EMER - ABANDON 5'-2" PMMP | [5 empty] | 0 | 67.1159 | -67.1159 |  |  |  | 45112
23026283801 | INSTALL 5705'-2"/4" PMMP | [5 empty] | 388707.97 | 361218.8401 | 27489.1299 |  |  |  | 45393
23026284000 | EMER-INSTALL 2' OF 3"PMMP MAIN | [5 empty] | 14848.12 | 4281.828 | 10566.292 |  |  |  | 45133
23026284100 | EMER-RETIRE 2' OF 3"PAMP MAIN | [5 empty] | 0 | 139.1159 | -139.1159 |  |  |  | 45133
23026285800 | EMER-INSTALL 3' OF 2"PMMP MAIN | [5 empty] | 8976.29 | 6991.8345 | 1984.4555 |  |  |  | 45132
23026285900 | EMER-RETIRE 3' OF 2"PMMP MAIN | [5 empty] | 0 | 139.1159 | -139.1159 |  |  |  | 45132
23026288700 | INSTALL NEW RELIEF VALVE | [5 empty] | 814.62 | 3278.6711 | -2464.0511 |  |  |  | 45149
23026288800 | RETIRE RELIEF VALVE | [5 empty] | 0 | 119.4953 | -119.4953 |  |  |  | 45149
23026289700 | INSTALL 70' OF 3"PMLP MAIN | [5 empty] | 43735.5 | 32180.0533 | 11555.4467 |  |  |  | 45356
23026289800 | RETIRE 271' OF 2"/3"BSLP MAIN | [5 empty] | 9.9 | 119.4953 | -109.5953 |  |  |  | #N/A
23026291400 | PAPER JOB - MP RETIREMENT | [5 empty] | 0 | 119.4953 | -119.4953 |  |  |  | 45104
23026292201 | INSTALL 360'-4" PMMP | [5 empty] | 171750.99 | 171123.5748 | 627.4152 |  |  |  | 45404
23026294600 | ABANDON ~790'-2" PMMP | [5 empty] | 392.35 | 3905.6711 | -3513.3211 |  |  |  | 45203
23026296400 | INSTALL 110' OF 2"PMMP MAIN | [5 empty] | 58459.83 | 46114.2728 | 12345.5572 |  |  |  | 45281 | CAPITAL JOB COMPLETE BY STANLEY PIPELINE AND CLEARED ASSOCIATED DPI'S. JOSH PASLEY 12/21/23
23026296500 | RETIRE 88' OF 2"CSMP MAIN | [5 empty] | 0 | 122.9261 | -122.9261 |  |  |  | 45281 | CAPITAL JOB COMPLETED BY STANLEY PIPELINE. CLEARED ASSOCIATED DPI'S. JOSH PASLEY 12/21/23
23026298800 | INSTALL 900'-2" PMMP MAIN | [5 empty] | 154240.87 | 120091.9279 | 34148.9421 |  |  |  | 45385
23026301200 | INSTALL 60' OF 6"PMMP MAIN | [5 empty] | 43879.22 | 42818.4272 | 1060.7928 |  |  |  | 45722
23026301300 | RETIRE 54' OF 6"PMP MAIN | [5 empty] | 0 | 156.7483 | -156.7483 |  |  |  | #N/A
23026301600 | INSTAL NEW MODEM | [5 empty] | 652.23 | 2605.8688 | -1953.6388 |  |  |  | 45236
23026301700 | RETIRE MODEM | [5 empty] | 365.2 | 122.9261 | 242.2739 |  |  |  | 45236
23026307400 | EMER-INSTALL 3' OF 2"PMMP | [5 empty] | 1388.66 | 2930.7643 | -1542.1043 |  |  |  | 45265
23026307500 | EMER-RETIRE 3' OF 2"PMP MAIN | [5 empty] | 0 | 123.4493 | -123.4493 |  |  |  | 45265
23026308601 | INSTALL 675'-2" PMMP | [5 empty] | 91036.22 | 75877.1307 | 15159.0893 |  |  |  | 45453 | JOB COMPLETED ON 5-14-24, ENGINEERING COMPLETED JOB ORDER REVISION ON 6-4-2 4 - RTINCHE 6-10-24
24026309500 | INSTALL 215'-2" PMMP | [5 empty] | 19486.43 | 20568.4833 | -1082.0533 |  |  |  | 45434
24026310000 | EMER-INSTALL 4' OF 2"PMIP MAIN | [5 empty] | 11757.28 | 6172.4499 | 5584.8301 |  |  |  | 45295
24026310100 | EMER-RETIRE 4' OF 2"PAIP MAIN | [5 empty] | 0 | 123.4493 | -123.4493 |  |  |  | #N/A
24026311500 | EMER-RETIRE 350' OF 4"PMP MAIN | [5 empty] | 1832.02 | 3055.4946 | -1223.4746 |  |  |  | #N/A
24026312100 | REMOVE SATELLITE UNIT | [5 empty] | 1333.97 | 4076.4833 | -2742.5133 |  |  |  | #N/A | CCC# 58738
24026312200 | INSTALL 230'-2" PMMP | [5 empty] | 37251.74 | 25802.5654 | 11449.1746 |  |  |  | 45450
24026312301 | INSTALL NEW GMB SETTING | [5 empty] | 230544.69 | 234758.3952 | -4213.7052 |  |  |  | #N/A
24026312400 | INSTALL 50'-4" PHHP-SERV | [5 empty] | 23459.51 | 13239.0974 | 10220.4126 |  |  |  | #N/A
24026313000 | INSTALL 1570'-2" PMMP | [5 empty] | 502657.55 | 526295.3733 | -23637.8233 |  |  |  | 45636
24026313100 | RETIRE~1346 OF BSLP/PLP MAIN | [5 empty] | 0 | 139.7787 | -139.7787 |  |  |  | #N/A
24026314800 | INSTALL MINI AT W/EC350 | [5 empty] | 5915.68 | 3917.1928 | 1998.4872 |  |  |  | #N/A | INSTALLED NEW EC350 WITH HONEYWELL MODEM
24026314900 | RETIRE ELECTRONICS | [5 empty] | 1358.47 | 160.3697 | 1198.1003 |  |  |  | #N/A | RETIRED OLD MINI AT
24026316500 | EMER - INSTALL 15'-2" PMMP | [5 empty] | 0 | 4538.5784 | -4538.5784 |  |  |  | 45329
24026316600 | EMER - ABANDON ~15'-2" PMMP | [5 empty] | 7172.61 | 160.3697 | 7012.2403 |  |  |  | #N/A
24026317300 | INSTALL 270'-2" PMMP | [5 empty] | 32804.09 | 44548.0974 | -11744.0074 |  |  |  | 45390
24026322900 | INSTALL MIWI W/ SOLAR | [5 empty] | 16866.28 | 22593.1928 | -5726.9128 |  |  |  | #N/A | CCC# 96304 CCC# 96304 X-RAY WELD AND DROP OFF PAPERWORK. G.HALE 11-18-2024
24026323000 | RETIRE FACILITIES | [5 empty] | 890.43 | 160.3697 | 730.0603 |  |  |  | #N/A | CCC# 96304
24026331100 | EMER - INSTALL ~5'-2" PMMP | [5 empty] | 523.81 | 3498.146 | -2974.336 |  |  |  | 45351
24026331200 | EMER-ABANDON ~5'-2" PMMP | [5 empty] | 0 | 118.4933 | -118.4933 |  |  |  | #N/A
24026331601 | INSTALL 475' OF 2"PMMP MAIN | [5 empty] | 142820.44 | 110575.0083 | 32245.4317 |  |  |  | 45495
24026331700 | REITRE 435' OF 2"BSLP MAIN | [5 empty] | 489.56 | 121.4465 | 368.1135 |  |  |  | #N/A
24026332800 | EMER - INSTALL 5'-4" PMIP | [5 empty] | 8388.17 | 3664.146 | 4724.024 |  |  |  | 45367
24026332900 | EMER - ABANDON 5'-4" PMIP | [5 empty] | 19.55 | 118.4933 | -98.9433 |  |  |  | #N/A
24026338200 | EMER - INSTALL 5'-3" PMMP | [5 empty] | 12009.27 | 3698.1293 | 8311.1407 |  |  |  | 45380
24026338300 | EMER - ABANDON 5'-3" PMMP | [5 empty] | 0 | 118.4933 | -118.4933 |  |  |  | #N/A
24026344900 | ABANDON ~30'-2" PMP | [5 empty] | 0 | 139.7787 | -139.7787 |  |  |  | #N/A
24026346100 | EMER - INSTALL 2'-2" PMMP | [5 empty] | 0 | 9472.4549 | -9472.4549 |  |  |  | 45448
24026346200 | EMER - ABANDON 2'-2" PMP | [5 empty] | 0 | 139.7787 | -139.7787 |  |  |  | #N/A
24026346900 | INSTALL 2"BYPASS REGULATOR | [5 empty] | 30803.34 | 18438.8164 | 12364.5236 |  |  |  | #N/A | INSTALL BYPASS REGS, CMCHOLAN 8-28-24 0815
24026347000 | RETIRE 4" BYASS REGULATORS | [5 empty] | 1210.3 | 139.7787 | 1070.5213 |  |  |  | #N/A
24026350100 | INSTALL RMU UNIT AT RECTIFER | [5 empty] | 6.49 | 5471.8027 | -5465.3127 |  |  |  | #N/A | RM5 I/04 DOME:510102550 MODEM:501004142 INSTALLED (TE866717) AT GLENNS CREEK REC / 07-10-24 JMM
24026350200 | RETIRE RMU UNIT AT RECTIFIER | [5 empty] | 0 | 139.7787 | -139.7787 |  |  |  | #N/A | OLD RMU RM4014 TE 673502 RETIRED / INSTALLED NEW RMU RM5 TE 866717 / JMM 673502 RETIRED VIA UFA IN ERROR. PU NUMBER RETIRED VIA 999
24026350300 | INSTALL RMU AT RECTIFIER | [5 empty] | 5998.89 | 6097.8027 | -98.9127 |  |  |  | #N/A | RM5 I/04 DOME:510102969 MODEM:501003622 INSTALLED (TE867224) AT AUSTIN REC 08-07-24 JMM
24026350400 | RETIRE RMU UNIT | [5 empty] | 0 | 139.7787 | -139.7787 |  |  |  | #N/A | OLD RMU RM4010 TE 655082 RETIRED / INSTALLED NEW RMU RM5 TE 867224 / JMM
24026354500 | RETIRE 4" BS-MP SERVICE LINE | [5 empty] | 0 | 127.2637 | -127.2637 |  |  |  | #N/A
24026354600 | INSTALL 790'-4" PMMP S/L | [5 empty] | 73956.17 | 108203.2906 | -34247.1206 |  |  |  | #N/A
24026355200 | INSTALL 150'-4" PMLP | [5 empty] | 57369.63 | 34225.265 | 23144.365 |  |  |  | 45644
24026355300 | INSTALL 250'-2" PMMP | [5 empty] | 24464.47 | 25692.6504 | -1228.1804 |  |  |  | 45553
24026357700 | EMER-INSTALL 2' OF 3"PMMP MAIN | [5 empty] | 13806.96 | 15212.4136 | -1405.4536 |  |  |  | 45527
24026357800 | EMER-RETIRE 3" POLY VLV C-145 | [5 empty] | 0 | 127.2637 | -127.2637 |  |  |  | #N/A
24026360200 | EMER-INSTALL 3' OF 2"PMMP MAIN | [5 empty] | 12791.75 | 12190.8831 | 600.8669 |  |  |  | 45539 | PAPERWORK ISSUES CFD
24026360300 | EMER-RETIRE 3' OF 2"PAMP MAIN | [5 empty] | 0 | 127.2637 | -127.2637 |  |  |  | #N/A | PAPERWORK ISSUES CFD
24026362000 | EMER-INSTALL 3' OF 3"PMMP MAIN | [5 empty] | 18283.02 | 5267.5068 | 13015.5132 |  |  |  | 45552
24026362100 | EMER-RETIRE 2' OF 3"PMP/VALVE | [5 empty] | 12763.63 | 127.2637 | 12636.3663 |  |  |  | #N/A
24026363800 | INSTALL EC-350 UNIT | [5 empty] | 5892.2 | 4869.446 | 1022.754 |  |  |  | #N/A
24026363900 | RETIRE EFC UNIT | [5 empty] | 0 | 135.7529 | -135.7529 |  |  |  | #N/A
24026372000 | INSTALLING 500'-2" PMMP | [5 empty] | 47889.55 | 43811.0834 | 4078.4666 |  |  |  | 45709
24026372200 | PM- SEWELL RPL OUTLET SYS ABAN | [5 empty] | 0 | 0 | 0 |  |  |  | #N/A
24026372300 | PM- SEWELL REPL OUTLET SYS# | [5 empty] | 0 | 0 | 0 |  |  |  | #N/A
25026377600 | EMER-INSTALL 4' OF 2"PMMP MAIN | [5 empty] | 8999.48 | 11901.0834 | -2901.6034 |  |  |  | 45659
25026377700 | EMER-RETIRE 4' OF 2"PMP MAIN | [5 empty] | 0 | 111.0024 | -111.0024 |  |  |  | #N/A
25026381100 | INSTALL SCADA VISIBILITY | [5 empty] | 8624.74 | 10377.5378 | -1752.7978 |  |  |  | #N/A | CCC 114389 WELD TAPS ON PRESSURE TEST 375# INLET CCC 124465 INSTALLED ER350 AND SUPER SOLAR KIT. COMMISSIONED WITH GC. 6/10/25 DSASH
25026392000 | INSTALL 140'-2" PMMP | [5 empty] | 21515.47 | 12869.0756 | 8646.3944 |  |  |  | 45789
25026403300 | INSTALL MONITOR REGULATOR | [5 empty] | 1909.6 | 7027.7205 | -5118.1205 |  |  |  | #N/A
25026403400 | RETIRE MONITORING REG | [5 empty] | 1316.2 | 79.8251 | 1236.3749 |  |  |  | #N/A
17026706600 | CONVERT FROM GMB TO CAB ACCT | [5 empty] | 14520.06 | 1078.4716 | 13441.5884 |  |  |  | 45124 | CCC# 36905 CCC#36905
17026724700 | RETIRE 350' - 3" PMLP | [5 empty] | 6306.19 | 2349.008 | 3957.182 |  |  |  | #N/A | PREP FOR JOB/GATHERED MATERIAL WILL DO PAPERWORK TOMORROW ABANDONED MAIN DOWNSTREAM OF METER AT 102 BLUEBERRY LN PER FOL - SOAP TEST DEAD END CAP FOR 5 MIN AT OP OK - BHB OK - 10.5 IWC VERIFIED - NRICHIE 2-20-24. IP OFF SITE.
18026766400 | I&C - INSTALL SCADA EQUIPMENT | [5 empty] | 143824.82 | 183526.0448 | -39701.2248 |  |  |  | 44833 | JMULLINS COMPLETE PAPERWORK TWALKER/KY 01-24-23: JOB UNDER RUN DUE TO MATERIAL COST WAS $33,000 LESS THAN PLANNED, NO SEGA CHARGED TO JOB ORDER PROJECT WAS PLANNED FOR $23,000
18026789001 | INSTALL 6900' - 4" PMMP | [5 empty] | 789465.56 | 783479.7367 | 5985.8233 |  |  |  | 44232
18026789100 | RETIRE 600' - 3" PMMP | [5 empty] | 70.37 | 218.671 | -148.301 |  |  |  | 44231
18026795501 | INSTALL 14,600'-2,4,6,8" PMMP | [5 empty] | 3426043.78 | 3061100.231 | 364943.549 |  |  |  | 45611
18026795600 | RETIRE 714' - 6" BSMP | [5 empty] | 0 | 124.7348 | -124.7348 |  |  |  | #N/A
18026823200 | INST. FN 164 EXTRA LP OPP | [5 empty] | 53697.68 | 24062.1646 | 29635.5154 |  |  |  | 44384 | TICKET CALLED IN BY JPASLEY NOT ON SITE ROUNDED UP PARTS. GCCC# 19363 CCC# 19363 CCC# 20802 NOT ON SITE CCC# 21442 P2P WITH GAS CONTROL REGULATOR AND ER350 INSTALLED BY WADE SHIMFESSEL ON 4/27/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/21 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026823300 | RET. FN 164 FOR EXTRA LP OPP | [5 empty] | 228.05 | 53.6219 | 174.4281 |  |  |  | 44384 | REGULATOR REPLACED BY WADE SHIMFESSEL ON 4/27/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/21 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026861100 | INSTALL HEATER | [5 empty] | 2372.11 | 3045.0298 | -672.9198 |  |  |  | #N/A | INSTALLED CAT HEATER
19026913900 | INSTALL 20' - 4" CSHP | [5 empty] | 82645.85 | 45390.8034 | 37255.0466 |  |  |  | 44278 | COULD NOT REVISE DUE TO UNFULLFILLED PURCHASE ORDERS, NEEDED REVISION DUE TO EXTRA MATERIAL, INCREASE CONTRACT LABOR REQUIRED, EXTRA COMPANY LABOR, EXTRA TRUCK COSTS, AND EXTRA SEGA TTOY 3/18/2021
19026914000 | RETIRE 10' - 3" CSHP | [5 empty] | 695.55 | 114.5339 | 581.0161 |  |  |  | 44278
20026918201 | INSTALL ELECTRONICS | [5 empty] | 199238.05 | 114999.9064 | 84238.1436 |  |  |  | 44831 | CCC#17216 CCC# 19029 STATION RTU UP GRADE JPASLEY 9-27-22
20026930000 | UPGRADE ELECTRONICS | [5 empty] | 4491.87 | 3038 | 1453.87 |  |  |  | 44841 | INSTALLED NED EC350 JPASLEY 10-7-22
20026930100 | UPGRADE ELECTRONICS | [5 empty] | 3919.3 | 3038 | 881.3 |  |  |  | 44210 | NO TICKET NEEDED FOR THE WORK PERFORMED. 1/14/21 GCCC TICKET NOT REQUIRED PE ENGINEER CINDY SPARKS GAVE VERBAL APPROVAL ON SITE TO PROCEED WITH JOB. EFC REPLACEMENT ONLY GAS FLOW NOT INTERUPTED JOB DELAYED DUE TO COVID 19 AND COMPLIANCE WORK AND BY NOW HAVING TO BE REVIEWED BY PE ENGINEER
20026930300 | UPGRADE ELECTRONICS | [5 empty] | 9306.71 | 3038 | 6268.71 |  |  |  | 44624 | MET MOOSE ONSITE TO INSTALL SOLAR PANEL, CELL BOOSTER,BATTERY/BOX INSTALLED NEW EC350 WSHIMFESSEL JMULLINS COMPLETED PAPER WORK 06-13-2022
20026930400 | UPGRADE ELECTRONICS | [5 empty] | 6567.19 | 3038 | 3529.19 |  |  |  | 44286 | CCC TICKET NOT REQUIRED 3/29/21 CFARIS REPLACED EFC AND WORKED TP ORDER JOB ON HOLD FOR 2020 DUE TO COVID 19 GCCC TICKET NOT REQUIRED ON 3/31/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK ALSO THIS IS NON-SCADA MONITORED GMB CFARIS
20026937200 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 |  |  |  | 44841 | RETIRE OLD MIN-AT INSTALLED NED EC350 JPASLEY 10-7-22
20026937300 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 |  |  |  | 44210 | GCCC TICKET NOT REQUIRED VERBAL APPROVAL GIVEN ONSITE BY PE ENGINEER CINDY SPARKS TO WORK JOB GAS FLOW NOT INTERUPTED TO WORK JOB THIS WAS EFC REPLACEMENT ONLY JOB DELAYED DUE TO COVID 19 COMPLIANCE WORK AND WAITING REVIEW BY PE ENGINEER
20026937500 | RETIRE ELECTRONICS | [5 empty] | 129.79 | 73.3494 | 56.4406 |  |  |  | 44624 | RETIRED MINI-AT INSTALLED NEW EC350 JMULLINS CO PAPER WORK 06132022
20026937600 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 |  |  |  | 44286 | REPLACED EFC JOB ON HOLD IN 2020 DUE TO COVID 19 GCCC TICKET NOT REQUIRED NOT AT STATION OFF SITE COMPLETING PAPERWORK ALSO THIS IS A NON-SCADA MONITORED GMB 3/31/21 CFARIS
20026940900 | INSTALL I&C EQUIPMENT | [5 empty] | 12849.77 | 18740.1071 | -5890.3371 |  |  |  | 44910 | CCC TICKET# 55594 CCC TICKET# 55594 PAPER WORK GATHER INFO 12-15-22 JBRADFORD
20026941000 | RETIRE GAUGE | [5 empty] | 1582.1 | 91.4991 | 1490.6009 |  |  |  | 44910 | CCC TICKET# 55594 CCC# 55594 ERX ONLINE P2P W/GAS CONTROL OK REMOVED CHART BOX AND FILED LAST CHART ON CABINET TICKET# 11209 GATHERED INFORMATION FOR CLOSEOUT PAPERWORK 12-15-22 JBRADFORD
20026947301 | INSTALL 3,950' - 2" PMMP | [5 empty] | 1895184.87 | 1562557.4499 | 332627.4201 |  |  |  | 44511 | TTOY/KY 3/2/22: OVERRUN EXPLANATION: FLAGGER OT ESTIMATED FOR 543 HOURS BUT ACTUAL WAS 1033 HOURS, CONTRACTOR CREWS HOURLY TIME WAS OVER ESTIMATE AT 167 EXTRA HOURS, SEGA HAD EXTRA $60,000 IN COST, COMPANY LABOR HAD ADDITIONAL $27,000 COST OVER ESTIMATE
20026947400 | RETIRE 5,000' - 4" CI/BS LP | [5 empty] | 71.35 | 103.8156 | -32.4656 |  |  |  | 44512
20026949900 | INSTALL 1100' - 2" PMMP | [5 empty] | 207663.91 | 207915.8181 | -251.9081 |  |  |  | 44392
20026950000 | RETIRE 1430' OF 2"/3" BS-MP | [5 empty] | 2502.68 | 81.9085 | 2420.7715 |  |  |  | 44392
20026955400 | RETIRE STATION | [5 empty] | 2363.47 | 1910.2958 | 453.1742 |  |  |  | 44231 | 8561 JOB WAS ON HOLD UNTIL AFTER BEGINNING OF THE YEAR
20026964102 | INSTALL 4000' OF 12"CSHP MAIN | [5 empty] | 1045900.23 | 909258.0027 | 136642.2273 |  |  |  | 44327 | TWALKER/KY 09-21-21: JOB OVER RUN DUE TO ADDITIONAL ENVIRONMENTAL AND SITE CLEANUP ON SITE DUE TO RAIN DURING CONSTRUCTION, THIS ADDED EXTRA $40,000 TO CONTRACT COST, PROJECT REQUIRED 2 COMPANY COORDINATORS BUT WAS PLANNED FOR 1 ADDED $35,000 IN LABOR COST AND SEGA INCREASED BY $33,000.
20026964200 | RETIRE 1200' OF 12"BSHP MAIN | [5 empty] | 3603.11 | 84.1799 | 3518.9301 |  |  |  | 44327
20026969900 | INSTALL FENCE & BOLLARDS | [5 empty] | 9603.34 | 36430.1489 | -26826.8089 |  |  |  | 44884 | INSTALLED NEW FENCE 11-19-22 JMULLINS
20026970000 | RETIRE BUILDING | [5 empty] | 26427.16 | 88.8156 | 26338.3444 |  |  |  | 44884 | CCC# 37831 CCC# 33819 CCC# 38966 TO BE COMP BY CFARRIS BUILDING REMOVED JMULLINS
20026976900 | INSTALL RTU & INSTRUMENTATION | [5 empty] | 362179.42 | 302143.1164 | 60036.3036 |  |  |  | 45160 | CCC# 2490 CCC# 2490 CCC# 2490 CCC# 5078 6417 CCC# 7314 CCC# 7314 CCC# 7314 CCC# 6417 CCC# 6417 CCC# 6417 CCC# 6417 CCC# 6417
20026977000 | RETIRE RTU & INSTRUMENTATION | [5 empty] | 2598.25 | 60.3089 | 2537.9411 |  |  |  | 45160
20026979600 | INSTALL 20' - 2"/6" PMMP | [5 empty] | 106288.64 | 65238.0736 | 41050.5664 |  |  |  | 44274 | ATTEMPTED TO REVISE DUE TO EXTRA HOURLY COST, COULD NOT REVISE DUE TO UNFULLFILLED PURCHASE ORDER TTOY 3/18/2021 OVERRUN EXPLANATION: JO WAS ORIGINALLY PLANNED ON 2018 FISHEL CONTRACT, JO WAS EXECUTED USING 2020 STANLEY PIPELINE CONTRACT, EXTRA VAC EXCA, EXTRA WLD AND RIG, EXTRA TOP SOIL REQUIRED, EXTRA HOURLY CREW REQUIRED, ESTIMATED HOURLY TIME WAS 56 HOURS, ACTUAL HOURLY TIME WAS 398 HOURS, ESTIMATED CONTRACT COST WAS $35,000, ACTUAL CONTRACT COST WAS $51,000
20026979700 | RETIRE 15' - 2" BSLP | [5 empty] | 71.35 | 92.1481 | -20.7981 |  |  |  | 44274
20026980401 | INSTALL 13,025'-PMMP/CSHP | [5 empty] | 2259933.17 | 1836238.4697 | 423694.7003 |  |  |  | 44833 | OVERRUN EXPLANATION: PROJECT INCLUDED ADDITIONAL PAVING THAT WAS UNFORSEEN DUE TO CITY REQUIREMENTS, SEGA HAD AN INCREASE OF OVER $100,000 TTOY 3/2/2023
20026980500 | RETIRE 12,520' - LP MAIN | [5 empty] | 809.88 | 52.2976 | 757.5824 |  |  |  | 44833
20026980601 | INSTALL 16,200'-2"/4" PMMP | [5 empty] | 4720247.08 | 4665902.1359 | 54344.9441 |  |  |  | 44833
20026980700 | RETIRE MAIN - LEAKAGE | [5 empty] | 2546.03 | 103.8156 | 2442.2144 |  |  |  | 44833
20026981601 | INSTALL 9,950' OF 2"/4"/6"PMMP | [5 empty] | 3477462.23 | 3261487.9737 | 215974.2563 |  |  |  | 44707
20026981700 | RETIRE 15,000' - LP MAIN | [5 empty] | 0 | 82.4486 | -82.4486 |  |  |  | 44707
20026981800 | RETIRE 18,000 - MP MAIN | [5 empty] | 0 | 82.4486 | -82.4486 |  |  |  | 44707
20026990100 | INSTALL 6" SS | [5 empty] | 245.63 | 1607.8146 | -1362.1846 |  |  |  | 44274
20026992600 | RETIRE MP MAIN | [5 empty] | 0 | 103.8156 | -103.8156 |  |  |  | 44845
21026101900 | RETIRE 6"MP SERVICE LINE | [5 empty] | 9737.82 | 9764.3857 | -26.5657 |  |  |  | 44726 | INSTALLED BOLTED DEAD END CAP AT END OF NC 216695 VALVE. JOSH PASLEY 6/14/22
21026103400 | INSTALL 2,700' - 2"/4" PMMP | [5 empty] | 185537.75 | 115766.1902 | 69771.5598 |  |  |  | 44673 | TTOY-9/20/22: LEVEL 2 VARIANCE OVERRUN EXPLANATION IN WMSDOCS
21026104700 | REMOVE OBSOLETE ELECTRONICS | [5 empty] | 236.27 | 135.8546 | 100.4154 |  |  |  | 44831 | INSTALLED NEW RTU BUILDING AND TRANSMITTERS JPASLEY 9-27-2022
21026107000 | INSTALL 250' - 2" PMMP | [5 empty] | 72807.39 | 25983.7669 | 46823.6231 |  |  |  | 44673 | OVERRUN EXPLANATION: PROJECT WAS PLANNED FOR OPEN CUT, NEW MAIN WAS INSTALL ED BY HEAVY ROCK BORE, ADDITIONAL LAND SERVICES WAS REQUIRED FOR EASMENT, BORE CREW HOURLY WAS MORE THAN ESTIMATED 3 MAN CREW
21026108400 | EMER - INSTALL 350' - 4" PMMP | [5 empty] | 86916.93 | 44073.8715 | 42843.0585 |  |  |  | 44271 | OVERRUN EXPLANATION: HOURLY TIME EXTIMATED AT 48 HOURS, ACTUAL TIME WAS 97 HOURS, SEGA WAS DOUBLED, CONTRACT WAS ESTIMATED FOR $29,000, ACTUAL WAS $68,000, PROJECT WAS ESTIMATED TO DIRECTIONAL BORE 150', ACTUAL INSTALL WAS OPEN CUT 345', PROJECT REQUIRED EXTRA PAVING DUE TO OPEN CUT, PROJECT REQUIRED EXTRA PROCESSED AND STONE DUST DUE TO OPEN CUT, EXTRA VACUUM EXCAV ATING WAS REQUIRED, ESTIMATED FOR 4 MAN CREW CONTRACT, ACTUAL USED 3 MAN, 4 MAN, AND 5 MAN CREWS
21026108500 | EMER - RETIRE 350' - 4" PMP | [5 empty] | 4479.43 | 85.3307 | 4394.0993 |  |  |  | 44271
21026110900 | INSTALL REPLACEMENT FENCE | [5 empty] | 4971.16 | 44982.9906 | -40011.8306 |  |  |  | 44386 | CCC# 30433 MONITORED FENCE INSTALLATION CCC# 30433 CCC# 30596 CC# 30596 MONTOR STATION CCC# 30956 NEW FENCE INSTALLED WSHIMFESSEL 07-09-2021 UNDERRUN EXPLANATION: COST WAS SIGNIFICANTLY LESS THAT WHAT THE CONTRACTOR HAD ESTIMATED OVER THE PHONE.
21026111300 | RETIRE R-1654 | [5 empty] | 0 | 3585.1779 | -3585.1779 |  |  |  | 44691 | ENTIRE STATION RETIRED INCLUDING INLET AND OUTLET PIPING WSHIMFESSEL 5/10/2 022, RWILLIAMS COMPLETED JOB AND PAPERWORK
21026111400 | RETIRE R-1653-B LP | [5 empty] | 0 | 3585.1779 | -3585.1779 |  |  |  | 44699 | RETIRED LP RUN FROM R-1653 BLIND FLANGED INLET VALVE AND BYPASS VALVE WSHIM FESSEL, RWILLIAMS COMPLETED JOB AND PAPERWORK
21026112900 | INSTALL 150' - 2" PMMP | [5 empty] | 14483.58 | 15892.286 | -1408.706 |  |  |  | 44468
21026117400 | INSTALL 190' - 4" PMMP SL | [5 empty] | 40096.06 | 22441.9346 | 17654.1254 |  |  |  | #N/A | INSTALLED 243'OF 4"PMP FOR SL TO FEED PSID 501307207-CAPPED AND BURRIED END OF SL FOR FUTURE TIE IN/INSTALLATION OF RISER AND SETTING ONCE FURTHER SITE CONSTRUCTION IS COMPLETED,PER CG ENGINEER J TOY AND CONSTRUCTION SITE GC- LINE MARKER WITH WIRE AT TAP,WIRE IN VALVE BOX,AND MARKER BALLS AT ALL CHANGES OF DIRECTIONAND END OF SL INSTALLED FOR LOCATABILITY
21026117500 | INSTALL GMB SETTING | [5 empty] | 77589.89 | 58469.7613 | 19120.1287 |  |  |  | 44684
21026119200 | PM- LAKE CARNICO REPLACEMENT | [5 empty] | 3041365.07 | 3161436 | -120070.93 |  |  |  | 44847
21026119300 | PM- LAKE CARNICO ABANDONMENT | [5 empty] | 739279.78 | 62500 | 676779.78 |  |  |  | 44847
21026120000 | PM-PARIS CYNTHIANA REPLACEMENT | [5 empty] | 3020752.24 | 1087500 | 1933252.24 |  |  |  | 44826
21026120100 | PM-PARIS CYNTHIANA ABANDONMENT | [5 empty] | 325920.13 | 62500 | 263420.13 |  |  |  | 44826
21026120900 | INSTALL 5' - 3" PMLP | [5 empty] | 1085.98 | 1134.2677 | -48.2877 |  |  |  | 44312
21026121000 | RETIRE 5' - 3" PMLP | [5 empty] | 0 | 58.9085 | -58.9085 |  |  |  | 44312
21026121100 | INSTALL 5' - 4" PMMP | [5 empty] | 2417.89 | 2822.803 | -404.913 |  |  |  | 44314
21026121200 | RETIRE 5' - 4" PMLP | [5 empty] | 0 | 58.9085 | -58.9085 |  |  |  | 44314
21026123100 | INSTALL 175'-4" PMMP | [5 empty] | 53913.76 | 39889.572 | 14024.188 |  |  |  | 44384
21026123200 | RETIRE 200'-4" BSMP | [5 empty] | 0 | 77.7619 | -77.7619 |  |  |  | 44384
21026123300 | INSTALL 125'-2" PMMP | [5 empty] | 36910.92 | 28847.4767 | 8063.4433 |  |  |  | 44397
21026123400 | RETIRE 160'-4" PMMP | [5 empty] | 0 | 77.7619 | -77.7619 |  |  |  | 44397
21026125100 | RETIRE 175' - 3" LP | [5 empty] | 0 | 88.1542 | -88.1542 |  |  |  | 44385
21026125200 | INSTALL 3" SS | [5 empty] | 5010.94 | 20373.572 | -15362.632 |  |  |  | 44385
21026128200 | INSTALL 1,300 OF 2"/4"PMMP | [5 empty] | 56524.7 | 51810.9858 | 4713.7142 |  |  |  | 44519
21026135300 | ABANDON 120'-4" PL SL | [5 empty] | 0 | 82.634 | -82.634 |  |  |  | 44413
21026135400 | INSTALL 100'-4" PL SL | [5 empty] | 12266.69 | 10216.5972 | 2050.0928 |  |  |  | 44414
21026135900 | INSTALL 140'-2" PMMP | [5 empty] | 8332.52 | 14039.3957 | -5706.8757 |  |  |  | 44532
21026136700 | INSTALL 1,750'-2" PMMP | [5 empty] | 47459.5 | 49760.6579 | -2301.1579 |  |  |  | 44523
21026137400 | RETIRE 120'-1" PMP - D304537 | [5 empty] | 399.97 | 3638.7915 | -3238.8215 |  |  |  | 44429
21026137900 | INSTALL OUTLET VLV R-1643 | [5 empty] | 80161.67 | 110321.1916 | -30159.5216 |  |  |  | 44812 | CCC# 80227 MONITOR WHILE BACKFILLING INSTALLED ALL NEW STATION VALVES JPASLEY 9-8-22 UNDERRUN EXPLANATION: PROJECT INCLUDED $27,000 OF CONTINGENCY AND HAD AN UNDERRUN OF 30,492 TTOY 3/2/23
21026138000 | RETIRE OUTLET VLV R-1643 | [5 empty] | 0 | 955.7874 | -955.7874 |  |  |  | 44812 | RETIRED ALL STATION VALVES AND INSTALLED NEW VALVES JPASLEY 9-8-22
21026138400 | EMER-INSTALL 2' OF 1"PMMP MAIN | [5 empty] | 227.74 | 3122.8539 | -2895.1139 |  |  |  | 44434
21026138500 | EMER-RETIRE 2'-1"PAMP MAIN | [5 empty] | 0 | 82.634 | -82.634 |  |  |  | 44434
21026140000 | RETIRE 489'-4" PMP | [5 empty] | 20306.35 | 13697.8754 | 6608.4746 |  |  |  | 44601
21026140501 | INSTALL 1,985'-6" CSHP | [5 empty] | 143065.13 | 116515.0569 | 26550.0731 |  |  |  | 45065
21026140600 | RETIRE 2,598'- 6" BSHP | [5 empty] | 182.4 | 61.5191 | 120.8809 |  |  |  | 45065
21026140700 | RETIRE 2,200' - CSMP | [5 empty] | 0 | 61.2976 | -61.2976 |  |  |  | 44845
21026142000 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 11087.26 | 7513.9749 | 3573.2851 |  |  |  | 44454
21026142100 | EMER - RETIRE 5'-3" PMMP | [5 empty] | 0 | 69.8875 | -69.8875 |  |  |  | 44454
21026142300 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 11040.25 | 3984.9999 | 7055.2501 |  |  |  | 44455
21026142400 | EMER - RETIRE 5'-2" PMP | [5 empty] | 133.69 | 69.8875 | 63.8025 |  |  |  | 44455
21026143200 | EMER - INSTALL 450'- 4" CSHP | [5 empty] | 257776.24 | 196595.4538 | 61180.7862 |  |  |  | 44544 | PROJECT WAS CODED AMRCB BECAUSE THE PIPE UNDER THE BRIDGE HAD NO COATING. OVERRUN EXPLANATION: MAIN REASON FOR PROJECT COST OVERRUN IS DUE TO 2,000 UNITS OF ASPHALT PAVING WHEN ONLY 1,000 UNITS WERE PLANNED. THE STATE REQUIRED EXTRA PAVING DUE TO EXISTING ROAD CONDITION.THE PROJECT WAS PLANNED FOR 1 CONSTRUCTION COORDINATORBUT ENDED UP HAVING MULTIPLE AND DOUBLED THE COMPANY LABOR CHARGES. FLAGGING FOR THEPROJECT INCLUDED A 30% INCREASECOMPARED TO THE PLANNED AMOUNT. THE PROJECT INCLUDED AN ADDITIONAL 49 UNITS OF STEELMAINLINE INSTALLATION AND ROCK AND LEDGE EXCAVATIONWAS REQUIRED BUT NOT PLANNED. TTOY 12/2/22
21026143300 | EMER - RETIRE 100'-3" CSHP | [5 empty] | 3034.48 | 61.5191 | 2972.9609 |  |  |  | 44544
21026147700 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 2531.33 | 2686.3426 | -155.0126 |  |  |  | 44489 | REPLACED 3' SECTION OF 2" PMP AFTER DIG IN. PRESSURE TESTED NEW MAIN AT 90 PSIG FOR 1 HOUR, SOAP TESTED FINAL TIE IN AT OP. OK 34 PSIG VERIFIED NRICHIE 10-20-21
21026147800 | EMER - RETIRE 5'-2" PMP | [5 empty] | 0 | 61.5191 | -61.5191 |  |  |  | 44489
21026149800 | RETIRE R-1615 | [5 empty] | 552.62 | 16113.7857 | -15561.1657 |  |  |  | 45055
21026152700 | EMER - INSTALL ODORIZER | [5 empty] | 170463.75 | 303602.2828 | -133138.5328 |  |  |  | 44789 | UNDERRUN EXPLANATION: PROJECT DID NOT REQUIRE AS MUCH CONTINGENCY, OR OUTSIDE LABOR COSTS FROM CONTRACTORS TTOY 3/2/23
21026152800 | EMER - RETIRE ODORIZER | [5 empty] | 62508.06 | 61.5191 | 62446.5409 |  |  |  | 44789
21026156100 | EMER-INSTALL 6' OF 2"PMMP MAIN | [5 empty] | 5612.12 | 6138.1743 | -526.0543 |  |  |  | 44544
21026156200 | EMR-RET 6'-2"PMP MAIN D222323 | [5 empty] | 75.03 | 61.2976 | 13.7324 |  |  |  | 44544
21026157501 | EMER - INSTALL 5'-3" PMMP | [5 empty] | 24476.25 | 13441.7151 | 11034.5349 |  |  |  | 44557
21026157600 | EMER - RETIRE 5'-3" PAMP | [5 empty] | 106.63 | 72.8047 | 33.8253 |  |  |  | 44557
21026993100 | RETIRE 229' - PMMP | [5 empty] | 0 | 103.8156 | -103.8156 |  |  |  | 44512
21026996700 | EMER - INSTALL 10'-4" PMMP | [5 empty] | 1315.39 | 1997.1109 | -681.7209 |  |  |  | 44207
21026996800 | EMER - RETIRE 10'-4" PMMP | [5 empty] | 0 | 95.6296 | -95.6296 |  |  |  | 44207
21026999000 | RETIRE 4"PLP SERVICE LINE | [5 empty] | 4696.25 | 5007.8601 | -311.6101 |  |  |  | 44832
22026158000 | INSTALL 200'-2" PMMP | [5 empty] | 23838.83 | 16273.357 | 7565.473 |  |  |  | 44636
22026159500 | EMER - INSTALL 5'-3" PMMP | [5 empty] | 11760.26 | 5999.0379 | 5761.2221 |  |  |  | 44571
22026159600 | EMER - RETIRE 5' - 3" PMMP | [5 empty] | 0 | 79.0999 | -79.0999 |  |  |  | 44571
22026161800 | INSTALL 8" PCF | [5 empty] | 29544.9 | 147.7348 | 29397.1652 |  |  |  | 45611
22026161900 | RETIRE LP MAIN - LEAKAGE | [5 empty] | 1465.95 | 124.7348 | 1341.2152 |  |  |  | #N/A
22026163000 | INSTALL ODORIZER | [5 empty] | 421358.34 | 596431.4654 | -175073.1254 |  |  |  | #N/A
22026164000 | INSTALL 5,100'-2" PMMP | [5 empty] | 1341919.13 | 1140024.6985 | 201894.4315 |  |  |  | 45392
22026164100 | RETIRE 6,711'-BS/CS IP | [5 empty] | 663.39 | 74.3089 | 589.0811 |  |  |  | #N/A
22026164201 | INSTALL 2,300'-2" PMMP | [5 empty] | 487634.39 | 442002.9907 | 45631.3993 |  |  |  | 45141
22026164300 | RETIRE 3,574'-BSLP | [5 empty] | 136.8 | 84.9152 | 51.8848 |  |  |  | 45141
22026168900 | STEPSTONE POD HVAC UPGRADE | [5 empty] | 19703.94 | 15710.0767 | 3993.8633 |  |  |  | 44778 | CCC# 59338 CCC# 55889 UPGRADED RTU JOSH MULLINS
22026169100 | RT. 89 POD RTU BUILDING | [5 empty] | 221479.78 | 143652.6755 | 77827.1045 |  |  |  | 45071 | CCC# 13947 MONITOR NOT ONSITE ACP NOT WORKING AT THAT SITE TODAY CCC# 13947 NOT ONSITE NOT ONSITE CCC#21297 CCC# 31371
22026170600 | INSTALL 7,200'-2"/4" PMMP | [5 empty] | 1527638.88 | 1129128.3572 | 398510.5228 |  |  |  | 45191
22026170700 | RETIRE BSLP | [5 empty] | 0 | 89.0305 | -89.0305 |  |  |  | 45191
22026172500 | INSTALL 5'-1" PMMP | [5 empty] | 4.3 | 1353.2384 | -1348.9384 |  |  |  | 44622
22026172600 | RETIRE 5'-1" PAMP | [5 empty] | 2198.83 | 66.5954 | 2132.2346 |  |  |  | 44622
22026173700 | 2022 SCADA VISIBILITY PROGRAM | [5 empty] | 28387.14 | 29658.8599 | -1271.7199 |  |  |  | 44826 | CCC# 66803 CCC# 66803 MONITOR FOR NEW COMM INSTALL CCC# 80236 INSTALLED NEW MIWI350 EBLANTON 9-22-2022
22026175300 | RETIRE R-1278 | [5 empty] | 1891.36 | 7307.4769 | -5416.1169 |  |  |  | 44910 | PREMISE IS RETIRED. GATHERED INFORMATION FOR CLOSEOUT PAPERWORK. JBRADFORD 12-15-22 CCC# 20387 TICKET# 20387
22026175400 | RETIRE R-1258 | [5 empty] | 114.11 | 7307.4769 | -7193.3669 |  |  |  | 44799 | CCC# 77893 STATIONRETIRED PER AMRP PROJECT WSHIMFESSEL 8-26-2022 ALL FACILITIES REMOVE D
22026175500 | RETIRE R-1275 | [5 empty] | 648.29 | 7307.4769 | -6659.1869 |  |  |  | 44799 | CCC# 77909 RETIRED REG STATION R-1275 ON AMRP PROJECT WSHIMFESSEL 8-26-2022 PREMISE IS RETIRED. GATHERED INFORMATION FOR CAPITOL CLOSEOUT.
22026175600 | RETIRE R-1256 | [5 empty] | 211.37 | 7307.4769 | -7096.1069 |  |  |  | 44729 | STATION RETIRED AND ALL PIPING REMOVED WSHIMFESSEL 06-07-2022
22026177500 | EMER - INSTALL 800'-6" CSHP | [5 empty] | 1030814.44 | 663631.3961 | 367183.0439 |  |  |  | 44832 | LEVEL 2 VARIANCE EXPLANATION IN WMSDOCS TTOY 2/3/23
22026177600 | EMER-RETIRE 800'-4" CSHP | [5 empty] | 1361.76 | 84.9152 | 1276.8448 |  |  |  | 44832
22026177700 | INSTALL 56'-6" PM-LP | [5 empty] | 107530.2 | 50137.1407 | 57393.0593 |  |  |  | 44697 | OVERRUN EXPLANATION: PROJECT WAS INITIALLY PLANNED FOR 56 FEET OF INSTALL. HOWEVER, 171 FEET OF DIRECTIONAL ROCK BORE WERE REQUIRED INSTEAD WITHOUT A SCOPE CHANGE REQUEST. ADDITIONAL SAW CUT AND CUT AND REMOVE WERE REQUIRED A S WELL. STEEL PLATES WERE NOT ESTIMATED. $7000 OF SEWER CAMERA WERE NOT EST IMATED EITHER SINCE IT WAS INITALLY PLANNED DIFFERENTLY. ALL THIS ADDITIONA L WORK TOOK MORE TIME SO LABOR INCREASED BY $19,000 AND THE OVERHEAD EFFECT OF THESE CHANGES WAS $9000.
22026177800 | ABDN 20'-6" BS-LP | [5 empty] | 142.7 | 73.9724 | 68.7276 |  |  |  | 44697
22026178200 | INSTALL 850'-2" PMIP | [5 empty] | 28727.79 | 33743.7503 | -5015.9603 |  |  |  | 44698
22026182101 | INSTALL 8,450' - 2"/4" PMMP | [5 empty] | 940113.78 | 861854.0803 | 78259.6997 |  |  |  | 45188
22026183800 | INSTALL 100'-2" PMIP | [5 empty] | 16969.45 | 18017.5748 | -1048.1248 |  |  |  | 44763
22026184000 | INSTALL 200'-6"/8" PMLP | [5 empty] | 210431.38 | 169438.8752 | 40992.5048 |  |  |  | 44803 | OVERRUN EXPLANATION: PROJECT WAS PLANNED FOR 360 HOURS OF LABOR TIME BUT ENDED UP WITH 565 HOURS DUE TO MULTIPLE COORDINATORS AND WELDER CHARGING 125 HOURS, SEGA WAS ORIGINALLY $20,641 BUT ENDED UP AT $34,463, PROJECT REQUIRED 698 TONS OF STONE AND DUST BUT WAS ORIGINALLY PLANNED FOR 60 TONS, ADDITIONAL EXTRA DEPTH UNITS OF 134, PROJECT ALSO CHAR CHARGED ~$6,000 OF SEWER CAMERA EVEN THOUGH THE SEWER WAS ALREADY UNCOVERED WHICH IS WHY WE WERE INSTALLING THE RELOCATION. TTOY 2/3/23
22026184100 | RETIRE 100'-BSLP | [5 empty] | 400 | 65.0112 | 334.9888 |  |  |  | 44803
22026185100 | INSTALL 10'-2" PMMP | [5 empty] | 6123.2 | 3850.4525 | 2272.7475 |  |  |  | 44691
22026185200 | RETIRE 10'-2" PMP | [5 empty] | 0 | 74.2578 | -74.2578 |  |  |  | 44691
22026190700 | INSTALL 4" SS *PAPER ONLY*** | [5 empty] | 0 | 84.2578 | -84.2578 |  |  |  | 44410 | FACILITY CREATED ON JO 20-0269816-01. UNABLE TO EDIT. SS ALREADY ABANDONED ON JO 22-0261909-00 BEFORE THIS JO WAS CREATED.
22026190800 | INSTALL 50'-4" PMLP | [5 empty] | 48441.53 | 45570.6341 | 2870.8959 |  |  |  | 44763
22026190900 | RETIRE 41'-4" BSLP | [5 empty] | 114.59 | 78.4365 | 36.1535 |  |  |  | 44763
22026191300 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 839.28 | 4801.1928 | -3961.9128 |  |  |  | 44733 | CCC# 71072
22026191400 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 0 | 124.8731 | -124.8731 |  |  |  | 44733
22026192500 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 400.52 | 4801.1928 | -4400.6728 |  |  |  | 44734 | CCC# 71244
22026192600 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 0 | 124.8731 | -124.8731 |  |  |  | 44747
22026194600 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 4024.88 | 4801.1928 | -776.3128 |  |  |  | 44846 | CCC# 3219 INSTALLED MIWI INSTALLED NEW MIWI350 WSHINFESSEL 10-12-22
22026194700 | RETIRED ELECTRONIC EXCHANGE | [5 empty] | 0 | 124.8731 | -124.8731 |  |  |  | 44846 | RETIRED OLD ERX WSHINFESSEL 10-12-22
22026194800 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5891.93 | 4801.1928 | 1090.7372 |  |  |  | 44798 | CCC# 78666 INSTALLED NEW MIWI350 JPASLEY 8-25-22
22026194900 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 0 | 124.8731 | -124.8731 |  |  |  | 44798 | RETIRED ERX INSTALLED NEW MIWI350 JPASLEY 8-25-22
22026195200 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 6702.65 | 4801.1928 | 1901.4572 |  |  |  | 44855 | CCC# 4229 CCC# 4229 INSTALLED NEW MIWI350 JPASLEY
22026195300 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 34.29 | 124.8731 | -90.5831 |  |  |  | 44855 | CCC# 4229 RETIRED OLD ERX INSTALLED NEW MIWI350 JPASLEY
22026196700 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5374.37 | 4801.1928 | 573.1772 |  |  |  | 44804 | CCC# 79339 INSTALLED NEW MIWI350. P2P W/GC OK 08/31/2022 WSHIMFE
22026196800 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 0 | 124.8731 | -124.8731 |  |  |  | 44804 | RETIRED OLD ERX INSTALLED NEW MIWI350 WSHIMFESSEL 8-31-2022
22026196900 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5192.52 | 4801.1928 | 391.3272 |  |  |  | 44799 | INSTALLED NEW MIWI350 JPASLEY 8-26-22
22026197000 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 698.72 | 124.8731 | 573.8469 |  |  |  | 44799 | RETIRED OLD ERX JPASLEY 8-26-22
22026198400 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5538.33 | 4801.1928 | 737.1372 |  |  |  | 44825 | ASSIST WITH RUNNING STAINLESS 09-21-2022 RHAYES CCOX RETIRED OLD ERX INSTALL NEW MIWI350 CCOX 9-21-22
22026198500 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 450.09 | 124.8731 | 325.2169 |  |  |  | 44825
22026199700 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5650.33 | 4801.1928 | 849.1372 |  |  |  | 44824 | RETIRED OLD ERX INSTALLED NEW MIWI350 EBLANTON 9-20-22
22026199800 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 592.76 | 124.8731 | 467.8869 |  |  |  | 44824 | RETIRED OLD RX INSTALLED NEW MIWI350 EBLANTON 9-20-22
22026205800 | RETIRE 20'-2" PMP | [5 empty] | 0 | 89.0305 | -89.0305 |  |  |  | 45187
22026205900 | RETIRE R-1682 | [5 empty] | 603.96 | 1417.3638 | -813.4038 |  |  |  | 45183
22026211500 | EMER-INSTALL 5'-2" PMMP | [5 empty] | 5656.19 | 16105.0112 | -10448.8212 |  |  |  | 44816
22026211600 | EMER-RETIRE 5'-2" PMMP | [5 empty] | 3884.45 | 4031.2726 | -146.8226 |  |  |  | 44816
22026212100 | INSTALL CHAIN LINK FENCE | [5 empty] | 9226.54 | 24086.2589 | -14859.7189 |  |  |  | 44876 | INSTALLED CHAIN LINK FENCE JMULLINS 11-11-22
22026214300 | STEPSTONE POD HVAC/RTU | [5 empty] | 0 | 55.5311 | -55.5311 |  |  |  | 44778 | UPGRADED RTU
22026217500 | EMER-INSTALL 2' OF 3"PMMP MAIN | [5 empty] | 6378.4 | 5764.1191 | 614.2809 |  |  |  | 44785
22026217600 | EMER-RETIRE 2' OF 3"PAMP MAIN | [5 empty] | 4155.42 | 1084.9152 | 3070.5048 |  |  |  | 44785
22026219700 | EMER-INSTALL 8" STOPPLE FITS | [5 empty] | 39002.9 | 30183.131 | 8819.769 |  |  |  | 44805
22026219800 | EMER-RETIRE 1' OF 8"CSHP MAIN | [5 empty] | 160 | 84.9152 | 75.0848 |  |  |  | 44805
22026221900 | EMER - RETIRE 20'-3" PMP | [5 empty] | 6987.81 | 3460.1765 | 3527.6335 |  |  |  | 44838
22026222300 | EMER - INSTALL 7'-4" PMLP | [5 empty] | 13873.55 | 4005.634 | 9867.916 |  |  |  | 44818
22026222400 | EMER - RETIRE 7'-4" PLP | [5 empty] | 0 | 89.0305 | -89.0305 |  |  |  | 44818
22026227600 | EMER - INSTALL 60'-4" PMLP | [5 empty] | 21421.89 | 30615.0582 | -9193.1682 |  |  |  | 44832
22026227700 | EMER - RETIRE 60'-4" BSLP | [5 empty] | 8123.84 | 74.3089 | 8049.5311 |  |  |  | 44832
22026228201 | INSTALL 4,225'-2"/6" PMMP | [5 empty] | 1935349.38 | 1875934.718 | 59414.662 |  |  |  | 45068
22026228300 | RETIRE 6,106'- LP MAIN | [5 empty] | 182.4 | 952.0929 | -769.6929 |  |  |  | 45065
22026228400 | RETIRE 1133'- MP MAIN | [5 empty] | 0 | 952.0929 | -952.0929 |  |  |  | 45050
22026228700 | RETIRE ELECTRONIC | [5 empty] | 0 | 74.3089 | -74.3089 |  |  |  | 44833
22026230301 | INSTALL 1,725'-2" PMMP | [5 empty] | 676511.46 | 636475.4754 | 40035.9846 |  |  |  | 45002
22026230400 | RETIRE 5,578' - IP MAIN | [5 empty] | 1019.8 | 475.239 | 544.561 |  |  |  | 45002
22026230500 | RETIRE 1,368' - MP MAIN | [5 empty] | 14.31 | 475.239 | -460.929 |  |  |  | 45002
22026231000 | EMER - INSTALL 1'-2" PMMP | [5 empty] | 6865.44 | 8585.1316 | -1719.6916 |  |  |  | 44899
22026231100 | EMER - RETIRE 1'-2" PMP | [5 empty] | 0 | 60.3089 | -60.3089 |  |  |  | 44899
22026232600 | INSTALL 200'-2" PMMP | [5 empty] | 20049.03 | 40586.0582 | -20537.0282 |  |  |  | 44911
22026234100 | NEW RTU/COMM BUILDING | [5 empty] | 0 | 136.2135 | -136.2135 |  |  |  | 44831
22026234500 | INSTALL NEW RTU/COMM BUILDING | [5 empty] | 0 | 136.2135 | -136.2135 |  |  |  | 44833 | JMULLINS COMPLETING PAPERWORK
22026234700 | INSTALL 3" STOPPLE FITTING | [5 empty] | 7929.81 | 13630.9028 | -5701.0928 |  |  |  | 44895
22026234800 | RETIRE 75' OF 3"BSMP MAIN | [5 empty] | 114.9 | 119.2135 | -4.3135 |  |  |  | 44894
22026234901 | INSTALL 4,100'-2" PMMP | [5 empty] | 217597.98 | 188453.1623 | 29144.8177 |  |  |  | 45250
22026236400 | INSTALL 450'-4" PMMP | [5 empty] | 52709.69 | 61251.1595 | -8541.4695 |  |  |  | 45104
22026237301 | INSTALL 11,150'-8"6"4"2" PMMP | [5 empty] | 3177275.55 | 2580803.0362 | 596472.5138 |  |  |  | 45643 | ADV JTOY FOL
22026237400 | RETIRE LP MAIN | [5 empty] | 886.14 | 139.1159 | 747.0241 |  |  |  | #N/A
22026237500 | RETIRE MP MAIN | [5 empty] | 554.6 | 139.1159 | 415.4841 |  |  |  | #N/A
22026237801 | INSTALL 4,100'-2" PMMP | [5 empty] | 836183.38 | 765451.6207 | 70731.7593 |  |  |  | 45349
22026237900 | RETIRE 5,265' IP MAIN | [5 empty] | 217.02 | 135.9942 | 81.0258 |  |  |  | #N/A
22026238100 | RETIRE R-1230-A | [5 empty] | 2779.72 | 1996.3422 | 783.3778 |  |  |  | #N/A | CCC#62228
22026240500 | INSTALL VRG | [5 empty] | 7577.2 | 14784.1417 | -7206.9417 |  |  |  | 44903 | NOT ON SITE. GETTING MATERIAL FROM SHOP FOR JOB. CCC# 6417 CCC# 6417 CCC# 6417 CCC# 6417
22026240600 | RETIRE VRG | [5 empty] | 1416.09 | 1478.5709 | -62.4809 |  |  |  | 44903
22026240700 | INSTALL FENCE FOR NEW LAND | [5 empty] | 63926.63 | 26194.1417 | 37732.4883 |  |  |  | 44895 | CCC# 12436 TICKET# 12436 CCC# 16515 GATHER INFO FOR CAPITAL PAPERWORK
22026244400 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 17382.14 | 26337.6752 | -8955.5352 |  |  |  | 45020 | CCC# 22134 WELDED NEW TAP ON INLET FOR MIWI INSTALL, JMARTIN DMARTIN 3-27-23 CCC# 23352 INSTALL NEW MIWI 350, UNIT IS WAITING FOR A TICKET # TO BE ABLE TO PUT ONLINE. JMARTIN 4-4-23 CCC# 23905 STILL NEED TO DO P2P WITH GAS CONTROL, MODEM NOT COMMUNICATING JMARTIN 4-6-23 CCC# 24126 TRIED TO FIX COMM ISSUE WITH MODEM CCC# 23905 P2P W/GAS CONTROL OK, JMARTIN 4-10-23 CCC# 26515 COMP ANOTHER P2P WITH GAS CONTROL. JMARTIN 4-21-23 NOT ONSITE, FIXED ISO AND SUBMITTED NEW CAP FOR DRAWING.
22026244500 | INSTALL NEW SCADA EQUIPMENT | [5 empty] | 17938.12 | 19488.6752 | -1550.5552 |  |  |  | 45026 | CCC# 22091 INSTALLED NEW INLET TAP FOR MIWI, JMARTIN DMARTIN 3-27-23 NOT ONSITE DELAY DUE TO RAIN NOT ONSITE ACP RESCHEDULED CCC# 24233 INSTALLED NEW MIWI 350 CCC# 26551 WORKED WITH GC TO GET SITE ONLINE. P2P COMP. JMARTIN 4-21-23 NOT ONSITE, UPDATED ISO AND SBMITTED REDLINED DRAWIN.
22026245300 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 3807.72 | 10393.9744 | -6586.2544 |  |  |  | 44945
22026245400 | EMER - RETIRE 5'-2" PMMP | [5 empty] | 0 | 131.2422 | -131.2422 |  |  |  | 44945
22026245700 | INSTALL BUILDING R-1667 | [5 empty] | 651.28 | 300.4844 | 350.7956 |  |  |  | 44923
22026245800 | RETIRE MIS FACILITIES R-1639 | [5 empty] | 0 | 131.2422 | -131.2422 |  |  |  | 44923
23026248700 | INSTALL 2" SS | [5 empty] | 2373.93 | 18496.357 | -16122.427 |  |  |  | 45007
23026248800 | RETIRE 50' - 2" CSMP | [5 empty] | 6678.36 | 138.8485 | 6539.5115 |  |  |  | 45007
23026250900 | INSTALL EC 350 | [5 empty] | 755.31 | 2339.3221 | -1584.0121 |  |  |  | 44964 | INSTALLED NEW EC 350 INSTALLED EC 350 J.BRADFORD 2-7-23
23026251000 | RETIRE PAPER BILLING CHART | [5 empty] | 803.89 | 131.2422 | 672.6478 |  |  |  | 44964 | BILLING CHART REMOVED AND EC 350 INSTALLED
23026251600 | INSTALL RTU BUILDING | [5 empty] | 2010.08 | 170.6969 | 1839.3831 |  |  |  | 45071 | CCC#28635 WORK DONE FOR WHAT THEY ARE DOING TODAY 5-5-23 JUSTIN HOBBS CCC# 31032 CREATED OTH FACID 861369 FOR HVAC. SM 12/1/23
23026252400 | RETIRE GMB MS#804399 RUN | [5 empty] | 21780.96 | 2962.0987 | 18818.8613 |  |  |  | 44963 | NOT ONSITE NOT ONSITE GATHERING PARTS CCC# 15748 TICKET# 15748 RETIRED GMB SETTING 2-6-23 BY J.BRADFORD
23026253100 | PM- GREENSITE TRABU INSTALL | [5 empty] | 30780.16 | 1236355 | -1205574.84 |  |  |  | 44830
23026253200 | PM- GREENSITE TRABU ABANDON | [5 empty] | 235.97 | 0 | 235.97 |  |  |  | 44830
23026253700 | PM-GREENSITE HWY 27 INSTALL | [5 empty] | 20755.46 | 1236355 | -1215599.54 |  |  |  | 44831
23026253800 | PM-GREENSITE HWY 27 ABANDON | [5 empty] | 137.28 | 0 | 137.28 |  |  |  | 44831
23026261100 | INSTALL ULTRASONIC METER | [5 empty] | 52334.12 | 48123.5304 | 4210.5896 |  |  |  | #N/A | TICKET# 41313 CCC# 60438 TICKET# 60438 CCC# 60946 P2P W/ GC
23026263200 | GMB TO CAB CONVERSION | [5 empty] | 758.88 | 124.7348 | 634.1452 |  |  |  | 45048 | GATHER PARTS INFO 27 - 300,000 BTU HANGING UNIT HEATERS = 8,100,000 3 - 300,000 BTU ROOF TOP UNITS = 900,000 TOTAL BTU LOAD - 9,000,000 GMB TO CAB CONVERSION
23026264000 | INSTALL NEW METER | [5 empty] | 29289.91 | 31875.3689 | -2585.4589 |  |  |  | #N/A | CCC 71591 INSTALLED NEW METER CCC 71591
23026266800 | EMER - INSTALL 7'-2" PMMP | [5 empty] | 537.54 | 15964.0017 | -15426.4617 |  |  |  | 45021
23026266900 | EMER - RETIRE 7'-2" PMAP | [5 empty] | 0 | 64.7348 | -64.7348 |  |  |  | 45021
23026267000 | EMER - INSTALL 2'-2" PMLP | [5 empty] | 1235.74 | 7754.9733 | -6519.2333 |  |  |  | 45021
23026267100 | EMER - RETIRE 2'-2" PLP | [5 empty] | 0 | 64.7348 | -64.7348 |  |  |  | 45021
23026267600 | INSTALL 110'-4"PMLP | [5 empty] | 32525.16 | 46300.0467 | -13774.8867 |  |  |  | 45180
23026268700 | PM-DE LINE PH 2 DENT 2/STPL 3 | [5 empty] | 705427.76 | 1307000 | -601572.24 |  |  |  | 45069
23026269400 | PM-DE LINE ILI PH2 DENT2,STPL3 | [5 empty] | 198957.22 | 216349 | -17391.78 |  |  |  | 45077
23026273200 | EMER-RETIRE 741'-1" PMP | [5 empty] | 1327.21 | 1738.6263 | -411.4163 |  |  |  | 45070
23026274800 | RETIRE REG BUILDING | [5 empty] | 0 | 117.7346 | -117.7346 |  |  |  | 45061
23026274900 | EMER - INSTALL 4'-2" PMMP | [5 empty] | 15519.62 | 31722.4446 | -16202.8246 |  |  |  | 45070
23026275000 | EMER - RETIRE 4'-2" PMMP | [5 empty] | 2331.35 | 139.1159 | 2192.2341 |  |  |  | 45070
23026275100 | RETIRE 276'-3" BSLP | [5 empty] | 5918.41 | 12701.243 | -6782.833 |  |  |  | 45069
23026276600 | RETIRE RTU FACILITY | [5 empty] | 2357.33 | 139.1159 | 2218.2141 |  |  |  | 45250 | CCC#33813 PICKED UP TRASH CPRRECTED PAPER WORK JPASLEY 11-20-23
23026278500 | EMER - INSTALL 3'-2" PMMP | [5 empty] | 3085.38 | 4078.3783 | -992.9983 |  |  |  | 45113
23026278600 | EMER - RETIRE 3'-2" PMMP | [5 empty] | 10.24 | 139.1159 | -128.8759 |  |  |  | 45113
23026279900 | RETIRE 38'-3" PMP | [5 empty] | 0 | 139.1159 | -139.1159 |  |  |  | 45103
23026281600 | EMER-INSTALL 3'-3" PMMP | [5 empty] | 5032.43 | 5640.4544 | -608.0244 |  |  |  | 45124
23026281700 | EMER-RETIRE 3'-3" PMAP | [5 empty] | 1946 | 67.1159 | 1878.8841 |  |  |  | 45124
23026282600 | EMER - RETIRE 216'-2" PAMP | [5 empty] | 5057.99 | 2153.608 | 2904.382 |  |  |  | 45121
23026286000 | EMER - INSTALL 6'-2" PMMP | [5 empty] | 5456.45 | 14279.5419 | -8823.0919 |  |  |  | 45159
23026286100 | EMER - RETIRE 6'-2" PMMP | [5 empty] | 5375.26 | 67.1159 | 5308.1441 |  |  |  | 45159
23026287800 | INSTALL 500'-4" PMMP | [5 empty] | 175667.6 | 99252.0533 | 76415.5467 |  |  |  | 45222
23026287900 | RETIRE 500'-3" PMP | [5 empty] | 0 | 119.4953 | -119.4953 |  |  |  | 45222
23026288500 | EMER - INSTALL 3'-2" PMMP | [5 empty] | 33.23 | 15193.894 | -15160.664 |  |  |  | 45159
23026288600 | EMER - RETIRE 3'-2" PMP | [5 empty] | 4237.6 | 119.4953 | 4118.1047 |  |  |  | 45159
23026289900 | EMER-INSTALL 8'-3" PMMP | [5 empty] | 3026.88 | 1914.647 | 1112.233 |  |  |  | 45170
23026290000 | EMER-RETIRE 8'-3" PAMP | [5 empty] | 9034.26 | 7157.6376 | 1876.6224 |  |  |  | 45170
23026293900 | EMER-INSTALL 3' OF 2"PMMP MAIN | [5 empty] | 7202.89 | 14157.3554 | -6954.4654 |  |  |  | 45187
23026294000 | EMER-RETIRE 3' OF 2"PMMP MAIN | [5 empty] | 0 | 119.4953 | -119.4953 |  |  |  | 45187
23026295300 | RETIRE FENCE | [5 empty] | 0 | 119.4953 | -119.4953 |  |  |  | 45188
23026297000 | INSTALL PCF'S LP | [5 empty] | 2982.68 | 145.9261 | 2836.7539 |  |  |  | 45183
23026298400 | INSTALL MODEM AND ANTENNA | [5 empty] | 0 | 8303.7376 | -8303.7376 |  |  |  | 45250 | CORRECTED PAPER WORK 11-20-23 JPASLEY
23026300401 | INSTALL 1150' 4/2" PMMP | [5 empty] | 291755.2 | 220213.1673 | 71542.0327 |  |  |  | 45428 | TTOY 5/6/24: ATTEMPTED TO REVISE DUE TO UNDERRUN, MATERIAL PO NOT FILLED,
23026300500 | RETIRE 3896' 4/3/2" PAMP | [5 empty] | 0 | 160.3697 | -160.3697 |  |  |  | #N/A
23026300600 | INSTALL 180'-4" PMLP | [5 empty] | 77710.69 | 62129.0817 | 15581.6083 |  |  |  | 45303
23026300700 | RETIRE 150'-4" PMLP | [5 empty] | 0 | 124.9261 | -124.9261 |  |  |  | #N/A
23026302300 | RETIRE PAPER GAUGE | [5 empty] | 835.24 | 989.8688 | -154.6288 |  |  |  | 45231 | NOT ONSITE WORK POSTPONED TILL TOMMOROW CCC# 49846
23026302800 | EMER - INSTALL 2'-3" PMP | [5 empty] | 4049.34 | 3855.2637 | 194.0763 |  |  |  | 45229
23026302900 | EMER - RETIRE 2'-3" PMP | [5 empty] | 1224.64 | 122.9261 | 1101.7139 |  |  |  | 45229
23026303000 | EMER - RETIRE 13'-3" BSLP | [5 empty] | 19694.3 | 23992.5325 | -4298.2325 |  |  |  | #N/A
23026303200 | R-1647 REBUILD INSTALL | [5 empty] | 123864.29 | 69868.5777 | 53995.7123 |  |  |  | #N/A | BYPASS HOSE PICK UP/OHIO NOT ONSITE NOT ONSITE BUILD AND TEST TEMP STATION CCC# 56331 CCC# 56478 INSTALLING TEMP STATION CCC# 56478 PUT TEMP STATION ONLINE. NOT ONSITE. DOING EXPENSE REPORT FOR PURCHASE FOR JOB. CCC# 56815 MONITOR FOR VAC TRUCK. JMARTIN 12/26/23 CCC# 57050 CCC# 57112 CCC# 57112 CCC# 57112 CCC# 57190
23026303300 | R-1647 PARTIAL RETIRE | [5 empty] | 0 | 124.9261 | -124.9261 |  |  |  | #N/A
23026303400 | INSTALL 20'-2" CSHP | [5 empty] | 212847.86 | 112306.0322 | 100541.8278 |  |  |  | 45516
23026306000 | EMER-INSTALL 2'-3" PMMP | [5 empty] | 6338.35 | 6158.638 | 179.712 |  |  |  | 45264
23026306100 | EMER-RETIRE 2'-3" PMMP | [5 empty] | 0 | 124.9261 | -124.9261 |  |  |  | 45264
23026306200 | INSTALL BUILDINGS R-1667 | [5 empty] | 0 | 147.9261 | -147.9261 |  |  |  | 45258
24026309800 | INSTALL 75' - 2" PMMP | [5 empty] | 21399.98 | 15016.2249 | 6383.7551 |  |  |  | 45320
24026310600 | INSTALL 2, 2" STOPPLE FITTINGS | [5 empty] | 21866.79 | 32187.8821 | -10321.0921 |  |  |  | 45460
24026310700 | ABANDON ~ 150'- 2" CSIP | [5 empty] | 577.39 | 118.4933 | 458.8967 |  |  |  | #N/A
24026310800 | INSTALL 1400' OF 2" PMMP | [5 empty] | 67204.19 | 90861.9332 | -23657.7432 |  |  |  | 45483
24026314400 | INSTALL 1,200'-4" PMMP | [5 empty] | 441793.04 | 166742.0112 | 275051.0288 |  |  |  | 45762 | PAST COMMIT DATE DUE TO WEATHER AND ROUGH DIFFULCT OF JOB AND BORE
24026315200 | INSTALL NEW EC 350 | [5 empty] | 8919.7 | 5524.5572 | 3395.1428 |  |  |  | #N/A | INSTALLED NEW EC350
24026315300 | RETIRE EC350 | [5 empty] | 273.05 | 160.3697 | 112.6803 |  |  |  | #N/A | RETIRED MINI AT
24026316000 | EMER - INSTALL 2'-3" PMLP | [5 empty] | 6877.79 | 9590.2924 | -2712.5024 |  |  |  | 45335
24026316100 | EMER - RETIRE 2'-3" PALP | [5 empty] | 0 | 160.3697 | -160.3697 |  |  |  | #N/A
24026319000 | ADD SOLAR BACKUP | [5 empty] | 6634.21 | 15005.0106 | -8370.8006 |  |  |  | #N/A
24026320400 | INSTALL MIWI W/FLOW SWITCH | [5 empty] | 17939.6 | 21508.3856 | -3568.7856 |  |  |  | #N/A | CCC# 93710 CCC# 94300 INSTALLED NEW TAPS FOR MIWI
24026325000 | MIWI WITH SOLAR | [5 empty] | 17266.04 | 19446.0487 | -2180.0087 |  |  |  | #N/A | CCC# 88776 INSTALL NEW TAPS FOR MIWI.
24026325100 | MIWI WITH SOLAR | [5 empty] | 0 | 121.4465 | -121.4465 |  |  |  | #N/A
24026326000 | UPGRADE SCADA SYSTEM | [5 empty] | 9009.11 | 10627.0487 | -1617.9387 |  |  |  | #N/A | CCC 92291 CCC 92291
24026326100 | UPGRADE SCADA SYSTEM | [5 empty] | 494.05 | 121.4465 | 372.6035 |  |  |  | #N/A | CCC 92291
24026327000 | INSTALL ELECTRONICS | [5 empty] | 8645.98 | 15644.0403 | -6998.0603 |  |  |  | #N/A | CCC# 84533
24026327100 | RETIRE ELECTRONICS | [5 empty] | 0 | 118.4933 | -118.4933 |  |  |  | #N/A
24026327200 | INSTALL ELECTRIONICS | [5 empty] | 7576.45 | 15644.0403 | -8067.5903 |  |  |  | #N/A | CCC# 84650
24026327300 | RETIRE ELECTRONICS | [5 empty] | 0 | 118.4933 | -118.4933 |  |  |  | #N/A
24026327800 | INSTALL ELECTRONICS | [5 empty] | 9991.66 | 15644.0403 | -5652.3803 |  |  |  | #N/A | CCC# 84481
24026327900 | RETIRE ELECTRONICS | [5 empty] | 9.73 | 118.4933 | -108.7633 |  |  |  | #N/A | CCC# 84481
24026329400 | EMER - INSTALL 2'-3" PMLP | [5 empty] | 6384.11 | 4221.248 | 2162.862 |  |  |  | 45352
24026329500 | EMER - RETIRE 2'-3" PALP | [5 empty] | 0 | 121.4465 | -121.4465 |  |  |  | #N/A
24026329700 | EMER - 2'-2" PMMP | [5 empty] | 8583.87 | 8686.5178 | -102.6478 |  |  |  | 45365
24026329800 | EMER - RETIRE 2'-2" PMP | [5 empty] | 0 | 121.4465 | -121.4465 |  |  |  | #N/A
24026331400 | RETIRE R-1279 | [5 empty] | 1587.88 | 973.0487 | 614.8313 |  |  |  | #N/A | CCC 63860 RETIRED STATION R-1279
24026332600 | EMER INSTALL 10'-6" PMMP | [5 empty] | 32430.81 | 29701.1651 | 2729.6449 |  |  |  | 45366
24026332700 | EMER - RETIRE 15'- PMMP | [5 empty] | 0 | 139.7787 | -139.7787 |  |  |  | #N/A
24026335100 | EMER - INSTALL 4'-3" PMMP | [5 empty] | 12497.25 | 9960.0387 | 2537.2113 |  |  |  | 45378
24026335200 | EMER - 4' - 3" PMMP | [5 empty] | 0 | 121.4465 | -121.4465 |  |  |  | #N/A
24026335400 | EMER - INSTALL 2'-2" PMMP | [5 empty] | 7568.56 | 5032.0911 | 2536.4689 |  |  |  | 45379
24026335500 | EMER - RETIRE - 2'-2" PMMP | [5 empty] | 0 | 121.4465 | -121.4465 |  |  |  | #N/A
24026337600 | INSTALL 30'-2" PMMP | [5 empty] | 27755.6 | 27915.2109 | -159.6109 |  |  |  | 45435
24026337700 | RETIRE 20'-2" PMMP | [5 empty] | 19.74 | 139.7787 | -120.0387 |  |  |  | #N/A
24026337900 | INSTALL 2,550'-2" PMMP | [5 empty] | 82903.24 | 91900.6833 | -8997.4433 |  |  |  | 45421
24026342300 | EMER - RETIRE 267'-2" PMP | [5 empty] | 2861.12 | 2962.6295 | -101.5095 |  |  |  | #N/A
24026343700 | EMER - INSTALL 3'-3" PMMP | [5 empty] | 10177.86 | 6477.801 | 3700.059 |  |  |  | 45443
24026343800 | EMER - RETIRE 3'-3" PMP | [5 empty] | 0 | 139.7787 | -139.7787 |  |  |  | #N/A
24026345000 | INSTALL NEW EC 350 UNIT | [5 empty] | 548.93 | 2029.8027 | -1480.8727 |  |  |  | #N/A | INSTALLED NEW EC350 S/N 232590014 0-300#PSIA
24026345100 | RETIRE EC 350 UNIT | [5 empty] | 123.53 | 70.7787 | 52.7513 |  |  |  | #N/A | RETIRED OLD EC350 INSTALLED NEW EC350
24026349900 | EMER - INSTALL 3'-2" PMMP | [5 empty] | 8029.62 | 7024.6066 | 1005.0134 |  |  |  | 45483
24026350000 | EMER - RETIRE 3'-2" PMP | [5 empty] | 0 | 139.7787 | -139.7787 |  |  |  | #N/A
24026350900 | RETIRE 38'-2" CSMP | [5 empty] | 0 | 139.7787 | -139.7787 |  |  |  | #N/A
24026352000 | INSTALL 700'-2" PMMP | [5 empty] | 75786.62 | 78413.3497 | -2626.7297 |  |  |  | 45698
24026353200 | EMER - INSTALL 3'-4" PMMP | [5 empty] | 3109.71 | 7993.6359 | -4883.9259 |  |  |  | 45505
24026353300 | EMER - RETIRE 3'-4" PAMP | [5 empty] | 0 | 139.7787 | -139.7787 |  |  |  | #N/A
24026354100 | EMER - RETIRE 308'-2" PLP | [5 empty] | 3269.44 | 2331.6111 | 937.8289 |  |  |  | #N/A
24026358600 | INSTALL 175' - 4" PMMP | [5 empty] | 90409.34 | 72423.4515 | 17985.8885 |  |  |  | 45628
24026359000 | EMER - INSTALL NEW REGULATOR | [5 empty] | 32098.29 | 163089.7838 | -130991.4938 |  |  |  | #N/A
24026359100 | EMER - RETIRE REGULATOR | [5 empty] | 3027.28 | 124.2298 | 2903.0502 |  |  |  | #N/A
24026361500 | EMER - INSTALL 2'-3" PMLP | [5 empty] | 4884.17 | 3524.9349 | 1359.2351 |  |  |  | 45562
24026361600 | EMER - RETIRE 2'-3" PALP | [5 empty] | 0 | 127.2637 | -127.2637 |  |  |  | #N/A
24026362300 | INSTALL 2" SS | [5 empty] | 0 | 159.2637 | -159.2637 |  |  |  | 45516
24026364900 | INSTALL 2,300'-4" PMMP | [5 empty] | 215200.02 | 164697.53 | 50502.49 |  |  |  | 45740
24026365600 | INSTALL SSD UNIT W/ZINC RIBBON | [5 empty] | 95863.74 | 55300.1794 | 40563.5606 |  |  |  | #N/A | INSTALLED DUAL RUNS OF 420' ZINC ON THE NORTH & SOUTH SIDE OF 12"CSHP MAIN 5' OFF FROM MAIN & BELOW THE PIPE / INSTALLED DAIRYLAND SOLID-STATE DECOUPLER (SSD-2/2-5.0-100R) SERIAL #64954 WITH ENCLOSURE / ZINC MAT INSTALLED WITH #6 WHITE WIRE AND GREEN TAPE / TS FAC 885476 INSTALLED ON THE EAST END OF PROJECT & TS FAC 885477 INSTALLED ON THE WEST END OF PROJECT WITH #6 WHITE WIRE RUN UP FROM ZINC
24026368000 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 4545.67 | 12185.6111 | -7639.9411 |  |  |  | 45635
24026368100 | EMER - RETIRE 5'-2" PMMP | [5 empty] | 295.06 | 137.4585 | 157.6015 |  |  |  | #N/A | WORKED ORDER
24026371800 | EMER - INSTALL 3'-2" PMMP | [5 empty] | 19259.53 | 14865.4926 | 4394.0374 |  |  |  | 45648
24026371900 | EMER - RETIRE 3'-2" PMP | [5 empty] | 0 | 111.0024 | -111.0024 |  |  |  | #N/A
24026373200 | INSTALL SOLAR BACKUP UNIT | [5 empty] | 7104.24 | 9877.4639 | -2773.2239 |  |  |  | #N/A | CCC# 108028
24026373700 | INSTALL SOLAR BACKUP UNIT | [5 empty] | 8114.69 | 9877.4639 | -1762.7739 |  |  |  | #N/A | CCC 107505 CCC#107505 WORK IS COMPLETE ON 2-18-2025 1550 J HOBBS
24026373800 | EMER - INSTALL 3'-2" PMMP | [5 empty] | 6014.6 | 4350.0713 | 1664.5287 |  |  |  | 45648
24026373900 | EMER - RETIRE 3'-2" PAMP | [5 empty] | 0 | 111.0024 | -111.0024 |  |  |  | #N/A
24026376300 | EMER - INSTALL 5'-2" PMIP | [5 empty] | 6514.7 | 6864.5633 | -349.8633 |  |  |  | 45681
24026376400 | EMER - RETIRE 5'-2" PAIP | [5 empty] | 0 | 111.0024 | -111.0024 |  |  |  | #N/A
25026377900 | INSTALL LP FITTING-PAPER ONLY | [5 empty] | 0 | 139.0024 | -139.0024 |  |  |  | 45643
25026378800 | EMER - INSTALL 25'-2" PMMP | [5 empty] | 81247.31 | 46887.3793 | 34359.9307 |  |  |  | 45681
25026378900 | EMER - RETIRE 25'-3" PAMP | [5 empty] | 0 | 111.0024 | -111.0024 |  |  |  | #N/A
25026379000 | EMER - INSTALL 9'-2" PMMP | [5 empty] | 1184.26 | 11723.1799 | -10538.9199 |  |  |  | 45685
25026379101 | EMER - RETIRE 9'-2" PMP | [5 empty] | 9245.89 | 6663.1804 | 2582.7096 |  |  |  | #N/A
25026379500 | INSTALL SCADA VISIBILITY | [5 empty] | 13338.87 | 16667 | -3328.13 |  |  |  | #N/A | NOT ONSITE ORDER NOT NEEDED CCC# 119324 NOT ONSITE WENT ENROUTE TO THE WRONG JOB CCC# 121903 INSTALL POLES, BATTERY BOX, AND ER350.
25026379700 | INSTALL SCADA VISIBILITY | [5 empty] | 11378.96 | 16667 | -5288.04 |  |  |  | #N/A | CCC 109193 INSTALLED 1'' TEE AND 1/4'' BALL VALVE FOR FUTURE SCADA VISIBILITY CCC 123850 CCC#123850
25026381800 | INSTALL 250'-2" PMMP | [5 empty] | 52355.75 | 32185.6133 | 20170.1367 |  |  |  | 45744
25026393800 | INSTALL 2,100'-2" PMMP | [5 empty] | 110997.26 | 177755.4678 | -66758.2078 |  |  |  | 45797
25026400200 | INSTALL 550'-2" PMMP | [5 empty] | 47508 | 57765.7205 | -10257.7205 |  |  |  | 45772
25026400700 | RETIRE 100'-4" PMMP | [5 empty] | 2247.29 | 5393.6654 | -3146.3754 |  |  |  | #N/A | ABANDONED 135' OF 4" PLASTIC TO ALLOW FOR DRIVEWAY ENTRANCE, STUB LEFT FOR FUTURE SERVICE TO PROPERTY- PAPERWORK CO OFF SITE
25026403000 | EMER - INSTALL 2'-3" PMMP | [5 empty] | 230.88 | 13653.342 | -13422.462 |  |  |  | 45743
25026403100 | EMER - RETIRE 2'-3" PAMP | [5 empty] | 15086.34 | 138.8251 | 14947.5149 |  |  |  | #N/A | ABANDONED SECTION OF LEAKING CRACKED PLASTIC PIPE AND REPLACED WITH NEW PIP E
16026666400 | INSTALL NEW CWT HEATER | [5 empty] | 188315.11 | 231341.3745 | -43026.2645 |  |  |  | 44911 | CC# 53363. DRAINED WATERBATH HEATER. 01-26-22 DSASH CCC 55246 CCC 55359 CCC 55691 CCC 56098 CCC 57419 NO TICKET NEEDED NO TICKET NEEDED NO TICKET NEEDED CC# 70901. 6/20/22 DSASH RETIRED OLD WATER BATH INSTALLED NEW CWT HEATER DASH 3-3-22
16026666500 | RETIRE EXIST WB HEATER | [5 empty] | 29153.65 | 140.0254 | 29013.6246 |  |  |  | 44623 | CCC # 53363 CCC 53705 CCC 54571 CCC # 54571 NO TICKET NEEDED CCC # 57419 NOT ON SITE NO CCC NEEDED NO CCC NOT ON SITE CHARGED TO LE TO GET VRG FOR REG REPLACE INSTALLED NEW CWT HEATER 3-3-22 DASH
17026698500 | INSTALL VRG PRESS CONT EQUIPMT | [5 empty] | 247791.39 | 128512.8191 | 119278.5709 |  |  |  | 44425 | CC# 27659. 6/11/21 DSASH CCC #27659 CC# 27769. 6/14/21 DSASH CC# 27972. 6/16/21 DSASH CC# 28248. 6/17/21 DSASH CCC #28248 CCC #28445 CC# 28445. 6/18/21 DSASH CC# 28787. 6/23/21 DSASH CCC #28787 NOT AT STATION OFF SITE WORKING ON PAPERWORK FOR JOB 7/1/2021 GCCC TICKET NOT REQUIRED NOT AT STATION OFF SITE COMPLETING PAPERWORK 7/19/21 AND 8/17/21 CFARIS
17026698600 | RETIRE EXIST PRESS CONT EQUIPM | [5 empty] | 299.36 | 131.3267 | 168.0333 |  |  |  | 44425
17026699800 | INSTALL ELEVATED BUS STOP ASSM | [5 empty] | 9561.04 | 61743.3758 | -52182.3358 |  |  |  | 44425 | UNDERRUN EXPLANATION: THIS JOB ORDER WAS WORKED IN ONJUNCTION WITH ANOTHER JOB ORDER, 17-0269850-00, WHICH OVERRAN DUE TO THE CONTRACT LABOR BEING CHA RGED TO THAT JOB ORDER INSTEAD. THAT AMOUNT WAS APPROXIMATELY $40,000.
17026699900 | INSTALL NEW CH LINK FENCING | [5 empty] | 0 | 20572.3069 | -20572.3069 |  |  |  | 44425
17026735700 | RETIRE 3510' MAIN - D243673 | [5 empty] | 8338.24 | 78.7024 | 8259.5376 |  |  |  | 44285
18026752700 | INSTALL VRG PILOT | [5 empty] | 5363.35 | 5404.3267 | -40.9767 |  |  |  | 44425 | CCC #27769 CCC #28734
18026752800 | RETIRE | [5 empty] | 838.05 | 52.1634 | 785.8866 |  |  |  | 44425
18026762800 | INSTALL NEW CHAIN LINK FENCE | [5 empty] | 16843.44 | 17042.1322 | -198.6922 |  |  |  | 44791 | MONITORED NEW CHAINLINK FENCE INSTALL AMCCORMICK 8-18-22
18026762900 | REPLACE CHAIN LINK FENCE | [5 empty] | 429.99 | 73.5943 | 356.3957 |  |  |  | 44791 | MONITORED FENCE REMOVAL AND INSTALL AMCCORMICK 8-18-22
18026764800 | INSTALL COMM BUILDING | [5 empty] | 132078.26 | 156664.9991 | -24586.7391 |  |  |  | 44742 | 72003 INSTALLED RTU BUILDING AND TRANSDUCERS
18026772300 | CONVERT FROM GMB TO CAB ACCT | [5 empty] | 725.53 | 2583.054 | -1857.524 |  |  |  | 44830 | CONVERTED GMB TO CAB ACCOUNT INSTALLED NEW 800 METER ON 5# FPCC DASH 9-26-2 2
18026778900 | INSTALL ERX & RTU BUILDING | [5 empty] | 113154.12 | 156098.7133 | -42944.5933 |  |  |  | 44546 | CC# 13231. 2/25/21 DSASH WORKED ON PAPERWORK OFF SITE. 2/26/21 DSASH EQUIPMENT INSTALLED ON 2/25/21 BY ACP AND DANNY ASH PAPERWORK COMPLETED ON 12/16/2021 BY CYNTHIA FARIS JOB CLOSEOUT DELAYED WAITING ON INFORMATION AND CORRECT ISO SKETCH UNDERRUN EXPLANATION: THE CONTRACT COSTS WERE SIGNIFICANT LESS THAT THE I&C TEAM HAD ORIGINALLY ESTIMATED.
18026781701 | INSTALL MONITOR/CONTROL REGS | [5 empty] | 141447.12 | 99301.7623 | 42145.3577 |  |  |  | 44369 | CCC TICKET 27187 CCC #27342 CCC #27472 CCC #27636 CCC #27973 CCC TICKET NOT REQUIRED NOT AT STATION 8/4/21
18026781800 | ABANDON REGULATORS | [5 empty] | 0 | 56.3894 | -56.3894 |  |  |  | 44369
18026793901 | INSTALL 4,123' - 2" PMMP | [5 empty] | 649583.26 | 506341.5777 | 143241.6823 |  |  |  | 45267
18026794000 | RETIRE 4748'-2"/3"/4"/6"P-BSLP | [5 empty] | 110 | 61.2976 | 48.7024 |  |  |  | 45267
18026794401 | INSTALL 4400'-2"/4"PMMP MAIN | [5 empty] | 1250897.35 | 1022806.1278 | 228091.2222 |  |  |  | 45804
18026794500 | RETIRE 2450' - CS/BSMP | [5 empty] | 589.7 | 118.4933 | 471.2067 |  |  |  | #N/A
19026855301 | INSTALL RTU AND BUILDING | [5 empty] | 186001.86 | 182784.6097 | 3217.2503 |  |  |  | 44637 | INSTALLED NEW RTU DASH 3-17-22
19026855400 | RETIRE OLD RTU EQUIPMENT | [5 empty] | 5219.78 | 69.4128 | 5150.3672 |  |  |  | 44637 | INSTALLED NEW COMM BUILDING AND RTU DASH 3-17-22
19026860400 | INSTALLING I&C EQUIPMENT | [5 empty] | 174669.84 | 222748.2628 | -48078.4228 |  |  |  | 44795 | CCC #27973 CCC #28142 CCC # 28275 CCC #28378 CCC #28665 CCC TICKET NOT REQUIRED NOT AT STATION 8/4/21
19026860500 | RETIRE I&C EQUIPMENT | [5 empty] | 511.34 | 84.9756 | 426.3644 |  |  |  | 44795 | CC# 78206
19026867100 | INSTALL VRG CONTROLLER | [5 empty] | 15917.94 | 15490.7518 | 427.1882 |  |  |  | 44649 | CCC 59916 CCC # 59916 INSTALLED NEW VRG CONTROLLERS DASH 3-29-22
19026867200 | RETIRE CURRENT CONTROLLERS | [5 empty] | 1038.8 | 64.4897 | 974.3103 |  |  |  | 44649 | CCC # INSTALLED NEW VRG'S RETIRED EXSISTING CONTROLLERS DASH 3-29-22
19026889700 | INSTALL METER AND SETTING | [5 empty] | 54709.93 | 55012.1889 | -302.2589 |  |  |  | 44692 | CCC #30162 CCC # 42745 CCC # 42908 CCC # 43108 CLENANER INSTALLED ON 10-29-2022 ALONG WITH PAPERWORK CO BY JOSH MULLINS ON 5-10-22
19026889800 | RETIRE METER AND SETTING | [5 empty] | 612.86 | 76.3408 | 536.5192 |  |  |  | 44692
19026913000 | INSTALL 730'-2"PMMP | [5 empty] | 242981.39 | 230850.9729 | 12130.4171 |  |  |  | 45377
19026913100 | RETIRE 705'-2/3/4" BS/PL/CSLP | [5 empty] | 354.92 | 239.7645 | 115.1555 |  |  |  | #N/A
20026918001 | INSTALL ELECTRONICS | [5 empty] | 203885.41 | 78849.9064 | 125035.5036 |  |  |  | 44425 | CC# 31091 CC# 34924 CC# 21685. 01-03-22 DSASH CC# 21685. 01-03-22 DSASH OVERRUN EXPLANATION: ASSUMED WE WOULD USE THE OLD BLOCK BUILDING BUT FOND T HAT IT WAS LEAKING SO HAD TO REPLACE WITH A NEW BUILDING.
20026918102 | INSTALL ELECTRONICS | [5 empty] | 173384.28 | 264607.6595 | -91223.3795 |  |  |  | 44501 | NO CC NEEDED ONSITE MEETING DID NOT GO INSIDE BUILDING GES: UNDERRUN EXPLANATION: JOB UNDERRAN BECAUSE SCADA BUILDING WAS PLACED O N ANOTHER JOB ORDER THAT IS PLANNED FOR 2022 CONSTRUCTION. ADDITIONALLY, ASSUMED THERE WAS PRESSURE CONTROL WHEN ESTIMATED AND THERE W AS NOT.
20026922500 | INSTALL ELECTRONICS | [5 empty] | 238947.63 | 123804 | 115143.63 |  |  |  | 44867 | CCC # 40652 NOT ON SITE CC# 47218. 12/01/21 DSASH CCC # 47218 CCC # 47356 CC# 47727. 12/07/21 DSASH
20026922600 | RETIRE ELECTRONICS | [5 empty] | 144.18 | 115.4611 | 28.7189 |  |  |  | 44867
20026930800 | UPGRADE ELECTRONICS | [5 empty] | 4644.07 | 3038 | 1606.07 |  |  |  | 44383 | REPLACED EFC NON SCADA MONITORED GMB ACCOUNT GCCC TICKET NOT REQUIRED
20026930900 | UPGRADE ELECTRONICS | [5 empty] | 3329.3 | 3038 | 291.3 |  |  |  | 44823 | RETIRED MINI AT INSTALLED NEW EC350 ON CELL MODEM DASH 9-19-22
20026936301 | INSTALL 1192'-4" PMMP | [5 empty] | 290217.29 | 375696.2322 | -85478.9422 |  |  |  | 44292 | UNDERRUN EXPLANATION: SIGNIFICANTLY LESS HARD SURFACE REPAIRS AND BACKFILL REQUIRED THAN ESTIMATED. ALSO NOFLAGGING ON OVERTIME WAS REQUIRED. THE OVER HEAD EFFECT OF THESE REDUCTIONS ALSO CONTRIBUTED TO THE UNDERRUN.
20026936400 | RETIRE 1228'-3"&4"BS/CS/P-LP | [5 empty] | 1214.98 | 400.0304 | 814.9496 |  |  |  | 44292
20026936600 | ABANDON ~10'-4" P-LP | [5 empty] | 167.31 | 173.6495 | -6.3395 |  |  |  | 44209
20026941600 | INSTALL I&C EQUIPMENT | [5 empty] | 11237.56 | 16155.4774 | -4917.9174 |  |  |  | 44540 | CC# 30132. ERX INSTALLED BY DANNY ASH AND JOSH MULLINS PAPERWORK COMPLETED BY CYNTHIA FARIS PAPERWORK ON HOLD AWAITING CORRECT ISO SKETCH
20026941700 | RETIRE GAUGE | [5 empty] | 0 | 91.4991 | -91.4991 |  |  |  | 44540 | ERX INSTALLED AND PAPER RECORDING GAUGE RETIRED BY DANNY ASH AND JOSH MULLINS PAPERWORK COMPLETED BY CYNTHIA FARIS PAPERWORK ON HOLD AWAITING CORRECT ISO SKETCH
20026941800 | INSTALL I&C EQUIPMENT | [5 empty] | 12411.86 | 16155.4774 | -3743.6174 |  |  |  | 44393 | GCC 13064 EQUIPMENT INSTALLED BY JOSH MULLINS ON 2/24/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/16/21 DELAY IN JOB COMPLETION WAITING ON PE APPROVAL FOR 584 JOB ORDER AND ISO SKETCH UPDATE GCCC TICKET NOT REQUIRED ON 7/16/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026941900 | RETIRE GAUGE | [5 empty] | 0 | 91.4991 | -91.4991 |  |  |  | 44393 | GAUGE RETIRE BY JOSH MULLINS ON 2/24/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/16/21 DELAY COMPLETING JOB ORDER DUE TO ISO SKETCH REVISION& PE APPROVAL GCCC TICKET NOT REQUIRED ON 7/16/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026942100 | INSTALL I&C EQUIPMENT | [5 empty] | 16401.86 | 16155.4774 | 246.3826 |  |  |  | 44389 | CCC #29962 CCC #30339 INSTALLED ERX, RV50 MODEM, BATTERY AND SUPER SOLAR KIT GCCC TICKET NOT REQUIRED ON 7/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026942200 | RETIRE GAUGE | [5 empty] | 0 | 91.4991 | -91.4991 |  |  |  | 44389 | RETIRED PAPER RECORDING GAUGE AND INSTALLED ERX WORK COMPLETED ON 909 JOB ORDER WITH GCCC TICKET NUMBER 29962 GCCC TICKET NOT REQUIRED ON 7/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026942300 | INSTALL I&C EQUIPMENT | [5 empty] | 11644.22 | 16155.4774 | -4511.2574 |  |  |  | 44547 | INSTALLED ERX DELAY IN SENDING JOB TO CLOSE OUT WAITING ON INFORMATION PE REVIEW/APPROVAL AND ISO SKETCH CFARIS
20026942400 | RETIRE GAUGE | [5 empty] | 1032.4 | 91.4991 | 940.9009 |  |  |  | 44547 | REPLACED MECHANICAL RECORDING GAUGE WITH ERX DELAY IN SENDING TO CLOSEOUT DUE TO WAITING ON INFORMATION, PE REVIEW/APPROVAL AND CORRECT ISO SKETCH CFARIS
20026942700 | INSTALL I&C EQUIPMENT | [5 empty] | 15613 | 16155.4774 | -542.4774 |  |  |  | 44540 | CCC # 28876 CC#29408. 6/28/21 DSASH CCC # 32222 INITIAL COMMISSIONING BY SHANE GIORDANO PAPERWORK COMPLETED BY CYNTHIA FARIS ON 12/10/21 PAPERWORK ON HOLD AWAITING ISO SKETCH
20026942800 | RETIRE GAUGE | [5 empty] | 0 | 91.4991 | -91.4991 |  |  |  | 44540 | PAPERWORK COMPLETION ON HOLD AWAITING ISO SKETCH
20026952500 | REPLACE VALVE C-16 | [5 empty] | 47582.37 | 56236.611 | -8654.241 |  |  |  | 44964
20026952600 | RETIRE VALVE C-16 | [5 empty] | 5789.59 | 952.0929 | 4837.4971 |  |  |  | 44964
20026967900 | INSTALL 315' 2" PMIP | [5 empty] | 71403.61 | 31888.6353 | 39514.9747 |  |  |  | 44225 | TWALKER/KY 02-23-21: ISSUED BACK ORDER CANCEL #48444 FOR JOB OVERRUN EXPLANATION: 150 SQUARE FEET OF 6&2 WAS ESTIMATED AND 990 SQ FEET W AS REQUIRED LEADING TO AN INCREASE IN CONTRACTOR COSTS AND OVERHEADS.
20026970100 | INSTALL 11400'-2"/4" PM/CSIP | [5 empty] | 1042042.95 | 1176644.8813 | -134601.9313 |  |  |  | 44512
20026970200 | RETIRE 10250'-2"/3"/4" BS/CSIP | [5 empty] | 272.31 | 278.4699 | -6.1599 |  |  |  | 44512
20026977301 | INSTALL 12,100 OF 2"PMMP MAIN | [5 empty] | 1937357.64 | 1697987.4343 | 239370.2057 |  |  |  | 44501
20026977400 | RETIRE 10,510'OF 4"/6"BSLP | [5 empty] | 1237.75 | 90.4074 | 1147.3426 |  |  |  | 44501
20026977500 | INSTALL 4335'-4" & 6" PMLP | [5 empty] | 1014309.73 | 818557.1832 | 195752.5468 |  |  |  | 44810 | TWALKER/KY 01-24-23: PROJECT OVER RUN COST DUE TO ADDITIONAL PAVING/HARD SURFACE REPAIR RESULTED IN $100,000 HIGHER CONTRACT COST, MATERIAL COST WERE $46,000 HIGHER THAN EST. ADN SEGA $68,000 HIGHER THAN EST.
20026977600 | RETIRE 4766'-2"/3"/4"/6" BSLP | [5 empty] | 11052.89 | 476.2758 | 10576.6142 |  |  |  | 44810
20026978100 | INSTALL 8620'- 2" PMMP | [5 empty] | 2117372.66 | 1435185.1923 | 682187.4677 |  |  |  | 45257
20026978200 | RETIRE 8983' LP - 2520' BS | [5 empty] | 513.02 | 476.2758 | 36.7442 |  |  |  | 45257
20026982200 | INSTALL 5'-4"PMMP & 4'-4"CS | [5 empty] | 40958.2 | 42642.7946 | -1684.5946 |  |  |  | 44355
20026982300 | ABANDON 5' - 4" CSMP | [5 empty] | 10.78 | 183.2963 | -172.5163 |  |  |  | 44355
20026982500 | INSTALL 120' - 4" PMLP | [5 empty] | 38925.35 | 30468.341 | 8457.009 |  |  |  | 44281
20026983300 | INSTALL 6,600'-2"/4" PMMP | [5 empty] | 2015230.05 | 1529743.322 | 485486.728 |  |  |  | 45645
20026983400 | RETIRE 5374'-4" BSLP/CSLP | [5 empty] | 92.88 | 119.4953 | -26.6153 |  |  |  | #N/A
20026983500 | INSTALL 1670' - 2" PMMP | [5 empty] | 426217.2 | 347784.1168 | 78433.0832 |  |  |  | 45166
20026983600 | ABANDON 1667'-2/3/4" PMLP/BSLP | [5 empty] | 290.24 | 360.3823 | -70.1423 |  |  |  | 45166
20026984500 | REPLACE IP OUTLET BLOCK VALVE | [5 empty] | 1480.71 | 2174.0477 | -693.3377 |  |  |  | 44706 | NOT ON SITE REPLACED INLET AND OUTLET IP RUN BLOCK VALVES SGIORDANO JMULLINS CO PAPERWORK 06132022
20026984600 | REPLACE IP OUTLET BLOCK VALVE | [5 empty] | 2409.31 | 50 | 2359.31 |  |  |  | 44706 | CCC 68181 REPLACED INLET AND OUTLET IP BLOCK VALVS SGIORDANO JMULLINS CO PAPERWORK 06132022
20026988800 | INSTALL 210'-2" PMLP | [5 empty] | 21827.5 | 42176.37 | -20348.87 |  |  |  | 44265
20026992200 | INSTALL 100'-2" PMIP | [5 empty] | 8539.31 | 11276.4442 | -2737.1342 |  |  |  | 44270
21026104900 | EMER INSTALL 5'-3" PMIP | [5 empty] | 4758.29 | 5995.5434 | -1237.2534 |  |  |  | 44280 | SEE PAPER PACKET FOR INFO
21026105000 | EMER RETIRE 5'-3" P-IP | [5 empty] | 3758.23 | 750.8346 | 3007.3954 |  |  |  | 44280 | SEE PAPER COPIES FOR TEST INFO SEE PAPER COPIES/ PIPE EXPOSURE FORM WILL NOT ACCEPT THE CORRECT MAIN NUMBER NOT LETTING ME COMPLETE THIS ORDER
21026105700 | EMER INST 360'-2" PMIP D244304 | [5 empty] | 109722.07 | 25736.2708 | 83985.7992 |  |  |  | 44264 | INSTALLED 345' OF 2" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7.5 P SIG OVERRUN EXPLANATION: THE SIGNIFICANT COST DIFFERENCE RESULTED FROM PAVING REQUIREMENTS. THE PROJECT WAS NOT ESTIMATED FOR CONTRACT RESTORATION. PAVE TICKETS WERE SUBMITTED TO REPAIR ROAD AND PARKING LOT AREA
21026105800 | EMER RETIRE 350'-3"/2" CSIP | [5 empty] | 27035.38 | 1114.7918 | 25920.5882 |  |  |  | 44264 | FOUND CRACKED MAIN RETIRED 345' OF 3" ST AND INSTALLED 345' OF NEW 2" PL TO STOP LEAKAGE TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7.5 PSIG
21026106400 | RETIRE PAPER RECORD GAUGE | [5 empty] | 92.38 | 341.3226 | -248.9426 |  |  |  | 44547 | TICKET 13749
21026109000 | EMER - INSTALL 10'-4" PMIP | [5 empty] | 2349.57 | 8970.0544 | -6620.4844 |  |  |  | 44273 | INSTALLED 5' OF NEW 4" PL MAIN TO REPAIR CRACKED PIPE TESTED 90 PSIG 1 HR
21026109100 | EMER - RETIRE 10'-4" CSIP | [5 empty] | 5925.07 | 556.9397 | 5368.1303 |  |  |  | 44273 | RETIRE 5' OF 4" CS MAIN DUE TO SPLIT MAIN SOAP TESTED OP 7.5 PSIG
21026110200 | EMER - INSTALL 5'-3" PMIP | [5 empty] | 880.36 | 7868.6589 | -6988.2989 |  |  |  | 44307 | INSTALLED 5' OF 3" PLASTIC. TESTED AT 90PSIG FOR 1HR.
21026110300 | EMER - RETIRE 5'-3" PIP | [5 empty] | 7215.11 | 441.8134 | 6773.2966 |  |  |  | 44307 | RETIRED 5' OF 3" PLASTIC DUE TO PAC CLAMPS LEAKING.
21026113401 | INSTALL 100'-2" PMMP | [5 empty] | 21410.67 | 11198.5401 | 10212.1299 |  |  |  | 44305
21026115100 | INSTALL 1'-4" PMLP | [5 empty] | 0 | 149.4587 | -149.4587 |  |  |  | 44292
21026115800 | EMER - INSTALL 138'-4" PM/CSIP | [5 empty] | 2573.82 | 10752.5629 | -8178.7429 |  |  |  | 44306 | INSTALLED 134' OF 4" PL IP TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7.5 PSIG
21026115900 | EMER - RETIRE 134'-4" CSIP | [5 empty] | 9847.31 | 1105.3087 | 8742.0013 |  |  |  | 44306 | RETIRED 134' OF 4" CS DUE MAIN EXPOSED OUT OF GROUND AND DETERIORATION
21026116900 | INSTALL 200'-2" PMLP | [5 empty] | 24792.54 | 39229.3021 | -14436.7621 |  |  |  | 44383
21026117300 | EMER - RETIRE 2'-4" P-LP | [5 empty] | 183.09 | 441.8134 | -258.7234 |  |  |  | 44307 | RETIRE 2' OF 4" PL DUE TO DAMAGE
21026120600 | RETIRE REG STATION WITH AMRP | [5 empty] | 1058.49 | 9924.8698 | -8866.3798 |  |  |  | 44910 | CC# 6407 RETIRED REG STATION DASH 12-15-2022
21026121500 | INSTALL 160'-2" PMIP | [5 empty] | 37719.27 | 21640.9206 | 16078.3494 |  |  |  | 44432
21026121600 | INSTALL 100'-2" PMIP | [5 empty] | 16499.56 | 13861.3812 | 2638.1788 |  |  |  | 44361
21026122300 | INSTALL 100'-2" PMMP | [5 empty] | 26947.59 | 25260.7035 | 1686.8865 |  |  |  | 44372
21026123800 | INSTALL 160'-4" CSLP/PMLP | [5 empty] | 86016.2 | 161313.4069 | -75297.2069 |  |  |  | 44417 | UNDERRUN EXPLANATION: SIGNIFICANTLY LESS HARD SURFACE RESTORATION AND BACKFILL REQUIRED THAN ESTIMATED KYTC REQUIRED RELOCATION AND TOLD US NOT TO WORRY ABOUT THE MILL & OVERLAY THAT THEY WOULD DO THAT WHEN THEY COMPLETED THEIR PART OF THE PROJECT, THIS RESULTED IN A SIGNIFICANT AMOUNT OF THE COST VARIATION
21026125300 | RETIRE 180'-4" BSLP | [5 empty] | 0 | 282.1429 | -282.1429 |  |  |  | 44415 | COMMITT DATE WAS PUSHED OUT TILL END OF AUG.2021
21026127800 | INSTALL 500'-2" PMMP | [5 empty] | 47089.22 | 43810.3768 | 3278.8432 |  |  |  | 44399
21026128500 | NSP - INSTALL 150'-2" PMLP | [5 empty] | 10156.16 | 16760.5972 | -6604.4372 |  |  |  | 44362 | INSTALLED 150' 2"P. PRESSURE TESTED 90LBS 1HR. SOAP TESTED 2" EF COUPLING AT OP. PRESS. (11 IWC) 15MIN. PRESS. TEST 2X1 MONITORING TEE 90LBS 15MIN. SOAP TESTED MONITORING TEE END CAP OP. PRESS (11 IWC) 15MIN.
21026129800 | INSTALL 200'-2" PMMP | [5 empty] | 25563.52 | 21853.3833 | 3710.1367 |  |  |  | 44455
21026130200 | EMER-INSTALL 5'-2" PMIP/CSIP | [5 empty] | 7558.85 | 6178.4541 | 1380.3959 |  |  |  | 45016
21026130300 | EMER-RETIRE 5'-2" BSIP | [5 empty] | 230.72 | 410.7144 | -179.9944 |  |  |  | 45016
21026130400 | INSTALL 25,111'-2",4" PMMP | [5 empty] | 4360387.57 | 3707985.656 | 652401.914 |  |  |  | 45265
21026130500 | RETIRE 25,000' OF BSLP MAINS | [5 empty] | 1741.22 | 485.0228 | 1256.1972 |  |  |  | 45265
21026131300 | RETIRE EFC UNIT | [5 empty] | 0 | 74.8797 | -74.8797 |  |  |  | 44383 | REPLACED EFC
21026132100 | INSTALL 600'-4" PMMP | [5 empty] | 75178.06 | 159985.8979 | -84807.8379 |  |  |  | 44470 | INSTALLED 573' OF 4" PL MP AND 9' OF 2" PL MP TESTED 90 PSIG 2 HRS SOAP TESTED FINAL CONN OP 44 PSIG UNDERRUN EXPLANATION: A SIGNIFICANT UNIT OF COST WAS THE PLANNED ROCK BORE BUT THE CREW WAS ABLE TO AVOID THE NEED FOR A ROCK BORE, THE JOB DURATION ESTIMATE TOOL ALSO PLANNED FOR 120 HOURS OF LABOR AND THE CREW COMPLETED THE JOB IN 60 HOURS AND SOME CREW MEMBERS WERE NOT NEEDED THE ENTIRE DURATION OF THE JOB.
21026132200 | RETIRE 450'-4" P-MP | [5 empty] | 212.81 | 875.427 | -662.617 |  |  |  | 44470 | RETIRED 487' OF 4" PL MP
21026133300 | INSTALL 200'-2" PMIP | [5 empty] | 19749.69 | 14590.9404 | 5158.7496 |  |  |  | 44441
21026133900 | INSTALL VRG CONTROLER | [5 empty] | 0 | 6187.1439 | -6187.1439 |  |  |  | 44867
21026134000 | RETIRE DAMAGED CONTROLLER | [5 empty] | 0 | 220.9908 | -220.9908 |  |  |  | 44867
21026139100 | EMER - INSTALL 5'-4" PMMP | [5 empty] | 2800.66 | 6493.0322 | -3692.3722 |  |  |  | 44468 | INSTALLED MAIN ON TESTED 90 PSIG 1 HOUR SOAP TESTED FINAL CONN OP 44 PSIG
21026139200 | EMER - RETIRE 5'-4" P-MP | [5 empty] | 5590.11 | 743.2708 | 4846.8392 |  |  |  | 44468
21026139800 | INSTALL 100'-2" PMIP | [5 empty] | 19936.66 | 27338.1249 | -7401.4649 |  |  |  | 44470
21026140100 | INSTALL 52'-4"/6" PMIP/CSIP | [5 empty] | 67346.12 | 83495.319 | -16149.199 |  |  |  | 44712
21026140200 | RETIRE 47'-4"/6" BSIP/CSIP | [5 empty] | 207.25 | 500 | -292.75 |  |  |  | 44712
21026143700 | INSTALL 4'-4" PMLP | [5 empty] | 478.5 | 3297.2047 | -2818.7047 |  |  |  | 44548 | INSTALLED 4' OF 4" PL LP MAIN LINE TESTED 90 PSIG 1 HOUR SOAP TESTED FINAL CONN OP 10" WC
21026143800 | RETIRE 4'-4" PMLP | [5 empty] | 44.74 | 295.4309 | -250.6909 |  |  |  | 44548 | RETIRED MAIN DUE TO STEEL SADDLE TEE BIENG ON PL PIPE INSTALLED NEW SECTION OF PIPE
21026144600 | INSTALL 12" SS | [5 empty] | 25613.83 | 13660.0322 | 11953.7978 |  |  |  | 44550 | INSTALLED 12" SS TO STOPPLE AND KILL 12" MAIN
21026144700 | RETIRE 1273'-6/12/16" CS/BSHP | [5 empty] | 167.43 | 388.1295 | -220.6995 |  |  |  | 44550 | RETIRE 1207' OF 12" BS HP TO AK STEEL SOAP TESTED OP 113 PSIG
21026146300 | INSTALL 4'-4" PMLP | [5 empty] | 424.36 | 2206.8953 | -1782.5353 |  |  |  | 44481 | INSTALLED 4' OF 4" PLASTIC MAIN. PRESSURE TESTED 90LBS FOR 1HR.
21026146400 | RETIRE 4'-4" P-LP | [5 empty] | 39.69 | 197.4141 | -157.7241 |  |  |  | 44481
21026146800 | RETIRE GMB #44535-AK STEEL | [5 empty] | 3852.12 | 2893.6188 | 958.5012 |  |  |  | 44494 | ALL FACILITIES REMOVED FROM AK STEEL BY MATT RYAN AND SHANE GIORDANO MAINLINE/SERVICE LINE ABANDONED ON 10/18/2021 BY CONSTRUCTION SERVICES M&R PAPERWORK COMPLETED BY CYNTHIA FARIS ON 10/25/2021
21026149000 | INSTALL 75'-2" PMIP | [5 empty] | 765.35 | 4287.763 | -3522.413 |  |  |  | 44550 | INSTALLED 66' OF 2" PL TESTED 90 PSIG 0005 MIN SOAP TESTED CAP OP 8 PSIG
21026150000 | EMER - INSTALL 14'-4" PMLP | [5 empty] | 72137.82 | 3163.1338 | 68974.6862 |  |  |  | 44552 | INSTALLED 16' OF 4" PL W/ 4 90'S TO GO ABOVE 24" CLAY TILE SEWER TESTED 90 PSIG 1 HR OVERRUN EXPLANATION: CROSSBORE FOUND- CAMERA CREW NEEDED AND ADDITIONAL HOURS NEEDED TO REMEDIATE THE CROSS-BORE ISSUE 2 MAINTENCE JOBS AND 1 PAVE JOB CHARGED BACK TO CAPITAL JOB AND WERE NOT ACCOUNTED FOR IN ORIGINAL PROPOSED COST, $26K IN FLAGGING AND RESTORATION CHARGED TO MAINTENCE JOBS AND $14K IN CAMERA WORK BY CONTRACTOR
21026150100 | EMER - RETIRE 6'-4" P-LP | [5 empty] | 669.23 | 335.9749 | 333.2551 |  |  |  | 44552 | REMOVED 4" PL FROM SEWER LINE CROSS BORE
21026150600 | EMER - INSTALL 5'-2" PMMP | [5 empty] | 378.77 | 1696.2756 | -1317.5056 |  |  |  | 44516
21026150700 | EMER - RETIRE 5'-2" PMP | [5 empty] | 64.43 | 335.9749 | -271.5449 |  |  |  | 44517
21026153400 | EMER - INSTALL 6'-4" PMIP | [5 empty] | 7455.58 | 4080.2324 | 3375.3476 |  |  |  | 44552
21026153500 | EMER - RETIRE 6'-4" PMIP | [5 empty] | 101.71 | 518.618 | -416.908 |  |  |  | 44552
21026154000 | INSTALL 160'-2" PMMP | [5 empty] | 28534.77 | 33091.7151 | -4556.9451 |  |  |  | 44606
21026154600 | RETIRE R-1354 | [5 empty] | 8911.51 | 163.2711 | 8748.2389 |  |  |  | 45256
21026154800 | RETIRE 35'-3" CSMP | [5 empty] | 27.2 | 485.0228 | -457.8228 |  |  |  | 45265
21026155700 | INSTALL FENCE - SCADA BUILDING | [5 empty] | 7557.57 | 15936.4497 | -8378.8797 |  |  |  | 44795
21026156500 | INSTALL 140'-2"/4" PMMP | [5 empty] | 2096.07 | 3669.7405 | -1573.6705 |  |  |  | 44551
21026157800 | INSTALL 5'-4" PMLP | [5 empty] | 2758.28 | 4114.4273 | -1356.1473 |  |  |  | 44564
21026157900 | RETIRE 5'-4" PMLP | [5 empty] | 485.31 | 72.8047 | 412.5053 |  |  |  | 44564
21026993200 | EMER- INSTALL 5'-4" PMMP | [5 empty] | 3260.67 | 4003.4824 | -742.8124 |  |  |  | 44204 | INSTALLED 4' OF 4" P. PRESSURE TESTED AT 90LBS FOR 1HR. SOAP TESTED (2) 4" EF COUPLINGS AT OPERATING PRESSURE (11PSIG).
21026993300 | EMER- RETIRE 5'-4" P-MP | [5 empty] | 184.74 | 647.029 | -462.289 |  |  |  | 44204 | REMOVED 4' OF DAMAGED 4" P
21026993401 | INSTALL 10750'-2"/4"PMMP MAIN | [5 empty] | 2072101.63 | 1880428.7756 | 191672.8544 |  |  |  | 44882
21026993500 | RETIRE 13650' OF 4"/6"BSLP | [5 empty] | 80 | 86.5975 | -6.5975 |  |  |  | 44882
21026993600 | EMER INST 40'-4" PMLP | [5 empty] | 772.98 | 13260.7401 | -12487.7601 |  |  |  | 44204 | INSTALLED 28' OF 4" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 10" WC
21026993700 | EMER RET 40'-4" BSLP/CSLP/P-LP | [5 empty] | 372.17 | 1322.2973 | -950.1273 |  |  |  | 44204 | RETIRED 28' OF 4" STEEL MAIN AND 3 WAY TEE
21026999201 | RETIRE 3"PIP SERVICE LINE | [5 empty] | 14749.54 | 6359.645 | 8389.895 |  |  |  | 45103 | STEP 3 NEEDS INVESTIGATED STEP 3 NEEDS STATE PERMIT STEP 3 NEEDS STATE PERMIT THIS IS A PAPER ABN. THIS LINE IS AN ACTIVE LINE BUT THEY ARE NOT OUR CUSTOMER. THEY ARE USING NATURAL ENERGY. OUR ASSETS ARE NOT WITHIN THE PROPERTY. U131418 J. PARKS 4-24-23
22026159700 | EMER - INSTALL 4'-4" PMLP | [5 empty] | 1914.95 | 4455.398 | -2540.448 |  |  |  | 44585
22026159800 | EMER - RETIRE 4'-4" P-LP | [5 empty] | 6434.1 | 448.5353 | 5985.5647 |  |  |  | 44581 | RETIRED 4' OF 4" PL LP TO REMOVED STEEL SADDLE FROM PLASTIC MAIN
22026159900 | EMER - INSTALL 2'-2" PMLP | [5 empty] | 2408.32 | 2367.5988 | 40.7212 |  |  |  | 44595
22026160000 | EMER - RETIRE 2'2"P-LP D244381 | [5 empty] | 487.19 | 506.8997 | -19.7097 |  |  |  | 44599
22026160300 | RETIRED ELECTRONICS | [5 empty] | 422.53 | 75.9523 | 346.5777 |  |  |  | 44425
22026169000 | MAVITY HVAC UPGRADE | [5 empty] | 5678.5 | 15264.0767 | -9585.5767 |  |  |  | 44778
22026172301 | INSTALL 5000' OF 2"PMMP MAIN | [5 empty] | 1225170.53 | 1183513.1452 | 41657.3848 |  |  |  | 45408
22026172400 | RETIRE 4792'-2/4/8" PL/CS/BSLP | [5 empty] | 220 | 709.5359 | -489.5359 |  |  |  | #N/A
22026174900 | INSTALL 50'-2" PMMP | [5 empty] | 36910.2 | 30717.8249 | 6192.3751 |  |  |  | 44692
22026175800 | EMER - INSTALL 120'-3" PMLP | [5 empty] | 32123.93 | 12124.3189 | 19999.6111 |  |  |  | 44656 | INSTALLED 120' OF 3" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 10" W C
22026175900 | EMER - RETIRE 121'-3" P-LP | [5 empty] | 931.56 | 373.4562 | 558.1038 |  |  |  | 44656 | RETIRE 121' OF 3" PL DUE TO WATER AND STEEL FITTINGS ON PL MAIN
22026177000 | EMER - INSTALL 2'-4" PMIP | [5 empty] | 2292.91 | 4197.8249 | -1904.9149 |  |  |  | 44652
22026177100 | EMER - RETIRE 2'-4" P-IP | [5 empty] | 2387.49 | 310.9595 | 2076.5305 |  |  |  | 44652
22026180500 | INSTALL 160'-2" PMIP | [5 empty] | 22724.8 | 36664.9938 | -13940.1938 |  |  |  | 44755
22026180700 | EMER - INSTALL 3'-3" PMIP | [5 empty] | 6701.19 | 4036.7887 | 2664.4013 |  |  |  | 45163
22026180800 | EMER - RETIRE 3'-3" PMIP | [5 empty] | 61.4 | 418.4749 | -357.0749 |  |  |  | 45163
22026182300 | RETIRE PAPER RECORD GAUGE | [5 empty] | 144.38 | 329.4627 | -185.0827 |  |  |  | 44671
22026184500 | INSTALL 250'-4" PMLP/CSLP | [5 empty] | 63976.36 | 60316.4006 | 3659.9594 |  |  |  | 44783
22026190600 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 817.09 | 4801.1928 | -3984.1028 |  |  |  | 44735 | CCC 71454 RETIRED ERX AND INSTALLED NEW MIWI350
22026191000 | RETIRED ELECTRONICS EQUIPMENT | [5 empty] | 261.55 | 124.8731 | 136.6769 |  |  |  | 44735 | CCC 71454 RETIRE ERX AND INSTALLED NEW MIWI 350
22026191700 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 10605.54 | 4801.1928 | 5804.3472 |  |  |  | 44785 | UPGRADED ERX TO MIWI JOSH MULLINS
22026191800 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 20.04 | 124.8731 | -104.8331 |  |  |  | 44785
22026191900 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 744.93 | 4801.1928 | -4056.2628 |  |  |  | 44735 | CCC 71454
22026192000 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 922.45 | 124.8731 | 797.5769 |  |  |  | 44735 | CCC 71454
22026192100 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 2317.01 | 4801.1928 | -2484.1828 |  |  |  | 44788 | CCC 75023
22026192200 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 884.51 | 124.8731 | 759.6369 |  |  |  | 44788 | CCC 75023 UPGRADED ERX TO MIWI J.MULLINS
22026196200 | EMER - INSTALL 1'-2" PMMP | [5 empty] | 6510.29 | 2866.3857 | 3643.9043 |  |  |  | 44727 | INSTALLED 1' OF 2" PL DUE TO FACILTY DAMAGE TESTED 90 PSIG 0005 MIN SOAP TE STED FINAL CONN OP 42 PSIG REVISED EXECUTE COMMENTS: INSTALLED 1' OF 2" PL DUE TO FACILITY DAMAGE TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 42 PSIG/MCOLLETT 7/8/22
22026196300 | EMER - RETIRE 1'-2" P-MP | [5 empty] | 1254.11 | 497.9695 | 756.1405 |  |  |  | 44727 | RETIRED 1' OF 2" PL MP DUE TO FACILITY DAMAGE SOAP TESTED OP TO VERIFY GAS SHUTOFF
22026198200 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5532.75 | 4801.1928 | 731.5572 |  |  |  | 44784 | CC 76915 UPGRADDED ERX TO MIWI 350
22026198300 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 467.24 | 124.8731 | 342.3669 |  |  |  | 44784 | CC 76915 UPDATTED ERX TO MIWI 350
22026198700 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 6293.17 | 4801.1928 | 1491.9772 |  |  |  | 44817 | CC 497 CC 497 REPLACED OLD ERX WITH NEW MIWI350 SGIORDANO 9-13-2022
22026198800 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 1014.14 | 124.8731 | 889.2669 |  |  |  | 44817 | CC 497 REPLACED ERX WITH NEW MIWI350 SGIORDANO 9-13-2022
22026199900 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 6476.38 | 4801.1928 | 1675.1872 |  |  |  | 44819 | CC 118 INSTALLED NEW MIWI350 RETIRED OLD ERX SGIORDANO 9-15-22
22026200200 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 1400.9 | 124.8731 | 1276.0269 |  |  |  | 44819 | CC 118 INSTALLED NEW MIWI350 SGIORDANO 9-15-22 C 2820
22026200300 | EMER - INSTALL 5'-2" PMIP | [5 empty] | 9101.9 | 2610.0199 | 6491.8801 |  |  |  | 44719 | REPLACED 5' SECTION OF 2" PMMP. TESTED MAIN AT 90 PSIG FOR 1 HOUR AND TEST WAS GOOD. TESTED 2X1 EF TEES AT 90 PSIG FOR 5 MINS AND SOAP TESTED THE CAPS AND DEAD ENDS AT OP FOR 5 MINS. ALL TEST ARE GOOD.
22026200900 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 6137.4 | 4801.1928 | 1336.2072 |  |  |  | 44818 | CC 632 UPGRADED TO MIWI 350 PAPERWORK DONE BY J.MULLINS
22026201000 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 485.58 | 124.8731 | 360.7069 |  |  |  | 44818 | CC 632 UPGRADED TO MIWI 350 PAPERWORK DONE BY J.MULLINS
22026205200 | INSTALL 115'-2" PMMP | [5 empty] | 21273.79 | 42423.5179 | -21149.7279 |  |  |  | 44840 | CJ HUGHES CASEY PACK'S CREW INSTALLED 103' 2" STEEL/PLASTIC MAIN LINE EXTEN TION AND A NEW 1" PLASTIC SERVICE TO 1519 MAPLE ST 10/6/22 MBLANKE U123965
22026205600 | INSTALL 1200'-2" PMMP | [5 empty] | 162971.11 | 61578.4138 | 101392.6962 |  |  |  | 44838 | LEVEL 2 BUDGET VARIANCE EXPLANATION FORM WAS SUBMITTED FOR APPROVAL IN WMSDOCS PER VAPIERCE 5/25/23
22026206400 | RETIRE ELECTRONIC | [5 empty] | 2331.95 | 65.0112 | 2266.9388 |  |  |  | 44823 | RETIRED OLD MINIAT INSTALLED NEW EC350 DASH 9-19-2022
22026207100 | INSTALL 7870'-2", 4" PMMP | [5 empty] | 1549123.72 | 1271473.5495 | 277650.1705 |  |  |  | 45593
22026207200 | RETIRE 6009'-2",3", 4" LP | [5 empty] | 873.05 | 1120.6093 | -247.5593 |  |  |  | #N/A
22026210700 | RETIRE METAL BUILDING | [5 empty] | 0 | 1009.5809 | -1009.5809 |  |  |  | 44910 | REG STATION AND BUILDING RETIRED DASH 12-15-22
22026211000 | EMER - INSTALL 3'-4" PMMP | [5 empty] | 8542 | 12351.4608 | -3809.4608 |  |  |  | 44770 | CUT OUT 3' OF 4" PL MP AND REPLACED WITH NEW 3' OF 4" PL MP TESTED 90 PSIG 1 HOUR
22026211100 | EMER - RETIRE 3'-4" PMMP | [5 empty] | 449.88 | 477.8601 | -27.9801 |  |  |  | 44770 | RETIRED 3' OF 4" PL MP AND INSTALLED NEW 3' OF 4" PL TESTED 90 PSIG 1 HOUR SOAP TESTD FINAL CONN OP 40 PSIG
22026211800 | RETIRE GMB SETTING | [5 empty] | 1541.41 | 1288.7874 | 252.6226 |  |  |  | 44936 | GMB NO CC NEEDED
22026213800 | EMER - RETIRE 150'-2" P-IP | [5 empty] | 4136.05 | 4412.2636 | -276.2136 |  |  |  | 44810 | ABANDONED 150' OF 2" PLASTIC. SOAP TESTED ABANDONMENT AT OP. PRESS. 15MIN.
22026214400 | MAVITY HVAC/RTU | [5 empty] | 0 | 55.5311 | -55.5311 |  |  |  | 44778 | UPGRADED RTU
22026216300 | INSTALL VRG CONTROLLER | [5 empty] | 28545.09 | 10806.1191 | 17738.9709 |  |  |  | 44966 | CC 15047 CC 15628 CC 15628 CC 15628 CC 15628 CC 16352 NOT ON SITE CAPITAL PAPERWORK/ISO SKETCH
22026216400 | RETIRE CONTROLLERS | [5 empty] | 572.67 | 84.9152 | 487.7548 |  |  |  | 44966 | RETIRED CONTROLLERS, INSTALLED NEW VRG'S
22026218400 | RETIRE 2'-4" BSLP | [5 empty] | 0 | 84.9152 | -84.9152 |  |  |  | 44788
22026218500 | INSTALL 35'-2"/4 PMLP | [5 empty] | 8610.21 | 16435.9913 | -7825.7813 |  |  |  | 44861 | INSTALLED 2' OF 4" PL AND 37' OF 2" PL LP TESTED 90 PSIG 1 HR
22026219600 | INSTALL 90'-2" PMIP | [5 empty] | 50608.23 | 21041.6638 | 29566.5662 |  |  |  | 44914
22026228900 | EMER - INSTALL 40'-2" PMIP | [5 empty] | 37570.14 | 32269.3764 | 5300.7636 |  |  |  | 44847
22026229000 | EMER - RETIRE 40'-2" PIP | [5 empty] | 0 | 132.427 | -132.427 |  |  |  | 44847
22026230800 | EMER - RETIRE 3'-2" P-IP | [5 empty] | 1400.06 | 1985.3283 | -585.2683 |  |  |  | 44910 | CONTRACTOR HIT MISS MARKED MAIN CUT OUT DAMAGED SECTION AND EF PURGE POINT ON END OF MAIN LINE SOAP TESTED OP 7 PSIG
22026231600 | EMER - INSTALL 2'-4" PMMP | [5 empty] | 196.47 | 5460.0467 | -5263.5767 |  |  |  | 44876 | INSTALLED 2' OF 4" PL MP TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 40 P SIG
22026231700 | EMER - RETIRE 2'-4" PMMP | [5 empty] | 24.23 | 263.239 | -239.009 |  |  |  | 44876 | RETIRED 2' OF 4" PL MP DUE TO LEAKAGE SOAP TESTED TO VERFY SHUTDOWN
22026232200 | INSTALL SKID MOUNTED GMB | [5 empty] | 40259.26 | 56170.7039 | -15911.4439 |  |  |  | 44910 | INSTALLED NEW SKID MOUNTED METER SETTING DASH 12-15-22
22026232300 | RETIRE GMB SETTING | [5 empty] | 1984.01 | 263.239 | 1720.771 |  |  |  | 44910 | INSTALLED NEW SKID MOUNT METER SETTING AND RETIRED OLD METER AND REGULATORS DASH 12-15-22
22026232700 | RETIRE GMB W/22-9790457-00 | [5 empty] | 0 | 545.7645 | -545.7645 |  |  |  | 44916
22026234200 | INSTALL 100'-6"PMMP S/L | [5 empty] | 60246.05 | 78909.8457 | -18663.7957 |  |  |  | 44901 | CJH JOE HADLEY REPLACED SL, TESTED SL AT 0106PSIG/0200HRS, OPEN CUT, SOAP TESTED FC/CAP AT OP, EXT CORR INSP, NO ANODE, WRAPPED EXPOSED MAIN, DS 12062022
22026234300 | RETIRE GMB SETTING | [5 empty] | 0 | 725.239 | -725.239 |  |  |  | 44886 | RETIRED GMB SETTING REMOVED METER BLIND PLATED SERVICE GAS NO LONGER NEEDED
22026235200 | INSTALL 200'-2" PMIP | [5 empty] | 11987.46 | 38455.6638 | -26468.2038 |  |  |  | 44914
22026235800 | EMER - INSTALL 3'-4" PMMP | [5 empty] | 7089.71 | 18999.7951 | -11910.0851 |  |  |  | 44910 | FOUND CLAMPS ON 4" PL MAIN CUT OUT AND INSTALLED NEW MAIN TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 15 PSIG
22026235900 | EMER - RETIRE 3'-4" P-MP | [5 empty] | 22647.66 | 117.5985 | 22530.0615 |  |  |  | 44910 | RETIRED 4" PL MAIN WITH CLAMPS ON IT TO INSTALL NEW
22026240200 | EMER - INSTALL 100'-4" PMLP | [5 empty] | 5141.88 | 38890.2222 | -33748.3422 |  |  |  | 44925 | INSTALLED 93' OF PL AND ST TESTED 90 PSIG 1 HR SOAP TESTED WELD CAPS AND SSTEE CAPS 10" WC
22026240300 | EMER - RETIRE 100'-4" BSLP | [5 empty] | 285.28 | 129.6266 | 155.6534 |  |  |  | 44925 | RETIRED 75' OF 4" BS DUE TO LEAKAGE
22026240400 | PAPER ONLY - RETIRE BSIP MAIN | [5 empty] | 0 | 119.2135 | -119.2135 |  |  |  | 44914
22026241300 | EMER - INSTALL 5'-4" PMMP | [5 empty] | 1144.39 | 10162.4624 | -9018.0724 |  |  |  | 44910 | INSTALLED 3' OF 4" PL DUE TO LEAKAGE ON SERVICE TEE TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 11 PSIG
22026241400 | EMER - RETIRE 5'-4" PMP | [5 empty] | 91.78 | 117.5985 | -25.8185 |  |  |  | 44910 | RETIRE 4" MP TO DUE TO LEAKAGE ON SERVIEC TEE TO INSTALL NEW
22026244600 | INSTALL BUILDING AND FENCE | [5 empty] | 0 | 28935.3221 | -28935.3221 |  |  |  | 44637 | INSTALLED COMM BUILDING AND FENCE DASH 3-17-22
22026245500 | INSTALL REG STATION BUILDING | [5 empty] | 12285 | 128388.6752 | -116103.6752 |  |  |  | 44911
23026246000 | INSTALL M&R CRANE - MARATHON | [5 empty] | 14182.67 | 36312.6752 | -22130.0052 |  |  |  | 44911
23026246200 | INSTALL VRG - MIS FACILITY | [5 empty] | 0 | 449.3532 | -449.3532 |  |  |  | 44911
23026246300 | INSTALL VRG - RETIRE MIS FAC | [5 empty] | 0 | 132.4844 | -132.4844 |  |  |  | 44911
23026246800 | INSTALL 800'-4" PMMP | [5 empty] | 287158.53 | 369832.3416 | -82673.8116 |  |  |  | 45035
23026246900 | RETIRE 1000'-4" P-MP | [5 empty] | 0 | 123.4477 | -123.4477 |  |  |  | 45035
23026247100 | EMER - INSTALL 9'-4" CSMP/PMP | [5 empty] | 5323.15 | 14951.5544 | -9628.4044 |  |  |  | 44957 | LOWERED MAIN DUE TO LEAKAGE AND 14" WATER LINE TESTED 90 PSIG 0005 MIN SOAP TESTED FINAL CONN OP 40 PSIG
23026247200 | EMER - RETIRE 9'-4" CSMP | [5 empty] | 806.29 | 149.6969 | 656.5931 |  |  |  | 44957 | RETIRED 9' OF 4" ST TO LOWER FOR 14" WATER MAIN SOAP TESTED OP TO VERIFY AD EQUATE SHUT DOWN 40 PSIG
23026248600 | RETIRE 3'-3" PMLP | [5 empty] | 3012.93 | 1635.0284 | 1377.9016 |  |  |  | 44951 | RETIRED 20' OF 3" PL MAIN DUE TO FACILITY DAMAGE SOAP TESTED OP 9.5" WC
23026249100 | INSTALL 100'-2" PMMP | [5 empty] | 13611.51 | 7008.1595 | 6603.3505 |  |  |  | 44988 | INSTALLED NEW MAIN ON RICHLAND CT TESTED 90 PSIG 1 HR SOAP TESTED BRANCHING TEE CAP AND PURGE POINT CAP OP 14 PSIG
23026249200 | GMB TO CAB CONVERSION | [5 empty] | 858.55 | 132.4844 | 726.0656 |  |  |  | 44943 | CONVERTED FROM GMB TO CAB SGIORDANO
23026251100 | INSTALL EC-350 UNIT | [5 empty] | 1808.88 | 3195.3221 | -1386.4421 |  |  |  | 44950 | INSTALLED NEW EC350 DASH 1-24-23
23026251200 | RETIRE PAPER BILLING CHART | [5 empty] | 975.93 | 131.2422 | 844.6878 |  |  |  | 44950 | RETIRED CHART INSTALLED NEW EC350 DASH 1-24-23
23026251300 | INSTALL EC 350 UNIT | [5 empty] | 8141.46 | 7475.3221 | 666.1379 |  |  |  | 44998 | INSTALLED NEW EC350 TO REPLACE PAPER BILLING CHART
23026251400 | RETIRE PAPER BILLING CHART | [5 empty] | 870.82 | 131.2422 | 739.5778 |  |  |  | 44998 | RETIRE PAPER BILLING CHART
23026254200 | RETIRE RECORDING GAUGE | [5 empty] | 107.1 | 552.5683 | -445.4683 |  |  |  | 44986 | CC 10596 RETIRE PAPER CHART SHANE G. 03012023
23026256700 | RETIRE PAPER GAUGE | [5 empty] | 756.49 | 138.8485 | 617.6415 |  |  |  | 44978 | CC 17512 REMOVED PAPER PRESSURE GAUGE
23026257200 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 3080.61 | 12042.2854 | -8961.6754 |  |  |  | 45150 | CC 41028
23026257300 | RETIRE CHART | [5 empty] | 386.09 | 124.7348 | 261.3552 |  |  |  | 45153
23026257500 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 3917.88 | 23732.2854 | -19814.4054 |  |  |  | 45119
23026257600 | RETIRE PAPER CHAT | [5 empty] | 575.02 | 121.7239 | 453.2961 |  |  |  | 45119
23026257700 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 3552.01 | 22126.2854 | -18574.2754 |  |  |  | 45154
23026257800 | RETIRE PAPER CHART | [5 empty] | 1141.91 | 121.7239 | 1020.1861 |  |  |  | 45154
23026258100 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 4339.86 | 20638.2854 | -16298.4254 |  |  |  | 45120 | CC 41992
23026258200 | RETIRE PAPER CHART | [5 empty] | 0 | 121.7239 | -121.7239 |  |  |  | 45120
23026258500 | INSTALL ULTRASONIC METER | [5 empty] | 51660.67 | 47491.9621 | 4168.7079 |  |  |  | #N/A | CC# 47829
23026258600 | EMER - INSTALL 5'-4" PMIP | [5 empty] | 29274.5 | 23135.0467 | 6139.4533 |  |  |  | 45091 | INSTALLED 3' OF 4" PL DUE TO BORE CREW BORING INTO MAIN TESTED 90 PSIG 1 HR
23026258700 | EMER- RETIRE 5'-4" PMIP | [5 empty] | 21718.99 | 137.555 | 21581.435 |  |  |  | 45090 | RETIRED 3' OF 4" IP DUE TO BORE CREW HITTING MAIN SOAP TESTED OP 7 PSIG TO VERIFY SQUEEZE OFF
23026258900 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 5852.27 | 22126.2854 | -16274.0154 |  |  |  | 45170
23026259200 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 4121.74 | 21353.2854 | -17231.5454 |  |  |  | 45121 | CC 37280
23026259300 | RETIRE PAPER CHART | [5 empty] | 0 | 121.7239 | -121.7239 |  |  |  | 45121
23026259400 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 3579.71 | 20638.2854 | -17058.5754 |  |  |  | 45125
23026259500 | RETIRE PAPER CHART | [5 empty] | 347.11 | 121.7239 | 225.3861 |  |  |  | 45125
23026259800 | INSTALL ERX W/SUPER SOLAR | [5 empty] | 3465.31 | 5058.9621 | -1593.6521 |  |  |  | 44987 | CC# 18720. 3/2/23 DSASH
23026259900 | RETIRE PAPER CHART | [5 empty] | 277.39 | 138.8485 | 138.5415 |  |  |  | 44987 | CC# 18720. 3/2/23 DSASH CC# 18720
23026260000 | INSTALL ERX W/SUPER SOLAR | [5 empty] | 3193.7 | 5058.9621 | -1865.2621 |  |  |  | 44985 | CC# 18341. 2/28/23 DSASH CC# 21913. P2P OK.
23026260100 | RETIRE PAPER GAUGE | [5 empty] | 257.79 | 138.8485 | 118.9415 |  |  |  | 44985 | CC# 18341. 2/28/23 DSASH
23026260200 | INSTALL ERX W/SUPER SOLAR | [5 empty] | 4114.48 | 6314.9621 | -2200.4821 |  |  |  | 44979 | CC 17668 NOT ON SITE CAPITAL PACKET PAPERWORK NOT ONSITE. ISO UPDATES CC 21100 ANNUAL GAUGE INSP AND P2P WITH GAS CONTROL COMPLETE.
23026260300 | RETIRE PAPER CHART | [5 empty] | 564.75 | 138.8485 | 425.9015 |  |  |  | 44979 | CC 17668
23026260400 | INSTALL ERX W/SUPER SOLAR | [5 empty] | 3437.82 | 6314.9621 | -2877.1421 |  |  |  | 44980 | CC 17834 NOT ON SITE. CAPITAL PACKET PAPERWORK NOT ON SITE ISO UPDATES CC 21100 ANNUAL GAUGE INSP AND P2P WITH GAS CONTROL COMPLETE
23026260500 | RETIRE PAPER CHART | [5 empty] | 605.66 | 138.8485 | 466.8115 |  |  |  | 44980 | CC 17834
23026260900 | INSTALL ERX W/SUPER SOLAR | [5 empty] | 1872.11 | 5458.9621 | -3586.8521 |  |  |  | 45002 | CC 20969 CC 24221 P2P OK WITH GC.
23026261000 | RETIRE PAPER CHART | [5 empty] | 174.56 | 138.8485 | 35.7115 |  |  |  | 45002 | CC 20961
23026261200 | INSTALL ULTRASONIC METER | [5 empty] | 57893.54 | 47951.5304 | 9942.0096 |  |  |  | 45274
23026261700 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 3770.68 | 21353.2854 | -17582.6054 |  |  |  | 45124
23026261800 | RETIRE PAPER CHART | [5 empty] | 642.64 | 121.7239 | 520.9161 |  |  |  | 45124 | CC 37443
23026262200 | EMER - INSTALL 4'-2" PMMP | [5 empty] | 15777.13 | 2419.7892 | 13357.3408 |  |  |  | 44988 | INSTALLED 4' OF 2" PLASTIC MAIN. PRESSURE TESTED AT 90LBS FOR 1 HR.
23026262300 | EMER - RETIRE 4'-2" PMMP | [5 empty] | 242.84 | 260.4446 | -17.6046 |  |  |  | 44988 | REMOVED 4' OF DAMAGED 2" PLASTIC
23026262400 | INSTALL RTU & INSTRUMENTATION | [5 empty] | 279231.64 | 257150.5602 | 22081.0798 |  |  |  | #N/A | CC 27892 NOT ON SITE CONTRACTOR RESCHEDULED CC 44847 CC 45180 CC 51942 CC 52129 CC# 52432 NO CC NEEDED CC 53623 CC 53623 CC 53373 CC 53373
23026262500 | RETIRE RTU & INSTRUMENTATION | [5 empty] | 0 | 117.7346 | -117.7346 |  |  |  | #N/A
23026262601 | INSTALL CHAIN LINK FENCE | [5 empty] | 72669.9 | 39848.4833 | 32821.4167 |  |  |  | 45289 | CC 44278 NOT ON SITE CC 53373 CC 53373 CC 57440 CC 58157
23026264500 | EMER - INSTALL ~5'-4" PM/CSMP | [5 empty] | 929.35 | 2069.4953 | -1140.1453 |  |  |  | 45163
23026264600 | EMER - RETIRE ~5'-4" CSMP | [5 empty] | 207.34 | 67.4953 | 139.8447 |  |  |  | 45163
23026265600 | EMER - INSTALL 4'-6" PMIP | [5 empty] | 19713.32 | 12463.1003 | 7250.2197 |  |  |  | 45164
23026265700 | EMER - RETIRE 4'-6" P-IP | [5 empty] | 0 | 391.4196 | -391.4196 |  |  |  | 45163
23026269500 | EMER - INSTALL 4'-2" PIP | [5 empty] | 2717.09 | 7943.8116 | -5226.7216 |  |  |  | 45164
23026269600 | EMER - RETIRE 5'-2" PIP | [5 empty] | 0 | 134.4334 | -134.4334 |  |  |  | 45163
23026270200 | EMER - RETIRE 5'-2" PIP | [5 empty] | 0 | 288.6068 | -288.6068 |  |  |  | 44719 | REPLACED 5' SECTION OF 2" PMMP. TESTED MAIN AT 90 PSIG FOR 1 HOUR AND TEST WAS GOOD. TESTED 2X1 EF TEES AT 90 PSIG FOR 5 MINS AND SOAP TESTED THE CAPS AND DEAD ENDS AT OP FOR 5 MINS. ALL TEST ARE GOOD.
23026270300 | EMER - INSTALL 2'-4" PMMP | [5 empty] | 526.5 | 9141.6411 | -8615.1411 |  |  |  | 45071
23026270400 | EMER - RETIRE 110'-4" P-MP | [5 empty] | 537.22 | 137.555 | 399.665 |  |  |  | 45071 | RETIRED 110' OF 4" PL MP DUE TO BUILDING COLLAPSING TESTED CAP 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 38 PSIG
23026271400 | EMER - INSTALL ~5'-2" PMMP | [5 empty] | 7739.82 | 5664.5366 | 2075.2834 |  |  |  | 45055 | INSTALLED 1' OF 2" PL MP DUE TO DAMAGE TESTED 90 PSIG 1 HR SOAP TESTED FINA L CONN OP 40 PSIG
23026271500 | EMER - RETIRE ~5'-2" PMMP | [5 empty] | 709.93 | 114.3981 | 595.5319 |  |  |  | 45055 | RETIRED 1" OF 2" PL MP DUE TO FACILITY DAMAGE SOAP TESTED TO VERIFY SQUEEZE OFF OP 40 PSIG
23026275200 | EMER - INSTALL 3'-2" PMIP | [5 empty] | 5562.78 | 9765.5645 | -4202.7845 |  |  |  | 45091 | INSTALLED 3' OF 2" MAIN DUE TO DAMAGE BY BORE CREW TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 5.5 PSIG
23026275300 | EMER - RETIRE 3'-2" PIP | [5 empty] | 235.76 | 134.4334 | 101.3266 |  |  |  | 45091 | RETIRED 3' OF 2" PL DUE TO BORE CREW HITTING MAIN TIEING CONDUIT TOGHETHER
23026277600 | INSTALL 595'-2"PMMP | [5 empty] | 137119.9 | 198539.3537 | -61419.4537 |  |  |  | 45240
23026277700 | RETIRE 2881'-12" BSMP | [5 empty] | 430.39 | 139.1159 | 291.2741 |  |  |  | 45240
23026278100 | RETIRE REG FAC | [5 empty] | 0 | 67.1159 | -67.1159 |  |  |  | 45083 | JOB TO EXECUTE PAPERWORK ONLY RWILLIAMS 6-6-2023
23026278700 | INSTALL 105'-2" PMMP | [5 empty] | 9899.17 | 17148.7846 | -7249.6146 |  |  |  | 45103 | INSTALLED 116' OF 2" PL MP TESTED 90 PSIG 0005 MIN SOAP TESTED CAPS AND DEA D HEADS OP 17 PSG
23026279500 | INSTALL 339'-8" PMLP | [5 empty] | 110539.26 | 126473.6122 | -15934.3522 |  |  |  | 45422 | INSTALLED 218' OF 8" PLASTIC TESTED 105 PSIG 4 HOURS SOAP TESTED FINAL CONN OP 10" WC
23026279600 | RETIRE 339'-8" BSLP | [5 empty] | 1599.81 | 119.4953 | 1480.3147 |  |  |  | #N/A | RETIRED MAIN LINES PURGED AND SEALED SOAP TESTED 10" WC TO VERIFY SHUTDOWN
23026280200 | RETIRE 18570'-2"-16" S&PMP | [5 empty] | 111917.81 | 113891.7734 | -1973.9634 |  |  |  | #N/A | IP 23175576300 2211 - REPAIR LEAK ON MAIN D200007
23026280300 | RETIRE 1107'-2"&8" CS&PHHP | [5 empty] | 2514.99 | 14918.7734 | -12403.7834 |  |  |  | #N/A
23026280600 | RETIRE FENCE | [5 empty] | 0 | 5554.3418 | -5554.3418 |  |  |  | #N/A
23026280700 | RETIRE STATIONS R-1375 | [5 empty] | 1935.34 | 4462.367 | -2527.027 |  |  |  | #N/A
23026283101 | INSTALL 780'-2" PMMP | [5 empty] | 71782.2 | 96018.7749 | -24236.5749 |  |  |  | 45805
23026283600 | INSTALL LP FITTINGS | [5 empty] | 9658.7 | 11183.6093 | -1524.9093 |  |  |  | 45593
23026284800 | EMER - INSTALL 40'-4" PMLP | [5 empty] | 630.98 | 16339.4428 | -15708.4628 |  |  |  | 45132 | INSTALLED 34' OF 4" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 10" WC
23026284900 | EMER - RETIRE 40'-4" BSLP | [5 empty] | 451.35 | 139.1159 | 312.2341 |  |  |  | 45132 | RETIRED 34' OF 4" BS MAIN DUE TO LEAKAGE SOAP TESTED OP TO VERIFY SHUTDOWN SOAP TESTED OP 10" WC
23026289300 | INSTALL 7'-2"&6" PMLP | [5 empty] | 447.65 | 141.4953 | 306.1547 |  |  |  | 45166
23026290100 | EMER - 3'-3" PMIP | [5 empty] | 5711.96 | 2929.2518 | 2782.7082 |  |  |  | 45189 | INSTALLED 3' OF 2" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 5 PSIG
23026290200 | EMER-RETIRE 3'-PIP | [5 empty] | 253 | 119.4953 | 133.5047 |  |  |  | 45189 | CUT OUT 3' OF 2" PL DUE TO HIT MAIN SOAP TESTED TO VERIFY SHUTDOWN AFTER SQUEEZE OP
23026291700 | EMER - INSTALL 3'-4" PMIP | [5 empty] | 2485.01 | 9351.5219 | -6866.5119 |  |  |  | 45177 | INSTALLED 3' OF 4" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7 PSIG
23026291800 | EMER - RETIRE 3'-4" PIP | [5 empty] | 685.77 | 119.4953 | 566.2747 |  |  |  | 45177 | RETIRED 3' OF 4" PL DUE TO LEAK ON 4" SF COUPLING SOAP TESTED OP 7 PSIG TO VERIFY ADEQUATE SHUTDOWN
23026292300 | INSTALL 2" SS | [5 empty] | 1292.35 | 15645.4681 | -14353.1181 |  |  |  | 45307 | INSTALED AND TESTED SS FITTING AT 90PSIG FOR 15 MINS
23026292400 | RETIRE 154'-2" CSIP | [5 empty] | 13487.05 | 119.4953 | 13367.5547 |  |  |  | #N/A | INSTALLED WELD CAP TO MAIN SOAP TESTED END CAP AT OP FOR 15 MINS
23026294700 | INSTALL 70'-2" PMIP | [5 empty] | 12372.22 | 22819.9245 | -10447.7045 |  |  |  | 45296 | INSTALLED 74' OF 2" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN AND PURGE POINT CAP OP 8 PSIG
23026296700 | INSTALL 165' OF 2" PMIP | [5 empty] | 15685.08 | 23912.4752 | -8227.3952 |  |  |  | 45289 | INSTALLED 157' OF 2" IP MAIN TESTED 90 PSIG 1 HR SOAP TESTED PURGE POINT CAP AND SST CAP OP 7.5 PSIG
23026299800 | PAPER ONLY SL RETIRE | [5 empty] | 0 | 122.9261 | -122.9261 |  |  |  | 45089
23026299900 | PAPER ONLY SL REPLACEMENT | [5 empty] | 1201.76 | 145.9261 | 1055.8339 |  |  |  | 45209
23026300000 | INSTALL NEW EQUIPMENT | [5 empty] | 570.56 | 3973.8688 | -3403.3088 |  |  |  | 45209
23026300300 | INSTALL 1810'-2" PMMP | [5 empty] | 217275.5 | 171679.8061 | 45595.6939 |  |  |  | 45610
23026306800 | INSTALL METER RUN | [5 empty] | 47050.46 | 89187.262 | -42136.802 |  |  |  | #N/A | CCC 94516 CCC 95365 SG 11/4/24 X 1109A
23026307000 | RETIRE METAL BLDG | [5 empty] | 0 | 124.9261 | -124.9261 |  |  |  | 45261 | TWALKER/KY 12-1-23: THIS BUILDING AND REG STATION RETIRED ON 21-0261546-00.
23026308100 | INSTALL NEW METER | [5 empty] | 7400.08 | 41682.6833 | -34282.6033 |  |  |  | #N/A | CCC 92257 NO CCC NEEDED. COMPLETING CAPITAL PAPERWORK. SG 10/30/24 1235P PER D.ASH NPRV NOT NEEDED SO IT WAS NOT ORDERED OR INSTALLED
24026316400 | EMER-INSTALL CATALYTIC HEATER | [5 empty] | 2159.35 | 3661.3856 | -1502.0356 |  |  |  | #N/A | TWALKER/KY 02-27-24: CORRECTED JOB TO EMER STATUS, MP SYSTEM 32051028 IS SUPPLIED BY REG #1381 AND #1374...REG#1381 HAD TO BE SHUT IN FOR M&R WORK, WITH ONLY ONE REG STATION SUPPLIED MP SYSTEM REQUIRED A CAT HEATER DUE TO FREEZING ISSUE.
24026318800 | ADD SOLAR BACKUP | [5 empty] | 9847.7 | 11051.1928 | -1203.4928 |  |  |  | #N/A | CCC 88756 CCC 90158
24026318900 | RETIRE COMPONENTS | [5 empty] | 0 | 160.3697 | -160.3697 |  |  |  | #N/A
24026319200 | UPGRADE SCADA SYSTEM | [5 empty] | 9821.8 | 11051.1928 | -1229.3928 |  |  |  | #N/A | CCC# 88928
24026319300 | RETIRE SCADA COMPONENTS | [5 empty] | 0 | 160.3697 | -160.3697 |  |  |  | #N/A
24026319400 | UPGRADE SCADA SYSTEM | [5 empty] | 11260.82 | 11051.1928 | 209.6272 |  |  |  | #N/A | CCC# 89146
24026319500 | RETIRE SCADA COMPONENTS | [5 empty] | 23092 | 160.3697 | 22931.6303 |  |  |  | #N/A
24026319800 | UPGRADE SCADA SYSTEM | [5 empty] | 7392.38 | 11051.1928 | -3658.8128 |  |  |  | #N/A | CCC# 89306
24026319900 | RETIRE SCADA COMPONENTS | [5 empty] | 0 | 160.3697 | -160.3697 |  |  |  | #N/A
24026320000 | INSTALL SOLAR BACK UP UNIT | [5 empty] | 6749.45 | 11051.1928 | -4301.7428 |  |  |  | #N/A
24026320200 | UPGRADE SCADA SYSTEM | [5 empty] | 9127.38 | 11051.1928 | -1923.8128 |  |  |  | #N/A
24026320300 | RETIRE SCADA COMPONENTS | [5 empty] | 1185.97 | 160.3697 | 1025.6003 |  |  |  | #N/A
24026320500 | INSTALL ULTRA SONIC METER | [5 empty] | 36964.47 | 47090.3856 | -10125.9156 |  |  |  | #N/A
24026320800 | EMER - INSTALL 5'-3" PMIP | [5 empty] | 25129.82 | 6546.5769 | 18583.2431 |  |  |  | 45344 | INSTALLED 4' OF 3" PL IP MAIN TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7 PSIG
24026320900 | EMER RETIRE 5'-3" PIP | [5 empty] | 403.88 | 160.3697 | 243.5103 |  |  |  | #N/A | RETIRED 4' OF 3" PL DUE TO FAILED 3X1 EF ON MAIN SOAP TESED TO VERIFY SHUT DOWN OP 7 PSIG
24026322500 | INSTALL MIWI W/ SOLAR | [5 empty] | 18888.98 | 29494.1928 | -10605.2128 |  |  |  | #N/A | CCC 88309 SG 9/11/24 250P CCC 93309 CCC 93309 CCC 93309 SG 11/1/24 250P CCC 93309 P2P COMPLETED. SG 11/4/24 240P
24026322600 | REITRE FACILITIES | [5 empty] | 0 | 160.3697 | -160.3697 |  |  |  | #N/A
24026323100 | UPGRADE TO FULL TIME | [5 empty] | 7625.67 | 14026.1928 | -6400.5228 |  |  |  | #N/A
24026323200 | RETIRE FACILITIES | [5 empty] | 501.62 | 160.3697 | 341.2503 |  |  |  | #N/A
24026323300 | UPGRADE TO FULL TIME | [5 empty] | 7465.2 | 14026.1928 | -6560.9928 |  |  |  | #N/A
24026323400 | RETIRE FACILITIES | [5 empty] | 722.69 | 160.3697 | 562.3203 |  |  |  | #N/A
24026323500 | UPGRADE TO FULL TIME | [5 empty] | 7331.42 | 14026.1928 | -6694.7728 |  |  |  | #N/A
24026323600 | RETIRE FACILITIES | [5 empty] | 717.61 | 160.3697 | 557.2403 |  |  |  | #N/A
24026323700 | UPGRADE TO FULL TIME | [5 empty] | 7820.77 | 14026.1928 | -6205.4228 |  |  |  | #N/A
24026323800 | RETIRE FACILITIES | [5 empty] | 748.22 | 160.3697 | 587.8503 |  |  |  | #N/A
24026324100 | INSTALL 670'-2' PMIP | [5 empty] | 91180.5 | 68828.4274 | 22352.0726 |  |  |  | 45610 | INSTALLED 704' OF 2" PL IP AND 3' OF 2" ST TESTED 111 PSIG FOR 1 HR SOAP TE STED SST CAP AND PURGE POINT CAPS OP 7.5 PSIG
24026325200 | INSTALL BYPASS VALVE | [5 empty] | 23298.82 | 30940.8061 | -7641.9861 |  |  |  | #N/A | CCC 73047 NO CCC NEEDED. NO CCC NEEDED. WORK BEING DONE AT GMB LOCATION.
24026325300 | UPGRADE SCADA SYSTEM | [5 empty] | 9037.36 | 10627.0487 | -1589.6887 |  |  |  | #N/A | CCC# 89894
24026325400 | UPGRADE SCADA SYSTEM | [5 empty] | 0 | 121.4465 | -121.4465 |  |  |  | #N/A
24026325500 | UPGRADE SCADA SYSTEM | [5 empty] | 7316.43 | 10627.0487 | -3310.6187 |  |  |  | #N/A
24026325600 | UPGRADE SCADA SYSTEM | [5 empty] | 563.53 | 121.4465 | 442.0835 |  |  |  | #N/A
24026326800 | INSTALL ELECTRINICS | [5 empty] | 8703.66 | 15644.0403 | -6940.3803 |  |  |  | #N/A | CCC 92181
24026326900 | RETIRE ELECTRONICS | [5 empty] | 0 | 118.4933 | -118.4933 |  |  |  | #N/A
24026327400 | INSTALL ELECTRONICS | [5 empty] | 9042.76 | 15644.0403 | -6601.2803 |  |  |  | #N/A | CCC 90038
24026327500 | RETIRE ELECTRONICS | [5 empty] | 0 | 118.4933 | -118.4933 |  |  |  | #N/A
24026327600 | INSTALL ELECTRONICS | [5 empty] | 8257.47 | 15644.0403 | -7386.5703 |  |  |  | #N/A
24026327700 | RETIRE ELECTRONICS | [5 empty] | 1025.99 | 118.4933 | 907.4967 |  |  |  | #N/A
24026328000 | INSTALL ELECTRONICS | [5 empty] | 7483.34 | 15644.0403 | -8160.7003 |  |  |  | #N/A
24026328100 | RETIRE ELECTRONICS | [5 empty] | 431.14 | 118.4933 | 312.6467 |  |  |  | #N/A
24026333201 | EMER - INSTALL 478'-4" PMLP | [5 empty] | 205447.29 | 106609.2647 | 98838.0253 |  |  |  | 45694
24026333301 | EMER - RETIRE 477'-4" CSLP | [5 empty] | 226.51 | 112.4469 | 114.0631 |  |  |  | #N/A
24026335800 | EMER - INSTALL PF REGULATOR | [5 empty] | 111967.23 | 48662.72 | 63304.51 |  |  |  | #N/A | TWALKER 08-29-24: JOB ORDER OVER RUN DUE TO LP OUTAGE AND LABOR TO RESTORE SERVICE ADDED $40,000 TO COST AND SEGA WAS $20,000 HIGHER THAN EST.
24026335900 | EMER - RETIRE PF REGULATOR | [5 empty] | 0 | 121.4465 | -121.4465 |  |  |  | #N/A
24026337800 | INSTALL 8" SS | [5 empty] | 2650.82 | 151.4465 | 2499.3735 |  |  |  | 45390
24026340600 | INSTALL LP FITTINGS | [5 empty] | 0 | 5899.0487 | -5899.0487 |  |  |  | 45407
24026344300 | EMER-INSTALL 6' OF 4" PMIP | [5 empty] | 20651.9 | 14215.6055 | 6436.2945 |  |  |  | 45440
24026344400 | EMER-RETIRE 6' OF 4" PAIP | [5 empty] | 0 | 139.7787 | -139.7787 |  |  |  | #N/A
24026347300 | EMER - INSTALL 12'-3" PMIP | [5 empty] | 52750.04 | 21463.3624 | 31286.6776 |  |  |  | 45460 | FOUND 2-3X3 PAC CLALMPS LEAKING AND 2-3" BOLTED COUPLINGS ON MAIN CUT OUT A ND REPLACED 12' OF 3" PL MAIN TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7 PSIG
24026347400 | EMER - RETIRE 12'-3" PIP | [5 empty] | 167.95 | 136.633 | 31.317 |  |  |  | #N/A | CUT OUT 2 LEAKING 3X3 CLAMPS AND 2 3" BOLTED COUPLINGS SOAP TESTED TO VERIF Y SHUTDOWN ASFTER SQUEEZE
24026348900 | INSTALL 70'-8" PMMP | [5 empty] | 110389.69 | 134812.2257 | -24422.5357 |  |  |  | 45572
24026349000 | RETIRE 70' OF 10"CSMP MAIN | [5 empty] | 110 | 136.633 | -26.633 |  |  |  | #N/A
24026349500 | INSTALL 40'-12" CSMP | [5 empty] | 237894.26 | 141636.0949 | 96258.1651 |  |  |  | 45730
24026349600 | RETIRE ~40'-12" CSHP | [5 empty] | 220 | 136.633 | 83.367 |  |  |  | #N/A
24026349700 | EMER INSTALL 2' OF 2" PMMP | [5 empty] | 6054.03 | 5242.4082 | 811.6218 |  |  |  | 45476 | SOUTHERN OHIO TRENCHING HIT MISS MARKED 2" PL MP MAIN CUT OUT 2' OF MAIN AN D INSTALLED 2' TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 40 PSIG
24026349800 | EMER ABANDON 2' OF 2" PAMP | [5 empty] | 315.69 | 139.7787 | 175.9113 |  |  |  | #N/A | RETIRED 2'' OF 2" PL MP SOAP TESTED 40 PSIG TO VERFIY SQUEEZE OFF SHUTDOWN
24026354400 | INSTALL 20'-4" PMLP | [5 empty] | 287.45 | 159.2637 | 128.1863 |  |  |  | 45511
24026356500 | EMER - INSTALL 2'-2" PMIP | [5 empty] | 4865.71 | 2544.1386 | 2321.5714 |  |  |  | 45539 | INSTALLED 2' OF 2" P DUE TO FAC DAM. TESTED 90PSIG 1HR SOAP TESTED FC AT OP 7PSIG. CWHEELE
24026356600 | EMER - RETIRE 2'-2" PIP | [5 empty] | 49.73 | 124.2298 | -74.4998 |  |  |  | #N/A | REITRED 2' OF 2" P MAIN DUE TO FAC DAM SOAP TESTED OP TO VERIFY ADEQUATE SQUEEZE. CWHEELE 9-4-2024
24026358700 | INSTALL 100' OF 2" PMMP MLE | [5 empty] | 24604.17 | 21795.7838 | 2808.3862 |  |  |  | 45730
24026359401 | INSTALL 200' OF 4" PMIP | [5 empty] | 61986.14 | 49205.4272 | 12780.7128 |  |  |  | 45715
24026361400 | INSTALL 100' OF 2" PMIP | [5 empty] | 28089.92 | 24014.3917 | 4075.5283 |  |  |  | 45747
24026362600 | DOCUMENT RTU BUILDING | [5 empty] | 0 | 159.2637 | -159.2637 |  |  |  | #N/A
24026365300 | EMER INSTALL 5" OF 4" PMLP | [5 empty] | 26234.06 | 17482.6388 | 8751.4212 |  |  |  | 45674 | INSTALLED NEW PL 4" DUE TO CRACKED SF JOINT ON MAIN TESTED 2' OF 4" PL 90 PSIG 0005 MIN SOAP TESTED FINAL CONN OP 10.5" WC
24026365400 | EMER RETIRE 5" OF 4" PALP | [5 empty] | 612.15 | 76.7529 | 535.3971 |  |  |  | #N/A | RETIRED 2' OF 4" PL ALDYL-A DUE TO CRACKED SF COUPLING ON MAIN SOAP TESTED OP 10.5" WC TO VERIFY SHUTDOWN
24026367000 | EMER INSTALL 5'-2" PMMP | [5 empty] | 7909.41 | 7419.9991 | 489.4109 |  |  |  | 45576
24026367100 | EMER RETIRE 5'-2" PMMP | [5 empty] | 451.33 | 137.4585 | 313.8715 |  |  |  | #N/A
24026372800 | INSTALL SOLAR BACKUP | [5 empty] | 8466.91 | 9877.4639 | -1410.5539 |  |  |  | #N/A | CCC 107099 AJM 2/13/2025
24026373300 | INSTALL SOLAR BACKUP UNIT | [5 empty] | 7710.91 | 9877.4639 | -2166.5539 |  |  |  | #N/A | INSTALLED SOLAR BACKUP, CCC#108529, DS 02272025
24026373500 | INSTALL SOLAR BACKUP UNIT | [5 empty] | 7634.88 | 9877.4639 | -2242.5839 |  |  |  | #N/A | CCC 107260 AJM 2/14/2025 12:46 PM
24026374100 | INSTALL SOLAR BACKUP UNIT | [5 empty] | 7964.76 | 9877.4639 | -1912.7039 |  |  |  | #N/A | CC 107886 SG 2/21/25 130P
25026381500 | EMER - RETIRE ~870'-3" PIP | [5 empty] | 8256.1 | 3411.7402 | 4844.3598 |  |  |  | #N/A | RETIRED 800' OF MAIN - SOAP TEST END CAP @ OP OK- BHB OK-ABHATFIE 3/14/25
25026381700 | INSTALL 230' OF 2" PMIP | [5 empty] | 89700.18 | 29656.6889 | 60043.4911 |  |  |  | 45740
25026382400 | INSTALL SCADA EQUIPMENT | [5 empty] | 11519.85 | 20669 | -9149.15 |  |  |  | #N/A
25026392800 | RETIRE MP - PAPER ONLY | [5 empty] | 251.75 | 160.2249 | 91.5251 |  |  |  | #N/A
25026411700 | INSTALL SHORTSTOP TEE | [5 empty] | 0 | 2670.4144 | -2670.4144 |  |  |  | 45804
18026837600 | INST. FN 176 EXTRA LP OPP | [5 empty] | 59791.79 | 35378.1646 | 24413.6254 |  |  |  | 44384 | CONTROL SHEET 008281 PAID ON 04/23/20 THURSDAY TO COVER 04/24/20 FRIDAY CONTROL SHEET008307 PAID ON 04/30/20 THURSDAY TO COVER 05/01/20 FRIDAY NOT ON SITE GETTING PARTS FOR JOB CCC# 23134 CCC# 23265 CCC# 23459 CCC# 25857 REGULATORS INSTALLED BY WADE SHIMFESSEL ON 5/13/2021 EC350 INSTALLED BY WADE SHIMFESSEL ON 5/14/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/2021 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS *EXISTING Y STRAINER STRAINER GASKET NOT INSTALLED
18026837700 | RET. FN 176 FOR EXTRA LP OPP | [5 empty] | 0 | 53.9767 | -53.9767 |  |  |  | 44384 | REGULATORS REPLACED BY WADE SHIMFESSEL ON 5/13/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/2021 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026895200 | RETIRE 2104' 2" P/BSLP | [5 empty] | 100.78 | 103.581 | -2.801 |  |  |  | 44223
19026895301 | INSTALL 6060' 2" PMMP | [5 empty] | 815947.98 | 549218.5288 | 266729.4512 |  |  |  | 44223 | JOB ORDER CODED COMPLETE IN ERROR. WILL BE CARRY OVER INTO 2021. SPENDLE OVERRUN EXPLANATION: ADDITIONAL PIPE WAS ADDED LATE INTO PROJECT AND ADDITI ONAL LABOR HOURS CAUSED INCREASE IN SEGA AS WELL AS LATE PAVING COSTS THAT HIT THE PROJECT SBRADY 6/18/21
19026895400 | RETIRE 5072' 2-4" IP | [5 empty] | 0 | 103.581 | -103.581 |  |  |  | 44223
19026895600 | RETIRE 1516' 2" BS/P/WILP | [5 empty] | 108.73 | 103.581 | 5.149 |  |  |  | 44223
19026900900 | RETIRE MP TO IP RUN S-1455 | [5 empty] | 152.33 | 690.3419 | -538.0119 |  |  |  | 44494 | MP TO IP RUN RETIRE ON 1/27/21 BY RYAN VANDERPOOL PAPERWORK DID NOT GET TURNED IN FOR COMPLETION STATION RETIREMENT FIELD VERIFIED ALONG WITH RETIREMENT DATE FROM THE STATION INSPECTION RECORD BY WADE SHIMFESSEL AND JOSH MARTIN ON 10/18/2021 RETIREMENT PAPERWORK COMPLETED BY CYNTHIA FARIS ON 10/25/2021 GCCC TICKET NOT REQUIRED ON 10/25/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK. SETTING BYPASS VALVE AND INLET SETTING VALVE NOT RETIRED THEY ARE TURNED OFF AND BLIND FLANGED CFARIS
19026901000 | RETIRE STATION 1464 | [5 empty] | 2654.56 | 690.3419 | 1964.2181 |  |  |  | 44207 | JOB CARRIED OVER UNTIL AFTER THE 1ST OF 2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/16/2021 GCCC TICKET NOT REQUIRED ON 2/16/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK 2/16/21 CFARIS
19026901100 | RETIRE STATION 1481 | [5 empty] | 2483.61 | 690.3419 | 1793.2681 |  |  |  | 44207 | JOB ON HOLD UNTIL AFTER THE 1ST OF 2021
19026901200 | RETIRE STATION 1480 | [5 empty] | 4464.65 | 690.3419 | 3774.3081 |  |  |  | 44207 | JOB WAS ON HOLD UNTIL AFTER THE 1ST OF 2021
20026918301 | INSTALL ELECTRONICS | [5 empty] | 163427.04 | 179105.9064 | -15678.8664 |  |  |  | 44552 | GCC# 13951 CCC TICKET #14135 TICKET# 15597 CCC# 49425 REPLACED PUCK IN TRANSMITTER W/NOLL COMPLETED PAPERWORK 12-22-21 JMARTIN
20026931100 | UPGRADE ELECTRONICS | [5 empty] | 265.67 | 3038 | -2772.33 |  |  |  | 44518 | REPLACED EFC
20026938100 | RETIRE ELECTRONICS | [5 empty] | 0 | 73.3494 | -73.3494 |  |  |  | 44518 | REPLACED EFC
20026942500 | INSTALL I&C EQUIPMENT | [5 empty] | 8341.61 | 16155.4774 | -7813.8674 |  |  |  | 44571 | ERX INSTALLED BY ACP AND WADE SHIMFESSEL PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/10/22
20026942600 | RETIRE GAUGE | [5 empty] | 0 | 91.4991 | -91.4991 |  |  |  | 44571 | GAUGE RETIRED AFTER ERX INSTALLED BY WADE SHIMFESSEL PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/10/2022
20026942900 | INSTALL I&C EQUIPMENT | [5 empty] | 11090.78 | 16155.4774 | -5064.6974 |  |  |  | 44571 | ERX INSTALLED BY ACP AND WADE SHIMFESSEL PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/10/22
20026943000 | RETIRE GAUGE | [5 empty] | 1496.7 | 91.4991 | 1405.2009 |  |  |  | 44571 | CCC# 49347 COMMISION ERX CCC# 50118 ERX INSTALLED AND GAUGE RETIRED BY WADE SHIMFESSEL PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/10/22
20026973001 | INSTALL 10,000--2" PMMP | [5 empty] | 2896168.82 | 2332285.9866 | 563882.8334 |  |  |  | 44742 | COST OVERRUN OF $378K DUE TO PROJECT SHUT DOWN AND RESTART OVER WINTER. PR OJECT REQUIRED ADDITIONAL RESOURCES THAT WERE NOT ESTIMATED. COST OVERUN O F $345K IN MATERIALS (PAVING), $124K IN CONTRACT AND $21K IN LABOR. THERE W AS A SAVINGS OF $213K IN OTHER DUE TO ORIGINAL PAVING ESTIMATE BEING CAPTUR ED THERE. THESE ADDITIONAL COSTS CAUSED INCREASE IN SEGA OF $97K. D.LEMONS 10/26/2022
20026973100 | RETIRE 120'-4" BSMP | [5 empty] | 1897.5 | 80.6441 | 1816.8559 |  |  |  | 44742
20026973200 | RETIRE 10875' BS/CI LP | [5 empty] | 142.7 | 57.6441 | 85.0559 |  |  |  | 44742
20026973400 | RETIRE STATION R-1452 | [5 empty] | 114.18 | 1281.7771 | -1167.5971 |  |  |  | 44720 | CCC# 68859 CCC# 68859 RETIRED REGSTATION PER AMRP PROJECT JMARTIN
20026973500 | RETIRE STATION R-1458 | [5 empty] | 1295 | 1281.7771 | 13.2229 |  |  |  | 44707
20026973700 | INSTALL 6150'-4" PMLP | [5 empty] | 2832541.47 | 2202632.8927 | 629908.5773 |  |  |  | 44686 | ODOR READS TOOK AT 128 E 3RD ST, MAYSVILLE,KY - WITH SN-16040105 12/17- .6@10:40 - 12/18 .5@16:30 - 12/19 .6@11:30 - 12/20 .5@ 16:29 - 12/21 .5@17:12 - 12/22 .5@16:45 - 12/23 .6@12:27 - TJETT 12/23/21 LEVEL 2 BUDGET VARIANCE COMPLETED AND FILED IN WMSDOCS. D.LEMONS 10/3/2022
20026973800 | RETIRE 6801'-4' CILP | [5 empty] | 1501.61 | 107.2796 | 1394.3304 |  |  |  | 44686
20026974100 | RETIRE 385'- 3" & 4" | [5 empty] | 2639.76 | 8962.6172 | -6322.8572 |  |  |  | 44686
20026975000 | INSTALL 150'-2" PMIP | [5 empty] | 12825.26 | 12346.2686 | 478.9914 |  |  |  | 44235
20026982100 | INSTALL 800'-2" PMIP | [5 empty] | 69244.93 | 47914.5682 | 21330.3618 |  |  |  | 44851
20026992100 | RETIRE STATION | [5 empty] | 0 | 3400.2343 | -3400.2343 |  |  |  | 44672 | RETIRED REGULATOR STATION JMARTIN
21026111600 | INSTALL FENCE | [5 empty] | 21225.79 | 2231 | 18994.79 |  |  |  | 44847 | CCC# 79626 MONITOR FOR FENCE INSTALL. JMARTIN 9-2-22 CCC# 79759 MONITOR FOR FENCE INSTALL
21026118000 | INSTALL 4" SS | [5 empty] | 13617.82 | 29193.606 | -15575.786 |  |  |  | 44330 | 4"SHORTSTOP INSTALLET BY RLA TESTED AND TAPPED BYCOMPANY 90 PSIG 15 MIN TEST NITROGN AS MEDIUM
21026127000 | INSTALL 8021'-2"&4" PMIP | [5 empty] | 2281682.81 | 1234240.1163 | 1047442.6937 |  |  |  | 45084
21026127100 | RETIRE 9400'-2"&4" BS&CS | [5 empty] | 1334.61 | 67.799 | 1266.811 |  |  |  | 45084
21026127200 | INSTALL 2200'-2"&4" PMMP | [5 empty] | 570820.34 | 433097.159 | 137723.181 |  |  |  | 44865 | COST OVERRUN DUE TO PAVING ESTIMATED IN CONTRACT, BUT CAPTURED IN MISC MATE RIALS WITH A DIFFERENCE OF $32,000. SOME ADDITIOANL MATERIALS WERE REQUIRE D THAT WERE NOT ESTIMATED FOR $6,000. SEGA ALSO INCREASED FOR ADDITIONAL $1 8,000. D.LEMONS 1/31/2023 ADDITIONAL $56,000 TRANSFERED FROM RETIREMENT JO THAT WAS ASSOCIATED WITH A DDITIONAL PAVING. D. LEMONS 2/23/2023
21026127300 | RETIRE 2100'-2"&4" BSMP | [5 empty] | 0 | 75.9523 | -75.9523 |  |  |  | 44840
21026127400 | INSTALL 1900'-2"&4" PMIP | [5 empty] | 479284.77 | 236888.6644 | 242396.1056 |  |  |  | 44868 | OVERRUN EXPLANATION LOADED INTO WMSDOCS. D.LEMONS 2/1/2023
21026127500 | RETIRE 1071'-3"&4" WIIP | [5 empty] | 0 | 75.9523 | -75.9523 |  |  |  | 44868
21026127600 | RETIRE 4700'-4" BSLP | [5 empty] | 0 | 67.1085 | -67.1085 |  |  |  | 44865
21026134500 | INSTALL 1537'-2"PMIP | [5 empty] | 332303.55 | 208782.1462 | 123521.4038 |  |  |  | 44799 | SEE PROJECT WORKSPACE 21-81540 FOR PROJECT OVERRUN EXPLANATION. D.LEMONS 10 /26/2022
21026134600 | RETIRE 1053'-2" CSIP | [5 empty] | 0 | 109.7476 | -109.7476 |  |  |  | 44799
21026139300 | RETIRE STATION R-1455 | [5 empty] | 0 | 1061.1136 | -1061.1136 |  |  |  | 44838 | RETIRED REG STATION R1455 W 2ND ST MAYSVILLE JMARTIN 10-4-22
21026139400 | REMOVE BUILDING FOR R-1455 | [5 empty] | 3989.86 | 117.5985 | 3872.2615 |  |  |  | 44944 | BUILDING REMOVED AND CLEANED UP BY PLANT. JMULLINS 1-18-23
21026145800 | REPLACE VALVES ON HP-MP REG | [5 empty] | 33552.7 | 14136.4861 | 19416.2139 |  |  |  | 44762 | CCC# 73837 CCC# 74028 CCC# 74317 REPLACED INLET, OUTLET, AND BOTH BYPASS VLVS ON STATION. JMARTIN 7/20/22
21026145900 | RETIRE 4 VALVES ON REG STATION | [5 empty] | 1355.49 | 600.4497 | 755.0403 |  |  |  | 44762 | INSTALLED TEMPORARY REG SETTING REPLACED ALL FOUR SETTING VALVES JMARTIN 07 -20-2022
21026994200 | RETIRE 3" SERVICE | [5 empty] | 0 | 98.6196 | -98.6196 |  |  |  | 44672
22026159400 | RETIRE S/L | [5 empty] | 2030.55 | 3024.4273 | -993.8773 |  |  |  | 44641
22026165100 | INSTALL 300'-2" PMIP | [5 empty] | 34102.05 | 29167.1057 | 4934.9443 |  |  |  | 44699
22026171800 | INSTALL 3178'-2" PMIP | [5 empty] | 830935.96 | 663052.9501 | 167883.0099 |  |  |  | 45127
22026171900 | RETIRE ~3325'-2" BS,CS & P | [5 empty] | 0 | 83.4538 | -83.4538 |  |  |  | 45127
22026185400 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 1456 | 5480.5156 | -4024.5156 |  |  |  | 44698 | JMARTIN REMOVED OLD ERX AND INSTALLED NEW MIWI 350 5-17-2022
22026185500 | RETIRE COMPONENTS | [5 empty] | 715.54 | 124.5156 | 591.0244 |  |  |  | 44698 | CCC# 67011 NOT ABLE TO COMP AT THIS TIME, HAS OLDER ERX AND NEED MORE PARTS. JMARTIN 5-16-22 CCC# 67183 REPLACE ERX WITH NEW MIWI 350. JMARTIN
22026185600 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 644.24 | 6006.2549 | -5362.0149 |  |  |  | 44732 | CCC# 70942 INSTALL NEW MIWI 350, P2P W/GAS CONTROL OK, JMARTIN 6-20-22
22026185700 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 93.74 | 124.5156 | -30.7756 |  |  |  | 44732 | CCC# 70942 RETIRE ERX AND REPLACE WITH MIWI 350, JMARTIN 6-20-22
22026187000 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 1100.73 | 4357.5409 | -3256.8109 |  |  |  | 44699 | CCC# 67356 REPLACE ERX WITH NEW MIWI 350, P2P OK, JMARTIN CCC# 67669 WORKED TO FIX COMM ISSUE WITH MIWI. CCC# 67669
22026187100 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 0 | 124.5156 | -124.5156 |  |  |  | 44699 | RETIRED OLD ERX JMARTIN 5/18/2022
22026187400 | EXCHANGE ELECTRONIC COMPONENTS | [5 empty] | 1016.56 | 4773.0565 | -3756.4965 |  |  |  | 44701 | CCC# 67055 INSTALL NEW MIWI 350, P2P OK, JMARTIN CCC# 67183
22026187500 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 0 | 124.5156 | -124.5156 |  |  |  | 44701
22026187600 | REPLACE ELECTRONIC COMPONENTS | [5 empty] | 31865.96 | 5349.5438 | 26516.4162 |  |  |  | 44697 | CCC# 67613 REPLACED ERX WITH NEW MIWI 350. P2P OK, JMARTIN CCC# 67613
22026187700 | RETIRE ELECTRONIC COMPONENTS | [5 empty] | 39.46 | 124.5156 | -85.0556 |  |  |  | 44697 | CCC# 67613 RETIRE ERX JMARTIN
22026195800 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 5580.46 | 4801.1928 | 779.2672 |  |  |  | 44803 | CCC# 79192 INSTALL NEW MIWI 350, P2P COMP. JMARTIN 8-30-22
22026195900 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 69.23 | 124.8731 | -55.6431 |  |  |  | 44803 | CCC# 79192 INSTALL NEW MIWI 350, P2P COMP. JMARTIN 8-30-22 RETIRED OLD ERX
22026204100 | RETIRE BUILDING | [5 empty] | 0 | 76.9137 | -76.9137 |  |  |  | 44957 | BUILDING DEMOLISHED BY CONTRACTORS
22026204400 | RETIRE BUILDING | [5 empty] | 0 | 76.9137 | -76.9137 |  |  |  | 44957 | BUILDING DEMOLISHED BY CONTRACTOR
22026205000 | RETIRE ERX | [5 empty] | 0 | 78.4365 | -78.4365 |  |  |  | 44552 | COMPLETED PAPERWORK 12-22-21 JMARTIN
22026206200 | INSTALL 33'-2" PMIP | [5 empty] | 37112.14 | 82983.2827 | -45871.1427 |  |  |  | 44859 | COST UNDERRUN DUE TO PROJECT BEING SIMPLIFIED AFTER START OF CONSTRUCTION. $2000 IN MATERIALS RETURNED AND NOT USED, $26000 IN CONTRACT ESTIMATED BUT NOT USED. ADDITIONAL SAVINGS IN OTHER AND SEGA CATAGORIA ASSOCIATED WITH LO WER COSTS. D. LEMONS 2/23/2023
22026206300 | RETIRE 22'-4" WIIP | [5 empty] | 3252.3 | 83.4538 | 3168.8462 |  |  |  | 44840
22026209201 | RETIRE BUILDING FOR R-1451 | [5 empty] | 3422.43 | 4594.5704 | -1172.1404 |  |  |  | 45001
22026222500 | EMER - INSTALL 5'-6" PMMP | [5 empty] | 5673.45 | 5662.1316 | 11.3184 |  |  |  | 44827
22026222600 | EMER - RETIRE 5'-6" PMMP | [5 empty] | 0 | 74.3089 | -74.3089 |  |  |  | 44827
23026254100 | RETIRE PRESSURE GAUGE | [5 empty] | 72.46 | 552.5683 | -480.1083 |  |  |  | 44960 | CCC# 10600 RETIRED PRESSURE CHART. JMARTIN 2-3-23
23026256800 | RETIRE PAPER GAUGE | [5 empty] | 43.28 | 138.8485 | -95.5685 |  |  |  | 44986 | CCC# 10600 RETIRE PRESSURE CHART, JMARTIN 3-1-23
23026257900 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 1494.37 | 22482.2854 | -20987.9154 |  |  |  | 45114 | CCC# 36022 INSTALL NEW MIWI 350. JMARTIN JHOBBS 7-5-23 CCC#36022
23026258000 | RETIRE PAPER CHART | [5 empty] | 555.95 | 121.7239 | 434.2261 |  |  |  | 45112 | CCC# 36022 RETIRED PAPER CHART. JMARTIN JHOBBS 7-5-23 CCC# 36022
23026258300 | INSTALL VRG CONTROLLER | [5 empty] | 41605.07 | 16195.69 | 25409.38 |  |  |  | #N/A | CCC#94028 VAC TRUCK WAS A NO SHOW CCC# 94512 W/VAC TRUCK CCC#94691 WELDED UP THE TAPS CCC#94691 WELDED TAP TEES ON FOR VRGS NOT ONSITE ORDER IS NOT MINE NOT NEEDED CCC#97247 TOOK OUT OLD CONTROLERS AND INSTALLED NEW VRG CONTROLER J HOBBS J BRADFORD 1700 11-18 24 CCC#97247 FINISH UP BACK FILLING 11-19-24 J HOBBS 1150
23026258400 | RETIRE BRISTOL CONTROL UNIT | [5 empty] | 600.77 | 138.8485 | 461.9215 |  |  |  | #N/A | NO TICKET NEEDED HAD TO FIND PARTS 11-15-2023 J HOBBS 1559
23026286900 | HIGHLAND HEIGHTS BREAK METER | [5 empty] | 40214.72 | 103097.3193 | -62882.5993 |  |  |  | #N/A | CCC 88243 NO TICKET NEED. HAD TO TURN IN PAPER WORK OFF SIGHT 9-20-24
23026287300 | INSTALL 121'-4" CSMP | [5 empty] | 188332.63 | 153650.3163 | 34682.3137 |  |  |  | 45555
23026287400 | RETIRE 98'-4" CSMP | [5 empty] | 0 | 136.633 | -136.633 |  |  |  | #N/A
23026302500 | RETIRE PAPER GAUGE | [5 empty] | 994.29 | 989.8688 | 4.4212 |  |  |  | 45232 | CCC# 50771 MONITOR FOR TC
24026324200 | UPGRADE TO FULL TIME | [5 empty] | 8739.85 | 10901.0487 | -2161.1987 |  |  |  | #N/A | CCC#83588 CCC# 83763 INSTALL SOLAR PANEL AND SWITCH TO CONTINUOUS POLL. JMARTIN 8-7-24
24026324300 | UPGRADE TO FULL TIME | [5 empty] | 92.55 | 121.4465 | -28.8965 |  |  |  | #N/A | CCC# 83763 INSTALLING SOLAR TO MAKE CONTINUOUS POLL, JMARTIN 8-7-24
24026326600 | UPGRADE TO FULL TIME | [5 empty] | 16219.76 | 10901.0487 | 5318.7113 |  |  |  | #N/A | CCC#83806 CCC 83806 CCC# 83806 INSTALL SOLAR FOR CONTINUOUS POLL, JMARTIN 8-7-24
24026326700 | UPGRADE TO FULL TIME | [5 empty] | 142.43 | 121.4465 | 20.9835 |  |  |  | #N/A | CCC# 83806 INSTALL SOLAR FOR CONTINUOUS POLL, JMARTIN 8-7-24
24026351600 | EMER - INSTALL 2'-2" PMMP | [5 empty] | 2939.49 | 5505.7838 | -2566.2938 |  |  |  | 45503
24026351700 | EMER - RETIRE 2'-2" PMP | [5 empty] | 0 | 136.633 | -136.633 |  |  |  | #N/A
24026352800 | INSTALL SS FITTING | [5 empty] | 5512.14 | 24859.1129 | -19346.9729 |  |  |  | 45505
24026352900 | RETIRE 4'-3"&4"CSMP | [5 empty] | 2114.27 | 136.633 | 1977.637 |  |  |  | #N/A
24026357400 | INSTALL 275'-3" CSMP | [5 empty] | 104472.75 | 87056.0137 | 17416.7363 |  |  |  | 45589
24026357500 | RETIRE 265'-3" CSMP | [5 empty] | 0 | 124.2298 | -124.2298 |  |  |  | #N/A
24026366400 | INSTALL ~390'-2" PMIP | [5 empty] | 44902.44 | 64432.6111 | -19530.1711 |  |  |  | 45747
24026373600 | INSTALL SOLAR BACKUP UNIT | [5 empty] | 7104.24 | 9877.4639 | -2773.2239 |  |  |  | #N/A | CCC# 107389. DSASH 2/17/25 1330
18026761400 | INSTALL BULLHORN RMU | [5 empty] | 2699.78 | 3922.4303 | -1222.6503 |  |  |  | 44469 | RMU WAS INSTALLED ON 09/30/2021 BY TIM SWARTS. SYSTEM SERIAL # IS 132395. -OSS
18026770000 | RETIRE CHART | [5 empty] | 3621.11 | 1613.3811 | 2007.7289 |  |  |  | #N/A | RETIRED MANUAL CHART INSTALLED NEW EC350
18026770100 | RETIRE CHART | [5 empty] | 0 | 1613.3811 | -1613.3811 |  |  |  | 44749 | RETIRED PAPER CHART MRYAN 07-07-2022
18026847000 | INSTALL CATALYTIC HEATER | [5 empty] | 3779.78 | 3926.2882 | -146.5082 |  |  |  | 44750 | CC# 49296. 12/21/21 DSASH NO CC# NEEDED, DID NOT GO ON SITE. 12/22/21 DSASH GMB NO CC NEEDED RETIRED OLD CATALYTIC HEATER INSTALLED NEW CATALYTIC HEATER MRAYN 7-8-22
18026847100 | RETIRE CATALYTIC HEATER | [5 empty] | 426.13 | 77.1956 | 348.9344 |  |  |  | 44750 | RETIRED OLD CATALYTIC HEATER INSTALLED NEW CATALYTIC HEATER MRYAN 7-8-2022
18026847200 | INSTALL CATALYTIC HEATER | [5 empty] | 3110.02 | 3926.2882 | -816.2682 |  |  |  | 44750 | RETIRED OLD CATALYTIC HEATER AND INSTALLED NEW CATALYTIC HEATER MRYAN 7-8-2022
18026847300 | RETIRE CATALYTIC HEATER | [5 empty] | 313.52 | 77.1956 | 236.3244 |  |  |  | 44750 | RETIRED CATALYTIC HEATER INSTALLED NEW CATALYTIC HEATER MRYAN 7-8-2022
19026850400 | INSTALL ODORIZATION | [5 empty] | 5241.78 | 6839.1611 | -1597.3811 |  |  |  | #N/A
19026867802 | INSTALL 376'-4" PMIP | [5 empty] | 262651.39 | 112969.7187 | 149681.6713 |  |  |  | 45793
19026867900 | RETIRE 396'-3" P&CS | [5 empty] | 48.51 | 79.9756 | -31.4656 |  |  |  | #N/A
19026875300 | INSTALL ODORIZER | [5 empty] | 9263.2 | 1300.1611 | 7963.0389 |  |  |  | 44834 | INSTALLED ODORIZER BOTTLE JMULLINS 9-30-22
19026875400 | INSTALL ODORIZER | [5 empty] | 1315.89 | 1300.1611 | 15.7289 |  |  |  | 44834 | INSTALLED FARM TAP ODORIZER BOTTLE JMULLINS 9-30-22
20026926200 | INSTALL NETWORK UPGRADE | [5 empty] | 853.47 | 3150 | -2296.53 |  |  |  | 44573 | SUPER SOLAR KIT AND RV50 INSTALLED BY NOLL DAVIS AND ACP PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/12/22
20026926400 | INSTALL NETWORK UPGRADE | [5 empty] | 7131.29 | 3150 | 3981.29 |  |  |  | 44813 | GMB NO CC NEEDED GMB NO CC NEEDED NO CC NEEDED--GMB NO CC NEEDED GMB INSTALLED SOAR,BATTERY,AND MODEM PAPERWORK DONE BY J.MULLINS
20026926600 | INSTALL NETWORK UPGRADE | [5 empty] | 6560.17 | 3150 | 3410.17 |  |  |  | 44802 | NO CC NEEDED GMB INSTALLED NEW SUPER SOLAR KIT MRYAN 8-29-22
20026980000 | INSTALL 675' - 2"/4" PMLP | [5 empty] | 186497.16 | 148515.2952 | 37981.8648 |  |  |  | 44259 | DUE TO WEATHER CONDITION ON STATE ROAD UNABLE TO MAKE COMMIT DATE OVERRUN EXPLANATION: ALL OPEN CUT WAS ESTIMATED, BUT 108 FEET OF DIRECTIONA L BORE WAS USED. ADDITIONALLY, APPROXIMATELY 4 TIMES AS MUCH FLAGGING WAS R EQUIRED THAN ESTIMATED. OVERHEADS INCREASED $10,500 DUE TO THESE OVERAGES.
20026980100 | RETIRE 622' - 2" BSLP | [5 empty] | 647.77 | 103.8156 | 543.9544 |  |  |  | 44259
20026991200 | RETIRE BUILDING | [5 empty] | 0 | 107.2796 | -107.2796 |  |  |  | 44203 | THIS IS PAPER ONLY JOB BUILDING WAS TORN DOWN MANY YEARS AGO THIS JOB IS TO CORRECT CKY RECORDS ONLY FIELD VERIFIED BY CKY ENGINEERING
21026100300 | EMER INS ~15'-2"/3" PMIP/CSIP | [5 empty] | 13138.1 | 15461.5913 | -2323.4913 |  |  |  | 44244 | 3" C.S. MAIN PULLED LOOSE FROM 4 BOLT COUPLING DUE TO STRESS ON MAIN FROM EXPOSURE DOWN STREAM. TAPPED & STOPPED 3" C.S. REPLACED LEAKING SECTION WITH 3" P 20' PRESSURE TEST 90 PSIG 1HR PURGED MAIN LINE, RESTORED SERVICE.
21026100400 | EMER RETIRE ~5'-3" CSIP | [5 empty] | 1505.21 | 1147.7777 | 357.4323 |  |  |  | 44238 | 3" CS MAIN PULLED LOOSE FROM 4 BOLT COUPLING DUE TO STRESS ON MAIN FROM EXPOSURE DOWN STREAM. TAPPED & STOP 3" CS MAIN REPLACED LEAKING SECTION WITH 3" P 20' PRESSURE TEST 90PSIG FOR 1 HR. PURGED MAIN & RESTORED SERVICE
21026121900 | INSTALL 100'-2" PMIP | [5 empty] | 30760.67 | 26223.5353 | 4537.1347 |  |  |  | 44421
21026131400 | INSTALL 300'-2" PMIP | [5 empty] | 158500.46 | 139158.4326 | 19342.0274 |  |  |  | 44511
21026131500 | RETIRE 300'-2" PMIP | [5 empty] | 39.34 | 88.8156 | -49.4756 |  |  |  | 44511
21026136300 | INSTALL 37'-2"/3" PMMP/CSMP | [5 empty] | 14615 | 33826.5433 | -19211.5433 |  |  |  | 44459 | INSTALLED NEW 030 CS AND PE MAIN. TEST @ 90# FOR 1 HR, NO LEAKS. PURGED INT O SERVICE. STOP OFF AND REMOVED OLD MAIN. 3" WELD CAPS & 2" PE CAP SOAP TES T, NO LEAKS. WRAPPED MAIN. SWING TIES & EM BALLS. J HOWARD 9-20-21
21026136400 | RETIRE 29'-2"/3" CSMP/PMMP | [5 empty] | 83.24 | 826.7837 | -743.5437 |  |  |  | 44452 | LEAK ON END OF STEEL MECH COMP END CAP. INSTALLED NEW 030 & 020 ST AND PE M L, TESTED AT 90# FOR 1 HR. SOAP TEST 030 AND 020 CAPS, NO LEAKS. BAR BANKS, NGF. INSTALLED ANODE, WRAPPED MAIN. J HOWARD 9-13-21
21026142800 | INSTALL 475'-4" PMLP | [5 empty] | 138313.25 | 59783.3635 | 78529.8865 |  |  |  | 44680 | TTOY-9/20/22: OVERRUN LEVEL 2 VARIANCE EXPLANATION IN WMSDOCS
21026146701 | INSTALL 100'-2" PMIP | [5 empty] | 6197.36 | 40630.8922 | -34433.5322 |  |  |  | 44803 | VAPIERCE (03/27/23); JOB OVER RUN DUE TO CONTRACT CHARGES ASSOCIATED TO EMERGENCY JOB ORDER 22-0262152-00 EMER-KY FLOODING 2022. $29,900 IN ESTIMATED CONTRACT COSTS AND $0 BOOKED TO THIS JOB ORDER, ALL CONTRACT COSTS WERE CHARGED TO EMER-KY FLOODING 2000 JO. MOST LABOR COSTS WERE ALSO BOOKED UNDER THE EMER JOB ORDER. CONSTRUCTION WAS UNAWARE THIS PLANNED PROJECT OVERLAPPED WITH EMER WORK.
21026994400 | EMER- INSTALL 5'-2" PMIP | [5 empty] | 5176.12 | 7281.2724 | -2105.1524 |  |  |  | 44209 | INSTALLED 6' NEW 020 MDPE ML. TESTED AT 90# 20 MINS. WELD-IN TRANSITIONS. S OAP TEST TIE IN. PURGED AT EOM. SWING TIES AND ELEC MARKERS. J HOWARD 1-13- 21
21026994500 | EMER- RETIRE 5'-2" BSIP | [5 empty] | 1169.82 | 239.0145 | 930.8055 |  |  |  | 44207 | INSTALLED 2 020 TDW SS. TAP AND STOP ML. NO UPSTREAM PRESSURE LOSS. REMOVED AND ABANDONED 6' SECTION OF 020 S ML FOR INSTALL OF 020 MDPE. J HOWARD 1-1 1-21
21026997600 | INSTALL 20'-2" PMIP | [5 empty] | 25490.16 | 28869.525 | -3379.365 |  |  |  | 44286
21026997700 | RETIRE 15'-2" BSIP | [5 empty] | 95.92 | 88.4533 | 7.4667 |  |  |  | 44285
22026158200 | INSTALL 100'-2" PMMP | [5 empty] | 22688.28 | 26700.5988 | -4012.3188 |  |  |  | 44687
22026164600 | EMER - INSTALL 220'-2" PMIP | [5 empty] | 49083.09 | 49188.5426 | -105.4526 |  |  |  | 44614
22026164700 | EMER - RETIRE 20'-4" CSIP | [5 empty] | 140.47 | 109.7476 | 30.7224 |  |  |  | 44614
22026174700 | EMER- INSTALL 82'-4" PMIP/CSIP | [5 empty] | 85702.82 | 94519.5369 | -8816.7169 |  |  |  | 44628 | REPAIRED LEAK ON MAIN BY REPLACING A SECTION OF BARE STEEL MAIN WITH 4" PLA STIC TESTED 105 PSIG FOR 1 HOUR WITH ELECTRONIC KUHLMAN GAUGE SERIAL NO 101 09154 3/8/22 REFER TO 2211 JOB ORDER# 22-9840666-00
22026174800 | EMER- RETIRE 76'-4" BSIP | [5 empty] | 0 | 0 | 0 |  |  |  | 44628
22026175100 | INSTALL 3" OUTLET VALVE | [5 empty] | 44613.77 | 40477.7168 | 4136.0532 |  |  |  | 45070
22026175200 | RETIRE ~10' - 3" CSHP | [5 empty] | 257.25 | 593 | -335.75 |  |  |  | 45070
22026179500 | EMER - INSTALL 5'-2" PMIP | [5 empty] | 2346.49 | 5401.378 | -3054.888 |  |  |  | 44656
22026179600 | EMER - RETIRE 5'-2" P-IP | [5 empty] | 0 | 238.1994 | -238.1994 |  |  |  | 44656
22026189100 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 2559.49 | 4745.0565 | -2185.5665 |  |  |  | 44741 | CC # 70264 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-29-2022
22026189200 | RETIRE ELECTRONIC EQUIPMENT | [5 empty] | 213.04 | 124.5156 | 88.5244 |  |  |  | 44741 | CC # 70264 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-29-2022
22026189300 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 487.15 | 4745.0565 | -4257.9065 |  |  |  | 44726 | CC# 70358 RETIRED BOTH ERX'S INSTALLED NEW MIWI350 MRYAN 6-14-2022
22026189400 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 243.32 | 124.5156 | 118.8044 |  |  |  | 44726 | CC # 70358 RETIRED OLD ERX'S INSTALLED NEW MIWI350 MRYAN 6-14-2022
22026189500 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 292.29 | 4745.0565 | -4452.7665 |  |  |  | 44727 | CC # 70566 RETIRED OLD ERX INSTALLED NEW HONEYWELL MIWI350 MRYAN 6-15-2022
22026189600 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 91.82 | 124.5156 | -32.6956 |  |  |  | 44727 | CC # 70566 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 06-15-2022
22026189700 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 91.91 | 4745.0565 | -4653.1465 |  |  |  | 44727 | CC # 70497 RETIRED OLD ERX INSTALLED NEW MIW350 MRYAN 06-15-2022
22026189800 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 213.04 | 124.5156 | 88.5244 |  |  |  | 44727 | CC # 70497 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-15-2022
22026189900 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 275.74 | 4745.0565 | -4469.3165 |  |  |  | 44742 | CC # 72215 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6/30/2022
22026190000 | RETIRED ELECTRONICS EQUIPMENT | [5 empty] | 61.53 | 124.5156 | -62.9856 |  |  |  | 44742 | CC # 72215 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6/30/2022
22026191100 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 1925.69 | 4801.1928 | -2875.5028 |  |  |  | 44739 | CC # 71822 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-27-2022
22026191200 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 229.57 | 124.8731 | 104.6969 |  |  |  | 44739 | CC # 71822 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-27-2022
22026191500 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 1457.43 | 4801.1928 | -3343.7628 |  |  |  | 44789 | UPGRADED ERX TO MIWI
22026191600 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 447.49 | 124.8731 | 322.6169 |  |  |  | 44789 | CC # 73221 UPGRADDED ERX TO MIWI
22026192700 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 780.12 | 4801.1928 | -4021.0728 |  |  |  | 44740 | CC # 71922 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-28-2022
22026192800 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 82.66 | 124.8731 | -42.2131 |  |  |  | 44740 | CC # 71984 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-28-2022
22026193200 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 271.17 | 4801.1928 | -4530.0228 |  |  |  | 44740 | CC # 71922 RETIRED OLD ERX INSTALLED NEW MIWI 350 MRYAN 6/28/2022
22026193300 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 156.09 | 124.8731 | 31.2169 |  |  |  | 44740 | CC # 71922 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6/28/2022
22026193400 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 1938.82 | 4801.1928 | -2862.3728 |  |  |  | 44790 | CC # 75237 NO CC NOT ONSITE PAPERWORK NO CC NEEDED UPGRADDED ERX TO MIWI JMULLINS
22026193500 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 22.08 | 124.8731 | -102.7931 |  |  |  | 44790 | CC # 75237
22026193600 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 1911.78 | 4801.1928 | -2889.4128 |  |  |  | 44852 | CC # 3865 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 10-18-22
22026193700 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 217.55 | 124.8731 | 92.6769 |  |  |  | 44852 | CC # 3865 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 10-18-22
22026193800 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 1577.79 | 4801.1928 | -3223.4028 |  |  |  | 44781 | CC # 73511
22026193900 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 235.52 | 124.8731 | 110.6469 |  |  |  | 44781 | CC # 73511 UPGRADED TO MIWI JOSH MULLINS
22026194000 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 1673.13 | 4801.1928 | -3128.0628 |  |  |  | 44781 | CC # 73511 UPGRADED FROM ERX TO MIWI JOSH MULLINS
22026194100 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 230.5 | 124.8731 | 105.6269 |  |  |  | 44781 | CC # 73511
22026194200 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 1788.47 | 4801.1928 | -3012.7228 |  |  |  | 44781 | CC # 73334
22026194300 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 470.99 | 124.8731 | 346.1169 |  |  |  | 44781 | CC # 73334 UPDATTED ERX TO MIWI 07-13-22 J. MULLINS
22026194400 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 356.51 | 4801.1928 | -4444.6828 |  |  |  | 44742 | CC # 72268 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-30-2022
22026194500 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 1.84 | 124.8731 | -123.0331 |  |  |  | 44742 | CC # 72268 RETIRED OLD ERX INSTALLED NEW MIWI 350 MRYAN 6-30-2022
22026196000 | EXCHANGE ELECTRONIC EQUIPMENT | [5 empty] | 6078.6 | 4801.1928 | 1277.4072 |  |  |  | 44769 | CC # 75237 RETIRED OLD ERX AND INSTALLED NEW HONEYWELL MIWI350 MRYAN 7-27-2022
22026196100 | RETIRED ELECTRONIC EQUIPMENT | [5 empty] | 232.52 | 124.8731 | 107.6469 |  |  |  | 44769 | CC # 75237 RETIRED OLD ERX INSTALLED NEW HONEY WELL MIWI350 MATT RYAN 7-27-2022
22026209100 | RETIRE METER | [5 empty] | 1187.88 | 136.5602 | 1051.3198 |  |  |  | #N/A | NO CC NEEDED---GMB ACCOUNT MCR 10-6-23 1600 METER READY TO BE REMOVED INLET OUTLET BLIND FLNGD
22026216500 | EMER-INSTALL 2"/4" POLY VALVES | [5 empty] | 433396.83 | 298130.9642 | 135265.8658 |  |  |  | 44784 | COMPLETED OVERRUN EXPLANATION FORM LOADED INTO WMSDOCS JO WORKSPACE. D.LEMO NS 2/24/2023
22026216600 | EMER-RETIRE 7'-2"/4" PMIP/CSIP | [5 empty] | 0 | 83.4538 | -83.4538 |  |  |  | 44784
22026216700 | EMER - INSTALL 456'-4" CS/PMIP | [5 empty] | 85192.39 | 50625 | 34567.39 |  |  |  | 44874
22026216801 | EMER-RETIRE 130'-4" CS/BS/PIP | [5 empty] | 439.01 | 132.427 | 306.583 |  |  |  | 44874
22026218600 | INSTALL NEW 1ST CUT REGULATOR | [5 empty] | 3338.51 | 2521.2589 | 817.2511 |  |  |  | 45236 | NOT ONSITE NO CC NEEDED GETTING MATERIAL/BUILDING REG PREPING FOR JOB MCR CC # 51243 INSTALLD NEW 1ST CUT REG DUE TO CORROSION MCR 11-6-23 1445 CC # 51776 ISTALLD TUBING ANF PAINTED SETTIN FIELD WORK COMPLETE
22026218700 | RETIRE 1ST CUT REGULATOR | [5 empty] | 1644.86 | 84.9152 | 1559.9448 |  |  |  | 45236 | CC # 51243 REMOVED OLD FIRST CUT REG MCR 11-6-23 1030
22026218900 | INSTALL NEW METER | [5 empty] | 17499.51 | 6441.3422 | 11058.1678 |  |  |  | #N/A | CCC NOT NEEDED--GMB MCR 6-18-24 1500
22026241900 | INSTALL 249'-2" PMIP | [5 empty] | 101153.64 | 81974.2921 | 19179.3479 |  |  |  | 45000
22026242000 | RETIRE 135'-3" BSIP | [5 empty] | 139.7 | 117.5985 | 22.1015 |  |  |  | 45000
23026256300 | INSTALL 130'-2" PMIP | [5 empty] | 19141.35 | 38002.449 | -18861.099 |  |  |  | 45128
23026261300 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 4877.76 | 26706.2854 | -21828.5254 |  |  |  | 45117 | CC # 36552 INSTALLD MIWI NO CC NOT ONSITE--PAPER WORK
23026261400 | RETIRE PAPER CHART | [5 empty] | 0 | 121.7239 | -121.7239 |  |  |  | 45117
23026261500 | INSTALL MIWI AND SUPER SOLAR | [5 empty] | 4069.95 | 26706.2854 | -22636.3354 |  |  |  | 45118 | CC # 36725 NO CC NEEDED---GMB ACCOUNT NOT ON SITE NO CC NEEDED---PAPERWORK OFF SITE CC # 40724
23026261600 | RETIRE PAPER CHART | [5 empty] | 388.77 | 121.7239 | 267.0461 |  |  |  | 45118 | CC # 36725
23026265300 | INSTALL PILOT REGULATORS | [5 empty] | 9398.99 | 7328.1838 | 2070.8062 |  |  |  | #N/A
23026274600 | EMER - INSTALL 5'-2" PMIP | [5 empty] | 2867.86 | 11073.0623 | -8205.2023 |  |  |  | 45057
23026274700 | EMER - INSTALL 5'-2" PM | [5 empty] | 0 | 116.0664 | -116.0664 |  |  |  | 45057
23026275800 | INSTALL NEW BATTERY/EQUIPMENT | [5 empty] | 135.94 | 2819.6093 | -2683.6693 |  |  |  | 45069
23026275900 | RETIRE BATTERY FACILITY | [5 empty] | 0 | 139.1159 | -139.1159 |  |  |  | 45063
23026282000 | INSTALL 40'-4" PMIP | [5 empty] | 49257.58 | 63454.1516 | -14196.5716 |  |  |  | 45125
23026282100 | RETIRE 36'-4" BSIP | [5 empty] | 124.74 | 139.1159 | -14.3759 |  |  |  | 45125
23026291200 | EMER - INSTALL 8'-3" PMIP | [5 empty] | 51206.39 | 32593.7477 | 18612.6423 |  |  |  | 45177 | INSTALLED 3INCH PLASTIC MAIN SECTION TO REPLACE LEAKING 3 INCH BS MAIN JCK 9.8.23
23026291300 | EMER - RETIRE 7'3" BS&P | [5 empty] | 392.93 | 119.4953 | 273.4347 |  |  |  | 45177 | ABANDON LEAKING METAL MAIN. INSTALLED 3 INCH PLASTIC MAIN JCK 9.8.23
23026302100 | RETIRE PAPER GAUGE | [5 empty] | 306.23 | 989.8688 | -683.6388 |  |  |  | 45212
23026302200 | RETIRE PAPER GAUGE | [5 empty] | 1131.38 | 989.8688 | 141.5112 |  |  |  | 45264
23026306500 | INSTALL DRIP TANK | [5 empty] | 22554.83 | 21571.6224 | 983.2076 |  |  |  | #N/A | NO CC NEEDED NOT ONSITE-- GATHERIN MATERIAL TO INSTALL MCR 2-5-24 1600 NO CC NEEDED CC # 57053 MCR 2-6-24 1600 CC # 57053 CC 57053 NO CC NEEDED. MATERIAL PICKUP. CC # 57053 DRIP INSTALLED MCR 2-15-2024 1500 CC # 50753
23026307300 | INSTALL ~100'-2" PMIP | [5 empty] | 40892.69 | 23189 | 17703.69 |  |  |  | 45323
24026311300 | EMER - INSTALL 2" 461S | [5 empty] | 2699.35 | 2282.9666 | 416.3834 |  |  |  | #N/A | CC # 57053 INSTLLD REGS MCR 1-22-24 1330 CC 57053 NO CC NEEDED NOT ONSITE-- CO PAPERWORK TO SEND TO WADE MCR 1-26-24 1000 NO CC NEEDED NOT ONSITE PAPAER WORK OFF SITE MCR 2-5-24 1205
24026311400 | EMER - RETIRE 2" MOONEYS | [5 empty] | 721.94 | 59.4493 | 662.4907 |  |  |  | #N/A | CC # 57053 REMOVED MOONEYS MCR 1-22-24 1030 CC 57053
24026317800 | EMER - INSTALL 5'-2" PMIP | [5 empty] | 8355.27 | 6092.2548 | 2263.0152 |  |  |  | 45338 | INSTALLED NEW 020 P ML. TESTED @ 90# 1 HOUR. SOAP TEST TIE IN COUPLING. MAR KER BALL AT EOM. J HOWARD 2-16-24
24026317900 | EMER - RETIRE 5'-2" PIP | [5 empty] | 162.78 | 160.3697 | 2.4103 |  |  |  | #N/A
24026320600 | INSTALL ERX BATTERY | [5 empty] | 2726.43 | 3894.6442 | -1168.2142 |  |  |  | #N/A
24026320700 | RETIRE ERX BATTERY | [5 empty] | 0 | 160.3697 | -160.3697 |  |  |  | #N/A
24026333600 | INSTALL 75'-2" PMIP | [5 empty] | 28387.83 | 31694.159 | -3306.329 |  |  |  | 45547
24026342600 | EMER ABANDON 200' OF 2" BSIP | [5 empty] | 5344.92 | 7907.5865 | -2562.6665 |  |  |  | #N/A
24026345800 | INSTALL 1400'-2" PMIP | [5 empty] | 263557.02 | 300748.5042 | -37191.4842 |  |  |  | 45749
24026345900 | RETIRE 1200'-2"/4" PA/BS/CS IP | [5 empty] | 0 | 76.7529 | -76.7529 |  |  |  | #N/A
24026347600 | EMER - INSTALL 7'-2" PMIP | [5 empty] | 6613.86 | 6644.7043 | -30.8443 |  |  |  | 45453
24026347700 | EMER -RETIRE 7'-2" PMIP | [5 empty] | 0 | 136.633 | -136.633 |  |  |  | #N/A
24026362700 | INSTALL EC-350 FOR GMB | [5 empty] | 0 | 159.2637 | -159.2637 |  |  |  | #N/A | INSTALLED EC350 REPLACE MANUAL CHART
24026367700 | INSTALL NEW EC-350 UNIT | [5 empty] | 706.81 | 6063.7288 | -5356.9188 |  |  |  | #N/A | CCC NOT NEEDED GMB ACCNT MCR 11-8-24 1530 INSTALLED NEW EC350
24026367800 | RETIRE EME UNIT | [5 empty] | 379.26 | 135.7529 | 243.5071 |  |  |  | #N/A | CCC NOT NEEDED GMB ACCNT MCR 11-8-24 1100 RETIRED MINI AT INSTALLED NEW EC350
24026375700 | INSTALL FLOAT SWITCH | [5 empty] | 1897.47 | 2988.4639 | -1090.9939 |  |  |  | #N/A | CCC 108219 INSTALLED FLOAT SWITCH WITH ACP 2-25-25 1300 TAX DISTRICT IS INCORRECT IN WMS, MAPPED CORRECTLY IN GIS. PER SYLVIA MORRISON LEAVE AS IS FOR NOW, FCA WILL BE NEEDED IN FUTURE CORRECT TAXING DISTRICT IS 1957702
24026375800 | INSTALL FLOAT SWITCH | [5 empty] | 2733.24 | 2988.4639 | -255.2239 |  |  |  | #N/A | CCC 108219 INSTLLD FLOAT SWITCH WITH ACP MCR 2-2-5-25 1200
24026375900 | INSTALL FLOAT SWITCH | [5 empty] | 2210.8 | 2988.4639 | -777.6639 |  |  |  | #N/A | CCC 108219 INSTLLD FLOAT SWITCHES WITH ACP MCR 2-25-25 1530
25026394000 | EMER INSERT 280'-1.2" PMIP | [5 empty] | 2217.44 | 34665.9445 | -32448.5045 |  |  |  | 45726 | INSERTED 280' 1.25" PMIP INTO 2" CASING. TOTAL INSTALL 287'. TESTED AT 90 P SIG FOR 20 MINS W/ FOL APPROVAL. EM BALLS AND TWS INSTALLED. OTHER JOB ORDE R FOR RETIRE 25026394100. J HOWARD 3-10-25
25026394100 | EMER - RETIRE 284'-2"BSIP | [5 empty] | 19.19 | 181.0849 | -161.8949 |  |  |  | #N/A | ABND 284FT OF 020 S. 268FT USED FOR CASING OF 280FT OF 0125 CARRIER PIPE. I NSTALL JOB ORDER 25026394000. J HOWARD 3-10-25
25026396000 | INSTALL CAT HEATER | [5 empty] | 0 | 8040.0756 | -8040.0756 |  |  |  | #N/A | CCC# 107424 2/17/25 JAMES PASLEY
25026396100 | RETIRE CAT HEATER | [5 empty] | 0 | 160.2249 | -160.2249 |  |  |  | #N/A
25026398400 | EMER - INSTALL FITTINGS | [5 empty] | 6860.25 | 11221.5028 | -4361.2528 |  |  |  | 45740
25026398500 | EMER - RETIRE 50'-4" CSIP | [5 empty] | 0 | 160.2249 | -160.2249 |  |  |  | #N/A
ANC32.0000.00050 | BLUE RIDGE 2025 SMRP CNV-23026290600 | [5 empty] | 1780369 | 1314824 | 465545 | 2025-01-01 | 2025-12-31 | 2025-07-07 | 2025-12-23
ANC32.0000.00049 | LEX SUNSET DR 2025 SMRP CNV-23026290300 | [5 empty] | 1353303 | 924157 | 429146 | 2025-01-01 | 2025-12-31 | 2025-09-02 | 2025-12-31
GRT32.0000.00134 | ACE HARDWARE MIDWAY | [5 empty] | 382863.3 | 46804.6 | 336058.7 | 2025-01-01 | 2025-12-31 | 2025-09-02 | 2025-10-31
ANC32.0000.00198 | MONTCLAIR/COOPER 2025 SMRP CNV-220262388 | [5 empty] | 1590817 | 1271603 | 319214 | 2025-01-01 | 2025-12-31 | 2025-08-01 | 2025-12-01
GRT32.0000.00098 | CNV-24026314400 INSTALL 1,200'-4\\\ PM. | [5 empty] | 441793 | 166742 | 275051 | 2025-01-01 | 2025-12-31 | 2025-03-31 | 2025-04-11
ANC32.0000.00200 | RIVERSIDE 2025 SMPR -CNV-23026293500 | [5 empty] | 397969.27 | 149415.74 | 248553.53 | 2025-01-01 | 2025-12-31 | 2025-07-29 | 2025-10-01
PIG32.0000.00059 | EMER - Dixon St- Ashland | [5 empty] | 293936.73 | 49189.54 | 244747.19 | 2025-01-01 | 2025-12-31 | 2025-09-22 | 2025-09-24
ANC32.0000.00289 | ELM TREE 2025 SMRP CROSSBORE CNV-2402636 | [5 empty] | 275901.46 | 55039.42 | 220862.04 | 2025-01-01 | 2025-12-31 | 2025-11-21 | 2025-12-31
ANC32.0000.00180 | CNV-22026171600 INSTALL 4371'-2\"&4\" PM | [5 empty] | 399600.77 | 192726.47 | 206874.3 | 2025-01-01 | 2025-12-31 | 2025-07-18 | 2025-12-31
22026236501 | INSTALL 1325' OF 4"/8"CSHP MN | [5 empty] | 1407086.76 | 1205185.7862 | 201900.9738 | 2025-01-01 | 2025-12-31 | 2025-04-01 | 2025-05-29
GRT32.0000.00120 | GRT - 2804 PLEASANT AVE MLE - ASHLAND | [5 empty] | 217321.22 | 30420.98 | 186900.24 | 2025-01-01 | 2025-12-31 | 2025-10-01 | 2025-10-31
ANC32.0000.00141 | FAYETTE PARK 2025 SMRP CNV-24026317600 | [5 empty] | 232457.82 | 51053.85 | 181403.97 | 2025-01-01 | 2025-12-31 | 2025-11-04 | 2025-12-31
ANC32.0000.00147 | ANC-SMRP E Main St-Mt Sterling | [5 empty] | 218977.66 | 42430.62 | 176547.04 | 2025-01-01 | 2025-12-31 | 2025-06-26 | 2025-07-31
ANC32.0000.00154 | CNV-25026404000 SMRP - INSTALL 650'-2\" | [5 empty] | 202446.55 | 31956.67 | 170489.88 | 2025-01-01 | 2025-12-31 | 2025-08-01 | 2025-08-29
ANC32.0000.00054 | SMRP JESSELIN DR 2025 CNV 24-0263154-00 | [5 empty] | 901632 | 734748 | 166884 | 2025-01-01 | 2025-12-31 | 2025-08-05 | 2025-12-31
GRT32.0000.00121 | GRT-Paddocks of Frankfort MLE | [5 empty] | 753323.74 | 596391.42 | 156932.32 | 2025-01-01 | 2025-12-31 | 2025-09-02 | 2025-12-31
BET32.0000.00027 | CNV-19026867802 INSTALL 376'-4\\\" PMIP. | [5 empty] | 159322.32 | 11431.35 | 147890.97 | 2025-01-01 | 2025-12-31 | 2025-09-11 | 2025-09-30
BET32.0000.00025 | CNV-25026382100 INSTALL 110'-4\" PMLP | [5 empty] | 348136.85 | 211351.06 | 136785.79 | 2025-01-01 | 2025-12-31 | 2025-10-17 | 2025-10-30
GRT32.0000.00096 | GRT-Bourbon Oaks Phase 1 MLE-Paris | [5 empty] | 139902.91 | 9884.28 | 130018.63 | 2025-01-01 | 2025-12-31 | 2025-06-20 | 2025-08-05
ANC32.0000.00157 | CNV-18026794401 INSTALL 4400'-2\"/4\"PMM | [5 empty] | 179679.93 | 53023.77 | 126656.16 | 2025-01-01 | 2025-12-31 | 2025-06-30 | 2025-12-31
GRT32.0000.00126 | Fortune Dr Frankfort Tierney MLE | [5 empty] | 208369.03 | 85824.43 | 122544.6 | 2025-01-01 | 2025-12-31 | 2025-08-07 | 2025-12-31
ANC32.0000.00163 | CNV-21026152101 INSTALL 535' OF 8\\\"CS. | [5 empty] | 118307.58 | 788 | 117519.58 | 2025-01-01 | 2025-12-31 | 2025-12-02 | 2025-12-31
PIG32.0000.00053 | Install 965'-4" PMMP | [5 empty] | 271321.62 | 156088.43 | 115233.19 | 2025-01-01 | 2025-12-31 | 2025-08-08 | 2025-09-26
GRT32.0000.00020 | GRT-Locust Hill Acres MLE-Winchester | [5 empty] | 163090.85 | 59513.98 | 103576.87 | 2025-01-01 | 2025-12-31 | 2025-09-11 | 2025-10-31
ANC32.0000.00264 | CNV-24026333201 EMER - INSTALL 478'-4\\. | [5 empty] | 205447 | 106609 | 98838 | 2025-01-01 | 2025-12-31 | 2025-02-17 | 2025-02-28
GRT32.0000.00097 | CNV-24026340200 INSTALL 600' OF 8\\\PM. | [5 empty] | 388585 | 296422 | 92163 | 2025-01-01 | 2025-12-31 | 2025-01-08 | 2025-01-31
GRT32.0000.00135 | Ball Homes Payne Crossing P2 Versailles | [5 empty] | 250951.48 | 164510.5 | 86440.98 | 2025-01-01 | 2025-12-31 | 2025-09-04 | 2025-09-04
ANC32.0000.00250 | WILSON ST SMRP - CNV-24026315000 | [5 empty] | 135400.19 | 49600.16 | 85800.03 | 2025-01-01 | 2025-12-31 | 2025-10-21 | 2025-12-31
PIG32.0000.00028 | CNV-24026376901 INSTALL 1218'-6\" PMMP | [5 empty] | 707095 | 626566 | 80529 | 2025-01-01 | 2025-12-31 | 2025-02-28 | 2025-04-30
ANC32.0000.00194 | SMRP LAFAYETTE HS | [5 empty] | 1322123.24 | 1246000 | 76123.24 | 2025-01-01 | 2025-12-31 | 2025-08-05 | 2025-12-31
GRT32.0000.00078 | DYER COVE MLE CNV-25026398900 | [5 empty] | 83056.5 | 7741 | 75315.5 | 2025-01-01 | 2025-12-31 | 2025-08-25 | 2025-09-15
GRT32.0000.00056 | GRT-BALL HOMES PENINSULA DOCKSIDE-LEX | [5 empty] | 79755.73 | 14249.76 | 65505.97 | 2025-01-01 | 2025-12-31 | 2025-11-18 | 2025-12-31
GRT32.0000.00002 | CNV-25026381700 INSTALL 230' OF 2\\\ P. | [5 empty] | 89700 | 29657 | 60043 | 2025-01-01 | 2025-12-31 | 2025-02-04 | 2025-02-07
GRT32.0000.00145 | GRT-TURNER COMMONS MLE-LEXINGTON | [5 empty] | 133757.7 | 81269.6 | 52488.1 | 2025-01-01 | 2025-12-31 | 2025-10-28 | 2025-12-01
ANC32.0000.00017 | 2621-TRAFTON SMRP-LEXINGTON | [5 empty] | 73009.05 | 21372.5 | 51636.55 | 2025-01-01 | 2025-12-31 | 2025-07-17 | 2025-08-18
BET32.0000.00052 | 2621 - STA 1073 VALVE REP - LEXINGTON | [5 empty] | 88181.36 | 38892.59 | 49288.77 | 2025-01-01 | 2025-12-31 | 2025-08-18 | 2025-09-25
PIG32.0000.00030 | CNV-24026370200 INSTALL 1415'-2\" PMMP | [5 empty] | 164287 | 125756 | 38531 | 2025-01-01 | 2025-12-31 | 2025-04-24 | 2025-05-30
GRT32.0000.00143 | 2621-50 & 52 LANTERN WAY-NICHOLASVILLE | [5 empty] | 60519.1 | 22677.35 | 37841.75 | 2025-01-01 | 2025-12-31 | 2025-10-09 | 2025-10-23
ANC32.0000.00085 | CNV-24026369000 INSTALL 65'-8\" PMLP | [5 empty] | 144967 | 108435 | 36532 | 2025-01-01 | 2025-12-31 | 2025-07-18 | 2025-07-31
PIG32.0000.00016 | UK PMMP RELOCATION-25026402500 | [5 empty] | 159024 | 122594 | 36430 | 2025-01-01 | 2025-12-31 | 2025-07-16 | 2025-07-31
ANC32.0000.00260 | CNV-24026331601 INSTALL 475' OF 2\"PMMP | [5 empty] | 142820 | 110575 | 32245 | 2025-01-01 | 2025-12-31 | 2025-04-15 | 2025-04-30
GRT32.0000.00122 | BALL HOMES - MASTERSON HILLS MLE | [5 empty] | 136154.07 | 104240.51 | 31913.56 | 2025-01-01 | 2025-12-31 | 2025-09-03 | 2025-10-18
ANC32.0000.00271 | CNV-24026347300 EMER - INSTALL 12'-3\" P | [5 empty] | 52750 | 21463 | 31287 | 2025-01-01 | 2025-12-31 | 2025-02-24 | 2025-02-28
BET32.0000.00046 | CNV-24026368800 INSTALL 5' OF 6\\\ PML. | [5 empty] | 53925 | 22845 | 31080 | 2025-01-01 | 2025-12-31 | 2025-06-26 | 2025-06-30
GRT32.0000.00062 | BALL HOMES ROSE RIDGE PH 2 NB | [5 empty] | 49509.72 | 23249.7 | 26260.02 | 2025-01-01 | 2025-12-31 | 2025-07-16 | 2025-09-02
PIG32.0000.00043 | CNV-24026328800 NEWTOWN PIKE MP RELOCATI | [5 empty] | 1540784.41 | 1516637 | 24147.41 | 2025-01-01 | 2025-12-31 | 2025-07-09 | 2025-10-03
BET32.0000.00042 | CNV-24026341000 INSTALL 300'OF 2\" PMIP | [5 empty] | 23226.43 | 1109.39 | 22117.04 | 2025-01-01 | 2025-12-31 | 2025-04-24 | 2025-04-30
GRT32.0000.00076 | CNV-25026408500 INSTALL ANODE BED FOR D. | [5 empty] | 26719 | 6419 | 20300 | 2025-01-01 | 2025-12-31 | 2025-12-31 | 2025-12-31
GRT32.0000.00107 | CNV-25026381800 INSTALL 250'-2\" PMMP | [5 empty] | 52356 | 32186 | 20170 | 2025-01-01 | 2025-12-31 | 2025-04-09 | 2025-04-11
ANC32.0000.00282 | CNV-24026356000 INSTALL 475' OF 2\\\PM. | [5 empty] | 138118 | 124486 | 13632 | 2025-01-01 | 2025-12-31 | 2025-10-31 | 2025-12-01
ANC32.0000.00286 | CNV-24026362000 EMER-INSTALL 3' OF 3\"PM | [5 empty] | 18283 | 5267 | 13016 | 2025-01-01 | 2025-12-31 | 2025-11-26 | 2025-11-30
GRT32.0000.00104 | CNV-24026359401 INSTALL 200' OF 4\" PMIP | [5 empty] | 61986 | 49205 | 12781 | 2025-01-01 | 2025-12-31 | 2025-02-13 | 2025-02-19
ANC32.0000.00071 | CNV-24026344300 EMER-INSTALL 6' OF 4\" P | [5 empty] | 12417.86 | 0 | 12417.86 | 2025-01-01 | 2025-12-31 | 2025-07-31 | 2025-07-31
ANC32.0000.00146 | GRT-Adena Dr MLE-Mt Sterling | [5 empty] | 80873.14 | 71358.4 | 9514.74 | 2025-01-01 | 2025-12-31 | 2025-07-28 | 2025-08-09
ANC32.0000.00288 | CNV-24026365300 EMER INSTALL 5\" OF 4\" | [5 empty] | 26234 | 17482 | 8752 | 2025-01-01 | 2025-12-31 | 2025-06-25 | 2025-06-30
GRT32.0000.00077 | CNV-25026392000 INSTALL 140'-2\" PMMP | [5 empty] | 21515 | 12869 | 8646 | 2025-01-01 | 2025-12-31 | 2025-02-27 | 2025-05-28
BET32.0000.00024 | CNV-25026403100 EMER - RETIRE 2'-3\" PAM | [5 empty] | 11554.81 | 3218.22 | 8336.59 | 2025-01-01 | 2025-12-31 | 2025-04-07 | 2025-04-07
ANC32.0000.00263 | CNV-24026332800 EMER - INSTALL 5'-4\" PM | [5 empty] | 8388 | 3665 | 4723 | 2025-01-01 | 2025-12-31 | 2025-02-27 | 2025-02-28
GRT32.0000.00066 | CNV-24026372000 INSTALLING 500'-2\" PMMP | [5 empty] | 47890 | 43811 | 4079 | 2025-01-01 | 2025-12-31 | 2025-02-28 | 2025-03-14
GRT32.0000.00105 | CNV-24026361400 INSTALL 100' OF 2\\\ P. | [5 empty] | 28090 | 24014 | 4076 | 2025-01-01 | 2025-12-31 | 2025-02-12 | 2025-02-16
ANC32.0000.00316 | Abandon ~279'-2" BSIP | [5 empty] | 6303.25 | 2651.7 | 3651.55 | 2025-01-01 | 2025-12-31 | 2025-08-15 | 2025-11-28
ANC32.0000.00063 | CNV-24026332600 EMER INSTALL 10'-6\" PMM | [5 empty] | 32431 | 29701 | 2730 | 2025-01-01 | 2025-12-31 | 2025-03-20 | 2025-03-31
ANC32.0000.00114 | CNV-25026381500 EMER - RETIRE ~870'-3\" | [5 empty] | 4189.61 | 2276.13 | 1913.48 | 2025-01-01 | 2025-12-31 | 2025-01-27 | 2025-01-30
ANC32.0000.00152 | CNV-25026406300 INSTALL 15'-6\" PMLP | [5 empty] | 2035.9 | 203.85 | 1832.05 | 2025-01-01 | 2025-12-31 | 2025-05-01 | 2025-05-04
PIG32.0000.00015 | CNV-25026378600 INSTALL 42' OF 2\"/4\" P | [5 empty] | 26011 | 24410 | 1601 | 2025-01-01 | 2025-12-31 | 2025-02-26 | 2025-03-01
ANC32.0000.00068 | CNV-24026338200 EMER - INSTALL 5'-3\" PM | [5 empty] | 5210.66 | 3698 | 1512.66 | 2025-01-01 | 2025-12-31 | 2025-01-30 | 2025-01-31
GRT32.0000.00065 | CNV-24026368600 INSTALL 640' OF 2\\\ P. | [5 empty] | 50385 | 48982 | 1403 | 2025-01-01 | 2025-12-31 | 2025-05-23 | 2025-08-03
GRT32.0000.00040 | CNV-23026288901 INSTALL 880'-4\" PMMP | [5 empty] | 232364 | 231086 | 1278 | 2025-01-01 | 2025-12-31 | 2025-07-31 | 2025-09-16
ANC32.0000.00095 | CNV-25026397400 EMER-INSTALL 3' OF 2\"PM | [5 empty] | 7928 | 6833 | 1095 | 2025-01-01 | 2025-12-31 | 2025-07-01 | 2025-07-01
BET32.0000.00018 | CNV-24026356800 REPLACE 20'-6\" CSLP | [5 empty] | 1069.37 | 0 | 1069.37 | 2025-01-01 | 2025-12-31 | 2025-12-30 | 2025-12-31
PIG32.0000.00007 | CNV-23026301200 INSTALL 60' OF 6\"PMMP M | [5 empty] | 43879 | 42818 | 1061 | 2025-01-01 | 2025-12-31 | 2025-03-26 | 2025-04-01
ANC32.0000.00274 | CNV-24026349700 EMER INSTALL 2' OF 2\" P | [5 empty] | 6054 | 5243 | 811 | 2025-01-01 | 2025-12-31 | 2025-03-31 | 2025-03-31
ANC32.0000.00086 | CNV-24026371100 EMER-INSTALL 6' OF 8\"PM | [5 empty] | 5337 | 5614 | -277 | 2025-01-01 | 2025-12-31 | 2025-07-01 | 2025-07-01
BET32.0000.00053 | EMER - Install 10'-2" PMMP | [5 empty] | 0 | 455.12 | -455.12 | 2025-01-01 | 2025-12-31 | 2025-08-18 | 2025-08-18
GRT32.0000.00108 | CNV-25026398800 INSTALL 3670' OF 2\"/4\" | [5 empty] | 130345 | 130832 | -487 | 2025-01-01 | 2025-12-31 | 2025-05-02 | 2025-05-30
ANC32.0000.00091 | CNV-24026375200 EMER-INSTALL 6' OF 2\"PM | [5 empty] | 6851 | 7800 | -949 | 2025-01-01 | 2025-12-31 | 2025-08-29 | 2025-08-31
ANC32.0000.00281 | CNV-24026355400 EMER-INSTALL 2' OF 2\"PM | [5 empty] | 4651 | 5647 | -996 | 2025-01-01 | 2025-12-31 | 2025-10-31 | 2025-10-31
ANC32.0000.00097 | CNV-25026399300 EMER - INSTALL 5'-2\" PM | [5 empty] | 2298 | 3695 | -1397 | 2025-01-01 | 2025-12-31 | 2025-11-26 | 2025-11-30
ANC32.0000.00077 | CNV-24026357700 EMER-INSTALL 2' OF 3\"PM | [5 empty] | 13807 | 15212 | -1405 | 2025-01-01 | 2025-12-31 | 2025-10-28 | 2025-10-31
ANC32.0000.00339 | EMER-10th Street-Catlettsburg | [5 empty] | 2.8 | 1792.45 | -1789.65 | 2025-01-01 | 2025-12-31 | 2025-12-04 | 2025-12-19
ANC32.0000.00285 | CNV-24026357000 EMER-INSTALL 50' OF 4\"P | [5 empty] | 19571 | 21586 | -2015 | 2025-01-01 | 2025-12-31 | 2025-11-24 | 2025-11-30
GRT32.0000.00064 | CNV-24026365700 INSTALL 320' OF 2\\\PM. | [5 empty] | 29755 | 31922 | -2167 | 2025-01-01 | 2025-12-31 | 2025-01-02 | 2025-01-10
GRT32.0000.00075 | CNV-25026407800 EMER - INSTALL 5'-2\" PM | [5 empty] | 1605 | 4099 | -2494 | 2025-01-01 | 2025-12-31 | 2025-05-13 | 2025-05-13
ANC32.0000.00075 | CNV-24026351600 EMER - INSTALL 2'-2\" PM | [5 empty] | 2939 | 5506 | -2567 | 2025-01-01 | 2025-12-31 | 2025-03-28 | 2025-03-31
GRT32.0000.00055 | CNV-24026352000 INSTALL 700'-2\\\ PMMP. | [5 empty] | 75787 | 78414 | -2627 | 2025-01-01 | 2025-12-31 | 2025-01-24 | 2025-01-30
ANC32.0000.00317 | 2629-EMER 499 Indian mound-Mt Sterling | [5 empty] | 0 | 2723.68 | -2723.68 | 2025-01-01 | 2025-12-31 | 2025-08-15 | 2025-12-31
BET32.0000.00013 | CNV-25026377600 EMER-INSTALL 4' OF 2\"PM | [5 empty] | 8999 | 11901 | -2902 | 2025-01-01 | 2025-12-31 | 2025-05-29 | 2025-06-01
GRT32.0000.00118 | 2629-Patsy Way MLE-Mt Sterling | [5 empty] | 23675.7 | 26720.71 | -3045.01 | 2025-01-01 | 2025-12-31 | 2025-07-31 | 2025-10-30
ANC32.0000.00150 | CNV-25026405400 EMER - INSTALL 2'-2\" PM | [5 empty] | 3579 | 7065 | -3486 | 2025-01-01 | 2025-12-31 | 2025-06-30 | 2025-07-01
ANC32.0000.00099 | CNV-25026400500 EMER - INSTALL 5'-2\" PM | [5 empty] | 4234 | 7746 | -3512 | 2025-01-01 | 2025-12-31 | 2025-11-25 | 2025-11-30
PIG32.0000.00011 | CNV-24026361300 INSTALL 750'-2\\\ PMMP. | [5 empty] | 206115 | 209702 | -3587 | 2025-01-01 | 2025-12-31 | 2025-03-04 | 2025-03-30
ANC32.0000.00283 | CNV-24026356200 INSTALL NEW 4\" CRITICAL | [5 empty] | 6238 | 9923 | -3685 | 2025-01-01 | 2025-12-31 | 2025-10-31 | 2025-12-01
ANC32.0000.00275 | CNV-24026351400 EMER - INSTALL 2'-2\" PM | [5 empty] | 1847 | 5751 | -3904 | 2025-01-01 | 2025-12-31 | 2025-03-31 | 2025-03-31
ANC32.0000.00295 | CNV-25026385100 EMER-INSTALL 4' OF 4\"PM | [5 empty] | 10552 | 14597 | -4045 | 2025-01-01 | 2025-12-31 | 2025-06-30 | 2025-06-30
ANC32.0000.00311 | Replace Coalton Rectifier - 25026408100 | [5 empty] | 1714.45 | 5858.32 | -4143.87 | 2025-01-01 | 2025-12-31 | 2025-07-24 | 2025-10-24
ANC32.0000.00292 | CNV-24026376700 EMER - INSTALL 3'-2\" PM | [5 empty] | 3142 | 7334 | -4192 | 2025-01-01 | 2025-12-31 | 2025-08-28 | 2025-08-31
ANC32.0000.00151 | CNV-25026406000 EMER - INSTALL 2'-2\" PM | [5 empty] | 4119 | 8338 | -4219 | 2025-01-01 | 2025-12-31 | 2025-04-11 | 2025-04-18
ANC32.0000.00096 | CNV-25026398400 EMER - INSTALL FITTINGS. | [5 empty] | 6860 | 11221 | -4361 | 2025-01-01 | 2025-12-31 | 2025-11-25 | 2025-11-30
ANC32.0000.00083 | CNV-24026364700 INSTALL 518'-4\" PMIP | [5 empty] | 30580.52 | 35276.7 | -4696.18 | 2025-01-01 | 2025-12-31 | 2025-07-30 | 2025-08-08
ANC32.0000.00076 | CNV-24026353200 EMER - INSTALL 3'-4\" PM | [5 empty] | 3110 | 7994 | -4884 | 2025-01-01 | 2025-12-31 | 2025-03-25 | 2025-03-31
ANC32.0000.00149 | CNV-25026403300 INSTALL MONITOR REGULATO | [5 empty] | 1694.06 | 7028 | -5333.94 | 2025-01-01 | 2025-12-31 | 2025-05-29 | 2025-05-30
GRT32.0000.00119 | 275 Heritage Dr MLE Versailles | [5 empty] | 10194.51 | 15748.01 | -5553.5 | 2025-01-01 | 2025-12-31 | 2025-07-30 | 2025-08-14
ANC32.0000.00100 | CNV-25026400900 EMER - INSTALL 2'-4\" PM | [5 empty] | 6330 | 12462 | -6132 | 2025-01-01 | 2025-12-31 | 2025-11-25 | 2025-11-30
ANC32.0000.00098 | CNV-25026399700 EMER - INSTALL 3'-2\" PM | [5 empty] | 250 | 6698 | -6448 | 2025-01-01 | 2025-12-31 | 2025-11-26 | 2025-11-30
ANC32.0000.00121 | CNV-23026276000 REPLACE ODORIZER R-1439 | [5 empty] | 17419 | 24767 | -7348 | 2025-01-01 | 2025-12-31 | 2025-12-23 | 2025-12-31
ANC32.0000.00293 | CNV-25026379000 EMER - INSTALL 9'-2\" PM | [5 empty] | 2522.61 | 11724 | -9201.39 | 2025-01-01 | 2025-12-31 | 2025-01-02 | 2025-01-02
BET32.0000.00026 | CNV-25026400200 INSTALL 550'-2\\\ PMMP. | [5 empty] | 47508 | 57766 | -10258 | 2025-01-01 | 2025-12-31 | 2025-04-28 | 2025-05-01
BET32.0000.00048 | CNV-24026310700 ABANDON ~ 150'- 2\" CSIP | [5 empty] | 21867 | 32187 | -10320 | 2025-01-01 | 2025-12-31 | 2025-12-23 | 2025-12-31
BET32.0000.00044 | CNV-24026349300 INSTALL 4\"POLY VALVE KY | [5 empty] | 22343 | 32959 | -10616 | 2025-01-01 | 2025-12-31 | 2025-05-28 | 2025-06-01
BET32.0000.00060 | Duke Rd. / Cooper Dr. Relocation | [5 empty] | 112.75 | 11380.49 | -11267.74 | 2025-01-01 | 2025-12-31 | 2025-12-05 | 2025-12-19
ANC32.0000.00120 | CNV-22026211900 INSTALL 1\" BYPASS VALVE | [5 empty] | 1683 | 15921 | -14238 | 2025-01-01 | 2025-12-31 | 2025-09-25 | 2025-10-01
PIG32.0000.00056 | Vandalay Dr Frankfort Relo | [5 empty] | 4123.36 | 18975.45 | -14852.09 | 2025-01-01 | 2025-12-31 | 2025-08-01 | 2025-08-15
ANC32.0000.00148 | CNV-25026397000 UPGRADE RECTIFIER W/ RMU | [5 empty] | 276.39 | 16611.6 | -16335.21 | 2025-01-01 | 2025-12-31 | 2025-08-28 | 2025-08-28
ANC32.0000.00006 | ANC-Wisemantown Rd Rectifier-Irvine | [5 empty] | 5618.83 | 22844.78 | -17225.95 | 2025-01-01 | 2025-12-31 | 2025-08-28 | 2025-10-31
GRT32.0000.00139 | GRT - 2029 FERN DR MLE - LOUISA | [5 empty] | 13372.78 | 31131.04 | -17758.26 | 2025-01-01 | 2025-12-31 | 2025-12-01 | 2025-12-10
BET32.0000.00054 | BET-Mitchell Ave-Lexington | [5 empty] | 2214.33 | 20539.08 | -18324.75 | 2025-01-01 | 2025-12-31 | 2025-11-18 | 2025-12-05
PIG32.0000.00051 | 2629 - 325 SANDE RIDGE LN - MT. STERLING | [5 empty] | 28187.08 | 46559 | -18371.92 | 2025-01-01 | 2025-12-31 | 2025-08-19 | 2025-11-30
GRT32.0000.00106 | CNV-24026366400 INSTALL ~390'-2\" PMIP | [5 empty] | 44902 | 64433 | -19531 | 2025-01-01 | 2025-12-31 | 2025-02-06 | 2025-02-14
PIG32.0000.00014 | CNV-24026370600 INSTALL 32'-6\" PMLP | [5 empty] | 8318 | 29726 | -21408 | 2025-01-01 | 2025-12-31 | 2025-05-23 | 2025-05-30
ANC32.0000.00170 | ANC-SMRP Burns Ave | [5 empty] | 1585256.47 | 1607553 | -22296.53 | 2025-01-01 | 2025-12-31 | 2025-05-05 | 2025-12-31
ANC32.0000.00052 | CNV-24026313000 INSTALL 1570'-2\\\ PMM. | [5 empty] | 502658 | 526295 | -23637 | 2025-01-01 | 2025-12-31 | 2025-08-19 | 2025-09-30
GRT32.0000.00044 | CNV-23026283101 INSTALL 780'-2\" PMMP | [5 empty] | 71782 | 96019 | -24237 | 2025-01-01 | 2025-12-31 | 2025-05-21 | 2025-05-30
GRT32.0000.00074 | CNV-25026404300 INSTALL 80' OF 2\" PMMP | [5 empty] | 6906.46 | 33570.17 | -26663.71 | 2025-01-01 | 2025-12-31 | 2025-08-12 | 2025-08-31
ANC32.0000.00143 | ANC-Wilson Ln Abandonment-Winchester | [5 empty] | 1973.6 | 30868.63 | -28895.03 | 2025-01-01 | 2025-12-31 | 2025-12-30 | 2025-12-31
PIG32.0000.00024 | CNV-25026409400 INSTALL ANODE BED. | [5 empty] | 21291 | 52966 | -31675 | 2025-01-01 | 2025-12-31 | 2025-12-23 | 2025-12-23
PIG32.0000.00055 | 2629-S Highland Relocation-Winchester | [5 empty] | 0 | 34563.32 | -34563.32 | 2025-01-01 | 2025-12-31 | 2025-08-06 | 2025-09-13
PIG32.0000.00001 | CNV-24026345800 INSTALL 1400'-2\\\ PMI. | [5 empty] | 263557 | 300749 | -37192 | 2025-01-01 | 2025-12-31 | 2025-03-26 | 2025-04-15
GRT32.0000.00130 | 2621-Quintana Estates MLE-Lexington WMS. | [5 empty] | 119825.18 | 163229.55 | -43404.37 | 2025-01-01 | 2025-12-31 | 2025-09-17 | 2025-11-14
ANC32.0000.00257 | WOLF RUN 2025 SMRP CNV-24026322000 | [5 empty] | 681714.43 | 730195.39 | -48480.96 | 2025-01-01 | 2025-12-31 | 2025-07-31 | 2025-12-31
ANC32.0000.00140 | ANC-Caney Circle- Pippa Passes | [5 empty] | 6712.5 | 60386.93 | -53674.43 | 2025-01-01 | 2025-12-31 | 2025-07-02 | 2025-12-31
GRT32.0000.00022 | CNV-25026393800 INSTALL 2,100'-2\\\ PM. | [5 empty] | 110997 | 177755 | -66758 | 2025-01-01 | 2025-12-31 | 2025-05-13 | 2025-05-30
GRT32.0000.00133 | Ball Homes South Crossing P3 Georgetown | [5 empty] | 281612.34 | 367711.37 | -86099.03 | 2025-01-01 | 2025-12-31 | 2025-09-02 | 2025-11-01
GRT32.0000.00125 | UK DORM WOODLAND | [5 empty] | 35464.16 | 127511.86 | -92047.7 | 2025-01-01 | 2025-12-31 | 2025-08-06 | 2025-08-30
ANC32.0000.00144 | CNV-24026367900 INSTALL 1060' OF 2\"PMMP | [5 empty] | 3411.34 | 101110.57 | -97699.23 | 2025-01-01 | 2025-12-31 | 2025-08-06 | 2025-08-08
PIG32.0000.00049 | CNV-24026367500 INSTALL 1600'-2\" PMMP | [5 empty] | 408326 | 509357 | -101031 | 2025-01-01 | 2025-12-31 | 2025-05-13 | 2025-07-01
PIG32.0000.00039 | CNV-24026358801 INSTALL 4200' OF 2\\\"/. | [5 empty] | 782268 | 884926 | -102658 | 2025-01-01 | 2025-12-31 | 2024-09-19 | 2025-06-01
GRT32.0000.00131 | GRT - CARRIAGE LN MLE - LEXINGTON | [5 empty] | 357427.11 | 495629.82 | -138202.71 | 2025-01-01 | 2025-12-31 | 2025-10-01 | 2025-12-31
PIG32.0000.00013 | CNV-24026363100 INSTALL 481'-8\" CSHP | [5 empty] | 47018.3 | 195428.52 | -148410.22 | 2025-01-01 | 2025-12-31 | 2025-07-15 | 2025-07-30
BET32.0000.00049 | EMER - E Broadway St Crossbore FRANKFORT | [5 empty] | 2978.58 | 157244.84 | -154266.26 | 2025-01-01 | 2025-12-31 | 2025-08-06 | 2025-08-29
BET32.0000.00003 | CNV-21026135500 INSTALL 75'-4/6/12\" CSH | [5 empty] | 28372.72 | 183004.72 | -154632 | 2025-01-01 | 2025-12-31 | 2025-07-25 | 2025-07-31
ANC32.0000.00256 | ANC - SMRP FLOYD STREET - ASHLAND | [5 empty] | 3291186.21 | 3500000 | -208813.79 | 2025-01-01 | 2025-12-31 | 2025-07-17 | 2025-12-31
ANC32.0000.00199 | SMRP-Castlewood Dr-Lexington | [5 empty] | 159842.86 | 497868.19 | -338025.33 | 2025-01-01 | 2025-12-31 | 2025-08-18 | 2025-12-31
ANC32.0000.00005 | ANC-SMRP Camelot Dr - Winchester | [5 empty] | 667229.79 | 2008502.28 | -1341272.49 | 2025-01-01 | 2025-12-31 | 2025-07-21 | 2025-12-31
Formulas:
Date Actual End = VLOOKUP([Project No.],'WMS JO Data'!$D20:BD27974,25,FALSE)

## Variance Data RAW (hidden)
Capital Job Order Variance
cognos.nisource.net:// NGD>>Reports>>Capital Performance | [8 empty] | Report Run: 05-21-2024 06:27:12 PM CDT
Job Status Codes: CO, EX | [8 empty] | **Nisource Confidential - For Internal Use Only
Dates: | Jan 1, 2019 through Dec 31, 2023 | [7 empty] | For questions, contact Business Intelligence at birepreq@nisource.com
Variance: | Only Level 1 - 15% Variance and 30K, Only Level 2 - 25% Variance and 50K, All Other Variances
State: | KY
State | Ops Center | TCC | Project Engineer Id | Engineer Name | Leader Name | Manager Name | Job Order | Job Type | Job Status | Job Summary | In Out Service Date | Address | Install Cd | Estimated Total Cost | Actual Total Cost | Cost Variance | Percent Variance | Estimated Footage | Actual Footage | Actual Cost Per Foot | Execution Comments
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 14026531302 | 561 | EX | INSTALL 20'-6" CSHP | 2020-02-17 | 600 CHESTNUT OAK ST | B | 40462.1821 | 74916.27 | 34454.0879 | 85% | 20 | 80 | 936.4534 | PROJECT OVERRUN OF $34,000 DUE TO SEVERAL MOVEIN/MOVE-OUTS AND REVISIONS TO THE PROJECT. PROJECT WAS PAID HOURLY AND HOURLY CONTRACT UNITS WERE UNDER ESTIMATED BY $23,000, LABOR WAS UNDERESTIMATED BY 100 HOURS WHICH INCREASED COST BY $5,000. THERE WAS ALSO INCREASE IN SEGA AND OVERHEADS OF $4,000. D.LEMONS 6/30/2020
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 14026531402 | 562 | EX | RETIRE 20'-6" CSHP | 2020-02-17 | 600 CHESTNUT OAK ST | B | 82.6789 | 461.39 | 378.7111 | 458% |  |  | 0
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 15026561600 | 2000 | EX | NEW CIRCLE RD PHASE II | 2019-11-22 | NEW CIRCLE RD |  | 10186 | 0 | -10186 | 100% |  |  | 0 | 11/22/19: KDOT AND HDR ENGINEERS AGREED TO REVISE DESIGN NEAR N-S RAILROAD AND POINTS EAST TO ALLEVIATE CONFLICT WITH CKY'S EXISTIGN 12' CSHP: BKSLONE
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 15026601101 | 561 | EX | INSTALL 3854'- 12 & 4" CSHP | 2019-02-13 | W NEW CIRCLE RD | B | 2142667.2506 | 2139888.06 | -2779.1906 | 0% | 3850 | 3633 | 589.0141
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 15026601201 | 562 | EX | RETIRE 3535'-12" & 4" CS/BSHP | 2019-02-16 | W NEW CIRCLE RD | B | 7584.9756 | 32537.12 | 24952.1444 | 329% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 15026619300 | 587 | EX | INSTALL NEW 2" BYPASS REGS | 2019-09-17 | 1900 RICHMOND RD | F | 1699.7526 | 642.3 | -1057.4526 | -62% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 15026619400 | 588 | EX | ABANDON BYPASS REGULATOR | 2019-09-17 | 1900 RICHMOND RD | F | 57.9825 | 0 | -57.9825 | 100% |  |  | 0
KY | KY - WEST | 2621 | U129042 |  |  |  | 15026622100 | 2000 | EX | STAKING/SURVEYING | 2019-10-01 | MT TABOR RD | B | 8100 | 0 | -8100 | 100% |  |  | 0 | CITY PROJECT WAS PLACED ON HOLD FOR A SIGNIFICANT AMOUNT OF TIME. FUNDING BECAME AVAILIBLE IN 2020 FISCAL YEAR FOR CONSTRUCTION. PLANS WERE ORIGINALL Y SENT OUT IN 2015. D.LEMONS 10/1/19
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 16026652700 | 2000 | EX | INVESTIGATE FOR SERVICE | 2021-11-18 | 961 NANDINO BV |  | 3820.3494 | 0 | -3820.3494 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 16026652800 | 2000 | EX | INVESTIGATE FOR SERVICE | 2021-11-18 | 1545 ALEXANDRIA DR |  | 3820.3494 | 0 | -3820.3494 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 16026664700 | 2000 | EX | INVESTIGATE NON-STANDARD S/L | 2021-11-18 | 1708 JENNIFER RD 1B | B | 5000 | 0 | -5000 | 100% |  |  | 0 | TWALKER/KY 11-18-21: LAND SERVICE COULD NOT OBTAIN EASEMENT(S) FROM PROPERTY OWNER. PROJECT CANCELLED.
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 16026676800 | 561 | EX | INSTALL 350'-4" PMMP | 2020-01-22 | 404 OLD FRANKFORT PK | A | 21485.8363 | 9902.28 | -11583.5563 | -54% | 350 | 271 | 36.5398 | INSTALLED 271' OF 4" PL-PRESS TEST 90LBS 1HR TEST OK-SOAP TEST FINAL TIE IN @OP TEST OK-50PSI VERIFIED-PERFORMED SQUEEZEING&GAUGEING&PURGING TO GAS STA NDARDS SOAP TESTED 4 TEE CAPS AND DE CAPS @ OP TEST OK-ANICHOLS 1-22-20
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 16026676900 | 562 | EX | RETIRE 350'-4" PMMP | 2020-01-22 | 404 OLD FRANKFORT PK | A | 75.6667 | 3951.76 | 3876.0933 | 5,123% |  |  | 0 | ABANDONED 301' OF 4" PLASTIC MP MAIN PURGED ALL GAS OUT TILL ZERO READINGS SEALED ENDS OF OLD MAIN-ANICHOLS 1-22-2020
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 16026683601 | 555 | EX | INSTALL 800' OF 2"/4"PMMP MAIN | 2019-02-14 | 1255 PROVIDENCE PLACE PY LOT 3 | B | 46066.6033 | 65648.19 | 19581.5867 | 43% | 800 | 967 | 67.8885
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 17026689601 | 557 | EX | INSTALL 4100' OF 2"/4"PMMP | 2020-10-02 | BENNETT AV | B | 1070240.1923 | 1043901.59 | -26338.6023 | -2% | 4100 | 4095 | 254.921
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 17026689700 | 558 | EX | RETIRE 4850' OF BS/CS/P LPMAIN | 2020-11-04 | BENNETT AV | B | 310.9221 | 62.11 | -248.8121 | -80% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 17026702600 | 584 | EX | RETIRE GUAGE | 2019-01-01 | 101 W LOUDON AV | F | 70.5104 | 0 | -70.5104 | 100% |  |  | 0 | GAUGE RETIRED - NEW GAUGE NOT REQUIRED PER CFARIS
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 17026704500 | 2000 | EX | SURVEY AN MAP FACILITIES | 2020-04-02 | AVE OF CHAMPIONS |  | 22786.8461 | 0 | -22786.8461 | 100% |  |  | 0 | PROJECT BROKE INTO 3 PHASES. PHASE 1 & 2 ARE READY, PHASE 3 STILL REQUIRES WORK AND EASEMENTS.
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 17026704800 | 2000 | EX | INVESTIGATE PROPERTY | 2021-11-18 | 803 CHILES AV |  | 5682.1692 | 0 | -5682.1692 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 17026705600 | 559 | EX | INSTALL 2"GV-10' 2"CSHP MAIN | 2019-04-29 | BEREA RD | B | 47831.1411 | 56876.12 | 9044.9789 | 19% | 10 | 19 | 2993.48
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 17026705700 | 560 | EX | ABANDON 2"GV C4-73 | 2019-04-29 | BEREA RD | B | 66.1634 | 362.38 | 296.2166 | 448% |  |  | 0
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 17026714600 | 2000 | EX | INVESTIGATE PIPLNE CONFLCTS | 2021-11-18 | LEESTOWN RD | B | 8227 | 0 | -8227 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 17026714900 | 557 | EX | INSTALL 4225' OF 2"PMMP MAIN | 2019-04-12 | MADISON PL | B | 813635.1267 | 923117.22 | 109482.0933 | 13% | 4225 | 4235 | 217.9734
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 17026715000 | 558 | EX | RETIRE 4000' OF 4"BS/CILP MAIN | 2019-05-29 | MADISON PL | B | 304.4407 | 0 | -304.4407 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 17026724300 | 2000 | EX | MAP SITE & FACILITIES | 2020-01-16 | 2350 FORTUNE DR |  | 4953.9871 | 0 | -4953.9871 | 100% |  |  | 0 | PS&I CHARGED TO 19026916300(575) TO ACQUIRE LAND FOR PROJECT. D.LEMONS 1/16 /20
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 17026725301 | 555 | EX | INSTALL 3300' OF 4"PMMP MAIN | 2019-02-04 | 5751 BRIAR HILL RD LT112 | B | 202202.0123 | 213118.5 | 10916.4877 | 5% | 3300 | 3583 | 59.4805
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 17026732801 | 561 | EX | INSTALL 6450' OF 4"/6"/8" PMLP | 2019-10-18 | CLAYS MILL RD | B | 1270165.8463 | 1682192.58 | 412026.7337 | 32% | 6450 | 6064 | 277.4064 | THE HOURLY ON INVOICE # 122237 WAS FOR TIE IN'S ON CLAYS MILL WORKED RELIGHTS FROM OUTAGE ON STRATFORD DR. PER GHATTON. 10/29/19 ZMARTIN LEVEL 2 EXPLANATION IN DOCS.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 17026732900 | 562 | EX | RETIRE 6400'OF CS/BSLP MAINS | 2019-11-15 | CLAYS MILL RD | B | 67.8275 | 430.7 | 362.8725 | 535% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 17026733101 | 561 | EX | INSTALL 6075' OF 2"/4"PMMP | 2019-10-03 | CLAYS MILL RD | B | 394597.4169 | 364568.47 | -30028.9469 | -8% | 5875 | 6443 | 56.5837
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 17026733200 | 562 | EX | RETIRE 3240'- 2"/4" PMP MAIN | 2019-11-15 | CLAYS MILL RD | B | 67.8275 | 217.84 | 150.0125 | 221% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 17026736101 | 557 | EX | INSTALL 12500' OF 2"PMMP MAIN | 2019-08-05 | 201 TAHOMA | B | 934081.8376 | 1131820.72 | 197738.8824 | 21% | 12500 | 11960 | 94.6338 | TWALKER/KY 12-23-19: JOB VARIANCE DUE TO ADDITIONAL STREET/ROAD REPAIRS REQUIRED BY LFUCG AT THE END OF PROJECT - ADDED OVER $100,000 IN PAVING CONTRACT COST.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 17026736200 | 558 | EX | ABANDON 13200'-2"/3"/4"BSLP | 2019-11-25 | 201 TAHOMA | B | 541.8773 | 5466.71 | 4924.8327 | 909% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 17026742600 | 2000 | EX | RESEARCH AND INVESTIGATE | 2019-04-15 | SOUTHLAND DR | B | 12230 | 0 | -12230 | 100% |  |  | 0 | LAND SERVICES COMPLETED INVESTIGATION AND PROPOSED ALLIGNMENT. D.LEMONS
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 17026742700 | 561 | EX | INSTALL 14'-8"CS&PMLP | 2019-07-10 | SOUTHLAND DR | B | 43711.5377 | 49872.05 | 6160.5123 | 14% | 14 | 11 | 4533.8227
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 17026742800 | 562 | EX | RETIRE 8'-8"BSLP | 2019-07-10 | SOUTHLAND DR | B | 77.825 | 0 | -77.825 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026744800 | 561 | EX | INSTALL 35'-6" CSHP | 2020-01-23 | 535 NEWTOWN PK | B | 61047.2348 | 149186.46 | 88139.2252 | 144% | 35 | 62 | 2406.2332 | LEVEL 2 VARIANCE EXPLANATION FILLED OUT AND SENT FOR APPROVAL. D.LEMONS 6/1 6/2020
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026744900 | 562 | EX | RETIRE 30'-6" CSHP | 2020-01-23 | 535 NEWTOWN PK | B | 82.7013 | 168.72 | 86.0187 | 104% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026745800 | 584 | EX | ABANDON REG STATION #1018 | 2019-05-29 | 420 PINE ST | F | 2856.7628 | 1548.46 | -1308.3028 | -46% |  |  | 0 | JOB WAS ON HOLD
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026746400 | 561 | EX | INSTALL 115'-6" PHHP/CSHP | 2019-02-05 | 763 W NEW CIRCLE RD | B | 29746.8817 | 34226.61 | 4479.7283 | 15% | 115 | 131 | 261.2718
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026746500 | 562 | EX | RETIRE 610'-4" CSHP | 2019-02-14 | 763 W NEW CIRCLE RD | B | 76.2873 | 0 | -76.2873 | 100% |  |  | 0
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026746700 | 562 | EX | RETIRE 927'-2" CS & PMMP | 2019-02-19 | W NEW CIRCLE RD | B | 1702.2179 | 0 | -1702.2179 | 100% |  |  | 0
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026746801 | 562 | EX | RETIRE 362'-2" CSHP + 2" GV | 2020-03-13 | COLESBURY CR | B | 36975.1316 | 53921.61 | 16946.4784 | 46% |  |  | 0
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026746900 | 561 | EX | INSTALL 1700' 12" CSHP | 2019-03-15 | W NEW CIRCLE RD | B | 1088739.318 | 969011.19 | -119728.128 | -11% | 1880 | 1744 | 555.6257
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026747000 | 562 | EX | RETIRE 1669'-12" BS/CSHP | 2019-03-15 | W NEW CIRCLE RD | B | 71.8476 | 132.2 | 60.3524 | 84% |  |  | 0
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026747100 | 561 | EX | INSTALL 753'-4" CSHP | 2020-04-13 | 250 LIMA DR | B | 160773.9961 | 186509.1 | 25735.1039 | 16% | 753 | 727 | 256.5462
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026747200 | 561 | EX | INSTALL 216-8" CSHP | 2020-04-13 | 250 LIMA DR | B | 83038.4197 | 78657.87 | -4380.5497 | -5% | 216 | 204 | 385.5778
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026747300 | 561 | EX | INSTALL 33' - 4" CSHP | 2019-11-22 | GEORGETOWN RD | B | 35486.9695 | 26193.3 | -9293.6695 | -26% | 33 | 28 | 935.475
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026747401 | 562 | EX | RETIRE 505'- 6"/4" BS/CSHP | 2019-12-02 | GEORGETOWN RD | B | 31756.1637 | 31608.64 | -147.5237 | 0% |  |  | 0
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026747501 | 561 | EX | INSTALL 1140'-4" PMLP | 2019-12-06 | GEORGETOWN RD | B | 212341.9469 | 192579.3 | -19762.6469 | -9% | 1141 | 1130 | 170.4242
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026747600 | 562 | EX | RETIRE 350'-4" BSLP | 2019-12-06 | GEORGETOWN RD | B | 74.8323 | 0 | -74.8323 | 100% |  |  | 0
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026749200 | 561 | EX | INSTALL 1170'-4"/2" PMMP | 2019-10-10 | FRONTAGE RD | B | 206432.4814 | 185275.59 | -21156.8914 | -10% | 1172 | 1140 | 162.5224
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026749300 | 562 | EX | RETIRE 1120'-2" CS/PMP | 2019-10-10 | FRONTAGE RD | B | 1264.2652 | 0 | -1264.2652 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026754500 | 561 | EX | INSTALL 1260'-4"&6" PMLP | 2019-07-31 | SOUTHLAND DR | B | 300465.316 | 210289.46 | -90175.856 | -30% | 1268 | 1144 | 183.8195 | UNDERRUN EXPLANATION: THE COMPANY DECIDED TO BORE MOST OF THE PROJECT INSTE AD OF OPEN CUT AND THOUGH THE BORE COST WAS MORE AVOIDE A SIGNIFICANT AMOUN T OF EXPENSIVE HARD SURFACE REPAIRS. . A LEVEL 2 VARIANCE EXPLANATION IS NOT REQUIRED FOR AN UNDERRUN.
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026754600 | 562 | EX | RETIRE 138'-6&8"LP | 2019-07-31 | SOUTHLAND DR | B | 79.9756 | 0 | -79.9756 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026754700 | 561 | EX | INSTALL 640'-4"PMLP | 2019-08-20 | SOUTHLAND DR | B | 64602.7097 | 34674.16 | -29928.5497 | -46% | 640 | 589 | 58.8695 | UNDERRUN EXPLANATION: THE UNDERRUN WAS CAUSED BY NOT HAVING TO PAY AS MUCH PAVING AS WAS ESTIMATED.
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026755802 | 557 | EX | INSTALL 70'-6" PMLP | 2019-03-20 | 1204 N BROADWAY ST APT | B | 147474.234 | 150272.74 | 2798.506 | 2% | 95 | 109 | 1378.649
KY | KY - WEST | 2621 | U131369 |  |  |  | 18026755900 | 558 | EX | RETIRE 90'-8" CSLP | 2019-03-20 | 1204 N BROADWAY ST APT | B | 80.4051 | 881.16 | 800.7549 | 996% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026756300 | 555 | EX | INSTALL 550' OF 2"PMMP MAIN | 2019-02-22 | 909 CROCUS CT | B | 23888.4008 | 22117.37 | -1771.0308 | -7% | 550 | 568 | 38.939
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026757700 | 909 | EX | INSTALL MI WIRELESS EFC | 2022-11-07 | BRIAR HILL RD | F | 13926.0597 | 14191.42 | 265.3603 | 2% |  |  | 0 | INSTALLED HONEYWELL ERX SUPER SOLAR KIT J MULLINS 11-7-22
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026757800 | 584 | EX | RETIRE RECORDING GAUGE | 2022-11-07 | BRIAR HILL RD | F | 73.0037 | 0 | -73.0037 | 100% |  |  | 0 | RETIRED CHART INSTALLED HONEYWELL ERX JMULLINS 11-7-22
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026763000 | 557 | EX | INSTALL 1600' OF 8"CSHP MAIN | 2019-12-23 | 469 PARKWAY DR | B | 605139.9338 | 693909.46 | 88769.5262 | 15% | 1800 | 1588 | 436.9707 | IN SERVICE ON 12/23/2019 BUT ABANDONMENT TOO PLACE ON 01/06/2020. FLL'S AND ENGINEERING ADVISED
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026763100 | 558 | EX | ABANDON 1750' OF 6 5/8"BSHP | 2020-01-06 | 469 PARKWAY DR | B | 257.241 | 285.4 | 28.159 | 11% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026767601 | 561 | EX | INSTALL 420'-4"&6" PMMP | 2019-03-04 | WILSON DOWNING RD | B | 103809.9847 | 139472.01 | 35662.0253 | 34% | 434 | 499 | 279.503 | OVERRUN EXPLANATION: THE JOB TOOK 39% MORE LABOR THAT ESTIMATED RESULTING I N $4500 OVER IN LABOR AND TRUCK EXPENSE. ADDITIONALLY, WE OVERRAN APROXIMAT ELY $12K IN PAVING.
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026767700 | 562 | EX | RETIRE 420'-4"&6" CSMP | 2019-03-25 | WILSON DOWNING RD | B | 76.2873 | 138.16 | 61.8727 | 81% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026772800 | 555 | EX | INSTALL 250' OF 2"PMMP | 2019-04-15 | 3525 CAVE HILL PL LT1 | B | 17789.2058 | 15452.23 | -2336.9758 | -13% | 250 | 245 | 63.0703
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026772900 | 555 | EX | INSTALL 575' OF 2"PMMP MAIN | 2019-05-23 | 507 ROGERS RD | B | 27269.8864 | 23438.09 | -3831.7964 | -14% | 575 | 604 | 38.8048
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026773000 | 2000 | EX | CONFLICT AND RELOCATION | 2019-10-18 |  |  | 14634 | 0 | -14634 | 100% |  |  | 0 | NO MORE INVESTIGATIONS NEEDED. D.LEMONS 10/18/19
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 18026773101 | 559 | EX | INSTALL 175' - 12" CSHP | 2019-06-21 | WINCHESTER RD | B | 599149.5397 | 626707.93 | 27558.3903 | 5% |  | 174 | 3601.7697
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 18026773200 | 560 | EX | RETIRE 100' 12" WTHP | 2019-06-21 | WINCHESTER RD | B | 55.8275 | 28884.59 | 28828.7625 | 51,639% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026773600 | 2000 | EX | INVESTIGATE RIGHTS - NEW FENCE | 2021-09-22 | BRIAR HILL RD | B | 7724 | 0 | -7724 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026774600 | 561 | EX | INSTALL 900' OF 8"CSHP | 2020-04-16 | 3801 HARRODSBURG RD | B | 362869.5724 | 409037.76 | 46168.1876 | 13% |  | 941 | 434.6841 | TWALKER/KY 07-02-2020: PROCESSED THIS PAID RELOCATION FOR FINAL BILLING AND ADDITIONAL AMOUT DUE BY CUSTOMER
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026774700 | 562 | EX | RETIRE 850' OF 8"CSHMP | 2020-04-16 | 3801 HARRODSBURG RD | B | 67.7459 | 806.24 | 738.4941 | 1,090% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026777600 | 2000 | EX | INVESTIGATE R/W AND CLEARING | 2019-03-13 | 3090 HARRODSBURG RD |  | 6664.1606 | 0 | -6664.1606 | 100% |  |  | 0
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026779000 | 583 | EX | R-1133 INSTALL NEW REG SETTING | 2019-02-14 | 763 W NEW CIRCLE RD | F | 90267.2523 | 65530.53 | -24736.7223 | -27% |  |  | 0 | JOB WAS ON HOLD - WAITING ON STATE HIGHWAY DEPARTMENT
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026779100 | 584 | EX | R-1133 RETIRE EXIST REG STA | 2019-02-14 | 763 W NEW CIRCLE RD | F | 154.0949 | 124.84 | -29.2549 | -19% |  |  | 0 | JOB WAS ON HOLD WAITING ON STATE TRANSPORTATION DEPARTMENT
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026779200 | 585 | EX | R-1133 INSTALL NEW 19X24 FENCE | 2019-09-23 | 763 W NEW CIRCLE RD | F | 16030.7484 | 9592.7 | -6438.0484 | -40% |  |  | 0 | FENCE INSTALLED BY INTERSTATE FENCE COMPANY
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026779600 | 573 | EX | R-1221 INSTALL NEW REG SETTING | 2020-05-15 | 250 LIMA DR | F | 85333.0009 | 51837.32 | -33495.6809 | -39% | 200 |  | 0 | DELAY IN PROJECT WITH STATE HIGHWAY DEPARTMENT AND ALSO WITH ACQUIRING LAND FOR THE STATION . 22SEP20 UNDERRUN EXPLANATION: ACTUAL UNDERRUN WAS ONLY $13240 (15.5%) AND WAS DUE MOSTLY TO FISHEL CONTRACT LABOR $5000 LESS THAN ESTIMATED AND THE ESTIMATED MISC DOLLARS AND CONTINGENCY AMOUNTING TO $8500 THAT NOT NEEDED MAKING UP THE AMOUNT OF UNDERRUN (BKSLONE).
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026779700 | 584 | EX | R-1071 RETIRE EXISTING REG STA | 2019-12-03 | 996 NEW CIRCLE RD NW | F | 883.5772 | 1141.93 | 258.3528 | 29% |  |  | 0
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026779800 | 577 | EX | R-1221 INSTALL NEW REG BLDG | 2020-06-18 | 250 LIMA DR | F | 89078.2364 | 96473.83 | 7395.5936 | 8% |  |  | 0 | ESPARKS 06-18-20
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026780001 | 575 | EX | R-1221 ACQUIRE NEW REG SITE | 2020-02-24 | 250 LIMA DR | F | 50787 | 64226.88 | 13439.88 | 26% |  |  | 0 | 24FEB20: COMPLETED BY AUTUMN DMYTREWYCZ OF TEMA FISHEL (BKSLONE)
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026780700 | 573 | EX | INSTALL NEW REG STA R-1222 | 2019-10-18 | 968 NANDINO BV | F | 56249.1748 | 33940.47 | -22308.7048 | -40% |  |  | 0
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026780800 | 584 | EX | R-1199 RETIRE EXIST REG STA | 2019-10-18 | 1008 NEW CIRCLE RD NW | F | 145.1528 | 471.12 | 325.9672 | 225% |  |  | 0
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026780900 | 577 | EX | R-1222 INSTALL NEW 20X20 FENCE | 2019-12-23 | 968 NANDINO BV | F | 16537.9613 | 18519.29 | 1981.3287 | 12% |  |  | 0 | SIGNS UP REG STATION LOCKED AND SECURED APARKS 12-20-19
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026781000 | 575 | EX | R-1222 ACQUIRE 25X25 REG SITE | 2019-05-31 | 968 NANDINO BV | F | 28537 | 18817.11 | -9719.89 | -34% |  |  | 0 | REG SITE & EASEMENT ACQUIRED BY AUTUMN DMYTREWYCZ MAY, 2019 (BKSLONE)
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026781100 | 584 | EX | R-1183 RETIRE EXIST REG STA | 2019-02-19 | 1512 COLESBURY CR | F | 341.6453 | 5015.16 | 4673.5147 | 1,368% |  |  | 0 | JOB WAS ON HOLD WAITING ON KY TRANSPORTATION CABINET OUTLET SYSTEM NUMBER RETIRED PRIOR PAPERWORK BEING COMPLETED HAD TO CHANGE SYSTEM NUMBER ON JOB ORDER IN ORDER TO COMPLETE
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026783800 | 561 | EX | INSTALL 320'-8" PMLP | 2019-04-11 | JEFFERSON ST | B | 186541.4534 | 231561.52 | 45020.0666 | 24% | 310 | 320 | 723.6297 | OVERRUN EXPLANATION: THIS PROJECT HAD TO BE WORKED AT NIGHT AND THE HOURLY CREW RATES TOOK EFFECT AND LED TO SUBSTANTUALLY MORE CONTRACT LABOR THAN ES TIMATED. ADDITIONALLY, THE CITY REQUIRED THAT WE USE THEIR SPECIFIED PAVER DUE TO THEIR INCREASED CAPABILITIES WHICH LED TO INCREASED COSTS AS WELL.
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026783900 | 562 | EX | RETIRE 525'-8" CSLP | 2019-04-11 | JEFFERSON ST | B | 75.0885 | 132.2 | 57.1115 | 76% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026784001 | 561 | EX | INSTALL 1385'-6" PMMP | 2019-04-10 | JEFFERSON ST | B | 471729.6551 | 427330.33 | -44399.3251 | -9% | 1508 | 1644 | 259.9333 | UNDERRUN EXPLANATION: IT APPEARS THAT SOME OF THE HARD SURFACE RESTORATION WAS CHARGED TO THE ASSOCIATED LP PROJECT THAT WAS WORKED SIMULTANEOUSLY WIT H THIS ONE.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026789202 | 555 | EX | INSTALL 350' OF 2"PMMP MAIN | 2019-11-11 | 405 LAREDO CT D | B | 22611.6744 | 24248.55 | 1636.8756 | 7% | 350 | 360 | 67.3571
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026790300 | 555 | EX | INSTALL 350' OF 2"PMMP MAIN | 2019-07-02 | MILL RIDGE RD LT1C | B | 14329.8594 | 18094.74 | 3764.8806 | 26% | 350 | 405 | 44.6784
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026790901 | 555 | EX | INSTALL 800' OF 4"PMMP MAIN | 2020-03-26 | 450 PARK PL LT 3 | B | 130601.3453 | 127535.23 | -3066.1153 | -2% | 800 | 806 | 158.2323
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026792402 | 557 | EX | INSTALL 19,575' OF 2"/4" PMMP | 2019-06-21 | LARCH LN | B | 993828.312 | 1094564.81 | 100736.498 | 10% | 19575 | 19541 | 56.0138
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026792500 | 558 | EX | RETIRE 15,000' OF 3"-6"BSLP | 2019-12-05 | LARCH LN | B | 276.6512 | 585.94 | 309.2888 | 112% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026793101 | 557 | EX | INSTALL 2990' OF 2"/4" PMMP | 2019-10-24 | 600 CENTRAL AV | B | 1176455.3136 | 1067558.09 | -108897.2236 | -9% | 2990 | 3012 | 354.435 | 3-12-20 98-140 (16) CUT WINDOWS FOR SL'S TO 286/256 CLAY AV 3-13-20 98-140 (12) 98-300 (5.5) FINISH CUTTING WINDOWS ON CLAY AV JOB COMPLETE. TWALKER/KY 06-30-20: JOB CURRENTLY UNDER RUN DUE TO PAVING COST HAVE NOT BEEN APPLIED TO 557 JOB#
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026793200 | 558 | EX | ABANDON 1525' OF 3"/6" BSMP | 2019-10-24 | 600 CENTRAL AV | B | 53.9767 | 1301.98 | 1248.0033 | 2,312% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026793300 | 2000 | EX | INVESTIGATE EASEMENT/RIGHTS | 2019-07-12 | 220 CLAY AV | B | 15377 | 0 | -15377 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026795700 | 561 | EX | INSTALL 1720'-2"&4" PMMP | 2019-08-08 | EDGELAWN AV | B | 134950.54 | 102973.29 | -31977.25 | -24% | 1712 | 1770 | 58.177 | UNDERRUN EXPLANATION: WE CHANGED CONTRACTORS THAT DECREASED COSTS AND WE DI D NOT UTILIZE MANY OF THE PAVING ITEMS BECAUSE THIS WAS A RELOCATION.
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026795800 | 562 | EX | RETIRE 845'-3" BS & P LP | 2019-09-13 | EDGELAWN AV | B | 74.1611 | 990.87 | 916.7089 | 1,236% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026796000 | 557 | EX | INSTALL 2450' OF 4"PMLP MAIN | 2019-11-12 | 200 W 2ND | B | 651866.7814 | 779231.58 | 127364.7986 | 20% | 2450 | 2450 | 318.0537 | TWALKER/KY 06-30-2020: JOB OVER RUN DUE TO CITY OF LEXINGTON REQUIRED ADDIT IONAL MILL/PAVE FOR STREET CUTS WHICH INCREASED COST BY $100,000 AND SEGA INCREASED BY $19,000 VS ESTIMATED.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026796100 | 558 | EX | ABANDON 2300' OF 4" CI/BSLP MN | 2019-11-22 | 200 W 2ND | B | 69.9718 | 183.11 | 113.1382 | 162% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026796401 | 557 | EX | INSTALL 11,750' OF 2"/4"PMMP | 2019-08-20 | FONTAINE RD | B | 814656.4822 | 853373.69 | 38717.2078 | 5% | 11750 | 7472 | 114.2095
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026796500 | 558 | EX | RETIRE 5500' - 6" BSLP MAIN | 2019-12-19 | FONTAINE RD | B | 141.5215 | 60620.98 | 60479.4585 | 42,735% |  |  | 0 | OVERRUN EXPLANATION:THIS WAS A RETIREMENT JOB ORDER AND SHOULD HAVE HAD ONL Y A FEW HOURS OF LABOR CHARGED. MOST OF THIS WORK SHOULD HAVE BEEN CHARGED TO THE INSTALL. I WILL CHECK WITH ACCOUNTING TO DETERMINE IF THEY WANT TO M OVE THE CHARGES TO THE 18-0267964-01.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026796600 | 2000 | EX | DETERMINE LAND RIGHTS | 2021-02-11 | 4940 ATHENS BOONESBORO RD | A | 8400 | 0 | -8400 | 100% |  |  | 0
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 18026796700 | 557 | EX | INSTALL 2150' - 2" PMMP | 2020-06-24 | MILL ST | B | 526359.4092 | 398583.36 | -127776.0492 | -24% | 2200 | 2079 | 191.7188 | UNDERRUN EXPLANATION: IT DOES NOT APPARE ALL OF THE PAVING HAS HIT YET. REC OMMEND WAITING UNTIL THAT OCCURS AND MAKE ANOTHER ASSESSMENT. 11/24/2020 UPDATE TO UNDERRUN EXPLANATION: SOME OF THE PAVING DID HIT AND P ERHAPS ALL OF IT. POWERPLANT SHOWS THE COSTS DIFFERENTLY THAN WMS. SINCE PO WERPLANT IS THE FINANCIAL SYSTEM OF RECORD, POWER PLANT IS PRESUMED CORRECT . THE COSTS AS OF 11/24/2020 ARE $358620.THE UNDERRUN IS DUE TO PAVING. TH IS WAS WORKED IN CONJUNCTION WITH A MUNICIPAL PROJECT AND PERHAPS THE CITY BILLED US LESS THAN WE ANTICIPATED.
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 18026796800 | 558 | EX | RETIRE 3500' - BS/CILP | 2020-06-24 | MILL ST | B | 359.3348 | 72.66 | -286.6748 | -80% |  |  | 0
KY | KY - WEST | 2621 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 18026797401 | 557 | EX | INSTALL 13225' OF 2"PMMP MAIN | 2019-10-17 | MARCELLUS | B | 1622403.4384 | 1499060.49 | -123342.9484 | -8% | 13251 | 7801 | 192.1626
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026797500 | 558 | EX | RETIRE 6800'-4" BSLP | 2019-12-17 | MARCELLUS | B | 72.7501 | 645.94 | 573.1899 | 788% |  |  | 0
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026798301 | 561 | EX | INSTALL 2500'-12" CSHP | 2020-02-20 | W NEW CIRCLE RD | B | 1166541.2469 | 1126864.76 | -39676.4869 | -3% | 3200 | 2485 | 453.4667
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026798900 | 555 | EX | INSTALL 625' OF 2"PMMP MAIN | 2019-01-18 | 401 UNITED CT LT | B | 24146.8881 | 33732.14 | 9585.2519 | 40% | 625 | 630 | 53.5431
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026800000 | 0001 | EX | DOCUMENT DOWNRATE FM 60# - 35# | 2019-02-20 | COLESBURY CR |  | 0 | 0 | 0 | 0% |  |  | 0 | TWALKER/KY 02-20-19: REG STATION #1183 RETIRED ON 18-0267811-00 AS PART OF THE NEW CIRCLE ROAD RELOCATION PROJECT ID 14-25507, SYSTEM 32010136 WAS DOWNRATED AND COMBINED WITH SYSTEM 32010135.
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026801000 | 584 | EX | RET. FN 49 FOR EXTRA LP OPP | 2020-10-22 | LP STATION INVENTORY AV | F | 53.9767 | 281.17 | 227.1933 | 421% |  |  | 0 | REGULATORS REPLACED BY CHRIS COX ON 10/22/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS 1/29/2021 GCCC TICKET NOT REQUIRED ON 1/29/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026801100 | 583 | EX | INST. FN 49 EXTRA LP OPP | 2020-10-22 | LP STATION INVENTORY AV | F | 41778.1646 | 39390.89 | -2387.2746 | -6% | 55 |  | 0 | REGULATORS AND ER350 INSTALLED BY CHRIS COX ON 10/22/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/29/2020 GCCC TICKET NOT REQUIRED ON 1/29/20 NOT AT STATION OFF SITE COMPETING PAPERWORK
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026801200 | 583 | EX | INST. FN 50 EXTRA LP OPP | 2019-05-06 | 100 VENICE PK | F | 21708.8722 | 24570.23 | 2861.3578 | 13% | 50 |  | 0 | REGULATOR REPLACED BY CYNTHIA FARIS ON 5/6/2019 ER350 INSTALLED BY WADE SHIMFESS ON 7/21/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/16/2021 GCCC TICKET NOT REQUIRED ON 2/16/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK 2/16/21 CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026801300 | 584 | EX | RET. FN 50 FOR EXTRA LP OPP | 2019-05-06 | 100 VENICE PK | F | 54.9718 | 245 | 190.0282 | 346% |  |  | 0 | REGULATOR REPLACED BY CYNTHIA FARIS ON 5/6/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/16/2021 GCCC TICKET NOT REQUIRED ON 2/16/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK 2/16/21 CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026801400 | 583 | EX | INST. FN 16538 EXTRA LP OPP | 2019-05-08 | 375 STONE RD | F | 21708.8722 | 28820.93 | 7112.0578 | 33% | 50 |  | 0 | REGULATOR INSTALLED BY JAMES KEESEE ON 5/8/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 7/22/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/13/2021 GCCC TICKET NOT REQUIRED ON 5/13/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026801500 | 584 | EX | RET. FN 16538 FOR EXTRA LP OPP | 2019-05-08 | 375 STONE RD | F | 54.9718 | 245.8 | 190.8282 | 347% |  |  | 0 | REGULATOR REPLACED BY JAMES KEESEE ON 5/8/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/13/2021 GCCC TICKET NOT REQUIRED ON 5/13/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026801600 | 583 | EX | INST. FN 14063 EXTRA LP OPP | 2019-05-08 | 649 S ADDISON ST | F | 21708.8722 | 19363.69 | -2345.1822 | -11% | 50 |  | 0 | GCCC# 11422 GCCC# 12986 CMCHOLAN 2-24-2021 CCC# 12986 REGULATOR INSTALLED BY JAMES KEESEE ON 5/8/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026801700 | 584 | EX | RET. FN 14063 FOR EXTRA LP OPP | 2019-05-08 | 649 S ADDISON ST | F | 54.9718 | 310.43 | 255.4582 | 465% |  |  | 0 | REGULATOR REPLACED BY JAMES KEESEE ON 5/8/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026801800 | 583 | EX | INST. FN 59 EXTRA LP OPP | 2019-04-24 | 101 PENMOKEN PK | F | 21708.8722 | 1234397.45 | 1212688.5778 | 5,586% | 50 |  | 0 | REGULATOR INSTALLED BY JAMES PASLEY ON 4/24/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 7/21/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026801900 | 584 | EX | RET. FN 59 FOR EXTRA LP OPP | 2019-04-24 | 101 PENMOKEN PK | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 4/24/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026802000 | 583 | EX | INST. FN 64 EXTRA LP OPP | 2020-09-24 | 410 MARQUIS AV | F | 23795.1646 | 35892.03 | 12096.8654 | 51% | 50 |  | 0 | ESPARKS 11-16-20 REGULATOR AND ER350 INSTALLED BY CHRIS COX ON 9/24/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/17/2021 GCCC TICKET NOT REQUIRED ON 5/17/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026802100 | 584 | EX | RET. FN 64 FOR EXTRA LP OPP | 2020-09-24 | 410 MARQUIS AV | F | 53.6219 | 0 | -53.6219 | 100% |  |  | 0 | REGULATOR REPLACED BY CHRIS COX ON 9/24/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/17/2021 GCCC TICKET NOT REQUIRED ON 5/17/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026802200 | 583 | EX | INST. FN 14459 EXTRA LP OPP | 2019-07-29 | 1590 HARRODSBURG RD | F | 21708.8722 | 38152.65 | 16443.7778 | 76% | 50 |  | 0 | REGULATORS INSTALLED BY JAMES PASLEY ON 7/29/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026802300 | 584 | EX | RET. FN 14459 FOR EXTRA LP OPP | 2019-07-29 | 1590 HARRODSBURG RD | F | 54.9718 | 315.03 | 260.0582 | 473% |  |  | 0 | REGULATORS REPLACED BY JAMES PASLEY ON 7/29/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026802400 | 583 | EX | INST. FN 13485 EXTRA LP OPP | 2019-05-01 | 707 LANE ALLEN RD | F | 21708.8722 | 37984.09 | 16275.2178 | 75% | 50 |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 5/1/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 7/23/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/19/2021 GCCC TICKET NOT REQUIRED ON 2/19/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026802500 | 584 | EX | RET. FN 13485 FOR EXTRA LP OPP | 2019-05-01 | 707 LANE ALLEN RD | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 5/1/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/19/2021 GCCC TICKET NOT REQUIRED ON 2/19/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026802600 | 583 | EX | INST. FN 13502 EXTRA LP OPP | 2019-07-23 | 2108 NICHOLASVILLE RD | F | 22950.8722 | 26279.01 | 3328.1378 | 15% | 50 |  | 0 | REGULATOR INSTALLED BY WADE SHIMFESSEL ON 07/23/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/18/2021 GCCC TICKET NOT REQUIRED ON 2/18/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026802700 | 584 | EX | RET. FN 13502 FOR EXTRA LP OPP | 2019-07-23 | 2108 NICHOLASVILLE RD | F | 54.9718 | 658.8 | 603.8282 | 1,098% |  |  | 0 | REGULATOR REPLACED BY WADE SHIMFESSEL ON 7/23/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/18/2021 GCCC TICKET NOT REQUIRED ON 2/18/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026802800 | 583 | EX | INST. FN 14168 EXTRA LP OPP | 2020-10-06 | 785 CHERYL LN | F | 42784.1646 | 51690.09 | 8905.9254 | 21% | 53 |  | 0 | REGULATOR REPLACED BY WADE SHIMFESSEL ON 10/6/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/18/2021 GCCC TICKET NOT REQUIRED ON 2/18/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026802900 | 584 | EX | RET. FN 14168 FOR EXTRA LP OPP | 2020-10-06 | 785 CHERYL LN | F | 53.6219 | 2180 | 2126.3781 | 3,966% |  |  | 0 | REGULATORS REPLACED BY WADE SHIMFESSEL ON 10/6/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/18/2021 GCCC TICKET NOT REQUIRED ON 2/18/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026803000 | 583 | EX | INST. FN 72 EXTRA LP OPP | 2019-07-22 | 1200 S BROADWAY ST | F | 21708.8722 | 38998.63 | 17289.7578 | 80% | 50 |  | 0 | REGULATOR REPLACED BY WADE SHIMFESSEL ON 7/22/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/18/2021 GCCC TICKET NOT REQUIRED ON 2/18/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026803100 | 584 | EX | RET. FN 72 FOR EXTRA LP OPP | 2019-07-22 | 1200 S BROADWAY ST | F | 54.9718 | 820.09 | 765.1182 | 1,392% |  |  | 0 | RETIRE MONITOR REG REGULATOR REPLACED BY WADE SHIMFESSEL ON 7/22/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/18/2021 GCCC TICKET NOT REQUIRED ON 2/18/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK 2/18/21 CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026803200 | 583 | EX | INST. FN 13481 EXTRA LP OPP | 2019-07-09 | 1630 N BROADWAY ST | F | 21708.8722 | 34055.64 | 12346.7678 | 57% | 50 |  | 0 | REGULATOR INSTALLED BY JAMES PASLEY ON 7/9/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026803300 | 584 | EX | RET. FN 13481 FOR EXTRA LP OPP | 2019-07-09 | 1630 N BROADWAY ST | F | 54.9718 | 326.13 | 271.1582 | 493% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 7/9/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026803400 | 583 | EX | INST. FN 14049 EXTRA LP OPP | 2020-07-08 | 1406 VERSAILLES RD | F | 21579.1646 | 23794.44 | 2215.2754 | 10% | 50 |  | 0 | GCCC# 11422 REGULATOR REPLACED AND ER350 INSTALLED BY CHRIS COX ON 7/8/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 02192021 GCCC TICKET NOT REQUIRED ON 2/19/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026803500 | 584 | EX | RET. FN 14049 FOR EXTRA LP OPP | 2020-07-08 | 1406 VERSAILLES RD | F | 53.9767 | 487.75 | 433.7733 | 804% |  |  | 0 | REGULATOR REPLACED BY CHRIS COX ON 7/8/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/19/2021 GCCC TICKET NOT REQUIRED ON 2/19/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026803600 | 583 | EX | INST. FN 78 EXTRA LP OPP | 2019-05-02 | 1706 CLAYS MILL RD | F | 21708.8722 | 36386.58 | 14677.7078 | 68% | 50 |  | 0 | CMCHOLAN 2-23-2021 CCC# 12914 GCCC# 12914 REGULATOR INSTALLED BY JAMES PASLEY ON 5/2/2019 ER350 INSTALLED ON 2/23/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026803700 | 584 | EX | RET. FN 78 FOR EXTRA LP OPP | 2019-05-02 | 1706 CLAYS MILL RD | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 5/2/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026803800 | 583 | EX | INST. FN 14160 EXTRA LP OPP | 2019-05-03 | 567 MITCHELL AV | F | 21708.8722 | 28008.15 | 6299.2778 | 29% | 50 |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 5/3/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 7/23/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/18/2021 GCCC TICKET NOT REQUIRED ON 2/18/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026803900 | 584 | EX | RET. FN 14160 FOR EXTRA LP OPP | 2019-05-03 | 567 MITCHELL AV | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 5/3/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/18/2021 GCCC TICKET NOT REQUIRED ON 2/18/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026804000 | 583 | EX | INST. FN 14154 EXTRA LP OPP | 2019-07-25 | 2209 CLAYS MILL RD | F | 22950.8722 | 23168.82 | 217.9478 | 1% | 50 |  | 0 | REGULATOR INSTALLED BY WADE SHIMFESSEL ON 7/25/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 7/22/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/11/2021 GCCC TICKET NOT REQUIRED ON 5/11/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026804100 | 584 | EX | RET. FN 14154 FOR EXTRA LP OPP | 2019-07-25 | 2209 CLAYS MILL RD | F | 54.9718 | 2296.06 | 2241.0882 | 4,077% |  |  | 0 | REGULATOR REPLACED BY WADE SHIMFESSEL ON 7/25/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/11/2021 GCCC TICKET NOT REQUIRED ON 5/11/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026804200 | 583 | EX | INST. FN 82 EXTRA LP OPP | 2020-11-05 | 402 QUEENSWAY DR | F | 23795.1646 | 25172.58 | 1377.4154 | 6% | 50 |  | 0 | GCCC# 11659 REGULATORS AND ER350 INSTALLED BY WADE SHIMFESSEL ON 11/5/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/23/2021 GCCC TICKET NOT REQUIRED ON 2/23/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026804300 | 583 | EX | INST. FN 83 EXTRA LP OPP | 2019-07-10 | 98 GLASS AV | F | 21708.8722 | 39811.91 | 18103.0378 | 83% | 50 |  | 0 | REGULATOR INSTALLED BY JAMES PASLEY ON 07-10-2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 08-17-2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 01292021 GCCC TICKET NOT REQUIRED ON 1-29-21 NOT AT STATION OFF SITE COMPLETING PAPERWORK
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026804400 | 584 | EX | RET. FN 83 FOR EXTRA LP OPP | 2019-07-10 | 98 GLASS AV | F | 54.9718 | 344.1 | 289.1282 | 526% |  |  | 0 | REGULATOR REPLACED BY JAMES PASELY ON 7/10/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/29/2021 GCCC TICKET NOT REQUIRED ON 1/29/21 PAPERWORK COMPLETED OFF SITE NOT AT REGULATOR STATION
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026804500 | 583 | EX | INST. FN 84 EXTRA LP OPP | 2020-11-24 | 1200 ROBERTSON AV | F | 23795.1646 | 22425.42 | -1369.7446 | -6% | 50 |  | 0 | REGULATORS REPLACED AND ER350 INSTALLED BY CHRIS COX ON 11/24/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/22/2021 GCCC TICKET NOT REQUIRED ON 2/22/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026804600 | 584 | EX | RET. FN 84 FOR EXTRA LP OPP | 2020-11-24 | 1200 ROBERTSON AV | F | 53.9767 | 0 | -53.9767 | 100% |  |  | 0 | REGULATORS REPLACED BY CHRIS COX ON 11/24/2020 PAPERWORK COMPLETD BY CYNTHIA FARIS ON 2/22/2021 GCCC TICKET NOT REQUIRED ON 2/22/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026804700 | 583 | EX | INST. FN 13493 EXTRA LP OPP | 2020-11-10 | 1805 OLD PARIS RD | F | 40101.1646 | 31354.84 | -8746.3246 | -22% | 55 |  | 0 | GCCC# 11422 REGULATORS AND ER350 INSTALLED BY WADE SHIMFESSEL ON 11/10/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/17/2021 GCCC TICKET NOT REQUIRED ON 5/17/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026804800 | 583 | EX | INST. FN 86 EXTRA LP OPP | 2020-12-08 | 1100 TATES CREEK RD | F | 43801.1646 | 60322.65 | 16521.4854 | 38% | 55 |  | 0 | PAID FRIDAY 05/22/20 ON THURSDAY 05/21/20 REGULATORS AND ER350 INSTALLED BY CHRIS COX ON 12/8/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026804900 | 584 | EX | RET. FN 86 FOR EXTRA LP OPP | 2020-12-08 | 1100 TATES CREEK RD | F | 53.6219 | 558.18 | 504.5581 | 941% |  |  | 0 | REGULATORS REPLACED BY CHRIS COX ON 12/8/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026805000 | 583 | EX | INST. FN 13503 EXTRA LP OPP | 2020-09-24 | 199 EDDIE ST | F | 44603.1646 | 63493.93 | 18890.7654 | 42% | 55 |  | 0 | VOIDED PAY SHEET 008277 PU IN WRONG DATE CORRECTED ON CONTROL SHEET 008278 REGULATORS AND ER350 INSTALLED BY WADE SHIMFESSEL ON 9/24/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/18/2021 GCCC TICKET NOT REQUIRED ON 5/18/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026805100 | 584 | EX | RET. FN 13503 FOR EXTRA LP OPP | 2020-09-24 | 199 EDDIE ST | F | 53.6219 | 0 | -53.6219 | 100% |  |  | 0 | REGULATORS REPLACED BY WADE SHIMFESSEL ON 9/24/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/18/2021 GCCC TICKET NOT REQUIRED ON 5/18/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026805200 | 583 | EX | INST. FN 88 EXTRA LP OPP | 2019-06-20 | 520 OLDHAM AV | F | 21708.8722 | 27335.82 | 5626.9478 | 26% | 50 |  | 0 | INLET AND OUTLET VLV FULL OPEN - BYPASS VLV OFF AND LOCKED REGULATOR INSTALLED BY JAMES PASLEY ON 6/20/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 8/28/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/29/2021 GCCC TICKET NOT REQUIRED ON 1/29/21 PAPERWORK COMPLETED OFF SITE NOT AT REQULATOR STATION
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026805300 | 584 | EX | RET. FN 88 FOR EXTRA LP OPP | 2019-06-20 | 520 OLDHAM AV | F | 54.9718 | 248.87 | 193.8982 | 353% |  |  | 0 | REGULATOR REPLACED BY JIM PASLEY ON 6/20/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS 1/29/2021 GCCC TICKET NOT REQUIRED ON 1/29/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026805400 | 583 | EX | INST. FN 89 EXTRA LP OPP | 2020-11-09 | 125 BARR ST | F | 23795.1646 | 23326.17 | -468.9946 | -2% | 50 |  | 0 | REGULATORS AND ER350 INSTALLED BY WADE SHIMFESSEL ON 11/9/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/17/2021 GCCC TICKET NOT REQUIRED ON 5/17/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026805500 | 584 | EX | RET. FN 89 FOR EXTRA LP OPP | 2020-11-09 | 125 BARR ST | F | 53.6219 | 0 | -53.6219 | 100% |  |  | 0 | REGULATORS REPLACED BY WADE SHIMFESSEL ON 11/9/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/17/2021 GCCC TICKET NOT REQUIRED ON 5/17/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026805600 | 583 | EX | INST. FN 13351 EXTRA LP OPP | 2019-06-26 | 1039 GOODWIN DR | F | 21708.8722 | 25284.87 | 3575.9978 | 16% | 50 |  | 0 | REGULATOR INSTALLED BY JAMES PASLEY ON 06-26-2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 8-28-2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1-29-2021 GCCC TICKET NOT REQUIRED ON 1-29-21 PAPERWORK COMPLETED OFF SITE NOT AT REGULATOR STATION
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026805700 | 584 | EX | RET. FN 13351 FOR EXTRA LP OPP | 2019-06-26 | 1039 GOODWIN DR | F | 54.9718 | 269.43 | 214.4582 | 390% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 6-26-2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1-29-2021 GCCC TICKET NOT REQUIRED ON 1-29-21 PAPERWORK COMPLETED OFF SITE NOT AT REGULATOR STATION
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026805800 | 583 | EX | INST. FN 13487 EXTRA LP OPP | 2019-07-26 | 551 NEWTOWN PK | F | 22950.8722 | 25980.27 | 3029.3978 | 13% | 50 |  | 0 | REGULATOR INSTALLED BY WADE SHIMFESSEL ON 7/26/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 8/17/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026805900 | 584 | EX | RET. FN 13487 FOR EXTRA LP OPP | 2019-07-26 | 551 NEWTOWN PK | F | 54.9718 | 566.82 | 511.8482 | 931% |  |  | 0 | REGULATOR REPLACED BY WADE SHIMFESSEL ON 7/26/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026806000 | 583 | EX | INST. FN 13441 EXTRA LP OPP | 2019-05-07 | 296 SOUTHLAND DR | F | 21708.8722 | 54596.92 | 32888.0478 | 151% | 50 |  | 0 | GCCC TICKET NOT REQUIRED ON 2/17/21 NOT AT STATION OFF SITE WORKING ON LP PAPERWORK CFARIS REGULATOR REPLACED BY CYNTHIA FARIS ON 5/7/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/19/2021 GCCC TICKET NOT REQUIRED ON 2/19/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026806100 | 584 | EX | RET. FN 13441 FOR EXTRA LP OPP | 2019-05-07 | 296 SOUTHLAND DR | F | 54.9718 | 261.78 | 206.8082 | 376% |  |  | 0 | REGULATOR REPLACED BY CYNTHIA FARIS ON 5/7/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/19/2021 GCCC TICKET NOT REQUIRED ON 2/19/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026806200 | 583 | EX | INST. FN 13573 EXTRA LP OPP | 2019-06-20 | 834 E 3RD ST | F | 21708.8722 | 31687.43 | 9978.5578 | 46% | 50 |  | 0 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 06202019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/11/2021 GCCC TICKET NOT RQUIRED ON 5/11/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026806300 | 584 | EX | RET. FN 13573 FOR EXTRA LP OPP | 2019-06-20 | 834 E 3RD ST | F | 54.9718 | 2.49 | -52.4818 | -95% |  |  | 0 | REGULATOR REPLACED BY CYNTHIA FARIS ON 6/20/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/11/2021 GCCC TICKET NOT REQUIRED ON 5/11/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026806400 | 583 | EX | INST. FN 14199 EXTRA LP OPP | 2019-06-17 | 364 LIMA DR | F | 21708.8722 | 21811.55 | 102.6778 | 0% | 50 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 6/17/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 8/17/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026806500 | 584 | EX | RET. FN 14199 FOR EXTRA LP OPP | 2019-06-17 | 364 LIMA DR | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 6/17/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026806600 | 583 | EX | INST. FN 14143 EXTRA LP OPP | 2019-06-04 | 676 LOUDON AV | F | 21708.8722 | 33726.29 | 12017.4178 | 55% | 50 |  | 0 | INLET VALVE AND OUTLET VALVE FULL ON. BYPASS VALVE OFF AND LOCKED. JPASLEY 05/31/2019. REGULATOR INSTALLED BY JAMES PASLEY ON 6/4/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026806700 | 584 | EX | RET. FN 14143 FOR EXTRA LP OPP | 2019-06-04 | 676 LOUDON AV | F | 54.9718 | 251 | 196.0282 | 357% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 6/4/2019 PAPERWORK COMPLETED BY CYTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026806800 | 583 | EX | INST. FN 114 EXTRA LP OPP | 2020-11-17 | 1310 BRYAN AV | F | 43910.1646 | 42655.72 | -1254.4446 | -3% | 57 |  | 0 | ESPARKS 11-18-20 REGULATORS AND ER350 INSTALLED BY CHRIS COX ON 11/17/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/18/2021 GCCC TICKET NOT REQUIRED ON 5/18/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026806900 | 584 | EX | RET. FN 114 FOR EXTRA LP OPP | 2020-11-17 | 1310 BRYAN AV | F | 53.6219 | 3001.35 | 2947.7281 | 5,497% |  |  | 0 | REGULATORS REPLACED BY CHRIS COX ON 11/17/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/18/2021 GCCC TICKET NOT REQUIRED ON 5/18/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026807000 | 583 | EX | INST. FN 115 EXTRA LP OPP | 2021-03-04 | 543 SMITH ST | F | 24102.8722 | 28771.63 | 4668.7578 | 19% | 50 |  | 0 | GCCC# 11422 CHARED TIME TO COLLECT MATERIAL. DID NOT VISIT SITE NO GCCC TICKET REQUIRED CMCOC 3/3/21 GCCC# 13985 CMCHOLAN 3-4-2021 CCC#13985 REGULATOR AND ER350 INSTALLED BY CHRIS COX ON 3/4/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026807100 | 584 | EX | RET. FN 115 FOR EXTRA LP OPP | 2021-03-04 | 543 SMITH ST | F | 54.9718 | 2550 | 2495.0282 | 4,539% |  |  | 0 | REGULATOR REPLACED BY CHRIS COX ON 3/4/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026807200 | 583 | EX | INST. FN 116 EXTRA LP OPP | 2020-08-12 | 739 AURORA AV | F | 24062.1646 | 21387.49 | -2674.6746 | -11% | 50 |  | 0 | GCCC# 11279 CMCOX 2/5/21 REGULATOR INSTALLED BY WADE SHIMFESSEL ON 8/12/2020 ER350 INSTALLED BY CHRIS COX ON 2/5/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/8/21 GCCC TICKET NOT REQUIRED ON 2/8/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026807300 | 584 | EX | RET. FN 116 FOR EXTRA LP OPP | 2020-08-12 | 739 AURORA AV | F | 53.9767 | 0 | -53.9767 | 100% |  |  | 0 | REGULATOR REPLACED BY WADE SHIMFESSEL ON 8/12/20 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/8/21 GCCC TICKET NOT REQUIRED ON 2/8/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026807400 | 583 | EX | INST. FN 117 EXTRA LP OPP | 2020-07-20 | 120 JERSEY ST | F | 22920.1646 | 31492.92 | 8572.7554 | 37% | 50 |  | 0 | GCCC# 12986 CMCHOLAN 2-24-2021 CCC#12986 REGULATOR INSTALLED BY WADE SHIMFESSEL ON 7/20/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026807500 | 584 | EX | RET. FN 117 FOR EXTRA LP OPP | 2020-07-20 | 120 JERSEY ST | F | 67.9767 | 4679.14 | 4611.1633 | 6,783% |  |  | 0 | REGULATOR REPLACED BY WADE SHIMFESSEL ON 7/20/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026807600 | 583 | EX | INST. FN 14207 EXTRA LP OPP | 2019-06-21 | 101 W LOUDON AV | F | 21708.8722 | 20146.93 | -1561.9422 | -7% | 50 |  | 0 | REGULATOR INSTALLED BY JAMES PASLEY ON 6/21/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 8/28/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/13/2021 GCCC TICKET NOT REQUIRED ON 5/13/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026807700 | 584 | EX | RET. FN 14207 FOR EXTRA LP OPP | 2019-06-21 | 101 W LOUDON AV | F | 54.9718 | 531.21 | 476.2382 | 866% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 6/21/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/13/2021 GCCC TICKET NOT REQUIRED ON 5/13/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026807800 | 583 | EX | INST. FN 119 EXTRA LP OPP | 2019-06-17 | 1091 MEADOW LN | F | 21708.8722 | 18902.08 | -2806.7922 | -13% | 50 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 6/17/19 ER350 INSTALLED BY CYNTHIA FARIS ON 9/10/19 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/2/21 GCCC TICKET NOT REQUIRED ON 2/2/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026807900 | 584 | EX | RET. FN 119 FOR EXTRA LP OPP | 2019-06-17 | 1091 MEADOW LN | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 6/17/19 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/2/21 GCCC TICKET NOT REQUIRED ON 2/2/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026808000 | 583 | EX | INST. FN 212 EXTRA LP OPP | 2020-12-16 | 403 E THIRD ST | F | 24102.8722 | 55008.15 | 30905.2778 | 128% | 50 |  | 0 | ESPARKS 12-16-20 REGULATOR INSTALLED BY CHRIS COX ON 12/16/2020 ER350 NOT INSTALLED STATION HAS EXISTING ERX PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS THIS IS A MAJOR PROJECTS PROJECT. THEY ARE MANAGING THE VARIANCE AT THE PROJECT LEVEL. SEE WMSDOCS. AS OF 6/14/21, THE PROJECT IS STILL ONGOING. CONTACT HEATH HOLMAN FOR DETAILS.
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026808100 | 584 | EX | RET. FN 212 FOR EXTRA LP OPP | 2020-12-16 | 403 E THIRD ST | F | 54.9718 | 2180 | 2125.0282 | 3,866% |  |  | 0 | REGULATOR REPLACED BY CHRIS COX ON 12/16/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026808200 | 583 | EX | INST. FN 13665 EXTRA LP OPP | 2019-06-25 | 101 IDLE HOUR DR | F | 21708.8722 | 29668.21 | 7959.3378 | 37% | 50 |  | 0 | REGULATOR INSTALLED BY JAMES PASLEY ON 6/25/2019 ER350 INSTALLED BY CHRIS COX ON 8/13/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/4/2021 GCCC TICKET NOT REQUIRED ON 5/4/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026808300 | 584 | EX | RET. FN 13665 FOR EXTRA LP OPP | 2019-06-25 | 101 IDLE HOUR DR | F | 54.9718 | 247.21 | 192.2382 | 350% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 6/25/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/4/2021 GCCC TICKET NOT REQUIRED ON 5/4/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026808400 | 583 | EX | INST. FN 223 EXTRA LP OPP | 2020-08-18 | 1107 COOPER DR | F | 23795.1646 | 18282.98 | -5512.1846 | -23% | 50 |  | 0 | CCC# 32488 - CHECKED SERIAL NUMBERS - BLONE - 07/23/21 REGULATOR INSTALLED BY JAMES PASLEY ON 8/18/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/26/2021 GCCC TICKET NOT REQUIRED ON 7/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026808500 | 584 | EX | RET. FN 223 FOR EXTRA LP OPP | 2020-08-18 | 1107 COOPER DR | F | 58.6033 | 577.85 | 519.2467 | 886% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 8/18/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/26/2021 GCCC TICKET NOT REQUIRED ON 7/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026808600 | 583 | EX | INST. FN 224 EXTRA LP OPP | 2020-09-02 | 1601 RICHMOND RD | F | 24062.1646 | 219880.56 | 195818.3954 | 814% | 50 |  | 0 | ESPARKS 11-20-20 REGULATOR AND ER350 INSTALLED BY CHRIS COX ON 9/2/20 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/17/2021 GCCC TICKET NOT REQUIRED ON 5/17/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS THIS IS A MAJOR PROJECTS PROJECT. THEY ARE MANAGING THE VARIANCE AT THE PROJECT LEVEL. SEE WMSDOCS. AS OF 6/14/21, THE PROJECT IS STILL ONGOING. CONTACT HEATH HOLMAN QUESTIONS ABOUT DETAILS.
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026808700 | 584 | EX | RET. FN 224 FOR EXTRA LP OPP | 2020-09-02 | 1601 RICHMOND RD | F | 53.9767 | 0 | -53.9767 | 100% |  |  | 0 | REGULATOR REPLACED BY CHRIS COX ON 9/2/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/17/2021 GCCC TICKET NOT REQUIRED ON 5/17/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026808800 | 583 | EX | INST. FN 259 EXTRA LP OPP | 2021-07-27 | 1005 RICHMOND RD | F | 23795.1646 | 258499.79 | 234704.6254 | 986% | 50 |  | 0 | NOT ONSITE. NO GCCC TICKET REQUIRED. CMCOX 7/6/21 GCCC# 30701 CMCOX 7/7/21 NOT ONSITE. NO GCCC TICKET REQUIRED. CMCOX 7/8/21 CCC# 31111 GCCC# 31231 CMCOX 7/13/21 GCCC# 31380 GCCC# 31536 GCCC# 31616 DID NOT ENTER PIT. NO GCCC# REQUIRED. CMCOX 7/19//21 GCCC# 31756 CMCOX 7/20/21 CC# 32093 REGULATORS INSTALLED BY CHRIS COX 7/27/21 PAPERWORK COMPLETED BY CFARIS 7/29/21 CCC# NOT REQUIRED BY CFARIS ON 7/29 OR 8/2 NOT AT STATION
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026808900 | 584 | EX | RET. FN 259 FOR EXTRA LP OPP | 2021-07-27 | 1005 RICHMOND RD | F | 53.9767 | 0 | -53.9767 | 100% |  |  | 0 | REGULATORS REPLACED BY CHRIS COX ON 7/27/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/29/2021 GCCC TICKET NOT REQUIRED ON 7/29/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026809200 | 583 | EX | INST. FN 264 EXTRA LP OPP | 2019-06-28 | ROSE ST | F | 21708.8722 | 23191.48 | 1482.6078 | 7% | 50 |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 6/28/19 ER350 INSTALLED BY WADE SHIMFESSEL ON 8/28/20 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/2/21 GCCC TICKET NOT REQUIRED ON 2/2/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026809300 | 584 | EX | RET. FN 264 FOR EXTRA LP OPP | 2020-06-28 | ROSE ST | F | 54.9718 | 348.91 | 293.9382 | 535% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 6/28/19 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/2/21 GCCC TICKET NOT REQUIRED ON 2/2/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026809400 | 583 | EX | INST. FN 265 EXTRA LP OPP | 2020-09-16 | 800 PRESS AV | F | 23795.1646 | 231884.47 | 208089.3054 | 875% | 50 |  | 0 | 2/19/21 GCCC TICKET NOT REQUIRED NOT AT STATION OFF SITE WORKING ON LP PAPERWORK CFARIS 2/25/21 GCCC TICKET NOT REQUIRED NOT AT STATION OFF SITE COMPLETING LP PAPERWORK CFARIS CCC TICKET NOT REQUIRED NOT AT STATION 4/21/21 CFARIS CCC TICKET NOT REQUIRED NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS 6/24/21 CCC# 32497 - CHECKING SERIAL NUMBERS - BLONE - 07/23/21 REGULATOR REPLACED BY JAMES PASLEY ON 9/16/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/26/2021 GCCC TICKET NOT REQUIRED ON 7/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS VAR EXPLANATION: MAJOR PROJECTS PROJECT. VARIANCE MANAGED AT PROJECT LEVEL
KY | KY - WEST | 2621 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 18026809500 | 584 | EX | RET. FN 265 FOR EXTRA LP OPP | 2020-09-16 | 800 PRESS AV | F | 50.3519 | 352.38 | 302.0281 | 600% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 9/16/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/26/2021 GCCC TICKET NOT REQUIRED ON 7/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026810200 | 583 | EX | INST. FN 275 EXTRA LP OPP | 2020-09-03 | 451 BOB O LINK DR | F | 23795.1646 | 41511.72 | 17716.5554 | 74% | 50 |  | 0 | 2/4/21 GCCC TICKET NOT REQUIRED NOT AT STATION OFF SITE WORKING ON LP PAPERWORK CFARIS GCCC TICKET NOT REQUIRED NOT AT STATION OFF SITE COMPLETING PAPERWORK 2/22/21 CFARIS CCC TICKET NOT REQUIRED 4/8/21 NOT AT STATION CFARIS REGULATOR INSTALLED BY CHRIS COX ON 9/3/2020 ER350 INSTALLED BY CHRIS COX ON 10/28/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/30/2021 GCCC TICKET NOT REQUIRED ON 4/30/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026810300 | 584 | EX | RET. FN 275 FOR EXTRA LP OPP | 2020-09-03 | 451 BOB O LINK DR | F | 53.6219 | 255 | 201.3781 | 376% |  |  | 0 | REGULATOR REPLACED BY CHRIS COX ON 9/3/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/30/2021 GCCC TICKET NOT REQUIRED ON 4/30/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026810800 | 583 | EX | INST. FN 14064 EXTRA LP OPP | 2019-05-01 | 1800 MASON-HEADLEY RD | F | 21708.8722 | 48664.41 | 26955.5378 | 124% | 50 |  | 0 | GCCC TICKET NOT REQUIRED NOT AT ANY STATION OFF SITE WORKING ON PAPERWORK CFARIS 1/29/21 REGULATOR INSTALLED BY JAMES PASLEY ON 5/1/2019 ER350 INSTALLED ON 12/7/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/19/2021 GCCC TICKET NOT REQUIRED ON 5/19/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026810900 | 584 | EX | RET. FN 14064 FOR EXTRA LP OPP | 2019-05-01 | 1800 MASON-HEADLEY RD | F | 54.9718 | 1353 | 1298.0282 | 2,361% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 5/1/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/19/2021 GCCC TICKET NOT REQUIRED ON 5/19/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026811200 | 583 | EX | INST. FN 311 EXTRA LP OPP | 2020-12-09 | 1040 MANCHESTER ST | F | 38500.1646 | 29005.69 | -9494.4746 | -25% | 55 |  | 0 | REGULATOR AND ER350 INSTALLED BY CHRIS COX ON 12/9/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026811300 | 584 | EX | RET. FN 311 FOR EXTRA LP OPP | 2020-12-09 | 1040 MANCHESTER ST | F | 53.9767 | 658.65 | 604.6733 | 1,120% |  |  | 0 | REGULATORS REPLACED BY CHRIS COX ON 12/09/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 05/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026811800 | 583 | EX | INST. FN 373 EXTRA LP OPP | 2019-07-30 | 469 GREENWOOD DR | F | 21708.8722 | 19746.85 | -1962.0222 | -9% | 50 |  | 0 | GCCC# 13164 CMCHOLAN 2-25-2021 CCC# 13164 REGULATOR INSTALLED BY JAMES PASLEY ON 7/30/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026811900 | 584 | EX | RET. FN 373 FOR EXTRA LP OPP | 2019-07-30 | 469 GREENWOOD DR | F | 54.9718 | 269.18 | 214.2082 | 390% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 7/30/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026812000 | 583 | EX | INST. FN 13501 EXTRA LP OPP | 2019-07-31 | 535 W MAIN ST | F | 22950.8722 | 17550.95 | -5399.9222 | -24% | 50 |  | 0 | GCCC# 13340 CMCHOLAN 2-26-2021 CCC#13340 REGULATOR INSTALLED BY JAMES PASLEY ON 7/31/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026812100 | 584 | EX | RET. FN 13501 FOR EXTRA LP OPP | 2019-07-31 | 535 W MAIN ST | F | 54.9718 | 826.34 | 771.3682 | 1,403% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 7/31/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026812200 | 583 | EX | INST. FN 14184 EXTRA LP OPP | 2020-07-28 | 881 REBECCA DR | F | 23795.1646 | 31976.99 | 8181.8254 | 34% | 50 |  | 0 | REGULATOR AND ER350 INSTALLED BY WADE SHIMFESSEL ON 7/29/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/29/2021 GCCC TICKET NOT REQUIRED ON 4/29/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026812300 | 584 | EX | RET. FN 14184 FOR EXTRA LP OPP | 2020-07-28 | 881 REBECCA DR | F | 53.6219 | 255 | 201.3781 | 376% |  |  | 0 | REGULATOR REPLACED BY WADE SHIMFESSEL ON 7/28/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/29/2021 GCCC TICKET NOT REQUIRED ON 4/29/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026812400 | 583 | EX | INST. FN 14068 EXTRA LP OPP | 2019-06-24 | ALUMNI DR | F | 21708.8722 | 28402.42 | 6693.5478 | 31% | 50 |  | 0 | INLET AND OUTLET VLV FULL ON - BYPASS OFF AND LOCKED JPASLEY GCCC# 11659 CMCHOLAN 2-10-2021 CCC# 11659 REGULATOR REPLACED BY JAMES PASLEY ON 6/24/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 8/18/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/19/2021 GCCC TICKET NOT REQUIRED ON 2/19/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026812500 | 584 | EX | RET. FN 14068 FOR EXTRA LP OPP | 2019-06-24 | ALUMNI DR | F | 54.9718 | 247.21 | 192.2382 | 350% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 6/24/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/19/2021 GCCC TICKET NOT REQUIRED ON 2/19/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026812800 | 583 | EX | INST. FN 13476 EXTRA LP OPP | 2019-06-21 | 138 PARIS AV | F | 21708.8722 | 23181.26 | 1472.3878 | 7% | 50 |  | 0 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 6/21/2019 ER350 INSTALLED BYWADE SHIMFESSEL ON 8/18/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026812900 | 584 | EX | RET. FN 13476 FOR EXTRA LP OPP | 2019-06-21 | 138 PARIS AV | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY CYNTHIA FARIS ON 6/21/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026813000 | 583 | EX | INST. FN 842 EXTRA LP OPP | 2020-09-08 | 601 COOPER DR | F | 23795.1646 | 29080.45 | 5285.2854 | 22% | 50 |  | 0 | 1/18/21 GCCC TICKET NOT REQUIRED NOT ON SITE AT ANY STATION OFF SITE WORKING ON PAPERWORK GCCC TICKET NOT REQUIRED 2/18/21 NOT AT STATION OFF SITE WORKING ON LP PAPERWORK CFARIS CCC TICKET NOT REQUIRED NOT AT STATION OFF SITE COMPLETING PAPERWORK 4/12/21 CFARIS CCC TICKET NOT REQUIRED 4/15/21 REGULATOR AND ER350 INSTALLED BY WADE SHIMFESSEL ON 9/8/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/29/2021 GCCC TICKET NOT REQUIRED ON 4/29/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026813100 | 584 | EX | RET. FN 842 FOR EXTRA LP OPP | 2020-09-08 | 601 COOPER DR | F | 57.9057 | 0 | -57.9057 | 100% |  |  | 0 | REGULATOR REPLACED BY WADE SHIMFESSEL ON 9/8/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/29/2021 GCCC TICKET NOT REQUIRED ON 4/29/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026813200 | 583 | EX | INST. FN 19921 EXTRA LP OPP | 2019-06-19 | 1684 WAKEFIELD TR | F | 21708.8722 | 29246.62 | 7537.7478 | 35% | 50 |  | 0 | INLET AND OUTLET VLVS ON - BYPASS VLV OFF AND LOCKED REGULATOR REPLACED BY JAMES PASLEY ON 06/19/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/4/2021 GCCC TICKET NOT REQUIRED ON 5/4/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026813300 | 584 | EX | RET. FN 19921 FOR EXTRA LP OPP | 2019-06-19 | 1684 WAKEFIELD TR | F | 54.9718 | 251.98 | 197.0082 | 358% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 6/19/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/4/2021 GCCC TICKET NOT REQUIRED ON 5/4/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026813400 | 583 | EX | INST. FN 22195 EXTRA LP OPP | 2019-05-23 | 2228 YOUNG DR | F | 21708.8722 | 22687.52 | 978.6478 | 5% | 50 |  | 0 | INLET AND OUTLET VLV FULL OPEN - NO BYPASS VALVE REGULATOR REPLACED BY JAMES PASLEY ON 5/23/2019 ER350 INSTALLED BY CHRIS COX ON 7/15/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/19/2021 GCCC TICKET NOT REQUIRED ON 2/19/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS REPLACED ASV CABLE RUN 1 CCOX RHAYES VS3-1303 RPLACED BOOT IN CONTROL REG DUE TO NO LOCK UP P2P WITH GAS CONTROL MONITORED 30 MIN 11-15-2021
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026813500 | 584 | EX | RET. FN 22195 FOR EXTRA LP OPP | 2019-05-23 | 2228 YOUNG DR | F | 54.9718 | 246.58 | 191.6082 | 349% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 5/23/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/19/2021 GCCC TICKET NOT REQUIRED ON 2/19/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026813600 | 583 | EX | INST. FN 22196 EXTRA LP OPP | 2019-05-24 | 2228 YOUNG DR | F | 21708.8722 | 22045.15 | 336.2778 | 2% | 50 |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 5/24/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/19/2021 GCCC TICKET NOT REQUIRED ON 2/19/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS REPLACED ASV CABLE RUN 2 RHAYES CCOX 11-15-2021 VS3-1295
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026813700 | 583 | EX | INST. FN 21499 EXTRA LP OPP | 2019-06-18 | 542 CHINOE RD | F | 21708.8722 | 13602.48 | -8106.3922 | -37% | 50 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 6/18/2019 GASKET STRAINER NOT REQUIRED SETTING HAS EXISTING T-STRAINER PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026813800 | 584 | EX | RET. FN 21499 FOR EXTRA LP OPP | 2019-06-18 | 542 CHINOE RD | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 6/18/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026813900 | 583 | EX | INST. FN 21500 EXTRA LP OPP | 2019-06-18 | 542 CHINOE RD | F | 21708.8722 | 12535.92 | -9172.9522 | -42% | 50 |  | 0 | CHECK TO SEE IF ASV WAS CLOSED, IT WAS OPEN, POSSIBLE CABLE CHANGE SMCHOLAN 10-20-2020 REGULATOR INSTALLED BY RYAN WILLIAMS ON 6/18/2019 GASKET STRAINER NOT REQUIRED SETTING HAS EXISTING T-STRAINER THIS IS PARALLEL RUN ER350 INSTALLED WITH RUN 1 JOB ORDER PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026814000 | 584 | EX | RET. FN 21500 FOR EXTRA LP OPP | 2019-06-18 | 542 CHINOE RD | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 6/18/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026814100 | 583 | EX | INST. FN 22270 EXTRA LP OPP | 2019-07-24 | SHAWNEETOWN DR | F | 22950.8722 | 24269.32 | 1318.4478 | 6% | 50 |  | 0 | REGULATOR REPLACED BY WADE SHIMFESSEL ON 7/24/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/11/2021 GCCC TICKET NOT REQUIRED ON 2/11/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026814200 | 584 | EX | RET. FN 22270 FOR EXTRA LP OPP | 2019-07-24 | SHAWNEETOWN DR | F | 54.9718 | 693.72 | 638.7482 | 1,162% |  |  | 0 | REGULATOR REPLACED BY WADE SHIMFESSEL ON 7/24/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/12/2021 GCCC TICKET NOT REQUIRED ON 2/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026814300 | 583 | EX | INST. FN 22271 EXTRA LP OPP | 2019-07-24 | SHAWNEETOWN DR | F | 22950.8722 | 16211.36 | -6739.5122 | -29% | 50 |  | 0 | CHECKED SLAM SHUT ON RUN 2 TO SEE IF IT HAD CLOSED, IT WAS NOT CLOSED SO POSSIBLE BAD ASV CABLE SMCHOLAN 10-20-2020 REGULATOR REPLACED BY WADE SHIMFESSEL 7/24/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS 2/12/2021 GCCC TICKET NOT REQUIRED ON 2/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS THIS IS PARELLEL SETING SO THERE IS ONLY 1 ER350 THAT WATCHES BOTH RUNS. IT WAS CREATED ON THE RUN 1 JOB . ALSO THERE IS NO GASKET STRAINERS BECAUSE OF EXISTING T-STRAINERS SO THE GASKETS WERE NOT REQUIRED.PER CYNITHIA FARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026814400 | 584 | EX | RET. FN 22271 FOR EXTRA LP OPP | 2019-07-24 | SHAWNEETOWN DR | F | 54.9718 | 628.28 | 573.3082 | 1,043% |  |  | 0 | REGULATOR REPLACED BY WADE SHIMFESSEL ON 7/24/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/16/2021 GCCC TICKET NOT REQUIRED ON 2/16/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS 2/16/21
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026840500 | 584 | EX | RET. FN 82 FOR EXTRA LP OPP | 2020-11-05 | 402 QUEENSWAY DR | F | 53.9767 | 0 | -53.9767 | 100% |  |  | 0 | REGULATORS REPLACED BY WADE SHIMFESSEL ON 11/5/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/23/2021 GCCC TICKET NOT REQUIRED ON 2/23/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026840600 | 584 | EX | RET. FN 13493 FOR EXTRA LP OPP | 2020-11-10 | 1805 OLD PARIS RD | F | 53.6219 | 1750 | 1696.3781 | 3,164% |  |  | 0 | REGULATORS REPLACED BY WADE SHIMFESSEL ON 11/10/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/17/2021 GCCC TICKET NOT REQUIRED ON 5/17/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026840700 | 584 | EX | RET. FN 22196 FOR EXTRA LP OPP | 2019-05-24 | 2228 YOUNG DR | F | 54.9718 | 247.38 | 192.4082 | 350% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 5/24/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/19/2021 GCCC TICKET NOT REQUIRED ON 2/19/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026841700 | 557 | EX | INSTALL 950' OF 2"PMMP MAIN | 2019-12-13 | 3319 TATES CREEK | B | 190505.477 | 174447.7 | -16057.777 | -8% | 951 | 858 | 203.319 | PORTABLE TOILET 4/28 THRU 5/17 - $78.35 TOP SOIL - 3 CY - $90.00 - #120169 - 6/3/20 TWALKER/KY 06-30-2020: JOB UNDER RUN DUE TO CKY PAID PROPERTY OWNER TO REPA IR PARKING LOT (THEY WERE IN THE PROCESS OF REPAVING THE FRONT SECTION OF THE SHOPPING CENTER). THIS LOWERED OUR PAVING COST/CONTRACTOR COST BY $30,000.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026841800 | 558 | EX | RETIRE 950' OF 4"BSLP MAIN | 2019-12-12 | 3319 TATES CREEK | B | 53.6219 | 648.04 | 594.4181 | 1,109% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026841900 | 2000 | EX | INVESTIGATE LAND RIGHTS | 2019-06-05 | 3319 TATES CREEK RD | B | 9405 | 0 | -9405 | 100% |  |  | 0
KY | KY - WEST | 2621 | U131982 |  |  |  | 18026842000 | 557 | EX | INSTALL 725' OF 2"PMMP MAIN | 2019-07-25 | 1034 E NEW CIRCLE RD | B | 154390.9956 | 92959.4 | -61431.5956 | -40% | 725 | 560 | 165.9989 | UNDERRUN EXPLANATION: THIS WAS ESTIMATED WITH UNITS BUT PERFORMED HOURLY WH ICH IN THIS CASE LOWERED THE COSTS. ALSO, PAVING OF THE STANDARD REQUIRED O F A HIGHWAY WAS ESTIMATED, BUT REPLACED IN A MANNER INDICATIVE OF A PARKING LOT. A LEVEL 2 BUDGET VARIANCE EXPLANTION IS NOT REQUIRED FOR AN UNDERRUN.
KY | KY - WEST | 2621 | U131982 |  |  |  | 18026842100 | 558 | EX | RETIRE 700' OF 4"BSLP MAIN | 2019-08-05 | 1034 E NEW CIRCLE RD | B | 61.0037 | 518.01 | 457.0063 | 749% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026842200 | 2000 | EX | INVESTIGATE LAND RIGHTS/ESM | 2019-02-05 | 1034 E NEW CIRCLE RD | A | 9815 | 0 | -9815 | 100% |  |  | 0
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026842500 | 561 | EX | INSTALL 1615'-12"/8" CSHP | 2019-10-21 | W NEW CIRCLE RD | B | 778679.7562 | 850897.48 | 72217.7238 | 9% | 2015 | 1578 | 539.2253
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 18026842600 | 562 | EX | RETIRE 2726'-12"/8"/6"/4"/2"HP | 2019-10-21 | W NEW CIRCLE RD | B | 2057.3296 | 180.3 | -1877.0296 | -91% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026842700 | 2000 | EX | INVESTIGATE AND MAP FACILITIES | 2020-04-02 | BOB-O-LINK |  | 2842 | 0 | -2842 | 100% |  |  | 0 | ISSUE RESOLVED THRU MAPPING. NO CAPITAL JO REQUIRED TO AVOID CONFLICT. D.LE MONS 4/3/2020
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026843200 | 2000 | EX | INVEST LAND RIGHT EXTRA LP-OPP | 2019-12-31 | 2001 MERCER RD | A | 20000 | 0 | -20000 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026843301 | 557 | EX | INSTALL 3000' OF 4/6/8"PMLP | 2022-09-07 | M L KING | B | 1495308.5734 | 1711065.31 | 215756.7366 | 14% | 2875 | 3068 | 557.7136
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026843400 | 558 | EX | RETIRE 2670' OF 3"/6"CILP MAIN | 2022-09-07 | M L KING | B | 81.035 | 598.25 | 517.215 | 638% |  |  | 0
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 18026843900 | 559 | EX | NSP INSTALL 800'-2" PMMP | 2020-07-08 | 1261 VILLAGE DR | B | 53353.5894 | 57609.11 | 4255.5206 | 8% | 800 | 599 | 96.1755
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026844100 | 2000 | EX | INVESTIGAT METERS & EASEMENTS | 2020-06-10 | 1261 VILLAGE DR |  | 15390 | 0 | -15390 | 100% |  |  | 0
KY | KY - WEST | 2621 | U124542 | Kipin,Coleen A | Campbell,Lynette | Scott,Chrisley | 18026846500 | 2000 | EX | PM LAND STATION MATERIALS | 2020-12-14 | 2001 MERCER RD |  | 70000 | 0 | -70000 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026846800 | 0001 | EX | LAND/MATERIAL O.P.P PROJECT | 2019-12-31 | 2001 MERCER RD | A | 60000 | 0 | -60000 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026847801 | 555 | EX | INSTALL 925' OF 2"/4"PMMP MAIN | 2019-06-25 | 961 CHINOE RD | B | 93860.0334 | 103960.01 | 10099.9766 | 11% | 925 | 966 | 107.6191
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026848000 | 2000 | EX | INVESTIGATE MAIN CONFLICTS | 2020-07-23 | OLD FRANKFORT RD |  | 6064.7131 | 0 | -6064.7131 | 100% |  |  | 0 | ALL INVESTIGATION COMPLETED AND JOBS RELEASED FOR CONSTRUCTION. D.LEMONS 7/ 23/2020
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026848300 | 555 | EX | INSTALL 100' OF 2"PMMP MAIN | 2019-10-16 | 4053 FORSYTHE DR | B | 15477.1344 | 13128.1 | -2349.0344 | -15% | 100 | 104 | 126.2317
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026848701 | 909 | EX | STATION UPGRADES (SEP RELATED) | 2022-12-15 | 4940 ATHENS BOONESBORO RD | F | 151848.4602 | 206545.63 | 54697.1698 | 36% |  |  | 0 | CCC 22581 CCC 23126 CCC 23442 CCC 24345 CCC 25855 CCC 26071
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026849600 | 2000 | EX | OBTAIN ROAD ROW LIMITS | 2019-02-05 | TAHOMA RD | B | 9915 | 0 | -9915 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026850600 | 555 | EX | INSTALL 375' OF 4"PMMP MAIN | 2019-04-01 | 1825 LITTLE HERB WY | B | 23051.3839 | 23683.26 | 631.8761 | 3% | 375 | 400 | 59.2082 | INSTALLED 400' OF 4" PLASTIC MAIN. TESTED AT 90PSIG FOR 1 HOURS. INSTALLED BY OC.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026850701 | 555 | EX | INSTALL 675' OF 2"PMMP MAIN | 2019-04-09 | 3121 CHERRY MEADOW PA | B | 105956.0473 | 83893.15 | -22062.8973 | -21% | 675 | 669 | 125.4008 | INSTALLED 669' OF 2" MAIN LINE PLASTIC PIPE. TESTED AT 90PSIG FOR 1 HOURS. INSTALLED BY DIRECTIONAL BORING. ALL PRE AND POST SEWER VIDEO WORK DONE.
KY | KY - WEST | 2621 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026852500 | 909 | EX | UPGRADE COMM EQUIPMENT | 2019-03-21 | 1511 RUSSELL CAVE RD | F | 8776.5399 | 6356.49 | -2420.0499 | -28% |  |  | 0 | SUPER SOLAR KIT AND RV 50 CELL MODEM INSTALLED BY ACP
KY | KY - WEST | 2621 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026854200 | 909 | EX | UPGRADE COMM EQUIPMENT | 2019-03-26 | PRESS AV | F | 8776.5399 | 5698.67 | -3077.8699 | -35% |  |  | 0 | SUPER SOLAR KIT AND RV 50 CELL MODEM INSTALL BY ACP
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026855000 | 2000 | EX | INVESTIGATE U/E AND RIGHTS | 2019-01-23 | 1435 N FORBES RD | B | 12207 | 0 | -12207 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026855500 | 584 | EX | RETIRE REG STATION #1034 | 2019-12-04 | 247 BURKE RD | F | 6105.9536 | 4169.62 | -1936.3336 | -32% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026856200 | 561 | EX | INSTALL 630'-2" PMMP | 2019-07-05 | HARRODSBURG RD | B | 44437.9939 | 71454.45 | 27016.4561 | 61% | 632 | 609 | 117.3308 | INSTALLED 622' OF 2" PLASTIC MAIN BY OC. TESTED AT 90PSIG FOR 1 HOUR
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026856300 | 562 | EX | RETIRE 400'-2" PMMP | 2019-07-05 | HARRODSBURG RD | B | 84.9756 | 0 | -84.9756 | 100% |  |  | 0 | RETIRED 430' OF 2" PLASTIC MAIN. DID NOT MEET COMMIT DATE DUE TO THE CUSTOMER NOT BEING READY ON TIME FOR GA S MAIN TO BE INSTALLED.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026857500 | 555 | EX | INSTALL 400' OF 2"PMMP MAIN | 2019-02-27 | 3545 ROBINHILL WY | B | 23797.3839 | 21900.72 | -1896.6639 | -8% | 400 | 363 | 60.3326
KY | KY - WEST | 2621 | U131982 |  |  |  | 19026858200 | 555 | EX | INSTALL 300' OF 2" PMMP MAIN | 2019-02-18 | 2828 JENNA REST RD | B | 16963.2095 | 20136.36 | 3173.1505 | 19% | 300 | 305 | 66.0209
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026858300 | 555 | EX | INSTALL 3100' OF 2"PMMP MAIN | 2019-04-09 | 760 HALFORD PL LT | B | 69931.5371 | 58970.19 | -10961.3471 | -16% | 3100 | 3445 | 17.1176
KY | KY - WEST | 2621 | U131982 |  |  |  | 19026858500 | 584 | EX | RETIRE REG STATION 1165 | 2019-08-05 | 1082 NEW CIRCLE RD NE | F | 3092.861 | 4474.52 | 1381.659 | 45% |  |  | 0
KY | KY - WEST | 2621 | U131982 |  |  |  | 19026859000 | 557 | EX | INSTALL 60'-4" PMLP | 2019-03-18 | BEAUMONT AV | A | 10460.1658 | 16141.38 | 5681.2142 | 54% | 60 | 68 | 237.3732
KY | KY - WEST | 2621 | U131982 |  |  |  | 19026859100 | 558 | EX | ABANDON 60'-4" BSLP | 2019-05-03 | BEAUMONT | A | 62.5459 | 9642.98 | 9580.4341 | 15,317% |  |  | 0 | ORDER CO BY LSTANFI REMOVED 58 FT OF BARE STEEL MAIN AND REPLACED WITH PLASTIC TESTED 90 LB FOR 1 HR
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026860100 | 587 | EX | INSTALL EFC | 2019-02-12 | 435 W HIGH ST RUPP AR | F | 7262.6656 | 5560.7 | -1701.9656 | -23% |  |  | 0 | REPLACED EFC COMMIT DATE ENTERED AS 12/31/18 BY MISTAKE COMMIT DATE ACUALLY SHOULD HAVE BEEN 12//31/19
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026860200 | 555 | EX | INSTALL 1025' OF 2"PMMP MAIN | 2019-03-20 | 3396 BAY SPRINGS PR LT | B | 44639.7355 | 35644.66 | -8995.0755 | -20% | 1025 | 1042 | 34.2079
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026860300 | 588 | EX | RETIRE EFC | 2019-02-12 | 435 W HIGH ST RUPP AR | F | 84.9756 | 0 | -84.9756 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026861500 | 562 | EX | ABANDON 333' OF 3"BSLP MAIN | 2019-02-15 | WHITE AV | A | 3171.371 | 2950.93 | -220.441 | -7% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026861600 | 561 | EX | INSTALL 97'-3" PMMP | 2019-03-29 | VINE ST | B | 45857.1641 | 59513.17 | 13656.0059 | 30% | 99 | 122 | 487.8129
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026861700 | 562 | EX | RETIRE 97'-3" PMP | 2019-03-29 | VINE ST | B | 84.9756 | 0 | -84.9756 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026863100 | 577 | EX | INSTALL NEW CHAIN LINK FENCE | 2019-02-18 | 1039 GOODWIN DR | F | 12912.8016 | 6867.37 | -6045.4316 | -47% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026863500 | 555 | EX | INSTALL 850' OF 2"PMMP MAIN | 2019-05-15 | 2947 EMINENT DR | B | 33977.8678 | 31192.57 | -2785.2978 | -8% | 850 | 845 | 36.9143
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026863800 | 584 | EX | RETIRE VAULT REG #1107 | 2019-12-19 | 303 CHINOE RD | F | 5202.8047 | 2436.33 | -2766.4747 | -53% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026864000 | 555 | EX | INSTALL 200' OF 2"PMMP MAIN | 2019-04-29 | 2017 SHAKER RUN RD | B | 13477.9207 | 19517.08 | 6039.1593 | 45% | 200 | 233 | 83.7643
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026864100 | 555 | EX | INSTALL 485' OF 2"PMMP MAIN | 2019-04-18 | 1981 TWAIN RIDGE DR | B | 22646.8678 | 26868.66 | 4221.7922 | 19% | 485 | 599 | 44.8559
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026864500 | 562 | EX | RETIRE 497'-4" CSLP | 2019-09-10 | SOUTHLAND DRIVE | B | 77.825 | 611 | 533.175 | 685% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026864600 | 555 | EX | INSTALL 435' OF 2"PMMP MAIN | 2019-05-14 | 3257 LOCH NESS DR | B | 20756.3589 | 37399.62 | 16643.2611 | 80% | 435 | 480 | 77.9159
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026864700 | 557 | EX | INSTALL 10' OF 4"PMLP MAIN | 2019-03-07 | 1836 CLAYS MILL | A | 12412.0783 | 7990.59 | -4421.4883 | -36% | 10 | 6 | 1331.765 | TWALKER/KY 05-02-19: PER GS 1500.010 7.2.4, THIS PROJECT WAS AN EMERGENCY LEAK REPAIR ON LP MAIN/SERVICE LINE (MAOP 14"WC) THE 4" PLASTIC PIPE WAS PRE-TESTED ON JOB 18-6316798-00 TESTED LESS THAN 1 HOUR. I REVIEWED TEST AND PROJECT WILL GARY SULLIVAN, I HEREBY APPROVE TEST AND TIME.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026864800 | 558 | EX | ABANDON 10' OF 4"BSLP MAIN | 2019-03-07 | 1836 CLAYS MILL | A | 73.0037 | 8380.2 | 8307.1963 | 11,379% |  |  | 0 | MEASUREMENT TAKEN FROM LAFAYETTE CHRISTAN CHURCH SIGN BARED BANKS -NRF- INT/EXT CORR INSPT COMPLETED 3-7-19 JENS JOB COMPLETED 3-7-19 INSTALLED 6' OF PRETESTED 040 PL MAIN. (18631679800). SOAP TESTED CONN POINTS @ OP INSTALLED 5 CLAMPS OVER DRILL HOLES SOAPED @ OP. INSTALLED 2 ANODES AND WRAPPED MAIN. MB INSTALLED OVER CPLG'S
KY | KY - WEST | 2621 | U131983 |  |  |  | 19026865000 | 559 | EX | INSTALL 253'-4" PMMP | 2020-01-08 | HARVARD DR | B | 35049.1103 | 53177.8 | 18128.6897 | 52% | 255 | 286 | 185.9364
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 19026865100 | 575 | EX | ACQUIRE ESMT OVER CARMAN PROPY | 2019-05-31 | 1505 COLESBURY CR | F | 170919 | 130139.09 | -40779.91 | -24% |  |  | 0 | EASEMENT ACQUIRED BY AUTUMN DYMTREWYCZ MAY, 2019 (BKSLONE) UNDERRUN EXPLANATION: WE WERE ABLE TO GET THE EASEMENT FOR LESS THAN WE ORI GINALLY ESTIMATED. IN ADDITON, OVERHEADS WERE NOT APPLIED TO THIS EXPENSE.
KY | KY - WEST | 2621 | U131983 |  |  |  | 19026865400 | 557 | EX | INSTALL 4'-3" PMMP | 2019-03-21 | COMANCHE TL | A | 10175.6826 | 5670.75 | -4504.9326 | -44% | 5 | 4 | 1417.6875 | INSTALLED 48.5'' OF 3'' PMP MAIN WITH CRITICAL VALVE. PRE TESTED PIPE FOR 1HR AT 90LBS TEST OK. INSTALLED WITH 2 EFC SOAP TEST FINAL TIE INS NGF. BARHOLE BANKS NGF. DPI IS CLEARED ON JO-19026865500 -- REFERENCE JO-19026865500 FOR THIS JOB AND JOB NUMBER FOR MATERIALS, PRESSURE TEST DATA, AND FACILITY FAILURE. KKINDER 03/21/19 1600
KY | KY - WEST | 2621 | U131983 |  |  |  | 19026865500 | 558 | EX | RETIRE 4'-3" PMMP | 2019-03-21 | COMANCHE TL | A | 74.7467 | 3224.08 | 3149.3333 | 4,213% |  |  | 0 | CRITICAL VALVE LEAKING.SQUEEZED OFF MAIN WITH 2 WAY FEED. FOLLOWED TIE IN PLAN AND INSTALLED NEW CV C32-232. INSTALLED 48.5'' OF MAIN LINE WITH CRICTICAL VALVE. TESTED FOR 1HR AT 90LBS. TEST OK SOAP TEST TIE INS NGF.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026865600 | 584 | EX | RETIRE LP REGULATOR STATION | 2020-06-04 | 3319 TATES-CREEK RD | F | 3511.4647 | 10386.32 | 6874.8553 | 196% |  |  | 0 | PROJECT ON HOLD FOR WINTER MONTHS DUE TO SWITCHING CUSTOMERS TO MP MAIN
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026866000 | 588 | EX | RETIRE GMB SETTING | 2020-09-30 | 1247 VERSAILLES RD | F | 1064.6002 | 1701.45 | 636.8498 | 60% |  |  | 0 | GMB TO CAB CONVERSTION COMPLETED
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026866100 | 555 | EX | INSTALL 450' OF 2"PMMP | 2019-11-22 | 2159 PAUL JONES WY LTOUTLT | B | 35637.9457 | 57080.5 | 21442.5543 | 60% | 450 | 583 | 97.9082
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026867300 | 557 | EX | INSTALL 40' OF 3"PMLP MAIN | 2019-03-21 | 496 PRICE RD | A | 24214.6883 | 27361.96 | 3147.2717 | 13% | 40 | 33 | 829.1503 | INSTALLED 33' OF NEW 030 PL MAIN TESTED ON SITE FOR 61 MINS REFUR TO DPI D094589
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026867400 | 558 | EX | RETIRE 40' OF 3"BSLP MAIN | 2019-03-21 | 496 PRICE RD | A | 69.9718 | 6132.21 | 6062.2382 | 8,664% |  |  | 0 | REPL 33' OF BS MAIN DUE TO EXT CORR PITTING. INSTALLED 33' OF 030 PL MAIN TESTED ON SITE FOR 61 MINS. SOAP TESTED CONN POINTS @ OP INSTALLED 6 CLAMP 2 ANODES MB INSTALLED OVER CPLG. WRAPPED ML BARED BANKS NRF 3-21-19
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026867500 | 566 | EX | RETIRE 3" SERVICE | 2019-07-19 | 353 SOUTHLAND DR | B | 77.825 | 0 | -77.825 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026868100 | 2000 | EX | INVESTIGATE EASEMENT OPTIONS | 2019-12-06 | 3765 WAVELAND MUSEUM LN |  | 5288 | 0 | -5288 | 100% |  |  | 0
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 19026868400 | 561 | EX | INSTALL 70'-2" CSHP TO R-1222 | 2019-07-09 | 968 NANDINO BV REAR | B | 21448.1103 | 43675.52 | 22227.4097 | 104% | 70 | 75 | 582.3403
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026869800 | 909 | EX | UPGRADE COMM EQUIPMENT | 2019-04-09 | PRESS AV | F | 6811.6795 | 2549.5 | -4262.1795 | -63% |  |  | 0 | CELL MODEM UPGRADED TO RV50 BY ACP
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026869900 | 555 | EX | INSTALL 225' OF 2"PMMP MAIN | 2019-05-24 | 194 WOODWIND CT | B | 14833.8493 | 12861.74 | -1972.1093 | -13% | 225 | 177 | 72.6652
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026870000 | 557 | EX | INSTALL 60' OF 3"BSLP MAIN | 2019-04-18 | 739 COOPER DR | A | 24476.1553 | 2756.75 | -21719.4053 | -89% | 60 | 61 | 45.1926 | INSTALLED 45' OF 030 AND 4' OF 040 PL ML TO REPL LEAKING 030 BS ML NEW ML TESTED @ 90 # FOR 1 HR THEN PIGGED INSTALLED 2 ANODES AND TRACER WIRE MB @ ALL POINTS NEEED
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026870100 | 558 | EX | RETIRE 60' OF 3"BSLP MAIN | 2019-04-18 | 739 COOPER DR | A | 68.4012 | 9332.65 | 9264.2488 | 13,544% |  |  | 0 | RETIRED 45' OF BS ML DUETO EXT CORR PITTING. INSTALLED 45' OF NEW 030 PL ML TESTED @ 90 # FOR 1 HR THEN PIGGED. BOLTED CPLG SOAP TESTED @ OP. INSTALLED 2 ANODES CV BOXES W/ WIRE AND MB @POINTS INT/EXT 4-18-19 JENS OK
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026870200 | 555 | EX | INSTALL 100' OF 2"PMMP MAIN | 2019-09-16 | 3349 MATHERN TL | B | 10252.9622 | 16886.43 | 6633.4678 | 65% | 100 | 67 | 252.0363
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026870300 | 555 | EX | INSTALL 35' OF 2"PMMP MAIN | 2019-04-17 | 633 LUCILLE DR LT | B | 4141.4247 | 4138.06 | -3.3647 | 0% | 35 | 35 | 118.2303
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026870400 | 555 | EX | INSTALL 60' OF 2"PMMP MAIN | 2019-05-17 | 2828 SATIN LEAF PK | B | 7261.6795 | 7392.67 | 130.9905 | 2% | 60 | 65 | 113.7334
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026870500 | 2000 | EX | CONFLICT ASSESSMENT FOR RELO | 2019-12-03 | 3801 HARRODSBURG RD | B | 14820 | 0 | -14820 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026870600 | 2000 | EX | ASSESS CONFLICT FOR RELOCATION | 2019-11-26 | 2751 LEESTOWN RD | A | 14820 | 0 | -14820 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026870700 | 561 | EX | INSTALL 1500' OF 6"PMMP MAIN | 2020-04-22 | 2751 LEESTOWN RD | B | 242580.6463 | 234941.1 | -7639.5463 | -3% | 1500 | 1501 | 156.5231
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026870800 | 562 | EX | RETIRE 500' OF 6"PMMP MAIN | 2020-04-24 | 2751 LEESTOWN RD | B | 131.4777 | 154.21 | 22.7323 | 17% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026870901 | 561 | EX | INSTALL 15'-2" PMMP | 2019-05-28 | GOODRICH AV | B | 25434.5407 | 20986.01 | -4448.5307 | -17% | 19 | 15 | 1399.0673
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026871000 | 562 | EX | RETIRE 5'-2" PMP | 2019-05-28 | 98 GOODRICH AV | A | 71.5425 | 1225.03 | 1153.4875 | 1,612% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026872800 | 558 | EX | RETIRE 292' OF 4"BSLP MAIN | 2019-12-13 | CHELAN DR | B | 8043.6795 | 27119.92 | 19076.2405 | 237% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026873400 | 559 | EX | INSTALL 2'-2" PMMP | 2019-05-20 | RICHMOND RD | A | 4522.9032 | 183.62 | -4339.2832 | -96% | 12 | 2 | 91.81 | INSTALLED 4 FT PEICE OF 2 IN MAIN TEST 90 LB FOR 20 MIN TEST BYPASS FOR 1 HR SOAP TEST FINAL TIE IN AT OP FOR 5 MIN BAR HOLE BANKS NO READINGS FOUND
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026873500 | 560 | EX | RETIRE 2'-2" PMMP | 2019-05-20 | RICHMOND RD | A | 77.825 | 3056.18 | 2978.355 | 3,827% |  |  | 0 | CUT OUT DAMAGE MAIN REPLACED WITH NEW PEICE OF MAIN THAT WAS TESTED AT 90 LB FOR 20 MIN ON SITE
KY | KY - WEST | 2621 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026874100 | 555 | EX | INSTALL 2800' OF 2"/4"PMMP | 2020-02-17 | 2311< ARMSTRONG MILL RD | B | 93000.1288 | 106780.18 | 13780.0512 | 15% | 2800 | 2565 | 41.6297
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026874401 | 557 | EX | INSTALL 2520' OF 2"PMMP MAIN | 2019-11-02 | EDGEMOOR DR | B | 460145.7795 | 481322.8 | 21177.0205 | 5% | 4500 | 2519 | 191.0769
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026874500 | 558 | EX | RETIRE 2200' OF 4"BSLP MAIN | 2019-12-12 | EDGEMOOR DR | B | 136.2899 | 1748.56 | 1612.2701 | 1,183% |  |  | 0
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 19026874600 | 562 | EX | RETIRE 2577'-12" BS/CSHP | 2020-02-20 | W NEW CIRCLE RD | B | 74.1455 | 214.05 | 139.9045 | 189% |  |  | 0
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 19026874900 | 557 | EX | INSTALL 4500' OF 2"PMMP MAIN | 2020-11-02 | BUCOTO CT | B | 756708.0009 | 562974.17 | -193733.8309 | -26% | 4500 | 3088 | 182.3103 | UNDERRUN EXPLANATION: THERE WAS A $65,000 CONTINGENCY FEE DUE TO THE UNKNOW NS IN THIS PROJECT THAT WAS NOT UTILIZED. THAT IN ADDITION TO THE OVERHEAD EFFECT WAS THE REASON FOR THE UNDERRUN.
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 19026875000 | 558 | EX | RETIRE 5000' OF 4"/8"BSLP MAIN | 2020-11-02 | BUCOTO CT | B | 276.9856 | 71.35 | -205.6356 | -74% |  |  | 0
KY | KY - WEST | 2621 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026875100 | 557 | EX | INSTALL 550' OF 2"PMMP MAIN | 2019-11-15 | 1018 RICHMOND | B | 91886.5131 | 158275.17 | 66388.6569 | 72% | 550 | 540 | 293.1022 | INSTALLED 540' OF 2" PE MAIN ALONG RICHMOND RD BETWEEN DESHA RD AND IRVINE RD. TESTED MAIN @ 95 PSIG FOR 1 HOUR.SOAP TESTED TIE INS AND DEAD END CAPS AT OPERATING PRESSURE FOR 5 MINS.
KY | KY - WEST | 2621 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026875200 | 558 | EX | RETIRE 280' OF 4"BSLP MAIN | 2019-12-02 | 1018 RICHMOND | B | 53.9767 | 7689.8 | 7635.8233 | 14,147% |  |  | 0 | RETIRED BARE STEEL MAIN ALONG RICHMOND ROAD BETWEEN DESHA RD AND IRVINE ROA D. SOAP TESTED DEAD END CAPS AND BAG OFF HOLE PLUGS AT OPERATING PRESSURE FOR 5 MINS. SOAP TEST IS GOOD.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026875500 | 559 | EX | INSTALL 14' OF 4"PMMP MAIN | 2019-05-13 | 610 CARDINAL LN | A | 6535.4567 | 16610.89 | 10075.4333 | 154% | 14 | 16 | 1038.1806
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026875600 | 560 | EX | RETIRE 10' OF 4"PMMP MAIN | 2019-05-13 | 610 CARDINAL LN | A | 65.1369 | 171.82 | 106.6831 | 164% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026876100 | 555 | EX | INSTALL 2760' OF 2"/4"PMMP | 2020-02-13 | 4235 HARRODSBURG RD | B | 70211.5565 | 68619.9 | -1591.6565 | -2% | 2760 | 1856 | 36.9719 | TWALKER/KY 2-13-20: SEE JOB ORDER CHANGE REQUEST IN WMS.DOCS, ONE OF THE PL ANNED STREETS FOR THIS DEVELOPMENT NOT INSTALLED AND PROJECT FOOTAGE IS 800' LESS THAN PLANNED. WMS WOULD NOT ALLOW REVISION DUE TO UNPAID INVOICES FOR MATERIAL
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026876200 | 2000 | EX | INVESTIGATE CONFLICTS | 2023-11-10 | WILSON DOWNING RD |  | 20833 | 0 | -20833 | 100% |  |  | 0 | INVESTIGATION, CONFLICT ASSESMNET AND DESIGN COMPLETED. WAITING ON LFUCG F OR CONSTRUCTION DATES. PROJECT WAS STARTED IN 2019 AND THEN PLACED ON HOLD BY LFUCG. D.LEMONS 11/10/2023
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026877500 | 555 | EX | INSTALL 50' OF 2"PMMP MAIN | 2019-06-20 | 600 LAKESHORE DR | B | 17465.4636 | 10196 | -7269.4636 | -42% | 50 | 60 | 169.9333
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 19026877600 | 562 | EX | RETIRE 92'-4" PMP | 2019-05-17 | 283 E HIGH ST | A | 15436.72 | 5993.06 | -9443.66 | -61% |  |  | 0 | 5-17-19. JENS INSTALLED ANODE AND TRACER WIRE WITH GREEN LID TO MAKE 040 PL ML LOCATABLE JENS NEW MAIN WITH REDUCER AND PURGE CAP TESTED FOR 1 HR ON SITE. 4X1 TEE TESTED 5 MINS. THE SOAP TESTED CAP AND SF END CAP WHEN DONE @ OP. PURGE CAP TESTED WHEN DONE RE MOVED OLD OUT OF THE WAY FOR KU INT/ EXT CORR INSPT COMPLETED
KY | KY - WEST | 2621 | U131983 |  |  |  | 19026878200 | 557 | EX | INSTALL 55' OF 3"PMLP MAIN | 2019-08-12 | 364 MOCKINGBIRD LN | A | 22186.5674 | 4487.67 | -17698.8974 | -80% | 55 | 56 | 80.137 | ABN 56' OF 040 SL MAIN. INSTALLED NEW 030 PL MAIN ON 8-7-19
KY | KY - WEST | 2621 | U131983 |  |  |  | 19026878300 | 558 | EX | RETIRE 40' OF 4"BSLP MAIN | 2019-08-12 | 364 MOCKINGBIRD LN | A | 69.5189 | 25405.15 | 25335.6311 | 36,444% |  |  | 0 | ANODES AND 3 MARKER BALLS OVER CPLS. INSTALLED NEW 030 TO REPL LEAKING. MAIN INSTALLED PER GS
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026878400 | 575 | EX | ACQUIRE NEW LAND RIGHTS | 2022-03-22 | 1800 MASON-HEADLEY RD | F | 10994 | 5313.62 | -5680.38 | -52% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026878600 | 555 | EX | INSTALL 320' OF 4"PMLP MAIN | 2019-08-07 | 951 NATIONAL AV NEW | B | 41650.159 | 36710.05 | -4940.109 | -12% | 325 | 317 | 115.8046
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026878800 | 583 | EX | INSTALL REGULATION | 2019-04-05 | 8721 DURBIN LN | F | 1744.2587 | 0 | -1744.2587 | 100% |  |  | 0 | WORK DONE ON 2612 JOB ORDER 19-6826920-00 TO CORRECT AUDIT FINDING CAPITAL JOB OBTAINED AFTER WORK COMPLETED
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026878900 | 584 | EX | RETIRE REGULATOR | 2019-04-05 | 8721 DURBIN LN | F | 74.2822 | 264.25 | 189.9678 | 256% |  |  | 0
KY | KY - WEST | 2621 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026879500 | 555 | EX | INSTALL 900' OF 2"PMMP MAIN | 2019-07-02 | 1721 HAYMAKER AL LT90 | B | 20687.159 | 20625.19 | -61.969 | 0% | 1000 | 895 | 23.0449
KY | KY - WEST | 2621 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026879900 | 557 | EX | INSTALL 40' OF 4"PMLP MAIN | 2019-06-13 | 1731 RICHMOND RD | A | 19353.5151 | 14489.69 | -4863.8251 | -25% | 40 | 32 | 452.8028
KY | KY - WEST | 2621 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026880000 | 558 | EX | RETIRE 40' OF 4"BSLP MAIN | 2019-06-13 | 1731 RICHMOND RD | A | 74.2822 | 2391.44 | 2317.1578 | 3,119% |  |  | 0 | RETIRED 32 FT OF MAIN AND REPLACED WITH PLASTIC MAIN TESTED90 LB FOR 1 HR
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026880100 | 557 | EX | INSTALL 11'-3" PMLP | 2019-06-14 | PERRY | B | 7810.5277 | 14762.46 | 6951.9323 | 89% | 31 | 11 | 1342.0418
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026880200 | 558 | EX | RETIRE 11'-3" PLP | 2019-06-14 | PERRY | B | 58.2181 | 332.94 | 274.7219 | 472% |  |  | 0 | ABDN MAIN AND TO INSTALL NW PEICE OF MAIN
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026880300 | 560 | EX | RETIRE 128' OF 3"BSLP MAIN | 2019-08-07 | 951 NATIONAL AV | B | 68.154 | 0 | -68.154 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026880400 | 575 | EX | LAND FACILITY FOR REG STATION | 2019-06-14 | 220 CLAY AV | F | 72.0899 | 1200 | 1127.9101 | 1,565% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026880501 | 557 | EX | INSTALL 590' OF 4"/8"PMLP MAIN | 2019-10-08 | 220 CLAY AV | B | 89456.2428 | 75795.04 | -13661.2028 | -15% | 610 | 557 | 136.0773 | JOB COMPLETED TO COMPAMY STANDARDS.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026880600 | 558 | EX | RETIRE 3908' OF 4"CI/BSLP MN | 2019-10-08 | 220 CLAY AV | B | 66.4345 | 9951.92 | 9885.4855 | 14,880% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026880700 | 583 | EX | INSTALL DUAL RUN REG STATION | 2019-11-05 | 220 CLAY AV | F | 48448.5827 | 30450.41 | -17998.1727 | -37% |  |  | 0 | WAITING ON MATERIAL FOR ERX AND PRV IN ORDER TO COMPLETE ALL COMPONENT INSTALLS ALSO WAITING ON CONSTRUCTION TO COMPLETE MAIN LINE JOBS AND SERVICE TIE-OVERS DELAYED DUE TO COVID 19
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026880800 | 584 | EX | RETIRE SINGLE RUN LP STATION | 2019-08-20 | 220 CLAY AV | F | 153.7751 | 236.36 | 82.5849 | 54% |  |  | 0 | STATION WAS RETIRED WITH LP MONITORING JOB PAPERWORK DID NOT GET TURNED IN TO ME TO BE EXECUTED PAPERWORK COMPLETED BY CFARIS 3/27/20
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026882300 | 557 | EX | INSTALL 130' OF 3"PMLP MAIN | 2020-02-28 | 617 KASTLE RD | A | 45765.5621 | 41762.72 | -4002.8421 | -9% | 90 | 128 | 326.2713 | INSTALLED 128' OF NEW 030 PL ML TESTED @ 90 # FOR 1 HR ONSITE. INSTALLED 4 ANODES ON BS ML. INSTALLED 5 MB AND TW STATION TO LOCATE NEW PLML INT/EXT CORR INSPT COMPLETED 2-28-20 JENS/RLA
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026882400 | 558 | EX | RETIRE 130' OF 3"/4"BSLP MAIN | 2020-02-28 | 617 KASTLE RD | A | 71.2512 | 8281.37 | 8210.1188 | 11,523% |  |  | 0 | INSTALLED 128' OF PL 030 TESTED FOR 1 HR ON SITE. INSTALLED 4 ANODES 5 MB &TW STATION TO LOCATE NEW PLML. INT/EXT CORR INSPT COMPLETED 2-28-20 JENS/RLA
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026882701 | 555 | EX | INSTALL 90' OF 2"PMMP MAIN | 2019-09-10 | 3360 LAWSON LN | B | 22347.5159 | 19457.63 | -2889.8859 | -13% | 90 | 81 | 240.2177
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026883600 | 587 | EX | INSTALL GMB STATION | 2020-06-04 | 435 W HIGH ST RUPP AR | F | 104215.9406 | 82488.69 | -21727.2506 | -21% |  |  | 0 | COMPLETION DELAYED WAITING ON RUPP ARENA
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026883700 | 588 | EX | RETIRE GMB SETTING | 2020-06-04 | 435 W HIGH ST RUPP AR | F | 81.1779 | 0 | -81.1779 | 100% |  |  | 0 | JOB ON HOLD WAITING ON RUPP ARENA
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026883800 | 566 | EX | NEEDS REVIEWED - RETIRE | 2020-06-16 | 435 W HIGH ST RUPP AR | B | 81.1135 | 4820.18 | 4739.0665 | 5,843% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026883900 | 565 | EX | INSTALL 150'-6" PMMP S/L | 2020-05-28 | 435 W HIGH ST RUPP AR | B | 47400.4851 | 42874.89 | -4525.5951 | -10% | 145 |  | 0 | THE OLD SERVICE LINE WAS CONVERTED TO MAIN LINE. THIS WAS TO INSTALL THE NE W SERVICE LINE.
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026884400 | 2000 | EX | INVESTIGATE CONFLICT | 2019-09-20 | FOREST PARK RD |  | 10171 | 0 | -10171 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026884501 | 561 | EX | INSTALL 70'-2" PMMP | 2020-03-06 | FOREST PARK RD | B | 62432.7017 | 130100.01 | 67667.3083 | 108% | 70 | 109 | 1193.5781 | ON EXTRA SECTION OF MAIN WAS FOUND THAT NEEDED TO BE RE-ROUTED WHICH ADDED TIME TO THE JOB. SCOPE CHANGE COMPLETED TO REFLECT SUBMITTED LEVEL 2 EXPLANATION AND LOADED INTO WMSDOCS. D.LEMONS 9/21/2020
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026884600 | 562 | EX | RETIRE 40'-2" PMMP | 2020-03-06 | FOREST PARK RD | B | 74.8323 | 0 | -74.8323 | 100% |  |  | 0 | EXTRA SECTION ADDED ON TO JOB TO RELOCATE MORE MAIN. SCOPE CHANGE COMPLETED
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026885100 | 557 | EX | INSTALL 16' OF 2"PMMP MAIN | 2019-07-29 | 588 CROMWELL WY | A | 23899.0834 | 16190.44 | -7708.6434 | -32% | 16 | 18 | 899.4689 | INSTALLED 16' OF NEW 020 PL MAIN TO REPL LEAKING COMP CPLG
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026885200 | 558 | EX | RETIRE 4' OF 2"PAMP MAIN | 2019-07-29 | 588 CROMWELL WY | A | 66.4345 | 9432.4 | 9365.9655 | 14,098% |  |  | 0 | WRAPPED MAIN. EXPOSED 020 MECH CPLG. LEAKING. INSTALLED 16' OF 020 AND REMOVED REOMOVED 2 020 MECH CPLG. TEDTED NEW MAIN FOR 1 HR ONSITE. TESTED ALL TEES @ 90 # FOR 5 MINS. SOAP TESTED WELDS @ OP. INSTALLED MB OVER LVT INSTALLED ANODE
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026885800 | 555 | EX | INSTALL 550' OF 2"PMMP MAIN | 2019-09-25 | 1720 FITZGERALD CT | B | 29896.7566 | 25765.69 | -4131.0666 | -14% | 550 | 573 | 44.9663
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026887301 | 555 | EX | INSTALL 925' OF 2"PMMP MAIN | 2020-02-20 | 1803 GEORGETOWN RD | B | 59176.4383 | 62516.06 | 3339.6217 | 6% | 925 | 887 | 70.4803
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 19026887500 | 557 | EX | INSTALL 20'-4" PMLP | 2019-07-26 | 155 OLD PARK AV | A | 14674.4724 | 8274.61 | -6399.8624 | -44% | 20 |  | 0
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 19026887600 | 558 | EX | RETIRE 20'-4"/3" CS/CILP | 2019-07-26 | 155 OLD PARK AV | A | 67.9767 | 21826.45 | 21758.4733 | 32,009% |  |  | 0 | COMPLETED 7-26-19 JENS MB INSTALLED ON CPLG AND 90'S TW INSTALLED IN CV BOXES OVER CPLG. ABN 3' OF 3" LP MAIN. SOAP TESTED CONN PTS @ 11" WC. REPL 18' 8" OF BS LP. W/ PL. TESTED PL ML FOR 1 HR TESTED 1" BY PASS FOR 1 HR. SOAP TEST ALL FITTINGS AND CONN @ 11" WC. INSTALLED 2 ANODES AND MB INT/EXT CORR
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026888000 | 561 | EX | INSTALL 40'-2" PMMP | 2019-09-25 | GREENTREE RD | B | 31034.6635 | 44534.95 | 13500.2865 | 44% | 40 | 142 | 313.6264
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026888100 | 562 | EX | RETIRE 40'-2" CSMP | 2019-09-25 | GREENTREE RD | B | 75.6877 | 18146.34 | 18070.6523 | 23,875% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026888200 | 2000 | EX | INVESTIGATE MAIN | 2019-08-01 | GREENTREE RD | A | 2219.9952 | 0 | -2219.9952 | 100% |  |  | 0 | VERIFIED MAIN LOCATION FOR DAVID LEMONS BY HYDRO VAC EQUIPMENT. WHIMES 7/30/19 EXPOSED MAIN PER DAVID LEMONS FOR A SURVEY FOR FUTURE WORK. WHIMES 08/01/19
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026889001 | 561 | EX | INSTALL 28'-8" PMLP | 2021-04-19 | DUNTREATH | B | 17790.2899 | 30769.7 | 12979.4101 | 73% | 28 | 35 | 879.1343
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026889100 | 562 | EX | RETIRE 28'-8" PMLP | 2019-09-12 | DUNTREATH | A | 5373.9457 | 1419.08 | -3954.8657 | -74% |  |  | 0 | -ANICHOLS 9-13-19 ABANDON 26FT OF 8" MAIN-WORKED TO TIE PLAN-SOAP TESTED ALL PAC CLAMPS AND DEADENDS CAPS @ OP-TEST OK-MONITORED GAUGES THROUGHOUT PROCESS AND 30MINS AFTER BAGS WERE REMOVED NO LOSE IN PRESSURE-CONTENT VERIFIED 11IWC-
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 19026889300 | 561 | EX | INSTALL 6" SS | 2019-09-05 | 924 GEORGETOWN ST | B | 15110.228 | 13497.3 | -1612.928 | -11% |  |  | 0
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 19026889400 | 562 | EX | RETIRE 1060'-6"/4" BSHP + GV | 2019-09-05 | 924 GEORGETOWN ST | B | 299.1242 | 0 | -299.1242 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026889500 | 557 | EX | INSTALL 410' OF 4"PMLP MAIN | 2020-04-20 | 161 N MILL ST | B | 184461.6222 | 191568.67 | 7107.0478 | 4% | 410 | 421 | 455.0325 | MISC DOLLARS AND CENTS PAID FOR PARKING METERS ON JOB PARTIAL LINE GASSED UP, FROM N MILL TO W SHORT ST INCLUDING CHURCHST
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026889600 | 558 | EX | RETIRE 625' OF 4"CI/BS LP MAIN | 2020-06-17 | 161 N MILL ST | B | 150.1203 | 60.49 | -89.6303 | -60% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026890500 | 558 | EX | RETIRE 40' OF 3"BSLP MAIN | 2019-12-23 | SOUTHPORT DR | A | 7745.9583 | 10945.84 | 3199.8817 | 41% |  |  | 0 | ABDN 51 FT OF 3 IN MAIN INSTALLED 2 END CAPS SOOAP TEST AT OP FOR 5 MIN SOAP TEST ALL PAC CLAMPS AT OP FOR 5 MIN BAR HOLE BANKS NO GAS FOUND INSTALLED 2 ANODES
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026890600 | 561 | EX | INSTALL 1440'-6" PMMP | 2020-03-04 | MT TABOR | B | 257137.6403 | 312393.01 | 55255.3697 | 21% | 1515 | 1522 | 205.2516 | DNLEMONS/KY 8/15/2020: JOB OVERRUN DUE TO ADDITIANAL CONTRACT COST AND LABO R HOURS. CONTRACT COST OVER BY $34,000 DUE TO ADDITIONAL VACUMEN EXCAVATION AND CONTRACT ENGINEERING AND LS TIME FOR FIELD ADJUSTMENTS. LABOR OVERRAN 150 HOURS FOR ADDITIONAL $15,000 IN COSTS.
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026890800 | 562 | EX | RETIRE 1669'-6"CS&PMP | 2020-03-04 | MT TABOR | B | 75.6877 | 274.58 | 198.8923 | 263% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026891200 | 557 | EX | INSTALL 20'OF 8"PMLP MAIN | 2019-10-01 | 232 E 5TH ST | B | 48701.1043 | 114420.23 | 65719.1257 | 135% | 20 | 34 | 3365.3009 | TWALKER/KY 03-04-20: LEVEL 2 VARIANCE REPORT IN WMS.DOCS FOR COST OVER RUN I COULD NOT REVISE JOB DUE TO UNPAID INVOICE FOR MATERIAL. THIS PROJECT TOOK AN EXTRA WEEK TO COMPLETED WHICH INCREASED COMPANY LABOR BY $4,000. ALSO, THIS PROJECT REQUIRED ADDITIONAL FLAGGERS DUE TO TRAFFIC/LANE CLOSURE PERMITS REQUIREMETNS AND STREET/HARD SURFACE REPAIR WHICH INCREASE CONTRACT COST BY $48,000. FINALLY, CHANGE IN TIE IN PROCESS ADDED $5,000 MATERIAL COST AND SEGA INCREASED BY $6,000
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026891300 | 558 | EX | RETIRE 12' OF 12"BSLP MAIN | 2019-10-01 | 232 E 5TH ST | B | 150.1203 | 6799.69 | 6649.5697 | 4,429% |  |  | 0
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026891500 | 557 | EX | INSTALL 1' - 2" PMMP | 2019-08-23 | GOODRICH | A | 6675.3807 | 6549.04 | -126.3407 | -2% | 0 | 5 | 1309.808
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026891600 | 558 | EX | RETIRE 1' - 2" PMMP | 2019-08-23 | GOODRICH | A | 72.9057 | 0 | -72.9057 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026892400 | 558 | EX | ABANDON 2' OF 4"BSLP MAIN | 2019-08-28 | BARBERRY LN | A | 4942.5468 | 5434.76 | 492.2132 | 10% |  |  | 0 | RETIRED 3 FT OF 4 IN BARE STEEL MAIN SOAP TEST DEAD END CAP AT OP FOR 5 MIN INSTALLED 1 ANOD PUT LINE MARKER AND MARKER BALL AT THE END OF MAIN BAR HOLE BANKS NO READINGS FOUND
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026893001 | 557 | EX | INSTALL 75' - 4" CSHP | 2020-05-14 | 421 PRICE RD | B | 102933.7365 | 122656.71 | 19722.9735 | 19% | 80 | 43 | 2852.4816
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026893100 | 558 | EX | RETIRE 25' - BSHP | 2020-05-14 | 421 PRICE RD | B | 236.0315 | 1355.96 | 1119.9285 | 474% |  |  | 0
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026893200 | 557 | EX | INSTALL 40' - 4" PMMP | 2020-01-09 | 2001 FORT HARRODS DR | A | 32848.7614 | 7215.29 | -25633.4714 | -78% | 40 | 30 | 240.5097 | INSTALLED 15' OF 4" AND 16' OF 2" TO FIX LEAK ON MAIN. ALL MAIN WAS GPS'ED DUE TO NO WIRE TO TIE ON TO. SWING TIES TAKEN TO ALL FITTINGS FROM 2001 FORT HARROD AND THE LIGHT POLE
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026893300 | 558 | EX | RETIRE 20' - 2" PMMP | 2020-01-09 | 2001 FORT HARRODS DR | A | 1524.4761 | 29519.26 | 27994.7839 | 1,836% |  |  | 0 | REPL MAIN DUE TO LEAKING MECH CPLG. INSTALLED 16' OF NEW 2" AND 15' OF NEW 4" MAIN REMOVED 4 MECH CPLGS AND ONE MAXY TROHL FITTING. TESTED ALL MAIN FOR 1 HR ON SITE. SOAP TESTED ALL FIITINGS @ 46 #.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026893800 | 557 | EX | INSTALL 40' OF 3"PMMP MAIN | 2019-09-17 | 1202 VERSAILLES | B | 57421.3808 | 57922.77 | 501.3892 | 1% | 40 | 59 | 981.7419 | INSTALLED 53' OF 030 PL WITH 3 SS TESTED FOR 15 MINS AND 3 SS TEES, 53' OF PL, 3 90 AND 3 TRANS FITTING ALL TESTED FOR 1 HR, INSTALLED NEW CV AND NEW TEST STATION SEALED ENDS OF ABN ML INT/EXT CORR INSPT COMPLETED 9-13-19 JEN
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026893900 | 558 | EX | RETIRE 15' OF 3"BSMP MAIN | 2019-09-17 | 1202 VERSAILLES | B | 178.6804 | 1045.62 | 866.9396 | 485% |  |  | 0 | AND A NEW TEST STATION. INT/EXT CORR COMPLETED BY JENS 9-13-19 REPL 40' OF BS ML DUE TO EXT CORR PITTING INSTALLED NEW WELDED TRANS WITH NEW 030 PL ML. INSTALLED NEW CV. TESTED NEW ML AND FITTINGS PER GS
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026895000 | 0001 | EX | ASV OPERABILITY HOLDING ACCT | 2020-12-14 | 2001 MERCER RD | B | 0 | 0 | 0 | 0% |  |  | 0
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026895800 | 559 | EX | INSTALL 12" CSHP | 2019-06-21 | WINCHESTER RD | B | 72.869 | 0 | -72.869 | 100% |  | 1 | 0 | THIS JO WAS CREATED TO ACCOUNT FOR FACILITIES/PROPERTY UNITS INSTALLED AND ABANDONED ON SYSTEM 32010138. ALL FACILITIES FOR THIS JO ARE ON INSTALL JO 18-0267731-01 AND ABN JO 18-0267732-00
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 19026896200 | 555 | EX | INSTALL 570' OF 2"PMMP MAIN | 2020-01-10 | 1585 MERCER RD | B | 26113.7225 | 66254.84 | 40141.1175 | 154% | 571 | 562 | 117.8912 | OVERRUN EXPLANATION: THIS JOB NEEDED 334 EXTRA UNITS OF HEAVY ROCK BORE INS TEAD OF THE DIRECTIONAL BORE ESTIMATED.
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026896300 | 561 | EX | INSTALL 5'-6" PMLP | 2019-09-13 | BLUE GRASS AV | B | 1441.3238 | 0 | -1441.3238 | 100% | 5 | 5 | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026896500 | 562 | EX | ABD 30'-8" BSLP | 2020-01-17 | 402 S BROADWAY | B | 9692.8277 | 10745.29 | 1052.4623 | 11% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026896700 | 555 | EX | INSTALL 100' OF 2"PMMP MAIN | 2019-10-02 | 1017 MAJESTIC DR | B | 7866.9075 | 9132.58 | 1265.6725 | 16% | 100 | 100 | 91.3258
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026897500 | 555 | EX | INSTALL 3400' OF 2"/4"PMMP | 2020-02-19 | TIDEWATER FLAT LT 132 | B | 75934.4643 | 76209.9 | 275.4357 | 0% | 3400 | 3300 | 23.0939
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026898700 | 557 | EX | INSERT 221' OF 4"PMLP MAIN | 2019-10-04 | 220 W HIGH ST | A | 45101.8024 | 53400.95 | 8299.1476 | 18% | 221 | 221 | 241.6333
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026898800 | 558 | EX | RETIRE 221'- 6"BSLP MN D221762 | 2019-10-04 | 220 W HIGH ST | A | 70.3067 | 38421.22 | 38350.9133 | 54,548% |  |  | 0 | REPL 060 BS ML WITH 220' OF 040 PL ML. TESTED @ 90 # FOR 1 HR, ON SITE NEW PIPE PURGED TO GS. TIED OVER AND TESTED 2 SL @ 90 # FOR 5 MINS SOAP TESTED CONN PTS @ 10" OF WC. INT/EXT CORR INSPT COMPLETED 10-4-19 JE
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026899400 | 555 | EX | INSTALL 350' OF 2"PMMP MAIN | 2019-12-05 | 815 SIESTA CV LT4 | B | 21423.1564 | 56465.73 | 35042.5736 | 164% | 350 | 380 | 148.594 | COMPLETED PAST COMMIT DATE DUE TO WEATHER,EXTRA VACUUM EXCAVATING DUE TO MISS MARKED UTILITY LOCATES, AND WAITING ON DEMO MACHINE TO MAKE ROCK BORE. TWALKER/KY 6-5-2020: PROJECT PLANNED FOR DIRECT BORE BUT CREWS HIT ROCK AND SPOTTING OTHER UTILITIES ADDED $28,000 IN CONTRACT COST, CO LABOR INCREASED BY $3000 AND SEGA WAS $5000 HIGHER THAN ESTIMATE.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026899500 | 555 | EX | INSTALL 385' OF 2"PMMP MAIN | 2019-12-04 | 519 WELLINGTON WY LT | B | 27253.815 | 28529.4 | 1275.585 | 5% | 385 | 385 | 74.1023
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026899900 | 555 | EX | INSTALL 3720' OF 2"/4"PMMP | 2020-02-28 | MOON RISE WY LT137 | B | 83267.4643 | 94770.28 | 11502.8157 | 14% | 3720 | 3982 | 23.7997 | MISSED COMMIT DATE DUE TO BAD WEATHER CONDITIONS.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026900001 | 557 | EX | INSTALL 10150'-2"/6"/8"PMMP | 2020-08-25 | WALTON AV | B | 1924983.1791 | 2564883.48 | 639900.3009 | 33% | 10150 | 10731 | 239.0163 | TWALKER/KY 06-14-21: LEVEL 2 VARIANCE ADDED TO WMS.DOCS TO EXPLAIN JOB COST OVER RUN. PROJECT WAS IMPACTED BY DELAYS ASSOCIATED WITH COVID - SEVERAL STREETS WERE PLANNED TO BE DIRECTIONAL BORE BUT SINCE WE COULD NOT ACCESS HOMES DURING COVID IN SPRING 2020 WE HAD TO OPEN CUT IN STREET AND CITY OF LEXINGTON REQUIRED ADDITIONAL PAVING/STREET REPAIRS WHICH INCREASED THE COST OF THE PROJECT.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026900100 | 558 | EX | RETIRE 12000'- CI/BSLP MAINS | 2020-12-18 | WALTON AV | B | 200.4185 | 963.39 | 762.9715 | 381% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026900800 | 566 | EX | RETIRE 6" LP SERVICE LINE | 2019-10-17 | 2250 CLAYS MILL RD | B | 279.2269 | 0 | -279.2269 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026901300 | 561 | EX | INSTALL 5'-6" PMMP | 2019-12-10 | WILSON DOWNING | B | 16908.4616 | 21620.33 | 4711.8684 | 28% | 460 | 5 | 4324.066
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026901400 | 562 | EX | RETIRE 5'-6" PMMP | 2019-12-10 | WILSON DOWNING | B | 74.8323 | 0 | -74.8323 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026901500 | 577 | EX | INSTALL CHAIN LINK FENCE | 2020-01-14 | 220 CLAY AV | F | 9450.3856 | 11671.37 | 2220.9844 | 24% |  |  | 0 | SIGNS UP APARKS
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026901600 | 2000 | EX | ACQUIRE NEW EASEMENT | 2020-01-10 | 450 PARK PL LT3 | B | 6133 | 0 | -6133 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026901901 | 555 | EX | INSTALL 3480' OF 2"/4"PMMP | 2020-06-24 | CLAYS MILL RD LT 1 | B | 154827.601 | 168603.1 | 13775.499 | 9% | 3480 | 2579 | 65.3754
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026902300 | 561 | EX | INSTALL 200'-4" PMMP | 2019-11-11 | ROSEMONT GN | B | 75295.2308 | 111439.24 | 36144.0092 | 48% | 200 | 204 | 546.2708 | KEVIN KOUNS COMPLETED PAPERWORK CONTRACT LABOR WAS $31,000 MORE THAN ESTIMATED, WHICH ALSO INCREASED SEGA B Y $9,000. THERE WAS A REDUCTION IN OTHER COSTS OF $6,000. D.LEMONS 6/16/202 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026902400 | 562 | EX | RETIRE 200'-4" PMMP | 2019-11-11 | ROSEMONT GN | B | 76.3408 | 50.23 | -26.1108 | -34% |  |  | 0 | KEVIN KOUNS COMPLETED PAPERWORK
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 19026902900 | 909 | EX | INSTALL ELECTRONIC EQUIP | 2019-08-30 | 1314 WINCHESTER RD | F | 6741.6923 | 4765.04 | -1976.6523 | -29% |  |  | 0 | EQUIPMENT INSTALLED BY ACP
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 19026903700 | 558 | EX | RETIRE 500'- 4" BSLP MAIN | 2019-10-22 | 535 S UPPER ST | A | 11769.1093 | 16709.48 | 4940.3707 | 42% |  |  | 0 | ABDN 481 FT OF 3 " AND 67 4" MAIN PURGED OUT MAIN PLUGED BOTH ENDS SOAP TEST BOTH END CAPS AT OP FOR 5 MIN SOAP TEST ALL PAC CLAMPS AT OP FOR 5 MIN BAR HOLE BANKS NO GAS FOUND INSTALL 1 ANODE ON EACH SEPERATED PEICE OF MAIN
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026904100 | 557 | EX | INSTALL 1300' OF 2"PMMP MAIN | 2020-03-27 | TRANSYLVANIA PR | B | 155044.5883 | 169376.29 | 14331.7017 | 9% | 1300 | 2250 | 75.2784
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026904200 | 558 | EX | RETIRE 2700' OF 3"/4"BSLP MAIN | 2020-03-27 | TRANSYLVANIA PR | B | 137.5058 | 0 | -137.5058 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026904500 | 557 | EX | INSTALL 8' OF 3"PMMP MAIN | 2019-10-18 | CANTERBURY GREEN | A | 9724.607 | 152.13 | -9572.477 | -98% | 8 | 5 | 30.426 | INSTALLED 5 FT OF 3 IN MAIN TEST 90 LB FOR 20 MIN TEST OK TESTED ALL TEES 90 LB FOR 5 MIN SOAP TESTED ALL TIE INS AND END CAPS ON TEES AT OP FOR 5MIN BAR HOLE BANKS NO GAS FOUND
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026904600 | 558 | EX | RETIRE 8" OF 3"PMP MAIN | 2019-10-18 | CANTERBURY GREEN | A | 65.5253 | 0 | -65.5253 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026904900 | 577 | EX | INSTALL NEW CHAIN LINK FENCE | 2020-01-14 | TOWNLEY DR | F | 7539.783 | 9554.71 | 2014.927 | 27% |  |  | 0 | SIGNS UP /// REG STATION SECURED APARKS 12-20-19
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026906100 | 557 | EX | INSTALL 10' OF 3"PMIP MAIN | 2019-10-29 | THE CURTILAGE | A | 15368.93 | 10991.02 | -4377.91 | -28% | 10 | 10 | 1099.102 | CUT OUT OLD MAIN PLACED WITH NEW PEICE OF MAIN TESTED 90 LB FOR FOR 20 MIN SOAP TEST FINAL TIE IN AT OP FOR 5 MIN BAR HOLE BANKS NO GAS FOUND
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026906200 | 558 | EX | RETIRE 10' OF 3"PIP MAIN | 2019-10-29 | THE CURTILAGE | A | 65.5253 | 13.82 | -51.7053 | -79% |  |  | 0 | RETIRED 6 FT OF MAIN THAT HAD A BAD TEE WELD CUT OUT AND REPLACED MAIN AND TIED BACK OVER 1 SL
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026906400 | 557 | EX | INSTALL 6' - 4" PMIP | 2019-10-30 | OLD NICHOLASVILLE RD | A | 8611.5734 | 5138.67 | -3472.9034 | -40% | 6 | 6 | 856.445 | TEST PIPE 90 LB FOR 20 MIN OK TEST ALL TEES 90 LB FOR 5 MIN OK SOAP TEST EFC 5 MIN AT OP SOAP TEST ALL END CAPS ON TEES AT OP FOR 5 MIN BAR HOLE BANKS NO GAS FOUND
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026906500 | 558 | EX | RETIRE 6' - 4" PMIP | 2019-10-30 | OLD NICHOLASVILLE RD | A | 55.3518 | 3943.05 | 3887.6982 | 7,024% |  |  | 0 | RETIRED 6 FT OF DAMAGED 4 IN PLASTIC MAIN PURGED OUT AND CUT OUT ACCORDING TO GAS STANDARDS
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026907300 | 2000 | EX | INVESTIGATE LAND RIGHTS | 2022-11-10 | STRADER RD |  | 5000 | 0 | -5000 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026907600 | 557 | EX | INSTALL 10'-3" PMLP EMERGENCY | 2019-11-11 | ROSEMONT GARDEN | B | 8524.8696 | 21952.97 | 13428.1004 | 158% | 10 | 37 | 593.3235
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026907700 | 558 | EX | RETIRE 10'-3" PLP EMERGENCY | 2019-11-14 | ROSEMONT GARDEN | B | 74.2651 | 0 | -74.2651 | 100% |  |  | 0
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 19026907800 | 561 | EX | RELOCATE 10'-3" PMMP | 2020-04-14 | LAFAYETTE ST | B | 16966.8702 | 10974.69 | -5992.1802 | -35% | 10 | 14 | 783.9064
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026908401 | 561 | EX | INSTALL 560-2" PMMP | 2020-04-10 | BOLIVAR | B | 124681.7584 | 87168.26 | -37513.4984 | -30% | 562 | 565 | 154.2801 | UNDERRUN EXPLANATION: THE ESTIMATED COLD PATCH AND OTHER HARD SURFACE REPAL RES WAS NOT NEEDED AS WAS ORIGINALLY INTENED LEADING TO THE UNDERRUN.
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026908500 | 562 | EX | RETIRE 910'-4" BSLP | 2020-04-10 | BOLIVAR | B | 81.1135 | 0 | -81.1135 | 100% |  |  | 0 | TOTAL FOOTAGE OF LP ABANDONED 913 FEET
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 19026908600 | 562 | EX | ABANDON 10'-3" PMMP | 2020-04-14 | LAFAYETTE ST | B | 55.9022 | 0 | -55.9022 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026908700 | 2000 | EX | INVESTIGATE ENCROACHMENT | 2023-11-21 | 4130 GEORGETOWN RD | B | 7000 | 0 | -7000 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026908800 | 584 | EX | RETIRE PIT REG STATION W/AMRP | 2020-11-04 | 130 E BELL CT | F | 5232.9569 | 16127.77 | 10894.8131 | 208% |  |  | 0 | STATION SHUT IN AT 1600 RETIRED AT 1800 APARKS 11-4-2020
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026909100 | 909 | EX | INSTALL SOLAR PANEL KIT | 2019-12-23 | 3005 TODDS RD | F | 12595.6597 | 10543.88 | -2051.7797 | -16% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026909200 | 910 | EX | RETIRE SOLAR PANEL | 2019-12-23 | 3005 TODDS RD | F | 75.281 | 0 | -75.281 | 100% |  |  | 0
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 19026909400 | 2000 | EX | LEESTOWN RD - ASSESS CONFLICT | 2023-08-16 | LEESTOWN @ NEW CIRCLE RD |  | 30829 | 0 | -30829 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026909901 | 561 | EX | INSTALL 1696'-4",6"&8" PMMP | 2020-06-10 | CHAMPIONS AV | B | 558448.3569 | 403238.27 | -155210.0869 | -28% | 1634 | 1713 | 235.3989 | PAID MISC DOLLARS AND CENTS FOR CONCRETE BLOCK. PAID MISC DOLLARS AND CENTS FOR PORTABLE TOILET INSTALLED: 1197' - 8" PMMP 357' - 4" PMMP 84' - 6" PMMP ABANDONED: 1455' - 8" BSMP 321' - 4" PMMP UNDERRUN EXPLANATION: PAVING COSTS WERE ESTIMATED THAT THE CITY ENDED UP PE RFORMING AND PAYING FOR.
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026910000 | 562 | EX | RETIRE 1814'-4",6"&8" BS,CS,P | 2020-06-22 | CHAMPIONS AV | B | 91.4991 | 214.05 | 122.5509 | 134% |  |  | 0
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 19026910500 | 584 | EX | RETIRE REG STATION WITH AMRP | 2020-10-28 | 360 BUCOTO CT | F | 2947.9713 | 4495.47 | 1547.4987 | 52% |  |  | 0 | CMCHOLAN 10-28-2020
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 19026910600 | 2000 | EX | INVESTIGATE THE RIGHT OF WAY | 2020-07-28 | BUCOTO CT | B | 4267 | 0 | -4267 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026912301 | 555 | EX | INSTALL 1800' OF 2"PMMP MAIN | 2020-09-08 | 3752 BRANHAM PK | B | 62341.3739 | 68420.98 | 6079.6061 | 10% | 1800 | 1838 | 37.2258
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026912600 | 555 | EX | INSTALL 150' OF 2"PMMP | 2020-01-15 | 3281 SQUIRE OAK DR | B | 12601.0923 | 14418.82 | 1817.7277 | 14% | 100 | 133 | 108.4122
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026912700 | 577 | EX | INSTALL FENCE & BOLLARDS | 2019-12-27 | 740 W NEW CIRCLE RD RR | F | 8318.1356 | 8608.62 | 290.4844 | 3% |  |  | 0 | SIGNS UP APARKS 01-09-20
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 19026912900 | 565 | EX | INSTALL 3" PLP CO/CUST SERVICE | 2019-12-06 | 913 GEORGETOWN ST | B | 16531.4093 | 2628.33 | -13903.0793 | -84% | 160 |  | 0
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 19026913800 | 2000 | EX | FAYETTE PLAZA - MAP EXIST MAIN | 2020-11-18 | FAYETTE PLAZA ESMT |  | 7225 | 0 | -7225 | 100% |  |  | 0
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 19026915100 | 575 | EX | BUY PERMANENT NS RR RIGHTS | 2019-12-31 | 2001 MERCER RD | F | 25861 | 25911.05 | 50.05 | 0% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026915201 | 557 | EX | INSTALL 5075' OF 4"/6"PMLP MN | 2020-05-14 | 206 N UPPER ST | B | 1601511.955 | 1646136.5 | 44624.545 | 3% | 4125 | 5285 | 311.4733 | UNDERRUN EXPLANATION: APPARENTLY POWERPLANT DID NOT UPDATE WMS THIS MONTH. WHILE THE OUT OF TOLERANCE REPORT SHOWS A SIGNIFICANT UNDERRUN, POWER PLANT SHOWS A SPEND OF$1,537,407 AS OF 11/24/2020. SINCE POWERPLANT IS THE SYSTE M OF RECORD, POWERPLANT IS PRESUMED CORRECT. THERE FOR NO EXPLANATION IS NE EDED.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026915300 | 558 | EX | RETIRE 5000' OF 4"CI/BSLP MAIN | 2020-10-13 | 206 N UPPER ST | B | 158.76 | 5463.17 | 5304.41 | 3,341% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026915400 | 577 | EX | PM INSTALL REG BUILDING PMF | 2020-10-09 | 2350 FORTUNE DR | F | 268939 | 251792.39 | -17146.61 | -6% |  |  | 0 | COMPLETED PAPERWORK AND CREATED FACILITIES AND RTS 3RD PARTY INSPECTOR RONNIE STANLEY ON SITE AND IN CHARGE OF PROJECT
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026915500 | 583 | EX | PM INSTALL REGULATION PMF | 2020-10-09 | 2350 FORTUNE DR | F | 3736473.7717 | 3950570.49 | 214096.7183 | 6% | 740 |  | 0 | ESPARKS 09-11-20 ESPARKS 11-03-20 DID ALL STAINLESS STEEL TUBING WORK AND CATALYTIC HEATER INSTALLS INSPECTED REGULATORS AND PLACE STATION IN SERVICE ALL PIPING AND EQUIPMENT INSTALLED BY CONTRACTOR 3RD PARTY INSPECTOR RONNIE STANLEY ON SITE AND IN CHARGE OF JOB CFARIS 12/5/20
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026915600 | 584 | EX | PM RETIRE REGULATION PMF | 2020-06-10 | 2350 FORTUNE DR | F | 1208.7846 | 69101.61 | 67892.8254 | 5,617% |  |  | 0 | SHUT STATION IN AND PURGED SETTING AND MAINLINE PIPING. 3RD PARTY INSPECTOR RONNIE STANLEY ON SITE AND OVER JOB UNDERRUN EXPLANATION: FIELD ENGINEERING ESTIMATED IN THE MANNER THAT WE HAV E BEEN INSTRUCTED TO. MAJOR PROJECTS CHARGED DIFFERENTLY. THEY DOCUMENT EHE IR EXPLANTIONS DIFFERENTLY. CONTACT HEATH HOLMAN IF THERE ARE ANY QUESTIONS .
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026915700 | 909 | EX | PM INSTALL I&C EQUIPMENT PMF | 2020-10-09 | 2350 FORTUNE DR | F | 150000 | 170738.63 | 20738.63 | 14% |  |  | 0 | COMPLETED PAPERWORK AND CREATED FACILITIES AND RTS 3RD PARTY INSPECTOR RONNIE STANLEY ON SITE AND IN CHARGE OF PROJECT
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026915800 | 910 | EX | PM RETIRE IC EQUIPMENT PMF | 2020-06-10 | 2350 FORTUNE DR | F | 127.6421 | 542.51 | 414.8679 | 325% |  |  | 0 | COMPLETED PAPERWORK AND RETIRED FACILITIES 3RD PARTY INSPECTOR RONNIE STANLEY ON SITE AND IN CHARGE OF PROJECT
KY | KY - WEST | 2621 | PTRUE |  |  |  | 19026916100 | 559 | EX | PM INSTALL OUTLET PIPING PMF | 2020-10-09 | 2350 FORTUNE DR | C | 224570 | 73044.38 | -151525.62 | -67% | 120 | 181 | 403.5601 | OUT OF TOLERERACE EXPLNATION: THIS IS A MAJOR PROJECTS PROJECT. ACCORDING T O LIZ EISENHART, JENNIFER HAMMONDS WAS ASKED TO DO AN EXPLANATION FOR THE O UT OF TOLERENCE SITUATION. HOWEVER, FIELD ENGINEERING DID NOT SEE THAT EXPL ANATION. CONTACT HEATH HOLMAN PROJECT MANAGER IF YOU HAVE ANY QUESTIONS. I PRESUME IT WILL BE DOCUMENATED IN WMSDOCS.
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026916200 | 560 | EX | PM RETIRE OUTLET PIPING PMF | 2020-10-09 | 2350 FORTUNE DR | C | 1027.6421 | 0 | -1027.6421 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026916300 | 575 | EX | PM AQUIRE LAND PMF | 2020-07-17 | 2350 FORTUNE DR | F | 75000 | 1040988.5 | 965988.5 | 1,288% |  |  | 0 | OVERRUN EXPLANATION: THIS IS A MAJOR PROJECTS PROJECT AND THE VARIANCE IS M ANAGED AT THE PROJECT LEVEL INSTEAD OF THE JOB ORDER LEVEL. IF THERE ARE AN Y QUESTIONS, PLEASE CONTACT MAJOR PROJECTS MANAGEMENT.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026916400 | 557 | EX | INSTALL 5' OF 4"PMLP MAIN | 2019-12-31 | 740 CHILES AV | A | 9665.1077 | 4965.37 | -4699.7377 | -49% | 5 | 5 | 993.074 | TWALKER/KY 1-30-20: THIS NOTE TO DOCUMENT APPROVAL FROM FOL BYRAN MORAN AND MYSELF ON THE 20 MINUTE TEST TIME FOR THIS SECTION OF REPLACEMENT MAIN FOR THIS EMERGENCY LEAK REPAIR PROJECT.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026916500 | 558 | EX | RETIRE 5' OF 4"PLP MAIN | 2019-12-31 | 740 CHILES AV | A | 65.7128 | 0 | -65.7128 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026916700 | 559 | EX | INSTALL 65' OF 4"PMMP | 2020-02-27 | 3700 OLD TATES CREEK RD | B | 32594.999 | 44512.84 | 11917.841 | 37% | 66 | 96 | 463.6754 | COMMIT DATE WAS ON SUNDAY 3-1-2020
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026916800 | 560 | EX | RETIRE 60' OF 6"CSMP MAIN | 2020-02-27 | 3713 OLD TATES CREEK RD | B | 79.38 | 71.35 | -8.03 | -10% |  |  | 0 | ONLY 1 WIPE SAMPLE TAKEN, DISREGARD SAMPLE #2 06082020 BREFFETT
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026917300 | 557 | EX | INSTALL 5' - 2" PMMP | 2019-12-19 | 117 LACKAWANNA | A | 1409.1077 | 117.13 | -1291.9777 | -92% | 0 | 5 | 23.426
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026917400 | 558 | EX | RETIRE 5' - 2" PMMP | 2019-12-19 | 117 LACKAWANNA | A | 48.7128 | 0.67 | -48.0428 | -99% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026917700 | 557 | EX | INSTALL 5'-2" PMMP | 2020-01-06 | 3117 CLAIR RD | A | 3370.5385 | 3055.88 | -314.6585 | -9% | 5 | 5 | 611.176 | INSTALLED 5 FT PEICE OF MAIN TEST 90 LB FOR 1 HR TEST OK SOAP TEST FINALL COUPLINGS AT OP FOR 5 MIN BAR HOLE BANKS NO GAS FOUND
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026917800 | 558 | EX | RETIRE 5'-2" PIP | 2020-01-06 | 3117 CLAIR RD | A | 69.8882 | 3439.84 | 3369.9518 | 4,822% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026917901 | 555 | EX | INSTALL 1150' OF 2"PMMP MAIN | 2020-09-16 | CRESTFIELD LN LT 1 | B | 40732.3468 | 36680.66 | -4051.6868 | -10% | 1150 | 1193 | 30.7466
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 20026918500 | 557 | EX | INSTALL 6'-2"PMMP | 2020-01-07 | ATHENS BOONESBORO RD | A | 5610.7846 | 4843.5 | -767.2846 | -14% | 6 | 6 | 807.25 | REPLACED 6 FT OF MAIN TEST 90 LB FFOR 1 HR TEST ALL TEES 90 LB FOR 5 MIN SOAP TEST FINAL EFC AT OP FOR 5 MIN 13 LB BAR HOLE BANKS NO GAS FOUND
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 20026918600 | 558 | EX | RETIRED 6'-2"PMMP | 2020-01-07 | ATHENS BOONESBORO RD | A | 64.321 | 3627.12 | 3562.799 | 5,539% |  |  | 0 | CUT OUT 6 FT OF MAIN LEAK ON TEE TO SL REPLACED PEICE OF MAIN TESTED MAIN 90 LB FOR 1 HR TEST OK
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 20026919200 | 557 | EX | INSTALL 5'-4"PMLP | 2020-01-13 | 309 OWSLEY AV | A | 5187.7846 | 254.03 | -4933.7546 | -95% | 5 | 6 | 42.3383 | INSTALLED 5'1" OF NEW 040 PL ML TO REPL LEAKING SF CPLG OFF SRV TEE TESTED @ 90 FOR 1 HR ON SITE. PURGE TEE TESTED @ 90 FOR 5 MINS ON SITE. CONN PTS TESTED @ 9.5" WC MB INSTTALLED OVER TEE 1-13-20 JENS
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 20026919300 | 558 | EX | RETIRE MAIN - LEAKAGE | 2020-01-13 | 309 OWSLEY AV | A | 64.321 | 4751.66 | 4687.339 | 7,287% |  |  | 0 | REPL 5' 1" OF 040 PL ML DUE TO SOCKET ELL LEAKING OF TEE. CUT OUT TEE AND BUTT FUSION ON MAIN REPL WITH 5' 1" OF NEW MAIN TESTED ON SITE FOR 1 HR. SOAP TESTED CONN PTS @ 9.5" WC. COMPLETED 1-13-20 JENS/RLA
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 20026919900 | 557 | EX | INSTALL 100'-8" PMLP | 2020-03-13 | 140 SOUTHLAND DR | B | 72449.2726 | 90885.82 | 18436.5474 | 25% | 106 | 100 | 908.8582
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 20026920000 | 558 | EX | RETIRE 100'-8"BS/CS LP | 2020-03-13 | 140 SOUTHLAND DR | B | 79.38 | 2841.11 | 2761.73 | 3,479% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026920400 | 584 | EX | RETIRE PIT REG STATION #1023 | 2020-09-03 | 1202 VERSAILLES RD | F | 6096.8063 | 11544.48 | 5447.6737 | 89% |  |  | 0
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 20026920600 | 2000 | EX | CLAYS MILL RD SECTION 1B | 2021-04-29 | CLAYS MILL RD SECT 1B |  | 55323 | 0 | -55323 | 100% |  |  | 0 | VERIFIED & EXPOSED VIA HYDRO EXCAVATION; SPOTTED PLLP MAIN TO VERIFY DEPTH MEASUREMENTS FOR MAPPING & SURVEY INFORMATION; INSTALLED FLUSH MOUNT TRACER WIRE STATION FOR FUTURE LOCATES & WORK; JNEWSOME 8/7/2020 EXPOSED 8'HP GAS MAIN FOR B SLONE VIA HYDRO EXCAVATION; RECORDED DEPTHS AT STAKED LOCATIONS TO MAP APPROXIMATE LOCATION FOR ENGINEERING PROJECT JNEWSOME 8/24/20 JOB NOT COMPLETE, USED HYDRO EXCAVATION TO EXPOSE PORTIONS OF GAS FACILITY FOR ENGINEERING B SLONE NEED TO EXPOSE MORE GAS FACILITIES, WILL RETURN FOR FURTHER IVESTIGATION EXPOSED FACILITIES FOR ENGINEERING B SLONE; INSTALLED ELECTONIC MARKERS & LINE MARKER W/WIRE FOR FUTURE REFERENCE; RECORDED DATA FOR DEPTHS & PIN POINT TIE INS JNEWSOME GCCC# 8772
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 20026920700 | 2000 | EX | TRC SURVEY/STUDIES | 2021-12-29 | 2001 MERCER RD | A | 90000 | 0 | -90000 | 100% |  |  | 0 | INSTRUCTED BY RICK WILBERT TO EXECUTE WE WERE TOLD THIS DATE THAT THE PROJECT WAS COMPLETED. THERE IS NO COMPLIAN CE ISSUE THAT I AM AWARE OF.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026921400 | 561 | EX | INSTALL 30' OF 2"PMLP MAIN | 2020-03-03 | GRAHAM AV | B | 25344.1992 | 47531.53 | 22187.3308 | 88% | 30 | 140 | 339.5109 | TWALKER/KY 03-09-20: I TRIED TO REVISE JOB ORDER AFTER SCOPE CHANGE AND ADDITIONAL WORK REQUIRED BY CONSTRUCTION BUT WMS WOULD NOT ALLOW REVISION DUE TO UNPAID INVOICES MESSAGE.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026921500 | 562 | EX | RETIRE 20' OF 2"BSLP MAIN | 2020-03-03 | GRAHAM AV | B | 81.0294 | 341.45 | 260.4206 | 321% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026921900 | 557 | EX | INSTALL 5'-1"CSHP W/GATE VLV | 2020-03-17 | 200 W LOUDON AV | B | 29034.4738 | 33092.16 | 4057.6862 | 14% | 15 | 4 | 8273.04
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026922000 | 558 | EX | RETIRE 6' - 2"CSHP MAIN | 2020-03-17 | 200 W LOUDON AV | B | 79.38 | 3464.67 | 3385.29 | 4,265% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026922100 | 557 | EX | INSTALL 400' OF 8"PMMP MAIN | 2020-04-21 | 1815 RICHMOND RD | B | 78194.4624 | 80494.44 | 2299.9776 | 3% | 400 | 359 | 224.2185
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026922200 | 558 | EX | RETIRE 380' OF 8"BSMP MAIN | 2020-04-21 | 1815 RICHMOND RD | B | 84.7492 | 0 | -84.7492 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026923000 | 2000 | EX | ACQUIRE EASEMENT FOR S/L | 2020-03-18 | 152 MARKET ST | B | 6433 | 0 | -6433 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026923200 | 562 | EX | RETIRE 70' OF 3"BSMP MAIN | 2020-03-09 | 1540 EASTLAND DR | B | 59.38 | 4728.22 | 4668.84 | 7,863% |  |  | 0 | ABANDON SECTION OF 3INCH MAIN SOAP TESTED DEADEND CAP FOR 15MIN
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026924001 | 561 | EX | INSTALL 165'-4" CSHP | 2020-11-20 | 1345 OLD FRANKFORT PK | B | 67409.6919 | 85877.29 | 18467.5981 | 27% | 165 | 75 | 1145.0305
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026924100 | 562 | EX | RETIRE 100'-4" CSHP | 2020-12-07 | 1345 OLD FRANKFORT PK | B | 91.4991 | 0 | -91.4991 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026924201 | 561 | EX | INSTALL 2000'-6" PMMP | 2020-12-02 | 1345 OLD FRANKFORT PK | B | 975569.1751 | 1121652.66 | 146083.4849 | 15% | 2141 | 2183 | 513.8125
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026924300 | 562 | EX | RETIRE 500'-8" CSMP | 2020-12-07 | 1345 OLD FRANKFORT PK | B | 91.4991 | 142.7 | 51.2009 | 56% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026924400 | 575 | EX | NEW REGULATOR SITE | 2021-02-05 | 1313 OLD FRANKFORT PK | F | 13408.4857 | 0 | -13408.4857 | 100% |  |  | 0 | JO BEING COMPLETED AT COMPLETION OF PROJECT. D.LEMONS
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026924600 | 583 | EX | INSTAL REGULATOR STATION | 2020-12-02 | 1313 OLD FRANKFORT PK | F | 149467.4285 | 126002.5 | -23464.9285 | -16% | 2 |  | 0 | ESPARKS 11-19-20 CCC#3481 11-23-20 0920 APARKS INSTALL NEW REG STATION, RUN1 CONTROL @ 29#, MONITOR @ 34#, RUN 2 CONTROL @ 27#, MONITOR @ 34#, INLET @ 136#, PRV @ 35# SOAP TEST AT 2:15PM, INSPECTED SEAT TO SEAT, INLET OUTLET AND CONTROL LINES ON TO BOTH RUNS, NO BYPASS, MONITORED 30 MIN CMCHOLAN 12-2-2020 STATION PLACED IN SERVICE BY SHAUN MCHOLAN PAPERWORK COMPLETED BY CYNTHIA FARIS UNDERRUN EXPLANATION: COST UNDERRUN DO TO MATERIAL ESTIMATE PROVIDED WAS $5 2K MORE THAN CHARGED. LABOR AND CONTRACT COST DID OVERRUN $24K. POWERPLANT SHOWS $18K (12%) UNDERUN ON REIMBURSABLE PROJECT. POWERPLANT PRESUMED TO BE CORRECT. D.LEMONS 6/14/2021
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026924700 | 584 | EX | RETIRE REGULATOR SETTING | 2020-12-02 | 1313 OLD FRANKFORT PK | F | 91.4991 | 158.15 | 66.6509 | 73% |  |  | 0 | STAION ABANDONED APARKS 12-03-20 PAPERWORK COMPLETED BY CYNTHIA FARIS
KY | KY - WEST | 2621 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 20026925100 | 587 | EX | UPGRADE ELECTRONICS | 2020-05-04 | 2575 PALUMBO DR | F | 3205 | 3615.83 | 410.83 | 13% |  |  | 0 | UPGRADED 2G/3G MODEM TO RV50 4G/5G CELL MODEM EQUIPMENT INSTALLED BY ACP
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026925301 | 562 | EX | RETIRE 40'-2" PMP | 2020-02-28 | DEROODE ST | B | 2813.697 | 2516 | -297.697 | -11% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026925400 | 557 | EX | INSTALL 775' OF 2"PMMP MAIN | 2020-05-22 | 401 N BROADWAY ST | B | 314223.8791 | 210896.27 | -103327.6091 | -33% | 1100 | 790 | 266.9573 | TWALKER/KY 09-21-2020: JOB UNDER RUNNING IN WMS DUE TO PAVING/RESTORATION COST HAVE NOT POSTED AT THIS TIME. EXPLANATION UPDATE: SOME OF THE PAVING HAS HIT, BUT NOT ALL. ALSO POWERPLAN T MAY NOT HAVE UPDATED WMS THIS MONTH. POWERPLANT SHOWS ABOUT $100,000 MORE COSTS THAN WMS. POWER PLANT PRESUMEND CORRECT. TWALKER/KY 06-14-21: POWERPLANT AND WMS REFLECT SAME JOB COST. JOB COST UNDER RUN DUE, PROJEC WAS PLANNED FOR 1100' OF DUAL MAINS BUT ONLY 800'OF MAIN WAS REQUIRED. THE SHORTER JOB LOWER CONTRACT AND STREET REPAIR COST BY $70,000 AND SEGA WAS $10,000 LESS THAN ESTIMATE.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026925500 | 558 | EX | RETIRE 1650' OF 3"/4" CILP MN | 2020-08-06 | 401 N BROADWAY ST | B | 76.455 | 57.23 | -19.225 | -25% |  |  | 0
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026925600 | 587 | EX | UPGRADE ELECTRONICS | 2020-05-01 | 4000 TERMINAL DR | F | 3038 | 3635.83 | 597.83 | 20% |  |  | 0 | UPGRADED CELL MODEM FROM 2G/3G TO RV50 4G/5G EQUIPMENT INSTALLED BY ACP
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026925700 | 587 | EX | UPGRADE ELECTRONICS | 2020-04-29 | 1800 MERCER RD | F | 3038 | 3626.23 | 588.23 | 19% |  |  | 0 | UPGRADED CELL MODEM FROM 2G/3G TO RV50 4G/5G MODEM EQUIPMENT INSTALLED BY ACP
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026927000 | 587 | EX | UPGRADE ELECTRONICS | 2020-04-29 | 100 WESTHAMPTON DR | F | 3038 | 9093.01 | 6055.01 | 199% |  |  | 0 | UPGRADED 2G/3G MODEM TO RV50 4G/5G MODEM EQUIPMENT INSTALLED BY ACP
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026927200 | 587 | EX | UPGRADE ELECTRONICS | 2020-05-04 | 1740 NICHOLASVILLE RD | F | 3038 | 3714.82 | 676.82 | 22% |  |  | 0 | UPGRADED 2G/3G MODEM TO RV50 4G/5G CELL MODEM EQUIPMENT INSTALLED BY ACP
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026927300 | 587 | EX | UPGRADE ELECTRONICS | 2020-05-01 | 4201 VERSAILLES RD RR | F | 3038 | 3704.23 | 666.23 | 22% |  |  | 0 | UPGRADED 2G/3G MODEM TO RV50 4G/5G CELL MODEM EQUIPMENT INSTALLED BY ACP
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026927400 | 587 | EX | UPGRADE ELECTRONICS | 2020-04-30 | 1400 HARRODSBURG RD | F | 3038 | 3775.71 | 737.71 | 24% |  |  | 0 | UPGRADED 2G/3G MODEM TO RV50 4G/5G CELL MODEM EQUPIMENT INSTALLED BY ACP
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026927500 | 587 | EX | UPGRADE ELECTRONICS | 2020-05-04 | 150 N EAGLE CREEK DR | F | 3038 | 8184.07 | 5146.07 | 169% |  |  | 0 | UPGRADED CELL MODEM FROM 2G/3G TO RV50 4G/5G CELL MODEM EQUIPMENT INSTALLED BY ACP
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026927600 | 587 | EX | UPGRADE ELECTRONICS | 2020-04-30 | MANCHESTER ST RR | F | 3038 | 3603.22 | 565.22 | 19% |  |  | 0 | UPGRADED 2G/3G MODEM TO RV50 4G/5G CELL MODEM EQUIPMENT INSTALLED BY ACP
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026927700 | 587 | EX | UPGRADE ELECTRONICS | 2020-04-28 | 3301 LEESTOWN RD | F | 3038 | 3653.56 | 615.56 | 20% |  |  | 0 | UPGRADED 2G/3G MODEM TO RV50 4G/5G MODEM EQUIPMENT INSTALLED BY ACP
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026927800 | 587 | EX | UPGRADE ELECTRONICS | 2020-11-25 | 1225 VERSAILLES RD | F | 3038 | 6404.17 | 3366.17 | 111% |  |  | 0 | EFC REPLACED BY CHRIS COX AND JIM PASLEY PAPERWORK COMPLETED BY CYNTHIA FARIS JOB DELAYED DUE TO COVID 19 AND COMPLIANCE WORK
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026927900 | 587 | EX | UPGRADE ELECTRONICS | 2022-03-01 | 310 S LIMESTONE ST | F | 3038 | 3660.91 | 622.91 | 21% |  |  | 0 | EFC REPLACED BY C. COX ON 3-1-22 PAPERWORK CO BY J MULLINS ON 3-2-22
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026928000 | 587 | EX | UPGRADE ELECTRONICS | 2021-09-23 | 767 WINCHESTER RD | F | 3038 | 7833.1 | 4795.1 | 158% |  |  | 0 | REPLACED EFC AND UPSIZED METER TO 16M ALSO WORKED TP AND MGRP WHILE ON SITE
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026928100 | 587 | EX | UPGRADE ELECTRONICS | 2021-10-20 | 451 HARBISON RD | F | 3038 | 6063.75 | 3025.75 | 100% |  |  | 0 | REPLACED EFC
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026928200 | 587 | EX | UPGRADE ELECTRONICS | 2022-07-14 | 1639 JAGGIE FOX WY | F | 3038 | 3460.63 | 422.63 | 14% |  |  | 0 | CMCHOLAN 7-14-2022 RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07-14-2022
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026928300 | 587 | EX | UPGRADE FROM 3G NETWORK | 2022-02-28 | 800 ROSE ST RR | F | 3038 | 6815.37 | 3777.37 | 124% |  |  | 0 | RETIRED OLD EFC INSTALLED NEW EC350 CCOX 02-28-2022
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026928400 | 587 | EX | UPGRADE FROM 3G NETWORK | 2022-07-14 | 454 FAIRMAN RD | F | 3038 | 3177.17 | 139.17 | 5% |  |  | 0 | RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07-14-2022
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026928500 | 587 | EX | UPGRADE ELECTRONICS | 2022-07-19 | 2510 RESEARCH PARK DR | F | 3038 | 3667.3 | 629.3 | 21% |  |  | 0 | CWEMPE BLONE 7/19/22 RETIRED MINI-AT INSTALLED NEW EC350 CWEMPE 07-19-2022
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026928600 | 587 | EX | UPGRADE ELECTRONICS | 2022-07-14 | 451 HARBISON RD | F | 5626 | 3158.07 | -2467.93 | -44% |  |  | 0 | RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026928700 | 587 | EX | UPGRADE ELECTRONICS | 2021-10-18 | 2250 LEESTOWN RD | F | 3038 | 8043.8 | 5005.8 | 165% |  |  | 0 | REPLACED EFC
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026928800 | 587 | EX | UPGRADE ELECTRONICS | 2022-03-02 | 1310 CENTRE PY | F | 3038 | 6614.01 | 3576.01 | 118% |  |  | 0 | ASSIST SMCHOLAN 03-02-2022 RHAYES ASSIST SMCHOLAN 03-02-2022 RHAYES INSTALLED NEW EC350 SOAP TEST TUBING 5MIN OPP PRESSURE SMCHOLAN 3-2-22
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026931400 | 566 | EX | NEEDS REVIEWED - RETIRE | 2020-06-17 | 271 W SHORT ST | B | 74.9022 | 0 | -74.9022 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026931500 | 565 | EX | INSTALL 30' OF 4"PMLP S/L | 2020-06-17 | 271 W SHORT ST | B | 13540.0439 | 25227.2 | 11687.1561 | 86% | 30 |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026931600 | 561 | EX | INSTALL 920' OF 6"PMLP MAIN | 2020-06-18 | ROSE ST | B | 135039.5537 | 129734.27 | -5305.2837 | -4% | 921 | 716 | 181.1931
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026931700 | 562 | EX | RETIRE 910' OF 6"BSLP MAIN | 2020-06-18 | ROSE ST | B | 84.5507 | 428.1 | 343.5493 | 406% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026932600 | 561 | EX | INSTALL 900' OF 2"PMMP MAIN | 2020-07-07 | GRAHAM AV | B | 109561.4915 | 83635.99 | -25925.5015 | -24% | 900 | 922 | 90.7115
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026932700 | 562 | EX | RETIRE 600' OF 3"BSLP MAIN | 2020-07-10 | GRAHAM AV | B | 84.5507 | 0 | -84.5507 | 100% |  |  | 0
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026933500 | 588 | EX | RETIRE ELECTRONICS | 2020-11-25 | 1225 VERSAILLES RD | F | 73.3494 | 0 | -73.3494 | 100% |  |  | 0 | EFC REPLACED BY CHRIS COX AND JAMES PASLEY PAPERWORK COMPLETED BY CYNTHIA FARIS JOB DELAYED BY COVID 19 AND COMPLIANCE WORK
KY | KY - WEST | 2621 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 20026933700 | 588 | EX | RETIRE ELECTRONICS | 2022-03-01 | 310 S LIMESTONE ST | F | 73.3494 | 452.45 | 379.1006 | 517% |  |  | 0 | GAUGE RETIRED BY C. COX PAPPER WORK CO BY J. MULLINS 3-2-2022
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026933800 | 588 | EX | RETIRE ELECTRONICS | 2021-10-20 | 451 HARBISON RD | F | 73.3494 | 0 | -73.3494 | 100% |  |  | 0 | REPLACED EFC
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026933900 | 588 | EX | RETIRE ELECTRONICS | 2022-07-14 | 1639 JAGGIE FOX WY | F | 73.3494 | 1039.15 | 965.8006 | 1,317% |  |  | 0 | CMCHOLAN 7-14-2022 RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07142022
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026934000 | 588 | EX | RETIRE ELECTRONICS | 2022-02-28 | 800 ROSE ST RR | F | 73.3494 | 626.57 | 553.2206 | 754% |  |  | 0 | RETIRED OLD EFC AND INSTALLED NEW EC350 CCOX 02-28-2022
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026934100 | 588 | EX | RETIRE ELECTRONICS | 2022-07-14 | 454 FAIRMAN RD | F | 73.3494 | 189.27 | 115.9206 | 158% |  |  | 0 | RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07-14-2022
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026934200 | 588 | EX | RETIRE ELECTRONICS | 2022-07-19 | 2510 RESEARCH PARK DR | F | 73.3494 | 502.89 | 429.5406 | 586% |  |  | 0 | CWEMPE BLONE 7/19/22 RETIRED OLD MINI-AT INSTALLED NEW EC350
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026934400 | 588 | EX | RETIRE ELECTRONICS | 2021-10-18 | 2250 LEESTOWN RD | F | 73.3494 | 0 | -73.3494 | 100% |  |  | 0 | REPLACED EFC
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026934500 | 588 | EX | RETIRE ELECTRONICS | 2022-03-02 | 1310 CENTRE PY | F | 73.3494 | 0 | -73.3494 | 100% |  |  | 0 | RETIRED MINI-AT INSTALLED NEW EC350 SMCHOLAN 3-2-22
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026935500 | 562 | EX | RETIRE 35'-4" PLP | 2020-03-07 | HUMMONS AV | A | 2057.5548 | 1252.91 | -804.6448 | -39% |  |  | 0 | ABANDONED 35FT OF 040 PLASTIC. SQUEEZED OFF AT INLINE TEE. INSTALLED VERFICATION GAUGE.TESTED TEE FOR 5MINS AT 90LBS-TEST OK.BUTT FUSED END CAP ON STUB. SOAP TEST FINAL TIE IN AT OP.TEST OK.BHB NGF KKINDER 03-06-20
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026936000 | 566 | EX | RETIRE 3"PMLP SERVICE LINE | 2020-03-20 | 325 COLUMBIA AV UK 127 | B | 5246.8263 | 5812.06 | 565.2337 | 11% |  |  | 0
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 20026936700 | 2000 | EX | ASESS CONFLICT W/HOTEL PROJECT | 2020-08-05 | 1810 BRYANT RD |  | 11320 | 0 | -11320 | 100% |  |  | 0 | PS&I COMPELTED BY JEFF PENDLETON AND DUKE MARTIN (BKSLONE)
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026938300 | 557 | EX | INSTALL 5' OF 6"PMLP MAIN | 2020-03-12 | 139 W SHORT ST | A | 8731.8561 | 183.13 | -8548.7261 | -98% | 5 | 4 | 45.7825
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026938400 | 558 | EX | RETIRE 5' OF 6"PLP MAIN | 2020-03-12 | 139 W SHORT ST | A | 74.9022 | 0 | -74.9022 | 100% |  |  | 0
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 20026938500 | 557 | EX | INSTALL 2" STOPPLE FITTING | 2020-04-28 | DEVONPORT | B | 16117.9739 | 6336.08 | -9781.8939 | -61% |  |  | 0
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 20026938600 | 558 | EX | RETIRE 200'-2" CS/P-MP | 2020-04-28 | DEVONPORT | B | 79.9022 | 924.26 | 844.3578 | 1,057% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026938800 | 559 | EX | INSTALL 10' OF 2"PMMP MAIN | 2020-03-26 | 232 BARROW RD | A | 11025.9805 | 3747.38 | -7278.6005 | -66% | 10 | 13 | 288.26 | INSTALLED 13' OF 020 MAIN. TESTED FROM HV TEE TO HV TEE FOR 1HR AT 90LBS. TEST OK.SQUEEZED OFF 040 TO CUT OUT TEE.INSTALLED END CAPS ON 040.SOAP TEST FITTINGS AT OP NGF.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026938900 | 560 | EX | RETIRE 5' OF 4"PMP MAIN | 2020-03-26 | 232 BARROW RD | A | 84.7492 | 148.86 | 64.1108 | 76% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026940000 | 909 | EX | INSTALL I&C EQUIPMENT | 2022-02-24 | 2005 VERSAILLES RD | F | 16155.4774 | 11589.34 | -4566.1374 | -28% |  |  | 0 | CCC# 43689 RETIRED PAPER CHART INSTALLED NEW ERX CCOX 02-24-2022
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026940100 | 584 | EX | RETIRE PAPER GUAGE | 2022-02-24 | 2005 VERSAILLES RD | F | 91.4991 | 172.3 | 80.8009 | 88% |  |  | 0 | RETIRED PAPER CHART INSTALLED HONEYWELL ERX CCOX 2-24-2022
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026940500 | 557 | EX | INSTALL 10' OF 4"PMMP MAIN | 2020-03-30 | 2235 BAHAMA RD | A | 7726.7 | 1760.54 | -5966.16 | -77% | 10 | 5 | 352.108
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026940600 | 558 | EX | RETIRE 10' OF 4"PAMP MAIN | 2020-03-30 | 2235 BAHAMA RD | A | 59.0617 | 1401.16 | 1342.0983 | 2,272% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026940700 | 566 | EX | RETIRE 40'-4" SERV | 2020-12-07 | 1375 OLD FRANKFORT PK FIRE | B | 72.7356 | 0 | -72.7356 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026940800 | 565 | EX | INSTALL 4" SEVICE | 2020-12-03 | 1375 OLD FRANKFORT PK FIRE | B | 13114.4692 | 8295.23 | -4819.2392 | -37% | 58 |  | 0 | REPLACED CAT1 SECTION OF SL AND 15'SECTION OF CAT2 OF SL TO TIE-IN POINT DETERMINED PER ENGINEER D LEMONS-CAT1 SECTION AND 15'PORTION OF CAT2 INSTALLED AND TESTED WITH MAIN INSTALLATION(20-0269242-01)-TESTED CAT2 FROM POINT OF BREAK-METER SETTING 90# 1HR
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026941400 | 909 | EX | INSTALL I&C EQUIPMENT | 2022-07-28 | KENNESAW DR | F | 16155.4774 | 12022.54 | -4132.9374 | -26% |  |  | 0 | INSTALLED TAP ON OUTLET LEG OF RUN 1 20# SYSTEM AND RAN SENSE LINES TO ERX FROM THE NEW TAP AND EXISTING HP SENSE LINE, AND COMMISSIONED ERX CCC 75328, CMCHOLAN CCOX 7-28-2022
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026943300 | 909 | EX | INSTALL I&C EQUIPMENT | 2022-05-27 | 1684 WAKEFIELD TR | F | 16155.4774 | 9146.19 | -7009.2874 | -43% |  |  | 0 | REMOVED BOTH PAPER CHARTS INSTALLED ERX FOR IP AND MP CMCHOLAN 4-14-2022 CC 65476 COMMISSIONED ERX RHAYES SMCHOLAN 05-03-2022 COMMITIONED ERX, PSP OK, CCC 65476 CMCHOLAN RHAYES 5-3-2022
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026943400 | 584 | EX | RETIRE GAUGE | 2022-05-27 | 1684 WAKEFIELD TR | F | 91.4991 | 543.13 | 451.6309 | 494% |  |  | 0 | REMOVED BOTH PAPER CHARTS INSTALLED ERX CC 62655 RHAYES SMCHOLAN CCOX EBLANTON 04-14-2022
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 20026943500 | 561 | EX | INSTALL 420'-4" PMMP | 2020-10-02 | 1810 BRYANT RD | B | 59269.1596 | 46882.16 | -12386.9996 | -21% | 420 | 364 | 128.7971
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 20026943600 | 562 | EX | RETIRE 396'-3"/4" PMP | 2020-10-02 | 1810 BRYANT RD | B | 91.4991 | 0 | -91.4991 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026943900 | 557 | EX | INSTALL NEW 4"POLY VALVE | 2020-04-21 | 937 MIDNIGHT PASS | A | 5878.4625 | 2938.81 | -2939.6525 | -50% | 6 | 8 | 367.3512
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026944000 | 558 | EX | RETIRE C8-180 4"POLY VALVE | 2020-04-21 | 937 MIDNIGHT PASS | A | 83.0617 | 2172.05 | 2088.9883 | 2,515% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026944500 | 2000 | EX | INVESTIGATE ROAD RIGHT OF WAY | 2020-10-28 | 1370 DEER HAVEN LN | B | 8617 | 0 | -8617 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026945201 | 555 | EX | INSTALL 5000' OF 2"PMMP MAIN | 2021-01-12 | WALDORF LN LT 1 | B | 223484.8945 | 228201.9 | 4717.0055 | 2% | 5000 | 4938 | 46.2134 | INSTALLED 4938"020 PMMP.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026945700 | 555 | EX | INSTALL 100' OF 2" PMMP MAIN | 2020-05-01 | 3116 RICHMOND RD | B | 11849.2172 | 9491.38 | -2357.8372 | -20% | 100 | 124 | 76.5434
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026945800 | 559 | EX | INSTAL 5'-2" PMMP (AS BUILT) | 2020-04-14 | 884 MARBLEHEAD DR | A | 4095.9465 | 2718.62 | -1377.3265 | -34% | 5 | 5 | 543.724
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026945900 | 560 | EX | RETIRE 5'-2" PMMP (AS B | 2020-04-14 | 884 MARBLEHEAD DR | A | 87.5813 | 0 | -87.5813 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026946100 | 557 | EX | INSTALL 1725' OF 2"PMMP MAIN | 2020-10-05 | CISCO RD | B | 289443.1144 | 414606.35 | 125163.2356 | 43% | 1725 | 1663 | 249.3123 | TWALKER/KY 03-18-21: LEVEL 2 EXPLAINATION ADDED TO WMS.DOCS DUE TO HIGHER PROJECT COST THAT RESULTED FROM ADDITIONAL HARD SURFACE/PAVING COST AND PROJECT TOOK ADDITIONAL TIME TO COMPLETED.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026946200 | 558 | EX | RETIRE 1905' OF 3"/4"BSLP MAIN | 2020-11-04 | CISCO RD | B | 54.5507 | 0 | -54.5507 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026946900 | 555 | EX | INSTALL 300' OF 2"PMMP MAIN | 2020-02-21 | 3159 BEAUMONT CENTR CR | B | 16395.5214 | 10451.88 | -5943.6414 | -36% | 300 | 190 | 55.0099
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026947600 | 586 | EX | DEMO BLOCK REG BUILDING | 2020-11-03 | 2171 CHRISTIAN DR | F | 19724.4167 | 17938.78 | -1785.6367 | -9% |  |  | 0 | BUILDING DEMO ON HOLD UNTIL MAIN RELOCATION COMPLETED
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 20026948400 | 575 | EX | LAND AGREEMENT LR115003 | 2019-12-31 |  | F | 0 | 19.65 | 19.65 | 100% |  |  | 0
KY | KY - WEST | 2621 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 20026948500 | 575 | EX | LAND AGREEMENT LR114662 | 2019-12-31 |  | F | 0 | 0 | 0 | 0% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026949400 | 557 | EX | INSTALL 5' OF 2"PMMP MAIN | 2020-05-11 | 152 EDGEMOOR DR | B | 8641.697 | 1894.3 | -6747.397 | -78% | 5 | 7 | 270.6143
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026949500 | 558 | EX | RETIRE 5' OF 2"PMMP MAIN | 2020-05-11 | 152 EDGEMOOR DR | B | 54.5507 | 372.11 | 317.5593 | 582% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026949700 | 557 | EX | INSTALL 20' OF 8"PMLP MAIN | 2020-05-20 | 633 E HIGH ST | A | 8890.7193 | 5176.53 | -3714.1893 | -42% | 20 | 15 | 345.102 | CUT OUT STEEL TO STEEL COUPLING-AND REPLACED WITH 15' OF 8" PLASTIC-PRESS TESTED @ 90LBS FOR 1 HR TEST OK-SOAP TEST FINAL TIE INS AND PAC CLAMPS @ OP TEST OK-BHBNGF-11IWC VERIFIED-COMPLETED TO TIE IN PLAN -ANICHOLS 5-20-2020
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026949800 | 558 | EX | RETIRE 20' - 8"BSLP MN D247035 | 2020-05-20 | 633 E HIGH ST | A | 65.2687 | 7426.84 | 7361.5713 | 11,279% |  |  | 0 | CUT OUT STEEL TO STEEL COUPLING-AND REPLACED WITH 15' OF 8" PLASTIC-PRESS TESTED @ 90LBS FOR 1 HR TEST OK-SOAP TEST FINAL TIE INS AND PAC CLAMPS @ OP TEST OK-BHBNGF-11IWC VERIFIED-COMPLETED TO TIE IN PLAN -ANICHOLS 5-20-2020
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026950800 | 585 | EX | INSTALL WOOD FENCE | 2020-11-30 | 542 CHINOE RD | F | 9731.8452 | 4327.44 | -5404.4052 | -56% |  |  | 0 | MONITORED FENCE INSTALL - ESPARKS 11-24-20 GCCC REF# 3641 ESPARKS 11-30-20 JOB ON HOLD DUE TO COVID19
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026950900 | 586 | EX | DEMO WOOD FENCE | 2020-11-30 | 542 CHINOE RD | F | 65.2687 | 2218.6 | 2153.3313 | 3,299% |  |  | 0 | JOB ON DELAYED DUE TO COVID19
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026951100 | 555 | EX | INSTALL 550' OF 2"PMMP MAIN | 2020-10-13 | 580 GREENFIELD DR BLDG 2 | B | 46540.7015 | 35511.21 | -11029.4915 | -24% | 550 | 511 | 69.4936
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026951300 | 557 | EX | INSTALL 6200' OF 2"PMMP MAIN | 2021-04-22 | 600 S LIMESTONE ST | B | 1180648.1173 | 1175556.48 | -5091.6373 | 0% | 6200 | 6324 | 185.8881
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026951400 | 558 | EX | RETIRE 7600' OF 4"CI/BSLP MAIN | 2021-05-11 | 600 S LIMESTONE ST | B | 165.7874 | 142.7 | -23.0874 | -14% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026951802 | 557 | EX | INSTALL 3980' OF 2"PMMP MAIN | 2021-03-26 | 250 S ASHLAND AV | B | 383869.9188 | 461944.16 | 78074.2412 | 20% | 3980 | 3755 | 123.0211 | TWALKER/KY 09-21-21: JOB OVER RUN DUE TO ADDITIONAL STREET AND HARD SURFACE REPAIR ADDED $70,000 TO CONTRACT COST AND SEGA WAS $7000 HIGHER THAN ESTIMA TE.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026951900 | 558 | EX | RETIRE 2100' OF 4"CI/PLP MAIN | 2021-03-26 | 250 S ASHLAND AV | B | 84.1799 | 0 | -84.1799 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026952100 | 557 | EX | INSTALL 20' OF 2"PMMP MAIN | 2020-05-27 | 374 NOTTINGHAM DR | A | 8084.5356 | 557.41 | -7527.1256 | -93% | 20 | 14 | 39.815 | CUT OUT AND REPLACED 14' SECTION OF MAIN-PRESS. TEST NEW MAIN @ 90LBS FOR 1HR TEST OK-SOAP TESTED FINAL TIE IN @OP TEST OK- SOAP TEST TEE CAPS @OP TEST OK- 14 PSI VERIFIED-BHBNGF-ANICHOLS 5-27-2020
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026952200 | 558 | EX | RETIRE 20' OF 2"PAMP MAIN | 2020-05-27 | 374 NOTTINGHAM DR | A | 52.2687 | 3423.89 | 3371.6213 | 6,451% |  |  | 0 | CUT OUT AND REPLACED 14' SECTION OF MAIN- PRESS. TEST NEW MAIN @ 90LBS FOR 1HR TEST OK-SOAP TEST FINAL TIE IN @ OP TEST OK-SOAP TEST TEE CAPS @ OP TEST OK-14PSI VERIFIED-BHBNGF-ANICHOLS 5-27-2020
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026952300 | 559 | EX | INSTALL 5'-6" PMMP | 2020-05-26 | MT VERNON DR | A | 2468.8932 | 4641.7 | 2172.8068 | 88% | 5 | 5 | 928.34
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026952400 | 560 | EX | RETIRE 5'-6" PMP | 2020-05-26 | MT VERNON DR | A | 71.2422 | 1383.86 | 1312.6178 | 1,842% |  |  | 0
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 20026953100 | 2000 | EX | RESEARCH LAND RIGHT | 2020-09-08 | 2931 GEORGETOWN RD |  | 4056 | 0 | -4056 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026953300 | 557 | EX | INSTALL 20' OF 4"PMMP MAIN | 2020-06-05 | 418 MACADAM DR | A | 6050.3807 | 3890.43 | -2159.9507 | -36% | 70 | 10 | 389.043 | FOR 5MINS TEST OK. SOAP TESTED EFC AT OP.TEST OK. TESTED S/L FOR 418 FROM MAIN TO MTR FOR 5MINS AT 90LBS TEST OK. REMOVED BYPASS AND GAUGES. INSTALLED END CAPS ON TEES. SOAP TESTED CAPS AT OP. NGF. BHB NGF INSTALLED 8' SECTION OF 040 WHILE ON MAIN ON BYPASS.TESTED MAIN FOR 20MINS AT 90LBS TEST OK.TEST BYPASS AND TEES FOR 1HR AT 90LBS TEST OK. TESTED VERF -ICATION TEES FOR 5MINS AT 90LBS TEST OK. TESTED PURGE TEE/ SCV TEE AT 90LB
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026953400 | 558 | EX | RETIRE 20' OF 4"PAMP MAIN | 2020-06-05 | 418 MACADAM DR | A | 65.2687 | 155.37 | 90.1013 | 138% |  |  | 0 | SOCKET COUPLING ON ADYL-A TEE LEAKING. REPLACED 8' SECTION OF MAIN AND TEE FOR S/L TO 418. WHILE ON BYPASS. ALL TESTING TIMES AND COMMENTS ON JO-20026953300. KKINDER
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026953500 | 557 | EX | INSTALL 20' OF 2"PMIP MAIN | 2020-06-05 | 3212 TATES CREEK RD | A | 4692.5356 | 2688.06 | -2004.4756 | -43% | 20 | 7 | 384.0086
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026953600 | 558 | EX | RETIRE 10' OF 2"PAIP MAIN | 2020-06-05 | 3212 TATES CREEK RD | A | 65.2687 | 657.25 | 591.9813 | 907% |  |  | 0
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 20026954200 | 559 | EX | INSTALL 825' OF 4" PMMP MAIN | 2020-11-04 | 2931 GEORGETOWN RD | B | 96092.6837 | 85457.14 | -10635.5437 | -11% | 827 | 728 | 117.3862
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 20026954300 | 560 | EX | RETIRE 940'-6"BSMP MAIN | 2020-11-12 | 2931 GEORGETOWN RD | B | 90.1729 | 1399.48 | 1309.3071 | 1,452% |  |  | 0 | DELETED PAY FOR WLD & RIG - MN/SVCS 5 MAN CREW CONTROL #165608 PAID ON WRONG JOB ORDER
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026955100 | 555 | EX | INSTALL 400'-4" PMMP | 2020-09-17 | 4925 KEENE RD F | B | 36445.6461 | 19268.03 | -17177.6161 | -47% | 400 | 371 | 51.9354
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026955200 | 555 | EX | INSTALL 1850' OF 2"/4"PMMP | 2020-09-16 | 2600 SANDERSVILLE RD LTCLUBH | B | 88356.8591 | 136599.49 | 48242.6309 | 55% | 1850 | 2020 | 67.6235 | TWALKER/KY 09-16-2020: I TRIED TO REVISE JOB DUE TO ROCK ENCOUNTERED DURING CONSTRUCTION BUT WMS WOULD NOT ALLOW ME TO REVISE DUE TO UNPAID INVOICES. I EXPECT CONTRACT COST TO INCREASE BY $50000 TWALKER/KY 06-14-21: JOB OVER RUN DUE TO ROCK (OPEN CUT AND DIRECT BORE) DURING CONSTRUCTION WITH INCREASE CONTRACT COST BY $50,000 AND SEGA WAS $5000 HIGHER THAN ESTIMATE.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026955300 | 555 | EX | INSTALL 3700' OF 2"/4"PMMP | 2020-08-03 | HOLLYHOCK DR 291 | B | 100593.9609 | 113734.73 | 13140.7691 | 13% | 3700 | 3871 | 29.3812 | PAID MISC DOLLARS AND CENTS FOR PORTABLE TOILET $117.49 CONTROL# 166019 10/02/2020
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026955503 | 561 | EX | INSTALL 2850'-8" CSHP | 2021-11-30 | CLAYS MILL RD | B | 1308080.823 | 1263938.35 | -44142.473 | -3% | 2960 | 2894 | 436.7444
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 20026955600 | 562 | EX | RETIRE 6100'-8"/3" BS/CSHP | 2021-11-30 | CLAYS MILL RD | B | 190.2592 | 142.7 | -47.5592 | -25% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026955701 | 561 | EX | INSTALL 3,945'-4"/2" PMMP | 2021-05-07 | CLAYS MILL RD | B | 724040.648 | 702217.99 | -21822.658 | -3% | 3945 | 3942 | 178.1375
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 20026955800 | 562 | EX | RETIRE 216'-2" PMMP | 2021-12-17 | CLAYS MILL RD | B | 85.5775 | 0 | -85.5775 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026955901 | 561 | EX | INSTALL 215'-4" PMMP | 2021-09-24 | CLAYS MILL RD | B | 67929.8606 | 63490.92 | -4438.9406 | -7% | 215 | 309 | 205.4722
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 20026956000 | 562 | EX | RETIRE 820'-2" PMMP | 2021-09-29 | CLAYS MILL RD | B | 85.0089 | 0 | -85.0089 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026956101 | 561 | EX | INSTALL 2475'-8"/6"/4" PMLP | 2021-10-04 | CLAYS MILL RD | B | 1170137.3307 | 1344804.09 | 174666.7593 | 15% | 2383 | 2469 | 544.6756 | WIPE SAMPLE RESULTS WERE ENTERED ON THE INSTALL JOB INSTEAD OF THE RETIREMENT JOB. RETIREMENT RESULTS WERE ENTERED HERE.
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 20026956200 | 562 | EX | RETIRE 4775'-12">3"PM/BS/CSLP | 2021-12-20 | CLAYS MILL RD | B | 85.5775 | 160 | 74.4225 | 87% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026956400 | 555 | EX | INSTALL 3000' OF 2"PMMP MAIN | 2020-07-30 | BARLEYS PASS | B | 83398.4788 | 87524.3 | 4125.8212 | 5% | 3000 | 3096 | 28.2701
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026956901 | 561 | EX | INSTALL 20'-6" PMMP | 2020-09-11 | 517 W MAIN ST | B | 42614.3064 | 32666.72 | -9947.5864 | -23% | 26 | 26 | 1256.4123
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026957000 | 562 | EX | RETIRE 20'-6" PMMP | 2020-09-11 | 517 W MAIN ST | B | 86.5808 | 142.7 | 56.1192 | 65% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026957100 | 557 | EX | INSTALL 5'-2" PMMP | 2020-06-22 | 4825 CHELMSBURY LN | A | 3193.011 | 3311.4 | 118.389 | 4% | 5 | 5 | 662.28 | INSTALLED NEW PEICE OF MAIN TEST 90 LB FOR 20 MIN FOL ON SITE PURGED OUT SOAP TEST FINAL TIE IN AT OP BAR HOLE BANKS NO GAS FOUND
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026957200 | 558 | EX | RETIRE 5'-2" PMMP | 2020-06-22 | 4825 CHELMSBURY LN | A | 86.6677 | 51.39 | -35.2777 | -41% |  |  | 0 | SQUEESZED OFF PURGED OUT MAIN AND CUT OUT DAMAGED PEICE OF MAIN
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026957400 | 557 | EX | INSTALL 5'-2" PMMP | 2020-06-22 | 227 TAHOMA RD | A | 3933.3497 | 1195.21 | -2738.1397 | -70% | 5 | 5 | 239.042 | TEST 90LBS 20 MINS WITH AIR PER EMERGENCY LEAK/ENGINEERING RC
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026957500 | 558 | EX | RETIRE 5'-2" PMMP | 2020-06-22 | 227 TAHOMA RD | A | 54.6677 | 0 | -54.6677 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026958301 | 561 | EX | INSTALL 720'-6" PMLP | 2020-10-14 | PIN OAK ST | B | 282646.1716 | 306190.36 | 23544.1884 | 8% | 735 | 714 | 428.838
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026958400 | 562 | EX | RETIRE 1880'-4" BSLP | 2020-12-16 | ROSEMONT GARDEN | B | 89.545 | 12409.8 | 12320.255 | 13,759% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026958500 | 2000 | EX | SURVEY AND INVESTIGATE | 2020-09-18 | ROSEMONT GN |  | 11138 | 0 | -11138 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026958800 | 566 | EX | RETIRE 3" SERVICE LINE | 2020-08-06 | 414 KENILWORTH CT | B | 83.7905 | 28.33 | -55.4605 | -66% |  |  | 0
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 20026958900 | 2000 | EX | ASSESS RD R/W & ESMTS FOR EXTN | 2020-09-14 | CLARK'S PUMP-N-SHOP |  | 4825 | 0 | -4825 | 100% |  |  | 0 | 14SEP20: COMPLETED AND CHARGED-OFF TO 20-0269663-00 (BKSLONE)
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026959100 | 561 | EX | INSTALL 200'-2" PMMP | 2020-10-27 | SOUTHPORT ST | B | 41735.7329 | 28435.3 | -13300.4329 | -32% | 200 | 224 | 126.9433
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026959400 | 557 | EX | INSTALL 5'-4" PMMP | 2020-07-03 | DOUGLAS | A | 5950.5246 | 11784.98 | 5834.4554 | 98% | 5 | 5 | 2356.996
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026959500 | 558 | EX | RETIRE 5'-4" PMP | 2020-07-03 | DOUGLAS | A | 86.6677 | 0 | -86.6677 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026959600 | 555 | EX | INSTALL 800' OF 2"PMIP MAIN | 2020-08-07 | WINNERS CR LT17 | B | 33356.3922 | 14955.41 | -18400.9822 | -55% | 800 | 615 | 24.3177
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026960000 | 557 | EX | INSTALL 5'-2" PMMP | 2020-07-06 | LAFAYETTE | A | 5425.135 | 154.14 | -5270.995 | -97% | 1 | 5 | 30.828 | INSTALLED 5 FT OF 2 IN MAIN TEST 90 LB FOR 20 MIN SOAP TEST FINAL TIE IN AT OP FOR 5 MIN BAR HOLE BANKS NO GAS FOUND GAUGED OFF OF METER SET
KY | KY - WEST | 2621 | U131983 |  |  |  | 20026960100 | 558 | EX | RETIRE 5'-2" PMMP | 2020-07-06 | LAFAYETTE | A | 83.7517 | 128.91 | 45.1583 | 54% |  |  | 0 | REMOVED 5 FT OF MAIN THAT WS DAMGED BY SEWER CREW
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026960200 | 557 | EX | INSTALL 5' OF 4"PMMP MAIN | 2020-07-13 | 3290 PEPPERHILL RD | B | 7137.1177 | 286.98 | -6850.1377 | -96% | 5 | 3 | 95.66
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026960300 | 558 | EX | RETIRE 5' OF 4"PMIP MAIN | 2020-07-13 | 3290 PEPPERHILL RD | B | 85.2291 | 449.43 | 364.2009 | 427% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026960400 | 562 | EX | RETIRE 220' OF 2"PMMP MAIN | 2020-07-13 | 901 OLD TODDS RD | A | 3110.3137 | 3219.21 | 108.8963 | 4% |  |  | 0 | ABDN MAIN GOING DOEN TODS RD THAT WAS A DEAD END WHERE THE ARE DOING SEWER AND SIDEWALK PROJECT
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026960800 | 558 | EX | RETIRE 5' OF 4"BSLP MAIN | 2020-07-21 | 704 E EUCLID AV | A | 2695.0511 | 1480.2 | -1214.8511 | -45% |  |  | 0 | RETIRED 5 FT OF MAIN SOAP TEST END CAP AND PAC CLAMPS AT OP FOR 5 MIN INSTALLED 1 ANODE BAR HOLE BANKS NO GAS FOUND
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026961700 | 2000 | EX | ACQUIRE EASEMENT FOR HP MAIN | 2021-01-22 | 2001 LAKESIDE DR | A | 5928 | 0 | -5928 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026961800 | 566 | EX | RETIRE 4" SERVICE LINE | 2020-10-28 | 1247 VERSAILLES RD | B | 133.2599 | 516.33 | 383.0701 | 287% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026961900 | 583 | EX | REPLACE REGULATORS | 2020-07-27 | 3210 LEESTOWN RD | F | 2574.9763 | 20141.23 | 17566.2537 | 682% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026962000 | 584 | EX | RETIRE REGULATORS | 2020-07-27 | 3210 LEESTOWN RD | F | 86.5808 | 0 | -86.5808 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026963300 | 559 | EX | INSTALL 30' OF 4"PMMP MAIN | 2020-10-27 | 2171 CHRISTIAN DR | B | 43056.4342 | 37006.62 | -6049.8142 | -14% | 30 | 44 | 841.0595
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026963400 | 560 | EX | RETIRE 30' OF 6"BSMP MAIN | 2020-10-27 | 2171 CHRISTIAN DR | B | 82.3372 | 71.35 | -10.9872 | -13% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026964800 | 557 | EX | INSTALL 5' OF 2"PMMP MAIN | 2020-08-04 | 777 NEWTOWN SP | A | 3448.1587 | 2052.61 | -1395.5487 | -40% | 5 | 5 | 410.522
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026964900 | 558 | EX | RETIRE 5' OF 2"PMMP MAIN | 2020-08-04 | 777 NEWTOWN SP | A | 82.3372 | 0 | -82.3372 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026965900 | 566 | EX | RETIRE 4" BSLP SERVICE LINE | 2020-08-25 | 163 N UPPER ST | B | 49.5082 | 0 | -49.5082 | 100% |  |  | 0 | CLOSED VALVE AND INSTALLED 4" CAP DOWNSTREAM OF VALVE. VALVE TO BE RETIRED WITH JOB # 19-0269153-00. JOSH PASLEY 8/28/20
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026966000 | 565 | EX | INSTALL 40' OF 4"PMLP S/L | 2020-08-25 | 163 N UPPER ST | B | 12842.5992 | 21255.78 | 8413.1808 | 66% | 40 |  | 0 | 6' OF 6" STEEL CASING USED
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026966100 | 557 | EX | INSTALL 12" FITTING | 2020-08-17 | ALUMNI DR | B | 20319.9407 | 112651.7 | 92331.7593 | 454% |  | 226 | 498.4588 | LEVEL 2 BUDGET VARIANCE EXPLANATION LOADED INTO WMSDOCS. 3/22/2021 D. LEMON S
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026966200 | 558 | EX | RETIRE 31'-12" BSHP | 2020-08-17 | ALUMNI DR | B | 86.5808 | 142.7 | 56.1192 | 65% |  |  | 0
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 20026966300 | 561 | EX | INSTALL 200'-2" PMMP | 2020-10-23 | CLARK'S PUMP-N-SHOP | B | 29254.458 | 29693.76 | 439.302 | 2% | 200 | 199 | 149.2149
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026966400 | 566 | EX | RETIRE 4" S/L WITH AMRP | 2020-08-19 | 201 W SHORT ST | B | 195.2037 | 5554.7 | 5359.4963 | 2,746% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026966701 | 557 | EX | INSTALL 3740' OF 2/4"PMMP MAIN | 2020-12-09 | MARIEMONT DR | B | 367967.1067 | 381730.14 | 13763.0333 | 4% | 3740 | 3719 | 102.6432
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026966800 | 558 | EX | RETIRE 2800' OF 4"/6"BSLP MAIN | 2021-02-03 | MARIEMONT DR | B | 90.1729 | 907.78 | 817.6071 | 907% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026967300 | 566 | EX | RETIRE SERVICE LINE | 2020-08-17 | 120 W 2ND ST | B | 53.1365 | 0 | -53.1365 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026967400 | 565 | EX | INSTALL 4" SERVICE LINE | 2020-08-17 | 120 W 2ND ST | B | 4582.3101 | 4192.45 | -389.8601 | -9% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026968000 | 557 | EX | INSTALL 10' OF 3"PMMP MAIN | 2020-09-14 | THAMES DR | B | 28353.826 | 22049.86 | -6303.966 | -22% | 10 | 24 | 918.7442
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026968100 | 558 | EX | RETIRE 10' OF 3"CSMP MAIN | 2020-09-14 | THAMES DR | B | 90.1729 | 0 | -90.1729 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026969200 | 555 | EX | INSTALL 490' OF 4"PMIP MAIN | 2020-10-02 | 953 TURKEYFOOT RD | B | 34319.2429 | 43812.04 | 9492.7971 | 28% | 490 | 530 | 82.6642
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026969700 | 555 | EX | INSTALL 8500' OF 2"/4"PMMP MN | 2021-01-04 | 299 SQUIRES CR | B | 301857.4038 | 270941.08 | -30916.3238 | -10% | 8500 | 6995 | 38.7335
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026970300 | 558 | EX | RETIRE 95' OF 2"BSLP MAIN | 2020-08-26 | 24 MENTELLE PR | A | 4389.6696 | 2131.99 | -2257.6796 | -51% |  |  | 0 | ABANDONED 020 MAIN 12FT FROM TIE IN. MAIN UNDER APRON LEAKING. PROPERLY ABANDONED WITH BAGGING.. INSTALLED END CAP SOAP TESTED AT OP NGF. BHB NGF. INSTALLED 9LB ANODE DENSO WRAPPED.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026970600 | 557 | EX | INSTALL 5' OF 4"PMLP MAIN | 2020-08-21 | UPPER ST | A | 5549.8956 | 2233.47 | -3316.4256 | -60% | 5 | 5 | 446.694
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026970700 | 558 | EX | RETIRE 5' OF 4"PLP MAIN | 2020-08-21 | UPPER | A | 87.1365 | 0 | -87.1365 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026971000 | 566 | EX | RETIRE 3"LP SERVICE LINE | 2020-10-21 | 100 MIDLAND AV | B | 179.8275 | 0 | -179.8275 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026971100 | 557 | EX | INSTALL 3300' OF 2"/4"PMMP MN | 2021-07-23 | 167 WITTLAND LN | B | 877421.2279 | 755817.87 | -121603.3579 | -14% | 3300 | 3399 | 222.3648 | TWALKER/KY 05-04-22: JOB ORDER RUN DUE TO NO PAVING/HARD SURFACE REPAIRS HA VE BEEN STARTED AT THIS TIME. THIS IS JOINT PAVING RESTORATION WITH CITY OF LEXINGTON AND KY AMERICAN WATER. LOOK FOR COST TO BOOK LATE SUMMER 2022
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026971200 | 558 | EX | RETIRE 2100' OF 3"BSLP MAIN | 2022-03-16 | 167 WITTLAND LN | B | 102.0836 | 1415.61 | 1313.5264 | 1,287% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026971300 | 555 | EX | INSTALL 1900' OF 2"PMMP MAIN | 2020-11-12 | FOUNTAINBLUE LN | B | 60260.4679 | 69558.89 | 9298.4221 | 15% | 1900 | 1850 | 37.5994
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026972201 | 555 | EX | INSTALL 3300' OF 2"/4" PMMP | 2021-11-04 | MEADOW RIDGE DR LT1 | B | 89953.3001 | 84926.85 | -5026.4501 | -6% | 3300 | 3160 | 26.8756
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026972300 | 566 | EX | RETIRE SERVICE | 2020-08-17 | 1740 NICHOLASVILLE RD | B | 94.7274 | 0 | -94.7274 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026972400 | 565 | EX | INSTALL SERVICE | 2020-08-17 | 1740 NICHOLASVILLE RD | B | 10176.4932 | 1795.03 | -8381.4632 | -82% | 22 |  | 0 | OLD SERVICE WAS ALSO 2"; PORTION OF SERVICE AND VALVE REPLACED WITH THIS JO AND ASSOC 566
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026974800 | 561 | EX | INSTALL 15' OF 6"PMLP MAIN | 2020-09-23 | ROSE ST | B | 12246.4323 | 8893.63 | -3352.8023 | -27% | 15 | 23 | 386.6796
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026974900 | 562 | EX | RETIRE 15' OF 6"PMLP MAIN | 2020-09-23 | ROSE ST | B | 78.9269 | 142.7 | 63.7731 | 81% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026975201 | 557 | EX | INSTALL 3000' OF 2"/4"PMMP | 2021-04-12 | MANHATTAN DR | B | 552556.8312 | 630664.21 | 78107.3788 | 14% | 3000 | 3052 | 206.6396
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026975300 | 558 | EX | RETIRE 1900' OF 6"BSLP MAIN | 2021-06-11 | MANHATTAN DR | B | 64.0836 | 1430.35 | 1366.2664 | 2,132% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026976301 | 557 | EX | INSTALL 6300' OF 2"/4"PMMP | 2021-09-29 | CHENAULT RD | B | 2132943.4537 | 2104702.57 | -28240.8837 | -1% | 6000 | 6294 | 334.3982
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026976400 | 558 | EX | RETIRE 6100' OF 3"/4"BSLP MN | 2021-12-14 | CHENAULT RD | B | 152.7248 | 1794.07 | 1641.3452 | 1,075% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026976501 | 557 | EX | INSTALL 4270' OF 2"/4"PMMP MN | 2022-08-05 | E 6TH ST | B | 1522347.7868 | 1937333.59 | 414985.8032 | 27% | 4280 | 4323 | 448.1456 | WIPE SAMPLE RESULTS WERE ENTERED ON THE INSTALL JOB IN ERROR. WIPE RESULTS FOR THE RETIREMENT PIPE WERE ENTERED HERE. TWALKER/KY 01-24-23: JOB OVER RUN DUE TO ADDITIONAL STREET/HARD SURFACE REP AIRS REQUIRED BY CITY OF LEXINGTON. CONTRACT COST INCREASED BY $200,000 WITH PAVING/FLAGGING COST, SEGA WAS $73,000 HIGHER THAN PLANNED, ADDITIONAL $22,000 CHARGED FOR MATERIAL COST. TWALKER/KY 08-29-23: LEVEL 2 VARIANCE ADDED TO WMS.DOCS. JOB COST OVERRUN DUE TO ADDITIONAL STREET MILL/RE-PAVED COST REQUIRED BY CITY OF LEXINGTON.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026976600 | 558 | EX | RETIRE 4650' OF 3"/4"BSLP MN | 2022-08-05 | E 6TH ST | B | 56.8875 | 320 | 263.1125 | 463% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026976700 | 557 | EX | INSTALL 5'-2" PMMP | 2020-09-24 | GEORGETOWN | A | 2239.0606 | 0 | -2239.0606 | 100% | 5 | 5 | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026976800 | 558 | EX | RETIRE 5'-2" PMMP | 2020-09-24 | GEORGETOWN | A | 80.4114 | 0 | -80.4114 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026977101 | 557 | EX | INSTALL 11,500' OF 2"/4"PMMP | 2021-07-13 | TREMONT AV | B | 926814.1047 | 1143604.07 | 216789.9653 | 23% | 11500 | 11391 | 100.3954 | TWALKER/KY 03-02-22: PROJECT COST OVER RUN DUE TO ADDITIONAL CONSTRUCTION COORINATOR ON SITE DURING CONSTRUCTION ADDED $65,000 IN LABOR COST, SEWER VIDEO FOR MAIN/SL BY BUCHANAN WAS $86,000 HIGHER THAN ESTIMATE, ADDITIONAL FLAGGING AND HARD SURFACE REPAIRS ADDED $25,000 TO CONTRACT COST. FINALLY SEGA WAS $35,000 HIGHER THAT PLANNED COST.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026977200 | 558 | EX | RETIRE 6900' OF 4"/6"BSLP MAIN | 2021-12-14 | TREMONT AV | B | 76.6277 | 848.1 | 771.4723 | 1,007% |  |  | 0
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026977900 | 557 | EX | INSTALL 10' - 2" PMMP | 2020-09-29 | OUR TIBBS TR | A | 4498.8377 | 228.49 | -4270.3477 | -95% | 10 | 9 | 25.3878
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026978000 | 558 | EX | RETIRE 10' - 2" PMMP | 2020-09-29 | OUR TIBBS TR | A | 75.9579 | 0 | -75.9579 | 100% |  |  | 0
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026978500 | 561 | EX | INSTALL 15' - 2" PMMP | 2020-10-09 | RED CLOVER LN | B | 10711.935 | 5965.56 | -4746.375 | -44% | 15 | 8 | 745.695
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026978600 | 562 | EX | RETIRE 10' - 2" PMMP | 2020-10-09 | RED CLOVER LN | B | 75.9579 | 0 | -75.9579 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026979800 | 559 | EX | INSTALL 5'-2" PMMP | 2020-10-07 | 3621 AMICK WY | A | 4118.0606 | 866.05 | -3252.0106 | -79% | 5 | 2 | 433.025
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026979900 | 560 | EX | RETIRE 5'-2" PMMP | 2020-10-07 | 3621 AMICK WY | A | 80.4114 | 0 | -80.4114 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026981200 | 557 | EX | INSTALL 1550' OF 2"PMMP MAIN | 2021-08-10 | M L KING | B | 414073.7744 | 479750.56 | 65676.7856 | 16% | 1550 | 1372 | 349.6724 | TWALKER/KY 05-04-22: JOB OVER RUN CAUSED BY ADDTIONAL $46,000 FOR SEWER CAMERA WORK, PROJECT TOOK LONGER TO COMPLETE DUE TO TRAFFIC AND URBAN SETTING INCREASED COMPANY LABOR BY $5000, SEGA $17000 HIGHER THAN ESTIMATE.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026981300 | 558 | EX | RETIRE 1600' OF 2"/3"BSLP MAIN | 2021-09-23 | M L KING | B | 84.1799 | 0 | -84.1799 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026981400 | 566 | EX | RETIRE 3" SERVICE-CAT2 | 2020-10-20 | 800 WINCHESTER RD | A | 81.035 | 0 | -81.035 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026982600 | 2000 | EX | INVESTIGATE AND DESIGN | 2021-08-19 | BLUEGRASS AV |  | 30898 | 0 | -30898 | 100% |  |  | 0 | PS&I IS STILL BEING USED BY CONTRACT SURVEYOR AND ENGINEER DURING CONSTRUCT ION. BUT PRELIMINARY DESIGN AND SURVEY COMPLETED. D.LEMONS 8/19/2021
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026982700 | 561 | EX | INSTALL 4500'-2"&4" PMMP | 2022-02-01 | BLUEGRASS AV | B | 959444.7901 | 885948.31 | -73496.4801 | -8% | 4471 | 4196 | 211.1412
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026982900 | 562 | EX | RETIRE 3700'-2&4" BSLP | 2022-03-10 | BLUEGRASS AV | B | 88.8156 | 142.7 | 53.8844 | 61% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026984100 | 2000 | EX | INVESTIGATE R/W & EASEMENTS | 2021-02-25 | GEORGETOWN PY |  | 3406 | 0 | -3406 | 100% |  |  | 0
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 20026984400 | 561 | EX | INSTALL 949'-6" PMLP | 2021-03-10 | LAFAYETTE PY | B | 204292.6769 | 282788.29 | 78495.6131 | 38% | 939 | 954 | 296.4238 | 14JUN21: OVERRRUN EXPLANATION = 1) REQUIRED FLAGGING WAS WAY UNDERESTIMATED AS $30K ADDITIONAL DOLLARS FOR FLAGGING WAS REQUIRED, 2) AN ADDITIONAL $10K IN DUST & STONE WAS REQUIRED, 3) THE 6" ROCK BORE WAS PAID ALL IN HEAVY ROCK WHEREAS IT WAS ESTIMATED 1/2 HEAVY AND 1/2 LIGHT WHICH CONTRIBUTED ANOTHER $8K TO THE OVERRUN,4) ADDITIONAL VAC EXCAVATION WAS REQUIRED ADDING $3K TO THE OVERRUN. THESE PLUS ADDITIONAL OH'S MAKE UP THE MAJORITY OF THE $57K OVERRUN (BKSLONE)
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026984700 | 560 | EX | ABANDON 1763'-2" PIP | 2020-12-10 | 1081 E NEW CIRCLE RD | A | 17220.804 | 32029.01 | 14808.206 | 86% | 7 |  | 0 | WORKED WITH CREWS TO EXPOSE MAINS & SERVICES VIA HYDRO EXCAVATION; WILL RETURN FOR FUTHER WORK; IN PROGRESS ASSIST WITH MAIN ABANDONMENT & SERVICE ABANDON ASSISTED WITH FINAL ABANDONMENTS FOR THE PROJECT; EXPOSED VIA HYDRO EXCAVATION; ABDN ALL MAIN AND SL THAT WAS DISCUSSED TO ALL GAS STANDARDS SEALED ENDS OF ALL ABDN LINES THAT WAS SEPERATED
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026985200 | 561 | EX | INSTALL 6" PCF | 2021-06-12 | 1060 WINBURN DR | B | 16280.811 | 9877.17 | -6403.641 | -39% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026985300 | 562 | EX | RETIRE 300'-6" CSMP | 2021-06-12 | 1060 WINBURN DR | B | 88.4533 | 71.35 | -17.1033 | -19% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026985600 | 561 | EX | INSTALL 375' OF 2"CSHP MAIN | 2021-12-21 | KING ST | B | 92169.2028 | 90203.73 | -1965.4728 | -2% | 375 | 401 | 224.947
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026985700 | 562 | EX | RETIRE 200' OF 2"CSHP MAIN | 2021-12-21 | KING ST | B | 84.1794 | 62.95 | -21.2294 | -25% |  |  | 0
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026986500 | 585 | EX | INSTALL FENCE AT R-1143 | 2020-12-02 | 1800 MASON HEADLEY RD | F | 7073.5793 | 12363.62 | 5290.0407 | 75% |  |  | 0
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026986600 | 586 | EX | RETIRE FENCE AT R-1143 | 2020-12-02 | 1800 MASON HEADLEY RD | F | 56.6075 | 1332.62 | 1276.0125 | 2,254% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026987200 | 557 | EX | EMER-INSTALL 8' OF 2"PMMP MAIN | 2020-11-17 | 3372 GRASMERE DR | A | 4618.1073 | 3016.93 | -1601.1773 | -35% | 6 | 8 | 377.1162 | ABANDONED SECTION OF MAIN-LEFT BYPASS AS NEW MAIN PER ENGINEERING AND TIE IN PLAN-BHBNGF-ALL READINGS GONE-COMPLETED JOB TO TIE IN PLAN-PRESS. TEST NEW MAIN @90LBS FOR 1HR SEE TESTPRESS. FORM-13PSI VERIFIED-ANICHOLS11-17-20
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026987300 | 558 | EX | RETIRE 4' OF 3"PAMP MAIN | 2020-11-17 | 3372 GRASMERE DR | A | 81.035 | 1238.33 | 1157.295 | 1,428% |  |  | 0 | ABANDONED SECTION OF MAIN-LEFT BYPASS AS NEW MAIN PER ENGINEERING AND TIE IN PLAN-BHBNGF-ALL READINGS GONE-COMPLETED JOB TO TIE IN PLAN-PRESS. TEST NEW MAIN@ 90LBS FOR 1HR SEE TESTPRESS.FORM-13PSI VERIFIED-ANICHOLS 11-17-20
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026987500 | 555 | EX | INSTALL 300' OF 2"PMMP MAIN | 2021-03-09 | 7020 ATHENS BOONESB RD | B | 19258.6597 | 18181.58 | -1077.0797 | -6% | 300 | 304 | 59.8078
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026988100 | 555 | EX | INSTALL 525' OF 2"PMMP MAIN | 2021-01-08 | BOBWHITE CT LT1 | B | 17405.4965 | 10228.67 | -7176.8265 | -41% | 525 | 501 | 20.4165
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026988300 | 562 | EX | RETIRE 1853'-4"/3" BS/CSMP | 2021-12-16 | CLAYS MILL RD | B | 5110.2031 | 47.8 | -5062.4031 | -99% |  |  | 0
KY | KY - WEST | 2621 | U124399 | Bishop,Steven | Gill,John | Dunn,David | 20026989100 | 583 | EX | PM INSTALL REG PMF (FAC ONLY) | 2020-10-09 | 2350 FORTUNE DR | F | 0 | 2795.05 | 2795.05 | 100% |  |  | 0 | THIS JOB WAS CREATED AND USED ONLY FOR FACILITY CREATION ALL WORK WAS PERFORMED ON 583 JOB ORDER 19-0269155-00 CFARIS
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026989300 | 557 | EX | EMRG - INSTALL 5'-4"PMLP MAIN | 2020-12-02 | 369 SHERMAN AV | A | 5551.8207 | 2958.08 | -2593.7407 | -47% | 5 | 3 | 986.0267 | INSTALLED END CAPS ON 3 TEE'S. SOAP TEST CAPS AT OP. TEST OK. BHB NGF. CHARGE TIME FROM 2412 TO 557 AND 558. KKINDER INSTALLED 2 VERFICATION GAUGES.SQUEEZED OFF 2 WAY FED MAIN IN SEPRATE BELLHOLES. REPLACED DAMAGED SECTION OF PIPE. SOAP TEST 2 EFC'S AT OP TEST OK.PURGED OUT MAIN WITH PURGE STACK CONNECTED TO PURGE TEE ON MAIN.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026989400 | 558 | EX | EMRG - RETIRE 5' OF 4"PLP MAIN | 2020-12-02 | 369 SHERMAN AV | A | 73.5667 | 342.79 | 269.2233 | 366% |  |  | 0 | ABANDONED 2FT OF 040 LP MAIN DUE TO EXCAVATOR ERROR. INSTALLED NEW PIPE ON JO 20026989300
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026989600 | 561 | EX | INSTALL 40'-2" PMMP | 2021-01-15 | 1631 OLD FRANKFORT PK | B | 30326.4153 | 36919.96 | 6593.5447 | 22% | 44 | 52 | 709.9992
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026989700 | 562 | EX | RETIRE 40'-2" CSMP | 2021-01-15 | 1631 OLD FRANKFORT PK | B | 107.2796 | 0 | -107.2796 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026989900 | 557 | EX | EMRG - INSTALL 5'-2"PMMP MAIN | 2020-12-07 | 4348 STEAMBOAT RD | A | 4780.1273 | 2613.3 | -2166.8273 | -45% | 5 | 2 | 1306.65 | STACK. SOAP TEST EFC AT OP.TEST OK. SOAP TEST END CAP ON TEE AT OP. TEST OK. BHB NGF. ABOVE GROUND SQUEEZED OFF TO MAKE SAFE.INSTALLED VERFICATION GAUGE.TESTED TEE FOR 5MINS AT 90LBS.TEST OK. REPLACED 2' OF 020 DAMAGED MAIN.TESTED 020 PIPE FOR 20MINS AT 90LBS.TEST OK.PURGED MAIN AT EOM 112' AWAY WITH PURGE
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026990000 | 558 | EX | EMRG - RETIRE 5'-2"PMMP MAIN | 2020-12-07 | 4348 STEAMBOAT RD | A | 73.5667 | 3.94 | -69.6267 | -95% |  |  | 0 | ABANDONED 2' OF 020 PLASTIC FROM HIT MAIN. WORKED WITH 557
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026990200 | 2000 | EX | RELOCATION DESIGN - CONFLICT | 2021-08-24 | KING ST | B | 6690 | 0 | -6690 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026990300 | 560 | EX | RETIRE 20' OF 4"BSLP MAIN | 2020-12-15 | 600 MONTCLAIR DR | A | 3506.58 | 2733.31 | -773.27 | -22% |  |  | 0 | CUT AND CAPPED 4" BS/LP MAIN ACCORDING TO TIE IN PLAN. INSTALLED ANODE. INSTALLED MARKER BALL OVER DEAD END CAP. SOAP TEST ON DEAD END CAP OK. BHB. NGF. CWEMPE 12/15/20
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026990400 | 558 | EX | PAPER ONLY FOR CLOSE OUT | 2020-11-02 | BUCOTO CT | B | 100.3516 | 0 | -100.3516 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026990600 | 558 | EX | PAPER ONLY FOR CLOSE OUT | 2021-01-21 | WALTON AV | B | 103.8156 | 0 | -103.8156 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026991100 | 563 | EX | INSTALL 100' OF 4"PMLP S/L | 2021-01-08 | 1003 N LIMESTONE ST | B | 29024.9725 | 33764.98 | 4740.0075 | 16% | 101 |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026991900 | 2000 | EX | INVESTIGATE ROAD RIGHT OF WAY | 2021-01-13 | 1751 BRYAN STATION RD | A | 3224 | 0 | -3224 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026992300 | 557 | EX | EMRG - INSTALL 5' OF 3"PMMP | 2020-12-23 | 2275 NICHOLASVILLE RD | A | 38582.9134 | 39401.13 | 818.2166 | 2% | 5 | 8 | 4925.1412 | EXPOSED LEAKING PAC CLAMP OVER OLD SVC TEE. CUT OUT REPLACED 7.75' OF 3" P MP MAIN PER GAS STANDARDS AND TIE-IN PLAN. BHB NGF. MCRAIG 12/28/20
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026992400 | 558 | EX | EMRG - RETIRE 5' OF 3"PMP MAIN | 2020-12-23 | 2275 NICHOLASVILLE RD | A | 102.0836 | 3619.31 | 3517.2264 | 3,445% |  |  | 0 | WORKED W/ 557 JOB# 20026992300 MCRAIG 12/28/20
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026992700 | 557 | EX | EMER-INSTALL 5'-4" PMMP | 2020-12-22 | RIDGEPOINT | A | 12865.6489 | 2839.86 | -10025.7889 | -78% | 30 | 5 | 567.972 | IDENTIFIED A LEAKING BUTT WELD ON MAIN LINE. REPLACED SECTION OF MAIN LINE THAT WAS LEAKING WITH A NEW PEICE OF MAIN. PRESSURE TESTED NEW PEICE OF MAIN @ 90PSIG FOR 1HR. TEST OK. BHB, NGF. VERIFIED CONTENT & PRESSURE
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026992800 | 558 | EX | EMER-RETIRE 5'-4" PMP | 2020-12-22 | RIDGEPOINT | A | 103.8156 | 94.74 | -9.0756 | -9% |  |  | 0 | IDENTIFIED A LEAKING BUTT WELD ON MAIN LINE. REPLACED SECTION OF MAIN LINE THAT WAS LEAKING WITH A NEW PEICE OF MAIN. PRESSURE TESTED NEW PEICE OF MAIN @ 90PSIG FOR 1HR. TEST OK. VERIFIED CONTENT AND PRESSURE. DMALONE
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 21026100800 | 575 | EX | ACQ GPL ESMT IN/OUT TO R-1035 | 2021-04-26 | 2211 CLAYS MILL RD | F | 6845 | 19245.71 | 12400.71 | 181% |  |  | 0 | CHRIS DAVIS ACQUIRED NECESSARY EASEMENTS OFF OF WELCH AND SAUNIER (BKSLONE)
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026100900 | 557 | EX | EMER INSTALL 5'-4" PMMP | 2021-02-04 | 600 OLD FRANKFORT CR | A | 15398.8131 | 49713.13 | 34314.3169 | 223% | 15 | 4 | 12428.2825 | RETIRED 4 FEET OF 4' PE MAIN LINE. REPLACED PEICE OF MAIN WITH NEW AND EF COUPLINGS. PRESSURE TESTED NEW PEICE OF MAIN FOR 1HR @ 90PSIG. TEST OK. SOAP TESTED FINALS CONNECTION @ OP. TEST, BHB, NGF. DMALONE 2/09/2021. OVERRUN EXPLANATION: UNEXPECTED CONTRACT COST OF $35,000 WAS NOT PLANNED, JO ORIGINALLY PLANNED FOR COMPANY CREW BUT WAS EXECUTED BY A CONTRACT CREW, COMPANY CREWS ALSO CHARGED 183 HOURS TO PROJECT
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026101000 | 558 | EX | EMER RETIRE 5'-4" PMP D222468 | 2021-02-04 | 600 OLD FRANKFORT CR | A | 69.6296 | 10.95 | -58.6796 | -84% |  |  | 0 | RETIRED 4 FEET OF 4' PE MAIN LINE. REPLACED PEICE OF MAIN WITH NEW AND EF COUPLINGS. PRESSURE TESTED NEW PEICE OF MAIN FOR 1HR @ 90PSIG. TEST OK. SOAP TESTED FINAL CONNECTION @ OP. TEST OK. BHB. NGF. DMALONE 2/09/2021 OVERRUN EXPLANATION: THIS RETIREMENT JOB ORDER WAS ESTIMATED IN THE ORDINAR Y MANNER FOR JUST 1 HOUR; HOWEVER, THERE WERE NO PROPERTY UNITS INSTALLED S O THE JOB WAS WORKED AS AN ABANDONMENT WITH ALL THE LABOR AND CONTRACT COST S BEING APPLIED TO THE RETIREMENT. THE INSTALL JOB ORDER WAS EXECUTED WITH AN HOUR OF LABOR.
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 21026101100 | 575 | EX | ACQ ESMT ON 556 ROSEMONT GDN | 2021-04-07 | 556 ROSEMONT GN | F | 5169 | 6675.64 | 1506.64 | 29% |  |  | 0 | 27APR21: CHRIS DAVIS COMPLETED AND ACQUIRED THREE SEPARATE EASEMENTS OFF OF ROSEMONT BAPTIST CHURCH.
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026101400 | 2000 | EX | INVESTIGATE MAINS | 2021-06-10 | WOODHILL DR |  | 17276 | 0 | -17276 | 100% |  |  | 0 | PS&I BEING EXECUTED TO CAPITOL JO. PROJECT EXPECTED TO START MID JULY 2021 . D.LEMONS 6/10/2021
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026101501 | 561 | EX | INSTALL 3800'-2",4"&6" PMMP | 2021-08-27 | WOODHILL DR | B | 710294.4849 | 842479.02 | 132184.5351 | 19% | 3957 | 4530 | 185.9777 | OVERRUN EXPLANATION: ENCOUNTERED MORE ROCK EXCAVATION THAN ESTIMATED AS WEL L AS THE ASSOCATED SPECIAL BACKFILL. PROJECT ALSO REQUIRED MORE SEWER CAMER A WORK THAN ESTIMATED.
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026101600 | 562 | EX | RETIRE 1200'-2"&4" BSMP | 2022-04-25 | WOODHILL DR | B | 85.0089 | 325.85 | 240.8411 | 283% |  |  | 0
KY | KY - WEST | 2621 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 21026102600 | 2000 | EX | INVESTIGATE ENCROACHMENT | 2023-08-08 | 375 STONE RD |  | 694 | 0 | -694 | 100% |  |  | 0
KY | KY - WEST | 2621 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 21026102800 | 2000 | EX | INVESTIGATE ENCROACMENT | 2023-08-08 | 1081 E NEW CIRCLE RD |  | 694 | 0 | -694 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026102900 | 555 | EX | INSTALL 2400' OF 4"PMMP MAIN | 2021-06-15 | 928 ENTERPRISE CT | B | 80646.5708 | 104251.17 | 23604.5992 | 29% | 2400 | 2371 | 43.9693
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026103700 | 2000 | EX | INVESTIGATE FACILITIES | 2021-03-11 | THUNDERSTICK DR |  | 6855 | 0 | -6855 | 100% |  |  | 0 | INVESTIGATION COMPLETED, AND NO DIRECT CONFLICT WITH PROPOSED SEWER FACILIT IES. HAVE REQUESTED TO BE INVITED TO ANY PRECONSTRUCTION MEETING TO TALK TO CONTRACTOR ABOUT INSTALATION PRACTICES. D.LEMONS 3/11/2021
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026104400 | 559 | EX | INSTALL 2"SS TO RETIRE INLET | 2021-05-12 | 1311 RICHMOND RD | B | 37406.9466 | 24511.65 | -12895.2966 | -34% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026104500 | 560 | EX | RETIRE 7' OF 2"BSMP MAIN | 2021-05-13 | 1311 RICHMOND RD | B | 80.8842 | 72.67 | -8.2142 | -10% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026104600 | 584 | EX | RETIRE PIT REG STATION 1016 | 2021-04-23 | 1311 RICHMOND RD | F | 138142.7376 | 188917.56 | 50774.8224 | 37% |  |  | 0 | REMOVED MONITOR AND CONTROL REG. AND BLIND FLANGED, MONITORED 30 MIN. DUE TO NOT BEING ABLE TO BLIND FLANGE BYPASS, ADVISED CONSTRUCTION ABOUT BYPASS CCC 20355 CMCHOLAN RHAYES NGINTER BLONE 4-23-2021 REGULATORS REMOVED AND BLIND FLANGED ON 4/23/2021 PIPING AND VAULT ABANDONED AND REMOVED BY CONSTRUCTION ON 5/12/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/14/2021 GCCC TICKET NOT REQUIRED ON 5/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS TWALKER/KY 11-15-21: LEVEL 2 VARIANCE FORM ADDED TO WMS.DOCS. JOB OVER RUN DUE TO $41,500 FROM LP/OPP MATERIAL CHARGED TO THIS ORDER. ADDITIONAL $11,000 IN COMPANY HIGHER THAN PLANNED ESTIMATE.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026105201 | 577 | EX | INSTALL CHAIN LINK FENCE | 2023-04-14 | BRIAR HILL RD | F | 78948.1342 | 84349.67 | 5401.5358 | 7% |  |  | 0 | FENCE INSTALL COMPLETE APARKS 04-19-23 1600 CCC#24962
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026105300 | 2000 | EX | INVESTIGATE EASEMENT | 2022-07-08 | 2397 RICHMOND RD | B | 1270 | 0 | -1270 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026105401 | 555 | EX | INSTALL 6520' OF 6"PMMP MAIN | 2021-12-15 | 2000 POLO CLUB BV | B | 403346.5487 | 421654.71 | 18308.1613 | 5% | 6325 | 6542 | 64.4535
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026105900 | 557 | EX | EMER INSTALL 5' OF 4"PMMP MAIN | 2021-02-25 | 916 BRAVINGTON WY | A | 24731.5705 | 12908.51 | -11823.0605 | -48% | 5 | 10 | 1290.851 | TWALKER/KY-04-20-21: I HAVE ADDED A SIGNED PRESSURE TEST TO APPROVE THE 20 MIN PRESSURE TEST TO WMS.DOCS WORKSPACE.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026106000 | 558 | EX | EMER RETIRE 5' OF 4"PAMP MAIN | 2021-02-25 | 916 BRAVINGTON WY | A | 82.208 | 0 | -82.208 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026106100 | 555 | EX | INSTALL 1350' OF 2"/4"PMMP | 2021-03-29 | PIERO WY LT1 | B | 45765.0925 | 39665.6 | -6099.4925 | -13% | 1350 | 1514 | 26.1992 | STANLEY PIPELNE INSTALLED MAIN
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026106200 | 559 | EX | INSTALL 6" PCF | 2021-04-12 | 1965 FAIR OAKS DR | B | 16594.9062 | 13429.76 | -3165.1462 | -19% |  |  | 0 | INSTALLED 6"SST
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026106300 | 560 | EX | RETIRE 575'-6" BSLP | 2021-04-12 | 1965 FAIR OAKS DR | B | 88.4533 | 1068.93 | 980.4767 | 1,108% |  |  | 0 | ABANDONED 640'060 CSLP
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 21026107700 | 557 | EX | INSTALL 20' OF 8"PMLP MAIN | 2021-04-13 | 856 ALBANY ST | A | 12704.2275 | 8482.5 | -4221.7275 | -33% | 20 | 36 | 235.625 | REPLACED 36' OF S LP MAON W/ 8" P PER TIE-IN PLAN AND GAS STANDARDS. SOAP TEST TIE-IN COUPLINGS NO LEAKS. BHB NGF. MAIN PTOS READ -0.482 INST 2 9LB ANODES.
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 21026107800 | 558 | EX | RETIRE 20' OF 8" BSLP | 2021-04-13 | 856 ALBANY ST | A | 56.3197 | 8727.02 | 8670.7003 | 15,395% |  |  | 0 | ABN 36' OF 8" S LP MAIN AND REPLACE WITH 8" P PER GAS STANDARDS AND TIE-IN PLAN. WORKED W/ 557 JOB# 21026107700. MCRAIG 4/14/21
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 21026107900 | 557 | EX | INSTALL 10' OF 3" PMLP | 2021-04-15 | 329 OHIO ST | A | 13301.2275 | 7671.47 | -5629.7575 | -42% | 10 | 23 | 333.5422 | ABANDONED 23' OF 030 S MAIN.DUE TO ATMOS CORR INSTALLED 23' OF 030 PLASTIC WORKED WITH TIE IN PLAN AND GAS STANDARD. BHB NGF. INSTALLED TWO TEST STATIONS AND TWO ANODED.DESNO WRAPPED STEEL MAIN.
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 21026108000 | 558 | EX | RETIRE 10' OF 3" BSLP | 2021-04-15 | 329 OHIO ST | A | 79.3197 | 8414.88 | 8335.5603 | 10,509% |  |  | 0 | ABANDONED 23' OF 030 S MAIN.DUE TO ATMOS CORR INSTALLED 23' OF 030 PLASTIC WORKED WITH TIE IN PLAN AND GAS STANDARD. BHB NGF. INSTALLED TWO TEST STATIONS AND TWO ANODED.DESNO WRAPPED STEEL MAIN.
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 21026108100 | 557 | EX | INSTALL 20' OF 3" PMMP | 2021-05-05 | 619 CHINOE RD | B | 21676.4521 | 70757.52 | 49081.0679 | 226% | 20 | 314 | 225.3424 | AWEBER/KY 09/21/2021: PROXIMITY OF LP MAIN TO MP MAIN RESULTED IN AN ACTUAL FOOTAGE INSTALL OF 320'-PMMP IN ORDER TO SEPERATE AND INSTALL FITTINGS AS NEEDED. UNABLE TO REVISE WMS JO DUE TO UNPAID MATERIAL INVOICES AND JO COMP LETION STATUS AT THE TIME.
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 21026108200 | 558 | EX | RETIRE 20' OF 3" BSMP | 2021-05-05 | 619 CHINOE RD | B | 56.3197 | 4.6 | -51.7197 | -92% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026108600 | 557 | EX | EMER-INSTAL 5'-2" PMMP | 2021-03-05 | 2434 SEINE | A | 5147.5997 | 116.02 | -5031.5797 | -98% | 5 | 5 | 23.204 | INSTALLED 5' OF TEST 2" PMMP, SOAP TEST TIE IN, NO LEAKS, BHB NGF TIE OVER 2 SERVICE LINES, ON 3-5-21 DMEDLEY 3-8-21
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026108700 | 558 | EX | EMER - RETIRE 5'-2" PAMP | 2021-03-05 | SEINE | A | 85.3307 | 4796.8 | 4711.4693 | 5,521% |  |  | 0 | INSTALLED GAUGE TEE, SQUEEZE OFF 2" PL MAIN, ABN 5' 2"PMP MAIN PER DLEMONS EMER DESIGN PLAN. WORKED ON 3-5-21, DMEDLEY 3-8-21
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026108801 | 555 | EX | INSTALL 1000' OF 2"PMMP MAIN | 2022-01-24 | 551 VINCENT WY | B | 46147.0126 | 51597.09 | 5450.0774 | 12% | 1000 | 847 | 60.9175
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 21026108900 | 575 | EX | ACQUIRE EASEMENT | 2021-04-07 | 796 DELLA DR | F | 6767 | 13632.99 | 6865.99 | 101% |  |  | 0 | CHRIS DAVIS ACQUIRED EASEMENT OFF OF 796 DELLA DR (KUBIAK)
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026109300 | 555 | EX | INSTALL 300' OF 2"PMMP MAIN | 2021-09-02 | 801 NANDINO BV | B | 25871.1277 | 26886.16 | 1015.0323 | 4% | 300 | 278 | 96.7128
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 21026109900 | 562 | EX | RETIRE 2155'-4"/3" BS/PMLP | 2021-04-07 | WOODBINE & REED | B | 343.31 | 3173.92 | 2830.61 | 825% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026110100 | 555 | EX | INSTALL 900' OF 2"PMMP MAIN | 2021-06-23 | LAFONTAINE CT | B | 26234.9875 | 24183.42 | -2051.5675 | -8% | 900 | 887 | 27.2643
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026110400 | 561 | EX | INSTALL 100'-12" CSMP | 2021-06-29 | 576 E THIRD ST | B | 142453.0552 | 188696.44 | 46243.3848 | 32% | 100 | 127 | 1485.7987 | OVERRUN EXPLANATION: PROJECT OVERRAN DUE TO FLAGGER TIME AND FLAGGER OVERTI ME. BUDGET VARIANCE EXPLANATION FORM LOADED INTO WMSDOCS WORKSPACE. D.LEMONS 12 /3/2021
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026110500 | 562 | EX | RETIRE 94'-12" CSMP | 2021-06-28 | 576 E THIRD ST | B | 85.5775 | 142.7 | 57.1225 | 67% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026110600 | 562 | EX | RETIRE 600'-2&3" PMLP | 2021-06-15 | 611 WINCHESTER RD | B | 21928.4488 | 701.12 | -21227.3288 | -97% |  |  | 0
KY | KY - WEST | 2621 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 21026110700 | 585 | EX | REPLACE FENCE | 2021-07-29 | 1511 RUSSELL CAVE RD | F | 14980.1771 | 480.98 | -14499.1971 | -97% |  |  | 0 | CCC# 33097 - BLONE - 07/29/21 FENCE REPLACED BY INTERSTATE FENCE COMPANY PAPERWORK COMPLETED BY CYNTHIA FARIS ON 12/17/2021
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026110800 | 586 | EX | RETIRE FENCE | 2021-07-29 | 1511 RUSSELL CAVE RD | F | 61.2976 | 0 | -61.2976 | 100% |  |  | 0 | FENCE REPLACED BY INTERSTATE FENCE COMPANY PAPERWORK COMPLETED BY CYNTHIA FARIS 12/17/2021
KY | KY - WEST | 2621 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 21026111101 | 585 | EX | INSTALL FENCE | 2021-07-29 | 834 E 3RD ST | F | 40000.9906 | 5601.7 | -34399.2906 | -86% |  |  | 0 | CCC# 31858 , 31996 , 32095 , 32237 , 32396 , 32702 ALL USED DURING PROJECT BLONE - 07/29/21 FENCE INSTALLED BY INTERSTATE FENCE COMPANY PAPERWORK COMPLETED BY CYNTHIA FARIS 12/16/21 UNDERRUN EXPLANATION: THE COST ESTIMATE THAT THE CONTRACTOR PROVIDED TURNED OUT TO BE SIGNIFICANTLY LESS THAN THEY HAD ESTIMATED. GES 3/2/22
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026111200 | 586 | EX | RETIRE FENCE | 2021-07-29 | 834 E 3RD ST | F | 61.2976 | 0 | -61.2976 | 100% |  |  | 0 | FENCE REPLACED BY INTERSTATE FENCE COMPANY PAPERWORK COMPLETED BY CYNTHIA FARIS 12/16/21
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026112000 | 2000 | EX | CONFLICT ASSESSMENT - RELOCATE | 2021-07-02 | 1180 NEWTOWN PK | B | 19090 | 0 | -19090 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026112100 | 561 | EX | INSTALL 1025'- 2"/4"PHHP MAIN | 2021-09-23 | 1180 NEWTOWN PK | B | 194441.8822 | 192775.66 | -1666.2222 | -1% | 1005 | 986 | 195.5128
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026112200 | 562 | EX | RETIRE 980' OF 4"CSHP MAIN | 2021-09-23 | 1180 NEWTOWN PK | B | 74.8797 | 723.52 | 648.6403 | 866% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026112300 | 563 | EX | INSTALL 180' OF 4"PMMP S/L | 2022-05-31 | 2000 POLO CLUB BV LT1 | B | 28556.5857 | 24370.71 | -4185.8757 | -15% | 180 |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026112400 | 587 | EX | INSTALL NEW GMB SETTING | 2022-08-22 | 2000 POLO CLUB BV | F | 57016.3076 | 55082.19 | -1934.1176 | -3% |  |  | 0 | INSTALLED NEW GMB SKID MOUNTED METER AND REGULATOR SETTING AJPARKS 8-22-202 2 PSID 501306155
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026112700 | 555 | EX | INSTALL 350' OF 2"PMIP MAIN | 2021-06-04 | 3405 FLEETWOOD DR | B | 19281.66 | 37226.93 | 17945.27 | 93% | 350 | 365 | 101.9916
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026113000 | 557 | EX | EMER - INSTALL 60' OF 4"PMLP | 2021-03-26 | 235 E NEW CIRCLE RD | A | 12530.1178 | 2022.21 | -10507.9078 | -84% | 60 | 54 | 37.4483 | INSTALLED 54' OF 040 PLASTIC DUE TO STEEL ATMOS CORR. BAGGED OFF MAIN, RETIRED 54' 040 STEEL.WORKED WITH TIE IN PLAN AND CAPITAL PACKET.INSTALLED TWO TEST STATIONS. BHB NGF. KKINDER
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026113100 | 558 | EX | EMER - RETIRE 60' OF 4"BSLP | 2021-03-26 | 235 E NEW CIRCLE RD | A | 57.8842 | 1338.57 | 1280.6858 | 2,212% |  |  | 0 | ABADONED 54' OF S LP DUE TO ATMOS CORR. WORKED WITH 557. BAGGED OFF MAIN WORKED WITH TIE IN PLAN. KKINDER
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026113600 | 584 | EX | RETIRE INLET/OUTLET BLK VALVES | 2021-07-19 | 361 PRICE RD | F | 88.1542 | 0 | -88.1542 | 100% |  |  | 0 | JOB COMPLETED BY WADE SHIMFESSEL ON 7/19/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/21/21 GCCC TICKET NOT REQUIRED ON 7/21/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026113701 | 561 | EX | INSTALL 4030' - 4"/2" PMMP | 2021-12-17 | CLAYS MILL RD | B | 778460.4875 | 862366.14 | 83905.6525 | 11% | 4030 | 4412 | 195.4592
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026114500 | 584 | EX | RETIRE PIT REG STATION# 1024 | 2022-05-12 | 300 E MAXWELL ST | F | 149437.1771 | 195061.46 | 45624.2829 | 31% |  |  | 0 | REMOVED 2 441 REGS AND BLIND FLANGED VALVES, STATION RETIRED, CMCHOLAN CCOX RHAYES 5-12-2022 RWILLIAMS COMPLETED PAPER WORK TWALKER/KY 11-30-22: JOB OVER RUN WAS DUE TO COST FOR 20-0269890-00 (2000) WITH LAND SERVICE AND CONTRACT ENG COST OF $65000, 19-0268950-00 (0001) MATERIAL FOR LPP MATERIAL OF $84000 AND 18-0268465-00 (2000) LAND SERVICES FOR LPP PROJECT APPROV $45000 FROM PROJECT MANAGEMENT AND GTMR GROUPS.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026114600 | 2000 | EX | LAND SERVICE - EASEMENT | 2021-04-15 | 928 ENTERPRISE CT | A | 1750 | 0 | -1750 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026115700 | 555 | EX | INSTALL 300' OF 2"PMMP MAIN | 2021-09-16 | 341 MEIJER WY | B | 22097.6064 | 21541.85 | -555.7564 | -3% | 300 | 347 | 62.0803
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026117000 | 2000 | EX | RESEARCH EASEMENT & R/W | 2021-08-13 | 800 S LIMESTONE ST | B | 10508 | 0 | -10508 | 100% |  |  | 0
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 21026117800 | 562 | EX | RETIRE 117' - 4" PLP | 2021-06-28 | CLAYS MILL RD | B | 9954.0712 | 11604.62 | 1650.5488 | 17% |  |  | 0 | ABN 102' OF 040 PL ML. TESTED 4' OF 040 W/ END CAPS FOR 1 HR @ 90# SOAP TESTED CONN PTS @ 11" WC. SOAP TESTED ALL TEE CAP AND END CAPS @ OP.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026117900 | 555 | EX | INSTALL 575' OF 2"PMIP MAIN | 2021-05-19 | WINNERS CR LT28 | B | 17428.325 | 15668.74 | -1759.585 | -10% | 575 | 484 | 32.3734 | TWALKER/KY 06-28-21: THIS 555 WAS COMPLETED IN THE FIELD BUT PAPERWORK NOT COMPLETED OR MAPPED WHEN A CONTRACTOR DAMAGED A SECTION OF THIS NEW GAS MAIN. ALL WORK AND COST INCLUDED IN THIS JOB ORDER AND THE REASON FOR TWO TIE IN PLANS AND TEST FORMS.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026118200 | 575 | EX | ACQUIRE EASEMENT | 2021-10-27 | 1608 CLAYS MILL RD | F | 4170 | 7902.64 | 3732.64 | 90% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026118300 | 555 | EX | INSTALL 210' OF 2"PMMP MAIN | 2021-09-09 | 637 ELK LAKE DR | B | 16739.4681 | 17888.9 | 1149.4319 | 7% | 210 | 225 | 79.5062
KY | KY - WEST | 2621 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 21026118400 | 2000 | EX | SURVEY REG STATION LOT | 2022-01-12 | 834 E 3RD ST |  | 1221.6818 | 0 | -1221.6818 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026118500 | 562 | EX | RETIRE 3,256' 10"-3" CS/BS/PLP | 2021-12-20 | CLAYS MILL RD | B | 151.2005 | 42.9 | -108.3005 | -72% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026118600 | 555 | EX | INSTALL 600' OF 2"PMMP MAIN | 2021-07-09 | 955 TARR TC | B | 37159.65 | 65051.29 | 27891.64 | 75% | 600 | 527 | 123.437
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026118700 | 557 | EX | EMER-INSTALL 2' OF 2"PMMP MAIN | 2021-04-27 | 621 CARDIFF LN | A | 4434.6174 | 2106.1 | -2328.5174 | -53% | 2 | 2 | 1053.05 | REFERENCE JOB# 21906644500 FOR COMMENTS AND JOB INFO DMARSTO 4/27/21
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026118800 | 558 | EX | EMER-RETIRE 2' OF 2"PAMP MAIN | 2021-04-27 | 621 CARDIFF LN | A | 78.808 | 755.09 | 676.282 | 858% |  |  | 0 | REFERENCE JOB# 21906644500 FOR COMMENTS AND JOB INFO DMARSTO 4/27/21
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026120700 | 584 | EX | RETIRE REG STATION 1002 | 2021-12-15 | 1706 CLAYS MILL RD | F | 5235.8425 | 6481.89 | 1246.0475 | 24% |  |  | 0 | CC# 48634 CMCOX 12/15/21 STATION RETIRED BY CHRIS COX AND CONSTRUCTION SERVICES PAPERWORK COMPLETED BY CYNTHIA FARIS ON 12/27/21
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026120800 | 584 | EX | RETIRE HP/MP RUN-1 OF R-1035 | 2021-11-03 | 2209 CLAYS MILL RD | F | 21706.5276 | 827.14 | -20879.3876 | -96% |  |  | 0 | HP TO MP RUN 1 HAS BEEN RETIRED AND LP RUN 2 HAS BEEN PLACED BACK INTO SERVICE WORKED COMPLETED ON 11/3/2021 BY CHRIS COX PAPERWORK COMPLETED BY CYNTHIA FARIS ON 11/29/2021 GCCC TICKET NOT REQUIRED ON 11/29/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026122000 | 555 | EX | INSTALL 2150' OF 2"PMMP MAIN | 2022-06-22 | WALDORF LN LT7 | B | 162365.3384 | 178403.1 | 16037.7616 | 10% | 2150 | 2331 | 76.535
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026122200 | 555 | EX | INSTALL 925' OF 2"PMMP MAIN | 2021-05-25 | LONGRIDGE DR LT25 | B | 32784.4942 | 41992.33 | 9207.8358 | 28% | 925 | 934 | 44.9597 | TWALKER/KY 06-28-21: THIS 555 PROJECT WAS COMPLETED IN FIELD BUT PAPERWORK NOT SUBMITTED TO CLOSE OR MAPPEND WHEN LEAK ON THE NEW MAIN WAS DETECTED. WE BELIEVE THE MAIN LINE WAS DAMAGED DURING BACK FIELD. LEAK WAS REPAIRED BY CONSTRUCTION THAT IS REASON FOR TWO TIE IN PLANS AND TEST FORMS.ALL COST AND WORK CAPTURED UNDER THIS JOB ORDER.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026122500 | 557 | EX | EMER-INSTALL 5' OF 4"PMLP MAIN | 2021-05-10 | 473 WEST SECOND ST | A | 6150.5343 | 9606.89 | 3456.3557 | 56% | 5 | 5 | 1921.378 | CONTRACTOR HIT 040 PLASTIC MAIN WITH EXCAVATOR. SQUEEZED OFF TO MAKE SAFE. REPLACED 5FT OF 040 P LP. TESTED MAIN FOR 20MINS AT 90LBS.TEST OK.SOAP TEST FINAL TIE INS AT OP. TEST OK.BHB NGF.WORKED WITH CAPITAL JO AND TIE IN PLAN TWALKER/KY 06-28-21: THIS PROJECT WAS GENERATED FROM 3RD PARTY DAMAGE FROM A CONTRACTOR REPLACING STORM/SEWER AT THE INTERSECTION OF MILLER AND 2ND ST. CONTRACTOR DAMAGE SMALL OF MAIN FIRST DAY AND THE VERY NEXT DAY HIT/DA MAGE THE REPAIR MAIN. THAT MAIN WAS NEVER BOOKED OR MAPPED IN WMS. ALL WORK AND COST CAPTURED ON THIS JOB ORDER. WE HAVE TWO TIE INS AND TEST.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026122600 | 558 | EX | EMER-RETIRE 5' OF 4"PMLP MAIN | 2021-05-10 | 473 WEST SECOND ST | A | 78.808 | 19.8 | -59.008 | -75% |  |  | 0 | CONTRACTOR HIT 040 PLASTIC MAIN WITH EXCAVATOR. SQUEEZED OFF TO MAKE SAFE. REPLACED 5FT OF 040 P LP. TESTED MAIN FOR 20MINS AT 90LBS.TEST OK.SOAP TEST FINAL TIE INS AT OP. TEST OK.BHB NGF.WORKED WITH CAPITAL JO AND TIE IN PLAN
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026122700 | 557 | EX | EMEG-INSTALL 5' OF 4"PMMP MAIN | 2021-05-10 | 3941 MORNING GLORY LN | A | 5607.5343 | 3856.8 | -1750.7343 | -31% | 5 | 2 | 1928.4 | RESPONDED OT MAIN LINE DAMAGE. INSTALLED 2' OF 4" PE MAIN LINE. PRESSURE TESTED MAIN @ 90PSIG FOR 20MINS PER FOL APPROVAL. TEST OK. SOAP TESTED LAST CONNECTION @ OP. TEST OK. CONTENT VERIFIED. PRESSURE VERIFIED @ 52PSIG DMAL
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026122800 | 558 | EX | EMER-RETIRE 5' OF 4"PMMP MAIN | 2021-05-10 | 3941 MORNING GLORY LN | A | 78.808 | 210.25 | 131.442 | 167% |  |  | 0 | RESPONDED TO MAIN LINE DAMAGE. INSTALLED 2' OF 4" PE MAIN LINE. PRESSURE TESTED MAIN @ 90PSIG. FOR 20MINS PER FOL APPROVAL. TEST OK. SOAP TESTED FINAL CONNECTION @ OP. TEST OK. CONTENT VERIFIED. VERIFIED PRESSURE @52PSIG
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026122900 | 559 | EX | INSTALL 8" SS | 2021-07-30 | 1005 RICHMOND RD | B | 30904.4019 | 48788.62 | 17884.2181 | 58% |  | 4 | 12197.155
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026124400 | 559 | EX | EMER-INSTALL 2' OF 2"PMMP | 2021-05-14 | GALATA DRIVE | A | 2935.5264 | 1470.21 | -1465.3164 | -50% | 2 | 2 | 735.105
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026124500 | 560 | EX | EMER-RETIRE 2' OF 2"PMMP | 2021-05-14 | GALATA DRIVE | A | 85.0408 | 0 | -85.0408 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026124600 | 559 | EX | INSTALL 3" OUTLET VALVE | 2021-07-19 | PRICE RD | B | 34892.3468 | 28606.82 | -6285.5268 | -18% | 4 | 12 | 2383.9017
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026124700 | 560 | EX | RETIRE 4' OF 3"BSIP MAIN | 2021-07-19 | PRICE RD | B | 86.5975 | 0 | -86.5975 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026124800 | 583 | EX | INSTALL INLET/OUTLET BLOCK VLV | 2021-07-19 | 361 PRICE RD | F | 13873.2524 | 20343.89 | 6470.6376 | 47% |  |  | 0 | CCC# 30839 CCC# 31113 CCC# 31169 IN PROGRESS CCC# 31169 CC# 31169 CC-31326 CC-31492 CCC# 31755 CC-31755 NOT ON SITE- OFFICE ISO UPDATE CAP WORK COMPLETED BY WADE SHIMFESSEL ON 7/19/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/21/20 GCCC TICKET NOT REQUIRED ON 7/21/20 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS 7/21/20
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 21026125400 | 561 | EX | INSTALL 28' 4" PMMP | 2021-06-15 | 2601 CLAYS MILL RD | B | 10969.2814 | 20147.11 | 9177.8286 | 84% | 28 | 37 | 544.5165
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 21026125500 | 562 | EX | RETIRE 20' OF 4" PMMP | 2021-06-15 | 2601 CLAYS MILL RD | B | 91.2676 | 0 | -91.2676 | 100% |  |  | 0
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 21026125600 | 561 | EX | INSTALL 28' 8" PMLP | 2021-06-15 | 2601 CLAYS MILL RD | B | 11805.2814 | 23277.54 | 11472.2586 | 97% | 28 | 33 | 705.38
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 21026125700 | 562 | EX | RETIRE 20' 8" PMLP | 2021-06-15 | 2601 CLAYS MILL RD | B | 91.2676 | 71.35 | -19.9176 | -22% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026125800 | 557 | EX | REPLACE C18-5 E | 2021-07-30 | 1005 RICHMOND RD | B | 77241.44 | 96855.51 | 19614.07 | 25% | 37 | 34 | 2848.6915
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026125900 | 558 | EX | RETIRE C18-5 | 2021-07-30 | 1005 RICHMOND RD | B | 91.2676 | 38.57 | -52.6976 | -58% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026126102 | 557 | EX | INSTALL 2000' OF 2"PMMP MAIN | 2022-04-27 | 1850 MERCER RD | B | 165212.1661 | 169255.42 | 4043.2539 | 2% | 2000 | 2017 | 83.9144
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026126200 | 558 | EX | RETIRE 270' OF 1"BSHP MAIN | 2022-04-29 | 1850 MERCER RD | B | 63.0891 | 0 | -63.0891 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026126300 | 2000 | EX | INVESTIGATE R/W AND EASEMENTS | 2021-11-22 | 1847 MERCER RD | A | 7043 | 0 | -7043 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026126600 | 584 | EX | RETIRE REG STATION #1181 | 2022-04-29 | 427 TRANSPORT CT | F | 4088.2989 | 1370.38 | -2717.9189 | -66% |  |  | 0 | RWILLIAMS COMPLETED PAPER WORK, EBLANTON RETIRED STATION ON 04/29/2022
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 21026126700 | 561 | EX | INSTALL 350' OF 2" PMMP | 2022-04-26 | 1501 RUSSELL CAVE RD | B | 123612.3972 | 99374.93 | -24237.4672 | -20% | 350 | 348 | 285.5601
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026126800 | 557 | EX | INSTALL 11,170' OF 2"/6"PMMP | 2022-08-15 | MENTELLE PR | B | 1492284.9718 | 1672773.41 | 180488.4383 | 12% | 11170 | 10916 | 153.2405
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026126900 | 558 | EX | RETIRE 9000' OF 4"/6"BSLP MAIN | 2022-10-10 | MENTELLE PR | B | 62.0792 | 24.95 | -37.1292 | -60% |  |  | 0
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 21026128000 | 561 | EX | INSTALL 265' OF 4" PMLP | 2022-03-01 | 118 E NEW CIRCLE RD | B | 71153.2979 | 96077.32 | 24924.0221 | 35% | 265 | 163 | 589.4314 | AWEBER - JO RAN OVER ESTIMATE DUE TO UNFORSEEN 8'X5' STORM BASIN @ 42" BELO W GRADE. EXCAVATION OF TOP OF BASIN OCCURRED TO PROVIDE REROUTE OF 4" PMMP INSTALL AT ACCEPTABLE DEPTH WITHOUT CROSSBORE.
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 21026128100 | 562 | EX | RETIRE 230'-4" & 50'-6" PMLP | 2022-03-01 | 118 E NEW CIRCLE RD | B | 354.2624 | 71.35 | -282.9124 | -80% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026128300 | 0001 | EX | DOCUMENT PRESSURE INCREASES | 2021-07-14 | MASON HEADLEY RD | B | 5085.0408 | 0 | -5085.0408 | 100% |  |  | 0 | TWALKER/KY 07-14-21: THIS JOB ORDER DOCUMENTED PRESSURE INCREASES ONLY FOR AN EXISTING 60PSIG SYSTEM THAT HAD BEEN SET AT 30PSIG FOR 20+ YEARS PRESSURE RAISED TO 42PSIG. THIS PROCESS IS PART OF THE CLAY MILL ROAD RELOCATION PROJECT AND IS NOT AN UPRATE.
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026128400 | 2000 | EX | INVESTIGATE MAINS & SERVICES | 2021-10-06 | ARMSTRONG MILL | B | 21541 | 0 | -21541 | 100% |  |  | 0 | PS&I COMPLETED AND EXECUTED TO 561 JO. D.LEMONS 10/6/2021
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026128601 | 555 | EX | INSTALL 700' OF 2"PMMP MAIN | 2021-10-12 | 3492 JACOB CT | B | 57445.0039 | 75716.28 | 18271.2761 | 32% | 700 | 862 | 87.8379
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026128700 | 584 | EX | RETIRE HP/MP REG RUN | 2021-11-09 | 785 CHERYL LN | F | 4148.6042 | 3741.83 | -406.7742 | -10% |  |  | 0 | HP/MP RUN RETIRED BY CHRIS COX ON 11/9/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 11/18/2021 GCCC TICKET NOT REQUIRED ON 11/18/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026128802 | 557 | EX | INSTALL 470' OF 4"PMMP MAIN | 2022-05-12 | 1119 COOPER | B | 96528.8129 | 106230.58 | 9701.7671 | 10% | 470 | 462 | 229.9363
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026128900 | 558 | EX | RETIRE 440' OF 4"BSMP MAIN | 2022-05-25 | 1119 COOPER | B | 67.1085 | 30.93 | -36.1785 | -54% |  |  | 0 | X
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026129000 | 558 | EX | RETIRE 680'-4"BSLP MN -D247885 | 2022-05-25 | 1119 COOPER DR | B | 67.1085 | 0 | -67.1085 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026129400 | 562 | EX | RETIRE 135' OF 8"CSMP MAIN | 2021-08-25 | 1983 HARRODSBURG RD | B | 151.2005 | 1142.2 | 990.9995 | 655% |  |  | 0 | ABN 135' ON CS MP MAIN.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026129500 | 562 | EX | RETIRE 109' OF 4"BSLP | 2021-08-26 | 1983 HARRODSBURG RD | B | 99.3208 | 71.35 | -27.9708 | -28% |  |  | 0 | ABN 4" BS LP MAIN PER GS
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026129600 | 557 | EX | INSTALL 100' OF 8"PMMP MAIN | 2021-11-16 | 249 WALTON AV | B | 99233.0142 | 152586.55 | 53353.5358 | 54% | 104 | 53 | 2878.9915 | TWALKER/KY 01-24-23: JOB ORDER OVER RUN DUE TO ADDITIONAL FLAGGING ADDED $50,000 TO CONTRACT COST, SEGA INCREASED BY $6,000 AND CO LABOR COST HIGHER BY $14,000 LEVEL 2 VARIANCE ADDED TO WMS.DOCS.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026129700 | 558 | EX | RETIRE 20' OF 8"BSMP MAIN | 2021-11-16 | 249 WALTON AV | B | 79.203 | 1960.6 | 1881.397 | 2,375% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026129900 | 584 | EX | RETIRE PIT REG STATION W/AMRP | 2022-11-16 | 800 PRESS AV | F | 4706.4362 | 3639 | -1067.4362 | -23% |  |  | 0 | RETIRED 800 PRESS AVE 200340, CMCHOLAN 11-16-22
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026130600 | 555 | EX | INSTALL 350' OF 2"PMMP MAIN | 2021-08-17 | 600 LAKE CLAIR CT | B | 31312.2411 | 42649.02 | 11336.7789 | 36% | 350 | 461 | 92.5141
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026130902 | 555 | EX | INSTALL 5150' OF 2"/4" PMMP | 2022-03-28 | CATTLE PH LT46 | B | 202239.5285 | 192645.27 | -9594.2585 | -5% | 4750 | 5599 | 34.4071
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026132400 | 555 | EX | INSTALL 225' OF 2"PMMP | 2022-11-09 | 200 W VINE ST GENERAT | B | 79492.8479 | 85412.94 | 5920.0921 | 7% | 225 | 201 | 424.94 | TTALKER/KY 01-25-23: JOB IS SHOWING COST UNDER RUN AT THIS TIME BUT PAVING/ STREET REPAIRS NOT TAKE PLACE UNTIL SPRING/WARM WEATHER. TWALKER/KY 06-23-23: JOB ORDER CURRENTLY UNDER RUNNING $32000 BUT STREET PAVING HAS NOT BEEN COMPLETED AT THIS TIME DUE TO DOWNTOWN AREA AND CONSTRU CTION BY OTHERS IN AREA. TWALKER/KY 07-21-23: PAVING HAS BEEN COMPLETED AND COST APPLIED TO JOB ORDE R, NOT OVER OR UNDER BUDGET VARIANCE REQUIRED AT THIS TIME. PAVING WAS DELAYED TO COLD AND WET WEATHER PLUS THIS PROJECT IS LOCATED IN DOWNTOWN AREA SO PERMIT RESTRICTION APPLIED.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026132500 | 555 | EX | INSTALL 450' OF 2"PMMP MAIN | 2021-10-06 | 3326 GRASMERE DR | B | 32348.6064 | 31237.4 | -1111.2064 | -3% | 450 | 278 | 112.3647
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026134100 | 555 | EX | INSTALL 850' OF 2"PMMP MAIN | 2021-10-21 | 196 TURNER COMMONS WY BLG 35 | B | 40949.6064 | 28285.71 | -12663.8964 | -31% | 850 | 561 | 50.4202
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026134200 | 2000 | EX | INVESTIGATE MAINS | 2022-12-15 |  |  | 21078 | 0 | -21078 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026134800 | 559 | EX | INSTALL 20'-2" PMMP | 2022-01-12 | 694 BISHOP DR | B | 39141.4028 | 67370.23 | 28228.8272 | 72% | 14 | 22 | 3062.2832
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026134900 | 560 | EX | RETIRE 16'-2" CSMP | 2022-01-12 | 694 BISHOP DR | B | 88.8156 | 0 | -88.8156 | 100% |  |  | 0
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 21026135200 | 2000 | EX | INVESTIGATE HP ENCROACHMENT | 2023-08-10 | 3021 BROOKMONTE LN | B | 5000 | 5946.09 | 946.09 | 19% |  |  | 0 | AWEBER 8/21/23 - JO CHARGED TO O&M, LAND WORK REQUIRED FOR ENCROACHMENT INV ESTIGATION.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026135700 | 2000 | EX | INVESTIGATE ENCROACHMENTS | 2022-03-29 | 260 OLD MOUNT TABOR RD 1 | B | 6526 | 0 | -6526 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026136000 | 2000 | EX | RAILROAD CROSSING & R/W | 2021-09-14 | SHROPSHIRE |  | 3013 | 0 | -3013 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026136100 | 557 | EX | EMER-INSTALL 10'-2" PMMP | 2021-08-10 | 345 PEACHTREE RD | A | 5241.7163 | 3664.07 | -1577.6463 | -30% | 10 | 2 | 1832.035
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026136200 | 558 | EX | EMER-RETIRE 10'-2" PMP | 2021-08-10 | 345 PEACHTREE RD | A | 88.8156 | 253.41 | 164.5944 | 185% |  |  | 0 | RETIRED 2' OF DAMAGED 2" PMP MAIN
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026136500 | 561 | EX | RELOCATE 12' OF 4"PMLP MAIN | 2021-08-18 | 2914 CLAYS MILL RD | B | 10466.234 | 25628.84 | 15162.606 | 145% | 10 | 7 | 3661.2629
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026136600 | 562 | EX | RETIRE 6' OF 4"PMLP MAIN | 2021-08-18 | 2914 CLAYS MILL RD | B | 85.7248 | 0 | -85.7248 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026136800 | 557 | EX | EMER-INSTALL 5' OF 4"PMMP | 2021-08-17 | 1246 CENTRE PY | A | 5949.1348 | 395.9 | -5553.2348 | -93% | 5 | 5 | 79.18 | INST 5' 4" P MP MAIN ACCORDING TO ENGINEERED TIE-IN PLAN AND GAS STANDARDS. WORKED ON 8/17/21. MCRAIG 8/24/21
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026136900 | 558 | EX | EMER-RETIRE 5' OF 4"PAMP | 2021-08-17 | 1246 CENTRE PY | A | 55.634 | 5438.98 | 5383.346 | 9,676% |  |  | 0 | ABN 5' 4"P MP MAIN ACCORDING TO ENGINEERED TIE-IN PLAN. WORKED ON 8/17/21. MCRAIG 8/24/21
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026137100 | 560 | EX | RETIRE 4'-8" BSLP | 2021-07-23 | 1005 RICHMOND RD | B | 177.6312 | 0 | -177.6312 | 100% |  |  | 0
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 21026137200 | 2000 | EX | INVESTIGATE UTILITY EASEMENT | 2023-11-03 | 2350 WINCHESTER RD | B | 5000 | 2212.54 | -2787.46 | -56% |  |  | 0 | AWEBER 11/3/2023 - EXECUTING LAND PS&I FOR 2350 WINCHESTER RD, LEX. WORK TO DETERMINE EASEMENTS FOR NEW SUBDIVISION ON SIR BARTON WAY IS COMPLETED PER CBOWLIN.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026137500 | 909 | EX | INSTALL SOLAR PANEL | 2021-10-13 | 707 LANE ALLEN RD | F | 4862.234 | 3598.81 | -1263.424 | -26% |  |  | 0 | CC# 41497 RHAYES 10-13-2021 RHAYES 10-13-2021 CHANGED ER350 FROM CRY IN TO FULL TIME MONITOR INSTALLED SUPER SOLAR KIT AN D RV 50 MODEM CCOX 10-13-2021
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026140400 | 555 | EX | INSTALL 2800' OF 2"/4"PMMP | 2022-03-03 | ANGUS TL LT40 | B | 86592.9986 | 116146.05 | 29553.0514 | 34% | 2800 | 2987 | 38.8838
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026140901 | 555 | EX | INSTALL 2750' OF 2"PMMP MAIN | 2022-04-14 | BACKSTRETCH LT30 | B | 96941.3864 | 104070.68 | 7129.2936 | 7% | 2750 | 2640 | 39.4207
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026141200 | 557 | EX | EMER-INSTALL 3'OF 6"PMLP MAIN | 2021-09-13 | 855 CHARLES AV | A | 4022.0999 | 5901.09 | 1878.9901 | 47% | 3 | 3 | 1967.03
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026141300 | 558 | EX | EMER-RETIRE 3' OF 6"PLP MAIN | 2021-09-13 | 855 CHARLES AV | A | 69.8875 | 38.15 | -31.7375 | -45% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026141400 | 561 | EX | INSTALL 130'-6" PMMP | 2022-02-15 | ARMSTRONG MILL RD | B | 140177.264 | 179014.36 | 38837.096 | 28% | 136 | 211 | 848.4093 | PROJECT OVERRUN OF $38,555 (28%) DUE TO ADDITIONAL TIME AND RESOURCES BEING REQUIRED. LABOR HOURS ESTIMATED AT 176 HRS, BUT 319 HRS WERE REQUIRED ($11 ,052 DIFF. LABOR RATE ESTIMTES TOO LOW). NEW CONTRACT WILL ADDITIONAL UNITS WAS USED WHICH ADDED $57,948. BUT THERE WERE SAVINGS OF $30,000 IN THE OT HER CATAGORY, WHICH WERE COVERED WITH UNITS IN THE UPDATED CONTRACT. D.LEMO NS 7/8/2022
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026141500 | 562 | EX | RETIRE 316'-6" PM&CS MP | 2022-02-15 | ARMSTRONG MILL RD | B | 76.2083 | 4123.73 | 4047.5217 | 5,311% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026141600 | 561 | EX | INSTALL 320' OF 2"PMMP MAIN | 2021-12-27 | 240 CANARY RD | B | 52296.0917 | 51396.03 | -900.0617 | -2% | 320 | 322 | 159.615
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026141700 | 562 | EX | RETIRE 315' OF 2"PMP MAIN | 2021-12-27 | 240 CANARY RD | B | 60.6987 | 46.05 | -14.6487 | -24% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026141800 | 2000 | EX | RELOCATION DESIGN IN EASEMENT | 2021-10-14 | 240 CANARY RD | B | 6917 | 0 | -6917 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026142200 | 555 | EX | INSTALL 575' OF 2"PMMP MAIN | 2021-11-02 | SNOWY EGRET WY LT109 | B | 20915.4686 | 25446.02 | 4530.5514 | 22% | 550 | 727 | 35.0014
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026142500 | 557 | EX | EMER-INSTALL 5' OF 2"PMMP | 2021-09-20 | 962 CHARWOOD DR | A | 3297.6583 | 417.14 | -2880.5183 | -87% | 5 | 5 | 83.428
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026142600 | 558 | EX | EMER-RETIRE 5' OF 2"PMP MAIN | 2021-09-20 | 962 CHARWOOD DR | A | 69.8875 | 263.29 | 193.4025 | 277% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026143000 | 588 | EX | RETIRE EME FACILITY | 2021-09-23 | 767 WINCHESTER RD | F | 63.4597 | 0 | -63.4597 | 100% |  |  | 0 | REPLACED EFC
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026143400 | 557 | EX | EMER-INSTALL 10'OF 4"PMIP MAIN | 2021-09-27 | CARLETON DR | A | 7432.5408 | 7913.03 | 480.4892 | 6% | 10 | 6 | 1318.8383
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026143500 | 558 | EX | EMER-RETIRE 10' OF 4"PAIP MAIN | 2021-09-27 | CARLETON DR | A | 60.6987 | 0 | -60.6987 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026143600 | 2000 | EX | INVESTIGATE MAINS & R/W | 2022-11-08 |  |  | 47385 | 0 | -47385 | 100% |  |  | 0
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 21026143900 | 557 | EX | EMER-INSTALL 5'-2"PMMP | 2021-09-27 | 535 LAKETOWER DR | A | 6000.6188 | 0 | -6000.6188 | 100% | 5 | 5 | 0
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 21026144000 | 558 | EX | EMER-RETIRE 5'-2"PMMP | 2021-09-27 | 535 LAKETOWER DR | A | 49.6987 | 0 | -49.6987 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026144100 | 555 | EX | INSTALL 350' OF 2"PMIP MAIN | 2021-10-27 | WINNERS CR LT9 | B | 20004.6217 | 19720.01 | -284.6117 | -1% | 350 | 360 | 54.7778
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026144200 | 560 | EX | RETIRE 4280' OF 2"/3"PAMP MAIN | 2021-10-13 | VALLEY FARM DR | A | 14091.9275 | 41269.58 | 27177.6525 | 193% |  |  | 0 | ABN 4280' P MP MAIN IN ACCORDNANCE WITH ENGINEERED TIE-IN PLAN AND GAS STANDARDS. SOAP TEST FINAL TIE-IN AT OP OK. BHB NGF. MCRAIG 10/13/21 TWALKER/KY 11-24-21: WMS WOULD NOT ALLOW FOR REVISION DUE TO UNPAID INVOICES, JOB ORDER OVER RUN DUE TO SCOPE OF WORK INCREASED AND WE RETIRED MORE UNLOCATED FIRST GENERATION PLASTIC MAIN THAN PLANNED AND SOME NEW EMPLOYEES WORKED WITH CREWS WITH INCREASED LABOR COST BY $14,000 OVER ESTIMATE
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 21026145500 | 2000 | EX | INVESTIGATE NEW CIRC SMRP | 2022-02-17 | 450 E NEW CIRCLE RD | B | 17684 | 0 | -17684 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026146000 | 557 | EX | INSTALL 404'-4"&6"PMMP | 2021-10-19 | EUCLID AV | A | 224207.9887 | 125105.39 | -99102.5987 | -44% | 405 | 395 | 316.7225 | LEVEL 2 BUDGET VARIANCE EXPLANATION FORM HAS BEEN APPROVED AND LOADED INTO WMSDOCS WORKSPACE. D.LEMONS 3/3/2022
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026146100 | 558 | EX | RETIRE 427'-4"BSLP | 2021-10-19 | EUCLID AV | A | 63.4597 | 1537.36 | 1473.9003 | 2,323% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026147000 | 0001 | EX | DOCUMENT DOWNRATE 32010119 | 2022-04-28 | TRANSPORT CT | A | 60.6987 | 0 | -60.6987 | 100% |  |  | 0 | TWALKER/KY-SEE JOB 21-0261261-00 FOR NEW MAIN LINE AND REG STATION RETIRED.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026147100 | 557 | EX | EMER-INSTALL 6' OF 4"PMMP | 2021-10-15 | 383 LANCELOT LN | A | 1045.4141 | 604.21 | -441.2041 | -42% | 6 | 5 | 120.842
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026147200 | 558 | EX | EMER-RETIRE 6' OF 4"PAMP MAIN | 2021-10-15 | 383 LANCELOT LN | A | 49.6987 | 38.59 | -11.1087 | -22% |  |  | 0
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026147900 | 559 | EX | EMER - INSTALL 5'-4" PMLP | 2021-10-12 | 732 WHITNEY AV | A | 2422.8089 | 3691.18 | 1268.3711 | 52% | 5 | 3 | 1230.3933 | INSTALLED 3FT OF 040 PLASTIC DUE TO 3 TEE'S BEING AN AOC. ALL TESTING INFO ON JO 21026147900 AND 21026148000 IN WMS DOCS.
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026148000 | 560 | EX | EMER - RETIRE 5'-4" PLP | 2021-10-12 | 732 WHITNEY AV | A | 66.2207 | 4.38 | -61.8407 | -93% |  |  | 0 | INSTALLED 3FT OF 040 PLASTIC DUE TO 3 TEE'S BEING AN AOC. ALL TESTING INFO ON JO 21026147900 AND 21026148000 IN WMS DOCS.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026148100 | 557 | EX | EMER-INSTALL 4' OF 2"HPHP MAIN | 2021-10-21 | 1450 NEWTOWN PK | A | 7370.71 | 2019.57 | -5351.14 | -73% | 4 | 7 | 288.51
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026148200 | 558 | EX | EMER-RETIRE 4' OF 2"HDHP MAIN | 2021-10-21 | 1450 NEWTOWN PK | A | 60.6987 | 0 | -60.6987 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026150300 | 2000 | EX | INVESTIGATE CONFLICTS | 2022-11-22 |  |  | 9460 | 0 | -9460 | 100% |  |  | 0 | PS&I COMPLETED FOR DESIGN. CONSTRUCTION WAS POSTPONED UNTIL 2023. D.LEMONS 11/22/2022
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026150400 | 2000 | EX | INVESTIGATE CONFLICTS | 2022-05-02 |  |  | 16069 | 0 | -16069 | 100% |  |  | 0 | INVESTIGATION AND DESIGN COMPLETE. D.LEMONS 5/2/2022
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026151100 | 2000 | EX | INVESTIGATE MAINS & SERVICES | 2022-02-24 | GREENTREE |  | 27112 | 0 | -27112 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026151200 | 561 | EX | INSTALL 2065'-2"&6" PMMP | 2022-08-29 | GREENTREE | B | 333722.7132 | 493527.08 | 159804.3668 | 48% | 2075 | 2224 | 221.9097
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026151300 | 562 | EX | RETIRE 2111'-2"&6" CSMP | 2022-10-12 | GREENTREE | B | 109.7476 | 80 | -29.7476 | -27% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026151500 | 557 | EX | EMER-INSTALL 10' OF 4"PMMP | 2021-11-17 | 3102 KIRKLEVINGTON DR | A | 5220.9567 | 210.64 | -5010.3167 | -96% | 10 | 3 | 70.2133 | LEAK ON SF CPLG ON TEE OF SVC TO 3102 KIRKLEVINGTON DR. DPI D221947 CLEARED ON 2212. ABN/INST 3'- 4" P MAIN ACCORDING TO GAS STANDARDS AND ENGINEERED TIE-IN PLAN. WORKED 11/17/21 MCRAIG
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026151600 | 558 | EX | EMER-RETIRE 10' OF 4"PAMP | 2021-11-17 | 3102 KIRKLEVINGTON DR | A | 64.6591 | 24.42 | -40.2391 | -62% |  |  | 0 | LEAK ON SF COUPLING ON TEE TO SVC OF 3102 KIRKLEVINGTON DR. DPI D221947 CLEARED ON 2212. ABN/ INST 3'- 4" P MAIN ACCORDING TO GAS STANDARDS AND ENGINEERED TIE-IN PLAN. WORKED 11/17/24 MCRAIG
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026155900 | 555 | EX | INSTALL 2400' OF 2"PMMP MAIN | 2022-02-09 | 272 SQUIRES CR | B | 61211.3642 | 72846.65 | 11635.2858 | 19% | 2400 | 2508 | 29.0457
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 21026156700 | 559 | EX | INSTALL 20'-3 PMMP | 2022-06-07 | 3030 LAKECREST CIR | B | 12546.0469 | 13109.07 | 563.0231 | 4% | 20 | 23 | 569.9596
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 21026156800 | 560 | EX | ABDN CB 12'-3" PMP | 2022-06-07 | 3030 LAKECREST CIR | B | 73.9724 | 0 | -73.9724 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026156900 | 559 | EX | INSTALL 10'-6" PMLP | 2022-07-21 | APPOMATTOX RD | A | 14786.2791 | 6980.82 | -7805.4591 | -53% | 10 | 4 | 1745.205 | INSTALLATION COMPLETE, HMCKUNE
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026157000 | 560 | EX | RETIRE 10'-6" PMLP | 2022-04-20 | APPOMATTOX RD | A | 72.8047 | 0 | -72.8047 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026993800 | 557 | EX | INSTALL 7200' OF 2"/6"PMMP | 2022-02-21 | 456 E HIGH ST | B | 2229015.8617 | 3006825.55 | 777809.6883 | 35% | 7200 | 7402 | 406.218
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026993900 | 558 | EX | RETIRE 9500' OF 4"CI/6"BSLP MN | 2022-12-09 | 456 E HIGH ST | B | 80.3582 | 5876.52 | 5796.1618 | 7,213% |  |  | 0 | ABANDONED ALL MAINS IN SCOPE OF PROJECT
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026994000 | 557 | EX | INSTALL 10930 - 2"/4"PMMP MAIN | 2022-11-16 | STATE ST | B | 1953601.844 | 1681569.14 | -272032.704 | -14% | 10930 | 10169 | 165.3623 | TWALKER/KY 05-22-23: PROJECT CURRENTLY UNDER RUNNING, WAITING ON FINAL RESTORATION/PAVING TO DETERMINE IF ADDITIONAL EXPLAINATION OR VARIANCE REQU IRED. TWALKER/KY 06-23-23: JOB UNDER RUNNING DUE TO PAVING/HARD SURFACES REPAIRS HAVE NOT BEEN FULLY COMPLETED. TWALKER/KY 07-24-23: PAVING/HARD SURFACE REPAIRS STILL IN PROGRESS TWALKER/KY 08-29-23: LEVEL 1 VARIANCE FORM ADDED IN WMS.DOCS NOT SURE IF ALL PAVING INVOICES HAVE BEEN PAID BUT COST UNDER RUN DRIVEN BY LESS PAVING COST BY PAVING CONTRACTOR INSTEAD OF PIPELINE CO.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026994100 | 558 | EX | RETIRE 14,600 - 4"CI/BSLP MAIN | 2022-11-16 | STATE ST | B | 84.1794 | 269.51 | 185.3306 | 220% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026994300 | 575 | EX | DOCUMENT HP EASEMENT | 2021-01-22 | 2001 LAKESIDE DR | F | 6229.6196 | 5365.64 | -863.9796 | -14% |  |  | 0 | TWALKER/KY 01-22-21: THIS JOB ORDER TO SET ADDITIONAL EASEMENT FOR EXISTING 12"HP GAS MAIN AT 2001 LAKESIDE DRIVE (FROM PS&I 20-0269617-00) COPY OF EASEMENT DRAWING IN WMS.DOCS AND RW# 592684.
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026994600 | 557 | EX | EMER INSTALL 5'-4" PMMP | 2021-01-08 | 2218 BAHAMA RD | A | 5854.5805 | 4622.23 | -1232.3505 | -21% | 35 | 5 | 924.446 | REPLACED 5 FT MAIN TEST 90 LB FOR 20 MIN TEST ALL TEES AT 5 MIN TEST BYPASS 90 LB FOR 1 HR TEST ALL END CAPS AT OP FOR 5 MIN BAR HOLE BANKS NO GAS FOUND MARKER BALL AT TEES AND CPLG
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026994700 | 558 | EX | EMER - RETIRE 5'-4" PMP | 2021-01-08 | 2218 BAHAMA | A | 103.8156 | 102.95 | -0.86559 | -1% |  |  | 0 | CUT OUT CRACKED MAIN PUT ON BYPASS AND PUT IN 5 FT OF MAIN
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 21026996200 | 561 | EX | INSTALL 2150'-2" PMMP | 2021-03-05 | REED LN | B | 214604.887 | 336530.83 | 121925.943 | 57% | 2154 | 2005 | 167.8458 | JOB ORDER CODED COMPLETE AT TIME OF MAIN LINE COMPLETION, STILL WORKING ON SERVICES. SPENDLE 3/10/21 20APR21: SEVERAL ATTEMPTS WERE MADE TO REVISE THIS JOB ORDER TO CAPTURE OVERRUN, HOWEVER, OUTSTANDING INVOICES PREVENTED ENGINEERING FROM DOING SO. . 29APR21: OVERRUN EXPLANATION = FISHEL'S CONTRACT OVER $21K DUE TO INCREASED LABOR & MATERIALS TO PREP STAGING (STONE, FENCING, AND ENVIRONMENTAL BMPS) ALONG WITH A LOT MORE FLAGGING BY AWP FOR TRAFFIC CONTROL. BUCHANAN'S COST FOR SEWER INSPECTION & CAMERING WAS WAY UNDERESTIMATED CONTRIBUTING ANOTHER $33K TO THE OVERRUN. LASTLY, COMPANY LABOR OVERRAN BY $14K FROM WHAT WAS ORIGINALY ESTIMATED. THESE COSTS PLUS OH'S MAKE UP THE OVERRUN (BKSLONE).
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026996400 | 558 | EX | EMER - ABANDON 37'-2" PIP | 2021-01-14 | 4035 WHITEMARK CT | A | 2872.6664 | 860.91 | -2011.7564 | -70% |  |  | 0 | ABANDONED 37' OF 020 MAIN DUE TO FAC DAM. WORKED WITH TIE IN PLAN. INSTALLED LINE MARKER AT EOM. UPDATED MAPPING. SOAP TEST END CAP AT OP.TEST OK. BHB NGF.
KY | KY - WEST | 2621 | BKSLONE |  |  |  | 21026997000 | 561 | EX | INSTALL 1100'-2" PMP | 2021-03-10 | WOODBINE DR | B | 340896.6283 | 532822.99 | 191926.3617 | 56% | 1104 | 1140 | 467.3886 | 14JUN21: UNDERRUN EXPLANATION = 1) ASPHALT MILL & OVERLAY WAS MISCALCULATED RESULTING IN AN ADDITIONAL $120K AND 2) FLAGGING TIME WAS UNDERESTIMATED RESULTING IN AND ADDITIONAL $35K. THESE COSTS, ALONG WITH ASSOCIATED OH'S, MAKE UP THE MAJORITY IF THE $166K OVERRUN. THE ERROR IN PAVING COSTS WAS NOT NOTICED UNTIL AFTER THE ORIGINAL JOB ORDER WAS EXECUTED THEREBY PROHIBITING PROCESSING A REVISION (BKSLONE).
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026997101 | 561 | EX | INSTALL 125' OF 4"PMMP MAIN | 2021-08-27 | 1983 HARRODSBURG RD REAR | B | 111178.7891 | 118779.98 | 7601.1909 | 7% | 123 | 125 | 950.2398
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026997500 | 2000 | EX | OBTAIN EASEMENTS FOR NEW MAIN | 2022-02-17 | DEER HAVEN LN | B | 8502 | 0 | -8502 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026997801 | 557 | EX | INSTALL 4600' OF 2"/6"PMMP | 2023-08-07 | E 4TH ST | B | 2229421.3209 | 2229938.96 | 517.6391 | 0% | 4061 | 4887 | 456.3002
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026997900 | 558 | EX | RETIRE 6300' OF 4"/6"CILP MN | 2023-10-19 | E 4TH ST | B | 126.9534 | 747.19 | 620.2366 | 489% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026998000 | 587 | EX | CONVERT TO GMB ACCOUNT | 2021-04-05 | 699 BYRD THURMAN DR | F | 4845.4443 | 6412.15 | 1566.7057 | 32% |  |  | 0 | CONVERTED FROM CAB TO GMB ACCOUNT CCC TICKET NOT REQUIRED THIS IS NON-SCADA MONITORED
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026998100 | 555 | EX | INSTALL 180' OF 2"PMMP MAIN | 2021-02-26 | 2708 MABLE LN LT123 | B | 11159.7406 | 36764.99 | 25605.2494 | 229% | 180 | 198 | 185.6818
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026998900 | 566 | EX | RETIRE 3"PLP SERVICE LINE | 2022-09-07 | 437 RACE ST | B | 9329.0565 | 9085.7 | -243.3565 | -3% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026999500 | 555 | EX | INSTALL 175' OF 2"PMMP | 2021-04-19 | 776 LONGWOOD RD | B | 9497.8185 | 16309.78 | 6811.9615 | 72% | 175 | 174 | 93.7344 | 174 '2"PLASTIC MED -DENSITY YELLOW PIPE INSTALLED BY BIRECTIONAL BOREBY STA NLEY PIPELINE.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026999600 | 561 | EX | INSTALL 90' OF 4"CS/PMMP MAIN | 2021-11-11 | FAIRCREST DR | B | 68922.5327 | 47302.77 | -21619.7627 | -31% | 90 | 98 | 482.6813 | NEW MAIN GASED UP 11-11-21
KY | KY - WEST | 2621 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 21026999900 | 2000 | EX | PERFORM CONFLICT ASSESSMENT | 2021-07-20 | W NEW CIRCLE RD | B | 1792 | 0 | -1792 | 100% |  |  | 0 | EXPOSURES ON NEW CIRCLE FOR ENGINEERING; 4 EXPOSURES VIA HYDRO EXCAVATION; JNEWSOME ORDER FOR HYDRO EXCAVATION COMPLETED BY JNEWSOME ON 05/13/21 EXPOSURES ON NEW CIRCLE FOR ENGINEERING; 4 EXPOSURES VIA HYDRO EXCAVATION; JNEWSOME
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026158400 | 555 | EX | INSTALL 1200' OF 2"PMMP MAIN | 2022-03-17 | MARLENA LN LT139 | B | 35742.3291 | 29132.57 | -6609.7591 | -18% | 1200 | 1137 | 25.6223
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026158800 | 557 | EX | INSTALL 540' OF 4"/8"PMMP MAIN | 2023-02-13 | WALTON AV | B | 262444.8259 | 378932.24 | 116487.4141 | 44% | 540 | 553 | 685.2301 | TWALKER/KY 09-27-23: LEVEL 1 VARIANCE FORM ADDED TO WMS.DOCS JOB OVER RUN DUE TO ADDITIONAL PAVING/RESTORATION REQUIREMENT BY THE CITY INCREASED CONTRACT COST BY $30,000, ALSO SEGA $12,000 HIGHER THAN ESTIMATE. COMPANY LABOR INCREASED BY $25,000 DUE TO ADDITIONAL COMPANY LABOR REQUIRED. TWALKER/KY 10-27-23: LEVEL 2 VARIANCE REPORTED ADDED TO WMS.DOCS, JOB OVER DUE TO CITY PAVING AND RE-PAVING REQUIREMENT.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026158900 | 558 | EX | RETIRE 594' OF 8"BSMP MAIN | 2023-02-13 | WALTON AV | B | 72.8047 | 0 | -72.8047 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026159301 | 2000 | EX | SURVEY FOR RELEASE OF EASEMENT | 2022-11-07 | TOWN CENTER DR |  | 1000 | 0 | -1000 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026160800 | 557 | EX | EMER-INSTALL 5' OF 2"PMMP MAIN | 2022-01-12 | COLCHESTER RD | A | 3947.9695 | 2109.29 | -1838.6795 | -47% | 5 | 5 | 421.858
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026160900 | 558 | EX | EMER-RETIRE 5' OF 2"PAMP MAIN | 2022-01-12 | COLCHESTER | A | 69.6571 | 0 | -69.6571 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026162000 | 560 | EX | RETIRE 110' OF 2"CSHP MAIN | 2022-06-23 | DEER HAVEN DR | B | 105.0102 | 716.93 | 611.9198 | 583% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026162102 | 557 | EX | INSTALL 8150' OF 2"/4"PMMP | 2023-08-30 | BERRY LN | B | 751182.165 | 755714.67 | 4532.505 | 1% | 8150 | 7928 | 95.3222
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026162200 | 558 | EX | RETIRE 4600' OF 4"/6"BSLP MAIN | 2023-11-27 | BERRY LN | B | 105.0102 | 1442.96 | 1337.9498 | 1,274% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026162500 | 561 | EX | INSTALL 8" STOPPLE FITTING | 2022-02-10 | SPORTS CENTER DR | B | 14352.6857 | 25751.7 | 11399.0143 | 79% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026162600 | 562 | EX | RETIRE 44' OF 8"BSMP MAIN | 2022-02-10 | SPORTS CENTER DR | B | 105.0102 | 0 | -105.0102 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026163200 | 557 | EX | INSTALL 775' OF 2"PMMP MAIN | 2023-03-09 | PARKWAY DR | B | 80533.8181 | 49762.97 | -30770.8481 | -38% | 775 | 702 | 70.8874 | TWALKER/KY- 09-27-23: LEVEL 1 VARIANCE ADDED TO WMS.DOCS JOB UNDER RUN WAS DUE TO NO FLAGGING OR STREET REPAIRS REQUIRED SINCE ALL MAIN WAS INSTALLED BY DIRECTIONAL BORE WHICH LOWER CONTRACT COST $23,000
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026163300 | 558 | EX | RETIRE 800' OF 4"BSLP MAIN | 2023-03-16 | PARKWAY DR | B | 105.0102 | 21.45 | -83.5602 | -80% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026163700 | 566 | EX | RETIRE 4"BSLP SERVICE LINE | 2022-04-08 | 125 BARR ST PARISH | B | 105.0102 | 1327.16 | 1222.1498 | 1,164% |  |  | 0 | CAPITAL SERVICE LINE WAS ABANDONED WITH JOB NUMBER 18-0268433-01 TIE IN A1A2. LSHARON
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026163900 | 2000 | EX | CONFLICT ASSESSMENT | 2022-03-15 | 1200 S BROADWAY ST 101 | B | 2275 | 0 | -2275 | 100% |  |  | 0
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026164400 | 557 | EX | EMER - INSTALL 10'-2" PMMP | 2022-02-08 | ANTIGUA DR | A | 13748.6188 | 10363.46 | -3385.1588 | -25% | 10 | 7 | 1480.4943
KY | KY - WEST | 2621 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026164500 | 558 | EX | EMER - RETIRE 10'-2" PMP | 2022-02-08 | ANTIGUA DR | A | 109.7476 | 111.44 | 1.6924 | 2% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026164900 | 557 | EX | EMER-INSTALL 4' OF 3"PMMP MAIN | 2022-02-01 | TATES CREEK | A | 14982.0392 | 15536.92 | 554.8808 | 4% | 4 | 4 | 3884.23 | INSTALLED 4' OF 030 P DUE TO EXC DMG TEST AT 90# FOR 20 MIN PER FOL APPROVA L, SOAP TEST TWO 030 EF CPLGS AT OP FOR 5 MIN OK. TEST FOR SEC DMG OK. WHIMES 02/17/2022
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026165000 | 558 | EX | EMER-RETIRE 4' OF 3"PMP MAIN | 2022-02-01 | TATES CREEK | A | 100.2728 | 119.3 | 19.0272 | 19% |  |  | 0 | COMPLETED W/ JO 22026164900
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026165400 | 584 | EX | RETIRE REG STATION #1203 | 2022-06-22 | 1321 BIG POND CR | F | 4576.607 | 5686.24 | 1109.633 | 24% |  |  | 0 | STATION RETIRED ALL PIPEING REMOVED 06-22-2022 AJPARKS
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026166200 | 561 | EX | INSTALL 20' OF 3"PMMP MAIN | 2022-05-04 | 1200 S BROADWAY ST | B | 28323.8584 | 23237.34 | -5086.5184 | -18% | 20 | 14 | 1659.81
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026166300 | 562 | EX | RETIRE 12' OF 3"PMP MAIN | 2022-05-04 | 1200 S BROADWAY ST | B | 62.3079 | 90.73 | 28.4221 | 46% |  |  | 0
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 22026166900 | 557 | EX | INSTALL 2010' - 8" & 6" PMMP | 2023-11-08 | 1814 RICHMOND RD | B | 400337.2549 | 525084.39 | 124747.1351 | 31% | 2010 | 1910 | 274.9133
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 22026167000 | 558 | EX | RETIRE 2260' OF 4-8" BSLP | 2023-12-12 | RICHMOND RD | B | 89.0305 | 0 | -89.0305 | 100% |  |  | 0
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 22026167100 | 2000 | EX | INVESTIGATE ROAD ROW | 2023-11-01 | RICHMOND RD | B | 4587 | 0 | -4587 | 100% |  |  | 0
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 22026167200 | 557 | EX | INSTALL 720'- 4" PMMP | 2023-01-23 | JEFFERSON ST | B | 309266.4996 | 293269.78 | -15996.7196 | -5% | 720 | 754 | 388.952 | ADETOMIWA FALADE 8/29/2023. JOB IS CURRENTLY SHOWING LEVEL 1 UNDER RUN BUT $35,000 IN PAVING WAS PROCESSED THIS WEEK. ONCE THIS PAYMENT IS APPLIED TO THIS JOB ORDER, NO VARIANCE PAPERWORK SHOULD BE REQUIRED. THE PAVING WAS PERFORMED BY PRIVATE CONTRACTOR INSTEAD OF PIPELINE CONTRACTOR WHICH SAVED THE COST OF PAVING.
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 22026167300 | 558 | EX | RETIRE 720'-4" BS-LP | 2023-02-13 | JEFFERSON ST | B | 62.2578 | 0 | -62.2578 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026167400 | 557 | EX | EMER - INSTALL 5'-3" PMLP | 2022-02-09 | 365 ROOSEVELT BV | A | 3781.5061 | 0 | -3781.5061 | 100% | 5 | 5 | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026167500 | 558 | EX | EMER - RETIRE 5'-3" PLP | 2022-02-09 | 365 ROOSEVELT BV | A | 109.7476 | 0 | -109.7476 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026167600 | 557 | EX | INSTALL 6' OF 3"PMLP MAIN | 2022-10-26 | 595 ALBANY RD | A | 16229.6788 | 8748.35 | -7481.3288 | -46% | 6 | 4 | 2187.0875 | CUT OUT 4' SECTION OF 3" MAIN. TESTED DROP IN PIECE 90#5MINS, TG. ST LTI, TG. BHBNGF. 2 17LB ANODES INSTALLED. PRSSURE NEVER DROPPED ON GAUGES. PURGED ALL AIR OUT BEFORE GAS UP. R.CRAWFORD 10-27-22
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026167700 | 558 | EX | RETIRE 6' OF 3"CSLP MAIN | 2022-10-26 | 595 ALBANY RD | A | 100.2728 | 9674.55 | 9574.2772 | 9,548% |  |  | 0 | CUT OUT 4' SECTION OF LEAKING 3" MAIN, TESTED DROP IN PIECE 90#20MINS, TG. ST LTI. TG. BHBNGF. INST. 2 17LB ANODES. PRESSURE NEVER DROPPED ON GAUGES. PURGED ALL AIR OUT BEFORE GAS UP. R.CRAWFORD 10-27-22
KY | KY - WEST | 2621 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026168800 | 909 | EX | ST. JAMES HVAC UPGRADE | 2022-03-16 | 1314 WINCHESTER RD | F | 37587.0767 | 24656.22 | -12930.8567 | -34% |  |  | 0 | MONITOR WHILE ACP SWAPS RTU STATION SET TO LOCAL MODE GC ADVISED CC 58614 UPGRADE RTU ON 3-16-22 JOSH MULLINS
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026171300 | 2000 | EX | INVESTIGATE AND OBTAIN U/E | 2022-11-07 | 804 CHEVY CHASE TE | A | 7489 | 0 | -7489 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026172800 | 566 | EX | RETIRE 5' OF 3"PLP S/L | 2022-03-16 | 151 M L KING BV | B | 58.5954 | 0 | -58.5954 | 100% |  |  | 0 | ABANDONED CAPITAL SERVICE LINE WITH ABANDON JOB # 18-0268434-00. LSHARON
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026172900 | 565 | EX | INSTALL 5' OF 4"PMLP S/L | 2022-03-15 | 151 M L KING BV | B | 13312.2384 | 3113 | -10199.2384 | -77% | 6 |  | 0
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 22026173000 | 909 | EX | 2022 SCADA VISABILITY PROGRAM | 2022-10-04 | ALUMNI DR | F | 30164.6195 | 47294.28 | 17129.6605 | 57% |  |  | 0 | CC# 66617 INSTALLED NEW MIWI350 SMCHOLAN 10-4-2022
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 22026173600 | 909 | EX | 2022 SCADA VISIBILITY PROGRAM | 2022-09-28 | 1313 OLD FRANKFORT PK | F | 31941 | 25271.05 | -6669.95 | -21% |  |  | 0 | INSTALLED NEW MIWI350 EBLANTON 9-28-2022
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 22026173800 | 909 | EX | 2022 SCADA VISIBILITY PROGRAM | 2022-09-29 | 1521 CONTINENTAL SQ | F | 30164.6195 | 24972.3 | -5192.3195 | -17% |  |  | 0 | WITH ACP CONTRACTOR WHILE THEY INSTALL POLE FOR COMM EQUIPMENT CC 66318 05-10-2022 RHAYES CC 1924 INSTALLED MIWI350 UNABLE TO PERFORM P2P NDAVIS WORKING ON TICKET MONITORED 30 MINUTES RHAYES 09-29-2022
KY | KY - WEST | 2621 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 22026174400 | 909 | EX | 2022 SCADA VISIBILITY PROGRAM | 2022-10-11 | 600 WOODWARD LN REAR | F | 29658.8599 | 28643.37 | -1015.4899 | -3% |  |  | 0 | INSTALL POLES FOR COMM EQUIPMENT 05-10-2022 CC 66285 RHAYES
KY | KY - WEST | 2621 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 22026174500 | 909 | EX | 2022 SCADA VISIBILITY PROGRAM | 2022-10-05 | 3090 HARRODSBURG RD | F | 29658.8599 | 29029.69 | -629.1699 | -2% |  |  | 0 | CC# 66436 CC# 79698 CC# 2587 CMCOX 10/5/22 INSTALLED NEW MIWI350 CCOX 10-05-2022
KY | KY - WEST | 2621 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 22026174600 | 909 | EX | 2022 SCADA VISIBILITY PROGRAM | 2022-09-27 | 4290 HARRODSBURG RD | F | 29658.8599 | 38527.05 | 8868.1901 | 30% |  |  | 0 | CC# 66475 CC#1503 INSTALLED NEW MIWI350 WITH SUPER SOLAR KIT 9-27-22 CCOX
KY | KY - WEST | 2621 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026175700 | 0001 | EX | SCADA MATERIAL ORDER | 2022-10-17 | STATE WIDE |  | 134999 | 0 | -134999 | 100% |  |  | 0 | GES - JOB ORDER USED IN CONJUNCTION WITH PBR TO PRE-ORDER MATERIAL FOR SCAD A VISABILITY PROJECT
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026177200 | 2000 | EX | INVESTIGATE & MAP MAINS | 2023-01-06 |  |  | 3206 | 0 | -3206 | 100% |  |  | 0 | CONFLICT ASSESMENT COMPLETED AND REVISIONS BY CITY TO ELLIMINATE KNOW CONFL ICTS COMPLETE. D.LEMONS 1/6/2023
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026177900 | 557 | EX | INSTALL 8' OF 6"PMMP MAIN | 2022-06-30 | 334 WILSON DOWNING RD | B | 29164.4 | 36900.11 | 7735.71 | 27% | 8 | 9 | 4100.0122
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026178000 | 558 | EX | RETIRE 4' OF 6"CSMP MAIN | 2022-06-30 | 334 WILSON DOWNING RD | B | 75.4968 | 876.45 | 800.9532 | 1,061% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026178100 | 559 | EX | INSTALL 20' OF 6"PMLP MAIN | 2022-05-11 | 1119 COOPER DR | B | 11448.7503 | 14787.97 | 3339.2197 | 29% | 20 | 55 | 268.8722
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026178500 | 561 | EX | INSTALL 44'-6" PMMP | 2022-08-22 | 620 PARKSIDE DR | B | 72684.0107 | 65200.97 | -7483.0407 | -10% | 44 | 63 | 1034.936
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026178600 | 562 | EX | RETIRE 26'-6" CSMP | 2022-08-22 | 620 PARKSIDE DR | B | 73.9724 | 1859.72 | 1785.7476 | 2,414% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026178800 | 2000 | EX | INVESTIGATE NEW HP EASEMENT | 2023-01-09 | 1320 BIG POND CR | A | 4875 | 0 | -4875 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026178900 | 557 | EX | INSTALL 620' OF 12"CSHP MAIN | 2023-06-29 | 1320 BIG POND CR | B | 330116.9371 | 268220 | -61896.9371 | -19% | 620 | 590 | 454.6102
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026179100 | 558 | EX | RETIRE 520' OF 12"MJBSHP | 2023-06-29 | 1320 BIG POND CR | B | 131.2422 | 3152.18 | 3020.9378 | 2,302% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026179200 | 563 | EX | INSTALL 50' OF 6"PMLP S/L | 2022-09-14 | 941 MANCHESTER ST | B | 47001.2003 | 45896.9 | -1104.3003 | -2% | 50 |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026179300 | 562 | EX | RETIRE 82'-2"&4" PMMP | 2022-03-10 | EDGELAWN AV | B | 73.9724 | 82.8 | 8.8276 | 12% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026180100 | 555 | EX | INSTALL 805' OF 2"/4"PMMP MAIN | 2022-08-30 | 5035 KEENE RD HOUSE | B | 54482.6036 | 116760.6 | 62277.9964 | 114% | 900 | 761 | 153.4305 | TWALKER/KY 09-08-22: PROJECT OVER RUN DUE TO ROCK ENCOUNTERED IN CONSTRUCTI ON REQUIRING ROCK BORE AND OPEN CUT ROCK WHICH INCREATED CONTRACT COST BY $30,000. WMS WOULD NOT ALLOW REVISION OF PROJECT DUE TO UNPAID INVOICES. COMPANY LABOR INCREASED BY OVER $16,000 DUE TO EXTRA TIME FOR CONSTRUCTION AND SEGA WAS $6000 THAN ESTIMATE TWALKER/KY 01-24-23: LEVEL 2 VARIANCE REPORT ADDED TO WMS.DOCS.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026180200 | 2000 | EX | INVESTIGATE ROAD RIGHT OF WAY | 2022-06-10 | 5035 KEENE RD HOUSE | A | 3754 | 0 | -3754 | 100% |  |  | 0
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 22026180600 | 2000 | EX | INVESTIGATE EASEMENT | 2022-04-07 | 2751 LEESTOWN RD | B | 2536 | 5169.39 | 2633.39 | 104% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026180900 | 557 | EX | EMER-INSTALL 4' OF 2"PMMP | 2022-02-28 | WESTON PARK | A | 3916.7503 | 3753.68 | -163.0703 | -4% | 4 | 5 | 750.736
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026181000 | 558 | EX | EMER-RETIRE 4' OF 2"PMMP | 2022-02-28 | WESTON PARK/WESTON CT | A | 75.4968 | 0 | -75.4968 | 100% |  |  | 0
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 22026181200 | 2000 | EX | INVESTIGATE EASEMENT | 2023-11-03 | 4630 BOSWORTH LN | B | 2536 | 3551.44 | 1015.44 | 40% |  |  | 0 | AWEBER 11/3/23 - LAND PS&I WORK COMPLETED PER CBOWLIN. INVESTIGATE EASEMENT AT 4630 BOSWORTH LANE, LEX.
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 22026181400 | 2000 | EX | REG STATION 1084 PS&I | 2023-09-15 | 3090 HARRODSBURG RD | B | 10000 | 0 | -10000 | 100% |  |  | 0 | AWEBER 9/15/23 - JO EXECUTED TO 583 JO ON PROJECT, TIME USED FOR LAND TO IN VESTIGATE EASEMENTS AND SURVEY FOR REG STATION.
KY | KY - WEST | 2621 | U133035 | Patteson,Ashley Johnson | Wood,Brittany | Mozina,Chris | 22026181900 | 909 | EX | LAB EQUIPMENT INSTALL | 2022-09-15 | 2001 MERCER RD | F | 15945.3111 | 5312.84 | -10632.4711 | -67% |  |  | 0
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 22026182000 | 555 | EX | INSTALL 2185' OF 2" PMMP | 2022-09-27 | 112 TURNER COMMONS WY | B | 110360.5276 | 141899.3 | 31538.7724 | 29% | 2200 | 2000 | 70.9497 | AWEBER 01/24/2023 - PROJECT OVERRUN DUE PRIMARILY TO LAND OWNER ISSUES & EXPANSIVE SEWER LINE CAMERA WORK PERFORMED BY BUCHANON. EASEMENT FROM FIRST LAND OWNER FELL THROUGH DUE TO HOA VOTE, INCREASING INSTALLATION BY +200' & PRIVATE EASEMENT. PROJECT ENCOUNTERED ROCK BORE ADDING ~34 HOURS TO DURATIO N. OVERRUN BUCHANON COST $17K + LAND COST $11K & INCREASED SEGA RATE $6K LE D TO VARIANCE.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026182200 | 2000 | EX | OBTAIN NEW HP EASEMENT | 2023-08-15 | 375 LISLE INDUSTRIAL RD |  | 8052 | 0 | -8052 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026182800 | 557 | EX | EMER-INSTALL 3' OF 2"PMMP | 2022-04-20 | SUNNY LANDINGS TL | A | 4826.1382 | 4419.13 | -407.0082 | -8% | 3 | 3 | 1473.0433 | INSTALLED 3' OF 2" PMMP DUE TO EXCAVATION DAMAGE, TESTED MAIN PIPE AT 90# F OR 20 MIN PER FOL APPROVAL OK, SOAP TEST 2 020 EF CPLGS AT OP FOR 5 MIN OK. INSTALLED MARKER BALLS ON CPLGS. MAP REVISED. WHIMES
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026182900 | 558 | EX | EMER-RETIRE 3' OF 2"PMMP | 2022-04-20 | SUNNY LANDING | A | 74.2578 | 2.72 | -71.5378 | -96% |  |  | 0 | RETIRED 3' OF 020 PMMP DUE TO EXCAVATION DAMAGE. WHIMES 04/20/2022
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 22026183100 | 561 | EX | INSTALL 3090' OF 2-4" PMMP | 2023-04-28 | LEESTOWN RD | B | 533028.4351 | 609662.9 | 76634.4649 | 14% | 3090 | 3183 | 191.5372 | PROJECT COMPLETE
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 22026183200 | 562 | EX | RETIRE 3765' OF 2-4" CS & PMMP | 2023-09-07 | LEESTOWN RD | B | 138.8485 | 273.03 | 134.1815 | 97% |  |  | 0 | PROJECT COMPLETED
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 22026183600 | 555 | EX | INSTALL 1700'-2" PMMP | 2022-06-22 | WINDFLOWER WY LT107 | B | 46580.9585 | 51519.58 | 4938.6215 | 11% | 1700 | 1860 | 27.6987
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026183700 | 555 | EX | INSTALL 100' OF 2"PMMP MAIN | 2022-10-11 | 3405 FRASERDALE DR | A | 12739.3747 | 19814.52 | 7075.1453 | 56% | 100 | 199 | 99.5705 | INSTALLED 199' OF 020 MAIN. TEST 199' OF MAIN FOR 1HR AT 90LBS. FOL APPROVED.SOAP TEST 2'' EFC AT OP OF FINAL TIE IN. SOAP TEST END CAP ON MONITORING GAUGE AT OP.TEST OK.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026184400 | 2000 | EX | CONFLICT ASSESSMENT | 2022-06-10 | 240 CANARY RD | A | 4720 | 0 | -4720 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026184600 | 561 | EX | INSTALL 64' OF 2"PMMP MAIN | 2022-07-11 | 240 CANARY RD | B | 17899.1411 | 16772.5 | -1126.6411 | -6% | 60 | 40 | 419.3125
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026184700 | 562 | EX | RETIRE 52' OF 2"PMMP MAIN | 2022-07-11 | 240 CANARY RD | B | 74.2578 | 0 | -74.2578 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026184800 | 561 | EX | INSTALL 3775'-2" PMMP | 2023-02-28 | LONE OAK DR | B | 567138.2381 | 689655.43 | 122517.1919 | 22% | 4390 | 4210 | 163.8136
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026184900 | 562 | EX | RETIRE 3315'-2"&4"BSLP | 2023-04-11 | LONE OAK DR | B | 72.7393 | 23.53 | -49.2093 | -68% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026185001 | 561 | EX | INSTALL 260' OF 2"PMMP MAIN | 2022-10-05 | 1602 CLAYS MILL RD | B | 27065.0582 | 30483.21 | 3418.1518 | 13% | 260 | 228 | 133.6983
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026185301 | 555 | EX | INSTALL 875' OF 2"PMMP MAIN | 2022-11-17 | COCOS WY LT1 | B | 74170.089 | 69561.33 | -4608.759 | -6% | 875 | 725 | 95.9467
KY | KY - WEST | 2621 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026186000 | 909 | EX | EXCHANGE ELECTRONIC COMPONENTS | 2022-05-27 | 1511 RUSSELL CAVE RD | F | 5480.5156 | 3201.06 | -2279.4556 | -42% |  |  | 0 | ACP REMOVED ERX REPLACED WITH MIWI CCOX RHAYES 05-27-2022
KY | KY - WEST | 2621 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026186100 | 910 | EX | RETIRE ELECTRONIC COMPONENTS | 2022-05-27 | 1511 RUSSELL CAVE RD | F | 124.5156 | 175.52 | 51.0044 | 41% |  |  | 0 | ACP REPLACED ERX WITH MIWI RHAYES CCOX 05-27-2022 ACP REPLACED ERX WITH MIWI RHAYES CCOX 05-27-2022
KY | KY - WEST | 2621 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026186600 | 909 | EX | EXCHANGE ELECTRONIC COMPONENTS | 2022-05-19 | PRESS AV | F | 4216.5438 | 616.42 | -3600.1238 | -85% |  |  | 0 | INSTALLED MIWI 350 AND TUBING, CCC 67481 CMCHOLAN 5-19-2022 NOT ON SITE, TURNED IN PAPERWORK IN WINCHESTER, NO CCC TICKET, CMCHOLAN 5-20-2022
KY | KY - WEST | 2621 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026186700 | 910 | EX | RETIRE ELECTRONIC COMPONENTS | 2022-05-19 | PRESS AV | F | 124.5156 | 485.53 | 361.0144 | 290% |  |  | 0 | REMOVED ERX, CCC 67481 CMCHOLAN 5-19-2022 RWILLIAMS EX CAPITAL JOB
KY | KY - WEST | 2621 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026187200 | 909 | EX | EXCHANGE ELECTRONIC COMPONENTS | 2022-05-26 | 3620 WILLOW SPRINGS | F | 4745.0565 | 1831.39 | -2913.6665 | -61% |  |  | 0 | CCC# 68726 INSTALLED NEW MIWI 350 AJPARKS
KY | KY - WEST | 2621 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026187300 | 910 | EX | RETIRE ELECTRONIC COMPONENTS | 2022-05-26 | 3620 WILLOW SPRINGS | F | 124.5156 | 185.7 | 61.1844 | 49% |  |  | 0 | CCC# 68726 RETIRED ERX 05/26/2022 APARKS
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026187800 | 561 | EX | INSTALL 10' OF 4"PMLP MAIN | 2022-05-25 | SPRINGRIDGE DR | B | 18153.0818 | 29076.83 | 10923.7482 | 60% | 10 | 24 | 1211.5346
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026187900 | 562 | EX | RETIRE 8' OF 4"PMLP MAIN | 2022-05-25 | SPRINGRIDGE DR | B | 74.2578 | 0 | -74.2578 | 100% |  |  | 0
KY | KY - WEST | 2621 | U937670 |  |  |  | 22026188900 | 2000 | EX | ENE PS&I FOR DURBIN VALVE REPL | 2023-06-08 | 8721 DURBIN LN | B | 7500 | 0 | -7500 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026192300 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-06-13 | 403 E THIRD ST | F | 4801.1928 | 281.87 | -4519.3228 | -94% |  |  | 0 | CHANGED ERX TO MIWI 350, P2P OK, CCC 70245 CMHOLAN 6-13-2022
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026192400 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-06-13 | 403 E THIRD ST | F | 124.8731 | 443.37 | 318.4969 | 255% |  |  | 0 | REMOVED ERX TO INSTALL MIWI, CCC 70245 CMCHOLAN 6-13-2022 INSTALLED NEW MIWI350
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026195000 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-08-29 | 5540 ATHENS WALNUT PK | F | 4801.1928 | 5607.88 | 806.6872 | 17% |  |  | 0 | SWAP COMP. PARKS 08-29-22 1545 CCC# 78985 RETIRED OLD ERX INSTALLED NEW MIWI350 AJPARKS 8-29-2022
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026195100 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-08-29 | 5540 ATHENS WALNUT PK | F | 124.8731 | 248.95 | 124.0769 | 99% |  |  | 0 | REMOVAL COMP. APARKS 08-29-22 1044 CCC# 78985 RETIRED OLD ERX INSTALLED NEW MIWI350 AJPARKS 8-29-2022
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026197100 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-09-07 | TOWNLEY DR | F | 4801.1928 | 5373.93 | 572.7372 | 12% |  |  | 0 | CCC 79940 RETIRED OLD ERX INSTALLED NEW MIWI350 9-7-2022
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026197200 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-09-07 | TOWNLEY DR | F | 124.8731 | 251.1 | 126.2269 | 101% |  |  | 0 | CCC 79940 RETIRED OLD ERX INSTALLED NEW MIWI350 EBLANTON 9-7-2022
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026197300 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-10-19 | 110 E TIVERTON WY | F | 4801.1928 | 6904.6 | 2103.4072 | 44% |  |  | 0 | CC# 3980 CMCOX 10/19/22 INSTALLED NEW MIWI350 CCOX 10-19-22
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026197400 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-10-19 | 110 E TIVERTON WY | F | 124.8731 | 305.47 | 180.5969 | 145% |  |  | 0 | CC# 3980 CMCOX 10/19/22 RETIRED OLD ERX CCOX 10-19-22
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026197700 | 557 | EX | INSTAL 3'-2" PMMP | 2022-05-21 | SNOWY EGRET WY | A | 2387.9592 | 1311.83 | -1076.1292 | -45% | 3 | 3 | 437.2767 | HIT MAIN BY CONCRETE STAKE.MADE SAFE BY SQUEEZING OFF IN TWO BELL HOLES. REPLACED DAMAGED SECTION OF PIPE.TESTED 10FT OF 020 AND PURGE TEE FOR 1HR 90LBS.TEST OK.SOAP TEST END CAP AND 2EFC'S CPLGS AT OP.TEST OK BHB NGF
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026197800 | 558 | EX | RETIRE 3'-2" PMMP | 2022-05-21 | SNOWY EGRET WY | A | 76.9137 | 914.45 | 837.5363 | 1,089% |  |  | 0 | HIT MAIN BY CONCRETE STAKE.MADE SAFE BY SQUEEZING OFF IN TWO BELL HOLES. REPLACED DAMAGED SECTION OF PIPE.TESTED 10FT OF 020 AND PURGE TEE FOR 1HR 90LBS.TEST OK.SOAP TEST END CAP AND 2EFC'S CPLGS AT OP.TEST OK BHB NGF
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026198601 | 555 | EX | INSTALL 1900' OF 2"PMMP MAIN | 2022-10-20 | DAHLIA DR LT78 | B | 50146.9852 | 71556.52 | 21409.5348 | 43% | 1900 | 2208 | 32.4078
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026199100 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-09-02 | 800 NEWTOWN CT | F | 4801.1928 | 5602.7 | 801.5072 | 17% |  |  | 0 | CCC 79615 RETIRED OLD ERX INSTALLED NEW MIWI350 EBLANTON 9-2-2022
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026199200 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-09-02 | 800 NEWTOWN CT | F | 124.8731 | 880.44 | 755.5669 | 605% |  |  | 0 | CCC 79615 RETIRED OLD ERX INSTALLED NEW MIWI350 EBLANTON 9-2-2022
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026200500 | 566 | EX | RETIRE 2' OF 3"PLP S/L | 2022-08-15 | 213 E 3RD ST | B | 62.4365 | 0 | -62.4365 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026200600 | 565 | EX | INSTALL 15' OF 3"/4"PMLP S/L | 2022-08-15 | 213 E 3RD ST | B | 11118.4162 | 10449.59 | -668.8262 | -6% | 13 |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026202200 | 555 | EX | INSTALL 125' OF 2" PMMP MAIN | 2022-07-14 | 1289 BARLEYS PASS | B | 8841.6395 | 11459.71 | 2618.0705 | 30% | 125 | 104 | 110.1895
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026202900 | 560 | EX | RETIRE 135' OF 2"PMP MAIN | 2022-08-30 | 5035 KEENE RD | B | 78.4365 | 2.29 | -76.1465 | -97% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026203900 | 584 | EX | RETIRE PAPER GAUGE | 2022-10-05 | 3090 HARRODSBURG RD | F | 78.4365 | 0 | -78.4365 | 100% |  |  | 0 | RETIRED PAPER CHART CCOX10-05-2022
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026204000 | 584 | EX | RETIRE PAPER GAUGE | 2022-09-27 | 4290 HARRODSBURG RD | F | 78.4365 | 157.99 | 79.5535 | 101% |  |  | 0 | RETIRED PAPER CHART CHRIS COX 9-27-22
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026204200 | 584 | EX | RETIRED GAUGE | 2022-10-04 | ALUMNI DR | F | 76.9137 | 0 | -76.9137 | 100% |  |  | 0 | RETIRED PAPER CHARTS SMCHOLAN 10-04-2022
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026204900 | 2000 | EX | INVESTIGATE ROAD R/W | 2022-09-23 | COCOS WY | B | 2543 | 0 | -2543 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026206900 | 557 | EX | EMER-INSTALL 16' OF 4"/6"PMLP | 2022-07-01 | 931 AURORA AV | A | 8399.775 | 11009.07 | 2609.295 | 31% | 36 | 18 | 611.615 | LEAKING POSI HOLD COUPLING.LEAKING OUT OF FITTING ON COUPLING. REPLACED 6'' TEE AND 19FT OF MAIN.TESTED MAIN FOR 1HR AT 90LBS.TEST OK. SOAP TEST FINAL TIE INS AT OP FOR 5MINS AT OP.TEST OK. BHB NGF.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026207000 | 558 | EX | EMER-RETIRE 14' OF 6"BSLP | 2022-07-01 | 931 AURORA AV | A | 60.0112 | 11230.19 | 11170.1788 | 18,614% |  |  | 0 | LEAKING POSI HOLD COUPLING.LEAKING OUT OF FITTING ON COUPLING. REPLACED 6'' TEE AND 19FT OF MAIN.TESTED MAIN FOR 1HR AT 90LBS.TEST OK. SOAP TEST FINAL TIE INS AT OP FOR 5MINS AT OP.TEST OK. BHB NGF.
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026208900 | 561 | EX | EMER - INSTALL ~10'-8" CSHP | 2022-07-07 | 1930 CLAYS MILL RD | B | 32930.2498 | 59795.62 | 26865.3702 | 82% | 10 |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026209400 | 586 | EX | RETIRE CHAIN LINK FENCE | 2022-06-28 | 1321 BIG POND CR | F | 65.0112 | 0 | -65.0112 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026209500 | 586 | EX | RETIRE CHAIN LINK FENCE | 2022-05-10 | 427 TRANSPORT CT | F | 65.0112 | 0 | -65.0112 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026209800 | 586 | EX | RETIRE VAULT STRUCTURE | 2022-11-16 | 800 PRESS AV | F | 1027.5809 | 0 | -1027.5809 | 100% |  |  | 0 | PIT RETIRED AND FILLED IN
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026210000 | 588 | EX | RETIRE ELECTRONICS | 2022-07-14 | 451 HARBISON RD | F | 65.0112 | 249.16 | 184.1488 | 283% |  |  | 0 | RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07-14-2022
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026210100 | 557 | EX | EMER - INSTALL 6'-4" PMMP | 2022-07-05 | 601 CLAYS MILL | A | 4810.9373 | 5514.88 | 703.9427 | 15% | 6 | 16 | 344.68 | DAMAGED SECTION OF PIPE DUE TO EXCAVATOR ERROR.MADE SAFE BY SQUEEZING OFF IN BELLHOLES.OC 16FT NEW MAIN DUE TO EXCAVATION WHERE DAMAGE WAS TOO DEEP. TESTED MAIN 1HR AR 90LB.TEST OK.SOAP TEST EFC'SAT OP.TEST OK BHB NGF
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026210200 | 558 | EX | EMER - RETIRE 6'-4" PMMP | 2022-07-05 | 601 CLAYS MILL | A | 63.5475 | 95.05 | 31.5025 | 50% |  |  | 0 | DAMAGED SECTION OF PIPE DUE TO EXCAVATOR ERROR.MADE SAFE BY SQUEEZING OFF IN BELLHOLES.OC 16FT NEW MAIN DUE TO EXCAVATION WHERE DAMAGE WAS TOO DEEP. TESTED MAIN 1HR AR 90LB.TEST OK.SOAP TEST EFC'SAT OP.TEST OK BHB NGF
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026210301 | 555 | EX | INSTALL 850' OF 4"PMMP MAIN | 2023-01-11 | 554 S FORBES RD VAUGHN | B | 192098.991 | 172217.52 | -19881.471 | -10% | 851 | 818 | 210.5349
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026210600 | 558 | EX | EMER-RETIRE 50' OF 3"BSLP MAIN | 2022-07-10 | LIMESTONE | A | 5032.3621 | 2854.75 | -2177.6121 | -43% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026211400 | 560 | EX | PAPER ONLY-RETIRE MP MAIN | 2022-06-22 | BIG POND | B | 65.0112 | 0 | -65.0112 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026211700 | 576 | EX | RETIRE LAND AND REG SITE | 2023-01-24 | 247 BURKE RD | F | 29152.0112 | 46152.61 | 17000.5988 | 58% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026212400 | 2000 | EX | INVESTIGATE AND MAP MAINS | 2022-12-28 | CULZEAN CT |  | 13587.2625 | 0 | -13587.2625 | 100% |  |  | 0 | LFUCG IS IN PROCESS OF OBTAINING EASEMENTS. START DATE PUSHED UNTIL LFUCG G IVES NOTICE TO PROCEED. D.LEMONS 12/28/22
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 22026212500 | 583 | EX | REPLACE VALVES AT R-1084 | 2023-09-06 | 3090 HARRODSBURG RD | F | 14531.0267 | 9402.89 | -5128.1367 | -35% |  |  | 0 | HELP CCOX WITH VALVE REPLACEMENT, CMCHOLAN 9-5-23 1600 CC# 43383 PAPERWORK ONLY. NO CC# REQUIRED. NOT ON SITE.
KY | KY - WEST | 2621 | U938437 |  |  |  | 22026212600 | 584 | EX | RETIRE STATION VALVES R-1084 | 2023-09-06 | 3090 HARRODSBURG RD | F | 119.4953 | 1269.98 | 1150.4847 | 963% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026212700 | 2000 | EX | INVESTIGATE MAINS | 2022-11-22 | 2595 MILITARY PK |  | 2226 | 0 | -2226 | 100% |  |  | 0 | VACUME EXCAVATION CONFIRMED NO CONFLICT WITH PROPOSED ROADWAY IMPROVEMNTS A S SHOWN IN PLANS PROVIDED. D.LEMONS 11/22/2022
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 22026213000 | 558 | EX | RETIRE 2015'-8/4/2" BSMP/CSMP | 2023-11-12 | 1900 RICHMOND RD | B | 89.0305 | 220 | 130.9695 | 147% |  |  | 0
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 22026213100 | 566 | EX | RETIRE 3"BSMP SERVICE LINE | 2023-12-05 | 1900 RICHMOND RD | B | 63.4096 | 0 | -63.4096 | 100% |  |  | 0
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 22026213200 | 565 | EX | INSTALL 30' OF 2-4" PMMP S/L | 2023-12-05 | 1900 RICHMOND RD | B | 27880.5873 | 33409.7 | 5529.1127 | 20% | 340 |  | 0
KY | KY - WEST | 2621 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026214700 | 910 | EX | ST. JAMES RTU PANEL | 2022-03-16 | 1314 WINCHESTER RD | F | 55.5311 | 0 | -55.5311 | 100% |  |  | 0 | UPGRADED RTU JOSH MULLINS
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 22026214800 | 557 | EX | EMER INSTALL 2' - PMMP | 2022-07-27 | 2492 SHADY HILLS LN | A | 2418.3858 | 8176.85 | 5758.4642 | 238% | 2 | 2 | 4088.425
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 22026214900 | 558 | EX | EMER RETIRE 2'-PMP | 2022-07-27 | 2492 SHADY HILLS LN | A | 84.9152 | 0 | -84.9152 | 100% |  |  | 0
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 22026215000 | 557 | EX | EMER INSTALL 2'-4" PMLP | 2022-07-28 | 444 KENTON ST | A | 3659.4376 | 9400.14 | 5740.7024 | 157% | 0 | 2 | 4700.07
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 22026215100 | 558 | EX | EMER RETIRE 2'-4" PLP | 2022-07-28 | 444 KENTON ST | A | 84.9152 | 0 | -84.9152 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026215300 | 557 | EX | EMER - INSTALL 20'-2" PMIP | 2022-07-21 | VERSAILLES | A | 10433.2304 | 15168.73 | 4735.4996 | 45% | 20 | 10 | 1516.873
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026215400 | 558 | EX | EMER - RETIRE 5'-2" PMIP | 2022-07-21 | VERSAILLES | A | 80.5311 | 0 | -80.5311 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026215500 | 557 | EX | EMER - INSTALL 5'-2" PMMP | 2022-07-21 | BRIDLE CT | A | 4479.378 | 6774.27 | 2294.892 | 51% | 5 | 4 | 1693.5675
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026215600 | 558 | EX | EMER - RETIRE 5'-2" PMMP | 2022-07-21 | BRIDLE CT | A | 84.9152 | 0 | -84.9152 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026215900 | 559 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | 2022-07-13 | BIRKENHEAD DR | A | 3722.1191 | 1854.5 | -1867.6191 | -50% | 3 | 3 | 618.1667 | REPLACED 3FT SECTION OF MAIN. TESTED NEW SECTION OF MAIN FOR 20MINS AT 90LBS.TEST OK SOAP TEST EFC'S AT OP FOR 5MINS.TEST OK. BHBNGF
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026216000 | 560 | EX | EMER-RETIRE 3' OF 2"PAMP MAIN | 2022-07-13 | BIRKENHEAD DR | A | 84.9152 | 143.19 | 58.2748 | 69% |  |  | 0 | REPLACED 3FT SECTION OF MAIN. TESTED NEW SECTION OF MAIN FOR 20MINS AT 90LBS.TEST OK SOAP TEST EFC'S AT OP FOR 5MINS.TEST OK. BHBNGF
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026216200 | 555 | EX | INSTALL 950' OF 2"/4"PMMP MAIN | 2022-09-09 | CALENDULA RD LT272 | B | 39269.0655 | 47379.78 | 8110.7145 | 21% | 950 | 1019 | 46.4963
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026216900 | 560 | EX | PAPER ONLY EXECUTE | 2022-04-29 | 1850 MERCER RD | B | 84.9152 | 0 | -84.9152 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026217300 | 566 | EX | RETIRE 3"PLP SERVICE LINE | 2022-09-08 | 124 N ASHLAND AV | B | 170.8304 | 0 | -170.8304 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026217400 | 566 | EX | RETIRE 6"PLP SERVICE LINE | 2022-10-06 | 301 WOODLAND AV | B | 144.8304 | 827.26 | 682.4296 | 471% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026217800 | 557 | EX | EMER-INSTALL 3' OF 4"PMLP MAIN | 2022-08-17 | 591 ROSEMILL DR | A | 6173.2589 | 12300.82 | 6127.5611 | 99% | 3 | 10 | 1230.082 | LEAK CLEARED USING DPI D311930 PW
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026217900 | 558 | EX | EMER-RETIRE 3' OF 4"BSLP MAIN | 2022-08-17 | 591 ROSEMILL DR | A | 170.8304 | 4448.33 | 4277.4996 | 2,504% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026218200 | 584 | EX | RETIRE PAPER GUAGE | 2022-07-28 | 3478 TATES CREEK RD | F | 339.1994 | 0 | -339.1994 | 100% |  |  | 0 | RETIRE PAPER CHART DUE TO ERX INSTALL AT ANOTHER STATION SMCHOLAN
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026218300 | 584 | EX | RETIRE PAPER GAUGE | 2022-07-28 | 2300 RICHMOND RD | F | 339.1994 | 0 | -339.1994 | 100% |  |  | 0 | RETIRED PAPER CHART DUE TO ERX INSTALL AT ANOTHER LOCATION
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026218800 | 909 | EX | INSTALL MI WIRELESS UNIT | 2022-10-06 | 108 SURFSIDE DR | F | 9310.2589 | 10259.75 | 949.4911 | 10% |  |  | 0 | CC# 79803 CC# 2675 CC# 2675 CMCOX 10/6/22 INSTALLED NEW MIWI350 CCOX 10-06-2022
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026219400 | 557 | EX | INSTALL 380' OF 4"PMMP MAIN | 2023-06-02 | 452 ROSE ST | B | 176409.6078 | 171665.76 | -4743.8478 | -3% | 381 | 494 | 347.5015
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026219500 | 558 | EX | RETIRE 380' OF 4"BSMP MAIN | 2023-06-08 | 452 ROSE ST | B | 89.0305 | 91.2 | 2.1695 | 2% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026220800 | 558 | EX | *PAPER ONLY* 2022 CAST IRON | 2022-10-19 | 4TH | B | 295.7645 | 0 | -295.7645 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026221200 | 557 | EX | EMER - INSTALL 8'-6"PMMP | 2022-08-31 | 1228 MANCHESTER | A | 32929.6819 | 11736.48 | -21193.2019 | -64% | 108 | 3 | 3912.16 | TEST 6 IN MAIN AT 90 LB FOR 20 MIN SOAP TEST EFC AT OP FOR 5 MIN
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026221300 | 558 | EX | EMER - RETIRE 8'-6" PMP | 2022-08-31 | 1228 MANCHESTER | A | 87.3224 | 595.27 | 507.9476 | 582% |  |  | 0 | REMOVED 2 FT OF 6 IN DAMAGE PIPE
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026222800 | 557 | EX | EMER-INSTALL 2' OF 4"PMMP MAIN | 2022-08-11 | 820 N LIMESTONE ST | A | 23837.8998 | 21988.24 | -1849.6598 | -8% | 2 | 2 | 10994.12
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026222900 | 558 | EX | EMER-RETIRE 2' OF 4"PMMP MAIN | 2022-08-11 | 820 N LIMESTONE ST | A | 89.0305 | 0 | -89.0305 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026223100 | 557 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | 2022-03-07 | 109 CAMBRIDGE LN | A | 4624.3747 | 4059.84 | -564.5347 | -12% | 3 | 3 | 1353.28 | COMPLETED PAPERWORK FOR JOB. R.CRAWFORD 10-11-22
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026223200 | 558 | EX | EMER-RETIRE 3' OF 2"PMP MAIN | 2022-03-07 | 109 CAMBRIDGE LN | A | 89.0305 | 125.23 | 36.1995 | 41% |  |  | 0 | R.CRAWFORD
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026223600 | 555 | EX | INSTALL 3000' OF 2"PMMP MAIN | 2023-08-23 | BAY SHOALS DR LT99 | B | 81410.7619 | 80798.26 | -612.5019 | -1% | 3000 | 2933 | 27.548
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026223700 | 561 | EX | INSTALL 1296'-2"&4" PMMP | 2023-04-12 | TUSCON DR | B | 306884.1479 | 286331.62 | -20552.5279 | -7% | 1296 | 1430 | 200.2319
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026223800 | 562 | EX | RETIRE 1212'-2",3"&4" CSMP | 2023-04-12 | TUSCON DR | B | 117.5985 | 0 | -117.5985 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026223900 | 561 | EX | INSTALL 1067'-4" PMMP | 2023-02-08 | BRANNON RD | B | 181608.1135 | 149979.89 | -31628.2235 | -17% | 1067 | 1095 | 136.9679
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026224000 | 562 | EX | RETIRE 1150'-4" PMMP | 2023-02-08 | BRANNON RD | B | 72.8379 | 0 | -72.8379 | 100% |  |  | 0
KY | KY - WEST | 2621 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026226900 | 0001 | EX | PAYROLL TRAINING | 2022-10-31 | 2001 MERCER RD | A | 6000 | 0 | -6000 | 100% |  |  | 0 | TWALKER/KY-THIS JOB ORDER IS TO DOCUMENT TRAINING COST, THERE IS NO MAPPING REQUIRED, NO WORK ORDER POLYGON, NO FACILITY TO CREATE AND NO UPRATE.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026227000 | 557 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | 2022-06-02 | FORT HARRODS | A | 5024.0582 | 5707.92 | 683.8618 | 14% | 3 | 3 | 1902.64 | INST 3" OF 2 P MP MAIN PER GAS STANDARDS. MCRAIG 9/30/22
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026227100 | 558 | EX | EMER-RETIRE 3' OF 2"PMP MAIN | 2022-06-02 | FORT HARRODS | A | 74.3089 | 316.08 | 241.7711 | 325% |  |  | 0 | ABN 3' OF 2" P MP MAIN DUE TO LEAK. PER GAS STANDARDS. MCRAIG 9/30/22
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026227200 | 910 | EX | RETIRE ELECTRONICS | 2022-12-15 | 4940 ATHENS BOONESBORO RD | F | 74.3089 | 0 | -74.3089 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026228000 | 557 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | 2022-09-21 | COSIMO | A | 4027.0582 | 2032.93 | -1994.1282 | -50% | 3 | 3 | 677.6433 | INSTALLED 3 FT OF 2 IN MAIN ON DAMAGE TEST FROM POINT A TO B 90 LB FOR 20 MIN TEST PURG TEE 90 LB FOR 5 MIN SOAP TEST 1 IN END CAP AT OP FOR 5 MIN SOAP TEST 2 EFC AT OP FOR 5 MIN BHB NO GAS FOUND
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026228100 | 558 | EX | EMER-RETIRE 3' OF 2"PMMP MAIN | 2022-09-21 | COSIMO | A | 74.3089 | 590.32 | 516.0111 | 694% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026228800 | 2000 | EX | INVESTIGATE EASEMENT/LAND RIGH | 2023-09-07 | COLUMBIA TE | B | 5556 | 0 | -5556 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026230100 | 557 | EX | EMER-INSTALL 2' OF 2"PMMP | 2022-10-06 | 3533 COLT NECK LN | A | 3890.5291 | 2249.75 | -1640.7791 | -42% | 2 | 3 | 749.9167
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026230200 | 558 | EX | EMER-RETIRE 2' OF 2"PMP MAIN | 2022-10-06 | 3533 COLT NECK LN | A | 74.3089 | 0 | -74.3089 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026231800 | 584 | EX | RETIRE PAPER CHART | 2022-08-23 | 707 LANE ALLEN RD | F | 1093 | 0 | -1093 | 100% |  |  | 0 | RETIRED PAPER CHART CCOX 8-23-22
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026232000 | 584 | EX | RETIRE PAPER GAUGE | 2022-07-26 | 2108 NICHOLASVILLE RD | F | 993 | 0 | -993 | 100% |  |  | 0 | RETIRED PAPER CHART 7-26-22 CCOX
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026232100 | 584 | EX | RETIRE PAPER GAUGE | 2022-12-01 | 3301 LANSDOWNE DR | F | 993 | 719.12 | -273.88 | -28% |  |  | 0 | REMOVED CHART, CCC 2244, CMCHOLAN 12-1-22
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026233800 | 563 | EX | INSTALL 380' OF 4"PMLP SL | 2022-11-29 | 960 DELAWARE AV | B | 36339.1396 | 35845.97 | -493.1696 | -1% | 380 |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026233900 | 575 | EX | OBTAIN EASEMENT FOR REG #1220 | 2022-10-28 | 4940 ATHENS BOONESBORO RD | F | 14490 | 12619.05 | -1870.95 | -13% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026234001 | 555 | EX | INSTALL 500' OF 2"/4"PMMP MAIN | 2023-04-25 | 112 LUCILLE DR | B | 89921.6185 | 88694.69 | -1226.9285 | -1% | 500 | 776 | 114.2973 | INSTALLED 422' 040-PMMP 185' 020-PMMP 607' TOTAL
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026238200 | 555 | EX | INSTALL 205' OF 2"PMMP MAIN | 2023-01-16 | 1770 VENDOR WY STE 100 | B | 19394.2346 | 13604.24 | -5789.9946 | -30% | 205 | 215 | 63.2755 | TWALKER/KY 01-20-23: ISSUED BACK ORDER REQUEST #52196 FOR THIS JOB
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026240100 | 588 | EX | GMB TO CAB CONVERSION | 2023-04-04 | 1310 CENTRE PY | F | 238.427 | 2136.59 | 1898.163 | 796% |  |  | 0 | CONVERTED GMB TO CAB ACCOUNT, CMCHOLAN 4-4-23
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026240900 | 560 | EX | PAPER ONLY EXECUTE | 2022-11-16 | PRESS AV | B | 119.2135 | 0 | -119.2135 | 100% |  |  | 0
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 22026241500 | 559 | EX | INSTALL 40'-2" PMMP | 2023-03-23 | 2051 CUMMINS CT | B | 23266.5784 | 14054.24 | -9212.3384 | -40% | 40 | 25 | 562.1696
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 22026241600 | 560 | EX | RETIRE 30'-2" PMMP | 2023-03-23 | 2051 CUMMINS CT | B | 124.7348 | 193.2 | 68.4652 | 55% |  |  | 0
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 22026242301 | 559 | EX | INSTALL 8"POLY VALVE W/10"SPH | 2023-09-05 | 3090 HARRODSBURG RD | B | 63212.0666 | 84380.42 | 21168.3534 | 33% | 10 | 12 | 7031.7017
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026242400 | 575 | EX | OBTAIN NEW HP EASEMENT | 2023-01-09 | 1320 BIG POND CR | F | 8747.2135 | 7607.73 | -1139.4835 | -13% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026242500 | 560 | EX | EMER-RETIRE 385' OF 2"/3"PAIP | 2022-12-12 | 4130 GEORGETOWN RD | B | 5363.3319 | 5628.45 | 265.1181 | 5% |  |  | 0
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 22026242600 | 559 | EX | INSTALL 500' - 4" PMMP | 2023-05-26 | 3725 MAN O WAR BD | B | 97718.819 | 115979.71 | 18260.891 | 19% | 520 | 524 | 221.3353
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026242700 | 561 | EX | INSTALL 350' OF 8"CSHP MAIN | 2023-08-24 | 2210 GEORGETOWN RD | B | 370158.4472 | 381751.32 | 11592.8728 | 3% | 350 | 385 | 991.5619
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026242800 | 562 | EX | RETIRE 326' OF 8"CSHP MAIN | 2023-08-24 | 2210 GEORGETOWN RD | B | 114.3981 | 0 | -114.3981 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026242900 | 2000 | EX | DESIGN AND RELOCATION CONFLICT | 2023-03-22 | 2210 GEORGETOWN RD | B | 10887 | 0 | -10887 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026243000 | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2023-04-20 | 2032 PARALLEL DR | F | 29336.8866 | 20860 | -8476.8866 | -29% |  |  | 0 | CC# 23362 CCC# 24092 DID NOT ENTER STATION. CWEMPE 4/27/23
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026243100 | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2023-04-26 | OLD FRANKFORT PK | F | 21860.8866 | 18742.99 | -3117.8966 | -14% |  |  | 0 | CC 22894 WELDED TAPS ON COULD NOT PRESSURE TEST DUE TO TIME CONSTRAINTS PER RTWAIT CCC# 24089
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026243200 | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2023-04-11 | 1750 SUMMERHILL DR | F | 25283.8866 | 20634.93 | -4648.9566 | -18% |  |  | 0 | CCC# 21042 CC 22745 WELD AND TEST STEEL TIE TAPS INLET 240# OUTLET 90# 5MINS RHAYES DMARTIN 03-30-2023 NOT ONSITE COLLECTING PARTS FOR JOB CCC#27524
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026243300 | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2023-04-12 | 567 MITCHELL AV | F | 20719.8866 | 20996.21 | 276.3234 | 1% |  |  | 0 | CCC# 21042 CC#23191 CC#24679 CC# 27421 CMCOX 4/27/23 1600
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026243400 | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2023-03-29 | 2540 RESEARCH PARK DR | F | 19008.8866 | 15857.32 | -3151.5666 | -17% |  |  | 0 | CCC#22649
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026243500 | 584 | EX | RETIRE RECORDING GAUGE | 2023-03-29 | 2540 RESEARCH PARK DR | F | 96.4823 | 241.8 | 145.3177 | 151% |  |  | 0 | CCC#22649
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026243600 | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2023-04-14 | 250 W LOUDON AV | F | 27565.8866 | 18807.4 | -8758.4866 | -32% |  |  | 0 | CCC 25146 INSTALLED NEW MIWI AND SOLAR KIT, NOT COMMIONSED YET CCC 25146 INSTALLED NEW SCADA EQUMENT NOT COMSSIONED YET BUT IS UP AND RUNNING CCC-30719PREFORMED POINT TO POINT FOR NEW WIMI
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026243900 | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2023-05-04 | KENNESAW DR | F | 14352.6752 | 13592.24 | -760.4352 | -5% |  |  | 0 | CHANGE OF PLAN, SCADA IS NOT BUILT FOR THIS SIGHT AND NOT READY TO BE CHANGED OVER, CMCHOLAN 3-28-23 INSTALL NEW MIWI, P2P OK, GAGE INSP OK, REMOVED PAPER PRESSURE CHART, PRESSURE TEST OK, CMCHOLAN 5-4-23 1358
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026244000 | 910 | EX | RETIRE ELECTRONICS | 2023-05-04 | KENNESAW DR | F | 131.2422 | 65.38 | -65.8622 | -50% |  |  | 0 | REMOVED ERX TO INSTALL MIWI, CCC 22274, CMCHOLAN 3-28-23
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026245000 | 560 | EX | PAPER ONLY EXECUTE | 2022-12-09 | ROSE ST | B | 131.2422 | 0 | -131.2422 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026246100 | 584 | EX | RETIRE PAPER GAUGE | 2023-01-02 | 3369 HOLWYN RD | F | 131.2422 | 389.08 | 257.8378 | 196% |  |  | 0 | RETIRE PRESSURE CHART GUAGE CCOX 1-2-23
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026246401 | 559 | EX | INSTALL 3100' OF 2"PMMP MAIN | 2023-04-13 | 2263 NICHOLASVILLE RD | B | 612252.3877 | 515222.82 | -97029.5677 | -16% | 3100 | 2905 | 177.3573
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026246500 | 560 | EX | RETIRE 2400' OF 4"BS/CSLP MAIN | 2023-05-19 | 2263 NICHOLASVILLE RD | B | 138.8485 | 0 | -138.8485 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026247500 | 2000 | EX | INVESTIGATE EASEMENT & ROW | 2023-03-03 | 145 BURT RD | B | 5841 | 0 | -5841 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026247700 | 587 | EX | INSTALL NEW GMB SETTING | 2023-08-04 | 3111 SPURR RD | F | 92317.8265 | 96486.51 | 4168.6835 | 5% |  |  | 0 | TICKET# 39340 CCC#39340 CCC#39492 08-04-2023 RHAYES CCC#39795
KY | KY - WEST | 2621 | U132257 | McGuire,Chera Lee | Opfer,Matthew | Dunn,David | 23026247900 | 2000 | EX | ILI AUXILIARY WORK | 2023-05-18 | 1001 CHERRY BLOSSOM WY | A | 150000 | 32.67 | -149967.33 | -100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026248200 | 557 | EX | EMER - INSTALL 2'-2" PMMP | 2023-01-09 | 107 TRAFTON ST 2150 | A | 13154.2985 | 135.67 | -13018.6285 | -99% | 3 | 2 | 67.835 | INSTALLED 2 ' OF 2'' PMP PIPE ( TESTED PIPE FOR 20MNS-GOOD PER FOL R. VANDERPOOL) J.OCHOA
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026248300 | 558 | EX | EMER - RETIRE ~2'-2"PMP | 2023-01-09 | 107 TRAFTON ST 2150 | A | 129.6266 | 1647.72 | 1518.0934 | 1,171% |  |  | 0 | RETIRED 2' OF 2'' P MP MAIN DUE TO DAMAGE. J.OCHOA 01-11-2023
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026248400 | 557 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | 2023-01-18 | 1384 FONTAINE RD | A | 5318.1948 | 2322.97 | -2995.2248 | -56% | 3 | 4 | 580.7425
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026248500 | 558 | EX | EMER-RETIRE 3' OF 2"PMMP MAIN | 2023-01-18 | 1384 FONTAINE RD | A | 131.2422 | 0 | -131.2422 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026248900 | 559 | EX | INSTALL 100' OF 2"PMMP MAIN | 2023-02-02 | 2093 FALLON RD | B | 30720.7606 | 28889.25 | -1831.5106 | -6% | 100 | 115 | 251.2109
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026249000 | 560 | EX | RETIRE 86' OF 2"CSMP MAIN | 2023-02-02 | 2093 FALLON RD | B | 131.2422 | 0 | -131.2422 | 100% |  |  | 0 | ABN 102' OF 2'' COATED STEELE MAIN PURGED AND END SEALED
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026249300 | 557 | EX | EMER-INSTALL 5' OF 2"PMMP | 2023-01-17 | 620 BLUE ASH DR | A | 8253.2559 | 5012.41 | -3240.8459 | -39% | 5 | 3 | 1670.8033 | REPLACED 3' OF DAMAGED 2" PLASTIC MAIN LINE WITH 2 EF COUPLINGS. PRESSURE TESTED THE THE NEW MAIN LINE AT 90PSIG FOR 1 HOUR. PRESSURE TEST OKAY. BHB, NGF. SOAP TESTED FINAL TIE IN AT OP. TEST OK. DMALONE
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026249400 | 558 | EX | EMER-RETIRE 5' OF 2"PMMP MAIN | 2023-01-17 | 620 BLUE ASH DR | A | 131.2422 | 219.4 | 88.1578 | 67% |  |  | 0 | REPLACED 3' OF DAMAGES 2" PLASTIC MAIN LINE WITH 2 EF COUPLINGS. PRESSURE TESTED THE NEW MAIN LINE AT 90PSIG FOR 1 HOUR. PRSSURE TEST OK. BHB, NGF. SOAP TESTED FINAL TIE IN AT OP. TEST OK. DMALONE
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026249800 | 587 | EX | INSTALL EC 350 UNIT | 2023-01-25 | 1900 RICHMOND RD | F | 7475.3221 | 5379.35 | -2095.9721 | -28% |  |  | 0 | CHECK TO SEE IF CARD WAS READY CMCHOLAN 1-27-2023 INSTALLED NEW EC350 CMCHOLAN 1-25-23
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026249900 | 588 | EX | RETIRE PAPER BILLING CHART | 2023-01-25 | 1900 RICHMOND RD | F | 131.2422 | 463.02 | 331.7778 | 253% |  |  | 0 | REMOVED PAPER BILLING CHART, CMCHOLAN EBLANTON 1-25-23
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026250000 | 587 | EX | INSTALL EC 350 UNIT | 2023-03-16 | 1490 BULL LEA RD | F | 5649.3221 | 6158.92 | 509.5979 | 9% |  |  | 0 | INSTALLED NEW HONEYWELL EC350 INPLACE OF CHART
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026250100 | 588 | EX | RETIRE PAPER BILLING CHART | 2023-03-16 | 1490 BULL LEA RD | F | 131.2422 | 525.01 | 393.7678 | 300% |  |  | 0 | RETIRED PAPER CHART EBLANTON 3-16-23
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026250200 | 587 | EX | INSTALL EC-350 | 2023-03-14 | 345 N BROADWAY ST | F | 6049.3221 | 8105.28 | 2055.9579 | 34% |  |  | 0 | INSTALLED IN HONEYWELL EC3560 IN PLACE OF CHART EBLANTON 3-14-23
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026250300 | 588 | EX | RETIRE PAPER BILLING CHART | 2023-03-14 | 345 N BROADWAY ST | F | 131.2422 | 185.13 | 53.8878 | 41% |  |  | 0 | RETIRE PAPER BILLING CHART EBLANTON 3-14-23
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026250500 | 587 | EX | INSTALL EC 350 | 2023-03-15 | 1587 BAUMANN DR | F | 7589.3221 | 6654.67 | -934.6521 | -12% |  |  | 0 | INSTALLED NEW HONEYWELL EC350 IN PLACE OF CHART EBLANTON 3-15-2023
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026250600 | 588 | EX | RETIRE PAPER BILLING CHART | 2023-03-15 | 1587 BAUMANN DR | F | 131.2422 | 144.2 | 12.9578 | 10% |  |  | 0 | RETIRED PAPER BILLING CHART EBLANTON 3-15-23
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026250700 | 587 | EX | INSTALL EC 350 | 2023-03-01 | 223 GOLD RUSH RD | F | 5649.3221 | 5810.87 | 161.5479 | 3% |  |  | 0 | RETIRED CHART INSTALLED NEW EC350
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026250800 | 588 | EX | RETIRE PAPER BILLING CHART | 2023-03-01 | 223 GOLD RUSH RD | F | 131.2422 | 528.15 | 396.9078 | 302% |  |  | 0 | RETIRED PAPER CHART CCOX
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 23026251700 | 555 | EX | INSTALL 2060' OF 2" PMMP | 2023-03-16 | MARLENA LN LT92 | B | 60788.4178 | 65881.72 | 5093.3022 | 8% | 2060 | 2523 | 26.1125
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026251800 | 562 | EX | RETIRE 900' OF 2"CSHP MAIN | 2023-08-07 | 3111 SPURR RD | B | 4095.9621 | 12666.75 | 8570.7879 | 209% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026252000 | 557 | EX | EMER-INSTALL 3' OF 6"PMMP MAIN | 2023-01-17 | 2575 PALUMBO DR | A | 12970.9861 | 13052.34 | 81.3539 | 1% | 3 | 3 | 4350.78
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026252100 | 558 | EX | RETIRE 3' OF 6"PMP MAIN | 2023-01-17 | 2575 PALUMBO DR | A | 138.8485 | 0 | -138.8485 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026252200 | 557 | EX | EMER-INSTALL 3' OF 4"PMMP MAIN | 2023-01-19 | 249 E REYNOLDS RD | A | 7839.2961 | 5339.51 | -2499.7861 | -32% | 3 | 3 | 1779.8367
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026252300 | 558 | EX | EMER-RETIRE 3' OF 4"PAMP MAIN | 2023-01-19 | 249 REYNOLDS RD | A | 138.8485 | 0 | -138.8485 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026252600 | 557 | EX | INSTALL 3' OF 4"PMLP MAIN | 2023-01-25 | 216 LOCUST AV | A | 9484.2961 | 16571.37 | 7087.0739 | 75% | 3 | 5 | 3314.274 | ABD 69 FT BS CUT OUT INLINE TEE AND INSTALLED 5 FT OF 4 IN PL TEST 90 LB FOR 1 HR OK SOAP TEST CPLG AND TEES AT OP FOR 5 MIN BAR HOLE BANKS NO GAS FOUND
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026252700 | 558 | EX | RETIRE 69' OF 4"BSLP MAIN | 2023-01-25 | 216 LOCUST AV | A | 138.8485 | 0 | -138.8485 | 100% |  |  | 0 | ABDN 69 FT OF 6 IN BARE STEEL BLEW DOWN AND SEALED ENDS
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026253900 | 584 | EX | RETIRE PRESSURE GAUGE | 2023-01-27 | 1039 GOODWIN DR | F | 552.5683 | 0 | -552.5683 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026254000 | 584 | EX | RETIRE PRESSURE GAUGE | 2023-01-31 | 1406 VERSAILLES RD | F | 552.5683 | 768.43 | 215.8617 | 39% |  |  | 0 | CC15136 CHART HAS BEEN REMOVED ISO UPDATED 1-31-23 CC15136 CHART HAS BEEN REMOVED ISO UPDATED 1-31-23
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026254400 | 561 | EX | INSTALL 420' OF 6"PMMP MAIN | 2023-08-25 | 2210 GEORGETOWN RD | B | 9832.3981 | -558.31 | -10390.7081 | -106% | 420 | 426 | -1.3106
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026254500 | 562 | EX | RETIRE 356' OF 6"PMMP MAIN | 2023-08-25 | 2210 GEORGETOWN RD | B | 114.3981 | 0 | -114.3981 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026254700 | 584 | EX | RETIRE PAPER GAUGE | 2023-02-01 | 400 ANNISTON DR | F | 552.5683 | 247.65 | -304.9183 | -55% |  |  | 0 | REMOVED PAPER CHART, CCC 10587
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026256201 | 573 | EX | INSTALL VRG CONTROLLERS | 2023-08-14 | 4940 ATHENS BOONESBORO RD | F | 47185.8659 | 78966.67 | 31780.8041 | 67% |  |  | 0 | DROPPING OF MATTERIAL 06-02-23 1324 CCC# 32360 CCC#32737 CC# 33503 CCC# 33503 CCC# 39939
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026256400 | 555 | EX | INSTALL 25' OF 2"PMMP MAIN | 2023-08-08 | 1600 VILLA MEDICI PS | A | 8978.2187 | 9201.52 | 223.3013 | 2% | 25 | 18 | 511.1956 | INSTALLED 18' OF NEW MAIN AND ONE SERVICE LINE TO 1600 VILLA MEDICI TWALKER/KY 10-19-23: ISSUED BACK ORDER CANCEL 53922 FOR THE 250' COIL OF 2"PIPE WHICH IS NO LONGER AVAILABLE
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 23026257000 | 910 | EX | ST JOE - RETIRE RTU | 2023-04-03 | 1590 HARRODSBURG RD | F | 138.8485 | 310.19 | 171.3415 | 123% |  |  | 0 | RETIRED OLD RTU EBLANTON 4-3-23
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026259000 | 557 | EX | EMER-INST 85'-4"PMMP MND311494 | 2023-02-20 | BAHAMA RD | A | 25540.4028 | 23726.73 | -1813.6728 | -7% | 85 | 85 | 279.138 | 4" MAIN/PINK PL LEAKING UNDER STAMPED CONCRETE ENTRANCE TO COUNTRY CLUB RETIRED 85' AND INSTALLED 85' OF NEW MAIN-BORING DONE BY STANLEY PIPELINE, MAIN TEST 1 HR @90IB OK, TIE IN COMPLETE 02/20/2023 HMCKUNE
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026259100 | 558 | EX | EMER-RETIRE 85' OF 4"PAMP MAIN | 2023-02-20 | BAHAMA RD | A | 138.8485 | 260.66 | 121.8115 | 88% |  |  | 0 | 4" MAIN/PINK PL LEAKING UNDER STAMPED CONCRETE ENTRANCE TO COUNTRY CLUB RETIRED 85' AND INSTALLED 85' OF NEW MAIN-BORING DONE BY STANELY PIPELINE, MAIN TEST 1HR @90 IB OK, TIE IN COMPLETE, 02/20/2023 HMCKUNE
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026260700 | 909 | EX | INSTALL ERX W/SUPER SOLAR | 2023-03-06 | 881 REBECCA DR | F | 5629.9621 | 3972.47 | -1657.4921 | -29% |  |  | 0 | INSTALLED SUPER SOLAR AND MEDIUM PRESSURE RUN TO ER350, WILL BE FULL TIME MONITOR WHEN BUILT IN SCADA AND WILL DO P2P THEM CCC 19108, CMCHOLAN 3-6-23 FINISHED UP PAPERWORK AND SUMMITED ISO, CCC 19108 CMCHOLAN 3-6-23 0859 CCC-27261 DID P2P WITH GAS CONTROL ON MP, GAGE INSP OK, CCC 27123 CMCHOLAN EBLANTON 4-26-23 1600
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026260800 | 584 | EX | RETIRE PAPER CHART | 2023-03-06 | 881 REBECCA DR | F | 138.8485 | 78.59 | -60.2585 | -43% |  |  | 0 | RETIRED PAPER CHART AND IS NOW CONNECTED ER350, CMCHOLAN CCC 19108
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026262700 | 557 | EX | EMER-INSTALL 5' OF 2"PMMP MAIN | 2023-02-23 | 3905 PALOMAR COVE LN | A | 7460.3676 | 3582.24 | -3878.1276 | -52% | 5 | 5 | 716.448 | WORKED WITH JO. 23026262700 INSTALLED 5FT OF 020 MAIN DUE TO LEAKING S/L TEE. TESTED 5FT OF 020, 010 TEE,010 COUPLING AND 020 PURGE END CAP FOR 1HR AT 90LBS.TEST OK. SOAP TEST 020 EFC AT OP. FOR 5MINS TEST OK. BHB NGF
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026262800 | 558 | EX | EMER-RETIRE 5' OF 2"PMP MAIN | 2023-02-23 | 3905 PALOMAR COVE LN | A | 124.7348 | 726.04 | 601.3052 | 482% |  |  | 0 | FROM MAIN TO MTR FOR 5MINS AT 90LBS.TEST OK. SOAP TEST FINAL TIE IN AT OP.TEST OK. BHB NGF WORKED WITH JO. 23026262700 INSTALLED 5FT OF 020 MAIN DUE TO LEAKING S/L TEE. TESTED 5FT OF 020, 010 TEE,010 COUPLING AND 020 PURGE END CAP FOR 1HR AT 90LBS.TEST OK. SOAP TEST 020 EFC AT OP. FOR 5MINS TEST OK. BHB NGF -- 010 S/L ELECTROFUSION TEE LEAKING AT SADDLE CONNECTION TO MAIN.REPLACED 5FT OF MAIN WITH NEW S/L TEE AND 020 PURGE END CAP.TESTED FOR 1HR AT 90LBS. TEST OK. SOAP TEST EFC COULPING AT OP. FOR 5MINS.TEST OK.TEST S/L FOR 3905
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026263000 | 557 | EX | INSTALL 5875' OF 2"/4"PMMP ENV | 2023-09-05 | 1228 STANDISH WY | B | 728668.2681 | 763454.52 | 34786.2519 | 5% | 34230 | 6739 | 113.289
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026263100 | 558 | EX | RETIRE 6090' OF 4"BSMP MAIN | 2023-09-05 | 1228 STANDISH WY | B | 124.7348 | 0 | -124.7348 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026263300 | 2000 | EX | INVESTIGATE ROAD R/W | 2023-03-02 | COLONIAL DR | A | 7031 | 0 | -7031 | 100% |  |  | 0
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 23026263400 | 557 | EX | INSTALL 40'-4" PMMP | 2023-04-10 | 1095 ROCKBRIDGE RD | B | 25145.0229 | 24778.88 | -366.1429 | -1% | 40 | 27 | 917.7363
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 23026263500 | 558 | EX | RETIRE 20'-4" PMMP | 2023-04-10 | 1095 ROCKBRIDGE | B | 124.7348 | 98.08 | -26.6548 | -21% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026264300 | 557 | EX | EMER-INSTALL 5' OF 4"PMMP MAIN | 2023-02-28 | 1055 DOVE RUN RD | A | 7456.0229 | 267.86 | -7188.1629 | -96% | 5 | 3 | 89.2867 | INSTALLED 3' OF 4" PL MAIN W/ EFC AND BF DE CAP- TEST 90# FOR 20MINS PER FOL DBANKS- SOAP TEST FINALTIEIN @ OP TEST OK- BHB NGF CONTENT VERIFIED DMARSTO 3/10/23
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026264400 | 558 | EX | EMER-RETIRE 520'- 4"PAIP MAIN | 2023-02-28 | 1055 DOVE RUN RD | A | 124.7348 | 325.83 | 201.0952 | 161% |  |  | 0 | ABN 520' SECTION OF 4" PL MAIN- PURGE ABN SECTION OF MAIN W/ AIR UNTIL 0% SUSTAINED- DMARSTO 3/10/23
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026264700 | 557 | EX | INSTALL 100' OF 3"PMLP MAIN | 2023-04-05 | 625 COLUMBIA AV | A | 29526.7351 | 21922.36 | -7604.3751 | -26% | 100 | 100 | 219.2236 | 100' OF BS MAIN RETIRED AND REPLACED W/3" PE PL MAIN DUE TO CORROSION
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026264800 | 558 | EX | RETIRE 100' OF 3"BSLP MAIN | 2023-04-05 | 625 COLUMBIA AV | A | 124.7348 | 6487.75 | 6363.0152 | 5,101% |  |  | 0 | 100' OF BS MAIN RETIRED AND REPLACED W/3" PE PL MAIN DUE TO CORROSION
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026265100 | 557 | EX | INSTALL 10'-3"PMLP | 2023-06-01 | 524 GEORGETOWN ST | A | 37610.5067 | 15746.7 | -21863.8067 | -58% | 10 | 10 | 1574.67 | INSTALLED 10 FT OF PL TEST FROM POINT A TO B 90 LB FOR 20 MIN TEST OK SOAP TEST 2 CPLG AND ALL BAG HOLES AT OP BHBNGF MAIN READ -0.601 INSTALLED 2 ANODES
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026265200 | 558 | EX | RETIRE 10'-3" BSLP | 2023-06-01 | 524 GEORGETOWN ST | A | 120.2184 | 190.67 | 70.4516 | 59% |  |  | 0 | RETIRED 10 FT OF 3 IN BS PIPE PURGED OUT AND SEALED THE INLINE TEE SIDE
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 23026265400 | 559 | EX | EMER - INSTALL 12' - 2" PMMP | 2023-04-06 | 232 DESHA RD | A | 5370.5784 | 9462.49 | 4091.9116 | 76% | 12 | 12 | 788.5408 | TEST 2 IN MAIN FROM POINT A TO B TEST 90 LB FOR 20 MIN SOAP TEST TIEINS AT OP BAR HOLE BANKS NO GAS FOUND
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 23026265500 | 560 | EX | EMER - RETIRE 12' - 2" PMMP | 2023-04-06 | 232 DESHA RD | A | 124.7348 | 165.55 | 40.8152 | 33% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026266000 | 2000 | EX | INVESTIGATE POSSIBLE ENCROACHM | 2023-08-18 | 360 W LOUDON AV | B | 5397 | 0 | -5397 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026266300 | 557 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | 2023-02-22 | HORTON | A | 7671.8121 | 4867.28 | -2804.5321 | -37% | 3 | 3 | 1622.4267
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026266400 | 558 | EX | EMER-RETIRE 3' OF 2"PMP MAIN | 2023-02-22 | HORTON | A | 124.7348 | 0 | -124.7348 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026267700 | 558 | EX | EMER-RETIRE 40' OF 6"BSLP MAIN | 2023-03-16 | INDIAN MOUND | A | 9430.1038 | 8203.54 | -1226.5638 | -13% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026267800 | 555 | EX | INSTALL 580' OF 2"PMMP MAIN | 2023-06-08 | 3381 PEPPERHILL RD | B | 40516.7801 | 35753.76 | -4763.0201 | -12% | 580 | 670 | 53.3638
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026268200 | 557 | EX | INSERT 160' OF 3"PMLP MAIN | 2023-04-13 | SAINT JOSEPH DR | A | 20952.5602 | 12586.85 | -8365.7102 | -40% | 160 | 165 | 76.2839
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026268300 | 558 | EX | RETIRE 160' OF 4"BSLP MAIN | 2023-04-13 | SAINT JOSEPH DR | A | 117.7346 | 8055.67 | 7937.9354 | 6,742% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026268400 | 555 | EX | INSTALL 2000' OF 2"PMMP MAIN | 2023-04-21 | STOLEN HORSE TC LT64 | B | 83632.6185 | 56232.52 | -27400.0985 | -33% | 2000 | 1997 | 28.1585
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026268800 | 910 | EX | RETIRE ER350 UNIT | 2023-04-12 | 567 MITCHELL AV | F | 117.7346 | 116.17 | -1.5646 | -1% |  |  | 0
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 23026269800 | 0001 | EX | DOCUMENT MP SYSTEM COMBINATION | 2023-05-26 | 3725 MAN O WAR BV | A | 71.7346 | 0 | -71.7346 | 100% |  |  | 0
KY | KY - WEST | 2621 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 23026270800 | 2000 | EX | INVESTIGATE ROW AND EASEMENT | 2023-12-05 | 424 CLAYTON AV |  | 13106 | -10195.52 | -23301.52 | -178% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026271200 | 587 | EX | INSTALL LEGACY ERX | 2023-04-03 | 1400 HARRODSBURG RD | F | 2907.8819 | 2465.58 | -442.3019 | -15% |  |  | 0 | INSTALLED LEGACY ERX IN PLACE OF OLD RTU AND TRANSMITTER EBLANTON 4-3-23
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026271600 | 573 | EX | PAPER ONLY TO SET UP WMS FAC | 2022-12-24 | 2001 MERCER RD M&R | F | 139.7346 | -1146.13 | -1285.8646 | -920% |  |  | 0 | THIS JOB IS TO CREATE FUNCTIONS AND FACILITIES FOR THE TEMPORARY SKID REGUL ATOR SETTING RWILLIAMS PUT TEMP STATION BACK TOGETHER, CMCHOLAN 6-26-2023
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026272200 | 555 | EX | INSTALL 200' OF 2"PMMP MAIN | 2023-06-16 | 604 MONTCLAIR DR | B | 23237.6457 | 27418.37 | 4180.7243 | 18% | 150 | 212 | 129.3319
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026272300 | 559 | EX | EMER-INSTALL 3" NC POLY VALVE | 2023-04-26 | 1146 ROCKBRIDGE RD | A | 7421.5276 | 6810.69 | -610.8376 | -8% | 4 | 4 | 1702.6725 | REPLACED BROKEN CRITICAL VLV WITH NEW 030 POLY VLV. TEST PIPE,VLV,&CPLGS 90#1HOUR, TG. ST LTI OK. BHBNGF. R.CRAWFORD 4-28-23
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026272400 | 560 | EX | EMER-RETIRE 3"PV C16-87 | 2023-04-26 | 1146 ROCKBRIDGE RD | A | 117.7346 | 85.95 | -31.7846 | -27% |  |  | 0 | REFER TO JOB#-23026272300 FOR COMMENTS. R.CRAWFORD 4-28-23
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026272600 | 555 | EX | INSTALL 875' OF 2"PMMP MAIN | 2023-05-09 | HOMESTRETCH CR LT26 | B | 32780.4095 | 29299.51 | -3480.8995 | -11% | 875 | 739 | 39.6475
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026272700 | 557 | EX | EMER - INSTALL 5'-2" PMMP | 2023-04-25 | 219 HIGHLAWN AV | A | 5551.3568 | 2367.44 | -3183.9168 | -57% | 30 | 3 | 789.1467
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026272800 | 558 | EX | EMER - RETIRE 5'-2" PMMP | 2023-04-25 | 219 HIGHLAWN AV | A | 112.7299 | 0 | -112.7299 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026273000 | 559 | EX | INSTALL 20'-4"PMMP W/NEW VALVE | 2023-06-26 | 1000 ANDOVER FOREST DR | A | 13458.2914 | 20711.38 | 7253.0886 | 54% | 20 | 20 | 1035.569 | LOWERED 4" MP PE MAIN,REPLACED CRITICAL VLV,TEST MAIN@90IB 1HR,TIED IN W/2 EF CPLG'S, SOAP TEST TIE IN,MOVE CV TO SOFT SURFACE 06/26/2023 HMCKUNE
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026273100 | 560 | EX | RETIRE 20'-4"PMMP W/C19-314 | 2023-06-26 | 1000 ANDOVER FOREST DR | A | 117.7346 | 0 | -117.7346 | 100% |  |  | 0
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 23026273300 | 557 | EX | INSTALL 290' OF 4" PMMP | 2023-06-28 | 208 CHINOE RD | B | 48321.0935 | 80935.68 | 32614.5865 | 67% | 291 | 337 | 240.1652
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 23026273400 | 558 | EX | RETIRE 283' OF 3" BSMP | 2023-06-28 | 208 CHINOE RD | B | 67.1159 | 0 | -67.1159 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026273900 | 583 | EX | INSTALL 441 REG (WEST RUN) | 2023-06-08 | 3005 OLD TODDS RD | F | 3436.7638 | 4130.38 | 693.6162 | 20% |  |  | 0 | (NOT ON-SITE GETTING PARTS TO COMPLETE JOB) G.HALE NOT ONSITE COLLECTING REG AND PARTS APARKS 05-18-23 1551 SWAPPED 461 REGS FOR 441 REGS 57S 1 3/4 ORFICE BROWN SPRING IN BOTH CONTROL AND MONITOR MAJOR INSP. COMPLETED ON BOTH REGS INLET@90# MON@55# CON@47# CCC# 33177 NOT ONSITE PAPER WORK ONLY APARKS 06-19-23 1000
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026274000 | 584 | EX | RETIRE 461 REGS (WEST RUN) | 2023-06-08 | 3005 OLD TODDS RD | F | 117.7346 | 0 | -117.7346 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026274301 | 555 | EX | INSTALL 3400' OF 2"PMMP MAIN | 2023-09-14 | CRAVAT PASS LT243 | B | 79169.604 | 82979.94 | 3810.336 | 5% | 3300 | 3399 | 24.413
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026275600 | 2000 | EX | CONFLICT ASSESSMENT | 2023-06-22 | 2585 POLO CLUB | A | 8460 | 0 | -8460 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026276300 | 559 | EX | EMER-INSTALL 2"POLY VALVE | 2023-06-27 | 3441 LAREDO DR | A | 10283.4841 | 6851.84 | -3431.6441 | -33% | 4 | 4 | 1712.96 | INSTALLED NEW CRIT.VLV. TEST VLV FOR 1 HOUR, TG. TEST 2 BYPASS, TG. TEST ALL TEES, TG. ST LTI'S, TG. ALL TIME FOR JOB# 23186718700 TO BE CHARGED BACK TO THIS JOB, R.CRAWFORD 6-23-23 REFER TO JOB# 23026276400 FOR COMMENTS. R.CRAWFORD 6-27-23
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026276400 | 560 | EX | EMER-RETIRE 2"VALVE C14-27 | 2023-06-27 | 3441 LAREDO DR | A | 139.1159 | 0 | -139.1159 | 100% |  |  | 0 | REFERENCE COMMENTS FOR JOB # 23026276300. R.CRAWFORD 6-23-23 REPLACED BROKEN CV. TEST NEW CV AND PIPE WITH IT 90#1HR, TG. TEST ALL TEES 9#5MINS, TG. TEST BYPASS' 90#1HOUR, TG. ST ALL FINAL TI'S, TG. R.CRAWFORD 6-27-23
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026276900 | 562 | EX | RETIRE 250' OF 3"BSLP MAIN | 2023-06-27 | ADDIE ST | A | 4585.4374 | 1716.17 | -2869.2674 | -63% |  |  | 0 | ABDN 252 FT OF 3 IN BS MAIN SOAP TEST 4 PAC CLAMPS AT OP FOR 5 MIN SOAP TEST END CAP AT OP FOR 5 MIN BHBNGF INSTALLED 1ANODE PURGED OUT OLD MAIN AND SEALED MAIN LEFT 36 FT LINE MARKER AT END
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026277000 | 557 | EX | EMER-INSTALL 15' OF 8"PMLP MN | 2023-08-10 | 210 W MAXWELL ST | A | 23129.0935 | 19403.77 | -3725.3235 | -16% | 15 | 11 | 1763.9791 | INSTALLED 8 IN PL MAIN TEST FROM POINT A TO POINT B SOAP TEST ALL PAC CLAMPS AND CPLG AT OP FOR 5 MIN BHBNGF INSTALLED 2 ANODE
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026277100 | 558 | EX | EMER-RETIRE 15' OF 8"BSLP MN | 2023-08-10 | 210 W MAXWELL ST | A | 139.1159 | 307.27 | 168.1541 | 121% |  |  | 0 | ABDN 11 FT 8 IN BS MAIN INSTALLED 11 8 IN PL MAIN TEST 90 LB FOR 1 HHR SOAP TEST FINAL TIE IN AT OP FOR 5MIN BHBNGF
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026277200 | 562 | EX | EMER-RETIRE 55' OF 6"PMLP MN | 2023-06-01 | ROSE ST | A | 4206.4374 | 5550.64 | 1344.2026 | 32% |  |  | 0 | RETIRED 52' OF 6'-P-LP WITH E/F COUPLING AND DEAD END CAP. PURGED 52' OF ' MAIN OUT OF SERVICE. SOAP TESTED FINAL CONNECTION FOR 5 MINTES AT OP. TEST OKAY.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026277300 | 561 | EX | INSTALL 265' OF 6"PMMP MAIN | 2023-08-30 | 2585 POLO CLUB | B | 71789.4841 | 29277.24 | -42512.2441 | -59% | 265 | 258 | 113.4777 | JOB COMPLETED. 08312023
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026277400 | 562 | EX | RETIRE 285' OF 6"PMMP MAIN | 2023-08-30 | 2585 POLO CLUB | B | 139.1159 | 439.67 | 300.5541 | 216% |  |  | 0 | JOB COMPLETED
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026277900 | 557 | EX | EMER - INSTALL 69'-6" PMLP | 2023-06-08 | WINDSOR | A | 35367.5186 | 31362.92 | -4004.5986 | -11% | 75 | 75 | 418.1723 | INSTALLED 40' 060 PMP TESTED FOR 1HR AT 90LBS.TEST OK. SOAP TEST TIE INS AT OP.TEST OK. BHB NGF WORKED WITH 558
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026278000 | 558 | EX | EMER - RETIRE 69'-6" BSLP | 2023-06-08 | WINDSOR | A | 139.1159 | 124.77 | -14.3459 | -10% |  |  | 0 | ABDN 40' OF 6'' STEEL WORKED WITH 557.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026278200 | 557 | EX | EMER-INSTALL 185' OF 4"PMLP | 2023-06-15 | 201 E 5TH ST | B | 28939.243 | 41523.49 | 12584.247 | 43% | 185 | 184 | 225.6711
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026278300 | 558 | EX | EMER-RETIRE 181' OF 4"BSLP MN | 2023-06-15 | 201 E 5TH ST | B | 139.1159 | 0 | -139.1159 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026278401 | 555 | EX | INSTALL 2300' OF 2"/4"PMMP MN | 2023-11-15 | LONGRIDGE DR LT30 | B | 101330.2336 | 116796.05 | 15465.8164 | 15% | 2300 | 2949 | 39.6053
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026279100 | 555 | EX | INSTALL 300' OF 2"PMIP MAIN | 2023-07-27 | 1590 WINNERS CR | B | 17364.828 | 7749.44 | -9615.388 | -55% | 300 | 161 | 48.1332
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026279700 | 2000 | EX | INVESTIGATE MAINS | 2023-07-11 | ALEXANDRIA DR |  | 2993 | 0 | -2993 | 100% |  |  | 0 | EXCAVATION FOUND HP MAIN IS DEEPER THAN PLANNED ROADWAY IMPROVEMENTS OVER P IPE. EXISTING PIPE IS DEEPER THAN 7 FEET, WITH 1-2 FOOT OF CUT FOR DITCH O PLANNED OVER PIPELINE. D.LEMONS 7/11/2023
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 23026280100 | 560 | EX | RETIRE 10' OF 10"CSMP MAIN | 2023-09-05 | 3090 HARRODSBURG RD | B | 139.1159 | 273.6 | 134.4841 | 97% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026280800 | 557 | EX | EMER-INSTALL 62' OF 4"PMLP | 2023-07-12 | 944 LIBERTY | A | 28754.8748 | 63661.35 | 34906.4752 | 121% | 62 | 62 | 1026.796 | INSTALLE 40 FT 4 IN MAIN TEST FROM POINT A TO POINT B 90 LB FOR 1 HR TEST ALL TEES AT 90 LB FOR 5 MIN SOAP TEST EFC AND BOLTD CPLG AT O OP FOR 5 MIN SOAP TEST 1 IN END CAP AT OP FOR 5 MIN INSTALL 1 ANODE
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026280900 | 558 | EX | EMER-RETIRE 62' OF 4"BSLP | 2023-07-12 | 944 LIBERTY | A | 139.1159 | 2161.53 | 2022.4141 | 1,454% |  |  | 0 | RETIRED 36 FT OF BS AND 9 FT OF PL 4 IN LOW PRESSURE MAIN
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026282700 | 558 | EX | EMER-ABANDON 333' OF 2"PAMP | 2023-07-06 | JANNELLE CT | A | 3839.4374 | 2936.25 | -903.1874 | -24% |  |  | 0 | ABND CUL-DE-SAC AFTER HIT LINE BY OTHER CONTRACTOR PER ENGINEER/FOL AFTER VERIFICATION NO CUSTOMERS ON GAS FOR SECTION OF MAIN TO BE ABND
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026283000 | 2000 | EX | INVESTIGATE CONFLICT & R/W | 2023-07-14 | 100 CODELL DR | A | 7835 | 0 | -7835 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026283200 | 561 | EX | INSTALL 480' OF 2"PMMP MAIN | 2023-08-10 | 100 CODELL DR | B | 59017.0935 | 47476.79 | -11540.3035 | -20% | 480 | 503 | 94.3873 | TWALKER/KY 10-20-23: REQUESTED CUSTOMER REFUND FOR THE CUSTOMER PAID RELOCA TION PROJECT.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026283300 | 562 | EX | RETIRE 400' OF 2"BSMP MAIN | 2023-08-17 | 100 CODELL DR | B | 139.1159 | 0 | -139.1159 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026283400 | 557 | EX | EMER - INSTALL 5'-3" PMMP | 2023-07-10 | 1054 REDWOOD DR | A | 10280.7214 | 4261.01 | -6019.7114 | -59% | 5 | 5 | 852.202 | INST 5'- 3" NEW PL MAIN BY ENGINEERED PLAN. MCRAIG 7/10/23
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026283500 | 558 | EX | EMER - RETIRE 5'-3" PMP | 2023-07-10 | 1054 REDWOOD DR | A | 139.1159 | 36.39 | -102.7259 | -74% |  |  | 0 | RETIRE 5' OF 3" PL MAIN DUE TO LEAK PER ENGINEERED PLAN. MCRAIG 7/10/23
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026284300 | 557 | EX | EMER-INSTALL 490' OF 2"PMMP | 2023-07-14 | 2230 NICHOLASVILLE RD | A | 184478.0101 | 132813.07 | -51664.9401 | -28% | 520 | 493 | 269.3977 | BARE STEEL LP MAIN LEAKING, CREW WAS UNABLE TO EXPOSE LEAK, ABANDONED BS MAIN AND BORED IN 490'OF 2"P- PRE AND POST CAMERA COMPLETED-PT NEW MAIN 90LBS FOR 1HR PER ENGINEERING-SOAP TESTED TIE IN AT OP
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026284400 | 558 | EX | EMER-RETIRE 520' OF 4"BSMP MN | 2023-07-14 | 2230 NICHOLASVILLE RD | A | 139.1159 | 223.9 | 84.7841 | 61% |  |  | 0 | REPLACED 493' OF 4'' S MP WITH 2'' PMP DUE TO GRADE 1 LEAK.DPI D304338.
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026284500 | 557 | EX | INSTALL 80'4" PMLP | 2023-07-27 | 1000 KEES RD | A | 47424.0373 | 23619.02 | -23805.0173 | -50% | 80 | 60 | 393.6503 | TEST FROM POINT A TO B TO C 90 LB FOR 1 HR TEST OK TEST FINAL TIE IN AT OP OK BHBNGF INSTALLED 3 ANODES MAIN READ -0.591 TEST PAAC CLAMPS AT OP OK
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026284600 | 558 | EX | RETIRE 80'-4" BSLP | 2023-07-27 | 1000 KEES RD | A | 139.1159 | 4684.11 | 4544.9941 | 3,267% |  |  | 0 | RETIRED 60 FT OF BS 4IN MAIN PURGED OUT AND REMOVED PIPE
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 23026285200 | 2000 | EX | LAND - INVESTIGATE ROW/STAKE | 2023-11-01 | 1732 RICHMOND RD | B | 8416 | 0 | -8416 | 100% |  |  | 0 | AWEBER 11/1/2023 - 6 EASEMENTS ACQUIRED BY LANDS CHRIS DAVIS AFTER INVESTIG ATION INTO LACK OF KYTC ROW ACQUISITION IN 1950'S.
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026285300 | 558 | EX | EMER - RETIRE 159'-3"BSLP | 2023-07-24 | NICHOLASVILLE | A | 10816.0505 | 5197.96 | -5618.0905 | -52% |  |  | 0 | ABDN 159' OF 3'' BS LP.LEAK UNDER DRIVEWAY APPRON.MAIN NOT FEEDING ANY S/L.LEFT 15' OF 3'' ACTIVE. SOAP TEST END CAP AT OP FOR 5MINS TEST OK. BHB NGF. INSTALLED ANODE DENSO WRAPPED.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026285500 | 584 | EX | RETIRE REG STATION #1129 | 2023-11-30 | 4130 GEORGETOWN RD | F | 22153.7376 | 19139.56 | -3014.1776 | -14% |  |  | 0 | CCC#54039
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026286300 | 562 | EX | RETIRE 306' OF 3"BSLP MAIN | 2023-09-05 | CHRYSALIS CT | A | 7586.4374 | 4872.41 | -2714.0274 | -36% |  |  | 0 | ABN. 40' OF PLASTIC AND 306' OF STEEL MAIN. PURGE ALL GAS OUT. PLUGGED ENDS NGF AFTER PURGED. USED EF EC, ST AT OP, TG. R.CRAWFORD 9-5-23
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026286800 | 555 | EX | INSTALL 100' OF 2"PMIP MAIN | 2023-09-05 | 3422 MONTAVESTA RD | A | 8938.3422 | 13755.57 | 4817.2278 | 54% | 100 | 101 | 136.1938 | SPOTTED UTILITIES WITH VAC TRUCK. BORED IN 100' OF 020 P MAIN, PRESSURE TEST 1 HOUR AT 90#, TG. ST LTI, TG. R.CRAWFORD 9-5-23
KY | KY - WEST | 2621 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 23026288000 | 557 | EX | EMER - INSTALL 5'-2" PMMP | 2023-08-09 | 3438 BIRKENHEAD | A | 3242.0133 | 267.7 | -2974.3133 | -92% | 5 | 5 | 53.54 | RELACED 5' OF 020 PMP DUE TO SOCKET ON TEE LEAKING. TESTED 5' OF 020 FOR 1HR AT 90LBS.TEST OK. SOAP TEST 2 2'' EFC AT OP. TEST OK. BHB NGF.
KY | KY - WEST | 2621 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 23026288100 | 558 | EX | EMER - RETIRE 5'-2" PMMP | 2023-08-10 | 3438 BIRKENHEAD | A | 119.4953 | 1.39 | -118.1053 | -99% |  |  | 0 | RELACED 5' OF 020 PMP DUE TO SOCKET ON TEE LEAKING. TESTED 5' OF 020 FOR 1HR AT 90LBS.TEST OK. SOAP TEST 2 2'' EFC AT OP. TEST OK. BHB NGF.
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026288200 | 909 | EX | INSTALL VERIZON MODEM | 2023-08-17 | 2350 FORTUNE DR | F | 4954.3422 | 1861.82 | -3092.5222 | -62% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026288300 | 910 | EX | RETIRE SATELLITE COMM EQUIP | 2023-08-17 | 2350 FORTUNE DR | F | 119.4953 | 0 | -119.4953 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026289100 | 577 | EX | INSTALL FENCE | 2023-10-30 | 1313 OLD FRANKFORT PK | F | 26355.734 | 23214.65 | -3141.084 | -12% |  |  | 0 | NOT ON SITE, OFFICE PAPERWORK
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026290800 | 557 | EX | INSERT/INSTALL 160'-3"PMLP MN | 2023-10-20 | 901 N BROADWAY ST | A | 46254.1681 | 45549.98 | -704.1881 | -2% | 160 | 173 | 263.2947 | TEST FROM POINT A TTO B 90 LB FOR 1 HR TEST 2 IN HV TEE AND 2 IN MAIN FROM POINT A TO B 90 LB FOR 1 HR
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026290900 | 558 | EX | RETIRE 60' OF 3"BSLP MAIN | 2023-10-20 | 901 N BROADWAY ST | A | 119.4953 | 7967.87 | 7848.3747 | 6,568% |  |  | 0 | ABDN 82 FT OF 4" BS MAIN AND 143 FT OF 2 " BS MAIN PURGED OUT AND SEALED UP AND INSTALLED ALL NEW 3 "PL MAIN
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 23026292501 | 561 | EX | INSTALL 800' OF 2-4" PMMP | 2023-10-06 | 1500 LEESTOWN RD | B | 229159.9279 | 232050.11 | 2890.1821 | 1% | 700 | 794 | 292.2545
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026292600 | 575 | EX | DOCUMENT 20'EASEMENT FROM UK | 2023-09-07 | COLUMBIA AV | F | 38069 | 34094.48 | -3974.52 | -10% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026294500 | 560 | EX | RETIRE 338' OF 4"BSLP MAIN | 2023-12-14 | COCHRAN DR | A | 4190.6844 | 6772.76 | 2582.0756 | 62% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026294800 | 555 | EX | INSTALL 225' OF 2"PMMP MAIN | 2023-12-05 | 491 RETRAC RD | B | 19109.6064 | 28626.52 | 9516.9136 | 50% | 225 | 263 | 108.8461
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026296800 | 561 | EX | EMER - INSTALL 40'-4" PMMP | 2023-10-25 | BRANNON RD | B | 32230.3112 | 47320.11 | 15089.7988 | 47% | 65 | 90 | 525.779
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026296900 | 562 | EX | EMER - RETIRE 40'-4" CSMP | 2023-10-25 | BRANNON RD | B | 122.9261 | 0 | -122.9261 | 100% |  |  | 0
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026297200 | 557 | EX | EMER - INSTALL 13'-2" PMMP | 2023-10-12 | 3832 GRASSY CREEK RD | A | 9353.5801 | 4970.8 | -4382.7801 | -47% | 16 | 23 | 216.1217 | VALVE RETIRED.SOAP TEST END CAPS AT OP FOR 5MINS. TEST OK.BHB NGF LEAKING 020 P CRITICAL VALVE.LEAKING FROM STEM.RETIRED VALVE WITH 020 BYPASS.TESTED BYPASS AS MAIN FOR 1HR AT 90LBS.TEST OK INSTALLED TWO END CAPS AT VALVE TO ABDN VALVE.020 BYPASS MADE TO ACVTIVE MAIN AFTER
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026297300 | 558 | EX | EMER - RETIRE 2'-2" PMP | 2023-10-12 | 3832 GRASSY CREEK RD | A | 122.9261 | 5943.6 | 5820.6739 | 4,735% |  |  | 0 | VALVE RETIRED.SOAP TEST END CAPS AT OP FOR 5MINS. TEST OK.BHB NGF LEAKING 020 P CRITICAL VALVE.LEAKING FROM STEM.RETIRED VALVE WITH 020 BYPASS.TESTED BYPASS AS MAIN FOR 1HR AT 90LBS.TEST OK INSTALLED TWO END CAPS AT VALVE TO ABDN VALVE.020 BYPASS MADE TO ACVTIVE MAIN AFTER
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 23026299400 | 2000 | EX | PERFORM CONFLICT ASSESSMENT | 2023-11-01 | 1500 RUSSELL CAVE RD | B | 5636 | 0 | -5636 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026300800 | 557 | EX | EMER-INSTALL 5' OF 3"PMLP | 2023-10-10 | 436 OHIO ST | A | 4600.4752 | 5351.34 | 750.8648 | 16% | 5 | 5 | 1070.268
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026300900 | 558 | EX | EMER-RETIRE 5' OF 3"PLP MAIN | 2023-10-10 | 436 OHIO ST | A | 122.9261 | 0 | -122.9261 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026301000 | 557 | EX | EMER-INSTALL 2' OF 4"PMMP MAIN | 2023-05-31 | 1071 KELSEY DR | A | 4675.4752 | 3269.69 | -1405.7852 | -30% | 2 | 2 | 1634.845
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026301100 | 558 | EX | EMER-RETIRE 2' OF 4"PAMP MAIN | 2023-05-31 | 1071 KELSEY DR | A | 122.9261 | 0 | -122.9261 | 100% |  |  | 0
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 23026303700 | 557 | EX | EMER - INSTALL 5' OF 2" PMMP | 2023-10-27 | 1291 LATONIA PK | A | 147.9261 | 579.53 | 431.6039 | 292% | 0 | 3 | 193.1767
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 23026303800 | 558 | EX | EMER - RETIRE 3' OF 2" PAMP | 2023-10-27 | 1291 LATONIA PK | A | 124.9261 | 114.6 | -10.3261 | -8% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026304100 | 562 | EX | RETIRE 667' OF 2"PMMP MAIN | 2023-11-29 | 144 STATE ST | A | 5490.3441 | 4930.16 | -560.1841 | -10% |  |  | 0 | ABND MAIN ON STATE ST
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026305300 | 557 | EX | EMER-INSTALL 11'-2" PMMP | 2023-11-13 | TATES CREEKS RD | A | 17054.8912 | 5028.51 | -12026.3812 | -71% | 11 | 11 | 457.1373 | INSTALLED 11' NEW 2"PL MAIN DURING DAMAGE/HIT LINE FROM BANK CAVE IN INSIDE UTILITY CONTRACTORS EXCAVATION-BHB,NGF-NGF UPON DEP
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026305400 | 558 | EX | EMER-RETIRE 11'-2" PMMP | 2023-11-13 | TATES CREEKS RD | A | 124.9261 | 383.65 | 258.7239 | 207% |  |  | 0 | ABND 11'SECTION OF MAIN FOR DAMAGE
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026307700 | 557 | EX | EMER - INSTALL 5'-2" PMMP | 2023-12-07 | 920 WITTHUHN WY | A | 5646.8353 | 3376.54 | -2270.2953 | -40% | 5 | 5 | 675.308
KY | KY - WEST | 2621 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026307800 | 558 | CO | EMER - RETIRE 5'-2" PMP | 2023-12-07 | 920 WITTHUHN WY | A | 123.4493 | 0 | -123.4493 | 100% |  |  | 0
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026307900 | 557 | EX | EMER-INSTALL 10'-4"PMMP/VALVE | 2023-12-05 | 103 FOREST TL | A | 6246.9893 | 8046.73 | 1799.7407 | 29% | 10 | 10 | 804.673 | LEAKING MAIN VALVE.LEAK FROM STEM.REPLACED WITH NEW VALVE. TESTED 10' OF 040 WITH VALVE FOR 1HR AT 90LBS.TEST OK. SOAP TEST 2 EFC AT OP FOR 5MINS.TEST OK. BHB NGF
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026308000 | 558 | EX | EMER-RETIRE 10'-4"PMP/C8-150 | 2023-12-05 | 103 FOREST TL | A | 123.4493 | 147.12 | 23.6707 | 19% |  |  | 0 | LEAKING MAIN VALVE.LEAK FROM STEM.REPLACED WITH NEW VALVE. TESTED 10' OF 040 WITH VALVE FOR 1HR AT 90LBS.TEST OK. SOAP TEST 2 EFC AT OP FOR 5MINS.TEST OK. BHB NGF
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 23026308900 | 557 | EX | EMER INSTALL 4' OF 3" PMMP | 2023-12-22 | 1158 KELSEY DR | A | 3360.6855 | 2961.2 | -399.4855 | -12% | 10 | 4 | 740.3 | INST 4'- 3" PL MAIN PER ENGINEERED PLAN AND GAS STANDARDS. TEST NEW MAIN @ 90LB 5MIN OK. SOAP TEST TIE-IN @ OP OK. WORKED ON 12/19/23. MCRAIG 12/22/23
KY | KY - WEST | 2621 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 23026309000 | 558 | EX | EMER RETIRE 4' OF 3" PMP | 2023-12-22 | 1158 KELSEY DR | A | 123.4493 | 218.46 | 95.0107 | 77% |  |  | 0 | RETIRE 4' OF 3" PL MAIN DUE TO LEAK IN ACCORDNANCE W/ ENGINEERING AND GAS STANDARDS. TEST NEW 4' PL @ 90LB 5MIN OK. SOAP TEST TIE-IN. WORKED 12/19/23. MCRAIG 12/22/23
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026309100 | 557 | EX | EMER-INSTALL 4'OF 2"PMMP MAIN | 2023-12-20 | 2009 FAMILY CR 4 | A | 4579.9666 | 2913.94 | -1666.0266 | -36% | 4 | 4 | 728.485 | INST 4'- 2" PL MAIN. TEST MAIN @ 90LB 5MIN OK. SOAP TEST TIE-IN @ OP OK. BHB NGF. CGI MAIN AND SVC OK. WRK 12/20/23. MCRAIG 1/3/24
KY | KY - WEST | 2621 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026309200 | 558 | EX | EMER-RETIRE 4' OF 3"PMP MAIN | 2023-12-20 | 2009 FAMILY CR 4 | A | 123.4493 | 259.03 | 135.5807 | 110% |  |  | 0 | RETIRE 4'- 2" PL MAIN DUE TO LEAKING WELD. WRK 12/20/23. MCRAIG 1/3/24
KY | KY - WEST | 2623 | U127466 | Sparks,Cynthia Joy | Miller,Gary | Belle,Eric | 17026708300 | 575 | EX | LAND FOR R1862 | 2019-08-12 | 110 GLENNS CREEK RD | F | 667.9784 | 0 | -667.9784 | 100% |  |  | 0
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 17026712401 | 561 | EX | INSTALL 4000'-2" & 6" PMMP | 2020-07-17 | E MAIN ST | B | 767672.4953 | 987300.97 | 219628.4747 | 29% | 3800 | 3861 | 255.7112 | OVERRUN EXPLANATION:THE FINA PAVING WAS ANTICIPATED TO BE DONE BY THE CITY; EVER, THAT FELL THROUGH. THE PAVING EXCEEDED THE ESTIMATE BY $280,000.
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 17026712500 | 562 | EX | RETIRE 3600'-2" & 6" BS&P | 2020-10-08 | E MAIN ST | B | 80.4051 | 20446.64 | 20366.2349 | 25,330% |  |  | 0
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 17026722200 | 2000 | EX | INVESTIGATE MAIN DEPTH | 2019-10-02 | 242 CARDWELL LN | A | 4871.8595 | 0 | -4871.8595 | 100% |  |  | 0 | INVESTIGATION WAS COMPLETED IN EARLY 2018 AND CONSTRUCTION OF CULVERT BY ST ATE WAS COMPLETED DURING SUMMER OF 2019. NOT SURE OF EXACT COMPLETIONS DAT E, BUT SITE IS NOW CLEAR. D.LEMONS 10/2/19
KY | KY - WEST | 2623 | U127466 | Sparks,Cynthia Joy | Miller,Gary | Belle,Eric | 17026730600 | 0001 | EX | UPRATE 2,199' - 4" PLP TO MP | 2019-02-15 | 100 ELKHORN DR | B | 1691.7001 | 0 | -1691.7001 | 100% |  |  | 0
KY | KY - WEST | 2623 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 17026740501 | 555 | EX | INSTALL 4,450' - 6/4/2" PMMP | 2019-03-28 | 134 AMERSON WY | B | 450558.9213 | 479246.27 | 28687.3487 | 6% | 4450 | 4711 | 101.7292 | PROJECT OVER RAN COMMIT DATE DUE TO HEAVY ROCK OVER 1000' WITH A MAJOR ROCK BORE
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026748900 | 2000 | EX | INVESTIGATE AND MAP SITE | 2019-02-11 | DELAPLANE RD |  | 4603.0752 | 0 | -4603.0752 | 100% |  |  | 0 | INVESTIGATION COMPLETED OF LAND RIGHTS. NO OTHER JO'S REQUIRED. D.LEMONS 2/ 11/19
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026749900 | 2000 | EX | INVESTIGATE R/W & EASEMENTS | 2019-11-26 | MAIN ST |  | 4719 | 0 | -4719 | 100% |  |  | 0 | INVESTIGATION COMPLETED, JO RELEASED TO CONSTRUCTION. D.LEMONS 11/26/19
KY | KY - WEST | 2623 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 18026761600 | 559 | EX | INSTALL 4" PIF | 2019-01-14 | 228 CLIFTON RD | B | 21889.8854 | 30474.32 | 8584.4346 | 39% | 20 | 16 | 1904.645
KY | KY - WEST | 2623 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 18026761700 | 560 | EX | RETIRE 5' - 4" CSMP | 2019-01-14 | 228 CLIFTON RD | B | 51.6839 | 1367.16 | 1315.4761 | 2,545% |  |  | 0
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026762102 | 587 | EX | INSTALL NEW GMB | 2021-04-20 | 113 GREAT BUFFALO TC | F | 544123.4415 | 551963 | 7839.5585 | 1% | 20 |  | 0 | GCCC TICKET NOT REQUIRED AT THIS TIME 1/11/21 CFARIS 1/13/21 GCCC TICKET NOT REQUIRED AT THIS TIME CFARIS 1/26/21 GCCC TICKET NOT REQUIRED FOR THIS JOB CFARIS DID NOT ENTER PREMISE CCC TICKET NOT REQUIRED 3/8/21 CFARIS 3/10/21 GCCC TICKET NOT REQUIRED CFARIS CCC TICKET NOT REQUIRED 3/16/21 CFARIS CCC TICKET NOT REQUIRED 3/18/21 CFARIS CMCHOLAN 4-13-2021 CCC TICKET NOT REQUIRED ON 9/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK. ERX PLACED IN SERVICE ON 9/13/2021 CFARIS
KY | KY - WEST | 2623 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 18026763200 | 555 | EX | INSTALL 6500' - 2"/4" PMMP | 2020-01-23 | PLEASANT VIEW DR LT43 | B | 367443.8945 | 447309.97 | 79866.0755 | 22% | 6590 | 5028 | 88.9638 | TTOY 6/8/2020 OVERRUN EXPLANATION: CONTRACT CHANGE MID PROJECT, INCREASED UNIT PRICES, ADDITIONAL LABOR ACCOUNTED FOR ~$25,000, AFUDC ACCOUNTED FOR EXTRA $2,500, SEGA INCREASED BY $8,000, ADDITIONAL ROCK EXCAVATION AND HEAVY ROCK BORE REQUIRED
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026775701 | 555 | EX | INSTALL 1,490' - 2"/6" PMIP | 2019-02-18 | REDDING RD LT160 | B | 156681.1595 | 174227.61 | 17546.4505 | 11% | 1490 | 2550 | 68.3246
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026776901 | 557 | EX | INSTALL 15,400 OF 2"/4"/6"PMMP | 2019-11-11 | HIGHLAND PY | B | 2640238.4188 | 3526925.46 | 886687.0412 | 34% | 15400 | 16236 | 217.2287 | TWALKER/KY 06-05-2020: JOB OVER RUN DUE TO CITY OF FRANKFORT PAVING REQUIRE MENTS WHICH ADDED $300,000 COST.
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026777000 | 558 | EX | RETIRE 14,800' OF 4"/6" BSLP | 2019-11-11 | HIGHLAND PY | B | 73.0037 | 334.76 | 261.7563 | 359% |  |  | 0
KY | KY - WEST | 2623 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 18026778601 | 555 | EX | INSTALL 3100' - 2"/4" PMMP | 2019-01-16 | SINCLAIR CT LT84 | B | 99496.0368 | 112278.35 | 12782.3132 | 13% | 3200 | 3112 | 36.0792
KY | KY - WEST | 2623 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 18026783401 | 555 | EX | INSTALL 5,400' - 2"/4" PMMP | 2019-04-09 | HERNDON BV LT115C | B | 230334.9213 | 250762.09 | 20427.1687 | 9% | 5420 | 5789 | 43.317
KY | KY - WEST | 2623 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 18026786201 | 555 | EX | INSTALL 3,250' - 2" PMMP | 2019-03-22 | WHISPERING PIN DR LT1 | B | 142507.1449 | 168826.19 | 26319.0451 | 18% | 3275 | 3481 | 48.4993
KY | KY - WEST | 2623 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 18026788300 | 2000 | EX | ACQUIRE LAND RIGHTS | 2020-01-22 | PISGAH PK | B | 9455 | 0 | -9455 | 100% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026791701 | 555 | EX | INSTALL 5400' OF 2"/4"PMMP | 2019-12-18 | CLASSIC CT LT1 | B | 204633.9866 | 179187.44 | -25446.5466 | -12% | 5400 | 5400 | 33.1829 | TWALKER/KY 06-05-2020: JOB COST UNDER RUN DUE TO LESS HARD SURFACE REPAIRS REQUIRED WHICH LOWERED CONTRACT COST BY $30000
KY | KY - WEST | 2623 | U127466 | Sparks,Cynthia Joy | Miller,Gary | Belle,Eric | 18026794900 | 561 | EX | INSTALL 10' - 3" PMLP | 2019-06-27 | FOUNTAIN AV | B | 9712.4728 | 30034.59 | 20322.1172 | 209% | 10 | 26 | 1155.1765 | INSTALLED 27' OF 3" P-MAIN, TEST MAIN ONSITE 90PSI 1HR OK, ST 2 BOLTED COUP AT TIE INS AND 6 SADDLES AT OP OK, BHB CGI NGF, CO OFFSITE, BAGGED OFF MAIN ALLOWED WAIT TIME FOR GAUGES BEFORE AND AFTER, INSTALLED 2- 9LB ANODES ON BOTH SIDES OP PLASTIC, MAIN READ BEFORE SEPERATION -0.592, MAIN READ ON CLAYTON AVE SIDE AFTER SEPERATION -0.601, MAIN READ ON E.JACKSON SIDE AFTER SEPERATION -0.586, CDESPAIN, DWAUGH RLA INSTALLED 27' OF 3" P-MAIN, TEST MAIN ONSITE 90PSI 1HR OK, ST 2 BOLTED COUP AT TIE INS AND 6 SADDLES AT OP OK, BHB CGI NGF, CO OFFSITE, BAGGED OFF MAIN ALLOWED WAIT TIME FOR GAUGES BEFORE AND AFTER, CDESPAIN RLA DWAUGH
KY | KY - WEST | 2623 | U127466 | Sparks,Cynthia Joy | Miller,Gary | Belle,Eric | 18026795000 | 562 | EX | RETIRE 10' - 3" BSLP | 2019-06-27 | FOUNTAIN AV | A | 72.6127 | 5583.52 | 5510.9073 | 7,589% |  |  | 0
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026798100 | 557 | EX | INSTALL 2" SS FITTING | 2019-01-14 | CLIFTON DR | B | 7049.9001 | 8906.34 | 1856.4399 | 26% |  |  | 0 | ABANDONED 78' OF 2" CSMP MAIN. TESTED 2" SST @ 90 PSIG FOR 15MINS. SOAP TE STED CAPS.
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026798200 | 558 | EX | RETIRE 39'-2" CSMP | 2019-01-14 | CLIFTON DR | B | 71.8476 | 0 | -71.8476 | 100% |  |  | 0 | ABANDONED 78' OF 2" CSMP MAIN. PURGED TO 0% GAS READINGS. INT/EXT INSPECTIO N COMPLETED BY BJACKSON @ 1400 ON 1/14/19.
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026800402 | 555 | EX | INSTALL 9000' OF 2"PMMP MAIN | 2019-10-08 | 8 CEDAR RIDGE LN LT1C | B | 597234.6599 | 601602 | 4367.3401 | 1% | 6050 | 9069 | 66.3361
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026814900 | 583 | EX | INST. FN 129 EXTRA LP OPP | 2020-11-23 | LAFAYETTE DR | F | 24062.1646 | 41183.17 | 17121.0054 | 71% | 50 |  | 0 | REGULATORS AND ER350 INSTALLED BY CHRIS COX ON 11/23/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/25/2021 GCCC TICKET NOT REQUIRED ON 2/25/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026815000 | 584 | EX | RET. FN 129 FOR EXTRA LP OPP | 2020-11-23 | LAFAYETTE DR | F | 53.6219 | 430 | 376.3781 | 702% |  |  | 0 | REGULATORS REPLACED BY CHRIS COX ON 11/23/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/25/2021 GCCC TICKET NOT REQUIRED ON 2/25/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026815100 | 583 | EX | INST. FN 130 EXTRA LP OPP | 2019-05-09 | THOMAS PL | F | 21708.8722 | 28514.32 | 6805.4478 | 31% | 50 |  | 0 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 5/9/19 ER350 INSTALLED BY WADE SHIMFESSEL ON 8/3/20 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/5/21 GCCC TICKET NOT REQUIRED ON 2/5/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026815200 | 584 | EX | RET. FN 130 FOR EXTRA LP OPP | 2019-05-09 | THOMAS PL | F | 54.9718 | 377.46 | 322.4882 | 587% |  |  | 0 | REGULATOR REPLACED BY CYNTHIA FARIS ON 5/9/19 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/5/21 GCCC TICKET NOT REQUIRED ON 2/5/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026815300 | 583 | EX | INST. FN 132 EXTRA LP OPP | 2019-06-14 | HOLMES ST | F | 21708.8722 | 26365.04 | 4656.1678 | 21% | 50 |  | 0 | INLET AND OUTLET VLVS FULL OPEN - BYPASS VLV OFF AND LOCKED GCCC# 13164 CMCHOLAN 2-25-2021 CCC# 13164 GCCC#13706 CMCHOLAN 3-2-2021 CCC#13706 REGULATOR INSTALLED BY JAMES PASLEY ON 6/14/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026815400 | 584 | EX | RET. FN 132 FOR EXTRA LP OPP | 2019-06-14 | HOLMES ST | F | 54.9718 | 267.47 | 212.4982 | 387% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 6/14/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026815500 | 583 | EX | INST. FN 134 EXTRA LP OPP | 2019-06-17 | LEWIS ST | F | 21708.8722 | 16647.05 | -5061.8222 | -23% | 50 |  | 0 | INLET AND OUTLET VLVS FULL ON - OUTLET VLVS OFF AND LOCKED JPASLEY REGULATOR INSTALLED BY JAMES PASLEY ON 6/17/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 6/22/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/25/2021 GCCC TICKET NOT REQUIRED ON 2/25/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026815600 | 584 | EX | RET. FN 134 FOR EXTRA LP OPP | 2019-06-17 | LEWIS ST | F | 54.9718 | 251.98 | 197.0082 | 358% |  |  | 0 | REGULATOR REPLAACED BY JAMES PASLEY ON 6/17/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/25/2021 GCCC TICKET NOT REQUIRED ON 2/25/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026815700 | 583 | EX | INST. FN 135 EXTRA LP OPP | 2020-09-15 | STANLEY ST | F | 22470.1646 | 39708.38 | 17238.2154 | 77% | 55 |  | 0 | REGULATOR INSTALLED BY WADE SHIMFESSEL ON 9/15/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/25/2021 GCCC TICKET NOT REQUIRED ON 2/25/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026815800 | 584 | EX | RET. FN 135 FOR EXTRA LP OPP | 2020-09-15 | STANLEY ST | F | 53.6219 | 871.34 | 817.7181 | 1,525% |  |  | 0 | REGULATOR REPLACED BY WADE SHIMFESSEL ON 9/15/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/25/2021 GCCC TICKET NOT REQUIRED ON 2/25/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026815900 | 583 | EX | INST. FN 136 EXTRA LP OPP | 2019-06-18 | SUTTERLIN LN | F | 21708.8722 | 16995.17 | -4713.7022 | -22% | 50 |  | 0 | INLET AND OUTLEY VLV FULL OPEN - BYPASS VLV OFF AND LOCKED JPASLEY 6-18-19 REGULATOR INSTALLED BY JAMES PASLEY ON 6/18/19 ER350 INSTALLED BY WADE SHIMFESSEL ON 6/22/20 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/5/21 GCCC TICKET NOT REQUIRED ON 2/5/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026816000 | 584 | EX | RET. FN 136 FOR EXTRA LP OPP | 2019-06-18 | SUTTERLIN LN | F | 54.9718 | 246.44 | 191.4682 | 348% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 6/18/19 BY JAMES PASLEY PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/5/21 GCCC TICKET NOT REQUIRED ON 2/5/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026816100 | 583 | EX | INST. FN 14429 EXTRA LP OPP | 2019-06-22 | WALNUT ST | F | 21708.8722 | 26276.03 | 4567.1578 | 21% | 50 |  | 0 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 6/22/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026816200 | 584 | EX | RET. FN 14429 FOR EXTRA LP OPP | 2019-06-22 | WALNUT ST | F | 54.9718 | 364.39 | 309.4182 | 563% |  |  | 0 | REGULATOR REPLACED BY CYNTHIA FARIS ON 6/22/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026816700 | 583 | EX | INST. FN 147 EXTRA LP OPP | 2019-07-03 | ROLLING ACRES DR | F | 21708.8722 | 14475.08 | -7233.7922 | -33% | 50 |  | 0 | REGULATOR INSTALLED BY JAMES PASLEY ON 7/3/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/23/2021 GCCC TICKET NOT REQUIRED ON 2/23/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS PER CYNTHIA FARIS - STATION HAD EXISTING ERX, BATTERY, SOLAR & RV50 NO NEW FACILITIES CREATED FOR THESE.
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026816800 | 584 | EX | RET. FN 147 FOR EXTRA LP OPP | 2019-07-03 | ROLLING ACRES DR | F | 54.9718 | 394.2 | 339.2282 | 617% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 7/3/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/23/2021 GCCC TICKET NOT REQUIRED ON 2/23/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026816900 | 583 | EX | INST. FN 190 EXTRA LP OPP | 2019-05-21 | N COURT AL | F | 21708.8722 | 33524.23 | 11815.3578 | 54% | 50 |  | 0 | INLET AND OUTLET VLVS FULLY OPEN AND BYPASS VLV OFF AND LOCKED JPASLEY 5-21-19 1050 PF REGULATOR INSTALLED BY JPASLEY 5/21/19 PAPERWORK COMPLETED BY CYNTHIA FARIS 1/25/21
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026817000 | 584 | EX | RET. FN 190 FOR EXTRA LP OPP | 2019-05-21 | N COURT AL | F | 54.9718 | 248.99 | 194.0182 | 353% |  |  | 0 | MONITOR REGULATOR REPLACED BY JAMES PASLEY 5/21/19 PAPERWORK COMPLETED BY CYNTHIA FARIS 1/25/21
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026817100 | 583 | EX | INST. FN 193 EXTRA LP OPP | 2019-05-20 | 521 N HAMILTON ST | F | 21708.8722 | 26494.08 | 4785.2078 | 22% | 50 |  | 0 | INLET AND OUTLET VALVE ON AND LOCKED - BYPASS VALVE OFF AND LOCKED JPASLEY 5-20-19 REGULATOR REPLACED BY JIM PASLEY ON 5/20/19 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/25/21
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026817200 | 584 | EX | RET. FN 193 FOR EXTRA LP OPP | 2019-05-20 | 521 N HAMILTON ST | F | 54.9718 | 252.76 | 197.7882 | 360% |  |  | 0 | MONITOR REGULATOR REPLACED BY JIM PASLEY ON 5/20/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS 1/25/2020
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026817300 | 583 | EX | INST. FN 194 EXTRA LP OPP | 2019-05-21 | S COURT AL | F | 21708.8722 | 34943.03 | 13234.1578 | 61% | 50 |  | 0 | INLET AND OUTLET VLV ON AND LOCKED - BYPASS VLV OFF AND LOCKED LOWERED PRESSURES BACK TO 10" WC REGULATOR INSTALLED BY JAMES PASLEY ER350 INSTALLED BY CYNTHIA FARIS WITH ACP PAPERWORK COMPLETED BY CYNTHIA FARIS APPROVAL JUST OBTAINED TO CO JOB AND SEND TO CLOSE OUT
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026817400 | 584 | EX | RET. FN 194 FOR EXTRA LP OPP | 2019-05-21 | S COURT AL | F | 54.9718 | 253.79 | 198.8182 | 362% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY PAPERWORK COMPLETED BY CYNTHIA FARIS JUST OBTAINED APPROVAL TO CO AND SEND JOB TO CLOSE OUT
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026817500 | 583 | EX | INST. FN 199 EXTRA LP OPP | 2019-05-22 | COLLEGE ST | F | 21708.8722 | 31321.51 | 9612.6378 | 44% | 50 |  | 0 | INLET AND OUTLET VALVES FULL OPEN - BYPASS VALVE FULLY CLOSED JPASLEY 5-22-19 MONITOR REGULATOR INSTALLED BY JAMES PASLEY 5/22/19 PAPERWORK COMPLETED BY CYNTHIA FARIS 1/25/21 GCCC TICKET NOT REQUIRED FOR PAPERWORK COMPLETION 1/25/21 NOT AT STATION OFF SITE AT REMOTE LOCATION
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026817600 | 584 | EX | RET. FN 199 FOR EXTRA LP OPP | 2019-05-22 | COLLEGE ST | F | 54.9718 | 247.38 | 192.4082 | 350% |  |  | 0 | REGULATOR REPLACEMENT WORKED BY JAMES PASLEY 5/22/19 PAPERWORK COMPLETED BY CYNTHIA FARIS 1/25/21
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026817700 | 583 | EX | INST. FN 202 EXTRA LP OPP | 2020-06-02 | 120 WASSAU AL | F | 37874.1646 | 77249.07 | 39374.9054 | 104% | 52 |  | 0 | GCCC TICKET NOT REQUIRED NOT AT STATION OFF SITE COMPLETING PAPERWORK 2/26/21 CFARIS REGULATORS REPLACED BY JAMES PASLEY ON 6/2/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/26/21 GCCC TICKET NOT REQUIRED ON 7/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS OVERRUN EXPLANATION: THIS JOB ORDER WAS PART OF A LARGE SET OF JOB ORDERS THAT WERE MANAGED BY MAJOR PROJECTS. THE COSTS WERE MANAGED AT THE PROJECT LEVEL RATHER THAN THE JOB ORDER LEVEL.
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026817800 | 584 | EX | RET. FN 202 FOR EXTRA LP OPP | 2020-06-02 | 120 WASSAU AL | F | 53.6219 | 13101.25 | 13047.6281 | 24,333% |  |  | 0 | REGULATORS REPLACED BY JAMES PASLEY ON 6/2/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/26/2021 GCCC TICKET NOT REQUIRED ON 7/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026817900 | 583 | EX | INST. FN 14557 EXTRA LP OPP | 2020-07-30 | 120 WALNUT ST | F | 39207.1646 | 45908.85 | 6701.6854 | 17% | 55 |  | 0 | REGULATORS AND ER350 INSTALLED BY WADE SHIMFESSEL ON 7/30/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/26/2021 GCCC TICKET NOT REQUIRED ON 2/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026818000 | 584 | EX | RET. FN 14557 FOR EXTRA LP OPP | 2020-07-30 | 120 WALNUT ST | F | 53.6219 | 0 | -53.6219 | 100% |  |  | 0 | REGULATORS REPLACED BY WADE SHIMFESSEL ON 7/30/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/26/2021 GCCC TICKET NOT REQUIRED ON 2/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026818100 | 583 | EX | INST. FN 14201 EXTRA LP OPP | 2019-06-10 | 197 FRANKFORT ST | F | 21708.8722 | 37179.93 | 15471.0578 | 71% | 50 |  | 0 | REGULATOR INSTALLED BY JAMES PASLEY ON 6/10/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 6/17/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/26/2021 GCCC TICKET NOT REQUIRED ON 2/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026818200 | 584 | EX | RET. FN 14201 FOR EXTRA LP OPP | 2019-06-10 | 197 FRANKFORT ST | F | 54.9718 | 249.64 | 194.6682 | 354% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 6/10/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/26/2021 GCCC TICKET NOT REQUIRED ON 2/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026818300 | 583 | EX | INST. FN 207 EXTRA LP OPP | 2019-06-13 | 202 BERRY AV | F | 21708.8722 | 45761.33 | 24052.4578 | 111% | 50 |  | 0 | INLET AND OUTLET VLV FULL ON - BYPASS OFF AND LOCKED REGULATOR INSTALLED BY JAMES PASLEY ON 6/13/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 6/15/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/26/2021 GCCC TICKET NOT REQUIRED ON 2/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026818400 | 584 | EX | RET. FN 207 FOR EXTRA LP OPP | 2019-06-13 | 202 BERRY AV | F | 54.9718 | 246.54 | 191.5682 | 348% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 6/13/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/26/2021 GCCC TICKET NOT REQUIRED ON 2/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026818500 | 583 | EX | INST. FN 208 EXTRA LP OPP | 2019-06-11 | 151 LOCUST ST | F | 21708.8722 | 30380.39 | 8671.5178 | 40% | 50 |  | 0 | INSTALLED SLAM SHUT SET POINTS 4" AND 20" W.C. MONITOR SET AT 14"W.C. INLE T & OUTLET VLVS ON, BYPASS OFF AND ALL VLV LOCKED. SOAP TEST OK. MMCKUNE 6-11-19. REGULATOR INSTALLED BY MIKE MCKUNE ON 6/11/2019 ER350 INSTALLED BY CYNTHIA FARIS ON 9/6/2019 ER350 REPLACED BY CHRIS COX ON 10/21/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/26/2021 GCCC TICKET NOT RQUIRED ON 2/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026818600 | 584 | EX | RET. FN 208 FOR EXTRA LP OPP | 2019-06-11 | 151 LOCUST ST | F | 54.9718 | 248.87 | 193.8982 | 353% |  |  | 0 | REGULATOR REPLACED BY MIKE MCKUNE ON 6/11/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/26/2021 GCCC TICKET NOT REQUIRED ON 2/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026818700 | 583 | EX | INST. FN 209 EXTRA LP OPP | 2020-07-08 | 120 HIGHVIEW DR | F | 21767.1646 | 39166.53 | 17399.3654 | 80% | 55 |  | 0 | GCCC TICKET NOT REQUIRED NOT AT STATION OFF SITE WORKING ON LP PAPERWORK 2/25/2021 CFARIS REGULATOR AND ER350 INSTALLED BY CHRIS COX ON 7/8/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/26/2021 GCCC TICKET NOT REQUIRED ON 2/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026818800 | 584 | EX | RET. FN 209 FOR EXTRA LP OPP | 2020-07-08 | 120 HIGHVIEW DR | F | 53.6219 | 1040.89 | 987.2681 | 1,841% |  |  | 0 | REGULATOR REPLACED BY CHRIS COX ON 7/8/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/26/2021 GCCC TICKET NOT REQUIRED ON 2/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026818900 | 583 | EX | INST. FN 210 EXTRA LP OPP | 2019-06-14 | 105 WOOLDRIDGE LN | F | 21708.8722 | 32905.82 | 11196.9478 | 52% | 50 |  | 0 | INLET AND OUTLET VLVS FULL OPEN - BYPASS VLV OFF AND LOCKED REGULATOR INSTALLED BY JAMES PASLEY ON 6/14/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 6/16/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/26/2021 GCCC TICKET NOT REQUIRED ON 2/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026819000 | 584 | EX | RET. FN 210 FOR EXTRA LP OPP | 2019-06-14 | 105 WOOLDRIDGE LN | F | 54.9718 | 303.1 | 248.1282 | 451% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 6/14/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/26/2021 GCCC TICKET NOT REQUIRED ON 2/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026819100 | 583 | EX | INST. FN 14426 EXTRA LP OPP | 2019-07-11 | MOCKINGBIRD LN | F | 21708.8722 | 30827.27 | 9118.3978 | 42% | 50 |  | 0 | REGULATOR INSTALLED BY JAMES PASLEY ON 7/11/19 ER350 INSTALLED 10/30/20 PAPERWORK COMPLETED BY CYNTHIA FARIS 2/4/21 GCCC TICKET NOT REQUIRED ON 2/4/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026819200 | 584 | EX | RET. FN 14426 FOR EXTRA LP OPP | 2019-07-11 | MOCKINGBIRD LN | F | 54.9718 | 320.32 | 265.3482 | 483% |  |  | 0 | REGULATOR REPLACED BY JIM PASLEY 7/11/19 PAPERWORK COMPLETED BY CYNTHIA FARIS 2/4/21 GCCC TICKET NOT REQUIRED ON 2/4/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026819300 | 583 | EX | INST. FN 218 EXTRA LP OPP | 2019-06-15 | 535 HOLMES ST | F | 21708.8722 | 26475.97 | 4767.0978 | 22% | 50 |  | 0 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 6/15/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/25/2021 GCCC TICKET NOT REQUIRED ON 2/25/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026819400 | 584 | EX | RET. FN 218 FOR EXTRA LP OPP | 2019-06-15 | 535 HOLMES ST | F | 54.9718 | 308.17 | 253.1982 | 461% |  |  | 0 | REGULATOR REPLACED BY CYNTHIA FARIS ON 6/15/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/25/2021 GCCC TICKET NOT REQUIRED ON 2/25/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026819500 | 583 | EX | INST. FN 219 EXTRA LP OPP | 2019-07-01 | COMPTON DR | F | 21708.8722 | 24740.79 | 3031.9178 | 14% | 50 |  | 0 | REGULATOR INSTALLED BY JAMES PASLEY ON 7/1/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/22/2021 GCCC TICKET NOT REQUIRED ON 2/22/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026819600 | 584 | EX | RET. FN 219 FOR EXTRA LP OPP | 2019-07-01 | COMPTON DR | F | 54.9718 | 319.67 | 264.6982 | 482% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 7/1/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS 02/22/2021 GCCC TICKET NOT REQUIRED ON 2/22/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026819700 | 583 | EX | INST. FN 350 EXTRA LP OPP | 2020-10-14 | TANGLEWOOD DR | F | 40148.1646 | 54102.95 | 13954.7854 | 35% | 55 |  | 0 | ACTUAL DATE 04/13/2020 04/16/2020 ENTERED BY MISTAKE INTO COMPUTER NEAL JOHNSON GCCC TICKET NOT REQUIRED OFF SITE NOT AT ANY STATION WORKING ON LP PAPERWORK CFARIS 1/28/21 REGULATORS INSTALLED BY CYTHIA FARIS AND JAMES PASLEY ON 10/14/20 ER350 INSTALLED BY CHRIS COX ON 10/21/20 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/29/20 GCCC TICKET NOT REQUIRED ON 1/29/20 NOT AT STATION COMPLETING PAPERWORK
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026819800 | 584 | EX | RET. FN 350 FOR EXTRA LP OPP | 2020-10-14 | TANGLEWOOD DR | F | 53.6219 | 802.6 | 748.9781 | 1,397% |  |  | 0 | REGULATORS REPLACED BY CYNTHIA FARIS AND JAMES PASLEY ON 10/14/20 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/29/20 GCCC TICKET NOT REQUIRED ON 1/29/20 OFF SITE NOT AT STATION COMPLETING PAPERWORK
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026819900 | 583 | EX | INST. FN 351 EXTRA LP OPP | 2020-12-10 | SERVICE DR | F | 21708.8722 | 29797.04 | 8088.1678 | 37% | 50 |  | 0 | REGULATOR AND ER350 INSTALLED BY CHRIS COX ON 12/10/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026820000 | 584 | EX | RET. FN 351 FOR EXTRA LP OPP | 2020-12-10 | SERVICE DR | F | 54.9718 | 374.3 | 319.3282 | 581% |  |  | 0 | REGULATOR REPLACED BY CHRIS COX ON 12/10/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026820100 | 583 | EX | INST. FN 352 EXTRA LP OPP | 2019-07-12 | 298 MYRTLE AV | F | 21708.8722 | 22668.02 | 959.1478 | 4% | 50 |  | 0 | GCCC TICKET NOT REQUIRED NOT AT STATION OFF SITE WORKING ON PAPERWORK 2/4/21 CFARIS REGULATOR INSTALLED BY JAMES PASLEY 7/12/19 PAPERWORK COMPLETED BY CYNTHIA FARIS 2/5/21 GCCC TICKET NOT REQUIRED ON 2/5/21 NOT AT STATION OFF SITE WORKING ON PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026820200 | 584 | EX | RET. FN 352 FOR EXTRA LP OPP | 2019-07-12 | 298 MYRTLE AV | F | 54.9718 | 316.47 | 261.4982 | 476% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 7/12/19 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/5/21 GCCC TICKET NOT REQUIRED ON 2/5/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026820300 | 583 | EX | INST. FN 354 EXTRA LP OPP | 2020-06-04 | 313 N WINTER ST | F | 42364.1646 | 37058.39 | -5305.7746 | -13% | 55 |  | 0 | 2/17/21 GCCC TICKET NOT REQUIRED NOT AT STATION OFF SITE WORKING ON LP PAPERWORK CFARIS 2/19/21 GCCC TICKET NOT REQUIRED NOT AT STATION OFF SITE COMPLETING LP PAPERWORK CFARIS REGULATOR AND ER350 INSTALLED BY JAMES PASLEY ON 6/4/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/13/2021 GCCC TICKET NOT REQUIRED ON 5/13/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026820400 | 584 | EX | RET. FN 354 FOR EXTRA LP OPP | 2020-06-04 | 313 N WINTER ST | F | 53.6219 | 430 | 376.3781 | 702% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 6/4/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/13/2021 GCCC TICKET NOT REQUIRED ON 5/13/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026845900 | 555 | EX | INSTALL 110'- 4"CSHP INLET MN | 2019-02-19 | WOODLAWN AV LT203 | B | 42605.0459 | 58871.29 | 16266.2441 | 38% | 110 | 131 | 449.3992
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026848501 | 555 | EX | INSTALL 7400' OF 2"/4"/6"PMMP | 2019-08-06 | ROCKY CREEK RD 306 | B | 499644.9702 | 573876.27 | 74231.2998 | 15% | 7200 | 7453 | 76.9994 | PAST COMMIT DATE DUE TO WEATHER, ROCK ON JOB, BEING PULLED OFF TO COMPLETE OTHER JOBS
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026849200 | 587 | EX | INSTALL MI WIRELESS EFC | 2020-02-14 | 824 LEMONS MILL RD | F | 10338.964 | 13047.12 | 2708.156 | 26% |  |  | 0 | WAITING ON EQUIPMENT EFC BACKORDERED
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026849300 | 588 | EX | RETIRE EME UNIT | 2020-02-14 | 824 LEMONS MILL RD | F | 64.5603 | 0 | -64.5603 | 100% |  |  | 0 | WAITING ON EQUIPMENT EFC BACKORDERED
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026849900 | 573 | EX | INSTALL REG #1863 DUAL RUN | 2019-04-17 | US 460 BYPASS | F | 93915.8656 | 89581.41 | -4334.4556 | -5% |  |  | 0 | JOB WAS ON HOLD FOR LAND/ACCESS ISSUES AND CREW AVAILABILITY
KY | KY - WEST | 2623 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 18026850000 | 559 | EX | REPLACE VALVE | 2019-01-10 | COMANCHE TL | B | 7869.4493 | 12239.28 | 4369.8307 | 56% | 20 | 1 | 12239.28 | REPLACED 4" PLASTIC BALL VALVE. TESTED AT 90PSIG FOR 1 HOUR.
KY | KY - WEST | 2623 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 18026850100 | 560 | EX | RETIRE VALVE | 2019-01-10 | COMMANCHE TL | B | 104.1449 | 0 | -104.1449 | 100% |  |  | 0
KY | KY - WEST | 2623 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026851100 | 909 | EX | UPGRADE COMMUNICATION EQUIP | 2019-02-19 | SHOWALTER DR | F | 8776.5399 | 5532.32 | -3244.2199 | -37% |  |  | 0 | ERX CELL MODEM UPGRADED TO RV50 BY ACP
KY | KY - WEST | 2623 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026853200 | 909 | EX | UPGRADE COMM EQUIPMENT | 2019-03-22 | E TODD ST | F | 8776.5399 | 3164.91 | -5611.6299 | -64% |  |  | 0 | ERX MODEM UPGRADED TO RV50 BY ACP
KY | KY - WEST | 2623 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026853400 | 909 | EX | UPGRADE COMM EQUIPMENT | 2019-03-27 | LOUISVILLE RD | F | 8776.5399 | 5934.04 | -2842.4999 | -32% |  |  | 0 | SUPER SOLAR KIT AND RV50 INSTALLED BY ACP
KY | KY - WEST | 2623 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026853600 | 909 | EX | UPGRADE COMM EQUIPMENT | 2019-01-30 | DELAPLANE RD | F | 8776.5399 | 2273.08 | -6503.4599 | -74% |  |  | 0 | BACK UP CELL MODEM UPGRADED TO RV50 CELL MODEM BY ACP
KY | KY - WEST | 2623 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026853700 | 910 | EX | RETIRE 2G/3G EQUIPMENT | 2019-01-30 | DELAPLANE RD | F | 145.0075 | 0 | -145.0075 | 100% |  |  | 0 | CDMA MODEM UPGRADED TO RV50 CELL MODEM BY ACP
KY | KY - WEST | 2623 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026854400 | 909 | EX | UPGRADE COMM EQUIPMENT | 2019-02-08 | WILKINSON BV | F | 8776.5399 | 6938.48 | -1838.0599 | -21% |  |  | 0
KY | KY - WEST | 2623 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026854600 | 909 | EX | UPGRADE COMM EQUIPMENT | 2019-01-29 | US 460 - GEORGETOWN RD | F | 8776.5399 | 2953.08 | -5823.4599 | -66% |  |  | 0 | BACK UP CELL MODEM UPGRADED TO RV50 CELL MODEM BY ACP
KY | KY - WEST | 2623 | BKSLONE |  |  |  | 19026855200 | 2000 | EX | WOODLAND PARK SUB - GRADING | 2021-01-19 | WOODLAND PARK SUB'N |  | 8668 | 0 | -8668 | 100% |  |  | 0
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026856100 | 584 | EX | RETIRE GAUGE | 2021-07-09 | COMANCHE TR | F | 73.6972 | 0 | -73.6972 | 100% |  |  | 0 | WAITING ON PE APPROVAL AND ISO SKETCH CCC TICKET NOT REQUIRED ON 9/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | BKSLONE |  |  |  | 19026856400 | 2000 | EX | CARDINAL DR IMPROVEMENTS | 2020-06-22 | CARDINAL DR |  | 9478 | 0 | -9478 | 100% |  |  | 0 | 6/22/2020: SENT TO CLOSE OUT (BKSLONE)
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026856500 | 557 | EX | INSTALL 445'-4" PMLP | 2019-01-23 | CRITTENDEN RD | B | 29115.9203 | 172303.77 | 143187.8497 | 492% | 448 | 447 | 385.467 | REPLACED 4" BSLP MAIN WITH 4" PE. OVERRUN EXPLANATION: THIS WAS A MULTIPLE DAY WATER OFF ISSUE WITH MANY EMPL OYES WORKING LONG HOURS FOR MORE THAN ONE OUTAGE. THE CHARGES FOR THE EMPLOYEES THAT WERE SUPPORTING THE EFFORT WHERE NOT CO NSIDERED IN THE ORIGINAL ESTIMATE. ADDITIONALLY, THE 4 MAN CONSTRACT CREW WORKED 52 HOURS OF OVERTIME AND THRE E TIMES THE AMOUNT OF ESTIMATED REGULAR TIME.
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026856600 | 558 | EX | RETIRE 443'-4" BSLP | 2019-01-22 | CRITTENDEN | B | 73.6972 | 785.12 | 711.4228 | 965% |  |  | 0
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026856800 | 561 | EX | INSTALL 3659'-2",4"&6" PMMP | 2021-06-21 | 2ND ST | B | 1978069.5146 | 1309555.48 | -668514.0346 | -34% | 3659 | 3730 | 351.0873 | W. 2ND ST SEING TIES WILL NEED TO BE UPDATED ONCE ROAD CONSTRUCTION PROJECT IS COMPLETE. ALL POLES AND MANHOLES ARE BEING MOVED. OVERRUN EXPLANATION HAS BEEN COMPLETE AND LOADED INTO WMSDOCS WORKSPACE. D. LEMONS 12/23/2021
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026856900 | 562 | EX | RETIRE 2166'- 2"-6" P/CS/BS | 2021-06-10 | 2ND ST | B | 94.7274 | 468.94 | 374.2126 | 395% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026857400 | 555 | EX | INSTALL 80' OF 2"PMMP MAIN | 2019-02-14 | 237 WARD HALL MN | B | 7770.1797 | 5253.13 | -2517.0497 | -32% | 80 | 97 | 54.156
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026857600 | 2000 | EX | INVESTIGATE PIPELINE CROSSIN | 2019-04-01 | 195 SOARDS RD | A | 7500 | 0 | -7500 | 100% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026857700 | 909 | EX | INSTALL SOLAR MI WIRELESS | 2020-04-28 | ROLLING ACRES DR | F | 12142.6047 | 11481.26 | -661.3447 | -5% |  |  | 0 | COMPLETING INSTALL PUSHED BACK DUE TO LP PROJECT AND COMPLIANCE WORK
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026858000 | 555 | EX | INSTALL 400' OF 4"PMLP MAIN | 2019-02-15 | 107 COLLISION CENTER DR | B | 23897.5118 | 42516.78 | 18619.2682 | 78% | 400 | 420 | 101.2304
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026858800 | 2000 | EX | ACQUIRE NEW REG STATION LOT | 2023-04-10 | MUDDY FORD KY-922 RD | B | 25680 | 0 | -25680 | 100% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026858900 | 2000 | EX | INVESTIGATE ROAD RIGHT OF WAY | 2019-03-11 | HIGHLAND PARKWAY | B | 16834 | 0 | -16834 | 100% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026859200 | 555 | EX | INSTALL 3250' OF 2"PMMP MAIN | 2019-04-03 | 124 BROOKFORD WY | B | 151407.471 | 162596.23 | 11188.759 | 7% | 3250 | 3040 | 53.4856
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026861900 | 555 | EX | INSTALL 250' OF 2"/4"PMMP | 2019-07-10 | 201 QUALITY DR | B | 17824.6192 | 18936.14 | 1111.5208 | 6% | 250 | 220 | 86.0734 | UNABLE TO MAKE COMMIT DATE DUE TO TIMING OF START DATE AND EXTRA BORE ADDED TO JOB .
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026863200 | 555 | EX | INSTALL 1600' OF 2"PMIP MAIN | 2019-04-29 | 1301 SEMINOLE TR LT | B | 63001.6694 | 104820.38 | 41818.7106 | 66% | 1600 | 1725 | 60.7654 | COMMIT DATE WAS NOT MET DUE TO THE CREW ENCOUNTERING ROCK DURING THE BORING PROCESS. SCHEDULING AND ENGINEERING ADV OVERRUN EXPLANATION: PROJECT WAS PLANNED FOR REGULATOR DIRECTIONAL BORE; HO WEVER, THERE WERE 533 UNDITS OF DIRECTIONAL ROCK BORE THAT WERE REQUIRED. T HE ADDED COST OF ROCK BORE PLUS THE OVERHEAD EFFECT OF THOSE ADDITIONAL COS T WERE THE PRIMARY DRIVERS OF OVERRUN.
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026863300 | 2000 | EX | INVESTIGATE NSP - EASEMENTS | 2020-04-09 | 4 WEEHAWKEN LN | B | 16834 | 0 | -16834 | 100% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026865900 | 2000 | EX | LAND WORK FOR RELOCATION | 2020-09-14 | 960 GEORGETOWN RD TRACT 3 | A | 7669 | 0 | -7669 | 100% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026867701 | 555 | EX | INSTALL 2100' OF 2"PMMP MAIN | 2019-05-29 | 100 OAK RIDGE DR LT | B | 146669.7395 | 159412.42 | 12742.6805 | 9% | 2100 | 2197 | 72.5591
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026868001 | 555 | EX | INSTALL 1050' OF 2"PMMP MAIN | 2019-07-24 | 393 HARRODSWOOD RD | B | 94155.5888 | 101407.9 | 7252.3112 | 8% | 1075 | 1115 | 90.9488 | MISSED COMMIT DUE TO OUR START DATE AND CHANGED FROM GRASS STRIP TO STREET BORE .
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026868301 | 555 | EX | INSTALL 450' OF 2"PMMP MAIN | 2019-06-21 | 59 FOXLEY LN | B | 72806.603 | 55625.1 | -17181.503 | -24% | 450 | 463 | 120.1406
KY | KY - WEST | 2623 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026868500 | 560 | EX | RETIRE 648' - 2" PMMP | 2019-03-29 | US HWY 460B | B | 109.9437 | 0 | -109.9437 | 100% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026869500 | 555 | EX | INSTALL 265' OF 2"PMMP MAIN | 2019-06-03 | 208 IKEBANA DR LT27 | B | 16744.8667 | 17429.7 | 684.8333 | 4% | 285 | 327 | 53.3018
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026873300 | 555 | EX | INSTALL 4000' OF 2"PMMP MAIN | 2019-08-16 | 2004 ELMWOOD DR | B | 133806.5895 | 186876.14 | 53069.5505 | 40% | 4000 | 3786 | 49.3598 | TWALKER/KY 12-23-19: JOB OVER RUN DUE TO ADDITIONAL ROCK AND DIRECTIONAL BORE REQUIRED (ALSO INCREASED SEWER VIDEO) WHICH ADDED $40,000 TO CONTRACT COST. ALSO INCREASE COMPANY LABOR BY $4000 DUE TO LONGER JOB DURATION THAN PLANNED. FINALLY SEGA WAS $9000 HIGHER THAN ESTIMATED. TWALKER/KY 9-21-2020: LEVEL 2 VARIANCE FORM ADDED TO WMS.DOCS
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026874200 | 555 | EX | INSTALL 4600' OF 2"/4"/6"PMMP | 2021-05-06 | 1341 CINCINNATI RD | B | 193673.3471 | 148082.56 | -45590.7871 | -24% | 4600 | 4504 | 32.878 | TWALKER/KY 11-15-21: PROJECT UNDER RUN WAS DUE TO LESS ROCK ON SITE THAN PL ANNED AND NO STREET/HARD SURFACE REPAIRS REQUIRED THAT LOWER CONTRACT COST BY $25,000. LACK OF ROCK AND HARD SURFACE REPAIRS SPED UP CONSTRUCTION TIME AND LOWER COMPANY COST BY $XXXX AND SEGA WAS $4000 LOWER THAN ESTIMATE. COMPANY COST LOWER BY $3000 THAN ESTIMATE.
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026874700 | 555 | EX | INSTALL 700' OF 2"PMMP MAIN | 2019-08-05 | 121 ARROWHEAD CT | B | 30503.159 | 31948.16 | 1445.001 | 5% | 700 | 610 | 52.374
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026877300 | 561 | EX | INSTALL 20'-3" PMLP | 2019-08-15 | 105 BRIGHTON PARK BV | B | 7207.2587 | 4627.96 | -2579.2987 | -36% | 23 | 60 | 77.1327 | INSTALLED 60' OF 2" P MAIN, TIED INTO EXISTING MAIN 372' OF 3" P MAIN W/ 2 SL ATTACHED, SHUT OFF MVS, TEST ENTIRE MAIN AS NEW THROUGH HV TEE 90PSI 1HR OK, ST TEE CAP AT OP OK, PURGED MAIN, BHB CGI NGF, CFD DWHITACKER RLA TIED ONTO AND TIED INTO 3" ORANGE PLASTIC MAIN INSTALLED 60' OF 2" P MAIN, TIED INTO EXISTING MAIN 372' OF 3" P MAIN W/ 2 SL ATTACHED, SHUT OFF MVS, TEST ENTIRE MAIN AS NEW THROUGH HV TEE 90PSI 1HR OK, ST TEE CAP AT OP OK, PURGED MAIN, BHB CGI NGF, CFD,DWHIT RLA
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026877400 | 562 | EX | RETIRE 20'-3" PLP | 2019-08-15 | 105 BRIGHTON PARK BV | B | 72.7501 | 8813.2 | 8740.4499 | 12,014% |  |  | 0
KY | KY - WEST | 2623 | U131983 |  |  |  | 19026877900 | 2000 | EX | INVESIGATE TIGER PROJECT | 2021-07-28 | 100 2ND ST |  | 4480 | 0 | -4480 | 100% |  |  | 0 | PS&I EXECUTED AFTER FINAL REVISION WERE MADE. D.LEMONS 7/28/2021
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026878500 | 555 | EX | INSTALL 1500' OF 4"PHHP MAIN | 2019-08-29 | 100 BRADLEY ST | B | 99430.7331 | 103609.21 | 4178.4769 | 4% | 1500 | 1634 | 63.4083
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026881000 | 557 | EX | INSTALL 28' OF 12"CSHP MAIN | 2019-08-01 | BONITA RD FG 29 | B | 54774.4112 | 94423.9 | 39649.4888 | 72% |  | 95 | 993.9358 | TWALKER/KY 08-01-19: TRIED TO REVISE PROJECT DUE TO ADDITIONAL 70' OF MAIN REQUIRED TO REPAIR LEAK BUT WMS WOULD NOT ALLOW ME TO REVISE DUE TO UNPAID INVOICE. REVIEWED PROJECT WILL JSMITH COORDINATOR. JOB COST OVER RUN EXPECTED DUE TO ADDITIONAL FOOTAGE. TWALKER/KY 9-21-2020: COST OVER RUN DUE TO ADDITIONAL 60' OF MAIN LINE REQUIRED, EXISTING MAIN LINE HP MAIN IS COUPLED, PROJECT REQUIRED 4 MAIN CREW AND WELDER, INCREASED CONTRACT COST BY $32,000 AND SEGA INCREASED BY $6000.
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026881100 | 558 | EX | RETIRE 20' OF 12"MJBSHP MAIN | 2019-08-01 | BONITA RD FG 29 | B | 68.154 | 217.75 | 149.596 | 219% |  |  | 0
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026881400 | 558 | EX | RETIRE 30'-4" BSLP | 2019-06-21 | 200 CAPITAL HEIGHTS DR | B | 2935.6187 | 22112.62 | 19177.0013 | 653% |  |  | 0 | PIPE TO SOIL READING# -0.341 - BLONE - 06/21/19 FOUND LEAKS DUE TO CORROSION - WENT BY TIE-IN PLAN WITH ENGINEER - INSTALL 4" END CAP TO ABANDON 30' OF 4" LP GAS MAIN - ST ALL FITTING & TIE-IN/CAP @ OP - PURGED LINES - INSTALLED 9# ANODE - CGI BANKS OK - INT/EXT INS OK --->
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026882501 | 555 | EX | INSTALL 2500' OF 2"PMMP MAIN | 2019-09-25 | 100 RICHWOOD CR | B | 161456.0751 | 152956.98 | -8499.0951 | -5% | 2550 | 2474 | 61.8258
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026885901 | 555 | EX | INSTALL 400' OF 2"PMMP MAIN | 2020-02-17 | 1505 PARIS PK | B | 43080.7988 | 36432.55 | -6648.2488 | -15% | 400 | 612 | 59.5303
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026886000 | 555 | EX | INSTALL 440' OF 4"PMMP MAIN | 2019-10-29 | 270 ETTER LN | B | 47785.9525 | 40198.78 | -7587.1725 | -16% | 440 | 427 | 94.1423 | INSTALL 427' OF MAIN EXTENSION
KY | KY - WEST | 2623 | U131982 |  |  |  | 19026886800 | 555 | EX | INSTALL 30' 2" PMMP | 2019-08-03 | 191 KENDALL DR LT88C | B | 11471.3026 | 9422.71 | -2048.5926 | -18% | 30 | 58 | 162.4605
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026890900 | 559 | EX | INSTALL 4" POLY VALVE | 2019-08-27 | HUNTERTOWN RD | A | 4599.6049 | 634.89 | -3964.7149 | -86% | 4 | 4 | 158.7225
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026891000 | 560 | EX | RETIRE 4"PV | 2019-08-27 | HUNTERTOWN RD | A | 56.2512 | 0 | -56.2512 | 100% |  |  | 0
KY | KY - WEST | 2623 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026891800 | 557 | EX | INSTALL 1' - 3" PMMP | 2019-08-20 | SPRUCE DR | B | 24821.333 | 24141.14 | -680.193 | -3% | 0 | 30 | 804.7047 | INSTALLED 30' OF 3" PLASTIC, TEST ONSITE 90PSI 1HR OK, TEST 5-3X1 TEES 90PSI 1HR OK, ST 2- EF COUPLINGS AND ALL DE CAPS AND TEE CAPS AT OP OK, BHB CGI NGF, LEAK CLEARED, CDESPAIN BSEXTON RLA INSTALLED 30' OF 3" PLASTIC, TEST ONSITE 90PSI 1HR OK, TEST 4-3X1 TEES 90PSI 1HR OK, ST 2- EF COUPLINGS AND ALL DE CAPS AND TEE CAPS AT OP OK, BHB CGI NGF, LEAK CLEARED, CDESPAIN BSEXTON RLA INSTALLED 30' OF 3" PLASTIC, TEST ONSITE 90PSI 1HR OK, TEST 5-3X1 TEES 90PSI 1HR OK, ST 2- EF COUPLINGS AND ALL DE CAPS AND TEE CAPS AT OP OK, BHB CGI NGF, LEAK CLEARED, DOUBLE SQUEEZE OFF MAIN, 2 WAY FEED, INSTALLED GAUGES ALLOWED 30MIN WAIT TIME AFTER SQUEEZE OFF AND AFTER SQUEEZE OFFS REMOVED, CDESPAIN BSEXTON RLA
KY | KY - WEST | 2623 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026891900 | 558 | EX | RETIRE 1' - 3" PMMP | 2019-08-20 | SPRUCE DR | A | 364.869 | 0 | -364.869 | 100% |  |  | 0
KY | KY - WEST | 2623 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026892000 | 557 | EX | INSTALL 1' - 2" PMMP | 2019-08-21 | CASTLE ACRE | A | 5823.0355 | 5470.4 | -352.6355 | -6% | 1 | 1 | 5470.4
KY | KY - WEST | 2623 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026892100 | 558 | EX | RETIRE 1' - 2" PMMP | 2019-08-21 | CASTLE ACRE | A | 445.869 | 0 | -445.869 | 100% |  |  | 0
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026892800 | 557 | EX | INSTALL 1' 2" PMLP | 2019-08-23 | 134 E STEPHENS ST | A | 4989.5667 | 1739.79 | -3249.7767 | -65% | 1 | 1 | 1739.79
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026892900 | 558 | EX | RETIRE 1' 2" PLP | 2019-08-23 | 134 E STEPHENS ST | A | 71.2512 | 0 | -71.2512 | 100% |  |  | 0
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026894900 | 555 | EX | INSTALL 100' 2" PMMP | 2019-10-22 | 7029 ARBOR MEADOW WY | B | 13228.3613 | 15155.82 | 1927.4587 | 15% | 100 | 120 | 126.2985
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026895900 | 557 | EX | REPLACE MAIN - LEAKAGE | 2019-09-11 | CLUBHOUSE | A | 3261.701 | 2657.76 | -603.941 | -19% | 4 | 4 | 664.44
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026896000 | 558 | EX | RETIRE MAIN - LEAKAGE | 2019-09-11 | CLUBHOUSE | A | 56.2512 | 0 | -56.2512 | 100% |  |  | 0
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026898200 | 557 | EX | INSTALL 300'-8" CSHP | 2020-08-12 | COUNTRY LN VERSALLES R | B | 160063.0632 | 217177.53 | 57114.4668 | 36% | 300 | 232 | 936.11 | OVERRUN EXPLNATION: PROJECT OVERRAN BECAUSE NON DESTRUCTIVE TESTING WAS NOT ESTIMATED. ADDITIONALLY, 40 HOURS OF SEWER LOCATE SERVICES WERE REQUIRED BUT NOT ESTIM ATED.
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026898300 | 558 | EX | RETIRE 300'-8"CSHP | 2020-08-11 | COUNTRY LN VERSALLES R | B | 148.8044 | 331.62 | 182.8156 | 123% |  |  | 0
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026898400 | 2000 | EX | INVESTIGATE EASEMENTS/ROW | 2020-06-26 | VERSAILLES RD | B | 2736 | 0 | -2736 | 100% |  |  | 0
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026899100 | 2000 | EX | INVESIGATE POSSIBLE ENCROACH | 2021-11-18 | HOPE DR |  | 10000 | 0 | -10000 | 100% |  |  | 0
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026899200 | 559 | EX | INSTALL 20'- 2" PMMP | 2019-09-26 | 203 HUNTER CT | A | 8977.3613 | 387.15 | -8590.2113 | -96% | 20 | 20 | 19.3575 | 19-7450990-00 REPLACED SL, TEST NEW MAIN TO MTR VLV 90PSI 5MIN OK, ST TEE CAP AT OP OK, 2" ORANGE PLASTIC MAIN, BHB CGI NGF, WORKED WITH MAIN REPLACEMENT JOB, LEAK CLEARED, CDESPAIN 9-25-19
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026899300 | 560 | EX | RETIRE 20'-2" PMMP | 2019-09-26 | 203 HUNTER CT | A | 54.3067 | 0.65 | -53.6567 | -99% |  |  | 0 | 19-7450990-00 REPLACED SL, TEST NEW MAIN TO MTR VLV 90PSI 5MIN OK, ST TEE CAP AT OP OK, 2" ORANGE PLASTIC MAIN, BHB CGI NGF, WORKED WITH MAIN REPLACEMENT JOB, LEAK CLEARED, CDESPAIN 9-25-19
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026900200 | 557 | EX | INSTALL 2775' 2"PMMP | 2020-08-14 | CLEMENTS | B | 550649.658 | 537713.18 | -12936.478 | -2% | 2775 | 3154 | 170.4861 | UNDERRUN EXPLANATIONS: THE UNDERRUN IS DUE TO PAVING THAT HAS NOT BEEN PERF ORMED YET. THERE ARE TWO FAR JOBS STILL IN PENDING THAT WILL CLOSE THE GAP.
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026900300 | 558 | EX | RETIRE 3100 4" BSLP | 2020-11-20 | CLEMENTS | B | 148.8044 | 393.82 | 245.0156 | 165% |  |  | 0
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026901700 | 2000 | EX | INVESTIGATE EASEMENT | 2019-12-11 | 5325 OLD FRANKFORT PK HOUSE | B | 2183 | 0 | -2183 | 100% |  |  | 0
KY | KY - WEST | 2623 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 19026902600 | 909 | EX | INSTALL ELECTRONIC EQUIP | 2019-12-31 | US 460 - GEORGETOWN RD | F | 6519.6923 | 4807.02 | -1712.6723 | -26% |  |  | 0 | BATTERY UPGRADE WORKED BY ACP AND NOLL DAVIS
KY | KY - WEST | 2623 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 19026902700 | 910 | EX | RETIRE ELECTRONIC EQUIP | 2019-12-31 | US 460 - GEORGETOWN RD | F | 76.3408 | 0 | -76.3408 | 100% |  |  | 0
KY | KY - WEST | 2623 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 19026902800 | 909 | EX | INSTALL ELECTRONIC EQUIP | 2019-12-31 | DELAPLANE RD | F | 6741.6923 | 4807.02 | -1934.6723 | -29% |  |  | 0
KY | KY - WEST | 2623 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 19026903500 | 587 | EX | INSTALL ELECTRONIC EQUIP | 2019-12-30 | 900 TYRONE PK FF | F | 6741.6923 | 5663.17 | -1078.5223 | -16% |  |  | 0 | EQUIPMENT REPLACED BY NOLL DAVIS AND ACP
KY | KY - WEST | 2623 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 19026903600 | 588 | EX | RETIRE ELECTRONIC EQUIP | 2019-12-30 | 900 TYRONE PK FF | F | 76.3408 | 0 | -76.3408 | 100% |  |  | 0 | EQUIPMENT REPLACED BY ACP AND NOLL DAVIS
KY | KY - WEST | 2623 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 19026905700 | 587 | EX | INSTALL ERX | 2019-11-21 | 100 SOWER | F | 4096.5878 | 905.65 | -3190.9378 | -78% |  |  | 0 | REPLACED EFC
KY | KY - WEST | 2623 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 19026905800 | 588 | EX | RETIRE EFC | 2019-11-21 | 100 SOWER | F | 58.2651 | 0 | -58.2651 | 100% |  |  | 0 | REPLACED EFC
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026905900 | 557 | EX | INSTALL 35' OF 2"/4"PMMP MAIN | 2020-03-16 | 1999 LEESTOWN RD | B | 24704.1056 | 62018.23 | 37314.1244 | 151% | 37 | 50 | 1240.3646 | OVERRUN EXPLANTION: PROJECT WAS ESTIMATED FOR A 3 MAN CREW FOR 40 HOURS WHE N A 4 MAN CREW FOR 69 HOURS WAS REQUIRED. COMPANY LABOR ALSO OVERRAN BOTH L EADING TO THE OVERRUN. TWALKER/KY 09-21-2020: COST OVER DUE TO PROJECT PLANNED FOR 3 MAIN CREW BUT PAIDFOR 4 MAIN CREW PLUS ADDITION WORK REQUIRED INCREASED CONTRACT COST BY $20,000 SEGA WAS INCREASED BY $3000
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026906000 | 558 | EX | RETIRE 150' OF 4"CSMP MAIN | 2020-03-16 | 1999 LEESTOWN RD | B | 79.38 | 3295.4 | 3216.02 | 4,051% |  |  | 0
KY | KY - WEST | 2623 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 19026907400 | 587 | EX | REPLACE EFC WITH EC350 | 2019-12-23 | 102 KUHLMAN BV | F | 3366.2939 | 4712.62 | 1346.3261 | 40% |  |  | 0
KY | KY - WEST | 2623 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 19026907500 | 588 | EX | REPLACE EFC WITH EC350 | 2019-12-23 | 102 KUHLMAN BV | F | 58.2651 | 0 | -58.2651 | 100% |  |  | 0
KY | KY - WEST | 2623 | BKSLONE |  |  |  | 19026908201 | 561 | EX | INSTALL 54'-4" PMMP | 2020-08-12 | KY 32/LONG LICK PK | B | 73887.2898 | 67959.55 | -5927.7398 | -8% | 136 | 57 | 1192.2728
KY | KY - WEST | 2623 | BKSLONE |  |  |  | 19026908300 | 562 | EX | RETIRE 46'-4" PMP | 2020-08-12 | KY 32/LONG LICK PK | B | 89.545 | 51.39 | -38.155 | -43% |  |  | 0
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 20026916900 | 555 | EX | INSTALL 2960' 2" PMMP | 2020-11-11 | JOHNSTONE TL LT 15 | B | 72637.757 | 75147.78 | 2510.023 | 3% | 6 | 2792 | 26.9154
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 20026921800 | 555 | EX | INSTALL 1050'4" PMMP | 2020-09-17 | 220 ENDEAVOR DR LT | B | 33901.1755 | 39770.15 | 5868.9745 | 17% | 1050 | 1152 | 34.5227
KY | KY - WEST | 2623 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 20026923500 | 2000 | EX | ILI FEASIBILITY STUDY | 2021-04-29 | DELEPLANE RD | A | 60000 | 0 | -60000 | 100% |  |  | 0 | CCC # 18077 CMCHOLAN 4-6-2021 18498
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 20026926800 | 586 | EX | DEMO BUILDING | 2020-09-09 | LAFAYETTE DR | F | 6685.9494 | 2592.53 | -4093.4194 | -61% |  |  | 0 | WAITING ON ENVIRONMENTAL AND CONTRACTOR AVAILABILITY ALSO DELAYED DUE TO COVID
KY | KY - WEST | 2623 | U131983 |  |  |  | 20026929000 | 587 | EX | UPGRADE ELECTRONICS | 2020-04-28 | 596 TRIPORT RD | F | 3038 | 7127.42 | 4089.42 | 135% |  |  | 0 | REPLACE 2G/3G MODEM WITH RV50 4G/5G MODEM EQUPIMENT INSTALLED BY ACP
KY | KY - WEST | 2623 | U131983 |  |  |  | 20026929200 | 587 | EX | UPGRADE ELECTRONICS | 2020-04-27 | 616 INDUSTRIAL PK | F | 3038 | 3657.08 | 619.08 | 20% |  |  | 0 | UPGRADED CELL MODEM TO RV50 4G/5G EQUPIMENT INSTALLED BY ACP
KY | KY - WEST | 2623 | U131983 |  |  |  | 20026929300 | 587 | EX | UPGRADE ELECTRONICS | 2021-04-16 | 2011 HOOVER BV | F | 3038 | 6355.62 | 3317.62 | 109% |  |  | 0 | REPLACED EFC
KY | KY - WEST | 2623 | U131983 |  |  |  | 20026929400 | 587 | EX | UPGRADE ELECTRONICS | 2021-11-02 | 100 CLINTON ST | F | 3038 | 293.46 | -2744.54 | -90% |  |  | 0 | REPLACED EFC
KY | KY - WEST | 2623 | U131983 |  |  |  | 20026929500 | 587 | EX | UPGRADE ELECTRONICS | 2022-07-11 | US60 BP | F | 3038 | 5670.86 | 2632.86 | 87% |  |  | 0 | RETIRED OLD MINNI-AT INSTALLED NEW EC350 BLONE 07-11-2022
KY | KY - WEST | 2623 | U131983 |  |  |  | 20026929600 | 587 | EX | UPGRADE ELECTRONICS | 2021-04-16 | 982 CHENAULT RD | F | 3038 | 3403.36 | 365.36 | 12% |  |  | 0 | REPLACED EFC
KY | KY - WEST | 2623 | U131983 |  |  |  | 20026929700 | 587 | EX | UPGRADE ELECTRONICS | 2021-11-08 | 980 CHENAULT RD | F | 3038 | 3985.53 | 947.53 | 31% |  |  | 0 | REPLACED EFC
KY | KY - WEST | 2623 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 20026932800 | 585 | EX | INSTALL FENCE | 2020-09-09 | LAFAYETTE DR | F | 4126.5897 | -1114.6 | -5241.1897 | -127% |  |  | 0
KY | KY - WEST | 2623 | U131983 |  |  |  | 20026935000 | 588 | EX | RETIRE ELECTRONICS | 2021-04-16 | 2011 HOOVER BV | F | 73.3494 | 0 | -73.3494 | 100% |  |  | 0 | REPLACE EFC JOB ON HOLD 2020 BECAUSE OF COVID 19
KY | KY - WEST | 2623 | U131983 |  |  |  | 20026935100 | 588 | EX | RETIRE ELECTRONICS | 2021-11-02 | 100 CLINTON ST | F | 73.3494 | 0 | -73.3494 | 100% |  |  | 0 | REPLACED EFC
KY | KY - WEST | 2623 | U131983 |  |  |  | 20026935200 | 588 | EX | RETIRE ELECTRONICS | 2022-07-11 | US60 BP | F | 73.3494 | 742.7 | 669.3506 | 913% |  |  | 0 | RETIRED OLD MINI-AT INSTALLED NEW EC350 BLONE 07-11-2022
KY | KY - WEST | 2623 | U131983 |  |  |  | 20026935400 | 588 | EX | RETIRE ELECTRONICS | 2021-11-08 | 980 CHENAULT RD | F | 73.3494 | 0 | -73.3494 | 100% |  |  | 0 | REPLACED EFC
KY | KY - WEST | 2623 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 20026935800 | 587 | EX | UPGRADE ELECTRONICS | 2020-04-27 | 299 KINGS DAUGHTER DR | F | 3205 | 3570.85 | 365.85 | 11% |  |  | 0 | UPGRADED CELL MODEM TO RV50 4G/5G EQUPIMENT INSTALLED BY ACP
KY | KY - WEST | 2623 | BKSLONE |  |  |  | 20026939300 | 2000 | EX | ASSESS CONFLICT W/STORM SEWERS | 2020-04-21 | MADDOX ST |  | 14086.9783 | 0 | -14086.9783 | 100% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026939600 | 562 | EX | RETIRE 680' OF 2"PMP MAIN | 2020-04-03 | 100 PINNACLE CT | B | 7303.987 | 7423.15 | 119.163 | 2% |  |  | 0
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 20026940300 | 559 | EX | INSTALL 10' PMIP | 2020-03-27 | 1110 STROURBRIDGE RD | A | 4738.9093 | 4445 | -293.9093 | -6% | 10 |  | 0 | ELECTROFUSE COUPLINGS WITH DEAD END CAPS FOR 5MINS @ OP, SOAP TESTED ALL END CAPS AT VERIFICATION TEES AND PURGE TEES FOR 5MINS @ OP, 3-30-2020 OM ELECTROFUSE COUPLINGS WITH DEAD END CAPS FOR 5MINS @ OP, SOAP TESTED ALL END CAPS AT VERIFICATION TEES AND PURGE TEES FOR 5MINS @ OP, 3-30-2020 OM INSTALLED 7' 10" OF 2" PLASTIC PIPE INCLUDING 2 90'S & 2 HV TEES, TESTED 2" PLASTIC PIPE INCLUDING 2 90'S & 2 HV TEES @ 90 PSI FOR 1HR, TESTED ALL VERIFICATION TEES & PURGE TEES @ 90 PSI FOR 1HR , SOAP TESTED BOTH
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 20026940400 | 560 | EX | RETIRE 10' PMIP | 2020-03-27 | 1110 STROURBRIDGE ST | A | 116.4359 | 116.54 | 0.10406 | 0% |  |  | 0 | ELECTROFUSE COUPLINGS WITH DEAD END CAPS FOR 5MINS @ OP, SOAP TESTED ALL END CAPS AT VERIFICATION TEES AND PURGE TEES FOR 5MINS @ OP, ABANDON ED 2' OF 2" MP PLASTIC GM, 3-27-2020 OM INSTALLED 7' 10" OF 2" PLASTIC PIPE INCLUDING 2 90'S & 2 HV TEES, TESTED 2" PLASTIC PIPE INCLUDING 2 90'S & 2 HV TEES @ 90 PSI FOR 1HR, TESTED ALL VERIFICATION TEES & PURGE TEES @ 90 PSI FOR 1HR , SOAP TESTED BOTH
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026942000 | 909 | EX | INSTALL I&C EQUIPMENT | 2021-07-09 | COMANCHE TR | F | 16155.4774 | 14182.01 | -1973.4674 | -12% |  |  | 0 | CCC# 30920 CCC TICKET NOT REQUIRED ON 9/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026943100 | 909 | EX | INSTALL I&C EQUIPMENT | 2022-02-25 | 202 BERRY AV | F | 16155.4774 | 14038.9 | -2116.5774 | -13% |  |  | 0 | CCC# 43654 INSTALLED ERX RETIRED PAPER CHART BLONE 2-25-2022
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026943200 | 584 | EX | RETIRE GAUGE | 2022-02-25 | 202 BERRY AV | F | 91.4991 | 259.73 | 168.2309 | 184% |  |  | 0 | INSTALLED NEW LEGACY ERX RETIRED PAPER CHART BLONE 2-25-2022
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 20026944100 | 557 | EX | INSTALL 1150'-2" PMMP | 2020-10-13 | HILLCREST | B | 197605.192 | 180126.1 | -17479.092 | -9% | 1150 | 1177 | 153.0383
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 20026944200 | 558 | EX | RETIRE 1134'-3"/4" BSLP | 2020-10-13 | HILLCREST | B | 104.5555 | 776.22 | 671.6645 | 642% |  |  | 0
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026945400 | 562 | EX | RETIRE 1431'-2"-4" BSLP | 2021-06-10 | 2ND ST | B | 94.7274 | 1066.35 | 971.6226 | 1,026% |  |  | 0 | ABANDONMENTS OF MAINLINE WERE DONE WITH JO# 20-0269755-00.
KY | KY - WEST | 2623 | BKSLONE |  |  |  | 20026945500 | 561 | EX | INSTALL 535'-4"PMLP | 2020-06-03 | MADDOX ST | B | 99653.3864 | 74906.33 | -24747.0564 | -25% | 537 | 499 | 150.1129
KY | KY - WEST | 2623 | BKSLONE |  |  |  | 20026945600 | 562 | EX | RETIRE 511'- 3"/4" BS/CS/PMSLP | 2020-06-16 | MADDOX ST | B | 90.6119 | 72.24 | -18.3719 | -20% |  |  | 0
KY | KY - WEST | 2623 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 20026948200 | 575 | EX | LAND AGREEMENT LR114666 | 2019-12-31 |  | F | 0 | 0 | 0 | 0% |  |  | 0
KY | KY - WEST | 2623 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 20026952900 | 585 | EX | REPLACE ROOF | 2023-02-28 | 298 MYRTLE AV | F | 4729 | 12246.18 | 7517.18 | 159% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026953701 | 557 | EX | INSTALL 6100' OF 2"/4"PMMP | 2021-05-12 | WALLACE AV | B | 1430757.5003 | 1646234.22 | 215476.7197 | 15% | 6260 | 6099 | 269.9187 | TWALKER/KY 05-04-22: JOB OVER RUN DUE TO $65,000 SPEND ON OFF DUTY POLICE DUE TO HIGH CRIME/TRAFFIC AREA, STATE REQUIRED MILL/PAVING OF HOLME ST INCREASED CONTRACT COST BY $85,000. SEGA INCREASED BY $51,000 OVER EST.
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 20026953800 | 558 | EX | RETIRE 8800' OF 4"/6"BSLP MAIN | 2021-10-22 | WALLACE | B | 240.2222 | 0 | -240.2222 | 100% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026954400 | 555 | EX | INSTALL 12,500' OF 6"PMMP | 2021-11-24 | 1171 MIDWAY RD | B | 584465.9269 | 671261.21 | 86795.2831 | 15% | 12500 | 12516 | 53.6322 | GAS WAS ONLINE BEFORE COMMIT DATE. HAD TO FINISH UP RESTORATION AND PROJEC T INFO. STEVE CANOY 12/17/2021
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026954500 | 555 | EX | INSTALL 72' OF 4"CSHP MAIN | 2021-05-06 | 1341 CINCINNATI RD | B | 48741.5249 | 50107.73 | 1366.2051 | 3% | 70 | 60 | 835.1288
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026954800 | 575 | EX | LAND FOR REG STATION SITE | 2021-01-25 | 1341 CINCINNATI PK | F | 31714 | 31181.26 | -532.74 | -2% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026954900 | 573 | EX | INSTALL SKID REG STATION #1574 | 2022-02-16 | 1341 CINCINNATI PK | F | 91083.0917 | 83537.33 | -7545.7617 | -8% |  |  | 0 | TUBE UP ONE RUN CCC #22458 CCC# 22583 CC# 23111 G.HALE 05-12-21 PLACED RUN 1 IN SERVICE ON 5/6/21 WITH TEMPORARY REGULATORS INSTALLED TO MEET COMMIT DATE WITH BUILDER RUN 2 OFF AND BLIND FLANGED PERMANENT EQUIPMENT ORDER WITH TENTATIVE DELIVERY DATE OF JUNE/JULY 2021 JOB CANNOT BE COMPLETED OR CLOSED OUT UNTIL PERMANENT EQUIPMENT IS INSTALLED CFARIS CCC# 43393 CCC# CALLED IN BY AL PARKS OR CONNER WIMPE CCC#55276 CWEMPE 2/15/22 GCCC# 56179 INSTALLED PERMANENT SLAMSHUT MOONEY'S COMMISSIONED STATION CWEMPE 2-16-22
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 20026958600 | 557 | EX | INSTAL 5'2" PMMP | 2020-06-29 | 874 KENTUCKY AV | B | 3022.0586 | 23861.05 | 20838.9914 | 690% | 5 | 17 | 1403.5912
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 20026958700 | 558 | EX | RETIRE 5'-2" PMP | 2020-06-29 | 874 KENTUCKY AV | B | 99.2651 | 860.93 | 761.6649 | 767% |  |  | 0 | REPLACED 13' - 2" PL MAIN, INSTALLED HARD BYPASS TESTED ONSITE 90PSI 1HR OK, ST 2- HVTT AT OP OK, ST ALL TEES AND TEE CAPS AT OP OK, BHB CGI NGF, LEAK CLEARED, CDESPAIN
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026960600 | 909 | EX | INSTALL NEW TRANSMITTERS | 2022-08-22 | US 460 - GEORGETOWN RD | F | 5450.0793 | 9652.42 | 4202.3407 | 77% |  |  | 0 | INSTALLED NEW INLET AND OUTLET ROSEMONT 4088B TRANSMITTERS GHALE 8-22-2022
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026960700 | 910 | EX | RETIRE DAMAGE TRANSMITTER | 2022-08-22 | US 460 - GEORGETOWN RD | F | 80.9227 | 542.77 | 461.8473 | 571% |  |  | 0 | INSTALLED NEW INLET AND OUTLET TRANSMITTERS GHALE 8-22-2022
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026963800 | 2000 | EX | OBTAIN AND RECORD EASEMENT | 2021-12-16 | CHERRY BLOSSUM WY | A | 2215 | 0 | -2215 | 100% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026964400 | 557 | EX | INSTALL 5' OF 4"PMMP MAIN | 2020-08-04 | US HWY 127 | B | 4046.0767 | 9852.15 | 5806.0733 | 143% | 5 | 6 | 1642.025 | REPLACED 6' - 4" P-MP MAIN, 4 BOLT COUP PL TO PL LEAKING, TEST NEW MAIN ONSITE 90PSI 1 HR OK, ST 2- 4" EF COUP AT OP OK, ST ALL TEES AND TEE CAPS AT OP OK, BHB CGI NGF, LEAK CLEARED, CDESPAIN 8-4-20
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026964500 | 558 | EX | RETIRE 5' OF 4"PMP MAIN | 2020-08-04 | US HWY 127 | A | 79.5082 | 0 | -79.5082 | 100% |  |  | 0
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 20026966500 | 557 | EX | REPLACE MAIN - LEAKAGE | 2020-08-12 | 406 POCAHONTAS | B | 7662.8219 | 8918.57 | 1255.7481 | 16% | 6 | 3 | 2972.8567 | REPLACED 3' - 4" P- MP MAIN, TEST MAIN ONSITE 90PSI 1 HOUR OK, ST 2 - EF COUP AT OP OK, ST ALL TEE CAPS AND END CAPS AT OP OK, BHB CGI NGF LEAK CLEARED, CDESPAIN 8-12-20
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 20026966600 | 558 | EX | RETIRE MAIN - LEAKAGE | 2020-08-12 | 406 POCAHONTAS | B | 97.6018 | 123.47 | 25.8682 | 27% |  |  | 0 | REPLACED 3' - 4" P- MP MAIN, TEST MAIN ONSITE 90PSI 1 HOUR OK, ST 2 - EF COUP AT OP OK, ST ALL TEE CAPS AND END CAPS AT OP OK, BHB CGI NGF LEAK CLEARED, CDESPAIN 8-12-20
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026967000 | 575 | EX | AQUIRE EASEMENT | 2021-12-16 | CHERRY BLOSSUM WY | F | 2271 | 2841.99 | 570.99 | 25% |  |  | 0
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 20026967700 | 557 | EX | REPLACE MAIN - LEAKAGE | 2020-08-18 | 407 AZTEC TL | A | 7808.2374 | 721.17 | -7087.0674 | -91% | 6 | 7 | 103.0243
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 20026967800 | 558 | EX | RETIRE MAIN - LEAKAGE | 2020-08-18 | 407 AZTEC TL | B | 104.7548 | 7669.4 | 7564.6452 | 7,221% |  |  | 0 | REPLACED 7' - 3" P- IP MAIN, TEST NEW MAIN ONSITE 90PSI 1HR OK, ST 2- 3" EF COUP AT OP OK, ST ALL TEE CAPS AND DE CAPS ON TEES AT OP OK, BHB CGI NGF, LEAK CLEARED, CDESPAIN 8-18-20
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026968200 | 2000 | EX | CONFLICT ASSESSMENT | 2020-09-16 | GRANITE RIDGE RD | B | 5230 | 0 | -5230 | 100% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026968401 | 558 | EX | RETIRE 10' OF 3"BSLP MAIN | 2020-08-21 | HIGH ST | B | 50161.2836 | 45080.62 | -5080.6636 | -10% |  |  | 0 | ABANDONED 91' OF 3" BS LP MAIN, ST DE CAPS ON MAIN AT OP OK, BHB CGI NGF, BLEW OUT ANS SEALED ABANDONED MAIN, LEAK CLEARED, CDESPAIN 8-20-20
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026969500 | 561 | EX | INSTALL 680' OF 4"PMMP MAIN | 2020-12-14 | GRANITE RIDGE RD | B | 52475.5703 | 53143.47 | 667.8997 | 1% | 680 | 610 | 87.1204
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026969600 | 562 | EX | RETIRE 680' OF 4"PMMP MAIN | 2020-12-14 | GRANITE RIDGE RD | B | 78.9269 | 0 | -78.9269 | 100% |  |  | 0
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 20026974601 | 557 | EX | INSTALL 6,500'-4"PMLP | 2023-10-13 | ANN ST | B | 2219393.0276 | 2600268.43 | 380875.4024 | 17% | 6860 | 6647 | 391.1943
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 20026974700 | 558 | EX | RETIRE 6,900'-BSLP,CSLP,PLP | 2023-12-18 | ANN | B | 66.2135 | 220 | 153.7865 | 232% |  |  | 0
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026975400 | 561 | EX | INSTALL 2250'-2" PMMP | 2021-09-08 | W 2ND ST | B | 623618.1819 | 859560.09 | 235941.9081 | 38% | 2250 | 2396 | 358.748 | PROJECT COMPLETED ON 11-16-2021 D.LEMONS 3/2/2022: PROJECT OVERRUN WAS DUE TO ADDITIONAL TIME REQUIRED TO C OMPLETE PROJECT DUE TO MULTIPLE CONTRACTORS IN AREA DURING PROJECT. ESTIMA TED FOR 645 MAN HOURS, BUT REQUIRED 1018 MAN HOURS. ADDITIONAL $85K IN CONT RACT EXPENSES, $36K IN LABOR COSTS WHICH LEAD TO INCREASE OF $32K IN SEGA. THERE WAS A SLIGHT REDUCTION IN OTHER COST TO ACCOUNT FOR THE $147K OVERRUN .
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026975500 | 562 | EX | RETIRE 3515'-2",3",4"& 6" | 2021-11-16 | W 2ND ST | B | 107.2796 | 142.7 | 35.4204 | 33% |  |  | 0 | PROJECT COMPLETE ON 11162021
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026978900 | 588 | EX | RETIRE GMB SETTING | 2021-04-20 | 113 GREAT BUFFALO TC | F | 83.3805 | 0 | -83.3805 | 100% |  |  | 0 | JOB WAS ON HOLD UNTIL 2021 GCCC TICKET NOT REQUIRED ON 9/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026979000 | 566 | EX | RETIRE SERVICE | 2021-04-22 | 113 GREAT BUFFALO TC | B | 83.3805 | 2450.84 | 2367.4595 | 2,839% |  |  | 0 | THIS IS PAPER KILL ONLY
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026979100 | 566 | EX | RETIRE SERVICE | 2021-04-15 | 113 GREAT BUFFALO TC | B | 83.3805 | 0 | -83.3805 | 100% |  |  | 0
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026979201 | 565 | EX | INSTALL SERVICE TO GMB | 2021-04-15 | 113 GREAT BUFFALO TC | B | 135908.7766 | 201470.53 | 65561.7534 | 48% | 67 |  | 0 | LEVEL 2 BUDGET VARIANCE LOADED INTO WMSSDOCS. D.LEMONS 9/22/21
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026979300 | 560 | EX | RETIRE 12'-8" CSHP | 2021-04-29 |  | B | 134.3805 | 3655.53 | 3521.1495 | 2,620% |  |  | 0
KY | KY - WEST | 2623 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 20026979500 | 2000 | EX | ACQUIRE FLOOD MAPS | 2022-11-03 | FRANKFORT |  | 448 | 0 | -448 | 100% |  |  | 0
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 20026981500 | 2000 | EX | INVESTIGATE REPLACEMENT RIGHTS | 2021-07-12 | 7855 MCCRACKEN PK | B | 1641 | 0 | -1641 | 100% |  |  | 0
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 20026981900 | 555 | EX | INSTALL 170'-2" PMMP | 2020-12-21 | 7069 ARBOR MEADOW WY | B | 14695.1167 | 9665.87 | -5029.2467 | -34% | 170 | 99 | 97.6351 | OPEN CUT MAIN TO METER. VERIFIED CONTENT AND PRESSURE.
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 20026986200 | 559 | EX | INSTALL 5'-6" PMMP | 2020-11-11 | 272 E MAIN ST | A | 11648.0607 | 10583.94 | -1064.1207 | -9% | 5 | 16 | 661.4963
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 20026986300 | 560 | EX | INSTALL 5'-6" PMMP | 2020-11-11 | 272 E MAIN ST | A | 108.4977 | 0 | -108.4977 | 100% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026986900 | 557 | EX | EMER-INSTALL 5' OF 3"PMLP MAIN | 2020-11-12 | BOURBON ST | A | 7816.0607 | 4384.48 | -3431.5807 | -44% | 5 | 5 | 876.896
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026987000 | 558 | EX | EMER-RETIRE 5' OF 3"PMLP MAIN | 2020-11-12 | BOURBON ST | A | 108.4977 | 0 | -108.4977 | 100% |  |  | 0
KY | KY - WEST | 2623 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 20026987100 | 0001 | EX | INSTALL HEATER ACCESSORY | 2022-11-03 | DELAPLANE RD |  | 11868.661 | 0 | -11868.661 | 100% |  |  | 0
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 20026989800 | 555 | EX | INSTALL 800'-2" PMMP | 2021-04-28 | 1 AMICK WY LT82 | B | 25809.9211 | 33245.15 | 7435.2289 | 29% | 800 | 1118 | 29.7363
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 20026990800 | 558 | EX | RETIRE INLET PIPING R 1502 | 2021-10-22 | FRANKLIN AVE | B | 240.2222 | 0 | -240.2222 | 100% |  |  | 0
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 20026991300 | 555 | EX | INSTALL 350'-2" PMMP | 2021-03-02 | 141 ARROWHEAD CT | B | 31069.259 | 19273.52 | -11795.739 | -38% | 350 | 337 | 57.1915 | 337 FT 2 " MEDIUM PRESSURE MAIN INSTALLED BY STANLEY PIPELINE YELLOW MED IUM DENSITY.PIPE
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 20026991500 | 2000 | EX | INVESTIGATE RAILROAD CROSSING | 2023-03-27 | SENATE DR | B | 5472 | 0 | -5472 | 100% |  |  | 0 | HYDRO EXCAVATD MULTIPLE LOCATIONS FOR DEPTH ON HP
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026100500 | 2000 | EX | CONFLICT ASSESSMENT FOR RELO | 2021-08-11 | 101 BIZZACK BV | B | 2800 | 0 | -2800 | 100% |  |  | 0
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 21026101700 | 587 | EX | INSTALL NEW GMB SETTING | 2021-11-10 | 7855 MCCRACKEN PK | F | 57815.8896 | 40071.73 | -17744.1596 | -31% |  |  | 0 | INSTALLED NEW GMB SETTING
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 21026102400 | 588 | EX | RETIRE WOODFORD GMB | 2021-11-10 | 7855 MCCRACKEN PK | F | 84.0131 | 0 | -84.0131 | 100% |  |  | 0 | RETIRED OLD GMB SETTING AFTER NEW SETTING PLACED IN SERVICE
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026103000 | 577 | EX | INSTALL CHAIN LINK FENCE | 2022-02-16 | 1341 CINCINNATI PK | F | 16434.2505 | 20497.91 | 4063.6595 | 25% |  |  | 0 | RHAYES 08-24-2021 MONITORED FENCE INSTALLATION CCC 35764 CWEMPE PAPER WORK COMPLETION 2-16-22
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026106500 | 557 | EX | EMER - INSTALL 4' OF 2"PMMP | 2021-02-25 | 199 QUAIL HOLLOW DR | A | 7343.079 | 7429.12 | 86.041 | 1% | 5 | 4 | 1857.28
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026106600 | 558 | EX | EMER - RETIRE 4' OF 2"PMMP | 2021-02-25 | 199 QUAIL HOLLOW DR | A | 82.208 | 0 | -82.208 | 100% |  |  | 0
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 21026107100 | 909 | EX | INSTALL COMMUNICATIONS | 2021-10-12 | COMPTON DR | F | 1691.2937 | 3375.12 | 1683.8263 | 100% |  |  | 0 | CCC#41275 CCC#17228 INSTALLED SUPER SOLAR KIT AND BATTERY UPGRADED TO RV50 CELL MODEM CONVERTED TO FULL TIME MONITORING RTU TICKET NUMBER 4339
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026107200 | 566 | EX | RETIRE 33' OF 4"PMMP S/L | 2021-08-24 | 7855 MCCRACKEN PK MTRSTAT | B | 76.3208 | 1.8 | -74.5208 | -98% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026107300 | 565 | EX | INSTALL 140' OF 4"PMMP S/L | 2021-08-24 | 7855 MCCRACKEN PK MTRSTAT | B | 57302.0236 | 53188.18 | -4113.8436 | -7% | 140 |  | 0
KY | KY - WEST | 2623 | U124399 | Bishop,Steven | Gill,John | Dunn,David | 21026107400 | 0001 | EX | PM- TOYOTA ILI MATERIAL | 2021-06-02 |  |  | 0 | 0 | 0 | 0% |  |  | 0
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 21026107500 | 557 | EX | EMER- INSTALL120'-2" PL | 2021-03-04 | 11 WARWICK LN | B | 13083 | 2045.88 | -11037.12 | -84% | 120 | 155 | 13.1992 | INSTALLED 155' OF 2" P-MP MAIN DUE TO LEAK, SEE CAPITAL PACKET JO# 21-0261075-00, CDESPAIN 3-4-21
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 21026107600 | 558 | EX | RETIRE MAIN - LEAKAGE D304381 | 2021-03-04 | 11 WARWICK LN | B | 56.3197 | 14663.28 | 14606.9603 | 25,936% |  |  | 0 | REPLACED 155' OF 2" P- MP MAIN, FOUND 2BOLT COUPLING PL-PL CORRODED AND LEAKING, SQUEEZED OFF, REPLACED MAIN, SEE JO PACKET 21-0261075-00 CDESPAIN 3-4-21
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 21026109600 | 555 | EX | INSTALL 351'-2" PMMP | 2021-07-15 | 2051 ELMWOOD DR | B | 20339.7093 | 28594.76 | 8255.0507 | 41% | 351 | 397 | 72.0271
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026111902 | 555 | EX | INSTALL 7,500' OF 2"/6"PMMP | 2022-03-10 | 2212 CYNTHIANA RD | B | 670404.9715 | 671698.12 | 1293.1485 | 0% | 10080 | 11549 | 58.1607 | LOWES (#207438) - MATERIAL FOR ECP - $27.62 + 10% = $30.38 U461423 9/2 3/2021 SITE SUPPLY (#207438) - MULCH LOGS - #424.00 + 10% = 466.40 U461423 9/23/2021
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 21026113900 | 555 | EX | INSTALL 1300' OF 2"/4"PMMP | 2021-09-21 | FURLONG TC LT125 | B | 66451.1814 | 34584.47 | -31866.7114 | -48% | 1300 | 1130 | 30.6057 | MISSED COMMIT DATE DUE TO WEATHER UNDERRUN EXPLANATION: THE UNDERRUN VARIANCE IS DUE TO 50% ROCK EXCAVATION A ND 50% LESS DUST AND STONE. THE OVER HEAD EFFECT OF THESE REDUCTIONS ALSO PLAYED A FACTOR.
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026114000 | 558 | EX | EMER - RETIRE 145' OF 2"BSLP | 2021-04-07 | 228 W MAIN ST | A | 3325.023 | 1254.24 | -2070.783 | -62% |  |  | 0 | RETIRED 146' OF 2" BSLP MAIN, SOAP TEST BOLTED DEAD END CAP AT OP, OK. SOAP TEST SADDLES AND PAC CLAMPS AT OP OK. BHB NGF. INSTALLED 9# ANODE. MAIN READ# -0.643. MAIN INSP OK. WHIMES 04/07/2021
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 21026114200 | 555 | EX | INSTALL 100'-2" PMMP | 2022-07-28 | 854 HICKMAN HILL RD | B | 12690.4563 | 19306.24 | 6615.7837 | 52% | 100 | 45 | 429.0276
KY | KY - WEST | 2623 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 21026114300 | 588 | EX | RETIRE EFC | 2021-04-16 | 982 CHENAULT RD | F | 111.0751 | 0 | -111.0751 | 100% |  |  | 0
KY | KY - WEST | 2623 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 21026115500 | 557 | EX | INSTALL 9560' OF 2"PMMP | 2023-04-21 | TANGLEWOOD DR | B | 1674772.7999 | 1791950.44 | 117177.6401 | 7% | 9400 | 8771 | 204.304
KY | KY - WEST | 2623 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 21026115600 | 558 | EX | RETIRE 9,590' OF BSLP & OTHER | 2023-06-27 | TANGLEWOOD DR | B | 67.799 | 182.4 | 114.601 | 169% |  |  | 0
KY | KY - WEST | 2623 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 21026117600 | 584 | EX | RETIRE REG STATION 1522 | 2023-06-22 | TANGLEWOOD DR | F | 3579.3015 | 0 | -3579.3015 | 100% |  |  | 0
KY | KY - WEST | 2623 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 21026117700 | 2000 | EX | RESEARCH ROAD ROW | 2021-12-23 | TANGLEWOOD DR | B | 10317 | 0 | -10317 | 100% |  |  | 0
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 21026118100 | 555 | EX | INSTALL 5680'-2"/4" PMMP | 2022-07-19 | CASTLE ACRE WY LT206C | B | 165876.9601 | 156088.03 | -9788.9301 | -6% | 5680 | 5606 | 27.843
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026118900 | 583 | EX | INSTALL REGULATORS | 2021-09-16 | ISSAC SHELBY CR W | F | 6803.6557 | 4450.3 | -2353.3557 | -35% |  |  | 0 | CCC# 38381 REPLACED REGULATORS ON 9/16/2021 GCCC TICKET NOT REQUIRED ON 9/21/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026119000 | 584 | EX | RETIRE REGULATORS | 2021-09-16 | ISSAC SHELBY CR W | F | 85.0089 | 572.72 | 487.7111 | 574% |  |  | 0 | REPLACED REGULATORS ON 9/16/21 CCC TICKET 38381 OBTAINED ON INSTALL JO CCC TICKET NOT REQUIRED ON 9/21/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U124399 | Bishop,Steven | Gill,John | Dunn,David | 21026119400 | 559 | CO | PM- INST FIL/SEP TOYOTA STA | 2022-10-06 | CHERRY BLOSSOM SPUR | C | 1687500 | 2073205.75 | 385705.75 | 23% |  | 119 | 17421.8971
KY | KY - WEST | 2623 | U124399 | Bishop,Steven | Gill,John | Dunn,David | 21026119500 | 560 | CO | PM-ABAN FOR FILTER INST TOYOTA | 2022-10-06 | CHERRY BLOSSOM SPUR | C | 62500 | 522788.31 | 460288.31 | 736% |  |  | 0
KY | KY - WEST | 2623 | U124399 | Bishop,Steven | Gill,John | Dunn,David | 21026119600 | 559 | CO | PM- TURNER STATION REPLACEMENT | 2022-08-23 | CHERRY BLOSSOM | C | 1012500 | 3311444.82 | 2298944.82 | 227% |  | 68 | 48697.7179
KY | KY - WEST | 2623 | U124399 | Bishop,Steven | Gill,John | Dunn,David | 21026119700 | 560 | CO | PM- TURNER STATION ABANDONMENT | 2022-08-23 | CHERRY BLOSSOM | C | 62500 | 378972.89 | 316472.89 | 506% |  |  | 0
KY | KY - WEST | 2623 | U124399 | Bishop,Steven | Gill,John | Dunn,David | 21026120200 | 559 | CO | PM-INS PIG REC/FILTER JIM BEAM | 2022-06-30 | US 460 | C | 2579017 | 2542524.27 | -36492.73 | -1% |  | 177 | 14364.5439
KY | KY - WEST | 2623 | U124399 | Bishop,Steven | Gill,John | Dunn,David | 21026120300 | 560 | CO | PM-ABA FOR EQUIP INST JIM BEAM | 2022-06-30 | US 460 | C | 62500 | 835157.07 | 772657.07 | 1,236% |  |  | 0
KY | KY - WEST | 2623 | U124399 | Bishop,Steven | Gill,John | Dunn,David | 21026121300 | 559 | CO | PM- SEWELL REPLACEMENT | 2022-06-09 | US 460 / US 62 | C | 1087500 | 2916870.85 | 1829370.85 | 168% |  | 75 | 38891.6113
KY | KY - WEST | 2623 | U124399 | Bishop,Steven | Gill,John | Dunn,David | 21026121400 | 560 | CO | PM- SEWELL ABANDONMENT | 2022-06-09 | US 460 / US 62 | C | 62500 | 692157.41 | 629657.41 | 1,007% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026121700 | 559 | EX | INSTALL 10' OF 6"PHHP MAIN | 2021-06-07 | 167 MCKINNEY AV | B | 16348.9255 | 14437.27 | -1911.6555 | -12% | 60 | 4 | 3609.3175
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026121800 | 560 | EX | RETIRE 10' OF 6"PHHP MAIN | 2021-06-07 | 167 MCKINNEY AV | B | 80.3582 | 0 | -80.3582 | 100% |  |  | 0
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 21026123600 | 557 | EX | REPLACE MAIN - LEAKAGE D253626 | 2021-05-13 | 499 E MAIN ST | A | 5432.0527 | 2711.68 | -2720.3727 | -50% | 10 | 4 | 677.92
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 21026123700 | 558 | EX | EMER 10'-2" PMLP | 2021-05-13 | 499 EAST MAIN ST | A | 85.0408 | 0 | -85.0408 | 100% |  |  | 0
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 21026124100 | 555 | EX | INSTALL 300'-2" PMMP | 2021-11-04 | 98 FINLEY DR | B | 24076.2901 | 41987.03 | 17910.7399 | 74% | 300 | 267 | 157.2548
KY | KY - WEST | 2623 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 21026129300 | 2000 | EX | INVESTIGATE RV PARK ENCROACHME | 2022-11-03 | MIDWAY RIGHT OF WAY |  | 5000 | 0 | -5000 | 100% |  |  | 0
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026130000 | 2000 | EX | CONFLICT ASSESMSNT W/ SEWER | 2023-07-31 | SENECA TL |  | 5098 | 0 | -5098 | 100% |  |  | 0 | CITY 90% COMPLETE WITH PROJECT. ALL CONFLICTS RESOLVED. D.LEMONS 7/31/23
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026131001 | 557 | EX | EMER-INSTALL 10' OF 2"PMMP | 2021-06-23 | MAPLE AV | A | 34334.8702 | 34645.29 | 310.4198 | 1% | 5 | 9 | 3849.4767
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 21026131100 | 558 | EX | EMER-RETIRE 10' OF 2"PAMP MAIN | 2021-02-23 | MAPLE AV | A | 74.8797 | 0 | -74.8797 | 100% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026131200 | 555 | EX | INSTALL 4875' OF 2"/4"PMMP | 2022-05-12 | 100 OLD OXFORD RD | B | 141168.2553 | 140463.01 | -705.2453 | 0% | 4775 | 2516 | 55.8279
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 21026131900 | 557 | EX | INSTALL 3843' OF 2"/4"PMMP MN | 2022-08-16 | LYONS DR | B | 807937.3693 | 1468486.46 | 660549.0907 | 82% | 3843 | 3796 | 386.851 | PROJECT COST OVERRUN DUE TO ADDITIONAL TIME AND RESOURCES NEEDED. CONTRACT COSTS AND LABOR COSTS INCREASED DUE TO UNEXPECTED ROCK ENCOUNTERED DURING C ONSTRUCTION FOR BORE/OPEN CUT OF NEW MAIN. ADDITIONAL TIE-IN LOCATIONS WERE REQUIRED FOR INSTALL AND ABANDONMENT. INCREASED FLAGGING AND INCREASED RES TORATION COSTS ALSO CONTRIBUTED TO THE OVERRUN, AS WELL AS INCREASED SEGA C OSTS. MOLIVER 1/24/23
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 21026132000 | 558 | EX | RETIRE 3700' OF 4"/6"BSLP MAIN | 2022-09-27 | LYONS | B | 52.2976 | 3419.35 | 3367.0524 | 6,438% |  |  | 0
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 21026132600 | 909 | EX | INSTALL NEW TRANSMITTERS | 2021-08-11 | DELAPLANE RD | F | 15506.2901 | 14392.01 | -1114.2801 | -7% |  |  | 0 | CCC #34292 WAITING ON ISO
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 21026132700 | 910 | EX | RETIRE DAMAGED TRANSMITTERS | 2021-08-11 | DELAPLANE RD | F | 82.634 | 0 | -82.634 | 100% |  |  | 0 | WAITING ON ISO SKETCH REPLACED TRANSMITTERS AND RV50 DAMAGED BY LIGHTENING
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026133100 | 587 | EX | INSTAL 2" MOONEY REGS | 2021-09-28 | 982 CHENAULT RD | F | 9907.1191 | 11609.08 | 1701.9609 | 17% | 60 |  | 0 | REPLACED REGULATORS GCCC TICKET NOT REQUIRED
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026133200 | 588 | EX | RETIRE FISHER 399 REGS | 2021-09-28 | 982 CHENAULT RD | F | 90.361 | 0 | -90.361 | 100% |  |  | 0 | REPLACED REGULATORS GCCC TICKET NOT REQUIRED
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026134400 | 562 | EX | RETIRE 98' OF 2"PMMP MAIN | 2021-08-10 | SUGARTREE PARK | B | 3547.617 | 4653.06 | 1105.443 | 31% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026138201 | 557 | EX | EMER-INSTALL 480' OF 6"PMLP | 2021-11-02 | WALNUT ST | A | 240281.6735 | 194700.21 | -45581.4635 | -19% | 480 | 472 | 412.5004 | CCC# 43819 CCC# 43967 TWALKER/KY 05-04-22: JOB CURRENTLY UNDER RUNNING SINCE CITY OF FRANKFORT HAS NOT PAVED STREET AND BILLED CKY - PAVING ESTIMATE AT $35,000.
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026138300 | 558 | EX | EMER-RETIRE 490' OF 6 5/8"BSLP | 2021-11-02 | WALNUT ST | A | 82.634 | 71.35 | -11.284 | -14% |  |  | 0 | KBOTKINS ENTERED WIPE SAMPLE FOR OLIVER MAYNARD WHO IS ATTEMPTING TO COMPLETE THE JOB FOR CLOSE OUT. SAMPLE TAKEN 4/20/22 BUT SYSTEM WOULD NOT ACCEPT THAT DATE DUE TO THE CO DATE.
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 21026138900 | 555 | EX | INSTALL 650'-6" PMMP | 2022-08-30 | 111 KADEN LN | B | 35779.3166 | 111751.03 | 75971.7134 | 212% | 650 | 675 | 165.5571 | COST INCREASE FOR LABOR HOURS AND CONTRACT COSTS DUE TO INCREASED DIRECTION AL BORE FOOTAGE, GPS DATA COLLECTION, INCREASED RESTORATION COSTS, ADDITION AL TIE-IN LOCATIONS NEEDED, AND INCREASE IN SEGA COSTS. - MOLIVER
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026141000 | 557 | EX | EMER - INSTALL 5'-4" PMMP | 2021-09-09 | ROCKY CREEK | A | 427 | 0 | -427 | 100% | 5 | 2 | 0
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026141100 | 558 | EX | EMER - RETIRE 5'-4" PMMP | 2021-09-09 | ROCKY CREEK | A | 68.3073 | 0 | -68.3073 | 100% |  |  | 0
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 21026142700 | 2000 | EX | PS&I OLD OXFORD PH 2 | 2022-08-10 | CASTLE ACRE WY | B | 0 | 0 | 0 | 0% |  |  | 0
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 21026144300 | 557 | EX | EMER - INSTALL 2' OF 2"PMIP | 2021-09-26 | 1118 CHICKASAW | A | 2750.8249 | 137.16 | -2613.6649 | -95% | 2 | 2 | 68.58
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 21026144400 | 558 | EX | EMER - RETIRE 2' OF 2"PAIP | 2021-09-26 | 1118 CHICKASAW TL | A | 75.4968 | 0 | -75.4968 | 100% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026145200 | 583 | EX | EMER-INSTALL NEW BYPASS VALVES | 2021-11-03 | WALNUT ST | F | 4285.9461 | 634.37 | -3651.5761 | -85% |  |  | 0 | CCC# 44725 BYPASS VALVES INSTALLED BY WADE SHIMFESSEL ALONG WITH CONTRACT CREW PAPERWORK COMPLETED BY CYNTHIA FARIS 12/27/21
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026145300 | 584 | EX | EMER-RETIRE BYPASS VALVE | 2021-11-03 | WALNUT ST | F | 60.6987 | 0 | -60.6987 | 100% |  |  | 0 | VALVE REPLACED BY WADE SHIMFESSEL AND CONTRACT CREW ON 11/3/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/11/2022
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 21026147300 | 563 | EX | INSTALL 400'-4" PMMP-SER | 2022-08-30 | 111 KADEN LN | B | 22333.8994 | 32919.84 | 10585.9406 | 47% | 400 |  | 0 | COMMIT DATE MISSED DUE TO WEATHER
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026149100 | 2000 | EX | INVESTIGATE LL SERVICE LINE | 2023-08-03 | 1050 MIDWAY RD |  | 885 | 1311.17 | 426.17 | 48% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026149500 | 557 | EX | EMER-INSTALL 26'-3"/4"PMMP MN | 2021-11-04 | 480 SCHENKEL LN | A | 10953.3154 | 23766.13 | 12812.8146 | 117% | 26 | 26 | 914.0819 | SPLIT IN ALDYLA MAIN.INSTALLED BYPASS.REPLACED CRACKED MAIN AND INLINE TEE WHILE MAIN ON BYPASS.ALL TESTING INFO ON 21026149600 AND 21026149500 IN DOCS
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026149600 | 558 | EX | EMER-RETIRE 26'- 4"PAMP MAIN | 2021-11-04 | 480 SCHENKEL LN | A | 61.5191 | 86.15 | 24.6309 | 40% |  |  | 0 | SPLIT IN ALDYLA MAIN.INSTALLED BYPASS.REPLACED CRACKED MAIN AND INLINE TEE WHILE MAIN ON BYPASS.ALL TESTING INFO ON 21026149600 AND 21026149500 IN DOCS
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 21026154200 | 2000 | EX | PS&I LANES RUN RELO | 2022-03-02 | OLD OXFORD RD | B | 0 | 0 | 0 | 0% |  |  | 0
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 21026154400 | 2000 | EX | PS&I LYONS DR SMRP | 2022-03-29 | LYONS DR | B | 0 | 0 | 0 | 0% |  |  | 0
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026156300 | 2000 | EX | INVESTIGATE MAINS | 2023-01-06 | US 25 |  | 5288 | 0 | -5288 | 100% |  |  | 0 | DEVELOPER TAKING RECOMENDED CHANGES TO ELLIMINATE CONFLICTS WITH EXISTING P IPELINE. D.LEMONS 1/6/2023
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 21026156600 | 555 | EX | INSTALL 230'-2" PMMP | 2022-03-01 | 161 ARROWHEAD CT | B | 15538.521 | 17647.7 | 2109.179 | 14% | 230 | 209 | 84.4388
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 21026157100 | 555 | EX | INSTALL 600'-2" PMMP | 2022-02-10 | 123 CANEWOOD CENTE DR | B | 21934.2504 | 29494.94 | 7560.6896 | 34% | 600 | 403 | 73.1884
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026157200 | 557 | EX | INSTALL 16' OF 3"PMMP MAIN | 2022-02-23 | SKYVIEW DR | B | 11827.5319 | 56295.03 | 44467.4981 | 376% |  | 10 | 5629.503 | TWALKER/KY 02-24-22: WMS WOULD NOT ALLOW PROJECT TO BE REVISED DUE TO UNPAID INVOICES MESSAGE. JOB OVER RUN DUE TO UNKNOWN BOLTED COUPLINGS FOUND DURING CONSTUCTION AND SCOPE OF WORK WAS INCREASED TO REMOVE THOSE COUPLINGS IN THE PAVED STREET. TWALKER/KY 09-16-22: DURING CONSTRUCTION BOLTED COUPLING WERE FOUND ON MP GAS MAIN AND HAD TO BE REMOVED WMS WOULD NOT ALLOW REVISION. ADDITIONAL WORK INCREASED COMPANY LABOR BY $6000 SEGA INCREASED BY $4500 STREET CUT REPAIR REQUIRED AND ADDITIONAL CONTRACT RESOURCES INCREASED BY $27,000
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026157300 | 558 | EX | RETIRE 14' OF 3"CSMP MAIN | 2022-02-23 | SKYVIEW DR | B | 72.8047 | 0 | -72.8047 | 100% |  |  | 0
KY | KY - WEST | 2623 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 21026994800 | 584 | EX | RETIRE STATION 1502 | 2021-10-12 | HOLMES ST | F | 4108.4893 | 8422.17 | 4313.6807 | 105% |  |  | 0 | CCC# 37974 CCC#41227 CCC#41449 CCC# 41449 STATION ABANDONED ON 10/12/2021 PAPERWORK COMPLETED ON 11/2/2021 GCCC TICKET NOT REQUIRED ON 11/2/21 OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 21026998201 | 555 | EX | INSTALL 1930'-2"/4" PMMP | 2022-11-01 | MAGELLAN LN LT1 | B | 114050.6727 | 114169.59 | 118.9173 | 0% | 1930 | 1934 | 59.0329 | GAS ON MAIN 11/01/2022
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026999700 | 561 | EX | INSTALL 125' OF 2"PMMP MAIN | 2021-10-13 | BIZZACK BV | B | 28787.2695 | 22070.53 | -6716.7395 | -23% | 125 | 134 | 164.7054
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026999800 | 562 | EX | RETIRE 115' OF 2"PMMP MAIN | 2021-10-13 | BIZZACK BV | B | 81.0887 | 0 | -81.0887 | 100% |  |  | 0
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 22026158100 | 555 | EX | INSTALL 70'-2" PMMP | 2022-03-10 | 101 BRIARWOOD ST | B | 9277.6445 | 10660.65 | 1383.0055 | 15% | 70 | 57 | 187.0289 | INSTALED 57'OF 020PMMP.
KY | KY - WEST | 2623 | U124399 | Bishop,Steven | Gill,John | Dunn,David | 22026160100 | 559 | EX | PM-GREENSITE I75 ILI DE RELO | 2022-02-16 |  | C | 0 | 6466.13 | 6466.13 | 100% |  | 38 | 170.1613
KY | KY - WEST | 2623 | U124399 | Bishop,Steven | Gill,John | Dunn,David | 22026160200 | 560 | EX | PM-GREENSITE I75 ILI DE ABAN | 2022-02-16 |  | C | 0 | 105.53 | 105.53 | 100% |  |  | 0 | GIS HAD LESS FOOTAGE THAN WHAT WAS FIELD VERIFIED. NO FAC CREATED, DUE TO F ACT IT WAS BEING ABANDONED.
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 22026160400 | 557 | EX | EMER - REPAIR LEAK | 2022-01-13 | 101 MOLLIE WY | A | 3388.6445 | 8003.12 | 4614.4755 | 136% | 20 | 3 | 2667.7067
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 22026160500 | 558 | EX | EMER - REPAIR LEAK | 2022-01-13 | 101 MOLLIE WY | A | 69.6571 | 0 | -69.6571 | 100% |  |  | 0
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026163400 | 2000 | EX | INVESTIGATE MAINS | 2022-03-15 | US HWY 460 | B | 1976 | 0 | -1976 | 100% |  |  | 0 | EXCAVATION SHOWED EXISTING PIPELINE 36" DEEP AND NOT IN DIRECT CONFLICT WIT H PROPOSED SEWER BORE (8' DEEP). D.LEMONS 3/15/2022
KY | KY - WEST | 2623 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026168000 | 909 | EX | HVAC AND RTU PANEL UPGRADE | 2023-04-03 | US 460 - GEORGETOWN RD | F | 39849.6755 | 22883.04 | -16966.6355 | -43% |  |  | 0 | PAPER JOB COMPLETION.
KY | KY - WEST | 2623 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 22026168600 | 557 | EX | INSTALL 13,800'-2"PMMP | 2023-08-08 | 204 PAYNE AV | B | 1751471.355 | 1531903.82 | -219567.535 | -13% | 13800 | 11202 | 136.7527
KY | KY - WEST | 2623 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 22026168700 | 558 | EX | RETIRE 12,327'-BSLP,CSLP,PLP | 2023-08-08 | 204 PAYNE | B | 89.0305 | 0 | -89.0305 | 100% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026175000 | 2000 | EX | INVESTIGATE NON-STANDARD S/L | 2023-08-11 | 165 N SCRUGGS LN | B | 5287 | 3102.15 | -2184.85 | -41% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026179400 | 560 | EX | RETIRE 100' OF 4"PMMP MAIN | 2022-05-13 | 100 OLD OXFORD RD | B | 75.4968 | 0 | -75.4968 | 100% |  |  | 0
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 22026181600 | 561 | EX | RELOCATE ~5"-2" PMMP | 2022-06-07 | 131 ARROWHEAD CT | A | 6138.9503 | 10366.16 | 4227.2097 | 69% | 9 | 10 | 1036.616 | DURING AND AFTER REPLACEMENT PURGE NEW MAIN INTO SERVICE CO M.COLLINS/B.SEXTON RLA 6-7-2022 REPLACED 10' OF 2" P MP MAIN TEST 10' OF 2" PIPE ONSITE 90LBS FOR 1 HR NO LEAKS SOAP TEST TIE IN NO LEAKS BHB NGF SOAP TEST ALL TEE'S CAPS AND DEAD ENDS AT OP AFTER GUAGE REMOVAL NO LEAKS VERIFY DELIVERY PRESSURE BEFORE
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 22026181700 | 562 | EX | RELOCATE ~5"-2" PMMP | 2022-06-07 | 131 ARROWHEAD CT | A | 75.4968 | 0 | -75.4968 | 100% |  |  | 0
KY | KY - WEST | 2623 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 22026183900 | 2000 | EX | INVEST. EASEMENT 22-0261686-00 | 2022-09-02 | 424 PAYNE AV |  | 5000 | 0 | -5000 | 100% |  |  | 0
KY | KY - WEST | 2623 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026185800 | 909 | EX | EXCHANGE ELECTRONIC COMPONENTS | 2022-05-25 | SHOWALTER DR | F | 5480.5156 | 1834.52 | -3645.9956 | -67% |  |  | 0 | CCC# 68240 - REPLACED ERX WITH MIWI 350 - BLONE/CWEMPE - 05/25/22 INSTALLED NEW MIWI 350
KY | KY - WEST | 2623 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026185900 | 910 | EX | RETIRE ELECTRONIC COMPONETS | 2022-05-25 | SHOWALTER DR | F | 124.5156 | 501.88 | 377.3644 | 303% |  |  | 0 | CCC# 68240 - REPLACED ERX WITH MIWI 350 - BLONE/CWEMPE - 05/25/22 RETIRED OLD ERX
KY | KY - WEST | 2623 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026186200 | 909 | EX | EXCHANGE ELECTRONIC COMPONENTS | 2022-05-23 | WILKINSON BV | F | 5480.5156 | 0 | -5480.5156 | 100% |  |  | 0 | INSTALLED NEW MIWI 350 05/23/2022 GHALE
KY | KY - WEST | 2623 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026186300 | 910 | EX | RETIRE ELECTRONIC COMPONENTS | 2022-05-23 | WILKINSON BV | F | 124.5156 | 190.3 | 65.7844 | 53% |  |  | 0 | RETIRED OLD ERX 05/23/2022 GHALE
KY | KY - WEST | 2623 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026186400 | 909 | EX | EXCHANGE ELECTRONIC COMPONENTS | 2022-05-24 | E TODD ST | F | 5480.5156 | 548.88 | -4931.6356 | -90% |  |  | 0 | CCC# 68048 RETIRED ERX AND INSTALLED NEW MIWI350 JPASLEY
KY | KY - WEST | 2623 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026186500 | 910 | EX | RETIRE ELECTRONIC COMPONENTS | 2022-05-24 | E TODD ST | F | 124.5156 | 0 | -124.5156 | 100% |  |  | 0 | RETIRED ERX AND INSTALLED NEW MIWI350 JPASLEY
KY | KY - WEST | 2623 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026186800 | 909 | EX | EXCHANGE ELECTRONIC COMPONENTS | 2022-06-03 | LOUISVILLE RD | F | 4357.5409 | 1456 | -2901.5409 | -67% |  |  | 0 | CCC-69443 INSTALLED NEW MIWI 350 SOAP TEST CONNECTIONS EBLANTON
KY | KY - WEST | 2623 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026186900 | 910 | EX | RETIRE ELECTRONIC COMPONENTS | 2022-06-03 | LOUISVILLE RD | F | 124.5156 | 504.03 | 379.5144 | 305% |  |  | 0 | CCC-69443 RETIRED ERX EBLANTON
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026188400 | 909 | EX | EXCHANGE ELECTRONIC COMPONENTS | 2022-06-02 | 104 FIELDVIEW DR | F | 6681.5691 | 1456 | -5225.5691 | -78% |  |  | 0 | CCC# 69290 - BLONE - 06/02/22 INSTALLED MIWI SN:13450082 P1-0-PSI P2-0-60 IP:10.22.4.15MDN 859-221-6738
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026188500 | 910 | EX | RETIRE ELECTRONICS | 2022-06-02 | 104 FIELDVIEW DR | F | 74.2578 | 473.46 | 399.2022 | 538% |  |  | 0 | CCC# 69290 - BLONE - 06/02/22
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 22026188600 | 555 | EX | INSTALL 165'-2" PMMP | 2022-06-29 | 102 OAK HILL LN | B | 14323.3857 | 11945.7 | -2377.6857 | -17% | 165 | 160 | 74.6606
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 22026188700 | 2000 | EX | INVESTIGATE LAND RIGHTS FOR SL | 2023-08-17 | 301 STANLEY ST | B | 3450 | 2481.72 | -968.28 | -28% |  |  | 0
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026195400 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-08-22 | US60 | F | 4801.1928 | 682.09 | -4119.1028 | -86% |  |  | 0 | CCC# 78156 PAPERWORK ONLY - NO CCC NEEDED - BLONE - 11/8/22 INSTALLED NEW MIWI350 B LONE 8-22-2022
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026195500 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-08-22 | US60 | F | 124.8731 | 676.72 | 551.8469 | 442% |  |  | 0 | CCC# 78156 RETIRED OLD ERX INSTALLED NEW MIWI350 BLONE 8-22-22
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026195600 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-08-23 | 510 VERSAILLES RD | F | 4801.1928 | 5406.36 | 605.1672 | 13% |  |  | 0 | CCC# 78341 - BLONE - 08/23/22 UPGRADED ERX TO MIME CO BY J.MULLINS
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026195700 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-08-23 | 510 VERSAILLES RD | F | 124.8731 | 381.79 | 256.9169 | 206% |  |  | 0 | CCC# 78341 B. LONE UPDATTED ERX TO MIWI CO BY J. MULLINS
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026198900 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-09-06 | US 460 BYPASS | F | 4801.1928 | 5462.44 | 661.2472 | 14% |  |  | 0 | CCC#79730 CWEMPE 9/6/22 UPGRADED ERX TO MIWI PAPERWORK DONE BY J.MULLINS
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026199000 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-09-06 | US 460 BYPASS | F | 124.8731 | 252.74 | 127.8669 | 102% |  |  | 0 | CCC#79730 CWEMPE 9/6/22
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026199300 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-09-01 | 113 GREAT BUFFALO TC | F | 4801.1928 | 5269.21 | 468.0172 | 10% |  |  | 0 | CCC# 79486 RETIRED ERX INSTALLED NEW MIWI350 GHALE 9-1-2022
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026199400 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-09-01 | 113 GREAT BUFFALO TC | F | 124.8731 | 169.77 | 44.8969 | 36% |  |  | 0 | CCC# 79486 RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 9-1-2022
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026199500 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-09-08 | 110 GLENNS CREEK RD | F | 4801.1928 | 5358.86 | 557.6672 | 12% |  |  | 0 | CCC# 80149 P2P OK RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 9-8-2022
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026199600 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-09-08 | 110 GLENNS CREEK RD | F | 124.8731 | 509.01 | 384.1369 | 308% |  |  | 0 | CCC# 80149 RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 09-08-2022
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026200700 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-08-24 | US 460 & IRONWORKS PK | F | 4801.1928 | 5573.15 | 771.9572 | 16% |  |  | 0 | CCC# 68204 - BLONE - 08/24/22 CCC#68204 TIME CHARGED FOR COMPLETING PAPERWORK. CWEMPE 8/30/22 RETIRED ERX INSTALLED NEW MIWI350 CWEMPE 8-24-2022
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026200800 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-08-24 | US 460 & IRONWORKS PK | F | 124.8731 | 285.19 | 160.3169 | 128% |  |  | 0 | CCC# 68204 - BLONE - 08/24/22 CCC#68204 RETIRED OLD ERX INSTALLED NEW MIWI350 CWEMPE 8-24-2022
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026201100 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-09-08 | ROLLING ACRES DR | F | 4801.1928 | 5540.17 | 738.9772 | 15% |  |  | 0 | CCC# 80069 P2P OK RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 9-8-2022
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026201200 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-09-08 | ROLLING ACRES DR | F | 124.8731 | 157.47 | 32.5969 | 26% |  |  | 0 | CCC# 80069 RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 9-8-2022
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 22026202500 | 555 | EX | INSTALL 1120'-2"/4" PMMP | 2022-11-02 | TRINITY LN LT154 | B | 49758.6341 | 50092.05 | 333.4159 | 1% | 1120 | 1096 | 45.7044
KY | KY - WEST | 2623 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 22026204700 | 2000 | EX | PERFORM CONFLICT ASSESSMENT | 2023-11-03 | CROSS COUNTRY | A | 3000 | 4405.73 | 1405.73 | 47% |  |  | 0 | AWEBER 11/3/23 - WORKED WITH DESIGN FIRM, MANHARD CONSULTING, TO MITIGATE A LL CONFLICTS OF DESIGN FOR TRUCKING FACILITY OWNED BY R+L CARRIERS. CONSTRU CTION TO BEGIN Q1-Q2 2024, MONITORING REQUIRED FOR LINES DE & DKT AROUND TH E PROPERTY ADJACENT TO TURNER STATION. SHANNON BARKER TO BE FOL CONTACT.
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026207500 | 583 | EX | INSTALL NEW CONTROL REGULATOR | 2022-08-18 | 177 RUCKER AV | F | 1471.7874 | 893.82 | -577.9674 | -39% |  |  | 0 | CCC#77790 INSTALLED NEW 461-57S CONTROL REGULATOR CWEMPE 8-18-22
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026207600 | 584 | EX | REPLACE CONTROL REG | 2022-08-18 | 177 RUCKER AV | F | 65.0112 | 487.94 | 422.9288 | 651% |  |  | 0 | CCC#77790 REMOVED CONTROL REGULATOR CWEMPE 8-18-22
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026208100 | 0001 | EX | BUFFALO TRACE HOUSE LINE | 2022-11-03 | GREAT BUFFALO TRACE | A | 6132.6749 | 0 | -6132.6749 | 100% |  |  | 0 | COMPETE. NOO LEAKAGE FOUND. S.LURTY 6-29-22 1040
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026208600 | 557 | EX | EMER - INSTALL 2'-2" PMMP | 2022-06-26 | HAWTHORNE | A | 5654.5749 | 7597.73 | 1943.1551 | 34% | 2 | 2 | 3798.865
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026208700 | 558 | EX | EMER - RETIRE 2'-2" PMP | 2022-06-24 | HAWTHORNE | A | 63.5475 | 0 | -63.5475 | 100% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026211200 | 557 | EX | EMER-INSTALL 6' OF 4"PMIP MAIN | 2022-07-07 | 1149 LISLE RD | A | 10641.1495 | 13924.65 | 3283.5005 | 31% | 6 | 6 | 2320.775
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026211300 | 558 | EX | EMER-RETIRE 6' OF 4"PAIP MAIN | 2022-07-07 | 1149 LISLE RD | A | 65.0112 | 0 | -65.0112 | 100% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026213400 | 583 | EX | INSTALL NEW 1" REGULATORS | 2022-10-07 | 488 LEXINGTON RD | F | 1461.8601 | 2234.49 | 772.6299 | 53% |  |  | 0 | REPLACED BOTH MONITOR AND CONTROL REGULATORS AND INLET AND OUTLET VALVES BL ONE 10-7-22
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026213500 | 584 | EX | RETIRE REGULATORS | 2022-10-07 | 488 LEXINGTON RD | F | 84.9152 | 856.14 | 771.2248 | 908% |  |  | 0 | REPLACED BOTH MONITOR AND CONTROL REGULATORS AND INLET AND OUTLET VALVES BL ONE 10-7-22
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 22026213900 | 555 | EX | INSTALL 200'-2"PMMP | 2022-10-20 | 216 SUGARTREE LN | B | 22574.1191 | 35208.99 | 12634.8709 | 56% | 200 | 308 | 114.3149 | BORED IN 308' OF 020 PL ML. TESTED 90# FOR 1 HR. SOAP TESTED CONN PTS @ 39#
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 22026214100 | 562 | EX | ABANDON 200'-2" PMMP | 2022-10-21 | SUGARTREE LN | B | 800.8601 | 921.07 | 120.2099 | 15% |  |  | 0
KY | KY - WEST | 2623 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026214500 | 910 | EX | JIM BEAN RTU PANEL | 2023-04-03 | US 460 - GEORGETOWN RD | F | 55.5311 | 2091.18 | 2035.6489 | 3,666% |  |  | 0 | CCC# 15710 CCC# 15710
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026215700 | 557 | EX | EMER-INSTALL 2' OF 2"PMMP MAIN | 2022-07-11 | W MAIN ST | A | 8681.8934 | 4910.67 | -3771.2234 | -43% | 2 | 2 | 2455.335 | REPLACED 2FT OF 020 DAMAGED MAIN.TESTED NEW MAIN FOR 20MINS AT 90LBS.TEST OK.SOAP TEST EFC'S AT OP FOR 5MINS.TEST OK. BHBNGF
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026215800 | 558 | EX | EMER-RETIRE 2' OF 2"PMP MAIN | 2022-07-11 | W MAIN ST | A | 84.9152 | 224.99 | 140.0748 | 165% |  |  | 0 | REPLACED 2FT OF 020 DAMAGED MAIN.TESTED NEW MAIN FOR 20MINS AT 90LBS.TEST OK.SOAP TEST EFC'S AT OP FOR 5MINS.TEST OK. BHBNGF
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026220400 | 562 | EX | ABANDON 550' OF 2"PMP MAIN | 2022-08-29 | 1175 GEORGETOWN RD | A | 3449.8998 | 184.67 | -3265.2298 | -95% |  |  | 0 | ABANDONED 020 MP PL ML. PREFORMED PER ABANDONMENT PLAN SOAP TEST DEAD END C AP OP 15 MINUTES. C HERNDON/S.BARKER PURGED ABANDONED SECTION OF LINE. CAPPED THE ENDS OF ABANDONED ML.
KY | KY - WEST | 2623 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 22026221000 | 555 | EX | INSTALL 160'-4"PMMP | 2022-11-14 | 515 EVERGREEN RD | B | 20578.0582 | 36375.08 | 15797.0218 | 77% | 160 | 177 | 205.5089 | AWEBER 12/6/22 - JOB ENCOUNTERED HEAVY ROCK BORE, RESULTING IN DOUBLE TIME FROM ORIGINAL ESTIMATE. ATTEMPT TO REVISE, UNABLE DUE TO UNPAID INVOICES.
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 22026222700 | 555 | EX | INSTALL 86'-2" PMMP | 2022-12-07 | 209 W LYNN ST | B | 12304.5709 | 13511.21 | 1206.6391 | 10% | 86 | 60 | 225.1868 | THERE WAS A TYPO ON THE PRESSURE SYSTEM WHEN IT WAS CREATED. CORRECT SYSTEM NUMBER 32010047. SYSTEM NUMBER HAS BEEN CORRECTED IN DIS.
KY | KY - WEST | 2623 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 22026225400 | 557 | EX | INSTALL APROX 180'-6" PMLP | 2023-08-17 | 601 VERSAILLES RD | B | 120007.3465 | 160069.05 | 40061.7035 | 33% | 180 | 215 | 744.5072 | GURU ADDED 2'-6"PLASTIC RISER PIPE TO TD 0735002. SM 11/7/23
KY | KY - WEST | 2623 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 22026225500 | 558 | EX | RETIRE 200' - 6" BSLP | 2023-08-17 | 601 VERSAILLES RD | B | 117.7346 | 510.72 | 392.9854 | 334% |  |  | 0
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 22026227300 | 2000 | EX | PS&I CROSSWINDS CENTER PATH | 2023-08-17 | 105 CROSSWINDS CENTER PATH | B | 2477 | 6814.09 | 4337.09 | 175% |  |  | 0
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 22026227400 | 2000 | EX | PS&I MACEY AVE SMRP | 2023-08-17 | MACEY AV | B | 1180 | 1180 | 0 | 0% |  |  | 0
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 22026229200 | 555 | EX | INSTALL 80'-2" PMMP | 2023-01-27 | 760 COLONIAL TC | B | 11104.5291 | 10781.29 | -323.2391 | -3% | 80 | 160 | 67.3831 | INSTALLED 160' 2'' MP-PL MAINLINE
KY | KY - WEST | 2623 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 22026230000 | 562 | EX | ABANDON 470'-2"&3"PLP | 2022-11-01 | 105 BRIGHTON PARK BV | B | 6027.5291 | 5899.02 | -128.5091 | -2% |  |  | 0 | ABANDONED 334' OF 030 PL LP ML PER ENGINEERING AND TIE IN PLAN. SOAP TEST END CAP @ OP 15 MINS NO LEAKS BHB NGF. PURGED OUT ABANDONED SECTION OF ML G OOD M. COLLINS 11/1/2022
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 22026231200 | 555 | EX | INSTALL 1870'-2"/4" PMMP | 2023-10-03 | SAFFRON LN LT19 | B | 71796.5181 | 89157.03 | 17360.5119 | 24% | 1870 | 1987 | 44.8702
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026236000 | 575 | EX | ADDITIONAL EASEMENT/LAND | 2022-11-11 | 3200 GEORGETOWN RD | F | 136.2135 | 0 | -136.2135 | 100% |  |  | 0
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 22026241001 | 555 | EX | INSTALL 6375'-2"/4" PMMP ENV | 2023-11-29 | STREET B LT15 | B | 793212.5591 | 797679.45 | 4466.8909 | 1% | 6375 | 6405 | 124.5401
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026241200 | 2000 | EX | RESEARCH EASEMENTS & R/W | 2023-10-24 | WINTER ST |  | 19599 | 0 | -19599 | 100% |  |  | 0 | PS&I FOR SMRP NORTH MIDWAY. D.LEMONS 10/24/2023
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026243700 | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2023-04-17 | 1175 LISLE RD | F | 29277.8866 | 17949.62 | -11328.2666 | -39% |  |  | 0 | CC 22683 CC 22535 WELDED INLET TAP TESTED INLET 375# 5 MINS RHAYES DMARTIN 03-29-2023 CCC# 24078 NOT ON SITE. CAPITAL PAPERWORK CCC#25522 CWEMPE 4/17/23 COMPLETED PAPERWORK OFFSITE. CWEMPE 4/20/23 DID NOT ENTER STATION. CHARGED TIME FOR PAPERWORK. CWEMPE 4/24/23
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026243800 | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2023-04-18 | LONG LICK RD | F | 32044.6752 | 17170.68 | -14873.9952 | -46% |  |  | 0 | CC 22535 WELDED TAPS TESTED INLET 375# OUTLET 45# MINS DMARTIN RHAYES 03-29-2023 CCC# 24067 CCC#25645 CWEMPE 4/18/23 COMPLETED PAPERWORK OFFSITE. CWEMPE 4/20/23 DID NOT ENTER STATION. CHARGED TIME FOR PAPERWORK. CWEMPE 4/24/23
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026244100 | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2023-04-19 | HILLSIDE DR | F | 32044.6752 | 17388.43 | -14656.2452 | -46% |  |  | 0 | CC 22622 CC 22535 WELDED TAPS TESTED INLET 375# OUTLET 90# 5 MINS RHAYES DMARTIN 03-29-2023 CCC# 24075 CALLED FOR CLEARANCE TICKET AT END OF DAY AND CCC REFUSED TO CREATE TICKET. CWEMPE 4/19/23 COMPLETED PAPERWORK OFFSITE. CWEMPE 4/20/23
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026244200 | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2023-04-25 | 413 VILLAGE DR | F | 33186.6752 | 20934.82 | -12251.8552 | -37% |  |  | 0 | CCC# 24912 WELDED ON PUNCH TEES FOR SCADA VISIBILITY PROJECT. TESTED TAPPED, AND MT COMPLETE. LOCKED AND PLUGGED VALVE. CCC# 26916
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026244300 | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2023-04-21 | DUCKER STATION RD | F | 29761.6752 | 21295.01 | -8466.6652 | -28% |  |  | 0 | CC 22295 TAPS WELDED TESTED INLET 375# OUTLET90# 5MIN TESTED GOOD RHAYES CCC# 24050 CCC#26526 CWEMPE 4/21/23
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026245100 | 557 | CO | EMER-INSTALL 3' OF 2"PHHP MAIN | 2022-12-07 | ROCKY WATERS | B | 4877.0569 | 2752.76 | -2124.2969 | -44% | 3 | 3 | 917.5867
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 23026249500 | 555 | EX | INSTALL 870'-2" PMMP | 2023-04-04 | 150 IKEBANA DR | B | 67614.2583 | 52378.28 | -15235.9783 | -23% | 870 | 876 | 59.7926
KY | KY - WEST | 2623 | U132257 | McGuire,Chera Lee | Opfer,Matthew | Dunn,David | 23026249600 | 559 | CO | PM- DE ILI PH 2 JIM BEAM INST | 2023-01-27 | 3200 GEORGETOWN RD | B | 593000 | 965942.08 | 372942.08 | 63% |  | 22 | 43906.4582
KY | KY - WEST | 2623 | U132257 | McGuire,Chera Lee | Opfer,Matthew | Dunn,David | 23026249700 | 560 | CO | PM- DE ILI PH 2 JIM BEAM ABAN | 2023-01-27 | 3200 GEORGETOWN RD | B | 132000 | 234155.55 | 102155.55 | 77% |  |  | 0
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 23026251500 | 555 | EX | INSTALL 70'-2" PMLP | 2023-05-05 | 244 W BRUEN ST | B | 20790.0608 | 16349.3 | -4440.7608 | -21% | 70 | 122 | 134.0107
KY | KY - WEST | 2623 | U124399 | Bishop,Steven | Gill,John | Dunn,David | 23026252900 | 559 | EX | PM-GREENSITE RAILROAD CROSSING | 2022-07-12 |  | B | 1236355 | 17890.94 | -1218464.06 | -99% |  | 41 | 436.3644
KY | KY - WEST | 2623 | U124399 | Bishop,Steven | Gill,John | Dunn,David | 23026253000 | 560 | EX | PM-GREENSITE RAILROAD ABANDON | 2022-07-12 |  | B | 0 | 328.14 | 328.14 | 100% |  |  | 0
KY | KY - WEST | 2623 | U124399 | Bishop,Steven | Gill,John | Dunn,David | 23026253500 | 559 | CO | PM-GREENSITE IRONWORKS DE REPL | 2022-05-13 |  | B | 1236355 | 18978.29 | -1217376.71 | -98% |  | 83 | 228.6541
KY | KY - WEST | 2623 | U124399 | Bishop,Steven | Gill,John | Dunn,David | 23026253600 | 560 | CO | PM-GREENSITE IRONWORKS ABAN | 2022-05-13 |  | B | 0 | 0 | 0 | 0% |  |  | 0
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 23026254300 | 555 | EX | TAP W/MAIN 23-0262543-00 | 2023-02-08 | 1220 DISCHER DR | B | 13015.0987 | 4459.75 | -8555.3487 | -66% | 60 | 9 | 495.5278
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026255400 | 588 | EX | GMB TO CAB CONVERSION | 2023-06-01 | 900 TYRONE PK FF | F | 2712.0987 | 9499.75 | 6787.6513 | 250% |  |  | 0 | REMOVED OLD GMB FACILITIES REBUILT METER SETTING INSTALLED NEW ROMET 16M ME TER AND CL838 REGS ON 15# DELIVERY BLONE 6-1-23
KY | KY - WEST | 2623 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 23026256000 | 557 | EX | INSTALL 800'OF 2"PMMP MAIN | 2023-07-19 | TIMBERLAWN | B | 192451.7008 | 92592.66 | -99859.0408 | -52% | 800 | 724 | 127.8904
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026256600 | 584 | EX | RETIRE PAPER GAUGE | 2023-03-02 | 1024 CAPITAL CENTER DR | F | 138.8485 | 468 | 329.1515 | 237% |  |  | 0 | CHART BOXES REMOVED. G.HALE A.PARKS 03-02-23 CHARTS REMOVED AND STORED AT LEX MOD APARKS 03-02-23
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 23026257100 | 555 | EX | INSTALL 300'-2" PMMP | 2023-09-28 | 135 AMERICAN PH | B | 32921.1974 | 68581.44 | 35660.2426 | 108% | 300 | 400 | 171.4536 | MAINLINE EXTENSION FOR ALDI'S INSTALLED BY STANLEY PIPELINE. JOSH PASLEY 9/28/23
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026259600 | 909 | EX | INSTALL ERX AND SUPER SOLAR | 2023-03-07 | 1625 MIDWAY RD | F | 5600.9621 | 3652.44 | -1948.5221 | -35% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026259700 | 584 | EX | RETIRE PAPER CHART | 2023-03-07 | US 62 AT LANES END FRM | F | 138.8485 | 269.78 | 130.9315 | 94% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026260600 | 588 | EX | GMB TO CAB CONVERSION | 2023-04-04 | 141 COMMERCE BV | F | 138.8485 | 1404.11 | 1265.2615 | 911% |  |  | 0 | GATHER PARTS FOR CONVERSION, MTR, FLANGES, GASKETS ETC. REGULATOR GMB TO CAB CONVERSION GAS ON BYPASS DURING REBUIL;D NO BYPASS GAS USED INST ALLED NEW ROMET 3M ON 2#
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026261900 | 2000 | EX | MAP AND INVESTIGATE MAINS | 2023-11-01 | DUNCAN RD |  | 31431 | 0 | -31431 | 100% |  |  | 0
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 23026265900 | 2000 | EX | PS&I BLUEGRASS DISTILLERY | 2023-08-17 | 158 W LEESTOWN RD | B | 0 | 0 | 0 | 0% |  |  | 0
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 23026266100 | 555 | EX | INSTALL 880'-4" PHHP | 2023-08-18 | 100 LACEFIELD ST | B | 60596.7317 | 70247.34 | 9650.6083 | 16% | 880 | 971 | 72.3454
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 23026266200 | 555 | EX | INSTALL 1100'-4" PHHP | 2023-09-12 | 1050 GEORGETOWN RD BLDG C | B | 81743.7317 | 125731.21 | 43987.4783 | 54% | 1100 | 1093 | 115.0331
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 23026268100 | 558 | EX | RETIRE MAIN - LEAKAGE | 2023-02-27 | ELMENDORF | A | 117.7346 | 0 | -117.7346 | 100% |  |  | 0
KY | KY - WEST | 2623 | U132257 | McGuire,Chera Lee | Opfer,Matthew | Dunn,David | 23026268500 | 559 | CO | PM-DE LINE ILI PH 2 BEND 260 | 2023-06-16 |  | B | 1150001 | 717133.15 | -432867.85 | -38% |  | 30 | 23904.4383
KY | KY - WEST | 2623 | U132257 | McGuire,Chera Lee | Opfer,Matthew | Dunn,David | 23026268600 | 559 | CO | PM-DE LINE ILI PH2 DENT 36 | 2023-06-03 |  | B | 1150001 | 1598843.54 | 448842.54 | 39% |  | 18 | 88824.6411
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026269000 | 557 | EX | EMER-INSTALL 4' OF 2"PMMP MAIN | 2023-03-17 | MACK ST | A | 5499.7073 | 6353.99 | 854.2827 | 16% | 4 | 4 | 1588.4975
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026269100 | 558 | EX | EMER-RETIRE 4' OF 2"PAMP MAIN | 2023-03-17 | MACK ST | A | 117.7346 | 0 | -117.7346 | 100% |  |  | 0
KY | KY - WEST | 2623 | U132257 | McGuire,Chera Lee | Opfer,Matthew | Dunn,David | 23026269200 | 560 | CO | PM-DE LINE ILI PH2 BEND 260 AB | 2023-06-23 |  | C | 192300 | 195099.48 | 2799.48 | 1% |  |  | 0
KY | KY - WEST | 2623 | U132257 | McGuire,Chera Lee | Opfer,Matthew | Dunn,David | 23026269300 | 560 | CO | PM-DE LINE ILI PH2 DENT 36 ABD | 2023-06-05 |  | C | 192300 | 279860.8 | 87560.8 | 46% |  |  | 0
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 23026271000 | 559 | EX | INSTALL 70'-2" PMMP | 2023-04-10 | 155 W MAIN ST | A | 9795.9371 | 606.43 | -9189.5071 | -94% | 70 | 70 | 8.6633
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 23026271100 | 560 | EX | ABANDON 60'-2" PMMP | 2023-04-10 | 155 W MAIN ST | A | 262.8722 | 4210.59 | 3947.7178 | 1,502% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026271300 | 575 | EX | OBTAIN ADDITIONAL LAND RIGHTS | 2023-07-10 | INDUSTRY RD | F | 83269 | 72514.71 | -10754.29 | -13% |  |  | 0 | TWALKER/KY 07-10-23: THIS JOB ORDER CREATE TO RECORD AND DOCUMENT NEW 40' X 40' SITE/LAND FOR FUTURE REG STATION EXPANSION.
KY | KY - WEST | 2623 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 23026271800 | 2000 | EX | INVESTIGATE RW AND EASEMENT | 2023-08-03 | 601 VERSAILLES RD |  | 3382 | 0 | -3382 | 100% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026273500 | 557 | EX | EMER-INSTALL 65' OF 2"PMIP | 2023-04-21 | 124 LEE LN | A | 8772.0552 | 5983.61 | -2788.4452 | -32% | 65 | 87 | 68.7771
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026273600 | 558 | EX | EMER-RETIRE 55' OF 2"PAIP | 2023-04-21 | 124 LEE LN | A | 117.7346 | 1024.42 | 906.6854 | 770% |  |  | 0
KY | KY - WEST | 2623 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026278800 | 2000 | EX | INVESTIGATE MAINS | 2023-07-31 | LEXINGTON RD |  | 3788 | 0 | -3788 | 100% |  |  | 0 | CONFLICTS CLEARED BY VAC EXCAVATE. D.LEMONS 7/31/2023
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 23026278900 | 555 | EX | INSTALL 150'-2" PMMP | 2023-07-28 | DOVE RUN CR LT160 | B | 13769.2187 | 10151.75 | -3617.4687 | -26% | 150 | 128 | 79.3105
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 23026279800 | 555 | EX | INSTALL 1800'-2" PMMP | 2023-07-24 | 131 OXFORD LANDING DR | B | 72065.7028 | 53278.51 | -18787.1928 | -26% | 1800 | 1807 | 29.4845
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026281200 | 557 | EX | EMER-INSTALL 2' OF 2"PMMP MAIN | 2023-06-26 | 111 MARKETPLACE CR | A | 5082.4374 | 6222.18 | 1139.7426 | 22% | 2 | 2 | 3111.09
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026281300 | 558 | EX | EMER-RETIRE 2' OF 2"PMMP MAIN | 2023-06-26 | 111 MARKETPLACE CR | A | 139.1159 | 0 | -139.1159 | 100% |  |  | 0
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 23026281400 | 555 | EX | INSTALL 1865'-2"/4" PMMP | 2023-11-01 | HOURGLASS LN LT13 | B | 77027.7111 | 90143.57 | 13115.8589 | 17% | 1865 | 1873 | 48.1279
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026284000 | 557 | EX | EMER-INSTALL 2' OF 3"PMMP MAIN | 2023-07-12 | 615 COMANCHE TL | A | 4281.828 | 14848.12 | 10566.292 | 247% | 2 | 2 | 7424.06
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026284100 | 558 | EX | EMER-RETIRE 2' OF 3"PAMP MAIN | 2023-07-12 | 615 COMANCHE TL | A | 139.1159 | 0 | -139.1159 | 100% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026285800 | 557 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | 2023-07-27 | 111 MARKETPLACE CR | A | 6991.8345 | 8976.29 | 1984.4555 | 28% | 3 | 3 | 2992.0967
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026285900 | 558 | EX | EMER-RETIRE 3' OF 2"PMMP MAIN | 2023-07-27 | 111 MARKETPLACE CR | A | 139.1159 | 0 | -139.1159 | 100% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026288700 | 583 | EX | INSTALL NEW RELIEF VALVE | 2023-08-11 | 488 LEXINGTON RD | F | 3278.6711 | 814.62 | -2464.0511 | -75% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026288800 | 584 | EX | RETIRE RELIEF VALVE | 2023-08-11 | 488 LEXINGTON RD | F | 119.4953 | 0 | -119.4953 | 100% |  |  | 0
KY | KY - WEST | 2623 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 23026291400 | 560 | EX | PAPER JOB - MP RETIREMENT | 2023-06-27 | 100 TANGLEWOOD DR | B | 119.4953 | 0 | -119.4953 | 100% |  |  | 0
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 23026294600 | 562 | EX | ABANDON ~790'-2" PMMP | 2023-10-03 | SAFFRON LN | B | 3905.6711 | 392.35 | -3513.3211 | -90% |  |  | 0
KY | KY - WEST | 2623 | U126783 | Oliver,Madison Jourdan | Parsley,Joe | Webb,Jared | 23026296100 | 2000 | EX | PS&I WOODFORD COUNTY HIGH | 2023-11-01 | TYRONE PIKE | B | 0 | 0 | 0 | 0% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026296400 | 557 | EX | INSTALL 110' OF 2"PMMP MAIN | 2023-12-14 | 565 SCHENKEL | B | 46114.2728 | 58459.83 | 12345.5572 | 27% | 110 | 164 | 356.4624 | CAPITAL JOB COMPLETE BY STANLEY PIPELINE AND CLEARED ASSOCIATED DPI'S. JOSH PASLEY 12/21/23
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026296500 | 558 | EX | RETIRE 88' OF 2"CSMP MAIN | 2023-12-14 | 565 SCHENKEL | B | 122.9261 | 0 | -122.9261 | 100% |  |  | 0 | CAPITAL JOB COMPLETED BY STANLEY PIPELINE. CLEARED ASSOCIATED DPI'S. JOSH PASLEY 12/21/23
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026301600 | 909 | EX | INSTAL NEW MODEM | 2023-11-06 | 120 WASSAU AL | F | 2605.8688 | 652.23 | -1953.6388 | -75% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026301700 | 910 | EX | RETIRE MODEM | 2023-11-06 | 120 WASSAU AL | F | 122.9261 | 365.2 | 242.2739 | 197% |  |  | 0
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026307400 | 557 | EX | EMER-INSTALL 3' OF 2"PMMP | 2023-12-05 | 122 OLD TOWNE | A | 2930.7643 | 1356.05 | -1574.7143 | -54% | 3 | 3 | 452.0167
KY | KY - WEST | 2623 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026307500 | 558 | EX | EMER-RETIRE 3' OF 2"PMP MAIN | 2023-12-05 | 122 OLD TOWNE | A | 123.4493 | 0 | -123.4493 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 06026166300 | 2000 | EX | INVESTIGATE R/W OF SERVICES | 2019-07-09 | WEBSTER AVE | B | 0 | 0 | 0 | 0% |  |  | 0 | 16JUL20: CHARGES ACCUMULATED DURING INVESTIGATION & EASEMENT ACQUISITIONS.
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 17026706600 | 588 | EX | CONVERT FROM GMB TO CAB ACCT | 2023-07-17 | 5555 ROCKWELL RD | F | 1078.4716 | 14520.06 | 13441.5884 | 1,246% |  |  | 0 | CCC# 36905 CCC#36905
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 17026708901 | 557 | EX | INSTALL 4400' OF 2"/4"PMMP | 2019-10-03 | PLEASANT ST | B | 820561.0822 | 1164532.13 | 343971.0478 | 42% | 4000 | 3990 | 291.8627 | LEVEL 2 VARIANCE EXPLANATION IN DOCS
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 17026709000 | 558 | EX | ABANDON 6500' OF 4"CI/BS/CS LP | 2019-12-20 | PLEASANT ST | B | 260.7833 | 60.1 | -200.6833 | -77% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 17026722401 | 557 | EX | INSTALL 250' - 4" CSHP | 2019-08-05 | 4413 LEVEE RD | B | 137260.0836 | 169943.98 | 32683.8964 | 24% | 250 | 354 | 480.0677 | OVERRUN EXPLANATION: THE ORIGINAL ESTIMATE DID NOT INCLUDE ENVIRONEMENTAL D OLLARS WHICH WAS ABOUT $4,000. IT ALSO DID NOT INCLULDE NON-DESTRUCTIVE TES TING WHICH WAS ABOUT $5000. THE COSTRACT COSTS ALSO EXCEEDED THE ESTIMATE P RIMARILY DUE TO ADDITIONAL OPERATOR HOURS REQUIRED.
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 17026722500 | 558 | EX | RETIRE 200' - 4" BSHP | 2019-08-05 | 4413 LEVEE | B | 51.2636 | 682.75 | 631.4864 | 1,232% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 17026727500 | 909 | EX | INSTALL MERCURY ERX | 2020-07-24 | MAIN ST | F | 27248.6934 | 22266.22 | -4982.4734 | -18% |  |  | 0 | JOB ON HOLD DUE TO MANPOWER ISSUES AND STATION TOP WORKS MODIFICATION
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 17026728801 | 557 | EX | INSTALL 1200' - 4" PMMP | 2019-10-23 | BETHLEHEM RD | B | 856768.8391 | 1004690.34 | 147921.5009 | 17% | 1200 | 3461 | 290.289 | TTOY - 3/5/20 JOB OVERUN DUE TO ~$30,000 IN ADDITIONAL SEGA COSTS, MATERIAL ORDERED MULTIPLE TIMES AT AN ADDITIONAL COST OF $11,475, EXTRA AFUDC COSTS OF $9,307, ADDITIONAL CONTRACT COSTS OF MISC DOLLARS FOR ~$40,000, AND ADDITIONAL LABOR ADDING UP TO $7,616.
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 17026728900 | 558 | EX | RETIRE 1209' - 2" MP MAIN | 2019-10-23 | BETHLEHEM RD | B | 64.9458 | 391.85 | 326.9042 | 503% |  |  | 0
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 17026730900 | 557 | EX | INSTALL 3700'-12" CSHP | 2020-06-08 | 3315 COLBY RD | B | 812061.6863 | 778663.08 | -33398.6063 | -4% | 3700 | 3369 | 231.1259
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 17026731000 | 558 | EX | RETIRE 3617'- 8"/12" CS/BSHP | 2020-06-09 | 3315 COLBY RD | B | 65342.8129 | 4882.18 | -60460.6329 | -93% |  |  | 0 | UNDERRUN EXPLANATION: THIS RETIREMENT JOB ORDER HAD ESTIMATED THAT FILLING THE PIPELINE WITH GROUT AFTER CONSTRUCTION TO FULFILL THE TERMS OF AN EASEM ENT. IT WAS DETERMINED THAT IT WAS APPROPRIATE TO CHARGE THIS ACTIVITY TO T HE INSTALLATION JOB ORDER INSTEAD. THE PROJECT BUDGET REQUEST WAS FOR $975, 000, AND THE TOTAL JOB ORDER COSTS WERE $786,000 OR A 19% UNDERRUN FOR THE PROJECT. THEREFORE IN ACCORDANCE WITH THE CAPITAL GOVERNANCE POLICY THIS DO ES NOT REQUIRE A LEVEL TWO VARAINCE, AND THE EXPLANATION FOR UNDERRUNNING T HIS PROJECT IS THAT THE GROUTING WAS PAID ON ANOTHER JOB ORDER IN THIS PROJ ECT.
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 17026738300 | 2000 | EX | 3315 COLBY RD AMRP - EASEMENTS | 2020-03-06 | 3315 COLBY RD |  | 9978 | 0 | -9978 | 100% |  |  | 0 | EXECUTED AND CHARGED-OFF TO (557) 17-0267309-00 (BKSLONE)
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 17026743700 | 559 | EX | INSTALL 450'-2" PMMP | 2020-08-20 | MONTICELLO HT | B | 39245.9421 | 24717.31 | -14528.6321 | -37% | 450 | 444 | 55.6696 | PROJECT ID FOR THIS AND 19-0268690-00 ARE THE SAME. STEVE CANOY 09/10/2020.
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 18026756801 | 557 | EX | INSTALL 500' - 2" CSHP | 2019-04-09 | SAFETY WY | B | 56417.9027 | 72110.42 | 15692.5173 | 28% | 500 | 435 | 165.7711
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 18026756900 | 558 | EX | RETIRE 750' - 2" BSHP | 2019-04-09 | SAFETY WY | B | 67.8275 | 0 | -67.8275 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 18026763300 | 2000 | EX | BEDFORD ACRES STORM WATER | 2019-07-02 | VARIOUS |  | 3941.3965 | 0 | -3941.3965 | 100% |  |  | 0 | 7/2/19: CONFLICT ASSESSMENT COMPLETED BY BRYAN SLONE AND REQUIRED TCE'S ACQUIRED BE CHRIS DAVIS. SEE (561'S) 19-0268662-00 & 19-0268777-00
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 18026763500 | 583 | EX | R-1238 INSTALL CWT HEATER | 2019-08-28 | 900 HICKORY RIDGE RD | F | 974892.3519 | 1266077.97 | 291185.6181 | 30% |  |  | 0 | 12/24/19: VARIANCE EXPLANATION = 1) CONTRACT LABOR WAS NOT ADEQUATELY ACCOUNTED FOR IN THE ORIGNAL ESTIMATE RESULTING IN $130K +/- OVERAGE; 2) RTU EQUIPMENT WAS ORIGINALLY UNDER ESTIMATED RESULTING IN $70K +/- OVERAGE; 3) COMPANY LABOR WAS OVER FIVE TIMES THE ORIGINAL ESTIMATE RESULTING IN $30K OVERAGE; + 4) OVERHEADS ASSOCIATED WITH THESE RESULTED IN AND ADDITIONAL $50K +/- OVERAGE = CAPTURES THE MAJORITY OF THE OVERRUN. . ATTEMPTS TO REVISE THE JOB ORDER DURING CONSTRUCTION WERE UNSUCCESSFUL DUE TO OUTSTANDING CONTRACT AND/OR MATERIAL INVOICES (BKSLONE).
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 18026763600 | 584 | EX | R-1238 RETIRE WATER BATH HTR | 2019-06-11 | 900 HICKORY RIDGE RD | F | 9719.5764 | 17505.78 | 7786.2036 | 80% |  |  | 0
KY | KY - CENTRAL | 2629 | U131369 |  |  |  | 18026766400 | 909 | EX | I&C - INSTALL SCADA EQUIPMENT | 2022-09-29 | LEVEE RD | F | 183526.0448 | 143824.82 | -39701.2248 | -22% |  |  | 0 | JMULLINS COMPLETE PAPERWORK TWALKER/KY 01-24-23: JOB UNDER RUN DUE TO MATERIAL COST WAS $33,000 LESS THAN PLANNED, NO SEGA CHARGED TO JOB ORDER PROJECT WAS PLANNED FOR $23,000
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 18026767000 | 575 | EX | ACQUIRE LAND FOR SCADA BUILD. | 2019-05-04 | LEVEE RD | F | 10852 | 15516.89 | 4664.89 | 43% |  |  | 0 | 1/7/20: COMPLETED BY BRYAN SLONE FOR CHRIS DAVIS W/TEAM FISHEL
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 18026767100 | 577 | EX | 25X25 FENCE FOR SCADA BUILDING | 2019-05-29 | LEVEE RD | F | 11651.8996 | 8742.75 | -2909.1496 | -25% |  |  | 0 | WSHIMFE05-29-2019
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 18026781300 | 555 | EX | INSTALL 750' OF 4"PMLP MAIN | 2019-06-14 | 430 FAIRHOLME WY | B | 21512.6987 | 24308.98 | 2796.2813 | 13% | 750 | 780 | 31.1654 | REVIEWED TIE-IN PLAN WITH ENGINEERING ON 6-14-19 MISSED COMMIT DUE TO WEATHER/PERSONNEL/EQUIPMENT
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026781901 | 555 | EX | INSTALL 1000' OF 6"PMMP MAIN | 2019-03-25 | 950 ROLLING HILLS LN | B | 215170.0254 | 211247.45 | -3922.5754 | -2% | 650 | 943 | 224.0164
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 18026783500 | 555 | EX | INSTALL 1500' - 4" PMMP | 2020-01-31 | 3100 CORPORATE DR | B | 54214.2804 | 92809.31 | 38595.0296 | 71% | 1500 | 1752 | 52.9734 | TTOY 6/8/2020 OVERRUN EXPLANATION: CONTRACT UPDATE CAUSING INCREASED UNIT COSTS, UNANTICIPATED ROCK EXCAVATION, ADDITIONAL ROCK CAUSING LONGER DURATION AND INCREASED HOURS, SEGA INCREASED $3,000, ADDTIONAL LABOR ADDING UP TO $10,000
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026786300 | 575 | EX | NEW EASEMENT FOR REG STATION | 2019-03-19 | PAULA DR | F | 8647.1239 | 17170 | 8522.8761 | 99% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 18026789001 | 559 | EX | INSTALL 6900' - 4" PMMP | 2021-01-12 | RICHMOND RD | B | 783479.7367 | 789465.56 | 5985.8233 | 1% | 7025 | 7098 | 111.2237
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 18026789100 | 560 | EX | RETIRE 600' - 3" PMMP | 2021-02-04 | RICHMOND RD | B | 218.671 | 70.37 | -148.301 | -68% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026794800 | 555 | EX | INSTALL 2200' OF 4"PMMP MAIN | 2019-03-20 | 316 JIM HUNT WY | B | 69179.2466 | 68775.48 | -403.7666 | -1% | 2200 | 2389 | 28.7884
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 18026796201 | 557 | EX | INSTALL 7600' - 2" PMMP | 2020-05-21 | COURT ST | B | 1236118.6701 | 1313128.04 | 77009.3699 | 6% | 7655 | 8114 | 161.8349
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 18026796300 | 558 | EX | RETIRE 5950' - BSLP | 2020-11-17 | COURT ST | B | 72.267 | 1297.62 | 1225.353 | 1,696% |  |  | 0
KY | KY - CENTRAL | 2629 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 18026797902 | 557 | EX | INSTALL 925'- 4" PMMP MAIN | 2020-08-07 | 8TH ST | B | 200349.0518 | 259233.12 | 58884.0682 | 29% | 1260 | 888 | 291.9292 | OVERRUN EXPLANATION: PAVING EXCEEDED THE ESTIMATE DUE TO HAVING TO MAKE ADD ITIONAL TIE-INS IN STATE RIGHT OF WAY THAT WERE NOT ANTICIPATED.
KY | KY - CENTRAL | 2629 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 18026798000 | 558 | EX | RETIRE 908' - BSLP MAIN | 2020-08-26 | 8TH ST | B | 155.0157 | 62.25 | -92.7657 | -60% |  |  | 0
KY | KY - CENTRAL | 2629 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 18026799501 | 559 | EX | INSTALL 4" PV | 2019-09-23 | LOCUST ST | B | 14476.0833 | 15223.31 | 747.2267 | 5% | 10 | 6 | 2537.2183
KY | KY - CENTRAL | 2629 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 18026799600 | 560 | EX | RETIRE 4" PV C3-09 | 2019-09-23 | LOCUST ST | B | 53.9767 | 0 | -53.9767 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 18026799700 | 559 | EX | INSTALL 6" PV | 2019-09-23 | LOCUST ST | B | 10736.1251 | 12249.1 | 1512.9749 | 14% | 10 | 6 | 2041.5167
KY | KY - CENTRAL | 2629 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 18026799800 | 560 | EX | RETIRE 6" PV C3-08 | 2019-09-23 | LOCUST ST | B | 53.9767 | 0 | -53.9767 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026820700 | 583 | EX | INST. FN 37 EXTRA LP OPP | 2019-06-08 | FORREST AV | F | 21708.8722 | 16312.92 | -5395.9522 | -25% | 50 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 6/8/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/26/2021 GCCC TICKET NOT REQUIRED ON 4/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026820800 | 584 | EX | RET. FN 37 FOR EXTRA LP OPP | 2019-06-08 | FORREST AV | F | 54.9718 | 228.05 | 173.0782 | 315% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 6/8/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/26/2021 GCCC TICKET NOT REQUIRED ON 4/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026820900 | 583 | EX | INST. FN 38 EXTRA LP OPP | 2020-08-28 | N WALL AL | F | 39188.1646 | 30427.64 | -8760.5246 | -22% | 55 |  | 0 | REGULATOR AND ER350 INSTALLED BY JAMES PASLEY ON 8/28/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/17/2021 GCCC TICKET NOT REQUIRED ON 5/17/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026821000 | 584 | EX | RET. FN 38 FOR EXTRA LP OPP | 2020-08-28 | N WALL AL | F | 53.6219 | 481.55 | 427.9281 | 798% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 8/28/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/17/2021 GCCC TICKET NOT REQUIRED ON 5/17/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026821100 | 583 | EX | INST. FN 40 EXTRA LP OPP | 2020-08-26 | S WALL AL | F | 39233.1646 | 28567.37 | -10665.7946 | -27% | 55 |  | 0 | REGULATOR AND ER350 INSTALLED BY JAMES PASLEY ON 8/26/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/18/2021 GCCC TICKET NOT REQUIRED ON 5/18/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026821200 | 584 | EX | RET. FN 40 FOR EXTRA LP OPP | 2020-08-26 | S WALL AL | F | 53.6219 | 735.05 | 681.4281 | 1,271% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 8/26/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/18/2021 GCCC TICKET NOT REQUIRED ON 5/18/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026821300 | 583 | EX | INST. FN 41 EXTRA LP OPP | 2020-07-27 | WALL AL | F | 24062.1646 | 29740.92 | 5678.7554 | 24% | 50 |  | 0 | REGULATOR INSTALLED BY JAMES PASLEY ON 7/27/2020 ER350 INSTALLED BY JAMES PASLEY ON 7/28/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/23/2021 GCCC TICKET NOT REQUIRED ON 4/23/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026821400 | 584 | EX | RET. FN 41 FOR EXTRA LP OPP | 2020-07-27 | WALL AL | F | 53.6219 | 1917.21 | 1863.5881 | 3,475% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEYON 7/27/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/23/2021 GCCC TICKET NOT REQUIRED ON 4/23/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026821500 | 583 | EX | INST. FN 42 EXTRA LP OPP | 2019-04-29 | ALLEY OFF MAIN ST | F | 21708.8722 | 65672.28 | 43963.4078 | 203% | 50 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 4/29/2019 ER350 INSTALLED ON 7/30/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/14/2021 GCCC TICKET NOT REQUIRED ON 4/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026821600 | 584 | EX | RET. FN 42 FOR EXTRA LP OPP | 2019-04-29 | ALLEY OFF MAIN ST | F | 54.9718 | 1229.75 | 1174.7782 | 2,137% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 4/29/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/14/2021 GCCC TICKET NOT REQUIRED ON 4/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026821700 | 583 | EX | INST. FN 43 EXTRA LP OPP | 2019-04-30 | MUTUAL AV | F | 21708.8722 | 26644.68 | 4935.8078 | 23% | 50 |  | 0 | CCC CALLED BY JPASLEY CLEARANCE TICKET# 13241 REGULATOR INSTALLED BY RYAN WILLIAMS ON 4/30/2019 ER350 INSTALLED ON 7/30/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/14/2021 GCCC TICKET NOT REQUIRED ON 4/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026821800 | 584 | EX | RET. FN 43 FOR EXTRA LP OPP | 2019-04-30 | MUTUAL AV | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 4/30/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/14/2021 GCCC TICKET NOT REQUIRED ON 4/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026821900 | 583 | EX | INST. FN 44 EXTRA LP OPP | 2019-05-01 | ALLEY OFF PARK AV | F | 21708.8722 | 18769.19 | -2939.6822 | -14% | 50 |  | 0 | CONTROL SHEET 007558 VOIDED INFO ENTERED ON CONTROR SHEET 007556 CCC# 14639 REGULATOR INSTALLED BY RYAN WILLIAMS ON 5/1/2019 ER350 INSTALLED ON 7/31/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/14/2021 GCCC TICKET NOT REQUIRED ON 4/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026822000 | 584 | EX | RET. FN 44 FOR EXTRA LP OPP | 2019-05-01 | ALLEY OFF PARK AV | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 5/1/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/14/2021 GCCC TICKET NOT REQUIRED ON 4/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026822100 | 583 | EX | INST. FN 45 EXTRA LP OPP | 2020-08-10 | ALLEY OF LINCOLN ST | F | 23886.1646 | 24405.96 | 519.7954 | 2% | 50 |  | 0 | REGULATOR AND ER350 INSTALLED BY WADE SHIMFESSEL ON 8/10/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/14/2021 GCCC TICKET NOT REQUIRED ON 4/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026822200 | 583 | EX | INST. FN 47 EXTRA LP OPP | 2019-05-07 | ALLEY | F | 21708.8722 | 23518.63 | 1809.7578 | 8% | 50 |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 6/7/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026822300 | 584 | EX | RET. FN 47 FOR EXTRA LP OPP | 2019-05-07 | ALLEY | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 6/7/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026822400 | 583 | EX | INST. FN 48 EXTRA LP OPP | 2019-05-07 | 3RD ST ALLEY | F | 21708.8722 | 22545.95 | 837.0778 | 4% | 50 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 5/7/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/26/2021 GCCC TICKET NOT REQUIRED ON 4/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS LP SYSTEM IN IRVINE HAS BEEN SEPERATED THIS IS NOW A SINGLE FEED STATION WITH NEW SYSTEM NUMBER 32049011 I&C HAS BEEN ADVISED THAT THEY WILL NEED TO CONVERT THIS TO A FULL TIME MONITORED ER350
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026822500 | 584 | EX | RET. FN 48 FOR EXTRA LP OPP | 2019-05-07 | 3RD ST ALLEY | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAIMS ON 5/7/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/26/2021 GCCC TICKET NOT REQUIRED ON 4/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026822600 | 583 | EX | INST. FN 161 EXTRA LP OPP | 2020-08-11 | MOY FOO ALLEY | F | 24062.1646 | 44631.35 | 20569.1854 | 85% | 50 |  | 0 | REGULATOR AND ER350 INSTALLED BY WADE SHIMFESSEL ON 8/11/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026822700 | 584 | EX | RET. FN 161 FOR EXTRA LP OPP | 2020-08-11 | MOY FOO ALLEY | F | 53.6219 | 735.05 | 681.4281 | 1,271% |  |  | 0 | REGULATOR REPLACED BY WADE SHIMFESSEL ON 8/11/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026822800 | 583 | EX | INST. FN 162 EXTRA LP OPP | 2019-05-20 | 5TH ST | F | 21708.8722 | 27758.39 | 6049.5178 | 28% | 50 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 5/20/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026822900 | 584 | EX | RET. FN 162 FOR EXTRA LP OPP | 2019-05-20 | 5TH ST | F | 54.9718 | 481.55 | 426.5782 | 776% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 5/20/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026823000 | 583 | EX | INST. FN 163 EXTRA LP OPP | 2020-11-04 | MAPLE ST | F | 23889.1646 | 51185.7 | 27296.5354 | 114% | 50 |  | 0 | REGULATOR AND ER350 INSTALLED BY WADE SHIMFESSEL ON 11/4/2020 PAPERWROK COMPLETED BY CYNTHIA FARIS ON 4/30/2021 GCCC TICKET NOT REQUIRED ON 4/30/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026823100 | 584 | EX | RET. FN 163 FOR EXTRA LP OPP | 2020-11-04 | MAPLE ST | F | 53.6219 | 481.55 | 427.9281 | 798% |  |  | 0 | REGULATOR REPLACED BY WADE SHIMFESSEL ON 11/4/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/30/2021 GCCC TICKET NOT REQUIRED ON 4/30/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026823200 | 583 | EX | INST. FN 164 EXTRA LP OPP | 2021-04-27 | 204 WILSON AV | F | 24062.1646 | 53697.68 | 29635.5154 | 123% | 50 |  | 0 | TICKET CALLED IN BY JPASLEY NOT ON SITE ROUNDED UP PARTS. GCCC# 19363 CCC# 19363 CCC# 20802 NOT ON SITE CCC# 21442 P2P WITH GAS CONTROL REGULATOR AND ER350 INSTALLED BY WADE SHIMFESSEL ON 4/27/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/21 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026823300 | 584 | EX | RET. FN 164 FOR EXTRA LP OPP | 2021-04-27 | 204 WILSON AV | F | 53.6219 | 228.05 | 174.4281 | 325% |  |  | 0 | REGULATOR REPLACED BY WADE SHIMFESSEL ON 4/27/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/21 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026823400 | 583 | EX | INST. FN 165 EXTRA LP OPP | 2019-07-26 | CARR AL | F | 46766.1646 | 24937.29 | -21828.8746 | -47% | 53 |  | 0 | CCC# 15036 REGULATOR INSTALLED BY RYAN WILLIAMS ON 7/26/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026823500 | 584 | EX | RET. FN 165 FOR EXTRA LP OPP | 2019-07-26 | CARR AL | F | 53.6219 | 854.77 | 801.1481 | 1,494% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 7/26/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026823600 | 583 | EX | INST. FN 182 EXTRA LP OPP | 2019-07-03 | S QUEEN ST | F | 43700.1646 | 23034.28 | -20665.8846 | -47% | 54 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 7/3/2019 ER350 INSTALLED BY WADE SHIMFESEL ON 6/30/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026823700 | 584 | EX | RET. FN 182 FOR EXTRA LP OPP | 2019-07-03 | S QUEEN ST | F | 53.6219 | 1500.56 | 1446.9381 | 2,698% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 7/3/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026823800 | 583 | EX | INST. FN 183 EXTRA LP OPP | 2019-05-03 | JOHNSON ST | F | 21708.8722 | 17019.94 | -4688.9322 | -22% | 50 |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 5/3/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 6/30/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026823900 | 584 | EX | RET. FN 183 FOR EXTRA LP OPP | 2019-05-03 | JOHNSON ST | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 5/3/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026824000 | 583 | EX | INST. FN 220 EXTRA LP OPP | 2019-05-01 | GRAVES ST | F | 21708.8722 | 19921.93 | -1786.9422 | -8% | 50 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 5/1/2019 ER350 INSTALLED ON 7/29/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/14/2021 GCCC TICKET NOT REQUIRED ON 4/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026824100 | 584 | EX | RET. FN 220 FOR EXTRA LP OPP | 2019-05-01 | GRAVES ST | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 5/1/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/14/2021 GCCC TICKET NOT REQUIRED ON 4/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026824200 | 583 | EX | INST. FN 221 EXTRA LP OPP | 2019-05-08 | CARHART AV | F | 21708.8722 | 16708.31 | -5000.5622 | -23% | 50 |  | 0 | 12 HRS FLAGGING PAID AS LABORERS STRIGHT TIME PER GREGORY PECK REGULATOR INSTALLED BY RYAN WILLIAMS ON 5/8/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026824300 | 584 | EX | RET. FN 221 FOR EXTRA LP OPP | 2019-05-08 | CARHART AV | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 5/8/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026824400 | 583 | EX | INST. FN 13986 EXTRA LP OPP | 2019-05-09 | RICHMOND AV | F | 21708.8722 | 19162.21 | -2546.6622 | -12% | 50 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 5/9/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 6/29/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026824500 | 584 | EX | RET. FN 13986 FOR EXTRA LP OPP | 2019-05-09 | RICHMOND AV | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 5/9/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026824600 | 583 | EX | INST. FN 232 EXTRA LP OPP | 2019-07-24 | HIGGINS ST | F | 21708.8722 | 15904.15 | -5804.7222 | -27% | 50 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 7/24/2019 ER350 INSTALLED BY CHRIS COX ON 7/6/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026824700 | 584 | EX | RET. FN 232 FOR EXTRA LP OPP | 2019-07-24 | HIGGINS ST | F | 54.9718 | 835.58 | 780.6082 | 1,420% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 7/24/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026824800 | 583 | EX | INST. FN 233 EXTRA LP OPP | 2019-07-16 | THOMAS ST | F | 21708.8722 | 20187.34 | -1521.5322 | -7% | 50 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 7/16/2019 ER350 INSTALLED BY CHRIS COX ON 7/6/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026824900 | 584 | EX | RET. FN 233 FOR EXTRA LP OPP | 2019-07-16 | THOMAS ST | F | 54.9718 | 714.32 | 659.3482 | 1,199% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 7/16/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026825800 | 583 | EX | INST. FN 13878 EXTRA LP OPP | 2020-07-21 | MAIN ST | F | 37874.1646 | 30583.49 | -7290.6746 | -19% | 52 |  | 0 | REGULATORS INSTALLED BY JAMES PASLEY ON 7/21/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/27/2021 GCCC TICKET NOT REQUIRED ON 7/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS ER350 NOT INSTALLED SETTING HAS EXISTING ERX
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026825900 | 584 | EX | RET. FN 13878 FOR EXTRA LP OPP | 2020-07-21 | MAIN ST | F | 53.6219 | 0 | -53.6219 | 100% |  |  | 0 | REGULATORS REPLACED BY JAMES PASLEY ON 7/21/20 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/27/21 GCCC TICKET NOT REQUIRED ON 7/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026826200 | 583 | EX | INST. FN 316 EXTRA LP OPP | 2019-07-19 | PLEASANT ST | F | 46766.1646 | 33895.41 | -12870.7546 | -28% | 53 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 7/19/2019 ER350 NOT INSTALLED STATION HAD EXISTING ERX PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026826300 | 584 | EX | RET. FN 316 FOR EXTRA LP OPP | 2019-07-19 | PLEASANT ST | F | 53.6219 | 3635.7 | 3582.0781 | 6,680% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 7/19/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026826400 | 583 | EX | INST. FN 317 EXTRA LP OPP | 2019-05-21 | SHORT ST | F | 21708.8722 | 22843.73 | 1134.8578 | 5% | 50 |  | 0 | JKEESEE 5-21-19 1524 INLET AND OUTLET VALVES ON / BYPASS OFF SENSING LINES ON REGULATOR INSTALLED BY JAMES KEESEE ON 5/21/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 7/1/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026826500 | 584 | EX | RET. FN 317 FOR EXTRA LP OPP | 2019-05-21 | SHORT ST | F | 54.9718 | 106.55 | 51.5782 | 94% |  |  | 0 | REGULATOR REPLACED BY JAMES KEESEE ON 5/21/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/28/2021 GCCC TICKET NOT REQUIRED ON 4/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026826600 | 583 | EX | INST. FN 357 EXTRA LP OPP | 2020-12-14 | S BURNS AV | F | 24062.1646 | 42518.46 | 18456.2954 | 77% | 50 |  | 0 | ESPARKS 12-14-20 REGULATOR INSTALLED BY WADE SHIMFESSEL ON 09/02/2020 REGULATOR REPLACED AND ER350 INSTALLED BY CHRIS COX ON 12/14/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/14/2021 GCCC TICKET NOT REQUIRED ON 4/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026826700 | 584 | EX | RET. FN 357 FOR EXTRA LP OPP | 2020-12-14 | S BURNS AV | F | 53.6219 | 0 | -53.6219 | 100% |  |  | 0 | REGULATOR REPLACED BY WADE SHIMFESSEL ON 09/02/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 04/14/2021 GCCC TICKET NOT REQUIRED ON 4/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026827200 | 583 | EX | INST. FN 661 EXTRA LP OPP | 2019-06-13 | BROADWAY ST | F | 21708.8722 | 16350.8 | -5358.0722 | -25% | 50 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 6/13/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/26/2021 GCCC TICKET NOT REQUIRED ON 4/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026827300 | 584 | EX | RET. FN 661 FOR EXTRA LP OPP | 2019-06-13 | BROADWAY ST | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 6/13/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/26/2021 GCCC TICKET NOT REQUIRED ON 4/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026827400 | 583 | EX | INST. FN 690 EXTRA LP OPP | 2020-09-10 | INDIAN MOUND DR | F | 42364.1646 | 45678.19 | 3314.0254 | 8% | 55 |  | 0 | REGULATORS INSTALLED BY WADE SHIMFESSEL ON 9/10/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/14/2021 GCCC TICKET NOT REQUIRED ON 7/14/2021 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026827500 | 583 | EX | INST. FN 691 EXTRA LP OPP | 2019-05-22 | ROGERS AV | F | 21708.8722 | 26998.54 | 5289.6678 | 24% | 50 |  | 0 | JKEESEE 5-22-19 1330 INLET AND OUTLET VALVES ON / BYPASS OFF SENSE LINES ON REGULATOR INSTALLED BY JAMES KEESEE ON 5/22/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 6/29/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE OCMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026827600 | 584 | EX | RET. FN 691 FOR EXTRA LP OPP | 2019-05-22 | ROGERS AV | F | 54.9718 | 481.55 | 426.5782 | 776% |  |  | 0 | REGULATOR REPLACED BY JAMES KEESEE ON 5/22/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026827700 | 583 | EX | INST. FN 693 EXTRA LP OPP | 2019-05-06 | WHITE AV | F | 21708.8722 | 22087.6 | 378.7278 | 2% | 50 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 5/6/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 6/30/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/2021 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026827800 | 584 | EX | RET. FN 693 FOR EXTRA LP OPP | 2019-05-06 | WHITE AV | F | 54.9718 | 481.55 | 426.5782 | 776% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 5/6/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/27/2021 GCCC TICKET NOT REQUIRED ON 4/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026827900 | 583 | EX | INST. FN 694 EXTRA LP OPP | 2019-05-04 | E LOCUST ST | F | 21708.8722 | 19425.28 | -2283.5922 | -11% | 50 |  | 0 | PAID STRIGHT TIME INSTEAD OF TIME AND 1/2 PAID MAKEUP 4 HRS 98-150 AND 4 HRS 98-130 .MAKE UP UNDER PAY FOR SATURDAY 05/04/19 ADVISED GREGORY PECK REGULATOR INSTALLED BY RYAN WILLIAMS ON 5/4/2019 ER350 NOT INSTALLED STATION HAS EXISTING ERX PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/29/2021 GCCC TICKET NOT RQUIRED ON 4/29/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026828000 | 584 | EX | RET. FN 694 FOR EXTRA LP OPP | 2019-05-04 | E LOCUST ST | F | 54.9718 | 741.15 | 686.1782 | 1,248% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 5/4/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/29/2021 GCCC TICKET NOT REQUIRED ON 4/29/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026828100 | 583 | EX | INST. FN 733 EXTRA LP OPP | 2020-09-29 | EDGEMONT DR | F | 23795.1646 | 29798.61 | 6003.4454 | 25% | 50 |  | 0 | ESPARKS 12-15-20 CCC #14454 REGULATOR INSTALLED BY WADE SHIMFESSEL ON 9/29/2020 ER350 INSTALLED BY CHRIS COX ON 12/15/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/14/2021 GCCC TICKET NOT REQUIRED ON 4/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026828200 | 584 | EX | RET. FN 733 FOR EXTRA LP OPP | 2020-09-29 | EDGEMONT DR | F | 53.6219 | 4355.07 | 4301.4481 | 8,022% |  |  | 0 | REGULATOR REPLACED BY WADE SHIMFESSEL ON 9/29/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/15/2021 GCCC TICKET NOT REQUIRED ON 4/15/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026828300 | 583 | EX | INST. FN 854 EXTRA LP OPP | 2020-09-17 | W LEXINGTON AV | F | 42364.1646 | 44381.28 | 2017.1154 | 5% | 55 |  | 0 | ACTUAL DATE 04/14/2020 04/16/2020 ENTERED INTO COMPUTER BY MISTAKE ON CONTROL SHEET 122348 ON CONTROL SHEET 122349 ACTUAL DATE 04/15/2020 04/14/2020 ENTERED INTO COMPUTER BY MISTAKE REGULATOR AND ER350 INSTALLED BY WADE SHIMFESSEL ON 9/17/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/14/2021 GCCC TICKET NOT REQUIRED ON 4/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026828600 | 583 | EX | INST. FN 21193 EXTRA LP OPP | 2019-05-02 | 620 BOONE AV | F | 21708.8722 | 20700.9 | -1007.9722 | -5% | 50 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 5/2/2019 ER350 INSTALLED BY WADE SHIMFESSEL ON 8/5/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/26/2021 GCCC TICKET NOT REQUIRED ON 4/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS GASKET STRAINER NOT REQUIRED SETTING HAS T-STRAINER INSTALLED
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026828700 | 584 | EX | RET. FN 21193 FOR EXTRA LP OPP | 2019-05-02 | 620 BOONE AV | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 5/2/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/26/2021 GCCC TICKET NOT REQUIRED ON 4/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026828800 | 583 | EX | INST. FN 21194 EXTRA LP OPP | 2019-05-02 | 620 BOONE AV | F | 21708.8722 | 15003.18 | -6705.6922 | -31% | 50 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 5/2/2019 GASKET STRAINER NOT REQUIRED T-STAINER INSTALLED IN SETTING CRY-IN ER350 INSTALLED ON RUN 1 GCCC TICKET NOT REQUIRED ON 4/26/2021 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026828900 | 584 | EX | RET. FN 21194 FOR EXTRA LP OPP | 2019-05-02 | 620 BOONE AV | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 5/2/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/26/2021 GCCC TICKET NOT REQUIRED ON 4/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026840800 | 584 | EX | RET. FN 45 FOR EXTRA LP OPP | 2020-08-10 | ALLEY OF LINCOLN ST | F | 53.6219 | 0 | -53.6219 | 100% |  |  | 0 | REGULATOR REPLACED BY WADE SHIMFESSEL ON 8/10/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/14/2021 GCCC TICKET NOT REQUIRED ON 4/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026840900 | 584 | EX | RET. FN 690 FOR EXTRA LP OPP | 2020-09-10 | INDIAN MOUND DR | F | 53.6219 | 1104.58 | 1050.9581 | 1,960% |  |  | 0 | REGULATORS REPLACED BY WADE SHIMFESSEL ON 9/10/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/14/2021 GCCC TICKET NOT REQUIRED ON 7/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026841000 | 584 | EX | RET. FN 854 FOR EXTRA LP OPP | 2020-09-17 | W LEXINGTON AV | F | 53.6219 | 481.55 | 427.9281 | 798% |  |  | 0 | REGULATOR REPLACED BY WADE SHIMFESSEL ON 9/17/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/14/2021 GCCC TICKET NOT REQUIRED ON 4/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 18026847900 | 575 | EX | ACQUIRE LAND FOR USS | 2022-04-19 | ALLEY OF LINCOLN ST | F | 5291 | 7723.99 | 2432.99 | 46% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026848800 | 587 | EX | INSTALL MI WIRELESS UNIT | 2019-01-08 | 1200 ROLLING HILLS LN | F | 10197.5731 | 10698.17 | 500.5969 | 5% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026848900 | 588 | EX | RETIRE EME UNIT | 2019-01-08 | 1200 ROLLING HILLS LN | F | 70.5114 | 0 | -70.5114 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026849000 | 587 | EX | INSTALL MI WIRELESS UNIT | 2019-01-07 | 500 GAWTHROP DR | F | 6384.5731 | 7324.71 | 940.1369 | 15% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026849100 | 588 | EX | RETIRE EME UNIT | 2019-01-07 | 500 GAWTHROP DR | F | 67.5358 | 0 | -67.5358 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026849400 | 587 | EX | INSTALL MI WIRELESS EFC | 2020-04-24 | 1308 NEW LAIR RD | F | 10338.964 | 8318.67 | -2020.294 | -20% |  |  | 0 | SOME MATERIAL BACK ORDERED FOR ALMOST 1 YEAR THEN PAPERWORK DID NOT GET TURNED IN FOR COMPLETION
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026849700 | 555 | EX | INSTALL 825' OF 2"PMMP MAIN | 2019-10-11 | 160 CODELLA DR LT | B | 24468.6987 | 43887.53 | 19418.8313 | 79% | 825 | 990 | 44.3308
KY | KY - CENTRAL | 2629 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026851300 | 909 | EX | UPGRADE COMM EQUIPMENT | 2019-02-15 | N MAPLE ST | F | 8776.5399 | 5919.36 | -2857.1799 | -33% |  |  | 0
KY | KY - CENTRAL | 2629 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026852300 | 909 | EX | UPGRADE COMM EQUIPMENT | 2019-02-11 | STATE RT 89 | F | 8776.5399 | 2154.22 | -6622.3199 | -75% |  |  | 0 | CELL MODEM UPGRADED TO RV50 BY ACP
KY | KY - CENTRAL | 2629 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026852400 | 910 | EX | RETIRE 2G/3G EQUIPMENT | 2019-02-11 | STATE RT 89 | F | 140.9437 | 0 | -140.9437 | 100% |  |  | 0 | CELL MODEM UPGRADED TO RV50
KY | KY - CENTRAL | 2629 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026853000 | 909 | EX | UPGRADE COMM EQUIPMENT | 2019-02-07 | STEPSTONE RD | F | 8776.5399 | 2449.26 | -6327.2799 | -72% |  |  | 0 | CELL MODEM UPGRADED TO RV50 BY ACP
KY | KY - CENTRAL | 2629 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026853100 | 910 | EX | RETIRE 2G/3G EQUIPMENT | 2019-02-07 | STEPSTONE RD | F | 140.9437 | 0 | -140.9437 | 100% |  |  | 0 | MODEM UPGRADED TO RV50 BY ACP
KY | KY - CENTRAL | 2629 | U127466 | Sparks,Cynthia Joy | Miller,Gary | Belle,Eric | 19026855100 | 555 | EX | INSTALL 50' - 2" PMMP | 2019-01-16 | 320 VANOVER WY | A | 7788.2638 | 7816.21 | 27.9462 | 0% | 50 | 40 | 195.4052 | INSTALLED 40' OF 2''
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026855600 | 557 | EX | INSTALL 4,275' OF 2"/4" PMMP | 2020-06-17 | 114 STERLING AV | B | 444260.5602 | 654541.34 | 210280.7798 | 47% | 4275 | 4245 | 154.1911 | OVERRUN EXPLANATION: PROJECT TOOK 544 MORE HOURS THAN LABOR ESTIMATING TOOL SUGGESTED RESULTING AN A $31K INCREASE IN LABOR. ALSO THE PAVING ESTIMATE W AS $183,510 BUT THE ACTUAL HARD SURFACE REPAIRS WAS $293,070. THESE INCREAS ES CAUSED A COMMENSURATE INCREASE IN THE OVERHEARDS.
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026855700 | 558 | EX | ABANDON 4,273 OF 3"/4"BSLP MN | 2020-08-20 | 114 STERLING AV | B | 171.8009 | 0 | -171.8009 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026855800 | 2000 | EX | INVESTIGATE EASEMENT/LAND RGHT | 2020-02-05 | STERLING AV | A | 6891 | 0 | -6891 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U131982 |  |  |  | 19026859300 | 909 | EX | INSTALL I&C EQUIPMENT | 2019-05-09 | RICHMOND AV | F | 16324.2503 | 12104.79 | -4219.4603 | -26% |  |  | 0 | WSHIMFE 05-02-2019 PAPERWORK DID NOT GET TURNED IN FOR COMPLETION
KY | KY - CENTRAL | 2629 | U131982 |  |  |  | 19026859400 | 910 | EX | RETIRE I&C EQUIP | 2019-05-09 | RICHMOND AV | F | 83.2326 | 0 | -83.2326 | 100% |  |  | 0 | PAPERWORK DID NOT GET TURNED IN FOR COMPLETION
KY | KY - CENTRAL | 2629 | U131982 |  |  |  | 19026859500 | 909 | EX | INSTALL I&C EQUIPMENT | 2019-05-21 | EWINGTON RD | F | 16448.1957 | 8180.76 | -8267.4357 | -50% |  |  | 0 | DID NOT RECEIVE PAPERWORK TO COMPLETE JOB
KY | KY - CENTRAL | 2629 | U131982 |  |  |  | 19026859600 | 910 | EX | RETIRE I&C EQUIPMENT | 2019-05-21 | EWINGTON RD | F | 83.2326 | 0 | -83.2326 | 100% |  |  | 0 | PAPERWORK DID NOT GET TURNED IN FOR COMPLETION
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026860701 | 559 | EX | INSTALL INLET/OUTLET PIPING | 2019-08-28 | PAULA DR | B | 153225.0225 | 165360.17 | 12135.1475 | 8% | 45 | 40 | 4134.0042
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026860800 | 560 | EX | RETIRE INLET & OUTLET PIPING | 2019-08-28 | PAULA DR | B | 74.7467 | 0 | -74.7467 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026860900 | 583 | EX | RELOCATE REG STATION #1684 | 2019-09-03 | PAULA DR | F | 24955.7243 | 24264.55 | -691.1743 | -3% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026861000 | 584 | EX | RETIRE PIT REGULATOR STATION | 2019-09-03 | PAULA DR | F | 83.2326 | 0 | -83.2326 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U131982 |  |  |  | 19026861100 | 573 | EX | INSTALL HEATER | 2022-06-13 | LEVEE RD | F | 3045.0298 | 2372.11 | -672.9198 | -22% |  |  | 0 | INSTALLED CAT HEATER
KY | KY - CENTRAL | 2629 | U131982 |  |  |  | 19026861800 | 573 | EX | INSTALL HEATER | 2019-12-06 | RICHMOND AV | F | 4140.0298 | 4650.58 | 510.5502 | 12% |  |  | 0 | CAT HEATER INSTALL
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 19026866200 | 561 | EX | INSTALL TWO 2" SS | 2019-08-12 | 605 SUMMIT DR REAR | B | 27449.4916 | 41712.88 | 14263.3884 | 52% |  |  | 0
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 19026866300 | 562 | EX | RETIRE 56'-2" CSMP | 2019-08-12 | 605 SUMMIT DR REAR | B | 72.7501 | 149.73 | 76.9799 | 106% |  |  | 0
KY | KY - CENTRAL | 2629 | U131982 |  |  |  | 19026866500 | 583 | EX | INSTALL VRG CONTROLLER | 2019-09-20 | EARLY DR | F | 15490.7518 | 26945.7 | 11454.9482 | 74% |  |  | 0 | REPLACED CONTROLLERS AND RELOCATED SUPPLY LINES AND TAPS
KY | KY - CENTRAL | 2629 | U131982 |  |  |  | 19026866600 | 584 | EX | RETIRE EXISTING CONTROLLER | 2019-09-20 | EARLY DR | F | 64.4897 | 621.64 | 557.1503 | 864% |  |  | 0 | REPLACED CONTROLLERS
KY | KY - CENTRAL | 2629 | U131982 |  |  |  | 19026866900 | 583 | EX | INSTALL VRG CONTROLLER | 2020-09-26 | 555 ROLLING HILLS DR | F | 15490.7518 | 30464.96 | 14974.2082 | 97% |  |  | 0 | JOB DELAYED DUE TO MANPOWER AND COMPLIANCE WORK
KY | KY - CENTRAL | 2629 | U131982 |  |  |  | 19026867000 | 584 | EX | RETIRE CURRENT CONTROLLERS | 2020-09-26 | 555 ROLLING HILLS DR | F | 64.4897 | 113.05 | 48.5603 | 75% |  |  | 0 | JOB DELAYED DUE TO MANPOWER AND COMPLIANCE WORK
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 19026868801 | 559 | EX | INSTALL 393'-4" CS/PMMP | 2019-12-03 | 1014 US HIGHWAY 62 | B | 88186.6195 | 98423.03 | 10236.4105 | 12% | 393 | 380 | 259.008
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 19026868900 | 560 | EX | RETIRE 276'-4" CSMP | 2019-12-03 | 1014 US HIGHWAY 62 | B | 76.2543 | 449.71 | 373.4557 | 490% |  |  | 0
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 19026869000 | 559 | EX | INSTALL 575'-2" PMMP | 2020-09-04 | 315 WEBSTER AV | B | 51230.9421 | 39642.81 | -11588.1321 | -23% | 525 | 669 | 59.2568 | PROJECT ID INCLUDES THIS AND 17-0267437-00. STEVE CANOY 09-10-2020
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026869100 | 555 | EX | INSTALL 150' - 4" PMMP | 2019-09-04 | 703 CYPRESS ST | B | 30279.2551 | 58200.14 | 27920.8849 | 92% | 150 | 197 | 295.4322 | ATTEMPTED TO REVISE JO, UNABLE DUE TO UNPAID INVOICES, EXTRA SIDEWALK AND ASPHALT RESTORATION REQUIRED, NON-STANDARD SERVICE LINE FOUND TTOY 9/6/19 MISSED COMMIT DATE DUE HOLIDAY WEEKEND AND RAIN DAY . ALSO HAD TO WORK EXTR A SERVICE LINE REPLACEMENT AT 706 CYPRESS ST
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026871100 | 559 | EX | INSTALL 40' OF 4"PMMP MAIN | 2019-05-16 | WINDSOR AV | A | 6260.678 | 5126.15 | -1134.528 | -18% | 40 | 38 | 134.8987 | SEE PAPER COPIES IN PACKET PIPE TEST WAS PERFORMED ON SITE AND WAS ACCEPTABLE/ 90# FOR ONE HOUR AND THE TIE IN JOINTS WERE SOAP TESTED FOR 5 MINUTES AT OPERATING PRESSURE SEE PAPER PACKET
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026871200 | 560 | EX | RETIRE 40' OF 4"PAP MAIN | 2019-05-16 | WINDSOR AV | A | 68.4012 | 288.73 | 220.3288 | 322% |  |  | 0 | SEE PAPER PACKET
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 19026872200 | 559 | EX | INSTALL 225' 2" PMMP | 2019-10-29 | 7915 LEVEE RD | B | 65634.421 | 66538.37 | 903.949 | 1% | 225 | 177 | 375.923
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 19026872300 | 560 | EX | RETIRE 200' 2" MAIN | 2019-10-29 | 7915 LEVEE RD | B | 74.1455 | 658.61 | 584.4645 | 788% |  |  | 0
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 19026872400 | 2000 | EX | INVESTIGATE LAND | 2019-09-06 | 7915 LEVEE RD | B | 3411 | 0 | -3411 | 100% |  |  | 0 | 9/6/19: TAYLOR CLARK SECURED EASEMENTS OFF OF JOHNSON AND MILLER PROPERTIES AND ACQUIRED HWY PERMIT FROM KDOT (BKSLONE)
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026875700 | 909 | EX | UPGRADE COMM EQUIPMENT | 2020-04-21 | E LOCUST ST | F | 7929.1918 | 1472.41 | -6456.7818 | -81% |  |  | 0 | EQUIPMENT INSTALLED BY NOLL DAVIS AND ACP PAPERWORK DID NOT GET TURNED IN FOR COMPLETION
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026875800 | 910 | EX | RETIRE ERX UNIT | 2020-04-21 | E LOCUST ST | F | 68.1449 | 0 | -68.1449 | 100% |  |  | 0 | EQUIPMENT REPLACED BY ACP AND NOLL DAVIS PAPERWORK NOT TURNED IN FOR COMPLETION
KY | KY - CENTRAL | 2629 | U131982 |  |  |  | 19026876000 | 562 | EX | ABAN 360' 2" PMMP | 2019-05-15 | 17 TIPTON TRAILER PK | A | 2376.3418 | 1968.98 | -407.3618 | -17% |  |  | 0 | SEE PAPER PACKET FOR DETAILS
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026876900 | 2000 | EX | CONFLICT ASSESSMENT | 2019-11-13 | 125 WHEAT DR | B | 16107 | 0 | -16107 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026877000 | 561 | EX | INSTALL 623' OF 4"CSHP MAIN | 2019-10-15 | 125 WHEAT DR | B | 125819.9196 | 114659.91 | -11160.0096 | -9% | 640 | 612 | 187.3528
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026877100 | 562 | EX | RETIRE 732' OF 4"CSHP MAIN | 2019-10-15 | 125 WHEAT DR | B | 69.5189 | 0 | -69.5189 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026877200 | 555 | EX | INSTALL 4,500' - 6" PMMP | 2019-09-03 | 4481 ROCKWELL RD | B | 317849.8474 | 291652.33 | -26197.5174 | -8% | 4500 | 4444 | 65.6283
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 19026877700 | 561 | EX | INSTALL 154'-2" PM/CSMP | 2019-08-21 | 275 ECHO DR REAR | B | 49694.9832 | 39253.55 | -10441.4332 | -21% | 154 | 153 | 256.5592
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 19026877800 | 562 | EX | RETIRE 136'-3" CSMP | 2019-08-21 | 275 ECHO DR REAR | B | 72.7501 | 411.89 | 339.1399 | 466% |  |  | 0
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 19026878700 | 575 | EX | ACQUIRE ESMT ON HOLT, ET AL | 2020-03-06 | 3315 COLBY RD | F | 56500 | 41783.72 | -14716.28 | -26% |  |  | 0 | COMPLETED BY CHRIS DAVIS W/TEAM FISHEL WHO ACQUIRED PERMANENT ESMTS OVER COLBY FARM, HOLT, ET AL, AND COYLE PROPERTIES (BKSLONE)
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026881900 | 2000 | EX | ACQUIRE NEW EASEMENT | 2021-03-23 | 3831 COLBY RD | B | 20000 | 0 | -20000 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026882600 | 2000 | EX | INVESTIGATE RAILROAD CROSSINGS | 2020-01-06 | FITHIAN ST | B | 10815 | 0 | -10815 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026882800 | 560 | EX | ABANDON 4500' - 2" PMMP | 2019-09-03 | ROCKWELL RD | B | 58.6033 | 0 | -58.6033 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U131983 |  |  |  | 19026885300 | 557 | EX | INSTALL 340' OF 2"PMLP | 2019-08-01 | S MAYSVILLE ST | A | 10016.8061 | 15057.16 | 5040.3539 | 50% | 329 | 259 | 58.1358
KY | KY - CENTRAL | 2629 | U131983 |  |  |  | 19026885500 | 558 | EX | RETIRE 329' OF 2"BSLP MAIN | 2019-08-01 | S MAYSVILLE ST | A | 75.6877 | 372.05 | 296.3623 | 392% |  |  | 0 | SEE PAPER COPIES FOR REMARKS
KY | KY - CENTRAL | 2629 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026886100 | 559 | EX | INSTALL 10' 4" PMLP | 2019-10-30 | 25 HAMPTON AV | B | 38744.9642 | 25555.38 | -13189.5842 | -34% | 10 | 12 | 2129.615
KY | KY - CENTRAL | 2629 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026886200 | 560 | EX | INSTALL 10' 4" PMLP | 2019-10-30 | 25 HAMPTON AV | B | 57.9057 | 0 | -57.9057 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026886300 | 909 | EX | REPLACE TRANSMITTERS | 2019-10-04 | STATE RT 89 | F | 26150.4879 | 17321.28 | -8829.2079 | -34% |  |  | 0 | TRANSMITTERS INSTALLED BY NOLL DAVIS AND ACP
KY | KY - CENTRAL | 2629 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026886400 | 910 | EX | REPLACE TRANSMITTERS | 2019-10-04 | STATE RT 89 | F | 60.1455 | 3176.19 | 3116.0445 | 5,181% |  |  | 0 | TRANSMITTERS REPALCED BY NOLL DAVIS AND ACP
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026886700 | 565 | EX | INSTALL 6" SERVICE | 2019-09-21 | 4481 ROCKWELL RD | B | 10366.6518 | 13514.15 | 3147.4982 | 30% | 120 |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026888700 | 587 | EX | INSTALL NEW GMB SETTING | 2020-10-28 | 125 WHEAT DR | F | 83475.5624 | 64525.44 | -18950.1224 | -23% |  |  | 0 | TAPED AND PIPE DOPED FITTINGS TO BE READY FOR INSTALL. WAITING ON CUSTOMER TO INSTALL HOUSE LINE
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026888800 | 563 | EX | INSTALL 125' OF 4"CSHP S/L | 2020-09-17 | 125< WHEAT DR NEW BLD | B | 46341.2251 | 63855.35 | 17514.1249 | 38% | 205 |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026888900 | 555 | EX | INSTALL 810' OF 8"CSHP MAIN | 2020-10-07 | 125< WHEAT DR NEW BLD | B | 389698.1154 | 265110.17 | -124587.9454 | -32% | 5 | 806 | 328.9208 | TWALKER/KY 03-22-21: LEVEL 2 VARIANCE FORM ADDED TO WMS.DOCS FOR JOB ORDER UNDER RUN EXPLANATION, CKY WAS ABLE TO OPEN CUT 1/2 THE PROJECT INSTEAD OF PLANNED DIRECT ROCK BORE THE IS LOWER CONTRACT COST AND COMPANY LABOR.
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026890200 | 557 | EX | INSTALL 5' - 2" PMMP | 2019-08-09 | VILLAGE CT | A | 3857.6547 | 2315.86 | -1541.7947 | -40% | 5 | 6 | 385.9767
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026890300 | 558 | EX | RETIRE 5' - 2" PMMP | 2019-08-09 | VILLAGE CT | A | 1011.678 | 0 | -1011.678 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026892500 | 577 | EX | INSTALL NEW CHAIN LINK FENCE | 2019-09-30 | PAULA DR | F | 6787.7217 | 9123.55 | 2335.8283 | 34% |  |  | 0 | M&R TECH THAT WAS ON SITE WITH FENCE CREW DID NOT TURN IN INFORMATION AND IS NO LONGER IN THE DEPARTMENT
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026893400 | 557 | EX | INSTALL 1' - 2" PMMP | 2019-08-22 | 1075 VINE ST | A | 12063.6947 | 2877.95 | -9185.7447 | -76% | 2 | 6 | 479.6583
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026893500 | 558 | EX | RETIRE 1' - 2" PMMP | 2019-08-22 | 1075 VINE ST | A | 188.6071 | 8380.85 | 8192.2429 | 4,344% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026894500 | 557 | EX | INSTALL 3' - 3" PMMP | 2019-09-03 | WINCHESTER PZ | A | 8920.8573 | 12316.08 | 3395.2227 | 38% | 3 | 4 | 3079.02 | ALL WORK AND TIME CHARGED TO JOB 19-6806841-00 WHICH WAS CHARGED TO CAPITOL JOB 19-0268945-00
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026894600 | 558 | EX | RETIRE 3' - 3" PMP | 2019-09-03 | WINCHESTER PZ | A | 119.1203 | 0 | -119.1203 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026897801 | 557 | EX | INSTALL 12,500' - 2"/4" PMMP | 2020-04-13 | 2ND ST | B | 2200144.6236 | 2255068.39 | 54923.7664 | 2% | 12500 | 12387 | 182.0512
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026897900 | 558 | EX | RETIRE 12,703' - CI/BS/CS/P LP | 2020-11-05 | 2ND ST | B | 359.3348 | 0 | -359.3348 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026898000 | 557 | EX | INSTALL 3,350' - 2" PMMP | 2020-10-06 | BANK ST | B | 299913.4411 | 324941.46 | 25028.0189 | 8% | 3350 | 4182 | 77.7
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026898100 | 558 | EX | RETIRE 3,200' - 4" BSLP | 2020-11-06 | BANK ST | B | 72.267 | 597.56 | 525.293 | 727% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026900400 | 557 | EX | INSTALL 5' - 2" PMMP D096803 | 2019-10-01 | WOODSPOINT DR | A | 8024.1801 | 12194.13 | 4169.9499 | 52% | 5 | 5 | 2438.826
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026900500 | 558 | EX | RETIRE 5' - 2" PMP D096803 | 2019-10-01 | WOODSPOINT DR | A | 114.6475 | 0 | -114.6475 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 19026901800 | 2000 | EX | US 460 ROADWAY IMPROVEMENTS | 2020-11-18 | US 460 & PARIS BYPASS |  | 12346 | 0 | -12346 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026902500 | 2000 | EX | ACQUIRE EASEMENT CREEK XING | 2021-03-18 | BROOKS ST | B | 5335 | 0 | -5335 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 19026903000 | 909 | EX | INSTALL ELECTRONIC EQUIP | 2019-10-04 | STATE RT 89 | F | 6852.6923 | 4765.04 | -2087.6523 | -30% |  |  | 0 | WORK COMPLETED BY ACP
KY | KY - CENTRAL | 2629 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 19026903300 | 909 | EX | INSTALL ELECTRONIC EQUIP | 2019-10-01 | STEPSTONE RD | F | 6852.6923 | 4765.04 | -2087.6523 | -30% |  |  | 0 | EQUIPMENT INSTALLED BY ACP
KY | KY - CENTRAL | 2629 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 19026903400 | 910 | EX | RETIRE ELECTRONIC EQUIP | 2019-10-01 | STEPSTONE RD | F | 76.3408 | 0 | -76.3408 | 100% |  |  | 0 | EQUIPMENT REPLACED BY ACP
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026904300 | 2000 | EX | INVESTIGATE POTENTIAL CONFLICT | 2020-11-23 | MAIN ST | B | 29172 | 0 | -29172 | 100% |  |  | 0 | PS&I CREATED FOR LARGE PROJECT, PROJECT HAS SINCE BEEN SPLIT INTO 2 PROJECTS AND ARE TAKING PLACE IN DIFFERENT YEARS, 25% OF THIS PS&I HAS BEEN CHARGED TO PS&I FOR 2ND PROJECT DUE TO EARLY SPENDING INVOLVING BOTH PROJECTS TTOY 11/23/2020
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026907900 | 2000 | EX | OBTAIN ADDITIONAL LAND RIGHTS | 2023-08-03 | EARLY DR |  | 5472 | 0 | -5472 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026909300 | 2000 | EX | LAND EASEMENT AND RESEARCH | 2020-06-24 | 125< WHEAT DR NEW BLD | B | 19067 | 0 | -19067 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026911800 | 555 | EX | INSTALL 3,000' - 2"/4" PMMP | 2020-04-09 | FRONTIER WY | B | 99658.7961 | 61292.18 | -38366.6161 | -38% | 3370 | 1649 | 37.1693 | GAS ON MAIN:11:03 AM - 04/08/2020 PAID MISC DOLLARS & CENTS FOR PORTAPOTTY 05/27/2020 CONTROL# 118352 $107.39 UNDERRUN EXPLANATION: ORIGINAL ESTIMATE FOR 3,000' OF 2" PMMP, ACTUAL INSTALL FOOTAGE 1,600' - 2" PMMP, DEVELOPMENT WAS NOT READY FOR ALL OF PLANNED FOOTAGE, PROJECT COST UNDERRUN BY 40% WHICH IS EQUIVALENT TO INSTALLED MAIN UDERRUN TTOY 9/21/2020
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026913900 | 559 | EX | INSTALL 20' - 4" CSHP | 2021-02-24 | 101 US 52 | B | 45390.8034 | 82645.85 | 37255.0466 | 82% | 25 | 18 | 4591.4361 | COULD NOT REVISE DUE TO UNFULLFILLED PURCHASE ORDERS, NEEDED REVISION DUE TO EXTRA MATERIAL, INCREASE CONTRACT LABOR REQUIRED, EXTRA COMPANY LABOR, EXTRA TRUCK COSTS, AND EXTRA SEGA TTOY 3/18/2021
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026914000 | 560 | EX | RETIRE 10' - 3" CSHP | 2021-02-24 | 101 US 52 | B | 114.5339 | 695.55 | 581.0161 | 507% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026914500 | 563 | EX | INSTALL 225' - 4" PMIP | 2020-09-18 | 2101 OLD BOONESBORO RD | B | 19524.1963 | 19603.67 | 79.4737 | 0% | 225 |  | 0
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 19026914600 | 2000 | EX | ASSESS ESMT REQ'S FOR NEW HTR | 2020-10-16 | 605 ROLLING HILLS LN |  | 38471.2001 | 0 | -38471.2001 | 100% |  |  | 0 | 18CT20: EXECUTED BUT CREATED A NEW PS&I IN ITS PLACE (20-0269820-00). THIS IS TO ALLOW FOR CHARGING OFF 40% OF ACCUMULATED CHARGES TO (583) 19-0269147-00 AND THE REMAINDER WILL CARRY FORWARD ON 20-0269820-00 BKSLONE
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 19026914700 | 583 | EX | INSTALL NEW CWT HEATER | 2020-09-30 | 605 ROLLING HILLS LN | F | 297220.7055 | 138206.36 | -159014.3455 | -54% | 30 |  | 0 | JOB WAS ON HOLD DUE TO COVID AND WEATHER 22MAR21: UNDER-RUN EXPLANATION: THE GREATEST CONTRIBUTOR TO THE UNDERRUN CAME FROM AN APPARENT DISCREPANCY IN ESTIMATED MATERIAL COSTS BETWEEN WHAT WMS IS SHOWING ($183,970) VS THE CORRECT ESTIMATED MATERIAL COST ($93,235) AS SHOWN ON THE JO APPROVAL COPY IN WMS DOCS, RESULTING IN A NET DIFFERENCE OF -$90,735. THE BALANCE OF THE OVER-RUN IS CONTRIBUTED TO: 1) FISHEL'S ACTUAL CONTRACT BEING ABOUT $26K LESS THAN ESTIMATED BECAUSE THE MAJORITY OF THEIR TIME ENDED UP BEING CHARGED TO THE RELATED (555) 20-0269491-00, 2) $20K IN CONTINGENCY FUNDS THAT WERE NOT NEEDED, 3) $11K IN REDUCED OH'S, AND 4) $10K IN R/W COSTS THAT WAS ESTIMATED UNDER "OTHER" TO COVER A PORITON OF PSI CHARGES, HOWEVER, ENDED UP BEING CAPTURED UNDER CONTRACT LABOR.
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 19026914800 | 584 | EX | RETIRE EXIST WATER BATH HTR | 2020-09-11 | 605 ROLLING HILLS LN | F | 9879.2311 | 6755.35 | -3123.8811 | -32% |  |  | 0 | JOB DELAYED DUE TO COVID AND WEATHER
KY | KY - CENTRAL | 2629 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 20026918201 | 909 | EX | INSTALL ELECTRONICS | 2022-09-27 | EARLY DR | F | 114999.9064 | 199238.05 | 84238.1436 | 73% |  |  | 0 | CCC#17216 CCC# 19029 STATION RTU UP GRADE JPASLEY 9-27-22
KY | KY - CENTRAL | 2629 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 20026921200 | 555 | EX | INSTALL 150' - 4" PMMP | 2020-08-27 | 161 CROSS CREEK DR | B | 12877.4661 | 47105.95 | 34228.4839 | 266% | 150 | 276 | 170.6737 | OVERRUN EXPLNATION: PROJECT WAS INITIALLY ESTIMATED UNDER A DATED CONTRACT. IT WAS ESTIMATED HOURLY. HOWEVER, BY THE TIME THE PROJECT CAME TO CONSTRUCT ION THE SCOPE HAD CREEPED TO OVER THE AMOUNT ALLOWED FOR HOURLY RATES. AS A RESULT, THE CONTRACT INSTALLATION WAS MUCH HIGHER DUE TO SIGNIFICANTLY MOR E ROCK EXCAVATION BACKFILL AND MORE FOOTAGE.
KY | KY - CENTRAL | 2629 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 20026921700 | 2000 | EX | INVESTIGATE ROW AND EASEMENT | 2020-08-14 | 8TH STREET | B | 7736 | 0 | -7736 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 20026924800 | 557 | EX | REPLACE 40'-2"PMMP | 2020-02-17 | 2558 DOYLESVILLE RD | A | 1911.1195 | 2579.36 | 668.2405 | 35% | 40 | 37 | 69.7124 | INSTALLED 37' OF 2'' PLASTIC PIPE IN OPEN TRENCH
KY | KY - CENTRAL | 2629 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 20026924900 | 558 | EX | RETIRE MAIN - LEAKAGE | 2020-02-17 | 2558 DOYLESVILLE RD | A | 142.0588 | 2558.98 | 2416.9212 | 1,701% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026925801 | 561 | EX | INSTALL 6,500' - 2"/6" PMMP | 2020-10-30 | MAIN ST | B | 1499015.1136 | 1564889.33 | 65874.2164 | 4% | 6500 | 7385 | 211.9011 | JOB ORDER CODED COMPLETE IN ERROR. SCHEDULED COMPLETION DATE WILL BE END OF NOVEMBER 2020. SPENDLE PER COORDINATOR 10/5/20
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026925900 | 562 | EX | RETIRE 9,059' - LP MAIN | 2020-12-10 | MAIN ST | B | 351.4966 | 608.53 | 257.0334 | 73% |  |  | 0
KY | KY - CENTRAL | 2629 | U131983 |  |  |  | 20026929800 | 587 | EX | UPGRADE ELECTRONICS | 2020-05-05 | 1077 CANE RIDGE RD | F | 3038 | 3860.13 | 822.13 | 27% |  |  | 0 | UPGRADED 2G/3G CELL MODEM TO RV50 4G/5G CELL MODEM EQUIPMENT INSTALLED BY ACP
KY | KY - CENTRAL | 2629 | U131983 |  |  |  | 20026929900 | 587 | EX | UPGRADE ELECTRONICS | 2020-05-05 | 1180 ENTERPRISE DR | F | 3038 | 12290.02 | 9252.02 | 305% |  |  | 0 | UPGRADED 2G/3G CELL MODEM TO RV50 4G/5G CELL MODEM EQUIPMENT INSTALLED BY ACP
KY | KY - CENTRAL | 2629 | U131983 |  |  |  | 20026930000 | 587 | EX | UPGRADE ELECTRONICS | 2022-10-07 | 700 TECH DR | F | 3038 | 4491.87 | 1453.87 | 48% |  |  | 0 | INSTALLED NED EC350 JPASLEY 10-7-22
KY | KY - CENTRAL | 2629 | U131983 |  |  |  | 20026930100 | 587 | EX | UPGRADE ELECTRONICS | 2021-01-14 | 125 WHEAT DR | F | 3038 | 3919.3 | 881.3 | 29% |  |  | 0 | NO TICKET NEEDED FOR THE WORK PERFORMED. 1/14/21 GCCC TICKET NOT REQUIRED PE ENGINEER CINDY SPARKS GAVE VERBAL APPROVAL ON SITE TO PROCEED WITH JOB. EFC REPLACEMENT ONLY GAS FLOW NOT INTERUPTED JOB DELAYED DUE TO COVID 19 AND COMPLIANCE WORK AND BY NOW HAVING TO BE REVIEWED BY PE ENGINEER
KY | KY - CENTRAL | 2629 | U131983 |  |  |  | 20026930200 | 587 | EX | UPGRADE ELECTRONICS | 2020-11-17 | 1100 ENTERPRISE DR | F | 3038 | 6244.14 | 3206.14 | 106% |  |  | 0 | CHANGED METER AND REPLACED EFC
KY | KY - CENTRAL | 2629 | U131983 |  |  |  | 20026930300 | 587 | EX | UPGRADE ELECTRONICS | 2022-03-04 | 435 E WASHINGTON ST | F | 3038 | 9306.71 | 6268.71 | 206% |  |  | 0 | MET MOOSE ONSITE TO INSTALL SOLAR PANEL, CELL BOOSTER,BATTERY/BOX INSTALLED NEW EC350 WSHIMFESSEL JMULLINS COMPLETED PAPER WORK 06-13-2022
KY | KY - CENTRAL | 2629 | U131983 |  |  |  | 20026930400 | 587 | EX | UPGRADE ELECTRONICS | 2021-03-29 | 2001 OWINGSVILLE RD | F | 3038 | 6567.19 | 3529.19 | 116% |  |  | 0 | CCC TICKET NOT REQUIRED 3/29/21 CFARIS REPLACED EFC AND WORKED TP ORDER JOB ON HOLD FOR 2020 DUE TO COVID 19 GCCC TICKET NOT REQUIRED ON 3/31/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK ALSO THIS IS NON-SCADA MONITORED GMB CFARIS
KY | KY - CENTRAL | 2629 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 20026933000 | 584 | EX | RETIRE STATION 1655 | 2020-08-26 | 815 ELM ST | F | 2459.9928 | 1062.75 | -1397.2428 | -57% |  |  | 0 | TIME NOT CHARGED TO THIS CAPITAL JOB MONITORING JOB CREATED AND TIME CHARGED TO 20-838529-00
KY | KY - CENTRAL | 2629 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 20026933101 | 557 | EX | INSTALL 430' 4" PMLP | 2020-07-22 | ELM | B | 181605.0857 | 134736.52 | -46868.5657 | -26% | 420 | 549 | 245.4217 | UNDERRUN EXPLANATION: THIS PROJECT IS UNDERRUNNING BECUASE 1600' OF 6 & 2 D ID NOT GET USED AS WELL AS TEMPORARY PAVING. THIS IS A COMMUNITY THAT PAVES OUR WORK AND WE HAVE NOT BEEN BILLED YET.
KY | KY - CENTRAL | 2629 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 20026933200 | 558 | EX | RETIRE 1502' 2"/3"/4"/6" BSLP | 2020-09-02 | ELM | B | 175.4976 | 62.25 | -113.2476 | -65% |  |  | 0
KY | KY - CENTRAL | 2629 | U131983 |  |  |  | 20026937200 | 588 | EX | RETIRE ELECTRONICS | 2022-10-07 | 700 TECH DR | F | 73.3494 | 0 | -73.3494 | 100% |  |  | 0 | RETIRE OLD MIN-AT INSTALLED NED EC350 JPASLEY 10-7-22
KY | KY - CENTRAL | 2629 | U131983 |  |  |  | 20026937300 | 588 | EX | RETIRE ELECTRONICS | 2021-01-14 | 125 WHEAT DR | F | 73.3494 | 0 | -73.3494 | 100% |  |  | 0 | GCCC TICKET NOT REQUIRED VERBAL APPROVAL GIVEN ONSITE BY PE ENGINEER CINDY SPARKS TO WORK JOB GAS FLOW NOT INTERUPTED TO WORK JOB THIS WAS EFC REPLACEMENT ONLY JOB DELAYED DUE TO COVID 19 COMPLIANCE WORK AND WAITING REVIEW BY PE ENGINEER
KY | KY - CENTRAL | 2629 | U131983 |  |  |  | 20026937400 | 588 | EX | RETIRE ELECTRONICS | 2020-11-17 | 1100 ENTERPRISE DR | F | 73.3494 | 0 | -73.3494 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U131983 |  |  |  | 20026937500 | 588 | EX | RETIRE ELECTRONICS | 2022-03-04 | 435 E WASHINGTON ST | F | 73.3494 | 129.79 | 56.4406 | 77% |  |  | 0 | RETIRED MINI-AT INSTALLED NEW EC350 JMULLINS CO PAPER WORK 06132022
KY | KY - CENTRAL | 2629 | U131983 |  |  |  | 20026937600 | 588 | EX | RETIRE ELECTRONICS | 2021-03-29 | 2001 OWINGSVILLE RD | F | 73.3494 | 0 | -73.3494 | 100% |  |  | 0 | REPLACED EFC JOB ON HOLD IN 2020 DUE TO COVID 19 GCCC TICKET NOT REQUIRED NOT AT STATION OFF SITE COMPLETING PAPERWORK ALSO THIS IS A NON-SCADA MONITORED GMB 3/31/21 CFARIS
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026939200 | 560 | EX | RETIRE 800' OF 4"CSHP MAIN | 2020-10-12 | PARIS BYPASS | B | 132.5241 | 989.15 | 856.6259 | 646% |  |  | 0
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 20026939700 | 575 | EX | ACQ ESMT OFF OF 325 WEBSTER AV | 2020-07-13 | 325 WEBSTER AV | F | 34881 | 29880.88 | -5000.12 | -14% |  |  | 0 | 16JUL20: ALL EASEMENTS ACQUIRED BY TAYLOR CLARK W/FISHEL & LRT'S CLEARED BY TIFFANY FRITCHLEY
KY | KY - CENTRAL | 2629 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026940900 | 909 | EX | INSTALL I&C EQUIPMENT | 2022-12-15 | PARIS BYPASS | F | 18740.1071 | 12849.77 | -5890.3371 | -31% |  |  | 0 | CCC TICKET# 55594 CCC TICKET# 55594 PAPER WORK GATHER INFO 12-15-22 JBRADFORD
KY | KY - CENTRAL | 2629 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026941000 | 584 | EX | RETIRE GAUGE | 2022-12-15 | PARIS BYPASS | F | 91.4991 | 1582.1 | 1490.6009 | 1,629% |  |  | 0 | CCC TICKET# 55594 CCC# 55594 ERX ONLINE P2P W/GAS CONTROL OK REMOVED CHART BOX AND FILED LAST CHART ON CABINET TICKET# 11209 GATHERED INFORMATION FOR CLOSEOUT PAPERWORK 12-15-22 JBRADFORD
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026941100 | 2000 | EX | INVESTIGATE CONFLICTS | 2020-06-16 | 233 US 60 OWINGSVILLE RD | A | 4146 | 0 | -4146 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026941200 | 561 | EX | INSTALL 145' OF 4"PMMP | 2020-08-18 | 233 US60 OWINGSVILLE RD | B | 27431.3922 | 33681.75 | 6250.3578 | 23% | 345 | 149 | 226.052
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026941300 | 562 | EX | RETIRE 140' OF 4"PMMP MAIN | 2020-08-18 | 233 US60 OWINGSVILLE RD | B | 85.2291 | 0 | -85.2291 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026943700 | 584 | EX | RETIRE REG STATION 1281 | 2020-07-16 | MAIN ST | F | 22407.6299 | 1081.34 | -21326.2899 | -95% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026943800 | 584 | EX | RETIRE REG STATION 1272 | 2020-11-06 | HIGH ST | F | 5011.4949 | 18232.64 | 13221.1451 | 264% |  |  | 0 | REF 1561 - ESPARKS 11-06-20
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026944600 | 562 | EX | RETIRE 2,043' - MP MAIN | 2020-09-24 | MAIN ST | B | 877.2414 | 214.05 | -663.1914 | -76% |  |  | 0
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 20026947100 | 557 | EX | INSTALL 20'-4" PMLP | 2020-04-23 | 157 COOK AV | A | 9973.7353 | 15483.28 | 5509.5447 | 55% | 20 | 20 | 774.164 | MATERIALS FAILED TO BE ORDERED WITH ORIGINAL JOB ORDER (20-0269471-00) THEREFORE WERE ORDER 5/5/20 TO REPLINISH STOCK VIA MATL J.O. 20-8074409-00
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 20026947200 | 558 | EX | RETIRE 20'-4" CSLP | 2020-04-23 | 157 COOK AV | A | 342.2335 | 336.88 | -5.3535 | -2% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026947301 | 561 | EX | INSTALL 3,950' - 2" PMMP | 2021-10-22 | HIGH ST | B | 1562557.4499 | 1895184.87 | 332627.4201 | 21% | 3950 | 4868 | 389.3149 | TTOY/KY 3/2/22: OVERRUN EXPLANATION: FLAGGER OT ESTIMATED FOR 543 HOURS BUT ACTUAL WAS 1033 HOURS, CONTRACTOR CREWS HOURLY TIME WAS OVER ESTIMATE AT 167 EXTRA HOURS, SEGA HAD EXTRA $60,000 IN COST, COMPANY LABOR HAD ADDITIONAL $27,000 COST OVER ESTIMATE
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026947400 | 562 | EX | RETIRE 5,000' - 4" CI/BS LP | 2021-10-29 | HIGH ST | B | 103.8156 | 71.35 | -32.4656 | -31% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026947500 | 555 | EX | INSTALL 300' - 2" PMMP | 2020-07-27 | 180 TIERNEY WY | B | 24580.9634 | 35150.12 | 10569.1566 | 43% | 300 | 336 | 104.6135
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026948600 | 557 | EX | INSTALL 10' - 2" PMMP | 2020-06-09 | 7100 LEVEE RD | A | 3859.8968 | 4813.41 | 953.5132 | 25% | 30 | 2 | 2406.705 | SEE PAPER PACKET SEE DPI COMMENTS
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026948700 | 558 | EX | RETIRE 10' - 2" PMMP | 2020-06-09 | 7100 LEVEE RD | A | 52.2687 | 534.22 | 481.9513 | 922% |  |  | 0 | SEE PAPER COPIES IN PACKET SYSTEM NUMBER 32001021
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 20026948800 | 557 | EX | INSTALL 6'-4"/2" PMMP | 2020-05-01 | 10 CEDAR GROVE RD | A | 8336.5018 | 4895.08 | -3441.4218 | -41% | 6 | 6 | 815.8467
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 20026948900 | 558 | EX | RETIRE 15'-4"/2" PMP | 2020-05-01 | 10 CEDAR GROVE RD | A | 428.2995 | 326.16 | -102.1395 | -24% |  |  | 0
KY | KY - CENTRAL | 2629 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 20026949000 | 2000 | EX | TOYOTAL ILI PROJECT | 2021-04-29 | HICKORY RIDGE RD | A | 274998 | 0 | -274998 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | BKSLONE |  |  |  | 20026949100 | 555 | EX | INSTALL 12'-2" CSHP HEATER PIP | 2020-09-25 | 605 ROLLING HILLS LN | B | 23398.3235 | 31026.28 | 7627.9565 | 33% | 12 | 16 | 1939.1425
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026949300 | 2000 | EX | INVESTIGATE LAND RIGHTS | 2020-05-26 | 180 TIERNEY WY | B | 3172 | 0 | -3172 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026949900 | 557 | EX | INSTALL 1100' - 2" PMMP | 2021-07-08 | 409 E MAIN ST | B | 207915.8181 | 206985.91 | -929.9081 | 0% | 1100 | 979 | 211.4259
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026950000 | 558 | EX | RETIRE 1430' OF 2"/3" BS-MP | 2021-07-15 | 409 E MAIN ST | B | 81.9085 | 2502.68 | 2420.7715 | 2,955% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026950400 | 2000 | EX | INSTALL/ADBN MAIN | 2021-04-21 | 409 E MAIN ST |  | 6634 | 0 | -6634 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 20026953200 | 2000 | EX | RESEARCH EASEMENT AND LAND ACQ | 2022-02-09 | 532 CLINTONVILLE RD |  | 4967 | 0 | -4967 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026955400 | 584 | EX | RETIRE STATION | 2021-02-04 | WINSTON RD | F | 1910.2958 | 2363.47 | 453.1742 | 24% |  |  | 0 | 8561 JOB WAS ON HOLD UNTIL AFTER BEGINNING OF THE YEAR
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026956300 | 0001 | EX | DERATE MP SYSTEM 32049005 | 2021-02-04 | RICHMOND RD |  | 0 | 0 | 0 | 0% |  |  | 0
KY | KY - CENTRAL | 2629 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 20026957600 | 2000 | EX | RESEARCH LAND RIGHT | 2021-08-19 | 724 DUG HILL RD | A | 2000 | 0 | -2000 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026957700 | 557 | EX | INSTALL 150' - 6" PMMP | 2020-07-10 | 1535 W LEXINGTON AV | B | 67436.4193 | 66063.67 | -1372.7493 | -2% | 112 | 81 | 815.6009
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026957800 | 558 | EX | RETIRE 375' - 4" PMP | 2020-07-13 | 1535 W LEXINGTON AV | B | 86.6677 | 0 | -86.6677 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 20026958200 | 2000 | EX | RESEARCH LAND RIGHT | 2022-11-03 | CLINTONVILLE RD | A | 2000 | 0 | -2000 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 20026959300 | 2000 | EX | RESEARCH EASEMENT AND ROW | 2022-11-03 | 4733 ROCKWELL RD |  | 7613 | 0 | -7613 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026960900 | 557 | EX | INSTALL 40' OF 2"PMMP MAIN | 2020-07-21 | 1083 VINE ST | A | 17478.1738 | 11798.31 | -5679.8638 | -32% | 20 | 30 | 393.277
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026961000 | 558 | EX | RETIRE 40' OF 2"PAMP MAIN | 2020-07-21 | 1083 VINE ST | A | 79.5082 | 616.76 | 537.2518 | 676% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026963900 | 557 | EX | INSTALL 10' - 2" PMMP | 2020-08-03 | 1118 VINE ST | A | 2010.0583 | 3015.21 | 1005.1517 | 50% | 10 | 4 | 753.8025
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026964000 | 558 | EX | RETIRE 10' - 2" PMP | 2020-08-03 | 1118 VINE ST | A | 79.5082 | 0 | -79.5082 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026964102 | 557 | EX | INSTALL 4000' OF 12"CSHP MAIN | 2021-04-27 | 4949 COLBY RD | B | 909258.0027 | 1045900.23 | 136642.2273 | 15% | 5500 | 3502 | 298.658 | TWALKER/KY 09-21-21: JOB OVER RUN DUE TO ADDITIONAL ENVIRONMENTAL AND SITE CLEANUP ON SITE DUE TO RAIN DURING CONSTRUCTION, THIS ADDED EXTRA $40,000 TO CONTRACT COST, PROJECT REQUIRED 2 COMPANY COORDINATORS BUT WAS PLANNED FOR 1 ADDED $35,000 IN LABOR COST AND SEGA INCREASED BY $33,000.
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026964200 | 558 | EX | RETIRE 1200' OF 12"BSHP MAIN | 2021-04-27 | 4949 COLBY RD | B | 84.1799 | 3603.11 | 3518.9301 | 4,180% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026964301 | 575 | EX | OBTAIN EASEMENTS FOR HP MAIN | 2020-12-07 | COLBY RD | F | 250078 | 456916.71 | 206838.71 | 83% |  |  | 0 | TWALKER/KY 09-21-21: LEVEL 2 VARIANCE REPORT ADDED TO WMS.DOCS COST OVER RUN DUE TO RIGHT OF WAY CLEARING AND EASEMENT COST.
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026964600 | 557 | EX | INSTALL 2" SS | 2020-08-04 | LITER | A | 3010.1002 | 487.11 | -2522.9902 | -84% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026964700 | 558 | EX | RETIRE 12' - 2" BSLP | 2020-08-04 | LITER | A | 82.3372 | 0 | -82.3372 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026967500 | 561 | EX | INSTALL 90' - 2" PMMP | 2020-09-25 | TIERNEY WY | B | 11568.0567 | 20878.42 | 9310.3633 | 80% | 90 | 98 | 213.0451
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026967600 | 562 | EX | RETIRE 146' - 2" PMMP | 2020-09-25 | TIERNEY WY | B | 91.691 | 56.19 | -35.501 | -39% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026968900 | 557 | EX | INSTALL 15' OF 4"PMMP MAIN | 2020-08-20 | 320 HILL ST | A | 7221.6954 | 4682 | -2539.6954 | -35% | 15 | 5 | 936.4
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026969000 | 558 | EX | RETIRE 15' OF 4"PAMP MAIN | 2020-08-20 | 320 HILL ST | A | 90.1729 | 0 | -90.1729 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026969800 | 2000 | EX | INVESTIGATE LAND RIGHTS | 2021-08-11 | JOHNSON ST | B | 1910 | 0 | -1910 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026969900 | 585 | EX | INSTALL FENCE & BOLLARDS | 2022-11-19 | JOHNSON ST | F | 36430.1489 | 9603.34 | -26826.8089 | -74% |  |  | 0 | INSTALLED NEW FENCE 11-19-22 JMULLINS
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026970000 | 586 | EX | RETIRE BUILDING | 2022-11-19 | JOHNSON ST | F | 88.8156 | 26427.16 | 26338.3444 | 29,655% |  |  | 0 | CCC# 37831 CCC# 33819 CCC# 38966 TO BE COMP BY CFARRIS BUILDING REMOVED JMULLINS
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026971800 | 0001 | EX | DOWNRATE 32010178 TO 199 PSIG | 2020-09-01 | CYNTHIANA RD |  | 87.1365 | 0 | -87.1365 | 100% |  |  | 0 | TWALKER/KY 9-10-20: UPDATED MAOP WORKSHEET ADDED TO WMS.DOCS FOR MAOP CHANGE.
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026971900 | 0001 | EX | DOWNRATE 32049008 TO 199 PSIG | 2020-09-01 | WISEMANTOWN RD |  | 91.691 | 0 | -91.691 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026972000 | 0001 | EX | DOWNRATE 32001004 TO 199 PSIG | 2020-09-01 | STEPSTONE RD |  | 91.691 | 0 | -91.691 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026972100 | 0001 | EX | DOWNRATE 32010026 TO 199 PSIG | 2020-09-01 | LINDEN AV |  | 87.1365 | 0 | -87.1365 | 100% |  |  | 0 | TWALKER/KY 09-10-20: NEW MAOP WORKSHEET ADDED TO WMS.DOCS
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026975600 | 584 | EX | RETIRE R-1262 | 2020-11-06 | ELIZABETH ST | F | 5011.4949 | 13026.11 | 8014.6151 | 160% |  |  | 0 | REF 1543 ESPARKS 11-06-20
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026975700 | 584 | EX | RETIRE R-1259 | 2020-11-06 | HOUSTON AV | F | 5011.4949 | 11155.43 | 6143.9351 | 123% |  |  | 0 | TICKET#1528
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026975800 | 584 | EX | RETIRE R-1261 | 2020-11-06 | RUCKER AV | F | 5011.4949 | 15299.94 | 10288.4451 | 205% |  |  | 0 | TICKET#1508 ESPARKS 11-06-20
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026976100 | 555 | EX | INSTALL 100' - 2" PMMP | 2020-09-30 | 180 TIERNEY WY | B | 10097.5832 | 14297.06 | 4199.4768 | 42% | 100 | 88 | 162.4666
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026976900 | 909 | EX | INSTALL RTU & INSTRUMENTATION | 2023-08-22 | 724 DUG HILL RD | F | 302143.1164 | 362179.42 | 60036.3036 | 20% |  |  | 0 | CCC# 2490 CCC# 2490 CCC# 2490 CCC# 5078 6417 CCC# 7314 CCC# 7314 CCC# 7314 CCC# 6417 CCC# 6417 CCC# 6417 CCC# 6417 CCC# 6417
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026977000 | 910 | EX | RETIRE RTU & INSTRUMENTATION | 2023-08-22 | 724 DUG HILL RD | F | 60.3089 | 2598.25 | 2537.9411 | 4,208% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026978700 | 557 | EX | INSTALL 10' - 3" PMMP | 2020-10-01 | US HIGHWAY 27 S | A | 3412.3872 | 3586.89 | 174.5028 | 5% | 10 | 8 | 448.3612
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026978800 | 558 | EX | RETIRE 10' - 3" PMMP | 2020-10-01 | US HIGHWAY 27 S | A | 75.9579 | 39.46 | -36.4979 | -48% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026979600 | 559 | EX | INSTALL 20' - 2"/6" PMMP | 2021-03-11 | WILSON AV | B | 65238.0736 | 106288.64 | 41050.5664 | 63% | 105 | 29 | 3665.1255 | ATTEMPTED TO REVISE DUE TO EXTRA HOURLY COST, COULD NOT REVISE DUE TO UNFULLFILLED PURCHASE ORDER TTOY 3/18/2021 OVERRUN EXPLANATION: JO WAS ORIGINALLY PLANNED ON 2018 FISHEL CONTRACT, JO WAS EXECUTED USING 2020 STANLEY PIPELINE CONTRACT, EXTRA VAC EXCA, EXTRA WLD AND RIG, EXTRA TOP SOIL REQUIRED, EXTRA HOURLY CREW REQUIRED, ESTIMATED HOURLY TIME WAS 56 HOURS, ACTUAL HOURLY TIME WAS 398 HOURS, ESTIMATED CONTRACT COST WAS $35,000, ACTUAL CONTRACT COST WAS $51,000
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026979700 | 560 | EX | RETIRE 15' - 2" BSLP | 2021-03-11 | WILSON AV | B | 92.1481 | 71.35 | -20.7981 | -23% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026980401 | 557 | EX | INSTALL 13,025'-PMMP/CSHP | 2022-09-06 | MT STERLING PK | B | 1836238.4697 | 2258910.28 | 422671.8103 | 23% | 12625 | 6818 | 331.3157 | OVERRUN EXPLANATION: PROJECT INCLUDED ADDITIONAL PAVING THAT WAS UNFORSEEN DUE TO CITY REQUIREMENTS, SEGA HAD AN INCREASE OF OVER $100,000 TTOY 3/2/2023
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026980500 | 558 | EX | RETIRE 12,520' - LP MAIN | 2022-09-20 | MT STERLING PK | B | 52.2976 | 809.88 | 757.5824 | 1,449% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026980601 | 557 | EX | INSTALL 16,200'-2"/4" PMMP | 2021-10-12 | HIGGINS ST | B | 4665902.1359 | 4720247.08 | 54344.9441 | 1% | 16925 | 20509 | 230.1549
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026980700 | 558 | EX | RETIRE MAIN - LEAKAGE | 2022-09-14 | HIGGINS ST | B | 103.8156 | 2546.03 | 2442.2144 | 2,352% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026981601 | 557 | EX | INSTALL 9,950' OF 2"/4"/6"PMMP | 2021-08-02 | MAIN ST | B | 3261487.9737 | 3477462.23 | 215974.2563 | 7% | 9980 | 9263 | 375.4143
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026981700 | 558 | EX | RETIRE 15,000' - LP MAIN | 2022-05-25 | MAIN ST | B | 82.4486 | 0 | -82.4486 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026981800 | 558 | EX | RETIRE 18,000 - MP MAIN | 2022-05-02 | MAIN ST | B | 82.4486 | 0 | -82.4486 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026983100 | 557 | EX | INSTALL 10' OF 3"PMMP MAIN | 2020-10-20 | FOREST AV | A | 4601.6704 | 3944.31 | -657.3604 | -14% | 10 | 5 | 788.862
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026983200 | 558 | EX | RETIRE 10' OF 3"PAMP MAIN | 2020-10-20 | FOREST AV | A | 58.1799 | 0 | -58.1799 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026986100 | 584 | EX | RETIRE R-1695 | 2020-11-12 | BANK ST | F | 22384.5607 | 19065.43 | -3319.1307 | -15% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026986400 | 584 | EX | RETIRE R-1656 | 2020-11-16 | ALLEY | F | 22384.5607 | 14724.32 | -7660.2407 | -34% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026987900 | 2000 | EX | INVESTIGATE CONFLICT | 2021-01-05 | HIGH ST | B | 24268 | 0 | -24268 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026988200 | 2000 | EX | INVESTIGATE LAND RIGHTS | 2021-03-26 | MAIN ST | B | 10944 | 0 | -10944 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026990100 | 559 | EX | INSTALL 6" SS | 2021-03-11 | WILSON AV | B | 1607.8146 | 245.63 | -1362.1846 | -85% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026991400 | 558 | EX | PAPER ONLY FOR CLOSE-OUT | 2020-11-17 | FRANCIS ST | B | 103.8156 | 0 | -103.8156 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026992600 | 558 | EX | RETIRE MP MAIN | 2022-09-14 | RUCKER ST | B | 103.8156 | 0 | -103.8156 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026101900 | 566 | EX | RETIRE 6"MP SERVICE LINE | 2022-06-14 | 824 KY HIGHWAY 356 | B | 9764.3857 | 9737.82 | -26.5657 | 0% |  |  | 0 | INSTALLED BOLTED DEAD END CAP AT END OF NC 216695 VALVE. JOSH PASLEY 6/14/22
KY | KY - CENTRAL | 2629 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 21026102700 | 2000 | EX | INVESTIGATE INCROACHMENT | 2022-11-08 | MACK ST |  | 694 | 0 | -694 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026103400 | 555 | EX | INSTALL 2,700' - 2"/4" PMMP | 2022-04-21 | HIBISCUS LN LT101 | B | 115766.1902 | 185537.75 | 69771.5598 | 60% | 3200 | 2712 | 68.4136 | TTOY-9/20/22: LEVEL 2 VARIANCE OVERRUN EXPLANATION IN WMSDOCS
KY | KY - CENTRAL | 2629 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 21026104700 | 910 | EX | REMOVE OBSOLETE ELECTRONICS | 2022-09-27 | EARLY DR | F | 135.8546 | 236.27 | 100.4154 | 74% |  |  | 0 | INSTALLED NEW RTU BUILDING AND TRANSMITTERS JPASLEY 9-27-2022
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026107000 | 555 | EX | INSTALL 250' - 2" PMMP | 2022-04-22 | 808 INDIAN MOUND DR | B | 25983.7669 | 72807.39 | 46823.6231 | 180% | 250 | 304 | 239.498 | OVERRUN EXPLANATION: PROJECT WAS PLANNED FOR OPEN CUT, NEW MAIN WAS INSTALL ED BY HEAVY ROCK BORE, ADDITIONAL LAND SERVICES WAS REQUIRED FOR EASMENT, BORE CREW HOURLY WAS MORE THAN ESTIMATED 3 MAN CREW
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026108400 | 557 | EX | EMER - INSTALL 350' - 4" PMMP | 2021-03-16 | ROCKWELL RD | B | 44073.8715 | 86916.93 | 42843.0585 | 97% | 400 | 343 | 253.4021 | OVERRUN EXPLANATION: HOURLY TIME EXTIMATED AT 48 HOURS, ACTUAL TIME WAS 97 HOURS, SEGA WAS DOUBLED, CONTRACT WAS ESTIMATED FOR $29,000, ACTUAL WAS $68,000, PROJECT WAS ESTIMATED TO DIRECTIONAL BORE 150', ACTUAL INSTALL WAS OPEN CUT 345', PROJECT REQUIRED EXTRA PAVING DUE TO OPEN CUT, PROJECT REQUIRED EXTRA PROCESSED AND STONE DUST DUE TO OPEN CUT, EXTRA VACUUM EXCAV ATING WAS REQUIRED, ESTIMATED FOR 4 MAN CREW CONTRACT, ACTUAL USED 3 MAN, 4 MAN, AND 5 MAN CREWS
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026108500 | 558 | EX | EMER - RETIRE 350' - 4" PMP | 2021-03-16 | ROCKWELL RD | B | 85.3307 | 4479.43 | 4394.0993 | 5,149% |  |  | 0
KY | KY - CENTRAL | 2629 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 21026110900 | 585 | EX | INSTALL REPLACEMENT FENCE | 2021-07-09 | 724 DUG HILL RD | F | 44982.9906 | 4971.16 | -40011.8306 | -89% |  |  | 0 | CCC# 30433 MONITORED FENCE INSTALLATION CCC# 30433 CCC# 30596 CC# 30596 MONTOR STATION CCC# 30956 NEW FENCE INSTALLED WSHIMFESSEL 07-09-2021 UNDERRUN EXPLANATION: COST WAS SIGNIFICANTLY LESS THAT WHAT THE CONTRACTOR HAD ESTIMATED OVER THE PHONE.
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026111300 | 584 | EX | RETIRE R-1654 | 2022-05-10 | CARHART AV | F | 3585.1779 | 0 | -3585.1779 | 100% |  |  | 0 | ENTIRE STATION RETIRED INCLUDING INLET AND OUTLET PIPING WSHIMFESSEL 5/10/2 022, RWILLIAMS COMPLETED JOB AND PAPERWORK
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026111400 | 584 | EX | RETIRE R-1653-B LP | 2022-05-18 | MAIN ST | F | 3585.1779 | 0 | -3585.1779 | 100% |  |  | 0 | RETIRED LP RUN FROM R-1653 BLIND FLANGED INLET VALVE AND BYPASS VALVE WSHIM FESSEL, RWILLIAMS COMPLETED JOB AND PAPERWORK
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026112900 | 555 | EX | INSTALL 150' - 2" PMMP | 2021-09-29 | 1048 CRESTWOOD HT | B | 15892.286 | 14483.58 | -1408.706 | -9% | 150 | 130 | 111.4122
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026113300 | 2000 | EX | INVESTIGATE PIPELINE EASEMENT | 2023-01-10 | 200 COMMERCE DR | B | 2421 | 0 | -2421 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026116000 | 2000 | EX | INVESTIGATE/ACQUIRE EASEMENT | 2021-08-18 | 236 REDWING DR | B | 5360 | 0 | -5360 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026117400 | 563 | EX | INSTALL 190' - 4" PMMP SL | 2021-06-21 | 605 ROLLING HILLS LN 1 | B | 22441.9346 | 40096.06 | 17654.1254 | 79% | 190 |  | 0 | INSTALLED 243'OF 4"PMP FOR SL TO FEED PSID 501307207-CAPPED AND BURRIED END OF SL FOR FUTURE TIE IN/INSTALLATION OF RISER AND SETTING ONCE FURTHER SITE CONSTRUCTION IS COMPLETED,PER CG ENGINEER J TOY AND CONSTRUCTION SITE GC- LINE MARKER WITH WIRE AT TAP,WIRE IN VALVE BOX,AND MARKER BALLS AT ALL CHANGES OF DIRECTIONAND END OF SL INSTALLED FOR LOCATABILITY
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026117500 | 587 | EX | INSTALL GMB SETTING | 2022-05-03 | 605 ROLLING HILLS LN | F | 58469.7613 | 77589.89 | 19120.1287 | 33% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026119100 | 2000 | EX | INVESTIGATE RELOCATION | 2021-06-15 | LINCOLN ST |  | 9923 | 0 | -9923 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U124399 | Bishop,Steven | Gill,John | Dunn,David | 21026119200 | 559 | CO | PM- LAKE CARNICO REPLACEMENT | 2022-10-13 | LAKESHORE RD | C | 3161436 | 3041283.83 | -120152.17 | -4% |  | 165 | 18432.0232
KY | KY - CENTRAL | 2629 | U124399 | Bishop,Steven | Gill,John | Dunn,David | 21026119300 | 560 | CO | PM- LAKE CARNICO ABANDONMENT | 2022-10-13 | LAKESHORE RD | C | 62500 | 729097.27 | 666597.27 | 1,067% |  |  | 0
KY | KY - CENTRAL | 2629 | U124399 | Bishop,Steven | Gill,John | Dunn,David | 21026120000 | 559 | EX | PM-PARIS CYNTHIANA REPLACEMENT | 2022-09-22 | US 27 | C | 1087500 | 1437073.2 | 349573.2 | 32% |  | 4 | 359268.3
KY | KY - CENTRAL | 2629 | U124399 | Bishop,Steven | Gill,John | Dunn,David | 21026120100 | 560 | EX | PM-PARIS CYNTHIANA ABANDONMENT | 2022-09-22 | US 27 | C | 62500 | 325920.13 | 263420.13 | 421% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026120900 | 557 | EX | INSTALL 5' - 3" PMLP | 2021-04-26 | 56 FLANAGAN ST | A | 1134.2677 | 1085.98 | -48.2877 | -4% | 5 | 3 | 361.9933
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026121000 | 558 | EX | RETIRE 5' - 3" PMLP | 2021-04-26 | 56 FLANAGAN ST | A | 58.9085 | 0 | -58.9085 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026121100 | 557 | EX | INSTALL 5' - 4" PMMP | 2021-04-28 | GARDEN SPRINGS | A | 2822.803 | 2417.89 | -404.913 | -14% | 10 | 10 | 241.789
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026121200 | 558 | EX | RETIRE 5' - 4" PMLP | 2021-04-28 | GARDEN SPRINGS | A | 58.9085 | 0 | -58.9085 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026123100 | 561 | EX | INSTALL 175'-4" PMMP | 2021-07-07 | LINCOLN ST | B | 39889.572 | 53913.76 | 14024.188 | 35% | 205 | 161 | 334.8681
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026123200 | 562 | EX | RETIRE 200'-4" BSMP | 2021-07-07 | LINCOLN ST | B | 77.7619 | 0 | -77.7619 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026123300 | 561 | EX | INSTALL 125'-2" PMMP | 2021-07-19 | PRIMROSE LN | B | 28847.4767 | 36910.92 | 8063.4433 | 28% | 125 | 124 | 297.6687
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026123400 | 562 | EX | RETIRE 160'-4" PMMP | 2021-07-19 | PRIMROSE LN | B | 77.7619 | 0 | -77.7619 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026123500 | 2000 | EX | INVESTIGATE ROAD R/W | 2021-06-18 | PRIMROSE LN | B | 3360 | 0 | -3360 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026125100 | 562 | EX | RETIRE 175' - 3" LP | 2021-07-08 | LINCOLN ST | B | 88.1542 | 0 | -88.1542 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026125200 | 561 | EX | INSTALL 3" SS | 2021-07-08 | LINCOLN ST | B | 20373.572 | 5010.94 | -15362.632 | -75% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026128200 | 555 | EX | INSTALL 1,300 OF 2"/4"PMMP | 2021-11-19 | GIBSON WY LT21 | B | 51810.9858 | 56524.7 | 4713.7142 | 9% | 1350 | 1500 | 37.6831
KY | KY - CENTRAL | 2629 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 21026129100 | 2000 | EX | TRC - DESIGN 4400' 6-INCH PMP | 2023-08-03 | ROCKWELL RD |  | 20000 | 0 | -20000 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026135300 | 566 | EX | ABANDON 120'-4" PL SL | 2021-08-05 | 605 ROLLING HILLS LN 1 | B | 82.634 | 0 | -82.634 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026135400 | 565 | EX | INSTALL 100'-4" PL SL | 2021-08-05 | 605 ROLLING HILLS LN 1 | B | 10216.5972 | 12266.69 | 2050.0928 | 20% | 100 |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026135900 | 555 | EX | INSTALL 140'-2" PMMP | 2021-12-02 | 275 EVANS DR | B | 14039.3957 | 8332.52 | -5706.8757 | -41% | 140 | 153 | 54.4609
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026136700 | 555 | EX | INSTALL 1,750'-2" PMMP | 2021-11-22 | SAND RIDGE LN LT1C | B | 49760.6579 | 47459.5 | -2301.1579 | -5% | 1750 | 1626 | 29.1879
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026137300 | 575 | EX | OBTAIN EASEMENT FOR POD | 2021-08-19 | 724 DUG HILL RD | F | 18975 | 18834.81 | -140.19 | -1% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026137400 | 558 | EX | RETIRE 120'-1" PMP - D304537 | 2021-08-21 | 2450 UNION CITY RD BLDG | A | 3638.7915 | 399.97 | -3238.8215 | -89% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026137900 | 583 | EX | INSTALL OUTLET VLV R-1643 | 2022-09-08 | GAWTHROP DR | F | 110321.1916 | 80161.67 | -30159.5216 | -27% | 160 |  | 0 | CCC# 80227 MONITOR WHILE BACKFILLING INSTALLED ALL NEW STATION VALVES JPASLEY 9-8-22 UNDERRUN EXPLANATION: PROJECT INCLUDED $27,000 OF CONTINGENCY AND HAD AN UNDERRUN OF 30,492 TTOY 3/2/23
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026138000 | 584 | EX | RETIRE OUTLET VLV R-1643 | 2022-09-08 | GAWTHROP DR | F | 955.7874 | 0 | -955.7874 | 100% |  |  | 0 | RETIRED ALL STATION VALVES AND INSTALLED NEW VALVES JPASLEY 9-8-22
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026138100 | 2000 | EX | INVESTIGATE LAND RIGHTS | 2022-03-03 | MAPLE ST | B | 11969 | 0 | -11969 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026138400 | 557 | EX | EMER-INSTALL 2' OF 1"PMMP MAIN | 2021-08-26 | 2450 UNION CITY RD | A | 3122.8539 | 227.74 | -2895.1139 | -93% | 2 | 2 | 113.87
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026138500 | 558 | EX | EMER-RETIRE 2'-1"PAMP MAIN | 2021-08-26 | 2450 UNION CITY RD | A | 82.634 | 0 | -82.634 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026140000 | 562 | EX | RETIRE 489'-4" PMP | 2022-02-02 | YEISER RD | B | 13697.8754 | 20306.35 | 6608.4746 | 48% |  |  | 0
KY | KY - CENTRAL | 2629 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 21026140300 | 2000 | EX | DESIGN SMRP PROJECT | 2022-10-17 | BURNS AV |  | 35000 | 0 | -35000 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026140501 | 557 | EX | INSTALL 1,985'-6" CSHP | 2023-05-04 | PARIS PK | B | 116515.0569 | 140188.39 | 23673.3331 | 20% |  | 1874 | 74.807
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026140600 | 558 | EX | RETIRE 2,598'- 6" BSHP | 2023-05-04 | PARIS PK | B | 61.5191 | 182.4 | 120.8809 | 196% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026140700 | 558 | EX | RETIRE 2,200' - CSMP | 2022-09-20 | N MAPLE ST | B | 61.2976 | 0 | -61.2976 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026141900 | 2000 | EX | INVESTIGATE AND ACQUIRE ESMNT | 2021-10-01 | SAND RIDGE LN LT1C | B | 14971 | 0 | -14971 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026142000 | 557 | EX | EMER - INSTALL 5'-2" PMMP | 2021-09-15 | WACO LOOP | A | 7513.9749 | 11087.26 | 3573.2851 | 48% | 5 | 5 | 2217.452
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026142100 | 558 | EX | EMER - RETIRE 5'-3" PMMP | 2021-09-15 | WACO LOOP | A | 69.8875 | 0 | -69.8875 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026142300 | 557 | EX | EMER - INSTALL 5'-2" PMMP | 2021-09-16 | 17 CHURCHILL DR | A | 3984.9999 | 11040.25 | 7055.2501 | 177% | 5 | 9 | 1226.6944
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026142400 | 558 | EX | EMER - RETIRE 5'-2" PMP | 2021-09-16 | 17 CHURCHILL DR | A | 69.8875 | 133.69 | 63.8025 | 91% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026142900 | 2000 | EX | INVESTIGATE RR & STATE PERMIT | 2021-12-02 | MAIN ST | B | 12497 | 0 | -12497 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026143100 | 2000 | EX | INVESTIGATE LAND RIGHTS | 2022-01-13 | YEISER RD | B | 8053 | 0 | -8053 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026143200 | 559 | EX | EMER - INSTALL 450'- 4" CSHP | 2021-12-13 | MAIN ST | B | 196595.4538 | 257776.24 | 61180.7862 | 31% | 455 | 496 | 519.7102 | PROJECT WAS CODED AMRCB BECAUSE THE PIPE UNDER THE BRIDGE HAD NO COATING. OVERRUN EXPLANATION: MAIN REASON FOR PROJECT COST OVERRUN IS DUE TO 2,000 UNITS OF ASPHALT PAVING WHEN ONLY 1,000 UNITS WERE PLANNED. THE STATE REQUIRED EXTRA PAVING DUE TO EXISTING ROAD CONDITION.THE PROJECT WAS PLANNED FOR 1 CONSTRUCTION COORDINATORBUT ENDED UP HAVING MULTIPLE AND DOUBLED THE COMPANY LABOR CHARGES. FLAGGING FOR THEPROJECT INCLUDED A 30% INCREASECOMPARED TO THE PLANNED AMOUNT. THE PROJECT INCLUDED AN ADDITIONAL 49 UNITS OF STEELMAINLINE INSTALLATION AND ROCK AND LEDGE EXCAVATIONWAS REQUIRED BUT NOT PLANNED. TTOY 12/2/22
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026143300 | 560 | EX | EMER - RETIRE 100'-3" CSHP | 2021-12-13 | MAIN ST | B | 61.5191 | 3034.48 | 2972.9609 | 4,833% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026147700 | 557 | EX | EMER - INSTALL 5'-2" PMMP | 2021-10-20 | DOYLESVILLE | A | 2686.3426 | 2531.33 | -155.0126 | -6% | 5 | 3 | 843.7767 | REPLACED 3' SECTION OF 2" PMP AFTER DIG IN. PRESSURE TESTED NEW MAIN AT 90 PSIG FOR 1 HOUR, SOAP TESTED FINAL TIE IN AT OP. OK 34 PSIG VERIFIED NRICHIE 10-20-21
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026147800 | 558 | EX | EMER - RETIRE 5'-2" PMP | 2021-10-20 | DOYLESVILLE | A | 61.5191 | 0 | -61.5191 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 21026149300 | 2000 | EX | TRC TO INVEISTIGATE PERM SOL | 2022-09-21 | HWY 52 |  | 32929 | 0 | -32929 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026149800 | 584 | EX | RETIRE R-1615 | 2023-05-09 | ALLEY OFF MAIN ST | F | 16113.7857 | 552.62 | -15561.1657 | -97% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026152700 | 583 | EX | EMER - INSTALL ODORIZER | 2022-08-16 | STATE RT 89 | F | 303602.2828 | 170463.75 | -133138.5328 | -44% |  |  | 0 | UNDERRUN EXPLANATION: PROJECT DID NOT REQUIRE AS MUCH CONTINGENCY, OR OUTSIDE LABOR COSTS FROM CONTRACTORS TTOY 3/2/23
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026152800 | 584 | EX | EMER - RETIRE ODORIZER | 2022-08-16 | STATE RT 89 | F | 61.5191 | 62508.06 | 62446.5409 | 101,508% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026156100 | 557 | EX | EMER-INSTALL 6' OF 2"PMMP MAIN | 2021-12-14 | 25 WESTCHESTER DR | A | 6138.1743 | 5612.12 | -526.0543 | -9% | 6 | 6 | 935.3533
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026156200 | 558 | EX | EMR-RET 6'-2"PMP MAIN D222323 | 2021-12-14 | WESTCHESTER DR | A | 61.2976 | 75.03 | 13.7324 | 22% |  |  | 0
KY | KY - CENTRAL | 2629 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 21026157501 | 557 | EX | EMER - INSTALL 5'-3" PMMP | 2021-12-27 | 1525 W LEXINGTON AV | A | 13441.7151 | 24476.25 | 11034.5349 | 82% | 5 | 4 | 6119.0625
KY | KY - CENTRAL | 2629 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 21026157600 | 558 | EX | EMER - RETIRE 5'-3" PAMP | 2021-12-27 | 1525 W LEXINGTON AV | A | 72.8047 | 106.63 | 33.8253 | 46% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026993100 | 562 | EX | RETIRE 229' - PMMP | 2021-07-20 | HIGH ST | B | 103.8156 | 0 | -103.8156 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026996700 | 557 | EX | EMER - INSTALL 10'-4" PMMP | 2021-01-11 | US HWY 60 | A | 1997.1109 | 1315.39 | -681.7209 | -34% | 10 | 5 | 263.078
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026996800 | 558 | EX | EMER - RETIRE 10'-4" PMMP | 2021-01-11 | US HWY 60 | A | 95.6296 | 0 | -95.6296 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026999000 | 566 | EX | RETIRE 4"PLP SERVICE LINE | 2022-09-28 | 405 4TH ST | B | 5007.8601 | 4696.25 | -311.6101 | -6% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026158000 | 555 | EX | INSTALL 200'-2" PMMP | 2022-03-15 | 1056 CRESTWOOD HT | B | 16273.357 | 23838.83 | 7565.473 | 46% | 200 | 102 | 233.714
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026159500 | 557 | EX | EMER - INSTALL 5'-3" PMMP | 2022-01-10 | 1183 US HWY 27 N | A | 5999.0379 | 11760.26 | 5761.2221 | 96% | 5 | 2 | 5880.13
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026159600 | 558 | EX | EMER - RETIRE 5' - 3" PMMP | 2022-01-10 | 1183 US HWY 27 N | A | 79.0999 | 0 | -79.0999 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026162300 | 2000 | EX | INVESTIGATE EASEMENT FOR DKZ | 2023-08-10 | 1495 MUDDY CREEK RD |  | 5000 | 2411.3 | -2588.7 | -52% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026162800 | 2000 | EX | ACQUIRE SITE SURVEY | 2022-12-12 | 724 DUG HILL RD |  | 12301 | 0 | -12301 | 100% |  |  | 0 | CCC# 54722
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026163000 | 573 | EX | INSTALL ODORIZER | 2022-12-16 | 724 DUG HILL RD | F | 596431.4654 | 418702.35 | -177729.1154 | -30% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026164000 | 557 | CO | INSTALL 5,100'-2" PMMP | 2023-11-01 | SCOTT AV | B | 1140024.6985 | 1135773.48 | -4251.2185 | 0% | 5130 | 5229 | 217.2066
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026164201 | 557 | EX | INSTALL 2,300'-2" PMMP | 2023-06-22 | SPRING ST | B | 442002.9907 | 487634.39 | 45631.3993 | 10% | 2310 | 2210 | 220.649
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026164300 | 558 | EX | RETIRE 3,574'-BSLP | 2023-08-01 | SPRING ST | B | 84.9152 | 136.8 | 51.8848 | 61% |  |  | 0
KY | KY - CENTRAL | 2629 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 22026165200 | 575 | EX | ACQUIRE REG STA EASEMENT | 2022-02-09 | 630 CLINTONVILLE RD | F | 25672 | 22954.4 | -2717.6 | -11% |  |  | 0
KY | KY - CENTRAL | 2629 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026168900 | 909 | EX | STEPSTONE POD HVAC UPGRADE | 2022-03-24 | STEPSTONE RD | F | 15710.0767 | 19703.94 | 3993.8633 | 25% |  |  | 0 | CCC# 59338 CCC# 55889 UPGRADED RTU JOSH MULLINS
KY | KY - CENTRAL | 2629 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026169100 | 909 | EX | RT. 89 POD RTU BUILDING | 2023-05-25 | STATE RT 89 | F | 143652.6755 | 221479.78 | 77827.1045 | 54% |  |  | 0 | CCC# 13947 MONITOR NOT ONSITE ACP NOT WORKING AT THAT SITE TODAY CCC# 13947 NOT ONSITE NOT ONSITE CCC#21297 CCC# 31371
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026169400 | 2000 | EX | INVESTIGATE LAND RIGHTS | 2022-10-05 | GAWTHROP DR |  | 3241 | 0 | -3241 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026170600 | 557 | EX | INSTALL 7,200'-2"/4" PMMP | 2023-06-20 | HOLT AV | B | 1129128.3572 | 1526718.34 | 397589.9828 | 35% | 7225 | 7917 | 192.8405
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026170700 | 558 | EX | RETIRE BSLP | 2023-09-14 | HOLT AV | B | 89.0305 | 0 | -89.0305 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026171000 | 2000 | EX | DESIGN RIVER CROSSING | 2022-10-03 | 20 S IRVINE RD |  | 30000 | 0 | -30000 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026172500 | 557 | EX | INSTALL 5'-1" PMMP | 2022-03-02 | 2450 UNION CITY RD | A | 1353.2384 | 4.3 | -1348.9384 | -100% | 5 | 1 | 4.3
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026172600 | 558 | EX | RETIRE 5'-1" PAMP | 2022-03-02 | 2450 UNION CITY RD | A | 66.5954 | 2198.83 | 2132.2346 | 3,202% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026173100 | 2000 | EX | INVESTIGATE ROW | 2023-03-28 | MOY FOO AL | B | 5214 | 0 | -5214 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026173200 | 2000 | EX | INVESTIGATE ROW AND RR PERMIT | 2022-10-05 | SCOTT AV | B | 5214 | 0 | -5214 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026173300 | 2000 | EX | INVESTIGATE ROAD ROW | 2022-09-14 | SPRING ST | B | 5214 | 0 | -5214 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026173400 | 2000 | EX | INVESTIGATE ROW | 2022-09-14 | HOLT AV | B | 5214 | 0 | -5214 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 22026173700 | 909 | EX | 2022 SCADA VISIBILITY PROGRAM | 2022-09-22 | WISEMANTOWN RD | F | 29658.8599 | 28387.14 | -1271.7199 | -4% |  |  | 0 | CCC# 66803 CCC# 66803 MONITOR FOR NEW COMM INSTALL CCC# 80236 INSTALLED NEW MIWI350 EBLANTON 9-22-2022
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026175300 | 584 | EX | RETIRE R-1278 | 2022-12-15 | HIGGINS ST | F | 7307.4769 | 1891.36 | -5416.1169 | -74% |  |  | 0 | PREMISE IS RETIRED. GATHERED INFORMATION FOR CLOSEOUT PAPERWORK. JBRADFORD 12-15-22 CCC# 20387 TICKET# 20387
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026175400 | 584 | EX | RETIRE R-1258 | 2022-08-26 | THOMAS ST | F | 7307.4769 | 114.11 | -7193.3669 | -98% |  |  | 0 | CCC# 77893 STATIONRETIRED PER AMRP PROJECT WSHIMFESSEL 8-26-2022 ALL FACILITIES REMOVE D
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026175500 | 584 | EX | RETIRE R-1275 | 2022-08-26 | SHORT ST | F | 7307.4769 | 648.29 | -6659.1869 | -91% |  |  | 0 | CCC# 77909 RETIRED REG STATION R-1275 ON AMRP PROJECT WSHIMFESSEL 8-26-2022 PREMISE IS RETIRED. GATHERED INFORMATION FOR CAPITOL CLOSEOUT.
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026175600 | 584 | EX | RETIRE R-1256 | 2022-06-17 | HIGGINS ST | F | 7307.4769 | 211.37 | -7096.1069 | -97% |  |  | 0 | STATION RETIRED AND ALL PIPING REMOVED WSHIMFESSEL 06-07-2022
KY | KY - CENTRAL | 2629 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026177400 | 2000 | EX | INVESTIGATE AND AQUIRE EASEMEN | 2022-10-03 | KIRKLAND AV |  | 50000 | 0 | -50000 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026177500 | 557 | EX | EMER - INSTALL 800'-6" CSHP | 2022-09-20 | KY RIVER | B | 663631.3961 | 1030814.44 | 367183.0439 | 55% | 960 | 917 | 1124.1161 | LEVEL 2 VARIANCE EXPLANATION IN WMSDOCS TTOY 2/3/23
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026177600 | 558 | EX | EMER-RETIRE 800'-4" CSHP | 2022-09-20 | KY RIVER | B | 84.9152 | 1361.76 | 1276.8448 | 1,504% |  |  | 0
KY | KY - CENTRAL | 2629 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 22026177700 | 561 | EX | INSTALL 56'-6" PM-LP | 2022-05-16 | 31 W BROADWAY ST | B | 50137.1407 | 100820.74 | 50683.5993 | 101% | 42 | 175 | 576.1185 | OVERRUN EXPLANATION: PROJECT WAS INITIALLY PLANNED FOR 56 FEET OF INSTALL. HOWEVER, 171 FEET OF DIRECTIONAL ROCK BORE WERE REQUIRED INSTEAD WITHOUT A SCOPE CHANGE REQUEST. ADDITIONAL SAW CUT AND CUT AND REMOVE WERE REQUIRED A S WELL. STEEL PLATES WERE NOT ESTIMATED. $7000 OF SEWER CAMERA WERE NOT EST IMATED EITHER SINCE IT WAS INITALLY PLANNED DIFFERENTLY. ALL THIS ADDITIONA L WORK TOOK MORE TIME SO LABOR INCREASED BY $19,000 AND THE OVERHEAD EFFECT OF THESE CHANGES WAS $9000.
KY | KY - CENTRAL | 2629 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 22026177800 | 562 | EX | ABDN 20'-6" BS-LP | 2022-05-16 | 31 W BROADWAY ST | B | 73.9724 | 142.7 | 68.7276 | 93% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026178200 | 555 | EX | INSTALL 850'-2" PMIP | 2022-05-17 | 1006 WARRIORS TR LT48 | B | 33743.7503 | 28727.79 | -5015.9603 | -15% | 850 | 773 | 37.164
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026182101 | 555 | EX | INSTALL 8,450' - 2"/4" PMMP | 2023-09-19 | 2130 MCCLURE RD | B | 861854.0803 | 940113.78 | 78259.6997 | 9% | 8505 | 7986 | 117.7202
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026183800 | 555 | EX | INSTALL 100'-2" PMIP | 2022-07-21 | 421 S WINN AV | B | 18017.5748 | 16969.45 | -1048.1248 | -6% | 125 | 91 | 186.4775
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026184000 | 561 | EX | INSTALL 200'-6"/8" PMLP | 2022-08-24 | MAIN ST | B | 169438.8752 | 210431.38 | 40992.5048 | 24% | 240 | 215 | 978.7506 | OVERRUN EXPLANATION: PROJECT WAS PLANNED FOR 360 HOURS OF LABOR TIME BUT ENDED UP WITH 565 HOURS DUE TO MULTIPLE COORDINATORS AND WELDER CHARGING 125 HOURS, SEGA WAS ORIGINALLY $20,641 BUT ENDED UP AT $34,463, PROJECT REQUIRED 698 TONS OF STONE AND DUST BUT WAS ORIGINALLY PLANNED FOR 60 TONS, ADDITIONAL EXTRA DEPTH UNITS OF 134, PROJECT ALSO CHAR CHARGED ~$6,000 OF SEWER CAMERA EVEN THOUGH THE SEWER WAS ALREADY UNCOVERED WHICH IS WHY WE WERE INSTALLING THE RELOCATION. TTOY 2/3/23
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026184100 | 562 | EX | RETIRE 100'-BSLP | 2022-08-24 | MAIN ST | B | 65.0112 | 400 | 334.9888 | 515% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026184200 | 0001 | EX | MATERIAL FOR KY RIVER BORE | 2022-10-03 | KY RIVER |  | 100000 | 0 | -100000 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026185100 | 557 | EX | INSTALL 10'-2" PMMP | 2022-05-10 | 4760 LEVEE RD | A | 3850.4525 | 6123.2 | 2272.7475 | 59% | 30 | 2 | 3061.6
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026185200 | 558 | EX | RETIRE 10'-2" PMP | 2022-05-10 | 4760 LEVEE RD | A | 74.2578 | 0 | -74.2578 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026188100 | 0001 | EX | KA-2 WIRE-LINE PIGGING | 2022-11-03 |  | A | 2479.682 | 0 | -2479.682 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026188800 | 2000 | EX | INVESTIGATE ENCROACHMENT | 2022-08-12 | 302 JEREMIAH DR |  | 4510 | 0 | -4510 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026190400 | 0001 | EX | COMBINE 32010039 & 32010023 | 2023-09-21 | RIDINGS RD |  | 8563.1746 | 0 | -8563.1746 | 100% |  |  | 0 | TWALKER/KY 09-21-23: THIS JOB ORDER DOCUMENTS THE DOWNRATE OF 32010039 FROM MAOP OF 60PSIG TO 45PSIG AND COMBINE WITH SYSTEM 32010023 (MAOP 45PSIG TWO SYSTEM TIED TOGETHER VIA JOB 22-0261621-01 WITH PROJECT ID 22-88186. GAS SYSTEM PLANNING HAS MOVED ALL CUSTOMER TO 32010023 AND WILL MOVE 32010039 TO INACTIVE STATUS ON DIS CONTROL TABLES.
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026190700 | 559 | EX | INSTALL 4" SS *PAPER ONLY*** | 2021-08-02 | BROADWAY ST | B | 84.2578 | 0 | -84.2578 | 100% |  |  | 0 | FACILITY CREATED ON JO 20-0269816-01. UNABLE TO EDIT. SS ALREADY ABANDONED ON JO 22-0261909-00 BEFORE THIS JO WAS CREATED.
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026190800 | 557 | EX | INSTALL 50'-4" PMLP | 2022-07-20 | 199 BROADWAY ST | B | 45570.6341 | 48441.53 | 2870.8959 | 6% | 55 | 43 | 1126.5472
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026190900 | 558 | EX | RETIRE 41'-4" BSLP | 2022-07-20 | 199 BROADWAY ST | B | 78.4365 | 114.59 | 36.1535 | 46% |  |  | 0
KY | KY - CENTRAL | 2629 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026191300 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-06-21 | N MAPLE ST | F | 4801.1928 | 839.28 | -3961.9128 | -83% |  |  | 0 | CCC# 71072
KY | KY - CENTRAL | 2629 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026191400 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-06-21 | N MAPLE ST | F | 124.8731 | 0 | -124.8731 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026192500 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-06-22 | MAIN ST | F | 4801.1928 | 400.52 | -4400.6728 | -92% |  |  | 0 | CCC# 71244
KY | KY - CENTRAL | 2629 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026192600 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-06-22 | MAIN ST | F | 124.8731 | 0 | -124.8731 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026194600 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-10-12 | HWY 977 | F | 4801.1928 | 4024.88 | -776.3128 | -16% |  |  | 0 | CCC# 3219 INSTALLED MIWI INSTALLED NEW MIWI350 WSHINFESSEL 10-12-22
KY | KY - CENTRAL | 2629 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026194700 | 910 | EX | RETIRED ELECTRONIC EXCHANGE | 2022-10-12 | HWY 977 | F | 124.8731 | 0 | -124.8731 | 100% |  |  | 0 | RETIRED OLD ERX WSHINFESSEL 10-12-22
KY | KY - CENTRAL | 2629 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026194800 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-08-25 | 555 ROLLING HILLS DR | F | 4801.1928 | 5891.93 | 1090.7372 | 23% |  |  | 0 | CCC# 78666 INSTALLED NEW MIWI350 JPASLEY 8-25-22
KY | KY - CENTRAL | 2629 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026194900 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-08-25 | 555 ROLLING HILLS DR | F | 124.8731 | 0 | -124.8731 | 100% |  |  | 0 | RETIRED ERX INSTALLED NEW MIWI350 JPASLEY 8-25-22
KY | KY - CENTRAL | 2629 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026195200 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-10-21 | GAWTHROP DR | F | 4801.1928 | 6702.65 | 1901.4572 | 40% |  |  | 0 | CCC# 4229 CCC# 4229 INSTALLED NEW MIWI350 JPASLEY
KY | KY - CENTRAL | 2629 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026195300 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-10-21 | GAWTHROP DR | F | 124.8731 | 34.29 | -90.5831 | -73% |  |  | 0 | CCC# 4229 RETIRED OLD ERX INSTALLED NEW MIWI350 JPASLEY
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026196500 | 2000 | EX | INVESTIGATE R/W | 2022-06-23 | MAIN ST | B | 2818 | 0 | -2818 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026196700 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-08-31 | EWINGTON RD | F | 4801.1928 | 5374.37 | 573.1772 | 12% |  |  | 0 | CCC# 79339 INSTALLED NEW MIWI350. P2P W/GC OK 08/31/2022 WSHIMFE
KY | KY - CENTRAL | 2629 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026196800 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-08-31 | EWINGTON RD | F | 124.8731 | 0 | -124.8731 | 100% |  |  | 0 | RETIRED OLD ERX INSTALLED NEW MIWI350 WSHIMFESSEL 8-31-2022
KY | KY - CENTRAL | 2629 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026196900 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-08-26 | LINDEN AV | F | 4801.1928 | 5192.52 | 391.3272 | 8% |  |  | 0 | INSTALLED NEW MIWI350 JPASLEY 8-26-22
KY | KY - CENTRAL | 2629 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026197000 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-08-26 | LINDEN AV | F | 124.8731 | 698.72 | 573.8469 | 460% |  |  | 0 | RETIRED OLD ERX JPASLEY 8-26-22
KY | KY - CENTRAL | 2629 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026198400 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-09-21 | RICHMOND AV | F | 4801.1928 | 5538.33 | 737.1372 | 15% |  |  | 0 | ASSIST WITH RUNNING STAINLESS 09-21-2022 RHAYES CCOX RETIRED OLD ERX INSTALL NEW MIWI350 CCOX 9-21-22
KY | KY - CENTRAL | 2629 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026198500 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-09-21 | RICHMOND AV | F | 124.8731 | 450.09 | 325.2169 | 260% |  |  | 0
KY | KY - CENTRAL | 2629 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026199700 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-09-20 | COUNTY LN | F | 4801.1928 | 5650.33 | 849.1372 | 18% |  |  | 0 | RETIRED OLD ERX INSTALLED NEW MIWI350 EBLANTON 9-20-22
KY | KY - CENTRAL | 2629 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026199800 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-09-20 | COUNTY LN | F | 124.8731 | 592.76 | 467.8869 | 375% |  |  | 0 | RETIRED OLD RX INSTALLED NEW MIWI350 EBLANTON 9-20-22
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026203800 | 2000 | EX | AQUIRE EASEMENT | 2023-08-03 | 409 E MAIN ST | A | 5556 | 2342.6 | -3213.4 | -58% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026205800 | 560 | EX | RETIRE 20'-2" PMP | 2023-09-18 | HOLT AV | B | 89.0305 | 0 | -89.0305 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026205900 | 584 | EX | RETIRE R-1682 | 2023-09-14 | ROGERS AV | F | 1417.3638 | 603.96 | -813.4038 | -57% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026210800 | 2000 | EX | INVESTIGATE LAND RIGHTS | 2022-08-23 | 2130 MCCLURE RD | B | 4228 | 0 | -4228 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026211500 | 557 | EX | EMER-INSTALL 5'-2" PMMP | 2022-07-11 | 164 STRODE STATION CR | A | 16105.0112 | 5656.19 | -10448.8212 | -65% | 5 | 2 | 2828.095
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026211600 | 558 | EX | EMER-RETIRE 5'-2" PMMP | 2022-07-11 | 164 STRODE STATION CR | A | 4031.2726 | 3884.45 | -146.8226 | -4% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026212100 | 577 | EX | INSTALL CHAIN LINK FENCE | 2022-11-11 | EWINGTON RD | F | 24086.2589 | 9226.54 | -14859.7189 | -62% |  |  | 0 | INSTALLED CHAIN LINK FENCE JMULLINS 11-11-22
KY | KY - CENTRAL | 2629 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026214300 | 910 | EX | STEPSTONE POD HVAC/RTU | 2022-03-24 | STEPSTONE RD | F | 55.5311 | 0 | -55.5311 | 100% |  |  | 0 | UPGRADED RTU
KY | KY - CENTRAL | 2629 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 22026217000 | 2000 | EX | INVESTIGATE RIGHT OF WAY | 2022-10-04 | 302 JEREMIAH DR |  | 5000 | 0 | -5000 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026217500 | 557 | EX | EMER-INSTALL 2' OF 3"PMMP MAIN | 2022-08-12 | 175 COLLEGE HILL RD | A | 5764.1191 | 6378.4 | 614.2809 | 11% | 2 | 2 | 3189.2
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026217600 | 558 | EX | EMER-RETIRE 2' OF 3"PAMP MAIN | 2022-08-12 | 175 COLLEGE HILL RD | A | 1084.9152 | 4155.42 | 3070.5048 | 283% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026219700 | 557 | EX | EMER-INSTALL 8" STOPPLE FITS | 2022-08-31 | PARIS BY PASS RD | B | 30183.131 | 39002.9 | 8819.769 | 29% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026219800 | 558 | EX | EMER-RETIRE 1' OF 8"CSHP MAIN | 2022-08-31 | PARIS BY PASS RD | B | 84.9152 | 160 | 75.0848 | 88% |  |  | 0
KY | KY - CENTRAL | 2629 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026221900 | 558 | EX | EMER - RETIRE 20'-3" PMP | 2022-09-03 | 423 OREO | A | 3460.1765 | 6987.81 | 3527.6335 | 102% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026222200 | 2000 | EX | ACQUIRE EASEMENT FOR S/L | 2022-12-19 | 3330 MILLERSBURG RU RD | B | 2536 | 0 | -2536 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026222300 | 557 | EX | EMER - INSTALL 7'-4" PMLP | 2022-08-29 | PLEASANT | A | 4005.634 | 13873.55 | 9867.916 | 246% | 10 | 7 | 1981.9357
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026222400 | 558 | EX | EMER - RETIRE 7'-4" PLP | 2022-08-29 | PLEASANT | A | 89.0305 | 0 | -89.0305 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026223000 | 2000 | EX | IVESTIGATE HP GAS CONFLICT | 2023-11-01 | COLBY RD | B | 11921 | 0 | -11921 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026227600 | 557 | EX | EMER - INSTALL 60'-4" PMLP | 2022-09-28 | 504 S MAPLE ST | B | 30615.0582 | 21421.89 | -9193.1682 | -30% | 60 | 55 | 389.4889
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026227700 | 558 | EX | EMER - RETIRE 60'-4" BSLP | 2022-09-28 | 504 S MAPLE ST | B | 74.3089 | 8123.84 | 8049.5311 | 10,833% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026228201 | 557 | EX | INSTALL 4,225'-2"/6" PMMP | 2023-05-04 | MAPLE ST | B | 1875934.718 | 1935349.38 | 59414.662 | 3% | 6200 | 3901 | 496.1162
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026228300 | 558 | EX | RETIRE 6,106'- LP MAIN | 2023-05-10 | N MAPLE ST | B | 952.0929 | 182.4 | -769.6929 | -81% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026228400 | 558 | EX | RETIRE 1133'- MP MAIN | 2023-05-04 | N MAPLE ST | B | 952.0929 | 0 | -952.0929 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026228700 | 910 | EX | RETIRE ELECTRONIC | 2022-09-29 | LEVEE RD | F | 74.3089 | 0 | -74.3089 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026230301 | 557 | EX | INSTALL 1,725'-2" PMMP | 2023-02-26 | MARSHALL ST | B | 636475.4754 | 676511.46 | 40035.9846 | 6% | 1725 | 1842 | 367.2701
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026230400 | 558 | EX | RETIRE 5,578' - IP MAIN | 2023-03-14 | MARSHALL ST | B | 475.239 | 1019.8 | 544.561 | 115% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026230500 | 558 | EX | RETIRE 1,368' - MP MAIN | 2023-03-14 | RUCKER ST | B | 475.239 | 14.31 | -460.929 | -97% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026231000 | 557 | EX | EMER - INSTALL 1'-2" PMMP | 2022-10-06 | VINE | A | 8585.1316 | 6865.44 | -1719.6916 | -20% | 1 | 2 | 3432.72
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026231100 | 558 | EX | EMER - RETIRE 1'-2" PMP | 2022-10-06 | VINE | A | 60.3089 | 0 | -60.3089 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026232600 | 555 | EX | INSTALL 200'-2" PMMP | 2022-12-16 | 325 GENEVA AV | B | 40586.0582 | 20049.03 | -20537.0282 | -51% | 205 | 166 | 120.7773
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026234100 | 577 | EX | NEW RTU/COMM BUILDING | 2022-09-27 | EARLY DR | F | 136.2135 | 0 | -136.2135 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026234500 | 577 | EX | INSTALL NEW RTU/COMM BUILDING | 2022-09-29 | LEVEE RD | F | 136.2135 | 0 | -136.2135 | 100% |  |  | 0 | JMULLINS COMPLETING PAPERWORK
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026234700 | 559 | EX | INSTALL 3" STOPPLE FITTING | 2022-11-29 | 1107 W LEXINGTON AV | B | 13630.9028 | 7929.81 | -5701.0928 | -42% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026234800 | 560 | EX | RETIRE 75' OF 3"BSMP MAIN | 2022-11-29 | 1107 W LEXINGTON AV | B | 119.2135 | 114.9 | -4.3135 | -4% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026234901 | 555 | EX | INSTALL 4,100'-2" PMMP | 2023-11-10 | DUCLAIR DR LT38 | B | 188453.1623 | 217597.98 | 29144.8177 | 15% | 4110 | 2130 | 102.1587
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026236400 | 555 | EX | INSTALL 450'-4" PMMP | 2023-06-26 | 755 COLLEGE HILL RD | B | 61251.1595 | 52709.69 | -8541.4695 | -14% | 355 | 477 | 110.5025
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026237600 | 2000 | EX | INVESTIGATE LAND & R/W | 2023-06-16 | MUTUAL AV | B | 12684 | 0 | -12684 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026238000 | 2000 | EX | INVESTIGATE R/W | 2023-06-16 | BROADWAY AV | B | 12684 | 0 | -12684 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026240500 | 583 | EX | INSTALL VRG | 2022-12-08 | 724 DUG HILL RD | F | 14784.1417 | 7577.2 | -7206.9417 | -49% |  |  | 0 | NOT ON SITE. GETTING MATERIAL FROM SHOP FOR JOB. CCC# 6417 CCC# 6417 CCC# 6417 CCC# 6417
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026240600 | 584 | EX | RETIRE VRG | 2022-12-08 | 724 DUG HILL RD | F | 1478.5709 | 1416.09 | -62.4809 | -4% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026240700 | 577 | EX | INSTALL FENCE FOR NEW LAND | 2022-11-30 | 724 DUG HILL RD | F | 26194.1417 | 63926.63 | 37732.4883 | 144% |  |  | 0 | CCC# 12436 TICKET# 12436 CCC# 16515 GATHER INFO FOR CAPITAL PAPERWORK
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026244400 | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2023-04-04 | PEA RIDGE RD | F | 26337.6752 | 17382.14 | -8955.5352 | -34% |  |  | 0 | CCC# 22134 WELDED NEW TAP ON INLET FOR MIWI INSTALL, JMARTIN DMARTIN 3-27-23 CCC# 23352 INSTALL NEW MIWI 350, UNIT IS WAITING FOR A TICKET # TO BE ABLE TO PUT ONLINE. JMARTIN 4-4-23 CCC# 23905 STILL NEED TO DO P2P WITH GAS CONTROL, MODEM NOT COMMUNICATING JMARTIN 4-6-23 CCC# 24126 TRIED TO FIX COMM ISSUE WITH MODEM CCC# 23905 P2P W/GAS CONTROL OK, JMARTIN 4-10-23 CCC# 26515 COMP ANOTHER P2P WITH GAS CONTROL. JMARTIN 4-21-23 NOT ONSITE, FIXED ISO AND SUBMITTED NEW CAP FOR DRAWING.
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026244500 | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2023-04-10 | RT 89 | F | 19488.6752 | 17938.12 | -1550.5552 | -8% |  |  | 0 | CCC# 22091 INSTALLED NEW INLET TAP FOR MIWI, JMARTIN DMARTIN 3-27-23 NOT ONSITE DELAY DUE TO RAIN NOT ONSITE ACP RESCHEDULED CCC# 24233 INSTALLED NEW MIWI 350 CCC# 26551 WORKED WITH GC TO GET SITE ONLINE. P2P COMP. JMARTIN 4-21-23 NOT ONSITE, UPDATED ISO AND SBMITTED REDLINED DRAWIN.
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026245300 | 557 | EX | EMER - INSTALL 5'-2" PMMP | 2022-12-19 | 711 COMBS FERRY RD | A | 10393.9744 | 3807.72 | -6586.2544 | -63% | 13 | 3 | 1269.24
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026245400 | 558 | EX | EMER - RETIRE 5'-2" PMMP | 2022-12-19 | 711 COMBS FERRY RD | A | 131.2422 | 0 | -131.2422 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026245700 | 585 | EX | INSTALL BUILDING R-1667 | 2022-08-16 | STATE RT 89 | F | 300.4844 | 651.28 | 350.7956 | 117% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026245800 | 586 | EX | RETIRE MIS FACILITIES R-1639 | 2022-08-16 | STATE RT 89 | F | 131.2422 | 0 | -131.2422 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026248000 | 2000 | EX | ACQUIRE LAND FOR GROUND BED | 2023-10-30 | MAPLE RIDGE DR | B | 11697 | 0 | -11697 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026248100 | 595R | EX | INSTALL GROUND BED | 2023-12-12 | US 60 | B | 149767.3441 | 158415.52 | 8648.1759 | 6% |  |  | 0 | MATCOR CORROSION INSTALLED 300' 8" DEEP WELL DURAMMO ANODE SYSTEM WITH 5000LBS OF COKE BREEZE AND 1300LBS OF PERMA PLUG COARSE / ACTIVE LENGTH OF ANODE BED 200' / MODEL MDM-F200-300-BK040K WITH 40A OUTPUT CAPACITY FOR 30 YEARS / #8HMWPE HALAR LEAD WIRES MAPLE RIDGE RECTIFIER FAC 605693 WAS RETIRED / RECTIFIER SERIAL# 133704 REINSTALLED AT 452 PREWITT PIKE GROUND BED / JMM GROUND BED FAC # 861695 / RMU FAC # 861697 / JMM
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026248700 | 559 | EX | INSTALL 2" SS | 2023-02-14 | HIGHLAND LN | A | 18496.357 | 2373.93 | -16122.427 | -87% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026248800 | 560 | EX | RETIRE 50' - 2" CSMP | 2023-02-14 | HIGHLAND AV | A | 138.8485 | 6678.36 | 6539.5115 | 4,710% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026250900 | 587 | EX | INSTALL EC 350 | 2023-02-07 | 1330 ENTERPRISE DR | F | 2339.3221 | 755.31 | -1584.0121 | -68% |  |  | 0 | INSTALLED NEW EC 350 INSTALLED EC 350 J.BRADFORD 2-7-23
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026251000 | 588 | EX | RETIRE PAPER BILLING CHART | 2023-02-07 | 1330 ENTERPRISE DR | F | 131.2422 | 803.89 | 672.6478 | 513% |  |  | 0 | BILLING CHART REMOVED AND EC 350 INSTALLED
KY | KY - CENTRAL | 2629 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 23026251600 | 577 | EX | INSTALL RTU BUILDING | 2023-05-25 | STATE RT 89 | F | 170.6969 | 2010.08 | 1839.3831 | 1,078% |  |  | 0 | CCC#28635 WORK DONE FOR WHAT THEY ARE DOING TODAY 5-5-23 JUSTIN HOBBS CCC# 31032 CREATED OTH FACID 861369 FOR HVAC. SM 12/1/23
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026252400 | 588 | EX | RETIRE GMB MS#804399 RUN | 2023-02-06 | HWY 977 | F | 2962.0987 | 21780.96 | 18818.8613 | 635% |  |  | 0 | NOT ONSITE NOT ONSITE GATHERING PARTS CCC# 15748 TICKET# 15748 RETIRED GMB SETTING 2-6-23 BY J.BRADFORD
KY | KY - CENTRAL | 2629 | U124399 | Bishop,Steven | Gill,John | Dunn,David | 23026253100 | 559 | CO | PM- GREENSITE TRABU INSTALL | 2022-09-26 | TRABU RD | B | 1236355 | 30739.67 | -1205615.33 | -98% |  | 44 | 698.6289
KY | KY - CENTRAL | 2629 | U124399 | Bishop,Steven | Gill,John | Dunn,David | 23026253200 | 560 | CO | PM- GREENSITE TRABU ABANDON | 2022-09-26 | TRABU RD | B | 0 | 172.67 | 172.67 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U124399 | Bishop,Steven | Gill,John | Dunn,David | 23026253700 | 559 | CO | PM-GREENSITE HWY 27 INSTALL | 2022-09-27 |  | B | 1236355 | 20730.94 | -1215624.06 | -98% |  | 55 | 376.9262
KY | KY - CENTRAL | 2629 | U124399 | Bishop,Steven | Gill,John | Dunn,David | 23026253800 | 560 | CO | PM-GREENSITE HWY 27 ABANDON | 2022-09-27 |  | B | 0 | 0 | 0 | 0% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026263200 | 588 | EX | GMB TO CAB CONVERSION | 2023-05-02 | 2001 OWINGSVILLE RD | F | 124.7348 | 758.88 | 634.1452 | 508% |  |  | 0 | GATHER PARTS INFO 27 - 300,000 BTU HANGING UNIT HEATERS = 8,100,000 3 - 300,000 BTU ROOF TOP UNITS = 900,000 TOTAL BTU LOAD - 9,000,000 GMB TO CAB CONVERSION
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026266800 | 557 | EX | EMER - INSTALL 7'-2" PMMP | 2023-03-03 | 1152 VINE ST | A | 15964.0017 | 537.54 | -15426.4617 | -97% | 2 | 7 | 76.7914
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026266900 | 558 | EX | EMER - RETIRE 7'-2" PMAP | 2023-03-03 | 1152 VINE | A | 64.7348 | 0 | -64.7348 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026267000 | 557 | EX | EMER - INSTALL 2'-2" PMLP | 2023-03-07 | ELM ST | A | 7754.9733 | 1235.74 | -6519.2333 | -84% | 2 | 2 | 617.87
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026267100 | 558 | EX | EMER - RETIRE 2'-2" PLP | 2023-03-07 | ELM ST | A | 64.7348 | 0 | -64.7348 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026267600 | 555 | EX | INSTALL 110'-4"PMLP | 2023-08-31 | 103 WHIRLAWAY DR | B | 46300.0467 | 32525.16 | -13774.8867 | -30% | 150 | 100 | 325.2516
KY | KY - CENTRAL | 2629 | U132257 | McGuire,Chera Lee | Opfer,Matthew | Dunn,David | 23026268700 | 559 | CO | PM-DE LINE PH 2 DENT 2/STPL 3 | 2023-05-23 |  | B | 1307000 | 703157.62 | -603842.38 | -46% |  | 25 | 28126.3048
KY | KY - CENTRAL | 2629 | U132257 | McGuire,Chera Lee | Opfer,Matthew | Dunn,David | 23026269400 | 560 | CO | PM-DE LINE ILI PH2 DENT2,STPL3 | 2023-05-31 |  | C | 216349 | 198957.22 | -17391.78 | -8% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026273200 | 558 | EX | EMER-RETIRE 741'-1" PMP | 2023-04-29 | 2450 UNION CITY RD | A | 1738.6263 | 1327.21 | -411.4163 | -24% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026274800 | 586 | EX | RETIRE REG BUILDING | 2023-05-09 | ALLEY OFF MAIN ST | F | 117.7346 | 0 | -117.7346 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026274900 | 557 | EX | EMER - INSTALL 4'-2" PMMP | 2023-05-15 | LEVEE RD | A | 31722.4446 | 15519.62 | -16202.8246 | -51% | 14 | 4 | 3879.905
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026275000 | 558 | EX | EMER - RETIRE 4'-2" PMMP | 2023-05-15 | LEVEE RD | A | 139.1159 | 2331.35 | 2192.2341 | 1,576% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026275100 | 562 | EX | RETIRE 276'-3" BSLP | 2023-05-23 | S QUEEN ST | B | 12701.243 | 5918.41 | -6782.833 | -53% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026276600 | 910 | EX | RETIRE RTU FACILITY | 2023-11-20 | STATE RT 89 | F | 139.1159 | 2357.33 | 2218.2141 | 1,595% |  |  | 0 | CCC#33813 PICKED UP TRASH CPRRECTED PAPER WORK JPASLEY 11-20-23
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026278500 | 557 | EX | EMER - INSTALL 3'-2" PMMP | 2023-06-06 | 212 BYBEE LOOP | A | 4078.3783 | 3085.38 | -992.9983 | -24% | 3 | 3 | 1028.46
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026278600 | 558 | EX | EMER - RETIRE 3'-2" PMMP | 2023-06-06 | 212 BYBEE LOOP | A | 139.1159 | 10.24 | -128.8759 | -93% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026279900 | 560 | EX | RETIRE 38'-3" PMP | 2023-06-21 | COLLEGE HILL RD | B | 139.1159 | 0 | -139.1159 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026281600 | 557 | EX | EMER-INSTALL 3'-3" PMMP | 2023-06-22 | 100 GRINDSTONE RD | A | 5640.4544 | 5032.43 | -608.0244 | -11% | 3 | 3 | 1677.4767
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026281700 | 558 | EX | EMER-RETIRE 3'-3" PMAP | 2023-06-22 | 100 GRINDSTONE RD | B | 67.1159 | 0 | -67.1159 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026281900 | 903 | EX | INSTALL TWO STORAGE BUILDINGS | 2023-06-29 | 281 SHOPPERS DR | F | 11634.7925 | 14600.26 | 2965.4675 | 25% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026282600 | 558 | EX | EMER - RETIRE 216'-2" PAMP | 2023-06-27 | 413 MIMOSA LN | A | 2153.608 | 5057.99 | 2904.382 | 135% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026286000 | 557 | EX | EMER - INSTALL 6'-2" PMMP | 2023-07-12 | 507 BROOKVIEW DRIVE | A | 14279.5419 | 5456.45 | -8823.0919 | -62% | 30 | 6 | 909.4083
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026286100 | 558 | EX | EMER - RETIRE 6'-2" PMMP | 2023-07-12 | 507 BROOKVIEW DRIVE | A | 67.1159 | 5375.26 | 5308.1441 | 7,909% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026287800 | 559 | EX | INSTALL 500'-4" PMMP | 2023-10-11 | PARIS PK | B | 99252.0533 | 175667.6 | 76415.5467 | 77% | 570 | 1079 | 162.8059
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026287900 | 560 | EX | RETIRE 500'-3" PMP | 2023-10-11 | PARIS PK | B | 119.4953 | 0 | -119.4953 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026288500 | 557 | EX | EMER - INSTALL 3'-2" PMMP | 2023-08-03 | LEVEE | A | 15193.894 | 33.23 | -15160.664 | -100% | 23 | 8 | 4.1537
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026288600 | 558 | EX | EMER - RETIRE 3'-2" PMP | 2023-08-03 | LEVEE | A | 119.4953 | 4237.6 | 4118.1047 | 3,446% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026289200 | 2000 | EX | INVESTIGATE R/W | 2023-09-05 | PARIS PK | B | 2818 | 0 | -2818 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026289900 | 557 | EX | EMER-INSTALL 8'-3" PMMP | 2023-08-17 | 158 COLLEGE HILL RD | A | 1914.647 | 2980.18 | 1065.533 | 56% | 18 | 8 | 372.5225
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026290000 | 558 | EX | EMER-RETIRE 8'-3" PAMP | 2023-08-17 | 158 COLLEGE HILL RD | A | 7157.6376 | 9034.26 | 1876.6224 | 26% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026293900 | 557 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | 2023-09-08 | 159 WESTSIDE DR | A | 14157.3554 | 7147.03 | -7010.3254 | -50% |  | 3 | 2382.3433
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026294000 | 558 | EX | EMER-RETIRE 3' OF 2"PMMP MAIN | 2023-09-08 | 159 WESTSIDE DR | A | 119.4953 | 0 | -119.4953 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026295300 | 586 | EX | RETIRE FENCE | 2023-09-14 | ROGERS AV | F | 119.4953 | 0 | -119.4953 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026297000 | 559 | EX | INSTALL PCF'S LP | 2023-09-14 | HOLT AV | B | 145.9261 | 2982.68 | 2836.7539 | 1,944% |  |  | 0
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026298400 | 909 | EX | INSTALL MODEM AND ANTENNA | 2023-11-20 | STATE RT 89 | F | 8303.7376 | 0 | -8303.7376 | 100% |  |  | 0 | CORRECTED PAPER WORK 11-20-23 JPASLEY
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026301900 | 596 | EX | RETIRE RECTIFIER/GROUND BED | 2023-12-12 | MAPLE RIDGE | F | 122.9261 | 71.79 | -51.1361 | -42% |  |  | 0 | RECTIFIER 605693 RETIRED / GROUND BED AND RECTIFIER RELOCATED TO 452 PREWITT PIKE WITH NEW RECTIFIER FAC 861691 & GROUND BED FAC 861695 / JMM
KY | KY - CENTRAL | 2629 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026302300 | 584 | CO | RETIRE PAPER GAUGE | 2023-11-01 | HWY 977 | F | 989.8688 | 835.24 | -154.6288 | -16% |  |  | 0 | NOT ONSITE WORK POSTPONED TILL TOMMOROW CCC# 49846
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026302800 | 557 | EX | EMER - INSTALL 2'-3" PMP | 2023-10-17 | 17 WESTCHESTER LANE | A | 3855.2637 | 3993.16 | 137.8963 | 4% | 2 | 2 | 1996.58
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026302900 | 558 | EX | EMER - RETIRE 2'-3" PMP | 2023-10-17 | 17 WESTCHESTER LANE | A | 122.9261 | 0 | -122.9261 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026305500 | 0001 | EX | SPECIAL ORDER MATERIAL HOLDING | 2023-12-05 | 201 MILLER DR | B | 100000 | -443.1 | -100443.1 | -100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026306000 | 557 | EX | EMER-INSTALL 2'-3" PMMP | 2023-11-18 | 206 WACO LOOP RD | A | 6158.638 | 6302.19 | 143.552 | 2% | 2 | 2 | 3151.095
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026306100 | 558 | EX | EMER-RETIRE 2'-3" PMMP | 2023-11-18 | 206 WACO LOOP RD | A | 124.9261 | 0 | -124.9261 | 100% |  |  | 0
KY | KY - CENTRAL | 2629 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026306200 | 577 | EX | INSTALL BUILDINGS R-1667 | 2023-11-28 | 724 DUG HILL RD | F | 147.9261 | 0 | -147.9261 | 100% |  |  | 0
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 15026619900 | 561 | EX | INSTALL 575'-8" PHHP | 2020-08-14 | US 60 | B | 428889.7324 | 370465.98 | -58423.7524 | -14% | 575 | 576 | 643.1701 | UNDERRUN EXPLANATION: THIS PROJECT AFFECTED THE INLET SUPPLY TO A STEEL FAC TORY. WHEN THE PROJECT WAS DESIGNED AND RELEASED, WE HAD INTENDED TO USE SO ME HIGH DOLLAR BUY-AMERICA COMPLIANT FITTINGS TO KEEP THE STEEL FACTORY IN GAS. TDW HAD DESIGNED ANSI 600 CLASS FITTINGS INSTEAD OF ANSI 150. IT WAS S UMMER BY THE TIME THE WORK WAS PERFORMED AND THE STEEL FACOTRY WENT TO MINI MUM DEMAND ON WEEKENDS AND WE SCHEDULED THE WORK TO COINCIDE. WE ALLOWED PR ODUCTION GAS TO BACKFEED AND SUPPLY THE GAS TO KEEP THE BLAST FURNACE HOT, BUT WERE ABLE TO SHUT VALVES AND TIE-IN STRAIGHT AND AVOID HAVING TO INSTAL L THE HIGH DOLLAR FITTINGS RESULTING IN AN UNDERRUN.
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 15026620000 | 562 | EX | RETIRE 482'-12"/16" CSHP | 2020-08-14 | US 60 | B | 85.9778 | 2975.92 | 2889.9422 | 3,361% |  |  | 0
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 15026620100 | 561 | EX | INSTALL 1735'-4"/2" PMMP | 2020-06-09 | SR 180 @ US 60 | B | 250393.7292 | 222838.78 | -27554.9492 | -11% | 1735 | 1499 | 148.6583 | 22MAR21: UNDERUN EXPLANATION: THE GREATEST CONTRIBUTORS TO THE UNDERRUN CAME FROM: 1) CJHUGHES' ACTUAL CONTRACT BEING ABOUT $53K LESS THAN ESTIMATED BECAUSE OF LESS ROCK ENCOUNTERED, LESS SAND & STONE BACKFILL REQUIRED, LESS HARD SURFACE RESTORATION NEEDED, AND NO DOZER & LESS TRACKHOE REQUIRED AND 2) $25K IN CONTINGENCY FUNDS THAT WE NOT NEEDED. FORELL'S $20K CLEARING CHARGES, ORIGINALLY ESTIMATED UNDER "OTHER", WAS CAPTURED UNDER CONTRACT LABOR.
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 15026620200 | 562 | EX | RETIRE 1700'-4"/2" PM/CSMP | 2020-06-16 | SR 180 @ US 60 | B | 85.9778 | 65.27 | -20.7078 | -24% |  |  | 0
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 15026620300 | 2000 | EX | US 60-SR 180 CONFLICT ASSESS | 2020-02-14 | US 60 |  | 34586 | 0 | -34586 | 100% |  |  | 0 | 14FEB20: EX'D AND SPLIT CHARGES BTWN 15-0266199-00 AND 15-0266201-00 (BKS) UNDERRUN EXPLANATION: THIS IS AN ERROR. PS&IS WILL ALWAYS UNDERRUN. THEY WI LL BE CHARGED TO EITHER CAPITAL OR OAND M. THIS SHOULD NOT BE ON THIS REPOR T.
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 16026661200 | 2000 | EX | ASSESS CONFLICT FOR NEW SDWLKS | 2020-11-18 | OHIO RIVER RD |  | 7820 | 0 | -7820 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 16026666400 | 587 | EX | INSTALL NEW CWT HEATER | 2022-03-03 | 15035 E OLD US 23 | F | 231341.3745 | 188315.11 | -43026.2645 | -19% |  |  | 0 | CC# 53363. DRAINED WATERBATH HEATER. 01-26-22 DSASH CCC 55246 CCC 55359 CCC 55691 CCC 56098 CCC 57419 NO TICKET NEEDED NO TICKET NEEDED NO TICKET NEEDED CC# 70901. 6/20/22 DSASH RETIRED OLD WATER BATH INSTALLED NEW CWT HEATER DASH 3-3-22
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 16026666500 | 588 | EX | RETIRE EXIST WB HEATER | 2022-03-03 | 15035 E OLD US 23 | F | 140.0254 | 29153.65 | 29013.6246 | 20,720% |  |  | 0 | CCC # 53363 CCC 53705 CCC 54571 CCC # 54571 NO TICKET NEEDED CCC # 57419 NOT ON SITE NO CCC NEEDED NO CCC NOT ON SITE CHARGED TO LE TO GET VRG FOR REG REPLACE INSTALLED NEW CWT HEATER 3-3-22 DASH
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 17026698500 | 909 | EX | INSTALL VRG PRESS CONT EQUIPMT | 2021-06-17 | PIQUA ST | F | 128512.8191 | 247791.39 | 119278.5709 | 93% |  |  | 0 | CC# 27659. 6/11/21 DSASH CCC #27659 CC# 27769. 6/14/21 DSASH CC# 27972. 6/16/21 DSASH CC# 28248. 6/17/21 DSASH CCC #28248 CCC #28445 CC# 28445. 6/18/21 DSASH CC# 28787. 6/23/21 DSASH CCC #28787 NOT AT STATION OFF SITE WORKING ON PAPERWORK FOR JOB 7/1/2021 GCCC TICKET NOT REQUIRED NOT AT STATION OFF SITE COMPLETING PAPERWORK 7/19/21 AND 8/17/21 CFARIS
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 17026698600 | 910 | EX | RETIRE EXIST PRESS CONT EQUIPM | 2021-06-17 | PIQUA ST | F | 131.3267 | 299.36 | 168.0333 | 128% |  |  | 0
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 17026699800 | 577 | EX | INSTALL ELEVATED BUS STOP ASSM | 2021-06-17 | PIQUA ST | F | 61743.3758 | 9561.04 | -52182.3358 | -85% |  |  | 0 | UNDERRUN EXPLANATION: THIS JOB ORDER WAS WORKED IN ONJUNCTION WITH ANOTHER JOB ORDER, 17-0269850-00, WHICH OVERRAN DUE TO THE CONTRACT LABOR BEING CHA RGED TO THAT JOB ORDER INSTEAD. THAT AMOUNT WAS APPROXIMATELY $40,000.
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 17026699900 | 585 | EX | INSTALL NEW CH LINK FENCING | 2021-06-17 | PIQUA ST | F | 20572.3069 | 0 | -20572.3069 | 100% |  |  | 0
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 17026713100 | 2000 | EX | INVESTIGATE MAIN DEPTH | 2019-02-11 | SLASH BRANCH RD |  | 4377.7099 | 0 | -4377.7099 | 100% |  |  | 0 | INVESTIGATION COMPLETED. CONFLICT AVOIDED AND NO FURTHER ACTION REQUIRED. D . LEMONS 2/11/19
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 17026716400 | 2000 | EX | T5 FRIEL CT. LAND RIGHTS | 2020-09-15 | 100 FRIEL CT | A | 2720 | 0 | -2720 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 17026726500 | 557 | EX | INSTALL 922' 6"-PHHP | 2020-11-18 | FRIEL CT | B | 180053.1311 | 150585.72 | -29467.4111 | -16% | 935 | 1036 | 145.353 | UNDERRUN EXPLANATION: THIS PROJECT WAS ESTIMATED FOR ROCK DUE TO TERRAIN EXAMINATION PRE-CONSTRUCTION. THERE WAS NO ROCK ENCOUNTERED IN THE AREA THE PIPE WAS INSTALLED THEREFORE NO ROCK EXCAVATION ASSOCIATED COSTS WERE CHARGED; ALSO NO SIDEBOOM WAS USED
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 17026726600 | 558 | EX | RETIRE 2804'-10" BSHP | 2020-11-18 | FRIEL CT | B | 599.2098 | 286.35 | -312.8598 | -52% |  |  | 0
KY | KY - EAST | 2631 | U127466 | Sparks,Cynthia Joy | Miller,Gary | Belle,Eric | 17026728500 | 558 | EX | RETIRE 2558' - BS/CS/PLP | 2019-04-02 | COGAN ST | B | 69.1112 | 146.09 | 76.9788 | 111% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 17026730701 | 557 | EX | INSTALL 780' 2" PMIP | 2020-06-16 | 5800 US HWY 60 | B | 83787.7101 | 48188.8 | -35598.9101 | -42% | 784 | 695 | 69.3364 | UNDERRUN EXPLANATION: THIS PROJECT WAS ESTIMATED FOR ONE CONTRACTOR WHOSE UNIT COSTS WERE HIGHER THAT THE CONTRACTOR WHO PERFORMED THE WORK LEADING T O THE UNDERRUN OF $36K.
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 17026735602 | 557 | EX | INSTALL 3486'-6" PMIP | 2020-12-15 | 322 BELLEFONTE PRINCESS DR | B | 400560.0388 | 569740.49 | 169180.4512 | 42% | 3494 | 3539 | 160.9891 | LEVEL 2 VARIANCE EXPLANATION COMPLETED AND LOADED INTO WMSDOCS. D.LEMONS 6- 16-2021
KY | KY - EAST | 2631 | U131042 | Bowlin,John Christopher | Tipton,James | Murray,Jennifer | 17026735700 | 558 | EX | RETIRE 3510' MAIN - D243673 | 2021-03-30 | 322 BELLEFONTE PRINCESS DR | B | 78.7024 | 8338.24 | 8259.5376 | 10,495% |  |  | 0
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 17026739300 | 557 | EX | INSTALL 274'- 8" PM/CSMP | 2019-03-27 | 4400 WINCHESTER AV | B | 76197.5408 | 93319.94 | 17122.3992 | 22% | 274 | 328 | 284.512
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 17026739400 | 558 | EX | RETIRE 245'-10"/2" BSMP | 2019-03-27 | 4400 WINCHESTER AV | B | 69.4128 | 132.2 | 62.7872 | 90% |  |  | 0
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 17026739500 | 2000 | EX | 4400 WINCHESTER AV AMRP | 2019-01-14 | 4400 WINCHESTER AV |  | 7592 | 0 | -7592 | 100% |  |  | 0 | 01/14/19: EXECUTED & CHARGED OFF TO 17-0267393-00 (BKSLONE) COMPLETION DATE > COMMIT DATE NO PROBLEM (BKSLONE)
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 17026739600 | 557 | EX | INSTALL 295 -4"/8" PHHP+VALVES | 2019-09-24 | 10048 DOZERMAN DR | B | 117387.4666 | 140058.6 | 22671.1334 | 19% | 295 | 339 | 413.1522
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 17026739700 | 558 | EX | RETIRE 263'-16"/8"/4" CS/BSHP | 2019-09-24 | 10048 DOZERMAN DR | B | 74.1455 | 3661.72 | 3587.5745 | 4,839% |  |  | 0
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 17026739800 | 2000 | EX | DOZERMAN DR LEAKAGE REPLACEMNT | 2019-08-07 | 10048 DOZERMAN DR |  | 10352.3261 | 0 | -10352.3261 | 100% |  |  | 0 | 07AUG19: EASMENT ACCUIRED OVER KEVIN CLARKE PROPERTY BY TAYLOR CLARK
KY | KY - EAST | 2631 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 17026740201 | 557 | EX | INSTALL 1900'-2"PMIP | 2019-03-11 | RIDGE | B | 99934.492 | 127641.85 | 27707.358 | 28% | 1900 | 1861 | 68.5878
KY | KY - EAST | 2631 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 17026740300 | 558 | EX | RETIRE 1887'-2"BSIP | 2019-03-11 | RIDGE | B | 64.7603 | 1758.23 | 1693.4697 | 2,615% |  |  | 0
KY | KY - EAST | 2631 | U131042 | Bowlin,John Christopher | Tipton,James | Murray,Jennifer | 17026742300 | 2000 | EX | INVESTIGATE R/W & SEWER | 2020-02-03 | BELLFONTE PRINCESS DR | B | 5498 | 0 | -5498 | 100% |  |  | 0 | EASEMENTS ACQUIRED. HWY PERMIT SHOULD BE RECIVED IN NEXT 2-3- WEEKS PER PHO NE CALL WITH STATE ENGINEER. D.LEMONS 2/3/20
KY | KY - EAST | 2631 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 18026752700 | 583 | EX | INSTALL VRG PILOT | 2021-06-17 | PIQUA ST | F | 5404.3267 | 5363.35 | -40.9767 | -1% |  |  | 0 | CCC #27769 CCC #28734
KY | KY - EAST | 2631 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 18026752800 | 584 | EX | RETIRE | 2021-06-17 | PIQUA ST | F | 52.1634 | 838.05 | 785.8866 | 1,507% |  |  | 0
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 18026754200 | 595R | EX | INSTALL RECTIFIER | 2019-09-25 | PIQUA ST | A | 14431.6138 | 21767.18 | 7335.5662 | 51% |  |  | 0 | INSTALLED NEW DROP POLE & RECTIFIER 50V/25A (UNIVERSAL) SERIAL #183368 REUSED EXISTING GROUND BED FAC 287748/ REUSED EXISTING STRUCTURE WIRE ALL RELATED TEST STATIONS AND FACILITIES FROM RETIRED REC 287747 WILL BE RELATED TO NEW RECTIFIER MAIN AND GROUND BED NOT EXPOSEED / 09-25-2019 JMM NEW RM4014 INSTALLED WITH FAC #751414
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 18026754300 | 596 | EX | RETIRE RECTIFIER | 2019-09-25 | PIQUA ST | F | 66.1634 | 0 | -66.1634 | 100% |  |  | 0 | RETIRED PIQUA STREET RECTIFIER (GOODALL) FACILITY 287747 09-25-2019 - INSTALLED NEW RECTIFIER AND NEW DROP POLE WITH CAP JOB 18-0267542-00 - GROUND BED FAC 287748 IS ACTIVE AND WILL BE RELATED TO NEWLY INSTALLED RECTIFIER - ALL EXISTING FACILITIES AND RELATED TEST STATIONS WILL BE RELATED TO NEWLY INSTALLED RECTIFIER RETIRED AS A 999 FACILITY BECAUSE FACILTIY WAS RETIRED INCORRECTLY THROUGH "UFA" - WILL COMPLETE FCA TO REMOVE FROM ASSETS. AFMARTI
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 18026759401 | 586 | EX | RETIRE OLD GMB BUILDING | 2020-07-23 | 100 E BIGGS LN | F | 8459.7702 | 0 | -8459.7702 | 100% |  |  | 0 | BUILDING TORN DOWN BY C J HUGHES
KY | KY - EAST | 2631 | U131374 |  |  |  | 18026762300 | 584 | EX | RETIRE PAPER GAUGE | 2020-02-20 | 516 3RD ST RR | F | 146.1887 | 0 | -146.1887 | 100% |  |  | 0
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026762800 | 585 | EX | INSTALL NEW CHAIN LINK FENCE | 2022-08-18 | US ROUTE 60 | F | 17042.1322 | 16843.44 | -198.6922 | -1% |  |  | 0 | MONITORED NEW CHAINLINK FENCE INSTALL AMCCORMICK 8-18-22
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026762900 | 586 | EX | REPLACE CHAIN LINK FENCE | 2022-08-18 | US ROUTE 60 | F | 73.5943 | 429.99 | 356.3957 | 484% |  |  | 0 | MONITORED FENCE REMOVAL AND INSTALL AMCCORMICK 8-18-22
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026764401 | 557 | EX | INSTALL 2000'-10" PMMP | 2019-10-28 | BLACKBURN AV | B | 1012979.8273 | 1040888.94 | 27909.1127 | 3% | 19 | 2060 | 505.2859
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026764500 | 558 | EX | RETIRE 1994'-10" BS&CS | 2019-11-06 | BLACKBURN AV | B | 70.5907 | 180.3 | 109.7093 | 155% |  |  | 0
KY | KY - EAST | 2631 | U131369 |  |  |  | 18026764800 | 909 | EX | INSTALL COMM BUILDING | 2022-06-30 | 8TH STREET | F | 156664.9991 | 132078.26 | -24586.7391 | -16% |  |  | 0 | 72003 INSTALLED RTU BUILDING AND TRANSDUCERS
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 18026766900 | 2000 | EX | ASSESS CONFLICT W/SW CONSTRUCT | 2019-07-02 | RUSSELL RD |  | 6171.8395 | 0 | -6171.8395 | 100% |  |  | 0 | 7/2/19: JEFF PENDLETON COPLETED FIELD SURVEY, DUKE MARTIN COMPELTED CONFLICT ASSESS MENT, AND BRYAN SLONE CREATED ASSOIATED 561'S.
KY | KY - EAST | 2631 | U131374 |  |  |  | 18026769200 | 584 | EX | RETIRE PAPER GAUGE | 2020-03-11 | 624 BIGGS LN | F | 131.2299 | 47910.5 | 47779.2701 | 36,409% |  |  | 0 | RECORDING GAUGE WAS RETIRED 11/2/17 WHEN ERX WAS INSTALLED. PAPERWORK DID NOT GET COMPLETED. THIS JOB IS TO CORRECT WORK MANAGEMENT AND RETIRE THE FACILITY ON PAPER IT APPEARS SOME OF THE LABOR FOR THE ERX GOT APPLIED HERE.
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 18026769400 | 2000 | EX | INVESTIGATE SLIP REPAIR | 2020-11-18 | CHALUPA DR ACCESS ROAD |  | 6641.2117 | 0 | -6641.2117 | 100% |  |  | 0
KY | KY - EAST | 2631 | U131042 | Bowlin,John Christopher | Tipton,James | Murray,Jennifer | 18026769500 | 566 | EX | II ABANDON OR CO SOII | 2020-01-09 | 1401 WINCHESTER AV | A | 5240.2646 | 3657.13 | -1583.1346 | -30% |  |  | 0 | UNDERRUN EXPLANATION: THE ABANDONMENT ONLY TOOK 2.5 HOURS AND 30 HOURS WERE ESTIMATED. THAT IS TE REASON FOR THE UNDERRUN. RETIRED 4" P SL ON THE 2" P BRANCHING TEE. USING 2" EF COUPLING AND DEAD CAP. SOAP TESTED COUPLING AND CAP AT OP. CWHEELE 1-10-2020
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026772300 | 588 | EX | CONVERT FROM GMB TO CAB ACCT | 2022-09-26 | 900 VERNON ST | F | 2583.054 | 725.53 | -1857.524 | -72% |  |  | 0 | CONVERTED GMB TO CAB ACCOUNT INSTALLED NEW 800 METER ON 5# FPCC DASH 9-26-2 2
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026774100 | 559 | EX | INSTALL 25'-4" PMIP | 2019-08-27 | DEER CREEK CT | B | 48783.4232 | 50642.22 | 1858.7968 | 4% | 50 | 50 | 1012.8444
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026774200 | 560 | EX | RETIRE 25' 4" PIP | 2019-08-27 | DEER CREEK CT | B | 74.1455 | 5539.23 | 5465.0845 | 7,371% |  |  | 0
KY | KY - EAST | 2631 | U131042 | Bowlin,John Christopher | Tipton,James | Murray,Jennifer | 18026774500 | 2000 | EX | RESEARCH LAND RIGHTS/SURVEY | 2019-10-07 | DEER CREEK CT | B | 5472 | 0 | -5472 | 100% |  |  | 0
KY | KY - EAST | 2631 | U131042 | Bowlin,John Christopher | Tipton,James | Murray,Jennifer | 18026775800 | 555 | EX | INSTALL 215'-2" PMIP | 2019-09-10 | 2223 JUDY LN LOT 6 | B | 38240.2156 | 27502.38 | -10737.8356 | -28% | 215 | 235 | 117.0314
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026777900 | 557 | EX | INSTALL 20'-6" CSHP-LEAKAGE | 2019-07-18 | 2103 RIVERSIDE DR | B | 60097.6347 | 117680.81 | 57583.1753 | 96% |  | 30 | 3922.6937 | OVERRUN EXPLANATION: THE CONTRACT LABOR WAS WAY UNDERESTIMATED. LEVEL 2 SUBMITTED TO CLOSE OUT
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026778000 | 558 | EX | RETIRE 10'-6" CSHP | 2019-07-19 | RIVERSIDE | B | 59.5221 | 66.1 | 6.5779 | 11% |  |  | 0
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026778100 | 2000 | EX | OBTAIN SEWER RECORDS | 2019-04-30 | BLACKBURN AV |  | 1716 | 0 | -1716 | 100% |  |  | 0
KY | KY - EAST | 2631 | U131042 | Bowlin,John Christopher | Tipton,James | Murray,Jennifer | 18026778900 | 909 | EX | INSTALL ERX & RTU BUILDING | 2021-02-25 | 202 CAROLINE AV | F | 156098.7133 | 113154.12 | -42944.5933 | -28% |  |  | 0 | CC# 13231. 2/25/21 DSASH WORKED ON PAPERWORK OFF SITE. 2/26/21 DSASH EQUIPMENT INSTALLED ON 2/25/21 BY ACP AND DANNY ASH PAPERWORK COMPLETED ON 12/16/2021 BY CYNTHIA FARIS JOB CLOSEOUT DELAYED WAITING ON INFORMATION AND CORRECT ISO SKETCH UNDERRUN EXPLANATION: THE CONTRACT COSTS WERE SIGNIFICANT LESS THAT THE I&C TEAM HAD ORIGINALLY ESTIMATED.
KY | KY - EAST | 2631 | U131042 | Bowlin,John Christopher | Tipton,James | Murray,Jennifer | 18026781701 | 587 | EX | INSTALL MONITOR/CONTROL REGS | 2021-06-22 | US 23 | F | 99301.7623 | 141447.12 | 42145.3577 | 42% |  |  | 0 | CCC TICKET 27187 CCC #27342 CCC #27472 CCC #27636 CCC #27973 CCC TICKET NOT REQUIRED NOT AT STATION 8/4/21
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026781800 | 588 | EX | ABANDON REGULATORS | 2021-06-22 | US 23 | F | 56.3894 | 0 | -56.3894 | 100% |  |  | 0
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 18026783100 | 2000 | EX | ZIP ZONE CONVENIENCE STORE/DQ | 2020-11-18 | ZIP ZONE EXPRESS |  | 5277 | 0 | -5277 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 18026784300 | 2000 | EX | RESEARCH LAND RIGHTS/UTILITES | 2022-11-03 | WASHINGTON ST | B | 2736 | 0 | -2736 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 18026785901 | 557 | EX | INSTALL 1400'-6" PMLP-LEAKAGE | 2020-02-27 | JOHNSON ST | B | 310400.4669 | 428087.51 | 117687.0431 | 38% | 1504 | 1528 | 280.162 | OVERRUN EXPLANATION: THIS POJECT TOOK A LITTLE OVER TWICE THE LABOR HOURS T O COMPLETE OVER WHAT WAS ESTIMATED RESULTING IN $33K IN EXTRA LABOR. ADDITI ONALLY, WE HAD TO GET OUR IN THE STREET MORE THAN ESTIMATED RESULTING IN AN OTHER $60K IN EXTRA PAVING CHARGES.
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 18026786001 | 558 | EX | RETIRE 1400'-6" BSLP | 2020-02-26 | JOHNSON ST | B | 57.3238 | 4474.88 | 4417.5562 | 7,706% |  |  | 0
KY | KY - EAST | 2631 | U131042 | Bowlin,John Christopher | Tipton,James | Murray,Jennifer | 18026786100 | 2000 | EX | INVESTIGATE R/W & UTILITIES | 2020-03-03 | JOHNSON ST | B | 2736 | 0 | -2736 | 100% |  |  | 0
KY | KY - EAST | 2631 | U131042 | Bowlin,John Christopher | Tipton,James | Murray,Jennifer | 18026790500 | 560 | EX | EMERGENCY RETIRE ~10'-2" PMP | 2020-01-09 | 1320 WOLOHAN DR | A | 3245.8243 | 7017.12 | 3771.2957 | 116% |  |  | 0 | RETIRED 77' OF 2" P MP THAT RAN UNDER BUILDING WITH 2" PURGE POINT SOAP TESTED OP 20 PSIG
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 18026791102 | 557 | EX | INSTALL 2,700' - 8" PHHP | 2020-12-22 | 6803 RT168 | B | 623910.1849 | 795163.94 | 171253.7551 | 27% | 2710 | 2804 | 283.582 | 7173 OVERRUN EXPLANATION: THE TOTAL LABOR HOURS INCLUDED ABOUT 100 ADDITIONAL HOURS; THERE WAS ALSO ABOUT $20K IN ADDITIONAL MATERIALS NEEDED TO COMPLETE THE JOB
KY | KY - EAST | 2631 | U127466 | Sparks,Cynthia Joy | Miller,Gary | Belle,Eric | 18026791200 | 558 | EX | RETIRE 2637' - 10" MJHP | 2020-12-22 | 6803 RT168 | B | 72.6127 | 12988.67 | 12916.0573 | 17,788% |  |  | 0
KY | KY - EAST | 2631 | U127466 | Sparks,Cynthia Joy | Miller,Gary | Belle,Eric | 18026791500 | 2000 | EX | INVESTIGATE LAND - T5 AMRP | 2020-09-14 | RT 168 |  | 2736 | 0 | -2736 | 100% |  |  | 0
KY | KY - EAST | 2631 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 18026793500 | 558 | EX | RETIRE 262' - 6" BSLP | 2019-12-12 | BELMONT ST | B | 9413.2712 | 25645.33 | 16232.0588 | 172% |  |  | 0
KY | KY - EAST | 2631 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 18026793901 | 557 | EX | INSTALL 4,123' - 2" PMMP | 2023-10-10 | TEAKWOOD DR | B | 506341.5777 | 603491.8 | 97150.2223 | 19% | 4123 | 4140 | 145.771
KY | KY - EAST | 2631 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 18026794000 | 558 | EX | RETIRE 4748'-2"/3"/4"/6"P-BSLP | 2023-12-04 | TEAKWOOD DR | B | 61.2976 | 110 | 48.7024 | 79% |  |  | 0
KY | KY - EAST | 2631 | U127466 | Sparks,Cynthia Joy | Miller,Gary | Belle,Eric | 18026794100 | 557 | EX | INSTALL 80' - 4" PMLP | 2020-04-01 | 2706 CUMBERLAND AV | B | 69878.1892 | 30729.55 | -39148.6392 | -56% | 88 | 75 | 409.7273 | UNDERRUN EXPLANATION: PROJECT WAS INITIALLY ESTIMATED FOR MUCH MORE CONCRET E AND ASPHAULT. INFACT 250 AND 240 USNITS RESPECTIVELY. NO HARD SURFACE REP ARES WERE USED WHICH THE UNDERRUN INDICATES.
KY | KY - EAST | 2631 | U127466 | Sparks,Cynthia Joy | Miller,Gary | Belle,Eric | 18026794200 | 558 | EX | RETIRE 80' - 4" BSLP | 2020-04-01 | 2706 CUMBERLAND AV | B | 158.1214 | 118.76 | -39.3614 | -25% |  |  | 0
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026800500 | 555 | EX | INSTALL 150'-2" PMLP | 2019-02-06 | 702 DEAL ST | B | 30813.8501 | 64011.45 | 33197.5999 | 108% | 150 | 153 | 418.3755 | HAD TO WAIT ON M&R TECH FOR TIE IN DUE TO LP TIE INS OVERRUN EXPLANATION: THE JOB TOOK 8X LONGER THAN THE LABOR ESTIMATING TOOL PREDICTED RESULTING IN $12K IN TRUCK AND LABOR EXPENSES MORE THAN ESTIMATED . THERE WAS ABOUT $5K IN ADDITIONAL OVERHEADS DUE TO THE ADDITIONAL WORK. T HERE WAS ALSO $8K IN ADDITIONAL PAVING OVER WHAT WAS ESTIMATED.
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026829000 | 583 | EX | INST. FN 5 EXTRA LP OPP | 2019-07-29 | 608 BELLEFONTE RD RR | F | 40101.1646 | 23459.55 | -16641.6146 | -41% | 55 |  | 0 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 7/29/2019 ER350 INSTALLED BY DANY ASH ON 6/18/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/24/2021 GCCC TICKET NOT REQUIRED ON 3/24/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026829100 | 584 | EX | RET. FN 5 FOR EXTRA LP OPP | 2019-07-29 | 608 BELLEFONTE RD RR | F | 53.6219 | 912.82 | 859.1981 | 1,602% |  |  | 0 | REGULATOR REPLACED BY CYNTHIA FARIS ON 7/29/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/24/2021 GCCC TICKET NOT REQUIRED ON 3/24/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026829200 | 583 | EX | INST. FN 7 EXTRA LP OPP | 2019-06-29 | 1403 FRENCH BROAD | F | 40101.1646 | 27074.09 | -13027.0746 | -32% | 55 |  | 0 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 6/29/2019 ER250 INSTALLED BY DANNY ASH ON 6/22/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/25/2021 GCCC TICKET NOT REQUIRED ON 3/25/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026829300 | 584 | EX | RET. FN 7 FOR EXTRA LP OPP | 2019-06-29 | 1403 FRENCH BROAD | F | 53.6219 | 897.57 | 843.9481 | 1,574% |  |  | 0 | REGULATOR REPLACED BY CYNTHIA FARIS ON 6/29/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/25/2021 GCCC TICKET NOT REQUIRED ON 3/25/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026829400 | 583 | EX | INST. FN 10 EXTRA LP OPP | 2019-06-28 | 4639 SHERWOOD DR RR | F | 40101.1646 | 20652.33 | -19448.8346 | -48% | 55 |  | 0 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 6/28/2019 ER350 INSTALLED BY JOSH MULLINS ON 6/16/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/26/2021 GCCC TICKET NOT REQUIRED ON 3/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026829500 | 584 | EX | RET. FN 10 FOR EXTRA LP OPP | 2019-06-28 | 4639 SHERWOOD DR RR | F | 53.6219 | 901.03 | 847.4081 | 1,580% |  |  | 0 | REGULATOR REPLACED BY CYNTHIA FARIS ON 6/28/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/26/2021 GCCC TICKET NOT REQUIRED ON 3/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026829800 | 583 | EX | INST. FN 12 EXTRA LP OPP | 2019-05-31 | 2424 KIRK ST | F | 22950.8722 | 24310.9 | 1360.0278 | 6% | 50 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 5/31/2019 ER350 INSTALLED BY DANNY ASH ON 6/22/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/25/2021 GCCC TICKET NOT REQUIRED ON 3/25/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026829900 | 584 | EX | RET. FN 12 FOR EXTRA LP OPP | 2019-05-31 | 2424 KIRK ST | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 5/31/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/25/2021 GCCC TICKET NOT REQUIRED ON 3/25/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026830000 | 583 | EX | INST. FN 12954 EXTRA LP OPP | 2019-08-05 | 490 FERGUSON RD | F | 43677.1646 | 24967.06 | -18710.1046 | -43% | 52 |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 8/5/19 ER350 INSTALLED BY DANNY ASH ON 6/17/20 PAPERWORK COMPLETED BY CYNTHIA FARIS 2/5/21 GCCC TICKET NOT REQUIRED ON 2/5/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026830100 | 584 | EX | RET. FN 12954 FOR EXTRA LP OPP | 2019-08-05 | 490 FERGUSON RD | F | 53.6219 | 1090.92 | 1037.2981 | 1,934% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 8/5/19 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/5/21 GCCC TICKET NUMBER NOT REQUIRED FOR 2/5/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026830200 | 583 | EX | INST. FN 14 EXTRA LP OPP | 2019-06-03 | 2610 GREENUP AV | F | 22950.8722 | 16717.37 | -6233.5022 | -27% | 50 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 6/3/2019 ER350 INSTALLED BY DANNY ASH ON 6/15/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/26/2021 GCCC TICKET NOT REQUIRED ON 3/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026830300 | 584 | EX | RET. FN 14 FOR EXTRA LP OPP | 2019-06-03 | 2610 GREENUP AV | F | 54.9718 | 1041.3 | 986.3282 | 1,794% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 6/3/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/26/2021 GCCC TICKET NOT REQUIRED ON 3/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026830400 | 583 | EX | INST. FN 16 EXTRA LP OPP | 2019-06-03 | 700 22ND ST | F | 22950.8722 | 17690.8 | -5260.0722 | -23% | 50 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 6/3/2019 ER350 INSTALLED BY DANNY ASH ON 6/23/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/22/2021 GCCC TICKET NOT REQUIRED ON 3/22/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026830500 | 584 | EX | RET. FN 16 FOR EXTRA LP OPP | 2019-06-03 | 700 22ND ST | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 6/3/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/22/2021 GCCC TICKET NOT REQUIRED ON 3/22/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026830600 | 583 | EX | INST. FN 17 EXTRA LP OPP | 2019-06-25 | 1210 PALMER ST | F | 22950.8722 | 23363.12 | 412.2478 | 2% | 50 |  | 0 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 06/25/2019 ER350 INSTALLED BY DANNY ASH ON 06/15/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/12/2021 GCCC TICKET NOT REQUIRED ON 4/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026830700 | 584 | EX | RET. FN 17 FOR EXTRA LP OPP | 2019-06-25 | 1210 PALMER ST | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY CYNTHIA FARIS ON 06/25/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/12/2021 GCCC TICKET NOT REQUIRED ON 4/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026830800 | 583 | EX | INST. FN 18 EXTRA LP OPP | 2019-07-08 | 100 CHESTNUT ST | F | 40101.1646 | 18923.72 | -21177.4446 | -53% | 55 |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 7/8/2019 ER350 INSTALLED BY DANNY ASH ON 6/12/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/26/2021 GCCC TICKET NOT REQUIRED ON 4/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026830900 | 583 | EX | INST. FN 19 EXTRA LP OPP | 2019-07-10 | 1820 WOODLAND AV | F | 40101.1646 | 16207.28 | -23893.8846 | -60% | 55 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 7/10/2019 ER350 INSTALLED BY JOSH MULLINS ON 6/12/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/22/2021 GCCC TICKET NOT REQUIRED ON 3/22/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026831000 | 584 | EX | RET. FN 19 FOR EXTRA LP OPP | 2019-07-10 | 1820 WOODLAND AV | F | 53.6219 | 658.1 | 604.4781 | 1,127% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 7/10/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/22/2021 GCCC TICKET NOT REQUIRED ON 3/22/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026831100 | 583 | EX | INST. FN 20 EXTRA LP OPP | 2020-09-18 | 1220 GREENUP AV ALLEY | F | 40098.1646 | 54629.08 | 14530.9154 | 36% | 55 |  | 0 | REGULATORS AND ER350 INSTALLED BY DANNY ASH ON 9/18/20 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/21 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026831200 | 584 | EX | RET. FN 20 FOR EXTRA LP OPP | 2020-09-18 | 1220 GREENUP AV ALLEY | F | 53.9767 | 747.04 | 693.0633 | 1,284% |  |  | 0 | REGULATORS REPLACED BY DANNY ASH ON 9/18/20 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/21 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026831300 | 583 | EX | INST. FN 21 EXTRA LP OPP | 2019-06-26 | 2254 29TH ST RR | F | 22950.8722 | 19021.59 | -3929.2822 | -17% | 50 |  | 0 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 6/26/2019 ER350 INSTALLED BY DANNY ASH ON 6/17/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/26/2021 GCCC TICKET NOT REQUIRED ON 3/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026831400 | 584 | EX | RET. FN 21 FOR EXTRA LP OPP | 2019-06-26 | 2254 29TH ST RR | F | 54.9718 | 423.6 | 368.6282 | 671% |  |  | 0 | REGULATOR REPLACED BY CYNTHIA FARIS ON 6/26/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/26/2021 GCCC TICKET NOT REQUIRED ON 3/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026831500 | 583 | EX | INST. FN 22 EXTRA LP OPP | 2019-08-02 | 2802 CAMPBELL ST | F | 48480.1646 | 25163.43 | -23316.7346 | -48% | 56 |  | 0 | NO ITEMS ENTERED FILLED OUT BY MISTAKE DISREGARD REGULATOR INSTALLED BY CYNTHIA FARIS ON 8/2/2019 ER350 INSTALLED BY DANNY ASH ON 6/23/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/26/2021 GCCC TICKET NOT REQUIRED ON 3/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026831600 | 584 | EX | RET. FN 22 FOR EXTRA LP OPP | 2019-08-02 | 2802 CAMPBELL ST | F | 53.6219 | 2163.53 | 2109.9081 | 3,935% |  |  | 0 | REGULATOR REPLACED BY CYNTHIA FARIS ON 8/2/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/26/2021 GCCC TICKET NOT REQUIRED ON 3/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026831700 | 583 | EX | INST. FN 23 EXTRA LP OPP | 2019-06-27 | 3441 DOUGLAS ST | F | 22950.8722 | 26454.88 | 3504.0078 | 15% | 50 |  | 0 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 6/27/2019 ER350 INSTALLED BY JOSH MULLINS ON 6/23/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/24/2021 GCCC TICKET NOT REQUIRED ON 3/24/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026831800 | 584 | EX | RET. FN 23 FOR EXTRA LP OPP | 2019-06-27 | 3441 DOUGLAS ST | F | 54.9718 | 446.7 | 391.7282 | 713% |  |  | 0 | REGULATOR REPLACED BY CYNTHIA FARIS ON 6/27/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/24/2021 GCCC TICKET NOT REQUIRED ON 3/24/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026831900 | 583 | EX | INST. FN 24 EXTRA LP OPP | 2019-06-04 | 318 33RD ST | F | 22950.8722 | 17470.8 | -5480.0722 | -24% | 50 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 6/4/2019 ER350 INSTALLED BY DANNY ASH ON 6/15/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/26/2021 GCCC TICKET NOT REQUIRED ON 3/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026832000 | 584 | EX | RET. FN 24 FOR EXTRA LP OPP | 2019-06-04 | 318 33RD ST | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 6/4/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/26/2021 GCCC TICKET NOT REQUIRED ON 3/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026832100 | 583 | EX | INST. FN 25 EXTRA LP OPP | 2019-07-12 | 1108 HALBERT ST RR | F | 40101.1646 | 19390.18 | -20710.9846 | -52% | 55 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 7/10/2019 ER350 INSTALLED BY JOSH MULLINS ON 6/24/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/24/2021 GCCC TICKET NOT REQUIRED ON 3/24/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026832200 | 584 | EX | RET. FN 25 FOR EXTRA LP OPP | 2019-07-12 | 1108 HALBERT ST RR | F | 53.6219 | 642.33 | 588.7081 | 1,098% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 7/12/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/24/2021 GCCC TICKET NOT REQUIRED ON 3/24/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026832300 | 583 | EX | INST. FN 26 EXTRA LP OPP | 2019-07-30 | 2313 BELMONT ST RR | F | 43801.1646 | 22183.57 | -21617.5946 | -49% | 55 |  | 0 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 7/30/2019 ER350 INSTALLED BY JOSH MULLINS ON 6/24/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/24/2021 GCCC TICKET NOT REQUIRED ON 3/24/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026832400 | 584 | EX | RET. FN 26 FOR EXTRA LP OPP | 2019-07-30 | 2313 BELMONT ST RR | F | 53.6219 | 982.94 | 929.3181 | 1,733% |  |  | 0 | REGULATOR REPLACED BY CYNTHIA FARIS ON 7/30/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/24/2021 GCCC TICKET NOT REQUIRED ON 3/24/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026832500 | 583 | EX | INST. FN 27 EXTRA LP OPP | 2019-07-09 | 413 39TH ST | F | 40101.1646 | 27487.7 | -12613.4646 | -31% | 55 |  | 0 | CCC#14002 CC# 14002. REPLACED ER-350. 3/4/21 DSASH 14002CCC REGULATOR REPLACED BY RYAN WILLIAMS ON 7/9/2019 ER350 INSTALLED BY DANNY ASH ON 6/16/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/24/2021 GCCC TICKET NOT REQUIRED ON 3/24/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026832600 | 584 | EX | RET. FN 27 FOR EXTRA LP OPP | 2019-07-09 | 413 39TH ST | F | 53.6219 | 1111.15 | 1057.5281 | 1,972% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 7/9/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/24/2021 GCCC TICKET NOT REQUIRED ON 3/24/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026832700 | 583 | EX | INST. FN 28 EXTRA LP OPP | 2019-07-31 | 1712 BLACKBURN AV RR | F | 43801.1646 | 27778.09 | -16023.0746 | -37% | 55 |  | 0 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 7/31/2019 ER350 INSTALLED BY DANNY ASH ON 6/17/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/22/2021 GCCC TICKET NOT REQUIRED ON 3/22/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK 3/22/21 CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026832800 | 584 | EX | RET. FN 28 FOR EXTRA LP OPP | 2019-07-31 | 1712 BLACKBURN AV RR | F | 53.6219 | 869.1 | 815.4781 | 1,521% |  |  | 0 | REGULATOR REPLACED BY CYNTHIA FARIS ON 7/31/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/22/2021 GCCC TICKET NOT REQUIRED ON 3/22/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK 3/22/21 CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026832900 | 583 | EX | INST. FN 29 EXTRA LP OPP | 2020-07-07 | 2925 NEWMAN ST RR | F | 42364.1646 | 19315.51 | -23048.6546 | -54% | 55 |  | 0 | REGULATOR AND ER350 INSTALLED BY DANNY ASH ON 7/7/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/26/2021 GCCC TICKET NOT REQUIRED ON 3/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026833000 | 584 | EX | RET. FN 29 FOR EXTRA LP OPP | 2020-07-07 | 2925 NEWMAN ST RR | F | 53.6219 | 4931.18 | 4877.5581 | 9,096% |  |  | 0 | REGULATOR REPLACED BY DANNY ASH ON 7/7/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/26/2021 GCCC TICKET NOT REQUIRED ON 3/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026833100 | 583 | EX | INST. FN 31 EXTRA LP OPP | 2020-06-11 | 210 55TH ST | F | 23795.1646 | 23067.9 | -727.2646 | -3% | 50 |  | 0 | REGULATOR AND ER350 INSTALLED BY DANNY ASH ON 6/11/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/8/2021 GCCC TICKET NOT REQUIRED ON 4/8/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026833200 | 584 | EX | RET. FN 31 FOR EXTRA LP OPP | 2020-06-11 | 210 55TH ST | F | 53.9767 | 8050 | 7996.0233 | 14,814% |  |  | 0 | REGULATORS REPLACED BY DANNY ASH ON 6/11/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/8/2021 GCCC TICKET NOT REQUIRED ON 4/8/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026833300 | 583 | EX | INST. FN 32 EXTRA LP OPP | 2020-09-30 | 2510 CENTER ST RR | F | 43700.1646 | 36471.48 | -7228.6846 | -17% | 54 |  | 0 | REGULATORS REPLACED BY DANNY ASH ON 9/30/21 ER350 NOT INSTALLED STATION HAS EXISTING ERX PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/6/21 GCCC TICKET NOT REQUIRED ON 7/6/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026833400 | 584 | EX | RET. FN 32 FOR EXTRA LP OPP | 2020-09-30 | 2510 CENTER ST RR | F | 53.9767 | 1170.61 | 1116.6333 | 2,069% |  |  | 0 | REGUALTORS REPLACED BY DANNY ASH ON 9/30/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/6/2021 GCCC TICKET NOT REQUIRED ON 7/6/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026833500 | 583 | EX | INST. FN 33 EXTRA LP OPP | 2020-07-06 | 1418 CENTER ST RR | F | 40101.1646 | 27276.55 | -12824.6146 | -32% | 55 |  | 0 | REGULATOR AND ER350 INSTALLED BY DANNY ASH ON 7/6/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/9/2021 GCCC TICKET NOT REQUIRED ON 4/9/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026833600 | 584 | EX | RET. FN 33 FOR EXTRA LP OPP | 2020-07-06 | 1418 CENTER ST RR | F | 53.6219 | 575.47 | 521.8481 | 973% |  |  | 0 | REGULATOR REPLACED BY DANNY ASH ON 7/6/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/9/2021 GCCC TICKET NOT REQUIRED ON 4/9/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026833700 | 583 | EX | INST. FN 35 EXTRA LP OPP | 2020-07-08 | 4570 LOUISA RD | F | 40101.1646 | 38079.03 | -2022.1346 | -5% | 55 |  | 0 | CC# 15636. 3/18/21 DSASH CCC 15636 REGULATOR AND ER350 INSTALLED BY JOSH MULLINS ON 7/8/2020 REGULATOR REPLACED BY DANNY ASH ON 3/19/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/31/2021 GCCC TICKET NOT REQUIRED ON 3/31/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026833800 | 584 | EX | RET. FN 35 FOR EXTRA LP OPP | 2020-07-08 | 4570 LOUISA RD | F | 53.6219 | 638.4 | 584.7781 | 1,091% |  |  | 0 | REGULATOR REPLACED BY JOSH MULLINS ON 7/8/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/31/2021 GCCC TICKET NOT REQUIRED ON 3/31/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026834100 | 583 | EX | INST. FN 154 EXTRA LP OPP | 2020-09-17 | 1106 POWELL LN | F | 46766.1646 | 20075.5 | -26690.6646 | -57% | 53 |  | 0 | REGULATORS AND ER350 INSTALLED BY JOSH MULLINS ON 9/17/20 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/21 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026834200 | 584 | EX | RET. FN 154 FOR EXTRA LP OPP | 2020-09-17 | 1106 POWELL LN | F | 53.6219 | 131.93 | 78.3081 | 146% |  |  | 0 | REGULATORS REPLACED BY JOSH MULLINS ON 9/17/20 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/21 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026834700 | 583 | EX | INST. FN 157 EXTRA LP OPP | 2019-06-11 | 501 RAILROAD ST RR | F | 22950.8722 | 20878.98 | -2071.8922 | -9% | 50 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 06/11/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/23/2021 GCCC TICKET NOT REQUIRED ON 3/23/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026834800 | 584 | EX | RET. FN 157 FOR EXTRA LP OPP | 2019-06-11 | 501 RAILROAD ST RR | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 6/11/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/23/2021 GCCC TICKET NOT REQUIRED ON 3/23/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026834900 | 583 | EX | INST. FN 158 EXTRA LP OPP | 2019-06-06 | 831 POND RUN RD | F | 22950.8722 | 35558.27 | 12607.3978 | 55% | 50 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 06/06/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/22/2021 GCCC TICKET NOT REQUIRED ON 3/22/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026835000 | 583 | EX | INST. FN 12957 EXTRA LP OPP | 2019-06-24 | 516 3RD ST RR | F | 21579.1646 | 33671.59 | 12092.4254 | 56% | 50 |  | 0 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 6/24/2019 ER350 INSTALLED BY SHANE GIORDIANO ON 6/30/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/23/2021 GCCC TICKET NOT REQUIRED ON 3/23/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026835100 | 584 | EX | RET. FN 12957 FOR EXTRA LP OPP | 2019-06-24 | 516 3RD ST RR | F | 64.3463 | 0 | -64.3463 | 100% |  |  | 0 | REGULATOR REPLACED BY CYNTHIA FARIS ON 6/24/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/23/2021 GCCC TICKET NOT REQUIRED ON 3/23/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026835200 | 583 | EX | INST. FN 160 EXTRA LP OPP | 2020-07-01 | 463 FERRY ST | F | 40101.1646 | 28453.14 | -11648.0246 | -29% | 55 |  | 0 | CLEARNCE 4817 REGULATOR AND ER350 INSTALLED BY JOSH MULLINS ON 7/1/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/24/2021 GCCC TICKET NOT REQUIRED ON 3/24/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026835300 | 584 | EX | RET. FN 160 FOR EXTRA LP OPP | 2020-07-01 | 463 FERRY ST | F | 53.6219 | 659.11 | 605.4881 | 1,129% |  |  | 0 | REGULATOR REPLACED BY JOSH MULLINS ON 7/1/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/24/2021 GCCC TICKET NOT REQUIRED ON 3/24/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026835400 | 583 | EX | INST. FN 167 EXTRA LP OPP | 2019-06-10 | 515 LACKEY AV RR | F | 21708.8722 | 22863.71 | 1154.8378 | 5% | 50 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 6/10/2019 ER350 INSTALLED BY DANNY ASH ON 6/10/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/31/2021 GCCC TICKET NOT REQUIRED ON 3/31/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026835500 | 584 | EX | RET. FN 167 FOR EXTRA LP OPP | 2019-06-10 | 515 LACKEY AV RR | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 6/10/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/31/2021 GCCC TICKET NOT REQUIRED ON 3/31/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026835600 | 583 | EX | INST. FN 168 EXTRA LP OPP | 2020-06-10 | 106 JEFFERSON ST | F | 40101.1646 | 51366.67 | 11265.5054 | 28% | 55 |  | 0 | CCC TICKET NOT REQUIRED NOT AT STATION 4/7/21 CFARIS CCC TICKET NOT REQUIRED ON 4/8/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS REGULATORS AND ER350 INSTALLED BY DANNY ASH ON 6/10/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/8/2021
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026835700 | 584 | EX | RET. FN 168 FOR EXTRA LP OPP | 2020-06-10 | 106 JEFFERSON ST | F | 53.6219 | 10015.27 | 9961.6481 | 18,578% |  |  | 0 | REGULATORS REPLACED BY DANNY ASH ON 6/10/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/8/2021 GCCC TICKET NOT REQUIRED ON 4/8/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026835800 | 583 | EX | INST. FN 216 EXTRA LP OPP | 2019-05-30 | 419 BUCKLEY RD | F | 21708.8722 | 19141.51 | -2567.3622 | -12% | 50 |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 5/30/2019 ER350 INSTALLED BY DANNY ASH ON 6/22/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/24/2021 GCCC TICKET NOT REQUIRED ON 3/24/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026835900 | 584 | EX | RET. FN 216 FOR EXTRA LP OPP | 2019-05-30 | 419 BUCKLEY RD | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 5/30/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/24/2021 GCCC TICKET NOT REQUIRED ON 3/24/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026836000 | 583 | EX | INST. FN 13023 EXTRA LP OPP | 2019-06-04 | LAUREL ST | F | 21708.8722 | 21342.27 | -366.6022 | -2% | 50 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 06/04/2019 ER350 INSTALLED BY DANNY ASH ON 06/29/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 03/24/2021 GCCC TICKET NOT REQUIRED ON 3/24/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026836100 | 584 | EX | RET. FN 13023 FOR EXTRA LP OPP | 2019-06-04 | LAUREL ST | F | 54.9718 | 38.39 | -16.5818 | -30% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 06/04/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 03/24/2021 GCCC TICKET NOT REQUIRED ON 3/24/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026836200 | 583 | EX | INST. FN 12819 EXTRA LP OPP | 2019-06-01 | 320 ELM ST | F | 21708.8722 | 26819.01 | 5110.1378 | 24% | 50 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 06/01/2019 ER350 INSTALLED BY JOSH MULLINS ON 08/30/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 03/23/2021 GCCC TICKET NOT REQUIRED ON 3/23/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026836300 | 584 | EX | RET. FN 12819 FOR EXTRA LP OPP | 2019-06-01 | 320 ELM ST | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 06/01/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/23/2021 GCCC TICKET NOT REQUIRED ON 3/23/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026836400 | 583 | EX | INST. FN 12813 EXTRA LP OPP | 2019-06-11 | 964 US 23 | F | 21708.8722 | 21946.94 | 238.0678 | 1% | 50 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 6/11/2019 ER350 INSTALLED BY DANNY ASH ON 6/29/20 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/24/2021 GCCC TICKET NOT REQUIRED ON 3/24/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026836500 | 583 | EX | INST. FN 12831 EXTRA LP OPP | 2019-05-30 | 900 ENGLAND LN | F | 21708.8722 | 25544.43 | 3835.5578 | 18% | 50 |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 5/30/2019 ER350 INSTALLED BY JOSH MULLINS ON 10/30/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/8/2021 GCCC TICKET NOT REQUIRED ON 4/8/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026836600 | 584 | EX | RET. FN 12831 FOR EXTRA LP OPP | 2019-05-30 | 900 ENGLAND LN | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 5/30/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/8/2021 GCCC TICKET NOT REQUIRED ON 4/8/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026836700 | 583 | EX | INST. FN 254 EXTRA LP OPP | 2019-08-03 | 309 PIKE ST RR | F | 35132.1646 | 16574.39 | -18557.7746 | -53% | 55 |  | 0 | REGULATOR INSTALLED BY CYNTHIA FARIS ON 8/3/2019 ER350 INSTALLED BY DANNY ASH ON 6/8/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/31/2021 GCCC TICKET NOT REQUIRED ON 3/31/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026836800 | 584 | EX | RET. FN 254 FOR EXTRA LP OPP | 2019-08-03 | 309 PIKE ST RR | F | 53.6219 | 969.39 | 915.7681 | 1,708% |  |  | 0 | REGULATOR REPLACED BY CYNTHIA FARIS ON 8/3/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/31/2021 GCCC TICKET NOT REQUIRED ON 3/31/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026836900 | 583 | EX | INST. FN 804 EXTRA LP OPP | 2019-07-11 | 1900 29TH ST RR | F | 40101.1646 | 21958.17 | -18142.9946 | -45% | 55 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 7/11/2019 ER350 INSTALLED BY JOSH MULLINS ON 6/16/2020 PAPERWORK COMPLETD BY CYNTHIA FARIS ON 3/26/2021 GCCC TICKET NOT REQUIRED ON 3/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026837000 | 584 | EX | RET. FN 804 FOR EXTRA LP OPP | 2019-07-11 | 1900 29TH ST RR | F | 53.6219 | 679.48 | 625.8581 | 1,167% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 7/11/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/26/2021 GCCC TICKET NOT REQUIRED ON 3/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026841100 | 584 | EX | RET. FN 18 FOR EXTRA LP OPP | 2019-07-08 | 100 CHESTNUT ST | F | 53.6219 | 1366.74 | 1313.1181 | 2,449% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 7/8/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 4/26/2021 GCCC TICKET NOT REQUIRED ON 4/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026841200 | 584 | EX | RET. FN 158 FOR EXTRA LP OPP | 2019-06-06 | 831 POND RUN RD | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 6/6/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/22/2021 GCCC TICKET NOT REQUIRED ON 3/22/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026841300 | 584 | EX | RET. FN 12813 FOR EXTRA LP OPP | 2019-06-11 | 964 US 23 | F | 54.9718 | 0 | -54.9718 | 100% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 6/11/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 3/24/2021 GCCC TICKET NOT REQUIRED ON 3/24/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026843700 | 557 | EX | INSTALL 8200' OF 2"PMMP MAIN | 2019-07-26 | MEADE ST | B | 645599.7026 | 667631.39 | 22031.6874 | 3% | 8200 | 8177 | 81.6475
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026843800 | 558 | EX | RETIRE 9500' OF 4"/6"BSLP | 2019-09-17 | MEADE ST | B | 62.7467 | 5295.39 | 5232.6433 | 8,339% |  |  | 0
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 18026844201 | 557 | EX | INSTALL 1619'-4"/2" PMLP | 2019-05-16 | WILLIAMS AV | B | 271601.8206 | 246337.53 | -25264.2906 | -9% | 1619 | 1742 | 141.4108
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 18026844301 | 558 | EX | RETIRE 1195'-4"/3" BS/CSLP | 2019-07-02 | WILLIAMS AV | B | 79.9756 | 1626.33 | 1546.3544 | 1,934% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 18026844501 | 557 | EX | INSTALL 2478'-4" PMLP | 2020-04-27 | OAKVIEW RD | B | 400557.4129 | 651316.9 | 250759.4871 | 63% | 2496 | 2530 | 257.4375 | OVERRUN EXPLANATION: TOTAL LABOR WAS ABOUT TWICE WHAT WAS ESTIMATED. ADDITI ONALLY CONTRACT COST WAS ABOUT TWICE AS MUCH AS WELL. THE PROJECT WAS ESTIM ATED UNDER A 2018 CONTRACT, BUT WORKED UNDER A 2020 CONTRACT. THERE WERE 57 0 MORE FLAGGER HOURS THAN ESTIMATED AND SIGNFICANTLY MORE COLD PATCH AND OT HER HARD SURFACE REPAIRS THAT ESTIMATED. FINALLY, THE OVERHEAD EFFECT FROM ALL THESE OVERRUNS CONTRIBUTED AS WELL.
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 18026844600 | 558 | EX | RETIRE 3103'-6"/4"/3"BS/CS/PLP | 2020-06-04 | OAKVIEW RD | B | 81.1779 | 640.63 | 559.4521 | 689% |  |  | 0
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026844900 | 2000 | EX | INVESTIGATE MAIN DEPTH | 2021-11-18 | HWY 3 | A | 3663.1174 | 0 | -3663.1174 | 100% |  |  | 0
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026846700 | 2000 | EX | INVESTIGATE LAND RIGHTS | 2019-03-04 |  |  | 2235.2882 | 0 | -2235.2882 | 100% |  |  | 0 | R/W DEFINED AND CUSTOMER METER LOCATION DETERMINED. DELAY IN STAKING DUE TO WEATHER THROUGHOUT WINTER MONTHS. D.LEMONS 3/4/19
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026846900 | 555 | EX | INSTALL 200'-2" PMIP | 2019-10-21 | 161 WILLOW DR | B | 14331.1641 | 47178.86 | 32847.6959 | 229% | 205 | 275 | 171.5595 | OVERRUN EXPLANATION: JOB WAS ESTIMATED FOR 40 HRS, BUT TOOK 110 HRS. APPROX IMATELY 75 FEET OF ADDITIONAL MAIN WAS INSTALLED. COST OVERRUN MAINLY CONTR IBUTED TO ADDITIONAL 30 HRS OF 3 MAN CREW, 198 UNITS OF EXTRA DEPTH AND ERR OSION CONTROL DEVICES NOT ORIGINALLY ESTIMATED (APPROXIMATELY $22,000). THE ADDITIONAL LABOR HOURS, OTHER COST AND SEGA ACOUNT FOR APPROXIMATELY $8,000 MORE IN OVERALL COST. D.LEMONS 3/4/2020
KY | KY - EAST | 2631 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 18026848100 | 575 | EX | ACQUIRE LAND FOR USS | 2020-03-10 | 4639 SHERWOOD DR RR | F | 5291 | 11183.58 | 5892.58 | 111% |  |  | 0
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026850200 | 2000 | EX | PM BRAIDY INDUSTRIES PROJECT | 2020-11-18 | 1 MARKWEST DR |  | 45000 | 0 | -45000 | 100% |  |  | 0 | TWALKER/KY 11-18-20: THIS WAS PM/LARGE PROJECT NEW BUSINESS PROJECT THAT CUSTOMER WENT WITH AN OTHER GAS COMPANY.
KY | KY - EAST | 2631 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026851900 | 909 | EX | UPGRADE COMM EQUIPMENT | 2020-04-23 | 516 3RD ST RR | F | 8776.5399 | 16447.96 | 7671.4201 | 87% |  |  | 0 | GAS CONTROL DID NOT HAVE CHANGES DONE IN SCADA TO BE ABLE TO PLACE ON LINE
KY | KY - EAST | 2631 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026852000 | 910 | EX | RETIRE 2G/3G EQUIPMENT | 2020-04-23 | 516 3RD ST RR | F | 167.0708 | 0 | -167.0708 | 100% |  |  | 0 | GAS CONTROL NOT READY WITH SCADA UPDATES
KY | KY - EAST | 2631 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026852100 | 909 | EX | UPGRADE COMM EQUIPMENT | 2019-04-05 | US 60 | F | 8776.5399 | 2612.52 | -6164.0199 | -70% |  |  | 0 | MODEM UPGRADED TO RV50 BY ACP
KY | KY - EAST | 2631 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026852700 | 909 | EX | UPGRADE COMM EQUIPMENT | 2019-12-31 | SKYLINE DR | F | 8776.5399 | 3037.75 | -5738.7899 | -65% |  |  | 0 | EQUIPMENT INSTALLED BY ACP
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026855301 | 909 | EX | INSTALL RTU AND BUILDING | 2022-03-17 | OLD US 23 | F | 182784.6097 | 186001.86 | 3217.2503 | 2% |  |  | 0 | INSTALLED NEW RTU DASH 3-17-22
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026855400 | 910 | EX | RETIRE OLD RTU EQUIPMENT | 2022-03-17 | OLD US 23 | F | 69.4128 | 5219.78 | 5150.3672 | 7,420% |  |  | 0 | INSTALLED NEW COMM BUILDING AND RTU DASH 3-17-22
KY | KY - EAST | 2631 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026855900 | 573 | EX | INSTALL NON-PRIMARY RELIEF | 2019-01-24 | 1001 RIVERSIDE DR | F | 1903.7546 | 5907.62 | 4003.8654 | 210% | 7 |  | 0
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 19026856700 | 560 | EX | RETIRE 2229'-6" CSHP(TC) | 2020-09-18 | SPECIAL METALS LINE | B | 212342.9254 | 110188.4 | -102154.5254 | -48% |  |  | 0 | STONE TICKET #'S FOR 09152020-212036,212757,212654,213134,212035,212034 STONE TICKET #'S FOR 9162020--212711,212763 MISCELLANEOUS DOLLARS AND CENTS PAID FOR GEOTEX, TICKET # 6401 09172020 NAME ON DAILY FOR FORMAN IS MIKE SHOPE NOT MIKE SPENCE MISCELLANEOUS DOLLARS AND CENTS PAID FOR JOB COST OF 76,600 AND VAC TRUCK F OR 4,052.23. TOTAL COST OF 80,652.23 APPROVED BY BDAWES AND BSLONE, DSKAGGS 9-28-2020 OVERRUN EXPLANATION: THE 80,653 WAS FOR A FITTING THAT WAS NOT USED.
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026857000 | 2000 | EX | INVESTIGATE LAND RIGHTS/ROW | 2019-03-07 | MEADE ST | A | 9805 | 0 | -9805 | 100% |  |  | 0
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026857100 | 555 | EX | INSTALL 40'-4" PMIP | 2019-02-21 | 812 ADAMS AV | B | 25566.3252 | 19263.47 | -6302.8552 | -25% | 40 | 51 | 377.7151
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026857200 | 584 | EX | RETIRE REG STATION W/AMRP | 2019-09-10 | 1001 ARGILLITE RD | F | 4287.0034 | 8397.38 | 4110.3766 | 96% |  |  | 0
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026857300 | 584 | EX | RETIRE REG STATION W/AMRP | 2019-09-18 | 1327 MEADE ST | F | 4287.0034 | 5930.35 | 1643.3466 | 38% |  |  | 0
KY | KY - EAST | 2631 | U131983 |  |  |  | 19026858700 | 2000 | EX | INVESTIGATE LAND RIGHTS | 2022-11-03 | SARAH DR | A | 14282 | 0 | -14282 | 100% |  |  | 0
KY | KY - EAST | 2631 | U131982 |  |  |  | 19026859700 | 909 | EX | INSTALL I&C EQUIPMENT | 2019-06-04 | 2510 CENTER ST RR | F | 16473.1112 | 8028.82 | -8444.2912 | -51% |  |  | 0
KY | KY - EAST | 2631 | U131982 |  |  |  | 19026859800 | 910 | EX | RETIRE I&C EQUIPMENT | 2019-06-04 | 2510 CENTER ST RR | F | 83.2326 | 0 | -83.2326 | 100% |  |  | 0
KY | KY - EAST | 2631 | U131982 |  |  |  | 19026859900 | 909 | EX | INSTALL I&C EQUIPMENT | 2019-06-04 | BARBECUE RD | F | 16440.2238 | 9455.97 | -6984.2538 | -42% |  |  | 0
KY | KY - EAST | 2631 | U131982 |  |  |  | 19026860000 | 910 | EX | RETIRE I&C EQUIPMENT | 2019-06-04 | BARBECUE RD | F | 83.2326 | 0 | -83.2326 | 100% |  |  | 0
KY | KY - EAST | 2631 | U131982 |  |  |  | 19026860400 | 909 | EX | INSTALLING I&C EQUIPMENT | 2021-06-22 | US 23 | F | 222748.2628 | 174669.84 | -48078.4228 | -22% |  |  | 0 | CCC #27973 CCC #28142 CCC # 28275 CCC #28378 CCC #28665 CCC TICKET NOT REQUIRED NOT AT STATION 8/4/21
KY | KY - EAST | 2631 | U131982 |  |  |  | 19026860500 | 910 | EX | RETIRE I&C EQUIPMENT | 2021-06-22 | US 23 | F | 84.9756 | 511.34 | 426.3644 | 502% |  |  | 0 | CC# 78206
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026861200 | 555 | EX | INSTALL 80'-2" PMMP | 2019-03-15 | 35 RUSSELL PLAZA DR | A | 7543.6626 | 4460.3 | -3083.3626 | -41% | 80 | 23 | 193.9261 | INSTALLED 23' OF 2" PLASTIC MAIN LINE TESTED 100 PSIG 1 HOUR SOAP TESTED FINAL CONN. OP
KY | KY - EAST | 2631 | U131982 |  |  |  | 19026862600 | 557 | EX | INSTALL 2400'-2" PMMP | 2019-10-11 | SWORD ST | B | 436945.7962 | 411838.03 | -25107.7662 | -6% | 2400 | 2422 | 170.0405 | UNDERRUN EXPLANATION: PROJECT UNDERRAN BECAUSE THE 10000 UNITS OF PAVING AN D 500 UNITS OF ROCK EXCAVATION WERE NOT REQUIRED.
KY | KY - EAST | 2631 | U131982 |  |  |  | 19026862700 | 558 | EX | RETIRE 3000'-4"BSLP | 2019-12-19 | SWORD ST | B | 79.9756 | 1602.55 | 1522.5744 | 1,904% |  |  | 0
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026863900 | 555 | EX | INSTALL 1450'-2" PMMP | 2019-09-27 | 12612 ANTHONY DR | B | 52175.9118 | 53339.99 | 1164.0782 | 2% | 1450 | 1450 | 36.7862
KY | KY - EAST | 2631 | U131982 |  |  |  | 19026864200 | 584 | EX | ABANDON REG STAT 1378 | 2019-12-19 | SWORD ST | F | 6385.6656 | 2537.25 | -3848.4156 | -60% |  |  | 0
KY | KY - EAST | 2631 | U131982 |  |  |  | 19026867100 | 583 | EX | INSTALL VRG CONTROLLER | 2022-03-29 | OLD US 23 | F | 15490.7518 | 15917.94 | 427.1882 | 3% |  |  | 0 | CCC 59916 CCC # 59916 INSTALLED NEW VRG CONTROLLERS DASH 3-29-22
KY | KY - EAST | 2631 | U131982 |  |  |  | 19026867200 | 584 | EX | RETIRE CURRENT CONTROLLERS | 2022-03-29 | OLD US 23 | F | 64.4897 | 1038.8 | 974.3103 | 1,511% |  |  | 0 | CCC # INSTALLED NEW VRG'S RETIRED EXSISTING CONTROLLERS DASH 3-29-22
KY | KY - EAST | 2631 | U131983 |  |  |  | 19026868200 | 587 | EX | INSTALL MI WIRELESS EFC | 2019-04-30 | 1300 W US60 | F | 11104.5495 | 4481.07 | -6623.4795 | -60% |  |  | 0
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026869300 | 557 | EX | INSTALL 10'-3" PMLP | 2019-04-04 | LOGAN | A | 7452.8403 | 0 | -7452.8403 | 100% | 10 | 5 | 0
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026869400 | 558 | EX | RETIRE 10'-3" PLP | 2019-04-04 | LOGAN | A | 74.6837 | 7595.77 | 7521.0863 | 10,071% |  |  | 0
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026871300 | 555 | EX | INSTAL 100'-2" PMMP | 2019-10-23 | 1302 BEECH GROVE RD | B | 10670.6344 | 20735.1 | 10064.4656 | 94% | 100 | 156 | 132.9173
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 19026873600 | 561 | EX | INSTALL 24'-4" PMIP | 2019-06-27 | KENWOOD DR | B | 15596.7203 | 22926.06 | 7329.3397 | 47% | 24 | 36 | 636.835
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 19026873700 | 562 | EX | RETIRE 20'-4" PIP | 2019-06-27 | KENWOOD DR | B | 72.657 | 11.6 | -61.057 | -84% |  |  | 0
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 19026873800 | 561 | EX | INSTALL 223'-4' CS/PMIP | 2019-07-18 | SEATON DR | B | 76834.8811 | 73995.15 | -2839.7311 | -4% | 223 | 230 | 321.718
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 19026873900 | 562 | EX | RETIRE 178'-4" BS/CS/PIP | 2019-07-18 | SEATON DR | B | 72.657 | 0 | -72.657 | 100% |  |  | 0
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026879200 | 588 | EX | RETIRE SETTING - PAPER JO ONLY | 2019-06-01 | 901 KILGORE DR | F | 147.0323 | 0 | -147.0323 | 100% |  |  | 0 | THIS WAS ORIGINALLY A GMB TO CAB CONVERSION WITH AN AMERICAN METER AND CORRECTOR INSTALLED THIS SETTING HAS NOW BEEN ABANDONED AND A NEW SERVICE AND METER SETTING INSTALLED TO BECOME A TRUE CAB ACCOUNT NO FACILITIES OR FUNCTIONS REMAIN THIS ORDER IS A PAPER ONLY ORDER TO CORRECT ALL INFOMRATION IN WORK MANAGEMENT
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026879700 | 557 | EX | INSTALL 5'-3" PMIP EMERGENCY | 2019-06-06 | STATE ROUTE 5 | A | 114.7501 | 53.98 | -60.7701 | -53% | 5 | 5 | 10.796 | INSTALLED 5' OF 3" PLASTIC TO REPAIR DIG IN SEE JO# 19711923300
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026879800 | 558 | EX | RETIRE MAIN - LEAKAGE | 2019-06-06 | STATE ROUTE 5 | A | 72.7501 | 710.09 | 637.3399 | 876% |  |  | 0 | RETIRED 5' OF 3" PL DUE TO DIG IN AND INSTALLED 5' OF 3" PL BACK IN ITS PLA CE SEE JO# 19711923300
KY | KY - EAST | 2631 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026880900 | 586 | EX | REMOVE DAMAGED BUILDING | 2019-07-27 | 240 BUCKLEY RD | F | 5677.9507 | 4223.65 | -1454.3007 | -26% |  |  | 0 | REMOVED BUILDING JOB PAST COMMIT DATE WAITING ON APPROVAL FROM M&R LEADERSHIP TO COMPLETE WORK ON SATURDAY
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026881200 | 559 | EX | INSTALL 5'-4" PMLP | 2019-11-19 | OLD 13TH ST | B | 21041.8141 | 30902.5 | 9860.6859 | 47% | 5 | 6 | 5150.4167
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026881300 | 560 | EX | RETIRE 5'-4" BS-LP | 2019-11-19 | OLD 13TH ST | B | 0 | 72.57 | 72.57 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026881600 | 557 | EX | INSTALL 2240'-4" PMLP | 2020-05-06 | GARTRELL | B | 332950.5928 | 393029.99 | 60079.3972 | 18% | 2245 | 2236 | 175.7737 | OVERRUN EXPLANATION: TOTAL LABOR WAS ABOUT TWICE WHAT WAS ESTIMATED.
KY | KY - EAST | 2631 | U131982 |  |  |  | 19026881700 | 558 | EX | RETIRE 2240'-4" BS-LP MAIN | 2020-07-20 | GARTRELL | B | 64.321 | 144.79 | 80.469 | 125% |  |  | 0
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026883200 | 555 | EX | INSTALL 100'-4" PMIP | 2019-08-06 | 1538 BIRCH ST | B | 15476.1437 | 10971.63 | -4504.5137 | -29% | 100 | 67 | 163.7557
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026884200 | 559 | EX | INSTALL 5'- 4" PMLP | 2020-04-21 | HORN ST | B | 38126.7812 | 29990.35 | -8136.4312 | -21% | 14 | 7 | 4284.3357
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026884300 | 560 | EX | RETIRE 5'- 4" BSLP | 2020-04-21 | HORN ST | B | 144.1459 | 0 | -144.1459 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026886500 | 557 | EX | INSTALL 1736'-2"PMIP | 2019-10-03 | LYCAN | B | 80811.325 | 115502.44 | 34691.115 | 43% | 1738 | 1788 | 64.5987 | OVERRUN EXPLANATION: JOB REQUIRED 65 TONS MORE OF SAND AND STONE THAN ESTIM ATED. ALSO, $4100 OF ADDITIONAL PAVING WAS REQUIRED, AND IT TOOK 200 MORE H OURS THAN THE LABOR ESTIMATING TOOL PREDICTED. THESE ITEMS PLUSS THE OVERHE AD EFFECT OF THESE COSTS RESULTING IN THE TOTAL OVERRUN.
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026886600 | 558 | EX | RETIRE 1736'-2"/3" BSIP | 2019-11-08 | LYCAN | B | 75.6877 | 3364.98 | 3289.2923 | 4,346% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026886901 | 557 | EX | INSTALL 985'-2" PMMP | 2020-05-07 | FRONT ST | B | 189725.2878 | 244428.99 | 54703.7022 | 29% | 985 | 1020 | 239.6363 | UNDERRUN EXPLANATION: THE 3000 FEET OF 6 & 2 HAS NOT HIT YET. THAT AMOUNT A ND THE CUMULATIVE EFFECT OF THAT AMOUT HAS LED TO THE UNDERRUN. THOSE CHARG ES ARE EXPECTED TO HIT. OVERUN EXPLANATION: THE PAVING COSTS FINALY HIT. THOSE EXCEEDED ESTIMATED B Y $37,800. THAT AMOUNT PLUS THE OVERHEAD EFFECT FROM THOSE CHANGES CONTROIB TED TO THE OVERRUN.
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026887000 | 558 | EX | RETIRE 1097'-2"/3"/4"P&4"BS/CS | 2020-06-02 | FRONT ST | B | 754.3499 | 172.79 | -581.5599 | -77% |  |  | 0
KY | KY - EAST | 2631 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026887200 | 585 | EX | REPLACE DAMAGED BUILDING | 2019-12-10 | 240 BUCKLEY RD | F | 65318.7178 | 63861.4 | -1457.3178 | -2% |  |  | 0
KY | KY - EAST | 2631 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026887700 | 557 | EX | INSTALL 1' - 2" PMMP AS-BUILT | 2019-07-27 | STATE RT 854 | A | 3265.9525 | 3086.49 | -179.4625 | -5% | 1 | 1 | 3086.49 | CUT OUT AND REPLACED DMAGE TESTED NEW MAIN 100 PSIG 0005 MIN SOAP TESTED FI NAL CONN. OP 31 PSIG MAP CORRECTION WAS MADE AFTER THE CONSTRUCTION COORDINATOR PROVIDED THE EXA CT COORDINATES OF THIS 1" REPLACEMENT.
KY | KY - EAST | 2631 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026887800 | 558 | EX | ABANDON 1' - 2" PMMP AS-BUILT | 2019-07-27 | STATE RT 854 | A | 53.9767 | 784.99 | 731.0133 | 1,354% |  |  | 0 | RETIRED 1' OF 2" PL MP DUE TO HIT WITH DOZER ON RIGHT OF WAY DID NOT TEST L INE WAS SQUEEZED OFF TO MAKE REPAIRS
KY | KY - EAST | 2631 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 19026888600 | 575 | EX | ACQUIRE LAND RIGHTS | 2020-03-10 | 1106 POWELL LN | F | 5332 | 1603.85 | -3728.15 | -70% |  |  | 0
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026889700 | 583 | EX | INSTALL METER AND SETTING | 2021-10-29 | LAUREL ST | F | 55012.1889 | 54709.93 | -302.2589 | -1% |  |  | 0 | CCC #30162 CCC # 42745 CCC # 42908 CCC # 43108 CLENANER INSTALLED ON 10-29-2022 ALONG WITH PAPERWORK CO BY JOSH MULLINS ON 5-10-22
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026889800 | 584 | EX | RETIRE METER AND SETTING | 2021-10-29 | LAUREL ST | F | 76.3408 | 612.86 | 536.5192 | 703% |  |  | 0
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026890100 | 588 | EX | RETIRE MERCURY-MINI UNIT | 2019-04-30 | 1300 W US60 | F | 71.0611 | 0 | -71.0611 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026896800 | 557 | EX | REPLACE MAIN - DIG IN | 2019-09-19 | BLACKBURN | A | 1669.0599 | 2407.06 | 738.0001 | 44% | 1 | 3 | 802.3533
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026896900 | 558 | EX | RETIRE MAIN - DIG IN | 2019-09-19 | BLACKBURN | A | 324.6502 | 17.61 | -307.0402 | -95% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026897600 | 557 | EX | REPLACE MAIN - DIG IN | 2019-09-17 | 100 ETNA ST | A | 3086.8087 | 5369.59 | 2282.7813 | 74% | 0 | 2 | 2684.795 | INSTALLED 2' OF 4" PLASTIC TESTED 100 PSIG 1 HOUR SOAP TESTED FINAL CONN OP 11 IWC
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026897700 | 558 | EX | RETIRE MAIN - DIG IN | 2019-09-17 | 100 ETNA ST | A | 0 | 324.26 | 324.26 | 100% |  |  | 0 | AFTER SQUEEZE OFF CUT OUT DAMAGE AND REPLACED WITH NEW 4" PL
KY | KY - EAST | 2631 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 19026903100 | 909 | EX | INSTALL ELECTRONIC EQUIP | 2019-10-02 | US 60 | F | 7075.6923 | 4765.04 | -2310.6523 | -33% |  |  | 0 | EQUIPMENT INSTALLED BY ACP
KY | KY - EAST | 2631 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 19026903200 | 909 | EX | INSTALL ELECTRONIC EQUIP | 2019-12-31 | SKYLINE DR | F | 4316.6923 | 4787.49 | 470.7977 | 11% |  |  | 0 | EQUIPMENT INSTALLED BY ACP
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026903800 | 561 | EX | INSTALL 5'-2" P-IP | 2019-10-15 | GREENAPPLE RD | A | 1653.0599 | 2004.22 | 351.1601 | 21% | 1 | 2 | 1002.11
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026903900 | 562 | EX | RETIRE 5'-2" P-IP | 2019-10-15 | GREENAPPLE RD | A | 509.8798 | 166.57 | -343.3098 | -67% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026904400 | 555 | EX | INSTALL 40'-2" PMMP | 2019-11-06 | 1039 IRIS LN | A | 8368.9054 | 2299.29 | -6069.6154 | -73% | 1 | 40 | 57.4823 | INSTALLED 40' OF 2" PMMP MAIN. TESTED MAIN 0090 PSIG FOR 1HR WITH AIR USING KUHLMAN GAUGE. TIME OF TEST 2:50PM-3:50PM 11-06-2019 CWHEELE 11-07-2019
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026904700 | 561 | EX | DIG IN - INSTALL 5'-4" PMLP | 2019-10-22 | 601 MCCLURE ST | A | 5076.4924 | 0 | -5076.4924 | 100% | 35 | 10 | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026904800 | 562 | EX | DIG IN - INSTALL 5'-4" | 2019-10-22 | 601 MCCLURE ST | A | 0 | 0 | 0 | 0% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026905500 | 558 | EX | RETIRE 26'-4" PMIP AS BUILT | 2019-10-23 | 3578 BOY SCOUT RD | A | 70.321 | 0 | -70.321 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026906700 | 595R | EX | INSTALL RECTIFIER, POLE | 2020-01-08 | US 23 | A | 9754.8443 | 2849.17 | -6905.6743 | -71% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026906800 | 596 | EX | RETIRE RECTIFIER | 2020-01-08 | U. S. 23 | F | 56.0811 | 208.4 | 152.3189 | 272% |  |  | 0 | RETIRED US23/A12 RECTIFIER FACILITY 208014 INSTALLED NEW RECTIFIER, POLE AND ELECTRIC SERVICE (19-0269067-00) EXISTING GROUNDBED STILL IN OPERATION ALL TEST STATIONS ARE ASSOCIATED WITH NEW RECTIFIER FACILITY
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026908900 | 559 | EX | INSTALL 3'-4" PMLP | 2019-11-13 | 8227 PADDLE CREEK RD | A | 6559.5374 | 5847.26 | -712.2774 | -11% | 80 | 3 | 1949.0867
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026909000 | 560 | EX | RETIRE 3'-4" PLP | 2019-11-13 | 8227 PADDLE CREEK RD | A | 0 | 0 | 0 | 0% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026909500 | 559 | EX | INSTALL 5'-4" PMIP | 2019-11-16 | 5236 SKYLINE DR | A | 5292.3952 | 788.33 | -4504.0652 | -85% | 2 | 3 | 262.7767 | INSTALLED 3' OF 4" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7.5 PSIG 0015 MIN
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026909600 | 560 | EX | RETIRE 5'-4" PIP (PRE-1982) | 2019-11-16 | 5236 SKYLINE DR | A | 0 | 93.47 | 93.47 | 100% |  |  | 0 | RETIRED 3' OF 4" PLASTIC DUE TO PAC CLAMP LINES PURGED AND SEALED
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026910800 | 595R | EX | INSTALL NEW RECITIFER | 2021-02-18 | 37TH (WINCHESTER AVE) ST | A | 10181.0696 | 8639.7 | -1541.3696 | -15% |  |  | 0 | RECTIFIER WAS INSTALLED BY SPELLECY ON 12/21/2020. UTILITY COMPANY VERIFIE D ELECTRICAL PERMIT AND ENERGIZED SERVICE IN JANUARY OF 2021. SERVICE WAS INSTALLED BY ACP LAST WEEK OF DECEMBER 2021. FIRST 2511 RT TO BE PERFOMED IN MARCH 2021. BULLHORN RMU MODEL 4014 S/N 138053 WAS INSTALLED -OSS
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026910900 | 596 | EX | RETIRE RECTIFIER | 2021-02-18 | THIRTY SEVENTH ST | F | 69.2529 | 572.64 | 503.3871 | 727% |  |  | 0
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026911000 | 595R | EX | INSTALL NEW RECTIFIER | 2021-02-18 | SLASH BRANCH RD | A | 10181.0696 | 14874.57 | 4693.5004 | 46% |  |  | 0
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026911100 | 596 | EX | RETIRE RECTIFIER | 2021-02-18 | SLASH BRANCH RD | F | 69.2529 | 0 | -69.2529 | 100% |  |  | 0
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026911400 | 595R | EX | INSTALL NEW RECTIFIER | 2020-12-21 | DIEDERICH BV | A | 10181.0696 | 9404.7 | -776.3696 | -8% |  |  | 0
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026911500 | 596 | EX | RETIRE RECTIFIER | 2020-12-21 | DIEDERICH BV | F | 69.2529 | 0 | -69.2529 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026914300 | 557 | EX | INSTALL 555'-4" PMLP MAIN | 2020-08-27 | 15TH | B | 98513.05 | 81264.75 | -17248.3 | -18% | 575 | 459 | 177.0474
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026914400 | 558 | EX | ABANDON 542' - 4" BSLP | 2020-09-02 | 15TH | B | 165.5555 | 193.55 | 27.9945 | 17% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026914900 | 557 | EX | INSTALL 1430'- 2" PMMP | 2020-04-02 | GARFIELD | B | 168273.1947 | 173110.85 | 4837.6553 | 3% | 1430 | 1660 | 104.2836 | 10/13/20 - COST TO DATE APPEARS UNDER DUE TO PAVING. PAVING HAS NOT BEEN PROCESSED AT THIS TIME. -VAH POWERPLANT IS SHOWING $171,982 IN CHARGES WHICH IS IN TOLERENCE. SINCE POWE RPLANT IS THE SYSTEM OF RECORD, POWERPLANT IS PRESUMEND CORRECT.
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026915000 | 558 | EX | RETIRE 1400' - 4" BSLP | 2020-09-17 | GARFIELD | B | 56.0811 | 5151.27 | 5095.1889 | 9,085% |  |  | 0
KY | KY - EAST | 2631 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 20026918001 | 909 | EX | INSTALL ELECTRONICS | 2021-08-17 | SKYLINE DR | F | 78849.9064 | 203885.41 | 125035.5036 | 159% |  |  | 0 | CC# 31091 CC# 34924 CC# 21685. 01-03-22 DSASH CC# 21685. 01-03-22 DSASH OVERRUN EXPLANATION: ASSUMED WE WOULD USE THE OLD BLOCK BUILDING BUT FOND T HAT IT WAS LEAKING SO HAD TO REPLACE WITH A NEW BUILDING.
KY | KY - EAST | 2631 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 20026918102 | 909 | EX | INSTALL ELECTRONICS | 2021-11-01 | US23--ASHLAND OIL | F | 264607.6595 | 173384.28 | -91223.3795 | -34% |  |  | 0 | NO CC NEEDED ONSITE MEETING DID NOT GO INSIDE BUILDING GES: UNDERRUN EXPLANATION: JOB UNDERRAN BECAUSE SCADA BUILDING WAS PLACED O N ANOTHER JOB ORDER THAT IS PLANNED FOR 2022 CONSTRUCTION. ADDITIONALLY, ASSUMED THERE WAS PRESSURE CONTROL WHEN ESTIMATED AND THERE W AS NOT.
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026918900 | 2000 | EX | SKYLINE REG PREMISE PROPERTY | 2022-12-15 | SKYLINE DR |  | 4236 | 0 | -4236 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026919000 | 2000 | EX | ASHLAND OIL REG LAND RIGHTS | 2023-07-31 | US 23 |  | 4236 | 0 | -4236 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026919100 | 2000 | EX | GREENUP CPG REG ST LAND RIGHTS | 2023-05-04 |  |  | 4236 | 0 | -4236 | 100% |  |  | 0
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 20026920100 | 561 | EX | INSTALL 350'-2" PMMP | 2020-05-26 | SR 180 @ US 60 | B | 26075.9323 | 14350.38 | -11725.5523 | -45% | 350 | 334 | 42.9652
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 20026920200 | 561 | EX | INSTALL 205'-2" PMMP | 2020-04-30 | SR 180 @ US 60 | B | 24080.9323 | 41692.15 | 17611.2177 | 73% | 205 | 201 | 207.4236
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 20026920300 | 562 | EX | RETIRE 205'-2" PMP | 2020-04-30 | SR 180 @ US 60 | B | 85.9778 | 1.25 | -84.7278 | -99% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026922300 | 557 | EX | INSTALL 3'-4" PMIP - D033617 | 2020-01-31 | 159 BEREA BV | A | 3187.1594 | 257.77 | -2929.3894 | -92% | 3 | 3 | 85.9233 | INSTALLED 3' OF 4" P MAIN TO REPAIR LEAKING SOCKET WELD ON SERVICE TEE. TESTED MAIN 100PSIG FOR 1HR. SOAP TESTED EF COUP AT OP 15MIN. CGI NO GAS DETECTED. CWHEELE 2-13-2020
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026922400 | 558 | EX | RETIRE 3'-4" PIP - D033617 | 2020-01-31 | 159 BEREA BV | A | 56.0811 | 3888.93 | 3832.8489 | 6,834% |  |  | 0 | FOUND LEAKING SOCKET FUSION JOINT ON SERVICE TEE OF 4" P MAIN. CUT OUT 3' OF 4" MAIN TO REPAIR LEAK. TESTED MAIN 100PSIG FOR 1HR. SOAP TESTED EF COUP AT OP. CGI NO GAS DETECTED. CWHEELE 1-13-2020
KY | KY - EAST | 2631 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 20026922500 | 909 | EX | INSTALL ELECTRONICS | 2022-11-02 | US 60 | F | 123804 | 238947.63 | 115143.63 | 93% |  |  | 0 | CCC # 40652 NOT ON SITE CC# 47218. 12/01/21 DSASH CCC # 47218 CCC # 47356 CC# 47727. 12/07/21 DSASH
KY | KY - EAST | 2631 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 20026922600 | 910 | EX | RETIRE ELECTRONICS | 2022-11-02 | US 60 | F | 115.4611 | 144.18 | 28.7189 | 25% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026922900 | 2000 | EX | DIXON ST WATER LINE RELOCATE | 2020-03-12 | DIXON ST | B | 13011.3772 | 0 | -13011.3772 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026923300 | 557 | EX | INSTALL 790'-2" PMMP | 2020-08-10 | VALLEY DR | B | 76231.0959 | 87441.25 | 11210.1541 | 15% | 790 | 797 | 109.713
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026923400 | 558 | EX | RETIRE 862'-4"BSLP/ 4"PLP | 2020-08-25 | VALLEY DR | B | 76.0811 | 0 | -76.0811 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026923800 | 561 | EX | INSTALL 815'-4" PMLP/DIXON ST | 2020-05-26 | DIXON ST | B | 99856.4425 | 114041.24 | 14184.7975 | 14% | 821 | 821 | 138.9053
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026923900 | 562 | EX | RETIRE 865'-3" BSLP | 2020-06-15 | DIXON ST | B | 81.1135 | 121.1 | 39.9865 | 49% |  |  | 0
KY | KY - EAST | 2631 | U131983 |  |  |  | 20026930800 | 587 | EX | UPGRADE ELECTRONICS | 2021-06-23 | CENTER ST | F | 3038 | 4644.07 | 1606.07 | 53% |  |  | 0 | REPLACED EFC NON SCADA MONITORED GMB ACCOUNT GCCC TICKET NOT REQUIRED
KY | KY - EAST | 2631 | U131983 |  |  |  | 20026930900 | 587 | EX | UPGRADE ELECTRONICS | 2022-09-19 | 2236 MONTGOMERY AV | F | 3038 | 3329.3 | 291.3 | 10% |  |  | 0 | RETIRED MINI AT INSTALLED NEW EC350 ON CELL MODEM DASH 9-19-22
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026935600 | 557 | EX | INSTALL 2'- 3" PMIP | 2020-03-05 | 2318 SHOPES CREEK RD | A | 4278.9348 | 483.74 | -3795.1948 | -89% | 22 | 2 | 241.87
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026935700 | 558 | EX | RETIRE 2'- 3" P-IP | 2020-03-05 | 2318 SHOPES CREEK RD | A | 54.3494 | 126.28 | 71.9306 | 132% |  |  | 0
KY | KY - EAST | 2631 | U461492 | Pierce,James M | Dawes,Bobby | McKune,Timothy | 20026936200 | 2000 | EX | DIXON ST DESIGN-PHASE II-III | 2020-04-22 | DIXON ST | B | 23752.7152 | 0 | -23752.7152 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026936301 | 561 | EX | INSTALL 1192'-4" PMMP | 2021-03-16 | DIXON ST | B | 375696.2322 | 290217.29 | -85478.9422 | -23% | 1226 | 1177 | 246.5737 | UNDERRUN EXPLANATION: SIGNIFICANTLY LESS HARD SURFACE REPAIRS AND BACKFILL REQUIRED THAN ESTIMATED. ALSO NOFLAGGING ON OVERTIME WAS REQUIRED. THE OVER HEAD EFFECT OF THESE REDUCTIONS ALSO CONTRIBUTED TO THE UNDERRUN.
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026936400 | 562 | EX | RETIRE 1228'-3"&4"BS/CS/P-LP | 2021-04-05 | DIXON ST | B | 400.0304 | 1214.98 | 814.9496 | 204% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026936500 | 561 | EX | INSTALL 90' 4" PMLP | 2020-01-12 | DIXON ST | B | 56562.4483 | 45539.48 | -11022.9683 | -19% | 90 | 114 | 399.4691
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026936600 | 562 | EX | ABANDON ~10'-4" P-LP | 2021-01-12 | DIXON ST | B | 173.6495 | 167.31 | -6.3395 | -4% |  |  | 0
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026938200 | 584 | EX | RETIRE PAPER GAUGE | 2020-03-12 | 501 RAILROAD ST RR | F | 161.2271 | 0 | -161.2271 | 100% |  |  | 0 | GAUGE PREVIOUSLY REMOVED FROM STATION THIS JOB IS TO CORRECT WORK MANAGEMENT
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026941600 | 909 | EX | INSTALL I&C EQUIPMENT | 2021-06-30 | 100 BOY SCOUT RD | F | 16155.4774 | 11237.56 | -4917.9174 | -30% |  |  | 0 | CC# 30132. ERX INSTALLED BY DANNY ASH AND JOSH MULLINS PAPERWORK COMPLETED BY CYNTHIA FARIS PAPERWORK ON HOLD AWAITING CORRECT ISO SKETCH
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026941700 | 584 | EX | RETIRE GAUGE | 2021-06-30 | 100 BOY SCOUT RD | F | 91.4991 | 0 | -91.4991 | 100% |  |  | 0 | ERX INSTALLED AND PAPER RECORDING GAUGE RETIRED BY DANNY ASH AND JOSH MULLINS PAPERWORK COMPLETED BY CYNTHIA FARIS PAPERWORK ON HOLD AWAITING CORRECT ISO SKETCH
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026941800 | 909 | EX | INSTALL I&C EQUIPMENT | 2021-02-24 | 2137 CANNON DR RR | F | 16155.4774 | 12411.86 | -3743.6174 | -23% |  |  | 0 | GCC 13064 EQUIPMENT INSTALLED BY JOSH MULLINS ON 2/24/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/16/21 DELAY IN JOB COMPLETION WAITING ON PE APPROVAL FOR 584 JOB ORDER AND ISO SKETCH UPDATE GCCC TICKET NOT REQUIRED ON 7/16/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026941900 | 584 | EX | RETIRE GAUGE | 2021-02-24 | 2137 CANNON DR RR | F | 91.4991 | 0 | -91.4991 | 100% |  |  | 0 | GAUGE RETIRE BY JOSH MULLINS ON 2/24/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/16/21 DELAY COMPLETING JOB ORDER DUE TO ISO SKETCH REVISION& PE APPROVAL GCCC TICKET NOT REQUIRED ON 7/16/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026942100 | 909 | EX | INSTALL I&C EQUIPMENT | 2021-06-29 | 324 KINGS RD | F | 16155.4774 | 16401.86 | 246.3826 | 2% |  |  | 0 | CCC #29962 CCC #30339 INSTALLED ERX, RV50 MODEM, BATTERY AND SUPER SOLAR KIT GCCC TICKET NOT REQUIRED ON 7/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026942200 | 584 | EX | RETIRE GAUGE | 2021-06-29 | 324 KINGS RD | F | 91.4991 | 0 | -91.4991 | 100% |  |  | 0 | RETIRED PAPER RECORDING GAUGE AND INSTALLED ERX WORK COMPLETED ON 909 JOB ORDER WITH GCCC TICKET NUMBER 29962 GCCC TICKET NOT REQUIRED ON 7/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026942300 | 909 | EX | INSTALL I&C EQUIPMENT | 2021-02-24 | PAUL COFFEY BV | F | 16155.4774 | 11644.22 | -4511.2574 | -28% |  |  | 0 | INSTALLED ERX DELAY IN SENDING JOB TO CLOSE OUT WAITING ON INFORMATION PE REVIEW/APPROVAL AND ISO SKETCH CFARIS
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026942400 | 584 | EX | RETIRE GAUGE | 2021-02-24 | PAUL COFFEY BV | F | 91.4991 | 1032.4 | 940.9009 | 1,028% |  |  | 0 | REPLACED MECHANICAL RECORDING GAUGE WITH ERX DELAY IN SENDING TO CLOSEOUT DUE TO WAITING ON INFORMATION, PE REVIEW/APPROVAL AND CORRECT ISO SKETCH CFARIS
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026942700 | 909 | EX | INSTALL I&C EQUIPMENT | 2021-06-28 | 460 SAND HILL RD | F | 16155.4774 | 15613 | -542.4774 | -3% |  |  | 0 | CCC # 28876 CC#29408. 6/28/21 DSASH CCC # 32222 INITIAL COMMISSIONING BY SHANE GIORDANO PAPERWORK COMPLETED BY CYNTHIA FARIS ON 12/10/21 PAPERWORK ON HOLD AWAITING ISO SKETCH
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026942800 | 584 | EX | RETIRE GAUGE | 2021-07-16 | 460 SAND HILL RD | F | 91.4991 | 0 | -91.4991 | 100% |  |  | 0 | PAPERWORK COMPLETION ON HOLD AWAITING ISO SKETCH
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026944300 | 584 | EX | RETIRE REG STN R-1326 | 2020-06-03 | 125 8TH ST REAR | F | 6430.175 | 321.94 | -6108.235 | -95% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026944700 | 557 | EX | INSTALL 791' - 2" PMLP | 2020-05-21 | GLENN | B | 146581.9295 | 142734.85 | -3847.0795 | -3% | 827 | 836 | 170.7355 | UNDERRUN EXPLANATION: PAVING HAS NOT HIT YET FOR THIS JOB SO IT IS TOO EARL Y FOR AN EXPLANATION. UPDATE EXPLANATION 11/24/2020. STILL NOT PAVING HAS HIT. 2400 UNITS OF 6 & 2 IS EXPECTED.
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026944800 | 558 | EX | RETIRE 684' - 3"&4" CS,BS,PL | 2020-06-05 | GLENN | B | 246.4976 | 96.71 | -149.7876 | -61% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026944900 | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2020-04-20 | 311 MAIN ST | A | 3952.8196 | 5427.36 | 1474.5404 | 37% |  |  | 0 | ABANDONED 5' OF 4" S MAIN. SOAP TESTED 4" END CAP AT OP PRESS.
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026946500 | 557 | EX | INSTALL 1012'/2" PMIP MAIN | 2020-08-28 | VALLANCE AV | B | 173270.4097 | 85045.62 | -88224.7897 | -51% | 1016 | 1001 | 84.9607 | UNDERRUN EXPLANATION: IT DOES NOT APPEAR THAT THE PAVING COSTS HAVE HIT YET . THERE ARE 3500 SQUARE FEET OF HARD SURFACE REPAIRS THAT HAVE NOT HIT.
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026946600 | 558 | EX | ABANDON 892'/2"&4" BS/CS MAIN | 2020-09-11 | VALLANCE AV | B | 248.591 | 165.09 | -83.501 | -34% |  |  | 0
KY | KY - EAST | 2631 | U938437 |  |  |  | 20026952500 | 559 | EX | REPLACE VALVE C-16 | 2023-02-06 | CHESTNUT ST | B | 56236.611 | 47582.37 | -8654.241 | -15% | 31 | 29 | 1640.7714
KY | KY - EAST | 2631 | U938437 |  |  |  | 20026952600 | 560 | EX | RETIRE VALVE C-16 | 2023-02-06 | CHESTNUT ST | B | 952.0929 | 5789.59 | 4837.4971 | 508% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026953000 | 2000 | EX | PS&I FOR CALGON HEATER REPLACE | 2022-09-20 | 15024 US 23 |  | 12833.7702 | 0 | -12833.7702 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026956700 | 557 | EX | INSTALL 5'-4" PMLP AS-BUILT | 2020-06-19 | KENWOOD | A | 3901.6492 | 209.55 | -3692.0992 | -95% | 5 | 2 | 104.775 | INSTALLED 2' OF 4" PL TO REPAIR DAMAGE TO SERVICE TEE TESTED MAIN 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 11" WC
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026956800 | 558 | EX | RETIRE 5'-4" PLP AS-BUILT | 2020-06-29 | KENWOOD | A | 99.2651 | 137.5 | 38.2349 | 39% |  |  | 0 | REITRED 2' OF 4" PL CONTRACTOR HIT SERVICE TEE AT MAIN LINE CUT OUT AND REP LACED MAIN LINE TESTED 90 PSIG 1 HR AND SERVIE TEE TESTED 90 PSIG 0005 MIN
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026958000 | 557 | EX | INSTALL 5'-4" PMIP LEAK REPAIR | 2020-06-25 | 7511 MIDLAND TRAIL RD | A | 6231.4115 | 1917.85 | -4313.5615 | -69% | 25 | 2 | 958.925 | INSTALLED 2' OF 4" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7 PSIG
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026958100 | 558 | EX | RETIRE 5'-4" P-IP LEAK REPAIR | 2020-06-25 | 7511 MIDLAND TRAIL RD | A | 99.2651 | 118.53 | 19.2649 | 19% |  |  | 0 | RETIRED 2" OF 4" ALDYL-A DUE TO LEAKAGE ON RETIRED SERVICE TEE
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 20026959800 | 557 | EX | INSTALL 3' - 4" PMLP | 2020-07-07 | W. PIKE ST | A | 4448.189 | 179.33 | -4268.859 | -96% | 3 | 3 | 59.7767
KY | KY - EAST | 2631 | BKSLONE |  |  |  | 20026959900 | 558 | EX | RETIRE 3'-4" PLP | 2020-07-07 | W. PIKE ST | A | 85.2291 | 422.89 | 337.6609 | 396% |  |  | 0 | ABANDONED 3' OF 4" PLASTIC DUE TO EXCAVATOR DAMAGE.
KY | KY - EAST | 2631 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026965500 | 583 | EX | INST. FN 24836 EXTRA LP OPP | 2020-09-28 | 243 KENWOOD BV | F | 21960.5353 | 1958.03 | -20002.5053 | -91% | 50 |  | 0 | REGULATOR REPLACED BY DANNY ASH ON 9/29/2020 GASKET STRAINER NOT REQUIRED OR INSTALLED SETTING HAS EXISTING T-STRAINER ER350 NOT INSTALLED STATION HAS EXISTING ERX PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/20/21 GCCC TICKET NOT REQUIRED ON 5/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026965600 | 584 | EX | RET. FN 24836 FOR EXTRA LP OPP | 2020-09-28 | 243 KENWOOD BV | F | 51.9579 | 7396.4 | 7344.4421 | 14,135% |  |  | 0 | REGULATOR REPLACED BY DANNY ASH ON 9/28/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/20/2021 GCCC TICKET NOT REQUIRED ON 5/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026965700 | 583 | EX | INST. FN 24837 EXTRA LP OPP | 2020-09-29 | 243 KENWOOD BV | F | 21960.5353 | 6039.42 | -15921.1153 | -72% | 50 |  | 0 | REGULATOR INSTALLED BY DANNY ASH ON 9/29/2020 GASKET STRAINER NOT REQUIRED OR INSTALLED SETTING HAS EXISTING T-STRAINER ER350 NOT INSTALLED STATION HAS EXISTING ERX PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/20/2021 GCCC TICKET NOT REQUIRED ON 5/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026965800 | 584 | EX | RET. FN 24837 FOR EXTRA LP OPP | 2020-09-29 | 243 KENWOOD BV | F | 51.9579 | 887.27 | 835.3121 | 1,608% |  |  | 0 | REGULATOR REPLACED BY DANNY ASH ON 9/29/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/20/2021 GCCC TICKET NOT REQUIRED ON 5/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026967900 | 555 | EX | INSTALL 315' 2" PMIP | 2021-01-27 | 600 AMANDA FURNACE DR | B | 31888.6353 | 71403.61 | 39514.9747 | 124% | 317 | 330 | 216.3746 | TWALKER/KY 02-23-21: ISSUED BACK ORDER CANCEL #48444 FOR JOB OVERRUN EXPLANATION: 150 SQUARE FEET OF 6&2 WAS ESTIMATED AND 990 SQ FEET W AS REQUIRED LEADING TO AN INCREASE IN CONTRACTOR COSTS AND OVERHEADS.
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026968700 | 557 | EX | EMER - INSTALL 5' - 2" PMIP | 2020-08-17 | NEW HAVEN | A | 4287.1494 | 299.11 | -3988.0394 | -93% | 5 | 2 | 149.555
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026968800 | 558 | EX | EMER - RETIRE 5'- 2" PMIP | 2020-08-17 | NEW HAVEN | A | 486.2644 | 182.45 | -303.8144 | -62% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026969100 | 2000 | EX | ACQUIRE EASEMENT FOR NEW CUST | 2021-05-13 | 600 AMANDA FURNACE DR | B | 2807 | 0 | -2807 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026970100 | 557 | EX | INSTALL 11400'-2"/4" PM/CSIP | 2021-11-01 | FULLERTON | B | 1176644.8813 | 1042042.95 | -134601.9313 | -11% | 11325 | 10870 | 95.8641
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026970200 | 558 | EX | RETIRE 10250'-2"/3"/4" BS/CSIP | 2021-11-10 | FULLERTON | B | 278.4699 | 272.31 | -6.1599 | -2% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026972500 | 2000 | EX | INVESTIGATE LAND RIGHTS | 2022-11-03 | 401 MAIN ST | B | 3417 | 0 | -3417 | 100% |  |  | 0
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026977301 | 557 | EX | INSTALL 12,100 OF 2"PMMP MAIN | 2021-08-23 | BATH AV | B | 1697987.4343 | 1937357.64 | 239370.2057 | 14% | 12100 | 11864 | 163.2972
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026977400 | 558 | EX | RETIRE 10,510'OF 4"/6"BSLP | 2021-10-20 | BATH AV | B | 90.4074 | 1237.75 | 1147.3426 | 1,269% |  |  | 0
KY | KY - EAST | 2631 | U938437 |  |  |  | 20026977500 | 557 | EX | INSTALL 4335'-4" & 6" PMLP | 2022-06-14 | FREDERICK | B | 818557.1832 | 1014309.73 | 195752.5468 | 24% | 4345 | 1022 | 992.4753 | TWALKER/KY 01-24-23: PROJECT OVER RUN COST DUE TO ADDITIONAL PAVING/HARD SURFACE REPAIR RESULTED IN $100,000 HIGHER CONTRACT COST, MATERIAL COST WERE $46,000 HIGHER THAN EST. ADN SEGA $68,000 HIGHER THAN EST.
KY | KY - EAST | 2631 | U938437 |  |  |  | 20026977600 | 558 | EX | RETIRE 4766'-2"/3"/4"/6" BSLP | 2022-09-01 | FREDERICK | B | 476.2758 | 11052.89 | 10576.6142 | 2,221% |  |  | 0
KY | KY - EAST | 2631 | U938437 |  |  |  | 20026978100 | 557 | EX | INSTALL 8620'- 2" PMMP | 2023-10-10 | HARRISON | B | 1435185.1923 | 1699797.2 | 264612.0077 | 18% | 8664 | 9303 | 182.715
KY | KY - EAST | 2631 | U938437 |  |  |  | 20026978200 | 558 | EX | RETIRE 8983' LP - 2520' BS | 2023-11-16 | HARRISON | B | 476.2758 | 513.02 | 36.7442 | 8% |  |  | 0
KY | KY - EAST | 2631 | U461492 | Pierce,James M | Dawes,Bobby | McKune,Timothy | 20026979400 | 560 | EX | ABANDON ~285' - 2" & 3" PMLP | 2020-10-02 | SYCAMORE ST | A | 1385.2821 | 299.74 | -1085.5421 | -78% |  |  | 0 | RETIRED 95' OF 2" P. MAIN AND APPPROX. 150' P. MAIN.
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026982200 | 559 | EX | INSTALL 5'-4"PMMP & 4'-4"CS | 2021-06-07 | TAYLOR AV | B | 42642.7946 | 40958.2 | -1684.5946 | -4% | 9 | 14 | 2925.5857
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026982300 | 560 | EX | ABANDON 5' - 4" CSMP | 2021-06-07 | TAYLOR AV | B | 183.2963 | 10.78 | -172.5163 | -94% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026982500 | 559 | EX | INSTALL 120' - 4" PMLP | 2021-03-23 | R/W - GREENUP BANK | B | 30468.341 | 38925.35 | 8457.009 | 28% | 122 | 85 | 457.9453
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026983500 | 557 | EX | INSTALL 1670' - 2" PMMP | 2023-07-28 | RIGGLES | B | 347784.1168 | 426217.2 | 78433.0832 | 23% | 1670 | 1805 | 236.1314
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026983600 | 558 | EX | ABANDON 1667'-2/3/4" PMLP/BSLP | 2023-07-28 | RIGGLES | B | 360.3823 | 290.24 | -70.1423 | -19% |  |  | 0
KY | KY - EAST | 2631 | U938437 |  |  |  | 20026984500 | 583 | EX | REPLACE IP OUTLET BLOCK VALVE | 2022-05-25 | 240 BUCKLEY RD | F | 2174.0477 | 1480.71 | -693.3377 | -32% |  |  | 0 | NOT ON SITE REPLACED INLET AND OUTLET IP RUN BLOCK VALVES SGIORDANO JMULLINS CO PAPERWORK 06132022
KY | KY - EAST | 2631 | U938437 |  |  |  | 20026984600 | 584 | EX | REPLACE IP OUTLET BLOCK VALVE | 2022-05-25 | 240 BUCKLEY RD | F | 50 | 2409.31 | 2359.31 | 4,719% |  |  | 0 | CCC 68181 REPLACED INLET AND OUTLET IP BLOCK VALVS SGIORDANO JMULLINS CO PAPERWORK 06132022
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026985800 | 558 | EX | RETIRE 10'-3" BSLP | 2020-11-06 | MITCHELL ST | A | 2005.1167 | 3541.4 | 1536.2833 | 77% |  |  | 0 | RETIRED 30' OF 3" BS DUE TO CONTRACTOR PULLING END OF MAIN OUT OF GROUND RETIRED WITH 3" 4 BOLT END CAP SOAP TESTED OP 12" WC
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026985900 | 557 | EX | INSTALL 5'-4" PMLP DIG IN | 2020-11-09 | FOREST | A | 5898.0652 | 2568.67 | -3329.3952 | -56% | 5 | 8 | 321.0838
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026986000 | 558 | EX | ABANDON 5' - 4" PMLP | 2020-11-09 | FOREST | A | 778.1775 | 29.59 | -748.5875 | -96% |  |  | 0 | RETIRED 8' OF 4" MAIN DUE TO DAMAGE FROM EXCAVATOR
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026986700 | 557 | EX | INSTALL 5' - 4" PMLP MAIN | 2020-11-12 | ALLEY | A | 4734.5045 | 642.11 | -4092.3945 | -86% | 25 | 5 | 128.422 | INSTALLED 5' OF 4" PL TO REPAIR DAMAGE BY CITY OF ASHLAND SEWER TESTED 90 P SIG 1 HR SOAP TESTED FINAL CONN OP 8" WC
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026986800 | 558 | EX | ABANDON 5'-4" PMLP MAIN | 2020-11-12 | ALLEY | A | 778.1775 | 624.83 | -153.3475 | -20% |  |  | 0 | RETIRED MAIN DUE TO DAMAGE BY CITY OF ASHLAND
KY | KY - EAST | 2631 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 20026988000 | 2000 | EX | INV LAND RIGHTS BXN STA AND RD | 2023-08-09 | 831 POND RUN RD | A | 2489 | 0 | -2489 | 100% |  |  | 0
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026988600 | 2000 | EX | RESEARCH R/W | 2021-02-10 | 4750 WINCHESTER AV |  | 3128 | 0 | -3128 | 100% |  |  | 0 | LS WAS UNABLE TO FIND EXISTING R/W OR OBTAIN NEW EASEMENTS. PATH WAS FINAL LY CHOSEN TO STAY IN ROAD R/W. D.LEMONS
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026988800 | 555 | EX | INSTALL 210'-2" PMLP | 2021-03-10 | 4750 WINCHESTER AV REAR | B | 42176.37 | 21827.5 | -20348.87 | -48% | 214 | 194 | 112.5129
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026989500 | 558 | EX | RETIRE 53'-2" P-IP DIG IN | 2020-12-04 | BRYAN DR | A | 931.148 | 237.75 | -693.398 | -74% |  |  | 0 | RETIRED 53' OF 2" PL IP MAIN DUE TO DIG IN SOAP TESTED 2" PURGE POINT AND 2" EF COUPLING OP 7PSIG
KY | KY - EAST | 2631 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026991600 | 595R | EX | INSTALL RECTIFIER- JOHNSON ST | 2023-11-14 | 10123 MAYO TRAIL RD | A | 12343.3281 | 8433.77 | -3909.5581 | -32% |  |  | 0 | 30/15 RECTIFIER SERIAL #202283 INSTALLED ON CAP RELOCATION PROJECT AT 10123 MAYO TRAIL / JMM RECTIFIER INSTALLED AND PUT ONLINE 2021 / RECTIFIER TO BE RETIRED AT THE CONCLUSION OF CAP RETIREMENT PROJECT 21-0261305-00 IN 2023 / JMM
KY | KY - EAST | 2631 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026991700 | 595R | EX | INSTALL RECTIFIER- 10325 MAYO | 2023-11-14 | 10325 MAYO TRAIL RD | A | 12973.4687 | 0 | -12973.4687 | 100% |  |  | 0 | 50/25 RECTIFIER SERIAL #201934 INSTALLED CAP RELOCATION PROJECT AT 10325 MAYO TRAIL / JMM RECTIFIER INSTALLED AND PUT ONLINE 2021 / RECTIFIER TO BE RETIRED AT THE CONCLUSION OF CAP RETIREMENT PROJECT 21-0261305-00 IN 2023 / JMM
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026992000 | 596 | EX | RETIRE RECTIFIER | 2023-11-14 | MAYO TL | F | 60.6196 | 0 | -60.6196 | 100% |  |  | 0 | RECTIFIER 207731 REMOVED FROM SERVICE IN 2021 WITH THE COMPLETION OF CAP JOB 18-0267859-01 (INSTALL) & 18-0267860-01 (RETIREMENT) / JMM TWO RECTIFIERS 860778 & 860865 WERE PLACED AT THE NORTH AND SOUTH ENDS OF CIRCUIT AFTER PLASTIC INSTALLED ON MAYO TRAIL DIVIDED UP CP CIRCUIT
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026992200 | 555 | EX | INSTALL 100'-2" PMIP | 2021-03-15 | 112 TANGO AV | B | 11276.4442 | 8539.31 | -2737.1342 | -24% | 100 | 38 | 224.7187
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026103200 | 2000 | EX | INVESTIGATE R/W AND SEWER PLAN | 2021-05-13 | LEE ST | B | 7553 | 0 | -7553 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026103300 | 2000 | EX | INVESTIGATE ROW & LAND RIGHTS | 2021-10-11 | MAIN ST |  | 7693 | 0 | -7693 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026104900 | 557 | EX | EMER INSTALL 5'-3" PMIP | 2021-02-22 | 6227 EMILY ST | A | 5995.5434 | 4758.29 | -1237.2534 | -21% | 5 | 4 | 1189.5725 | SEE PAPER PACKET FOR INFO
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026105000 | 558 | EX | EMER RETIRE 5'-3" P-IP | 2021-02-22 | 6227 EMILY ST | A | 750.8346 | 3758.23 | 3007.3954 | 401% |  |  | 0 | SEE PAPER COPIES FOR TEST INFO SEE PAPER COPIES/ PIPE EXPOSURE FORM WILL NOT ACCEPT THE CORRECT MAIN NUMBER NOT LETTING ME COMPLETE THIS ORDER
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026105700 | 557 | EX | EMER INST 360'-2" PMIP D244304 | 2021-02-25 | 4446 13TH ST | A | 25736.2708 | 109722.07 | 83985.7992 | 326% | 345 | 349 | 314.3899 | INSTALLED 345' OF 2" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7.5 P SIG OVERRUN EXPLANATION: THE SIGNIFICANT COST DIFFERENCE RESULTED FROM PAVING REQUIREMENTS. THE PROJECT WAS NOT ESTIMATED FOR CONTRACT RESTORATION. PAVE TICKETS WERE SUBMITTED TO REPAIR ROAD AND PARKING LOT AREA
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026105800 | 558 | EX | EMER RETIRE 350'-3"/2" CSIP | 2021-02-25 | 4446 13TH ST | A | 1114.7918 | 27035.38 | 25920.5882 | 2,325% |  |  | 0 | FOUND CRACKED MAIN RETIRED 345' OF 3" ST AND INSTALLED 345' OF NEW 2" PL TO STOP LEAKAGE TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7.5 PSIG
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026106400 | 584 | EX | RETIRE PAPER RECORD GAUGE | 2021-12-17 | 425 CAROLINE RD | F | 341.3226 | 92.38 | -248.9426 | -73% |  |  | 0 | TICKET 13749
KY | KY - EAST | 2631 | U938437 |  |  |  | 21026106800 | 2000 | EX | DESIGN COSTS | 2022-10-17 | BLACKBURN ST | B | 10000 | 0 | -10000 | 100% |  |  | 0
KY | KY - EAST | 2631 | U938437 |  |  |  | 21026106900 | 2000 | EX | DESIGN COSTS | 2022-10-17 | HARRISON ST | B | 10000 | 0 | -10000 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026109000 | 557 | EX | EMER - INSTALL 10'-4" PMIP | 2021-03-08 | COUNTRY CLUB DR | A | 8970.0544 | 2349.57 | -6620.4844 | -74% |  | 5 | 469.914 | INSTALLED 5' OF NEW 4" PL MAIN TO REPAIR CRACKED PIPE TESTED 90 PSIG 1 HR
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026109100 | 558 | EX | EMER - RETIRE 10'-4" CSIP | 2021-03-08 | COUNTRY CLUB DR | A | 556.9397 | 5925.07 | 5368.1303 | 964% |  |  | 0 | RETIRE 5' OF 4" CS MAIN DUE TO SPLIT MAIN SOAP TESTED OP 7.5 PSIG
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026110200 | 557 | EX | EMER - INSTALL 5'-3" PMIP | 2021-04-20 | 2326 SHOPES CREEK RD | A | 7868.6589 | 880.36 | -6988.2989 | -89% | 5 | 5 | 176.072 | INSTALLED 5' OF 3" PLASTIC. TESTED AT 90PSIG FOR 1HR.
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026110300 | 558 | EX | EMER - RETIRE 5'-3" PIP | 2021-04-20 | 2326 SHOPES CREEK RD | A | 441.8134 | 7215.11 | 6773.2966 | 1,533% |  |  | 0 | RETIRED 5' OF 3" PLASTIC DUE TO PAC CLAMPS LEAKING.
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026113401 | 555 | EX | INSTALL 100'-2" PMMP | 2021-04-16 | 2000 FERN DR | B | 11198.5401 | 21410.67 | 10212.1299 | 91% | 100 | 82 | 261.1057
KY | KY - EAST | 2631 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 21026114100 | 2000 | EX | ROW CLEARING AND ROAD ACCESS | 2023-08-08 | BBQ HOLLOW | A | 30000 | 0 | -30000 | 100% |  |  | 0
KY | KY - EAST | 2631 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 21026114400 | 2000 | EX | BUY-OUT CUSTOMERS | 2023-11-07 | RIVA RIDGE | B | 45000 | 0 | -45000 | 100% |  |  | 0 | CUSTOMER BUY OUTS STARTED, ALL PAPERWORK FOR COMMISION OBTAINED. D.LEMONS 1 1/7/2023
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026114900 | 2000 | EX | INVESTIGATE LAND ROW & STAKE | 2021-05-11 | 2000 FERN DR | B | 1992 | 0 | -1992 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026115100 | 557 | EX | INSTALL 1'-4" PMLP | 2021-03-16 | DIXON | A | 149.4587 | 0 | -149.4587 | 100% | 1 | 1 | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026115800 | 557 | EX | EMER - INSTALL 138'-4" PM/CSIP | 2021-03-16 | SHORT WHITE OAK | A | 10752.5629 | 2573.82 | -8178.7429 | -76% | 134 | 138 | 18.6509 | INSTALLED 134' OF 4" PL IP TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7.5 PSIG
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026115900 | 558 | EX | EMER - RETIRE 134'-4" CSIP | 2021-03-16 | SHORT WHITE OAK | A | 1105.3087 | 9847.31 | 8742.0013 | 791% |  |  | 0 | RETIRED 134' OF 4" CS DUE MAIN EXPOSED OUT OF GROUND AND DETERIORATION
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026116900 | 555 | EX | INSTALL 200'-2" PMLP | 2021-07-02 | 306 W FRANKLIN ST | B | 39229.3021 | 24792.54 | -14436.7621 | -37% | 200 | 200 | 123.9627
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026117200 | 557 | EX | EMER - INSTALL 2' - 4" PMLP | 2020-04-19 | SYCAMORE ST | A | 3095.6422 | 3814.78 | 719.1378 | 23% | 5 | 2 | 1907.39 | INSTALLED 2' OF 4" PL DUE TO DAMAGE
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026117300 | 558 | EX | EMER - RETIRE 2'-4" P-LP | 2021-04-19 | SYCAMORE ST | A | 441.8134 | 183.09 | -258.7234 | -59% |  |  | 0 | RETIRE 2' OF 4" PL DUE TO DAMAGE
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026120600 | 584 | EX | RETIRE REG STATION WITH AMRP | 2022-12-15 | 419 BUCKLEY RD | F | 9924.8698 | 1058.49 | -8866.3798 | -89% |  |  | 0 | CC# 6407 RETIRED REG STATION DASH 12-15-2022
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026121500 | 555 | EX | INSTALL 160'-2" PMIP | 2021-08-24 | 1604 BIRCH ST | B | 21640.9206 | 37719.27 | 16078.3494 | 74% | 160 | 210 | 179.6156
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026121600 | 555 | EX | INSTALL 100'-2" PMIP | 2021-06-11 | 7625 OXCART HILL DR | B | 13861.3812 | 16499.56 | 2638.1788 | 19% | 100 | 100 | 164.9956
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026122300 | 555 | EX | INSTALL 100'-2" PMMP | 2021-06-25 | 1213 WINCHESTER AV NEW | B | 25260.7035 | 26947.59 | 1686.8865 | 7% | 102 | 85 | 317.0305
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026123800 | 561 | EX | INSTALL 160'-4" CSLP/PMLP | 2021-08-05 | 8175 CANNONSBURG RD | B | 161313.4069 | 86016.2 | -75297.2069 | -47% | 159 | 134 | 641.9119 | UNDERRUN EXPLANATION: SIGNIFICANTLY LESS HARD SURFACE RESTORATION AND BACKFILL REQUIRED THAN ESTIMATED KYTC REQUIRED RELOCATION AND TOLD US NOT TO WORRY ABOUT THE MILL & OVERLAY THAT THEY WOULD DO THAT WHEN THEY COMPLETED THEIR PART OF THE PROJECT, THIS RESULTED IN A SIGNIFICANT AMOUNT OF THE COST VARIATION
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026125300 | 562 | EX | RETIRE 180'-4" BSLP | 2021-08-06 | 8175 CANNONSBURG RD | B | 282.1429 | 0 | -282.1429 | 100% |  |  | 0 | COMMITT DATE WAS PUSHED OUT TILL END OF AUG.2021
KY | KY - EAST | 2631 | U938437 |  |  |  | 21026126500 | 2000 | EX | DESIGN FARMERS MKT SMRP | 2023-07-27 | 4570 LOUISA RD |  | 40000 | 0 | -40000 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026127800 | 555 | EX | INSTALL 500'-2" PMMP | 2021-07-19 | 1819 ASHLAND RD | B | 43810.3768 | 47089.22 | 3278.8432 | 7% | 500 | 500 | 94.1784
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026127900 | 2000 | EX | INVESTIGATE ROW | 2021-08-04 | 1819 US RTE 23 |  | 3361 | 0 | -3361 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026128500 | 559 | EX | NSP - INSTALL 150'-2" PMLP | 2021-06-15 | 1510 POPLAR AV | A | 16760.5972 | 10156.16 | -6604.4372 | -39% | 150 | 150 | 67.7077 | INSTALLED 150' 2"P. PRESSURE TESTED 90LBS 1HR. SOAP TESTED 2" EF COUPLING AT OP. PRESS. (11 IWC) 15MIN. PRESS. TEST 2X1 MONITORING TEE 90LBS 15MIN. SOAP TESTED MONITORING TEE END CAP OP. PRESS (11 IWC) 15MIN.
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026129800 | 555 | EX | INSTALL 200'-2" PMMP | 2021-09-16 | 2745 CRESTVIEW DR | B | 21853.3833 | 25563.52 | 3710.1367 | 17% | 200 | 230 | 111.1457
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026130200 | 557 | EX | EMER-INSTALL 5'-2" PMIP/CSIP | 2021-06-29 | 610 CENTRAL AV | A | 6178.4541 | 7558.85 | 1380.3959 | 22% | 26 | 6 | 1259.8083
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026130300 | 558 | EX | EMER-RETIRE 5'-2" BSIP | 2021-06-29 | 610 CENTRAL AV | A | 410.7144 | 230.72 | -179.9944 | -44% |  |  | 0
KY | KY - EAST | 2631 | U938437 |  |  |  | 21026130400 | 557 | EX | INSTALL 25,111'-2",4" PMMP | 2023-08-15 | PADDLE CREEK RD | B | 3707985.656 | 4355642.45 | 647656.794 | 17% | 25131 | 23540 | 185.0315
KY | KY - EAST | 2631 | U938437 |  |  |  | 21026130500 | 558 | EX | RETIRE 25,000' OF BSLP MAINS | 2023-11-16 | PADDLE CREEK RD | B | 485.0228 | 1741.22 | 1256.1972 | 259% |  |  | 0
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026131300 | 588 | EX | RETIRE EFC UNIT | 2021-06-23 | CENTER ST | F | 74.8797 | 0 | -74.8797 | 100% |  |  | 0 | REPLACED EFC
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026132100 | 561 | EX | INSTALL 600'-4" PMMP | 2021-07-27 | 18648 E KY-8 | A | 159985.8979 | 75178.06 | -84807.8379 | -53% | 608 | 582 | 129.1719 | INSTALLED 573' OF 4" PL MP AND 9' OF 2" PL MP TESTED 90 PSIG 2 HRS SOAP TESTED FINAL CONN OP 44 PSIG UNDERRUN EXPLANATION: A SIGNIFICANT UNIT OF COST WAS THE PLANNED ROCK BORE BUT THE CREW WAS ABLE TO AVOID THE NEED FOR A ROCK BORE, THE JOB DURATION ESTIMATE TOOL ALSO PLANNED FOR 120 HOURS OF LABOR AND THE CREW COMPLETED THE JOB IN 60 HOURS AND SOME CREW MEMBERS WERE NOT NEEDED THE ENTIRE DURATION OF THE JOB.
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026132200 | 562 | EX | RETIRE 450'-4" P-MP | 2021-07-27 | 18648 KY-8 | A | 875.427 | 212.81 | -662.617 | -76% |  |  | 0 | RETIRED 487' OF 4" PL MP
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026133300 | 555 | EX | INSTALL 200'-2" PMIP | 2021-09-02 | 801 MCCOWAN ST | B | 14590.9404 | 19749.69 | 5158.7496 | 35% | 200 | 190 | 103.9457
KY | KY - EAST | 2631 | U938437 |  |  |  | 21026133600 | 2000 | EX | INVESTIGATE VALVE REPLACEMENT | 2022-06-30 | 240 BUCKLEY RD |  | 10000 | 0 | -10000 | 100% |  |  | 0
KY | KY - EAST | 2631 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 21026133900 | 583 | EX | INSTALL VRG CONTROLER | 2021-11-02 | US 60 | F | 6187.1439 | 0 | -6187.1439 | 100% |  |  | 0
KY | KY - EAST | 2631 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 21026134000 | 584 | EX | RETIRE DAMAGED CONTROLLER | 2021-11-02 | US 60 | F | 220.9908 | 0 | -220.9908 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026139100 | 557 | EX | EMER - INSTALL 5'-4" PMMP | 2021-09-01 | 35TH ST | A | 6493.0322 | 2800.66 | -3692.3722 | -57% | 2 | 2 | 1400.33 | INSTALLED MAIN ON TESTED 90 PSIG 1 HOUR SOAP TESTED FINAL CONN OP 44 PSIG
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026139200 | 558 | EX | EMER - RETIRE 5'-4" P-MP | 2021-09-01 | 35TH ST | A | 743.2708 | 5590.11 | 4846.8392 | 652% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026139800 | 555 | EX | INSTALL 100'-2" PMIP | 2021-09-29 | 5720 SWANSON DR | B | 27338.1249 | 19936.66 | -7401.4649 | -27% | 102 | 102 | 195.4575
KY | KY - EAST | 2631 | U938437 |  |  |  | 21026140100 | 559 | EX | INSTALL 52'-4"/6" PMIP/CSIP | 2022-05-25 | 240 BUCKLEY RD | B | 83495.319 | 67346.12 | -16149.199 | -19% | 52 | 35 | 1924.1749
KY | KY - EAST | 2631 | U938437 |  |  |  | 21026140200 | 560 | EX | RETIRE 47'-4"/6" BSIP/CSIP | 2022-05-25 | 240 BUCKLEY RD | B | 500 | 207.25 | -292.75 | -59% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026143700 | 559 | EX | INSTALL 4'-4" PMLP | 2021-09-28 | 301 RIVERSIDE DR | A | 3297.2047 | 478.5 | -2818.7047 | -85% | 5 | 4 | 119.625 | INSTALLED 4' OF 4" PL LP MAIN LINE TESTED 90 PSIG 1 HOUR SOAP TESTED FINAL CONN OP 10" WC
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026143800 | 560 | EX | RETIRE 4'-4" PMLP | 2021-09-28 | 301 RIVERSIDE DR | A | 295.4309 | 44.74 | -250.6909 | -85% |  |  | 0 | RETIRED MAIN DUE TO STEEL SADDLE TEE BIENG ON PL PIPE INSTALLED NEW SECTION OF PIPE
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026144600 | 559 | EX | INSTALL 12" SS | 2021-10-19 | 150 ARMCO RD | B | 13660.0322 | 25613.83 | 11953.7978 | 88% |  |  | 0 | INSTALLED 12" SS TO STOPPLE AND KILL 12" MAIN
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026144700 | 560 | EX | RETIRE 1273'-6/12/16" CS/BSHP | 2021-10-19 | 150 ARMCO RD | B | 388.1295 | 167.43 | -220.6995 | -57% |  |  | 0 | RETIRE 1207' OF 12" BS HP TO AK STEEL SOAP TESTED OP 113 PSIG
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026146300 | 559 | EX | INSTALL 4'-4" PMLP | 2021-10-07 | 317 RIVERSIDE DR | A | 2206.8953 | 424.36 | -1782.5353 | -81% | 4 | 4 | 106.09 | INSTALLED 4' OF 4" PLASTIC MAIN. PRESSURE TESTED 90LBS FOR 1HR.
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026146400 | 560 | EX | RETIRE 4'-4" P-LP | 2021-10-07 | 317 RIVERSIDE DR | A | 197.4141 | 39.69 | -157.7241 | -80% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026146800 | 588 | EX | RETIRE GMB #44535-AK STEEL | 2021-10-18 | 150 ARMCO RD | F | 2893.6188 | 3852.12 | 958.5012 | 33% |  |  | 0 | ALL FACILITIES REMOVED FROM AK STEEL BY MATT RYAN AND SHANE GIORDANO MAINLINE/SERVICE LINE ABANDONED ON 10/18/2021 BY CONSTRUCTION SERVICES M&R PAPERWORK COMPLETED BY CYNTHIA FARIS ON 10/25/2021
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026146900 | 2000 | EX | INVESTIGATE PIPE DEPTH | 2023-03-23 | 7117 US ROUTE 60 |  | 23315.9979 | 0 | -23315.9979 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026149000 | 555 | EX | INSTALL 75'-2" PMIP | 2021-11-02 | 1222 HILLCREST CT | A | 4287.763 | 765.35 | -3522.413 | -82% | 75 | 66 | 11.5962 | INSTALLED 66' OF 2" PL TESTED 90 PSIG 0005 MIN SOAP TESTED CAP OP 8 PSIG
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026150000 | 559 | EX | EMER - INSTALL 14'-4" PMLP | 2021-11-10 | 306 FERRY ST | A | 3163.1338 | 72137.82 | 68974.6862 | 2,181% | 20 | 14 | 5152.7014 | INSTALLED 16' OF 4" PL W/ 4 90'S TO GO ABOVE 24" CLAY TILE SEWER TESTED 90 PSIG 1 HR OVERRUN EXPLANATION: CROSSBORE FOUND- CAMERA CREW NEEDED AND ADDITIONAL HOURS NEEDED TO REMEDIATE THE CROSS-BORE ISSUE 2 MAINTENCE JOBS AND 1 PAVE JOB CHARGED BACK TO CAPITAL JOB AND WERE NOT ACCOUNTED FOR IN ORIGINAL PROPOSED COST, $26K IN FLAGGING AND RESTORATION CHARGED TO MAINTENCE JOBS AND $14K IN CAMERA WORK BY CONTRACTOR
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026150100 | 560 | EX | EMER - RETIRE 6'-4" P-LP | 2021-11-10 | 306 FERRY ST | A | 335.9749 | 669.23 | 333.2551 | 99% |  |  | 0 | REMOVED 4" PL FROM SEWER LINE CROSS BORE
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026150600 | 557 | EX | EMER - INSTALL 5'-2" PMMP | 2021-11-14 | BELMONT | A | 1696.2756 | 378.77 | -1317.5056 | -78% | 5 | 4 | 94.6925
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026150700 | 558 | EX | EMER - RETIRE 5'-2" PMP | 2021-11-14 | BELMONT | A | 335.9749 | 64.43 | -271.5449 | -81% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026153400 | 557 | EX | EMER - INSTALL 6'-4" PMIP | 2021-12-01 | 416 CAROLINE RD | A | 4080.2324 | 7455.58 | 3375.3476 | 83% | 10 | 10 | 745.558
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026153500 | 558 | EX | EMER - RETIRE 6'-4" PMIP | 2021-12-01 | 416 CAROLINE RD | A | 518.618 | 101.71 | -416.908 | -80% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026154000 | 555 | EX | INSTALL 160'-2" PMMP | 2022-02-11 | 1999 FERN DR | B | 33091.7151 | 28534.77 | -4556.9451 | -14% | 160 | 130 | 219.4982
KY | KY - EAST | 2631 | U938437 |  |  |  | 21026154600 | 584 | EX | RETIRE R-1354 | 2023-11-26 | 4570 LOUISA RD | F | 163.2711 | 8911.51 | 8748.2389 | 5,358% |  |  | 0
KY | KY - EAST | 2631 | U938437 |  |  |  | 21026154800 | 558 | EX | RETIRE 35'-3" CSMP | 2023-11-16 | PADDLE CREEK RD | B | 485.0228 | 27.2 | -457.8228 | -94% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026155700 | 577 | EX | INSTALL FENCE - SCADA BUILDING | 2022-08-22 | US 23 | F | 15936.4497 | 7557.57 | -8378.8797 | -53% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026156500 | 555 | EX | INSTALL 140'-2"/4" PMMP | 2021-12-21 | 101 A ST | A | 3669.7405 | 2096.07 | -1573.6705 | -43% | 140 | 141 | 14.8657
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026157400 | 2000 | EX | INVESTIGATE PROPERTY | 2023-10-25 | 100 HARRIS RD |  | 2000 | 930.65 | -1069.35 | -53% |  |  | 0 | PS&I CHARGED TO GROUND BED INSTALATION. TECH REQUESTING WORK IN NOTES HAS R ETIRED AND NO INFORMATION IS AVAILIBLE TO SEE WHAT WORK MAY OR MAY NOT HAVE BEEN ACOMPLISHED. D.LEMONS 10/25/2023
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026157800 | 557 | EX | INSTALL 5'-4" PMLP | 2021-12-30 | 216 PERRY | A | 4114.4273 | 2758.28 | -1356.1473 | -33% | 5 | 1 | 2758.28
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026157900 | 558 | EX | RETIRE 5'-4" PMLP | 2021-12-30 | PERRY | A | 72.8047 | 485.31 | 412.5053 | 567% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026993200 | 557 | EX | EMER- INSTALL 5'-4" PMMP | 2021-01-05 | STATE RT 1 | A | 4003.4824 | 3260.67 | -742.8124 | -19% | 1 | 4 | 815.1675 | INSTALLED 4' OF 4" P. PRESSURE TESTED AT 90LBS FOR 1HR. SOAP TESTED (2) 4" EF COUPLINGS AT OPERATING PRESSURE (11PSIG).
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026993300 | 558 | EX | EMER- RETIRE 5'-4" P-MP | 2021-01-05 | STATE RT 1 | A | 647.029 | 184.74 | -462.289 | -71% |  |  | 0 | REMOVED 4' OF DAMAGED 4" P
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026993401 | 557 | EX | INSTALL 10750'-2"/4"PMMP MAIN | 2022-09-16 | LEE ST | B | 1880428.7756 | 2072101.63 | 191672.8544 | 10% | 10750 | 11749 | 176.3641
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026993500 | 558 | EX | RETIRE 13650' OF 4"/6"BSLP | 2022-11-09 | LEE ST | B | 86.5975 | 80 | -6.5975 | -8% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026993600 | 557 | EX | EMER INST 40'-4" PMLP | 2021-01-07 | 2049 FOREST AV | A | 13260.7401 | 772.98 | -12487.7601 | -94% | 40 | 27 | 28.6289 | INSTALLED 28' OF 4" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 10" WC
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026993700 | 558 | EX | EMER RET 40'-4" BSLP/CSLP/P-LP | 2021-01-07 | ELMWOOD | A | 1322.2973 | 372.17 | -950.1273 | -72% |  |  | 0 | RETIRED 28' OF 4" STEEL MAIN AND 3 WAY TEE
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026996600 | 2000 | EX | OBTAIN SEWER AND ROAD PLANS | 2021-02-05 | BATH AV |  | 3500 | 0 | -3500 | 100% |  |  | 0
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 21026999201 | 566 | EX | RETIRE 3"PIP SERVICE LINE | 2023-06-26 | 924 SUMMIT RD | A | 6359.645 | 14749.54 | 8389.895 | 132% |  |  | 0 | STEP 3 NEEDS INVESTIGATED STEP 3 NEEDS STATE PERMIT STEP 3 NEEDS STATE PERMIT THIS IS A PAPER ABN. THIS LINE IS AN ACTIVE LINE BUT THEY ARE NOT OUR CUSTOMER. THEY ARE USING NATURAL ENERGY. OUR ASSETS ARE NOT WITHIN THE PROPERTY. U131418 J. PARKS 4-24-23
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026159700 | 559 | EX | EMER - INSTALL 4'-4" PMLP | 2022-01-11 | 222 34TH ST | A | 4455.398 | 1914.95 | -2540.448 | -57% | 4 | 4 | 478.7375
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026159800 | 560 | EX | EMER - RETIRE 4'-4" P-LP | 2022-01-11 | 222 34TH ST | A | 448.5353 | 6434.1 | 5985.5647 | 1,334% |  |  | 0 | RETIRED 4' OF 4" PL LP TO REMOVED STEEL SADDLE FROM PLASTIC MAIN
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026159900 | 557 | EX | EMER - INSTALL 2'-2" PMLP | 2022-01-12 | 431 ETNA ST | A | 2367.5988 | 2408.32 | 40.7212 | 2% | 2 | 2 | 1204.16
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026160000 | 558 | EX | EMER - RETIRE 2'2"P-LP D244381 | 2022-01-12 | 431 ETNA ST | A | 506.8997 | 487.19 | -19.7097 | -4% |  |  | 0
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026160300 | 910 | EX | RETIRED ELECTRONICS | 2021-08-17 | SKYLINE DR | F | 75.9523 | 422.53 | 346.5777 | 456% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026165300 | 595R | EX | INSTALL NEW GROUND BED | 2022-03-11 | 624 BIGGS LN | B | 69071.4307 | 78142.25 | 9070.8193 | 13% |  |  | 0 | GROUND BED INSTALLED BY MATCOR W/FOREMAN GENE PETITE. THE EXPECTED WELL LIFE OF THE GROUND BED AS INSTALLED IS CONSERVATIVELY 8AMPS/38YEARS OR 10AMPS/30YEARS. VENDER IS CONFIDENT WE WOULD COULD SEE 15AMPS/30YEARS. -OSS
KY | KY - EAST | 2631 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026169000 | 909 | EX | MAVITY HVAC UPGRADE | 2022-06-08 | US 60 | F | 15264.0767 | 5678.5 | -9585.5767 | -63% |  |  | 0
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026172301 | 557 | CO | INSTALL 5000' OF 2"PMMP MAIN | 2023-10-03 | VERNA | B | 1183513.1452 | 906953.7 | -276559.4452 | -23% | 4359 | 4923 | 184.2278
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026174900 | 555 | EX | INSTALL 50'-2" PMMP | 2022-05-10 | 923 DIEDRICH DR | B | 30717.8249 | 36910.2 | 6192.3751 | 20% | 50 | 50 | 738.204
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026175800 | 559 | EX | EMER - INSTALL 120'-3" PMLP | 2022-03-11 | 423 MARCIA ST | A | 12124.3189 | 32123.93 | 19999.6111 | 165% | 120 | 120 | 267.6994 | INSTALLED 120' OF 3" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 10" W C
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026175900 | 560 | EX | EMER - RETIRE 121'-3" P-LP | 2022-03-11 | 423 MARCIA ST | A | 373.4562 | 931.56 | 558.1038 | 149% |  |  | 0 | RETIRE 121' OF 3" PL DUE TO WATER AND STEEL FITTINGS ON PL MAIN
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026177000 | 557 | EX | EMER - INSTALL 2'-4" PMIP | 2022-03-17 | 1803 W LITTLE GARNER RD | A | 4197.8249 | 2292.91 | -1904.9149 | -45% | 0 | 2 | 1146.455
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026177100 | 558 | EX | EMER - RETIRE 2'-4" P-IP | 2022-03-17 | 1803 W LITTLE GARNER RD | A | 310.9595 | 2387.49 | 2076.5305 | 668% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026180500 | 555 | EX | INSTALL 160'-2" PMIP | 2022-07-13 | 1132 HOWARD DR | B | 36664.9938 | 22724.8 | -13940.1938 | -38% | 160 | 150 | 151.4987
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026180700 | 557 | EX | EMER - INSTALL 3'-3" PMIP | 2022-04-09 | WOODHAVEN | A | 4036.7887 | 6701.19 | 2664.4013 | 66% | 0 | 4 | 1675.2975
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026180800 | 558 | EX | EMER - RETIRE 3'-3" PMIP | 2022-04-09 | WOODHAVEN | A | 418.4749 | 61.4 | -357.0749 | -85% |  |  | 0
KY | KY - EAST | 2631 | U937670 |  |  |  | 22026181500 | 2000 | EX | ENE PS&I FOR WESTWOOD PH2 SMRP | 2023-09-06 | VERNA | B | 25000 | 0 | -25000 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026182300 | 584 | EX | RETIRE PAPER RECORD GAUGE | 2022-04-20 | 490 FERGUSON RD | F | 329.4627 | 144.38 | -185.0827 | -56% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026184500 | 555 | EX | INSTALL 250'-4" PMLP/CSLP | 2022-08-09 | 3430 EUCLID AV A | B | 60316.4006 | 63976.36 | 3659.9594 | 6% | 252 | 234 | 273.4032
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026190600 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-06-23 | 624 BIGGS LN | F | 4801.1928 | 817.09 | -3984.1028 | -83% |  |  | 0 | CCC 71454 RETIRED ERX AND INSTALLED NEW MIWI350
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026191000 | 910 | EX | RETIRED ELECTRONICS EQUIPMENT | 2022-06-23 | 624 BIGGS LN | F | 124.8731 | 261.55 | 136.6769 | 109% |  |  | 0 | CCC 71454 RETIRE ERX AND INSTALLED NEW MIWI 350
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026191700 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-07-25 | BARBECUE RD | F | 4801.1928 | 10605.54 | 5804.3472 | 121% |  |  | 0 | UPGRADED ERX TO MIWI JOSH MULLINS
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026191800 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-07-25 | BARBECUE RD | F | 124.8731 | 20.04 | -104.8331 | -84% |  |  | 0
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026191900 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-06-23 | 828 MAIN ST RR | F | 4801.1928 | 744.93 | -4056.2628 | -84% |  |  | 0 | CCC 71454
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026192000 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-06-23 | 828 MAIN ST RR | F | 124.8731 | 922.45 | 797.5769 | 639% |  |  | 0 | CCC 71454
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026192100 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-07-26 | 243 KENWOOD BV | F | 4801.1928 | 2317.01 | -2484.1828 | -52% |  |  | 0 | CCC 75023
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026192200 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-07-26 | 243 KENWOOD BV | F | 124.8731 | 884.51 | 759.6369 | 608% |  |  | 0 | CCC 75023 UPGRADED ERX TO MIWI J.MULLINS
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026196200 | 557 | EX | EMER - INSTALL 1'-2" PMMP | 2022-06-02 | 1020 BELMONT ST | A | 2866.3857 | 6510.29 | 3643.9043 | 127% | 0 | 1 | 6510.29 | INSTALLED 1' OF 2" PL DUE TO FACILTY DAMAGE TESTED 90 PSIG 0005 MIN SOAP TE STED FINAL CONN OP 42 PSIG REVISED EXECUTE COMMENTS: INSTALLED 1' OF 2" PL DUE TO FACILITY DAMAGE TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 42 PSIG/MCOLLETT 7/8/22
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026196300 | 558 | EX | EMER - RETIRE 1'-2" P-MP | 2022-06-02 | 1020 BELMONT ST | A | 497.9695 | 1254.11 | 756.1405 | 152% |  |  | 0 | RETIRED 1' OF 2" PL MP DUE TO FACILITY DAMAGE SOAP TESTED OP TO VERIFY GAS SHUTOFF
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026198200 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-08-11 | 29022 E MAYO TRAIL | F | 4801.1928 | 5532.75 | 731.5572 | 15% |  |  | 0 | CC 76915 UPGRADDED ERX TO MIWI 350
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026198300 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-08-11 | 29022 E MAYO TRAIL | F | 124.8731 | 467.24 | 342.3669 | 274% |  |  | 0 | CC 76915 UPDATTED ERX TO MIWI 350
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026198700 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-09-13 | 100 BOY SCOUT RD | F | 4801.1928 | 6293.17 | 1491.9772 | 31% |  |  | 0 | CC 497 CC 497 REPLACED OLD ERX WITH NEW MIWI350 SGIORDANO 9-13-2022
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026198800 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-09-13 | 100 BOY SCOUT RD | F | 124.8731 | 1014.14 | 889.2669 | 712% |  |  | 0 | CC 497 REPLACED ERX WITH NEW MIWI350 SGIORDANO 9-13-2022
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026199900 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-09-15 | 516 3RD ST RR | F | 4801.1928 | 6476.38 | 1675.1872 | 35% |  |  | 0 | CC 118 INSTALLED NEW MIWI350 RETIRED OLD ERX SGIORDANO 9-15-22
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026200200 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-09-15 | 516 3RD AVE RR | F | 124.8731 | 1400.9 | 1276.0269 | 1,022% |  |  | 0 | CC 118 INSTALLED NEW MIWI350 SGIORDANO 9-15-22 C 2820
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026200300 | 559 | EX | EMER - INSTALL 5'-2" PMIP | 2022-06-07 | 2210 SLOAN ST | A | 2610.0199 | 9101.9 | 6491.8801 | 249% | 3 | 5 | 1820.38 | REPLACED 5' SECTION OF 2" PMMP. TESTED MAIN AT 90 PSIG FOR 1 HOUR AND TEST WAS GOOD. TESTED 2X1 EF TEES AT 90 PSIG FOR 5 MINS AND SOAP TESTED THE CAPS AND DEAD ENDS AT OP FOR 5 MINS. ALL TEST ARE GOOD.
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026200900 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-09-14 | PAUL COFFEY BV | F | 4801.1928 | 6137.4 | 1336.2072 | 28% |  |  | 0 | CC 632 UPGRADED TO MIWI 350 PAPERWORK DONE BY J.MULLINS
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026201000 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-09-14 | PAUL COFFEY BV | F | 124.8731 | 485.58 | 360.7069 | 289% |  |  | 0 | CC 632 UPGRADED TO MIWI 350 PAPERWORK DONE BY J.MULLINS
KY | KY - EAST | 2631 | U938437 |  |  |  | 22026205200 | 555 | EX | INSTALL 115'-2" PMMP | 2022-10-05 | 1519 MAPLE ST | B | 42423.5179 | 21273.79 | -21149.7279 | -50% | 117 | 103 | 206.5417 | CJ HUGHES CASEY PACK'S CREW INSTALLED 103' 2" STEEL/PLASTIC MAIN LINE EXTEN TION AND A NEW 1" PLASTIC SERVICE TO 1519 MAPLE ST 10/6/22 MBLANKE U123965
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026205500 | 2000 | EX | INVESTIGATE AND STAKE ROW | 2022-10-26 | CENTRAL PY |  | 7194 | 0 | -7194 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026205600 | 557 | EX | INSTALL 1200'-2" PMMP | 2022-10-03 | CENTRAL PY | B | 61578.4138 | 162971.11 | 101392.6962 | 165% | 1204 | 1268 | 128.5261 | LEVEL 2 BUDGET VARIANCE EXPLANATION FORM WAS SUBMITTED FOR APPROVAL IN WMSDOCS PER VAPIERCE 5/25/23
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026206400 | 588 | EX | RETIRE ELECTRONIC | 2022-09-19 | 2236 MONTGOMERY AV | F | 65.0112 | 2331.95 | 2266.9388 | 3,487% |  |  | 0 | RETIRED OLD MINIAT INSTALLED NEW EC350 DASH 9-19-2022
KY | KY - EAST | 2631 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026208400 | 2000 | EX | BIGGS LANE - INV EASEMENTS | 2023-04-14 | 624 BIGGS LN |  | 5000 | 0 | -5000 | 100% |  |  | 0 | CC 4026
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026210700 | 586 | EX | RETIRE METAL BUILDING | 2022-12-15 | 419 BUCKLEY RD | F | 1009.5809 | 0 | -1009.5809 | 100% |  |  | 0 | REG STATION AND BUILDING RETIRED DASH 12-15-22
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026211000 | 557 | EX | EMER - INSTALL 3'-4" PMMP | 2022-07-06 | 35TH | A | 12351.4608 | 8542 | -3809.4608 | -31% | 2 | 3 | 2847.3333 | CUT OUT 3' OF 4" PL MP AND REPLACED WITH NEW 3' OF 4" PL MP TESTED 90 PSIG 1 HOUR
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026211100 | 558 | EX | EMER - RETIRE 3'-4" PMMP | 2022-07-06 | 35TH | A | 477.8601 | 449.88 | -27.9801 | -6% |  |  | 0 | RETIRED 3' OF 4" PL MP AND INSTALLED NEW 3' OF 4" PL TESTED 90 PSIG 1 HOUR SOAP TESTD FINAL CONN OP 40 PSIG
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026211800 | 588 | EX | RETIRE GMB SETTING | 2023-01-10 | 100 WURTS RD R | F | 1288.7874 | 1541.41 | 252.6226 | 20% |  |  | 0 | GMB NO CC NEEDED
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026213800 | 560 | EX | EMER - RETIRE 150'-2" P-IP | 2022-08-01 | TOOTSIE DR | A | 4412.2636 | 4136.05 | -276.2136 | -6% |  |  | 0 | ABANDONED 150' OF 2" PLASTIC. SOAP TESTED ABANDONMENT AT OP. PRESS. 15MIN.
KY | KY - EAST | 2631 | U938437 |  |  |  | 22026214200 | 2000 | EX | LAND RESEARCH | 2023-09-06 |  | B | 4428 | 2481.72 | -1946.28 | -44% |  |  | 0
KY | KY - EAST | 2631 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026214400 | 910 | EX | MAVITY HVAC/RTU | 2022-06-08 | US 60 | F | 55.5311 | 0 | -55.5311 | 100% |  |  | 0 | UPGRADED RTU
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026216300 | 587 | EX | INSTALL VRG CONTROLLER | 2023-02-09 | US23--ASHLAND OIL | F | 10806.1191 | 28545.09 | 17738.9709 | 164% |  |  | 0 | CC 15047 CC 15628 CC 15628 CC 15628 CC 15628 CC 16352 NOT ON SITE CAPITAL PAPERWORK/ISO SKETCH
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026216400 | 588 | EX | RETIRE CONTROLLERS | 2023-02-09 | US23--ASHLAND OIL | F | 84.9152 | 572.67 | 487.7548 | 574% |  |  | 0 | RETIRED CONTROLLERS, INSTALLED NEW VRG'S
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026218400 | 560 | EX | RETIRE 2'-4" BSLP | 2022-08-09 | 3430 EUCLID AV | B | 84.9152 | 0 | -84.9152 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026218500 | 555 | EX | INSTALL 35'-2"/4 PMLP | 2022-09-07 | 508 BELLEFONTE ST A | A | 16435.9913 | 8610.21 | -7825.7813 | -48% | 35 | 39 | 220.7746 | INSTALLED 2' OF 4" PL AND 37' OF 2" PL LP TESTED 90 PSIG 1 HR
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026219600 | 555 | EX | INSTALL 90'-2" PMIP | 2022-12-15 | 85 YANKEES LN | B | 21041.6638 | 50608.23 | 29566.5662 | 141% | 90 | 57 | 887.8637
KY | KY - EAST | 2631 | U937670 |  |  |  | 22026223300 | 2000 | EX | EN PS&I FOR C-16 VALVE REPL | 2023-02-14 | CHESTNUT ST | B | 10000 | 0 | -10000 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026226600 | 2000 | EX | INVEST ROW/OBTAIN EASEMENT | 2023-02-03 | 85 YANKEES LN |  | 11694 | 0 | -11694 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026228900 | 561 | EX | EMER - INSTALL 40'-2" PMIP | 2022-10-13 | TONI DR | B | 32269.3764 | 37570.14 | 5300.7636 | 16% | 20 | 88 | 426.9334
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026229000 | 562 | EX | EMER - RETIRE 40'-2" PIP | 2022-10-13 | TONI DR | B | 132.427 | 0 | -132.427 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026229300 | 2000 | EX | EMER RELOCATION & INVST ROW | 2023-01-17 | TONI DR |  | 11694 | 0 | -11694 | 100% |  |  | 0
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026230800 | 558 | EX | EMER - RETIRE 3'-2" P-IP | 2022-10-06 | 215 TONI DR C | A | 1985.3283 | 1400.06 | -585.2683 | -29% | 0 |  | 0 | CONTRACTOR HIT MISS MARKED MAIN CUT OUT DAMAGED SECTION AND EF PURGE POINT ON END OF MAIN LINE SOAP TESTED OP 7 PSIG
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026231600 | 557 | EX | EMER - INSTALL 2'-4" PMMP | 2022-10-18 | BRENDA SUE | A | 5460.0467 | 196.47 | -5263.5767 | -96% | 2 | 2 | 98.235 | INSTALLED 2' OF 4" PL MP TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 40 P SIG
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026231700 | 558 | EX | EMER - RETIRE 2'-4" PMMP | 2022-10-18 | BRENDA SUE | A | 263.239 | 24.23 | -239.009 | -91% |  |  | 0 | RETIRED 2' OF 4" PL MP DUE TO LEAKAGE SOAP TESTED TO VERFY SHUTDOWN
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026232200 | 587 | EX | INSTALL SKID MOUNTED GMB | 2022-12-15 | CENTER ST | F | 56170.7039 | 40259.26 | -15911.4439 | -28% |  |  | 0 | INSTALLED NEW SKID MOUNTED METER SETTING DASH 12-15-22
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026232300 | 588 | EX | RETIRE GMB SETTING | 2022-12-15 | CENTER ST | F | 263.239 | 1984.01 | 1720.771 | 654% |  |  | 0 | INSTALLED NEW SKID MOUNT METER SETTING AND RETIRED OLD METER AND REGULATORS DASH 12-15-22
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026232700 | 588 | EX | RETIRE GMB W/22-9790457-00 | 2022-12-21 | 3700 13TH ST | F | 545.7645 | 0 | -545.7645 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026233100 | 2000 | EX | INVESTIGATE ROW & RR PERMIT | 2022-12-15 | CENTER ST |  | 4378 | 0 | -4378 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026234200 | 565 | EX | INSTALL 100'-6"PMMP S/L | 2022-12-06 | 74 CENTER ST | B | 78909.8457 | 60246.05 | -18663.7957 | -24% | 120 |  | 0 | CJH JOE HADLEY REPLACED SL, TESTED SL AT 0106PSIG/0200HRS, OPEN CUT, SOAP TESTED FC/CAP AT OP, EXT CORR INSP, NO ANODE, WRAPPED EXPOSED MAIN, DS 12062022
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026234300 | 588 | EX | RETIRE GMB SETTING | 2022-11-21 | 101 23RD ST | F | 725.239 | 0 | -725.239 | 100% |  |  | 0 | RETIRED GMB SETTING REMOVED METER BLIND PLATED SERVICE GAS NO LONGER NEEDED
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026235200 | 555 | EX | INSTALL 200'-2" PMIP | 2022-12-15 | 65 BROWN LN | B | 38455.6638 | 11987.46 | -26468.2038 | -69% | 200 | 241 | 49.7405
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026235800 | 557 | EX | EMER - INSTALL 3'-4" PMMP | 2022-10-10 | OLD LOCKANDDAM | A | 18999.7951 | 7089.71 | -11910.0851 | -63% | 2 | 3 | 2363.2367 | FOUND CLAMPS ON 4" PL MAIN CUT OUT AND INSTALLED NEW MAIN TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 15 PSIG
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026235900 | 558 | EX | EMER - RETIRE 3'-4" P-MP | 2022-10-10 | OLD LOCKANDDAM | A | 117.5985 | 22647.66 | 22530.0615 | 19,158% |  |  | 0 | RETIRED 4" PL MAIN WITH CLAMPS ON IT TO INSTALL NEW
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026240200 | 557 | EX | EMER - INSTALL 100'-4" PMLP | 2022-12-02 | 909 ASHLAND AV | A | 38890.2222 | 5141.88 | -33748.3422 | -87% | 100 | 93 | 55.289 | INSTALLED 93' OF PL AND ST TESTED 90 PSIG 1 HR SOAP TESTED WELD CAPS AND SSTEE CAPS 10" WC
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026240300 | 558 | EX | EMER - RETIRE 100'-4" BSLP | 2022-12-02 | 909 ASHLAND AV | A | 129.6266 | 285.28 | 155.6534 | 120% |  |  | 0 | RETIRED 75' OF 4" BS DUE TO LEAKAGE
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026240400 | 560 | EX | PAPER ONLY - RETIRE BSIP MAIN | 2022-11-17 | OLD BUCKLEY RD | B | 119.2135 | 0 | -119.2135 | 100% |  |  | 0
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026241300 | 557 | EX | EMER - INSTALL 5'-4" PMMP | 2022-12-06 | 1173 STATE RT 1 | A | 10162.4624 | 1144.39 | -9018.0724 | -89% | 55 | 3 | 381.4633 | INSTALLED 3' OF 4" PL DUE TO LEAKAGE ON SERVICE TEE TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 11 PSIG
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026241400 | 558 | EX | EMER - RETIRE 5'-4" PMP | 2022-12-06 | STATE RT 1 | A | 117.5985 | 91.78 | -25.8185 | -22% |  |  | 0 | RETIRE 4" MP TO DUE TO LEAKAGE ON SERVIEC TEE TO INSTALL NEW
KY | KY - EAST | 2631 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026244600 | 577 | EX | INSTALL BUILDING AND FENCE | 2022-03-17 | OLD US 23 | F | 28935.3221 | 0 | -28935.3221 | 100% |  |  | 0 | INSTALLED COMM BUILDING AND FENCE DASH 3-17-22
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026245500 | 577 | EX | INSTALL REG STATION BUILDING | 2022-11-18 | US23--ASHLAND OIL | F | 128388.6752 | 12285 | -116103.6752 | -90% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 23026246000 | 587 | EX | INSTALL M&R CRANE - MARATHON | 2022-11-18 | US23--ASHLAND OIL | F | 36312.6752 | 14182.67 | -22130.0052 | -61% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 23026246200 | 585 | EX | INSTALL VRG - MIS FACILITY | 2022-11-02 | US 60 | F | 449.3532 | 0 | -449.3532 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 23026246300 | 586 | EX | INSTALL VRG - RETIRE MIS FAC | 2022-11-02 | US 60 | F | 132.4844 | 0 | -132.4844 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 23026246800 | 561 | EX | INSTALL 800'-4" PMMP | 2023-04-13 | MONTGOMERY AV | B | 369832.3416 | 248116.67 | -121715.6716 | -33% | 800 | 409 | 606.6422
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 23026246900 | 562 | EX | RETIRE 1000'-4" P-MP | 2023-04-13 | MONTGOMERY AV | B | 123.4477 | 0 | -123.4477 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 23026247100 | 557 | EX | EMER - INSTALL 9'-4" CSMP/PMP | 2022-09-26 | ELWOOD | A | 14951.5544 | 5323.15 | -9628.4044 | -64% | 9 | 9 | 591.4611 | LOWERED MAIN DUE TO LEAKAGE AND 14" WATER LINE TESTED 90 PSIG 0005 MIN SOAP TESTED FINAL CONN OP 40 PSIG
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 23026247200 | 558 | EX | EMER - RETIRE 9'-4" CSMP | 2022-09-26 | ELWOOD | A | 149.6969 | 806.29 | 656.5931 | 439% |  |  | 0 | RETIRED 9' OF 4" ST TO LOWER FOR 14" WATER MAIN SOAP TESTED OP TO VERIFY AD EQUATE SHUT DOWN 40 PSIG
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 23026247600 | 2000 | EX | KDMC - INVT. ROW/ STAKE ROW | 2023-06-13 | MONTGOMERY AV |  | 7184 | 0 | -7184 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 23026248600 | 558 | EX | RETIRE 3'-3" PMLP | 2023-01-10 | 22ND | A | 1635.0284 | 3012.93 | 1377.9016 | 84% |  |  | 0 | RETIRED 20' OF 3" PL MAIN DUE TO FACILITY DAMAGE SOAP TESTED OP 9.5" WC
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 23026249100 | 555 | EX | INSTALL 100'-2" PMMP | 2023-02-28 | 15514 RICHLAND CT | A | 7008.1595 | 13611.51 | 6603.3505 | 94% | 100 | 128 | 106.3399 | INSTALLED NEW MAIN ON RICHLAND CT TESTED 90 PSIG 1 HR SOAP TESTED BRANCHING TEE CAP AND PURGE POINT CAP OP 14 PSIG
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026249200 | 588 | EX | GMB TO CAB CONVERSION | 2023-01-17 | 23 HARRIS RD | F | 132.4844 | 858.55 | 726.0656 | 548% |  |  | 0 | CONVERTED FROM GMB TO CAB SGIORDANO
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026251100 | 587 | EX | INSTALL EC-350 UNIT | 2023-01-24 | 15085 OLD US 23 CAT | F | 3195.3221 | 1808.88 | -1386.4421 | -43% |  |  | 0 | INSTALLED NEW EC350 DASH 1-24-23
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026251200 | 588 | EX | RETIRE PAPER BILLING CHART | 2023-01-24 | LINE-B/OLD-US23 CAT | F | 131.2422 | 975.93 | 844.6878 | 644% |  |  | 0 | RETIRED CHART INSTALLED NEW EC350 DASH 1-24-23
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026251300 | 587 | EX | INSTALL EC 350 UNIT | 2023-03-13 | 23< HARRIS RD | F | 7475.3221 | 8141.46 | 666.1379 | 9% |  |  | 0 | INSTALLED NEW EC350 TO REPLACE PAPER BILLING CHART
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026251400 | 588 | EX | RETIRE PAPER BILLING CHART | 2023-03-13 | 23< HARRIS RD | F | 131.2422 | 870.82 | 739.5778 | 564% |  |  | 0 | RETIRE PAPER BILLING CHART
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026254200 | 584 | EX | RETIRE RECORDING GAUGE | 2023-03-01 | 220 LOCK LN | F | 552.5683 | 107.1 | -445.4683 | -81% |  |  | 0 | CC 10596 RETIRE PAPER CHART SHANE G. 03012023
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 23026255800 | 2000 | EX | INVESTIGATE ROW / OBTAIN EASMT | 2023-05-01 | ALLEY |  | 11694 | 0 | -11694 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 23026255900 | 2000 | EX | RESEARCH ROW/OBTAIN EASEMENT | 2023-03-23 | 15514 RICHLAND CT |  | 7184 | 0 | -7184 | 100% |  |  | 0
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026256700 | 584 | EX | RETIRE PAPER GAUGE | 2023-02-21 | 964 US 23 | F | 138.8485 | 756.49 | 617.6415 | 445% |  |  | 0 | CC 17512 REMOVED PAPER PRESSURE GAUGE
KY | KY - EAST | 2631 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 23026257200 | 909 | EX | INSTALL MIWI AND SUPER SOLAR | 2023-08-15 | 516 3RD ST RR | F | 12042.2854 | 3080.61 | -8961.6754 | -74% |  |  | 0 | CC 41028
KY | KY - EAST | 2631 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 23026257300 | 584 | EX | RETIRE CHART | 2023-08-15 | 516 3RD ST RR | F | 124.7348 | 386.09 | 261.3552 | 210% |  |  | 0
KY | KY - EAST | 2631 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 23026257500 | 909 | EX | INSTALL MIWI AND SUPER SOLAR | 2023-07-12 | 1030 WINSLOW RD | F | 23732.2854 | 3917.88 | -19814.4054 | -83% |  |  | 0
KY | KY - EAST | 2631 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 23026257600 | 584 | EX | RETIRE PAPER CHAT | 2023-07-12 | 1030 WINSLOW RD | F | 121.7239 | 575.02 | 453.2961 | 372% |  |  | 0
KY | KY - EAST | 2631 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 23026257700 | 909 | EX | INSTALL MIWI AND SUPER SOLAR | 2023-08-16 | 78 ROSE STREET | F | 22126.2854 | 3552.01 | -18574.2754 | -84% |  |  | 0
KY | KY - EAST | 2631 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 23026257800 | 584 | EX | RETIRE PAPER CHART | 2023-08-16 | 78 ROSE STREET | F | 121.7239 | 1141.91 | 1020.1861 | 838% |  |  | 0
KY | KY - EAST | 2631 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 23026258100 | 909 | EX | INSTALL MIWI AND SUPER SOLAR | 2023-07-13 | 210 55TH ST | F | 20638.2854 | 4339.86 | -16298.4254 | -79% |  |  | 0 | CC 41992
KY | KY - EAST | 2631 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 23026258200 | 584 | EX | RETIRE PAPER CHART | 2023-07-13 | 210 55TH ST | F | 121.7239 | 0 | -121.7239 | 100% |  |  | 0
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026258600 | 557 | EX | EMER - INSTALL 5'-4" PMIP | 2023-02-15 | 104 BELLEFONTE CR | A | 23135.0467 | 29274.5 | 6139.4533 | 27% | 5 | 3 | 9758.1667 | INSTALLED 3' OF 4" PL DUE TO BORE CREW BORING INTO MAIN TESTED 90 PSIG 1 HR
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 23026258700 | 558 | EX | EMER- RETIRE 5'-4" PMIP | 2023-02-15 | BELLEFONTE ST | A | 137.555 | 1956.38 | 1818.825 | 1,322% |  |  | 0 | RETIRED 3' OF 4" IP DUE TO BORE CREW HITTING MAIN SOAP TESTED OP 7 PSIG TO VERIFY SQUEEZE OFF
KY | KY - EAST | 2631 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 23026258900 | 909 | EX | INSTALL MIWI AND SUPER SOLAR | 2023-09-01 | PAUL COFFEY BV | F | 22126.2854 | 5852.27 | -16274.0154 | -74% |  |  | 0
KY | KY - EAST | 2631 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 23026259200 | 909 | EX | INSTALL MIWI AND SUPER SOLAR | 2023-07-14 | 240 BUCKLEY RD | F | 21353.2854 | 4121.74 | -17231.5454 | -81% |  |  | 0 | CC 37280
KY | KY - EAST | 2631 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 23026259300 | 584 | EX | RETIRE PAPER CHART | 2023-07-14 | 240 BUCKLEY RD | F | 121.7239 | 0 | -121.7239 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 23026259400 | 909 | EX | INSTALL MIWI AND SUPER SOLAR | 2023-07-18 | 309 PIKE ST RR | F | 20638.2854 | 3579.71 | -17058.5754 | -83% |  |  | 0
KY | KY - EAST | 2631 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 23026259500 | 584 | EX | RETIRE PAPER CHART | 2023-07-18 | 309 PIKE ST RR | F | 121.7239 | 347.11 | 225.3861 | 185% |  |  | 0
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026259800 | 909 | EX | INSTALL ERX W/SUPER SOLAR | 2023-03-02 | JEFFERSON ST | F | 5058.9621 | 3465.31 | -1593.6521 | -32% |  |  | 0 | CC# 18720. 3/2/23 DSASH
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026259900 | 584 | EX | RETIRE PAPER CHART | 2023-03-02 | JEFFERSON ST | F | 138.8485 | 277.39 | 138.5415 | 100% |  |  | 0 | CC# 18720. 3/2/23 DSASH CC# 18720
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026260000 | 909 | EX | INSTALL ERX W/SUPER SOLAR | 2023-02-28 | 1271 RT 5 | F | 5058.9621 | 3193.7 | -1865.2621 | -37% |  |  | 0 | CC# 18341. 2/28/23 DSASH CC# 21913. P2P OK.
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026260100 | 584 | EX | RETIRE PAPER GAUGE | 2023-02-28 | 1271 RT 5 | F | 138.8485 | 257.79 | 118.9415 | 86% |  |  | 0 | CC# 18341. 2/28/23 DSASH
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026260200 | 909 | EX | INSTALL ERX W/SUPER SOLAR | 2023-02-22 | 1001 RIVERSIDE DR | F | 6314.9621 | 4114.48 | -2200.4821 | -35% |  |  | 0 | CC 17668 NOT ON SITE CAPITAL PACKET PAPERWORK NOT ONSITE. ISO UPDATES CC 21100 ANNUAL GAUGE INSP AND P2P WITH GAS CONTROL COMPLETE.
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026260300 | 584 | EX | RETIRE PAPER CHART | 2023-02-22 | 1001 RIVERSIDE DR | F | 138.8485 | 564.75 | 425.9015 | 307% |  |  | 0 | CC 17668
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026260400 | 909 | EX | INSTALL ERX W/SUPER SOLAR | 2023-02-23 | 2149 OLD US 23 | F | 6314.9621 | 3437.82 | -2877.1421 | -46% |  |  | 0 | CC 17834 NOT ON SITE. CAPITAL PACKET PAPERWORK NOT ON SITE ISO UPDATES CC 21100 ANNUAL GAUGE INSP AND P2P WITH GAS CONTROL COMPLETE
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026260500 | 584 | EX | RETIRE PAPER CHART | 2023-02-23 | 2149 OLD US 23 | F | 138.8485 | 605.66 | 466.8115 | 336% |  |  | 0 | CC 17834
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026260900 | 909 | EX | INSTALL ERX W/SUPER SOLAR | 2023-03-17 | LAUREL ST | F | 5458.9621 | 1872.11 | -3586.8521 | -66% |  |  | 0 | CC 20969 CC 24221 P2P OK WITH GC.
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026261000 | 584 | EX | RETIRE PAPER CHART | 2023-03-17 | LAUREL ST | F | 138.8485 | 174.56 | 35.7115 | 26% |  |  | 0 | CC 20961
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026261200 | 909 | EX | INSTALL ULTRASONIC METER | 2023-12-14 | US 60 | F | 47951.5304 | 36758.54 | -11192.9904 | -23% |  |  | 0
KY | KY - EAST | 2631 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 23026261700 | 909 | EX | INSTALL MIWI AND SUPER SOLAR | 2023-07-17 | CATLETT CREEK ROAD | F | 21353.2854 | 3770.68 | -17582.6054 | -82% |  |  | 0
KY | KY - EAST | 2631 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 23026261800 | 584 | EX | RETIRE PAPER CHART | 2023-07-17 | CATLETT CREEK ROAD | F | 121.7239 | 642.64 | 520.9161 | 428% |  |  | 0 | CC 37443
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 23026262200 | 557 | EX | EMER - INSTALL 4'-2" PMMP | 2023-02-21 | US 60 | A | 2419.7892 | 15777.13 | 13357.3408 | 552% | 4 | 4 | 3944.2825 | INSTALLED 4' OF 2" PLASTIC MAIN. PRESSURE TESTED AT 90LBS FOR 1 HR.
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 23026262300 | 558 | EX | EMER - RETIRE 4'-2" PMMP | 2023-02-21 | US 60 | A | 260.4446 | 242.84 | -17.6046 | -7% |  |  | 0 | REMOVED 4' OF DAMAGED 2" PLASTIC
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026262601 | 577 | EX | INSTALL CHAIN LINK FENCE | 2023-12-29 | 624 BIGGS LN | F | 39848.4833 | 72669.9 | 32821.4167 | 82% |  |  | 0 | CC 44278 NOT ON SITE CC 53373 CC 53373 CC 57440 CC 58157
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026264500 | 557 | EX | EMER - INSTALL ~5'-4" PM/CSMP | 2023-03-02 | MIDLAND TRAIL | A | 2069.4953 | 929.35 | -1140.1453 | -55% | 5 | 5 | 185.87
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026264600 | 558 | EX | EMER - RETIRE ~5'-4" CSMP | 2023-03-02 | MIDLAND TRAIL | A | 67.4953 | 207.34 | 139.8447 | 207% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 23026265600 | 557 | EX | EMER - INSTALL 4'-6" PMIP | 2023-03-07 | 508 OLD BUCKLEY RD | A | 12463.1003 | 19713.32 | 7250.2197 | 58% | 34 | 4 | 4928.33
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 23026265700 | 558 | EX | EMER - RETIRE 4'-6" P-IP | 2023-03-07 | 508 OLD BUCKLEY RD | A | 391.4196 | 0 | -391.4196 | 100% |  |  | 0
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026266501 | 575 | EX | ACQUIRE EASEMENT | 2023-12-06 | 624 BIGGS LN | F | 49332.6068 | 62488.9 | 13156.2932 | 27% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 23026269500 | 557 | EX | EMER - INSTALL 4'-2" PIP | 2023-03-28 | WURTLAND | A | 7943.8116 | 2717.09 | -5226.7216 | -66% | 4 | 4 | 679.2725
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 23026269600 | 558 | EX | EMER - RETIRE 5'-2" PIP | 2023-03-28 | WURTLAND | A | 134.4334 | 0 | -134.4334 | 100% |  |  | 0
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 23026270200 | 560 | EX | EMER - RETIRE 5'-2" PIP | 2022-06-07 | 2210 SLOAN ST | A | 288.6068 | 0 | -288.6068 | 100% |  |  | 0 | REPLACED 5' SECTION OF 2" PMMP. TESTED MAIN AT 90 PSIG FOR 1 HOUR AND TEST WAS GOOD. TESTED 2X1 EF TEES AT 90 PSIG FOR 5 MINS AND SOAP TESTED THE CAPS AND DEAD ENDS AT OP FOR 5 MINS. ALL TEST ARE GOOD.
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 23026270300 | 559 | EX | EMER - INSTALL 2'-4" PMMP | 2023-04-02 | 2503 CENTER ST | A | 9141.6411 | 526.5 | -8615.1411 | -94% | 2 | 2 | 263.25
KY | KY - EAST | 2631 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 23026270400 | 560 | EX | EMER - RETIRE 110'-4" P-MP | 2023-04-02 | 2503 CENTER ST | A | 137.555 | 537.22 | 399.665 | 291% |  |  | 0 | RETIRED 110' OF 4" PL MP DUE TO BUILDING COLLAPSING TESTED CAP 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 38 PSIG
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026271400 | 557 | EX | EMER - INSTALL ~5'-2" PMMP | 2023-04-10 | 3624 29TH ST | A | 5664.5366 | 7739.82 | 2075.2834 | 37% | 10 | 1 | 7739.82 | INSTALLED 1' OF 2" PL MP DUE TO DAMAGE TESTED 90 PSIG 1 HR SOAP TESTED FINA L CONN OP 40 PSIG
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026271500 | 558 | EX | EMER - RETIRE ~5'-2" PMMP | 2023-04-10 | 3624 29TH ST | A | 114.3981 | 709.93 | 595.5319 | 521% |  |  | 0 | RETIRED 1" OF 2" PL MP DUE TO FACILITY DAMAGE SOAP TESTED TO VERIFY SQUEEZE OFF OP 40 PSIG
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026275200 | 557 | EX | EMER - INSTALL 3'-2" PMIP | 2023-05-05 | 31600 US 23 | A | 9765.5645 | 5562.78 | -4202.7845 | -43% | 3 | 3 | 1854.26 | INSTALLED 3' OF 2" MAIN DUE TO DAMAGE BY BORE CREW TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 5.5 PSIG
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026275300 | 558 | EX | EMER - RETIRE 3'-2" PIP | 2023-05-05 | 31600 US 23 | A | 134.4334 | 235.76 | 101.3266 | 75% |  |  | 0 | RETIRED 3' OF 2" PL DUE TO BORE CREW HITTING MAIN TIEING CONDUIT TOGHETHER
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026276500 | 560 | EX | EMER - ABANDON 5'-4"CSLP | 2020-04-20 | 301 MAIN ST | A | 821.1159 | 734.44 | -86.6759 | -11% |  |  | 0
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026277500 | 2000 | EX | INVESTIGATE R/W & EASEMENTS | 2023-08-09 | GREENUP ST |  | 17751 | 0 | -17751 | 100% |  |  | 0
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026277600 | 557 | EX | INSTALL 595'-2"PMMP | 2023-11-02 | HARRIS | B | 198539.3537 | 137119.9 | -61419.4537 | -31% | 595 | 704 | 194.7726
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026277700 | 558 | EX | RETIRE 2881'-12" BSMP | 2023-11-07 | HARRIS | B | 139.1159 | 430.39 | 291.2741 | 209% |  |  | 0
KY | KY - EAST | 2631 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026278100 | 588 | EX | RETIRE REG FAC | 2023-06-06 | 5726 ROBERTS DR | F | 67.1159 | 0 | -67.1159 | 100% |  |  | 0 | JOB TO EXECUTE PAPERWORK ONLY RWILLIAMS 6-6-2023
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026278700 | 555 | EX | INSTALL 105'-2" PMMP | 2023-06-22 | 120 KELLY LN | A | 17148.7846 | 8200.66 | -8948.1246 | -52% | 107 | 116 | 70.6953 | INSTALLED 116' OF 2" PL MP TESTED 90 PSIG 0005 MIN SOAP TESTED CAPS AND DEA D HEADS OP 17 PSG
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026284800 | 557 | EX | EMER - INSTALL 40'-4" PMLP | 2023-07-21 | 3412 WILLIS ST | A | 16339.4428 | 630.98 | -15708.4628 | -96% | 40 | 34 | 18.5582 | INSTALLED 34' OF 4" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 10" WC
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026284900 | 558 | EX | EMER - RETIRE 40'-4" BSLP | 2023-07-21 | 3412 WILLIS ST | A | 139.1159 | 451.35 | 312.2341 | 224% |  |  | 0 | RETIRED 34' OF 4" BS MAIN DUE TO LEAKAGE SOAP TESTED OP TO VERIFY SHUTDOWN SOAP TESTED OP 10" WC
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026289300 | 557 | EX | INSTALL 7'-2"&6" PMLP | 2023-07-28 | BLACKBURN | B | 141.4953 | 447.65 | 306.1547 | 216% |  | 6 | 74.6083
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026289500 | 596 | EX | RETIRE GROUND BED | 2022-03-11 | US ROUTE 23 | F | 119.4953 | 0 | -119.4953 | 100% |  |  | 0
KY | KY - EAST | 2631 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026290100 | 557 | EX | EMER - 3'-3" PMIP | 2023-08-15 | BERNITA | A | 2929.2518 | 5680.32 | 2751.0682 | 94% | 3 | 3 | 1893.44 | INSTALLED 3' OF 2" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 5 PSIG
KY | KY - EAST | 2631 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026290200 | 558 | EX | EMER-RETIRE 3'-PIP | 2023-08-15 | BERNITA | A | 119.4953 | 253 | 133.5047 | 112% |  |  | 0 | CUT OUT 3' OF 2" PL DUE TO HIT MAIN SOAP TESTED TO VERIFY SHUTDOWN AFTER SQUEEZE OP
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026291700 | 557 | EX | EMER - INSTALL 3'-4" PMIP | 2023-08-31 | 5332 SKYLINE DR | A | 9351.5219 | 2433.5 | -6918.0219 | -74% | 23 | 3 | 811.1667 | INSTALLED 3' OF 4" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7 PSIG
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026291800 | 558 | EX | EMER - RETIRE 3'-4" PIP | 2023-08-31 | 5332 SKYLINE DR | A | 119.4953 | 685.77 | 566.2747 | 474% |  |  | 0 | RETIRED 3' OF 4" PL DUE TO LEAK ON 4" SF COUPLING SOAP TESTED OP 7 PSIG TO VERIFY ADEQUATE SHUTDOWN
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026294200 | 2000 | EX | INVESTIGATE & MAP MAINS/SERV. | 2023-10-25 | POWELL LN |  | 4565 | 0 | -4565 | 100% |  |  | 0 | PS&I CHARGED TO SERVICE LINE THAT WAS RELOCATED FOR SIDEWALK/STORM PROJECT. NO MAIN RELOCATION WAS NECESSARY, BUT SERVICES NEEDED GRADE SET TO CLEAR G RADING AND SEWER WORK. D.LEMONS 10/25/2023
KY | KY - EAST | 2631 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026296600 | 2000 | EX | INVESTIGATE TAP LOCATION | 2023-11-01 |  |  | 1716 | 0 | -1716 | 100% |  |  | 0
KY | KY - EAST | 2631 | U134275 | Weber,Andrew Paul | Parsley,Joe | Webb,Jared | 23026296700 | 555 | EX | INSTALL 165' OF 2" PMIP | 2023-11-16 | 2114 BROOKE CR | A | 23912.4752 | 17527.84 | -6384.6352 | -27% | 165 | 152 | 115.3147 | INSTALLED 157' OF 2" IP MAIN TESTED 90 PSIG 1 HR SOAP TESTED PURGE POINT CAP AND SST CAP OP 7.5 PSIG
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026299800 | 566 | EX | PAPER ONLY SL RETIRE | 2023-06-12 | 2236 MONTGOMERY AV | B | 122.9261 | 0 | -122.9261 | 100% |  |  | 0
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026299900 | 565 | EX | PAPER ONLY SL REPLACEMENT | 2023-06-12 | 2236 MONTGOMERY AV | B | 145.9261 | 1201.76 | 1055.8339 | 724% |  |  | 0
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026300000 | 909 | EX | INSTALL NEW EQUIPMENT | 2023-10-10 | 1403 FRENCH BROAD | F | 3973.8688 | 570.56 | -3403.3088 | -86% |  |  | 0
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026300100 | 2000 | EX | INVESTIGATE R/W LIMITS | 2023-11-15 | RIVERSIDE DR | B | 8037 | 0 | -8037 | 100% |  |  | 0
KY | KY - EAST | 2631 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026307000 | 586 | EX | RETIRE METAL BLDG | 2023-11-26 | 4570 LOUISA RD | F | 124.9261 | 0 | -124.9261 | 100% |  |  | 0 | TWALKER/KY 12-1-23: THIS BUILDING AND REG STATION RETIRED ON 21-0261546-00.
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 17026728201 | 557 | EX | INSTL 3778'-6"&8"PMLP D096801 | 2019-07-27 | 2ND | B | 999130.1284 | 1152970.88 | 153840.7516 | 15% | 3778 | 4081 | 282.5217 | PROJECT OVERRUN OF $153,000 DUE TO UNDERESTIMATING RESTORATION. ADDITIONAL $300,000 IN CONTRACT COSTS PAID, BUT RESTORATION WAS ESTIMATED UNDER MISC MATERIALS WHICH UNDERRAN $190,000. THERE WAS ALSO A INCREASE IN LABOR AND O VERHEADS $59,000. D.LEMONS 6/30/2020
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 17026728300 | 558 | EX | RETIRE 4633' OF CI/BS D096801 | 2019-10-24 | 2ND | B | 71.8476 | 6663.17 | 6591.3224 | 9,174% |  |  | 0
KY | KY - CENTRAL | 2632 | U127466 | Sparks,Cynthia Joy | Miller,Gary | Belle,Eric | 17026734200 | 557 | EX | INSTALL 800' - 2" PMMP MAIN | 2019-02-13 | LIMESTONE TERRACE | B | 147884.7838 | 158951.66 | 11066.8762 | 7% | 800 | 786 | 202.2286
KY | KY - CENTRAL | 2632 | U127466 | Sparks,Cynthia Joy | Miller,Gary | Belle,Eric | 17026734300 | 558 | EX | RETIRE 3,000' - CILP/BSLP/PLP | 2019-05-22 | LIMESTONE TERRACE | B | 257.7357 | 631.49 | 373.7543 | 145% |  |  | 0
KY | KY - CENTRAL | 2632 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 18026757300 | 584 | EX | RETIRE REG STATION WITH AMRP | 2019-05-16 | R11 & LEXINGTON ST EXT | F | 1993.7357 | 452.18 | -1541.5557 | -77% |  |  | 0 | JOB WAS ON HOLD
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026776501 | 557 | EX | INSTALL 12,000' - 2"/4" PMMP | 2020-05-12 | TYLER ST | B | 1751148.4008 | 1871920.67 | 120772.2692 | 7% | 11792 | 12828 | 145.9246 | UNDERRUN EXPLANATION: THE WMS OUT OF TOLERENCE REPORT IS INCORRECT. POWERPL ANT INDICATES $1.77M HAS HIT TO DATE 11/24/2020. THAT IS WITHIN TOLERENCE A ND NO EXPLANATION IS NEEDED AT THIS TIME.
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026776600 | 558 | EX | RETIRE 14800'-2"/4"/6" CI&BSLP | 2020-10-26 | TYLER ST | B | 75.281 | 468.51 | 393.229 | 522% |  |  | 0
KY | KY - CENTRAL | 2632 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 18026781200 | 2000 | EX | INVESTIGATE ROAD ROW | 2020-01-27 | TYLER ST |  | 2599 | 0 | -2599 | 100% |  |  | 0 | PS&I BEING CHARGED TO 557. D.LEMONS 1/27/20
KY | KY - CENTRAL | 2632 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026837200 | 583 | EX | INST. FN 174 EXTRA LP OPP | 2019-07-17 | 2ND ST | F | 21708.8722 | 17414.67 | -4294.2022 | -20% | 50 |  | 0 | INSTALLED NEW MONITOR REG, SET POINTS ON SLAM SHUT 4.5" AND 20 " W.C. MONITOR SET POINT 14"W.C, INLET OUTLET, CONTROL LINES VLVS ON BYPASS OFF. 7-17-19 MMCKUNE REGULATOR INSTALLED BY MIKE MCKUNE ON 7/17/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/17/2021 GCCC TICKET NOT REQUIRED ON 5/17/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2632 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026837300 | 584 | EX | RET. FN 174 FOR EXTRA LP OPP | 2019-07-17 | 2ND ST | F | 54.9718 | 241.46 | 186.4882 | 339% |  |  | 0 | REGULATOR REPLACED BY MIKE MCKUNE ON 7/17/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/17/2021 GCCC TICKET NOT REQUIRED ON 5/17/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2632 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026837600 | 583 | EX | INST. FN 176 EXTRA LP OPP | 2021-05-13 | W 4TH ST | F | 35378.1646 | 59791.79 | 24413.6254 | 69% | 60 |  | 0 | CONTROL SHEET 008281 PAID ON 04/23/20 THURSDAY TO COVER 04/24/20 FRIDAY CONTROL SHEET008307 PAID ON 04/30/20 THURSDAY TO COVER 05/01/20 FRIDAY NOT ON SITE GETTING PARTS FOR JOB CCC# 23134 CCC# 23265 CCC# 23459 CCC# 25857 REGULATORS INSTALLED BY WADE SHIMFESSEL ON 5/13/2021 EC350 INSTALLED BY WADE SHIMFESSEL ON 5/14/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/2021 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS *EXISTING Y STRAINER STRAINER GASKET NOT INSTALLED
KY | KY - CENTRAL | 2632 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026837700 | 584 | EX | RET. FN 176 FOR EXTRA LP OPP | 2021-05-13 | W 4TH ST | F | 53.9767 | 0 | -53.9767 | 100% |  |  | 0 | REGULATORS REPLACED BY WADE SHIMFESSEL ON 5/13/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/2021 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2632 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026837800 | 583 | EX | INST. FN 19809 EXTRA LP OPP | 2019-07-18 | W 2ND ST | F | 21708.8722 | 27342.05 | 5633.1778 | 26% | 50 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 7/18/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/5/2021 GCCC TICKET NOT REQUIRED ON 5/5/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2632 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026837900 | 584 | EX | RET. FN 19809 FOR EXTRA LP OPP | 2019-07-18 | W 2ND ST | F | 54.9718 | 1108.6 | 1053.6282 | 1,917% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 7/18/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/5/2021 GCCC TICKET NOT REQUIRED ON 5/5/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2632 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026838000 | 583 | EX | INST. FN 179 EXTRA LP OPP | 2019-07-19 | BUGLE AL | F | 21708.8722 | 31852.71 | 10143.8378 | 47% | 50 |  | 0 | REGULATOR INSTALLED BY JAMES PASLEY ON 7/19/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/5/2021 GCCC TICKET NOT REQUIRED ON 5/5/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2632 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026838100 | 584 | EX | RET. FN 179 FOR EXTRA LP OPP | 2019-07-19 | BUGLE AL | F | 54.9718 | 302.46 | 247.4882 | 450% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 7/19/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/5/2021 GCCC TICKET NOT REQUIRED ON 5/5/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2632 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026838200 | 583 | EX | INST. FN 228 EXTRA LP OPP | 2020-10-27 | 4TH ST | F | 40147.5762 | 49930.82 | 9783.2438 | 24% | 55 |  | 0 | REGULATORS REPLACED BY RYAN VANDERPOOL ON 10/27/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/28/2021 GCCC TICKET NOT REQUIRED ON 7/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2632 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026838300 | 584 | EX | RET. FN 228 FOR EXTRA LP OPP | 2020-10-27 | 4TH ST | F | 53.9767 | 641.06 | 587.0833 | 1,088% |  |  | 0 | REGULATORS REPLACED BY RYAN VANDERPOOL ON 10/27/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/28/2021 GCCC TICKET NOT REQUIRED ON 7/28/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2632 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026838400 | 583 | EX | INST. FN 257 EXTRA LP OPP | 2020-08-12 | CARNATION STATION-1458 | F | 37874.1646 | 65502.92 | 27628.7554 | 73% | 52 |  | 0 | REGULATORS REPLACED BY JAMES PASLEY ON 8/12/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/27/2021 GCCC TICKET NOT REQUIRED ON 7/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2632 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026838500 | 584 | EX | RET. FN 257 FOR EXTRA LP OPP | 2020-08-12 | CARNATION STATION-1458 | F | 53.6219 | 2790.41 | 2736.7881 | 5,104% |  |  | 0 | REGULATORS REPLACED BY JAMES PASLEY ON 8/12/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/27/2021 GCCC TICKET NOT REQUIRED ON 7/27/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2632 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026839200 | 583 | EX | INST. FN 758 EXTRA LP OPP | 2020-08-14 | REYNOLDS DR | F | 40101.1646 | 65169.83 | 25068.6654 | 63% | 55 |  | 0 | REGULATORS REPLACED BY JAMES PASLEY ON 8/14/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/26/2021 GCCC TICKET NOT REQUIRED ON 7/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2632 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026839300 | 583 | EX | INST. FN 19900 EXTRA LP OPP | 2019-07-15 | MITCHELL AL | F | 21708.8722 | 22176.6 | 467.7278 | 2% | 50 |  | 0 | REGULATOR INSTALLED BY JAMES PASLEY ON 7/15/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/5/2021 GCCC TICKET NOT REQUIRED ON 5/5/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2632 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026839400 | 584 | EX | RET. FN 19900 FOR EXTRA LP OPP | 2019-07-15 | MITCHELL AL | F | 54.9718 | 269.75 | 214.7782 | 391% |  |  | 0 | REGULATOR REPLACED BY JAMES PASLEY ON 7/15/2019 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/5/2021 GCCC TICKET NOT REQUIRED ON 5/5/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2632 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026841500 | 584 | EX | RET. FN 758 FOR EXTRA LP OPP | 2020-08-14 | REYNOLDS DR | F | 53.6219 | 2180 | 2126.3781 | 3,966% |  |  | 0 | REGULATORS REPLACED BY JAMES PASLEY ON 8/14/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/26/2021 GCCC TICKET NOT REQUIRED ON 7/26/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026843000 | 557 | EX | INSTALL 110'-2" PMLP | 2019-01-04 | 5TH | B | 34180.4409 | 78922.81 | 44742.3691 | 131% | 110 | 123 | 641.6489 | OVERRUN EXPLANATION: COMPANY LABOR EXCEEDED THE ESTIMATE BECAUSE THE LEAKAG E HAD TO BE MONITORED UNTIL WE COULD GET A BORING MACHINE UP THERE AND GET THE PIPE REPLACED.
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026843100 | 558 | EX | RETIRE 110'-2" BSLP | 2019-01-04 | 5TH | B | 77.1956 | 0 | -77.1956 | 100% |  |  | 0
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026871400 | 555 | EX | INSTALL 1000'-2" PMIP | 2020-05-06 | 700 BUFFALO TRACE | B | 75531.5699 | 80013.85 | 4482.2801 | 6% | 1000 | 1389 | 57.6054
KY | KY - CENTRAL | 2632 | U131983 |  |  |  | 19026876700 | 557 | EX | INSTALL 3117'-2"PMMP | 2019-11-21 | 5TH ST | B | 359131.1637 | 681450.12 | 322318.9563 | 90% | 3117 | 2827 | 241.0506 | OVERRUN EXPLANATION: IT APPEARS THAT $279,268 IN SERVICE LINE MATERIALS WAS CHARGED TO THIS JOB ORDER INSTEAD OF THE BLANKET SERVICE LINE BUDGET. WE NE ED TO VERIFY.
KY | KY - CENTRAL | 2632 | U131983 |  |  |  | 19026876800 | 558 | EX | RETIRE 4573'- 3&4"BSLP | 2019-12-16 | 5TH | B | 79.3553 | 0 | -79.3553 | 100% |  |  | 0
KY | KY - CENTRAL | 2632 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026895200 | 558 | EX | RETIRE 2104' 2" P/BSLP | 2021-01-27 | ROGERS | B | 103.581 | 100.78 | -2.801 | -3% |  |  | 0
KY | KY - CENTRAL | 2632 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026895301 | 557 | EX | INSTALL 6060' 2" PMMP | 2021-01-20 | DRYDEN | B | 549218.5288 | 815947.98 | 266729.4512 | 49% | 6080 | 6914 | 118.0139 | JOB ORDER CODED COMPLETE IN ERROR. WILL BE CARRY OVER INTO 2021. SPENDLE OVERRUN EXPLANATION: ADDITIONAL PIPE WAS ADDED LATE INTO PROJECT AND ADDITI ONAL LABOR HOURS CAUSED INCREASE IN SEGA AS WELL AS LATE PAVING COSTS THAT HIT THE PROJECT SBRADY 6/18/21
KY | KY - CENTRAL | 2632 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026895400 | 558 | EX | RETIRE 5072' 2-4" IP | 2021-01-27 | DRYDEN | B | 103.581 | 0 | -103.581 | 100% |  |  | 0
KY | KY - CENTRAL | 2632 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026895600 | 558 | EX | RETIRE 1516' 2" BS/P/WILP | 2021-01-27 | GERMANTOWN | B | 103.581 | 108.73 | 5.149 | 5% |  |  | 0
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026897100 | 565 | EX | INSTALL 4" SERVICE | 2019-10-17 | 31 E 2ND ST REAR | B | 9612.2483 | 8763.34 | -848.9083 | -9% | 30 |  | 0
KY | KY - CENTRAL | 2632 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026897200 | 557 | EX | INSTALL 2" SS FITTING | 2019-10-03 | 710 KATHY LEE CR | A | 6488.17 | 4876.06 | -1612.11 | -25% |  |  | 0
KY | KY - CENTRAL | 2632 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026897300 | 558 | EX | RETIRE 1' OF 2"CSMP MAIN | 2019-10-03 | 710 KATHY LEE CI | A | 67.2897 | 729.47 | 662.1803 | 984% |  |  | 0
KY | KY - CENTRAL | 2632 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026897400 | 2000 | EX | INVESTIGATE LAND RIGHTS | 2020-08-14 | GERMANTOWN RD |  | 1641 | 0 | -1641 | 100% |  |  | 0
KY | KY - CENTRAL | 2632 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026900900 | 584 | EX | RETIRE MP TO IP RUN S-1455 | 2021-01-27 | W 2ND ST | F | 690.3419 | 152.33 | -538.0119 | -78% |  |  | 0 | MP TO IP RUN RETIRE ON 1/27/21 BY RYAN VANDERPOOL PAPERWORK DID NOT GET TURNED IN FOR COMPLETION STATION RETIREMENT FIELD VERIFIED ALONG WITH RETIREMENT DATE FROM THE STATION INSPECTION RECORD BY WADE SHIMFESSEL AND JOSH MARTIN ON 10/18/2021 RETIREMENT PAPERWORK COMPLETED BY CYNTHIA FARIS ON 10/25/2021 GCCC TICKET NOT REQUIRED ON 10/25/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK. SETTING BYPASS VALVE AND INLET SETTING VALVE NOT RETIRED THEY ARE TURNED OFF AND BLIND FLANGED CFARIS
KY | KY - CENTRAL | 2632 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026901000 | 584 | EX | RETIRE STATION 1464 | 2021-01-11 | KY 8 ON PRIVATE R/W | F | 690.3419 | 2654.56 | 1964.2181 | 285% |  |  | 0 | JOB CARRIED OVER UNTIL AFTER THE 1ST OF 2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/16/2021 GCCC TICKET NOT REQUIRED ON 2/16/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK 2/16/21 CFARIS
KY | KY - CENTRAL | 2632 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026901100 | 584 | EX | RETIRE STATION 1481 | 2021-01-11 | GERMANTOWN RD | F | 690.3419 | 2483.61 | 1793.2681 | 260% |  |  | 0 | JOB ON HOLD UNTIL AFTER THE 1ST OF 2021
KY | KY - CENTRAL | 2632 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026901200 | 584 | EX | RETIRE STATION 1480 | 2021-01-11 | KY435 | F | 690.3419 | 4464.65 | 3774.3081 | 547% |  |  | 0 | JOB WAS ON HOLD UNTIL AFTER THE 1ST OF 2021
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026908000 | 2000 | EX | OBTAIN ADD LAND RIGHTS 4 I&C | 2023-01-06 | MAPLE LEAF RD |  | 5472 | 0 | -5472 | 100% |  |  | 0 | DISCOVERED BUILDING WAS INSTALLED ON 909 JO, SO PS&I WAS EXECUTED TO IT. D. LEMONS 1/6/2023
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026909700 | 566 | EX | RETIRE 4" SERVICE | 2019-08-08 | 48 E 2ND ST | B | 75.281 | 0 | -75.281 | 100% |  |  | 0
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026909800 | 565 | EX | INSTALL 4" SERVICE | 2019-08-08 | 48 E 2ND ST | B | 5664.2199 | 66.44 | -5597.7799 | -99% |  |  | 0
KY | KY - CENTRAL | 2632 | U130604 | Brady,Shannon | McCuen,Matt | Lowder,Jeb | 19026910400 | 575 | EX | MAYSVILLE LP AMRP EASEMENTS | 2021-02-09 | 6500 GERMANTOWN RD | F | 14458 | 19743.69 | 5285.69 | 37% |  |  | 0
KY | KY - CENTRAL | 2632 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026911600 | 595R | EX | INSTALL NEW RECTIFIER | 2021-02-18 | STATE ROUTE 10 | A | 10181.0696 | 5775.31 | -4405.7596 | -43% |  |  | 0
KY | KY - CENTRAL | 2632 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026911700 | 596 | EX | RETIRE RECTIFIER | 2021-02-18 | ST. RT. 10 | F | 69.2529 | 0 | -69.2529 | 100% |  |  | 0
KY | KY - CENTRAL | 2632 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026912100 | 595R | EX | INSTALL NEW RECTIFIER | 2020-12-28 | ROGERS (FERNLEAF) AV | A | 10181.0696 | 6662.91 | -3518.1596 | -35% |  |  | 0
KY | KY - CENTRAL | 2632 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026912200 | 596 | EX | RETIRE RECTIFIER | 2020-12-28 | ROGERS AV | F | 69.2529 | 0 | -69.2529 | 100% |  |  | 0
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026913600 | 584 | EX | RETIRE LP STATION R-1476 | 2020-10-22 | E 5TH ST MAY | F | 1187.4398 | 12934.25 | 11746.8102 | 989% |  |  | 0 | TIME CHARGED TO MONITORING JOB 20-8544267-00 RATHER THAN THE 584 JOB TO RETIRE THE STATION
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026913700 | 560 | EX | RETIRE 70'-2" CSMP | 2020-10-27 | E 5TH ST | B | 10996.4398 | 6716.3 | -4280.1398 | -39% |  |  | 0
KY | KY - CENTRAL | 2632 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 20026917000 | 2000 | EX | RESEARCH PROPERTY RIGHTS | 2022-12-16 | MAPLE LEAF RD |  | 3967 | 0 | -3967 | 100% |  |  | 0
KY | KY - CENTRAL | 2632 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 20026918301 | 909 | EX | INSTALL ELECTRONICS | 2021-12-22 | MAPLE LEAF RD | F | 179105.9064 | 163427.04 | -15678.8664 | -9% |  |  | 0 | GCC# 13951 CCC TICKET #14135 TICKET# 15597 CCC# 49425 REPLACED PUCK IN TRANSMITTER W/NOLL COMPLETED PAPERWORK 12-22-21 JMARTIN
KY | KY - CENTRAL | 2632 | U131983 |  |  |  | 20026931000 | 587 | EX | UPGRADE ELECTRONICS | 2020-05-06 | 9127 MASON LEWIS RD | F | 3150 | 468.63 | -2681.37 | -85% |  |  | 0 | UPGRADED 2G/3G MODEM TO RV50 4G/5G CELL MODEM EQUIPMENT INSTALLED BY ACP
KY | KY - CENTRAL | 2632 | U131983 |  |  |  | 20026931100 | 587 | EX | UPGRADE ELECTRONICS | 2021-10-27 | 207 MAIN ST | F | 3038 | 265.67 | -2772.33 | -91% |  |  | 0 | REPLACED EFC
KY | KY - CENTRAL | 2632 | U131983 |  |  |  | 20026938100 | 588 | EX | RETIRE ELECTRONICS | 2021-10-27 | 207 MAIN ST | F | 73.3494 | 0 | -73.3494 | 100% |  |  | 0 | REPLACED EFC
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026942500 | 909 | EX | INSTALL I&C EQUIPMENT | 2021-12-22 | MASON LEWIS RD | F | 16155.4774 | 8341.61 | -7813.8674 | -48% |  |  | 0 | ERX INSTALLED BY ACP AND WADE SHIMFESSEL PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/10/22
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026942600 | 584 | EX | RETIRE GAUGE | 2021-12-22 | MASON LEWIS RD | F | 91.4991 | 0 | -91.4991 | 100% |  |  | 0 | GAUGE RETIRED AFTER ERX INSTALLED BY WADE SHIMFESSEL PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/10/2022
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026942900 | 909 | EX | INSTALL I&C EQUIPMENT | 2022-01-03 | PRV R/W TCO LOT | F | 16155.4774 | 11090.78 | -5064.6974 | -31% |  |  | 0 | ERX INSTALLED BY ACP AND WADE SHIMFESSEL PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/10/22
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026943000 | 584 | EX | RETIRE GAUGE | 2022-01-03 | PRV R/W TCO LOT | F | 91.4991 | 1496.7 | 1405.2009 | 1,536% |  |  | 0 | CCC# 49347 COMMISION ERX CCC# 50118 ERX INSTALLED AND GAUGE RETIRED BY WADE SHIMFESSEL PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/10/22
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026950100 | 2000 | EX | RESEARCH LAND RIGHTS | 2023-02-08 | US68 |  | 15740 | 0 | -15740 | 100% |  |  | 0
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026950500 | 575 | EX | ACQUIRE LAND FOR STATION | 2023-02-08 | US68 | F | 15620 | 13667.26 | -1952.74 | -13% |  |  | 0
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026956500 | 557 | EX | INSTALL 5'-4" PMMP | 2020-06-17 | COMMERCE ST | A | 4635.7623 | 15511.9 | 10876.1377 | 235% | 5 | 4 | 3877.975 | ABN 4 FEET OF 4" PL GM AFTER FACDAM - INSTALLED 4 FEET OF 4" PL TESTED PIPE ON SITE 90 PSI FOR 20 MINS - TESTED OK - SOAP TESTED 2 E/F CPLGS @ OP CGI BANKS FOR SECONDARY DAMAGE OK - SDADAMS 06-17-20 0030 CO OFF SITE
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026956600 | 558 | EX | RETIRE 5'-4" PMMP | 2020-06-17 | COMMERCE ST | A | 86.6677 | 44.03 | -42.6377 | -49% |  |  | 0 | ABN 4 FEET OF 4" PL GM AFTER FACDAM - INSTALLED 4 FEET OF 4" PL TESTED PIPE ON SITE 90 PSI FOR 20 MINS - TESTED OK - SOAP TESTED 2 E/F CPLGS @ OP CGI BANKS FOR SECONDARY DAMAGE OK - SDADAMS 06-17-20 0030 CO OFF SITE
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026961300 | 557 | EX | INSTALL 10'-6" PMMP | 2020-09-22 | E 2ND MP ST | A | 13678.3374 | 7217.5 | -6460.8374 | -47% | 10 | 10 | 721.75
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026961400 | 558 | EX | RETIRE 10'-6" PMMP | 2020-09-22 | E 2ND MP ST | A | 83.7517 | 241.23 | 157.4783 | 188% |  |  | 0
KY | KY - CENTRAL | 2632 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 20026962200 | 2000 | EX | RESEARCH LAND RIGHT/ ROW | 2022-12-16 | CROSS COUNTRY | A | 18194 | 0 | -18194 | 100% |  |  | 0
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026973001 | 557 | EX | INSTALL 10,000--2" PMMP | 2021-11-17 | CLARK | B | 2332285.9866 | 2896168.82 | 563882.8334 | 24% | 10649 | 10954 | 264.3937 | COST OVERRUN OF $378K DUE TO PROJECT SHUT DOWN AND RESTART OVER WINTER. PR OJECT REQUIRED ADDITIONAL RESOURCES THAT WERE NOT ESTIMATED. COST OVERUN O F $345K IN MATERIALS (PAVING), $124K IN CONTRACT AND $21K IN LABOR. THERE W AS A SAVINGS OF $213K IN OTHER DUE TO ORIGINAL PAVING ESTIMATE BEING CAPTUR ED THERE. THESE ADDITIONAL COSTS CAUSED INCREASE IN SEGA OF $97K. D.LEMONS 10/26/2022
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026973100 | 558 | EX | RETIRE 120'-4" BSMP | 2022-06-09 | CLARK | B | 80.6441 | 1897.5 | 1816.8559 | 2,253% |  |  | 0
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026973200 | 558 | EX | RETIRE 10875' BS/CI LP | 2022-06-09 | FOREST | B | 57.6441 | 142.7 | 85.0559 | 148% |  |  | 0
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026973300 | 2000 | EX | INVESTIGATE AEASEMENTS | 2021-06-26 |  |  | 13472 | 0 | -13472 | 100% |  |  | 0
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026973400 | 584 | EX | RETIRE STATION R-1452 | 2022-06-08 | REYNOLDS DR | F | 1281.7771 | 114.18 | -1167.5971 | -91% |  |  | 0 | CCC# 68859 CCC# 68859 RETIRED REGSTATION PER AMRP PROJECT JMARTIN
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026973500 | 584 | EX | RETIRE STATION R-1458 | 2022-05-26 | CARNATION STATION-1458 | F | 1281.7771 | 1295 | 13.2229 | 1% |  |  | 0
KY | KY - CENTRAL | 2632 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 20026973600 | 2000 | EX | OBTAIN CSX VAL MAPS | 2022-11-03 | MAPLE PARKWAY | B | 4000 | 0 | -4000 | 100% |  |  | 0
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026973700 | 557 | EX | INSTALL 6150'-4" PMLP | 2021-09-18 | 4TH | B | 2202632.8927 | 2832541.47 | 629908.5773 | 29% | 5671 | 6687 | 423.5893 | ODOR READS TOOK AT 128 E 3RD ST, MAYSVILLE,KY - WITH SN-16040105 12/17- .6@10:40 - 12/18 .5@16:30 - 12/19 .6@11:30 - 12/20 .5@ 16:29 - 12/21 .5@17:12 - 12/22 .5@16:45 - 12/23 .6@12:27 - TJETT 12/23/21 LEVEL 2 BUDGET VARIANCE COMPLETED AND FILED IN WMSDOCS. D.LEMONS 10/3/2022
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026973800 | 558 | EX | RETIRE 6801'-4' CILP | 2022-04-22 | 4TH | B | 107.2796 | 1501.61 | 1394.3304 | 1,300% |  |  | 0
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026974100 | 558 | EX | RETIRE 385'- 3" & 4" | 2022-04-22 | 4TH | B | 8962.6172 | 2639.76 | -6322.8572 | -71% |  |  | 0
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026975000 | 555 | EX | INSTALL 150'-2" PMIP | 2021-02-08 | 2223 MEADOW RIDGE DR | A | 12346.2686 | 12825.26 | 478.9914 | 4% | 150 | 244 | 52.5625
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026975100 | 558 | EX | RETIRE 30'-2" PMLP | 2020-09-17 | LOWER W FORTH ST | A | 2035.7071 | 1842.29 | -193.4171 | -10% |  |  | 0
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026980800 | 555 | EX | INSTALL 50'-2" PMMP | 2020-10-22 | 343 E 2ND ST | A | 13229.5604 | 5887.25 | -7342.3104 | -55% | 50 | 48 | 122.651
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026982100 | 555 | EX | INSTALL 800'-2" PMIP | 2022-10-17 | 725 CLARKS RUN RD MIDDLE | B | 47914.5682 | 69244.93 | 21330.3618 | 45% | 800 | 892 | 77.6288
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026992100 | 584 | EX | RETIRE STATION | 2022-04-21 | BUGLE AL | F | 3400.2343 | 0 | -3400.2343 | 100% |  |  | 0 | RETIRED REGULATOR STATION JMARTIN
KY | KY - CENTRAL | 2632 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 21026111600 | 577 | EX | INSTALL FENCE | 2022-10-13 | MAPLE LEAF RD | F | 2231 | 21225.79 | 18994.79 | 851% |  |  | 0 | CCC# 79626 MONITOR FOR FENCE INSTALL. JMARTIN 9-2-22 CCC# 79759 MONITOR FOR FENCE INSTALL
KY | KY - CENTRAL | 2632 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026118000 | 559 | EX | INSTALL 4" SS | 2021-05-13 | W 4TH ST | B | 29193.606 | 13617.82 | -15575.786 | -53% |  |  | 0 | 4"SHORTSTOP INSTALLET BY RLA TESTED AND TAPPED BYCOMPANY 90 PSIG 15 MIN TEST NITROGN AS MEDIUM
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026127000 | 557 | EX | INSTALL 8021'-2"&4" PMIP | 2023-03-16 | CIRCLE | B | 1234240.1163 | 2281682.81 | 1047442.6937 | 85% | 8021 | 8100 | 281.6892
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026127100 | 558 | EX | RETIRE 9400'-2"&4" BS&CS | 2023-06-07 | CIRCLE | B | 67.799 | 1334.61 | 1266.811 | 1,868% |  |  | 0
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026127200 | 557 | EX | INSTALL 2200'-2"&4" PMMP | 2022-08-25 | LEXINGTON | B | 433097.159 | 570820.34 | 137723.181 | 32% | 2211 | 1678 | 340.179 | COST OVERRUN DUE TO PAVING ESTIMATED IN CONTRACT, BUT CAPTURED IN MISC MATE RIALS WITH A DIFFERENCE OF $32,000. SOME ADDITIOANL MATERIALS WERE REQUIRE D THAT WERE NOT ESTIMATED FOR $6,000. SEGA ALSO INCREASED FOR ADDITIONAL $1 8,000. D.LEMONS 1/31/2023 ADDITIONAL $56,000 TRANSFERED FROM RETIREMENT JO THAT WAS ASSOCIATED WITH A DDITIONAL PAVING. D. LEMONS 2/23/2023
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026127300 | 558 | EX | RETIRE 2100'-2"&4" BSMP | 2022-10-06 |  | B | 75.9523 | 0 | -75.9523 | 100% |  |  | 0
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026127400 | 557 | EX | INSTALL 1900'-2"&4" PMIP | 2022-09-22 |  | B | 236888.6644 | 479284.77 | 242396.1056 | 102% | 1901 | 1978 | 242.3078 | OVERRUN EXPLANATION LOADED INTO WMSDOCS. D.LEMONS 2/1/2023
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026127500 | 558 | EX | RETIRE 1071'-3"&4" WIIP | 2022-09-22 |  | B | 75.9523 | 0 | -75.9523 | 100% |  |  | 0
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026127600 | 558 | EX | RETIRE 4700'-4" BSLP | 2022-10-06 |  | B | 67.1085 | 0 | -67.1085 | 100% |  |  | 0
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026134500 | 561 | EX | INSTALL 1537'-2"PMIP | 2022-05-02 | KENNEDY CREEK RD | B | 208782.1462 | 332303.55 | 123521.4038 | 59% | 1539 | 1562 | 212.7423 | SEE PROJECT WORKSPACE 21-81540 FOR PROJECT OVERRUN EXPLANATION. D.LEMONS 10 /26/2022
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026134600 | 562 | EX | RETIRE 1053'-2" CSIP | 2022-05-09 | KENNEDY CREEK RD | B | 109.7476 | 0 | -109.7476 | 100% |  |  | 0
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026134700 | 2000 | EX | INVESTIGATE MAINS | 2022-03-24 | KENNEDY CREEK RD |  | 21179 | 0 | -21179 | 100% |  |  | 0 | CORP PERMIT RECIEVED ALONG WITH EASEMENTS PER CHRIS DAVIS. D. LEMONS 3/24/2 022
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026138600 | 2000 | EX | INVESTIGATE EASEMENT | 2022-02-24 | LEXINGTON PK | B | 26241 | 0 | -26241 | 100% |  |  | 0 | CCC# 53392 MEET WITH ATLAS ONSITE AT STATION FOR BUILDING SAMPLES
KY | KY - CENTRAL | 2632 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 21026139000 | 2000 | EX | DESIGN COSTS | 2022-09-21 | KY 546 |  | 20000 | 0 | -20000 | 100% |  |  | 0
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026139300 | 584 | EX | RETIRE STATION R-1455 | 2022-10-04 | W 2ND ST | F | 1061.1136 | 0 | -1061.1136 | 100% |  |  | 0 | RETIRED REG STATION R1455 W 2ND ST MAYSVILLE JMARTIN 10-4-22
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026139400 | 586 | EX | REMOVE BUILDING FOR R-1455 | 2023-01-18 | W 2ND ST | F | 117.5985 | 3989.86 | 3872.2615 | 3,293% |  |  | 0 | BUILDING REMOVED AND CLEANED UP BY PLANT. JMULLINS 1-18-23
KY | KY - CENTRAL | 2632 | U938437 |  |  |  | 21026145800 | 583 | EX | REPLACE VALVES ON HP-MP REG | 2022-07-20 | KY 546 | F | 14136.4861 | 33552.7 | 19416.2139 | 137% | 19 |  | 0 | CCC# 73837 CCC# 74028 CCC# 74317 REPLACED INLET, OUTLET, AND BOTH BYPASS VLVS ON STATION. JMARTIN 7/20/22
KY | KY - CENTRAL | 2632 | U938437 |  |  |  | 21026145900 | 584 | EX | RETIRE 4 VALVES ON REG STATION | 2022-07-20 | KY 546 | F | 600.4497 | 1355.49 | 755.0403 | 126% |  |  | 0 | INSTALLED TEMPORARY REG SETTING REPLACED ALL FOUR SETTING VALVES JMARTIN 07 -20-2022
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026154100 | 2000 | EX | OBTAIN EASEMENT | 2022-10-24 | CLARKS RUN RD | B | 7970 | 0 | -7970 | 100% |  |  | 0 | EASEMENT OBTAINED FOR NEW MAIN INSTALATION AND STAKED. D.LEMONS 10/24/2022
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026994200 | 566 | EX | RETIRE 3" SERVICE | 2022-04-21 | 322 LIMESTONE ST | B | 98.6196 | 0 | -98.6196 | 100% |  |  | 0
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026159400 | 566 | EX | RETIRE S/L | 2022-03-21 | 636 FOREST AV | A | 3024.4273 | 2030.55 | -993.8773 | -33% |  |  | 0
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026162700 | 575 | EX | OBTAIN EASEMENT | 2022-03-24 | KY HWY 10 | F | 3693.7476 | 3309.48 | -384.2676 | -10% |  |  | 0 | COPR PERMIT AND EASEMENT OBTAINED PER CHRIS DAVIS. D. LEMONS 3/24/2022
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026165100 | 555 | EX | INSTALL 300'-2" PMIP | 2022-05-18 | 1079 SMITH TERRACE | A | 29167.1057 | 34102.05 | 4934.9443 | 17% | 300 | 250 | 136.4082
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026171800 | 557 | EX | INSTALL 3178'-2" PMIP | 2023-06-13 | 4TH | B | 663052.9501 | 806129.21 | 143076.2599 | 22% | 3228 | 2949 | 273.3568
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026171900 | 558 | EX | RETIRE ~3325'-2" BS,CS & P | 2023-07-14 | 4TH | B | 83.4538 | 0 | -83.4538 | 100% |  |  | 0
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026172700 | 2000 | EX | INVESTIGATE EASEMENTS & R/W | 2020-12-30 |  |  | 9058 | 0 | -9058 | 100% |  |  | 0
KY | KY - CENTRAL | 2632 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026185400 | 909 | EX | EXCHANGE ELECTRONIC COMPONENTS | 2022-05-17 | ROUTE 10 | F | 5480.5156 | 1456 | -4024.5156 | -73% |  |  | 0 | JMARTIN REMOVED OLD ERX AND INSTALLED NEW MIWI 350 5-17-2022
KY | KY - CENTRAL | 2632 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026185500 | 910 | EX | RETIRE COMPONENTS | 2022-05-17 | ROUTE 10 | F | 124.5156 | 715.54 | 591.0244 | 475% |  |  | 0 | CCC# 67011 NOT ABLE TO COMP AT THIS TIME, HAS OLDER ERX AND NEED MORE PARTS. JMARTIN 5-16-22 CCC# 67183 REPLACE ERX WITH NEW MIWI 350. JMARTIN
KY | KY - CENTRAL | 2632 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026185600 | 909 | EX | EXCHANGE ELECTRONIC COMPONENTS | 2022-06-20 | US68 | F | 6006.2549 | 644.24 | -5362.0149 | -89% |  |  | 0 | CCC# 70942 INSTALL NEW MIWI 350, P2P W/GAS CONTROL OK, JMARTIN 6-20-22
KY | KY - CENTRAL | 2632 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026185700 | 910 | EX | RETIRE ELECTRONIC COMPONENTS | 2022-06-20 | US68 | F | 124.5156 | 93.74 | -30.7756 | -25% |  |  | 0 | CCC# 70942 RETIRE ERX AND REPLACE WITH MIWI 350, JMARTIN 6-20-22
KY | KY - CENTRAL | 2632 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026187000 | 909 | EX | EXCHANGE ELECTRONIC COMPONENTS | 2022-05-18 | 4TH ST | F | 4357.5409 | 1100.73 | -3256.8109 | -75% |  |  | 0 | CCC# 67356 REPLACE ERX WITH NEW MIWI 350, P2P OK, JMARTIN CCC# 67669 WORKED TO FIX COMM ISSUE WITH MIWI. CCC# 67669
KY | KY - CENTRAL | 2632 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026187100 | 910 | EX | RETIRE ELECTRONIC COMPONENTS | 2022-05-18 | 4TH ST | F | 124.5156 | 0 | -124.5156 | 100% |  |  | 0 | RETIRED OLD ERX JMARTIN 5/18/2022
KY | KY - CENTRAL | 2632 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026187400 | 909 | EX | EXCHANGE ELECTRONIC COMPONENTS | 2022-05-20 | KY10 | F | 4773.0565 | 1016.56 | -3756.4965 | -79% |  |  | 0 | CCC# 67055 INSTALL NEW MIWI 350, P2P OK, JMARTIN CCC# 67183
KY | KY - CENTRAL | 2632 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026187500 | 910 | EX | RETIRE ELECTRONIC COMPONENTS | 2022-05-20 | KY10 | F | 124.5156 | 0 | -124.5156 | 100% |  |  | 0
KY | KY - CENTRAL | 2632 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026187600 | 909 | EX | REPLACE ELECTRONIC COMPONENTS | 2022-05-16 | 1241 WALTON PK | F | 5349.5438 | 31245.53 | 25895.9862 | 484% |  |  | 0 | CCC# 67613 REPLACED ERX WITH NEW MIWI 350. P2P OK, JMARTIN CCC# 67613
KY | KY - CENTRAL | 2632 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026187700 | 910 | EX | RETIRE ELECTRONIC COMPONENTS | 2022-05-16 | 1241 WALTON PK | F | 124.5156 | 39.46 | -85.0556 | -68% |  |  | 0 | CCC# 67613 RETIRE ERX JMARTIN
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026195800 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-08-30 | KY 546 | F | 4801.1928 | 5580.46 | 779.2672 | 16% |  |  | 0 | CCC# 79192 INSTALL NEW MIWI 350, P2P COMP. JMARTIN 8-30-22
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026195900 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-08-30 | KY 546 | F | 124.8731 | 69.23 | -55.6431 | -45% |  |  | 0 | CCC# 79192 INSTALL NEW MIWI 350, P2P COMP. JMARTIN 8-30-22 RETIRED OLD ERX
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026204100 | 586 | EX | RETIRE BUILDING | 2023-01-31 | CARNATION STATION-1458 | F | 76.9137 | 0 | -76.9137 | 100% |  |  | 0 | BUILDING DEMOLISHED BY CONTRACTORS
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026204400 | 586 | EX | RETIRE BUILDING | 2023-01-31 | REYNOLDS DR | F | 76.9137 | 0 | -76.9137 | 100% |  |  | 0 | BUILDING DEMOLISHED BY CONTRACTOR
KY | KY - CENTRAL | 2632 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026205000 | 910 | EX | RETIRE ERX | 2021-12-22 | MAPLE LEAF RD | F | 78.4365 | 0 | -78.4365 | 100% |  |  | 0 | COMPLETED PAPERWORK 12-22-21 JMARTIN
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026206200 | 557 | EX | INSTALL 33'-2" PMIP | 2022-10-06 | RT 62 | B | 82983.2827 | 37112.14 | -45871.1427 | -55% | 41 | 19 | 1953.2705 | COST UNDERRUN DUE TO PROJECT BEING SIMPLIFIED AFTER START OF CONSTRUCTION. $2000 IN MATERIALS RETURNED AND NOT USED, $26000 IN CONTRACT ESTIMATED BUT NOT USED. ADDITIONAL SAVINGS IN OTHER AND SEGA CATAGORIA ASSOCIATED WITH LO WER COSTS. D. LEMONS 2/23/2023
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026206300 | 558 | EX | RETIRE 22'-4" WIIP | 2022-10-06 | RT 62 | B | 83.4538 | 3252.3 | 3168.8462 | 3,797% |  |  | 0
KY | KY - CENTRAL | 2632 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026208800 | 2000 | EX | GERMANTOWN-INV EASEMENTS | 2023-08-09 | 1241 WALTON PK |  | 5000 | 620.43 | -4379.57 | -88% |  |  | 0
KY | KY - CENTRAL | 2632 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026209201 | 586 | EX | RETIRE BUILDING FOR R-1451 | 2023-03-16 | BUGLE AL | F | 4594.5704 | 3422.43 | -1172.1404 | -26% |  |  | 0
KY | KY - CENTRAL | 2632 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026222500 | 557 | EX | EMER - INSTALL 5'-6" PMMP | 2022-09-02 | 206 E 3RD ST | A | 5662.1316 | 5673.45 | 11.3184 | 0% | 3 | 3 | 1891.15
KY | KY - CENTRAL | 2632 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026222600 | 558 | EX | EMER - RETIRE 5'-6" PMMP | 2022-09-02 | 206 E 3RD ST | A | 74.3089 | 0 | -74.3089 | 100% |  |  | 0
KY | KY - CENTRAL | 2632 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026254100 | 584 | EX | RETIRE PRESSURE GAUGE | 2023-02-03 | US 68 | F | 552.5683 | 72.46 | -480.1083 | -87% |  |  | 0 | CCC# 10600 RETIRED PRESSURE CHART. JMARTIN 2-3-23
KY | KY - CENTRAL | 2632 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026256800 | 584 | EX | RETIRE PAPER GAUGE | 2023-03-01 | S HILL CITY RD | F | 138.8485 | 43.28 | -95.5685 | -69% |  |  | 0 | CCC# 10600 RETIRE PRESSURE CHART, JMARTIN 3-1-23
KY | KY - CENTRAL | 2632 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 23026257900 | 909 | EX | INSTALL MIWI AND SUPER SOLAR | 2023-07-05 | MAPLE DR | F | 22482.2854 | 1323.01 | -21159.2754 | -94% |  |  | 0 | CCC# 36022 INSTALL NEW MIWI 350. JMARTIN JHOBBS 7-5-23 CCC#36022
KY | KY - CENTRAL | 2632 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 23026258000 | 584 | EX | RETIRE PAPER CHART | 2023-07-05 | MAPLE DR | F | 121.7239 | 555.95 | 434.2261 | 357% |  |  | 0 | CCC# 36022 RETIRED PAPER CHART. JMARTIN JHOBBS 7-5-23 CCC# 36022
KY | KY - CENTRAL | 2632 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026302500 | 584 | EX | RETIRE PAPER GAUGE | 2023-11-02 | 3020 HIGHLAND DR | F | 989.8688 | 994.29 | 4.4212 | 0% |  |  | 0 | CCC# 50771 MONITOR FOR TC
KY | KY - EAST | 2633 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 17026723100 | 583 | EX | INSTALL TEMP REG STATION | 2019-06-20 | SR899 1429 | F | 3792.9756 | 16495.12 | 12702.1444 | 335% |  |  | 0 | INSTALLED TEMP MOONEY SKID GURU ADDED 4 - 2"BV, 1 - 2"PV, MISSED ON ORIGINAL JOB. SM 3/15/24
KY | KY - EAST | 2633 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 17026723200 | 584 | EX | RETIRE REG STATION | 2019-06-20 | SR899 1429 | F | 53.4103 | 0 | -53.4103 | 100% |  |  | 0
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026744500 | 583 | EX | INSTALL TOP WORKS R-1442 | 2020-09-19 | MIDDLE FORK RD. | F | 11143.9613 | 16656.18 | 5512.2187 | 49% | 120 |  | 0 | GCCC TICKET NOT REQUIRED NOT AT STATION OFF SITE WORKING ON PAPERWORK 2/26/21 CFARIS NO CCC TICKET-NOT ON SITE CHARGED TO JOB FOR PAPERWOKR NOT ONSITE --SIGNING CAPITALJOB PAPER WORK PER CYNTHIA MCR JOB COMPLETION DELAYED WAITING ON INFORMATION AND ISO SKETCHES JOB COMPLETED BY MATTHEW RYAN 9/19/2020
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026744600 | 584 | EX | RETIRE TOP WORKS | 2020-09-19 | MIDDLE FORK RD. | F | 59.2873 | 2429.38 | 2370.0927 | 3,998% |  |  | 0 | WORK COMPLETED BY MATT RYAN ON 9/19/20 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 12/10/21
KY | KY - EAST | 2633 | U131042 | Bowlin,John Christopher | Tipton,James | Murray,Jennifer | 18026751600 | 2000 | EX | INVEST RECTIFIER SITE & EASE | 2021-11-18 | US 23 & 960 | B | 5000 | 0 | -5000 | 100% |  |  | 0
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026761400 | 909 | EX | INSTALL BULLHORN RMU | 2021-09-30 | 98 OLD JOHNS CREEK RD | F | 3922.4303 | 2699.78 | -1222.6503 | -31% |  |  | 0 | RMU WAS INSTALLED ON 09/30/2021 BY TIM SWARTS. SYSTEM SERIAL # IS 132395. -OSS
KY | KY - EAST | 2633 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 18026763900 | 2000 | EX | ACQUIRE LAND RIGHTS | 2022-11-03 | DUDLEY DR | B | 4572 | 0 | -4572 | 100% |  |  | 0
KY | KY - EAST | 2633 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 18026764000 | 2000 | EX | ACQUIRE LAND RIGHTS | 2022-11-03 | US23 UPPER HAROLD 1419 | B | 4572 | 0 | -4572 | 100% |  |  | 0
KY | KY - EAST | 2633 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 18026764100 | 2000 | EX | ACQUIRE LAND RIGHTS | 2022-11-03 | LOWER HAROLD 1418 | B | 4572 | 0 | -4572 | 100% |  |  | 0
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026768600 | 557 | EX | INSTALL 1402'-2"&4" PMIP | 2019-05-06 | KY RT 1428 | B | 105475.5706 | 190345.26 | 84869.6894 | 80% | 1402 | 1493 | 127.4918 | OVERRUN EXPLANATION: 580 HOURS OF FLAGGING WERE REQUIRED OVER WHAT WAS ESTI MATED AND 52 DAYS OF PER DIEM. IN ADDITION, 1166 UNITS OF EXTRA DEPTH AND 591 UNITS OF COLD PATCH WERE NOT ESTIMATED ALL OF WHCIH CONTRIBUTED TO THE OVERRUN. LEVEL 2 VARIANCE ENTERED IN WMSDOCS.
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026768700 | 558 | EX | RETIRE 2604' BSIP | 2019-07-01 | KY RT 1428 | B | 73.6972 | 0 | -73.6972 | 100% |  |  | 0
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026770100 | 588 | EX | RETIRE CHART | 2022-07-07 | 200 PURPOSE RD | F | 1613.3811 | 0 | -1613.3811 | 100% |  |  | 0 | RETIRED PAPER CHART MRYAN 07-07-2022
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026770200 | 588 | EX | RETIRE GUAGE | 2020-12-23 | 572 HIGHWAY 899 R | F | 1613.3811 | 2481.33 | 867.9489 | 54% |  |  | 0 | CONVERTED TO CAB ACCOUNT ON 12/23/20
KY | KY - EAST | 2633 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026839500 | 583 | EX | INST. FN 14992 EXTRA LP OPP | 2020-06-01 | R40 UPPER BEAUTY 1412 | F | 22520.5762 | 19984.79 | -2535.7862 | -11% | 50 |  | 0 | REGULATORS REPLACED BY MATT RYAN ON 6/1/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/19/2021 GCCC TICKET NOT REQUIRED ON 5/19/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2633 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026839600 | 584 | EX | RET. FN 14992 FOR EXTRA LP OPP | 2020-06-01 | R40 UPPER BEAUTY 1412 | F | 53.9767 | 467.48 | 413.5033 | 766% |  |  | 0 | REGULATOR REPLACED BY MATT RYAN ON 6/1/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/19/2021 GCCC TICKET NOT REQUIRED ON 5/19/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2633 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026839700 | 583 | EX | INST. FN 15001 EXTRA LP OPP | 2019-06-10 | SR3 INEZ OFFICE 1408 | F | 21579.1646 | 18285.03 | -3294.1346 | -15% | 50 |  | 0 | REGULATOR INSTALLED BY RYAN WILLIAMS ON 6/10/19 ER350 NOT INSTALLED STATION HAS EXISTING ERX PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/21 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2633 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026839800 | 584 | EX | RET. FN 15001 FOR EXTRA LP OPP | 2019-06-10 | SR3 INEZ OFFICE 1408 | F | 53.6219 | 0 | -53.6219 | 100% |  |  | 0 | REGULATOR REPLACED BY RYAN WILLIAMS ON 6/10/19 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/20 GCCC TICKET NOT REQUIRED ON 7/7/20 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2633 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026840100 | 583 | EX | INST. FN 14977 EXTRA LP OPP | 2020-06-05 | CASSADY AVE 1410 | F | 42364.1646 | 44746.31 | 2382.1454 | 6% | 55 |  | 0 | REGULATORS INSTALLED BY MATT RYAN ON 6/5/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/20/2021 GCCC TICKET NOT REQUIRED ON 5/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS ER350 NOT INSTALLED STATION HAS EXISTING ERX
KY | KY - EAST | 2633 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026840200 | 584 | EX | RET. FN 14977 FOR EXTRA LP OPP | 2020-06-05 | CASSADY AVE 1410 | F | 53.9767 | 454.36 | 400.3833 | 742% |  |  | 0 | REGUALTORS REPLACED BY MATT RYAN ON 6/5/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/20/2021 GCCC TICKET NOT REQUIRED ON 5/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2633 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026840300 | 583 | EX | INST. FN 13340 EXTRA LP OPP | 2020-06-05 | SR40 LOWER BEAUTY 1411 | F | 23446.5762 | 38579.07 | 15132.4938 | 65% | 55 |  | 0 | REGULATORS REPLACED BY MATT RYAN ON 6/5/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/20/2021 ER350 NOT INSTALLED STATION HAS EXISTING ERX GCCC TICKET NOT REQUIRED ON 5/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2633 | U123279 | Slowbe,Eric | Flynn,Craig | Miller,Gary | 18026840400 | 584 | EX | RET. FN 13340 FOR EXTRA LP OPP | 2020-06-05 | SR40 LOWER BEAUTY 1411 | F | 53.9767 | 0 | -53.9767 | 100% |  |  | 0 | REGULATORS REPLACED BY MATT RYAN ON 6/5/2020 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/20/2021 GCCC TICKET NOT REQUIRED ON 5/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026847000 | 583 | EX | INSTALL CATALYTIC HEATER | 2022-07-08 | 8 SAWMILL RD | F | 3926.2882 | 3779.78 | -146.5082 | -4% |  |  | 0 | CC# 49296. 12/21/21 DSASH NO CC# NEEDED, DID NOT GO ON SITE. 12/22/21 DSASH GMB NO CC NEEDED RETIRED OLD CATALYTIC HEATER INSTALLED NEW CATALYTIC HEATER MRAYN 7-8-22
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026847100 | 584 | EX | RETIRE CATALYTIC HEATER | 2022-07-08 | 8 SAWMILL RD | F | 77.1956 | 426.13 | 348.9344 | 452% |  |  | 0 | RETIRED OLD CATALYTIC HEATER INSTALLED NEW CATALYTIC HEATER MRYAN 7-8-2022
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026847200 | 583 | EX | INSTALL CATALYTIC HEATER | 2022-07-08 | SR 292 LOVELY 1414 | F | 3926.2882 | 3110.02 | -816.2682 | -21% |  |  | 0 | RETIRED OLD CATALYTIC HEATER AND INSTALLED NEW CATALYTIC HEATER MRYAN 7-8-2022
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 18026847300 | 584 | EX | RETIRE CATALYTIC HEATER | 2022-07-08 | SR 292 LOVELY 1414 | F | 77.1956 | 313.52 | 236.3244 | 306% |  |  | 0 | RETIRED CATALYTIC HEATER INSTALLED NEW CATALYTIC HEATER MRYAN 7-8-2022
KY | KY - EAST | 2633 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 18026848600 | 909 | EX | MATERIAL ORDER FOR 2G/3G | 2020-04-03 | US23 BLAIRTOWN 1420 | F | 8877.5399 | 6377.89 | -2499.6499 | -28% |  |  | 0 | EQUIPMENT INSTALLED BY ACP
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026850400 | 573 | EX | INSTALL ODORIZATION | 2022-09-30 | SR 1428 | F | 6839.1611 | 5241.78 | -1597.3811 | -23% |  |  | 0
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026850500 | 2000 | EX | INVESTIGATE AND AQUIRE LAND | 2019-05-13 | SR 1428 |  | 5000 | 0 | -5000 | 100% |  |  | 0
KY | KY - EAST | 2633 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026850800 | 910 | EX | RETIRE 2G/3G EQUIPMENT | 2020-04-03 | US23 BLAIRTOWN 1420 | F | 118.1234 | 0 | -118.1234 | 100% |  |  | 0 | EQUIPMENT REPLACED BY ACP
KY | KY - EAST | 2633 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026850900 | 909 | EX | UPGRADE EQUIPMENT | 2020-04-02 | HIGH & PERRY ST 1422 | F | 8776.5399 | 4411.56 | -4364.9799 | -50% |  |  | 0 | EQUIPMENT INSTALLED BY ACP
KY | KY - EAST | 2633 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026851500 | 909 | EX | UPGRADE COMM EQUIPMENT | 2020-04-02 | LOWER BETSY LAYNE 1416 | F | 8776.5399 | 4280.62 | -4495.9199 | -51% |  |  | 0 | EQUIPMENT INSTALLED BY ACP
KY | KY - EAST | 2633 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026851600 | 910 | EX | RETIRE 2G/3G EQUIPMENT | 2020-04-02 | LOWER BETSY LAYNE 1416 | F | 146.9693 | 0 | -146.9693 | 100% |  |  | 0 | EQUIPMENT RETIRED BY ACP
KY | KY - EAST | 2633 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026851700 | 909 | EX | UPGRADE COMM EQUIPMENT | 2020-04-02 | SR 550 LEBURN 1424 | F | 8776.5399 | 3299.3 | -5477.2399 | -62% |  |  | 0 | EQUIPMENT INSTALLED BY NOLL DAVIS AND ACP
KY | KY - EAST | 2633 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026851800 | 910 | EX | RETIRE 2G/3G EQUIPMENT | 2020-04-02 | SR 550 LEBURN 1424 | F | 146.9693 | -374.31 | -521.2793 | -355% |  |  | 0 | EQUIPMENT RETIRED BY ACP
KY | KY - EAST | 2633 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026854000 | 909 | EX | UPGRADE COMM EQUIPMENT | 2020-04-01 | R40 UPPER BEAUTY 1412 | F | 8776.5399 | 3616.74 | -5159.7999 | -59% |  |  | 0 | EQUPIMENT INSTALLED BY ACP AND NOLL DAVIS
KY | KY - EAST | 2633 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026854100 | 910 | EX | RETIRE 2G/3G EQUIPMENT | 2020-04-01 | R40 UPPER BEAUTY 1412 | F | 165.1234 | 0 | -165.1234 | 100% |  |  | 0 | EQUIPMENT RETIRED BY NOLL DAVIS AND ACP
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026858401 | 555 | EX | INSTALL 1020'-2" PMMP | 2019-11-19 | 3283 SR292 | B | 120785.7301 | 121199.77 | 414.0399 | 0% | 1020 | 986 | 122.9207
KY | KY - EAST | 2633 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026862000 | 2000 | EX | DETERMINE CURRENT LAND OWNER | 2019-05-13 | JARRELL FORK | B | 5000 | 0 | -5000 | 100% |  |  | 0
KY | KY - EAST | 2633 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026862100 | 2000 | EX | DETERMINE EXISTING LAND OWNER | 2019-05-13 | 100 LAKE RD | B | 5000 | 0 | -5000 | 100% |  |  | 0
KY | KY - EAST | 2633 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026862200 | 2000 | EX | DETERMINE EXISTING LAND OWNER | 2019-12-05 | 8 SAWMILL RD |  | 5000 | 0 | -5000 | 100% |  |  | 0
KY | KY - EAST | 2633 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026862400 | 2000 | EX | DETERMINE CURRENT LAND OWNER | 2019-05-13 | SR 3 JOHNS CREEK 1434 | B | 5000 | 0 | -5000 | 100% |  |  | 0
KY | KY - EAST | 2633 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026865200 | 584 | EX | RETIRE PAPER GAUGE | 2019-03-08 | VIRGINIA AVE 1425 | F | 76.4897 | 41.9 | -34.5897 | -45% |  |  | 0 | GAUGE WAS RETIRED WHEN ERX WAS INSTALLED. 584 JOB ORDER DID NOT GET CREATED AT THAT TIME
KY | KY - EAST | 2633 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026865300 | 584 | EX | RETIRE PAPER GAUGES | 2019-03-08 | SR3 INEZ OFFICE 1408 | F | 78.2326 | 321.3 | 243.0674 | 311% |  |  | 0 | ERX WAS INSTALLED. 584 JOB ORDER WAS NOT CREATED AT THAT TIME TO RETIRE THE GAUGE FACILITIES
KY | KY - EAST | 2633 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026866400 | 2000 | EX | INVEST AND ACQUIRE LAND RIGHTS | 2019-05-08 | PURPOSE DR | B | 12440 | 0 | -12440 | 100% |  |  | 0
KY | KY - EAST | 2633 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026872900 | 561 | EX | INSTALL 378' 4" & 10' 3" PMMP | 2019-05-21 | PURPOSE DR | B | 98659.184 | 76245.32 | -22413.864 | -23% | 418 | 363 | 210.0422
KY | KY - EAST | 2633 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026873000 | 562 | EX | RETIRE 84' 3" PMMP | 2019-06-21 | PURPOSE DR | B | 105.2818 | 0 | -105.2818 | 100% |  |  | 0
KY | KY - EAST | 2633 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 19026873100 | 561 | EX | INSTALL 60' OF 2"CSHP MAIN | 2019-06-20 | PURPOSE DR | B | 21475.2385 | 51028 | 29552.7615 | 138% | 60 | 76 | 671.4211
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026875300 | 587 | EX | INSTALL ODORIZER | 2022-09-30 | 100 LAKE RD | F | 1300.1611 | 9263.2 | 7963.0389 | 612% |  |  | 0 | INSTALLED ODORIZER BOTTLE JMULLINS 9-30-22
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026875400 | 587 | EX | INSTALL ODORIZER | 2022-09-30 | SR 3 JOHNS CREEK 1434 | F | 1300.1611 | 1315.89 | 15.7289 | 1% |  |  | 0 | INSTALLED FARM TAP ODORIZER BOTTLE JMULLINS 9-30-22
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026879300 | 2000 | EX | INVESTIGATE R/W AND EASEMENTS | 2020-01-28 | SR 40 |  | 4543 | 0 | -4543 | 100% |  |  | 0 | PERMITS RECIEVED AND JOB RELEASED TO CONSTRUCTION. PS&I BEING CHARGE TO 55 9 JO. D.LEMONS 1/28/20
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026881500 | 2000 | EX | INVESTIGATE LAND RIGHTS | 2020-11-18 | HWY 40 |  | 12137 | 0 | -12137 | 100% |  |  | 0
KY | KY - EAST | 2633 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 19026883300 | 555 | EX | INSTALL 100' OF 2"PMIP MAIN | 2020-02-27 | 188 GREEN MEADOW LN | B | 25386.0335 | 25567.26 | 181.2265 | 1% | 100 | 134 | 190.8004
KY | KY - EAST | 2633 | U131982 |  |  |  | 19026884700 | 2000 | EX | PS&I HWY PERMIT 572 SR899 R | 2022-11-03 | 572 SR899 |  | 1641 | 0 | -1641 | 100% |  |  | 0
KY | KY - EAST | 2633 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026891100 | 561 | EX | OFFSET 20'-2"P-MP MAIN | 2019-08-23 | 6238 KY-899 | A | 2980.8091 | 555.23 | -2425.5791 | -81% | 30 | 22 | 25.2377 | INSTALLED 020 P MP OFFSET. TESTED AT 90# FOR 1 HOUR. SOAP TEST CAPS ON HVTT , NO LEAKS. NO CHANGE IN OPER PRESSURE. MARKER BALLS PLACED ON 90S AND TAPP ING TEES. MAP REVISION COMP. J HOWARD 8-26-19
KY | KY - EAST | 2633 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026891400 | 562 | EX | RETIRE 20'-2"P-MP MAIN | 2019-08-23 | 6238 KY 899 | A | 0 | 5917.05 | 5917.05 | 100% |  |  | 0 | RETIRED 8 FT OF 020 P ML DURING OFFSET JOB ORDER. E/F PURGE POINTS TO ENDS OF MAIN. SOAP TEST, NO LEAKS. J HOWARD 8-26-19
KY | KY - EAST | 2633 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026893600 | 557 | EX | INSTALL 6132'-2" PMMP/2" CSMP | 2020-11-04 | SECOND ST | B | 887844.9551 | 732498.31 | -155346.6451 | -17% | 6210 | 5753 | 127.3246 | UNDERRUN EXPLANATION: PROJECT UNDERRAN BECAUSE ABOUT HALF AS MUCH FLAGGING WAS NEEDED AS ESTIMATED, ABOUT HALF AS MUCH COLD PATCH AND 500' LESS REPLAC EMENT THAN ESTIMATED WAS NEEDED. THE OVERHEAD EFFECT OF THESE REDUCTIONS AL SO ACCOUNTED FOR A REDUCTION OF $32K IN OVERHEADS.
KY | KY - EAST | 2633 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 19026893700 | 558 | EX | RETIRE 6221'-2"TO 8" BSLP/CSLP | 2020-11-20 | SECOND ST | B | 627.8219 | 537.32 | -90.5019 | -14% |  |  | 0
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 19026908100 | 560 | EX | RETIRE 108'-2" PMP | 2019-11-19 | HWY 292 | B | 74.2651 | 89.36 | 15.0949 | 20% |  |  | 0
KY | KY - EAST | 2633 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026926000 | 587 | EX | INSTALL NETWORK UPGRADE | 2020-05-12 | SR292 | F | 3150 | 801.02 | -2348.98 | -75% |  |  | 0 | SUPER SOLAR KIT INSTALLED BY NOLL DAVIS AND ACP PAPERWORK COMPLETED BY CYNTHIA FARIS 1/1/2022
KY | KY - EAST | 2633 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026926100 | 588 | EX | RETIRE NETWORK | 2020-05-12 | SR292 | F | 59.0079 | 0 | -59.0079 | 100% |  |  | 0 | REPLACED SOLAR PANEL WITH SUPER SOLAR KIT WORK DONE BY NOLL DAVIS AND ACP PAPERWORK COMPLETED BY CYNTHIA FARIS 1/11/2022
KY | KY - EAST | 2633 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026926200 | 587 | EX | INSTALL NETWORK UPGRADE | 2022-01-12 | 2000 CENTRAL AV | F | 3150 | 853.47 | -2296.53 | -73% |  |  | 0 | SUPER SOLAR KIT AND RV50 INSTALLED BY NOLL DAVIS AND ACP PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/12/22
KY | KY - EAST | 2633 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026926400 | 587 | EX | INSTALL NETWORK UPGRADE | 2022-08-23 | 400 E US23 | F | 3150 | 7131.29 | 3981.29 | 126% |  |  | 0 | GMB NO CC NEEDED GMB NO CC NEEDED NO CC NEEDED--GMB NO CC NEEDED GMB INSTALLED SOAR,BATTERY,AND MODEM PAPERWORK DONE BY J.MULLINS
KY | KY - EAST | 2633 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026926600 | 587 | EX | INSTALL NETWORK UPGRADE | 2022-08-29 | JARRELL FORK | F | 3150 | 6560.17 | 3410.17 | 108% |  |  | 0 | NO CC NEEDED GMB INSTALLED NEW SUPER SOLAR KIT MRYAN 8-29-22
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026930600 | 555 | EX | INSTALL 10'-2" PMMP | 2020-02-24 | 50 MULLINS 1ST ST | A | 5414.5548 | 1901.31 | -3513.2448 | -65% | 10 | 10 | 190.131
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026944400 | 2000 | EX | INVESTIGATE AND RESEARCH | 2022-11-03 | PURPOSE DR |  | 49576 | 0 | -49576 | 100% |  |  | 0
KY | KY - EAST | 2633 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026946400 | 2000 | EX | BASEMAPPING FOR INEZ AMRP | 2020-06-26 | MAIN | B | 6498 | 0 | -6498 | 100% |  |  | 0
KY | KY - EAST | 2633 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 20026946700 | 2000 | EX | BASE MAPPING FOR LOVELY AMRP | 2023-08-03 | 1ST ST | B | 1710 | 0 | -1710 | 100% |  |  | 0
KY | KY - EAST | 2633 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026963700 | 584 | EX | ABANDON REG R1425-LP RUN ONLY | 2020-11-23 | VIRGINIA AVE 1425 | F | 10078.224 | 7383.42 | -2694.804 | -27% |  |  | 0
KY | KY - EAST | 2633 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 20026966900 | 575 | EX | OBTAIN EASEMENT FOR 3"CSMP MN | 2020-08-13 | 5331 KY RT 302 | F | 18170 | 15068.43 | -3101.57 | -17% |  |  | 0
KY | KY - EAST | 2633 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 20026968500 | 566 | EX | RETIRE 3" SERVICE LINE | 2020-11-18 | 230 CENTRAL AV | B | 423.9421 | 0 | -423.9421 | 100% |  |  | 0 | CHUCK MILLAY'S CREW ABANDONED 3" SERVICE LINE SOAP SUDS TESTE 3" CAP AT OPE RATING PRESSURE LP REPLACED WITH 1" MP SERVICE LINE 2600 UMAC FLOW VALVE IN STALLED 11/18/20 MBLANKE U123965
KY | KY - EAST | 2633 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026980000 | 557 | EX | INSTALL 675' - 2"/4" PMLP | 2021-03-03 | SR 40 | B | 148515.2952 | 186497.16 | 37981.8648 | 26% | 735 | 298 | 625.8294 | DUE TO WEATHER CONDITION ON STATE ROAD UNABLE TO MAKE COMMIT DATE OVERRUN EXPLANATION: ALL OPEN CUT WAS ESTIMATED, BUT 108 FEET OF DIRECTIONA L BORE WAS USED. ADDITIONALLY, APPROXIMATELY 4 TIMES AS MUCH FLAGGING WAS R EQUIRED THAN ESTIMATED. OVERHEADS INCREASED $10,500 DUE TO THESE OVERAGES.
KY | KY - EAST | 2633 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 20026980100 | 558 | EX | RETIRE 622' - 2" BSLP | 2021-03-04 | SR 40 | B | 103.8156 | 647.77 | 543.9544 | 524% |  |  | 0
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026990900 | 560 | EX | RETIRE 1104'-2" CSIP | 2020-12-31 | HWY 194 | B | 107.2796 | 0 | -107.2796 | 100% |  |  | 0 | THIS WAS PAPER ONLY JOB MAIN AND STATION RETIRED BY SUPPLIER WITH THEIR MAIN REPLACEMENT JOB THIS STATION AND MAIN HAVE BEEN INACTIVE FOR YEARS THIS WAS FIELD VERIFIED BY ENGINEERING JOB COMPLETED TO CORRECT CKY RECORDS
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026991000 | 584 | EX | RETIRE R-1430 | 2020-12-31 | SR194 PHYLLIS 1430 | F | 107.2796 | 0 | -107.2796 | 100% |  |  | 0 | COMPLETED THIS JOB ON PAPER ONLY TO CORRECT CKY RECORDS. STATION AND ALL PIPING RETIRED YEARS AGO AND PAPERWORK NOT COMPLETED SEE JOB CREATE COMMENTS THIS WAS FIELD VERIFIED BY ENGINEERING
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 20026991200 | 586 | EX | RETIRE BUILDING | 2021-01-07 | SR194 PHYLLIS 1430 | F | 107.2796 | 0 | -107.2796 | 100% |  |  | 0 | THIS IS PAPER ONLY JOB BUILDING WAS TORN DOWN MANY YEARS AGO THIS JOB IS TO CORRECT CKY RECORDS ONLY FIELD VERIFIED BY CKY ENGINEERING
KY | KY - EAST | 2633 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026100300 | 557 | EX | EMER INS ~15'-2"/3" PMIP/CSIP | 2021-02-05 | 5000 ELEMENTARY DR | A | 15461.5913 | 13138.1 | -2323.4913 | -15% | 80 | 20 | 656.905 | 3" C.S. MAIN PULLED LOOSE FROM 4 BOLT COUPLING DUE TO STRESS ON MAIN FROM EXPOSURE DOWN STREAM. TAPPED & STOPPED 3" C.S. REPLACED LEAKING SECTION WITH 3" P 20' PRESSURE TEST 90 PSIG 1HR PURGED MAIN LINE, RESTORED SERVICE.
KY | KY - EAST | 2633 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026100400 | 558 | EX | EMER RETIRE ~5'-3" CSIP | 2021-02-05 | 5000 ELEMENTARY DR | A | 1147.7777 | 1505.21 | 357.4323 | 31% |  |  | 0 | 3" CS MAIN PULLED LOOSE FROM 4 BOLT COUPLING DUE TO STRESS ON MAIN FROM EXPOSURE DOWN STREAM. TAPPED & STOP 3" CS MAIN REPLACED LEAKING SECTION WITH 3" P 20' PRESSURE TEST 90PSIG FOR 1 HR. PURGED MAIN & RESTORED SERVICE
KY | KY - EAST | 2633 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026121900 | 555 | EX | INSTALL 100'-2" PMIP | 2021-08-12 | 14 2ND ST FOX BTM | B | 26223.5353 | 30760.67 | 4537.1347 | 17% | 100 | 115 | 267.4841
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026131400 | 559 | EX | INSTALL 300'-2" PMIP | 2021-11-09 | MAIN ST | B | 139158.4326 | 158500.46 | 19342.0274 | 14% | 300 | 300 | 528.3349
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026131500 | 560 | EX | RETIRE 300'-2" PMIP | 2021-11-09 | MAIN ST | B | 88.8156 | 39.34 | -49.4756 | -56% |  |  | 0
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026131600 | 2000 | EX | INVESTIGATE MAINS | 2021-11-12 | MAIN ST | B | 34568 | 0 | -34568 | 100% |  |  | 0 | PS&I COMPLETED PRIOR TO CAPITAL JO BEING COMPLETED. D.LEMONS 11/12/2021
KY | KY - EAST | 2633 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026136300 | 557 | EX | INSTALL 37'-2"/3" PMMP/CSMP | 2021-09-10 | 7 BLAIRTOWN RD | A | 33826.5433 | 14615 | -19211.5433 | -57% | 37 | 20 | 730.75 | INSTALLED NEW 030 CS AND PE MAIN. TEST @ 90# FOR 1 HR, NO LEAKS. PURGED INT O SERVICE. STOP OFF AND REMOVED OLD MAIN. 3" WELD CAPS & 2" PE CAP SOAP TES T, NO LEAKS. WRAPPED MAIN. SWING TIES & EM BALLS. J HOWARD 9-20-21
KY | KY - EAST | 2633 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026136400 | 558 | EX | RETIRE 29'-2"/3" CSMP/PMMP | 2021-09-10 | 7 BLAIRTOWN RD | A | 826.7837 | 83.24 | -743.5437 | -90% |  |  | 0 | LEAK ON END OF STEEL MECH COMP END CAP. INSTALLED NEW 030 & 020 ST AND PE M L, TESTED AT 90# FOR 1 HR. SOAP TEST 030 AND 020 CAPS, NO LEAKS. BAR BANKS, NGF. INSTALLED ANODE, WRAPPED MAIN. J HOWARD 9-13-21
KY | KY - EAST | 2633 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026142800 | 555 | EX | INSTALL 475'-4" PMLP | 2022-04-26 | 122 BOARDWALK ST | B | 59783.3635 | 138313.25 | 78529.8865 | 131% | 350 | 462 | 299.3793 | TTOY-9/20/22: OVERRUN LEVEL 2 VARIANCE EXPLANATION IN WMSDOCS
KY | KY - EAST | 2633 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026146701 | 559 | EX | INSTALL 100'-2" PMIP | 2022-08-19 | 89 COWTOWN RD | B | 40630.8922 | 6197.36 | -34433.5322 | -85% | 100 | 101 | 61.36 | VAPIERCE (03/27/23); JOB OVER RUN DUE TO CONTRACT CHARGES ASSOCIATED TO EMERGENCY JOB ORDER 22-0262152-00 EMER-KY FLOODING 2022. $29,900 IN ESTIMATED CONTRACT COSTS AND $0 BOOKED TO THIS JOB ORDER, ALL CONTRACT COSTS WERE CHARGED TO EMER-KY FLOODING 2000 JO. MOST LABOR COSTS WERE ALSO BOOKED UNDER THE EMER JOB ORDER. CONSTRUCTION WAS UNAWARE THIS PLANNED PROJECT OVERLAPPED WITH EMER WORK.
KY | KY - EAST | 2633 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 21026149200 | 2000 | EX | INVESTIGATE R/W & LAND RIGHTS | 2021-11-23 | 122 BOARDWALK ST | B | 9790 | 0 | -9790 | 100% |  |  | 0
KY | KY - EAST | 2633 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 21026151700 | 2000 | EX | ENE DESIGN STATION OUTLET VLV | 2023-08-22 | 29320 KY 292 |  | 20000 | 6509.1 | -13490.9 | -67% |  |  | 0
KY | KY - EAST | 2633 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026993000 | 558 | EX | RETIRE 616'-4"/2" BSMP | 2020-11-20 | VIRGINIA | A | 195.5073 | 0 | -195.5073 | 100% |  |  | 0
KY | KY - EAST | 2633 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026994400 | 557 | EX | EMER- INSTALL 5'-2" PMIP | 2021-01-08 | RAILROAD | A | 7281.2724 | 5176.12 | -2105.1524 | -29% | 1 | 6 | 862.6867 | INSTALLED 6' NEW 020 MDPE ML. TESTED AT 90# 20 MINS. WELD-IN TRANSITIONS. S OAP TEST TIE IN. PURGED AT EOM. SWING TIES AND ELEC MARKERS. J HOWARD 1-13- 21
KY | KY - EAST | 2633 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 21026994500 | 558 | EX | EMER- RETIRE 5'-2" BSIP | 2021-01-08 | RAILROAD | A | 239.0145 | 1169.82 | 930.8055 | 389% |  |  | 0 | INSTALLED 2 020 TDW SS. TAP AND STOP ML. NO UPSTREAM PRESSURE LOSS. REMOVED AND ABANDONED 6' SECTION OF 020 S ML FOR INSTALL OF 020 MDPE. J HOWARD 1-1 1-21
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026997600 | 557 | EX | INSTALL 20'-2" PMIP | 2021-03-30 | BEVINS ST | B | 28869.525 | 25490.16 | -3379.365 | -12% | 19 | 12 | 2124.18
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 21026997700 | 558 | EX | RETIRE 15'-2" BSIP | 2021-03-30 | BEVINS ST | B | 88.4533 | 95.92 | 7.4667 | 8% |  |  | 0
KY | KY - EAST | 2633 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 22026158200 | 555 | EX | INSTALL 100'-2" PMMP | 2022-05-05 | 71 PENNINGTON DR | B | 26700.5988 | 22688.28 | -4012.3188 | -15% | 100 | 95 | 238.824
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026164600 | 557 | EX | EMER - INSTALL 220'-2" PMIP | 2022-02-18 | 1200 E HWY 550 | B | 49188.5426 | 49083.09 | -105.4526 | 0% | 220 | 289 | 169.8377
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026164700 | 558 | EX | EMER - RETIRE 20'-4" CSIP | 2022-02-18 | 1200 E HWY 550 | B | 109.7476 | 140.47 | 30.7224 | 28% |  |  | 0
KY | KY - EAST | 2633 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026174700 | 557 | EX | EMER- INSTALL 82'-4" PMIP/CSIP | 2022-03-08 | 44 SARAH EVERAGE RD | A | 94519.5369 | 85702.82 | -8816.7169 | -9% | 55 | 82 | 1045.1563 | REPAIRED LEAK ON MAIN BY REPLACING A SECTION OF BARE STEEL MAIN WITH 4" PLA STIC TESTED 105 PSIG FOR 1 HOUR WITH ELECTRONIC KUHLMAN GAUGE SERIAL NO 101 09154 3/8/22 REFER TO 2211 JOB ORDER# 22-9840666-00
KY | KY - EAST | 2633 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026174800 | 558 | EX | EMER- RETIRE 76'-4" BSIP | 2022-03-08 | 44 SARAH EVERAGE RD | A | 0 | 0 | 0 | 0% |  |  | 0
KY | KY - EAST | 2633 | U938437 |  |  |  | 22026175100 | 559 | EX | INSTALL 3" OUTLET VALVE | 2023-05-23 | HWY 119 | B | 40477.7168 | 36249.58 | -4228.1368 | -10% | 15 | 14 | 2589.2557
KY | KY - EAST | 2633 | U938437 |  |  |  | 22026175200 | 560 | EX | RETIRE ~10' - 3" CSHP | 2023-05-23 | HWY 119 | B | 593 | 257.25 | -335.75 | -57% |  |  | 0
KY | KY - EAST | 2633 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026179500 | 557 | EX | EMER - INSTALL 5'-2" PMIP | 2022-04-05 | FLOYD | A | 5401.378 | 2346.49 | -3054.888 | -57% | 5 | 5 | 469.298
KY | KY - EAST | 2633 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026179600 | 558 | EX | EMER - RETIRE 5'-2" P-IP | 2022-04-05 | FLOYD | A | 238.1994 | 0 | -238.1994 | 100% |  |  | 0
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026189100 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-06-29 | SR40 LOWER BEAUTY 1411 | F | 4745.0565 | 2559.49 | -2185.5665 | -46% |  |  | 0 | CC # 70264 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-29-2022
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026189200 | 910 | EX | RETIRE ELECTRONIC EQUIPMENT | 2022-06-29 | SR40 LOWER BEAUTY 1411 | F | 124.5156 | 213.04 | 88.5244 | 71% |  |  | 0 | CC # 70264 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-29-2022
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026189300 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-06-14 | R40 UPPER BEAUTY 1412 | F | 4745.0565 | 487.15 | -4257.9065 | -90% |  |  | 0 | CC# 70358 RETIRED BOTH ERX'S INSTALLED NEW MIWI350 MRYAN 6-14-2022
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026189400 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-06-14 | R40 UPPER BEAUTY 1412 | F | 124.5156 | 243.32 | 118.8044 | 95% |  |  | 0 | CC # 70358 RETIRED OLD ERX'S INSTALLED NEW MIWI350 MRYAN 6-14-2022
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026189500 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-06-15 | LOWER BETSY LAYNE 1416 | F | 4745.0565 | 292.29 | -4452.7665 | -94% |  |  | 0 | CC # 70566 RETIRED OLD ERX INSTALLED NEW HONEYWELL MIWI350 MRYAN 6-15-2022
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026189600 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-06-15 | LOWER BETSY LAYNE 1416 | F | 124.5156 | 91.82 | -32.6956 | -26% |  |  | 0 | CC # 70566 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 06-15-2022
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026189700 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-06-15 | STORE HOLLOW RD 1417 | F | 4745.0565 | 91.91 | -4653.1465 | -98% |  |  | 0 | CC # 70497 RETIRED OLD ERX INSTALLED NEW MIW350 MRYAN 06-15-2022
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026189800 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-06-15 | STORE HOLLOW RD 1417 | F | 124.5156 | 213.04 | 88.5244 | 71% |  |  | 0 | CC # 70497 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-15-2022
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026189900 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-06-30 | WARFIELD SR40 1413 | F | 4745.0565 | 275.74 | -4469.3165 | -94% |  |  | 0 | CC # 72215 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6/30/2022
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026190000 | 910 | EX | RETIRED ELECTRONICS EQUIPMENT | 2022-06-30 | WARFIELD SR40 1413 | F | 124.5156 | 61.53 | -62.9856 | -51% |  |  | 0 | CC # 72215 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6/30/2022
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026191100 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-06-27 | US 119 1433 | F | 4801.1928 | 1305.26 | -3495.9328 | -73% |  |  | 0 | CC # 71822 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-27-2022
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026191200 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-06-27 | US 119 1433 | F | 124.8731 | 229.57 | 104.6969 | 84% |  |  | 0 | CC # 71822 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-27-2022
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026191500 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-07-12 | SR899 1429 | F | 4801.1928 | 1457.43 | -3343.7628 | -70% |  |  | 0 | UPGRADED ERX TO MIWI
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026191600 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-07-12 | SR899 1429 | F | 124.8731 | 447.49 | 322.6169 | 258% |  |  | 0 | CC # 73221 UPGRADDED ERX TO MIWI
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026192700 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-06-28 | VIRGINIA AVE 1425 | F | 4801.1928 | 780.12 | -4021.0728 | -84% |  |  | 0 | CC # 71922 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-28-2022
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026192800 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-06-28 | VIRGINIA AVE 1425 | F | 124.8731 | 82.66 | -42.2131 | -34% |  |  | 0 | CC # 71984 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-28-2022
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026193200 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-06-28 | SR292 | F | 4801.1928 | 271.17 | -4530.0228 | -94% |  |  | 0 | CC # 71922 RETIRED OLD ERX INSTALLED NEW MIWI 350 MRYAN 6/28/2022
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026193300 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-06-28 | SR292 | F | 124.8731 | 156.09 | 31.2169 | 25% |  |  | 0 | CC # 71922 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6/28/2022
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026193400 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-07-27 | US23 BLAIRTOWN 1420 | F | 4801.1928 | 1938.82 | -2862.3728 | -60% |  |  | 0 | CC # 75237 NO CC NOT ONSITE PAPERWORK NO CC NEEDED UPGRADDED ERX TO MIWI JMULLINS
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026193500 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-07-27 | US23 BLAIRTOWN 1420 | F | 124.8731 | 22.08 | -102.7931 | -82% |  |  | 0 | CC # 75237
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026193600 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-10-18 | MIDDLE FORK RD. | F | 4801.1928 | 1911.78 | -2889.4128 | -60% |  |  | 0 | CC # 3865 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 10-18-22
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026193700 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-10-18 | MIDDLE FORK RD. | F | 124.8731 | 217.55 | 92.6769 | 74% |  |  | 0 | CC # 3865 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 10-18-22
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026193800 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-07-14 | SR 550 LEBURN 1424 | F | 4801.1928 | 1577.79 | -3223.4028 | -67% |  |  | 0 | CC # 73511
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026193900 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-07-14 | SR 550 LEBURN 1424 | F | 124.8731 | 235.52 | 110.6469 | 89% |  |  | 0 | CC # 73511 UPGRADED TO MIWI JOSH MULLINS
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026194000 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-07-14 | PRATT HOLLOW 1423 | F | 4801.1928 | 1673.13 | -3128.0628 | -65% |  |  | 0 | CC # 73511 UPGRADED FROM ERX TO MIWI JOSH MULLINS
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026194100 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-07-14 | PRATT HOLLOW 1423 | F | 124.8731 | 230.5 | 105.6269 | 85% |  |  | 0 | CC # 73511
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026194200 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-07-13 | HIGH & PERRY ST 1422 | F | 4801.1928 | 1788.47 | -3012.7228 | -63% |  |  | 0 | CC # 73334
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026194300 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-07-13 | HIGH & PERRY ST 1422 | F | 124.8731 | 470.99 | 346.1169 | 277% |  |  | 0 | CC # 73334 UPDATTED ERX TO MIWI 07-13-22 J. MULLINS
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026194400 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-06-30 | SR 292 LOVELY 1414 | F | 4801.1928 | 356.51 | -4444.6828 | -93% |  |  | 0 | CC # 72268 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-30-2022
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026194500 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-06-30 | SR 292 LOVELY 1414 | F | 124.8731 | 1.84 | -123.0331 | -99% |  |  | 0 | CC # 72268 RETIRED OLD ERX INSTALLED NEW MIWI 350 MRYAN 6-30-2022
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026196000 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 2022-07-27 | SR 1428 | F | 4801.1928 | 6078.6 | 1277.4072 | 27% |  |  | 0 | CC # 75237 RETIRED OLD ERX AND INSTALLED NEW HONEYWELL MIWI350 MRYAN 7-27-2022
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026196100 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 2022-07-27 | SR 1428 | F | 124.8731 | 232.52 | 107.6469 | 86% |  |  | 0 | CC # 75237 RETIRED OLD ERX INSTALLED NEW HONEY WELL MIWI350 MATT RYAN 7-27-2022
KY | KY - EAST | 2633 | GSULLI1 | Sullivan,Gary E | Flynn,Craig | Miller,Gary | 22026208500 | 2000 | EX | S WILLIAMSON-INV EASEMENTS | 2023-08-09 | US 119 1433 |  | 5000 | 620.43 | -4379.57 | -88% |  |  | 0
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026215200 | 2000 | EX | EMER-KY FLOODING 2022 | 2022-12-19 |  | A | 50000 | 0 | -50000 | 100% |  |  | 0
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026216500 | 559 | EX | EMER-INSTALL 2"/4" POLY VALVES | 2022-08-10 |  | B | 298130.9642 | 433396.83 | 135265.8658 | 45% | 11 | 10 | 43339.683 | COMPLETED OVERRUN EXPLANATION FORM LOADED INTO WMSDOCS JO WORKSPACE. D.LEMO NS 2/24/2023
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026216600 | 560 | EX | EMER-RETIRE 7'-2"/4" PMIP/CSIP | 2022-08-11 |  | B | 83.4538 | 0 | -83.4538 | 100% |  |  | 0
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026216700 | 559 | EX | EMER - INSTALL 456'-4" CS/PMIP | 2022-11-08 | PRATT HOLLOW | B | 50625 | 85192.39 | 34567.39 | 68% | 454 | 533 | 159.8356
KY | KY - EAST | 2633 | U132280 | Pierce,Victoria Ann | MacLaughlin,Cary | Koenig,Clay | 22026216801 | 560 | EX | EMER-RETIRE 130'-4" CS/BS/PIP | 2022-11-08 | PRATT HOLLOW | B | 132.427 | 439.01 | 306.583 | 232% |  |  | 0
KY | KY - EAST | 2633 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026218600 | 583 | EX | INSTALL NEW 1ST CUT REGULATOR | 2023-11-06 | US23 UPPER HAROLD 1419 | F | 2521.2589 | 3338.51 | 817.2511 | 32% |  |  | 0 | NOT ONSITE NO CC NEEDED GETTING MATERIAL/BUILDING REG PREPING FOR JOB MCR CC # 51243 INSTALLD NEW 1ST CUT REG DUE TO CORROSION MCR 11-6-23 1445 CC # 51776 ISTALLD TUBING ANF PAINTED SETTIN FIELD WORK COMPLETE
KY | KY - EAST | 2633 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 22026218700 | 584 | EX | RETIRE 1ST CUT REGULATOR | 2023-11-06 | US23 UPPER HAROLD 1419 | F | 84.9152 | 1644.86 | 1559.9448 | 1,837% |  |  | 0 | CC # 51243 REMOVED OLD FIRST CUT REG MCR 11-6-23 1030
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026241900 | 561 | EX | INSTALL 249'-2" PMIP | 2023-03-14 | E MAIN ST | B | 81974.2921 | 101153.64 | 19179.3479 | 23% | 269 | 284 | 356.1748
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026242000 | 562 | EX | RETIRE 135'-3" BSIP | 2023-03-14 | E MAIN ST | B | 117.5985 | 139.7 | 22.1015 | 19% |  |  | 0
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 22026242100 | 2000 | EX | INVESTIGATE MAINS | 2023-02-20 | E MAIN ST | B | 6298 | 0 | -6298 | 100% |  |  | 0
KY | KY - EAST | 2633 | U128885 | Toy,John Trevor | Parsley,Joe | Webb,Jared | 23026256300 | 555 | EX | INSTALL 130'-2" PMIP | 2023-07-21 | 40 2ND ST | B | 38002.449 | 19141.35 | -18861.099 | -50% | 130 | 129 | 148.3826
KY | KY - EAST | 2633 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 23026261300 | 909 | EX | INSTALL MIWI AND SUPER SOLAR | 2023-07-10 | LOWER HAROLD 1418 | F | 26706.2854 | 4877.76 | -21828.5254 | -82% |  |  | 0 | CC # 36552 INSTALLD MIWI NO CC NOT ONSITE--PAPER WORK
KY | KY - EAST | 2633 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 23026261400 | 584 | EX | RETIRE PAPER CHART | 2023-07-10 | LOWER HAROLD 1418 | F | 121.7239 | 0 | -121.7239 | 100% |  |  | 0
KY | KY - EAST | 2633 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 23026261500 | 909 | EX | INSTALL MIWI AND SUPER SOLAR | 2023-07-11 | US23 UPPER HAROLD 1419 | F | 26706.2854 | 4069.95 | -22636.3354 | -85% |  |  | 0 | CC # 36725 NO CC NEEDED---GMB ACCOUNT NOT ON SITE NO CC NEEDED---PAPERWORK OFF SITE CC # 40724
KY | KY - EAST | 2633 | U132703 | Falade,Adetomiwa O | Parsley,Joe | Webb,Jared | 23026261600 | 584 | EX | RETIRE PAPER CHART | 2023-07-11 | US23 UPPER HAROLD 1419 | F | 121.7239 | 388.77 | 267.0461 | 219% |  |  | 0 | CC # 36725
KY | KY - EAST | 2633 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026265300 | 573 | CO | INSTALL PILOT REGULATORS | 2023-10-26 | SR899 1429 | F | 7328.1838 | 9398.99 | 2070.8062 | 28% |  |  | 0
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026274600 | 559 | EX | EMER - INSTALL 5'-2" PMIP | 2023-05-11 | 143 RAILROAD CR | B | 11073.0623 | 2867.86 | -8205.2023 | -74% | 5 | 3 | 955.9533
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026274700 | 560 | EX | EMER - INSTALL 5'-2" PM | 2023-05-11 | 143 RAILROAD CR | B | 116.0664 | 0 | -116.0664 | 100% |  |  | 0
KY | KY - EAST | 2633 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026275800 | 587 | EX | INSTALL NEW BATTERY/EQUIPMENT | 2023-05-23 | JARRELL FORK | F | 2819.6093 | 135.94 | -2683.6693 | -95% |  |  | 0
KY | KY - EAST | 2633 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026275900 | 588 | EX | RETIRE BATTERY FACILITY | 2023-05-17 | JARRELL FORK | F | 139.1159 | 0 | -139.1159 | 100% |  |  | 0
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026282000 | 561 | EX | INSTALL 40'-4" PMIP | 2023-07-17 | HWY 550 | B | 63454.1516 | 49257.58 | -14196.5716 | -22% | 44 | 60 | 820.9597
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026282100 | 562 | EX | RETIRE 36'-4" BSIP | 2023-07-17 | HWY 550 | B | 139.1159 | 124.74 | -14.3759 | -10% |  |  | 0
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026291200 | 557 | EX | EMER - INSTALL 8'-3" PMIP | 2023-09-01 | 153 OLD MIDDLE FORK RD | A | 32593.7477 | 51065.27 | 18471.5223 | 57% | 8 | 9 | 5673.9189 | INSTALLED 3INCH PLASTIC MAIN SECTION TO REPLACE LEAKING 3 INCH BS MAIN JCK 9.8.23
KY | KY - EAST | 2633 | U122858 | Lemons,David Nelson | Parsley,Joe | Webb,Jared | 23026291300 | 558 | EX | EMER - RETIRE 7'3" BS&P | 2023-09-01 | 153 OLD MIDDLE FORK RD | A | 119.4953 | 392.93 | 273.4347 | 229% |  |  | 0 | ABANDON LEAKING METAL MAIN. INSTALLED 3 INCH PLASTIC MAIN JCK 9.8.23
KY | KY - EAST | 2633 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026302100 | 584 | CO | RETIRE PAPER GAUGE | 2023-10-13 | DUDLEY DR | F | 989.8688 | 306.23 | -683.6388 | -69% |  |  | 0
KY | KY - EAST | 2633 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 23026302200 | 584 | EX | RETIRE PAPER GAUGE | 2023-12-04 | LOWER HAROLD 1418 | F | 989.8688 | 1131.38 | 141.5112 | 14% |  |  | 0
KY | KY - EAST | 2633 | U461383 | Walker,Thomas B | Parsley,Joe | Webb,Jared | 24026311100 | 588 | EX | RETIRE GMB FACILITIES | 2019-01-10 | 3185 MIDDLE FORK WF CR | F | 123.4493 | 0 | -123.4493 | 100% |  |  | 0 | THIS HASN'T BEEN IN SERVICE FOR MANY YEARS - APPROX OUT OF SERVICE IN 2009. WMS ONLY ALLOWS OUT OF SERVICE DATE OF 5 YEARS BACK. PAPER ABANDON ONLY

## WMS Variance Data (hidden)
Report Run: 05-29-2026 12:41:48 PM CDT
**Nisource Confidential - For Internal Use Only
For questions, contact Business Intelligence at birepreq@nisource.com
Job Order | Job Type | Job Status | Job Summary | Address | Install Cd | Estimated Total Cost | Actual Total Cost | Cost Variance | Percent Variance | Estimated Footage | Actual Footage | Actual Cost Per Foot | Execution Comments
16026652700 | 2000 | EX | INVESTIGATE FOR SERVICE | 961 NANDINO BV |  | 3820.3494 | 0 | -3820.3494 | 100% |  |  | 0
16026652800 | 2000 | EX | INVESTIGATE FOR SERVICE | 1545 ALEXANDRIA DR |  | 3820.3494 | 0 | -3820.3494 | 100% |  |  | 0
16026664700 | 2000 | EX | INVESTIGATE NON-STANDARD S/L | 1708 JENNIFER RD 1B | B | 5000 | 0 | -5000 | 100% |  |  | 0 | TWALKER/KY 11-18-21: LAND SERVICE COULD NOT OBTAIN EASEMENT(S) FROM PROPERTY OWNER. PROJECT CANCELLED.
17026704800 | 2000 | EX | INVESTIGATE PROPERTY | 803 CHILES AV |  | 5682.1692 | 0 | -5682.1692 | 100% |  |  | 0
17026714600 | 2000 | EX | INVESTIGATE PIPLNE CONFLCTS | LEESTOWN RD | B | 8227 | 0 | -8227 | 100% |  |  | 0
18026757700 | 909 | EX | INSTALL MI WIRELESS EFC | BRIAR HILL RD | F | 13926.0597 | 14191.42 | 265.3603 | 2% |  |  | 0 | INSTALLED HONEYWELL ERX SUPER SOLAR KIT J MULLINS 11-7-22
18026757800 | 584 | EX | RETIRE RECORDING GAUGE | BRIAR HILL RD | F | 73.0037 | 0 | -73.0037 | 100% |  |  | 0 | RETIRED CHART INSTALLED HONEYWELL ERX JMULLINS 11-7-22
18026773600 | 2000 | EX | INVESTIGATE RIGHTS - NEW FENCE | BRIAR HILL RD | B | 7724 | 0 | -7724 | 100% |  |  | 0
18026779401 | 575 | CO | ACQ 25X25 SITE FOR NEW R-1133 | 763 W NEW CIRCLE KDOT ESMT RD | F | 17250 | 16121.32 | -1128.68 | -7% |  |  | 0 | ENGINEERING PROJECT REQUIRED EXPOSURE OF FACILITIES FOR UPCOMING PROJECT EXPOSED GAS FACILITIES VIA HYDRO EXCAVATION
18026796600 | 2000 | EX | DETERMINE LAND RIGHTS | 4940 ATHENS BOONESBORO RD | A | 8400 | 0 | -8400 | 100% |  |  | 0
18026807000 | 583 | EX | INST. FN 115 EXTRA LP OPP | 543 SMITH ST | F | 24102.8722 | 28771.63 | 4668.7578 | 19% | 50 |  | 0 | GCCC# 11422 CHARED TIME TO COLLECT MATERIAL. DID NOT VISIT SITE NO GCCC TICKET REQUIRED CMCOC 3/3/21 GCCC# 13985 CMCHOLAN 3-4-2021 CCC#13985 REGULATOR AND ER350 INSTALLED BY CHRIS COX ON 3/4/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026807100 | 584 | EX | RET. FN 115 FOR EXTRA LP OPP | 543 SMITH ST | F | 54.9718 | 2550 | 2495.0282 | 4,539% |  |  | 0 | REGULATOR REPLACED BY CHRIS COX ON 3/4/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/12/2021 GCCC TICKET NOT REQUIRED ON 5/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026808800 | 583 | EX | INST. FN 259 EXTRA LP OPP | 1005 RICHMOND RD | F | 23795.1646 | 258499.79 | 234704.6254 | 986% | 50 |  | 0 | NOT ONSITE. NO GCCC TICKET REQUIRED. CMCOX 7/6/21 GCCC# 30701 CMCOX 7/7/21 NOT ONSITE. NO GCCC TICKET REQUIRED. CMCOX 7/8/21 CCC# 31111 GCCC# 31231 CMCOX 7/13/21 GCCC# 31380 GCCC# 31536 GCCC# 31616 DID NOT ENTER PIT. NO GCCC# REQUIRED. CMCOX 7/19//21 GCCC# 31756 CMCOX 7/20/21 CC# 32093 REGULATORS INSTALLED BY CHRIS COX 7/27/21 PAPERWORK COMPLETED BY CFARIS 7/29/21 CCC# NOT REQUIRED BY CFARIS ON 7/29 OR 8/2 NOT AT STATION
18026808900 | 584 | EX | RET. FN 259 FOR EXTRA LP OPP | 1005 RICHMOND RD | F | 53.9767 | 0 | -53.9767 | 100% |  |  | 0 | REGULATORS REPLACED BY CHRIS COX ON 7/27/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/29/2021 GCCC TICKET NOT REQUIRED ON 7/29/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026843301 | 557 | EX | INSTALL 3000' OF 4/6/8"PMLP | M L KING | B | 1495308.5734 | 1711065.31 | 215756.7366 | 14% | 2875 | 3068 | 557.7136
18026843400 | 558 | EX | RETIRE 2670' OF 3"/6"CILP MAIN | M L KING | B | 81.035 | 598.25 | 517.215 | 638% |  |  | 0
18026848701 | 909 | EX | STATION UPGRADES (SEP RELATED) | 4940 ATHENS BOONESBORO RD | F | 151848.4602 | 206545.63 | 54697.1698 | 36% |  |  | 0 | CCC 22581 CCC 23126 CCC 23442 CCC 24345 CCC 25855 CCC 26071
19026876200 | 2000 | EX | INVESTIGATE CONFLICTS | WILSON DOWNING RD |  | 20833 | 0 | -20833 | 100% |  |  | 0 | INVESTIGATION, CONFLICT ASSESMNET AND DESIGN COMPLETED. WAITING ON LFUCG F OR CONSTRUCTION DATES. PROJECT WAS STARTED IN 2019 AND THEN PLACED ON HOLD BY LFUCG. D.LEMONS 11/10/2023
19026878400 | 575 | EX | ACQUIRE NEW LAND RIGHTS | 1800 MASON-HEADLEY RD | F | 10994 | 5313.62 | -5680.38 | -52% |  |  | 0
19026889001 | 561 | EX | INSTALL 28'-8" PMLP | DUNTREATH | B | 17790.2899 | 30769.7 | 12979.4101 | 73% | 28 | 35 | 879.1343
19026907300 | 2000 | EX | INVESTIGATE LAND RIGHTS | STRADER RD |  | 5000 | 0 | -5000 | 100% |  |  | 0
19026908700 | 2000 | EX | INVESTIGATE ENCROACHMENT | 4130 GEORGETOWN RD | B | 7000 | 0 | -7000 | 100% |  |  | 0
19026909400 | 2000 | EX | LEESTOWN RD - ASSESS CONFLICT | LEESTOWN @ NEW CIRCLE RD |  | 30829 | 0 | -30829 | 100% |  |  | 0
20026920600 | 2000 | EX | CLAYS MILL RD SECTION 1B | CLAYS MILL RD SECT 1B |  | 55323 | 0 | -55323 | 100% |  |  | 0 | VERIFIED & EXPOSED VIA HYDRO EXCAVATION; SPOTTED PLLP MAIN TO VERIFY DEPTH MEASUREMENTS FOR MAPPING & SURVEY INFORMATION; INSTALLED FLUSH MOUNT TRACER WIRE STATION FOR FUTURE LOCATES & WORK; JNEWSOME 8/7/2020 EXPOSED 8'HP GAS MAIN FOR B SLONE VIA HYDRO EXCAVATION; RECORDED DEPTHS AT STAKED LOCATIONS TO MAP APPROXIMATE LOCATION FOR ENGINEERING PROJECT JNEWSOME 8/24/20 JOB NOT COMPLETE, USED HYDRO EXCAVATION TO EXPOSE PORTIONS OF GAS FACILITY FOR ENGINEERING B SLONE NEED TO EXPOSE MORE GAS FACILITIES, WILL RETURN FOR FURTHER IVESTIGATION EXPOSED FACILITIES FOR ENGINEERING B SLONE; INSTALLED ELECTONIC MARKERS & LINE MARKER W/WIRE FOR FUTURE REFERENCE; RECORDED DATA FOR DEPTHS & PIN POINT TIE INS JNEWSOME GCCC# 8772
20026920700 | 2000 | EX | TRC SURVEY/STUDIES | 2001 MERCER RD | A | 90000 | 0 | -90000 | 100% |  |  | 0 | INSTRUCTED BY RICK WILBERT TO EXECUTE WE WERE TOLD THIS DATE THAT THE PROJECT WAS COMPLETED. THERE IS NO COMPLIAN CE ISSUE THAT I AM AWARE OF.
20026924400 | 575 | EX | NEW REGULATOR SITE | 1313 OLD FRANKFORT PK | F | 13408.4857 | 0 | -13408.4857 | 100% |  |  | 0 | JO BEING COMPLETED AT COMPLETION OF PROJECT. D.LEMONS
20026927900 | 587 | EX | UPGRADE ELECTRONICS | 310 S LIMESTONE ST | F | 3038 | 3660.91 | 622.91 | 21% |  |  | 0 | EFC REPLACED BY C. COX ON 3-1-22 PAPERWORK CO BY J MULLINS ON 3-2-22
20026928000 | 587 | EX | UPGRADE ELECTRONICS | 767 WINCHESTER RD | F | 3038 | 7833.1 | 4795.1 | 158% |  |  | 0 | REPLACED EFC AND UPSIZED METER TO 16M ALSO WORKED TP AND MGRP WHILE ON SITE
20026928100 | 587 | EX | UPGRADE ELECTRONICS | 451 HARBISON RD | F | 3038 | 6063.75 | 3025.75 | 100% |  |  | 0 | REPLACED EFC
20026928200 | 587 | EX | UPGRADE ELECTRONICS | 1639 JAGGIE FOX WY | F | 3038 | 3460.63 | 422.63 | 14% |  |  | 0 | CMCHOLAN 7-14-2022 RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07-14-2022
20026928300 | 587 | EX | UPGRADE FROM 3G NETWORK | 800 ROSE ST RR | F | 3038 | 6815.37 | 3777.37 | 124% |  |  | 0 | RETIRED OLD EFC INSTALLED NEW EC350 CCOX 02-28-2022
20026928400 | 587 | EX | UPGRADE FROM 3G NETWORK | 454 FAIRMAN RD | F | 3038 | 3177.17 | 139.17 | 5% |  |  | 0 | RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07-14-2022
20026928500 | 587 | EX | UPGRADE ELECTRONICS | 2510 RESEARCH PARK DR | F | 3038 | 3667.3 | 629.3 | 21% |  |  | 0 | CWEMPE BLONE 7/19/22 RETIRED MINI-AT INSTALLED NEW EC350 CWEMPE 07-19-2022
20026928600 | 587 | EX | UPGRADE ELECTRONICS | 451 HARBISON RD | F | 5626 | 3158.07 | -2467.93 | -44% |  |  | 0 | RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON
20026928700 | 587 | EX | UPGRADE ELECTRONICS | 2250 LEESTOWN RD | F | 3038 | 8043.8 | 5005.8 | 165% |  |  | 0 | REPLACED EFC
20026928800 | 587 | EX | UPGRADE ELECTRONICS | 1310 CENTRE PY | F | 3038 | 6614.01 | 3576.01 | 118% |  |  | 0 | ASSIST SMCHOLAN 03-02-2022 RHAYES ASSIST SMCHOLAN 03-02-2022 RHAYES INSTALLED NEW EC350 SOAP TEST TUBING 5MIN OPP PRESSURE SMCHOLAN 3-2-22
20026933700 | 588 | EX | RETIRE ELECTRONICS | 310 S LIMESTONE ST | F | 73.3494 | 452.45 | 379.1006 | 517% |  |  | 0 | GAUGE RETIRED BY C. COX PAPPER WORK CO BY J. MULLINS 3-2-2022
20026933800 | 588 | EX | RETIRE ELECTRONICS | 451 HARBISON RD | F | 73.3494 | 0 | -73.3494 | 100% |  |  | 0 | REPLACED EFC
20026933900 | 588 | EX | RETIRE ELECTRONICS | 1639 JAGGIE FOX WY | F | 73.3494 | 1039.15 | 965.8006 | 1,317% |  |  | 0 | CMCHOLAN 7-14-2022 RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07142022
20026934000 | 588 | EX | RETIRE ELECTRONICS | 800 ROSE ST RR | F | 73.3494 | 626.57 | 553.2206 | 754% |  |  | 0 | RETIRED OLD EFC AND INSTALLED NEW EC350 CCOX 02-28-2022
20026934100 | 588 | EX | RETIRE ELECTRONICS | 454 FAIRMAN RD | F | 73.3494 | 189.27 | 115.9206 | 158% |  |  | 0 | RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07-14-2022
20026934200 | 588 | EX | RETIRE ELECTRONICS | 2510 RESEARCH PARK DR | F | 73.3494 | 502.89 | 429.5406 | 586% |  |  | 0 | CWEMPE BLONE 7/19/22 RETIRED OLD MINI-AT INSTALLED NEW EC350
20026934400 | 588 | EX | RETIRE ELECTRONICS | 2250 LEESTOWN RD | F | 73.3494 | 0 | -73.3494 | 100% |  |  | 0 | REPLACED EFC
20026934500 | 588 | EX | RETIRE ELECTRONICS | 1310 CENTRE PY | F | 73.3494 | 0 | -73.3494 | 100% |  |  | 0 | RETIRED MINI-AT INSTALLED NEW EC350 SMCHOLAN 3-2-22
20026940000 | 909 | EX | INSTALL I&C EQUIPMENT | 2005 VERSAILLES RD | F | 16155.4774 | 11589.34 | -4566.1374 | -28% |  |  | 0 | CCC# 43689 RETIRED PAPER CHART INSTALLED NEW ERX CCOX 02-24-2022
20026940100 | 584 | EX | RETIRE PAPER GUAGE | 2005 VERSAILLES RD | F | 91.4991 | 172.3 | 80.8009 | 88% |  |  | 0 | RETIRED PAPER CHART INSTALLED HONEYWELL ERX CCOX 2-24-2022
20026941400 | 909 | EX | INSTALL I&C EQUIPMENT | KENNESAW DR | F | 16155.4774 | 12022.54 | -4132.9374 | -26% |  |  | 0 | INSTALLED TAP ON OUTLET LEG OF RUN 1 20# SYSTEM AND RAN SENSE LINES TO ERX FROM THE NEW TAP AND EXISTING HP SENSE LINE, AND COMMISSIONED ERX CCC 75328, CMCHOLAN CCOX 7-28-2022
20026943300 | 909 | EX | INSTALL I&C EQUIPMENT | 1684 WAKEFIELD TR | F | 16155.4774 | 9146.19 | -7009.2874 | -43% |  |  | 0 | REMOVED BOTH PAPER CHARTS INSTALLED ERX FOR IP AND MP CMCHOLAN 4-14-2022 CC 65476 COMMISSIONED ERX RHAYES SMCHOLAN 05-03-2022 COMMITIONED ERX, PSP OK, CCC 65476 CMCHOLAN RHAYES 5-3-2022
20026943400 | 584 | EX | RETIRE GAUGE | 1684 WAKEFIELD TR | F | 91.4991 | 543.13 | 451.6309 | 494% |  |  | 0 | REMOVED BOTH PAPER CHARTS INSTALLED ERX CC 62655 RHAYES SMCHOLAN CCOX EBLANTON 04-14-2022
20026945201 | 555 | EX | INSTALL 5000' OF 2"PMMP MAIN | WALDORF LN LT 1 | B | 223484.8945 | 228201.9 | 4717.0055 | 2% | 5000 | 4938 | 46.2134 | INSTALLED 4938"020 PMMP.
20026951300 | 557 | EX | INSTALL 6200' OF 2"PMMP MAIN | 600 S LIMESTONE ST | B | 1180648.1173 | 1175556.48 | -5091.6373 | 0% | 6200 | 6324 | 185.8881
20026951400 | 558 | EX | RETIRE 7600' OF 4"CI/BSLP MAIN | 600 S LIMESTONE ST | B | 165.7874 | 142.7 | -23.0874 | -14% |  |  | 0
20026951802 | 557 | EX | INSTALL 3980' OF 2"PMMP MAIN | 250 S ASHLAND AV | B | 383869.9188 | 461944.16 | 78074.2412 | 20% | 3980 | 3755 | 123.0211 | TWALKER/KY 09-21-21: JOB OVER RUN DUE TO ADDITIONAL STREET AND HARD SURFACE REPAIR ADDED $70,000 TO CONTRACT COST AND SEGA WAS $7000 HIGHER THAN ESTIMA TE.
20026951900 | 558 | EX | RETIRE 2100' OF 4"CI/PLP MAIN | 250 S ASHLAND AV | B | 84.1799 | 0 | -84.1799 | 100% |  |  | 0
20026955503 | 561 | EX | INSTALL 2850'-8" CSHP | CLAYS MILL RD | B | 1308080.823 | 1263938.35 | -44142.473 | -3% | 2960 | 2894 | 436.7444
20026955600 | 562 | EX | RETIRE 6100'-8"/3" BS/CSHP | CLAYS MILL RD | B | 190.2592 | 142.7 | -47.5592 | -25% |  |  | 0
20026955701 | 561 | EX | INSTALL 3,945'-4"/2" PMMP | CLAYS MILL RD | B | 724040.648 | 702217.99 | -21822.658 | -3% | 3945 | 3942 | 178.1375
20026955800 | 562 | EX | RETIRE 216'-2" PMMP | CLAYS MILL RD | B | 85.5775 | 0 | -85.5775 | 100% |  |  | 0
20026955901 | 561 | EX | INSTALL 215'-4" PMMP | CLAYS MILL RD | B | 67929.8606 | 63490.92 | -4438.9406 | -7% | 215 | 309 | 205.4722
20026956000 | 562 | EX | RETIRE 820'-2" PMMP | CLAYS MILL RD | B | 85.0089 | 0 | -85.0089 | 100% |  |  | 0
20026956101 | 561 | EX | INSTALL 2475'-8"/6"/4" PMLP | CLAYS MILL RD | B | 1170137.3307 | 1344804.09 | 174666.7593 | 15% | 2383 | 2469 | 544.6756 | WIPE SAMPLE RESULTS WERE ENTERED ON THE INSTALL JOB INSTEAD OF THE RETIREMENT JOB. RETIREMENT RESULTS WERE ENTERED HERE.
20026956200 | 562 | EX | RETIRE 4775'-12">3"PM/BS/CSLP | CLAYS MILL RD | B | 85.5775 | 160 | 74.4225 | 87% |  |  | 0
20026961700 | 2000 | EX | ACQUIRE EASEMENT FOR HP MAIN | 2001 LAKESIDE DR | A | 5928 | 0 | -5928 | 100% |  |  | 0
20026966800 | 558 | EX | RETIRE 2800' OF 4"/6"BSLP MAIN | MARIEMONT DR | B | 90.1729 | 907.78 | 817.6071 | 907% |  |  | 0
20026969700 | 555 | EX | INSTALL 8500' OF 2"/4"PMMP MN | 299 SQUIRES CR | B | 301857.4038 | 270941.08 | -30916.3238 | -10% | 8500 | 6995 | 38.7335
20026971100 | 557 | EX | INSTALL 3300' OF 2"/4"PMMP MN | 167 WITTLAND LN | B | 877421.2279 | 755817.87 | -121603.3579 | -14% | 3300 | 3399 | 222.3648 | TWALKER/KY 05-04-22: JOB ORDER RUN DUE TO NO PAVING/HARD SURFACE REPAIRS HA VE BEEN STARTED AT THIS TIME. THIS IS JOINT PAVING RESTORATION WITH CITY OF LEXINGTON AND KY AMERICAN WATER. LOOK FOR COST TO BOOK LATE SUMMER 2022
20026971200 | 558 | EX | RETIRE 2100' OF 3"BSLP MAIN | 167 WITTLAND LN | B | 102.0836 | 1415.61 | 1313.5264 | 1,287% |  |  | 0
20026972201 | 555 | EX | INSTALL 3300' OF 2"/4" PMMP | MEADOW RIDGE DR LT1 | B | 89953.3001 | 84926.85 | -5026.4501 | -6% | 3300 | 3160 | 26.8756
20026975201 | 557 | EX | INSTALL 3000' OF 2"/4"PMMP | MANHATTAN DR | B | 552556.8312 | 630664.21 | 78107.3788 | 14% | 3000 | 3052 | 206.6396
20026975300 | 558 | EX | RETIRE 1900' OF 6"BSLP MAIN | MANHATTAN DR | B | 64.0836 | 1430.35 | 1366.2664 | 2,132% |  |  | 0
20026976301 | 557 | EX | INSTALL 6300' OF 2"/4"PMMP | CHENAULT RD | B | 2132943.4537 | 2104702.57 | -28240.8837 | -1% | 6000 | 6294 | 334.3982
20026976400 | 558 | EX | RETIRE 6100' OF 3"/4"BSLP MN | CHENAULT RD | B | 152.7248 | 1794.07 | 1641.3452 | 1,075% |  |  | 0
20026976501 | 557 | EX | INSTALL 4270' OF 2"/4"PMMP MN | E 6TH ST | B | 1522347.7868 | 1937333.59 | 414985.8032 | 27% | 4280 | 4323 | 448.1456 | WIPE SAMPLE RESULTS WERE ENTERED ON THE INSTALL JOB IN ERROR. WIPE RESULTS FOR THE RETIREMENT PIPE WERE ENTERED HERE. TWALKER/KY 01-24-23: JOB OVER RUN DUE TO ADDITIONAL STREET/HARD SURFACE REP AIRS REQUIRED BY CITY OF LEXINGTON. CONTRACT COST INCREASED BY $200,000 WITH PAVING/FLAGGING COST, SEGA WAS $73,000 HIGHER THAN PLANNED, ADDITIONAL $22,000 CHARGED FOR MATERIAL COST. TWALKER/KY 08-29-23: LEVEL 2 VARIANCE ADDED TO WMS.DOCS. JOB COST OVERRUN DUE TO ADDITIONAL STREET MILL/RE-PAVED COST REQUIRED BY CITY OF LEXINGTON.
20026976600 | 558 | EX | RETIRE 4650' OF 3"/4"BSLP MN | E 6TH ST | B | 56.8875 | 320 | 263.1125 | 463% |  |  | 0
20026977101 | 557 | EX | INSTALL 11,500' OF 2"/4"PMMP | TREMONT AV | B | 926814.1047 | 1143604.07 | 216789.9653 | 23% | 11500 | 11391 | 100.3954 | TWALKER/KY 03-02-22: PROJECT COST OVER RUN DUE TO ADDITIONAL CONSTRUCTION COORINATOR ON SITE DURING CONSTRUCTION ADDED $65,000 IN LABOR COST, SEWER VIDEO FOR MAIN/SL BY BUCHANAN WAS $86,000 HIGHER THAN ESTIMATE, ADDITIONAL FLAGGING AND HARD SURFACE REPAIRS ADDED $25,000 TO CONTRACT COST. FINALLY SEGA WAS $35,000 HIGHER THAT PLANNED COST.
20026977200 | 558 | EX | RETIRE 6900' OF 4"/6"BSLP MAIN | TREMONT AV | B | 76.6277 | 848.1 | 771.4723 | 1,007% |  |  | 0
20026981200 | 557 | EX | INSTALL 1550' OF 2"PMMP MAIN | M L KING | B | 414073.7744 | 479750.56 | 65676.7856 | 16% | 1550 | 1372 | 349.6724 | TWALKER/KY 05-04-22: JOB OVER RUN CAUSED BY ADDTIONAL $46,000 FOR SEWER CAMERA WORK, PROJECT TOOK LONGER TO COMPLETE DUE TO TRAFFIC AND URBAN SETTING INCREASED COMPANY LABOR BY $5000, SEGA $17000 HIGHER THAN ESTIMATE.
20026981300 | 558 | EX | RETIRE 1600' OF 2"/3"BSLP MAIN | M L KING | B | 84.1799 | 0 | -84.1799 | 100% |  |  | 0
20026982600 | 2000 | EX | INVESTIGATE AND DESIGN | BLUEGRASS AV |  | 30898 | 0 | -30898 | 100% |  |  | 0 | PS&I IS STILL BEING USED BY CONTRACT SURVEYOR AND ENGINEER DURING CONSTRUCT ION. BUT PRELIMINARY DESIGN AND SURVEY COMPLETED. D.LEMONS 8/19/2021
20026982700 | 561 | EX | INSTALL 4500'-2"&4" PMMP | BLUEGRASS AV | B | 959444.7901 | 885948.31 | -73496.4801 | -8% | 4471 | 4196 | 211.1412
20026982900 | 562 | EX | RETIRE 3700'-2&4" BSLP | BLUEGRASS AV | B | 88.8156 | 142.7 | 53.8844 | 61% |  |  | 0
20026984100 | 2000 | EX | INVESTIGATE R/W & EASEMENTS | GEORGETOWN PY |  | 3406 | 0 | -3406 | 100% |  |  | 0
20026984300 | 2000 | EX | INVESTIGATE HP EASEMENT | 629 ADDISON AV | B | 4748 | 0 | -4748 | 100% |  |  | 0
20026984400 | 561 | EX | INSTALL 949'-6" PMLP | LAFAYETTE PY | B | 204292.6769 | 282788.29 | 78495.6131 | 38% | 939 | 954 | 296.4238 | 14JUN21: OVERRRUN EXPLANATION = 1) REQUIRED FLAGGING WAS WAY UNDERESTIMATED AS $30K ADDITIONAL DOLLARS FOR FLAGGING WAS REQUIRED, 2) AN ADDITIONAL $10K IN DUST & STONE WAS REQUIRED, 3) THE 6" ROCK BORE WAS PAID ALL IN HEAVY ROCK WHEREAS IT WAS ESTIMATED 1/2 HEAVY AND 1/2 LIGHT WHICH CONTRIBUTED ANOTHER $8K TO THE OVERRUN,4) ADDITIONAL VAC EXCAVATION WAS REQUIRED ADDING $3K TO THE OVERRUN. THESE PLUS ADDITIONAL OH'S MAKE UP THE MAJORITY OF THE $57K OVERRUN (BKSLONE)
20026985200 | 561 | EX | INSTALL 6" PCF | 1060 WINBURN DR | B | 16280.811 | 9877.17 | -6403.641 | -39% |  |  | 0
20026985300 | 562 | EX | RETIRE 300'-6" CSMP | 1060 WINBURN DR | B | 88.4533 | 71.35 | -17.1033 | -19% |  |  | 0
20026985600 | 561 | EX | INSTALL 375' OF 2"CSHP MAIN | KING ST | B | 92169.2028 | 90203.73 | -1965.4728 | -2% | 375 | 401 | 224.947
20026985700 | 562 | EX | RETIRE 200' OF 2"CSHP MAIN | KING ST | B | 84.1794 | 62.95 | -21.2294 | -25% |  |  | 0
20026987500 | 555 | EX | INSTALL 300' OF 2"PMMP MAIN | 7020 ATHENS BOONESB RD | B | 19258.6597 | 18181.58 | -1077.0797 | -6% | 300 | 304 | 59.8078
20026987600 | 2000 | EX | CONFLICT ASSESMENT | RICHMOND RD |  | 11315.2615 | 0 | -11315.2615 | 100% |  |  | 0 | ALL RESEARCH AND DESIGN COMPLETE. D.LEMONS 1/29/2025
20026988100 | 555 | EX | INSTALL 525' OF 2"PMMP MAIN | BOBWHITE CT LT1 | B | 17405.4965 | 10228.67 | -7176.8265 | -41% | 525 | 501 | 20.4165
20026988300 | 562 | EX | RETIRE 1853'-4"/3" BS/CSMP | CLAYS MILL RD | B | 5110.2031 | 47.8 | -5062.4031 | -99% |  |  | 0
20026989600 | 561 | EX | INSTALL 40'-2" PMMP | 1631 OLD FRANKFORT PK | B | 30326.4153 | 36919.96 | 6593.5447 | 22% | 44 | 52 | 709.9992
20026989700 | 562 | EX | RETIRE 40'-2" CSMP | 1631 OLD FRANKFORT PK | B | 107.2796 | 0 | -107.2796 | 100% |  |  | 0
20026990200 | 2000 | EX | RELOCATION DESIGN - CONFLICT | KING ST | B | 6690 | 0 | -6690 | 100% |  |  | 0
20026990600 | 558 | EX | PAPER ONLY FOR CLOSE OUT | WALTON AV | B | 103.8156 | 0 | -103.8156 | 100% |  |  | 0
20026991100 | 563 | EX | INSTALL 100' OF 4"PMLP S/L | 1003 N LIMESTONE ST | B | 29024.9725 | 33764.98 | 4740.0075 | 16% | 101 |  | 0
20026991900 | 2000 | EX | INVESTIGATE ROAD RIGHT OF WAY | 1751 BRYAN STATION RD | A | 3224 | 0 | -3224 | 100% |  |  | 0
21026100800 | 575 | EX | ACQ GPL ESMT IN/OUT TO R-1035 | 2211 CLAYS MILL RD | F | 6845 | 19245.71 | 12400.71 | 181% |  |  | 0 | CHRIS DAVIS ACQUIRED NECESSARY EASEMENTS OFF OF WELCH AND SAUNIER (BKSLONE)
21026100900 | 557 | EX | EMER INSTALL 5'-4" PMMP | 600 OLD FRANKFORT CR | A | 15398.8131 | 49713.13 | 34314.3169 | 223% | 15 | 4 | 12428.2825 | RETIRED 4 FEET OF 4' PE MAIN LINE. REPLACED PEICE OF MAIN WITH NEW AND EF COUPLINGS. PRESSURE TESTED NEW PEICE OF MAIN FOR 1HR @ 90PSIG. TEST OK. SOAP TESTED FINALS CONNECTION @ OP. TEST, BHB, NGF. DMALONE 2/09/2021. OVERRUN EXPLANATION: UNEXPECTED CONTRACT COST OF $35,000 WAS NOT PLANNED, JO ORIGINALLY PLANNED FOR COMPANY CREW BUT WAS EXECUTED BY A CONTRACT CREW, COMPANY CREWS ALSO CHARGED 183 HOURS TO PROJECT
21026101000 | 558 | EX | EMER RETIRE 5'-4" PMP D222468 | 600 OLD FRANKFORT CR | A | 69.6296 | 10.95 | -58.6796 | -84% |  |  | 0 | RETIRED 4 FEET OF 4' PE MAIN LINE. REPLACED PEICE OF MAIN WITH NEW AND EF COUPLINGS. PRESSURE TESTED NEW PEICE OF MAIN FOR 1HR @ 90PSIG. TEST OK. SOAP TESTED FINAL CONNECTION @ OP. TEST OK. BHB. NGF. DMALONE 2/09/2021 OVERRUN EXPLANATION: THIS RETIREMENT JOB ORDER WAS ESTIMATED IN THE ORDINAR Y MANNER FOR JUST 1 HOUR; HOWEVER, THERE WERE NO PROPERTY UNITS INSTALLED S O THE JOB WAS WORKED AS AN ABANDONMENT WITH ALL THE LABOR AND CONTRACT COST S BEING APPLIED TO THE RETIREMENT. THE INSTALL JOB ORDER WAS EXECUTED WITH AN HOUR OF LABOR.
21026101100 | 575 | EX | ACQ ESMT ON 556 ROSEMONT GDN | 556 ROSEMONT GN | F | 5169 | 6675.64 | 1506.64 | 29% |  |  | 0 | 27APR21: CHRIS DAVIS COMPLETED AND ACQUIRED THREE SEPARATE EASEMENTS OFF OF ROSEMONT BAPTIST CHURCH.
21026101400 | 2000 | EX | INVESTIGATE MAINS | WOODHILL DR |  | 17276 | 0 | -17276 | 100% |  |  | 0 | PS&I BEING EXECUTED TO CAPITOL JO. PROJECT EXPECTED TO START MID JULY 2021 . D.LEMONS 6/10/2021
21026101501 | 561 | EX | INSTALL 3800'-2",4"&6" PMMP | WOODHILL DR | B | 710294.4849 | 842479.02 | 132184.5351 | 19% | 3957 | 4530 | 185.9777 | OVERRUN EXPLANATION: ENCOUNTERED MORE ROCK EXCAVATION THAN ESTIMATED AS WEL L AS THE ASSOCATED SPECIAL BACKFILL. PROJECT ALSO REQUIRED MORE SEWER CAMER A WORK THAN ESTIMATED.
21026101600 | 562 | EX | RETIRE 1200'-2"&4" BSMP | WOODHILL DR | B | 85.0089 | 325.85 | 240.8411 | 283% |  |  | 0
21026102600 | 2000 | EX | INVESTIGATE ENCROACHMENT | 375 STONE RD |  | 694 | 0 | -694 | 100% |  |  | 0
21026102800 | 2000 | EX | INVESTIGATE ENCROACMENT | 1081 E NEW CIRCLE RD |  | 694 | 0 | -694 | 100% |  |  | 0
21026102900 | 555 | EX | INSTALL 2400' OF 4"PMMP MAIN | 928 ENTERPRISE CT | B | 80646.5708 | 104251.17 | 23604.5992 | 29% | 2400 | 2371 | 43.9693
21026103700 | 2000 | EX | INVESTIGATE FACILITIES | THUNDERSTICK DR |  | 6855 | 0 | -6855 | 100% |  |  | 0 | INVESTIGATION COMPLETED, AND NO DIRECT CONFLICT WITH PROPOSED SEWER FACILIT IES. HAVE REQUESTED TO BE INVITED TO ANY PRECONSTRUCTION MEETING TO TALK TO CONTRACTOR ABOUT INSTALATION PRACTICES. D.LEMONS 3/11/2021
21026104400 | 559 | EX | INSTALL 2"SS TO RETIRE INLET | 1311 RICHMOND RD | B | 37406.9466 | 24511.65 | -12895.2966 | -34% |  |  | 0
21026104500 | 560 | EX | RETIRE 7' OF 2"BSMP MAIN | 1311 RICHMOND RD | B | 80.8842 | 72.67 | -8.2142 | -10% |  |  | 0
21026104600 | 584 | EX | RETIRE PIT REG STATION 1016 | 1311 RICHMOND RD | F | 138142.7376 | 188917.56 | 50774.8224 | 37% |  |  | 0 | REMOVED MONITOR AND CONTROL REG. AND BLIND FLANGED, MONITORED 30 MIN. DUE TO NOT BEING ABLE TO BLIND FLANGE BYPASS, ADVISED CONSTRUCTION ABOUT BYPASS CCC 20355 CMCHOLAN RHAYES NGINTER BLONE 4-23-2021 REGULATORS REMOVED AND BLIND FLANGED ON 4/23/2021 PIPING AND VAULT ABANDONED AND REMOVED BY CONSTRUCTION ON 5/12/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 5/14/2021 GCCC TICKET NOT REQUIRED ON 5/14/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS TWALKER/KY 11-15-21: LEVEL 2 VARIANCE FORM ADDED TO WMS.DOCS. JOB OVER RUN DUE TO $41,500 FROM LP/OPP MATERIAL CHARGED TO THIS ORDER. ADDITIONAL $11,000 IN COMPANY HIGHER THAN PLANNED ESTIMATE.
21026105201 | 577 | EX | INSTALL CHAIN LINK FENCE | BRIAR HILL RD | F | 78948.1342 | 84349.67 | 5401.5358 | 7% |  |  | 0 | FENCE INSTALL COMPLETE APARKS 04-19-23 1600 CCC#24962
21026105300 | 2000 | EX | INVESTIGATE EASEMENT | 2397 RICHMOND RD | B | 1270 | 0 | -1270 | 100% |  |  | 0
21026105401 | 555 | EX | INSTALL 6520' OF 6"PMMP MAIN | 2000 POLO CLUB BV | B | 403346.5487 | 427430.93 | 24084.3813 | 6% | 6325 | 6542 | 65.3364
21026105900 | 557 | EX | EMER INSTALL 5' OF 4"PMMP MAIN | 916 BRAVINGTON WY | A | 24731.5705 | 12908.51 | -11823.0605 | -48% | 5 | 10 | 1290.851 | TWALKER/KY-04-20-21: I HAVE ADDED A SIGNED PRESSURE TEST TO APPROVE THE 20 MIN PRESSURE TEST TO WMS.DOCS WORKSPACE.
21026106000 | 558 | EX | EMER RETIRE 5' OF 4"PAMP MAIN | 916 BRAVINGTON WY | A | 82.208 | 0 | -82.208 | 100% |  |  | 0
21026106100 | 555 | EX | INSTALL 1350' OF 2"/4"PMMP | PIERO WY LT1 | B | 45765.0925 | 39665.6 | -6099.4925 | -13% | 1350 | 1514 | 26.1992 | STANLEY PIPELNE INSTALLED MAIN
21026106200 | 559 | EX | INSTALL 6" PCF | 1965 FAIR OAKS DR | B | 16594.9062 | 13429.76 | -3165.1462 | -19% |  |  | 0 | INSTALLED 6"SST
21026106300 | 560 | EX | RETIRE 575'-6" BSLP | 1965 FAIR OAKS DR | B | 88.4533 | 1068.93 | 980.4767 | 1,108% |  |  | 0 | ABANDONED 640'060 CSLP
21026107700 | 557 | EX | INSTALL 20' OF 8"PMLP MAIN | 856 ALBANY ST | A | 12704.2275 | 8482.5 | -4221.7275 | -33% | 20 | 36 | 235.625 | REPLACED 36' OF S LP MAON W/ 8" P PER TIE-IN PLAN AND GAS STANDARDS. SOAP TEST TIE-IN COUPLINGS NO LEAKS. BHB NGF. MAIN PTOS READ -0.482 INST 2 9LB ANODES.
21026107800 | 558 | EX | RETIRE 20' OF 8" BSLP | 856 ALBANY ST | A | 56.3197 | 8727.02 | 8670.7003 | 15,395% |  |  | 0 | ABN 36' OF 8" S LP MAIN AND REPLACE WITH 8" P PER GAS STANDARDS AND TIE-IN PLAN. WORKED W/ 557 JOB# 21026107700. MCRAIG 4/14/21
21026107900 | 557 | EX | INSTALL 10' OF 3" PMLP | 329 OHIO ST | A | 13301.2275 | 7671.47 | -5629.7575 | -42% | 10 | 23 | 333.5422 | ABANDONED 23' OF 030 S MAIN.DUE TO ATMOS CORR INSTALLED 23' OF 030 PLASTIC WORKED WITH TIE IN PLAN AND GAS STANDARD. BHB NGF. INSTALLED TWO TEST STATIONS AND TWO ANODED.DESNO WRAPPED STEEL MAIN.
21026108000 | 558 | EX | RETIRE 10' OF 3" BSLP | 329 OHIO ST | A | 79.3197 | 8414.88 | 8335.5603 | 10,509% |  |  | 0 | ABANDONED 23' OF 030 S MAIN.DUE TO ATMOS CORR INSTALLED 23' OF 030 PLASTIC WORKED WITH TIE IN PLAN AND GAS STANDARD. BHB NGF. INSTALLED TWO TEST STATIONS AND TWO ANODED.DESNO WRAPPED STEEL MAIN.
21026108100 | 557 | EX | INSTALL 20' OF 3" PMMP | 619 CHINOE RD | B | 21676.4521 | 70757.52 | 49081.0679 | 226% | 20 | 314 | 225.3424 | AWEBER/KY 09/21/2021: PROXIMITY OF LP MAIN TO MP MAIN RESULTED IN AN ACTUAL FOOTAGE INSTALL OF 320'-PMMP IN ORDER TO SEPERATE AND INSTALL FITTINGS AS NEEDED. UNABLE TO REVISE WMS JO DUE TO UNPAID MATERIAL INVOICES AND JO COMP LETION STATUS AT THE TIME.
21026108200 | 558 | EX | RETIRE 20' OF 3" BSMP | 619 CHINOE RD | B | 56.3197 | 4.6 | -51.7197 | -92% |  |  | 0
21026108600 | 557 | EX | EMER-INSTAL 5'-2" PMMP | 2434 SEINE | A | 5147.5997 | 116.02 | -5031.5797 | -98% | 5 | 5 | 23.204 | INSTALLED 5' OF TEST 2" PMMP, SOAP TEST TIE IN, NO LEAKS, BHB NGF TIE OVER 2 SERVICE LINES, ON 3-5-21 DMEDLEY 3-8-21
21026108700 | 558 | EX | EMER - RETIRE 5'-2" PAMP | SEINE | A | 85.3307 | 4796.8 | 4711.4693 | 5,521% |  |  | 0 | INSTALLED GAUGE TEE, SQUEEZE OFF 2" PL MAIN, ABN 5' 2"PMP MAIN PER DLEMONS EMER DESIGN PLAN. WORKED ON 3-5-21, DMEDLEY 3-8-21
21026108801 | 555 | EX | INSTALL 1000' OF 2"PMMP MAIN | 551 VINCENT WY | B | 46147.0126 | 51597.09 | 5450.0774 | 12% | 1000 | 847 | 60.9175
21026108900 | 575 | EX | ACQUIRE EASEMENT | 796 DELLA DR | F | 6767 | 13632.99 | 6865.99 | 101% |  |  | 0 | CHRIS DAVIS ACQUIRED EASEMENT OFF OF 796 DELLA DR (KUBIAK)
21026109300 | 555 | EX | INSTALL 300' OF 2"PMMP MAIN | 801 NANDINO BV | B | 25871.1277 | 26886.16 | 1015.0323 | 4% | 300 | 278 | 96.7128
21026109900 | 562 | EX | RETIRE 2155'-4"/3" BS/PMLP | WOODBINE & REED | B | 343.31 | 3173.92 | 2830.61 | 825% |  |  | 0
21026110100 | 555 | EX | INSTALL 900' OF 2"PMMP MAIN | LAFONTAINE CT | B | 26234.9875 | 24183.42 | -2051.5675 | -8% | 900 | 887 | 27.2643
21026110400 | 561 | EX | INSTALL 100'-12" CSMP | 576 E THIRD ST | B | 142453.0552 | 188696.44 | 46243.3848 | 32% | 100 | 127 | 1485.7987 | OVERRUN EXPLANATION: PROJECT OVERRAN DUE TO FLAGGER TIME AND FLAGGER OVERTI ME. BUDGET VARIANCE EXPLANATION FORM LOADED INTO WMSDOCS WORKSPACE. D.LEMONS 12 /3/2021
21026110500 | 562 | EX | RETIRE 94'-12" CSMP | 576 E THIRD ST | B | 85.5775 | 142.7 | 57.1225 | 67% |  |  | 0
21026110600 | 562 | EX | RETIRE 600'-2&3" PMLP | 611 WINCHESTER RD | B | 21928.4488 | 701.12 | -21227.3288 | -97% |  |  | 0
21026110700 | 585 | EX | REPLACE FENCE | 1511 RUSSELL CAVE RD | F | 14980.1771 | 480.98 | -14499.1971 | -97% |  |  | 0 | CCC# 33097 - BLONE - 07/29/21 FENCE REPLACED BY INTERSTATE FENCE COMPANY PAPERWORK COMPLETED BY CYNTHIA FARIS ON 12/17/2021
21026110800 | 586 | EX | RETIRE FENCE | 1511 RUSSELL CAVE RD | F | 61.2976 | 0 | -61.2976 | 100% |  |  | 0 | FENCE REPLACED BY INTERSTATE FENCE COMPANY PAPERWORK COMPLETED BY CYNTHIA FARIS 12/17/2021
21026111101 | 585 | EX | INSTALL FENCE | 834 E 3RD ST | F | 40000.9906 | 5601.7 | -34399.2906 | -86% |  |  | 0 | CCC# 31858 , 31996 , 32095 , 32237 , 32396 , 32702 ALL USED DURING PROJECT BLONE - 07/29/21 FENCE INSTALLED BY INTERSTATE FENCE COMPANY PAPERWORK COMPLETED BY CYNTHIA FARIS 12/16/21 UNDERRUN EXPLANATION: THE COST ESTIMATE THAT THE CONTRACTOR PROVIDED TURNED OUT TO BE SIGNIFICANTLY LESS THAN THEY HAD ESTIMATED. GES 3/2/22
21026111200 | 586 | EX | RETIRE FENCE | 834 E 3RD ST | F | 61.2976 | 0 | -61.2976 | 100% |  |  | 0 | FENCE REPLACED BY INTERSTATE FENCE COMPANY PAPERWORK COMPLETED BY CYNTHIA FARIS 12/16/21
21026112000 | 2000 | EX | CONFLICT ASSESSMENT - RELOCATE | 1180 NEWTOWN PK | B | 19090 | 0 | -19090 | 100% |  |  | 0
21026112100 | 561 | EX | INSTALL 1025'- 2"/4"PHHP MAIN | 1180 NEWTOWN PK | B | 194441.8822 | 192775.66 | -1666.2222 | -1% | 1005 | 986 | 195.5128
21026112200 | 562 | EX | RETIRE 980' OF 4"CSHP MAIN | 1180 NEWTOWN PK | B | 74.8797 | 723.52 | 648.6403 | 866% |  |  | 0
21026112300 | 563 | EX | INSTALL 180' OF 4"PMMP S/L | 2000 POLO CLUB BV LT1 | B | 28556.5857 | 24370.71 | -4185.8757 | -15% | 180 |  | 0
21026112400 | 587 | EX | INSTALL NEW GMB SETTING | 2000 POLO CLUB BV | F | 57016.3076 | 55082.19 | -1934.1176 | -3% |  |  | 0 | INSTALLED NEW GMB SKID MOUNTED METER AND REGULATOR SETTING AJPARKS 8-22-202 2 PSID 501306155
21026112700 | 555 | EX | INSTALL 350' OF 2"PMIP MAIN | 3405 FLEETWOOD DR | B | 19281.66 | 37226.93 | 17945.27 | 93% | 350 | 365 | 101.9916
21026113000 | 557 | EX | EMER - INSTALL 60' OF 4"PMLP | 235 E NEW CIRCLE RD | A | 12530.1178 | 2022.21 | -10507.9078 | -84% | 60 | 54 | 37.4483 | INSTALLED 54' OF 040 PLASTIC DUE TO STEEL ATMOS CORR. BAGGED OFF MAIN, RETIRED 54' 040 STEEL.WORKED WITH TIE IN PLAN AND CAPITAL PACKET.INSTALLED TWO TEST STATIONS. BHB NGF. KKINDER
21026113100 | 558 | EX | EMER - RETIRE 60' OF 4"BSLP | 235 E NEW CIRCLE RD | A | 57.8842 | 1338.57 | 1280.6858 | 2,212% |  |  | 0 | ABADONED 54' OF S LP DUE TO ATMOS CORR. WORKED WITH 557. BAGGED OFF MAIN WORKED WITH TIE IN PLAN. KKINDER
21026113600 | 584 | EX | RETIRE INLET/OUTLET BLK VALVES | 361 PRICE RD | F | 88.1542 | 0 | -88.1542 | 100% |  |  | 0 | JOB COMPLETED BY WADE SHIMFESSEL ON 7/19/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/21/21 GCCC TICKET NOT REQUIRED ON 7/21/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026113701 | 561 | EX | INSTALL 4030' - 4"/2" PMMP | CLAYS MILL RD | B | 778460.4875 | 862366.14 | 83905.6525 | 11% | 4030 | 4412 | 195.4592
21026114500 | 584 | EX | RETIRE PIT REG STATION# 1024 | 300 E MAXWELL ST | F | 149437.1771 | 195061.46 | 45624.2829 | 31% |  |  | 0 | REMOVED 2 441 REGS AND BLIND FLANGED VALVES, STATION RETIRED, CMCHOLAN CCOX RHAYES 5-12-2022 RWILLIAMS COMPLETED PAPER WORK TWALKER/KY 11-30-22: JOB OVER RUN WAS DUE TO COST FOR 20-0269890-00 (2000) WITH LAND SERVICE AND CONTRACT ENG COST OF $65000, 19-0268950-00 (0001) MATERIAL FOR LPP MATERIAL OF $84000 AND 18-0268465-00 (2000) LAND SERVICES FOR LPP PROJECT APPROV $45000 FROM PROJECT MANAGEMENT AND GTMR GROUPS.
21026114600 | 2000 | EX | LAND SERVICE - EASEMENT | 928 ENTERPRISE CT | A | 1750 | 0 | -1750 | 100% |  |  | 0
21026115700 | 555 | EX | INSTALL 300' OF 2"PMMP MAIN | 341 MEIJER WY | B | 22097.6064 | 21541.85 | -555.7564 | -3% | 300 | 347 | 62.0803
21026117000 | 2000 | EX | RESEARCH EASEMENT & R/W | 800 S LIMESTONE ST | B | 10508 | 0 | -10508 | 100% |  |  | 0
21026117800 | 562 | EX | RETIRE 117' - 4" PLP | CLAYS MILL RD | B | 9954.0712 | 11604.62 | 1650.5488 | 17% |  |  | 0 | ABN 102' OF 040 PL ML. TESTED 4' OF 040 W/ END CAPS FOR 1 HR @ 90# SOAP TESTED CONN PTS @ 11" WC. SOAP TESTED ALL TEE CAP AND END CAPS @ OP.
21026117900 | 555 | EX | INSTALL 575' OF 2"PMIP MAIN | WINNERS CR LT28 | B | 17428.325 | 15668.74 | -1759.585 | -10% | 575 | 484 | 32.3734 | TWALKER/KY 06-28-21: THIS 555 WAS COMPLETED IN THE FIELD BUT PAPERWORK NOT COMPLETED OR MAPPED WHEN A CONTRACTOR DAMAGED A SECTION OF THIS NEW GAS MAIN. ALL WORK AND COST INCLUDED IN THIS JOB ORDER AND THE REASON FOR TWO TIE IN PLANS AND TEST FORMS.
21026118200 | 575 | EX | ACQUIRE EASEMENT | 1608 CLAYS MILL RD | F | 4170 | 7902.64 | 3732.64 | 90% |  |  | 0
21026118300 | 555 | EX | INSTALL 210' OF 2"PMMP MAIN | 637 ELK LAKE DR | B | 16739.4681 | 17888.9 | 1149.4319 | 7% | 210 | 225 | 79.5062
21026118400 | 2000 | EX | SURVEY REG STATION LOT | 834 E 3RD ST |  | 1221.6818 | 0 | -1221.6818 | 100% |  |  | 0
21026118500 | 562 | EX | RETIRE 3,256' 10"-3" CS/BS/PLP | CLAYS MILL RD | B | 151.2005 | 42.9 | -108.3005 | -72% |  |  | 0
21026118600 | 555 | EX | INSTALL 600' OF 2"PMMP MAIN | 955 TARR TC | B | 37159.65 | 65051.29 | 27891.64 | 75% | 600 | 527 | 123.437
21026118700 | 557 | EX | EMER-INSTALL 2' OF 2"PMMP MAIN | 621 CARDIFF LN | A | 4434.6174 | 2106.1 | -2328.5174 | -53% | 2 | 2 | 1053.05 | REFERENCE JOB# 21906644500 FOR COMMENTS AND JOB INFO DMARSTO 4/27/21
21026118800 | 558 | EX | EMER-RETIRE 2' OF 2"PAMP MAIN | 621 CARDIFF LN | A | 78.808 | 755.09 | 676.282 | 858% |  |  | 0 | REFERENCE JOB# 21906644500 FOR COMMENTS AND JOB INFO DMARSTO 4/27/21
21026120700 | 584 | EX | RETIRE REG STATION 1002 | 1706 CLAYS MILL RD | F | 5235.8425 | 6481.89 | 1246.0475 | 24% |  |  | 0 | CC# 48634 CMCOX 12/15/21 STATION RETIRED BY CHRIS COX AND CONSTRUCTION SERVICES PAPERWORK COMPLETED BY CYNTHIA FARIS ON 12/27/21
21026120800 | 584 | EX | RETIRE HP/MP RUN-1 OF R-1035 | 2209 CLAYS MILL RD | F | 21706.5276 | 827.14 | -20879.3876 | -96% |  |  | 0 | HP TO MP RUN 1 HAS BEEN RETIRED AND LP RUN 2 HAS BEEN PLACED BACK INTO SERVICE WORKED COMPLETED ON 11/3/2021 BY CHRIS COX PAPERWORK COMPLETED BY CYNTHIA FARIS ON 11/29/2021 GCCC TICKET NOT REQUIRED ON 11/29/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026122000 | 555 | EX | INSTALL 2150' OF 2"PMMP MAIN | WALDORF LN LT7 | B | 162365.3384 | 178403.1 | 16037.7616 | 10% | 2150 | 2331 | 76.535
21026122200 | 555 | EX | INSTALL 925' OF 2"PMMP MAIN | LONGRIDGE DR LT25 | B | 32784.4942 | 41992.33 | 9207.8358 | 28% | 925 | 934 | 44.9597 | TWALKER/KY 06-28-21: THIS 555 PROJECT WAS COMPLETED IN FIELD BUT PAPERWORK NOT SUBMITTED TO CLOSE OR MAPPEND WHEN LEAK ON THE NEW MAIN WAS DETECTED. WE BELIEVE THE MAIN LINE WAS DAMAGED DURING BACK FIELD. LEAK WAS REPAIRED BY CONSTRUCTION THAT IS REASON FOR TWO TIE IN PLANS AND TEST FORMS.ALL COST AND WORK CAPTURED UNDER THIS JOB ORDER.
21026122500 | 557 | EX | EMER-INSTALL 5' OF 4"PMLP MAIN | 473 WEST SECOND ST | A | 6150.5343 | 9606.89 | 3456.3557 | 56% | 5 | 5 | 1921.378 | CONTRACTOR HIT 040 PLASTIC MAIN WITH EXCAVATOR. SQUEEZED OFF TO MAKE SAFE. REPLACED 5FT OF 040 P LP. TESTED MAIN FOR 20MINS AT 90LBS.TEST OK.SOAP TEST FINAL TIE INS AT OP. TEST OK.BHB NGF.WORKED WITH CAPITAL JO AND TIE IN PLAN TWALKER/KY 06-28-21: THIS PROJECT WAS GENERATED FROM 3RD PARTY DAMAGE FROM A CONTRACTOR REPLACING STORM/SEWER AT THE INTERSECTION OF MILLER AND 2ND ST. CONTRACTOR DAMAGE SMALL OF MAIN FIRST DAY AND THE VERY NEXT DAY HIT/DA MAGE THE REPAIR MAIN. THAT MAIN WAS NEVER BOOKED OR MAPPED IN WMS. ALL WORK AND COST CAPTURED ON THIS JOB ORDER. WE HAVE TWO TIE INS AND TEST.
21026122600 | 558 | EX | EMER-RETIRE 5' OF 4"PMLP MAIN | 473 WEST SECOND ST | A | 78.808 | 19.8 | -59.008 | -75% |  |  | 0 | CONTRACTOR HIT 040 PLASTIC MAIN WITH EXCAVATOR. SQUEEZED OFF TO MAKE SAFE. REPLACED 5FT OF 040 P LP. TESTED MAIN FOR 20MINS AT 90LBS.TEST OK.SOAP TEST FINAL TIE INS AT OP. TEST OK.BHB NGF.WORKED WITH CAPITAL JO AND TIE IN PLAN
21026122700 | 557 | EX | EMEG-INSTALL 5' OF 4"PMMP MAIN | 3941 MORNING GLORY LN | A | 5607.5343 | 3856.8 | -1750.7343 | -31% | 5 | 2 | 1928.4 | RESPONDED OT MAIN LINE DAMAGE. INSTALLED 2' OF 4" PE MAIN LINE. PRESSURE TESTED MAIN @ 90PSIG FOR 20MINS PER FOL APPROVAL. TEST OK. SOAP TESTED LAST CONNECTION @ OP. TEST OK. CONTENT VERIFIED. PRESSURE VERIFIED @ 52PSIG DMAL
21026122800 | 558 | EX | EMER-RETIRE 5' OF 4"PMMP MAIN | 3941 MORNING GLORY LN | A | 78.808 | 210.25 | 131.442 | 167% |  |  | 0 | RESPONDED TO MAIN LINE DAMAGE. INSTALLED 2' OF 4" PE MAIN LINE. PRESSURE TESTED MAIN @ 90PSIG. FOR 20MINS PER FOL APPROVAL. TEST OK. SOAP TESTED FINAL CONNECTION @ OP. TEST OK. CONTENT VERIFIED. VERIFIED PRESSURE @52PSIG
21026122900 | 559 | EX | INSTALL 8" SS | 1005 RICHMOND RD | B | 30904.4019 | 48788.62 | 17884.2181 | 58% |  | 4 | 12197.155
21026124400 | 559 | EX | EMER-INSTALL 2' OF 2"PMMP | GALATA DRIVE | A | 2935.5264 | 1470.21 | -1465.3164 | -50% | 2 | 2 | 735.105
21026124500 | 560 | EX | EMER-RETIRE 2' OF 2"PMMP | GALATA DRIVE | A | 85.0408 | 0 | -85.0408 | 100% |  |  | 0
21026124600 | 559 | EX | INSTALL 3" OUTLET VALVE | PRICE RD | B | 34892.3468 | 28606.82 | -6285.5268 | -18% | 4 | 12 | 2383.9017
21026124700 | 560 | EX | RETIRE 4' OF 3"BSIP MAIN | PRICE RD | B | 86.5975 | 0 | -86.5975 | 100% |  |  | 0
21026124800 | 583 | EX | INSTALL INLET/OUTLET BLOCK VLV | 361 PRICE RD | F | 13873.2524 | 20343.89 | 6470.6376 | 47% |  |  | 0 | CCC# 30839 CCC# 31113 CCC# 31169 IN PROGRESS CCC# 31169 CC# 31169 CC-31326 CC-31492 CCC# 31755 CC-31755 NOT ON SITE- OFFICE ISO UPDATE CAP WORK COMPLETED BY WADE SHIMFESSEL ON 7/19/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/21/20 GCCC TICKET NOT REQUIRED ON 7/21/20 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS 7/21/20
21026125400 | 561 | EX | INSTALL 28' 4" PMMP | 2601 CLAYS MILL RD | B | 10969.2814 | 20147.11 | 9177.8286 | 84% | 28 | 37 | 544.5165
21026125500 | 562 | EX | RETIRE 20' OF 4" PMMP | 2601 CLAYS MILL RD | B | 91.2676 | 0 | -91.2676 | 100% |  |  | 0
21026125600 | 561 | EX | INSTALL 28' 8" PMLP | 2601 CLAYS MILL RD | B | 11805.2814 | 23277.54 | 11472.2586 | 97% | 28 | 33 | 705.38
21026125700 | 562 | EX | RETIRE 20' 8" PMLP | 2601 CLAYS MILL RD | B | 91.2676 | 71.35 | -19.9176 | -22% |  |  | 0
21026125800 | 557 | EX | REPLACE C18-5 E | 1005 RICHMOND RD | B | 77241.44 | 96855.51 | 19614.07 | 25% | 37 | 34 | 2848.6915
21026125900 | 558 | EX | RETIRE C18-5 | 1005 RICHMOND RD | B | 91.2676 | 38.57 | -52.6976 | -58% |  |  | 0
21026126102 | 557 | EX | INSTALL 2000' OF 2"PMMP MAIN | 1850 MERCER RD | B | 165212.1661 | 169255.42 | 4043.2539 | 2% | 2000 | 2017 | 83.9144
21026126200 | 558 | EX | RETIRE 270' OF 1"BSHP MAIN | 1850 MERCER RD | B | 63.0891 | 0 | -63.0891 | 100% |  |  | 0
21026126300 | 2000 | EX | INVESTIGATE R/W AND EASEMENTS | 1847 MERCER RD | A | 7043 | 0 | -7043 | 100% |  |  | 0
21026126600 | 584 | EX | RETIRE REG STATION #1181 | 427 TRANSPORT CT | F | 4088.2989 | 1370.38 | -2717.9189 | -66% |  |  | 0 | RWILLIAMS COMPLETED PAPER WORK, EBLANTON RETIRED STATION ON 04/29/2022
21026126700 | 561 | EX | INSTALL 350' OF 2" PMMP | 1501 RUSSELL CAVE RD | B | 123612.3972 | 99374.93 | -24237.4672 | -20% | 350 | 348 | 285.5601
21026126800 | 557 | EX | INSTALL 11,170' OF 2"/6"PMMP | MENTELLE PR | B | 1492284.9718 | 1675598.92 | 183313.9482 | 12% | 11170 | 10916 | 153.4994
21026126900 | 558 | EX | RETIRE 9000' OF 4"/6"BSLP MAIN | MENTELLE PR | B | 62.0792 | 24.95 | -37.1292 | -60% |  |  | 0
21026128000 | 561 | EX | INSTALL 265' OF 4" PMLP | 118 E NEW CIRCLE RD | B | 71153.2979 | 96077.32 | 24924.0221 | 35% | 265 | 163 | 589.4314 | AWEBER - JO RAN OVER ESTIMATE DUE TO UNFORSEEN 8'X5' STORM BASIN @ 42" BELO W GRADE. EXCAVATION OF TOP OF BASIN OCCURRED TO PROVIDE REROUTE OF 4" PMMP INSTALL AT ACCEPTABLE DEPTH WITHOUT CROSSBORE.
21026128100 | 562 | EX | RETIRE 230'-4" & 50'-6" PMLP | 118 E NEW CIRCLE RD | B | 354.2624 | 71.35 | -282.9124 | -80% |  |  | 0
21026128300 | 0001 | EX | DOCUMENT PRESSURE INCREASES | MASON HEADLEY RD | B | 5085.0408 | 0 | -5085.0408 | 100% |  |  | 0 | TWALKER/KY 07-14-21: THIS JOB ORDER DOCUMENTED PRESSURE INCREASES ONLY FOR AN EXISTING 60PSIG SYSTEM THAT HAD BEEN SET AT 30PSIG FOR 20+ YEARS PRESSURE RAISED TO 42PSIG. THIS PROCESS IS PART OF THE CLAY MILL ROAD RELOCATION PROJECT AND IS NOT AN UPRATE.
21026128400 | 2000 | EX | INVESTIGATE MAINS & SERVICES | ARMSTRONG MILL | B | 21541 | 0 | -21541 | 100% |  |  | 0 | PS&I COMPLETED AND EXECUTED TO 561 JO. D.LEMONS 10/6/2021
21026128601 | 555 | EX | INSTALL 700' OF 2"PMMP MAIN | 3492 JACOB CT | B | 57445.0039 | 75716.28 | 18271.2761 | 32% | 700 | 862 | 87.8379
21026128700 | 584 | EX | RETIRE HP/MP REG RUN | 785 CHERYL LN | F | 4148.6042 | 3741.83 | -406.7742 | -10% |  |  | 0 | HP/MP RUN RETIRED BY CHRIS COX ON 11/9/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 11/18/2021 GCCC TICKET NOT REQUIRED ON 11/18/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026128802 | 557 | EX | INSTALL 470' OF 4"PMMP MAIN | 1119 COOPER | B | 96528.8129 | 106230.58 | 9701.7671 | 10% | 470 | 462 | 229.9363
21026128900 | 558 | EX | RETIRE 440' OF 4"BSMP MAIN | 1119 COOPER | B | 67.1085 | 30.93 | -36.1785 | -54% |  |  | 0 | X
21026129000 | 558 | EX | RETIRE 680'-4"BSLP MN -D247885 | 1119 COOPER DR | B | 67.1085 | 0 | -67.1085 | 100% |  |  | 0
21026129400 | 562 | EX | RETIRE 135' OF 8"CSMP MAIN | 1983 HARRODSBURG RD | B | 151.2005 | 1142.2 | 990.9995 | 655% |  |  | 0 | ABN 135' ON CS MP MAIN.
21026129500 | 562 | EX | RETIRE 109' OF 4"BSLP | 1983 HARRODSBURG RD | B | 99.3208 | 71.35 | -27.9708 | -28% |  |  | 0 | ABN 4" BS LP MAIN PER GS
21026129600 | 557 | EX | INSTALL 100' OF 8"PMMP MAIN | 249 WALTON AV | B | 99233.0142 | 152586.55 | 53353.5358 | 54% | 104 | 53 | 2878.9915 | TWALKER/KY 01-24-23: JOB ORDER OVER RUN DUE TO ADDITIONAL FLAGGING ADDED $50,000 TO CONTRACT COST, SEGA INCREASED BY $6,000 AND CO LABOR COST HIGHER BY $14,000 LEVEL 2 VARIANCE ADDED TO WMS.DOCS.
21026129700 | 558 | EX | RETIRE 20' OF 8"BSMP MAIN | 249 WALTON AV | B | 79.203 | 1960.6 | 1881.397 | 2,375% |  |  | 0
21026129900 | 584 | EX | RETIRE PIT REG STATION W/AMRP | 800 PRESS AV | F | 4706.4362 | 3639 | -1067.4362 | -23% |  |  | 0 | RETIRED 800 PRESS AVE 200340, CMCHOLAN 11-16-22
21026130600 | 555 | EX | INSTALL 350' OF 2"PMMP MAIN | 600 LAKE CLAIR CT | B | 31312.2411 | 42649.02 | 11336.7789 | 36% | 350 | 461 | 92.5141
21026130902 | 555 | EX | INSTALL 5150' OF 2"/4" PMMP | CATTLE PH LT46 | B | 202239.5285 | 192645.27 | -9594.2585 | -5% | 4750 | 5599 | 34.4071
21026132400 | 555 | EX | INSTALL 225' OF 2"PMMP | 200 W VINE ST GENERAT | B | 79492.8479 | 85412.94 | 5920.0921 | 7% | 225 | 201 | 424.94 | TTALKER/KY 01-25-23: JOB IS SHOWING COST UNDER RUN AT THIS TIME BUT PAVING/ STREET REPAIRS NOT TAKE PLACE UNTIL SPRING/WARM WEATHER. TWALKER/KY 06-23-23: JOB ORDER CURRENTLY UNDER RUNNING $32000 BUT STREET PAVING HAS NOT BEEN COMPLETED AT THIS TIME DUE TO DOWNTOWN AREA AND CONSTRU CTION BY OTHERS IN AREA. TWALKER/KY 07-21-23: PAVING HAS BEEN COMPLETED AND COST APPLIED TO JOB ORDE R, NOT OVER OR UNDER BUDGET VARIANCE REQUIRED AT THIS TIME. PAVING WAS DELAYED TO COLD AND WET WEATHER PLUS THIS PROJECT IS LOCATED IN DOWNTOWN AREA SO PERMIT RESTRICTION APPLIED.
21026132500 | 555 | EX | INSTALL 450' OF 2"PMMP MAIN | 3326 GRASMERE DR | B | 32348.6064 | 31237.4 | -1111.2064 | -3% | 450 | 278 | 112.3647
21026134100 | 555 | EX | INSTALL 850' OF 2"PMMP MAIN | 196 TURNER COMMONS WY BLG 35 | B | 40949.6064 | 28285.71 | -12663.8964 | -31% | 850 | 561 | 50.4202
21026134200 | 2000 | EX | INVESTIGATE MAINS |  |  | 21078 | 0 | -21078 | 100% |  |  | 0
21026134800 | 559 | EX | INSTALL 20'-2" PMMP | 694 BISHOP DR | B | 39141.4028 | 67370.23 | 28228.8272 | 72% | 14 | 22 | 3062.2832
21026134900 | 560 | EX | RETIRE 16'-2" CSMP | 694 BISHOP DR | B | 88.8156 | 0 | -88.8156 | 100% |  |  | 0
21026135200 | 2000 | EX | INVESTIGATE HP ENCROACHMENT | 3021 BROOKMONTE LN | B | 5000 | 0 | -5000 | 100% |  |  | 0 | AWEBER 8/21/23 - JO CHARGED TO O&M, LAND WORK REQUIRED FOR ENCROACHMENT INV ESTIGATION.
21026135700 | 2000 | EX | INVESTIGATE ENCROACHMENTS | 260 OLD MOUNT TABOR RD 1 | B | 6526 | 0 | -6526 | 100% |  |  | 0
21026136000 | 2000 | EX | RAILROAD CROSSING & R/W | SHROPSHIRE |  | 3013 | 0 | -3013 | 100% |  |  | 0
21026136100 | 557 | EX | EMER-INSTALL 10'-2" PMMP | 345 PEACHTREE RD | A | 5241.7163 | 3664.07 | -1577.6463 | -30% | 10 | 2 | 1832.035
21026136200 | 558 | EX | EMER-RETIRE 10'-2" PMP | 345 PEACHTREE RD | A | 88.8156 | 253.41 | 164.5944 | 185% |  |  | 0 | RETIRED 2' OF DAMAGED 2" PMP MAIN
21026136500 | 561 | EX | RELOCATE 12' OF 4"PMLP MAIN | 2914 CLAYS MILL RD | B | 10466.234 | 25628.84 | 15162.606 | 145% | 10 | 7 | 3661.2629
21026136600 | 562 | EX | RETIRE 6' OF 4"PMLP MAIN | 2914 CLAYS MILL RD | B | 85.7248 | 0 | -85.7248 | 100% |  |  | 0
21026136800 | 557 | EX | EMER-INSTALL 5' OF 4"PMMP | 1246 CENTRE PY | A | 5949.1348 | 395.9 | -5553.2348 | -93% | 5 | 5 | 79.18 | INST 5' 4" P MP MAIN ACCORDING TO ENGINEERED TIE-IN PLAN AND GAS STANDARDS. WORKED ON 8/17/21. MCRAIG 8/24/21
21026136900 | 558 | EX | EMER-RETIRE 5' OF 4"PAMP | 1246 CENTRE PY | A | 55.634 | 5438.98 | 5383.346 | 9,676% |  |  | 0 | ABN 5' 4"P MP MAIN ACCORDING TO ENGINEERED TIE-IN PLAN. WORKED ON 8/17/21. MCRAIG 8/24/21
21026137100 | 560 | EX | RETIRE 4'-8" BSLP | 1005 RICHMOND RD | B | 177.6312 | 0 | -177.6312 | 100% |  |  | 0
21026137200 | 2000 | EX | INVESTIGATE UTILITY EASEMENT | 2350 WINCHESTER RD | B | 5000 | 0 | -5000 | 100% |  |  | 0 | AWEBER 11/3/2023 - EXECUTING LAND PS&I FOR 2350 WINCHESTER RD, LEX. WORK TO DETERMINE EASEMENTS FOR NEW SUBDIVISION ON SIR BARTON WAY IS COMPLETED PER CBOWLIN.
21026137500 | 909 | EX | INSTALL SOLAR PANEL | 707 LANE ALLEN RD | F | 4862.234 | 3598.81 | -1263.424 | -26% |  |  | 0 | CC# 41497 RHAYES 10-13-2021 RHAYES 10-13-2021 CHANGED ER350 FROM CRY IN TO FULL TIME MONITOR INSTALLED SUPER SOLAR KIT AN D RV 50 MODEM CCOX 10-13-2021
21026140400 | 555 | EX | INSTALL 2800' OF 2"/4"PMMP | ANGUS TL LT40 | B | 86592.9986 | 116146.05 | 29553.0514 | 34% | 2800 | 2971 | 39.0933
21026140901 | 555 | EX | INSTALL 2750' OF 2"PMMP MAIN | BACKSTRETCH LT30 | B | 96941.3864 | 104070.68 | 7129.2936 | 7% | 2750 | 2640 | 39.4207
21026141200 | 557 | EX | EMER-INSTALL 3'OF 6"PMLP MAIN | 855 CHARLES AV | A | 4022.0999 | 5901.09 | 1878.9901 | 47% | 3 | 3 | 1967.03
21026141300 | 558 | EX | EMER-RETIRE 3' OF 6"PLP MAIN | 855 CHARLES AV | A | 69.8875 | 38.15 | -31.7375 | -45% |  |  | 0
21026141400 | 561 | EX | INSTALL 130'-6" PMMP | ARMSTRONG MILL RD | B | 140177.264 | 179014.36 | 38837.096 | 28% | 136 | 211 | 848.4093 | PROJECT OVERRUN OF $38,555 (28%) DUE TO ADDITIONAL TIME AND RESOURCES BEING REQUIRED. LABOR HOURS ESTIMATED AT 176 HRS, BUT 319 HRS WERE REQUIRED ($11 ,052 DIFF. LABOR RATE ESTIMTES TOO LOW). NEW CONTRACT WILL ADDITIONAL UNITS WAS USED WHICH ADDED $57,948. BUT THERE WERE SAVINGS OF $30,000 IN THE OT HER CATAGORY, WHICH WERE COVERED WITH UNITS IN THE UPDATED CONTRACT. D.LEMO NS 7/8/2022
21026141500 | 562 | EX | RETIRE 316'-6" PM&CS MP | ARMSTRONG MILL RD | B | 76.2083 | 4123.73 | 4047.5217 | 5,311% |  |  | 0
21026141600 | 561 | EX | INSTALL 320' OF 2"PMMP MAIN | 240 CANARY RD | B | 52296.0917 | 51396.03 | -900.0617 | -2% | 320 | 322 | 159.615
21026141700 | 562 | EX | RETIRE 315' OF 2"PMP MAIN | 240 CANARY RD | B | 60.6987 | 46.05 | -14.6487 | -24% |  |  | 0
21026141800 | 2000 | EX | RELOCATION DESIGN IN EASEMENT | 240 CANARY RD | B | 6917 | 0 | -6917 | 100% |  |  | 0
21026142200 | 555 | EX | INSTALL 575' OF 2"PMMP MAIN | SNOWY EGRET WY LT109 | B | 20915.4686 | 25446.02 | 4530.5514 | 22% | 550 | 727 | 35.0014
21026142500 | 557 | EX | EMER-INSTALL 5' OF 2"PMMP | 962 CHARWOOD DR | A | 3297.6583 | 417.14 | -2880.5183 | -87% | 5 | 5 | 83.428
21026142600 | 558 | EX | EMER-RETIRE 5' OF 2"PMP MAIN | 962 CHARWOOD DR | A | 69.8875 | 263.29 | 193.4025 | 277% |  |  | 0
21026143000 | 588 | EX | RETIRE EME FACILITY | 767 WINCHESTER RD | F | 63.4597 | 0 | -63.4597 | 100% |  |  | 0 | REPLACED EFC
21026143400 | 557 | EX | EMER-INSTALL 10'OF 4"PMIP MAIN | CARLETON DR | A | 7432.5408 | 7913.03 | 480.4892 | 6% | 10 | 6 | 1318.8383
21026143500 | 558 | EX | EMER-RETIRE 10' OF 4"PAIP MAIN | CARLETON DR | A | 60.6987 | 0 | -60.6987 | 100% |  |  | 0
21026143600 | 2000 | EX | INVESTIGATE MAINS & R/W |  |  | 47385 | 0 | -47385 | 100% |  |  | 0
21026143900 | 557 | EX | EMER-INSTALL 5'-2"PMMP | 535 LAKETOWER DR | A | 6000.6188 | 0 | -6000.6188 | 100% | 5 | 5 | 0
21026144000 | 558 | EX | EMER-RETIRE 5'-2"PMMP | 535 LAKETOWER DR | A | 49.6987 | 0 | -49.6987 | 100% |  |  | 0
21026144100 | 555 | EX | INSTALL 350' OF 2"PMIP MAIN | WINNERS CR LT9 | B | 20004.6217 | 19720.01 | -284.6117 | -1% | 350 | 360 | 54.7778
21026144200 | 560 | EX | RETIRE 4280' OF 2"/3"PAMP MAIN | VALLEY FARM DR | A | 14091.9275 | 41269.58 | 27177.6525 | 193% |  |  | 0 | ABN 4280' P MP MAIN IN ACCORDNANCE WITH ENGINEERED TIE-IN PLAN AND GAS STANDARDS. SOAP TEST FINAL TIE-IN AT OP OK. BHB NGF. MCRAIG 10/13/21 TWALKER/KY 11-24-21: WMS WOULD NOT ALLOW FOR REVISION DUE TO UNPAID INVOICES, JOB ORDER OVER RUN DUE TO SCOPE OF WORK INCREASED AND WE RETIRED MORE UNLOCATED FIRST GENERATION PLASTIC MAIN THAN PLANNED AND SOME NEW EMPLOYEES WORKED WITH CREWS WITH INCREASED LABOR COST BY $14,000 OVER ESTIMATE
21026145500 | 2000 | EX | INVESTIGATE NEW CIRC SMRP | 450 E NEW CIRCLE RD | B | 17684 | 0 | -17684 | 100% |  |  | 0
21026145601 | 557 | EX | INSTALL 1885' - 4" PMMP MAIN | 450 E NEW CIRCLE RD | B | 712573.3764 | 816623.03 | 104049.6536 | 15% | 2000 | 1874 | 435.7647 | JOB COMPLETE
21026145700 | 558 | EX | RETIRE 1840' OF 4" BSMP | 450 E NEW CIRCLE RD | B | 100.2728 | 110 | 9.7272 | 10% |  |  | 0 | JOB COMPLETE
21026146000 | 557 | EX | INSTALL 404'-4"&6"PMMP | EUCLID AV | A | 224207.9887 | 125105.39 | -99102.5987 | -44% | 405 | 395 | 316.7225 | LEVEL 2 BUDGET VARIANCE EXPLANATION FORM HAS BEEN APPROVED AND LOADED INTO WMSDOCS WORKSPACE. D.LEMONS 3/3/2022
21026146100 | 558 | EX | RETIRE 427'-4"BSLP | EUCLID AV | A | 63.4597 | 1537.36 | 1473.9003 | 2,323% |  |  | 0
21026147000 | 0001 | EX | DOCUMENT DOWNRATE 32010119 | TRANSPORT CT | A | 60.6987 | 0 | -60.6987 | 100% |  |  | 0 | TWALKER/KY-SEE JOB 21-0261261-00 FOR NEW MAIN LINE AND REG STATION RETIRED.
21026147100 | 557 | EX | EMER-INSTALL 6' OF 4"PMMP | 383 LANCELOT LN | A | 1045.4141 | 604.21 | -441.2041 | -42% | 6 | 5 | 120.842
21026147200 | 558 | EX | EMER-RETIRE 6' OF 4"PAMP MAIN | 383 LANCELOT LN | A | 49.6987 | 38.59 | -11.1087 | -22% |  |  | 0
21026147900 | 559 | EX | EMER - INSTALL 5'-4" PMLP | 732 WHITNEY AV | A | 2422.8089 | 3691.18 | 1268.3711 | 52% | 5 | 3 | 1230.3933 | INSTALLED 3FT OF 040 PLASTIC DUE TO 3 TEE'S BEING AN AOC. ALL TESTING INFO ON JO 21026147900 AND 21026148000 IN WMS DOCS.
21026148000 | 560 | EX | EMER - RETIRE 5'-4" PLP | 732 WHITNEY AV | A | 66.2207 | 4.38 | -61.8407 | -93% |  |  | 0 | INSTALLED 3FT OF 040 PLASTIC DUE TO 3 TEE'S BEING AN AOC. ALL TESTING INFO ON JO 21026147900 AND 21026148000 IN WMS DOCS.
21026148100 | 557 | EX | EMER-INSTALL 4' OF 2"HPHP MAIN | 1450 NEWTOWN PK | A | 7370.71 | 2019.57 | -5351.14 | -73% | 4 | 7 | 288.51
21026148200 | 558 | EX | EMER-RETIRE 4' OF 2"HDHP MAIN | 1450 NEWTOWN PK | A | 60.6987 | 0 | -60.6987 | 100% |  |  | 0
21026150300 | 2000 | EX | INVESTIGATE CONFLICTS |  |  | 9460 | 0 | -9460 | 100% |  |  | 0 | PS&I COMPLETED FOR DESIGN. CONSTRUCTION WAS POSTPONED UNTIL 2023. D.LEMONS 11/22/2022
21026150400 | 2000 | EX | INVESTIGATE CONFLICTS |  |  | 16069 | 0 | -16069 | 100% |  |  | 0 | INVESTIGATION AND DESIGN COMPLETE. D.LEMONS 5/2/2022
21026151100 | 2000 | EX | INVESTIGATE MAINS & SERVICES | GREENTREE |  | 27112 | 0 | -27112 | 100% |  |  | 0
21026151200 | 561 | EX | INSTALL 2065'-2"&6" PMMP | GREENTREE | B | 333722.7132 | 493527.08 | 159804.3668 | 48% | 2075 | 2224 | 221.9097
21026151300 | 562 | EX | RETIRE 2111'-2"&6" CSMP | GREENTREE | B | 109.7476 | 80 | -29.7476 | -27% |  |  | 0
21026151500 | 557 | EX | EMER-INSTALL 10' OF 4"PMMP | 3102 KIRKLEVINGTON DR | A | 5220.9567 | 210.64 | -5010.3167 | -96% | 10 | 3 | 70.2133 | LEAK ON SF CPLG ON TEE OF SVC TO 3102 KIRKLEVINGTON DR. DPI D221947 CLEARED ON 2212. ABN/INST 3'- 4" P MAIN ACCORDING TO GAS STANDARDS AND ENGINEERED TIE-IN PLAN. WORKED 11/17/21 MCRAIG
21026151600 | 558 | EX | EMER-RETIRE 10' OF 4"PAMP | 3102 KIRKLEVINGTON DR | A | 64.6591 | 24.42 | -40.2391 | -62% |  |  | 0 | LEAK ON SF COUPLING ON TEE TO SVC OF 3102 KIRKLEVINGTON DR. DPI D221947 CLEARED ON 2212. ABN/ INST 3'- 4" P MAIN ACCORDING TO GAS STANDARDS AND ENGINEERED TIE-IN PLAN. WORKED 11/17/24 MCRAIG
21026152101 | 557 | EX | INSTALL 535' OF 8"CSHP MAIN | 629 ADDISON AV | B | 444968.002 | 480960.85 | 35992.848 | 8% |  | 554 | 868.1604
21026152200 | 558 | EX | RETIRE 457' OF 6 5/8"BSHP MAIN | 629 ADDISON AV | B | 74.2578 | 1859.99 | 1785.7322 | 2,405% |  |  | 0
21026155900 | 555 | EX | INSTALL 2400' OF 2"PMMP MAIN | 272 SQUIRES CR | B | 61211.3642 | 72846.65 | 11635.2858 | 19% | 2400 | 2508 | 29.0457
21026156700 | 559 | EX | INSTALL 20'-3 PMMP | 3030 LAKECREST CIR | B | 12546.0469 | 13109.07 | 563.0231 | 4% | 20 | 23 | 569.9596
21026156800 | 560 | EX | ABDN CB 12'-3" PMP | 3030 LAKECREST CIR | B | 73.9724 | 0 | -73.9724 | 100% |  |  | 0
21026156900 | 559 | EX | INSTALL 10'-6" PMLP | APPOMATTOX RD | A | 14786.2791 | 6980.82 | -7805.4591 | -53% | 10 | 4 | 1745.205 | INSTALLATION COMPLETE, HMCKUNE
21026157000 | 560 | EX | RETIRE 10'-6" PMLP | APPOMATTOX RD | A | 72.8047 | 0 | -72.8047 | 100% |  |  | 0
21026993800 | 557 | EX | INSTALL 7200' OF 2"/6"PMMP | 456 E HIGH ST | B | 2229015.8617 | 3013391.75 | 784375.8883 | 35% | 7200 | 7402 | 407.1051
21026993900 | 558 | EX | RETIRE 9500' OF 4"CI/6"BSLP MN | 456 E HIGH ST | B | 80.3582 | 5876.52 | 5796.1618 | 7,213% |  |  | 0 | ABANDONED ALL MAINS IN SCOPE OF PROJECT
21026994000 | 557 | EX | INSTALL 10930 - 2"/4"PMMP MAIN | STATE ST | B | 1953601.844 | 1681569.14 | -272032.704 | -14% | 10930 | 10169 | 165.3623 | TWALKER/KY 05-22-23: PROJECT CURRENTLY UNDER RUNNING, WAITING ON FINAL RESTORATION/PAVING TO DETERMINE IF ADDITIONAL EXPLAINATION OR VARIANCE REQU IRED. TWALKER/KY 06-23-23: JOB UNDER RUNNING DUE TO PAVING/HARD SURFACES REPAIRS HAVE NOT BEEN FULLY COMPLETED. TWALKER/KY 07-24-23: PAVING/HARD SURFACE REPAIRS STILL IN PROGRESS TWALKER/KY 08-29-23: LEVEL 1 VARIANCE FORM ADDED IN WMS.DOCS NOT SURE IF ALL PAVING INVOICES HAVE BEEN PAID BUT COST UNDER RUN DRIVEN BY LESS PAVING COST BY PAVING CONTRACTOR INSTEAD OF PIPELINE CO.
21026994100 | 558 | EX | RETIRE 14,600 - 4"CI/BSLP MAIN | STATE ST | B | 84.1794 | 269.51 | 185.3306 | 220% |  |  | 0
21026994300 | 575 | EX | DOCUMENT HP EASEMENT | 2001 LAKESIDE DR | F | 6229.6196 | 5365.64 | -863.9796 | -14% |  |  | 0 | TWALKER/KY 01-22-21: THIS JOB ORDER TO SET ADDITIONAL EASEMENT FOR EXISTING 12"HP GAS MAIN AT 2001 LAKESIDE DRIVE (FROM PS&I 20-0269617-00) COPY OF EASEMENT DRAWING IN WMS.DOCS AND RW# 592684.
21026994600 | 557 | EX | EMER INSTALL 5'-4" PMMP | 2218 BAHAMA RD | A | 5854.5805 | 4622.23 | -1232.3505 | -21% | 35 | 5 | 924.446 | REPLACED 5 FT MAIN TEST 90 LB FOR 20 MIN TEST ALL TEES AT 5 MIN TEST BYPASS 90 LB FOR 1 HR TEST ALL END CAPS AT OP FOR 5 MIN BAR HOLE BANKS NO GAS FOUND MARKER BALL AT TEES AND CPLG
21026994700 | 558 | EX | EMER - RETIRE 5'-4" PMP | 2218 BAHAMA | A | 103.8156 | 102.95 | -0.86559 | -1% |  |  | 0 | CUT OUT CRACKED MAIN PUT ON BYPASS AND PUT IN 5 FT OF MAIN
21026996200 | 561 | EX | INSTALL 2150'-2" PMMP | REED LN | B | 214604.887 | 336530.83 | 121925.943 | 57% | 2154 | 2005 | 167.8458 | JOB ORDER CODED COMPLETE AT TIME OF MAIN LINE COMPLETION, STILL WORKING ON SERVICES. SPENDLE 3/10/21 20APR21: SEVERAL ATTEMPTS WERE MADE TO REVISE THIS JOB ORDER TO CAPTURE OVERRUN, HOWEVER, OUTSTANDING INVOICES PREVENTED ENGINEERING FROM DOING SO. . 29APR21: OVERRUN EXPLANATION = FISHEL'S CONTRACT OVER $21K DUE TO INCREASED LABOR & MATERIALS TO PREP STAGING (STONE, FENCING, AND ENVIRONMENTAL BMPS) ALONG WITH A LOT MORE FLAGGING BY AWP FOR TRAFFIC CONTROL. BUCHANAN'S COST FOR SEWER INSPECTION & CAMERING WAS WAY UNDERESTIMATED CONTRIBUTING ANOTHER $33K TO THE OVERRUN. LASTLY, COMPANY LABOR OVERRAN BY $14K FROM WHAT WAS ORIGINALY ESTIMATED. THESE COSTS PLUS OH'S MAKE UP THE OVERRUN (BKSLONE).
21026996400 | 558 | EX | EMER - ABANDON 37'-2" PIP | 4035 WHITEMARK CT | A | 2872.6664 | 860.91 | -2011.7564 | -70% |  |  | 0 | ABANDONED 37' OF 020 MAIN DUE TO FAC DAM. WORKED WITH TIE IN PLAN. INSTALLED LINE MARKER AT EOM. UPDATED MAPPING. SOAP TEST END CAP AT OP.TEST OK. BHB NGF.
21026997000 | 561 | EX | INSTALL 1100'-2" PMP | WOODBINE DR | B | 340896.6283 | 532822.99 | 191926.3617 | 56% | 1104 | 1140 | 467.3886 | 14JUN21: UNDERRUN EXPLANATION = 1) ASPHALT MILL & OVERLAY WAS MISCALCULATED RESULTING IN AN ADDITIONAL $120K AND 2) FLAGGING TIME WAS UNDERESTIMATED RESULTING IN AND ADDITIONAL $35K. THESE COSTS, ALONG WITH ASSOCIATED OH'S, MAKE UP THE MAJORITY IF THE $166K OVERRUN. THE ERROR IN PAVING COSTS WAS NOT NOTICED UNTIL AFTER THE ORIGINAL JOB ORDER WAS EXECUTED THEREBY PROHIBITING PROCESSING A REVISION (BKSLONE).
21026997101 | 561 | EX | INSTALL 125' OF 4"PMMP MAIN | 1983 HARRODSBURG RD REAR | B | 111178.7891 | 118779.98 | 7601.1909 | 7% | 123 | 125 | 950.2398
21026997500 | 2000 | EX | OBTAIN EASEMENTS FOR NEW MAIN | DEER HAVEN LN | B | 8502 | 0 | -8502 | 100% |  |  | 0
21026997801 | 557 | EX | INSTALL 4600' OF 2"/6"PMMP | E 4TH ST | B | 2229421.3209 | 2405348.07 | 175926.7491 | 8% | 4061 | 4887 | 492.1932
21026997900 | 558 | EX | RETIRE 6300' OF 4"/6"CILP MN | E 4TH ST | B | 126.9534 | 747.19 | 620.2366 | 489% |  |  | 0
21026998000 | 587 | EX | CONVERT TO GMB ACCOUNT | 699 BYRD THURMAN DR | F | 4845.4443 | 6412.15 | 1566.7057 | 32% |  |  | 0 | CONVERTED FROM CAB TO GMB ACCOUNT CCC TICKET NOT REQUIRED THIS IS NON-SCADA MONITORED
21026998100 | 555 | EX | INSTALL 180' OF 2"PMMP MAIN | 2708 MABLE LN LT123 | B | 11159.7406 | 36764.99 | 25605.2494 | 229% | 180 | 198 | 185.6818
21026998900 | 566 | EX | RETIRE 3"PLP SERVICE LINE | 437 RACE ST | B | 9329.0565 | 9085.7 | -243.3565 | -3% |  |  | 0
21026999500 | 555 | EX | INSTALL 175' OF 2"PMMP | 776 LONGWOOD RD | B | 9497.8185 | 16309.78 | 6811.9615 | 72% | 175 | 174 | 93.7344 | 174 '2"PLASTIC MED -DENSITY YELLOW PIPE INSTALLED BY BIRECTIONAL BOREBY STA NLEY PIPELINE.
21026999600 | 561 | EX | INSTALL 90' OF 4"CS/PMMP MAIN | FAIRCREST DR | B | 68922.5327 | 47302.77 | -21619.7627 | -31% | 90 | 98 | 482.6813 | NEW MAIN GASED UP 11-11-21
21026999900 | 2000 | EX | PERFORM CONFLICT ASSESSMENT | W NEW CIRCLE RD | B | 1792 | 0 | -1792 | 100% |  |  | 0 | EXPOSURES ON NEW CIRCLE FOR ENGINEERING; 4 EXPOSURES VIA HYDRO EXCAVATION; JNEWSOME ORDER FOR HYDRO EXCAVATION COMPLETED BY JNEWSOME ON 05/13/21 EXPOSURES ON NEW CIRCLE FOR ENGINEERING; 4 EXPOSURES VIA HYDRO EXCAVATION; JNEWSOME
22026158400 | 555 | EX | INSTALL 1200' OF 2"PMMP MAIN | MARLENA LN LT139 | B | 35742.3291 | 29132.57 | -6609.7591 | -18% | 1200 | 1137 | 25.6223
22026158800 | 557 | EX | INSTALL 540' OF 4"/8"PMMP MAIN | WALTON AV | B | 262444.8259 | 378932.24 | 116487.4141 | 44% | 540 | 553 | 685.2301 | TWALKER/KY 09-27-23: LEVEL 1 VARIANCE FORM ADDED TO WMS.DOCS JOB OVER RUN DUE TO ADDITIONAL PAVING/RESTORATION REQUIREMENT BY THE CITY INCREASED CONTRACT COST BY $30,000, ALSO SEGA $12,000 HIGHER THAN ESTIMATE. COMPANY LABOR INCREASED BY $25,000 DUE TO ADDITIONAL COMPANY LABOR REQUIRED. TWALKER/KY 10-27-23: LEVEL 2 VARIANCE REPORTED ADDED TO WMS.DOCS, JOB OVER DUE TO CITY PAVING AND RE-PAVING REQUIREMENT.
22026158900 | 558 | EX | RETIRE 594' OF 8"BSMP MAIN | WALTON AV | B | 72.8047 | 0 | -72.8047 | 100% |  |  | 0
22026159301 | 2000 | EX | SURVEY FOR RELEASE OF EASEMENT | TOWN CENTER DR |  | 1000 | 0 | -1000 | 100% |  |  | 0
22026160800 | 557 | EX | EMER-INSTALL 5' OF 2"PMMP MAIN | COLCHESTER RD | A | 3947.9695 | 2109.29 | -1838.6795 | -47% | 5 | 5 | 421.858
22026160900 | 558 | EX | EMER-RETIRE 5' OF 2"PAMP MAIN | COLCHESTER | A | 69.6571 | 0 | -69.6571 | 100% |  |  | 0
22026162000 | 560 | EX | RETIRE 110' OF 2"CSHP MAIN | DEER HAVEN DR | B | 105.0102 | 716.93 | 611.9198 | 583% |  |  | 0
22026162102 | 557 | EX | INSTALL 8150' OF 2"/4"PMMP | BERRY LN | B | 751182.165 | 756346.06 | 5163.895 | 1% | 8150 | 7928 | 95.4019
22026162200 | 558 | EX | RETIRE 4600' OF 4"/6"BSLP MAIN | BERRY LN | B | 105.0102 | 1442.96 | 1337.9498 | 1,274% |  |  | 0
22026162500 | 561 | EX | INSTALL 8" STOPPLE FITTING | SPORTS CENTER DR | B | 14352.6857 | 25751.7 | 11399.0143 | 79% |  |  | 0
22026162600 | 562 | EX | RETIRE 44' OF 8"BSMP MAIN | SPORTS CENTER DR | B | 105.0102 | 0 | -105.0102 | 100% |  |  | 0
22026163200 | 557 | EX | INSTALL 775' OF 2"PMMP MAIN | PARKWAY DR | B | 80533.8181 | 49762.97 | -30770.8481 | -38% | 775 | 702 | 70.8874 | TWALKER/KY- 09-27-23: LEVEL 1 VARIANCE ADDED TO WMS.DOCS JOB UNDER RUN WAS DUE TO NO FLAGGING OR STREET REPAIRS REQUIRED SINCE ALL MAIN WAS INSTALLED BY DIRECTIONAL BORE WHICH LOWER CONTRACT COST $23,000
22026163300 | 558 | EX | RETIRE 800' OF 4"BSLP MAIN | PARKWAY DR | B | 105.0102 | 21.45 | -83.5602 | -80% |  |  | 0
22026163700 | 566 | EX | RETIRE 4"BSLP SERVICE LINE | 125 BARR ST PARISH | B | 105.0102 | 1327.16 | 1222.1498 | 1,164% |  |  | 0 | CAPITAL SERVICE LINE WAS ABANDONED WITH JOB NUMBER 18-0268433-01 TIE IN A1A2. LSHARON
22026163900 | 2000 | EX | CONFLICT ASSESSMENT | 1200 S BROADWAY ST 101 | B | 2275 | 0 | -2275 | 100% |  |  | 0
22026164400 | 557 | EX | EMER - INSTALL 10'-2" PMMP | ANTIGUA DR | A | 13748.6188 | 10363.46 | -3385.1588 | -25% | 10 | 7 | 1480.4943
22026164500 | 558 | EX | EMER - RETIRE 10'-2" PMP | ANTIGUA DR | A | 109.7476 | 111.44 | 1.6924 | 2% |  |  | 0
22026164900 | 557 | EX | EMER-INSTALL 4' OF 3"PMMP MAIN | TATES CREEK | A | 14982.0392 | 15536.92 | 554.8808 | 4% | 4 | 4 | 3884.23 | INSTALLED 4' OF 030 P DUE TO EXC DMG TEST AT 90# FOR 20 MIN PER FOL APPROVA L, SOAP TEST TWO 030 EF CPLGS AT OP FOR 5 MIN OK. TEST FOR SEC DMG OK. WHIMES 02/17/2022
22026165000 | 558 | EX | EMER-RETIRE 4' OF 3"PMP MAIN | TATES CREEK | A | 100.2728 | 119.3 | 19.0272 | 19% |  |  | 0 | COMPLETED W/ JO 22026164900
22026165400 | 584 | EX | RETIRE REG STATION #1203 | 1321 BIG POND CR | F | 4576.607 | 5686.24 | 1109.633 | 24% |  |  | 0 | STATION RETIRED ALL PIPEING REMOVED 06-22-2022 AJPARKS
22026165501 | 557 | EX | INSTALL 3385' OF 2" PMMP | CHEROKEE PK | B | 345650.6876 | 347952.13 | 2301.4424 | 1% | 4080 | 3336 | 104.3022
22026165600 | 558 | EX | RETIRE 2715'-BSLP & 425'-PLP | CHEROKEE PK | B | 75.4968 | 1766 | 1690.5032 | 2,239% |  |  | 0
22026165700 | 2000 | EX | INVESTIGATE ROAD ROW | CHEROKEE PK | B | 7194 | 0 | -7194 | 100% |  |  | 0
22026166200 | 561 | EX | INSTALL 20' OF 3"PMMP MAIN | 1200 S BROADWAY ST | B | 28323.8584 | 23237.34 | -5086.5184 | -18% | 20 | 14 | 1659.81
22026166300 | 562 | EX | RETIRE 12' OF 3"PMP MAIN | 1200 S BROADWAY ST | B | 62.3079 | 90.73 | 28.4221 | 46% |  |  | 0
22026166900 | 557 | EX | INSTALL 2010' - 8" & 6" PMMP | 1814 RICHMOND RD | B | 400337.2549 | 525084.39 | 124747.1351 | 31% | 2010 | 1910 | 274.9133
22026167000 | 558 | EX | RETIRE 2260' OF 4-8" BSLP | RICHMOND RD | B | 89.0305 | 0 | -89.0305 | 100% |  |  | 0
22026167100 | 2000 | EX | INVESTIGATE ROAD ROW | RICHMOND RD | B | 4587 | 0 | -4587 | 100% |  |  | 0
22026167200 | 557 | EX | INSTALL 720'- 4" PMMP | JEFFERSON ST | B | 309266.4996 | 293269.78 | -15996.7196 | -5% | 720 | 754 | 388.952 | ADETOMIWA FALADE 8/29/2023. JOB IS CURRENTLY SHOWING LEVEL 1 UNDER RUN BUT $35,000 IN PAVING WAS PROCESSED THIS WEEK. ONCE THIS PAYMENT IS APPLIED TO THIS JOB ORDER, NO VARIANCE PAPERWORK SHOULD BE REQUIRED. THE PAVING WAS PERFORMED BY PRIVATE CONTRACTOR INSTEAD OF PIPELINE CONTRACTOR WHICH SAVED THE COST OF PAVING.
22026167300 | 558 | EX | RETIRE 720'-4" BS-LP | JEFFERSON ST | B | 62.2578 | 0 | -62.2578 | 100% |  |  | 0
22026167400 | 557 | EX | EMER - INSTALL 5'-3" PMLP | 365 ROOSEVELT BV | A | 3781.5061 | 0 | -3781.5061 | 100% | 5 | 5 | 0
22026167500 | 558 | EX | EMER - RETIRE 5'-3" PLP | 365 ROOSEVELT BV | A | 109.7476 | 0 | -109.7476 | 100% |  |  | 0
22026167600 | 557 | EX | INSTALL 6' OF 3"PMLP MAIN | 595 ALBANY RD | A | 16229.6788 | 8748.35 | -7481.3288 | -46% | 6 | 4 | 2187.0875 | CUT OUT 4' SECTION OF 3" MAIN. TESTED DROP IN PIECE 90#5MINS, TG. ST LTI, TG. BHBNGF. 2 17LB ANODES INSTALLED. PRSSURE NEVER DROPPED ON GAUGES. PURGED ALL AIR OUT BEFORE GAS UP. R.CRAWFORD 10-27-22
22026167700 | 558 | EX | RETIRE 6' OF 3"CSLP MAIN | 595 ALBANY RD | A | 100.2728 | 9674.55 | 9574.2772 | 9,548% |  |  | 0 | CUT OUT 4' SECTION OF LEAKING 3" MAIN, TESTED DROP IN PIECE 90#20MINS, TG. ST LTI. TG. BHBNGF. INST. 2 17LB ANODES. PRESSURE NEVER DROPPED ON GAUGES. PURGED ALL AIR OUT BEFORE GAS UP. R.CRAWFORD 10-27-22
22026168800 | 909 | EX | ST. JAMES HVAC UPGRADE | 1314 WINCHESTER RD | F | 37587.0767 | 24656.22 | -12930.8567 | -34% |  |  | 0 | MONITOR WHILE ACP SWAPS RTU STATION SET TO LOCAL MODE GC ADVISED CC 58614 UPGRADE RTU ON 3-16-22 JOSH MULLINS
22026169800 | 2000 | EX | SURVEY ENCROACHMENT | LEXINGTON | B | 5000 | 0 | -5000 | 100% |  |  | 0
22026171100 | 557 | EX | INSTALL 2715' OF 2"/4"PMMP | ASHLAND TR | B | 852559.9514 | 734298.53 | -118261.4214 | -14% | 2715 | 2642 | 277.9328 | TWALKER/KY 08-16-24: FINAL PAVING RESTORATION FOR THIS PROJECT WILL NOT HAPPEN UNTIL 2025 DUE TO PLANNED WATER COMPANY PROJECT ON SAME STREETS AND CITY OF LEXINGTON SHARED PAVING REQUIREMENTS
22026171200 | 558 | EX | RETIRE 2300' OF 3"/6"BSLP | ASHLAND TR | B | 75.4968 | 220 | 144.5032 | 191% |  |  | 0
22026171300 | 2000 | EX | INVESTIGATE AND OBTAIN U/E | 804 CHEVY CHASE TE | A | 7489 | 0 | -7489 | 100% |  |  | 0
22026172800 | 566 | EX | RETIRE 5' OF 3"PLP S/L | 151 M L KING BV | B | 58.5954 | 0 | -58.5954 | 100% |  |  | 0 | ABANDONED CAPITAL SERVICE LINE WITH ABANDON JOB # 18-0268434-00. LSHARON
22026172900 | 565 | EX | INSTALL 5' OF 4"PMLP S/L | 151 M L KING BV | B | 13312.2384 | 3113 | -10199.2384 | -77% | 6 |  | 0
22026173000 | 909 | EX | 2022 SCADA VISABILITY PROGRAM | ALUMNI DR | F | 30164.6195 | 47294.28 | 17129.6605 | 57% |  |  | 0 | CC# 66617 INSTALLED NEW MIWI350 SMCHOLAN 10-4-2022
22026173600 | 909 | EX | 2022 SCADA VISIBILITY PROGRAM | 1313 OLD FRANKFORT PK | F | 31941 | 25271.05 | -6669.95 | -21% |  |  | 0 | INSTALLED NEW MIWI350 EBLANTON 9-28-2022
22026173800 | 909 | EX | 2022 SCADA VISIBILITY PROGRAM | 1521 CONTINENTAL SQ | F | 30164.6195 | 24972.3 | -5192.3195 | -17% |  |  | 0 | WITH ACP CONTRACTOR WHILE THEY INSTALL POLE FOR COMM EQUIPMENT CC 66318 05-10-2022 RHAYES CC 1924 INSTALLED MIWI350 UNABLE TO PERFORM P2P NDAVIS WORKING ON TICKET MONITORED 30 MINUTES RHAYES 09-29-2022
22026174400 | 909 | EX | 2022 SCADA VISIBILITY PROGRAM | 600 WOODWARD LN REAR | F | 29658.8599 | 28643.37 | -1015.4899 | -3% |  |  | 0 | INSTALL POLES FOR COMM EQUIPMENT 05-10-2022 CC 66285 RHAYES
22026174500 | 909 | EX | 2022 SCADA VISIBILITY PROGRAM | 3090 HARRODSBURG RD | F | 29658.8599 | 29029.69 | -629.1699 | -2% |  |  | 0 | CC# 66436 CC# 79698 CC# 2587 CMCOX 10/5/22 INSTALLED NEW MIWI350 CCOX 10-05-2022
22026174600 | 909 | EX | 2022 SCADA VISIBILITY PROGRAM | 4290 HARRODSBURG RD | F | 29658.8599 | 38527.05 | 8868.1901 | 30% |  |  | 0 | CC# 66475 CC#1503 INSTALLED NEW MIWI350 WITH SUPER SOLAR KIT 9-27-22 CCOX
22026175700 | 0001 | EX | SCADA MATERIAL ORDER | STATE WIDE |  | 134999 | 0 | -134999 | 100% |  |  | 0 | GES - JOB ORDER USED IN CONJUNCTION WITH PBR TO PRE-ORDER MATERIAL FOR SCAD A VISABILITY PROJECT
22026177200 | 2000 | EX | INVESTIGATE & MAP MAINS |  |  | 3206 | 0 | -3206 | 100% |  |  | 0 | CONFLICT ASSESMENT COMPLETED AND REVISIONS BY CITY TO ELLIMINATE KNOW CONFL ICTS COMPLETE. D.LEMONS 1/6/2023
22026177900 | 557 | EX | INSTALL 8' OF 6"PMMP MAIN | 334 WILSON DOWNING RD | B | 29164.4 | 36900.11 | 7735.71 | 27% | 8 | 9 | 4100.0122
22026178000 | 558 | EX | RETIRE 4' OF 6"CSMP MAIN | 334 WILSON DOWNING RD | B | 75.4968 | 876.45 | 800.9532 | 1,061% |  |  | 0
22026178100 | 559 | EX | INSTALL 20' OF 6"PMLP MAIN | 1119 COOPER DR | B | 11448.7503 | 14787.97 | 3339.2197 | 29% | 20 | 55 | 268.8722
22026178500 | 561 | EX | INSTALL 44'-6" PMMP | 620 PARKSIDE DR | B | 72684.0107 | 77349.62 | 4665.6093 | 6% | 44 | 63 | 1227.7717
22026178600 | 562 | EX | RETIRE 26'-6" CSMP | 620 PARKSIDE DR | B | 73.9724 | 1859.72 | 1785.7476 | 2,414% |  |  | 0
22026178800 | 2000 | EX | INVESTIGATE NEW HP EASEMENT | 1320 BIG POND CR | A | 4875 | 0 | -4875 | 100% |  |  | 0
22026178900 | 557 | EX | INSTALL 620' OF 12"CSHP MAIN | 1320 BIG POND CR | B | 330116.9371 | 268220 | -61896.9371 | -19% | 620 | 590 | 454.6102
22026179100 | 558 | EX | RETIRE 520' OF 12"MJBSHP | 1320 BIG POND CR | B | 131.2422 | 3152.18 | 3020.9378 | 2,302% |  |  | 0
22026179200 | 563 | EX | INSTALL 50' OF 6"PMLP S/L | 941 MANCHESTER ST | B | 47001.2003 | 45896.9 | -1104.3003 | -2% | 50 |  | 0
22026179300 | 562 | EX | RETIRE 82'-2"&4" PMMP | EDGELAWN AV | B | 73.9724 | 82.8 | 8.8276 | 12% |  |  | 0
22026180100 | 555 | EX | INSTALL 805' OF 2"/4"PMMP MAIN | 5035 KEENE RD HOUSE | B | 54482.6036 | 116760.6 | 62277.9964 | 114% | 900 | 761 | 153.4305 | TWALKER/KY 09-08-22: PROJECT OVER RUN DUE TO ROCK ENCOUNTERED IN CONSTRUCTI ON REQUIRING ROCK BORE AND OPEN CUT ROCK WHICH INCREATED CONTRACT COST BY $30,000. WMS WOULD NOT ALLOW REVISION OF PROJECT DUE TO UNPAID INVOICES. COMPANY LABOR INCREASED BY OVER $16,000 DUE TO EXTRA TIME FOR CONSTRUCTION AND SEGA WAS $6000 THAN ESTIMATE TWALKER/KY 01-24-23: LEVEL 2 VARIANCE REPORT ADDED TO WMS.DOCS.
22026180200 | 2000 | EX | INVESTIGATE ROAD RIGHT OF WAY | 5035 KEENE RD HOUSE | A | 3754 | 0 | -3754 | 100% |  |  | 0
22026180300 | 2000 | EX | INVESTIGATE CONFLICTS | PICADOME PK |  | 7897 | 0 | -7897 | 100% |  |  | 0
22026180600 | 2000 | EX | INVESTIGATE EASEMENT | 2751 LEESTOWN RD | B | 2536 | 0 | -2536 | 100% |  |  | 0
22026180900 | 557 | EX | EMER-INSTALL 4' OF 2"PMMP | WESTON PARK | A | 3916.7503 | 3753.68 | -163.0703 | -4% | 4 | 5 | 750.736
22026181000 | 558 | EX | EMER-RETIRE 4' OF 2"PMMP | WESTON PARK/WESTON CT | A | 75.4968 | 0 | -75.4968 | 100% |  |  | 0
22026181200 | 2000 | EX | INVESTIGATE EASEMENT | 4630 BOSWORTH LN | B | 2536 | 0 | -2536 | 100% |  |  | 0 | AWEBER 11/3/23 - LAND PS&I WORK COMPLETED PER CBOWLIN. INVESTIGATE EASEMENT AT 4630 BOSWORTH LANE, LEX.
22026181300 | 584 | EX | RETIRE PIT REG STATION 1124 | 410 MARQUIS AV | F | 5746.3751 | 4926.17 | -820.2051 | -14% |  |  | 0 | CCC# 72702 RETIRED REG STATION, REMOVED REGS AND BLIND PLATED VAVLES, REMOVED OIL FROM PRV AND PLUGGED INSIDE PIT, PREFORMED LEAK TEST ON ALL ON CONNECTIONS, CCC 73281 CMCHOLAN 5-17-24 1600
22026181400 | 2000 | EX | REG STATION 1084 PS&I | 3090 HARRODSBURG RD | B | 10000 | 0 | -10000 | 100% |  |  | 0 | AWEBER 9/15/23 - JO EXECUTED TO 583 JO ON PROJECT, TIME USED FOR LAND TO IN VESTIGATE EASEMENTS AND SURVEY FOR REG STATION.
22026181900 | 909 | EX | LAB EQUIPMENT INSTALL | 2001 MERCER RD | F | 15945.3111 | 5312.84 | -10632.4711 | -67% |  |  | 0
22026182000 | 555 | EX | INSTALL 2185' OF 2" PMMP | 112 TURNER COMMONS WY | B | 110360.5276 | 141899.3 | 31538.7724 | 29% | 2200 | 2000 | 70.9497 | AWEBER 01/24/2023 - PROJECT OVERRUN DUE PRIMARILY TO LAND OWNER ISSUES & EXPANSIVE SEWER LINE CAMERA WORK PERFORMED BY BUCHANON. EASEMENT FROM FIRST LAND OWNER FELL THROUGH DUE TO HOA VOTE, INCREASING INSTALLATION BY +200' & PRIVATE EASEMENT. PROJECT ENCOUNTERED ROCK BORE ADDING ~34 HOURS TO DURATIO N. OVERRUN BUCHANON COST $17K + LAND COST $11K & INCREASED SEGA RATE $6K LE D TO VARIANCE.
22026182200 | 2000 | EX | OBTAIN NEW HP EASEMENT | 375 LISLE INDUSTRIAL RD |  | 8052 | 0 | -8052 | 100% |  |  | 0
22026182800 | 557 | EX | EMER-INSTALL 3' OF 2"PMMP | SUNNY LANDINGS TL | A | 4826.1382 | 4419.13 | -407.0082 | -8% | 3 | 3 | 1473.0433 | INSTALLED 3' OF 2" PMMP DUE TO EXCAVATION DAMAGE, TESTED MAIN PIPE AT 90# F OR 20 MIN PER FOL APPROVAL OK, SOAP TEST 2 020 EF CPLGS AT OP FOR 5 MIN OK. INSTALLED MARKER BALLS ON CPLGS. MAP REVISED. WHIMES
22026182900 | 558 | EX | EMER-RETIRE 3' OF 2"PMMP | SUNNY LANDING | A | 74.2578 | 2.72 | -71.5378 | -96% |  |  | 0 | RETIRED 3' OF 020 PMMP DUE TO EXCAVATION DAMAGE. WHIMES 04/20/2022
22026183100 | 561 | EX | INSTALL 3090' OF 2-4" PMMP | LEESTOWN RD | B | 533028.4351 | 610263.34 | 77234.9049 | 14% | 3090 | 3183 | 191.7258 | PROJECT COMPLETE
22026183200 | 562 | EX | RETIRE 3765' OF 2-4" CS & PMMP | LEESTOWN RD | B | 138.8485 | 273.03 | 134.1815 | 97% |  |  | 0 | PROJECT COMPLETED
22026183301 | 561 | EX | SMRP INSTALL 1120' 8-12" CSHP | 1498 LEESTOWN RD | B | 1201596.3067 | 1650295.52 | 448699.2133 | 37% | 800 | 1101 | 1498.906
22026183400 | 562 | EX | RETIRE 702' OF 6" BSHP | 1498 LEESTOWN RD | B | 121.7239 | 220 | 98.2761 | 81% |  |  | 0
22026183600 | 555 | EX | INSTALL 1700'-2" PMMP | WINDFLOWER WY LT107 | B | 46580.9585 | 51519.58 | 4938.6215 | 11% | 1700 | 1860 | 27.6987
22026183700 | 555 | EX | INSTALL 100' OF 2"PMMP MAIN | 3405 FRASERDALE DR | A | 12739.3747 | 19814.52 | 7075.1453 | 56% | 100 | 199 | 99.5705 | INSTALLED 199' OF 020 MAIN. TEST 199' OF MAIN FOR 1HR AT 90LBS. FOL APPROVED.SOAP TEST 2'' EFC AT OP OF FINAL TIE IN. SOAP TEST END CAP ON MONITORING GAUGE AT OP.TEST OK.
22026184400 | 2000 | EX | CONFLICT ASSESSMENT | 240 CANARY RD | A | 4720 | 0 | -4720 | 100% |  |  | 0
22026184600 | 561 | EX | INSTALL 64' OF 2"PMMP MAIN | 240 CANARY RD | B | 17899.1411 | 16772.5 | -1126.6411 | -6% | 60 | 40 | 419.3125
22026184700 | 562 | EX | RETIRE 52' OF 2"PMMP MAIN | 240 CANARY RD | B | 74.2578 | 0 | -74.2578 | 100% |  |  | 0
22026184800 | 561 | EX | INSTALL 3775'-2" PMMP | LONE OAK DR | B | 567138.2381 | 689655.43 | 122517.1919 | 22% | 4390 | 4210 | 163.8136
22026184900 | 562 | EX | RETIRE 3315'-2"&4"BSLP | LONE OAK DR | B | 72.7393 | 23.53 | -49.2093 | -68% |  |  | 0
22026185001 | 561 | EX | INSTALL 260' OF 2"PMMP MAIN | 1602 CLAYS MILL RD | B | 27065.0582 | 30483.21 | 3418.1518 | 13% | 260 | 228 | 133.6983
22026185301 | 555 | EX | INSTALL 875' OF 2"PMMP MAIN | COCOS WY LT1 | B | 74170.089 | 69561.33 | -4608.759 | -6% | 875 | 725 | 95.9467
22026186000 | 909 | EX | EXCHANGE ELECTRONIC COMPONENTS | 1511 RUSSELL CAVE RD | F | 5480.5156 | 3201.06 | -2279.4556 | -42% |  |  | 0 | ACP REMOVED ERX REPLACED WITH MIWI CCOX RHAYES 05-27-2022
22026186100 | 910 | EX | RETIRE ELECTRONIC COMPONENTS | 1511 RUSSELL CAVE RD | F | 124.5156 | 175.52 | 51.0044 | 41% |  |  | 0 | ACP REPLACED ERX WITH MIWI RHAYES CCOX 05-27-2022 ACP REPLACED ERX WITH MIWI RHAYES CCOX 05-27-2022
22026186600 | 909 | EX | EXCHANGE ELECTRONIC COMPONENTS | PRESS AV | F | 4216.5438 | 616.42 | -3600.1238 | -85% |  |  | 0 | INSTALLED MIWI 350 AND TUBING, CCC 67481 CMCHOLAN 5-19-2022 NOT ON SITE, TURNED IN PAPERWORK IN WINCHESTER, NO CCC TICKET, CMCHOLAN 5-20-2022
22026186700 | 910 | EX | RETIRE ELECTRONIC COMPONENTS | PRESS AV | F | 124.5156 | 485.53 | 361.0144 | 290% |  |  | 0 | REMOVED ERX, CCC 67481 CMCHOLAN 5-19-2022 RWILLIAMS EX CAPITAL JOB
22026187200 | 909 | EX | EXCHANGE ELECTRONIC COMPONENTS | 3620 WILLOW SPRINGS | F | 4745.0565 | 1831.39 | -2913.6665 | -61% |  |  | 0 | CCC# 68726 INSTALLED NEW MIWI 350 AJPARKS
22026187300 | 910 | EX | RETIRE ELECTRONIC COMPONENTS | 3620 WILLOW SPRINGS | F | 124.5156 | 185.7 | 61.1844 | 49% |  |  | 0 | CCC# 68726 RETIRED ERX 05/26/2022 APARKS
22026187800 | 561 | EX | INSTALL 10' OF 4"PMLP MAIN | SPRINGRIDGE DR | B | 18153.0818 | 29076.83 | 10923.7482 | 60% | 10 | 24 | 1211.5346
22026187900 | 562 | EX | RETIRE 8' OF 4"PMLP MAIN | SPRINGRIDGE DR | B | 74.2578 | 0 | -74.2578 | 100% |  |  | 0
22026188900 | 2000 | EX | ENE PS&I FOR DURBIN VALVE REPL | 8721 DURBIN LN | B | 7500 | 0 | -7500 | 100% |  |  | 0
22026192300 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 403 E THIRD ST | F | 4801.1928 | 281.87 | -4519.3228 | -94% |  |  | 0 | CHANGED ERX TO MIWI 350, P2P OK, CCC 70245 CMHOLAN 6-13-2022
22026192400 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 403 E THIRD ST | F | 124.8731 | 443.37 | 318.4969 | 255% |  |  | 0 | REMOVED ERX TO INSTALL MIWI, CCC 70245 CMCHOLAN 6-13-2022 INSTALLED NEW MIWI350
22026195000 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 5540 ATHENS WALNUT PK | F | 4801.1928 | 5607.88 | 806.6872 | 17% |  |  | 0 | SWAP COMP. PARKS 08-29-22 1545 CCC# 78985 RETIRED OLD ERX INSTALLED NEW MIWI350 AJPARKS 8-29-2022
22026195100 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 5540 ATHENS WALNUT PK | F | 124.8731 | 248.95 | 124.0769 | 99% |  |  | 0 | REMOVAL COMP. APARKS 08-29-22 1044 CCC# 78985 RETIRED OLD ERX INSTALLED NEW MIWI350 AJPARKS 8-29-2022
22026197100 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | TOWNLEY DR | F | 4801.1928 | 5373.93 | 572.7372 | 12% |  |  | 0 | CCC 79940 RETIRED OLD ERX INSTALLED NEW MIWI350 9-7-2022
22026197200 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | TOWNLEY DR | F | 124.8731 | 251.1 | 126.2269 | 101% |  |  | 0 | CCC 79940 RETIRED OLD ERX INSTALLED NEW MIWI350 EBLANTON 9-7-2022
22026197300 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 110 E TIVERTON WY | F | 4801.1928 | 6904.6 | 2103.4072 | 44% |  |  | 0 | CC# 3980 CMCOX 10/19/22 INSTALLED NEW MIWI350 CCOX 10-19-22
22026197400 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 110 E TIVERTON WY | F | 124.8731 | 305.47 | 180.5969 | 145% |  |  | 0 | CC# 3980 CMCOX 10/19/22 RETIRED OLD ERX CCOX 10-19-22
22026197700 | 557 | EX | INSTAL 3'-2" PMMP | SNOWY EGRET WY | A | 2387.9592 | 1311.83 | -1076.1292 | -45% | 3 | 3 | 437.2767 | HIT MAIN BY CONCRETE STAKE.MADE SAFE BY SQUEEZING OFF IN TWO BELL HOLES. REPLACED DAMAGED SECTION OF PIPE.TESTED 10FT OF 020 AND PURGE TEE FOR 1HR 90LBS.TEST OK.SOAP TEST END CAP AND 2EFC'S CPLGS AT OP.TEST OK BHB NGF
22026197800 | 558 | EX | RETIRE 3'-2" PMMP | SNOWY EGRET WY | A | 76.9137 | 914.45 | 837.5363 | 1,089% |  |  | 0 | HIT MAIN BY CONCRETE STAKE.MADE SAFE BY SQUEEZING OFF IN TWO BELL HOLES. REPLACED DAMAGED SECTION OF PIPE.TESTED 10FT OF 020 AND PURGE TEE FOR 1HR 90LBS.TEST OK.SOAP TEST END CAP AND 2EFC'S CPLGS AT OP.TEST OK BHB NGF
22026198601 | 555 | EX | INSTALL 1900' OF 2"PMMP MAIN | DAHLIA DR LT78 | B | 50146.9852 | 71556.52 | 21409.5348 | 43% | 1900 | 2208 | 32.4078
22026199100 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 800 NEWTOWN CT | F | 4801.1928 | 5602.7 | 801.5072 | 17% |  |  | 0 | CCC 79615 RETIRED OLD ERX INSTALLED NEW MIWI350 EBLANTON 9-2-2022
22026199200 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 800 NEWTOWN CT | F | 124.8731 | 880.44 | 755.5669 | 605% |  |  | 0 | CCC 79615 RETIRED OLD ERX INSTALLED NEW MIWI350 EBLANTON 9-2-2022
22026200500 | 566 | EX | RETIRE 2' OF 3"PLP S/L | 213 E 3RD ST | B | 62.4365 | 0 | -62.4365 | 100% |  |  | 0
22026200600 | 565 | EX | INSTALL 15' OF 3"/4"PMLP S/L | 213 E 3RD ST | B | 11118.4162 | 10449.59 | -668.8262 | -6% | 13 |  | 0
22026202200 | 555 | EX | INSTALL 125' OF 2" PMMP MAIN | 1289 BARLEYS PASS | B | 8841.6395 | 11459.71 | 2618.0705 | 30% | 125 | 104 | 110.1895
22026202900 | 560 | EX | RETIRE 135' OF 2"PMP MAIN | 5035 KEENE RD | B | 78.4365 | 2.29 | -76.1465 | -97% |  |  | 0
22026203900 | 584 | EX | RETIRE PAPER GAUGE | 3090 HARRODSBURG RD | F | 78.4365 | 0 | -78.4365 | 100% |  |  | 0 | RETIRED PAPER CHART CCOX10-05-2022
22026204000 | 584 | EX | RETIRE PAPER GAUGE | 4290 HARRODSBURG RD | F | 78.4365 | 157.99 | 79.5535 | 101% |  |  | 0 | RETIRED PAPER CHART CHRIS COX 9-27-22
22026204200 | 584 | EX | RETIRED GAUGE | ALUMNI DR | F | 76.9137 | 0 | -76.9137 | 100% |  |  | 0 | RETIRED PAPER CHARTS SMCHOLAN 10-04-2022
22026204900 | 2000 | EX | INVESTIGATE ROAD R/W | COCOS WY | B | 2543 | 0 | -2543 | 100% |  |  | 0
22026206900 | 557 | EX | EMER-INSTALL 16' OF 4"/6"PMLP | 931 AURORA AV | A | 8399.775 | 11009.07 | 2609.295 | 31% | 36 | 18 | 611.615 | LEAKING POSI HOLD COUPLING.LEAKING OUT OF FITTING ON COUPLING. REPLACED 6'' TEE AND 19FT OF MAIN.TESTED MAIN FOR 1HR AT 90LBS.TEST OK. SOAP TEST FINAL TIE INS AT OP FOR 5MINS AT OP.TEST OK. BHB NGF.
22026207000 | 558 | EX | EMER-RETIRE 14' OF 6"BSLP | 931 AURORA AV | A | 60.0112 | 11230.19 | 11170.1788 | 18,614% |  |  | 0 | LEAKING POSI HOLD COUPLING.LEAKING OUT OF FITTING ON COUPLING. REPLACED 6'' TEE AND 19FT OF MAIN.TESTED MAIN FOR 1HR AT 90LBS.TEST OK. SOAP TEST FINAL TIE INS AT OP FOR 5MINS AT OP.TEST OK. BHB NGF.
22026208900 | 561 | EX | EMER - INSTALL ~10'-8" CSHP | 1930 CLAYS MILL RD | B | 32930.2498 | 59795.62 | 26865.3702 | 82% | 10 |  | 0
22026209400 | 586 | EX | RETIRE CHAIN LINK FENCE | 1321 BIG POND CR | F | 65.0112 | 0 | -65.0112 | 100% |  |  | 0
22026209500 | 586 | EX | RETIRE CHAIN LINK FENCE | 427 TRANSPORT CT | F | 65.0112 | 0 | -65.0112 | 100% |  |  | 0
22026209800 | 586 | EX | RETIRE VAULT STRUCTURE | 800 PRESS AV | F | 1027.5809 | 0 | -1027.5809 | 100% |  |  | 0 | PIT RETIRED AND FILLED IN
22026209900 | 586 | EX | RETIRE VAULT STRUCTURE | 410 MARQUIS AV | F | 859.5809 | 2265.12 | 1405.5391 | 164% |  |  | 0
22026210000 | 588 | EX | RETIRE ELECTRONICS | 451 HARBISON RD | F | 65.0112 | 249.16 | 184.1488 | 283% |  |  | 0 | RETIRED OLD MINI-AT INSTALLED NEW EC350 EBLANTON 07-14-2022
22026210100 | 557 | EX | EMER - INSTALL 6'-4" PMMP | 601 CLAYS MILL | A | 4810.9373 | 5514.88 | 703.9427 | 15% | 6 | 16 | 344.68 | DAMAGED SECTION OF PIPE DUE TO EXCAVATOR ERROR.MADE SAFE BY SQUEEZING OFF IN BELLHOLES.OC 16FT NEW MAIN DUE TO EXCAVATION WHERE DAMAGE WAS TOO DEEP. TESTED MAIN 1HR AR 90LB.TEST OK.SOAP TEST EFC'SAT OP.TEST OK BHB NGF
22026210200 | 558 | EX | EMER - RETIRE 6'-4" PMMP | 601 CLAYS MILL | A | 63.5475 | 95.05 | 31.5025 | 50% |  |  | 0 | DAMAGED SECTION OF PIPE DUE TO EXCAVATOR ERROR.MADE SAFE BY SQUEEZING OFF IN BELLHOLES.OC 16FT NEW MAIN DUE TO EXCAVATION WHERE DAMAGE WAS TOO DEEP. TESTED MAIN 1HR AR 90LB.TEST OK.SOAP TEST EFC'SAT OP.TEST OK BHB NGF
22026210301 | 555 | EX | INSTALL 850' OF 4"PMMP MAIN | 554 S FORBES RD VAUGHN | B | 192098.991 | 173794.47 | -18304.521 | -10% | 851 | 818 | 212.4627
22026210600 | 558 | EX | EMER-RETIRE 50' OF 3"BSLP MAIN | LIMESTONE | A | 5032.3621 | 2854.75 | -2177.6121 | -43% |  |  | 0
22026211400 | 560 | EX | PAPER ONLY-RETIRE MP MAIN | BIG POND | B | 65.0112 | 0 | -65.0112 | 100% |  |  | 0
22026211700 | 576 | EX | RETIRE LAND AND REG SITE | 247 BURKE RD | F | 29152.0112 | 46152.61 | 17000.5988 | 58% |  |  | 0
22026212400 | 2000 | EX | INVESTIGATE AND MAP MAINS | CULZEAN CT |  | 13587.2625 | 0 | -13587.2625 | 100% |  |  | 0 | LFUCG IS IN PROCESS OF OBTAINING EASEMENTS. START DATE PUSHED UNTIL LFUCG G IVES NOTICE TO PROCEED. D.LEMONS 12/28/22
22026212500 | 583 | EX | REPLACE VALVES AT R-1084 | 3090 HARRODSBURG RD | F | 14531.0267 | 9402.89 | -5128.1367 | -35% |  |  | 0 | HELP CCOX WITH VALVE REPLACEMENT, CMCHOLAN 9-5-23 1600 CC# 43383 PAPERWORK ONLY. NO CC# REQUIRED. NOT ON SITE.
22026212600 | 584 | EX | RETIRE STATION VALVES R-1084 | 3090 HARRODSBURG RD | F | 119.4953 | 1269.98 | 1150.4847 | 963% |  |  | 0
22026212700 | 2000 | EX | INVESTIGATE MAINS | 2595 MILITARY PK |  | 2226 | 0 | -2226 | 100% |  |  | 0 | VACUME EXCAVATION CONFIRMED NO CONFLICT WITH PROPOSED ROADWAY IMPROVEMNTS A S SHOWN IN PLANS PROVIDED. D.LEMONS 11/22/2022
22026213000 | 558 | EX | RETIRE 2015'-8/4/2" BSMP/CSMP | 1900 RICHMOND RD | B | 89.0305 | 220 | 130.9695 | 147% |  |  | 0
22026213100 | 566 | EX | RETIRE 3"BSMP SERVICE LINE | 1900 RICHMOND RD | B | 63.4096 | 0 | -63.4096 | 100% |  |  | 0
22026213200 | 565 | EX | INSTALL 30' OF 2-4" PMMP S/L | 1900 RICHMOND RD | B | 27880.5873 | 33540.05 | 5659.4627 | 20% | 340 |  | 0
22026214700 | 910 | EX | ST. JAMES RTU PANEL | 1314 WINCHESTER RD | F | 55.5311 | 0 | -55.5311 | 100% |  |  | 0 | UPGRADED RTU JOSH MULLINS
22026214800 | 557 | EX | EMER INSTALL 2' - PMMP | 2492 SHADY HILLS LN | A | 2418.3858 | 8176.85 | 5758.4642 | 238% | 2 | 2 | 4088.425
22026214900 | 558 | EX | EMER RETIRE 2'-PMP | 2492 SHADY HILLS LN | A | 84.9152 | 0 | -84.9152 | 100% |  |  | 0
22026215000 | 557 | EX | EMER INSTALL 2'-4" PMLP | 444 KENTON ST | A | 3659.4376 | 9400.14 | 5740.7024 | 157% | 0 | 2 | 4700.07
22026215100 | 558 | EX | EMER RETIRE 2'-4" PLP | 444 KENTON ST | A | 84.9152 | 0 | -84.9152 | 100% |  |  | 0
22026215300 | 557 | EX | EMER - INSTALL 20'-2" PMIP | VERSAILLES | A | 10433.2304 | 15168.73 | 4735.4996 | 45% | 20 | 10 | 1516.873
22026215400 | 558 | EX | EMER - RETIRE 5'-2" PMIP | VERSAILLES | A | 80.5311 | 0 | -80.5311 | 100% |  |  | 0
22026215500 | 557 | EX | EMER - INSTALL 5'-2" PMMP | BRIDLE CT | A | 4479.378 | 6774.27 | 2294.892 | 51% | 5 | 4 | 1693.5675
22026215600 | 558 | EX | EMER - RETIRE 5'-2" PMMP | BRIDLE CT | A | 84.9152 | 0 | -84.9152 | 100% |  |  | 0
22026215900 | 559 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | BIRKENHEAD DR | A | 3722.1191 | 1854.5 | -1867.6191 | -50% | 3 | 3 | 618.1667 | REPLACED 3FT SECTION OF MAIN. TESTED NEW SECTION OF MAIN FOR 20MINS AT 90LBS.TEST OK SOAP TEST EFC'S AT OP FOR 5MINS.TEST OK. BHBNGF
22026216000 | 560 | EX | EMER-RETIRE 3' OF 2"PAMP MAIN | BIRKENHEAD DR | A | 84.9152 | 143.19 | 58.2748 | 69% |  |  | 0 | REPLACED 3FT SECTION OF MAIN. TESTED NEW SECTION OF MAIN FOR 20MINS AT 90LBS.TEST OK SOAP TEST EFC'S AT OP FOR 5MINS.TEST OK. BHBNGF
22026216200 | 555 | EX | INSTALL 950' OF 2"/4"PMMP MAIN | CALENDULA RD LT272 | B | 39269.0655 | 47379.78 | 8110.7145 | 21% | 950 | 1019 | 46.4963
22026216900 | 560 | EX | PAPER ONLY EXECUTE | 1850 MERCER RD | B | 84.9152 | 0 | -84.9152 | 100% |  |  | 0
22026217300 | 566 | EX | RETIRE 3"PLP SERVICE LINE | 124 N ASHLAND AV | B | 170.8304 | 0 | -170.8304 | 100% |  |  | 0
22026217400 | 566 | EX | RETIRE 6"PLP SERVICE LINE | 301 WOODLAND AV | B | 144.8304 | 827.26 | 682.4296 | 471% |  |  | 0
22026217800 | 557 | EX | EMER-INSTALL 3' OF 4"PMLP MAIN | 591 ROSEMILL DR | A | 6173.2589 | 12300.82 | 6127.5611 | 99% | 3 | 10 | 1230.082 | LEAK CLEARED USING DPI D311930 PW
22026217900 | 558 | EX | EMER-RETIRE 3' OF 4"BSLP MAIN | 591 ROSEMILL DR | A | 170.8304 | 4448.33 | 4277.4996 | 2,504% |  |  | 0
22026218200 | 584 | EX | RETIRE PAPER GUAGE | 3478 TATES CREEK RD | F | 339.1994 | 0 | -339.1994 | 100% |  |  | 0 | RETIRE PAPER CHART DUE TO ERX INSTALL AT ANOTHER STATION SMCHOLAN
22026218300 | 584 | EX | RETIRE PAPER GAUGE | 2300 RICHMOND RD | F | 339.1994 | 0 | -339.1994 | 100% |  |  | 0 | RETIRED PAPER CHART DUE TO ERX INSTALL AT ANOTHER LOCATION
22026218800 | 909 | EX | INSTALL MI WIRELESS UNIT | 108 SURFSIDE DR | F | 9310.2589 | 10259.75 | 949.4911 | 10% |  |  | 0 | CC# 79803 CC# 2675 CC# 2675 CMCOX 10/6/22 INSTALLED NEW MIWI350 CCOX 10-06-2022
22026219400 | 557 | EX | INSTALL 380' OF 4"PMMP MAIN | 452 ROSE ST | B | 176409.6078 | 172779.97 | -3629.6378 | -2% | 381 | 494 | 349.757
22026219500 | 558 | EX | RETIRE 380' OF 4"BSMP MAIN | 452 ROSE ST | B | 89.0305 | 91.2 | 2.1695 | 2% |  |  | 0
22026220500 | 2000 | EX | OBTAIN R/R PERMIT AND EASEMENT | TRAFTON ST | A | 36729 | 0 | -36729 | 100% |  |  | 0
22026220800 | 558 | EX | *PAPER ONLY* 2022 CAST IRON | 4TH | B | 295.7645 | 0 | -295.7645 | 100% |  |  | 0
22026221200 | 557 | EX | EMER - INSTALL 8'-6"PMMP | 1228 MANCHESTER | A | 32929.6819 | 11736.48 | -21193.2019 | -64% | 108 | 3 | 3912.16 | TEST 6 IN MAIN AT 90 LB FOR 20 MIN SOAP TEST EFC AT OP FOR 5 MIN
22026221300 | 558 | EX | EMER - RETIRE 8'-6" PMP | 1228 MANCHESTER | A | 87.3224 | 595.27 | 507.9476 | 582% |  |  | 0 | REMOVED 2 FT OF 6 IN DAMAGE PIPE
22026222800 | 557 | EX | EMER-INSTALL 2' OF 4"PMMP MAIN | 820 N LIMESTONE ST | A | 23837.8998 | 21988.24 | -1849.6598 | -8% | 2 | 2 | 10994.12
22026222900 | 558 | EX | EMER-RETIRE 2' OF 4"PMMP MAIN | 820 N LIMESTONE ST | A | 89.0305 | 0 | -89.0305 | 100% |  |  | 0
22026223100 | 557 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | 109 CAMBRIDGE LN | A | 4624.3747 | 4059.84 | -564.5347 | -12% | 3 | 3 | 1353.28 | COMPLETED PAPERWORK FOR JOB. R.CRAWFORD 10-11-22
22026223200 | 558 | EX | EMER-RETIRE 3' OF 2"PMP MAIN | 109 CAMBRIDGE LN | A | 89.0305 | 125.23 | 36.1995 | 41% |  |  | 0 | R.CRAWFORD
22026223600 | 555 | EX | INSTALL 3000' OF 2"PMMP MAIN | BAY SHOALS DR LT99 | B | 81410.7619 | 80798.26 | -612.5019 | -1% | 3000 | 2933 | 27.548
22026223700 | 561 | EX | INSTALL 1296'-2"&4" PMMP | TUSCON DR | B | 306884.1479 | 286331.62 | -20552.5279 | -7% | 1296 | 1430 | 200.2319
22026223800 | 562 | EX | RETIRE 1212'-2",3"&4" CSMP | TUSCON DR | B | 117.5985 | 0 | -117.5985 | 100% |  |  | 0
22026223900 | 561 | EX | INSTALL 1067'-4" PMMP | BRANNON RD | B | 181608.1135 | 149979.89 | -31628.2235 | -17% | 1067 | 1095 | 136.9679
22026224000 | 562 | EX | RETIRE 1150'-4" PMMP | BRANNON RD | B | 72.8379 | 0 | -72.8379 | 100% |  |  | 0
22026224201 | 557 | EX | INSTALL 2300' OF 2"/4"PMMP | 321 COLUMBIA AV | B | 524527.3047 | 588766.29 | 64238.9853 | 12% | 2300 | 2283 | 257.8915
22026224300 | 558 | EX | RETIRE 4500' OF 6"/4"BSLP MAIN | 321 COLUMBIA AV | B | 114.3981 | 2115.84 | 2001.4419 | 1,750% |  |  | 0
22026226900 | 0001 | EX | PAYROLL TRAINING | 2001 MERCER RD | A | 6000 | 0 | -6000 | 100% |  |  | 0 | TWALKER/KY-THIS JOB ORDER IS TO DOCUMENT TRAINING COST, THERE IS NO MAPPING REQUIRED, NO WORK ORDER POLYGON, NO FACILITY TO CREATE AND NO UPRATE.
22026227000 | 557 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | FORT HARRODS | A | 5024.0582 | 5707.92 | 683.8618 | 14% | 3 | 3 | 1902.64 | INST 3" OF 2 P MP MAIN PER GAS STANDARDS. MCRAIG 9/30/22
22026227100 | 558 | EX | EMER-RETIRE 3' OF 2"PMP MAIN | FORT HARRODS | A | 74.3089 | 316.08 | 241.7711 | 325% |  |  | 0 | ABN 3' OF 2" P MP MAIN DUE TO LEAK. PER GAS STANDARDS. MCRAIG 9/30/22
22026227200 | 910 | EX | RETIRE ELECTRONICS | 4940 ATHENS BOONESBORO RD | F | 74.3089 | 0 | -74.3089 | 100% |  |  | 0
22026228000 | 557 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | COSIMO | A | 4027.0582 | 2032.93 | -1994.1282 | -50% | 3 | 3 | 677.6433 | INSTALLED 3 FT OF 2 IN MAIN ON DAMAGE TEST FROM POINT A TO B 90 LB FOR 20 MIN TEST PURG TEE 90 LB FOR 5 MIN SOAP TEST 1 IN END CAP AT OP FOR 5 MIN SOAP TEST 2 EFC AT OP FOR 5 MIN BHB NO GAS FOUND
22026228100 | 558 | EX | EMER-RETIRE 3' OF 2"PMMP MAIN | COSIMO | A | 74.3089 | 590.32 | 516.0111 | 694% |  |  | 0
22026228500 | 561 | EX | INSTALL 167'-2" PMMP | CULZEAN CT | B | 82180.2832 | 84729.46 | 2549.1768 | 3% | 177 | 258 | 328.4088
22026228600 | 562 | EX | RETIRE 136'-2" PMMP | CULZEAN CT | B | 72.8379 | 50.09 | -22.7479 | -31% |  |  | 0
22026228800 | 2000 | EX | INVESTIGATE EASEMENT/LAND RIGH | COLUMBIA TE | B | 5556 | 0 | -5556 | 100% |  |  | 0
22026230100 | 557 | EX | EMER-INSTALL 2' OF 2"PMMP | 3533 COLT NECK LN | A | 3890.5291 | 2249.75 | -1640.7791 | -42% | 2 | 3 | 749.9167
22026230200 | 558 | EX | EMER-RETIRE 2' OF 2"PMP MAIN | 3533 COLT NECK LN | A | 74.3089 | 0 | -74.3089 | 100% |  |  | 0
22026231301 | 557 | EX | INSTALL 925' OF 2"PMMP MAIN | 626 E HIGH ST | B | 399340.9217 | 388671.62 | -10669.3017 | -3% | 920 | 838 | 463.8086 | TWALKER/KY 10-25-24: JOB COST OVER RUN DUE TO CITY OF LEXINGTON REQUIRING MILL/PAVE FOR HIGH STREET WHICH ADDED $80,000 COPY INVOICE IN WMS.DOCS
22026231400 | 558 | EX | RETIRE 975' OF 8"BSLP MAIN | 626 E HIGH ST | B | 121.7239 | 110 | -11.7239 | -10% |  |  | 0
22026231800 | 584 | EX | RETIRE PAPER CHART | 707 LANE ALLEN RD | F | 1093 | 0 | -1093 | 100% |  |  | 0 | RETIRED PAPER CHART CCOX 8-23-22
22026232000 | 584 | EX | RETIRE PAPER GAUGE | 2108 NICHOLASVILLE RD | F | 993 | 0 | -993 | 100% |  |  | 0 | RETIRED PAPER CHART 7-26-22 CCOX
22026232100 | 584 | EX | RETIRE PAPER GAUGE | 3301 LANSDOWNE DR | F | 993 | 719.12 | -273.88 | -28% |  |  | 0 | REMOVED CHART, CCC 2244, CMCHOLAN 12-1-22
22026233800 | 563 | EX | INSTALL 380' OF 4"PMLP SL | 960 DELAWARE AV | B | 36339.1396 | 35845.97 | -493.1696 | -1% | 380 |  | 0
22026233900 | 575 | EX | OBTAIN EASEMENT FOR REG #1220 | 4940 ATHENS BOONESBORO RD | F | 14490 | 12619.05 | -1870.95 | -13% |  |  | 0
22026234001 | 555 | EX | INSTALL 500' OF 2"/4"PMMP MAIN | 112 LUCILLE DR | B | 89921.6185 | 95523.45 | 5601.8315 | 6% | 500 | 776 | 123.0972 | INSTALLED 422' 040-PMMP 185' 020-PMMP 607' TOTAL
22026235500 | 575 | EX | ACQUIRE EASEMENT | 2201 LEESTOWN RD | F | 8471 | 1026.17 | -7444.83 | -88% |  |  | 0 | AWEBER 5/29/24 - JO FOUND IN RATE CASE LIST, EXECUTED AS PROJECT IS COMPLET E.
22026236300 | 2000 | EX | SURVEY AND MAP MAINS | LOCUST AV | B | 11747 | 0 | -11747 | 100% |  |  | 0
22026236501 | 557 | CO | INSTALL 1325' OF 4"/8"CSHP MN | TRAFTON ST | B | 1205185.7862 | 1407086.76 | 201900.9738 | 17% | 1325 | 1386 | 1015.2141
22026236600 | 558 | CO | RETIRE 1300'- 6 5/8"BSHP MAIN | TRAFTON ST | B | 119.4953 | 484.04 | 364.5447 | 305% |  |  | 0
22026236700 | 561 | EX | INSTALL 134'-4" PMLP | 328 LOCUST AV | A | 32463.7981 | 27660 | -4803.7981 | -15% | 134 | 160 | 172.875 | INST 160'- 4" P LP MAIN FOR SEWER PROJECT PER ENGINEERED TIE-IN PLAN. MCRAIG 2/27/24
22026236800 | 562 | EX | RETIRE 130'-4" PLP | 328 LOCUST AV | A | 160.3697 | 10308.08 | 10147.7103 | 6,328% |  |  | 0 | RETIRE 148'- 4" P LP MAIN TO RELOCATE PER ENGINEERED PLAN. MCRAIG 2/27/24
22026238200 | 555 | EX | INSTALL 205' OF 2"PMMP MAIN | 1770 VENDOR WY STE 100 | B | 19394.2346 | 13604.24 | -5789.9946 | -30% | 205 | 215 | 63.2755 | TWALKER/KY 01-20-23: ISSUED BACK ORDER REQUEST #52196 FOR THIS JOB
22026239702 | 557 | CO | INSTALL 8650' - 2,4,6" PMMP | 209 CASTLEWOOD DR | B | 1422627.7319 | 1934664.05 | 512036.3181 | 36% | 8740 | 8591 | 225.1966
22026239800 | 558 | CO | RETIRE 6065' - 4/6" BS/CS/PLP | CASTLEWOOD | B | 139.1159 | 149.74 | 10.6241 | 8% |  |  | 0
22026240100 | 588 | EX | GMB TO CAB CONVERSION | 1310 CENTRE PY | F | 238.427 | 2136.59 | 1898.163 | 796% |  |  | 0 | CONVERTED GMB TO CAB ACCOUNT, CMCHOLAN 4-4-23
22026240900 | 560 | EX | PAPER ONLY EXECUTE | PRESS AV | B | 119.2135 | 0 | -119.2135 | 100% |  |  | 0
22026241500 | 559 | EX | INSTALL 40'-2" PMMP | 2051 CUMMINS CT | B | 23266.5784 | 14054.24 | -9212.3384 | -40% | 40 | 25 | 562.1696
22026241600 | 560 | EX | RETIRE 30'-2" PMMP | 2051 CUMMINS CT | B | 124.7348 | 193.2 | 68.4652 | 55% |  |  | 0
22026242301 | 559 | EX | INSTALL 8"POLY VALVE W/10"SPH | 3090 HARRODSBURG RD | B | 63212.0666 | 84736.28 | 21524.2134 | 34% | 10 | 12 | 7061.3567
22026242400 | 575 | EX | OBTAIN NEW HP EASEMENT | 1320 BIG POND CR | F | 8747.2135 | 7607.73 | -1139.4835 | -13% |  |  | 0
22026242500 | 560 | EX | EMER-RETIRE 385' OF 2"/3"PAIP | 4130 GEORGETOWN RD | B | 5363.3319 | 5628.45 | 265.1181 | 5% |  |  | 0
22026242600 | 559 | EX | INSTALL 500' - 4" PMMP | 3725 MAN O WAR BD | B | 97718.819 | 115979.71 | 18260.891 | 19% | 520 | 524 | 221.3353
22026242700 | 561 | EX | INSTALL 350' OF 8"CSHP MAIN | 2210 GEORGETOWN RD | B | 370158.4472 | 383081.64 | 12923.1928 | 3% | 350 | 385 | 995.0172
22026242800 | 562 | EX | RETIRE 326' OF 8"CSHP MAIN | 2210 GEORGETOWN RD | B | 114.3981 | 0 | -114.3981 | 100% |  |  | 0
22026242900 | 2000 | EX | DESIGN AND RELOCATION CONFLICT | 2210 GEORGETOWN RD | B | 10887 | 0 | -10887 | 100% |  |  | 0
22026243000 | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2032 PARALLEL DR | F | 29336.8866 | 20860 | -8476.8866 | -29% |  |  | 0 | CC# 23362 CCC# 24092 DID NOT ENTER STATION. CWEMPE 4/27/23
22026243100 | 909 | EX | INSTALL NEW SCADA EQUIPMENT | OLD FRANKFORT PK | F | 21860.8866 | 18742.99 | -3117.8966 | -14% |  |  | 0 | CC 22894 WELDED TAPS ON COULD NOT PRESSURE TEST DUE TO TIME CONSTRAINTS PER RTWAIT CCC# 24089
22026243200 | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 1750 SUMMERHILL DR | F | 25283.8866 | 20634.93 | -4648.9566 | -18% |  |  | 0 | CCC# 21042 CC 22745 WELD AND TEST STEEL TIE TAPS INLET 240# OUTLET 90# 5MINS RHAYES DMARTIN 03-30-2023 NOT ONSITE COLLECTING PARTS FOR JOB CCC#27524
22026243300 | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 567 MITCHELL AV | F | 20719.8866 | 20996.21 | 276.3234 | 1% |  |  | 0 | CCC# 21042 CC#23191 CC#24679 CC# 27421 CMCOX 4/27/23 1600
22026243400 | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 2540 RESEARCH PARK DR | F | 19008.8866 | 15857.32 | -3151.5666 | -17% |  |  | 0 | CCC#22649
22026243500 | 584 | EX | RETIRE RECORDING GAUGE | 2540 RESEARCH PARK DR | F | 96.4823 | 241.8 | 145.3177 | 151% |  |  | 0 | CCC#22649
22026243600 | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 250 W LOUDON AV | F | 27565.8866 | 18807.4 | -8758.4866 | -32% |  |  | 0 | CCC 25146 INSTALLED NEW MIWI AND SOLAR KIT, NOT COMMIONSED YET CCC 25146 INSTALLED NEW SCADA EQUMENT NOT COMSSIONED YET BUT IS UP AND RUNNING CCC-30719PREFORMED POINT TO POINT FOR NEW WIMI
22026243900 | 909 | EX | INSTALL NEW SCADA EQUIPMENT | KENNESAW DR | F | 14352.6752 | 13592.24 | -760.4352 | -5% |  |  | 0 | CHANGE OF PLAN, SCADA IS NOT BUILT FOR THIS SIGHT AND NOT READY TO BE CHANGED OVER, CMCHOLAN 3-28-23 INSTALL NEW MIWI, P2P OK, GAGE INSP OK, REMOVED PAPER PRESSURE CHART, PRESSURE TEST OK, CMCHOLAN 5-4-23 1358
22026244000 | 910 | EX | RETIRE ELECTRONICS | KENNESAW DR | F | 131.2422 | 65.38 | -65.8622 | -50% |  |  | 0 | REMOVED ERX TO INSTALL MIWI, CCC 22274, CMCHOLAN 3-28-23
22026245000 | 560 | EX | PAPER ONLY EXECUTE | ROSE ST | B | 131.2422 | 0 | -131.2422 | 100% |  |  | 0
23026246100 | 584 | EX | RETIRE PAPER GAUGE | 3369 HOLWYN RD | F | 131.2422 | 389.08 | 257.8378 | 196% |  |  | 0 | RETIRE PRESSURE CHART GUAGE CCOX 1-2-23
23026246401 | 559 | EX | INSTALL 3100' OF 2"PMMP MAIN | 2263 NICHOLASVILLE RD | B | 612252.3877 | 515222.82 | -97029.5677 | -16% | 3100 | 2905 | 177.3573
23026246500 | 560 | EX | RETIRE 2400' OF 4"BS/CSLP MAIN | 2263 NICHOLASVILLE RD | B | 138.8485 | 0 | -138.8485 | 100% |  |  | 0
23026247500 | 2000 | EX | INVESTIGATE EASEMENT & ROW | 145 BURT RD | B | 5841 | 0 | -5841 | 100% |  |  | 0
23026247700 | 587 | EX | INSTALL NEW GMB SETTING | 3111 SPURR RD | F | 92317.8265 | 96486.51 | 4168.6835 | 5% |  |  | 0 | TICKET# 39340 CCC#39340 CCC#39492 08-04-2023 RHAYES CCC#39795
23026247900 | 2000 | EX | ILI AUXILIARY WORK | 1001 CHERRY BLOSSOM WY | A | 150000 | 0 | -150000 | 100% |  |  | 0
23026248200 | 557 | EX | EMER - INSTALL 2'-2" PMMP | 107 TRAFTON ST 2150 | A | 13154.2985 | 135.67 | -13018.6285 | -99% | 3 | 2 | 67.835 | INSTALLED 2 ' OF 2'' PMP PIPE ( TESTED PIPE FOR 20MNS-GOOD PER FOL R. VANDERPOOL) J.OCHOA
23026248300 | 558 | EX | EMER - RETIRE ~2'-2"PMP | 107 TRAFTON ST 2150 | A | 129.6266 | 1647.72 | 1518.0934 | 1,171% |  |  | 0 | RETIRED 2' OF 2'' P MP MAIN DUE TO DAMAGE. J.OCHOA 01-11-2023
23026248400 | 557 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | 1384 FONTAINE RD | A | 5318.1948 | 2322.97 | -2995.2248 | -56% | 3 | 4 | 580.7425
23026248500 | 558 | EX | EMER-RETIRE 3' OF 2"PMMP MAIN | 1384 FONTAINE RD | A | 131.2422 | 0 | -131.2422 | 100% |  |  | 0
23026248900 | 559 | EX | INSTALL 100' OF 2"PMMP MAIN | 2093 FALLON RD | B | 30720.7606 | 28889.25 | -1831.5106 | -6% | 100 | 115 | 251.2109
23026249000 | 560 | EX | RETIRE 86' OF 2"CSMP MAIN | 2093 FALLON RD | B | 131.2422 | 0 | -131.2422 | 100% |  |  | 0 | ABN 102' OF 2'' COATED STEELE MAIN PURGED AND END SEALED
23026249300 | 557 | EX | EMER-INSTALL 5' OF 2"PMMP | 620 BLUE ASH DR | A | 8253.2559 | 5012.41 | -3240.8459 | -39% | 5 | 3 | 1670.8033 | REPLACED 3' OF DAMAGED 2" PLASTIC MAIN LINE WITH 2 EF COUPLINGS. PRESSURE TESTED THE THE NEW MAIN LINE AT 90PSIG FOR 1 HOUR. PRESSURE TEST OKAY. BHB, NGF. SOAP TESTED FINAL TIE IN AT OP. TEST OK. DMALONE
23026249400 | 558 | EX | EMER-RETIRE 5' OF 2"PMMP MAIN | 620 BLUE ASH DR | A | 131.2422 | 219.4 | 88.1578 | 67% |  |  | 0 | REPLACED 3' OF DAMAGES 2" PLASTIC MAIN LINE WITH 2 EF COUPLINGS. PRESSURE TESTED THE NEW MAIN LINE AT 90PSIG FOR 1 HOUR. PRSSURE TEST OK. BHB, NGF. SOAP TESTED FINAL TIE IN AT OP. TEST OK. DMALONE
23026249800 | 587 | EX | INSTALL EC 350 UNIT | 1900 RICHMOND RD | F | 7475.3221 | 5379.35 | -2095.9721 | -28% |  |  | 0 | CHECK TO SEE IF CARD WAS READY CMCHOLAN 1-27-2023 INSTALLED NEW EC350 CMCHOLAN 1-25-23
23026249900 | 588 | EX | RETIRE PAPER BILLING CHART | 1900 RICHMOND RD | F | 131.2422 | 463.02 | 331.7778 | 253% |  |  | 0 | REMOVED PAPER BILLING CHART, CMCHOLAN EBLANTON 1-25-23
23026250000 | 587 | EX | INSTALL EC 350 UNIT | 1490 BULL LEA RD | F | 5649.3221 | 6158.92 | 509.5979 | 9% |  |  | 0 | INSTALLED NEW HONEYWELL EC350 INPLACE OF CHART
23026250100 | 588 | EX | RETIRE PAPER BILLING CHART | 1490 BULL LEA RD | F | 131.2422 | 525.01 | 393.7678 | 300% |  |  | 0 | RETIRED PAPER CHART EBLANTON 3-16-23
23026250200 | 587 | EX | INSTALL EC-350 | 345 N BROADWAY ST | F | 6049.3221 | 8105.28 | 2055.9579 | 34% |  |  | 0 | INSTALLED IN HONEYWELL EC3560 IN PLACE OF CHART EBLANTON 3-14-23
23026250300 | 588 | EX | RETIRE PAPER BILLING CHART | 345 N BROADWAY ST | F | 131.2422 | 185.13 | 53.8878 | 41% |  |  | 0 | RETIRE PAPER BILLING CHART EBLANTON 3-14-23
23026250500 | 587 | EX | INSTALL EC 350 | 1587 BAUMANN DR | F | 7589.3221 | 6654.67 | -934.6521 | -12% |  |  | 0 | INSTALLED NEW HONEYWELL EC350 IN PLACE OF CHART EBLANTON 3-15-2023
23026250600 | 588 | EX | RETIRE PAPER BILLING CHART | 1587 BAUMANN DR | F | 131.2422 | 144.2 | 12.9578 | 10% |  |  | 0 | RETIRED PAPER BILLING CHART EBLANTON 3-15-23
23026250700 | 587 | EX | INSTALL EC 350 | 223 GOLD RUSH RD | F | 5649.3221 | 5810.87 | 161.5479 | 3% |  |  | 0 | RETIRED CHART INSTALLED NEW EC350
23026250800 | 588 | EX | RETIRE PAPER BILLING CHART | 223 GOLD RUSH RD | F | 131.2422 | 528.15 | 396.9078 | 302% |  |  | 0 | RETIRED PAPER CHART CCOX
23026251700 | 555 | EX | INSTALL 2060' OF 2" PMMP | MARLENA LN LT92 | B | 60788.4178 | 65881.72 | 5093.3022 | 8% | 2060 | 2523 | 26.1125
23026251800 | 562 | EX | RETIRE 900' OF 2"CSHP MAIN | 3111 SPURR RD | B | 4095.9621 | 12666.75 | 8570.7879 | 209% |  |  | 0
23026252000 | 557 | EX | EMER-INSTALL 3' OF 6"PMMP MAIN | 2575 PALUMBO DR | A | 12970.9861 | 13052.34 | 81.3539 | 1% | 3 | 3 | 4350.78
23026252100 | 558 | EX | RETIRE 3' OF 6"PMP MAIN | 2575 PALUMBO DR | A | 138.8485 | 0 | -138.8485 | 100% |  |  | 0
23026252200 | 557 | EX | EMER-INSTALL 3' OF 4"PMMP MAIN | 249 E REYNOLDS RD | A | 7839.2961 | 5339.51 | -2499.7861 | -32% | 3 | 3 | 1779.8367
23026252300 | 558 | EX | EMER-RETIRE 3' OF 4"PAMP MAIN | 249 REYNOLDS RD | A | 138.8485 | 0 | -138.8485 | 100% |  |  | 0
23026252600 | 557 | EX | INSTALL 3' OF 4"PMLP MAIN | 216 LOCUST AV | A | 9484.2961 | 16571.37 | 7087.0739 | 75% | 3 | 5 | 3314.274 | ABD 69 FT BS CUT OUT INLINE TEE AND INSTALLED 5 FT OF 4 IN PL TEST 90 LB FOR 1 HR OK SOAP TEST CPLG AND TEES AT OP FOR 5 MIN BAR HOLE BANKS NO GAS FOUND
23026252700 | 558 | EX | RETIRE 69' OF 4"BSLP MAIN | 216 LOCUST AV | A | 138.8485 | 0 | -138.8485 | 100% |  |  | 0 | ABDN 69 FT OF 6 IN BARE STEEL BLEW DOWN AND SEALED ENDS
23026252800 | 2000 | EX | INVERSTIGATE MAINS & SERVICES | FORBES RD |  | 18055 | 0 | -18055 | 100% |  |  | 0 | EXECUTED TO PENDING RELOCATION 23-0262937-00. D.LEMONS 2/15/2024
23026253900 | 584 | EX | RETIRE PRESSURE GAUGE | 1039 GOODWIN DR | F | 552.5683 | 0 | -552.5683 | 100% |  |  | 0
23026254000 | 584 | EX | RETIRE PRESSURE GAUGE | 1406 VERSAILLES RD | F | 552.5683 | 768.43 | 215.8617 | 39% |  |  | 0 | CC15136 CHART HAS BEEN REMOVED ISO UPDATED 1-31-23 CC15136 CHART HAS BEEN REMOVED ISO UPDATED 1-31-23
23026254400 | 561 | EX | INSTALL 420' OF 6"PMMP MAIN | 2210 GEORGETOWN RD | B | 9832.3981 | -558.31 | -10390.7081 | -106% | 420 | 426 | -1.3106
23026254500 | 562 | EX | RETIRE 356' OF 6"PMMP MAIN | 2210 GEORGETOWN RD | B | 114.3981 | 0 | -114.3981 | 100% |  |  | 0
23026254700 | 584 | EX | RETIRE PAPER GAUGE | 400 ANNISTON DR | F | 552.5683 | 247.65 | -304.9183 | -55% |  |  | 0 | REMOVED PAPER CHART, CCC 10587
23026254900 | 561 | EX | INSTALL 620' OF 8"CSHP MAIN | CONN TERRACE ST | B | 398676.678 | 230200.58 | -168476.098 | -42% | 620 | 646 | 356.3476 | TWALKER/KY 01-20-25: LEVEL 1 VARIANCE ADDED TO WMS.DOCS: JOB UNDER RUN DUE TO THE UNIVERSITY OF KENTUCKY TAKING OWNERSHIP OF ALL THE STREETS IN PROJECT AREA - CKY DID NOT HAVE TO RESTORE/REPLACE ANY STREETS OR HARD SURFACE REPAIRS WHICH LOWERED CONTRACT COST BY $53,000, ALSO PROJECT WAS COMPLETED FASTER THAN ESTIMATE BECAUSE OF THE LACK OF STREET REPAIRS WHICH LOWERED LABOR COST BY $11,000. CKY WAS ABLE TO USED 8" STEEL PIPE LEFT OVER FROM LEESTOWN ROAD WIDENING PROJECT THAT SAVED $50,000 AND SEGA WAS $12,000 LOWER THAN ESTIMATE. FINALLY, THIS WAS A CUSTOMER PAID RELOCATION 100% REIMBURSEMENT PROJECT AND CUSTOMER WAS REFUNDED OVER PAYMENT IN 2024
23026255000 | 562 | EX | RETIRE 620' OF 8"CSHP MAIN | CONN TERRACE ST | B | 116.356 | 330 | 213.644 | 184% |  |  | 0
23026256201 | 573 | EX | INSTALL VRG CONTROLLERS | 4940 ATHENS BOONESBORO RD | F | 47185.8659 | 79546.52 | 32360.6541 | 69% |  |  | 0 | DROPPING OF MATTERIAL 06-02-23 1324 CCC# 32360 CCC#32737 CC# 33503 CCC# 33503 CCC# 39939
23026256400 | 555 | EX | INSTALL 25' OF 2"PMMP MAIN | 1600 VILLA MEDICI PS | A | 8978.2187 | 9201.52 | 223.3013 | 2% | 25 | 18 | 511.1956 | INSTALLED 18' OF NEW MAIN AND ONE SERVICE LINE TO 1600 VILLA MEDICI TWALKER/KY 10-19-23: ISSUED BACK ORDER CANCEL 53922 FOR THE 250' COIL OF 2"PIPE WHICH IS NO LONGER AVAILABLE
23026257000 | 910 | EX | ST JOE - RETIRE RTU | 1590 HARRODSBURG RD | F | 138.8485 | 310.19 | 171.3415 | 123% |  |  | 0 | RETIRED OLD RTU EBLANTON 4-3-23
23026259000 | 557 | EX | EMER-INST 85'-4"PMMP MND311494 | BAHAMA RD | A | 25540.4028 | 23726.73 | -1813.6728 | -7% | 85 | 85 | 279.138 | 4" MAIN/PINK PL LEAKING UNDER STAMPED CONCRETE ENTRANCE TO COUNTRY CLUB RETIRED 85' AND INSTALLED 85' OF NEW MAIN-BORING DONE BY STANLEY PIPELINE, MAIN TEST 1 HR @90IB OK, TIE IN COMPLETE 02/20/2023 HMCKUNE
23026259100 | 558 | EX | EMER-RETIRE 85' OF 4"PAMP MAIN | BAHAMA RD | A | 138.8485 | 260.66 | 121.8115 | 88% |  |  | 0 | 4" MAIN/PINK PL LEAKING UNDER STAMPED CONCRETE ENTRANCE TO COUNTRY CLUB RETIRED 85' AND INSTALLED 85' OF NEW MAIN-BORING DONE BY STANELY PIPELINE, MAIN TEST 1HR @90 IB OK, TIE IN COMPLETE, 02/20/2023 HMCKUNE
23026260700 | 909 | EX | INSTALL ERX W/SUPER SOLAR | 881 REBECCA DR | F | 5629.9621 | 3972.47 | -1657.4921 | -29% |  |  | 0 | INSTALLED SUPER SOLAR AND MEDIUM PRESSURE RUN TO ER350, WILL BE FULL TIME MONITOR WHEN BUILT IN SCADA AND WILL DO P2P THEM CCC 19108, CMCHOLAN 3-6-23 FINISHED UP PAPERWORK AND SUMMITED ISO, CCC 19108 CMCHOLAN 3-6-23 0859 CCC-27261 DID P2P WITH GAS CONTROL ON MP, GAGE INSP OK, CCC 27123 CMCHOLAN EBLANTON 4-26-23 1600
23026260800 | 584 | EX | RETIRE PAPER CHART | 881 REBECCA DR | F | 138.8485 | 78.59 | -60.2585 | -43% |  |  | 0 | RETIRED PAPER CHART AND IS NOW CONNECTED ER350, CMCHOLAN CCC 19108
23026262700 | 557 | EX | EMER-INSTALL 5' OF 2"PMMP MAIN | 3905 PALOMAR COVE LN | A | 7460.3676 | 3582.24 | -3878.1276 | -52% | 5 | 5 | 716.448 | WORKED WITH JO. 23026262700 INSTALLED 5FT OF 020 MAIN DUE TO LEAKING S/L TEE. TESTED 5FT OF 020, 010 TEE,010 COUPLING AND 020 PURGE END CAP FOR 1HR AT 90LBS.TEST OK. SOAP TEST 020 EFC AT OP. FOR 5MINS TEST OK. BHB NGF
23026262800 | 558 | EX | EMER-RETIRE 5' OF 2"PMP MAIN | 3905 PALOMAR COVE LN | A | 124.7348 | 726.04 | 601.3052 | 482% |  |  | 0 | FROM MAIN TO MTR FOR 5MINS AT 90LBS.TEST OK. SOAP TEST FINAL TIE IN AT OP.TEST OK. BHB NGF WORKED WITH JO. 23026262700 INSTALLED 5FT OF 020 MAIN DUE TO LEAKING S/L TEE. TESTED 5FT OF 020, 010 TEE,010 COUPLING AND 020 PURGE END CAP FOR 1HR AT 90LBS.TEST OK. SOAP TEST 020 EFC AT OP. FOR 5MINS TEST OK. BHB NGF -- 010 S/L ELECTROFUSION TEE LEAKING AT SADDLE CONNECTION TO MAIN.REPLACED 5FT OF MAIN WITH NEW S/L TEE AND 020 PURGE END CAP.TESTED FOR 1HR AT 90LBS. TEST OK. SOAP TEST EFC COULPING AT OP. FOR 5MINS.TEST OK.TEST S/L FOR 3905
23026263000 | 557 | EX | INSTALL 5875' OF 2"/4"PMMP ENV | 1228 STANDISH WY | B | 728668.2681 | 763454.52 | 34786.2519 | 5% | 34230 | 6739 | 113.289
23026263100 | 558 | EX | RETIRE 6090' OF 4"BSMP MAIN | 1228 STANDISH WY | B | 124.7348 | 0 | -124.7348 | 100% |  |  | 0
23026263300 | 2000 | EX | INVESTIGATE ROAD R/W | COLONIAL DR | A | 7031 | 0 | -7031 | 100% |  |  | 0
23026263400 | 557 | EX | INSTALL 40'-4" PMMP | 1095 ROCKBRIDGE RD | B | 25145.0229 | 24778.88 | -366.1429 | -1% | 40 | 27 | 917.7363
23026263500 | 558 | EX | RETIRE 20'-4" PMMP | 1095 ROCKBRIDGE | B | 124.7348 | 98.08 | -26.6548 | -21% |  |  | 0
23026264300 | 557 | EX | EMER-INSTALL 5' OF 4"PMMP MAIN | 1055 DOVE RUN RD | A | 7456.0229 | 267.86 | -7188.1629 | -96% | 5 | 3 | 89.2867 | INSTALLED 3' OF 4" PL MAIN W/ EFC AND BF DE CAP- TEST 90# FOR 20MINS PER FOL DBANKS- SOAP TEST FINALTIEIN @ OP TEST OK- BHB NGF CONTENT VERIFIED DMARSTO 3/10/23
23026264400 | 558 | EX | EMER-RETIRE 520'- 4"PAIP MAIN | 1055 DOVE RUN RD | A | 124.7348 | 325.83 | 201.0952 | 161% |  |  | 0 | ABN 520' SECTION OF 4" PL MAIN- PURGE ABN SECTION OF MAIN W/ AIR UNTIL 0% SUSTAINED- DMARSTO 3/10/23
23026264700 | 557 | EX | INSTALL 100' OF 3"PMLP MAIN | 625 COLUMBIA AV | A | 29526.7351 | 21922.36 | -7604.3751 | -26% | 100 | 100 | 219.2236 | 100' OF BS MAIN RETIRED AND REPLACED W/3" PE PL MAIN DUE TO CORROSION
23026264800 | 558 | EX | RETIRE 100' OF 3"BSLP MAIN | 625 COLUMBIA AV | A | 124.7348 | 6487.75 | 6363.0152 | 5,101% |  |  | 0 | 100' OF BS MAIN RETIRED AND REPLACED W/3" PE PL MAIN DUE TO CORROSION
23026265100 | 557 | EX | INSTALL 10'-3"PMLP | 524 GEORGETOWN ST | A | 37610.5067 | 203249.18 | 165638.6733 | 440% | 10 | 10 | 20324.918 | INSTALLED 10 FT OF PL TEST FROM POINT A TO B 90 LB FOR 20 MIN TEST OK SOAP TEST 2 CPLG AND ALL BAG HOLES AT OP BHBNGF MAIN READ -0.601 INSTALLED 2 ANODES
23026265200 | 558 | EX | RETIRE 10'-3" BSLP | 524 GEORGETOWN ST | A | 120.2184 | 190.67 | 70.4516 | 59% |  |  | 0 | RETIRED 10 FT OF 3 IN BS PIPE PURGED OUT AND SEALED THE INLINE TEE SIDE
23026265400 | 559 | EX | EMER - INSTALL 12' - 2" PMMP | 232 DESHA RD | A | 5370.5784 | 9462.49 | 4091.9116 | 76% | 12 | 12 | 788.5408 | TEST 2 IN MAIN FROM POINT A TO B TEST 90 LB FOR 20 MIN SOAP TEST TIEINS AT OP BAR HOLE BANKS NO GAS FOUND
23026265500 | 560 | EX | EMER - RETIRE 12' - 2" PMMP | 232 DESHA RD | A | 124.7348 | 165.55 | 40.8152 | 33% |  |  | 0
23026266000 | 2000 | EX | INVESTIGATE POSSIBLE ENCROACHM | 360 W LOUDON AV | B | 5397 | 0 | -5397 | 100% |  |  | 0
23026266300 | 557 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | HORTON | A | 7671.8121 | 4867.28 | -2804.5321 | -37% | 3 | 3 | 1622.4267
23026266400 | 558 | EX | EMER-RETIRE 3' OF 2"PMP MAIN | HORTON | A | 124.7348 | 0 | -124.7348 | 100% |  |  | 0
23026267200 | 557 | EX | INSTALL 60'-4" PMLP | 107 JESSELIN DR | B | 41669.6267 | 34888.84 | -6780.7867 | -16% | 60 | 89 | 392.0094
23026267300 | 558 | EX | RETIRE ~60'-4" BSLP | 107 JESSELIN DR | B | 120.2184 | 136.28 | 16.0616 | 13% |  |  | 0
23026267400 | 2000 | EX | RELOCATION CONFLICT ASSESSMENT | CONN TERRACE | B | 7977 | 0 | -7977 | 100% |  |  | 0
23026267700 | 558 | EX | EMER-RETIRE 40' OF 6"BSLP MAIN | INDIAN MOUND | A | 9430.1038 | 8203.54 | -1226.5638 | -13% |  |  | 0
23026267800 | 555 | EX | INSTALL 580' OF 2"PMMP MAIN | 3381 PEPPERHILL RD | B | 40516.7801 | 35753.76 | -4763.0201 | -12% | 580 | 670 | 53.3638
23026268200 | 557 | EX | INSERT 160' OF 3"PMLP MAIN | SAINT JOSEPH DR | A | 20952.5602 | 15778.59 | -5173.9702 | -25% | 160 | 165 | 95.6278
23026268300 | 558 | EX | RETIRE 160' OF 4"BSLP MAIN | SAINT JOSEPH DR | A | 117.7346 | 8055.67 | 7937.9354 | 6,742% |  |  | 0
23026268400 | 555 | EX | INSTALL 2000' OF 2"PMMP MAIN | STOLEN HORSE TC LT64 | B | 83632.6185 | 56232.52 | -27400.0985 | -33% | 2000 | 1997 | 28.1585
23026268800 | 910 | EX | RETIRE ER350 UNIT | 567 MITCHELL AV | F | 117.7346 | 116.17 | -1.5646 | -1% |  |  | 0
23026269800 | 0001 | EX | DOCUMENT MP SYSTEM COMBINATION | 3725 MAN O WAR BV | A | 71.7346 | 0 | -71.7346 | 100% |  |  | 0
23026270100 | 584 | EX | RETIRE REG STATION# 1020 | ROSE ST | F | 10605.8819 | 1847.24 | -8758.6419 | -83% |  |  | 0 | RETIRED STATION AND REMOVED REGS, MONITORED PRESSURE FOR 30 MIN AFTER RETIREMENT, SOAPED BLING FLANGES AND PLUGS, CCC 77786, CMCHOLAN 6-20-24 1500
23026270600 | 555 | EX | INSTALL 550' OF 2" PMMP | 3833 MERRIDEW WY | B | 42706.9586 | 43345.7 | 638.7414 | 1% | 550 | 530 | 81.7843
23026270700 | 2000 | EX | INVESTIGATE EASEMENT & R/W | 200 VISTA ST |  | 13106 | 0 | -13106 | 100% |  |  | 0
23026270800 | 2000 | EX | INVESTIGATE ROW AND EASEMENT | 424 CLAYTON AV |  | 13106 | 0 | -13106 | 100% |  |  | 0
23026271200 | 587 | EX | INSTALL LEGACY ERX | 1400 HARRODSBURG RD | F | 2907.8819 | 2465.58 | -442.3019 | -15% |  |  | 0 | INSTALLED LEGACY ERX IN PLACE OF OLD RTU AND TRANSMITTER EBLANTON 4-3-23
23026271600 | 573 | EX | PAPER ONLY TO SET UP WMS FAC | 2001 MERCER RD M&R | F | 139.7346 | 14353.75 | 14214.0154 | 10,172% |  |  | 0 | THIS JOB IS TO CREATE FUNCTIONS AND FACILITIES FOR THE TEMPORARY SKID REGUL ATOR SETTING RWILLIAMS PUT TEMP STATION BACK TOGETHER, CMCHOLAN 6-26-2023
23026272200 | 555 | EX | INSTALL 200' OF 2"PMMP MAIN | 604 MONTCLAIR DR | B | 23237.6457 | 27418.37 | 4180.7243 | 18% | 150 | 212 | 129.3319
23026272300 | 559 | EX | EMER-INSTALL 3" NC POLY VALVE | 1146 ROCKBRIDGE RD | A | 7421.5276 | 6810.69 | -610.8376 | -8% | 4 | 4 | 1702.6725 | REPLACED BROKEN CRITICAL VLV WITH NEW 030 POLY VLV. TEST PIPE,VLV,&CPLGS 90#1HOUR, TG. ST LTI OK. BHBNGF. R.CRAWFORD 4-28-23
23026272400 | 560 | EX | EMER-RETIRE 3"PV C16-87 | 1146 ROCKBRIDGE RD | A | 117.7346 | 85.95 | -31.7846 | -27% |  |  | 0 | REFER TO JOB#-23026272300 FOR COMMENTS. R.CRAWFORD 4-28-23
23026272600 | 555 | EX | INSTALL 875' OF 2"PMMP MAIN | HOMESTRETCH CR LT26 | B | 32780.4095 | 29299.51 | -3480.8995 | -11% | 875 | 739 | 39.6475
23026272700 | 557 | EX | EMER - INSTALL 5'-2" PMMP | 219 HIGHLAWN AV | A | 5551.3568 | 2367.44 | -3183.9168 | -57% | 30 | 3 | 789.1467
23026272800 | 558 | EX | EMER - RETIRE 5'-2" PMMP | 219 HIGHLAWN AV | A | 112.7299 | 0 | -112.7299 | 100% |  |  | 0
23026272901 | 555 | EX | INSTALL 2500' OF 2"PMMP MAIN | POLLY CT LT1 | B | 209814.7415 | 251654.55 | 41839.8085 | 20% | 2500 | 2675 | 94.0765
23026273000 | 559 | EX | INSTALL 20'-4"PMMP W/NEW VALVE | 1000 ANDOVER FOREST DR | A | 13458.2914 | 20711.38 | 7253.0886 | 54% | 20 | 20 | 1035.569 | LOWERED 4" MP PE MAIN,REPLACED CRITICAL VLV,TEST MAIN@90IB 1HR,TIED IN W/2 EF CPLG'S, SOAP TEST TIE IN,MOVE CV TO SOFT SURFACE 06/26/2023 HMCKUNE
23026273100 | 560 | EX | RETIRE 20'-4"PMMP W/C19-314 | 1000 ANDOVER FOREST DR | A | 117.7346 | 0 | -117.7346 | 100% |  |  | 0
23026273300 | 557 | EX | INSTALL 290' OF 4" PMMP | 208 CHINOE RD | B | 48321.0935 | 80935.68 | 32614.5865 | 67% | 291 | 337 | 240.1652
23026273400 | 558 | EX | RETIRE 283' OF 3" BSMP | 208 CHINOE RD | B | 67.1159 | 0 | -67.1159 | 100% |  |  | 0
23026273700 | 557 | EX | INSTALL 6' OF 2"PMMP MAIN | 4184 CLEMONS DR | A | 15141.0552 | 5850.76 | -9290.2952 | -61% | 6 | 3 | 1950.2533 | LEAKING CV ON STEM.REMOVED CV AND INSTALLED 3' OF 020PMP.TESTED PURGE TEE AND 3FT OF MAIN FOR 1HR AT 90LBS.TEST OK.SOAP TEST EFC'S AT OP FOR 5MINS AT OP.TEST OK. BHB NGF. REMOVED CV C9-113.
23026273800 | 558 | EX | RETIRE 2" POLY VALVE C9-113 | 4184 CLEMONS DR | A | 117.7346 | 3847.88 | 3730.1454 | 3,168% |  |  | 0 | LEAKING CV ON STEM.REMOVED CV AND INSTALLED 3' OF 020PMP.TESTED PURGE TEE AND 3FT OF MAIN FOR 1HR AT 90LBS.TEST OK.SOAP TEST EFC'S AT OP FOR 5MINS AT OP.TEST OK. BHB NGF. REMOVED CV C9-113.
23026273900 | 583 | EX | INSTALL 441 REG (WEST RUN) | 3005 OLD TODDS RD | F | 3436.7638 | 4130.38 | 693.6162 | 20% |  |  | 0 | (NOT ON-SITE GETTING PARTS TO COMPLETE JOB) G.HALE NOT ONSITE COLLECTING REG AND PARTS APARKS 05-18-23 1551 SWAPPED 461 REGS FOR 441 REGS 57S 1 3/4 ORFICE BROWN SPRING IN BOTH CONTROL AND MONITOR MAJOR INSP. COMPLETED ON BOTH REGS INLET@90# MON@55# CON@47# CCC# 33177 NOT ONSITE PAPER WORK ONLY APARKS 06-19-23 1000
23026274000 | 584 | EX | RETIRE 461 REGS (WEST RUN) | 3005 OLD TODDS RD | F | 117.7346 | 0 | -117.7346 | 100% |  |  | 0
23026274301 | 555 | EX | INSTALL 3400' OF 2"PMMP MAIN | CRAVAT PASS LT243 | B | 79169.604 | 82979.94 | 3810.336 | 5% | 3300 | 3399 | 24.413
23026275600 | 2000 | EX | CONFLICT ASSESSMENT | 2585 POLO CLUB | A | 8460 | 0 | -8460 | 100% |  |  | 0
23026276300 | 559 | EX | EMER-INSTALL 2"POLY VALVE | 3441 LAREDO DR | A | 10283.4841 | 6885.74 | -3397.7441 | -33% | 4 | 4 | 1721.435 | INSTALLED NEW CRIT.VLV. TEST VLV FOR 1 HOUR, TG. TEST 2 BYPASS, TG. TEST ALL TEES, TG. ST LTI'S, TG. ALL TIME FOR JOB# 23186718700 TO BE CHARGED BACK TO THIS JOB, R.CRAWFORD 6-23-23 REFER TO JOB# 23026276400 FOR COMMENTS. R.CRAWFORD 6-27-23
23026276400 | 560 | EX | EMER-RETIRE 2"VALVE C14-27 | 3441 LAREDO DR | A | 139.1159 | 0 | -139.1159 | 100% |  |  | 0 | REFERENCE COMMENTS FOR JOB # 23026276300. R.CRAWFORD 6-23-23 REPLACED BROKEN CV. TEST NEW CV AND PIPE WITH IT 90#1HR, TG. TEST ALL TEES 9#5MINS, TG. TEST BYPASS' 90#1HOUR, TG. ST ALL FINAL TI'S, TG. R.CRAWFORD 6-27-23
23026276900 | 562 | EX | RETIRE 250' OF 3"BSLP MAIN | ADDIE ST | A | 4585.4374 | 1716.17 | -2869.2674 | -63% |  |  | 0 | ABDN 252 FT OF 3 IN BS MAIN SOAP TEST 4 PAC CLAMPS AT OP FOR 5 MIN SOAP TEST END CAP AT OP FOR 5 MIN BHBNGF INSTALLED 1ANODE PURGED OUT OLD MAIN AND SEALED MAIN LEFT 36 FT LINE MARKER AT END
23026277000 | 557 | EX | EMER-INSTALL 15' OF 8"PMLP MN | 210 W MAXWELL ST | A | 23129.0935 | 19444.34 | -3684.7535 | -16% | 15 | 11 | 1767.6673 | INSTALLED 8 IN PL MAIN TEST FROM POINT A TO POINT B SOAP TEST ALL PAC CLAMPS AND CPLG AT OP FOR 5 MIN BHBNGF INSTALLED 2 ANODE
23026277100 | 558 | EX | EMER-RETIRE 15' OF 8"BSLP MN | 210 W MAXWELL ST | A | 139.1159 | 307.27 | 168.1541 | 121% |  |  | 0 | ABDN 11 FT 8 IN BS MAIN INSTALLED 11 8 IN PL MAIN TEST 90 LB FOR 1 HHR SOAP TEST FINAL TIE IN AT OP FOR 5MIN BHBNGF
23026277200 | 562 | EX | EMER-RETIRE 55' OF 6"PMLP MN | ROSE ST | A | 4206.4374 | 5550.64 | 1344.2026 | 32% |  |  | 0 | RETIRED 52' OF 6'-P-LP WITH E/F COUPLING AND DEAD END CAP. PURGED 52' OF ' MAIN OUT OF SERVICE. SOAP TESTED FINAL CONNECTION FOR 5 MINTES AT OP. TEST OKAY.
23026277300 | 561 | EX | INSTALL 265' OF 6"PMMP MAIN | 2585 POLO CLUB | B | 71789.4841 | 29277.24 | -42512.2441 | -59% | 265 | 258 | 113.4777 | JOB COMPLETED. 08312023
23026277400 | 562 | EX | RETIRE 285' OF 6"PMMP MAIN | 2585 POLO CLUB | B | 139.1159 | 439.67 | 300.5541 | 216% |  |  | 0 | JOB COMPLETED
23026277900 | 557 | EX | EMER - INSTALL 69'-6" PMLP | WINDSOR | A | 35367.5186 | 31362.92 | -4004.5986 | -11% | 75 | 75 | 418.1723 | INSTALLED 40' 060 PMP TESTED FOR 1HR AT 90LBS.TEST OK. SOAP TEST TIE INS AT OP.TEST OK. BHB NGF WORKED WITH 558
23026278000 | 558 | EX | EMER - RETIRE 69'-6" BSLP | WINDSOR | A | 139.1159 | 124.77 | -14.3459 | -10% |  |  | 0 | ABDN 40' OF 6'' STEEL WORKED WITH 557.
23026278200 | 557 | EX | EMER-INSTALL 185' OF 4"PMLP | 201 E 5TH ST | B | 28939.243 | 41688.69 | 12749.447 | 44% | 185 | 184 | 226.569
23026278300 | 558 | EX | EMER-RETIRE 181' OF 4"BSLP MN | 201 E 5TH ST | B | 139.1159 | 0 | -139.1159 | 100% |  |  | 0
23026278401 | 555 | EX | INSTALL 2300' OF 2"/4"PMMP MN | LONGRIDGE DR LT30 | B | 101330.2336 | 116796.05 | 15465.8164 | 15% | 2300 | 2949 | 39.6053
23026279100 | 555 | EX | INSTALL 300' OF 2"PMIP MAIN | 1590 WINNERS CR | B | 17364.828 | 7749.44 | -9615.388 | -55% | 300 | 161 | 48.1332
23026279700 | 2000 | EX | INVESTIGATE MAINS | ALEXANDRIA DR |  | 2993 | 0 | -2993 | 100% |  |  | 0 | EXCAVATION FOUND HP MAIN IS DEEPER THAN PLANNED ROADWAY IMPROVEMENTS OVER P IPE. EXISTING PIPE IS DEEPER THAN 7 FEET, WITH 1-2 FOOT OF CUT FOR DITCH O PLANNED OVER PIPELINE. D.LEMONS 7/11/2023
23026280100 | 560 | EX | RETIRE 10' OF 10"CSMP MAIN | 3090 HARRODSBURG RD | B | 139.1159 | 273.6 | 134.4841 | 97% |  |  | 0
23026280800 | 557 | EX | EMER-INSTALL 62' OF 4"PMLP | 944 LIBERTY | A | 28754.8748 | 63661.35 | 34906.4752 | 121% | 62 | 62 | 1026.796 | INSTALLE 40 FT 4 IN MAIN TEST FROM POINT A TO POINT B 90 LB FOR 1 HR TEST ALL TEES AT 90 LB FOR 5 MIN SOAP TEST EFC AND BOLTD CPLG AT O OP FOR 5 MIN SOAP TEST 1 IN END CAP AT OP FOR 5 MIN INSTALL 1 ANODE
23026280900 | 558 | EX | EMER-RETIRE 62' OF 4"BSLP | 944 LIBERTY | A | 139.1159 | 2161.53 | 2022.4141 | 1,454% |  |  | 0 | RETIRED 36 FT OF BS AND 9 FT OF PL 4 IN LOW PRESSURE MAIN
23026282700 | 558 | EX | EMER-ABANDON 333' OF 2"PAMP | JANNELLE CT | A | 3839.4374 | 2936.25 | -903.1874 | -24% |  |  | 0 | ABND CUL-DE-SAC AFTER HIT LINE BY OTHER CONTRACTOR PER ENGINEER/FOL AFTER VERIFICATION NO CUSTOMERS ON GAS FOR SECTION OF MAIN TO BE ABND
23026283000 | 2000 | EX | INVESTIGATE CONFLICT & R/W | 100 CODELL DR | A | 7835 | 0 | -7835 | 100% |  |  | 0
23026283200 | 561 | EX | INSTALL 480' OF 2"PMMP MAIN | 100 CODELL DR | B | 59017.0935 | 47476.79 | -11540.3035 | -20% | 480 | 503 | 94.3873 | TWALKER/KY 10-20-23: REQUESTED CUSTOMER REFUND FOR THE CUSTOMER PAID RELOCA TION PROJECT.
23026283300 | 562 | EX | RETIRE 400' OF 2"BSMP MAIN | 100 CODELL DR | B | 139.1159 | 0 | -139.1159 | 100% |  |  | 0
23026283400 | 557 | EX | EMER - INSTALL 5'-3" PMMP | 1054 REDWOOD DR | A | 10280.7214 | 4304.94 | -5975.7814 | -58% | 5 | 5 | 860.988 | INST 5'- 3" NEW PL MAIN BY ENGINEERED PLAN. MCRAIG 7/10/23
23026283500 | 558 | EX | EMER - RETIRE 5'-3" PMP | 1054 REDWOOD DR | A | 139.1159 | 36.39 | -102.7259 | -74% |  |  | 0 | RETIRE 5' OF 3" PL MAIN DUE TO LEAK PER ENGINEERED PLAN. MCRAIG 7/10/23
23026284300 | 557 | EX | EMER-INSTALL 490' OF 2"PMMP | 2230 NICHOLASVILLE RD | A | 184478.0101 | 133294.53 | -51183.4801 | -28% | 520 | 493 | 270.3743 | BARE STEEL LP MAIN LEAKING, CREW WAS UNABLE TO EXPOSE LEAK, ABANDONED BS MAIN AND BORED IN 490'OF 2"P- PRE AND POST CAMERA COMPLETED-PT NEW MAIN 90LBS FOR 1HR PER ENGINEERING-SOAP TESTED TIE IN AT OP
23026284400 | 558 | EX | EMER-RETIRE 520' OF 4"BSMP MN | 2230 NICHOLASVILLE RD | A | 139.1159 | 223.9 | 84.7841 | 61% |  |  | 0 | REPLACED 493' OF 4'' S MP WITH 2'' PMP DUE TO GRADE 1 LEAK.DPI D304338.
23026284500 | 557 | EX | INSTALL 80'4" PMLP | 1000 KEES RD | A | 47424.0373 | 23619.02 | -23805.0173 | -50% | 80 | 60 | 393.6503 | TEST FROM POINT A TO B TO C 90 LB FOR 1 HR TEST OK TEST FINAL TIE IN AT OP OK BHBNGF INSTALLED 3 ANODES MAIN READ -0.591 TEST PAAC CLAMPS AT OP OK
23026284600 | 558 | EX | RETIRE 80'-4" BSLP | 1000 KEES RD | A | 139.1159 | 4684.11 | 4544.9941 | 3,267% |  |  | 0 | RETIRED 60 FT OF BS 4IN MAIN PURGED OUT AND REMOVED PIPE
23026285100 | 2000 | EX | LAND - INVESTIGATE ROW/STAKE | 209 CASTLEWOOD DR | B | 7586 | -4476.4 | -12062.4 | -159% |  |  | 0 | AWEBER 3/25/25 - PS&I CHARGED TO SMRP 557 JO
23026285200 | 2000 | EX | LAND - INVESTIGATE ROW/STAKE | 1732 RICHMOND RD | B | 8416 | 0 | -8416 | 100% |  |  | 0 | AWEBER 11/1/2023 - 6 EASEMENTS ACQUIRED BY LANDS CHRIS DAVIS AFTER INVESTIG ATION INTO LACK OF KYTC ROW ACQUISITION IN 1950'S.
23026285300 | 558 | EX | EMER - RETIRE 159'-3"BSLP | NICHOLASVILLE | A | 10816.0505 | 5197.96 | -5618.0905 | -52% |  |  | 0 | ABDN 159' OF 3'' BS LP.LEAK UNDER DRIVEWAY APPRON.MAIN NOT FEEDING ANY S/L.LEFT 15' OF 3'' ACTIVE. SOAP TEST END CAP AT OP FOR 5MINS TEST OK. BHB NGF. INSTALLED ANODE DENSO WRAPPED.
23026285400 | 560 | EX | RETIRE 300' OF 2"PIP MAIN | 4130 GEORGETOWN RD | B | 16251.9287 | 17543.67 | 1291.7413 | 8% |  |  | 0 | CAPPED OFF HP INLET TO ABANDONED STATION AND REMOVED STATION AND FENCE. CONTRACTORS REMOVED ALL VISIBLE LINE MARKERS AND RISERS IN TRAILER PARK. JOSH PASLEY 2/5/24
23026285500 | 584 | EX | RETIRE REG STATION #1129 | 4130 GEORGETOWN RD | F | 22153.7376 | 19139.56 | -3014.1776 | -14% |  |  | 0 | CCC#54039
23026285700 | 2000 | EX | INVESTIGATE CONFLICTS | 1800 NEWTOWN PK | B | 28768 | -10985.87 | -39753.87 | -138% |  |  | 0
23026286300 | 562 | EX | RETIRE 306' OF 3"BSLP MAIN | CHRYSALIS CT | A | 7586.4374 | 10623.01 | 3036.5726 | 40% |  |  | 0 | ABN. 40' OF PLASTIC AND 306' OF STEEL MAIN. PURGE ALL GAS OUT. PLUGGED ENDS NGF AFTER PURGED. USED EF EC, ST AT OP, TG. R.CRAWFORD 9-5-23
23026286800 | 555 | EX | INSTALL 100' OF 2"PMIP MAIN | 3422 MONTAVESTA RD | A | 8938.3422 | 17844.41 | 8906.0678 | 100% | 100 | 101 | 176.6773 | SPOTTED UTILITIES WITH VAC TRUCK. BORED IN 100' OF 020 P MAIN, PRESSURE TEST 1 HOUR AT 90#, TG. ST LTI, TG. R.CRAWFORD 9-5-23
23026287600 | 559 | EX | INSTALL 30'-4" PMMP | 1918 OXFORD CIRCLE | A | 14529.6064 | 19740.37 | 5210.7636 | 36% | 30 | 2 | 9870.185
23026287700 | 560 | EX | RETIRE ~30'-4" PMP | 1918 OXFORD CIRCLE | A | 124.9261 | 6450.91 | 6325.9839 | 5,064% |  |  | 0
23026288000 | 557 | EX | EMER - INSTALL 5'-2" PMMP | 3438 BIRKENHEAD | A | 3242.0133 | 267.7 | -2974.3133 | -92% | 5 | 5 | 53.54 | RELACED 5' OF 020 PMP DUE TO SOCKET ON TEE LEAKING. TESTED 5' OF 020 FOR 1HR AT 90LBS.TEST OK. SOAP TEST 2 2'' EFC AT OP. TEST OK. BHB NGF.
23026288100 | 558 | EX | EMER - RETIRE 5'-2" PMMP | 3438 BIRKENHEAD | A | 119.4953 | 1.39 | -118.1053 | -99% |  |  | 0 | RELACED 5' OF 020 PMP DUE TO SOCKET ON TEE LEAKING. TESTED 5' OF 020 FOR 1HR AT 90LBS.TEST OK. SOAP TEST 2 2'' EFC AT OP. TEST OK. BHB NGF.
23026288200 | 909 | EX | INSTALL VERIZON MODEM | 2350 FORTUNE DR | F | 4954.3422 | 1861.82 | -3092.5222 | -62% |  |  | 0
23026288300 | 910 | EX | RETIRE SATELLITE COMM EQUIP | 2350 FORTUNE DR | F | 119.4953 | 0 | -119.4953 | 100% |  |  | 0
23026288401 | 555 | EX | INSTALL 5500' OF 4"PMMP MAIN | 1021 PROVIDENCE PL PY | B | 319863.8272 | 294615.62 | -25248.2072 | -8% | 5500 | 5648 | 52.1628
23026289000 | 2000 | EX | METER PROVER REPLACEMENT | 2001 MERCER RD | A | 25000 | 0 | -25000 | 100% |  |  | 0
23026289100 | 577 | EX | INSTALL FENCE | 1313 OLD FRANKFORT PK | F | 26355.734 | 23214.65 | -3141.084 | -12% |  |  | 0 | NOT ON SITE, OFFICE PAPERWORK
23026290800 | 557 | EX | INSERT/INSTALL 160'-3"PMLP MN | 901 N BROADWAY ST | A | 46254.1681 | 45855.9 | -398.2681 | -1% | 160 | 173 | 265.063 | TEST FROM POINT A TTO B 90 LB FOR 1 HR TEST 2 IN HV TEE AND 2 IN MAIN FROM POINT A TO B 90 LB FOR 1 HR
23026290900 | 558 | EX | RETIRE 60' OF 3"BSLP MAIN | 901 N BROADWAY ST | A | 119.4953 | 7967.87 | 7848.3747 | 6,568% |  |  | 0 | ABDN 82 FT OF 4" BS MAIN AND 143 FT OF 2 " BS MAIN PURGED OUT AND SEALED UP AND INSTALLED ALL NEW 3 "PL MAIN
23026292000 | 555 | EX | INSTALL 2450' OF 2"PMMP MAIN | 376 WESTON PK LT1 | B | 75092.497 | 93897.7 | 18805.203 | 25% | 2450 | 2811 | 33.4037
23026292501 | 561 | EX | INSTALL 800' OF 2-4" PMMP | 1500 LEESTOWN RD | B | 229159.9279 | 232050.11 | 2890.1821 | 1% | 700 | 794 | 292.2545
23026292600 | 575 | EX | DOCUMENT 20'EASEMENT FROM UK | COLUMBIA AV | F | 38069 | 36650.73 | -1418.27 | -4% |  |  | 0
23026293700 | 561 | EX | INSTALL 74'-2" PMMP | FORBES DR | B | 102229.172 | 52073.55 | -50155.622 | -49% | 51 | 84 | 619.9232
23026293800 | 562 | EX | RETIRE 88'-2"&4" PMMP | FORBES DR | B | 119.4953 | 12669.1 | 12549.6047 | 10,502% |  |  | 0
23026294500 | 560 | EX | RETIRE 338' OF 4"BSLP MAIN | COCHRAN DR | A | 4190.6844 | 13645.62 | 9454.9356 | 226% |  |  | 0
23026294800 | 555 | EX | INSTALL 225' OF 2"PMMP MAIN | 491 RETRAC RD | B | 19109.6064 | 29004.09 | 9894.4836 | 52% | 225 | 263 | 110.2817
23026296000 | 555 | EX | INSTALL 220' OF 2" PMMP | 1801 ALEXANDRIA DR OUTLOT | B | 32123.3441 | 50792.43 | 18669.0859 | 58% | 220 | 210 | 241.8687
23026296200 | 561 | EX | INSTALL 1429'-6" PMMP | WILSON DOWNING RD | B | 234311.6314 | 975067.42 | 740755.7886 | 316% | 1459 | 1779 | 548.0986 | LEVEL 2 VARIANCE EXPLANATION APPROVED AND LOCATED IN JO WORKSPACE IN WMSDOC S. D.LEMONS 9/23/2024
23026296300 | 562 | EX | RETIRE 1479'-6" CS&PMMP | WILSON DOWNING RD | B | 122.9261 | 577.39 | 454.4639 | 370% |  |  | 0
23026296800 | 561 | EX | EMER - INSTALL 40'-4" PMMP | BRANNON RD | B | 32230.3112 | 48671.57 | 16441.2588 | 51% | 65 | 90 | 540.7952
23026296900 | 562 | EX | EMER - RETIRE 40'-4" CSMP | BRANNON RD | B | 122.9261 | 0 | -122.9261 | 100% |  |  | 0
23026297200 | 557 | EX | EMER - INSTALL 13'-2" PMMP | 3832 GRASSY CREEK RD | A | 9353.5801 | 5013.23 | -4340.3501 | -46% | 16 | 23 | 217.9665 | VALVE RETIRED.SOAP TEST END CAPS AT OP FOR 5MINS. TEST OK.BHB NGF LEAKING 020 P CRITICAL VALVE.LEAKING FROM STEM.RETIRED VALVE WITH 020 BYPASS.TESTED BYPASS AS MAIN FOR 1HR AT 90LBS.TEST OK INSTALLED TWO END CAPS AT VALVE TO ABDN VALVE.020 BYPASS MADE TO ACVTIVE MAIN AFTER
23026297300 | 558 | EX | EMER - RETIRE 2'-2" PMP | 3832 GRASSY CREEK RD | A | 122.9261 | 5943.6 | 5820.6739 | 4,735% |  |  | 0 | VALVE RETIRED.SOAP TEST END CAPS AT OP FOR 5MINS. TEST OK.BHB NGF LEAKING 020 P CRITICAL VALVE.LEAKING FROM STEM.RETIRED VALVE WITH 020 BYPASS.TESTED BYPASS AS MAIN FOR 1HR AT 90LBS.TEST OK INSTALLED TWO END CAPS AT VALVE TO ABDN VALVE.020 BYPASS MADE TO ACVTIVE MAIN AFTER
23026299400 | 2000 | EX | PERFORM CONFLICT ASSESSMENT | 1500 RUSSELL CAVE RD | B | 5636 | 0 | -5636 | 100% |  |  | 0
23026299700 | 555 | EX | INSTALL 325' OF 2"PMMP MAIN | 340 LEGION DR | B | 30286.964 | 52412.36 | 22125.396 | 73% | 325 | 426 | 123.0337 | TWALKER/KY 03-22-24: JOB OVER RUN DUE TO UNKNOWN CROSS BORE DISCOVERED AT TIE IN POINT FOR THIS PROJECT, CREWS HAD TO CORRECT THAT ISSUE WHICH ADDED ADDITIONAL TIME/MONEY FOR CONTRACTOR AND CONS COORDINATOR
23026300800 | 557 | EX | EMER-INSTALL 5' OF 3"PMLP | 436 OHIO ST | A | 4600.4752 | 5389.28 | 788.8048 | 17% | 5 | 5 | 1077.856
23026300900 | 558 | EX | EMER-RETIRE 5' OF 3"PLP MAIN | 436 OHIO ST | A | 122.9261 | 0 | -122.9261 | 100% |  |  | 0
23026301000 | 557 | EX | EMER-INSTALL 2' OF 4"PMMP MAIN | 1071 KELSEY DR | A | 4675.4752 | 3269.69 | -1405.7852 | -30% | 2 | 2 | 1634.845
23026301100 | 558 | EX | EMER-RETIRE 2' OF 4"PAMP MAIN | 1071 KELSEY DR | A | 122.9261 | 0 | -122.9261 | 100% |  |  | 0
23026302701 | 555 | EX | INSTALL 2700' OF 2"/4"PMMP | 1952 STOCKTON WY | B | 294198.9734 | 288308.66 | -5890.3134 | -2% | 2720 | 2662 | 108.3053
23026303700 | 557 | EX | EMER - INSTALL 5' OF 2" PMMP | 1291 LATONIA PK | A | 147.9261 | 617.17 | 469.2439 | 317% | 0 | 3 | 205.7233
23026303800 | 558 | EX | EMER - RETIRE 3' OF 2" PAMP | 1291 LATONIA PK | A | 124.9261 | 114.6 | -10.3261 | -8% |  |  | 0
23026303900 | 557 | EX | EMER-INSTALL 3'-2" PMMP MAIN | OXHILL DR | A | 5599.8489 | 2236.53 | -3363.3189 | -60% | 3 | 3 | 745.51
23026304000 | 558 | EX | EMER-RETIRE 3'-2"PAMP MAIN | OXHILL | A | 124.9261 | 0 | -124.9261 | 100% |  |  | 0
23026304100 | 562 | EX | RETIRE 667' OF 2"PMMP MAIN | 144 STATE ST | A | 5490.3441 | 4930.16 | -560.1841 | -10% |  |  | 0 | ABND MAIN ON STATE ST
23026305300 | 557 | EX | EMER-INSTALL 11'-2" PMMP | TATES CREEKS RD | A | 17054.8912 | 5063.47 | -11991.4212 | -70% | 11 | 11 | 460.3155 | INSTALLED 11' NEW 2"PL MAIN DURING DAMAGE/HIT LINE FROM BANK CAVE IN INSIDE UTILITY CONTRACTORS EXCAVATION-BHB,NGF-NGF UPON DEP
23026305400 | 558 | EX | EMER-RETIRE 11'-2" PMMP | TATES CREEKS RD | A | 124.9261 | 383.65 | 258.7239 | 207% |  |  | 0 | ABND 11'SECTION OF MAIN FOR DAMAGE
23026305800 | 586 | EX | RETIRE CHAIN LINK FENCE | 4130 GEORGETOWN RD | F | 502.1911 | 0 | -502.1911 | 100% |  |  | 0
23026305900 | 2000 | EX | INVESTIGATE MAINS & SERVICES | COOPER DR |  | 25741 | -4379.84 | -30120.84 | -117% |  |  | 0
23026307700 | 557 | EX | EMER - INSTALL 5'-2" PMMP | 920 WITTHUHN WY | A | 5646.8353 | 3856.33 | -1790.5053 | -32% | 5 | 5 | 771.266
23026307800 | 558 | EX | EMER - RETIRE 5'-2" PMP | 920 WITTHUHN WY | A | 123.4493 | 0 | -123.4493 | 100% |  |  | 0
23026307900 | 557 | EX | EMER-INSTALL 10'-4"PMMP/VALVE | 103 FOREST TL | A | 6246.9893 | 8083.2 | 1836.2107 | 29% | 10 | 10 | 808.32 | LEAKING MAIN VALVE.LEAK FROM STEM.REPLACED WITH NEW VALVE. TESTED 10' OF 040 WITH VALVE FOR 1HR AT 90LBS.TEST OK. SOAP TEST 2 EFC AT OP FOR 5MINS.TEST OK. BHB NGF
23026308000 | 558 | EX | EMER-RETIRE 10'-4"PMP/C8-150 | 103 FOREST TL | A | 123.4493 | 147.12 | 23.6707 | 19% |  |  | 0 | LEAKING MAIN VALVE.LEAK FROM STEM.REPLACED WITH NEW VALVE. TESTED 10' OF 040 WITH VALVE FOR 1HR AT 90LBS.TEST OK. SOAP TEST 2 EFC AT OP FOR 5MINS.TEST OK. BHB NGF
23026308900 | 557 | EX | EMER INSTALL 4' OF 3" PMMP | 1158 KELSEY DR | A | 3360.6855 | 2998.44 | -362.2455 | -11% | 10 | 4 | 749.61 | INST 4'- 3" PL MAIN PER ENGINEERED PLAN AND GAS STANDARDS. TEST NEW MAIN @ 90LB 5MIN OK. SOAP TEST TIE-IN @ OP OK. WORKED ON 12/19/23. MCRAIG 12/22/23
23026309000 | 558 | EX | EMER RETIRE 4' OF 3" PMP | 1158 KELSEY DR | A | 123.4493 | 218.46 | 95.0107 | 77% |  |  | 0 | RETIRE 4' OF 3" PL MAIN DUE TO LEAK IN ACCORDNANCE W/ ENGINEERING AND GAS STANDARDS. TEST NEW 4' PL @ 90LB 5MIN OK. SOAP TEST TIE-IN. WORKED 12/19/23. MCRAIG 12/22/23
23026309100 | 557 | EX | EMER-INSTALL 4'OF 2"PMMP MAIN | 2009 FAMILY CR 4 | A | 4579.9666 | 2952.18 | -1627.7866 | -36% | 4 | 4 | 738.045 | INST 4'- 2" PL MAIN. TEST MAIN @ 90LB 5MIN OK. SOAP TEST TIE-IN @ OP OK. BHB NGF. CGI MAIN AND SVC OK. WRK 12/20/23. MCRAIG 1/3/24
23026309200 | 558 | EX | EMER-RETIRE 4' OF 3"PMP MAIN | 2009 FAMILY CR 4 | A | 123.4493 | 259.03 | 135.5807 | 110% |  |  | 0 | RETIRE 4'- 2" PL MAIN DUE TO LEAKING WELD. WRK 12/20/23. MCRAIG 1/3/24
23026309300 | 557 | EX | EMER - INSTALL 5'-4" PMMP | 548 MERRIMAC DR | A | 8753.3832 | 3958.19 | -4795.1932 | -55% | 5 | 6 | 659.6983 | TEST 6 FT MAIN90LB FOR 20 MIN OK TEST 3 EF TEES 90 LB FOR 5 MIN SOAP TEST 2 EFC AT OP FOR 5 MINSOAP TEST 2 END 1 IN END CAPS AT OP OK BHBNGF
23026309400 | 558 | EX | EMER - RETIRE 5'-4" PMP | 548 MERRIMAC DR | A | 123.4493 | 158.95 | 35.5007 | 29% |  |  | 0 | CPLNG ON TEE LEAKING REPLACED 6 FT OF MAIN TEST NEW MAIN 90 LB FOR 20 MIN SOAP TEST FINAL TIE IN AT OP BHBNGF
24026310400 | 559 | EX | INSTALL VALVE & 5' OF 2" PMMP | 3101 RICHMOND RD | A | 11731.9279 | 10413.42 | -1318.5079 | -11% | 5 |  | 0
24026310500 | 560 | EX | RETIRE VALVE & 5' OF 2" PMP | 3101 RICHMOND RD | A | 160.3697 | 3446.12 | 3285.7503 | 2,049% |  |  | 0
24026311700 | 555 | EX | INSTALL 360' OF 2"PMMP MAIN | 295 CHILESBURG RD FG 49 | B | 32438.7712 | 38311.55 | 5872.7788 | 18% | 350 | 415 | 92.317
24026311800 | 557 | EX | EMER-INSTALL 5' OF 2"PMMP MAIN | 3051 KIRKLEVINGTON | A | 5455.4783 | 2941.72 | -2513.7583 | -46% | 5 | 4 | 735.43 | REPLACED 5 FT OF MAIN TEST ALL MATERIAL TO ALL GAS STANDERDS TEST MAIN 90 FOR 20 MIN TEST ALL TEES 90 FOR 5 MIN SOAP TEST EFC AND SL END CAPS AT OP FOR 5 MIN BHBNGF
24026311900 | 558 | EX | EMER-RETIRE 5' OF 2"PAMP MAIN | 3051 KIRKLEVINGTON DR | A | 123.4493 | 22.89 | -100.5593 | -81% |  |  | 0 | FOUND LEAK ON MAIN INSTALLED 5 FT OF MAIN TEST 90 LB FOR 20 MIN ABDN 5 FT OF MAIN
24026312600 | 2000 | EX | INVESTIGATE MAINS | 2515 LIBERTY RD |  | 5708 | 0 | -5708 | 100% |  |  | 0 | CONFLICT ASSESMENT COMPLETED AND NO CONFLICTS FOUND. D.LEMONS 6/27/2024
24026312700 | 562 | EX | RETIRE 310' OF 2"PMMP MAIN | 122 UNIVERSITY AV | A | 4362.2109 | 1540.57 | -2821.6409 | -65% |  |  | 0 | ABN MAIN DUE TO DEMO OF HOUSES - ABN 2" PLASTIC MAIN WITH 2" EF DEAD END CAP - SOAP TEST @ OP FOR 5 MIN TEST GOOD
24026314000 | 557 | EX | EMER-INSTALL 5' OF 4"PMMP MAIN | 3451 WINTHROP DR | A | 1932.1928 | 519.5 | -1412.6928 | -73% | 5 | 5 | 103.9
24026314100 | 558 | EX | EMER-RETIRE 5' OF 4"PAMP MAIN | 3451 WINTHROP DR | A | 160.3697 | 29.31 | -131.0597 | -82% |  |  | 0
24026314600 | 557 | EX | EMER-INSTALL 170' OF 2"/4"PMMP | 100 S HANOVER AV | B | 145005.519 | 141557.61 | -3447.909 | -2% | 173 | 161 | 879.2398
24026314700 | 558 | EX | EMER-RETIRE 120'- 8"BSMP MAIN | 100 S HANOVER AV | B | 160.3697 | 0 | -160.3697 | 100% |  |  | 0
24026316701 | 557 | EX | INSTALL 11245' OF 2"PMMP MAIN | SAINT PHILLIP DR | B | 1012154.1196 | 1084887.24 | 72733.1204 | 7% | 4000 | 10987 | 98.7428
24026316800 | 558 | EX | RETIRE 9920' OF 4"/6"BSLP MAIN | SAINT PHILLIP DR | B | 118.4933 | 717.72 | 599.2267 | 506% |  |  | 0 | GURU RETIRED 1-4"DRIP. SM 6/11.25
24026318600 | 557 | EX | EMER - INSTALL 11' OF 2" PMMP | 150 W LOWRY LN | A | 30688.3135 | 41990.31 | 11301.9965 | 37% | 11 | 11 | 3817.3009 | INST 8' AND 3' SECTION OF 2" P MP MAIN DUE TO LEAK PER ENGINEERED TIE-IN PLAN. TEST NEW MAIN @ 90LB 20MIN OK. SOAP TEST TIE-IN @ OP OK
24026318700 | 558 | EX | EMER - RETIRE 11' OF 2" PMP | 150 W LOWRY LN | A | 160.3697 | 180.42 | 20.0503 | 13% |  |  | 0 | RETIRE 11' OF 2" P MP MAIN DUE TO LEAK PER ENGINEERED TIE-IN PLAN. WORKED ON 2/7. MCRAIG 2/21/24
24026319600 | 909 | EX | INSTALL SOLAR BACK UP UNIT | 600 WOODWARD LN REAR | F | 10754.1928 | 6617.58 | -4136.6128 | -38% |  |  | 0
24026321000 | 560 | EX | PAPER-RETIRE ~250-3" PLP | 450 E NEW CIRCLE RD | B | 160.3697 | 0 | -160.3697 | 100% |  |  | 0 | JOB COMPLETED
24026321100 | 555 | EX | INSTALL 1400' OF 2" PMMP MAIN | 661 DAHLIA DR LT88 | B | 53956.9279 | 68220.66 | 14263.7321 | 26% | 1400 | 1351 | 50.4964
24026321200 | 909 | EX | INSTALL EQUIPMENT & BUILDING | 4940 ATHENS BOONESBORO RD | F | 181907.9279 | 177086.72 | -4821.2079 | -3% |  |  | 0 | CCC 86957 CCC 89138
24026321300 | 910 | EX | RETIRE EQUIPMENT | 4940 ATHENS BOONESBORO RD | F | 160.3697 | 0 | -160.3697 | 100% |  |  | 0
24026322700 | 909 | EX | INSTALL MIWI W/ SOLAR | 375 STONE RD | F | 25805.1928 | 18428.99 | -7376.2028 | -29% |  |  | 0
24026322800 | 910 | EX | RETIRE FACILITIES | 375 STONE RD | F | 160.3697 | 339.76 | 179.3903 | 112% |  |  | 0 | CCC 95201
24026323900 | 909 | EX | UPGRADE TO FULL TIME | 1107 COOPER DR | F | 10457.1928 | 15170.64 | 4713.4472 | 45% |  |  | 0 | CONVERTER ER350 TO FULL TIME MONITOR WITH ACP, CCC 82460, CMCHOLAN 7-29-24 FILLED OUT PAPERWORK FOR SOLAR PANEL INSTALL, CCC 86978, CMCHOLAN 9-3-24 1050
24026324000 | 910 | EX | UPGRADE TO FULL TIME | 1107 COOPER DR | F | 160.3697 | 90.3 | -70.0697 | -44% |  |  | 0 | UPGRADED TO FULL TIME MONITORED WITH ACP, CCC 82460, CMCHOLAN 1343
24026324400 | 909 | EX | UPGRADE TO FULL TIME | 551 NEWTOWN PK | F | 10901.0487 | 1964.52 | -8936.5287 | -82% |  |  | 0
24026324500 | 910 | EX | UPGRADE TO FULL TIME | 551 NEWTOWN PK | F | 121.4465 | 709.33 | 587.8835 | 484% |  |  | 0
24026324600 | 909 | EX | UPGRADE TO FULL TIME | 1590 HARRODSBURG RD | F | 10901.0487 | 8507.07 | -2393.9787 | -22% |  |  | 0 | CCC 82823 SUPER SOLAR INSTALL FORM COMPLETE, CCC 86978, CMCHOLAN 9-3-24 1200
24026324700 | 910 | EX | UPGRADE TO FULL TIME | 1590 HARRODSBURG RD | F | 121.4465 | 568.65 | 447.2035 | 368% |  |  | 0 | CCC 82823
24026324800 | 909 | EX | MIWI WITH SOLAR | 2108 NICHOLASVILLE RD | F | 13977.0487 | 10379.92 | -3597.1287 | -26% |  |  | 0
24026324900 | 910 | EX | RETIRE | 2108 NICHOLASVILLE RD | F | 121.4465 | 532.44 | 410.9935 | 338% |  |  | 0
24026325700 | 909 | EX | UPGRADE SCADA SYSTEM | 649 S ADDISON ST | F | 10627.0487 | 9180.49 | -1446.5587 | -14% |  |  | 0
24026325900 | 910 | EX | UPGRADE SCADA SYSTEM | 649 S ADDISON ST | F | 121.4465 | 362.79 | 241.3435 | 199% |  |  | 0
24026326200 | 909 | EX | UPGRADE SCADA SYSTEM | 785 CHERYL LN | F | 10627.0487 | 8523.81 | -2103.2387 | -20% |  |  | 0 | CCC 82629 CMCOX 7/30/24
24026326300 | 910 | EX | UPGRADE SCADA SYSTEM | 785 CHERYL LN | F | 121.4465 | 462.23 | 340.7835 | 281% |  |  | 0 | CCC 82629 CMCOX 7/30/24
24026326400 | 909 | EX | UPGRADE SCADA SYSTEM | 364 LIMA DR | F | 10627.0487 | 2879.61 | -7747.4387 | -73% |  |  | 0 | CCC-82971 CCC 87260, DID SOLAR PANEL PAPERWORK, CMCHOLAN 9-4-24 1600
24026326500 | 910 | EX | UPGRADE SCADA SYSTEM | 364 LIMA DR | F | 121.4465 | 499.97 | 378.5235 | 312% |  |  | 0 | CCC-82971
24026328300 | 557 | EX | EMER - INSTALL 26'-6" PMLP | MONTCLAIR DR | A | 28720.319 | 14201.79 | -14518.529 | -51% | 50 | 26 | 546.2227 | REPLACED 26FT OF 060 S WITH 060 P DUE TO ATMOS CORR. TESTED PIPE FOR 1HR AT 90LBS.TEST OK. SOAP TEST BOTH COUPLINGS AT OP FOR 5MINS.TEST OK. BHB NGF. INSTALLED 2 ANODES. DENSO WRAP MAIN.
24026328400 | 558 | EX | EMER - RETIRE 26'-6" BSLP | MONTCLAIR DR | A | 115.5402 | 2990.24 | 2874.6998 | 2,488% |  |  | 0 | REPLACED 26FT OF 060 S WITH 060 P DUE TO ATMOS CORR. TESTED PIPE FOR 1HR AT 90LBS.TEST OK. SOAP TEST BOTH COUPLINGS AT OP FOR 5MINS.TEST OK. BHB NGF. INSTALLED 2 ANODES. DENSO WRAP MAIN.
24026328700 | 2000 | EX | INVESTIGATE EASEMENTS/ROAD RW | ATHENS BOONESBORO RD | B | 10248 | 0 | -10248 | 100% |  |  | 0
24026330000 | 566 | EX | ABANDON S/L - DEMO/ CITY RQD | 2041 RICHMOND RD | A | 6179.2921 | 7688.07 | 1508.7779 | 24% |  |  | 0 | SL ABN DUE TO DEMO OF BLDG. TAP CREW AND WELDER CAPPED SL AT TAP BHB NGF, MRK BALL AT TAP, SOAP TEST AT OP OK, PLUGGED EXSISTING LINE JOB EXECUTE W/CAPITAL PACKET
24026330300 | 557 | EX | EMER - INSTALL 5'- 2" PMMP | 2104 WILTSHIRE PL | A | 11353.2418 | 10905.49 | -447.7518 | -4% | 20 | 6 | 1817.5817 | EXPOSED TWO ISOLATED STEEL COUPLINGS ON 020 PMP MAIN. REPLACED SECTION OF MAIN WHILE ON BYPASS.TESTED BYPASS FOR 20MINS AT 90LBS.TEST OK. TESTED MAIN FOR 1HR AT 90LBS.TEST OK. SOAP TEST COUPLINGS AT OP.TEST OK.
24026330400 | 558 | EX | EMER-RETIRE 5'-2"PMMP | 2104 WILTSHIRE PL | A | 118.4933 | 180.38 | 61.8867 | 52% |  |  | 0 | EXPOSED TWO ISOLATED STEEL COUPLINGS ON 020 PMP MAIN. REPLACED SECTION OF MAIN WHILE ON BYPASS.TESTED BYPASS FOR 20MINS AT 90LBS.TEST OK. TESTED MAIN FOR 1HR AT 90LBS.TEST OK. SOAP TEST COUPLINGS AT OP.TEST OK.
24026331300 | 566 | EX | RETIRE 3"PLP S/L & C18-82 VALV | 475 S ASHLAND AV | B | 132.893 | 0 | -132.893 | 100% |  |  | 0
24026331500 | 555 | EX | INSTALL 300' OF 2"PMMP MAIN | 2350 NORMAN LN | B | 28768.72 | 40161.78 | 11393.06 | 40% | 300 | 378 | 106.2481
24026331800 | 566 | EX | RETIRE 3"BSLP S/L & C14-35 VLV | 444 S ASHLAND AV | B | 66.4465 | 0 | -66.4465 | 100% |  |  | 0
24026331900 | 557 | EX | EMER - INSTALL 1' OF 2"PMMP | 3051 KIRKLEVINGTON DR | A | 3799.146 | 3472.1 | -327.046 | -9% | 1 | 1 | 3472.1 | REPAIRED DAMAGES SECTION OF PIPE. TEST REPAIR PIECE 90#20MINS, TG. ST LTI, TG. TEST FOR SECONDARY DAMAGE OK. R.CRAWFORD 4-2-24
24026332000 | 558 | EX | EMER - RETIRE 1' OF 2"PAMP | 3051 KIRKLEVINGTON DR | A | 121.4465 | 295.06 | 173.6135 | 143% |  |  | 0 | REPAIRED DAMAGED SECTION OF PIPE. TEST REPAIR PIECE 90#20MINS, TG. ST LTI. TEST FOR SECONDARY DAMAGE OK. R.CRAWFORD 4-2-24
24026332100 | 557 | EX | INSERT 50' OF 3" PMLP | 2069 HEATHER WY | A | 34491.8294 | 25644.18 | -8847.6494 | -26% | 50 | 50 | 512.8836
24026332200 | 558 | EX | RETIRE 52' - 4" CSLP | 2069 HEATHER WY | A | 121.4465 | 12630.36 | 12508.9135 | 10,300% |  |  | 0 | PART OF CAPITAL JOB
24026333000 | 557 | EX | EMER-INSTALL 18'-4"PMLP MAIN | 263 N LIMESTONE ST | A | 29428.3233 | 20568.01 | -8860.3133 | -30% | 18 | 18 | 1142.6672
24026333100 | 558 | EX | EMER-RETIRE 18'-4"BSLP MAIN | 263 N LIMESTONE ST | A | 121.4465 | 0 | -121.4465 | 100% |  |  | 0
24026334000 | 557 | EX | INSTALL 5' OF 2" PMMP | 5004 MARCHMONT WY | A | 3841.146 | 11358.98 | 7517.834 | 196% | 5 | 5 | 2271.796 | FOUND COMPRESSION COUPLINGS LEAKING - SQEEZED OFFF MAIN WITH GAGE FOR PRESSURE VERIFICATION - PRESSURE REMAINED @ 53 - SOAP TEST LAST CONNECTIONS @ OP FOR 5 MIN TEST GOOD
24026334200 | 558 | EX | RETIRE 5' OF 2" PMP | 5004 MARCHMONT WY | A | 121.4465 | 47.65 | -73.7965 | -61% |  |  | 0 | FOUND COMPRESSION COUPLINGS LEAKING - SQUEEZED OFF MAIN WITH GAGE FOR PRESSURE VERIFICATION- PRESSURE REMAINED @ 53 PSIG TEST NEW PIPE @ 90 FOR 1 HR TEST GOOD - INSTALLED 5 FT
24026336400 | 566 | EX | RETIRE ~71-4" PMMP S/L | 223 GOLD RUSH RD | A | 124.2298 | 2817.23 | 2693.0002 | 2,168% |  |  | 0
24026336500 | 565 | EX | INSTALL ~75'-4" PMMP S/L | 223 GOLD RUSH RD | A | 35134.784 | 26538.42 | -8596.364 | -24% | 80 |  | 0 | REPL SL WITH NEW 4" PLASTIC- TST SL AND MAIN IN ONE FOR 90LBS FOR 1HOUR TST OK- SOAP TST FINAL TIE IN @OP FOR 5MIN TST OK- BHB NGF- TROE
24026336600 | 587 | CO | INSTALL GMB SETTING | 223 GOLD RUSH RD | F | 48285.9326 | 23056.34 | -25229.5926 | -52% |  |  | 0
24026336700 | 588 | EX | RETIRE GMB SETTING | 223 GOLD RUSH RD | F | 65.2298 | 0 | -65.2298 | 100% |  |  | 0
24026336800 | 557 | EX | EMER - INSTALL 5' OF 2" PMMP | 3709 HORSEMINT TR | A | 3378.146 | 5104.57 | 1726.424 | 51% | 5 | 5 | 1020.914
24026336900 | 558 | EX | EMER - RETIRE 5' - 2" PMMP | 3709 HORSEMINT TR | A | 121.4465 | 0 | -121.4465 | 100% |  |  | 0
24026337000 | 555 | EX | INSTALL 675' OF 2"PMMP MAIN | 470 RETRAC RD | B | 60312.9634 | 44370.55 | -15942.4134 | -26% | 675 | 664 | 66.8231
24026338000 | 561 | EX | INSTALL 65'-2"&4" PMMP | 1295 CROSS KEYS RD | B | 74853.6852 | 59541.79 | -15311.8952 | -20% | 65 | 72 | 826.9693
24026338100 | 562 | EX | RETIRE 42'-2"&4" CSMP | 1295 CROSS KEYS RD | B | 118.4933 | 96.62 | -21.8733 | -18% |  |  | 0 | START DATE OF INSTALL JOB WAS 5/20/24 - COMMIT DATE FOR INSTALL 5/30, COMMIT DATE FOR ABANDONMENT 5/17 - START DATE WAS AFTER COMMMIT DATE - RTINCHER 6-21-24
24026338500 | 555 | EX | INSTALL 585' OF 2"PMMP MAIN | CAVERSHAM PARK LN LT2 | B | 37261.72 | 30882.37 | -6379.35 | -17% | 585 | 538 | 57.4022
24026339000 | 909 | EX | INSTALL OT NETWORK HARDWARE | 2350 FORTUNE DR | F | 3063.0974 | 5456.41 | 2393.3126 | 78% |  |  | 0 | CCC#68493
24026339100 | 910 | EX | RETIRE MODEM WITH IT UPGRADES | 2350 FORTUNE DR | F | 121.4465 | 563.82 | 442.3735 | 364% |  |  | 0
24026339400 | 562 | EX | RETIRE 322'-4" CSLP | RACE ST | A | 8828.6617 | 6251.56 | -2577.1017 | -29% |  |  | 0 | ABD 322 FT OF CS MAIN TEST TEE 90 LB FOR 5 MIN SOAP TEST END CAP AT OP SOAP TEST 1 IN CAP AT OP BHBNGF ABDN 322 FT CS 4 IN MAIN SOAP TEST END CAP AT OP BLEW OUT ABDN MAIN AND SEALED THE END UP ON IT MARKER BALL AT DEAD END CAP
24026339500 | 2000 | EX | RESEARCH ROAD RIGHT OF WAY | BLUE RIDGE DR | B | 7608 | 0 | -7608 | 100% |  |  | 0
24026339600 | 2000 | EX | INVESTIGATE AN MAP MAINS/SERV | SAVANNAH LN |  | 15407 | 0 | -15407 | 100% |  |  | 0 | LAND SERVICES WORK COMPLETE. ALL CHARGES BEING MOVED TO 24-0263613-00. D.LE MONS 9/23/2024
24026339800 | 557 | EX | INSTALL 35' OF 6"PMLP MAIN | 1800 GETTYSBURG RD | A | 45030.1866 | 43718.9 | -1311.2866 | -3% | 90 | 56 | 780.6946 | REPLACED 56' OF 060 P LP DUE TO CROSS BORE IN SEWER. TESTED MAIN FOR 1HR AT 90LBS.TEST OK. TESTED TEMP BYPASS FOR 20MINS AT 90LBS.TESTS OK. SOAP TEST BOLTED COUPLINGS AT OP.TEST OK.SOAP TEST CLAPS AND SADDLES AT OP.TEST OK
24026339900 | 558 | EX | RETIRE 25' OF 6"BSLP MAIN | 1800 GETTYSBURG RD | A | 139.7787 | 4843.71 | 4703.9313 | 3,365% |  |  | 0 | REPLACED 56' OF 060 P LP DUE TO CROSS BORE IN SEWER. TESTED MAIN FOR 1HR AT 90LBS.TEST OK. TESTED TEMP BYPASS FOR 20MINS AT 90LBS.TESTS OK. SOAP TEST BOLTED COUPLINGS AT OP.TEST OK.SOAP TEST CLAPS AND SADDLES AT OP.TEST OK
24026340000 | 583 | EX | EMER-INSTALL NEW PF REGULATOR | 199 EDDIE ST | F | 5188.1947 | 2398.18 | -2790.0147 | -54% |  |  | 0 | CC 69018 NEW REG INSTALLED 04-17-2024 APARKS GHALE RHAYES CC 69018 INSTALLED PF REG SN 201920474068 AND ASV SN 201920474092 APARKS GHALE RHAYES 04-18-2024
24026340100 | 584 | EX | EMER-RETIRE PF REGULATOR | 199 EDDIE ST | F | 66.4465 | 1088.91 | 1022.4635 | 1,539% |  |  | 0 | CC 69018 REMOVED PF REG AND SLAMSHUT INSTALLED NEW PF AND SLAMSHUT ALPARKS GHALE RHAYES
24026340200 | 555 | EX | INSTALL 600' OF 8"PMMP MAIN | 409 S LIMESTONE ST | B | 296422.5677 | 388585.22 | 92162.6523 | 31% | 600 | 629 | 617.7825
24026341200 | 2000 | EX | INVESTIGATE EASEMENT/LAND RIGH | 3478 GREENTREE RD | B | 8726 | 0 | -8726 | 100% |  |  | 0
24026341900 | 555 | EX | INSTALL 4250' OF 2"/4"PMMP | BLACKFORD PY LT1 | B | 152744.147 | 160153.35 | 7409.203 | 5% | 4250 | 4678 | 34.2354
24026342000 | 557 | EX | EMER - INSTALL 2' OF 2"PMMP | CREATIVE | A | 4292.2109 | 6607.96 | 2315.7491 | 54% | 5 | 2 | 3303.98 | INST 2'- 2" P MP MAIN DUE TO DAMAGE. INST PER ENGINEERED TIE-IN PLAN. WORKED 5/2/24. SOAP TEST TIE-IN OK. MCRAIG 5/14/24
24026342100 | 558 | EX | EMER - RETIRE 2' OF 2"PMP MAIN | CREATIVE | A | 139.7787 | 109.14 | -30.6387 | -22% |  |  | 0 | ABN 2' OF 2" P MP MAIN DUE TO DAMGE. PER ENGINEERED TIE-IN PLAN WORKED 5/2/24. MCRAIG 5/14/24
24026342400 | 561 | EX | INSTALL ~585'-2" PMMP | 3855 FOUNTAINBLUE LN | B | 85571.2987 | 81606.34 | -3964.9587 | -5% | 601 | 793 | 102.9084
24026342500 | 562 | EX | RETIRE ~600'-2" PMMP | 3855 FOUNTAINBLUE LN | B | 139.7787 | 324.53 | 184.7513 | 132% |  |  | 0
24026342700 | 2000 | EX | INVESTIGATE MAINS | 3855 FOUNTAINBLUE LN |  | 6332 | 0 | -6332 | 100% |  |  | 0 | ALIGNMENT AND CONFLICT ASSESMENT COMPLETE. WAITING ON PLAT RECORDING BY CUS TOMER. D.LEMONS 6/10/2024
24026343000 | 2000 | EX | INVESTIGATE MAINS | MASON HEADLEY RD |  | 29331 | 0 | -29331 | 100% |  |  | 0 | EASEMENTS OBTAINED. D.LEMONS 4/16/2025
24026343200 | 586 | EX | DEMO BLOCK BUILDING | ROSE ST | F | 279.5575 | 0 | -279.5575 | 100% |  |  | 0
24026343300 | 559 | EX | INSTALL 4" POLY VALVE | 1916 PAVILION WY | A | 18376.2056 | 7689.14 | -10687.0656 | -58% | 4 | 10 | 768.914
24026343400 | 560 | EX | RETIRE 4"POLY VALVE C19-270 | 1916 PAVILION WY | A | 139.7787 | 796.71 | 656.9313 | 470% |  |  | 0 | REPLACED VALVE C19-270 NEW VALVE NUMBER KY-C1414 REFER TO JOB#24-0263433-00 A WILLIAMSON 6-6-2024
24026343500 | 561 | EX | INSTALL 25'-8" PMLP | ELM TREE LN | B | 72915.1812 | 48462.2 | -24452.9812 | -34% | 35 | 24 | 2019.2583
24026343600 | 562 | EX | RETIRE 15'-8" CSLP | ELM TREE LN | B | 136.633 | 110 | -26.633 | -19% |  |  | 0
24026345300 | 560 | EX | RETIRE 350' OF 4"CSLP MAIN | 1064 MANCHESTER ST | A | 10488.3069 | 10006.29 | -482.0169 | -5% |  |  | 0 | RETIRED 4" CS MAIN DUE TO CORROSION- PURGED ABN MAIN OUT- CAPPED ABN MAIN- SOAP TST DEAD END CAP OF MAIN FOR 5MIN @OP TST OK- BHB NGF- INST 17LB ANODE INST TESTS STATION @ END OF MAIN- TROE GURU ADDED A TEST STATION FACILITY. SM 3/28/25
24026346300 | 557 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | 1809 ALEXANDRIA DR | A | 8304.9467 | 6040.26 | -2264.6867 | -27% | 3 | 3 | 2013.42 | INSTALLED 3' 2" PL MIAIN DUE TO DAMAGE PER ENG. TIE IN PLAN
24026346400 | 558 | EX | EMER-RETIRE 3' OF 2"PMMP MAIN | 1809 ALEXANDRIA DR | A | 139.7787 | 157.44 | 17.6613 | 13% |  |  | 0 | ABN 3' 2" PL MAIN PER ENG. TIE IN PLAN ABDN 322 FT CS 4 IN MAIN SOAP TEST END CAP AT OP BLEW OUT ABDN MAIN AND SEALED THE END UP ON IT MARKER BALL AT DEAD END CAP
24026346500 | 2000 | EX | INVESTIGATE LAND RIGHTS | JESSELIN DR | B | 5075 | 0 | -5075 | 100% |  |  | 0
24026346600 | 557 | EX | EMER-INSTALL 8' OF 4"PMLP | 307 LOCUST AV | A | 11094.6001 | 6502.78 | -4591.8201 | -41% | 10 | 8 | 812.8475 | REPLACED TWO SECTIONS OF MAIN DUE TO DAMAGES. ALL WORK PREFORMED BY GAS STANDARDS AND TESTED BY GAS STANDARDS. ALL TESTING AND CLERICAL PAPERWORK ON CAPITAL PACKET.
24026346700 | 558 | EX | EMER-RETIRE 8' OF 4"PMLP | 307 LOCUST AV | A | 139.7787 | 10.1 | -129.6787 | -93% |  |  | 0 | REPLACED TWO SECTIONS OF MAIN DUE TO DAMAGES. ALL WORK PREFORMED BY GAS STANDARDS AND TESTED BY GAS STANDARDS. ALL TESTING AND CLERICAL PAPERWORK ON CAPITAL PACKET.
24026348000 | 557 | EX | EMER-INSTALL 4' OF 3"PMMP MAIN | GRIBBON DR | A | 6161.5865 | 2333.5 | -3828.0865 | -62% | 4 | 4 | 583.375 | INST 4' OF 3" PLASTIC PIPE- TSTED PIPE FOR 20MIN @90LBS PER FOL - TST OK- SOAP TST FINSL TIE IN @OP FOR 5MIN TST OK- BHB NGF- TROE
24026348100 | 558 | EX | EMER-RETIRE 4' OF 3"PMMP MAIN | GRIBBON DR | A | 139.7787 | 0 | -139.7787 | 100% |  |  | 0
24026348200 | 559 | EX | INSTALL ~30'-4" PMMP | 223 GOLD RUSH RD | A | 17592.9326 | 16880.63 | -712.3026 | -4% | 50 | 47 | 359.1623 | INST 34' OF 4" PLASTIC MAIN AND 13' OF 2" PLASTIC MAIN- AND 58' OF 4" SL- TSTED ALL NEW MAIN FOR 90LBS FOR 1 HOUR- TST OK- SOAP TST FINAL TIE IN @OP FOR 5MIN TST OK- BHB NGF- TROE
24026348300 | 560 | EX | RETIRE ~30'-4" PMMP | 223 GOLD RUSH RD | A | 124.2298 | 3460.68 | 3336.4502 | 2,686% |  |  | 0 | ABN 25' OF 4" PLASTIC MAIN DUE TO CONFLICT WITH WATER BOX- SOAP TST DEAD END CAP ON 4" FOR 5MIN @OP TST OK- SOAP TST DEAD END CAP FOR 2" MAIN @OP FOR 5MIN TST OK- TROE
24026348400 | 2000 | EX | INVESTIGATE CONFLICTS | NEW CIRCLE RD |  | 38330 | 0 | -38330 | 100% |  |  | 0
24026348700 | 557 | EX | EMER - INSTALL 5' OF 2" PMMP | OVERBROOK FOUNTAIN | A | 5410.4082 | 8763.23 | 3352.8218 | 62% | 5 | 5 | 1752.646
24026348800 | 558 | EX | EMER-LEAK RETIRE C14-37 | OVERBROOK FOUNTAIN | A | 139.7787 | 693.84 | 554.0613 | 396% |  |  | 0
24026349300 | 559 | EX | INSTALL 4"POLY VALVE KY-C1556 | 3005 OLD TODDS RD | B | 32958.9947 | 22343.49 | -10615.5047 | -32% | 14 | 4 | 5585.8725
24026349400 | 560 | EX | RETIRE 10' OF 3"PMP MAIN | 3005 OLD TODDS RD | B | 139.7787 | 21.79 | -117.9887 | -84% |  |  | 0
24026350500 | 559 | EX | EMER-INSTALL 2"VALVE KY-C1586 | 1333 CENTRE PY | A | 5722.6534 | 3282.54 | -2440.1134 | -43% | 4 | 5 | 656.508
24026350600 | 560 | EX | EMER-RETIRE C15-66 POLY VALVE | 1333 CENTRE PY | A | 139.7787 | 0 | -139.7787 | 100% |  |  | 0
24026350800 | 560 | EX | PAPER ONLY MP RETIREMENT | MARQUIS AV | A | 139.7787 | 0 | -139.7787 | 100% |  |  | 0
24026351200 | 555 | EX | INSTALL 150' OF 2"PMIP MAIN | 1600 WINNERS CR LT40 | B | 12159.6055 | 14499.2 | 2339.5945 | 19% | 150 | 117 | 123.9248
24026351400 | 557 | EX | EMER - INSTALL 2'-2" PMMP | 2233 EXECUTIVE | A | 5752.0111 | 1846.55 | -3905.4611 | -68% | 2 | 2 | 923.275 | INST 2' OF 2" PLASTIC MAIN- TSTED FOR 90LBS FOR 20MIN PER FOL TST OK- SOAP TST POINT A AND POINT B FOR 5MIN @OP TST OK- BHB NGF TROE
24026351500 | 558 | EX | EMER - RETIRE 2'-2" PMP | 2233 EXECUTIVE | A | 136.633 | 14.54 | -122.093 | -89% |  |  | 0 | REMVED 2' OF 2" DAMAGED PLASTIC PIPE DUE TO HIT LINE- REPLACED WIT NEW 2" PLASTIC PIPE TSTED FOR 90LBS FOR 20MIN PER FOL SOAP TST POINT A AND POINT B @OP FOR 5MIN TST OK- TROE
24026351800 | 557 | EX | EMER-INSTALL 8' OF 3" PMMP | 720 PINE ST B | A | 8361.8798 | 6274.49 | -2087.3898 | -25% | 8 | 8 | 784.3112 | INSTALLED 8' OF NEW 030 P PIPE AFTER REMOVING DAMAGED SECTION OF MAIN. TEST PIPE 90#20MINS, TG. PER R.VANDERPOOL. R.CRAWFORD 7-26-24
24026351900 | 558 | EX | EMER-RETIRE 8' OF 3" PMP | 720 PINE ST B | A | 139.7787 | 6.23 | -133.5487 | -96% |  |  | 0 | TOOK OUT 8' OF 030 P PIPE. REPLACED W/ 8' OF NEW 030 P PIPE. R.CRAWFORD 7-26-24
24026352600 | 557 | EX | EMER - INSTALL 2'-2" PMMP | 1649 OLD LEESTOWN RD | A | 3613.4082 | 1939.02 | -1674.3882 | -46% | 2 | 3 | 646.34 | CONTRACTOR HIT 020 PMP WHILE DIGGING OUT SEWER BOX.SQUEEZE OFF IN BELLHOL TO MAKE SAFE.INSTALLED 3FT MAIN.TEST MAIN FOR 20MINS AT 90LBS.TEST OK.TES TEE 5MINS AT 90LBS.TEST OK.SOAP TEST EFC AT OP FOR 5MINS.TEST OK.BHB NGF
24026352700 | 558 | EX | EMER - RETIRE 2'-2" PMMP | 1649 OLD LEESTOWN RD | A | 139.7787 | 122.63 | -17.1487 | -12% |  |  | 0 | JO COMMENTS ON 557 AND 2412
24026353000 | 2000 | EX | LAND SURVEY FOR ENCROACHMENT | 4468 HARTLAND PY |  | 6441 | 0 | -6441 | 100% |  |  | 0
24026353800 | 557 | EX | INSTALL 180' OF 4"PMMP MAIN | 3385 NICHOLASVILLE RD | B | 169246.7693 | 167555.7 | -1691.0693 | -1% | 180 | 201 | 833.6104
24026353900 | 558 | EX | RETIRE 164' OF 4"CSMP MAIN | 3508 NICHOLASVILLE RD | B | 68.2637 | 419.02 | 350.7563 | 514% |  |  | 0
24026354000 | 555 | EX | INSTALL 850' OF 2"PMMP MAIN | 700 DOCKSIDE PK LT54C | B | 37954.6504 | 61100.31 | 23145.6596 | 61% | 850 | 546 | 111.9053 | COULD NOT INSTALL MAIN LINE ON DOCKSIDE PK. CT. BECAUSE ROAD WAS NOT INSTAL LED AT THIS TIME COMPLETED JOB PR ANDY ELLIOT DEVELLOPER WILL CALL WHEN REA DY, LSHARON 0/26/24
24026354300 | 555 | EX | INSTALL 1750' OF 2"PMMP MAIN | CRAVAT PASS LT241 | B | 59204.7838 | 49920.61 | -9284.1738 | -16% | 1750 | 1750 | 28.5261
24026354900 | 559 | EX | PAPER ONLY-LP STOPPLE FITTINGS | ASHLAND TR | A | 159.2637 | 0 | -159.2637 | 100% |  |  | 0
24026355100 | 558 | EX | EMER - RETIRE 12'-2" PMMP | 1735 SHARKEY WAY | A | 1059.1985 | 482.5 | -576.6985 | -54% |  |  | 0 | CONTRACTOR HIT 020 PMP MAIN DIGGING FOOTER FOR BUILDING.SQUEEZED OFF TO MAKE SAFE. END CAP INSTALLED BEFORE DITCH OF FOOTER. SOAP TEST END CAP AT OP.TEST OK. BHB NGF. ADV FOL OF ENCROACHMENT. ABDN 12FT OF MAIN.
24026355400 | 557 | EX | EMER-INSTALL 2' OF 2"PMMP MAIN | 1567 VAN BUREN | A | 5647.5068 | 4651.3 | -996.2068 | -18% | 4 | 2 | 2325.65 | SERVICE TEE AND SERVICE FOR 5MIN @90LBS TST OK- TSTED GAUGE TEES @90LBS FOR 5MIN TST OK- SOAP TST DEAD END CAPS ON GAUGE TEES FOR 5MIN @OP TST OK INST 2' OF 2" PLASTIC MAIN- TST MAIN @90LBS FOR 1HOUR, TST OK- SOAP TST FINAL TIE IN POINT A AND POINT B @OP FOR 5MIN TST OK- BHB NGFTST 2 PURGE TEES 5MIN @90LBS TST OK- TEST 2X1"
24026355500 | 558 | EX | EMER-RETIRE 2' OF 2"PAMP MAIN | 1567 VAN BUREN | A | 127.2637 | 7.56 | -119.7037 | -94% |  |  | 0 | REMOVED 2' OF 2" PLASTIC MAIN- INDTALLED 2" OF 2" PLASTIC MAIN- TST FOR 1HR @90LBS TST OK- SOAP TSTT FINAL TIE IN @OP FOR 5MIN TST OK- TROE
24026355900 | 555 | EX | INSTALL 250' OF 2"PMMP MAIN | 3216 CARRIAGE LN | B | 23765.9793 | 56306.29 | 32540.3107 | 137% | 250 | 278 | 202.5406 | TWALKER/KY 11-01-24: WMS WOULD NOT ALLOW JOB ORDER REVISION DUE TO UNPAID INVOICE ERROR, PROJECT PLANNED DIRECT BORE BUT CREWS HIT ROCK REASON FOR JOB COST OVER RUN.
24026356000 | 557 | EX | INSTALL 475' OF 2"PMMP MAIN | WILGUS AV | B | 124485.9173 | 138117.86 | 13631.9427 | 11% | 475 | 468 | 295.1236
24026356100 | 558 | EX | RETIRE 420' OF 2"BSLP MAIN | WILGUS AV | B | 127.2637 | 0 | -127.2637 | 100% |  |  | 0
24026356200 | 557 | EX | INSTALL NEW 4" CRITICAL VALVE | 4999 HARTLAND PY | A | 9922.9586 | 6237.92 | -3685.0386 | -37% | 2 | 2 | 3118.96 | INST NEW 4" POLY CRITICAL VALVE C16-184 PER ENGINEERED TIE-IN AND GS. TEST NEW VALVE @ 90LB 1HR OK. SOAP TEST TIE-IN @ OP OK. BHB NGF. CO ON 9/19 MCRAIG 9/20/24
24026356300 | 558 | EX | RETIRE 4" POLY VALVE C16-184 | 4999 HARTLAND PY | A | 127.2637 | 6591.98 | 6464.7163 | 5,080% |  |  | 0 | CUT OUT CRITICAL VALVE C16-184 PER ENGINEERED TIE-IN AND GS. MCRAIG 9/20/24
24026356400 | 566 | CO | RETIRE 4"PLP SERVICE LINE | 2101 SAINT MATHILDA DR | B | 127.2637 | 2580.83 | 2453.5663 | 1,928% |  |  | 0 | ABANDONED 4" SERVICE LINE USING EXISTING 4" CURB VALVE. THE REMAINING SERVICE LINE IS TO BE ABANDONED ON CAPITAL ABANDONMENT ORDER 24-0263168-00. JOSH PASLEY 8/13/24
24026357000 | 557 | EX | EMER-INSTALL 50' OF 4"PMLP | 137 SAINT ANN DR | A | 21585.4343 | 19570.62 | -2014.8143 | -9% | 50 | 50 | 391.4124 | INSTALLED NEW 040 P PIPE DUE TO CORROSION. TEST PIPE 90#1HOUR, TG. ST LTI, TG. MAIN READIN TAKEN AT "GOOD" SECTIONS OF PIPE FOR NEW INSTALL R.CRAWFORD 9-10-24
24026357100 | 558 | EX | EMER-RETIRE 50' OF 4"BSLP MAIN | 137 SAINT ANN DR | A | 127.2637 | 8645.9 | 8518.6363 | 6,694% |  |  | 0 | RETIRED PIPE DUE TO CORROSION FOR INSTALL OF NEW 040 P PIPE. MAIN READING TAKEN AT "GOOD" SECTIONS OF PIPE FOR INSTALL OF NEW PIPE. R.CRAWFORD 9-10-24
24026357600 | 562 | EX | RETIRE 490' OF 2"/4"PMP MAIN | FARM RD | A | 4637.6504 | 3022.51 | -1615.1404 | -35% |  |  | 0 | ABN PARTIAL MAIN - SOAP TEST DEAD END CAP @ OP FOR 5 MIN TEST GOOD -
24026358801 | 561 | EX | INSTALL 4200' OF 2"/4"PMMP | COOPER DR | B | 884925.4499 | 782267.64 | -102657.8099 | -12% | 2810 | 3897 | 200.7359
24026358900 | 562 | EX | RETIRE 914' OF 4"BSMP MAIN | COOPER DR | B | 135.7529 | 0 | -135.7529 | 100% |  |  | 0
24026360500 | 561 | EX | INSTALL 18'-2" PMMP | N FORBES RD | A | 23343.2435 | 10627.85 | -12715.3935 | -54% | 18 | 20 | 531.3925 | INST 35' OF 2" P MP MAIN PER ENGINEERED PLAN TO OFFSET IN 2 INTERSECTIONS FOR SEWER PROJECT. MCRAIG 10/29/24
24026360600 | 562 | EX | RETIRE 10'-2" PMMP | N FORBES RD | A | 127.2637 | 2874.37 | 2747.1063 | 2,159% |  |  | 0 | RETIRE 10' OF 2" P MP MAIN PER ENGINEERED PLAN AND GS TO OFFSET MAIN FOR SEWER PROJECT. MCRAIG 10/29/24
24026360700 | 561 | EX | INSTALL 230' OF 4"PMLP MAIN | 310 ROMANY RD | B | 12568.7288 | 19505.93 | 6937.2012 | 55% | 255 | 395 | 49.3821
24026360800 | 562 | EX | RETIRE 620' OF 4"BSLP MAIN | 310 ROMANY RD | B | 135.7529 | 110 | -25.7529 | -19% |  |  | 0
24026361300 | 561 | EX | INSTALL 750'-2" PMMP | SAVANNAH LN | B | 209702.6457 | 206114.64 | -3588.0057 | -2% | 750 | 735 | 280.4281
24026363300 | 2000 | EX | INVESTIGATE MAINS | 375 LISLE INDUSTRIAL RD |  | 9814 | 0 | -9814 | 100% |  |  | 0 | JOB RELEASED FOR CONSTRUCTION.
24026363400 | 560 | EX | PAPER ONLY MP RETIREMENT | ROSE ST | B | 127.2637 | 0 | -127.2637 | 100% |  |  | 0
24026363600 | 557 | EX | INSTALL 620' OF 4"PMMP MAIN | EASTIN RD | B | 142827.5782 | 275193.6 | 132366.0218 | 93% | 620 | 682 | 403.5097 | TWALKER/KY 11-19-24: WMS WOULD NOT ALLOW JOB ORDER TO BE REVISED DUE TO UNPAID INVOICES. JOB WILL OVER RUN.
24026363700 | 558 | EX | RETIRE 580' OF 4"BSMP MAIN | EASTIN RD | B | 135.7529 | 0 | -135.7529 | 100% |  |  | 0
24026365000 | 557 | EX | EMER-INSTALL 10' - 2" PMMP | FOUNTAINBLUE LN | A | 3276.1865 | 3040.57 | -235.6165 | -7% | 10 | 10 | 304.057 | INST 10' OF 2" P MP MAIN PER ENGINEERED PLAN DUE TO FAC DAMAGE. MCRAIG 10/30/24
24026365100 | 558 | EX | EMER-RETIRE 10' - 2" PMMP | FOUNTAINBLUE LN | A | 135.7529 | 2.82 | -132.9329 | -98% |  |  | 0 | CUT OUT 10' OF 2" P MP MAIN FROM DAMAGE. MCRAIG 10/30/24
24026365700 | 555 | EX | INSTALL 320' OF 2"PMIP MAIN | 3426 MONTAVESTA RD | B | 31921.5843 | 29754.73 | -2166.8543 | -7% | 320 | 365 | 81.5198
24026368600 | 555 | EX | INSTALL 640' OF 2" PMMP | 3980 FOUNTAINBLUE LN LT4 | B | 48981.3497 | 50384.93 | 1403.5803 | 3% | 645 | 682 | 73.8782
24026368800 | 559 | EX | INSTALL 5' OF 6" PMLP (PIF) | 256 ZANDALE DR | B | 22844.1865 | 53924.5 | 31080.3135 | 136% | 5 |  | 0
24026368900 | 560 | EX | RETIRE 5' OF 6" BSLP | 256 ZANDALE DR | B | 135.7529 | 806.6 | 670.8471 | 494% |  |  | 0
24026369000 | 557 | EX | INSTALL 65'-8" PMLP | 501 N LIMESTONE | A | 108434.8433 | 144966.81 | 36531.9667 | 34% | 65 | 178 | 814.4203 | INSTALLED NEW 8" PLASTIC MAIN, TESTED NEW MAIN AT 90PSI FOR 1 HR, TEST OKAY SOAP TEST FINAL TIE IN AT OP 5 MINS, TEST OKAY, BHBNGF
24026369100 | 558 | EX | RETIRE 70'-12'&6" BSLP | LIMESTONE | A | 108.1134 | 6.18 | -101.9334 | -94% |  |  | 0 | INSTALLED NEW 8" PLASTIC MAIN,TESTED NEW MAIN AT 90PSI FOR 1HR, TEST OKAY SOAP TEST FINAL TIE IN AT OP 5MINS, TEST OKAY, BHBNGF
24026370400 | 577 | EX | INSTALL RTU BUILDING | 4940 ATHENS BOONESBORO RD | F | 170.7529 | 0 | -170.7529 | 100% |  |  | 0
24026370600 | 561 | CO | INSTALL 32'-6" PMLP | 873 FURLONG DR | A | 29726.9608 | 8317.84 | -21409.1208 | -72% | 32 |  | 0
24026370700 | 562 | CO | RETIRE 20'-6" BSLP | 873 FURLONG DR | A | 112.4469 | 8109.18 | 7996.7331 | 7,112% |  |  | 0
24026371100 | 557 | EX | EMER-INSTALL 6' OF 8"PMMP | 2550 WINCHESTER RD | A | 5613.764 | 5742.34 | 128.576 | 2% | 10 | 6 | 957.0567 | INSTALLED 6' OF 8" PLASTIC TO REPAIR DAMAGE, TEST 90# FOR 1.0 HR TEST OK SOAP TEST FINAL TIE IN AT OP 5 MINS, TEST OK
24026371200 | 558 | EX | EMER-RETIRE 6' OF 8"PMP MAIN | 2550 WINCHESTER RD | A | 111.0024 | 397.39 | 286.3876 | 258% |  |  | 0 | ABANDONED 6' OF 8"PMP AND REPLACED WITH 6' OF 8" PMP. TEST 90# 1.0 HR TEST OK. SOAP TEST FINAL TIE IN AT OP 5 MINS TEST OK
24026371600 | 557 | EX | EMER - INSTALL 5' - 2" PMMP | 1120 FONTAINE RD | A | 4001.8556 | 6372.3 | 2370.4444 | 59% | 5 | 5 | 1274.46 | CUST . CUT A 2' MAIN IN HALF WITH A DITCH WITCH - PRESSURE TEST @ 90 FOR 1 HOUR - SOAP TEST LAST CONNECTION @ OP FOR 5 MIN TEST GOOD
24026371700 | 558 | EX | EMER - RETIRE 5' - 2" PMMP | 1120 FONTAINE RD | A | 111.0024 | 45.7 | -65.3024 | -59% |  |  | 0 | CUST. CUT 2' MAIN IN HALF WITH A DITCH WITCH - REPLACED DAMAGED PIPED - PRESSURE TEST @ 90 FOR 1 HOUR TEST GOOD -
24026372500 | 909 | CO | REPLACE VSAT WITH AT&T MODEM | 1314 WINCHESTER RD | F | 7998.4639 | 6289.92 | -1708.5439 | -21% |  |  | 0 | CCC 119698 SWITCHED PRIMARY COMMS FROM SAT TO CELL POINT 2 POINT VERIFIED WITH GAS CONTROL
24026372600 | 910 | CO | REPLACE VSAT | 1314 WINCHESTER RD | F | 111.0024 | 0 | -111.0024 | 100% |  |  | 0
24026372700 | 909 | CO | INSTALL SOLAR BACKUP | 1314 WINCHESTER RD | F | 9877.4639 | 7232.8 | -2644.6639 | -27% |  |  | 0
24026373100 | 909 | EX | INSTALL SOLAR BACKUP | 2350 FORTUNE DR | F | 9877.4639 | 7699.73 | -2177.7339 | -22% |  |  | 0 | INSTALL COMPLETE APARKS 02-12-25 1318 CCC 106887
24026375200 | 557 | EX | EMER-INSTALL 6' OF 2"PMMP MAIN | ADCOLOR DR | A | 7800.6918 | 6850.53 | -950.1618 | -12% | 6 | 6 | 1141.755
24026375300 | 558 | EX | EMER-RETIRE 6' OF 2"PMMP MAIN | ADCOLOR DR | A | 111.0024 | 0 | -111.0024 | 100% |  |  | 0
24026376700 | 557 | EX | EMER - INSTALL 3'-2" PMMP | 188 HEDGEWOOD CT | A | 7334.5817 | 3141.8 | -4192.7817 | -57% | 3 | 3 | 1047.2667 | JOB COMPLETE WITH CAPITAL PACKET
24026376800 | 558 | EX | EMER - RETIRE 3'-2" PMP | 188 HEDGEWOOD CT | A | 112.4469 | 6.4 | -106.0469 | -94% |  |  | 0 | COMPLETE WITH CAPITAL PACKET
24026376901 | 561 | EX | INSTALL 1218'-6" PMMP | RICHMOND RD | B | 626565.8286 | 707094.52 | 80528.6914 | 13% | 1248 | 1408 | 502.1978
24026377000 | 562 | EX | RETIRE 1140'-6" PMP | RICHMOND RD | B | 112.4469 | 571.78 | 459.3331 | 408% |  |  | 0
25026378600 | 561 | EX | INSTALL 42' OF 2"/4" PMMP MAIN | 201 STATE ST | B | 24410.382 | 26011.02 | 1600.638 | 7% | 20 | 41 | 634.4151
25026378700 | 562 | EX | RETIRE 30' OF 2"/4"PMMP MAIN | 201 STATE ST | B | 65.0024 | 0 | -65.0024 | 100% |  |  | 0
25026380600 | 909 | CO | INSTALL SCADA VISIBILITY | 1198 OAKWOOD DR | F | 10377.5378 | 10718.92 | 341.3822 | 3% |  |  | 0 | CCC 113973 CCC-117909 CCC-122674 INSTALL ER350 AND SOLAR PANEL, CMCHOLAN 5-29-25
25026380800 | 909 | CO | INSTALL SCADA VISIBILITY | 1621 KENSINGTON WY | F | 10377.5378 | 9824.48 | -553.0578 | -5% |  |  | 0 | CCC# 125214
25026389900 | 2000 | EX | INVESTIGATE EASEMENTS | 2089 VERSAILLES RD | A | 5560 | 0 | -5560 | 100% |  |  | 0
25026392100 | 2000 | EX | INVESTIGATE ROAD R/W FOR SMRP | 1600 NICHOLASVILLE RD |  | 3636 | 0 | -3636 | 100% |  |  | 0
25026395600 | 557 | EX | EMER-INSTALL 3' OF 3"PMMP MAIN | 511 GIBSON AV | A | 1646.6381 | 330.23 | -1316.4081 | -80% | 3 | 3 | 110.0767
25026395700 | 558 | EX | EMER-RETIRE 3' OF 3"PMP MAIN | 511 GIBSON AV | B | 160.2249 | 435.29 | 275.0651 | 172% |  |  | 0
25026398800 | 555 | EX | INSTALL 3670' OF 2"/4"PMMP MN | BUTTERMILK RD LT1 | B | 130832.2322 | 130345.4 | -486.8322 | 0% | 3670 | 3551 | 36.7067
25026399900 | 575 | EX | OBTAIN EASEMENTS | MASON HEADLEY RD | F | 9628 | 7818.06 | -1809.94 | -19% |  |  | 0
25026400900 | 557 | EX | EMER - INSTALL 2'-4" PMMP | RIDGEPOINT | A | 12461.1986 | 6330.01 | -6131.1886 | -49% | 2 | 2 | 3165.005
25026401000 | 558 | EX | EMER - RETIRE 2'-4" PMP | RIDGEPOINT | A | 137.1267 | 0 | -137.1267 | 100% |  |  | 0
25026402100 | 2000 | EX | UK HP/MP CONFLICT ASSESSMENT | ELIZABETH ST | B | 8482 | 0 | -8482 | 100% |  |  | 0
25026405400 | 557 | EX | EMER - INSTALL 2'-2" PMMP | 547 W NEW CIRCLE RD | A | 7065.0993 | 3579.32 | -3485.7793 | -49% | 2 | 2 | 1789.66
25026405500 | 558 | EX | EMER - RETIRE 2'-2" PMP | 547 W NEW CIRCLE RD | A | 137.1267 | 108.37 | -28.7567 | -21% |  |  | 0
25026408500 | 595R | EX | INSTALL ANODE BED FOR DRAIN | 399 SOUTHLAND DR | A | 6419 | 26718.81 | 20299.81 | 316% |  |  | 0 | TS FAC 891422 INSTALLED AT 399 SOUTHLAND TO MONITOR 600' OF 1952 CSHP MAIN WITH RT 1114579 IN LEXINGTON ANODE BOOK 23 / INSTALLED #8 WHITE WIRE ON WEST SIDE OF CABLE DUCT BANK CROSSING WITH 2 #32 ANODES ON WHITE WIRE WITH RED TAPE / INSTALLED #8 BLACK WIRE ON EAST SIDE OF CABLE DUCT BANK CROSSING WITH 2 #32 ANODES ON BLACK WIRE WITH RED TAPE / CABLE DUCT BANK EXPOSED AND WAS IN CONTACT WITH 8" CSHP 1952 MAIN / WINDSTREAM REMOVED CONCRETE THAT WAS IN CONFLICT & MAIN WAS RECOATED WITH DENSO S105 PASTE, DENSO LT TAPE & BLACK UTILITY TAPE / 05-21-25 JMM
25026409300 | 559 | EX | PAPER ONLY LP STOPPLE FITTINGS | SAINT PHILLIPS | A | 96.4144 | 6269.9 | 6173.4856 | 6,403% |  |  | 0
25026409400 | 595R | EX | INSTALL ANODE BED | 1015 ALEXANDRIA DR | A | 52965.9467 | 21290.62 | -31675.3267 | -60% |  |  | 0
25026410600 | 557 | CO | EMER-INSTALL 3'-2"PMMP MAIN | 2021 SAINT TERESA | B | 178.4144 | 59.2 | -119.2144 | -67% |  |  | 0 | REPL SECTION OF MAIN DUE TO FAILURE
25026410700 | 558 | CO | EMER-RETIRE 3' OF 2"PMMP MAIN | 2021 SAINT TERESA | B | 138.4144 | 59.14 | -79.2744 | -57% |  |  | 0
18026762102 | 587 | EX | INSTALL NEW GMB | 113 GREAT BUFFALO TC | F | 544123.4415 | 551963 | 7839.5585 | 1% | 20 |  | 0 | GCCC TICKET NOT REQUIRED AT THIS TIME 1/11/21 CFARIS 1/13/21 GCCC TICKET NOT REQUIRED AT THIS TIME CFARIS 1/26/21 GCCC TICKET NOT REQUIRED FOR THIS JOB CFARIS DID NOT ENTER PREMISE CCC TICKET NOT REQUIRED 3/8/21 CFARIS 3/10/21 GCCC TICKET NOT REQUIRED CFARIS CCC TICKET NOT REQUIRED 3/16/21 CFARIS CCC TICKET NOT REQUIRED 3/18/21 CFARIS CMCHOLAN 4-13-2021 CCC TICKET NOT REQUIRED ON 9/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK. ERX PLACED IN SERVICE ON 9/13/2021 CFARIS
18026845002 | 595I | EX | INSTALL THREE SSD UNITS | US 25 CINCINNATI | A | 142836.3088 | 151615.63 | 8779.3212 | 6% |  |  | 0 | INSTALLED TRITON COUPON TS CSE AND DAIRYLAND SOLID-STATE DECOUPLER (SSD) - DAIRYLAND SSD-2/2-5.0-100R (50-60) WITH EXTERNAL OR INTERNAL ISOLATION SWITCHWITH SWX-100 ENCLOSURE. TS FAC 408323 AT CARDOME, TS FAC 409481 AT BEVINS FARM REAR AND NEW TS FAC 865373 ON BEVINS FARM FIELD 2/3 ALL HAVE 1/2" ZINC RIBBON FOR AC MITIGATION AND COUPON TS WITH SSD INSTALLED. TS FAC 408320 IS NOW FLUSH MOUNT READ ONLY TS / REUSED APX 600' OF ZINC RIBBON AND ZINC MAT AT TS 408323 / REUSED 585' AND INSTALLED 565' OF ZINC RIBBON AND NEW ZINC MAT AT NEW TS 865373 / REUSED APX 1000' OF ZINC AND ZINC MAT AT TS 409481 / JMM
19026855200 | 2000 | EX | WOODLAND PARK SUB - GRADING | WOODLAND PARK SUB'N |  | 8668 | 0 | -8668 | 100% |  |  | 0
19026856100 | 584 | EX | RETIRE GAUGE | COMANCHE TR | F | 73.6972 | 0 | -73.6972 | 100% |  |  | 0 | WAITING ON PE APPROVAL AND ISO SKETCH CCC TICKET NOT REQUIRED ON 9/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026856800 | 561 | EX | INSTALL 3659'-2",4"&6" PMMP | 2ND ST | B | 1978069.5146 | 1309555.48 | -668514.0346 | -34% | 3659 | 3730 | 351.0873 | W. 2ND ST SEING TIES WILL NEED TO BE UPDATED ONCE ROAD CONSTRUCTION PROJECT IS COMPLETE. ALL POLES AND MANHOLES ARE BEING MOVED. OVERRUN EXPLANATION HAS BEEN COMPLETE AND LOADED INTO WMSDOCS WORKSPACE. D. LEMONS 12/23/2021
19026856900 | 562 | EX | RETIRE 2166'- 2"-6" P/CS/BS | 2ND ST | B | 94.7274 | 468.94 | 374.2126 | 395% |  |  | 0
19026858800 | 2000 | EX | ACQUIRE NEW REG STATION LOT | MUDDY FORD KY-922 RD | B | 25680 | 0 | -25680 | 100% |  |  | 0
19026874200 | 555 | EX | INSTALL 4600' OF 2"/4"/6"PMMP | 1341 CINCINNATI RD | B | 193673.3471 | 148082.56 | -45590.7871 | -24% | 4600 | 4504 | 32.878 | TWALKER/KY 11-15-21: PROJECT UNDER RUN WAS DUE TO LESS ROCK ON SITE THAN PL ANNED AND NO STREET/HARD SURFACE REPAIRS REQUIRED THAT LOWER CONTRACT COST BY $25,000. LACK OF ROCK AND HARD SURFACE REPAIRS SPED UP CONSTRUCTION TIME AND LOWER COMPANY COST BY $XXXX AND SEGA WAS $4000 LOWER THAN ESTIMATE. COMPANY COST LOWER BY $3000 THAN ESTIMATE.
19026877900 | 2000 | EX | INVESIGATE TIGER PROJECT | 100 2ND ST |  | 4480 | 0 | -4480 | 100% |  |  | 0 | PS&I EXECUTED AFTER FINAL REVISION WERE MADE. D.LEMONS 7/28/2021
19026899100 | 2000 | EX | INVESIGATE POSSIBLE ENCROACH | HOPE DR |  | 10000 | 0 | -10000 | 100% |  |  | 0
20026923500 | 2000 | EX | ILI FEASIBILITY STUDY | DELEPLANE RD | A | 60000 | 0 | -60000 | 100% |  |  | 0 | CCC # 18077 CMCHOLAN 4-6-2021 18498
20026929300 | 587 | EX | UPGRADE ELECTRONICS | 2011 HOOVER BV | F | 3038 | 6355.62 | 3317.62 | 109% |  |  | 0 | REPLACED EFC
20026929400 | 587 | EX | UPGRADE ELECTRONICS | 100 CLINTON ST | F | 3038 | 293.46 | -2744.54 | -90% |  |  | 0 | REPLACED EFC
20026929500 | 587 | EX | UPGRADE ELECTRONICS | US60 BP | F | 3038 | 5670.86 | 2632.86 | 87% |  |  | 0 | RETIRED OLD MINNI-AT INSTALLED NEW EC350 BLONE 07-11-2022
20026929600 | 587 | EX | UPGRADE ELECTRONICS | 982 CHENAULT RD | F | 3038 | 3403.36 | 365.36 | 12% |  |  | 0 | REPLACED EFC
20026929700 | 587 | EX | UPGRADE ELECTRONICS | 980 CHENAULT RD | F | 3038 | 3985.53 | 947.53 | 31% |  |  | 0 | REPLACED EFC
20026935000 | 588 | EX | RETIRE ELECTRONICS | 2011 HOOVER BV | F | 73.3494 | 0 | -73.3494 | 100% |  |  | 0 | REPLACE EFC JOB ON HOLD 2020 BECAUSE OF COVID 19
20026935100 | 588 | EX | RETIRE ELECTRONICS | 100 CLINTON ST | F | 73.3494 | 0 | -73.3494 | 100% |  |  | 0 | REPLACED EFC
20026935200 | 588 | EX | RETIRE ELECTRONICS | US60 BP | F | 73.3494 | 742.7 | 669.3506 | 913% |  |  | 0 | RETIRED OLD MINI-AT INSTALLED NEW EC350 BLONE 07-11-2022
20026935400 | 588 | EX | RETIRE ELECTRONICS | 980 CHENAULT RD | F | 73.3494 | 0 | -73.3494 | 100% |  |  | 0 | REPLACED EFC
20026942000 | 909 | EX | INSTALL I&C EQUIPMENT | COMANCHE TR | F | 16155.4774 | 14182.01 | -1973.4674 | -12% |  |  | 0 | CCC# 30920 CCC TICKET NOT REQUIRED ON 9/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026943100 | 909 | EX | INSTALL I&C EQUIPMENT | 202 BERRY AV | F | 16155.4774 | 14038.9 | -2116.5774 | -13% |  |  | 0 | CCC# 43654 INSTALLED ERX RETIRED PAPER CHART BLONE 2-25-2022
20026943200 | 584 | EX | RETIRE GAUGE | 202 BERRY AV | F | 91.4991 | 259.73 | 168.2309 | 184% |  |  | 0 | INSTALLED NEW LEGACY ERX RETIRED PAPER CHART BLONE 2-25-2022
20026945400 | 562 | EX | RETIRE 1431'-2"-4" BSLP | 2ND ST | B | 94.7274 | 1066.35 | 971.6226 | 1,026% |  |  | 0 | ABANDONMENTS OF MAINLINE WERE DONE WITH JO# 20-0269755-00.
20026952900 | 585 | EX | REPLACE ROOF | 298 MYRTLE AV | F | 4729 | 12246.18 | 7517.18 | 159% |  |  | 0
20026953701 | 557 | EX | INSTALL 6100' OF 2"/4"PMMP | WALLACE AV | B | 1430757.5003 | 1646234.22 | 215476.7197 | 15% | 6260 | 6099 | 269.9187 | TWALKER/KY 05-04-22: JOB OVER RUN DUE TO $65,000 SPEND ON OFF DUTY POLICE DUE TO HIGH CRIME/TRAFFIC AREA, STATE REQUIRED MILL/PAVING OF HOLME ST INCREASED CONTRACT COST BY $85,000. SEGA INCREASED BY $51,000 OVER EST.
20026953800 | 558 | EX | RETIRE 8800' OF 4"/6"BSLP MAIN | WALLACE | B | 240.2222 | 0 | -240.2222 | 100% |  |  | 0
20026954400 | 555 | EX | INSTALL 12,500' OF 6"PMMP | 1171 MIDWAY RD | B | 584465.9269 | 671261.21 | 86795.2831 | 15% | 12500 | 12516 | 53.6322 | GAS WAS ONLINE BEFORE COMMIT DATE. HAD TO FINISH UP RESTORATION AND PROJEC T INFO. STEVE CANOY 12/17/2021
20026954500 | 555 | EX | INSTALL 72' OF 4"CSHP MAIN | 1341 CINCINNATI RD | B | 48741.5249 | 50107.73 | 1366.2051 | 3% | 70 | 60 | 835.1288
20026954800 | 575 | EX | LAND FOR REG STATION SITE | 1341 CINCINNATI PK | F | 31714 | 31181.26 | -532.74 | -2% |  |  | 0
20026954900 | 573 | EX | INSTALL SKID REG STATION #1574 | 1341 CINCINNATI PK | F | 91083.0917 | 83537.33 | -7545.7617 | -8% |  |  | 0 | TUBE UP ONE RUN CCC #22458 CCC# 22583 CC# 23111 G.HALE 05-12-21 PLACED RUN 1 IN SERVICE ON 5/6/21 WITH TEMPORARY REGULATORS INSTALLED TO MEET COMMIT DATE WITH BUILDER RUN 2 OFF AND BLIND FLANGED PERMANENT EQUIPMENT ORDER WITH TENTATIVE DELIVERY DATE OF JUNE/JULY 2021 JOB CANNOT BE COMPLETED OR CLOSED OUT UNTIL PERMANENT EQUIPMENT IS INSTALLED CFARIS CCC# 43393 CCC# CALLED IN BY AL PARKS OR CONNER WIMPE CCC#55276 CWEMPE 2/15/22 GCCC# 56179 INSTALLED PERMANENT SLAMSHUT MOONEY'S COMMISSIONED STATION CWEMPE 2-16-22
20026960600 | 909 | EX | INSTALL NEW TRANSMITTERS | US 460 - GEORGETOWN RD | F | 5450.0793 | 9652.42 | 4202.3407 | 77% |  |  | 0 | INSTALLED NEW INLET AND OUTLET ROSEMONT 4088B TRANSMITTERS GHALE 8-22-2022
20026960700 | 910 | EX | RETIRE DAMAGE TRANSMITTER | US 460 - GEORGETOWN RD | F | 80.9227 | 542.77 | 461.8473 | 571% |  |  | 0 | INSTALLED NEW INLET AND OUTLET TRANSMITTERS GHALE 8-22-2022
20026963800 | 2000 | EX | OBTAIN AND RECORD EASEMENT | CHERRY BLOSSUM WY | A | 2215 | 0 | -2215 | 100% |  |  | 0
20026967000 | 575 | EX | AQUIRE EASEMENT | CHERRY BLOSSUM WY | F | 2271 | 2841.99 | 570.99 | 25% |  |  | 0
20026974601 | 557 | EX | INSTALL 6,500'-4"PMLP | ANN ST | B | 2219393.0276 | 2992726.14 | 773333.1124 | 35% | 6860 | 6647 | 450.2371
20026974700 | 558 | EX | RETIRE 6,900'-BSLP,CSLP,PLP | ANN | B | 66.2135 | 220 | 153.7865 | 232% |  |  | 0
20026975400 | 561 | EX | INSTALL 2250'-2" PMMP | W 2ND ST | B | 623618.1819 | 859560.09 | 235941.9081 | 38% | 2250 | 2396 | 358.748 | PROJECT COMPLETED ON 11-16-2021 D.LEMONS 3/2/2022: PROJECT OVERRUN WAS DUE TO ADDITIONAL TIME REQUIRED TO C OMPLETE PROJECT DUE TO MULTIPLE CONTRACTORS IN AREA DURING PROJECT. ESTIMA TED FOR 645 MAN HOURS, BUT REQUIRED 1018 MAN HOURS. ADDITIONAL $85K IN CONT RACT EXPENSES, $36K IN LABOR COSTS WHICH LEAD TO INCREASE OF $32K IN SEGA. THERE WAS A SLIGHT REDUCTION IN OTHER COST TO ACCOUNT FOR THE $147K OVERRUN .
20026975500 | 562 | EX | RETIRE 3515'-2",3",4"& 6" | W 2ND ST | B | 107.2796 | 142.7 | 35.4204 | 33% |  |  | 0 | PROJECT COMPLETE ON 11162021
20026978900 | 588 | EX | RETIRE GMB SETTING | 113 GREAT BUFFALO TC | F | 83.3805 | 0 | -83.3805 | 100% |  |  | 0 | JOB WAS ON HOLD UNTIL 2021 GCCC TICKET NOT REQUIRED ON 9/20/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026979000 | 566 | EX | RETIRE SERVICE | 113 GREAT BUFFALO TC | B | 83.3805 | 2450.84 | 2367.4595 | 2,839% |  |  | 0 | THIS IS PAPER KILL ONLY
20026979100 | 566 | EX | RETIRE SERVICE | 113 GREAT BUFFALO TC | B | 83.3805 | 0 | -83.3805 | 100% |  |  | 0
20026979201 | 565 | EX | INSTALL SERVICE TO GMB | 113 GREAT BUFFALO TC | B | 135908.7766 | 201470.53 | 65561.7534 | 48% | 67 |  | 0 | LEVEL 2 BUDGET VARIANCE LOADED INTO WMSSDOCS. D.LEMONS 9/22/21
20026979300 | 560 | EX | RETIRE 12'-8" CSHP |  | B | 134.3805 | 3655.53 | 3521.1495 | 2,620% |  |  | 0
20026979500 | 2000 | EX | ACQUIRE FLOOD MAPS | FRANKFORT |  | 448 | 0 | -448 | 100% |  |  | 0
20026981500 | 2000 | EX | INVESTIGATE REPLACEMENT RIGHTS | 7855 MCCRACKEN PK | B | 1641 | 0 | -1641 | 100% |  |  | 0
20026987100 | 0001 | EX | INSTALL HEATER ACCESSORY | DELAPLANE RD |  | 11868.661 | 0 | -11868.661 | 100% |  |  | 0
20026989800 | 555 | EX | INSTALL 800'-2" PMMP | 1 AMICK WY LT82 | B | 25809.9211 | 33245.15 | 7435.2289 | 29% | 800 | 1118 | 29.7363
20026990800 | 558 | EX | RETIRE INLET PIPING R 1502 | FRANKLIN AVE | B | 240.2222 | 0 | -240.2222 | 100% |  |  | 0
20026991300 | 555 | EX | INSTALL 350'-2" PMMP | 141 ARROWHEAD CT | B | 31069.259 | 19273.52 | -11795.739 | -38% | 350 | 337 | 57.1915 | 337 FT 2 " MEDIUM PRESSURE MAIN INSTALLED BY STANLEY PIPELINE YELLOW MED IUM DENSITY.PIPE
20026991500 | 2000 | EX | INVESTIGATE RAILROAD CROSSING | SENATE DR | B | 5472 | 0 | -5472 | 100% |  |  | 0 | HYDRO EXCAVATD MULTIPLE LOCATIONS FOR DEPTH ON HP
21026100500 | 2000 | EX | CONFLICT ASSESSMENT FOR RELO | 101 BIZZACK BV | B | 2800 | 0 | -2800 | 100% |  |  | 0
21026101700 | 587 | EX | INSTALL NEW GMB SETTING | 7855 MCCRACKEN PK | F | 57815.8896 | 40071.73 | -17744.1596 | -31% |  |  | 0 | INSTALLED NEW GMB SETTING
21026102400 | 588 | EX | RETIRE WOODFORD GMB | 7855 MCCRACKEN PK | F | 84.0131 | 0 | -84.0131 | 100% |  |  | 0 | RETIRED OLD GMB SETTING AFTER NEW SETTING PLACED IN SERVICE
21026103000 | 577 | EX | INSTALL CHAIN LINK FENCE | 1341 CINCINNATI PK | F | 16434.2505 | 20497.91 | 4063.6595 | 25% |  |  | 0 | RHAYES 08-24-2021 MONITORED FENCE INSTALLATION CCC 35764 CWEMPE PAPER WORK COMPLETION 2-16-22
21026106500 | 557 | EX | EMER - INSTALL 4' OF 2"PMMP | 199 QUAIL HOLLOW DR | A | 7343.079 | 7429.12 | 86.041 | 1% | 5 | 4 | 1857.28
21026106600 | 558 | EX | EMER - RETIRE 4' OF 2"PMMP | 199 QUAIL HOLLOW DR | A | 82.208 | 0 | -82.208 | 100% |  |  | 0
21026107100 | 909 | EX | INSTALL COMMUNICATIONS | COMPTON DR | F | 1691.2937 | 3375.12 | 1683.8263 | 100% |  |  | 0 | CCC#41275 CCC#17228 INSTALLED SUPER SOLAR KIT AND BATTERY UPGRADED TO RV50 CELL MODEM CONVERTED TO FULL TIME MONITORING RTU TICKET NUMBER 4339
21026107200 | 566 | EX | RETIRE 33' OF 4"PMMP S/L | 7855 MCCRACKEN PK MTRSTAT | B | 76.3208 | 1.8 | -74.5208 | -98% |  |  | 0
21026107300 | 565 | EX | INSTALL 140' OF 4"PMMP S/L | 7855 MCCRACKEN PK MTRSTAT | B | 57302.0236 | 53188.18 | -4113.8436 | -7% | 140 |  | 0
21026107400 | 0001 | EX | PM- TOYOTA ILI MATERIAL |  |  | 0 | 0 | 0 | 0% |  |  | 0
21026107500 | 557 | EX | EMER- INSTALL120'-2" PL | 11 WARWICK LN | B | 13083 | 2045.88 | -11037.12 | -84% | 120 | 155 | 13.1992 | INSTALLED 155' OF 2" P-MP MAIN DUE TO LEAK, SEE CAPITAL PACKET JO# 21-0261075-00, CDESPAIN 3-4-21
21026107600 | 558 | EX | RETIRE MAIN - LEAKAGE D304381 | 11 WARWICK LN | B | 56.3197 | 14663.28 | 14606.9603 | 25,936% |  |  | 0 | REPLACED 155' OF 2" P- MP MAIN, FOUND 2BOLT COUPLING PL-PL CORRODED AND LEAKING, SQUEEZED OFF, REPLACED MAIN, SEE JO PACKET 21-0261075-00 CDESPAIN 3-4-21
21026109600 | 555 | EX | INSTALL 351'-2" PMMP | 2051 ELMWOOD DR | B | 20339.7093 | 28594.76 | 8255.0507 | 41% | 351 | 397 | 72.0271
21026111902 | 555 | EX | INSTALL 7,500' OF 2"/6"PMMP | 2212 CYNTHIANA RD | B | 670404.9715 | 671698.12 | 1293.1485 | 0% | 10080 | 11549 | 58.1607 | LOWES (#207438) - MATERIAL FOR ECP - $27.62 + 10% = $30.38 U461423 9/2 3/2021 SITE SUPPLY (#207438) - MULCH LOGS - #424.00 + 10% = 466.40 U461423 9/23/2021
21026113900 | 555 | EX | INSTALL 1300' OF 2"/4"PMMP | FURLONG TC LT125 | B | 66451.1814 | 34584.47 | -31866.7114 | -48% | 1300 | 1130 | 30.6057 | MISSED COMMIT DATE DUE TO WEATHER UNDERRUN EXPLANATION: THE UNDERRUN VARIANCE IS DUE TO 50% ROCK EXCAVATION A ND 50% LESS DUST AND STONE. THE OVER HEAD EFFECT OF THESE REDUCTIONS ALSO PLAYED A FACTOR.
21026114000 | 558 | EX | EMER - RETIRE 145' OF 2"BSLP | 228 W MAIN ST | A | 3325.023 | 1254.24 | -2070.783 | -62% |  |  | 0 | RETIRED 146' OF 2" BSLP MAIN, SOAP TEST BOLTED DEAD END CAP AT OP, OK. SOAP TEST SADDLES AND PAC CLAMPS AT OP OK. BHB NGF. INSTALLED 9# ANODE. MAIN READ# -0.643. MAIN INSP OK. WHIMES 04/07/2021
21026114200 | 555 | EX | INSTALL 100'-2" PMMP | 854 HICKMAN HILL RD | B | 12690.4563 | 19306.24 | 6615.7837 | 52% | 100 | 45 | 429.0276
21026114300 | 588 | EX | RETIRE EFC | 982 CHENAULT RD | F | 111.0751 | 0 | -111.0751 | 100% |  |  | 0
21026115500 | 557 | EX | INSTALL 9560' OF 2"PMMP | TANGLEWOOD DR | B | 1674772.7999 | 2294747.45 | 619974.6501 | 37% | 9400 | 8771 | 261.6289
21026115600 | 558 | EX | RETIRE 9,590' OF BSLP & OTHER | TANGLEWOOD DR | B | 67.799 | 182.4 | 114.601 | 169% |  |  | 0
21026117600 | 584 | EX | RETIRE REG STATION 1522 | TANGLEWOOD DR | F | 3579.3015 | 0 | -3579.3015 | 100% |  |  | 0
21026117700 | 2000 | EX | RESEARCH ROAD ROW | TANGLEWOOD DR | B | 10317 | 0 | -10317 | 100% |  |  | 0
21026118100 | 555 | EX | INSTALL 5680'-2"/4" PMMP | CASTLE ACRE WY LT206C | B | 165876.9601 | 156088.03 | -9788.9301 | -6% | 5680 | 5606 | 27.843
21026118900 | 583 | EX | INSTALL REGULATORS | ISSAC SHELBY CR W | F | 6803.6557 | 4450.3 | -2353.3557 | -35% |  |  | 0 | CCC# 38381 REPLACED REGULATORS ON 9/16/2021 GCCC TICKET NOT REQUIRED ON 9/21/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026119000 | 584 | EX | RETIRE REGULATORS | ISSAC SHELBY CR W | F | 85.0089 | 572.72 | 487.7111 | 574% |  |  | 0 | REPLACED REGULATORS ON 9/16/21 CCC TICKET 38381 OBTAINED ON INSTALL JO CCC TICKET NOT REQUIRED ON 9/21/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
21026119400 | 559 | EX | PM- INST FIL/SEP TOYOTA STA | CHERRY BLOSSOM SPUR | C | 1687500 | 3658431.91 | 1970931.91 | 117% |  | 121 | 30234.9745
21026119500 | 560 | EX | PM-ABAN FOR FILTER INST TOYOTA | CHERRY BLOSSOM SPUR | C | 62500 | 522788.31 | 460288.31 | 736% |  |  | 0
21026119600 | 559 | EX | PM- TURNER STATION REPLACEMENT | CHERRY BLOSSOM | C | 1012500 | 4896097.44 | 3883597.44 | 384% |  | 68 | 72001.4329
21026119700 | 560 | EX | PM- TURNER STATION ABANDONMENT | CHERRY BLOSSOM | C | 62500 | 379030.64 | 316530.64 | 506% |  |  | 0
21026120200 | 559 | EX | PM-INS PIG REC/FILTER JIM BEAM | US 460 | C | 2579017 | 4126203.26 | 1547186.26 | 60% |  | 177 | 23311.8828
21026120300 | 560 | EX | PM-ABA FOR EQUIP INST JIM BEAM | US 460 | C | 62500 | 835157.07 | 772657.07 | 1,236% |  |  | 0
21026121300 | 559 | EX | PM- SEWELL REPLACEMENT | US 460 / US 62 | C | 1087500 | 4500640.76 | 3413140.76 | 314% |  | 75 | 60008.5435
21026121400 | 560 | EX | PM- SEWELL ABANDONMENT | US 460 / US 62 | C | 62500 | 692165.24 | 629665.24 | 1,007% |  |  | 0
21026121700 | 559 | EX | INSTALL 10' OF 6"PHHP MAIN | 167 MCKINNEY AV | B | 16348.9255 | 14437.27 | -1911.6555 | -12% | 60 | 4 | 3609.3175
21026121800 | 560 | EX | RETIRE 10' OF 6"PHHP MAIN | 167 MCKINNEY AV | B | 80.3582 | 0 | -80.3582 | 100% |  |  | 0
21026123000 | 575 | EX | INVESTIGATE/AQUIRE EASEMENT | LAKEVIEW PK | F | 17354 | 10986.84 | -6367.16 | -37% |  |  | 0
21026123600 | 557 | EX | REPLACE MAIN - LEAKAGE D253626 | 499 E MAIN ST | A | 5432.0527 | 2711.68 | -2720.3727 | -50% | 10 | 4 | 677.92
21026123700 | 558 | EX | EMER 10'-2" PMLP | 499 EAST MAIN ST | A | 85.0408 | 0 | -85.0408 | 100% |  |  | 0
21026124100 | 555 | EX | INSTALL 300'-2" PMMP | 98 FINLEY DR | B | 24076.2901 | 41987.03 | 17910.7399 | 74% | 300 | 267 | 157.2548
21026129300 | 2000 | EX | INVESTIGATE RV PARK ENCROACHME | MIDWAY RIGHT OF WAY |  | 5000 | 0 | -5000 | 100% |  |  | 0
21026130000 | 2000 | EX | CONFLICT ASSESMSNT W/ SEWER | SENECA TL |  | 5098 | 0 | -5098 | 100% |  |  | 0 | CITY 90% COMPLETE WITH PROJECT. ALL CONFLICTS RESOLVED. D.LEMONS 7/31/23
21026131001 | 557 | EX | EMER-INSTALL 10' OF 2"PMMP | MAPLE AV | A | 34334.8702 | 34645.29 | 310.4198 | 1% | 5 | 9 | 3849.4767
21026131100 | 558 | EX | EMER-RETIRE 10' OF 2"PAMP MAIN | MAPLE AV | A | 74.8797 | 0 | -74.8797 | 100% |  |  | 0
21026131200 | 555 | EX | INSTALL 4875' OF 2"/4"PMMP | 100 OLD OXFORD RD | B | 141168.2553 | 140463.01 | -705.2453 | 0% | 4775 | 2516 | 55.8279
21026131900 | 557 | EX | INSTALL 3843' OF 2"/4"PMMP MN | LYONS DR | B | 807937.3693 | 1468486.46 | 660549.0907 | 82% | 3843 | 3796 | 386.851 | PROJECT COST OVERRUN DUE TO ADDITIONAL TIME AND RESOURCES NEEDED. CONTRACT COSTS AND LABOR COSTS INCREASED DUE TO UNEXPECTED ROCK ENCOUNTERED DURING C ONSTRUCTION FOR BORE/OPEN CUT OF NEW MAIN. ADDITIONAL TIE-IN LOCATIONS WERE REQUIRED FOR INSTALL AND ABANDONMENT. INCREASED FLAGGING AND INCREASED RES TORATION COSTS ALSO CONTRIBUTED TO THE OVERRUN, AS WELL AS INCREASED SEGA C OSTS. MOLIVER 1/24/23
21026132000 | 558 | EX | RETIRE 3700' OF 4"/6"BSLP MAIN | LYONS | B | 52.2976 | 3419.35 | 3367.0524 | 6,438% |  |  | 0
21026132600 | 909 | EX | INSTALL NEW TRANSMITTERS | DELAPLANE RD | F | 15506.2901 | 14392.01 | -1114.2801 | -7% |  |  | 0 | CCC #34292 WAITING ON ISO
21026132700 | 910 | EX | RETIRE DAMAGED TRANSMITTERS | DELAPLANE RD | F | 82.634 | 0 | -82.634 | 100% |  |  | 0 | WAITING ON ISO SKETCH REPLACED TRANSMITTERS AND RV50 DAMAGED BY LIGHTENING
21026133100 | 587 | EX | INSTAL 2" MOONEY REGS | 982 CHENAULT RD | F | 9907.1191 | 11609.08 | 1701.9609 | 17% | 60 |  | 0 | REPLACED REGULATORS GCCC TICKET NOT REQUIRED
21026133200 | 588 | EX | RETIRE FISHER 399 REGS | 982 CHENAULT RD | F | 90.361 | 0 | -90.361 | 100% |  |  | 0 | REPLACED REGULATORS GCCC TICKET NOT REQUIRED
21026134400 | 562 | EX | RETIRE 98' OF 2"PMMP MAIN | SUGARTREE PARK | B | 3547.617 | 4653.06 | 1105.443 | 31% |  |  | 0
21026138201 | 557 | EX | EMER-INSTALL 480' OF 6"PMLP | WALNUT ST | A | 240281.6735 | 194700.21 | -45581.4635 | -19% | 480 | 472 | 412.5004 | CCC# 43819 CCC# 43967 TWALKER/KY 05-04-22: JOB CURRENTLY UNDER RUNNING SINCE CITY OF FRANKFORT HAS NOT PAVED STREET AND BILLED CKY - PAVING ESTIMATE AT $35,000.
21026138300 | 558 | EX | EMER-RETIRE 490' OF 6 5/8"BSLP | WALNUT ST | A | 82.634 | 71.35 | -11.284 | -14% |  |  | 0 | KBOTKINS ENTERED WIPE SAMPLE FOR OLIVER MAYNARD WHO IS ATTEMPTING TO COMPLETE THE JOB FOR CLOSE OUT. SAMPLE TAKEN 4/20/22 BUT SYSTEM WOULD NOT ACCEPT THAT DATE DUE TO THE CO DATE.
21026138900 | 555 | EX | INSTALL 650'-6" PMMP | 111 KADEN LN | B | 35779.3166 | 111751.03 | 75971.7134 | 212% | 650 | 675 | 165.5571 | COST INCREASE FOR LABOR HOURS AND CONTRACT COSTS DUE TO INCREASED DIRECTION AL BORE FOOTAGE, GPS DATA COLLECTION, INCREASED RESTORATION COSTS, ADDITION AL TIE-IN LOCATIONS NEEDED, AND INCREASE IN SEGA COSTS. - MOLIVER
21026141000 | 557 | EX | EMER - INSTALL 5'-4" PMMP | ROCKY CREEK | A | 427 | 0 | -427 | 100% | 5 | 2 | 0
21026141100 | 558 | EX | EMER - RETIRE 5'-4" PMMP | ROCKY CREEK | A | 68.3073 | 0 | -68.3073 | 100% |  |  | 0
21026142700 | 2000 | EX | PS&I OLD OXFORD PH 2 | CASTLE ACRE WY | B | 0 | 0 | 0 | 0% |  |  | 0
21026144300 | 557 | EX | EMER - INSTALL 2' OF 2"PMIP | 1118 CHICKASAW | A | 2750.8249 | 137.16 | -2613.6649 | -95% | 2 | 2 | 68.58
21026144400 | 558 | EX | EMER - RETIRE 2' OF 2"PAIP | 1118 CHICKASAW TL | A | 75.4968 | 0 | -75.4968 | 100% |  |  | 0
21026145200 | 583 | EX | EMER-INSTALL NEW BYPASS VALVES | WALNUT ST | F | 4285.9461 | 634.37 | -3651.5761 | -85% |  |  | 0 | CCC# 44725 BYPASS VALVES INSTALLED BY WADE SHIMFESSEL ALONG WITH CONTRACT CREW PAPERWORK COMPLETED BY CYNTHIA FARIS 12/27/21
21026145300 | 584 | EX | EMER-RETIRE BYPASS VALVE | WALNUT ST | F | 60.6987 | 0 | -60.6987 | 100% |  |  | 0 | VALVE REPLACED BY WADE SHIMFESSEL AND CONTRACT CREW ON 11/3/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/11/2022
21026147300 | 563 | EX | INSTALL 400'-4" PMMP-SER | 111 KADEN LN | B | 22333.8994 | 32919.84 | 10585.9406 | 47% | 400 |  | 0 | COMMIT DATE MISSED DUE TO WEATHER
21026149100 | 2000 | EX | INVESTIGATE LL SERVICE LINE | 1050 MIDWAY RD |  | 885 | 0 | -885 | 100% |  |  | 0
21026149500 | 557 | EX | EMER-INSTALL 26'-3"/4"PMMP MN | 480 SCHENKEL LN | A | 10953.3154 | 23766.13 | 12812.8146 | 117% | 26 | 26 | 914.0819 | SPLIT IN ALDYLA MAIN.INSTALLED BYPASS.REPLACED CRACKED MAIN AND INLINE TEE WHILE MAIN ON BYPASS.ALL TESTING INFO ON 21026149600 AND 21026149500 IN DOCS
21026149600 | 558 | EX | EMER-RETIRE 26'- 4"PAMP MAIN | 480 SCHENKEL LN | A | 61.5191 | 86.15 | 24.6309 | 40% |  |  | 0 | SPLIT IN ALDYLA MAIN.INSTALLED BYPASS.REPLACED CRACKED MAIN AND INLINE TEE WHILE MAIN ON BYPASS.ALL TESTING INFO ON 21026149600 AND 21026149500 IN DOCS
21026154200 | 2000 | EX | PS&I LANES RUN RELO | OLD OXFORD RD | B | 0 | 0 | 0 | 0% |  |  | 0
21026154400 | 2000 | EX | PS&I LYONS DR SMRP | LYONS DR | B | 0 | 0 | 0 | 0% |  |  | 0
21026155100 | 2000 | EX | SURVEY ENCROACHMENT | 310 VERSAILLES RD |  | 5000 | 0 | -5000 | 100% |  |  | 0
21026156300 | 2000 | EX | INVESTIGATE MAINS | US 25 |  | 5288 | 0 | -5288 | 100% |  |  | 0 | DEVELOPER TAKING RECOMENDED CHANGES TO ELLIMINATE CONFLICTS WITH EXISTING P IPELINE. D.LEMONS 1/6/2023
21026156600 | 555 | EX | INSTALL 230'-2" PMMP | 161 ARROWHEAD CT | B | 15538.521 | 17647.7 | 2109.179 | 14% | 230 | 209 | 84.4388
21026157100 | 555 | EX | INSTALL 600'-2" PMMP | 123 CANEWOOD CENTE DR | B | 21934.2504 | 29494.94 | 7560.6896 | 34% | 600 | 403 | 73.1884
21026157200 | 557 | EX | INSTALL 16' OF 3"PMMP MAIN | SKYVIEW DR | B | 11827.5319 | 56295.03 | 44467.4981 | 376% |  | 10 | 5629.503 | TWALKER/KY 02-24-22: WMS WOULD NOT ALLOW PROJECT TO BE REVISED DUE TO UNPAID INVOICES MESSAGE. JOB OVER RUN DUE TO UNKNOWN BOLTED COUPLINGS FOUND DURING CONSTUCTION AND SCOPE OF WORK WAS INCREASED TO REMOVE THOSE COUPLINGS IN THE PAVED STREET. TWALKER/KY 09-16-22: DURING CONSTRUCTION BOLTED COUPLING WERE FOUND ON MP GAS MAIN AND HAD TO BE REMOVED WMS WOULD NOT ALLOW REVISION. ADDITIONAL WORK INCREASED COMPANY LABOR BY $6000 SEGA INCREASED BY $4500 STREET CUT REPAIR REQUIRED AND ADDITIONAL CONTRACT RESOURCES INCREASED BY $27,000
21026157300 | 558 | EX | RETIRE 14' OF 3"CSMP MAIN | SKYVIEW DR | B | 72.8047 | 0 | -72.8047 | 100% |  |  | 0
21026994800 | 584 | EX | RETIRE STATION 1502 | HOLMES ST | F | 4108.4893 | 8422.17 | 4313.6807 | 105% |  |  | 0 | CCC# 37974 CCC#41227 CCC#41449 CCC# 41449 STATION ABANDONED ON 10/12/2021 PAPERWORK COMPLETED ON 11/2/2021 GCCC TICKET NOT REQUIRED ON 11/2/21 OFF SITE COMPLETING PAPERWORK CFARIS
21026998201 | 555 | EX | INSTALL 1930'-2"/4" PMMP | MAGELLAN LN LT1 | B | 114050.6727 | 114169.59 | 118.9173 | 0% | 1930 | 1934 | 59.0329 | GAS ON MAIN 11/01/2022
21026999700 | 561 | EX | INSTALL 125' OF 2"PMMP MAIN | BIZZACK BV | B | 28787.2695 | 22070.53 | -6716.7395 | -23% | 125 | 134 | 164.7054
21026999800 | 562 | EX | RETIRE 115' OF 2"PMMP MAIN | BIZZACK BV | B | 81.0887 | 0 | -81.0887 | 100% |  |  | 0
22026158100 | 555 | EX | INSTALL 70'-2" PMMP | 101 BRIARWOOD ST | B | 9277.6445 | 10660.65 | 1383.0055 | 15% | 70 | 57 | 187.0289 | INSTALED 57'OF 020PMMP.
22026160100 | 559 | EX | PM-GREENSITE I75 ILI DE RELO |  | C | 0 | 9503.69 | 9503.69 | 100% |  | 38 | 250.0971
22026160200 | 560 | EX | PM-GREENSITE I75 ILI DE ABAN |  | C | 0 | 105.53 | 105.53 | 100% |  |  | 0 | GIS HAD LESS FOOTAGE THAN WHAT WAS FIELD VERIFIED. NO FAC CREATED, DUE TO F ACT IT WAS BEING ABANDONED.
22026160400 | 557 | EX | EMER - REPAIR LEAK | 101 MOLLIE WY | A | 3388.6445 | 8003.12 | 4614.4755 | 136% | 20 | 3 | 2667.7067
22026160500 | 558 | EX | EMER - REPAIR LEAK | 101 MOLLIE WY | A | 69.6571 | 0 | -69.6571 | 100% |  |  | 0
22026163400 | 2000 | EX | INVESTIGATE MAINS | US HWY 460 | B | 1976 | 0 | -1976 | 100% |  |  | 0 | EXCAVATION SHOWED EXISTING PIPELINE 36" DEEP AND NOT IN DIRECT CONFLICT WIT H PROPOSED SEWER BORE (8' DEEP). D.LEMONS 3/15/2022
22026164800 | 2000 | EX | INVESTIGATE SERVICE LINE | 1020 MOSS LN | B | 3274 | 0 | -3274 | 100% |  |  | 0
22026168000 | 909 | EX | HVAC AND RTU PANEL UPGRADE | US 460 - GEORGETOWN RD | F | 39849.6755 | 22883.04 | -16966.6355 | -43% |  |  | 0 | PAPER JOB COMPLETION.
22026168600 | 557 | EX | INSTALL 13,800'-2"PMMP | 204 PAYNE AV | B | 1751471.355 | 1532684.69 | -218786.665 | -12% | 13800 | 11202 | 136.8224
22026168700 | 558 | EX | RETIRE 12,327'-BSLP,CSLP,PLP | 204 PAYNE | B | 89.0305 | 0 | -89.0305 | 100% |  |  | 0
22026169200 | 557 | CO | EMER-INSTALL 4' OF 2"PMMP MAIN | W 2ND ST | A | 5880.7828 | 4368.24 | -1512.5428 | -26% | 4 | 4 | 1092.06
22026169300 | 558 | CO | EMER-RETIRE 4' OF 2"PMMP MAIN | W 2ND ST | A | 107.3789 | 0 | -107.3789 | 100% |  |  | 0
22026169900 | 2000 | EX | SURVEY ENCROACHMENT | FRANKFORT | B | 5000 | 0 | -5000 | 100% |  |  | 0
22026175000 | 2000 | EX | INVESTIGATE NON-STANDARD S/L | 165 N SCRUGGS LN | B | 5287 | 0 | -5287 | 100% |  |  | 0
22026179400 | 560 | EX | RETIRE 100' OF 4"PMMP MAIN | 100 OLD OXFORD RD | B | 75.4968 | 0 | -75.4968 | 100% |  |  | 0
22026181600 | 561 | EX | RELOCATE ~5"-2" PMMP | 131 ARROWHEAD CT | A | 6138.9503 | 10366.16 | 4227.2097 | 69% | 9 | 10 | 1036.616 | DURING AND AFTER REPLACEMENT PURGE NEW MAIN INTO SERVICE CO M.COLLINS/B.SEXTON RLA 6-7-2022 REPLACED 10' OF 2" P MP MAIN TEST 10' OF 2" PIPE ONSITE 90LBS FOR 1 HR NO LEAKS SOAP TEST TIE IN NO LEAKS BHB NGF SOAP TEST ALL TEE'S CAPS AND DEAD ENDS AT OP AFTER GUAGE REMOVAL NO LEAKS VERIFY DELIVERY PRESSURE BEFORE
22026181700 | 562 | EX | RELOCATE ~5"-2" PMMP | 131 ARROWHEAD CT | A | 75.4968 | 0 | -75.4968 | 100% |  |  | 0
22026183001 | 555 | EX | INSTALL 4955'-2" PMMP | 1100 LEESTOWN RD | B | 134870.3496 | 124010.5 | -10859.8496 | -8% | 4955 | 1705 | 72.7334
22026183900 | 2000 | EX | INVEST. EASEMENT 22-0261686-00 | 424 PAYNE AV |  | 5000 | 0 | -5000 | 100% |  |  | 0
22026185800 | 909 | EX | EXCHANGE ELECTRONIC COMPONENTS | SHOWALTER DR | F | 5480.5156 | 1834.52 | -3645.9956 | -67% |  |  | 0 | CCC# 68240 - REPLACED ERX WITH MIWI 350 - BLONE/CWEMPE - 05/25/22 INSTALLED NEW MIWI 350
22026185900 | 910 | EX | RETIRE ELECTRONIC COMPONETS | SHOWALTER DR | F | 124.5156 | 501.88 | 377.3644 | 303% |  |  | 0 | CCC# 68240 - REPLACED ERX WITH MIWI 350 - BLONE/CWEMPE - 05/25/22 RETIRED OLD ERX
22026186200 | 909 | EX | EXCHANGE ELECTRONIC COMPONENTS | WILKINSON BV | F | 5480.5156 | 0 | -5480.5156 | 100% |  |  | 0 | INSTALLED NEW MIWI 350 05/23/2022 GHALE
22026186300 | 910 | EX | RETIRE ELECTRONIC COMPONENTS | WILKINSON BV | F | 124.5156 | 190.3 | 65.7844 | 53% |  |  | 0 | RETIRED OLD ERX 05/23/2022 GHALE
22026186400 | 909 | EX | EXCHANGE ELECTRONIC COMPONENTS | E TODD ST | F | 5480.5156 | 548.88 | -4931.6356 | -90% |  |  | 0 | CCC# 68048 RETIRED ERX AND INSTALLED NEW MIWI350 JPASLEY
22026186500 | 910 | EX | RETIRE ELECTRONIC COMPONENTS | E TODD ST | F | 124.5156 | 0 | -124.5156 | 100% |  |  | 0 | RETIRED ERX AND INSTALLED NEW MIWI350 JPASLEY
22026186800 | 909 | EX | EXCHANGE ELECTRONIC COMPONENTS | LOUISVILLE RD | F | 4357.5409 | 1456 | -2901.5409 | -67% |  |  | 0 | CCC-69443 INSTALLED NEW MIWI 350 SOAP TEST CONNECTIONS EBLANTON
22026186900 | 910 | EX | RETIRE ELECTRONIC COMPONENTS | LOUISVILLE RD | F | 124.5156 | 504.03 | 379.5144 | 305% |  |  | 0 | CCC-69443 RETIRED ERX EBLANTON
22026188400 | 909 | EX | EXCHANGE ELECTRONIC COMPONENTS | 104 FIELDVIEW DR | F | 6681.5691 | 1456 | -5225.5691 | -78% |  |  | 0 | CCC# 69290 - BLONE - 06/02/22 INSTALLED MIWI SN:13450082 P1-0-PSI P2-0-60 IP:10.22.4.15MDN 859-221-6738
22026188500 | 910 | EX | RETIRE ELECTRONICS | 104 FIELDVIEW DR | F | 74.2578 | 473.46 | 399.2022 | 538% |  |  | 0 | CCC# 69290 - BLONE - 06/02/22
22026188600 | 555 | EX | INSTALL 165'-2" PMMP | 102 OAK HILL LN | B | 14323.3857 | 11945.7 | -2377.6857 | -17% | 165 | 160 | 74.6606
22026188700 | 2000 | EX | INVESTIGATE LAND RIGHTS FOR SL | 301 STANLEY ST | B | 3450 | 0 | -3450 | 100% |  |  | 0
22026195400 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | US60 | F | 4801.1928 | 682.09 | -4119.1028 | -86% |  |  | 0 | CCC# 78156 PAPERWORK ONLY - NO CCC NEEDED - BLONE - 11/8/22 INSTALLED NEW MIWI350 B LONE 8-22-2022
22026195500 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | US60 | F | 124.8731 | 676.72 | 551.8469 | 442% |  |  | 0 | CCC# 78156 RETIRED OLD ERX INSTALLED NEW MIWI350 BLONE 8-22-22
22026195600 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 510 VERSAILLES RD | F | 4801.1928 | 5406.36 | 605.1672 | 13% |  |  | 0 | CCC# 78341 - BLONE - 08/23/22 UPGRADED ERX TO MIME CO BY J.MULLINS
22026195700 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 510 VERSAILLES RD | F | 124.8731 | 381.79 | 256.9169 | 206% |  |  | 0 | CCC# 78341 B. LONE UPDATTED ERX TO MIWI CO BY J. MULLINS
22026198900 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | US 460 BYPASS | F | 4801.1928 | 5462.44 | 661.2472 | 14% |  |  | 0 | CCC#79730 CWEMPE 9/6/22 UPGRADED ERX TO MIWI PAPERWORK DONE BY J.MULLINS
22026199000 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | US 460 BYPASS | F | 124.8731 | 252.74 | 127.8669 | 102% |  |  | 0 | CCC#79730 CWEMPE 9/6/22
22026199300 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 113 GREAT BUFFALO TC | F | 4801.1928 | 5269.21 | 468.0172 | 10% |  |  | 0 | CCC# 79486 RETIRED ERX INSTALLED NEW MIWI350 GHALE 9-1-2022
22026199400 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 113 GREAT BUFFALO TC | F | 124.8731 | 169.77 | 44.8969 | 36% |  |  | 0 | CCC# 79486 RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 9-1-2022
22026199500 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 110 GLENNS CREEK RD | F | 4801.1928 | 5358.86 | 557.6672 | 12% |  |  | 0 | CCC# 80149 P2P OK RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 9-8-2022
22026199600 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 110 GLENNS CREEK RD | F | 124.8731 | 509.01 | 384.1369 | 308% |  |  | 0 | CCC# 80149 RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 09-08-2022
22026200700 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | US 460 & IRONWORKS PK | F | 4801.1928 | 5573.15 | 771.9572 | 16% |  |  | 0 | CCC# 68204 - BLONE - 08/24/22 CCC#68204 TIME CHARGED FOR COMPLETING PAPERWORK. CWEMPE 8/30/22 RETIRED ERX INSTALLED NEW MIWI350 CWEMPE 8-24-2022
22026200800 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | US 460 & IRONWORKS PK | F | 124.8731 | 285.19 | 160.3169 | 128% |  |  | 0 | CCC# 68204 - BLONE - 08/24/22 CCC#68204 RETIRED OLD ERX INSTALLED NEW MIWI350 CWEMPE 8-24-2022
22026201100 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | ROLLING ACRES DR | F | 4801.1928 | 5540.17 | 738.9772 | 15% |  |  | 0 | CCC# 80069 P2P OK RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 9-8-2022
22026201200 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | ROLLING ACRES DR | F | 124.8731 | 157.47 | 32.5969 | 26% |  |  | 0 | CCC# 80069 RETIRED OLD ERX INSTALLED NEW MIWI350 GHALE 9-8-2022
22026202500 | 555 | EX | INSTALL 1120'-2"/4" PMMP | TRINITY LN LT154 | B | 49758.6341 | 50092.05 | 333.4159 | 1% | 1120 | 1096 | 45.7044
22026204700 | 2000 | EX | PERFORM CONFLICT ASSESSMENT | CROSS COUNTRY | A | 3000 | 0 | -3000 | 100% |  |  | 0 | AWEBER 11/3/23 - WORKED WITH DESIGN FIRM, MANHARD CONSULTING, TO MITIGATE A LL CONFLICTS OF DESIGN FOR TRUCKING FACILITY OWNED BY R+L CARRIERS. CONSTRU CTION TO BEGIN Q1-Q2 2024, MONITORING REQUIRED FOR LINES DE & DKT AROUND TH E PROPERTY ADJACENT TO TURNER STATION. SHANNON BARKER TO BE FOL CONTACT.
22026205401 | 555 | EX | INSTALL 1330'-4" PMMP | SCHOOL HOUSE RD | B | 229795.8687 | 288486.41 | 58690.5413 | 26% | 1330 |  | 0
22026207500 | 583 | EX | INSTALL NEW CONTROL REGULATOR | 177 RUCKER AV | F | 1471.7874 | 893.82 | -577.9674 | -39% |  |  | 0 | CCC#77790 INSTALLED NEW 461-57S CONTROL REGULATOR CWEMPE 8-18-22
22026207600 | 584 | EX | REPLACE CONTROL REG | 177 RUCKER AV | F | 65.0112 | 487.94 | 422.9288 | 651% |  |  | 0 | CCC#77790 REMOVED CONTROL REGULATOR CWEMPE 8-18-22
22026208100 | 0001 | EX | BUFFALO TRACE HOUSE LINE | GREAT BUFFALO TRACE | A | 6132.6749 | 0 | -6132.6749 | 100% |  |  | 0 | COMPETE. NOO LEAKAGE FOUND. S.LURTY 6-29-22 1040
22026208600 | 557 | EX | EMER - INSTALL 2'-2" PMMP | HAWTHORNE | A | 5654.5749 | 7597.73 | 1943.1551 | 34% | 2 | 2 | 3798.865
22026208700 | 558 | EX | EMER - RETIRE 2'-2" PMP | HAWTHORNE | A | 63.5475 | 0 | -63.5475 | 100% |  |  | 0
22026210901 | 555 | EX | INSTALL 8OO' OF 2"PMMP MAIN | OAK HILL LN LT1 | B | 49945.6881 | 53441.52 | 3495.8319 | 7% | 500 | 789 | 67.7332
22026211200 | 557 | EX | EMER-INSTALL 6' OF 4"PMIP MAIN | 1149 LISLE RD | A | 10641.1495 | 13924.65 | 3283.5005 | 31% | 6 | 6 | 2320.775
22026211300 | 558 | EX | EMER-RETIRE 6' OF 4"PAIP MAIN | 1149 LISLE RD | A | 65.0112 | 0 | -65.0112 | 100% |  |  | 0
22026213400 | 583 | EX | INSTALL NEW 1" REGULATORS | 488 LEXINGTON RD | F | 1461.8601 | 2234.49 | 772.6299 | 53% |  |  | 0 | REPLACED BOTH MONITOR AND CONTROL REGULATORS AND INLET AND OUTLET VALVES BL ONE 10-7-22
22026213500 | 584 | EX | RETIRE REGULATORS | 488 LEXINGTON RD | F | 84.9152 | 856.14 | 771.2248 | 908% |  |  | 0 | REPLACED BOTH MONITOR AND CONTROL REGULATORS AND INLET AND OUTLET VALVES BL ONE 10-7-22
22026213900 | 555 | EX | INSTALL 200'-2"PMMP | 216 SUGARTREE LN | B | 22574.1191 | 35208.99 | 12634.8709 | 56% | 200 | 308 | 114.3149 | BORED IN 308' OF 020 PL ML. TESTED 90# FOR 1 HR. SOAP TESTED CONN PTS @ 39#
22026214100 | 562 | EX | ABANDON 200'-2" PMMP | SUGARTREE LN | B | 800.8601 | 921.07 | 120.2099 | 15% |  |  | 0
22026214500 | 910 | EX | JIM BEAN RTU PANEL | US 460 - GEORGETOWN RD | F | 55.5311 | 2091.18 | 2035.6489 | 3,666% |  |  | 0 | CCC# 15710 CCC# 15710
22026215700 | 557 | EX | EMER-INSTALL 2' OF 2"PMMP MAIN | W MAIN ST | A | 8681.8934 | 4910.67 | -3771.2234 | -43% | 2 | 2 | 2455.335 | REPLACED 2FT OF 020 DAMAGED MAIN.TESTED NEW MAIN FOR 20MINS AT 90LBS.TEST OK.SOAP TEST EFC'S AT OP FOR 5MINS.TEST OK. BHBNGF
22026215800 | 558 | EX | EMER-RETIRE 2' OF 2"PMP MAIN | W MAIN ST | A | 84.9152 | 224.99 | 140.0748 | 165% |  |  | 0 | REPLACED 2FT OF 020 DAMAGED MAIN.TESTED NEW MAIN FOR 20MINS AT 90LBS.TEST OK.SOAP TEST EFC'S AT OP FOR 5MINS.TEST OK. BHBNGF
22026220400 | 562 | EX | ABANDON 550' OF 2"PMP MAIN | 1175 GEORGETOWN RD | A | 3449.8998 | 184.67 | -3265.2298 | -95% |  |  | 0 | ABANDONED 020 MP PL ML. PREFORMED PER ABANDONMENT PLAN SOAP TEST DEAD END C AP OP 15 MINUTES. C HERNDON/S.BARKER PURGED ABANDONED SECTION OF LINE. CAPPED THE ENDS OF ABANDONED ML.
22026221000 | 555 | EX | INSTALL 160'-4"PMMP | 515 EVERGREEN RD | B | 20578.0582 | 36375.08 | 15797.0218 | 77% | 160 | 177 | 205.5089 | AWEBER 12/6/22 - JOB ENCOUNTERED HEAVY ROCK BORE, RESULTING IN DOUBLE TIME FROM ORIGINAL ESTIMATE. ATTEMPT TO REVISE, UNABLE DUE TO UNPAID INVOICES.
22026222700 | 555 | EX | INSTALL 86'-2" PMMP | 209 W LYNN ST | B | 12304.5709 | 13511.21 | 1206.6391 | 10% | 86 | 60 | 225.1868 | THERE WAS A TYPO ON THE PRESSURE SYSTEM WHEN IT WAS CREATED. CORRECT SYSTEM NUMBER 32010047. SYSTEM NUMBER HAS BEEN CORRECTED IN DIS.
22026225400 | 557 | EX | INSTALL APROX 180'-6" PMLP | 601 VERSAILLES RD | B | 120007.3465 | 161513.7 | 41506.3535 | 35% | 180 | 215 | 751.2265 | GURU ADDED 2'-6"PLASTIC RISER PIPE TO TD 0735002. SM 11/7/23
22026225500 | 558 | EX | RETIRE 200' - 6" BSLP | 601 VERSAILLES RD | B | 117.7346 | 510.72 | 392.9854 | 334% |  |  | 0
22026227300 | 2000 | EX | PS&I CROSSWINDS CENTER PATH | 105 CROSSWINDS CENTER PATH | B | 2477 | 0 | -2477 | 100% |  |  | 0
22026227400 | 2000 | EX | PS&I MACEY AVE SMRP | MACEY AV | B | 1180 | 0 | -1180 | 100% |  |  | 0
22026229200 | 555 | EX | INSTALL 80'-2" PMMP | 760 COLONIAL TC | B | 11104.5291 | 10781.29 | -323.2391 | -3% | 80 | 160 | 67.3831 | INSTALLED 160' 2'' MP-PL MAINLINE
22026230000 | 562 | EX | ABANDON 470'-2"&3"PLP | 105 BRIGHTON PARK BV | B | 6027.5291 | 5899.02 | -128.5091 | -2% |  |  | 0 | ABANDONED 334' OF 030 PL LP ML PER ENGINEERING AND TIE IN PLAN. SOAP TEST END CAP @ OP 15 MINS NO LEAKS BHB NGF. PURGED OUT ABANDONED SECTION OF ML G OOD M. COLLINS 11/1/2022
22026230600 | 557 | CO | EMER-INSTALL 5' OF 3"PMMP MAIN | 806 COLONIAL | A | 828.6177 | 0 | -828.6177 | 100% | 5 |  | 0
22026230700 | 558 | CO | EMER-RETIRE 5' OF 3"PAMP MAIN | 806 COLONIAL | A | 4289.0582 | 12302.62 | 8013.5618 | 187% |  |  | 0
22026231200 | 555 | EX | INSTALL 1870'-2"/4" PMMP | SAFFRON LN LT19 | B | 71796.5181 | 213474.97 | 141678.4519 | 197% | 1870 | 1987 | 107.4358
22026232800 | 2000 | EX | INVESTIGATE & MAP MAINS | BRIDGEPORT-BANSON RD |  | 2843 | 0 | -2843 | 100% |  |  | 0 | CONFLICT ASSESMENT COMPLETED AND CONFLICTS ELLIMINATED WITH PROPOSED PROJEC T. D.LEMONS 6/27/2024
22026235100 | 555 | EX | INSTALL 2160'-2"/4" PMMP | BILL PERKINS LN LT62 | B | 82352.5181 | 179472.03 | 97119.5119 | 118% | 2160 | 2216 | 80.9892
22026235300 | 557 | EX | INST 1865'-8" & 390'-2" PMMP | 325 OLD LEMONS MILL | B | 895303.7297 | 1121157.31 | 225853.5803 | 25% | 2270 | 2215 | 506.1658
22026235400 | 558 | EX | RETIRE 2111'- 2",4",6",8" BSMP | OLD LEMONS MILL | B | 139.1159 | 220 | 80.8841 | 58% |  |  | 0
22026236000 | 575 | EX | ADDITIONAL EASEMENT/LAND | 3200 GEORGETOWN RD | F | 136.2135 | 0 | -136.2135 | 100% |  |  | 0
22026236901 | 557 | EX | INSTALL 11300'-2" PMMP | CLAYTON | B | 2204167.7449 | 2626590.92 | 422423.1751 | 19% | 11300 | 11185 | 234.8316
22026237000 | 558 | EX | ABDN~8924'-2",3",4" BS,CS,P LP | CLAYTON | B | 124.9261 | 0 | -124.9261 | 100% |  |  | 0
22026238301 | 555 | EX | INSTALL 2505'-4" PHHP | 158 W LEESTOWN RD BOILER | B | 265393.3206 | 297291.9 | 31898.5794 | 12% | 2505 | 2990 | 99.4287
22026238401 | 557 | EX | INSTALL 5765'-2" PMMP | WINTER | B | 1269865.7251 | 1422160.57 | 152294.8449 | 12% | 5765 | 6764 | 210.2544
22026238500 | 558 | EX | RETIRE 7260'-2"-6" BS,CS & P | WINTER | B | 139.1159 | 0 | -139.1159 | 100% |  |  | 0
22026238600 | 558 | EX | RETIRE 116'-2"&3" CS&PMP |  | B | 139.1159 | 0 | -139.1159 | 100% |  |  | 0
22026241001 | 555 | EX | INSTALL 6375'-2"/4" PMMP ENV | STREET B LT15 | B | 793212.5591 | 797679.45 | 4466.8909 | 1% | 6375 | 6405 | 124.5401
22026241200 | 2000 | EX | RESEARCH EASEMENTS & R/W | WINTER ST |  | 19599 | 0 | -19599 | 100% |  |  | 0 | PS&I FOR SMRP NORTH MIDWAY. D.LEMONS 10/24/2023
22026241701 | 561 | EX | INSTALL 1425' OF 2"PMMP MAIN | W WASHINGTON ST | B | 729573.6534 | 698687.73 | -30885.9234 | -4% | 1300 | 1425 | 490.3072
22026241800 | 562 | EX | RETIRE 1175' OF 3"/4"BSLP MAIN | W WASHINGTON ST | B | 119.4953 | 10.85 | -108.6453 | -91% |  |  | 0
22026243700 | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 1175 LISLE RD | F | 29277.8866 | 17949.62 | -11328.2666 | -39% |  |  | 0 | CC 22683 CC 22535 WELDED INLET TAP TESTED INLET 375# 5 MINS RHAYES DMARTIN 03-29-2023 CCC# 24078 NOT ON SITE. CAPITAL PAPERWORK CCC#25522 CWEMPE 4/17/23 COMPLETED PAPERWORK OFFSITE. CWEMPE 4/20/23 DID NOT ENTER STATION. CHARGED TIME FOR PAPERWORK. CWEMPE 4/24/23
22026243800 | 909 | EX | INSTALL NEW SCADA EQUIPMENT | LONG LICK RD | F | 32044.6752 | 17170.68 | -14873.9952 | -46% |  |  | 0 | CC 22535 WELDED TAPS TESTED INLET 375# OUTLET 45# MINS DMARTIN RHAYES 03-29-2023 CCC# 24067 CCC#25645 CWEMPE 4/18/23 COMPLETED PAPERWORK OFFSITE. CWEMPE 4/20/23 DID NOT ENTER STATION. CHARGED TIME FOR PAPERWORK. CWEMPE 4/24/23
22026244100 | 909 | EX | INSTALL NEW SCADA EQUIPMENT | HILLSIDE DR | F | 32044.6752 | 17388.43 | -14656.2452 | -46% |  |  | 0 | CC 22622 CC 22535 WELDED TAPS TESTED INLET 375# OUTLET 90# 5 MINS RHAYES DMARTIN 03-29-2023 CCC# 24075 CALLED FOR CLEARANCE TICKET AT END OF DAY AND CCC REFUSED TO CREATE TICKET. CWEMPE 4/19/23 COMPLETED PAPERWORK OFFSITE. CWEMPE 4/20/23
22026244200 | 909 | EX | INSTALL NEW SCADA EQUIPMENT | 413 VILLAGE DR | F | 33186.6752 | 20934.82 | -12251.8552 | -37% |  |  | 0 | CCC# 24912 WELDED ON PUNCH TEES FOR SCADA VISIBILITY PROJECT. TESTED TAPPED, AND MT COMPLETE. LOCKED AND PLUGGED VALVE. CCC# 26916
22026244300 | 909 | EX | INSTALL NEW SCADA EQUIPMENT | DUCKER STATION RD | F | 29761.6752 | 21295.01 | -8466.6652 | -28% |  |  | 0 | CC 22295 TAPS WELDED TESTED INLET 375# OUTLET90# 5MIN TESTED GOOD RHAYES CCC# 24050 CCC#26526 CWEMPE 4/21/23
22026245100 | 557 | EX | EMER-INSTALL 3' OF 2"PHHP MAIN | ROCKY WATERS | B | 4877.0569 | 2741.28 | -2135.7769 | -44% | 3 | 3 | 913.76
22026245200 | 558 | EX | EMER-RETIRE 3' OF 2"PHHP MAIN | ROCKY WATERS | B | 131.2422 | 0 | -131.2422 | 100% |  |  | 0
23026249500 | 555 | EX | INSTALL 870'-2" PMMP | 150 IKEBANA DR | B | 67614.2583 | 52378.28 | -15235.9783 | -23% | 870 | 876 | 59.7926
23026249600 | 559 | EX | PM- DE ILI PH 2 JIM BEAM INST | 3200 GEORGETOWN RD | B | 593000 | 966229.4 | 373229.4 | 63% |  | 24 | 40259.5583
23026249700 | 560 | EX | PM- DE ILI PH 2 JIM BEAM ABAN | 3200 GEORGETOWN RD | B | 132000 | 234155.55 | 102155.55 | 77% |  |  | 0
23026251500 | 555 | EX | INSTALL 70'-2" PMLP | 244 W BRUEN ST | B | 20790.0608 | 16349.3 | -4440.7608 | -21% | 70 | 122 | 134.0107
23026252900 | 559 | EX | PM-GREENSITE RAILROAD CROSSING |  | B | 1236355 | 17890.94 | -1218464.06 | -99% |  | 41 | 436.3644
23026253000 | 560 | EX | PM-GREENSITE RAILROAD ABANDON |  | B | 0 | 328.14 | 328.14 | 100% |  |  | 0
23026253500 | 559 | EX | PM-GREENSITE IRONWORKS DE REPL |  | B | 1236355 | 18995.31 | -1217359.69 | -98% |  | 87 | 218.3369
23026253600 | 560 | EX | PM-GREENSITE IRONWORKS ABAN |  | B | 0 | 6.23 | 6.23 | 100% |  |  | 0
23026254300 | 555 | EX | TAP W/MAIN 23-0262543-00 | 1220 DISCHER DR | B | 13015.0987 | 4459.75 | -8555.3487 | -66% | 60 | 9 | 495.5278
23026255400 | 588 | EX | GMB TO CAB CONVERSION | 900 TYRONE PK FF | F | 2712.0987 | 9499.75 | 6787.6513 | 250% |  |  | 0 | REMOVED OLD GMB FACILITIES REBUILT METER SETTING INSTALLED NEW ROMET 16M ME TER AND CL838 REGS ON 15# DELIVERY BLONE 6-1-23
23026256000 | 557 | EX | INSTALL 800'OF 2"PMMP MAIN | TIMBERLAWN | B | 192451.7008 | 92657.71 | -99793.9908 | -52% | 800 | 724 | 127.9803
23026256600 | 584 | EX | RETIRE PAPER GAUGE | 1024 CAPITAL CENTER DR | F | 138.8485 | 468 | 329.1515 | 237% |  |  | 0 | CHART BOXES REMOVED. G.HALE A.PARKS 03-02-23 CHARTS REMOVED AND STORED AT LEX MOD APARKS 03-02-23
23026257100 | 555 | EX | INSTALL 300'-2" PMMP | 135 AMERICAN PH | B | 32921.1974 | 68581.44 | 35660.2426 | 108% | 300 | 400 | 171.4536 | MAINLINE EXTENSION FOR ALDI'S INSTALLED BY STANLEY PIPELINE. JOSH PASLEY 9/28/23
23026259600 | 909 | EX | INSTALL ERX AND SUPER SOLAR | 1625 MIDWAY RD | F | 5600.9621 | 4884.63 | -716.3321 | -13% |  |  | 0
23026259700 | 584 | EX | RETIRE PAPER CHART | US 62 AT LANES END FRM | F | 138.8485 | 269.78 | 130.9315 | 94% |  |  | 0
23026260600 | 588 | EX | GMB TO CAB CONVERSION | 141 COMMERCE BV | F | 138.8485 | 1404.11 | 1265.2615 | 911% |  |  | 0 | GATHER PARTS FOR CONVERSION, MTR, FLANGES, GASKETS ETC. REGULATOR GMB TO CAB CONVERSION GAS ON BYPASS DURING REBUIL;D NO BYPASS GAS USED INST ALLED NEW ROMET 3M ON 2#
23026261900 | 2000 | EX | MAP AND INVESTIGATE MAINS | DUNCAN RD |  | 31431 | 0 | -31431 | 100% |  |  | 0
23026265900 | 2000 | EX | PS&I BLUEGRASS DISTILLERY | 158 W LEESTOWN RD | B | 0 | 0 | 0 | 0% |  |  | 0
23026266100 | 555 | EX | INSTALL 880'-4" PHHP | 100 LACEFIELD ST | B | 60596.7317 | 70247.34 | 9650.6083 | 16% | 880 | 971 | 72.3454
23026266200 | 555 | EX | INSTALL 1100'-4" PHHP | 1050 GEORGETOWN RD BLDG C | B | 81743.7317 | 127648.14 | 45904.4083 | 56% | 1100 | 1093 | 116.787
23026268100 | 558 | EX | RETIRE MAIN - LEAKAGE | ELMENDORF | A | 117.7346 | 0 | -117.7346 | 100% |  |  | 0
23026268500 | 559 | EX | PM-DE LINE ILI PH 2 BEND 260 |  | B | 1150001 | 770197.91 | -379803.09 | -33% |  | 30 | 25673.2637
23026268600 | 559 | EX | PM-DE LINE ILI PH2 DENT 36 |  | B | 1150001 | 1598859.3 | 448858.3 | 39% |  | 18 | 88825.5167
23026269000 | 557 | EX | EMER-INSTALL 4' OF 2"PMMP MAIN | MACK ST | A | 5499.7073 | 6353.99 | 854.2827 | 16% | 4 | 4 | 1588.4975
23026269100 | 558 | EX | EMER-RETIRE 4' OF 2"PAMP MAIN | MACK ST | A | 117.7346 | 0 | -117.7346 | 100% |  |  | 0
23026269200 | 560 | EX | PM-DE LINE ILI PH2 BEND 260 AB |  | C | 192300 | 195099.48 | 2799.48 | 1% |  |  | 0
23026269300 | 560 | EX | PM-DE LINE ILI PH2 DENT 36 ABD |  | C | 192300 | 282014.56 | 89714.56 | 47% |  |  | 0
23026271000 | 559 | EX | INSTALL 70'-2" PMMP | 155 W MAIN ST | A | 9795.9371 | 606.43 | -9189.5071 | -94% | 70 | 70 | 8.6633
23026271100 | 560 | EX | ABANDON 60'-2" PMMP | 155 W MAIN ST | A | 262.8722 | 4210.59 | 3947.7178 | 1,502% |  |  | 0
23026271300 | 575 | EX | OBTAIN ADDITIONAL LAND RIGHTS | INDUSTRY RD | F | 83269 | 72514.71 | -10754.29 | -13% |  |  | 0 | TWALKER/KY 07-10-23: THIS JOB ORDER CREATE TO RECORD AND DOCUMENT NEW 40' X 40' SITE/LAND FOR FUTURE REG STATION EXPANSION.
23026271800 | 2000 | EX | INVESTIGATE RW AND EASEMENT | 601 VERSAILLES RD |  | 3382 | 0 | -3382 | 100% |  |  | 0
23026273500 | 557 | EX | EMER-INSTALL 65' OF 2"PMIP | 124 LEE LN | A | 8772.0552 | 5983.61 | -2788.4452 | -32% | 65 | 87 | 68.7771
23026273600 | 558 | EX | EMER-RETIRE 55' OF 2"PAIP | 124 LEE LN | A | 117.7346 | 1024.42 | 906.6854 | 770% |  |  | 0
23026276700 | 584 | EX | RETIRE STATION R-1581 | 313 N WINTER ST | F | 541.8551 | 1722.38 | 1180.5249 | 218% |  |  | 0 | NO CCC NEEDED -RETIRED STATION - CHECKED TO SEE RETIRED STATUS AND STATUS OF INLET VALVE - BLONE - 05/02/25
23026276800 | 586 | EX | RETIRE FENCE | 313 N WINTER ST | F | 139.1159 | 0 | -139.1159 | 100% |  |  | 0
23026278800 | 2000 | EX | INVESTIGATE MAINS | LEXINGTON RD |  | 3788 | 0 | -3788 | 100% |  |  | 0 | CONFLICTS CLEARED BY VAC EXCAVATE. D.LEMONS 7/31/2023
23026278900 | 555 | EX | INSTALL 150'-2" PMMP | DOVE RUN CR LT160 | B | 13769.2187 | 10151.75 | -3617.4687 | -26% | 150 | 128 | 79.3105
23026279800 | 555 | EX | INSTALL 1800'-2" PMMP | 131 OXFORD LANDING DR | B | 72065.7028 | 53278.51 | -18787.1928 | -26% | 1800 | 1807 | 29.4845
23026281000 | 575 | EX | OBTAIN NEW EASEMENT | OLD LEMONS MILL RD | F | 11896 | 19487.14 | 7591.14 | 64% |  |  | 0
23026281200 | 557 | EX | EMER-INSTALL 2' OF 2"PMMP MAIN | 111 MARKETPLACE CR | A | 5082.4374 | 6222.18 | 1139.7426 | 22% | 2 | 2 | 3111.09
23026281300 | 558 | EX | EMER-RETIRE 2' OF 2"PMMP MAIN | 111 MARKETPLACE CR | A | 139.1159 | 0 | -139.1159 | 100% |  |  | 0
23026281400 | 555 | EX | INSTALL 1865'-2"/4" PMMP | HOURGLASS LN LT13 | B | 77027.7111 | 90143.57 | 13115.8589 | 17% | 1865 | 1873 | 48.1279
23026282800 | 557 | EX | EMER - INSTALL 5'-2" PMMP | REGENTS PARK | A | 5465.9794 | 8915.85 | 3449.8706 | 63% | 5 | 5 | 1783.17
23026282900 | 558 | EX | EMER - ABANDON 5'-2" PMMP | REGENTS PARK | A | 67.1159 | 0 | -67.1159 | 100% |  |  | 0
23026283801 | 555 | EX | INSTALL 5705'-2"/4" PMMP | GLENEAGLES WY LT54 | B | 361218.8401 | 388707.97 | 27489.1299 | 8% | 5705 | 5975 | 65.0557
23026284000 | 557 | EX | EMER-INSTALL 2' OF 3"PMMP MAIN | 615 COMANCHE TL | A | 4281.828 | 14848.12 | 10566.292 | 247% | 2 | 2 | 7424.06
23026284100 | 558 | EX | EMER-RETIRE 2' OF 3"PAMP MAIN | 615 COMANCHE TL | A | 139.1159 | 0 | -139.1159 | 100% |  |  | 0
23026285800 | 557 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | 111 MARKETPLACE CR | A | 6991.8345 | 8976.29 | 1984.4555 | 28% | 3 | 3 | 2992.0967
23026285900 | 558 | EX | EMER-RETIRE 3' OF 2"PMMP MAIN | 111 MARKETPLACE CR | A | 139.1159 | 0 | -139.1159 | 100% |  |  | 0
23026288700 | 583 | EX | INSTALL NEW RELIEF VALVE | 488 LEXINGTON RD | F | 3278.6711 | 814.62 | -2464.0511 | -75% |  |  | 0
23026288800 | 584 | EX | RETIRE RELIEF VALVE | 488 LEXINGTON RD | F | 119.4953 | 0 | -119.4953 | 100% |  |  | 0
23026289700 | 557 | EX | INSTALL 70' OF 3"PMLP MAIN | 359 N BROADWAY ST DN | A | 32180.0533 | 43735.5 | 11555.4467 | 36% | 70 | 70 | 624.7929
23026289800 | 558 | EX | RETIRE 271' OF 2"/3"BSLP MAIN | 359 N BROADWAY ST DN | A | 119.4953 | 9.9 | -109.5953 | -92% |  |  | 0
23026291400 | 560 | EX | PAPER JOB - MP RETIREMENT | 100 TANGLEWOOD DR | B | 119.4953 | 0 | -119.4953 | 100% |  |  | 0
23026292201 | 555 | EX | INSTALL 360'-4" PMMP | 106 E BROADWAY ST NEW | B | 171123.5748 | 171750.99 | 627.4152 | 0% | 360 | 357 | 481.0952
23026294600 | 562 | EX | ABANDON ~790'-2" PMMP | SAFFRON LN | B | 3905.6711 | 392.35 | -3513.3211 | -90% |  |  | 0
23026296100 | 2000 | EX | PS&I WOODFORD COUNTY HIGH | TYRONE PIKE | B | 0 | 0 | 0 | 0% |  |  | 0
23026296400 | 557 | EX | INSTALL 110' OF 2"PMMP MAIN | 565 SCHENKEL | B | 46114.2728 | 58459.83 | 12345.5572 | 27% | 110 | 164 | 356.4624 | CAPITAL JOB COMPLETE BY STANLEY PIPELINE AND CLEARED ASSOCIATED DPI'S. JOSH PASLEY 12/21/23
23026296500 | 558 | EX | RETIRE 88' OF 2"CSMP MAIN | 565 SCHENKEL | B | 122.9261 | 0 | -122.9261 | 100% |  |  | 0 | CAPITAL JOB COMPLETED BY STANLEY PIPELINE. CLEARED ASSOCIATED DPI'S. JOSH PASLEY 12/21/23
23026298800 | 555 | EX | INSTALL 900'-2" PMMP MAIN | 335 E YUSEN DR REAR | B | 120091.9279 | 154240.87 | 34148.9421 | 28% | 900 | 861 | 179.1415
23026300200 | 2000 | EX | CONFLICT ASSESSMENT | CONNECTOR RD | A | 4097 | 0 | -4097 | 100% |  |  | 0
23026301200 | 561 | EX | INSTALL 60' OF 6"PMMP MAIN | CONNECTOR RD | B | 42818.4272 | 43879.22 | 1060.7928 | 2% | 60 | 75 | 585.0563
23026301300 | 562 | EX | RETIRE 54' OF 6"PMP MAIN | CONNECTOR RD | B | 156.7483 | 0 | -156.7483 | 100% |  |  | 0
23026301600 | 909 | EX | INSTAL NEW MODEM | 120 WASSAU AL | F | 2605.8688 | 652.23 | -1953.6388 | -75% |  |  | 0
23026301700 | 910 | EX | RETIRE MODEM | 120 WASSAU AL | F | 122.9261 | 365.2 | 242.2739 | 197% |  |  | 0
23026307400 | 557 | EX | EMER-INSTALL 3' OF 2"PMMP | 122 OLD TOWNE | A | 2930.7643 | 1388.66 | -1542.1043 | -53% | 3 | 3 | 462.8867
23026307500 | 558 | EX | EMER-RETIRE 3' OF 2"PMP MAIN | 122 OLD TOWNE | A | 123.4493 | 0 | -123.4493 | 100% |  |  | 0
23026308601 | 555 | EX | INSTALL 675'-2" PMMP | 690 DUNCAN RD | B | 75877.1307 | 91036.22 | 15159.0893 | 20% | 675 | 1049 | 86.7838 | JOB COMPLETED ON 5-14-24, ENGINEERING COMPLETED JOB ORDER REVISION ON 6-4-2 4 - RTINCHE 6-10-24
24026309500 | 555 | EX | INSTALL 215'-2" PMMP | 115 MEADOW LARK TR | B | 20568.4833 | 19486.43 | -1082.0533 | -5% | 215 | 238 | 81.8758
24026310000 | 557 | EX | EMER-INSTALL 4' OF 2"PMIP MAIN | 1112 CHOCTAW TL | A | 6172.4499 | 11757.28 | 5584.8301 | 90% | 4 | 4 | 2939.32
24026310100 | 558 | EX | EMER-RETIRE 4' OF 2"PAIP MAIN | 1112 CHOCTAW TL | A | 123.4493 | 0 | -123.4493 | 100% |  |  | 0
24026311500 | 558 | EX | EMER-RETIRE 350' OF 4"PMP MAIN | 5799 MCCRACKEN PIKE | A | 3055.4946 | 1832.02 | -1223.4746 | -40% |  |  | 0
24026312100 | 910 | EX | REMOVE SATELLITE UNIT | US 460 - GEORGETOWN RD | F | 4076.4833 | 1333.97 | -2742.5133 | -67% |  |  | 0 | CCC# 58738
24026312200 | 555 | EX | INSTALL 230'-2" PMMP | 200 NORMANDY RD | B | 25802.5654 | 37251.74 | 11449.1746 | 44% | 230 | 237 | 157.1803
24026312301 | 587 | EX | INSTALL NEW GMB SETTING | 158 W LEESTOWN RD | F | 234758.3952 | 230544.69 | -4213.7052 | -2% |  |  | 0
24026312400 | 563 | EX | INSTALL 50'-4" PHHP-SERV | 158 W LEESTOWN RD DISTILL | B | 13239.0974 | 23459.51 | 10220.4126 | 77% | 50 |  | 0
24026313000 | 557 | EX | INSTALL 1570'-2" PMMP | 124 JEFFERSON | B | 526295.3733 | 502657.55 | -23637.8233 | -4% | 1570 | 1390 | 361.6241
24026313100 | 558 | EX | RETIRE~1346 OF BSLP/PLP MAIN | 124 W JEFFERSON ST | A | 139.7787 | 0 | -139.7787 | 100% |  |  | 0
24026314200 | 2000 | EX | INVESTIGATE EASEMENT & R/W | 303 MOCKINGBIRD LN | B | 14233 | 0 | -14233 | 100% |  |  | 0
24026314300 | 2000 | EX | INVESTIGATE EASEMENT & R/W | 214 GANO AV | B | 14233 | 0 | -14233 | 100% |  |  | 0
24026314500 | 2000 | EX | INVESTIGATE EASEMENT & R/W | 323 US 62 | B | 14233 | 0 | -14233 | 100% |  |  | 0
24026314800 | 587 | EX | INSTALL MINI AT W/EC350 | GEORGETOWN RD | F | 3917.1928 | 5915.68 | 1998.4872 | 51% |  |  | 0 | INSTALLED NEW EC350 WITH HONEYWELL MODEM
24026314900 | 588 | EX | RETIRE ELECTRONICS | GEORGETOWN RD | F | 160.3697 | 1358.47 | 1198.1003 | 747% |  |  | 0 | RETIRED OLD MINI AT
24026316500 | 557 | EX | EMER - INSTALL 15'-2" PMMP | 879 KENTUCKY AVE | A | 4538.5784 | 0 | -4538.5784 | 100% | 15 | 10 | 0
24026316600 | 558 | EX | EMER - ABANDON ~15'-2" PMMP | 879 KENTUCKY AVE | B | 160.3697 | 7172.61 | 7012.2403 | 4,373% |  |  | 0
24026316900 | 2000 | EX | PM-2023 DE ILI VALIDATIONS | 1001 CHERRY BLOSSOM WY | A | 44959 | 0 | -44959 | 100% |  |  | 0 | AWEBER 4/30/24 - CONFIRMED CHARGE TO FOR VALIDATION PS&I'S TO 2023 559 WORK
24026317300 | 555 | EX | INSTALL 270'-2" PMMP | 224 SUGARTREE LN | B | 44548.0974 | 32804.09 | -11744.0074 | -26% | 270 | 174 | 188.5293
24026322900 | 909 | EX | INSTALL MIWI W/ SOLAR | MOCKINGBIRD LN | F | 22593.1928 | 16866.28 | -5726.9128 | -25% |  |  | 0 | CCC# 96304 CCC# 96304 X-RAY WELD AND DROP OFF PAPERWORK. G.HALE 11-18-2024
24026323000 | 910 | EX | RETIRE FACILITIES | MOCKINGBIRD LN | F | 160.3697 | 890.43 | 730.0603 | 455% |  |  | 0 | CCC# 96304
24026329600 | 2000 | EX | INVESTIGATE ROW AND EASEMENT | 325 OLD LEMONS MILL RD |  | 6553 | 0 | -6553 | 100% |  |  | 0
24026331100 | 557 | CO | EMER - INSTALL ~5'-2" PMMP | WINDING CREEK | A | 3498.146 | 523.81 | -2974.336 | -85% | 5 |  | 0
24026331200 | 558 | CO | EMER-ABANDON ~5'-2" PMMP | WINDING CREEK | B | 118.4933 | 0 | -118.4933 | 100% |  |  | 0
24026331601 | 557 | EX | INSTALL 475' OF 2"PMMP MAIN | 226 HENTON CT | B | 110575.0083 | 142820.44 | 32245.4317 | 29% | 475 | 440 | 324.5919
24026331700 | 558 | EX | REITRE 435' OF 2"BSLP MAIN | 226 HENTON CT | B | 121.4465 | 489.56 | 368.1135 | 303% |  |  | 0
24026332800 | 557 | CO | EMER - INSTALL 5'-4" PMIP | 230 SUNDOWN | B | 3664.146 | 8388.17 | 4724.024 | 129% | 15 |  | 0
24026332900 | 558 | CO | EMER - ABANDON 5'-4" PMIP | 230 SUNDOWN | B | 118.4933 | 19.55 | -98.9433 | -84% |  |  | 0
24026336000 | 2000 | EX | INVESTIGATE LAND RIGHTS | 4200 OLD FRANKFORT PK | B | 29902 | 0 | -29902 | 100% |  |  | 0
24026338200 | 557 | CO | EMER - INSTALL 5'-3" PMMP | 1017 COLONIEL TRACE | B | 3698.1293 | 12009.27 | 8311.1407 | 225% | 5 |  | 0
24026338300 | 558 | CO | EMER - ABANDON 5'-3" PMMP | 1017 COLONIEL TRACE | B | 118.4933 | 0 | -118.4933 | 100% |  |  | 0
24026342900 | 2000 | EX | CHECK EASEMENT/LAND RIGHTS | 3530 OLD FRANKFORT PK | A | 12336 | 0 | -12336 | 100% |  |  | 0
24026344000 | 575 | EX | DOCUMENT REG STAT EASEMENT | OLD FRANKFORT PK | F | 1428.5575 | 0 | -1428.5575 | 100% |  |  | 0
24026344900 | 560 | EX | ABANDON ~30'-2" PMP | NORMANDY RD | B | 139.7787 | 0 | -139.7787 | 100% |  |  | 0
24026346100 | 557 | EX | EMER - INSTALL 2'-2" PMMP | 531 SHEFFIELD DR | A | 9472.4549 | 0 | -9472.4549 | 100% | 2 | 2 | 0
24026346200 | 558 | EX | EMER - ABANDON 2'-2" PMP | SHEFFIELD | A | 139.7787 | 0 | -139.7787 | 100% |  |  | 0
24026346900 | 587 | EX | INSTALL 2"BYPASS REGULATOR | 596 TRIPORT RD | F | 18438.8164 | 30803.34 | 12364.5236 | 67% |  |  | 0 | INSTALL BYPASS REGS, CMCHOLAN 8-28-24 0815
24026347000 | 588 | EX | RETIRE 4" BYASS REGULATORS | 596 TRIPORT RD | F | 139.7787 | 1210.3 | 1070.5213 | 766% |  |  | 0
24026350100 | 909 | EX | INSTALL RMU UNIT AT RECTIFER | 705 GLENNS CREEK RD | F | 5471.8027 | 6.49 | -5465.3127 | -100% |  |  | 0 | RM5 I/04 DOME:510102550 MODEM:501004142 INSTALLED (TE866717) AT GLENNS CREEK REC / 07-10-24 JMM
24026350200 | 910 | EX | RETIRE RMU UNIT AT RECTIFIER | 705 GLENNS CREEK RD | F | 139.7787 | 0 | -139.7787 | 100% |  |  | 0 | OLD RMU RM4014 TE 673502 RETIRED / INSTALLED NEW RMU RM5 TE 866717 / JMM 673502 RETIRED VIA UFA IN ERROR. PU NUMBER RETIRED VIA 999
24026350300 | 909 | EX | INSTALL RMU AT RECTIFIER | 1180 OLD FRANKFORT PK FG 73 | F | 6097.8027 | 5998.89 | -98.9127 | -2% |  |  | 0 | RM5 I/04 DOME:510102969 MODEM:501003622 INSTALLED (TE867224) AT AUSTIN REC 08-07-24 JMM
24026350400 | 910 | EX | RETIRE RMU UNIT | 1180 OLD FRANKFORT PK FG 73 | F | 139.7787 | 0 | -139.7787 | 100% |  |  | 0 | OLD RMU RM4010 TE 655082 RETIRED / INSTALLED NEW RMU RM5 TE 867224 / JMM
24026354500 | 566 | EX | RETIRE 4" BS-MP SERVICE LINE | 421 DUDLEY AV RR-GMB | B | 127.2637 | 0 | -127.2637 | 100% |  |  | 0
24026354600 | 565 | EX | INSTALL 790'-4" PMMP S/L | 421 DUDLEY AV RR-GMB | B | 108203.2906 | 73956.17 | -34247.1206 | -32% | 790 |  | 0
24026355200 | 555 | EX | INSTALL 150'-4" PMLP | 403 WAPPING ST | B | 34225.265 | 57369.63 | 23144.365 | 68% | 150 | 218 | 263.1634
24026355300 | 555 | EX | INSTALL 250'-2" PMMP | 101 FINANCIAL WY | B | 25692.6504 | 24464.47 | -1228.1804 | -5% | 250 | 179 | 136.673
24026357700 | 557 | EX | EMER-INSTALL 2' OF 3"PMMP MAIN | 335 CHESTNUT LN | A | 15212.4136 | 13806.96 | -1405.4536 | -9% | 2 | 2 | 6903.48
24026357800 | 558 | EX | EMER-RETIRE 3" POLY VLV C-145 | 335 CHESTNUT LN | A | 127.2637 | 0 | -127.2637 | 100% |  |  | 0
24026360200 | 557 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | FRANKFORT ST | A | 12190.8831 | 12791.75 | 600.8669 | 5% | 3 | 3 | 4263.9167 | PAPERWORK ISSUES CFD
24026360300 | 558 | EX | EMER-RETIRE 3' OF 2"PAMP MAIN | FRANKFORT ST | A | 127.2637 | 0 | -127.2637 | 100% |  |  | 0 | PAPERWORK ISSUES CFD
24026362000 | 557 | EX | EMER-INSTALL 3' OF 3"PMMP MAIN | 211 CHESTNUT LN | A | 5267.5068 | 18283.02 | 13015.5132 | 247% | 3 | 3 | 6094.34
24026362100 | 558 | EX | EMER-RETIRE 2' OF 3"PMP/VALVE | 211 CHESTNUT LN | A | 127.2637 | 12763.63 | 12636.3663 | 9,929% |  |  | 0
24026363800 | 587 | EX | INSTALL EC-350 UNIT | 5701 US 127NORTH | F | 4869.446 | 5892.2 | 1022.754 | 21% |  |  | 0
24026363900 | 588 | EX | RETIRE EFC UNIT | 5701 US 127NORTH | F | 135.7529 | 0 | -135.7529 | 100% |  |  | 0
24026372000 | 555 | EX | INSTALLING 500'-2" PMMP | AZALEA LN LT87 | B | 43811.0834 | 47889.55 | 4078.4666 | 9% | 500 | 451 | 106.1853
24026372200 | 560 | EX | PM- SEWELL RPL OUTLET SYS ABAN | US 460 / US 62 | B | 0 | 0 | 0 | 0% |  |  | 0
24026372300 | 559 | EX | PM- SEWELL REPL OUTLET SYS# | US 460 / US 62 | C | 0 | 0 | 0 | 0% |  | 2 | 0
25026377600 | 559 | EX | EMER-INSTALL 4' OF 2"PMMP MAIN | 621 POCAHONTAS TL | A | 11901.0834 | 8999.48 | -2901.6034 | -24% | 4 | 4 | 2249.87
25026377700 | 560 | EX | EMER-RETIRE 4' OF 2"PMP MAIN | 621 POCAHONTAS TL | A | 111.0024 | 0 | -111.0024 | 100% |  |  | 0
25026381100 | 909 | CO | INSTALL SCADA VISIBILITY | GLENNS CREEK PK | F | 10377.5378 | 8624.74 | -1752.7978 | -17% |  |  | 0 | CCC 114389 WELD TAPS ON PRESSURE TEST 375# INLET CCC 124465 INSTALLED ER350 AND SUPER SOLAR KIT. COMMISSIONED WITH GC. 6/10/25 DSASH
25026392000 | 555 | EX | INSTALL 140'-2" PMMP | 309 WHITE PINE LN | B | 12869.0756 | 21515.47 | 8646.3944 | 67% | 140 | 138 | 155.9092
25026403300 | 583 | EX | INSTALL MONITOR REGULATOR | COMPTON DR | F | 7027.7205 | 1909.6 | -5118.1205 | -73% |  |  | 0
25026403400 | 584 | EX | RETIRE MONITORING REG | COMPTON DR | F | 79.8251 | 1316.2 | 1236.3749 | 1,549% |  |  | 0
17026706600 | 588 | EX | CONVERT FROM GMB TO CAB ACCT | 5555 ROCKWELL RD | F | 1078.4716 | 14520.06 | 13441.5884 | 1,246% |  |  | 0 | CCC# 36905 CCC#36905
17026724700 | 560 | EX | RETIRE 350' - 3" PMLP | 102 BLUEBERRY LN | A | 2349.008 | 6306.19 | 3957.182 | 168% |  |  | 0 | PREP FOR JOB/GATHERED MATERIAL WILL DO PAPERWORK TOMORROW ABANDONED MAIN DOWNSTREAM OF METER AT 102 BLUEBERRY LN PER FOL - SOAP TEST DEAD END CAP FOR 5 MIN AT OP OK - BHB OK - 10.5 IWC VERIFIED - NRICHIE 2-20-24. IP OFF SITE.
18026766400 | 909 | EX | I&C - INSTALL SCADA EQUIPMENT | LEVEE RD | F | 183526.0448 | 143824.82 | -39701.2248 | -22% |  |  | 0 | JMULLINS COMPLETE PAPERWORK TWALKER/KY 01-24-23: JOB UNDER RUN DUE TO MATERIAL COST WAS $33,000 LESS THAN PLANNED, NO SEGA CHARGED TO JOB ORDER PROJECT WAS PLANNED FOR $23,000
18026789001 | 559 | EX | INSTALL 6900' - 4" PMMP | RICHMOND RD | B | 783479.7367 | 789465.56 | 5985.8233 | 1% | 7025 | 7098 | 111.2237
18026789100 | 560 | EX | RETIRE 600' - 3" PMMP | RICHMOND RD | B | 218.671 | 70.37 | -148.301 | -68% |  |  | 0
18026795501 | 557 | EX | INSTALL 14,600'-2,4,6,8" PMMP | MOY FOO AL | B | 3061100.231 | 3426043.78 | 364943.549 | 12% | 14640 | 13948 | 245.6298
18026795600 | 558 | EX | RETIRE 714' - 6" BSMP | MOY FOO AL | B | 124.7348 | 0 | -124.7348 | 100% |  |  | 0
18026823200 | 583 | EX | INST. FN 164 EXTRA LP OPP | 204 WILSON AV | F | 24062.1646 | 53697.68 | 29635.5154 | 123% | 50 |  | 0 | TICKET CALLED IN BY JPASLEY NOT ON SITE ROUNDED UP PARTS. GCCC# 19363 CCC# 19363 CCC# 20802 NOT ON SITE CCC# 21442 P2P WITH GAS CONTROL REGULATOR AND ER350 INSTALLED BY WADE SHIMFESSEL ON 4/27/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/21 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026823300 | 584 | EX | RET. FN 164 FOR EXTRA LP OPP | 204 WILSON AV | F | 53.6219 | 228.05 | 174.4281 | 325% |  |  | 0 | REGULATOR REPLACED BY WADE SHIMFESSEL ON 4/27/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/21 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
18026847900 | 575 | EX | ACQUIRE LAND FOR USS | ALLEY OF LINCOLN ST | F | 5291 | 7723.99 | 2432.99 | 46% |  |  | 0
19026861100 | 573 | EX | INSTALL HEATER | LEVEE RD | F | 3045.0298 | 2372.11 | -672.9198 | -22% |  |  | 0 | INSTALLED CAT HEATER
19026881900 | 2000 | EX | ACQUIRE NEW EASEMENT | 3831 COLBY RD | B | 20000 | 0 | -20000 | 100% |  |  | 0
19026902500 | 2000 | EX | ACQUIRE EASEMENT CREEK XING | BROOKS ST | B | 5335 | 0 | -5335 | 100% |  |  | 0
19026907900 | 2000 | EX | OBTAIN ADDITIONAL LAND RIGHTS | EARLY DR |  | 5472 | 0 | -5472 | 100% |  |  | 0
19026913900 | 559 | EX | INSTALL 20' - 4" CSHP | 101 US 52 | B | 45390.8034 | 82645.85 | 37255.0466 | 82% | 25 | 18 | 4591.4361 | COULD NOT REVISE DUE TO UNFULLFILLED PURCHASE ORDERS, NEEDED REVISION DUE TO EXTRA MATERIAL, INCREASE CONTRACT LABOR REQUIRED, EXTRA COMPANY LABOR, EXTRA TRUCK COSTS, AND EXTRA SEGA TTOY 3/18/2021
19026914000 | 560 | EX | RETIRE 10' - 3" CSHP | 101 US 52 | B | 114.5339 | 695.55 | 581.0161 | 507% |  |  | 0
20026917500 | 2000 | EX | 2629-COLLEGE HILL- REPL JO | COLLEGE HILL |  | 7250 | 0 | -7250 | 100% |  |  | 0
20026918201 | 909 | EX | INSTALL ELECTRONICS | EARLY DR | F | 114999.9064 | 199238.05 | 84238.1436 | 73% |  |  | 0 | CCC#17216 CCC# 19029 STATION RTU UP GRADE JPASLEY 9-27-22
20026930000 | 587 | EX | UPGRADE ELECTRONICS | 700 TECH DR | F | 3038 | 4491.87 | 1453.87 | 48% |  |  | 0 | INSTALLED NED EC350 JPASLEY 10-7-22
20026930100 | 587 | EX | UPGRADE ELECTRONICS | 125 WHEAT DR | F | 3038 | 3919.3 | 881.3 | 29% |  |  | 0 | NO TICKET NEEDED FOR THE WORK PERFORMED. 1/14/21 GCCC TICKET NOT REQUIRED PE ENGINEER CINDY SPARKS GAVE VERBAL APPROVAL ON SITE TO PROCEED WITH JOB. EFC REPLACEMENT ONLY GAS FLOW NOT INTERUPTED JOB DELAYED DUE TO COVID 19 AND COMPLIANCE WORK AND BY NOW HAVING TO BE REVIEWED BY PE ENGINEER
20026930300 | 587 | EX | UPGRADE ELECTRONICS | 435 E WASHINGTON ST | F | 3038 | 9306.71 | 6268.71 | 206% |  |  | 0 | MET MOOSE ONSITE TO INSTALL SOLAR PANEL, CELL BOOSTER,BATTERY/BOX INSTALLED NEW EC350 WSHIMFESSEL JMULLINS COMPLETED PAPER WORK 06-13-2022
20026930400 | 587 | EX | UPGRADE ELECTRONICS | 2001 OWINGSVILLE RD | F | 3038 | 6567.19 | 3529.19 | 116% |  |  | 0 | CCC TICKET NOT REQUIRED 3/29/21 CFARIS REPLACED EFC AND WORKED TP ORDER JOB ON HOLD FOR 2020 DUE TO COVID 19 GCCC TICKET NOT REQUIRED ON 3/31/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK ALSO THIS IS NON-SCADA MONITORED GMB CFARIS
20026937200 | 588 | EX | RETIRE ELECTRONICS | 700 TECH DR | F | 73.3494 | 0 | -73.3494 | 100% |  |  | 0 | RETIRE OLD MIN-AT INSTALLED NED EC350 JPASLEY 10-7-22
20026937300 | 588 | EX | RETIRE ELECTRONICS | 125 WHEAT DR | F | 73.3494 | 0 | -73.3494 | 100% |  |  | 0 | GCCC TICKET NOT REQUIRED VERBAL APPROVAL GIVEN ONSITE BY PE ENGINEER CINDY SPARKS TO WORK JOB GAS FLOW NOT INTERUPTED TO WORK JOB THIS WAS EFC REPLACEMENT ONLY JOB DELAYED DUE TO COVID 19 COMPLIANCE WORK AND WAITING REVIEW BY PE ENGINEER
20026937500 | 588 | EX | RETIRE ELECTRONICS | 435 E WASHINGTON ST | F | 73.3494 | 129.79 | 56.4406 | 77% |  |  | 0 | RETIRED MINI-AT INSTALLED NEW EC350 JMULLINS CO PAPER WORK 06132022
20026937600 | 588 | EX | RETIRE ELECTRONICS | 2001 OWINGSVILLE RD | F | 73.3494 | 0 | -73.3494 | 100% |  |  | 0 | REPLACED EFC JOB ON HOLD IN 2020 DUE TO COVID 19 GCCC TICKET NOT REQUIRED NOT AT STATION OFF SITE COMPLETING PAPERWORK ALSO THIS IS A NON-SCADA MONITORED GMB 3/31/21 CFARIS
20026940900 | 909 | EX | INSTALL I&C EQUIPMENT | PARIS BYPASS | F | 18740.1071 | 12849.77 | -5890.3371 | -31% |  |  | 0 | CCC TICKET# 55594 CCC TICKET# 55594 PAPER WORK GATHER INFO 12-15-22 JBRADFORD
20026941000 | 584 | EX | RETIRE GAUGE | PARIS BYPASS | F | 91.4991 | 1582.1 | 1490.6009 | 1,629% |  |  | 0 | CCC TICKET# 55594 CCC# 55594 ERX ONLINE P2P W/GAS CONTROL OK REMOVED CHART BOX AND FILED LAST CHART ON CABINET TICKET# 11209 GATHERED INFORMATION FOR CLOSEOUT PAPERWORK 12-15-22 JBRADFORD
20026947301 | 561 | EX | INSTALL 3,950' - 2" PMMP | HIGH ST | B | 1562557.4499 | 1895184.87 | 332627.4201 | 21% | 3950 | 4868 | 389.3149 | TTOY/KY 3/2/22: OVERRUN EXPLANATION: FLAGGER OT ESTIMATED FOR 543 HOURS BUT ACTUAL WAS 1033 HOURS, CONTRACTOR CREWS HOURLY TIME WAS OVER ESTIMATE AT 167 EXTRA HOURS, SEGA HAD EXTRA $60,000 IN COST, COMPANY LABOR HAD ADDITIONAL $27,000 COST OVER ESTIMATE
20026947400 | 562 | EX | RETIRE 5,000' - 4" CI/BS LP | HIGH ST | B | 103.8156 | 71.35 | -32.4656 | -31% |  |  | 0
20026949000 | 2000 | EX | TOYOTAL ILI PROJECT | HICKORY RIDGE RD | A | 274998 | 0 | -274998 | 100% |  |  | 0
20026949900 | 557 | EX | INSTALL 1100' - 2" PMMP | 409 E MAIN ST | B | 207915.8181 | 207663.91 | -251.9081 | 0% | 1100 | 979 | 212.1184
20026950000 | 558 | EX | RETIRE 1430' OF 2"/3" BS-MP | 409 E MAIN ST | B | 81.9085 | 2502.68 | 2420.7715 | 2,955% |  |  | 0
20026950400 | 2000 | EX | INSTALL/ADBN MAIN | 409 E MAIN ST |  | 6634 | 0 | -6634 | 100% |  |  | 0
20026953200 | 2000 | EX | RESEARCH EASEMENT AND LAND ACQ | 532 CLINTONVILLE RD |  | 4967 | 0 | -4967 | 100% |  |  | 0
20026955400 | 584 | EX | RETIRE STATION | WINSTON RD | F | 1910.2958 | 2363.47 | 453.1742 | 24% |  |  | 0 | 8561 JOB WAS ON HOLD UNTIL AFTER BEGINNING OF THE YEAR
20026956300 | 0001 | EX | DERATE MP SYSTEM 32049005 | RICHMOND RD |  | 0 | 0 | 0 | 0% |  |  | 0
20026957600 | 2000 | EX | RESEARCH LAND RIGHT | 724 DUG HILL RD | A | 2000 | 0 | -2000 | 100% |  |  | 0
20026958200 | 2000 | EX | RESEARCH LAND RIGHT | CLINTONVILLE RD | A | 2000 | 0 | -2000 | 100% |  |  | 0
20026959300 | 2000 | EX | RESEARCH EASEMENT AND ROW | 4733 ROCKWELL RD |  | 7613 | 0 | -7613 | 100% |  |  | 0
20026964102 | 557 | EX | INSTALL 4000' OF 12"CSHP MAIN | 4949 COLBY RD | B | 909258.0027 | 1045900.23 | 136642.2273 | 15% | 5500 | 3502 | 298.658 | TWALKER/KY 09-21-21: JOB OVER RUN DUE TO ADDITIONAL ENVIRONMENTAL AND SITE CLEANUP ON SITE DUE TO RAIN DURING CONSTRUCTION, THIS ADDED EXTRA $40,000 TO CONTRACT COST, PROJECT REQUIRED 2 COMPANY COORDINATORS BUT WAS PLANNED FOR 1 ADDED $35,000 IN LABOR COST AND SEGA INCREASED BY $33,000.
20026964200 | 558 | EX | RETIRE 1200' OF 12"BSHP MAIN | 4949 COLBY RD | B | 84.1799 | 3603.11 | 3518.9301 | 4,180% |  |  | 0
20026969800 | 2000 | EX | INVESTIGATE LAND RIGHTS | JOHNSON ST | B | 1910 | 0 | -1910 | 100% |  |  | 0
20026969900 | 585 | EX | INSTALL FENCE & BOLLARDS | JOHNSON ST | F | 36430.1489 | 9603.34 | -26826.8089 | -74% |  |  | 0 | INSTALLED NEW FENCE 11-19-22 JMULLINS
20026970000 | 586 | EX | RETIRE BUILDING | JOHNSON ST | F | 88.8156 | 26427.16 | 26338.3444 | 29,655% |  |  | 0 | CCC# 37831 CCC# 33819 CCC# 38966 TO BE COMP BY CFARRIS BUILDING REMOVED JMULLINS
20026976900 | 909 | EX | INSTALL RTU & INSTRUMENTATION | 724 DUG HILL RD | F | 302143.1164 | 362179.42 | 60036.3036 | 20% |  |  | 0 | CCC# 2490 CCC# 2490 CCC# 2490 CCC# 5078 6417 CCC# 7314 CCC# 7314 CCC# 7314 CCC# 6417 CCC# 6417 CCC# 6417 CCC# 6417 CCC# 6417
20026977000 | 910 | EX | RETIRE RTU & INSTRUMENTATION | 724 DUG HILL RD | F | 60.3089 | 2598.25 | 2537.9411 | 4,208% |  |  | 0
20026979600 | 559 | EX | INSTALL 20' - 2"/6" PMMP | WILSON AV | B | 65238.0736 | 106288.64 | 41050.5664 | 63% | 105 | 29 | 3665.1255 | ATTEMPTED TO REVISE DUE TO EXTRA HOURLY COST, COULD NOT REVISE DUE TO UNFULLFILLED PURCHASE ORDER TTOY 3/18/2021 OVERRUN EXPLANATION: JO WAS ORIGINALLY PLANNED ON 2018 FISHEL CONTRACT, JO WAS EXECUTED USING 2020 STANLEY PIPELINE CONTRACT, EXTRA VAC EXCA, EXTRA WLD AND RIG, EXTRA TOP SOIL REQUIRED, EXTRA HOURLY CREW REQUIRED, ESTIMATED HOURLY TIME WAS 56 HOURS, ACTUAL HOURLY TIME WAS 398 HOURS, ESTIMATED CONTRACT COST WAS $35,000, ACTUAL CONTRACT COST WAS $51,000
20026979700 | 560 | EX | RETIRE 15' - 2" BSLP | WILSON AV | B | 92.1481 | 71.35 | -20.7981 | -23% |  |  | 0
20026980401 | 557 | EX | INSTALL 13,025'-PMMP/CSHP | MT STERLING PK | B | 1836238.4697 | 2259933.17 | 423694.7003 | 23% | 12625 | 6818 | 331.4657 | OVERRUN EXPLANATION: PROJECT INCLUDED ADDITIONAL PAVING THAT WAS UNFORSEEN DUE TO CITY REQUIREMENTS, SEGA HAD AN INCREASE OF OVER $100,000 TTOY 3/2/2023
20026980500 | 558 | EX | RETIRE 12,520' - LP MAIN | MT STERLING PK | B | 52.2976 | 809.88 | 757.5824 | 1,449% |  |  | 0
20026980601 | 557 | EX | INSTALL 16,200'-2"/4" PMMP | HIGGINS ST | B | 4665902.1359 | 4720247.08 | 54344.9441 | 1% | 16925 | 20509 | 230.1549
20026980700 | 558 | EX | RETIRE MAIN - LEAKAGE | HIGGINS ST | B | 103.8156 | 2546.03 | 2442.2144 | 2,352% |  |  | 0
20026981601 | 557 | EX | INSTALL 9,950' OF 2"/4"/6"PMMP | MAIN ST | B | 3261487.9737 | 3477462.23 | 215974.2563 | 7% | 9980 | 9263 | 375.4143
20026981700 | 558 | EX | RETIRE 15,000' - LP MAIN | MAIN ST | B | 82.4486 | 0 | -82.4486 | 100% |  |  | 0
20026981800 | 558 | EX | RETIRE 18,000 - MP MAIN | MAIN ST | B | 82.4486 | 0 | -82.4486 | 100% |  |  | 0
20026987900 | 2000 | EX | INVESTIGATE CONFLICT | HIGH ST | B | 24268 | 0 | -24268 | 100% |  |  | 0
20026988200 | 2000 | EX | INVESTIGATE LAND RIGHTS | MAIN ST | B | 10944 | 0 | -10944 | 100% |  |  | 0
20026990100 | 559 | EX | INSTALL 6" SS | WILSON AV | B | 1607.8146 | 245.63 | -1362.1846 | -85% |  |  | 0
20026992600 | 558 | EX | RETIRE MP MAIN | RUCKER ST | B | 103.8156 | 0 | -103.8156 | 100% |  |  | 0
21026101900 | 566 | EX | RETIRE 6"MP SERVICE LINE | 824 KY HIGHWAY 356 | B | 9764.3857 | 9737.82 | -26.5657 | 0% |  |  | 0 | INSTALLED BOLTED DEAD END CAP AT END OF NC 216695 VALVE. JOSH PASLEY 6/14/22
21026102700 | 2000 | EX | INVESTIGATE INCROACHMENT | MACK ST |  | 694 | 0 | -694 | 100% |  |  | 0
21026103400 | 555 | EX | INSTALL 2,700' - 2"/4" PMMP | HIBISCUS LN LT101 | B | 115766.1902 | 185537.75 | 69771.5598 | 60% | 3200 | 2712 | 68.4136 | TTOY-9/20/22: LEVEL 2 VARIANCE OVERRUN EXPLANATION IN WMSDOCS
21026104700 | 910 | EX | REMOVE OBSOLETE ELECTRONICS | EARLY DR | F | 135.8546 | 236.27 | 100.4154 | 74% |  |  | 0 | INSTALLED NEW RTU BUILDING AND TRANSMITTERS JPASLEY 9-27-2022
21026106700 | 2000 | EX | INVESTIGATIVE ENCROACHMENT | 415 MAGNOLIA ST | B | 10000 | 0 | -10000 | 100% |  |  | 0 | TWALKER/KY 06-27-24: PER MEDHA LALLBEEHARRYWITH CAPITAL OVERSIGHT SR ANALY ST ADVISED TO CHARGED THIS JOB TO O/M
21026107000 | 555 | EX | INSTALL 250' - 2" PMMP | 808 INDIAN MOUND DR | B | 25983.7669 | 72807.39 | 46823.6231 | 180% | 250 | 304 | 239.498 | OVERRUN EXPLANATION: PROJECT WAS PLANNED FOR OPEN CUT, NEW MAIN WAS INSTALL ED BY HEAVY ROCK BORE, ADDITIONAL LAND SERVICES WAS REQUIRED FOR EASMENT, BORE CREW HOURLY WAS MORE THAN ESTIMATED 3 MAN CREW
21026108400 | 557 | EX | EMER - INSTALL 350' - 4" PMMP | ROCKWELL RD | B | 44073.8715 | 86916.93 | 42843.0585 | 97% | 400 | 343 | 253.4021 | OVERRUN EXPLANATION: HOURLY TIME EXTIMATED AT 48 HOURS, ACTUAL TIME WAS 97 HOURS, SEGA WAS DOUBLED, CONTRACT WAS ESTIMATED FOR $29,000, ACTUAL WAS $68,000, PROJECT WAS ESTIMATED TO DIRECTIONAL BORE 150', ACTUAL INSTALL WAS OPEN CUT 345', PROJECT REQUIRED EXTRA PAVING DUE TO OPEN CUT, PROJECT REQUIRED EXTRA PROCESSED AND STONE DUST DUE TO OPEN CUT, EXTRA VACUUM EXCAV ATING WAS REQUIRED, ESTIMATED FOR 4 MAN CREW CONTRACT, ACTUAL USED 3 MAN, 4 MAN, AND 5 MAN CREWS
21026108500 | 558 | EX | EMER - RETIRE 350' - 4" PMP | ROCKWELL RD | B | 85.3307 | 4479.43 | 4394.0993 | 5,149% |  |  | 0
21026110900 | 585 | EX | INSTALL REPLACEMENT FENCE | 724 DUG HILL RD | F | 44982.9906 | 4971.16 | -40011.8306 | -89% |  |  | 0 | CCC# 30433 MONITORED FENCE INSTALLATION CCC# 30433 CCC# 30596 CC# 30596 MONTOR STATION CCC# 30956 NEW FENCE INSTALLED WSHIMFESSEL 07-09-2021 UNDERRUN EXPLANATION: COST WAS SIGNIFICANTLY LESS THAT WHAT THE CONTRACTOR HAD ESTIMATED OVER THE PHONE.
21026111300 | 584 | EX | RETIRE R-1654 | CARHART AV | F | 3585.1779 | 0 | -3585.1779 | 100% |  |  | 0 | ENTIRE STATION RETIRED INCLUDING INLET AND OUTLET PIPING WSHIMFESSEL 5/10/2 022, RWILLIAMS COMPLETED JOB AND PAPERWORK
21026111400 | 584 | EX | RETIRE R-1653-B LP | MAIN ST | F | 3585.1779 | 0 | -3585.1779 | 100% |  |  | 0 | RETIRED LP RUN FROM R-1653 BLIND FLANGED INLET VALVE AND BYPASS VALVE WSHIM FESSEL, RWILLIAMS COMPLETED JOB AND PAPERWORK
21026112900 | 555 | EX | INSTALL 150' - 2" PMMP | 1048 CRESTWOOD HT | B | 15892.286 | 14483.58 | -1408.706 | -9% | 150 | 130 | 111.4122
21026113300 | 2000 | EX | INVESTIGATE PIPELINE EASEMENT | 200 COMMERCE DR | B | 2421 | 0 | -2421 | 100% |  |  | 0
21026116000 | 2000 | EX | INVESTIGATE/ACQUIRE EASEMENT | 236 REDWING DR | B | 5360 | 0 | -5360 | 100% |  |  | 0
21026117400 | 563 | EX | INSTALL 190' - 4" PMMP SL | 605 ROLLING HILLS LN 1 | B | 22441.9346 | 40096.06 | 17654.1254 | 79% | 190 |  | 0 | INSTALLED 243'OF 4"PMP FOR SL TO FEED PSID 501307207-CAPPED AND BURRIED END OF SL FOR FUTURE TIE IN/INSTALLATION OF RISER AND SETTING ONCE FURTHER SITE CONSTRUCTION IS COMPLETED,PER CG ENGINEER J TOY AND CONSTRUCTION SITE GC- LINE MARKER WITH WIRE AT TAP,WIRE IN VALVE BOX,AND MARKER BALLS AT ALL CHANGES OF DIRECTIONAND END OF SL INSTALLED FOR LOCATABILITY
21026117500 | 587 | EX | INSTALL GMB SETTING | 605 ROLLING HILLS LN | F | 58469.7613 | 77589.89 | 19120.1287 | 33% |  |  | 0
21026119100 | 2000 | EX | INVESTIGATE RELOCATION | LINCOLN ST |  | 9923 | 0 | -9923 | 100% |  |  | 0
21026119200 | 559 | EX | PM- LAKE CARNICO REPLACEMENT | LAKESHORE RD | C | 3161436 | 3041365.07 | -120070.93 | -4% |  | 164 | 18544.909
21026119300 | 560 | EX | PM- LAKE CARNICO ABANDONMENT | LAKESHORE RD | C | 62500 | 739279.78 | 676779.78 | 1,083% |  |  | 0
21026120000 | 559 | EX | PM-PARIS CYNTHIANA REPLACEMENT | US 27 | C | 1087500 | 3020752.24 | 1933252.24 | 178% |  | 4 | 755188.06
21026120100 | 560 | EX | PM-PARIS CYNTHIANA ABANDONMENT | US 27 | C | 62500 | 325920.13 | 263420.13 | 421% |  |  | 0
21026120900 | 557 | EX | INSTALL 5' - 3" PMLP | 56 FLANAGAN ST | A | 1134.2677 | 1085.98 | -48.2877 | -4% | 5 | 3 | 361.9933
21026121000 | 558 | EX | RETIRE 5' - 3" PMLP | 56 FLANAGAN ST | A | 58.9085 | 0 | -58.9085 | 100% |  |  | 0
21026121100 | 557 | EX | INSTALL 5' - 4" PMMP | GARDEN SPRINGS | A | 2822.803 | 2417.89 | -404.913 | -14% | 10 | 10 | 241.789
21026121200 | 558 | EX | RETIRE 5' - 4" PMLP | GARDEN SPRINGS | A | 58.9085 | 0 | -58.9085 | 100% |  |  | 0
21026123100 | 561 | EX | INSTALL 175'-4" PMMP | LINCOLN ST | B | 39889.572 | 53913.76 | 14024.188 | 35% | 205 | 161 | 334.8681
21026123200 | 562 | EX | RETIRE 200'-4" BSMP | LINCOLN ST | B | 77.7619 | 0 | -77.7619 | 100% |  |  | 0
21026123300 | 561 | EX | INSTALL 125'-2" PMMP | PRIMROSE LN | B | 28847.4767 | 36910.92 | 8063.4433 | 28% | 125 | 124 | 297.6687
21026123400 | 562 | EX | RETIRE 160'-4" PMMP | PRIMROSE LN | B | 77.7619 | 0 | -77.7619 | 100% |  |  | 0
21026123500 | 2000 | EX | INVESTIGATE ROAD R/W | PRIMROSE LN | B | 3360 | 0 | -3360 | 100% |  |  | 0
21026125100 | 562 | EX | RETIRE 175' - 3" LP | LINCOLN ST | B | 88.1542 | 0 | -88.1542 | 100% |  |  | 0
21026125200 | 561 | EX | INSTALL 3" SS | LINCOLN ST | B | 20373.572 | 5010.94 | -15362.632 | -75% |  |  | 0
21026128200 | 555 | EX | INSTALL 1,300 OF 2"/4"PMMP | GIBSON WY LT21 | B | 51810.9858 | 56524.7 | 4713.7142 | 9% | 1350 | 1500 | 37.6831
21026129100 | 2000 | EX | TRC - DESIGN 4400' 6-INCH PMP | ROCKWELL RD |  | 20000 | 0 | -20000 | 100% |  |  | 0
21026130100 | 2000 | EX | INVESTIGATE OUT OF EASEMENT | COMBS FERRY RD |  | 5000 | 0 | -5000 | 100% |  |  | 0
21026135300 | 566 | EX | ABANDON 120'-4" PL SL | 605 ROLLING HILLS LN 1 | B | 82.634 | 0 | -82.634 | 100% |  |  | 0
21026135400 | 565 | EX | INSTALL 100'-4" PL SL | 605 ROLLING HILLS LN 1 | B | 10216.5972 | 12266.69 | 2050.0928 | 20% | 100 |  | 0
21026135900 | 555 | EX | INSTALL 140'-2" PMMP | 275 EVANS DR | B | 14039.3957 | 8332.52 | -5706.8757 | -41% | 140 | 153 | 54.4609
21026136700 | 555 | EX | INSTALL 1,750'-2" PMMP | SAND RIDGE LN LT1C | B | 49760.6579 | 47459.5 | -2301.1579 | -5% | 1750 | 1626 | 29.1879
21026137300 | 575 | EX | OBTAIN EASEMENT FOR POD | 724 DUG HILL RD | F | 18975 | 18834.81 | -140.19 | -1% |  |  | 0
21026137400 | 558 | EX | RETIRE 120'-1" PMP - D304537 | 2450 UNION CITY RD BLDG | A | 3638.7915 | 399.97 | -3238.8215 | -89% |  |  | 0
21026137900 | 583 | EX | INSTALL OUTLET VLV R-1643 | GAWTHROP DR | F | 110321.1916 | 80161.67 | -30159.5216 | -27% | 160 |  | 0 | CCC# 80227 MONITOR WHILE BACKFILLING INSTALLED ALL NEW STATION VALVES JPASLEY 9-8-22 UNDERRUN EXPLANATION: PROJECT INCLUDED $27,000 OF CONTINGENCY AND HAD AN UNDERRUN OF 30,492 TTOY 3/2/23
21026138000 | 584 | EX | RETIRE OUTLET VLV R-1643 | GAWTHROP DR | F | 955.7874 | 0 | -955.7874 | 100% |  |  | 0 | RETIRED ALL STATION VALVES AND INSTALLED NEW VALVES JPASLEY 9-8-22
21026138100 | 2000 | EX | INVESTIGATE LAND RIGHTS | MAPLE ST | B | 11969 | 0 | -11969 | 100% |  |  | 0
21026138400 | 557 | EX | EMER-INSTALL 2' OF 1"PMMP MAIN | 2450 UNION CITY RD | A | 3122.8539 | 227.74 | -2895.1139 | -93% | 2 | 2 | 113.87
21026138500 | 558 | EX | EMER-RETIRE 2'-1"PAMP MAIN | 2450 UNION CITY RD | A | 82.634 | 0 | -82.634 | 100% |  |  | 0
21026140000 | 562 | EX | RETIRE 489'-4" PMP | YEISER RD | B | 13697.8754 | 20306.35 | 6608.4746 | 48% |  |  | 0
21026140300 | 2000 | EX | DESIGN SMRP PROJECT | BURNS AV |  | 35000 | 0 | -35000 | 100% |  |  | 0
21026140501 | 557 | EX | INSTALL 1,985'-6" CSHP | PARIS PK | B | 116515.0569 | 143065.13 | 26550.0731 | 23% |  | 1874 | 76.3421
21026140600 | 558 | EX | RETIRE 2,598'- 6" BSHP | PARIS PK | B | 61.5191 | 182.4 | 120.8809 | 196% |  |  | 0
21026140700 | 558 | EX | RETIRE 2,200' - CSMP | N MAPLE ST | B | 61.2976 | 0 | -61.2976 | 100% |  |  | 0
21026141900 | 2000 | EX | INVESTIGATE AND ACQUIRE ESMNT | SAND RIDGE LN LT1C | B | 14971 | 0 | -14971 | 100% |  |  | 0
21026142000 | 557 | EX | EMER - INSTALL 5'-2" PMMP | WACO LOOP | A | 7513.9749 | 11087.26 | 3573.2851 | 48% | 5 | 5 | 2217.452
21026142100 | 558 | EX | EMER - RETIRE 5'-3" PMMP | WACO LOOP | A | 69.8875 | 0 | -69.8875 | 100% |  |  | 0
21026142300 | 557 | EX | EMER - INSTALL 5'-2" PMMP | 17 CHURCHILL DR | A | 3984.9999 | 11040.25 | 7055.2501 | 177% | 5 | 9 | 1226.6944
21026142400 | 558 | EX | EMER - RETIRE 5'-2" PMP | 17 CHURCHILL DR | A | 69.8875 | 133.69 | 63.8025 | 91% |  |  | 0
21026142900 | 2000 | EX | INVESTIGATE RR & STATE PERMIT | MAIN ST | B | 12497 | 0 | -12497 | 100% |  |  | 0
21026143100 | 2000 | EX | INVESTIGATE LAND RIGHTS | YEISER RD | B | 8053 | 0 | -8053 | 100% |  |  | 0
21026143200 | 559 | EX | EMER - INSTALL 450'- 4" CSHP | MAIN ST | B | 196595.4538 | 257776.24 | 61180.7862 | 31% | 455 | 496 | 519.7102 | PROJECT WAS CODED AMRCB BECAUSE THE PIPE UNDER THE BRIDGE HAD NO COATING. OVERRUN EXPLANATION: MAIN REASON FOR PROJECT COST OVERRUN IS DUE TO 2,000 UNITS OF ASPHALT PAVING WHEN ONLY 1,000 UNITS WERE PLANNED. THE STATE REQUIRED EXTRA PAVING DUE TO EXISTING ROAD CONDITION.THE PROJECT WAS PLANNED FOR 1 CONSTRUCTION COORDINATORBUT ENDED UP HAVING MULTIPLE AND DOUBLED THE COMPANY LABOR CHARGES. FLAGGING FOR THEPROJECT INCLUDED A 30% INCREASECOMPARED TO THE PLANNED AMOUNT. THE PROJECT INCLUDED AN ADDITIONAL 49 UNITS OF STEELMAINLINE INSTALLATION AND ROCK AND LEDGE EXCAVATIONWAS REQUIRED BUT NOT PLANNED. TTOY 12/2/22
21026143300 | 560 | EX | EMER - RETIRE 100'-3" CSHP | MAIN ST | B | 61.5191 | 3034.48 | 2972.9609 | 4,833% |  |  | 0
21026145100 | 2000 | EX | INVESTIGATE POD | 201 MILLER DR |  | 50000 | 0 | -50000 | 100% |  |  | 0
21026147700 | 557 | EX | EMER - INSTALL 5'-2" PMMP | DOYLESVILLE | A | 2686.3426 | 2531.33 | -155.0126 | -6% | 5 | 3 | 843.7767 | REPLACED 3' SECTION OF 2" PMP AFTER DIG IN. PRESSURE TESTED NEW MAIN AT 90 PSIG FOR 1 HOUR, SOAP TESTED FINAL TIE IN AT OP. OK 34 PSIG VERIFIED NRICHIE 10-20-21
21026147800 | 558 | EX | EMER - RETIRE 5'-2" PMP | DOYLESVILLE | A | 61.5191 | 0 | -61.5191 | 100% |  |  | 0
21026149300 | 2000 | EX | TRC TO INVEISTIGATE PERM SOL | HWY 52 |  | 32929 | 0 | -32929 | 100% |  |  | 0
21026149800 | 584 | EX | RETIRE R-1615 | ALLEY OFF MAIN ST | F | 16113.7857 | 552.62 | -15561.1657 | -97% |  |  | 0
21026152700 | 583 | EX | EMER - INSTALL ODORIZER | STATE RT 89 | F | 303602.2828 | 170463.75 | -133138.5328 | -44% |  |  | 0 | UNDERRUN EXPLANATION: PROJECT DID NOT REQUIRE AS MUCH CONTINGENCY, OR OUTSIDE LABOR COSTS FROM CONTRACTORS TTOY 3/2/23
21026152800 | 584 | EX | EMER - RETIRE ODORIZER | STATE RT 89 | F | 61.5191 | 62508.06 | 62446.5409 | 101,508% |  |  | 0
21026154300 | 2000 | EX | SURVEY ENCROACHMENT | 229 MAIN ST | B | 5000 | 0 | -5000 | 100% |  |  | 0 | ENCROACHMENT INVESTIGATED, WAITING FUNDING.
21026155000 | 2000 | EX | SURVEY ENCROACHMENT | 235 MAIN ST |  | 5000 | 0 | -5000 | 100% |  |  | 0
21026155200 | 2000 | EX | SURVEY ENCROACHMENT | 413 MIMOSA DR |  | 5000 | 0 | -5000 | 100% |  |  | 0
21026155300 | 2000 | EX | SURVEY ENCROACHMENT | CORK AV |  | 5000 | 0 | -5000 | 100% |  |  | 0
21026155400 | 2000 | EX | SURVEY ENCROACHMENT | YORKTOWN DR |  | 5000 | 0 | -5000 | 100% |  |  | 0
21026156100 | 557 | EX | EMER-INSTALL 6' OF 2"PMMP MAIN | 25 WESTCHESTER DR | A | 6138.1743 | 5612.12 | -526.0543 | -9% | 6 | 6 | 935.3533
21026156200 | 558 | EX | EMR-RET 6'-2"PMP MAIN D222323 | WESTCHESTER DR | A | 61.2976 | 75.03 | 13.7324 | 22% |  |  | 0
21026157501 | 557 | EX | EMER - INSTALL 5'-3" PMMP | 1525 W LEXINGTON AV | A | 13441.7151 | 24476.25 | 11034.5349 | 82% | 5 | 4 | 6119.0625
21026157600 | 558 | EX | EMER - RETIRE 5'-3" PAMP | 1525 W LEXINGTON AV | A | 72.8047 | 106.63 | 33.8253 | 46% |  |  | 0
21026993100 | 562 | EX | RETIRE 229' - PMMP | HIGH ST | B | 103.8156 | 0 | -103.8156 | 100% |  |  | 0
21026996700 | 557 | EX | EMER - INSTALL 10'-4" PMMP | US HWY 60 | A | 1997.1109 | 1315.39 | -681.7209 | -34% | 10 | 5 | 263.078
21026996800 | 558 | EX | EMER - RETIRE 10'-4" PMMP | US HWY 60 | A | 95.6296 | 0 | -95.6296 | 100% |  |  | 0
21026999000 | 566 | EX | RETIRE 4"PLP SERVICE LINE | 405 4TH ST | B | 5007.8601 | 4696.25 | -311.6101 | -6% |  |  | 0
22026158000 | 555 | EX | INSTALL 200'-2" PMMP | 1056 CRESTWOOD HT | B | 16273.357 | 23838.83 | 7565.473 | 46% | 200 | 102 | 233.714
22026159500 | 557 | EX | EMER - INSTALL 5'-3" PMMP | 1183 US HWY 27 N | A | 5999.0379 | 11760.26 | 5761.2221 | 96% | 5 | 2 | 5880.13
22026159600 | 558 | EX | EMER - RETIRE 5' - 3" PMMP | 1183 US HWY 27 N | A | 79.0999 | 0 | -79.0999 | 100% |  |  | 0
22026161400 | 2000 | EX | REPLACE STATION VALVES | RED LICK RD |  | 15000 | 0 | -15000 | 100% |  |  | 0
22026161800 | 557 | EX | INSTALL 8" PCF | MOY FOO AL | B | 147.7348 | 29544.9 | 29397.1652 | 19,899% |  |  | 0
22026161900 | 558 | EX | RETIRE LP MAIN - LEAKAGE | MOY FOO AL | B | 124.7348 | 1465.95 | 1341.2152 | 1,075% |  |  | 0
22026162300 | 2000 | EX | INVESTIGATE EASEMENT FOR DKZ | 1495 MUDDY CREEK RD |  | 5000 | 0 | -5000 | 100% |  |  | 0
22026162800 | 2000 | EX | ACQUIRE SITE SURVEY | 724 DUG HILL RD |  | 12301 | 0 | -12301 | 100% |  |  | 0 | CCC# 54722
22026163000 | 573 | EX | INSTALL ODORIZER | 724 DUG HILL RD | F | 596431.4654 | 421358.34 | -175073.1254 | -29% |  |  | 0
22026164000 | 557 | EX | INSTALL 5,100'-2" PMMP | SCOTT AV | B | 1140024.6985 | 1341919.13 | 201894.4315 | 18% | 5130 | 5198 | 258.1607
22026164100 | 558 | EX | RETIRE 6,711'-BS/CS IP | SCOTT AV | B | 74.3089 | 663.39 | 589.0811 | 793% |  |  | 0
22026164201 | 557 | EX | INSTALL 2,300'-2" PMMP | SPRING ST | B | 442002.9907 | 487634.39 | 45631.3993 | 10% | 2310 | 2210 | 220.649
22026164300 | 558 | EX | RETIRE 3,574'-BSLP | SPRING ST | B | 84.9152 | 136.8 | 51.8848 | 61% |  |  | 0
22026165200 | 575 | EX | ACQUIRE REG STA EASEMENT | 630 CLINTONVILLE RD | F | 25672 | 32454.4 | 6782.4 | 26% |  |  | 0
22026168900 | 909 | EX | STEPSTONE POD HVAC UPGRADE | STEPSTONE RD | F | 15710.0767 | 19703.94 | 3993.8633 | 25% |  |  | 0 | CCC# 59338 CCC# 55889 UPGRADED RTU JOSH MULLINS
22026169100 | 909 | EX | RT. 89 POD RTU BUILDING | STATE RT 89 | F | 143652.6755 | 221479.78 | 77827.1045 | 54% |  |  | 0 | CCC# 13947 MONITOR NOT ONSITE ACP NOT WORKING AT THAT SITE TODAY CCC# 13947 NOT ONSITE NOT ONSITE CCC#21297 CCC# 31371
22026169400 | 2000 | EX | INVESTIGATE LAND RIGHTS | GAWTHROP DR |  | 3241 | 0 | -3241 | 100% |  |  | 0
22026170000 | 2000 | EX | SURVEY ENCROACHMENT | AUBERY LANE | B | 5000 | 0 | -5000 | 100% |  |  | 0
22026170100 | 2000 | EX | SURVEY ENCROACHMENT | ELIZABETH | B | 5000 | 0 | -5000 | 100% |  |  | 0
22026170200 | 2000 | EX | SURVEY ENCROACHMENT | DANIEL DR | B | 5000 | 0 | -5000 | 100% |  |  | 0
22026170600 | 557 | EX | INSTALL 7,200'-2"/4" PMMP | HOLT AV | B | 1129128.3572 | 1527638.88 | 398510.5228 | 35% | 7225 | 7917 | 192.9568
22026170700 | 558 | EX | RETIRE BSLP | HOLT AV | B | 89.0305 | 0 | -89.0305 | 100% |  |  | 0
22026171000 | 2000 | EX | DESIGN RIVER CROSSING | 20 S IRVINE RD |  | 30000 | 0 | -30000 | 100% |  |  | 0
22026172200 | 2000 | EX | CONFLICT ASSESSMENT & RELO DES | 31 W BROADWAY |  | 3000 | 0 | -3000 | 100% |  |  | 0
22026172500 | 557 | EX | INSTALL 5'-1" PMMP | 2450 UNION CITY RD | A | 1353.2384 | 4.3 | -1348.9384 | -100% | 5 | 1 | 4.3
22026172600 | 558 | EX | RETIRE 5'-1" PAMP | 2450 UNION CITY RD | A | 66.5954 | 2198.83 | 2132.2346 | 3,202% |  |  | 0
22026173100 | 2000 | EX | INVESTIGATE ROW | MOY FOO AL | B | 5214 | 0 | -5214 | 100% |  |  | 0
22026173200 | 2000 | EX | INVESTIGATE ROW AND RR PERMIT | SCOTT AV | B | 5214 | 0 | -5214 | 100% |  |  | 0
22026173300 | 2000 | EX | INVESTIGATE ROAD ROW | SPRING ST | B | 5214 | 0 | -5214 | 100% |  |  | 0
22026173400 | 2000 | EX | INVESTIGATE ROW | HOLT AV | B | 5214 | 0 | -5214 | 100% |  |  | 0
22026173700 | 909 | EX | 2022 SCADA VISIBILITY PROGRAM | WISEMANTOWN RD | F | 29658.8599 | 28387.14 | -1271.7199 | -4% |  |  | 0 | CCC# 66803 CCC# 66803 MONITOR FOR NEW COMM INSTALL CCC# 80236 INSTALLED NEW MIWI350 EBLANTON 9-22-2022
22026175300 | 584 | EX | RETIRE R-1278 | HIGGINS ST | F | 7307.4769 | 1891.36 | -5416.1169 | -74% |  |  | 0 | PREMISE IS RETIRED. GATHERED INFORMATION FOR CLOSEOUT PAPERWORK. JBRADFORD 12-15-22 CCC# 20387 TICKET# 20387
22026175400 | 584 | EX | RETIRE R-1258 | THOMAS ST | F | 7307.4769 | 114.11 | -7193.3669 | -98% |  |  | 0 | CCC# 77893 STATIONRETIRED PER AMRP PROJECT WSHIMFESSEL 8-26-2022 ALL FACILITIES REMOVE D
22026175500 | 584 | EX | RETIRE R-1275 | SHORT ST | F | 7307.4769 | 648.29 | -6659.1869 | -91% |  |  | 0 | CCC# 77909 RETIRED REG STATION R-1275 ON AMRP PROJECT WSHIMFESSEL 8-26-2022 PREMISE IS RETIRED. GATHERED INFORMATION FOR CAPITOL CLOSEOUT.
22026175600 | 584 | EX | RETIRE R-1256 | HIGGINS ST | F | 7307.4769 | 211.37 | -7096.1069 | -97% |  |  | 0 | STATION RETIRED AND ALL PIPING REMOVED WSHIMFESSEL 06-07-2022
22026177400 | 2000 | EX | INVESTIGATE AND AQUIRE EASEMEN | KIRKLAND AV |  | 50000 | 0 | -50000 | 100% |  |  | 0
22026177500 | 557 | EX | EMER - INSTALL 800'-6" CSHP | KY RIVER | B | 663631.3961 | 1030814.44 | 367183.0439 | 55% | 960 | 917 | 1124.1161 | LEVEL 2 VARIANCE EXPLANATION IN WMSDOCS TTOY 2/3/23
22026177600 | 558 | EX | EMER-RETIRE 800'-4" CSHP | KY RIVER | B | 84.9152 | 1361.76 | 1276.8448 | 1,504% |  |  | 0
22026177700 | 561 | EX | INSTALL 56'-6" PM-LP | 31 W BROADWAY ST | B | 50137.1407 | 107530.2 | 57393.0593 | 114% | 42 | 175 | 614.4583 | OVERRUN EXPLANATION: PROJECT WAS INITIALLY PLANNED FOR 56 FEET OF INSTALL. HOWEVER, 171 FEET OF DIRECTIONAL ROCK BORE WERE REQUIRED INSTEAD WITHOUT A SCOPE CHANGE REQUEST. ADDITIONAL SAW CUT AND CUT AND REMOVE WERE REQUIRED A S WELL. STEEL PLATES WERE NOT ESTIMATED. $7000 OF SEWER CAMERA WERE NOT EST IMATED EITHER SINCE IT WAS INITALLY PLANNED DIFFERENTLY. ALL THIS ADDITIONA L WORK TOOK MORE TIME SO LABOR INCREASED BY $19,000 AND THE OVERHEAD EFFECT OF THESE CHANGES WAS $9000.
22026177800 | 562 | EX | ABDN 20'-6" BS-LP | 31 W BROADWAY ST | B | 73.9724 | 142.7 | 68.7276 | 93% |  |  | 0
22026178200 | 555 | EX | INSTALL 850'-2" PMIP | 1006 WARRIORS TR LT48 | B | 33743.7503 | 28727.79 | -5015.9603 | -15% | 850 | 773 | 37.164
22026182101 | 555 | EX | INSTALL 8,450' - 2"/4" PMMP | 2130 MCCLURE RD | B | 861854.0803 | 940113.78 | 78259.6997 | 9% | 8505 | 7986 | 117.7202
22026183800 | 555 | EX | INSTALL 100'-2" PMIP | 421 S WINN AV | B | 18017.5748 | 16969.45 | -1048.1248 | -6% | 125 | 91 | 186.4775
22026184000 | 561 | EX | INSTALL 200'-6"/8" PMLP | MAIN ST | B | 169438.8752 | 210431.38 | 40992.5048 | 24% | 240 | 215 | 978.7506 | OVERRUN EXPLANATION: PROJECT WAS PLANNED FOR 360 HOURS OF LABOR TIME BUT ENDED UP WITH 565 HOURS DUE TO MULTIPLE COORDINATORS AND WELDER CHARGING 125 HOURS, SEGA WAS ORIGINALLY $20,641 BUT ENDED UP AT $34,463, PROJECT REQUIRED 698 TONS OF STONE AND DUST BUT WAS ORIGINALLY PLANNED FOR 60 TONS, ADDITIONAL EXTRA DEPTH UNITS OF 134, PROJECT ALSO CHAR CHARGED ~$6,000 OF SEWER CAMERA EVEN THOUGH THE SEWER WAS ALREADY UNCOVERED WHICH IS WHY WE WERE INSTALLING THE RELOCATION. TTOY 2/3/23
22026184100 | 562 | EX | RETIRE 100'-BSLP | MAIN ST | B | 65.0112 | 400 | 334.9888 | 515% |  |  | 0
22026184200 | 0001 | EX | MATERIAL FOR KY RIVER BORE | KY RIVER |  | 100000 | 0 | -100000 | 100% |  |  | 0
22026185100 | 557 | EX | INSTALL 10'-2" PMMP | 4760 LEVEE RD | A | 3850.4525 | 6123.2 | 2272.7475 | 59% | 30 | 2 | 3061.6
22026185200 | 558 | EX | RETIRE 10'-2" PMP | 4760 LEVEE RD | A | 74.2578 | 0 | -74.2578 | 100% |  |  | 0
22026188100 | 0001 | EX | KA-2 WIRE-LINE PIGGING |  | A | 2479.682 | 0 | -2479.682 | 100% |  |  | 0
22026188800 | 2000 | EX | INVESTIGATE ENCROACHMENT | 302 JEREMIAH DR |  | 4510 | 0 | -4510 | 100% |  |  | 0
22026190100 | 0001 | EX | PM- 1" REPAIR TRACKING |  |  | 0 | 0 | 0 | 0% |  |  | 0
22026190400 | 0001 | EX | COMBINE 32010039 & 32010023 | RIDINGS RD |  | 8563.1746 | 0 | -8563.1746 | 100% |  |  | 0 | TWALKER/KY 09-21-23: THIS JOB ORDER DOCUMENTS THE DOWNRATE OF 32010039 FROM MAOP OF 60PSIG TO 45PSIG AND COMBINE WITH SYSTEM 32010023 (MAOP 45PSIG TWO SYSTEM TIED TOGETHER VIA JOB 22-0261621-01 WITH PROJECT ID 22-88186. GAS SYSTEM PLANNING HAS MOVED ALL CUSTOMER TO 32010023 AND WILL MOVE 32010039 TO INACTIVE STATUS ON DIS CONTROL TABLES.
22026190700 | 559 | EX | INSTALL 4" SS *PAPER ONLY*** | BROADWAY ST | B | 84.2578 | 0 | -84.2578 | 100% |  |  | 0 | FACILITY CREATED ON JO 20-0269816-01. UNABLE TO EDIT. SS ALREADY ABANDONED ON JO 22-0261909-00 BEFORE THIS JO WAS CREATED.
22026190800 | 557 | EX | INSTALL 50'-4" PMLP | 199 BROADWAY ST | B | 45570.6341 | 48441.53 | 2870.8959 | 6% | 55 | 43 | 1126.5472
22026190900 | 558 | EX | RETIRE 41'-4" BSLP | 199 BROADWAY ST | B | 78.4365 | 114.59 | 36.1535 | 46% |  |  | 0
22026191300 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | N MAPLE ST | F | 4801.1928 | 839.28 | -3961.9128 | -83% |  |  | 0 | CCC# 71072
22026191400 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | N MAPLE ST | F | 124.8731 | 0 | -124.8731 | 100% |  |  | 0
22026192500 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | MAIN ST | F | 4801.1928 | 400.52 | -4400.6728 | -92% |  |  | 0 | CCC# 71244
22026192600 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | MAIN ST | F | 124.8731 | 0 | -124.8731 | 100% |  |  | 0
22026194600 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | HWY 977 | F | 4801.1928 | 4024.88 | -776.3128 | -16% |  |  | 0 | CCC# 3219 INSTALLED MIWI INSTALLED NEW MIWI350 WSHINFESSEL 10-12-22
22026194700 | 910 | EX | RETIRED ELECTRONIC EXCHANGE | HWY 977 | F | 124.8731 | 0 | -124.8731 | 100% |  |  | 0 | RETIRED OLD ERX WSHINFESSEL 10-12-22
22026194800 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 555 ROLLING HILLS DR | F | 4801.1928 | 5891.93 | 1090.7372 | 23% |  |  | 0 | CCC# 78666 INSTALLED NEW MIWI350 JPASLEY 8-25-22
22026194900 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 555 ROLLING HILLS DR | F | 124.8731 | 0 | -124.8731 | 100% |  |  | 0 | RETIRED ERX INSTALLED NEW MIWI350 JPASLEY 8-25-22
22026195200 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | GAWTHROP DR | F | 4801.1928 | 6702.65 | 1901.4572 | 40% |  |  | 0 | CCC# 4229 CCC# 4229 INSTALLED NEW MIWI350 JPASLEY
22026195300 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | GAWTHROP DR | F | 124.8731 | 34.29 | -90.5831 | -73% |  |  | 0 | CCC# 4229 RETIRED OLD ERX INSTALLED NEW MIWI350 JPASLEY
22026196500 | 2000 | EX | INVESTIGATE R/W | MAIN ST | B | 2818 | 0 | -2818 | 100% |  |  | 0
22026196700 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | EWINGTON RD | F | 4801.1928 | 5374.37 | 573.1772 | 12% |  |  | 0 | CCC# 79339 INSTALLED NEW MIWI350. P2P W/GC OK 08/31/2022 WSHIMFE
22026196800 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | EWINGTON RD | F | 124.8731 | 0 | -124.8731 | 100% |  |  | 0 | RETIRED OLD ERX INSTALLED NEW MIWI350 WSHIMFESSEL 8-31-2022
22026196900 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | LINDEN AV | F | 4801.1928 | 5192.52 | 391.3272 | 8% |  |  | 0 | INSTALLED NEW MIWI350 JPASLEY 8-26-22
22026197000 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | LINDEN AV | F | 124.8731 | 698.72 | 573.8469 | 460% |  |  | 0 | RETIRED OLD ERX JPASLEY 8-26-22
22026198400 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | RICHMOND AV | F | 4801.1928 | 5538.33 | 737.1372 | 15% |  |  | 0 | ASSIST WITH RUNNING STAINLESS 09-21-2022 RHAYES CCOX RETIRED OLD ERX INSTALL NEW MIWI350 CCOX 9-21-22
22026198500 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | RICHMOND AV | F | 124.8731 | 450.09 | 325.2169 | 260% |  |  | 0
22026199700 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | COUNTY LN | F | 4801.1928 | 5650.33 | 849.1372 | 18% |  |  | 0 | RETIRED OLD ERX INSTALLED NEW MIWI350 EBLANTON 9-20-22
22026199800 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | COUNTY LN | F | 124.8731 | 592.76 | 467.8869 | 375% |  |  | 0 | RETIRED OLD RX INSTALLED NEW MIWI350 EBLANTON 9-20-22
22026203800 | 2000 | EX | AQUIRE EASEMENT | 409 E MAIN ST | A | 5556 | 0 | -5556 | 100% |  |  | 0
22026205800 | 560 | EX | RETIRE 20'-2" PMP | HOLT AV | B | 89.0305 | 0 | -89.0305 | 100% |  |  | 0
22026205900 | 584 | EX | RETIRE R-1682 | ROGERS AV | F | 1417.3638 | 603.96 | -813.4038 | -57% |  |  | 0
22026210800 | 2000 | EX | INVESTIGATE LAND RIGHTS | 2130 MCCLURE RD | B | 4228 | 0 | -4228 | 100% |  |  | 0
22026211500 | 557 | EX | EMER-INSTALL 5'-2" PMMP | 164 STRODE STATION CR | A | 16105.0112 | 5656.19 | -10448.8212 | -65% | 5 | 2 | 2828.095
22026211600 | 558 | EX | EMER-RETIRE 5'-2" PMMP | 164 STRODE STATION CR | A | 4031.2726 | 3884.45 | -146.8226 | -4% |  |  | 0
22026212100 | 577 | EX | INSTALL CHAIN LINK FENCE | EWINGTON RD | F | 24086.2589 | 9226.54 | -14859.7189 | -62% |  |  | 0 | INSTALLED CHAIN LINK FENCE JMULLINS 11-11-22
22026214300 | 910 | EX | STEPSTONE POD HVAC/RTU | STEPSTONE RD | F | 55.5311 | 0 | -55.5311 | 100% |  |  | 0 | UPGRADED RTU
22026217000 | 2000 | EX | INVESTIGATE RIGHT OF WAY | 302 JEREMIAH DR |  | 5000 | 0 | -5000 | 100% |  |  | 0
22026217500 | 557 | EX | EMER-INSTALL 2' OF 3"PMMP MAIN | 175 COLLEGE HILL RD | A | 5764.1191 | 6378.4 | 614.2809 | 11% | 2 | 2 | 3189.2
22026217600 | 558 | EX | EMER-RETIRE 2' OF 3"PAMP MAIN | 175 COLLEGE HILL RD | A | 1084.9152 | 4155.42 | 3070.5048 | 283% |  |  | 0
22026219700 | 557 | EX | EMER-INSTALL 8" STOPPLE FITS | PARIS BY PASS RD | B | 30183.131 | 39002.9 | 8819.769 | 29% |  |  | 0
22026219800 | 558 | EX | EMER-RETIRE 1' OF 8"CSHP MAIN | PARIS BY PASS RD | B | 84.9152 | 160 | 75.0848 | 88% |  |  | 0
22026221100 | 575 | EX | ACQUIRE EASEMENT | SCOTT AV | F | 5819 | 500.94 | -5318.06 | -91% |  |  | 0
22026221900 | 558 | EX | EMER - RETIRE 20'-3" PMP | 423 OREO | A | 3460.1765 | 6987.81 | 3527.6335 | 102% |  |  | 0
22026222200 | 2000 | EX | ACQUIRE EASEMENT FOR S/L | 3330 MILLERSBURG RU RD | B | 2536 | 0 | -2536 | 100% |  |  | 0
22026222300 | 557 | EX | EMER - INSTALL 7'-4" PMLP | PLEASANT | A | 4005.634 | 13873.55 | 9867.916 | 246% | 10 | 7 | 1981.9357
22026222400 | 558 | EX | EMER - RETIRE 7'-4" PLP | PLEASANT | A | 89.0305 | 0 | -89.0305 | 100% |  |  | 0
22026223000 | 2000 | EX | IVESTIGATE HP GAS CONFLICT | COLBY RD | B | 11921 | 0 | -11921 | 100% |  |  | 0
22026224600 | 575 | EX | ACQUIRE LAND RIGHTS | MOY FOO AL | F | 5705 | 4090.19 | -1614.81 | -28% |  |  | 0
22026227600 | 557 | EX | EMER - INSTALL 60'-4" PMLP | 504 S MAPLE ST | B | 30615.0582 | 21421.89 | -9193.1682 | -30% | 60 | 55 | 389.4889
22026227700 | 558 | EX | EMER - RETIRE 60'-4" BSLP | 504 S MAPLE ST | B | 74.3089 | 8123.84 | 8049.5311 | 10,833% |  |  | 0
22026228201 | 557 | EX | INSTALL 4,225'-2"/6" PMMP | MAPLE ST | B | 1875934.718 | 1935349.38 | 59414.662 | 3% | 6200 | 3901 | 496.1162
22026228300 | 558 | EX | RETIRE 6,106'- LP MAIN | N MAPLE ST | B | 952.0929 | 182.4 | -769.6929 | -81% |  |  | 0
22026228400 | 558 | EX | RETIRE 1133'- MP MAIN | N MAPLE ST | B | 952.0929 | 0 | -952.0929 | 100% |  |  | 0
22026228700 | 910 | EX | RETIRE ELECTRONIC | LEVEE RD | F | 74.3089 | 0 | -74.3089 | 100% |  |  | 0
22026230301 | 557 | EX | INSTALL 1,725'-2" PMMP | MARSHALL ST | B | 636475.4754 | 676511.46 | 40035.9846 | 6% | 1725 | 1842 | 367.2701
22026230400 | 558 | EX | RETIRE 5,578' - IP MAIN | MARSHALL ST | B | 475.239 | 1019.8 | 544.561 | 115% |  |  | 0
22026230500 | 558 | EX | RETIRE 1,368' - MP MAIN | RUCKER ST | B | 475.239 | 14.31 | -460.929 | -97% |  |  | 0
22026231000 | 557 | EX | EMER - INSTALL 1'-2" PMMP | VINE | A | 8585.1316 | 6865.44 | -1719.6916 | -20% | 1 | 2 | 3432.72
22026231100 | 558 | EX | EMER - RETIRE 1'-2" PMP | VINE | A | 60.3089 | 0 | -60.3089 | 100% |  |  | 0
22026232600 | 555 | EX | INSTALL 200'-2" PMMP | 325 GENEVA AV | B | 40586.0582 | 20049.03 | -20537.0282 | -51% | 205 | 166 | 120.7773
22026234100 | 577 | EX | NEW RTU/COMM BUILDING | EARLY DR | F | 136.2135 | 0 | -136.2135 | 100% |  |  | 0
22026234500 | 577 | EX | INSTALL NEW RTU/COMM BUILDING | LEVEE RD | F | 136.2135 | 0 | -136.2135 | 100% |  |  | 0 | JMULLINS COMPLETING PAPERWORK
22026234700 | 559 | EX | INSTALL 3" STOPPLE FITTING | 1107 W LEXINGTON AV | B | 13630.9028 | 7929.81 | -5701.0928 | -42% |  |  | 0
22026234800 | 560 | EX | RETIRE 75' OF 3"BSMP MAIN | 1107 W LEXINGTON AV | B | 119.2135 | 114.9 | -4.3135 | -4% |  |  | 0
22026234901 | 555 | EX | INSTALL 4,100'-2" PMMP | DUCLAIR DR LT38 | B | 188453.1623 | 217597.98 | 29144.8177 | 15% | 4110 | 2130 | 102.1587
22026236400 | 555 | EX | INSTALL 450'-4" PMMP | 755 COLLEGE HILL RD | B | 61251.1595 | 52709.69 | -8541.4695 | -14% | 355 | 477 | 110.5025
22026237301 | 557 | EX | INSTALL 11,150'-8"6"4"2" PMMP | MUTUAL AV | B | 2580803.0362 | 3177275.55 | 596472.5138 | 23% | 11145 | 11972 | 265.3922 | ADV JTOY FOL
22026237400 | 558 | EX | RETIRE LP MAIN | MUTUAL AV | B | 139.1159 | 886.14 | 747.0241 | 537% |  |  | 0
22026237500 | 558 | EX | RETIRE MP MAIN | MUTUAL AV | B | 139.1159 | 554.6 | 415.4841 | 299% |  |  | 0
22026237600 | 2000 | EX | INVESTIGATE LAND & R/W | MUTUAL AV | B | 12684 | 0 | -12684 | 100% |  |  | 0
22026237801 | 557 | EX | INSTALL 4,100'-2" PMMP | BROADWAY AV | B | 765451.6207 | 836183.38 | 70731.7593 | 9% | 4105 | 4299 | 194.5065
22026237900 | 558 | EX | RETIRE 5,265' IP MAIN | BROADWAY AV | B | 135.9942 | 217.02 | 81.0258 | 60% |  |  | 0
22026238000 | 2000 | EX | INVESTIGATE R/W | BROADWAY AV | B | 12684 | 0 | -12684 | 100% |  |  | 0
22026238100 | 584 | EX | RETIRE R-1230-A | 110 5TH ST | F | 1996.3422 | 2779.72 | 783.3778 | 39% |  |  | 0 | CCC#62228
22026240500 | 583 | EX | INSTALL VRG | 724 DUG HILL RD | F | 14784.1417 | 7577.2 | -7206.9417 | -49% |  |  | 0 | NOT ON SITE. GETTING MATERIAL FROM SHOP FOR JOB. CCC# 6417 CCC# 6417 CCC# 6417 CCC# 6417
22026240600 | 584 | EX | RETIRE VRG | 724 DUG HILL RD | F | 1478.5709 | 1416.09 | -62.4809 | -4% |  |  | 0
22026240700 | 577 | EX | INSTALL FENCE FOR NEW LAND | 724 DUG HILL RD | F | 26194.1417 | 63926.63 | 37732.4883 | 144% |  |  | 0 | CCC# 12436 TICKET# 12436 CCC# 16515 GATHER INFO FOR CAPITAL PAPERWORK
22026244400 | 909 | EX | INSTALL NEW SCADA EQUIPMENT | PEA RIDGE RD | F | 26337.6752 | 17382.14 | -8955.5352 | -34% |  |  | 0 | CCC# 22134 WELDED NEW TAP ON INLET FOR MIWI INSTALL, JMARTIN DMARTIN 3-27-23 CCC# 23352 INSTALL NEW MIWI 350, UNIT IS WAITING FOR A TICKET # TO BE ABLE TO PUT ONLINE. JMARTIN 4-4-23 CCC# 23905 STILL NEED TO DO P2P WITH GAS CONTROL, MODEM NOT COMMUNICATING JMARTIN 4-6-23 CCC# 24126 TRIED TO FIX COMM ISSUE WITH MODEM CCC# 23905 P2P W/GAS CONTROL OK, JMARTIN 4-10-23 CCC# 26515 COMP ANOTHER P2P WITH GAS CONTROL. JMARTIN 4-21-23 NOT ONSITE, FIXED ISO AND SUBMITTED NEW CAP FOR DRAWING.
22026244500 | 909 | EX | INSTALL NEW SCADA EQUIPMENT | RT 89 | F | 19488.6752 | 17938.12 | -1550.5552 | -8% |  |  | 0 | CCC# 22091 INSTALLED NEW INLET TAP FOR MIWI, JMARTIN DMARTIN 3-27-23 NOT ONSITE DELAY DUE TO RAIN NOT ONSITE ACP RESCHEDULED CCC# 24233 INSTALLED NEW MIWI 350 CCC# 26551 WORKED WITH GC TO GET SITE ONLINE. P2P COMP. JMARTIN 4-21-23 NOT ONSITE, UPDATED ISO AND SBMITTED REDLINED DRAWIN.
22026245300 | 557 | EX | EMER - INSTALL 5'-2" PMMP | 711 COMBS FERRY RD | A | 10393.9744 | 3807.72 | -6586.2544 | -63% | 13 | 3 | 1269.24
22026245400 | 558 | EX | EMER - RETIRE 5'-2" PMMP | 711 COMBS FERRY RD | A | 131.2422 | 0 | -131.2422 | 100% |  |  | 0
22026245700 | 585 | EX | INSTALL BUILDING R-1667 | STATE RT 89 | F | 300.4844 | 651.28 | 350.7956 | 117% |  |  | 0
22026245800 | 586 | EX | RETIRE MIS FACILITIES R-1639 | STATE RT 89 | F | 131.2422 | 0 | -131.2422 | 100% |  |  | 0
23026248000 | 2000 | EX | ACQUIRE LAND FOR GROUND BED | MAPLE RIDGE DR | B | 11697 | 0 | -11697 | 100% |  |  | 0
23026248100 | 595R | EX | INSTALL GROUND BED | US 60 | B | 149767.3441 | 158524.5 | 8757.1559 | 6% |  |  | 0 | MATCOR CORROSION INSTALLED 300' 8" DEEP WELL DURAMMO ANODE SYSTEM WITH 5000LBS OF COKE BREEZE AND 1300LBS OF PERMA PLUG COARSE / ACTIVE LENGTH OF ANODE BED 200' / MODEL MDM-F200-300-BK040K WITH 40A OUTPUT CAPACITY FOR 30 YEARS / #8HMWPE HALAR LEAD WIRES MAPLE RIDGE RECTIFIER FAC 605693 WAS RETIRED / RECTIFIER SERIAL# 133704 REINSTALLED AT 452 PREWITT PIKE GROUND BED / JMM GROUND BED FAC # 861695 / RMU FAC # 861697 / JMM
23026248700 | 559 | EX | INSTALL 2" SS | HIGHLAND LN | A | 18496.357 | 2373.93 | -16122.427 | -87% |  |  | 0
23026248800 | 560 | EX | RETIRE 50' - 2" CSMP | HIGHLAND AV | A | 138.8485 | 6678.36 | 6539.5115 | 4,710% |  |  | 0
23026250900 | 587 | EX | INSTALL EC 350 | 1330 ENTERPRISE DR | F | 2339.3221 | 755.31 | -1584.0121 | -68% |  |  | 0 | INSTALLED NEW EC 350 INSTALLED EC 350 J.BRADFORD 2-7-23
23026251000 | 588 | EX | RETIRE PAPER BILLING CHART | 1330 ENTERPRISE DR | F | 131.2422 | 803.89 | 672.6478 | 513% |  |  | 0 | BILLING CHART REMOVED AND EC 350 INSTALLED
23026251600 | 577 | EX | INSTALL RTU BUILDING | STATE RT 89 | F | 170.6969 | 2010.08 | 1839.3831 | 1,078% |  |  | 0 | CCC#28635 WORK DONE FOR WHAT THEY ARE DOING TODAY 5-5-23 JUSTIN HOBBS CCC# 31032 CREATED OTH FACID 861369 FOR HVAC. SM 12/1/23
23026252400 | 588 | EX | RETIRE GMB MS#804399 RUN | HWY 977 | F | 2962.0987 | 21780.96 | 18818.8613 | 635% |  |  | 0 | NOT ONSITE NOT ONSITE GATHERING PARTS CCC# 15748 TICKET# 15748 RETIRED GMB SETTING 2-6-23 BY J.BRADFORD
23026253100 | 559 | EX | PM- GREENSITE TRABU INSTALL | TRABU RD | B | 1236355 | 30780.16 | -1205574.84 | -98% |  | 50 | 615.6032
23026253200 | 560 | EX | PM- GREENSITE TRABU ABANDON | TRABU RD | B | 0 | 235.97 | 235.97 | 100% |  |  | 0
23026253700 | 559 | EX | PM-GREENSITE HWY 27 INSTALL |  | B | 1236355 | 20755.46 | -1215599.54 | -98% |  | 52 | 399.1435
23026253800 | 560 | EX | PM-GREENSITE HWY 27 ABANDON |  | B | 0 | 137.28 | 137.28 | 100% |  |  | 0
23026261100 | 909 | EX | INSTALL ULTRASONIC METER | 900 HICKORY RIDGE RD | F | 48123.5304 | 52334.12 | 4210.5896 | 9% |  |  | 0 | TICKET# 41313 CCC# 60438 TICKET# 60438 CCC# 60946 P2P W/ GC
23026263200 | 588 | EX | GMB TO CAB CONVERSION | 2001 OWINGSVILLE RD | F | 124.7348 | 758.88 | 634.1452 | 508% |  |  | 0 | GATHER PARTS INFO 27 - 300,000 BTU HANGING UNIT HEATERS = 8,100,000 3 - 300,000 BTU ROOF TOP UNITS = 900,000 TOTAL BTU LOAD - 9,000,000 GMB TO CAB CONVERSION
23026264000 | 583 | EX | INSTALL NEW METER | CLINTONVILLE RD | F | 31875.3689 | 29289.91 | -2585.4589 | -8% |  |  | 0 | CCC 71591 INSTALLED NEW METER CCC 71591
23026266800 | 557 | EX | EMER - INSTALL 7'-2" PMMP | 1152 VINE ST | A | 15964.0017 | 537.54 | -15426.4617 | -97% | 2 | 7 | 76.7914
23026266900 | 558 | EX | EMER - RETIRE 7'-2" PMAP | 1152 VINE | A | 64.7348 | 0 | -64.7348 | 100% |  |  | 0
23026267000 | 557 | EX | EMER - INSTALL 2'-2" PMLP | ELM ST | A | 7754.9733 | 1235.74 | -6519.2333 | -84% | 2 | 2 | 617.87
23026267100 | 558 | EX | EMER - RETIRE 2'-2" PLP | ELM ST | A | 64.7348 | 0 | -64.7348 | 100% |  |  | 0
23026267600 | 555 | EX | INSTALL 110'-4"PMLP | 103 WHIRLAWAY DR | B | 46300.0467 | 32525.16 | -13774.8867 | -30% | 150 | 100 | 325.2516
23026268700 | 559 | EX | PM-DE LINE PH 2 DENT 2/STPL 3 |  | B | 1307000 | 705427.76 | -601572.24 | -46% |  | 25 | 28217.1104
23026269400 | 560 | EX | PM-DE LINE ILI PH2 DENT2,STPL3 |  | C | 216349 | 198957.22 | -17391.78 | -8% |  |  | 0
23026271700 | 0001 | EX | MUTUAL AVE UPRATE | MUTUAL AV |  | 1706.4576 | 0 | -1706.4576 | 100% |  |  | 0
23026273200 | 558 | EX | EMER-RETIRE 741'-1" PMP | 2450 UNION CITY RD | A | 1738.6263 | 1327.21 | -411.4163 | -24% |  |  | 0
23026274800 | 586 | EX | RETIRE REG BUILDING | ALLEY OFF MAIN ST | F | 117.7346 | 0 | -117.7346 | 100% |  |  | 0
23026274900 | 557 | EX | EMER - INSTALL 4'-2" PMMP | LEVEE RD | A | 31722.4446 | 15519.62 | -16202.8246 | -51% | 14 | 4 | 3879.905
23026275000 | 558 | EX | EMER - RETIRE 4'-2" PMMP | LEVEE RD | A | 139.1159 | 2331.35 | 2192.2341 | 1,576% |  |  | 0
23026275100 | 562 | EX | RETIRE 276'-3" BSLP | S QUEEN ST | B | 12701.243 | 5918.41 | -6782.833 | -53% |  |  | 0
23026276600 | 910 | EX | RETIRE RTU FACILITY | STATE RT 89 | F | 139.1159 | 2357.33 | 2218.2141 | 1,595% |  |  | 0 | CCC#33813 PICKED UP TRASH CPRRECTED PAPER WORK JPASLEY 11-20-23
23026278500 | 557 | EX | EMER - INSTALL 3'-2" PMMP | 212 BYBEE LOOP | A | 4078.3783 | 3085.38 | -992.9983 | -24% | 3 | 3 | 1028.46
23026278600 | 558 | EX | EMER - RETIRE 3'-2" PMMP | 212 BYBEE LOOP | A | 139.1159 | 10.24 | -128.8759 | -93% |  |  | 0
23026279900 | 560 | EX | RETIRE 38'-3" PMP | COLLEGE HILL RD | B | 139.1159 | 0 | -139.1159 | 100% |  |  | 0
23026281100 | 2000 | EX | INVESTIGATE CONFLICT | CLEVELAND RD | B | 14748 | 0 | -14748 | 100% |  |  | 0 | CONFLICT INVESTIGATION COMPLETE. CONFLICTS RESOLVED WITH PROPOSED PROJECT D . LEMONS 6/27/2024
23026281600 | 557 | EX | EMER-INSTALL 3'-3" PMMP | 100 GRINDSTONE RD | A | 5640.4544 | 5032.43 | -608.0244 | -11% | 3 | 3 | 1677.4767
23026281700 | 558 | EX | EMER-RETIRE 3'-3" PMAP | 100 GRINDSTONE RD | B | 67.1159 | 1946 | 1878.8841 | 2,799% |  |  | 0
23026281900 | 903 | EX | INSTALL TWO STORAGE BUILDINGS | 281 SHOPPERS DR | F | 11634.7925 | 14600.26 | 2965.4675 | 25% |  |  | 0
23026282600 | 558 | EX | EMER - RETIRE 216'-2" PAMP | 413 MIMOSA LN | A | 2153.608 | 5057.99 | 2904.382 | 135% |  |  | 0
23026286000 | 557 | EX | EMER - INSTALL 6'-2" PMMP | 507 BROOKVIEW DRIVE | A | 14279.5419 | 5456.45 | -8823.0919 | -62% | 30 | 6 | 909.4083
23026286100 | 558 | EX | EMER - RETIRE 6'-2" PMMP | 507 BROOKVIEW DRIVE | A | 67.1159 | 5375.26 | 5308.1441 | 7,909% |  |  | 0
23026287800 | 559 | EX | INSTALL 500'-4" PMMP | PARIS PK | B | 99252.0533 | 175667.6 | 76415.5467 | 77% | 570 | 1079 | 162.8059
23026287900 | 560 | EX | RETIRE 500'-3" PMP | PARIS PK | B | 119.4953 | 0 | -119.4953 | 100% |  |  | 0
23026288500 | 557 | EX | EMER - INSTALL 3'-2" PMMP | LEVEE | A | 15193.894 | 33.23 | -15160.664 | -100% | 23 | 8 | 4.1537
23026288600 | 558 | EX | EMER - RETIRE 3'-2" PMP | LEVEE | A | 119.4953 | 4237.6 | 4118.1047 | 3,446% |  |  | 0
23026289200 | 2000 | EX | INVESTIGATE R/W | PARIS PK | B | 2818 | 0 | -2818 | 100% |  |  | 0
23026289900 | 557 | EX | EMER-INSTALL 8'-3" PMMP | 158 COLLEGE HILL RD | A | 1914.647 | 3026.88 | 1112.233 | 58% | 18 | 8 | 378.36
23026290000 | 558 | EX | EMER-RETIRE 8'-3" PAMP | 158 COLLEGE HILL RD | A | 7157.6376 | 9034.26 | 1876.6224 | 26% |  |  | 0
23026293900 | 557 | EX | EMER-INSTALL 3' OF 2"PMMP MAIN | 159 WESTSIDE DR | A | 14157.3554 | 7202.89 | -6954.4654 | -49% |  | 3 | 2400.9633
23026294000 | 558 | EX | EMER-RETIRE 3' OF 2"PMMP MAIN | 159 WESTSIDE DR | A | 119.4953 | 0 | -119.4953 | 100% |  |  | 0
23026295300 | 586 | EX | RETIRE FENCE | ROGERS AV | F | 119.4953 | 0 | -119.4953 | 100% |  |  | 0
23026297000 | 559 | EX | INSTALL PCF'S LP | HOLT AV | B | 145.9261 | 2982.68 | 2836.7539 | 1,944% |  |  | 0
23026297600 | 2000 | EX | INVESTIGATE LAND FOR STAKING | RIO VISTA DR | B | 6612 | 0 | -6612 | 100% |  |  | 0
23026297900 | 2000 | EX | INVESTIGATE LAND FOR STAKING | SUNSET SR | B | 6673 | 0 | -6673 | 100% |  |  | 0
23026298200 | 2000 | EX | INVESTIGATE AND ACQUIRE LAND | CAMELOT DR | B | 5778 | -1109 | -6887 | -119% |  |  | 0
23026298400 | 909 | EX | INSTALL MODEM AND ANTENNA | STATE RT 89 | F | 8303.7376 | 0 | -8303.7376 | 100% |  |  | 0 | CORRECTED PAPER WORK 11-20-23 JPASLEY
23026298600 | 2000 | EX | INVESTIGATE CONFLICT | FULTON RD | B | 6958 | -7971.72 | -14929.72 | -215% |  |  | 0
23026299300 | 2000 | EX | INVESTIGATE LAND FOR STAKING | HARRISON AV | B | 9260 | 0 | -9260 | 100% |  |  | 0
23026300401 | 561 | EX | INSTALL 1150' 4/2" PMMP | MARKET ST | B | 220213.1673 | 291755.2 | 71542.0327 | 32% | 1150 | 1139 | 256.1503 | TTOY 5/6/24: ATTEMPTED TO REVISE DUE TO UNDERRUN, MATERIAL PO NOT FILLED,
23026300500 | 562 | EX | RETIRE 3896' 4/3/2" PAMP | MARKET ST | B | 160.3697 | 0 | -160.3697 | 100% |  |  | 0
23026300600 | 561 | EX | INSTALL 180'-4" PMLP | KITTISON DR | B | 62129.0817 | 77710.69 | 15581.6083 | 25% | 180 | 207 | 375.414
23026300700 | 562 | EX | RETIRE 150'-4" PMLP | KITTISON DR | B | 124.9261 | 0 | -124.9261 | 100% |  |  | 0
23026301900 | 596 | EX | RETIRE RECTIFIER/GROUND BED | MAPLE RIDGE | F | 122.9261 | 83.75 | -39.1761 | -32% |  |  | 0 | RECTIFIER 605693 RETIRED / GROUND BED AND RECTIFIER RELOCATED TO 452 PREWITT PIKE WITH NEW RECTIFIER FAC 861691 & GROUND BED FAC 861695 / JMM
23026302000 | 575 | EX | ACQUIRE LAND FOR GROUND BED | PREWITT PK | F | 12042.9261 | 12672.53 | 629.6039 | 5% |  |  | 0
23026302300 | 584 | EX | RETIRE PAPER GAUGE | HWY 977 | F | 989.8688 | 835.24 | -154.6288 | -16% |  |  | 0 | NOT ONSITE WORK POSTPONED TILL TOMMOROW CCC# 49846
23026302800 | 557 | EX | EMER - INSTALL 2'-3" PMP | 17 WESTCHESTER LANE | A | 3855.2637 | 4049.34 | 194.0763 | 5% | 2 | 2 | 2024.67
23026302900 | 558 | EX | EMER - RETIRE 2'-3" PMP | 17 WESTCHESTER LANE | A | 122.9261 | 1224.64 | 1101.7139 | 896% |  |  | 0
23026303000 | 558 | EX | EMER - RETIRE 13'-3" BSLP | W HIGH ST | A | 23992.5325 | 19694.3 | -4298.2325 | -18% |  |  | 0
23026303200 | 583 | EX | R-1647 REBUILD INSTALL | 201 MILLER DR | F | 69868.5777 | 123864.29 | 53995.7123 | 77% |  |  | 0 | BYPASS HOSE PICK UP/OHIO NOT ONSITE NOT ONSITE BUILD AND TEST TEMP STATION CCC# 56331 CCC# 56478 INSTALLING TEMP STATION CCC# 56478 PUT TEMP STATION ONLINE. NOT ONSITE. DOING EXPENSE REPORT FOR PURCHASE FOR JOB. CCC# 56815 MONITOR FOR VAC TRUCK. JMARTIN 12/26/23 CCC# 57050 CCC# 57112 CCC# 57112 CCC# 57112 CCC# 57190
23026303300 | 584 | EX | R-1647 PARTIAL RETIRE | 201 MILLER DR | F | 124.9261 | 0 | -124.9261 | 100% |  |  | 0
23026303400 | 559 | EX | INSTALL 20'-2" CSHP | MILLER DR | B | 112306.0322 | 212847.86 | 100541.8278 | 90% | 140 | 30 | 7094.9287
23026305200 | 2000 | EX | INVESTIGATE & ACQUIRE EASEMENT | NEW LAIR RD | B | 3664 | 0 | -3664 | 100% |  |  | 0
23026305500 | 0001 | EX | SPECIAL ORDER MATERIAL HOLDING | 201 MILLER DR | B | 100000 | 0 | -100000 | 100% |  |  | 0
23026306000 | 557 | EX | EMER-INSTALL 2'-3" PMMP | 206 WACO LOOP RD | A | 6158.638 | 6338.35 | 179.712 | 3% | 2 | 2 | 3169.175
23026306100 | 558 | EX | EMER-RETIRE 2'-3" PMMP | 206 WACO LOOP RD | A | 124.9261 | 0 | -124.9261 | 100% |  |  | 0
23026306200 | 577 | EX | INSTALL BUILDINGS R-1667 | 724 DUG HILL RD | F | 147.9261 | 0 | -147.9261 | 100% |  |  | 0
23026307600 | 2000 | EX | EN PS&I FOR STATION DESIGN | 66 RED LICK RD | B | 7500 | 0 | -7500 | 100% |  |  | 0
24026309800 | 555 | EX | INSTALL 75' - 2" PMMP | 17 SYCAMORE ST | B | 15016.2249 | 21399.98 | 6383.7551 | 43% | 75 | 98 | 218.3671
24026309900 | 2000 | EX | OBTAIN HP EASEMENT | 3007 BASIN SPRINGS RD | B | 11339 | 0 | -11339 | 100% |  |  | 0
24026310600 | 559 | EX | INSTALL 2, 2" STOPPLE FITTINGS | 133 WOODMONT DR | B | 32187.8821 | 21866.79 | -10321.0921 | -32% |  |  | 0
24026310700 | 560 | EX | ABANDON ~ 150'- 2" CSIP | 133 WOODMONT DR | A | 118.4933 | 577.39 | 458.8967 | 387% |  |  | 0
24026310800 | 555 | EX | INSTALL 1400' OF 2" PMMP | 1929 FOGG PK | B | 90861.9332 | 67204.19 | -23657.7432 | -26% | 1400 | 1360 | 49.4148
24026312500 | 575 | EX | ACQUIRE EASEMENT FOR RELOCATE | MARKET ST | F | 892 | 515.95 | -376.05 | -42% |  |  | 0
24026313400 | 595R | EX | REPLACE EXISTING RECTIFIER | 389 CYNTHIANA RD | A | 4512.3856 | 3464.96 | -1047.4256 | -23% |  |  | 0 | RE-INSTALLED RECTIFIER SERIAL NUMBER 202283 / OLD FACILITY NUMBER 860865 AT 389 CYNTHIANA ROAD ON BRENTSVILLE RD TO REPLACE RETIRED FACILITY 457161 AT SAME LOCATION / NEW FACILITY FOR RECTIFIER SERIAL 202283 AT 389 CYNTHIANA ROAD IS 863011 / RECTIFIER INSTALLED ON EXISTING POLE AND RE-USED EXISTING STRUCTURE WIRE AND GROUND BED WIRE / RECTIFIER INSTALLED ON 01-22-24 & SET AT C1-F4 WITH 6.85V AND 1.41A / WILL RETIRE FACIITY 457161 WITH JOB ORDER 24-0263135-00 RECTIFER 202283 IS UNIVERSAL RECTIFIER WITH 30VDC & 15ADC MAX OUTPUT. 01-25-24 1055 JMM
24026313500 | 596 | EX | RETIRE EXISTING RECTIFIER | 389 CYNTHIANA RD | F | 160.3697 | 0 | -160.3697 | 100% |  |  | 0 | RECTIFIER 457161 RETIRED AND RT 109854 VOID WITH CAP JOB 24-0263135-00 NEW RECTIFIER 863011 WITH RT 1091194 INSTALLED ON CAP JOB 24-0263134-00 ALL TEST STATIONS HAVE BEEN MOVED TO NEW RECTIFIER ID / THIS WAS A NON DIG RECTIFIER ONLY CHANGE OUT / OLD RECTIFIER HAS BEEN REMOVED FROM SERVICE
24026313900 | 2000 | EX | INVESTIGATE ENCROACHMENT | 133 WOODMONT DR | A | 3000 | 0 | -3000 | 100% |  |  | 0
24026314400 | 555 | EX | INSTALL 1,200'-4" PMMP | 1414 ROBERT MARTIN | B | 166742.0112 | 441793.04 | 275051.0288 | 165% | 1200 | 1122 | 393.7549 | PAST COMMIT DATE DUE TO WEATHER AND ROUGH DIFFULCT OF JOB AND BORE
24026315200 | 587 | EX | INSTALL NEW EC 350 | 7001 MARTIN LUTHER BV | F | 5524.5572 | 8919.7 | 3395.1428 | 61% |  |  | 0 | INSTALLED NEW EC350
24026315300 | 588 | EX | RETIRE EC350 | 7001 MARTIN LUTHER BV | F | 160.3697 | 273.05 | 112.6803 | 70% |  |  | 0 | RETIRED MINI AT
24026316000 | 557 | EX | EMER - INSTALL 2'-3" PMLP | 145 PLUM ST | A | 9590.2924 | 6877.79 | -2712.5024 | -28% | 3 | 2 | 3438.895
24026316100 | 558 | EX | EMER - RETIRE 2'-3" PALP | 145 PLUM ST | A | 160.3697 | 0 | -160.3697 | 100% |  |  | 0
24026317000 | 2000 | EX | PM-2023 DE ILI VALIDATIONS |  | A | 44959 | 0 | -44959 | 100% |  |  | 0 | AWEBER 4/30/24 - CONFIRMED CHARGE TO FOR VALIDATION OF 2023 559 WORK
24026319000 | 909 | EX | ADD SOLAR BACKUP | US 27 | F | 15005.0106 | 6634.21 | -8370.8006 | -56% |  |  | 0
24026320400 | 909 | EX | INSTALL MIWI W/FLOW SWITCH | KIRKLAND AV | F | 21508.3856 | 17939.6 | -3568.7856 | -17% |  |  | 0 | CCC# 93710 CCC# 94300 INSTALLED NEW TAPS FOR MIWI
24026325000 | 909 | CO | MIWI WITH SOLAR | 620 BOONE AV | F | 19446.0487 | 17266.04 | -2180.0087 | -11% |  |  | 0 | CCC# 88776 INSTALL NEW TAPS FOR MIWI.
24026325100 | 910 | EX | MIWI WITH SOLAR | 620 BOONE AV | F | 121.4465 | 0 | -121.4465 | 100% |  |  | 0
24026325800 | 2000 | EX | INVESTIGATE AND ACQUIRE LAND | MILLER DR | B | 5663 | 0 | -5663 | 100% |  |  | 0
24026326000 | 909 | EX | UPGRADE SCADA SYSTEM | CARR AL | F | 10627.0487 | 9009.11 | -1617.9387 | -15% |  |  | 0 | CCC 92291 CCC 92291
24026326100 | 910 | EX | UPGRADE SCADA SYSTEM | CARR AL | F | 121.4465 | 494.05 | 372.6035 | 307% |  |  | 0 | CCC 92291
24026327000 | 909 | EX | INSTALL ELECTRONICS | S WALL AL | F | 15644.0403 | 8645.98 | -6998.0603 | -45% |  |  | 0 | CCC# 84533
24026327100 | 910 | EX | RETIRE ELECTRONICS | S WALL AL | F | 118.4933 | 0 | -118.4933 | 100% |  |  | 0
24026327200 | 909 | EX | INSTALL ELECTRIONICS | N WALL AL | F | 15644.0403 | 7576.45 | -8067.5903 | -52% |  |  | 0 | CCC# 84650
24026327300 | 910 | EX | RETIRE ELECTRONICS | N WALL AL | F | 118.4933 | 0 | -118.4933 | 100% |  |  | 0
24026327800 | 909 | EX | INSTALL ELECTRONICS | FOREST AV | F | 15644.0403 | 9991.66 | -5652.3803 | -36% |  |  | 0 | CCC# 84481
24026327900 | 910 | EX | RETIRE ELECTRONICS | FOREST AV | F | 118.4933 | 9.73 | -108.7633 | -92% |  |  | 0 | CCC# 84481
24026329300 | 2000 | EX | INVESTIGATE STATION PIPING | EARLY DR | B | 19419.0806 | 0 | -19419.0806 | 100% |  |  | 0 | CCC 80359 HYDRO EXCAVATE FOR MAOP RECONFIRMATION TWALKER/KY 09-26-24-M/R MEGA RULE ALL MATERIAL VERIFICATION WAS COMPLETED BY CAMPOS AND NOTHING TO REPLACE.
24026329400 | 557 | EX | EMER - INSTALL 2'-3" PMLP | ORAGE | A | 4221.248 | 6384.11 | 2162.862 | 51% | 2 | 2 | 3192.055
24026329500 | 558 | EX | EMER - RETIRE 2'-3" PALP | ORAGE | A | 121.4465 | 0 | -121.4465 | 100% |  |  | 0
24026329700 | 557 | EX | EMER - 2'-2" PMMP | SHALA-MAR RUE | A | 8686.5178 | 8583.87 | -102.6478 | -1% | 30 | 2 | 4291.935
24026329800 | 558 | EX | EMER - RETIRE 2'-2" PMP | SHALA-MAR RUE | A | 121.4465 | 0 | -121.4465 | 100% |  |  | 0
24026331400 | 584 | EX | RETIRE R-1279 | VINE ST | F | 973.0487 | 1587.88 | 614.8313 | 63% |  |  | 0 | CCC 63860 RETIRED STATION R-1279
24026332600 | 557 | EX | EMER INSTALL 10'-6" PMMP | 2ND ST | B | 29701.1651 | 32430.81 | 2729.6449 | 9% | 20 | 10 | 3243.081
24026332700 | 558 | EX | EMER - RETIRE 15'- PMMP | 2ND ST | B | 139.7787 | 0 | -139.7787 | 100% |  |  | 0
24026335100 | 557 | EX | EMER - INSTALL 4'-3" PMMP | WACO LOOP RD | A | 9960.0387 | 12497.25 | 2537.2113 | 25% | 18 | 4 | 3124.3125
24026335200 | 558 | EX | EMER - 4' - 3" PMMP | WACO LOOP RD | A | 121.4465 | 0 | -121.4465 | 100% |  |  | 0
24026335400 | 557 | EX | EMER - INSTALL 2'-2" PMMP | FIKE RD | A | 5032.0911 | 7568.56 | 2536.4689 | 50% | 3 | 2 | 3784.28
24026335500 | 558 | EX | EMER - RETIRE - 2'-2" PMMP | FIKE RD | A | 121.4465 | 0 | -121.4465 | 100% |  |  | 0
24026337300 | 2000 | EX | DESIGN CONFLICT RELOCATION | 539 BARLOW DR | B | 8275 | 0 | -8275 | 100% |  |  | 0
24026337600 | 561 | EX | INSTALL 30'-2" PMMP | 539 BARLOW DR | B | 27915.2109 | 27755.6 | -159.6109 | -1% | 55 | 27 | 1027.9852
24026337700 | 562 | EX | RETIRE 20'-2" PMMP | 539 BARLOW DR | B | 139.7787 | 19.74 | -120.0387 | -86% |  |  | 0
24026337900 | 555 | EX | INSTALL 2,550'-2" PMMP | 105 DUCLAIR DR LT38 | B | 91900.6833 | 82903.24 | -8997.4433 | -10% | 2550 | 3127 | 26.5121
24026340500 | 575 | EX | ACQUIRE EASEMENT | COMBS FERRY RD | F | 11900 | 45920.11 | 34020.11 | 286% |  |  | 0
24026342300 | 558 | EX | EMER - RETIRE 267'-2" PMP | 546 CONSTITUTION DR | A | 2962.6295 | 2861.12 | -101.5095 | -3% |  |  | 0
24026342800 | 2000 | EX | INVESTIGATE ROW FOR STAKING | ROWLAND AV | B | 8878 | 0 | -8878 | 100% |  |  | 0
24026343700 | 557 | EX | EMER - INSTALL 3'-3" PMMP | MEADOW | A | 6477.801 | 10177.86 | 3700.059 | 57% | 18 | 3 | 3392.62
24026343800 | 558 | EX | EMER - RETIRE 3'-3" PMP | MEADOW | A | 139.7787 | 0 | -139.7787 | 100% |  |  | 0
24026345000 | 587 | EX | INSTALL NEW EC 350 UNIT | 150 WHEAT DR PROACE | F | 2029.8027 | 548.93 | -1480.8727 | -73% |  |  | 0 | INSTALLED NEW EC350 S/N 232590014 0-300#PSIA
24026345100 | 588 | EX | RETIRE EC 350 UNIT | 150 WHEAT DR PROACE | F | 70.7787 | 123.53 | 52.7513 | 75% |  |  | 0 | RETIRED OLD EC350 INSTALLED NEW EC350
24026349100 | 2000 | EX | INVETIGATE LAND RIGHTS | HORSESHOE DR | B | 6673 | 0 | -6673 | 100% |  |  | 0
24026349200 | 575 | EX | ACQUIRE EASEMENT | 616 COLBY RD | F | 1252 | 1800.46 | 548.46 | 44% |  |  | 0
24026349900 | 557 | EX | EMER - INSTALL 3'-2" PMMP | STRODE STATION | A | 7024.6066 | 8029.62 | 1005.0134 | 14% | 3 | 3 | 2676.54
24026350000 | 558 | EX | EMER - RETIRE 3'-2" PMP | STRODE STATION | A | 139.7787 | 0 | -139.7787 | 100% |  |  | 0
24026350900 | 558 | EX | RETIRE 38'-2" CSMP | VINE ST | B | 139.7787 | 0 | -139.7787 | 100% |  |  | 0
24026352000 | 555 | EX | INSTALL 700'-2" PMMP | 550 BULLION BV | B | 78413.3497 | 75786.62 | -2626.7297 | -3% | 700 | 716 | 105.8472
24026353200 | 557 | EX | EMER - INSTALL 3'-4" PMMP | GARDEN SPRINGS | A | 7993.6359 | 3109.71 | -4883.9259 | -61% | 3 | 3 | 1036.57
24026353300 | 558 | EX | EMER - RETIRE 3'-4" PAMP | GARDEN SPRINGS | A | 139.7787 | 0 | -139.7787 | 100% |  |  | 0
24026354100 | 560 | EX | EMER - RETIRE 308'-2" PLP | BARNES TRAILER PARK | A | 2331.6111 | 3269.44 | 937.8289 | 40% |  |  | 0
24026358600 | 561 | EX | INSTALL 175' - 4" PMMP | S CHURCH AL | B | 72423.4515 | 90409.34 | 17985.8885 | 25% | 175 | 195 | 463.6376
24026359000 | 583 | EX | EMER - INSTALL NEW REGULATOR | 3RD ST ALLEY | F | 163089.7838 | 32098.29 | -130991.4938 | -80% |  |  | 0
24026359100 | 584 | EX | EMER - RETIRE REGULATOR | 3RD ST ALLEY | F | 124.2298 | 3027.28 | 2903.0502 | 2,337% |  |  | 0
24026361500 | 557 | EX | EMER - INSTALL 2'-3" PMLP | MARKET | A | 3524.9349 | 4884.17 | 1359.2351 | 39% | 2 | 2 | 2442.085
24026361600 | 558 | EX | EMER - RETIRE 2'-3" PALP | MARKET | A | 127.2637 | 0 | -127.2637 | 100% |  |  | 0
24026362300 | 559 | EX | INSTALL 2" SS | MILLER DR | B | 159.2637 | 0 | -159.2637 | 100% |  |  | 0
24026362500 | 2000 | EX | INVESTIGATE LAND | CHURCH AL | B | 3566 | 0 | -3566 | 100% |  |  | 0
24026364900 | 555 | EX | INSTALL 2,300'-4" PMMP | LINZI WY LT45 | B | 164697.53 | 215200.02 | 50502.49 | 31% | 2300 | 2375 | 90.6105
24026365500 | 2000 | EX | INVESTIGATE LAND RIGHTS | 660 BOONE AV | B | 5112 | 0 | -5112 | 100% |  |  | 0
24026365600 | 595I | EX | INSTALL SSD UNIT W/ZINC RIBBON | 620 BOONE AV | B | 55300.1794 | 95863.74 | 40563.5606 | 73% |  |  | 0 | INSTALLED DUAL RUNS OF 420' ZINC ON THE NORTH & SOUTH SIDE OF 12"CSHP MAIN 5' OFF FROM MAIN & BELOW THE PIPE / INSTALLED DAIRYLAND SOLID-STATE DECOUPLER (SSD-2/2-5.0-100R) SERIAL #64954 WITH ENCLOSURE / ZINC MAT INSTALLED WITH #6 WHITE WIRE AND GREEN TAPE / TS FAC 885476 INSTALLED ON THE EAST END OF PROJECT & TS FAC 885477 INSTALLED ON THE WEST END OF PROJECT WITH #6 WHITE WIRE RUN UP FROM ZINC
24026365900 | 2000 | EX | INVESTIGATE LAND RIGHTS | LINZI WY LT45 | B | 5112 | 0 | -5112 | 100% |  |  | 0
24026366000 | 2000 | EX | INVESTIGATE LAND RIGHTS | 1305 IRVINE RD LT1 | B | 2556 | 0 | -2556 | 100% |  |  | 0
24026366100 | 2000 | EX | INVESTIGATE ROW FOR STAKING | 609 BULLION BV | B | 2556 | 0 | -2556 | 100% |  |  | 0
24026368000 | 557 | EX | EMER - INSTALL 5'-2" PMMP | 6845 LEVEE RD | A | 12185.6111 | 4545.67 | -7639.9411 | -63% | 5 | 6 | 757.6117
24026368100 | 558 | EX | EMER - RETIRE 5'-2" PMMP | 6845 LEVEE RD | A | 137.4585 | 295.06 | 157.6015 | 115% |  |  | 0 | WORKED ORDER
24026370500 | 575 | EX | ACQUIRE LAND RIGHTS | 231 MILLER DR | F | 25047 | 20657.58 | -4389.42 | -18% |  |  | 0 | LAND RIGHT AGREEMENTS 601984, 601985 AND 601986 ARE TEMPO EASEMENTS THAT CEASED TO EXIST ONCE INSTALL WAS COMPLETED.
24026371800 | 557 | EX | EMER - INSTALL 3'-2" PMMP | ARLINGTON | A | 14865.4926 | 19259.53 | 4394.0374 | 30% | 3 | 3 | 6419.8433
24026371900 | 558 | EX | EMER - RETIRE 3'-2" PMP | ALVERSON | A | 111.0024 | 0 | -111.0024 | 100% |  |  | 0
24026373200 | 909 | EX | INSTALL SOLAR BACKUP UNIT | CLINTONVILLE RD | F | 9877.4639 | 7104.24 | -2773.2239 | -28% |  |  | 0 | CCC# 108028
24026373700 | 909 | EX | INSTALL SOLAR BACKUP UNIT | EARLY DR | F | 9877.4639 | 8114.69 | -1762.7739 | -18% |  |  | 0 | CCC 107505 CCC#107505 WORK IS COMPLETE ON 2-18-2025 1550 J HOBBS
24026373800 | 557 | EX | EMER - INSTALL 3'-2" PMMP | VINE | A | 4350.0713 | 6014.6 | 1664.5287 | 38% | 3 | 3 | 2004.8667
24026373900 | 558 | EX | EMER - RETIRE 3'-2" PAMP | VINE | A | 111.0024 | 0 | -111.0024 | 100% |  |  | 0
24026376300 | 557 | EX | EMER - INSTALL 5'-2" PMIP | CONSTITUTION | A | 6864.5633 | 6514.7 | -349.8633 | -5% | 5 | 5 | 1302.94
24026376400 | 558 | EX | EMER - RETIRE 5'-2" PAIP | CONSTITUTION | A | 111.0024 | 0 | -111.0024 | 100% |  |  | 0
25026377800 | 2000 | EX | INVESTIGATE LAND RIGHTS | 1200 DOGWOOD DR | B | 3627 | 0 | -3627 | 100% |  |  | 0
25026377900 | 559 | EX | INSTALL LP FITTING-PAPER ONLY | MAIN ST | B | 139.0024 | 0 | -139.0024 | 100% |  |  | 0
25026378800 | 557 | EX | EMER - INSTALL 25'-2" PMMP | 6 WINCHESTER PZ E | A | 46887.3793 | 81247.31 | 34359.9307 | 73% | 35 | 25 | 3249.8924
25026378900 | 558 | EX | EMER - RETIRE 25'-3" PAMP | 6 WINCHESTER PZ E | A | 111.0024 | 0 | -111.0024 | 100% |  |  | 0
25026379000 | 557 | EX | EMER - INSTALL 9'-2" PMMP | 213 LAMOND RUELLE | A | 11723.1799 | 1184.26 | -10538.9199 | -90% | 19 | 9 | 131.5844
25026379101 | 558 | EX | EMER - RETIRE 9'-2" PMP | 213 LAMOND RUELLE | A | 6663.1804 | 9245.89 | 2582.7096 | 39% |  |  | 0
25026379500 | 909 | CO | INSTALL SCADA VISIBILITY | FOGG PK | F | 16667 | 13338.87 | -3328.13 | -20% |  |  | 0 | NOT ONSITE ORDER NOT NEEDED CCC# 119324 NOT ONSITE WENT ENROUTE TO THE WRONG JOB CCC# 121903 INSTALL POLES, BATTERY BOX, AND ER350.
25026379700 | 909 | CO | INSTALL SCADA VISIBILITY | FORDS MILL RD | F | 16667 | 11378.96 | -5288.04 | -32% |  |  | 0 | CCC 109193 INSTALLED 1'' TEE AND 1/4'' BALL VALVE FOR FUTURE SCADA VISIBILITY CCC 123850 CCC#123850
25026381800 | 555 | EX | INSTALL 250'-2" PMMP | 1200 DOGWOOD DR | B | 32185.6133 | 52355.75 | 20170.1367 | 63% | 250 | 233 | 224.7028
25026385300 | 2000 | EX | INVESTIGATE ROAD ROW | 265 STUMP RD | B | 2265 | 0 | -2265 | 100% |  |  | 0
25026393800 | 555 | EX | INSTALL 2,100'-2" PMMP | HAWK LN LT1 | B | 177755.4678 | 110997.26 | -66758.2078 | -38% | 2105 | 2037 | 54.4906
25026395400 | 2000 | EX | INVESTIGATE ROW | E MAIN ST | B | 5655 | 0 | -5655 | 100% |  |  | 0
25026397200 | 2000 | EX | INVESTIGATE ROW CONCERNS | 1340 US HWY 27 | B | 5021 | 0 | -5021 | 100% |  |  | 0
25026400200 | 559 | EX | INSTALL 550'-2" PMMP | 1282 US HIGHWAY 27 S | B | 57765.7205 | 47508 | -10257.7205 | -18% | 550 | 523 | 90.8375
25026400700 | 562 | EX | RETIRE 100'-4" PMMP | 740 ECTON RD | B | 5393.6654 | 2247.29 | -3146.3754 | -58% |  |  | 0 | ABANDONED 135' OF 4" PLASTIC TO ALLOW FOR DRIVEWAY ENTRANCE, STUB LEFT FOR FUTURE SERVICE TO PROPERTY- PAPERWORK CO OFF SITE
25026403000 | 557 | CO | EMER - INSTALL 2'-3" PMMP | 191 WACO LOOP | A | 13653.342 | 230.88 | -13422.462 | -98% | 18 |  | 0
25026403100 | 558 | CO | EMER - RETIRE 2'-3" PAMP | 191 WACO LOOP | A | 138.8251 | 15086.34 | 14947.5149 | 10,767% |  |  | 0 | ABANDONED SECTION OF LEAKING CRACKED PLASTIC PIPE AND REPLACED WITH NEW PIP E
16026666400 | 587 | EX | INSTALL NEW CWT HEATER | 15035 E OLD US 23 | F | 231341.3745 | 188315.11 | -43026.2645 | -19% |  |  | 0 | CC# 53363. DRAINED WATERBATH HEATER. 01-26-22 DSASH CCC 55246 CCC 55359 CCC 55691 CCC 56098 CCC 57419 NO TICKET NEEDED NO TICKET NEEDED NO TICKET NEEDED CC# 70901. 6/20/22 DSASH RETIRED OLD WATER BATH INSTALLED NEW CWT HEATER DASH 3-3-22
16026666500 | 588 | EX | RETIRE EXIST WB HEATER | 15035 E OLD US 23 | F | 140.0254 | 29153.65 | 29013.6246 | 20,720% |  |  | 0 | CCC # 53363 CCC 53705 CCC 54571 CCC # 54571 NO TICKET NEEDED CCC # 57419 NOT ON SITE NO CCC NEEDED NO CCC NOT ON SITE CHARGED TO LE TO GET VRG FOR REG REPLACE INSTALLED NEW CWT HEATER 3-3-22 DASH
17026698500 | 909 | EX | INSTALL VRG PRESS CONT EQUIPMT | PIQUA ST | F | 128512.8191 | 247791.39 | 119278.5709 | 93% |  |  | 0 | CC# 27659. 6/11/21 DSASH CCC #27659 CC# 27769. 6/14/21 DSASH CC# 27972. 6/16/21 DSASH CC# 28248. 6/17/21 DSASH CCC #28248 CCC #28445 CC# 28445. 6/18/21 DSASH CC# 28787. 6/23/21 DSASH CCC #28787 NOT AT STATION OFF SITE WORKING ON PAPERWORK FOR JOB 7/1/2021 GCCC TICKET NOT REQUIRED NOT AT STATION OFF SITE COMPLETING PAPERWORK 7/19/21 AND 8/17/21 CFARIS
17026698600 | 910 | EX | RETIRE EXIST PRESS CONT EQUIPM | PIQUA ST | F | 131.3267 | 299.36 | 168.0333 | 128% |  |  | 0
17026699800 | 577 | EX | INSTALL ELEVATED BUS STOP ASSM | PIQUA ST | F | 61743.3758 | 9561.04 | -52182.3358 | -85% |  |  | 0 | UNDERRUN EXPLANATION: THIS JOB ORDER WAS WORKED IN ONJUNCTION WITH ANOTHER JOB ORDER, 17-0269850-00, WHICH OVERRAN DUE TO THE CONTRACT LABOR BEING CHA RGED TO THAT JOB ORDER INSTEAD. THAT AMOUNT WAS APPROXIMATELY $40,000.
17026699900 | 585 | EX | INSTALL NEW CH LINK FENCING | PIQUA ST | F | 20572.3069 | 0 | -20572.3069 | 100% |  |  | 0
17026735700 | 558 | EX | RETIRE 3510' MAIN - D243673 | 322 BELLEFONTE PRINCESS DR | B | 78.7024 | 8338.24 | 8259.5376 | 10,495% |  |  | 0
18026752700 | 583 | EX | INSTALL VRG PILOT | PIQUA ST | F | 5404.3267 | 5363.35 | -40.9767 | -1% |  |  | 0 | CCC #27769 CCC #28734
18026752800 | 584 | EX | RETIRE | PIQUA ST | F | 52.1634 | 838.05 | 785.8866 | 1,507% |  |  | 0
18026762800 | 585 | EX | INSTALL NEW CHAIN LINK FENCE | US ROUTE 60 | F | 17042.1322 | 16843.44 | -198.6922 | -1% |  |  | 0 | MONITORED NEW CHAINLINK FENCE INSTALL AMCCORMICK 8-18-22
18026762900 | 586 | EX | REPLACE CHAIN LINK FENCE | US ROUTE 60 | F | 73.5943 | 429.99 | 356.3957 | 484% |  |  | 0 | MONITORED FENCE REMOVAL AND INSTALL AMCCORMICK 8-18-22
18026764800 | 909 | EX | INSTALL COMM BUILDING | 8TH STREET | F | 156664.9991 | 132078.26 | -24586.7391 | -16% |  |  | 0 | 72003 INSTALLED RTU BUILDING AND TRANSDUCERS
18026772300 | 588 | EX | CONVERT FROM GMB TO CAB ACCT | 900 VERNON ST | F | 2583.054 | 725.53 | -1857.524 | -72% |  |  | 0 | CONVERTED GMB TO CAB ACCOUNT INSTALLED NEW 800 METER ON 5# FPCC DASH 9-26-2 2
18026778900 | 909 | EX | INSTALL ERX & RTU BUILDING | 202 CAROLINE AV | F | 156098.7133 | 113154.12 | -42944.5933 | -28% |  |  | 0 | CC# 13231. 2/25/21 DSASH WORKED ON PAPERWORK OFF SITE. 2/26/21 DSASH EQUIPMENT INSTALLED ON 2/25/21 BY ACP AND DANNY ASH PAPERWORK COMPLETED ON 12/16/2021 BY CYNTHIA FARIS JOB CLOSEOUT DELAYED WAITING ON INFORMATION AND CORRECT ISO SKETCH UNDERRUN EXPLANATION: THE CONTRACT COSTS WERE SIGNIFICANT LESS THAT THE I&C TEAM HAD ORIGINALLY ESTIMATED.
18026781701 | 587 | EX | INSTALL MONITOR/CONTROL REGS | US 23 | F | 99301.7623 | 141447.12 | 42145.3577 | 42% |  |  | 0 | CCC TICKET 27187 CCC #27342 CCC #27472 CCC #27636 CCC #27973 CCC TICKET NOT REQUIRED NOT AT STATION 8/4/21
18026781800 | 588 | EX | ABANDON REGULATORS | US 23 | F | 56.3894 | 0 | -56.3894 | 100% |  |  | 0
18026784200 | 2000 | EX | RESEARCH R/W & UTILITES | 13TH ST |  | 2736 | 0 | -2736 | 100% |  |  | 0 | EXECUTED AND STARTED NEW CHARGES TO 22-0261743-00. D.LEMONS 4/24/2024
18026784300 | 2000 | EX | RESEARCH LAND RIGHTS/UTILITES | WASHINGTON ST | B | 2736 | 0 | -2736 | 100% |  |  | 0
18026793901 | 557 | EX | INSTALL 4,123' - 2" PMMP | TEAKWOOD DR | B | 506341.5777 | 649583.26 | 143241.6823 | 28% | 4123 | 4140 | 156.9042
18026794000 | 558 | EX | RETIRE 4748'-2"/3"/4"/6"P-BSLP | TEAKWOOD DR | B | 61.2976 | 110 | 48.7024 | 79% |  |  | 0
18026794401 | 557 | CO | INSTALL 4400'-2"/4"PMMP MAIN | SULLIVAN ST | B | 1022806.1278 | 1250897.35 | 228091.2222 | 22% | 4233 | 2324 | 538.2519
18026794500 | 558 | CO | RETIRE 2450' - CS/BSMP | SULLIVAN ST | B | 118.4933 | 589.7 | 471.2067 | 398% |  |  | 0
18026844900 | 2000 | EX | INVESTIGATE MAIN DEPTH | HWY 3 | A | 3663.1174 | 0 | -3663.1174 | 100% |  |  | 0
19026855301 | 909 | EX | INSTALL RTU AND BUILDING | OLD US 23 | F | 182784.6097 | 186001.86 | 3217.2503 | 2% |  |  | 0 | INSTALLED NEW RTU DASH 3-17-22
19026855400 | 910 | EX | RETIRE OLD RTU EQUIPMENT | OLD US 23 | F | 69.4128 | 5219.78 | 5150.3672 | 7,420% |  |  | 0 | INSTALLED NEW COMM BUILDING AND RTU DASH 3-17-22
19026858700 | 2000 | EX | INVESTIGATE LAND RIGHTS | SARAH DR | A | 14282 | 0 | -14282 | 100% |  |  | 0
19026860400 | 909 | EX | INSTALLING I&C EQUIPMENT | US 23 | F | 222748.2628 | 174669.84 | -48078.4228 | -22% |  |  | 0 | CCC #27973 CCC #28142 CCC # 28275 CCC #28378 CCC #28665 CCC TICKET NOT REQUIRED NOT AT STATION 8/4/21
19026860500 | 910 | EX | RETIRE I&C EQUIPMENT | US 23 | F | 84.9756 | 511.34 | 426.3644 | 502% |  |  | 0 | CC# 78206
19026867100 | 583 | EX | INSTALL VRG CONTROLLER | OLD US 23 | F | 15490.7518 | 15917.94 | 427.1882 | 3% |  |  | 0 | CCC 59916 CCC # 59916 INSTALLED NEW VRG CONTROLLERS DASH 3-29-22
19026867200 | 584 | EX | RETIRE CURRENT CONTROLLERS | OLD US 23 | F | 64.4897 | 1038.8 | 974.3103 | 1,511% |  |  | 0 | CCC # INSTALLED NEW VRG'S RETIRED EXSISTING CONTROLLERS DASH 3-29-22
19026889700 | 583 | EX | INSTALL METER AND SETTING | LAUREL ST | F | 55012.1889 | 54709.93 | -302.2589 | -1% |  |  | 0 | CCC #30162 CCC # 42745 CCC # 42908 CCC # 43108 CLENANER INSTALLED ON 10-29-2022 ALONG WITH PAPERWORK CO BY JOSH MULLINS ON 5-10-22
19026889800 | 584 | EX | RETIRE METER AND SETTING | LAUREL ST | F | 76.3408 | 612.86 | 536.5192 | 703% |  |  | 0
19026910800 | 595R | EX | INSTALL NEW RECITIFER | 37TH (WINCHESTER AVE) ST | A | 10181.0696 | 8639.7 | -1541.3696 | -15% |  |  | 0 | RECTIFIER WAS INSTALLED BY SPELLECY ON 12/21/2020. UTILITY COMPANY VERIFIE D ELECTRICAL PERMIT AND ENERGIZED SERVICE IN JANUARY OF 2021. SERVICE WAS INSTALLED BY ACP LAST WEEK OF DECEMBER 2021. FIRST 2511 RT TO BE PERFOMED IN MARCH 2021. BULLHORN RMU MODEL 4014 S/N 138053 WAS INSTALLED -OSS
19026910900 | 596 | EX | RETIRE RECTIFIER | THIRTY SEVENTH ST | F | 69.2529 | 572.64 | 503.3871 | 727% |  |  | 0
19026911000 | 595R | EX | INSTALL NEW RECTIFIER | SLASH BRANCH RD | A | 10181.0696 | 14874.57 | 4693.5004 | 46% |  |  | 0
19026911100 | 596 | EX | RETIRE RECTIFIER | SLASH BRANCH RD | F | 69.2529 | 0 | -69.2529 | 100% |  |  | 0
19026913000 | 557 | EX | INSTALL 730'-2"PMMP | PANOLA | B | 230850.9729 | 242981.39 | 12130.4171 | 5% | 730 | 689 | 352.658
19026913100 | 558 | EX | RETIRE 705'-2/3/4" BS/PL/CSLP | PANOLA ST | B | 239.7645 | 354.92 | 115.1555 | 48% |  |  | 0
20026918001 | 909 | EX | INSTALL ELECTRONICS | SKYLINE DR | F | 78849.9064 | 203885.41 | 125035.5036 | 159% |  |  | 0 | CC# 31091 CC# 34924 CC# 21685. 01-03-22 DSASH CC# 21685. 01-03-22 DSASH OVERRUN EXPLANATION: ASSUMED WE WOULD USE THE OLD BLOCK BUILDING BUT FOND T HAT IT WAS LEAKING SO HAD TO REPLACE WITH A NEW BUILDING.
20026918102 | 909 | EX | INSTALL ELECTRONICS | US23--ASHLAND OIL | F | 264607.6595 | 173384.28 | -91223.3795 | -34% |  |  | 0 | NO CC NEEDED ONSITE MEETING DID NOT GO INSIDE BUILDING GES: UNDERRUN EXPLANATION: JOB UNDERRAN BECAUSE SCADA BUILDING WAS PLACED O N ANOTHER JOB ORDER THAT IS PLANNED FOR 2022 CONSTRUCTION. ADDITIONALLY, ASSUMED THERE WAS PRESSURE CONTROL WHEN ESTIMATED AND THERE W AS NOT.
20026918900 | 2000 | EX | SKYLINE REG PREMISE PROPERTY | SKYLINE DR |  | 4236 | 0 | -4236 | 100% |  |  | 0
20026919000 | 2000 | EX | ASHLAND OIL REG LAND RIGHTS | US 23 |  | 4236 | 0 | -4236 | 100% |  |  | 0
20026919100 | 2000 | EX | GREENUP CPG REG ST LAND RIGHTS |  |  | 4236 | 0 | -4236 | 100% |  |  | 0
20026922500 | 909 | EX | INSTALL ELECTRONICS | US 60 | F | 123804 | 238947.63 | 115143.63 | 93% |  |  | 0 | CCC # 40652 NOT ON SITE CC# 47218. 12/01/21 DSASH CCC # 47218 CCC # 47356 CC# 47727. 12/07/21 DSASH
20026922600 | 910 | EX | RETIRE ELECTRONICS | US 60 | F | 115.4611 | 144.18 | 28.7189 | 25% |  |  | 0
20026930800 | 587 | EX | UPGRADE ELECTRONICS | CENTER ST | F | 3038 | 4644.07 | 1606.07 | 53% |  |  | 0 | REPLACED EFC NON SCADA MONITORED GMB ACCOUNT GCCC TICKET NOT REQUIRED
20026930900 | 587 | EX | UPGRADE ELECTRONICS | 2236 MONTGOMERY AV | F | 3038 | 3329.3 | 291.3 | 10% |  |  | 0 | RETIRED MINI AT INSTALLED NEW EC350 ON CELL MODEM DASH 9-19-22
20026936301 | 561 | EX | INSTALL 1192'-4" PMMP | DIXON ST | B | 375696.2322 | 290217.29 | -85478.9422 | -23% | 1226 | 1177 | 246.5737 | UNDERRUN EXPLANATION: SIGNIFICANTLY LESS HARD SURFACE REPAIRS AND BACKFILL REQUIRED THAN ESTIMATED. ALSO NOFLAGGING ON OVERTIME WAS REQUIRED. THE OVER HEAD EFFECT OF THESE REDUCTIONS ALSO CONTRIBUTED TO THE UNDERRUN.
20026936400 | 562 | EX | RETIRE 1228'-3"&4"BS/CS/P-LP | DIXON ST | B | 400.0304 | 1214.98 | 814.9496 | 204% |  |  | 0
20026936600 | 562 | EX | ABANDON ~10'-4" P-LP | DIXON ST | B | 173.6495 | 167.31 | -6.3395 | -4% |  |  | 0
20026941600 | 909 | EX | INSTALL I&C EQUIPMENT | 100 BOY SCOUT RD | F | 16155.4774 | 11237.56 | -4917.9174 | -30% |  |  | 0 | CC# 30132. ERX INSTALLED BY DANNY ASH AND JOSH MULLINS PAPERWORK COMPLETED BY CYNTHIA FARIS PAPERWORK ON HOLD AWAITING CORRECT ISO SKETCH
20026941700 | 584 | EX | RETIRE GAUGE | 100 BOY SCOUT RD | F | 91.4991 | 0 | -91.4991 | 100% |  |  | 0 | ERX INSTALLED AND PAPER RECORDING GAUGE RETIRED BY DANNY ASH AND JOSH MULLINS PAPERWORK COMPLETED BY CYNTHIA FARIS PAPERWORK ON HOLD AWAITING CORRECT ISO SKETCH
20026941800 | 909 | EX | INSTALL I&C EQUIPMENT | 2137 CANNON DR RR | F | 16155.4774 | 12411.86 | -3743.6174 | -23% |  |  | 0 | GCC 13064 EQUIPMENT INSTALLED BY JOSH MULLINS ON 2/24/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/16/21 DELAY IN JOB COMPLETION WAITING ON PE APPROVAL FOR 584 JOB ORDER AND ISO SKETCH UPDATE GCCC TICKET NOT REQUIRED ON 7/16/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026941900 | 584 | EX | RETIRE GAUGE | 2137 CANNON DR RR | F | 91.4991 | 0 | -91.4991 | 100% |  |  | 0 | GAUGE RETIRE BY JOSH MULLINS ON 2/24/21 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/16/21 DELAY COMPLETING JOB ORDER DUE TO ISO SKETCH REVISION& PE APPROVAL GCCC TICKET NOT REQUIRED ON 7/16/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026942100 | 909 | EX | INSTALL I&C EQUIPMENT | 324 KINGS RD | F | 16155.4774 | 16401.86 | 246.3826 | 2% |  |  | 0 | CCC #29962 CCC #30339 INSTALLED ERX, RV50 MODEM, BATTERY AND SUPER SOLAR KIT GCCC TICKET NOT REQUIRED ON 7/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026942200 | 584 | EX | RETIRE GAUGE | 324 KINGS RD | F | 91.4991 | 0 | -91.4991 | 100% |  |  | 0 | RETIRED PAPER RECORDING GAUGE AND INSTALLED ERX WORK COMPLETED ON 909 JOB ORDER WITH GCCC TICKET NUMBER 29962 GCCC TICKET NOT REQUIRED ON 7/12/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
20026942300 | 909 | EX | INSTALL I&C EQUIPMENT | PAUL COFFEY BV | F | 16155.4774 | 11644.22 | -4511.2574 | -28% |  |  | 0 | INSTALLED ERX DELAY IN SENDING JOB TO CLOSE OUT WAITING ON INFORMATION PE REVIEW/APPROVAL AND ISO SKETCH CFARIS
20026942400 | 584 | EX | RETIRE GAUGE | PAUL COFFEY BV | F | 91.4991 | 1032.4 | 940.9009 | 1,028% |  |  | 0 | REPLACED MECHANICAL RECORDING GAUGE WITH ERX DELAY IN SENDING TO CLOSEOUT DUE TO WAITING ON INFORMATION, PE REVIEW/APPROVAL AND CORRECT ISO SKETCH CFARIS
20026942700 | 909 | EX | INSTALL I&C EQUIPMENT | 460 SAND HILL RD | F | 16155.4774 | 15613 | -542.4774 | -3% |  |  | 0 | CCC # 28876 CC#29408. 6/28/21 DSASH CCC # 32222 INITIAL COMMISSIONING BY SHANE GIORDANO PAPERWORK COMPLETED BY CYNTHIA FARIS ON 12/10/21 PAPERWORK ON HOLD AWAITING ISO SKETCH
20026942800 | 584 | EX | RETIRE GAUGE | 460 SAND HILL RD | F | 91.4991 | 0 | -91.4991 | 100% |  |  | 0 | PAPERWORK COMPLETION ON HOLD AWAITING ISO SKETCH
20026952500 | 559 | EX | REPLACE VALVE C-16 | CHESTNUT ST | B | 56236.611 | 47582.37 | -8654.241 | -15% | 31 | 29 | 1640.7714
20026952600 | 560 | EX | RETIRE VALVE C-16 | CHESTNUT ST | B | 952.0929 | 5789.59 | 4837.4971 | 508% |  |  | 0
20026953000 | 2000 | EX | PS&I FOR CALGON HEATER REPLACE | 15024 US 23 |  | 12833.7702 | 0 | -12833.7702 | 100% |  |  | 0
20026967900 | 555 | EX | INSTALL 315' 2" PMIP | 600 AMANDA FURNACE DR | B | 31888.6353 | 71403.61 | 39514.9747 | 124% | 317 | 330 | 216.3746 | TWALKER/KY 02-23-21: ISSUED BACK ORDER CANCEL #48444 FOR JOB OVERRUN EXPLANATION: 150 SQUARE FEET OF 6&2 WAS ESTIMATED AND 990 SQ FEET W AS REQUIRED LEADING TO AN INCREASE IN CONTRACTOR COSTS AND OVERHEADS.
20026969100 | 2000 | EX | ACQUIRE EASEMENT FOR NEW CUST | 600 AMANDA FURNACE DR | B | 2807 | 0 | -2807 | 100% |  |  | 0
20026970100 | 557 | EX | INSTALL 11400'-2"/4" PM/CSIP | FULLERTON | B | 1176644.8813 | 1042042.95 | -134601.9313 | -11% | 11325 | 10870 | 95.8641
20026970200 | 558 | EX | RETIRE 10250'-2"/3"/4" BS/CSIP | FULLERTON | B | 278.4699 | 272.31 | -6.1599 | -2% |  |  | 0
20026972500 | 2000 | EX | INVESTIGATE LAND RIGHTS | 401 MAIN ST | B | 3417 | 0 | -3417 | 100% |  |  | 0
20026977301 | 557 | EX | INSTALL 12,100 OF 2"PMMP MAIN | BATH AV | B | 1697987.4343 | 1937357.64 | 239370.2057 | 14% | 12100 | 11864 | 163.2972
20026977400 | 558 | EX | RETIRE 10,510'OF 4"/6"BSLP | BATH AV | B | 90.4074 | 1237.75 | 1147.3426 | 1,269% |  |  | 0
20026977500 | 557 | EX | INSTALL 4335'-4" & 6" PMLP | FREDERICK | B | 818557.1832 | 1014309.73 | 195752.5468 | 24% | 4345 | 1022 | 992.4753 | TWALKER/KY 01-24-23: PROJECT OVER RUN COST DUE TO ADDITIONAL PAVING/HARD SURFACE REPAIR RESULTED IN $100,000 HIGHER CONTRACT COST, MATERIAL COST WERE $46,000 HIGHER THAN EST. ADN SEGA $68,000 HIGHER THAN EST.
20026977600 | 558 | EX | RETIRE 4766'-2"/3"/4"/6" BSLP | FREDERICK | B | 476.2758 | 11052.89 | 10576.6142 | 2,221% |  |  | 0
20026978100 | 557 | EX | INSTALL 8620'- 2" PMMP | HARRISON | B | 1435185.1923 | 2117372.66 | 682187.4677 | 48% | 8664 | 9303 | 227.6011
20026978200 | 558 | EX | RETIRE 8983' LP - 2520' BS | HARRISON | B | 476.2758 | 513.02 | 36.7442 | 8% |  |  | 0
20026982200 | 559 | EX | INSTALL 5'-4"PMMP & 4'-4"CS | TAYLOR AV | B | 42642.7946 | 40958.2 | -1684.5946 | -4% | 9 | 14 | 2925.5857
20026982300 | 560 | EX | ABANDON 5' - 4" CSMP | TAYLOR AV | B | 183.2963 | 10.78 | -172.5163 | -94% |  |  | 0
20026982500 | 559 | EX | INSTALL 120' - 4" PMLP | R/W - GREENUP BANK | B | 30468.341 | 38925.35 | 8457.009 | 28% | 122 | 85 | 457.9453
20026983300 | 557 | EX | INSTALL 6,600'-2"/4" PMMP | CHESTNUT DR | B | 1529743.322 | 2015230.05 | 485486.728 | 32% | 6575 | 6220 | 323.992
20026983400 | 558 | EX | RETIRE 5374'-4" BSLP/CSLP | CHESTNUT | B | 119.4953 | 92.88 | -26.6153 | -22% |  |  | 0
20026983500 | 557 | EX | INSTALL 1670' - 2" PMMP | RIGGLES | B | 347784.1168 | 426217.2 | 78433.0832 | 23% | 1670 | 1805 | 236.1314
20026983600 | 558 | EX | ABANDON 1667'-2/3/4" PMLP/BSLP | RIGGLES | B | 360.3823 | 290.24 | -70.1423 | -19% |  |  | 0
20026984500 | 583 | EX | REPLACE IP OUTLET BLOCK VALVE | 240 BUCKLEY RD | F | 2174.0477 | 1480.71 | -693.3377 | -32% |  |  | 0 | NOT ON SITE REPLACED INLET AND OUTLET IP RUN BLOCK VALVES SGIORDANO JMULLINS CO PAPERWORK 06132022
20026984600 | 584 | EX | REPLACE IP OUTLET BLOCK VALVE | 240 BUCKLEY RD | F | 50 | 2409.31 | 2359.31 | 4,719% |  |  | 0 | CCC 68181 REPLACED INLET AND OUTLET IP BLOCK VALVS SGIORDANO JMULLINS CO PAPERWORK 06132022
20026988000 | 2000 | EX | INV LAND RIGHTS BXN STA AND RD | 831 POND RUN RD | A | 2489 | 0 | -2489 | 100% |  |  | 0
20026988600 | 2000 | EX | RESEARCH R/W | 4750 WINCHESTER AV |  | 3128 | 0 | -3128 | 100% |  |  | 0 | LS WAS UNABLE TO FIND EXISTING R/W OR OBTAIN NEW EASEMENTS. PATH WAS FINAL LY CHOSEN TO STAY IN ROAD R/W. D.LEMONS
20026988800 | 555 | EX | INSTALL 210'-2" PMLP | 4750 WINCHESTER AV REAR | B | 42176.37 | 21827.5 | -20348.87 | -48% | 214 | 194 | 112.5129
20026991600 | 595R | EX | INSTALL RECTIFIER- JOHNSON ST | 10123 MAYO TRAIL RD | A | 12343.3281 | 8433.77 | -3909.5581 | -32% |  |  | 0 | 30/15 RECTIFIER SERIAL #202283 INSTALLED ON CAP RELOCATION PROJECT AT 10123 MAYO TRAIL / JMM RECTIFIER INSTALLED AND PUT ONLINE 2021 / RECTIFIER TO BE RETIRED AT THE CONCLUSION OF CAP RETIREMENT PROJECT 21-0261305-00 IN 2023 / JMM
20026991700 | 595R | EX | INSTALL RECTIFIER- 10325 MAYO | 10325 MAYO TRAIL RD | A | 12973.4687 | 0 | -12973.4687 | 100% |  |  | 0 | 50/25 RECTIFIER SERIAL #201934 INSTALLED CAP RELOCATION PROJECT AT 10325 MAYO TRAIL / JMM RECTIFIER INSTALLED AND PUT ONLINE 2021 / RECTIFIER TO BE RETIRED AT THE CONCLUSION OF CAP RETIREMENT PROJECT 21-0261305-00 IN 2023 / JMM
20026992000 | 596 | EX | RETIRE RECTIFIER | MAYO TL | F | 60.6196 | 0 | -60.6196 | 100% |  |  | 0 | RECTIFIER 207731 REMOVED FROM SERVICE IN 2021 WITH THE COMPLETION OF CAP JOB 18-0267859-01 (INSTALL) & 18-0267860-01 (RETIREMENT) / JMM TWO RECTIFIERS 860778 & 860865 WERE PLACED AT THE NORTH AND SOUTH ENDS OF CIRCUIT AFTER PLASTIC INSTALLED ON MAYO TRAIL DIVIDED UP CP CIRCUIT
20026992200 | 555 | EX | INSTALL 100'-2" PMIP | 112 TANGO AV | B | 11276.4442 | 8539.31 | -2737.1342 | -24% | 100 | 38 | 224.7187
21026103200 | 2000 | EX | INVESTIGATE R/W AND SEWER PLAN | LEE ST | B | 7553 | 0 | -7553 | 100% |  |  | 0
21026103300 | 2000 | EX | INVESTIGATE ROW & LAND RIGHTS | MAIN ST |  | 7693 | 0 | -7693 | 100% |  |  | 0
21026104900 | 557 | EX | EMER INSTALL 5'-3" PMIP | 6227 EMILY ST | A | 5995.5434 | 4758.29 | -1237.2534 | -21% | 5 | 4 | 1189.5725 | SEE PAPER PACKET FOR INFO
21026105000 | 558 | EX | EMER RETIRE 5'-3" P-IP | 6227 EMILY ST | A | 750.8346 | 3758.23 | 3007.3954 | 401% |  |  | 0 | SEE PAPER COPIES FOR TEST INFO SEE PAPER COPIES/ PIPE EXPOSURE FORM WILL NOT ACCEPT THE CORRECT MAIN NUMBER NOT LETTING ME COMPLETE THIS ORDER
21026105700 | 557 | EX | EMER INST 360'-2" PMIP D244304 | 4446 13TH ST | A | 25736.2708 | 109722.07 | 83985.7992 | 326% | 345 | 349 | 314.3899 | INSTALLED 345' OF 2" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7.5 P SIG OVERRUN EXPLANATION: THE SIGNIFICANT COST DIFFERENCE RESULTED FROM PAVING REQUIREMENTS. THE PROJECT WAS NOT ESTIMATED FOR CONTRACT RESTORATION. PAVE TICKETS WERE SUBMITTED TO REPAIR ROAD AND PARKING LOT AREA
21026105800 | 558 | EX | EMER RETIRE 350'-3"/2" CSIP | 4446 13TH ST | A | 1114.7918 | 27035.38 | 25920.5882 | 2,325% |  |  | 0 | FOUND CRACKED MAIN RETIRED 345' OF 3" ST AND INSTALLED 345' OF NEW 2" PL TO STOP LEAKAGE TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7.5 PSIG
21026106400 | 584 | EX | RETIRE PAPER RECORD GAUGE | 425 CAROLINE RD | F | 341.3226 | 92.38 | -248.9426 | -73% |  |  | 0 | TICKET 13749
21026106800 | 2000 | EX | DESIGN COSTS | BLACKBURN ST | B | 10000 | 0 | -10000 | 100% |  |  | 0
21026106900 | 2000 | EX | DESIGN COSTS | HARRISON ST | B | 10000 | 0 | -10000 | 100% |  |  | 0
21026109000 | 557 | EX | EMER - INSTALL 10'-4" PMIP | COUNTRY CLUB DR | A | 8970.0544 | 2349.57 | -6620.4844 | -74% |  | 5 | 469.914 | INSTALLED 5' OF NEW 4" PL MAIN TO REPAIR CRACKED PIPE TESTED 90 PSIG 1 HR
21026109100 | 558 | EX | EMER - RETIRE 10'-4" CSIP | COUNTRY CLUB DR | A | 556.9397 | 5925.07 | 5368.1303 | 964% |  |  | 0 | RETIRE 5' OF 4" CS MAIN DUE TO SPLIT MAIN SOAP TESTED OP 7.5 PSIG
21026110200 | 557 | EX | EMER - INSTALL 5'-3" PMIP | 2326 SHOPES CREEK RD | A | 7868.6589 | 880.36 | -6988.2989 | -89% | 5 | 5 | 176.072 | INSTALLED 5' OF 3" PLASTIC. TESTED AT 90PSIG FOR 1HR.
21026110300 | 558 | EX | EMER - RETIRE 5'-3" PIP | 2326 SHOPES CREEK RD | A | 441.8134 | 7215.11 | 6773.2966 | 1,533% |  |  | 0 | RETIRED 5' OF 3" PLASTIC DUE TO PAC CLAMPS LEAKING.
21026113401 | 555 | EX | INSTALL 100'-2" PMMP | 2000 FERN DR | B | 11198.5401 | 21410.67 | 10212.1299 | 91% | 100 | 82 | 261.1057
21026114100 | 2000 | EX | ROW CLEARING AND ROAD ACCESS | BBQ HOLLOW | A | 30000 | 0 | -30000 | 100% |  |  | 0
21026114400 | 2000 | EX | BUY-OUT CUSTOMERS | RIVA RIDGE | B | 45000 | 0 | -45000 | 100% |  |  | 0 | CUSTOMER BUY OUTS STARTED, ALL PAPERWORK FOR COMMISION OBTAINED. D.LEMONS 1 1/7/2023
21026114900 | 2000 | EX | INVESTIGATE LAND ROW & STAKE | 2000 FERN DR | B | 1992 | 0 | -1992 | 100% |  |  | 0
21026115100 | 557 | EX | INSTALL 1'-4" PMLP | DIXON | A | 149.4587 | 0 | -149.4587 | 100% | 1 | 1 | 0
21026115800 | 557 | EX | EMER - INSTALL 138'-4" PM/CSIP | SHORT WHITE OAK | A | 10752.5629 | 2573.82 | -8178.7429 | -76% | 134 | 138 | 18.6509 | INSTALLED 134' OF 4" PL IP TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7.5 PSIG
21026115900 | 558 | EX | EMER - RETIRE 134'-4" CSIP | SHORT WHITE OAK | A | 1105.3087 | 9847.31 | 8742.0013 | 791% |  |  | 0 | RETIRED 134' OF 4" CS DUE MAIN EXPOSED OUT OF GROUND AND DETERIORATION
21026116900 | 555 | EX | INSTALL 200'-2" PMLP | 306 W FRANKLIN ST | B | 39229.3021 | 24792.54 | -14436.7621 | -37% | 200 | 200 | 123.9627
21026117300 | 558 | EX | EMER - RETIRE 2'-4" P-LP | SYCAMORE ST | A | 441.8134 | 183.09 | -258.7234 | -59% |  |  | 0 | RETIRE 2' OF 4" PL DUE TO DAMAGE
21026120600 | 584 | EX | RETIRE REG STATION WITH AMRP | 419 BUCKLEY RD | F | 9924.8698 | 1058.49 | -8866.3798 | -89% |  |  | 0 | CC# 6407 RETIRED REG STATION DASH 12-15-2022
21026121500 | 555 | EX | INSTALL 160'-2" PMIP | 1604 BIRCH ST | B | 21640.9206 | 37719.27 | 16078.3494 | 74% | 160 | 210 | 179.6156
21026121600 | 555 | EX | INSTALL 100'-2" PMIP | 7625 OXCART HILL DR | B | 13861.3812 | 16499.56 | 2638.1788 | 19% | 100 | 100 | 164.9956
21026122300 | 555 | EX | INSTALL 100'-2" PMMP | 1213 WINCHESTER AV NEW | B | 25260.7035 | 26947.59 | 1686.8865 | 7% | 102 | 85 | 317.0305
21026123800 | 561 | EX | INSTALL 160'-4" CSLP/PMLP | 8175 CANNONSBURG RD | B | 161313.4069 | 86016.2 | -75297.2069 | -47% | 159 | 134 | 641.9119 | UNDERRUN EXPLANATION: SIGNIFICANTLY LESS HARD SURFACE RESTORATION AND BACKFILL REQUIRED THAN ESTIMATED KYTC REQUIRED RELOCATION AND TOLD US NOT TO WORRY ABOUT THE MILL & OVERLAY THAT THEY WOULD DO THAT WHEN THEY COMPLETED THEIR PART OF THE PROJECT, THIS RESULTED IN A SIGNIFICANT AMOUNT OF THE COST VARIATION
21026125300 | 562 | EX | RETIRE 180'-4" BSLP | 8175 CANNONSBURG RD | B | 282.1429 | 0 | -282.1429 | 100% |  |  | 0 | COMMITT DATE WAS PUSHED OUT TILL END OF AUG.2021
21026126500 | 2000 | EX | DESIGN FARMERS MKT SMRP | 4570 LOUISA RD |  | 40000 | 0 | -40000 | 100% |  |  | 0
21026127800 | 555 | EX | INSTALL 500'-2" PMMP | 1819 ASHLAND RD | B | 43810.3768 | 47089.22 | 3278.8432 | 7% | 500 | 500 | 94.1784
21026127900 | 2000 | EX | INVESTIGATE ROW | 1819 US RTE 23 |  | 3361 | 0 | -3361 | 100% |  |  | 0
21026128500 | 559 | EX | NSP - INSTALL 150'-2" PMLP | 1510 POPLAR AV | A | 16760.5972 | 10156.16 | -6604.4372 | -39% | 150 | 150 | 67.7077 | INSTALLED 150' 2"P. PRESSURE TESTED 90LBS 1HR. SOAP TESTED 2" EF COUPLING AT OP. PRESS. (11 IWC) 15MIN. PRESS. TEST 2X1 MONITORING TEE 90LBS 15MIN. SOAP TESTED MONITORING TEE END CAP OP. PRESS (11 IWC) 15MIN.
21026129800 | 555 | EX | INSTALL 200'-2" PMMP | 2745 CRESTVIEW DR | B | 21853.3833 | 25563.52 | 3710.1367 | 17% | 200 | 230 | 111.1457
21026130200 | 557 | EX | EMER-INSTALL 5'-2" PMIP/CSIP | 610 CENTRAL AV | A | 6178.4541 | 7558.85 | 1380.3959 | 22% | 26 | 6 | 1259.8083
21026130300 | 558 | EX | EMER-RETIRE 5'-2" BSIP | 610 CENTRAL AV | A | 410.7144 | 230.72 | -179.9944 | -44% |  |  | 0
21026130400 | 557 | EX | INSTALL 25,111'-2",4" PMMP | PADDLE CREEK RD | B | 3707985.656 | 4360387.57 | 652401.914 | 18% | 25131 | 23540 | 185.2331
21026130500 | 558 | EX | RETIRE 25,000' OF BSLP MAINS | PADDLE CREEK RD | B | 485.0228 | 1741.22 | 1256.1972 | 259% |  |  | 0
21026131300 | 588 | EX | RETIRE EFC UNIT | CENTER ST | F | 74.8797 | 0 | -74.8797 | 100% |  |  | 0 | REPLACED EFC
21026132100 | 561 | EX | INSTALL 600'-4" PMMP | 18648 E KY-8 | A | 159985.8979 | 75178.06 | -84807.8379 | -53% | 608 | 582 | 129.1719 | INSTALLED 573' OF 4" PL MP AND 9' OF 2" PL MP TESTED 90 PSIG 2 HRS SOAP TESTED FINAL CONN OP 44 PSIG UNDERRUN EXPLANATION: A SIGNIFICANT UNIT OF COST WAS THE PLANNED ROCK BORE BUT THE CREW WAS ABLE TO AVOID THE NEED FOR A ROCK BORE, THE JOB DURATION ESTIMATE TOOL ALSO PLANNED FOR 120 HOURS OF LABOR AND THE CREW COMPLETED THE JOB IN 60 HOURS AND SOME CREW MEMBERS WERE NOT NEEDED THE ENTIRE DURATION OF THE JOB.
21026132200 | 562 | EX | RETIRE 450'-4" P-MP | 18648 KY-8 | A | 875.427 | 212.81 | -662.617 | -76% |  |  | 0 | RETIRED 487' OF 4" PL MP
21026133300 | 555 | EX | INSTALL 200'-2" PMIP | 801 MCCOWAN ST | B | 14590.9404 | 19749.69 | 5158.7496 | 35% | 200 | 190 | 103.9457
21026133600 | 2000 | EX | INVESTIGATE VALVE REPLACEMENT | 240 BUCKLEY RD |  | 10000 | 0 | -10000 | 100% |  |  | 0
21026133900 | 583 | EX | INSTALL VRG CONTROLER | US 60 | F | 6187.1439 | 0 | -6187.1439 | 100% |  |  | 0
21026134000 | 584 | EX | RETIRE DAMAGED CONTROLLER | US 60 | F | 220.9908 | 0 | -220.9908 | 100% |  |  | 0
21026139100 | 557 | EX | EMER - INSTALL 5'-4" PMMP | 35TH ST | A | 6493.0322 | 2800.66 | -3692.3722 | -57% | 2 | 2 | 1400.33 | INSTALLED MAIN ON TESTED 90 PSIG 1 HOUR SOAP TESTED FINAL CONN OP 44 PSIG
21026139200 | 558 | EX | EMER - RETIRE 5'-4" P-MP | 35TH ST | A | 743.2708 | 5590.11 | 4846.8392 | 652% |  |  | 0
21026139800 | 555 | EX | INSTALL 100'-2" PMIP | 5720 SWANSON DR | B | 27338.1249 | 19936.66 | -7401.4649 | -27% | 102 | 102 | 195.4575
21026140100 | 559 | EX | INSTALL 52'-4"/6" PMIP/CSIP | 240 BUCKLEY RD | B | 83495.319 | 67346.12 | -16149.199 | -19% | 52 | 35 | 1924.1749
21026140200 | 560 | EX | RETIRE 47'-4"/6" BSIP/CSIP | 240 BUCKLEY RD | B | 500 | 207.25 | -292.75 | -59% |  |  | 0
21026143700 | 559 | EX | INSTALL 4'-4" PMLP | 301 RIVERSIDE DR | A | 3297.2047 | 478.5 | -2818.7047 | -85% | 5 | 4 | 119.625 | INSTALLED 4' OF 4" PL LP MAIN LINE TESTED 90 PSIG 1 HOUR SOAP TESTED FINAL CONN OP 10" WC
21026143800 | 560 | EX | RETIRE 4'-4" PMLP | 301 RIVERSIDE DR | A | 295.4309 | 44.74 | -250.6909 | -85% |  |  | 0 | RETIRED MAIN DUE TO STEEL SADDLE TEE BIENG ON PL PIPE INSTALLED NEW SECTION OF PIPE
21026144600 | 559 | EX | INSTALL 12" SS | 150 ARMCO RD | B | 13660.0322 | 25613.83 | 11953.7978 | 88% |  |  | 0 | INSTALLED 12" SS TO STOPPLE AND KILL 12" MAIN
21026144700 | 560 | EX | RETIRE 1273'-6/12/16" CS/BSHP | 150 ARMCO RD | B | 388.1295 | 167.43 | -220.6995 | -57% |  |  | 0 | RETIRE 1207' OF 12" BS HP TO AK STEEL SOAP TESTED OP 113 PSIG
21026146300 | 559 | EX | INSTALL 4'-4" PMLP | 317 RIVERSIDE DR | A | 2206.8953 | 424.36 | -1782.5353 | -81% | 4 | 4 | 106.09 | INSTALLED 4' OF 4" PLASTIC MAIN. PRESSURE TESTED 90LBS FOR 1HR.
21026146400 | 560 | EX | RETIRE 4'-4" P-LP | 317 RIVERSIDE DR | A | 197.4141 | 39.69 | -157.7241 | -80% |  |  | 0
21026146800 | 588 | EX | RETIRE GMB #44535-AK STEEL | 150 ARMCO RD | F | 2893.6188 | 3852.12 | 958.5012 | 33% |  |  | 0 | ALL FACILITIES REMOVED FROM AK STEEL BY MATT RYAN AND SHANE GIORDANO MAINLINE/SERVICE LINE ABANDONED ON 10/18/2021 BY CONSTRUCTION SERVICES M&R PAPERWORK COMPLETED BY CYNTHIA FARIS ON 10/25/2021
21026146900 | 2000 | EX | INVESTIGATE PIPE DEPTH | 7117 US ROUTE 60 |  | 23315.9979 | 0 | -23315.9979 | 100% |  |  | 0
21026149000 | 555 | EX | INSTALL 75'-2" PMIP | 1222 HILLCREST CT | A | 4287.763 | 765.35 | -3522.413 | -82% | 75 | 66 | 11.5962 | INSTALLED 66' OF 2" PL TESTED 90 PSIG 0005 MIN SOAP TESTED CAP OP 8 PSIG
21026150000 | 559 | EX | EMER - INSTALL 14'-4" PMLP | 306 FERRY ST | A | 3163.1338 | 72137.82 | 68974.6862 | 2,181% | 20 | 14 | 5152.7014 | INSTALLED 16' OF 4" PL W/ 4 90'S TO GO ABOVE 24" CLAY TILE SEWER TESTED 90 PSIG 1 HR OVERRUN EXPLANATION: CROSSBORE FOUND- CAMERA CREW NEEDED AND ADDITIONAL HOURS NEEDED TO REMEDIATE THE CROSS-BORE ISSUE 2 MAINTENCE JOBS AND 1 PAVE JOB CHARGED BACK TO CAPITAL JOB AND WERE NOT ACCOUNTED FOR IN ORIGINAL PROPOSED COST, $26K IN FLAGGING AND RESTORATION CHARGED TO MAINTENCE JOBS AND $14K IN CAMERA WORK BY CONTRACTOR
21026150100 | 560 | EX | EMER - RETIRE 6'-4" P-LP | 306 FERRY ST | A | 335.9749 | 669.23 | 333.2551 | 99% |  |  | 0 | REMOVED 4" PL FROM SEWER LINE CROSS BORE
21026150600 | 557 | EX | EMER - INSTALL 5'-2" PMMP | BELMONT | A | 1696.2756 | 378.77 | -1317.5056 | -78% | 5 | 4 | 94.6925
21026150700 | 558 | EX | EMER - RETIRE 5'-2" PMP | BELMONT | A | 335.9749 | 64.43 | -271.5449 | -81% |  |  | 0
21026153400 | 557 | EX | EMER - INSTALL 6'-4" PMIP | 416 CAROLINE RD | A | 4080.2324 | 7455.58 | 3375.3476 | 83% | 10 | 10 | 745.558
21026153500 | 558 | EX | EMER - RETIRE 6'-4" PMIP | 416 CAROLINE RD | A | 518.618 | 101.71 | -416.908 | -80% |  |  | 0
21026154000 | 555 | EX | INSTALL 160'-2" PMMP | 1999 FERN DR | B | 33091.7151 | 28534.77 | -4556.9451 | -14% | 160 | 130 | 219.4982
21026154600 | 584 | EX | RETIRE R-1354 | 4570 LOUISA RD | F | 163.2711 | 8911.51 | 8748.2389 | 5,358% |  |  | 0
21026154800 | 558 | EX | RETIRE 35'-3" CSMP | PADDLE CREEK RD | B | 485.0228 | 27.2 | -457.8228 | -94% |  |  | 0
21026155700 | 577 | EX | INSTALL FENCE - SCADA BUILDING | US 23 | F | 15936.4497 | 7557.57 | -8378.8797 | -53% |  |  | 0
21026156500 | 555 | EX | INSTALL 140'-2"/4" PMMP | 101 A ST | A | 3669.7405 | 2096.07 | -1573.6705 | -43% | 140 | 141 | 14.8657
21026157400 | 2000 | EX | INVESTIGATE PROPERTY | 100 HARRIS RD |  | 2000 | 0 | -2000 | 100% |  |  | 0 | PS&I CHARGED TO GROUND BED INSTALATION. TECH REQUESTING WORK IN NOTES HAS R ETIRED AND NO INFORMATION IS AVAILIBLE TO SEE WHAT WORK MAY OR MAY NOT HAVE BEEN ACOMPLISHED. D.LEMONS 10/25/2023
21026157800 | 557 | EX | INSTALL 5'-4" PMLP | 216 PERRY | A | 4114.4273 | 2758.28 | -1356.1473 | -33% | 5 | 1 | 2758.28
21026157900 | 558 | EX | RETIRE 5'-4" PMLP | PERRY | A | 72.8047 | 485.31 | 412.5053 | 567% |  |  | 0
21026993200 | 557 | EX | EMER- INSTALL 5'-4" PMMP | STATE RT 1 | A | 4003.4824 | 3260.67 | -742.8124 | -19% | 1 | 4 | 815.1675 | INSTALLED 4' OF 4" P. PRESSURE TESTED AT 90LBS FOR 1HR. SOAP TESTED (2) 4" EF COUPLINGS AT OPERATING PRESSURE (11PSIG).
21026993300 | 558 | EX | EMER- RETIRE 5'-4" P-MP | STATE RT 1 | A | 647.029 | 184.74 | -462.289 | -71% |  |  | 0 | REMOVED 4' OF DAMAGED 4" P
21026993401 | 557 | EX | INSTALL 10750'-2"/4"PMMP MAIN | LEE ST | B | 1880428.7756 | 2072101.63 | 191672.8544 | 10% | 10750 | 11749 | 176.3641
21026993500 | 558 | EX | RETIRE 13650' OF 4"/6"BSLP | LEE ST | B | 86.5975 | 80 | -6.5975 | -8% |  |  | 0
21026993600 | 557 | EX | EMER INST 40'-4" PMLP | 2049 FOREST AV | A | 13260.7401 | 772.98 | -12487.7601 | -94% | 40 | 27 | 28.6289 | INSTALLED 28' OF 4" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 10" WC
21026993700 | 558 | EX | EMER RET 40'-4" BSLP/CSLP/P-LP | ELMWOOD | A | 1322.2973 | 372.17 | -950.1273 | -72% |  |  | 0 | RETIRED 28' OF 4" STEEL MAIN AND 3 WAY TEE
21026996600 | 2000 | EX | OBTAIN SEWER AND ROAD PLANS | BATH AV |  | 3500 | 0 | -3500 | 100% |  |  | 0
21026999201 | 566 | EX | RETIRE 3"PIP SERVICE LINE | 924 SUMMIT RD | A | 6359.645 | 14749.54 | 8389.895 | 132% |  |  | 0 | STEP 3 NEEDS INVESTIGATED STEP 3 NEEDS STATE PERMIT STEP 3 NEEDS STATE PERMIT THIS IS A PAPER ABN. THIS LINE IS AN ACTIVE LINE BUT THEY ARE NOT OUR CUSTOMER. THEY ARE USING NATURAL ENERGY. OUR ASSETS ARE NOT WITHIN THE PROPERTY. U131418 J. PARKS 4-24-23
22026159700 | 559 | EX | EMER - INSTALL 4'-4" PMLP | 222 34TH ST | A | 4455.398 | 1914.95 | -2540.448 | -57% | 4 | 4 | 478.7375
22026159800 | 560 | EX | EMER - RETIRE 4'-4" P-LP | 222 34TH ST | A | 448.5353 | 6434.1 | 5985.5647 | 1,334% |  |  | 0 | RETIRED 4' OF 4" PL LP TO REMOVED STEEL SADDLE FROM PLASTIC MAIN
22026159900 | 557 | EX | EMER - INSTALL 2'-2" PMLP | 431 ETNA ST | A | 2367.5988 | 2408.32 | 40.7212 | 2% | 2 | 2 | 1204.16
22026160000 | 558 | EX | EMER - RETIRE 2'2"P-LP D244381 | 431 ETNA ST | A | 506.8997 | 487.19 | -19.7097 | -4% |  |  | 0
22026160300 | 910 | EX | RETIRED ELECTRONICS | SKYLINE DR | F | 75.9523 | 422.53 | 346.5777 | 456% |  |  | 0
22026165300 | 595R | EX | INSTALL NEW GROUND BED | 624 BIGGS LN | B | 69071.4307 | 79502.86 | 10431.4293 | 15% |  |  | 0 | GROUND BED INSTALLED BY MATCOR W/FOREMAN GENE PETITE. THE EXPECTED WELL LIFE OF THE GROUND BED AS INSTALLED IS CONSERVATIVELY 8AMPS/38YEARS OR 10AMPS/30YEARS. VENDER IS CONFIDENT WE WOULD COULD SEE 15AMPS/30YEARS. -OSS
22026169000 | 909 | EX | MAVITY HVAC UPGRADE | US 60 | F | 15264.0767 | 5678.5 | -9585.5767 | -63% |  |  | 0
22026169600 | 2000 | EX | SURVEY ENCROACHMENT | ASHLAND FIND LOC | B | 5000 | 0 | -5000 | 100% |  |  | 0
22026169700 | 2000 | EX | SURVEY ENCROACHMENT | ASHLAND | B | 5000 | 0 | -5000 | 100% |  |  | 0
22026172301 | 557 | EX | INSTALL 5000' OF 2"PMMP MAIN | VERNA | B | 1183513.1452 | 1225170.53 | 41657.3848 | 4% | 4359 | 4923 | 248.8667
22026172400 | 558 | EX | RETIRE 4792'-2/4/8" PL/CS/BSLP | VERNA | B | 709.5359 | 220 | -489.5359 | -69% |  |  | 0
22026174300 | 2000 | EX | INVESTIGATE & STAKE ROW | 13TH ST |  | 7194 | 0 | -7194 | 100% |  |  | 0
22026174900 | 555 | EX | INSTALL 50'-2" PMMP | 923 DIEDRICH DR | B | 30717.8249 | 36910.2 | 6192.3751 | 20% | 50 | 50 | 738.204
22026175800 | 559 | EX | EMER - INSTALL 120'-3" PMLP | 423 MARCIA ST | A | 12124.3189 | 32123.93 | 19999.6111 | 165% | 120 | 120 | 267.6994 | INSTALLED 120' OF 3" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 10" W C
22026175900 | 560 | EX | EMER - RETIRE 121'-3" P-LP | 423 MARCIA ST | A | 373.4562 | 931.56 | 558.1038 | 149% |  |  | 0 | RETIRE 121' OF 3" PL DUE TO WATER AND STEEL FITTINGS ON PL MAIN
22026177000 | 557 | EX | EMER - INSTALL 2'-4" PMIP | 1803 W LITTLE GARNER RD | A | 4197.8249 | 2292.91 | -1904.9149 | -45% | 0 | 2 | 1146.455
22026177100 | 558 | EX | EMER - RETIRE 2'-4" P-IP | 1803 W LITTLE GARNER RD | A | 310.9595 | 2387.49 | 2076.5305 | 668% |  |  | 0
22026180500 | 555 | EX | INSTALL 160'-2" PMIP | 1132 HOWARD DR | B | 36664.9938 | 22724.8 | -13940.1938 | -38% | 160 | 150 | 151.4987
22026180700 | 557 | EX | EMER - INSTALL 3'-3" PMIP | WOODHAVEN | A | 4036.7887 | 6701.19 | 2664.4013 | 66% | 0 | 4 | 1675.2975
22026180800 | 558 | EX | EMER - RETIRE 3'-3" PMIP | WOODHAVEN | A | 418.4749 | 61.4 | -357.0749 | -85% |  |  | 0
22026181500 | 2000 | EX | ENE PS&I FOR WESTWOOD PH2 SMRP | VERNA | B | 25000 | 0 | -25000 | 100% |  |  | 0
22026182300 | 584 | EX | RETIRE PAPER RECORD GAUGE | 490 FERGUSON RD | F | 329.4627 | 144.38 | -185.0827 | -56% |  |  | 0
22026184500 | 555 | EX | INSTALL 250'-4" PMLP/CSLP | 3430 EUCLID AV A | B | 60316.4006 | 63976.36 | 3659.9594 | 6% | 252 | 234 | 273.4032
22026190600 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 624 BIGGS LN | F | 4801.1928 | 817.09 | -3984.1028 | -83% |  |  | 0 | CCC 71454 RETIRED ERX AND INSTALLED NEW MIWI350
22026191000 | 910 | EX | RETIRED ELECTRONICS EQUIPMENT | 624 BIGGS LN | F | 124.8731 | 261.55 | 136.6769 | 109% |  |  | 0 | CCC 71454 RETIRE ERX AND INSTALLED NEW MIWI 350
22026191700 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | BARBECUE RD | F | 4801.1928 | 10605.54 | 5804.3472 | 121% |  |  | 0 | UPGRADED ERX TO MIWI JOSH MULLINS
22026191800 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | BARBECUE RD | F | 124.8731 | 20.04 | -104.8331 | -84% |  |  | 0
22026191900 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 828 MAIN ST RR | F | 4801.1928 | 744.93 | -4056.2628 | -84% |  |  | 0 | CCC 71454
22026192000 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 828 MAIN ST RR | F | 124.8731 | 922.45 | 797.5769 | 639% |  |  | 0 | CCC 71454
22026192100 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 243 KENWOOD BV | F | 4801.1928 | 2317.01 | -2484.1828 | -52% |  |  | 0 | CCC 75023
22026192200 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 243 KENWOOD BV | F | 124.8731 | 884.51 | 759.6369 | 608% |  |  | 0 | CCC 75023 UPGRADED ERX TO MIWI J.MULLINS
22026193100 | 2000 | EX | INVEST ROW & OBTAIN RR PERMIT | SULLIVAN ST |  | 7470 | 0 | -7470 | 100% |  |  | 0
22026196200 | 557 | EX | EMER - INSTALL 1'-2" PMMP | 1020 BELMONT ST | A | 2866.3857 | 6510.29 | 3643.9043 | 127% | 0 | 1 | 6510.29 | INSTALLED 1' OF 2" PL DUE TO FACILTY DAMAGE TESTED 90 PSIG 0005 MIN SOAP TE STED FINAL CONN OP 42 PSIG REVISED EXECUTE COMMENTS: INSTALLED 1' OF 2" PL DUE TO FACILITY DAMAGE TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 42 PSIG/MCOLLETT 7/8/22
22026196300 | 558 | EX | EMER - RETIRE 1'-2" P-MP | 1020 BELMONT ST | A | 497.9695 | 1254.11 | 756.1405 | 152% |  |  | 0 | RETIRED 1' OF 2" PL MP DUE TO FACILITY DAMAGE SOAP TESTED OP TO VERIFY GAS SHUTOFF
22026198200 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 29022 E MAYO TRAIL | F | 4801.1928 | 5532.75 | 731.5572 | 15% |  |  | 0 | CC 76915 UPGRADDED ERX TO MIWI 350
22026198300 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 29022 E MAYO TRAIL | F | 124.8731 | 467.24 | 342.3669 | 274% |  |  | 0 | CC 76915 UPDATTED ERX TO MIWI 350
22026198700 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 100 BOY SCOUT RD | F | 4801.1928 | 6293.17 | 1491.9772 | 31% |  |  | 0 | CC 497 CC 497 REPLACED OLD ERX WITH NEW MIWI350 SGIORDANO 9-13-2022
22026198800 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 100 BOY SCOUT RD | F | 124.8731 | 1014.14 | 889.2669 | 712% |  |  | 0 | CC 497 REPLACED ERX WITH NEW MIWI350 SGIORDANO 9-13-2022
22026199900 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | 516 3RD ST RR | F | 4801.1928 | 6476.38 | 1675.1872 | 35% |  |  | 0 | CC 118 INSTALLED NEW MIWI350 RETIRED OLD ERX SGIORDANO 9-15-22
22026200200 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | 516 3RD AVE RR | F | 124.8731 | 1400.9 | 1276.0269 | 1,022% |  |  | 0 | CC 118 INSTALLED NEW MIWI350 SGIORDANO 9-15-22 C 2820
22026200300 | 559 | EX | EMER - INSTALL 5'-2" PMIP | 2210 SLOAN ST | A | 2610.0199 | 9101.9 | 6491.8801 | 249% | 3 | 5 | 1820.38 | REPLACED 5' SECTION OF 2" PMMP. TESTED MAIN AT 90 PSIG FOR 1 HOUR AND TEST WAS GOOD. TESTED 2X1 EF TEES AT 90 PSIG FOR 5 MINS AND SOAP TESTED THE CAPS AND DEAD ENDS AT OP FOR 5 MINS. ALL TEST ARE GOOD.
22026200900 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | PAUL COFFEY BV | F | 4801.1928 | 6137.4 | 1336.2072 | 28% |  |  | 0 | CC 632 UPGRADED TO MIWI 350 PAPERWORK DONE BY J.MULLINS
22026201000 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | PAUL COFFEY BV | F | 124.8731 | 485.58 | 360.7069 | 289% |  |  | 0 | CC 632 UPGRADED TO MIWI 350 PAPERWORK DONE BY J.MULLINS
22026205200 | 555 | EX | INSTALL 115'-2" PMMP | 1519 MAPLE ST | B | 42423.5179 | 21273.79 | -21149.7279 | -50% | 117 | 103 | 206.5417 | CJ HUGHES CASEY PACK'S CREW INSTALLED 103' 2" STEEL/PLASTIC MAIN LINE EXTEN TION AND A NEW 1" PLASTIC SERVICE TO 1519 MAPLE ST 10/6/22 MBLANKE U123965
22026205500 | 2000 | EX | INVESTIGATE AND STAKE ROW | CENTRAL PY |  | 7194 | 0 | -7194 | 100% |  |  | 0
22026205600 | 557 | EX | INSTALL 1200'-2" PMMP | CENTRAL PY | B | 61578.4138 | 162971.11 | 101392.6962 | 165% | 1204 | 1268 | 128.5261 | LEVEL 2 BUDGET VARIANCE EXPLANATION FORM WAS SUBMITTED FOR APPROVAL IN WMSDOCS PER VAPIERCE 5/25/23
22026206400 | 588 | EX | RETIRE ELECTRONIC | 2236 MONTGOMERY AV | F | 65.0112 | 2331.95 | 2266.9388 | 3,487% |  |  | 0 | RETIRED OLD MINIAT INSTALLED NEW EC350 DASH 9-19-2022
22026207100 | 557 | EX | INSTALL 7870'-2", 4" PMMP | VIRGINIA | B | 1271473.5495 | 1549123.72 | 277650.1705 | 22% | 7870 | 7580 | 204.3699
22026207200 | 558 | EX | RETIRE 6009'-2",3", 4" LP | VIRGINIA | B | 1120.6093 | 873.05 | -247.5593 | -22% |  |  | 0
22026208400 | 2000 | EX | BIGGS LANE - INV EASEMENTS | 624 BIGGS LN |  | 5000 | 0 | -5000 | 100% |  |  | 0 | CC 4026
22026210700 | 586 | EX | RETIRE METAL BUILDING | 419 BUCKLEY RD | F | 1009.5809 | 0 | -1009.5809 | 100% |  |  | 0 | REG STATION AND BUILDING RETIRED DASH 12-15-22
22026211000 | 557 | EX | EMER - INSTALL 3'-4" PMMP | 35TH | A | 12351.4608 | 8542 | -3809.4608 | -31% | 2 | 3 | 2847.3333 | CUT OUT 3' OF 4" PL MP AND REPLACED WITH NEW 3' OF 4" PL MP TESTED 90 PSIG 1 HOUR
22026211100 | 558 | EX | EMER - RETIRE 3'-4" PMMP | 35TH | A | 477.8601 | 449.88 | -27.9801 | -6% |  |  | 0 | RETIRED 3' OF 4" PL MP AND INSTALLED NEW 3' OF 4" PL TESTED 90 PSIG 1 HOUR SOAP TESTD FINAL CONN OP 40 PSIG
22026211800 | 588 | EX | RETIRE GMB SETTING | 100 WURTS RD R | F | 1288.7874 | 1541.41 | 252.6226 | 20% |  |  | 0 | GMB NO CC NEEDED
22026213300 | 2000 | EX | INVESTIGATE ROW & STAKE | PANOLA ST |  | 4428 | 0 | -4428 | 100% |  |  | 0
22026213800 | 560 | EX | EMER - RETIRE 150'-2" P-IP | TOOTSIE DR | A | 4412.2636 | 4136.05 | -276.2136 | -6% |  |  | 0 | ABANDONED 150' OF 2" PLASTIC. SOAP TESTED ABANDONMENT AT OP. PRESS. 15MIN.
22026214200 | 2000 | EX | LAND RESEARCH |  | B | 4428 | 0 | -4428 | 100% |  |  | 0
22026214400 | 910 | EX | MAVITY HVAC/RTU | US 60 | F | 55.5311 | 0 | -55.5311 | 100% |  |  | 0 | UPGRADED RTU
22026216300 | 587 | EX | INSTALL VRG CONTROLLER | US23--ASHLAND OIL | F | 10806.1191 | 28545.09 | 17738.9709 | 164% |  |  | 0 | CC 15047 CC 15628 CC 15628 CC 15628 CC 15628 CC 16352 NOT ON SITE CAPITAL PAPERWORK/ISO SKETCH
22026216400 | 588 | EX | RETIRE CONTROLLERS | US23--ASHLAND OIL | F | 84.9152 | 572.67 | 487.7548 | 574% |  |  | 0 | RETIRED CONTROLLERS, INSTALLED NEW VRG'S
22026218400 | 560 | EX | RETIRE 2'-4" BSLP | 3430 EUCLID AV | B | 84.9152 | 0 | -84.9152 | 100% |  |  | 0
22026218500 | 555 | EX | INSTALL 35'-2"/4 PMLP | 508 BELLEFONTE ST A | A | 16435.9913 | 8610.21 | -7825.7813 | -48% | 35 | 39 | 220.7746 | INSTALLED 2' OF 4" PL AND 37' OF 2" PL LP TESTED 90 PSIG 1 HR
22026219600 | 555 | EX | INSTALL 90'-2" PMIP | 85 YANKEES LN | B | 21041.6638 | 50608.23 | 29566.5662 | 141% | 90 | 57 | 887.8637
22026223300 | 2000 | EX | EN PS&I FOR C-16 VALVE REPL | CHESTNUT ST | B | 10000 | 0 | -10000 | 100% |  |  | 0
22026226600 | 2000 | EX | INVEST ROW/OBTAIN EASEMENT | 85 YANKEES LN |  | 11694 | 0 | -11694 | 100% |  |  | 0
22026228900 | 561 | EX | EMER - INSTALL 40'-2" PMIP | TONI DR | B | 32269.3764 | 37570.14 | 5300.7636 | 16% | 20 | 88 | 426.9334
22026229000 | 562 | EX | EMER - RETIRE 40'-2" PIP | TONI DR | B | 132.427 | 0 | -132.427 | 100% |  |  | 0
22026229300 | 2000 | EX | EMER RELOCATION & INVST ROW | TONI DR |  | 11694 | 0 | -11694 | 100% |  |  | 0
22026230800 | 558 | EX | EMER - RETIRE 3'-2" P-IP | 215 TONI DR C | A | 1985.3283 | 1400.06 | -585.2683 | -29% | 0 |  | 0 | CONTRACTOR HIT MISS MARKED MAIN CUT OUT DAMAGED SECTION AND EF PURGE POINT ON END OF MAIN LINE SOAP TESTED OP 7 PSIG
22026231600 | 557 | EX | EMER - INSTALL 2'-4" PMMP | BRENDA SUE | A | 5460.0467 | 196.47 | -5263.5767 | -96% | 2 | 2 | 98.235 | INSTALLED 2' OF 4" PL MP TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 40 P SIG
22026231700 | 558 | EX | EMER - RETIRE 2'-4" PMMP | BRENDA SUE | A | 263.239 | 24.23 | -239.009 | -91% |  |  | 0 | RETIRED 2' OF 4" PL MP DUE TO LEAKAGE SOAP TESTED TO VERFY SHUTDOWN
22026232200 | 587 | EX | INSTALL SKID MOUNTED GMB | CENTER ST | F | 56170.7039 | 40259.26 | -15911.4439 | -28% |  |  | 0 | INSTALLED NEW SKID MOUNTED METER SETTING DASH 12-15-22
22026232300 | 588 | EX | RETIRE GMB SETTING | CENTER ST | F | 263.239 | 1984.01 | 1720.771 | 654% |  |  | 0 | INSTALLED NEW SKID MOUNT METER SETTING AND RETIRED OLD METER AND REGULATORS DASH 12-15-22
22026232700 | 588 | EX | RETIRE GMB W/22-9790457-00 | 3700 13TH ST | F | 545.7645 | 0 | -545.7645 | 100% |  |  | 0
22026233100 | 2000 | EX | INVESTIGATE ROW & RR PERMIT | CENTER ST |  | 4378 | 0 | -4378 | 100% |  |  | 0
22026234200 | 565 | EX | INSTALL 100'-6"PMMP S/L | 74 CENTER ST | B | 78909.8457 | 60246.05 | -18663.7957 | -24% | 120 |  | 0 | CJH JOE HADLEY REPLACED SL, TESTED SL AT 0106PSIG/0200HRS, OPEN CUT, SOAP TESTED FC/CAP AT OP, EXT CORR INSP, NO ANODE, WRAPPED EXPOSED MAIN, DS 12062022
22026234300 | 588 | EX | RETIRE GMB SETTING | 101 23RD ST | F | 725.239 | 0 | -725.239 | 100% |  |  | 0 | RETIRED GMB SETTING REMOVED METER BLIND PLATED SERVICE GAS NO LONGER NEEDED
22026235200 | 555 | EX | INSTALL 200'-2" PMIP | 65 BROWN LN | B | 38455.6638 | 11987.46 | -26468.2038 | -69% | 200 | 241 | 49.7405
22026235800 | 557 | EX | EMER - INSTALL 3'-4" PMMP | OLD LOCKANDDAM | A | 18999.7951 | 7089.71 | -11910.0851 | -63% | 2 | 3 | 2363.2367 | FOUND CLAMPS ON 4" PL MAIN CUT OUT AND INSTALLED NEW MAIN TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 15 PSIG
22026235900 | 558 | EX | EMER - RETIRE 3'-4" P-MP | OLD LOCKANDDAM | A | 117.5985 | 22647.66 | 22530.0615 | 19,158% |  |  | 0 | RETIRED 4" PL MAIN WITH CLAMPS ON IT TO INSTALL NEW
22026240200 | 557 | EX | EMER - INSTALL 100'-4" PMLP | 909 ASHLAND AV | A | 38890.2222 | 5141.88 | -33748.3422 | -87% | 100 | 93 | 55.289 | INSTALLED 93' OF PL AND ST TESTED 90 PSIG 1 HR SOAP TESTED WELD CAPS AND SSTEE CAPS 10" WC
22026240300 | 558 | EX | EMER - RETIRE 100'-4" BSLP | 909 ASHLAND AV | A | 129.6266 | 285.28 | 155.6534 | 120% |  |  | 0 | RETIRED 75' OF 4" BS DUE TO LEAKAGE
22026240400 | 560 | EX | PAPER ONLY - RETIRE BSIP MAIN | OLD BUCKLEY RD | B | 119.2135 | 0 | -119.2135 | 100% |  |  | 0
22026241300 | 557 | EX | EMER - INSTALL 5'-4" PMMP | 1173 STATE RT 1 | A | 10162.4624 | 1144.39 | -9018.0724 | -89% | 55 | 3 | 381.4633 | INSTALLED 3' OF 4" PL DUE TO LEAKAGE ON SERVICE TEE TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 11 PSIG
22026241400 | 558 | EX | EMER - RETIRE 5'-4" PMP | STATE RT 1 | A | 117.5985 | 91.78 | -25.8185 | -22% |  |  | 0 | RETIRE 4" MP TO DUE TO LEAKAGE ON SERVIEC TEE TO INSTALL NEW
22026244600 | 577 | EX | INSTALL BUILDING AND FENCE | OLD US 23 | F | 28935.3221 | 0 | -28935.3221 | 100% |  |  | 0 | INSTALLED COMM BUILDING AND FENCE DASH 3-17-22
22026245500 | 577 | EX | INSTALL REG STATION BUILDING | US23--ASHLAND OIL | F | 128388.6752 | 12285 | -116103.6752 | -90% |  |  | 0
23026246000 | 587 | EX | INSTALL M&R CRANE - MARATHON | US23--ASHLAND OIL | F | 36312.6752 | 14182.67 | -22130.0052 | -61% |  |  | 0
23026246200 | 585 | EX | INSTALL VRG - MIS FACILITY | US 60 | F | 449.3532 | 0 | -449.3532 | 100% |  |  | 0
23026246300 | 586 | EX | INSTALL VRG - RETIRE MIS FAC | US 60 | F | 132.4844 | 0 | -132.4844 | 100% |  |  | 0
23026246800 | 561 | EX | INSTALL 800'-4" PMMP | MONTGOMERY AV | B | 369832.3416 | 287158.53 | -82673.8116 | -22% | 800 | 409 | 702.0991
23026246900 | 562 | EX | RETIRE 1000'-4" P-MP | MONTGOMERY AV | B | 123.4477 | 0 | -123.4477 | 100% |  |  | 0
23026247100 | 557 | EX | EMER - INSTALL 9'-4" CSMP/PMP | ELWOOD | A | 14951.5544 | 5323.15 | -9628.4044 | -64% | 9 | 9 | 591.4611 | LOWERED MAIN DUE TO LEAKAGE AND 14" WATER LINE TESTED 90 PSIG 0005 MIN SOAP TESTED FINAL CONN OP 40 PSIG
23026247200 | 558 | EX | EMER - RETIRE 9'-4" CSMP | ELWOOD | A | 149.6969 | 806.29 | 656.5931 | 439% |  |  | 0 | RETIRED 9' OF 4" ST TO LOWER FOR 14" WATER MAIN SOAP TESTED OP TO VERIFY AD EQUATE SHUT DOWN 40 PSIG
23026247600 | 2000 | EX | KDMC - INVT. ROW/ STAKE ROW | MONTGOMERY AV |  | 7184 | 0 | -7184 | 100% |  |  | 0
23026248600 | 558 | EX | RETIRE 3'-3" PMLP | 22ND | A | 1635.0284 | 3012.93 | 1377.9016 | 84% |  |  | 0 | RETIRED 20' OF 3" PL MAIN DUE TO FACILITY DAMAGE SOAP TESTED OP 9.5" WC
23026249100 | 555 | EX | INSTALL 100'-2" PMMP | 15514 RICHLAND CT | A | 7008.1595 | 13611.51 | 6603.3505 | 94% | 100 | 128 | 106.3399 | INSTALLED NEW MAIN ON RICHLAND CT TESTED 90 PSIG 1 HR SOAP TESTED BRANCHING TEE CAP AND PURGE POINT CAP OP 14 PSIG
23026249200 | 588 | EX | GMB TO CAB CONVERSION | 23 HARRIS RD | F | 132.4844 | 858.55 | 726.0656 | 548% |  |  | 0 | CONVERTED FROM GMB TO CAB SGIORDANO
23026251100 | 587 | EX | INSTALL EC-350 UNIT | 15085 OLD US 23 CAT | F | 3195.3221 | 1808.88 | -1386.4421 | -43% |  |  | 0 | INSTALLED NEW EC350 DASH 1-24-23
23026251200 | 588 | EX | RETIRE PAPER BILLING CHART | LINE-B/OLD-US23 CAT | F | 131.2422 | 975.93 | 844.6878 | 644% |  |  | 0 | RETIRED CHART INSTALLED NEW EC350 DASH 1-24-23
23026251300 | 587 | EX | INSTALL EC 350 UNIT | 23< HARRIS RD | F | 7475.3221 | 8141.46 | 666.1379 | 9% |  |  | 0 | INSTALLED NEW EC350 TO REPLACE PAPER BILLING CHART
23026251400 | 588 | EX | RETIRE PAPER BILLING CHART | 23< HARRIS RD | F | 131.2422 | 870.82 | 739.5778 | 564% |  |  | 0 | RETIRE PAPER BILLING CHART
23026254200 | 584 | EX | RETIRE RECORDING GAUGE | 220 LOCK LN | F | 552.5683 | 107.1 | -445.4683 | -81% |  |  | 0 | CC 10596 RETIRE PAPER CHART SHANE G. 03012023
23026255800 | 2000 | EX | INVESTIGATE ROW / OBTAIN EASMT | ALLEY |  | 11694 | 0 | -11694 | 100% |  |  | 0
23026255900 | 2000 | EX | RESEARCH ROW/OBTAIN EASEMENT | 15514 RICHLAND CT |  | 7184 | 0 | -7184 | 100% |  |  | 0
23026256700 | 584 | EX | RETIRE PAPER GAUGE | 964 US 23 | F | 138.8485 | 756.49 | 617.6415 | 445% |  |  | 0 | CC 17512 REMOVED PAPER PRESSURE GAUGE
23026257200 | 909 | EX | INSTALL MIWI AND SUPER SOLAR | 516 3RD ST RR | F | 12042.2854 | 3080.61 | -8961.6754 | -74% |  |  | 0 | CC 41028
23026257300 | 584 | EX | RETIRE CHART | 516 3RD ST RR | F | 124.7348 | 386.09 | 261.3552 | 210% |  |  | 0
23026257500 | 909 | EX | INSTALL MIWI AND SUPER SOLAR | 1030 WINSLOW RD | F | 23732.2854 | 3917.88 | -19814.4054 | -83% |  |  | 0
23026257600 | 584 | EX | RETIRE PAPER CHAT | 1030 WINSLOW RD | F | 121.7239 | 575.02 | 453.2961 | 372% |  |  | 0
23026257700 | 909 | EX | INSTALL MIWI AND SUPER SOLAR | 78 ROSE STREET | F | 22126.2854 | 3552.01 | -18574.2754 | -84% |  |  | 0
23026257800 | 584 | EX | RETIRE PAPER CHART | 78 ROSE STREET | F | 121.7239 | 1141.91 | 1020.1861 | 838% |  |  | 0
23026258100 | 909 | EX | INSTALL MIWI AND SUPER SOLAR | 210 55TH ST | F | 20638.2854 | 4339.86 | -16298.4254 | -79% |  |  | 0 | CC 41992
23026258200 | 584 | EX | RETIRE PAPER CHART | 210 55TH ST | F | 121.7239 | 0 | -121.7239 | 100% |  |  | 0
23026258500 | 909 | EX | INSTALL ULTRASONIC METER | 1200 US ROUTE 23 | F | 47491.9621 | 51660.67 | 4168.7079 | 9% |  |  | 0 | CC# 47829
23026258600 | 557 | EX | EMER - INSTALL 5'-4" PMIP | 104 BELLEFONTE CR | A | 23135.0467 | 29274.5 | 6139.4533 | 27% | 5 | 3 | 9758.1667 | INSTALLED 3' OF 4" PL DUE TO BORE CREW BORING INTO MAIN TESTED 90 PSIG 1 HR
23026258700 | 558 | EX | EMER- RETIRE 5'-4" PMIP | BELLEFONTE ST | A | 137.555 | 21718.99 | 21581.435 | 15,689% |  |  | 0 | RETIRED 3' OF 4" IP DUE TO BORE CREW HITTING MAIN SOAP TESTED OP 7 PSIG TO VERIFY SQUEEZE OFF
23026258900 | 909 | EX | INSTALL MIWI AND SUPER SOLAR | PAUL COFFEY BV | F | 22126.2854 | 5852.27 | -16274.0154 | -74% |  |  | 0
23026259200 | 909 | EX | INSTALL MIWI AND SUPER SOLAR | 240 BUCKLEY RD | F | 21353.2854 | 4121.74 | -17231.5454 | -81% |  |  | 0 | CC 37280
23026259300 | 584 | EX | RETIRE PAPER CHART | 240 BUCKLEY RD | F | 121.7239 | 0 | -121.7239 | 100% |  |  | 0
23026259400 | 909 | EX | INSTALL MIWI AND SUPER SOLAR | 309 PIKE ST RR | F | 20638.2854 | 3579.71 | -17058.5754 | -83% |  |  | 0
23026259500 | 584 | EX | RETIRE PAPER CHART | 309 PIKE ST RR | F | 121.7239 | 347.11 | 225.3861 | 185% |  |  | 0
23026259800 | 909 | EX | INSTALL ERX W/SUPER SOLAR | JEFFERSON ST | F | 5058.9621 | 3465.31 | -1593.6521 | -32% |  |  | 0 | CC# 18720. 3/2/23 DSASH
23026259900 | 584 | EX | RETIRE PAPER CHART | JEFFERSON ST | F | 138.8485 | 277.39 | 138.5415 | 100% |  |  | 0 | CC# 18720. 3/2/23 DSASH CC# 18720
23026260000 | 909 | EX | INSTALL ERX W/SUPER SOLAR | 1271 RT 5 | F | 5058.9621 | 3193.7 | -1865.2621 | -37% |  |  | 0 | CC# 18341. 2/28/23 DSASH CC# 21913. P2P OK.
23026260100 | 584 | EX | RETIRE PAPER GAUGE | 1271 RT 5 | F | 138.8485 | 257.79 | 118.9415 | 86% |  |  | 0 | CC# 18341. 2/28/23 DSASH
23026260200 | 909 | EX | INSTALL ERX W/SUPER SOLAR | 1001 RIVERSIDE DR | F | 6314.9621 | 4114.48 | -2200.4821 | -35% |  |  | 0 | CC 17668 NOT ON SITE CAPITAL PACKET PAPERWORK NOT ONSITE. ISO UPDATES CC 21100 ANNUAL GAUGE INSP AND P2P WITH GAS CONTROL COMPLETE.
23026260300 | 584 | EX | RETIRE PAPER CHART | 1001 RIVERSIDE DR | F | 138.8485 | 564.75 | 425.9015 | 307% |  |  | 0 | CC 17668
23026260400 | 909 | EX | INSTALL ERX W/SUPER SOLAR | 2149 OLD US 23 | F | 6314.9621 | 3437.82 | -2877.1421 | -46% |  |  | 0 | CC 17834 NOT ON SITE. CAPITAL PACKET PAPERWORK NOT ON SITE ISO UPDATES CC 21100 ANNUAL GAUGE INSP AND P2P WITH GAS CONTROL COMPLETE
23026260500 | 584 | EX | RETIRE PAPER CHART | 2149 OLD US 23 | F | 138.8485 | 605.66 | 466.8115 | 336% |  |  | 0 | CC 17834
23026260900 | 909 | EX | INSTALL ERX W/SUPER SOLAR | LAUREL ST | F | 5458.9621 | 1872.11 | -3586.8521 | -66% |  |  | 0 | CC 20969 CC 24221 P2P OK WITH GC.
23026261000 | 584 | EX | RETIRE PAPER CHART | LAUREL ST | F | 138.8485 | 174.56 | 35.7115 | 26% |  |  | 0 | CC 20961
23026261200 | 909 | EX | INSTALL ULTRASONIC METER | US 60 | F | 47951.5304 | 57893.54 | 9942.0096 | 21% |  |  | 0
23026261700 | 909 | EX | INSTALL MIWI AND SUPER SOLAR | CATLETT CREEK ROAD | F | 21353.2854 | 3770.68 | -17582.6054 | -82% |  |  | 0
23026261800 | 584 | EX | RETIRE PAPER CHART | CATLETT CREEK ROAD | F | 121.7239 | 642.64 | 520.9161 | 428% |  |  | 0 | CC 37443
23026262200 | 557 | EX | EMER - INSTALL 4'-2" PMMP | US 60 | A | 2419.7892 | 15777.13 | 13357.3408 | 552% | 4 | 4 | 3944.2825 | INSTALLED 4' OF 2" PLASTIC MAIN. PRESSURE TESTED AT 90LBS FOR 1 HR.
23026262300 | 558 | EX | EMER - RETIRE 4'-2" PMMP | US 60 | A | 260.4446 | 242.84 | -17.6046 | -7% |  |  | 0 | REMOVED 4' OF DAMAGED 2" PLASTIC
23026262400 | 909 | CO | INSTALL RTU & INSTRUMENTATION | 624 BIGGS LN | F | 257150.5602 | 279231.64 | 22081.0798 | 9% |  |  | 0 | CC 27892 NOT ON SITE CONTRACTOR RESCHEDULED CC 44847 CC 45180 CC 51942 CC 52129 CC# 52432 NO CC NEEDED CC 53623 CC 53623 CC 53373 CC 53373
23026262500 | 910 | EX | RETIRE RTU & INSTRUMENTATION | 624 BIGGS LN | F | 117.7346 | 0 | -117.7346 | 100% |  |  | 0
23026262601 | 577 | EX | INSTALL CHAIN LINK FENCE | 624 BIGGS LN | F | 39848.4833 | 72669.9 | 32821.4167 | 82% |  |  | 0 | CC 44278 NOT ON SITE CC 53373 CC 53373 CC 57440 CC 58157
23026264500 | 557 | EX | EMER - INSTALL ~5'-4" PM/CSMP | MIDLAND TRAIL | A | 2069.4953 | 929.35 | -1140.1453 | -55% | 5 | 5 | 185.87
23026264600 | 558 | EX | EMER - RETIRE ~5'-4" CSMP | MIDLAND TRAIL | A | 67.4953 | 207.34 | 139.8447 | 207% |  |  | 0
23026265600 | 557 | EX | EMER - INSTALL 4'-6" PMIP | 508 OLD BUCKLEY RD | A | 12463.1003 | 19713.32 | 7250.2197 | 58% | 34 | 4 | 4928.33
23026265700 | 558 | EX | EMER - RETIRE 4'-6" P-IP | 508 OLD BUCKLEY RD | A | 391.4196 | 0 | -391.4196 | 100% |  |  | 0
23026266501 | 575 | EX | ACQUIRE EASEMENT | 624 BIGGS LN | F | 49332.6068 | 62373.74 | 13041.1332 | 26% |  |  | 0
23026269500 | 557 | EX | EMER - INSTALL 4'-2" PIP | WURTLAND | A | 7943.8116 | 2717.09 | -5226.7216 | -66% | 4 | 4 | 679.2725
23026269600 | 558 | EX | EMER - RETIRE 5'-2" PIP | WURTLAND | A | 134.4334 | 0 | -134.4334 | 100% |  |  | 0
23026270200 | 560 | EX | EMER - RETIRE 5'-2" PIP | 2210 SLOAN ST | A | 288.6068 | 0 | -288.6068 | 100% |  |  | 0 | REPLACED 5' SECTION OF 2" PMMP. TESTED MAIN AT 90 PSIG FOR 1 HOUR AND TEST WAS GOOD. TESTED 2X1 EF TEES AT 90 PSIG FOR 5 MINS AND SOAP TESTED THE CAPS AND DEAD ENDS AT OP FOR 5 MINS. ALL TEST ARE GOOD.
23026270300 | 559 | EX | EMER - INSTALL 2'-4" PMMP | 2503 CENTER ST | A | 9141.6411 | 526.5 | -8615.1411 | -94% | 2 | 2 | 263.25
23026270400 | 560 | EX | EMER - RETIRE 110'-4" P-MP | 2503 CENTER ST | A | 137.555 | 537.22 | 399.665 | 291% |  |  | 0 | RETIRED 110' OF 4" PL MP DUE TO BUILDING COLLAPSING TESTED CAP 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 38 PSIG
23026271400 | 557 | EX | EMER - INSTALL ~5'-2" PMMP | 3624 29TH ST | A | 5664.5366 | 7739.82 | 2075.2834 | 37% | 10 | 1 | 7739.82 | INSTALLED 1' OF 2" PL MP DUE TO DAMAGE TESTED 90 PSIG 1 HR SOAP TESTED FINA L CONN OP 40 PSIG
23026271500 | 558 | EX | EMER - RETIRE ~5'-2" PMMP | 3624 29TH ST | A | 114.3981 | 709.93 | 595.5319 | 521% |  |  | 0 | RETIRED 1" OF 2" PL MP DUE TO FACILITY DAMAGE SOAP TESTED TO VERIFY SQUEEZE OFF OP 40 PSIG
23026274400 | 2000 | EX | EN PS&I FOR VIRGINIA AVE SMRP | VIRGINIA | B | 27500 | 0 | -27500 | 100% |  |  | 0
23026275200 | 557 | EX | EMER - INSTALL 3'-2" PMIP | 31600 US 23 | A | 9765.5645 | 5562.78 | -4202.7845 | -43% | 3 | 3 | 1854.26 | INSTALLED 3' OF 2" MAIN DUE TO DAMAGE BY BORE CREW TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 5.5 PSIG
23026275300 | 558 | EX | EMER - RETIRE 3'-2" PIP | 31600 US 23 | A | 134.4334 | 235.76 | 101.3266 | 75% |  |  | 0 | RETIRED 3' OF 2" PL DUE TO BORE CREW HITTING MAIN TIEING CONDUIT TOGHETHER
23026277500 | 2000 | EX | INVESTIGATE R/W & EASEMENTS | GREENUP ST |  | 17751 | 0 | -17751 | 100% |  |  | 0
23026277600 | 557 | EX | INSTALL 595'-2"PMMP | HARRIS | B | 198539.3537 | 137119.9 | -61419.4537 | -31% | 595 | 704 | 194.7726
23026277700 | 558 | EX | RETIRE 2881'-12" BSMP | HARRIS | B | 139.1159 | 430.39 | 291.2741 | 209% |  |  | 0
23026277800 | 596 | EX | RETIRE RECTIFIER | HARRIS ST | F | 554.3418 | 2898.38 | 2344.0382 | 423% |  |  | 0 | METER DISCONNECT WITH AEP COMPLETED. ORDER PENDING RT CLEARED AND TEST STATIONS REMOVED THAT WERE EFFECTED DUE TO REMOVAL OF THIS RECTIFER. HARRIS REC FACILITY 411142 RETIRED WITH CAP JOB 23-0262778-00 / REMAINING RELATED TEST STATION FACILITIES MOVED TO MARSH HILL RECTIFIER 413988 IN BOOK R12 / 3 TEST STATIONS 281856 281857 & 281858 RETIRED WITH CAP JOB 23-0262777-00 / JMM
23026278100 | 588 | EX | RETIRE REG FAC | 5726 ROBERTS DR | F | 67.1159 | 0 | -67.1159 | 100% |  |  | 0 | JOB TO EXECUTE PAPERWORK ONLY RWILLIAMS 6-6-2023
23026278700 | 555 | EX | INSTALL 105'-2" PMMP | 120 KELLY LN | A | 17148.7846 | 9899.17 | -7249.6146 | -42% | 107 | 116 | 85.3377 | INSTALLED 116' OF 2" PL MP TESTED 90 PSIG 0005 MIN SOAP TESTED CAPS AND DEA D HEADS OP 17 PSG
23026279000 | 2000 | EX | INVESTIGATE ROAD R/W | CHESTNUT DR | B | 5432 | 0 | -5432 | 100% |  |  | 0
23026279400 | 2000 | EX | INVESTIGATE MAINS | WINCHESTER AV |  | 5109.367 | 0 | -5109.367 | 100% |  |  | 0
23026279500 | 561 | EX | INSTALL 339'-8" PMLP | 18TH ST | A | 126473.6122 | 110539.26 | -15934.3522 | -13% | 339 | 225 | 491.2856 | INSTALLED 218' OF 8" PLASTIC TESTED 105 PSIG 4 HOURS SOAP TESTED FINAL CONN OP 10" WC
23026279600 | 562 | EX | RETIRE 339'-8" BSLP | 18TH ST | A | 119.4953 | 1599.81 | 1480.3147 | 1,239% |  |  | 0 | RETIRED MAIN LINES PURGED AND SEALED SOAP TESTED 10" WC TO VERIFY SHUTDOWN
23026280200 | 558 | EX | RETIRE 18570'-2"-16" S&PMP | RIVA RIDGE | B | 113891.7734 | 111917.81 | -1973.9634 | -2% |  |  | 0 | IP 23175576300 2211 - REPAIR LEAK ON MAIN D200007
23026280300 | 560 | EX | RETIRE 1107'-2"&8" CS&PHHP | RIVA RIDGE RD | B | 14918.7734 | 2514.99 | -12403.7834 | -83% | 6 |  | 0
23026280600 | 586 | EX | RETIRE FENCE | RIVA RIDGE RD | F | 5554.3418 | 0 | -5554.3418 | 100% |  |  | 0
23026280700 | 584 | EX | RETIRE STATIONS R-1375 | RIVA RIDGE RD | F | 4462.367 | 1935.34 | -2527.027 | -57% |  |  | 0
23026283101 | 555 | CO | INSTALL 780'-2" PMMP | 191 FALLS CREEK DR | B | 96018.7749 | 71782.2 | -24236.5749 | -25% | 784 | 770 | 93.2236
23026283600 | 557 | EX | INSTALL LP FITTINGS | VIRGINIA AV | B | 11183.6093 | 9658.7 | -1524.9093 | -14% |  |  | 0
23026284800 | 557 | EX | EMER - INSTALL 40'-4" PMLP | 3412 WILLIS ST | A | 16339.4428 | 630.98 | -15708.4628 | -96% | 40 | 34 | 18.5582 | INSTALLED 34' OF 4" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 10" WC
23026284900 | 558 | EX | EMER - RETIRE 40'-4" BSLP | 3412 WILLIS ST | A | 139.1159 | 451.35 | 312.2341 | 224% |  |  | 0 | RETIRED 34' OF 4" BS MAIN DUE TO LEAKAGE SOAP TESTED OP TO VERIFY SHUTDOWN SOAP TESTED OP 10" WC
23026289300 | 557 | EX | INSTALL 7'-2"&6" PMLP | BLACKBURN | B | 141.4953 | 447.65 | 306.1547 | 216% |  | 6 | 74.6083
23026289500 | 596 | EX | RETIRE GROUND BED | US ROUTE 23 | F | 119.4953 | 0 | -119.4953 | 100% |  |  | 0
23026289600 | 2000 | EX | INVESTIGATE STATION PIPING | 2715 GREENBO BV |  | 21548.1209 | 0 | -21548.1209 | 100% |  |  | 0 | TWALKER/KY 09-26-24-M/R MEGA RULE ALL MATERIAL VERIFICATION WAS COMPLETED BY CAMPOS AND NOTHING TO REPLACE.
23026290100 | 557 | EX | EMER - 3'-3" PMIP | BERNITA | A | 2929.2518 | 5711.96 | 2782.7082 | 95% | 3 | 3 | 1903.9867 | INSTALLED 3' OF 2" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 5 PSIG
23026290200 | 558 | EX | EMER-RETIRE 3'-PIP | BERNITA | A | 119.4953 | 253 | 133.5047 | 112% |  |  | 0 | CUT OUT 3' OF 2" PL DUE TO HIT MAIN SOAP TESTED TO VERIFY SHUTDOWN AFTER SQUEEZE OP
23026291700 | 557 | EX | EMER - INSTALL 3'-4" PMIP | 5332 SKYLINE DR | A | 9351.5219 | 2485.01 | -6866.5119 | -73% | 23 | 3 | 828.3367 | INSTALLED 3' OF 4" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7 PSIG
23026291800 | 558 | EX | EMER - RETIRE 3'-4" PIP | 5332 SKYLINE DR | A | 119.4953 | 685.77 | 566.2747 | 474% |  |  | 0 | RETIRED 3' OF 4" PL DUE TO LEAK ON 4" SF COUPLING SOAP TESTED OP 7 PSIG TO VERIFY ADEQUATE SHUTDOWN
23026292100 | 2000 | EX | INVESTIGATE ENCHROACHMENT | W LITTLE GARNER RD |  | 1866 | 0 | -1866 | 100% |  |  | 0 | PER CONVERSATION WITH TONY AND AUTUMN, RELOCATION WAS AVOIDED, SO NO CAPITA L JO TO CHARGE. D.LEMONS 1/30/2024
23026292300 | 559 | EX | INSTALL 2" SS | 3308 ROBERTS DR | A | 15645.4681 | 1292.35 | -14353.1181 | -92% |  |  | 0 | INSTALED AND TESTED SS FITTING AT 90PSIG FOR 15 MINS
23026292400 | 560 | EX | RETIRE 154'-2" CSIP | 3308 ROBERTS DR | A | 119.4953 | 13487.05 | 13367.5547 | 11,187% |  |  | 0 | INSTALLED WELD CAP TO MAIN SOAP TESTED END CAP AT OP FOR 15 MINS
23026294200 | 2000 | EX | INVESTIGATE & MAP MAINS/SERV. | POWELL LN |  | 4565 | 0 | -4565 | 100% |  |  | 0 | PS&I CHARGED TO SERVICE LINE THAT WAS RELOCATED FOR SIDEWALK/STORM PROJECT. NO MAIN RELOCATION WAS NECESSARY, BUT SERVICES NEEDED GRADE SET TO CLEAR G RADING AND SEWER WORK. D.LEMONS 10/25/2023
23026294700 | 555 | EX | INSTALL 70'-2" PMIP | 7914 STATE RT 168 | A | 22819.9245 | 12372.22 | -10447.7045 | -46% | 72 | 74 | 167.1922 | INSTALLED 74' OF 2" PL TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN AND PURGE POINT CAP OP 8 PSIG
23026296600 | 2000 | EX | INVESTIGATE TAP LOCATION |  |  | 1716 | 0 | -1716 | 100% |  |  | 0
23026296700 | 555 | EX | INSTALL 165' OF 2" PMIP | 2114 BROOKE CR | A | 23912.4752 | 15685.08 | -8227.3952 | -34% | 165 | 152 | 103.1913 | INSTALLED 157' OF 2" IP MAIN TESTED 90 PSIG 1 HR SOAP TESTED PURGE POINT CAP AND SST CAP OP 7.5 PSIG
23026299800 | 566 | EX | PAPER ONLY SL RETIRE | 2236 MONTGOMERY AV | B | 122.9261 | 0 | -122.9261 | 100% |  |  | 0
23026299900 | 565 | EX | PAPER ONLY SL REPLACEMENT | 2236 MONTGOMERY AV | B | 145.9261 | 1201.76 | 1055.8339 | 724% |  |  | 0
23026300000 | 909 | EX | INSTALL NEW EQUIPMENT | 1403 FRENCH BROAD | F | 3973.8688 | 570.56 | -3403.3088 | -86% |  |  | 0
23026300100 | 2000 | EX | INVESTIGATE R/W LIMITS | RIVERSIDE DR | B | 8037 | 0 | -8037 | 100% |  |  | 0
23026300300 | 555 | EX | INSTALL 1810'-2" PMMP | TOWN HILL RD | B | 171679.8061 | 217275.5 | 45595.6939 | 27% | 1810 | 1686 | 128.8704
23026302600 | 2000 | EX | INVESTIGATE SETTING | 320 ELM ST |  | 489.7311 | 0 | -489.7311 | 100% |  |  | 0 | USED FOR INVESTIGATION AT STATION OF FITTINGS. DETERMINED JOB WAS NEEDED TO REPLACE COMPONENTS, SO UPDATING METER SETTING WAS CHOSEN TO ELLIMINATE OTH ER COMPLIANCE ISSUES AND OLDER STYLE DIAPHRAM METER. D.LEMONS 4/1/2024
23026305600 | 596 | EX | RETIRE RECTIFIER | 10325 MAYO TRAIL RD | F | 1995.4622 | 1384.83 | -610.6322 | -31% |  |  | 0 | AEP DISCONNECT AND SERVICE REMOVAL ORDER # 032-765-675 FURTHER WORK REQUIRED RECTIFIER RT VOIDED SENT TO CAPITAL CLOSEOUT FOR RETIREMENT RECTIFIER FAC 860778 RETIRED WITH CAP JOB 23-0263056-00
23026305700 | 596 | EX | RETIRE RECTIFIER | 10123 MAYO TRAIL RD | F | 1995.4622 | 2180.78 | 185.3178 | 9% |  |  | 0 | RT AND ALL FACILITIES TIED TO THIS PORTION OF RECTIFER HAVE BEEN RETIRED.. RECTIFER 860865 RETIRED WITH CAP JOB 23-0263057-00
23026306800 | 583 | EX | INSTALL METER RUN | 320 ELM ST | F | 89187.262 | 47050.46 | -42136.802 | -47% |  |  | 0 | CCC 94516 CCC 95365 SG 11/4/24 X 1109A
23026307000 | 586 | EX | RETIRE METAL BLDG | 4570 LOUISA RD | F | 124.9261 | 0 | -124.9261 | 100% |  |  | 0 | TWALKER/KY 12-1-23: THIS BUILDING AND REG STATION RETIRED ON 21-0261546-00.
23026308100 | 583 | EX | INSTALL NEW METER | 2149 OLD US 23 | F | 41682.6833 | 7400.08 | -34282.6033 | -82% |  |  | 0 | CCC 92257 NO CCC NEEDED. COMPLETING CAPITAL PAPERWORK. SG 10/30/24 1235P PER D.ASH NPRV NOT NEEDED SO IT WAS NOT ORDERED OR INSTALLED
24026316400 | 583 | EX | EMER-INSTALL CATALYTIC HEATER | 11433 MIDLAND TRAIL RD | F | 3661.3856 | 2159.35 | -1502.0356 | -41% |  |  | 0 | TWALKER/KY 02-27-24: CORRECTED JOB TO EMER STATUS, MP SYSTEM 32051028 IS SUPPLIED BY REG #1381 AND #1374...REG#1381 HAD TO BE SHUT IN FOR M&R WORK, WITH ONLY ONE REG STATION SUPPLIED MP SYSTEM REQUIRED A CAT HEATER DUE TO FREEZING ISSUE.
24026318800 | 909 | EX | ADD SOLAR BACKUP | 320 ELM ST | F | 11051.1928 | 9847.7 | -1203.4928 | -11% |  |  | 0 | CCC 88756 CCC 90158
24026318900 | 910 | EX | RETIRE COMPONENTS | 320 ELM ST | F | 160.3697 | 0 | -160.3697 | 100% |  |  | 0
24026319200 | 909 | EX | UPGRADE SCADA SYSTEM | 515 LACKEY AV RR | F | 11051.1928 | 9821.8 | -1229.3928 | -11% |  |  | 0 | CCC# 88928
24026319300 | 910 | EX | RETIRE SCADA COMPONENTS | 515 LACKEY AV RR | F | 160.3697 | 0 | -160.3697 | 100% |  |  | 0
24026319400 | 909 | EX | UPGRADE SCADA SYSTEM | 1418 CENTER ST RR | F | 11051.1928 | 11260.82 | 209.6272 | 2% |  |  | 0 | CCC# 89146
24026319500 | 910 | EX | RETIRE SCADA COMPONENTS | 1418 CENTER ST RR | F | 160.3697 | 23092 | 22931.6303 | 14,299% |  |  | 0
24026319800 | 909 | EX | UPGRADE SCADA SYSTEM | 100 CHESTNUT ST | F | 11051.1928 | 7392.38 | -3658.8128 | -33% |  |  | 0 | CCC# 89306
24026319900 | 910 | EX | RETIRE SCADA COMPONENTS | 100 CHESTNUT ST | F | 160.3697 | 0 | -160.3697 | 100% |  |  | 0
24026320000 | 909 | EX | INSTALL SOLAR BACK UP UNIT | 2674 PIQUA ST | F | 11051.1928 | 6749.45 | -4301.7428 | -39% |  |  | 0
24026320200 | 909 | EX | UPGRADE SCADA SYSTEM | 1108 HALBERT ST RR | F | 11051.1928 | 9127.38 | -1923.8128 | -17% |  |  | 0
24026320300 | 910 | EX | RETIRE SCADA COMPONENTS | 1108 HALBERT ST RR | F | 160.3697 | 1185.97 | 1025.6003 | 640% |  |  | 0
24026320500 | 909 | EX | INSTALL ULTRA SONIC METER | 12000 US 23 | F | 47090.3856 | 36964.47 | -10125.9156 | -22% |  |  | 0
24026320800 | 557 | EX | EMER - INSTALL 5'-3" PMIP | 235 KENTUCKY ST | A | 6546.5769 | 25129.82 | 18583.2431 | 284% | 5 | 4 | 6282.455 | INSTALLED 4' OF 3" PL IP MAIN TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7 PSIG
24026320900 | 558 | EX | EMER RETIRE 5'-3" PIP | 235 KENTUCKY ST | A | 160.3697 | 403.88 | 243.5103 | 152% |  |  | 0 | RETIRED 4' OF 3" PL DUE TO FAILED 3X1 EF ON MAIN SOAP TESED TO VERIFY SHUT DOWN OP 7 PSIG
24026322500 | 909 | EX | INSTALL MIWI W/ SOLAR | 900 ENGLAND LN | F | 29494.1928 | 18888.98 | -10605.2128 | -36% |  |  | 0 | CCC 88309 SG 9/11/24 250P CCC 93309 CCC 93309 CCC 93309 SG 11/1/24 250P CCC 93309 P2P COMPLETED. SG 11/4/24 240P
24026322600 | 910 | EX | REITRE FACILITIES | 900 ENGLAND LN | F | 160.3697 | 0 | -160.3697 | 100% |  |  | 0
24026323100 | 909 | CO | UPGRADE TO FULL TIME | 2254 29TH ST RR | F | 14026.1928 | 7625.67 | -6400.5228 | -46% |  |  | 0
24026323200 | 910 | EX | RETIRE FACILITIES | 2254 29TH ST RR | F | 160.3697 | 501.62 | 341.2503 | 213% |  |  | 0
24026323300 | 909 | CO | UPGRADE TO FULL TIME | 1820 WOODLAND AV | F | 14026.1928 | 7465.2 | -6560.9928 | -47% |  |  | 0
24026323400 | 910 | EX | RETIRE FACILITIES | 1820 WOODLAND AV | F | 160.3697 | 722.69 | 562.3203 | 351% |  |  | 0
24026323500 | 909 | CO | UPGRADE TO FULL TIME | 1210 PALMER ST | F | 14026.1928 | 7331.42 | -6694.7728 | -48% |  |  | 0
24026323600 | 910 | EX | RETIRE FACILITIES | 1210 PALMER ST | F | 160.3697 | 717.61 | 557.2403 | 347% |  |  | 0
24026323700 | 909 | CO | UPGRADE TO FULL TIME | 1900 29TH ST RR | F | 14026.1928 | 7820.77 | -6205.4228 | -44% |  |  | 0
24026323800 | 910 | EX | RETIRE FACILITIES | 1900 29TH ST RR | F | 160.3697 | 748.22 | 587.8503 | 367% |  |  | 0
24026324100 | 555 | EX | INSTALL 670'-2' PMIP | 137 OLYMPIC DR | A | 68828.4274 | 91180.5 | 22352.0726 | 32% | 679 | 704 | 129.5178 | INSTALLED 704' OF 2" PL IP AND 3' OF 2" ST TESTED 111 PSIG FOR 1 HR SOAP TE STED SST CAP AND PURGE POINT CAPS OP 7.5 PSIG
24026325200 | 583 | CO | INSTALL BYPASS VALVE | 490 FERGUSON RD | F | 30940.8061 | 23298.82 | -7641.9861 | -25% | 40 |  | 0 | CCC 73047 NO CCC NEEDED. NO CCC NEEDED. WORK BEING DONE AT GMB LOCATION.
24026325300 | 909 | EX | UPGRADE SCADA SYSTEM | 413 39TH ST | F | 10627.0487 | 9037.36 | -1589.6887 | -15% |  |  | 0 | CCC# 89894
24026325400 | 910 | EX | UPGRADE SCADA SYSTEM | 413 39TH ST | F | 121.4465 | 0 | -121.4465 | 100% |  |  | 0
24026325500 | 909 | EX | UPGRADE SCADA SYSTEM | 608 BELLEFONTE RD RR | F | 10627.0487 | 7316.43 | -3310.6187 | -31% |  |  | 0
24026325600 | 910 | EX | UPGRADE SCADA SYSTEM | 608 BELLEFONTE RD RR | F | 121.4465 | 563.53 | 442.0835 | 364% |  |  | 0
24026326800 | 909 | CO | INSTALL ELECTRINICS | 2802 CAMPBELL ST | F | 15644.0403 | 8703.66 | -6940.3803 | -44% |  |  | 0 | CCC 92181
24026326900 | 910 | EX | RETIRE ELECTRONICS | 2802 CAMPBELL ST | F | 118.4933 | 0 | -118.4933 | 100% |  |  | 0
24026327400 | 909 | EX | INSTALL ELECTRONICS | 318 33RD ST | F | 15644.0403 | 9042.76 | -6601.2803 | -42% |  |  | 0 | CCC 90038
24026327500 | 910 | EX | RETIRE ELECTRONICS | 318 33RD ST | F | 118.4933 | 0 | -118.4933 | 100% |  |  | 0
24026327600 | 909 | EX | INSTALL ELECTRONICS | 3441 DOUGLAS ST | F | 15644.0403 | 8257.47 | -7386.5703 | -47% |  |  | 0
24026327700 | 910 | EX | RETIRE ELECTRONICS | 3441 DOUGLAS ST | F | 118.4933 | 1025.99 | 907.4967 | 766% |  |  | 0
24026328000 | 909 | EX | INSTALL ELECTRONICS | 2925 NEWMAN ST RR | F | 15644.0403 | 7483.34 | -8160.7003 | -52% |  |  | 0
24026328100 | 910 | EX | RETIRE ELECTRONICS | 2925 NEWMAN ST RR | F | 118.4933 | 431.14 | 312.6467 | 264% |  |  | 0
24026328500 | 2000 | EX | MEGA RULE STATION VERIFICATION | 202 CAROLINE AV | B | 44868.72 | 0 | -44868.72 | 100% |  |  | 0 | TWALKER/KY 09-26-24-M/R MEGA RULE ALL MATERIAL VERIFICATION WAS COMPLETED BY CAMPOS AND NOTHING TO REPLACE.
24026328600 | 2000 | EX | MEGA RULE STATION VERIFICATION | OLD US 23 | B | 44868.72 | 0 | -44868.72 | 100% |  |  | 0 | TWALKER/KY 09-26-24-M/R MEGA RULE ALL MATERIAL VERIFICATION WAS COMPLETED BY CAMPOS AND NOTHING TO REPLACE.
24026329200 | 2000 | EX | INVESTIGATE STATION PIPING | LAUREL ST | A | 19419.0806 | 0 | -19419.0806 | 100% |  |  | 0 | TWALKER/KY 09-26-24-M/R MEGA RULE ALL MATERIAL VERIFICATION WAS COMPLETED BY CAMPOS AND NOTHING TO REPLACE.
24026333201 | 557 | EX | EMER - INSTALL 478'-4" PMLP | 2001 WILSHIRE BLVD | B | 106609.2647 | 205447.29 | 98838.0253 | 93% | 478 | 540 | 380.4579
24026333301 | 558 | EX | EMER - RETIRE 477'-4" CSLP | 2001 WILSHIRE BLVD | B | 112.4469 | 226.51 | 114.0631 | 101% |  |  | 0
24026335300 | 2000 | EX | INVESTIGATE STATION | 1030 WINSLOW RD | B | 44868.72 | 0 | -44868.72 | 100% |  |  | 0 | TWALKER/KY 09-26-24-M/R MEGA RULE ALL MATERIAL VERIFICATION WAS COMPLETED BY CAMPOS AND NOTHING TO REPLACE.
24026335800 | 583 | EX | EMER - INSTALL PF REGULATOR | 2510 CENTER ST RR | F | 48662.72 | 111967.23 | 63304.51 | 130% |  |  | 0 | TWALKER 08-29-24: JOB ORDER OVER RUN DUE TO LP OUTAGE AND LABOR TO RESTORE SERVICE ADDED $40,000 TO COST AND SEGA WAS $20,000 HIGHER THAN EST.
24026335900 | 584 | EX | EMER - RETIRE PF REGULATOR | 2510 CENTER ST RR | F | 121.4465 | 0 | -121.4465 | 100% |  |  | 0
24026337800 | 559 | EX | INSTALL 8" SS | PANOLA ST | B | 151.4465 | 2650.82 | 2499.3735 | 1,650% |  |  | 0
24026340600 | 557 | EX | INSTALL LP FITTINGS | HOUSTON ST | B | 5899.0487 | 0 | -5899.0487 | 100% |  |  | 0
24026341100 | 0001 | EX | DOCUMENT MAIN LINE RE-TEST | 2236 MONTGOMERY AV | B | 14275.1947 | 0 | -14275.1947 | 100% |  |  | 0 | CCC NOT NEEDED GMB MCR 5-16-24 2030 TWALKER/KY 05-20-24: SEE PRESSURE TEST INFORMATION IN WMS.DOCS FOR THIS PROJECT.
24026344300 | 557 | EX | EMER-INSTALL 6' OF 4" PMIP | 2892 MCNIPP DR | A | 14215.6055 | 20651.9 | 6436.2945 | 45% | 25 | 6 | 3441.9833
24026344400 | 558 | EX | EMER-RETIRE 6' OF 4" PAIP | 2892 MCNIPP DR | A | 139.7787 | 0 | -139.7787 | 100% |  |  | 0
24026347300 | 557 | EX | EMER - INSTALL 12'-3" PMIP | TANGLEWOOD | A | 21463.3624 | 52750.04 | 31286.6776 | 146% | 12 | 12 | 4395.8367 | FOUND 2-3X3 PAC CLALMPS LEAKING AND 2-3" BOLTED COUPLINGS ON MAIN CUT OUT A ND REPLACED 12' OF 3" PL MAIN TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 7 PSIG
24026347400 | 558 | EX | EMER - RETIRE 12'-3" PIP | TANGLEWOOD | A | 136.633 | 167.95 | 31.317 | 23% |  |  | 0 | CUT OUT 2 LEAKING 3X3 CLAMPS AND 2 3" BOLTED COUPLINGS SOAP TESTED TO VERIF Y SHUTDOWN ASFTER SQUEEZE
24026348900 | 561 | EX | INSTALL 70'-8" PMMP | GREENUP AV | B | 134812.2257 | 110389.69 | -24422.5357 | -18% | 70 | 119 | 927.6445
24026349000 | 562 | EX | RETIRE 70' OF 10"CSMP MAIN | GREENUP AV | B | 136.633 | 110 | -26.633 | -19% |  |  | 0
24026349500 | 557 | EX | INSTALL 40'-12" CSMP | 213 BELLEF PRIN RD | B | 141636.0949 | 237894.26 | 96258.1651 | 68% | 40 | 34 | 6996.89
24026349600 | 558 | EX | RETIRE ~40'-12" CSHP | 213 BELLEF PRIN RD | B | 136.633 | 220 | 83.367 | 61% |  |  | 0
24026349700 | 557 | EX | EMER INSTALL 2' OF 2" PMMP | 907 LINWOOD ST | A | 5242.4082 | 6054.03 | 811.6218 | 15% | 2 | 2 | 3027.015 | SOUTHERN OHIO TRENCHING HIT MISS MARKED 2" PL MP MAIN CUT OUT 2' OF MAIN AN D INSTALLED 2' TESTED 90 PSIG 1 HR SOAP TESTED FINAL CONN OP 40 PSIG
24026349800 | 558 | EX | EMER ABANDON 2' OF 2" PAMP | 907 LINWOOD ST | A | 139.7787 | 315.69 | 175.9113 | 126% |  |  | 0 | RETIRED 2'' OF 2" PL MP SOAP TESTED 40 PSIG TO VERFIY SQUEEZE OFF SHUTDOWN
24026354400 | 561 | EX | INSTALL 20'-4" PMLP | PROSPECT AV | B | 159.2637 | 287.45 | 128.1863 | 80% |  | 58 | 4.956
24026356500 | 557 | EX | EMER - INSTALL 2'-2" PMIP | 802 MONROE ST | A | 2544.1386 | 4865.71 | 2321.5714 | 91% | 2 | 2 | 2432.855 | INSTALLED 2' OF 2" P DUE TO FAC DAM. TESTED 90PSIG 1HR SOAP TESTED FC AT OP 7PSIG. CWHEELE
24026356600 | 558 | EX | EMER - RETIRE 2'-2" PIP | 802 MONROE ST | A | 124.2298 | 49.73 | -74.4998 | -60% |  |  | 0 | REITRED 2' OF 2" P MAIN DUE TO FAC DAM SOAP TESTED OP TO VERIFY ADEQUATE SQUEEZE. CWHEELE 9-4-2024
24026358700 | 555 | CO | INSTALL 100' OF 2" PMMP MLE | 1037 LIME ST | A | 21795.7838 | 24604.17 | 2808.3862 | 13% | 100 |  | 0
24026359401 | 555 | EX | INSTALL 200' OF 4" PMIP | 1226 FAIRWAY DR LT67 | B | 49205.4272 | 61986.14 | 12780.7128 | 26% | 250 | 154 | 402.5074
24026361400 | 555 | EX | INSTALL 100' OF 2" PMIP | 150 DOYLE LN | B | 24014.3917 | 28089.92 | 4075.5283 | 17% | 100 | 136 | 206.5435
24026362600 | 577 | CO | DOCUMENT RTU BUILDING | 624 BIGGS LN | F | 159.2637 | 0 | -159.2637 | 100% |  |  | 0
24026365300 | 557 | EX | EMER INSTALL 5" OF 4" PMLP | GREENBRIAR RD | A | 17482.6388 | 26234.06 | 8751.4212 | 50% | 5 | 2 | 13117.03 | INSTALLED NEW PL 4" DUE TO CRACKED SF JOINT ON MAIN TESTED 2' OF 4" PL 90 PSIG 0005 MIN SOAP TESTED FINAL CONN OP 10.5" WC
24026365400 | 558 | EX | EMER RETIRE 5" OF 4" PALP | GREENBRIAR RD | A | 76.7529 | 612.15 | 535.3971 | 698% |  |  | 0 | RETIRED 2' OF 4" PL ALDYL-A DUE TO CRACKED SF COUPLING ON MAIN SOAP TESTED OP 10.5" WC TO VERIFY SHUTDOWN
24026367000 | 557 | EX | EMER INSTALL 5'-2" PMMP | 1511 CHESTNUT DR | A | 7419.9991 | 7909.41 | 489.4109 | 7% | 5 | 5 | 1581.882
24026367100 | 558 | EX | EMER RETIRE 5'-2" PMMP | 1511 CHESTNUT DR | A | 137.4585 | 451.33 | 313.8715 | 228% |  |  | 0
24026367400 | 2000 | EX | INVESTIGATE MAINS | DIXON ST |  | 17947 | 0 | -17947 | 100% |  |  | 0
24026372800 | 909 | EX | INSTALL SOLAR BACKUP | SKYLINE DR | F | 9877.4639 | 8466.91 | -1410.5539 | -14% |  |  | 0 | CCC 107099 AJM 2/13/2025
24026373300 | 909 | CO | INSTALL SOLAR BACKUP UNIT | US23--ASHLAND OIL | F | 9877.4639 | 7710.91 | -2166.5539 | -22% |  |  | 0 | INSTALLED SOLAR BACKUP, CCC#108529, DS 02272025
24026373500 | 909 | EX | INSTALL SOLAR BACKUP UNIT | OLD US 23 | F | 9877.4639 | 7634.88 | -2242.5839 | -23% |  |  | 0 | CCC 107260 AJM 2/14/2025 12:46 PM
24026374100 | 909 | EX | INSTALL SOLAR BACKUP UNIT | 202 CAROLINE AV | F | 9877.4639 | 7964.76 | -1912.7039 | -19% |  |  | 0 | CC 107886 SG 2/21/25 130P
25026381500 | 558 | CO | EMER - RETIRE ~870'-3" PIP | WILDWOOD DR | A | 3411.7402 | 8256.1 | 4844.3598 | 142% |  |  | 0 | RETIRED 800' OF MAIN - SOAP TEST END CAP @ OP OK- BHB OK-ABHATFIE 3/14/25
25026381700 | 555 | EX | INSTALL 230' OF 2" PMIP | 524 SUNSET DR | B | 29656.6889 | 89700.18 | 60043.4911 | 202% | 230 | 348 | 257.7591
25026382400 | 909 | CO | INSTALL SCADA EQUIPMENT | 7124 US 23 | F | 20669 | 11519.85 | -9149.15 | -44% |  |  | 0
25026392800 | 560 | CO | RETIRE MP - PAPER ONLY | E PIKE ST | B | 160.2249 | 251.75 | 91.5251 | 57% |  |  | 0
25026404200 | 2000 | EX | INVESTIGATE R/WLONG ST | LONG ST |  | 4804 | 0 | -4804 | 100% |  |  | 0
25026411700 | 559 | CO | INSTALL SHORTSTOP TEE | PIKE ST | C | 2670.4144 | 0 | -2670.4144 | 100% |  |  | 0
18026837600 | 583 | EX | INST. FN 176 EXTRA LP OPP | W 4TH ST | F | 35378.1646 | 59791.79 | 24413.6254 | 69% | 60 |  | 0 | CONTROL SHEET 008281 PAID ON 04/23/20 THURSDAY TO COVER 04/24/20 FRIDAY CONTROL SHEET008307 PAID ON 04/30/20 THURSDAY TO COVER 05/01/20 FRIDAY NOT ON SITE GETTING PARTS FOR JOB CCC# 23134 CCC# 23265 CCC# 23459 CCC# 25857 REGULATORS INSTALLED BY WADE SHIMFESSEL ON 5/13/2021 EC350 INSTALLED BY WADE SHIMFESSEL ON 5/14/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/2021 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS *EXISTING Y STRAINER STRAINER GASKET NOT INSTALLED
18026837700 | 584 | EX | RET. FN 176 FOR EXTRA LP OPP | W 4TH ST | F | 53.9767 | 0 | -53.9767 | 100% |  |  | 0 | REGULATORS REPLACED BY WADE SHIMFESSEL ON 5/13/2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 7/7/2021 GCCC TICKET NOT REQUIRED ON 7/7/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK CFARIS
19026895200 | 558 | EX | RETIRE 2104' 2" P/BSLP | ROGERS | B | 103.581 | 100.78 | -2.801 | -3% |  |  | 0
19026895301 | 557 | EX | INSTALL 6060' 2" PMMP | DRYDEN | B | 549218.5288 | 815947.98 | 266729.4512 | 49% | 6080 | 6914 | 118.0139 | JOB ORDER CODED COMPLETE IN ERROR. WILL BE CARRY OVER INTO 2021. SPENDLE OVERRUN EXPLANATION: ADDITIONAL PIPE WAS ADDED LATE INTO PROJECT AND ADDITI ONAL LABOR HOURS CAUSED INCREASE IN SEGA AS WELL AS LATE PAVING COSTS THAT HIT THE PROJECT SBRADY 6/18/21
19026895400 | 558 | EX | RETIRE 5072' 2-4" IP | DRYDEN | B | 103.581 | 0 | -103.581 | 100% |  |  | 0
19026895600 | 558 | EX | RETIRE 1516' 2" BS/P/WILP | GERMANTOWN | B | 103.581 | 108.73 | 5.149 | 5% |  |  | 0
19026900900 | 584 | EX | RETIRE MP TO IP RUN S-1455 | W 2ND ST | F | 690.3419 | 152.33 | -538.0119 | -78% |  |  | 0 | MP TO IP RUN RETIRE ON 1/27/21 BY RYAN VANDERPOOL PAPERWORK DID NOT GET TURNED IN FOR COMPLETION STATION RETIREMENT FIELD VERIFIED ALONG WITH RETIREMENT DATE FROM THE STATION INSPECTION RECORD BY WADE SHIMFESSEL AND JOSH MARTIN ON 10/18/2021 RETIREMENT PAPERWORK COMPLETED BY CYNTHIA FARIS ON 10/25/2021 GCCC TICKET NOT REQUIRED ON 10/25/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK. SETTING BYPASS VALVE AND INLET SETTING VALVE NOT RETIRED THEY ARE TURNED OFF AND BLIND FLANGED CFARIS
19026901000 | 584 | EX | RETIRE STATION 1464 | KY 8 ON PRIVATE R/W | F | 690.3419 | 2654.56 | 1964.2181 | 285% |  |  | 0 | JOB CARRIED OVER UNTIL AFTER THE 1ST OF 2021 PAPERWORK COMPLETED BY CYNTHIA FARIS ON 2/16/2021 GCCC TICKET NOT REQUIRED ON 2/16/21 NOT AT STATION OFF SITE COMPLETING PAPERWORK 2/16/21 CFARIS
19026901100 | 584 | EX | RETIRE STATION 1481 | GERMANTOWN RD | F | 690.3419 | 2483.61 | 1793.2681 | 260% |  |  | 0 | JOB ON HOLD UNTIL AFTER THE 1ST OF 2021
19026901200 | 584 | EX | RETIRE STATION 1480 | KY435 | F | 690.3419 | 4464.65 | 3774.3081 | 547% |  |  | 0 | JOB WAS ON HOLD UNTIL AFTER THE 1ST OF 2021
19026908000 | 2000 | EX | OBTAIN ADD LAND RIGHTS 4 I&C | MAPLE LEAF RD |  | 5472 | 0 | -5472 | 100% |  |  | 0 | DISCOVERED BUILDING WAS INSTALLED ON 909 JO, SO PS&I WAS EXECUTED TO IT. D. LEMONS 1/6/2023
19026910400 | 575 | EX | MAYSVILLE LP AMRP EASEMENTS | 6500 GERMANTOWN RD | F | 14458 | 19743.69 | 5285.69 | 37% |  |  | 0
19026911600 | 595R | EX | INSTALL NEW RECTIFIER | STATE ROUTE 10 | A | 10181.0696 | 5775.31 | -4405.7596 | -43% |  |  | 0
19026911700 | 596 | EX | RETIRE RECTIFIER | ST. RT. 10 | F | 69.2529 | 0 | -69.2529 | 100% |  |  | 0
20026917000 | 2000 | EX | RESEARCH PROPERTY RIGHTS | MAPLE LEAF RD |  | 3967 | 0 | -3967 | 100% |  |  | 0
20026918301 | 909 | EX | INSTALL ELECTRONICS | MAPLE LEAF RD | F | 179105.9064 | 163427.04 | -15678.8664 | -9% |  |  | 0 | GCC# 13951 CCC TICKET #14135 TICKET# 15597 CCC# 49425 REPLACED PUCK IN TRANSMITTER W/NOLL COMPLETED PAPERWORK 12-22-21 JMARTIN
20026931100 | 587 | EX | UPGRADE ELECTRONICS | 207 MAIN ST | F | 3038 | 265.67 | -2772.33 | -91% |  |  | 0 | REPLACED EFC
20026938100 | 588 | EX | RETIRE ELECTRONICS | 207 MAIN ST | F | 73.3494 | 0 | -73.3494 | 100% |  |  | 0 | REPLACED EFC
20026942500 | 909 | EX | INSTALL I&C EQUIPMENT | MASON LEWIS RD | F | 16155.4774 | 8341.61 | -7813.8674 | -48% |  |  | 0 | ERX INSTALLED BY ACP AND WADE SHIMFESSEL PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/10/22
20026942600 | 584 | EX | RETIRE GAUGE | MASON LEWIS RD | F | 91.4991 | 0 | -91.4991 | 100% |  |  | 0 | GAUGE RETIRED AFTER ERX INSTALLED BY WADE SHIMFESSEL PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/10/2022
20026942900 | 909 | EX | INSTALL I&C EQUIPMENT | PRV R/W TCO LOT | F | 16155.4774 | 11090.78 | -5064.6974 | -31% |  |  | 0 | ERX INSTALLED BY ACP AND WADE SHIMFESSEL PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/10/22
20026943000 | 584 | EX | RETIRE GAUGE | PRV R/W TCO LOT | F | 91.4991 | 1496.7 | 1405.2009 | 1,536% |  |  | 0 | CCC# 49347 COMMISION ERX CCC# 50118 ERX INSTALLED AND GAUGE RETIRED BY WADE SHIMFESSEL PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/10/22
20026950100 | 2000 | EX | RESEARCH LAND RIGHTS | US68 |  | 15740 | 0 | -15740 | 100% |  |  | 0
20026950500 | 575 | EX | ACQUIRE LAND FOR STATION | US68 | F | 15620 | 13667.26 | -1952.74 | -13% |  |  | 0
20026962200 | 2000 | EX | RESEARCH LAND RIGHT/ ROW | CROSS COUNTRY | A | 18194 | 0 | -18194 | 100% |  |  | 0
20026973001 | 557 | EX | INSTALL 10,000--2" PMMP | CLARK | B | 2332285.9866 | 2896168.82 | 563882.8334 | 24% | 10649 | 10954 | 264.3937 | COST OVERRUN OF $378K DUE TO PROJECT SHUT DOWN AND RESTART OVER WINTER. PR OJECT REQUIRED ADDITIONAL RESOURCES THAT WERE NOT ESTIMATED. COST OVERUN O F $345K IN MATERIALS (PAVING), $124K IN CONTRACT AND $21K IN LABOR. THERE W AS A SAVINGS OF $213K IN OTHER DUE TO ORIGINAL PAVING ESTIMATE BEING CAPTUR ED THERE. THESE ADDITIONAL COSTS CAUSED INCREASE IN SEGA OF $97K. D.LEMONS 10/26/2022
20026973100 | 558 | EX | RETIRE 120'-4" BSMP | CLARK | B | 80.6441 | 1897.5 | 1816.8559 | 2,253% |  |  | 0
20026973200 | 558 | EX | RETIRE 10875' BS/CI LP | FOREST | B | 57.6441 | 142.7 | 85.0559 | 148% |  |  | 0
20026973300 | 2000 | EX | INVESTIGATE AEASEMENTS |  |  | 13472 | 0 | -13472 | 100% |  |  | 0
20026973400 | 584 | EX | RETIRE STATION R-1452 | REYNOLDS DR | F | 1281.7771 | 114.18 | -1167.5971 | -91% |  |  | 0 | CCC# 68859 CCC# 68859 RETIRED REGSTATION PER AMRP PROJECT JMARTIN
20026973500 | 584 | EX | RETIRE STATION R-1458 | CARNATION STATION-1458 | F | 1281.7771 | 1295 | 13.2229 | 1% |  |  | 0
20026973600 | 2000 | EX | OBTAIN CSX VAL MAPS | MAPLE PARKWAY | B | 4000 | 0 | -4000 | 100% |  |  | 0
20026973700 | 557 | EX | INSTALL 6150'-4" PMLP | 4TH | B | 2202632.8927 | 2832541.47 | 629908.5773 | 29% | 5671 | 6687 | 423.5893 | ODOR READS TOOK AT 128 E 3RD ST, MAYSVILLE,KY - WITH SN-16040105 12/17- .6@10:40 - 12/18 .5@16:30 - 12/19 .6@11:30 - 12/20 .5@ 16:29 - 12/21 .5@17:12 - 12/22 .5@16:45 - 12/23 .6@12:27 - TJETT 12/23/21 LEVEL 2 BUDGET VARIANCE COMPLETED AND FILED IN WMSDOCS. D.LEMONS 10/3/2022
20026973800 | 558 | EX | RETIRE 6801'-4' CILP | 4TH | B | 107.2796 | 1501.61 | 1394.3304 | 1,300% |  |  | 0
20026974100 | 558 | EX | RETIRE 385'- 3" & 4" | 4TH | B | 8962.6172 | 2639.76 | -6322.8572 | -71% |  |  | 0
20026975000 | 555 | EX | INSTALL 150'-2" PMIP | 2223 MEADOW RIDGE DR | A | 12346.2686 | 12825.26 | 478.9914 | 4% | 150 | 244 | 52.5625
20026982100 | 555 | EX | INSTALL 800'-2" PMIP | 725 CLARKS RUN RD MIDDLE | B | 47914.5682 | 69244.93 | 21330.3618 | 45% | 800 | 892 | 77.6288
20026992100 | 584 | EX | RETIRE STATION | BUGLE AL | F | 3400.2343 | 0 | -3400.2343 | 100% |  |  | 0 | RETIRED REGULATOR STATION JMARTIN
21026111600 | 577 | EX | INSTALL FENCE | MAPLE LEAF RD | F | 2231 | 21225.79 | 18994.79 | 851% |  |  | 0 | CCC# 79626 MONITOR FOR FENCE INSTALL. JMARTIN 9-2-22 CCC# 79759 MONITOR FOR FENCE INSTALL
21026118000 | 559 | EX | INSTALL 4" SS | W 4TH ST | B | 29193.606 | 13617.82 | -15575.786 | -53% |  |  | 0 | 4"SHORTSTOP INSTALLET BY RLA TESTED AND TAPPED BYCOMPANY 90 PSIG 15 MIN TEST NITROGN AS MEDIUM
21026127000 | 557 | EX | INSTALL 8021'-2"&4" PMIP | CIRCLE | B | 1234240.1163 | 2281682.81 | 1047442.6937 | 85% | 8021 | 8100 | 281.6892
21026127100 | 558 | EX | RETIRE 9400'-2"&4" BS&CS | CIRCLE | B | 67.799 | 1334.61 | 1266.811 | 1,868% |  |  | 0
21026127200 | 557 | EX | INSTALL 2200'-2"&4" PMMP | LEXINGTON | B | 433097.159 | 570820.34 | 137723.181 | 32% | 2211 | 1678 | 340.179 | COST OVERRUN DUE TO PAVING ESTIMATED IN CONTRACT, BUT CAPTURED IN MISC MATE RIALS WITH A DIFFERENCE OF $32,000. SOME ADDITIOANL MATERIALS WERE REQUIRE D THAT WERE NOT ESTIMATED FOR $6,000. SEGA ALSO INCREASED FOR ADDITIONAL $1 8,000. D.LEMONS 1/31/2023 ADDITIONAL $56,000 TRANSFERED FROM RETIREMENT JO THAT WAS ASSOCIATED WITH A DDITIONAL PAVING. D. LEMONS 2/23/2023
21026127300 | 558 | EX | RETIRE 2100'-2"&4" BSMP |  | B | 75.9523 | 0 | -75.9523 | 100% |  |  | 0
21026127400 | 557 | EX | INSTALL 1900'-2"&4" PMIP |  | B | 236888.6644 | 479284.77 | 242396.1056 | 102% | 1901 | 1978 | 242.3078 | OVERRUN EXPLANATION LOADED INTO WMSDOCS. D.LEMONS 2/1/2023
21026127500 | 558 | EX | RETIRE 1071'-3"&4" WIIP |  | B | 75.9523 | 0 | -75.9523 | 100% |  |  | 0
21026127600 | 558 | EX | RETIRE 4700'-4" BSLP |  | B | 67.1085 | 0 | -67.1085 | 100% |  |  | 0
21026134500 | 561 | EX | INSTALL 1537'-2"PMIP | KENNEDY CREEK RD | B | 208782.1462 | 332303.55 | 123521.4038 | 59% | 1539 | 1562 | 212.7423 | SEE PROJECT WORKSPACE 21-81540 FOR PROJECT OVERRUN EXPLANATION. D.LEMONS 10 /26/2022
21026134600 | 562 | EX | RETIRE 1053'-2" CSIP | KENNEDY CREEK RD | B | 109.7476 | 0 | -109.7476 | 100% |  |  | 0
21026134700 | 2000 | EX | INVESTIGATE MAINS | KENNEDY CREEK RD |  | 21179 | 0 | -21179 | 100% |  |  | 0 | CORP PERMIT RECIEVED ALONG WITH EASEMENTS PER CHRIS DAVIS. D. LEMONS 3/24/2 022
21026138600 | 2000 | EX | INVESTIGATE EASEMENT | LEXINGTON PK | B | 26241 | 0 | -26241 | 100% |  |  | 0 | CCC# 53392 MEET WITH ATLAS ONSITE AT STATION FOR BUILDING SAMPLES
21026139000 | 2000 | EX | DESIGN COSTS | KY 546 |  | 20000 | 0 | -20000 | 100% |  |  | 0
21026139300 | 584 | EX | RETIRE STATION R-1455 | W 2ND ST | F | 1061.1136 | 0 | -1061.1136 | 100% |  |  | 0 | RETIRED REG STATION R1455 W 2ND ST MAYSVILLE JMARTIN 10-4-22
21026139400 | 586 | EX | REMOVE BUILDING FOR R-1455 | W 2ND ST | F | 117.5985 | 3989.86 | 3872.2615 | 3,293% |  |  | 0 | BUILDING REMOVED AND CLEANED UP BY PLANT. JMULLINS 1-18-23
21026145800 | 583 | EX | REPLACE VALVES ON HP-MP REG | KY 546 | F | 14136.4861 | 33552.7 | 19416.2139 | 137% | 19 |  | 0 | CCC# 73837 CCC# 74028 CCC# 74317 REPLACED INLET, OUTLET, AND BOTH BYPASS VLVS ON STATION. JMARTIN 7/20/22
21026145900 | 584 | EX | RETIRE 4 VALVES ON REG STATION | KY 546 | F | 600.4497 | 1355.49 | 755.0403 | 126% |  |  | 0 | INSTALLED TEMPORARY REG SETTING REPLACED ALL FOUR SETTING VALVES JMARTIN 07 -20-2022
21026154100 | 2000 | EX | OBTAIN EASEMENT | CLARKS RUN RD | B | 7970 | 0 | -7970 | 100% |  |  | 0 | EASEMENT OBTAINED FOR NEW MAIN INSTALATION AND STAKED. D.LEMONS 10/24/2022
21026994200 | 566 | EX | RETIRE 3" SERVICE | 322 LIMESTONE ST | B | 98.6196 | 0 | -98.6196 | 100% |  |  | 0
22026159400 | 566 | EX | RETIRE S/L | 636 FOREST AV | A | 3024.4273 | 2030.55 | -993.8773 | -33% |  |  | 0
22026162700 | 575 | EX | OBTAIN EASEMENT | KY HWY 10 | F | 3693.7476 | 3309.48 | -384.2676 | -10% |  |  | 0 | COPR PERMIT AND EASEMENT OBTAINED PER CHRIS DAVIS. D. LEMONS 3/24/2022
22026165100 | 555 | EX | INSTALL 300'-2" PMIP | 1079 SMITH TERRACE | A | 29167.1057 | 34102.05 | 4934.9443 | 17% | 300 | 250 | 136.4082
22026170300 | 2000 | EX | SURVEY ENCROACHMENT | 4R7.3/7252276K/WAS Z3 | B | 5000 | 0 | -5000 | 100% |  |  | 0
22026171800 | 557 | EX | INSTALL 3178'-2" PMIP | 4TH | B | 663052.9501 | 830935.96 | 167883.0099 | 25% | 3228 | 2949 | 281.7687
22026171900 | 558 | EX | RETIRE ~3325'-2" BS,CS & P | 4TH | B | 83.4538 | 0 | -83.4538 | 100% |  |  | 0
22026185400 | 909 | EX | EXCHANGE ELECTRONIC COMPONENTS | ROUTE 10 | F | 5480.5156 | 1456 | -4024.5156 | -73% |  |  | 0 | JMARTIN REMOVED OLD ERX AND INSTALLED NEW MIWI 350 5-17-2022
22026185500 | 910 | EX | RETIRE COMPONENTS | ROUTE 10 | F | 124.5156 | 715.54 | 591.0244 | 475% |  |  | 0 | CCC# 67011 NOT ABLE TO COMP AT THIS TIME, HAS OLDER ERX AND NEED MORE PARTS. JMARTIN 5-16-22 CCC# 67183 REPLACE ERX WITH NEW MIWI 350. JMARTIN
22026185600 | 909 | EX | EXCHANGE ELECTRONIC COMPONENTS | US68 | F | 6006.2549 | 644.24 | -5362.0149 | -89% |  |  | 0 | CCC# 70942 INSTALL NEW MIWI 350, P2P W/GAS CONTROL OK, JMARTIN 6-20-22
22026185700 | 910 | EX | RETIRE ELECTRONIC COMPONENTS | US68 | F | 124.5156 | 93.74 | -30.7756 | -25% |  |  | 0 | CCC# 70942 RETIRE ERX AND REPLACE WITH MIWI 350, JMARTIN 6-20-22
22026187000 | 909 | EX | EXCHANGE ELECTRONIC COMPONENTS | 4TH ST | F | 4357.5409 | 1100.73 | -3256.8109 | -75% |  |  | 0 | CCC# 67356 REPLACE ERX WITH NEW MIWI 350, P2P OK, JMARTIN CCC# 67669 WORKED TO FIX COMM ISSUE WITH MIWI. CCC# 67669
22026187100 | 910 | EX | RETIRE ELECTRONIC COMPONENTS | 4TH ST | F | 124.5156 | 0 | -124.5156 | 100% |  |  | 0 | RETIRED OLD ERX JMARTIN 5/18/2022
22026187400 | 909 | EX | EXCHANGE ELECTRONIC COMPONENTS | KY10 | F | 4773.0565 | 1016.56 | -3756.4965 | -79% |  |  | 0 | CCC# 67055 INSTALL NEW MIWI 350, P2P OK, JMARTIN CCC# 67183
22026187500 | 910 | EX | RETIRE ELECTRONIC COMPONENTS | KY10 | F | 124.5156 | 0 | -124.5156 | 100% |  |  | 0
22026187600 | 909 | EX | REPLACE ELECTRONIC COMPONENTS | 1241 WALTON PK | F | 5349.5438 | 31865.96 | 26516.4162 | 496% |  |  | 0 | CCC# 67613 REPLACED ERX WITH NEW MIWI 350. P2P OK, JMARTIN CCC# 67613
22026187700 | 910 | EX | RETIRE ELECTRONIC COMPONENTS | 1241 WALTON PK | F | 124.5156 | 39.46 | -85.0556 | -68% |  |  | 0 | CCC# 67613 RETIRE ERX JMARTIN
22026195800 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | KY 546 | F | 4801.1928 | 5580.46 | 779.2672 | 16% |  |  | 0 | CCC# 79192 INSTALL NEW MIWI 350, P2P COMP. JMARTIN 8-30-22
22026195900 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | KY 546 | F | 124.8731 | 69.23 | -55.6431 | -45% |  |  | 0 | CCC# 79192 INSTALL NEW MIWI 350, P2P COMP. JMARTIN 8-30-22 RETIRED OLD ERX
22026204100 | 586 | EX | RETIRE BUILDING | CARNATION STATION-1458 | F | 76.9137 | 0 | -76.9137 | 100% |  |  | 0 | BUILDING DEMOLISHED BY CONTRACTORS
22026204400 | 586 | EX | RETIRE BUILDING | REYNOLDS DR | F | 76.9137 | 0 | -76.9137 | 100% |  |  | 0 | BUILDING DEMOLISHED BY CONTRACTOR
22026205000 | 910 | EX | RETIRE ERX | MAPLE LEAF RD | F | 78.4365 | 0 | -78.4365 | 100% |  |  | 0 | COMPLETED PAPERWORK 12-22-21 JMARTIN
22026206200 | 557 | EX | INSTALL 33'-2" PMIP | RT 62 | B | 82983.2827 | 37112.14 | -45871.1427 | -55% | 41 | 19 | 1953.2705 | COST UNDERRUN DUE TO PROJECT BEING SIMPLIFIED AFTER START OF CONSTRUCTION. $2000 IN MATERIALS RETURNED AND NOT USED, $26000 IN CONTRACT ESTIMATED BUT NOT USED. ADDITIONAL SAVINGS IN OTHER AND SEGA CATAGORIA ASSOCIATED WITH LO WER COSTS. D. LEMONS 2/23/2023
22026206300 | 558 | EX | RETIRE 22'-4" WIIP | RT 62 | B | 83.4538 | 3252.3 | 3168.8462 | 3,797% |  |  | 0
22026208800 | 2000 | EX | GERMANTOWN-INV EASEMENTS | 1241 WALTON PK |  | 5000 | 0 | -5000 | 100% |  |  | 0
22026209201 | 586 | EX | RETIRE BUILDING FOR R-1451 | BUGLE AL | F | 4594.5704 | 3422.43 | -1172.1404 | -26% |  |  | 0
22026222500 | 557 | EX | EMER - INSTALL 5'-6" PMMP | 206 E 3RD ST | A | 5662.1316 | 5673.45 | 11.3184 | 0% | 3 | 3 | 1891.15
22026222600 | 558 | EX | EMER - RETIRE 5'-6" PMMP | 206 E 3RD ST | A | 74.3089 | 0 | -74.3089 | 100% |  |  | 0
23026254100 | 584 | EX | RETIRE PRESSURE GAUGE | US 68 | F | 552.5683 | 72.46 | -480.1083 | -87% |  |  | 0 | CCC# 10600 RETIRED PRESSURE CHART. JMARTIN 2-3-23
23026256800 | 584 | EX | RETIRE PAPER GAUGE | S HILL CITY RD | F | 138.8485 | 43.28 | -95.5685 | -69% |  |  | 0 | CCC# 10600 RETIRE PRESSURE CHART, JMARTIN 3-1-23
23026257900 | 909 | EX | INSTALL MIWI AND SUPER SOLAR | MAPLE DR | F | 22482.2854 | 1494.37 | -20987.9154 | -93% |  |  | 0 | CCC# 36022 INSTALL NEW MIWI 350. JMARTIN JHOBBS 7-5-23 CCC#36022
23026258000 | 584 | EX | RETIRE PAPER CHART | MAPLE DR | F | 121.7239 | 555.95 | 434.2261 | 357% |  |  | 0 | CCC# 36022 RETIRED PAPER CHART. JMARTIN JHOBBS 7-5-23 CCC# 36022
23026258300 | 583 | EX | INSTALL VRG CONTROLLER | MAPLE LEAF RD | F | 16195.69 | 41605.07 | 25409.38 | 157% |  |  | 0 | CCC#94028 VAC TRUCK WAS A NO SHOW CCC# 94512 W/VAC TRUCK CCC#94691 WELDED UP THE TAPS CCC#94691 WELDED TAP TEES ON FOR VRGS NOT ONSITE ORDER IS NOT MINE NOT NEEDED CCC#97247 TOOK OUT OLD CONTROLERS AND INSTALLED NEW VRG CONTROLER J HOBBS J BRADFORD 1700 11-18 24 CCC#97247 FINISH UP BACK FILLING 11-19-24 J HOBBS 1150
23026258400 | 584 | EX | RETIRE BRISTOL CONTROL UNIT | MAPLE LEAF RD | F | 138.8485 | 600.77 | 461.9215 | 333% |  |  | 0 | NO TICKET NEEDED HAD TO FIND PARTS 11-15-2023 J HOBBS 1559
23026284700 | 2000 | EX | INVESTIGATE CONFLICT | AA HWY |  | 12154 | 0 | -12154 | 100% |  |  | 0 | LAND SERVICES COMPLETED AND PROJECT RELEASED FOR CONSTRUCTION. D.LEMONS 6/1 7/2024
23026286900 | 583 | EX | HIGHLAND HEIGHTS BREAK METER | 3020 HIGHLAND DR | F | 103097.3193 | 40214.72 | -62882.5993 | -61% |  |  | 0 | CCC 88243 NO TICKET NEED. HAD TO TURN IN PAPER WORK OFF SIGHT 9-20-24
23026287300 | 561 | EX | INSTALL 121'-4" CSMP | ALGONQUIN DR E | B | 153650.3163 | 188332.63 | 34682.3137 | 23% | 131 | 188 | 1001.7693
23026287400 | 562 | EX | RETIRE 98'-4" CSMP | ALGONQUIN DR E | B | 136.633 | 0 | -136.633 | 100% |  |  | 0
23026302500 | 584 | EX | RETIRE PAPER GAUGE | 3020 HIGHLAND DR | F | 989.8688 | 994.29 | 4.4212 | 0% |  |  | 0 | CCC# 50771 MONITOR FOR TC
24026324200 | 909 | EX | UPGRADE TO FULL TIME | W 2ND ST | F | 10901.0487 | 8739.85 | -2161.1987 | -20% |  |  | 0 | CCC#83588 CCC# 83763 INSTALL SOLAR PANEL AND SWITCH TO CONTINUOUS POLL. JMARTIN 8-7-24
24026324300 | 910 | EX | UPGRADE TO FULL TIME | W 2ND ST | F | 121.4465 | 92.55 | -28.8965 | -24% |  |  | 0 | CCC# 83763 INSTALLING SOLAR TO MAKE CONTINUOUS POLL, JMARTIN 8-7-24
24026326600 | 909 | EX | UPGRADE TO FULL TIME | 128 W 4TH ST | F | 10901.0487 | 16219.76 | 5318.7113 | 49% |  |  | 0 | CCC#83806 CCC 83806 CCC# 83806 INSTALL SOLAR FOR CONTINUOUS POLL, JMARTIN 8-7-24
24026326700 | 910 | EX | UPGRADE TO FULL TIME | W 4TH ST | F | 121.4465 | 142.43 | 20.9835 | 17% |  |  | 0 | CCC# 83806 INSTALL SOLAR FOR CONTINUOUS POLL, JMARTIN 8-7-24
24026351600 | 557 | EX | EMER - INSTALL 2'-2" PMMP | 203 E 2ND ST | A | 5505.7838 | 2939.49 | -2566.2938 | -47% | 2 | 2 | 1469.745
24026351700 | 558 | EX | EMER - RETIRE 2'-2" PMP | 203 E 2ND ST | A | 136.633 | 0 | -136.633 | 100% |  |  | 0
24026352400 | 2000 | EX | INVESTIGATE AND MAP MAINS | CSX PROPERTY |  | 8250 | 0 | -8250 | 100% |  |  | 0 | PENDING CAPITAL JO.
24026352800 | 557 | EX | INSTALL SS FITTING | MAIN ST | A | 24859.1129 | 5512.14 | -19346.9729 | -78% |  |  | 0
24026352900 | 558 | EX | RETIRE 4'-3"&4"CSMP | MAIN ST | A | 136.633 | 2114.27 | 1977.637 | 1,447% |  |  | 0
24026357400 | 561 | EX | INSTALL 275'-3" CSMP | RIVER DR | B | 87056.0137 | 104472.75 | 17416.7363 | 20% | 275 | 292 | 357.7834
24026357500 | 562 | EX | RETIRE 265'-3" CSMP | RIVER DR | B | 124.2298 | 0 | -124.2298 | 100% |  |  | 0
24026366400 | 555 | EX | INSTALL ~390'-2" PMIP | EVERGREEN LN LT1 | A | 64432.6111 | 44902.44 | -19530.1711 | -30% | 375 | 532 | 84.4031
24026373600 | 909 | EX | INSTALL SOLAR BACKUP UNIT | MAPLE LEAF RD | F | 9877.4639 | 7104.24 | -2773.2239 | -28% |  |  | 0 | CCC# 107389. DSASH 2/17/25 1330
18026751600 | 2000 | EX | INVEST RECTIFIER SITE & EASE | US 23 & 960 | B | 5000 | 0 | -5000 | 100% |  |  | 0
18026761400 | 909 | EX | INSTALL BULLHORN RMU | 98 OLD JOHNS CREEK RD | F | 3922.4303 | 2699.78 | -1222.6503 | -31% |  |  | 0 | RMU WAS INSTALLED ON 09/30/2021 BY TIM SWARTS. SYSTEM SERIAL # IS 132395. -OSS
18026763900 | 2000 | EX | ACQUIRE LAND RIGHTS | DUDLEY DR | B | 4572 | 0 | -4572 | 100% |  |  | 0
18026764000 | 2000 | EX | ACQUIRE LAND RIGHTS | US23 UPPER HAROLD 1419 | B | 4572 | 0 | -4572 | 100% |  |  | 0
18026764100 | 2000 | EX | ACQUIRE LAND RIGHTS | LOWER HAROLD 1418 | B | 4572 | 0 | -4572 | 100% |  |  | 0
18026770000 | 588 | EX | RETIRE CHART | 608 SR80 | F | 1613.3811 | 3621.11 | 2007.7289 | 124% |  |  | 0 | RETIRED MANUAL CHART INSTALLED NEW EC350
18026770100 | 588 | EX | RETIRE CHART | 200 PURPOSE RD | F | 1613.3811 | 0 | -1613.3811 | 100% |  |  | 0 | RETIRED PAPER CHART MRYAN 07-07-2022
18026847000 | 583 | EX | INSTALL CATALYTIC HEATER | 8 SAWMILL RD | F | 3926.2882 | 3779.78 | -146.5082 | -4% |  |  | 0 | CC# 49296. 12/21/21 DSASH NO CC# NEEDED, DID NOT GO ON SITE. 12/22/21 DSASH GMB NO CC NEEDED RETIRED OLD CATALYTIC HEATER INSTALLED NEW CATALYTIC HEATER MRAYN 7-8-22
18026847100 | 584 | EX | RETIRE CATALYTIC HEATER | 8 SAWMILL RD | F | 77.1956 | 426.13 | 348.9344 | 452% |  |  | 0 | RETIRED OLD CATALYTIC HEATER INSTALLED NEW CATALYTIC HEATER MRYAN 7-8-2022
18026847200 | 583 | EX | INSTALL CATALYTIC HEATER | SR 292 LOVELY 1414 | F | 3926.2882 | 3110.02 | -816.2682 | -21% |  |  | 0 | RETIRED OLD CATALYTIC HEATER AND INSTALLED NEW CATALYTIC HEATER MRYAN 7-8-2022
18026847300 | 584 | EX | RETIRE CATALYTIC HEATER | SR 292 LOVELY 1414 | F | 77.1956 | 313.52 | 236.3244 | 306% |  |  | 0 | RETIRED CATALYTIC HEATER INSTALLED NEW CATALYTIC HEATER MRYAN 7-8-2022
19026850400 | 573 | EX | INSTALL ODORIZATION | SR 1428 | F | 6839.1611 | 5241.78 | -1597.3811 | -23% |  |  | 0
19026867802 | 559 | CO | INSTALL 376'-4" PMIP | SR 40 | B | 112969.7187 | 262651.39 | 149681.6713 | 132% | 396 | 350 | 750.4325
19026867900 | 560 | EX | RETIRE 396'-3" P&CS | SR 40 | B | 79.9756 | 48.51 | -31.4656 | -39% |  |  | 0
19026875300 | 587 | EX | INSTALL ODORIZER | 100 LAKE RD | F | 1300.1611 | 9263.2 | 7963.0389 | 612% |  |  | 0 | INSTALLED ODORIZER BOTTLE JMULLINS 9-30-22
19026875400 | 587 | EX | INSTALL ODORIZER | SR 3 JOHNS CREEK 1434 | F | 1300.1611 | 1315.89 | 15.7289 | 1% |  |  | 0 | INSTALLED FARM TAP ODORIZER BOTTLE JMULLINS 9-30-22
19026884700 | 2000 | EX | PS&I HWY PERMIT 572 SR899 R | 572 SR899 |  | 1641 | 0 | -1641 | 100% |  |  | 0
20026926200 | 587 | EX | INSTALL NETWORK UPGRADE | 2000 CENTRAL AV | F | 3150 | 853.47 | -2296.53 | -73% |  |  | 0 | SUPER SOLAR KIT AND RV50 INSTALLED BY NOLL DAVIS AND ACP PAPERWORK COMPLETED BY CYNTHIA FARIS ON 1/12/22
20026926400 | 587 | EX | INSTALL NETWORK UPGRADE | 400 E US23 | F | 3150 | 7131.29 | 3981.29 | 126% |  |  | 0 | GMB NO CC NEEDED GMB NO CC NEEDED NO CC NEEDED--GMB NO CC NEEDED GMB INSTALLED SOAR,BATTERY,AND MODEM PAPERWORK DONE BY J.MULLINS
20026926600 | 587 | EX | INSTALL NETWORK UPGRADE | JARRELL FORK | F | 3150 | 6560.17 | 3410.17 | 108% |  |  | 0 | NO CC NEEDED GMB INSTALLED NEW SUPER SOLAR KIT MRYAN 8-29-22
20026944400 | 2000 | EX | INVESTIGATE AND RESEARCH | PURPOSE DR |  | 49576 | 0 | -49576 | 100% |  |  | 0
20026946700 | 2000 | EX | BASE MAPPING FOR LOVELY AMRP | 1ST ST | B | 1710 | 0 | -1710 | 100% |  |  | 0
20026980000 | 557 | EX | INSTALL 675' - 2"/4" PMLP | SR 40 | B | 148515.2952 | 186497.16 | 37981.8648 | 26% | 735 | 298 | 625.8294 | DUE TO WEATHER CONDITION ON STATE ROAD UNABLE TO MAKE COMMIT DATE OVERRUN EXPLANATION: ALL OPEN CUT WAS ESTIMATED, BUT 108 FEET OF DIRECTIONA L BORE WAS USED. ADDITIONALLY, APPROXIMATELY 4 TIMES AS MUCH FLAGGING WAS R EQUIRED THAN ESTIMATED. OVERHEADS INCREASED $10,500 DUE TO THESE OVERAGES.
20026980100 | 558 | EX | RETIRE 622' - 2" BSLP | SR 40 | B | 103.8156 | 647.77 | 543.9544 | 524% |  |  | 0
20026991200 | 586 | EX | RETIRE BUILDING | SR194 PHYLLIS 1430 | F | 107.2796 | 0 | -107.2796 | 100% |  |  | 0 | THIS IS PAPER ONLY JOB BUILDING WAS TORN DOWN MANY YEARS AGO THIS JOB IS TO CORRECT CKY RECORDS ONLY FIELD VERIFIED BY CKY ENGINEERING
21026100300 | 557 | EX | EMER INS ~15'-2"/3" PMIP/CSIP | 5000 ELEMENTARY DR | A | 15461.5913 | 13138.1 | -2323.4913 | -15% | 80 | 20 | 656.905 | 3" C.S. MAIN PULLED LOOSE FROM 4 BOLT COUPLING DUE TO STRESS ON MAIN FROM EXPOSURE DOWN STREAM. TAPPED & STOPPED 3" C.S. REPLACED LEAKING SECTION WITH 3" P 20' PRESSURE TEST 90 PSIG 1HR PURGED MAIN LINE, RESTORED SERVICE.
21026100400 | 558 | EX | EMER RETIRE ~5'-3" CSIP | 5000 ELEMENTARY DR | A | 1147.7777 | 1505.21 | 357.4323 | 31% |  |  | 0 | 3" CS MAIN PULLED LOOSE FROM 4 BOLT COUPLING DUE TO STRESS ON MAIN FROM EXPOSURE DOWN STREAM. TAPPED & STOP 3" CS MAIN REPLACED LEAKING SECTION WITH 3" P 20' PRESSURE TEST 90PSIG FOR 1 HR. PURGED MAIN & RESTORED SERVICE
21026121900 | 555 | EX | INSTALL 100'-2" PMIP | 14 2ND ST FOX BTM | B | 26223.5353 | 30760.67 | 4537.1347 | 17% | 100 | 115 | 267.4841
21026131400 | 559 | EX | INSTALL 300'-2" PMIP | MAIN ST | B | 139158.4326 | 158500.46 | 19342.0274 | 14% | 300 | 300 | 528.3349
21026131500 | 560 | EX | RETIRE 300'-2" PMIP | MAIN ST | B | 88.8156 | 39.34 | -49.4756 | -56% |  |  | 0
21026131600 | 2000 | EX | INVESTIGATE MAINS | MAIN ST | B | 34568 | 0 | -34568 | 100% |  |  | 0 | PS&I COMPLETED PRIOR TO CAPITAL JO BEING COMPLETED. D.LEMONS 11/12/2021
21026136300 | 557 | EX | INSTALL 37'-2"/3" PMMP/CSMP | 7 BLAIRTOWN RD | A | 33826.5433 | 14615 | -19211.5433 | -57% | 37 | 20 | 730.75 | INSTALLED NEW 030 CS AND PE MAIN. TEST @ 90# FOR 1 HR, NO LEAKS. PURGED INT O SERVICE. STOP OFF AND REMOVED OLD MAIN. 3" WELD CAPS & 2" PE CAP SOAP TES T, NO LEAKS. WRAPPED MAIN. SWING TIES & EM BALLS. J HOWARD 9-20-21
21026136400 | 558 | EX | RETIRE 29'-2"/3" CSMP/PMMP | 7 BLAIRTOWN RD | A | 826.7837 | 83.24 | -743.5437 | -90% |  |  | 0 | LEAK ON END OF STEEL MECH COMP END CAP. INSTALLED NEW 030 & 020 ST AND PE M L, TESTED AT 90# FOR 1 HR. SOAP TEST 030 AND 020 CAPS, NO LEAKS. BAR BANKS, NGF. INSTALLED ANODE, WRAPPED MAIN. J HOWARD 9-13-21
21026142800 | 555 | EX | INSTALL 475'-4" PMLP | 122 BOARDWALK ST | B | 59783.3635 | 138313.25 | 78529.8865 | 131% | 350 | 462 | 299.3793 | TTOY-9/20/22: OVERRUN LEVEL 2 VARIANCE EXPLANATION IN WMSDOCS
21026146701 | 559 | EX | INSTALL 100'-2" PMIP | 89 COWTOWN RD | B | 40630.8922 | 6197.36 | -34433.5322 | -85% | 100 | 101 | 61.36 | VAPIERCE (03/27/23); JOB OVER RUN DUE TO CONTRACT CHARGES ASSOCIATED TO EMERGENCY JOB ORDER 22-0262152-00 EMER-KY FLOODING 2022. $29,900 IN ESTIMATED CONTRACT COSTS AND $0 BOOKED TO THIS JOB ORDER, ALL CONTRACT COSTS WERE CHARGED TO EMER-KY FLOODING 2000 JO. MOST LABOR COSTS WERE ALSO BOOKED UNDER THE EMER JOB ORDER. CONSTRUCTION WAS UNAWARE THIS PLANNED PROJECT OVERLAPPED WITH EMER WORK.
21026149200 | 2000 | EX | INVESTIGATE R/W & LAND RIGHTS | 122 BOARDWALK ST | B | 9790 | 0 | -9790 | 100% |  |  | 0
21026151700 | 2000 | EX | ENE DESIGN STATION OUTLET VLV | 29320 KY 292 |  | 20000 | 0 | -20000 | 100% |  |  | 0
21026994400 | 557 | EX | EMER- INSTALL 5'-2" PMIP | RAILROAD | A | 7281.2724 | 5176.12 | -2105.1524 | -29% | 1 | 6 | 862.6867 | INSTALLED 6' NEW 020 MDPE ML. TESTED AT 90# 20 MINS. WELD-IN TRANSITIONS. S OAP TEST TIE IN. PURGED AT EOM. SWING TIES AND ELEC MARKERS. J HOWARD 1-13- 21
21026994500 | 558 | EX | EMER- RETIRE 5'-2" BSIP | RAILROAD | A | 239.0145 | 1169.82 | 930.8055 | 389% |  |  | 0 | INSTALLED 2 020 TDW SS. TAP AND STOP ML. NO UPSTREAM PRESSURE LOSS. REMOVED AND ABANDONED 6' SECTION OF 020 S ML FOR INSTALL OF 020 MDPE. J HOWARD 1-1 1-21
21026997600 | 557 | EX | INSTALL 20'-2" PMIP | BEVINS ST | B | 28869.525 | 25490.16 | -3379.365 | -12% | 19 | 12 | 2124.18
21026997700 | 558 | EX | RETIRE 15'-2" BSIP | BEVINS ST | B | 88.4533 | 95.92 | 7.4667 | 8% |  |  | 0
22026158200 | 555 | EX | INSTALL 100'-2" PMMP | 71 PENNINGTON DR | B | 26700.5988 | 22688.28 | -4012.3188 | -15% | 100 | 95 | 238.824
22026164600 | 557 | EX | EMER - INSTALL 220'-2" PMIP | 1200 E HWY 550 | B | 49188.5426 | 49083.09 | -105.4526 | 0% | 220 | 289 | 169.8377
22026164700 | 558 | EX | EMER - RETIRE 20'-4" CSIP | 1200 E HWY 550 | B | 109.7476 | 140.47 | 30.7224 | 28% |  |  | 0
22026174700 | 557 | EX | EMER- INSTALL 82'-4" PMIP/CSIP | 44 SARAH EVERAGE RD | A | 94519.5369 | 85702.82 | -8816.7169 | -9% | 55 | 82 | 1045.1563 | REPAIRED LEAK ON MAIN BY REPLACING A SECTION OF BARE STEEL MAIN WITH 4" PLA STIC TESTED 105 PSIG FOR 1 HOUR WITH ELECTRONIC KUHLMAN GAUGE SERIAL NO 101 09154 3/8/22 REFER TO 2211 JOB ORDER# 22-9840666-00
22026174800 | 558 | EX | EMER- RETIRE 76'-4" BSIP | 44 SARAH EVERAGE RD | A | 0 | 0 | 0 | 0% |  |  | 0
22026175100 | 559 | EX | INSTALL 3" OUTLET VALVE | HWY 119 | B | 40477.7168 | 44613.77 | 4136.0532 | 10% | 15 | 14 | 3186.6979
22026175200 | 560 | EX | RETIRE ~10' - 3" CSHP | HWY 119 | B | 593 | 257.25 | -335.75 | -57% |  |  | 0
22026179500 | 557 | EX | EMER - INSTALL 5'-2" PMIP | FLOYD | A | 5401.378 | 2346.49 | -3054.888 | -57% | 5 | 5 | 469.298
22026179600 | 558 | EX | EMER - RETIRE 5'-2" P-IP | FLOYD | A | 238.1994 | 0 | -238.1994 | 100% |  |  | 0
22026189100 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | SR40 LOWER BEAUTY 1411 | F | 4745.0565 | 2559.49 | -2185.5665 | -46% |  |  | 0 | CC # 70264 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-29-2022
22026189200 | 910 | EX | RETIRE ELECTRONIC EQUIPMENT | SR40 LOWER BEAUTY 1411 | F | 124.5156 | 213.04 | 88.5244 | 71% |  |  | 0 | CC # 70264 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-29-2022
22026189300 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | R40 UPPER BEAUTY 1412 | F | 4745.0565 | 487.15 | -4257.9065 | -90% |  |  | 0 | CC# 70358 RETIRED BOTH ERX'S INSTALLED NEW MIWI350 MRYAN 6-14-2022
22026189400 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | R40 UPPER BEAUTY 1412 | F | 124.5156 | 243.32 | 118.8044 | 95% |  |  | 0 | CC # 70358 RETIRED OLD ERX'S INSTALLED NEW MIWI350 MRYAN 6-14-2022
22026189500 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | LOWER BETSY LAYNE 1416 | F | 4745.0565 | 292.29 | -4452.7665 | -94% |  |  | 0 | CC # 70566 RETIRED OLD ERX INSTALLED NEW HONEYWELL MIWI350 MRYAN 6-15-2022
22026189600 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | LOWER BETSY LAYNE 1416 | F | 124.5156 | 91.82 | -32.6956 | -26% |  |  | 0 | CC # 70566 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 06-15-2022
22026189700 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | STORE HOLLOW RD 1417 | F | 4745.0565 | 91.91 | -4653.1465 | -98% |  |  | 0 | CC # 70497 RETIRED OLD ERX INSTALLED NEW MIW350 MRYAN 06-15-2022
22026189800 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | STORE HOLLOW RD 1417 | F | 124.5156 | 213.04 | 88.5244 | 71% |  |  | 0 | CC # 70497 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-15-2022
22026189900 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | WARFIELD SR40 1413 | F | 4745.0565 | 275.74 | -4469.3165 | -94% |  |  | 0 | CC # 72215 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6/30/2022
22026190000 | 910 | EX | RETIRED ELECTRONICS EQUIPMENT | WARFIELD SR40 1413 | F | 124.5156 | 61.53 | -62.9856 | -51% |  |  | 0 | CC # 72215 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6/30/2022
22026191100 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | US 119 1433 | F | 4801.1928 | 1925.69 | -2875.5028 | -60% |  |  | 0 | CC # 71822 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-27-2022
22026191200 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | US 119 1433 | F | 124.8731 | 229.57 | 104.6969 | 84% |  |  | 0 | CC # 71822 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-27-2022
22026191500 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | SR899 1429 | F | 4801.1928 | 1457.43 | -3343.7628 | -70% |  |  | 0 | UPGRADED ERX TO MIWI
22026191600 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | SR899 1429 | F | 124.8731 | 447.49 | 322.6169 | 258% |  |  | 0 | CC # 73221 UPGRADDED ERX TO MIWI
22026192700 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | VIRGINIA AVE 1425 | F | 4801.1928 | 780.12 | -4021.0728 | -84% |  |  | 0 | CC # 71922 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-28-2022
22026192800 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | VIRGINIA AVE 1425 | F | 124.8731 | 82.66 | -42.2131 | -34% |  |  | 0 | CC # 71984 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-28-2022
22026193200 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | SR292 | F | 4801.1928 | 271.17 | -4530.0228 | -94% |  |  | 0 | CC # 71922 RETIRED OLD ERX INSTALLED NEW MIWI 350 MRYAN 6/28/2022
22026193300 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | SR292 | F | 124.8731 | 156.09 | 31.2169 | 25% |  |  | 0 | CC # 71922 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6/28/2022
22026193400 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | US23 BLAIRTOWN 1420 | F | 4801.1928 | 1938.82 | -2862.3728 | -60% |  |  | 0 | CC # 75237 NO CC NOT ONSITE PAPERWORK NO CC NEEDED UPGRADDED ERX TO MIWI JMULLINS
22026193500 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | US23 BLAIRTOWN 1420 | F | 124.8731 | 22.08 | -102.7931 | -82% |  |  | 0 | CC # 75237
22026193600 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | MIDDLE FORK RD. | F | 4801.1928 | 1911.78 | -2889.4128 | -60% |  |  | 0 | CC # 3865 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 10-18-22
22026193700 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | MIDDLE FORK RD. | F | 124.8731 | 217.55 | 92.6769 | 74% |  |  | 0 | CC # 3865 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 10-18-22
22026193800 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | SR 550 LEBURN 1424 | F | 4801.1928 | 1577.79 | -3223.4028 | -67% |  |  | 0 | CC # 73511
22026193900 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | SR 550 LEBURN 1424 | F | 124.8731 | 235.52 | 110.6469 | 89% |  |  | 0 | CC # 73511 UPGRADED TO MIWI JOSH MULLINS
22026194000 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | PRATT HOLLOW 1423 | F | 4801.1928 | 1673.13 | -3128.0628 | -65% |  |  | 0 | CC # 73511 UPGRADED FROM ERX TO MIWI JOSH MULLINS
22026194100 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | PRATT HOLLOW 1423 | F | 124.8731 | 230.5 | 105.6269 | 85% |  |  | 0 | CC # 73511
22026194200 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | HIGH & PERRY ST 1422 | F | 4801.1928 | 1788.47 | -3012.7228 | -63% |  |  | 0 | CC # 73334
22026194300 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | HIGH & PERRY ST 1422 | F | 124.8731 | 470.99 | 346.1169 | 277% |  |  | 0 | CC # 73334 UPDATTED ERX TO MIWI 07-13-22 J. MULLINS
22026194400 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | SR 292 LOVELY 1414 | F | 4801.1928 | 356.51 | -4444.6828 | -93% |  |  | 0 | CC # 72268 RETIRED OLD ERX INSTALLED NEW MIWI350 MRYAN 6-30-2022
22026194500 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | SR 292 LOVELY 1414 | F | 124.8731 | 1.84 | -123.0331 | -99% |  |  | 0 | CC # 72268 RETIRED OLD ERX INSTALLED NEW MIWI 350 MRYAN 6-30-2022
22026196000 | 909 | EX | EXCHANGE ELECTRONIC EQUIPMENT | SR 1428 | F | 4801.1928 | 6078.6 | 1277.4072 | 27% |  |  | 0 | CC # 75237 RETIRED OLD ERX AND INSTALLED NEW HONEYWELL MIWI350 MRYAN 7-27-2022
22026196100 | 910 | EX | RETIRED ELECTRONIC EQUIPMENT | SR 1428 | F | 124.8731 | 232.52 | 107.6469 | 86% |  |  | 0 | CC # 75237 RETIRED OLD ERX INSTALLED NEW HONEY WELL MIWI350 MATT RYAN 7-27-2022
22026208500 | 2000 | EX | S WILLIAMSON-INV EASEMENTS | US 119 1433 |  | 5000 | 0 | -5000 | 100% |  |  | 0
22026209100 | 588 | EX | RETIRE METER | 100 LAKE RD | F | 136.5602 | 1187.88 | 1051.3198 | 770% |  |  | 0 | NO CC NEEDED---GMB ACCOUNT MCR 10-6-23 1600 METER READY TO BE REMOVED INLET OUTLET BLIND FLNGD
22026215200 | 2000 | EX | EMER-KY FLOODING 2022 |  | A | 50000 | 0 | -50000 | 100% |  |  | 0
22026216500 | 559 | EX | EMER-INSTALL 2"/4" POLY VALVES |  | B | 298130.9642 | 433396.83 | 135265.8658 | 45% | 11 | 10 | 43339.683 | COMPLETED OVERRUN EXPLANATION FORM LOADED INTO WMSDOCS JO WORKSPACE. D.LEMO NS 2/24/2023
22026216600 | 560 | EX | EMER-RETIRE 7'-2"/4" PMIP/CSIP |  | B | 83.4538 | 0 | -83.4538 | 100% |  |  | 0
22026216700 | 559 | EX | EMER - INSTALL 456'-4" CS/PMIP | PRATT HOLLOW | B | 50625 | 85192.39 | 34567.39 | 68% | 454 | 533 | 159.8356
22026216801 | 560 | EX | EMER-RETIRE 130'-4" CS/BS/PIP | PRATT HOLLOW | B | 132.427 | 439.01 | 306.583 | 232% |  |  | 0
22026218600 | 583 | EX | INSTALL NEW 1ST CUT REGULATOR | US23 UPPER HAROLD 1419 | F | 2521.2589 | 3338.51 | 817.2511 | 32% |  |  | 0 | NOT ONSITE NO CC NEEDED GETTING MATERIAL/BUILDING REG PREPING FOR JOB MCR CC # 51243 INSTALLD NEW 1ST CUT REG DUE TO CORROSION MCR 11-6-23 1445 CC # 51776 ISTALLD TUBING ANF PAINTED SETTIN FIELD WORK COMPLETE
22026218700 | 584 | EX | RETIRE 1ST CUT REGULATOR | US23 UPPER HAROLD 1419 | F | 84.9152 | 1644.86 | 1559.9448 | 1,837% |  |  | 0 | CC # 51243 REMOVED OLD FIRST CUT REG MCR 11-6-23 1030
22026218900 | 587 | CO | INSTALL NEW METER | 100 LAKE RD | F | 6441.3422 | 17499.51 | 11058.1678 | 172% |  |  | 0 | CCC NOT NEEDED--GMB MCR 6-18-24 1500
22026241900 | 561 | EX | INSTALL 249'-2" PMIP | E MAIN ST | B | 81974.2921 | 101153.64 | 19179.3479 | 23% | 269 | 284 | 356.1748
22026242000 | 562 | EX | RETIRE 135'-3" BSIP | E MAIN ST | B | 117.5985 | 139.7 | 22.1015 | 19% |  |  | 0
22026242100 | 2000 | EX | INVESTIGATE MAINS | E MAIN ST | B | 6298 | 0 | -6298 | 100% |  |  | 0
23026256300 | 555 | EX | INSTALL 130'-2" PMIP | 40 2ND ST | B | 38002.449 | 19141.35 | -18861.099 | -50% | 130 | 129 | 148.3826
23026261300 | 909 | EX | INSTALL MIWI AND SUPER SOLAR | LOWER HAROLD 1418 | F | 26706.2854 | 4877.76 | -21828.5254 | -82% |  |  | 0 | CC # 36552 INSTALLD MIWI NO CC NOT ONSITE--PAPER WORK
23026261400 | 584 | EX | RETIRE PAPER CHART | LOWER HAROLD 1418 | F | 121.7239 | 0 | -121.7239 | 100% |  |  | 0
23026261500 | 909 | EX | INSTALL MIWI AND SUPER SOLAR | US23 UPPER HAROLD 1419 | F | 26706.2854 | 4069.95 | -22636.3354 | -85% |  |  | 0 | CC # 36725 NO CC NEEDED---GMB ACCOUNT NOT ON SITE NO CC NEEDED---PAPERWORK OFF SITE CC # 40724
23026261600 | 584 | EX | RETIRE PAPER CHART | US23 UPPER HAROLD 1419 | F | 121.7239 | 388.77 | 267.0461 | 219% |  |  | 0 | CC # 36725
23026265300 | 573 | EX | INSTALL PILOT REGULATORS | SR899 1429 | F | 7328.1838 | 9398.99 | 2070.8062 | 28% |  |  | 0
23026274600 | 559 | EX | EMER - INSTALL 5'-2" PMIP | 143 RAILROAD CR | B | 11073.0623 | 2867.86 | -8205.2023 | -74% | 5 | 3 | 955.9533
23026274700 | 560 | EX | EMER - INSTALL 5'-2" PM | 143 RAILROAD CR | B | 116.0664 | 0 | -116.0664 | 100% |  |  | 0
23026275800 | 587 | EX | INSTALL NEW BATTERY/EQUIPMENT | JARRELL FORK | F | 2819.6093 | 135.94 | -2683.6693 | -95% |  |  | 0
23026275900 | 588 | EX | RETIRE BATTERY FACILITY | JARRELL FORK | F | 139.1159 | 0 | -139.1159 | 100% |  |  | 0
23026276200 | 2000 | EX | INVESTIGATE MAINS | KY RT 122 | B | 7761 | 0 | -7761 | 100% |  |  | 0 | RESEARCH COMPLETED. CHARGED TO 561 - 24-0263458-00 .
23026282000 | 561 | EX | INSTALL 40'-4" PMIP | HWY 550 | B | 63454.1516 | 49257.58 | -14196.5716 | -22% | 44 | 60 | 820.9597
23026282100 | 562 | EX | RETIRE 36'-4" BSIP | HWY 550 | B | 139.1159 | 124.74 | -14.3759 | -10% |  |  | 0
23026291200 | 557 | EX | EMER - INSTALL 8'-3" PMIP | 153 OLD MIDDLE FORK RD | A | 32593.7477 | 51206.39 | 18612.6423 | 57% | 8 | 9 | 5689.5989 | INSTALLED 3INCH PLASTIC MAIN SECTION TO REPLACE LEAKING 3 INCH BS MAIN JCK 9.8.23
23026291300 | 558 | EX | EMER - RETIRE 7'3" BS&P | 153 OLD MIDDLE FORK RD | A | 119.4953 | 392.93 | 273.4347 | 229% |  |  | 0 | ABANDON LEAKING METAL MAIN. INSTALLED 3 INCH PLASTIC MAIN JCK 9.8.23
23026302100 | 584 | EX | RETIRE PAPER GAUGE | DUDLEY DR | F | 989.8688 | 306.23 | -683.6388 | -69% |  |  | 0
23026302200 | 584 | EX | RETIRE PAPER GAUGE | LOWER HAROLD 1418 | F | 989.8688 | 1131.38 | 141.5112 | 14% |  |  | 0
23026304600 | 2000 | EX | INVESTIGATE ENCROACHMENT | 50 ASHLEY DR |  | 5000 | 0 | -5000 | 100% |  |  | 0 | PS&I IS NOT COMPLETE
23026306500 | 583 | EX | INSTALL DRIP TANK | SR899 1429 | F | 21571.6224 | 22554.83 | 983.2076 | 5% |  |  | 0 | NO CC NEEDED NOT ONSITE-- GATHERIN MATERIAL TO INSTALL MCR 2-5-24 1600 NO CC NEEDED CC # 57053 MCR 2-6-24 1600 CC # 57053 CC 57053 NO CC NEEDED. MATERIAL PICKUP. CC # 57053 DRIP INSTALLED MCR 2-15-2024 1500 CC # 50753
23026307300 | 555 | EX | INSTALL ~100'-2" PMIP | 1825 BLACKLOG RD B | B | 23189 | 40892.69 | 17703.69 | 76% | 100 | 149 | 274.4476
24026311300 | 583 | EX | EMER - INSTALL 2" 461S | SR899 1429 | F | 2282.9666 | 2699.35 | 416.3834 | 18% |  |  | 0 | CC # 57053 INSTLLD REGS MCR 1-22-24 1330 CC 57053 NO CC NEEDED NOT ONSITE-- CO PAPERWORK TO SEND TO WADE MCR 1-26-24 1000 NO CC NEEDED NOT ONSITE PAPAER WORK OFF SITE MCR 2-5-24 1205
24026311400 | 584 | EX | EMER - RETIRE 2" MOONEYS | SR899 1429 | F | 59.4493 | 721.94 | 662.4907 | 1,114% |  |  | 0 | CC # 57053 REMOVED MOONEYS MCR 1-22-24 1030 CC 57053
24026317800 | 557 | EX | EMER - INSTALL 5'-2" PMIP | 94 WALNUT ST | A | 6092.2548 | 8355.27 | 2263.0152 | 37% | 5 | 7 | 1193.61 | INSTALLED NEW 020 P ML. TESTED @ 90# 1 HOUR. SOAP TEST TIE IN COUPLING. MAR KER BALL AT EOM. J HOWARD 2-16-24
24026317900 | 558 | EX | EMER - RETIRE 5'-2" PIP | 94 WALNUT ST | A | 160.3697 | 162.78 | 2.4103 | 2% |  |  | 0
24026320600 | 583 | EX | INSTALL ERX BATTERY | US 119 1433 | F | 3894.6442 | 2726.43 | -1168.2142 | -30% |  |  | 0
24026320700 | 584 | EX | RETIRE ERX BATTERY | US 119 1433 | F | 160.3697 | 0 | -160.3697 | 100% |  |  | 0
24026333600 | 555 | EX | INSTALL 75'-2" PMIP | 111 CHERRY ST | B | 31694.159 | 28387.83 | -3306.329 | -10% | 80 | 83 | 342.022
24026342600 | 558 | EX | EMER ABANDON 200' OF 2" BSIP | 2ND ST | A | 7907.5865 | 5344.92 | -2562.6665 | -32% |  |  | 0
24026345800 | 561 | EX | INSTALL 1400'-2" PMIP | COW HOLLOW RD | B | 300748.5042 | 263557.02 | -37191.4842 | -12% | 1900 | 1212 | 217.4563
24026345900 | 562 | EX | RETIRE 1200'-2"/4" PA/BS/CS IP | COW HOLLOW RD | B | 76.7529 | 0 | -76.7529 | 100% |  |  | 0
24026347600 | 557 | EX | EMER - INSTALL 7'-2" PMIP | E MAIN ST | A | 6644.7043 | 6613.86 | -30.8443 | 0% | 13 | 7 | 944.8371
24026347700 | 558 | EX | EMER -RETIRE 7'-2" PMIP | E MAIN ST | A | 136.633 | 0 | -136.633 | 100% |  |  | 0
24026362700 | 587 | EX | INSTALL EC-350 FOR GMB | 608 SR80 | F | 159.2637 | 0 | -159.2637 | 100% |  |  | 0 | INSTALLED EC350 REPLACE MANUAL CHART
24026367700 | 587 | EX | INSTALL NEW EC-350 UNIT | 2000 CENTRAL AV | F | 6063.7288 | 706.81 | -5356.9188 | -88% |  |  | 0 | CCC NOT NEEDED GMB ACCNT MCR 11-8-24 1530 INSTALLED NEW EC350
24026367800 | 588 | EX | RETIRE EME UNIT | 2000 CENTRAL AV | F | 135.7529 | 379.26 | 243.5071 | 179% |  |  | 0 | CCC NOT NEEDED GMB ACCNT MCR 11-8-24 1100 RETIRED MINI AT INSTALLED NEW EC350
24026375700 | 909 | EX | INSTALL FLOAT SWITCH | US23 UPPER HAROLD 1419 | F | 2988.4639 | 1897.47 | -1090.9939 | -37% |  |  | 0 | CCC 108219 INSTALLED FLOAT SWITCH WITH ACP 2-25-25 1300 TAX DISTRICT IS INCORRECT IN WMS, MAPPED CORRECTLY IN GIS. PER SYLVIA MORRISON LEAVE AS IS FOR NOW, FCA WILL BE NEEDED IN FUTURE CORRECT TAXING DISTRICT IS 1957702
24026375800 | 909 | EX | INSTALL FLOAT SWITCH | US 119 1433 | F | 2988.4639 | 2733.24 | -255.2239 | -9% |  |  | 0 | CCC 108219 INSTLLD FLOAT SWITCH WITH ACP MCR 2-2-5-25 1200
24026375900 | 909 | EX | INSTALL FLOAT SWITCH | LOWER HAROLD 1418 | F | 2988.4639 | 2210.8 | -777.6639 | -26% |  |  | 0 | CCC 108219 INSTLLD FLOAT SWITCHES WITH ACP MCR 2-25-25 1530
25026384800 | 2000 | EX | ENVIROMENTAL RESEARCH |  |  | 5000 | 0 | -5000 | 100% |  |  | 0 | PROJECT RELEASE TO SCHEDULING AND PS&I CHARGE TO MAIN INSTALATION JO. D.LEM ONS 5/29/2025
25026394000 | 557 | EX | EMER INSERT 280'-1.2" PMIP | DOW HUNTER | A | 34665.9445 | 2217.44 | -32448.5045 | -94% | 292 | 284 | 7.8079 | INSERTED 280' 1.25" PMIP INTO 2" CASING. TOTAL INSTALL 287'. TESTED AT 90 P SIG FOR 20 MINS W/ FOL APPROVAL. EM BALLS AND TWS INSTALLED. OTHER JOB ORDE R FOR RETIRE 25026394100. J HOWARD 3-10-25
25026394100 | 558 | EX | EMER - RETIRE 284'-2"BSIP | DOW HUNTER | A | 181.0849 | 19.19 | -161.8949 | -89% |  |  | 0 | ABND 284FT OF 020 S. 268FT USED FOR CASING OF 280FT OF 0125 CARRIER PIPE. I NSTALL JOB ORDER 25026394000. J HOWARD 3-10-25
25026396000 | 583 | EX | INSTALL CAT HEATER | LOWER HAROLD 1418 | F | 8040.0756 | 0 | -8040.0756 | 100% |  |  | 0 | CCC# 107424 2/17/25 JAMES PASLEY
25026396100 | 584 | EX | RETIRE CAT HEATER | LOWER HAROLD 1418 | F | 160.2249 | 0 | -160.2249 | 100% |  |  | 0
25026397900 | 2000 | EX | INVESTIGATE BORE PATH | 6102 KY 899 |  | 22218 | 0 | -22218 | 100% |  |  | 0 | STATE PERMIT FINALLY RECIEVED FOR CONSTRUCTION. D.LEMONS 5/7/2025
25026398400 | 557 | EX | EMER - INSTALL FITTINGS | BOOOMERANG | A | 11221.5028 | 6860.25 | -4361.2528 | -39% |  |  | 0
25026398500 | 558 | EX | EMER - RETIRE 50'-4" CSIP | BOOOMERANG | A | 160.2249 | 0 | -160.2249 | 100% |  |  | 0
25026403700 | 2000 | EX | INVESTIGATE LAND RIGHTS | 6018 N WOLF CREEK RD |  | 8985 | 0 | -8985 | 100% |  |  | 0 | PROJECT RELEAASED TO SCHEDULING FOR COMPLETION. JO CHARGED TO MAIN INSTALAT ION JO. D.LEMONS 5/29/2025

## WMS JO Data (hidden)
Job Orders with Account Class and Actual Costs
cognos.nisource.net:// NGD>>Reports>>Job Orders | [27 empty] | Report Run: May 21, 2024 6:30:02 PM
Date Type: Jo Complete Date | [27 empty] | **Nisource Confidential - For Internal Use Only
Date Range: Jan 1, 2019 Thru Dec 31, 2023 | [27 empty] | For questions, contact Business Intelligence at birepreq@nisource.com
Job Type: 555 - MAINS-NEW BUSINESS, 557 - MAINS-LEAKAGE ELIMINATION, 558 - MAINS-LEAKAGE ELIMINATION (RET.), 559 - MAINS-SERVICE IMPROVEMENT, 560 - MAINS-SERVICE IMPROVEMENT (RET.), 561 - MAINS-STREET IMPROVEMENT, 562 - MAINS-STREET IMPROVEMENT (RET.), 565 - SERVICE LINE - REPLACE, 566 - SERVICE LINE - ABANDON, 575 - REGULATOR SITES, 576 - REGULATOR SITES (RET.), 577 - REGULATOR STRUCTURES - NEW, 583 - PLANT REGULATORS - REPL, 584 - PLANT REGULATORS (RET.), 585 - REGULATOR STRUCTURES - REPL, 586 - REGULATOR STRUCTURES (RET.), 587 - L V EXCESS PRESSURE M&R, 588 - L V EXCESS PRESSURE M&R (RET.), 909 - COMMUNICATION EQUIPMENT, 910 - COMMUNICATION EQUIPMENT (RET.)
Job Status:
Responsible Supervisor:
State, Ops Center, Work Loc, County: KY
Project Id:
Accounting Project Code:
PSID:
State | Ops Center | Work Loc | Job Order | Cap Flag | PSID | PSID Seq No | Map No | Project Id | Project Engineer | Current RT No | Job Type | Job Status | Job Summary | Resp Suprv | Located At | Address | Cnty Cd | Cty Cd | Stat Dt | Executed By | Entered By | Entered Dt | Priority Dt | Commit Dt | In Out Service Dt | Completed By | Complete Dt | Crew Start Dt | Actual Start Dt | Instl Cd | Bus Unit | Account | Home Dp | Chrg Dp | Affil | Activ | Project | Cst Elem Cd | Cost Obj Cd | Fclty cd | Proj Cd | Chrg Jo No | Chrg Pc | Nifit Work Order | Hours | Units | Total Actual Cost | Actual Labor Cost | Actual Mtl Cost | Actual Oth Cost | Actual Contr Cost | Actual Store Cost | Actual AFUDC Cost | Actual SEGA Cost | Footage
KY | KY - WEST | 2621 | 17026702600 |  |  |  | 16720212A | 1744515 | U122858 |  | 584 | EX | RETIRE GUAGE | 2600E | LOUDON | 101 W LOUDON AV | 067 | LEX | 2019-01-22 | U462463 | U122858 | 2017-04-07 | 2019-12-31 | 2019-12-31 | 2019-01-01 | JAMES PASLEY | 2019-01-01 |  |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00584 | 3200584 |  |  | WP7026 |  |  | 100 | 058432170267026 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12975817300 |  | 100270407 |  | U-1015/41 |  |  |  | 566 | EX | SOII - ABANDON METER ONLY | 2600B | PIKE | 213 E PIKE ST 8 | 097 | CYN | 2019-03-01 | JTOY | U123854 | 2012-06-11 | 2019-12-31 |  |  | JDSKAGG | 2019-01-02 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.46667 | 1 | 27.35 | 25.68 | 0 | 1.67 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 12985089900 |  | 100344524 |  | 6700224O |  | U125208 |  | 566 | EX | LCB / ABANDON / RI 08-26-2009 | 2621P | HIGGINS | 309 W HIGGINS ST | 239 | MID | 2019-01-03 | U131002 | U125208 | 2012-08-20 | 2049-12-31 |  |  | RVANDER | 2019-01-02 | 2018-12-19 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 10.1333 | 3 | 680.26 | 606.72 | 41.54 | 32 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 17026696000 |  |  |  | 6724208P | 1743326 | U122858 |  | 909 | EX | ADDIING SUPER SOLAR KITS | 2600E | WILLOW SPRINGS | 3620 WILLOW SPRINGS | 067 | LEX | 2019-01-09 | U462463 | U122858 | 2017-03-10 | 2018-12-31 | 2018-12-31 | 2017-04-19 | CYNTHIA FARIS | 2019-01-02 | 2018-08-06 | 2018-08-06 | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP6960 |  |  | 100 | 090932170266960 | 7.2333 | 0 | 3856.81 | 410.42 | 2456.72 | 103.68 | 859.04 | 0 | 26.95 | 0
KY | KY - WEST | 2621 | 18026753100 |  |  |  | 6724208E | 1851121 | U128885 |  | 583 | EX | INSTALL 2 VRG PILOTS | 2600E | WOODWARD | 600 WOODWARD LN | 067 | LEX | 2019-01-09 | U462463 | U128885 | 2018-02-26 | 2018-12-31 | 2018-12-31 | 2018-12-04 | CYNTHIA FARIS | 2019-01-02 | 2018-11-26 | 2018-11-26 | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00583 | 3200583 |  |  | WP7531 |  |  | 100 | 058332180267531 | 108.2667 | 0 | 16948.81 | 6413.91 | 7207.6 | 806.02 | 0 | 0 | 188.72 | 2332.56
KY | KY - WEST | 2621 | 18026753200 |  |  |  | 6724208E | 1851121 | U128885 |  | 584 | EX | RETIRE | 2600E | WOODWARD | 600 WOODWARD LN | 067 | LEX | 2019-01-09 | U462463 | U128885 | 2018-02-26 | 2018-12-28 | 2018-12-31 | 2018-12-04 | CYNTHIA FARIS | 2019-01-02 |  |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00584 | 3200584 |  |  | WP7532 |  |  | 100 | 058432180267532 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18026755000 |  |  |  | 6724208E | 1851121 | U131369 |  | 909 | EX | I&C INSTALLATION | 2600E | WOODWARD | 600 WOODWARD LN | 067 | LEX | 2019-01-09 | U462463 | U131369 | 2018-03-02 | 2018-12-21 | 2018-12-31 | 2018-12-04 | CYNTHIA FARIS | 2019-01-02 | 2018-04-25 | 2018-04-25 | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP7550 |  |  | 100 | 090932180267550 | 147.3333 | 0 | 201720.08 | 9107.63 | 129209.6 | 1736.83 | 58630.07 | 0 | 3035.95 | 0
KY | KY - WEST | 2621 | 18627921000 |  | 100296216 |  | 6716216O |  | U125208 |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | ERIE | 490 ERIE RD | 067 | LEX | 2019-01-03 | U131002 | U125208 | 2018-07-17 | 2019-01-16 | 2020-07-31 |  | DBANKS | 2019-01-02 | 2018-12-27 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.2167 | 3 | 2043.82 | 263.24 | 110.15 | 79.12 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18630657900 |  | 100310416 |  | 6716208E |  | U125208 |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | STRATFORD | 625 STRATFORD DR | 067 | LEX | 2019-01-03 | U131002 | U125208 | 2018-07-27 | 2019-01-25 | 2020-07-31 |  | DBANKS | 2019-01-02 | 2018-12-27 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.1167 | 3 | 3215.34 | 477.11 | 231.74 | 154.86 | 2351.63 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18631096500 |  | 100270405 |  | 6736252M |  |  |  | 566 | EX | II - ABANDON ON SOII | 2600B | PIKE | 211 E PIKE ST | 097 | CYN | 2019-03-01 | JTOY | U126129 | 2018-07-30 | 2019-12-31 |  |  | JDSKAGG | 2019-01-02 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.76667 | 1 | 694.08 | 42.43 | 8.98 | 2.77 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18650790100 |  | 100273937 |  | 6684228I |  | U125208 |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SKYVIEW | 138 SKYVIEW DR | 073 | FRA | 2019-01-02 | CDESPAI | U125208 | 2018-10-15 | 2019-04-12 | 2020-10-31 |  | CDESPAI | 2019-01-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.6 | 1 | 4320.88 | 596.68 | 363.31 | 349.1 | 3011.79 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18655922900 |  | 100270401 |  | 6736252M | 1855043 |  |  | 566 | EX | II- ABANDON OR CO SOII | 2600B | PIKE | 213 E PIKE ST 3 | 097 | CYN | 2019-03-01 | JTOY | U126926 | 2018-11-06 | 2019-12-31 |  |  | JDSKAGG | 2019-01-02 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.36667 | 1 | 21.39 | 20.09 | 0 | 1.3 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18655923100 |  | 100270404 |  | 6736252M | 1855043 |  |  | 566 | EX | II- ABANDON OR CO SOII | 2600B | PIKE | 213 E PIKE ST 6 | 097 | CYN | 2019-03-01 | JTOY | U126926 | 2018-11-06 | 2019-12-31 |  |  | JDSKAGG | 2019-01-02 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.55 | 1 | 32.73 | 30.74 | 0 | 1.99 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18655923200 |  | 100270408 |  | 6736252M | 1855043 |  |  | 566 | EX | II- ABANDON OR CO SOII | 2600B | PIKE | 213 E PIKE ST 2 | 097 | CYN | 2019-03-01 | JTOY | U126926 | 2018-11-06 | 2019-12-31 |  |  | JDSKAGG | 2019-01-02 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.75 | 1 | 44.61 | 41.88 | 0 | 2.73 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18655923300 |  | 100270409 |  | 6736252M | 1855043 |  |  | 566 | EX | II- ABANDON OR CO SOII | 2600B | PIKE | 215 E PIKE ST | 097 | CYN | 2019-03-01 | JTOY | U126926 | 2018-11-06 | 2019-12-31 |  |  | JDSKAGG | 2019-01-02 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.85 | 1 | 50.54 | 47.46 | 0 | 3.08 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 07690246200 |  | 100268893 |  | U-1015/34 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2600B | MARSHALL | 107 MARSHALL AV | 097 | CYN | 2019-01-03 | JDSKAGG | U903504 | 2007-06-08 | 2019-01-03 |  |  | JDSKAGG | 2019-01-03 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.6 | 1 | 672.19 | 33.52 | 10.36 | 2.18 | 626.13 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 09772756200 |  | 100271229 | 16 | ADVISE | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2600B | HIGHLAND | 130 HIGHLAND AV | 097 | CYN | 2019-01-03 | JDSKAGG | SRICHIE | 2009-02-16 | 2019-01-03 |  |  | JDSKAGG | 2019-01-03 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.5167 | 1 | 851.4 | 141.76 | 74.31 | 9.2 | 626.13 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11898486400 |  | 100343409 |  | 7240212B | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2600B | MAIN | 124 W MAIN ST | 173 | MT | 2019-01-16 | JTOY | U906631 | 2011-03-30 | 2018-12-21 |  |  | RJJOHNS | 2019-01-03 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.6333 | 1 | 798.68 | 97.66 | 54.76 | 6.36 | 639.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11919115800 |  | 100343411 |  | 7240212B | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2600B | MAIN | 116 W MAIN ST | 173 | MT | 2019-01-16 | JTOY | U907469 | 2011-08-05 | 2018-12-21 |  |  | RJJOHNS | 2019-01-03 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.7 | 1 | 844.94 | 161.75 | 32.77 | 10.52 | 639.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11919115900 |  | 100343417 |  | 7240212B | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2600B | MAIN | 106 W MAIN ST | 173 | MT | 2019-01-16 | JTOY | U907469 | 2011-08-05 | 2018-12-21 |  |  | RJJOHNS | 2019-01-03 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.3833 | 1 | 762 | 83.87 | 32.77 | 5.46 | 639.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12975816100 |  | 100269946 |  | 6732252P | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2600B | 4TH | 104 4TH ST | 097 | CYN | 2019-02-08 | JTOY | U123854 | 2012-06-11 | 2018-12-21 |  |  | JDSKAGG | 2019-01-03 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.86667 | 1 | 763.46 | 48.01 | 86.19 | 3.13 | 626.13 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12975816200 |  | 100269987 |  | 6732252P | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2600B | 3RD | 212 3RD ST | 097 | CYN | 2019-01-03 | JDSKAGG | U123854 | 2012-06-11 | 2018-12-27 |  |  | JDSKAGG | 2019-01-03 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.46667 | 1 | 727.79 | 25.68 | 74.31 | 1.67 | 626.13 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12975869100 |  | 100343416 |  | 7240212B | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2600B | MAIN | 112 W MAIN ST | 173 | MT | 2019-01-03 | RJJOHNS | U123854 | 2012-06-11 | 2018-12-21 |  |  | RJJOHNS | 2019-01-03 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.4 | 1 | 762 | 83.87 | 32.77 | 5.46 | 639.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18574501000 |  | 100270330 | 53 | 6736252M | 1855043 |  |  | 566 | EX | ABANDON SL FOR FIRE PS MAILBOX | 2600B | WALNUT | 105 S WALNUT ST | 097 | CYN | 2019-01-04 | U131002 | U129302 | 2018-01-12 | 2019-01-03 |  |  | JDSKAGG | 2019-01-03 | 2019-01-02 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10.4833 | 2 | 1351.21 | 584.81 | 102.29 | 37.98 | 626.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18620845100 |  | 500205288 |  | 6716216K | 0677358 | U125208 |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | NANDINO | 1088 NANDINO BV | 067 | LEX | 2019-01-04 | U131002 | U125208 | 2018-06-18 | 2018-12-29 | 2019-01-16 |  | KKINDER | 2019-01-03 | 2019-01-02 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 34.4167 | 4 | 3012.17 | 1847.69 | 348.76 | 183.56 | 632.16 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18636016400 |  | 100269912 |  | 6732252P | 1855043 |  |  | 566 | EX | II - ABANDON ON SOII | 2600B | BROADWAY | 304 BROADWAY AV | 097 | CYN | 2019-02-11 | JTOY | U126129 | 2018-08-17 | 2018-12-21 |  |  | JDSKAGG | 2019-01-03 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.95 | 2 | 1522.34 | 111.25 | 102.29 | 7.23 | 1301.57 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18646050600 |  | 100280782 |  | 6688228E |  | U125208 |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MARLOWE | 128 MARLOWE CT | 073 | FRA | 2019-01-03 | CDESPAI | U125208 | 2018-09-25 | 2019-01-03 | 2020-09-30 |  | CDESPAI | 2019-01-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 10.6 | 1 | 3957.45 | 832.22 | 357.99 | 486.94 | 2280.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18663494700 |  | 100335368 |  | 6720212P |  | U128293 |  | 566 | EX | ABANDON SERVICE | 2621P | PRIDEMORE | 1360 PRIDEMORE CT | 067 | LEX | 2019-01-03 | MCRAIG | U128293 | 2018-12-20 | 2018-02-01 |  |  | MCRAIG | 2019-01-03 | 2018-12-31 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 30.95 | 9 | 1734.45 | 1614.23 | 19.09 | 101.13 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18663614100 |  | 100341696 |  | 7240216O |  |  |  | 566 | EX | ABANDON SL FOR DEMO PS MAILBOX | 2621P | MONTGOMERY | 220 MONTGOMERY AV | 173 | MT | 2019-01-03 | DENNING | U130722 | 2018-12-21 | 2019-02-08 | 2019-03-01 |  | DENNING | 2019-01-03 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 7.5 | 3 | 494.12 | 389.74 | 20.16 | 84.22 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18664080200 |  | 100284382 |  | 6764176N |  |  |  | 566 | EX | ABANDON SL FOR DEMO PS MAILBOX | 2621P | CEDAR GROVE | 300 W CEDAR GROVE RD | 065 | IRV | 2019-01-03 | DENNING | U124962 | 2018-12-26 | 2019-02-12 | 2019-03-05 |  | DENNING | 2019-01-03 | 2018-12-28 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 19.4 | 6 | 1244.11 | 1018.77 | 0 | 225.34 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19666119800 |  | 100296669 |  | 6716212C |  | U124447 |  | 565 | EX | GRADE ONE LEAK ON SERVICE | 2621P | DOUGLAS | 412 DOUGLAS AV | 067 | LEX | 2019-01-03 | JENSMIN | U124447 | 2019-01-03 | 2019-01-03 | 2019-01-03 |  | JENSMIN | 2019-01-03 | 2019-01-03 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.8833 | 3 | 4823.94 | 1222.84 | 187.03 | 415.3 | 2998.77 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11897635500 |  | 100343475 |  | 7240212B | 1855043 |  |  | 566 | EX | SOII - ABANDON / RI 03-30-2010 | 2600B | LOCUST | 111 W LOCUST ST | 173 | MT | 2019-01-04 | RJJOHNS | U124961 | 2011-03-24 | 2019-12-31 |  |  | RJJOHNS | 2019-01-04 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 6.2 | 3 | 1112.76 | 335.35 | 60.75 | 76.76 | 639.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11916316400 |  | 100341995 |  | 7240216N | 1855043 |  |  | 566 | EX | SOII - ABANDON SERV/ RI 7-2008 | 2600B | HIGH | 101 E HIGH ST | 173 | MT | 2019-01-04 | RJJOHNS | U124964 | 2011-07-18 | 2019-12-31 |  |  | RJJOHNS | 2019-01-04 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.85 | 1 | 1026.92 | 170.74 | 32.77 | 11.1 | 812.31 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12949805700 |  | 100341993 |  | 7240216N | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2600B | HIGH | 103 E HIGH ST 2F | 173 | MT | 2019-01-04 | RJJOHNS | U125208 | 2012-01-16 | 2019-12-31 |  |  | RJJOHNS | 2019-01-04 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.9667 | 1 | 1164.53 | 117.41 | 54.76 | 7.64 | 984.72 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12968024200 |  | 100343410 |  | 7240212B | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2600B | MAIN | 122 W MAIN ST | 173 | MT | 2019-01-04 | RJJOHNS | U124967 | 2012-05-02 | 2018-12-21 |  |  | RJJOHNS | 2019-01-04 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.6 | 1 | 102.07 | 95.83 | 0 | 6.24 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 18026843000 |  |  |  | 7256280G | 1858763 | U122858 |  | 557 | EX | INSTALL 110'-2" PMLP | 2600B | 5TH | 5TH | 161 | MAY | 2019-01-12 | U131296 | U122858 | 2018-10-27 | 2020-02-24 | 2020-10-01 | 2019-01-04 | DAVID STAGGS | 2019-01-04 | 2018-12-11 | 2018-12-11 | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00557 | 3200557 |  |  | WP8430 | AMRCB |  | 100 | 055732180268430 | 106 | 1599 | 78922.81 | 26503.55 | 1749.03 | 5845.09 | 34089.15 | 0 | 306.02 | 10429.97 | 123
KY | KY - CENTRAL | 2632 | 18026843100 |  |  |  | 7256280G | 1858763 | U122858 |  | 558 | EX | RETIRE 110'-2" BSLP | 2600B | 5TH | 5TH | 161 | MAY | 2019-01-12 | U131296 | U122858 | 2018-10-27 | 2020-02-28 | 2020-10-01 | 2019-01-04 | DAVID STAGGS | 2019-01-04 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00558 | 3200558 |  |  | WP8431 | AMRCB |  | 100 | 055832180268431 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19665370600 |  | 100467259 |  | 6688232N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | DEER | 1117 DEER HA | 073 | FRA | 2019-01-07 | U131002 | U131002 | 2019-01-02 | 2019-01-02 | 2019-01-20 |  | RVANDER | 2019-01-04 | 2019-01-04 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 10.15 | 2 | 659.77 | 591.07 | 30.29 | 38.41 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19666571200 |  | 100411397 |  | 6720206K |  | U130867 |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | RUSSELL CAVE | 1824 RUSSELL CAVE RD | 067 | LEX | 2019-01-07 | U131002 | U130867 | 2019-01-04 | 2019-01-04 | 2019-01-04 |  | JENSMIN | 2019-01-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.6167 | 1 | 4752.03 | 444.44 | 205.17 | 28.89 | 4073.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19666622500 |  | 100315438 |  | 6716208C |  | U130867 |  | 565 | EX | RERUN SERVICE | 2621P | WALLER | 122 WALLER AV | 067 | LEX | 2019-01-07 | U131002 | U130867 | 2019-01-04 | 2019-01-04 | 2019-01-23 |  | DBANKS | 2019-01-05 | 2019-01-04 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.4 | 2 | 7380.97 | 2242.1 | 27.45 | 276.75 | 4834.67 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 07671290300 |  | 100343412 |  | 7240212B | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2600B | MAIN | 116 W MAIN ST 2F | 173 | MT | 2019-01-07 | RJJOHNS | SKSMITH | 2007-01-05 | 2019-12-31 |  |  | RJJOHNS | 2019-01-07 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.73333 | 1 | 46.59 | 43.75 | 0 | 2.84 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11903718100 |  | 100334277 |  | 6720212P |  |  |  | 566 | EX | ABANDON SL | 2621P | DOWNS | 723 DOWNS AV | 067 | LEX | 2019-01-07 | CMCHOLA | U124961 | 2011-04-28 | 2049-12-31 |  |  | CMCHOLA | 2019-01-07 | 2019-01-07 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.1 | 2 | 263.42 | 247.35 | 0 | 16.07 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18026849000 |  |  |  | 6740212O | 1860106 | U461383 |  | 587 | EX | INSTALL MI WIRELESS UNIT | 2600M | GAWTHROP | 500 GAWTHROP DR | 049 | WIN | 2019-01-16 | U462463 | U461383 | 2018-12-17 | 2019-04-01 | 2019-04-01 | 2019-01-07 | CYNTHIA FARIS | 2019-01-07 | 2019-01-07 | 2019-01-07 | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00587 | 3200587 |  |  | WP8490 |  |  | 100 | 058732180268490 | 28.5 | 5 | 7324.71 | 1695.43 | 4336.47 | 281.16 | 0 | 0 | 32.33 | 979.32
KY | KY - CENTRAL | 2629 | 18026849100 |  |  |  | 6740212O | 1860106 | U461383 |  | 588 | EX | RETIRE EME UNIT | 2600M | GAWTHROP | 500 GAWTHROP DR | 049 | WIN | 2019-01-16 | U462463 | U461383 | 2018-12-17 | 2019-04-01 | 2019-04-01 | 2019-01-07 | CYNTHIA FARIS | 2019-01-07 |  |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00588 | 3200588 |  |  | WP8491 |  |  | 100 | 058832180268491 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18596243500 |  | 100468418 |  | 6700212N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HUNTERS RIDGE | 537 HUNTERS RIDGE DR | 239 | VER | 2019-01-08 | U131002 | U125208 | 2018-03-22 | 2018-09-20 | 2020-03-31 |  | LCLARK | 2019-01-07 | 2018-12-13 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 24.0167 | 6 | 1616.2 | 1404.41 | 124.5 | 87.29 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18650809400 |  | 100251922 |  | 7328284A |  |  |  | 566 | EX | ABANDON / DEMO / RI 10-22-18 | 2621P | WALNUT | 31 WALNUT ST | 089 | S S | 2019-01-07 | MCOLLET | U131560 | 2018-10-15 | 2018-11-15 | 2018-11-15 |  | MCOLLET | 2019-01-07 | 2019-01-07 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 10.4333 | 3 | 852.96 | 634.4 | 21.99 | 196.57 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11894686700 |  | 100270451 |  | 6736252M | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2600B | PLEASANT | 207 E PLEASANT ST | 097 | CYN | 2019-01-29 | U125208 | U906307 | 2011-03-08 | 2019-12-31 |  |  | JDSKAGG | 2019-01-08 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.56667 | 1 | 682.19 | 31.25 | 8.98 | 2.06 | 639.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11925343700 |  | 100270292 |  | 6736252M | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2600B | MAIN | 138 S MAIN ST | 097 | CYN | 2019-01-08 | JDSKAGG | U906631 | 2011-09-19 | 2019-12-31 |  |  | JDSKAGG | 2019-01-08 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.61667 | 1 | 685.16 | 34.07 | 8.98 | 2.21 | 639.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12967994900 |  | 100270406 |  | U-1015/41 |  |  |  | 566 | EX | SOII - ABANDON METER ONLY | 2600B | PIKE | 213 E PIKE ST 1 | 097 | CYN | 2019-01-08 | JDSKAGG | U124967 | 2012-05-02 | 2019-12-31 |  |  | JDSKAGG | 2019-01-08 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.8167 | 1 | 110.53 | 103.8 | 0 | 6.73 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12968591100 |  | 100270403 |  | U-1015/41 |  |  |  | 566 | EX | SOII - ABANDON METER ONLY | 2600B | PIKE | 213 E PIKE ST 7 | 097 | CYN | 2019-01-08 | JDSKAGG | U124967 | 2012-05-07 | 2019-12-31 |  |  | JDSKAGG | 2019-01-08 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.28333 | 1 | 16.66 | 15.64 | 0 | 1.02 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12975869300 |  | 100343418 |  | 7240212B | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2600B | MAIN | 108 W MAIN ST | 173 | MT | 2019-01-08 | RJJOHNS | U123854 | 2012-06-11 | 2019-12-31 |  |  | RJJOHNS | 2019-01-08 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.75 | 1 | 111.64 | 104.82 | 0 | 6.82 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18026848800 |  |  |  | 6744208H | 1860106 | U461383 |  | 587 | EX | INSTALL MI WIRELESS UNIT | 2600M | ROLLING HILLS | 1200 ROLLING HILLS LN | 049 | WIN | 2019-01-22 | U462463 | U461383 | 2018-12-17 | 2019-04-01 | 2019-04-01 | 2019-01-08 | CYNTHIA FARIS | 2019-01-08 | 2019-01-08 | 2019-01-08 | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00587 | 3200587 |  |  | WP8488 |  |  | 100 | 058732180268488 | 34.9667 | 4 | 10698.17 | 2080.41 | 6040.03 | 240.37 | 892.84 | 0 | 38.85 | 1405.67
KY | KY - CENTRAL | 2629 | 18026848900 |  |  |  | 16744208G | 1860106 | U461383 |  | 588 | EX | RETIRE EME UNIT | 2600M | ROLLING HILLS | 1200 ROLLING HILLS LN | 049 | WIN | 2019-01-22 | U462463 | U461383 | 2018-12-17 | 2019-04-01 | 2019-04-01 | 2019-01-08 | CYNTHIA FARIS | 2019-01-08 |  |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00588 | 3200588 |  |  | WP8489 |  |  | 100 | 058832180268489 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572337500 |  | 100277566 |  | 6688228E | 1748493 |  |  | 565 | EX | RPLC SL/17026732600/ | 2600B | BUFFALO | 130 BUFFALO TL | 073 | FRA | 2019-02-11 | U461327 | U131066 | 2018-01-04 | 2018-12-31 |  |  | WBURCHETT | 2019-01-08 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1502.85 | 0 | 0 | 0 | 1502.85 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18636012000 |  | 100325624 |  | 6720208J | 1855043 |  |  | 566 | EX | ABANDON PER DEMO | 2621P | LAKEWOOD | 1847 LAKEWOOD DR W | 067 | LEX | 2019-01-08 | LMCDONA | U126129 | 2018-08-17 | 2018-10-30 | 2018-10-30 |  | LMCDONA | 2019-01-08 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 23.45 | 3 | 1836.42 | 1292.71 | 0 | 83.95 | 459.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18638619900 |  | 100301990 |  | 6712212H |  | U125208 |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CAMBRIDGE | 1981 CAMBRIDGE DR A | 067 | LEX | 2019-01-08 | DBANKS | U125208 | 2018-08-28 | 2019-02-27 | 2020-08-31 |  | DBANKS | 2019-01-08 | 2019-01-07 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.2 | 2 | 3660.92 | 301.09 | 202.09 | 125.35 | 3032.39 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18648151900 |  | 100273535 |  | 6680224F |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SHARON | 152 SHARON RD | 073 | FRA | 2019-01-08 | CDESPAI | U125208 | 2018-10-03 | 2019-01-08 | 2020-10-31 |  | CDESPAI | 2019-01-08 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.8833 | 1 | 2682.79 | 539.38 | 236.5 | 315.6 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18651646300 |  | 100303797 |  | 6712208D |  | U125208 |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | TEAROSE | 840 TEAROSE CT | 067 | LEX | 2019-01-08 | DBANKS | U125208 | 2018-10-18 | 2019-01-08 | 2020-10-31 |  | DBANKS | 2019-01-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.5167 | 1 | 3236.99 | 262.16 | 322.28 | 109.13 | 2543.42 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18663427400 |  | 100421655 |  | 6712228C |  |  |  | 566 | EX | ABANDON SL FOR DEMO PS MAILBOX | 2621P | PARIS | 1047 PARIS PK | 209 | GEO | 2019-01-09 | U131002 | U130722 | 2018-12-20 | 2019-02-07 | 2019-02-28 |  | DCOLLIN | 2019-01-08 | 2019-01-08 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 15.35 | 2 | 1075.92 | 960.69 | 52.81 | 62.42 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18664203800 |  | 100330745 |  | 6720212O |  | U128293 |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SHERMAN | 364 SHERMAN AV | 067 | LEX | 2019-01-09 | U131002 | U128293 | 2018-12-27 | 2018-12-28 | 2019-01-16 |  | CMCHOLA | 2019-01-08 | 2019-01-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.7167 | 2 | 1136.53 | 945.16 | 129.96 | 61.41 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19666206000 |  | 100288100 |  | 6724208K |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SHEFFIELD | 1709 SHEFFIELD CT | 067 | LEX | 2019-01-08 | MPETTUS | U125964 | 2019-01-03 | 2019-01-04 | 2019-01-23 |  | MPETTUS | 2019-01-08 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 33.4667 | 6 | 1783.73 | 1674.89 | 0 | 108.84 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 07684967400 |  | 100342160 |  | V-1221/40 | 1855043 |  |  | 566 | EX | II- ABANDON SL | 2600B | WINN | 246 WINN ST | 173 | MT | 2019-01-09 | RJJOHNS | DMCCULL | 2007-04-30 | 2019-12-31 |  |  | RJJOHNS | 2019-01-09 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.6667 | 1 | 844.31 | 161.15 | 32.77 | 10.49 | 639.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 08735948600 |  | 100427984 |  | 7348264L |  |  |  | 566 | EX | ABANDON SL PER IDLE MEMO | 2621P | TURLEY | 848 TURLEY AV | 089 | FLA | 2019-01-09 | BROBERT | SSUTHER | 2008-06-20 | 2019-01-09 |  |  | BROBERT | 2019-01-09 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.4 | 1 | 2569.84 | 80.52 | 20.16 | 5.23 | 2463.93 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11880832300 |  | 100343659 |  | 7240212B | 1855043 |  |  | 566 | EX | SOII - ABANDON / RI 1-25-10 | 2600B | LOCUST | 260 W LOCUST ST | 173 | MT | 2019-01-09 | RJJOHNS | U123219 | 2011-01-25 | 2019-12-31 |  |  | RJJOHNS | 2019-01-09 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.4833 | 1 | 939.5 | 88.66 | 32.77 | 5.76 | 812.31 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11892882000 |  | 100342146 |  | 7240216N | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2600B | WINN | 245 WINN ST | 173 | MT | 2019-01-09 | RJJOHNS | U906307 | 2011-03-01 | 2019-12-31 |  |  | RJJOHNS | 2019-01-09 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.5833 | 1 | 801.46 | 94.65 | 60.75 | 6.16 | 639.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 12101677900 |  | 100255820 |  | 7348264-L |  |  |  | 566 | EX | ABANDON / RI 12-23-2010 | 2621P | TURLEY | 841 TURLEY AV | 089 | FLA | 2019-01-09 | BROBERT | U125208 | 2012-12-07 | 2019-01-09 |  |  | BROBERT | 2019-01-09 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.0167 | 1 | 969.88 | 173.16 | 63.54 | 11.29 | 721.89 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 12981336600 |  | 100353383 |  | 17256280G |  |  |  | 566 | EX | ABANDON/ IDLE 24MO/ RI 07-2010 | 2621P | ROGERS | 325 ROGERS RD | 161 | MAY | 2020-01-15 | U461478 | U125208 | 2012-07-23 | 2020-12-30 |  |  | DAVID STAGGS | 2019-01-09 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1 | 475.63 | 0 | 0 | 0 | 475.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18602593700 |  | 100309506 |  | 6712208K |  | U125208 |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | APACHE | 805 APACHE TL | 067 | LEX | 2019-01-10 | U131002 | U125208 | 2018-04-12 | 2018-10-11 | 2020-04-30 |  | RTINCHE | 2019-01-09 | 2018-10-09 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.6333 | 2 | 2524.5 | 89.98 | 278.37 | 6.18 | 2149.97 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18603289800 |  | 100289012 |  | 6720212D |  | U125208 |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SANDALWOOD | 506 SANDALWOOD DR | 067 | LEX | 2019-01-10 | U131002 | U125208 | 2018-04-16 | 2018-10-12 | 2020-04-30 |  | RTINCHE | 2019-01-09 | 2018-09-27 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.0833 | 4 | 2034.93 | 176.21 | 266.48 | 35.19 | 1557.05 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18632786600 |  | 100268095 |  | 7356256B |  |  |  | 566 | EX | ABANDON SL FOR DEMO PS MBOX | 2600B | GREENUP | 2208 GREENUP AV | 019 | ASH | 2019-01-09 | MCOLLET | U129294 | 2018-08-06 | 2019-01-09 | 2019-01-09 |  | MCOLLET | 2019-01-09 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.6333 | 2 | 238.36 | 163.9 | 0 | 74.46 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18636019000 |  | 100342820 |  | 7240216N | 1855043 |  |  | 566 | EX | II - ABANDON ON SOII | 2600B | HIGH | 420 W HIGH ST | 173 | MT | 2019-01-09 | RJJOHNS | U126129 | 2018-08-17 | 2019-12-31 |  |  | RJJOHNS | 2019-01-09 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.4167 | 1 | 941.09 | 84.45 | 96.31 | 5.49 | 754.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18650995800 |  | 100290525 |  | 6720216P |  | U125208 |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | EDGEWORTH | 1909 EDGEWORTH DR | 067 | LEX | 2019-01-09 | DBANKS | U125208 | 2018-10-16 | 2019-01-09 | 2020-10-31 |  | DBANKS | 2019-01-09 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.15 | 1 | 2026.31 | 125.54 | 257.2 | 52.26 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18657763400 |  | 100302499 |  | 6712212G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BORDEAUX | 1263 BORDEAUX DR | 067 | LEX | 2019-01-15 | U128381 | U125208 | 2018-11-19 | 2019-01-09 | 2020-11-30 |  | DBANKS | 2019-01-09 | 2019-01-09 | 2019-01-09 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.4667 | 2 | 2091.78 | 201.12 | 215.63 | 83.72 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18661697600 |  | 100337115 |  | 6720212I |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | 5TH | 443 E 5TH ST | 067 | LEX | 2019-01-10 | U131002 | U125208 | 2018-12-12 | 2019-01-09 | 2020-12-31 |  | LMCDONA | 2019-01-09 | 2019-01-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 22.1167 | 4 | 1804.35 | 1163.01 | 178.66 | 75.56 | 387.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18663440200 |  | 100322170 |  | 6716212P |  |  |  | 566 | EX | ABANDON SL FOR DEMO PS MAILBOX | 2621P | OLDHAM | 450 OLDHAM AV | 067 | LEX | 2019-01-10 | U131002 | U130722 | 2018-12-20 | 2019-02-07 | 2019-02-28 |  | ASNICHO | 2019-01-09 | 2019-01-07 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 22.9167 | 6 | 1359.52 | 1266.88 | 10.36 | 82.28 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19666570900 |  | 100355575 |  | 7260280N |  |  |  | 566 | EX | ABANDON SL FOR DEMO PS MAILBOX | 2621P | CLARK | 419 CLARK ST | 161 | MAY | 2019-01-14 | JTOY | U130722 | 2019-01-04 | 2019-02-20 | 2019-03-13 |  | SADAMS | 2019-01-09 | 2019-01-07 | 2019-01-07 | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 10 | 5 | 751.37 | 591.29 | 1.38 | 158.7 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19667326700 |  | 100348147 |  | 6748208I |  |  |  | 566 | EX | ABD SVC LINE | 2621P | MUTUAL | 248 MUTUAL AV | 049 | WIN | 2019-01-09 | SDENNIS | U130193 | 2019-01-09 | 2019-01-09 |  |  | SDENNIS | 2019-01-09 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.1833 | 2 | 357.33 | 314.74 | 21.99 | 20.6 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19667373700 |  | 100466523 |  | 7364188G |  |  |  | 566 | EX | ABD METER SET | 2621P | KY FIELD | KY FIELD | 159 | INE | 2019-01-10 | U131002 | U130193 | 2019-01-09 | 2019-01-09 |  |  | CHAMMON | 2019-01-09 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.3 | 1 | 86.47 | 81.19 | 0 | 5.28 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19667511900 |  | 100337114 |  | 6720212I |  |  |  | 565 | EX | REPLACE SERVICE | 2621P | 5TH | 447 E 5TH ST | 067 | LEX | 2019-01-09 | LMCDONA | U131168 | 2019-01-09 | 2019-01-09 |  |  | LMCDONA | 2019-01-09 | 2019-01-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.6833 | 3 | 1974.9 | 91.17 | 71.54 | 16.21 | 1795.98 | 0 | 0 | 0
KY | KY - EAST | 2631 | 06642955800 |  | 100252569 | 08 | ? |  |  |  | 566 | EX | RETIRE SL ASAP | 2621P | POWELL | 622 POWELL LN | 089 | FLA | 2019-01-10 | BROBERT | SJUDE | 2006-03-29 | 2019-01-10 |  |  | BROBERT | 2019-01-10 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.78333 | 1 | 1273.87 | 46.6 | 21.99 | 3.03 | 1202.25 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11895720600 |  | 100252669 |  | 1 |  |  |  | 566 | EX | SERVICE LINE ABANDON | 2621P | OAK | 2306 OAK ST | 089 | FLA | 2019-01-10 | BROBERT | U124960 | 2011-03-15 | 2019-01-10 |  |  | BROBERT | 2019-01-10 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.33333 | 1 | 742.12 | 19 | 0 | 1.23 | 721.89 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11902014100 |  | 100263765 |  | 7352260O |  |  |  | 566 | EX | ABANDON / RI 04-23-2010 | 2600B | LAUREL | 413 LAUREL AV | 019 | ASH | 2019-01-10 | U125573 | U906631 | 2011-04-19 | 2019-01-10 |  |  | BCOFER | 2019-01-10 |  | 2019-01-10 | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.15 | 1 | 4358.65 | 287.33 | 0 | 84.48 | 3986.84 | 0 | 0 | 0
KY | KY - EAST | 2631 | 12101677500 |  | 100252674 |  | ? |  |  |  | 566 | EX | ABANDON / RA 01-10-2011 | 2621P | OAK | 2314 OAK ST | 089 | FLA | 2019-01-10 | BROBERT | U125208 | 2012-12-07 | 2019-01-10 |  |  | BROBERT | 2019-01-10 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.28333 | 1 | 761.03 | 16.11 | 21.99 | 1.04 | 721.89 | 0 | 0 | 0
KY | KY - EAST | 2631 | 14258060500 |  | 100248215 |  | 7356256E |  |  |  | 566 | EX | ABANDON SL | 2600B | LIBERTY | 2208 LIBERTY ST | 019 | ASH | 2019-01-10 | U125573 | U125201 | 2014-10-16 | 2019-01-10 |  |  | BCOFER | 2019-01-10 |  | 2019-01-10 | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.85 | 1 | 943.84 | 214.82 | 0 | 63.14 | 665.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18026850000 |  |  |  | 6688288B | 1860275 | GSULLI1 |  | 559 | EX | REPLACE VALVE | 2600B | COMANCHE | COMANCHE TL | 073 | FRA | 2019-01-14 | U129900 | GSULLI1 | 2018-12-27 | 2019-01-14 | 2019-01-15 | 2019-01-10 | JAMIE LYNN | 2019-01-10 | 2019-01-10 | 2019-01-10 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00559 | 3200559 |  |  | WP8500 |  |  | 100 | 055932180268500 | 19 | 2 | 12239.28 | 2628.3 | 452.9 | 516.76 | 7070.62 | 0 | 22.85 | 1547.85 | 1
KY | KY - WEST | 2623 | 18026850100 |  |  |  | 6688288B | 1860275 | GSULLI1 |  | 560 | EX | RETIRE VALVE | 2600E | COMMANCHE | COMMANCHE TL | 073 | FRA | 2019-01-14 | U129900 | GSULLI1 | 2018-12-27 | 2019-01-15 | 2019-01-15 | 2019-01-10 | JAMIE LYNN | 2019-01-10 |  | 2019-01-10 | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00560 | 3200560 |  |  | WP8501 |  |  | 100 | 056032180268501 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18602548700 |  | 100464290 |  | 6720204L |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SUMMERHILL | 1717 SUMMERHILL DR | 067 | LEX | 2019-01-10 | RTINCHE | U125208 | 2018-04-12 | 2018-10-11 | 2020-04-30 |  | RTINCHE | 2019-01-10 | 2018-10-09 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.9833 | 3 | 2352.36 | 244.11 | 129.11 | 126.1 | 1853.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18602550600 |  | 100465960 |  | 6720204L |  | U125208 |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HUNTING HILLS | 3321 HUNTING HILLS DR | 067 | LEX | 2019-01-10 | RTINCHE | U125208 | 2018-04-12 | 2018-10-11 | 2020-04-30 |  | RTINCHE | 2019-01-10 | 2018-10-09 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.6333 | 2 | 2160.29 | 91.65 | 142.28 | 453.43 | 1472.93 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18603290000 |  | 100289082 |  | 6720212D |  | U125208 |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SANDALWOOD | 491 SANDALWOOD DR | 067 | LEX | 2019-01-10 | RTINCHE | U125208 | 2018-04-16 | 2018-10-12 | 2020-04-30 |  | RTINCHE | 2019-01-10 | 2018-08-21 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.4 | 4 | 1707.52 | 363.76 | 142.75 | 175.18 | 1025.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18605171000 |  | 100407193 |  | 6716208M |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | RUNNYMEADE | 2988 RUNNYMEADE WY | 067 | LEX | 2019-01-10 | RTINCHE | U125208 | 2018-04-23 | 2018-10-17 | 2020-04-30 |  | RTINCHE | 2019-01-10 | 2018-08-27 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.1167 | 3 | 1641.28 | 297.79 | 213.23 | 104.43 | 1025.83 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19667620400 |  | 100342161 |  | 7240216N |  |  |  | 565 | EX | SL MAINTENANCE | 2621P | WINN | 244 WINN ST | 173 | MT | 2019-01-10 | RJJOHNS | U125964 | 2019-01-10 | 2019-01-30 |  |  | RJJOHNS | 2019-01-10 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 3.9167 | 1 | 2359.81 | 266.37 | 253.92 | 27.66 | 1811.86 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 07689052600 |  | 100284754 |  | 06760172K |  |  |  | 566 | EX | ABANDON SERV LINE/IDLE 48 MO | 2600B | PEA RIDGE | 425 PEA RIDGE RD | 065 | IRV | 2019-01-11 | DENNING | U903504 | 2007-05-31 | 2019-01-11 |  |  | DENNING | 2019-01-11 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 7.5 | 3 | 490.45 | 386.24 | 20.16 | 84.05 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 08726347200 |  | 100255018 |  | T-1726-44 |  |  |  | 566 | EX | ABANDON SL - IDLE 24 MONTHS | 2621P | FIELDS | 2702 FIELDS AV | 089 | FLA | 2019-01-11 | BROBERT | SSUTHER | 2008-04-04 | 2019-01-11 |  |  | BROBERT | 2019-01-11 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.45 | 1 | 771.49 | 25.93 | 21.99 | 1.68 | 721.89 | 0 | 0 | 0
KY | KY - EAST | 2631 | 08730764700 |  | 100255336 |  | 7348264-K |  |  |  | 566 | EX | ABANDON SL - IDLE 24 MONTHS | 2621P | MULLINS | 1206 MULLINS ST | 089 | FLA | 2019-01-11 | BROBERT | SSUTHER | 2008-05-09 | 2019-01-11 |  |  | BROBERT | 2019-01-11 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.33333 | 1 | 1223.86 | 19 | 1.38 | 1.23 | 1202.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 10868084800 |  | 100451487 |  | 6760172K |  |  |  | 566 | EX | ABANDON/ RA 11-09-2010 - DEMO | 2621P | PEA RIDGE | 435 PEA RIDGE RD | 065 | IRV | 2019-01-11 | DENNING | U123166 | 2010-11-10 | 2020-12-31 |  |  | DENNING | 2019-01-11 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 26.1167 | 9 | 1952.54 | 1349.69 | 0 | 277.51 | 325.34 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11900130700 |  | 100243129 |  | 7356256K |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2600B | MOUND | 4016 MOUND ST | 019 | ASH | 2019-01-11 | U125573 | U124961 | 2011-04-06 | 2019-01-11 |  |  | BCOFER | 2019-01-11 |  | 2019-01-11 | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.9667 | 1 | 880.3 | 165.7 | 0 | 48.72 | 665.88 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11906791100 |  | 100342892 |  | V/1222-42 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2600B | COURT | 10 COURT ST | 173 | MT | 2019-01-16 | JTOY | U906631 | 2011-05-16 | 2019-12-31 |  |  | RJJOHNS | 2019-01-11 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.3333 | 1 | 734.88 | 79.68 | 10.11 | 5.19 | 639.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12975911000 |  | 100452354 |  | V/1222-42 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2600B | COURT | 4 COURT ST | 173 | MT | 2019-01-16 | JTOY | U123854 | 2012-06-11 | 2019-12-31 |  |  | RJOHNSON | 2019-01-11 | 2019-01-11 | 2019-01-11 | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.38333 | 1 | 23.59 | 22.14 | 0 | 1.45 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 12984340100 |  | 100262963 |  | 7352260N |  |  |  | 566 | EX | ABANDON / RI 08/16/10 | 2600B | NEWSOME | 697 NEWSOME ST | 019 | ASH | 2019-01-11 | U125573 | U908784 | 2012-08-14 | 2019-01-11 |  |  | BCOFER | 2019-01-11 |  | 2019-01-11 | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.0333 | 1 | 1029.03 | 280.64 | 0 | 82.51 | 665.88 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18642452100 |  | 100341491 |  | 7240212B | 1855043 |  |  | 566 | EX | II- ABANDON SERVICE LINE | 2600B | MAIN | 35 E MAIN ST | 173 | MT | 2019-01-14 | U131002 | U126926 | 2018-09-12 | 2019-12-31 |  |  | RJJOHNS | 2019-01-11 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.4667 | 1 | 829.62 | 147.35 | 32.77 | 9.6 | 639.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18649535500 |  | 100445481 |  | 6740212N |  |  |  | 565 | EX | REPLACE CAT 1 SERVICE | 2621P | WEXFORD | 216 WEXFORD DR | 049 | WIN | 2019-01-11 | LSHARON | JTOY | 2018-10-09 | 2019-01-11 |  |  | LSHARON | 2019-01-11 | 2018-10-09 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26290031 | 23.2333 | 4 | 2163.38 | 1420.15 | 151.25 | 591.98 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18651245600 |  | 100304127 |  | 6712208H |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SAGE | 2129 SAGE RD | 067 | LEX | 2019-01-11 | DBANKS | U125208 | 2018-10-17 | 2019-01-11 | 2020-10-31 |  | DBANKS | 2019-01-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.75 | 1 | 2162.47 | 217.39 | 230.78 | 90.51 | 1623.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18652631900 |  | 100303227 |  | 6712208C |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LILY | 952 LILY DR | 067 | LEX | 2019-01-14 | U131002 | U125208 | 2018-10-23 | 2019-01-11 | 2020-10-31 |  | DBANKS | 2019-01-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.9167 | 1 | 1790.58 | 169.1 | 219.56 | 70.42 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18661715100 |  | 100293570 |  | 6720216N |  |  |  | 565 | EX | NBT - TAP/CL/MTR RELOC | 2621P | NEW CIRCLE | 407 W NEW CIRCLE RD | 067 | LEX | 2019-01-14 | U131002 | U125208 | 2018-12-12 | 2018-12-12 | 2019-01-14 |  | CMCHOLA | 2019-01-11 | 2019-01-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 41.1333 | 5 | 3092.39 | 2385.92 | 551.44 | 155.03 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19667440200 |  | 100342896 |  | 7240212B | 1855043 |  |  | 566 | EX | II -ABANDON OR CO SOII | 2621P | COURT | 2 COURT ST | 173 | MT | 2019-01-14 | U131002 | U126129 | 2019-01-09 | 2019-01-30 | 2019-02-09 |  | IC OFFICE | 2019-01-11 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - CENTRAL | 2629 | 19667440300 |  | 100342898 |  | 7240212B | 1855043 |  |  | 566 | EX | II -ABANDON OR CO SOII | 2621P | COURT | 2 COURT ST | 173 | MT | 2019-01-14 | U131002 | U126129 | 2019-01-09 | 2019-01-30 | 2019-02-09 |  | RJJOHNS | 2019-01-11 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.4667 | 1 | 871.17 | 147.37 | 74.31 | 9.59 | 639.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19668098800 |  | 100284753 |  | 6760172B |  |  |  | 566 | EX | ABANDON LINE | 2621P | PEA RIDGE | 407 PEA RIDGE RD | 065 | IRV | 2019-01-11 | DENNING | U131169 | 2019-01-11 | 2019-01-11 |  |  | DENNING | 2019-01-11 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.75 | 3 | 170.45 | 140.01 | 0 | 30.44 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19668207400 |  | 100241742 |  | 7356252P |  |  |  | 565 | EX | REPLACE SERVICE | 2621P | 52ND | 326 52ND ST | 019 | ASH | 2019-01-11 | BROBERT | U131169 | 2019-01-11 | 2019-01-11 |  |  | BROBERT | 2019-01-11 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.51667 | 1 | 2276.9 | 29.36 | 85.7 | 1.92 | 2159.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19668222100 |  | 100301157 |  | 6716212E |  | U131169 |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | DUNKIRK | 1840 DUNKIRK DR | 067 | LEX | 2019-01-11 | JENSMIN | U131169 | 2019-01-11 | 2019-03-07 | 2020-09-30 |  | JENSMIN | 2019-01-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26210022 | 7.8333 | 1 | 3443.13 | 456.15 | 90.46 | 281.04 | 2615.48 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19668701600 |  | 100342897 |  | 7240212B |  |  |  | 566 | EX | PAPER ABANDON | 2621P | COURT | 2< COURT ST | 173 | MT | 2019-01-14 | U131002 | U131002 | 2019-01-14 | 2019-01-14 |  |  | IC OFFICE | 2019-01-11 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - EAST | 2631 | 10872015700 |  | 100263509 |  | 7352256C |  |  |  | 566 | EX | ABANDON / RI 01-13-2010 | 2600B | LEE | 315 LEE ST | 019 | ASH | 2019-01-14 | U127189 | U906609 | 2010-12-13 | 2019-12-31 |  |  | MATT WILSON | 2019-01-14 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.4667 | 1 | 1871.55 | 80.05 | 0 | 23.86 | 1767.64 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11898476300 |  | 100262560 |  | 7352256D |  |  |  | 566 | EX | ABADNON/ RI 02-2010/ IDLE48MO | 2600B | POLLARD | 2237 POLLARD RD | 019 | ASH | 2019-01-15 | U127189 | U906631 | 2011-03-30 | 2020-12-31 |  |  | MATT WILSON | 2019-01-14 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 7.0333 | 1 | 1473.09 | 385.84 | 0 | 115.01 | 972.24 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11924044600 |  | 100341510 |  | V-1222/42 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2600B | MAYSVILLE | 29< N MAYSVILLE ST | 173 | MT | 2019-01-30 | JTOY | U906631 | 2011-09-12 | 2019-12-31 |  |  | RJJOHNS | 2019-01-14 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.3833 | 1 | 866.05 | 142.59 | 74.31 | 9.25 | 639.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12968590800 |  | 100461797 |  | V/1222-42 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2600B | COURT | 12 COURT ST | 173 | MT | 2019-01-14 | RJJOHNS | U124967 | 2012-05-07 | 2019-12-31 |  |  | RJJOHNS | 2019-01-14 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1 | 1 | 63.78 | 59.9 | 0 | 3.88 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 14258303800 |  | 100263371 |  | 7352256B |  |  |  | 566 | EX | ABANDON SL | 2600B | OHIO | 2927 OHIO ST | 019 | ASH | 2019-01-15 | U125573 | U125201 | 2014-10-17 | 2019-01-14 |  |  | BCOFER | 2019-01-14 | 2019-01-14 | 2019-01-14 | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 9.5 | 1 | 1351.74 | 530.04 | 0 | 155.82 | 665.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18026798100 |  |  |  | 6680228G | 1855977 | U122858 |  | 557 | EX | INSTALL 2" SS FITTING | 2600B | CLIFTON DR | CLIFTON DR | 073 | FRA | 2019-01-16 | U131296 | U122858 | 2018-09-28 | 2019-05-30 | 2019-05-31 | 2019-01-14 | BJACKSON | 2019-01-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP7981 |  |  | 100 | 055732180267981 | 11 | 0 | 8906.34 | 707.19 | 306.09 | 190.22 | 6559.54 | 0 | 17.06 | 1126.24
KY | KY - WEST | 2623 | 18026798200 |  |  |  | 6680228G | 1855977 | U122858 |  | 558 | EX | RETIRE 39'-2" CSMP | 2600B | CLIFTON DR | CLIFTON DR | 073 | FRA | 2019-01-16 | U131296 | U122858 | 2018-09-28 | 2019-05-31 | 2019-05-31 | 2019-01-14 | BJACKSON | 2019-01-14 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP7982 |  |  | 100 | 055832180267982 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18636016600 |  | 100342040 |  | 7240216N | 1855043 |  |  | 566 | EX | II - ABANDON ON SOII | 2600B | JOHNSON | 10 JOHNSON AV | 173 | MT | 2019-02-27 | JTOY | U126129 | 2018-08-17 | 2019-12-31 |  |  | RJJOHNS | 2019-01-14 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.0833 | 1 | 783.13 | 64.69 | 74.31 | 4.23 | 639.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18636020100 |  | 100343758 |  | 7240212B | 1855043 | U126129 |  | 566 | EX | II - ABANDON ON SOII | 2600B | APPERSON | 114 APPERSON HT | 173 | MT | 2019-02-26 | JTOY | U126129 | 2018-08-17 | 2019-12-31 |  |  | RJJOHNS | 2019-01-14 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.3833 | 1 | 1217.18 | 202.48 | 74.31 | 13.14 | 927.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18636020200 |  | 100342551 |  | 7240216N | 1855043 |  |  | 566 | EX | II - ABANDON ON SOII | 2600B | HOLT | 409 HOLT AV | 173 | MT | 2019-01-14 | RJJOHNS | U126129 | 2018-08-17 | 2019-12-31 |  |  | RJJOHNS | 2019-01-14 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.15 | 1 | 788.21 | 69.48 | 74.31 | 4.52 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18651931500 |  | 100303698 |  | 6712208D |  | U125208 |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | DOGWOOD | 2080 DOGWOOD DR | 067 | LEX | 2019-01-15 | U131002 | U125208 | 2018-10-19 | 2019-01-14 | 2020-10-31 |  | JENSMIN | 2019-01-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.3333 | 1 | 2813.3 | 194.22 | 280.48 | 119.65 | 2218.95 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19667404600 |  | 100258977 |  | 7356256A |  |  |  | 565 | EX | RELOCATE SERVICE LINE | 2621P | 15TH | 707 15TH ST | 019 | ASH | 2019-01-14 | MCOLLET | U131392 | 2019-01-09 | 2019-01-31 |  |  | MCOLLET | 2019-01-14 | 2019-01-11 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 19.2333 | 5 | 2154.86 | 1208.73 | 137.58 | 808.55 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19668689600 |  | 100253531 |  | 7364188G |  |  |  | 566 | EX | ABD SVC LINE | 2621P | FLUTY LICK | 357 FLUTY LICK RD | 159 | LOU | 2019-01-15 | U131002 | U130193 | 2019-01-14 | 2019-01-14 |  |  | CHAMMON | 2019-01-14 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.2167 | 1 | 83.14 | 78.06 | 0 | 5.08 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19668798200 |  | 100251874 |  | 7328284B |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | MAIN | 204 MAIN ST | 089 | S S | 2019-01-15 | U131002 | U130193 | 2019-01-14 | 2019-01-14 | 2019-01-14 |  | DESKAGG | 2019-01-14 | 2019-01-14 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 3.4833 | 2 | 578.13 | 216.2 | 258.16 | 103.77 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19668826700 |  | 100413930 |  | 6704208E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CYPRESS | 188 CYPRESS DR | 239 | VER | 2019-01-15 | U131002 | U131168 | 2019-01-14 | 2019-01-14 | 2019-01-14 |  | EFGOINS | 2019-01-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.25 | 1 | 3376.8 | 241.47 | 154.27 | 15.11 | 2965.95 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19673629500 |  | 100341511 |  | 7240212B |  |  |  | 566 | EX | ABANDON W/100341510 | 2621P | MAYSVILLE | 29 N MAYSVILLE ST | 173 | MT | 2019-01-30 | JTOY | JTOY | 2019-01-30 | 2019-01-14 |  |  | BJOHNSON | 2019-01-14 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - EAST | 2631 | 07680139800 |  | 100458347 |  | ? |  |  |  | 566 | EX | ABANDON SL - IDLE 24 MONTHS | 2600B | COUNTRY CLUB | 104 COUNTRY CLUB DR | 089 | ASH | 2019-01-15 | U127189 | SSUTHER | 2007-03-23 | 2019-12-31 |  |  | MATT WILSON | 2019-01-15 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.6167 | 1 | 1311.86 | 143.63 | 0 | 42.81 | 1125.42 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 10869457600 |  | 100360007 |  | 16740232M | 1855043 |  |  | 566 | EX | SOII - METER ABANDON ONLY | 2600B | MAIN | 420 MAIN ST | 017 | PAR | 2019-01-16 | U131002 | U906307 | 2010-11-23 | 2019-12-31 |  |  | RJJOHNS | 2019-01-15 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.8167 | 1 | 764.39 | 108.45 | 8.98 | 7.06 | 639.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11919715900 |  | 100267148 |  | 7352260N |  |  |  | 566 | EX | ABANDON SERV IDLE 36 MO | 2600B | HOODS CREEK | 2301 HOODS CREEK PK | 019 | ASH | 2019-01-15 | U127189 | U124449 | 2011-08-10 | 2020-12-31 |  |  | MATT WILSON | 2019-01-15 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 6.3833 | 1 | 2107.32 | 349.69 | 0 | 104.25 | 1653.38 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11930216800 |  | 100265442 |  | 7352256E |  |  |  | 566 | EX | ABANDON / RA 10-28-2009 | 2600B | MIDLAND TRAIL | 6512 MIDLAND TRAIL RD | 019 | ASH | 2019-01-16 | U125573 | U125208 | 2011-10-25 | 2020-12-31 |  |  | BCOFER | 2019-01-15 |  | 2019-01-15 | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 665.88 | 0 | 0 | 0 | 665.88 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12968023400 |  | 100341512 |  | V-1222/42 | 1855043 |  |  | 566 | EX | ABANDON W/ 100341510 | 2600B | MAYSVILLE | 29 N MAYSVILLE ST | 173 | MT | 2019-01-15 | RJJOHNS | U124967 | 2012-05-02 | 2019-12-31 |  |  | RJJOHNS | 2019-01-15 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.5167 | 1 | 96.34 | 90.46 | 0 | 5.88 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12968023900 |  | 100342895 |  | V/1222-42 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2600B | COURT | 8 COURT ST | 173 | MT | 2019-01-15 | RJJOHNS | U124967 | 2012-05-02 | 2019-12-31 |  |  | RJJOHNS | 2019-01-15 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.78333 | 0 | 51.05 | 47.93 | 0 | 3.12 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12975888800 |  | 100360151 |  | 16740232M | 1855043 |  |  | 566 | EX | SOII - ABANDON / RI 08-30-2011 | 2600B | MAIN | 517 MAIN ST | 017 | PAR | 2019-01-15 | RJJOHNS | U123854 | 2012-06-11 | 2019-12-31 |  |  | RJJOHNS | 2019-01-15 | 2018-07-19 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.0333 | 2 | 903.38 | 241.16 | 6.69 | 15.63 | 639.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18626832400 |  | 100268102 |  | 7356256B |  |  |  | 566 | EX | ABANDON / RA 11/17/2017 | 2600B | GREENUP | 2236 GREENUP AV | 019 | ASH | 2019-01-16 | U125573 | U125208 | 2018-07-12 | 2019-01-15 |  |  | BCOFER | 2019-01-15 | 2019-01-15 | 2019-01-15 | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 18 | 2 | 3003.26 | 1004.29 | 0 | 295.29 | 1703.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18662762300 |  | 100328455 |  | 6720208F | 1859893 |  |  | 565 | EX | SERVICE LINE UPGRADE | 2621P | CLINTON | 517 CLINTON RD | 067 | LEX | 2019-01-15 | DBANKS | U128293 | 2018-12-17 | 2019-01-17 | 2019-01-17 |  | DBANKS | 2019-01-15 | 2019-01-07 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 18.2333 | 3 | 7266.58 | 1002.33 | 352.55 | 287.67 | 5624.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18663270700 |  | 100306523 |  | 6716212M |  |  |  | 565 | EX | SERVICE LINE/METER RELOCATION | 2621P | COLD HARBOR | 1724 COLD HARBOR DR | 067 | LEX | 2019-01-15 | ATWILLI | U128293 | 2018-12-19 | 2019-01-18 |  |  | ATWILLI | 2019-01-15 | 2019-01-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.1333 | 5 | 1088.4 | 996.49 | 27.18 | 64.73 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18664356400 |  | 100282177 |  | 6712228C |  |  |  | 566 | EX | ABANDON SL FOR DEMO PS MAILBOX | 2621P | WASHINGTON | 335 E WASHINGTON ST | 209 | GEO | 2019-01-15 | RVANDER | U131800 | 2018-12-28 | 2019-03-07 | 2019-03-07 |  | RVANDER | 2019-01-15 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 2.6667 | 2 | 154.06 | 144.64 | 0 | 9.42 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18664358500 |  | 100283094 |  | 6712228G |  |  |  | 566 | EX | ABANDON SL FOR DEMO PS MAILBOX | 2621P | OLD LEMONS MIL | 519 OLD LEMONS MIL RD | 209 | GEO | 2019-01-16 | U131002 | U131800 | 2018-12-28 | 2019-03-07 | 2019-03-07 |  | RVANDER | 2019-01-15 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 7.7333 | 2 | 494.83 | 454.09 | 11.24 | 29.5 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19668687000 |  | 100279310 |  | 6688228K |  |  |  | 565 | EX | REPL SVC LINE | 2621P | MCDOWELL | 461 MCDOWELL AV | 073 | FRA | 2019-01-15 | CDESPAI | U125964 | 2019-01-14 | 2019-01-31 |  |  | CDESPAI | 2019-01-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.9833 | 1 | 4526.44 | 468.71 | 147.7 | 274.27 | 3635.76 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19668814300 |  | 100258322 |  | 7348264O |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | DANIELS | 829 DANIELS DR | 089 | WOR | 2019-01-16 | U131002 | U130193 | 2019-01-14 | 2019-01-14 | 2019-01-14 |  | AMCCORM | 2019-01-15 | 2019-01-14 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 16.2 | 5 | 1545.82 | 975.25 | 172.17 | 398.4 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19668934000 |  | 100253533 |  | 7364188G |  |  |  | 566 | EX | ABD LINE | 2621P | KY FIELD | KY FIELD | 159 | INE | 2019-01-16 | U131002 | U130193 | 2019-01-15 | 2019-01-15 |  |  | JCKIRK | 2019-01-15 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.4167 | 1 | 85.09 | 79.89 | 0 | 5.2 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 07680142600 |  | 100405591 |  | T-1726-43 |  |  |  | 566 | EX | ABANDON SL - IDLE 24 MONTHS | 2621P | STATE RT 207 | STATE RT 207 | 089 | FLA | 2019-01-16 | BROBERT | SSUTHER | 2007-03-23 | 2014-12-31 |  |  | BROBERT | 2019-01-16 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.85 | 1 | 2699.22 | 220.92 | 0 | 14.37 | 2463.93 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 07685169100 |  | 100359274 | 12 | 16740232M | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2600B | 8TH | 405 W 8TH ST | 017 | PAR | 2019-01-16 | RJJOHNS | PMCNABB | 2007-05-01 | 2019-12-31 |  |  | RJJOHNS | 2019-01-16 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.7667 | 1 | 957.37 | 105.43 | 32.77 | 6.86 | 812.31 | 0 | 0 | 0
KY | KY - EAST | 2631 | 07691587400 |  | 100264164 | 35 | 7352256-B |  |  |  | 566 | EX | ABANDON COMPANY SERVICE LINE | 2600B | OLD BUCKLEY | 635 W OLD BUCKLEY RD | 019 | ASH | 2019-01-16 | U127189 | DHORN | 2007-06-20 | 2020-12-31 |  |  | MATT WILSON | 2019-01-16 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.3833 | 1 | 1386.68 | 240.6 | 0 | 71.72 | 1074.36 | 0 | 0 | 0
KY | KY - EAST | 2631 | 08735955700 |  | 500579535 |  | 73482640 | 9723038 |  |  | 566 | EX | ABANDON SL PER IDLE MEMO | 2621P | ARGILLITE | 2000 ARGILLITE RD 3 | 089 | FLA | 2019-01-16 | BROBERT | SSUTHER | 2008-06-20 | 2014-12-23 |  |  | BROBERT | 2019-01-16 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.65 | 1 | 779.09 | 37.39 | 1.38 | 18.43 | 721.89 | 0 | 0 | 0
KY | KY - EAST | 2631 | 08737011100 |  | 100255606 |  | 7348264-H |  |  |  | 566 | EX | ABANDON SL PER IDLE MEMO | 2621P | 1ST | 514 N 1ST ST | 089 | FLA | 2019-01-16 | BROBERT | SSUTHER | 2008-06-26 | 2019-01-16 |  |  | BROBERT | 2019-01-16 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.46667 | 1 | 1609.43 | 26.5 | 63.54 | 1.72 | 1517.67 | 0 | 0 | 0
KY | KY - EAST | 2631 | 08743718000 |  | 100255544 |  | 7348264-K |  |  |  | 566 | EX | ABANDON SL PER IDLE MEMO | 2621P | WHEELER | 1214 WHEELER ST | 089 | FLA | 2019-01-16 | BROBERT | SSUTHER | 2008-08-07 | 2019-01-16 |  |  | BROBERT | 2019-01-16 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.18333 | 1 | 2574.46 | 10.35 | 11.24 | 0.67 | 2552.2 | 0 | 0 | 0
KY | KY - EAST | 2631 | 10870897900 |  | 500497630 |  | 7352256L |  |  |  | 566 | EX | ABANDON SERVICE | 2600B | MCCLELLAND | 3167 MCCLELLAND ST | 019 | ASH | 2019-01-16 | U125573 | U906307 | 2010-12-06 | 2020-12-31 |  |  | BCOFER | 2019-01-16 |  | 2019-01-16 | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 665.88 | 0 | 0 | 0 | 665.88 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11921078400 |  | 100248694 |  | 7356256E |  |  |  | 566 | EX | ABANDON SERV / RI 08-24-2009 | 2600B | MOORE | 2111 MOORE ST | 019 | ASH | 2019-01-16 | U127189 | U124449 | 2011-08-22 | 2020-12-31 |  |  | MATT WILSON | 2019-01-16 | 2019-01-16 | 2019-01-16 | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.1167 | 1 | 1437.94 | 280.08 | 0 | 83.5 | 1074.36 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12975868800 |  | 100342894 |  | V/1222-42 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2600B | COURT | 6 COURT ST | 173 | MT | 2019-01-16 | RJJOHNS | U123854 | 2012-06-11 | 2019-12-31 |  |  | RJJOHNS | 2019-01-16 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.8167 | 1 | 115.51 | 108.45 | 0 | 7.06 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12975887500 |  | 100359733 |  | 16740232M | 1855043 |  |  | 566 | EX | SOII - ABANDON / RI 12-06-2011 | 2600B | HIGH | 524 HIGH ST | 017 | PAR | 2019-01-16 | RJJOHNS | U123854 | 2012-06-11 | 2019-12-31 |  |  | RJJOHNS | 2019-01-16 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.4833 | 1 | 807.98 | 88.05 | 74.31 | 5.72 | 639.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 12988319900 |  | 100255710 |  | 7348264G |  |  |  | 566 | EX | ABANDON / RA 9-7-10 | 2621P | 4TH | 509 N 4TH ST | 089 | FLA | 2019-01-16 | BROBERT | U125208 | 2012-09-13 | 2020-12-31 |  |  | BROBERT | 2019-01-16 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.43333 | 1 | 749.6 | 24.72 | 1.38 | 1.61 | 721.89 | 0 | 0 | 0
KY | KY - EAST | 2631 | 12992728800 |  | 100254155 | 29 | T1726/36 |  |  |  | 566 | EX | ABANDON / RA 10-11-12 | 2621P | COLLINS | 1410 W COLLINS ST | 089 | FLA | 2019-01-16 | BROBERT | SJUDE | 2012-10-11 | 2020-12-31 |  |  | BROBERT | 2019-01-16 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.25 | 1 | 748.46 | 14.4 | 11.24 | 0.93 | 721.89 | 0 | 0 | 0
KY | KY - EAST | 2631 | 14258063900 |  | 100248152 |  | 7356256I |  |  |  | 566 | EX | ABANDON SL | 2600B | SELLARS | 2325 SELLARS ST | 019 | ASH | 2019-01-18 | U125573 | U125201 | 2014-10-16 | 2019-12-31 |  |  | BCOFER | 2019-01-16 |  | 2019-01-16 | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 1496.12 | 0 | 0 | 0 | 1496.12 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18026778601 |  | 501242346 |  | 6716232M | 1853461 | U128885 |  | 555 | EX | INSTALL 3100' - 2"/4" PMMP | 2600B | SINCLAIR | SINCLAIR CT LT84 | 209 | GEO | 2019-05-10 | U131296 | U128885 | 2019-01-18 | 2018-10-09 | 2019-01-31 | 2019-01-16 | JDUNN | 2019-01-16 | 2018-10-15 | 2018-10-15 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP7786 |  |  | 100 | 055532180267786 | 276.7167 | 99584 | 112278.35 | 16114 | 8513.83 | 2979.67 | 68949.01 | 0 | 639.53 | 15082.31 | 3112
KY | KY - CENTRAL | 2629 | 18636018900 |  | 100360111 |  | 6740232M | 1855043 |  |  | 566 | EX | II - ABANDON ON SOII | 2600B | MAIN | 723 MAIN ST | 017 | PAR | 2019-02-05 | JTOY | U126129 | 2018-08-17 | 2019-12-31 |  |  | RJJOHNS | 2019-01-16 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.8167 | 1 | 774.51 | 108.45 | 19.1 | 7.06 | 639.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18653645200 |  | 500031046 |  | 6740232M | 1855043 |  |  | 566 | EX | II - ABANDON OR CO SOII | 2600B | MAIN | 418 MAIN ST | 017 | PAR | 2019-01-16 | U131002 | U126129 | 2018-10-26 | 2019-12-31 |  |  | IC OFFICE | 2019-01-16 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1
KY | KY - WEST | 2621 | 18661475500 |  | 100323185 |  | 6716208P | 1859238 |  |  | 565 | EX | NBT - SL/MTR UPG 110' 1-1/14" | 2621P | SHERWOOD | 798 SHERWOOD DR | 067 | LEX | 2019-01-16 | DBANKS | U125208 | 2018-12-11 | 2018-12-10 | 2019-01-10 |  | DBANKS | 2019-01-16 | 2019-01-15 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 12.5 | 4 | 5877.8 | 703.07 | 269.06 | 229.26 | 4676.41 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19026855100 |  | 501255493 |  | 6748208K | 1960457 | U127466 |  | 555 | EX | INSTALL 50' - 2" PMMP | 2621P | VANOVER | 320 VANOVER WY | 049 | WIN | 2019-03-11 | U129900 | U127466 | 2019-01-09 | 2019-03-07 | 2019-03-08 | 2019-01-16 | 125572 | 2019-01-16 | 2019-01-16 | 2019-01-16 | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP8551 |  |  | 100 | 055532190268551 | 25.4667 | 240 | 7816.21 | 1501.97 | 0 | 333.86 | 4980.34 | 0 | 3.58 | 996.46 | 40
KY | KY - EAST | 2633 | 19668785000 |  | 100241959 |  | 7344168K |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | EVERGREEN | 55 N EVERGREEN LN | 071 | LNC | 2019-01-16 | BBMULLI | U131002 | 2019-01-14 | 2019-01-17 | 2019-02-04 |  | BBMULLI | 2019-01-16 |  |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 16 | 2 | 1364.24 | 942.39 | 172.98 | 248.87 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19668888000 |  | 100407690 |  | 6716208M |  |  |  | 565 | EX | SERVICE LINE REPLACE | 2621P | RUNNYMEADE | 2992 RUNNYMEADE WY | 067 | LEX | 2019-02-01 | U125208 | U131739 | 2019-01-15 | 2019-01-15 | 2019-01-15 |  | RVANDER | 2019-01-16 | 2019-01-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.6833 | 4 | 1431.15 | 1343.96 | 0 | 87.19 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11930214100 |  | 100360159 |  | 16740232M | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2600B | 5TH | 11 W 5TH ST | 017 | PAR | 2019-01-17 | RJJOHNS | U125208 | 2011-10-25 | 2019-12-31 |  |  | RJJOHNS | 2019-01-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.5667 | 1 | 908.73 | 153.38 | 105.49 | 9.96 | 639.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12975888900 |  | 100360168 |  | 16740232M | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2600B | 5TH | 10 W 5TH ST | 017 | PAR | 2019-02-05 | JTOY | U123854 | 2012-06-11 | 2019-12-31 |  |  | RJJOHNS | 2019-01-17 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.3667 | 1 | 895.94 | 141.37 | 105.49 | 9.18 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 17026717800 |  |  |  | 6684232O | 1744612 | U127466 |  | 587 | EX | INSTALL GMB SETTING | 2600M | US 127NORTH | 5701 US 127NORTH | 073 | FRA | 2019-01-24 | U462463 | U127466 | 2017-07-18 | 2017-10-31 | 2017-11-01 | 2017-12-11 | CYNTHIA FARIS | 2019-01-17 | 2017-10-18 | 2017-10-18 | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00587 | 3200587 |  |  | WP7178 |  |  | 100 | 058732170267178 | 235.6667 | 672 | 154867.73 | 14123.2 | 49617.48 | 2721.99 | 40852.18 | 0 | 287.24 | 47265.64
KY | KY - WEST | 2623 | 18599689700 |  | 100466138 |  | 6700212M |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SECRETARIAT | 6017 SECRETARIAT CR | 239 | VER | 2019-01-21 | U131002 | U125208 | 2018-04-02 | 2018-09-26 | 2020-03-31 |  | RVANDER | 2019-01-17 | 2019-01-16 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8.4 | 4 | 538.98 | 497.27 | 9.37 | 32.34 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18642594700 |  | 100320213 |  | 6716208G |  |  |  | 566 | EX | DEMO / ABANDON / RA 09-13-18 | 2621P | SHADY | 218 SHADY LN | 067 | LEX | 2019-01-17 | CMCHOLA | U129799 | 2018-09-12 | 2018-10-12 | 2018-10-13 |  | CMCHOLA | 2019-01-17 | 2018-09-17 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.2833 | 3 | 376.92 | 315.16 | 41.54 | 20.22 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19669359700 |  | 100345643 |  | 6696212C |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | MOLLY | 104 MOLLY ST | 239 | VER | 2019-01-21 | U131002 | U130193 | 2019-01-16 | 2019-01-16 | 2019-01-16 |  | RVANDER | 2019-01-17 | 2019-01-16 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 12.8833 | 3 | 994.18 | 740.21 | 205.91 | 48.06 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19669602300 |  | 100349515 |  | 6744208P |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LEXINGTON | 23 E LEXINGTON AV 1 | 049 | WIN | 2019-01-17 | DENNING | U124447 | 2019-01-17 | 2019-01-16 | 2019-01-16 |  | DENNING | 2019-01-17 | 2019-01-16 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 59.75 | 6 | 5321.06 | 3434.53 | 174.26 | 465.12 | 1247.15 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19669659300 |  | 100464620 |  | 6716212H |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | SHORT | 541 W SHORT ST 21 | 067 | LEX | 2019-01-21 | U131002 | U131365 | 2019-01-17 | 2019-01-17 | 2019-01-17 |  | KKINDER | 2019-01-17 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.4 | 2 | 802.06 | 582.66 | 181.54 | 37.86 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19669674700 |  | 500012328 |  | 7364188G |  |  |  | 566 | EX | ABANDON SERVICELINE | 2621P | KY FIELD | KY FIELD | 159 | INE | 2019-01-21 | U131002 | U131365 | 2019-01-17 | 2019-01-17 |  |  | CHAMMON | 2019-01-17 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.98333 | 1 | 67.84 | 63.71 | 0 | 4.13 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 02495975800 |  | 100292387 | 20 | X00000000 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | THURMAN | 521 THURMAN DR | 067 | LEX | 2019-01-18 | JENSMIN | RSTOKLE | 2002-01-30 | 2014-12-23 |  |  | JENSMIN | 2019-01-18 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.16667 | 1 | 665.82 | 9.35 | 10.81 | 5.76 | 639.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 07671553400 |  | 100285176 |  | 6756176O |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | WINSTON | 1025 WINSTON RD | 065 | WIN | 2021-01-19 | U461309 | SKSMITH | 2007-01-08 | 2021-12-30 |  |  | R.HUMPHREYS | 2019-01-18 | 2021-01-18 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 22.1 | 3 | 2050.82 | 1255.06 | 0 | 203.51 | 592.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 09794538200 |  | 100292268 | 33 | ? | 1855043 |  |  | 566 | EX | SOII - ABANDON SERV/ RI 7-2009 | 2621P | LIN WAL | 413 LIN WAL DR | 067 | LEX | 2019-01-18 | JENSMIN | JMMCDON | 2009-07-07 | 2019-01-18 |  |  | JENSMIN | 2019-01-18 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.18333 | 1 | 709.24 | 10.51 | 52.36 | 6.47 | 639.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 09807803500 |  | 100242261 |  | 7356252H |  |  |  | 566 | EX | ABD S/L-IDLE 36MO MEMO 091809 | 2621P | HORSE BRANCH | 337 HORSE BRANCH RD | 019 | CAT | 2019-01-18 | BROBERT | RPOLLY | 2009-10-14 | 2019-01-18 |  |  | BROBERT | 2019-01-18 | 2018-09-14 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 16.5167 | 5 | 3230.86 | 926.58 | 11.24 | 317.47 | 1975.57 | 0 | 0 | 0
KY | KY - EAST | 2631 | 09809407700 |  | 100249829 |  | 7356248H |  |  |  | 566 | EX | ABD S/L-IDLE 36MO MEMO 101909 | 2621P | PADDLE CREEK | 8131 PADDLE CREEK RD | 019 | CAT | 2019-01-18 | BROBERT | RPOLLY | 2009-10-27 | 2019-01-18 |  |  | BROBERT | 2019-01-18 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.7667 | 1 | 1010.06 | 101.26 | 69.52 | 6.59 | 832.69 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11916882000 |  | 100292440 |  | 6720216O | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | SOUTHRIDGE | 520 SOUTHRIDGE DR | 067 | LEX | 2019-01-18 | JENSMIN | U124964 | 2011-07-21 | 2014-12-23 |  |  | JENSMIN | 2019-01-18 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.28333 | 1 | 675.26 | 16.32 | 8.98 | 10.06 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11925999600 |  | 100292279 |  | 00NEW | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | LIN WAL | 453 LIN WAL DR | 067 | LEX | 2019-01-25 | U125208 | U125208 | 2011-09-22 | 2019-01-18 |  |  | JENSMIN | 2019-01-18 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.8 | 1 | 767.69 | 46.67 | 52.36 | 28.76 | 639.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12975887900 |  | 100360038 |  | 6740232M |  |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | MAIN | 610 MAIN ST | 017 | PAR | 2019-01-18 | RJJOHNS | U123854 | 2012-06-11 | 2017-12-29 | 2018-06-08 |  | RJJOHNS | 2019-01-18 | 2018-11-06 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.1167 | 3 | 918.37 | 245.43 | 15.68 | 17.36 | 639.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 14257817800 |  | 500346060 |  | 7352260O |  |  |  | 566 | EX | ABANDON SL | 2600B | WHEATLEY | 319< WHEATLEY RD | 019 | ASH | 2019-01-18 | U127189 | U125201 | 2014-10-15 | 2019-12-31 |  |  | MATT WILSON | 2019-01-18 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.4333 | 1 | 1319.11 | 188.54 | 0 | 56.21 | 1074.36 | 0 | 0 | 0
KY | KY - EAST | 2631 | 14258303400 |  | 100265841 |  | 7348252D |  |  |  | 566 | EX | ABANDON SL | 2600B | OAKLEY | 6118 OAKLEY ST | 019 | ASH | 2019-01-18 | U127189 | U125201 | 2014-10-17 | 2019-12-31 |  |  | MATT WILSON | 2019-01-18 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.5667 | 1 | 1531.73 | 249.92 | 0 | 74.49 | 1207.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18026798900 |  | 501249780 |  | 6728204K | 1856104 | U461383 |  | 555 | EX | INSTALL 625' OF 2"PMMP MAIN | 2600B | UNITED | 401 UNITED CT LT | 067 | LEX | 2019-01-31 | U129900 | U461383 | 2018-10-03 | 2019-01-16 | 2019-01-18 | 2019-01-18 | STEVE CANOY | 2019-01-18 | 2019-01-02 | 2019-01-02 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP7989 |  |  | 100 | 055532180267989 | 108.3667 | 8190 | 33732.14 | 6129.79 | 1424.24 | 1644.74 | 20209.77 | 0 | 52.49 | 4271.11 | 630
KY | KY - EAST | 2631 | 18026848400 |  | 501248731 |  | 7352260F |  | U122858 |  | 555 | EX | INSTALL 80'-2" PMMP | 2600E | RUSSELL PLAZA | 480 RUSSELL PLAZA DR | 089 | ASH | 2019-01-28 | U129900 | U122858 | 2018-12-14 | 2018-12-20 | 2018-12-30 | 2018-12-19 | AMCCORM | 2019-01-18 | 2018-12-19 | 2018-12-19 | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP8484 |  |  | 100 | 055532180268484 | 31.85 | 803 | 3124.34 | 2074.09 | 0 | 621.16 | 0 | 0 | 4.45 | 424.64 | 73
KY | KY - WEST | 2621 | 18621205700 |  | 100322852 |  | 6720208E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | TATES CREEK | 1550 TATES CREEK RD | 067 | LEX | 2019-01-25 | U125208 | U125208 | 2018-06-19 | 2018-12-18 | 2020-06-30 |  | CWEMPE | 2019-01-18 | 2019-01-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 48.3667 | 8 | 4146.22 | 2426.78 | 431.21 | 191.39 | 1096.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18636019100 |  | 100359328 |  | 6736232P | 1855043 |  |  | 566 | EX | II - ABANDON ON SOII | 2600B | VIRGINIA | 114 VIRGINIA AV | 017 | PAR | 2019-02-13 | U125208 | U126129 | 2018-08-17 | 2019-12-31 |  |  | RJJOHNS | 2019-01-18 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.4833 | 1 | 1657.71 | 208.45 | 105.49 | 13.55 | 1330.22 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18636021100 |  | 100360135 |  | 6740232M | 1855043 |  |  | 566 | EX | II - ABANDON ON SOII | 2600B | HIGH | 610 HIGH ST | 017 | PAR | 2019-01-18 | RJJOHNS | U126129 | 2018-08-17 | 2019-12-31 |  |  | RJJOHNS | 2019-01-18 | 2019-01-17 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.55 | 2 | 98.24 | 92.23 | 0 | 6.01 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18663068100 |  | 100325510 |  | 6720208E |  |  |  | 565 | EX | SERVICE LINE/METER UPGRADE | 2621P | INDIAN MOUND | 1229 INDIAN MOUND RD | 067 | LEX | 2019-01-18 | DBANKS | U128293 | 2018-12-18 | 2018-01-18 |  |  | DBANKS | 2019-01-18 | 2019-01-17 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 6.8833 | 2 | 6297.77 | 399.87 | 609.7 | 166.45 | 5121.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18663069000 |  | 100325845 |  | 6720208E |  |  |  | 565 | EX | SERVICE LINE/METER UPGRADE | 2621P | COLONY | 332 COLONY BV | 067 | LEX | 2019-01-18 | DBANKS | U128293 | 2018-12-18 | 2019-01-18 | 2019-01-18 |  | DBANKS | 2019-01-18 | 2019-01-16 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 10.7167 | 4 | 3412.92 | 586.15 | 264.39 | 138.54 | 2423.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19666893600 |  | 100294274 |  | 6720212A |  |  |  | 566 | EX | ABANDON SL FOR DEMO PS MAILBOX | 2621P | HEADLEY | 662 HEADLEY AV | 067 | LEX | 2019-01-18 | LMCDONA | U130722 | 2019-01-07 | 2019-02-21 | 2019-03-14 |  | LMCDONA | 2019-01-18 | 2019-01-17 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 22.1333 | 5 | 1111.74 | 1042.64 | 1.38 | 67.72 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19670121100 |  | 100295574 |  | 6716216L |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | REDWOOD | 1079 REDWOOD DR | 067 | LEX | 2019-01-18 | CMCHOLA | U131169 | 2019-01-18 | 2019-01-18 | 2019-02-06 |  | CMCHOLA | 2019-01-18 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.3 | 2 | 1102.34 | 839.2 | 208.71 | 54.43 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19670073100 |  | 100348870 |  | 6748208N |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | CRAWFORD | 113 CRAWFORD AV | 049 | WIN | 2019-01-25 | U125208 | U125964 | 2019-01-18 | 2019-01-31 |  |  | DENNING | 2019-01-19 | 2019-01-18 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 14.65 | 7 | 1132.27 | 778.08 | 225.39 | 128.8 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 03536370000 |  | 100240981 | 18 | 7324132F |  |  |  | 566 | EX | ABANDON / RI 04-03-2002 | 2600B | SR550 | SR550 | 119 | HIN | 2019-01-21 | JCKIRK | BFMULLI | 2003-04-08 | 2049-12-31 |  |  | JCKIRK | 2019-01-21 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.1 | 2 | 72.01 | 63.62 | 0 | 8.39 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18660667000 |  | 100340264 |  | 6724212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | RALEIGH | 1774 RALEIGH RD | 067 | LEX | 2019-01-28 | U131002 | U125208 | 2018-12-05 | 2019-06-05 | 2020-12-31 |  | KKINDER | 2019-01-21 | 2019-01-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.0333 | 5 | 859.58 | 807.12 | 0 | 52.46 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19668937800 |  | 100259520 |  | 7348264B |  |  |  | 566 | EX | ABANDON SL FOR DEMO | 2621P | HOFFMAN | 1013 HOFFMAN AV | 089 | WOR | 2019-01-21 | DESKAGG | U130722 | 2019-01-15 | 2019-01-21 |  |  | DESKAGG | 2019-01-21 | 2019-01-21 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 10.4167 | 3 | 1034.2 | 636.4 | 63.54 | 334.26 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19669116300 |  | 100320293 |  | 6716208G |  |  |  | 566 | EX | PAPER ABD PSID: 100320293 | 2621P | NICHOLASVILLE | 1828 NICHOLASVILLE RD 2F | 067 | LEX | 2019-01-21 | CMCHOLA | U125964 | 2019-01-15 | 2019-01-18 |  |  | CMCHOLA | 2019-01-21 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.28333 | 1 | 15.86 | 14.9 | 0 | 0.96 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19670849600 |  | 100267682 |  | 7328284K |  |  |  | 565 | EX | REPLACE SERV LINE | 2621P | STATE RT 784 | 464 STATE RT 784 | 089 | S S | 2019-01-21 | MCOLLET | U129939 | 2019-01-19 | 2019-01-19 | 2019-01-19 |  | MCOLLET | 2019-01-21 | 2019-01-19 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 19.1833 | 6 | 1605.95 | 1163.97 | 208.89 | 233.09 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19670931300 |  | 100249926 |  | 7360248E |  |  |  | 566 | EX | ABD LINE | 2621P | FIFTH | 1042 FIFTH ST | 019 | CAT | 2019-01-21 | BROBERT | U131010 | 2019-01-21 | 2019-01-21 |  |  | BROBERT | 2019-01-21 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.23333 | 1 | 16.81 | 13.24 | 0 | 3.57 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 06660316900 |  | 100293840 |  | 6720212A | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | MCCLAIN | 1105 MCCLAIN DR | 067 | LEX | 2019-01-22 | JENSMIN | SSUTHER | 2006-09-15 | 2014-12-23 |  |  | JENSMIN | 2019-01-22 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.1333 | 1 | 798.78 | 65.91 | 52.36 | 40.61 | 639.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 07682753500 |  | 100242150 | 36 | U-1708-38 |  |  |  | 566 | EX | ABANDON COMPANY SERVICE LINE | 2621P | 10TH | 331 10TH ST | 019 | CAT | 2019-01-22 | BROBERT | BCHATTE | 2007-04-12 | 2014-12-31 |  |  | BROBERT | 2019-01-22 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.7 | 1 | 2158.48 | 98.95 | 69.52 | 6.44 | 1983.57 | 0 | 0 | 0
KY | KY - EAST | 2631 | 07691496400 |  | 100263998 | 24 | ? |  |  |  | 566 | EX | ABANDON COMPANY SERVICE LINE | 2600B | MAIN | 1902 MAIN ST W | 019 | ASH | 2019-01-22 | U127189 | DHORN | 2007-06-19 | 2019-12-31 |  |  | MATT WILSON | 2019-01-22 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.9333 | 1 | 1230.59 | 160.59 | 0 | 47.9 | 1022.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 07698886700 |  | 100417888 | 40 | 7352256-G |  |  |  | 566 | EX | ABANDON COMPANY SERVICE LINE | 2600B | ROBERTS | 3308 ROBERTS DR 1 | 019 | ASH | 2019-01-22 | U127189 | JWHEATL | 2007-08-17 | 2020-12-23 |  |  | MATT WILSON | 2019-01-22 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.7 | 1 | 2345.15 | 93.72 | 0 | 27.95 | 2223.48 | 0 | 0 | 0
KY | KY - EAST | 2631 | 08737079700 |  | 100242159 |  | 7356252D |  |  |  | 566 | EX | ABANDON / RI 06-12-06 / LCB | 2621P | 10TH | 508 10TH ST | 019 | CAT | 2019-01-22 | BROBERT | SSUTHER | 2008-06-26 | 2049-12-31 |  |  | BROBERT | 2019-01-22 | 2018-12-07 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.33333 | 2 | 785.25 | 18.46 | 43.72 | 1.18 | 721.89 | 0 | 0 | 0
KY | KY - EAST | 2631 | 10823964100 |  | 100242167 |  | 7356252-D |  |  |  | 566 | EX | ABANDON/ IDLE48MO | 2621P | 10TH | 524 10TH ST | 019 | CAT | 2019-01-22 | BROBERT | RPOLLY | 2010-02-08 | 2014-12-23 |  |  | BROBERT | 2019-01-22 | 2018-08-30 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 6.0333 | 2 | 1271.71 | 348.51 | 63.54 | 26.97 | 832.69 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12967998000 |  | 100287012 |  | 00NEW | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | OAKHILL | 812 OAKHILL DR | 067 | LEX | 2019-01-22 | JENSMIN | U124967 | 2012-05-02 | 2014-12-23 |  |  | JENSMIN | 2019-01-22 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.9667 | 1 | 971.3 | 172.65 | 52.36 | 106.39 | 639.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 14257816000 |  | 500440258 |  | 7352260O |  |  |  | 566 | EX | ABANDON W/ 100263998 | 2600B | MAIN | 1902< MAIN ST W | 019 | ASH | 2019-01-22 | U127189 | U125201 | 2014-10-15 | 2049-12-25 |  |  | MATT WILSON | 2019-01-22 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.2 | 1 | 986.5 | 10.98 | 0 | 3.28 | 972.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18636017200 |  | 100293828 |  | 6720212A | 1855043 |  |  | 566 | EX | II - ABANDON ON SOII | 2621P | MCCLAIN | 1002 MCCLAIN DR | 067 | LEX | 2019-01-28 | U131002 | U126129 | 2018-08-17 | 2018-10-30 | 2018-10-30 |  | JENSMIN | 2019-01-22 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.9333 | 1 | 1062.72 | 229.23 | 52.36 | 141.23 | 639.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18639065200 |  | 100251783 |  | 7328284B |  |  |  | 565 | EX | REPLACE S/LN PER FOL M.PIERCE | 2600B | RIDGE | 191 RIDGE ST | 089 | S S | 2019-01-22 | MCOLLET | U131066 | 2018-08-29 | 2019-01-22 |  |  | MCOLLET | 2019-01-22 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 10.15 | 2 | 1102.28 | 636.74 | 156.27 | 309.27 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 07680137400 |  | 100441595 |  | 7352256J |  |  |  | 566 | EX | ABANDON SL - IDLE 24 MONTHS | 2600B | ROBERTS | 4108 ROBERTS DR RR | 019 | ASH | 2019-01-23 | U127189 | SSUTHER | 2007-03-23 | 2020-12-21 |  |  | MATT WILSON | 2019-01-23 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.9833 | 1 | 806.73 | 108.5 | 0 | 32.35 | 665.88 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11900859600 |  | 100264245 |  | 7352256A |  |  |  | 566 | EX | ABANDON / RI 04-27-2010 | 2600B | OLD BUCKLEY | 900 W OLD BUCKLEY RD | 019 | ASH | 2019-01-23 | U127189 | U123853 | 2011-04-12 | 2019-12-31 |  |  | MATT WILSON | 2019-01-23 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.1333 | 1 | 747.68 | 63.01 | 0 | 18.79 | 665.88 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11919589600 |  | 100265401 |  | U-1707-20 |  |  |  | 566 | EX | ABANDON COMPANY SERVICE | 2600B | SHANNON | 4932 SHANNON DR | 019 | ASH | 2019-01-23 | U127189 | U907469 | 2011-08-10 | 2019-01-18 |  |  | MATT WILSON | 2019-01-23 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.3833 | 1 | 1047.94 | 294.32 | 0 | 87.74 | 665.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18026761600 |  |  |  | 6696212J | 1746193 | U128885 |  | 559 | EX | INSTALL 4" PIF | 2600B | CLIFTON | 228 CLIFTON RD | 239 | VER | 2019-02-11 | U131296 | U128885 | 2018-03-14 | 2019-01-28 | 2019-01-31 | 2019-01-14 | LYN STAFFORD | 2019-01-23 | 2019-01-08 | 2019-01-08 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00559 | 3200559 |  |  | WP7616 |  |  | 100 | 055932180267616 | 52.55 | 128 | 30474.32 | 3305.87 | 4298.29 | 906.26 | 18027.27 | 0 | 43.9 | 3892.73 | 16
KY | KY - WEST | 2621 | 18661291000 |  | 100427032 |  | 6720208E |  |  |  | 565 | EX | REROUTE S/L - NOT ACCESSIBLE | 2621P | WOODLAKE | 479 WOODLAKE WY | 067 | LEX | 2019-01-24 | U128293 | U125208 | 2018-12-10 | 2019-01-10 |  |  | LMCDONA | 2019-01-23 | 2019-01-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 76.4167 | 12 | 4189.32 | 3800.52 | 127.52 | 261.28 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19026856500 |  |  |  | 6688228K | 1960710 | U122858 |  | 557 | EX | INSTALL 445'-4" PMLP | 2600E | CRITTENDEN | CRITTENDEN RD | 073 | FRA | 2019-02-06 | U129900 | U122858 | 2019-01-16 | 2019-09-19 | 2019-09-30 | 2019-01-23 | BJACKSON | 2019-01-23 | 2019-01-18 | 2019-01-18 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP8565 | AMRCB |  | 100 | 055732190268565 | 136.0167 | 5811 | 172303.77 | 53710.97 | 2377.08 | 9118.6 | 85224.35 | 0 | 176.29 | 21696.48 | 447
KY | KY - WEST | 2623 | 19026856600 |  |  |  | 6688228K | 1960710 | U122858 |  | 558 | EX | RETIRE 443'-4" BSLP | 2600E | CRITTENDEN | CRITTENDEN | 073 | FRA | 2019-02-05 | U129900 | U122858 | 2019-01-16 | 2019-09-30 | 2019-09-30 | 2019-01-22 | BJACKSON | 2019-01-23 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP8566 | AMRCB |  | 100 | 055832190268566 | 6 | 0 | 785.12 | 337.88 | 0 | 447.24 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671955000 |  | 100357098 |  | 7248280F |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | GERMANTOWN | 3538 GERMANTOWN RD | 161 | MAY | 2019-01-29 | U125208 | U130193 | 2019-01-22 | 2019-01-22 | 2019-01-22 |  | RDENHAM | 2019-01-23 | 2019-01-22 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 | 35.9333 | 5 | 2691.08 | 2156.64 | 105.38 | 429.06 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19672238900 |  | 100279362 |  | 6688228K | 1960710 |  |  | 565 | EX | REPL SVC BRECKENRIDGE OUTAGE | 2621P | CRITTENDEN | 127 CRITTENDEN RD | 073 | FRA | 2019-01-24 | U125208 | U125964 | 2019-01-23 | 2019-01-31 |  |  | CMCHOLA | 2019-01-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.5 | 1 | 388.39 | 292.53 | 76.86 | 19 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19672239900 |  | 100279356 |  | 6688228K | 1960710 |  |  | 565 | EX | REPL SVC BRECKENRIDGE OUTAGE | 2621P | CRITTENDEN | 130 CRITTENDEN RD | 073 | FRA | 2019-01-23 | JENSMIN | U125964 | 2019-01-23 | 2019-01-31 |  |  | JENSMIN | 2019-01-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.5333 | 2 | 3153.95 | 205.89 | 94.38 | 126.86 | 2726.82 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19672242100 |  | 100279361 |  | 6688228K | 1960710 |  |  | 565 | EX | REPL SVC BRECKENRIDGE OUTAGE | 2621P | CRITTENDEN | 131 CRITTENDEN RD | 073 | FRA | 2019-01-23 | DBANKS | U125964 | 2019-01-23 | 2019-01-31 |  |  | DBANKS | 2019-01-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.85 | 1 | 1704.6 | 107.55 | 37.37 | 44.78 | 1514.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19672242400 |  | 100279357 |  | 6688228K | 1960710 |  |  | 565 | EX | REPL SVC BRECKENRIDGE OUTAGE | 2621P | CRITTENDEN | 134 CRITTENDEN RD | 073 | FRA | 2019-01-23 | DBANKS | U125964 | 2019-01-23 | 2019-01-31 |  |  | DBANKS | 2019-01-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.31667 | 1 | 1577.76 | 18 | 37.37 | 7.49 | 1514.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19672242700 |  | 100279358 |  | 6688228K | 1960710 |  |  | 565 | EX | REPL SVC BRECKENRIDGE OUTAGE | 2621P | CRITTENDEN | 136 CRITTENDEN RD | 073 | FRA | 2019-01-24 | U125208 | U125964 | 2019-01-23 | 2019-01-31 |  |  | JENSMIN | 2019-01-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.3333 | 2 | 1919.63 | 135.92 | 185.07 | 83.74 | 1514.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19672243000 |  | 100279360 |  | 6688228K | 1960710 |  |  | 565 | EX | REPL SVC BRECKENRIDGE OUTAGE | 2621P | CRITTENDEN | 137 CRITTENDEN RD | 073 | FRA | 2019-01-24 | U125208 | U125964 | 2019-01-23 | 2019-01-31 |  |  | DBANKS | 2019-01-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.25 | 1 | 3742.38 | 246.43 | 184.66 | 102.61 | 3208.68 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19672243200 |  | 100279359 |  | 6688228K | 1960710 |  |  | 565 | EX | REPL SVC BRECKENRIDGE OUTAGE | 2621P | CRITTENDEN | 142 CRITTENDEN RD | 073 | FRA | 2019-01-24 | U125208 | U125964 | 2019-01-23 | 2019-01-31 |  |  | JENSMIN | 2019-01-23 | 2019-01-22 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.9667 | 1 | 9163.45 | 233.89 | 185.74 | 144.13 | 8599.69 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19672245500 |  | 100279344 |  | 6688228L | 1960710 |  |  | 565 | EX | REPL SVC BRECKENRIDGE OUTAGE | 2621P | BRECKENRIDGE | 541 BRECKENRIDGE BV | 073 | FRA | 2019-01-24 | U125208 | U125964 | 2019-01-23 | 2019-01-31 |  |  | DBANKS | 2019-01-23 | 2019-01-23 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.5 | 1 | 3553.78 | 147.64 | 135.98 | 61.48 | 3208.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 03541200200 |  | 100290364 |  | V-1021-29 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | ROSEMARY | 111 ROSEMARY AV | 067 | LEX | 2019-01-30 | U125208 | DMCCULL | 2003-05-29 | 2014-12-23 |  |  | JENSMIN | 2019-01-24 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.1 | 1 | 739.64 | 64.16 | 8.98 | 26.6 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07688140500 |  | 100286733 |  | 6720212B | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | AVON | 112 AVON AV | 067 | LEX | 2019-01-24 | JENSMIN | SSUTHER | 2007-05-23 | 2014-12-23 |  |  | JENSMIN | 2019-01-24 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.1 | 1 | 700.51 | 5.84 | 52.36 | 2.41 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07689002700 |  | 100290317 |  | 6720212I | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | BERMUDA | 104 BERMUDA AV | 067 | LEX | 2019-01-24 | JENSMIN | U903504 | 2007-05-31 | 2014-12-23 |  |  | JENSMIN | 2019-01-24 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.38333 | 1 | 714.68 | 22.18 | 43.38 | 9.22 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 07689175400 |  | 100466421 |  | V8099 | 1534464 |  |  | 566 | EX | PAPER ABANDON/IDLE > 3-13-2008 | 2600B | MAIN | 610 E MAIN ST B | 073 | FRA | 2019-01-24 | U461383 | U903504 | 2007-06-01 | 2020-12-31 |  |  | STEVE PRICE | 2019-01-24 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - EAST | 2631 | 07696173000 |  | 100256363 | 11 | 7356256-F |  |  |  | 566 | EX | ABANDON COMPANY SERVICE LINE | 2600B | MAY | 612 MAY CT | 019 | ASH | 2019-01-24 | U127189 | BCHATTE | 2007-07-27 | 2020-12-31 |  |  | MATT WILSON | 2019-01-24 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.7 | 1 | 858.69 | 148.53 | 0 | 44.28 | 665.88 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11919866200 |  | 100263931 |  | U-1702-28 |  |  |  | 566 | EX | ABANDON / R 8/18/09 | 2600B | UNRUE | 709< UNRUE ST | 019 | ASH | 2019-01-24 | U127189 | U124449 | 2011-08-11 | 2020-12-31 |  |  | MATT WILSON | 2019-01-24 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.7 | 1 | 928.49 | 202.31 | 0 | 60.3 | 665.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18026761700 |  |  |  | 6696212J | 1746193 | U128885 |  | 560 | EX | RETIRE 5' - 4" CSMP | 2600B | CLIFTON | 228 CLIFTON RD | 239 | VER | 2019-02-08 | U131296 | U128885 | 2018-03-14 | 2019-01-31 | 2019-01-31 | 2019-01-14 | LYN STAFFORD | 2019-01-24 | 2019-01-14 | 2019-01-14 | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00560 | 3200560 |  |  | WP7617 |  |  | 100 | 056032180267617 | 19.0667 | 0 | 1367.16 | 1085.51 | 0 | 281.65 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18651929400 |  | 100303099 |  | 6712208C |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | PINEBLOOM | 1027 PINEBLOOM DR | 067 | LEX | 2019-01-30 | U125208 | U125208 | 2018-10-19 | 2019-04-18 | 2020-10-31 |  | LSTANFI | 2019-01-24 | 2019-01-22 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.6167 | 2 | 3676.31 | 427.91 | 0 | 65.78 | 3182.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19669604300 |  | 100330733 |  | 6720212N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SHERMAN | 316 SHERMAN AV | 067 | LEX | 2019-01-30 | U125208 | U125964 | 2019-01-17 | 2019-01-18 | 2019-02-06 |  | MCRAIG | 2019-01-24 | 2019-01-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.0667 | 7 | 1142.02 | 899.67 | 175.44 | 66.91 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11877000500 |  | 100267890 |  | 1 |  |  |  | 566 | EX | SERVICE LINE ABANDON | 2621P | WILSON | 408 N WILSON ST | 127 | LOU | 2019-01-25 | BROBERT | U906609 | 2011-01-04 | 2020-12-31 |  |  | BROBERT | 2019-01-25 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.6167 | 1 | 2394.54 | 93.19 | 41.54 | 6.07 | 2253.74 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11909241100 |  | 100268288 |  | 7356260M |  |  |  | 566 | EX | ABANDON / RA 06-10-2008 | 2600B | WINCHESTER | 825 WINCHESTER AV | 019 | ASH | 2019-01-25 | U127189 | U907001 | 2011-06-01 | 2019-12-31 |  |  | MATT WILSON | 2019-01-25 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.5 | 1 | 2011.85 | 302.01 | 0 | 20.15 | 1689.69 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19668227300 |  | 500045642 |  | 6724208I | 0779990 |  |  | 566 | EX | ABANDON SL FOR DEMO PS MAILBOX | 2621P | LOCUST HILL | 133 N LOCUST HILL DR | 067 | LEX | 2019-01-31 | U125208 | U130722 | 2019-01-11 | 2019-02-27 | 2019-03-20 |  | LMCDONA | 2019-01-25 | 2019-01-25 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 23.7833 | 4 | 1364.88 | 1273.53 | 8.54 | 82.81 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19668897100 |  | 100326739 |  | 6720208E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | CHINOE | 719 CHINOE RD | 067 | LEX | 2019-01-30 | U125208 | U128293 | 2019-01-15 | 2019-01-22 |  |  | TNEAL | 2019-01-25 | 2019-01-22 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 28.7 | 6 | 2199.62 | 1418.78 | 204.77 | 92.17 | 483.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19673008500 |  | 100245205 |  | 7356256M |  |  |  | 565 | EX | RERUN SERVICE | 2621P | WYNDHAM | 3712 WYNDHAM CT | 019 | ASH | 2019-01-26 | AMCCORM | U130867 | 2019-01-26 | 2019-01-25 |  |  | AMCCORM | 2019-01-26 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 1.15 | 2 | 383.44 | 73.95 | 304.68 | 4.81 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 04568649900 |  | 100294820 |  | X00000000 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | UPPER | 422 N UPPER ST 1F | 067 | LEX | 2019-01-30 | U125208 | SSUTHER | 2004-03-10 | 2014-12-23 |  |  | DBANKS | 2019-01-28 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.45 | 1 | 1260.44 | 83.59 | 41.54 | 45.57 | 1089.74 | 0 | 0 | 0
KY | KY - EAST | 2631 | 07686098700 |  | 100418654 | 53 | 1718/6 |  |  |  | 566 | EX | ABANDON COMPANY SERVICE LINE | 2621P | ADAMS | 917 ADAMS ST 2F | 127 | LOU | 2019-01-28 | BROBERT | LDAVIS | 2007-05-07 | 2014-12-31 |  |  | BROBERT | 2019-01-28 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.1333 | 1 | 913.67 | 169.53 | 11.24 | 11.01 | 721.89 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11920343700 |  | 100261545 |  | 7356256E |  |  |  | 566 | EX | ABANDON / RI 08-19-2009 | 2600B | OAKVIEW | 2134 OAKVIEW RD | 019 | ASH | 2019-01-28 | U127189 | U124449 | 2011-08-16 | 2020-12-31 |  |  | MATT WILSON | 2019-01-28 | 2019-01-22 | 2019-01-22 | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 7.0833 | 2 | 1633.18 | 395.01 | 0 | 113.95 | 1124.22 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11929478600 |  | 100248907 |  | 7356256I |  |  |  | 566 | EX | ABANDON / RI 10-17-2008 | 2600B | HIGH | 2237 HIGH ST | 019 | ASH | 2019-01-28 | U127189 | U125208 | 2011-10-19 | 2020-12-31 |  |  | MATT WILSON | 2019-01-28 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.6167 | 1 | 1408.56 | 260.56 | 0 | 73.64 | 1074.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12967999700 |  | 100294819 |  | 00NEW | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | UPPER | 422 N UPPER ST 2F | 067 | LEX | 2019-01-28 | DBANKS | U124967 | 2012-05-02 | 2014-12-23 |  |  | DBANKS | 2019-01-28 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.05 | 1 | 4.45 | 2.87 | 0 | 1.58 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 13175752100 |  | 100267878 |  | 1 |  |  |  | 566 | EX | ABANDON SL | 2621P | LACKEY | 503 N LACKEY AV | 127 | LOU | 2019-01-28 | BROBERT | U125201 | 2013-11-15 | 2019-01-25 |  |  | BROBERT | 2019-01-28 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.1 | 1 | 901.28 | 168.45 | 0 | 10.94 | 721.89 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18658821000 |  | 100346091 |  | 6700212I |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | WOODFORD | 116 WOODFORD ST | 239 | VER | 2019-01-28 | CDESPAI | U125208 | 2018-11-27 | 2019-05-24 | 2020-11-30 |  | CDESPAI | 2019-01-28 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.1833 | 1 | 2873.48 | 54.09 | 253.29 | 168.87 | 2397.23 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19669442300 |  | 100275808 |  | 6684228C | 1635077 |  |  | 565 | EX | REPLACE SL | 2600B | AUDUBON | 112 AUDUBON DR | 073 | FRA | 2019-01-28 | U126309 | U131066 | 2019-01-16 | 2019-12-31 |  |  | JAMIE LYNN | 2019-01-28 | 2019-01-22 | 2019-01-22 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 18.5 | 2 | 3545.93 | 1038.14 | 220.78 | 317.98 | 1969.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 94192221800 |  | 100294840 | 09 | 6720212E | 1855043 |  |  | 566 | EX | ABANDON / RI 11-08-1990 | 2621P | UPPER | 461 N UPPER ST | 067 | LEX | 2019-01-28 | DBANKS | KAUSTIN | 1994-11-14 | 2049-12-31 |  |  | DBANKS | 2019-01-28 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.93333 | 1 | 750.71 | 53.59 | 27.98 | 29.24 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 96255272500 |  | 100294835 | 10 | X | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | UPPER | 462 N UPPER ST | 067 | LEX | 2019-01-28 | DBANKS | CMELROS | 1996-04-30 | 2014-12-23 |  |  | DBANKS | 2019-01-28 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.9333 | 1 | 853.35 | 111.24 | 41.54 | 60.67 | 639.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 05630621800 |  | 100271149 |  | 6752264T | 1315787 |  |  | 566 | EX | ABANDON GAS SERVICE (TCO TAP) | 2621P | R2 | R2 | 201 | MT | 2019-01-30 | JTOY | U901364 | 2005-12-06 | 2014-12-23 |  |  | DENNING | 2019-01-29 | 2019-01-24 | 2019-01-24 | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 26.4667 | 8 | 1874.83 | 1478.97 | 0 | 395.86 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07671553000 |  | 100291083 |  | 6720212A | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2600B | DAKOTA | 707 DAKOTA ST | 067 | LEX | 2019-01-29 | DBANKS | SSUTHER | 2007-01-08 | 2019-01-29 |  |  | DBANKS | 2019-01-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.2667 | 1 | 845.85 | 129.66 | 5.55 | 70.74 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07675246000 |  | 100294883 |  | 6720212E | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | CAMPBELL | 446 CAMPBELL ST | 067 | LEX | 2019-01-31 | U125208 | SSUTHER | 2007-02-08 | 2019-01-29 |  |  | DBANKS | 2019-01-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.0833 | 1 | 741.64 | 62.25 | 5.55 | 33.94 | 639.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 08743091100 |  | 100249449 |  | 7356216H |  |  |  | 566 | EX | ABANDON SL PER IDLE MEMO | 2621P | KY 2565 | 2212 KY 2565 | 127 | LOU | 2019-01-29 | BROBERT | SSUTHER | 2008-08-04 | 2049-12-31 |  |  | BROBERT | 2019-01-29 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.3 | 1 | 1495.83 | 124.97 | 21.99 | 8.12 | 1340.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12967999900 |  | 100294884 |  | 6720212E | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | CAMPBELL | 448 CAMPBELL ST 1FL | 067 | LEX | 2019-01-31 | U125208 | U124967 | 2012-05-02 | 2014-12-23 | 2018-10-31 |  | DBANKS | 2019-01-29 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - EAST | 2631 | 15343323500 |  | 100460984 |  | 7356216K |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | CARPET MILL | CARPET MILL RD | 127 | LOU | 2019-01-29 | BROBERT | U124444 | 2015-09-14 | 2016-09-09 |  |  | BROBERT | 2019-01-29 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.25 | 1 | 2616.13 | 122.26 | 21.99 | 7.95 | 2463.93 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18594266200 |  | 100291023 |  | 6720212E | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | FLORIDA | 717 FLORIDA ST | 067 | LEX | 2019-02-05 | GHATTON | U125765 | 2018-03-14 | 2019-01-29 |  |  | DBANKS | 2019-01-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.41667 | 1 | 681.94 | 23.61 | 5.55 | 12.88 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18652218000 |  | 100304121 |  | 6712208D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SAGE | 2105 SAGE RD | 067 | LEX | 2019-01-29 | MCRAIG | U125208 | 2018-10-22 | 2019-04-18 | 2020-10-31 |  | MCRAIG | 2019-01-29 | 2019-01-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.4333 | 4 | 1201.28 | 807.03 | 341.81 | 52.44 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18659419800 |  | 100308353 |  | 6716212N |  |  |  | 565 | EX | REPLACE SERVICE | 2621P | DUNCAN | 1083 DUNCAN AV | 067 | LEX | 2019-01-31 | U125208 | U131168 | 2018-11-30 | 2018-12-03 |  |  | KKINDER | 2019-01-29 | 2018-12-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 33.3667 | 7 | 2467.49 | 2007.23 | 196.23 | 264.03 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19669646600 |  | 100302007 |  | 6712212H |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CAMBRIDGE | 2001 CAMBRIDGE DR A | 067 | LEX | 2019-01-31 | U125208 | U125964 | 2019-01-17 | 2019-01-18 | 2019-02-06 |  | DBANKS | 2019-01-29 | 2019-01-28 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.2333 | 3 | 4291.07 | 682 | 192.17 | 226.48 | 3190.42 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19673372200 |  | 500009014 |  | 6704212M |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | GAYBOURNE | 123 GAYBOURNE WY | 239 | VER | 2019-01-31 | U125208 | U130193 | 2019-01-29 | 2019-01-18 | 2019-02-06 |  | RVANDER | 2019-01-29 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.1167 | 2 | 304.49 | 228.58 | 4.61 | 71.3 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19673372500 |  | 100345851 |  | 6704212M |  |  |  | 566 | EX | RETIRE SERVICE LINE - LEAKAGE | 2621P | GAYBOURNE | 128 GAYBOURNE WY | 239 | VER | 2019-02-05 | U125208 | U130193 | 2019-01-29 | 2019-07-19 | 2021-01-31 |  | RVANDER | 2019-01-29 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26230043 | 13.05 | 3 | 805.8 | 712.23 | 0 | 93.57 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11889237900 |  | 100287078 |  | V-1021-45 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | CHURCHILL | 1018 CHURCHILL DR | 067 | LEX | 2019-02-05 | U125208 | U906631 | 2011-02-16 | 2019-01-30 |  |  | DBANKS | 2019-01-30 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.9 | 1 | 724.77 | 51.33 | 5.55 | 27.99 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12975834200 |  | 100287077 |  | 16720212F | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | CHURCHILL | 1016 CHURCHILL DR | 067 | LEX | 2019-01-30 | DBANKS | U123854 | 2012-06-11 | 2019-01-30 |  |  | DBANKS | 2019-01-30 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.98333 | 1 | 731.88 | 55.93 | 5.55 | 30.5 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18636017500 |  | 100290316 |  | 6720212B | 1855043 |  |  | 566 | EX | II - ABANDON ON SOII | 2621P | BERMUDA | 102 BERMUDA AV | 067 | LEX | 2019-01-30 | DBANKS | U126129 | 2018-08-17 | 2019-01-30 |  |  | DBANKS | 2019-01-30 | 2019-01-24 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.0167 | 2 | 1142.51 | 289.55 | 63.54 | 149.52 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19676251700 |  | 100315048 |  | 6716212O |  |  |  | 565 | VO | REPLACE SVC LINE | 2621P | LEADER | 156 LEADER AV 1 | 067 | LEX | 2019-02-12 |  | U130193 | 2019-01-31 | 2019-01-31 |  |  | S. BARKER | 2019-01-31 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1
KY | KY - WEST | 2621 | 19678727200 |  | 500700186 |  | 6720208H |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | WOODHILL | 2350 WOODHILL DR 4 UPSTA | 067 | LEX | 2019-02-04 | U126332 | U131168 | 2019-01-31 | 2019-01-31 | 2019-01-31 |  | TNEAL | 2019-01-31 | 2019-01-31 | 2019-01-31 | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 43.9667 | 7 | 3059.28 | 2634.16 | 211.58 | 213.54 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 04573191300 |  | 100312770 |  | 6716208E | 1855043 |  |  | 566 | EX | ABANDON / CV-FILLED IN..VACANT | 2621P | STRATFORD | 475 STRATFORD DR | 067 | LEX | 2019-02-01 | DBANKS | SSUTHER | 2004-04-27 | 2019-02-01 |  |  | DBANKS | 2019-02-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.55 | 1 | 1211.99 | 31.69 | 63.54 | 17.1 | 1099.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 05597373500 |  | 100312133 |  | 16716208I | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | CLAYMONT | 513 CLAYMONT DR | 067 | LEX | 2019-02-01 | DBANKS | SSUTHER | 2005-01-05 | 2019-02-01 |  |  | DBANKS | 2019-02-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.8167 | 1 | 828.49 | 104.28 | 27.98 | 56.33 | 639.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 06646229500 |  | 100285351 |  | 6764176P |  |  |  | 566 | EX | ABANOND/ IDLE | 2621P | EVERGREEN | 217 EVERGREEN DR | 065 | IRV | 2019-02-01 | DENNING | SKSMITH | 2006-04-28 | 2049-12-31 |  |  | DENNING | 2019-02-01 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.2333 | 5 | 267.94 | 212 | 0 | 55.94 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 08727659400 |  | 100312538 |  | 16716208E | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | SHERIDAN | 399 SHERIDAN DR | 067 | LEX | 2019-02-01 | DBANKS | RPOLLY | 2008-04-16 | 2019-02-01 | 2019-02-01 |  | DBANKS | 2019-02-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.45 | 1 | 685.38 | 25.94 | 5.55 | 13.99 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 10870587400 |  | 100312377 | 15 | 600000000 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | EASTWAY | 2436 EASTWAY DR | 067 | LEX | 2019-02-01 | DBANKS | ESEMONE | 2010-12-02 | 2019-02-01 | 2019-02-01 |  | DBANKS | 2019-02-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.66667 | 1 | 767.97 | 38.03 | 69.52 | 20.52 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11891844000 |  | 100312963 |  | 00NEW | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | ROSEMILL | 598 ROSEMILL DR | 067 | LEX | 2019-02-01 | DBANKS | U906307 | 2011-02-24 | 2019-02-01 | 2019-02-01 |  | DBANKS | 2019-02-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.45 | 1 | 3173.19 | 25.94 | 69.52 | 13.99 | 3063.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19667717600 |  | 100314210 | 14 | 6716212O |  |  |  | 566 | EX | ABANDON SERVICE | 2621P | BROADWAY | 365 BROADWAY PR SO | 067 | LEX | 2019-02-01 | MCRAIG | AJPARKS | 2019-01-10 | 2019-03-14 | 2019-03-14 |  | MCRAIG | 2019-02-01 | 2019-01-16 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 36.4333 | 9 | 2097.23 | 1974.6 | 0 | 122.63 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19676173400 |  | 100352173 |  | 6744208K |  |  |  | 566 | EX | DEMO / ABANDON / RI 02/01/19 | 2621P | MARYLAND | 24 MARYLAND AV | 049 | WIN | 2019-02-06 | U930915 | U125208 | 2019-01-31 | 2019-02-01 |  |  | RJJOHNS | 2019-02-01 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 14.1167 | 2 | 1009.69 | 842.35 | 117.37 | 49.97 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 03545419800 |  | 100310175 | 28 | 6716208E | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | SPRINGRIDGE | 628 SPRINGRIDGE DR | 067 | LEX | 2019-02-04 | LMCDONA | LABRAMS | 2003-07-15 | 2014-12-23 |  |  | LMCDONA | 2019-02-04 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.1 | 1 | 769.13 | 56.36 | 69.52 | 3.35 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 04577820300 |  | 100337207 |  | 6720212E |  |  |  | 566 | EX | ABANDON SERVICE | 2600B | RAND | 124 RAND AV | 067 | LEX | 2019-02-04 | DBANKS | SSUTHER | 2004-06-14 | 2019-02-04 |  |  | DBANKS | 2019-02-04 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.3833 | 1 | 892.59 | 137.11 | 41.54 | 74.04 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07703775000 |  | 100337193 |  | 16720212E |  |  |  | 566 | EX | ABN SERV LINE PER 24 MO MEMO | 2600B | RAND | 129 RAND AV | 067 | LEX | 2019-02-04 | DBANKS | DMCCULL | 2007-09-25 | 2019-02-04 |  |  | DBANKS | 2019-02-04 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.21667 | 1 | 700.08 | 12.1 | 41.54 | 6.54 | 639.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 09807806400 |  | 100265579 |  | . |  |  |  | 566 | EX | ABD S/L-IDLE 36MO 091909 | 2621P | STATE RT 5 | 7121 STATE RT 5 | 019 | ASH | 2019-02-04 | BROBERT | RPOLLY | 2009-10-14 | 2019-02-04 |  |  | BROBERT | 2019-02-04 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.51667 | 1 | 1828.67 | 28.25 | 11.24 | 1.66 | 1787.52 | 0 | 0 | 0
KY | KY - EAST | 2631 | 09809410800 |  | 500094857 |  | U-1706-27 |  |  |  | 566 | EX | ABD S/L-IDLE 36MO MEMO 101909 | 2600B | STATE RT 5 | 7220 STATE RT 5 | 019 | ASH | 2019-02-04 | BROBERT | RPOLLY | 2009-10-27 | 2019-02-04 |  |  | BROBERT | 2019-02-04 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.5333 | 1 | 887.65 | 83.11 | 11.24 | 4.93 | 788.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 10872025800 |  | 100315425 |  | V-930-22 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | WALLER | 210 WALLER AV | 067 | LEX | 2019-02-06 | U125208 | U906609 | 2010-12-13 | 2019-02-04 |  |  | LMCDONA | 2019-02-04 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.2167 | 1 | 717.85 | 64.04 | 10.11 | 3.8 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11903615800 |  | 100315282 |  | 16716208C | 1855043 |  |  | 566 | EX | SOII - ABANDON RI 07-15-2008 | 2621P | STATE | 211 STATE ST | 067 | LEX | 2019-02-04 | LMCDONA | U124961 | 2011-04-28 | 2014-12-23 |  |  | LMCDONA | 2019-02-04 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.73333 | 1 | 679.52 | 37.41 | 0 | 2.21 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18634190600 |  | 100345257 |  | 6696212H |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BOSTON | 228 BOSTON DR | 239 | VER | 2019-02-04 | CDESPAI | U125208 | 2018-08-10 | 2019-02-08 | 2020-08-31 |  | CDESPAI | 2019-02-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.15 | 1 | 3032.21 | 236.86 | 197.69 | 400.39 | 2197.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18636007700 |  | 100315404 |  | 6716208C | 1855043 |  |  | 566 | EX | II - ABANDON ON SOII | 2621P | WALLER | 209 WALLER AV | 067 | LEX | 2019-02-06 | U125208 | U126129 | 2018-08-17 | 2019-02-04 |  |  | LMCDONA | 2019-02-04 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.85 | 1 | 696.14 | 43.55 | 10.11 | 2.58 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18636012900 |  | 100304844 |  | 6712212L | 1855043 |  |  | 566 | EX | II - ABANDON ON SOII | 2621P | CELIA | 969 CELIA LN | 067 | LEX | 2019-02-11 | U125208 | U126129 | 2018-08-17 | 2018-10-30 | 2018-10-30 |  | LMCDONA | 2019-02-04 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.61667 | 1 | 701.01 | 31.28 | 27.98 | 1.85 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18636037200 |  | 100315303 |  | 6716208C | 1855043 |  |  | 566 | EX | II - ABANDON ON SOII | 2621P | STATE | 214 STATE ST | 067 | LEX | 2019-02-06 | U125208 | U126129 | 2018-08-17 | 2018-10-30 | 2018-10-30 |  | LMCDONA | 2019-02-04 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.2167 | 1 | 3301.83 | 215.19 | 10.11 | 12.79 | 3063.74 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18644560300 |  | 100346059 |  | 6700212J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | ROAN | 120 ROAN RD | 239 | VER | 2019-02-04 | CDESPAI | U125208 | 2018-09-20 | 2019-03-19 | 2020-09-30 |  | CDESPAI | 2019-02-04 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.9 | 2 | 2224.69 | 178.66 | 189.95 | 264.77 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18651931700 |  | 100303676 |  | 6712208D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | DOGWOOD | 2021 DOGWOOD DR | 067 | LEX | 2019-02-06 | U125208 | U125208 | 2018-10-19 | 2019-02-04 | 2020-10-31 |  | DBANKS | 2019-02-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.76667 | 1 | 1656.11 | 43.78 | 257.18 | 23.65 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18663595600 |  | 100337209 |  | 6720212E |  |  |  | 565 | EX | SERVICE LINE/METER RELOCATION | 2621P | RAND | 130 RAND AV | 067 | LEX | 2019-02-06 | U125208 | U128293 | 2018-12-21 | 2019-01-22 | 2019-01-22 |  | DBANKS | 2019-02-04 | 2019-01-16 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.3333 | 3 | 5274.51 | 306.4 | 236.82 | 149.09 | 4582.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19666914800 |  | 100338842 | 36 | 6720212F |  |  |  | 566 | EX | ABANDON / RI 01-07-19 / CONVRT | 2621P | MARCELLUS | 810 MARCELLUS DR | 067 | LEX | 2019-02-04 | MCRAIG | JFAWNS | 2019-01-07 | 2019-02-08 |  |  | MCRAIG | 2019-02-04 | 2019-02-04 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.3667 | 3 | 474.8 | 438.64 | 10.11 | 26.05 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19672815900 |  | 100290175 |  | 6720212B |  |  |  | 566 | EX | DEMO / WORK 1-29 / RA 1-29 | 2621P | BLUE GRASS | 318 BLUE GRASS AV | 067 | LEX | 2019-02-04 | MCRAIG | U125208 | 2019-01-25 | 2019-01-29 |  |  | MCRAIG | 2019-02-04 | 2019-01-28 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.65 | 6 | 696.14 | 637.98 | 19.14 | 39.02 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19673365000 |  | 100275551 |  | 6684228F |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2600B | LILY | 105 LILY ST | 073 | FRA | 2019-02-04 | U126309 | U125768 | 2019-01-29 | 2049-12-31 |  |  | JAMIE LYNN | 2019-02-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 8.5 | 1 | 1900.29 | 473.23 | 41.53 | 157.8 | 1227.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19679112500 |  | 100417482 |  | 6716204F |  |  |  | 565 | EX | GRADE 1 REPLACE SERV LINE | 2621P | TIVERTON | 212 E TIVERTON WY | 067 | LEX | 2019-02-11 | U125208 | U129939 | 2019-02-03 | 2019-02-03 | 2019-02-03 |  | LSTANFI | 2019-02-04 | 2019-02-04 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.4333 | 3 | 948.87 | 764.48 | 139.04 | 45.35 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 09768724700 |  | 500357541 | 22 | 7348256-N |  |  |  | 566 | EX | ABN/ IDLE 36MO 12/2011 RA 2009 | 2600B | STATE RT 5 | 6304 STATE RT 5 | 019 | ASH | 2019-02-05 | BROBERT | JWHEATL | 2009-01-21 | 2019-02-05 |  |  | BROBERT | 2019-02-05 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.8167 | 1 | 1847.7 | 98.25 | 1.38 | 5.84 | 1742.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 10872024700 |  | 100315149 |  | 6716212O | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | JOURNAL | 903 JOURNAL AV | 067 | LEX | 2019-02-06 | U125208 | U906609 | 2010-12-13 | 2019-02-05 |  |  | LMCDONA | 2019-02-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.7833 | 1 | 801.86 | 91.23 | 65.32 | 5.41 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11882415100 |  | 100287472 |  | 6720212G | 1855043 |  |  | 566 | EX | SOII -ABN/DC 3-29-07 RI 2-2010 | 2621P | DARLEY | 906 DARLEY DR | 067 | LEX | 2019-02-06 | U125208 | U906307 | 2011-01-31 | 2019-02-05 |  |  | LMCDONA | 2019-02-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.46667 | 1 | 1175.15 | 23.57 | 50.52 | 1.4 | 1099.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11906853900 |  | 100311746 |  | 00NEW | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | LAMONT | 584 LAMONT DR | 067 | LEX | 2019-02-06 | U125208 | U124017 | 2011-05-16 | 2019-02-05 |  |  | LMCDONA | 2019-02-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.61667 | 1 | 738.35 | 31.28 | 65.32 | 1.85 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12975834600 |  | 100287473 |  | V-1021-54 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | DARLEY | 908 DARLEY DR | 067 | LEX | 2019-02-06 | U125208 | U123854 | 2012-06-11 | 2019-02-05 |  |  | LMCDONA | 2019-02-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.38333 | 1 | 711.05 | 19.49 | 50.52 | 1.14 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12999080300 |  | 100313359 | 18 | ? | 1855043 |  |  | 566 | EX | ABANDON/ RA 11-16-2012 TOFF CV | 2621P | BOB O LINK | 584 BOB O LINK DR | 067 | LEX | 2019-02-06 | U125208 | U807359 | 2012-11-19 | 2020-12-31 |  |  | LMCDONA | 2019-02-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.28333 | 1 | 108.48 | 14.33 | 93.3 | 0.85 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 17026725301 |  | 501090751 |  | 6732216L | 1747692 | U461383 |  | 555 | EX | INSTALL 3300' OF 4"PMMP MAIN | 2600B | BRIAR HILL | 5751 BRIAR HILL RD LT112 | 067 | LEX | 2019-02-13 | U129900 | U461383 | 2019-01-21 | 2018-11-19 | 2019-02-15 | 2019-02-04 | JPASLEY | 2019-02-05 | 2019-01-22 | 2019-01-22 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP7253 |  |  | 100 | 055532170267253 | 286.65 | 132571 | 213118.5 | 16865.35 | 14341.26 | 5098.14 | 147467.16 | 0 | 1457.38 | 27889.21 | 3583
KY | KY - WEST | 2621 | 18594264700 |  | 100313360 |  | ? | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | BOB O LINK | 582 BOB O LINK DR | 067 | LEX | 2019-02-06 | U125208 | U125765 | 2018-03-14 | 2019-02-05 |  |  | LMCDONA | 2019-02-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.95 | 1 | 899.19 | 48.18 | 93.3 | 2.87 | 754.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18636014200 |  | 100308590 |  | 6716212N | 1855043 |  |  | 566 | EX | II - ABANDON ON SOII | 2621P | GIBSON | 416 GIBSON AV | 067 | LEX | 2019-02-12 | U125208 | U126129 | 2018-08-17 | 2019-02-05 |  |  | LMCDONA | 2019-02-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.4333 | 1 | 969.2 | 75.82 | 19.1 | 4.5 | 869.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18650412400 |  | 100455137 |  | 6720216M | 1425507 |  |  | 565 | EX | REPLACE SL W/18026746600 | 2600B | BOARDWALK | 1498 BOARDWALK ST | 067 | LEX | 2019-02-05 | U461467 | U131066 | 2018-10-12 | 2019-12-31 |  |  | D REFFETT | 2019-02-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0 | 1 | 2408.21 | 0 | 0 | 0 | 2408.21 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18656364500 |  | 100338241 |  | 6720212J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BRECKENRIDGE | 558 BRECKENRIDGE ST | 067 | LEX | 2019-02-06 | U125208 | U125208 | 2018-11-08 | 2019-05-07 | 2020-11-30 |  | DBANKS | 2019-02-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.05 | 1 | 2340.64 | 290.91 | 143.99 | 157.12 | 1748.62 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19673364700 |  | 100280036 |  | 6688228N |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2600B | LYONS | 309 LYONS DR | 073 | FRA | 2019-02-06 | U126309 | U125768 | 2019-01-29 | 2049-12-31 |  |  | JAMIE LYNN | 2019-02-05 | 2019-02-05 | 2019-02-05 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 11.6 | 2 | 2714.94 | 645.79 | 41.53 | 215.36 | 1812.26 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673424100 |  | 100331109 |  | 6720212N |  |  |  | 565 | EX | REPLACE/UNMTRD GAS - 60 DC | 2621P | PRESTON | 211 PRESTON AV | 067 | LEX | 2019-02-05 | LSTANFI | U125208 | 2019-01-29 | 2019-02-28 | 2019-03-29 |  | LSTANFI | 2019-02-05 | 2019-02-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 44.7 | 8 | 4862.79 | 2641 | 142.24 | 156.67 | 1922.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19679241200 |  | 100316684 |  | 6716208G |  |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | LACKAWANNA | 103 LACKAWANNA RD | 067 | LEX | 2019-02-06 | U125208 | U125208 | 2019-02-04 | 2019-02-05 |  |  | LMCDONA | 2019-02-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.2 | 1 | 732.47 | 60.97 | 27.98 | 3.62 | 639.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19679242800 |  | 100268910 |  | 6736252M |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MARSHALL | 116 MARSHALL AV | 097 | CYN | 2019-02-05 | LSHARON | U125208 | 2019-02-04 | 2019-02-04 | 2019-02-04 |  | LSHARON | 2019-02-05 | 2019-02-05 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 28.2167 | 3 | 2529.52 | 1696.3 | 181.26 | 651.96 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18026800500 |  | 501077374 |  | 7356256G | 1319400 | U122858 |  | 555 | EX | INSTALL 150'-2" PMLP | 2600B | DEAL | 702 DEAL ST | 019 | ASH | 2019-02-20 | U129900 | U122858 | 2018-10-16 | 2019-01-16 | 2019-01-20 | 2019-02-06 | BCOFER | 2019-02-06 | 2018-11-26 | 2018-11-26 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP8005 |  |  | 100 | 055532180268005 | 191.4333 | 3519 | 64011.45 | 11550.11 | 1024.42 | 3361.49 | 39075.12 | 0 | 456.86 | 8543.45 | 153
KY | KY - WEST | 2621 | 19679109500 |  | 100465958 |  | 6720204O |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | WOODFIELD | 2472 WOODFIELD CR | 067 | LEX | 2019-02-11 | U125208 | U129939 | 2019-02-03 | 2019-02-22 | 2019-02-23 |  | MCRAIG | 2019-02-06 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.9167 | 3 | 1112.43 | 774.54 | 291.94 | 45.95 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19679777100 |  | 100413628 |  | 6720212H |  |  |  | 566 | EX | ABD SVC LINE | 2621P | ARUNDEL | 1844 ARUNDEL DR 1FR | 067 | LEX | 2019-02-06 | LSTANFI | U130193 | 2019-02-06 | 2019-02-06 |  |  | LSTANFI | 2019-02-06 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.9 | 2 | 49.64 | 46.6 | 0 | 3.04 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19679780400 |  | 100413627 |  | 6720212H |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | ARUNDEL | 1844 ARUNDEL DR 1FL | 067 | LEX | 2019-02-11 | U125208 | U130193 | 2019-02-06 | 2019-02-05 | 2019-02-05 |  | LSTANFI | 2019-02-06 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.4 | 4 | 2282.56 | 1109.94 | 174.18 | 65.89 | 932.55 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12950633200 |  | 100285277 |  | 6764176O |  |  |  | 566 | EX | DEMO / ABANDON / RI 2009 MNFLD | 2600B | WILDWOOD | 95 WILDWOOD PL | 065 | IRV | 2019-02-08 | U125208 | U125208 | 2012-01-20 | 2019-03-06 |  |  | DENNING | 2019-02-07 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10.1 | 3 | 646.33 | 513.32 | 0 | 133.01 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19669428900 |  | 100281965 |  | 6712232O |  |  |  | 566 | EX | ABANDON SL FOR DEMO PS MAILBOX | 2621P | MAIN | 502 MAIN AV | 209 | GEO | 2019-02-21 | U125208 | U130722 | 2019-01-16 | 2019-03-04 | 2019-03-25 |  | RVANDER | 2019-02-07 | 2019-01-31 | 2019-01-31 | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 14.8333 | 5 | 974.24 | 826.82 | 98.33 | 49.09 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19669996200 |  | 100333130 |  | 6720212I |  |  |  | 566 | EX | DEMO / ABANDON / RI 01-22-19 | 2621P | CORRAL | 364 CORRAL ST | 067 | LEX | 2019-02-11 | U125208 | U130722 | 2019-01-18 | 2019-03-06 | 2019-03-27 |  | LMCDONA | 2019-02-07 | 2019-02-07 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 19.5833 | 5 | 1341.22 | 1100.24 | 74.31 | 166.67 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19672822800 |  | 100328224 |  | 6720208F |  |  |  | 565 | EX | REPLACE S/L | 2621P | CULPEPPER | 321 CULPEPPER RD | 067 | LEX | 2019-02-11 | U125208 | U131171 | 2019-01-25 | 2019-01-25 |  |  | MCRAIG | 2019-02-07 | 2019-01-25 | 2019-01-25 | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.15 | 7 | 1153.77 | 975.16 | 115.71 | 62.9 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19679187700 |  | 100461196 |  | 6716204C |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LAREDO | 3441 LAREDO DR 10 | 067 | LEX | 2019-02-11 | U125208 | U125208 | 2019-02-04 |  |  |  | MCRAIG | 2019-02-07 | 2019-02-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.7667 | 4 | 1366.42 | 1188.87 | 107.05 | 70.5 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 06668177100 |  | 100346819 |  | 6696212O | 1855043 |  |  | 565 | EX | UPGRADE SERVICE LINE | 2621P | HILLCREST | 362 HILLCREST DR | 239 | VER | 2019-02-08 | CDESPAI | RPOLLY | 2006-12-11 | 2014-12-23 | 2019-02-06 |  | CDESPAI | 2019-02-08 | 2019-02-06 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.3 | 2 | 2131.77 | 104.51 | 303.52 | 132.43 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 08763242100 |  | 100287545 | 14 | 16720212G | 1855043 |  |  | 566 | EX | SOII - ABANDON / RA 12-11-2008 | 2621P | DARLEY | 919 DARLEY DR | 067 | LEX | 2019-02-12 | U125208 | U462080 | 2008-12-15 | 2019-02-08 |  |  | LMCDONA | 2019-02-08 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.8167 | 1 | 1655.62 | 298.7 | 93.3 | 17.76 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572198200 |  | 100276750 |  | 6684228D | 1747736 |  |  | 565 | EX | RPLC SL/17026730000/ | 2600B | 5TH | 816 5TH AV | 073 | FRA | 2019-02-08 | U126309 | U131066 | 2018-01-04 | 2019-12-31 |  |  | JAMIE LYNN | 2019-02-08 | 2019-02-06 | 2019-02-06 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 17.0167 | 3 | 4052.35 | 946.99 | 388.12 | 315.84 | 2401.4 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18613648900 |  | 100260787 |  | 7352256K | 1747947 |  |  | 565 | EX | RPLC SL/17026728400/ | 2600B | NORWOOD | 1124 NORWOOD AV | 019 | ASH | 2019-02-08 | MBLANKE | U131066 | 2018-05-22 | 2019-12-31 |  |  | MBLANKE | 2019-02-08 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.5 | 1 | 1691.53 | 28.81 | 0 | 9.33 | 1653.39 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18639064000 |  | 100243443 |  | 7348268M | 1749172 |  |  | 565 | EX | RPLC SL/17026740200/ | 2600B | 2ND | 60 E 2ND AV | 089 | S S | 2019-02-08 | U127189 | U131066 | 2018-08-29 | 2019-12-31 |  |  | MATT WILSON | 2019-02-08 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.18333 | 1 | 1762.4 | 10.93 | 0 | 0.62 | 1750.85 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18664277100 |  | 100281750 |  | 6712232O |  |  |  | 566 | EX | DEMO / ABANDON / RI 01-04-19 | 2621P | HAMILTON | 626 N HAMILTON ST | 209 | GEO | 2019-02-12 | U125208 | U124962 | 2018-12-28 | 2019-02-13 | 2019-03-06 |  | RVANDER | 2019-02-08 | 2019-01-31 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 7.7333 | 5 | 484.26 | 430.71 | 27.98 | 25.57 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19679759000 |  | 100409727 |  | 6720204B |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | GREENTREE | 3388 GREENTREE PL | 067 | LEX | 2019-02-08 | MCRAIG | U125208 | 2019-02-06 | 2019-02-08 | 2019-02-26 |  | MCRAIG | 2019-02-08 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.85 | 2 | 1195.69 | 953.43 | 185.68 | 56.58 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19680341100 |  | 100463377 |  | 6680224G |  |  |  | 565 | EX | REPLACE SERV LINE | 2621P | HIGHVIEW | 1607 HIGHVIEW CR | 073 | FRA | 2019-02-12 | U125208 | U129939 | 2019-02-08 | 2019-02-08 |  |  | CDESPAI | 2019-02-08 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.95 | 1 | 2646.48 | 43.09 | 124.94 | 54.61 | 2423.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680480500 |  | 100298404 |  | 6716212H |  |  |  | 565 | EX | GRADE 1 REPLACE SERV | 2621P | SHORT | 522 W SHORT ST | 067 | LEX | 2019-02-12 | U125208 | U129939 | 2019-02-08 | 2019-02-08 | 2019-02-08 |  | KKINDER | 2019-02-08 | 2019-02-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 27.1833 | 5 | 2454.99 | 1599.35 | 129.97 | 169.19 | 556.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19679188300 |  | 100460691 |  | 6716204C |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LAREDO | 3441 LAREDO DR 12 | 067 | LEX | 2019-02-11 | MCRAIG | U125208 | 2019-02-04 |  |  |  | MCRAIG | 2019-02-11 | 2019-02-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24 | 3 | 1194.68 | 1040.06 | 92.94 | 61.68 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 07689052300 |  | 100460493 |  | X1103-20 |  |  |  | 566 | EX | ABANDON SERV LINE/IDLE 48 MOS | 2621P | WACO LOOP | 564 WACO LOOP TLR | 151 | WAC | 2019-02-13 | U125208 | U903504 | 2007-05-31 | 2014-12-23 |  |  | DENNING | 2019-02-12 | 2019-02-01 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 20.95 | 7 | 1338.86 | 1063.29 | 0 | 275.57 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 11878837200 |  | 100353421 |  | 7256280G |  |  |  | 566 | EX | ABANDON / RI 01-26-2009 | 2621P | 2ND | 701 W 2ND ST | 161 | MAY | 2019-02-13 | U125208 | U906609 | 2011-01-13 | 2019-02-13 | 2019-03-03 |  | SDADAMS | 2019-02-12 | 2019-02-11 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 25.8 | 5 | 2046.94 | 1460.31 | 23.78 | 562.85 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11928063600 |  | 100421197 |  | X-1103-29 |  |  |  | 566 | EX | ABANDON/ RA 09-08-2006 - FIRE | 2621P | WACO LOOP | 580 WACO LOOP | 151 | WAC | 2019-02-12 | DENNING | DMCCULL | 2011-10-06 | 2014-12-23 |  |  | DENNING | 2019-02-12 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.4 | 4 | 348.18 | 276.54 | 0 | 71.64 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 17026716200 |  |  |  | 6720212P | 1744729 | PTRUE |  | 910 | EX | RETIRE CONTROLLERS | 2600E | FORTUNE | 2350 FORTUNE DR | 067 | LEX | 2019-03-13 | U462463 | U122858 | 2017-07-03 | 2018-12-31 | 2018-12-31 | 2018-10-16 | CYNTHIA FARIS | 2019-02-12 |  |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00910 | 3200910 |  |  | WP7162 |  |  | 100 | 091032170267162 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19680891800 |  | 501092445 |  | 6760172C |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | PEA RIDGE | 895 PEA RIDGE RD | 065 | IRV | 2019-02-13 | U125208 | U130867 | 2019-02-12 | 2019-02-11 | 2019-02-11 |  | RJJOHNS | 2019-02-12 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26290021 | 20.9833 | 5 | 2456.09 | 1945.24 | 211.8 | 299.05 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11916457200 |  | 500438324 |  | X-1207/33 |  |  |  | 566 | EX | ABDN SERV LINE/48 MONTHS | 2621P | DANIELS AD | 413 DANIELS AD | 065 | RAV | 2019-02-13 | DENNING | U124964 | 2011-07-19 | 2014-12-23 |  |  | DENNING | 2019-02-13 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 13.3 | 3 | 856.09 | 679.87 | 0 | 176.22 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 14247971400 |  | 100417300 |  | 6736180D |  |  |  | 565 | EX | REPLACE SERVICE | 2621P | GILBERT | 556 GILBERT DR | 151 | RIC | 2019-02-13 | DENNING | JTOY | 2014-09-04 | 2014-09-02 |  |  | DENNING | 2019-02-13 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26290031 | 32.5667 | 7 | 2373.46 | 1596.21 | 209.01 | 568.24 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18613647900 |  | 100260933 |  | 7352256G | 1747947 |  |  | 565 | EX | RPLC SL/17026728400/ | 2600B | EDGEWOOD | 905 EDGEWOOD AV | 019 | ASH | 2019-02-13 | U461496 | U131066 | 2018-05-22 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-02-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 4.2333 | 1 | 2283.91 | 235.42 | 0 | 78.69 | 1969.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18615601400 |  | 100345767 |  | 6696212D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MARCELLA | 778 MARCELLA ST | 239 | VER | 2019-02-13 | CDESPAI | U125208 | 2018-05-30 | 2018-11-29 | 2020-05-31 |  | CDESPAI | 2019-02-13 | 2019-01-02 | 2019-01-02 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8.0167 | 2 | 2774.25 | 380.04 | 242.32 | 560.58 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18628358200 |  | 500331415 |  | 6720216M | 1425507 | U131066 |  | 565 | EX | REPLACE SL W/18-0267464-00 | 2600B | NEW CIRCLE | 763 W NEW CIRCLE RD | 067 | LEX | 2019-02-13 | U123110 | U131066 | 2018-07-18 | 2019-12-31 |  |  | D REFFETT | 2019-02-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.016667 | 1 | 5219.95 | 1.73 | 1091.38 | 0.57 | 4126.27 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18639063800 |  | 100243464 |  | 7328284A | 1749172 |  |  | 565 | EX | RPLC SL/17026740200/ | 2600B | 1ST | 589 E 1ST AV | 089 | S S | 2019-02-13 | MBLANKE | U131066 | 2018-08-29 | 2019-12-31 |  |  | MBLANKE | 2019-02-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.16667 | 1 | 961.43 | 9.21 | 0 | 3 | 949.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026860100 |  |  |  | 6716212H | 1853770 | U122858 |  | 587 | EX | INSTALL EFC | 2600M | HIGH | 435 W HIGH ST RUPP AR | 067 | LEX | 2019-02-26 | U462463 | U122858 | 2019-02-07 | 2018-12-31 | 2018-12-31 | 2019-02-12 | RYAN WILLIAMS | 2019-02-13 |  |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00587 | 3200587 |  |  | WP8601 |  |  | 100 | 058732190268601 | 2.65 | 0 | 5560.7 | 169 | 4636.59 | 50.49 | 0 | 0 | 0.48 | 704.14
KY | KY - WEST | 2621 | 19026860300 |  |  |  | 6716212H | 1853770 | U122858 |  | 588 | EX | RETIRE EFC | 2600M | HIGH | 435 W HIGH ST RUPP AR | 067 | LEX | 2019-02-26 | U462463 | U122858 | 2019-02-07 | 2019-12-31 | 2019-12-31 | 2019-02-12 | RYAN WILLIAMS | 2019-02-13 |  |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00588 | 3200588 |  |  | WP8603 |  |  | 100 | 058832190268603 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673013300 |  | 100414570 |  | 6712204C |  |  |  | 565 | EX | GRADE 2*/ REPLACE SERV LINE | 2621P | CORNWALL | 3513 CORNWALL DR | 067 | LEX | 2019-02-15 | U128381 | U129939 | 2019-01-27 | 2019-01-30 | 2019-02-17 |  | TGNELSO | 2019-02-13 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 30.1667 | 3 | 1441.26 | 1360.53 | 0 | 80.73 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19679231300 |  | 500959506 |  | 6716204B | 0570223 |  |  | 566 | EX | DEMO / ABANDON / RI 02-07-19 | 2621P | NICHOLASVILLE | 3401 NICHOLASVILLE RD FRONT | 067 | LEX | 2019-02-18 | U125208 | U125208 | 2019-02-04 | 2019-02-28 |  |  | MCRAIG | 2019-02-13 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.9 | 2 | 911.41 | 850.8 | 10.15 | 50.46 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680428500 |  | 100298091 |  | 6716212L |  |  |  | 565 | EX | GRADE 1 REPLACE | 2621P | SHORT | 107 W SHORT ST | 067 | LEX | 2019-02-18 | U125208 | U129939 | 2019-02-08 | 2019-02-08 | 2019-02-08 |  | DBANKS | 2019-02-13 | 2019-02-08 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.1 | 3 | 12009.15 | 755.28 | 105.92 | 341.43 | 10806.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19681100900 |  | 100457547 |  | 6712208F |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | ROLLINGDALE | 2101 ROLLINGDALE RD | 067 | LEX | 2019-02-18 | U125208 | U129939 | 2019-02-13 | 2019-02-22 | 2019-02-23 |  | DBANKS | 2019-02-13 | 2019-02-06 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.45 | 3 | 1930.84 | 149.25 | 152.95 | 68.67 | 1559.97 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11919116400 |  | 100243463 |  | T-1601-38 |  |  |  | 565 | EX | RPLC COMPANY SERVICE | 2600B | 1ST | 1330 E 1ST AV | 089 | S S | 2019-02-14 | U123965 | U907469 | 2011-08-05 | 2020-12-31 |  |  | MBLANKE | 2019-02-14 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 0.48333 | 1 | 2076.6 | 27.67 | 0 | 8.97 | 2039.96 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18604444700 |  | 100358810 |  | 6736232P |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | THOMAS | 706 THOMAS AV | 017 | PAR | 2019-02-14 | LSHARON | U125208 | 2018-04-19 | 2018-10-18 | 2020-04-30 |  | LSHARON | 2019-02-14 | 2018-08-27 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 25.1333 | 11 | 2616.49 | 1482.12 | 300.86 | 833.51 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18613647800 |  | 100260932 |  | 7352256G | 1747947 |  |  | 565 | EX | RPLC SL/17026728400/ | 2600B | EDGEWOOD | 901 EDGEWOOD AV | 019 | ASH | 2019-02-14 | U461496 | U131066 | 2018-05-22 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-02-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.31667 | 1 | 1801.1 | 18.35 | 0 | 6.12 | 1776.63 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18613648700 |  | 100260788 |  | 7352256K | 1747947 |  |  | 565 | EX | RPLC SL/17026728400/ | 2600B | NORWOOD | 1116 NORWOOD AV | 019 | ASH | 2019-02-14 | U461496 | U131066 | 2018-05-22 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-02-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.26667 | 1 | 1630.76 | 14.43 | 0 | 4.82 | 1611.51 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18639063700 |  | 100243461 |  | 7328284A | 1749172 |  |  | 565 | EX | RPLC SL/17026740200/ | 2600B | 1ST | 551 E 1ST AV | 089 | S S | 2019-02-14 | MBLANKE | U131066 | 2018-08-29 | 2019-12-31 |  |  | MBLANKE | 2019-02-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.86667 | 1 | 1930.44 | 49.57 | 0 | 16.08 | 1864.79 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18664276800 |  | 100281956 |  | 6712232O |  |  |  | 566 | EX | DEMO / ABANDON / RI 01-02-19 | 2621P | MAIN | 617 MAIN AV | 209 | GEO | 2019-02-14 | RVANDER | U124962 | 2018-12-28 | 2019-02-13 | 2019-03-06 |  | RVANDER | 2019-02-14 | 2019-01-03 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 12.9 | 5 | 960.03 | 788.51 | 0 | 171.52 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19026857400 |  | 501257089 |  | 6708228D | 1960832 | U461383 |  | 555 | EX | INSTALL 80' OF 2"PMMP MAIN | 2600B | WARD HALL | 237 WARD HALL MN | 209 | GEO | 2019-02-22 | U131296 | U461383 | 2019-01-22 | 2019-03-28 | 2019-03-31 | 2019-02-14 | BGRAVES | 2019-02-14 | 2019-02-14 | 2019-02-14 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP8574 |  |  | 100 | 055532190268574 | 17.9833 | 194 | 5253.13 | 999.99 | 433 | 211.79 | 2933.52 | 0 | 10.98 | 663.85 | 97
KY | KY - CENTRAL | 2632 | 19666816100 |  | 100356665 |  | 7260280M | 1748617 |  |  | 565 | EX | RPLC SL/17026734200/ | 2600B | LIMESTONE TER | 685 LIMESTONE TER | 161 | MAY | 2019-02-18 | U461478 | U131066 | 2019-01-07 | 2019-11-27 |  |  | DAVID STAGGS | 2019-02-14 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1125.75 | 0 | 0 | 0 | 1125.75 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19666816200 |  | 100356664 |  | 7260280M | 1748617 |  |  | 566 | EX | ABND SL/17026734200/ | 2600B | LIMESTONE TER | 695 LIMESTONE TER | 161 | MAY | 2019-03-01 | U461478 | U131066 | 2019-01-07 | 2019-11-27 |  |  | DAVID STAGGS | 2019-02-14 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26320043 |  | 1 | 292.29 | 0 | 0 | 0 | 292.29 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673013100 |  | 100463065 |  | 6720208L |  |  |  | 565 | EX | GRADE 2 */ REPLACE SERV | 2621P | RICHMOND | 2899 RICHMOND RD | 067 | LEX | 2019-02-15 | U124841 | U129939 | 2019-01-27 | 2019-01-30 | 2019-02-17 |  | MCRAIG | 2019-02-14 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.1333 | 4 | 1516.65 | 1381.19 | 18.24 | 117.22 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19681113500 |  | 100314538 |  | 6716212L |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | UPPER | 521 S UPPER ST 1 | 067 | LEX | 2019-02-15 | U126308 | U125208 | 2019-02-13 | 2019-02-13 | 2019-02-13 |  | JENSMIN | 2019-02-14 | 2019-02-14 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.1833 | 5 | 8051.65 | 1186.49 | 330.25 | 222.89 | 6312.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19681257000 |  | 100427391 |  | 6720208K |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BRIDGEPORT | 2088 BRIDGEPORT DR | 067 | LEX | 2019-02-18 | U125208 | U129939 | 2019-02-14 | 2019-02-06 | 2019-02-24 |  | DBANKS | 2019-02-14 | 2019-02-08 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.3667 | 2 | 2391.52 | 251.81 | 201.44 | 118.49 | 1819.78 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 08721745300 |  | 100446240 | 66 | X-1207-33 |  |  |  | 566 | EX | ABANDON/ IDLE 48MO/ RI 02-2008 | 2621P | DANIELS ADDITI | 407 DANIELS ADDITI | 065 | RAV | 2019-02-15 | DENNING | KSTEEL1 | 2008-02-28 | 2014-12-23 |  |  | DENNING | 2019-02-15 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.4833 | 1 | 184.09 | 137.91 | 0 | 46.18 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 14242006300 |  | 100426213 |  | 7364188G |  |  |  | 566 | EX | ABANDON / RA 06-07-2012 | 2621P | KY FIELD | KY FIELD | 159 | INE | 2019-02-18 | U125208 | U125208 | 2014-08-12 | 2014-06-09 |  |  | JCKIRK | 2019-02-15 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.7333 | 1 | 120.99 | 114.21 | 0 | 6.78 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 16026683601 |  | 501204687 |  | 6720220M | 1642409 | U461383 |  | 555 | EX | INSTALL 800' OF 2"/4"PMMP MAIN | 2600B | PROVIDENCE PLACE | 1255 PROVIDENCE PLACE PY LOT 3 | 067 | LEX | 2019-02-20 | U129900 | U461383 | 2019-02-04 | 2019-03-12 | 2019-04-01 | 2019-02-14 | STEVE CANOY | 2019-02-15 | 2019-02-04 | 2019-01-23 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP6836 |  |  | 100 | 055532160266836 | 190.1667 | 22241 | 65648.19 | 11120.39 | 3109.32 | 3423.41 | 39538.77 | 0 | 151.53 | 8304.77 | 967
KY | KY - WEST | 2621 | 18577679500 |  | 100441868 |  | 6716212H | 1743881 |  |  | 565 | EX | REPLACE SL W/17026695600 | 2600B | 4TH | 421 W 4TH ST | 067 | LEX | 2019-05-29 | U461423 | U131066 | 2018-01-29 | 2019-12-31 |  |  | KKOUNS | 2019-02-15 | 2018-12-14 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 2 | 699.53 | 536.27 | 0 | 163.26 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18613648000 |  | 100260934 |  | 7352256G | 1747947 |  |  | 565 | EX | RPLC SL/17026728400/ | 2600B | EDGEWOOD | 911 EDGEWOOD AV | 019 | ASH | 2019-02-15 | U461496 | U131066 | 2018-05-22 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-02-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.23333 | 1 | 2743.89 | 13.88 | 0 | 4.64 | 2725.37 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18613649100 |  | 100260784 |  | 7352256K | 1747947 |  |  | 565 | EX | RPLC SL/17026728400/ | 2600B | SHELBY | 1117 SHELBY AV | 019 | ASH | 2019-02-15 | U461496 | U131066 | 2018-05-22 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-02-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.31667 | 1 | 2072.49 | 17.23 | 0 | 5.74 | 2049.52 | 0 | 0 | 0
KY | KY - EAST | 2633 | 18627636700 |  | 100266035 |  | 7356156T |  |  |  | 566 | EX | ABANDON - FARM TAP | 2621P | BROAD BOTTOM | 1115 BROAD BOTTOM RD | 195 | PIK | 2019-02-18 | U125208 | U125208 | 2018-07-16 | 2018-07-31 |  |  | JCKIRK | 2019-02-15 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.0667 | 1 | 140.82 | 132.94 | 0 | 7.88 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 18627637000 |  | 500178154 |  | 7360152E |  |  |  | 566 | VO | ABANDON - FARM TAP | 2621P | BROAD BOTTOM | 1484 BROAD BOTTOM RD | 195 | PIK | 2019-02-18 |  | U125208 | 2018-07-16 | 2018-07-31 |  |  | JCKIRK | 2019-02-15 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.15 | 1 | 146.35 | 138.13 | 0 | 8.22 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 18627637200 |  | 100266009 |  | 7356156T |  |  |  | 566 | EX | ABANDON - FARM TAP | 2621P | P26 | P26 | 195 | BRO | 2019-02-18 | U125208 | U125208 | 2018-07-16 | 2018-07-31 |  |  | BBMULLI | 2019-02-15 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.43333 | 1 | 28.33 | 26.75 | 0 | 1.58 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 18627638600 |  | 100451905 |  | 7356156T |  |  |  | 566 | EX | ABANDON - FARM TAP | 2621P | P26 | P26 | 195 | BRO | 2019-02-18 | U125208 | U125208 | 2018-07-16 | 2018-07-31 |  |  | BBMULLI | 2019-02-15 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.4333 | 1 | 161.37 | 152.32 | 0 | 9.05 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 18627639900 |  | 100266011 |  | 7356156T |  |  |  | 566 | EX | ABANDON - FARM TAP | 2621P | BROAD BOTTOM | 1115 BROAD BOTTOM RD | 195 | PIK | 2019-02-18 | U125208 | U125208 | 2018-07-16 | 2018-07-31 |  |  | JCKIRK | 2019-02-15 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.96667 | 1 | 65.66 | 61.96 | 0 | 3.7 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 18627640600 |  | 100430178 |  | 7356156T |  |  |  | 566 | EX | ABANDON - FARM TAP | 2621P | BROAD BOTTOM | 1068 BROAD BOTTOM RD | 195 | PIK | 2019-02-18 | U125208 | U125208 | 2018-07-16 | 2018-07-31 |  |  | JCKIRK | 2019-02-15 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.0833 | 1 | 73.18 | 69.07 | 0 | 4.11 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19026858000 |  | 500126028 |  | 6688228K | 1960937 | U461383 |  | 555 | EX | INSTALL 400' OF 4"PMLP MAIN | 2600B | COLLISION CENTER | 107 COLLISION CENTER DR | 073 | FRA | 2019-02-19 | U131296 | U461383 | 2019-01-27 | 2019-02-25 | 2019-03-01 | 2019-02-15 | BJACKSON | 2019-02-15 | 2019-02-04 | 2019-02-04 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP8580 |  |  | 100 | 055532190268580 | 83 | 4200 | 42516.78 | 4671.24 | 2048.32 | 1543.96 | 28823.04 | 0 | 52.67 | 5377.55 | 420
KY | KY - WEST | 2621 | 19026861500 |  |  |  | 6720212N | 1961352 | U461383 |  | 562 | EX | ABANDON 333' OF 3"BSLP MAIN | 2621P | WHITE | WHITE AV | 067 | LEX | 2019-03-07 | U129900 | U461383 | 2019-02-11 | 2019-03-29 | 2019-04-01 | 2019-02-15 | KKINDER | 2019-02-15 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP8615 | AMRCB |  | 100 | 056232190268615 |  | 0 | 2950.93 | 2521.66 | 149.87 | 279.4 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19666815800 |  | 100356668 |  | 7260280M | 1748617 |  |  | 565 | EX | RPLC SL/17026734200/ | 2600B | LIMESTONE TER | 655 LIMESTONE TER | 161 | MAY | 2019-02-25 | U461478 | U131066 | 2019-01-07 | 2019-11-27 |  |  | DAVID STAGGS | 2019-02-15 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1046.58 | 0 | 0 | 0 | 1046.58 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19666815900 |  | 100356667 |  | 7260280M | 1748617 |  |  | 565 | EX | RPLC SL/17026734200/ | 2600B | LIMESTONE TER | 665 LIMESTONE TER | 161 | MAY | 2019-02-25 | U461478 | U131066 | 2019-01-07 | 2019-11-27 |  |  | DAVID STAGGS | 2019-02-15 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1332.86 | 0 | 0 | 0 | 1332.86 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19666816000 |  | 100356666 |  | 7260280M | 1748617 |  |  | 565 | EX | RPLC SL/17026734200/ | 2600B | LIMESTONE TER | 675 LIMESTONE TER | 161 | MAY | 2019-02-25 | U461478 | U131066 | 2019-01-07 | 2019-11-27 |  |  | DAVID STAGGS | 2019-02-15 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1116.46 | 0 | 0 | 0 | 1116.46 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19673022200 |  | 500126028 |  | 6688228K | 1960937 |  |  | 565 | EX | REPLACE SL W/19026858000 | 2600B | COLLISION CENT | 107 COLLISION CENT DR | 073 | FRA | 2019-02-19 | U125559 | U131066 | 2019-01-28 | 2019-12-31 |  |  | BJACKSON | 2019-02-15 | 2019-02-07 | 2019-02-07 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 4.3833 | 1 | 1550.05 | 244.39 | 0 | 81.49 | 1224.17 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19673023400 |  | 100460015 |  | 6688228K | 1960937 |  |  | 565 | EX | REPLACE SL W/19026858000 | 2600B | PULLIAM | 103 PULLIAM DR | 073 | FRA | 2019-02-19 | U125559 | U131066 | 2019-01-28 | 2019-12-31 |  |  | BJACKSON | 2019-02-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 4612.24 | 0 | 0 | 0 | 4612.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673389800 |  | 100314585 |  | 6716212L |  |  |  | 566 | EX | DEMO / ABANDON / RI 1-29-19 | 2621P | HIGH | 132 W HIGH ST | 067 | LEX | 2019-02-15 | MCRAIG | U125208 | 2019-01-29 | 2019-02-15 | 2019-02-17 |  | MCRAIG | 2019-02-15 | 2019-02-13 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 34.3167 | 5 | 2090.74 | 1680.84 | 84.28 | 99.8 | 225.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19679190300 |  | 500020318 |  | 6708204L |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LANTERN | 87 LANTERN WY | 113 | NIC | 2019-02-18 | U125208 | U125208 | 2019-02-04 | 2019-02-07 | 2019-02-25 |  | DBANKS | 2019-02-15 | 2019-02-07 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.6167 | 6 | 3495.58 | 1070.53 | 152.95 | 223.85 | 2048.25 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19681263900 |  | 100280281 |  | 6688228J |  |  |  | 566 | EX | ABANDON SERV LINE | 2621P | DEWEY | 218 DEWEY CT | 073 | FRA | 2019-02-21 | U125208 | U129939 | 2019-02-14 | 2019-02-14 |  |  | CDESPAI | 2019-02-15 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 1.1 | 1 | 1719.9 | 50.41 | 10.36 | 63.92 | 1595.21 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19681574400 |  | 100303442 |  | 6712208C |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | WINTERBERRY | 2187 WINTERBERRY DR B | 067 | LEX | 2019-02-15 | DBANKS | U131552 | 2019-02-15 | 2019-06-18 | 2020-12-31 |  | DBANKS | 2019-02-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26210022 | 1.9167 | 1 | 3839.5 | 112.32 | 179.77 | 60.67 | 3486.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07689826300 |  | 100327718 | 26 | 16720212M | 1199570 |  |  | 566 | EX | RETIRE S/L WITH 11-0263580-000 | 2621P | DESHA | 232 DESHA RD | 067 | LEX | 2019-02-17 | U461383 | U803006 | 2007-06-06 | 2014-12-23 |  |  | CONSTRUCTION SERVICES | 2019-02-17 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 19734920800 |  | 100287581 |  | 6720212G | 1855823 |  |  | 565 | EX | RPLC SL/18026797400/ | 2600B | MARCELLUS | 986 MARCELLUS DR | 067 | LEX | 2020-02-17 | U461375 | U131066 | 2019-08-21 | 2020-06-30 |  |  | LARRY BROWN | 2019-02-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1592.99 | 0 | 0 | 0 | 1592.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19734920900 |  | 100287620 |  | 6720212G | 1855823 |  |  | 565 | EX | RPLC SL/18026797400/ | 2600B | MARCELLUS | 987 MARCELLUS DR | 067 | LEX | 2020-02-17 | U461375 | U131066 | 2019-08-21 | 2020-06-30 |  |  | LARRY BROWN | 2019-02-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1762.99 | 0 | 0 | 0 | 1762.99 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 06663654100 |  | 500296432 |  | 6764176O |  |  |  | 566 | EX | ABANDON S/L IDLE 24 MONTHS | 2621P | KIRKLAND | 499 KIRKLAND AV | 065 | RAV | 2019-02-20 | JTOY | CTAULBE | 2006-10-19 | 2014-12-23 |  |  | DENNING | 2019-02-18 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9.3 | 3 | 594.64 | 471.49 | 0 | 123.15 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12965296000 |  | 100327930 |  | 16720208A | 1199570 |  |  | 566 | EX | RETIRE S/L WITH 11-0263580-00 | 2621P | SYCAMORE | 213 SYCAMORE RD | 067 | LEX | 2019-02-18 | U461383 | U124967 | 2012-04-16 | 2014-12-01 |  |  | CONSTRUCTION SERVICES | 2019-02-18 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 12968618300 |  | 100337044 |  | NEW | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | 5TH | 304 E 5TH ST | 067 | LEX | 2019-02-18 | LSTANFI | U124967 | 2012-05-07 | 2019-02-18 |  |  | LSTANFI | 2019-02-18 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.36667 | 1 | 663.32 | 22.1 | 0 | 1.32 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18594024800 |  | 100337040 |  | 6720212I | 1855043 |  |  | 566 | EX | ABANDON SL | 2621P | OHIO | 450 OHIO ST | 067 | LEX | 2019-03-04 | U125208 | U125765 | 2018-03-13 | 2019-02-18 |  |  | LSTANFI | 2019-02-18 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.33333 | 1 | 661.38 | 20.28 | 0 | 1.2 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18594265600 |  | 100287445 |  | 6720212G | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | MEADOW | 1005 MEADOW LN | 067 | LEX | 2019-02-18 | LSTANFI | U125765 | 2018-03-14 | 2019-02-08 |  |  | LSTANFI | 2019-02-18 | 2019-02-08 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.4333 | 2 | 720.24 | 75.86 | 0 | 4.48 | 639.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18613648100 |  | 100260935 |  | 7352256G | 1747947 |  |  | 565 | EX | RPLC SL/17026728400/ | 2600B | EDGEWOOD | 915 EDGEWOOD AV | 019 | ASH | 2019-02-18 | U461496 | U131066 | 2018-05-22 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-02-18 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.18333 | 1 | 1849.72 | 10 | 0 | 3.35 | 1836.37 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18613648600 |  | 100260789 |  | 7352256K | 1747947 |  |  | 565 | EX | RPLC SL/17026728400/ | 2600B | NORWOOD | 1112 NORWOOD AV | 019 | ASH | 2019-02-18 | U461496 | U131066 | 2018-05-22 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-02-18 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.36667 | 1 | 1382.69 | 20.01 | 0 | 6.67 | 1356.01 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18613650300 |  | 100260938 |  | 7352256G | 1747947 |  |  | 565 | EX | REPLACE SL W/17026728400 | 2600B | COGAN | 2918 COGAN ST | 019 | ASH | 2019-02-18 | U461496 | U131066 | 2018-05-22 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-02-18 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.1 | 1 | 1364.9 | 6.67 | 0 | 2.22 | 1356.01 | 0 | 0 | 0
KY | KY - EAST | 2633 | 18627637300 |  | 100457732 |  | 7356156T |  |  |  | 566 | EX | ABANDON - FARM TAP | 2621P | STAMPER | 45 STAMPER LN | 195 | PIK | 2019-02-22 | U125208 | U125208 | 2018-07-16 | 2018-07-31 |  |  | JCKIRK | 2019-02-18 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.16667 | 1 | 13.38 | 10.32 | 0 | 3.06 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 18627637500 |  | 100266033 |  | 7356156T |  |  |  | 566 | EX | ABANDON - FARM TAP | 2621P | BROAD BOTTOM | 1492 BROAD BOTTOM RD | 195 | PIK | 2019-02-22 | U125208 | U125208 | 2018-07-16 | 2018-07-31 |  |  | JCKIRK | 2019-02-18 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.36667 | 1 | 30.1 | 23.24 | 0 | 6.86 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18639063600 |  | 100251808 |  | 7328284A | 1749172 |  |  | 565 | EX | RPLC SL/17026740200/ | 2600B | 1ST | 535 E 1ST ST | 089 | S S | 2019-02-18 | U123965 | U131066 | 2018-08-29 | 2019-12-31 |  |  | MBLANKE | 2019-02-18 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.05 | 1 | 2336.54 | 2.31 | 0 | 0.75 | 2333.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18644563100 |  | 100306227 |  | 6712212K |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | ROANOKE | 1513 ROANOKE RD | 067 | LEX | 2019-02-22 | U125208 | U125208 | 2018-09-20 | 2019-02-18 | 2020-09-30 |  | LSTANFI | 2019-02-18 | 2019-01-10 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.2167 | 3 | 1956.34 | 189.52 | 120.5 | 55.01 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18651929700 |  | 100302874 |  | 6712212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | OLD NASSAU | 2039 OLD NASSAU RD | 067 | LEX | 2019-02-22 | U125208 | U125208 | 2018-10-19 | 2019-04-18 | 2020-10-31 |  | LSTANFI | 2019-02-18 | 2019-01-24 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.75 | 8 | 3576.71 | 455.11 | 200.75 | 117.62 | 2803.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18659423200 |  | 100336517 |  | 6720212I | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | OHIO | 316 OHIO ST | 067 | LEX | 2019-02-26 | U125208 | AOC SYST | 2018-11-30 | 2019-02-18 | 2019-12-31 |  | LSTANFI | 2019-02-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.6167 | 1 | 4267.34 | 405.56 | 264.01 | 24.06 | 3573.71 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026858200 |  | 501198562 |  | 6712216D | 1852431 | U131982 |  | 555 | EX | INSTALL 300' OF 2" PMMP MAIN | 2600B | JENNA REST | 2828 JENNA REST RD | 067 | LEX | 2019-02-21 | U129900 | U131982 | 2019-01-28 | 2019-02-25 | 2019-02-28 | 2019-02-18 | JPASLEY | 2019-02-18 | 2019-02-11 | 2019-02-11 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP8582 |  |  | 100 | 055532190268582 | 55.4667 | 2135 | 20136.36 | 3265.84 | 881.88 | 1076.76 | 12327.77 | 0 | 39.03 | 2545.08 | 305
KY | KY - WEST | 2621 | 19026863100 |  |  |  | 6720212K | 1961494 | U461383 |  | 577 | EX | INSTALL NEW CHAIN LINK FENCE | 2600E | GOODWIN | 1039 GOODWIN DR | 067 | LEX | 2019-02-26 | U462463 | U461383 | 2019-02-15 | 2019-05-28 | 2019-06-01 | 2019-02-18 | MIKE MCKUNE | 2019-02-18 | 2019-02-15 | 2019-02-15 | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00577 | 3200577 |  |  | WP8631 |  |  | 100 | 057732190268631 | 6.9167 | 2 | 6867.37 | 394.15 | 5573.22 | 29.51 | 0 | 0 | 0.94 | 869.55
KY | KY - CENTRAL | 2632 | 19681485800 |  | 100355196 |  | 7260280N |  |  |  | 566 | EX | CITY/DEMO - 02/15/19 EMER | 2621P | FOREST | 919 FOREST AV | 161 | MAY | 2019-02-18 | SDADAMS | U125208 | 2019-02-15 | 2019-02-15 |  |  | SDADAMS | 2019-02-18 | 2019-02-15 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 14.7167 | 4 | 1054.51 | 833.55 | 32.77 | 188.19 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19681865300 |  | 100303571 |  | 6712208C |  |  |  | 565 | EX | GRADE 1 REPLACE | 2621P | OLEANDER | 2224 OLEANDER CT | 067 | LEX | 2019-02-18 | CWEMPE | U129939 | 2019-02-17 | 2019-02-17 | 2019-02-17 |  | CWEMPE | 2019-02-18 | 2019-02-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 31.3833 | 6 | 2300.53 | 2031.19 | 136.22 | 133.12 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 01478235000 |  | 100337004 |  | 6720212E | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | 5TH | 268 E 5TH ST | 067 | LEX | 2019-02-22 | U125208 | DMCCULL | 2001-08-02 | 2019-02-19 |  |  | LMCDONA | 2019-02-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.9667 | 1 | 848.56 | 100.41 | 102.29 | 5.96 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 05623354700 |  | 100336996 | 34 | V-1021-51 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | 5TH | 232 E 5TH ST | 067 | LEX | 2019-02-22 | U125208 | MPILON | 2005-09-19 | 2019-02-19 |  |  | LMCDONA | 2019-02-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.5333 | 1 | 819.27 | 78.41 | 96.3 | 4.66 | 639.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12965305900 |  | 100285304 |  | X-1206-13 |  |  |  | 566 | EX | ABANDON METER ONLY | 2621P | BROADWAY | 155 BROADWAY ST | 065 | IRV | 2019-02-19 | DENNING | U124967 | 2012-04-16 | 2014-12-23 | 2018-11-10 |  | DENNING | 2019-02-19 | 2019-02-18 |  | D | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 15.05 | 6 | 965.67 | 766.96 | 0 | 198.71 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18026781100 |  |  |  | 6720216M | 1425507 | BKSLONE |  | 584 | EX | R-1183 RETIRE EXIST REG STA | 2600E | COLESBURY | 1512 COLESBURY CR | 067 | LEX | 2019-03-12 | U462463 | BKSLONE | 2018-06-19 | 2018-12-31 | 2018-12-31 | 2019-02-19 | CYNTHIA FARIS | 2019-02-19 | 2019-02-18 | 2019-02-18 | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00584 | 3207514 |  |  | WP7811 |  |  | 100 | 751432180267811 | 21.2333 | 0 | 5015.16 | 1877.49 | 0 | 316.07 | 2821.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18611598400 |  | 100293354 |  | 6720216F |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BARKSDALE | 1880 BARKSDALE DR | 067 | LEX | 2019-02-22 | U125208 | U125208 | 2018-05-14 | 2018-11-09 | 2020-05-31 |  | DBANKS | 2019-02-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.5833 | 1 | 1654.6 | 91.03 | 182.9 | 49.17 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18613591300 |  | 100458787 |  | 6696212G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SPRING RUN | 173 SPRING RUN ST | 239 | VER | 2019-02-19 | CDESPAI | U125208 | 2018-05-22 | 2018-11-21 | 2020-05-31 |  | CDESPAI | 2019-02-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.2167 | 1 | 2078.51 | 147.05 | 153.66 | 186.49 | 1591.31 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18613647000 |  | 100260937 |  | 7352256G | 1747947 |  |  | 565 | EX | RPLC SL/17026728400/ | 2600B | COGAN | 2912 COGAN ST | 019 | ASH | 2019-02-19 | U461496 | U131066 | 2018-05-22 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-02-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.31667 | 1 | 1859.34 | 17.23 | 0 | 5.74 | 1836.37 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18613647100 |  | 100260939 |  | 7352256G | 1747947 |  |  | 565 | EX | RPLC SL/17026728400/ | 2600B | COGAN | 2922 COGAN ST | 019 | ASH | 2019-02-19 | U461496 | U131066 | 2018-05-22 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-02-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.23333 | 1 | 966.25 | 12.75 | 0 | 4.28 | 949.22 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18613648500 |  | 100260790 |  | 7352256K | 1747947 |  |  | 565 | EX | RPLC SL/17026728400/ | 2600B | NORWOOD | 1104 NORWOOD AV | 019 | ASH | 2019-02-19 | U461496 | U131066 | 2018-05-22 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-02-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.2 | 1 | 1852.67 | 12.21 | 0 | 4.09 | 1836.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18644562200 |  | 100306274 |  | 6712212L |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | FAIR OAKS | 1977 FAIR OAKS DR 1FL | 067 | LEX | 2019-02-22 | U125208 | U125208 | 2018-09-20 | 2019-03-19 | 2020-09-30 |  | DBANKS | 2019-02-19 | 2019-01-16 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.2 | 3 | 2779.84 | 300.14 | 215.32 | 138.38 | 2126 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18661647700 |  | 100313612 |  | 6716208B |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HUMMINGBIRD | 342 HUMMINGBIRD LN | 067 | LEX | 2019-02-21 | U125208 | U125208 | 2018-12-12 | 2019-02-19 | 2020-12-31 |  | DBANKS | 2019-02-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.1167 | 1 | 1867.23 | 179.16 | 0 | 96.76 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18664360500 |  | 100282279 |  | 6712228B |  |  |  | 566 | EX | ABANDON SL FOR DEMO PS MAILBOX | 2621P | COURT | 214 N COURT ST | 209 | GEO | 2019-02-19 | RVANDER | U131800 | 2018-12-28 | 2019-03-07 | 2019-03-07 |  | RVANDER | 2019-02-19 | 2019-02-07 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 9.3333 | 6 | 554.61 | 523.2 | 0 | 31.41 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19665382300 |  | 100308608 |  | 6716212N |  |  |  | 566 | EX | ABANDON / DEMO / RA 01/04/19 | 2621P | PARKWAY | 437 PARKWAY DR | 067 | LEX | 2019-02-21 | U125208 | U131002 | 2019-01-02 | 2019-01-07 | 2019-02-16 |  | LMCDONA | 2019-02-19 | 2019-02-06 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.3667 | 2 | 877.69 | 224.45 | 0 | 13.34 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19665386900 |  | 100308607 |  | 6716212N |  |  |  | 566 | EX | ABANDON / DEMO / RA 01/07/19 | 2621P | PARKWAY | 441 PARKWAY DR | 067 | LEX | 2019-02-21 | U125208 | U131002 | 2019-01-02 | 2019-01-07 | 2019-02-16 |  | LMCDONA | 2019-02-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.26667 | 3 | 653.52 | 12.86 | 0 | 0.76 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19665389400 |  | 100308606 |  | 6716212N |  |  |  | 566 | EX | ABANDON / DEMO / RA 01/08/19 | 2621P | PARKWAY | 445 PARKWAY DR | 067 | LEX | 2019-02-21 | U125208 | U131002 | 2019-01-02 | 2019-01-08 | 2019-02-16 |  | LMCDONA | 2019-02-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.26667 | 1 | 654.01 | 13.32 | 0 | 0.79 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19665390000 |  | 100308605 |  | 6716212N |  |  |  | 566 | EX | ABANDON / DEMO / RI 01/04/19 | 2621P | PARKWAY | 449 PARKWAY DR | 067 | LEX | 2019-02-21 | U125208 | U131002 | 2019-01-02 | 2019-01-07 | 2019-02-16 |  | LMCDONA | 2019-02-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.25 | 1 | 653.47 | 12.8 | 0 | 0.77 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19665390500 |  | 100308604 |  | 6716212N |  |  |  | 566 | EX | ABANDON / DEMO / RA 01/08/19 | 2621P | PARKWAY | 453 PARKWAY DR | 067 | LEX | 2019-02-21 | U125208 | U131002 | 2019-01-02 | 2019-01-08 | 2019-02-16 |  | LMCDONA | 2019-02-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.2167 | 1 | 1405.13 | 64.06 | 0 | 3.8 | 1337.27 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19666814000 |  | 100355140 |  | 7260280M | 1748617 |  |  | 565 | EX | RPLC SL/17026734200/ | 2600B | LEXINGTON | 304 LEXINGTON ST | 161 | MAY | 2019-03-04 | U461478 | U131066 | 2019-01-07 | 2019-11-27 |  |  | DAVID STAGGS | 2019-02-19 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2564.05 | 0 | 0 | 0 | 2564.05 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19666814300 |  | 100355133 |  | 7260280M | 1748617 |  |  | 565 | EX | RPLC SL/17026734200/ | 2600B | LEXINGTON | 311 LEXINGTON ST | 161 | MAY | 2019-03-04 | U461478 | U131066 | 2019-01-07 | 2019-11-27 |  |  | DAVID STAGGS | 2019-02-19 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1808.2 | 0 | 0 | 0 | 1808.2 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19671980600 |  | 100430941 |  | 7340268A |  |  |  | 565 | EX | MOVE SERVICE LINE TO RR HOUSE | 2621P | PERRY | 605 PERRY ST RR | 089 | GRE | 2019-02-19 | MCOLLET | DYOUNG | 2019-01-22 | 2019-01-25 |  |  | MCOLLET | 2019-02-19 | 2019-02-18 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 10.3167 | 3 | 1152.92 | 625.86 | 119.6 | 407.46 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19671980900 |  | 100250838 |  | 7340268A |  |  |  | 566 | EX | ABDN W/565-605 RR-HOUSE GONE | 2621P | PERRY | 605 PERRY ST | 089 | GRE | 2019-02-19 | AMCCORM | DYOUNG | 2019-01-22 | 2019-01-25 |  |  | AMCCORM | 2019-02-19 | 2019-02-18 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 6.6167 | 3 | 643.86 | 401.11 | 0 | 242.75 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19680782300 |  | 501230104 |  | 6692228B | 1853102 |  |  | 565 | EX | REPLACE SL | 2600B | ELKHORN HILLS | 2001 ELKHORN HILLS LN | 073 | FRA | 2019-02-19 | U461322 | U131066 | 2019-02-11 | 2019-12-31 |  |  | STEVE CANOY | 2019-02-19 | 2019-02-15 | 2019-02-15 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 25.4833 | 6 | 6993.25 | 1498.48 | 0 | 477.51 | 5017.26 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19682215000 |  | 100458076 |  | 6720216M | 1425507 |  |  | 565 | EX | RPLC SL W/18026746600 | 2600B | COLESBURY | 1516 COLESBURY CR | 067 | LEX | 2019-02-19 | U461467 | U131279 | 2019-02-19 | 2019-12-20 |  |  | D REFFETT | 2019-02-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1
KY | KY - EAST | 2631 | 19682238100 |  | 100243436 |  | 7348268M | 1749172 |  |  | 565 | EX | REPLACE W/ 17026740200 | 2600B | 2ND | 204 E 2ND AV | 089 | S S | 2019-02-19 | MBLANKE | U125768 | 2019-02-19 | 2049-12-31 |  |  | MBLANKE | 2019-02-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.23333 | 1 | 2019.92 | 13.25 | 0 | 4.3 | 2002.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19682279300 |  | 100321230 |  | 716212P |  |  |  | 565 | EX | METER MOVE OUT | 2621P | TRANSYLVANIA | 333 TRANSYLVANIA PR 1F | 067 | LEX | 2019-02-19 | CWEMPE | U130193 | 2019-02-19 | 2019-02-19 | 2019-02-19 |  | CWEMPE | 2019-02-19 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 38.2 | 5 | 2413.77 | 2001.04 | 155.84 | 256.89 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 99379245600 |  | 100337129 |  | 6720212I | 1855043 |  |  | 566 | EX | ABANDON / IDLE | 2621P | 5TH | 307 E 5TH ST | 067 | LEX | 2019-02-22 | U125208 | KEMBERT | 1999-02-15 | 2019-02-19 |  |  | LMCDONA | 2019-02-19 | 2018-09-04 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.6167 | 3 | 824.92 | 78.1 | 102.29 | 4.63 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19682512700 |  | 100337686 |  | 6720212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MAPLE | 625 MAPLE AV A | 067 | LEX | 2019-02-21 | U125208 | U130193 | 2019-02-20 | 2019-02-18 | 2019-02-18 |  | MCRAIG | 2019-02-20 | 2019-02-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 80.2667 | 7 | 6180.1 | 4760.78 | 248.87 | 282.45 | 888 | 0 | 0 | 0
KY | KY - EAST | 2633 | 06643104400 |  | 100250696 | 48 | 7376184A |  |  |  | 566 | EX | ABANDON / RI 03-29-2005 | 2621P | SR292 | SR292 | 159 | LOV | 2019-02-22 | U125208 | LDAVIS | 2006-03-30 | 2049-12-31 |  |  | JCKIRK | 2019-02-21 | 2019-01-25 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 8.0833 | 2 | 673.02 | 513.7 | 20.16 | 139.16 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 07689161300 |  | 100447499 |  | 7260280M |  |  |  | 566 | EX | DEMO / ABANDON W/322 UNION | 2621P | UNION | 320 UNION ST | 161 | MAY | 2019-02-22 | U125208 | U903504 | 2007-06-01 | 2019-02-21 |  |  | RALLISO | 2019-02-21 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 6.7833 | 2 | 591.24 | 381.28 | 10.38 | 199.58 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 08761215100 |  | 100304645 | 40 | 16712212P | 1855043 |  |  | 566 | EX | SOII - ABANDON / RA 12-01-2008 | 2621P | NORMANDY | 1729 NORMANDY RD | 067 | LEX | 2019-02-22 | U125208 | CTSTEEL | 2008-12-01 | 2019-02-21 |  |  | LMCDONA | 2019-02-21 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.66667 | 1 | 772.02 | 33.82 | 96.3 | 2 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11894295800 |  | 100304594 |  | ? | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | NORMANDY | 1825 NORMANDY RD | 067 | LEX | 2019-02-22 | U125208 | U906314 | 2011-03-04 | 2019-02-21 |  |  | LMCDONA | 2019-02-21 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.85 | 1 | 836.64 | 94.8 | 96.3 | 5.64 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12975906200 |  | 100430684 |  | 6720212I | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | OHIO | 367 OHIO ST 1FL | 067 | LEX | 2019-03-26 | U125208 | U123854 | 2012-06-11 | 2019-02-21 |  |  | LMCDONA | 2019-02-21 | 2019-02-18 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.2167 | 2 | 1357.62 | 173.35 | 74.31 | 10.3 | 1099.66 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18610330500 |  | 100467315 |  | 6700212N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LYNNWOOD | 339 LYNNWOOD DR | 239 | VER | 2019-02-21 | CDESPAI | U125208 | 2018-05-09 | 2018-11-08 | 2020-05-31 |  | CDESPAI | 2019-02-21 | 2019-02-19 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.95 | 2 | 2382.18 | 180.5 | 152.95 | 228.95 | 1819.78 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18613647200 |  | 100260941 |  | 7352256G | 1747947 |  |  | 565 | EX | RPLC SL/17026728400/ | 2600B | COGAN | 3000 COGAN ST | 019 | ASH | 2019-02-21 | U461496 | U131066 | 2018-05-22 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-02-21 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 3.2667 | 1 | 1732.51 | 181.02 | 0 | 60.51 | 1490.98 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18613650500 |  | 100260940 |  | 7352256G | 1747947 |  |  | 565 | EX | REPLACE SL W/17026728400 | 2600B | COGAN | 2926 COGAN ST | 019 | ASH | 2019-02-21 | U461496 | U131066 | 2018-05-22 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-02-21 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 2.2167 | 1 | 1112.93 | 122.7 | 0 | 41.01 | 949.22 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18614938100 |  | 100412681 |  | 6700212I |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BRYANWOOD | 316 BRYANWOOD ST | 239 | VER | 2019-02-21 | CDESPAI | U125208 | 2018-05-25 | 2018-11-21 | 2020-05-31 |  | CDESPAI | 2019-02-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.7833 | 1 | 2146.52 | 126.9 | 224.17 | 160.97 | 1634.48 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18639064200 |  | 100243438 |  | 7328284B | 1749172 |  |  | 565 | EX | RPLC SL/17026740200/ | 2600B | 2ND | 192 E 2ND AV | 089 | S S | 2019-02-21 | MBLANKE | U131066 | 2018-08-29 | 2019-12-31 |  |  | MBLANKE | 2019-02-21 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.1 | 1 | 2072.07 | 5.77 | 0 | 1.87 | 2064.43 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18648782700 |  | 100337048 |  | 6720212I | 1855043 |  |  | 566 | EX | II- ABANDON SL | 2621P | 5TH | 322 E 5TH ST | 067 | LEX | 2019-03-22 | U125208 | U126926 | 2018-10-05 | 2019-02-21 |  |  | LMCDONA | 2019-02-21 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.45 | 1 | 24.44 | 23.08 | 0 | 1.36 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18648782900 |  | 100337049 |  | 6720212I | 1855043 |  |  | 566 | EX | II- ABANDON SL | 2621P | 5TH | 324 E 5TH ST | 067 | LEX | 2019-03-22 | U125208 | U126926 | 2018-10-05 | 2019-02-21 |  |  | LMCDONA | 2019-02-21 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.7167 | 1 | 873.15 | 138.84 | 86.18 | 8.23 | 639.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19666813800 |  | 100355139 |  | 7260280M | 1748617 |  |  | 565 | EX | RPLC SL/17026734200/ | 2600B | LEXINGTON | 302 LEXINGTON ST | 161 | MAY | 2019-03-04 | U461478 | U131066 | 2019-01-07 | 2019-11-27 |  |  | DAVID STAGGS | 2019-02-21 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 3639.17 | 0 | 0 | 0 | 3639.17 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19666813900 |  | 100355138 |  | 7260280M | 1748617 |  |  | 565 | EX | RPLC SL/17026734200/ | 2600B | LEXINGTON | 303 LEXINGTON ST | 161 | MAY | 2019-03-04 | U461478 | U131066 | 2019-01-07 | 2019-11-27 |  |  | DAVID STAGGS | 2019-02-21 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1313.04 | 0 | 0 | 0 | 1313.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19681616900 |  | 100461567 |  | 6720200F |  |  |  | 565 | EX | GR 2+ LK ON SERVICE D221810 | 2621P | LEAFLAND | 2129 LEAFLAND PL | 067 | LEX | 2019-02-21 | DBANKS | U131169 | 2019-02-15 | 2019-02-18 | 2019-03-08 |  | DBANKS | 2019-02-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.4167 | 1 | 2415.04 | 138.86 | 152.95 | 74.98 | 2048.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19681943900 |  | 100461482 |  | 6720200F |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LEAFLAND | 2125 LEAFLAND PL | 067 | LEX | 2019-02-22 | U125208 | U125208 | 2019-02-18 | 2019-02-21 | 2021-02-28 |  | DBANKS | 2019-02-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.4 | 1 | 2388.63 | 195.89 | 152.95 | 105.78 | 1934.01 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19682019600 |  | 500796797 |  | 7260280M | 0250327 |  |  | 566 | EX | DEMO / ABN / CH & RA 02-19-19 | 2621P | UNION | 322 UNION ST REAR | 161 | MAY | 2019-02-22 | U125208 | U131718 | 2019-02-18 | 2019-04-18 | 2019-04-19 |  | SDADAMS | 2019-02-21 | 2019-02-21 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 10.7833 | 3 | 727.7 | 612 | 10.38 | 105.32 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19682189900 |  | 100279339 |  | 6688228K | 1960710 |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | WEEHAWKEN | 4 WEEHAWKEN LN | 073 | FRA | 2019-02-21 | CDESPAI | U129531 | 2019-02-19 | 2019-02-19 |  |  | CDESPAI | 2019-02-21 | 2019-02-19 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 18.5833 | 5 | 13221.32 | 860.88 | 471.94 | 1035.26 | 10853.24 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19682241200 |  | 100260782 |  | 7352260K | 1747947 |  |  | 565 | EX | REPLACE W/ 17026728400 | 2600B | SHELBY | 1105 SHELBY AV | 019 | ASH | 2019-02-21 | U461496 | U125768 | 2019-02-19 | 2049-12-31 |  |  | ROCKIE MULLINS | 2019-02-21 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 2.4167 | 1 | 1558.73 | 133.84 | 0 | 44.72 | 1380.17 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19682780900 |  | 100260791 |  | 7356256G | 1747947 |  |  | 565 | EX | REPLACE W/17026728400 | 2600B | NORWOOD | 1012 NORWOOD AV | 019 | ASH | 2019-02-21 | U461496 | U125768 | 2019-02-21 | 2049-12-31 |  |  | ROCKIE MULLINS | 2019-02-21 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 2.6 | 1 | 1628.24 | 145.48 | 0 | 48.63 | 1434.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19682812300 |  | 100306673 |  | 6716212I |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | PINE MEADOWS | 1525 PINE MEADOWS RD | 067 | LEX | 2019-02-22 | U125208 | U130193 | 2019-02-21 | 2019-02-21 | 2019-02-21 |  | LMCDONA | 2019-02-21 | 2019-02-21 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.5 | 2 | 2295.56 | 232.68 | 275.24 | 31.81 | 1755.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19682817400 |  | 100326319 |  | 6716204L |  |  |  | 566 | EX | ABANDON SERVICE | 2621P | TATES CREEK | 911 TATES CREEK RD | 067 | LEX | 2019-02-22 | U125208 | U131168 | 2019-02-21 | 2019-02-21 | 2019-02-21 |  | MCRAIG | 2019-02-21 | 2019-02-21 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10.0167 | 2 | 676.22 | 570 | 72.39 | 33.83 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 08726308600 |  | 100433340 |  | X-1103-29 |  |  |  | 566 | EX | ABANDON SL - IDLE 24 MONTHS | 2621P | WACO LOOP | 616 WACO LOOP | 151 | WAC | 2019-02-22 | DENNING | SSUTHER | 2008-04-04 | 2014-12-23 |  |  | DENNING | 2019-02-22 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.9667 | 2 | 290.64 | 228 | 11.24 | 51.4 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11894290700 |  | 100304675 |  | 16712212P | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | YORKTOWN | 1710 YORKTOWN RD | 067 | LEX | 2019-02-25 | U125208 | U906314 | 2011-03-04 | 2019-02-22 |  |  | LMCDONA | 2019-02-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.5667 | 1 | 1280.63 | 79.93 | 96.3 | 4.74 | 1099.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11894296200 |  | 100304863 |  | 1 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | CELIA | 1029 CELIA LN | 067 | LEX | 2019-02-25 | U125208 | U906314 | 2011-03-04 | 2019-02-22 |  |  | LMCDONA | 2019-02-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.0167 | 1 | 855.05 | 154.24 | 51.73 | 9.18 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11917017000 |  | 100308562 |  | 16716212N | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | ADDISON | 514 ADDISON AV | 067 | LEX | 2019-02-25 | U125208 | U124964 | 2011-07-22 | 2019-02-22 |  |  | LMCDONA | 2019-02-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.98333 | 1 | 702.09 | 50.22 | 8.98 | 2.99 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12965183400 |  | 100309061 |  | V-930-11 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | DELLA | 868 DELLA DR | 067 | LEX | 2019-02-25 | U125208 | U124967 | 2012-04-16 | 2019-02-22 |  |  | LMCDONA | 2019-02-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.0167 | 1 | 846.95 | 104.53 | 96.3 | 6.22 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 15026601101 |  |  |  | 6716216P | 1425507 | BKSLONE |  | 561 | EX | INSTALL 3854'- 12 & 4" CSHP | 2600B | NEW CIRCLE | W NEW CIRCLE RD | 067 | LEX | 2019-03-12 | U129900 | BKSLONE | 2019-02-20 | 2018-10-05 | 2019-02-28 | 2019-02-13 | JOHN SMITH | 2019-02-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3207513 |  |  | WP6011 | AMRCB |  | 100 | 751332150266011 | 997.8667 | 523152 | 2139888.06 | 57567.72 | 214823.44 | 141193.62 | 1403596.8 | 0 | 32134.37 | 290572.11 | 3633
KY | KY - WEST | 2621 | 15026601201 |  |  |  | 6716216P | 1425507 | BKSLONE |  | 562 | EX | RETIRE 3535'-12" & 4" CS/BSHP | 2600B | NEW CIRCLE | W NEW CIRCLE RD | 067 | LEX | 2019-03-07 | U131296 | BKSLONE | 2019-02-20 | 2019-02-28 | 2019-02-28 | 2019-02-16 | JOHN SMITH | 2019-02-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3207514 |  |  | WP6012 | AMRCB |  | 100 | 751432150266012 | 0.016667 | 0 | 32537.12 | 5081.72 | 4511.78 | 1183.55 | 21760.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18026746400 |  |  |  | 6716216L | 1425507 | BKSLONE |  | 561 | EX | INSTALL 115'-6" PHHP/CSHP | 2600B | NEW CIRCLE | 763 W NEW CIRCLE RD | 067 | LEX | 2019-03-05 | U131296 | BKSLONE | 2018-01-28 | 2019-02-21 | 2019-02-28 | 2019-02-05 | JOHN SMITH | 2019-02-22 | 2019-02-01 | 2019-02-01 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3207513 |  |  | WP7464 |  |  | 100 | 751332180267464 | 63.5833 | 917 | 34226.61 | 4789.67 | 7773.09 | 1490.24 | 15391.84 | 0 | 327.37 | 4454.4 | 131
KY | KY - WEST | 2621 | 18026746500 |  |  |  | 6716216L | 1425507 | BKSLONE |  | 562 | EX | RETIRE 610'-4" CSHP | 2600B | NEW CIRCLE | 763 W NEW CIRCLE RD | 067 | LEX | 2019-03-05 | U131296 | BKSLONE | 2018-01-28 | 2019-02-28 | 2019-02-28 | 2019-02-14 | JOHN SMITH | 2019-02-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3207514 |  |  | WP7465 |  |  | 100 | 751432180267465 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18026746600 |  |  |  | 6720216M | 1425507 | BKSLONE |  | 561 | EX | INSTALL 1320'-2" PMMP | 2600B | W NEW CIRCLE RD | W NEW CIRCLE RD | 067 | LEX | 2019-03-05 | U131296 | BKSLONE | 2018-01-28 | 2019-02-06 | 2019-03-01 | 2018-01-16 | JOHN SMITH | 2019-02-22 | 2018-10-25 | 2018-10-25 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3207513 |  |  | WP7466 | AMRCB |  | 100 | 751332180267466 | 242.3167 | 49665 | 140295.81 | 17395.77 | 2407.21 | 5392.36 | 96814.43 | 0 | -57.77 | 18343.81 | 1505
KY | KY - WEST | 2621 | 18026746700 |  |  |  | 6720216M | 1425507 | BKSLONE |  | 562 | EX | RETIRE 927'-2" CS & PMMP | 2600B | W NEW CIRCLE RD | W NEW CIRCLE RD | 067 | LEX | 2019-03-05 | U131296 | BKSLONE | 2018-01-28 | 2019-03-01 | 2019-03-01 | 2019-02-19 | JOHN SMITH | 2019-02-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3207514 |  |  | WP7467 | AMRCB |  | 100 | 751432180267467 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18026756300 |  | 501232767 |  | 6716216E | 1850994 | U461383 |  | 555 | EX | INSTALL 550' OF 2"PMMP MAIN | 2600B | CROCUS | 909 CROCUS CT | 067 | LEX | 2019-02-26 | U131296 | U461383 | 2018-03-05 | 2019-02-28 | 2019-06-30 | 2019-02-22 | BJACKSON | 2019-02-22 | 2019-02-19 | 2019-02-19 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP7563 |  |  | 100 | 055532180267563 | 35.75 | 2272 | 22117.37 | 2012.06 | 1410.23 | 665.06 | 15199.86 | 0 | 33.51 | 2796.65 | 568
KY | KY - WEST | 2621 | 18611598700 |  | 100293379 |  | 6720216F |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BARKSDALE | 1820 BARKSDALE DR | 067 | LEX | 2019-02-22 | DBANKS | U125208 | 2018-05-14 | 2019-02-22 | 2020-05-31 |  | DBANKS | 2019-02-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.7333 | 1 | 1791.46 | 216.03 | 127.26 | 116.67 | 1331.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18613647300 |  | 100260942 |  | 7352256G | 1747947 |  |  | 565 | EX | RPLC SL/17026728400/ | 2600B | COGAN | 3008 COGAN ST | 019 | ASH | 2019-02-22 | U461496 | U131066 | 2018-05-22 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-02-22 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.18333 | 1 | 1697.77 | 10 | 0 | 3.35 | 1684.42 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18613648400 |  | 100260792 |  | 7352256K | 1747947 |  |  | 565 | EX | RPLC SL/17026728400/ | 2600B | NORWOOD | 1008 NORWOOD AV | 019 | ASH | 2019-02-22 | U461496 | U131066 | 2018-05-22 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-02-22 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.26667 | 1 | 1674.12 | 15.54 | 0 | 5.19 | 1653.39 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18635285300 |  | 100457595 |  | 6700212E |  |  |  | 565 | EX | REPLACE SERV - LEAKAGED095542 | 2621P | CROSSFIELD | 360 CROSSFIELD DR | 239 | VER | 2019-02-25 | U125208 | U125208 | 2018-08-15 | 2019-02-22 | 2020-08-31 |  | EFGOINS | 2019-02-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.25 | 1 | 2093.72 | 296.86 | 187.93 | 17.62 | 1591.31 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18639073300 |  | 100243453 |  | 7328284A | 1749172 |  |  | 565 | EX | RPLC SL/17026740200/ | 2600B | 1ST | 493 E 1ST AV | 089 | S S | 2019-02-22 | MBLANKE | U131066 | 2018-08-29 | 2019-12-31 |  |  | MBLANKE | 2019-02-22 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.71667 | 1 | 1003.38 | 40.91 | 0 | 13.25 | 949.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18660473600 |  | 100326772 |  | 6720208I |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | PENDENNIS | 1405 PENDENNIS CR | 067 | LEX | 2019-02-22 | JENSMIN | U125208 | 2018-12-04 | 2019-02-22 | 2020-12-31 |  | JENSMIN | 2019-02-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.3167 | 1 | 2151.75 | 233.58 | 170.83 | 156.03 | 1591.31 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19026857100 |  | 501256303 |  | 7344264B | 1960562 | U122858 |  | 555 | EX | INSTALL 40'-4" PMIP | 2600B | ADAMS | 812 ADAMS AV | 089 | WUR | 2019-02-26 | U129900 | U122858 | 2019-01-20 | 2019-02-21 | 2019-02-27 | 2019-02-21 | MARCUS BLANKENSHIP | 2019-02-22 | 2019-02-18 | 2019-02-18 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP8571 |  |  | 100 | 055532190268571 | 26.1667 | 255 | 19263.47 | 1641.09 | 1767.59 | 539.64 | 12843.38 | 0 | 35.03 | 2436.74 | 51
KY | KY - WEST | 2621 | 19681617000 |  | 100459250 |  | 6720200F |  |  |  | 565 | EX | GR 2+ LK ON SERVICE D221808 | 2621P | LEAFLAND | 2132 LEAFLAND PL | 067 | LEX | 2019-02-25 | U125208 | U131169 | 2019-02-15 | 2019-02-22 | 2019-03-08 |  | DBANKS | 2019-02-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.1333 | 1 | 2697.74 | 237.93 | 168.83 | 128.5 | 2162.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11894293400 |  | 100304727 |  | 1 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | GETTYSBURG | 1737 GETTYSBURG RD | 067 | LEX | 2019-02-26 | U125208 | U906314 | 2011-03-04 | 2019-02-25 |  |  | LMCDONA | 2019-02-25 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.3333 | 1 | 873.15 | 134.88 | 90.38 | 7.99 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12975847000 |  | 100319317 |  | 6716208O | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | LOWRY | 238 E LOWRY LN | 067 | LEX | 2019-02-26 | U125208 | U123854 | 2012-06-11 | 2013-02-11 |  |  | LMCDONA | 2019-02-25 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.85 | 1 | 794.31 | 49.2 | 102.29 | 2.92 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 14193710500 |  | 100321969 |  | 6716212P | 1855043 |  |  | 566 | EX | ABN SL/PROPERTY TO BE DEMO'D | 2621P | TRANSYLVANIA | 430 TRANSYLVANIA PR | 067 | LEX | 2019-03-22 | U125208 | U125201 | 2014-01-16 | 2019-02-25 |  |  | LMCDONA | 2019-02-25 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.8167 | 2 | 1080.41 | 267.36 | 108.19 | 64.96 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18594168200 |  | 100322028 |  | 6716212P | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | TRANSYLVANIA | 425 TRANSYLVANIA PR | 067 | LEX | 2019-02-26 | U125208 | U125765 | 2018-03-13 | 2019-02-25 |  |  | LMCDONA | 2019-02-25 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.91667 | 1 | 769.99 | 52.66 | 74.31 | 3.12 | 639.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18613647600 |  | 100260795 |  | 7352256G | 1747947 |  |  | 565 | EX | RPLC SL/17026728400/ | 2600B | COGAN | 3123 COGAN ST | 019 | ASH | 2019-02-25 | U461496 | U131066 | 2018-05-22 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-02-25 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2133.75 | 0 | 0 | 0 | 2133.75 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18613648300 |  | 100260931 |  | 7352256G | 1747947 |  |  | 565 | EX | RPLC SL/17026728400/ | 2600B | MADGE | 2930 MADGE ST | 019 | ASH | 2019-02-25 | U461496 | U131066 | 2018-05-22 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-02-25 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.31667 | 1 | 2466.42 | 18.9 | 0 | 5.76 | 2441.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18636013300 |  | 100319728 |  | 6716208K | 1855043 |  |  | 566 | EX | II - ABANDON ON SOII | 2621P | DELLWOOD | 2005 DELLWOOD DR | 067 | LEX | 2019-02-26 | U125208 | U126129 | 2018-08-17 | 2018-10-30 | 2018-10-30 |  | LMCDONA | 2019-02-25 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.9167 | 1 | 777.88 | 110.56 | 20.86 | 6.56 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18636016900 |  | 100323330 |  | 6716208L | 1855043 |  |  | 566 | EX | II - ABANDON ON SOII | 2621P | BRECKENWOOD | 3053 BRECKENWOOD DR | 067 | LEX | 2019-03-05 | U125208 | U126129 | 2018-08-17 | 2019-02-25 |  |  | LMCDONA | 2019-02-25 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.28333 | 1 | 765.22 | 16.18 | 108.19 | 0.95 | 639.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18639063500 |  | 100243456 |  | 7328284B | 1749172 |  |  | 565 | EX | RPLC SL/17026740200/ | 2600B | 1ST | 527 E 1ST AV | 089 | S S | 2019-02-26 | U123965 | U131066 | 2018-08-29 | 2019-12-31 |  |  | MARCUS BLANKENSHIP | 2019-02-25 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.1 | 1 | 2038.24 | 5.89 | 0 | 1.74 | 2030.61 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19667440000 |  | 100316592 |  | 6716208F | 1855043 |  |  | 566 | EX | II -ABANDON OR CO SOII | 2621P | PENMOKEN | 126 PENMOKEN PA | 067 | LEX | 2019-02-26 | U125208 | U126129 | 2019-01-09 | 2019-02-25 |  |  | LMCDONA | 2019-02-25 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.43333 | 1 | 740.58 | 24.9 | 74.31 | 1.47 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19681864300 |  | 100296707 |  | 6716212C |  |  |  | 565 | EX | REPLACE SERV LINE | 2621P | GLEN ARVIN | 409 GLEN ARVIN AV | 067 | LEX | 2019-02-25 | TGNELSO | U129939 | 2019-02-17 | 2019-02-18 |  |  | TGNELSO | 2019-02-25 | 2019-02-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 32.4 | 9 | 2009.92 | 1897.35 | 0 | 112.57 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19683145500 |  | 100326311 |  | 6720208A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | TATES CREEK | 1011 TATES CREEK RD | 067 | LEX | 2019-02-26 | U125208 | U131168 | 2019-02-22 | 2019-02-22 | 2019-02-22 |  | KKINDER | 2019-02-25 | 2019-02-22 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 38.85 | 9 | 2708.36 | 1636.74 | 151.89 | 97.1 | 822.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19683203400 |  | 100319827 |  | 6716208K |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | ALBANY | 230 ALBANY RD | 067 | LEX | 2019-02-26 | U125208 | U130193 | 2019-02-25 | 2019-02-25 | 2020-10-31 |  | DBANKS | 2019-02-25 | 2018-12-12 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.7 | 3 | 3206.52 | 306.39 | 218.91 | 15.07 | 2666.15 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19683224500 |  | 100327840 |  | 6720212N | 1313369 |  |  | 565 | EX | REP SVC LINE FROM WATER OFF | 2621P | RICHMOND | 1220 RICHMOND RD | 067 | LEX | 2019-02-25 | JENSMIN | U125964 | 2019-02-25 | 2019-02-28 |  |  | JENSMIN | 2019-02-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.5 | 1 | 8589.35 | 267.63 | 77.88 | 252.44 | 7991.4 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19683405400 |  | 100243440 |  | 7328284B | 1749172 |  |  | 565 | EX | REPLACE W/ 17026740200 | 2600B | 2ND | 160 E 2ND AV | 089 | S S | 2019-02-26 | U123965 | U125768 | 2019-02-26 | 2049-12-31 |  |  | MARCUS BLANKENSHIP | 2019-02-25 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.78333 | 1 | 3226.37 | 46.07 | 0 | 13.7 | 3166.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 02518553300 |  | 100336569 |  | 6720212I | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | 4TH | 418 E 4TH ST 1F | 067 | LEX | 2019-03-01 | U125208 | DMCCULL | 2002-09-27 | 2019-02-26 |  |  | LMCDONA | 2019-02-26 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.53333 | 1 | 1344.94 | 30.69 | 90.38 | 9.27 | 1214.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 04586345400 |  | 100289978 |  | 600000000 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | NORTHWOOD | 309 NORTHWOOD DR | 067 | LEX | 2019-03-01 | U125208 | SSUTHER | 2004-09-10 | 2014-12-23 |  |  | LMCDONA | 2019-02-26 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.45 | 1 | 764.2 | 26.06 | 90.38 | 7.86 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 04588976300 |  | 100293538 |  | 6720216J |  |  |  | 566 | EX | ABANDON SERVICE D094275 | 2621P | KILPATRICK | 413 KILPATRICK CT | 067 | LEX | 2019-03-01 | U125208 | SSUTHER | 2004-10-07 | 2019-02-26 | 2020-06-30 |  | ATWILLI | 2019-02-26 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.65 | 1 | 826.58 | 158.74 | 18.51 | 9.43 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 05597979400 |  | 100306417 |  | 6716212M | 1855043 |  |  | 566 | EX | SOII - ABANDON / RI 1-28-2003 | 2621P | LAUREL HILL | 856 LAUREL HILL RD | 067 | LEX | 2019-03-01 | U125208 | SSUTHER | 2005-01-11 | 2049-12-31 |  |  | LMCDONA | 2019-02-26 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.53333 | 1 | 801.42 | 30.69 | 121.56 | 9.27 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11894290200 |  | 100304584 |  | 16712212P | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | YORKTOWN | 1812 YORKTOWN RD | 067 | LEX | 2019-03-01 | U125208 | U906314 | 2011-03-04 | 2014-12-23 |  |  | LMCDONA | 2019-02-26 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.33333 | 1 | 778.95 | 19.11 | 114.17 | 5.77 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11908131000 |  | 100286684 |  | 6720212B | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | BURNETT | 122 BURNETT AV | 067 | LEX | 2019-03-01 | U125208 | U906631 | 2011-05-24 | 2014-12-23 | 2018-11-10 |  | LMCDONA | 2019-02-26 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.1833 | 1 | 937.69 | 126.19 | 133.47 | 38.13 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12960217900 |  | 100286708 |  | 6720212B | 1855043 |  |  | 566 | EX | SOII - ABANDON / RI 09-16-2011 | 2621P | BURNETT | 147 BURNETT AV | 067 | LEX | 2019-03-01 | U125208 | U123724 | 2012-03-14 | 2019-02-26 |  |  | LMCDONA | 2019-02-26 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.0167 | 1 | 837.61 | 58.47 | 121.56 | 17.68 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12965296900 |  | 100336570 |  | 16720212I | 1855043 |  |  | 566 | EX | ABANDON W/ 100336569 | 2621P | 4TH | 418 E 4TH ST 2F | 067 | LEX | 2019-02-26 | LMCDONA | U124967 | 2012-04-16 | 2019-02-26 |  |  | LMCDONA | 2019-02-26 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.48333 | 2 | 40.44 | 31.83 | 0 | 8.61 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12968023000 |  | 100339099 |  | 00NEW | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | GLENN | 162 GLENN PL | 067 | LEX | 2019-03-01 | U125208 | U124967 | 2012-05-02 | 2019-02-26 |  |  | LMCDONA | 2019-02-26 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.95 | 1 | 813.8 | 54.99 | 102.29 | 16.62 | 639.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18613647700 |  | 100467125 |  | 7352256G | 1747947 |  |  | 565 | EX | RPLC SL/17026728400/ | 2600B | COGAN | 3201 COGAN ST | 019 | ASH | 2019-02-26 | U461496 | U131066 | 2018-05-22 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-02-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.21667 | 1 | 3135.4 | 13.16 | 0 | 4.01 | 3118.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18636018500 |  | 100320226 |  | 6716208K | 1748686 |  |  | 566 | EX | RETIRE S/L W/17-0267361-00 | 2600B | SHADY | 253 SHADY LN | 067 | LEX | 2019-03-04 | U125208 | U126129 | 2018-08-17 | 2019-02-26 |  |  | LMCDONA | 2019-02-26 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 0.88333 | 1 | 796.6 | 50.95 | 90.38 | 15.37 | 639.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18639063300 |  | 100243455 |  | 7328284A | 1749172 |  |  | 565 | EX | RPLC SL/17026740200/ | 2600B | 1ST | 517 E 1ST AV | 089 | S S | 2019-02-26 | U123965 | U131066 | 2018-08-29 | 2019-12-31 |  |  | MARCUS BLANKENSHIP | 2019-02-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2499.41 | 0 | 0 | 0 | 2499.41 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18642636400 |  | 100260818 |  | 7352256G | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2631D | HIGHLAND | 916 HIGHLAND AV | 019 | ASH | 2019-02-26 | U461496 | AOC SYST | 2018-09-12 | 2018-09-12 | 2021-08-27 |  | ROCKIE MULLINS | 2019-02-26 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.18333 | 1 | 1624.95 | 10.29 | 0 | 3.15 | 1611.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18655718200 |  | 100322808 |  | 6716208D | 1855043 |  |  | 566 | EX | II - ABANDON OR CO SOII | 2621P | KASTLE | 1240 KASTLE RD | 067 | LEX | 2019-03-12 | U125208 | U126926 | 2018-11-05 | 2018-10-30 | 2018-11-30 |  | LMCDONA | 2019-02-26 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.68333 | 1 | 836.49 | 39.36 | 145.35 | 11.88 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18660334000 |  | 100467251 |  | 6680224G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HIGHVIEW | 1647 HIGHVIEW CR | 073 | FRA | 2019-03-01 | U125208 | U125208 | 2018-12-03 | 2019-06-03 | 2020-12-31 |  | CDESPAI | 2019-02-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.9833 | 1 | 3319.27 | 466.73 | 161.2 | 643.09 | 2048.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673121700 |  | 100452426 |  | 6716212J |  |  |  | 566 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SPARTA | 877 SPARTA CT | 067 | LEX | 2019-02-28 | U125208 | U125208 | 2019-01-28 | 2019-02-26 | 2021-01-31 |  | ATWILLI | 2019-02-26 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 3.3167 | 1 | 850.55 | 198.87 | 0 | 11.78 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19682867600 |  | 100280401 |  | 6688228F |  |  |  | 565 | EX | MOVE METER / SHORTEN SL | 2621P | GREENHILL | 127 GREENHILL AV | 073 | FRA | 2019-02-26 | BJLONE | U125208 | 2019-02-22 | 2019-02-22 |  |  | BJLONE | 2019-02-26 | 2019-02-25 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26230031 | 23.3 | 4 | 1532.57 | 1352.39 | 99.97 | 80.21 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19683468200 |  | 100243439 |  | 7328284B | 1749172 |  |  | 565 | EX | REPLACE W/ 17026740200 | 2600B | 2ND | 176 2ND AV | 089 | S S | 2019-02-26 | U123965 | U125768 | 2019-02-26 | 2049-12-31 |  |  | MARCUS BLANKENSHIP | 2019-02-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.083333 | 1 | 2618.89 | 4.73 | 0 | 1.41 | 2612.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 01484777300 |  | 100315412 | 23 | 6716208C | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | WALLER | 225 WALLER AV | 067 | LEX | 2019-03-05 | U125208 | LABRAMS | 2001-10-09 | 2019-02-27 |  |  | LMCDONA | 2019-02-27 | 2018-10-08 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.4667 | 2 | 939.33 | 272.29 | 0 | 27.14 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11898061500 |  | 100290174 |  | V-1021-37 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | BLUE GRASS | 316 BLUE GRASS AV | 067 | LEX | 2019-03-01 | U125208 | U906631 | 2011-03-28 | 2014-12-23 |  |  | LMCDONA | 2019-02-27 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.36667 | 1 | 719.18 | 23.16 | 54.76 | 1.36 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11903612700 |  | 100315363 |  | 00NEW | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | UNIVERSITY | 224 UNIVERSITY AV | 067 | LEX | 2019-03-01 | U125208 | U124961 | 2011-04-28 | 2019-02-27 |  |  | LMCDONA | 2019-02-27 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.35 | 1 | 807.07 | 78.14 | 84.4 | 4.63 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11912612400 |  | 100331999 |  | 6720212M | 1855043 |  |  | 566 | EX | SOII - ABANDON SERV/ RI 7-2009 | 2621P | HAMBRICK | 710 HAMBRICK AV 1 | 067 | LEX | 2019-03-01 | U125208 | U124964 | 2011-06-21 | 2019-02-27 |  |  | LMCDONA | 2019-02-27 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.43333 | 1 | 699.04 | 24.9 | 32.77 | 1.47 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12968018500 |  | 100331998 |  | 6720212M | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | HAMBRICK | 710 HAMBRICK AV 2 | 067 | LEX | 2019-02-27 | LMCDONA | U124967 | 2012-05-02 | 2019-02-27 |  |  | LMCDONA | 2019-02-27 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.13333 | 1 | 7.99 | 7.54 | 0 | 0.45 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18026775701 |  | 501223420 |  | 6712228E | 1748102 | U461383 |  | 555 | EX | INSTALL 1,490' - 2"/6" PMIP | 2600B | REDDING | REDDING RD LT160 | 209 | GEO | 2019-03-19 | U129900 | U461383 | 2019-01-25 | 2018-10-25 | 2019-02-28 | 2019-02-18 | DDAVIS | 2019-02-27 | 2019-02-12 | 2019-02-12 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP7757 |  |  | 100 | 055532180267757 | 286.95 | 112200 | 174227.61 | 16769.45 | 13043.47 | 4743.52 | 115663.36 | 0 | 1243.59 | 22764.22 | 2550
KY | KY - WEST | 2623 | 18026845900 |  | 501223381 |  | 6712228I | 1748102 | U461383 |  | 555 | EX | INSTALL 110'- 4"CSHP INLET MN | 2600B | WOODLAWN | WOODLAWN AV LT203 | 209 | GEO | 2019-03-11 | U129900 | U127466 | 2018-11-15 | 2019-03-14 | 2019-04-01 | 2019-02-19 | DDAVIS | 2019-02-27 | 2019-01-22 | 2019-01-22 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP8459 |  |  | 100 | 055532180268459 | 158.4167 | 3013 | 58871.29 | 9382.36 | 14828.91 | 2985.96 | 24072.36 | 0 | 168.59 | 7433.11 | 131
KY | KY - WEST | 2621 | 18577394900 |  | 100444501 |  | 6716212G | 1746168 |  |  | 565 | EX | RPLC SL/17026714900/ | 2600B | MAXWELL | 900 W MAXWELL ST | 067 | LEX | 2019-02-27 | U461439 | U131066 | 2018-01-26 | 2019-12-31 |  |  | A PARRIS | 2019-02-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1246.27 | 0 | 0 | 0 | 1246.27 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18630583500 |  | 500017705 |  | 6688228G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MAN O WAR | 1006 MAN O WAR DR | 073 | FRA | 2019-03-01 | U125208 | U125208 | 2018-07-27 | 2019-01-25 | 2020-07-31 |  | CDESPAI | 2019-02-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.9667 | 1 | 3056.63 | 465.5 | 161.2 | 641.49 | 1788.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18636012400 |  | 100290240 |  | 6720212B | 1855043 |  |  | 566 | EX | II - ABANDON ON SOII | 2621P | HIGHLAWN | 1408 HIGHLAWN AV | 067 | LEX | 2019-03-01 | U125208 | U126129 | 2018-08-17 | 2019-02-27 |  |  | LMCDONA | 2019-02-27 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.4333 | 1 | 829.27 | 82.21 | 102.29 | 4.87 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18636013400 |  | 100328572 |  | 6720208F | 1855043 |  |  | 566 | EX | II - ABANDON ON SOII | 2621P | FONTAINE | 1943 FONTAINE RD | 067 | LEX | 2019-03-28 | U125208 | U126129 | 2018-08-17 | 2019-02-27 |  |  | LMCDONA | 2019-02-27 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.3167 | 1 | 804.62 | 75.82 | 84.4 | 4.5 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18636019300 |  | 100330374 |  | 6720212O | 1855043 |  |  | 566 | EX | II - ABANDON ON SOII | 2621P | KINGSWOOD | 408 KINGSWOOD DR | 067 | LEX | 2019-03-01 | U125208 | U126129 | 2018-08-17 | 2019-02-27 |  |  | LMCDONA | 2019-02-27 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.43333 | 1 | 998.44 | 24.9 | 102.29 | 1.47 | 869.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18641009900 |  | 100331997 |  | 6720212M | 1855043 |  |  | 566 | EX | II - ABANDON OR CO SOII | 2621P | HAMBRICK | 710 HAMBRICK AV 3 | 067 | LEX | 2019-02-27 | LMCDONA | U126129 | 2018-09-06 | 2019-02-27 |  |  | LMCDONA | 2019-02-27 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.15 | 1 | 9.21 | 8.69 | 0 | 0.52 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18644713800 |  | 100345829 |  | 6704212I | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | LEXINGTON | 3150 LEXINGTON RD | 239 | VER | 2019-03-01 | U125208 | AOC SYST | 2018-09-20 | 2019-02-26 | 2021-09-04 |  | RVANDER | 2019-02-27 | 2019-02-26 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.1667 | 2 | 218.72 | 71.78 | 142.69 | 4.25 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673116500 |  | 100460524 |  | 6712208J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | FORT HARRODS | 2053 FORT HARRODS DR | 067 | LEX | 2019-03-01 | U125208 | U125208 | 2019-01-28 | 2019-02-27 | 2021-01-31 |  | LSTANFI | 2019-02-27 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.4833 | 1 | 1652.45 | 150.1 | 161.94 | 8.91 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19683414100 |  | 100327837 |  | 6720212N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | RICHMOND | 1214 RICHMOND RD | 067 | LEX | 2019-02-27 | JENSMIN | U130193 | 2019-02-26 | 2019-02-26 | 2019-02-26 |  | JENSMIN | 2019-02-27 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 0.05 | 1 | 3271.92 | 2.96 | 229.38 | 2.8 | 3036.78 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19683425000 |  | 500330550 |  | 6712228E | 1748102 |  |  | 565 | EX | RPLC SL/18026775701 | 2600B | REDDING | 228 REDDING RD | 209 | GEO | 2019-02-27 | U461443 | U125201 | 2019-02-26 | 2019-03-29 |  |  | WGRAVES | 2019-02-27 | 2019-02-26 | 2019-02-26 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.45 | 2 | 2523.16 | 356.34 | 231.02 | 65.55 | 1870.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19683702200 |  | 500607462 |  | 6712208J | 1960885 |  |  | 565 | EX | RPLC SL/19026857500 | 2600B | ROBINHILL | 3517 ROBINHILL WY | 067 | LEX | 2019-02-27 | U461322 | U125201 | 2019-02-27 | 2019-03-29 |  |  | STEVE CANOY | 2019-02-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 0.28333 | 1 | 931.02 | 16.7 | 0 | 4.92 | 909.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19683764800 |  | 100412954 |  | 6716204I |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | FOXE BASIN | 4089 FOXE BASIN RD | 067 | LEX | 2019-03-01 | U125208 | U130193 | 2019-02-27 | 2019-02-27 | 2019-02-27 |  | MCRAIG | 2019-02-27 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.9 | 2 | 2087.86 | 963.97 | 313.52 | 57.19 | 753.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19683779800 |  | 100311439 |  | 6712204H |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | PLYMOUTH | 490 PLYMOUTH DR | 067 | LEX | 2019-03-01 | U125208 | U130193 | 2019-02-27 | 2019-02-27 | 2019-02-27 |  | LSTANFI | 2019-02-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.0333 | 1 | 1301.35 | 122.84 | 213.01 | 7.28 | 958.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19683780400 |  | 100311440 |  | 6712204H |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | PLYMOUTH | 486 PLYMOUTH DR | 067 | LEX | 2019-03-01 | U125208 | U130193 | 2019-02-27 | 2019-02-27 | 2019-02-27 |  | LSTANFI | 2019-02-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.5 | 1 | 1466.63 | 211.26 | 182.41 | 12.53 | 1060.43 | 0 | 0 | 0
KY | KY - WEST | 2621 | 06651135600 |  | 100286823 |  | 6720212B | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | DEVONIA | 124 DEVONIA AV | 067 | LEX | 2019-03-01 | U125208 | SSUTHER | 2006-06-16 | 2019-02-28 |  |  | LMCDONA | 2019-02-28 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.26667 | 1 | 1207.17 | 16.18 | 90.38 | 0.95 | 1099.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12975835600 |  | 100290160 |  | 6720212B | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | BLUE GRASS | 206 BLUE GRASS AV | 067 | LEX | 2019-03-06 | U131002 | U123854 | 2012-06-11 | 2014-12-23 |  |  | LMCDONA | 2019-02-28 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.98333 | 1 | 802.3 | 56.74 | 102.29 | 3.37 | 639.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18588356900 |  | 100360031 |  | 6740232M | 1745023 |  |  | 565 | EX | REPLACE SL W/17026708900 | 2600B | MAIN | 600 MAIN ST | 017 | PAR | 2019-03-05 | JTOY | U131066 | 2018-02-19 | 2019-03-08 |  |  | LSHARON | 2019-02-28 | 2019-02-25 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 46.1333 | 7 | 3760.17 | 2525.1 | 200.52 | 1034.55 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18614935100 |  | 100344570 |  | 6700224O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MAIN | 119 W MAIN ST | 239 | MID | 2019-02-28 | CDESPAI | U125208 | 2018-05-25 | 2018-11-21 | 2020-05-31 |  | CDESPAI | 2019-02-28 | 2019-02-25 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 18.7333 | 3 | 4511.42 | 1094.02 | 161.29 | 1507.49 | 1748.62 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18639073100 |  | 100413483 |  | 7328284A | 1749172 |  |  | 565 | EX | RPLC SL/17026740200/ | 2600B | 1ST | 479 E 1ST AV | 089 | S S | 2019-02-28 | MBLANKE | U131066 | 2018-08-29 | 2019-12-31 |  |  | MBLANKE | 2019-02-28 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.4 | 1 | 979.83 | 23.6 | 0 | 7.01 | 949.22 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18642634500 |  | 100260820 |  | 7356256G | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2631D | HIGHLAND | 908 HIGHLAND AV | 019 | ASH | 2019-02-28 | U461496 | AOC SYST | 2018-09-12 | 2018-09-12 | 2021-08-27 |  | ROCKIE MULINS | 2019-02-28 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.23333 | 1 | 1415.78 | 13.71 | 0 | 4.18 | 1397.89 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18648785000 |  | 100333642 |  | 6720212I | 1855043 |  |  | 566 | EX | II- ABANDON SL | 2621P | 3RD | 326 E 3RD ST | 067 | LEX | 2019-03-27 | U125208 | U126926 | 2018-10-05 | 2018-11-09 | 2018-11-10 |  | LMCDONA | 2019-02-28 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.25 | 1 | 1331.51 | 246.02 | 86.19 | 14.58 | 984.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026857500 |  | 500736959 |  | 6712208J | 1960885 | U461383 |  | 555 | EX | INSTALL 400' OF 2"PMMP MAIN | 2600B | ROBINHILL | 3545 ROBINHILL WY | 067 | LEX | 2019-03-05 | U129900 | U461383 | 2019-01-23 | 2019-02-14 | 2019-02-28 | 2019-02-27 | STEVE CANOY | 2019-02-28 | 2019-02-20 | 2019-02-20 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP8575 |  |  | 100 | 055532190268575 | 65 | 3267 | 21900.72 | 3843.31 | 910.49 | 1172.76 | 13170.53 | 0 | 34.56 | 2769.07 | 363
KY | KY - EAST | 2631 | 19682240900 |  | 100260819 |  | 7352256G | 1747947 |  |  | 565 | EX | REPLACE W/ 17026728400 | 2600B | HIGHLAND | 912 HIGHLAND AV | 019 | ASH | 2019-02-28 | U461496 | U125768 | 2019-02-19 | 2049-12-31 |  |  | ROCKIE MULLINS | 2019-02-28 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.21667 | 1 | 1413.57 | 12.02 | 0 | 3.66 | 1397.89 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19683287900 |  | 100286121 |  | 6764176O |  |  |  | 566 | EX | DEMO / ABANDON / RI 05-07-15 | 2621P | BROADWAY | 184 BROADWAY ST | 065 | IRV | 2019-02-28 | DENNING | U130722 | 2019-02-25 | 2019-04-05 | 2019-04-26 |  | DENNING | 2019-02-28 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.9 | 2 | 700.4 | 504.1 | 41.54 | 154.76 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19683984700 |  | 100243451 |  | 7348264A | 1749172 |  |  | 565 | EX | REPLACE W/ 17026740200 | 2600B | 1ST | 453 E 1ST AV | 089 | S S | 2019-02-28 | MBLANKE | U125768 | 2019-02-28 | 2049-12-31 |  |  | MBLANKE | 2019-02-28 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.36667 | 1 | 1892.39 | 21.28 | 0 | 6.32 | 1864.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19684022300 |  | 100312205 |  | 6716208E |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | FAIRFIELD | 508 FAIRFIELD DR | 067 | LEX | 2019-02-28 | LSTANFI | U130193 | 2019-02-28 | 2019-02-28 | 2019-02-28 |  | LSTANFI | 2019-02-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.4833 | 1 | 2835.27 | 271.14 | 297.6 | 16.08 | 2250.45 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19684088700 |  | 100243442 |  | 7328284B | 1749172 |  |  | 565 | EX | REPLACE W/ 17026740200 | 2600B | 2ND | 132 E 2ND AV | 089 | S S | 2019-02-28 | U123965 | U125768 | 2019-02-28 | 2049-12-31 |  |  | MBLANKE | 2019-02-28 | 2019-02-28 | 2019-02-28 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.15 | 1 | 1889.74 | 8.85 | 0 | 2.64 | 1878.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 05604318700 |  | 100294066 |  | 6720212E | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE/IDLE | 2621P | LIMESTONE | 647 N LIMESTONE ST | 067 | LEX | 2019-03-01 | LMCDONA | SSUTHER | 2005-03-14 | 2019-03-01 |  |  | LMCDONA | 2019-03-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.45 | 1 | 838.65 | 79.86 | 114.17 | 4.72 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 05604736500 |  | 100296091 |  | 6716216O | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | ERIE | 495 ERIE RD | 067 | LEX | 2019-03-05 | U125208 | SSUTHER | 2005-03-17 | 2019-03-01 |  |  | LMCDONA | 2019-03-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.63333 | 1 | 822.26 | 34.93 | 145.35 | 2.08 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 06667996500 |  | 100327388 | 21 | 16720212M | 1855043 |  |  | 566 | EX | ABANDON S/L W/18-0267931-00 | 2600B | OLD PARK | 187 OLD PARK AV 2FR | 067 | LEX | 2019-03-05 | U125208 | LABRAMS | 2006-12-08 | 2019-03-01 | 2019-12-31 |  | LMCDONA | 2019-03-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 0.73333 | 1 | 743.51 | 40.46 | 60.75 | 2.4 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 06667996800 |  | 100327385 | 17 | 6720212M | 1855043 |  |  | 566 | EX | ABANDON S/L W-18-0267931-00 | 2600B | OLD PARK | 185 OLD PARK AV 3 | 067 | LEX | 2019-03-01 | LMCDONA | LABRAMS | 2006-12-08 | 2019-03-01 | 2019-12-31 |  | LMCDONA | 2019-03-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 1.45 | 1 | 85.15 | 80.38 | 0 | 4.77 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 06667997400 |  | 100327386 | 13 | 6720212M | 1855043 |  |  | 566 | EX | ABANDON S/L W/18-0267931-00 | 2600B | OLD PARK | 187 OLD PARK AV 1FL | 067 | LEX | 2019-03-01 | LMCDONA | LABRAMS | 2006-12-08 | 2019-03-01 |  |  | LMCDONA | 2019-03-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.16667 | 1 | 469.19 | 8.9 | 0 | 0.53 | 459.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 06667997600 |  | 100327387 | 26 | 6 | 1855043 |  |  | 566 | EX | ABANDON S/L W/18-0267931-00 | 2600B | OLD PARK | 187 OLD PARK AV 2FL | 067 | LEX | 2019-03-01 | LMCDONA | LABRAMS | 2006-12-08 | 2019-03-01 | 2019-12-31 |  | LMCDONA | 2019-03-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.16667 | 1 | 9.43 | 8.9 | 0 | 0.53 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07698739600 |  | 100290062 | 06 | ? | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | CARLISLE | 175 CARLISLE AV | 067 | LEX | 2019-03-01 | LMCDONA | DTALBER | 2007-08-16 | 2019-03-01 |  |  | LMCDONA | 2019-03-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.6167 | 1 | 807.09 | 91.49 | 70.29 | 5.41 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18026779000 |  |  |  | 6716216P | 1425507 | BKSLONE |  | 583 | EX | R-1133 INSTALL NEW REG SETTING | 2600E | NEW CIRCLE | 763 W NEW CIRCLE RD | 067 | LEX | 2019-03-12 | U462463 | BKSLONE | 2018-06-17 | 2019-02-26 | 2019-02-28 | 2019-02-14 | CYNTHIA FARIS | 2019-03-01 | 2018-10-23 | 2018-10-23 | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00583 | 3207513 |  |  | WP7790 |  |  | 100 | 751332180267790 | 125.0167 | 336 | 65530.53 | 8773.44 | 9315.66 | 1627.74 | 35489.87 | 0 | 949.96 | 9373.86
KY | KY - WEST | 2621 | 18026779100 |  |  |  | 6716216P | 1425507 | BKSLONE |  | 584 | EX | R-1133 RETIRE EXIST REG STA | 2600E | NEW CIRCLE | 763 W NEW CIRCLE RD | 067 | LEX | 2019-03-12 | U462463 | BKSLONE | 2018-06-17 | 2019-02-28 | 2019-02-28 | 2019-02-14 | CYNTHIA FARIS | 2019-03-01 |  |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00584 | 3207514 |  |  | WP7791 |  |  | 100 | 751432180267791 | 1.5833 | 0 | 124.84 | 96.88 | 0 | 27.96 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18613922800 |  | 100325357 |  | 6720208M |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CLAIR | 3104 CLAIR RD | 067 | LEX | 2019-03-01 | LSTANFI | U125208 | 2018-05-23 | 2018-11-21 | 2020-05-31 |  | LSTANFI | 2019-03-01 | 2019-02-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.7 | 2 | 2083.94 | 271.17 | 205.37 | 16.09 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18636012200 |  | 100296627 |  | 6716212C | 1855043 |  |  | 566 | EX | II - ABANDON ON SOII | 2621P | SELF | 700 SELF ST | 067 | LEX | 2019-03-08 | U125208 | U126129 | 2018-08-17 | 2018-10-30 | 2018-10-30 |  | LMCDONA | 2019-03-01 | 2019-02-28 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.2833 | 2 | 973.38 | 300.67 | 14.97 | 17.84 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18652218500 |  | 100304020 |  | 6712208D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | TALISMAN | 2104 TALISMAN RD | 067 | LEX | 2019-03-05 | U125208 | U125208 | 2018-10-22 | 2019-04-18 | 2020-10-31 |  | LSTANFI | 2019-03-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.5667 | 1 | 1746.91 | 148.4 | 258.22 | 8.79 | 1331.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19683393100 |  | 100260796 |  | 7352256G | 1747947 |  |  | 565 | EX | REPLACE W/ 17026728400 | 2600B | COGAN | 3119 COGAN ST | 019 | ASH | 2019-03-01 | U461496 | U125768 | 2019-02-26 | 2049-12-31 |  |  | ROCKIE MULLINS | 2019-03-01 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.23333 | 1 | 1702.39 | 13.15 | 0 | 4.16 | 1685.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19683472600 |  | 100465171 |  | 6716200D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | WATERMILL | 1044 WATERMILL LN | 067 | LEX | 2019-03-01 | MCRAIG | U125208 | 2019-02-26 | 2019-03-01 | 2019-03-19 |  | MCRAIG | 2019-03-01 | 2019-03-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.7333 | 4 | 1483.8 | 1274.56 | 133.72 | 75.52 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 05630093400 |  | 100446613 |  | 6768172B | 1315787 |  |  | 566 | EX | ABANDON GAS SERVICE LINE | 2621P | 3RD | 512 3RD ST | 065 | RAV | 2019-03-04 | DENNING | U901364 | 2005-12-01 | 2014-12-23 |  |  | DENNING | 2019-03-04 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 10.95 | 3 | 679.44 | 544.27 | 0 | 135.17 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12965308400 |  | 100403783 |  | X-1206-13 |  |  |  | 566 | EX | ABANDON METER ONLY | 2621P | BROADWAY | 155 BROADWAY ST | 065 | IRV | 2019-03-04 | DENNING | U124967 | 2012-04-16 | 2014-12-31 | 2018-11-10 |  | DENNING | 2019-03-04 |  |  | D | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 13.05 | 3 | 805.76 | 645.42 | 0 | 160.34 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12975864900 |  | 100337771 |  | 6720212F | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | OHIO | 671 OHIO ST | 067 | LEX | 2019-03-05 | U125208 | U123854 | 2012-06-11 | 2019-02-18 |  |  | LSTANFI | 2019-03-04 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.3667 | 2 | 734.83 | 80.06 | 10.11 | 4.76 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18650272400 |  | 100282619 |  | 6712228B | 9402590 |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BROADWAY | 136 S BROADWAY ST | 209 | GEO | 2019-03-04 | CDESPAI | U125208 | 2018-10-11 | 2019-04-10 | 2020-10-31 |  | CDESPAI | 2019-03-04 | 2019-03-01 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 15.95 | 2 | 10392.3 | 892.21 | 290.85 | 749.56 | 8459.68 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19683768100 |  | 500169027 |  | 7332288N |  |  |  | 565 | EX | RELOCATE SERVICE- WORK 3/4/19 | 2621P | 2ND | 268 2ND ST | 089 | S S | 2019-03-05 | U125208 | U125208 | 2019-02-27 | 2019-03-04 |  |  | AMCCORM | 2019-03-04 | 2019-03-04 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 29.0667 | 3 | 2484.85 | 1708.77 | 174.19 | 601.89 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19685864800 |  | 100291287 |  | 6720216H |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | ELMWOOD | 224 ELMWOOD DR | 067 | LEX | 2019-03-04 | LSTANFI | U130193 | 2019-03-04 | 2019-03-04 | 2019-03-04 |  | LSTANFI | 2019-03-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.3 | 1 | 3052.57 | 307.21 | 303.32 | 18.2 | 2423.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 03543191700 |  | 100315907 | 14 | 16716208G | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | NICHOLASVILLE | 1713 NICHOLASVILLE RD | 067 | LEX | 2019-03-05 | LSTANFI | LABRAMS | 2003-06-18 | 2019-03-05 |  |  | LSTANFI | 2019-03-05 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.41667 | 1 | 1306.82 | 23.77 | 1.84 | 1.41 | 1279.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18615381400 |  | 100293893 |  | 6720212A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | RUSSELL CAVE | 1024 RUSSELL CAVE RD | 067 | LEX | 2019-03-05 | TNEAL | U125208 | 2018-05-29 | 2018-11-21 | 2020-05-31 |  | TNEAL | 2019-03-05 | 2019-01-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21 | 6 | 2126.34 | 1184.95 | 354.27 | 70.96 | 516.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18619471800 |  | 100293456 |  | 6720216I |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MONTROSE | 1555 MONTROSE DR | 067 | LEX | 2019-03-11 | U125208 | U125208 | 2018-06-13 | 2018-12-12 | 2020-06-30 |  | LSTANFI | 2019-03-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.3667 | 1 | 1954.13 | 194.79 | 156.49 | 11.54 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18636011900 |  | 100322555 |  | 6720208A | 1855043 |  |  | 566 | EX | II - ABANDON ON SOII | 2621P | TATES CREEK | 1116 TATES CREEK RD | 067 | LEX | 2019-03-11 | U125208 | U126129 | 2018-08-17 | 2019-03-01 |  |  | LSTANFI | 2019-03-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.2833 | 2 | 882.43 | 228.95 | 0 | 13.58 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 04569255600 |  | 100320184 | 45 | 16716208G | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | NICHOLASVILLE | 1868 NICHOLASVILLE RD | 067 | LEX | 2019-03-06 | DBANKS | PLINSCO | 2004-03-17 | 2014-12-23 |  |  | DBANKS | 2019-03-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.56667 | 1 | 672.28 | 30.56 | 0 | 1.82 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 08727872100 |  | 100297155 |  | 16716212C | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | WHITNEY | 912 WHITNEY AV | 067 | LEX | 2019-03-06 | DBANKS | RPOLLY | 2008-04-17 | 2014-12-23 |  |  | DBANKS | 2019-03-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.95 | 1 | 760.27 | 107.98 | 5.99 | 6.4 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12968588600 |  | 100336498 |  | 6720212I | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | OHIO | 367 OHIO ST 1FR | 067 | LEX | 2019-03-06 | U131002 | U124967 | 2012-05-07 | 2014-12-23 |  |  | OFFICE | 2019-03-06 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2623 | 18642630100 |  | 100283331 |  | 6712228F | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | ARAPAHO | 1002 ARAPAHO TL | 209 | GEO | 2019-03-06 | CDESPAI | AOC SYST | 2018-09-12 | 2019-03-06 | 2021-08-27 |  | CDESPAI | 2019-03-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.5833 | 1 | 1960.69 | 88.37 | 154.07 | 126.94 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18642631200 |  | 100283367 |  | 6712228F | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | SHAWNEE | 204 SHAWNEE TL | 209 | GEO | 2019-03-06 | CDESPAI | AOC SYST | 2018-09-12 | 2018-09-12 | 2021-08-27 |  | CDESPAI | 2019-03-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.2333 | 1 | 1761.56 | 68.8 | 262.45 | 98.81 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18642634600 |  | 100283329 |  | 6712228F | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | ARAPAHO | 904 ARAPAHO TL | 209 | GEO | 2019-03-06 | CDESPAI | AOC SYST | 2018-09-12 | 2019-03-06 | 2021-08-27 |  | CDESPAI | 2019-03-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.6667 | 1 | 1956.44 | 148.8 | 262.45 | 213.69 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19682981100 |  | 100277868 |  | 6688228E |  |  |  | 566 | EX | DEMO / ABNADON / RI 02-26-19 | 2621P | HILLWOOD | 813 HILLWOOD AV | 073 | FRA | 2019-03-12 | U125208 | U130722 | 2019-02-22 | 2019-04-04 | 2019-04-25 |  | RVANDER | 2019-03-06 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 15.1 | 2 | 901.39 | 850.95 | 0 | 50.44 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19683781400 |  | 100321857 |  | 6716212P |  |  |  | 566 | EX | ABANDON - WORK 03/04/19 | 2621P | COLUMBIA | 507 COLUMBIA AV | 067 | LEX | 2019-03-12 | U125208 | U125208 | 2019-02-27 | 2019-03-04 |  |  | LMCDONA | 2019-03-06 | 2019-03-04 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.5 | 6 | 873.01 | 580.55 | 0 | 34.38 | 258.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19684089000 |  | 100329281 |  | 6720208G |  |  |  | 565 | EX | REPLACE SERVICE - RLA 03/06/19 | 2621P | SAINT PHILLIP | 118 SAINT PHILLIP DR | 067 | LEX | 2019-03-06 | DBANKS | U125208 | 2019-02-28 | 2019-03-06 |  |  | DBANKS | 2019-03-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.8667 | 1 | 2245.88 | 209.9 | 274.92 | 12.44 | 1748.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19686116100 |  | 100313106 |  | 6716208A |  |  |  | 565 | EX | REPLACE SERVICE - LEAKAGE | 2621P | CLAYS MILL | 1836 CLAYS MILL RD | 067 | LEX | 2019-03-12 | U125208 | U125208 | 2019-03-05 | 2019-02-07 | 2020-08-31 |  | JENSMIN | 2019-03-06 | 2019-03-05 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 33.6833 | 7 | 7196.94 | 1901.57 | 332.54 | 1344.97 | 3617.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19686402500 |  | 100310840 |  | 000000000 |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | CORNWALL | 3508 CORNWALL DR | 067 | LEX | 2019-03-12 | U125208 | U130193 | 2019-03-06 | 2019-03-06 | 2019-03-06 |  | TNEAL | 2019-03-06 | 2019-03-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.3833 | 2 | 1008.06 | 755.34 | 207.97 | 44.75 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19686426200 |  | 100283330 |  | 6712228F |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | ARAPAHO | 1000 ARAPAHO TL | 209 | GEO | 2019-03-06 | CDESPAI | U130193 | 2019-03-06 | 2019-03-06 |  |  | CDESPAI | 2019-03-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 1.7167 | 1 | 1756.96 | 96.78 | 189.73 | 138.95 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 10872509100 |  | 100296631 |  | 00NEW | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | LINDBERG | 460 LINDBERG DR | 067 | LEX | 2019-03-07 | JENSMIN | U906609 | 2010-12-16 | 2019-03-07 |  |  | JENSMIN | 2019-03-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.1 | 1 | 651.19 | 5.69 | 0 | 5.6 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11903344100 |  | 100337843 |  | 6716216O |  |  |  | 566 | EX | RETIRE SL-BUILDING BEING DEMO | 2621P | MERCER | 1408 MERCER RD | 067 | LEX | 2019-03-07 | LMCDONA | U123933 | 2011-04-27 | 2019-03-01 | 2019-03-01 |  | LMCDONA | 2019-03-07 | 2019-03-06 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.2667 | 4 | 836.42 | 779.88 | 10.36 | 46.18 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11910291400 |  | 100295572 |  | 16716216K |  |  |  | 566 | EX | ABANDON S/L | 2600B | REDWOOD | 1071 REDWOOD DR | 067 | LEX | 2019-03-13 | U125208 | U124017 | 2011-06-07 | 2019-03-07 |  |  | DBANKS | 2019-03-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.4 | 1 | 672.51 | 21.8 | 9.52 | 1.29 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11927394800 |  | 100287288 | 12 | 6720212G | 1855043 |  |  | 566 | EX | LOCATE / ABANDON | 2621P | MEADOW | 1066 MEADOW LN | 067 | LEX | 2019-03-13 | U125208 | SCHASTE | 2011-10-01 | 2019-03-07 |  |  | JENSMIN | 2019-03-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.8167 | 1 | 998.71 | 160.07 | 41.54 | 157.2 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12968000400 |  | 100296592 |  | 00NEW | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | LINDBERG | 455 LINDBERG DR | 067 | LEX | 2019-03-22 | U125208 | U124967 | 2012-05-02 | 2019-03-07 |  |  | JENSMIN | 2019-03-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.5667 | 1 | 948.01 | 145.8 | 19.1 | 143.21 | 639.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12975869600 |  | 100343441 |  | V-1222/42 |  |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | MAYSVILLE | 38 S MAYSVILLE ST | 173 | MT | 2019-03-13 | U125208 | U123854 | 2012-06-11 | 2014-12-31 |  |  | DENNING | 2019-03-07 |  |  | D | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 7.5167 | 5 | 444.87 | 367.33 | 0 | 77.54 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 15315253500 |  | 100347108 |  | 6696212J |  |  |  | 566 | EX | ABANDON SL FOR DEMO PS MAILBOX | 2621P | M L KING JR | 250 M L KING JR BV | 239 | VER | 2019-03-22 | U125208 | U125208 | 2015-05-27 | 2015-05-29 | 2017-07-17 |  | RVANDER | 2019-03-07 | 2019-02-11 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 18.6 | 7 | 1693.77 | 826.76 | 821.88 | 45.13 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 15315253800 |  | 100347107 |  | 6696212J |  |  |  | 566 | EX | DEMO / ABANDON W/100347108 | 2621P | M L KING | 254 M L KING BV | 239 | VER | 2019-03-22 | U125208 | U125208 | 2015-05-27 | 2015-06-26 |  |  | RVANDER | 2019-03-07 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2623 | 15315286100 |  | 100347110 |  | 6696212J |  |  |  | 566 | EX | ABANDON / W/100347108 & 107 | 2621P | M L KING | 266 M L KING BV | 239 | VER | 2019-03-22 | U125208 | U125208 | 2015-05-27 | 2015-06-26 |  |  | RVANDER | 2019-03-07 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2623 | 17518490200 |  | 100441485 |  | 6700212E |  | U125208 |  | 566 | EX | ABANDON SL FOR DEMO PS MAILBOX | 2621P | CROSSFIELD | 417 CROSSFIELD DR | 239 | VER | 2019-04-11 | U125208 | U125208 | 2017-06-23 | 2017-06-28 | 2017-06-28 |  | RVANDER | 2019-03-07 | 2017-12-18 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 77.2833 | 30 | 3582.12 | 3371.82 | 0 | 210.3 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18620840400 |  | 100295558 |  | 6716216L |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | REDWOOD | 1070 REDWOOD DR | 067 | LEX | 2019-03-07 | DBANKS | U125208 | 2018-06-18 | 2019-03-07 | 2020-06-30 |  | DBANKS | 2019-03-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.75 | 1 | 2169.46 | 203.82 | 133.8 | 12.06 | 1819.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18624628900 |  | 100459806 |  | 6716208J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LOWRY | 175 W LOWRY LN 104 | 067 | LEX | 2019-03-13 | U125208 | U125208 | 2018-07-02 | 2019-03-07 | 2020-06-30 |  | DBANKS | 2019-03-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.91667 | 1 | 1540.32 | 49.58 | 156.29 | 2.95 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18638180400 |  | 500016857 |  | 6712228A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | TRINITY | 301 TRINITY DR | 209 | GEO | 2019-03-13 | U125208 | U125208 | 2018-08-27 | 2018-11-15 | 2020-05-31 |  | CDESPAI | 2019-03-07 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.9167 | 1 | 3631.5 | 218.72 | 515.84 | 314.08 | 2582.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18664331500 |  | 100323296 |  | 000000000 |  |  |  | 565 | EX | REPLACE SERV LINE | 2621P | ALBANY | 720 ALBANY RD | 067 | LEX | 2019-03-13 | U125208 | U129939 | 2018-12-28 | 2019-04-09 | 2020-10-31 |  | DBANKS | 2019-03-07 | 2018-12-28 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.3833 | 6 | 5971.93 | 1093.81 | 157.35 | 342.34 | 4378.43 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19670127700 |  | 100281350 |  | 6712228B | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | BROADWAY | 135 N BROADWAY ST | 209 | GEO | 2019-03-07 | CDESPAI | AOC SYST | 2019-01-18 | 2019-07-18 | 2020-12-31 |  | CDESPAI | 2019-03-07 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.0167 | 1 | 2593.39 | 112.44 | 316.87 | 161.45 | 2002.63 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19686618400 |  | 100260835 |  | 7352256G | 1747947 |  |  | 565 | EX | REPLACE W/ 17026728400 | 2600B | LUCILLE | 3005 LUCILLE ST | 019 | ASH | 2019-03-07 | U461496 | U125768 | 2019-03-07 | 2049-12-31 |  |  | ROCKIE MULLINS | 2019-03-07 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.2 | 1 | 922.48 | 11.5 | 0 | 3.64 | 907.34 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19026865200 |  |  |  | 7384168K | 1636946 | U461383 |  | 584 | EX | RETIRE PAPER GAUGE | 2600E | VIRGINIA AVE 1425 | VIRGINIA AVE 1425 | 195 | S W | 2019-03-12 | U462463 | U461383 | 2019-03-07 | 2019-04-01 | 2019-04-01 | 2019-03-08 | CYNTHIA FARIS | 2019-03-08 |  |  | F | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00584 | 3200584 |  |  | WP8652 |  |  | 100 | 058432190268652 | 0.53333 | 0 | 41.9 | 32.52 | 0 | 9.38 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19026865300 |  |  |  | 7364192M | 1743326 | U461383 |  | 584 | EX | RETIRE PAPER GAUGES | 2600E | SR3 INEZ OFFICE 1408 | SR3 INEZ OFFICE 1408 | 159 | INE | 2019-03-12 | U462463 | U461383 | 2019-03-07 | 2019-04-01 | 2019-04-01 | 2019-03-08 | CYNTHIA FARIS | 2019-03-08 |  |  | F | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00584 | 3200584 |  |  | WP8653 |  |  | 100 | 058432190268653 | 0.53333 | 0 | 321.3 | 295.71 | 0 | 25.59 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19686842300 |  | 100319348 |  | 6716208P |  |  |  | 565 | EX | REPLACE CSL | 2621P | LOWRY | 335 E LOWRY LN | 067 | LEX | 2019-03-13 | U125208 | U131168 | 2019-03-07 | 2019-03-07 | 2019-03-07 |  | MCRAIG | 2019-03-08 | 2019-03-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 32.35 | 4 | 2211.99 | 1890.23 | 209.78 | 111.98 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18661079500 |  | 100299124 |  | 6716212B |  |  |  | 565 | EX | NBT - SERV/MTR UPG 2" PM LP | 2621P | LEESTOWN | 1451 LEESTOWN RD | 067 | LEX | 2019-03-13 | U125208 | U125208 | 2018-12-07 | 2018-12-07 | 2019-01-01 |  | ASNICHO | 2019-03-09 | 2019-02-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 59.2833 | 11 | 11228.52 | 3365.87 | 726.78 | 199.45 | 6936.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 00418736000 |  | 100296626 | 08 | 6716212C | 1315787 |  |  | 566 | EX | ABANDON / IDLE | 2621P | SELF | 701 SELF ST | 067 | LEX | 2019-03-11 | JENSMIN | GMCALPI | 2000-01-13 | 2019-03-11 |  |  | JENSMIN | 2019-03-11 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.0333 | 1 | 1456.18 | 402.21 | 19.1 | 394.97 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07671548200 |  | 100296628 |  | 6716212G |  |  |  | 566 | EX | LOCATE/ABANDON SERVICE LINE | 2621P | SELF | 702 SELF ST | 067 | LEX | 2019-03-11 | JENSMIN | SSUTHER | 2007-01-08 | 2019-03-11 |  |  | JENSMIN | 2019-03-11 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.1 | 1 | 670.29 | 5.69 | 19.1 | 5.6 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07688873800 |  | 100296625 | 47 | ? | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | SELF | 703 SELF ST | 067 | LEX | 2019-03-11 | JENSMIN | U803233 | 2007-05-30 | 2019-03-11 |  |  | JENSMIN | 2019-03-11 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.23333 | 1 | 684.97 | 13.1 | 19.1 | 12.87 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11891034900 |  | 100291144 |  | 16720212B | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | BROADWAY | 1208 N BROADWAY ST | 067 | LEX | 2019-03-11 | DBANKS | U123933 | 2011-02-22 | 2014-12-23 | 2018-10-31 |  | DBANKS | 2019-03-11 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.7 | 1 | 699.41 | 38.15 | 19.1 | 2.26 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12965322400 |  | 100299217 |  | 6716216N | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2600B | LARCH | 264 LARCH LN | 067 | LEX | 2019-03-11 | JENSMIN | U124967 | 2012-04-16 | 2019-03-11 |  |  | JENSMIN | 2019-03-11 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.5833 | 1 | 895.32 | 90.03 | 76.99 | 88.4 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18596223500 |  | 500008324 |  | 6700212J |  |  |  | 566 | EX | ABANDON SVC LINE- IDLE ACC | 2621P | FOXHOUND | 407 FOXHOUND CT | 239 | VER | 2019-03-20 | U125208 | U125208 | 2018-03-22 | 2019-03-11 | 2020-03-31 |  | RVANDER | 2019-03-11 | 2019-03-07 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26230043 | 19.4833 | 5 | 998.97 | 943.11 | 0 | 55.86 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18619472600 |  | 100293519 |  | 6720216J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HALSTED | 1586 HALSTED CT | 067 | LEX | 2019-03-13 | U125208 | U125208 | 2018-06-13 | 2019-03-11 | 2020-06-30 |  | DBANKS | 2019-03-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.2333 | 1 | 1638.3 | 121.54 | 178.06 | 7.2 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18620844200 |  | 100295554 |  | 6716216L |  |  |  | 566 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | REDWOOD | 1094 REDWOOD DR | 067 | LEX | 2019-03-11 | DBANKS | U125208 | 2018-06-18 | 2019-03-11 | 2020-06-30 |  | DBANKS | 2019-03-11 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 2.15 | 1 | 782.6 | 116.68 | 19.1 | 6.92 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18648235100 |  | 100273492 |  | 6680224E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | VICKY | 39 VICKY WY | 073 | FRA | 2019-03-11 | CDESPAI | AOC SYST | 2018-10-03 | 2018-10-03 | 2021-09-17 |  | CDESPAI | 2019-03-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.4667 | 1 | 2932.29 | 249.49 | 276.28 | 358.27 | 2048.25 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18648235800 |  | 100273503 |  | 6680224E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | VICKY | 92 VICKY WY | 073 | FRA | 2019-03-11 | CDESPAI | AOC SYST | 2018-10-03 | 2018-10-03 | 2021-09-17 |  | CDESPAI | 2019-03-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.4167 | 1 | 2559.14 | 135.92 | 179.77 | 195.2 | 2048.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18659141900 |  | 100451280 |  | 6716204P |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | DARDA | 924 DARDA CT | 067 | LEX | 2019-03-13 | U125208 | U125208 | 2018-11-29 | 2019-03-11 | 2020-11-30 |  | DBANKS | 2019-03-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.2333 | 1 | 2109.91 | 121.05 | 161.92 | 7.16 | 1819.78 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19682241400 |  | 100260817 |  | 7352256G | 1747947 |  |  | 565 | EX | REPLACE W/ 17026728400 | 2600B | HIGHLAND | 922 HIGHLAND AV | 019 | ASH | 2019-03-11 | U461496 | U125768 | 2019-02-19 | 2049-12-31 |  |  | ROCKIE MULLINS | 2019-03-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.16667 | 1 | 1849.36 | 9.87 | 0 | 3.12 | 1836.37 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687177800 |  | 100272599 |  | 6684224A |  | U130193 |  | 566 | EX | ABANDON SVC LINE - PER DAMAGE | 2621P | THISTLEWOOD | 140 THISTLEWOOD AV | 073 | FRA | 2019-03-19 | U125208 | U130193 | 2019-03-11 | 2019-03-11 | 2019-03-11 |  | EFGOINS | 2019-03-11 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 15.2 | 3 | 816.43 | 714.21 | 59.94 | 42.28 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19687194800 |  | 100330740 |  | 6720212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SHERMAN | 344 SHERMAN AV | 067 | LEX | 2019-03-11 | LSTANFI | U130193 | 2019-03-11 | 2019-02-24 | 2019-03-14 |  | LSTANFI | 2019-03-11 | 2019-02-27 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 29.6667 | 8 | 1531.73 | 1243.08 | 178.04 | 110.61 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 02519129000 |  | 100333074 | 27 | X | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | WILSON | 317 WILSON ST | 067 | LEX | 2019-03-13 | U125208 | RSTOKLE | 2002-10-03 | 2019-03-12 |  |  | JENSMIN | 2019-03-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.98333 | 1 | 759.53 | 55.83 | 8.98 | 54.82 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 03540944300 |  | 100443193 |  | V-1021-49 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | SAUNIER | 165 SAUNIER AV | 067 | LEX | 2019-03-12 | DBANKS | DMCCULL | 2003-05-27 | 2014-12-23 |  |  | DBANKS | 2019-03-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.1333 | 1 | 1403.57 | 115.54 | 1.38 | 6.85 | 1279.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 06663531500 |  | 100355079 |  | 7260280M | 1855043 |  |  | 566 | EX | SOII - ABANDON / RI 10-21-2004 | 2621P | COMMERCE | 301 COMMERCE ST | 161 | MAY | 2019-03-12 | SDADAMS | CTAULBE | 2006-10-18 | 2019-03-12 |  |  | SDADAMS | 2019-03-12 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 2.2 | 2 | 181.18 | 121.85 | 8.98 | 50.35 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 08735953200 |  | 100286447 |  | 6768172B |  |  |  | 566 | EX | ABANDON / RI 06-10-2005 | 2621P | 4TH | 423 4TH ST | 065 | RAV | 2019-03-12 | DENNING | SSUTHER | 2008-06-20 | 2014-12-26 |  |  | DENNING | 2019-03-12 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.2 | 3 | 140.18 | 102.34 | 11.24 | 26.6 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 08754076400 |  | 100286668 | 55 | 6768172E |  |  |  | 566 | EX | ABANDON W/500613390 - RI 2008 | 2621P | 4TH | 104 4TH ST | 065 | RAV | 2019-03-13 | U125208 | KSTEEL1 | 2008-10-14 | 2014-12-26 |  |  | DENNING | 2019-03-12 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 15.05 | 3 | 882.97 | 700.86 | 0 | 182.11 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 10874369600 |  | 100298350 |  | 6716212H | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE / IDLE | 2621P | OLD GEORGETOWN | 159 OLD GEORGETOWN ST | 067 | LEX | 2019-03-12 | JENSMIN | U906609 | 2010-12-30 | 2019-03-12 |  |  | JENSMIN | 2019-03-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.8833 | 1 | 984.18 | 164.07 | 19.1 | 161.11 | 639.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 12968041300 |  | 500516514 |  | 7260280M | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | COMMERCE | 301< COMMERCE ST | 161 | MAY | 2019-03-12 | RALLISO | U124967 | 2012-05-02 | 2013-01-02 | 2018-10-31 |  | RALLISO | 2019-03-12 | 2019-03-11 |  | D | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 17.2667 | 4 | 1341.03 | 950.26 | 69.48 | 321.29 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12975841500 |  | 100300836 |  | 0 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | GARRETT | 133 GARRETT AV | 067 | LEX | 2019-03-18 | U125208 | U123854 | 2012-06-11 | 2013-02-11 | 2018-11-30 |  | DBANKS | 2019-03-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.8333 | 1 | 1209.1 | 101.38 | 2.07 | 5.99 | 1099.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12975908500 |  | 100442061 |  | V-925/31 | 1855043 |  |  | 566 | EX | SOII - ABANDON / RI 10-25-2010 | 2621P | ROOSEVELT | 385 ROOSEVELT BV | 067 | LEX | 2019-03-13 | U125208 | U123854 | 2012-06-11 | 2014-12-23 | 2018-11-10 |  | JENSMIN | 2019-03-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.1333 | 1 | 1116.34 | 235.84 | 8.98 | 231.62 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 13108766000 |  | 100282337 |  | 6712232N |  |  |  | 566 | EX | ABANDON - RI 01/04/2011 | 2621P | BROADWAY | 322 N BROADWAY ST | 209 | GEO | 2019-03-12 | CDESPAI | U908784 | 2013-01-09 | 2017-12-29 |  |  | CDESPAI | 2019-03-12 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.16667 | 1 | 1332.99 | 8.96 | 65.32 | 12.85 | 1245.86 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 14257674200 |  | 500613390 |  | 6768172E |  |  |  | 566 | EX | ABANDON SL/100286668 | 2621P | 4TH | 104< 4TH ST | 065 | RAV | 2019-03-12 | DENNING | U125201 | 2014-10-15 | 2019-03-12 |  |  | DENNING | 2019-03-12 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 6.75 | 3 | 400.84 | 318.16 | 0 | 82.68 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 14257816900 |  | 100288079 |  | 6720212C |  |  |  | 566 | EX | ABANDON / RA 10-16-14 CONVRT | 2621P | BRYAN STATION | 1698 BRYAN STATION RD | 067 | LEX | 2019-03-22 | U125208 | U128016 | 2014-10-15 | 2017-06-19 |  |  | CWEMPE | 2019-03-12 | 2018-08-16 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 54 | 19 | 3417.27 | 2516.09 | 0 | 164.24 | 736.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 17026715401 |  |  |  | 6720212P | 1744729 | U461383 |  | 909 | EX | INSTALL CONTROLLER | 2600E | FORTUNE | 2350 FORTUNE DR | 067 | LEX | 2019-03-13 | U462463 | U461383 | 2018-05-02 | 2018-12-21 | 2018-12-31 | 2018-10-16 | CYNTHIA FARIS | 2019-03-12 | 2018-05-04 | 2018-05-04 | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP7154 |  |  | 100 | 090932170267154 | 47.0333 | 0 | 138677.53 | 2879.4 | 106712.5 | 466.53 | 25869.02 | 0 | 2750.08 | 0
KY | KY - WEST | 2621 | 18026752900 |  |  |  | 6720212P | 1851114 | U128885 |  | 583 | EX | INSTALL 3 VRG PILOTS | 2600E | FORTUNE | 2350 FORTUNE DR | 067 | LEX | 2019-03-14 | U462463 | U128885 | 2018-02-26 | 2018-12-31 | 2018-12-31 | 2018-10-16 | CYNTHIA FARIS | 2019-03-12 | 2018-06-26 | 2018-06-26 | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00583 | 3200583 |  |  | WP7529 |  |  | 100 | 058332180267529 | 31.0333 | 65 | 36328.01 | 1919.73 | 28523.31 | 300 | 0 | 0 | 342.36 | 5242.61
KY | KY - WEST | 2621 | 18026753000 |  |  |  | 6720212P | 1851114 | U128885 |  | 584 | EX | RETIRE | 2600E | FORTUNE | 2350 FORTUNE DR | 067 | LEX | 2019-03-14 | U462463 | U128885 | 2018-02-26 | 2018-12-31 | 2018-12-31 | 2018-10-16 | CYNTHIA FARIS | 2019-03-12 | 2018-07-25 | 2018-07-25 | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00584 | 3200584 |  |  | WP7530 |  |  | 100 | 058432180267530 | 17.95 | 0 | 1183.17 | 998.53 | 0 | 184.64 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18026771900 |  |  |  | 6720212P | 1851114 | U461383 |  | 583 | EX | INSTALL NEW MON/CON REGULATORS | 2600E | FORTUNE | 2350 FORTUNE DR | 067 | LEX | 2019-03-18 | U462463 | U461383 | 2018-05-09 | 2018-11-26 | 2018-12-01 | 2018-10-16 | CYNTHIA FARIS | 2019-03-12 | 2018-06-13 | 2018-06-13 | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00583 | 3200583 |  |  | WP7719 |  |  | 100 | 058332180267719 | 1039.2167 | 258 | 264288.92 | 65183.57 | 72821.27 | 10217.52 | 78931.22 | 0 | 626.61 | 36508.73
KY | KY - WEST | 2621 | 18026772000 |  |  |  | 6720212P | 1851114 | U461383 |  | 584 | EX | RETIRE MONITOR/CONTROL REGS | 2600E | FORTUNE | 2350 FORTUNE DR | 067 | LEX | 2019-03-18 | U462463 | U461383 | 2018-05-09 | 2018-11-30 | 2018-12-01 | 2018-10-16 | CYNTHIA FARIS | 2019-03-12 | 2018-07-25 | 2018-07-25 | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00584 | 3200584 |  |  | WP7720 |  |  | 100 | 058432180267720 | 25.4833 | 0 | 1572.47 | 1381.01 | 0 | 191.46 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18616005300 |  | 100281580 |  | 6712232N | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | CHESTNUT | 516 CHESTNUT ST | 209 | GEO | 2019-03-20 | U125208 | AOC SYST | 2018-05-31 | 2018-05-31 | 2021-05-15 |  | CDESPAI | 2019-03-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26230032 | 1 | 1 | 2106.64 | 55.4 | 380.39 | 79.54 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18617876500 |  | 100282335 |  | 6712232N | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | BROADWAY | 326 N BROADWAY ST | 209 | GEO | 2019-03-12 | CDESPAI | AOC SYST | 2018-06-06 | 2018-06-06 | 2021-05-21 |  | CDESPAI | 2019-03-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.95 | 1 | 3949.95 | 108.57 | 380.39 | 155.87 | 3305.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18630380400 |  | 100297153 |  | 6716212C |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | WHITNEY | 922 WHITNEY AV | 067 | LEX | 2019-03-12 | DBANKS | U125208 | 2018-07-26 | 2019-03-12 | 2020-07-31 |  | DBANKS | 2019-03-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.3167 | 1 | 2009.29 | 180.42 | 143.99 | 10.68 | 1674.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18636012300 |  | 100297168 |  | 6716212C | 1855043 |  |  | 566 | EX | II - ABANDON ON SOII | 2621P | WHITNEY | 824 WHITNEY AV | 067 | LEX | 2019-03-15 | U125208 | U126129 | 2018-08-17 | 2019-03-12 |  |  | DBANKS | 2019-03-12 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.71667 | 1 | 691.04 | 38.73 | 10.11 | 2.3 | 639.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18639065800 |  | 100251779 |  | 7328284B | 1749172 |  |  | 565 | EX | RPLC SL/17026740200/ | 2600B | RIDGE | 1230 RIDGE ST | 089 | S S | 2019-03-12 | MBLANKE | U131066 | 2018-08-29 | 2019-12-31 |  |  | MBLANKE | 2019-03-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.3 | 1 | 1858.58 | 16.99 | 0 | 5.22 | 1836.37 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18645228300 |  | 100273376 |  | 6680224G | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | TULIP | 107 TULIP DR | 073 | FRA | 2019-03-12 | CDESPAI | AOC SYST | 2018-09-21 | 2018-09-21 | 2021-09-05 |  | CDESPAI | 2019-03-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.9667 | 1 | 2043.28 | 168.95 | 300.22 | 242.61 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18648238500 |  | 100273497 |  | 6680224E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | VICKY | 155 VICKY WY | 073 | FRA | 2019-03-12 | CDESPAI | AOC SYST | 2018-10-03 | 2018-10-03 | 2021-09-17 |  | CDESPAI | 2019-03-12 | 2019-03-04 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.96667 | 2 | 1960.21 | 53.16 | 239.41 | 76.33 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18653383000 |  | 100304395 |  | 6712212P |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HOLLY SPRINGS | 905 HOLLY SPRINGS DR | 067 | LEX | 2019-03-13 | U125208 | U125208 | 2018-10-25 | 2019-04-23 | 2020-10-31 |  | MCRAIG | 2019-03-12 | 2019-03-04 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 22.75 | 5 | 1513.76 | 1156.39 | 288.85 | 68.52 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673609900 |  | 100311726 |  | 6712208L | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2934 CLAYS MILL RD | 067 | LEX | 2019-03-12 | U461475 | U131066 | 2019-01-30 | 2019-11-27 |  |  | D SORRELL | 2019-03-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.7167 | 1 | 2338.76 | 317.02 | 253.82 | 99.09 | 1668.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19682606600 |  | 100329492 |  | 6720208C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER / | 2621D | SAINT WILLIAM | 150 SAINT WILLIAM DR | 067 | LEX | 2019-03-12 | MCRAIG | AOC SYST | 2019-02-20 | 2019-03-21 | 2019-04-20 |  | MCRAIG | 2019-03-12 | 2019-02-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 38.5333 | 10 | 2339.71 | 1952.36 | 271.65 | 115.7 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19685918800 |  | 100265616 |  | 7348256N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | STATE RT 5 | 6344 STATE RT 5 | 019 | ASH | 2019-03-12 | AMCCORM | U125208 | 2019-03-04 | 2019-03-07 | 2019-03-25 |  | AMCCORM | 2019-03-12 | 2019-03-11 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 13.7333 | 4 | 1452.26 | 813.02 | 157.4 | 481.84 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19686381500 |  | 100243452 |  | 7348264A | 1749172 |  |  | 565 | EX | RPLC SL/17026740200 | 2600B | 1ST | 467 E 1ST AV BOX 10 | 089 | S S | 2019-03-12 | MBLANKE | U131066 | 2019-03-06 | 2019-12-31 |  |  | MBLANKE | 2019-03-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.7 | 1 | 1930.03 | 39.58 | 0 | 12.2 | 1878.25 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19686382000 |  | 100243448 |  | 7348264A | 1749172 |  |  | 565 | EX | RPLC SL/17026740200 | 2600B | 1ST | 407 E 1ST AV | 089 | S S | 2019-03-12 | MBLANKE | U131066 | 2019-03-06 | 2019-12-31 |  |  | MBLANKE | 2019-03-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.5 | 1 | 1873.39 | 28.31 | 0 | 8.71 | 1836.37 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19686382300 |  | 100251778 |  | 7328284B | 1749172 |  |  | 565 | EX | RPLC SL/17026740200 | 2600B | 2ND | 46 W 2ND AV | 089 | S S | 2019-03-12 | MBLANKE | U131066 | 2019-03-06 | 2019-12-31 |  |  | MBLANKE | 2019-03-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.38333 | 1 | 1906.37 | 21.5 | 0 | 6.62 | 1878.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19686717200 |  | 100301171 |  | 6716212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | DELMONT | 160 DELMONT CT A | 067 | LEX | 2019-03-13 | U125208 | U131392 | 2019-03-07 | 2019-03-08 | 2019-03-28 |  | ASNICHO | 2019-03-12 | 2019-03-12 | 2019-03-12 | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.8167 | 3 | 1856.65 | 1256.8 | 525.36 | 74.49 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19687269400 |  | 100334204 |  | 6720212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LIBERTY | 1664 LIBERTY RD | 067 | LEX | 2019-03-13 | U125208 | U125208 | 2019-03-11 | 2019-03-11 | 2019-03-11 |  | TGNELSO | 2019-03-12 | 2019-03-12 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.75 | 3 | 1233.32 | 1004.36 | 169.42 | 59.54 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 11916478400 |  | 100355749 |  | 7260280N |  |  |  | 566 | EX | ABANDON/ IDLE 36MO/ RI 07-2009 | 2621P | CENTRAL | 408 CENTRAL AV | 161 | MAY | 2019-03-14 | U125208 | U124964 | 2011-07-19 | 2020-12-30 |  |  | RALLISO | 2019-03-13 | 2019-03-13 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 2.9833 | 2 | 253.68 | 165.24 | 8.98 | 79.46 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 17500352500 |  | 100282845 | 28 | 6712228C | 1638340 |  |  | 565 | EX | REPL SL/MOVE MTR - ATMOS CORR | 2621P | JACKSON | 700 E JACKSON ST | 209 | GEO | 2019-03-13 | EFGOINS | RVANDER | 2017-04-24 | 2017-12-29 |  |  | EFGOINS | 2019-03-13 | 2019-03-13 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.9 | 3 | 2085.73 | 101.23 | 229.11 | 6.77 | 1748.62 | 0 | 0 | 0
KY | KY - WEST | 2623 | 17533666500 |  | 100281786 | 22 | 6712232N | 1638340 |  |  | 565 | EX | REPL SL / MOVE MTR - CKY CORR | 2621P | GANO | 310 GANO AV | 209 | GEO | 2019-03-13 | EFGOINS | JDBRADF | 2017-08-15 | 2017-12-29 |  |  | EFGOINS | 2019-03-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.5333 | 3 | 2300.3 | 278.47 | 102.36 | 85.05 | 1834.42 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18613647500 |  | 100260798 |  | 7352256G | 1747947 |  |  | 565 | EX | RPLC SL/17026728400/ | 2600B | COGAN | 3122 COGAN ST | 019 | ASH | 2019-03-13 | U461496 | U131066 | 2018-05-22 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-03-13 | 2019-03-11 | 2019-03-11 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.45 | 2 | 1740.95 | 42.25 | 0 | 13.62 | 1685.08 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18644134400 |  | 100350681 |  | 6744204C |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | COLBY | 505 COLBY RD | 049 | WIN | 2019-03-13 | DENNING | U125208 | 2018-09-19 | 2019-03-18 | 2020-09-30 |  | DENNING | 2019-03-13 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 9.15 | 3 | 1058.49 | 426.12 | 199.07 | 110.7 | 322.6 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18645226800 |  | 100273377 |  | 6680224G | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | TULIP | 109 TULIP DR | 073 | FRA | 2019-03-13 | CDESPAI | AOC SYST | 2018-09-21 | 2018-09-21 | 2021-09-05 |  | CDESPAI | 2019-03-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 2 | 2170.12 | 349.59 | 160.22 | 328.81 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18645227400 |  | 100273404 |  | 6680224G | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | CEDAR | 106 CEDAR DR | 073 | FRA | 2019-03-13 | EFGOINS | AOC SYST | 2018-09-21 | 2018-09-21 | 2021-09-05 |  | EFGOINS | 2019-03-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.1667 | 1 | 1641.12 | 116.51 | 186.22 | 6.89 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18645227500 |  | 100273392 |  | 6680224G | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | WILLOWCREST | 204 WILLOWCREST DR | 073 | FRA | 2019-03-14 | U125208 | AOC SYST | 2018-09-21 | 2018-09-21 | 2021-09-05 |  | EFGOINS | 2019-03-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.2333 | 1 | 1624.77 | 121.9 | 164.15 | 7.22 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18645227700 |  | 100273428 |  | 6680224G | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | SPRUCE | 212 SPRUCE DR | 073 | FRA | 2019-03-13 | U125208 | AOC SYST | 2018-09-21 | 2019-03-12 | 2019-03-12 |  | RVANDER | 2019-03-13 | 2019-03-04 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 13.2667 | 5 | 981.52 | 658.95 | 188 | 134.57 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18648237300 |  | 100273453 |  | 6676224L | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | BRIDGEPORT | 725 BRIDGEPORT RD | 073 | FRA | 2019-03-13 | CDESPAI | AOC SYST | 2018-10-03 | 2018-10-03 | 2021-09-17 |  | CDESPAI | 2019-03-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.1667 | 2 | 3242.87 | 271 | 438.91 | 254.83 | 2278.13 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19026851300 |  |  |  | 6748208E | 1860094 | GSULLI1 |  | 909 | EX | UPGRADE COMM EQUIPMENT | 2600E | MAPLE | N MAPLE ST | 049 | WIN | 2019-03-13 | U462463 | GSULLI1 | 2019-01-04 | 2019-12-30 | 2019-12-31 | 2019-02-15 | CYNTHIA FARIS | 2019-03-13 | 2019-02-15 | 2019-02-15 | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00909 | 3200909 |  |  | WP8513 |  |  | 100 | 090932190268513 | 7.6667 | 0 | 5919.36 | 504.55 | 4664 | 42.72 | 680 | 0 | 28.09 | 0
KY | KY - WEST | 2623 | 19026854400 |  |  |  | 6684228C | 1860094 | GSULLI1 |  | 909 | EX | UPGRADE COMM EQUIPMENT | 2600E | WILKINSON | WILKINSON BV | 073 | FRA | 2019-03-14 | U462463 | GSULLI1 | 2019-01-04 | 2019-12-30 | 2019-12-31 | 2019-02-08 | CYNTHIA FARIS | 2019-03-13 | 2019-02-08 | 2019-02-08 | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00909 | 3200909 |  |  | WP8544 |  |  | 100 | 090932190268544 | 3.5833 | 0 | 6938.48 | 225.07 | 5088 | 65.61 | 1530 | 0 | 29.8 | 0
KY | KY - EAST | 2631 | 19686381600 |  | 100243450 |  | 7348264A | 1749172 |  |  | 565 | EX | RPLC SL/17026740200 | 2600B | 1ST | 441 E 1ST AV | 089 | S S | 2019-03-13 | MBLANKE | U131066 | 2019-03-06 | 2019-12-31 |  |  | MBLANKE | 2019-03-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.51667 | 1 | 2004.66 | 28.84 | 0 | 8.89 | 1966.93 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19686381800 |  | 100243449 |  | 7348264A | 1749172 |  |  | 565 | EX | RPLC SL/17026740200 | 2600B | 1ST | 425 E 1ST AV | 089 | S S | 2019-03-13 | MBLANKE | U131066 | 2019-03-06 | 2019-12-31 |  |  | MBLANKE | 2019-03-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.15 | 1 | 2330.23 | 8.51 | 0 | 2.61 | 2319.11 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19686382700 |  | 100251783 |  | 7328284B | 1749172 |  |  | 565 | EX | RPLC SL/17026740200 | 2600B | RIDGE | 191 RIDGE ST | 089 | S S | 2019-03-13 | MBLANKE | U131066 | 2019-03-06 | 2019-12-31 |  |  | MBLANKE | 2019-03-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.16667 | 1 | 1848.21 | 9.06 | 0 | 2.78 | 1836.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19686974200 |  | 100460690 |  | 6716204C |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LAREDO | 3441 LAREDO DR 8 | 067 | LEX | 2019-03-14 | U125208 | U125208 | 2019-03-08 | 2019-03-11 | 2019-03-29 |  | ATWILLI | 2019-03-13 | 2019-03-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13 | 3 | 789.65 | 651.77 | 99.22 | 38.66 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19687816800 |  | 100322503 |  | 6720208A |  |  |  | 565 | EX | REPLACE SVC LINE WITH MMO | 2621P | TREMONT | 819 TREMONT AV | 067 | LEX | 2019-03-14 | U125208 | U130193 | 2019-03-13 | 2019-03-13 | 2019-03-13 |  | MCRAIG | 2019-03-13 | 2019-03-13 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 29.5667 | 4 | 2180.16 | 1684.51 | 395.79 | 99.86 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 07671794100 |  | 100467694 |  | 6764176O |  |  |  | 566 | EX | ABANDON S/L | 2621P | CHESTNUT | 7 CHESTNUT ST | 065 | IRV | 2019-03-21 | U125208 | SKSMITH | 2007-01-09 | 2019-03-14 |  |  | DENNING | 2019-03-14 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.2667 | 3 | 244.94 | 189.81 | 11.24 | 43.89 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 10834541500 |  | 100300711 | 16 | 6716212I | 1855043 |  |  | 566 | EX | ABANDON / KMC - RA 04-09-2010 | 2600B | VERSAILLES | 1411 VERSAILLES RD | 067 | LEX | 2019-03-14 | DBANKS | RSTOKLE | 2010-04-09 | 2019-03-14 |  |  | DBANKS | 2019-03-14 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.25 | 1 | 1332.59 | 68.67 | 74.79 | 4.07 | 1185.06 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11915888800 |  | 100243454 |  | 7328284B |  |  |  | 566 | EX | ABDN SERV LINE/48 MONTHS | 2600B | 1ST | 1450 E 1ST AV | 089 | S S | 2019-03-14 | U123965 | U124964 | 2011-07-14 | 2020-12-31 |  |  | MARCUS BLANKENSHIP | 2019-03-14 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1
KY | KY - WEST | 2621 | 11923203000 |  | 100297337 |  | 00NEW | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | BROADWAY | 331 N BROADWAY ST | 067 | LEX | 2019-03-14 | DBANKS | U124449 | 2011-09-02 | 2014-12-23 | 2018-11-30 |  | DBANKS | 2019-03-14 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.3 | 1 | 1364.96 | 179.85 | 74.79 | 10.66 | 1099.66 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 12968030900 |  | 100355812 |  | 7260280N |  |  |  | 566 | EX | SOII - ABANDON METER ONLY | 2621P | CENTRAL | 407 CENTRAL AV 7 | 161 | MAY | 2019-03-14 | SDADAMS | U124967 | 2012-05-02 | 2013-02-11 |  |  | SDADAMS | 2019-03-14 | 2019-03-11 |  | D | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 13.6333 | 4 | 1010.87 | 748.53 | 0 | 262.34 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 12980579900 |  | 100243465 |  | 7328284B |  |  |  | 566 | EX | ABANDON/ IDLE 24MO/ RI 07-2010 | 2600B | MAIN | 15 MAIN ST | 089 | S S | 2019-03-14 | U123965 | U125208 | 2012-07-17 | 2020-12-31 |  |  | MARCUS BLANKENSHIP | 2019-03-14 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1
KY | KY - CENTRAL | 2629 | 12986729300 |  | 100439374 |  | 6760172T |  |  |  | 566 | EX | ABANDON/ RI 08-27-2010 | 2621P | HINTON BRANCH | 135 HINTON BRANCH PTER MT | 065 | IRV | 2019-03-18 | JTOY | U125208 | 2012-08-31 | 2017-12-29 |  |  | DENNING | 2019-03-14 | 2019-03-07 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 2.2667 | 4 | 151.1 | 118.62 | 0 | 32.48 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 13135571000 |  | 500624624 |  | 6764176O |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | CHESTNUT | 209 CHESTNUT ST TRL 6 | 065 | IRV | 2019-03-21 | U125208 | U123694 | 2013-05-09 | 2019-03-14 |  |  | DENNING | 2019-03-14 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.3 | 2 | 69.4 | 56.89 | 0 | 12.51 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 15335970000 |  | 100355142 | 12 | 7260280M | 1748617 |  |  | 565 | EX | REPL S/L - UNMTRD GAS | 2600B | LEXINGTON | 316 LEXINGTON ST | 161 | MAY | 2019-04-08 | U461478 | DSMARTI | 2015-08-17 | 2019-12-31 |  |  | DAVID STAGGS | 2019-03-14 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 4250.54 | 0 | 0 | 0 | 4250.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18577386800 |  | 500240075 |  | 6720208A | 1746168 |  |  | 565 | EX | RPLC SL/17026714900/ | 2600B | CROSS | 412 CROSS ST | 067 | LEX | 2019-03-14 | U461439 | U131066 | 2018-01-26 | 2019-12-31 |  |  | A PARRIS | 2019-03-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1772.57 | 0 | 356.71 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18613649000 |  | 100260783 |  | 7352256K | 1747947 |  |  | 565 | EX | RPLC SL/17026728400/ | 2600B | SHELBY | 1113 SHELBY AV | 019 | ASH | 2019-03-14 | U461496 | U131066 | 2018-05-22 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-03-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.21667 | 1 | 2608.51 | 12.6 | 0 | 3.97 | 2591.94 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18647874900 |  | 100273879 |  | 6680228H | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | MOSS | 705 MOSS LN | 073 | FRA | 2019-03-14 | CDESPAI | AOC SYST | 2018-10-02 | 2018-10-02 | 2021-09-16 |  | CDESPAI | 2019-03-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.6833 | 1 | 3409.36 | 205.84 | 287.17 | 295.59 | 2620.76 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18647878100 |  | 100273896 |  | 6680228H | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | MOSS | 829 MOSS LN | 073 | FRA | 2019-03-14 | CDESPAI | AOC SYST | 2018-10-02 | 2018-10-02 | 2021-09-16 |  | CDESPAI | 2019-03-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.5167 | 1 | 3462.91 | 196.92 | 401.92 | 282.81 | 2581.26 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19686382500 |  | 100251777 |  | 7328284B | 1749172 |  |  | 565 | EX | RPLC SL/17026740200 | 2600B | 2ND | 68 W 2ND AV | 089 | S S | 2019-03-14 | MBLANKE | U131066 | 2019-03-06 | 2019-12-31 |  |  | MBLANKE | 2019-03-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.51667 | 1 | 1915.98 | 28.84 | 0 | 8.89 | 1878.25 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19686434800 |  | 100266280 |  | 7360152J |  |  |  | 566 | EX | DEMO / ABANDON / RA 03-07-19 | 2621P | CHURCH | 149 CHURCH ST | 195 | COA | 2019-03-21 | U125208 | U132002 | 2019-03-06 | 2019-04-05 | 2019-04-07 |  | JAHOWARD | 2019-03-14 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 15.75 | 2 | 1190.11 | 886.18 | 138.95 | 164.98 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19686880300 |  | 100332066 |  | 6720212J |  |  |  | 566 | EX | DEMO / ABANDON / RI ??/??/19 | 2621P | AURORA | 706 AURORA AV | 067 | LEX | 2019-03-19 | U125208 | U125208 | 2019-03-08 | 2019-04-08 | 2019-04-08 |  | LMCDONA | 2019-03-14 | 2019-03-13 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.0167 | 4 | 769.91 | 708.54 | 19.35 | 42.02 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19686919600 |  | 100355809 |  | 7260280N |  |  |  | 566 | EX | ABANDON / 1-10 | 2621P | CENTRAL | 407 CENTRAL AV | 161 | MAY | 2019-03-21 | U125208 | U125208 | 2019-03-08 | 2019-03-14 |  |  | SDADAMS | 2019-03-14 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 0.6 | 1 | 34.6 | 32.66 | 0 | 1.94 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19686920700 |  | 100355810 |  | 7260280N |  |  |  | 566 | EX | ABANDON / 1-10 | 2621P | CENTRAL | 407 CENTRAL AV 1 | 161 | MAY | 2019-03-14 | RALLISO | U125208 | 2019-03-08 | 2019-03-29 |  |  | RALLISO | 2019-03-14 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 0.11667 | 1 | 10.73 | 6.13 | 0 | 4.6 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19686921100 |  | 100355811 |  | 7260280N |  |  |  | 566 | EX | ABANDON / 1- 10 | 2621P | CENTRAL | 407 CENTRAL AV 3 | 161 | MAY | 2019-03-14 | RALLISO | U125208 | 2019-03-08 | 2019-03-29 |  |  | RALLISO | 2019-03-14 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 0.21667 | 1 | 20.51 | 11.72 | 0 | 8.79 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19686921500 |  | 100355813 |  | 7260280N |  |  |  | 566 | EX | ABANDON / 1-10 | 2621P | CENTRAL | 407 CENTRAL AV 4 | 161 | MAY | 2019-03-14 | RALLISO | U125208 | 2019-03-08 | 2019-03-29 |  |  | RALLISO | 2019-03-14 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 1.0333 | 1 | 103.52 | 59.19 | 0 | 44.33 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19686922200 |  | 100355816 |  | 7260280N |  |  |  | 566 | EX | ABANDON / 1-10 | 2621P | CENTRAL | 407 CENTRAL AV 6 | 161 | MAY | 2019-03-14 | RALLISO | U125208 | 2019-03-08 | 2019-03-29 |  |  | RALLISO | 2019-03-14 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 0.76667 | 1 | 74.22 | 42.43 | 0 | 31.79 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19686922800 |  | 100355817 |  | 7260280N |  |  |  | 566 | EX | ABANDON / 1-10 | 2621P | CENTRAL | 407 CENTRAL AV 8 | 161 | MAY | 2019-03-14 | SDADAMS | U125208 | 2019-03-08 | 2019-03-29 |  |  | SDADAMS | 2019-03-14 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 0.33333 | 1 | 19.6 | 18.52 | 0 | 1.08 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19686923200 |  | 100355818 |  | 7260280N |  |  |  | 566 | EX | ABANDON / 1-10 | 2621P | CENTRAL | 407 CENTRAL AV 2 | 161 | MAY | 2019-03-14 | SDADAMS | U125208 | 2019-03-08 | 2019-03-29 |  |  | SDADAMS | 2019-03-14 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 0.63333 | 1 | 36.33 | 34.3 | 0 | 2.03 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19688277600 |  | 100322497 |  | 6720208A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | TREMONT | 859 TREMONT AV | 067 | LEX | 2019-03-21 | U125208 | U130193 | 2019-03-14 | 2019-03-13 | 2019-03-29 |  | ATWILLI | 2019-03-14 | 2019-03-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.6833 | 2 | 854.23 | 535.22 | 287.32 | 31.69 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19688602200 |  | 100251784 |  | 7328284A | 1749172 |  |  | 565 | EX | REPLACE W/ 17026740200 | 2600B | MAIN | 90 MAIN ST | 089 | S S | 2019-03-15 | U123965 | U125768 | 2019-03-15 | 2049-12-31 |  |  | MARCUS BLANKENSHIP | 2019-03-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.33333 | 1 | 1479.99 | 18.67 | 0 | 1.1 | 1460.22 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19690398200 |  | 100355814 |  | 7260280N |  |  |  | 566 | EX | ABANDON / 1-10 | 2621P | CENTRAL | 407 CENTRAL AV 5 | 161 | MAY | 2019-03-21 | U125208 | U125208 | 2019-03-21 | 2019-03-14 |  |  | SDADAMS | 2019-03-14 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1
KY | KY - EAST | 2633 | 11911175400 |  | 100404668 |  | 7372188N |  |  |  | 566 | EX | ABANDON/ IDLE / RI 07-10-2007 | 2621P | SR40 | SR40 | 159 | BEA | 2019-03-21 | U125208 | U124964 | 2011-06-13 | 2019-03-15 |  |  | JCKIRK | 2019-03-15 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 15.8167 | 2 | 1080.78 | 890.23 | 27.98 | 162.57 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12968022300 |  | 100337075 |  | 00NEW | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | CHESTNUT | 404 CHESTNUT ST | 067 | LEX | 2019-03-21 | U125208 | U124967 | 2012-05-02 | 2019-03-15 |  |  | JENSMIN | 2019-03-15 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.3 | 1 | 1429.58 | 359.45 | 77.2 | 353.03 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18627367400 |  | 100282917 |  | 6712228C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER / | 2623D | DUDLEY | 504 DUDLEY AV DN | 209 | GEO | 2019-03-15 | CDESPAI | AOC SYST | 2018-07-13 | 2018-08-10 | 2018-09-09 |  | CDESPAI | 2019-03-15 | 2019-03-08 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 11.6 | 2 | 6132.21 | 648.88 | 380.39 | 931.89 | 4171.05 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18649374900 |  | 100463022 |  | 6684228I | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | KIMBERLY | 108 KIMBERLY DR | 073 | FRA | 2019-03-15 | BJLONE | AOC SYST | 2018-10-08 | 2018-10-08 | 2021-09-22 |  | BJLONE | 2019-03-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 14.1667 | 2 | 3715.23 | 627.02 | 216.32 | 37.18 | 2834.71 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19668096000 |  | 100317580 |  | 6716204F | 1852188 |  |  | 565 | EX | REPLACE SL W/18026767600 | 2600B | WILSON DOWNING | 210 WILSON DOWNING RD | 067 | LEX | 2019-03-15 | U461516 | U131066 | 2019-01-11 | 2019-12-31 |  |  | NEAL JOHNSON | 2019-03-15 | 2019-03-06 | 2019-03-06 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 27.7833 | 4 | 7619.82 | 1514.09 | 25.9 | 480.47 | 5599.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19681230600 |  | 100310440 | 46 | 6716208E |  |  |  | 565 | EX | REPLACE S-SL: 25'UNMETERED GAS | 2621P | STRATFORD | 604 STRATFORD DR | 067 | LEX | 2019-03-15 | DBANKS | MAWAN | 2019-02-14 | 2019-02-18 | 2019-03-14 |  | DBANKS | 2019-03-15 | 2019-03-11 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.4333 | 2 | 4080.65 | 461.15 | 300.32 | 27.33 | 3291.85 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19683192300 |  | 100356116 |  | 7260280M | 1748617 |  |  | 565 | EX | REPLACE W/ 17026734200 | 2600B | FOREST | 600 FOREST AV | 161 | MAY | 2019-04-24 | U461478 | U125768 | 2019-02-25 | 2049-12-31 |  |  | DAVID STAGGS | 2019-03-15 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 3697.51 | 0 | 0 | 0 | 3697.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19687206600 |  | 100404439 |  | 6712204C |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MAIDSTONE | 3514 MAIDSTONE CT | 067 | LEX | 2019-03-21 | U125208 | U125208 | 2019-03-11 | 2019-03-14 | 2019-04-01 |  | MCRAIG | 2019-03-15 | 2019-03-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.6667 | 3 | 1154.14 | 787.72 | 319.76 | 46.66 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19687526500 |  | 100463091 |  | 6720200A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | IRONBRIDGE | 4650 IRONBRIDGE DR | 067 | LEX | 2019-03-21 | U125208 | U125208 | 2019-03-12 | 2019-03-15 | 2019-04-02 |  | LSTANFI | 2019-03-15 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.3167 | 3 | 1228.67 | 1129.46 | 32.29 | 66.92 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19687532500 |  | 100460628 |  | 6720200A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | IRONBRIDGE | 4654 IRONBRIDGE DR | 067 | LEX | 2019-03-21 | U125208 | U125208 | 2019-03-12 | 2019-03-15 | 2019-04-02 |  | LSTANFI | 2019-03-15 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.6167 | 3 | 161.41 | 94.14 | 61.7 | 5.57 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689022900 |  | 100251775 |  | NEW |  |  |  | 565 | EX | REPLACE SERVICE | 2621P | 2ND | 56 W 2ND AV | 089 | S S | 2019-03-21 | U125208 | U461699 | 2019-03-16 | 2019-03-15 |  |  | AMCCORM | 2019-03-17 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 12.5833 | 4 | 1171.2 | 730 | 34.75 | 406.45 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19689029900 |  | 100302169 |  | 6712212L |  |  |  | 565 | EX | GRADE 1 REPLACE | 2621P | CAMBRIDGE | 1904 CAMBRIDGE DR | 067 | LEX | 2019-03-18 | DMCCULL | U129939 | 2019-03-17 | 2019-03-17 | 2019-03-17 |  | RVANDER | 2019-03-17 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.75 | 4 | 719.35 | 592.8 | 0 | 126.55 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 01474801100 |  | 100298231 | 11 | ? | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | SHORT | 535 W SHORT ST | 067 | LEX | 2019-03-21 | U125208 | RSTOKLE | 2001-06-28 | 2014-12-23 |  |  | JENSMIN | 2019-03-18 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.3667 | 1 | 1522.28 | 191.41 | 19.1 | 187.97 | 1123.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 08727616600 |  | 100286510 |  | 6768172A |  |  |  | 566 | EX | ABD S/L-IDLE 24 MO MEMO2/08 | 2621P | 6TH | 303 6TH ST | 065 | RAV | 2019-03-18 | DENNING | RPOLLY | 2008-04-16 | 2019-04-02 |  |  | DENNING | 2019-03-18 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 11.25 | 3 | 662.22 | 525.62 | 0 | 136.6 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11886647200 |  | 100286602 |  | 6768172A |  |  |  | 566 | EX | SERVICE LINE ABANDON | 2621P | 6TH | 204 6TH ST | 065 | RAV | 2019-03-18 | DENNING | U906307 | 2011-02-08 | 2019-04-02 |  |  | DENNING | 2019-03-18 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 12.75 | 3 | 761.77 | 595.7 | 11.24 | 154.83 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11928275800 |  | 100287424 | 37 | 16720212G | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | MEADOW | 1081 MEADOW LN | 067 | LEX | 2019-03-21 | U125208 | U462080 | 2011-10-10 | 2019-03-18 |  |  | JENSMIN | 2019-03-18 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.85 | 1 | 777.41 | 48.42 | 41.54 | 47.55 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12965320400 |  | 100300801 |  | 6712212I | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | VERSAILLES | 1607 VERSAILLES RD | 067 | LEX | 2019-03-18 | JENSMIN | U124967 | 2012-04-16 | 2014-12-23 | 2018-11-30 |  | JENSMIN | 2019-03-18 | 2019-03-15 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.0167 | 2 | 1197.15 | 228.42 | 19.1 | 224.33 | 725.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12968034700 |  | 100431711 |  | 00NEW | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | SHORT | 535 W SHORT ST 2F | 067 | LEX | 2019-03-18 | JENSMIN | U124967 | 2012-05-02 | 2014-12-23 |  |  | JENSMIN | 2019-03-18 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.033333 | 1 | 3.39 | 1.71 | 0 | 1.68 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 17026695602 |  |  |  | 6716212H | 1743881 | U461383 |  | 557 | EX | INSTALL 4225' OF 2"/4"/8"PMLP | 2600B | 3RD | 455 W 3RD ST | 067 | LEX | 2019-06-18 | U123258 | U461383 | 2019-02-20 | 2018-05-03 | 2019-01-31 | 2018-10-18 | KKOUNS | 2019-03-18 | 2019-03-05 | 2018-02-26 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3207607 |  |  | WP6956 | AMRCB |  | 100 | 760732170266956 | 1306.5667 | 526845 | 1173531.41 | 86435.91 | 36118.43 | 26363.3 | 867160.92 | 0 | -1775.49 | 159228.34 | 3193
KY | KY - WEST | 2621 | 18026746900 |  |  |  | 6716216O | 1425507 | BKSLONE |  | 561 | EX | INSTALL 1700' 12" CSHP | 2600B | NEW CIRCLE | W NEW CIRCLE RD | 067 | LEX | 2019-04-10 | U123258 | BKSLONE | 2018-01-28 | 2019-01-08 | 2019-04-15 | 2019-03-15 | JOHN SMITH | 2019-03-18 | 2019-01-10 | 2019-01-10 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3207513 |  |  | WP7469 |  |  | 100 | 751332180267469 | 385.2 | 80224 | 969011.19 | 22601.76 | 135412.09 | 6626.71 | 674359.48 | 0 | 6652.87 | 123358.28 | 1744
KY | KY - WEST | 2621 | 18026747000 |  |  |  | 6716216O | 1425507 | BKSLONE |  | 562 | EX | RETIRE 1669'-12" BS/CSHP | 2600B | NEW CIRCLE | W NEW CIRCLE RD | 067 | LEX | 2019-04-09 | U123258 | BKSLONE | 2018-01-28 | 2019-04-15 | 2019-04-15 | 2019-03-15 | JOHN SMITH | 2019-03-18 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3207514 |  |  | WP7470 |  |  | 100 | 751432180267470 |  | 0 | 132.2 | 0 | 0 | 0 | 132.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18651640500 |  | 100292260 |  | 6720216K |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BROADWAY | 1987 N BROADWAY ST HOTEL | 067 | LEX | 2019-03-21 | U125208 | U125208 | 2018-10-18 | 2019-03-11 | 2020-10-31 |  | DBANKS | 2019-03-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.05 | 1 | 2338.34 | 111.73 | 131.03 | 6.63 | 2088.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18656108400 |  | 100333845 |  | 6720212J |  |  |  | 566 | EX | DEMO / ABANDON / RI 11-13-18 | 2621P | DAYTON | 918 DAYTON AV | 067 | LEX | 2019-03-18 | LMCDONA | U130722 | 2018-11-07 | 2018-12-20 | 2019-01-16 |  | LMCDONA | 2019-03-18 | 2019-03-13 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 28.1833 | 6 | 1307.64 | 1224.77 | 10.36 | 72.51 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19668096400 |  | 100317581 |  | 6716204F | 1852188 |  |  | 565 | EX | REPLACE SL W/18026767600 | 2600B | WILSON DOWNING | 214 WILSON DOWNING RD | 067 | LEX | 2019-03-18 | U461516 | U131066 | 2019-01-11 | 2019-12-31 |  |  | NEAL JOHNSON | 2019-03-18 | 2019-03-05 | 2019-03-05 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 29.5333 | 6 | 7642.82 | 1608.26 | 0 | 510.35 | 5524.21 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19686922100 |  | 100355815 |  | 7260280N |  |  |  | 566 | EX | ABANDON / 1-10 | 2621P | CENTRAL | 407 CENTRAL AV 9 | 161 | MAY | 2019-03-18 | SDADAMS | U125208 | 2019-03-08 | 2019-03-29 |  |  | SDADAMS | 2019-03-18 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 1.6667 | 2 | 140.52 | 91.47 | 0 | 49.05 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19686923600 |  | 100355819 |  | 7260280N |  |  |  | 566 | EX | ABANDON / 1-10 | 2621P | CENTRAL | 407 CENTRAL AV 10 | 161 | MAY | 2019-03-18 | RALLISO | U125208 | 2019-03-08 | 2019-03-29 |  |  | RALLISO | 2019-03-18 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 1.0667 | 2 | 89.77 | 58.43 | 0 | 31.34 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687915700 |  | 100272602 |  | 6684224A |  |  |  | 566 | EX | ABANDON W/100272599 | 2621P | THISTLEWOOD | 134 THISTLEWOOD AV | 073 | FRA | 2019-03-18 | EFGOINS | U125208 | 2019-03-13 | 2019-03-11 |  |  | EFGOINS | 2019-03-18 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 2.2667 | 3 | 195.58 | 184.64 | 0 | 10.94 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687915800 |  | 100272600 |  | 6684224A |  |  |  | 566 | EX | ABANDON W/100272599 | 2621P | THISTLEWOOD | 138 THISTLEWOOD AV | 073 | FRA | 2019-03-18 | EFGOINS | U125208 | 2019-03-13 | 2019-03-11 |  |  | EFGOINS | 2019-03-18 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0 | 1 | 1.71 | 1.62 | 0 | 0.09 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687915900 |  | 100272601 |  | 6684224A |  |  |  | 566 | EX | ABANDON W/100272599 | 2621P | THISTLEWOOD | 136 THISTLEWOOD AV | 073 | FRA | 2019-03-18 | EFGOINS | U125208 | 2019-03-13 | 2019-03-11 |  |  | EFGOINS | 2019-03-18 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0 | 1 | 34.89 | 32.94 | 0 | 1.95 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19688148400 |  | 100257598 |  | 7344264B |  |  |  | 566 | EX | ABANDON / RI 03-13-19 | 2621P | EAST | 502 EAST ST RR | 089 | WUR | 2019-03-18 | MCOLLET | U125208 | 2019-03-14 | 2019-04-12 |  |  | MCOLLET | 2019-03-18 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 6.2 | 2 | 608.11 | 367.2 | 11.24 | 229.67 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19689032200 |  | 100310660 |  | 6712208L |  |  |  | 565 | EX | GRADE 1/ REPLACE | 2621P | NAKOMI | 603 NAKOMI DR | 067 | LEX | 2019-03-21 | U125208 | U129939 | 2019-03-17 | 2019-03-17 | 2019-03-17 |  | DBANKS | 2019-03-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.4667 | 3 | 3119.13 | 405.29 | 265.99 | 24.01 | 2423.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19689074700 |  | 100329496 |  | 6720208C |  |  |  | 565 | EX | REPLACE SL | 2600B | SAINT WILLIAM | 166 SAINT WILLIAM DR | 067 | LEX | 2019-03-19 | U126309 | U131066 | 2019-03-18 | 2019-12-31 |  |  | JAMIE LYNN | 2019-03-18 | 2019-03-18 | 2019-03-18 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.1167 | 1 | 3182.17 | 213.48 | 190.69 | 70.57 | 2707.43 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19689101300 |  | 100278996 |  | 6688228F |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BUTLER | 131 BUTLER ST | 073 | FRA | 2019-03-18 | CDESPAI | U130193 | 2019-03-18 | 2019-03-16 | 2019-03-16 |  | CDESPAI | 2019-03-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26230022 | 8 | 1 | 3776.52 | 447.5 | 262.5 | 642.68 | 2423.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19689106900 |  | 100459849 |  | 6696212G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SPRING RUN | 143 SPRING RUN ST | 239 | VER | 2019-03-18 | BJLONE | U130193 | 2019-03-18 | 2019-03-15 | 2019-04-02 |  | BJLONE | 2019-03-18 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 17.0167 | 5 | 1204.45 | 1137.09 | 0 | 67.36 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 06658359800 |  | 100334049 | 10 | V-1026-6 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | SPARKS | 1102 SPARKS RD | 067 | LEX | 2019-03-21 | U125208 | SCHASTE | 2006-08-26 | 2014-12-23 |  |  | JENSMIN | 2019-03-19 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.6167 | 1 | 840.8 | 91.72 | 19.1 | 90.08 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07670932000 |  | 100334045 | 50 | V-1026-6 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | SPARKS | 1110 SPARKS RD | 067 | LEX | 2019-03-21 | U125208 | SCHASTE | 2007-01-03 | 2019-03-19 |  |  | JENSMIN | 2019-03-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.4 | 1 | 694.04 | 22.79 | 8.98 | 22.37 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11880738000 |  | 100287389 |  | V-1021-38 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | EMERSON | 414 EMERSON DR | 067 | LEX | 2019-03-19 | JENSMIN | U906307 | 2011-01-24 | 2014-12-23 | 2018-11-30 |  | JENSMIN | 2019-03-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1 | 1 | 835.24 | 58.66 | 79.04 | 57.64 | 639.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12968035700 |  | 100439212 |  | V-1222/42 |  |  |  | 566 | EX | SOII - ABANDON METER ONLY | 2621P | MAIN | 131 W MAIN ST 2F | 173 | MT | 2019-03-19 | DENNING | U124967 | 2012-05-02 | 2014-12-31 |  |  | DENNING | 2019-03-19 |  |  | D | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.1 | 3 | 480.37 | 381.27 | 0 | 99.1 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12981922300 |  | 100287509 | 10 | ? | 1855043 |  |  | 566 | EX | ABANDON/ RI 07-27-2012 | 2600B | DARLEY | 1060 DARLEY DR | 067 | LEX | 2019-03-19 | JENSMIN | OWHITT | 2012-07-27 | 2019-12-31 |  |  | JENSMIN | 2019-03-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.35 | 1 | 793.03 | 76.32 | 1.83 | 74.98 | 639.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 17026740201 |  |  |  | 7328284B | 1749172 | U128885 |  | 557 | EX | INSTALL 1900'-2"PMIP | 2600B | RIDGE | RIDGE | 089 | S S | 2019-04-11 | U123258 | U128885 | 2019-03-19 | 2019-10-17 | 2019-12-31 | 2019-03-11 | MARCUS BLANKENSHIP | 2019-03-19 | 2018-09-12 | 2018-09-12 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP7402 | AMRCB |  | 100 | 055732170267402 | 456.25 | 111660 | 127641.85 | 27641.21 | 3177.01 | 8676.11 | 70784.28 | 0 | 945.54 | 16417.7 | 1861
KY | KY - EAST | 2631 | 17026740300 |  |  |  | 7328284B | 1749172 | U128885 |  | 558 | EX | RETIRE 1887'-2"BSIP | 2600E | RIDGE | RIDGE | 089 | S S | 2019-04-11 | U123258 | U131042 | 2017-11-27 | 2019-12-31 | 2019-12-31 | 2019-03-11 | MARCUS BLANKENSHIP | 2019-03-19 | 2019-02-27 | 2019-02-27 | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP7403 | AMRCB |  | 100 | 055832170267403 | 8 | 0 | 1758.23 | 472.45 | 0 | 140.5 | 1145.28 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18026786300 |  |  |  | 7240212N | 1745093 | U461383 |  | 575 | EX | NEW EASEMENT FOR REG STATION | 2600E | PAULA | PAULA DR | 173 | MT | 2019-03-20 | U462463 | U461383 | 2018-07-26 | 2018-11-30 | 2018-12-01 | 2019-03-19 | CHRIS DAVIS | 2019-03-19 |  |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00575 | 3200575 |  |  | WP7863 |  |  | 100 | 057532180267863 |  | 1 | 17170 | 0 | 0 | 5000 | 11720.4 | 0 | 449.6 | 0
KY | KY - WEST | 2623 | 18640833500 |  | 100278641 |  | 6688232O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | HOPI | 1212 HOPI TL | 073 | FRA | 2019-03-19 | CDESPAI | AOC SYST | 2018-09-05 | 2018-09-05 | 2021-08-20 |  | CDESPAI | 2019-03-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.9667 | 1 | 5967.8 | 445.83 | 359 | 640.27 | 4522.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18644562600 |  | 100306184 |  | 6712212L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094613 | 2621P | PORT ROYAL | 1517 PORT ROYAL DR | 067 | LEX | 2019-03-21 | U125208 | U125208 | 2018-09-20 | 2019-03-19 | 2020-09-30 |  | DBANKS | 2019-03-19 | 2019-01-10 | 2019-01-10 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.3833 | 5 | 5891.91 | 409.72 | 157.97 | 97.15 | 5227.07 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19666815200 |  | 100356657 |  | 7260280M | 1748617 |  |  | 565 | EX | RPLC SL/17026734200/ | 2600B | LEXINGTON | 668 LEXINGTON ST | 161 | MAY | 2019-04-12 | U461478 | U131066 | 2019-01-07 | 2019-11-27 |  |  | DAVID STAGGS | 2019-03-19 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 3295.09 | 0 | 0 | 0 | 3295.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19667439800 |  | 100313996 |  | 6716212N | 1855043 |  |  | 566 | EX | II -ABANDON OR CO SOII | 2621P | BURLEY | 340 BURLEY AV | 067 | LEX | 2019-03-19 | JENSMIN | U126129 | 2019-01-09 | 2019-01-30 | 2019-02-09 |  | JENSMIN | 2019-03-19 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.25 | 1 | 1492.62 | 185.15 | 1.83 | 181.84 | 1123.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19668096100 |  | 100318615 |  | 6716204F | 1852188 |  |  | 565 | EX | REPLACE SL W/18026767600 | 2600B | WILSON DOWNING | 211 WILSON DOWNING RD | 067 | LEX | 2019-03-19 | U461516 | U131066 | 2019-01-11 | 2019-12-31 |  |  | NEAL JOHNSON | 2019-03-19 |  | 2019-03-19 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 7.85 | 1 | 2350.52 | 427.71 | 0 | 135.72 | 1787.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680815600 |  | 100325310 |  | 6720208M | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER / | 2621D | LAMAR | 3161 LAMAR DR | 067 | LEX | 2019-03-19 | LSTANFI | AOC SYST | 2019-02-11 | 2019-03-08 | 2019-04-09 |  | LSTANFI | 2019-03-19 | 2019-03-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.1667 | 3 | 1330.64 | 1004.91 | 266.18 | 59.55 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19681214900 |  | 100304519 |  | 6712212P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D000732 | 2621P | MAYWICK | 941 MAYWICK DR | 067 | LEX | 2019-03-21 | U125208 | U125208 | 2019-02-14 | 2019-08-13 | 2021-02-28 |  | DBANKS | 2019-03-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.15 | 1 | 1680.26 | 116.65 | 225.22 | 6.89 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19682803300 |  | 100449290 |  | 6716212N | 0357847 |  |  | 565 | EX | NBT - SERV/MTR UPGRADE | 2621P | BROADWAY | 1250 S BROADWAY ST | 067 | LEX | 2019-03-21 | U125208 | U125208 | 2019-02-21 | 2019-02-21 | 2019-03-19 |  | ASNICHO | 2019-03-19 | 2019-02-27 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 52.7 | 10 | 3363.18 | 2719.04 | 183.95 | 202.11 | 258.08 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19683986400 |  | 100260838 |  | 7352256G | 1747947 |  |  | 565 | EX | REPLACE SL W/17026728400 | 2600B | HIGHLAND | 841 HIGHLAND AV | 019 | ASH | 2019-03-19 | U461496 | U131066 | 2019-02-28 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-03-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.18333 | 1 | 1891.24 | 9.87 | 0 | 3.12 | 1878.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19687149400 |  | 100270942 |  | 6736248A |  |  |  | 565 | EX | REPLACE SERVICE LINE - D097241 | 2621P | MILEY | 111 MILEY AV | 097 | CYN | 2019-03-21 | U125208 | U125208 | 2019-03-11 | 2019-03-11 | 2019-03-29 |  | LSHARON | 2019-03-19 | 2019-03-19 | 2019-03-19 | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 24.7333 | 3 | 2148.3 | 1304.88 | 209.69 | 633.73 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19687513300 |  | 100245826 |  | 7360252M |  |  |  | 566 | EX | DEMO / ABANDON / RA 03/12/19 | 2621P | 28TH | 403 28TH ST | 019 | CAT | 2019-03-22 | U125208 | U132002 | 2019-03-12 | 2019-03-12 | 2019-04-12 |  | MCOLLET | 2019-03-19 | 2019-03-19 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 19.1667 | 3 | 1752.28 | 1127.01 | 27.98 | 597.29 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19688150000 |  | 100456241 |  | 6700212E |  |  |  | 565 | EX | REPLACE SERVICE - NO LEAK | 2621P | CROSSFIELD | 105 CROSSFIELD DR | 239 | VER | 2019-03-19 | EFGOINS | U125208 | 2019-03-14 | 2019-03-18 |  |  | EFGOINS | 2019-03-19 | 2019-03-18 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 38.1667 | 8 | 2196.53 | 1944.18 | 137.13 | 115.22 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19689397700 |  | 100329617 |  | 6720208D |  |  |  | 565 | EX | REPLACE SL | 2600B | SAINT CHRISTOP | 2072 SAINT CHRISTOP DR | 067 | LEX | 2019-03-20 | U126309 | U131066 | 2019-03-19 | 2019-12-31 |  |  | JAMIE LYNN | 2019-03-19 | 2019-03-19 | 2019-03-19 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 8 | 1 | 2207.3 | 414.5 | 87.34 | 137.05 | 1568.41 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19689425400 |  | 100311369 |  | 6712204D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HALIFAX | 604 HALIFAX DR | 067 | LEX | 2019-03-21 | U125208 | U130193 | 2019-03-19 | 2019-08-02 | 2021-02-28 |  | DBANKS | 2019-03-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.3333 | 1 | 1915.75 | 127 | 189.35 | 7.52 | 1591.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19689425900 |  | 100463675 |  | 6720204P |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | FARMVIEW | 1837 FARMVIEW DR | 067 | LEX | 2019-03-21 | U125208 | U130193 | 2019-03-19 | 2019-06-14 | 2020-12-31 |  | DBANKS | 2019-03-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.8833 | 1 | 1534.67 | 156.98 | 36.9 | 9.29 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19689503400 |  | 100287516 |  | 6720212G |  |  |  | 566 | EX | ABD SVC LINE | 2621P | DARLEY | 1059 DARLEY DR | 067 | LEX | 2019-03-22 | U125208 | U130193 | 2019-03-19 | 2019-03-19 |  |  | JENSMIN | 2019-03-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.51667 | 1 | 740.89 | 29.07 | 43.38 | 28.54 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 02504376200 |  | 100281326 | 33 | 6712232N |  |  |  | 566 | EX | ABANDON SERVICE - IDLE 2001 | 2621P | ROYAL SPRINGS | 129 ROYAL SPRINGS AV | 209 | GEO | 2019-03-20 | BJLONE | NARTRIP | 2002-04-24 | 2017-12-29 |  |  | BJLONE | 2019-03-20 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 18.7 | 4 | 1128.17 | 971.63 | 0 | 156.54 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11879641400 |  | 100338265 | 35 | 1 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | BRECKENRIDGE | 639 BRECKENRIDGE ST | 067 | LEX | 2019-03-20 | JENSMIN | MPILON | 2011-01-18 | 2017-03-31 | 2018-11-10 |  | JENSMIN | 2019-03-20 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.0833 | 1 | 805.22 | 61.52 | 43.38 | 60.42 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11918561500 |  | 100335981 |  | 00NEW | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | SHELBY | 801 SHELBY AV | 067 | LEX | 2019-03-21 | U125208 | U907469 | 2011-08-02 | 2019-03-20 |  |  | JENSMIN | 2019-03-20 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.5833 | 1 | 827.31 | 90.03 | 8.98 | 88.4 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18615016700 |  | 100272020 |  | 6684228O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | ADMIRALS LNDG | 106 ADMIRALS LNDG | 073 | FRA | 2019-03-20 | CDESPAI | AOC SYST | 2018-05-25 | 2018-05-25 | 2021-05-09 |  | CDESPAI | 2019-03-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.1 | 1 | 3749.77 | 285.26 | 285.51 | 409.71 | 2769.29 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19666815300 |  | 100356656 |  | 7260280M | 1748617 |  |  | 565 | EX | RPLC SL/17026734200/ | 2600B | LEXINGTON | 678 LEXINGTON ST | 161 | MAY | 2019-04-13 | U461478 | U131066 | 2019-01-07 | 2019-11-27 |  |  | DAVID STAGGS | 2019-03-20 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 3295.09 | 0 | 0 | 0 | 3295.09 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19666815400 |  | 100356655 |  | 7260280M | 1748617 |  |  | 565 | EX | RPLC SL/17026734200/ | 2600B | LEXINGTON | 688 LEXINGTON ST | 161 | MAY | 2019-04-24 | U461478 | U131066 | 2019-01-07 | 2019-11-27 |  |  | DAVID STAGGS | 2019-03-20 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 3237.62 | 0 | 0 | 0 | 3237.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19668096200 |  | 100318614 |  | 6716204F | 1852188 |  |  | 565 | EX | REPLACE SL W/18026767600 | 2600B | WILSON DOWNING | 213 WILSON DOWNING RD | 067 | LEX | 2019-03-20 | U461516 | U131066 | 2019-01-11 | 2019-12-31 |  |  | NEAL JOHNSON | 2019-03-20 |  | 2019-03-20 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.5333 | 1 | 2088.84 | 247.37 | 0 | 78.48 | 1762.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19668096500 |  | 100318613 |  | 6716204F | 1852188 |  |  | 565 | EX | REPLACE SL W/18026767600 | 2600B | WILSON DOWNING | 215 WILSON DOWNING RD | 067 | LEX | 2019-03-21 | U461516 | U131066 | 2019-01-11 | 2019-12-31 |  |  | NEAL JOHNSON | 2019-03-20 | 2019-03-19 | 2019-03-19 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 6.3667 | 2 | 2279.75 | 346.54 | 0 | 109.97 | 1823.24 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19683986600 |  | 100260840 |  | 7352256G | 1747947 |  |  | 565 | EX | REPLACE SL W/17026728400 | 2600B | HIGHLAND | 915 HIGHLAND AV | 019 | ASH | 2019-03-20 | U461496 | U131066 | 2019-02-28 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-03-20 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.18333 | 1 | 2104.86 | 9.87 | 0 | 3.12 | 2091.87 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19683986700 |  | 100260841 |  | 7352256G | 1747947 |  |  | 565 | EX | REPLACE SL W/17026728400 | 2600B | HIGHLAND | 919 HIGHLAND AV | 019 | ASH | 2019-03-20 | U461496 | U131066 | 2019-02-28 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-03-20 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.033333 | 1 | 1401.48 | 2.73 | 0 | 0.86 | 1397.89 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19686662300 |  | 100418042 |  | 7348248D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | THOMPSON | 2109 E THOMPSON RD | 019 | CAN | 2019-03-20 | MCOLLET | U131392 | 2019-03-07 | 2019-03-08 | 2019-03-28 |  | MCOLLET | 2019-03-20 | 2019-03-18 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 17.5667 | 4 | 1875.24 | 1032.18 | 197.57 | 645.49 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689558500 |  | 100260843 |  | 7352256G | 1747947 |  |  | 565 | EX | REPLACE SL W/17026728400 | 2600B | EDGEWOOD | 922 EDGEWOOD AV | 019 | ASH | 2019-03-20 | U461496 | U131066 | 2019-03-19 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-03-20 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.31667 | 1 | 2506.33 | 17.02 | 0 | 5.37 | 2483.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19689858500 |  | 100465220 |  | 6712204K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D027091 | 2600B | LANSFORD | 808 LANSFORD CT | 067 | LEX | 2019-03-25 | U128381 | U124449 | 2019-03-20 | 2019-06-20 | 2020-12-31 |  | DBANKS | 2019-03-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.0167 | 3 | 2145.73 | 169.45 | 161.93 | 25.91 | 1788.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19689911400 |  | 100288492 |  | 6720212D |  |  |  | 565 | EX | GRADE 1 LK ON SVC LINE | 2621P | ROOKWOOD | 480 ROOKWOOD PY | 067 | LEX | 2019-03-20 | RVANDER | U130193 | 2019-03-20 | 2019-03-20 | 2019-03-20 |  | RVANDER | 2019-03-20 | 2019-03-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 28.9833 | 4 | 1843 | 1468.6 | 171.91 | 202.49 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19689916100 |  | 100464273 |  | 6720208J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | NORBORNE | 2063 NORBORNE DR | 067 | LEX | 2019-03-21 | U125208 | U130193 | 2019-03-20 | 2019-03-20 | 2020-12-31 |  | DBANKS | 2019-03-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26210022 | 2.75 | 1 | 1847.27 | 149.38 | 129.08 | 8.84 | 1559.97 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19689927000 |  | 100301499 |  | 6712212H |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | RUGBY | 156 RUGBY RD | 067 | LEX | 2019-03-20 | JENSMIN | U130193 | 2019-03-20 | 2019-03-20 |  |  | JENSMIN | 2019-03-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.3833 | 1 | 1180.56 | 79.75 | 224.9 | 78.31 | 797.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12990742100 |  | 100347387 | 54 | 6744208L | 1635077 |  |  | 566 | EX | AOC POSS THEFT OF GAS -D095198 | 2629D | DENNY | 23 DENNY AV | 049 | WIN | 2019-03-22 | U125208 | SWCANOY | 2012-09-27 | 2019-03-20 | 2019-03-20 |  | JOCHOA | 2019-03-21 | 2019-03-20 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 26.6167 | 8 | 1524.21 | 1286.36 | 0 | 237.85 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18026794800 |  | 501249724 |  | 6736232N | 1855498 | U461383 |  | 555 | EX | INSTALL 2200' OF 4"PMMP MAIN | 2600B | JIM HUNT | 316 JIM HUNT WY | 017 | PAR | 2019-03-28 | U129900 | U127466 | 2018-09-13 | 2019-03-28 | 2019-04-15 | 2019-03-20 | WGRAVES | 2019-03-21 | 2019-03-05 | 2019-03-05 | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP7948 |  |  | 100 | 055532180267948 | 107 | 31057 | 68775.48 | 5652.64 | 9440.98 | 1839.46 | 42765.73 | 0 | 230.24 | 8846.43 | 2389
KY | KY - WEST | 2623 | 18615016600 |  | 100271997 |  | 6684228K | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | GOEBEL | 301 GOEBEL CT | 073 | FRA | 2019-03-21 | CDESPAI | AOC SYST | 2018-05-25 | 2018-11-21 | 2021-05-09 |  | CDESPAI | 2019-03-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.6167 | 1 | 2447.06 | 90.04 | 290.24 | 129.32 | 1937.46 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18615016900 |  | 100271991 |  | 6684228K | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | 4TH | 310 E 4TH ST | 073 | FRA | 2019-03-21 | CDESPAI | AOC SYST | 2018-05-25 | 2018-11-21 | 2019-12-31 |  | CDESPAI | 2019-03-21 | 2019-03-06 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.55 | 2 | 3160.96 | 423.49 | 191.87 | 608.14 | 1937.46 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18624737100 |  | 100281864 |  | 6712232O | 1635077 |  |  | 566 | EX | AOC ATMOS CORR REMEDIATE | 2623D | BOURBON | 100 BOURBON CT | 209 | GEO | 2019-03-27 | U125208 | AOC SYST | 2018-07-02 | 2018-07-02 | 2021-06-16 |  | CDESPAI | 2019-03-21 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 | KYACA |  | 100 | 056632B26230057 | 2.55 | 2 | 1030.32 | 143.21 | 41.54 | 205.67 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18652217400 |  | 100329418 |  | 6720208G |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094105 | 2621P | SAINT JAMES | 154 SAINT JAMES DR | 067 | LEX | 2019-03-22 | U125208 | U125208 | 2018-10-22 | 2019-04-18 | 2020-10-31 |  | DBANKS | 2019-03-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.2833 | 1 | 2159.56 | 287.76 | 209.11 | 17.05 | 1645.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026865400 |  |  |  | 6712208K | 1962073 | U131983 |  | 557 | EX | INSTALL 4'-3" PMMP | 2621P | COMANCHE | COMANCHE TL | 067 | LEX | 2019-04-26 | U123258 | U131983 | 2019-03-08 | 2019-03-19 | 2019-03-22 | 2019-03-21 | KKINDER | 2019-03-21 | 2019-03-20 | 2019-03-20 | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP8654 |  |  | 100 | 055732190268654 | 65.5667 | 40 | 5670.75 | 3715.65 | 631.13 | 339.33 | 258.08 | 0 | 9.65 | 716.91 | 4
KY | KY - WEST | 2621 | 19026865500 |  |  |  | 6712208K | 1962073 | U131983 |  | 558 | EX | RETIRE 4'-3" PMMP | 2621P | COMANCHE | COMANCHE TL | 067 | LEX | 2019-04-26 | U123258 | U131983 | 2019-03-08 | 2019-03-19 | 2019-03-22 | 2019-03-21 | KKINDER | 2019-03-21 | 2019-03-20 | 2019-03-20 | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP8655 |  |  | 100 | 055832190268655 | 36.1833 | 0 | 3224.08 | 1777.59 | 0 | 105.34 | 1341.15 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19666814900 |  | 100356661 |  | 7260280M | 1748617 |  |  | 565 | EX | RPLC SL/17026734200/ | 2600B | LEXINGTON | 648 LEXINGTON ST | 161 | MAY | 2019-04-13 | U461478 | U131066 | 2019-01-07 | 2019-11-27 |  |  | DAVID STAGGS | 2019-03-21 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 3295.09 | 0 | 0 | 0 | 3295.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19668095800 |  | 100318616 |  | 6716204F | 1852188 |  |  | 565 | EX | REPLACE SL W/18026767600 | 2600B | WILSON DOWNING | 209 WILSON DOWNING RD | 067 | LEX | 2019-03-21 | U461516 | U131066 | 2019-01-11 | 2019-12-31 |  |  | NEAL JOHNSON | 2019-03-21 |  | 2019-03-21 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 4.5833 | 1 | 2109.59 | 250.06 | 0 | 79.34 | 1780.19 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19688584400 |  | 100281865 |  | 6712232O |  |  |  | 566 | EX | ABANDON W/100281864* | 2621P | BOURBON | 333 BOURBON ST | 209 | GEO | 2019-03-21 | CDESPAI | U125208 | 2019-03-15 | 2019-03-07 |  |  | CDESPAI | 2019-03-21 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.066667 | 1 | 8.15 | 3.34 | 0 | 4.81 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689057600 |  | 100256259 | 20 | 7356256G |  |  |  | 566 | EX | ABANDON CO.SERVICE LINE-DEMO | 2621P | MILL | 2801 MILL ST | 019 | ASH | 2019-03-21 | MCOLLET | SJUDE | 2019-03-18 | 2019-03-21 |  |  | MCOLLET | 2019-03-21 | 2019-03-21 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 6.9833 | 2 | 656.24 | 409.49 | 69.52 | 177.23 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19689975900 |  | 100338266 |  | 6720212J |  |  |  | 566 | EX | ABD SVC LINE | 2621P | BRECKENRIDGE | 637 BRECKENRIDGE ST | 067 | LEX | 2019-03-21 | JENSMIN | U130193 | 2019-03-20 | 2019-03-20 |  |  | JENSMIN | 2019-03-21 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.6 | 1 | 1772.85 | 91.13 | 43.38 | 89.5 | 1548.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 03555653300 |  | 100337674 | 58 | X00000000 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | M L KING | 664 M L KING BV | 067 | LEX | 2019-03-22 | LSTANFI | MPILON | 2003-10-30 | 2019-03-22 |  |  | LSTANFI | 2019-03-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.3167 | 1 | 888.45 | 135.06 | 105.48 | 8.01 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 04573183700 |  | 100337194 |  | 6720212E | 1855043 |  |  | 566 | EX | ABANDON / ALL ELEC / 05-14-01 | 2621P | RAND | 127 RAND AV | 067 | LEX | 2019-03-22 | LSTANFI | SSUTHER | 2004-04-27 | 2019-03-22 |  |  | LSTANFI | 2019-03-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.45 | 1 | 1454.36 | 257.94 | 81.48 | 15.28 | 1099.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 10868488000 |  | 100296053 |  | V-925-24 |  |  |  | 566 | EX | ABANDON SL - | 2600B | GEORGETOWN | 901 GEORGETOWN ST | 067 | LEX | 2019-03-22 | JENSMIN | U123166 | 2010-11-15 | 2019-03-21 |  |  | JENSMIN | 2019-03-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10.1167 | 2 | 643.23 | 576.47 | 0 | 66.76 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11908251800 |  | 100343812 |  | 7240204B |  |  |  | 566 | EX | ABANDON/ IDLE 24MO/ RA 05-2010 | 2600B | LEVEE | 4660 LEVEE RD | 173 | MT | 2019-03-26 | U125208 | U906631 | 2011-05-25 | 2019-05-17 |  |  | DENNING | 2019-03-22 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.5167 | 3 | 227.17 | 202.37 | 0 | 24.8 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18026755802 |  |  |  | 6720212B | 1851269 | U122858 |  | 557 | EX | INSTALL 70'-6" PMLP | 2600B | BROADWAY | 1204 N BROADWAY ST APT | 067 | LEX | 2019-04-09 | U123258 | U122858 | 2019-03-21 | 2019-03-21 | 2019-04-30 | 2019-03-20 | JOHN SMITH | 2019-03-22 | 2019-03-20 | 2019-03-20 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP7558 |  |  | 100 | 055732180267558 | 250.15 | 3379 | 150272.74 | 14972.18 | 7762.76 | 4689.36 | 101210.06 | 0 | 1734.61 | 19903.77 | 109
KY | KY - WEST | 2621 | 18026755900 |  |  |  | 6720212B | 1851269 | U131369 |  | 558 | EX | RETIRE 90'-8" CSLP | 2600B | BROADWAY | 1204 N BROADWAY ST APT | 067 | LEX | 2019-04-09 | U123258 | U131369 | 2018-03-05 | 2019-03-29 | 2019-04-30 | 2019-03-20 | JOHN SMITH | 2019-03-22 | 2019-03-20 | 2019-03-20 | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP7559 |  |  | 100 | 055832180267559 | 10.25 | 0 | 881.16 | 570.98 | 0 | 177.98 | 132.2 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18628970100 |  | 100279366 |  | 6688228K | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | COUNTRY | 122 COUNTRY LN | 073 | FRA | 2019-03-22 | CDESPAI | AOC SYST | 2018-07-19 | 2018-07-19 | 2021-07-03 |  | CDESPAI | 2019-03-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.3167 | 1 | 2753.03 | 185.16 | 250.88 | 265.92 | 2051.07 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18650649600 |  | 100273971 |  | 6684228M | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | BROWNS FERRY | 863 BROWNS FERRY RD | 073 | FRA | 2019-03-22 | CDESPAI | AOC SYST | 2018-10-12 | 2018-10-12 | 2021-09-26 |  | CDESPAI | 2019-03-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.65 | 1 | 3156.97 | 360.34 | 229.57 | 515.99 | 2051.07 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19026861200 |  | 501255722 |  | 7352260F |  | U122858 |  | 555 | EX | INSTALL 80'-2" PMMP | 2600E | RUSSELL PLAZA | 35 RUSSELL PLAZA DR | 089 | ASH | 2019-04-09 | U129900 | U122858 | 2019-02-08 | 2019-05-10 | 2019-05-13 | 2019-03-15 | MCOLLET | 2019-03-22 | 2019-03-15 | 2019-03-15 | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP8612 |  |  | 100 | 055532190268612 | 29.6 | 138 | 4460.3 | 1738.44 | 184.59 | 1002.5 | 960.76 | 0 | 7.52 | 566.49 | 23
KY | KY - CENTRAL | 2632 | 19666814500 |  | 100356118 |  | 7260280M | 1748617 |  |  | 565 | EX | RPLC SL/17026734200/ | 2600B | LEXINGTON | 451 LEXINGTON ST | 161 | MAY | 2019-04-24 | U461478 | U131066 | 2019-01-07 | 2019-11-27 |  |  | DAVID STAGGS | 2019-03-22 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2896.78 | 0 | 0 | 0 | 2896.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19679175300 |  | 100310161 |  | 6716208A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SPRINGRIDGE | 678 SPRINGRIDGE DR | 067 | LEX | 2019-03-28 | U125208 | U125208 | 2019-02-04 | 2019-08-01 | 2021-02-28 |  | DBANKS | 2019-03-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.3 | 1 | 2532.56 | 234.4 | 243.36 | 13.89 | 2040.91 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19683490200 |  | 100316843 |  | 6716208F |  |  |  | 566 | EX | DEMO / ABANDON / RI 02-28-19 | 2621P | SOUTHLAND | 115 SOUTHLAND DR | 067 | LEX | 2019-03-22 | TGNELSO | U130722 | 2019-02-26 | 2019-04-08 | 2019-04-29 |  | TGNELSO | 2019-03-22 | 2019-03-04 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.3167 | 4 | 641.36 | 605.49 | 0 | 35.87 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19683986800 |  | 100260842 |  | 7352256G | 1747947 |  |  | 565 | EX | REPLACE SL W/17026728400 | 2600B | HIGHLAND | 923 HIGHLAND AV | 019 | ASH | 2019-03-22 | U461496 | U131066 | 2019-02-28 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-03-22 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.25 | 1 | 1416.67 | 14.28 | 0 | 4.5 | 1397.89 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689558100 |  | 100260844 |  | 7352256G | 1747947 |  |  | 565 | EX | REPLACE SL W/17026728400 | 2600B | EDGEWOOD | 902 EDGEWOOD AV | 019 | ASH | 2019-03-22 | U461496 | U131066 | 2019-03-19 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-03-22 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.26667 | 1 | 968 | 14.28 | 0 | 4.5 | 949.22 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689558300 |  | 500943221 |  | 7352256G | 1747947 |  |  | 565 | EX | REPLACE SL W/17026728400 | 2600B | EDGEWOOD | 914 EDGEWOOD AV | 019 | ASH | 2019-03-22 | U461496 | U131066 | 2019-03-19 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-03-22 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.15 | 1 | 960.04 | 8.23 | 0 | 2.59 | 949.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19689976000 |  | 100309389 |  | 6712208L |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BUCKINGHAM | 665 BUCKINGHAM LN | 067 | LEX | 2019-03-22 | RVANDER | U125208 | 2019-03-20 | 2019-03-22 | 2019-04-09 |  | RVANDER | 2019-03-22 | 2019-03-22 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 22.8667 | 4 | 1320.76 | 1168.13 | 0 | 152.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19690367200 |  | 100296481 |  | 6716216O | 1962477 |  |  | 566 | EX | RETIRE S/L W/19-0268673-00 | 2621P | PRICE | 496 PRICE RD | 067 | LEX | 2019-03-22 | JENSMIN | U129939 | 2019-03-21 | 2019-03-21 |  |  | JENSMIN | 2019-03-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.45 | 2 | 50.82 | 25.64 | 0 | 25.18 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19690407300 |  | 100323503 |  | 6716208O |  |  |  | 565 | EX | GRADE 1 REPLACE SERV | 2621P | MALABU | 282 MALABU CT | 067 | LEX | 2019-03-22 | LMCDONA | U129939 | 2019-03-21 | 2019-03-21 | 2019-03-21 |  | LMCDONA | 2019-03-22 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.2833 | 4 | 1157.87 | 962.83 | 129.95 | 65.09 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026860200 |  | 501215341 |  | 6728208F | 1746354 | U461383 |  | 555 | EX | INSTALL 1025' OF 2"PMMP MAIN | 2600B | BAY SPRINGS | 3396 BAY SPRINGS PR LT | 067 | LEX | 2019-03-27 | U129900 | U461383 | 2019-02-07 | 2019-06-05 | 2019-06-18 | 2019-03-20 | A PARRIS | 2019-03-25 | 2019-03-12 | 2019-03-12 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP8602 |  |  | 100 | 055532190268602 | 69.5 | 8336 | 35644.66 | 3881.06 | 2009.46 | 1207.21 | 23973.78 | 0 | 67.78 | 4505.37 | 1042
KY | KY - WEST | 2621 | 19026864800 |  |  |  | 6716208A | 1962004 | U461383 |  | 558 | EX | ABANDON 10' OF 4"BSLP MAIN | 2621P | CLAYS MILL | 1836 CLAYS MILL | 067 | LEX | 2019-06-10 | U123258 | U461383 | 2019-03-06 | 2019-03-06 | 2019-07-01 | 2019-03-07 | JENSMIN | 2019-03-25 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP8648 | AMRCB |  | 100 | 055832190268648 | 3.9333 | 0 | 8380.2 | 228.79 | 0 | 220.16 | 7931.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680072600 |  | 100320170 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100 | 2600B | TAHOMA | 201 TAHOMA RD | 067 | LEX | 2019-03-25 | U126284 | U131066 | 2019-02-07 | 2019-03-29 |  |  | JOSH PASLEY | 2019-03-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.9333 | 1 | 2286.15 | 343.91 | 0 | 103.91 | 1838.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19690367900 |  | 100317800 |  | 6716204F | 1852188 |  |  | 565 | EX | REPLACE SL W/18026767600 | 2600B | DARTMOUTH | 3004 DARTMOUTH DR | 067 | LEX | 2019-04-02 | U461516 | U131066 | 2019-03-21 | 2019-12-31 |  |  | NEAL JOHNSON | 2019-03-25 |  | 2019-03-25 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.85 | 1 | 2078.32 | 319.23 | 0 | 101.01 | 1658.08 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19690993100 |  | 100408672 |  | 6688232O |  |  |  | 565 | EX | REPLACE SVC LINE D192906 | 2621P | PAPAGO | 207 PAPAGO TL | 073 | FRA | 2019-03-27 | U125208 | U130193 | 2019-03-25 | 2019-03-25 | 2019-03-25 |  | BJLONE | 2019-03-25 | 2019-03-25 | 2019-03-25 | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 13.0167 | 2 | 727.65 | 686.94 | 0 | 40.71 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 07710733300 |  | 100453687 |  | 6756176N |  |  |  | 566 | EX | ABANDON / RI 11-14-2007 | 2621P | WINSTON | 1186 WINSTON RD | 065 | IRV | 2019-03-26 | DENNING | DMCCULL | 2007-11-21 | 2016-10-14 |  |  | DENNING | 2019-03-26 | 2019-03-13 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 12.6 | 9 | 1527.79 | 609.08 | 11.24 | 138.09 | 769.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12971051900 |  | 100336902 | 11 | 16720212E | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | JOHNSON | 442 JOHNSON AV | 067 | LEX | 2019-03-26 | LSTANFI | DENNING | 2012-05-23 | 2014-12-23 |  |  | LSTANFI | 2019-03-26 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.8667 | 1 | 951.39 | 230.65 | 67.16 | 13.68 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 17526237800 |  | 100271968 | 61 | 6684228K |  |  |  | 565 | EX | REPL SERV - UNMTRD / MMO-MNFLD | 2621P | 4TH | 226 E 4TH ST | 073 | FRA | 2019-03-26 | CDESPAI | NARTRIP | 2017-07-20 | 2017-10-20 |  |  | CDESPAI | 2019-03-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.0333 | 1 | 3980.9 | 231.04 | 393.57 | 324.09 | 3032.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18026767700 |  |  |  | 6716204F | 1852188 | U122858 |  | 562 | EX | RETIRE 420'-4"&6" CSMP | 2600B | WILSON DOWNING | WILSON DOWNING RD | 067 | LEX | 2019-04-23 | U123258 | U122858 | 2018-04-13 | 2019-04-29 | 2019-04-29 | 2019-03-25 | NEAL JOHNSON | 2019-03-26 |  | 2019-04-11 | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP7677 |  |  | 100 | 056232180267677 |  | 0 | 138.16 | 0 | 0 | 0 | 138.16 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18026781901 |  | 501217528 |  | 6744208H | 1853803 | U461383 |  | 555 | EX | INSTALL 1000' OF 6"PMMP MAIN | 2600B | ROLLING HILLS | 950 ROLLING HILLS LN | 049 | WIN | 2019-04-17 | U123258 | U461383 | 2019-03-17 | 2019-02-26 | 2019-04-15 | 2019-03-25 | KEVIN KOUNS | 2019-03-26 | 2019-03-18 | 2019-02-27 | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP7819 |  |  | 100 | 055532180267819 | 160.95 | 21689 | 211247.45 | 9082.73 | 7452.1 | 2918.51 | 164658.41 | 0 | 424.48 | 26711.22 | 943
KY | KY - WEST | 2623 | 18026786201 |  | 501243574 |  | 6692228N | 1854273 | U128885 |  | 555 | EX | INSTALL 3,250' - 2" PMMP | 2600B | WHISPERING PIN | WHISPERING PIN DR LT1 | 073 | FRA | 2019-04-26 | U123258 | U128885 | 2019-03-27 | 2018-10-09 | 2019-04-15 | 2019-03-22 | LYNSTAFFORD | 2019-03-26 | 2018-11-05 | 2018-11-05 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP7862 |  |  | 100 | 055532180267862 | 395.75 | 198417 | 168826.19 | 21948.53 | 4639.16 | 7543.32 | 110697.52 | 0 | 1775.56 | 22222.1 | 3481
KY | KY - WEST | 2623 | 18614410100 |  | 100272090 |  | 6684228K | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | LOGAN | 429 LOGAN ST 1 | 073 | FRA | 2019-03-26 | CDESPAI | AOC SYST | 2018-05-24 | 2018-05-24 | 2021-05-08 |  | CDESPAI | 2019-03-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.3833 | 1 | 5767.83 | 250.49 | 477.95 | 351.42 | 4687.97 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18636038000 |  | 100336896 |  | 6720212E | 1855043 |  |  | 566 | EX | II - ABANDON ON SOII | 2621P | JOHNSON | 426 JOHNSON AV | 067 | LEX | 2019-03-26 | LSTANFI | U126129 | 2018-08-17 | 2019-03-26 |  |  | LSTANFI | 2019-03-26 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.2 | 1 | 750.96 | 72.89 | 33.87 | 4.3 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680072900 |  | 100320131 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | TAHOMA | 204 TAHOMA RD | 067 | LEX | 2019-03-26 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-03-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.95 | 1 | 4951 | 286.56 | 0 | 86.58 | 4577.86 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19683986100 |  | 100260836 |  | 7352256G | 1747947 |  |  | 565 | EX | REPLACE SL W/17026728400 | 2600B | HIGHLAND | 823 HIGHLAND AV | 019 | ASH | 2019-03-26 | U461496 | U131066 | 2019-02-28 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-03-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.16667 | 1 | 1409.3 | 8.65 | 0 | 2.76 | 1397.89 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19683986300 |  | 100260837 |  | 7352256G | 1747947 |  |  | 565 | EX | REPLACE SL W/17026728400 | 2600B | HIGHLAND | 837 HIGHLAND AV | 019 | ASH | 2019-03-26 | U123965 | U131066 | 2019-02-28 | 2019-12-31 |  |  | MARCUS BLANKENSHIP | 2019-03-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.21667 | 1 | 1851.36 | 11.37 | 0 | 3.62 | 1836.37 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19689103800 |  | 100346077 |  | 6700212J |  |  |  | 565 | EX | REROUTE SL - 03/25/19 | 2621P | LEXINGTON | 1325 LEXINGTON RD FRONT | 239 | VER | 2019-03-27 | U125208 | U125208 | 2019-03-18 | 2019-03-25 |  |  | BJLONE | 2019-03-26 | 2019-03-25 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 56.4167 | 6 | 3430.49 | 2950.01 | 115.99 | 364.49 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689557200 |  | 100260848 |  | 7352256G | 1747947 |  |  | 565 | EX | REPLACE SL W/17026728400 | 2600B | EDGEWOOD | 800 EDGEWOOD AV | 019 | ASH | 2019-03-26 | U461496 | U131066 | 2019-03-19 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-03-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.18333 | 1 | 1410.75 | 9.75 | 0 | 3.11 | 1397.89 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689557500 |  | 100260847 |  | 7352256G | 1747947 |  |  | 565 | EX | REPLACE SL W/17026728400 | 2600B | EDGEWOOD | 808 EDGEWOOD AV | 019 | ASH | 2019-03-26 | U123965 | U131066 | 2019-03-19 | 2019-12-31 |  |  | MARCUS BLANKENSHIP | 2019-03-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.16667 | 1 | 1411.45 | 10.29 | 0 | 3.27 | 1397.89 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19690580500 |  | 100287410 |  | 6720212G |  |  |  | 565 | EX | GRADE 1 / REPLACE | 2621P | EMERSON | 518 EMERSON DR | 067 | LEX | 2019-03-26 | TNEAL | U129939 | 2019-03-22 | 2019-03-22 | 2019-03-22 |  | TNEAL | 2019-03-26 | 2019-03-22 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 79.55 | 10 | 4483.4 | 3913.87 | 325.57 | 243.96 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691017100 |  | 100292019 |  | 6720216G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | PARKSIDE | 609 PARKSIDE DR | 067 | LEX | 2019-03-27 | U125208 | U130193 | 2019-03-25 | 2019-03-26 | 2019-04-13 |  | TGNELSO | 2019-03-26 | 2019-03-25 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 38.25 | 5 | 1594.56 | 1385.87 | 126.62 | 82.07 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19691017700 |  | 100343261 |  | 7236212G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | PREWITT | 490 PREWITT PK | 173 | MT | 2019-03-26 | DENNING | U125208 | 2019-03-25 | 2019-03-28 | 2019-04-15 |  | DENNING | 2019-03-26 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 11.7167 | 3 | 1115.11 | 580.59 | 393.28 | 141.24 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19691263400 |  | 100260846 |  | 7352256G |  |  |  | 566 | EX | RETIRE SVC LINE AT TAP | 2621P | EDGEWOOD | 814 EDGEWOOD AV | 019 | ASH | 2019-03-26 | U123965 | U130193 | 2019-03-26 | 2019-03-26 |  |  | MARCUS BLANKENSHIP | 2019-03-26 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.18333 | 1 | 678.74 | 9.75 | 0 | 3.11 | 665.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691294100 |  | 100338503 |  | 6720212E |  |  |  | 566 | EX | ABANDON LINE | 2621P | EDDIE | 196 EDDIE ST | 067 | LEX | 2019-03-27 | U125208 | U130193 | 2019-03-26 | 2019-03-26 |  |  | JENSMIN | 2019-03-26 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.51667 | 1 | 58.27 | 29.7 | 0 | 28.57 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691301100 |  | 100460689 |  | 6716204C |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LAREDO | 3441 LAREDO DR 5 | 067 | LEX | 2019-03-26 | DBANKS | U130193 | 2019-03-26 | 2019-03-26 |  |  | DBANKS | 2019-03-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.7833 | 1 | 347.17 | 150.73 | 187.52 | 8.92 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 06633839200 |  | 100276145 |  | 6684228G | 1855043 |  |  | 566 | EX | ABANDON MANI * / RI 02-11-2013 | 2600B | WALLACE | 135 WALLACE AV | 073 | FRA | 2019-04-02 | U125208 | RPOLLY | 2006-01-04 | 2019-03-27 |  |  | MCRAIG | 2019-03-27 | 2018-04-20 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 27 | 5 | 2102.45 | 1798.55 | 34.55 | 269.35 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 06633839500 |  | 100276144 |  | 6684228G | 1855043 |  |  | 566 | EX | ABANDON W/ 10276145 | 2621P | WALLACE | 137 WALLACE AV | 073 | FRA | 2019-03-27 | MCRAIG | RPOLLY | 2006-01-04 | 2019-03-27 |  |  | MCRAIG | 2019-03-27 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.36667 | 2 | 21.47 | 17.89 | 0 | 3.58 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12965323300 |  | 500228525 |  | 7240212B |  |  |  | 566 | EX | SOII - METER ABANDON ONLY | 2621P | APPERSON | 112 APPERSON HT | 173 | MT | 2019-03-27 | DENNING | U124967 | 2012-04-16 | 2014-12-31 |  |  | DENNING | 2019-03-27 | 2019-03-25 |  | D | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.4667 | 6 | 387.6 | 294.28 | 0 | 93.32 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12968019700 |  | 100333084 |  | 00NEW | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | CURLEY | 159 CURLEY AV | 067 | LEX | 2019-04-04 | U125208 | U124967 | 2012-05-02 | 2014-12-23 | 2018-11-30 |  | JENSMIN | 2019-03-27 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.3 | 1 | 862.8 | 75.67 | 74.41 | 72.82 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18604861500 |  | 100417466 |  | 6680224H | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | WILDWOOD | 219 WILDWOOD PL | 073 | FRA | 2019-03-27 | CDESPAI | AOC SYST | 2018-04-20 | 2018-04-20 | 2021-04-04 |  | CDESPAI | 2019-03-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.9333 | 1 | 3186.34 | 283.76 | 160.04 | 398.05 | 2344.49 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18606997400 |  | 100279703 | 17 | 6688228O | 1635077 |  |  | 565 | EX | REPLACE SERVICE - CORROSION | 2621P | BLUEBIRD | 342 BLUEBIRD LN | 073 | FRA | 2019-03-27 | CDESPAI | EBLANTO | 2018-04-30 | 2018-05-30 | 2018-06-30 |  | CDESPAI | 2019-03-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.6833 | 1 | 3694.08 | 210.97 | 383.95 | 295.93 | 2803.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680073300 |  | 100320167 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | TAHOMA | 209 TAHOMA RD | 067 | LEX | 2019-03-27 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-03-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.1333 | 1 | 2460.89 | 297.58 | 0 | 89.9 | 2073.41 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19683986200 |  | 500062063 |  | 7352256G | 1747947 |  |  | 565 | EX | REPLACE SL W/17026728400 | 2600B | HIGHLAND | 829 HIGHLAND AV | 019 | ASH | 2019-03-28 | U123965 | U131066 | 2019-02-28 | 2019-12-31 |  |  | MARCUS BLANKENSHIP | 2019-03-27 | 2019-03-27 | 2019-03-27 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.25 | 1 | 1854.96 | 14.1 | 0 | 4.49 | 1836.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19688543500 |  | 100337068 |  | 6720212I |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | CHESTNUT | 411 CHESTNUT ST | 067 | LEX | 2019-04-02 | U125208 | U129531 | 2019-03-15 | 2019-03-15 |  |  | LMCDONA | 2019-03-27 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2623 | 19691619800 |  | 100276141 |  | 6684228G |  |  |  | 566 | EX | ABANDON SVC LINE | 2621P | WALLACE | 141 WALLACE AV | 073 | FRA | 2019-04-02 | U125208 | U130193 | 2019-03-27 | 2019-03-27 |  |  | MCRAIG | 2019-03-27 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 1.2667 | 2 | 77.55 | 64.6 | 0 | 12.95 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19691640300 |  | 100250715 |  | 7376184A |  |  |  | 566 | EX | ABANDON SVC LINE | 2621P | TAYLOR CEMETAR | 39 TAYLOR CEMETAR LN | 159 | LOV | 2019-03-27 | JCKIRK | U130193 | 2019-03-27 | 2019-03-27 |  |  | JCKIRK | 2019-03-27 | 2019-03-27 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 9.1667 | 2 | 609.8 | 509.48 | 0 | 100.32 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691641500 |  | 100306592 |  | 6716212I |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | SUMMERVILLE | 917 SUMMERVILLE DR | 067 | LEX | 2019-03-27 | DBANKS | U130193 | 2019-03-27 | 2019-03-27 | 2019-03-27 |  | DBANKS | 2019-03-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.5333 | 1 | 1830.91 | 191.42 | 224.6 | 11.33 | 1403.56 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19691760100 |  | 100276142 |  | 6684228G |  |  |  | 566 | EX | ABAND SVC LINE | 2621P | WALLACE | 139 WALLACE AV | 073 | FRA | 2019-04-02 | U125208 | U130193 | 2019-03-27 | 2019-03-27 |  |  | MCRAIG | 2019-03-27 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.26667 | 2 | 15.48 | 12.89 | 0 | 2.59 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11933270200 |  | 100337739 |  | 6720212E | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | ELM TREE | 613 ELM TREE LN | 067 | LEX | 2019-03-28 | LSTANFI | U125208 | 2011-11-17 | 2017-03-31 | 2018-11-30 |  | LSTANFI | 2019-03-28 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.15 | 1 | 776.71 | 128.47 | 0.73 | 7.61 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18636012800 |  | 100441565 |  | 6720212J | 1855043 |  |  | 566 | EX | II - ABANDON ON SOII | 2621P | PEMBERTON | 555 PEMBERTON ST | 067 | LEX | 2019-04-11 | U125208 | U126129 | 2018-08-17 | 2019-03-27 |  |  | JENSMIN | 2019-03-28 | 2019-03-27 | 2019-03-27 | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.4333 | 2 | 872.35 | 83.25 | 69.11 | 80.09 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18642257500 |  | 100345845 |  | 6704212M | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | GAYBOURNE | 112 GAYBOURNE WY | 239 | VER | 2019-03-28 | EFGOINS | AOC SYST | 2018-09-11 | 2018-09-11 | 2021-08-26 |  | EFGOINS | 2019-03-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.16667 | 1 | 1875.35 | 8.57 | 178.93 | 0.51 | 1687.34 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18642260700 |  | 100345843 |  | 6704212M | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | GAYBOURNE | 108 GAYBOURNE WY | 239 | VER | 2019-03-28 | EFGOINS | AOC SYST | 2018-09-11 | 2018-09-11 | 2021-08-26 |  | EFGOINS | 2019-03-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.7167 | 2 | 2042.98 | 207.13 | 178.93 | 12.26 | 1644.66 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18642261400 |  | 100345855 |  | 6704212M | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | GAYBOURNE | 140 GAYBOURNE WY | 239 | VER | 2019-03-28 | EFGOINS | AOC SYST | 2018-09-11 | 2018-09-11 | 2021-08-26 |  | EFGOINS | 2019-03-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.9167 | 1 | 2161.28 | 157.64 | 178.93 | 9.33 | 1815.38 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18642261700 |  | 100345862 |  | 6704212M | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | GAYBOURNE | 111 GAYBOURNE WY | 239 | VER | 2019-03-28 | EFGOINS | AOC SYST | 2018-09-11 | 2018-09-11 | 2021-08-26 |  | EFGOINS | 2019-03-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.9167 | 1 | 1965.85 | 170.66 | 178.93 | 24.95 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18642264800 |  | 100345850 |  | 6704212M | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | GAYBOURNE | 126 GAYBOURNE WY | 239 | VER | 2019-03-28 | EFGOINS | AOC SYST | 2018-09-11 | 2018-09-11 | 2021-08-26 |  | EFGOINS | 2019-03-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.2333 | 1 | 1840.11 | 65.96 | 178.93 | 3.91 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18647396300 |  | 100337302 |  | 6720212E | 1855043 |  |  | 566 | EX | ABANDON - CUST REQ | 2621P | ELM TREE | 551 ELM TREE LN | 067 | LEX | 2019-04-02 | U125208 | U125208 | 2018-10-01 | 2018-10-26 | 2018-10-28 |  | LSTANFI | 2019-03-28 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.1833 | 1 | 1240.18 | 70.52 | 65.83 | 4.17 | 1099.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18655718000 |  | 100337332 |  | 6720212E | 1855043 |  |  | 566 | EX | II - ABANDON OR CO SOII | 2621P | ELM TREE | 554 ELM TREE LN | 067 | LEX | 2019-04-02 | U125208 | U126926 | 2018-11-05 | 2018-10-30 | 2018-11-30 |  | LSTANFI | 2019-03-28 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.2 | 1 | 790.15 | 71.71 | 74.29 | 4.25 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18655718100 |  | 100337333 |  | 6720212E | 1855043 |  |  | 566 | EX | II - ABANDON OR CO SOII | 2621P | ELM TREE | 558 ELM TREE LN | 067 | LEX | 2019-03-28 | LSTANFI | U126926 | 2018-11-05 | 2018-10-30 | 2018-11-30 |  | LSTANFI | 2019-03-28 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.2 | 1 | 75.94 | 71.7 | 0 | 4.24 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18655720500 |  | 100296825 |  | 6716212C | 1855043 |  |  | 566 | EX | II- ABANDON OR CO SOII | 2621P | ASH | 436 ASH ST | 067 | LEX | 2019-04-02 | U125208 | U126926 | 2018-11-05 | 2018-11-30 | 2018-11-30 |  | LSTANFI | 2019-03-28 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.35 | 1 | 662.77 | 20.9 | 0.73 | 1.24 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680073500 |  | 100320134 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | TAHOMA | 210 TAHOMA RD | 067 | LEX | 2019-03-28 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-03-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.4333 | 1 | 3391.92 | 314.96 | 0 | 95.15 | 2981.81 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19686970800 |  | 100327521 |  | 6720212M |  |  |  | 565 | EX | NBT - SERV/MTR UPG - 2" P | 2621P | ASHLAND | 251 S ASHLAND AV | 067 | LEX | 2019-04-02 | U125208 | U125208 | 2019-03-08 | 2019-03-08 | 2019-04-04 |  | JENSMIN | 2019-03-28 | 2019-03-25 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.7667 | 3 | 7467.74 | 488.78 | 123 | 217.68 | 6638.28 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689557600 |  | 500183009 |  | 7352256G | 1747947 |  |  | 565 | EX | REPLACE SL W/17026728400 | 2600B | EDGEWOOD | 820 EDGEWOOD AV | 019 | ASH | 2019-03-28 | U123965 | U131066 | 2019-03-19 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-03-28 | 2019-03-27 | 2019-03-27 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.28333 | 1 | 2153.75 | 15.17 | 0 | 4.83 | 2133.75 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689558000 |  | 100260845 |  | 7352256G | 1747947 |  |  | 565 | EX | REPLACE SL W/17026728400 | 2600B | EDGEWOOD | 824 EDGEWOOD AV | 019 | ASH | 2019-03-28 | U123965 | U131066 | 2019-03-19 | 2019-12-31 |  |  | MARCUS BLANKENSHIP | 2019-03-28 | 2019-03-28 | 2019-03-28 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 8.5 | 1 | 1811.86 | 460.35 | 0 | 146.79 | 1204.72 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19690532800 |  | 100267187 |  | 7352260N |  |  |  | 565 | EX | REPLACE SERV W/MMO | 2621P | JANE HILL | 213 JANE HILL RD | 019 | ASH | 2019-03-28 | MCOLLET | U125208 | 2019-03-22 | 2019-04-11 |  |  | MCOLLET | 2019-03-28 | 2019-03-27 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 15.4833 | 3 | 1711.09 | 913.89 | 185.97 | 611.23 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19690969700 |  | 100257778 |  | 7344268N |  |  |  | 566 | EX | DEMO / ABANDON / RI 03-28-19 | 2621P | RIVERSIDE | 714 RIVERSIDE BV | 089 | WUR | 2019-03-28 | MCOLLET | U125208 | 2019-03-25 | 2019-04-25 | 2019-04-25 |  | MCOLLET | 2019-03-28 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.7 | 2 | 618.07 | 335.64 | 63.54 | 218.89 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19691717900 |  | 100351139 |  | 6744208P |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | COLLEGE | 207 COLLEGE ST | 049 | WIN | 2019-03-28 | DENNING | U130193 | 2019-03-27 | 2019-03-27 | 2019-03-27 |  | DENNING | 2019-03-28 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 5.7833 | 2 | 589.69 | 314.5 | 175.44 | 99.75 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19692119600 |  | 100337259 |  | 6720212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D192717 | 2621P | RAND | 245 RAND AV | 067 | LEX | 2019-04-02 | U125208 | U131168 | 2019-03-28 | 2019-03-27 | 2019-03-27 |  | LCLARK | 2019-03-28 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.9167 | 3 | 4071.93 | 1022.94 | 137.18 | 60.61 | 2851.2 | 0 | 0 | 0
KY | KY - WEST | 2623 | 06654113800 |  | 100412901 |  | 6700212I |  |  |  | 566 | EX | ABANDON / RI 03-24-2004 | 2600B | BRYANWOOD | 304 BRYANWOOD ST | 239 | VER | 2019-03-29 | BJLONE | RPOLLY | 2006-07-19 | 2019-03-29 |  |  | BJLONE | 2019-03-29 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.96667 | 1 | 696.77 | 53.69 | 0 | 3.18 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07698914500 |  | 100336867 | 18 | ? | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | JOHNSON | 465 JOHNSON AV | 067 | LEX | 2019-03-29 | DBANKS | MPILON | 2007-08-17 | 2019-03-29 |  |  | DBANKS | 2019-03-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.1833 | 1 | 865.82 | 174.08 | 41.54 | 10.3 | 639.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11902003200 |  | 100341499 |  | 7240212B |  |  |  | 566 | EX | SOII - METER ABANDON ONLY | 2621P | MAIN | 21 E MAIN ST | 173 | MT | 2019-04-02 | U125208 | U906631 | 2011-04-19 | 2014-12-23 |  |  | DENNING | 2019-03-29 |  |  | D | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.93333 | 1 | 66.49 | 50.43 | 0 | 16.06 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11903441400 |  | 100337225 |  | 00NEW | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | ENGMAN | 206 ENGMAN AV | 067 | LEX | 2019-03-29 | DBANKS | U123933 | 2011-04-27 | 2019-03-29 |  |  | DBANKS | 2019-03-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.4333 | 2 | 1237.54 | 138.67 | 50.02 | 105.97 | 942.88 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12965306100 |  | 100340965 |  | 7240212B |  |  |  | 566 | EX | SOII - ABANDON METER ONLY | 2621P | MAIN | 10 E MAIN ST | 173 | MT | 2019-03-29 | DENNING | U124967 | 2012-04-16 | 2014-12-23 |  |  | DENNING | 2019-03-29 |  |  | D | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.8 | 1 | 127.86 | 96.95 | 0 | 30.91 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12975864200 |  | 100337446 |  | V-1021-51 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | PEMBERTON | 520 PEMBERTON AV | 067 | LEX | 2019-04-02 | U125208 | U123854 | 2012-06-11 | 2019-03-29 |  |  | DBANKS | 2019-03-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.81667 | 1 | 728.52 | 43.93 | 42.1 | 2.59 | 639.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 17026739300 |  |  |  | 7356256P | 1749141 | BKSLONE |  | 557 | EX | INSTALL 274'- 8" PM/CSMP | 2600B | WINCHESTER | 4400 WINCHESTER AV | 019 | ASH | 2019-04-25 | U124014 | BKSLONE | 2017-11-21 | 2019-03-14 | 2019-04-14 | 2019-03-27 | BCOFER | 2019-03-29 | 2019-03-11 | 2019-03-11 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP7393 | AMRCB |  | 100 | 055732170267393 | 171.5833 | 6560 | 93319.94 | 10044.06 | 36386.71 | 2435.53 | 32526.67 | 0 | 246.04 | 11680.93 | 328
KY | KY - EAST | 2631 | 17026739400 |  |  |  | 7356256P | 1749141 | BKSLONE |  | 558 | EX | RETIRE 245'-10"/2" BSMP | 2600B | WINCHESTER | 4400 WINCHESTER AV | 019 | ASH | 2019-04-25 | U124014 | BKSLONE | 2017-11-21 | 2019-04-01 | 2019-04-14 | 2019-03-27 | BCOFER | 2019-03-29 |  | 2019-03-27 | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP7394 | AMRCB |  | 100 | 055832170267394 |  | 0 | 132.2 | 0 | 0 | 0 | 132.2 | 0 | 0 | 0
KY | KY - WEST | 2623 | 17558980800 |  | 100345716 | 15 | 6696212D | 1635077 |  |  | 565 | EX | REPL SERV/ATMOS CORR | 2621P | NANCY | 782 NANCY ST | 239 | VER | 2019-03-29 | BJLONE | RVANDER | 2017-10-31 | 2017-12-29 |  |  | BJLONE | 2019-03-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.1333 | 1 | 2023.24 | 176.39 | 245.09 | 10.45 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18026767601 |  |  |  | 6716204F | 1852188 | U122858 |  | 561 | EX | INSTALL 420'-4"&6" PMMP | 2600B | WILSON DOWNING | WILSON DOWNING RD | 067 | LEX | 2019-04-23 | U123258 | U122858 | 2019-03-21 | 2019-04-01 | 2019-04-29 | 2019-03-04 | NEAL JOHNSON | 2019-03-29 | 2019-04-10 | 2019-04-10 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP7676 |  |  | 100 | 056132180267676 | 335.4667 | 21956 | 139472.01 | 19212.46 | 10696.54 | 6308.85 | 85080.21 | 0 | 592.55 | 17581.4 | 499
KY | KY - WEST | 2621 | 18026799100 |  |  |  | 6720216K | 1856126 | U122858 |  | 561 | VO | INSTALL 67'-2" PMMP | 2600B | JUDY | 581 JUDY LN | 067 | LEX | 2019-03-29 |  | U122858 | 2018-10-04 | 2019-04-24 | 2019-04-30 |  | U122858 | 2019-03-29 |  |  | B | 00032 | 88000000 | 0326210 | 0326210 | 00032 | 05007 |  |  |  |  | AMRCB |  | 100 | AMRCB |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18643246500 |  | 100413186 |  | 6700212N | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | DUNROVEN | 182 DUNROVEN DR | 239 | VER | 2019-04-02 | U125208 | AOC SYST | 2018-09-14 | 2018-09-14 | 2021-08-29 |  | BJLONE | 2019-03-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.0833 | 1 | 1580.47 | 60.49 | 184.91 | 3.57 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18643247400 |  | 100346054 |  | 6700212J | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | DERBY | 116 DERBY CT | 239 | VER | 2019-04-02 | U125208 | AOC SYST | 2018-09-14 | 2018-09-14 | 2021-08-29 |  | BJLONE | 2019-03-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.6167 | 1 | 1884.38 | 147.59 | 136.75 | 8.73 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18662693900 |  | 100325709 |  | 6720208E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | GARDEN | 305 GARDEN RD | 067 | LEX | 2019-03-29 | JENSMIN | U128293 | 2018-12-17 | 2019-06-14 | 2020-12-31 |  | JENSMIN | 2019-03-29 | 2019-03-28 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.6333 | 3 | 2883.44 | 136.32 | 236.36 | 45.39 | 2465.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026861600 |  |  |  | 6716212L | 1640402 | U122858 |  | 561 | EX | INSTALL 97'-3" PMMP | 2600B | VINE | VINE ST | 067 | LEX | 2019-06-24 | U123258 | U122858 | 2019-02-11 | 2019-04-24 | 2019-04-30 | 2019-03-29 | LARRY BROWN | 2019-03-29 | 2019-03-13 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP8616 |  |  | 100 | 056132190268616 | 24 | 366 | 59513.17 | 1337.04 | 754.57 | 754.13 | 49078.29 | 0 | 67.72 | 7521.42 | 122
KY | KY - WEST | 2621 | 19026861700 |  |  |  | 6716212L | 1640402 | U122858 |  | 562 | EX | RETIRE 97'-3" PMP | 2600B | VINE | VINE ST | 067 | LEX | 2019-05-29 | U123258 | U122858 | 2019-02-11 | 2019-04-30 | 2019-04-30 | 2019-03-29 | LARRY BROWN | 2019-03-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP8617 |  |  | 100 | 056232190268617 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19683756900 |  | 100312347 |  | 6716208J |  |  |  | 565 | EX | MOVE PL SERV LINE - MAR 14TH | 2621P | HOLLYHILL | 332 HOLLYHILL DR | 067 | LEX | 2019-03-29 | LMCDONA | U125208 | 2019-02-27 | 2019-03-14 | 2019-03-14 |  | LMCDONA | 2019-03-29 | 2019-03-29 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 19.8167 | 3 | 1716.12 | 1051.98 | 110.14 | 554 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19686913800 |  | 100457411 | 35 | 6716212K |  |  |  | 566 | EX | DEMO / ABANDON / RI 03-08-19 | 2621P | WINSLOW | 130 WINSLOW ST | 067 | LEX | 2019-04-02 | U125208 | MAWAN | 2019-03-08 | 2019-04-08 | 2019-04-08 |  | TNEAL | 2019-03-29 | 2019-03-21 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 22.3 | 5 | 1830.8 | 1157.81 | 15.67 | 68.58 | 588.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19687871600 |  | 100313220 |  | 6716208A |  |  |  | 566 | EX | DEMO / ABANDON / RI 03-12-19 | 2621P | WOODBINE | 535 WOODBINE RD | 067 | LEX | 2019-03-29 | LMCDONA | U132002 | 2019-03-13 | 2019-04-12 | 2019-04-13 |  | LMCDONA | 2019-03-29 | 2019-03-27 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.1333 | 7 | 713.32 | 646.92 | 27.98 | 38.42 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19692113400 |  | 100286953 |  | 6720212F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D192718 | 2621P | CASTLEWOOD | 206 CASTLEWOOD DR | 067 | LEX | 2019-04-02 | U125208 | U130193 | 2019-03-28 | 2019-03-28 | 2019-03-28 |  | DBANKS | 2019-03-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.5667 | 1 | 3056.04 | 301.51 | 312.85 | 17.84 | 2423.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19692283000 |  | 501200049 |  | 6712228H | 1749206 |  |  | 565 | EX | REPLACE SL W/17026740500 | 2600B | LEMONS MILL | 1005 LEMONS MILL RD | 209 | GEO | 2019-03-29 | U126285 | U131066 | 2019-03-29 | 2019-12-31 |  |  | DDAVIS | 2019-03-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 8.5 | 1 | 1316.86 | 501.36 | 30.65 | 29.7 | 755.15 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19692295000 |  | 100272215 |  | 6684228O |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | TODD | 127 E TODD ST | 073 | FRA | 2019-04-02 | U125208 | U131367 | 2019-03-29 | 2019-03-29 |  |  | MCRAIG | 2019-03-29 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 12.3667 | 2 | 814.61 | 613.76 | 87.98 | 112.87 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19692324000 |  | 100311413 |  | 6712204D |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | SAYBROOK | 3424 SAYBROOK RD | 067 | LEX | 2019-03-29 | JENSMIN | U131367 | 2019-03-29 | 2019-03-29 |  |  | JENSMIN | 2019-03-29 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.7833 | 1 | 2447.29 | 278.87 | 79.72 | 268.35 | 1820.35 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19688206400 |  | 100467531 |  | 6716212N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094060 | 2621P | BOB O LINK | 701 BOB O LINK DR | 067 | LEX | 2019-04-02 | U125208 | U125208 | 2019-03-14 | 2019-03-15 | 2019-04-03 |  | ASNICHO | 2019-03-30 | 2019-03-19 | 2019-03-19 | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 41.3 | 9 | 3136.26 | 1963.07 | 1056.73 | 116.46 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07690085400 |  | 100286957 | 35 | V-1021-44 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | CASTLEWOOD | 214 CASTLEWOOD DR | 067 | LEX | 2019-04-01 | JENSMIN | MPILON | 2007-06-07 | 2014-12-23 |  |  | JENSMIN | 2019-04-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.63333 | 1 | 749.89 | 37.44 | 43.38 | 29.17 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 09797841400 |  | 100334205 | 30 | 6720212O | 1855043 |  |  | 566 | EX | SOII - ABANDON SERV/ RA 7-2009 | 2621P | LIBERTY | 1668 LIBERTY RD | 067 | LEX | 2019-04-01 | LSTANFI | MPILON | 2009-07-30 | 2019-03-28 |  |  | LSTANFI | 2019-04-01 | 2019-03-28 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.53333 | 3 | 741.73 | 34.7 | 65.32 | 1.81 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 17557865700 |  | 100345727 | 22 | 6696212D | 1635077 |  |  | 565 | EX | REPLACE SERV - ATMOS CORR | 2621P | NANCY | 793 NANCY ST | 239 | VER | 2019-04-01 | CDESPAI | RVANDER | 2017-10-26 | 2017-12-29 |  |  | CDESPAI | 2019-04-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.93333 | 2 | 1617.12 | 42.15 | 213.73 | 29.74 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18642263400 |  | 100412904 |  | 6700212N | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | PADDOCK | 224 PADDOCK DR | 239 | VER | 2019-04-01 | CDESPAI | AOC SYST | 2018-09-11 | 2018-09-11 | 2021-08-26 |  | CDESPAI | 2019-04-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.2333 | 2 | 1973.86 | 239.04 | 234.6 | 168.72 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18643243300 |  | 100345839 |  | 6704212N | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | GLENHAVEN | 1 GLENHAVEN DR | 239 | VER | 2019-04-01 | CDESPAI | AOC SYST | 2018-09-14 | 2018-09-14 | 2021-08-29 |  | CDESPAI | 2019-04-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 12.0667 | 2 | 6166.88 | 554.78 | 302.02 | 391.71 | 4918.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026850600 |  | 501255964 |  | 6724208D | 1960364 | U461383 |  | 555 | EX | INSTALL 375' OF 4"PMMP MAIN | 2600B | LITTLE HERB | 1825 LITTLE HERB WY | 067 | LEX | 2019-04-15 | U123258 | U461383 | 2019-01-03 | 2019-01-31 | 2019-04-01 | 2019-04-01 | JAMIE LYNN | 2019-04-01 | 2019-03-27 | 2019-03-27 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP8506 |  |  | 100 | 055532190268506 | 34.4167 | 2000 | 23683.26 | 1819.5 | 311.37 | 573.1 | 17921.33 | 0 | 67.29 | 2990.67 | 400
KY | KY - WEST | 2621 | 19680073000 |  | 100320168 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | TAHOMA | 205 TAHOMA RD | 067 | LEX | 2019-04-01 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-04-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.6167 | 1 | 3810.49 | 390.89 | 0 | 109.58 | 3310.02 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19684248900 |  | 100243907 | 11 | 7348256N |  |  |  | 566 | EX | DEMO / ABANDON / RI 03-01-19 | 2621P | MILLER | 1724 MILLER ST | 019 | ASH | 2019-04-01 | AMCCORM | SJUDE | 2019-03-01 | 2019-04-01 | 2019-04-01 |  | AMCCORM | 2019-04-01 | 2019-04-01 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 6.7333 | 2 | 715.7 | 402.68 | 1.38 | 311.64 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19687222600 |  | 100304363 |  | 6712212P |  |  |  | 566 | EX | ABANDON / RI 04-10-15 / NCV | 2621P | MAYWICK | 968 MAYWICK DR | 067 | LEX | 2019-04-01 | LMCDONA | U125208 | 2019-03-11 | 2019-04-09 |  |  | LMCDONA | 2019-04-01 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.2667 | 2 | 763.3 | 670.46 | 54.65 | 38.19 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689043000 |  | 100245216 | 59 | 7356256M |  |  |  | 566 | EX | ABANDON ASAP / RI 03-18-19 | 2621P | GREENWAY | 3831 GREENWAY RD | 019 | ASH | 2019-04-01 | AMCCORM | SJUDE | 2019-03-18 | 2019-04-12 |  |  | AMCCORM | 2019-04-01 | 2019-03-29 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 9.6 | 4 | 987.32 | 570.28 | 0 | 417.04 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19691400400 |  | 100438595 |  | 6752180E |  |  |  | 566 | EX | ABANDON / RI 08-11-16 | 2621P | WALTER | 129 WALTER LN | 151 | WAC | 2019-04-01 | DENNING | U125208 | 2019-03-26 | 2019-04-16 |  |  | DENNING | 2019-04-01 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 23.8667 | 4 | 1408.84 | 1183.12 | 1.38 | 224.34 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691626300 |  | 100291868 |  | 6720216G |  |  |  | 565 | EX | REPLACE SERVICE LINE - D193690 | 2621P | EDEN | 684 EDEN RD | 067 | LEX | 2019-04-02 | U125208 | U125208 | 2019-03-27 | 2019-03-29 | 2019-04-17 |  | LSTANFI | 2019-04-01 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.6833 | 3 | 1353.24 | 968.64 | 329.39 | 55.21 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19692428400 |  | 100323277 |  | 6716208P |  |  |  | 565 | EX | REPLACE SERVICE | 2621P | ROBIN | 863 ROBIN RD | 067 | LEX | 2019-04-01 | DBANKS | U131168 | 2019-03-29 | 2019-03-29 | 2019-03-29 |  | DBANKS | 2019-04-01 | 2019-03-30 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.95 | 6 | 4655.98 | 966.96 | 250.83 | 56.13 | 3382.06 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19692616600 |  | 100337265 |  | 6720212E |  |  |  | 565 | EX | REPLACE SVC LINE D000060 | 2621P | RAND | 223 RAND AV 1F | 067 | LEX | 2019-04-02 | U125208 | U130193 | 2019-04-01 | 2019-04-01 | 2019-04-01 |  | JENSMIN | 2019-04-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.3333 | 1 | 3903.83 | 257.76 | 477.43 | 200.89 | 2967.75 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19692693700 |  | 100467664 |  | 7352144 |  |  |  | 566 | EX | AABANDON LINE | 2621P | PM3 | PM3 | 071 | GRE | 2019-04-02 | U125208 | U130193 | 2019-04-01 | 2019-04-01 |  |  | JCKIRK | 2019-04-01 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.2167 | 1 | 231.48 | 178.7 | 0 | 52.78 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18604210300 |  | 100272308 |  | 6684224B | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER | 2621P | VALLEY VISTA | 233 VALLEY VISTA DR | 073 | FRA | 2019-04-03 | U125208 | U125208 | 2018-04-18 | 2018-05-02 | 2018-06-02 |  | CDESPAI | 2019-04-02 | 2019-03-27 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.6167 | 2 | 4497.03 | 268.99 | 241.1 | 306.88 | 3680.06 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18607232600 |  | 100443295 |  | 6712232O |  |  |  | 566 | EX | DEMO / ABANDON / RI 05-02-18 | 2621P | HAMILTON | 804 N HAMILTON ST 15 | 209 | GEO | 2019-04-03 | U125208 | U129799 | 2018-05-01 | 2018-06-01 | 2018-06-01 |  | KKINDER | 2019-04-02 | 2018-05-09 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 17.9333 | 5 | 866.34 | 797.34 | 23.54 | 45.46 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18642264100 |  | 100346053 |  | 6700212J | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | PADDOCK | 151 PADDOCK DR | 239 | VER | 2019-04-02 | CDESPAI | AOC SYST | 2018-09-11 | 2018-09-11 | 2021-08-26 |  | CDESPAI | 2019-04-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.6667 | 1 | 2131.57 | 158.44 | 211.76 | 170.06 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680074200 |  | 100320162 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | TAHOMA | 219 TAHOMA RD | 067 | LEX | 2019-04-02 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-04-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.9833 | 1 | 2886.98 | 353.71 | 0 | 99.15 | 2434.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19683842900 |  | 100288721 |  | 6720212D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER / | 2621D | HI CREST | 640 HI CREST DR | 067 | LEX | 2019-04-03 | U125208 | AOC SYST | 2019-02-27 | 2019-04-02 | 2019-04-28 |  | DBANKS | 2019-04-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.46667 | 1 | 2201.63 | 25.46 | 166.28 | 1.46 | 2008.43 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19688682400 |  | 100298405 |  | 6716212H | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER / | 2621D | SHORT | 514 W SHORT ST | 067 | LEX | 2019-04-02 | JENSMIN | AOC SYST | 2019-03-15 | 2019-03-29 | 2019-04-29 |  | JENSMIN | 2019-04-02 | 2019-03-25 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.35 | 3 | 4888.04 | 418.13 | 156.83 | 196.25 | 4116.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19689511600 |  | 100314675 |  | 6716212K |  |  |  | 566 | EX | DEMO / ABANDON / RI 03-08-19 | 2621P | LIMESTONE | 405 S LIMESTONE ST | 067 | LEX | 2019-04-03 | U125208 | U125208 | 2019-03-19 | 2019-04-02 |  |  | DBANKS | 2019-04-02 | 2019-03-25 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.0333 | 9 | 7737.23 | 838.23 | 10.36 | 245.62 | 6643.02 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19692269100 |  | 100284948 |  | 6764176K |  |  |  | 566 | EX | DEMO / ABANDON / RI 04-01-19 | 2621P | RIDDELL | 421 RIDDELL CT | 065 | IRV | 2019-04-02 | DENNING | U132002 | 2019-03-29 | 2019-04-29 | 2019-04-29 |  | DENNING | 2019-04-02 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 18.8667 | 4 | 1111.7 | 934.51 | 0 | 177.19 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19692283200 |  | 100466002 |  | 6760176I |  |  |  | 566 | EX | ABANDON / RA 04-01-19 TRL GONE | 2621P | SUB STATION | 435 SUB STATION RD | 065 | IRV | 2019-04-02 | DENNING | U125208 | 2019-03-29 | 2019-04-02 | 2019-04-29 |  | DENNING | 2019-04-02 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 13.1333 | 4 | 780.6 | 656.17 | 0 | 124.43 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19693913300 |  | 100435744 |  | 6716212K |  |  |  | 566 | EX | ABANDON SVC LINE | 2621P | LIMESTONE | 401 S LIMESTONE ST | 067 | LEX | 2019-04-02 | DBANKS | U130193 | 2019-04-02 | 2019-04-02 |  |  | DBANKS | 2019-04-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.0833 | 1 | 3230.31 | 335.7 | 0 | 19.13 | 2875.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19693917100 |  | 100314671 |  | 6716212K |  |  |  | 566 | EX | ABANDON SVC LINE | 2621P | WINSLOW | 108 WINSLOW ST | 067 | LEX | 2019-04-02 | DBANKS | U130193 | 2019-04-02 | 2019-04-02 |  |  | DBANKS | 2019-04-02 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.0667 | 1 | 72.7 | 60.29 | 8.98 | 3.43 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19694016900 |  | 100446838 |  | 7364188G |  |  |  | 566 | EX | ABANDON SVC LINE | 2621P | KY FIELD | KY FIELD | 159 | INE | 2019-04-03 | U125208 | U130193 | 2019-04-02 | 2019-04-02 |  |  | JCKIRK | 2019-04-02 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 0.7 | 1 | 42.12 | 39.84 | 0 | 2.28 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 17026740501 |  | 501226574 |  | 6712228H | 1749206 | U128885 |  | 555 | EX | INSTALL 4,450' - 6/4/2" PMMP | 2600B | AMERSON | 134 AMERSON WY | 209 | GEO | 2019-04-15 | U123258 | U128885 | 2019-01-24 | 2018-11-20 | 2019-04-01 | 2019-03-28 | DDAVIS | 2019-04-03 | 2018-11-12 | 2018-11-12 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP7405 |  |  | 100 | 055532170267405 | 494.5667 | 325059 | 479246.27 | 28794.82 | 21834.35 | 8714.39 | 354450.06 | 0 | 3502.09 | 61950.56 | 4711
KY | KY - WEST | 2623 | 18623306400 |  | 100278422 |  | 6688228B | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | HOPI | 512 HOPI TL | 073 | FRA | 2019-04-03 | CDESPAI | AOC SYST | 2018-06-26 | 2018-06-26 | 2021-06-10 |  | CDESPAI | 2019-04-03 | 2019-03-20 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.2833 | 3 | 2083.35 | 247.74 | 216.57 | 287.54 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18651138000 |  | 100303569 |  | 6712208C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | OLEANDER | 2225 OLEANDER CT | 067 | LEX | 2019-04-03 | JENSMIN | AOC SYST | 2018-10-16 | 2019-04-03 | 2019-12-31 |  | JENSMIN | 2019-04-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.2333 | 1 | 2256.83 | 253.52 | 270.69 | 141.31 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19026868500 |  |  |  | 6712228H | 1749206 | U128885 |  | 560 | EX | RETIRE 648' - 2" PMMP | 2600B | US HWY 460B | US HWY 460B | 209 | GEO | 2019-04-15 | U123258 | U128885 | 2019-03-29 | 2019-04-15 | 2019-04-15 | 2019-03-29 | DDAVIS | 2019-04-03 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00560 | 3200560 |  |  | WP8685 |  |  | 100 | 056032190268685 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19683520200 |  | 100303287 |  | 6712208C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER / | 2621D | PINEBLOOM | 977 PINEBLOOM DR | 067 | LEX | 2019-04-03 | JENSMIN | AOC SYST | 2019-02-26 | 2019-03-28 | 2019-04-27 |  | JENSMIN | 2019-04-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.8167 | 1 | 1701.83 | 107.48 | 202.96 | 59.89 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 08726682100 |  | 100311042 |  | 6712208O |  |  |  | 566 | EX | ABANDON SL - | 2621P | ROXBURG | 3209 ROXBURG DR | 067 | LEX | 2019-04-04 | RVANDER | SSUTHER | 2008-04-08 | 2015-05-15 |  |  | RVANDER | 2019-04-04 | 2019-03-25 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.5333 | 6 | 697.91 | 659.72 | 0 | 38.19 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12965306500 |  | 100342877 |  | 7240212B |  |  |  | 566 | EX | SOII - ABANDON METER ONLY | 2621P | BANK | 13 N BANK ST | 173 | MT | 2019-04-04 | RJJOHNS | U124967 | 2012-04-16 | 2014-12-23 |  |  | RJJOHNS | 2019-04-04 | 2019-04-03 |  | D | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 11.3333 | 5 | 613.34 | 538.85 | 0 | 74.49 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 17550790800 |  | 100346786 |  | 6696212O | 1635077 |  |  | 565 | EX | REPL SERV LINE - ATMOS CORR | 2621P | MACEY | 300 MACEY AV | 239 | VER | 2019-04-04 | CDESPAI | U125208 | 2017-10-04 | 2017-12-29 |  |  | CDESPAI | 2019-04-04 | 2019-04-03 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.45 | 2 | 2427.21 | 205.24 | 310.36 | 320.3 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18642260600 |  | 100346046 |  | 6700212J | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | YORKSHIRE | 116 YORKSHIRE CT | 239 | VER | 2019-04-04 | CDESPAI | AOC SYST | 2018-09-11 | 2018-09-11 | 2021-08-26 |  | CDESPAI | 2019-04-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.45 | 1 | 1985.86 | 84.18 | 219.98 | 90.39 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18642265600 |  | 100346047 |  | 6700212J | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | YORKSHIRE | 108 YORKSHIRE CT | 239 | VER | 2019-04-04 | CDESPAI | AOC SYST | 2018-09-11 | 2018-09-11 | 2021-08-26 |  | CDESPAI | 2019-04-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.65 | 1 | 1991.44 | 38.61 | 219.98 | 41.44 | 1691.41 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18643241900 |  | 100422534 |  | 6700212J | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | ROAN | 107 ROAN RD | 239 | VER | 2019-04-04 | CDESPAI | AOC SYST | 2018-09-14 | 2018-09-14 | 2021-08-29 |  | CDESPAI | 2019-04-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.4833 | 1 | 2001.34 | 85.92 | 231.85 | 92.26 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18643243200 |  | 100346057 |  | 6700212J | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | ROAN | 114 ROAN RD | 239 | VER | 2019-04-04 | CDESPAI | AOC SYST | 2018-09-14 | 2018-09-14 | 2021-08-29 |  | CDESPAI | 2019-04-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.9333 | 1 | 2183.16 | 173.63 | 231.85 | 186.37 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19026859200 |  | 501188606 |  | 6716232I | 1853242 | U461383 |  | 555 | EX | INSTALL 3250' OF 2"PMMP MAIN | 2600B | BROOKFORD | 124 BROOKFORD WY | 209 | GEO | 2019-05-14 | U462463 | U461383 | 2019-02-04 | 2019-05-15 | 2019-06-12 | 2019-04-03 | MARK ROGERS | 2019-04-04 | 2019-03-04 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP8592 |  |  | 100 | 055532190268592 | 152.4333 | 69920 | 162596.23 | 7965.88 | 6438.82 | 2578.18 | 124356.58 | 0 | 763.76 | 20493.01 | 3040
KY | KY - EAST | 2631 | 19026869300 |  |  |  | 7356256J | 1962825 | U122858 |  | 557 | EX | INSTALL 10'-3" PMLP | 2621P | LOGAN | LOGAN | 019 | ASH | 2019-07-17 | U124014 | U122858 | 2019-04-03 | 2019-06-28 | 2019-07-03 | 2019-04-04 | AMCCORMICK | 2019-04-04 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP8693 |  |  | 100 | 055732190268693 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
KY | KY - EAST | 2631 | 19026869400 |  |  |  | 7356256J | 1962825 | U122858 |  | 558 | EX | RETIRE 10'-3" PLP | 2621P | LOGAN | LOGAN | 019 | ASH | 2019-07-17 | U124014 | U122858 | 2019-04-03 | 2019-04-03 | 2019-07-03 | 2019-04-04 | AMCCORMICK | 2019-04-04 | 2019-06-19 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP8694 |  |  | 100 | 055832190268694 | 0.05 | 0 | 7595.77 | 5674.55 | 24.46 | 1896.76 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678775600 |  | 100299164 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 288 BURKE RD | 067 | LEX | 2019-04-11 | U125208 | U131066 | 2019-02-01 | 2019-04-04 | 2019-04-04 |  | JENSMIN | 2019-04-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.25 | 1 | 2033.38 | 134.8 | 178.96 | 75.13 | 1644.49 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680074400 |  | 100320161 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | TAHOMA | 221 TAHOMA RD | 067 | LEX | 2019-04-04 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-04-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.1333 | 1 | 2603.6 | 362.54 | 0 | 101.62 | 2139.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19694681200 |  | 100467287 |  | W90528 |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | TIVERTON | 101 E TIVERTON WY | 067 | LEX | 2019-04-04 | JENSMIN | U130193 | 2019-04-04 | 2019-04-04 |  |  | JENSMIN | 2019-04-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.5667 | 1 | 4225.66 | 270.75 | 114.15 | 150.93 | 3689.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11926473800 |  | 500768836 |  | 6716212J | 0146400 |  |  | 566 | EX | ABANDON SL/IDLE 48MTHS 09/2011 | 2600B | RED MILE | 979 RED MILE RD | 067 | LEX | 2019-04-11 | U125208 | U125208 | 2011-09-27 | 2019-04-05 |  |  | DBANKS | 2019-04-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.3833 | 1 | 735.32 | 77.44 | 13.56 | 4.42 | 639.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 17026728401 |  |  |  | 7352256G | 1747947 | U122858 |  | 557 | EX | INSTALL 3209' - 4"/2" PMLP | 2600B | COGAN | COGAN ST | 019 | ASH | 2019-05-13 | U123258 | U122858 | 2019-03-05 | 2019-02-07 | 2019-06-01 | 2018-12-18 | ROCKIE MULLINS | 2019-04-05 | 2018-08-20 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP7284 | AMRCB |  | 100 | 055732170267284 | 740.6167 | 492178 | 516625.22 | 53791 | 42704.68 | 15363.66 | 333159 | 0 | 2845.44 | 68761.44 | 4171
KY | KY - EAST | 2631 | 17026728500 |  |  |  | 7352256G | 1747947 | U127466 |  | 558 | EX | RETIRE 2558' - BS/CS/PLP | 2600B | COGAN | COGAN ST | 019 | ASH | 2019-05-13 | U123258 | U127466 | 2017-09-22 | 2019-05-31 | 2019-06-01 | 2019-04-02 | ROCKIE MULLINS | 2019-04-05 | 2018-10-23 | 2018-10-23 | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP7285 | AMRCB |  | 100 | 055832170267285 | 0.2 | 0 | 146.09 | 10.31 | 0 | 3.58 | 132.2 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18650073200 |  | 100345571 |  | 6696212L | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | HENTON | 225 HENTON CT | 239 | VER | 2019-04-05 | CDESPAI | AOC SYST | 2018-10-10 | 2018-10-10 | 2021-09-24 |  | CDESPAI | 2019-04-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.2333 | 1 | 2261.34 | 130.96 | 298.49 | 240.58 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18651244400 |  | 100293906 |  | 6720212A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BROADWAY | 805 N BROADWAY ST | 067 | LEX | 2019-06-12 | U125208 | U125208 | 2018-10-17 |  |  |  | RVANDER | 2019-04-05 | 2019-01-17 | 2019-01-17 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.5833 | 6 | 9923.6 | 1085.45 | 0 | 563.83 | 8274.32 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19026852100 |  |  |  | 7348248F | 1860094 | GSULLI1 |  | 909 | EX | UPGRADE COMM EQUIPMENT | 2631M | US 60 | US 60 | 019 | CAN | 2019-04-09 | U462463 | GSULLI1 | 2019-01-04 | 2019-12-30 | 2019-12-31 | 2019-04-05 | CYNTHIA FARIS | 2019-04-05 |  |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP8521 |  |  | 100 | 090932190268521 | 5.6167 | 0 | 2612.52 | 392.63 | 1590 | 96.35 | 510 | 0 | 23.54 | 0
KY | KY - WEST | 2621 | 19026878800 |  |  |  | 6732196N | 1964100 | U122858 |  | 583 | EX | INSTALL REGULATION | 2600E | DURBIN | 8721 DURBIN LN | 067 | LEX | 2019-06-03 | U462463 | U122858 | 2019-05-24 | 2019-05-30 | 2019-05-30 | 2019-04-05 | JAMES KEESEE | 2019-04-05 |  |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00583 | 3200583 |  |  | WP8788 |  |  | 100 | 058332190268788 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026878900 |  |  |  | 6732196N | 1964100 | U122858 |  | 584 | EX | RETIRE REGULATOR | 2600E | DURBIN | 8721 DURBIN LN | 067 | LEX | 2019-06-06 | U462463 | U122858 | 2019-05-24 | 2019-05-30 | 2019-05-30 | 2019-04-05 | JAMES KEESEE | 2019-04-05 |  |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00584 | 3200584 |  |  | WP8789 |  |  | 100 | 058432190268789 | 3 | 0 | 264.25 | 209.61 | 0 | 54.64 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19679376900 |  | 100465485 |  | 6720216P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D107476 | 2621P | TANGLEWOOD | 17 TANGLEWOOD DR | 067 | LEX | 2019-04-10 | U125208 | U125208 | 2019-02-05 | 2019-08-01 | 2021-02-28 |  | DBANKS | 2019-04-05 | 2019-04-02 | 2019-04-02 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.4833 | 2 | 3429.45 | 357.86 | 168.52 | 20.39 | 2882.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19689859300 |  | 100337418 |  | 6720212F |  |  |  | 566 | EX | DEMO / ABANDON W/568-570+ | 2621P | 6TH | 406 E 6TH ST | 067 | LEX | 2019-04-10 | U125208 | U132002 | 2019-03-20 | 2019-04-30 | 2019-05-21 |  | LCLARK | 2019-04-05 | 2019-04-02 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.45 | 5 | 544.55 | 515.2 | 0 | 29.35 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19689895900 |  | 100337417 |  | 6720212F |  |  |  | 566 | EX | ABANDON W/100337418* | 2621P | CHESTNUT | 568 CHESTNUT ST | 067 | LEX | 2019-04-05 | LCLARK | U125208 | 2019-03-20 | 2019-04-18 |  |  | LCLARK | 2019-04-05 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.1 | 0 | 464.44 | 164.72 | 0 | 9.38 | 290.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19689896400 |  | 100337416 |  | 6720212F |  |  |  | 566 | EX | ABANDON W/100337418* | 2621P | CHESTNUT | 570 CHESTNUT ST | 067 | LEX | 2019-04-05 | LCLARK | U125208 | 2019-03-20 | 2019-04-18 |  |  | LCLARK | 2019-04-05 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.1 | 2 | 174.1 | 164.72 | 0 | 9.38 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19695064800 |  | 100287048 |  | 6720212F |  |  |  | 565 | EX | GRADE 1 LEAK D221501 | 2621P | HIGHLAND PARK | 914 HIGHLAND PARK DR | 067 | LEX | 2019-04-10 | U125208 | U131169 | 2019-04-05 | 2019-04-05 | 2019-04-05 |  | KKINDER | 2019-04-05 | 2019-04-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.0167 | 3 | 1371.93 | 1077.47 | 233.14 | 61.32 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19695075600 |  | 100303974 |  | 6712208C |  |  |  | 566 | EX | ABANDON SERVICE | 2621P | JASMINE | 2204 JASMINE DR | 067 | LEX | 2019-04-25 | U125208 | U131169 | 2019-04-05 | 2019-04-05 |  |  | DBANKS | 2019-04-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.5167 | 1 | 792.16 | 83.55 | 63.95 | 4.76 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19695376600 |  | 500764490 |  | 6716212J | 0146400 |  |  | 566 | EX | ABANDON SL | 2600B | RED MILE | 983 RED MILE RD | 067 | LEX | 2019-04-11 | U125208 | U131066 | 2019-04-08 | 2019-12-31 |  |  | DBANKS | 2019-04-05 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2623 | 18604560500 |  | 100273078 |  | 6680224D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | WOODHILL | 248 WOODHILL LN | 073 | FRA | 2019-04-08 | CDESPAI | AOC SYST | 2018-04-19 | 2018-04-19 | 2021-04-03 |  | CDESPAI | 2019-04-08 | 2019-04-05 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.0333 | 6 | 2748.64 | 279.8 | 347.93 | 49.24 | 2071.67 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026850701 |  | 501231983 |  | 6728208A | 1960362 | U461383 |  | 555 | EX | INSTALL 675' OF 2"PMMP MAIN | 2600B | CHERRY MEADOW | 3121 CHERRY MEADOW PA | 067 | LEX | 2019-05-02 | U123258 | U461383 | 2019-03-28 | 2019-04-01 | 2019-04-12 | 2019-04-09 | JAMIE LYNN | 2019-04-08 | 2019-04-04 | 2019-04-04 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP8507 |  |  | 100 | 055532190268507 | 77.55 | 8697 | 83893.15 | 4078.61 | 1530.22 | 1299.95 | 66245.7 | 0 | 189.79 | 10548.88 | 669
KY | KY - CENTRAL | 2632 | 19671927700 |  | 100353708 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 111 W 2ND ST | 161 | MAY | 2019-05-09 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-04-08 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1520.3 | 0 | 0 | 0 | 1520.3 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671928000 |  | 100353711 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 117 W 2ND ST | 161 | MAY | 2019-05-09 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-04-08 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1568.21 | 0 | 0 | 0 | 1568.21 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671928200 |  | 100420212 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 123 W 2ND ST | 161 | MAY | 2019-05-09 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-04-08 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1562.66 | 0 | 0 | 0 | 1562.66 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671929100 |  | 100353733 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 145 W 2ND ST | 161 | MAY | 2019-05-10 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-04-08 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1609.34 | 0 | 0 | 0 | 1609.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680073700 |  | 100320135 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | TAHOMA | 212 TAHOMA RD | 067 | LEX | 2019-04-08 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-04-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.6667 | 1 | 2486.54 | 216.71 | 0 | 60.74 | 2209.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680076700 |  | 100320044 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | VALLEY | 166 VALLEY RD | 067 | LEX | 2019-04-08 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-04-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1841.19 | 0 | 0 | 0 | 1841.19 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19689397000 |  | 100291007 |  | 6720212A |  |  |  | 566 | EX | DEMO / ABANDON / RI 03-25-19 | 2621P | FLORIDA | 778 FLORIDA ST 1FR | 067 | LEX | 2019-04-08 | LMCDONA | U132002 | 2019-03-19 | 2019-04-18 | 2019-04-19 |  | LMCDONA | 2019-04-08 | 2019-04-02 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 22.95 | 4 | 1350.91 | 1184.75 | 8.98 | 157.18 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 09766022700 |  | 100333271 | 08 | V-1021-50 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | CONSTITUTION | 118 CONSTITUTION ST | 067 | LEX | 2019-04-09 | JENSMIN | MPILON | 2009-01-02 | 2014-12-23 |  |  | JENSMIN | 2019-04-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.91667 | 1 | 1733.52 | 54.03 | 88.51 | 42.14 | 1548.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 17531037000 |  | 100274016 |  | 6684228N | 1638340 |  |  | 565 | EX | SL PITTED-MNFLD : REPL SL | 2621P | WOODLAND | 728 WOODLAND AV | 073 | FRA | 2019-04-09 | CDESPAI | U125208 | 2017-08-04 | 2017-12-29 |  |  | CDESPAI | 2019-04-09 | 2019-03-26 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.95 | 2 | 4746.44 | 347.78 | 403.3 | 394.76 | 3600.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18636018200 |  | 100333119 |  | 6720212I | 1855043 |  |  | 566 | EX | II - ABANDON ON SOII | 2621P | CORRAL | 326 CORRAL ST | 067 | LEX | 2019-04-25 | U125208 | U126129 | 2018-08-17 | 2019-04-09 |  |  | JENSMIN | 2019-04-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.8167 | 1 | 886.08 | 108.65 | 52.85 | 84.68 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19026851100 |  |  |  | 6712228J | 1860094 | GSULLI1 |  | 909 | EX | UPGRADE COMMUNICATION EQUIP | 2600E | SHOWALTER | SHOWALTER DR | 209 | GEO | 2019-04-09 | U462463 | GSULLI1 | 2019-01-04 | 2019-12-30 | 2019-12-31 | 2019-02-19 | CYNTHIA FARIS | 2019-04-09 | 2019-02-19 | 2019-02-19 | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00909 | 3200909 |  |  | WP8511 |  |  | 100 | 090932190268511 | 2 | 0 | 5532.32 | 123.03 | 4664 | 37.81 | 680 | 0 | 27.48 | 0
KY | KY - CENTRAL | 2629 | 19026852300 |  |  |  | 7348204H | 1860094 | GSULLI1 |  | 909 | EX | UPGRADE COMM EQUIPMENT | 2600E | STATE RT 89 | STATE RT 89 | 049 | WIN | 2019-04-11 | U462463 | GSULLI1 | 2019-01-04 | 2019-12-30 | 2019-12-31 | 2019-02-11 | CYNTHIA FARIS | 2019-04-09 |  |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00909 | 3200909 |  |  | WP8523 |  |  | 100 | 090932190268523 |  | 0 | 2154.22 | 0 | 1590 | 0 | 554.96 | 0 | 9.26 | 0
KY | KY - CENTRAL | 2629 | 19026852400 |  |  |  | 6748204H | 1860094 | GSULLI1 |  | 910 | EX | RETIRE 2G/3G EQUIPMENT | 2600E | STATE RT 89 | STATE RT 89 | 049 | WIN | 2019-04-11 | U462463 | GSULLI1 | 2019-01-04 | 2019-12-31 | 2019-12-31 | 2019-02-11 | CYNTHIA FARIS | 2019-04-09 |  |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00910 | 3200910 |  |  | WP8524 |  |  | 100 | 091032190268524 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026852500 |  |  |  | 6720216N | 1860094 | GSULLI1 |  | 909 | EX | UPGRADE COMM EQUIPMENT | 2600E | RUSSELL CAVE | 1511 RUSSELL CAVE RD | 067 | LEX | 2019-04-11 | U462463 | GSULLI1 | 2019-01-04 | 2019-12-30 | 2019-12-31 | 2019-03-21 | CYNTHIA FARIS | 2019-04-09 | 2019-03-21 | 2019-03-21 | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP8525 |  |  | 100 | 090932190268525 | 13.0333 | 0 | 6356.49 | 751.17 | 4664 | 44.49 | 850 | 0 | 46.83 | 0
KY | KY - CENTRAL | 2629 | 19026853000 |  |  |  | 7244216D | 1860094 | GSULLI1 |  | 909 | EX | UPGRADE COMM EQUIPMENT | 2600E | STEPSTONE | STEPSTONE RD | 173 | MT | 2019-04-11 | U462463 | GSULLI1 | 2019-01-04 | 2019-12-30 | 2019-12-31 | 2019-02-07 | CYNTHIA FARIS | 2019-04-09 |  |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00909 | 3200909 |  |  | WP8530 |  |  | 100 | 090932190268530 |  | 0 | 2449.26 | 0 | 1590 | 0 | 850 | 0 | 9.26 | 0
KY | KY - CENTRAL | 2629 | 19026853100 |  |  |  | 7244216D | 1860094 | GSULLI1 |  | 910 | EX | RETIRE 2G/3G EQUIPMENT | 2600E | STEPSTONE | STEPSTONE RD | 173 | MT | 2019-04-11 | U462463 | GSULLI1 | 2019-01-04 | 2019-12-31 | 2019-12-31 | 2019-02-07 | CYNTHIA FARIS | 2019-04-09 |  |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00910 | 3200910 |  |  | WP8531 |  |  | 100 | 091032190268531 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19026853200 |  |  |  | 6684228O | 1860094 | GSULLI1 |  | 909 | EX | UPGRADE COMM EQUIPMENT | 2600E | TODD | E TODD ST | 073 | FRA | 2019-04-09 | U462463 | GSULLI1 | 2019-01-04 | 2019-12-30 | 2019-12-31 | 2019-03-22 | CYNTHIA FARIS | 2019-04-09 | 2019-03-22 | 2019-03-22 | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00909 | 3200909 |  |  | WP8532 |  |  | 100 | 090932190268532 | 1.3167 | 0 | 3164.91 | 81.21 | 2544 | 4.82 | 510 | 0 | 24.88 | 0
KY | KY - WEST | 2623 | 19026853400 |  |  |  | 6684228M | 1860094 | GSULLI1 |  | 909 | EX | UPGRADE COMM EQUIPMENT | 2600E | LOUISVILLE | LOUISVILLE RD | 073 | FRA | 2019-04-09 | U462463 | GSULLI1 | 2019-01-04 | 2019-12-30 | 2019-12-31 | 2019-03-27 | CYNTHIA FARIS | 2019-04-09 | 2019-03-27 | 2019-03-27 | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00909 | 3200909 |  |  | WP8534 |  |  | 100 | 090932190268534 | 5.7667 | 0 | 5934.04 | 359.75 | 4664 | 100.01 | 765 | 0 | 45.28 | 0
KY | KY - WEST | 2623 | 19026853600 |  |  |  | 6712236G | 1860094 | GSULLI1 |  | 909 | EX | UPGRADE COMM EQUIPMENT | 2600E | DELAPLANE | DELAPLANE RD | 209 | GEO | 2019-04-09 | U462463 | GSULLI1 | 2019-01-04 | 2019-12-30 | 2019-12-31 | 2019-01-30 | CYNTHIA FARIS | 2019-04-09 |  |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00909 | 3200909 |  |  | WP8536 |  |  | 100 | 090932190268536 |  | 0 | 2273.08 | 0 | 1590 | 0 | 680 | 0 | 3.08 | 0
KY | KY - WEST | 2623 | 19026853700 |  |  |  | 6712236G | 1860094 | GSULLI1 |  | 910 | EX | RETIRE 2G/3G EQUIPMENT | 2600E | DELAPLANE | DELAPLANE RD | 209 | GEO | 2019-04-09 | U462463 | GSULLI1 | 2019-01-04 | 2019-12-31 | 2019-12-31 | 2019-01-30 | CYNTHIA FARIS | 2019-04-09 |  |  | F | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00910 | 3200910 |  |  | WP8537 |  |  | 100 | 091032190268537 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026854200 |  |  |  | 6716220O | 1860094 | GSULLI1 |  | 909 | EX | UPGRADE COMM EQUIPMENT | 2600E | PRESS | PRESS AV | 067 | LEX | 2019-04-11 | U462463 | GSULLI1 | 2019-01-04 | 2019-12-30 | 2019-12-31 | 2019-03-26 | CYNTHIA FARIS | 2019-04-09 | 2019-03-26 | 2019-03-26 | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP8542 |  |  | 100 | 090932190268542 | 3.9833 | 0 | 5698.67 | 254.21 | 4664 | 55.18 | 680 | 0 | 45.28 | 0
KY | KY - WEST | 2623 | 19026854600 |  |  |  | 6684228C | 1860094 | GSULLI1 |  | 909 | EX | UPGRADE COMM EQUIPMENT | 2600E | US 460 - GEORGETOWN RD | US 460 - GEORGETOWN RD | 073 | FRA | 2019-04-09 | U462463 | GSULLI1 | 2019-01-04 | 2019-12-30 | 2019-12-31 | 2019-01-29 | CYNTHIA FARIS | 2019-04-09 |  |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00909 | 3200909 |  |  | WP8546 |  |  | 100 | 090932190268546 |  | 0 | 2953.08 | 0 | 1590 | 0 | 1360 | 0 | 3.08 | 0
KY | KY - WEST | 2621 | 19026869800 |  |  |  | 6716212O | 1860094 | U461383 |  | 909 | EX | UPGRADE COMM EQUIPMENT | 2600E | PRESS | PRESS AV | 067 | LEX | 2019-04-11 | U462463 | U461383 | 2019-04-08 | 2019-10-01 | 2019-10-01 | 2019-04-09 | CYNTHIA FARIS | 2019-04-09 |  |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP8698 |  |  | 100 | 090932190268698 | 5.1333 | 0 | 2549.5 | 477.72 | 1590 | 124.39 | 340 | 0 | 17.39 | 0
KY | KY - CENTRAL | 2632 | 19671927000 |  | 100353696 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 51 W 2ND ST | 161 | MAY | 2019-05-09 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-04-09 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1528.8 | 0 | 0 | 0 | 1528.8 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671941900 |  | 100353693 |  | 7256280L | 1747939 |  |  | 565 | EX | REPLACE SL W/17026728200 | 2600B | 2ND | 45 W 2ND ST | 161 | MAY | 2019-05-09 | U461478 | U131066 | 2019-01-22 | 2019-12-31 |  |  | DAVID STAGGS | 2019-04-09 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1525.06 | 0 | 0 | 0 | 1525.06 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680089600 |  | 100320045 |  | 6716208K | 1748686 |  |  | 565 | EX | REPLACE SL W/17026736100 | 2600B | VALLEY | 172 VALLEY RD | 067 | LEX | 2019-04-09 | U461516 | U131066 | 2019-02-07 | 2019-12-31 |  |  | NEALJOHNSON | 2019-04-09 |  | 2019-04-09 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.0333 | 1 | 2457.96 | 225.26 | 0 | 66.11 | 2166.59 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19682829500 |  | 100304589 |  | 6712212P | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER / | 2621D | NORMANDY | 1805 NORMANDY RD | 067 | LEX | 2019-04-09 | DBANKS | AOC SYST | 2019-02-21 | 2019-04-22 | 2019-04-22 |  | DBANKS | 2019-04-09 | 2019-04-08 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.5 | 6 | 2750.72 | 276.76 | 207.8 | 17.13 | 2249.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19692440200 |  | 100310379 |  | 6716208A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER / | 2621D | MITCHELL | 644 MITCHELL AV | 067 | LEX | 2019-04-15 | U125208 | AOC SYST | 2019-03-29 | 2019-04-26 | 2019-05-27 |  | RVANDER | 2019-04-09 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 36.0167 | 6 | 1962.72 | 1712.35 | 152.9 | 97.47 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19692577800 |  | 100310345 |  | 6716208A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CLAYS MILL | 1919 CLAYS MILL RD | 067 | LEX | 2019-04-11 | U125208 | U125208 | 2019-04-01 | 2019-04-01 | 2019-04-19 |  | TGNELSO | 2019-04-09 | 2019-04-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 38.8167 | 5 | 2034.87 | 1849.89 | 79.6 | 105.38 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19695774300 |  | 100310496 |  | 6712208L |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | NAKOMI | 623 NAKOMI DR | 067 | LEX | 2019-04-11 | U125208 | U130193 | 2019-04-09 | 2019-04-09 | 2019-04-09 |  | KKINDER | 2019-04-09 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.5167 | 4 | 1541.89 | 1203.95 | 269.35 | 68.59 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12968023200 |  | 100340984 |  | 7240212B |  |  |  | 566 | EX | SOII - ABANDON METER ONLY | 2621P | MAIN | 34 E MAIN ST | 173 | MT | 2019-04-10 | DENNING | U124967 | 2012-05-02 | 2014-12-31 |  |  | DENNING | 2019-04-10 |  |  | D | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.5667 | 2 | 328.11 | 253.54 | 0 | 74.57 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12968024500 |  | 100343459 |  | 7240212B |  |  |  | 566 | EX | SOII - ABANDON METER ONLY | 2621P | BANK | 27 S BANK ST | 173 | MT | 2019-04-10 | DENNING | U124967 | 2012-05-02 | 2014-12-31 |  |  | DENNING | 2019-04-10 |  |  | D | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.6667 | 2 | 407.33 | 314.78 | 0 | 92.55 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 13117526700 |  | 100445506 |  | 6680228K |  |  |  | 566 | EX | ABANDON W/LCB: IDLE | 2621P | MILLIE | 601 MILLIE DR | 073 | FRA | 2019-04-10 | MCRAIG | U908786 | 2013-02-11 | 2019-04-26 |  |  | MCRAIG | 2019-04-10 | 2019-03-12 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 22.4 | 9 | 1768.16 | 1081.64 | 0 | 686.52 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 13170665900 |  | 100344689 |  | 6700224O |  |  |  | 566 | EX | ABN SERV LINE /IDLE | 2621P | WINTER | 222 S WINTER ST | 239 | MID | 2019-04-10 | MCRAIG | DMCCULL | 2013-10-25 | 2019-04-26 |  |  | MCRAIG | 2019-04-10 | 2019-03-21 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 11.5167 | 7 | 939.15 | 601.94 | 0 | 34.14 | 303.07 | 0 | 0 | 0
KY | KY - WEST | 2623 | 17501893100 |  | 100276287 | 46 | 6684228G | 1638340 |  |  | 565 | EX | REPLACE SL - MOVE METER : CORR | 2621P | ADAIR | 106 ADAIR ST | 073 | FRA | 2019-04-10 | CDESPAI | RVANDER | 2017-04-28 | 2017-12-29 |  |  | CDESPAI | 2019-04-10 | 2019-04-08 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.7833 | 2 | 2515.96 | 220.4 | 310.37 | 236.57 | 1748.62 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18026783401 |  | 501245278 |  | 6716232B | 1854058 | U128885 |  | 555 | EX | INSTALL 5,400' - 2"/4" PMMP | 2600B | HERNDON | HERNDON BV LT115C | 209 | GEO | 2019-04-26 | U123258 | U128885 | 2019-04-10 | 2019-02-19 | 2019-05-17 | 2019-04-09 | JDUNN | 2019-04-10 | 2019-01-09 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP7834 |  |  | 100 | 055532180267834 | 490.7833 | 329973 | 250762.09 | 27853.06 | 13485.86 | 3964.85 | 172145.88 | 0 | 1806.83 | 31505.61 | 5789
KY | KY - WEST | 2621 | 18026784001 |  |  |  | 6716212H | 1853770 | U122858 |  | 561 | EX | INSTALL 1385'-6" PMMP | 2600B | JEFFERSON | JEFFERSON ST | 067 | LEX | 2019-06-24 | U123258 | U122858 | 2019-04-09 | 2019-02-19 | 2019-04-30 | 2019-04-10 | LARRY BROWN | 2019-04-10 | 2019-04-09 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP7840 |  |  | 100 | 056132180267840 | 561.1333 | 116724 | 427330.33 | 39658.13 | 46673.42 | 9067.38 | 277481.18 | 0 | 1931.74 | 52518.48 | 1644
KY | KY - WEST | 2621 | 18651132600 |  | 100302941 |  | 6712212N | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | ATHENIA | 1155 ATHENIA DR | 067 | LEX | 2019-04-10 | DBANKS | AOC SYST | 2018-10-16 | 2019-12-31 | 2019-12-31 |  | DBANKS | 2019-04-10 | 2019-04-08 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.0833 | 2 | 4062.79 | 394.34 | 220.29 | 38.97 | 3409.19 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18651233800 |  | 100273963 |  | 6684228I |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LEE | 112 LEE DR | 073 | FRA | 2019-04-11 | U125208 | U125208 | 2018-10-17 | 2019-04-11 | 2020-10-31 |  | CDESPAI | 2019-04-10 | 2019-04-09 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 12.9833 | 3 | 4590.79 | 753.1 | 301.42 | 707.24 | 2829.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18657398000 |  | 100337073 |  | 6720212I | 1855043 |  |  | 566 | EX | II- CO SOII OR ABANDON | 2621P | CHESTNUT | 400 CHESTNUT ST | 067 | LEX | 2019-04-26 | U125208 | U126926 | 2018-11-15 | 2019-03-15 |  |  | JENSMIN | 2019-04-10 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.35 | 1 | 756.44 | 46.04 | 52.85 | 17.65 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026858300 |  | 501257798 |  | 6716216A | 1960987 | U461383 |  | 555 | EX | INSTALL 3100' OF 2"PMMP MAIN | 2600B | HALFORD | 760 HALFORD PL LT | 067 | LEX | 2019-04-18 | U123258 | U461383 | 2019-01-29 | 2019-04-02 | 2019-04-26 | 2019-04-09 | WGRAVES | 2019-04-10 | 2019-03-21 | 2019-03-21 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP8583 |  |  | 100 | 055532190268583 | 99.7667 | 51675 | 58970.19 | 5355.35 | 4433.3 | 1509.16 | 40059.34 | 0 | 178.79 | 7434.25 | 3445
KY | KY - CENTRAL | 2632 | 19666814700 |  | 100356672 |  | 7260280M | 1748617 |  |  | 565 | EX | RPLC SL/17026734200/ | 2600B | LEXINGTON | 484 LEXINGTON ST | 161 | MAY | 2019-04-24 | U461478 | U131066 | 2019-01-07 | 2019-11-27 |  |  | DAVID STAGGS | 2019-04-10 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 7140.29 | 0 | 0 | 0 | 7140.29 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671926200 |  | 100353687 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 37 W 2ND ST | 161 | MAY | 2019-05-07 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-04-10 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1408.06 | 0 | 0 | 0 | 1408.06 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671926500 |  | 100353690 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 41 W 2ND ST | 161 | MAY | 2019-04-29 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-04-10 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1557.69 | 0 | 0 | 0 | 1557.69 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671926900 |  | 100353695 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 49 W 2ND ST | 161 | MAY | 2019-05-08 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-04-10 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1525.06 | 0 | 0 | 0 | 1525.06 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671927100 |  | 100353774 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 52 W 2ND ST | 161 | MAY | 2019-05-07 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-04-10 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1409.08 | 0 | 0 | 0 | 1409.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680076800 |  | 100320043 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | VALLEY | 175 VALLEY RD | 067 | LEX | 2019-04-10 | U461516 | U131066 | 2019-02-07 | 2019-11-27 |  |  | NEAL JOHNSON | 2019-04-10 |  | 2019-04-10 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.45 | 1 | 2663.19 | 248.11 | 0 | 72.84 | 2342.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680089800 |  | 100320042 |  | 6716208K | 1748686 |  |  | 565 | EX | REPLACE SL W/17026736100 | 2600B | VALLEY | 179 VALLEY RD | 067 | LEX | 2019-04-10 | U461516 | U131066 | 2019-02-07 | 2019-12-31 |  |  | NEAL JOHNSON | 2019-04-10 |  | 2019-04-10 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.3 | 2 | 2266.15 | 17.89 | 0 | 5.25 | 2243.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19695801700 |  | 100295797 |  | 6716216G |  |  |  | 565 | EX | GRADE 1 LEAK | 2621P | ALICE | 1959 ALICE DR | 067 | LEX | 2019-04-12 | U126308 | U131168 | 2019-04-09 | 2019-04-09 | 2019-04-09 |  | JENSMIN | 2019-04-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.75 | 4 | 2654.71 | 1029.29 | 116.6 | 136.28 | 1372.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19696071900 |  | 500021318 |  | 6720204M |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | SPRING CREEK | 4601 SPRING CREEK DR | 067 | LEX | 2019-04-11 | U125208 | U130193 | 2019-04-10 | 2019-04-10 |  |  | KKINDER | 2019-04-10 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.2333 | 3 | 764.38 | 568.89 | 163.1 | 32.39 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 04576157800 |  | 100305791 |  | 6712212O |  |  |  | 566 | EX | ABANDON SERVICE AT #1#8 | 2600B | MAYWICK VIEW | 1657 MAYWICK VIEW LN 1 | 067 | LEX | 2019-04-16 | U125208 | SSUTHER | 2004-05-26 | 2020-12-31 |  |  | TNEAL | 2019-04-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.6667 | 2 | 564.49 | 411.45 | 51.52 | 101.52 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 06646075000 |  | 100305785 |  | 6712212O | 1315787 |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | MAYWICK VIEW | 1657 MAYWICK VIEW LN 6 | 067 | LEX | 2019-04-12 | U125208 | SSUTHER | 2006-04-27 | 2019-04-01 |  |  | TNEAL | 2019-04-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.21667 | 1 | 11.27 | 10.66 | 0 | 0.61 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12992513100 |  | 100305789 |  | 6712212O |  |  |  | 566 | EX | REMOVE MTR / ABN / CONDEMNED | 2621P | MAYWICK VIEW | 1657 MAYWICK VIEW LN 7 | 067 | LEX | 2019-04-11 | TNEAL | U125201 | 2012-10-10 | 2019-04-01 |  |  | TNEAL | 2019-04-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.05 | 1 | 273.59 | 258.85 | 0 | 14.74 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12992513600 |  | 100305783 |  | 6712212O |  |  |  | 566 | EX | ABANDON / RI 10-03-2007 | 2621P | MAYWICK VIEW | 1657 MAYWICK VIEW LN 2 | 067 | LEX | 2019-04-11 | TNEAL | U125201 | 2012-10-10 | 2019-05-01 |  |  | TNEAL | 2019-04-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.05 | 1 | 2.68 | 2.54 | 0 | 0.14 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12992513700 |  | 100305784 |  | 6712212O |  |  |  | 566 | EX | ABANDON / RI 03-27-2008 | 2621P | MAYWICK VIEW | 1657 MAYWICK VIEW LN 4 | 067 | LEX | 2019-04-11 | TNEAL | U125201 | 2012-10-10 | 2020-12-31 |  |  | TNEAL | 2019-04-11 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.25 | 1 | 12.33 | 11.66 | 0 | 0.67 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18026783800 |  |  |  | 6716212H | 1853770 | U122858 |  | 561 | EX | INSTALL 320'-8" PMLP | 2600B | JEFFERSON | JEFFERSON ST | 067 | LEX | 2019-06-24 | U123258 | U122858 | 2018-07-13 | 2019-04-02 | 2019-04-30 | 2019-04-11 | LARRY BROWN | 2019-04-11 | 2019-02-14 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP7838 |  |  | 100 | 056132180267838 | 64.0667 | 2560 | 231561.52 | 4057.58 | 14688.01 | 1141.74 | 181697.15 | 0 | 0 | 29977.04 | 320
KY | KY - WEST | 2621 | 18026783900 |  |  |  | 6716212H | 1853770 | U122858 |  | 562 | EX | RETIRE 525'-8" CSLP | 2600B | JEFFERSON | JEFFERSON ST | 067 | LEX | 2019-06-12 | U123258 | U122858 | 2018-07-13 | 2019-04-30 | 2019-04-30 | 2019-04-11 | LARRY BROWN | 2019-04-11 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP7839 |  |  | 100 | 056232180267839 |  | 0 | 132.2 | 0 | 0 | 0 | 132.2 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18650649700 |  | 100274000 |  | 6684224A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | LOUISVILLE | 960 LOUISVILLE RD | 073 | FRA | 2019-04-11 | CDESPAI | AOC SYST | 2018-10-12 | 2018-10-12 | 2021-09-26 |  | CDESPAI | 2019-04-11 | 2019-03-25 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 18.6167 | 3 | 8245.92 | 1085.44 | 272.95 | 1258.07 | 5629.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18651130300 |  | 100302942 |  | 6712212N | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | ATHENIA | 1159 ATHENIA DR | 067 | LEX | 2019-04-11 | DBANKS | AOC SYST | 2018-10-16 | 2019-12-31 | 2019-12-31 |  | DBANKS | 2019-04-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.9 | 1 | 1988.78 | 169.8 | 218.01 | 9.66 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18660706700 |  | 100306412 |  | 6716212M | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER / | 2621D | LAUREL HILL | 876 LAUREL HILL RD | 067 | LEX | 2019-04-11 | DBANKS | AOC SYST | 2018-12-05 | 2019-02-02 | 2019-02-02 |  | DBANKS | 2019-04-11 | 2019-04-08 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.9333 | 2 | 2147.39 | 216.8 | 167.24 | 14.73 | 1748.62 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671925900 |  | 100353810 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 28 W 2ND ST | 161 | MAY | 2019-05-08 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-04-11 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1250.51 | 0 | 0 | 0 | 1250.51 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671926400 |  | 100353688 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 39 W 2ND ST | 161 | MAY | 2019-05-08 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-04-11 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1483.49 | 0 | 0 | 0 | 1483.49 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678768700 |  | 100299368 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 205 BOILING SPRING DR | 067 | LEX | 2019-04-11 | U461467 | U131066 | 2019-02-01 | 2019-12-31 |  |  | D REFFETT | 2019-04-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.9167 | 1 | 1676.12 | 285.66 | 0 | 81.17 | 1309.29 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680076900 |  | 100320046 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | VALLEY | 176 VALLEY RD | 067 | LEX | 2019-04-11 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-04-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.0833 | 1 | 3284.27 | 182.46 | 0 | 51.16 | 3050.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19692587900 |  | 100305788 |  | 6712212O |  |  |  | 566 | EX | REMOVE MTR / ABN - CONDEMNED | 2621P | MAYWICK VIEW | 1657 MAYWICK VIEW LN 5 | 067 | LEX | 2019-04-11 | TNEAL | U125208 | 2019-04-01 | 2019-05-01 |  |  | TNEAL | 2019-04-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.21667 | 1 | 11.27 | 10.66 | 0 | 0.61 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19692588600 |  | 100305790 |  | 6712212O |  |  |  | 566 | EX | ABANDON / CONDEMNED | 2621P | MAYWICK VIEW | 1657 MAYWICK VIEW LN 3 | 067 | LEX | 2019-04-11 | TNEAL | U125208 | 2019-04-01 | 2019-04-01 |  |  | TNEAL | 2019-04-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.066667 | 1 | 3.22 | 3.05 | 0 | 0.17 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19692588700 |  | 100305787 |  | 6712212O |  |  |  | 566 | EX | ABANDON / CONDEMNED | 2621P | MAYWICK VIEW | 1657 MAYWICK VIEW LN 8 | 067 | LEX | 2019-04-11 | TNEAL | U125208 | 2019-04-01 | 2019-04-01 |  |  | TNEAL | 2019-04-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.88333 | 1 | 47.23 | 44.68 | 0 | 2.55 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19692591400 |  | 100305792 |  | 6712212O |  |  |  | 566 | EX | RMV METER / ABN / CONDEMNED | 2621P | MAYWICK VIEW | 1665 MAYWICK VIEW LN 1 | 067 | LEX | 2019-04-12 | U125208 | U125208 | 2019-04-01 | 2019-05-01 |  |  | LMCDONA | 2019-04-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.6333 | 2 | 715.79 | 636.78 | 42.72 | 36.29 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19692591500 |  | 100305793 |  | 6712212O |  |  |  | 566 | EX | RMV METER / ABN / CONDEMNED | 2621P | MAYWICK VIEW | 1665 MAYWICK VIEW LN 2 | 067 | LEX | 2019-04-11 | LMCDONA | U125208 | 2019-04-01 | 2019-05-01 |  |  | LMCDONA | 2019-04-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.2 | 2 | 10.65 | 10.08 | 0 | 0.57 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19692591700 |  | 100305795 |  | 6712212O |  |  |  | 566 | EX | RMV METER / ABN / CONDEMNED | 2621P | MAYWICK VIEW | 1665 MAYWICK VIEW LN 3 | 067 | LEX | 2019-04-11 | LMCDONA | U125208 | 2019-04-01 | 2019-05-01 |  |  | LMCDONA | 2019-04-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.2 | 2 | 10.65 | 10.08 | 0 | 0.57 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19692592100 |  | 100305797 |  | 6712212O |  |  |  | 566 | EX | RMV METER / ABN / CONDEMNED | 2621P | MAYWICK VIEW | 1665 MAYWICK VIEW LN 4 | 067 | LEX | 2019-04-11 | LMCDONA | U125208 | 2019-04-01 | 2019-05-01 |  |  | LMCDONA | 2019-04-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.26667 | 2 | 13.88 | 13.15 | 0 | 0.73 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19692592200 |  | 100305798 |  | 6712212O |  |  |  | 566 | EX | RMV METER / ABN / CONDEMNED | 2621P | MAYWICK VIEW | 1665 MAYWICK VIEW LN 5 | 067 | LEX | 2019-04-11 | LMCDONA | U125208 | 2019-04-01 | 2019-05-01 |  |  | LMCDONA | 2019-04-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.2 | 2 | 10.65 | 10.08 | 0 | 0.57 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19692592300 |  | 100305799 |  | 6712212O |  |  |  | 566 | EX | RMV METER / ABN / CONDEMNED | 2621P | MAYWICK VIEW | 1665 MAYWICK VIEW LN 6 | 067 | LEX | 2019-04-11 | LMCDONA | U125208 | 2019-04-01 | 2019-05-01 |  |  | LMCDONA | 2019-04-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.16667 | 2 | 8.52 | 8.06 | 0 | 0.46 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19692592600 |  | 100305801 |  | 6712212O |  |  |  | 566 | EX | RMV METER / ABN / CONDEMNED | 2621P | MAYWICK VIEW | 1665 MAYWICK VIEW LN 7 | 067 | LEX | 2019-04-11 | LMCDONA | U125208 | 2019-04-01 | 2019-05-01 |  |  | LMCDONA | 2019-04-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.2 | 2 | 10.65 | 10.08 | 0 | 0.57 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19692592800 |  | 100305802 |  | 6712212O |  |  |  | 566 | EX | RMV METER / ABN / CONDEMNED | 2621P | MAYWICK VIEW | 1665 MAYWICK VIEW LN 8 | 067 | LEX | 2019-04-11 | LMCDONA | U125208 | 2019-04-01 | 2019-05-01 |  |  | LMCDONA | 2019-04-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.1333 | 2 | 115.21 | 108.97 | 0 | 6.24 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19695430600 |  | 100308617 |  | 6716208A | 0571843 |  |  | 566 | EX | DEMO BLDG B - REMOVE METER | 2621P | HARRODSBURG | 1733 HARRODSBURG RD | 067 | LEX | 2019-04-25 | U125208 | U125208 | 2019-04-08 | 2049-12-31 |  |  | RVANDER | 2019-04-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.7167 | 2 | 504.88 | 477.66 | 0 | 27.22 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19696287600 |  | 100353778 |  | 7256280L | 1747939 |  |  | 565 | EX | REPLACE SL W/17026728200 | 2600B | 2ND | 46 W 2ND ST | 161 | MAY | 2019-05-10 | U461478 | U131066 | 2019-04-11 | 2019-12-31 |  |  | DAVID STAGGS | 2019-04-11 | 2019-04-15 |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 | 0.016667 | 1 | 1218.16 | 0.56 | 0 | 0.16 | 1217.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026867300 |  |  |  | 6716216O | 1962477 | U461383 |  | 557 | EX | INSTALL 40' OF 3"PMLP MAIN | 2621P | PRICE | 496 PRICE RD | 067 | LEX | 2019-05-29 | U123258 | U461383 | 2019-03-21 | 2020-09-08 | 2020-09-13 | 2019-03-21 | JENSMIN | 2019-04-12 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP8673 | AMRCB |  | 100 | 055732190268673 | 0.7 | 33 | 27361.96 | 4224.05 | 416.31 | 2037.23 | 17136.85 | 0 | 47.12 | 3500.4 | 33
KY | KY - WEST | 2621 | 19026867400 |  |  |  | 6716216O | 1962477 | U461383 |  | 558 | EX | RETIRE 40' OF 3"BSLP MAIN | 2621P | PRICE | 496 PRICE RD | 067 | LEX | 2019-05-29 | U123258 | U461383 | 2019-03-21 | 2020-09-11 | 2020-09-13 | 2019-03-21 | JENSMIN | 2019-04-12 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP8674 | AMRCB |  | 100 | 055832190268674 | 0.25 | 0 | 6132.21 | 397.66 | 0 | 280.99 | 5453.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671926800 |  | 100353694 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 47 W 2ND ST | 161 | MAY | 2019-05-08 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-04-12 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1519.51 | 0 | 0 | 0 | 1519.51 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671927500 |  | 100353754 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 102 W 2ND ST | 161 | MAY | 2019-05-10 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-04-12 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1257.43 | 0 | 0 | 0 | 1257.43 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680074000 |  | 100320164 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | TAHOMA | 215 TAHOMA RD | 067 | LEX | 2019-04-12 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-04-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.5333 | 1 | 2705.1 | 149.97 | 0 | 42.04 | 2513.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19689248900 |  | 100335035 |  | 6720212O | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER / | 2621D | WYATT | 1634 WYATT PY | 067 | LEX | 2019-04-12 | TGNELSO | AOC SYST | 2019-03-18 | 2019-04-15 | 2019-05-15 |  | TGNELSO | 2019-04-12 | 2019-04-12 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 37.1 | 5 | 2194.38 | 1692.57 | 212.91 | 96.42 | 192.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19696601800 |  | 100415039 |  | 6720216I |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | GRANT | 1498 GRANT DR | 067 | LEX | 2019-04-15 | U125208 | U131169 | 2019-04-12 | 2019-04-16 | 2020-10-31 |  | DBANKS | 2019-04-12 | 2018-10-25 | 2018-10-25 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.5833 | 7 | 4055.6 | 1006.19 | 164.94 | 58.16 | 2826.31 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19696602800 |  | 100279193 |  | 6688228F |  |  |  | 565 | EX | REPLACE SL MCRAIG | 2621P | ELKHORN | 150 ELKHORN CT | 073 | FRA | 2019-04-15 | U125208 | U125964 | 2019-04-12 | 2019-04-15 |  |  | MCRAIG | 2019-04-12 | 2019-04-12 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 42.2 | 4 | 2780.27 | 2002.86 | 663.31 | 114.1 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19696752600 |  | 500506986 |  | 7352256B |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | OLD BUCKLEY | 241 OLD BUCKLEY RD | 019 | ASH | 2019-04-12 | DESKAGG | U131367 | 2019-04-12 | 2019-04-12 |  |  | DESKAGG | 2019-04-12 | 2019-04-12 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 6.8167 | 3 | 597.04 | 377.89 | 11.19 | 207.96 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19696754300 |  | 100453439 |  | 6720208D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CREATIVE | 2040 CREATIVE DR 300-F | 067 | LEX | 2019-04-15 | U125208 | U131168 | 2019-04-12 | 2019-04-12 | 2019-04-12 |  | RVANDER | 2019-04-12 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 27.2 | 3 | 1374.11 | 1300.04 | 0 | 74.07 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 03528757200 |  | 100292178 |  | 6720216L | 1315787 |  |  | 566 | EX | ABN SERV LINE | 2621P | JUDY | 525 JUDY LN | 067 | LEX | 2019-04-16 | U125208 | DMCCULL | 2003-01-24 | 2019-04-16 |  |  | KKINDER | 2019-04-15 | 2019-03-25 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.0333 | 6 | 602.3 | 499.7 | 65.73 | 36.87 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 13121301200 |  | 100274422 | 57 | 6684228J |  |  |  | 565 | EX | REPL SERV W/415 CONWAY ST | 2621P | CONWAY | 413 CONWAY ST | 073 | FRA | 2019-04-16 | U125208 | RSTOKLE | 2013-03-01 | 2019-04-02 |  |  | BJLONE | 2019-04-15 | 2019-03-12 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 41.7667 | 11 | 2690.84 | 2213.01 | 351.38 | 126.45 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18026772800 |  | 501239819 |  | 6712208J | 1852798 | U461383 |  | 555 | EX | INSTALL 250' OF 2"PMMP | 2600B | CAVE HILL | 3525 CAVE HILL PL LT1 | 067 | LEX | 2019-04-26 | U124014 | U461383 | 2018-05-15 | 2019-05-01 | 2019-05-03 | 2019-04-15 | WGRAVES | 2019-04-15 | 2018-06-14 | 2018-06-14 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP7728 |  |  | 100 | 055532180267728 | 28.2167 | 1470 | 15452.23 | 1533.25 | 1011.72 | 338.79 | 10309.78 | 0 | 215.24 | 2043.45 | 245
KY | KY - WEST | 2621 | 18577388800 |  | 500260479 |  | 6716212G | 1746168 |  |  | 565 | EX | RPLC SL/17026714900/ | 2600B | MADISON | 300 MADISON PL A | 067 | LEX | 2019-04-15 | U461439 | U131066 | 2018-01-26 | 2019-12-31 |  |  | A PARRIS | 2019-04-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.3333 | 1 | 1841.13 | 302.82 | 0 | 87.65 | 1450.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18650072000 |  | 100303318 |  | 6712208C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | CAMELLIA | 1021 CAMELLIA DR | 067 | LEX | 2019-04-16 | U125208 | AOC SYST | 2018-10-10 | 2018-10-10 | 2021-09-24 |  | DBANKS | 2019-04-15 | 2019-04-12 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.85 | 2 | 1735.13 | 212.38 | 179.16 | 12.09 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18650076300 |  | 100303341 |  | 6712208D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | CAMELLIA | 1012 CAMELLIA DR | 067 | LEX | 2019-04-15 | DBANKS | AOC SYST | 2018-10-10 | 2018-10-10 | 2021-09-24 |  | DBANKS | 2019-04-15 | 2019-04-08 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.95 | 2 | 1935.33 | 107.3 | 223.88 | 12.84 | 1591.31 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671925400 |  | 100353814 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 20 W 2ND ST | 161 | MAY | 2019-05-03 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-04-15 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1198.55 | 0 | 0 | 0 | 1198.55 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671925500 |  | 100353813 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 22 W 2ND ST | 161 | MAY | 2019-05-03 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-04-15 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1252.13 | 0 | 0 | 0 | 1252.13 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671925700 |  | 100353812 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 24 W 2ND ST | 161 | MAY | 2019-05-03 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-04-15 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1189.26 | 0 | 0 | 0 | 1189.26 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671925800 |  | 100353811 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 26 W 2ND ST | 161 | MAY | 2019-04-30 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-04-15 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1249.06 | 0 | 0 | 0 | 1249.06 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678769000 |  | 100299270 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 212 BOILING SPRING DR | 067 | LEX | 2019-04-15 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-04-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1053.79 | 0 | 0 | 0 | 1053.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678769100 |  | 100299365 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 213 BOILING SPRING DR | 067 | LEX | 2019-04-15 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-04-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.3833 | 1 | 1711.71 | 196.26 | 0 | 6.23 | 1509.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678769500 |  | 100299363 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 221 BOILING SPRING DR | 067 | LEX | 2019-04-15 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-04-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.5667 | 1 | 1298.37 | 322.82 | 0 | 18.4 | 957.15 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680074300 |  | 100320137 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | TAHOMA | 220 TAHOMA RD | 067 | LEX | 2019-04-15 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-04-15 | 2019-04-15 | 2019-04-15 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.3833 | 1 | 2599.46 | 258.62 | 0 | 72.49 | 2268.35 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680077100 |  | 100320041 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | VALLEY | 183 VALLEY RD | 067 | LEX | 2019-04-15 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-04-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.0667 | 1 | 2505.06 | 63.21 | 0 | 17.71 | 2424.14 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19692724700 |  | 100241263 |  | 7356256G |  |  |  | 566 | EX | DEMO / ABANDON / RI 04/01/19 | 2621P | CARTER | 3100 CARTER AV | 019 | ASH | 2019-04-15 | MCOLLET | U132002 | 2019-04-01 | 2019-05-02 | 2019-05-02 |  | MCOLLET | 2019-04-15 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.7333 | 2 | 570.16 | 343.92 | 53.67 | 172.57 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19695075900 |  | 100429339 |  | 7352244J |  |  |  | 566 | EX | ABANDON / RI 04-08-19/ CONVRT | 2621P | BRIARWOOD | 4000 BRIARWOOD DR | 019 | CAT | 2019-04-15 | MCOLLET | U125208 | 2019-04-05 | 2019-05-03 |  |  | MCOLLET | 2019-04-15 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.6333 | 2 | 458 | 278.41 | 0 | 179.59 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19696007300 |  | 100435302 |  | 6748204J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MUDDY CREEK | 2440 MUDDY CREEK RD | 049 | WIN | 2019-04-16 | U125208 | U125208 | 2019-04-10 | 2019-04-05 | 2019-04-07 |  | DENNING | 2019-04-15 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 17 | 2 | 1507.51 | 945.15 | 284.3 | 278.06 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19697353500 |  | 100242917 |  | 7356256O |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | RUSSELL | 914 RUSSELL ST | 019 | ASH | 2019-04-15 | MCOLLET | U130193 | 2019-04-15 | 2019-04-15 | 2019-04-15 |  | MCOLLET | 2019-04-15 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 10.7333 | 2 | 1134.48 | 644.77 | 152.33 | 337.38 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11936467100 |  | 100330789 | 18 | V-1026 | 1855043 |  |  | 566 | EX | SOII - ABANDON / RI 12-07-2011 | 2621P | SHERMAN | 309 SHERMAN AV | 067 | LEX | 2019-04-16 | JENSMIN | SCHASTE | 2011-12-07 | 2019-04-15 |  |  | JENSMIN | 2019-04-16 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.75 | 1 | 728.17 | 44.54 | 18.91 | 24.82 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18601389500 |  | 100290486 |  | 6720216O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | WHISPERING WOO | 125 WHISPERING WOO LN | 067 | LEX | 2019-04-17 | U125208 | U125208 | 2018-04-09 | 2018-10-04 | 2020-04-30 |  | JENSMIN | 2019-04-16 | 2018-08-24 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 37.8833 | 11 | 12926.08 | 2205.37 | 249.71 | 3059.37 | 7411.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18613621500 |  | 100307396 |  | 6716212G | 1746168 |  |  | 565 | EX | REPLACE SL W/17026714900 | 2600B | HIGH | 722 W HIGH ST A-1F | 067 | LEX | 2019-04-16 | U461439 | U131066 | 2018-05-22 | 2019-12-31 |  |  | A PARRIS | 2019-04-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.7 | 1 | 2131.56 | 210.4 | 0 | 60.9 | 1860.26 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18636013900 |  | 100330684 |  | 6720208B | 1855043 |  |  | 566 | EX | II - ABANDON ON SOII | 2621P | SHERMAN | 128 SHERMAN AV | 067 | LEX | 2019-04-16 | JENSMIN | U126129 | 2018-08-17 | 2018-10-30 | 2018-10-30 |  | JENSMIN | 2019-04-16 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.45 | 1 | 700.45 | 26.74 | 18.91 | 14.9 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18650071600 |  | 100303332 |  | 6712208D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | CAMELLIA | 1077 CAMELLIA DR | 067 | LEX | 2019-04-16 | JENSMIN | AOC SYST | 2018-10-10 | 2019-04-16 | 2021-09-24 |  | JENSMIN | 2019-04-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.75 | 1 | 1636.75 | 46.32 | 233.1 | 25.83 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678768900 |  | 100299367 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 209 BOILING SPRING DR | 067 | LEX | 2019-04-16 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-04-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.4333 | 1 | 3266.16 | 141.09 | 0 | 40.08 | 3084.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678769300 |  | 100299364 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 217 BOILING SPRING DR | 067 | LEX | 2019-04-16 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-04-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.1167 | 1 | 1667.27 | 123.09 | 0 | 34.96 | 1509.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680074100 |  | 100320163 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | TAHOMA | 217 TAHOMA RD | 067 | LEX | 2019-04-16 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-04-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.4833 | 1 | 3635.66 | 206.07 | 0 | 57.75 | 3371.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19696399000 |  | 100283427 |  | 6712228E |  |  |  | 565 | EX | CONT - REPL SERV | 2621P | CHOCTAW | 1122 CHOCTAW TL | 209 | GEO | 2019-04-16 | CDESPAI | U125208 | 2019-04-11 | 2049-12-31 |  |  | CDESPAI | 2019-04-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.0833 | 1 | 1897.87 | 63.16 | 175.62 | 67.78 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19696399300 |  | 100282231 |  | 6712228B |  |  |  | 565 | EX | CONT - REPL SERV | 2621P | JEFFERSON | 204 E JEFFERSON ST | 209 | GEO | 2019-04-16 | CDESPAI | U125208 | 2019-04-11 | 2049-12-31 |  |  | CDESPAI | 2019-04-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4 | 1 | 2136.31 | 233.89 | 319.9 | 251.02 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19697812500 |  | 100421405 |  | 6700208H |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | BALSAM | 182 BALSAM CT | 239 | VER | 2019-04-16 | BJLONE | U130193 | 2019-04-16 | 2019-04-16 | 2019-04-16 |  | BJLONE | 2019-04-16 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 15.3 | 3 | 1007.7 | 792.13 | 170.46 | 45.11 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19697843600 |  | 100282232 |  | 6712228B |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | JEFFERSON | 202 E JEFFERSON ST | 209 | GEO | 2019-04-16 | CDESPAI | U130193 | 2019-04-16 | 2019-04-16 |  |  | CDESPAI | 2019-04-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.1833 | 1 | 3729.12 | 244.97 | 404.63 | 334.44 | 2745.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07676067300 |  | 100338454 |  | 6720212E |  |  |  | 566 | EX | ABANDON SL - IDLE 24 MONTHS | 2600B | 7TH | 157 E 7TH ST | 067 | LEX | 2019-04-17 | JENSMIN | SSUTHER | 2007-02-16 | 2019-04-12 |  |  | JENSMIN | 2019-04-17 | 2019-04-12 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.13333 | 2 | 13.75 | 7.72 | 0 | 6.03 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11878497500 |  | 100330893 |  | V1026-13 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | BASSETT | 324 BASSETT AV | 067 | LEX | 2019-04-17 | JENSMIN | U906609 | 2011-01-11 | 2014-12-23 | 2018-11-30 |  | JENSMIN | 2019-04-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.36667 | 1 | 710.24 | 21.38 | 32.28 | 16.68 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18613622500 |  | 100307392 |  | 6716212G | 1746168 |  |  | 565 | EX | REPLACE SL W/17026714900 | 2600B | HIGH | 828 W HIGH ST | 067 | LEX | 2019-04-18 | U461439 | U131066 | 2018-05-22 | 2019-12-31 |  |  | A PARRIS | 2019-04-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1776.41 | 0 | 0 | 0 | 1776.41 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18613699100 |  | 100307397 |  | 6716212G | 1746168 |  |  | 565 | EX | REPLACE SL W/17026714900 | 2600B | HIGH | 710 W HIGH ST | 067 | LEX | 2019-04-18 | U461439 | U131066 | 2018-05-22 | 2019-12-31 |  |  | A PARRIS | 2019-04-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1902.81 | 0 | 0 | 0 | 1902.81 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 18648806500 |  | 100353740 |  | 7256280L | 1747939 |  |  | 565 | EX | REPLACE SL W/17026728200 | 2600B | 2ND | 134 W 2ND ST | 161 | MAY | 2019-05-15 | U461478 | U126926 | 2018-10-05 | 2019-12-31 |  |  | DAVID STAGGS | 2019-04-17 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1
KY | KY - CENTRAL | 2632 | 19671927300 |  | 100353703 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 101 W 2ND ST | 161 | MAY | 2019-05-09 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-04-17 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1557.15 | 0 | 0 | 0 | 1557.15 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671928600 |  | 100353740 |  | 7256280L | 1747939 |  |  | 565 | VO | RPLC SL/17026728200/ | 2600B | 2ND | 134 W 2ND ST | 161 | MAY | 2019-05-13 |  | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-04-17 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1121.51 | 0 | 0 | 0 | 1121.51 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671928800 |  | 100353739 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 136 W 2ND ST | 161 | MAY | 2019-05-10 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-04-17 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1177.37 | 0 | 0 | 0 | 1177.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678768600 |  | 100299268 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 204 BOILING SPRING DR | 067 | LEX | 2019-04-17 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-04-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.85 | 1 | 1875.59 | 49.36 | 0 | 14.03 | 1812.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19692372300 |  | 100343531 |  | 7240212A |  |  |  | 566 | EX | DEMO / ABANDON / RA 04-03-19 | 2621P | SPRING | 415 SPRING ST | 173 | MT | 2019-04-17 | DENNING | U132002 | 2019-03-29 | 2019-04-29 | 2019-04-29 |  | DENNING | 2019-04-17 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 9.1333 | 2 | 670.26 | 509.28 | 11.19 | 149.79 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19696389100 |  | 100320048 |  | 6716208K | 1748686 |  |  | 565 | EX | REPLACE SL W/17026736100 | 2600B | GLENDOVER | 223 GLENDOVER RD | 067 | LEX | 2019-04-17 | U126284 | U131066 | 2019-04-11 | 2019-12-31 |  |  | JOSH PASLEY | 2019-04-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.9667 | 1 | 3975.49 | 352.51 | 0 | 98.82 | 3524.16 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19696398700 |  | 500010187 |  | 6712232I |  |  |  | 565 | EX | CONT - REPL SERV | 2621P | KEELRIDGE | 172 KEELRIDGE DR | 209 | GEO | 2019-04-18 | U125208 | U125208 | 2019-04-11 | 2049-12-31 |  |  | CDESPAI | 2019-04-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.1667 | 1 | 2275.07 | 243.25 | 179.44 | 261.07 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19696642300 |  | 100282066 | 67 | 6712232O |  |  |  | 566 | EX | DEMO / ABANDON / IDLE | 2621P | M L KING JR | 348 M L KING JR DR | 209 | GEO | 2019-04-18 | U125208 | JDBRADF | 2019-04-12 | 2019-04-17 |  |  | MCRAIG | 2019-04-17 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 28 | 2 | 1658.93 | 1487.48 | 86.74 | 84.71 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19697005400 |  | 100322435 |  | 6720208A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | TATES CREEK | 914 TATES CREEK RD | 067 | LEX | 2019-04-17 | JENSMIN | U125208 | 2019-04-15 | 2019-04-15 | 2019-05-03 |  | JENSMIN | 2019-04-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.3 | 1 | 3775.67 | 373.48 | 203.32 | 291.13 | 2907.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19698099500 |  | 100330746 |  | 6720212O |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | SHERMAN | 366 SHERMAN AV | 067 | LEX | 2019-04-17 | JENSMIN | U130193 | 2019-04-17 | 2019-04-17 |  |  | JENSMIN | 2019-04-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.5833 | 1 | 2046.28 | 154.39 | 176.35 | 120.33 | 1595.21 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19698105800 |  | 500010186 |  | 6712232I |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | KEELRIDGE | 164 KEELRIDGE DR | 209 | GEO | 2019-04-18 | U125208 | U130193 | 2019-04-17 | 2019-04-17 |  |  | CDESPAI | 2019-04-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.4667 | 1 | 2190.17 | 202.28 | 179.44 | 217.14 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19698205900 |  | 501256999 |  | 6724208E | 1961389 |  |  | 565 | EX | REPLACE SL | 2600B | PALUMBO | 2553 PALUMBO DR 100 | 067 | LEX | 2019-04-18 | U461327 | U131066 | 2019-04-17 | 2019-12-31 |  |  | WBURCHET | 2019-04-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 4 | 1 | 2145.77 | 218.17 | 0 | 65.2 | 1862.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 10869813500 |  | 100331862 |  | 00NEW | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | HANOVER | 159 N HANOVER AV 1FL | 067 | LEX | 2019-04-19 | U125208 | U906314 | 2010-11-29 | 2019-04-18 |  |  | JENSMIN | 2019-04-18 | 2019-04-18 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.3 | 1 | 715.49 | 17.82 | 43.88 | 13.89 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12968018000 |  | 100331863 |  | 00NEW | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | HANOVER | 159 N HANOVER AV 1FR | 067 | LEX | 2019-04-19 | U125208 | U124967 | 2012-05-02 | 2014-12-23 | 2018-11-30 |  | JENSMIN | 2019-04-18 | 2019-04-18 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.033333 | 1 | 3.18 | 1.78 | 0 | 1.4 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12975856400 |  | 100330899 |  | 167202120 | 1855043 |  |  | 566 | EX | SOII - ABNDN METER IN PLACE | 2621P | BASSETT | 348 BASSETT AV | 067 | LEX | 2019-05-20 | U125208 | U123854 | 2012-06-11 | 2019-04-18 |  |  | JENSMIN | 2019-04-18 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.26667 | 1 | 920.05 | 15.44 | 18.83 | 12.05 | 873.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18613622200 |  | 100307394 |  | 6716212G | 1746168 |  |  | 565 | EX | REPLACE SL W/17026714900 | 2600B | HIGH | 820 W HIGH ST | 067 | LEX | 2019-04-18 | U461439 | U131066 | 2018-05-22 | 2019-12-31 |  |  | A PARRIS | 2019-04-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1703.73 | 0 | 0 | 0 | 1703.73 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18620234300 |  | 100350628 |  | 6744208N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | REDWING | 16 REDWING DR | 049 | WIN | 2019-04-18 | LSHARON | U125208 | 2018-06-15 | 2018-12-14 | 2020-06-30 |  | LSHARON | 2019-04-18 | 2019-04-17 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 63.3833 | 10 | 5209.86 | 3316.08 | 306.49 | 1087.26 | 500.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026870300 |  | 501262567 |  | 6716216A | 1962959 | U461383 |  | 555 | EX | INSTALL 35' OF 2"PMMP MAIN | 2600B | LUCILLE | 633 LUCILLE DR LT | 067 | LEX | 2019-04-26 | U124014 | U461383 | 2019-04-12 | 2019-05-09 | 2019-05-10 | 2019-04-17 | WGRAVES | 2019-04-18 | 2019-04-16 | 2019-04-16 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP8703 |  |  | 100 | 055532190268703 | 12.9333 | 105 | 4138.06 | 709.59 | 178.1 | 211.33 | 2508 | 0 | 8.02 | 523.02 | 35
KY | KY - CENTRAL | 2632 | 19671927200 |  | 100353697 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 53 W 2ND ST | 161 | MAY | 2019-04-29 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-04-18 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1537.43 | 0 | 0 | 0 | 1537.43 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671937300 |  | 100353785 |  | 7256280L | 1747939 |  |  | 565 | EX | REPLACE SL W/17026728200 | 2600B | 2ND | 42 W 2ND ST | 161 | MAY | 2019-05-09 | U461478 | U131066 | 2019-01-22 | 2019-12-31 |  |  | DAVID STAGGS | 2019-04-18 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1223.47 | 0 | 0 | 0 | 1223.47 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19696398800 |  | 100281568 |  | 6712232N |  |  |  | 565 | EX | CONT - REPL SERV | 2621P | CHESTNUT | 511 CHESTNUT ST | 209 | GEO | 2019-04-18 | CDESPAI | U125208 | 2019-04-11 | 2049-12-31 |  |  | CDESPAI | 2019-04-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.2 | 1 | 2261.83 | 130.95 | 241.69 | 140.57 | 1748.62 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19696399100 |  | 500010245 |  | 6712232I |  |  |  | 565 | EX | CONT - REPL SERV | 2621P | JAMESTOWN | 109 JAMESTOWN CT | 209 | GEO | 2019-04-19 | U125208 | U125208 | 2019-04-11 | 2049-12-31 |  |  | CDESPAI | 2019-04-18 | 2019-04-17 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.7333 | 2 | 2220.49 | 216.92 | 179.44 | 232.82 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19697810100 |  | 100410473 |  | 6700208H |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | BALSAM | 192 BALSAM CT | 239 | VER | 2019-04-26 | U125208 | U130193 | 2019-04-16 | 2019-04-16 | 2019-04-16 |  | BJLONE | 2019-04-18 | 2019-04-17 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 29.3167 | 5 | 2093.59 | 1577.06 | 165.22 | 351.31 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19698198000 |  | 100345892 |  | 6700208D |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | HAWTHORNE | 107 HAWTHORNE CT | 239 | VER | 2019-04-19 | U125208 | U130193 | 2019-04-17 | 2019-04-17 | 2019-04-17 |  | CDESPAI | 2019-04-18 | 2019-04-17 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.4167 | 3 | 3011.99 | 241.08 | 204.39 | 142.68 | 2423.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19698637600 |  | 500010244 |  | 6712232I |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | JAMESTOWN | 105 JAMESTOWN CT | 209 | GEO | 2019-04-18 | CDESPAI | U130193 | 2019-04-18 | 2019-04-18 |  |  | CDESPAI | 2019-04-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.6333 | 1 | 1986.73 | 95.3 | 197.83 | 102.29 | 1591.31 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18026756801 |  |  |  | 6736248E | 1851316 | U128885 |  | 557 | EX | INSTALL 500' - 2" CSHP | 2600B | SAFETY | SAFETY WY | 097 | CYN | 2019-04-30 | U124014 | U128885 | 2019-04-16 | 2019-07-12 | 2020-03-05 | 2019-04-09 | JOHN SMITH | 2019-04-19 | 2019-04-01 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP7568 | AMRCB |  | 100 | 055732180267568 | 118.4833 | 6960 | 72110.42 | 8911.45 | 11783.61 | 4115.63 | 37636.89 | 0 | 587.83 | 9075.01 | 435
KY | KY - CENTRAL | 2629 | 18026756900 |  |  |  | 6736248E | 1851316 | U128885 |  | 558 | EX | RETIRE 750' - 2" BSHP | 2600B | SAFETY | SAFETY WY | 097 | CYN | 2019-04-30 | U124014 | U128885 | 2018-03-06 | 2019-07-31 | 2020-03-05 | 2019-04-09 | JOHN SMITH | 2019-04-19 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP7569 | AMRCB |  | 100 | 055832180267569 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18577390200 |  | 100307698 |  | 6716212G | 1746168 |  |  | 565 | EX | RPLC SL/17026714900/ | 2600B | MADISON | 330 MADISON PL | 067 | LEX | 2019-04-19 | U461439 | U131066 | 2018-01-26 | 2019-12-31 |  |  | A PARRIS | 2019-04-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2695.25 | 0 | 0 | 0 | 2695.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18601922800 |  | 100307400 |  | 6716212G | 1746168 |  |  | 565 | EX | RPLC SL/17026714900/ | 2621P | HIGH | 628 W HIGH ST 1F | 067 | LEX | 2019-04-19 | U461439 | U125964 | 2018-04-11 | 2018-11-30 |  |  | A PARRIS | 2019-04-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1243.8 | 0 | 0 | 0 | 1243.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18636011600 |  | 100334104 |  | 6720212O | 1855043 |  |  | 566 | EX | II - ABANDON ON SOII | 2621P | HENRY CLAY | 532 HENRY CLAY BV | 067 | LEX | 2019-05-20 | U125208 | U126129 | 2018-08-17 | 2018-10-30 | 2018-10-30 |  | DBANKS | 2019-04-19 | 2019-04-18 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 18.1333 | 3 | 2167.85 | 1060.93 | 54.52 | 412.5 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026864100 |  | 501255007 |  | 6712204A | 1961730 | U461383 |  | 555 | EX | INSTALL 485' OF 2"PMMP MAIN | 2600E | TWAIN RIDGE | 1981 TWAIN RIDGE DR | 067 | LEX | 2019-04-30 | U123258 | U461383 | 2019-02-27 | 2019-04-10 | 2019-07-12 | 2019-04-18 | DDAVIS | 2019-04-19 | 2019-04-08 | 2019-04-08 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP8641 |  |  | 100 | 055532190268641 | 43.8667 | 3594 | 26868.66 | 2638.66 | 1036.7 | 728.8 | 18935.79 | 0 | 11.86 | 3516.85 | 599
KY | KY - WEST | 2621 | 19690294600 |  | 100289255 |  | 6724212A |  |  |  | 566 | EX | ABANDON / RI 12-22-16 | 2621P | LOMBARDY | 669 LOMBARDY DR | 067 | LEX | 2019-04-19 | TNEAL | U132002 | 2019-03-21 | 2019-04-22 | 2019-04-22 |  | TNEAL | 2019-04-19 | 2019-03-22 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 22.2833 | 6 | 1221.85 | 1098.36 | 60.56 | 62.93 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691010800 |  | 100334225 |  | 6720212P |  |  |  | 566 | EX | DEMO / ABANDON / RA 04/02/19 | 2621P | LIBERTY | 2003 LIBERTY RD | 067 | LEX | 2019-04-25 | U125208 | U125208 | 2019-03-25 | 2019-04-25 |  |  | LMCDONA | 2019-04-19 | 2019-04-09 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 14.5667 | 6 | 1033.57 | 704.41 | 30.88 | 40.2 | 258.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18577387900 |  | 100307393 |  | 6716212G | 1746168 |  |  | 565 | EX | RPLC SL/17026714900/ | 2600B | HIGH | 822 W HIGH ST FT | 067 | LEX | 2019-04-22 | U461439 | U131066 | 2018-01-26 | 2019-12-31 |  |  | A PARRIS | 2019-04-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1989.5 | 0 | 0 | 0 | 1989.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18577388100 |  | 100300308 |  | 6716212G | 1746168 |  |  | 565 | EX | RPLC SL/17026714900/ | 2600B | HIGH | 841 W HIGH ST 2F | 067 | LEX | 2019-04-22 | U461439 | U131066 | 2018-01-26 | 2019-12-31 |  |  | A PARRIS | 2019-04-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1815.34 | 0 | 0 | 0 | 1815.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18577388200 |  | 100300312 |  | 6716212G | 1746168 |  |  | 565 | EX | RPLC SL/17026714900/ | 2600B | HIGH | 843 W HIGH ST | 067 | LEX | 2019-06-04 | U461439 | U131066 | 2018-01-26 | 2019-12-31 |  |  | A PARRIS | 2019-04-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1
KY | KY - WEST | 2621 | 18594263000 |  | 100326364 |  | 6720208A | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | COCHRAN | 210 COCHRAN RD | 067 | LEX | 2019-04-22 | JENSMIN | U125765 | 2018-03-14 | 2019-04-22 |  |  | JENSMIN | 2019-04-22 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0 | 1 | 683.78 | 0 | 43.88 | 0 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18651778800 |  | 100303866 |  | 6712208D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | LARKSPUR | 2012 LARKSPUR DR | 067 | LEX | 2019-04-22 | DBANKS | AOC SYST | 2018-10-18 | 2019-12-31 | 2019-12-31 |  | DBANKS | 2019-04-22 | 2019-04-19 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.7667 | 2 | 1658.28 | 97.35 | 223.88 | 5.55 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18655983200 |  | 100291964 |  | 6720216H | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER / | 2621D | NANCY | 2313 NANCY LN | 067 | LEX | 2019-04-26 | U125208 | AOC SYST | 2018-11-06 | 2019-01-04 | 2019-01-04 |  | JENSMIN | 2019-04-22 | 2019-04-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.7 | 2 | 3581.88 | 443.88 | 280.16 | 208.93 | 2648.91 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18659029300 |  | 100318851 |  | 6716204B | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | TARTAN | 163 TARTAN DR | 067 | LEX | 2019-04-26 | U125208 | AOC SYST | 2018-11-28 | 2019-12-31 | 2019-12-31 |  | DBANKS | 2019-04-22 | 2019-04-08 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.55 | 3 | 2201.14 | 361.66 | 223.86 | 24.31 | 1591.31 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671927900 |  | 100353751 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 116 W 2ND ST | 161 | MAY | 2019-05-08 | U123111 | U131066 | 2019-01-22 | 2019-11-27 |  |  | LYN STAFFORD | 2019-04-22 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 983.21 | 0 | 0 | 0 | 983.21 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678769200 |  | 100299271 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 216 BOILING SPRING DR | 067 | LEX | 2019-04-24 | U126285 | U131066 | 2019-02-01 | 2019-11-27 |  |  | DDAVIS | 2019-04-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.23333 | 1 | 1216.69 | 13.83 | 0 | 0.79 | 1202.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678769600 |  | 100299274 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 224 BOILING SPRING DR | 067 | LEX | 2019-04-24 | U126285 | U131066 | 2019-02-01 | 2019-11-27 |  |  | DDAVIS | 2019-04-22 | 2019-04-22 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.4167 | 1 | 3420.63 | 266.52 | 919.76 | 73.61 | 2160.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19687613900 |  | 100308456 |  | 6716212I | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | ADDISON | 728 ADDISON AV | 067 | LEX | 2019-04-26 | U125208 | AOC SYST | 2019-03-12 | 2019-04-22 | 2020-12-31 |  | JENSMIN | 2019-04-22 | 2019-04-22 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 | KYACA |  | 100 | 056532B26210032 | 1.2667 | 1 | 145.69 | 84.53 | 18.91 | 42.25 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19696232500 |  | 100295609 |  | 6716216K |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | OAKWOOD | 1170 OAKWOOD DR | 067 | LEX | 2019-04-22 | RVANDER | U130193 | 2019-04-10 | 2019-04-12 | 2019-05-01 |  | RVANDER | 2019-04-22 | 2019-04-12 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.8833 | 5 | 967.61 | 915.47 | 0 | 52.14 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19696399400 |  | 100281618 |  | 6712232N |  |  |  | 565 | EX | CONT - REPL SERV | 2621P | WALNUT | 538 WALNUT ST | 209 | GEO | 2019-04-22 | BJLONE | U125208 | 2019-04-11 | 2049-12-31 |  |  | BJLONE | 2019-04-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.15 | 1 | 2293.81 | 123.43 | 225.9 | 7.02 | 1937.46 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19699457400 |  | 100345942 |  | 6700208D |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | LAUREL | 113 LAUREL WY | 239 | VER | 2019-04-26 | U125208 | U130193 | 2019-04-22 | 2019-04-22 | 2019-04-22 |  | BJLONE | 2019-04-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.5833 | 1 | 2931.57 | 265.3 | 227.32 | 15.11 | 2423.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 05607610500 |  | 100331578 |  | 6720212N | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | HAZEL | 105 HAZEL AV | 067 | LEX | 2019-04-23 | JENSMIN | SSUTHER | 2005-04-14 | 2019-04-23 |  |  | JENSMIN | 2019-04-23 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.21667 | 1 | 1235.83 | 14.09 | 0 | 9.82 | 1211.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12967998100 |  | 100288023 |  | 16720212F | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | PARKVIEW | 401 PARKVIEW AV | 067 | LEX | 2019-04-26 | U125208 | U124967 | 2012-05-02 | 2019-04-23 |  |  | JENSMIN | 2019-04-23 | 2019-04-22 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.2 | 2 | 715.48 | 13.38 | 52.85 | 9.35 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18601922700 |  | 100444500 |  | 6716212G | 1746168 |  |  | 565 | EX | RPLC SL/17026714900/ | 2621P | HIGH | 844 W HIGH ST 1F | 067 | LEX | 2019-04-23 | U461439 | U125964 | 2018-04-11 | 2018-11-30 |  |  | A PARRIS | 2019-04-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1734.37 | 0 | 0 | 0 | 1734.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18613622000 |  | 100307395 |  | 6716212G | 1746168 |  |  | 565 | EX | REPLACE SL W/17026714900 | 2600B | HIGH | 816 W HIGH ST | 067 | LEX | 2019-04-23 | U461439 | U131066 | 2018-05-22 | 2019-12-31 |  |  | A PARRIS | 2019-04-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1844.66 | 51.99 | 0 | 15.85 | 1776.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18636012100 |  | 100288795 |  | 6720212D | 1855043 |  |  | 566 | EX | II - ABANDON ON SOII | 2621P | SAINT ANTHONY | 568 SAINT ANTHONY DR | 067 | LEX | 2019-05-20 | U125208 | U126129 | 2018-08-17 | 2019-04-23 |  |  | JENSMIN | 2019-04-23 | 2019-04-22 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.31667 | 2 | 793.49 | 20.8 | 118.3 | 14.49 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678770000 |  | 100299279 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 232 BOILING SPRING DR | 067 | LEX | 2019-04-23 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-04-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.21667 | 1 | 1069.46 | 12.2 | 0 | 3.47 | 1053.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678770200 |  | 100299280 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 236 BOILING SPRING DR | 067 | LEX | 2019-04-23 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-04-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.6167 | 1 | 1629.22 | 93.45 | 0 | 26.55 | 1509.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678770600 |  | 100299283 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 244 BOILING SPRING DR | 067 | LEX | 2019-04-23 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-04-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.3833 | 1 | 1231.26 | 138.21 | 0 | 39.26 | 1053.79 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19692254400 |  | 100275126 | 59 | 6684228J |  |  |  | 566 | EX | ABANDON / RI 3-28-19 / CNVRT | 2621P | MAIN | 236 W MAIN ST | 073 | FRA | 2019-04-30 | U125208 | U129148 | 2019-03-29 | 2049-12-31 |  |  | MCRAIG | 2019-04-23 | 2019-04-18 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 13.6833 | 6 | 739.25 | 681.46 | 18.91 | 38.88 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19696399500 |  | 100281675 |  | 6712232O |  |  |  | 565 | EX | CONT - REPL SERV | 2621P | PAYNE | 519 PAYNE AV | 209 | GEO | 2019-04-23 | CDESPAI | U125208 | 2019-04-11 | 2049-12-31 |  |  | CDESPAI | 2019-04-23 | 2019-04-19 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.45 | 2 | 3718.9 | 376.55 | 310.86 | 228.26 | 2803.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19696628300 |  | 100316998 |  | 6716208J |  |  |  | 565 | EX | SERVICE LINE - REPLACE RVANDER | 2621P | RAINBOW | 2055 RAINBOW RD | 067 | LEX | 2019-04-23 | RVANDER | U125208 | 2019-04-12 | 2049-12-31 |  |  | RVANDER | 2019-04-23 | 2019-04-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 29.45 | 5 | 1588.66 | 1468 | 0 | 120.66 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19698100400 |  | 100279509 |  | 6688228O |  |  |  | 565 | EX | REPLACE SL/CFCB 2016 | 2621P | LAGO | 1303 LAGO DR | 073 | FRA | 2019-04-23 | CDESPAI | U125208 | 2019-04-17 | 2049-12-31 |  |  | CDESPAI | 2019-04-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.1333 | 1 | 1920.91 | 66.11 | 192.55 | 70.94 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19698588600 |  | 100316997 |  | 6716208J |  |  |  | 565 | EX | REPLACE SERVICE - MOVE METER | 2621P | RAINBOW | 2051 RAINBOW RD | 067 | LEX | 2019-04-23 | RVANDER | U125208 | 2019-04-18 | 2019-04-18 |  |  | RVANDER | 2019-04-23 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.75 | 4 | 462.45 | 437.54 | 0 | 24.91 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19699419300 |  | 100330951 |  | 6720212N |  |  |  | 565 | EX | REPLACE SERV LINE | 2621P | BASSETT | 287 BASSETT AV 1FL-1 | 067 | LEX | 2019-04-25 | U125208 | U129939 | 2019-04-20 | 2019-04-18 |  |  | KKINDER | 2019-04-23 | 2019-04-22 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 46.2333 | 10 | 2378.66 | 2104.24 | 90.32 | 184.1 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19699791300 |  | 100336470 |  | 6720212I |  |  |  | 565 | EX | REPLACE SERVICE | 2621P | CAMPSIE | 239 CAMPSIE PL | 067 | LEX | 2019-04-30 | U125208 | U131168 | 2019-04-22 | 2019-04-22 | 2019-04-22 |  | TGNELSO | 2019-04-23 | 2019-04-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 33.75 | 3 | 1687.4 | 1596.45 | 0 | 90.95 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19699821600 |  | 100278297 |  | 6688228B |  |  |  | 565 | EX | REPLACE SERVICE W/LCB | 2621P | AZTEC | 532 AZTEC TL | 073 | FRA | 2019-04-30 | U125208 | U125208 | 2019-04-23 | 2019-05-23 |  |  | CDESPAI | 2019-04-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.8833 | 1 | 2277.27 | 171.88 | 329.58 | 184.5 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 09787701900 |  | 100288881 | 06 | V-1021-32 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | NORTHSIDE | 544 NORTHSIDE DR | 067 | LEX | 2019-04-26 | U125208 | HMONTGO | 2009-05-18 | 2014-12-23 |  |  | LSTANFI | 2019-04-24 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.7833 | 1 | 821.54 | 171.85 | 0 | 9.79 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11896774500 |  | 100308575 |  | 16716212N | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | DEVONSHIRE | 1206 DEVONSHIRE AV | 067 | LEX | 2019-04-29 | U125208 | U906631 | 2011-03-21 | 2019-04-24 |  |  | LSTANFI | 2019-04-24 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.5667 | 1 | 740.4 | 95.08 | 0 | 5.42 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11900047600 |  | 100314237 |  | V-930-6 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | BUCOTO | 373 BUCOTO CT | 067 | LEX | 2019-04-24 | LSTANFI | U123933 | 2011-04-06 | 2014-12-23 |  |  | LSTANFI | 2019-04-24 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.5667 | 1 | 906.03 | 216.91 | 36.86 | 12.36 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18618897600 |  | 100293442 |  | 6720216I |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | VAN BUREN | 1531 VAN BUREN DR | 067 | LEX | 2019-04-30 | U125208 | U125208 | 2018-06-11 | 2019-04-24 | 2020-06-30 |  | DBANKS | 2019-04-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.5167 | 1 | 2344.07 | 84.62 | 206.38 | 4.82 | 2048.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18652909600 |  | 100304332 |  | 6712208D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | LANE ALLEN | 937 LANE ALLEN RD | 067 | LEX | 2019-04-24 | LSTANFI | AOC SYST | 2018-10-23 | 2019-12-31 | 2019-12-31 |  | LSTANFI | 2019-04-24 | 2019-04-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.8833 | 3 | 3783.91 | 289.72 | 0 | 16.52 | 3477.67 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678770800 |  | 100299287 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 248 BOILING SPRING DR | 067 | LEX | 2019-04-24 | U126285 | U131066 | 2019-02-01 | 2019-11-27 |  |  | DDAVIS | 2019-04-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.7667 | 1 | 2962.38 | 647.92 | 0 | 36.89 | 2277.57 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19696399800 |  | 100448865 |  | 6712232O |  |  |  | 565 | EX | CONT - REPL SERV | 2621P | HICKMAN | 305 HICKMAN ST | 209 | GEO | 2019-04-24 | CDESPAI | U125208 | 2019-04-11 | 2049-12-31 |  |  | CDESPAI | 2019-04-24 | 2019-04-19 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8.2833 | 2 | 3099.4 | 484.11 | 332.32 | 345.51 | 1937.46 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19698104000 |  | 100278443 |  | 6688232N |  |  |  | 565 | EX | REPLACE SERV W/LCB | 2621P | MOHEGAN | 508 MOHEGAN TL | 073 | FRA | 2019-04-24 | CDESPAI | U125208 | 2019-04-17 | 2049-12-31 |  |  | CDESPAI | 2019-04-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.65 | 1 | 2580.11 | 271.83 | 425.18 | 291.79 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19699269600 |  | 500223980 |  | 6688228C |  |  |  | 566 | EX | DEMO / ABANDON / FIRE DMG | 2621P | KEENELAND | 1056 KEENELAND CT | 073 | FRA | 2019-04-30 | U125208 | U125770 | 2019-04-19 | 2019-06-21 | 2019-06-21 |  | MCRAIG | 2019-04-24 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 9.6333 | 2 | 559.09 | 511.07 | 18.91 | 29.11 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12975868000 |  | 100342131 |  | 7240216N |  |  |  | 566 | EX | SOII - RI - ABANDON SERVICE | 2621P | WINN | 207 WINN ST | 173 | MT | 2019-04-25 | DENNING | U123854 | 2012-06-11 | 2019-04-02 |  |  | DENNING | 2019-04-25 | 2019-03-28 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 18.5167 | 8 | 1118.23 | 895.33 | 0 | 222.9 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18577403300 |  | 100456266 |  | 6716212G | 1746168 |  |  | 565 | EX | REPLACE SL W/17026714900 | 2600B | HIGH | 838 W HIGH ST APT 3 | 067 | LEX | 2019-04-25 | U461439 | U131066 | 2018-01-26 | 2019-12-31 |  |  | A PARRIS | 2019-04-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4446.17 | 0 | 0 | 0 | 4446.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18613623100 |  | 100307381 |  | 6716212G | 1746168 |  |  | 565 | EX | REPLACE SL W/17026714900 | 2600B | HIGH | 856 W HIGH ST | 067 | LEX | 2019-04-25 | U461439 | U131066 | 2018-05-22 | 2019-12-31 |  |  | A PARRIS | 2019-04-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1592.99 | 0 | 0 | 0 | 1592.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18648910100 |  | 100326396 |  | 6720208A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CHENAULT | 212 CHENAULT RD | 067 | LEX | 2019-04-25 | DBANKS | U125208 | 2018-10-05 | 2019-03-11 | 2020-10-31 |  | DBANKS | 2019-04-25 | 2019-04-15 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.4 | 3 | 3466.7 | 302.57 | 229.5 | 17.26 | 2917.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678771000 |  | 100299289 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 252 BOILING SPRING DR | 067 | LEX | 2019-04-25 | U126285 | U131066 | 2019-02-01 | 2019-11-27 |  |  | DDAVIS | 2019-04-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.5 | 1 | 3005.91 | 571.55 | 0 | 157.84 | 2276.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19685884300 |  | 100317636 |  | 6716204F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D193320 | 2621P | DARTMOUTH | 3025 DARTMOUTH DR | 067 | LEX | 2019-04-25 | DBANKS | U125208 | 2019-03-04 | 2019-04-25 | 2021-03-31 |  | DBANKS | 2019-04-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.8833 | 1 | 1949.66 | 103.98 | 248.45 | 5.92 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19698103300 |  | 100278450 |  | 6688228B |  |  |  | 565 | EX | REPLACE SERV W/LCB | 2621P | HIAWATHA | 417 HIAWATHA TL | 073 | FRA | 2019-04-25 | CDESPAI | U125208 | 2019-04-17 | 2049-12-31 |  |  | CDESPAI | 2019-04-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 1 | 4916.45 | 467.79 | 223.88 | 502.03 | 3722.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19700615900 |  | 100298818 |  | 6716216O |  |  |  | 565 | EX | GRADE 1 REPLACE SERV | 2621P | DALRAY | 207 DALRAY DR | 067 | LEX | 2019-04-30 | U125208 | U129939 | 2019-04-25 | 2019-04-25 | 2019-04-25 |  | ASNICHO | 2019-04-26 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.7167 | 4 | 1374.9 | 847.66 | 478.92 | 48.32 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11898679600 |  | 100467586 |  | 6724212E |  |  |  | 566 | EX | ABANDON SERVICE | 2621P | ANNISTON | 1474 ANNISTON DR A9 | 067 | LEX | 2019-04-30 | U125208 | U123933 | 2011-03-30 | 2019-04-28 | 2019-05-16 |  | TNEAL | 2019-04-29 | 2019-04-25 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.5333 | 6 | 800.52 | 739.5 | 18.91 | 42.11 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18577386600 |  | 100428569 |  | 6716212G | 1746168 |  |  | 565 | EX | RPLC SL/17026714900/ | 2600B | COX | 158 COX ST | 067 | LEX | 2019-04-29 | U461439 | U131066 | 2018-01-26 | 2019-12-31 |  |  | A PARRIS | 2019-04-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.2 | 1 | 1657.38 | 289.36 | 0 | 122.16 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18636019900 |  | 100336012 |  | 6720212K | 1855043 |  |  | 566 | EX | II - ABANDON ON SOII | 2621P | BYARS | 909 BYARS AV | 067 | LEX | 2019-05-06 | U125208 | U126129 | 2018-08-17 | 2018-10-30 | 2018-10-30 |  | JENSMIN | 2019-04-29 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.33333 | 1 | 678.98 | 22.14 | 8.97 | 7.97 | 639.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19672568700 |  | 100258279 |  | 7348268M |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | 1ST | 316 1ST AV | 089 | WOR | 2019-04-29 | AMCCORM | U125208 | 2019-01-24 | 2019-04-29 | 2021-01-31 |  | AMCCORM | 2019-04-29 | 2019-04-29 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 14.4833 | 2 | 1805.63 | 856.63 | 144.05 | 804.95 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678771400 |  | 100299292 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 260 BOILING SPRING DR | 067 | LEX | 2019-06-10 | U125208 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-04-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.28333 | 1 | 1076.09 | 15.71 | 0 | 6.59 | 1053.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678771700 |  | 100299293 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 268 BOILING SPRING DR | 067 | LEX | 2019-04-29 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-04-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.3 | 1 | 1369.94 | 16.8 | 0 | 7.06 | 1346.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680089400 |  | 100320139 |  | 6716208K | 1748686 |  |  | 565 | EX | REPLACE SL W/17026736100 | 2600B | TAHOMA | 230 TAHOMA RD | 067 | LEX | 2019-04-29 | U126284 | U131066 | 2019-02-07 | 2019-12-31 |  |  | JOSH PASLEY | 2019-04-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1224.17 | 0 | 0 | 0 | 1224.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19699462800 |  | 500704421 |  | 6724208H | 1961727 |  |  | 565 | EX | RPLC SL/19026864000 | 2600B | SHAKER RUN | 2016 SHAKER RUN RD | 067 | LEX | 2019-04-30 | HROGERS | U125201 | 2019-04-22 | 2019-06-28 |  |  | MARK ROGERS | 2019-04-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 57.52 | 0 | 57.52 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19701085700 |  | 100275128 |  | 6684228J |  |  |  | 566 | EX | ABANDON/KILL SERV LINE | 2621P | MAIN | 232 W MAIN ST | 073 | FRA | 2019-04-30 | U125208 | U129939 | 2019-04-28 | 2019-04-28 | 2019-04-28 |  | CDESPAI | 2019-04-29 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 3.8333 | 1 | 3911.49 | 214.94 | 18.47 | 334.72 | 3343.36 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19701136700 |  | 100279485 |  | 6688228O |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | ARROYO | 1401 ARROYO DR | 073 | FRA | 2019-04-29 | CDESPAI | U130193 | 2019-04-29 | 2019-04-29 | 2019-04-29 |  | CDESPAI | 2019-04-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.05 | 1 | 2429.29 | 113.92 | 320.04 | 177.45 | 1817.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19701196400 |  | 100279494 |  | 6688228O |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | ARBOLADO | 314 ARBOLADO DR | 073 | FRA | 2019-04-29 | CDESPAI | U130193 | 2019-04-29 | 2019-04-29 |  |  | CDESPAI | 2019-04-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.75 | 1 | 2750.47 | 43.78 | 1047.2 | 68.18 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026864000 |  | 500704404 |  | 6724208H | 1961727 | U461383 |  | 555 | EX | INSTALL 200' OF 2"PMMP MAIN | 2600B | SHAKER RUN | 2017 SHAKER RUN RD | 067 | LEX | 2019-06-20 | U462463 | U461383 | 2019-02-26 | 2019-04-05 | 2019-07-08 | 2019-04-29 | HROGERS | 2019-04-30 | 2019-04-16 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP8640 |  |  | 100 | 055532190268640 | 55.6667 | 2097 | 19517.08 | 3028.38 | 692.53 | 994.82 | 12277.14 | 0 | 27.33 | 2496.88 | 233
KY | KY - EAST | 2631 | 19026868200 |  |  |  | 7344244B | 1427508 | U131983 |  | 587 | EX | INSTALL MI WIRELESS EFC | 2631M | US60 | 1300 W US60 | 019 | RUS | 2019-12-31 | U462463 | U131983 | 2019-03-28 | 2019-12-30 | 2019-12-31 | 2019-04-30 | CYNTHIA FARIS | 2019-04-30 | 2019-04-30 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00587 | 3200587 |  |  | WP8682 |  |  | 100 | 058732190268682 | 18.85 | 3 | 4481.07 | 1127.68 | 2457.99 | 317.87 | 0 | 0 | 0.2 | 577.33
KY | KY - EAST | 2631 | 19026890100 |  |  |  | 7344244B | 1427508 | U461383 |  | 588 | EX | RETIRE MERCURY-MINI UNIT | 2631M | US60 | 1300 W US60 | 019 | RUS | 2019-12-31 | U462463 | U461383 | 2019-08-11 | 2019-12-31 | 2019-12-31 | 2019-04-30 | CYNTHIA FARIS | 2019-04-30 |  |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00588 | 3200588 |  |  | WP8901 |  |  | 100 | 058832190268901 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671928300 |  | 100353748 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 124 W 2ND ST | 161 | MAY | 2019-05-02 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-04-30 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2922.73 | 0 | 0 | 0 | 2922.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678771100 |  | 100299352 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 253 BOILING SPRING DR | 067 | LEX | 2019-04-30 | U126284 | U131066 | 2019-02-01 | 2019-11-27 |  |  | JOSH PASLEY | 2019-04-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1202.07 | 0 | 0 | 0 | 1202.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678772200 |  | 100299343 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 281 BOILING SPRING DR | 067 | LEX | 2019-04-30 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-04-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.3167 | 1 | 1306.3 | 73.42 | 0 | 30.81 | 1202.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678772300 |  | 100299342 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 285 BOILING SPRING DR | 067 | LEX | 2019-04-30 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-04-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.18333 | 1 | 1217.97 | 11.2 | 0 | 4.7 | 1202.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680075300 |  | 100320142 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | TAHOMA | 238 TAHOMA RD | 067 | LEX | 2019-04-30 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-04-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.5167 | 1 | 2389.17 | 149.06 | 0 | 59.5 | 2180.61 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19681935400 |  | 100405690 |  | 6716208P |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | TATES CREEK | 3320 TATES CREEK RD | 067 | LEX | 2019-05-03 | U125208 | U125208 | 2019-02-18 | 2019-04-16 | 2021-02-28 |  | DBANKS | 2019-04-30 | 2019-03-27 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 62.95 | 14 | 14038.18 | 3550.6 | 259.38 | 1048.07 | 9180.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19684338900 |  | 100313883 |  | 6716212N | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | SOUTHERN | 1310 SOUTHERN AV | 067 | LEX | 2019-04-30 | DBANKS | AOC SYST | 2019-03-01 | 2020-12-31 | 2020-12-31 |  | DBANKS | 2019-04-30 | 2019-04-08 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.48333 | 2 | 2122.8 | 26.94 | 257.52 | 3.92 | 1834.42 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19697381500 |  | 100448421 |  | 7240216F |  |  |  | 565 | EX | REPLACE CAT 2 SERVICE | 2621P | EVANS | 186 EVANS DR | 173 | MT | 2019-05-06 | JTOY | JTOY | 2019-04-15 | 2019-04-18 |  |  | WDENNINGHOFF | 2019-04-30 | 2019-04-18 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 27.7833 | 8 | 1959.69 | 1354.62 | 141.71 | 463.36 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19701574600 |  | 100264327 |  | 7356260M |  |  |  | 566 | EX | ABN INF MCOLLET | 2621P | CENTRAL | 1112 CENTRAL AV | 019 | ASH | 2019-04-30 | MCOLLET | U131167 | 2019-04-30 | 2019-04-30 |  |  | MCOLLET | 2019-04-30 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 4.6667 | 2 | 440.33 | 265.62 | 27.89 | 146.82 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 12968023800 |  | 100342879 |  | 7240212B |  |  |  | 566 | EX | SOII - ABANDON METER ONLY | 2621P | BROADWAY | 32 BROADWAY ST | 173 | MT | 2019-05-01 | DENNING | U124967 | 2012-05-02 | 2014-12-31 |  |  | DENNING | 2019-05-01 |  |  | D | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 3.9 | 3 | 240.55 | 177.89 | 0 | 62.66 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 17026705600 |  |  |  | 6716220A | 1744704 | U461383 |  | 559 | EX | INSTALL 2"GV-10' 2"CSHP MAIN | 2600B | BEREA | BEREA RD | 067 | LEX | 2024-03-21 | U123258 | U461383 | 2017-04-18 | 2019-05-22 | 2019-05-31 | 2019-04-29 | WGRAVES | 2019-05-01 | 2019-04-17 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP7056 |  |  | 100 | 055932170267056 | 97.7833 | 285 | 56876.12 | 6573.31 | 6949.56 | 1976.29 | 33788.65 | 0 | 259.87 | 7328.44 | 19
KY | KY - WEST | 2621 | 17026705700 |  |  |  | 6716220A | 1744704 | U461383 |  | 560 | EX | ABANDON 2"GV C4-73 | 2600B | BEREA | BEREA RD | 067 | LEX | 2019-05-06 | U123258 | U461383 | 2017-04-18 | 2019-05-31 | 2019-05-31 | 2019-04-29 | WGRAVES | 2019-05-01 | 2019-04-29 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00560 | 3200560 |  |  | WP7057 |  |  | 100 | 056032170267057 | 3.85 | 0 | 362.38 | 206.28 | 0 | 90 | 66.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572292800 |  | 100279795 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 189 SUNSET DR | 073 | FRA | 2019-05-01 | U461439 | U131066 | 2018-01-04 | 2019-12-31 |  |  | A PARRIS | 2019-05-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572292900 |  | 100279802 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 190 SUNSET DR | 073 | FRA | 2019-05-01 | U461439 | U131066 | 2018-01-04 | 2019-12-31 |  |  | A PARRIS | 2019-05-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572293100 |  | 100279801 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 192 SUNSET DR | 073 | FRA | 2019-05-01 | U461439 | U131066 | 2018-01-04 | 2019-12-31 |  |  | A PARRIS | 2019-05-01 | 2018-03-22 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 11 | 1 | 2390.26 | 580.38 | 0 | 33.47 | 1776.41 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572293200 |  | 100279797 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 193 SUNSET DR | 073 | FRA | 2019-05-01 | U461439 | U131066 | 2018-01-04 | 2019-12-31 |  |  | A PARRIS | 2019-05-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2603.35 | 0 | 0 | 0 | 2603.35 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572293300 |  | 100279800 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 194 SUNSET DR | 073 | FRA | 2019-05-01 | U461439 | U131066 | 2018-01-04 | 2019-12-31 |  |  | A PARRIS | 2019-05-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1776.41 | 0 | 0 | 0 | 1776.41 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572293500 |  | 100279799 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 197 SUNSET DR | 073 | FRA | 2019-05-01 | U461439 | U131066 | 2018-01-04 | 2019-12-31 |  |  | A PARRIS | 2019-05-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680075000 |  | 100320140 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | TAHOMA | 234 TAHOMA RD | 067 | LEX | 2019-05-01 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-05-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.46667 | 1 | 1815.83 | 26.45 | 0 | 10.92 | 1778.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19700965800 |  | 100319696 |  | 6716208K |  |  |  | 565 | EX | REPLACE SERVICE - PER SC | 2621P | ZANDALE | 256 ZANDALE DR | 067 | LEX | 2019-05-03 | U125208 | U125208 | 2019-04-26 | 2019-05-02 |  |  | DBANKS | 2019-05-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.6333 | 1 | 2699.44 | 472.53 | 209.02 | 28.34 | 1989.55 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19700995300 |  | 100337067 |  | 6720212I |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CHESTNUT | 413 CHESTNUT ST | 067 | LEX | 2019-05-02 | U125208 | U124447 | 2019-04-26 | 2019-04-26 | 2019-04-26 |  | ANICHOLS | 2019-05-01 | 2019-04-26 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 26 | 7 | 6830.45 | 1579.7 | 293.38 | 778.79 | 4178.58 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19701433700 |  | 100345136 |  | 6696212G |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | VIRGINIA | 195< VIRGINIA AV | 239 | VER | 2019-05-03 | U125208 | U130193 | 2019-04-30 | 2019-04-30 |  |  | CDESPAI | 2019-05-01 | 2019-04-30 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 19.6333 | 2 | 12791.03 | 1087.34 | 415.49 | 1716.94 | 9571.26 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19702028200 |  | 100331994 |  | 6720212M |  |  |  | 565 | EX | REPLACE SERVICE LINE G1D192720 | 2621P | HAMBRICK | 700 HAMBRICK AV | 067 | LEX | 2019-05-03 | U125208 | U131367 | 2019-05-01 | 2019-05-01 | 2019-05-01 |  | DBANKS | 2019-05-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.0167 | 1 | 1724.83 | 110.09 | 53.09 | 6.6 | 1555.05 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19702123400 |  | 100414874 |  | 6720208H |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HEDGEWOOD | 265 HEDGEWOOD CT | 067 | LEX | 2019-05-03 | U125208 | U131168 | 2019-05-01 | 2019-05-01 | 2019-05-01 |  | TNEAL | 2019-05-01 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.4333 | 4 | 1002.31 | 637.61 | 326.4 | 38.3 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11908849100 |  | 100451299 |  | 6716212B |  |  |  | 566 | EX | ABANDON W/100299693* | 2600B | FORBES | 157< S FORBES RD | 067 | LEX | 2019-05-03 | U125208 | U907001 | 2011-05-27 | 2020-12-31 |  |  | JENSMIN | 2019-05-02 | 2019-04-05 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.95 | 0 | 7891.25 | 1090.21 | 172.8 | 630.23 | 5998.01 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572291600 |  | 100279809 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 178 SUNSET DR | 073 | FRA | 2019-05-14 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1592.99 | 0 | 0 | 0 | 1592.99 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572291800 |  | 100279808 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 180 SUNSET DR | 073 | FRA | 2019-05-14 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2487.77 | 0 | 0 | 0 | 2487.77 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572292300 |  | 100279806 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 184 SUNSET DR | 073 | FRA | 2019-05-14 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572292500 |  | 100279805 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 186 SUNSET DR | 073 | FRA | 2019-05-02 | U461439 | U131066 | 2018-01-04 | 2019-12-31 |  |  | A PARRIS | 2019-05-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572292600 |  | 100279794 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 187 SUNSET DR | 073 | FRA | 2019-05-14 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2072.8 | 0 | 0 | 0 | 2072.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572293000 |  | 100279796 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 191 SUNSET DR | 073 | FRA | 2019-05-02 | U461439 | U131066 | 2018-01-04 | 2019-12-31 |  |  | A PARRIS | 2019-05-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2369.21 | 0 | 0 | 0 | 2369.21 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19026863200 |  | 501208592 |  | 6708228H | 1961459 | U461383 |  | 555 | EX | INSTALL 1600' OF 2"PMIP MAIN | 2600B | SEMINOLE | 1301 SEMINOLE TR LT | 209 | GEO | 2019-05-09 | U123258 | U461383 | 2019-02-18 | 2019-04-02 | 2019-04-26 | 2019-04-29 | KKOUNS | 2019-05-02 | 2019-03-28 | 2019-03-28 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP8632 |  |  | 100 | 055532190268632 | 223.0333 | 44850 | 104820.38 | 12315.15 | 3079.84 | 3908.52 | 72007.9 | 0 | 193.34 | 13315.63 | 1725
KY | KY - WEST | 2621 | 19026864700 |  |  |  | 6716208A | 1962004 | U461383 |  | 557 | EX | INSTALL 10' OF 4"PMLP MAIN | 2621P | CLAYS MILL | 1836 CLAYS MILL | 067 | LEX | 2019-06-10 | U123258 | U461383 | 2019-03-06 | 2019-06-27 | 2019-07-01 | 2019-03-07 | JENSMINGER | 2019-05-02 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP8647 | AMRCB |  | 100 | 055732190268647 |  | 6 | 7990.59 | 0 | 670.05 | 0 | 6291.4 | 0 | 19.73 | 1009.41 | 6
KY | KY - WEST | 2621 | 19678771600 |  | 100299348 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 265 BOILING SPRING DR | 067 | LEX | 2019-06-07 | U126285 | U131066 | 2019-02-01 | 2019-11-27 |  |  | DDAVIS | 2019-05-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2285.48 | 420.32 | 0 | 187.79 | 1677.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680075200 |  | 100320156 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | TAHOMA | 237 TAHOMA RD | 067 | LEX | 2019-05-02 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-05-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.6333 | 1 | 3073.75 | 209.01 | 0 | 86.52 | 2778.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19685884400 |  | 100317639 |  | 6716204F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D193321 | 2621P | DARTMOUTH | 3037 DARTMOUTH DR | 067 | LEX | 2019-05-03 | U125208 | U125208 | 2019-03-04 | 2019-04-29 | 2021-03-31 |  | JENSMIN | 2019-05-02 | 2019-04-29 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.9667 | 2 | 1978.56 | 399.08 | 90.16 | 157.82 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19686665500 |  | 100289703 |  | 6720216P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D193496 | 2621P | SPRING STATION | 1936 SPRING STATION DR | 067 | LEX | 2019-05-02 | DBANKS | U131392 | 2019-03-07 | 2019-09-06 | 2021-03-31 |  | DBANKS | 2019-05-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.9333 | 1 | 1998.09 | 105.1 | 256.34 | 45.34 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19687272100 |  | 500918626 |  | 6720216M | 0464916 |  |  | 566 | EX | DEMO / ABANDON / RA 04/05/19 | 2621P | NEW CIRCLE | 506 W NEW CIRCLE RD | 067 | LEX | 2019-05-03 | U125208 | U125208 | 2019-03-11 | 2019-05-01 | 2019-05-01 |  | LSTANFI | 2019-05-02 | 2019-05-01 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.1167 | 7 | 578.1 | 545.39 | 0 | 32.71 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19688517400 |  | 100292130 |  | 6720216G |  |  |  | 565 | EX | REPLACE SERVICE LINE - D193498 | 2621P | CHYLEEN | 2208 CHYLEEN DR | 067 | LEX | 2019-05-02 | JENSMIN | U125208 | 2019-03-15 | 2019-09-13 | 2021-03-31 |  | JENSMIN | 2019-05-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.6333 | 1 | 2423.17 | 430.57 | 220.79 | 440.31 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19688535600 |  | 100338584 |  | 6720212F |  |  |  | 566 | EX | ABN-UNDER CONST / RI 3-25-19 | 2621P | LANCASTER | 735 LANCASTER AV | 067 | LEX | 2019-05-02 | LMCDONA | U125208 | 2019-03-15 | 2019-04-22 |  |  | LMCDONA | 2019-05-02 | 2019-04-03 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 17.5167 | 5 | 951.29 | 887.96 | 10.35 | 52.98 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19689140000 |  | 100306437 |  | 6716212M |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094001 | 2621P | LAUREL HILL | 837 LAUREL HILL RD | 067 | LEX | 2019-05-02 | DBANKS | U125208 | 2019-03-18 | 2019-09-13 | 2021-03-31 |  | DBANKS | 2019-05-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.7167 | 1 | 1946.38 | 147.86 | 143.47 | 63.74 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19701966500 |  | 100422922 |  | 6724208E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HEDGEWOOD | 290 HEDGEWOOD CT | 067 | LEX | 2019-05-03 | U125208 | U125208 | 2019-05-01 | 2019-04-30 | 2019-04-30 |  | KKINDER | 2019-05-02 | 2019-05-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 27.0333 | 8 | 1310.26 | 1236.11 | 0 | 74.15 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19702120400 |  | 100346622 |  | 6696212P |  |  |  | 565 | EX | REPLACE SERVICE LINE D095267 | 2621P | MCDONALD | 343 MCDONALD DR | 239 | VER | 2019-05-03 | U125208 | U131367 | 2019-05-01 | 2019-05-01 | 2019-05-01 |  | EFGOINS | 2019-05-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.5667 | 1 | 2341.07 | 234.02 | 275.15 | 14.02 | 1817.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026859000 |  |  |  | 6716208D | 1961144 | U131982 |  | 557 | EX | INSTALL 60'-4" PMLP | 2621P | BEAUMONT | BEAUMONT AV | 067 | LEX | 2019-05-14 | U123258 | U131982 | 2019-02-04 | 2019-10-30 | 2019-10-31 | 2019-03-18 | LES STANFIELD | 2019-05-03 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP8590 | AMRCB |  | 100 | 055732190268590 | 1.1667 | 136 | 16141.38 | 509.7 | 2182.74 | 36.76 | 11332.52 | 0 | 6.18 | 2073.48 | 68
KY | KY - WEST | 2621 | 19026859100 |  |  |  | 6716208D | 1961144 | U131982 |  | 558 | EX | ABANDON 60'-4" BSLP | 2621P | BEAUMONT | BEAUMONT | 067 | LEX | 2019-05-14 | U125208 | U131982 | 2019-02-04 | 2019-10-31 | 2019-10-31 | 2019-05-03 | LSTANFI | 2019-05-03 | 2019-03-26 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP8591 | AMRCB |  | 100 | 055832190268591 | 139.7833 | 0 | 9642.98 | 8606.29 | 13.7 | 1022.99 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680926300 |  | 100308603 |  | 6716212N | 1960652 |  |  | 565 | EX | REPLACE SL W/19-0268562-00 | 2600B | BROADWAY | 1221 S BROADWAY ST | 067 | LEX | 2019-05-07 | U126309 | U131066 | 2019-02-12 | 2019-12-31 |  |  | JAMIE LYNN | 2019-05-03 | 2019-05-03 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.1833 | 2 | 7134.8 | 626.09 | 987.65 | 285.06 | 5236 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19691291300 |  | 100354900 |  | 7260280N |  |  |  | 566 | EX | DEMO / ABANDON / RI 03-27-19 | 2621P | WOOD | 227 WOOD ST | 161 | MAY | 2019-05-03 | RALLISO | U132002 | 2019-03-26 | 2019-04-26 | 2019-04-26 |  | RALLISO | 2019-05-03 | 2019-05-02 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 11.05 | 4 | 933.01 | 580.99 | 8.97 | 343.05 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19691293000 |  | 100355934 |  | 7260280N |  |  |  | 566 | EX | DEMO / ABANDON / RI 03-27-19 | 2621P | WOOD | 439 WOOD ST | 161 | MAY | 2019-05-06 | U125208 | U132002 | 2019-03-26 | 2019-04-26 | 2019-04-26 |  | SDADAMS | 2019-05-03 | 2019-04-29 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 5.3167 | 3 | 346 | 287.64 | 41.12 | 17.24 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19695058400 |  | 100315269 |  | 6716208C |  |  |  | 566 | EX | DEMO / ABANDON W/500439316 | 2621P | STATE | 129 STATE ST B | 067 | LEX | 2019-05-03 | DBANKS | U125208 | 2019-04-05 | 2019-05-03 | 2019-05-05 |  | DBANKS | 2019-05-03 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.033333 | 1 | 1.74 | 1.63 | 0 | 0.11 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19695058800 |  | 500439316 |  | 6716208C |  |  |  | 566 | EX | DEMO / ABANDON / RI 04-20-19 | 2621P | STATE | 129 STATE ST A | 067 | LEX | 2019-05-06 | U125208 | U125208 | 2019-04-05 | 2019-05-03 | 2019-05-05 |  | DBANKS | 2019-05-03 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.1 | 1 | 2474.27 | 333.41 | 0 | 20 | 2120.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19698730800 |  | 100452808 |  | 6716208H |  |  |  | 566 | EX | DEMO / ABANDON / RA 04-30-19 | 2621P | COLLEGE | 1510 COLLEGE WY UK 177 | 067 | LEX | 2019-05-06 | U125208 | U132002 | 2019-04-18 | 2019-05-29 | 2019-06-19 |  | ASNICHO | 2019-05-03 | 2019-05-03 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 14.3167 | 3 | 827.81 | 702.72 | 82.95 | 42.14 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19701570700 |  | 100264326 |  | 7356260M |  | U130193 |  | 566 | EX | ABANDON SVC LINE | 2621P | CENTRAL | 1116 CENTRAL AV | 019 | ASH | 2019-05-03 | MCOLLET | U130193 | 2019-04-30 |  |  |  | MCOLLET | 2019-05-03 | 2019-04-30 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 15.1667 | 4 | 1913.72 | 906.26 | 27.89 | 721.49 | 258.08 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19703169600 |  | 501254824 |  | 730192P |  |  |  | 565 | EX | INSTALL NEW LINE | 2621P | SYCAMORE | 65 SYCAMORE | 159 | INE | 2019-05-03 | BBMULLI | U125964 | 2019-05-03 | 2019-05-10 |  |  | BBMULLI | 2019-05-03 | 2019-05-03 |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26330031 | 21.2167 | 3 | 1382.5 | 1150.88 | 0 | 231.62 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19703301600 |  | 100355933 |  | 7260280N |  | U131367 |  | 566 | EX | ABAN SERVICE LINE | 2621P | WOOD | 441 WOOD ST | 161 | MAY | 2019-05-06 | U125208 | U131367 | 2019-05-03 | 2019-05-03 |  |  | SDADAMS | 2019-05-03 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 1.4833 | 1 | 138.05 | 80.04 | 53.2 | 4.81 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19703471700 |  | 100332131 |  | 6720212N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D000064 | 2621P | MEMORY | 327 MEMORY LN | 067 | LEX | 2019-05-06 | U125208 | U131168 | 2019-05-03 | 2019-05-03 | 2019-05-03 |  | RVANDER | 2019-05-03 | 2019-05-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 47.6167 | 8 | 2599.44 | 2166.52 | 62.35 | 129.97 | 240.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18026767000 |  |  |  | 7240204B | 1852103 | BKSLONE |  | 575 | EX | ACQUIRE LAND FOR SCADA BUILD. | 2600E | LEVEE | LEVEE RD | 173 | MT | 2020-01-20 | U462463 | U131369 | 2018-04-12 | 2019-12-30 | 2019-12-31 | 2019-05-04 | BRYAN SLONE FOR CHRIS DAVIS | 2019-05-04 |  |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00575 | 3200575 |  |  | WP7670 |  |  | 100 | 057532180267670 |  | 1 | 15516.89 | 0 | 0 | 6200 | 9198.93 | 0 | 117.96 | 0
KY | KY - WEST | 2623 | 19703485900 |  | 100404266 |  | 6704208A |  |  |  | 565 | EX | GRADE 1 REPLACE | 2621P | RAVENWOOD | 129 RAVENWOOD RD | 239 | VER | 2019-05-04 | LSTANFI | U129939 | 2019-05-04 | 2019-05-04 | 2019-05-04 |  | LSTANFI | 2019-05-04 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 11.05 | 4 | 660.29 | 622.92 | 0 | 37.37 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 17538698400 |  | 100272361 |  | 6684228N |  |  |  | 566 | EX | ABANDON SL FOR DEMO PS MAILBOX | 2621P | OWSLEY | 301 OWSLEY AV | 073 | FRA | 2019-05-06 | CDESPAI | U130154 | 2017-08-29 | 2019-05-06 |  |  | CDESPAI | 2019-05-06 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 2.0667 | 1 | 1000.45 | 112.9 | 65.73 | 181.92 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572291400 |  | 100279810 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 176 SUNSET DR | 073 | FRA | 2019-05-14 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1902.8 | 0 | 0 | 0 | 1902.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572292700 |  | 100279804 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 188 SUNSET DR | 073 | FRA | 2019-05-14 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1592.99 | 0 | 0 | 0 | 1592.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18663634000 |  | 100335600 |  | 6716220C |  |  |  | 566 | EX | DEMO / ABANDON / RA 01-02-19 | 2621P | IRON WORKS | 3250 IRON WORKS PK 2791 | 067 | LEX | 2019-05-06 | LSTANFI | U130722 | 2018-12-21 | 2019-05-06 |  |  | LSTANFI | 2019-05-06 | 2019-01-03 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 14.7333 | 8 | 783.36 | 737.97 | 0 | 45.39 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18663638200 |  | 100335586 |  | 6716220C |  |  |  | 566 | EX | DEMO / ABANDON / RI 04-24-19 | 2621P | IRON WORKS | 3250 IRON WORKS PK 3289 | 067 | LEX | 2019-05-06 | LSTANFI | U130722 | 2018-12-21 | 2019-05-06 |  |  | LSTANFI | 2019-05-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.9333 | 4 | 329.75 | 311.05 | 0 | 18.7 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678770300 |  | 100299357 |  | 6716216N | 1855322 |  |  | 565 | EX | REPLACE SL/18026792400/ | 2600B | BOILING SPRING | 237 BOILING SPRING DR | 067 | LEX | 2019-05-06 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-05-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.45 | 1 | 989.23 | 132.77 | 0 | 57.77 | 798.69 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680075400 |  | 100320155 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | TAHOMA | 239 TAHOMA RD | 067 | LEX | 2019-05-06 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-05-06 | 2019-05-06 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.5833 | 1 | 2686.75 | 90.72 | 0 | 37.56 | 2558.47 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680075500 |  | 100320143 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | TAHOMA | 240 TAHOMA RD | 067 | LEX | 2019-05-06 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-05-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.16667 | 1 | 2392.19 | 10.35 | 0 | 4.28 | 2377.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19686064200 |  | 100295676 |  | 6716216K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D193322 | 2621P | BOXWOOD | 922 BOXWOOD CT | 067 | LEX | 2019-05-06 | DBANKS | U125208 | 2019-03-05 | 2019-05-06 | 2021-03-31 |  | DBANKS | 2019-05-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.8833 | 1 | 2132.02 | 268.27 | 256.35 | 16.09 | 1591.31 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689095500 |  | 100239624 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | MAPLE | 102 MAPLE ST | 089 | RUS | 2019-05-06 | U461496 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ROCKIE MULLINS | 2019-05-06 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.21667 | 1 | 966.1 | 11.69 | 0 | 5.19 | 949.22 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19691288300 |  | 100354899 |  | 7260280N |  |  |  | 566 | EX | DEMO / ABANDON / RI 03-27-19 | 2621P | WOOD | 231 WOOD ST | 161 | MAY | 2019-05-06 | SDADAMS | U132002 | 2019-03-26 | 2019-04-26 | 2019-04-26 |  | SDADAMS | 2019-05-06 | 2019-05-06 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 9.85 | 2 | 584.03 | 533.13 | 18.91 | 31.99 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19694307400 |  | 100335895 |  | 6720212K |  |  |  | 566 | EX | DEMO / ABANDON / RA 04-16-19 | 2621P | LOUDON | 701 E LOUDON AV | 067 | LEX | 2019-05-06 | LMCDONA | U132002 | 2019-04-03 | 2019-05-03 | 2019-05-03 |  | LMCDONA | 2019-05-06 | 2019-04-29 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 33.2833 | 7 | 2740.49 | 1592.23 | 37.02 | 95.16 | 1016.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19695968900 |  | 100407983 |  | 6720220M |  |  |  | 566 | EX | DEMO / ABANDON / RA 04-25-19 | 2621P | NEWTOWN | 2099 NEWTOWN PK 2150 | 067 | LEX | 2019-05-07 | U125208 | U132002 | 2019-04-10 | 2019-05-10 | 2019-05-10 |  | LSTANFI | 2019-05-06 | 2019-05-01 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 25.3167 | 8 | 1204.16 | 1135.99 | 0 | 68.17 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19698105400 |  | 100439645 |  | 6684228N |  |  |  | 565 | EX | REPLACE SERV W/LCB | 2621P | OWSLEY | 305 OWSLEY AV | 073 | FRA | 2019-05-06 | CDESPAI | U125208 | 2019-04-17 | 2019-04-29 | 2019-04-29 |  | CDESPAI | 2019-05-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.8667 | 1 | 3144.87 | 263.73 | 518.63 | 425.05 | 1937.46 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19703546800 |  | 100351681 |  | 6744208O |  |  |  | 566 | EX | RETIRE SERVICE LINE - LEAKAGE | 2621P | HAYS | 29 HAYS ST | 049 | WIN | 2019-05-09 | U125208 | U130193 | 2019-05-06 | 2019-04-30 | 2019-04-30 |  | RJJOHNS | 2019-05-06 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26290043 | 4.8667 | 2 | 250.9 | 236.69 | 0 | 14.21 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703562500 |  | 100421388 |  | 6688228N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SADDLEBACK | 1309 SADDLEBACK TL | 073 | FRA | 2019-05-07 | U125208 | U130193 | 2019-05-06 | 2019-06-21 | 2020-12-31 |  | MCRAIG | 2019-05-06 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 14.1667 | 2 | 1803.61 | 796.68 | 206 | 47.75 | 753.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19703631300 |  | 100335587 |  | 6716220C |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | IRON WORKS | 3250 IRON WORKS PK 3287 | 067 | LEX | 2019-05-07 | U125208 | U130193 | 2019-05-06 | 2019-05-06 |  |  | LSTANFI | 2019-05-06 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.6667 | 4 | 999.98 | 747.93 | 202.92 | 49.13 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 17569348500 |  | 100311968 | 21 | 6716208I |  |  |  | 565 | EX | REPLACE S/L - BY 01/12/18 JTOY | 2621P | PASADENA | 462 PASADENA DR | 067 | LEX | 2019-05-07 | TGNELSO | NRICHIE | 2017-12-21 | 2017-12-28 | 2018-01-12 |  | TGNELSO | 2019-05-07 | 2019-02-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 48.9333 | 13 | 2818.18 | 2419.09 | 0 | 399.09 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572292000 |  | 100279807 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 182 SUNSET DR | 073 | FRA | 2019-05-14 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-07 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1776.41 | 0 | 0 | 0 | 1776.41 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572292100 |  | 100279792 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 183 SUNSET DR | 073 | FRA | 2019-05-14 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-07 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1776.5 | 0 | 0 | 0 | 1776.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572292400 |  | 100279793 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 185 SUNSET DR | 073 | FRA | 2019-05-14 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-07 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1776.5 | 0 | 0 | 0 | 1776.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18652218900 |  | 100320307 |  | 6716208G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HILTONIA | 118 HILTONIA PR | 067 | LEX | 2019-05-07 | DBANKS | U125208 | 2018-10-22 | 2019-04-18 | 2020-10-31 |  | DBANKS | 2019-05-07 | 2019-01-28 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.8833 | 8 | 2397.09 | 424.08 | 199.48 | 24.91 | 1748.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673609800 |  | 100311727 |  | 6712208L | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2924 CLAYS MILL RD | 067 | LEX | 2019-05-07 | U461475 | U131066 | 2019-01-30 | 2019-11-27 |  |  | D SORRELL | 2019-05-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 5.05 | 1 | 2613.33 | 274.46 | 283.52 | 119.1 | 1936.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678770900 |  | 100299353 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 249 BOILING SPRING DR | 067 | LEX | 2019-05-07 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-05-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.1 | 1 | 1517.8 | 5.98 | 0 | 2.6 | 1509.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678771200 |  | 100299291 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 256 BOILING SPRING DR | 067 | LEX | 2019-05-07 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-05-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.0333 | 1 | 1980.1 | 380.97 | 0 | 165.74 | 1433.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678771500 |  | 100299350 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 261 BOILING SPRING DR | 067 | LEX | 2019-05-08 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-05-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.13333 | 1 | 1423.48 | 7.59 | 0 | 3.31 | 1412.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680075600 |  | 100320154 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | TAHOMA | 241 TAHOMA RD | 067 | LEX | 2019-05-07 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-05-07 | 2019-05-07 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.3 | 1 | 3204.11 | 246.91 | 0 | 102.2 | 2855 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680075700 |  | 100320144 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | TAHOMA | 242 TAHOMA RD | 067 | LEX | 2019-05-07 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-05-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.9167 | 1 | 2446.18 | 167.69 | 0 | 69.4 | 2209.09 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689095400 |  | 100239626 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | MAPLE | 101 MAPLE ST | 089 | RUS | 2019-05-07 | U461496 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ROCKIE MULLINS | 2019-05-07 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.28333 | 1 | 970.7 | 14.89 | 0 | 6.59 | 949.22 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689095600 |  | 100239625 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | MAPLE | 102< MAPLE ST | 089 | RUS | 2019-05-07 | U461496 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ROCKIE MULLINS | 2019-05-07 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.23333 | 1 | 1417.06 | 13.3 | 0 | 5.87 | 1397.89 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691271700 |  | 100305981 |  | 6712212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D107226 | 2621P | MAYWICK VIEW | 1658 MAYWICK VIEW LN 1 | 067 | LEX | 2019-05-09 | U125208 | U125208 | 2019-03-26 | 2019-09-18 | 2021-03-31 |  | DBANKS | 2019-05-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.45 | 1 | 3521.43 | 188.88 | 80.62 | 11.33 | 3240.6 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19698101300 |  | 100459474 |  | 6696212G |  |  |  | 565 | EX | REPLACE SERV W/LCB | 2621P | SPRING RUN | 153 SPRING RUN ST | 239 | VER | 2019-05-07 | CDESPAI | U125208 | 2019-04-17 | 2049-12-31 |  |  | CDESPAI | 2019-05-07 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 7.35 | 1 | 3401.7 | 399.33 | 161.41 | 643.69 | 2197.27 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19701963400 |  | 100348228 |  | 6748208I |  |  |  | 566 | EX | ABANDON / RI 05-06-19 | 2621P | HILL | 337 HILL ST | 049 | WIN | 2019-05-07 | RJJOHNS | U125208 | 2019-05-01 | 2019-05-06 |  |  | RJJOHNS | 2019-05-07 | 2019-05-06 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 11.2333 | 4 | 597.86 | 547.42 | 17.6 | 32.84 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19703577800 |  | 500610157 |  | 6744208O |  |  |  | 566 | EX | ABANDON SVC LINE | 2621P | HAYS | 29< HAYS ST | 049 | WIN | 2019-05-07 | RJJOHNS | U130193 | 2019-05-06 | 2019-05-06 |  |  | RJJOHNS | 2019-05-07 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.3667 | 2 | 70.25 | 66.25 | 0 | 4 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19703612900 |  | 100289968 |  | 6720212C |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | NORTHWOOD | 349 NORTHWOOD DR | 067 | LEX | 2019-05-09 | U125208 | U130193 | 2019-05-06 | 2019-05-06 | 2019-05-06 |  | JENSMIN | 2019-05-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.86667 | 1 | 1611.34 | 57.1 | 203.63 | 58.38 | 1292.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19703926700 |  | 100312980 |  | 6716208E |  |  |  | 566 | EX | RETIRE SERVICE LINE - LEAKAGE | 2621P | ROSEMILL | 566 ROSEMILL DR | 067 | LEX | 2019-05-07 | JENSMIN | U130193 | 2019-05-07 | 2019-05-07 |  |  | JENSMIN | 2019-05-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 1.9167 | 1 | 1784.33 | 123.86 | 18.91 | 126.66 | 1514.9 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19703927000 |  | 100259678 |  | 600000000 |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MARKET | 1112 MARKET ST | 089 | WOR | 2019-05-09 | U125208 | U130193 | 2019-05-07 | 2019-05-02 | 2019-05-02 |  | MCOLLET | 2019-05-07 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 10.0667 | 2 | 1437.36 | 704.52 | 174.23 | 558.61 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19704025500 |  | 100300324 |  | 6716212G | 1746168 |  |  | 565 | EX | RPLC SL/17026714900/ | 2600B | HIGH | 859 W HIGH ST 1F | 067 | LEX | 2019-05-07 | U461439 | U131279 | 2019-05-07 | 2019-12-31 |  |  | A PARRIS | 2019-05-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.86667 | 1 | 1655.04 | 47.33 | 0 | 20.72 | 1586.99 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572290800 |  | 100279813 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 170 SUNSET DR | 073 | FRA | 2019-05-14 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-08 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1606.5 | 0 | 0 | 0 | 1606.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572291000 |  | 100279812 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 172 SUNSET DR | 073 | FRA | 2019-05-14 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-08 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1776.41 | 0 | 0 | 0 | 1776.41 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572291300 |  | 100279788 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 175 SUNSET DR | 073 | FRA | 2019-05-14 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-08 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1776.5 | 0 | 0 | 0 | 1776.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572291500 |  | 100279789 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 177 SUNSET DR | 073 | FRA | 2019-05-14 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-08 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1776.5 | 0 | 0 | 0 | 1776.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572291700 |  | 100279790 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 179 SUNSET DR | 073 | FRA | 2019-05-14 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-08 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1776.5 | 0 | 0 | 0 | 1776.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572291900 |  | 100279791 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 181 SUNSET DR | 073 | FRA | 2019-05-14 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-08 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1776.5 | 0 | 0 | 0 | 1776.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18577388700 |  | 100300320 |  | 6716212G | 1746168 |  |  | 565 | EX | RPLC SL/17026714900/ | 2600B | HIGH | 853 W HIGH ST 2F | 067 | LEX | 2019-05-08 | HROGERS | U131066 | 2018-01-26 | 2019-12-31 |  |  | MARK ROGERS | 2019-05-08 | 2019-05-07 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.85 | 2 | 2325.22 | 361.88 | 219.55 | 156.8 | 1586.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18577396300 |  | 100300327 |  | 6716212G | 1746168 |  |  | 565 | EX | REPLACE SL W/17026714900 | 2600B | HERLIHY | 820 HERLIHY ST | 067 | LEX | 2019-05-09 | HROGERS | U131066 | 2018-01-26 | 2019-12-26 |  |  | MARK ROGERS | 2019-05-08 | 2019-05-08 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.45 | 2 | 1324.05 | 181.58 | 217.32 | 81.22 | 843.93 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673609700 |  | 100311729 |  | 6712208L | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2920 CLAYS MILL RD B-1FL | 067 | LEX | 2019-05-08 | U461475 | U131066 | 2019-01-30 | 2019-11-27 |  |  | D SORRELL | 2019-05-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 4.3667 | 1 | 2442.75 | 236.94 | 187.03 | 102.81 | 1915.97 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678772100 |  | 100299295 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 276 BOILING SPRING DR | 067 | LEX | 2019-05-08 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-05-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.1667 | 1 | 1931.31 | 279.64 | 0 | 121.64 | 1530.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680075900 |  | 100320145 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | TAHOMA | 244 TAHOMA RD | 067 | LEX | 2019-05-08 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-05-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.9 | 1 | 4501.53 | 338.77 | 0 | 140.23 | 4022.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680954800 |  | 500774397 |  | 6712208L | 1636363 |  |  | 566 | EX | RETIRE S/L W/17-0267331-00 | 2600B | CLAYS MILL | 2914 CLAYS MILL RD CABLE | 067 | LEX | 2019-05-08 | U461475 | U461383 | 2019-02-12 | 2019-08-01 | 2019-08-01 |  | D SORRELL | 2019-05-08 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.26667 | 1 | 20.26 | 14.13 | 0 | 6.13 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19683746100 |  | 100317269 |  | 6716204J |  |  |  | 565 | EX | REPLACE SERVICE LINE - D221862 | 2621P | MANITOBA | 176 MANITOBA LN | 067 | LEX | 2019-05-08 | DBANKS | U125208 | 2019-02-27 | 2019-05-08 | 2021-02-28 |  | DBANKS | 2019-05-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.1333 | 1 | 2220.31 | 116.09 | 162.53 | 6.97 | 1934.72 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19689080500 |  | 100241912 |  | 7344168G | 1852308 |  |  | 565 | EX | RPLC SL/18026768600/ | 2600B | KY RT 1428 | 181 KY RT 1428 | 071 | LNC | 2019-05-08 | MBLANKE | U131066 | 2019-03-18 | 2019-11-27 |  |  | MBLANKE | 2019-05-08 |  |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 0.26667 | 1 | 1580.94 | 15.15 | 0 | 6.19 | 1559.6 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19689080600 |  | 100241911 |  | 7344168H | 1852308 |  |  | 565 | EX | RPLC SL/18026768600/ | 2600B | KY RT 1428 | 189 KY RT 1428 | 071 | LNC | 2019-05-08 | MBLANKE | U131066 | 2019-03-18 | 2019-11-27 |  |  | MBLANKE | 2019-05-08 |  |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 0.98333 | 1 | 2250.34 | 57.02 | 0 | 23.34 | 2169.98 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19689080800 |  | 100432784 |  | 7344168G | 1852308 |  |  | 565 | EX | RPLC SL/18026768600/ | 2600B | KY RT 1428 | 203 KY RT 1428 | 071 | LNC | 2019-05-08 | MBLANKE | U131066 | 2019-03-18 | 2019-11-27 |  |  | MBLANKE | 2019-05-08 |  |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 0.1 | 1 | 957.45 | 5.85 | 0 | 2.38 | 949.22 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689095700 |  | 100239623 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | MAPLE | 103 MAPLE ST | 089 | RUS | 2019-05-08 | U461496 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ROCKIE MULLINS | 2019-05-08 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.28333 | 1 | 1900.48 | 15.42 | 0 | 6.81 | 1878.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19699947900 |  | 100341206 |  | 7240216L |  |  |  | 566 | EX | DEMO / ABANDON / RI 04-29-19 | 2621P | WOODBURN | 1305 WOODBURN DR | 173 | MT | 2019-05-10 | U125208 | U132002 | 2019-04-23 | 2019-06-03 | 2019-06-24 |  | DENNING | 2019-05-08 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 15.7 | 3 | 980.8 | 725.12 | 0 | 255.68 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19704277400 |  | 100316118 |  | 6716208F |  |  |  | 565 | EX | REPLACE SERVICE - MOVE METER | 2621P | PIN OAK | 218 PIN OAK DR | 067 | LEX | 2019-05-08 | DBANKS | U125208 | 2019-05-08 | 2019-05-09 |  |  | DBANKS | 2019-05-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.0167 | 1 | 2454.16 | 110.04 | 216.66 | 6.6 | 2120.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19704322500 |  | 100333985 |  | 600000000 |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | LIBERTY | 1032 LIBERTY RD 1FL | 067 | LEX | 2019-05-08 | JENSMIN | U130193 | 2019-05-08 | 2019-05-08 | 2019-05-08 |  | JENSMIN | 2019-05-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.85 | 1 | 4044.03 | 250.97 | 243.47 | 256.65 | 3292.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19704354300 |  | 100295636 |  | 6716216G |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | OAKWOOD | 1060 OAKWOOD DR | 067 | LEX | 2019-05-08 | DBANKS | U131010 | 2019-05-08 | 2019-05-08 | 2019-05-08 |  | DBANKS | 2019-05-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.5 | 1 | 1611.49 | 136.31 | 214.91 | 8.2 | 1252.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19704387200 |  | 100310645 |  | 6712208L |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | CECIL | 612 CECIL WY | 067 | LEX | 2019-05-10 | U125208 | U130193 | 2019-05-08 | 2019-05-08 | 2019-05-08 |  | DBANKS | 2019-05-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.2333 | 1 | 1677.27 | 122.13 | 94.97 | 7.32 | 1452.85 | 0 | 0 | 0
KY | KY - WEST | 2623 | 17534182300 |  | 100281674 | 22 | 6712232O |  |  |  | 565 | EX | REPL-MOV MTR-NO AXS TO SHUTOFF | 2621P | POPLAR | 627 POPLAR ST | 209 | GEO | 2019-05-09 | CDESPAI | JDBRADF | 2017-08-16 | 2019-05-08 |  |  | CDESPAI | 2019-05-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.5 | 1 | 3577.11 | 352.65 | 232.15 | 568.47 | 2423.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572290500 |  | 100279815 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 166 SUNSET DR | 073 | FRA | 2019-05-14 | U461375 | U131066 | 2018-01-04 | 2019-12-31 | 2020-10-31 |  | LARRY BROWN | 2019-05-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572290700 |  | 100279785 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 169 SUNSET DR | 073 | FRA | 2019-05-14 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18601922600 |  | 100307385 |  | 6716212G | 1746168 |  |  | 565 | EX | RPLC SL/17026714900/ | 2621P | HIGH | 848 W HIGH ST 1F-A | 067 | LEX | 2019-05-10 | HROGERS | U125964 | 2018-04-11 | 2018-11-30 |  |  | MARK ROGERS | 2019-05-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.1 | 1 | 1148.34 | 110.22 | 141.73 | 49.28 | 847.11 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026870000 |  |  |  | 6716208D | 1962980 | U461383 |  | 557 | EX | INSTALL 60' OF 3"BSLP MAIN | 2621P | COOPER | 739 COOPER DR | 067 | LEX | 2019-06-11 | U123258 | U461383 | 2019-04-10 | 2020-11-19 | 2020-11-24 | 2019-04-18 | JENSMIN | 2019-05-09 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP8700 | AMRCB |  | 100 | 055732190268700 | 0.4 | 61 | 2756.75 | 26.59 | 658.56 | 27.18 | 1680.26 | 0 | 4.55 | 359.61 | 61
KY | KY - WEST | 2621 | 19026870100 |  |  |  | 6716208D | 1962980 | U461383 |  | 558 | EX | RETIRE 60' OF 3"BSLP MAIN | 2621P | COOPER | 739 COOPER DR | 067 | LEX | 2019-06-11 | U123258 | U461383 | 2019-04-10 | 2020-11-24 | 2020-11-24 | 2019-04-18 | JENSMIN | 2019-05-09 | 2019-04-18 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP8701 | AMRCB |  | 100 | 055832190268701 | 14.65 | 0 | 9332.65 | 1349.88 | 0 | 1018.23 | 6964.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678771300 |  | 100299351 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 257 BOILING SPRING DR | 067 | LEX | 2019-05-09 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-05-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.25 | 1 | 1365.43 | 284.52 | 0 | 123.76 | 957.15 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19688284000 |  | 100309784 |  | 6712208H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D000105 | 2621P | HILL N DALE | 670 HILL N DALE RD | 067 | LEX | 2019-05-09 | DBANKS | U125208 | 2019-03-14 | 2019-05-07 | 2021-03-31 |  | DBANKS | 2019-05-09 | 2019-05-07 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.7167 | 3 | 2241.75 | 371.23 | 256.95 | 22.26 | 1591.31 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19689081000 |  | 100241917 |  | 7344168G | 1852308 |  |  | 565 | EX | RPLC SL/18026768600/ | 2600B | KY ROUTE 1428 | 88 KY ROUTE 1428 | 071 | PRE | 2019-05-09 | MBLANKE | U131066 | 2019-03-18 | 2019-11-27 |  |  | MBLANKE | 2019-05-09 |  |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 0.2 | 1 | 1575.98 | 11.62 | 0 | 4.76 | 1559.6 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689095900 |  | 100239620 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | MAPLE | 105 MAPLE ST | 089 | RUS | 2019-05-09 | U461496 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ROCKIE MULLINS | 2019-05-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1429.58 | 0 | 0 | 0 | 1429.58 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689097000 |  | 100239612 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | POPLAR | 110 POPLAR ST | 089 | RUS | 2019-05-09 | U461496 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ROCKIE MULLINS | 2019-05-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0 | 1 | 949.22 | 0 | 0 | 0 | 949.22 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19704649700 |  | 100241913 |  | 7344168G | 1852308 |  |  | 565 | EX | REPLACE W/ 18026768600 | 2600B | KY ROUTE 1428 | 170 KY ROUTE 1428 | 071 | PRE | 2019-05-09 | MBLANKE | U125768 | 2019-05-09 | 2049-12-31 |  |  | MBLANKE | 2019-05-09 |  |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 1.3833 | 1 | 1977.94 | 80.28 | 0 | 32.87 | 1864.79 | 0 | 0 | 0
KY | KY - EAST | 2633 | 06658533900 |  | 100264680 | 09 | 7348168F |  |  |  | 566 | EX | ABANDON/ IDLE PRIOR 02-25-2008 | 2621P | TURKEY CREEK | 863 TURKEY CREEK RD | 195 | S W | 2019-05-10 | BBMULLI | LDAVIS | 2006-08-29 | 2020-12-31 |  |  | BBMULLI | 2019-05-10 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 11.35 | 2 | 771.66 | 616.98 | 0 | 154.68 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 10858707500 |  | 100266281 |  | 7360152J | 0994083 |  |  | 566 | EX | ABANDON/ RI 8-2010/ DEMOLITION | 2621P | CHURCH | 163 CHURCH ST | 195 | COA | 2019-05-15 | U125208 | U123166 | 2010-09-02 | 2020-12-31 |  |  | JAHOWARD | 2019-05-10 | 2019-05-08 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.8333 | 2 | 222.04 | 209.46 | 0 | 12.58 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 13181265200 |  | 100266272 | 30 | 7360152J |  |  |  | 566 | EX | ABANDON / RI 03-04-11 | 2621P | CHURCH | 105 CHURCH ST | 195 | COA | 2019-05-16 | U125208 | DHANSFO | 2013-12-13 | 2049-12-31 |  |  | JAHOWARD | 2019-05-10 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 3.4833 | 1 | 197.26 | 186.08 | 0 | 11.18 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572290100 |  | 100279818 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 160 SUNSET DR | 073 | FRA | 2019-05-14 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2559.74 | 0 | 0 | 0 | 2559.74 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572290200 |  | 100279781 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 161 SUNSET DR | 073 | FRA | 2019-05-14 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2729.74 | 0 | 0 | 0 | 2729.74 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572290600 |  | 100279784 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 167 SUNSET DR | 073 | FRA | 2019-05-14 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572290900 |  | 100279786 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 171 SUNSET DR | 073 | FRA | 2019-05-14 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18613622900 |  | 100307383 |  | 6716212G | 1746168 |  |  | 565 | EX | REPLACE SL W/17026714900 | 2600B | HIGH | 852 W HIGH ST | 067 | LEX | 2019-05-10 | HROGERS | U131066 | 2018-05-22 | 2019-12-31 |  |  | MARK ROGERS | 2019-05-10 | 2019-05-09 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.3667 | 2 | 3637.27 | 596.65 | 218.28 | 266.88 | 2555.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673609600 |  | 100311731 |  | 6712208L | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2916 CLAYS MILL RD | 067 | LEX | 2019-05-10 | U461475 | U131066 | 2019-01-30 | 2019-11-27 |  |  | D SORRELL | 2019-05-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 10.5 | 1 | 4422.12 | 570.63 | 259.04 | 247.61 | 3344.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678793300 |  | 100299345 |  | 6716216N | 1855322 |  |  | 565 | EX | REPLACE SL W/18026792400 | 2600B | BOILING SPRING | 277 BOILING SPRING DR | 067 | LEX | 2019-05-10 | U461467 | U131066 | 2019-02-01 | 2019-12-31 |  |  | D REFFETT | 2019-05-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.9 | 1 | 1900.53 | 102.97 | 0 | 44.79 | 1752.77 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680075800 |  | 100320153 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | TAHOMA | 243 TAHOMA RD | 067 | LEX | 2019-05-10 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-05-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.4833 | 1 | 4335.59 | 200.38 | 0 | 82.95 | 4052.26 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19692273500 |  | 100311146 |  | 6712208O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094073 | 2621P | CORNWALL | 3240 CORNWALL DR | 067 | LEX | 2019-05-10 | DBANKS | U125208 | 2019-03-29 | 2019-05-10 | 2021-03-31 |  | DBANKS | 2019-05-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.9833 | 1 | 2046.15 | 217.36 | 224.45 | 13.03 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19692274400 |  | 100311115 |  | 6712208O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094074 | 2621P | CORNWALL | 3263 CORNWALL DR | 067 | LEX | 2019-05-10 | DBANKS | U125208 | 2019-03-29 | 2019-05-10 | 2021-03-31 |  | DBANKS | 2019-05-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.6667 | 1 | 1969.56 | 145.63 | 223.89 | 8.73 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19695059800 |  | 100315147 |  | 6716212O |  |  |  | 566 | EX | DEMO / ABANDON / RI 04-20-19 | 2621P | TRANSCRIPT | 225 TRANSCRIPT AV | 067 | LEX | 2019-05-10 | TNEAL | U125208 | 2019-04-05 | 2019-05-03 | 2019-05-05 |  | TNEAL | 2019-05-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.5 | 3 | 1107.29 | 786.07 | 96.62 | 47.17 | 177.43 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19702819500 |  | 100261096 |  | 7356252D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D188718 | 2621P | 6TH | 1818 6TH ST | 019 | ASH | 2019-05-15 | U125208 | U125208 | 2019-05-02 | 2019-05-03 | 2019-05-23 |  | MCOLLET | 2019-05-10 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 16 | 2 | 2486.93 | 914.5 | 196.19 | 1053.64 | 322.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19705060300 |  | 100316213 |  | 6716208F |  |  |  | 565 | EX | REPALCE SVL | 2621P | KOSTER | 206 KOSTER DR | 067 | LEX | 2019-05-10 | JENSMIN | U131375 | 2019-05-10 | 2019-07-17 | 2021-01-31 |  | JENSMIN | 2019-05-10 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.6167 | 1 | 3742.43 | 493.45 | 320.5 | 504.64 | 2423.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 14217565700 |  | 100419212 |  | 6696220C | 0674080 |  |  | 566 | EX | METER ABN /MNFLD *** ALL ELEC | 2621P | OLD FRANKFORT | 2260 OLD FRANKFORT PK | 239 | MID | 2019-05-14 | U125208 | U125208 | 2014-05-02 | 2020-12-31 |  |  | MCRAIG | 2019-05-13 | 2019-03-21 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 5.6833 | 5 | 270.89 | 248.65 | 0 | 22.24 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572289900 |  | 100279779 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 157 SUNSET DR | 073 | FRA | 2019-05-14 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2729.74 | 0 | 0 | 0 | 2729.74 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572290300 |  | 100279782 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 163 SUNSET DR | 073 | FRA | 2019-05-14 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2729.74 | 0 | 0 | 0 | 2729.74 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572291100 |  | 100279787 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 173 SUNSET DR | 073 | FRA | 2019-05-14 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1776.5 | 0 | 0 | 0 | 1776.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572296400 |  | 100279816 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 156 SUNSET DR | 073 | FRA | 2019-05-14 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1776.41 | 0 | 0 | 0 | 1776.41 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18577388600 |  | 100300317 |  | 6716212G | 1746168 |  |  | 565 | EX | RPLC SL/17026714900/ | 2600B | HIGH | 849 W HIGH ST | 067 | LEX | 2019-05-14 | HROGERS | U131066 | 2018-01-26 | 2019-12-31 |  |  | MARK ROGERS | 2019-05-13 | 2019-05-13 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.6333 | 2 | 3793.86 | 452.87 | 191.68 | 202.57 | 2946.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026875500 |  |  |  | 6716208E | 1963675 | U461383 |  | 559 | EX | INSTALL 14' OF 4"PMMP MAIN | 2621P | CARDINAL | 610 CARDINAL LN | 067 | LEX | 2019-05-24 | U123258 | U461383 | 2019-05-07 | 2019-05-30 | 2019-06-01 | 2019-05-13 | JAMIE ENSMINGER | 2019-05-13 | 2019-05-09 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP8755 |  |  | 100 | 055932190268755 | 32.5333 | 64 | 16610.89 | 2132.23 | 554.67 | 1409.15 | 10324.82 | 0 | 26.89 | 2163.13 | 16
KY | KY - WEST | 2621 | 19026875600 |  |  |  | 6716208E | 1963675 | U461383 |  | 560 | EX | RETIRE 10' OF 4"PMMP MAIN | 2621P | CARDINAL | 610 CARDINAL LN | 067 | LEX | 2019-05-24 | U123258 | U461383 | 2019-05-07 | 2019-05-31 | 2019-06-01 | 2019-05-13 | JAMIE ENSMINGER | 2019-05-13 | 2019-05-13 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00560 | 3200560 |  |  | WP8756 |  |  | 100 | 056032190268756 | 1.3167 | 0 | 171.82 | 84.95 | 0 | 86.87 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678770100 |  | 100299359 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 233 BOILING SPRING DR | 067 | LEX | 2019-05-14 | U123111 | U131066 | 2019-02-01 | 2019-11-27 |  |  | LYN STAFFORD | 2019-05-13 | 2019-05-13 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.7667 | 2 | 2348.22 | 201.95 | 0 | 88.33 | 2057.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678770700 |  | 100299354 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 245 BOILING SPRING DR | 067 | LEX | 2019-05-13 | U123111 | U131066 | 2019-02-01 | 2019-11-27 |  |  | LYN STAFFORD | 2019-05-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.7667 | 1 | 1724.38 | 149.68 | 0 | 65.48 | 1509.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680077300 |  | 100320204 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | WILDWOOD | 1864 WILDWOOD AV | 067 | LEX | 2019-05-13 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-05-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.2167 | 1 | 3409.48 | 356.61 | 0 | 147.59 | 2905.28 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689097100 |  | 100239613 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | POPLAR | 112 POPLAR ST | 089 | RUS | 2019-05-13 | MBLANKE | U131066 | 2019-03-18 | 2019-11-27 |  |  | MBLANKE | 2019-05-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 4.4 | 3 | 1977.01 | 241.85 | 0 | 226.47 | 1508.69 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691967900 |  | 100306584 |  | 6716212I |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094776 | 2621P | SUMMERVILLE | 877 SUMMERVILLE DR | 067 | LEX | 2019-05-20 | U125208 | U125208 | 2019-03-28 | 2019-05-13 | 2021-03-31 |  | DBANKS | 2019-05-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.2333 | 1 | 2216.94 | 341.13 | 264.03 | 20.47 | 1591.31 | 0 | 0 | 0
KY | KY - EAST | 2633 | 06664989600 |  | 500128071 |  | 7384168F |  |  |  | 566 | EX | ABANDON/ IDLE PRIOR 02-25-2008 | 2621P | TURKEY CREEK | TURKEY CREEK RD | 195 | S W | 2019-05-20 | U125208 | U901436 | 2006-11-02 | 2049-12-31 |  |  | JCKIRK | 2019-05-14 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 12.9167 | 2 | 853.37 | 698.67 | 11.15 | 143.55 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572289600 |  | 100279777 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 153 SUNSET DR | 073 | FRA | 2019-05-15 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572289700 |  | 100279820 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 154 SUNSET DR | 073 | FRA | 2019-05-15 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572289800 |  | 100279778 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 155 SUNSET DR | 073 | FRA | 2019-05-15 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3292.91 | 0 | 0 | 0 | 3292.91 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572290000 |  | 100279819 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 158 SUNSET DR | 073 | FRA | 2019-05-15 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3179.21 | 0 | 0 | 0 | 3179.21 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572290400 |  | 100279817 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 164 SUNSET DR | 073 | FRA | 2019-05-15 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2559.74 | 0 | 0 | 0 | 2559.74 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572291200 |  | 100279811 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 174 SUNSET DR | 073 | FRA | 2019-05-15 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673609300 |  | 100310686 |  | 16712208L | 1636363 |  |  | 566 | EX | ABANDON SL/17026733100/ | 2600B | CLAYS MILL | 2913 CLAYS MILL RD | 067 | LEX | 2019-05-14 | U126602 | U131066 | 2019-01-30 | 2019-11-27 |  |  | DPAYTON | 2019-05-14 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.4333 | 2 | 935.15 | 293.64 | 1.37 | 73.11 | 567.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673609400 |  | 100432232 |  | 6712208L | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2914 CLAYS MILL RD | 067 | LEX | 2019-05-14 | U126602 | U131066 | 2019-01-30 | 2019-11-27 |  |  | DPAYTON | 2019-05-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 7.9667 | 2 | 2743.66 | 427.06 | 183.64 | 106.32 | 2026.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678771900 |  | 100299294 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 272 BOILING SPRING DR | 067 | LEX | 2019-06-10 | U125208 | U131066 | 2019-02-01 | 2019-11-27 |  |  | LYN STAFFORD | 2019-05-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2 | 1 | 1726.46 | 107.69 | 0 | 47.12 | 1571.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678794400 |  | 100299298 |  | 6716216N | 1855322 |  |  | 565 | EX | REPLACE SL W/18026792400 | 2600B | BOILING SPRING | 284 BOILING SPRING DR | 067 | LEX | 2019-05-14 | U123111 | U131066 | 2019-02-01 | 2019-12-31 |  |  | LYN STAFFORD | 2019-05-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.56667 | 1 | 2039.57 | 30.17 | 0 | 13.19 | 1996.21 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680076000 |  | 100320146 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | TAHOMA | 246 TAHOMA RD | 067 | LEX | 2019-05-14 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-05-14 | 2019-05-14 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.4 | 1 | 2366.83 | 367.48 | 0 | 152.11 | 1847.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680076300 |  | 100320148 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | TAHOMA | 250 TAHOMA RD | 067 | LEX | 2019-05-14 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-05-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.1167 | 1 | 2166.05 | 64.3 | 0 | 26.62 | 2075.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19688605500 |  | 100295567 |  | 6716216L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D193499 | 2621P | REDWOOD | 1051 REDWOOD DR | 067 | LEX | 2019-05-20 | U125208 | U125208 | 2019-03-15 | 2019-09-13 | 2021-03-31 |  | DBANKS | 2019-05-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.41667 | 1 | 2148.19 | 22.46 | 190.37 | 1.35 | 1934.01 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689097200 |  | 100239614 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | POPLAR | 114 POPLAR ST | 089 | RUS | 2019-05-14 | U461496 | U131066 | 2019-03-18 | 2019-11-27 |  |  | DAVID SKAGGS | 2019-05-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.56667 | 2 | 945.02 | 30.18 | 0 | 7.5 | 907.34 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689097300 |  | 100239617 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | POPLAR | 116 POPLAR ST | 089 | RUS | 2019-05-14 | U461496 | U131066 | 2019-03-18 | 2019-11-27 |  |  | DAVID SKAGGS | 2019-05-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.43333 | 2 | 980.17 | 24.79 | 0 | 6.16 | 949.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691270700 |  | 100457253 |  | 6720204O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | WOODFIELD | 2477 WOODFIELD CR | 067 | LEX | 2019-05-20 | U125208 | U125208 | 2019-03-26 | 2019-05-14 | 2021-03-31 |  | DBANKS | 2019-05-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.2833 | 1 | 2072.56 | 124.84 | 151.79 | 7.49 | 1788.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691624400 |  | 100460207 |  | 6720200A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | TIMBERWOOD | 3608 TIMBERWOOD LN | 067 | LEX | 2019-05-20 | U125208 | U125208 | 2019-03-27 | 2019-05-13 | 2021-03-31 |  | DBANKS | 2019-05-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.45 | 1 | 3540.93 | 132.54 | 163 | 7.95 | 3237.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19705585900 |  | 100322372 |  | 6720208A |  |  |  | 565 | EX | REPLACE/REROUTE SL 05/14/19 | 2621P | SUNSET | 809 SUNSET DR | 067 | LEX | 2019-05-14 | LMCDONA | U125208 | 2019-05-14 | 2019-05-14 |  |  | LMCDONA | 2019-05-14 | 2019-05-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.3833 | 5 | 921.36 | 869.19 | 0 | 52.17 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19705626000 |  | 100255155 |  | 7348156T |  |  |  | 566 | EX | ABANDON SVC | 2621P | KY ROUTE 1426 | 4327 KY ROUTE 1426 | 071 | DAN | 2019-06-10 | U125208 | U130193 | 2019-05-14 | 2019-05-14 |  |  | JAHOWARD | 2019-05-14 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.25 | 1 | 71.98 | 67.91 | 0 | 4.07 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19705635700 |  | 100264442 |  | 7356260M |  | U130193 |  | 565 | EX | REPLACE TO SVC LINE | 2621P | BATH | 841 BATH AV | 019 | ASH | 2019-05-20 | DYOUNG | U130193 | 2019-05-14 | 2019-05-14 | 2019-05-14 |  | MCOLLET | 2019-05-14 | 2019-05-14 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 19.4667 | 3 | 2043.4 | 1070.28 | 193.97 | 779.15 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19705674700 |  | 100310831 |  | 6712204C |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | SHASTA | 680 SHASTA CR | 067 | LEX | 2019-05-14 | DBANKS | U130193 | 2019-05-14 | 2019-05-14 | 2019-05-14 |  | DBANKS | 2019-05-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.1333 | 1 | 1911.43 | 116.62 | 143.31 | 7.01 | 1644.49 | 0 | 0 | 0
KY | KY - WEST | 2623 | 07689187800 |  | 100412474 |  | 6684228O |  |  |  | 566 | EX | LOCATE/ABANDON | 2621P | SPRINGHILL | 170 SPRINGHILL RD | 073 | FRA | 2019-05-20 | U125208 | U903504 | 2007-06-01 | 2019-05-13 |  |  | CDESPAI | 2019-05-15 | 2019-05-13 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 20.75 | 3 | 14112.1 | 1126.41 | 0 | 1815.57 | 11170.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 17557491400 |  | 100299296 | 24 | 6716216N |  |  |  | 565 | EX | MOVE METER - REPLACE SERV | 2621P | BOILING SPRING | 280 BOILING SPRING DR | 067 | LEX | 2019-05-15 | U123111 | LSTANFI | 2017-10-25 | 2018-01-25 |  |  | LYN STAFFORD | 2019-05-15 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.2333 | 1 | 1817.42 | 281.66 | 0 | 123.18 | 1412.58 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572288900 |  | 100279773 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 145 SUNSET DR | 073 | FRA | 2019-05-16 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2064.97 | 0 | 0 | 0 | 2064.97 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572289000 |  | 100279823 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 146 SUNSET DR | 073 | FRA | 2019-05-16 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1776.41 | 0 | 0 | 0 | 1776.41 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572289200 |  | 100279822 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 148 SUNSET DR | 073 | FRA | 2019-05-16 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1894.97 | 0 | 0 | 0 | 1894.97 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572289300 |  | 100279775 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 149 SUNSET DR | 073 | FRA | 2019-05-16 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572289400 |  | 100279821 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 150 SUNSET DR | 073 | FRA | 2019-05-16 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572289500 |  | 100279776 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 151 SUNSET DR | 073 | FRA | 2019-05-16 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-15 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1902.8 | 0 | 0 | 0 | 1902.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18577395800 |  | 500220800 |  | 6716212K | 1746168 |  |  | 565 | EX | RPLC SL/17026714900/ | 2600B | PINE | 736 PINE ST | 067 | LEX | 2019-05-16 | HROGERS | U131066 | 2018-01-26 | 2019-12-31 |  |  | MARK ROGERS | 2019-05-15 | 2019-05-14 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.8333 | 3 | 1309.59 | 307.51 | 141.13 | 137.55 | 723.4 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18600312000 |  | 100275713 |  | 6684228C |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | GLEN MURRAY | 112 GLEN MURRAY CT | 073 | FRA | 2019-05-15 | U126285 | U126890 | 2018-04-04 | 2018-06-27 | 2019-12-31 |  | DDAVIS | 2019-05-15 | 2018-09-12 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 29.3833 | 12 | 2555.39 | 1293.4 | 0 | 76.15 | 1185.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18613622600 |  | 100300306 |  | 6716212G | 1746168 |  |  | 565 | EX | REPLACE SL W/17026714900 | 2600B | HIGH | 835 W HIGH ST | 067 | LEX | 2019-05-15 | HROGERS | U131066 | 2018-05-22 | 2019-12-31 |  |  | MARK ROGERS | 2019-05-15 | 2019-05-14 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.4 | 3 | 4179.47 | 702.11 | 217.34 | 314.08 | 2945.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026864600 |  | 501259443 |  | 6716204B | 1961939 | U461383 |  | 555 | EX | INSTALL 435' OF 2"PMMP MAIN | 2600B | LOCH NESS | 3257 LOCH NESS DR | 067 | LEX | 2019-05-20 | U123258 | U461383 | 2019-03-05 | 2019-05-10 | 2019-05-17 | 2019-05-14 | DDAVIS | 2019-05-15 | 2019-05-03 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP8646 |  |  | 100 | 055532190268646 | 71.3833 | 4800 | 37399.62 | 3752.75 | 993.71 | 1676.19 | 26091.07 | 0 | 47.43 | 4838.47 | 480
KY | KY - CENTRAL | 2629 | 19026876000 |  |  |  | 7240212C | 1963775 | U131982 |  | 562 | EX | ABAN 360' 2" PMMP | 2621P | TIPTON TRAILER PK | 17 TIPTON TRAILER PK | 173 | MT | 2019-07-03 | U124014 | U131982 | 2019-05-10 | 2019-05-15 | 2019-07-01 | 2019-05-15 | DENNING | 2019-05-15 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00562 | 3200562 |  |  | WP8760 |  |  | 100 | 056232190268760 | 26.3167 | 0 | 1968.98 | 1410.74 | 100.74 | 457.5 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689096400 |  | 100239618 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | POPLAR | 94 POPLAR ST | 089 | RUS | 2019-05-15 | U461496 | U131066 | 2019-03-18 | 2019-11-27 |  |  | DAVID SKAGGS | 2019-05-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.5 | 2 | 1464.59 | 28.06 | 0 | 6.95 | 1429.58 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689096500 |  | 100239619 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | POPLAR | 100 POPLAR ST | 089 | RUS | 2019-05-15 | U461496 | U131066 | 2019-03-18 | 2019-11-27 |  |  | DAVID SKAGGS | 2019-05-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.43333 | 2 | 1021.78 | 22.61 | 0 | 5.63 | 993.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691664600 |  | 100328549 |  | 6720208B | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | CLINTON | 300 CLINTON RD | 067 | LEX | 2019-05-15 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-05-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1099.93 | 0 | 0 | 0 | 1099.93 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691674800 |  | 100328550 |  | 6720208F | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1900 FONTAINE RD | 067 | LEX | 2019-05-15 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-05-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1739.55 | 0 | 0 | 0 | 1739.55 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19700245400 |  | 100292200 |  | 6720216K |  |  |  | 565 | EX | REPLACE SL / REPAIR CV / 3811 | 2621P | JUDY | 581 JUDY LN | 067 | LEX | 2019-05-15 | LMCDONA | U125208 | 2019-04-24 | 2019-05-15 |  |  | LMCDONA | 2019-05-15 | 2019-05-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.3167 | 3 | 1484.38 | 1140.77 | 275.16 | 68.45 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19702044600 |  | 100412959 |  | 6720208J |  |  |  | 566 | EX | DEMO / ABANDON / RI 05-06-19 | 2621P | LAKEWOOD VIEW | 1543 LAKEWOOD VIEW CT | 067 | LEX | 2019-05-21 | U125208 | U132002 | 2019-05-01 | 2019-06-11 | 2019-07-02 |  | LSTANFI | 2019-05-15 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.5 | 3 | 691.66 | 643.4 | 9.66 | 38.6 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19705684100 |  | 100269825 |  | 6732252O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CLADORBON | 225 CLADORBON DR | 097 | CYN | 2019-05-15 | LSHARON | U130193 | 2019-05-14 | 2019-05-14 | 2019-05-14 |  | LSHARON | 2019-05-15 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 16.55 | 3 | 1715.24 | 886.5 | 317.38 | 511.36 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19705692600 |  | 100310837 |  | 6712204C |  |  |  | 565 | EX | GR 1 - REPL SERV | 2621P | SHASTA | 657 SHASTA CR | 067 | LEX | 2019-05-15 | DBANKS | U125208 | 2019-05-14 | 2019-05-14 | 2019-05-14 |  | DBANKS | 2019-05-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.4333 | 1 | 2654.08 | 78.32 | 147.21 | 4.71 | 2423.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19705991200 |  | 100312551 |  | 000000000 |  |  |  | 565 | EX | GRADE ONE LK ON SVC D193639 | 2621P | SHERIDAN | 350 SHERIDAN DR | 067 | LEX | 2019-05-16 | U125208 | U130193 | 2019-05-15 | 2019-05-15 | 2019-05-15 |  | LSTANFI | 2019-05-15 | 2019-05-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.2167 | 4 | 1341.64 | 1171.39 | 100.01 | 70.24 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19706019600 |  | 500207959 |  | 7240212C |  |  |  | 566 | EX | ABANDON | 2621P | TIPTON TRAILER | 17 TIPTON TRAILER PR | 173 | MT | 2019-05-15 | DENNING | U130193 | 2019-05-15 | 2019-05-15 |  |  | DENNING | 2019-05-15 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.3333 | 2 | 101.91 | 70.83 | 0 | 31.08 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 04578202300 |  | 100264665 | 77 | 7348168I |  |  |  | 566 | EX | ABANDON COMPANY SERVICE LINE | 2621P | ROGERS PARK | ROGERS PARK RD A1 | 195 | S W | 2019-05-16 | JCKIRK | CESTEP | 2004-06-17 | 2049-12-31 |  |  | JCKIRK | 2019-05-16 | 2019-05-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 18.7167 | 3 | 1358.59 | 1020.01 | 0 | 338.58 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11912525000 |  | 100331024 |  | 6720212N | 1855043 |  |  | 566 | EX | SOII - ABANDON SERV/RI 06-2010 | 2621P | PRESTON | 244 PRESTON AV | 067 | LEX | 2019-05-16 | LSTANFI | U906631 | 2011-06-21 | 2019-05-16 |  |  | LSTANFI | 2019-05-16 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.76667 | 1 | 1190.94 | 47.36 | 0 | 2.84 | 1140.74 | 0 | 0 | 0
KY | KY - WEST | 2623 | 14198296500 |  | 100280819 |  | 6688228E |  |  |  | 566 | EX | DEMO / RI 10-08-1996 CODE ENF | 2621P | MAIN | 533 E MAIN ST | 073 | FRA | 2019-05-16 | BJLONE | U125208 | 2014-02-06 | 2017-04-03 | 2019-05-03 |  | BJLONE | 2019-05-16 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 13.9667 | 6 | 742.42 | 666.17 | 0 | 76.25 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 18026757300 |  |  |  | 7260276A | 1748617 | U461383 |  | 584 | EX | RETIRE REG STATION WITH AMRP | 2600E | R11 & LEXINGTON ST EXT | R11 & LEXINGTON ST EXT | 161 | MAY | 2019-06-04 | U462463 | U461383 | 2018-03-07 | 2018-12-31 | 2018-12-31 | 2019-05-16 | RYAN WILLIAMS | 2019-05-16 | 2019-05-16 |  | F | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00584 | 3200584 |  |  | WP7573 | AMRCB |  | 100 | 058432180267573 | 6.5667 | 0 | 452.18 | 363.69 | 0 | 88.49 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572288500 |  | 100279771 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 141 SUNSET DR | 073 | FRA | 2019-05-16 | U461322 | U131066 | 2018-01-04 | 2019-12-31 |  |  | STEVE CANOY | 2019-05-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 11.0833 | 1 | 3613.78 | 621.57 | 0 | 262.47 | 2729.74 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572288600 |  | 100279825 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 142 SUNSET DR | 073 | FRA | 2019-05-17 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572289100 |  | 100279774 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 147 SUNSET DR | 073 | FRA | 2019-05-17 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3260.29 | 0 | 0 | 0 | 3260.29 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18577395700 |  | 500340737 |  | 16716212K | 1746168 |  |  | 565 | EX | RPLC SL/17026714900/ | 2600B | PINE | 720 PINE ST B | 067 | LEX | 2019-05-20 | HROGERS | U131066 | 2018-01-26 | 2019-12-31 |  |  | MARK ROGERS | 2019-05-16 | 2019-05-16 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.35 | 2 | 1971.14 | 490.13 | 218.84 | 219.22 | 1042.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026863500 |  | 501154184 |  | 6716220M | 1961633 | U461383 |  | 555 | EX | INSTALL 850' OF 2"PMMP MAIN | 2600B | EMINENT | 2947 EMINENT DR | 067 | LEX | 2019-05-20 | U123258 | U461383 | 2019-02-21 | 2019-06-28 | 2019-07-05 | 2019-05-15 | KEVIN KOUNS | 2019-05-16 | 2019-05-03 | 2019-05-03 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP8635 |  |  | 100 | 055532190268635 | 65.3333 | 6760 | 31192.57 | 3472.99 | 1567.64 | 1493.63 | 20487.99 | 0 | 73.91 | 4096.41 | 845
KY | KY - WEST | 2621 | 19673609000 |  | 100310685 |  | 6712208L | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2911 CLAYS MILL RD | 067 | LEX | 2019-06-10 | U125208 | U131066 | 2019-01-30 | 2019-11-27 |  |  | DPAYTON | 2019-05-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 6.7 | 2 | 2699.99 | 361.41 | 226.25 | 89.96 | 2022.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678780200 |  | 100299208 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 224 LARCH LN | 067 | LEX | 2019-05-16 | U123111 | U131066 | 2019-02-01 | 2019-11-27 |  |  | LYN STAFFORD | 2019-05-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.35 | 1 | 1467.12 | 287.56 | 0 | 125.77 | 1053.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678780400 |  | 100299209 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 232 LARCH LN | 067 | LEX | 2019-05-16 | U123111 | U131066 | 2019-02-01 | 2019-11-27 |  |  | LYN STAFFORD | 2019-05-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.7833 | 2 | 1270.51 | 150.78 | 0 | 65.94 | 1053.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680076400 |  | 100320149 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | TAHOMA | 254 TAHOMA RD | 067 | LEX | 2019-05-16 | U126284 | U131066 | 2019-02-07 | 2019-05-16 |  |  | JOSH PASLEY | 2019-05-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.8333 | 1 | 2499.37 | 295.57 | 0 | 95.77 | 2108.03 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689097500 |  | 500358525 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | POPLAR | 120 POPLAR ST | 089 | RUS | 2019-05-16 | U461496 | U131066 | 2019-03-18 | 2019-11-27 |  |  | DAVID SKAGGS | 2019-05-16 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.43333 | 2 | 1604.8 | 23.71 | 0 | 5.92 | 1575.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19690957800 |  | 100466126 |  | 6712208J |  |  |  | 565 | EX | REPLACE SERVICE LINE - D221867 | 2621P | ERMINE | 2000 ERMINE CT | 067 | LEX | 2019-05-20 | U125208 | U125208 | 2019-03-25 | 2019-05-16 | 2021-03-31 |  | LSTANFI | 2019-05-16 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.78333 | 1 | 1875.55 | 46.77 | 151.79 | 2.79 | 1674.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691308600 |  | 100301514 |  | 6712212H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D221754 | 2621P | LONDONDERRY | 145 LONDONDERRY DR | 067 | LEX | 2019-05-20 | U125208 | U125208 | 2019-03-26 | 2019-09-26 | 2021-03-31 |  | LSTANFI | 2019-05-16 | 2019-05-15 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.6167 | 3 | 2136.79 | 260.57 | 269.29 | 15.62 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691625000 |  | 100457302 |  | 6720204O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | WOODFIELD | 2376 WOODFIELD CR | 067 | LEX | 2019-05-20 | U125208 | U125208 | 2019-03-27 | 2019-05-16 | 2021-03-31 |  | LSTANFI | 2019-05-16 | 2019-05-16 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.6167 | 2 | 2274.22 | 269.98 | 168.27 | 16.19 | 1819.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691676300 |  | 100328557 |  | 6720208F | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1922 FONTAINE RD | 067 | LEX | 2019-05-16 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-05-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1654.19 | 0 | 0 | 0 | 1654.19 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691677100 |  | 100328556 |  | 6720208F | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1924 FONTAINE RD | 067 | LEX | 2019-05-16 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-05-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1193.11 | 0 | 0 | 0 | 1193.11 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691677400 |  | 100328558 |  | 6720208F | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1928 FONTAINE RD | 067 | LEX | 2019-05-16 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-05-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2233.11 | 0 | 0 | 0 | 2233.11 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19695057500 |  | 100315153 |  | 6716212O |  |  |  | 566 | EX | DEMO / ABANDON / RA 04-20-19 | 2621P | TRANSCRIPT | 220 TRANSCRIPT AV | 067 | LEX | 2019-05-16 | LMCDONA | U125208 | 2019-04-05 | 2019-05-03 | 2019-05-05 |  | LMCDONA | 2019-05-16 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.25 | 2 | 1085.91 | 933.66 | 96.23 | 56.02 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19706346900 |  | 100299206 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 212 LARCH LN | 067 | LEX | 2019-05-16 | U123111 | U131066 | 2019-05-16 | 2019-12-31 |  |  | LYN STAFFORD | 2019-05-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.25 | 1 | 1130.55 | 120.63 | 0 | 52.77 | 957.15 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19706365600 |  | 500363495 |  | 6684228O |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | SPRINGHILL | 170 SPRINGHILL RD DOWN | 073 | FRA | 2019-05-16 | CDESPAI | U130193 | 2019-05-16 | 2019-05-16 |  |  | CDESPAI | 2019-05-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.75 | 1 | 4949.7 | 312.54 | 429.45 | 503.74 | 3703.97 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19706476000 |  | 100322644 |  | 6716208D |  |  |  | 565 | EX | REPLACE SERVICE | 2621P | BERRY | 700 BERRY LN | 067 | LEX | 2019-05-20 | U125208 | U131169 | 2019-05-16 | 2019-05-16 |  |  | KKINDER | 2019-05-16 | 2019-05-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 29.9667 | 4 | 2184.43 | 1937.98 | 131 | 115.45 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07680887600 |  | 100320908 | 38 | 600000000 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | ARLINGTON | 217 ARLINGTON AV | 067 | LEX | 2019-05-20 | U125208 | LABRAMS | 2007-03-29 | 2019-05-17 |  |  | LSTANFI | 2019-05-17 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.45 | 1 | 795.89 | 88.11 | 62.59 | 5.29 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572288200 |  | 100279769 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 137 SUNSET DR | 073 | FRA | 2019-05-20 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572288400 |  | 100279826 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 140 SUNSET DR | 073 | FRA | 2019-05-17 | U461322 | U131066 | 2018-01-04 | 2019-12-31 |  |  | STEVE CANOY | 2019-05-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 10 | 1 | 2574.28 | 560.98 | 0 | 236.89 | 1776.41 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572288800 |  | 100279824 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 144 SUNSET DR | 073 | FRA | 2019-05-20 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1776.41 | 0 | 0 | 0 | 1776.41 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18644561700 |  | 100350336 |  | 6744204C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094596 | 2621P | LISLE | 18 LISLE LN | 049 | WIN | 2019-05-20 | U125208 | U125208 | 2018-09-20 | 2019-03-19 | 2020-09-30 |  | RJJOHNS | 2019-05-17 | 2019-05-13 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 19.2667 | 4 | 1147.46 | 938.09 | 153.11 | 56.26 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026870400 |  | 501231610 |  | 6712216P | 1962882 | U461383 |  | 555 | EX | INSTALL 60' OF 2"PMMP MAIN | 2600B | SATIN LEAF | 2828 SATIN LEAF PK | 067 | LEX | 2019-05-24 | U123258 | U461383 | 2019-04-12 | 2019-05-06 | 2019-05-24 | 2019-05-17 | DDAVIS | 2019-05-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP8704 |  |  | 100 | 055532190268704 | 9.5 | 65 | 7392.67 | 499.13 | 433.4 | 222.98 | 5249.3 | 0 | 14.33 | 973.53 | 65
KY | KY - CENTRAL | 2629 | 19026871100 |  |  |  | 7240212C | 1963127 | U461383 |  | 559 | EX | INSTALL 40' OF 4"PMMP MAIN | 2621P | WINDSOR | WINDSOR AV | 173 | MT | 2019-07-02 | U124014 | U461383 | 2019-04-16 | 2019-06-28 | 2019-07-01 | 2019-05-16 | DENNING | 2019-05-17 | 2019-05-16 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00559 | 3200559 |  |  | WP8711 |  |  | 100 | 055932190268711 | 45.4333 | 266 | 5126.15 | 2662.98 | 610.4 | 1168.57 | 0 | 0 | 11.56 | 672.64 | 38
KY | KY - CENTRAL | 2629 | 19026871200 |  |  |  | 7240212C | 1963127 | U461383 |  | 560 | EX | RETIRE 40' OF 4"PAP MAIN | 2621P | WINDSOR | WINDSOR AV | 173 | MT | 2019-07-02 | U124014 | U461383 | 2019-04-16 | 2019-07-01 | 2019-07-01 | 2019-05-16 | DENNING | 2019-05-17 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00560 | 3200560 |  |  | WP8712 |  |  | 100 | 056032190268712 | 3.7667 | 0 | 288.73 | 200.7 | 0 | 88.03 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678769900 |  | 100299360 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400 | 2600B | BOILING SPRING | 229 BOILING SPRING DR | 067 | LEX | 2019-05-17 | U123111 | U131066 | 2019-02-01 | 2019-06-28 |  |  | LYN STAFFORD | 2019-05-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.1 | 1 | 1447.77 | 274.09 | 0 | 119.89 | 1053.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680072300 |  | 100320225 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100 | 2600B | SHADY | 255 SHADY LN | 067 | LEX | 2019-05-17 | U126284 | U131066 | 2019-02-07 | 2019-06-28 |  |  | JOSH PASLEY | 2019-05-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.4667 | 1 | 2832.61 | 199.24 | 0 | 82.48 | 2550.89 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687252500 |  | 501033305 | 21 | 6688224G | 0783920 |  |  | 566 | EX | ABANDON-LCB / RI 03-11-19 | 2621P | FORTUNE | 109 FORTUNE DR | 073 | FRA | 2019-05-20 | U125208 | JDBRADF | 2019-03-11 | 2049-12-31 |  |  | MCRAIG | 2019-05-17 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 11.5 | 2 | 706.57 | 648.83 | 18.83 | 38.91 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691675900 |  | 100328555 |  | 6720208F | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1918 FONTAINE RD | 067 | LEX | 2019-05-17 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-05-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1810.94 | 0 | 0 | 0 | 1810.94 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19704650400 |  | 100263769 |  | 7352260O |  |  |  | 566 | EX | ABANDON / RI 5-8-19 / CONVRT | 2621P | LAUREL | 395 LAUREL AV | 019 | ASH | 2019-05-17 | MCOLLET | U132002 | 2019-05-09 | 2019-06-19 | 2019-07-11 |  | MCOLLET | 2019-05-17 | 2019-05-14 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 7.7167 | 4 | 754.4 | 429.48 | 9.9 | 315.02 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19705047900 |  | 100344073 |  | 7244216G |  |  |  | 566 | EX | ABANDON LINES & SETTING / IDLE | 2621P | HOWARDS MILL | 3361 HOWARDS MILL RD | 173 | MT | 2019-05-20 | JTOY | U125208 | 2019-05-10 | 2019-05-31 |  |  | DENNING | 2019-05-17 | 2019-05-15 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 5.1 | 4 | 392.14 | 272.53 | 0 | 119.61 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19705621600 |  | 100436237 |  | 7344264C |  |  |  | 566 | EX | RETIRE SERVICE LINE - D192896 | 2621P | WURTLAND | 1399 WURTLAND AV L18 | 089 | WUR | 2019-05-20 | U125208 | U130193 | 2019-05-14 | 2019-05-14 | 2019-05-14 |  | MCOLLET | 2019-05-17 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.6 | 1 | 101.49 | 34.21 | 27.77 | 39.51 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19707205000 |  | 100459178 |  | 6716216G |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094257 | 2621P | GEORGETOWN | 2150 GEORGETOWN RD | 067 | LEX | 2019-05-22 | U125964 | U129939 | 2019-05-18 | 2018-11-09 | 2020-05-31 |  | ASNICHO | 2019-05-18 | 2019-05-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 65.0833 | 10 | 7680.77 | 3378.68 | 1424.94 | 266.15 | 2611 | 0 | 0 | 0
KY | KY - WEST | 2623 | 04569492900 |  | 100347263 |  | 6696212K |  |  |  | 566 | EX | SOII - METER ABANDON ONLY | 2621P | ROSE HILL | 219 ROSE HILL AV | 239 | VER | 2019-05-21 | U125208 | RCALDWE | 2004-03-19 | 2013-01-02 |  |  | MCRAIG | 2019-05-20 | 2018-04-10 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 3.5167 | 4 | 250.23 | 192.54 | 0 | 57.69 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572287700 |  | 100279830 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 132 SUNSET DR | 073 | FRA | 2019-05-23 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572287800 |  | 100279767 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 133 SUNSET DR | 073 | FRA | 2019-05-23 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | JAMIE LYNN | 2019-05-20 | 2019-05-21 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.033333 | 1 | 2731.53 | 1.52 | 0 | 0.27 | 2729.74 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572287900 |  | 100279829 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 134 SUNSET DR | 073 | FRA | 2019-05-23 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | JAMIE LYNN | 2019-05-20 | 2019-05-20 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8.3167 | 1 | 2276.81 | 427.65 | 0 | 72.75 | 1776.41 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572288100 |  | 100279828 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 136 SUNSET DR | 073 | FRA | 2019-05-23 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | JAMIE LYNN | 2019-05-20 | 2019-05-21 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.1167 | 1 | 1903.33 | 108.46 | 0 | 18.46 | 1776.41 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572288700 |  | 100279772 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 143 SUNSET DR | 073 | FRA | 2019-05-23 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18644913400 |  | 100274376 |  | 6684228J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | EWING | 401 EWING ST | 073 | FRA | 2019-05-20 | EFGOINS | U125208 | 2018-09-21 | 2019-03-20 | 2020-09-30 |  | EFGOINS | 2019-05-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.3667 | 1 | 1967.66 | 70.82 | 143.96 | 4.26 | 1748.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673608900 |  | 100310658 |  | 6712208L | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2909 CLAYS MILL RD | 067 | LEX | 2019-05-20 | U126602 | U131066 | 2019-01-30 | 2019-11-27 |  |  | DPAYTON | 2019-05-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.7 | 2 | 3181.77 | 468.97 | 186.24 | 116.72 | 2409.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678768500 |  | 100299267 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 200 BOILING SPRING DR | 067 | LEX | 2019-05-20 | U123111 | U131066 | 2019-02-01 | 2019-05-20 |  |  | LYN STAFFORD | 2019-05-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.8833 | 1 | 1521.04 | 102.31 | 0 | 6.15 | 1412.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678780900 |  | 100299212 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 244 LARCH LN | 067 | LEX | 2019-05-20 | U123111 | U131066 | 2019-02-01 | 2019-11-27 |  |  | LYN STAFFORD | 2019-05-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.0333 | 1 | 1015.95 | 55.47 | 0 | 3.33 | 957.15 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678781300 |  | 100299214 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 252 LARCH LN | 067 | LEX | 2019-05-20 | U123111 | U131066 | 2019-02-01 | 2019-11-27 |  |  | LYN STAFFORD | 2019-05-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.7167 | 1 | 2031.23 | 307.47 | 0 | 18.45 | 1705.31 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19685902500 |  | 100241776 |  | 7356256P | 1859020 |  |  | 565 | EX | RPLC SL/18026844201/ | 2600B | WINCHESTER | 4762 WINCHESTER AV | 019 | ASH | 2019-05-21 | U125573 | U131066 | 2019-03-04 | 2019-11-27 |  |  | BCOFER | 2019-05-20 |  | 2019-05-20 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1414.11 | 39.92 | 0 | 18.18 | 1356.01 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689096700 |  | 100239611 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | POPLAR | 104 POPLAR ST | 089 | RUS | 2019-05-21 | U461496 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ROCKIE MULLINS | 2019-05-20 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.4 | 2 | 1455.46 | 21.21 | 0 | 5.33 | 1428.92 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689096900 |  | 100239610 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | POPLAR | 108 POPLAR ST | 089 | RUS | 2019-05-21 | U461496 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ROCKIE MULLINS | 2019-05-20 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.46667 | 2 | 981.1 | 25.46 | 0 | 6.42 | 949.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691678500 |  | 100328566 |  | 6720208F | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1944 FONTAINE RD | 067 | LEX | 2019-05-20 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-05-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2227.48 | 0 | 0 | 0 | 2227.48 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19695118500 |  | 501046748 |  | 7348248A |  |  |  | 566 | EX | ABANDON / IDLE | 2621P | DONNA | 2060 DONNA DR | 019 | ASH | 2019-05-20 | MCOLLET | U125208 | 2019-04-05 | 2019-04-26 |  |  | MCOLLET | 2019-05-20 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 13.0667 | 2 | 1009.39 | 699.7 | 9.9 | 299.79 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19696399200 |  | 100282969 |  | 6712228B |  |  |  | 565 | EX | CONT - REPL SERV | 2621P | HAMILTON | 504 S HAMILTON ST | 209 | GEO | 2019-05-20 | EFGOINS | U125208 | 2019-04-11 | 2019-05-20 |  |  | EFGOINS | 2019-05-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.11667 | 1 | 5.99 | 5.65 | 0 | 0.34 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19705130800 |  | 500833187 |  | 6736208M | 1963009 |  |  | 565 | EX | NBT - SERV LINE/MTR UPGRADE | 2621P | COMBS FERRY | 599 COMBS FERRY RD | 049 | WIN | 2019-05-20 | JOCHOA | U125208 | 2019-05-10 | 2019-05-10 | 2019-05-30 |  | JOCHOA | 2019-05-20 | 2019-05-16 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26290031 | 13.5333 | 4 | 1176.69 | 656.3 | 197.26 | 51.77 | 271.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19706345700 |  | 100312580 |  | 6716208E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D093757 | 2621P | STRATFORD | 371 STRATFORD DR | 067 | LEX | 2019-05-21 | U125208 | U125208 | 2019-05-16 | 2019-05-17 | 2019-06-05 |  | MCRISP | 2019-05-20 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.3167 | 5 | 1364.33 | 1136.91 | 159.21 | 68.21 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19707318400 |  | 100346206 |  | 6696212L |  |  |  | 566 | EX | ABANDON PSID | 2621P | MAIN | 114< S MAIN ST | 239 | VER | 2019-05-20 | MCRAIG | U130193 | 2019-05-20 | 2019-05-20 |  |  | MCRAIG | 2019-05-20 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.16667 | 2 | 8.15 | 7.71 | 0 | 0.44 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07694955500 |  | 100338362 |  | 6720212F |  |  |  | 566 | EX | DEMO / ABANDON / RI 07-25-05 | 2621P | SHROPSHIRE | 746 SHROPSHIRE AV | 067 | LEX | 2019-05-21 | DBANKS | DMCCULL | 2007-07-18 | 2019-01-11 | 2019-01-11 |  | DBANKS | 2019-05-21 | 2019-01-07 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.2 | 10 | 1821.73 | 499.84 | 43.24 | 32.79 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 17561363100 |  | 100274169 | 39 | 6684228N | 1638340 |  |  | 565 | EX | REPLACE SERV - ATMOS CORR | 2621P | SHELBY | 616 SHELBY ST | 073 | FRA | 2019-05-21 | CDESPAI | RVANDER | 2017-11-06 | 2017-12-29 |  |  | CDESPAI | 2019-05-21 | 2019-04-08 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 18.2333 | 6 | 7630.5 | 1015.76 | 359.84 | 988.32 | 5266.58 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572287300 |  | 100279832 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 128 SUNSET DR | 073 | FRA | 2019-05-23 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572287400 |  | 100279765 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 129 SUNSET DR | 073 | FRA | 2019-05-23 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | JAMIE LYNN | 2019-05-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.85 | 1 | 1998.74 | 44.73 | 0 | 7.6 | 1946.41 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572287500 |  | 100279831 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 130 SUNSET DR | 073 | FRA | 2019-05-23 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | JAMIE LYNN | 2019-05-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572287600 |  | 100279766 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 131 SUNSET DR | 073 | FRA | 2019-05-23 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | JAMIE LYNN | 2019-05-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.9333 | 1 | 2242.94 | 253.4 | 0 | 43.13 | 1946.41 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572288300 |  | 100279827 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 138 SUNSET DR | 073 | FRA | 2019-05-23 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2559.74 | 0 | 0 | 0 | 2559.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18601922200 |  | 100300279 |  | 6716212G | 1746168 |  |  | 565 | EX | RPLC SL/17026714900/ | 2621P | HIGH | 817 W HIGH ST 1A | 067 | LEX | 2019-05-22 | U461439 | U125964 | 2018-04-11 | 2018-11-30 |  |  | A PARRIS | 2019-05-21 | 2019-05-21 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.45 | 2 | 5373.64 | 579.32 | 0 | 247.33 | 4546.99 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19667378000 |  | 100241867 | 33 | NEW |  |  |  | 566 | EX | ABANDON SERVICE DUE TO FIRE | 2621P | WILLIAMS | 5019 WILLIAMS AV | 019 | ASH | 2019-05-21 | MCOLLET | JWHEATL | 2019-01-09 | 2019-03-13 | 2019-03-13 |  | MCOLLET | 2019-05-21 | 2019-04-02 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 7.9 | 6 | 726.51 | 461.49 | 11.15 | 253.87 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678780700 |  | 100299211 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400 | 2600B | LARCH | 240 LARCH LN | 067 | LEX | 2019-05-21 | U123111 | U131066 | 2019-02-01 | 2019-06-28 |  |  | LYN STAFFORD | 2019-05-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.05 | 1 | 1667.13 | 109.85 | 0 | 48.06 | 1509.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678781500 |  | 100299215 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400 | 2600B | LARCH | 256 LARCH LN | 067 | LEX | 2019-05-21 | U123111 | U131066 | 2019-02-01 | 2019-06-28 |  |  | LYN STAFFORD | 2019-05-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.0667 | 1 | 1726.84 | 218.63 | 0 | 95.63 | 1412.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680072100 |  | 100320228 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 247 SHADY LN | 067 | LEX | 2019-05-21 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-05-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3785.16 | 0 | 0 | 0 | 3785.16 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19685900300 |  | 100241775 |  | 7356256P | 1859020 |  |  | 565 | EX | RPLC SL/18026844201/ | 2600B | 49TH | 317 49TH ST | 019 | ASH | 2019-05-22 | U125573 | U131066 | 2019-03-04 | 2019-11-27 |  |  | BCOFER | 2019-05-21 |  | 2019-05-21 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1823.36 | 0 | 0 | 0 | 1823.36 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19687543900 |  | 100343299 |  | 7240212A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | OAKLAWN | 504 OAKLAWN DR | 173 | MT | 2019-05-21 | DENNING | U125208 | 2019-03-12 | 2019-09-12 | 2021-03-31 |  | DENNING | 2019-05-21 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 11.0667 | 2 | 993.03 | 592.36 | 140.8 | 259.87 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689095800 |  | 100239621 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | MAPLE | 104 MAPLE ST | 089 | RUS | 2019-05-21 | U461496 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-05-21 | 2019-05-09 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.96667 | 3 | 1460.02 | 51.52 | 0 | 16.08 | 1392.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691664300 |  | 100328551 |  | 6720208F | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | ADAIR | 301 ADAIR RD | 067 | LEX | 2019-05-21 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-05-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 789.27 | 0 | 0 | 0 | 789.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691677700 |  | 100328562 |  | 6720208F | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1934 FONTAINE RD | 067 | LEX | 2019-06-10 | U125208 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-05-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1798.22 | 0 | 0 | 0 | 1798.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691698800 |  | 100328565 |  | 6720208F | 1855692 |  |  | 565 | EX | REPLACE SL W/18026796400 | 2600B | FONTAINE | 1938 FONTAINE RD | 067 | LEX | 2019-05-23 | U125559 | U131066 | 2019-03-27 | 2019-12-31 |  |  | BJACKSON | 2019-05-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1622.58 | 0 | 0 | 0 | 1622.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19695055300 |  | 100315113 |  | 6716212O |  |  |  | 566 | EX | DEMO / ABANDON / RA 04-20-19 | 2621P | GAZETTE | 150 GAZETTE AV | 067 | LEX | 2019-05-23 | U125208 | U125208 | 2019-04-05 | 2019-05-03 | 2019-05-05 |  | KKINDER | 2019-05-21 | 2019-05-21 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 23.6 | 5 | 1302.21 | 1210.71 | 18.83 | 72.67 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19695055800 |  | 100315108 |  | 6716212O |  |  |  | 566 | EX | DEMO / ABANDON / RA 04-20-19 | 2621P | GAZETTE | 164 GAZETTE AV | 067 | LEX | 2019-05-21 | TGNELSO | U125208 | 2019-04-05 | 2019-05-03 | 2019-05-05 |  | TGNELSO | 2019-05-21 | 2019-05-21 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.6 | 2 | 609.58 | 575.06 | 0 | 34.52 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19695056200 |  | 100315109 |  | 6716212O |  |  |  | 566 | EX | DEMO / ABANDON / RI 04-20-19 | 2621P | GAZETTE | 162 GAZETTE AV | 067 | LEX | 2019-05-21 | TGNELSO | U125208 | 2019-04-05 | 2019-05-03 | 2019-05-05 |  | TGNELSO | 2019-05-21 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.4833 | 2 | 152.53 | 143.89 | 0 | 8.64 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19695058000 |  | 100315325 |  | 6716208C |  |  |  | 566 | EX | DEMO / ABANDON / RA 04-20-19 | 2621P | LIMESTONE | 1119 S LIMESTONE ST | 067 | LEX | 2019-05-23 | U125208 | U125208 | 2019-04-05 | 2019-05-03 | 2019-05-05 |  | KKINDER | 2019-05-21 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.55 | 3 | 654.56 | 547.32 | 74.4 | 32.84 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19699174700 |  | 100288313 |  | 6720212H |  |  |  | 565 | EX | GRADE 1 REPLACE SERV LINE | 2621P | WARRINGTON | 642 WARRINGTON DR | 067 | LEX | 2019-05-21 | CWEMPE | U129939 | 2019-04-19 | 2019-04-18 | 2019-04-19 |  | CWEMPE | 2019-05-21 | 2019-04-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.5 | 5 | 1049.77 | 993.06 | 0 | 56.71 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19707614400 |  | 500038709 |  | 6688228L |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | ISAAC SHELBY | 745 ISAAC SHELBY CR W | 073 | FRA | 2019-05-23 | U125208 | U125208 | 2019-05-21 | 2019-05-13 | 2019-05-13 |  | CDESPAI | 2019-05-21 | 2019-05-21 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 13.1833 | 1 | 9128.14 | 715.67 | 202.16 | 42.95 | 8167.36 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 06653983400 |  | 100356659 |  | 17260280M |  |  |  | 566 | EX | ABANDON SL - IDLE/INACTIVE | 2600B | LEXINGTON | 658 LEXINGTON ST A1 | 161 | MAY | 2021-02-26 | U461478 | RPOLLY | 2006-07-18 | 2007-05-08 | 2008-05-08 |  | DAVID STAGGS | 2019-05-22 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1 | 632.92 | 0 | 0 | 0 | 632.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12980359800 |  | 100308499 |  | 6716212M |  |  |  | 566 | EX | DEMO / ABANDON / RI 06-25-11 | 2600B | GOLFVIEW | 705 GOLFVIEW DR | 067 | LEX | 2019-06-10 | U125208 | U125208 | 2012-07-16 | 2019-04-26 |  |  | ASNICHO | 2019-05-22 | 2019-04-25 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 26.5333 | 8 | 1339.2 | 1218.89 | 18.83 | 101.48 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 17026734200 |  |  |  | 7260280M | 1748617 | U127466 |  | 557 | EX | INSTALL 800' - 2" PMMP MAIN | 2600B | LIMESTONE TERRACE | LIMESTONE TERRACE | 161 | MAY | 2019-06-21 | U125423 | U127466 | 2017-10-26 | 2019-10-17 | 2019-12-31 | 2019-02-13 | DAVID STAGGS | 2019-05-22 | 2019-01-22 | 2019-01-22 | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00557 | 3200557 |  |  | WP7342 | AMRCB |  | 100 | 055732170267342 | 204.3333 | 21222 | 158951.66 | 16642.24 | 17933.07 | 5052.27 | 99308.36 | 0 | 447.52 | 19568.2 | 786
KY | KY - CENTRAL | 2632 | 17026734300 |  |  |  | 7260280M | 1748617 | U127466 |  | 558 | EX | RETIRE 3,000' - CILP/BSLP/PLP | 2600B | LIMESTONE TERRACE | LIMESTONE TERRACE | 161 | MAY | 2019-06-21 | U125423 | U127466 | 2017-10-26 | 2019-12-31 | 2019-12-31 | 2019-05-22 | DAVID STAGGS | 2019-05-22 | 2019-05-16 |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00558 | 3200558 |  |  | WP7343 | AMRCB |  | 100 | 055832170267343 | 10.5 | 0 | 631.49 | 594.43 | 0 | 37.06 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572286900 |  | 100279834 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 124 SUNSET DR | 073 | FRA | 2019-06-10 | U125208 | U131066 | 2018-01-04 | 2019-12-31 |  |  | JAMIE LYNN | 2019-05-22 | 2019-05-22 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.25 | 2 | 2029.06 | 372.66 | 0 | 63.41 | 1592.99 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572287100 |  | 100279833 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 126 SUNSET DR | 073 | FRA | 2019-06-10 | U125208 | U131066 | 2018-01-04 | 2019-12-31 |  |  | JAMIE LYNN | 2019-05-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.15 | 1 | 2350.34 | 110.52 | 0 | 18.81 | 2221.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18577388400 |  | 100300314 |  | 6716212G | 1746168 |  |  | 565 | EX | RPLC SL/17026714900/ | 2600B | HIGH | 847 W HIGH ST | 067 | LEX | 2019-05-22 | U461439 | U131066 | 2018-01-26 | 2019-12-31 |  |  | A PARRIS | 2019-05-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.95 | 1 | 1802.19 | 269.75 | 0 | 116.58 | 1415.86 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 18664362700 |  | 100357333 |  | 7240280G |  |  |  | 566 | EX | DEMO / ABANDON / RI 07-18-17 | 2621P | BROADWAY | 4020 BROADWAY AL | 161 | GER | 2019-05-22 | SDADAMS | U131800 | 2018-12-28 | 2019-03-07 | 2019-03-07 |  | SDADAMS | 2019-05-22 | 2019-02-07 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 15.0833 | 8 | 1104.59 | 816.58 | 189.24 | 98.77 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026877600 |  |  |  | 6716212L | 1963923 | BKSLONE |  | 562 | EX | RETIRE 92'-4" PMP | 2621P | HIGH | 283 E HIGH ST | 067 | LEX | 2019-06-13 | U123258 | BKSLONE | 2019-05-16 | 2019-05-16 |  | 2019-05-17 | JENSMIN | 2019-05-22 | 2019-05-17 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP8776 |  |  | 100 | 056232190268776 | 2.2333 | 0 | 5993.06 | 144.47 | 153 | 146 | 5549.59 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19666814800 |  | 100356670 |  | 7260280M | 1748617 |  |  | 566 | VO | ABANDON SL/17026734200/ | 2600B | LEXINGTON | 630 LEXINGTON ST | 161 | MAY | 2021-04-13 |  | U131066 | 2019-01-07 | 2019-11-27 |  |  | DAVID STAGGS | 2019-05-22 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 4.0333 | 2 | 241.34 | 226.18 | 0 | 15.16 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19666817200 |  | 100356653 |  | 7260280M | 1748617 |  |  | 566 | EX | ABANDON SL W/17026734300 | 2600B | LEXINGTON | 706 LEXINGTON ST | 161 | MAY | 2020-03-27 | U461478 | U131066 | 2019-01-07 | 2019-12-31 |  |  | DAVID STAGGS | 2019-05-22 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1
KY | KY - WEST | 2621 | 19673608800 |  | 100310657 |  | 6712208L | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2907 CLAYS MILL RD | 067 | LEX | 2019-05-22 | U126602 | U131066 | 2019-01-30 | 2019-11-27 |  |  | DPAYTON | 2019-05-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 10.1 | 2 | 3082.01 | 543.2 | 256.07 | 135.23 | 2147.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678782600 |  | 100299221 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 280 LARCH LN | 067 | LEX | 2019-05-22 | U123111 | U131066 | 2019-02-01 | 2019-11-27 |  |  | LYN STAFFORD | 2019-05-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1509.22 | 0 | 0 | 0 | 1509.22 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19685900400 |  | 100241774 |  | 7356256P | 1859020 |  |  | 565 | EX | RPLC SL/18026844201/ | 2600B | 49TH | 319 49TH ST | 019 | ASH | 2019-05-22 | U125573 | U131066 | 2019-03-04 | 2019-11-27 |  |  | BCOFER | 2019-05-22 |  | 2019-05-22 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 951.66 | 0 | 0 | 0 | 951.66 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689096200 |  | 100239604 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | OAK | 205 OAK ST | 089 | RUS | 2019-05-22 | U125566 | U131066 | 2019-03-18 | 2019-11-27 |  |  | DAVID SKAGGS | 2019-05-22 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.31667 | 1 | 1148.12 | 18.09 | 0 | 1.09 | 1128.94 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689096800 |  | 100239609 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | POPLAR | 106 POPLAR ST | 089 | RUS | 2019-05-22 | U125566 | U131066 | 2019-03-18 | 2019-11-27 |  |  | DAVID SKAGGS | 2019-05-22 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.41667 | 1 | 1110.85 | 21.82 | 0 | 1.31 | 1087.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691677300 |  | 100328579 |  | 6720208F | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1925 FONTAINE RD | 067 | LEX | 2019-05-22 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-05-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2006.36 | 0 | 0 | 0 | 2006.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19702068700 |  | 100290311 |  | 6720212B |  |  |  | 566 | VO | DEMO / ABANDON / RA ??/??/?? | 2621P | LIMESTONE | 1406 N LIMESTONE ST | 067 | LEX | 2019-05-23 |  | U125208 | 2019-05-01 | 2049-12-31 |  |  | RHAYES | 2019-05-22 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 19704430400 |  | 500118680 |  | 6720220M |  |  |  | 566 | EX | DEMO / ABANDON / RA 05-27-19 | 2621P | NEWTOWN | 2099 NEWTOWN PK 1955 | 067 | LEX | 2019-05-22 | TGNELSO | U132002 | 2019-05-08 | 2019-06-18 | 2019-07-10 |  | TGNELSO | 2019-05-22 | 2019-05-14 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.9 | 6 | 687.54 | 648.62 | 0 | 38.92 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19706002000 |  | 100271095 |  | NCV |  |  |  | 566 | EX | DEMO / ABANDON / RA 05-29-19 | 2621P | ASBURY | 3166 ASBURY RD | 023 | AUG | 2019-05-24 | U125208 | U132002 | 2019-05-15 | 2019-06-25 | 2019-07-17 |  | SDADAMS | 2019-05-22 | 2019-05-22 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 2.4833 | 1 | 142.2 | 134.14 | 0 | 8.06 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19706002400 |  | 100460193 |  | 6712212M |  |  |  | 565 | EX | REPLACE SERVICE LINE - D221812 | 2621P | WELLESLEY | 1552 WELLESLEY DR | 067 | LEX | 2019-05-23 | U125208 | U130193 | 2019-05-15 | 2019-04-18 | 2021-02-28 |  | JENSMIN | 2019-05-22 | 2019-05-17 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.66667 | 3 | 3348.61 | 53.65 | 241.64 | 23.52 | 3029.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19708149400 |  | 100282778 |  | 6712228B |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | CLINTON | 128 E CLINTON ST | 209 | GEO | 2019-05-22 | CDESPAI | U130193 | 2019-05-22 | 2019-05-22 |  |  | CDESPAI | 2019-05-22 | 2019-05-22 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.5833 | 1 | 3874.9 | 434.09 | 197.74 | 699.65 | 2543.42 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19708230700 |  | 100241812 |  | 7336276N | 1859020 |  |  | 565 | EX | RPLC SL/18026844201/ | 2600B | WILLIAMS | 4812 WILLIAMS AV | 019 | ASH | 2019-05-24 | U125573 | U131279 | 2019-05-22 | 2019-12-31 |  |  | BCOFER | 2019-05-22 |  | 2019-05-22 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 907.34 | 0 | 0 | 0 | 907.34 | 0 | 0 | 0
KY | KY - WEST | 2623 | 06654124200 |  | 100277175 |  | 6684228H |  |  |  | 566 | EX | ABD S/L-IDLE 24 MO MEMO | 2621P | HOLMES | 529 HOLMES ST | 073 | FRA | 2019-05-23 | BJLONE | RPOLLY | 2006-07-19 | 2049-12-31 |  |  | BJLONE | 2019-05-23 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 2.0833 | 1 | 759.84 | 113.15 | 0 | 6.79 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572287000 |  | 100279763 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 125 SUNSET DR | 073 | FRA | 2019-05-23 | U126309 | U131066 | 2018-01-04 | 2019-12-31 |  |  | JAMIE LYNN | 2019-05-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.5333 | 1 | 2164.83 | 78.66 | 0 | 13.37 | 2072.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572287200 |  | 100279764 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 127 SUNSET DR | 073 | FRA | 2019-05-23 | U126309 | U131066 | 2018-01-04 | 2019-12-31 |  |  | JAMIE LYNN | 2019-05-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.4333 | 1 | 1562.59 | 125.4 | 0 | 21.33 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18577395000 |  | 500063367 |  | 6716212G | 1746168 |  |  | 565 | EX | RPLC SL/17026714900/ | 2600B | MCCARTY | 234 MCCARTY CT | 067 | LEX | 2019-05-23 | U461439 | U131066 | 2018-01-26 | 2019-12-31 |  |  | A PARRIS | 2019-05-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.2167 | 1 | 1494.92 | 173.22 | 0 | 75.84 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18594169700 |  | 100320230 |  | 6716208K | 1748686 |  |  | 566 | EX | RETIRE S/L W/17-0267361-00 | 2600B | SHADY | 243 SHADY LN | 067 | LEX | 2019-11-12 | U126284 | U125765 | 2018-03-13 | 2019-12-31 | 2019-12-31 |  | JOSH PASLEY | 2019-05-23 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 19678782800 |  | 100299222 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 284 LARCH LN | 067 | LEX | 2019-05-23 | U123111 | U131066 | 2019-02-01 | 2019-11-27 |  |  | LYN STAFFORD | 2019-05-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1053.79 | 0 | 0 | 0 | 1053.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680071900 |  | 100320229 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 243 SHADY LN | 067 | LEX | 2019-05-24 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-05-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.4333 | 1 | 2251.64 | 197.51 | 0 | 81.76 | 1972.37 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19685900600 |  | 100241773 |  | 7356256P | 1859020 |  |  | 565 | EX | RPLC SL/18026844201/ | 2600B | 49TH | 323 49TH ST | 019 | ASH | 2019-05-24 | U125573 | U131066 | 2019-03-04 | 2019-11-27 |  |  | BCOFER | 2019-05-23 |  | 2019-05-23 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2676.86 | 120.66 | 0 | 53 | 2503.2 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689096000 |  | 100239606 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | OAK | 202 OAK ST | 089 | RUS | 2019-05-23 | U125566 | U131066 | 2019-03-18 | 2019-11-27 |  |  | DAVID SKAGGS | 2019-05-23 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.25 | 1 | 1759.52 | 14.2 | 0 | 6.13 | 1739.19 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691675700 |  | 100328584 |  | 6720208F | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1917 FONTAINE RD | 067 | LEX | 2019-05-23 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-05-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2108.84 | 0 | 0 | 0 | 2108.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19703931400 |  | 100312083 | 38 | 6716208I |  |  |  | 565 | EX | REPLACE CAT2 | 2621P | HILL N DALE | 269 HILL N DALE RD | 067 | LEX | 2019-05-23 | DBANKS | DMYOUNG | 2019-05-07 | 2019-05-16 |  |  | DBANKS | 2019-05-23 | 2019-05-20 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 9.45 | 3 | 2391.08 | 516.88 | 94.57 | 31.01 | 1748.62 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18661468300 |  | 100274705 |  | 6684228J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SHELBY | 323 SHELBY ST 1F | 073 | FRA | 2019-05-30 | U125208 | U125208 | 2018-12-11 | 2019-05-23 | 2020-12-31 |  | BJLONE | 2019-05-24 | 2019-05-23 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 10.9833 | 2 | 6787.83 | 596.83 | 0 | 35.78 | 6155.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026869900 |  | 501249897 |  | 6712204I | 1962845 | U461383 |  | 555 | EX | INSTALL 225' OF 2"PMMP MAIN | 2600B | WOODWIND | 194 WOODWIND CT | 113 | NIC | 2019-05-30 | U125423 | U461383 | 2019-04-09 | 2019-05-10 | 2019-05-24 | 2019-05-24 | DDAVIS | 2019-05-24 | 2019-05-20 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP8699 |  |  | 100 | 055532190268699 | 43.75 | 885 | 12861.74 | 2298.64 | 887.9 | 1026.98 | 6929.54 | 0 | 24.93 | 1693.75 | 177
KY | KY - WEST | 2621 | 19680070700 |  | 100320215 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 224 SHADY LN | 067 | LEX | 2019-05-24 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-05-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.1667 | 1 | 2534.8 | 124.59 | 0 | 51.57 | 2358.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19682869200 |  | 100460810 |  | 6716204K |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BELLEAU WOOD | 3832 BELLEAU WOOD DR | 067 | LEX | 2019-05-30 | U125208 | U125208 | 2019-02-22 | 2019-05-24 | 2021-02-28 |  | DBANKS | 2019-05-24 | 2019-05-24 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.4833 | 2 | 2608.74 | 484.25 | 160.73 | 29.04 | 1934.72 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689096600 |  | 100239608 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | POPLAR | 102 POPLAR ST | 089 | RUS | 2019-05-24 | U125566 | U131066 | 2019-03-18 | 2019-11-27 |  |  | DAVID SKAGGS | 2019-05-24 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.23333 | 1 | 2384.07 | 13.11 | 0 | 5.66 | 2365.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19708901500 |  | 100311367 |  | 6712204D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HALIFAX | 612 HALIFAX DR | 067 | LEX | 2019-05-30 | U125208 | U129939 | 2019-05-24 | 2019-05-22 | 2019-05-22 |  | MCRISP | 2019-05-24 | 2019-05-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.8 | 5 | 1439.59 | 1131.76 | 239.89 | 67.94 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19709010600 |  | 500010329 |  | W-905/34 |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BERRYMAN | 4140 BERRYMAN CT | 067 | LEX | 2019-05-29 | U125208 | U129939 | 2019-05-24 | 2019-05-23 | 2019-06-10 |  | MCRISP | 2019-05-27 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.65 | 4 | 801.5 | 638.82 | 124.33 | 38.35 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12965292800 |  | 100320231 |  | 6716208K | 1748686 |  |  | 566 | EX | RETIRE S/L W/17-0267361-00 | 2600B | SHADY | 241 SHADY LN | 067 | LEX | 2019-11-12 | U126284 | U124967 | 2012-04-16 | 2019-12-31 | 2019-12-31 |  | JOSH PASLEY | 2019-05-28 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 |  | 1
KY | KY - WEST | 2621 | 18026784100 |  |  |  | 6716212H | 1853770 | U122858 |  | 562 | EX | RETIRE 994'-6" PM&CS | 2600B | JEFFERSON | JEFFERSON ST | 067 | LEX | 2019-06-13 | U123258 | U122858 | 2018-07-13 | 2019-05-30 | 2019-05-30 | 2018-10-13 | A PARRIS | 2019-05-28 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP7841 |  |  | 100 | 056232180267841 |  | 0 | 564.55 | 0 | 0 | 0 | 564.55 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572286200 |  | 100279759 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 117 SUNSET DR | 073 | FRA | 2019-05-28 | U126309 | U131066 | 2018-01-04 | 2019-12-31 |  |  | JAMIE LYNN | 2019-05-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.4333 | 1 | 1338.51 | 75.29 | 0 | 17.36 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572286400 |  | 100279760 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 119 SUNSET DR | 073 | FRA | 2019-05-28 | U126309 | U131066 | 2018-01-04 | 2019-12-31 |  |  | JAMIE LYNN | 2019-05-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.5667 | 1 | 2368.42 | 342.97 | 0 | 79.04 | 1946.41 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572286600 |  | 100279761 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 121 SUNSET DR | 073 | FRA | 2019-06-11 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2458.13 | 0 | 0 | 0 | 2458.13 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572286700 |  | 100279835 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 122 SUNSET DR | 073 | FRA | 2019-06-11 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18577395900 |  | 100461079 |  | 6716212K | 1746168 |  |  | 565 | EX | RPLC SL/17026714900/ | 2600B | PINE | 756 PINE ST | 067 | LEX | 2019-05-28 | U461439 | U131066 | 2018-01-26 | 2019-12-31 |  |  | A PARRIS | 2019-05-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2196.26 | 0 | 0 | 0 | 2196.26 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18588355300 |  | 100357408 |  | 6740232M | 1745023 |  |  | 565 | EX | RPLC SL/17026708900/ | 2600B | PLEASANT | 1126 PLEASANT ST | 017 | PAR | 2019-05-28 | U123111 | U131066 | 2018-02-19 | 2019-11-27 |  |  | LYN STAFFORD | 2019-05-28 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 8.75 | 1 | 1700.51 | 493.2 | 0 | 153.52 | 1053.79 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19667439700 |  | 100282567 |  | 6712228B | 1855043 |  |  | 566 | EX | ABANDON / RI 05-23-19 | 2621P | HAMILTON | 105 S HAMILTON ST | 209 | GEO | 2019-05-28 | BJLONE | U126129 | 2019-01-09 | 2019-01-30 | 2019-02-09 |  | BJLONE | 2019-05-28 | 2019-05-21 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 27.8 | 7 | 1303.6 | 1229.83 | 0 | 73.77 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673608600 |  | 100310654 |  | 6712208L | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2903 CLAYS MILL RD | 067 | LEX | 2019-05-28 | U126284 | U131066 | 2019-01-30 | 2019-11-27 |  |  | JOSH PASLEY | 2019-05-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 5.0833 | 1 | 1770.57 | 281.26 | 0 | 88.83 | 1400.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680870800 |  | 100461194 |  | 6716204C |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LAREDO | 3441 LAREDO DR 7 | 067 | LEX | 2019-05-30 | U125208 | U125208 | 2019-02-12 | 2019-05-28 | 2021-02-28 |  | LSTANFI | 2019-05-28 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.35 | 1 | 2327.36 | 205.55 | 262.86 | 12.34 | 1846.61 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691674900 |  | 100328589 |  | 6720208F | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1905 FONTAINE RD | 067 | LEX | 2019-05-29 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-05-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 7125.83 | 0 | 4867.03 | 0 | 2258.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691675000 |  | 100328588 |  | 6720208F | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1909 FONTAINE RD | 067 | LEX | 2019-05-29 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-05-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1671.99 | 0 | 0 | 0 | 1671.99 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19698106500 |  | 100278279 |  | 6688228B |  |  |  | 565 | EX | REPLACE SERV | 2621P | ARAPAHO | 1038 ARAPAHO TL | 073 | FRA | 2019-05-28 | CDESPAI | U125208 | 2019-04-17 | 2049-12-31 |  |  | CDESPAI | 2019-05-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 8.5 | 1 | 5487.53 | 488.68 | 423.39 | 939.7 | 3635.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 02494876200 |  | 500480364 | 22 | 6712208M | 1315787 |  |  | 566 | EX | RETIRE SERVICE 500480364 | 2621P | HARRODSBURG | 3955 HARRODSBURG RD HSE | 067 | LEX | 2019-05-29 | JENSMIN | SWCANOY | 2002-01-21 | 2019-05-28 |  |  | JENSMIN | 2019-05-29 | 2019-05-23 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.15 | 2 | 2243.82 | 537.39 | 9.86 | 637.29 | 1059.28 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572286800 |  | 100279762 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 123 SUNSET DR | 073 | FRA | 2019-06-11 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671928900 |  | 100353724 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 137 W 2ND ST | 161 | MAY | 2019-05-29 | U126286 | U131066 | 2019-01-22 | 2019-11-27 |  |  | TYLER ALLISON | 2019-05-29 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1616.95 | 0 | 0 | 0 | 1616.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673204500 |  | 100325916 |  | 6720208E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER / | 2621D | DUKE | 366 DUKE RD | 067 | LEX | 2019-05-30 | U125208 | AOC SYST | 2019-01-28 | 2019-01-04 | 2019-02-05 |  | LSTANFI | 2019-05-29 | 2019-04-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.4667 | 9 | 4583.23 | 722.12 | 597.68 | 169.13 | 3094.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678821500 |  | 100299210 |  | 6716216N | 1855322 |  |  | 565 | EX | REPLACE SL W/18026792400 | 2600B | LARCH | 236 LARCH LN | 067 | LEX | 2019-05-29 | U123111 | U131066 | 2019-02-01 | 2019-12-31 |  |  | LYN STAFFORD | 2019-05-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1509.22 | 0 | 0 | 0 | 1509.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680072000 |  | 100320221 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 244 SHADY LN | 067 | LEX | 2019-05-29 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-05-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0 | 1 | 2422.79 | 0 | 0 | 0 | 2422.79 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19685900500 |  | 100241764 |  | 7356256P | 1859020 |  |  | 565 | EX | RPLC SL/18026844201/ | 2600B | 49TH | 320 49TH ST | 019 | ASH | 2019-05-31 | U125573 | U131066 | 2019-03-04 | 2019-11-27 |  |  | BCOFER | 2019-05-29 |  | 2019-05-29 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1976.84 | 0 | 0 | 0 | 1976.84 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689097400 |  | 100239616 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | POPLAR | 116 POPLAR ST RR | 089 | RUS | 2019-05-29 | U125566 | U131066 | 2019-03-18 | 2019-11-27 |  |  | DAVID SKAGGS | 2019-05-29 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.35 | 1 | 2095.4 | 19.1 | 0 | 6.24 | 2070.06 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691675100 |  | 100328552 |  | 6720208F | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1910 FONTAINE RD | 067 | LEX | 2019-06-03 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-05-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2517.2 | 0 | 0 | 0 | 2517.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691675400 |  | 100328553 |  | 6720208F | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1912 FONTAINE RD | 067 | LEX | 2019-06-04 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-05-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1778.46 | 0 | 0 | 0 | 1778.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19694444800 |  | 100290771 |  | 6720212B | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | WITHERS | 125 WITHERS AV | 067 | LEX | 2019-06-04 | U128555 | AOC SYST | 2019-04-03 | 2019-05-29 | 2019-05-29 |  | LSTANFI | 2019-05-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.3667 | 3 | 2830.09 | 217.06 | 157.93 | 13 | 2442.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19696398600 |  | 100282522 |  | 6712L28B |  |  |  | 565 | EX | CONT - REPL SERV | 2621P | MULBERRY | 119 S MULBERRY ST | 209 | GEO | 2019-05-29 | CDESPAI | U125208 | 2019-04-11 | 2049-12-31 |  |  | CDESPAI | 2019-05-29 | 2019-05-23 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.2833 | 2 | 5022.99 | 417.34 | 300.05 | 782.27 | 3523.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19699473000 |  | 100334188 |  | 6720212O |  |  |  | 565 | EX | RELOCATE MTR MNFLD/SERV LINE | 2621P | HENRY CLAY | 714 HENRY CLAY BV | 067 | LEX | 2019-05-30 | U125208 | U125208 | 2019-04-22 | 2019-05-22 |  |  | JENSMIN | 2019-05-29 | 2019-05-28 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 12.5 | 2 | 4923.42 | 700.74 | 370.97 | 269.78 | 3581.93 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19705992700 |  | 100267874 |  | 7356216C |  |  |  | 566 | EX | DEMO / ABANDON / RA 05-20-19 | 2621P | LACKEY | 513 N LACKEY AV | 127 | LOU | 2019-05-29 | MCOLLET | U132002 | 2019-05-15 | 2019-06-24 | 2019-07-16 |  | MCOLLET | 2019-05-29 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 2.75 | 1 | 383.51 | 165.52 | 21.83 | 196.16 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19707355700 |  | 100254653 |  | 7348264E |  |  |  | 566 | EX | DEMO / ABANDON / RI 05-28-19 | 2621P | WILLIAMS | 1004 WILLIAMS ST | 089 | FLA | 2019-05-29 | MCOLLET | U132002 | 2019-05-20 | 2019-07-01 | 2019-07-23 |  | MCOLLET | 2019-05-29 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 9.1333 | 2 | 732.62 | 508.44 | 0 | 224.18 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19709035700 |  | 100301672 |  | 6712212H |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LIVERPOOL | 237 LIVERPOOL RD | 067 | LEX | 2019-05-30 | U125208 | U125208 | 2019-05-24 | 2019-05-22 | 2019-05-22 |  | LSTANFI | 2019-05-29 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.9167 | 2 | 2422.65 | 518.17 | 207 | 31.09 | 1666.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19709496300 |  | 501103679 |  | 6720212O | 1206590 |  |  | 565 | EX | REPLACE SVC LINE | 2621P | HENRY CLAY | 720 HENRY CLAY BV | 067 | LEX | 2019-05-29 | JENSMIN | U130193 | 2019-05-29 | 2019-05-29 |  |  | JENSMIN | 2019-05-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.15 | 1 | 1767.7 | 8.41 | 0 | 10.67 | 1748.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 17026714900 |  |  |  | 6716212G | 1746168 | U461383 |  | 557 | EX | INSTALL 4225' OF 2"PMMP MAIN | 2600B | MADISON | MADISON PL | 067 | LEX | 2019-06-18 | U462463 | U461383 | 2017-06-27 | 2019-01-04 | 2019-07-01 | 2019-04-12 | A PARRIS | 2019-05-30 | 2018-03-12 | 2018-03-19 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP7149 | AMRCB |  | 100 | 055732170267149 | 1507.8 | 889350 | 923117.22 | 89297.12 | 50892.29 | 29400.7 | 616430.76 | 0 | 16521.61 | 120574.74 | 4235
KY | KY - WEST | 2621 | 17026715000 |  |  |  | 6716212G | 1746168 | U461383 |  | 558 | EX | RETIRE 4000' OF 4"BS/CILP MAIN | 2600B | MADISON | MADISON PL | 067 | LEX | 2019-06-19 | U462463 | U461383 | 2017-06-27 | 2019-07-01 | 2019-07-01 | 2019-05-29 | A PARRIS | 2019-05-30 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP7150 | AMRCB |  | 100 | 055832170267150 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572286100 |  | 100279838 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 116 SUNSET DR | 073 | FRA | 2019-05-30 | U126309 | U131066 | 2018-01-04 | 2019-12-31 |  |  | JAMIE LYNN | 2019-05-30 | 2019-05-29 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 10.5 | 2 | 1921.36 | 548.97 | 0 | 126.53 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678782000 |  | 100299254 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 267 LARCH LN | 067 | LEX | 2019-05-31 | U123111 | U131066 | 2019-02-01 | 2019-11-27 |  |  | LYN STAFFORD | 2019-05-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2160.74 | 0 | 0 | 0 | 2160.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678783500 |  | 100299245 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 299 LARCH LN | 067 | LEX | 2019-05-31 | U123111 | U131066 | 2019-02-01 | 2019-11-27 |  |  | LYN STAFFORD | 2019-05-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1509.22 | 0 | 0 | 0 | 1509.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680071300 |  | 100320235 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 233 SHADY LN | 067 | LEX | 2019-05-31 | HROGERS | U131066 | 2019-02-07 | 2019-11-27 |  |  | MARK ROGERS | 2019-05-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2166.59 | 0 | 0 | 0 | 2166.59 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680071700 |  | 100320220 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 240 SHADY LN | 067 | LEX | 2019-05-31 | HROGERS | U131066 | 2019-02-07 | 2019-11-27 |  |  | MARK ROGERS | 2019-05-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1829.78 | 0 | 0 | 0 | 1829.78 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19685907300 |  | 100241771 |  | 7356256P | 1859020 |  |  | 565 | EX | REPLACE SL W/18026844201 | 2600B | 49TH | 331 49TH ST | 019 | ASH | 2019-05-31 | U125573 | U131066 | 2019-03-04 | 2019-12-31 |  |  | BCOFER | 2019-05-30 |  | 2019-05-30 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1420.94 | 0 | 0 | 0 | 1420.94 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19691623000 |  | 100343250 |  | 7236212C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D09404 | 2621P | PREWITT | 434 PREWITT PK | 173 | MT | 2019-05-31 | U125208 | U125208 | 2019-03-27 | 2019-09-26 | 2021-03-31 |  | DENNING | 2019-05-30 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 17.05 | 3 | 1697.58 | 840.86 | 137.29 | 211.32 | 508.11 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19693994300 |  | 100308163 |  | 6716212J |  |  |  | 566 | EX | DEMO / ABANDON / RA 04-16-19 | 2621P | ANGLIANA | 527 ANGLIANA AV | 067 | LEX | 2019-05-31 | U125208 | U132002 | 2019-04-02 | 2019-04-24 | 2019-04-24 |  | JENSMIN | 2019-05-30 | 2019-05-06 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.6833 | 5 | 3836.77 | 732.27 | 13.12 | 667.54 | 2423.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19709889800 |  | 100286218 |  | 6764172G |  |  |  | 566 | EX | ABANDNON SERV | 2621P | SUGAR HOLLOW | 50 SUGAR HOLLOW RD | 065 | IRV | 2019-05-30 | DBANKS | U131555 | 2019-05-30 | 2019-05-30 |  |  | DBANKS | 2019-05-30 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 11.1833 | 2 | 571.7 | 538.07 | 1.37 | 32.26 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18026781000 |  |  |  | 6716216P | 1425507 | BKSLONE |  | 575 | EX | R-1222 ACQUIRE 25X25 REG SITE | 2600E | NANDINO | 968 NANDINO BV | 067 | LEX | 2019-12-13 | U462463 | BKSLONE | 2018-06-19 | 2019-12-30 | 2019-12-31 | 2019-05-31 | AUTUMN DMYTREWYCZ W/FISHEL | 2019-05-31 |  |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00575 | 3207513 |  |  | WP7810 |  |  | 100 | 751332180267810 |  | 1 | 18817.11 | 0 | 0 | 15000 | 3782.69 | 0 | 34.42 | 0
KY | KY - WEST | 2623 | 18572286300 |  | 100279837 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 118 SUNSET DR | 073 | FRA | 2019-05-31 | U126309 | U131066 | 2018-01-04 | 2019-12-31 |  |  | JAMIE LYNN | 2019-05-31 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 1 | 1760.5 | 418.23 | 0 | 96.41 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572286500 |  | 100279836 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 120 SUNSET DR | 073 | FRA | 2019-06-11 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-05-31 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18594263600 |  | 100337765 |  | 6720212F | 1855043 | U125765 |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | 7TH | 310 E 7TH ST | 067 | LEX | 2019-06-10 | U125208 | U125765 | 2018-03-14 | 2018-12-21 |  |  | ATWILLI | 2019-05-31 | 2019-04-30 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.35 | 3 | 1920.28 | 389.61 | 18.83 | 178.32 | 1333.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18636015100 |  | 100337761 |  | 6720212F |  |  |  | 566 | EX | ABANDON / IDLE / CUST CONVRT | 2621P | ELM TREE | 666 ELM TREE LN | 067 | LEX | 2019-05-31 | ATWILLI | U126129 | 2018-08-17 | 2019-05-31 |  |  | ATWILLI | 2019-05-31 | 2019-03-14 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.7 | 8 | 1870.55 | 408.32 | 18.83 | 45.39 | 1398.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026865100 |  |  |  | 6720216M | 1425507 | BKSLONE |  | 575 | EX | ACQUIRE ESMT OVER CARMAN PROPY | 2600E | COLESBURY | 1505 COLESBURY CR | 067 | LEX | 2020-01-15 | U123258 | BKSLONE | 2019-03-07 | 2019-04-29 | 2019-06-30 | 2019-05-31 | AUTUMN DYNTREWYCZ W/FISHEL | 2019-05-31 |  |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00575 | 3207513 |  |  | WP8651 |  |  | 100 | 751332190268651 |  | 1 | 130139.09 | 0 | 0 | 125000 | 4864.24 | 0 | 274.85 | 0
KY | KY - WEST | 2621 | 19678781000 |  | 100299259 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 247 LARCH LN | 067 | LEX | 2019-05-31 | U123111 | U131066 | 2019-02-01 | 2019-11-27 |  |  | LYN STAFFORD | 2019-05-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678781600 |  | 100299256 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 259 LARCH LN | 067 | LEX | 2019-05-31 | U123111 | U131066 | 2019-02-01 | 2019-11-27 |  |  | LYN STAFFORD | 2019-05-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1509.22 | 0 | 0 | 0 | 1509.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678781700 |  | 100299216 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 260 LARCH LN | 067 | LEX | 2019-06-05 | U123111 | U131066 | 2019-02-01 | 2019-11-27 |  |  | LYN STAFFORD | 2019-05-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1509.22 | 0 | 0 | 0 | 1509.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678782200 |  | 100299253 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 271 LARCH LN | 067 | LEX | 2019-05-31 | U123111 | U131066 | 2019-02-01 | 2019-11-27 |  |  | LYN STAFFORD | 2019-05-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1053.79 | 0 | 0 | 0 | 1053.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678782500 |  | 100299251 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 279 LARCH LN | 067 | LEX | 2019-05-31 | U123111 | U131066 | 2019-02-01 | 2019-11-27 |  |  | LYN STAFFORD | 2019-05-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1053.79 | 0 | 0 | 0 | 1053.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680071400 |  | 100320218 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 234 SHADY LN | 067 | LEX | 2019-05-31 | HROGERS | U131066 | 2019-02-07 | 2019-11-27 |  |  | MARK ROGERS | 2019-05-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2585.81 | 0 | 0 | 0 | 2585.81 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19682870500 |  | 100445683 |  | 6716204H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D221728 | 2621P | WINDGATE | 3525 WINDGATE WY | 067 | LEX | 2019-06-03 | U125208 | U125208 | 2019-02-22 | 2019-05-31 | 2021-02-28 |  | LSTANFI | 2019-05-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.45 | 1 | 2580.4 | 88.99 | 254.28 | 5.34 | 2231.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19683312900 |  | 100452429 |  | 6716204L |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | TROY | 717 TROY TL | 067 | LEX | 2019-06-03 | U125208 | U125208 | 2019-02-25 | 2019-05-31 | 2021-02-28 |  | LSTANFI | 2019-05-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.9 | 1 | 2086.61 | 116.6 | 174.58 | 6.99 | 1788.44 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19685900800 |  | 100241770 |  | 7356256P | 1859020 |  |  | 565 | EX | RPLC SL/18026844201/ | 2600B | 49TH | 335 49TH ST 1 | 019 | ASH | 2019-05-31 | U125573 | U131066 | 2019-03-04 | 2019-11-27 |  |  | BCOFER | 2019-05-31 |  | 2019-05-31 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1420.94 | 0 | 0 | 0 | 1420.94 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19708604900 |  | 100344052 |  | TRANSCANA |  |  |  | 566 | EX | ABANDON | 2621P | NEW CUT | 2390 NEW CUT RD | 173 | JEF | 2019-06-05 | U125208 | U125208 | 2019-05-23 | 2019-06-21 |  |  | DENNING | 2019-05-31 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.7 | 3 | 103.72 | 82.9 | 0 | 20.82 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19708953300 |  | 100442309 |  | 6680228H |  |  |  | 566 | EX | DEMO / ABANDON / RI 05-28-19 | 2621P | MOSS | 1010 MOSS LN | 073 | FRA | 2019-06-03 | U125208 | U132002 | 2019-05-24 | 2019-07-05 | 2019-07-26 |  | BJLONE | 2019-05-31 | 2019-05-31 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8.1667 | 2 | 446.42 | 421.17 | 0 | 25.25 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19708967600 |  | 100438846 |  | 6680228H |  |  |  | 566 | EX | DEMO / ABANDON / RI 05-28-19 | 2621P | MOSS | 931 MOSS LN | 073 | FRA | 2019-06-05 | U125208 | U125208 | 2019-05-24 | 2019-06-21 | 2019-06-23 |  | BJLONE | 2019-05-31 | 2019-05-30 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 7.8167 | 4 | 441.94 | 412.12 | 0 | 29.82 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19709210800 |  | 100343253 |  | 7236212C |  |  |  | 566 | EX | RETIRE SERVICE LINE - LEAKAGE | 2621P | PREWITT | 452 PREWITT PK | 173 | MT | 2019-05-31 | DENNING | U130193 | 2019-05-28 | 2019-09-26 | 2021-03-31 |  | DENNING | 2019-05-31 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26290043 | 0.5 | 3 | 35.22 | 28.14 | 0 | 7.08 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19710713100 |  | 501186669 |  | 7332132K | 1963346 |  |  | 565 | EX | REPLACE SL W/19026872900 | 2600B | PURPOSE | 100 PURPOSE RD | 119 | PIP | 2019-05-31 | MBLANKE | U131066 | 2019-05-31 | 2019-12-31 |  |  | MBLANKE | 2019-05-31 |  |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26330032 | 0.61667 | 1 | 1698.64 | 35.19 | 0 | 10.76 | 1652.69 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19710722700 |  | 100349073 |  | 6748208M |  |  |  | 565 | EX | GRADE 1 REPLACE | 2621P | PARK | 39 PARK AV | 049 | WIN | 2019-05-31 | DENNING | U129939 | 2019-05-31 | 2019-05-31 | 2019-05-31 |  | DENNING | 2019-05-31 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 13.75 | 3 | 1057.45 | 678.02 | 209.04 | 170.39 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19710779100 |  | 100323305 |  | 6716208P |  |  |  | 565 | EX | GRADE 1 REPLACE SERV D095356 | 2621P | ALBANY | 848 ALBANY RD | 067 | LEX | 2019-06-03 | U125208 | U129939 | 2019-05-31 | 2019-05-31 | 2019-05-31 |  | LSTANFI | 2019-05-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.6833 | 1 | 3093.65 | 227.06 | 297.86 | 13.61 | 2555.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18026745800 |  |  |  | 6716212G | 1746168 | U461383 |  | 584 | EX | ABANDON REG STATION #1018 | 2600E | PINE | 420 PINE ST | 067 | LEX | 2019-06-03 | U462463 | U461383 | 2018-01-23 | 2018-12-31 | 2018-12-31 | 2019-05-29 | CYNTHIA FARIS | 2019-06-01 | 2019-05-29 |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00584 | 3200584 |  |  | WP7458 |  |  | 100 | 058432180267458 | 23.85 | 0 | 1548.46 | 1357.25 | 0 | 191.21 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19026879200 |  |  |  | 7356256K | 1852042 | U122858 |  | 588 | EX | RETIRE SETTING - PAPER JO ONLY | 2631M | KILGORE | 901 KILGORE DR | 019 | ASH | 2019-06-03 | U462463 | U122858 | 2019-05-31 | 2019-12-31 | 2019-12-31 | 2019-06-01 | CYNTHIA FARIS | 2019-06-01 |  |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00588 | 3200588 |  |  | WP8792 |  |  | 100 | 058832190268792 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07683531100 |  | 100337625 |  | 6720212E | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | 7TH | 114 E 7TH ST | 067 | LEX | 2019-06-03 | JENSMIN | DMCCULL | 2007-04-18 | 2019-06-03 | 2019-06-03 |  | JENSMIN | 2019-06-03 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.4 | 1 | 1608.75 | 256.45 | 10.76 | 250 | 1091.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11880626400 |  | 100337420 |  | 700000000 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | 6TH | 410 E 6TH ST | 067 | LEX | 2019-06-03 | JENSMIN | U906307 | 2011-01-24 | 2019-06-03 |  |  | JENSMIN | 2019-06-03 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.7833 | 1 | 1157.15 | 103.99 | 8.93 | 101.35 | 942.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11905429800 |  | 100412807 |  | 16720216I |  |  |  | 566 | EX | ABANDON/ IDLE FOR 36 MONTHS | 2600B | HOLLOW CREEK | 449 HOLLOW CREEK RD | 067 | LEX | 2019-06-03 | LSTANFI | U906631 | 2011-05-06 | 2019-06-03 |  |  | LSTANFI | 2019-06-03 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.0667 | 2 | 778.61 | 51.49 | 76.73 | 10.49 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 17547369000 |  | 100344979 |  | 6700224O |  |  |  | 565 | EX | REPL SERV-MOVE MTR W/2315 | 2621P | WINTER | 336 S WINTER ST | 239 | MID | 2019-06-03 | CDESPAI | U125208 | 2017-09-22 | 2017-09-27 |  |  | CDESPAI | 2019-06-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.0667 | 1 | 3521.29 | 422.63 | 309.55 | 780.68 | 2008.43 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572285300 |  | 100279842 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 110 SUNSET DR | 073 | FRA | 2019-06-11 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-06-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1886.7 | 0 | 0 | 0 | 1886.7 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572285700 |  | 100279757 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 113 SUNSET DR | 073 | FRA | 2019-06-11 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-06-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1762.99 | 0 | 0 | 0 | 1762.99 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572285800 |  | 100279839 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 114 SUNSET DR | 073 | FRA | 2019-06-11 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-06-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2123.54 | 0 | 0 | 0 | 2123.54 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572285900 |  | 100279758 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 115 SUNSET DR | 073 | FRA | 2019-06-11 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-06-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678779900 |  | 100299265 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 219 LARCH LN | 067 | LEX | 2019-06-03 | U123111 | U131066 | 2019-02-01 | 2019-11-27 |  |  | LYN STAFFORD | 2019-06-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1509.22 | 0 | 0 | 0 | 1509.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678780000 |  | 100299207 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400 | 2600B | LARCH | 220 LARCH LN | 067 | LEX | 2019-06-03 | U123111 | U131066 | 2019-02-01 | 2019-06-28 |  |  | LYN STAFFORD | 2019-06-03 | 2019-05-21 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.6 | 2 | 1538 | 87.26 | 0 | 38.16 | 1412.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678780300 |  | 100299263 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 227 LARCH LN | 067 | LEX | 2019-06-03 | U123111 | U131066 | 2019-02-01 | 2019-11-27 |  |  | LYN STAFFORD | 2019-06-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1202.07 | 0 | 0 | 0 | 1202.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678780500 |  | 100299262 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 233 LARCH LN | 067 | LEX | 2019-06-05 | U123111 | U131066 | 2019-02-01 | 2019-11-27 |  |  | LYN STAFFORD | 2019-06-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1053.79 | 0 | 0 | 0 | 1053.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678780800 |  | 100299260 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 243 LARCH LN | 067 | LEX | 2019-06-04 | U123111 | U131066 | 2019-02-01 | 2019-11-27 |  |  | LYN STAFFORD | 2019-06-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1053.79 | 0 | 0 | 0 | 1053.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678782400 |  | 100299220 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 276 LARCH LN | 067 | LEX | 2019-06-03 | U123111 | U131066 | 2019-02-01 | 2019-11-27 |  |  | LYN STAFFORD | 2019-06-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1053.79 | 0 | 0 | 0 | 1053.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680070400 |  | 100320214 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 220 SHADY LN | 067 | LEX | 2019-06-04 | HROGERS | U131066 | 2019-02-07 | 2019-11-27 |  |  | MARK ROGERS | 2019-06-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3868.88 | 0 | 0 | 0 | 3868.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680071200 |  | 100320217 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 230 SHADY LN | 067 | LEX | 2019-06-04 | HROGERS | U131066 | 2019-02-07 | 2019-11-27 |  |  | MARK ROGERS | 2019-06-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2333.33 | 0 | 0 | 0 | 2333.33 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19685907500 |  | 100241769 |  | 7356256P | 1859020 |  |  | 565 | EX | REPLACE SL W/18026844201 | 2600B | 49TH | 339 49TH ST | 019 | ASH | 2019-06-05 | U125573 | U131066 | 2019-03-04 | 2019-12-31 |  |  | BCOFER | 2019-06-03 |  | 2019-06-03 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1451.58 | 0 | 0 | 0 | 1451.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691677500 |  | 100328578 |  | 6720208F | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1931 FONTAINE RD | 067 | LEX | 2019-06-03 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-06-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2405.82 | 0 | 0 | 0 | 2405.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19706490300 |  | 100314663 |  | 6716212L |  |  |  | 566 | EX | DEMO 5-28 / ABN & RA 05-24-19 | 2621P | LIMESTONE | 357 S LIMESTONE ST | 067 | LEX | 2019-06-05 | U125208 | U132002 | 2019-05-16 | 2019-06-27 | 2019-07-19 |  | MCRAIG | 2019-06-03 | 2019-06-03 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 11.2 | 2 | 771.99 | 583.36 | 154.78 | 33.85 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19709516500 |  | 100268089 |  | 7356256B |  |  |  | 566 | EX | DEMO / ABANDON W100268088* | 2621P | 22ND | 218< 22ND ST | 019 | ASH | 2019-06-03 | MCOLLET | U132002 | 2019-05-29 | 2019-06-28 | 2019-06-29 |  | MCOLLET | 2019-06-03 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.11667 | 1 | 14.76 | 6.91 | 0 | 7.85 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19709532900 |  | 100268088 |  | 7356256B |  |  |  | 566 | EX | DEMO / ABANDON W100268089+ | 2621P | 22ND | 218 22ND ST | 019 | ASH | 2019-06-05 | U125208 | U132002 | 2019-05-29 | 2019-07-08 | 2019-07-29 |  | MCOLLET | 2019-06-03 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 7.3333 | 2 | 604.9 | 424.52 | 0 | 180.38 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19709565900 |  | 500501069 |  | 7260280N |  |  |  | 566 | EX | DEMO / ABANDON / RI 05-30-19 | 2621P | CLARK | 421 CLARK ST | 161 | MAY | 2019-06-03 | SDADAMS | U132002 | 2019-05-29 | 2019-07-09 | 2019-07-30 |  | SDADAMS | 2019-06-03 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 17.3833 | 3 | 1038.21 | 963.06 | 19.23 | 55.92 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19710996000 |  | 100271396 |  | 6736252N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094019 | 2621P | MEADOW | 308 MEADOW LN | 097 | CYN | 2019-06-05 | U125208 | U131167 | 2019-06-03 | 2019-05-21 | 2019-06-05 |  | DBANKS | 2019-06-03 | 2019-06-03 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 37.85 | 6 | 1951.84 | 1851.52 | 0 | 100.32 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19711000600 |  | 100305303 |  | 6712212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LINSTEAD | 1649 LINSTEAD DR | 067 | LEX | 2019-06-05 | U125208 | U131167 | 2019-06-03 | 2019-06-05 | 2019-06-23 |  | LSTANFI | 2019-06-03 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.5 | 2 | 2842.39 | 363 | 284.48 | 74.05 | 2120.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19711001100 |  | 100412806 |  | 6720216N |  |  |  | 566 | EX | ABN OLD UNUSED | 2621P | HOLLOW CREEK | 437 HOLLOW CREEK RD | 067 | LEX | 2019-06-03 | LSTANFI | U131167 | 2019-06-03 | 2019-06-03 |  |  | LSTANFI | 2019-06-03 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.86667 | 2 | 126.98 | 41.74 | 76.73 | 8.51 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19711007800 |  | 100328576 |  | 6720208F | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1937 FONTAINE RD | 067 | LEX | 2019-06-03 | U125559 | U131279 | 2019-06-03 | 2019-12-31 |  |  | BJACKSON | 2019-06-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1828.66 | 0 | 0 | 0 | 1828.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19711016500 |  | 100416237 |  | 6720216N |  |  |  | 566 | EX | ABN SERVICE | 2621P | HOLLOW CREEK | 441 HOLLOW CREEK RD | 067 | LEX | 2019-06-05 | U125208 | U131167 | 2019-06-03 | 2019-10-05 | 2021-04-30 |  | LSTANFI | 2019-06-03 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.36667 | 2 | 1578.15 | 120.33 | 153.46 | 24.56 | 1279.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19711095800 |  | 100305140 |  | 6712212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D093751 | 2621P | TRAVELLER | 1833 TRAVELLER RD | 067 | LEX | 2019-06-05 | U125208 | U131167 | 2019-06-03 | 2019-06-03 | 2021-05-31 |  | LSTANFI | 2019-06-03 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.2 | 2 | 2085.63 | 155.3 | 307.34 | 31.68 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19711112400 |  | 100305141 |  | 6712212O |  |  |  | 565 | EX | REPLACE | 2621P | TRAVELLER | 1837 TRAVELLER RD | 067 | LEX | 2019-06-05 | U125208 | U131167 | 2019-06-03 | 2019-06-03 |  |  | LSTANFI | 2019-06-03 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.26667 | 2 | 1805.79 | 12.65 | 199.27 | 2.56 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19711140800 |  | 100301057 |  | 6716212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094835 | 2621P | BRITTANY | 1640 BRITTANY LN | 067 | LEX | 2019-06-05 | U125208 | U131167 | 2019-06-03 | 2019-05-31 | 2021-05-31 |  | LSTANFI | 2019-06-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.2 | 2 | 1651.97 | 61.18 | 246.8 | 12.49 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 08727717300 |  | 100316724 |  | 6716208F |  |  |  | 566 | EX | ABANDON / RI 03-01-06 DBANKS | 2621P | PENSACOLA | 1871 PENSACOLA DR | 067 | LEX | 2019-06-04 | MCRAIG | RPOLLY | 2008-04-16 | 2019-06-12 |  |  | MCRAIG | 2019-06-04 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.4833 | 3 | 413.8 | 391.1 | 0 | 22.7 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572284900 |  | 100279845 |  | 6688228J | 1748294 |  |  | 565 | EX | RPLC SL/17026731300/ | 2600B | SUNSET | 104 SUNSET DR | 073 | FRA | 2019-06-11 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-06-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1865.33 | 0 | 0 | 0 | 1865.33 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572285100 |  | 100279843 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 108 SUNSET DR | 073 | FRA | 2019-06-11 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-06-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1456.47 | 0 | 0 | 0 | 1456.47 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572285200 |  | 100279755 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 109 SUNSET DR | 073 | FRA | 2019-06-11 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-06-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1946.41 | 0 | 0 | 0 | 1946.41 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572285400 |  | 100279756 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 111 SUNSET DR | 073 | FRA | 2019-06-11 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-06-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1946.41 | 0 | 0 | 0 | 1946.41 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19026859700 |  |  |  | 7360252I | 1961267 | U131982 |  | 909 | EX | INSTALL I&C EQUIPMENT | 2631M | CENTER | 2510 CENTER ST RR | 019 | CAT | 2020-04-10 | U462463 | U131982 | 2019-02-07 | 2019-12-30 | 2019-12-31 | 2019-06-04 | JOSH MULLINS | 2019-06-04 | 2019-05-30 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP8597 |  |  | 100 | 090932190268597 | 22.7333 | 0 | 8028.82 | 1363.85 | 4109.02 | 194.32 | 2316.25 | 0 | 45.38 | 0
KY | KY - EAST | 2631 | 19026859800 |  |  |  | 7360252I | 1961267 | U131982 |  | 910 | EX | RETIRE I&C EQUIPMENT | 2631M | CENTER | 2510 CENTER ST RR | 019 | CAT | 2020-04-10 | U462463 | U131982 | 2019-02-07 | 2019-12-31 | 2019-12-31 | 2019-06-04 | JOSH MULLINS | 2019-06-04 |  |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00910 | 3200910 |  |  | WP8598 |  |  | 100 | 091032190268598 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19026859900 |  |  |  | 7356252P | 1961267 | U131982 |  | 909 | EX | INSTALL I&C EQUIPMENT | 2631M | BARBECUE | BARBECUE RD | 019 | CAT | 2020-03-11 | U462463 | U131982 | 2019-02-07 | 2019-12-30 | 2019-12-31 | 2019-06-04 | JOSH MULLINS | 2019-06-04 | 2019-05-31 |  | F | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00909 | 3200909 |  |  | WP8599 |  |  | 100 | 090932190268599 | 18.7833 | 0 | 9455.97 | 1190.39 | 4232.21 | 192.12 | 3825 | 0 | 16.25 | 0
KY | KY - EAST | 2631 | 19026860000 |  |  |  | 7356252P | 1961267 | U131982 |  | 910 | EX | RETIRE I&C EQUIPMENT | 2631M | BARBECUE | BARBECUE RD | 019 | CAT | 2020-03-11 | U462463 | U131982 | 2019-02-07 | 2019-12-31 | 2019-12-31 | 2019-06-04 | JOSH MULLINS | 2019-06-04 |  |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00910 | 3200910 |  |  | WP8600 |  |  | 100 | 091032190268600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678780600 |  | 100299261 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 239 LARCH LN | 067 | LEX | 2019-06-05 | U123111 | U131066 | 2019-02-01 | 2019-11-27 |  |  | LYN STAFFORD | 2019-06-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1509.22 | 0 | 0 | 0 | 1509.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678781100 |  | 100299213 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 248 LARCH LN | 067 | LEX | 2019-06-04 | U123111 | U131066 | 2019-02-01 | 2019-11-27 |  |  | LYN STAFFORD | 2019-06-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1053.79 | 0 | 0 | 0 | 1053.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678782700 |  | 100299250 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 283 LARCH LN | 067 | LEX | 2019-06-04 | U123111 | U131066 | 2019-02-01 | 2019-11-27 |  |  | LYN STAFFORD | 2019-06-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1608.67 | 0 | 0 | 0 | 1608.67 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678782900 |  | 100299249 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 287 LARCH LN | 067 | LEX | 2019-06-05 | U123111 | U131066 | 2019-02-01 | 2019-11-27 |  |  | LYN STAFFORD | 2019-06-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 990.94 | 0 | 0 | 0 | 990.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680071100 |  | 100320236 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 229 SHADY LN | 067 | LEX | 2019-06-05 | HROGERS | U131066 | 2019-02-07 | 2019-11-27 |  |  | MARK ROGERS | 2019-06-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3252.49 | 0 | 0 | 0 | 3252.49 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19685900900 |  | 100241767 |  | 7356256P | 1859020 |  |  | 565 | EX | RPLC SL/18026844201/ | 2600B | 49TH | 336 49TH ST | 019 | ASH | 2019-06-05 | U125573 | U131066 | 2019-03-04 | 2019-11-27 |  |  | BCOFER | 2019-06-04 |  | 2019-06-04 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1520.66 | 0 | 0 | 0 | 1520.66 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689096300 |  | 100239598 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | OAK | 207 OAK ST | 089 | RUS | 2019-06-04 | U461496 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ROCKIE MULLINS | 2019-06-04 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.25 | 1 | 967.28 | 13.72 | 0 | 4.34 | 949.22 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689097700 |  | 100239602 |  | 7328284B | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | RIDGE | 201 RIDGE ST | 089 | RUS | 2019-06-04 | U461496 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ROCKIE MULLINS | 2019-06-04 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.16667 | 1 | 960.77 | 8.77 | 0 | 2.78 | 949.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691675600 |  | 100328586 |  | 6720208F | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1913 FONTAINE RD 1FL | 067 | LEX | 2019-06-07 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-06-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2233.11 | 0 | 0 | 0 | 2233.11 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19695829000 |  | 100330709 |  | 6720212N | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER / | 2621D | SHERMAN | 220 SHERMAN AV | 067 | LEX | 2019-06-10 | U125208 | AOC SYST | 2019-04-09 | 2019-05-03 | 2019-06-04 |  | JBENNET | 2019-06-04 | 2019-06-04 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 37.8167 | 6 | 2006.91 | 1727.52 | 179.14 | 100.25 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19695921200 |  | 100295622 |  | 6716216K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D000063 | 2621P | OAKWOOD | 1122 OAKWOOD DR | 067 | LEX | 2019-06-05 | U125208 | U125208 | 2019-04-10 | 2019-06-04 | 2021-04-30 |  | LSTANFI | 2019-06-04 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.4667 | 1 | 1856.43 | 348.87 | 155.82 | 20.24 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19706368000 |  | 100312349 |  | 6716208J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HOLLYHILL | 324 HOLLYHILL DR | 067 | LEX | 2019-06-04 | LSTANFI | U125208 | 2019-05-16 | 2019-05-17 | 2019-06-05 |  | LSTANFI | 2019-06-04 | 2019-05-20 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.3333 | 4 | 3207.33 | 410.58 | 299.5 | 24.13 | 2473.12 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19708500700 |  | 100438526 |  | 7352260N |  |  |  | 566 | EX | DEMO / ABANDON / RI 05-29-19 | 2621P | 1ST | 2400 1ST ST W 1 WW | 019 | ASH | 2019-06-04 | MCOLLET | U132002 | 2019-05-23 | 2019-07-03 | 2019-07-25 |  | MCOLLET | 2019-06-04 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 7.6333 | 2 | 589.74 | 435.77 | 27.77 | 126.2 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19708503800 |  | 100438805 |  | 7352260N |  |  |  | 566 | EX | ABANDON / RI 05-29-19 | 2621P | 1ST | 2400 1ST ST W 2 | 019 | ASH | 2019-06-04 | BROBERT | U132002 | 2019-05-23 | 2019-07-03 | 2019-07-25 |  | BROBERT | 2019-06-04 | 2019-06-04 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.4667 | 2 | 630.17 | 330.47 | 21.83 | 277.87 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19710698200 |  | 100239614 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700 | 2600B | POPLAR | 114 POPLAR ST | 089 | RUS | 2019-06-04 | U461496 | U124960 | 2019-05-31 | 2019-12-23 |  |  | ROCKIE MULLINS | 2019-06-04 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.2 | 1 | 2304.55 | 10.96 | 0 | 3.46 | 2290.13 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19710700100 |  | 100347980 |  | 6748208I |  |  |  | 565 | EX | REPLACE SERV LINE | 2621P | SYCAMORE | 15 SYCAMORE ST | 049 | WIN | 2019-06-05 | U125208 | U129939 | 2019-05-31 | 2019-05-31 |  |  | RJJOHNS | 2019-06-04 | 2019-05-31 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 12.15 | 3 | 699.98 | 584.29 | 80.77 | 34.92 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19710998900 |  | 100349611 |  | 6748204A |  |  |  | 566 | EX | ABANDON PER DEMO / RI 6/4/19 | 2621P | KENTUCKY | 109 KENTUCKY ST | 049 | WIN | 2019-06-04 | DENNING | U125208 | 2019-06-03 | 2019-06-04 |  |  | DENNING | 2019-06-04 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 11.9333 | 2 | 878.72 | 670.4 | 0 | 208.32 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19711340800 |  | 100293329 |  | 6720216G |  |  |  | 565 | EX | REPLACE SL D094789 | 2621P | RADCLIFFE | 204 RADCLIFFE RD | 067 | LEX | 2019-06-05 | U125208 | U131167 | 2019-06-04 | 2019-10-30 | 2021-04-30 |  | LSTANFI | 2019-06-04 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.91667 | 1 | 2538.49 | 58.13 | 245.19 | 3.38 | 2231.79 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19711347300 |  | 100350626 |  | 6744208M |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094510 | 2621P | MALLARD | 108 MALLARD LN | 049 | WIN | 2019-06-05 | U125208 | U131167 | 2019-06-04 | 2019-06-03 | 2020-07-31 |  | DBANKS | 2019-06-04 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 20.0667 | 3 | 1322.25 | 1004.53 | 259.44 | 58.28 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19711373700 |  | 100412656 |  | 6680224H |  |  |  | 565 | EX | REPLACE SL | 2621P | PIN OAK | 221 PIN OAK PL | 073 | FRA | 2019-06-04 | CDESPAI | U131167 | 2019-06-04 | 2019-06-04 |  |  | CDESPAI | 2019-06-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8 | 1 | 3788.84 | 480.07 | 161.67 | 27.86 | 3119.24 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19711405400 |  | 100262921 |  | 7352260N |  |  |  | 566 | EX | ABDN SL | 2621P | 1ST | 2400 1ST ST W | 019 | ASH | 2019-06-04 | MCOLLET | U131167 | 2019-06-04 | 2019-06-04 |  |  | MCOLLET | 2019-06-04 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.1 | 1 | 146.09 | 68.32 | 0 | 77.77 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19711520600 |  | 100299259 |  | 6716216N | 1855322 |  |  | 565 | EX | REPLACE SL W/18026792400 | 2600B | LARCH | 247 LARCH LN | 067 | LEX | 2019-06-05 | U123111 | U131066 | 2019-06-04 | 2019-12-31 |  |  | LYN STAFFORD | 2019-06-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.016667 | 1 | 1054.4 | 0.58 | 0 | 0.03 | 1053.79 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19711522600 |  | 100424740 |  | 7360184T |  |  |  | 566 | EX | ABN SERVICE | 2621P | KY FIELD | KY FIELD | 159 | DAV | 2019-06-05 | U125208 | U131167 | 2019-06-04 | 2019-06-04 |  |  | CHAMMON | 2019-06-04 |  |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 1.3167 | 1 | 76.5 | 72.29 | 0 | 4.21 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 05603743300 |  | 100277100 |  | 600000000 | 1855043 |  |  | 566 | EX | SOII - ABANDON SERVICE LINE | 2621P | HOLMES | 915 HOLMES ST | 073 | FRA | 2019-07-05 | JCOOPER | RPOLLY | 2005-03-07 | 2014-12-23 |  |  | JCOOPER | 2019-06-05 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2621 | 19680070300 |  | 100320211 |  | 6716208G | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 214 SHADY LN | 067 | LEX | 2019-06-06 | HROGERS | U131066 | 2019-02-07 | 2019-11-27 |  |  | MARK ROGERS | 2019-06-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1878.42 | 0 | 0 | 0 | 1878.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680070500 |  | 100320239 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 223 SHADY LN | 067 | LEX | 2019-06-06 | HROGERS | U131066 | 2019-02-07 | 2019-11-27 |  |  | MARK ROGERS | 2019-06-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1978.82 | 0 | 0 | 0 | 1978.82 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687818400 |  | 100280124 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | BONNYCASTLE | 252 BONNYCASTLE AV | 073 | FRA | 2019-06-11 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-06-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687819800 |  | 100280173 |  | 6688228I | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | BONNYCASTLE | 274 BONNYCASTLE AV | 073 | FRA | 2019-06-11 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-06-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691677900 |  | 100328575 |  | 6720208F | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1935 FONTAINE RD | 067 | LEX | 2019-06-05 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-06-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1755.53 | 0 | 0 | 0 | 1755.53 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19697781400 |  | 100345778 |  | 6696212D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SELMA | 204 SELMA ST | 239 | VER | 2019-06-05 | CDESPAI | U125208 | 2019-04-16 | 2019-06-04 | 2021-04-30 |  | CDESPAI | 2019-06-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.3833 | 1 | 2210.3 | 202.35 | 302.69 | 373.76 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19710778000 |  | 100312391 |  | 6716208J |  |  |  | 566 | EX | ABANDON / RI 04-05-19 | 2621P | EASTWAY | 2304 EASTWAY DR | 067 | LEX | 2019-06-05 | MCRAIG | U125208 | 2019-05-31 | 2019-06-21 | 2019-06-23 |  | MCRAIG | 2019-06-05 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 20.9 | 3 | 1131.63 | 966.92 | 108.61 | 56.1 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19711499600 |  | 100311777 |  | 6716208I |  |  |  | 565 | EX | REPLACE SERVICE LINE - D000717 | 2621P | SOUTHVIEW | 2909 SOUTHVIEW DR | 067 | LEX | 2019-06-07 | U125208 | U125208 | 2019-06-04 | 2019-06-04 | 2019-06-04 |  | JENSMIN | 2019-06-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.1167 | 1 | 3990.25 | 473.79 | 128.81 | 576.69 | 2810.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19711501300 |  | 100311915 |  | 6716208I |  |  |  | 565 | EX | REPLACE SERVICE LINE - D000718 | 2621P | WESTERFIELD | 495 WESTERFIELD WY | 067 | LEX | 2019-06-07 | U125208 | U125208 | 2019-06-04 | 2019-06-04 | 2019-06-04 |  | LSTANFI | 2019-06-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.2333 | 1 | 3558.31 | 334.18 | 242.12 | 19.4 | 2962.61 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19711506300 |  | 100311812 |  | 6716208M |  |  |  | 565 | EX | REPLACE SERVICE LINE - D193641 | 2621P | KIMBERLY | 407 KIMBERLY PL | 067 | LEX | 2019-06-07 | U125208 | U125208 | 2019-06-04 | 2019-06-04 | 2019-06-04 |  | LSTANFI | 2019-06-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.1833 | 1 | 2248.65 | 138.67 | 284.06 | 8.04 | 1817.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19711512800 |  | 100311912 |  | 6716208I |  |  |  | 565 | EX | REPLACE SERVICE LINE - D221747 | 2621P | WESTERFIELD | 483 WESTERFIELD WY | 067 | LEX | 2019-06-07 | U125208 | U125208 | 2019-06-04 | 2019-06-04 | 2019-06-04 |  | LSTANFI | 2019-06-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.5 | 1 | 3649.85 | 287.54 | 218.27 | 16.67 | 3127.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19711589400 |  | 100311880 |  | 6716208I | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | BLACK ARROW | 2886 BLACK ARROW CT | 067 | LEX | 2019-06-05 | JENSMIN | AOC SYST | 2019-06-04 | 2019-06-05 | 2020-12-31 |  | JENSMIN | 2019-06-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.28333 | 1 | 2038.06 | 16.35 | 183.93 | 19.9 | 1817.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572285000 |  | 100279754 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL/17026731300/ | 2600B | SUNSET | 107 SUNSET DR | 073 | FRA | 2019-06-11 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-06-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2072.8 | 0 | 0 | 0 | 2072.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18593275300 |  | 500660537 |  | 6712208M | 9934603 |  |  | 566 | EX | ABN / RI 03-13-18 500660537 | 2621P | HARRODSBURG | 3955 HARRODSBURG RD RESTAUR | 067 | LEX | 2019-06-06 | JENSMIN | U125208 | 2018-03-08 | 2019-05-28 |  |  | JENSMIN | 2019-06-06 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.15 | 1 | 19.43 | 8.76 | 0 | 10.67 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18622493500 |  | 100272346 |  | 6684224B |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | TANGLEWOOD | 118 TANGLEWOOD DR | 073 | FRA | 2019-06-06 | CDESPAI | U125208 | 2018-06-22 | 2018-12-21 | 2020-06-30 |  | CDESPAI | 2019-06-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.7667 | 1 | 3013.59 | 285.54 | 309.55 | 16.56 | 2401.94 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19026869500 |  | 501206138 |  | 6716232I | 1962812 | U461383 |  | 555 | EX | INSTALL 265' OF 2"PMMP MAIN | 2600B | IKEBANA | 208 IKEBANA DR LT27 | 209 | GEO | 2019-06-12 | U462463 | U122858 | 2019-04-04 | 2019-05-13 | 2019-07-03 | 2019-06-03 | KKOUNS | 2019-06-06 | 2019-05-28 | 2019-05-28 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP8695 |  |  | 100 | 055532190268695 | 55.45 | 2289 | 17429.7 | 3022.24 | 912.37 | 911.39 | 10262.5 | 0 | 37.21 | 2283.99 | 327
KY | KY - WEST | 2621 | 19026879600 |  |  |  | 6716212H | 1743881 | U461383 |  | 559 | EX | DOCUMENT MP MAIN INSTALL | 2600B | HAMPTON | HAMPTON CT | 067 | LEX | 2019-06-18 | U123258 | U461383 | 2019-06-06 | 2019-10-01 | 2019-10-01 | 2018-10-18 | KKOUNS | 2019-06-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP8796 | AMRCB |  | 100 | 055932190268796 |  | 905 | 2180.35 | 26.98 | 1857.91 | 8.14 | 0 | 0 | 0 | 287.32 | 905
KY | KY - WEST | 2621 | 19678783000 |  | 100299223 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 288 LARCH LN | 067 | LEX | 2019-06-07 | U123111 | U131066 | 2019-02-01 | 2019-11-27 |  |  | LYN STAFFORD | 2019-06-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1053.79 | 0 | 0 | 0 | 1053.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678783200 |  | 100299224 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 292 LARCH LN | 067 | LEX | 2019-06-07 | U123111 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1053.79 | 0 | 0 | 0 | 1053.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678783400 |  | 100299225 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 296 LARCH LN | 067 | LEX | 2019-06-07 | U123111 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1053.79 | 0 | 0 | 0 | 1053.79 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19679380000 |  | 100463064 |  | 6696212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D192934 | 2621P | BERLIN | 537 BERLIN DR | 239 | VER | 2019-06-07 | U125208 | U125208 | 2019-02-05 | 2019-08-02 | 2021-02-28 |  | CDESPAI | 2019-06-06 | 2019-06-05 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.1667 | 2 | 1756.77 | 249.01 | 160.73 | 15.53 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680071600 |  | 100320219 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 236 SHADY LN | 067 | LEX | 2019-06-07 | HROGERS | U131066 | 2019-02-07 | 2019-11-27 |  |  | MARK ROGERS | 2019-06-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3090.38 | 0 | 0 | 0 | 3090.38 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19685900700 |  | 100241766 |  | 7356256P | 1859020 |  |  | 565 | EX | RPLC SL/18026844201/ | 2600B | 49TH | 332 49TH ST | 019 | ASH | 2019-06-06 | U125573 | U131066 | 2019-03-04 | 2019-11-27 |  |  | BCOFER | 2019-06-06 |  | 2019-06-06 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1542.82 | 0 | 0 | 0 | 1542.82 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19685901300 |  | 100241815 |  | 7356256P | 1859020 |  |  | 565 | EX | RPLC SL/18026844201/ | 2600B | WILLIAMS | 4820 WILLIAMS AV | 019 | ASH | 2019-06-07 | U125573 | U131066 | 2019-03-04 | 2019-11-27 |  |  | BCOFER | 2019-06-06 |  | 2019-06-06 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1542.82 | 0 | 0 | 0 | 1542.82 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689097600 |  | 100239597 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | RIDGE | 102 RIDGE ST | 089 | RUS | 2019-06-06 | U125566 | U131066 | 2019-03-18 | 2019-11-27 |  |  | DAVID SKAGGS | 2019-06-06 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2631.92 | 0 | 0 | 0 | 2631.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691678200 |  | 100328573 |  | 6720208F | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1941 FONTAINE RD | 067 | LEX | 2019-06-07 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-06-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1969.04 | 0 | 0 | 0 | 1969.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19694353200 |  | 100291867 |  | 6720216G |  |  |  | 565 | EX | REPLACE SERVICE LINE - D000061 | 2621P | EDEN | 686 EDEN RD | 067 | LEX | 2019-06-07 | U125208 | U125208 | 2019-04-03 | 2019-06-06 | 2021-04-30 |  | LSTANFI | 2019-06-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.7 | 1 | 1492 | 44.09 | 113.85 | 2.56 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19695830800 |  | 100308852 |  | 6716208A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPL SL/MOVEOUT | 2621D | LYNN | 824 LYNN DR | 067 | LEX | 2019-06-06 | JBENNET | AOC SYST | 2019-04-09 | 2019-05-06 | 2019-06-05 |  | JBENNET | 2019-06-06 | 2019-06-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 31.7167 | 6 | 1807.86 | 1492.63 | 187.35 | 127.88 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19702863400 |  | 100302390 |  | 6712212G |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094780 | 2621P | KELSEY | 1150 KELSEY DR | 067 | LEX | 2019-06-07 | U125208 | U125208 | 2019-05-02 | 2019-06-06 | 2021-04-30 |  | LSTANFI | 2019-06-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.8 | 1 | 1710.36 | 242.79 | 121.98 | 14.09 | 1331.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19708634700 |  | 100408367 |  | 7328284F |  |  |  | 566 | EX | ABANDON / RI 05-23-19 | 2621P | MAIN | 849 MAIN ST | 089 | S S | 2019-06-06 | MCOLLET | U125208 | 2019-05-23 | 2019-05-29 |  |  | MCOLLET | 2019-06-06 | 2019-06-06 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.2167 | 2 | 530.81 | 310.83 | 21.83 | 198.15 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19708693900 |  | 100439554 |  | 6720208K | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER / | 2621D | LAKESHORE | 508 LAKESHORE DR | 067 | LEX | 2019-06-06 | MCRAIG | AOC SYST | 2019-05-23 | 2019-06-21 | 2019-07-22 |  | MCRAIG | 2019-06-06 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25 | 3 | 1554.96 | 1162.41 | 325.08 | 67.47 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19711113300 |  | 100353451 |  | 7256280K |  |  |  | 566 | EX | ABANDON / RA 09-28-19 CONVRT | 2621P | 2ND | 322 W 2ND ST | 161 | MAY | 2019-06-06 | SDADAMS | U125208 | 2019-06-03 | 2049-12-31 |  |  | SDADAMS | 2019-06-06 | 2019-06-06 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 7.6167 | 3 | 466.15 | 422.8 | 18.83 | 24.52 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19712174900 |  | 100293493 |  | 6720216J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | KILDARE | 505 KILDARE CT | 067 | LEX | 2019-06-06 | LSTANFI | U129939 | 2019-06-06 | 2019-06-06 | 2021-04-30 |  | LSTANFI | 2019-06-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.6167 | 1 | 1659.13 | 102.87 | 218.79 | 5.97 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19712180900 |  | 100279753 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL/18026776900 | 2600B | VERSAILLES | 331 VERSAILLES RD | 073 | FRA | 2019-06-11 | U461375 | U131066 | 2019-06-06 | 2019-12-31 |  |  | LARRY BROWN | 2019-06-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2729.74 | 0 | 0 | 0 | 2729.74 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671926000 |  | 100403957 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 33 W 2ND ST | 161 | MAY | 2019-06-07 | U126286 | U131066 | 2019-01-22 | 2019-11-27 |  |  | TYLER ALLISON | 2019-06-07 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1465.25 | 0 | 0 | 0 | 1465.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19708280400 |  | 100310007 |  | 6716208E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER / | 2621D | SHERIDAN | 648 SHERIDAN DR | 067 | LEX | 2019-06-10 | U125208 | AOC SYST | 2019-05-22 | 2019-06-19 | 2019-07-19 |  | ASNICHO | 2019-06-07 | 2019-06-06 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25.5167 | 4 | 1447.19 | 1196.75 | 180.97 | 69.47 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19712281000 |  | 100311628 |  | 6712204D |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MONTICELLO | 543 MONTICELLO BV | 067 | LEX | 2019-06-07 | LSTANFI | U125208 | 2019-06-06 | 2019-06-06 | 2019-06-06 |  | LSTANFI | 2019-06-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.2 | 2 | 3273.03 | 541.88 | 275.85 | 31.46 | 2423.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19712282500 |  | 100292835 |  | 6720216K |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | RADCLIFFE | 573 RADCLIFFE RD | 067 | LEX | 2019-06-07 | JENSMIN | U125208 | 2019-06-06 | 2019-06-06 | 2019-06-06 |  | JENSMIN | 2019-06-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.8167 | 1 | 3166.74 | 223.19 | 248.11 | 271.6 | 2423.84 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19712558000 |  | 100244830 |  | 7356220O |  |  |  | 566 | EX | ABANDON SERV LINE | 2621P | JEFFERSON | 607 N JEFFERSON ST | 127 | LOU | 2019-06-07 | MCOLLET | U129939 | 2019-06-07 | 2019-06-07 |  |  | MCOLLET | 2019-06-07 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.1 | 2 | 115.9 | 71.15 | 0 | 44.75 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19026867701 |  | 501259026 |  | 6680228L | 1420805 | U461383 |  | 555 | EX | INSTALL 2100' OF 2"PMMP MAIN | 2600B | OAK RIDGE | 100 OAK RIDGE DR LT | 073 | FRA | 2019-06-13 | U125423 | GSULLI1 | 2019-05-31 | 2019-05-01 | 2019-07-31 | 2019-05-29 | WGRAVES | 2019-06-10 | 2019-05-02 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP8677 |  |  | 100 | 055532190268677 | 167.5 | 50531 | 159412.42 | 8753.6 | 4387.52 | 3057.95 | 121984.48 | 0 | 301.77 | 20927.1 | 2197
KY | KY - WEST | 2621 | 19678775000 |  | 100299169 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 275 BURKE RD | 067 | LEX | 2019-06-10 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1705.31 | 0 | 0 | 0 | 1705.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678781200 |  | 100299258 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 251 LARCH LN | 067 | LEX | 2019-06-10 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.1 | 1 | 1961 | 345.35 | 0 | 106.43 | 1509.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678798000 |  | 100299170 |  | 6716216N | 1855322 |  |  | 565 | EX | REPLACE SL W/18026792400 | 2600B | BURKE | 271 BURKE RD | 067 | LEX | 2019-06-10 | U126603 | U131066 | 2019-02-01 | 2019-12-31 |  |  | SHAWN DENNIS | 2019-06-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1509.22 | 0 | 0 | 0 | 1509.22 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19685901500 |  | 100241874 |  | 7356256P | 1859020 |  |  | 565 | EX | RPLC SL/18026844201/ | 2600B | WILLIAMS | 4905 WILLIAMS AV | 019 | ASH | 2019-06-11 | U125573 | U131066 | 2019-03-04 | 2019-11-27 |  |  | BCOFER | 2019-06-10 |  | 2019-06-10 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1387.7 | 0 | 0 | 0 | 1387.7 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687819400 |  | 100280189 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | BONNYCASTLE | 269 BONNYCASTLE AV | 073 | FRA | 2019-06-11 | U126309 | U131066 | 2019-03-13 | 2019-11-27 |  |  | JAMIE LYNN | 2019-06-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.9167 | 1 | 1542.89 | 103.97 | 0 | 23.06 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687819600 |  | 100280188 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | BONNYCASTLE | 271 BONNYCASTLE AV | 073 | FRA | 2019-06-11 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-06-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19701107700 |  | 100468500 |  | 6708204H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094779 | 2621P | CREEKVIEW | 2413 CREEKVIEW CT | 067 | LEX | 2019-06-11 | U125208 | U125208 | 2019-04-29 | 2019-10-25 | 2021-04-30 |  | JOSHUA COX | 2019-06-10 | 2019-06-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.8667 | 2 | 2596.1 | 220.14 | 171.84 | 170.01 | 2034.11 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19707335200 |  | 100262134 |  | 7352256D |  |  |  | 566 | EX | DEMO / ABANDON / RI 05-28-19 | 2621P | DIXON | 2008 DIXON ST | 019 | ASH | 2019-06-12 | U125208 | U132002 | 2019-05-20 | 2019-06-28 | 2019-07-22 |  | AMCCORM | 2019-06-10 | 2019-06-06 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 12.6333 | 3 | 1357.17 | 777.08 | 0.93 | 579.16 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19711012200 |  | 100268362 |  | 7356260M |  |  |  | 566 | EX | DEMO / ABANDON / RA 06-05-19 | 2621P | 12TH | 332 12TH ST | 019 | ASH | 2019-06-11 | U125208 | U132002 | 2019-06-03 | 2019-07-12 | 2019-08-02 |  | MCOLLET | 2019-06-10 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.56667 | 2 | 74.9 | 35.1 | 0 | 39.8 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19711021500 |  | 100241618 |  | 7356260M |  |  |  | 566 | EX | DEMO / ABANDON / RA 06-05-19 | 2621P | CARTER | 1201 CARTER AV | 019 | ASH | 2019-06-11 | U125208 | U132002 | 2019-06-03 | 2019-07-12 | 2019-08-02 |  | AMCCORM | 2019-06-10 | 2019-06-10 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 12.2667 | 2 | 1521.81 | 756.3 | 0 | 765.51 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19712180800 |  | 500182934 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL/18026776900 | 2600B | VERSAILLES | 325 VERSAILLES RD | 073 | FRA | 2019-06-11 | U126309 | U131066 | 2019-06-06 | 2019-12-31 |  |  | JAMIE LYNN | 2019-06-10 | 2019-06-10 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.4 | 2 | 2955.89 | 185.12 | 0 | 41.03 | 2729.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19712750100 |  | 100311685 |  | 6712204D |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | POST | 3362 POST RD | 067 | LEX | 2019-06-10 | JBENNET | U130193 | 2019-06-10 | 2019-06-10 | 2019-06-10 |  | JBENNET | 2019-06-10 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.2167 | 2 | 2864.53 | 1091.46 | 283.18 | 349.89 | 1140 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19712765200 |  | 100311576 |  | 6712204D |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | MONTICELLO | 638 MONTICELLO BV | 067 | LEX | 2019-06-10 | JENSMIN | U130193 | 2019-06-10 | 2019-06-10 | 2019-06-10 |  | JENSMIN | 2019-06-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.6333 | 2 | 3893.66 | 840.5 | 385.54 | 648.97 | 2018.65 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19712776900 |  | 100273791 |  | 6680228K |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | SINGLETON | 100 SINGLETON LN | 073 | FRA | 2019-06-10 | CDESPAI | U130193 | 2019-06-10 | 2019-06-10 | 2019-06-10 |  | CDESPAI | 2019-06-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.1333 | 1 | 4166.16 | 354.99 | 372.53 | 582.23 | 2856.41 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19713023900 |  | 100262135 |  | 7352256D |  |  |  | 566 | EX | ABANDON W/100262134 - 06/10/19 | 2621P | DIXON | 2008< DIXON ST | 019 | ASH | 2019-06-12 | U125208 | U125208 | 2019-06-11 | 2019-06-10 |  |  | AMCCORM | 2019-06-10 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 0
KY | KY - WEST | 2623 | 17026741900 |  |  |  | 6684228K | 1749478 | U127466 |  | 560 | EX | ABANDON 96' - 6" BSLP | 2621P | 4TH | 4TH ST | 073 | FRA | 2019-06-11 | U123258 | U127466 | 2017-12-11 | 2018-12-28 | 2018-12-31 | 2017-12-18 | COREY DESPAIN | 2019-06-11 | 2017-12-15 | 2017-12-15 | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00560 | 3200560 |  |  | WP7419 | AMRCB |  | 100 | 056032170267419 | 44.7667 | 0 | 2711.99 | 1953.41 | 635.2 | 123.38 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678773400 |  | 100299151 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 232 BURKE RD | 067 | LEX | 2019-06-11 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2 | 1 | 1250.9 | 114.39 | 0 | 35.26 | 1101.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678773700 |  | 100299177 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 243 BURKE RD | 067 | LEX | 2019-06-11 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.083333 | 1 | 1711.24 | 4.54 | 0 | 1.39 | 1705.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678774100 |  | 100299155 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 252 BURKE RD | 067 | LEX | 2019-06-11 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.75 | 1 | 2557.4 | 325 | 0 | 100.16 | 2132.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678775400 |  | 100299167 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 283 BURKE RD | 067 | LEX | 2019-06-11 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2285.6 | 0 | 0 | 0 | 2285.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678775700 |  | 100299165 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 291 BURKE RD | 067 | LEX | 2019-06-11 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.05 | 1 | 1612.12 | 2.82 | 99.21 | 0.87 | 1509.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680071000 |  | 100320216 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 228 SHADY LN | 067 | LEX | 2019-06-11 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-06-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.5 | 2 | 3993.95 | 603.65 | 0 | 183.75 | 3206.55 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19685901100 |  | 100241819 |  | 7356256P | 1859020 |  |  | 565 | EX | RPLC SL/18026844201/ | 2600B | LOTUS | 416 LOTUS ST | 019 | ASH | 2019-06-12 | U125573 | U131066 | 2019-03-04 | 2019-11-27 |  |  | BCOFER | 2019-06-11 |  | 2019-06-11 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1947.17 | 0 | 0 | 0 | 1947.17 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19685901200 |  | 100241816 |  | 7356256P | 1859020 |  |  | 565 | EX | RPLC SL/18026844201/ | 2600B | LOTUS | 425 LOTUS ST | 019 | ASH | 2019-06-12 | U125573 | U131066 | 2019-03-04 | 2019-11-27 |  |  | BCOFER | 2019-06-11 |  | 2019-06-11 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2879.84 | 0 | 0 | 0 | 2879.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19686694100 |  | 100273555 |  | 6680224F |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CARLA | 153 CARLA CT | 073 | FRA | 2019-06-11 | CDESPAI | U131392 | 2019-03-07 | 2019-06-10 | 2021-03-31 |  | CDESPAI | 2019-06-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26230022 | 0.81667 | 1 | 1886.82 | 48.48 | 244.22 | 2.81 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687819200 |  | 100280126 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | BONNYCASTLE | 266 BONNYCASTLE AV | 073 | FRA | 2019-06-11 | U126309 | U131066 | 2019-03-13 | 2019-11-27 |  |  | JAMIE LYNN | 2019-06-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8.6333 | 1 | 1819.85 | 469.79 | 0 | 104.2 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687819300 |  | 100280190 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | BONNYCASTLE | 267 BONNYCASTLE AV | 073 | FRA | 2019-06-11 | U126309 | U131066 | 2019-03-13 | 2019-11-27 |  |  | JAMIE LYNN | 2019-06-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.36667 | 1 | 1439.82 | 19.6 | 0 | 4.36 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687819700 |  | 100280187 |  | 6688228I | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | BONNYCASTLE | 273 BONNYCASTLE AV | 073 | FRA | 2019-06-11 | U126309 | U131066 | 2019-03-13 | 2019-11-27 |  |  | JAMIE LYNN | 2019-06-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.51667 | 1 | 1449.82 | 27.79 | 0 | 6.17 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687820500 |  | 100280180 |  | 6688228I | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | BONNYCASTLE | 284 BONNYCASTLE AV | 073 | FRA | 2019-06-11 | U126309 | U131066 | 2019-03-13 | 2019-06-11 |  |  | JAMIE LYNN | 2019-06-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.1 | 1 | 1254.53 | 7.09 | 0 | 1.58 | 1245.86 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689097800 |  | 100239595 |  | 7328288O | 1859009 |  |  | 566 | EX | ABND SL/18026843700/ | 2600B | RIDGE | RIDGE ST | 089 | RUS | 2019-06-17 | U125208 | U131066 | 2019-03-18 | 2019-11-27 |  |  | DAVID SKAGGS | 2019-06-11 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.11667 | 1 | 1117.07 | 6.07 | 0 | 1.92 | 1109.08 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689200400 |  | 100239596 |  | 7348264G | 1859009 |  |  | 565 | EX | REPLACE SL W/18026843700 | 2600B | RIDGE | 100 RIDGE ST | 089 | RUS | 2019-06-11 | U125566 | U131066 | 2019-03-18 | 2019-12-31 |  |  | DAVID SKAGGS | 2019-06-11 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.11667 | 1 | 1704.96 | 7.2 | 0 | 2.26 | 1695.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19711469600 |  | 100273691 |  | 6684228M |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | EXMOOR | 200 EXMOOR DR | 073 | FRA | 2019-06-11 | CDESPAI | U125208 | 2019-06-04 | 2019-06-07 | 2019-06-25 |  | CDESPAI | 2019-06-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.3667 | 1 | 3143.07 | 380.75 | 316.38 | 22.1 | 2423.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19711843000 |  | 501055878 |  | 6684224E | 0992764 |  |  | 565 | EX | REPLACE SVC LINE | 2621P | US 127 | 1300 US 127 SO | 073 | FRA | 2019-06-12 | U125208 | U130193 | 2019-06-05 | 2019-06-05 |  |  | BJLONE | 2019-06-11 | 2019-06-05 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 60.8 | 9 | 4096.96 | 3345.15 | 17.25 | 734.56 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19711871400 |  | 100305156 |  | 6712212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D193643 | 2621P | MERIDIAN | 1094 MERIDIAN CT | 067 | LEX | 2019-06-12 | U125208 | U125208 | 2019-06-05 | 2019-06-05 | 2019-06-05 |  | JENSMIN | 2019-06-11 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.25 | 2 | 1608.36 | 130.87 | 290.05 | 127.01 | 1060.43 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19712288400 |  | 100447919 |  | 7352156L |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | JUSTELL BRIDGE | 464 JUSTELL BRIDGE RD | 071 | JUS | 2019-06-11 | BBMULLI | U125208 | 2019-06-06 | 2019-06-07 | 2019-06-27 |  | BBMULLI | 2019-06-11 |  |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 16 | 2 | 1195.06 | 915.3 | 0 | 279.76 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19712818500 |  | 100311402 |  | 6712204D |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | SAYBROOK | 3447 SAYBROOK RD | 067 | LEX | 2019-06-11 | JWCOX | U130193 | 2019-06-10 | 2019-06-10 | 2019-06-10 |  | JWCOX | 2019-06-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.9333 | 2 | 2086.56 | 501.75 | 191.73 | 29.67 | 1363.41 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19712823600 |  | 100311339 |  | 6712204C |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HOLWYN | 3421 HOLWYN RD | 067 | LEX | 2019-06-11 | JWCOX | U130193 | 2019-06-10 | 2019-06-10 | 2019-06-10 |  | JWCOX | 2019-06-11 | 2019-06-11 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.2833 | 3 | 1684.52 | 264.97 | 191.73 | 15.9 | 1211.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19712830600 |  | 100301417 |  | 6712212H |  |  |  | 565 | EX | REPLACE SERVICE - D221759 | 2621P | MANDALAY | 217 MANDALAY RD | 067 | LEX | 2019-06-12 | U125208 | U131168 | 2019-06-10 | 2019-06-10 | 2019-06-10 |  | JENSMIN | 2019-06-11 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.1333 | 2 | 1512.64 | 65.42 | 243.26 | 63.22 | 1140.74 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19712951300 |  | 100348432 |  | 6748208L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D193305 | 2621P | SKYLINE | 141 SKYLINE DR | 049 | WIN | 2019-06-12 | U125208 | U130193 | 2019-06-11 | 2019-06-03 | 2020-07-31 |  | DBANKS | 2019-06-11 | 2019-06-11 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 32.9167 | 6 | 1902.05 | 1660.25 | 0 | 241.8 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19713025100 |  | 100302171 |  | 6712212L |  |  |  | 566 | EX | RETIRE SERVICE LINE - D000067 | 2621P | OXFORD | 1931 OXFORD CR | 067 | LEX | 2019-06-12 | U125208 | U130193 | 2019-06-11 | 2019-06-10 | 2019-06-10 |  | JENSMIN | 2019-06-11 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 3.7 | 1 | 1755.93 | 215.59 | 118.3 | 210.12 | 1211.92 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19713049800 |  | 100273675 |  | 6684228M |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | EXMOOR | 205 EXMOOR DR | 073 | FRA | 2019-06-11 | CDESPAI | U130193 | 2019-06-11 | 2019-06-11 |  |  | CDESPAI | 2019-06-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.3167 | 1 | 3008.23 | 438.8 | 244.22 | 25.47 | 2299.74 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19713068700 |  | 100247550 |  | 7352256L |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | ROOSEVELT | 2628 ROOSEVELT AV | 019 | ASH | 2019-06-11 | AMCCORM | U130193 | 2019-06-11 | 2019-06-11 |  |  | AMCCORM | 2019-06-11 | 2019-06-11 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 8.3667 | 2 | 1289.43 | 517.99 | 234.19 | 537.25 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18641839200 |  | 100269934 |  | 6732252P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094587 | 2621P | 4TH | 222 4TH ST | 097 | CYN | 2019-06-13 | U125208 | U125208 | 2018-09-10 | 2019-03-06 | 2020-09-30 |  | DBANKS | 2019-06-12 | 2019-06-12 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 28.7 | 3 | 1593.58 | 1500.63 | 0 | 92.95 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678779800 |  | 100299266 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 215 LARCH LN | 067 | LEX | 2019-06-12 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.9333 | 1 | 1830.27 | 165.88 | 0 | 51.12 | 1613.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678796000 |  | 100299152 |  | 6716216N | 1855322 |  |  | 565 | EX | REPLACE SL W/18026792400 | 2600B | BURKE | 240 BURKE RD | 067 | LEX | 2019-06-12 | U126603 | U131066 | 2019-02-01 | 2019-12-31 |  |  | SHAWN DENNIS | 2019-06-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.8 | 1 | 1885.7 | 158.54 | 0 | 48.85 | 1678.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680089300 |  | 100320212 |  | 6716208G | 1748686 |  |  | 565 | EX | REPLACE SL W/17026736100 | 2600B | SHADY | 216 SHADY LN | 067 | LEX | 2019-06-12 | U126532 | U131066 | 2019-02-07 | 2019-12-31 |  |  | LSHARON | 2019-06-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.6167 | 2 | 3774.35 | 607.09 | 0 | 185.85 | 2981.41 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19685901800 |  | 100241872 |  | 7356256P | 1859020 |  |  | 565 | EX | RPLC SL/18026844201/ | 2600B | WILLIAMS | 4917 WILLIAMS AV | 019 | ASH | 2019-06-12 | U125573 | U131066 | 2019-03-04 | 2019-11-27 |  |  | BCOFER | 2019-06-12 |  | 2019-06-12 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1869.61 | 0 | 0 | 0 | 1869.61 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19685901900 |  | 100241820 |  | 7356256P | 1859020 |  |  | 565 | EX | RPLC SL/18026844201/ | 2600B | WILLIAMS | 5000 WILLIAMS AV | 019 | ASH | 2019-06-12 | U125573 | U131066 | 2019-03-04 | 2019-11-27 |  |  | BCOFER | 2019-06-12 |  | 2019-06-12 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2349.97 | 0 | 0 | 0 | 2349.97 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687819000 |  | 100280192 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | BONNYCASTLE | 263 BONNYCASTLE AV | 073 | FRA | 2019-06-27 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-06-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687819500 |  | 100280172 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | BONNYCASTLE | 270 BONNYCASTLE AV | 073 | FRA | 2019-06-27 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-06-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1565.89 | 0 | 0 | 0 | 1565.89 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687819900 |  | 100280186 |  | 6688228I | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | BONNYCASTLE | 275 BONNYCASTLE AV | 073 | FRA | 2019-06-27 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-06-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687820600 |  | 100280181 |  | 6688228I | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | BONNYCASTLE | 287 BONNYCASTLE AV | 073 | FRA | 2019-06-27 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-06-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19698105100 |  | 100272369 |  | 6684228N |  |  |  | 565 | EX | REPLACE SERV W/LCB | 2621P | CAPITAL HEIGHT | 200 CAPITAL HEIGHT DR | 073 | FRA | 2019-06-13 | U125208 | U125208 | 2019-04-17 | 2049-12-31 |  |  | CDESPAI | 2019-06-12 | 2019-04-26 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 10.7833 | 4 | 5155.79 | 630.62 | 446.76 | 536.82 | 3541.59 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19707423400 |  | 100289965 |  | 6720212C | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER / | 2621D | NORTHWOOD | 361 NORTHWOOD DR | 067 | LEX | 2019-06-18 | U125208 | AOC SYST | 2019-05-20 | 2019-06-17 | 2019-07-17 |  | JENSMIN | 2019-06-12 | 2019-05-22 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.8333 | 4 | 3117.15 | 675.29 | 0 | 470.02 | 1971.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19713279600 |  | 100272139 |  | 6684228O |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | MURRAY | 509 MURRAY ST | 073 | FRA | 2019-06-13 | U125208 | U130193 | 2019-06-12 | 2019-06-12 |  |  | CDESPAI | 2019-06-12 | 2019-06-12 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.15 | 1 | 2836.02 | 247.81 | 309.55 | 81.39 | 2197.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19713364900 |  | 100311330 |  | 6712204C |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | CROMWELL | 637 CROMWELL WY | 067 | LEX | 2019-06-12 | JENSMIN | U130193 | 2019-06-12 | 2019-06-12 | 2019-06-12 |  | JENSMIN | 2019-06-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.2667 | 2 | 3132.57 | 589.37 | 261.13 | 455.06 | 1827.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19713534400 |  | 100460696 |  | 6720204O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | GLEN OAK | 3612 GLEN OAK WY | 067 | LEX | 2019-06-12 | JBENNET | U130193 | 2019-06-12 | 2019-06-08 | 2019-06-26 |  | JBENNET | 2019-06-12 | 2019-06-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.6667 | 5 | 2065.93 | 1213.81 | 211.65 | 70.47 | 570 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678769800 |  | 100299275 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 228 BOILING SPRING DR | 067 | LEX | 2019-06-13 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-06-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2 | 1 | 2018.52 | 110.11 | 0 | 6.37 | 1902.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678774300 |  | 100299173 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 259 BURKE RD | 067 | LEX | 2019-06-13 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-06-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.2 | 1 | 1695.59 | 176.15 | 0 | 10.22 | 1509.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678774700 |  | 100299171 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 267 BURKE RD | 067 | LEX | 2019-06-13 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-06-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.8 | 1 | 1672.91 | 154.71 | 0 | 8.98 | 1509.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678794800 |  | 100299150 |  | 6716216N | 1855322 |  |  | 565 | EX | REPLACE SL W/18026792400 | 2600B | BURKE | 228 BURKE RD | 067 | LEX | 2019-06-13 | U461467 | U131066 | 2019-02-01 | 2019-12-31 |  |  | D REFFETT | 2019-06-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.2833 | 1 | 2024.34 | 70.45 | 0 | 4.1 | 1949.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680070200 |  | 100320210 |  | 6716208G | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 212 SHADY LN | 067 | LEX | 2019-06-13 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-06-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.2833 | 2 | 3740.38 | 477.07 | 0 | 145.25 | 3118.06 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19685902000 |  | 100241870 |  | 7356256P | 1859020 |  |  | 565 | EX | RPLC SL/18026844201/ | 2600B | WILLIAMS | 5001 WILLIAMS AV | 019 | ASH | 2019-06-13 | U125573 | U131066 | 2019-03-04 | 2019-11-27 |  |  | BCOFER | 2019-06-13 |  | 2019-06-13 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1969.33 | 0 | 0 | 0 | 1969.33 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19685902100 |  | 100241821 |  | 7356252D | 1859020 |  |  | 565 | EX | RPLC SL/18026844201/ | 2600B | WILLIAMS | 5004 WILLIAMS AV | 019 | ASH | 2019-06-13 | U125573 | U131066 | 2019-03-04 | 2019-11-27 |  |  | BCOFER | 2019-06-13 |  | 2019-06-13 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1969.33 | 0 | 0 | 0 | 1969.33 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687818700 |  | 100280195 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | BONNYCASTLE | 257 BONNYCASTLE DR | 073 | FRA | 2019-06-27 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-06-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2640.67 | 0 | 0 | 0 | 2640.67 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687819100 |  | 100280191 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | BONNYCASTLE | 265 BONNYCASTLE AV | 073 | FRA | 2019-06-27 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-06-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687820200 |  | 100280183 |  | 6688228I | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | BONNYCASTLE | 281 BONNYCASTLE AV | 073 | FRA | 2019-06-27 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-06-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687820300 |  | 100280179 |  | 6688228I | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | BONNYCASTLE | 282 BONNYCASTLE AV | 073 | FRA | 2019-06-27 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-06-13 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689091700 |  | 100255713 |  | 7348264H | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | MEADE | 1606 MEADE ST | 089 | FLA | 2019-06-13 | U125566 | U131066 | 2019-03-18 | 2019-11-27 |  |  | DAVID SKAGGS | 2019-06-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.23333 | 1 | 966.67 | 13.28 | 0 | 4.17 | 949.22 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689091900 |  | 100255718 |  | 7348264G | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | MEADE | 1616 MEADE ST | 089 | FLA | 2019-06-13 | U125566 | U131066 | 2019-03-18 | 2019-11-27 |  |  | DAVID SKAGGS | 2019-06-13 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.05 | 1 | 1433.22 | 2.77 | 0 | 0.87 | 1429.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19702864400 |  | 100302522 |  | 6712212G |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094784 | 2621P | CHERBOURG | 1236 CHERBOURG RD | 067 | LEX | 2019-06-14 | U125208 | U125208 | 2019-05-02 | 2019-10-29 | 2021-04-30 |  | JENSMIN | 2019-06-13 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.5167 | 2 | 2764.43 | 600.57 | 207.42 | 365.13 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19713849600 |  | 100319395 |  | 6716208O |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | LOWRY | 209 E LOWRY LN | 067 | LEX | 2019-06-14 | U125208 | U130193 | 2019-06-13 | 2019-06-13 |  |  | JENSMIN | 2019-06-13 | 2019-06-13 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.7167 | 2 | 2889.83 | 387.01 | 223.26 | 260.91 | 2018.65 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18026781300 |  | 501243658 |  | 6744204H | 1853673 | U128885 |  | 555 | EX | INSTALL 750' OF 4"PMLP MAIN | 2600B | FAIRHOLME | 430 FAIRHOLME WY | 049 | WIN | 2019-07-01 | U123258 | U128885 | 2018-06-22 | 2019-05-13 | 2019-06-13 | 2019-06-14 | KKOUNS | 2019-06-14 | 2019-06-07 | 2019-06-10 | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP7813 |  |  | 100 | 055532180267813 | 72.25 | 6240 | 24308.98 | 4037.19 | 2939.54 | 1257.7 | 12822.12 | 0 | 51.83 | 3200.6 | 780
KY | KY - WEST | 2621 | 19026880100 |  |  |  | 6716212G | 1964610 | U122858 |  | 557 | EX | INSTALL 11'-3" PMLP | 2600B | PERRY | PERRY | 067 | LEX | 2019-10-31 | U460266 | U122858 | 2019-06-14 | 2020-02-27 | 2020-02-29 | 2019-06-14 | L.STANFIELD | 2019-06-14 | 2019-07-11 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP8801 |  |  | 100 | 055732190268801 | 0.1 | 11 | 14762.46 | 1038.45 | 0 | 172.43 | 12071.89 | 0 | 2.66 | 1477.03 | 11
KY | KY - WEST | 2621 | 19026880400 |  |  |  | 6720212M | 1855408 | U461383 |  | 575 | EX | LAND FACILITY FOR REG STATION | 2600E | CLAY | 220 CLAY AV | 067 | LEX | 2019-06-18 | U462463 | U461383 | 2019-06-16 | 2019-10-01 | 2019-10-01 | 2019-06-14 | LAND SERVICES | 2019-06-14 |  |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00575 | 3200575 |  |  | WP8804 |  |  | 100 | 057532190268804 |  | 1 | 1200 | 0 | 0 | 1200 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678783100 |  | 100299247 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 291 LARCH LN | 067 | LEX | 2019-06-14 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.016667 | 1 | 1413.32 | 0.57 | 0 | 0.17 | 1412.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678783300 |  | 100299246 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 295 LARCH LN | 067 | LEX | 2019-06-14 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.5667 | 1 | 1836.98 | 202.69 | 0 | 62.47 | 1571.82 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19681012800 |  | 100262768 |  | 7352260K |  |  |  | 566 | EX | DEMO / ABANDON / RI 02-18-19 | 2621P | HOODS CREEK | 801 HOODS CREEK PK | 019 | ASH | 2019-06-17 | U125208 | U130722 | 2019-02-13 | 2019-03-26 | 2019-04-16 |  | AMCCORM | 2019-06-14 | 2019-02-20 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 32.2667 | 10 | 4430.93 | 1979.1 | 0 | 1657.16 | 794.67 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19689080300 |  | 100241914 |  | 7344168G | 1852308 |  |  | 565 | EX | RPLC SL/18026768600/ | 2600B | KY RT 1428 | 153 KY RT 1428 | 071 | LNC | 2019-06-17 | U123965 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-06-14 |  |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 0.45 | 1 | 2471.78 | 27.05 | 0 | 7.94 | 2436.79 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19697781700 |  | 500010367 |  | 6700212A |  |  |  | 565 | EX | REPLACE SERVICE LINE - D107134 | 2621P | ASHBY | 206 ASHBY CR | 239 | VER | 2019-06-17 | U125208 | U125208 | 2019-04-16 | 2019-10-11 | 2021-04-30 |  | LCLARK | 2019-06-14 | 2019-06-14 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 10.1667 | 3 | 618.02 | 553.11 | 32.83 | 32.08 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19712769200 |  | 100325635 |  | 6720208J |  |  |  | 566 | EX | DEMO / ABANDON / RA 06-14-19 | 2621P | LAKEWOOD | 1739 LAKEWOOD LN | 067 | LEX | 2019-06-14 | JENSMIN | U132002 | 2019-06-10 | 2019-07-10 | 2019-07-10 |  | JENSMIN | 2019-06-14 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.88333 | 1 | 113.97 | 51.4 | 0 | 62.57 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19713359500 |  | 100274359 |  | 6684228N |  |  |  | 565 | EX | REPLACE SVC LINE | 2621P | CAMPBELL | 329 W CAMPBELL ST | 073 | FRA | 2019-06-14 | CDESPAI | U130193 | 2019-06-12 | 2019-06-12 | 2019-06-12 |  | CDESPAI | 2019-06-14 | 2019-06-12 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 23.05 | 3 | 13370.06 | 1381.63 | 130.96 | 1285.97 | 10571.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19714271900 |  | 100312572 |  | 6716208F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D221529 | 2621P | STRATFORD | 339 STRATFORD DR | 067 | LEX | 2019-06-17 | U125208 | U124447 | 2019-06-14 | 2019-06-13 | 2019-06-13 |  | JWCOX | 2019-06-14 | 2019-06-14 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.0833 | 2 | 6890.9 | 629.56 | 901.92 | 252.55 | 5106.87 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19714328200 |  | 500495390 |  | 6716204D | 9615067 |  |  | 565 | EX | REPLACED SERVICE - D221616 GR1 | 2621P | TATES CREEK | 3393 TATES CREEK RD | 067 | LEX | 2019-06-17 | U125208 | U125964 | 2019-06-14 | 2019-06-13 | 2019-06-13 |  | JENSMIN | 2019-06-14 | 2019-06-14 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26210022 | 16.3833 | 2 | 6459.93 | 937.34 | 53.21 | 554.16 | 4915.22 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19714527600 |  | 100241869 |  | 7356252D | 1859020 |  |  | 565 | EX | REPLACE SL W/18026844201 | 2600B | WILLIAMS | 5007 WILLIAMS AV | 019 | ASH | 2019-06-14 | U125566 | U131066 | 2019-06-14 | 2019-12-31 |  |  | DAVID SKAGGS | 2019-06-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.45 | 1 | 2176.87 | 24.89 | 0 | 7.81 | 2144.17 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19679181400 |  | 100466417 |  | 6684228I |  |  |  | 565 | EX | REPLACE SERVICE LINE - D095261 | 2621P | SIGNAL RIDGE | 201 SIGNAL RIDGE RD | 073 | FRA | 2019-06-18 | U125208 | U125208 | 2019-02-04 | 2019-06-10 | 2021-02-28 |  | CDESPAI | 2019-06-17 | 2019-06-14 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.6833 | 2 | 4418.81 | 401.12 | 160 | 740.9 | 3116.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680070900 |  | 100320237 |  | 6716208K | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 227 SHADY LN | 067 | LEX | 2019-06-17 | U126532 | U131066 | 2019-02-07 | 2019-11-27 |  |  | LSHARON | 2019-06-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.85 | 2 | 4139.15 | 566.55 | 0 | 172.55 | 3400.05 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19685902200 |  | 100241822 |  | 7356252D | 1859020 |  |  | 565 | EX | RPLC SL/18026844201/ | 2600B | WILLIAMS | 5008 WILLIAMS AV | 019 | ASH | 2019-06-17 | U125566 | U131066 | 2019-03-04 | 2019-11-27 |  |  | DAVID SKAGGS | 2019-06-17 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.016667 | 1 | 1089.91 | 1.66 | 0 | 0.53 | 1087.72 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687820100 |  | 100280184 |  | 6688228I | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | BONNYCASTLE | 279 BONNYCASTLE AV | 073 | FRA | 2019-06-27 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-06-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687820400 |  | 100280182 |  | 6688228I | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | BONNYCASTLE | 283 BONNYCASTLE AV | 073 | FRA | 2019-06-27 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-06-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19689080700 |  | 100241906 |  | 7344168G | 1852308 |  |  | 565 | EX | RPLC SL/18026768600/ | 2600B | KY RT 1428 | 202 KY RT 1428 | 071 | LNC | 2019-06-17 | U123965 | U131066 | 2019-03-18 | 2019-11-27 |  |  | MARCUS BLANKENSHIP | 2019-06-17 |  |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 0.58333 | 1 | 1072.66 | 34.86 | 0 | 10.24 | 1027.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19699804300 |  | 100319096 |  | 6716208O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CURTIN | 319 CURTIN DR | 067 | LEX | 2019-06-17 | JWCOX | U125208 | 2019-04-23 | 2019-10-22 | 2021-04-30 |  | JWCOX | 2019-06-17 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.8667 | 1 | 2331.43 | 442.07 | 272.4 | 25.65 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19703225900 |  | 100303305 |  | 6712212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094792 | 2621P | LANE ALLEN | 1018 LANE ALLEN RD | 067 | LEX | 2019-06-18 | U125208 | U125208 | 2019-05-03 | 2019-11-01 | 2021-05-31 |  | JENSMIN | 2019-06-17 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.2333 | 1 | 2811.22 | 188.73 | 357.93 | 229.67 | 2034.89 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19703226700 |  | 100305253 |  | 6712212O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LANE ALLEN | 1133 LANE ALLEN RD | 067 | LEX | 2019-06-17 | JENSMIN | U125208 | 2019-05-03 | 2019-06-17 | 2021-05-31 |  | JENSMIN | 2019-06-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.5333 | 1 | 2226.17 | 148.97 | 304.57 | 181.32 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19711829300 |  | 100333010 |  | 6728200D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D192777 | 2621P | ATHENS WALNUT | 6270 ATHENS WALNUT PK | 067 | LEX | 2019-06-18 | U125208 | U125208 | 2019-06-05 | 2018-11-07 | 2020-05-31 |  | ATWILLI | 2019-06-17 | 2019-06-14 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 59.55 | 17 | 5191.27 | 3307.57 | 295.12 | 161.05 | 1427.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026873400 |  |  |  | 6724208M | 1963423 | U122858 |  | 559 | EX | INSTALL 2'-2" PMMP | 2600E | RICHMOND | RICHMOND RD | 067 | LEX | 2019-08-09 | U123258 | U122858 | 2019-04-26 | 2019-05-29 | 2019-05-30 | 2019-05-20 | LSTANFI | 2019-06-18 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP8734 |  |  | 100 | 055932190268734 | 1.4167 | 2 | 183.62 | 153.57 | 0 | 8.85 | 0 | 0 | 0 | 21.2 | 2
KY | KY - WEST | 2621 | 19026873500 |  |  |  | 6724208M | 1963423 | U122858 |  | 560 | EX | RETIRE 2'-2" PMMP | 2600E | RICHMOND | RICHMOND RD | 067 | LEX | 2019-08-09 | U123258 | U122858 | 2019-04-26 | 2019-05-30 | 2019-05-30 | 2019-05-20 | LSTANFI | 2019-06-18 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00560 | 3200560 |  |  | WP8735 |  |  | 100 | 056032190268735 | 38.05 | 0 | 3056.18 | 2213.74 | 0 | 132.72 | 709.72 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19026879700 |  |  |  | 7348256M | 1964469 | U122858 |  | 557 | EX | INSTALL 5'-3" PMIP EMERGENCY | 2621P | STATE ROUTE 5 | STATE ROUTE 5 | 019 | ASH | 2019-11-21 | U128132 | U122858 | 2019-06-10 | 2020-02-28 | 2020-02-29 | 2019-06-06 | MCOLLET | 2019-06-18 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP8797 |  |  | 100 | 055732190268797 | 0.35 | 5 | 53.98 | 21.95 | 0 | 24.98 | 0 | 0 | 0.11 | 6.94 | 5
KY | KY - EAST | 2631 | 19026879800 |  |  |  | 7348256M | 1964469 | U122858 |  | 558 | EX | RETIRE MAIN - LEAKAGE | 2621P | STATE ROUTE 5 | STATE ROUTE 5 | 019 | ASH | 2019-11-21 | U128132 | U122858 | 2019-06-10 | 2020-02-28 | 2020-02-29 | 2019-06-06 | MCOLLET | 2019-06-18 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP8798 |  |  | 100 | 055832190268798 | 0.78333 | 0 | 710.09 | 48.89 | 0 | 55.65 | 605.55 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673608500 |  | 100310653 |  | 6716208E | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2901 CLAYS MILL RD | 067 | LEX | 2019-06-18 | U126602 | U131066 | 2019-01-30 | 2019-11-27 |  |  | DPAYTON | 2019-06-18 | 2019-06-17 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.5167 | 2 | 1691.57 | 138.44 | 256.71 | 8.04 | 1288.38 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687818900 |  | 100280193 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | BONNYCASTLE | 261 BONNYCASTLE AV | 073 | FRA | 2019-06-18 | U126309 | U131066 | 2019-03-13 | 2019-11-27 |  |  | JAMIE LYNN | 2019-06-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.3333 | 1 | 1685.75 | 72.95 | 0 | 16.19 | 1596.61 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687820000 |  | 100280185 |  | 6688228I | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | BONNYCASTLE | 277 BONNYCASTLE AV | 073 | FRA | 2019-06-18 | U126309 | U131066 | 2019-03-13 | 2019-11-27 |  |  | JAMIE LYNN | 2019-06-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.1667 | 1 | 2239.25 | 389.78 | 0 | 86.48 | 1762.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19710044100 |  | 100320465 |  | 6716208C |  |  |  | 566 | EX | ABANDON / 30DAY COMMIT | 2621P | NICHOLASVILLE | 1312 NICHOLASVILLE RD | 067 | LEX | 2019-06-24 | U125208 | U125208 | 2019-05-30 | 2019-06-28 | 2019-06-30 |  | ASNICHO | 2019-06-18 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.45 | 3 | 721.71 | 682.11 | 0 | 39.6 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19712486600 |  | 100351647 |  | 6744208P |  |  |  | 566 | EX | DEMO / ABANDON / IDLE | 2621P | LEXINGTON | 208 W LEXINGTON AV 2F | 049 | WIN | 2019-06-25 | U125208 | U132002 | 2019-06-07 | 2019-07-17 | 2019-08-07 |  | DBANKS | 2019-06-18 | 2019-06-24 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.5333 | 1 | 93.07 | 87.97 | 0 | 5.1 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19712487100 |  | 100351646 |  | 6744208P |  |  |  | 566 | EX | DEMO / ABANDON / IDLE | 2621P | LEXINGTON | 208 W LEXINGTON AV 1F | 049 | WIN | 2019-06-25 | U125208 | U132002 | 2019-06-07 | 2019-07-17 | 2019-08-07 |  | DBANKS | 2019-06-18 | 2019-06-14 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 6.8667 | 6 | 449.75 | 328.67 | 90.36 | 30.72 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19713445200 |  | 100270921 |  | 6736248A |  |  |  | 566 | EX | ABN / IDLE | 2621P | ROCK QUARRY | 24 ROCK QUARRY RD | 097 | CYN | 2019-06-24 | U125208 | U125208 | 2019-06-12 | 2019-07-03 |  |  | DBANKS | 2019-06-18 | 2019-06-17 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 25.8833 | 6 | 1395.67 | 1319.09 | 0 | 76.58 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19714544800 |  | 100436703 |  | 6716204D |  |  |  | 565 | EX | REPLACE SERVICE - LEAKAGE | 2621P | TATES CREEK | 3399 TATES CREEK RD | 067 | LEX | 2019-06-25 | U126308 | U129939 | 2019-06-14 | 2019-06-17 | 2019-07-05 |  | JENSMIN | 2019-06-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2 | 2 | 1434.41 | 119.46 | 102.3 | 96.39 | 1116.26 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19715163200 |  | 100322748 |  | 6716208D |  |  |  | 565 | EX | SERVICE LINE REPLACE D221533 | 2621P | COOPER | 601 COOPER DR | 067 | LEX | 2019-06-26 | U125208 | U131739 | 2019-06-18 | 2019-06-17 | 2019-06-17 |  | JWCOX | 2019-06-18 | 2019-06-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 30.4667 | 6 | 6878.67 | 1759.77 | 410.89 | 376.19 | 4331.82 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671925200 |  | 100353683 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 15 W 2ND ST | 161 | MAY | 2019-06-21 | U126286 | U131066 | 2019-01-22 | 2019-11-27 |  |  | TYLER ALLISON | 2019-06-19 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1653.73 | 0 | 0 | 0 | 1653.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673611100 |  | 100312181 |  | 6716208I | 1636363 |  |  | 565 | EX | REPLACE SL W/17026733100 | 2600B | CLAYS MILL | 2790 CLAYS MILL RD | 067 | LEX | 2019-06-19 | U126602 | U131066 | 2019-01-30 | 2019-12-31 |  |  | DEREK PAYTON | 2019-06-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.4 | 1 | 1496.02 | 22.53 | 183.8 | 1.31 | 1288.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673611600 |  | 100312180 |  | 6716208I | 1636363 |  |  | 565 | EX | REPLACE SL W/17026733100 | 2600B | CLAYS MILL | 2794 CLAYS MILL RD | 067 | LEX | 2019-06-19 | U126602 | U131066 | 2019-01-30 | 2019-12-31 |  |  | DEREK PAYTON | 2019-06-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.2833 | 1 | 2178.83 | 70.3 | 255.12 | 4.09 | 1849.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673611800 |  | 100452315 |  | 6712208L | 1636363 |  |  | 565 | EX | REPLACE SL W/17026733100 | 2600B | CLAYS MILL | 2808 CLAYS MILL RD | 067 | LEX | 2019-06-19 | U126602 | U131066 | 2019-01-30 | 2019-12-31 |  |  | DEREK PAYTON | 2019-06-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.8167 | 1 | 1983.34 | 429.04 | 237.39 | 28.53 | 1288.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678773500 |  | 100299179 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 235 BURKE RD | 067 | LEX | 2019-06-19 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.55 | 1 | 2023.07 | 143.78 | 0 | 44.31 | 1834.98 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678774000 |  | 100299175 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 251 BURKE RD | 067 | LEX | 2019-06-19 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.31667 | 1 | 1273.88 | 18.69 | 0 | 5.75 | 1249.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678774200 |  | 100299156 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 256 BURKE RD | 067 | LEX | 2019-06-19 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.4 | 1 | 1388.87 | 192.52 | 0 | 59.32 | 1137.03 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19685902300 |  | 100241868 |  | 7356252D | 1859020 |  |  | 565 | EX | RPLC SL/18026844201/ | 2600B | WILLIAMS | 5011 WILLIAMS AV | 019 | ASH | 2019-06-19 | U125566 | U131066 | 2019-03-04 | 2019-11-27 |  |  | DAVID SKAGGS | 2019-06-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.65 | 1 | 2228.58 | 36.51 | 0 | 8 | 2184.07 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687817800 |  | 100280178 |  | 6688228M | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | ANNEX | 288 ANNEX DR | 073 | FRA | 2019-06-19 | U126309 | U131066 | 2019-03-13 | 2019-11-27 |  |  | JAMIE LYNN | 2019-06-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.1667 | 1 | 1456.7 | 172.57 | 0 | 38.27 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687831600 |  | 100280074 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 300 WESTLAND DR | 073 | FRA | 2019-06-19 | U126309 | U131066 | 2019-03-13 | 2019-11-27 |  |  | JAMIE LYNN | 2019-06-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.8333 | 1 | 1980.81 | 317.41 | 0 | 70.41 | 1592.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19702864100 |  | 100302342 |  | 6712212G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | ALEXANDRIA | 1230 ALEXANDRIA DR | 067 | LEX | 2019-06-19 | JWCOX | U125208 | 2019-05-02 | 2019-10-29 | 2021-04-30 |  | JWCOX | 2019-06-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.1833 | 1 | 1653.3 | 67.48 | 250.4 | 3.92 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19710741900 |  | 100291774 |  | 6720216H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094020 | 2621P | ZORN | 721 ZORN CT | 067 | LEX | 2019-06-25 | U125208 | U125208 | 2019-05-31 | 2019-11-22 | 2021-05-31 |  | ASNICHO | 2019-06-19 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.7 | 2 | 958.46 | 905.87 | 0 | 52.59 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19711866100 |  | 100249356 |  | 7356216 |  |  |  | 566 | EX | DEMO / LCB-ABN / RI 06-11-19 | 2621P | ELOISE | 362 ELOISE RD | 127 | LOU | 2019-06-19 | MCOLLET | U132002 | 2019-06-05 | 2019-07-16 | 2019-08-06 |  | MCOLLET | 2019-06-19 | 2019-06-07 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 21.6 | 5 | 1931.64 | 1259.9 | 27.77 | 643.97 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19715293500 |  | 100290426 |  | 6720212C |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | NORTHWOOD | 158 NORTHWOOD DR | 067 | LEX | 2019-06-19 | JWCOX | U125208 | 2019-06-18 | 2019-06-18 | 2019-06-18 |  | JWCOX | 2019-06-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.5167 | 1 | 1902.95 | 197.43 | 179.14 | 11.48 | 1514.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19715528600 |  | 100323911 |  | 6716208P |  |  |  | 565 | EX | REPLACE SERVICE | 2621P | BROOK HILL | 3315 BROOK HILL CR | 067 | LEX | 2019-06-19 | JWCOX | U131168 | 2019-06-18 | 2019-06-18 | 2019-06-18 |  | JWCOX | 2019-06-19 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.25 | 1 | 2951.81 | 238.47 | 275.68 | 13.82 | 2423.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026879900 |  |  |  | 6720208B | 1964540 | U130604 |  | 557 | EX | INSTALL 40' OF 4"PMLP MAIN | 2621P | RICHMOND | 1731 RICHMOND RD | 067 | LEX | 2019-09-24 | U460266 | U461383 | 2019-06-12 | 2019-06-19 | 2021-04-30 | 2019-06-13 | LSTANFI | 2019-06-20 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP8799 | AMRCB |  | 100 | 055732190268799 | 3.3 | 32 | 14489.69 | 212.78 | 926.74 | 12.34 | 11565.61 | 0 | 6.65 | 1765.57 | 32
KY | KY - WEST | 2621 | 19026880000 |  |  |  | 6720208B | 1964540 | U130604 |  | 558 | EX | RETIRE 40' OF 4"BSLP MAIN | 2621P | RICHMOND | 1731 RICHMOND RD | 067 | LEX | 2019-09-24 | U460266 | U461383 | 2019-06-12 | 2019-06-20 | 2021-04-30 | 2019-06-13 | LSTANFI | 2019-06-20 | 2019-06-13 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP8800 | AMRCB |  | 100 | 055832190268800 | 14.15 | 0 | 2391.44 | 903.44 | 0 | 52.43 | 1435.57 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687818600 |  | 100280196 |  | 6688228J | 1853312 |  |  | 566 | EX | ABANDON SL/18026776900/ | 2600B | BONNYCASTLE | 255 BONNYCASTLE AV | 073 | FRA | 2019-06-21 | U126309 | U131066 | 2019-03-13 | 2019-11-27 |  |  | JAMIE LYNN | 2019-06-20 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 1.3833 | 1 | 1146.78 | 75.12 | 0 | 16.66 | 1055 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687818800 |  | 100280194 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | BONNYCASTLE | 259 BONNYCASTLE AV | 073 | FRA | 2019-07-11 | U126309 | U131066 | 2019-03-13 | 2019-11-27 |  |  | JAMIE LYNN | 2019-06-20 | 2019-06-20 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.1167 | 1 | 1624.02 | 170.38 | 0 | 37.78 | 1415.86 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19714900600 |  | 100250572 |  | 7376184A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | RIVER FRONT | 1160 RIVER FRONT RD | 159 | LOV | 2019-06-20 | BBMULLI | U125208 | 2019-06-17 | 2019-06-17 | 2019-07-05 |  | BBMULLI | 2019-06-20 | 2019-06-19 |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 35.4833 | 4 | 3813.11 | 2071.9 | 0 | 466.94 | 1274.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19715935300 |  | 100302190 |  | 6712212K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094851 | 2621P | LE HAVRE | 2352 LE HAVRE RD | 067 | LEX | 2019-06-26 | U125208 | U130193 | 2019-06-20 | 2019-06-20 | 2021-05-31 |  | JWCOX | 2019-06-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.4167 | 1 | 1842.06 | 248.06 | 248.09 | 14.41 | 1331.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19716006500 |  | 100306831 |  | 6716212I |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HILL VIEW | 1692 HILL VIEW PL | 067 | LEX | 2019-06-26 | U125208 | U130193 | 2019-06-20 | 2019-06-20 | 2021-05-31 |  | JWCOX | 2019-06-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26210022 | 2.0667 | 1 | 2590.28 | 116.98 | 186.51 | 6.79 | 2280 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19716012200 |  | 100301510 |  | 6712212H |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | PICADILLY | 1902 PICADILLY ST | 067 | LEX | 2019-06-20 | JENSMIN | U130193 | 2019-06-20 | 2019-06-20 | 2021-05-31 |  | JENSMIN | 2019-06-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.2833 | 1 | 2307.24 | 250.63 | 267.7 | 305.04 | 1483.87 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19026881400 |  |  |  | 6684228N | 1964732 | U122858 |  | 558 | EX | RETIRE 30'-4" BSLP | 2621P | CAPITAL HEIGHTS | 200 CAPITAL HEIGHTS DR | 073 | FRA | 2019-09-23 | U128132 | U122858 | 2019-06-19 | 2019-06-20 | 2021-06-12 | 2019-06-21 | BJLONE | 2019-06-21 | 2019-06-20 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP8814 | AMRCB |  | 100 | 055832190268814 | 31.6167 | 0 | 22112.62 | 1870.84 | 0 | 1186.79 | 19054.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673608700 |  | 100310655 |  | 6712208L | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2905 CLAYS MILL RD | 067 | LEX | 2019-06-21 | U461439 | U131066 | 2019-01-30 | 2019-11-27 |  |  | A PARRIS | 2019-06-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 1527.3 | 0 | 218.64 | 0 | 1308.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678774500 |  | 100299172 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 263 BURKE RD | 067 | LEX | 2019-06-21 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.8167 | 1 | 1791.42 | 215.7 | 0 | 66.5 | 1509.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678774600 |  | 100299158 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 264 BURKE RD | 067 | LEX | 2019-06-21 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.2833 | 1 | 1604.76 | 73.02 | 0 | 22.52 | 1509.22 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19685902400 |  | 100241866 |  | 7356252D | 1859020 |  |  | 565 | EX | RPLC SL/18026844201/ | 2600B | WILLIAMS | 5021 WILLIAMS AV | 019 | ASH | 2019-06-21 | U125566 | U131066 | 2019-03-04 | 2019-06-21 |  |  | DAVID SKAGGS | 2019-06-21 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1397.89 | 0 | 0 | 0 | 1397.89 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19685907700 |  | 100444788 |  | 7356252D | 1859020 |  |  | 565 | EX | REPLACE SL W/18026844201 | 2600B | WILLIAMS | 5016 WILLIAMS AV | 019 | ASH | 2019-06-21 | U125566 | U131066 | 2019-03-04 | 2019-12-31 |  |  | DAVID SKAGGS | 2019-06-21 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1397.89 | 0 | 0 | 0 | 1397.89 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687818100 |  | 100280176 |  | 6688228M | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | ANNEX | 292 ANNEX DR | 073 | FRA | 2019-06-21 | U126309 | U131066 | 2019-03-13 | 2019-11-27 |  |  | JAMIE LYNN | 2019-06-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.11667 | 1 | 1424.53 | 7.09 | 0 | 1.58 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687818500 |  | 100280197 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | BONNYCASTLE | 253 BONNYCASTLE AV | 073 | FRA | 2019-06-21 | U126309 | U131066 | 2019-03-13 | 2019-11-27 |  |  | JAMIE LYNN | 2019-06-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.5 | 1 | 2194.66 | 353.32 | 0 | 78.35 | 1762.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19690932100 |  | 100309193 |  | 6716208A |  |  |  | 566 | EX | DEMO / ABANDON / RI 04-02-19 | 2621P | LANE ALLEN | 825 LANE ALLEN RD | 067 | LEX | 2019-06-21 | JENSMIN | U132002 | 2019-03-25 | 2019-05-02 | 2019-05-23 |  | JENSMIN | 2019-06-21 | 2019-06-19 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.8333 | 3 | 1436.56 | 283.33 | 10.76 | 344.87 | 797.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19714344100 |  | 100313063 |  | 6716208A |  |  |  | 565 | EX | REPLACE SERV - RELOC METER | 2621P | ROSEMONT | 515 ROSEMONT GN | 067 | LEX | 2019-06-21 | JENSMIN | U125208 | 2019-06-14 | 2019-07-05 |  |  | JENSMIN | 2019-06-21 | 2019-06-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 8.1333 | 2 | 4289.78 | 474.38 | 112.7 | 577.21 | 3125.49 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19716009400 |  | 100350918 |  | 6744208O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LOCUST | 10 LOCUST DR | 049 | WIN | 2019-06-21 | RJJOHNS | U125208 | 2019-06-20 | 2019-06-20 | 2019-06-20 |  | RJJOHNS | 2019-06-21 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 19.4333 | 3 | 1182.03 | 955.86 | 170.49 | 55.68 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19716321000 |  | 100330341 |  | 6720208B |  |  |  | 565 | EX | GRADE 1 REPLACE | 2621P | KINGSWAY | 229 KINGSWAY DR | 067 | LEX | 2019-06-21 | JWCOX | U129939 | 2019-06-20 | 2019-06-20 | 2019-06-20 |  | JWCOX | 2019-06-21 | 2019-06-21 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.0333 | 2 | 5579.76 | 793.11 | 297.02 | 136.78 | 4352.85 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19716579900 |  | 100293461 |  | 6720216I |  |  |  | 565 | EX | REPLACE SERV LINE | 2621P | MONTROSE | 1562 MONTROSE DR | 067 | LEX | 2019-06-21 | LSTANFI | U129939 | 2019-06-21 | 2019-06-21 |  |  | LSTANFI | 2019-06-21 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 13.4333 | 3 | 792.21 | 674.98 | 26.22 | 91.01 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026877500 |  | 500334110 |  | 6720208O | 1963898 | U461383 |  | 555 | EX | INSTALL 50' OF 2"PMMP MAIN | 2600B | LAKESHORE | 600 LAKESHORE DR | 067 | LEX | 2019-07-01 | U123258 | U461383 | 2019-05-16 | 2019-06-12 | 2019-06-28 | 2019-06-20 | KKOUNS | 2019-06-24 | 2019-06-20 | 2019-06-18 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP8775 |  |  | 100 | 055532190268775 | 15.25 | 120 | 10196 | 857.63 | 720.03 | 265.74 | 7008.01 | 0 | 5.03 | 1339.56 | 60
KY | KY - WEST | 2621 | 11919544000 |  | 100299157 |  | 16716216N |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | BURKE | 260 BURKE RD | 067 | LEX | 2019-06-25 | U126603 | U907469 | 2011-08-09 | 2016-08-08 |  |  | SHAWN DENNIS | 2019-06-25 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.8 | 1 | 754.89 | 222.91 | 0 | 66.59 | 465.39 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19026872900 |  |  |  | 7332132J | 1963346 | GSULLI1 |  | 561 | EX | INSTALL 378' 4" & 10' 3" PMMP | 2600B | PURPOSE | PURPOSE DR | 119 | PIP | 2019-07-17 | U462463 | GSULLI1 | 2019-04-24 | 2019-06-06 | 2019-06-30 | 2019-05-21 | MARCUS BLANKENSHIP | 2019-06-25 | 2019-05-09 |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00561 | 3200561 |  |  | WP8729 |  |  | 100 | 056132190268729 | 282.8167 | 10527 | 76245.32 | 16293.67 | 2133.92 | 5007.54 | 42650.5 | 0 | 116.04 | 10043.65 | 363
KY | KY - EAST | 2633 | 19026873000 |  |  |  | 7332132J | 1963346 | GSULLI1 |  | 562 | EX | RETIRE 84' 3" PMMP | 2600B | PURPOSE | PURPOSE DR | 119 | PIP | 2019-07-16 | U462463 | GSULLI1 | 2019-04-24 | 2019-06-28 | 2019-06-30 | 2019-06-21 | MARCUS BLANKENSHIP | 2019-06-25 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00562 | 3200562 |  |  | WP8730 |  |  | 100 | 056232190268730 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19026873100 |  |  |  | 7332132J | 1963346 | GSULLI1 |  | 561 | EX | INSTALL 60' OF 2"CSHP MAIN | 2600B | PURPOSE | PURPOSE DR | 119 | PIP | 2019-07-19 | U462463 | GSULLI1 | 2019-04-24 | 2019-06-24 | 2019-06-30 | 2019-06-20 | MARCUS BLANKENSHIP | 2019-06-25 | 2019-05-28 |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00561 | 3200561 |  |  | WP8731 |  |  | 100 | 056132190268731 | 208.65 | 1520 | 51028 | 12591.27 | 2298.15 | 2920.63 | 26369.16 | 0 | 139.75 | 6709.04 | 76
KY | KY - CENTRAL | 2632 | 19671925100 |  | 100353682 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 13 W 2ND ST | 161 | MAY | 2019-06-25 | U126286 | U131066 | 2019-01-22 | 2019-11-27 |  |  | TYLER ALLISON | 2019-06-25 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1392.93 | 0 | 0 | 0 | 1392.93 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678769700 |  | 100299362 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BOILING SPRING | 225 BOILING SPRING DR | 067 | LEX | 2019-06-26 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.1667 | 1 | 1820.04 | 127.02 | 0 | 37.96 | 1655.06 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678772600 |  | 100299185 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 211 BURKE RD | 067 | LEX | 2019-06-25 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.15 | 1 | 1291.44 | 68.82 | 0 | 20.55 | 1202.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678775300 |  | 100299162 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 280 BURKE RD | 067 | LEX | 2019-06-25 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.35 | 1 | 1233.31 | 138.21 | 0 | 41.31 | 1053.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678781400 |  | 100299257 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LARCH | 255 LARCH LN | 067 | LEX | 2019-06-25 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2064.1 | 0 | 0 | 0 | 2064.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678788800 |  | 100299203 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | MEADOWTHORPE | 1530 MEADOWTHORPE AV | 067 | LEX | 2019-06-25 | U126603 | U131066 | 2019-02-01 | 2019-06-25 |  |  | SHAWN DENNIS | 2019-06-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.35 | 1 | 1525.6 | 138.21 | 0 | 41.31 | 1346.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678789300 |  | 100299199 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | MEADOWTHORPE | 1546 MEADOWTHORPE AV | 067 | LEX | 2019-06-25 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.8167 | 1 | 1344.84 | 224.08 | 0 | 66.97 | 1053.79 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19685901400 |  | 100241817 |  | 7356256P | 1859020 |  |  | 565 | EX | RPLC SL/18026844201/ | 2600B | WILLIAMS | 4900 WILLIAMS AV | 019 | ASH | 2019-06-28 | U125573 | U131066 | 2019-03-04 | 2019-11-27 |  |  | BCOFER | 2019-06-25 |  | 2019-06-25 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3250.76 | 27.42 | 0 | 8.92 | 3214.42 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687817900 |  | 100280177 |  | 6688228M | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | ANNEX | 290 ANNEX DR | 073 | FRA | 2019-06-27 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-06-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687818200 |  | 100280175 |  | 6688228M | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | ANNEX | 294 ANNEX DR | 073 | FRA | 2019-06-27 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-06-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2124.49 | 0 | 0 | 0 | 2124.49 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687836900 |  | 100280174 |  | 6688228M | 1853312 |  |  | 565 | EX | REPLACE SL W/18026776900 | 2600B | ANNEX | 291 ANNEX DR | 073 | FRA | 2019-06-27 | U461375 | U131066 | 2019-03-13 | 2019-12-31 |  |  | LARRY BROWN | 2019-06-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1762.99 | 0 | 0 | 0 | 1762.99 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19689080100 |  | 100241898 |  | 7344168G | 1852308 |  |  | 565 | EX | RPLC SL/18026768600/ | 2600B | KY RT 1428 | 65 KY RT 1428 | 071 | LNC | 2019-06-25 | U123965 | U131066 | 2019-03-18 | 2019-11-27 |  |  | MARCUS BLANKENSHIP | 2019-06-25 |  |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 1.1833 | 1 | 1364.45 | 66.99 | 0 | 20.6 | 1276.86 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689091600 |  | 100255712 |  | 7348264H | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | MEADE | 1604 MEADE ST | 089 | FLA | 2019-06-25 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-06-25 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.31667 | 1 | 973.1 | 18.3 | 0 | 5.58 | 949.22 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19696896200 |  | 100278914 |  | 6688228D | 1962699 | U461383 |  | 565 | EX | REPLACE S/L & RELOCATE METER | 2600B | FOXLEY | 60 FOXLEY LN | 073 | FRA | 2019-06-25 | U461443 | U461383 | 2019-04-14 | 2019-07-01 | 2019-07-01 |  | WGRAVES | 2019-06-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 16.4333 | 2 | 3178.55 | 907.81 | 181.2 | 285.39 | 1804.15 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19714037100 |  | 100343745 | 44 | 7240212B |  |  |  | 566 | EX | ABANDON / RI 6-13-19 TRL GONE | 2621P | WILMONT | 481 WILMONT DR | 173 | MT | 2019-06-25 | DENNING | JDSKAGG | 2019-06-13 | 2019-07-10 |  |  | DENNING | 2019-06-25 | 2019-06-24 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 13.6833 | 4 | 1040.88 | 801.08 | 0 | 239.8 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19716978600 |  | 500658367 |  | 6716212P |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | ROSE | 469 ROSE ST | 067 | LEX | 2019-06-25 | JWCOX | U130193 | 2019-06-24 | 2019-06-24 |  |  | JWCOX | 2019-06-25 | 2019-06-24 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 28.7667 | 4 | 7799.71 | 1491.48 | 32.48 | 86.56 | 6189.19 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19717184000 |  | 100332224 |  | 6720212N |  |  |  | 565 | EX | REPLACE SERVICE D221629 GR 1 | 2621P | AURORA | 721 AURORA AV | 067 | LEX | 2019-06-26 | U125208 | U131168 | 2019-06-24 | 2019-06-24 | 2019-06-24 |  | JWCOX | 2019-06-25 | 2019-06-25 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.5667 | 6 | 3846.82 | 578.27 | 298.31 | 33.52 | 2936.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19717264200 |  | 100335697 |  | 6720212L |  |  |  | 566 | EX | ABANDON SVC LINE PAPER ONLY | 2621P | NEW CIRCLE | 761 E NEW CIRCLE RD | 067 | LEX | 2019-06-25 | BWHITE | U130193 | 2019-06-25 | 2019-06-25 |  |  | BWHITE | 2019-06-25 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.6333 | 1 | 81.48 | 77.02 | 0 | 4.46 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19717369900 |  | 500562026 |  | 6692224A | 1964020 |  |  | 566 | VO | ABANDON SVC LINE | 2621P | CHENAULT | 982 CHENAULT RD | 073 | FRA | 2019-06-25 |  | U130193 | 2019-06-25 | 2019-06-25 |  |  | BJLONE | 2019-06-25 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - EAST | 2631 | 19717408500 |  | 100255711 |  | 7348264G | 1859009 |  |  | 566 | EX | ABANDON SL W/18026843700 | 2600B | 4TH | 507 N 4TH ST | 089 | FLA | 2019-06-26 | U125566 | U131066 | 2019-06-25 | 2019-12-31 |  |  | DAVID SKAGGS | 2019-06-25 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.016667 | 1 | 1147.52 | 1.05 | 0 | 0.23 | 1146.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11900081500 |  | 100467275 |  | 6712208M |  |  |  | 566 | EX | ABANDON SERVICE | 2600B | FORSYTHE | 3933 FORSYTHE DR | 067 | LEX | 2019-06-27 | U125208 | U123933 | 2011-04-06 | 2049-12-31 |  |  | JWCOX | 2019-06-26 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.7333 | 2 | 1502.73 | 356.67 | 10.3 | 75.33 | 1060.43 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572284600 |  | 100279972 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | STRATHMORE | 317 STRATHMORE DR | 073 | FRA | 2019-06-27 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-06-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572284700 |  | 100279973 |  | 6688228N | 1748294 |  |  | 565 | EX | RPLC SL/17026731300/ | 2600B | STRATHMORE | 319 STRATHMORE DR | 073 | FRA | 2019-06-27 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-06-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026880200 |  |  |  | 6716212G | 1964610 | U122858 |  | 558 | EX | RETIRE 11'-3" PLP | 2600E | PERRY | PERRY | 067 | LEX | 2019-10-30 | U460266 | U122858 | 2019-06-14 | 2020-02-28 | 2020-02-29 | 2019-06-14 | LSTANFI | 2019-06-26 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP8802 |  |  | 100 | 055832190268802 | 2.75 | 0 | 332.94 | 173.97 | 0 | 158.97 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678774900 |  | 100299160 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 272 BURKE RD | 067 | LEX | 2019-06-26 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.0333 | 1 | 1460.52 | 62.34 | 0 | 18.63 | 1379.55 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678775500 |  | 100299166 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 287 BURKE RD | 067 | LEX | 2019-06-26 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-26 | 2019-06-14 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.6667 | 3 | 2635.22 | 613.81 | 0 | 186.43 | 1834.98 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678789400 |  | 100299198 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | MEADOWTHORPE | 1550 MEADOWTHORPE AV | 067 | LEX | 2019-06-26 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.25 | 1 | 1681.66 | 191.16 | 0 | 57.11 | 1433.39 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19686065600 |  | 100465693 |  | 6680224F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D913618 | 2621P | GAME FARM | 4 GAME FARM RD | 073 | FRA | 2019-06-27 | U125208 | U125208 | 2019-03-05 | 2019-09-04 | 2021-03-31 |  | CDESPAI | 2019-06-26 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.3333 | 1 | 3774.2 | 382.73 | 147.88 | 700.17 | 2543.42 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19686151900 |  | 100241818 |  | 7356256P | 1859020 |  |  | 565 | EX | REPLACE SL W/18026844200 | 2600B | WILLIAMS | 4950 WILLIAMS AV | 019 | ASH | 2019-06-28 | U125573 | U131066 | 2019-03-05 | 2019-12-31 |  |  | BCOFER | 2019-06-26 |  | 2019-06-26 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2181.85 | 34.2 | 0 | 11.1 | 2136.55 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687830000 |  | 100279974 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | STRATHMORE | 321 STRATHMORE DR | 073 | FRA | 2019-06-27 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-06-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687830100 |  | 100280013 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | STRATHMORE | 322 STRATHMORE DR | 073 | FRA | 2019-06-27 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-06-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687830300 |  | 100280012 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | STRATHMORE | 324 STRATHMORE DR | 073 | FRA | 2019-06-27 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-06-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19689080200 |  | 100241902 |  | 7344168G | 1852308 |  |  | 565 | EX | RPLC SL/18026768600/ | 2600B | KY RT 1428 | 141 KY RT 1428 | 071 | LNC | 2019-06-26 | U123965 | U131066 | 2019-03-18 | 2019-11-27 |  |  | MARCUS BLANKENSHIP | 2019-06-26 |  |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 0.26667 | 1 | 1046.87 | 14.78 | 0 | 4.53 | 1027.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19713373800 |  | 100286635 | 37 | 6768172A |  |  |  | 565 | EX | ABANDON / RA 06-11-19 REMODEL | 2621P | ELM | 717 ELM ST | 065 | RAV | 2019-06-26 | DENNING | U130963 | 2019-06-12 | 2019-07-11 |  |  | DENNING | 2019-06-26 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26290031 | 17.3333 | 2 | 1460.36 | 1017.67 | 138.03 | 304.66 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19717431400 |  | 100312701 |  | 6716208E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D221618 | 2621P | LONGVIEW | 460 LONGVIEW DR | 067 | LEX | 2019-06-27 | U125208 | U125208 | 2019-06-25 | 2019-06-25 | 2019-06-25 |  | JWCOX | 2019-06-26 | 2019-06-26 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.3667 | 2 | 3236.43 | 62.84 | 232.74 | 13.26 | 2927.59 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19717454600 |  | 100332225 |  | 6720212N |  |  |  | 565 | EX | REPLACE SERVICE | 2621P | AURORA | 717 AURORA AV | 067 | LEX | 2019-06-27 | U125208 | U131168 | 2019-06-25 | 2019-06-25 |  |  | JWCOX | 2019-06-26 | 2019-06-25 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.1667 | 3 | 3117.01 | 69.59 | 298.31 | 4.03 | 2745.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19717643200 |  | 500347263 |  | 6720212B |  | U131168 |  | 566 | EX | ABANDON SERVICE | 2621P | BLUE GRASS | 303 BLUE GRASS AV | 067 | LEX | 2019-06-26 | JENSMIN | U131168 | 2019-06-25 | 2019-06-25 |  |  | JENSMIN | 2019-06-26 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.3 | 2 | 3591.58 | 589.16 | 10.76 | 116.18 | 2875.48 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19717985000 |  | 100412183 |  | 7356252A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LEIGHWOOD | 3899 LEIGHWOOD DR | 019 | ASH | 2019-06-27 | U125208 | U125208 | 2019-06-26 | 2019-06-26 | 2019-06-26 |  | BROBERT | 2019-06-26 | 2019-06-26 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 7.95 | 3 | 1009.18 | 464.17 | 170.69 | 374.32 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19718189900 |  | 100255665 |  | 7348264G | 1859009 |  |  | 565 | EX | RPLC SL/18026843700 | 2600B | 4TH | 510 N 4TH ST | 089 | FLA | 2019-06-26 | U125566 | U125201 | 2019-06-26 | 2019-09-30 |  |  | DAVID SKAGGS | 2019-06-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1677.82 | 0 | 0 | 0 | 1677.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19719534400 |  | 100311733 |  | 6712208L | 1636363 |  |  | 565 | EX | REPLACE SL W/17026733100 | 2600B | CLAYS MILL | 2814 CLAYS MILL RD | 067 | LEX | 2019-06-27 | U461439 | U131066 | 2019-06-27 | 2019-12-31 |  |  | A PARRIS | 2019-06-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.5 | 1 | 1538.26 | 84.27 | 237.96 | 26.14 | 1189.89 | 0 | 0 | 0
KY | KY - EAST | 2631 | 20776019200 |  | 100243114 |  | 7356256O | 1964808 |  |  | 565 | EX | REPLACE W/ 19-0268816-00 | 2600B | MOUND | 4101 MOUND ST | 019 | ASH | 2020-06-26 | U461496 | U131066 | 2020-01-30 | 2020-06-24 |  |  | ROCKIE MULLINS | 2019-06-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.46667 | 1 | 2313.73 | 48.22 | 0 | 16.89 | 2248.62 | 0 | 0 | 0
KY | KY - WEST | 2621 | 13136372600 |  | 100299174 |  | 671621N | 1855322 |  |  | 565 | EX | REPLACE SL W/180267924-01 | 2621P | BURKE | 255 BURKE RD | 067 | LEX | 2019-06-27 | U126532 | U123119 | 2013-05-10 | 2013-12-23 |  |  | LSHARON | 2019-06-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.5667 | 1 | 1685.3 | 209.98 | 0 | 62.74 | 1412.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18026847801 |  | 500514167 |  | 6720208M | 1859847 | U461383 |  | 555 | EX | INSTALL 925' OF 2"/4"PMMP MAIN | 2600B | CHINOE | 961 CHINOE RD | 067 | LEX | 2019-07-17 | U124014 | U461383 | 2019-06-11 | 2019-05-20 | 2019-06-30 | 2019-06-25 | DDAVIS | 2019-06-27 | 2019-06-24 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP8478 |  |  | 100 | 055532180268478 | 272.3667 | 33810 | 103960.01 | 15237.59 | 3137.56 | 4169.8 | 67534.83 | 0 | 188.1 | 13692.13 | 966
KY | KY - WEST | 2623 | 19026868301 |  | 501247590 |  | 6688228D | 1962699 | U461383 |  | 555 | EX | INSTALL 450' OF 2"PMMP MAIN | 2600B | FOXLEY | 59 FOXLEY LN | 073 | FRA | 2019-07-02 | U123258 | U461383 | 2019-06-14 | 2019-06-03 | 2019-07-01 | 2019-06-21 | WGRAVES | 2019-06-27 | 2019-06-14 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP8683 |  |  | 100 | 055532190268683 | 120.0167 | 8334 | 55625.1 | 6424.87 | 756.66 | 1933.93 | 38932.38 | 0 | 106.33 | 7470.93 | 463
KY | KY - WEST | 2621 | 19673608200 |  | 100310471 |  | 6712208L | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2893 CLAYS MILL RD | 067 | LEX | 2019-06-27 | U461439 | U131066 | 2019-01-30 | 2019-11-27 |  |  | A PARRIS | 2019-06-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 3.65 | 1 | 1866.68 | 205.6 | 237.96 | 63.76 | 1359.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678775200 |  | 100299168 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 279 BURKE RD | 067 | LEX | 2019-06-27 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1509.22 | 0 | 0 | 0 | 1509.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678794600 |  | 100299184 |  | 6716212B | 1855322 |  |  | 565 | EX | REPLACE SL W/18026792400 | 2600B | BURKE | 215 BURKE RD | 067 | LEX | 2019-06-27 | U126532 | U131066 | 2019-02-01 | 2019-12-31 |  |  | LSHARON | 2019-06-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.5333 | 1 | 1624.52 | 325.26 | 0 | 97.19 | 1202.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678797500 |  | 100299154 |  | 6716216N | 1855322 |  |  | 565 | EX | REPLACE SL W/18026792400 | 2600B | BURKE | 248 BURKE RD | 067 | LEX | 2019-06-27 | U126603 | U131066 | 2019-02-01 | 2019-12-31 |  |  | SHAWN DENNIS | 2019-06-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.55 | 1 | 2650.79 | 208.81 | 0 | 62.38 | 2379.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680084700 |  | 100320270 |  | 6716208G | 1748686 |  |  | 565 | EX | REPLACE SL W/17026736100 | 2600B | MCDONALD | 1830 MCDONALD AV | 067 | LEX | 2019-07-17 | U125208 | U131066 | 2019-02-07 | 2019-06-26 | 2019-06-26 |  | JENSMIN | 2019-06-27 | 2019-06-26 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.15 | 5 | 3816.36 | 727.29 | 222.21 | 152.81 | 2714.05 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19685901700 |  | 100241871 |  | 7356256P | 1859020 |  |  | 565 | EX | RPLC SL/18026844201/ | 2600B | WILLIAMS | 4911 WILLIAMS AV | 019 | ASH | 2019-06-28 | U125573 | U131066 | 2019-03-04 | 2019-11-27 |  |  | BCOFER | 2019-06-27 |  | 2019-06-27 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1947.17 | 0 | 0 | 0 | 1947.17 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687830400 |  | 100279975 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | STRATHMORE | 325 STRATHMORE DR | 073 | FRA | 2019-07-09 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-06-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687830700 |  | 100280010 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | STRATHMORE | 328 STRATHMORE DR | 073 | FRA | 2019-07-09 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-06-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19689080400 |  | 100241904 |  | 7344168G | 1852308 |  |  | 565 | EX | RPLC SL/18026768600/ | 2600B | KY RT 1428 | 172 KY RT 1428 | 071 | LNC | 2019-06-27 | U123965 | U131066 | 2019-03-18 | 2019-11-27 |  |  | MARCUS BLANKENSHIP | 2019-06-27 |  |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 0.31667 | 1 | 1050.56 | 17.6 | 0 | 5.4 | 1027.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689200100 |  | 100255656 |  | 7348264H | 1859009 |  |  | 565 | EX | REPLACE SL W/18026843700 | 2600B | MEADE | 1422 MEADE ST | 089 | FLA | 2019-06-27 | U125566 | U131066 | 2019-03-18 | 2019-12-31 |  |  | DAVID SKAGGS | 2019-06-27 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 949.22 | 0 | 0 | 0 | 949.22 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19715640600 |  | 100275441 |  | 6684228F |  |  |  | 566 | EX | ABDN SL/COVERT ELEC PS MAILBOX | 2621P | KENTUCKY | 640 KENTUCKY AV 1 | 073 | FRA | 2019-07-02 | U125208 | U132002 | 2019-06-19 | 2019-07-30 | 2019-08-20 |  | BJLONE | 2019-06-27 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 17.3833 | 2 | 1050.25 | 992.65 | 0 | 57.6 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19715643300 |  | 100275442 |  | 6684228F |  |  |  | 566 | EX | ABDN SL/CONV ELECT PS MAILBOX | 2621P | KENTUCKY | 640 KENTUCKY AV 2 | 073 | FRA | 2019-06-27 | BJLONE | U132002 | 2019-06-19 | 2019-07-30 | 2019-08-20 |  | BJLONE | 2019-06-27 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.083333 | 2 | 4.78 | 4.52 | 0 | 0.26 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19715644500 |  | 100275444 |  | 6684228F |  |  |  | 566 | EX | ABDN SL/CONV ELECT PS MAILBOX | 2621P | KENTUCKY | 640 KENTUCKY AV 3 | 073 | FRA | 2019-06-27 | BJLONE | U132002 | 2019-06-19 | 2019-07-30 | 2019-08-20 |  | BJLONE | 2019-06-27 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.11667 | 2 | 6.63 | 6.28 | 0 | 0.35 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19715646700 |  | 100275445 |  | 6684228F |  |  |  | 566 | EX | ABDN SL/CONV ELECT PS MAILBOX | 2621P | KENTUCKY | 640 KENTUCKY AV 4 | 073 | FRA | 2019-06-27 | BJLONE | U132002 | 2019-06-19 | 2019-07-30 | 2019-08-20 |  | BJLONE | 2019-06-27 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.066667 | 2 | 3.53 | 3.34 | 0 | 0.19 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19715649300 |  | 100275448 |  | 6684228F |  |  |  | 566 | EX | ABDN SL/CONV ELECT PS MAILBOX | 2621P | KENTUCKY | 640 KENTUCKY AV 5 | 073 | FRA | 2019-06-27 | BJLONE | U132002 | 2019-06-19 | 2019-07-30 | 2019-08-20 |  | BJLONE | 2019-06-27 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.36667 | 2 | 31.93 | 21.02 | 9.71 | 1.2 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19716977400 |  | 100258800 |  | 7356256F |  |  |  | 566 | EX | ABDN ASAP DUE TO DEMO-COA-FIRE | 2621P | MONTGOMERY | 2712 MONTGOMERY AV | 019 | ASH | 2019-06-27 | BROBERT | DYOUNG | 2019-06-24 | 2019-06-27 |  |  | BROBERT | 2019-06-27 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.0667 | 1 | 71.49 | 57.04 | 11.15 | 3.3 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19720179500 |  | 100281476 |  | 6712232N |  |  |  | 566 | EX | PAPER ABANDON ONLY | 2621P | BROADWAY | 422 N BROADWAY ST 10 | 209 | GEO | 2019-06-27 | BBRIGHT | BBRIGHT | 2019-06-27 | 2019-06-27 |  |  | BBRIGHT | 2019-06-27 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - WEST | 2623 | 19720189100 |  | 100281477 |  | ER VALVE |  |  |  | 566 | EX | PAPAER ABANDON ONLY | 2621P | BROADWAY | 418 N BROADWAY ST | 209 | GEO | 2019-06-27 | BBRIGHT | BBRIGHT | 2019-06-27 | 2019-06-27 |  |  | BBRIGHT | 2019-06-27 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1
KY | KY - EAST | 2631 | 19720191700 |  | 100255662 |  | 7348264G | 1859009 |  |  | 565 | EX | REPLACE SL W/18026843700 | 2600B | MEADE | 1513 MEADE ST | 089 | FLA | 2019-06-27 | U125566 | U131066 | 2019-06-27 | 2019-12-31 |  |  | DAVID SKAGGS | 2019-06-27 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 790.13 | 0 | 0 | 0 | 790.13 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572284400 |  | 100280027 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | STRATHMORE | 312 STRATHMORE DR | 073 | FRA | 2019-07-09 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-06-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19026873600 |  |  |  | 7352260A | 1852140 | BKSLONE |  | 561 | EX | INSTALL 24'-4" PMIP | 2600B | KENWOOD | KENWOOD DR | 089 | RUS | 2019-07-09 | U124014 | BKSLONE | 2019-04-26 | 2019-07-17 | 2019-07-19 | 2019-06-27 | ORA SLONE | 2019-06-28 | 2019-06-26 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00561 | 3200561 |  |  | WP8736 |  |  | 100 | 056132190268736 | 40.3 | 180 | 22926.06 | 2324.93 | 688.75 | 628.4 | 16257.07 | 0 | 4.25 | 3022.66 | 36
KY | KY - EAST | 2631 | 19026873700 |  |  |  | 7352260A | 1852140 | BKSLONE |  | 562 | EX | RETIRE 20'-4" PIP | 2600B | KENWOOD | KENWOOD DR | 089 | RUS | 2019-07-09 | U124014 | BKSLONE | 2019-04-26 | 2019-07-19 | 2019-07-19 | 2019-06-27 | ORA SLONE | 2019-06-28 | 2019-06-28 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00562 | 3200562 |  |  | WP8737 |  |  | 100 | 056232190268737 | 0.13333 | 0 | 11.6 | 9.23 | 0 | 2.37 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678772400 |  | 100299186 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 207 BURKE RD | 067 | LEX | 2019-06-28 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.55 | 1 | 1703.22 | 149.37 | 0 | 44.63 | 1509.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678773300 |  | 100299180 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 231 BURKE RD | 067 | LEX | 2019-06-28 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-28 | 2019-06-28 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.6833 | 1 | 1790.31 | 216.42 | 0 | 64.67 | 1509.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678773800 |  | 100299153 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 244 BURKE RD | 067 | LEX | 2019-06-28 | U126532 | U131066 | 2019-02-01 | 2019-11-27 |  |  | LSHARON | 2019-06-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.36667 | 1 | 2519.18 | 22.35 | 0 | 6.68 | 2490.15 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678789000 |  | 100299201 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | MEADOWTHORPE | 1538 MEADOWTHORPE AV | 067 | LEX | 2019-06-28 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-06-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.55 | 1 | 2778.85 | 149.98 | 0 | 44.81 | 2584.06 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687830500 |  | 100280011 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | STRATHMORE | 326 STRATHMORE DR | 073 | FRA | 2019-07-09 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-06-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19720456800 |  | 100317509 |  | 6716204J |  |  |  | 565 | EX | REPLACE SERV LINE | 2621P | NORTHAMPTON | 3811 NORTHAMPTON DR | 067 | LEX | 2019-06-28 | JWCOX | U129939 | 2019-06-28 | 2019-06-28 | 2019-06-28 |  | JWCOX | 2019-06-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.2333 | 2 | 2339.68 | 191.03 | 316.54 | 11.08 | 1821.03 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671924900 |  | 100353680 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 9 W 2ND ST | 161 | MAY | 2019-07-01 | U126286 | U131066 | 2019-01-22 | 2019-11-27 |  |  | TYLER ALLISON | 2019-07-01 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1361.32 | 0 | 0 | 0 | 1361.32 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671925000 |  | 100353681 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 11 W 2ND ST | 161 | MAY | 2019-07-01 | U126286 | U131066 | 2019-01-22 | 2019-11-27 |  |  | TYLER ALLISON | 2019-07-01 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1547.7 | 0 | 0 | 0 | 1547.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673608100 |  | 100310470 |  | 6712208L | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2889 CLAYS MILL RD | 067 | LEX | 2019-07-01 | U461439 | U131066 | 2019-01-30 | 2019-11-27 |  |  | A PARRIS | 2019-07-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.5333 | 1 | 2370.76 | 152.63 | 239.08 | 48.61 | 1930.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678788700 |  | 100299204 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | MEADOWTHORPE | 1526 MEADOWTHORPE AV | 067 | LEX | 2019-07-02 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-07-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.016667 | 1 | 1802.33 | 0.63 | 0 | 0.19 | 1801.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678788900 |  | 100299202 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | MEADOWTHORPE | 1534 MEADOWTHORPE AV | 067 | LEX | 2019-07-01 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-07-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.9 | 1 | 1374.51 | 245.41 | 0 | 75.31 | 1053.79 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19685901600 |  | 100241873 |  | 7356256P | 1859020 |  |  | 565 | EX | RPLC SL/18026844201/ | 2600B | WILLIAMS | 4909 WILLIAMS AV | 019 | ASH | 2019-07-03 | U125573 | U131066 | 2019-03-04 | 2019-11-27 |  |  | BCOFER | 2019-07-01 |  | 2019-06-28 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 3775.35 | 32.75 | 0 | 10.64 | 3731.96 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687830600 |  | 100279976 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | STRATHMORE | 327 STRATHMORE DR | 073 | FRA | 2019-07-09 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1401.99 | 0 | 0 | 0 | 1401.99 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687830900 |  | 100280009 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | STRATHMORE | 330 STRATHMORE DR | 073 | FRA | 2019-07-09 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1246.27 | 0 | 0 | 0 | 1246.27 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19695722300 |  | 100273110 |  | 6680224H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D193622 | 2621P | BELLWOOD | 210 BELLWOOD CT | 073 | FRA | 2019-07-02 | U125208 | U125208 | 2019-04-09 | 2019-10-09 | 2021-04-30 |  | BJLONE | 2019-07-01 | 2019-06-24 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.0667 | 3 | 2822.28 | 441.57 | 0 | 140.27 | 2240.44 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19718695600 |  | 500249662 |  | 6744208I |  |  |  | 566 | EX | ABANDON / DEMO / IDLE | 2621P | BY PASS | 1060 BY PASS RD | 049 | WIN | 2019-07-02 | U125208 | U125208 | 2019-06-26 | 2019-07-01 |  |  | DBANKS | 2019-07-01 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 30.2333 | 4 | 1522.39 | 1424.87 | 10.62 | 86.9 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19720842000 |  | 100461865 |  | 6764176I |  |  |  | 565 | EX | REPLACE SERVICE LINE - D097387 | 2621P | CEDAR GROVE | 877 CEDAR GROVE RD | 065 | IRV | 2019-07-02 | U125208 | U129939 | 2019-07-01 | 2019-06-28 | 2019-06-28 |  | DENNING | 2019-07-01 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 24.9333 | 4 | 671.74 | 433.84 | 211.5 | 26.4 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 08727615500 |  | 100241995 | 29 | 7344168H |  |  |  | 566 | EX | ABANDON/ IDLE 48MO/ RI 04-2008 | 2621P | LAKE | 2956 S LAKE DR | 071 | LNC | 2019-07-05 | U128293 | DHANSFO | 2008-04-16 | 2019-07-18 |  |  | JCKIRK | 2019-07-02 | 2019-01-28 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 13.65 | 4 | 1186.13 | 828.95 | 95.42 | 261.76 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 12988701000 |  | 100240369 |  | 7352260A |  |  |  | 566 | EX | ABANDON / RA 09-13-2011 | 2621P | POLLITT | 105 POLLITT RD | 089 | RUS | 2019-07-02 | U124015 | U125208 | 2012-09-18 | 2018-08-27 |  |  | ORA SLONE | 2019-07-02 | 2018-08-09 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 7.9167 | 5 | 1341.63 | 438.38 | 0 | 237.37 | 665.88 | 0 | 0 | 0
KY | KY - EAST | 2633 | 18026768600 |  |  |  | 7344168H | 1852308 | U122858 |  | 557 | EX | INSTALL 1402'-2"&4" PMIP | 2600B | KY RT 1428 | KY RT 1428 | 071 | LNC | 2019-07-23 | U462463 | U131369 | 2018-04-19 | 2019-12-04 | 2019-12-31 | 2019-05-06 | MARCUS BLANKENSHIP | 2019-07-02 | 2019-04-01 |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00557 | 3200557 |  |  | WP7686 | AMRCB |  | 100 | 055732180267686 | 474.0667 | 77636 | 190345.26 | 29238.05 | 7242.49 | 8852.08 | 119736.28 | 0 | 639.28 | 24637.08 | 1493
KY | KY - EAST | 2633 | 18026768700 |  |  |  | 7344168H | 1852308 | U122858 |  | 558 | EX | RETIRE 2604' BSIP | 2600B | KY RT 1428 | KY RT 1428 | 071 | LNC | 2019-07-23 | U462463 | U131369 | 2018-04-19 | 2019-12-31 | 2019-12-31 | 2019-07-01 | MARCUS BLANKENSHIP | 2019-07-02 |  |  | B | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00558 | 3200558 |  |  | WP7687 | AMRCB |  | 100 | 055832180267687 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671924800 |  | 100353678 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 3 W 2ND ST | 161 | MAY | 2019-07-02 | U126286 | U131066 | 2019-01-22 | 2019-11-27 |  |  | TYLER ALLISON | 2019-07-02 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1020.09 | 0 | 0 | 0 | 1020.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678773100 |  | 100299149 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 224 BURKE RD | 067 | LEX | 2019-07-02 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-07-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1 | 1 | 1475.76 | 62.92 | 0 | 19.3 | 1393.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678773600 |  | 100299178 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 239 BURKE RD | 067 | LEX | 2019-07-03 | U126603 | U131066 | 2019-02-01 | 2019-04-30 |  |  | SHAWN DENNIS | 2019-07-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2160.74 | 0 | 0 | 0 | 2160.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678775100 |  | 100299161 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 276 BURKE RD | 067 | LEX | 2019-07-02 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-07-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.0667 | 1 | 1843.09 | 255.45 | 0 | 78.42 | 1509.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678787800 |  | 100433224 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | MEADOWTHORPE | 1462 MEADOWTHORPE AV L | 067 | LEX | 2019-07-02 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-07-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.45 | 1 | 1671.75 | 219 | 0 | 67.21 | 1385.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678788000 |  | 100299090 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | MEADOWTHORPE | 1474 MEADOWTHORPE AV | 067 | LEX | 2019-07-02 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-07-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1116.39 | 0 | 0 | 0 | 1116.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678788100 |  | 100299089 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | MEADOWTHORPE | 1476 MEADOWTHORPE AV | 067 | LEX | 2019-07-02 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-07-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1053.79 | 0 | 0 | 0 | 1053.79 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687831000 |  | 100279978 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | STRATHMORE | 333 STRATHMORE DR | 073 | FRA | 2019-07-09 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687831100 |  | 500035955 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | STRATHMORE | 335 STRATHMORE DR | 073 | FRA | 2019-07-09 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689091500 |  | 100255655 |  | 7348264H | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | MEADE | 1416 MEADE ST | 089 | FLA | 2019-07-02 | U125566 | U131066 | 2019-03-18 | 2019-11-27 |  |  | DAVID SKAGGS | 2019-07-02 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 790.13 | 0 | 0 | 0 | 790.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19716520100 |  | 100466676 |  | 6716204L |  |  |  | 566 | EX | DEMO / ABANDON / RI 06-27-19 | 2621P | TATES CREEK CENTRE | 4161 TATES CREEK CENTRE DR | 067 | LEX | 2019-07-02 | JWCOX | U125208 | 2019-06-21 | 2019-07-19 | 2019-07-21 |  | JWCOX | 2019-07-02 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.4 | 2 | 1097.81 | 217.47 | 1.38 | 13.24 | 865.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19717215700 |  | 100297854 |  | 6716212H |  |  |  | 566 | EX | DEMO / ABANDON / RI 6-27-19 | 2621P | MARYLAND | 541< MARYLAND AV | 067 | LEX | 2019-07-05 | U128293 | U125208 | 2019-06-25 | 2019-07-16 |  |  | JWCOX | 2019-07-02 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 19717219000 |  | 100297853 |  | 6716212H |  |  |  | 566 | EX | DEMO / ABANDON / RA 6-28-19 | 2621P | MARYLAND | 541 MARYLAND AV | 067 | LEX | 2019-07-05 | U128293 | U125208 | 2019-06-25 | 2019-07-16 |  |  | JWCOX | 2019-07-02 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.8 | 2 | 1222.68 | 335.16 | 1.38 | 20.42 | 865.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19721267100 |  | 100323172 |  | 6716208P |  |  |  | 565 | EX | REPLACE SERV - D221532 D221602 | 2621P | SHERWOOD | 746 SHERWOOD DR | 067 | LEX | 2019-07-18 | U125208 | U131367 | 2019-07-02 |  |  |  | JWCOX | 2019-07-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.15 | 3 | 5769.03 | 518.2 | 292.28 | 253.23 | 4705.32 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19721316800 |  | 100340687 |  | 6736180C |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | GILBERT | 551 GILBERT DR | 151 | RIC | 2019-07-02 | DENNING | U131367 | 2019-07-02 | 2019-07-02 | 2019-07-02 |  | DENNING | 2019-07-02 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 21.7333 | 4 | 747.57 | 402.75 | 317.24 | 27.58 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18026790300 |  | 501247734 |  | 6712204K | 1854993 | U461383 |  | 555 | EX | INSTALL 350' OF 2"PMMP MAIN | 2600B | MILL RIDGE | MILL RIDGE RD LT1C | 067 | LEX | 2019-07-23 | U123258 | U461383 | 2018-08-22 | 2019-07-01 | 2019-07-03 | 2019-07-02 | DDAVIS | 2019-07-03 | 2019-06-28 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP7903 |  |  | 100 | 055532180267903 | 47.4833 | 2430 | 18094.74 | 2892.32 | 699.62 | 633.86 | 11436.43 | 0 | 54.41 | 2378.1 | 405
KY | KY - EAST | 2631 | 18026844201 |  |  |  | 7356256P | 1859020 | BKSLONE |  | 557 | EX | INSTALL 1619'-4"/2" PMLP | 2600B | WILLIAMS | WILLIAMS AV | 019 | ASH | 2019-07-25 | U462463 | BKSLONE | 2019-02-28 | 2019-10-22 | 2019-12-31 | 2019-05-16 | BCOFER | 2019-07-03 | 2019-04-01 | 2019-04-02 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP8442 | AMRCB |  | 100 | 055732180268442 | 574.4667 | 108004 | 246337.53 | 33287.63 | 18837.78 | 10325.37 | 154340.9 | 0 | 554.14 | 28991.71 | 1742
KY | KY - EAST | 2631 | 18026844301 |  |  |  | 7356256P | 1859020 | BKSLONE |  | 558 | EX | RETIRE 1195'-4"/3" BS/CSLP | 2600B | WILLIAMS | WILLIAMS AV | 019 | ASH | 2019-07-25 | U462463 | BKSLONE | 2019-02-28 | 2019-12-31 | 2019-12-31 | 2019-07-02 | BCOFER | 2019-07-03 |  | 2019-07-02 | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP8443 | AMRCB |  | 100 | 055832180268443 |  | 0 | 1626.33 | 0 | 0 | 0 | 1626.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026879500 |  | 501229851 |  | 6724212M | 1964318 | U130604 |  | 555 | EX | INSTALL 900' OF 2"PMMP MAIN | 2600B | HAYMAKER | 1721 HAYMAKER AL LT90 | 067 | LEX | 2019-07-09 | U462463 | U130604 | 2019-06-04 | 2019-06-28 | 2019-07-09 | 2019-07-02 | KKOUNS | 2019-07-03 | 2019-06-25 | 2019-06-25 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP8795 |  |  | 100 | 055532190268795 | 47.25 | 4475 | 20625.19 | 2786.93 | 1371.61 | 858.49 | 12846.77 | 0 | 46.1 | 2715.29 | 895
KY | KY - CENTRAL | 2632 | 19671931500 |  | 100353658 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | MARKET | 124 MARKET ST | 161 | MAY | 2019-07-03 | U126286 | U131066 | 2019-01-22 | 2019-11-27 |  |  | TYLER ALLISON | 2019-07-03 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1052.22 | 0 | 0 | 0 | 1052.22 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671931700 |  | 100353657 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | MARKET | 126 MARKET ST | 161 | MAY | 2019-07-03 | U126286 | U131066 | 2019-01-22 | 2019-11-27 |  |  | TYLER ALLISON | 2019-07-03 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1059.7 | 0 | 0 | 0 | 1059.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673607200 |  | 100311734 |  | 6712208L | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2810 CLAYS MILL RD | 067 | LEX | 2019-07-03 | U461439 | U131066 | 2019-01-30 | 2019-11-27 |  |  | A PARRIS | 2019-07-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 3.2167 | 1 | 1384.98 | 194.13 | 239.08 | 57.37 | 894.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678772900 |  | 100299147 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 220 BURKE RD | 067 | LEX | 2019-07-03 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-07-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.95 | 1 | 1426.93 | 249.19 | 0 | 76.49 | 1101.25 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19685903600 |  | 100241763 |  | 7356256P | 1859020 |  |  | 566 | EX | ABANDON SL W/18026844201 | 2600B | 49TH | 316 49TH ST | 019 | ASH | 2020-09-15 | U125573 | U131066 | 2019-03-04 | 2020-12-31 |  |  | BCOFER | 2019-07-03 |  | 2019-07-03 | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 |  | 1
KY | KY - EAST | 2631 | 19689199800 |  | 100412861 |  | 7348264H | 1859009 |  |  | 565 | EX | REPLACE SL W/18026843700 | 2600B | MEADE | 1410 MEADE ST | 089 | FLA | 2019-07-03 | U125566 | U131066 | 2019-03-18 | 2019-12-31 |  |  | DAVID SKAGGS | 2019-07-03 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 949.22 | 0 | 0 | 0 | 949.22 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19696934300 |  | 100278784 |  | 6688232O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SEQUOYAH | 101 SEQUOYAH TL | 073 | FRA | 2019-07-05 | U128293 | U125208 | 2019-04-15 | 2019-10-11 | 2021-04-30 |  | BJLONE | 2019-07-03 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.6 | 2 | 1620.92 | 272.78 | 0 | 16.64 | 1331.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19713445000 |  | 100270920 |  | 6736248A |  |  |  | 566 | EX | LCB-ABN / IDLE | 2621P | ROCK QUARRY | 36 ROCK QUARRY RD | 097 | CYN | 2019-07-03 | DBANKS | U125208 | 2019-06-12 | 2019-07-03 |  |  | DBANKS | 2019-07-03 | 2019-07-02 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 21.7 | 6 | 1188.62 | 1109.15 | 11.84 | 67.63 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19717677600 |  | 100251152 |  | 7340268A |  |  |  | 566 | EX | DEMO / ABANDON / RI 07-01-19 | 2621P | MAIN | 1206 MAIN ST | 089 | GRE | 2019-07-03 | AMCCORM | U132002 | 2019-06-26 | 2019-07-26 | 2019-07-26 |  | AMCCORM | 2019-07-03 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 9.5667 | 2 | 767.63 | 564.35 | 14.32 | 188.96 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19720389200 |  | 100313157 |  | 6716208A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LAFAYETTE | 264 LAFAYETTE PY | 067 | LEX | 2019-07-05 | U128293 | U125208 | 2019-06-28 | 2019-06-28 | 2019-07-18 |  | JWCOX | 2019-07-03 | 2019-06-28 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 92.55 | 13 | 17166.02 | 4314.48 | 176.46 | 364.4 | 12310.68 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19721378000 |  | 100340735 |  | 6736180C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D097365 | 2621P | PLEASURE | 230 PLEASURE DR | 151 | RIC | 2019-07-03 | DENNING | U125208 | 2019-07-02 | 2019-07-05 | 2019-07-23 |  | DENNING | 2019-07-03 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 25.7333 | 4 | 691.61 | 447.88 | 216.49 | 27.24 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 09806616300 |  | 500321232 |  | V-804/44 |  |  |  | 566 | EX | ABANDON SL/IDLE 48MTHS 09/2011 | 2600B | MIAMI | 1209 MIAMI TL | 073 | FRA | 2019-07-08 | BJLONE | RPOLLY | 2009-10-02 | 2019-07-08 |  |  | BJLONE | 2019-07-08 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 2.1667 | 1 | 1480.57 | 136.13 | 42.27 | 8.29 | 1293.88 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671931900 |  | 100353656 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | MARKET | 128 MARKET ST | 161 | MAY | 2019-07-08 | U126286 | U131066 | 2019-01-22 | 2019-11-27 |  |  | TYLER ALLISON | 2019-07-08 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1105.79 | 0 | 0 | 0 | 1105.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678772800 |  | 100299183 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 219 BURKE RD | 067 | LEX | 2019-07-08 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-07-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.7 | 1 | 1529.38 | 295.74 | 0 | 90.77 | 1142.87 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678773000 |  | 100299182 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 223 BURKE RD | 067 | LEX | 2019-07-08 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-07-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.1333 | 1 | 2066.59 | 196.93 | 0 | 60.44 | 1809.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678790800 |  | 500325182 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | PELICAN | 317 PELICAN LN | 067 | LEX | 2019-07-08 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SAHWN DENNIS | 2019-07-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.5333 | 1 | 1785.48 | 222.76 | 0 | 68.36 | 1494.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680088600 |  | 100320202 |  | 6716208G | 1748686 |  |  | 565 | EX | REPLACE SL W/17026736100 | 2600B | SHADY | 134 SHADY LN | 067 | LEX | 2019-07-08 | U126284 | U131066 | 2019-02-07 | 2019-12-31 |  |  | JOSH PASLEY | 2019-07-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.9833 | 1 | 3798.23 | 439.95 | 0 | 135.02 | 3223.26 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687831300 |  | 100279981 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | STRATHMORE | 339 STRATHMORE DR | 073 | FRA | 2019-07-09 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-08 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687831400 |  | 100280007 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | STRATHMORE | 340 STRATHMORE DR | 073 | FRA | 2019-07-09 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-08 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687831500 |  | 100279982 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | STRATHMORE | 341 STRATHMORE DR | 073 | FRA | 2019-07-09 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-08 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2329.93 | 0 | 0 | 80 | 2249.93 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689199700 |  | 100255652 |  | 7348264H | 1859009 |  |  | 565 | EX | REPLACE SL W/18026843700 | 2600B | MEADE | 1408 MEADE ST | 089 | FLA | 2019-07-08 | U124015 | U131066 | 2019-03-18 | 2019-12-31 |  |  | ORA SLONE | 2019-07-08 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.23333 | 1 | 968.53 | 14.71 | 0 | 4.6 | 949.22 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19716899900 |  | 100247539 |  | 7352256H |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | ROOSEVELT | 2414 ROOSEVELT AV | 019 | ASH | 2019-07-08 | MCOLLET | U125208 | 2019-06-24 | 2019-07-15 |  |  | MCOLLET | 2019-07-08 | 2019-07-08 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 16 | 2 | 1730.12 | 973.74 | 215.93 | 540.45 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19722257100 |  | 100422606 |  | 6724208E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | WOODHILL | 2500 WOODHILL DR | 067 | LEX | 2019-07-10 | U128293 | U131367 | 2019-07-07 | 2019-07-08 | 2019-07-28 |  | LSTANFI | 2019-07-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.2333 | 1 | 2950.16 | 349.53 | 203.16 | 21.36 | 2376.11 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19722289600 |  | 100278627 |  | 6688232O |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | MIAMI | 1208 MIAMI TL | 073 | FRA | 2019-07-08 | BJLONE | U129005 | 2019-07-08 | 2019-10-10 | 2021-04-30 |  | BJLONE | 2019-07-08 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.8667 | 2 | 3954.43 | 243.25 | 287.14 | 14.85 | 3409.19 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19722368100 |  | 100422607 |  | 6724208E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | WOODHILL | 2502 WOODHILL DR | 067 | LEX | 2019-07-08 | LSTANFI | U129005 | 2019-07-08 | 2019-07-08 |  |  | LSTANFI | 2019-07-08 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.4167 | 1 | 2956.82 | 164.06 | 153.94 | 10.01 | 2628.81 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12983834500 |  | 500576376 |  | 6712216L | 9824778 |  |  | 566 | EX | ABANDON SERV // IDLE 24 MONTHS | 2600B | OVER | 2432 OVER DR | 067 | LEX | 2019-07-10 | U128293 | U908784 | 2012-08-10 | 2019-07-09 |  |  | LSTANFI | 2019-07-09 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.1 | 1 | 764.4 | 140.62 | 9.24 | 8.58 | 605.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678788500 |  | 100299079 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | MEADOWTHORPE | 1498 MEADOWTHORPE AV | 067 | LEX | 2019-07-09 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-07-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.25 | 1 | 2190.38 | 248.94 | 0 | 70.92 | 1870.52 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687824400 |  | 100280014 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | MAGNOLIA | 315 MAGNOLIA ST | 073 | FRA | 2019-07-09 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2479.22 | 0 | 0 | 0 | 2479.22 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687830200 |  | 500291722 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | STRATHMORE | 323 STRATHMORE DR | 073 | FRA | 2019-07-09 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1623.34 | 0 | 0 | 0 | 1623.34 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687830800 |  | 100279977 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | STRATHMORE | 329 STRATHMORE DR | 073 | FRA | 2019-07-09 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3725.98 | 0 | 0 | 0 | 3725.98 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687831200 |  | 100279980 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | STRATHMORE | 337 STRATHMORE DR | 073 | FRA | 2019-07-09 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1730.93 | 0 | 0 | 0 | 1730.93 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689199600 |  | 100422804 |  | 7348264H | 1859009 |  |  | 565 | EX | REPLACE SL W/18026843700 | 2600B | MEADE | 1406 MEADE ST | 089 | FLA | 2019-07-09 | U124015 | U131066 | 2019-03-18 | 2019-12-31 |  |  | ORA SLONE | 2019-07-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.26667 | 1 | 1740.21 | 17.18 | 0 | 5.37 | 1717.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691664700 |  | 100328441 |  | 6720208B | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | CLINTON | 301 CLINTON RD | 067 | LEX | 2019-07-09 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-07-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1099.93 | 0 | 0 | 0 | 1099.93 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19705033800 |  | 100260110 |  | 7356256A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HILTON | 1628 HILTON AV | 019 | ASH | 2019-07-09 | MCOLLET | U125208 | 2019-05-10 | 2019-11-08 | 2021-05-31 |  | MCOLLET | 2019-07-09 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 19.35 | 2 | 2272.66 | 1244.69 | 135.67 | 892.3 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19717838500 |  | 100274943 |  | 6684228K | 1964663 |  |  | 565 | EX | NBT - SL/MTR UPGRADE | 2621P | MAIN | 109 W MAIN ST | 073 | FRA | 2019-07-17 | U125208 | U125208 | 2019-06-26 | 2019-06-24 | 2019-07-23 |  | BJLONE | 2019-07-09 | 2019-07-03 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 11.7 | 3 | 5855.68 | 719.09 | 121.32 | 43.87 | 4971.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 05612327800 |  | 100313551 |  | 6716208B |  |  |  | 566 | EX | ABANDON SERVICE | 2600B | HERON | 1576 HERON LN | 067 | LEX | 2019-07-16 | U125208 | SSUTHER | 2005-05-27 | 2019-07-10 |  |  | MCRAIG | 2019-07-10 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.2833 | 2 | 533.35 | 412.68 | 95.51 | 25.16 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026856200 |  |  |  | 6716212N | 1960652 | U122858 |  | 561 | EX | INSTALL 630'-2" PMMP | 2600B | HARRODSBURG | HARRODSBURG RD | 067 | LEX | 2019-07-19 | U462463 | U122858 | 2019-01-15 | 2019-06-13 | 2019-06-30 | 2019-07-05 | JAMIE LYNN | 2019-07-10 | 2019-04-15 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP8562 |  |  | 100 | 056132190268562 | 135.0333 | 13398 | 71454.45 | 7276.08 | 2991.99 | 2301.9 | 49752.68 | 0 | 39.11 | 9092.69 | 609
KY | KY - WEST | 2621 | 19026856300 |  |  |  | 6716212N | 1960652 | U122858 |  | 562 | EX | RETIRE 400'-2" PMMP | 2600B | HARRODSBURG | HARRODSBURG RD | 067 | LEX | 2019-07-18 | U462463 | U122858 | 2019-01-15 | 2019-06-28 | 2019-06-30 | 2019-07-05 | JAMIE LYNN | 2019-07-10 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP8563 |  |  | 100 | 056232190268563 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19026861900 |  | 501260029 |  | 6712228K | 1961391 | U461383 |  | 555 | EX | INSTALL 250' OF 2"/4"PMMP | 2600B | QUALITY | 201 QUALITY DR | 209 | GEO | 2019-07-12 | U462463 | U461383 | 2019-02-12 | 2019-06-13 | 2019-07-03 | 2019-07-10 | WGRAVES | 2019-07-10 | 2019-06-28 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP8619 |  |  | 100 | 055532190268619 | 57.8333 | 1760 | 18936.14 | 3388.27 | 921.16 | 1090 | 11001.71 | 0 | 42.02 | 2492.98 | 220
KY | KY - WEST | 2621 | 19026868400 |  |  |  | 6716216P | 1425507 | BKSLONE |  | 561 | EX | INSTALL 70'-2" CSHP TO R-1222 | 2600B | NANDINO | 968 NANDINO BV REAR | 067 | LEX | 2019-07-12 | U462463 | BKSLONE | 2019-03-29 | 2019-08-26 | 2019-12-31 | 2019-07-09 | JOHN SMITH | 2019-07-10 | 2019-06-26 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3207513 |  |  | WP8684 |  |  | 100 | 751332190268684 | 33.4333 | 375 | 43675.52 | 2386.74 | 1420.51 | 786.83 | 33954.53 | 0 | 35.72 | 5091.19 | 75
KY | KY - WEST | 2621 | 19678779500 |  | 100299051 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | FORBES | 1491 N FORBES RD | 067 | LEX | 2019-07-10 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-07-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1412.58 | 0 | 0 | 0 | 1412.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678789500 |  | 100299197 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | MEADOWTHORPE | 1554 MEADOWTHORPE AV | 067 | LEX | 2019-07-10 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-07-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 957.15 | 0 | 0 | 0 | 957.15 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678798100 |  | 100299163 |  | 6716216N | 1855322 |  |  | 565 | EX | REPLACE SL W/18026792400 | 2600B | BURKE | 284 BURKE RD | 067 | LEX | 2019-07-10 | U126603 | U131066 | 2019-02-01 | 2019-12-31 |  |  | SHAWN DENNIS | 2019-07-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1412.58 | 0 | 0 | 0 | 1412.58 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19685874600 |  | 100247889 |  | 7364188A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MAIN | 126 E MAIN ST | 159 | INE | 2019-07-11 | U128293 | U125208 | 2019-03-04 | 2019-07-10 | 2019-07-10 |  | JCKIRK | 2019-07-10 | 2019-07-10 |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 37.9167 | 4 | 3550.81 | 2373.34 | 259.25 | 337.54 | 580.68 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689091400 |  | 100255647 |  | 7348264H | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | MEADE | 1321 MEADE ST | 089 | FLA | 2019-07-10 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-07-10 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.25 | 1 | 1080.94 | 15.93 | 0 | 4.99 | 1060.02 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689197600 |  | 100255648 |  | 7348264H | 1859009 |  |  | 565 | EX | REPLACE SL W/18026843700 | 2600B | MEADE | 1325 MEADE ST | 089 | FLA | 2019-07-10 | U124015 | U131066 | 2019-03-18 | 2019-12-31 |  |  | ORA SLONE | 2019-07-10 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 1.4167 | 2 | 1150.59 | 81.73 | 0 | 8.84 | 1060.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691674700 |  | 100326695 |  | 6720208B | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1520 FONTAINE RD | 067 | LEX | 2019-07-10 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-07-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1676 | 0 | 0 | 0 | 1676 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703186600 |  | 100279986 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 288 HIGHLAND PY | 073 | FRA | 2019-08-26 | U461375 | U131066 | 2019-05-03 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703186700 |  | 100279985 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 290 HIGHLAND PY | 073 | FRA | 2019-08-26 | U461375 | U131066 | 2019-05-03 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703186800 |  | 100279984 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 292 HIGHLAND PY | 073 | FRA | 2019-08-26 | U461375 | U131066 | 2019-05-03 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703187000 |  | 100280008 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 319 HIGHLAND PY | 073 | FRA | 2019-08-26 | U461375 | U131066 | 2019-05-03 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2293.54 | 0 | 0 | 0 | 2293.54 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19721735600 |  | 100340752 |  | 6736180C |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | DEE DEE | 1209 DEE DEE DR | 151 | RIC | 2019-07-10 | DBANKS | U131172 | 2019-07-03 | 2019-07-05 | 2019-07-23 |  | DBANKS | 2019-07-10 | 2019-07-10 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 16.25 | 3 | 1990.43 | 1013.73 | 161.69 | 61.83 | 753.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19722352900 |  | 100316352 |  | 6716208F |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SOUTHPORT | 90 SOUTHPORT DR | 067 | LEX | 2019-07-11 | U125964 | U131723 | 2019-07-08 | 2019-07-08 | 2019-07-08 |  | LSTANFI | 2019-07-10 | 2019-07-09 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 27.9167 | 6 | 13818.44 | 1845.92 | 143.65 | 445.85 | 11383.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19722686400 |  | 100318783 |  | 6716204B |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BRIGADOON | 2910 BRIGADOON PY | 067 | LEX | 2019-07-10 | JWCOX | U131723 | 2019-07-09 | 2019-07-09 | 2019-07-09 |  | JWCOX | 2019-07-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.9333 | 1 | 3072.18 | 247.24 | 386.03 | 15.07 | 2423.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19722688000 |  | 100318717 |  | 6716204B |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BRIGADOON | 2911 BRIGADOON PY | 067 | LEX | 2019-07-10 | JWCOX | U131723 | 2019-07-09 | 2019-07-09 | 2019-07-09 |  | JWCOX | 2019-07-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.5667 | 1 | 2419.14 | 100.31 | 319.84 | 6.12 | 1992.87 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19722702100 |  | 100318819 |  | 6716204B |  |  |  | 565 | EX | GRADE 1 SL RERUN | 2621P | TARTAN | 160 TARTAN DR | 067 | LEX | 2019-07-11 | U128293 | U131010 | 2019-07-09 | 2019-07-09 | 2019-07-09 |  | JWCOX | 2019-07-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.3833 | 1 | 1619.19 | 150.12 | 248 | 9.15 | 1211.92 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19722974200 |  | 100255646 |  | 7348264H | 1859009 |  |  | 566 | EX | ABANDON SL W/18026843700 | 2600B | MEADE | 1321< MEADE ST | 089 | FLA | 2019-07-10 | U124015 | U131066 | 2019-07-10 | 2019-12-31 |  |  | ORA SLONE | 2019-07-10 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1 | 78.8 | 0 | 0 | 0 | 78.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572288000 |  | 100279768 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 135 SUNSET DR | 073 | FRA | 2019-08-26 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-07-11 | 2019-05-21 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.7 | 3 | 1662 | 138.26 | 0 | 23.53 | 1500.21 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18572293400 |  | 100279798 |  | 6688228J | 1853312 |  |  | 565 | EX | RPLC SL W/18026776900 | 2600B | SUNSET | 195 SUNSET DR | 073 | FRA | 2019-08-26 | U461375 | U131066 | 2018-01-04 | 2019-12-31 |  |  | LARRY BROWN | 2019-07-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2687.41 | 0 | 0 | 0 | 2687.41 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671931300 |  | 100353668 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | MARKET | 121 MARKET ST | 161 | MAY | 2019-07-11 | U126286 | U131066 | 2019-01-22 | 2019-11-27 |  |  | TYLER ALLISON | 2019-07-11 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1501.72 | 0 | 0 | 0 | 1501.72 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671931400 |  | 100353671 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | MARKET | 123 MARKET ST | 161 | MAY | 2019-07-11 | U126286 | U131066 | 2019-01-22 | 2019-11-27 |  |  | TYLER ALLISON | 2019-07-11 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1218.72 | 0 | 0 | 0 | 1218.72 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671931600 |  | 100353673 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | MARKET | 125 MARKET ST | 161 | MAY | 2019-07-11 | U126286 | U131066 | 2019-01-22 | 2019-11-27 |  |  | TYLER ALLISON | 2019-07-11 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1341.52 | 0 | 0 | 0 | 1341.52 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671931800 |  | 100353676 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | MARKET | 127 MARKET ST | 161 | MAY | 2019-07-11 | U126286 | U131066 | 2019-01-22 | 2019-11-27 |  |  | TYLER ALLISON | 2019-07-11 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1553.19 | 0 | 0 | 0 | 1553.19 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671932000 |  | 100353655 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | MARKET | 130 MARKET ST | 161 | MAY | 2019-07-12 | U126286 | U131066 | 2019-01-22 | 2019-11-27 |  |  | TYLER ALLISON | 2019-07-11 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1194.25 | 0 | 0 | 0 | 1194.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678773200 |  | 100299181 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 227 BURKE RD | 067 | LEX | 2019-07-12 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-07-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.15 | 1 | 1789.05 | 198.2 | 0 | 60.82 | 1530.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678774800 |  | 100299159 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | BURKE | 268 BURKE RD | 067 | LEX | 2019-08-13 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-07-11 | 2019-07-12 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.4 | 1 | 2420.69 | 151.01 | 0 | 46.34 | 2223.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678777400 |  | 100298947 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | FORBES | 1435 N FORBES RD 13 | 067 | LEX | 2019-07-12 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-07-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2223.34 | 0 | 0 | 0 | 2223.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678779100 |  | 100299047 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400 | 2600B | FORBES | 1475 N FORBES RD | 067 | LEX | 2019-07-12 | U126603 | U131066 | 2019-02-01 | 2019-09-30 |  |  | SHAWN DENNIS | 2019-07-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.15 | 1 | 1148.35 | 72.35 | 0 | 22.21 | 1053.79 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703186300 |  | 100280006 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 283 HIGHLAND PY | 073 | FRA | 2019-08-26 | U461375 | U131066 | 2019-05-03 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1902.8 | 0 | 0 | 0 | 1902.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703186500 |  | 100279987 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 286 HIGHLAND PY | 073 | FRA | 2019-08-26 | U461375 | U131066 | 2019-05-03 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19720389700 |  | 100320070 |  | 6716208K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D093792 | 2621P | JESSELIN | 123 JESSELIN DR | 067 | LEX | 2019-07-16 | U125208 | U125208 | 2019-06-28 | 2019-06-28 | 2019-07-18 |  | JWCOX | 2019-07-11 | 2019-07-01 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.6167 | 5 | 3089.94 | 490.18 | 235.84 | 29.88 | 2334.04 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19722347900 |  | 100283008 |  | 6712228C |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | CLAYTON | 615 CLAYTON AV | 209 | GEO | 2019-07-15 | U125208 | U131723 | 2019-07-08 | 2019-08-08 | 2019-09-08 |  | BJLONE | 2019-07-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.55 | 1 | 2709.42 | 437.98 | 236.29 | 26.72 | 2008.43 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19722920900 |  | 100318710 |  | 6716204B |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | WALLACE | 101 WALLACE CT | 067 | LEX | 2019-07-16 | U125208 | U131723 | 2019-07-10 | 2019-07-12 | 2019-07-30 |  | JWCOX | 2019-07-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.8167 | 1 | 1652.88 | 114.16 | 319.85 | 6.95 | 1211.92 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19723296200 |  | 100353675 |  | 7256280L | 1747939 |  |  | 566 | VO | ABANDON SL/17026728200 | 2600B | MARKET | 127< MARKET ST A1 | 161 | MAY | 2019-07-12 |  | U131066 | 2019-07-11 | 2019-12-31 |  |  | TYLER ALLISON | 2019-07-11 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1
KY | KY - CENTRAL | 2632 | 19723296500 |  | 100353677 |  | 7256280L | 1747939 |  |  | 566 | VO | ABANDON SL/17026728200 | 2600B | MARKET | 127< MARKET ST 3RD FL | 161 | MAY | 2019-07-12 |  | U131066 | 2019-07-11 | 2019-12-31 |  |  | TYLER ALLISON | 2019-07-11 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 |  | 1
KY | KY - WEST | 2621 | 19723297100 |  | 100326690 |  | 6720208B | 1855692 |  |  | 565 | EX | REPLACE SL W/18026796400 | 2600B | FONTAINE | 1500 FONTAINE RD 1FL | 067 | LEX | 2019-07-12 | U126309 | U131066 | 2019-07-11 | 2019-12-31 |  |  | JAMIE LYNN | 2019-07-11 | 2019-07-11 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16 | 2 | 3433.07 | 921.35 | 0 | 177.14 | 2334.58 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19723386100 |  | 100318636 |  | 6716204F |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LOCH LOMOND | 111 LOCH LOMOND DR | 067 | LEX | 2019-07-16 | U125208 | U131946 | 2019-07-11 | 2019-07-10 | 2019-07-10 |  | JWCOX | 2019-07-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.85 | 1 | 3609.84 | 181.04 | 280.26 | 11.04 | 3137.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673608300 |  | 100310473 |  | 6712208L | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2897 CLAYS MILL RD | 067 | LEX | 2019-07-12 | U461439 | U131066 | 2019-01-30 | 2019-11-27 |  |  | DPAYTON | 2019-07-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1636.12 | 0 | 220.99 | 0 | 1415.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678788400 |  | 100299082 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | MEADOWTHORPE | 1492 MEADOWTHORPE AV | 067 | LEX | 2019-07-12 | U126603 | U131066 | 2019-02-01 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-07-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3435.99 | 33.16 | 0 | 6.04 | 3396.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680088700 |  | 100320205 |  | 6716208G | 1748686 |  |  | 565 | EX | REPLACE SL W/17026736100 | 2600B | SHADY | 200 SHADY LN | 067 | LEX | 2019-07-12 | U126284 | U131066 | 2019-02-07 | 2019-12-31 |  |  | JOSH PASLEY | 2019-07-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.15 | 1 | 2681.23 | 73.02 | 0 | 22.4 | 2585.81 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689091300 |  | 100255645 |  | 7348264H | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | MEADE | 1319 MEADE ST | 089 | FLA | 2019-07-12 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-07-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.25 | 1 | 1540.33 | 15.93 | 0 | 4.99 | 1519.41 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703186000 |  | 100279990 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 280 HIGHLAND PY | 073 | FRA | 2019-08-26 | U461375 | U131066 | 2019-05-03 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1246.27 | 0 | 0 | 0 | 1246.27 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703186100 |  | 100280005 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 281 HIGHLAND PY | 073 | FRA | 2019-08-26 | U461375 | U131066 | 2019-05-03 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1246.27 | 0 | 0 | 0 | 1246.27 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19723259900 |  | 100254303 |  | 7348264N |  |  |  | 565 | EX | REPLACE SERVICE | 2621P | PATTERSON | 1413 PATTERSON ST | 089 | FLA | 2019-07-12 | AMCCORM | U131168 | 2019-07-10 | 2019-07-10 | 2019-07-10 |  | AMCCORM | 2019-07-12 | 2019-07-11 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 47.6667 | 5 | 4040.35 | 2918.12 | 367.87 | 754.36 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19723726200 |  | 100317643 |  | 6716204F |  |  |  | 565 | EX | GRADE 1 REPLACE | 2621P | DARTMOUTH | 3067 DARTMOUTH DR | 067 | LEX | 2019-07-16 | U125208 | U129939 | 2019-07-12 | 2019-07-12 | 2019-07-12 |  | LSTANFI | 2019-07-12 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.3167 | 4 | 493.75 | 288.82 | 187.33 | 17.6 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19723748500 |  | 100322021 |  | 6716212P |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | TRANSYLVANIA | 407 TRANSYLVANIA PR | 067 | LEX | 2019-07-16 | U125208 | U131168 | 2019-07-12 | 2019-07-12 | 2019-07-12 |  | MCRAIG | 2019-07-12 | 2019-07-12 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 33.1667 | 3 | 1700.33 | 1333.66 | 285.31 | 81.36 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19723375700 |  | 100406904 |  | 6716204C |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | REYNOLDS | 249 E REYNOLDS RD | 067 | LEX | 2019-07-13 | JENSMIN | U129005 | 2019-07-11 | 2019-07-11 | 2019-07-11 |  | JENSMIN | 2019-07-13 | 2019-07-11 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.5333 | 5 | 14524.53 | 1299.54 | 1207.24 | 457.54 | 11560.21 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678779200 |  | 100299048 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | FORBES | 1479 N FORBES RD | 067 | LEX | 2019-07-15 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFFETT | 2019-07-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.0833 | 1 | 1214.51 | 121.02 | 0 | 39.7 | 1053.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680089100 |  | 100320208 |  | 6716208G | 1748686 |  |  | 565 | EX | REPLACE SL W/17026736100 | 2600B | SHADY | 208 SHADY LN | 067 | LEX | 2019-07-15 | U126309 | U131066 | 2019-02-07 | 2019-12-31 |  |  | JAMIE LYNN | 2019-07-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.8667 | 2 | 3812.58 | 222.3 | 0 | 42.7 | 3547.58 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687857100 |  | 100272610 |  | 6684224A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BELVOIR | 923 BELVOIR DR | 073 | FRA | 2019-07-15 | CDESPAI | U125208 | 2019-03-13 | 2019-09-13 | 2021-03-31 |  | CDESPAI | 2019-07-15 | 2019-07-03 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.4667 | 3 | 4631.3 | 705.67 | 345.21 | 777.19 | 2803.23 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689092300 |  | 100255640 |  | 7348264H | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | OSBORNE | 511 OSBORNE RD | 089 | FLA | 2019-07-15 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-07-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.23333 | 1 | 968.53 | 14.71 | 0 | 4.6 | 949.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691698000 |  | 100326625 |  | 6720208B | 1855692 |  |  | 565 | EX | REPLACE SL W/18026796400 | 2600B | FONTAINE | 1400 FONTAINE RD FURN | 067 | LEX | 2019-07-16 | U126309 | U131066 | 2019-03-27 | 2019-12-31 |  |  | JAMIE LYNN | 2019-07-15 | 2019-07-15 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.5 | 2 | 6763.04 | 201.54 | 0 | 38.72 | 6522.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19705072800 |  | 100310605 |  | 6712208L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094858 | 2621P | SEATTLE | 712 SEATTLE DR | 067 | LEX | 2019-09-19 | U128336 | U125208 | 2019-05-10 | 2019-11-08 | 2021-05-31 |  | JWCOX | 2019-07-15 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.3333 | 1 | 2206.34 | 273.14 | 325.23 | 16.66 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19723949800 |  | 100421641 |  | 6680224H |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BRIARWOOD | 226 BRIARWOOD PL | 073 | FRA | 2019-07-16 | U125208 | U131723 | 2019-07-15 | 2019-07-13 | 2019-07-13 |  | BJLONE | 2019-07-15 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 15.2833 | 4 | 1199.55 | 920.29 | 223.12 | 56.14 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19724040800 |  | 100255635 |  | 7348264H | 1859009 |  |  | 565 | EX | REPLACE W/ 18026843700 | 2600B | MEADE | 1311 MEADE ST APT G | 089 | FLA | 2019-07-15 | U124015 | U125768 | 2019-07-15 | 2049-12-31 |  |  | ORA SLONE | 2019-07-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.25 | 1 | 969.33 | 15.31 | 0 | 4.8 | 949.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19724258600 |  | 100312419 |  | 6716208F | 1749637 |  |  | 565 | EX | REPL SL W/18-0267547-00 | 2621P | SOUTHLAND | 361 SOUTHLAND DR | 067 | LEX | 2019-07-16 | HROGERS | LCHAMBE | 2019-07-16 | 2019-07-16 |  |  | MARK ROGERS | 2019-07-15 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 |  | 1 | 2193.52 | 0 | 167.25 | 0 | 2026.27 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18637684600 |  | 100282920 |  | 6712228C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094551 | 2621P | DUDLEY | 508 DUDLEY AV | 209 | GEO | 2019-07-17 | U125208 | U125208 | 2018-08-24 | 2019-01-30 | 2020-07-31 |  | CDESPAI | 2019-07-16 | 2018-11-28 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 24.7167 | 7 | 7681.81 | 1519.16 | 375.38 | 2386.37 | 3400.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671924100 |  | 100353863 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 12 E 2ND ST | 161 | MAY | 2019-07-16 | U126286 | U131066 | 2019-01-22 | 2019-11-27 |  |  | TYLER ALLISON | 2019-07-16 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1906.93 | 0 | 0 | 0 | 1906.93 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678778600 |  | 100299041 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792401 | 2600B | FORBES | 1455 N FORBES RD | 067 | LEX | 2019-07-16 | U461467 | U131066 | 2019-02-01 | 2019-09-30 |  |  | D REFFETT | 2019-07-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.0333 | 1 | 1118.29 | 60.79 | 0 | 3.71 | 1053.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678790900 |  | 500284785 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792401 | 2600B | PELICAN | 324 PELICAN LN | 067 | LEX | 2019-07-16 | U461467 | U131066 | 2019-02-01 | 2019-09-30 |  |  | D REFFETT | 2019-07-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.7167 | 1 | 1158.85 | 99.02 | 0 | 6.04 | 1053.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678791400 |  | 100299065 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792401 | 2600B | PEPPER | 227 PEPPER DR | 067 | LEX | 2019-07-16 | U461467 | U131066 | 2019-02-01 | 2019-09-30 |  |  | D REFFETT | 2019-07-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.38333 | 1 | 1791.07 | 22 | 0 | 1.33 | 1767.74 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689092000 |  | 100424467 |  | 7348624H | 1859009 |  |  | 566 | EX | ABNDN SL/18026843700 | 2600B | OSBORNE | 395 OSBORNE RD | 089 | FLA | 2019-07-16 | U124015 | U131066 | 2019-03-18 | 2019-09-30 |  |  | ORA SLONE | 2019-07-16 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.55 | 1 | 120.05 | 34.89 | 0 | 6.36 | 78.8 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689092200 |  | 100255642 |  | 7348624H | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | OSBORNE | 510 OSBORNE RD | 089 | FLA | 2019-07-16 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-07-16 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 2.3667 | 1 | 1309.78 | 146.99 | 0 | 26.81 | 1135.98 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691674000 |  | 100326689 |  | 6720208B | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1500 FONTAINE RD 1FR | 067 | LEX | 2019-07-16 | U126309 | U131066 | 2019-03-27 | 2019-11-27 |  |  | JAMIE LYNN | 2019-07-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.75 | 1 | 3064.06 | 44.33 | 0 | 8.54 | 3011.19 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703186200 |  | 100279989 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 282 HIGHLAND PY | 073 | FRA | 2019-08-26 | U461375 | U131066 | 2019-05-03 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1401.99 | 0 | 0 | 0 | 1401.99 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703186400 |  | 100279988 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 284 HIGHLAND PY | 073 | FRA | 2019-08-26 | U461375 | U131066 | 2019-05-03 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1246.27 | 0 | 0 | 0 | 1246.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19716504200 |  | 100332484 |  | 6720212M |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | BELL | 146 E BELL CT | 067 | LEX | 2019-07-17 | U125208 | U125208 | 2019-06-21 | 2019-07-15 |  |  | JENSMIN | 2019-07-16 | 2019-07-15 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.6833 | 2 | 2291.98 | 390.69 | 44.84 | 354.19 | 1502.26 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19724037700 |  | 100317609 |  | 6716204F |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | STANFORD | 3009 STANFORD DR | 067 | LEX | 2019-07-17 | U125208 | U125208 | 2019-07-15 | 2019-07-18 | 2019-08-05 |  | JWCOX | 2019-07-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.8667 | 1 | 2445.34 | 432.7 | 319.85 | 26.4 | 1666.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19724130700 |  | 100316914 |  | 6716208J | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMED D221310 | 2621D | REGENCY | 2092 REGENCY RD | 067 | LEX | 2019-07-24 | U125208 | AOC SYST | 2019-07-15 | 2019-07-18 | 2019-08-05 |  | JWCOX | 2019-07-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.3833 | 1 | 2417.42 | 87.03 | 266.27 | 5.31 | 2058.81 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19724257400 |  | 100317879 |  | 6716204G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | YALE | 405 YALE DR | 067 | LEX | 2019-07-16 | JWCOX | U125208 | 2019-07-16 | 2019-07-15 | 2019-07-15 |  | JWCOX | 2019-07-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.83333 | 1 | 1564.2 | 52.37 | 367.88 | 3.21 | 1140.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19724299600 |  | 100312410 |  | 6716208F | 1749637 |  |  | 565 | EX | RPLC SL/18026754500 | 2600B | SOUTHLAND | 305 SOUTHLAND DR | 067 | LEX | 2019-07-17 | HROGERS | U125201 | 2019-07-16 | 2019-09-30 |  |  | MARK ROGERS | 2019-07-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 1213.77 | 0 | 76.83 | 0 | 1136.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19724315100 |  | 100317842 |  | 6716204G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | TEMPLE | 3793 TEMPLE DR | 067 | LEX | 2019-07-16 | JWCOX | U129005 | 2019-07-16 | 2019-07-15 | 2019-07-15 |  | JWCOX | 2019-07-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2 | 1 | 2236.08 | 126.18 | 284.33 | 7.69 | 1817.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19724327100 |  | 100303585 |  | 6712208C |  |  |  | 565 | EX | REPLACE SERVICE LINE D221541 | 2621P | ALEXANDRIA | 2101 ALEXANDRIA DR | 067 | LEX | 2019-07-17 | U125208 | U129005 | 2019-07-16 | 2019-07-16 | 2019-07-16 |  | WHIMES | 2019-07-16 | 2019-07-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 26.9 | 4 | 2076.32 | 1228.9 | 772.43 | 74.99 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671924200 |  | 100353646 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 17 E 2ND ST | 161 | MAY | 2019-07-18 | U126286 | U131066 | 2019-01-22 | 2019-11-27 |  |  | TYLER ALLISON | 2019-07-17 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1394.86 | 0 | 0 | 0 | 1394.86 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671936300 |  | 100353647 |  | 7256280L | 1747939 |  |  | 565 | EX | REPLACE SL W/17026728200 | 2600B | 2ND | 15 E 2ND ST | 161 | MAY | 2019-07-18 | U126286 | U131066 | 2019-01-22 | 2019-12-31 |  |  | TYLER ALLISON | 2019-07-17 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1962.79 | 0 | 0 | 0 | 1962.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673607800 |  | 100310467 |  | 6712208L | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2865 CLAYS MILL RD | 067 | LEX | 2019-07-17 | U126602 | U131066 | 2019-01-30 | 2019-11-27 |  |  | DEREK PAYTON | 2019-07-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.5833 | 1 | 2508 | 338.4 | 299.61 | 20.67 | 1849.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680069900 |  | 100320203 |  | 6716208G | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 138 SHADY LN | 067 | LEX | 2019-07-18 | U126309 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JAMIE LYNN | 2019-07-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.65 | 1 | 4566.86 | 152.59 | 0 | 29.33 | 4384.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691698500 |  | 100326636 |  | 6720208B | 1855692 |  |  | 565 | EX | REPLACE SL W/18026796400 | 2600B | FONTAINE | 1406 FONTAINE RD FURN | 067 | LEX | 2019-07-18 | U126309 | U131066 | 2019-03-27 | 2019-12-31 |  |  | JAMIE LYNN | 2019-07-17 | 2019-07-17 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 6000.55 | 460.66 | 0 | 88.56 | 5451.33 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19694360300 |  | 100457218 |  | 6720204O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BIRCHAM | 3600 BIRCHAM WY | 067 | LEX | 2019-07-17 | JWCOX | U125208 | 2019-04-03 | 2019-10-02 | 2021-04-30 |  | JWCOX | 2019-07-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.8 | 1 | 2024.59 | 239.71 | 178.94 | 14.63 | 1591.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19705073200 |  | 100310523 |  | 6712208L |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | SEATTLE | 604 SEATTLE DR | 067 | LEX | 2019-07-17 | JWCOX | U125208 | 2019-05-10 | 2019-11-08 | 2021-05-31 |  | JWCOX | 2019-07-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.7 | 1 | 2298.01 | 359.55 | 325.21 | 21.94 | 1591.31 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19721315300 |  | 500415145 |  | 6764176B |  |  |  | 566 | EX | DEMO / ABANDON / RA 07-05-19 | 2621P | ENGINEER | 495< ENGINEER DR | 065 | IRV | 2019-07-17 | SDWILHO | U132002 | 2019-07-02 | 2019-08-12 | 2019-09-03 |  | SDWILHO | 2019-07-17 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.8667 | 2 | 570.5 | 537.69 | 0 | 32.81 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19722938200 |  | 500814249 |  | 6716208J | 1749637 |  |  | 565 | EX | REPLACE SL W/18026754500 | 2600B | SOUTHLAND | 173 SOUTHLAND DR CABLE | 067 | LEX | 2020-01-28 | HROGERS | U131066 | 2019-07-10 | 2019-12-31 |  |  | MARK ROGERS | 2019-07-17 | 2019-07-16 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 8.9167 | 3 | 4162.11 | 511.01 | 256.15 | 181.43 | 3213.52 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19724076400 |  | 100341900 |  | 7240216O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | QUEEN | 122 N QUEEN ST | 173 | MT | 2019-07-18 | JTOY | JTOY | 2019-07-15 | 2019-07-13 | 2019-07-13 |  | DBANKS | 2019-07-17 | 2019-07-15 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 25.7833 | 7 | 2217.34 | 1786.21 | 193.32 | 237.81 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19724305500 |  | 100282921 |  | 6712228C |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | DUDLEY | 510 DUDLEY AV | 209 | GEO | 2019-07-17 | U125208 | U129005 | 2019-07-16 | 2019-07-16 |  |  | CDESPAI | 2019-07-17 | 2019-07-16 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.76667 | 2 | 4280.14 | 50.5 | 312.99 | 83.75 | 3832.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19724376500 |  | 100317267 |  | 6716204J |  |  |  | 565 | EX | REPLACE SERVICE LINE - D221328 | 2621P | MANITOBA | 164 MANITOBA LN | 067 | LEX | 2019-07-19 | U125208 | U125208 | 2019-07-16 | 2019-07-19 | 2019-08-06 |  | WHIMES | 2019-07-17 | 2019-07-17 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.2167 | 3 | 1619.88 | 827.25 | 742.2 | 50.43 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19724410900 |  | 100332503 |  | 6720212M |  |  |  | 565 | EX | REPLACE SERVICE D193531 | 2621P | BELL | 141 W BELL CT | 067 | LEX | 2019-07-19 | U125208 | U131168 | 2019-07-16 | 2019-07-16 | 2019-07-16 |  | JENSMIN | 2019-07-17 | 2019-07-16 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.5667 | 2 | 7983.76 | 876.29 | 209.79 | 897.99 | 5999.69 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19724617500 |  | 100418822 |  | 6688228O |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | MAVERICK | 1204 MAVERICK TL | 073 | FRA | 2019-07-17 | CDESPAI | U129005 | 2019-07-17 | 2019-07-17 |  |  | CDESPAI | 2019-07-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.2 | 2 | 4052.83 | 401.08 | 178.94 | 665.68 | 2807.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19724617600 |  | 100318129 |  | 6716204G |  |  |  | 565 | EX | REPLACE SERVICE LINE - D221311 | 2621P | KING ARTHUR | 3629 KING ARTHUR DR | 067 | LEX | 2019-07-19 | U125208 | U125208 | 2019-07-17 | 2019-07-19 | 2019-08-06 |  | JNEWSOM | 2019-07-17 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.0333 | 2 | 1311.74 | 1014.39 | 235.54 | 61.81 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19724691500 |  | 100317990 |  | 6716204G |  |  |  | 565 | EX | REPLACE SERVICE LINE - D221331 | 2621P | GAWAINE | 383 GAWAINE DR | 067 | LEX | 2019-07-18 | U125208 | U125208 | 2019-07-17 | 2019-07-17 | 2019-07-17 |  | WHIMES | 2019-07-17 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.7833 | 3 | 909.06 | 856.78 | 0 | 52.28 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673606900 |  | 100311736 |  | 6712208L | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2802 CLAYS MILL RD | 067 | LEX | 2019-07-18 | U126602 | U131066 | 2019-01-30 | 2019-11-27 |  |  | DEREK PAYTON | 2019-07-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.8 | 1 | 2348.79 | 230.06 | 255.36 | 14.05 | 1849.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678778800 |  | 100299043 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | FORBES | 1463 N FORBES RD | 067 | LEX | 2019-07-18 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-07-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.4 | 1 | 1736.07 | 23.16 | 0 | 7.6 | 1705.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678778900 |  | 100299044 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | FORBES | 1467 N FORBES RD | 067 | LEX | 2019-07-18 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-07-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.8167 | 1 | 1269.91 | 162.71 | 0 | 53.41 | 1053.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678779400 |  | 100299054 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | FORBES | 1490 N FORBES RD | 067 | LEX | 2019-07-18 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-07-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.7 | 1 | 1107.65 | 40.56 | 0 | 13.3 | 1053.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678790400 |  | 500325180 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | PELICAN | 309 PELICAN LN | 067 | LEX | 2019-07-18 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-07-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.0167 | 1 | 1627.14 | 59.65 | 0 | 19.57 | 1547.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678790700 |  | 500325185 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | PELICAN | 316 PELICAN LN | 067 | LEX | 2019-07-18 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-07-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.2833 | 1 | 1383 | 247.86 | 0 | 81.35 | 1053.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680069700 |  | 500251622 |  | 6716208G | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 129 SHADY LN | 067 | LEX | 2019-07-18 | U126309 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JAMIE LYNN | 2019-07-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.1167 | 1 | 2693.02 | 294.27 | 0 | 56.57 | 2342.18 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689092100 |  | 100255639 |  | 7348624H | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | OSBORNE | 507 OSBORNE RD | 089 | FLA | 2019-07-18 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-07-18 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 2.7167 | 1 | 1852.94 | 168.77 | 0 | 30.78 | 1653.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691673300 |  | 100326630 |  | 6720208B | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1404 FONTAINE RD | 067 | LEX | 2019-07-18 | U126309 | U131066 | 2019-03-27 | 2019-11-27 |  |  | JAMIE LYNN | 2019-07-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.23333 | 1 | 2141.21 | 13.82 | 0 | 2.66 | 2124.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19722314900 |  | 100302671 |  | 6712212L | 1964881 |  |  | 565 | EX | SERVICE LINE/METER UPGRADE | 2621P | VERSAILLES | 2205 VERSAILLES RD | 067 | LEX | 2019-07-24 | U125208 | U131723 | 2019-07-08 | 2019-07-03 | 2019-07-25 |  | ATWILLI | 2019-07-18 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 55.75 | 5 | 3173.34 | 2940.41 | 53.72 | 179.21 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19722921500 |  | 100340878 |  | 6736192J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | RUTH | 213 RUTH DR | 151 | RIC | 2019-07-18 | DBANKS | U131723 | 2019-07-10 | 2019-07-12 | 2019-07-30 |  | DBANKS | 2019-07-18 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 23.6 | 3 | 1648.12 | 1408.49 | 153.68 | 85.95 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19724715400 |  | 100318344 |  | 6716204G |  |  |  | 565 | EX | REPLACE SERVICE LINE - D221332 | 2621P | BROOKVIEW | 3530 BROOKVIEW DR | 067 | LEX | 2019-07-24 | U125208 | U125208 | 2019-07-17 | 2019-07-19 | 2019-08-07 |  | ASNICHO | 2019-07-18 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.7 | 2 | 979.24 | 922.95 | 0 | 56.29 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19724716200 |  | 100318219 |  | 6716204C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D221330 | 2621P | GREENLAWN | 3448 GREENLAWN DR | 067 | LEX | 2019-07-24 | U125208 | U125208 | 2019-07-17 | 2019-07-19 | 2019-08-07 |  | WHIMES | 2019-07-18 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.85 | 2 | 781.44 | 736.52 | 0 | 44.92 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19725087000 |  | 100283406 |  | 6712228F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D221351 | 2621P | POCAHONTAS | 208 POCAHONTAS TL | 209 | GEO | 2019-07-18 | CDESPAI | U125208 | 2019-07-18 | 2019-07-17 | 2019-07-17 |  | CDESPAI | 2019-07-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.3 | 1 | 3132.09 | 343.5 | 311.14 | 570.13 | 1907.32 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19725087600 |  | 100283465 |  | 6712228F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D221352 | 2621P | POCAHONTAS | 209 POCAHONTAS TL | 209 | GEO | 2019-07-18 | CDESPAI | U125208 | 2019-07-18 | 2019-07-17 | 2019-07-17 |  | CDESPAI | 2019-07-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.0167 | 1 | 2959.43 | 324.09 | 279.54 | 537.92 | 1817.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19725095500 |  | 100312414 |  | 6716208F | 1749637 |  |  | 565 | EX | REPL W/18-0267547-00 | 2621P | SOUTHLAND | 349 SOUTHLAND DR | 067 | LEX | 2019-07-19 | HROGERS | LCHAMBE | 2019-07-18 | 2019-07-18 |  |  | MARK ROGERS | 2019-07-18 | 2019-07-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 8 | 1 | 2743.06 | 456.54 | 134.13 | 88.3 | 2064.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19725112500 |  | 100326249 |  | 6708212M |  |  |  | 566 | EX | ABANDON/ SEPARATE 100326250 | 2621P | OLD VERSAILLES | 5002 OLD VERSAILLES RD | 067 | LEX | 2019-07-24 | U128336 | U125208 | 2019-07-18 | 2019-07-18 |  |  | JWCOX | 2019-07-18 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.58333 | 1 | 48.07 | 36.61 | 9.24 | 2.22 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 17505944300 |  | 100257734 |  | 7344268O | 1853404 |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | RIVERSIDE | 2103 RIVERSIDE DR | 089 | WUR | 2019-07-24 | U125573 | U125208 | 2017-05-12 | 2017-11-10 | 2019-05-31 |  | BCOFER | 2019-07-19 | 2018-04-18 | 2019-07-19 | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 19.9667 | 6 | 12661.43 | 1134.56 | 0 | 777.14 | 10749.73 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18026777900 |  |  |  | 73442680 | 1853404 | U122858 |  | 557 | EX | INSTALL 20'-6" CSHP-LEAKAGE | 2600B | RIVERSIDE | 2103 RIVERSIDE DR | 089 | WUR | 2019-08-06 | U123258 | U131042 | 2018-06-11 | 2019-07-11 | 2019-07-19 | 2019-07-18 | BCOFER | 2019-07-19 | 2019-03-19 | 2019-07-09 | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP7779 |  |  | 100 | 055732180267779 | 227.9333 | 690 | 117680.81 | 14201.62 | 10260.97 | 3572.31 | 74311.13 | 0 | 560.7 | 14774.08 | 30
KY | KY - EAST | 2631 | 18026778000 |  |  |  | 7344268O | 1853404 | U122858 |  | 558 | EX | RETIRE 10'-6" CSHP | 2600B | RIVERSIDE | RIVERSIDE | 089 | WUR | 2019-08-06 | U123258 | U131042 | 2018-06-11 | 2019-07-19 | 2019-07-19 | 2019-07-19 | BCOFER | 2019-07-19 |  | 2019-07-18 | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP7780 |  |  | 100 | 055832180267780 |  | 0 | 66.1 | 0 | 0 | 0 | 66.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026867500 |  | 100312418 |  | 6716208F | 1749637 | U122858 |  | 566 | EX | RETIRE 3" SERVICE | 2600B | SOUTHLAND | 353 SOUTHLAND DR | 067 | LEX | 2020-01-03 | HROGERS | U122858 | 2019-03-21 | 2019-12-31 | 2019-12-31 | 2019-07-19 | MARK ROGERS | 2019-07-19 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP8675 |  |  | 100 | 056632190268675 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19026873800 |  |  |  | 7348264P | 1852140 | BKSLONE |  | 561 | EX | INSTALL 223'-4' CS/PMIP | 2600B | SEATON | SEATON DR | 089 | RUS | 2019-07-29 | U123258 | BKSLONE | 2019-04-26 | 2019-07-03 | 2019-07-19 | 2019-07-18 | ROCKIE MULLINS | 2019-07-19 | 2019-07-01 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00561 | 3200561 |  |  | WP8738 | AMRCB |  | 100 | 056132190268738 | 93.8167 | 3910 | 73995.15 | 5884.96 | 4759.28 | 2131.86 | 51618.05 | 0 | 149.15 | 9451.85 | 230
KY | KY - EAST | 2631 | 19026873900 |  |  |  | 7348264P | 1852140 | BKSLONE |  | 562 | EX | RETIRE 178'-4" BS/CS/PIP | 2600B | SEATON | SEATON DR | 089 | RUS | 2019-07-29 | U123258 | BKSLONE | 2019-04-26 | 2019-07-19 | 2019-07-19 | 2019-07-18 | ROCKIE MULLINS | 2019-07-19 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00562 | 3200562 |  |  | WP8739 | AMRCB |  | 100 | 056232190268739 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671932100 |  | 100353652 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | MARKET | 132 MARKET ST | 161 | MAY | 2019-07-19 | U126286 | U131066 | 2019-01-22 | 2019-11-27 |  |  | TYLER ALLISON | 2019-07-19 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1243.81 | 0 | 0 | 0 | 1243.81 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673608000 |  | 100310469 |  | 6712208L | 1636363 | U131066 |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2881 CLAYS MILL RD | 067 | LEX | 2019-07-22 | U126602 | U131066 | 2019-01-30 | 2019-07-19 | 2021-05-31 |  | DEREK PAYTON | 2019-07-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.3333 | 1 | 2313.59 | 141.66 | 313.96 | 8.65 | 1849.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678779700 |  | 100299053 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | FORBES | 1499 N FORBES RD | 067 | LEX | 2019-07-19 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-07-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.51667 | 1 | 996.37 | 29.53 | 0 | 9.69 | 957.15 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678821400 |  | 100299050 |  | 6716216N | 1855322 |  |  | 565 | EX | REPLACE SL W/18026792400 | 2600B | FORBES | 1487 N FORBES RD | 067 | LEX | 2019-07-19 | U461467 | U131066 | 2019-02-01 | 2019-12-31 |  |  | D REFFETT | 2019-07-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.8833 | 1 | 1653.81 | 108.87 | 0 | 35.72 | 1509.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19701109900 |  | 100467140 |  | 6720200C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094822 | 2621P | ABBEYWOOD | 2260 ABBEYWOOD RD | 067 | LEX | 2019-07-24 | U125208 | U125208 | 2019-04-29 | 2019-10-25 | 2021-04-30 |  | ATWILLI | 2019-07-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.6833 | 1 | 2467.4 | 230.4 | 61.41 | 14.28 | 2161.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19725412600 |  | 100332483 |  | 6720212M |  |  |  | 565 | EX | REPLACE SERV LINE | 2621P | BELL | 140 E BELL CT | 067 | LEX | 2019-07-24 | U125208 | U129939 | 2019-07-19 | 2019-07-19 |  |  | ATWILLI | 2019-07-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 6.5 | 1 | 4983.53 | 413.86 | 167.11 | 25.26 | 4377.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19761462500 |  | 100312418 |  | 6716208F | 1749637 |  |  | 565 | EX | INSTALL 2" SERVICE | 2600B | SOUTHLAND | 353 SOUTHLAND DR | 067 | LEX | 2020-01-08 | HROGERS | U122858 | 2019-11-26 | 2019-12-31 | 2019-12-31 |  | MARK ROGERS | 2019-07-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1
KY | KY - WEST | 2621 | 19680088500 |  | 100320201 |  | 6716208G | 1748686 |  |  | 565 | EX | REPLACE SL W/17026736100 | 2600B | SHADY | 132 SHADY LN | 067 | LEX | 2019-07-22 | U126284 | U131066 | 2019-02-07 | 2019-12-31 |  |  | JOSH PASLEY | 2019-07-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.3667 | 1 | 4071.49 | 400.91 | 0 | 72.61 | 3597.97 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19699159900 |  | 100457408 |  | 6720200B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094819 | 2621P | BROADHEAD | 2168 BROADHEAD PL | 067 | LEX | 2019-07-24 | U125208 | U125208 | 2019-04-19 | 2019-07-22 | 2021-04-30 |  | JWCOX | 2019-07-22 | 2019-06-20 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.2833 | 2 | 2253.42 | 192.5 | 261.06 | 11.42 | 1788.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19701108200 |  | 100463528 |  | 6720200B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094821 | 2621P | ELMSPRING | 2309 ELMSPRING WY | 067 | LEX | 2019-07-24 | U125208 | U125208 | 2019-04-29 | 2019-10-25 | 2021-04-30 |  | JWCOX | 2019-07-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.4833 | 1 | 2657.63 | 471.81 | 185.04 | 28.8 | 1971.98 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19702888700 |  | 500498108 |  | 7356256M |  |  |  | 566 | EX | ABANDON / RI 05-10-19 / CNVRT | 2621P | BELMONT | 2914 S BELMONT ST | 019 | ASH | 2019-07-22 | MCOLLET | U132002 | 2019-05-02 | 2019-06-03 | 2019-06-18 |  | MCOLLET | 2019-07-22 | 2019-06-20 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 11.7 | 6 | 1575.06 | 706.8 | 22.36 | 587.82 | 258.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19721311800 |  | 100326250 |  | 6708212M |  |  |  | 565 | EX | SEPARATE FROM 100326249* | 2621P | OLD VERSAILLES | 4996 OLD VERSAILLES RD | 067 | LEX | 2019-07-22 | JWCOX | U125208 | 2019-07-02 | 2019-07-16 | 2019-07-16 |  | JWCOX | 2019-07-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.0667 | 1 | 3525.02 | 68.14 | 304.56 | 4.16 | 3148.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19722928300 |  | 100318694 |  | 6716204B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D193697 | 2621P | BRIGADOON | 100 BRIGADOON PY | 067 | LEX | 2019-07-24 | U125208 | U131172 | 2019-07-10 | 2019-07-12 | 2019-07-30 |  | JENSMIN | 2019-07-22 | 2019-07-15 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.0333 | 4 | 4240.23 | 457.15 | 1343.76 | 139.59 | 2299.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19725085500 |  | 100309190 |  | 6716208A |  |  |  | 566 | EX | DEMO / ABANDON / RA 07/19/19 | 2621P | LANE ALLEN | 809 LANE ALLEN RD | 067 | LEX | 2019-07-24 | U125208 | U125208 | 2019-07-18 | 2019-08-19 | 2019-08-19 |  | WHIMES | 2019-07-22 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 7.0167 | 2 | 497.78 | 439.38 | 31.6 | 26.8 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19725967700 |  | 100408465 |  | 6712224H |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | LAURIE | 108 LAURIE LN | 209 | GEO | 2019-07-22 | CDESPAI | U129005 | 2019-07-22 | 2019-07-21 | 2019-07-21 |  | CDESPAI | 2019-07-22 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 4.3 | 1 | 3171.46 | 277.53 | 9.5 | 460.59 | 2423.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673607900 |  | 100310468 |  | 6712208L | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2873 CLAYS MILL RD | 067 | LEX | 2019-07-23 | U126602 | U131066 | 2019-01-30 | 2019-11-27 |  |  | DEREK PAYTON | 2019-07-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 5.1 | 1 | 2589.15 | 308.74 | 256.3 | 18.82 | 2005.29 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680088300 |  | 100320199 |  | 6716208G | 1748686 |  |  | 565 | EX | REPLACE SL W/17026736100 | 2600B | SHADY | 128 SHADY LN | 067 | LEX | 2019-07-23 | U126284 | U131066 | 2019-02-07 | 2019-12-31 |  |  | JOSH PASLEY | 2019-07-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2489.27 | 0 | 0 | 0 | 2489.27 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689091200 |  | 100255637 |  | 7348264H | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | MEADE | 1304 MEADE ST | 089 | FLA | 2019-07-23 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-07-23 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.25 | 1 | 1596.09 | 15.93 | 0 | 4.99 | 1575.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19699830500 |  | 100465811 |  | 6716200D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D107141 | 2621P | CHARWOOD | 882 CHARWOOD DR | 067 | LEX | 2019-07-24 | U125208 | U125208 | 2019-04-23 | 2019-10-22 | 2021-04-30 |  | JWCOX | 2019-07-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1 | 1 | 2544.28 | 63.06 | 185.17 | 3.83 | 2292.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19700521900 |  | 100465395 |  | 6720200A |  |  |  | 565 | EX | REPLACE SERVICE LINE - D107145 | 2621P | STOWBRIDGE | 1096 STOWBRIDGE LN | 067 | LEX | 2019-07-24 | U125208 | U125208 | 2019-04-25 | 2019-10-24 | 2021-04-30 |  | JWCOX | 2019-07-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.65 | 1 | 2471.44 | 230.23 | 178.94 | 14.02 | 2048.25 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703185400 |  | 100279993 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 274 HIGHLAND PY | 073 | FRA | 2019-08-26 | U461375 | U131066 | 2019-05-03 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703185500 |  | 100280002 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 275 HIGHLAND PY | 073 | FRA | 2019-08-26 | U461375 | U131066 | 2019-05-03 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1776.41 | 0 | 0 | 0 | 1776.41 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703185800 |  | 100279991 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 278 HIGHLAND PY | 073 | FRA | 2019-08-26 | U461375 | U131066 | 2019-05-03 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703185900 |  | 100280004 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 279 HIGHLAND PY | 073 | FRA | 2019-08-26 | U461375 | U131066 | 2019-05-03 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19705444700 |  | 100240370 |  | 7352264M | 1852140 |  |  | 565 | EX | REPLACE SL W/19026873600 | 2600B | POLLITT | 107 POLLITT RD | 089 | RUS | 2019-07-23 | U461496 | U131066 | 2019-05-13 | 2019-12-31 |  |  | ROCKIE MULLINS | 2019-07-23 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.25 | 1 | 2310.24 | 15.31 | 0 | 4.8 | 2290.13 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19721317400 |  | 100436048 |  | 6764176B |  |  |  | 566 | EX | DEMO / ABANDON / RA 07-05-19 | 2621P | ENGINEER | 495 ENGINEER RD | 065 | IRV | 2019-07-23 | SDWILHO | U132002 | 2019-07-02 | 2019-08-12 | 2019-09-03 |  | SDWILHO | 2019-07-23 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 7.8333 | 2 | 544.21 | 484.42 | 0 | 59.79 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19722931300 |  | 100318780 |  | 6716204B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D193699 | 2621P | BRIGADOON | 2916 BRIGADOON PY | 067 | LEX | 2019-07-24 | U125208 | U131172 | 2019-07-10 | 2019-07-12 | 2019-07-30 |  | LSTANFI | 2019-07-23 | 2019-07-11 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.0833 | 2 | 2709.85 | 521.71 | 189.77 | 31.83 | 1966.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19724781000 |  | 100331073 |  | 6720212N | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER / | 2621D | PRESTON | 353 PRESTON AV | 067 | LEX | 2019-07-24 | U125208 | AOC SYST | 2019-07-17 | 2019-08-15 | 2019-09-14 |  | WHIMES | 2019-07-23 | 2019-07-22 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.0667 | 4 | 1208.24 | 975.39 | 173.37 | 59.48 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19726214600 |  | 100353860 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 6 E 2ND ST | 161 | MAY | 2019-07-23 | U126286 | U125768 | 2019-07-23 | 2049-12-31 |  |  | TYLER ALLISON | 2019-07-23 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1560.06 | 0 | 0 | 0 | 1560.06 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19726224200 |  | 100421266 |  | 6688228A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | WILLIAMSBURG | 538 WILLIAMSBURG RD | 073 | FRA | 2019-07-23 | CDESPAI | U129005 | 2019-07-23 | 2019-07-12 | 2019-07-31 |  | CDESPAI | 2019-07-23 | 2019-07-22 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.9833 | 2 | 3671.2 | 515.66 | 178.94 | 855.74 | 2120.86 | 0 | 0 | 0
KY | KY - EAST | 2631 | 07682109800 |  | 500815082 |  | 7328284-D |  |  |  | 566 | EX | ABANDON SL - IDLE 24 MONTHS | 2600B | COUNTY | 356 COUNTY RD TRAILER | 089 | S S | 2019-07-24 | MCOLLET | SSUTHER | 2007-04-06 | 2019-07-23 |  |  | MCOLLET | 2019-07-24 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 1.5333 | 1 | 218.17 | 99.37 | 9.94 | 108.86 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 12965301500 |  | 100274735 |  | 00NEW |  |  |  | 566 | EX | SOII - METER ABANDON ONLY | 2621P | 3RD | 229 W 3RD ST 2FF | 073 | FRA | 2019-07-25 | U125208 | U124967 | 2012-04-16 | 2019-07-24 |  |  | CDESPAI | 2019-07-24 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.73333 | 1 | 140.84 | 47.24 | 15.22 | 78.38 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680069500 |  | 100320198 |  | 6716208G | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 126 SHADY LN | 067 | LEX | 2019-07-24 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-07-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.4167 | 1 | 3266.6 | 404.1 | 0 | 73.17 | 2789.33 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689091100 |  | 100255636 |  | 7348264H | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | MEADE | 1302 MEADE ST | 089 | FLA | 2019-07-24 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-07-24 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.25 | 1 | 2032.13 | 15.93 | 0 | 4.99 | 2011.21 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19699149700 |  | 100460638 |  | 6720200B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094817 | 2621P | BROADHEAD | 2181 BROADHEAD PL | 067 | LEX | 2019-07-25 | U125208 | U125208 | 2019-04-19 | 2019-10-18 | 2021-04-30 |  | JWCOX | 2019-07-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.3 | 1 | 4039.32 | 208.13 | 178.94 | 12.69 | 3639.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19700522900 |  | 100462919 |  | 6720200A |  |  |  | 565 | EX | REPLACE SERVICE LINE - D107146 | 2621P | IRONBRIDGE | 4623 IRONBRIDGE DR | 067 | LEX | 2019-07-25 | U125208 | U125208 | 2019-04-25 | 2019-10-24 | 2021-04-30 |  | JWCOX | 2019-07-24 | 2019-07-23 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.85 | 2 | 2371.29 | 243.48 | 178.94 | 14.86 | 1934.01 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703185600 |  | 100279992 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 276 HIGHLAND PY | 073 | FRA | 2019-08-26 | U461375 | U131066 | 2019-05-03 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2123.54 | 0 | 0 | 0 | 2123.54 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703185700 |  | 100280003 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 277 HIGHLAND PY | 073 | FRA | 2019-08-26 | U461375 | U131066 | 2019-05-03 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1592.99 | 0 | 0 | 0 | 1592.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19725944500 |  | 100320068 |  | 6716208K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D000113 | 2621P | JESSELIN | 131 JESSELIN DR | 067 | LEX | 2019-07-30 | U461475 | U125208 | 2019-07-22 | 2019-07-24 | 2019-08-11 |  | JWCOX | 2019-07-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.5667 | 1 | 3237.71 | 520.24 | 242.07 | 31.72 | 2443.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19726226500 |  | 100312409 |  | 6716208F | 1749637 |  |  | 565 | EX | REPLACE W/ 18026754500 | 2600B | SOUTHLAND | 303 SOUTHLAND DR | 067 | LEX | 2019-07-25 | HROGERS | U125768 | 2019-07-23 | 2049-12-31 |  |  | MARK ROGERS | 2019-07-24 | 2019-07-23 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.0333 | 2 | 4324.38 | 458.32 | 166.3 | 88.66 | 3611.1 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19726237600 |  | 100274736 |  | 6684228J |  |  |  | 565 | EX | REPLACE SERVICE LINE D192976 | 2621P | 3RD | 229 W 3RD ST 1FE | 073 | FRA | 2019-08-29 | U125208 | U129005 | 2019-07-23 | 2019-07-23 | 2019-07-23 |  | CDESPAI | 2019-07-24 | 2019-07-23 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 11.6333 | 2 | 9112.69 | 946.36 | 159.89 | 1570.82 | 6435.62 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19726281000 |  | 100279496 |  | 6688224C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D192954 | 2621P | ARROYO | 1308 ARROYO DR | 073 | FRA | 2019-07-25 | U125208 | U125208 | 2019-07-23 | 2019-07-23 | 2019-07-23 |  | CDESPAI | 2019-07-24 | 2019-07-24 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 9.1667 | 1 | 4603.63 | 594.51 | 339.36 | 986.73 | 2683.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19726296400 |  | 100318532 |  | 6716204C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D221623 | 2621P | FLINTRIDGE | 3409 FLINTRIDGE CR | 067 | LEX | 2019-07-25 | U125208 | U125208 | 2019-07-23 | 2019-07-23 | 2019-07-23 |  | ATWILLI | 2019-07-24 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 32.75 | 3 | 2609.7 | 2158.06 | 320.11 | 131.53 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19726305200 |  | 100421654 |  | 6688228O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D192977 | 2621P | LAGO | 1313 LAGO DR | 073 | FRA | 2019-07-24 | CDESPAI | U125208 | 2019-07-23 | 2019-07-23 | 2019-07-23 |  | CDESPAI | 2019-07-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8.8667 | 1 | 4249.21 | 572.5 | 302.66 | 950.21 | 2423.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19726418200 |  | 100312408 |  | 6716208F | 1749637 |  |  | 565 | EX | REPLACE W/ 18026754500 | 2600B | SOUTHLAND | 301 SOUTHLAND DR | 067 | LEX | 2019-07-25 | HROGERS | U125768 | 2019-07-24 | 2049-12-31 |  |  | MARK ROGERS | 2019-07-24 | 2019-07-24 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.0333 | 2 | 1699.53 | 458.33 | 76.83 | 88.66 | 1075.71 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19726639500 |  | 100312319 |  | 6716208I |  |  |  | 565 | EX | REPLACE SERVICE LINE D093760 | 2621P | BRADFORD | 395 BRADFORD DR | 067 | LEX | 2019-07-29 | U126308 | U129005 | 2019-07-24 | 2019-11-15 | 2021-05-31 |  | JENSMIN | 2019-07-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.63333 | 1 | 4751.58 | 43.93 | 239.03 | 35.26 | 4433.36 | 0 | 0 | 0
KY | KY - EAST | 2631 | 07672818500 |  | 100255625 | 23 | 7348264H |  |  |  | 566 | EX | ABANDON COMPANY SERVICE LINE | 2600B | 1ST | 525 N 1ST ST | 089 | FLA | 2019-07-25 | U124015 | WMAY | 2007-01-17 | 2019-07-25 |  |  | ORA SLONE | 2019-07-25 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.38333 | 1 | 107.53 | 24.29 | 0 | 4.44 | 78.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678778500 |  | 100298988 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | FORBES | 1451 N FORBES RD | 067 | LEX | 2019-07-25 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-07-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.7333 | 1 | 1817.99 | 159.24 | 0 | 9.71 | 1649.04 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689091000 |  | 100255603 |  | 7348264H | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | MEADE | 1218 MEADE ST | 089 | FLA | 2019-07-25 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-07-25 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.2 | 1 | 1612.68 | 12.87 | 0 | 4.03 | 1595.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691674500 |  | 100326851 |  | 6720208B | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1515 FONTAINE RD 1 | 067 | LEX | 2019-07-25 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-07-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 7390.55 | 0 | 2217.81 | 0 | 5172.74 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703185100 |  | 500271265 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 269< HIGHLAND PY | 073 | FRA | 2019-08-26 | U461375 | U131066 | 2019-05-03 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703185300 |  | 100279994 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 272 HIGHLAND PY | 073 | FRA | 2019-08-26 | U461375 | U131066 | 2019-05-03 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19720404200 |  | 100453359 |  | 6720204D |  |  |  | 566 | EX | DEMO / ABANDON / RA 07/11/19 | 2621P | CUSTER | 3130 CUSTER DR | 067 | LEX | 2019-07-29 | U125208 | U125208 | 2019-06-28 | 2019-07-11 | 2019-07-28 |  | ASNICHO | 2019-07-25 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 8.7 | 2 | 639.12 | 584.97 | 18.5 | 35.65 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19727120700 |  | 100302435 |  | 6712212G |  |  |  | 565 | EX | REPLACE SERVICE LINE - D095357 | 2621P | DEVONPORT | 1164 DEVONPORT CR | 067 | LEX | 2019-07-29 | U125208 | U129005 | 2019-07-25 | 2019-07-26 | 2019-08-14 |  | WHIMES | 2019-07-25 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.8167 | 3 | 1694.58 | 978.83 | 181.06 | 59.69 | 475 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19727784800 |  | 100457755 |  | 6720200B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094820 | 2621P | HARTLAND | 4958 HARTLAND PY | 067 | LEX | 2019-07-30 | DMCCULL | U125208 | 2019-07-29 | 2019-10-18 | 2021-04-30 |  | JOSH COX | 2019-07-25 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 206.61 | 0 | 206.61 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 14258303900 |  | 100264085 |  | 7352256A |  |  |  | 566 | EX | ABANDON SL | 2600B | OLD BUCKLEY | 818 W OLD BUCKLEY RD | 019 | ASH | 2019-07-26 | MCOLLET | U125201 | 2014-10-17 | 2019-07-26 |  |  | MCOLLET | 2019-07-26 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 8.3833 | 2 | 948.11 | 546.27 | 0 | 401.84 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18636014900 |  | 100280001 |  | 6688228N | 1853312 |  |  | 566 | EX | ABANDON SL W/18026776900 | 2600B | HIGHLAND | 271 HIGHLAND PY | 073 | FRA | 2019-11-01 | U125208 | U126129 | 2018-08-17 | 2019-12-31 |  |  | LARRY BROWN | 2019-07-26 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1055 | 0 | 0 | 0 | 1055 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026887500 |  |  |  | 6720212M | 1965505 | BKSLONE |  | 557 | EX | INSTALL 20'-4" PMLP | 2621P | OLD PARK | 155 OLD PARK AV | 067 | LEX | 2020-01-31 | U460266 | BKSLONE | 2019-07-25 | 2019-01-16 | 2020-01-31 | 2019-07-26 | J.ENSMINGER | 2019-07-26 | 2019-07-26 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP8875 | AMRCB |  | 100 | 055732190268875 | 3.6167 | 0 | 8274.61 | 252.37 | 1681.88 | 258.57 | 5174.41 | 0 | 81.61 | 825.77
KY | KY - WEST | 2621 | 19026887600 |  |  |  | 6720212M | 1965505 | BKSLONE |  | 558 | EX | RETIRE 20'-4"/3" CS/CILP | 2621P | OLD PARK | 155 OLD PARK AV | 067 | LEX | 2020-01-24 | U460266 | BKSLONE | 2019-07-25 | 2019-07-25 | 2020-01-31 | 2019-07-26 | JENSMIN | 2019-07-26 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP8876 | AMRCB |  | 100 | 055832190268876 | 9.55 | 0 | 21826.45 | 6108.11 | 0 | 1796.26 | 13922.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678778700 |  | 100299042 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | FORBES | 1459 N FORBES RD | 067 | LEX | 2019-07-26 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-07-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.75 | 1 | 2365.91 | 101.34 | 0 | 33.25 | 2231.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19707366100 |  | 100303512 |  | 6712208C |  | U125208 |  | 565 | EX | REPLACE SERVICE LINE - D094800 | 2621P | BALSAM | 1028 BALSAM DR | 067 | LEX | 2019-08-02 | U125208 | U125208 | 2019-05-20 | 2019-11-15 | 2021-05-31 |  | JWCOX | 2019-07-26 | 2019-07-09 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.1 | 3 | 3321.71 | 509.67 | 389.05 | 31.08 | 2391.91 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19708279800 |  | 100313039 |  | 6716208E | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER / | 2621D | MITCHELL | 597 MITCHELL AV | 067 | LEX | 2019-07-26 | WHIMES | AOC SYST | 2019-05-22 | 2019-06-20 | 2019-07-20 |  | WHIMES | 2019-07-26 | 2019-07-25 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.1333 | 4 | 1317.3 | 1241.54 | 0 | 75.76 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19726842200 |  | 100353517 |  | 7256280K |  |  |  | 565 | EX | REPLACE SERVICE LINE D095091 | 2621P | 3RD | 237 W 3RD ST | 161 | MAY | 2019-08-02 | U125208 | U129005 | 2019-07-24 | 2019-07-24 | 2019-07-24 |  | SDADAMS | 2019-07-26 | 2019-07-24 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 | 39.3667 | 6 | 3186.84 | 2418.31 | 621.03 | 147.5 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19727415800 |  | 100304808 |  | 6712212L |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CELIA | 966 CELIA LN | 067 | LEX | 2019-07-26 | JWCOX | U129939 | 2019-07-26 | 2019-11-06 | 2021-05-31 |  | JWCOX | 2019-07-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.7833 | 1 | 2191.96 | 142.15 | 277.13 | 29.88 | 1742.8 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19026880900 |  |  |  | 7352256-B | 1964643 | GSULLI1 |  | 586 | EX | REMOVE DAMAGED BUILDING | 2600E | BUCKLEY | 240 BUCKLEY RD | 019 | ASH | 2019-08-05 | U462463 | GSULLI1 | 2019-06-17 | 2019-06-27 | 2019-06-30 | 2019-07-27 | JOSH MULLINS | 2019-07-27 | 2019-07-27 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00586 | 3200586 |  |  | WP8809 |  |  | 100 | 058632190268809 | 8.5 | 0 | 4223.65 | 1771.64 | 0 | 353.66 | 2098.35 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19026887700 |  |  |  | 7344240A | 1965538 | U128885 |  | 557 | EX | INSTALL 1' - 2" PMMP AS-BUILT | 2621P | STATE RT 854 | STATE RT 854 | 019 | RUS | 2019-09-24 | U460266 | U128885 | 2019-07-29 | 2019-12-23 | 2019-12-31 | 2019-07-27 | MCOLLET | 2019-07-27 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP8877 |  |  | 100 | 055732190268877 | 3.4667 | 2 | 3086.49 | 2169.16 | 128.15 | 404.22 | 0 | 0 | 5 | 379.96 | 1
KY | KY - EAST | 2631 | 19026887800 |  |  |  | 7344240A | 1965538 | U128885 |  | 558 | EX | ABANDON 1' - 2" PMMP AS-BUILT | 2621P | STATE RT 854 | STATE RT 854 | 019 | RUS | 2019-09-24 | U460266 | U128885 | 2019-07-29 | 2019-12-31 | 2019-12-31 | 2019-07-27 | MCOLLET | 2019-07-27 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP8878 |  |  | 100 | 055832190268878 | 7.0667 | 0 | 784.99 | 428.86 | 0 | 292.33 | 63.8 | 0 | 0 | 0
KY | KY - WEST | 2623 | 07671781400 |  | 100280000 |  | 6688228N | 1853312 |  |  | 566 | EX | RETIRE S/L W/18-0267769-00 | 2600B | HIGHLAND | 269 HIGHLAND PY | 073 | FRA | 2019-08-26 | U461375 | RPOLLY | 2007-01-09 | 2019-12-31 | 2019-12-31 |  | LARRY BROWN | 2019-07-29 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26230043 |  | 1 | 1055 | 0 | 0 | 0 | 1055 | 0 | 0 | 0
KY | KY - WEST | 2621 | 09816541000 |  | 100326855 |  | V-1026-28 | 1855692 |  |  | 565 | EX | REPLACE SL W/18026796400 | 2600B | FONTAINE | 1501 FONTAINE RD 1FR | 067 | LEX | 2019-07-29 | U125559 | U123173 | 2009-12-30 | 2019-12-30 |  |  | BJACKSON | 2019-07-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2204.9 | 0 | 0 | 0 | 2204.9 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11919116000 |  | 100340956 |  | 7240212B |  |  |  | 566 | EX | ABANDON COMPANY SERVICE | 2621P | MAYSVILLE | 59 S MAYSVILLE ST | 173 | MT | 2019-07-29 | DENNING | U907469 | 2011-08-05 | 2017-12-29 |  |  | DENNING | 2019-07-29 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 11.1 | 5 | 701.79 | 595.03 | 0 | 106.76 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19026868001 |  | 501258026 |  | 6680224H |  | U461383 |  | 555 | EX | INSTALL 1050' OF 2"PMMP MAIN | 2600B | HARRODSWOOD | 393 HARRODSWOOD RD | 073 | FRA | 2019-08-02 | U123258 | U461383 | 2019-07-29 | 2019-05-20 | 2019-09-01 | 2019-07-24 | WGRAVES | 2019-07-29 | 2019-07-12 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP8680 |  |  | 100 | 055532190268680 | 84.85 | 13380 | 101407.9 | 5014.2 | 1771.09 | 1619.01 | 79981.07 | 0 | 182.51 | 12840.02 | 1115
KY | KY - CENTRAL | 2632 | 19671924000 |  | 100353648 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 9 E 2ND ST | 161 | MAY | 2019-07-30 | U126286 | U131066 | 2019-01-22 | 2019-11-27 |  |  | TYLER ALLISON | 2019-07-29 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2394.91 | 0 | 0 | 0 | 2394.91 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673607700 |  | 100310466 |  | 6712208L | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2857 CLAYS MILL RD | 067 | LEX | 2019-07-30 | U461439 | U131066 | 2019-01-30 | 2019-11-27 |  |  | A PARRIS | 2019-07-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2044.27 | 0 | 239.08 | 0 | 1805.19 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678779300 |  | 100299049 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | FORBES | 1483 N FORBES RD | 067 | LEX | 2019-07-29 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-07-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.7333 | 1 | 2053.27 | 217.03 | 0 | 71.46 | 1764.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680088900 |  | 100320206 |  | 6716208G | 1748686 |  |  | 565 | EX | REPLACE SL W/17026736100 | 2600B | SHADY | 204 SHADY LN | 067 | LEX | 2019-07-29 | U126602 | U131066 | 2019-02-07 | 2019-12-31 |  |  | DEREK PAYTON | 2019-07-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.4167 | 1 | 3544.71 | 276.02 | 254.8 | 16.84 | 2997.05 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689093000 |  | 100255817 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | TURLEY | 856 TURLEY AV | 089 | FLA | 2019-07-29 | U124015 | U131066 | 2019-03-18 | 2019-07-29 |  |  | ORA SLONE | 2019-07-29 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.23333 | 1 | 1414.92 | 15.15 | 0 | 1.88 | 1397.89 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689194400 |  | 100255611 |  | 7348264H | 1859009 |  |  | 565 | EX | REPLACE SL W/18026843700 | 2600B | 1ST | 524 N 1ST ST | 089 | FLA | 2019-07-29 | U124015 | U131066 | 2019-03-18 | 2019-07-29 |  |  | ORA SLONE | 2019-07-29 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.28333 | 1 | 2008.16 | 17.01 | 0 | 2.1 | 1989.05 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19700517400 |  | 100464508 |  | 6716204L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094777 | 2621P | TATES CREEK | 4030 TATES CREEK RD 3906 | 067 | LEX | 2019-07-30 | U125208 | U125208 | 2019-04-25 | 2019-10-17 | 2021-04-30 |  | JWCOX | 2019-07-29 | 2019-07-29 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.0167 | 1 | 3777.43 | 437.55 | 540.64 | 26.66 | 2772.58 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703184800 |  | 100279997 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 266 HIGHLAND PY | 073 | FRA | 2019-08-26 | U461375 | U131066 | 2019-05-03 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-29 | 2019-07-31 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.15 | 1 | 1492.15 | 67.75 | 0 | 8.54 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703184900 |  | 100279996 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 268 HIGHLAND PY | 073 | FRA | 2019-08-26 | U461375 | U131066 | 2019-05-03 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1776.41 | 0 | 0 | 0 | 1776.41 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19725254200 |  | 100406122 |  | 6716204J | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER / | 2621D | KENLOCK | 213 KENLOCK DR | 067 | LEX | 2019-07-29 | LSTANFI | AOC SYST | 2019-07-18 | 2019-08-16 | 2019-09-16 |  | LSTANFI | 2019-07-29 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.4667 | 1 | 819.71 | 645.98 | 134.33 | 39.4 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19726594700 |  | 100340959 |  | 7240212B |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | MAYSVILLE | 29 S MAYSVILLE ST | 173 | MT | 2019-07-29 | DENNING | U125208 | 2019-07-24 | 2019-08-23 |  |  | DENNING | 2019-07-29 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 15.7833 | 5 | 1140.77 | 834.25 | 156.81 | 149.71 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19726599200 |  | 100343440 |  | 7240212B |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | MAYSVILLE | 32 S MAYSVILLE ST | 173 | MT | 2019-07-29 | DENNING | U125208 | 2019-07-24 | 2019-08-23 |  |  | DENNING | 2019-07-29 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 24.95 | 9 | 1815.88 | 1379.54 | 240.3 | 196.04 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19727738600 |  | 500284408 |  | 6692224B |  |  |  | 565 | EX | REPLACE SERVICE LINE D094154 | 2621P | CINNAMON TEAL | 111 CINNAMON TEAL CT | 073 | FRA | 2019-07-30 | U125208 | U129005 | 2019-07-29 | 2019-07-26 | 2019-08-13 |  | CDESPAI | 2019-07-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.1833 | 1 | 3284 | 288.32 | 178.94 | 392.9 | 2423.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19727860800 |  | 100334808 |  | 6720212P | 1858577 |  |  | 565 | EX | REPLACE SL W/18026842000 | 2621P | NEW CIRCLE | 1032 E NEW CIRCLE RD A | 067 | LEX | 2019-07-29 | U126603 | U124960 | 2019-07-29 | 2019-12-23 |  |  | SHAWN DENNIS | 2019-07-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.6833 | 1 | 4253.76 | 108.8 | 0 | 32.78 | 4112.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026885100 |  |  |  | 6712204C | 1965265 | U461383 |  | 557 | EX | INSTALL 16' OF 2"PMMP MAIN | 2621P | CROMWELL | 588 CROMWELL WY | 067 | LEX | 2019-10-08 | U128132 | U461383 | 2019-07-16 | 2019-08-29 | 2020-04-13 | 2019-07-29 | JENSMIN | 2019-07-30 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP8851 |  |  | 100 | 055732190268851 | 10.4167 | 36 | 16190.44 | 705.99 | 736.64 | 380.25 | 12736.73 | 0 | 0 | 1630.83 | 18
KY | KY - WEST | 2621 | 19026885200 |  |  |  | 6712204C | 1965265 | U461383 |  | 558 | EX | RETIRE 4' OF 2"PAMP MAIN | 2621P | CROMWELL | 588 CROMWELL WY | 067 | LEX | 2019-10-08 | U128132 | U461383 | 2019-07-16 | 2019-08-30 | 2020-04-13 | 2019-07-29 | JENSMIN | 2019-07-30 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP8852 |  |  | 100 | 055832190268852 | 0.78333 | 0 | 9432.4 | 1404.5 | 0 | 1316.12 | 6711.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673607000 |  | 100311735 |  | 6712208L | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2804 CLAYS MILL RD | 067 | LEX | 2019-07-30 | U126602 | U131066 | 2019-01-30 | 2019-11-27 |  |  | DEREK PAYTON | 2019-07-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4 | 1 | 1712.16 | 249.79 | 257.25 | 15.23 | 1189.89 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19679411700 |  | 100428160 | 08 | 7356216H |  |  |  | 566 | EX | MTR ABN 100249498* RI 2-5-19 | 2621P | FORT BISHOP | 98 FORT BISHOP | 127 | LOU | 2019-07-30 | AMCCORM | SGIORDA | 2019-02-05 | 2049-12-31 |  |  | AMCCORM | 2019-07-30 | 2019-07-18 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 5.8667 | 4 | 708.95 | 374.75 | 0 | 334.2 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680069400 |  | 100320197 |  | 6716208G | 1748686 |  |  | 565 | EX | REPLACE SL/17026736100 | 2600B | SHADY | 124 SHADY LN | 067 | LEX | 2019-07-31 | U126284 | U131066 | 2019-02-07 | 2019-09-30 |  |  | JOSH PASLEY | 2019-07-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.5333 | 1 | 3552.06 | 342.29 | 0 | 107.14 | 3102.63 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689093100 |  | 100255812 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | TURLEY | 1002 TURLEY AV | 089 | FLA | 2019-07-30 | U125566 | U131066 | 2019-03-18 | 2019-11-27 |  |  | DAVID SKAGGS | 2019-07-30 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.81667 | 1 | 1646.4 | 50.44 | 0 | 6.26 | 1589.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691688600 |  | 100417285 |  | 6720208B | 1855692 |  |  | 565 | EX | REPLACE SL W/18026796400 | 2600B | CHINOE | 239 CHINOE RD | 067 | LEX | 2019-07-31 | U125559 | U131066 | 2019-03-27 | 2019-12-31 |  |  | BJACKSON | 2019-07-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2614.49 | 0 | 0 | 0 | 2614.49 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19696299000 |  | 100328196 |  | 6720208B |  | U125208 |  | 566 | EX | DEMO 4/23 - RA 04/26 | 2621P | CHINOE | 123 CHINOE RD | 067 | LEX | 2019-08-05 | U125208 | U125208 | 2019-04-11 | 2019-04-23 | 2019-04-23 |  | ATWILLI | 2019-07-30 | 2019-04-24 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 13.6833 | 4 | 795.75 | 750.42 | 0 | 45.33 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703186900 |  | 100279983 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 294 HIGHLAND PY | 073 | FRA | 2019-08-26 | U461375 | U131066 | 2019-05-03 | 2019-11-27 |  |  | LARRY BROWN | 2019-07-30 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2293.54 | 0 | 0 | 0 | 2293.54 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703189200 |  | 100279995 |  | 6688228N | 1853312 |  |  | 565 | EX | REPLACE SL W/18026776900 | 2600B | HIGHLAND | 270 HIGHLAND PY | 073 | FRA | 2019-08-26 | U461375 | U131066 | 2019-05-03 | 2019-12-31 |  |  | LARRY BROWN | 2019-07-30 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2686.7 | 0 | 0 | 0 | 2686.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19715634900 |  | 100334805 |  | 6720212P | 1858577 |  |  | 565 | EX | REPLACE SL W/18026842000 | 2600B | NEW CIRCLE | 1030 E NEW CIRCLE RD | 067 | LEX | 2019-08-02 | U126603 | U131066 | 2019-06-19 | 2019-12-31 |  |  | SHAWN DENNIS | 2019-07-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.2667 | 1 | 3862.29 | 193.3 | 0 | 61.71 | 3607.28 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19715635200 |  | 100334811 |  | 6720212P | 1858577 |  |  | 565 | EX | REPLACE SL W/18026842000 | 2600B | NEW CIRCLE | 1036 E NEW CIRCLE RD | 067 | LEX | 2019-08-06 | U126603 | U131066 | 2019-06-19 | 2019-12-31 |  |  | SHAWN DENNIS | 2019-07-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.93333 | 1 | 10879.94 | 55.73 | 0 | 17.8 | 10806.41 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19715635300 |  | 100334818 |  | 6720212P | 1858577 |  |  | 565 | EX | RPLC SL/18026842000 | 2600B | NEW CIRCLE | 1050 E NEW CIRCLE RD | 067 | LEX | 2019-08-02 | U126603 | U131066 | 2019-06-19 | 2019-09-30 |  |  | SHAWN DENNIS | 2019-07-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.75 | 1 | 4063.67 | 163.67 | 0 | 52.22 | 3847.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19721806900 |  | 100318222 |  | 6716204C | 1534702 |  |  | 565 | EX | AOC - ATMOS CORROSION | 2621P | GREENLAWN | 3440 GREENLAWN DR | 067 | LEX | 2019-07-30 | ASNICHO | U131723 | 2019-07-03 | 2019-08-02 | 2019-10-03 |  | ASNICHO | 2019-07-30 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 20.1333 | 2 | 1425.97 | 1344.11 | 0 | 81.86 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19724045200 |  | 100267728 |  | 7356216D |  |  |  | 566 | EX | DEMO / ABANDON / RI 07-18-19 | 2621P | MAIN | 326 W MAIN ST | 127 | LOU | 2019-08-05 | U125208 | U132002 | 2019-07-15 | 2019-08-22 | 2019-09-13 |  | BROBERT | 2019-07-30 | 2019-07-19 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 12.55 | 5 | 1043.33 | 775.14 | 0 | 268.19 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19725264200 |  | 100422307 |  | 6716204K | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER / | 2621D | CHAMBERLAIN | 381 CHAMBERLAIN DR | 067 | LEX | 2019-07-30 | ATWILLI | AOC SYST | 2019-07-18 | 2019-08-16 | 2019-09-16 |  | ATWILLI | 2019-07-30 | 2019-07-29 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.1167 | 5 | 2224.35 | 1370.56 | 200.19 | 83.6 | 570 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19726443500 |  | 100318456 |  | 6716204C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D093801 | 2621P | HIGHTOWER | 344 HIGHTOWER RD | 067 | LEX | 2019-07-30 | ASNICHO | U125208 | 2019-07-24 | 2019-07-26 | 2019-08-13 |  | ASNICHO | 2019-07-30 | 2019-07-26 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 26.4333 | 5 | 1739.95 | 1560.5 | 0 | 179.45 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19728495600 |  | 100412896 |  | 6720208F |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | HART | 2012 HART RD | 067 | LEX | 2019-08-05 | U125208 | U129005 | 2019-07-30 | 2019-07-29 | 2019-07-29 |  | JWCOX | 2019-07-30 | 2019-07-30 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.8 | 1 | 6872.12 | 742.22 | 194.73 | 45.26 | 5889.91 | 0 | 0 | 0
KY | KY - WEST | 2621 | 17026742700 |  |  |  | 6716208F | 1749637 | U122858 |  | 561 | EX | INSTALL 14'-8"CS&PMLP | 2600B | SOUTHLAND | SOUTHLAND DR | 067 | LEX | 2019-08-08 | U123258 | U122858 | 2017-12-18 | 2019-08-21 | 2019-08-30 | 2019-07-10 | A PARRIS | 2019-07-31 | 2019-06-25 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP7427 | AMRCB |  | 100 | 056132170267427 | 79.5667 | 99 | 49872.05 | 4676.15 | 10071.67 | 1533.38 | 27372.04 | 0 | 157.05 | 6061.76 | 11
KY | KY - WEST | 2621 | 17026742800 |  |  |  | 6716208F | 1749637 | U122858 |  | 562 | EX | RETIRE 8'-8"BSLP | 2600B | SOUTHLAND | SOUTHLAND DR | 067 | LEX | 2019-08-08 | U123258 | U122858 | 2017-12-18 | 2019-08-30 | 2019-08-30 | 2019-07-10 | A PARRIS | 2019-07-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP7428 | AMRCB |  | 100 | 056232170267428 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18026754500 |  |  |  | 6716208F | 1749637 | U122858 |  | 561 | EX | INSTALL 1260'-4"&6" PMLP | 2600B | SOUTHLAND | SOUTHLAND DR | 067 | LEX | 2019-10-03 | U123258 | U122858 | 2018-03-01 | 2019-07-16 | 2019-08-30 | 2019-07-31 | A PARRIS | 2019-07-31 | 2019-05-31 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP7545 | AMRCB |  | 100 | 056132180267545 | 183.6833 | 25168 | 210289.46 | 11163.47 | 12837.4 | 3322.42 | 155738.2 | 0 | 990.61 | 26237.36 | 1144
KY | KY - WEST | 2621 | 18026754600 |  |  |  | 6716208F | 1749637 | U122858 |  | 562 | EX | RETIRE 138'-6&8"LP | 2600B | SOUTHLAND | SOUTHLAND DR | 067 | LEX | 2019-10-03 | U123258 | U122858 | 2018-03-01 | 2019-08-30 | 2019-08-30 | 2019-07-31 | A PARRIS | 2019-07-31 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP7546 | AMRCB |  | 100 | 056232180267546 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689107900 |  | 100255626 |  | 7348264H | 1859009 |  |  | 565 | EX | REPLACE SL W/18026843700 | 2600B | 1ST | 523 N 1ST ST | 089 | FLA | 2019-07-31 | U124015 | U131066 | 2019-03-18 | 2019-12-31 |  |  | ORA SLONE | 2019-07-31 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1651.18 | 0 | 0 | 0 | 1651.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691673500 |  | 100326870 |  | 6720208B | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1407 FONTAINE RD 1 | 067 | LEX | 2019-07-31 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-07-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3445.41 | 0 | 0 | 0 | 3445.41 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703184700 |  | 100279998 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 264 HIGHLAND PY | 073 | FRA | 2019-08-01 | U126309 | U131066 | 2019-05-03 | 2019-11-27 |  |  | JAMIE LYNN | 2019-07-31 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.11667 | 1 | 2523.59 | 5.96 | 0 | 0.76 | 2516.87 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19715635600 |  | 100442028 |  | 6720212P | 1858577 |  |  | 565 | EX | REPLACE SL W/18026842000 | 2600B | NEW CIRCLE | 1058 E NEW CIRCLE RD | 067 | LEX | 2019-08-03 | U126603 | U131066 | 2019-06-19 | 2019-12-31 |  |  | SHAWN DENNIS | 2019-07-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.9833 | 2 | 2769.98 | 295.25 | 0 | 94.24 | 2380.49 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19724016000 |  | 100282946 |  | 6712228B |  |  |  | 566 | EX | DEMO / PER CODE ENFORCEMENT | 2621P | ESTILL | 502 ESTILL CT | 209 | GEO | 2019-08-01 | U125208 | U132002 | 2019-07-15 | 2019-08-22 | 2019-09-13 |  | BJLONE | 2019-07-31 | 2019-07-24 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 11.05 | 3 | 738.18 | 695.82 | 0 | 42.36 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19724016800 |  | 100282945 |  | 6712228B |  |  |  | 566 | EX | DEMO / PER CODE ENFORCEMENT | 2621P | ESTILL | 502< ESTILL CT | 209 | GEO | 2019-08-01 | U125208 | U132002 | 2019-07-15 | 2019-08-22 | 2019-09-13 |  | EFGOINS | 2019-07-31 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 0.91667 | 2 | 121.6 | 57.35 | 60.77 | 3.48 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19726591900 |  | 100340960 |  | 7240212B |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | MAYSVILLE | 15 S MAYSVILLE ST | 173 | MT | 2019-07-31 | DENNING | U125208 | 2019-07-24 | 2019-08-23 |  |  | DENNING | 2019-07-31 | 2019-07-30 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 32.05 | 11 | 2141.22 | 1728.81 | 214.1 | 198.31 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19726593800 |  | 100343437 |  | 7240212B |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | MAYSVILLE | 26 S MAYSVILLE ST | 173 | MT | 2019-07-31 | DENNING | U125208 | 2019-07-24 | 2019-08-23 |  |  | DENNING | 2019-07-31 | 2019-07-31 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 28.5 | 6 | 1996.17 | 1615.69 | 156.81 | 223.67 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19726597900 |  | 100340958 |  | 7240212B |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | MAYSVILLE | 31 S MAYSVILLE ST | 173 | MT | 2019-07-31 | DENNING | U125208 | 2019-07-24 | 2019-08-23 |  |  | DENNING | 2019-07-31 | 2019-07-30 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 84.7 | 17 | 5038.07 | 4540.42 | 156.81 | 340.84 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19726606600 |  | 100340957 |  | 7240212B |  |  |  | 565 | EX | SERVICE LINE - REPLACE/MNFLD | 2621P | MAYSVILLE | 39 S MAYSVILLE ST | 173 | MT | 2019-07-31 | DENNING | U125208 | 2019-07-24 | 2019-08-23 |  |  | DENNING | 2019-07-31 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 17.4167 | 5 | 1238.3 | 917.26 | 156.81 | 164.23 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19728728100 |  | 100332217 |  | 6720212N |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | AURORA | 741 AURORA AV 1F | 067 | LEX | 2019-07-31 | JWCOX | U129005 | 2019-07-31 | 2019-07-31 |  |  | JWCOX | 2019-07-31 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.4333 | 1 | 4202.93 | 588.32 | 388.31 | 35.88 | 3190.42 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19728742000 |  | 100276576 |  | 6684228H |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | LIME | 606 N LIME ST | 073 | FRA | 2019-07-31 | CDESPAI | U129005 | 2019-07-31 | 2019-07-30 | 2019-07-30 |  | CDESPAI | 2019-07-31 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.65 | 1 | 5126.07 | 457.58 | 217.49 | 623.6 | 3827.4 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19728781500 |  | 100255830 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700 | 2600B | BLUM | 1004 BLUM ST | 089 | FLA | 2019-07-31 | U125566 | U131066 | 2019-07-31 | 2019-12-31 |  |  | DAVID SKAGGS | 2019-07-31 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.43333 | 1 | 2295.04 | 26.71 | 0 | 3.32 | 2265.01 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19728891500 |  | 100255610 |  | 7348264H | 1859009 |  |  | 565 | EX | REPLACE SL W/18026843700 | 2600B | 1ST | 522 N 1ST ST | 089 | FLA | 2019-07-31 | U124015 | U131066 | 2019-07-31 | 2019-12-31 |  |  | ORA SLONE | 2019-07-31 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 2442.73 | 0 | 0 | 0 | 2442.73 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19026885500 |  |  |  | 7240212B | 1965273 | U131983 |  | 558 | EX | RETIRE 329' OF 2"BSLP MAIN | 2621P | MAYSVILLE | S MAYSVILLE ST | 173 | MT | 2019-08-23 | U123258 | U131983 | 2019-07-16 | 2019-08-01 | 2019-12-31 | 2019-08-01 | DENNING | 2019-08-01 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP8855 | AMRCB |  | 100 | 055832190268855 | 6.5 | 0 | 372.05 | 313.79 | 0 | 58.26 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680069200 |  | 100320195 |  | 6716208G | 1748686 |  |  | 565 | EX | REPLACE SL/17026736100/ | 2600B | SHADY | 118 SHADY LN | 067 | LEX | 2019-08-01 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-08-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5 | 1 | 3733.13 | 282.87 | 0 | 35.17 | 3415.09 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687824000 |  | 100280019 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | MAGNOLIA | 324 MAGNOLIA AV | 073 | FRA | 2019-08-26 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-08-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687825100 |  | 100280021 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | MAGNOLIA | 322 MAGNOLIA ST | 073 | FRA | 2019-08-26 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-08-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1621.79 | 0 | 0 | 0 | 1621.79 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687850400 |  | 100280018 |  | 6688228N | 1853312 |  |  | 566 | EX | ABANDON SL W/18026777000 | 2600B | MAGNOLIA | 323 MAGNOLIA ST | 073 | FRA | 2019-11-01 | U125208 | U131066 | 2019-03-13 | 2019-12-31 |  |  | LARRY BROWN | 2019-08-01 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1055 | 0 | 0 | 0 | 1055 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19715635700 |  | 100334821 |  | 6720212P | 1858577 |  |  | 565 | EX | REPLACE SL W/18026842000 | 2600B | NEW CIRCLE | 1066 E NEW CIRCLE RD STE1 | 067 | LEX | 2019-08-01 | U461467 | U131066 | 2019-06-19 | 2019-12-31 |  |  | D REFFETT | 2019-08-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.3833 | 1 | 13257.22 | 180.09 | 0 | 62.97 | 13014.16 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19723614700 |  | 100345389 |  | 6696212H |  |  |  | 566 | EX | ABANDON / RI 07-11-19 | 2621P | DOUGLAS | 241 DOUGLAS AV | 239 | VER | 2019-08-07 | U125208 | U131723 | 2019-07-12 | 2019-08-09 | 2019-08-26 |  | EFGOINS | 2019-08-01 | 2019-07-30 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 10.3333 | 3 | 920.16 | 596.13 | 0 | 33.69 | 290.34 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19725466600 |  | 100279346 |  | 6688228K |  |  |  | 566 | EX | DEMO / ABANDON / RI 07-22-2019 | 2621P | RANDOLPH | 131 RANDOLPH RD | 073 | FRA | 2019-08-06 | U125208 | U132002 | 2019-07-19 | 2019-08-27 | 2019-09-18 |  | BJLONE | 2019-08-01 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 5.1333 | 2 | 398.36 | 296.14 | 85.48 | 16.74 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19726840700 |  | 100264011 |  | 7352260N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D188507 | 2621P | MAIN | 2128 MAIN ST W | 019 | ASH | 2019-08-06 | U125208 | U125208 | 2019-07-24 | 2019-07-24 | 2019-07-24 |  | BROBERT | 2019-08-01 | 2019-07-25 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 69.9333 | 10 | 7976.56 | 4476.78 | 283.18 | 2120.15 | 1096.45 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19728789500 |  | 100308715 |  | 6712212P |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | BEACON HILL | 1785 BEACON HILL RD | 067 | LEX | 2019-08-01 | JENSMIN | U129005 | 2019-07-31 | 2019-07-31 | 2019-07-31 |  | JENSMIN | 2019-08-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.1 | 2 | 4048.54 | 621.92 | 771.5 | 587.03 | 2068.09 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19728823700 |  | 100257418 |  | 7356256E |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | 3RD CIRCLE PRO | 2032 3RD CIRCLE PRO | 019 | ASH | 2019-08-01 | MCOLLET | U129005 | 2019-07-31 | 2019-07-31 |  |  | MCOLLET | 2019-08-01 | 2019-07-31 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 6.3 | 3 | 626.29 | 383.3 | 14.32 | 228.67 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19729182300 |  | 100317407 |  | 6716204J |  |  |  | 565 | EX | REPLACE SERVICE LINE - D107493 | 2621P | TANGLEY | 326 TANGLEY WY | 067 | LEX | 2019-08-06 | U125208 | U129005 | 2019-08-01 | 2019-08-01 | 2019-08-01 |  | JWCOX | 2019-08-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.8333 | 1 | 3093.22 | 390.34 | 211.83 | 22.09 | 2468.96 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19729189300 |  | 100264012 |  | 7352260N |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | MAIN | 2132 MAIN ST W | 019 | ASH | 2019-08-06 | U125208 | U129005 | 2019-08-01 | 2019-08-01 |  |  | BROBERT | 2019-08-01 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.75 | 2 | 265.56 | 41.47 | 189.09 | 2.36 | 32.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19729229300 |  | 100331527 |  | 6720212N |  |  |  | 565 | EX | REPLACE SERVICE D107494 | 2621P | CRAMER | 1017 CRAMER AV | 067 | LEX | 2019-08-06 | U125208 | U125208 | 2019-08-01 | 2019-08-01 | 2019-08-01 |  | ATWILLI | 2019-08-01 | 2019-08-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.3833 | 2 | 1275.35 | 1003.08 | 179.96 | 56.79 | 35.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19729231900 |  | 100338253 |  | 6720212J |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | BRECKENRIDGE | 604 BRECKENRIDGE ST | 067 | LEX | 2019-08-01 | JENSMIN | U129005 | 2019-08-01 | 2019-08-01 |  |  | JENSMIN | 2019-08-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.16667 | 1 | 490.67 | 10.06 | 383.02 | 10.23 | 87.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19729246400 |  | 100319533 |  | 6716208L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D221315 | 2621P | GREENBRIAR | 421 GREENBRIAR RD | 067 | LEX | 2019-08-06 | U125208 | U129005 | 2019-08-01 | 2019-07-31 | 2019-07-31 |  | ASNICHO | 2019-08-01 | 2019-07-31 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.1167 | 5 | 2316.36 | 1644.91 | 473.34 | 91.55 | 106.56 | 0 | 0 | 0
KY | KY - EAST | 2633 | 17026723100 |  |  |  | 7332132K | 1963346 | U128885 |  | 583 | EX | INSTALL TEMP REG STATION | 2600E | SR899 1429 | SR899 1429 | 119 | PIP | 2024-03-15 | U462463 | U128885 | 2017-08-28 | 2017-12-28 |  | 2019-06-20 | CYNTHIA FARIS | 2019-08-02 | 2019-06-20 |  | F | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00583 | 3200583 |  |  | WP7231 |  |  | 100 | 058332170267231 | 64.3 | 126 | 16495.12 | 4288.27 | 1235.72 | 744.93 | 7675 | 0 | 151.45 | 2399.75
KY | KY - EAST | 2633 | 17026723200 |  |  |  | 7332132K | 1963346 | U128885 |  | 584 | EX | RETIRE REG STATION | 2600E | SR899 1429 | SR899 1429 | 119 | PIP | 2019-08-05 | U462463 | U128885 | 2017-08-28 | 2017-12-29 | 2017-12-31 | 2019-06-20 | CYNTHIA FARIS | 2019-08-02 |  |  | F | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00584 | 3200584 |  |  | WP7232 |  |  | 100 | 058432170267232 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680069300 |  | 100320196 |  | 6716208G | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 122 SHADY LN | 067 | LEX | 2019-08-02 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-08-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.2833 | 1 | 3190.92 | 186.12 | 0 | 23.14 | 2981.66 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687824700 |  | 100280022 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | MAGNOLIA | 318 MAGNOLIA ST | 073 | FRA | 2019-08-26 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-08-02 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1278.5 | 0 | 0 | 0 | 1278.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689088300 |  | 100255607 |  | 7348264H | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | 1ST | 516 N 1ST ST | 089 | FLA | 2019-08-02 | U124015 | U131066 | 2019-03-18 | 2019-08-02 |  |  | ORA SLONE | 2019-08-02 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.5 | 1 | 1507.49 | 27.77 | 0 | 3.48 | 1476.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691674200 |  | 100326854 |  | 6720208B | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1509 FONTAINE RD | 067 | LEX | 2019-08-12 | U125208 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-08-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 5495.72 | 286.4 | 0 | 16.43 | 5192.89 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19729210600 |  | 100338252 |  | 6720212J |  |  |  | 565 | EX | REPLACE SERVICE LINE - D221545 | 2621P | BRECKENRIDGE | 602 BRECKENRIDGE ST | 067 | LEX | 2019-08-06 | U125208 | U129005 | 2019-08-01 | 2019-07-31 | 2019-07-31 |  | JENSMIN | 2019-08-02 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.3833 | 3 | 6001.71 | 323.9 | 1296.07 | 311.06 | 4070.68 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19026886800 |  | 501250413 |  | 6712232I | 1853461 | U131982 |  | 555 | EX | INSTALL 30' 2" PMMP | 2600B | KENDALL | 191 KENDALL DR LT88C | 209 | GEO | 2019-08-27 | U125423 | U131982 | 2019-07-23 | 2019-08-29 | 2019-09-01 | 2019-08-03 | NEAL JOHNSON | 2019-08-03 | 2019-08-02 | 2019-08-02 | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP8868 |  |  | 100 | 055532190268868 | 16.6833 | 174 | 9422.71 | 953.69 | 454.44 | 313.69 | 6780.82 | 0 | 18.22 | 901.85 | 58
KY | KY - WEST | 2621 | 19026858500 |  |  |  | 6720212P | 1858577 | U131982 |  | 584 | EX | RETIRE REG STATION 1165 | 2600E | NEW CIRCLE | 1082 NEW CIRCLE RD NE | 067 | LEX | 2019-08-12 | U462463 | U131982 | 2019-01-31 | 2019-12-31 | 2019-12-31 | 2019-08-05 | WADE SHIMFESSEL | 2019-08-05 | 2019-05-08 |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00584 | 3200584 |  |  | WP8585 | AMRCB |  | 100 | 058432190268585 | 26.1167 | 0 | 4474.52 | 1671.71 | 332.82 | 367.94 | 2100.47 | 0 | 1.58 | 0
KY | KY - WEST | 2621 | 19678821200 |  | 100298987 |  | 6716212B | 1855322 |  |  | 565 | EX | REPLACE SL W/18026792400 | 2600B | FORBES | 1443 N FORBES RD | 067 | LEX | 2019-08-05 | U461467 | U131066 | 2019-02-01 | 2019-12-31 |  |  | D REFFETT | 2019-08-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.15 | 1 | 2027.98 | 61.65 | 0 | 21.54 | 1944.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680069100 |  | 100320194 |  | 6716208G | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 116 SHADY LN | 067 | LEX | 2019-08-05 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-08-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.4667 | 1 | 3246.28 | 366.03 | 0 | 20.72 | 2859.53 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689088400 |  | 100255609 |  | 7348264H | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | 1ST | 520 N 1ST ST | 089 | FLA | 2019-08-05 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-08-05 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 1.1167 | 1 | 4001.3 | 59.59 | 0 | 3.37 | 3938.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19710742900 |  | 100466262 |  | 6720216H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094756 | 2621P | OLD KINGSTON | 291 OLD KINGSTON RD | 067 | LEX | 2019-08-06 | U125208 | U125208 | 2019-05-31 | 2019-08-05 | 2021-05-31 |  | JWCOX | 2019-08-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.1667 | 1 | 3284.64 | 66.17 | 284.85 | 3.75 | 2929.87 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19727853600 |  | 100279295 |  | 6688228K |  |  |  | 565 | EX | REPLACE CAT 1 AND 2 | 2621P | RINGO | 119 RINGO AV | 073 | FRA | 2019-08-05 | CDESPAI | U125208 | 2019-07-29 | 2019-10-29 |  |  | CDESPAI | 2019-08-05 | 2019-08-02 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 13.9 | 2 | 6983.08 | 875.74 | 328.75 | 1294.65 | 4483.94 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19729251300 |  | 100286091 |  | 6764176P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D097370 | 2621P | BROADWAY | 212 BROADWAY ST | 065 | IRV | 2019-08-05 | DENNING | U125208 | 2019-08-01 | 2019-08-01 | 2019-08-01 |  | DENNING | 2019-08-05 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 28.7667 | 4 | 1978.86 | 1359.22 | 302.44 | 188.56 | 128.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19729919300 |  | 100292613 |  | 6720216N |  |  |  | 565 | EX | GRADE 1 REPLACE D192823 | 2621P | HAWTHORNE | 1725 HAWTHORNE LN | 067 | LEX | 2019-08-06 | U125208 | U129939 | 2019-08-03 | 2019-08-02 | 2019-08-03 |  | JWCOX | 2019-08-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.45 | 2 | 3750.01 | 369.59 | 305.04 | 20.93 | 3054.45 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19729981600 |  | 100288634 |  | 6720212D |  |  |  | 565 | EX | REPLACE SERVICE LINE D107496 | 2621P | BELLCASTLE | 593 BELLCASTLE RD | 067 | LEX | 2019-08-06 | U125208 | U129005 | 2019-08-05 | 2019-08-05 | 2019-08-05 |  | ATWILLI | 2019-08-05 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.3 | 1 | 966.02 | 552.15 | 329.79 | 31.28 | 52.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19730025200 |  | 100326404 |  | 6720208A |  | U129005 |  | 565 | EX | REPLACE SERVICE LINE - D221316 | 2621P | CHENAULT | 228< CHENAULT RD | 067 | LEX | 2019-08-12 | U125208 | U129005 | 2019-08-05 | 2019-08-05 | 2019-08-05 |  | JENSMIN | 2019-08-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 4505.09 | 503.41 | 873.99 | 511.37 | 2616.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12965296800 |  | 100334816 |  | 6720212P | 1858577 |  |  | 566 | EX | ABNDN MANIFOLD/18026842000 | 2600B | NEW CIRCLE | 1044 E NEW CIRCLE RD | 067 | LEX | 2019-08-06 | U126603 | U124967 | 2012-04-16 | 2019-09-30 |  |  | SHAWN DENNIS | 2019-08-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 0
KY | KY - WEST | 2621 | 12968021100 |  | 100334814 |  | 16720212P | 1858577 |  |  | 566 | EX | ABANDON SL W/18026842000 | 2600B | NEW CIRCLE | 1042 E NEW CIRCLE RD A | 067 | LEX | 2019-08-06 | U126603 | U124967 | 2012-05-02 | 2019-12-31 |  |  | SHAWN DENNIS | 2019-08-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 12968021200 |  | 100334820 |  | 6720212P | 1858577 |  |  | 566 | EX | ABANDON SL W/18026842000 | 2600B | NEW CIRCLE | 1066 E NEW CIRCLE RD RR-BSM | 067 | LEX | 2019-08-06 | U126603 | U124967 | 2012-05-02 | 2019-12-31 |  |  | SHAWN DENNIS | 2019-08-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.25 | 1 | 19.53 | 14.81 | 0 | 4.72 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18648909900 |  | 100306859 |  | 6716212I |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | TERRACE VIEW | 740 TERRACE VIEW DR | 067 | LEX | 2019-08-06 | JWCOX | U125208 | 2018-10-05 | 2019-04-03 | 2020-10-31 |  | JWCOX | 2019-08-06 | 2019-01-10 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.4333 | 5 | 4013.26 | 752.59 | 464.41 | 47.35 | 2748.91 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19026883200 |  | 501268861 |  | 7348264N | 1964961 | U122858 |  | 555 | EX | INSTALL 100'-4" PMIP | 2600B | BIRCH | 1538 BIRCH ST | 089 | FLA | 2019-08-13 | U124014 | U132280 | 2019-07-03 | 2019-08-06 | 2019-08-09 | 2019-08-06 | DAVID SKAGGS | 2019-08-06 | 2019-08-02 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP8832 |  |  | 100 | 055532190268832 | 26.2333 | 201 | 10971.63 | 1459.49 | 539.97 | 183.14 | 7717.32 | 0 | 21.17 | 1050.54 | 67
KY | KY - CENTRAL | 2632 | 19671924600 |  | 100353889 |  | 7256280P | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 101 E 2ND ST | 161 | MAY | 2019-08-09 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-08-06 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1922.27 | 0 | 0 | 0 | 1922.27 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678821300 |  | 100299045 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792401 | 2600B | FORBES | 1471 N FORBES RD | 067 | LEX | 2019-08-06 | U461467 | U131066 | 2019-02-01 | 2019-09-30 |  |  | D REFFETT | 2019-08-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.3167 | 1 | 2295.71 | 70.13 | 0 | 24.52 | 2201.06 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680069000 |  | 100320193 |  | 6716208G | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 114 SHADY LN | 067 | LEX | 2019-08-06 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-08-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.4833 | 1 | 3222.19 | 310.62 | 0 | 103.04 | 2808.53 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19682158100 |  | 100442139 |  | 7344168H |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MEADOWS | 721 MEADOWS BR | 071 | PRE | 2019-08-06 | BBMULLI | U125208 | 2019-02-19 | 2019-08-16 | 2021-02-28 |  | BBMULLI | 2019-08-06 | 2019-07-30 |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 154.7667 | 20 | 15488.25 | 10345.84 | 0 | 2848.61 | 2293.8 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689088600 |  | 100255612 |  | 7348264H | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | 1ST | 526 N 1ST ST | 089 | FLA | 2019-08-06 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-08-06 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.6 | 1 | 1516.63 | 33.31 | 0 | 4.2 | 1479.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691673100 |  | 100326873 |  | 6720208B | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1403 FONTAINE RD 1F | 067 | LEX | 2019-08-06 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-08-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3044.26 | 69.42 | 229.61 | 4.05 | 2741.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19727760300 |  | 100334817 |  | 6720212P | 1858577 |  |  | 566 | EX | ABNDN MANIFOLD/18026842000 | 2600B | NEW CIRCLE | 1046 E NEW CIRCLE RD BSM | 067 | LEX | 2019-08-06 | U126603 | U125201 | 2019-07-29 | 2019-09-30 |  |  | SHAWN DENNIS | 2019-08-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2623 | 19730017500 |  | 100276172 |  | 6684228G |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | HOGE | 705 HOGE AV | 073 | FRA | 2019-08-06 | CDESPAI | U125208 | 2019-08-05 | 2019-08-06 |  |  | CDESPAI | 2019-08-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 9.2 | 1 | 4277.92 | 579 | 358.64 | 855.96 | 2484.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19730761600 |  | 100334790 |  | 6724208F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D107497 | 2621P | CADEN | 771 CADEN LN | 067 | LEX | 2019-08-07 | U125208 | U131367 | 2019-08-06 | 2019-08-05 | 2019-08-05 |  | WHIMES | 2019-08-06 | 2019-08-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.3833 | 4 | 1447.29 | 1166.79 | 178.94 | 66.04 | 35.52 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19730812400 |  | 100268883 |  | 6736252N |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | ELMARCH | 131 N ELMARCH AV | 097 | CYN | 2019-08-06 | DBANKS | U131168 | 2019-08-06 | 2019-07-26 | 2019-08-15 |  | DBANKS | 2019-08-06 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 51.3333 | 4 | 2900.5 | 2409.64 | 295.95 | 136.35 | 58.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 94170905900 |  | 100334806 | 11 | 6720212P | 1858577 |  |  | 566 | EX | ABANDON SL W/18026842100 | 2600B | NEW CIRCLE | 1034 NEW CIRCLE RD NE B | 067 | LEX | 2019-08-06 | U126603 | KAUSTIN | 1994-05-12 | 2019-12-31 |  |  | SHAWN DENNIS | 2019-08-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1
KY | KY - WEST | 2621 | 09816540400 |  | 100326860 |  | NEW | 1855692 |  |  | 565 | EX | REPLACE SL W/18026796400 | 2600B | FONTAINE | 1411 FONTAINE RD 1 | 067 | LEX | 2019-08-08 | U125559 | U123173 | 2009-12-30 | 2019-12-30 |  |  | BJACKSON | 2019-08-07 | 2010-01-19 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.2333 | 2 | 5314.8 | 62.45 | 245.54 | 9.68 | 4997.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18026773101 |  |  |  | 6720212L | 1852951 | U128885 |  | 559 | EX | INSTALL 175' - 12" CSHP | 2600B | WINCHESTER | WINCHESTER RD | 067 | LEX | 2019-10-10 | U123258 | U128885 | 2019-07-30 | 2019-04-10 | 2019-08-31 | 2019-06-21 | JOHN SMITH | 2019-08-07 | 2019-01-02 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP7731 | AMRCB |  | 100 | 055932180267731 | 830.6167 | 18792 | 626707.93 | 84679.3 | 92369.93 | 18469.35 | 347840.18 | 0 | 7627.73 | 75721.44 | 174
KY | KY - WEST | 2621 | 18026773200 |  |  |  | 6720212L | 1852951 | U128885 |  | 560 | EX | RETIRE 100' 12" WTHP | 2600B | WINCHESTER | WINCHESTER RD | 067 | LEX | 2019-10-10 | U123258 | GSULLI1 | 2018-05-17 | 2019-08-30 | 2019-08-31 | 2019-06-21 | JOHN SMITH | 2019-08-07 | 2019-04-23 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00560 | 3200560 |  |  | WP7732 | AMRCB |  | 100 | 056032180267732 | 18.6667 | 0 | 28884.59 | 1050.79 | 0 | 313.81 | 27519.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18026842000 |  |  |  | 6720212P | 1858577 | U131982 |  | 557 | EX | INSTALL 725' OF 2"PMMP MAIN | 2600B | NEW CIRCLE | 1034 E NEW CIRCLE RD | 067 | LEX | 2019-10-16 | U462463 | U461383 | 2018-10-21 | 2019-11-21 | 2019-12-31 | 2019-07-25 | SHAWN DENNIS | 2019-08-07 | 2019-07-22 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP8420 | AMRCB |  | 100 | 055732180268420 | 127.4 | 7280 | 92959.4 | 9858.78 | 1290.36 | 2120.2 | 68790.96 | 0 | 257.78 | 10641.32 | 560
KY | KY - WEST | 2621 | 18026842100 |  |  |  | 6720212P | 1858577 | U131982 |  | 558 | EX | RETIRE 700' OF 4"BSLP MAIN | 2600B | NEW CIRCLE | 1034 E NEW CIRCLE RD | 067 | LEX | 2019-10-16 | U462463 | U461383 | 2018-10-21 | 2019-12-31 | 2019-12-31 | 2019-08-05 | SHAWN DENNIS | 2019-08-07 | 2019-08-06 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP8421 | AMRCB |  | 100 | 055832180268421 | 1 | 0 | 518.01 | 59.3 | 0 | 18.92 | 439.79 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19026874700 |  | 501263665 |  | 6688228P | 1963026 | U461383 |  | 555 | EX | INSTALL 700' OF 2"PMMP MAIN | 2600B | ARROWHEAD | 121 ARROWHEAD CT | 073 | FRA | 2019-08-12 | U124014 | U461383 | 2019-05-02 | 2019-06-25 | 2019-08-15 | 2019-08-05 | WGRAVES | 2019-08-07 | 2019-07-29 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP8747 |  |  | 100 | 055532190268747 | 53.85 | 4880 | 31948.16 | 3012.51 | 1072.31 | 1019.7 | 23528.26 | 0 | 84.55 | 3230.83 | 610
KY | KY - WEST | 2621 | 19026880300 |  |  |  | 6720212N | 1854827 | U461383 |  | 560 | EX | RETIRE 128' OF 3"BSLP MAIN | 2600E | NATIONAL | 951 NATIONAL AV | 067 | LEX | 2019-10-02 | U460266 | U461383 | 2019-06-14 | 2019-10-01 | 2019-10-01 | 2019-08-07 | KKOUNS | 2019-08-07 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00560 | 3200560 |  |  | WP8803 | AMRCB |  | 100 | 056032190268803 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19026881000 |  |  |  | 6700216I | 1964668 | U461383 |  | 557 | EX | INSTALL 28' OF 12"CSHP MAIN | 2600B | BONITA | BONITA RD FG 29 | 239 | VER | 2019-08-12 | U123258 | U461383 | 2019-06-17 | 2019-09-25 | 2021-06-03 | 2019-08-01 | JOHN SMITH | 2019-08-07 | 2019-07-18 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP8810 | AMRCB |  | 100 | 055732190268810 | 152.5 | 1615 | 94423.9 | 10103.88 | 19549.84 | 3058.41 | 50084.59 | 0 | 458.73 | 11168.45 | 95
KY | KY - WEST | 2623 | 19026881100 |  |  |  | 6700216I | 1964668 | U461383 |  | 558 | EX | RETIRE 20' OF 12"MJBSHP MAIN | 2600B | BONITA | BONITA RD FG 29 | 239 | VER | 2019-08-12 | U123258 | U461383 | 2019-06-17 | 2019-10-01 | 2021-06-03 | 2019-08-01 | JOHN SMITH | 2019-08-07 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP8811 | AMRCB |  | 100 | 055832190268811 | 1.1167 | 0 | 217.75 | 64.61 | 0 | 20.94 | 132.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671924300 |  | 100353865 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 20 E 2ND ST | 161 | MAY | 2019-08-15 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-08-07 | 2019-08-07 |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 | 14 | 1 | 4238.09 | 862.36 | 0 | 266.8 | 3108.93 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678779000 |  | 100299076 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | FORBES | 1470 N FORBES RD | 067 | LEX | 2019-08-07 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-08-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.8167 | 1 | 1566.42 | 96.19 | 0 | 12.37 | 1457.86 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689088700 |  | 100255613 |  | 7348264H | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | 1ST | 530 N 1ST ST | 089 | FLA | 2019-08-07 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-08-07 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 1.0167 | 1 | 2133.34 | 56.61 | 0 | 7.11 | 2069.62 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689093500 |  | 100255805 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | TURLEY | 1010 TURLEY AV | 089 | FLA | 2019-08-07 | U125566 | U131066 | 2019-03-18 | 2019-11-27 |  |  | DAVID SKAGGS | 2019-08-07 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.16667 | 1 | 1123.97 | 10.01 | 0 | 1.26 | 1112.7 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19729277000 |  | 100348616 |  | 6748208M |  |  |  | 566 | EX | DEMO / ABANDON / RI 08-02-19 | 2621P | WASHINGTON | 17 E WASHINGTON ST | 049 | WIN | 2019-08-12 | U125208 | U132002 | 2019-08-01 | 2019-09-10 | 2019-10-01 |  | DENNING | 2019-08-07 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 19.4667 | 4 | 1118.6 | 919.71 | 0 | 198.89 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19730787500 |  | 100453626 |  | 6684228G |  |  |  | 565 | EX | REPLACE SERVICE | 2621P | HOGE | 706 HOGE AV 2 | 073 | FRA | 2019-08-07 | CDESPAI | U131168 | 2019-08-06 | 2019-08-06 |  |  | CDESPAI | 2019-08-07 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8.3 | 2 | 5552.03 | 523.54 | 421.58 | 774.01 | 3832.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19730810200 |  | 100326783 |  | 6720208I |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | CHINOE | 774 CHINOE RD | 067 | LEX | 2019-08-07 | JWCOX | U131367 | 2019-08-06 | 2019-08-06 |  |  | JWCOX | 2019-08-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.8333 | 1 | 6382.55 | 105.01 | 373.83 | 5.95 | 5897.76 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19731050800 |  | 100274294 |  | 6684228N |  |  |  | 565 | EX | REPLACE SERVICE LINE - NO DPI | 2621P | TODD | 210 W TODD ST | 073 | FRA | 2019-08-12 | U125208 | U131555 | 2019-08-07 | 2019-08-07 |  |  | CDESPAI | 2019-08-07 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 18.3333 | 2 | 7203.85 | 1155.44 | 307.34 | 1708.23 | 4032.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19731054300 |  | 100350819 |  | 6744208P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D097391 | 2621P | WHEELER | 23 WHEELER ST 4 | 049 | WIN | 2019-08-07 | DENNING | U125208 | 2019-08-07 | 2019-08-06 | 2019-08-06 |  | DENNING | 2019-08-07 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 8.9333 | 4 | 1220.46 | 569.86 | 445.42 | 140.86 | 64.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19731144600 |  | 100313766 |  | 6716208B |  |  |  | 565 | EX | REPLACE SERVICE LINE D221547 | 2621P | ROYALTY | 1345 ROYALTY CT 1 | 067 | LEX | 2019-08-12 | U125208 | U131367 | 2019-08-07 | 2019-08-07 | 2019-08-07 |  | LSTANFI | 2019-08-07 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.1667 | 2 | 2147.23 | 925.15 | 1100.6 | 52.36 | 69.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07698425000 |  | 100290828 |  | ? |  |  |  | 566 | EX | ABN SERV LINE PER 24 MO MEMO | 2600B | LIMESTONE | 1111 N LIMESTONE ST | 067 | LEX | 2019-08-08 | JWCOX | DMCCULL | 2007-08-14 | 2019-08-08 |  |  | JWCOX | 2019-08-08 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 1.1833 | 1 | 71.75 | 67.91 | 0 | 3.84 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 17026722401 |  |  |  | 7240208N | 1747361 | U128885 |  | 557 | EX | INSTALL 250' - 4" CSHP | 2600B | LEVEE | 4413 LEVEE RD | 173 | MT | 2019-08-15 | U123258 | U128885 | 2019-07-30 | 2019-09-05 | 2019-10-19 | 2019-08-05 | DDAVIS | 2019-08-08 | 2019-07-09 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP7224 | AMRCB |  | 100 | 055732170267224 | 424.4167 | 16992 | 169943.98 | 26704.21 | 21588.81 | 6374.06 | 93439.87 | 0 | 1795.18 | 20041.85 | 354
KY | KY - CENTRAL | 2629 | 17026722500 |  |  |  | 7240208N | 1747361 | U128885 |  | 558 | EX | RETIRE 200' - 4" BSHP | 2600B | LEVEE | 4413 LEVEE | 173 | MT | 2019-08-15 | U123258 | U128885 | 2017-08-28 | 2019-10-18 | 2019-10-19 | 2019-08-05 | DDAVIS | 2019-08-08 | 2019-08-07 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP7225 | AMRCB |  | 100 | 055832170267225 | 9.9167 | 0 | 682.75 | 554.61 | 0 | 128.14 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678791200 |  | 100299066 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | PEPPER | 223 PEPPER DR | 067 | LEX | 2019-08-08 | U126286 | U131066 | 2019-02-01 | 2019-11-27 |  |  | TYLER ALLISON | 2019-08-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1308.11 | 0 | 0 | 0 | 1308.11 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678791600 |  | 100299072 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | PEPPER | 232 PEPPER DR | 067 | LEX | 2019-08-08 | U126286 | U131066 | 2019-02-01 | 2019-11-27 |  |  | TYLER ALLISON | 2019-08-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2071.97 | 0 | 0 | 0 | 2071.97 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680068800 |  | 100320192 |  | 6716208G | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 112 SHADY LN | 067 | LEX | 2019-08-09 | U126309 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JAMIE LYNN | 2019-08-08 | 2019-08-08 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.5167 | 1 | 1942.9 | 189.3 | 0 | 10.71 | 1742.89 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680068900 |  | 100320240 |  | 6716208G | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 113 SHADY LN | 067 | LEX | 2019-08-09 | U126309 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JAMIE LYNN | 2019-08-08 | 2019-08-08 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.2667 | 1 | 2110.06 | 67.97 | 0 | 3.85 | 2038.24 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689088800 |  | 100255623 |  | 7348264H | 1859009 |  |  | 566 | EX | ABND SL/18026843700/ | 2600B | 1ST | 701 N 1ST ST | 089 | FLA | 2019-08-08 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-08-08 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 | 0.76667 | 1 | 126.31 | 42.21 | 0 | 5.3 | 78.8 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689088900 |  | 100255622 |  | 7348264H | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | 1ST | 705 N 1ST ST | 089 | FLA | 2019-08-08 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-08-08 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.51667 | 1 | 1781.39 | 29.43 | 0 | 3.71 | 1748.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691673700 |  | 100326862 |  | 6720208B | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1409 FONTAINE RD | 067 | LEX | 2019-09-11 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-08-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 11160.19 | 0 | 0 | 0 | 11160.19 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691694000 |  | 100326500 |  | 6720208A | 1855692 |  |  | 565 | EX | REPLACE SL W/18026796400 | 2600B | FONTAINE | 1054 FONTAINE RD | 067 | LEX | 2019-08-14 | U125559 | U131066 | 2019-03-27 | 2019-12-31 |  |  | BJACKSON | 2019-08-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2051.49 | 0 | 265.63 | 0 | 1785.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19731169400 |  | 100311762 |  | 6716208I |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | SOUTHVIEW | 2825 SOUTHVIEW DR | 067 | LEX | 2019-08-08 | JWCOX | U131367 | 2019-08-07 | 2019-08-07 |  |  | JWCOX | 2019-08-08 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.9667 | 1 | 3489.2 | 283.04 | 266.28 | 16.02 | 2923.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19731417500 |  | 100313869 |  | 6716212N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D095360 | 2621P | SOUTHERN | 1305 SOUTHERN AV | 067 | LEX | 2019-08-12 | U125208 | U129005 | 2019-08-08 | 2019-08-07 | 2019-08-07 |  | WHIMES | 2019-08-08 | 2019-08-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.7167 | 2 | 1049.72 | 650.27 | 305.05 | 36.8 | 57.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19731429300 |  | 100353869 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 48 E 2ND ST | 161 | MAY | 2019-08-09 | U461478 | U125768 | 2019-08-08 | 2049-12-31 |  |  | DAVID STAGGS | 2019-08-08 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 5704.11 | 0 | 0 | 0 | 5704.11 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19026890200 |  |  |  | 6744208O | 1965825 | U128885 |  | 557 | EX | INSTALL 5' - 2" PMMP | 2621P | VILLAGE | VILLAGE CT | 049 | WIN | 2019-09-06 | U460266 | U128885 | 2019-08-12 | 2020-04-23 | 2020-04-30 | 2019-08-09 | B.JOHNSON | 2019-08-09 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP8902 |  |  | 100 | 055732190268902 |  | 6 | 2315.86 | 1978.17 | 0 | 111.85 | 0 | 0 | 4.51 | 221.33 | 6
KY | KY - CENTRAL | 2629 | 19026890300 |  |  |  | 6744208O | 1965825 | U128885 |  | 558 | EX | RETIRE 5' - 2" PMMP | 2621P | VILLAGE | VILLAGE CT | 049 | WIN | 2019-11-12 | U460266 | U128885 | 2019-08-12 | 2020-04-30 | 2020-04-30 | 2019-08-09 | B.JOHNSON | 2019-08-09 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP8903 |  |  | 100 | 055832190268903 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678791500 |  | 100299064 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | PEPPER | 231 PEPPER DR | 067 | LEX | 2019-08-15 | U125208 | U131066 | 2019-02-01 | 2019-11-27 |  |  | ED FOX | 2019-08-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1434.15 | 26.03 | 0 | 1.45 | 1406.67 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680068700 |  | 100320191 |  | 6716208G | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 110 SHADY LN | 067 | LEX | 2019-08-09 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-08-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.5167 | 1 | 2313.84 | 142.59 | 0 | 17.72 | 2153.53 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689089100 |  | 100255621 |  | 7348264H | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | 1ST | 711 N 1ST ST | 089 | FLA | 2019-08-09 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-08-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 1.2167 | 1 | 1962.6 | 67.74 | 0 | 8.51 | 1886.35 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689093400 |  | 100255808 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | TURLEY | 1009 TURLEY AV | 089 | FLA | 2019-08-09 | U125566 | U131066 | 2019-03-18 | 2019-11-27 |  |  | DAVID SKAGGS | 2019-08-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.81667 | 1 | 1955.43 | 46.2 | 0 | 5.81 | 1903.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19707015600 |  | 100311016 |  | 6712208O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | ROXBURG | 3171 ROXBURG DR | 067 | LEX | 2019-08-09 | LSTANFI | U125208 | 2019-05-17 | 2019-11-14 | 2021-05-31 |  | LSTANFI | 2019-08-09 | 2019-07-25 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.5167 | 2 | 2465.55 | 345.27 | 410.15 | 19.94 | 1690.19 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19722679700 |  | 500303593 |  | 6720212N | 1854827 |  |  | 565 | EX | REPLACE SL W/19026878600 | 2600B | RICHMOND | 340 RICHMOND AV | 067 | LEX | 2019-08-21 | U461423 | U131066 | 2019-07-09 | 2019-12-31 |  |  | KKOUNS | 2019-08-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 800.71 | 0 | 0 | 0 | 800.71 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19724663800 |  | 500016382 |  | 6700208B |  |  |  | 565 | EX | NO HSE LN-CUST 2 CALL WHN REDY | 2621P | TIM TAM | 3019 TIM TAM TL LT53 | 239 | VER | 2019-08-12 | U125208 | U125208 | 2019-07-17 | 2049-12-31 | 2049-12-31 |  | EFGOINS | 2019-08-09 | 2019-08-09 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 19.9667 | 4 | 1289.89 | 995.01 | 180.04 | 56.28 | 58.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19728840400 |  | 100360649 |  | 6736228G | 1851755 |  |  | 565 | EX | REPLACE SL W/19026866200 | 2600B | DOBBIN | 508 DOBBIN DR | 017 | PAR | 2019-08-15 | U125208 | U131066 | 2019-07-31 | 2019-12-31 |  |  | WGRAVES | 2019-08-09 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26290032 | 1.85 | 1 | 1998.56 | 100.01 | 328.74 | 34.47 | 1535.34 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19729232300 |  | 100285983 |  | 6764176P |  |  |  | 565 | EX | REPLACE SERVICE | 2621P | EDGEWATER | 423 EDGEWATER DR | 065 | IRV | 2019-08-09 | DENNING | U125208 | 2019-08-01 | 2019-08-30 |  |  | DENNING | 2019-08-09 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 32 | 4 | 2072.12 | 1513.94 | 261.56 | 210.22 | 86.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19729981800 |  | 100322511 |  | 6716208D |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | TREMONT | 731 TREMONT AV | 067 | LEX | 2019-08-12 | U125208 | U125208 | 2019-08-05 | 2019-08-08 |  |  | LSTANFI | 2019-08-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 1.6 | 2 | 2897.64 | 101.29 | 173.04 | 5.72 | 2617.59 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19730797100 |  | 100290830 |  | 6720212B |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | LIMESTONE | 1109 N LIMESTONE ST | 067 | LEX | 2019-08-09 | LSTANFI | U131367 | 2019-08-06 | 2019-08-06 |  |  | LSTANFI | 2019-08-09 | 2019-08-07 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.75 | 4 | 6009.67 | 481.9 | 179.03 | 27.24 | 5321.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19731058500 |  | 100276253 |  | 6684228G |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | MURRELL | 314 MURRELL ST | 073 | FRA | 2019-08-09 | CDESPAI | U131367 | 2019-08-07 | 2019-08-06 | 2019-08-06 |  | CDESPAI | 2019-08-09 | 2019-08-07 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 16.8 | 3 | 7693.25 | 1057.78 | 328.76 | 940.65 | 5366.06 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19731221400 |  | 100340491 |  | 6724212E |  |  |  | 565 | VO | REPLACE SERVICE LINE D192824 | 2621P | FORT SUMTER | 1701 FORT SUMTER DR | 067 | LEX | 2019-08-12 |  | U131367 | 2019-08-07 | 2019-08-07 | 2019-08-07 |  | ATWILLI | 2019-08-09 | 2019-08-08 |  | A | [11 empty] | 19732231800 | 100 |  |  | 1 | 1537.25 | 1454.91 | 0 | 82.34 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19731461500 |  | 501007837 |  | 6708204F | 0677701 |  |  | 565 | EX | REPLACE SERVICE | 2621P | RENAISSANCE | 104 RENAISSANCE CT | 113 | NIC | 2019-08-12 | U125208 | U125208 | 2019-08-08 | 2019-08-09 |  |  | ATWILLI | 2019-08-09 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 11.4 | 2 | 963.34 | 689.76 | 0 | 138.22 | 135.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19731819300 |  | 100340492 |  | 6724212E |  |  |  | 565 | EX | REPLACE SERV LINE | 2621P | ATLANTA | 1617 ATLANTA DR | 067 | LEX | 2019-08-09 | ATWILLI | U129939 | 2019-08-09 | 2019-08-09 |  |  | ATWILLI | 2019-08-09 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.86667 | 1 | 724.86 | 50.99 | 570.18 | 2.89 | 100.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19732231800 |  | 100340469 |  | 6724212E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | FORT SUMTER | 1615 FORT SUMTER DR | 067 | LEX | 2019-08-12 | U125208 | U125208 | 2019-08-12 | 2019-08-07 | 2019-08-07 |  | ATWILLI | 2019-08-09 | 2019-08-08 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 27 | 5 | 47.04 | 0 | 0 | 0 | 47.04 | 0 | 0 | 0
KY | KY - WEST | 2623 | 17026708400 |  |  |  | 6684228L | 1744517 | U127466 |  | 577 | EX | INSTALL FENCE FOR R1862 | 2600E | GLENNS CREEK | 110 GLENNS CREEK RD | 073 | FRA | 2019-08-12 | U462463 | U127466 | 2017-05-03 | 2017-12-29 | 2017-12-31 | 2018-12-01 | CYNTHIA FARIS | 2019-08-10 | 2018-04-12 |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00577 | 3207713 |  |  | WP7084 | AMRCB |  | 100 | 771332170267084 | 34.0833 | 6 | 28589.69 | 1886.47 | 0 | 1050.96 | 21708.07 | 0 | 239.46 | 3704.73
KY | KY - WEST | 2621 | 19701431900 |  | 100312446 |  | 6716208E | 1749637 | U131066 |  | 565 | EX | RPLC SL/18026754700/D000119 | 2600B | SOUTHLAND | 527 SOUTHLAND DR 1FL | 067 | LEX | 2019-11-04 | U125527 | U131066 | 2019-04-30 | 2019-08-09 | 2019-08-09 |  | ASNICHO | 2019-08-10 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26210021 | 10.3 | 3 | 1511.76 | 1095.24 | 225.87 | 62.01 | 128.64 | 0 | 0 | 0
KY | KY - WEST | 2623 | 17026708300 |  |  |  | 6684228L | 1744517 | U127466 |  | 575 | EX | LAND FOR R1862 | 2600E | GLENNS CREEK | 110 GLENNS CREEK RD | 073 | FRA | 2019-08-12 | U462463 | U127466 | 2017-05-03 | 2017-12-29 | 2017-12-31 | 2019-08-12 | LAND SERVICES | 2019-08-12 |  |  | F | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00575 | 3207713 |  |  | WP7083 | AMRCB |  | 100 | 771332170267083 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18588356200 |  | 100357498 |  | 6740232M | 1745023 |  |  | 566 | EX | ABN SL/17026708900/ | 2621P | 8TH | 808 E 8TH ST | 017 | PAR | 2019-08-12 | DBANKS | U131066 | 2018-02-19 | 2019-08-12 |  |  | DBANKS | 2019-08-12 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26290043 | 12.05 | 5 | 569.92 | 510.22 | 30.85 | 28.85 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18616890400 |  | 100303895 | 19 | 6712208D | 1635077 |  |  | 565 | EX | AOC - CORROSION ON STL RISER | 2621P | HONEYSUCKLE | 837 HONEYSUCKLE RD | 067 | LEX | 2019-08-14 | U125208 | MAWAN | 2018-06-02 | 2018-07-03 | 2018-07-03 |  | LSTANFI | 2019-08-12 | 2018-06-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18.8167 | 4 | 1294.82 | 886.56 | 306.23 | 50.19 | 51.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026878200 |  |  |  | 6716208B | 1963991 | U131983 |  | 557 | EX | INSTALL 55' OF 3"PMLP MAIN | 2621P | MOCKINGBIRD | 364 MOCKINGBIRD LN | 067 | LEX | 2019-12-05 | U460266 | U461383 | 2019-05-20 | 2019-12-26 | 2021-01-01 | 2019-08-12 | JENSMIN | 2019-08-12 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP8782 | AMRCB |  | 100 | 055732190268782 | 2.3167 | 56 | 4487.67 | 212.59 | 1227.97 | 151.75 | 2450.02 | 0 | 3.51 | 441.83 | 56
KY | KY - WEST | 2621 | 19026878300 |  |  |  | 6716208B | 1963991 | U131983 |  | 558 | EX | RETIRE 40' OF 4"BSLP MAIN | 2621P | MOCKINGBIRD | 364 MOCKINGBIRD LN | 067 | LEX | 2019-10-09 | U460266 | U461383 | 2019-05-20 | 2019-12-31 | 2021-01-01 | 2019-08-12 | JENSMIN | 2019-08-12 | 2019-08-06 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP8783 | AMRCB |  | 100 | 055832190268783 | 38.9667 | 0 | 25405.15 | 4566.71 | 0 | 1625.77 | 19212.67 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19026885300 |  |  |  | 7240212B | 1965273 | U131983 |  | 557 | EX | INSTALL 340' OF 2"PMLP | 2621P | MAYSVILLE | S MAYSVILLE ST | 173 | MT | 2019-08-23 | U123258 | U131983 | 2019-07-16 | 2019-12-26 | 2019-12-31 | 2019-08-01 | DENNING | 2019-08-12 | 2019-07-29 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP8853 | AMRCB |  | 100 | 055732190268853 | 144.95 | 7770 | 15057.16 | 7402.83 | 3242.38 | 2572.69 | 332.16 | 0 | 19.89 | 1487.21 | 259
KY | KY - WEST | 2621 | 19678792100 |  | 100299061 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | PEPPER | 243 PEPPER DR | 067 | LEX | 2019-08-12 | U461327 | U131066 | 2019-02-01 | 2019-11-27 |  |  | WBURCHETT | 2019-08-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4 | 1 | 1812.44 | 228.87 | 0 | 75.22 | 1508.35 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678792200 |  | 100299075 |  | 16716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | PEPPER | 244 PEPPER DR | 067 | LEX | 2019-08-12 | U461327 | U131066 | 2019-02-01 | 2019-11-27 |  |  | WBURCHETT | 2019-08-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.4833 | 1 | 1398.46 | 199.11 | 0 | 65.46 | 1133.89 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678792300 |  | 100299060 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | PEPPER | 247 PEPPER DR | 067 | LEX | 2019-08-12 | U461327 | U131066 | 2019-02-01 | 2019-11-27 |  |  | WBURCHETT | 2019-08-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.0167 | 1 | 1090.45 | 230.01 | 0 | 75.61 | 784.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680088000 |  | 100320190 |  | 6716208G | 1748686 |  |  | 565 | EX | REPLACE SL W/17026736100 | 2600B | SHADY | 108 SHADY LN | 067 | LEX | 2019-08-12 | U126284 | U131066 | 2019-02-07 | 2019-12-31 |  |  | JOSH PASLEY | 2019-08-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.4333 | 1 | 2832.62 | 81.46 | 0 | 10.13 | 2741.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680088200 |  | 100320241 |  | 6716208G | 1748686 |  |  | 565 | EX | REPLACE SL W/17026736100 | 2600B | SHADY | 111 SHADY LN | 067 | LEX | 2019-08-12 | U126284 | U131066 | 2019-02-07 | 2019-12-31 |  |  | JOSH PASLEY | 2019-08-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.4833 | 1 | 3161.01 | 140.3 | 0 | 17.45 | 3003.26 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689089000 |  | 100255614 |  | 7348264H | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | 1ST | 708 N 1ST ST | 089 | FLA | 2019-08-12 | U124015 | U131066 | 2019-03-18 | 2019-08-12 |  |  | ORA SLONE | 2019-08-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.88333 | 1 | 1733.14 | 49.39 | 0 | 6.22 | 1677.53 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689093800 |  | 100255810 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | TURLEY | 1013 TURLEY AV | 089 | FLA | 2019-08-12 | U125566 | U131066 | 2019-03-18 | 2019-08-12 |  |  | DAVID SKAGGS | 2019-08-12 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 1.4333 | 1 | 1885.41 | 80.1 | 0 | 10.05 | 1795.26 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19707674900 |  | 100290198 |  | 6720212C | 1855586 |  |  | 565 | EX | RPLC SL/18026795700/ | 2600B | EDGELAWN | 1434 EDGELAWN AV | 067 | LEX | 2019-08-28 | U461423 | U131066 | 2019-05-21 | 2019-11-27 |  |  | KKOUNS | 2019-08-12 | 2019-08-12 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 18 | 2 | 2226.44 | 1036.89 | 0 | 338.92 | 850.63 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19729750600 |  | 100285594 |  | 6768172A |  |  |  | 565 | EX | REPLACE SERVICE LINE - D097371 | 2621P | BROADWAY | 611 BROADWAY ST | 065 | IRV | 2019-08-14 | JTOY | U125208 | 2019-08-02 | 2019-08-05 | 2019-08-23 |  | DENNING | 2019-08-12 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 31.5333 | 4 | 2452.94 | 1493.04 | 203.46 | 683.48 | 72.96 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19732157500 |  | 100273085 |  | 6680224D |  |  |  | 565 | EX | REPLACE SERVICE | 2621P | WOODHILL | 234 WOODHILL LN | 073 | FRA | 2019-08-12 | CDESPAI | U131169 | 2019-08-12 | 2019-08-12 |  |  | CDESPAI | 2019-08-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 6.5833 | 1 | 4332.38 | 415.19 | 558.55 | 613.81 | 2744.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 03527280800 |  | 100294407 |  | 6720212E |  |  |  | 566 | EX | SOII-ABN / NEED FLAGGERS | 2621P | LIMESTONE | 563 N LIMESTONE ST | 067 | LEX | 2019-08-13 | JPARSON | DMCCULL | 2003-01-09 | 2019-08-30 |  |  | JPARSON | 2019-08-13 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.4 | 2 | 4437.36 | 378.72 | 0 | 21.42 | 4037.22 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 12980741800 |  | 100355309 |  | 7260280O | 1640955 |  |  | 566 | EX | ABANDON SL/16026678200 | 2600B | CARMEL | 307 CARMEL ST | 161 | MAY | 2019-08-13 | SDADAMS | U125208 | 2012-07-18 | 2019-08-13 |  |  | SDADAMS | 2019-08-13 |  |  | B | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 0.6 | 2 | 34.86 | 33 | 0 | 1.86 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19026866200 |  |  |  | 6736228G | 1851755 | BKSLONE |  | 561 | EX | INSTALL TWO 2" SS | 2600B | SUMMIT | 605 SUMMIT DR REAR | 017 | PAR | 2019-08-20 | U123258 | BKSLONE | 2019-03-17 | 2019-09-09 | 2019-09-13 | 2019-08-12 | WGRAVES | 2019-08-13 | 2019-08-08 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00561 | 3200561 |  |  | WP8662 |  |  | 100 | 056132190268662 | 45.6667 | 0 | 41712.88 | 5128.38 | 17477.53 | 2577.73 | 12327.65 | 0 | 86.73 | 4114.86
KY | KY - CENTRAL | 2629 | 19026866300 |  |  |  | 6736228G | 1851755 | BKSLONE |  | 562 | EX | RETIRE 56'-2" CSMP | 2600B | SUMMIT | 605 SUMMIT DR REAR | 017 | PAR | 2019-08-20 | U123258 | BKSLONE | 2019-03-17 | 2019-09-13 | 2019-09-13 | 2019-08-12 | WGRAVES | 2019-08-13 | 2019-08-12 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00562 | 3200562 |  |  | WP8663 |  |  | 100 | 056232190268663 | 2.0667 | 0 | 149.73 | 111.35 | 0 | 38.38 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671932700 |  | 100353764 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | SUTTON | 218 SUTTON ST | 161 | MAY | 2019-08-16 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-08-13 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1086.64 | 0 | 0 | 0 | 1086.64 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671932900 |  | 100353992 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | SUTTON | 226 SUTTON ST | 161 | MAY | 2019-08-26 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-08-13 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1052.88 | 0 | 0 | 0 | 1052.88 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671942500 |  | 100353765 |  | 7256280L | 1747939 |  |  | 565 | EX | REPLACE SL W/17026728200 | 2600B | SUTTON | 216 SUTTON ST | 161 | MAY | 2019-08-22 | U125208 | U131066 | 2019-01-22 | 2019-12-31 |  |  | DAVID STAGGS | 2019-08-13 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1118.7 | 0 | 0 | 0 | 1118.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 17490477400 |  | 100297742 | 27 | 6716212H | 1855598 |  |  | 565 | EX | REPLACE SL W/18026796000 | 2600B | MILL | 243 N MILL ST | 067 | LEX | 2019-08-14 | U126285 | JLYNN | 2017-03-21 | 2019-12-31 |  |  | DDAVIS | 2019-08-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5 | 1 | 2547.9 | 293.15 | 914.47 | 94.42 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 17518026300 |  | 100346868 |  | 6696212K | 1638340 |  |  | 565 | EX | REPL SL/MOVE MTR - PITTED | 2621P | MAPLE | 110 MAPLE AV | 239 | VER | 2019-08-14 | EFGOINS | U125208 | 2017-06-22 | 2017-12-29 |  |  | EFGOINS | 2019-08-14 | 2019-08-13 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 28.4667 | 8 | 2020 | 1641.29 | 285.82 | 92.89 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026878600 |  | 500636883 |  | 6720212N | 1854827 | U461383 |  | 555 | EX | INSTALL 320' OF 4"PMLP MAIN | 2600B | NATIONAL | 951 NATIONAL AV NEW | 067 | LEX | 2019-10-02 | U460266 | U461383 | 2019-05-23 | 2019-07-30 | 2019-08-14 | 2019-08-07 | KKOUNS | 2019-08-14 | 2019-08-07 | 2019-07-31 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP8786 | AMRCB |  | 100 | 055532190268786 | 9.0167 | 634 | 36710.05 | 517.69 | 1469.05 | 63.77 | 30867.36 | 0 | 84.27 | 3707.91 | 317
KY | KY - CENTRAL | 2632 | 19671942300 |  | 100353769 |  | 7256280L | 1747939 |  |  | 565 | EX | REPLACE SL W/17026728200 | 2600B | SUTTON | 212 SUTTON ST | 161 | MAY | 2019-08-26 | U461478 | U131066 | 2019-01-22 | 2019-12-31 |  |  | DAVID STAGGS | 2019-08-14 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1487.63 | 0 | 0 | 0 | 1487.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678791800 |  | 100299073 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | PEPPER | 236 PEPPER DR | 067 | LEX | 2019-08-14 | U127414 | U131066 | 2019-02-01 | 2019-11-27 |  |  | ED FOX | 2019-08-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1823.79 | 0 | 0 | 0 | 1823.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678822600 |  | 100299071 |  | 6716212B | 1855322 |  |  | 565 | EX | REPLACE SL W/18026792400 | 2600B | PEPPER | 228 PEPPER DR | 067 | LEX | 2019-08-14 | U126286 | U131066 | 2019-02-01 | 2019-12-31 |  |  | TYLER ALLISON | 2019-08-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1481.01 | 0 | 0 | 0 | 1481.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680087600 |  | 100320244 |  | 6716208G | 1748686 |  |  | 565 | EX | REPLACE SL W/17026736100 | 2600B | SHADY | 105 SHADY LN | 067 | LEX | 2019-08-14 | U126284 | U131066 | 2019-02-07 | 2019-12-31 |  |  | JOSH PASLEY | 2019-08-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.5 | 1 | 2754.23 | 311.18 | 0 | 38.68 | 2404.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680087700 |  | 100320189 |  | 6716208G | 1748686 |  |  | 565 | EX | REPLACE SL W/17026736100 | 2600B | SHADY | 106 SHADY LN | 067 | LEX | 2019-08-14 | U126284 | U131066 | 2019-02-07 | 2019-12-31 |  |  | JOSH PASLEY | 2019-08-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.5 | 1 | 2547.32 | 367.72 | 0 | 45.73 | 2133.87 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689089700 |  | 100255617 |  | 7348264H | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | 1ST | 723 N 1ST ST | 089 | FLA | 2019-08-14 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-08-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.51667 | 1 | 1848.9 | 28.34 | 0 | 3.56 | 1817 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691664900 |  | 100328218 |  | 6720208B | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | CULPEPPER | 229 CULPEPPER RD | 067 | LEX | 2019-08-15 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-08-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2318.09 | 0 | 0 | 0 | 2318.09 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19707674700 |  | 100290212 |  | 6720212C | 1855586 |  |  | 565 | EX | RPLC SL/18026795700/ | 2600B | EDGELAWN | 1431 EDGELAWN AV | 067 | LEX | 2019-08-29 | U461423 | U131066 | 2019-05-21 | 2019-11-27 |  |  | KKOUNS | 2019-08-14 | 2019-08-14 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12 | 1 | 1841.37 | 691.25 | 0 | 225.96 | 924.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19711109600 |  | 100297743 |  | 6716212H | 1855598 |  |  | 565 | EX | RPLC SL/18026796000/ | 2600B | MILL | 247 N MILL ST | 067 | LEX | 2019-08-14 | U126285 | U131066 | 2019-06-03 | 2019-11-27 |  |  | DDAVIS | 2019-08-14 | 2019-08-14 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.25 | 1 | 1730.34 | 366.44 | 0 | 118.04 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19723712300 |  | 100306358 |  | 6712212L |  |  |  | 565 | EX | SERVICE LINE REPLACE/MMO | 2621P | MASON HEADLEY | 934 MASON HEADLEY RD | 067 | LEX | 2019-08-14 | LSTANFI | U131723 | 2019-07-12 | 2019-08-30 |  |  | LSTANFI | 2019-08-14 | 2019-08-14 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14 | 2 | 3353.72 | 848.92 | 281.71 | 48.04 | 2175.05 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19729983400 |  | 100338197 |  | 6720212F |  |  |  | 566 | EX | ABANDON / RA 08-06-19 / CONVRT | 2621P | BRECKENRIDGE | 405 BRECKENRIDGE ST | 067 | LEX | 2019-08-14 | CWEMPE | U132002 | 2019-08-05 | 2019-09-12 | 2019-10-03 |  | CWEMPE | 2019-08-14 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 10.6833 | 2 | 785.89 | 610.44 | 140.91 | 34.54 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19731440800 |  | 100252268 |  | 7348264L |  |  |  | 566 | EX | DEMO / IDLE / ABANDON | 2621P | HIGHLAND | 706 HIGHLAND AV | 089 | FLA | 2019-08-14 | AMCCORM | U130722 | 2019-08-08 | 2019-09-19 | 2019-10-10 |  | AMCCORM | 2019-08-14 | 2019-08-13 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 15.1667 | 3 | 1397.17 | 908.65 | 1.17 | 487.35 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19731602100 |  | 100316200 |  | 6716208F | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMED D093804 | 2621D | KOSTER | 226 KOSTER DR | 067 | LEX | 2019-08-21 | U125208 | AOC SYST | 2019-08-08 | 2019-08-09 | 2019-08-29 |  | WHIMES | 2019-08-14 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.5333 | 2 | 1485.25 | 980.75 | 390.43 | 55.51 | 58.56 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19732491500 |  | 100273531 |  | 6680224F |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | SHARON | 206 SHARON RD | 073 | FRA | 2019-08-14 | CDESPAI | U131367 | 2019-08-13 | 2019-04-05 | 2020-10-31 |  | CDESPAI | 2019-08-14 | 2019-08-13 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8.6333 | 2 | 5237.9 | 543.72 | 499.25 | 803.82 | 3391.11 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19732495900 |  | 100405526 |  | 6688228O |  |  |  | 565 | EX | SERVICE LINE - REPLACE CDESPAI | 2621P | ENTRADA | 1013 ENTRADA DR | 073 | FRA | 2019-08-14 | CDESPAI | U125208 | 2019-08-13 | 2019-08-13 |  |  | CDESPAI | 2019-08-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.3833 | 1 | 5464.41 | 338.98 | 223.69 | 501.08 | 4400.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19732500500 |  | 100293901 |  | 6720212A |  |  |  | 566 | EX | RETIRE SERVICE LINE - D000715 | 2621P | RUSSELL CAVE | 890 RUSSELL CAVE RD | 067 | LEX | 2019-08-21 | U125208 | U131367 | 2019-08-13 | 2019-11-15 | 2021-05-31 |  | JWCOX | 2019-08-14 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26210043 | 6.8333 | 2 | 3526.22 | 389.18 | 51.3 | 22 | 3063.74 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19732838500 |  | 100273532 |  | 6680224F |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | SHARON | 196 SHARON RD | 073 | FRA | 2019-08-14 | CDESPAI | U129005 | 2019-08-14 | 2019-08-14 |  |  | CDESPAI | 2019-08-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.93333 | 1 | 2053.19 | 59.22 | 209.51 | 87.55 | 1696.91 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19732900400 |  | 100255618 |  | 7348264H |  |  |  | 566 | EX | REPLACE SERVICE | 2621P | 1ST | 721 N 1ST ST | 089 | FLA | 2019-08-14 | U124015 | U131168 | 2019-08-14 | 2019-08-14 |  |  | ORA SLONE | 2019-08-14 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.5 | 1 | 110.7 | 28.34 | 0 | 3.56 | 78.8 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19732906400 |  | 100255827 |  | 7348264L | 1859009 |  |  | 565 | VO | REPLACE SL W/18026843700 | 2621P | TURLEY | 829 TURLEY AV | 089 | FLA | 2019-08-15 |  | U131168 | 2019-08-14 | 2019-08-14 |  |  | DAVID SKAGGS | 2019-08-14 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.11667 | 1 | 8.77 | 7.79 | 0 | 0.98 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19732910800 |  | 100463350 |  | 7344244M |  |  |  | 565 | EX | REPLACE SERVICE | 2621P | STATE RT 854 | 15650 STATE RT 854 | 019 | RUS | 2019-08-21 | U125208 | U131168 | 2019-08-14 | 2019-08-14 |  |  | MCOLLET | 2019-08-14 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 0.65 | 1 | 397.7 | 40.11 | 183.61 | 41.5 | 132.48 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18026848501 |  | 500941977 |  | 6716232J | 1859545 | U461383 |  | 555 | EX | INSTALL 7400' OF 2"/4"/6"PMMP | 2600B | ROCKY CREEK | ROCKY CREEK RD 306 | 209 | GEO | 2019-09-05 | U128132 | U461383 | 2019-06-25 | 2019-02-04 | 2019-08-09 | 2019-08-06 | JDUNN | 2019-08-15 | 2019-07-19 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP8485 |  |  | 100 | 055532180268485 | 699.3667 | 655864 | 573876.27 | 39888.31 | 28112.31 | 5574.78 | 423725.52 | 0 | 5956.29 | 70619.06 | 7453
KY | KY - CENTRAL | 2632 | 19671932800 |  | 100353763 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | SUTTON | 220 SUTTON ST | 161 | MAY | 2019-08-26 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-08-15 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1380 | 0 | 0 | 0 | 1380 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678791000 |  | 100299067 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | PEPPER | 215 PEPPER DR | 067 | LEX | 2019-08-15 | U126286 | U131066 | 2019-02-01 | 2019-11-27 |  |  | TYLER ALLISON | 2019-08-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1637.31 | 0 | 0 | 0 | 1637.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678791100 |  | 100299068 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | PEPPER | 220 PEPPER DR | 067 | LEX | 2019-08-15 | U126286 | U131066 | 2019-02-01 | 2019-11-27 |  |  | TYLER ALLISON | 2019-08-15 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1895.93 | 0 | 0 | 0 | 1895.93 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689089300 |  | 100255620 |  | 7348264H | 1859009 |  |  | 566 | EX | ABND SL/18026843700/ | 2600B | 1ST | 713 N 1ST ST | 089 | FLA | 2019-08-15 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-08-15 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 | 0.3 | 1 | 98.79 | 17.76 | 0 | 2.23 | 78.8 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689089400 |  | 100255616 |  | 7348264H | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | 1ST | 716 N 1ST ST | 089 | FLA | 2019-08-15 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-08-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.76667 | 1 | 2435.57 | 42.21 | 0 | 5.3 | 2388.06 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689092600 |  | 100255827 |  | 7348264L | 1859009 |  |  | 565 | EX | REPLACE SL W/18026843700 | 2600B | TURLEY | 829 TURLEY AV | 089 | FLA | 2019-08-15 | U125566 | U131066 | 2019-03-18 | 2019-11-27 |  |  | DAVID SKAGGS | 2019-08-15 | 2019-08-14 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.71667 | 2 | 1725.24 | 38.97 | 0 | 4.9 | 1681.37 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689092700 |  | 100255824 |  | 7348264L | 1859009 |  |  | 565 | EX | REPLACE SL/18026843700/ | 2600B | TURLEY | 832 TURLEY AV | 089 | FLA | 2019-08-15 | U125566 | U131066 | 2019-03-18 | 2019-11-27 |  |  | DAVID SKAGGS | 2019-08-15 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.26667 | 1 | 2064.18 | 15.57 | 0 | 1.96 | 2046.65 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19707675000 |  | 100290210 |  | 6720212C | 1855586 |  |  | 565 | EX | RPLC SL/18026795700/ | 2600B | EDGELAWN | 1437 EDGELAWN AV | 067 | LEX | 2019-08-28 | U461423 | U131066 | 2019-05-21 | 2019-11-27 |  |  | KKOUNS | 2019-08-15 | 2019-08-15 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.25 | 1 | 2268.54 | 590.45 | 0 | 192.99 | 1485.1 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19724694900 |  | 500836232 |  | 7348248A | 0355162 |  |  | 565 | EX | NBT - UPG SL & MTR | 2621P | DONNA | 2201 DONNA DR A | 019 | ASH | 2019-08-22 | U125208 | U125208 | 2019-07-17 | 2019-07-16 | 2019-08-12 |  | MCOLLET | 2019-08-15 | 2019-07-22 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 51.6833 | 11 | 5016.17 | 3028.18 | 589.25 | 1296.98 | 101.76 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19729936800 |  | 100318865 |  | 6716204B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D107495 | 2621P | TARTAN | 107 TARTAN DR | 067 | LEX | 2019-08-21 | U125208 | U125208 | 2019-08-05 | 2019-08-08 | 2019-08-26 |  | CWEMPE | 2019-08-15 | 2019-08-15 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 31.85 | 2 | 3166.99 | 1890.44 | 747.27 | 414.08 | 115.2 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19733119100 |  | 500746999 |  | 7344244M |  |  |  | 566 | EX | ABANDON IDLE MANIFOLD-NOT USED | 2621P | STATE RT 854 | 15650< STATE RT 854 | 019 | RUS | 2019-08-15 | MCOLLET | DYOUNG | 2019-08-15 | 2019-08-14 |  |  | MCOLLET | 2019-08-15 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.3 | 1 | 33.01 | 18.53 | 0 | 14.48 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 06645393800 |  | 100290211 |  | 16720212C |  |  |  | 566 | EX | ABANDON SERVICE | 2600B | EDGELAWN | 1433 EDGELAWN AV | 067 | LEX | 2019-08-28 | U461423 | SSUTHER | 2006-04-21 | 2020-12-31 |  |  | KKOUNS | 2019-08-16 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 567.03 | 0 | 0 | 0 | 567.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 17507974500 |  | 100326691 |  | 6720208B | 1855692 |  |  | 565 | EX | REPL SERV W/1W,3,4 | 2621P | FONTAINE | 1512 FONTAINE RD 1E | 067 | LEX | 2019-08-16 | U126284 | U125208 | 2017-05-19 | 2018-12-26 |  |  | JOSH PASLEY | 2019-08-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.8167 | 3 | 5140.95 | 233.76 | 0 | 67.65 | 4839.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18599698000 |  | 100286892 | 15 | 6720212B |  |  |  | 565 | EX | REPL S/L - UNMETERED GAS | 2621P | CARLISLE | 128 CARLISLE AV | 067 | LEX | 2019-08-16 | JWCOX | NRICHIE | 2018-04-02 | 2019-08-16 |  |  | JWCOX | 2019-08-16 | 2018-04-11 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.2167 | 2 | 3580.48 | 780.24 | 187.13 | 123.03 | 2490.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026864500 |  |  |  | 6716208E | 1749637 | U122858 |  | 562 | EX | RETIRE 497'-4" CSLP | 2600B | SOUTHLAND DRIVE | SOUTHLAND DRIVE | 067 | LEX | 2019-10-24 | U128132 | U122858 | 2019-03-04 | 2019-08-30 | 2019-08-30 | 2019-09-10 | APARRIS | 2019-08-16 | 2019-09-09 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP8645 |  |  | 100 | 056232190268645 | 8.5833 | 0 | 611 | 494.02 | 0 | 116.98 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671933000 |  | 100430337 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | SUTTON | 227 SUTTON ST 1FN | 161 | MAY | 2019-08-26 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-08-16 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1980.12 | 0 | 0 | 0 | 1980.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673607600 |  | 100310465 |  | 6712208L | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2849 CLAYS MILL RD | 067 | LEX | 2019-08-16 | U126602 | U131066 | 2019-01-30 | 2019-11-27 |  |  | DEREK PAYTON | 2019-08-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 4371.32 | 0 | 240.55 | 0 | 4130.77 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678822900 |  | 100299056 |  | 6716216N | 1855322 |  |  | 565 | EX | REPLACE SL W/1802679400 | 2600B | PEPPER | 263 PEPPER DR | 067 | LEX | 2019-08-19 | U127414 | U131066 | 2019-02-01 | 2019-12-31 |  |  | TYLER ALLISON | 2019-08-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 1191.09 | 0 | 0 | 0 | 1191.09 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689089500 |  | 100255619 |  | 7348264H | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | 1ST | 717 N 1ST ST | 089 | FLA | 2019-08-16 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-08-16 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.46667 | 1 | 1287.09 | 26.08 | 0 | 3.25 | 1257.76 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19705068100 |  | 100467255 |  | 6688228A |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094017 | 2621P | COLONIAL | 512 COLONIAL TC | 073 | FRA | 2019-08-22 | U125208 | U125208 | 2019-05-10 | 2019-08-16 | 2021-05-31 |  | BJLONE | 2019-08-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.0667 | 1 | 2112.68 | 294.13 | 153.96 | 16.64 | 1647.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19707674600 |  | 100290197 |  | 6720212C | 1855586 |  |  | 565 | EX | RPLC SL/18026795700/ | 2600B | EDGELAWN | 1424 EDGELAWN AV | 067 | LEX | 2019-08-29 | U461423 | U131066 | 2019-05-21 | 2019-11-27 |  |  | KKOUNS | 2019-08-16 | 2019-08-16 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 1539.49 | 460.85 | 0 | 150.64 | 928 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19732244300 |  | 100277310 |  | 6684228G |  |  |  | 566 | EX | DEMO / ABANDON / RI 08-13-19 | 2621P | HOLMES | 215 HOLMES ST | 073 | FRA | 2019-08-22 | U125208 | U132002 | 2019-08-12 | 2019-09-23 | 2019-10-14 |  | EFGOINS | 2019-08-16 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 1.4667 | 1 | 102.06 | 83.81 | 13.51 | 4.74 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19732311600 |  | 100319967 |  | 6716208K | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER / | 2621D | JESSELIN | 333 JESSELIN DR | 067 | LEX | 2019-08-22 | U125208 | AOC SYST | 2019-08-12 | 2019-09-06 | 2019-10-08 |  | WHIMES | 2019-08-16 | 2019-08-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 12.1667 | 2 | 1107.04 | 738.35 | 326.87 | 41.82 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19733597100 |  | 100259427 |  | 7344148J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CEDAR | 61 CEDAR LN | 071 | DRI | 2019-08-16 | BBMULLI | U125964 | 2019-08-16 | 2019-08-09 | 2019-08-29 |  | BBMULLI | 2019-08-16 |  |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 19.95 | 3 | 412.47 | 390.38 | 0 | 22.09 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671927400 |  | 100353704 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | 2ND | 101< W 2ND ST W | 161 | MAY | 2019-08-26 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | ED FOX | 2019-08-19 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1325.31 | 0 | 0 | 0 | 1325.31 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671932500 |  | 100353699 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | SUTTON | 119 SUTTON ST | 161 | MAY | 2019-08-26 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | ED FOX | 2019-08-19 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1234.57 | 0 | 0 | 0 | 1234.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673606700 |  | 100311737 |  | V930-50 | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2800 CLAYS MILL RD | 067 | LEX | 2019-08-19 | U126602 | U131066 | 2019-01-30 | 2019-08-19 |  |  | DEREK PAYTON | 2019-08-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.2333 | 2 | 5378.14 | 70.9 | 256.3 | 4.01 | 5046.93 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678792600 |  | 100299057 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | PEPPER | 259 PEPPER DR | 067 | LEX | 2019-08-27 | U126286 | U131066 | 2019-02-01 | 2019-11-27 |  |  | TYLER ALLISON | 2019-08-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1100.83 | 0 | 0 | 0 | 1100.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678792700 |  | 100299055 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | PEPPER | 267 PEPPER DR | 067 | LEX | 2019-08-19 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-08-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.3667 | 1 | 1509.97 | 179.06 | 0 | 62.6 | 1268.31 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689090100 |  | 100255790 |  | 7348264H | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | ARGILLITE | 534 ARGILLITE RD | 089 | FLA | 2019-08-19 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-08-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.48333 | 1 | 1875.2 | 27.77 | 0 | 3.48 | 1843.95 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691672700 |  | 100326553 |  | 6720208A | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1380 FONTAINE RD | 067 | LEX | 2019-08-19 | U126284 | U131066 | 2019-03-27 | 2019-11-27 |  |  | JOSH PASLEY | 2019-08-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.7333 | 1 | 2504.99 | 211.61 | 0 | 26.31 | 2267.07 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691697200 |  | 100326554 |  | 6720208B | 1855692 |  |  | 565 | EX | REPLACE SL W/18026796400 | 2600B | FONTAINE | 1384 FONTAINE RD | 067 | LEX | 2019-08-19 | U126284 | U131066 | 2019-03-27 | 2019-12-31 |  |  | JOSH PASLEY | 2019-08-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.33333 | 1 | 2296.71 | 18.68 | 0 | 2.32 | 2275.71 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19707674200 |  | 100290191 |  | 6720212B | 1855586 |  |  | 565 | EX | RPLC SL/18026795700/ | 2600B | EDGELAWN | 1412 EDGELAWN AV | 067 | LEX | 2019-08-29 | U461423 | U131066 | 2019-05-21 | 2019-11-27 |  |  | KKOUNS | 2019-08-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 1528.93 | 460.85 | 0 | 150.64 | 917.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19711113200 |  | 100297739 |  | 6716212H | 1855598 |  |  | 565 | EX | REPLACE SL W/18026796000 | 2600B | MILL | 231 N MILL ST FT | 067 | LEX | 2019-08-19 | U126285 | U131066 | 2019-06-03 | 2019-12-31 |  |  | DDAVIS | 2019-08-19 | 2019-08-19 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25 | 2 | 4522.4 | 1465.84 | 611.27 | 472.18 | 1973.11 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19733934600 |  | 100268140 |  | 7356256C |  |  |  | 565 | EX | GRADE 1 REPLACE SERV | 2621P | WINCHESTER | 2737 WINCHESTER AV | 019 | ASH | 2019-08-19 | MCOLLET | U129939 | 2019-08-18 | 2019-08-17 | 2019-08-17 |  | MCOLLET | 2019-08-19 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 32 | 4 | 3777.87 | 1907.22 | 334.88 | 839.95 | 695.82 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19733944900 |  | 100282887 |  | 6712228C |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | MILITARY | 514 MILITARY ST | 209 | GEO | 2019-08-19 | CDESPAI | U125208 | 2019-08-19 | 2019-08-19 |  |  | CDESPAI | 2019-08-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.8667 | 1 | 4784.12 | 432.78 | 328.75 | 639.87 | 3382.72 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 09809426800 |  | 100355256 |  | 7260280N |  |  |  | 566 | EX | DEMO / IDLE / ABN - CD ENFRCMN | 2621P | FOREST | 1217 FOREST AV | 161 | MAY | 2019-08-20 | SDADAMS | RPOLLY | 2009-10-27 | 2020-12-31 |  |  | SDADAMS | 2019-08-20 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 11.85 | 2 | 724.61 | 652.18 | 35.55 | 36.88 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 09809426900 |  | 500519858 |  | 7260280N |  |  |  | 566 | EX | ABANDON / RI 11-10-2006 | 2621P | FOREST | 1217< FOREST AV | 161 | MAY | 2019-08-20 | SDADAMS | RPOLLY | 2009-10-27 | 2020-12-31 |  |  | SDADAMS | 2019-08-20 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 8.5667 | 3 | 510.85 | 449.83 | 35.55 | 25.47 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19026873300 |  | 501264465 |  | 6700208A | 1962993 | U461383 |  | 555 | EX | INSTALL 4000' OF 2"PMMP MAIN | 2600B | ELMWOOD | 2004 ELMWOOD DR | 239 | VER | 2019-10-24 | U460266 | U461383 | 2019-04-24 | 2019-06-12 | 2019-08-21 | 2019-08-16 | BPULLIAM/STANLEY PIPELINE | 2019-08-20 | 2019-07-08 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP8733 |  |  | 100 | 055532190268733 | 250.6833 | 128724 | 186876.14 | 14368.98 | 6194.89 | 5537.74 | 138186.59 | 0 | 839.55 | 21748.39 | 3786
KY | KY - CENTRAL | 2632 | 19671929500 |  | 100353611 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | FRONT | 110 W FRONT ST | 161 | MAY | 2019-08-26 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | ED FOX | 2019-08-20 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1165.55 | 0 | 0 | 0 | 1165.55 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671932400 |  | 100405202 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | SUTTON | 116 SUTTON ST | 161 | MAY | 2019-08-26 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | ED FOX | 2019-08-20 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1644.63 | 0 | 0 | 0 | 1644.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678792400 |  | 100299059 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | PEPPER | 251 PEPPER DR | 067 | LEX | 2019-08-20 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-08-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.8833 | 1 | 2263.85 | 100.43 | 0 | 35.12 | 2128.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678792500 |  | 100299058 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | PEPPER | 255 PEPPER DR | 067 | LEX | 2019-08-20 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-08-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.1 | 1 | 1351.98 | 5.31 | 0 | 1.86 | 1344.81 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687824500 |  | 100280023 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | MAGNOLIA | 316 MAGNOLIA ST | 073 | FRA | 2019-08-20 | U126284 | U131066 | 2019-03-13 | 2019-11-27 |  |  | JOSH PASLEY | 2019-08-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.7833 | 1 | 1359.48 | 100.69 | 0 | 12.52 | 1246.27 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687824800 |  | 100280016 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | MAGNOLIA | 319 MAGNOLIA ST | 073 | FRA | 2019-08-20 | U126284 | U131066 | 2019-03-13 | 2019-11-27 |  |  | JOSH PASLEY | 2019-08-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.6833 | 1 | 1442.05 | 95.05 | 0 | 11.81 | 1335.19 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687824900 |  | 100280020 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | MAGNOLIA | 320 MAGNOLIA ST | 073 | FRA | 2019-08-20 | U126284 | U131066 | 2019-03-13 | 2019-11-27 |  |  | JOSH PASLEY | 2019-08-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.15 | 1 | 2634.15 | 66.17 | 0 | 8.24 | 2559.74 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687825000 |  | 100280017 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | MAGNOLIA | 321 MAGNOLIA ST | 073 | FRA | 2019-08-20 | U126284 | U131066 | 2019-03-13 | 2019-11-27 |  |  | JOSH PASLEY | 2019-08-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.8167 | 1 | 1469.73 | 158.98 | 0 | 19.77 | 1290.98 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691672600 |  | 100326552 |  | 6720208B | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1378 FONTAINE RD | 067 | LEX | 2019-08-21 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-08-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2962.87 | 0 | 0 | 0 | 2962.87 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691697000 |  | 100326551 |  | 6720208B | 1855692 |  |  | 565 | EX | REPLACE SL W/18026796400 | 2600B | FONTAINE | 1376 FONTAINE RD | 067 | LEX | 2019-08-21 | U125559 | U131066 | 2019-03-27 | 2019-12-31 |  |  | BJACKSON | 2019-08-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4897.28 | 0 | 2404.13 | 0 | 2493.15 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19701107300 |  | 100310439 |  | 6716208E |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | STRATFORD | 608 STRATFORD DR | 067 | LEX | 2019-08-20 | U128293 | U125208 | 2019-04-29 | 2019-10-25 | 2021-04-30 |  | JENSMIN | 2019-08-20 | 2019-08-19 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.9 | 3 | 8981.79 | 903.79 | 909.24 | 487.5 | 6681.26 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19701431800 |  | 100312445 |  | 6716208E | 1749637 |  |  | 565 | EX | RPLC SL/18026754700/ | 2600B | SOUTHLAND | 521 SOUTHLAND DR | 067 | LEX | 2019-08-21 | HROGERS | U131066 | 2019-04-30 | 2019-11-27 |  |  | MARK ROGERS | 2019-08-20 | 2019-08-20 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 2.95 | 1 | 2056.54 | 153.89 | 289.65 | 20.01 | 1592.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19701432400 |  | 100312444 |  | 6716208E | 1749637 |  |  | 565 | EX | REPLACE SL W/18026754700 | 2600B | SOUTHLAND | 517 SOUTHLAND DR BSMT | 067 | LEX | 2019-08-21 | HROGERS | U131066 | 2019-04-30 | 2019-12-31 |  |  | MARK ROGERS | 2019-08-20 | 2019-08-20 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.65 | 1 | 2327.37 | 86.06 | 166.3 | 11.18 | 2063.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19707674000 |  | 100439211 |  | 6720212B | 1855586 |  |  | 565 | EX | RPLC SL/18026795700/ | 2600B | EDGELAWN | 1410< EDGELAWN AV | 067 | LEX | 2019-08-29 | U461423 | U131066 | 2019-05-21 | 2019-11-27 |  |  | KKOUNS | 2019-08-20 | 2019-08-20 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5 | 1 | 1308.24 | 288.02 | 0 | 94.14 | 926.08 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19733116900 |  | 100351199 |  | 6744208N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D097484 | 2621P | CHURCHILL | 12 CHURCHILL DR | 049 | WIN | 2019-08-20 | DBANKS | U125208 | 2019-08-15 | 2019-08-16 | 2019-09-04 |  | DBANKS | 2019-08-20 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 32.8667 | 5 | 1862.16 | 1483.12 | 214.25 | 91.83 | 72.96 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19734379500 |  | 100345980 |  | 6700208H |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | WOODLARK | 194 WOODLARK RD | 239 | VER | 2019-08-20 | CDESPAI | U129005 | 2019-08-20 | 2019-08-20 |  |  | CDESPAI | 2019-08-20 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 8.6833 | 1 | 4199.34 | 587.57 | 182.47 | 945.94 | 2483.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19734529600 |  | 100292603 |  | 6720216O |  |  |  | 565 | EX | GRADE 1 REPLACE D221362 | 2621P | HAWTHORNE | 1761 HAWTHORNE LN | 067 | LEX | 2019-08-22 | U125208 | U129939 | 2019-08-20 | 2019-08-20 | 2019-08-20 |  | WHIMES | 2019-08-20 | 2019-08-20 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.2 | 2 | 1134.78 | 624.17 | 367.77 | 35.32 | 107.52 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19026892000 |  |  |  | 6716232B | 1966074 | U128885 |  | 557 | EX | INSTALL 1' - 2" PMMP | 2621P | CASTLE ACRE | CASTLE ACRE | 209 | GEO | 2019-10-02 | U128132 | U128885 | 2019-08-22 | 2019-09-03 | 2020-04-30 | 2019-08-21 | OMAYNARD | 2019-08-21 | 2019-09-04 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP8920 |  |  | 100 | 055732190268920 | 2.0667 | 1 | 5470.4 | 987.23 | 36.1 | 82.52 | 3832.9 | 0 | 10.26 | 521.39 | 1
KY | KY - WEST | 2623 | 19026892100 |  |  |  | 6716232B | 1966074 | U128885 |  | 558 | EX | RETIRE 1' - 2" PMMP | 2621P | CASTLE ACRE | CASTLE ACRE | 209 | GEO | 2020-02-19 | U128132 | U128885 | 2019-08-22 | 2019-09-04 | 2020-04-30 | 2019-08-21 | OMAYNARD | 2019-08-21 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP8921 |  |  | 100 | 055832190268921 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671929400 |  | 100353612 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | FRONT | 108 W FRONT ST | 161 | MAY | 2019-09-11 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | ED FOX | 2019-08-21 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1221.38 | 0 | 0 | 0 | 1221.38 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671929600 |  | 100353609 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | FRONT | 112 W FRONT ST | 161 | MAY | 2019-09-11 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | ED FOX | 2019-08-21 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1205.86 | 0 | 0 | 0 | 1205.86 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671929900 |  | 100353606 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | FRONT | 116 W FRONT ST | 161 | MAY | 2019-09-11 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | ED FOX | 2019-08-21 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1200.49 | 0 | 0 | 0 | 1200.49 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678787100 |  | 100299193 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LEESTOWN | 1537 LEESTOWN RD | 067 | LEX | 2019-08-21 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-08-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 988.83 | 0 | 0 | 0 | 988.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678792000 |  | 100299074 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | PEPPER | 240 PEPPER DR | 067 | LEX | 2019-08-21 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-08-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2372.84 | 0 | 0 | 0 | 2372.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687824100 |  | 100280026 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | MAGNOLIA | 310 MAGNOLIA ST | 073 | FRA | 2019-08-28 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-08-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687824300 |  | 100280024 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | MAGNOLIA | 314 MAGNOLIA ST | 073 | FRA | 2019-08-28 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-08-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1280.42 | 0 | 0 | 0 | 1280.42 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687824600 |  | 100280015 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | MAGNOLIA | 317 MAGNOLIA ST | 073 | FRA | 2019-08-28 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-08-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689095100 |  | 100255841 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | TURLEY | 1132 TURLEY AV | 089 | FLA | 2019-08-21 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-08-21 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.53333 | 1 | 1415.6 | 29.99 | 0 | 3.77 | 1381.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691672400 |  | 100326548 |  | 6720208A | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1372 FONTAINE RD | 067 | LEX | 2019-08-21 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-08-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 6292.18 | 0 | 3467.33 | 0 | 2824.85 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19707673800 |  | 100290188 |  | 6720212B | 1855586 |  |  | 565 | EX | RPLC SL/18026795700/ | 2600B | EDGELAWN | 1408 EDGELAWN AV | 067 | LEX | 2019-08-29 | U461423 | U131066 | 2019-05-21 | 2019-11-27 |  |  | KKOUNS | 2019-08-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11 | 1 | 1663.58 | 633.67 | 0 | 207.12 | 822.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19707673900 |  | 100290189 |  | 6720212B | 1855586 |  |  | 565 | EX | RPLC SL/18026795700/ | 2600B | EDGELAWN | 1410 EDGELAWN AV | 067 | LEX | 2019-08-21 | U461423 | U131066 | 2019-05-21 | 2019-11-27 |  |  | KEVIN KOUNS | 2019-08-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 920.32 | 0 | 0 | 0 | 920.32 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19707742400 |  | 100262079 |  | 7352256D | 1961470 |  |  | 565 | EX | RPLC SL/19026862600/ | 2600B | FLORENCE | 1342 FLORENCE ST | 019 | ASH | 2019-08-21 | U123965 | U131066 | 2019-05-21 | 2019-11-27 |  |  | MARCUS BLANKENSHIP | 2019-08-21 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1456.45 | 0 | 0 | 0 | 1456.45 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19026893400 |  |  |  | 6740228A | 1966183 | U128885 |  | 557 | EX | INSTALL 1' - 2" PMMP | 2621P | VINE | 1075 VINE ST | 017 | PAR | 2019-12-27 | U128132 | U128885 | 2019-08-27 | 2019-12-23 | 2019-12-31 | 2019-08-22 | BJOHNSON | 2019-08-22 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP8934 |  |  | 100 | 055732190268934 |  | 6 | 2877.95 | 0 | 218.44 | 0 | 2324.84 | 0 | 0.01 | 334.66 | 6
KY | KY - CENTRAL | 2629 | 19026893500 |  |  |  | 6740228A | 1966183 | U128885 |  | 558 | EX | RETIRE 1' - 2" PMMP | 2621P | VINE | 1075 VINE ST | 017 | PAR | 2019-12-27 | U128132 | U128885 | 2019-08-27 |  | 2049-12-31 | 2019-08-22 | BJOHNSON | 2019-08-22 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP8935 |  |  | 100 | 055832190268935 | 0.45 | 0 | 8380.85 | 7809.35 | 0 | 571.5 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671929800 |  | 100353608 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | FRONT | 114 W FRONT ST DN | 161 | MAY | 2019-08-26 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-08-22 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1276.63 | 0 | 0 | 0 | 1276.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680068400 |  | 100320247 |  | 6716208G | 1748686 |  |  | 565 | EX | RPLC SL/17026736101 | 2600B | SHADY | 101 SHADY LN | 067 | LEX | 2019-08-22 | U126284 | U131066 | 2019-02-07 | 2019-09-30 |  |  | JOSH PASLEY | 2019-08-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.95 | 1 | 2119.41 | 166.89 | 0 | 20.75 | 1931.77 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691672000 |  | 100326545 |  | 6720208A | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1364 FONTAINE RD | 067 | LEX | 2019-08-22 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-08-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2684.52 | 0 | 408.69 | 0 | 2275.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691672100 |  | 100326546 |  | 6720208A | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1368 FONTAINE RD | 067 | LEX | 2019-08-22 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-08-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2264.19 | 0 | 0 | 0 | 2264.19 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19707674400 |  | 100290218 |  | 6720212C | 1855586 |  |  | 565 | EX | RPLC SL/18026795700/ | 2600B | EDGELAWN | 1419 EDGELAWN AV | 067 | LEX | 2019-08-22 | U461423 | U131066 | 2019-05-21 | 2019-11-27 |  |  | KKOUNS | 2019-08-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.5 | 1 | 1724.79 | 604.85 | 0 | 197.7 | 922.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19711908100 |  | 100319178 |  | 6716208O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MELBOURNE | 360 MELBOURNE WY | 067 | LEX | 2019-08-22 | JWCOX | U125208 | 2019-06-05 | 2019-12-04 | 2021-06-30 |  | JWCOX | 2019-08-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.91667 | 1 | 1756.14 | 51.94 | 319.83 | 2.95 | 1381.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19712456700 |  | 100311445 |  | 6712204H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D093779 | 2621P | PLYMOUTH | 470 PLYMOUTH DR | 067 | LEX | 2019-08-22 | JWCOX | U125208 | 2019-06-07 | 2019-12-06 | 2021-06-30 |  | JWCOX | 2019-08-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.81667 | 1 | 1682.02 | 46.24 | 252.71 | 2.61 | 1380.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19713884600 |  | 100453083 |  | 6712208J |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MANTILLA | 3394 MANTILLA DR | 067 | LEX | 2019-08-26 | U125208 | U125208 | 2019-06-13 | 2019-08-22 | 2021-06-30 |  | JENSMIN | 2019-08-22 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.5667 | 2 | 10639.2 | 306.9 | 6455.93 | 201.48 | 3674.89 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19729220200 |  | 100445862 |  | 7356256P |  |  |  | 566 | EX | ABANDON / RI 08-01-19 PR.SJUDE | 2621P | WINCHESTER | 4748< WINCHESTER AV | 019 | ASH | 2019-08-22 | MCOLLET | U125208 | 2019-08-01 | 2019-08-22 |  |  | MCOLLET | 2019-08-22 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 10.8167 | 3 | 982.16 | 642.5 | 22.36 | 317.3 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19731057800 |  | 100315332 |  | 6716208C |  |  |  | 566 | EX | DEMO / ABANDON / RI 08-10-19 | 2621P | UNIVERSITY | 119 UNIVERSITY AV | 067 | LEX | 2019-08-22 | ATWILLI | U125208 | 2019-08-07 | 2019-08-28 | 2019-09-07 |  | ATWILLI | 2019-08-22 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 16.7667 | 2 | 1091.07 | 948.69 | 88.72 | 53.66 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19731058400 |  | 100315333 |  | 6716208C |  |  |  | 566 | EX | DEMO / ABANDON / RI 08-14-19 | 2621P | UNIVERSITY | 123 UNIVERSITY AV | 067 | LEX | 2019-08-22 | ATWILLI | U125208 | 2019-08-07 | 2019-08-28 | 2019-09-07 |  | ATWILLI | 2019-08-22 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.2333 | 2 | 211.16 | 191.14 | 9.24 | 10.78 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19734963300 |  | 100343294 |  | 7240212A |  |  |  | 565 | EX | REPLACE SERVICE LINE D097393 | 2621P | ELMWOOD | 806 ELMWOOD DR | 173 | MT | 2019-08-22 | DENNING | U129005 | 2019-08-21 | 2019-08-21 | 2019-08-21 |  | DENNING | 2019-08-22 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 17.4667 | 8 | 1457.11 | 828.9 | 265.7 | 323.15 | 39.36 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19735468100 |  | 100416844 |  | 6680224G |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | SPRUCE | 313 SPRUCE DR | 073 | FRA | 2019-08-22 | CDESPAI | U129005 | 2019-08-22 | 2019-08-22 |  |  | CDESPAI | 2019-08-22 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.18333 | 1 | 303.13 | 11.34 | 193.42 | 16.77 | 81.6 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19026892800 |  |  |  | 6700224O | 1966123 | U130604 |  | 557 | EX | INSTALL 1' 2" PMLP | 2621P | E STEPHENS | 134 E STEPHENS ST | 239 | MID | 2020-05-04 | U128132 | U130604 | 2019-08-23 | 2019-08-22 | 2019-08-23 | 2019-08-23 | SBARKER | 2019-08-23 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP8928 |  |  | 100 | 055732190268928 |  | 1 | 1739.79 | 1114.41 | 392.76 | 63.11 | 0 | 0 | 2.56 | 166.95 | 1
KY | KY - WEST | 2623 | 19026892900 |  |  |  | 6700224O | 1966123 | U130604 |  | 558 | EX | RETIRE 1' 2" PLP | 2621P | E STEPHENS | 134 E STEPHENS ST | 239 | MID | 2020-05-04 | U128132 | U130604 | 2019-08-23 | 2019-08-23 | 2019-08-23 | 2019-08-23 | SBARKER | 2019-08-23 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP8929 |  |  | 100 | 055832190268929 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671930000 |  | 100353604 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | FRONT | 120 W FRONT ST | 161 | MAY | 2019-08-26 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-08-23 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1124.05 | 0 | 0 | 0 | 1124.05 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678786700 |  | 100299189 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LEESTOWN | 1519 LEESTOWN RD | 067 | LEX | 2019-08-23 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-08-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.6667 | 1 | 1626.11 | 141.85 | 0 | 49.6 | 1434.66 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680068100 |  | 100320248 |  | 6716208G | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 99 SHADY LN | 067 | LEX | 2019-08-23 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-08-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 2686.4 | 452.62 | 0 | 56.27 | 2177.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19681889100 |  | 500642062 |  | 6712208G | 1961497 |  |  | 565 | EX | RELOCATE SERVICE LINE | 2621P | BEAUMONT CENTR | 3251 BEAUMONT CENTR CR | 067 | LEX | 2019-08-27 | U125208 | U125208 | 2019-02-18 | 2019-03-29 | 2019-03-31 |  | JENSMIN | 2019-08-23 | 2019-08-21 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 16.2 | 2 | 8914.01 | 1018.79 | 248.15 | 1034.86 | 6612.21 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689094800 |  | 100255838 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | TURLEY | 1122 TURLEY AV | 089 | FLA | 2019-08-23 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-08-23 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.3 | 1 | 1295.32 | 17.2 | 0 | 2.16 | 1275.96 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691672200 |  | 100326547 |  | X | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1370 FONTAINE RD | 067 | LEX | 2019-08-23 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-08-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2881.47 | 0 | 0 | 0 | 2881.47 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19707674300 |  | 100290222 |  | 6720212B | 1855586 |  |  | 565 | EX | RPLC SL/18026795700/ | 2600B | EDGELAWN | 1415 EDGELAWN AV | 067 | LEX | 2019-08-23 | U461423 | U131066 | 2019-05-21 | 2019-11-27 |  |  | KKOUNS | 2019-08-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.5 | 1 | 1648.39 | 547.27 | 0 | 178.88 | 922.24 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19734544900 |  | 100263051 |  | 7384168G |  |  |  | 565 | EX | REPLACE SERV LNE D133210 | 2621P | KENTUCKY | 132 KENTUCKY AV 4 | 195 | S W | 2019-08-29 | U125208 | U129939 | 2019-08-20 | 2019-08-20 | 2019-08-20 |  | JCKIRK | 2019-08-23 | 2019-08-20 |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 40.9667 | 7 | 3316.61 | 2517.38 | 149.23 | 580.88 | 69.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19735940600 |  | 100290142 |  | 6720212B |  |  |  | 565 | EX | REPLACE SERVICE LINE - D222378 | 2621P | LIMESTONE | 1306 N LIMESTONE ST | 067 | LEX | 2019-08-23 | JWCOX | U125208 | 2019-08-23 | 2019-08-22 | 2019-08-22 |  | JWCOX | 2019-08-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.9333 | 1 | 4139.2 | 396.05 | 298.65 | 22.42 | 3422.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19736047900 |  | 100417582 |  | 6720216D |  |  |  | 565 | EX | GRADE 1 REPLACE SERV - D221364 | 2621P | FAULKNER | 744 FAULKNER AV | 067 | LEX | 2019-08-29 | U125208 | U129939 | 2019-08-23 | 2019-08-23 | 2019-08-23 |  | JENSMIN | 2019-08-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.3333 | 1 | 3679.54 | 209.55 | 930.64 | 212.84 | 2326.51 | 0 | 0 | 0
KY | KY - WEST | 2623 | 07689904600 |  | 100273519 |  | 6680224F |  |  |  | 566 | EX | ABANDON / IDLE GR 2 D094715 | 2600B | DONNA | 165 DONNA DR | 073 | FRA | 2019-08-24 | CDESPAI | U903504 | 2007-06-06 | 2019-08-13 | 2020-10-31 |  | CDESPAI | 2019-08-24 | 2019-08-13 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 8.4333 | 4 | 4207.07 | 535.58 | 53.9 | 733.99 | 2883.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671929200 |  | 100353617 |  | 7256280L | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | FRONT | 104 W FRONT ST | 161 | MAY | 2019-08-24 | U126286 | U131066 | 2019-01-22 | 2019-11-27 |  |  | TYLER ALLISON | 2019-08-24 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2513.52 | 0 | 0 | 0 | 2513.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19707673700 |  | 100442005 |  | 6720212B | 1855586 |  |  | 565 | EX | RPLC SL/18026795700/ | 2600B | EDGELAWN | 1407 EDGELAWN AV | 067 | LEX | 2019-08-29 | U461423 | U131066 | 2019-05-21 | 2019-11-27 |  |  | KKOUNS | 2019-08-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 1443.91 | 460.87 | 0 | 150.65 | 832.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19736276400 |  | 100291768 |  | 6720216G |  |  |  | 565 | EX | REPLACE SERV LINE - D222379 | 2621P | PIERSON | 2433 PIERSON DR | 067 | LEX | 2019-08-29 | U125208 | U131168 | 2019-08-24 | 2019-08-23 | 2019-08-23 |  | ASNICHO | 2019-08-24 | 2019-08-24 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 21.75 | 5 | 1828.12 | 1184.06 | 488.72 | 67.02 | 88.32 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19736904700 |  | 100353636 |  | 7256280L | 1747939 |  |  | 565 | EX | REPLACE SL W/17026728200 | 2600B | FRONT | 104 W FRONT ST 6 | 161 | MAY | 2019-08-28 | U126286 | U124960 | 2019-08-27 | 2049-12-31 |  |  | TYLER ALLISON | 2019-08-24 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 2615.35 | 0 | 0 | 0 | 2615.35 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19026877700 |  |  |  | 6736228F | 1851755 | BKSLONE |  | 561 | EX | INSTALL 154'-2" PM/CSMP | 2600B | ECHO | 275 ECHO DR REAR | 017 | PAR | 2019-09-04 | U460266 | BKSLONE | 2019-05-17 | 2019-08-21 | 2019-08-30 | 2019-08-21 | WGRAVES | 2019-08-26 | 2019-08-14 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00561 | 3200561 |  |  | WP8777 |  |  | 100 | 056132190268777 | 98.8 | 2142 | 39253.55 | 5976.78 | 3291.53 | 3064.12 | 22825.73 | 0 | 104.16 | 3991.23 | 153
KY | KY - CENTRAL | 2629 | 19026877800 |  |  |  | 6736228F | 1851755 | BKSLONE |  | 562 | EX | RETIRE 136'-3" CSMP | 2600B | ECHO | 275 ECHO DR REAR | 017 | PAR | 2019-09-04 | U460266 | BKSLONE | 2019-05-17 | 2019-08-30 | 2019-08-30 | 2019-08-21 | WGRAVES | 2019-08-26 | 2019-08-06 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00562 | 3200562 |  |  | WP8778 |  |  | 100 | 056232190268778 | 4.7 | 0 | 411.89 | 308.05 | 0 | 103.84 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19026891100 |  |  |  | 7332132G | 1965995 | U132280 |  | 561 | EX | OFFSET 20'-2"P-MP MAIN | 2621P | KY-899 | 6238 KY-899 | 119 | PIP | 2019-09-23 | U128132 | U132280 | 2019-08-19 | 2019-08-21 | 2019-08-22 | 2019-08-23 | JAHOWARD | 2019-08-26 |  |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00561 | 3200561 |  |  | WP8911 |  |  | 100 | 056132190268911 | 6.6667 | 22 | 555.23 | 377.03 | 0 | 125.03 | 0 | 0 | 0 | 53.17 | 22
KY | KY - EAST | 2633 | 19026891400 |  |  |  | 7332132G | 1965995 | U132280 |  | 562 | EX | RETIRE 20'-2"P-MP MAIN | 2621P | KY 899 | 6238 KY 899 | 119 | PIP | 2019-09-23 | U128132 | U132280 | 2019-08-20 | 2019-08-22 | 2019-08-23 | 2019-08-23 | JAHOWARD | 2019-08-26 | 2019-08-22 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00562 | 3200562 |  |  | WP8914 |  |  | 100 | 056232190268914 | 64.1667 | 0 | 5917.05 | 3512.67 | 0 | 699.93 | 1704.45 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026891500 |  |  |  | 6716208F | 1966058 | U128885 |  | 557 | EX | INSTALL 1' - 2" PMMP | 2621P | GOODRICH | GOODRICH | 067 | LEX | 2019-10-01 | U123258 | U128885 | 2019-08-21 | 2020-04-29 | 2020-04-30 | 2019-08-23 | DODD SORRELL | 2019-08-26 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP8915 |  |  | 100 | 055732190268915 |  | 5 | 6549.04 | 1218.98 | 245.38 | 127.66 | 4318.86 | 0 | 12.2 | 625.96 | 5
KY | KY - WEST | 2621 | 19026891600 |  |  |  | 6716208F | 1966058 | U128885 |  | 558 | EX | RETIRE 1' - 2" PMMP | 2621P | GOODRICH | GOODRICH | 067 | LEX | 2019-10-01 | U123258 | U128885 | 2019-08-21 | 2020-04-30 | 2020-04-30 | 2019-08-23 | DODD SORRELL | 2019-08-26 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP8916 |  |  | 100 | 055832190268916 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689094900 |  | 100255840 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | TURLEY | 1126 TURLEY AV | 089 | FLA | 2019-08-26 | U124015 | U131066 | 2019-03-18 | 2019-08-26 |  |  | ORA SLONE | 2019-08-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.36667 | 1 | 1124.64 | 22.54 | 0 | 2.72 | 1099.38 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689200300 |  | 100255839 |  | 7348264L | 1859009 |  |  | 565 | EX | REPLACE SL W/18026843700 | 2600B | TURLEY | 1124 TURLEY AV | 089 | FLA | 2019-08-26 | U124015 | U131066 | 2019-03-18 | 2019-12-31 |  |  | ORA SLONE | 2019-08-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1106.1 | 0 | 0 | 0 | 1106.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18603009300 |  | 100290221 |  | 6720212C | 1635077 |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | EDGELAWN | 1417 EDGELAWN AV 1F | 067 | LEX | 2019-08-27 | U461423 | U125964 | 2018-04-13 | 2019-12-31 | 2019-12-31 |  | KKOUNS | 2019-08-27 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 8 | 1 | 2309.37 | 452.61 | 0 | 150.15 | 1706.61 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19026890900 |  |  |  | 6700212M | 1965988 | U130604 |  | 559 | EX | INSTALL 4" POLY VALVE | 2621P | HUNTERTOWN RD | HUNTERTOWN RD | 239 | VER | 2019-10-01 | U128132 | U130604 | 2019-08-19 | 2019-09-30 | 2019-10-01 | 2019-08-27 | BLONE | 2019-08-27 | 2019-08-27 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00559 | 3200559 |  |  | WP8909 |  |  | 100 | 055932190268909 | 0.51667 | 8 | 634.89 | 28.67 | 542.98 | 1.62 | 0 | 0 | 0.91 | 60.71 | 4
KY | KY - WEST | 2623 | 19026891000 |  |  |  | 6700212M | 1965988 | U130604 |  | 560 | EX | RETIRE 4"PV | 2621P | HUNTERTOWN RD | HUNTERTOWN RD | 239 | VER | 2019-10-01 | U128132 | U130604 | 2019-08-19 | 2019-10-01 | 2019-10-01 | 2019-08-27 | BLONE | 2019-08-27 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00560 | 3200560 |  |  | WP8910 |  |  | 100 | 056032190268910 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678787300 |  | 100299195 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LEESTOWN | 1549 LEESTOWN RD | 067 | LEX | 2019-08-27 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-08-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.5167 | 1 | 1729.9 | 139.01 | 0 | 47.11 | 1543.78 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680067900 |  | 100467031 |  | 6716208G | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 95 SHADY LN | 067 | LEX | 2019-08-27 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-08-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10 | 1 | 6176.35 | 602.08 | 0 | 72.38 | 5501.89 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689094600 |  | 100255834 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | TURLEY | 1112 TURLEY AV | 089 | FLA | 2019-08-27 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-08-27 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.75 | 1 | 1277.63 | 44.48 | 0 | 5.39 | 1227.76 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689094700 |  | 100255837 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | TURLEY | 1116 TURLEY AV | 089 | FLA | 2019-08-27 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-08-27 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 1.35 | 1 | 1146.72 | 80.04 | 0 | 9.7 | 1056.98 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691672500 |  | 100326549 |  | 6720208A | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1374 FONTAINE RD | 067 | LEX | 2019-09-09 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-08-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3684.59 | 0 | 0 | 0 | 3684.59 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19733950600 |  | 100257068 |  | 7348264J |  |  |  | 565 | EX | REPL S/L PER FOL-LN HIT 8/16 | 2621P | BELLEFONTE | 50 BELLEFONTE RD | 089 | RAC | 2019-08-27 | BROBERT | DYOUNG | 2019-08-19 | 2019-08-28 |  |  | BROBERT | 2019-08-27 | 2019-08-21 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 42.45 | 8 | 3541.56 | 2441.34 | 177.27 | 856.71 | 66.24 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19736836700 |  | 100263212 |  | 7384168G |  |  |  | 565 | EX | REPLACE SERVICE LINE - D133211 | 2621P | VIRGINIA | 221 VIRGINIA AV | 195 | S W | 2019-08-29 | U125208 | U129005 | 2019-08-27 | 2019-08-26 | 2019-08-26 |  | JCKIRK | 2019-08-27 |  |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 18.9667 | 2 | 1400.51 | 1156.72 | 28.34 | 197.21 | 18.24 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19736862500 |  | 100348129 |  | 6748208I |  |  |  | 565 | EX | REPLACE SERVICE LINE - D095167 | 2621P | COOK | 157 COOK AV | 049 | WIN | 2019-08-29 | U125208 | U129005 | 2019-08-27 | 2019-08-16 | 2019-09-03 |  | DBANKS | 2019-08-27 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 23.95 | 4 | 2025.74 | 1386.34 | 180.32 | 436.04 | 23.04 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19736866500 |  | 100326101 |  | 6720208A |  |  |  | 565 | EX | RELOC SERV LINE - ABN OLD SERV | 2621P | LOUISIANA | 133 LOUISIANA AV | 067 | LEX | 2019-08-27 | JWCOX | U125208 | 2019-08-27 | 2019-08-27 |  |  | JWCOX | 2019-08-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 2.85 | 1 | 3722.93 | 166.94 | 268.07 | 53.81 | 3234.11 | 0 | 0 | 0
KY | KY - WEST | 2621 | 06654926300 |  | 100290213 |  | 6720212C | 1855586 |  |  | 566 | EX | ABNDN SL/18026795700 | 2600B | EDGELAWN | 1429 EDGELAWN AV | 067 | LEX | 2019-08-28 | U461423 | SSUTHER | 2006-07-26 | 2019-09-30 |  |  | KKOUNS | 2019-08-28 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 429.03 | 0 | 0 | 0 | 429.03 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18026763500 |  |  |  | 6760248M | 1851783 | BKSLONE |  | 583 | EX | R-1238 INSTALL CWT HEATER | 2600E | HICKORY RIDGE | 900 HICKORY RIDGE RD | 181 | CAR | 2020-01-22 | U462463 | BKSLONE | 2018-03-26 | 2019-08-19 | 2019-12-31 | 2019-08-28 | CYNTHIA FARIS | 2019-08-28 | 2019-04-23 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00583 | 3200583 |  |  | WP7635 |  |  | 100 | 058332180267635 | 917.8167 | 2772 | 1266077.97 | 58670.6 | 789753.54 | 13300.82 | 246843.35 | 0 | 9870.22 | 147639.44
KY | KY - CENTRAL | 2629 | 18026763600 |  |  |  | 6760248M | 1851783 | BKSLONE |  | 584 | EX | R-1238 RETIRE WATER BATH HTR | 2600E | HICKORY RIDGE | 900 HICKORY RIDGE RD | 181 | CAR | 2019-12-17 | U462463 | BKSLONE | 2018-03-26 | 2019-08-30 | 2019-12-31 | 2019-06-11 | CYNTHIA FARIS | 2019-08-28 | 2019-06-11 |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00584 | 3200584 |  |  | WP7636 |  |  | 100 | 058432180267636 | 48.35 | 0 | 17505.78 | 2769.84 | 8631.38 | 516.02 | 5588.54 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18026774100 |  |  |  | 7344264L | 1853100 | U122858 |  | 559 | EX | INSTALL 25'-4" PMIP | 2600B | DEER CREEK CT | DEER CREEK CT | 089 | FLA | 2019-09-04 | U125423 | U131042 | 2018-05-29 | 2019-11-18 | 2019-12-01 | 2019-08-27 | DAVID SKAGGS | 2019-08-28 | 2019-08-19 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00559 | 3200559 |  |  | WP7741 |  |  | 100 | 055932180267741 | 54.6333 | 450 | 50642.22 | 3114.59 | 2290.47 | 475.28 | 39385.87 | 0 | 52.97 | 5323.04 | 50
KY | KY - EAST | 2631 | 18026774200 |  |  |  | 7344264L | 1853100 | U122858 |  | 560 | EX | RETIRE 25' 4" PIP | 2600B | DEER CREEK CT | DEER CREEK CT | 089 | FLA | 2019-09-04 | U125423 | U131042 | 2018-05-29 | 2019-12-31 | 2019-12-31 | 2019-08-27 | DAVID SKAGGS | 2019-08-28 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00560 | 3200560 |  |  | WP7742 |  |  | 100 | 056032180267742 | 2.6 | 0 | 5539.23 | 148.48 | 0 | 18.37 | 5372.38 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19026860701 |  |  |  | 7240212N | 1745093 | U461383 |  | 559 | EX | INSTALL INLET/OUTLET PIPING | 2600B | PAULA | PAULA DR | 173 | MT | 2019-09-26 | U462463 | U461383 | 2019-08-29 | 2019-08-20 | 2019-10-01 | 2019-08-28 | WILL FULKS | 2019-08-28 | 2019-08-29 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00559 | 3200559 |  |  | WP8607 |  |  | 100 | 055932190268607 | 429.0333 | 2160 | 165360.17 | 26043 | 26060.95 | 6337.36 | 89191.73 | 0 | 485.21 | 17241.92 | 40
KY | KY - CENTRAL | 2629 | 19026860800 |  |  |  | 7240212N | 1745093 | U461383 |  | 560 | EX | RETIRE INLET & OUTLET PIPING | 2600B | PAULA | PAULA DR | 173 | MT | 2019-09-26 | U462463 | U461383 | 2019-02-07 | 2019-10-01 | 2019-10-01 | 2019-08-28 | WILL FULKS | 2019-08-28 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00560 | 3200560 |  |  | WP8608 |  |  | 100 | 056032190268608 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026892400 |  |  |  | 6716208G | 1966076 | U461383 |  | 558 | EX | ABANDON 2' OF 4"BSLP MAIN | 2621P | BARBERRY | BARBERRY LN | 067 | LEX | 2019-09-11 | U460266 | U461383 | 2019-08-22 | 2019-08-21 | 2019-08-22 | 2019-08-28 | LSTANFI | 2019-08-28 | 2019-08-28 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP8924 | AMRCB |  | 100 | 055832190268924 | 31.7 | 0 | 5434.76 | 2287.34 | 228.55 | 129.43 | 2789.44 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19671930900 |  | 100353875 |  | 7256280P | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | LIMESTONE | 222 LIMESTONE ST | 161 | MAY | 2019-09-04 | U461478 | U131066 | 2019-01-22 | 2019-11-27 |  |  | DAVID STAGGS | 2019-08-28 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1268.53 | 0 | 0 | 0 | 1268.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678791900 |  | 100299062 |  | 6716216N | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | PEPPER | 239 PEPPER DR | 067 | LEX | 2019-08-28 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-08-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.7 | 1 | 2671.89 | 204.13 | 0 | 69.16 | 2398.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680068000 |  | 100450816 |  | 6716208G | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 97 SHADY LN | 067 | LEX | 2019-08-28 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-08-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9 | 1 | 3200.31 | 541.88 | 0 | 65.14 | 2593.29 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689095200 |  | 100255835 |  | 7348264H | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | VOYER | 1116 VOYER ST | 089 | FLA | 2019-08-28 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-08-28 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.26667 | 1 | 967.16 | 16.01 | 0 | 1.93 | 949.22 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689095300 |  | 100255836 |  | 7348264H | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | VOYER | 1118 VOYER ST | 089 | FLA | 2019-08-28 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-08-28 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.55 | 1 | 1318.8 | 32.6 | 0 | 3.95 | 1282.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691671900 |  | 100326544 |  | 6720208A | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1360 FONTAINE RD | 067 | LEX | 2019-08-28 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-08-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2615.57 | 0 | 0 | 0 | 2615.57 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703184500 |  | 100280047 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 260 HIGHLAND PY | 073 | FRA | 2019-08-28 | U461327 | U131066 | 2019-05-03 | 2019-11-27 |  |  | WBURCHETT | 2019-08-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.7333 | 1 | 2728.74 | 209.11 | 0 | 70.05 | 2449.58 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703184600 |  | 100279999 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 262 HIGHLAND PY | 073 | FRA | 2019-08-28 | U461327 | U131066 | 2019-05-03 | 2019-11-27 |  |  | WBURCHETT | 2019-08-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.5167 | 1 | 1908.55 | 252.15 | 0 | 84.5 | 1571.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19713884200 |  | 100452091 |  | 6712208J |  |  |  | 566 | EX | REPLACE SERVICE LINE - D093781 | 2621P | FORT HARRODS | 2140 FORT HARRODS DR 21 | 067 | LEX | 2019-08-29 | U125208 | U125208 | 2019-06-13 | 2019-08-27 | 2021-06-30 |  | JENSMIN | 2019-08-28 | 2019-08-27 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.4333 | 2 | 2729.84 | 561.9 | 9.24 | 74.67 | 2084.03 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19734414000 |  | 100351864 |  | 6744208O |  |  |  | 565 | EX | AOC - ATMOS CORROSION | 2621P | LINDBERG | 128 LINDBERG AV | 049 | WIN | 2019-08-28 | DBANKS | U131723 | 2019-08-20 | 2020-02-20 | 2020-08-20 |  | DBANKS | 2019-08-28 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 11.1667 | 4 | 1108.73 | 652.56 | 143.52 | 246.41 | 66.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19737194800 |  | 100311113 |  | 6712208O |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HAVERHILL | 712 HAVERHILL RD | 067 | LEX | 2019-08-28 | JWCOX | U129005 | 2019-08-28 | 2019-08-28 | 2019-08-28 |  | JWCOX | 2019-08-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.5333 | 1 | 3390.2 | 441.01 | 247.34 | 24.93 | 2676.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19737333500 |  | 100404239 |  | 6724208E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | PEACHTREE | 372 PEACHTREE RD | 067 | LEX | 2019-08-29 | U125208 | U129005 | 2019-08-28 | 2019-08-28 |  |  | JENSMIN | 2019-08-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.5833 | 1 | 5610.88 | 95.45 | 984.51 | 101.95 | 4428.97 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19026878500 |  | 501267850 |  | 6704224E | 1964076 | U461383 |  | 555 | EX | INSTALL 1500' OF 4"PHHP MAIN | 2600B | BRADLEY | 100 BRADLEY ST | 239 | MID | 2019-09-25 | U124014 | U461383 | 2019-05-23 | 2019-09-11 | 2019-10-01 | 2019-08-29 | JAMIE LYNN | 2019-08-29 | 2019-08-09 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP8785 |  |  | 100 | 055532190268785 | 121.7667 | 31046 | 103609.21 | 6786.7 | 8075.8 | 1054.02 | 77548.45 | 0 | 159.83 | 9984.41 | 1634
KY | KY - WEST | 2621 | 19673607400 |  | 100310463 |  | 6712208L | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2833 CLAYS MILL RD | 067 | LEX | 2019-08-29 | U126602 | U131066 | 2019-01-30 | 2019-11-27 |  |  | DEREK PAYTON | 2019-08-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.9167 | 1 | 1976.01 | 289.22 | 257.25 | 16.36 | 1413.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673607500 |  | 100310464 |  | 6712208L | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2841 CLAYS MILL RD | 067 | LEX | 2019-08-29 | U461439 | U131066 | 2019-01-30 | 2019-11-27 |  |  | A PARRIS | 2019-08-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 2377.54 | 0 | 239.08 | 0 | 2138.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678786800 |  | 100299190 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LEESTOWN | 1523 LEESTOWN RD | 067 | LEX | 2019-09-03 | U126286 | U131066 | 2019-02-01 | 2019-11-27 |  |  | TYLER ALLISON | 2019-08-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1502.59 | 0 | 0 | 0 | 1502.59 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680087400 |  | 100320188 |  | 6716208G | 1748686 |  |  | 565 | EX | REPLACE SL W/17026736100 | 2600B | SHADY | 104 SHADY LN | 067 | LEX | 2019-08-29 | U126284 | U131066 | 2019-02-07 | 2019-12-31 |  |  | JOSH PASLEY | 2019-08-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.75 | 1 | 3268.69 | 346.78 | 0 | 41.7 | 2880.21 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689090700 |  | 100255798 |  | 7348264H | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | CENTRAL | 1105 CENTRAL AV | 089 | FLA | 2019-08-29 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-08-29 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.85 | 1 | 1277.24 | 50.38 | 0 | 6.12 | 1220.74 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689094000 |  | 100255803 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | TURLEY | 1014 TURLEY AV | 089 | FLA | 2019-08-29 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-08-29 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.46667 | 1 | 1007.36 | 27.89 | 0 | 3.37 | 976.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691695900 |  | 100326538 |  | 6720208A | 1855692 |  |  | 565 | EX | REPLACE SL W/18026796400 | 2600B | FONTAINE | 1332 FONTAINE RD | 067 | LEX | 2019-08-30 | U125559 | U131066 | 2019-03-27 | 2019-12-31 |  |  | BJACKSON | 2019-08-29 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4365.69 | 0 | 0 | 0 | 4365.69 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703184000 |  | 100280111 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 253 HIGHLAND PY | 073 | FRA | 2019-08-29 | U461375 | U131066 | 2019-05-03 | 2019-11-27 |  |  | LARRY BROWN | 2019-08-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2906.87 | 0 | 0 | 0 | 2906.87 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703184100 |  | 100280050 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 254 HIGHLAND PY | 073 | FRA | 2019-08-29 | U461375 | U131066 | 2019-05-03 | 2019-11-27 |  |  | LARRY BROWN | 2019-08-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703184300 |  | 100280049 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 256 HIGHLAND PY | 073 | FRA | 2019-08-29 | U461375 | U131066 | 2019-05-03 | 2019-11-27 |  |  | LARRY BROWN | 2019-08-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1475.38 | 0 | 0 | 0 | 1475.38 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703184400 |  | 100280048 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 258 HIGHLAND PY | 073 | FRA | 2019-08-29 | U461375 | U131066 | 2019-05-03 | 2019-11-27 |  |  | LARRY BROWN | 2019-08-29 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19711109200 |  | 100297735 |  | 6716212H | 1855598 |  |  | 565 | EX | RPLC SL/18026796000/ | 2600B | MILL | 201 N MILL ST | 067 | LEX | 2019-08-30 | HROGERS | U131066 | 2019-06-03 | 2019-11-27 |  |  | MARK ROGERS | 2019-08-29 | 2019-08-28 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.1667 | 2 | 2508.07 | 274.81 | 129.78 | 35.4 | 2068.08 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19725498000 |  | 100425963 |  | 6700212E |  |  |  | 565 | EX | REPLACE SERV D097223 | 2621P | US BYPASS 60 | 100 US BYPASS 60 | 239 | VER | 2019-08-30 | U125208 | U129939 | 2019-07-19 | 2018-11-09 | 2020-05-31 |  | CDESPAI | 2019-08-29 | 2019-07-19 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 44.0833 | 6 | 39252.39 | 6582.43 | 402.13 | 5014.58 | 27253.25 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19733165800 |  | 100277183 |  | 6684228H |  |  |  | 566 | EX | ABANDON / RI 12-02-15 / CONVRT | 2621P | GAYLE | 108 GAYLE ST | 073 | FRA | 2019-08-29 | BJLONE | U132002 | 2019-08-15 | 2019-09-24 | 2019-10-15 |  | BJLONE | 2019-08-29 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 13.5833 | 2 | 791.8 | 749.43 | 0 | 42.37 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19736424200 |  | 500474405 |  | 6716208K |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | NICHOLASVILLE | 1975 NICHOLASVILLE RD | 067 | LEX | 2019-08-30 | U125208 | U125208 | 2019-08-26 | 2019-08-29 |  |  | WHIMES | 2019-08-29 | 2019-08-29 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 29.0667 | 3 | 2874.18 | 1459.85 | 198.28 | 82.61 | 1133.44 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 16434587600 |  | 100353877 | 05 | 7256280P | 1747939 |  |  | 565 | EX | REPLACE SVC LINE-UNMTRD GAS | 2621P | LIMESTONE | 220 LIMESTONE ST | 161 | MAY | 2019-08-30 | U126286 | JDSKAGG | 2016-08-15 | 2016-09-15 |  |  | TYLER ALLISON | 2019-08-30 |  |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1895.02 | 0 | 0 | 0 | 1895.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18026754700 |  |  |  | 6716208E | 1749637 | U122858 |  | 561 | EX | INSTALL 640'-4"PMLP | 2600B | SOUTHLAND | SOUTHLAND DR | 067 | LEX | 2019-10-24 | U128132 | U122858 | 2018-03-01 | 2019-08-07 | 2019-08-30 | 2019-08-20 | A PARRIS | 2019-08-30 | 2019-07-15 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP7547 |  |  | 100 | 056132180267547 | 8 | 589 | 34674.16 | 583.48 | 2774.07 | 159.37 | 27200.9 | 0 | 138.27 | 3818.07 | 589
KY | KY - WEST | 2621 | 19026902900 |  |  |  | 6720212L | 1967433 | U132703 |  | 909 | EX | INSTALL ELECTRONIC EQUIP | 2600E | WINCHESTER | 1314 WINCHESTER RD | 067 | LEX | 2020-04-13 | U462463 | U132703 | 2019-10-15 | 2019-12-31 | 2019-12-31 | 2019-08-30 | NOLL DAVIS | 2019-08-30 |  |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00909 | 3200909 |  |  | WP9029 |  |  | 100 | 090932190269029 |  | 0 | 4765.04 | 0 | 3165.43 | 0 | 1613.75 | 0 | -14.14 | 0
KY | KY - CENTRAL | 2632 | 19671931100 |  | 100353872 |  | 7256280P | 1747939 |  |  | 565 | EX | RPLC SL/17026728200/ | 2600B | LIMESTONE | 226 LIMESTONE ST | 161 | MAY | 2019-08-30 | U126286 | U131066 | 2019-01-22 | 2019-11-27 |  |  | TYLER ALLISON | 2019-08-30 |  |  | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 |  | 1 | 1172.59 | 0 | 0 | 0 | 1172.59 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19707673500 |  | 100290228 |  | 6720212B | 1855586 |  |  | 565 | VO | RPLC SL/18026795700/ | 2600B | EDGELAWN | 1405 EDGELAWN AV | 067 | LEX | 2019-09-17 |  | U131066 | 2019-05-21 | 2019-11-27 |  |  | NEAL JOHNSON | 2019-08-30 |  | 2019-08-30 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.7333 | 1 | 1184.18 | 152.75 | 0 | 51.3 | 980.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19731484900 |  | 100298324 |  | 6716212H |  |  |  | 566 | EX | DEMO / RA 8-15-19 / ABANDON | 2621P | BALLARD | 630 BALLARD ST | 067 | LEX | 2019-08-30 | ATWILLI | U125208 | 2019-08-08 | 2019-09-06 |  |  | ATWILLI | 2019-08-30 | 2019-08-23 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.8833 | 7 | 912.92 | 839.75 | 25.6 | 47.57 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19736297200 |  | 100427205 |  | 7252276P |  |  |  | 566 | EX | ABANDON / IDLE | 2621P | OLD MAIN | 2332 OLD MAIN ST | 161 | MAY | 2019-09-05 | U125208 | U125208 | 2019-08-26 | 2019-09-16 |  |  | SDADAMS | 2019-08-30 | 2019-08-29 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 11.2 | 4 | 685.26 | 617.39 | 32.95 | 34.92 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19737669300 |  | 100290476 |  | 6720216O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094227 | 2621P | TANGLEWOOD | 4 TANGLEWOOD DR | 067 | LEX | 2019-09-05 | U125208 | U129005 | 2019-08-29 | 2019-08-29 | 2019-08-29 |  | JENSMIN | 2019-08-30 | 2019-08-29 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.05 | 2 | 3490.02 | 599.42 | 245.24 | 640.47 | 2004.89 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19737688700 |  | 100348713 |  | 6748208M |  |  |  | 565 | EX | REPLACE SERVICE LINE - D096354 | 2621P | WASHINGTON | 221 E WASHINGTON ST | 049 | WIN | 2019-08-30 | RJJOHNS | U125208 | 2019-08-29 | 2019-08-29 | 2019-08-29 |  | RJJOHNS | 2019-08-30 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 17.8 | 4 | 1399.61 | 794.01 | 256.94 | 44.88 | 303.78 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19738368200 |  | 100360453 |  | 6736228H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D000694 | 2621P | HILLCREST | 20 HILLCREST ST | 017 | PAR | 2019-08-30 | RJJOHNS | U124447 | 2019-08-30 | 2019-08-29 | 2019-08-29 |  | RJJOHNS | 2019-08-30 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 20.6667 | 4 | 1251.37 | 928.14 | 213.16 | 52.47 | 57.6 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19738430700 |  | 100359611 |  | 6736232O |  |  |  | 565 | EX | GRADE 1 REPLACE | 2621P | SPRINGHILL | 292 SPRINGHILL DR | 017 | PAR | 2019-08-30 | DENNING | U129939 | 2019-08-30 | 2019-08-30 | 2019-08-30 |  | DENNING | 2019-08-30 | 2019-08-30 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 22.8833 | 4 | 1319.41 | 979.66 | 161.72 | 152.11 | 25.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19738450400 |  | 100336998 |  | 6720212E |  |  |  | 565 | EX | GRADE 1 REPLACE D222178 | 2621P | 5TH | 252 E 5TH ST | 067 | LEX | 2019-09-05 | U125208 | U129939 | 2019-08-30 | 2019-08-30 | 2019-08-30 |  | JENSMIN | 2019-08-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.8167 | 1 | 9150.68 | 288.66 | 5484.22 | 308.46 | 3069.34 | 0 | 0 | 0
KY | KY - WEST | 2621 | 05618446000 |  | 100299666 |  | 6716212B | 1315787 |  |  | 566 | EX | ABANDON / LEAKAGE - D094552 | 2621P | LISLE INDUSTRI | 220 LISLE INDUSTRI AV | 067 | LEX | 2019-09-03 | LSTANFI | SSUTHER | 2005-07-29 | 2019-09-03 | 2020-08-31 |  | LSTANFI | 2019-09-03 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.75 | 1 | 2482.72 | 427.1 | 105.44 | 28.96 | 1921.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 12985079500 |  | 100290228 |  | 16720212C |  |  |  | 566 | EX | ABANDON / RI 08-20-2010 | 2600B | EDGELAWN | 1405 EDGELAWN AV | 067 | LEX | 2019-09-03 | U461516 | U125208 | 2012-08-20 | 2020-12-31 |  |  | NEAL JOHNSON | 2019-09-03 |  | 2019-09-03 | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 |  | 1 | 1.38 | 0 | 1.38 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18641088500 |  | 100327485 |  | 6720212M |  |  |  | 565 | EX | NBT-RELOC NEW SL W/100327486 | 2621P | CLAY | 266 CLAY AV 1FL | 067 | LEX | 2019-09-05 | U125208 | U125208 | 2018-09-06 | 2019-07-18 | 2019-08-14 |  | JWCOX | 2019-09-03 | 2019-07-31 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.4667 | 3 | 3188.18 | 582.88 | 377.67 | 38.84 | 2188.79 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18660482200 |  | 100278461 |  | 6688228B |  |  |  | 565 | EX | REPL SERV - ENCROACHMENT | 2621P | SHAWNEE | 1009 SHAWNEE TL | 073 | FRA | 2019-09-03 | CDESPAI | U125208 | 2018-12-04 | 2019-01-04 |  |  | CDESPAI | 2019-09-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 8.3 | 1 | 5600.05 | 483.58 | 392.97 | 964.18 | 3759.32 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19026860900 |  |  |  | 7240212N | 1745093 | U461383 |  | 583 | EX | RELOCATE REG STATION #1684 | 2600E | PAULA | PAULA DR | 173 | MT | 2019-09-26 | U462463 | U461383 | 2019-02-07 | 2019-09-26 | 2019-10-01 | 2019-09-03 | WADE SHIMFESSEL | 2019-09-03 | 2019-08-12 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00583 | 3200583 |  |  | WP8609 |  |  | 100 | 058332190268609 | 346.1167 | 378 | 24264.55 | 19331.11 | 90.08 | 1515.63 | 634.91 | 0 | 137.99 | 2554.83
KY | KY - CENTRAL | 2629 | 19026861000 |  |  |  | 7240212N | 1745093 | U461383 |  | 584 | EX | RETIRE PIT REGULATOR STATION | 2600E | PAULA | PAULA DR | 173 | MT | 2019-09-26 | U462463 | U461383 | 2019-02-07 | 2019-10-01 | 2019-10-01 | 2019-09-03 | WADE SHIMFESSEL | 2019-09-03 |  |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00584 | 3200584 |  |  | WP8610 |  |  | 100 | 058432190268610 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678786900 |  | 100299191 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LEESTOWN | 1527 LEESTOWN RD | 067 | LEX | 2019-09-03 | U126286 | U131066 | 2019-02-01 | 2019-11-27 |  |  | TYLER ALLISON | 2019-09-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1507.39 | 0 | 0 | 0 | 1507.39 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678787000 |  | 100299192 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LEESTOWN | 1533 LEESTOWN RD | 067 | LEX | 2019-09-03 | U126286 | U131066 | 2019-02-01 | 2019-11-27 |  |  | TYLER ALLISON | 2019-09-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1743.09 | 0 | 0 | 0 | 1743.09 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687823400 |  | 100280113 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | LYONS | 324 LYONS DR | 073 | FRA | 2019-09-03 | U126602 | U131066 | 2019-03-13 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.9667 | 1 | 1968.15 | 278.6 | 254.8 | 18.89 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687823800 |  | 100280045 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | LYONS | 329 LYONS DR | 073 | FRA | 2019-09-03 | U126602 | U131066 | 2019-03-13 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1990.69 | 0 | 227.7 | 0 | 1762.99 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689090300 |  | 100255584 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | ARGILLITE | 801 ARGILLITE RD | 089 | FLA | 2019-09-03 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-09-03 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.95 | 2 | 1657.91 | 53.85 | 0 | 11.05 | 1593.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691670700 |  | 100326535 |  | 6720208A | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1324 FONTAINE RD | 067 | LEX | 2019-09-03 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-09-03 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2793.3 | 0 | 0 | 0 | 2793.3 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703183800 |  | 100280109 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 251 HIGHLAND PY | 073 | FRA | 2019-09-03 | U126602 | U131066 | 2019-05-03 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1499.71 | 0 | 253.85 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703183900 |  | 100280051 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 252 HIGHLAND PY | 073 | FRA | 2019-09-03 | U126602 | U131066 | 2019-05-03 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-03 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.5333 | 1 | 1952.9 | 423.53 | 254.8 | 28.71 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19707673600 |  | 100290187 |  | 6720212B | 1855586 |  |  | 565 | EX | RPLC SL/18026795700/ | 2600B | EDGELAWN | 1406 EDGELAWN AV | 067 | LEX | 2019-09-03 | U461516 | U131066 | 2019-05-21 | 2019-11-27 |  |  | NEAL JOHNSON | 2019-09-03 |  | 2019-09-03 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.6833 | 1 | 1849.11 | 196.57 | 185.59 | 73.95 | 1393 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19725676800 |  | 500008331 |  | 6760248M | 1851783 | BKSLONE |  | 565 | EX | INSTALL 2" CSHP SRV TO HEATER | 2621P | HICKORY RIDGE | 900 HICKORY RIDGE RD HEATER | 181 | CAR | 2019-09-03 | U123110 | BKSLONE | 2019-07-19 | 2019-09-12 | 2019-09-30 |  | JOHN SMITH | 2019-09-03 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26290032 |  | 1
KY | KY - WEST | 2621 | 19734114600 |  | 100326799 |  | 6720208E | 1965588 |  |  | 565 | EX | NBT: SERVICE LINE - REPLACE | 2621P | ESSEX | 1409 ESSEX PR | 067 | LEX | 2019-09-05 | U125208 | U125208 | 2019-08-19 | 2019-08-19 | 2019-08-29 |  | JWCOX | 2019-09-03 | 2019-09-03 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 1.1333 | 2 | 7001.4 | 63.15 | 347.72 | 4.28 | 6586.25 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19736888600 |  | 100358776 |  | 6736232P |  |  |  | 565 | EX | REPLACE SERVICE LINE - D096281 | 2621P | 7TH | 560 W 7TH ST | 017 | PAR | 2019-09-03 | RJJOHNS | U125208 | 2019-08-27 | 2019-08-27 | 2019-08-27 |  | RJJOHNS | 2019-09-03 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 17.55 | 3 | 1007.83 | 703.23 | 256.94 | 47.66 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19736921600 |  | 100325863 |  | 6720208E |  |  |  | 565 | EX | SERVICE LINE - RELOCATE | 2621P | COLONY | 337 COLONY BV | 067 | LEX | 2019-09-03 | ATWILLI | U125208 | 2019-08-27 | 2019-08-30 |  |  | ATWILLI | 2019-09-03 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 13.35 | 2 | 917.97 | 685.66 | 107.11 | 46.48 | 78.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19737309600 |  | 100337661 |  | 6720212E |  |  |  | 566 | EX | ABANDON / RI 08-21-19 | 2621P | M L KING | 620 N M L KING BV | 067 | LEX | 2019-09-05 | U125208 | U125208 | 2019-08-28 | 2019-09-18 |  |  | WHIMES | 2019-09-03 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 25.7333 | 4 | 1309 | 1174.33 | 55.04 | 79.63 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19738379900 |  | 100405031 |  | 6688228I |  |  |  | 565 | EX | SL REPL | 2621P | COLLEGE PARK | 419 COLLEGE PARK DR | 073 | FRA | 2019-09-03 | CDESPAI | U125964 | 2019-08-30 | 2019-09-30 |  |  | CDESPAI | 2019-09-03 | 2019-08-30 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3.9167 | 2 | 3558.61 | 237.08 | 465.03 | 377.94 | 2478.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19738695600 |  | 100294408 |  | 6720212E |  |  |  | 565 | EX | REPLACE SERV LINE | 2621P | LIMESTONE | 561 N LIMESTONE ST | 067 | LEX | 2019-09-05 | U125208 | U129939 | 2019-09-03 | 2019-09-03 |  |  | LSTANFI | 2019-09-03 | 2019-09-03 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.1333 | 1 | 3590.35 | 451.2 | 356.11 | 30.59 | 2752.45 | 0 | 0 | 0
KY | KY - EAST | 2631 | 08760333800 |  | 100246061 | 13 | 7328284J |  |  |  | 566 | EX | RETIRE SL ASAP--SJ | 2600B | STATE RT 8 | 1639 STATE RT 8 | 089 | S P | 2019-09-04 | BROBERT | SJUDE | 2008-11-21 | 2019-09-24 | 2019-09-24 |  | BROBERT | 2019-09-04 | 2019-09-03 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 13.7333 | 4 | 737.35 | 524.98 | 22.36 | 190.01 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19026894500 |  |  |  | 6744208E | 1966393 | U128885 |  | 557 | EX | INSTALL 3' - 3" PMMP | 2621P | WINCHESTER | WINCHESTER PZ | 049 | WIN | 2020-01-07 | U128132 | U128885 | 2019-09-05 |  | 2049-12-31 | 2019-09-03 | WDENNINGHOFF | 2019-09-04 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP8945 |  |  | 100 | 055732190268945 |  | 4 | 12316.08 | 4701.08 | 465.32 | 2356.44 | 3197.88 | 0 | 0.66 | 1594.7 | 4
KY | KY - CENTRAL | 2629 | 19026894600 |  |  |  | 6744208E | 1966393 | U128885 |  | 558 | EX | RETIRE 3' - 3" PMP | 2621P | WINCHESTER | WINCHESTER PZ | 049 | WIN | 2020-01-07 | U128132 | U128885 | 2019-09-05 |  | 2049-12-31 | 2019-09-03 | WDENNINGOFF | 2019-09-04 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP8946 |  |  | 100 | 055832190268946 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680067800 |  | 100467563 |  | 6716208G | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 93 SHADY LN | 067 | LEX | 2019-09-04 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-09-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.1167 | 1 | 3694.16 | 63.85 | 0 | 13 | 3617.31 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680068600 |  | 100320242 |  | 6716208G | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | SHADY | 109 SHADY LN | 067 | LEX | 2019-09-04 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-09-04 | 2019-09-03 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.9167 | 2 | 5514.43 | 339.99 | 0 | 69.15 | 5105.29 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680447800 |  | 100298092 | 39 | 6716212L |  |  |  | 566 | EX | ABN / REMODEL / RI 02-08-19 | 2621P | SHORT | 109 W SHORT ST | 067 | LEX | 2019-09-06 | U125208 | JWCOX | 2019-02-08 | 2019-03-08 | 2019-03-08 |  | JWCOX | 2019-09-04 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.9333 | 2 | 881.92 | 130.05 | 17.75 | 8.82 | 725.3 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687822900 |  | 100280116 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | LYONS | 318 LYONS DR | 073 | FRA | 2019-09-04 | U126602 | U131066 | 2019-03-13 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1820.69 | 0 | 227.7 | 0 | 1592.99 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687823100 |  | 100280115 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | LYONS | 320 LYONS DR | 073 | FRA | 2019-09-04 | U126602 | U131066 | 2019-03-13 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1670.66 | 0 | 254.8 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687823500 |  | 100280043 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | LYONS | 325 LYONS DR | 073 | FRA | 2019-09-04 | U126602 | U131066 | 2019-03-13 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1670.66 | 0 | 254.8 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687823700 |  | 100280044 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | LYONS | 327 LYONS DR | 073 | FRA | 2019-09-04 | U126602 | U131066 | 2019-03-13 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 10.5 | 1 | 2300.44 | 589.79 | 254.8 | 39.99 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687823900 |  | 100280046 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | LYONS | 331 LYONS DR | 073 | FRA | 2019-09-04 | U126602 | U131066 | 2019-03-13 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-04 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1500.66 | 0 | 254.8 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691695600 |  | 100326533 |  | 6720208A | 1855692 |  |  | 565 | EX | REPLACE SL W/18026796400 | 2600B | FONTAINE | 1320 FONTAINE RD 1 | 067 | LEX | 2019-09-05 | U125559 | U131066 | 2019-03-27 | 2019-12-31 |  |  | BJACKSON | 2019-09-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 6684.97 | 0 | 0 | 0 | 6684.97 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19695149000 |  | 100334743 | 67 | 6724208A |  |  |  | 566 | EX | DEMO/ABN W/LCB - RA 02-04-19 | 2621P | WOODWARD | 651 WOODWARD LN | 067 | LEX | 2019-09-06 | U125208 | JFAWNS | 2019-04-05 | 2019-04-05 | 2019-09-19 |  | ASNICHO | 2019-09-04 | 2019-09-04 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 15.9667 | 4 | 943.49 | 853.99 | 31.6 | 57.9 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19707674500 |  | 100290195 |  | 6720212C | 1855586 |  |  | 566 | EX | ABN SL/18026795700 W/100290196 | 2600B | EDGELAWN | 1422 EDGELAWN AV FT | 067 | LEX | 2019-09-16 | U461516 | U131066 | 2019-05-21 | 2019-11-27 |  |  | NEAL JOHNSON | 2019-09-04 | 2019-09-04 | 2019-09-05 | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 2.8167 | 1 | 778.22 | 150.73 | 3.74 | 56.72 | 567.03 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19733999300 |  | 500526104 | 20 | 6724204A | 9613371 |  |  | 566 | EX | ABN BY 9/3/19 - RA 08-19-19 | 2621P | FOREST COVE | 3528 FOREST COVE LN | 067 | LEX | 2019-09-04 | JWCOX | JFAWNS | 2019-08-19 | 2019-09-03 | 2019-09-03 |  | JWCOX | 2019-09-04 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3 | 2 | 1115.65 | 135.35 | 12.9 | 9.18 | 958.22 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19736298400 |  | 100356938 |  | 7252276L |  |  |  | 565 | EX | AOC SERVICE LINE - REPLACE | 2621P | GREEN | 2229 GREEN ST | 161 | MAY | 2019-09-04 | SDADAMS | U125208 | 2019-08-26 | 2019-09-16 |  |  | SDADAMS | 2019-09-04 | 2019-08-29 |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26320055 | 30.3667 | 10 | 1921.44 | 1601.17 | 175.57 | 106.3 | 38.4 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19738980500 |  | 100239529 |  | 7352264E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D187701 | 2621P | BELLEFONTE | 509 BELLEFONTE ST | 089 | RUS | 2019-09-06 | U125208 | U129939 | 2019-09-04 | 2019-08-28 | 2019-08-28 |  | CWHEELE | 2019-09-04 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 33.6 | 6 | 4431.94 | 2738.73 | 251.04 | 1407.61 | 34.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19738992300 |  | 100349594 |  | 6748208M |  |  |  | 566 | EX | RETIRE SERVICE LINE - D097486 | 2621P | SEABOARD | 24 SEABOARD ST | 049 | WIN | 2019-09-09 | U125208 | U129939 | 2019-09-04 | 2019-08-23 | 2019-09-11 |  | RJJOHNS | 2019-09-04 | 2019-08-28 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26290043 | 18 | 10 | 1639.09 | 1465.12 | 82.88 | 91.09 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19739016000 |  | 100294068 |  | 6720212E |  |  |  | 565 | EX | REPLACE SERV LINE | 2621P | LIMESTONE | 643 N LIMESTONE ST | 067 | LEX | 2019-09-04 | JWCOX | U129939 | 2019-09-04 | 2019-09-04 |  |  | JWCOX | 2019-09-04 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 9.2333 | 2 | 2413.1 | 410.57 | 227.9 | 27.84 | 1746.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19739055100 |  | 100296274 |  | 6716216O |  |  |  | 565 | EX | GRADE 1 REPLACE SERV D094228 | 2621P | EFFIE | 945 EFFIE RD | 067 | LEX | 2019-09-06 | U125208 | U129939 | 2019-09-04 | 2019-09-04 | 2019-09-04 |  | JWCOX | 2019-09-04 | 2019-09-04 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.7667 | 3 | 2218.25 | 239.87 | 179.95 | 178.89 | 1619.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19739332000 |  | 100290196 |  | 6720212C | 1855586 |  |  | 566 | EX | ABANDON W/100290195 - MV OFF | 2600B | EDGELAWN | 1422 EDGELAWN AV RR | 067 | LEX | 2019-09-16 | U461516 | LCHAMBE | 2019-09-05 | 2019-09-05 |  |  | NEAL JOHNSON | 2019-09-04 |  | 2019-09-04 | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.1167 | 0 | 887.7 | 645.01 | 0 | 242.69 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19739744400 |  | 500421212 |  | 7240212J | 1745093 |  |  | 565 | EX | REPLACE SL W/19-0268607-00 | 2600B | LEVEE | 2203 LEVEE RD | 173 | MT | 2019-09-11 | U126604 | U131066 | 2019-09-06 | 2019-12-31 |  |  | WILL FULKS | 2019-09-04 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26290032 |  | 1 | 1810.09 | 0 | 60.59 | 0 | 1749.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18657396600 |  | 100280041 |  | 6688228N | 1853312 |  |  | 566 | EX | ABANDON SL W/18026777000 | 2600B | LYONS | 321 LYONS DR | 073 | FRA | 2019-09-16 | U131066 | U126926 | 2018-11-15 | 2019-12-31 |  |  | DEREK PAYTON | 2019-09-05 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 2.6833 | 1 | 1215.73 | 150.52 | 0 | 10.21 | 1055 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678787200 |  | 100299194 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LEESTOWN | 1545 LEESTOWN RD | 067 | LEX | 2019-09-05 | U126286 | U131066 | 2019-02-01 | 2019-11-27 |  |  | TYLER ALLISON | 2019-09-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2036.16 | 0 | 0 | 0 | 2036.16 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687822500 |  | 100280118 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | LYONS | 312 LYONS DR | 073 | FRA | 2019-09-05 | U126602 | U131066 | 2019-03-13 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 2.8 | 1 | 3258.82 | 157.84 | 0 | 10.69 | 3090.29 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687822700 |  | 100280039 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | LYONS | 313 LYONS DR | 073 | FRA | 2019-09-05 | U126602 | U131066 | 2019-03-13 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687823000 |  | 100280040 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | LYONS | 319 LYONS DR | 073 | FRA | 2019-09-05 | U126602 | U131066 | 2019-03-13 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687823300 |  | 100280042 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | LYONS | 323 LYONS DR | 073 | FRA | 2019-09-05 | U126602 | U131066 | 2019-03-13 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-05 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.0167 | 1 | 2508.07 | 281.41 | 0 | 19.07 | 2207.59 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689090500 |  | 100412344 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | ARGILLITE | 819 ARGILLITE RD | 089 | FLA | 2019-09-05 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-09-05 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.4 | 1 | 2464.02 | 23.24 | 0 | 4.77 | 2436.01 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691671200 |  | 100326541 |  | 6720208A | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1348 FONTAINE RD | 067 | LEX | 2019-09-05 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-09-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1737.19 | 0 | 0 | 0 | 1737.19 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691671300 |  | 100326542 |  | 6720208A | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1350 FONTAINE RD | 067 | LEX | 2019-09-05 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-09-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2542.93 | 0 | 0 | 0 | 2542.93 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19707675700 |  | 100290185 |  | 6720212B | 1855586 |  |  | 565 | EX | RPLC SL/18026795700/ | 2600B | EDGELAWN | 1402 EDGELAWN AV | 067 | LEX | 2019-09-05 | U461516 | U131066 | 2019-05-21 | 2019-11-27 |  |  | NEAL JOHNSON | 2019-09-05 |  | 2019-09-05 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.75 | 1 | 2459.33 | 466.06 | 261.98 | 175.36 | 1555.93 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19715177300 |  | 100301291 |  | 6712212H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D000068 | 2621P | DUNKIRK | 2044 DUNKIRK DR | 067 | LEX | 2019-09-06 | U125208 | U125208 | 2019-06-18 | 2019-09-05 | 2021-06-30 |  | JENSMIN | 2019-09-05 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.95 | 1 | 4874.2 | 852.02 | 1395.9 | 57.75 | 2568.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19736498700 |  | 100323357 |  | 6716208P | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER / | 2621D | RAVEN | 3225 RAVEN CR | 067 | LEX | 2019-09-09 | U125208 | AOC SYST | 2019-08-26 | 2019-09-20 | 2019-10-20 |  | WHIMES | 2019-09-05 | 2019-09-05 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 27.15 | 4 | 1778.76 | 1293.44 | 330.43 | 87.69 | 67.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19737209900 |  | 100348275 |  | 6748208I |  |  |  | 566 | EX | DEMO / ABANDON / RA 08-27-19 | 2621P | WINN | 43 WINN AV | 049 | WIN | 2019-09-10 | U125208 | U132002 | 2019-08-28 | 2019-08-19 | 2019-08-19 |  | DENNING | 2019-09-05 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 20.6667 | 4 | 1755.38 | 942.6 | 0 | 522.44 | 290.34 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19737217900 |  | 100451517 |  | 6748208I |  |  |  | 566 | EX | DEMO / ABANDON / RI 09-03-19 | 2621P | WINN | 49 WINN AV A | 049 | WIN | 2019-09-05 | DENNING | U132002 | 2019-08-28 | 2019-09-18 | 2019-09-18 |  | DENNING | 2019-09-05 | 2019-09-04 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 33.0833 | 8 | 2345.74 | 1506.97 | 0 | 838.77 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19737222100 |  | 100348278 |  | 6748208I |  |  |  | 566 | EX | DEMO / ABANDON / RA 08-28-19 | 2621P | WINN | 51 WINN AV | 049 | WIN | 2019-09-05 | DENNING | U132002 | 2019-08-28 | 2019-10-07 | 2019-10-28 |  | DENNING | 2019-09-05 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 1.2 | 4 | 85.21 | 54.79 | 0 | 30.42 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19738975600 |  | 100358739 |  | 6740232I | 1962701 |  |  | 565 | EX | REPLACE SL W/19-0268691-00 | 2600B | CYPRESS | 706 CYPRESS EX | 017 | PAR | 2019-09-05 | U461443 | U131066 | 2019-09-04 | 2019-12-31 |  |  | WGRAVES | 2019-09-05 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26290032 | 10 | 1 | 3050.89 | 516.52 | 0 | 199.34 | 2335.03 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19738993900 |  | 100254325 |  | 7348264N |  |  |  | 565 | EX | GRADE 1 REPLACE | 2621P | WILKERSON | 1213 WILKERSON ST | 089 | FLA | 2019-09-05 | MCOLLET | U129939 | 2019-09-04 | 2019-09-04 | 2019-09-04 |  | MCOLLET | 2019-09-05 | 2019-09-04 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 37.3333 | 4 | 3871.65 | 2215.9 | 224.13 | 1390.34 | 41.28 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19739039600 |  | 100254323 |  | 7348264N |  |  |  | 565 | EX | REPLACE SERVICE | 2621P | WILKERSON | 1215 WILKERSON ST | 089 | FLA | 2019-09-10 | U125208 | U131168 | 2019-09-04 | 2019-09-04 |  |  | MCOLLET | 2019-09-05 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.31667 | 1 | 258.22 | 19.02 | 140.54 | 23.78 | 74.88 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19739335000 |  | 100255579 |  | 7348264L | 1859009 |  |  | 565 | EX | REPLACE W/18026843700 | 2600B | ARGILLITE | 1003 ARGILLITE RD | 089 | FLA | 2019-09-05 | U124015 | U125768 | 2019-09-05 | 2049-12-31 |  |  | ORA SLONE | 2019-09-05 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.43333 | 1 | 1827.02 | 24.37 | 0 | 5.01 | 1797.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19739387500 |  | 100313151 |  | 6716208A |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | LONE OAK | 514 LONE OAK DR | 067 | LEX | 2019-09-05 | LSTANFI | U131168 | 2019-09-05 | 2019-09-04 | 2019-09-04 |  | LSTANFI | 2019-09-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.4833 | 1 | 3204.54 | 410.66 | 108.15 | 27.84 | 2657.89 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 13108762800 |  | 100268959 |  | 6736252M |  |  |  | 566 | EX | ABANDON / RI 12-30-10 / CONVRT | 2621P | VINE | 104 VINE ST | 097 | CYN | 2019-09-06 | RJJOHNS | U908784 | 2013-01-09 | 2019-09-20 | 2019-09-21 |  | RJJOHNS | 2019-09-06 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 24.4667 | 4 | 1120.78 | 1044.03 | 5.97 | 70.78 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 14258297100 |  | 100248476 |  | 7356256J |  |  |  | 566 | EX | ABANDON SL | 2600B | LOGAN | 3920 LOGAN ST | 019 | ASH | 2019-09-17 | U125208 | U125201 | 2014-10-17 | 2019-09-06 |  |  | BROBERT | 2019-09-06 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.31667 | 1 | 44.54 | 16.83 | 21.49 | 6.22 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19026869100 |  | 501018724 |  | 6740232M | 1962701 | U128885 |  | 555 | EX | INSTALL 150' - 4" PMMP | 2600B | CYPRESS | 703 CYPRESS ST | 017 | PAR | 2019-09-12 | U128132 | U128885 | 2019-04-03 | 2019-08-27 | 2019-08-31 | 2019-09-04 | WGRAVES | 2019-09-06 | 2019-08-24 | 2019-08-24 | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP8691 |  |  | 100 | 055532190268691 | 69.7 | 1773 | 58200.14 | 3762.43 | 1695.64 | 1236.59 | 46407.61 | 0 | 87.39 | 5010.48 | 197
KY | KY - WEST | 2621 | 19026889300 |  |  |  | 6716216O | 1425507 | BKSLONE |  | 561 | EX | INSTALL 6" SS | 2600B | GEORGETOWN | 924 GEORGETOWN ST | 067 | LEX | 2019-09-23 | U460266 | BKSLONE | 2019-08-02 | 2019-09-05 | 2019-09-13 | 2019-09-05 | DDAVIS | 2019-09-06 | 2019-09-03 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3207513 |  |  | WP8893 | AMRCB |  | 100 | 751332190268893 | 73.5167 | 0 | 13497.3 | 4198.49 | 500.84 | 1623.88 | 5808.72 | 0 | 24.24 | 1341.13
KY | KY - WEST | 2621 | 19026889400 |  |  |  | 6716216O | 1425507 | BKSLONE |  | 562 | EX | RETIRE 1060'-6"/4" BSHP + GV | 2600B | GEORGETOWN | 924 GEORGETOWN ST | 067 | LEX | 2019-09-17 | U460266 | BKSLONE | 2019-08-02 | 2020-05-31 | 2021-01-11 | 2019-09-05 | DDAVIS | 2019-09-06 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3207514 |  |  | WP8894 | AMRCB |  | 100 | 751432190268894 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678787400 |  | 100299196 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LEESTOWN | 1553 LEESTOWN RD | 067 | LEX | 2019-09-06 | U126286 | U131066 | 2019-02-01 | 2019-11-27 |  |  | TYLER ALLISON | 2019-09-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1505.47 | 0 | 0 | 0 | 1505.47 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680087300 |  | 100320245 |  | 6716208G | 1748686 |  |  | 565 | EX | REPLACE SL W/17026736100 | 2600B | SHADY | 103 SHADY LN | 067 | LEX | 2019-09-06 | U126284 | U131066 | 2019-02-07 | 2019-12-31 |  |  | JOSH PASLEY | 2019-09-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9 | 1 | 4534.31 | 517.77 | 0 | 105.29 | 3911.25 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687822300 |  | 100280038 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | LYONS | 311< LYONS DR | 073 | FRA | 2019-09-06 | U126602 | U131066 | 2019-03-13 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.9833 | 1 | 1544.56 | 279.73 | 0 | 18.97 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687823200 |  | 100280114 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | LYONS | 322 LYONS DR | 073 | FRA | 2019-09-06 | U126602 | U131066 | 2019-03-13 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689090400 |  | 100255582 |  | 7348264L | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | ARGILLITE | 809 ARGILLITE RD | 089 | FLA | 2019-09-06 | U124015 | U131066 | 2019-03-18 | 2019-09-06 |  |  | ORA SLONE | 2019-09-06 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.43333 | 1 | 1893.94 | 24.95 | 0 | 5.12 | 1863.87 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689196300 |  | 100446861 |  | 7348264H | 1859009 |  |  | 565 | EX | REPLACE SL W/18026843700 | 2600B | ARGILLITE | 709 ARGILLITE RD | 089 | FLA | 2019-09-06 | U124015 | U131066 | 2019-03-18 | 2019-12-31 |  |  | ORA SLONE | 2019-09-06 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1594.94 | 0 | 0 | 0 | 1594.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691696300 |  | 100326539 |  | 6720208A | 1855692 |  |  | 565 | EX | REPLACE SL W/18026796400 | 2600B | FONTAINE | 1336 FONTAINE RD | 067 | LEX | 2019-09-06 | U125559 | U131066 | 2019-03-27 | 2019-12-31 |  |  | BJACKSON | 2019-09-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2737.95 | 0 | 310.3 | 0 | 2427.65 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19703184200 |  | 100280110 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | HIGHLAND | 255 HIGHLAND PY | 073 | FRA | 2019-09-06 | U126602 | U131066 | 2019-05-03 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-06 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.0167 | 1 | 3677.38 | 225.82 | 0 | 15.31 | 3436.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19707673100 |  | 100290182 |  | 6720212B | 1855586 |  |  | 565 | EX | RPLC SL/18026795700/ | 2600B | BLUE GRASS | 337 BLUE GRASS AV | 067 | LEX | 2019-09-07 | U461516 | U131066 | 2019-05-21 | 2019-11-27 |  |  | NEAL JOHNSON | 2019-09-06 |  | 2019-09-06 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.5 | 1 | 1813.14 | 505.98 | 191.66 | 190.38 | 925.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19708204200 |  | 500008670 |  | 6780204L |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CLUBHOUSE | 101 CLUBHOUSE DR | 113 | NIC | 2019-09-10 | U125208 | U125208 | 2019-05-22 | 2019-09-06 | 2021-05-31 |  | LSTANFI | 2019-09-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.95 | 1 | 2197.68 | 79.37 | 154.76 | 5.41 | 1958.14 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19734924900 |  | 100254305 |  | 7348264N |  |  |  | 566 | EX | ABANDON / RA 08-28-19 / CONVRT | 2621P | PATTERSON | 1416 PATTERSON ST | 089 | FLA | 2019-09-06 | AMCCORM | U132002 | 2019-08-21 | 2019-10-01 | 2019-10-22 |  | AMCCORM | 2019-09-06 | 2019-08-28 |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 57.9667 | 11 | 4123.44 | 2322.73 | 86.82 | 1634.39 | 79.5 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19738398700 |  | 100405419 |  | 6764176O |  |  |  | 566 | EX | DEMO / ABANDON / RI 09-04-19 | 2621P | CHURCH | 115 CHURCH ST | 065 | IRV | 2019-09-11 | U125208 | U132002 | 2019-08-30 | 2019-10-09 | 2019-10-30 |  | DENNING | 2019-09-06 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 21.0667 | 4 | 1499.4 | 960.75 | 10.27 | 528.38 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19738700200 |  | 100342069 |  | 7240216N |  |  |  | 566 | EX | DEMO / ABANDON / RI 09-04-19 | 2621P | JOHNSON | 27 JOHNSON AV | 173 | MT | 2019-09-11 | U125208 | U132002 | 2019-09-03 | 2019-10-10 | 2019-10-31 |  | DENNING | 2019-09-06 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 16.7333 | 4 | 1229.44 | 763.45 | 42.06 | 423.93 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19738992600 |  | 100349595 |  | 6748208M |  |  |  | 566 | EX | PAPER ABANDON | 2621P | SEABOARD | 26 SEABOARD ST | 049 | WIN | 2019-09-06 | RJJOHNS | U129939 | 2019-09-04 | 2019-09-04 |  |  | RJJOHNS | 2019-09-06 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.3333 | 4 | 456.37 | 357.16 | 75.01 | 24.2 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19739713200 |  | 100344904 |  | 6700224O |  |  |  | 565 | EX | REPLACE SERV / EFGOINS D192920 | 2621P | STEPHENS | 124 E STEPHENS ST | 239 | MID | 2019-09-10 | U125208 | U462294 | 2019-09-05 | 2019-09-05 |  |  | DCOLLIN | 2019-09-06 | 2019-09-05 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.2667 | 2 | 358.09 | 71.07 | 164.62 | 77.28 | 45.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19739742100 |  | 500017944 |  | 6712204M |  |  |  | 565 | EX | REPLACE SERV LINE - D094867 | 2621P | SUMMERTREE | 114 SUMMERTREE DR | 113 | NIC | 2019-09-11 | U125208 | U129939 | 2019-09-06 | 2020-01-31 |  |  | LSTANFI | 2019-09-06 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.3667 | 1 | 2462.21 | 86.2 | 113.81 | 5.85 | 2256.35 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 11881545600 |  | 500031816 |  | 7256280P |  |  |  | 566 | EX | ABANDON/ IDLE 48MO/ RI 02-2008 | 2621P | 6TH | 330 E 6TH ST | 161 | MAY | 2019-09-07 | SDADAMS | U906609 | 2011-01-27 | 2019-09-06 |  |  | SDADAMS | 2019-09-07 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 1.1833 | 1 | 70.46 | 65.99 | 0 | 4.47 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673607300 |  | 100310462 |  | 6712208L | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2817 CLAYS MILL RD | 067 | LEX | 2019-09-09 | U461439 | U131066 | 2019-01-30 | 2019-11-27 |  |  | A PARRIS | 2019-09-07 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2204.53 | 0 | 240.01 | 0 | 1964.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19707673300 |  | 100290229 |  | 6720212B | 1855586 |  |  | 565 | EX | RPLC SL/18026795700/ | 2600B | EDGELAWN | 1403 EDGELAWN AV | 067 | LEX | 2019-09-17 | U125208 | U131066 | 2019-05-21 | 2019-11-27 |  |  | NEAL JOHNSON | 2019-09-07 |  | 2019-09-07 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1274.8 | 0 | 0 | 0 | 1274.8 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19740026500 |  | 500571937 |  | 7348264H |  |  |  | 565 | EX | REPLACE SERV LINE | 2621P | ARGILLITE | 708 ARGILLITE RD | 089 | FLA | 2019-09-07 | U124015 | U129939 | 2019-09-07 | 2019-09-06 |  |  | ORA SLONE | 2019-09-07 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26310031 | 0.21667 | 2 | 2140.12 | 12.46 | 0 | 2.57 | 2125.09 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 14192873100 |  | 500329090 |  | 7240216H |  |  |  | 566 | EX | ABANDON SERV- UNITED STORAGE | 2621P | MIDLAND | 211 MIDLAND TL E4 | 173 | MT | 2019-09-11 | U125208 | U124961 | 2014-01-13 | 2049-12-31 |  |  | DENNING | 2019-09-09 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4.1333 | 4 | 275.72 | 188.16 | 0 | 87.56 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680085600 |  | 100320264 |  | 6716208G | 1748686 |  |  | 565 | EX | REPLACE SL W/17026736100 | 2600B | MCDONALD | 1848 MCDONALD AV | 067 | LEX | 2019-09-10 | U126284 | U131066 | 2019-02-07 | 2019-12-31 |  |  | JOSH PASLEY | 2019-09-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2091.86 | 0 | 0 | 0 | 2091.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687821700 |  | 100280121 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | LYONS | 306 LYONS DR | 073 | FRA | 2019-09-10 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1295.78 | 0 | 0 | 0 | 1295.78 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687821800 |  | 100280034 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | LYONS | 307 LYONS DR | 073 | FRA | 2019-09-09 | U126602 | U131066 | 2019-03-13 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1762.99 | 0 | 0 | 0 | 1762.99 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687821900 |  | 100280120 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | LYONS | 308 LYONS DR | 073 | FRA | 2019-09-09 | U126602 | U131066 | 2019-03-13 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.5 | 1 | 1515.76 | 252.75 | 0 | 17.15 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687822000 |  | 100280036 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | LYONS | 309 LYONS DR | 073 | FRA | 2019-09-09 | U126602 | U131066 | 2019-03-13 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687822200 |  | 100280037 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | LYONS | 311 LYONS DR | 073 | FRA | 2019-09-09 | U126602 | U131066 | 2019-03-13 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-09 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.5333 | 1 | 1747.53 | 310.62 | 0 | 21.05 | 1415.86 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689090200 |  | 100255586 |  | 7348264H | 1859009 |  |  | 565 | EX | RPLC SL/18026843700/ | 2600B | ARGILLITE | 725 ARGILLITE RD | 089 | FLA | 2019-09-09 | U124015 | U131066 | 2019-03-18 | 2019-09-09 |  |  | ORA SLONE | 2019-09-09 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.58333 | 1 | 1778.18 | 33.43 | 0 | 6.88 | 1737.87 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689093200 |  | 100255811 |  | 7348264L | 1859009 |  |  | 566 | EX | ABND SL/18026843700/ | 2600B | TURLEY | 1004 TURLEY AV | 089 | FLA | 2019-09-09 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-09-09 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 |  | 1
KY | KY - EAST | 2631 | 19689093300 |  | 100255806 |  | 7348264L | 1859009 |  |  | 566 | EX | ABND SL/18026843700/ | 2600B | TURLEY | 1005 TURLEY AV | 089 | FLA | 2019-09-09 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-09-09 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 |  | 1
KY | KY - EAST | 2631 | 19689093700 |  | 100255804 |  | 7348264L | 1859009 |  |  | 566 | EX | ABND SL/18026843700/ | 2600B | TURLEY | 1012 TURLEY AV | 089 | FLA | 2019-09-09 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-09-09 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 |  | 1
KY | KY - WEST | 2621 | 19691670500 |  | 100326529 |  | 6720208A | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1316 FONTAINE RD | 067 | LEX | 2019-09-09 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-09-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2302.13 | 0 | 0 | 0 | 2302.13 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19694358000 |  | 100457833 |  | 6720204O |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094075 | 2621P | GLEN OAK | 3633 GLEN OAK WY | 067 | LEX | 2019-09-11 | U125208 | U125208 | 2019-04-03 | 2019-10-02 | 2021-04-30 |  | JWCOX | 2019-09-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.0333 | 1 | 3760.37 | 113.63 | 178.94 | 7.7 | 3460.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19708203700 |  | 500017941 |  | 6712204I |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094868 | 2621P | BRANNON | 300 BRANNON RD | 113 | NIC | 2019-09-11 | U125208 | U125208 | 2019-05-22 | 2019-09-05 | 2021-05-31 |  | JWCOX | 2019-09-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.4167 | 1 | 2161.34 | 358.75 | 178.94 | 24.32 | 1599.33 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19721797600 |  | 100430032 |  | 7240216O | 1855043 |  |  | 566 | EX | II - METER ABANDON OR CO SOII | 2621P | HIGH | 203 E HIGH ST RS | 173 | MT | 2019-09-11 | U125208 | U126129 | 2019-07-03 | 2019-07-30 | 2019-08-30 |  | DENNING | 2019-09-09 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.66667 | 4 | 42.81 | 29.22 | 0 | 13.59 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19737225000 |  | 100302186 |  | 6712212L |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | VERSAILLES | 2089 VERSAILLES RD | 067 | LEX | 2019-09-09 | JENSMIN | U129005 | 2019-08-28 | 2019-08-28 |  |  | JENSMIN | 2019-09-09 | 2019-08-28 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 16.35 | 3 | 7773.21 | 953.35 | 657.11 | 1136.27 | 5026.48 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19739048100 |  | 100347935 |  | 6748208I |  |  |  | 566 | EX | ABN ASAP DEMO--NCV--RA 9-3-19 | 2621P | MAIN | 608 N MAIN ST | 049 | WIN | 2019-09-09 | RJJOHNS | U125208 | 2019-09-04 | 2019-09-25 |  |  | RJJOHNS | 2019-09-09 | 2019-09-09 |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 8.3167 | 4 | 356.73 | 334.06 | 0 | 22.67 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19740232200 |  | 100312086 |  | 6716208I |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094024 | 2621P | HILL N DALE | 281 HILL N DALE RD | 067 | LEX | 2019-09-11 | U125208 | U129939 | 2019-09-09 | 2019-12-20 | 2021-06-30 |  | JWCOX | 2019-09-09 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26210022 | 1.1833 | 1 | 3559.08 | 100.77 | 5.53 | 6.84 | 3445.94 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 11904200600 |  | 100448873 |  | 6740232I |  |  |  | 566 | EX | ABANDON/ IDLE 24MO/ RI 04-2010 | 2621P | BROOKS | 240 BROOKS ST | 017 | PAR | 2019-09-10 | DBANKS | U906631 | 2011-04-29 | 2017-12-29 |  |  | DBANKS | 2019-09-10 | 2019-09-10 |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 20.4 | 4 | 993.46 | 877.07 | 56.88 | 59.51 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18602167100 |  | 100280033 |  | 6688228J | 1748294 |  |  | 565 | EX | RPLC SL/17026731300/ | 2621P | STRATHMORE | 300 STRATHMORE DR A | 073 | FRA | 2019-09-12 | U461375 | U125964 | 2018-04-11 | 2018-11-30 |  |  | LARRY BROWN | 2019-09-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1812.39 | 0 | 0 | 0 | 1812.39 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19026857200 |  |  |  | 7348264H | 1859009 | U461383 |  | 584 | EX | RETIRE REG STATION W/AMRP | 2600E | ARGILLITE | 1001 ARGILLITE RD | 089 | FLA | 2019-09-26 | U462463 | U461383 | 2019-01-20 | 2019-12-31 | 2019-12-31 | 2019-09-10 | JOSHUA MULLINS | 2019-09-10 | 2019-09-09 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00584 | 3200584 |  |  | WP8572 | AMRCB |  | 100 | 058432190268572 | 16.0833 | 0 | 8397.38 | 1132.73 | 332.82 | 382.52 | 6525.32 | 0 | 23.99 | 0
KY | KY - WEST | 2621 | 19026882701 |  | 501122881 |  | 6724208L | 1964909 | U461383 |  | 555 | EX | INSTALL 90' OF 2"PMMP MAIN | 2600B | LAWSON | 3360 LAWSON LN | 067 | LEX | 2019-11-12 | U128132 | U461383 | 2019-09-09 | 2019-07-22 | 2019-09-15 | 2019-09-10 | WILL FULKS | 2019-09-10 | 2019-09-09 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP8827 |  |  | 100 | 055532190268827 | 41.4167 | 729 | 19457.63 | 2331.52 | 372.16 | 481.06 | 14356.32 | 0 | 40.98 | 1875.59 | 81
KY | KY - WEST | 2621 | 19678776900 |  | 100299104 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | FORBES | 1428 N FORBES RD | 067 | LEX | 2019-09-11 | U126286 | U131066 | 2019-02-01 | 2019-11-27 |  |  | TYLER ALLISON | 2019-09-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1328.99 | 0 | 0 | 0 | 1328.99 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678777000 |  | 100299103 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | FORBES | 1430 N FORBES RD | 067 | LEX | 2019-09-10 | U126286 | U131066 | 2019-02-01 | 2019-11-27 |  |  | TYLER ALLISON | 2019-09-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1742.75 | 0 | 0 | 0 | 1742.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680066900 |  | 100320261 |  | 6716208G | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | MCDONALD | 1833 MCDONALD AV | 067 | LEX | 2019-09-10 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-09-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.4667 | 1 | 3188.68 | 372.2 | 0 | 75.69 | 2740.79 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687825300 |  | 100280078 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | QUEENSWAY | 253 QUEENSWAY DR | 073 | FRA | 2019-09-10 | U126602 | U131066 | 2019-03-13 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1828.25 | 0 | 0 | 0 | 1828.25 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687825400 |  | 100280080 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | QUEENSWAY | 254 QUEENSWAY DR | 073 | FRA | 2019-09-10 | U126602 | U131066 | 2019-03-13 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.6667 | 1 | 2946.72 | 374.1 | 0 | 25.36 | 2547.26 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687825500 |  | 100280077 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | QUEENSWAY | 255 QUEENSWAY DR | 073 | FRA | 2019-09-10 | U126602 | U131066 | 2019-03-13 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.7833 | 1 | 2236.83 | 380.83 | 0 | 25.83 | 1830.17 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687825600 |  | 100280081 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | QUEENSWAY | 256 QUEENSWAY DR | 073 | FRA | 2019-09-10 | U126602 | U131066 | 2019-03-13 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-10 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1281.38 | 0 | 0 | 0 | 1281.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691695500 |  | 100326528 |  | 6720208A | 1855692 |  |  | 565 | EX | REPLACE SL W/18026796400 | 2600B | FONTAINE | 1314 FONTAINE RD | 067 | LEX | 2019-09-10 | U125559 | U131066 | 2019-03-27 | 2019-12-31 |  |  | BJACKSON | 2019-09-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 4611.26 | 0 | 0 | 0 | 4611.26 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19705073700 |  | 100467925 |  | 6712208L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094860 | 2621P | WACO | 2932 WACO RD | 067 | LEX | 2019-09-11 | U125208 | U125208 | 2019-05-10 | 2019-11-08 | 2021-05-31 |  | JWCOX | 2019-09-10 | 2019-09-03 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.25 | 3 | 3086.41 | 461.19 | 178.94 | 31.26 | 2415.02 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19711590500 |  | 100273688 |  | 6684228M | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | EXMOOR | 212 EXMOOR DR | 073 | FRA | 2019-09-10 | CDESPAI | AOC SYST | 2019-06-04 | 2019-12-04 | 2020-12-31 |  | CDESPAI | 2019-09-10 | 2019-09-06 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.4333 | 2 | 3523.49 | 316.19 | 354.9 | 630.34 | 2222.06 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19711591600 |  | 100273668 |  | 6684228M | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2623D | JUNIPER | 204 JUNIPER DR | 073 | FRA | 2019-09-10 | CDESPAI | AOC SYST | 2019-06-04 | 2019-12-04 | 2020-12-31 |  | CDESPAI | 2019-09-10 | 2019-08-02 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.7333 | 3 | 3358.8 | 454.63 | 336.33 | 884.93 | 1682.91 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19720513500 |  | 100410587 |  | 6716208D |  |  |  | 565 | EX | REPLACE SERVICE LINE - D093767 | 2621P | COOPER | 560 COOPER DR | 067 | LEX | 2019-09-11 | U125208 | U125208 | 2019-06-28 | 2019-12-27 | 2021-06-30 |  | JENSMIN | 2019-09-10 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.9667 | 1 | 5542.46 | 226.83 | 906.49 | 304.35 | 4104.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19720513900 |  | 100320017 |  | 6716208L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D093791 | 2621P | GLENDOVER | 354 GLENDOVER RD | 067 | LEX | 2019-09-10 | JWCOX | U125208 | 2019-06-28 | 2019-09-09 | 2021-06-30 |  | JWCOX | 2019-09-10 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.4 | 2 | 2742.85 | 171.27 | 291.67 | 26.41 | 2253.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19729820700 |  | 100334681 |  | 6720208D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER / | 2621D | WILDERNESS | 2355 WILDERNESS PL | 067 | LEX | 2019-09-10 | ATWILLI | AOC SYST | 2019-08-02 | 2019-08-30 | 2019-09-29 |  | ATWILLI | 2019-09-10 | 2019-09-10 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.9667 | 4 | 632.01 | 382.17 | 145.43 | 59.29 | 45.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19738382000 |  | 100331294 |  | 6720212N |  |  |  | 565 | EX | REPLACE SERV LINE G1 D221764 | 2621P | OWSLEY | 130 OWSLEY AV | 067 | LEX | 2019-09-11 | U125208 | U129939 | 2019-08-30 | 2019-08-28 | 2019-08-28 |  | JENSMIN | 2019-09-10 | 2019-08-30 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.8667 | 2 | 4232.77 | 220.44 | 960 | 292.87 | 2759.46 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19740221500 |  | 100319545 |  | 6716208K |  |  |  | 565 | EX | GRADE 1 REPLACE D221976 | 2621P | GREENBRIAR | 335 GREENBRIAR RD | 067 | LEX | 2019-09-11 | U125208 | U131167 | 2019-09-09 | 2019-09-09 | 2019-09-09 |  | JWCOX | 2019-09-10 | 2019-09-09 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.65 | 2 | 3608.36 | 205.43 | 295.48 | 13.92 | 3093.53 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19026895900 |  |  |  | 6716232E | 1966596 | U130604 |  | 557 | EX | REPLACE MAIN - LEAKAGE | 2621P | CLUBHOUSE | CLUBHOUSE | 209 | GEO | 2020-04-02 | U128132 | U130604 | 2019-09-12 | 2020-05-29 |  | 2019-09-11 | CDESPAIN | 2019-09-11 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP8959 |  |  | 100 | 055732190268959 |  | 4 | 2657.76 | 277.85 | 13.36 | 213.2 | 1898.19 | 0 | 0.32 | 254.84 | 4
KY | KY - WEST | 2623 | 19026896000 |  |  |  | 6716232E | 1966596 | U130604 |  | 558 | EX | RETIRE MAIN - LEAKAGE | 2621P | CLUBHOUSE | CLUBHOUSE | 209 | GEO | 2020-04-02 | U128132 | U130604 | 2019-09-12 | 2020-05-29 |  | 2019-09-11 | CDESPAIN | 2019-09-11 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP8960 |  |  | 100 | 055832190268960 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678776800 |  | 100299105 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | FORBES | 1426 N FORBES RD | 067 | LEX | 2019-09-11 | U126286 | U131066 | 2019-02-01 | 2019-11-27 |  |  | TYLER ALLISON | 2019-09-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 997.47 | 0 | 0 | 0 | 997.47 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687821000 |  | 100280088 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | KINGSWAY | 252 KINGSWAY DR | 073 | FRA | 2019-09-11 | U126602 | U131066 | 2019-03-13 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 4.95 | 1 | 1712.76 | 278.05 | 0 | 18.85 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687821200 |  | 100280089 |  | V-809/26 | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | KINGSWAY | 254 KINGSWAY DR | 073 | FRA | 2019-09-11 | U126602 | U131066 | 2019-03-13 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.3 | 1 | 2627.8 | 297.69 | 0 | 20.18 | 2309.93 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687821300 |  | 100280090 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | KINGSWAY | 256 KINGSWAY DR | 073 | FRA | 2019-09-12 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2205.89 | 0 | 0 | 0 | 2205.89 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687821600 |  | 100280122 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | LYONS | 304 LYONS DR | 073 | FRA | 2019-09-12 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1480.18 | 0 | 0 | 0 | 1480.18 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691670100 |  | 100326523 |  | 6720208A | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1220 FONTAINE RD | 067 | LEX | 2019-09-11 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACSKON | 2019-09-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1657.47 | 0 | 0 | 0 | 1657.47 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691670200 |  | 100326524 |  | 6720208A | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1300 FONTAINE RD | 067 | LEX | 2019-09-11 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-09-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3107.75 | 0 | 773.88 | 0 | 2333.87 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19707367500 |  | 500007492 |  | 6712208M |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094866 | 2621P | PALMETTO | 4081 PALMETTO DR | 067 | LEX | 2019-09-12 | U125208 | U125208 | 2019-05-20 | 2019-11-15 | 2021-05-31 |  | JWCOX | 2019-09-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.0333 | 1 | 2194.94 | 58.22 | 178.48 | 3.94 | 1954.3 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19720514000 |  | 100312958 |  | 6716208E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D093832 | 2621P | CLAYS MILL | 2116 CLAYS MILL RD | 067 | LEX | 2019-09-11 | JWCOX | U125208 | 2019-06-28 | 2019-09-11 | 2021-06-30 |  | JWCOX | 2019-09-11 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.8167 | 1 | 3555.14 | 605.02 | 343.57 | 41 | 2565.55 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19723710700 |  | 100287658 | 29 | 6720212G |  |  |  | 566 | EX | ABANDON / RI 7-12-19 / CONVRT | 2621P | CARNEAL | 944 CARNEAL RD | 067 | LEX | 2019-09-12 | U125208 | JEMARTI | 2019-07-12 | 2019-09-12 |  |  | ASNICHO | 2019-09-11 | 2019-09-11 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 9.3833 | 2 | 620.51 | 508.01 | 78.06 | 34.44 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19731451100 |  | 100282178 |  | 6712228C |  |  |  | 566 | EX | ABANDON SL W/100282177 | 2621P | WASHINGTON | 337 E WASHINGTON ST | 209 | GEO | 2019-09-11 | EFGOINS | U132002 | 2019-08-08 | 2019-09-06 | 2019-09-27 |  | EFGOINS | 2019-09-11 | 2019-09-11 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 16.3833 | 2 | 1434.99 | 884.64 | 0 | 550.35 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19737314600 |  | 100359963 |  | 6740232M |  |  |  | 565 | EX | REPLACE SERVICE LINE - D096282 | 2621P | HIGH | 417 HIGH ST | 017 | PAR | 2019-09-12 | U125208 | U125208 | 2019-08-28 | 2019-08-28 | 2019-08-28 |  | DBANKS | 2019-09-11 | 2019-09-04 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 41.15 | 9 | 2241.19 | 1793.74 | 255.79 | 121.58 | 70.08 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19738965900 |  | 100282430 |  | 6712232L |  |  |  | 565 | EX | SERVICE LINE - REPLACE - CONT | 2621P | DEGARIS MILL | 1066 DEGARIS MILL RD | 209 | GEO | 2019-09-11 | CDESPAI | U125208 | 2019-09-04 | 2019-09-11 |  |  | CDESPAI | 2019-09-11 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 12.2833 | 1 | 4889.63 | 716.87 | 308.96 | 1429.33 | 2434.47 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19740029300 |  | 100286391 |  | 6768172F |  |  |  | 565 | EX | GRADE 1 REPLACE | 2621P | 3RD | 108 3RD ST | 065 | RAV | 2019-09-11 | DENNING | U129939 | 2019-09-07 | 2019-09-06 | 2019-09-06 |  | DENNING | 2019-09-11 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 37.1333 | 4 | 2863.28 | 1696.75 | 177.35 | 942.14 | 47.04 | 0 | 0 | 0
KY | KY - EAST | 2631 | 06653372600 |  | 100255697 |  | 7348264G | 1859009 |  |  | 566 | EX | ABANDON SL--IDLE 24 MONTHS | 2600B | 4TH | 1607 N 4TH ST | 089 | FLA | 2019-09-12 | U124015 | U901436 | 2006-07-11 | 2019-09-06 |  |  | ORA SLONE | 2019-09-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 0.26667 | 1 | 17.78 | 14.75 | 0 | 3.03 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11900878600 |  | 100255615 |  | T-1726-15 | 1859009 |  |  | 566 | EX | ABANDON/ IDLE 48MO/ RI 04-2008 | 2600B | 1ST | 712 N 1ST ST | 089 | FLA | 2019-09-12 | U124015 | U123853 | 2011-04-12 | 2020-12-31 |  |  | ORA SLONE | 2019-09-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1
KY | KY - EAST | 2631 | 11911883100 |  | 100255698 |  | 7348264G | 1859009 |  |  | 566 | EX | ABANDON / RI 06-2010 | 2600B | 4TH | 432 N 4TH ST | 089 | FLA | 2019-09-12 | U124015 | U906631 | 2011-06-16 | 2019-09-06 |  |  | ORA SLONE | 2019-09-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 3.2167 | 2 | 210.19 | 179.68 | 0 | 30.51 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 11926566600 |  | 100255832 |  | ? | 1859009 |  |  | 566 | EX | ABANDON / RI 09-11-2009 | 2600B | TURLEY | 1106 TURLEY AV | 089 | FLA | 2019-09-12 | U124015 | U124449 | 2011-09-27 | 2020-12-31 |  |  | ORA SLONE | 2019-09-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1
KY | KY - EAST | 2631 | 18026775800 |  | 501240774 |  | 7352252M | 1853277 | U131042 |  | 555 | EX | INSTALL 215'-2" PMIP | 2600B | JUDY | 2223 JUDY LN LOT 6 | 019 | ASH | 2019-10-02 | U124014 | U131042 | 2018-06-06 | 2019-09-03 | 2019-09-15 | 2019-09-10 | MARCUS BLANKENSHIP | 2019-09-12 | 2019-08-30 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP7758 |  |  | 100 | 055532180267758 | 64.2667 | 2585 | 27502.38 | 3681.41 | 1174.87 | 1303.22 | 18604.25 | 0 | 53.87 | 2684.76 | 235
KY | KY - WEST | 2623 | 18026794900 |  |  |  | 6712228C | 1855525 | U127466 |  | 561 | EX | INSTALL 10' - 3" PMLP | 2621P | FOUNTAIN | FOUNTAIN AV | 209 | GEO | 2020-04-28 | U123258 | U127466 | 2018-09-13 | 2019-09-09 |  | 2019-06-27 | CDESPAI | 2019-09-12 | 2019-05-30 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00561 | 3200561 |  |  | WP7949 | AMRCB |  | 100 | 056132180267949 | 6.3833 | 104 | 30034.59 | 366.67 | 175.31 | 707.44 | 25584.57 | 0 | 19.5 | 3181.1 | 26
KY | KY - WEST | 2623 | 18026795000 |  |  |  | 6712228C | 1855525 | U127466 |  | 562 | EX | RETIRE 10' - 3" BSLP | 2621P | FOUNTAIN | FOUNTAIN AV | 209 | GEO | 2020-04-28 | U123258 | U127466 | 2018-09-13 | 2020-07-01 | 2020-07-01 | 2019-06-27 | CEDSPAIN | 2019-09-12 | 2019-05-31 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00562 | 3200562 |  |  | WP7950 | AMRCB |  | 100 | 056232180267950 | 23.5333 | 0 | 5583.52 | 1417.72 | 0 | 1741.96 | 2423.84 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19026877300 |  |  |  | 6688228K | 1963877 | U122858 |  | 561 | EX | INSTALL 20'-3" PMLP | 2600E | BRIGHTON PARK | 105 BRIGHTON PARK BV | 073 | FRA | 2021-11-01 | U128132 | U122858 | 2019-05-15 | 2019-08-29 |  | 2019-08-15 | CDESPAI | 2019-09-12 | 2019-07-11 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00561 | 3200561 |  |  | WP8773 |  |  | 100 | 056132190268773 | 2.1167 | 300 | 4627.96 | 131.88 | 0 | 65.53 | 3876.69 | 0 | 0 | 553.86 | 60
KY | KY - WEST | 2623 | 19026877400 |  |  |  | 6688228K | 1963877 | U122858 |  | 562 | EX | RETIRE 20'-3" PLP | 2600E | BRIGHTON PARK | 105 BRIGHTON PARK BV | 073 | FRA | 2021-11-01 | U128132 | U122858 | 2019-05-15 | 2019-06-28 | 2019-06-30 | 2019-08-15 | CDESPAIN | 2019-09-12 | 2019-07-12 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00562 | 3200562 |  |  | WP8774 |  |  | 100 | 056232190268774 | 6.3333 | 0 | 8813.2 | 410.13 | 0 | 680.72 | 7722.35 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19026891800 |  |  |  | 6680224G | 1966073 | U128885 |  | 557 | EX | INSTALL 1' - 3" PMMP | 2621P | SPRUCE DR | SPRUCE DR | 073 | FRA | 2020-04-07 | U128132 | U128885 | 2019-08-22 | 2019-09-09 | 2020-04-30 | 2019-08-20 | CDESPAI | 2019-09-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP8918 |  |  | 100 | 055732190268918 | 0.33333 | 30 | 24141.14 | 1878.21 | 125.37 | 2028.93 | 17755.44 | 0 | 45.88 | 2307.31 | 30
KY | KY - WEST | 2623 | 19026891900 |  |  |  | 6680224G | 1966073 | U128885 |  | 558 | EX | RETIRE 1' - 3" PMMP | 2621P | SPRUCE DR | SPRUCE DR | 073 | FRA | 2020-04-07 | U128132 | U128885 | 2019-08-22 | 2020-04-30 | 2020-04-30 | 2019-08-20 | CDESPAI | 2019-09-12 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00558 | 3200558 |  |  | WP8919 |  |  | 100 | 055832190268919 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19667382300 |  | 100272709 |  | 6684224B | 0573125 |  |  | 566 | VO | DEMO / ABANDON / RA 01-11-2019 | 2621P | COUGAR | 1 COUGAR LN | 073 | FRA | 2020-05-08 |  | U130722 | 2019-01-09 | 2019-02-22 | 2019-03-15 |  |  | 2019-09-12 | 2019-02-01 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 31 | 10 | 1814.78 | 1697.17 | 0 | 117.61 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19669124200 |  | 100242038 |  | 7344168G |  |  |  | 565 | EX | REPLACE SERVICE LINE - D095688 | 2621P | RIVERVIEW | 104 S RIVERVIEW LN | 071 | LNC | 2019-09-12 | BBMULLI | U128293 | 2019-01-15 | 2019-07-12 | 2021-01-31 |  | BBMULLI | 2019-09-12 | 2019-09-11 |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 30.8 | 5 | 2403.93 | 1691.81 | 91.52 | 620.6 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673607100 |  | 100310461 |  | 6712208L | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2809 CLAYS MILL RD | 067 | LEX | 2019-09-12 | U461443 | U131066 | 2019-01-30 | 2019-11-27 |  |  | WGRAVES | 2019-09-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.3667 | 1 | 2485.3 | 276.87 | 169.88 | 106.85 | 1931.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678776500 |  | 100299111 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | FORBES | 1416 N FORBES RD | 067 | LEX | 2019-09-12 | U126286 | U131066 | 2019-02-01 | 2019-11-27 |  |  | TYLER ALLISON | 2019-09-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1746.59 | 0 | 0 | 0 | 1746.59 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678776600 |  | 100299110 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | FORBES | 1418 N FORBES RD | 067 | LEX | 2019-09-12 | U126286 | U131066 | 2019-02-01 | 2019-11-27 |  |  | TYLER ALLISON | 2019-09-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1323.23 | 0 | 0 | 0 | 1323.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678776700 |  | 100299108 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | FORBES | 1420 N FORBES RD | 067 | LEX | 2019-09-12 | U126286 | U131066 | 2019-02-01 | 2019-11-27 |  |  | TYLER ALLISON | 2019-09-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1418.91 | 0 | 0 | 0 | 1418.91 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680084300 |  | 100320274 |  | 6716208G | 1748686 |  |  | 565 | EX | REPLACE SL W/17026736100 | 2600B | MCDONALD | 1822 MCDONALD AV | 067 | LEX | 2019-09-12 | U126284 | U131066 | 2019-02-07 | 2019-12-31 |  |  | JOSH PASLEY | 2019-09-12 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.5 | 1 | 2928.07 | 258.89 | 0 | 52.65 | 2616.53 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687821100 |  | 100280087 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | KINGSWAY | 253 KINGSWAY DR | 073 | FRA | 2019-09-13 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2123.54 | 0 | 0 | 0 | 2123.54 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687825200 |  | 100280079 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | QUEENSWAY | 252 QUEENSWAY DR | 073 | FRA | 2019-09-12 | U126602 | U131066 | 2019-03-13 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 3 | 1 | 2303.46 | 168.5 | 0 | 11.42 | 2123.54 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687833100 |  | 100280085 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 317 WESTLAND DR | 073 | FRA | 2019-09-12 | U126602 | U131066 | 2019-03-13 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6 | 1 | 1952.84 | 337 | 0 | 22.85 | 1592.99 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687849300 |  | 100280086 |  | 6688228N | 1853312 |  |  | 566 | EX | ABANDON SL W/18026777000 | 2600B | KINGSWAY | 255 KINGSWAY DR | 073 | FRA | 2019-11-01 | U125208 | U131066 | 2019-03-13 | 2019-12-31 |  |  | LARRY BROWN | 2019-09-12 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1055 | 0 | 0 | 0 | 1055 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689090600 |  | 100255799 |  | 7348264L | 1859009 |  |  | 566 | EX | ABND SL/18026843700/ | 2600B | BLUM | 100 BLUM ST | 089 | FLA | 2019-09-12 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-09-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 | 0.91667 | 1 | 62.17 | 51.58 | 0 | 10.59 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689090800 |  | 100255794 |  | 7348264H | 1859009 |  |  | 566 | EX | ABND SL/18026843700/ | 2600B | CENTRAL | 1124 CENTRAL AV | 089 | FLA | 2019-09-12 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-09-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 |  | 1
KY | KY - EAST | 2631 | 19689090900 |  | 100255793 |  | 7348264H | 1859009 |  |  | 566 | EX | ABND SL/18026843700/ | 2600B | CENTRAL | 1128 CENTRAL AV | 089 | FLA | 2019-09-12 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-09-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 | 0.05 | 1 | 6.15 | 5.11 | 0 | 1.04 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689091800 |  | 100255715 |  | 7348264G | 1859009 |  |  | 566 | EX | ABANDONED | 2600B | MEADE | 1610 MEADE ST | 089 | FLA | 2019-09-12 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-09-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 | 0.05 | 1 | 3.41 | 2.83 | 0 | 0.58 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689092400 |  | 100255815 |  | 7348264L | 1859009 |  |  | 566 | EX | ABND SL/18026843700/ | 2600B | TURLEY | 333 TURLEY AV | 089 | FLA | 2019-09-12 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-09-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 | 0.016667 | 1 | 0.69 | 0.57 | 0 | 0.12 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689092500 |  | 100255813 |  | 7348264L | 1859009 |  |  | 566 | EX | ABND SL/18026843700/ | 2600B | TURLEY | 811 TURLEY AV | 089 | FLA | 2019-09-12 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-09-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 | 1.7167 | 1 | 116.81 | 96.89 | 0 | 19.92 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689092800 |  | 100255819 |  | 7348264L | 1859009 |  |  | 566 | EX | ABND SL/18026843700/ | 2600B | TURLEY | 833 TURLEY AV | 089 | FLA | 2019-09-12 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-09-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 | 0.66667 | 1 | 45.08 | 37.4 | 0 | 7.68 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689092900 |  | 100255822 |  | 7348264L | 1859009 |  |  | 566 | EX | ABND SL/18026843700/ | 2600B | TURLEY | 853 TURLEY AV | 089 | FLA | 2019-09-12 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-09-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 | 0.43333 | 1 | 29.38 | 24.37 | 0 | 5.01 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689094200 |  | 100255801 |  | 7348264L | 1859009 |  |  | 566 | EX | ABND SL/18026843700/ | 2600B | TURLEY | 1018 TURLEY AV | 089 | FLA | 2019-09-12 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-09-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 | 0.33333 | 1 | 22.53 | 18.69 | 0 | 3.84 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689094500 |  | 100255833 |  | 7348264L | 1859009 |  |  | 566 | EX | ABND SL/18026843700/ | 2600B | TURLEY | 1108 TURLEY AV | 089 | FLA | 2019-09-13 | U124015 | U131066 | 2019-03-18 | 2019-11-27 |  |  | ORA SLONE | 2019-09-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 | 0.85 | 2 | 58.07 | 48.19 | 0 | 9.88 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19689196800 |  | 100255795 |  | 7348264H | 1859009 |  |  | 566 | EX | ABANDON | 2600B | CENTRAL | 1115 CENTRAL AV | 089 | FLA | 2019-09-12 | U124015 | U131066 | 2019-03-18 | 2019-12-31 |  |  | ORA SLONE | 2019-09-12 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0043 | AMRSL |  | 100 | 056632B26310043 |  | 1
KY | KY - CENTRAL | 2629 | 19721793900 |  | 100342051 |  | 7240216N | 1855043 |  |  | 566 | EX | II - METER ABANDON OR CO SOII | 2621P | JOHNSON | 38 JOHNSON AV | 173 | MT | 2019-09-12 | DENNING | U126129 | 2019-07-03 | 2019-07-30 | 2019-08-30 |  | DENNING | 2019-09-12 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19734563000 |  | 100416844 |  | 6680224G |  |  |  | 565 | EX | REPLACE SERV LINE | 2621P | SPRUCE | 313 SPRUCE DR | 073 | FRA | 2019-09-12 | CDESPAI | U129939 | 2019-08-20 | 2019-08-20 |  |  | CDESPAI | 2019-09-12 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 2.7667 | 1 | 683.71 | 160.99 | 201.72 | 321 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18026795800 |  |  |  | 6720212B | 1855586 | U122858 |  | 562 | EX | RETIRE 845'-3" BS & P LP | 2600B | EDGELAWN | EDGELAWN AV | 067 | LEX | 2019-11-18 | U123258 | U122858 | 2018-09-15 | 2019-09-30 | 2019-09-30 | 2019-09-13 | KKOUNS | 2019-09-13 | 2019-09-13 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP7958 | AMRCB |  | 100 | 056232180267958 | 10.25 | 0 | 990.87 | 554.09 | 0 | 205.98 | 230.8 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026889100 |  |  |  | 6712212L | 1965634 | U122858 |  | 562 | EX | RETIRE 28'-8" PMLP | 2621P | DUNTREATH | DUNTREATH | 067 | LEX | 2021-03-17 | U460266 | U122858 | 2019-08-01 | 2020-09-29 | 2020-09-30 | 2019-09-12 | ASNICHO | 2019-09-13 | 2019-09-13 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP8891 | AMRCB |  | 100 | 056232190268891 | 0.9 | 0 | 1419.08 | 50.31 | 1365.37 | 3.4 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026896300 |  |  |  | 6720212B | 1855586 | U122858 |  | 561 | EX | INSTALL 5'-6" PMLP | 2600B | BLUE GRASS | BLUE GRASS AV | 067 | LEX | 2019-11-18 | U123258 | U122858 | 2019-09-16 | 2019-10-31 | 2019-10-31 | 2019-09-13 | KKOUNS | 2019-09-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP8963 | AMRCB |  | 100 | 056132190268963 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
KY | KY - WEST | 2621 | 19678776300 |  | 100299113 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | FORBES | 1410 N FORBES RD | 067 | LEX | 2019-09-13 | U126602 | U131066 | 2019-02-01 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.1833 | 1 | 2387.22 | 290.97 | 0 | 19.72 | 2076.53 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678776400 |  | 100299112 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | FORBES | 1414 N FORBES RD | 067 | LEX | 2019-09-13 | U126602 | U131066 | 2019-02-01 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.8167 | 1 | 1227.54 | 214.56 | 0 | 14.55 | 998.43 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19694358700 |  | 100456766 |  | 7236212L |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | IROQUOIS | 1092 IROQUOIS DR | 173 | MT | 2019-09-13 | DENNING | U125208 | 2019-04-03 | 2019-09-27 | 2021-03-31 |  | DENNING | 2019-09-13 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 23.4 | 4 | 1740.37 | 1064.85 | 41.07 | 591.25 | 43.2 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19705069200 |  | 100465371 |  | 6712208L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094854 | 2621P | DARDANELLES | 633 DARDANELLES DR | 067 | LEX | 2019-09-19 | U128336 | U125208 | 2019-05-10 | 2019-11-07 | 2021-05-31 |  | JWCOX | 2019-09-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.88333 | 1 | 3163.46 | 49.26 | 294.11 | 3.34 | 2816.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19715555200 |  | 100329358 |  | 6720208D |  |  |  | 566 | EX | ABANDON W/2313-POSSIBLE THEFT | 2621P | SAINT ANN | 236 SAINT ANN DR | 067 | LEX | 2019-09-25 | U125208 | U125208 | 2019-06-19 | 2019-07-10 |  |  | ASNICHO | 2019-09-13 |  |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 3.6167 | 1 | 297.2 | 201.79 | 81.73 | 13.68 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19741527900 |  | 100466127 |  | 6712212K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D107150 | 2621P | PARTERRE | 2429 PARTERRE PL | 067 | LEX | 2019-09-26 | U125208 | U129939 | 2019-09-13 | 2019-11-01 | 2021-05-31 |  | JWCOX | 2019-09-13 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.1667 | 1 | 3371.85 | 122.61 | 294.1 | 8.32 | 2946.82 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678776100 |  | 100299114 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | FORBES | 1406 N FORBES RD | 067 | LEX | 2019-09-14 | U126286 | U131066 | 2019-02-01 | 2019-09-13 |  |  | JOSH PASLEY | 2019-09-14 | 2019-09-14 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.5167 | 4 | 2839.27 | 316.97 | 0 | 64.45 | 2457.85 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678789100 |  | 100299200 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | MEADOWTHORPE | 1542 MEADOWTHORPE AV | 067 | LEX | 2019-09-14 | U126286 | U131066 | 2019-02-01 | 2019-09-13 |  |  | TYLER ALLISON | 2019-09-14 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8.1333 | 2 | 2880.35 | 454.15 | 0 | 69.72 | 2356.48 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687824200 |  | 100280025 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | MAGNOLIA | 312 MAGNOLIA ST | 073 | FRA | 2019-09-14 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-14 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2370.47 | 0 | 0 | 0 | 2370.47 | 0 | 0 | 0
KY | KY - EAST | 2631 | 07698109200 |  | 100255800 |  | 7348264L | 1859009 |  |  | 566 | EX | RETIRE WITH 18-0268437-00 | 2600B | TURLEY | 1020 TURLEY AV | 089 | FLA | 2019-09-16 | U461383 | DMCCULL | 2007-08-10 | 2049-12-31 |  |  | OSLOAN | 2019-09-16 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1
KY | KY - EAST | 2631 | 11895721000 |  | 100255809 |  | 7348264L | 1859009 |  |  | 566 | EX | RETIRE S/L WITH 18-0268437-00 | 2600B | TURLEY | 1011 TURLEY AV | 089 | FLA | 2019-09-16 | U461383 | U124960 | 2011-03-15 | 2049-12-31 |  |  | OSLOAN | 2019-09-16 |  |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1
KY | KY - EAST | 2631 | 12949814400 |  | 100255802 |  | 7348264L | 1859009 |  |  | 566 | EX | ABANDON / RI 01-11-2010- ELEC | 2600B | TURLEY | 1016 TURLEY AV | 089 | FLA | 2019-09-16 | U461383 | U125208 | 2012-01-16 | 2049-12-31 |  |  | RMULLINS | 2019-09-16 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 |  | 1
KY | KY - WEST | 2621 | 19673604900 |  | 100312947 |  | 6716208E | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2236 CLAYS MILL RD | 067 | LEX | 2019-09-16 | U461439 | U131066 | 2019-01-30 | 2019-11-27 |  |  | A PARRIS | 2019-09-16 | 2019-09-16 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 2.3667 | 1 | 1187.56 | 137.43 | 158.14 | 48.08 | 843.91 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673606500 |  | 100310458 |  | 6716208I | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2791 CLAYS MILL RD | 067 | LEX | 2019-09-16 | U461443 | U131066 | 2019-01-30 | 2019-11-27 |  |  | WGRAVES | 2019-09-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.3167 | 1 | 2393.06 | 170.97 | 241.5 | 65.99 | 1914.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678784100 |  | 100298896 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LEESTOWN | 1389 LEESTOWN RD | 067 | LEX | 2019-09-16 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-09-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.3167 | 1 | 2866.41 | 70.11 | 0 | 26.6 | 2769.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680066700 |  | 100320272 |  | 6716208G | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | MCDONALD | 1826 MCDONALD AV | 067 | LEX | 2019-09-16 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-09-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7.9333 | 1 | 2758.49 | 456.77 | 0 | 92.89 | 2208.83 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687834100 |  | 100280095 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 327 WESTLAND DR | 073 | FRA | 2019-09-16 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1305.38 | 0 | 0 | 0 | 1305.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19711113100 |  | 100297731 |  | 6716212H | 1855598 |  |  | 565 | EX | REPLACE SL W/18026796000 | 2600B | MARKET | 258 MARKET ST | 067 | LEX | 2019-09-17 | HROGERS | U131066 | 2019-06-03 | 2019-12-31 |  |  | MARK ROGERS | 2019-09-16 | 2019-09-16 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.5667 | 1 | 2135.63 | 282.36 | 131.68 | 62.59 | 1659 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19733206700 |  | 100280100 |  | 6688228N | 1853312 |  |  | 565 | EX | REPLACE SL W/18026776900 | 2600B | SYCAMORE | 254 SYCAMORE DR | 073 | FRA | 2019-09-16 | U461375 | U131066 | 2019-08-15 | 2019-12-31 |  |  | LARRY BROWN | 2019-09-16 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1290.02 | 0 | 0 | 0 | 1290.02 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19734465500 |  | 100346343 |  | 6696212L |  |  |  | 566 | EX | DEMO 8/27 - ABN - RI 08-22-19 | 2621P | MONTGOMERY | 231 MONTGOMERY AV | 239 | VER | 2019-09-20 | U125208 | U125208 | 2019-08-20 | 2019-09-16 |  |  | DCOLLIN | 2019-09-16 | 2019-09-16 |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 15.35 | 3 | 1417.74 | 827.16 | 0.89 | 589.69 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19740093600 |  | 500539563 |  | V808/30 | 9612815 |  |  | 565 | EX | REPLACE SL | 2621P | GLENNS CREEK | 1130 GLENNS CREEK RD | 073 | FRA | 2019-09-16 | CDESPAI | U131167 | 2019-09-09 | 2019-09-09 |  |  | CDESPAI | 2019-09-16 | 2019-09-09 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 31.15 | 5 | 15703.11 | 1818.26 | 166.57 | 2253.08 | 11465.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19740197600 |  | 500021605 |  | 6744208P |  |  |  | 566 | EX | DEMO / ABANDON / RA 09-11-19 | 2621P | TAYLOR | 28 TAYLOR AV | 049 | WIN | 2019-09-17 | U125208 | U132002 | 2019-09-09 | 2019-10-10 | 2019-10-10 |  | DBANKS | 2019-09-16 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 18 | 4 | 855.2 | 799.55 | 1.38 | 54.27 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19740445800 |  | 100254063 |  | 7348264N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D188581 | 2621P | FARM HILL | 2511 FARM HILL DR | 089 | FLA | 2019-09-16 | BROBERT | U125208 | 2019-09-10 | 2019-09-12 | 2019-09-30 |  | BROBERT | 2019-09-16 | 2019-09-16 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 19.0667 | 2 | 1551.43 | 1013.62 | 304.8 | 233.01 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19741672400 |  | 100268608 |  | 7356256G |  |  |  | 565 | EX | REPLACE SERV LINE | 2621P | 35TH | 225 35TH ST | 019 | ASH | 2019-09-16 | MCOLLET | U129939 | 2019-09-13 | 2019-09-13 | 2019-09-13 |  | MCOLLET | 2019-09-16 | 2019-09-13 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 14.9667 | 5 | 1646.9 | 914.43 | 152.08 | 580.39 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19741894400 |  | 100334444 |  | 6720208H |  |  |  | 565 | EX | REPLACE SERVICE LINE-D094872 | 2621P | PEACHTREE | 328 PEACHTREE RD | 067 | LEX | 2019-09-17 | U125208 | U129005 | 2019-09-16 | 2019-11-30 | 2021-05-31 |  | LSTANFI | 2019-09-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.7167 | 1 | 2307.64 | 298.48 | 332.36 | 20.21 | 1656.59 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19741896400 |  | 100263620 |  | 7352256C |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | ROBERTS | 3022 ROBERTS DR | 019 | ASH | 2019-09-17 | U125208 | U129005 | 2019-09-16 | 2019-09-16 |  |  | MCOLLET | 2019-09-16 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 6.8667 | 2 | 892.8 | 422.04 | 0 | 470.76 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19742015000 |  | 100319733 |  | 6716208K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D221981 | 2621P | DELLWOOD | 2025 DELLWOOD DR | 067 | LEX | 2019-09-17 | U125208 | U129005 | 2019-09-16 | 2019-09-16 | 2019-09-16 |  | LSTANFI | 2019-09-16 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26210022 | 3.6167 | 1 | 2324.64 | 228.77 | 292.16 | 15.52 | 1788.19 | 0 | 0 | 0
KY | KY - WEST | 2623 | 20861163500 |  | 100280096 |  | 6688228N | 1853312 |  |  | 566 | EX | ABANDON SL W/18026776900 | 2600B | SYCAMORE | 257 SYCAMORE DR | 073 | FRA | 2020-11-18 | U461375 | U131066 | 2020-11-18 | 2020-12-31 |  |  | LARRY BROWN | 2019-09-16 |  |  | B | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 |  | 1 | 1055 | 0 | 0 | 0 | 1055 | 0 | 0 | 0
KY | KY - WEST | 2621 | 15026619300 |  |  |  | 6720208B | 1534246 | U461383 |  | 587 | EX | INSTALL NEW 2" BYPASS REGS | 2600M | RICHMOND | 1900 RICHMOND RD | 067 | LEX | 2019-12-06 | U462463 | U461383 | 2015-11-23 | 2020-06-01 | 2020-06-01 | 2019-09-17 | MIKE MCKUNE | 2019-09-17 | 2019-09-17 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00587 | 3200587 |  |  | WP6193 |  |  | 100 | 058732150266193 | 10.3333 | 2 | 642.3 | 542.85 | 0 | 36.81 | 0 | 0 | 1.26 | 61.38
KY | KY - WEST | 2621 | 15026619400 |  |  |  | 16720208B | 1534246 | U461383 |  | 588 | EX | ABANDON BYPASS REGULATOR | 2600M | RICHMOND | 1900 RICHMOND RD | 067 | LEX | 2019-12-06 | U462463 | U461383 | 2015-11-23 | 2020-06-01 | 2020-06-01 | 2019-09-17 | MIKE MCKUNE | 2019-09-17 |  |  | F | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00588 | 3200588 |  |  | WP6194 |  |  | 100 | 058832150266194 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18026843700 |  |  |  | 7348264H | 1859009 | U461383 |  | 557 | EX | INSTALL 8200' OF 2"PMMP MAIN | 2600B | MEADE | MEADE ST | 089 | FLA | 2019-11-05 | U123258 | U461383 | 2018-11-02 | 2019-05-28 | 2019-12-31 | 2019-07-26 | ORA SLONE | 2019-09-17 | 2019-04-08 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP8437 | AMRCB |  | 100 | 055732180268437 | 1019.0167 | 1185665 | 667631.39 | 58396.15 | 24768.58 | 15798.51 | 482377.3 | 0 | 3300.39 | 82990.46 | 8177
KY | KY - EAST | 2631 | 18026843800 |  |  |  | 7348264H | 1859009 | U461383 |  | 558 | EX | RETIRE 9500' OF 4"/6"BSLP | 2600B | MEADE | MEADE ST | 089 | FLA | 2019-11-05 | U123258 | U461383 | 2018-11-02 | 2019-12-31 | 2019-12-31 | 2019-09-17 | 0RA SLONE | 2019-09-17 | 2019-09-11 |  | B | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00558 | 3200558 |  |  | WP8438 | AMRCB |  | 100 | 055832180268438 | 5.8167 | 0 | 5295.39 | 330.09 | 0 | 32.13 | 4933.17 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026870200 |  | 501263527 |  | 6728208F | 1962867 | U461383 |  | 555 | EX | INSTALL 100' OF 2"PMMP MAIN | 2600B | MATHERN | 3349 MATHERN TL | 067 | LEX | 2019-09-27 | U460266 | U461383 | 2019-04-11 | 2019-09-13 | 2019-10-01 | 2019-09-16 | WILL FULKS | 2019-09-17 | 2019-09-12 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP8702 |  |  | 100 | 055532190268702 | 52.45 | 469 | 16886.43 | 2953.39 | 370.76 | 691.37 | 11221.32 | 0 | 33.03 | 1616.56 | 67
KY | KY - WEST | 2621 | 19673606600 |  | 100310459 |  | 6712208L | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2799 CLAYS MILL RD | 067 | LEX | 2019-09-17 | U461443 | U131066 | 2019-01-30 | 2019-11-27 |  |  | WGRAVES | 2019-09-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 5.55 | 1 | 2461.36 | 286.18 | 257.25 | 110.43 | 1807.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680084600 |  | 100320271 |  | 6716208G | 1748686 |  |  | 565 | EX | REPLACE SL W/17026736100 | 2600B | MCDONALD | 1828 MCDONALD AV | 067 | LEX | 2019-09-17 | U126284 | U131066 | 2019-02-07 | 2019-12-31 |  |  | JOSH PASLEY | 2019-09-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11 | 1 | 4012.09 | 632.8 | 0 | 128.68 | 3250.61 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687820700 |  | 100280106 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | DESHA | 252 DESHA DR | 073 | FRA | 2019-09-17 | U126602 | U131066 | 2019-03-13 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 9.25 | 1 | 1800.7 | 519.61 | 0 | 35.23 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687820800 |  | 100280105 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | DESHA | 253 DESHA DR | 073 | FRA | 2019-09-17 | U126602 | U131066 | 2019-03-13 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1415.86 | 0 | 0 | 0 | 1415.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687822800 |  | 100280117 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | LYONS | 314 LYONS DR | 073 | FRA | 2019-09-17 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2419.94 | 0 | 0 | 0 | 2419.94 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19703682600 |  | 100450992 |  | 6716204H | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER / | 2621D | TRAILS END | 3505 TRAILS END | 067 | LEX | 2019-09-20 | U125208 | AOC SYST | 2019-05-06 | 2019-05-31 | 2019-07-02 |  | KKINDER | 2019-09-17 | 2019-09-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 42.3667 | 5 | 2384.29 | 2053.43 | 134.06 | 139.2 | 57.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19705074400 |  | 100467145 |  | 6712208L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094861 | 2621P | GALATA | 608 GALATA DR | 067 | LEX | 2019-09-25 | U125208 | U125208 | 2019-05-10 | 2019-11-08 | 2021-05-31 |  | JWCOX | 2019-09-17 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.75 | 1 | 2984.37 | 545.68 | 178.94 | 37 | 2222.75 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19705446900 |  | 100278216 |  | 6688228B |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | CHOCTAW | 602 CHOCTAW TL | 073 | FRA | 2019-09-17 | CDESPAI | U125208 | 2019-05-13 | 2019-11-08 | 2021-05-31 |  | CDESPAI | 2019-09-17 | 2019-09-13 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 5.2 | 2 | 3419.3 | 304.55 | 260.46 | 607.1 | 2247.19 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19707742100 |  | 100262075 |  | 7352256D | 1961470 |  |  | 565 | EX | RPLC SL/19026862600/ | 2600B | FLORENCE | 1331 FLORENCE ST | 019 | ASH | 2019-09-17 | U124015 | U131066 | 2019-05-21 | 2019-11-27 |  |  | ORA SLONE | 2019-09-17 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1040.45 | 0 | 0 | 0 | 1040.45 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19711109000 |  | 100297733 |  | V102149 | 1855598 |  |  | 565 | EX | RPLC SL/18026796000/ | 2600B | MARKET | 253 MARKET ST | 067 | LEX | 2019-09-17 | U461516 | U131066 | 2019-06-03 | 2019-11-27 |  |  | NEAL JOHNSON | 2019-09-17 |  | 2019-09-17 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.9167 | 4 | 6823.17 | 575.82 | 0 | 197.2 | 6050.15 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19733205700 |  | 100280099 |  | 6688228N | 1853312 |  |  | 565 | EX | REPLACE SL W/18026776900 | 2600B | SYCAMORE | 252 SYCAMORE DR | 073 | FRA | 2019-09-17 | U126602 | U131066 | 2019-08-15 | 2019-12-31 |  |  | DEREK PAYTON | 2019-09-17 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2123.54 | 0 | 0 | 0 | 2123.54 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19736443500 |  | 100427092 |  | 6688228K |  |  |  | 565 | EX | SERVICE LINE - REPLACE | 2621P | RYSWICK | 26 RYSWICK LN | 073 | FRA | 2019-09-17 | CDESPAI | U125208 | 2019-08-26 | 2019-08-27 |  |  | CDESPAI | 2019-09-17 | 2019-09-06 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 1.4333 | 2 | 2446.79 | 82.91 | 190.22 | 165.16 | 2008.5 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19738670500 |  | 100294765 |  | 6716212H |  |  |  | 566 | EX | DEMO / ABANDON / RA 09-06-19 | 2621P | ADDIE | 458 ADDIE ST | 067 | LEX | 2019-09-20 | U125208 | U132002 | 2019-09-03 | 2019-10-10 | 2019-10-31 |  | WHIMES | 2019-09-17 | 2019-09-05 |  | A | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 6.4667 | 3 | 526.57 | 352.69 | 149.93 | 23.95 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19740518300 |  | 100349589 |  | 6748208 |  |  |  | 566 | EX | LOCATE/ABANDON - NON USAGE2016 | 2621P | HICKMAN | 307 E HICKMAN ST | 049 | WIN | 2019-09-17 | DBANKS | U125208 | 2019-09-10 | 2049-12-31 |  |  | DBANKS | 2019-09-17 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 20.0833 | 4 | 977.42 | 834.55 | 86.29 | 56.58 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 11878461900 |  | 100355185 |  | 7260280M |  |  |  | 566 | EX | ABN/ IDLE 36MO 1-2012 RI 2009 | 2621P | 3RD | 708< E 3RD ST | 161 | MAY | 2019-09-18 | SDADAMS | U906307 | 2011-01-11 | 2019-09-30 |  |  | SDADAMS | 2019-09-18 |  |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 7.9667 | 4 | 456.6 | 417.68 | 10.62 | 28.3 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18637828100 |  | 100345294 |  | 6696212H |  |  |  | 565 | EX | REPL SERV - UNMETERED GAS | 2621P | BOSTON | 216 BOSTON DR | 239 | VER | 2019-09-20 | U125208 | U125208 | 2018-08-24 | 2018-08-27 |  |  | CDESPAI | 2019-09-18 | 2019-08-30 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 9.95 | 2 | 5703.79 | 582.32 | 302.6 | 1140.91 | 3677.96 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19026857300 |  |  |  | 7348264H | 1859009 | U461383 |  | 584 | EX | RETIRE REG STATION W/AMRP | 2600E | MEADE | 1327 MEADE ST | 089 | FLA | 2019-09-24 | U462463 | U461383 | 2019-01-20 | 2019-12-31 | 2019-12-31 | 2019-09-18 | JOSHUA MULLINS | 2019-09-18 | 2019-09-09 |  | F | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00584 | 3200584 |  |  | WP8573 | AMRCB |  | 100 | 058432190268573 | 23.7833 | 0 | 5930.35 | 1673.75 | 332.82 | 487.03 | 3434.93 | 0 | 1.82 | 0
KY | KY - CENTRAL | 2629 | 19026877200 |  | 500717790 |  | 6740208D | 1961723 | U128885 |  | 555 | EX | INSTALL 4,500' - 6" PMMP | 2600B | ROCKWELL | 4481 ROCKWELL RD | 049 | WIN | 2019-10-14 | U123258 | U128885 | 2019-05-15 | 2019-08-12 | 2019-10-11 | 2019-09-03 | SHAWN DENNIS | 2019-09-18 | 2019-08-01 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP8772 |  |  | 100 | 055532190268772 | 213.9 | 119988 | 291652.33 | 13119.43 | 30540.72 | 4275.24 | 213949.63 | 0 | 469.03 | 29298.28 | 4444
KY | KY - CENTRAL | 2629 | 19026882800 |  |  |  | 6740208D | 1961723 | U128885 |  | 560 | EX | ABANDON 4500' - 2" PMMP | 2600B | ROCKWELL | ROCKWELL RD | 049 | WIN | 2019-10-14 | U123258 | U128885 | 2019-07-01 | 2019-10-11 | 2019-10-11 | 2019-09-03 | SHAWN DENNIS | 2019-09-18 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00560 | 3200560 |  |  | WP8828 |  |  | 100 | 056032190268828 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673606400 |  | 100310457 |  | 6716208I | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2783 CLAYS MILL RD | 067 | LEX | 2019-09-18 | U461443 | U131066 | 2019-01-30 | 2019-11-27 |  |  | WGRAVES | 2019-09-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.55 | 1 | 2020.97 | 286.17 | 257.26 | 110.44 | 1367.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678785300 |  | 100299123 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LEESTOWN | 1441 LEESTOWN RD | 067 | LEX | 2019-09-18 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-09-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2795.08 | 0 | 0 | 0 | 2795.08 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678821900 |  | 100410333 |  | 6716212B | 1855322 |  |  | 565 | EX | REPLACE SL W/18026792400 | 2600B | LEESTOWN | 1353 LEESTOWN RD | 067 | LEX | 2019-09-18 | U124003 | U131066 | 2019-02-01 | 2019-12-31 |  |  | BPULLIAM/RLA | 2019-09-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2399.38 | 0 | 0 | 0 | 2399.38 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680081600 |  | 100320311 |  | 6716208G | 1748686 |  |  | 565 | EX | REPLACE SL W/17026736100 | 2600B | HILTONIA | 124 HILTONIA PR | 067 | LEX | 2019-09-18 | U461516 | U131066 | 2019-02-07 | 2019-12-31 |  |  | NEAL JOHNSON | 2019-09-18 |  | 2019-09-18 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 15.0167 | 2 | 3362.98 | 842.12 | 0 | 139.43 | 2381.43 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687820900 |  | 100280104 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | DESHA | 255 DESHA DR | 073 | FRA | 2019-09-18 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687834800 |  | 100280056 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 336 WESTLAND DR | 073 | FRA | 2019-09-18 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1592.99 | 0 | 0 | 0 | 1592.99 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687835000 |  | 100280055 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 338 WESTLAND DR | 073 | FRA | 2019-09-18 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687835200 |  | 100280053 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 342 WESTLAND DR | 073 | FRA | 2019-09-18 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1282.34 | 0 | 0 | 0 | 1282.34 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19707742200 |  | 100262074 |  | 7352256D | 1961470 |  |  | 565 | EX | RPLC SL/19026862600/ | 2600B | FLORENCE | 1335 FLORENCE ST | 019 | ASH | 2019-09-18 | U124015 | U131066 | 2019-05-21 | 2019-11-27 |  |  | ORA SLONE | 2019-09-18 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1620.73 | 0 | 0 | 0 | 1620.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19711108800 |  | 100297729 |  | 6716212H | 1855598 |  |  | 565 | EX | RPLC SL/18026796000/ | 2600B | MARKET | 248 MARKET ST | 067 | LEX | 2019-09-19 | HROGERS | U131066 | 2019-06-03 | 2019-11-27 |  |  | MARK ROGERS | 2019-09-18 | 2019-09-18 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.0167 | 1 | 1662.38 | 253.95 | 106.28 | 56.29 | 1245.86 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19724381800 |  | 100348844 |  | 6748208M |  |  |  | 565 | EX | REPL S/L - MOVE METER - GR 2 | 2621P | ASHLAND | 117 ASHLAND AV | 049 | WIN | 2019-09-20 | U125208 | U125208 | 2019-07-16 | 2019-09-27 |  |  | DBANKS | 2019-09-18 | 2019-09-16 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 28.6333 | 7 | 2125.83 | 1201.47 | 800.25 | 81.87 | 42.24 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19733206900 |  | 100280097 |  | 6688228N | 1853312 |  |  | 565 | EX | REPLACE SL W/18026776900 | 2600B | SYCAMORE | 255 SYCAMORE DR | 073 | FRA | 2019-09-18 | U126602 | U131066 | 2019-08-15 | 2019-12-31 |  |  | DEREK PAYTON | 2019-09-18 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 10.5 | 1 | 1924.59 | 589.79 | 0 | 39.98 | 1294.82 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19740192700 |  | 100355184 |  | 7260280M |  |  |  | 566 | EX | ABANDON - PER SDADAMS | 2621P | 3RD | 708 E 3RD ST | 161 | MAY | 2019-09-18 | MSHARON | U125208 | 2019-09-09 | 2019-09-30 |  |  | MSHARON | 2019-09-18 | 2019-09-16 |  | A | 00032 | 10800011 | 0326320 | 0326320 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26320057 | 10.2667 | 3 | 588.09 | 540.78 | 10.62 | 36.69 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19740460800 |  | 100330066 |  | 6720208C |  |  |  | 565 | EX | NBT - INST SL TO NEW HL | 2621P | HOLIDAY | 312 HOLIDAY RD | 067 | LEX | 2019-09-18 | MCRAIG | U125208 | 2019-09-10 | 2019-09-10 | 2019-09-23 |  | MCRAIG | 2019-09-18 | 2019-09-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 8.9833 | 2 | 730.18 | 502.08 | 141.26 | 34.04 | 52.8 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19742009500 |  | 100246194 |  | 7372188L |  |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | BARRETT | BARRETT ST | 159 | WAR | 2019-09-20 | U125208 | U129005 | 2019-09-16 | 2019-09-16 |  |  | JCKIRK | 2019-09-18 | 2019-09-16 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 24.3833 | 0 | 2278.03 | 1384.31 | 0 | 409.82 | 483.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19742721400 |  | 100324438 |  | 6720204E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D031816 | 2621P | OLYMPIA | 3556 OLYMPIA DR | 067 | LEX | 2019-09-18 | JWCOX | U125208 | 2019-09-18 | 2019-09-17 | 2019-09-17 |  | JWCOX | 2019-09-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.85 | 1 | 2943.7 | 160.85 | 252.73 | 19.88 | 2510.24 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19742813800 |  | 100319135 |  | 6716208O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | MELBOURNE | 220 MELBOURNE WY | 067 | LEX | 2019-09-18 | JWCOX | U129005 | 2019-09-18 | 2019-09-17 | 2019-09-17 |  | JWCOX | 2019-09-18 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26210022 | 1.95 | 1 | 2881.9 | 109.13 | 258 | 7.41 | 2507.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673610500 |  | 100310455 |  | 6716208I | 1636363 |  |  | 565 | EX | REPLACE SL W/17026733100 | 2600B | CLAYS MILL | 2623 CLAYS MILL RD | 067 | LEX | 2019-09-19 | U461443 | U131066 | 2019-01-30 | 2019-12-31 |  |  | WGRAVES | 2019-09-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.7833 | 1 | 4193.61 | 299.09 | 257.26 | 115.41 | 3521.85 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678775900 |  | 500148932 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | FORBES | 1401 N FORBES RD | 067 | LEX | 2019-09-19 | U124003 | U131066 | 2019-02-01 | 2019-11-27 |  |  | BPULLIAM/RLA | 2019-09-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3639.79 | 0 | 0 | 0 | 3639.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678784900 |  | 100299119 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LEESTOWN | 1421 LEESTOWN RD | 067 | LEX | 2019-09-19 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-09-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.5833 | 1 | 3554.34 | 83.83 | 0 | 18.1 | 3452.41 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680085000 |  | 100320260 |  | 6716208G | 1748686 |  |  | 565 | EX | REPLACE SL W/17026736100 | 2600B | MCDONALD | 1831 MCDONALD AV | 067 | LEX | 2019-09-19 | U126284 | U131066 | 2019-02-07 | 2019-12-27 | 2021-06-30 |  | JOSH PASLEY | 2019-09-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6 | 1 | 3604.16 | 345.16 | 0 | 121.98 | 3137.02 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19682020300 |  | 100420070 |  | 6696212H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094326 | 2621P | WOODSON | WOODSON DR 61-64 | 239 | VER | 2019-09-20 | U125208 | U130193 | 2019-02-18 | 2018-11-29 | 2020-05-31 |  | CDESPAI | 2019-09-19 | 2019-02-18 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 7.5 | 2 | 4612.93 | 418.31 | 382.15 | 784.36 | 3028.11 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687823600 |  | 100280112 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | LYONS | 326 LYONS DR | 073 | FRA | 2019-09-19 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687834400 |  | 100280058 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 332 WESTLAND DR | 073 | FRA | 2019-09-19 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1287.14 | 0 | 0 | 0 | 1287.14 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687834600 |  | 100280057 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 334 WESTLAND DR | 073 | FRA | 2019-09-19 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1592.99 | 0 | 0 | 0 | 1592.99 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687834700 |  | 100280102 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 335 WESTLAND DR | 073 | FRA | 2019-09-19 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1294.82 | 0 | 0 | 0 | 1294.82 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687835100 |  | 100280108 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 339 WESTLAND DR | 073 | FRA | 2019-09-19 | U126602 | U131066 | 2019-03-13 | 2019-11-27 |  |  | DEREK PAYTON | 2019-09-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 10.5 | 1 | 2576.17 | 589.78 | 0 | 39.98 | 1946.41 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19707742300 |  | 100262073 |  | 7352256D | 1961470 |  |  | 565 | EX | RPLC SL/19026862600/ | 2600B | FLORENCE | 1339 FLORENCE ST | 019 | ASH | 2019-09-19 | U124015 | U131066 | 2019-05-21 | 2019-11-27 |  |  | ORA SLONE | 2019-09-19 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1316.1 | 0 | 0 | 0 | 1316.1 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19711108700 |  | 100297728 |  | 6716212H | 1855598 |  |  | 565 | EX | RPLC SL/18026796000/ | 2600B | MARKET | 240 MARKET ST | 067 | LEX | 2019-09-20 | HROGERS | U131066 | 2019-06-03 | 2019-11-27 |  |  | MARK ROGERS | 2019-09-19 | 2019-09-19 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.2 | 1 | 2182.64 | 314.3 | 108.18 | 69.65 | 1690.51 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19731923800 |  | 100264789 |  | 7384168L |  |  |  | 565 | EX | REPLACE SERVICE LINE - D133208 | 2621P | HAPPY VALLEY | 252 HAPPY VALLEY RD | 195 | S W | 2019-09-19 | BBMULLI | U125208 | 2019-08-09 | 2020-02-07 | 2021-08-31 |  | BBMULLI | 2019-09-19 | 2019-09-17 |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26330055 | 25.7 | 4 | 1896.85 | 1414.64 | 0 | 470.69 | 11.52 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19738530800 |  | 100322527 |  | 6716208D | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMEDIATE | 2621D | TREMONT | 726 TREMONT AV | 067 | LEX | 2019-09-19 | MCRAIG | AOC SYST | 2019-08-30 | 2020-02-28 | 2020-12-31 |  | MCRAIG | 2019-09-19 | 2019-09-18 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 17.35 | 4 | 1261.97 | 965.48 | 167.67 | 65.46 | 63.36 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19742488800 |  | 100291068 |  | 6720212A | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPLACE RISER / | 2621D | DAKOTA | 751 DAKOTA ST | 067 | LEX | 2019-09-20 | U125208 | AOC SYST | 2019-09-17 | 2019-10-17 | 2019-11-16 |  | WHIMES | 2019-09-19 | 2019-09-19 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 23.3 | 4 | 1420.84 | 1157.32 | 177.35 | 78.49 | 7.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19742878200 |  | 100291295 |  | 6720216H |  |  |  | 565 | EX | REPLACE SERVICE LINE - D031817 | 2621P | ELMWOOD | 196 ELMWOOD DR | 067 | LEX | 2019-09-20 | U125208 | U129005 | 2019-09-18 | 2019-09-18 | 2019-09-18 |  | JWCOX | 2019-09-19 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6 | 1 | 3118.94 | 335.84 | 289.45 | 22.77 | 2470.88 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19743231400 |  | 100417723 |  | 6696212H |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | WOODSON | WOODSON DR 65-68 | 239 | VER | 2019-09-19 | CDESPAI | U129005 | 2019-09-19 | 2019-09-19 |  |  | CDESPAI | 2019-09-19 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26230032 | 2 | 1 | 1913.61 | 116.68 | 202.1 | 232.61 | 1362.22 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19744228400 |  | 100360875 |  | 6736228K | 1747968 |  |  | 565 | EX | REPLACE SL W/17026728800 | 2621P | BETHLEHEM | 376 BETHLEHEM RD | 017 | PAR | 2019-09-25 | U123111 | U124960 | 2019-09-23 | 2049-12-31 |  |  | LYN STAFFORD | 2019-09-19 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 0.016667 | 1 | 1306.74 | 0.57 | 0 | 0.2 | 1305.97 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 06662823800 |  | 100352047 |  | 6744208J |  |  |  | 566 | EX | ABANDON / BLDG 2B RAISED/ IDLE | 2621P | LEXINGTON | 1417 W LEXINGTON AV | 049 | WIN | 2019-09-20 | DBANKS | KEMBERT | 2006-10-10 | 2015-08-28 |  |  | DBANKS | 2019-09-20 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 35.8 | 6 | 1920.67 | 1633.16 | 0 | 287.51 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19026866500 |  |  |  | 6748208E | 1962355 | U131982 |  | 583 | EX | INSTALL VRG CONTROLLER | 2600E | EARLY | EARLY DR | 049 | WIN | 2019-09-30 | U462463 | U131982 | 2019-03-18 | 2019-12-30 | 2019-12-31 | 2019-09-20 | CYNTHIA FARIS | 2019-09-20 | 2019-06-19 |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00583 | 3200583 |  |  | WP8665 |  |  | 100 | 058332190268665 | 118.0667 | 30 | 26945.7 | 6948.65 | 10784.81 | 1581.87 | 4274.88 | 0 | 136.47 | 3219.02
KY | KY - CENTRAL | 2629 | 19026866600 |  |  |  | 6748208E | 1962355 | U131982 |  | 584 | EX | RETIRE EXISTING CONTROLLER | 2600E | EARLY | EARLY DR | 049 | WIN | 2019-09-30 | U462463 | U131982 | 2019-03-18 | 2019-12-31 | 2019-12-31 | 2019-09-20 | CYNTHIA FARIS | 2019-09-20 |  |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00584 | 3200584 |  |  | WP8666 |  |  | 100 | 058432190268666 | 10 | 0 | 621.64 | 588.24 | 0 | 33.4 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673606300 |  | 100310456 |  | 6716208I | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2779 CLAYS MILL RD | 067 | LEX | 2019-09-20 | U461443 | U131066 | 2019-01-30 | 2019-11-27 |  |  | WGRAVES | 2019-09-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 | 4.2333 | 1 | 1975.77 | 219.02 | 256.31 | 84.53 | 1415.91 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678785100 |  | 100299120 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LEESTOWN | 1431 LEESTOWN RD | 067 | LEX | 2019-09-20 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-09-20 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.7667 | 1 | 3586.74 | 146.04 | 0 | 31.5 | 3409.2 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19692439700 |  | 100458508 |  | 7236212L | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REMED - D094049 | 2629D | MCCROSKY | 1240 MCCROSKY DR | 173 | MT | 2019-09-20 | DENNING | AOC SYST | 2019-03-29 | 2019-09-27 | 2021-03-31 |  | DENNING | 2019-09-20 | 2019-07-02 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 43.4667 | 15 | 2879.58 | 1806.27 | 38.8 | 975.95 | 58.56 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19707742500 |  | 100262072 |  | 7352256D | 1961470 |  |  | 565 | EX | RPLC SL/19026862600/ | 2600B | FLORENCE | 1343 FLORENCE ST | 019 | ASH | 2019-09-20 | U124015 | U131066 | 2019-05-21 | 2019-11-27 |  |  | ORA SLONE | 2019-09-20 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1570.72 | 0 | 0 | 0 | 1570.72 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19726235500 |  | 100292427 |  | 6720216J |  |  |  | 565 | EX | UPGRADE SL TO NEW MTR LOCATION | 2621P | SILVER | 1709 SILVER LN | 067 | LEX | 2019-09-24 | U125208 | U125208 | 2019-07-23 | 2019-08-15 | 2019-08-15 |  | WHIMES | 2019-09-20 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25.5333 | 4 | 2206.71 | 1167.31 | 901.7 | 79.14 | 58.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 19743221400 |  | 100356483 |  | 7256280K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D097248 | 2621P | HILLCREST | 701 HILLCREST RD | 161 | MAY | 2019-09-20 | SDADAMS | U125964 | 2019-09-19 | 2019-09-18 | 2019-09-18 |  | SDADAMS | 2019-09-20 |  |  | A | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26320021 | 16.6 | 2 | 1488.33 | 878.95 | 241.64 | 59.58 | 308.16 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678785000 |  | 500141969 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LEESTOWN | 1423 LEESTOWN RD B-C | 067 | LEX | 2019-09-21 | U461423 | U131066 | 2019-02-01 | 2019-11-27 |  |  | KKOUNS | 2019-09-21 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 7 | 1 | 2723.68 | 378.4 | 0 | 140.67 | 2204.61 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687834300 |  | 100280059 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 330 WESTLAND DR | 073 | FRA | 2019-09-21 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-21 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2621 | 07701342600 |  | 500422309 |  | 16708204G |  |  |  | 566 | EX | ABN SERV LINE PER 24 MO MEMO | 2600B | FONDA | 112 FONDA LN | 113 | NIC | 2019-09-23 | JWCOX | DMCCULL | 2007-09-07 | 2019-09-23 |  |  | JWCOX | 2019-09-23 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 12.1667 | 1 | 1584.94 | 681.68 | 17.04 | 246.32 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18026779200 |  |  |  | 6716216P | 1425507 | BKSLONE |  | 585 | EX | R-1133 INSTALL NEW 19X24 FENCE | 2600E | NEW CIRCLE | 763 W NEW CIRCLE RD | 067 | LEX | 2019-09-24 | U462463 | BKSLONE | 2018-06-17 | 2019-09-30 | 2019-09-30 | 2019-09-23 | CYNTHIA FARIS | 2019-09-23 | 2019-09-06 |  | F | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00585 | 3207513 |  |  | WP7792 |  |  | 100 | 751332180267792 | 25.3667 | 6 | 9592.7 | 1406.39 | 0 | 149.69 | 6982.6 | 0 | 27.37 | 1026.65
KY | KY - CENTRAL | 2629 | 18588347800 |  | 100357558 |  | 6740232M | 1745023 |  |  | 565 | EX | RPLC SL/17026708900/ | 2600B | 4TH | 123 E 4TH ST REAR | 017 | PAR | 2019-09-30 | U126603 | U131066 | 2018-02-19 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-09-23 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3053.54 | 0 | 0 | 0 | 3053.54 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678783800 |  | 100298893 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LEESTOWN | 1307 LEESTOWN RD | 067 | LEX | 2019-09-23 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-09-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.9333 | 1 | 2093.38 | 365.87 | 0 | 24.8 | 1702.71 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678785900 |  | 100299131 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LEESTOWN | 1475 LEESTOWN RD | 067 | LEX | 2019-09-23 | U124003 | U131066 | 2019-02-01 | 2019-11-27 |  |  | BPULLIAM/RLA | 2019-09-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3371.37 | 0 | 0 | 0 | 3371.37 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680085300 |  | 100320267 |  | 6716208G | 1748686 |  |  | 565 | EX | REPLACE SL W/17026736100 | 2600B | MCDONALD | 1836 MCDONALD AV | 067 | LEX | 2019-09-23 | U126284 | U131066 | 2019-02-07 | 2019-12-27 | 2021-06-30 |  | JOSH PASLEY | 2019-09-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.95 | 1 | 3228.26 | 227.8 | 0 | 80.51 | 2919.95 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687834200 |  | 100280060 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 328 WESTLAND DR | 073 | FRA | 2019-09-30 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2123.54 | 0 | 0 | 0 | 2123.54 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687834500 |  | 100280101 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 333 WESTLAND DR | 073 | FRA | 2019-09-30 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-23 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2363.63 | 0 | 0 | 0 | 2363.63 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691695400 |  | 100326518 |  | 6720208A | 1855692 |  |  | 565 | EX | REPLACE SL W/18026796400 | 2600B | FONTAINE | 1212 FONTAINE RD | 067 | LEX | 2019-09-23 | U125559 | U131066 | 2019-03-27 | 2019-12-31 |  |  | BJACKSON | 2019-09-23 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1649.77 | 0 | 0 | 0 | 1649.77 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19707743000 |  | 100262071 |  | 7352256D | 1961470 |  |  | 565 | EX | RPLC SL/19026862600/ | 2600B | FLORENCE | 1359 FLORENCE ST | 019 | ASH | 2019-09-23 | U124015 | U131066 | 2019-05-21 | 2019-11-27 |  |  | ORA SLONE | 2019-09-23 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.2 | 1 | 1232.5 | 11.91 | 0 | 0.81 | 1219.78 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19744144500 |  | 100252715 |  | 7348264O |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | GILLEY | 904 GILLEY ST | 089 | FLA | 2019-09-23 | MCOLLET | U129005 | 2019-09-23 | 2019-09-23 | 2019-09-23 |  | MCOLLET | 2019-09-23 | 2019-09-23 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 17.5167 | 2 | 2176.38 | 1077.78 | 186.36 | 858.48 | 53.76 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18026799501 |  |  |  | 7240216O | 1856175 | U130604 |  | 559 | EX | INSTALL 4" PV | 2600B | LOCUST | LOCUST ST | 173 | MT | 2019-10-17 | U123258 | U130604 | 2019-09-24 | 2019-10-30 | 2019-10-31 | 2019-09-23 | WILL FULKS | 2019-09-24 | 2019-09-24 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00559 | 3200559 |  |  | WP7995 |  |  | 100 | 055932180267995 | 18.0667 | 18 | 15223.31 | 2896.38 | 508.44 | 599.97 | 9577.99 | 0 | 90.28 | 1550.25 | 6
KY | KY - CENTRAL | 2629 | 18026799700 |  |  |  | 7240216O | 1856175 | U130604 |  | 559 | EX | INSTALL 6" PV | 2600B | LOCUST | LOCUST ST | 173 | MT | 2019-10-17 | U123258 | U128885 | 2018-10-05 | 2019-10-30 | 2019-10-31 | 2019-09-23 | WILL FULKS | 2019-09-24 | 2019-09-18 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00559 | 3200559 |  |  | WP7997 |  |  | 100 | 055932180267997 | 31.9333 | 24 | 12249.1 | 1795.15 | 938.67 | 404.4 | 7913.62 | 0 | 26.89 | 1170.37 | 6
KY | KY - CENTRAL | 2629 | 18601930800 |  | 100357566 |  | 6740232M | 1745023 |  |  | 565 | EX | RPLC SL/17026708900/ | 2600B | 4TH | 118 E 4TH ST | 017 | PAR | 2019-09-30 | U126603 | U125964 | 2018-04-11 | 2019-12-31 |  |  | SHAWN DENNIS | 2019-09-24 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 3020.4 | 0 | 0 | 0 | 3020.4 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678786000 |  | 100299132 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LEESTOWN | 1477 LEESTOWN RD 2F | 067 | LEX | 2019-09-24 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-09-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.4167 | 1 | 2932.45 | 74.86 | 0 | 16.17 | 2841.42 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687833200 |  | 100280065 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 318 WESTLAND DR | 073 | FRA | 2019-09-30 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687833800 |  | 100280062 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 324 WESTLAND DR | 073 | FRA | 2019-09-30 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-24 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1924.61 | 0 | 0 | 0 | 1924.61 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19711109100 |  | 100297681 |  | 6716212H | 1855598 |  |  | 565 | EX | RPLC SL/18026796000/ | 2600B | MECHANIC | 201 MECHANIC ST | 067 | LEX | 2019-09-27 | U461516 | U131066 | 2019-06-03 | 2019-11-27 |  |  | NEAL JOHNSON | 2019-09-24 | 2019-09-23 | 2019-09-24 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 19.1 | 4 | 3715.68 | 1017.82 | 488.33 | 382.98 | 1826.55 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19742827400 |  | 100409014 |  | 6716212I |  |  |  | 565 | EX | AOC - REPL SL & REBUILD MP LOO | 2621P | HILL RISE | 730 HILL RISE CT 2 | 067 | LEX | 2019-09-24 | WHIMES | U125208 | 2019-09-18 | 2019-09-23 |  |  | WHIMES | 2019-09-24 | 2019-09-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 44.3333 | 6 | 3719.99 | 2100.72 | 1106.35 | 347.8 | 165.12 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19742851300 |  | 100406005 |  | 6716212I | 1635077 |  |  | 565 | EX | AOC - REPL SL & REBUILD MP LO | 2621P | HILL RISE | 1701 HILL RISE DR 3 | 067 | LEX | 2019-09-26 | U125208 | U125208 | 2019-09-18 | 2019-09-30 |  |  | KKINDER | 2019-09-24 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 25.65 | 4 | 7650.94 | 1384.03 | 6116.43 | 93.84 | 56.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19744279300 |  | 100319806 |  | 6716208K |  |  |  | 565 | EX | GRADE 1 REPLACE SERV | 2621P | JESSELIN | 122 JESSELIN DR | 067 | LEX | 2019-09-24 | JWCOX | U129939 | 2019-09-23 | 2019-09-23 | 2019-09-23 |  | JWCOX | 2019-09-24 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.98333 | 1 | 3171.02 | 55.42 | 108.15 | 20.03 | 2987.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19744579100 |  | 100408310 |  | 6716212I | 1635077 |  |  | 565 | EX | AOC ATMOS CORR REPL RISER/SL | 2621P | HILL RISE | 734 HILL RISE CT 2 | 067 | LEX | 2019-09-26 | U125208 | U125964 | 2019-09-24 | 2019-09-24 | 2019-11-24 |  | WHIMES | 2019-09-24 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 | KYACA |  | 100 | 056532B26210031 | 2.1667 | 2 | 1173.66 | 99.48 | 1003.11 | 6.75 | 64.32 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19744605300 |  | 100258986 |  | 7356256A |  |  |  | 565 | EX | REPLACE SERVICE LINE - D188625 | 2621P | 15TH | 714< 15TH ST | 019 | ASH | 2019-09-26 | U125208 | U129005 | 2019-09-24 | 2019-09-18 | 2019-09-18 |  | CWHEELE | 2019-09-24 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0021 |  |  | 100 | 056532B26310021 | 2.2667 | 1 | 8952.81 | 5820.61 | 187.52 | 2855.4 | 89.28 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19744738700 |  | 100405895 |  | 6716212I |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HILL RISE | 1701 HILL RISE DR 1 | 067 | LEX | 2019-09-26 | U125208 | U129005 | 2019-09-24 | 2019-09-24 |  |  | KKINDER | 2019-09-24 | 2019-09-24 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 0.71667 | 2 | 883.79 | 35.99 | 787.74 | 2.46 | 57.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 06638046700 |  | 500089377 |  | 16708204L |  |  |  | 566 | EX | ABANDON SERVICE | 2600B | LANTERN | 67 LANTERN WY | 113 | NIC | 2019-09-25 | JENSMIN | SSUTHER | 2006-02-10 | 2019-09-25 |  |  | JENSMIN | 2019-09-25 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 5.25 | 1 | 1391.07 | 299.23 | 50.49 | 401.45 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 06638047000 |  | 500674485 |  | 6708204L | 9934915 |  |  | 566 | EX | ABANDON SERVICE | 2621P | HARRODSBURG | 5001 HARRODSBURG RD CONCESS | 113 | NIC | 2019-09-25 | JWCOX | SSUTHER | 2006-02-10 | 2019-09-25 |  |  | JWCOX | 2019-09-25 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.48333 | 1 | 680.14 | 26.86 | 11.56 | 1.82 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11878474000 |  | 500089176 |  | 6708204L |  |  |  | 566 | EX | ABANDON / RI 01-11-2010 | 2600B | WOODBRIAR | 55 WOODBRIAR CT | 113 | NIC | 2019-09-25 | JWCOX | U906307 | 2011-01-11 | 2019-09-25 |  |  | JWCOX | 2019-09-25 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 0.71667 | 1 | 698.76 | 40.87 | 15.22 | 2.77 | 639.9 | 0 | 0 | 0
KY | KY - WEST | 2621 | 11894322400 |  | 500749581 |  | 16708204L | 9717617 |  |  | 566 | EX | ABANDON SERVICE LINE | 2621P | WINDY VIEW | 103 WINDY VIEW CT | 113 | NIC | 2019-09-25 | JWCOX | U124961 | 2011-03-04 | 2019-09-25 |  |  | JWCOX | 2019-09-25 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26210057 | 4.2167 | 1 | 902.14 | 235.64 | 10.62 | 15.98 | 639.9 | 0 | 0 | 0
KY | KY - EAST | 2633 | 17465537800 |  | 100264758 |  | 7384168O |  |  |  | 566 | EX | RA 01-04-17 CUST REQ | 2621P | NEW CAMP | 696 NEW CAMP RD | 195 | S W | 2019-09-25 | JCKIRK | U125208 | 2017-01-05 | 2049-12-31 |  |  | JCKIRK | 2019-09-25 | 2019-09-24 |  | A | 00032 | 10800011 | 0326330 | 0326330 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26330057 | 2.4167 | 2 | 170.21 | 135.08 | 0 | 35.13 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18601930700 |  | 100357557 |  | 6740232M | 1745023 |  |  | 565 | EX | RPLC SL/17026708900/ | 2600B | 4TH | 119 E 4TH ST | 017 | PAR | 2019-09-30 | U126603 | U125964 | 2018-04-11 | 2019-12-31 |  |  | SHAWN DENNIS | 2019-09-25 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 2422.03 | 0 | 0 | 0 | 2422.03 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19026882501 |  | 501264789 |  | 6716232M | 1964872 | U461383 |  | 555 | EX | INSTALL 2500' OF 2"PMMP MAIN | 2600B | RICHWOOD | 100 RICHWOOD CR | 209 | GEO | 2019-10-14 | U121330 | U461383 | 2019-09-24 | 2019-07-30 | 2019-09-30 | 2019-09-25 | JDUNN | 2019-09-25 | 2019-09-24 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP8825 |  |  | 100 | 055532190268825 | 197.7833 | 84116 | 152956.98 | 11166.68 | 2851.4 | 1685.6 | 122021.55 | 0 | 395.6 | 14836.15 | 2474
KY | KY - WEST | 2621 | 19026895800 |  |  |  | 6720212L | 1852951 | U128885 |  | 559 | EX | INSTALL 12" CSHP | 2600B | WINCHESTER | WINCHESTER RD | 067 | LEX | 2019-10-10 | U123258 | U128885 | 2019-09-12 | 2019-12-31 | 2019-12-31 | 2019-06-21 | JOHN SMITH | 2019-09-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP8958 | AMRCB |  | 100 | 055932190268958 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
KY | KY - WEST | 2623 | 19026899200 |  |  |  | 6700212N | 1966988 | U122858 |  | 559 | EX | INSTALL 20'- 2" PMMP | 2621P | HUNTER | 203 HUNTER CT | 239 | VER | 2020-08-13 | U128132 | U132703 | 2019-09-26 | 2020-02-12 | 2020-02-16 | 2019-09-26 | CDESPAI | 2019-09-25 | 2020-02-26 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00559 | 3200559 |  |  | WP8992 |  |  | 100 | 055932190268992 | 0.016667 | 20 | 387.15 | 0.61 | 347.17 | 0.04 | 0 | 0 | -2.49 | 41.82 | 20
KY | KY - WEST | 2623 | 19026899300 |  |  |  | 6700212N | 1966988 | U122858 |  | 560 | EX | RETIRE 20'-2" PMMP | 2621P | HUNTER | 203 HUNTER CT | 239 | VER | 2020-08-13 | U128132 | U132703 | 2019-09-26 | 2020-06-30 | 2020-06-30 | 2019-09-26 | CDESPAI | 2019-09-25 | 2020-02-26 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00560 | 3200560 |  |  | WP8993 |  |  | 100 | 056032190268993 | 0.016667 | 0 | 0.65 | 0.61 | 0 | 0.04 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678785200 |  | 100299121 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LEESTOWN | 1437 LEESTOWN RD | 067 | LEX | 2019-09-25 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-09-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 8 | 1 | 3360.93 | 421.72 | 0 | 28.61 | 2910.6 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678786300 |  | 100299136 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LEESTOWN | 1485 LEESTOWN RD | 067 | LEX | 2019-09-25 | U124003 | U131066 | 2019-02-01 | 2019-11-27 |  |  | BPULLIAM/RLA | 2019-09-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3312.23 | 0 | 0 | 0 | 3312.23 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680067000 |  | 100320268 |  | 6716208G | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | MCDONALD | 1834 MCDONALD AV | 067 | LEX | 2019-09-25 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-09-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 4.3 | 1 | 3939.89 | 247.95 | 0 | 87.65 | 3604.29 | 0 | 0 | 0
KY | KY - EAST | 2633 | 19686364800 |  | 501128693 |  | 7384168K |  | U125208 |  | 565 | EX | REROUTE SL, SET MTR LOOP - NCV | 2621P | CENTRAL | 747 CENTRAL AV | 195 | S W | 2019-09-25 | JCKIRK | U125208 | 2019-03-06 | 2049-12-31 |  |  | JCKIRK | 2019-09-25 | 2019-03-08 |  | A | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26330031 | 27.8 | 5 | 1905.03 | 1573.96 | 0 | 296.51 | 34.56 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687833700 |  | 100280093 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 323 WESTLAND DR | 073 | FRA | 2019-09-30 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1762.99 | 0 | 0 | 0 | 1762.99 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687834000 |  | 100280061 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 326 WESTLAND DR | 073 | FRA | 2019-09-30 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-25 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2479.22 | 0 | 0 | 0 | 2479.22 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691668200 |  | 100326907 |  | 6720208A | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1125 FONTAINE RD 1F | 067 | LEX | 2019-09-25 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-09-25 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 6652.82 | 64.24 | 726.33 | 5.53 | 5856.72 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19707742000 |  | 100262077 |  | 7352256D | 1961470 |  |  | 565 | EX | RPLC SL/19026862600/ | 2600B | FLORENCE | 1330 FLORENCE ST | 019 | ASH | 2019-09-25 | U124015 | U131066 | 2019-05-21 | 2019-11-27 |  |  | ORA SLONE | 2019-09-25 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 |  | 1 | 1218.74 | 0 | 0 | 0 | 1218.74 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19711108500 |  | 100297724 |  | 6716212H | 1855598 |  |  | 565 | EX | RPLC SL/18026796000/ | 2600B | MARKET | 216 MARKET ST | 067 | LEX | 2019-09-30 | U461516 | U131066 | 2019-06-03 | 2019-11-27 |  |  | NEAL JOHNSON | 2019-09-25 | 2019-09-25 | 2019-09-25 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.4667 | 2 | 2061.44 | 504.49 | 120.66 | 189.73 | 1246.56 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19711112500 |  | 100297725 |  | 6716212H | 1855598 |  |  | 565 | EX | REPLACE SL W/18026796000 | 2600B | MARKET | 220 MARKET ST | 067 | LEX | 2019-09-25 | U461516 | U131066 | 2019-06-03 | 2019-12-31 |  |  | NEAL JOHNSON | 2019-09-25 |  | 2019-09-25 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 867.99 | 0 | 91.99 | 0 | 776 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19734466200 |  | 500727913 |  | 7344244G | 1749147 |  |  | 565 | EX | REPLACE SL W/17026739600 | 2600B | TRACE | 15100 TRACE RD | 019 | RUS | 2019-09-26 | U125566 | U131066 | 2019-08-20 | 2019-12-31 |  |  | DAVID SKAGGS | 2019-09-25 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.016667 | 1 | 950.52 | 1.08 | 0 | 0.22 | 949.22 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19742304200 |  | 100244588 |  | 7356256G |  |  |  | 566 | EX | DEMO / ABANDON / RA 09-18-19 | 2621P | CENTRAL | 3029 CENTRAL AV | 019 | ASH | 2019-10-08 | U125208 | U132002 | 2019-09-17 | 2019-10-17 | 2019-10-17 |  | SMULLIN | 2019-09-25 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 7.5333 | 2 | 585.38 | 412.37 | 21.49 | 151.52 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19742837500 |  | 100280831 |  | 6688228I |  |  |  | 566 | EX | DEMO / ABANDON / RI 09-18-19 | 2621P | KNOTT | 510 KNOTT AV | 073 | FRA | 2019-09-25 | DCOLLIN | U132002 | 2019-09-18 | 2019-09-23 | 2019-10-18 |  | DCOLLIN | 2019-09-25 |  |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 14.0667 | 2 | 1351.26 | 759.45 | 43.73 | 548.08 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19745100100 |  | 100464135 |  | 6700212N |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HUNTERS | 201 HUNTERS CT | 239 | VER | 2019-09-27 | U125208 | U129005 | 2019-09-25 | 2019-09-25 |  |  | CDESPAI | 2019-09-25 | 2019-09-25 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 0.38333 | 2 | 1918.55 | 21.6 | 200.2 | 43.04 | 1653.71 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18026799600 |  |  |  | 7240216O | 1856175 | U130604 |  | 560 | EX | RETIRE 4" PV C3-09 | 2600B | LOCUST | LOCUST ST | 173 | MT | 2019-10-17 | U123258 | U128885 | 2018-10-05 | 2019-10-31 | 2019-10-31 | 2019-09-23 | WFULKS | 2019-09-26 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00560 | 3200560 |  |  | WP7996 |  |  | 100 | 056032180267996 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18026799800 |  |  |  | 7240216O | 1856175 | U130604 |  | 560 | EX | RETIRE 6" PV C3-08 | 2600B | LOCUST | LOCUST ST | 173 | MT | 2019-10-17 | U123258 | U128885 | 2018-10-05 | 2019-10-31 | 2019-10-31 | 2019-09-23 | WFULKS | 2019-09-26 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00560 | 3200560 |  |  | WP7998 |  |  | 100 | 056032180267998 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026885800 |  | 501271348 |  | 6724208D | 1965164 | U461383 |  | 555 | EX | INSTALL 550' OF 2"PMMP MAIN | 2600E | FITZGERALD | 1720 FITZGERALD CT | 067 | LEX | 2019-10-04 | U460266 | U461383 | 2019-07-18 | 2019-09-16 | 2019-09-20 | 2019-09-25 | KKOUNS | 2019-09-26 | 2019-09-16 | 2019-09-16 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP8858 |  |  | 100 | 055532190268858 | 85.1167 | 5157 | 25765.69 | 4600.81 | 1252.81 | 1537.82 | 15667.6 | 0 | 34.3 | 2672.35 | 573
KY | KY - WEST | 2621 | 19678776000 |  | 100298911 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | FORBES | 1403 N FORBES RD 140 | 067 | LEX | 2019-09-26 | U461467 | U131066 | 2019-02-01 | 2019-11-27 |  |  | D REFFETT | 2019-09-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 6.5667 | 1 | 5907.79 | 346.34 | 0 | 74.72 | 5486.73 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680084100 |  | 100320277 |  | 6716208G | 1748686 |  |  | 565 | EX | REPLACE SL W/17026736100 | 2600B | JOHNSTON | 127 JOHNSTON BV | 067 | LEX | 2019-09-26 | U126286 | U131066 | 2019-02-07 | 2019-12-31 |  |  | TYLER ALLISON | 2019-09-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2719.06 | 0 | 0 | 0 | 2719.06 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687835300 |  | 100280052 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 344 WESTLAND DR | 073 | FRA | 2019-09-30 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1919.03 | 0 | 0 | 0 | 1919.03 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19688215600 |  | 100466793 |  | 6740208C |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094646 | 2621P | WESTCHESTER | 24 WESTCHESTER DR | 049 | WIN | 2019-09-26 | DENNING | U125208 | 2019-03-14 | 2019-09-13 | 2021-03-31 |  | DENNING | 2019-09-26 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 9.1333 | 4 | 802.57 | 421.97 | 37.86 | 234.26 | 108.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691694600 |  | 100326909 |  | 6720208A | 1855692 |  |  | 565 | EX | REPLACE SL W/18026796400 | 2600B | FONTAINE | 1121 FONTAINE RD | 067 | LEX | 2019-09-26 | U125559 | U131066 | 2019-03-27 | 2019-12-31 |  |  | BJACKSON | 2019-09-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 5399 | 0 | 0 | 0 | 5399 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19711112100 |  | 100297723 |  | 6716212H | 1855598 |  |  | 565 | EX | REPLACE SL W/18026796000 | 2600B | MARKET | 200 MARKET ST | 067 | LEX | 2019-09-27 | U461516 | U131066 | 2019-06-03 | 2019-12-31 |  |  | NEAL JOHNSON | 2019-09-26 |  | 2019-09-26 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5 | 1 | 1733.76 | 266.34 | 120.66 | 100.2 | 1246.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19739405800 |  | 100269033 |  | 6736252M |  |  |  | 565 | EX | REPLACE SERVICE LINE - D096283 | 2621P | MILLER | 114 N MILLER ST DN | 097 | CYN | 2019-10-03 | U125208 | U125208 | 2019-09-05 | 2019-09-05 | 2019-09-05 |  | DBANKS | 2019-09-26 | 2019-09-25 |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 43.7167 | 7 | 2643.02 | 1892.38 | 561.85 | 128.31 | 60.48 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19743223700 |  | 100344927 |  | 6700224O |  |  |  | 565 | EX | SERV LINE - REPL: CONT 09/26 | 2621P | BRUEN | 109 E BRUEN ST | 239 | MID | 2019-10-03 | U125208 | U125208 | 2019-09-19 | 2019-09-26 |  |  | BJLONE | 2019-09-26 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 6.6 | 1 | 4877.51 | 347.26 | 605.98 | 23.52 | 3900.75 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19744711400 |  | 100406066 |  | 6716212I | 1635077 |  |  | 565 | EX | AOC - REPL SL & REBUILD MP LO | 2621P | HILL RISE | 1691 HILL RISE DR 1 | 067 | LEX | 2019-09-26 | LSTANFI | U125208 | 2019-09-24 | 2019-09-25 |  |  | LSTANFI | 2019-09-26 | 2019-09-25 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 42.9833 | 7 | 2945.5 | 2175.9 | 563.82 | 154.9 | 50.88 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19744713700 |  | 100406068 |  | 6716212I |  |  |  | 565 | EX | AOC - REPL SL & REBUILD MP LO | 2621P | HILL RISE | 1691 HILL RISE DR 3 | 067 | LEX | 2019-09-26 | LSTANFI | U125208 | 2019-09-24 | 2019-09-25 |  |  | LSTANFI | 2019-09-26 | 2019-09-25 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 24.9833 | 3 | 1482.6 | 1319.27 | 0 | 89.41 | 73.92 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19744718500 |  | 100406056 |  | 6716212I |  |  |  | 565 | EX | AOC - REPL SL & REBUILD MP LO | 2621P | HILL RISE | 1692 HILL RISE DR 3 | 067 | LEX | 2019-09-26 | LSTANFI | U125208 | 2019-09-24 | 2019-09-26 |  |  | LSTANFI | 2019-09-26 | 2019-09-26 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 28.3833 | 5 | 2922.34 | 1475.03 | 0 | 99.99 | 1347.32 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19744718800 |  | 100406054 |  | 6716212I |  |  |  | 565 | EX | AOC - REPL SL & REBUILD MP LO | 2621P | HILL RISE | 1692 HILL RISE DR 1 | 067 | LEX | 2019-09-26 | LSTANFI | U125208 | 2019-09-24 | 2019-09-27 |  |  | LSTANFI | 2019-09-26 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.1833 | 4 | 662.39 | 540.35 | 0 | 36.6 | 85.44 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19745099000 |  | 100464134 |  | 6700212N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D095265 | 2621P | HUNTERS | 203 HUNTERS CT | 239 | VER | 2019-09-27 | U125208 | U129005 | 2019-09-25 | 2019-09-25 | 2021-04-30 |  | CDESPAI | 2019-09-26 | 2019-09-25 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 28.3 | 2 | 12311.23 | 1652.53 | 200.2 | 3426.25 | 7032.25 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19745495600 |  | 100324407 |  | 6720204E |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | MILANO | 3535 MILANO RD | 067 | LEX | 2019-09-26 | JWCOX | U129005 | 2019-09-26 | 2019-09-26 |  |  | JWCOX | 2019-09-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.4833 | 1 | 1720.37 | 82.83 | 244.74 | 5.62 | 1387.18 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19745516400 |  | 100262076 |  | 7352256D | 1961470 |  |  | 565 | EX | REPLACE W/ 19026862600 | 2600B | FLORENCE | 1326 FLORENCE ST | 019 | ASH | 2019-09-26 | U124015 | U125768 | 2019-09-26 | 2049-12-31 |  |  | ORA SLONE | 2019-09-26 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26310032 | 0.1 | 1 | 1452.27 | 5.67 | 0 | 1.16 | 1445.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19745565600 |  | 100330416 |  | 6720212O |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | KINGSWOOD | 413 KINGSWOOD DR | 067 | LEX | 2019-09-26 | JENSMIN | U129005 | 2019-09-26 | 2019-09-26 | 2019-09-26 |  | JENSMIN | 2019-09-26 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 2.35 | 1 | 2434.07 | 178.03 | 250.28 | 181.47 | 1824.29 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19745620100 |  | 100408309 |  | 6716212I |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | HILL RISE | 734 HILL RISE CT 1 | 067 | LEX | 2019-09-26 | LSTANFI | U129005 | 2019-09-26 | 2019-09-26 |  |  | LSTANFI | 2019-09-26 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0031 |  |  | 100 | 056532B26210031 | 11 | 4 | 604.76 | 514.2 | 0 | 34.88 | 55.68 | 0 | 0 | 0
KY | KY - WEST | 2623 | 18635573900 |  | 500017116 |  | 6712228A | 1635077 |  |  | 565 | EX | REPLACE SERVICE LINE - D095022 | 2621P | MAIN | 802 W MAIN ST | 209 | GEO | 2019-10-03 | U125208 | U129939 | 2018-08-16 | 2018-09-12 | 2020-03-31 |  | BJLONE | 2019-09-27 | 2018-08-16 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 | 97.4167 | 27 | 32930.73 | 5127.09 | 1007 | 2528.2 | 24268.44 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026893900 |  |  |  | 6716212F | 1966196 | U461383 |  | 558 | EX | RETIRE 15' OF 3"BSMP MAIN | 2600B | VERSAILLES | 1202 VERSAILLES | 067 | LEX | 2019-10-08 | U460266 | U461383 | 2019-08-27 | 2019-09-29 | 2019-10-02 | 2019-09-17 | JENSMIN | 2019-09-27 | 2019-09-11 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP8939 | AMRCB |  | 100 | 055832190268939 | 9.4667 | 0 | 1045.62 | 541.48 | 0 | 504.14 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673605600 |  | 100312191 |  | 6716208E | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2602 CLAYS MILL RD | 067 | LEX | 2019-09-28 | U461439 | U131066 | 2019-01-30 | 2019-11-27 |  |  | A PARRIS | 2019-09-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 1857.41 | 0 | 218.39 | 0 | 1639.02 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680065100 |  | 100320309 |  | 6716208G | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | HILTONIA | 120 HILTONIA PR | 067 | LEX | 2019-09-27 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-09-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 0.35 | 1 | 1856.53 | 20.7 | 0 | 7.33 | 1828.5 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687833900 |  | 100280094 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 325 WESTLAND DR | 073 | FRA | 2019-09-30 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-27 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1919.03 | 0 | 0 | 0 | 1919.03 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19689419000 |  | 100360882 |  | 6736228G | 1747968 |  |  | 565 | EX | RPLC SL/17026728800/ | 2600B | BETHLEHEM | 263 BETHLEHEM RD | 017 | PAR | 2019-09-27 | U126532 | U131066 | 2019-03-19 | 2019-11-27 |  |  | LESLIE SHARON | 2019-09-27 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 4102.88 | 0 | 0 | 0 | 4102.88 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19691975700 |  | 100344209 |  | 7240212G |  |  |  | 565 | EX | REPLACE SERVICE LINE - LEAKAGE | 2621P | WOODFORD | 1002 WOODFORD DR | 173 | MT | 2019-09-27 | DENNING | U125208 | 2019-03-28 | 2019-09-27 | 2021-03-31 |  | DENNING | 2019-09-27 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 13.2 | 4 | 1209.87 | 602.69 | 268.68 | 334.66 | 3.84 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19739854100 |  | 100269034 |  | 6736252M |  |  |  | 566 | EX | REMOVE METER / ABN W/100269033 | 2621P | MILLER | 114 N MILLER ST UP | 097 | CYN | 2019-10-03 | U125208 | U125208 | 2019-09-06 | 2019-09-27 |  |  | RJJOHNS | 2019-09-27 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 4 | 3 | 193.71 | 181.41 | 0 | 12.3 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19742829800 |  | 100409013 |  | 6716212I | 1635077 |  |  | 565 | EX | AOC - REPL SL & REBUILD MP LOO | 2621P | HILL RISE | 730 HILL RISE CT 1 | 067 | LEX | 2019-09-27 | WHIMES | U125208 | 2019-09-18 | 2019-09-23 |  |  | WHIMES | 2019-09-27 | 2019-09-23 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 14.0333 | 2 | 1898.96 | 804.78 | 863.95 | 54.55 | 175.68 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19743224800 |  | 100324385 |  | 6720204E |  |  |  | 565 | EX | REPLACE SERVICE LINE - D094128 | 2621P | VENETIAN | 1156 VENETIAN WY | 067 | LEX | 2019-09-27 | JWCOX | U125208 | 2019-09-19 | 2019-09-25 | 2019-10-09 |  | JWCOX | 2019-09-27 | 2019-09-26 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.15 | 2 | 3166.38 | 568.06 | 252.71 | 99.82 | 2245.79 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19745903000 |  | 100323927 |  | 6716208P |  |  |  | 565 | EX | GRADE ONE LK CO SERV D031818 | 2621P | RAVEN | 832 RAVEN RD | 067 | LEX | 2019-09-27 | JWCOX | U124447 | 2019-09-27 | 2019-09-26 | 2019-09-26 |  | JWCOX | 2019-09-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 1.15 | 1 | 2036.35 | 64.34 | 357.04 | 23.27 | 1591.7 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19745929300 |  | 100406079 |  | 6716212I |  |  |  | 565 | EX | REPL SL & REBUILD MP LO | 2621P | HILL RISE | 1695 HILL RISE DR 3 | 067 | LEX | 2019-10-03 | U125208 | U125208 | 2019-09-27 | 2019-09-27 |  |  | WHIMES | 2019-09-27 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.6667 | 4 | 1564.54 | 625.56 | 863.91 | 42.43 | 32.64 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19745929500 |  | 100406077 |  | 6716212I |  |  |  | 565 | EX | REPL SL & REBUILD MP LO | 2621P | HILL RISE | 1695 HILL RISE DR 1 | 067 | LEX | 2019-10-03 | U125208 | U125208 | 2019-09-27 | 2019-09-27 |  |  | WHIMES | 2019-09-27 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 30.2333 | 5 | 2453.78 | 1384.32 | 947.73 | 93.89 | 27.84 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19745995300 |  | 100287015 |  | 6720212F |  |  |  | 565 | EX | REPLACE SERVICE LINE - D221344 | 2621P | OAKHILL | 818 OAKHILL DR | 067 | LEX | 2019-10-04 | U125208 | U129939 | 2019-09-27 | 2019-09-30 | 2019-10-18 |  | JENSMIN | 2019-09-27 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0022 |  |  | 100 | 056532B26210022 | 7.7333 | 2 | 7053.49 | 441.71 | 3571.23 | 588.87 | 2451.68 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 07671584300 |  | 100340827 |  | 6740184P |  |  |  | 566 | EX | RETIRE SL | 2621P | UNION CITY | UNION CITY RD TR2 | 151 | RIC | 2019-09-28 | DENNING | SKSMITH | 2007-01-08 | 2019-09-30 |  |  | DENNING | 2019-09-28 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 | 0.98333 | 2 | 55.59 | 44.68 | 0 | 10.91 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18588351700 |  | 100357553 |  | 6740232M | 1745023 |  |  | 565 | EX | RPLC SL/17026708900/ | 2600B | PLEASANT | 406 PLEASANT ST | 017 | PAR | 2019-09-28 | U461516 | U131066 | 2018-02-19 | 2019-11-27 |  |  | NEAL JOHNSON | 2019-09-28 |  | 2019-09-28 | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 9.4667 | 1 | 3026.99 | 503.86 | 245.83 | 189.6 | 2087.7 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19026863900 |  | 501258589 |  | 7348248A | 1961710 | U122858 |  | 555 | EX | INSTALL 1450'-2" PMMP | 2600B | ANTHONY | 12612 ANTHONY DR | 019 | ASH | 2019-10-07 | U128132 | U122858 | 2019-02-25 | 2019-09-09 | 2019-09-30 | 2019-09-27 | MARCUS BLANKENSHIP | 2019-09-28 | 2019-09-12 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP8639 |  |  | 100 | 055532190268639 | 88.9333 | 18850 | 53339.99 | 5090.86 | 3663.82 | 1806.31 | 37018.52 | 0 | 81.6 | 5678.88 | 1450
KY | KY - WEST | 2621 | 19673605800 |  | 100312189 |  | 6716208E | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2610 CLAYS MILL RD | 067 | LEX | 2019-09-28 | U461439 | U131066 | 2019-01-30 | 2019-11-27 |  |  | A PARRIS | 2019-09-28 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 1863.34 | 0 | 143.32 | 0 | 1720.02 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687833400 |  | 100280064 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 320 WESTLAND DR | 073 | FRA | 2019-09-30 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1592.99 | 0 | 0 | 0 | 1592.99 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687833600 |  | 100280063 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 322 WESTLAND DR | 073 | FRA | 2019-09-30 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-28 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1282.34 | 0 | 0 | 0 | 1282.34 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19689418500 |  | 100360892 |  | 6736228G | 1747968 |  |  | 565 | EX | RPLC SL/17026728800/ | 2600B | BETHLEHEM | 195 BETHLEHEM RD | 017 | PAR | 2019-09-28 | U126532 | U131066 | 2019-03-19 | 2019-11-27 |  |  | LESLIE SHARON | 2019-09-28 | 2019-07-22 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 0.65 | 1 | 6539.85 | 38.08 | 0 | 12.38 | 6489.39 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 09782673300 |  | 100357359 | 06 | 16740232M | 1745023 |  |  | 566 | EX | RETIRE S/L WITH 17-0267089-00 | 2600B | PLEASANT | 407 PLEASANT ST | 017 | PAR | 2019-10-01 | U126603 | U804954 | 2009-04-10 | 2019-12-31 | 2019-12-31 |  | SHAWN DENNIS | 2019-09-30 |  |  | B | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26290057 |  | 1 | 932.19 | 0 | 0 | 0 | 932.19 | 0 | 0 | 0
KY | KY - WEST | 2621 | 18026795700 |  |  |  | 6720212B | 1855586 | U122858 |  | 561 | EX | INSTALL 1720'-2"&4" PMMP | 2600B | EDGELAWN | EDGELAWN AV | 067 | LEX | 2019-11-18 | U123258 | U122858 | 2018-09-15 | 2019-09-12 | 2019-09-30 | 2019-08-08 | KKOUNS | 2019-09-30 | 2019-07-08 | 2019-07-08 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP7957 | AMRCB |  | 100 | 056132180267957 | 297.75 | 60180 | 102973.29 | 19372.22 | 3982.15 | 6103.03 | 61683.13 | 0 | 357.48 | 11475.28 | 1770
KY | KY - EAST | 2631 | 18576362300 |  | 100242079 | 19 | 7356252D |  |  |  | 566 | EX | ABN/RI 01-22-18 THEFT-NCV VACA | 2621P | GREENUP | 968 GREENUP ST | 019 | CAT | 2019-09-30 | MCOLLET | SJUDE | 2018-01-22 | 2018-02-22 |  |  | MCOLLET | 2019-09-30 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 13.7 | 4 | 1074.64 | 602.28 | 1.38 | 470.98 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 18609120400 |  | 100245585 |  | 7360252I |  |  |  | 566 | EX | DEMO / ABANDON / RI 2004 | 2621P | 25TH | 209 25TH ST | 019 | CAT | 2019-09-30 | MCOLLET | U129799 | 2018-05-04 | 2018-07-10 | 2018-07-10 |  | MCOLLET | 2019-09-30 |  |  | A | 00032 | 10800011 | 0326310 | 0326310 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26310057 | 10.6333 | 3 | 692.95 | 405.58 | 22.36 | 265.01 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680066800 |  | 100320269 |  | 6716208G | 1748686 |  |  | 565 | EX | RPLC SL/17026736100/ | 2600B | MCDONALD | 1832 MCDONALD AV | 067 | LEX | 2019-09-30 | U126284 | U131066 | 2019-02-07 | 2019-11-27 |  |  | JOSH PASLEY | 2019-09-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 5.5167 | 1 | 3006.91 | 298.74 | 0 | 101.31 | 2606.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687832800 |  | 100280067 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 314 WESTLAND DR | 073 | FRA | 2019-10-01 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-30 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687832900 |  | 100280084 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 315 WESTLAND DR | 073 | FRA | 2019-10-01 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-30 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2331.02 | 0 | 0 | 0 | 2331.02 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687833000 |  | 100280066 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 316 WESTLAND DR | 073 | FRA | 2019-10-01 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-30 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1245.86 | 0 | 0 | 0 | 1245.86 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687833500 |  | 100280091 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 321 WESTLAND DR | 073 | FRA | 2019-10-01 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-09-30 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1534.42 | 0 | 0 | 0 | 1534.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691696500 |  | 100326877 |  | 6720208A | 1855692 |  |  | 565 | EX | REPLACE SL W/18026796400 | 2600B | FONTAINE | 1375 FONTAINE RD 1 | 067 | LEX | 2019-09-30 | U125559 | U131066 | 2019-03-27 | 2019-12-31 |  |  | BJACKSON | 2019-09-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 5760.19 | 0 | 0 | 0 | 5760.19 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19699891300 |  | 100299124 |  | 6716212B | 1855322 |  |  | 565 | EX | REPLACE SL W/18026792400 | 2600B | LEESTOWN | 1451 LEESTOWN RD | 067 | LEX | 2019-10-01 | U124003 | U131066 | 2019-04-23 | 2019-12-31 |  |  | BPULLIAM/RLA | 2019-09-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3943.5 | 0 | 0 | 0 | 3943.5 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19707742700 |  | 100262080 |  | 7352256D | 1961470 |  |  | 565 | EX | RPLC SL/19026862600/ | 2600B | FLORENCE | 1346 FLORENCE ST | 019 | ASH | 2019-09-30 | U124015 | U131066 | 2019-05-21 | 2019-11-27 |  |  | ORA SLONE | 2019-09-30 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.51667 | 1 | 1674.4 | 28.86 | 0 | 6.05 | 1639.49 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19734912500 |  | 100287396 |  | 6720212C | 1855823 |  |  | 565 | EX | RPLC SL/18026797400/ D094232 | 2600B | EMERSON | 442 EMERSON DR | 067 | LEX | 2020-01-20 | U128336 | U131066 | 2019-08-21 | 2019-09-27 | 2019-09-27 |  | JWCOX | 2019-09-30 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 10.15 | 1 | 3952.04 | 560.41 | 285.75 | 37.99 | 3067.89 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19743784400 |  | 100319848 |  | 6716208K |  |  |  | 565 | EX | REPLACE SERVICE LINE - D221341 | 2621P | ALBANY | 336 ALBANY RD | 067 | LEX | 2019-10-03 | U125208 | U125208 | 2019-09-20 | 2019-09-20 | 2019-10-10 |  | JWCOX | 2019-09-30 | 2019-09-30 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 3.15 | 1 | 3962.67 | 173.92 | 426.14 | 11.78 | 3350.83 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19744722400 |  | 100405996 |  | 6716212I |  |  |  | 565 | EX | AOC - REPL SL & REBUILD MP LO | 2621P | HILL RISE | 1696 HILL RISE DR 3 | 067 | LEX | 2019-10-03 | U125208 | U125208 | 2019-09-24 | 2019-09-27 |  |  | WHIMES | 2019-09-30 | 2019-09-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 29.9333 | 6 | 2589.4 | 1510.78 | 941.66 | 102.4 | 34.56 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19745129800 |  | 100351253 |  | 6744208N |  |  |  | 565 | EX | REPLACE SERVICE LINE - D097489 | 2621P | HOLIDAY | 109 HOLIDAY RD | 049 | WIN | 2019-09-30 | DENNING | U125208 | 2019-09-25 | 2019-09-27 | 2019-10-16 |  | DENNING | 2019-09-30 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 | 14.0667 | 2 | 1130.03 | 426.05 | 170.61 | 484.41 | 48.96 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19745977600 |  | 100265337 |  | 7348260P |  |  |  | 565 | EX | GRADE 1 REPLACE SERV D187678 | 2621P | LAWHORN | 2202 W LAWHORN HW | 019 | ASH | 2019-10-03 | U125208 | U129939 | 2019-09-27 | 2019-09-27 | 2019-09-27 |  | CWHEELE | 2019-09-30 | 2019-09-27 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 31.65 | 5 | 2368.5 | 1755.04 | 127.64 | 398.46 | 87.36 | 0 | 0 | 0
KY | KY - EAST | 2631 | 19746100100 |  | 100265343 |  | 7348260P |  |  |  | 565 | EX | REPLACE SERVICE LINE | 2621P | STATE RT 5 | 3141 STATE RT 5 | 019 | ASH | 2019-09-30 | CWHEELE | U129005 | 2019-09-27 | 2019-09-27 |  |  | CWHEELE | 2019-09-30 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26310055 | 0.36667 | 2 | 305.2 | 10.71 | 291.13 | 3.36 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19746418800 |  | 100405995 |  | 6716212I | 1635077 |  |  | 565 | EX | AOC - REPL SL & REBUILD MP LO | 2621P | HILL RISE | 1696 HILL RISE DR 1 | 067 | LEX | 2019-10-03 | U125208 | U125208 | 2019-09-30 | 2019-09-30 |  |  | WHIMES | 2019-09-30 | 2019-09-30 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 11.7333 | 4 | 1554.81 | 583.17 | 907.13 | 39.55 | 24.96 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19746733600 |  | 100360872 |  | 6736228K | 1747968 |  |  | 565 | EX | REPLACE SL W/17026728801 | 2600B | BETHLEHEM | 350 BETHLEHEM RD | 017 | PAR | 2019-10-01 | U123111 | U131066 | 2019-10-01 | 2019-12-31 |  |  | LYN STAFFORD | 2019-09-30 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1258.23 | 0 | 0 | 0 | 1258.23 | 0 | 0 | 0
KY | KY - WEST | 2623 | 15323430400 |  | 100464107 |  | 6696212K |  |  |  | 566 | EX | ABANDON / ALL ELE / RA 6-29-15 | 2621P | TYRONE | 830 TYRONE PK | 239 | VER | 2019-10-01 | EFGOINS | U128016 | 2015-06-29 | 2019-10-11 | 2019-10-11 |  | EFGOINS | 2019-10-01 | 2019-10-01 |  | A | 00032 | 10800011 | 0326230 | 0326230 | 00032 | 00566 | 3200566 |  |  | WP0057 |  |  | 100 | 056632B26230057 | 12.3 | 2 | 1085.65 | 697.33 | 21.09 | 367.23 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 18588351600 |  | 100459136 |  | 6740232M | 1745023 |  |  | 565 | EX | RPLC SL/17026708900/ | 2600B | PLEASANT | 329 PLEASANT ST | 017 | PAR | 2019-10-04 | U126603 | U131066 | 2018-02-19 | 2019-11-27 |  |  | SHAWN DENNIS | 2019-10-01 |  |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26290055 |  | 1 | 1404.51 | 0 | 0 | 0 | 1404.51 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026888000 |  |  |  | 6720204E | 1426400 | U122858 |  | 561 | EX | INSTALL 40'-2" PMMP | 2600B | GREENTREE | GREENTREE RD | 067 | LEX | 2019-11-14 | U128132 | U122858 | 2019-07-30 | 2019-09-25 | 2019-10-01 | 2019-09-25 | DEREK PAYTON | 2019-10-01 | 2019-08-03 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP8880 |  |  | 100 | 056132190268880 | 113.4 | 1846 | 44534.95 | 7127.49 | 2983.77 | 1654.32 | 28300.82 | 0 | 112.54 | 4356.01 | 142
KY | KY - WEST | 2621 | 19026888100 |  |  |  | 6720204E | 1426400 | U122858 |  | 562 | EX | RETIRE 40'-2" CSMP | 2600B | GREENTREE | GREENTREE RD | 067 | LEX | 2019-11-14 | U128132 | U122858 | 2019-07-30 | 2019-10-01 | 2019-10-01 | 2019-09-25 | DEREK PAYTON | 2019-10-01 | 2019-08-03 |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00562 | 3200562 |  |  | WP8881 |  |  | 100 | 056232190268881 | 40 | 0 | 18146.34 | 2308.99 | 0 | 885.87 | 14951.48 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19026891200 |  |  |  | 6720212E | 1965989 | U461383 |  | 557 | EX | INSTALL 20'OF 8"PMLP MAIN | 2600B | 5TH | 232 E 5TH ST | 067 | LEX | 2019-11-07 | U128132 | U461383 | 2019-08-19 | 2019-10-09 | 2019-10-15 | 2019-10-01 | JOSH PASLEY | 2019-10-01 | 2019-09-03 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP8912 | AMRCB |  | 100 | 055732190268912 | 126.9167 | 578 | 114420.23 | 8927.11 | 17047.17 | 1873.08 | 73671.84 | 0 | 491.83 | 12409.2 | 34
KY | KY - WEST | 2621 | 19026891300 |  |  |  | 6720212E | 1965989 | U461383 |  | 558 | EX | RETIRE 12' OF 12"BSLP MAIN | 2600B | 5TH | 232 E 5TH ST | 067 | LEX | 2019-10-17 | U128132 | U461383 | 2019-08-19 | 2019-10-15 | 2019-10-15 | 2019-10-01 | JOSH PASLEY | 2019-10-01 |  |  | B | 00032 | 10800011 | 0326210 | 0326210 | 00032 | 00558 | 3200558 |  |  | WP8913 | AMRCB |  | 100 | 055832190268913 |  | 0 | 6799.69 | 0 | 6739.59 | 0 | 60.1 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19026900400 |  |  |  | 6764176K | 1967049 | U128885 |  | 557 | EX | INSTALL 5' - 2" PMMP D096803 | 2621P | WOODSPOINT | WOODSPOINT DR | 065 | IRV | 2019-12-11 | U128132 | U128885 | 2019-09-30 |  | 2049-12-31 | 2019-10-01 | WDENNING | 2019-10-01 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP9004 |  |  | 100 | 055732190269004 |  | 5 | 12194.13 | 3565.37 | 345.07 | 1467.11 | 5408.66 | 0 | 11.62 | 1396.3 | 5
KY | KY - CENTRAL | 2629 | 19026900500 |  |  |  | 6764176K | 1967049 | U128885 |  | 558 | EX | RETIRE 5' - 2" PMP D096803 | 2621P | WOODSPOINT | WOODSPOINT DR | 065 | IRV | 2019-12-11 | U128132 | U128885 | 2019-09-30 |  | 2049-12-31 | 2019-10-01 | WDENNINGHOFF | 2019-10-01 |  |  | A | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00558 | 3200558 |  |  | WP9005 |  |  | 100 | 055832190269005 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 19026903300 |  |  |  | 7244216D | 1967433 | U132703 |  | 909 | EX | INSTALL ELECTRONIC EQUIP | 2600E | STEPSTONE | STEPSTONE RD | 173 | MT | 2020-04-15 | U462463 | U132703 | 2019-10-15 | 2019-12-31 | 2019-12-31 | 2019-10-01 | NOLL DAVIS | 2019-10-01 |  |  | F | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00909 | 3200909 |  |  | WP9033 |  |  | 100 | 090932190269033 |  | 0 | 4765.04 | 0 | 3165.43 | 0 | 1613.75 | 0 | -14.14 | 0
KY | KY - CENTRAL | 2629 | 19026903400 |  |  |  | 7244216D | 1967433 | U132703 |  | 910 | EX | RETIRE ELECTRONIC EQUIP | 2600E | STEPSTONE | STEPSTONE RD | 173 | MT | 2020-04-14 | U462463 | U132703 | 2019-10-15 | 2019-12-31 | 2019-12-31 | 2019-10-01 | NOLL DAVIS | 2019-10-01 |  |  | F | 00032 | 10800011 | 0326290 | 0326290 | 00032 | 00910 | 3200910 |  |  | WP9034 |  |  | 100 | 091032190269034 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19673605900 |  | 100312188 |  | 6716208E | 1636363 |  |  | 565 | EX | RPLC SL/17026733100/ | 2600B | CLAYS MILL | 2614 CLAYS MILL RD | 067 | LEX | 2019-10-01 | U461439 | U131066 | 2019-01-30 | 2019-11-27 |  |  | A PARRIS | 2019-10-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0032 |  |  | 100 | 056532B26210032 |  | 1 | 1976.65 | 0 | 239.23 | 0 | 1737.42 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19678785800 |  | 100299130 |  | 6716212B | 1855322 |  |  | 565 | EX | RPLC SL/18026792400/ | 2600B | LEESTOWN | 1473 LEESTOWN RD | 067 | LEX | 2019-10-01 | U126602 | U131066 | 2019-02-01 | 2019-11-27 |  |  | DEREK PAYTON | 2019-10-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 3022.91 | 0 | 0 | 0 | 3022.91 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19680085400 |  | 100320265 |  | 6716208G | 1748686 |  |  | 565 | EX | REPLACE SL W/17026736100 | 2600B | MCDONALD | 1844 MCDONALD AV | 067 | LEX | 2019-10-01 | U461516 | U131066 | 2019-02-07 | 2019-12-31 |  |  | NEAL JOHNSON | 2019-10-01 |  | 2019-10-01 | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 | 9.75 | 1 | 3648.38 | 571.75 | 0 | 175.3 | 2901.33 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687832400 |  | 100280070 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 308 WESTLAND DR | 073 | FRA | 2019-10-02 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-10-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1289.06 | 0 | 0 | 0 | 1289.06 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687832500 |  | 100280082 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 309 WESTLAND DR | 073 | FRA | 2019-10-02 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-10-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 3145.97 | 0 | 0 | 0 | 3145.97 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687832600 |  | 100280069 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 310 WESTLAND DR | 073 | FRA | 2019-10-02 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-10-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 2336.9 | 0 | 0 | 0 | 2336.9 | 0 | 0 | 0
KY | KY - WEST | 2623 | 19687832700 |  | 100280068 |  | 6688228N | 1853312 |  |  | 565 | EX | RPLC SL/18026776900/ | 2600B | WESTLAND | 312 WESTLAND DR | 073 | FRA | 2019-10-02 | U461375 | U131066 | 2019-03-13 | 2019-11-27 |  |  | LARRY BROWN | 2019-10-01 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26230055 |  | 1 | 1886.57 | 0 | 0 | 0 | 1886.57 | 0 | 0 | 0
KY | KY - WEST | 2621 | 19691671500 |  | 100326879 |  | 6720208A | 1855692 |  |  | 565 | EX | RPLC SL/18026796400/ | 2600B | FONTAINE | 1351 FONTAINE RD | 067 | LEX | 2019-10-01 | U125559 | U131066 | 2019-03-27 | 2019-11-27 |  |  | BJACKSON | 2019-10-01 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00565 | 3200565 |  |  | WP0055 | AMRSL |  | 100 | 056532B26210055 |  | 1 | 2818.64 | 0 | 0 | 0 | 2818.64 | 0 | 0 | 0