## Sheet1
Farm Tap Main Extension
Erlanger, KY
Project Cost Breakdown
Erlanger
2026-10-16
|  | Capital Improvement |  |  | Retirement | Cabin Creek | Upper Tug Fork | Poplar Ridge | Carthage | Gubser Mill Wagoner | Gubser Mill Daniels | Pendleton | Pendleton HP Station
|  | Size / Name | 8"/6" Steel, 1 HDD | Actuals Spent | 4" Steel | 2 INCH PL | 4 INCH PL | 4 & 6 INCH PL | 4 & 6 INCH PL | 4 INCH PL | 4 INCH PL | 2 & 4 INCH PL | N/A |  | Pipe length
|  | Length (LF) | 9,839 LF | Sunk Cost from Scope Change | 1,500 LF | 2350 | 1575 | 1,100 & 3,100 | 4,100 & 12,350 | 11250 | 14400 | 14,100 & 14,500 | N/A | 2350 | 2350 | 0.029809 | 0.029809 | 0.028058
|  | Services |  |  |  | 1 | 1 | 1 | 4 | 6 | 3 | 11 |  | 1575 | 1575 | 0.019978 | 0.019978 | 0.018805
WBS 1 | Description | Total | Pipelay 1 | Actuals Spent | Pipe Abandon 1 | [8 empty] | 1100 |  | 0.053276 | 0.053276 | 0.050145
NGENGNC | Engineering | 1380900 | 792900 | 380100 | 7500 | 38744.619 | 25967.1383 | 69245.7021 | 271377.2041 | 185479.5593 | 237413.8359 | 471530.2573 | 81141.684 | 3100 | 4200 |  | 0.20879 | 0.19652
NGLANDC | Land - Permanent | 250000 | 985800 | 0 | 0 | 7005.1373 | 4694.9325 | 12519.8199 | 49065.7703 | 33535.2318 | 42925.0967 | 85254.0115 | 15000 | 4100 |  | 0.20879 | 0.1427 | 0.13432
NGLANDC | Land - Temporary | 293675 | 83900 | 221500 | 0 | 8228.9348 | 5515.1372 | 14707.0324 | 57637.5603 | 39393.8368 | 50424.1111 | 100147.8874 | 17620.5 | 12360 | 16460 |  | 0.18266 | 0.17193
NGLANDC | Land - Support | 60500 | 60500 | 0 | 0 | 1695.2432 | 1136.1737 | 3029.7964 | 11873.9164 | 8115.5261 | 10387.8734 | 20631.4708 | 3630 | 11250 | 11250 | 0.1427 | 0.36278 | 0.34147
NGLANDC | Land Legal | 60000 | 60000 | 0 | 0 | 1681.233 | 1126.7838 | 3004.7568 | 11775.7849 | 8048.4556 | 10302.0232 | 20460.9628 | 3600 | 14400 | 14400 | 0.18266
NGMATEC | Materials/Equipment | 690486 | 564200 | 57500 | 6200 | 19347.797 | 12967.1405 | 34579.0414 | 135516.9098 | 92622.4323 | 118556.7133 | 235466.8057 | 41429.16 | 14100 |  | 0.36278
NGCONPC | Construction Serv - Pipeline | 7769300 | 7067000 | 0 | 86500 | 231595.8014 | 155218.4626 | 413915.9003 | 1622156.1235 | 1108703.3044 | 1419140.2296 | 2818570.1782 | - | 14500 | 28600
NGCONFC | Construction Serv - Facility | 485000 | 0 | 0 | 0 | - | - | - | - | - | - | - | 485000 | 78835 | 78835 | 1
NGFITSC | Field Inspections | 1009836 | 961900 | 0 | 10400 | 28296.1594 | 18964.4472 | 50571.8593 | 198193.5248 | 135460.3374 | 173389.2319 | 344370.28 | 60590.16
NGFITSC | Field Testing | 112204 | 106100 | 0 | 0 | 3144.0177 | 2107.1608 | 5619.0955 | 22021.5028 | 15051.1486 | 19265.4702 | 38263.3644 | 6732.24
NGMPGL | Duke Energy Labor | 700000 | 597000 | 81000 | 87500 | 19614.3845 | 13145.8109 | 35055.4957 | 137384.1568 | 93898.6491 | 120190.2708 | 238711.2323 | 42000
NGMOTH | Other Direct Costs | 64700 | 60200 | 4500 | 8800 | 1812.9295 | 1215.0485 | 3240.1294 | 12698.2213 | 8678.918 | 11109.015 | 22063.7382 | 3882
Subtotal Direct Cost |  | 12876601 | 11339500 | 744600 | 206900 | 361166.2568 | 242058.2359 | 645488.6291 | 2529700.675 | 1728987.3994 | 2213103.8712 | 4395470.1886 | 760625.744
| Project Contingency | 1718000 | 1728000 | 0 | 31500 | 48202.9472 | 32306.2305 | 86149.9481 | 337625.749 | 230758.7896 | 295371.2507 | 586640.1229 | 100944.962
| Project Escalation | 150000 | 492100 | 18700 | 7800 | 4208.6392 | 2820.6837 | 7521.8232 | 29478.3832 | 20147.7407 | 25789.108 | 51220.034 | 8813.5881
Total Contingency & Escalation |  | 1868000 | 2220100 | 18700 | 39300 | 52411.5863 | 35126.9142 | 93671.7713 | 367104.1322 | 250906.5302 | 321160.3587 | 637860.1569 | 109758.5501
Total Direct Cost |  | 14744601 | 13559600 | 763300 | 246200 | 413577.8431 | 277185.1501 | 739160.4004 | 2896804.8072 | 1979893.9296 | 2534264.2299 | 5033330.3455 | 870384.2941
NGMAFD | AFUDC Debt | 373974 | 388500 | 97200 | 0 | 10492.8108 | 7032.4158 | 18753.1087 | 73494.3259 | 50231.5411 | 64296.3726 | 127699.74 | 21973.6852
NGMOVH | Overhead and Allocations | 2182175.77 | 1819100 | 146700 | #REF! | 61226.6026 | 41034.8507 | 109426.2685 | 428846.7572 | 293106.0765 | 375175.7779 | 745140.781 | 128218.6555
Total Duke Energy Overhead Cost |  | 2556149.77 | 2207600 | 243900 | #REF! | 71719.4134 | 48067.2665 | 128179.3772 | 502341.0831 | 343337.6175 | 439472.1505 | 872840.521 | 150192.3408
Project Total |  | 17300750.77 | 15767200 | 1007200 | #REF! | 485297.2565 | 325252.4166 | 867339.7776 | 3399145.8903 | 2323231.5472 | 2973736.3804 | 5906170.8666 | 1020576.6349
Cost per Customer |  | N/A |  |  |  | 485297.2565 | 325252.4166 | 867339.7776 | 849786.4726 | 387205.2579 | 991245.4601 | 629704.3183
[11 empty] | 7769300 | 0.94124
[11 empty] | 485000 | 0.058757