## 2026 DR-CPCN
cost center | Town | Length (ft) | Length (mi) | In-Service Date | Outside Diameter | MAOP | % SMYS at MAOP | Consequence Area Type | Consequence Number: | Proposed MAOP Reconfirmation Method | Forecast Reconfirmation (Fiscal Year) | Current Estimated Capital Cost | Cumulative Miles Completed | % Complete | * Bowling Green Removed from 624 Replacement Schedule Per Robert Arnold Email 2/18/2026
8502 | Barnsley | 4788 | 0.90682 | 1992-11-01 | 8.625 | 900 | 28.7% | HCA | HCA 9 | Pressure Test | 2022 | Complete | 0.90682 | 3.96%
8502 | Barnsley | 6138 | 1.1625 | 1965-01-01 | 4.5 | 900 | 30.8% | HCA | HCA10 | Pressure Test | 2022 | Complete | 2.0693 | 9.036%
8502 | Barnsley | 993 | 0.18807 | 1965-01-01 | 3.5 | 900 | 20.8% | N/A | N/A | Pressure Test | 2022 | Complete | 2.2574 | 9.858%
2609 | St. Charles | 10032 | 1.9 | 1968-12-31 | 8.625 | 850 | 46.4% | N/A | N/A | Pressure Reduction | 2023 | Complete | 4.1574 | 18.15%
| Murfreesboro | 10695 | 2.0256 | 1997-10-07 | 8.625 | 550 | 30% | HCA |  | Pipe Replacement | 2025 | Complete | 6.183 | 27%
2636 | Hawesville | 206 | 0.039015 | 1969-07-25 | 6.625 | 594 | 43.6% | N/A | N/A | Pipe Replacement | 2025 | Complete | 6.222 | 27.17%
2636 | Hawesville | 5916 | 1.1205 | 1968-07-16 | 8.625 | 594 | 56.8% | N/A | N/A | Pressure Reduction | 2025 | Complete | 7.3424 | 32.06%
2636 | Hawesville | 5649.6 | 1.07 | 1964-12-05 | 6.625 | 594 | 29.9% | N/A | N/A | Pipe Replacement | 2026 | In Progress | 8.4124 | 36.74%
2634 | Madisonville | 6142 | 1.1633 |  | 6.625 | 594 | 43.6% | MCA | KY_51 | Pipe Replacement | 2026 | In Progress | 9.5757 | 41.82%
2634 | Madisonville | 4699 | 0.88996 | 1955-11-25 | 6.625 | 425 | 23.5% | N/A | N/A | Pipe Replacement | 2026 | Complete | 10.4656 | 45.7%
| Hawesville | 5322 | 1.008 | 1966-11-15 | 6.625 | 500 | 36.7% | N/A | N/A | Pipe Replacement | 2027 | 2511740 | 11.4736 | 50.1%
2609 | Bon Harbor | 2202 | 0.41705 | 1964-08-01 | 6.625* | 529 | 38.8%** | N/A | N/A | Pipe Replacement | 2027 | 935802 | 11.8906 | 51.92%
2637 | Paducah | 20333 | 3.8509 | 1954-11-14 | 8.625 | 395 | 28.39% | N/A | KY_84 | Pipe Replacement | 2028 |  | 15.7416 | 68.74%
2637 | Paducah | 11508 | 2.1795 | 1969-12-04 | 8.625 | 395 | 37.8% | N/A | N/A | Pipe Replacement | 2029 |  | 17.9211 | 78.26%
2637 | Paducah | 5185 | 0.98201 | 1958-09-16 | 8.625 | 395 | 37.8% | N/A | KY_83 | Pipe Replacement | 2030 |  | 18.9031 | 82.55%
2637 | Paducah | 3860 | 0.73106 | 1956-09-04 | 8.625 | 395 | 37.8% | N/A | N/A | Pipe Replacement | 2030 |  | 19.6342 | 85.74%
2637 | Paducah | 16558 | 3.136 | 1959-10-12 | 8.625 | 395 | 37.8% | N/A | N/A | Pipe Replacement | 2031 |  | 22.7702 | 99.43%
2637 | Paducah | 667 | 0.12633 | 1970-07-13 | 6.625 | 395 | 29% | MCA | KY_82 | Pipe Replacement | 2032 |  | 22.8965 | 99.98%
|  | 22.8965 | 0.0043365 | [9 empty] | 22.9009 | #DIV/0!
Template |  | 24.306 | 0.0046034 | 12.153 | [8 empty] | 22.9055 | #DIV/0!
F22 |  | 2.2574 | 0.00042754 | 22.0486 | 2.2574 | 9.859% | [6 empty] | 22.9059 | #DIV/0!
F23 |  | 1.9 | 0.00035985 | 20.1486 | 4.1574 | 18.16% | [6 empty] | 22.9062 | #DIV/0!
F24 |  | 2.2295 | 0.00042226 | 17.9191 | 6.3869 | 27.89% | [6 empty] | 22.9067 | #DIV/0!
F25 |  | 3.1888 | 0.00060394 | 14.7302 | 9.5758 | 41.82% | [6 empty] | 22.9073 | #DIV/0!
F26 |  | 0.88996 | 0.00016855 | 13.8403 | 10.4657 | 43.06% | [6 empty] | 22.9074 | #DIV/0!
F27 |  | 3.8509 | 0.00072935 | 9.9893 | 14.3167 | 62.53% | [6 empty] | 22.9082 | #DIV/0!
F28 |  | 1.008 | 0.0001909 | 8.9814 | 15.3246 | 66.93% | [6 empty] | 22.9084 | #DIV/0!
F29 |  | 2.04 | 0.00038636 | 6.9414 | 17.3646 | 75.84% | [6 empty] | 22.9087 | #DIV/0!
F30 |  | 1.683 | 0.00031874 | 5.2585 | 19.0475 | 83.19% | [6 empty] | 22.9091 | #DIV/0!
F31 |  | 1.7131 | 0.00032444 | 3.5454 | 20.7606 | 90.67% | [6 empty] | 22.9094 | #DIV/0!
F32 |  | 0.41705 | 7.8986e-05 | 3.1283 | 21.1777 | 92.49% | [6 empty] | 22.9095 | #DIV/0!
F33 |  | 3.1282 | 0.00059247 | 0.00012879 | 24.3059 | 106.2% | [6 empty] | 22.9101 | #DIV/0!
2035-07-02
* Bon Harbor Field Lines consist of 3 separate pipe sizes with different outside diameters. For calculations of SMYS, 6" Nominal Pipe Size was utililzed
** Reference Material Specification Spreadsheet for breakout of pipe characteristics

## 26 template 03062026
cost center | Town | Length (ft) | Length (mi) | In-Service Date | Outside Diameter | MAOP | % SMYS at MAOP | Consequence Area Type | Consequence Number: | Proposed MAOP Reconfirmation Method | Forecast Reconfirmation (Fiscal Year) | Current Estimated Capital Cost | Cumulative Miles Completed | % Complete |  | * Bowling Green Removed from 624 Replacement Schedule Per Robert Arnold Email 2/18/2026
8502 | Barnsley | 4788 | 0.90682 | 1992-11-01 | 8.625 | 900 | 28.7% | HCA | HCA 9 | Pressure Test | 2022 |  | 0.90682 | 3.96%
8502 | Barnsley | 6138 | 1.1625 | 1965-01-01 | 4.5 | 900 | 30.8% | HCA | HCA10 | Pressure Test | 2022 |  | 2.0693 | 9.036%
8502 | Barnsley | 993 | 0.18807 | 1965-01-01 | 3.5 | 900 | 20.8% | N/A | N/A | Pressure Test | 2022 |  | 2.2574 | 9.858%
2609 | St. Charles | 10032 | 1.9 | 1968-12-31 | 8.625 | 850 | 46.4% | N/A | N/A | Pressure Reduction | 2023 |  | 4.1574 | 18.15%
| Murfreesboro | 10695 | 2.0256 | 1997-10-07 | 8.625 | 550 | 30% | HCA |  | Pipe Replacement | 2025 |  | 6.183 | 27%
2636 | Hawesville | 206 | 0.039015 | 1969-07-25 | 6.625 | 594 | 43.6% | N/A | N/A | Pipe Replacement | 2025 | 2677220 | 6.222 | 27.17%
2636 | Hawesville | 5916 | 1.1205 | 1968-07-16 | 8.625 | 594 | 56.8% | N/A | N/A | Pressure Reduction | 2025 |  | 7.3424 | 32.06%
2636 | Hawesville | 5649.6 | 1.07 | 1964-12-05 | 6.625 | 594 | 29.9% | N/A | N/A | Pipe Replacement | 2026 | 2064546 | 8.4124 | 36.74%
2634 | Madisonville | 6142 | 1.1633 |  | 6.625 | 594 | 43.6% | MCA | KY_51 | Pipe Replacement | 2026 | 2456257 | 9.5757 | 41.82%
2634 | Madisonville | 4699 | 0.88996 | 1955-11-25 | 6.625 | 425 | 23.5% | N/A | N/A | Pipe Replacement | 2026 | 1603894 | 10.4656 | 45.7%
| Hawesville | 5322 | 1.008 | 1966-11-15 | 6.625 | 500 | 36.7% | N/A | N/A | Pipe Replacement | 2027 | 2270348 | 11.4736 | 50.1% | <--- Will be 50% complete in FY27
2609 | Bon Harbor | 2202 | 0.41705 | 1964-08-01 | 6.625 | 529 | 38.8% | N/A | N/A | Pipe Replacement | 2027 | 849075 | 11.8906 | 51.92%
2637 | Paducah | 20333 | 3.8509 | 1954-11-14 | 8.625 | 395 | 28.39% | N/A | KY_84 | Pipe Replacement | 2028 | 8410312 | 15.7416 | 68.74%
2637 | Paducah | 11508 | 2.1795 | 1969-12-04 | 8.625 | 395 | 37.8% | N/A | N/A | Pipe Replacement | 2029 |  | 17.9211 | 78.26%
2637 | Paducah | 5185 | 0.98201 | 1958-09-16 | 8.625 | 395 | 37.8% | N/A | KY_83 | Pipe Replacement | 2030 |  | 18.9031 | 82.55%
2637 | Paducah | 3860 | 0.73106 | 1956-09-04 | 8.625 | 395 | 37.8% | N/A | N/A | Pipe Replacement | 2030 |  | 19.6342 | 85.74%
2637 | Paducah | 16558 | 3.136 | 1959-10-12 | 8.625 | 395 | 37.8% | N/A | N/A | Pipe Replacement | 2031 |  | 22.7702 | 99.43%
2637 | Paducah | 667 | 0.12633 | 1970-07-13 | 6.625 | 395 | 29% | MCA | KY_82 | Pipe Replacement | 2032 |  | 22.8965 | 99.98% | <--- Need to be finished by July 1 2035
|  | 22.8965 | 0.0043365 | [9 empty] | 22.9009 | #DIV/0!
Template |  | 24.306 | 0.0046034 | 12.153 | [8 empty] | 22.9055 | #DIV/0!
F22 |  | 2.2574 | 0.00042754 | 22.0486 | 2.2574 | 9.859% | [6 empty] | 22.9059 | #DIV/0!
F23 |  | 1.9 | 0.00035985 | 20.1486 | 4.1574 | 18.16% | [6 empty] | 22.9062 | #DIV/0!
F24 |  | 2.2295 | 0.00042226 | 17.9191 | 6.3869 | 27.89% | [6 empty] | 22.9067 | #DIV/0!
F25 |  | 3.1888 | 0.00060394 | 14.7302 | 9.5758 | 41.82% | [6 empty] | 22.9073 | #DIV/0!
F26 |  | 0.88996 | 0.00016855 | 13.8403 | 10.4657 | 43.06% | [6 empty] | 22.9074 | #DIV/0!
F27 |  | 3.8509 | 0.00072935 | 9.9893 | 14.3167 | 62.53% | [6 empty] | 22.9082 | #DIV/0!
F28 |  | 1.008 | 0.0001909 | 8.9814 | 15.3246 | 66.93% | [6 empty] | 22.9084 | #DIV/0!
F29 |  | 2.04 | 0.00038636 | 6.9414 | 17.3646 | 75.84% | [6 empty] | 22.9087 | #DIV/0!
F30 |  | 1.683 | 0.00031874 | 5.2585 | 19.0475 | 83.19% | [6 empty] | 22.9091 | #DIV/0!
F31 |  | 1.7131 | 0.00032444 | 3.5454 | 20.7606 | 90.67% | [6 empty] | 22.9094 | #DIV/0!
F32 |  | 0.41705 | 7.8986e-05 | 3.1283 | 21.1777 | 92.49% | [6 empty] | 22.9095 | #DIV/0!
F33 |  | 3.1282 | 0.00059247 | 0.00012879 | 24.3059 | 106.2% | [6 empty] | 22.9101 | #DIV/0!
F34
2035-07-02
Note on I1: Choices: High Consequence Medium Consequence None
Note on J1: If a Consequence Area is noted, please list the corresponding number or identifier?
Note on K1: Choices: Pressure Test Pressure Reduction Engineering Critical Assessment Pipe Replacement PIR Reduction (PIR<150') Alternative Technology
Note on L1: Proposed Year for Reconformation: FY2021 - FY2035 (Note: 50% must be accomplished by July 3, 2028)
Note on G5: Robert H Arnold: lowered from 920 to 850
Note on C13: Robert H Arnold: 8:, 6", and 4"

## 24 template 08272024
cost center | Town | Length (ft) | Length (mi) | In-Service Date | Outside Diameter | MAOP | % SMYS at MAOP | Consequence Area Type | Consequence Number: | Proposed MAOP Reconfirmation Method | Forecast Reconfirmation (Fiscal Year) | Current Estimated Capital Cost | Cumulative Miles Completed | % Complete
8502 | Barnsley | 4788 | 0.90682 | 1992-11-01 | 8.625 | 900 | 28.7% | HCA | HCA 9 | Pressure Test | 2022 |  | 0.90682 | 4.066%
8502 | Barnsley | 6138 | 1.1625 | 1965-01-01 | 4.5 | 900 | 30.8% | HCA | HCA10 | Pressure Test | 2022 |  | 2.0693 | 9.279%
8502 | Barnsley | 993 | 0.18807 | 1965-01-01 | 3.5 | 900 | 20.8% | N/A | N/A | Pressure Test | 2022 |  | 2.2574 | 10.12%
2609 | St. Charles | 10032 | 1.9 | 1968-12-31 | 8.625 | 850 | 46.4% | N/A | N/A | Pressure Reduction | 2023 |  | 4.1574 | 18.64%
| Murfreesboro | 10695 | 2.0256 | 1997-10-07 | 8.625 | 550 | 30% | HCA |  | Pipe Replacement | 2025 |  | 6.183 | 27.73%
2636 | Hawesville | 206 | 0.039015 | 1969-07-25 | 6.625 | 594 | 43.6% | N/A | N/A | Pipe Replacement | 2025 | 2677220 | 6.222 | 27.9%
2636 | Hawesville | 5916 | 1.1205 | 1968-07-16 | 8.625 | 594 | 56.8% | N/A | N/A | Pressure Reduction | 2025 |  | 7.3424 | 32.93%
2636 | Hawesville | 5649.6 | 1.07 | 1964-12-05 | 6.625 | 594 | 29.9% | N/A | N/A | Pipe Replacement | 2026 | 2064546 | 8.4124 | 37.72%
2634 | Madisonville | 6142 | 1.1633 |  | 6.625 | 594 | 43.6% | MCA | KY_51 | Pipe Replacement | 2026 | 2456257 | 9.5757 | 42.94%
2634 | Madisonville | 4699 | 0.88996 | 1955-11-25 | 6.625 | 425 | 23.5% | N/A | N/A | Pipe Replacement | 2026 | 1603894 | 10.4656 | 46.93%
| Hawesville | 5322 | 1.008 | 1966-11-15 | 6.625 | 500 | 36.7% | N/A | N/A | Pipe Replacement | 2027 | 2270348 | 11.4736 | 51.45% | <--- Will be 50% complete in FY27
2609 | Bon Harbor | 2202 | 0.41705 | 1964-08-01 | 6.625 | 529 | 38.8% | N/A | N/A | Pipe Replacement | 2027 | 849075 | 11.8906 | 53.32%
2734 | Bowling Green |  | 0 | 1995-02-24 | 8.625 | 814 | 44.5% | N/A | N/A | Pipe Replacement | 2028 | 5022910 | 11.8906 | 53.32% | <--- Need to be finished by July 1 2028
2637 | Paducah | 20333 | 3.8509 | 1954-11-14 | 8.625 | 395 | 28.39% | N/A | KY_84 | Pipe Replacement | 2029 | 8410312 | 15.7416 | 70.59%
2637 | Paducah | 8886 | 1.683 | 1969-12-04 | 8.625 | 395 | 37.8% | N/A | N/A | Pipe Replacement | 2030 |  | 17.4245 | 78.14% | Combine to 2030?
2637 | Paducah | 5185 | 0.98201 | 1958-09-16 | 8.625 | 395 | 37.8% | N/A | KY_83 | Pipe Replacement | 2031 |  | 18.4066 | 82.54%
2637 | Paducah | 3860 | 0.73106 | 1956-09-04 | 8.625 | 395 | 37.8% | N/A | N/A | Pipe Replacement | 2031 |  | 19.1376 | 85.82%
2637 | Paducah | 15850 | 3.0019 | 1959-10-12 | 8.625 | 395 | 37.8% | N/A | N/A | Pipe Replacement | 2032 |  | 22.1395 | 99.28%
2637 | Paducah | 667 | 0.12633 | 1970-07-13 | 6.625 | 395 | 29% | MCA | KY_82 | Pipe Replacement | 2033 |  | 22.2658 | 99.85% | <--- Need to be finished by July 1 2035
|  | 22.2658 | 0.004217 | [9 empty] | 22.2701
Template |  | 24.306 | 0.0046034 | 12.153 | [8 empty] | 22.2747
F22 |  | 2.2574 | 0.00042754 | 22.0486 | 2.2574 | 10.14% | [6 empty] | 22.2751
F23 |  | 1.9 | 0.00035985 | 20.1486 | 4.1574 | 18.67% | [6 empty] | 22.2754
F24 |  | 2.2295 | 0.00042226 | 17.9191 | 6.3869 | 28.68% | [6 empty] | 22.2759
F25 |  | 3.1888 | 0.00060394 | 14.7302 | 9.5758 | 43.01% | [6 empty] | 22.2765
F26 |  | 0.88996 | 0.00016855 | 13.8403 | 10.4657 | 43.06% | [6 empty] | 22.2766
F27 |  | 3.8509 | 0.00072935 | 9.9893 | 14.3167 | 64.3% | [6 empty] | 22.2774
F28 |  | 1.008 | 0.0001909 | 8.9814 | 15.3246 | 68.83% | [6 empty] | 22.2776
F29 |  | 2.04 | 0.00038636 | 6.9414 | 17.3646 | 77.99% | [6 empty] | 22.2779
F30 |  | 1.683 | 0.00031874 | 5.2585 | 19.0475 | 85.55% | [6 empty] | 22.2783
F31 |  | 1.7131 | 0.00032444 | 3.5454 | 20.7606 | 93.24% | [6 empty] | 22.2786
F32 |  | 0.41705 | 7.8986e-05 | 3.1283 | 21.1777 | 95.11% | [6 empty] | 22.2787
F33 |  | 3.1282 | 0.00059247 | 0.00012879 | 24.3059 | 109.2% | [6 empty] | 22.2793
F34
2035-07-02
10771
Note on I1: Choices: High Consequence Medium Consequence None
Note on J1: If a Consequence Area is noted, please list the corresponding number or identifier?
Note on K1: Choices: Pressure Test Pressure Reduction Engineering Critical Assessment Pipe Replacement PIR Reduction (PIR<150') Alternative Technology
Note on L1: Proposed Year for Reconformation: FY2021 - FY2035 (Note: 50% must be accomplished by July 3, 2028)
Note on G5: Robert H Arnold: lowered from 920 to 850
Note on C13: Robert H Arnold: 8:, 6", and 4"

## 5 year plan slides
2021-2028 Remediation
# Segments | 13
#HCA | 3
Total Miles | 13.9
2029-2035 Remediation
# Segments | 6
#HCA | 0
Total Miles | 10.4
Forecast of Work for each FY | FY25 | FY26P | FY27P | FY28P | FY29P | FY30P
Hydro | 0 | 0 | 0 | 0 | 0 | 0 | *Could probably remove Hydro row if wanted
MAOP Derate | 1.2 | 0 | 0 | 0 | 0 | 0
Pipeline Replacement | 3.2 | 3.1 | 1.4 | 2 | 3.9 | 1.7
| FY | % Complete
| 22 | 9.29
| 23 | 17.1
| 24 | 17.1
| 25 | 30.21
| 26 | 43.06
| 27 | 48.92
| 28 | 57.31
| 29 | 73.16
| 30 | 80.08
| 31 | 87.13
| 32 | 99.48
| 33 | 100
34
35